## Sheet1
PUB_DATE | BORO | MANAGING_AGCY_CD | MANAGING_AGCY | PROJECT_ID | PROJECT_DESCR | SEQ_NUMBER | TASK_DESCRIPTION | ORIG_START_DATE | ORIG_END_DATE | TASK_START_DATE | TASK_END_DATE
20201123 | CITYWIDE | 042 | CITY UNIVERSITY | CA202-006 | ADA Compliance | 4 | BID AWARD AND REGISTER CONTRCT | 2006-06-24 | 2006-09-21 | 2006-06-24 | 2006-09-21
20201123 | CITYWIDE | 042 | CITY UNIVERSITY | CA202-006 | ADA Compliance | 5 | CONSTRUCTION TO 25% | 2006-09-22 | 2007-01-19 | 2006-09-22 | 2007-01-19
20201123 | CITYWIDE | 042 | CITY UNIVERSITY | CA202-006 | ADA Compliance | 6 | CONSTRUCTION TO 50% | 2007-01-20 | 2007-05-19 | 2007-01-20 | 2007-05-19
20201123 | CITYWIDE | 042 | CITY UNIVERSITY | CA202-006 | ADA Compliance | 7 | CONSTRUCTION TO 75% | 2007-05-20 | 2007-09-16 | 2007-05-20 | 2007-09-16
20201123 | CITYWIDE | 042 | CITY UNIVERSITY | CA202-006 | ADA Compliance | 8 | ORIGINAL EQUIP & FURNISHING | 2007-09-17 | 2007-12-15 | 2007-09-17 | 2007-12-15
20201123 | CITYWIDE | 042 | CITY UNIVERSITY | CA202-006 | ADA Compliance | 9 | SUBSTANTIAL COMPLETION | 2007-12-16 | 2008-02-13 | 2007-12-16 | 2008-02-13
20201123 | CITYWIDE | 042 | CITY UNIVERSITY | CA202-006 | ADA Compliance | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-02-14 | 2008-03-14 | 2008-02-14 | 2008-03-14
20201123 | CITYWIDE | 042 | CITY UNIVERSITY | CA207-006 | CUNY Incubator Network | 1 | DEVELOP SCOPE | 2009-05-30 | 2009-08-27 | 2021-07-01 | 2021-09-28
20201123 | CITYWIDE | 042 | CITY UNIVERSITY | CA207-006 | CUNY Incubator Network | 2 | PRELIMINARY DESIGN | 2009-08-28 | 2009-12-25 | 2021-09-29 | 2022-01-26
20201123 | CITYWIDE | 042 | CITY UNIVERSITY | CA207-006 | CUNY Incubator Network | 3 | FINAL DESIGN | 2009-12-26 | 2010-06-23 | 2022-01-27 | 2022-07-25
20201123 | CITYWIDE | 042 | CITY UNIVERSITY | CA207-006 | CUNY Incubator Network | 4 | BID AWARD AND REGISTER CONTRCT | 2010-06-24 | 2010-09-21 | 2022-07-26 | 2022-10-23
20201123 | CITYWIDE | 042 | CITY UNIVERSITY | CA207-006 | CUNY Incubator Network | 5 | CONSTRUCTION TO 25% | 2010-09-22 | 2011-01-19 | 2022-10-24 | 2023-02-20
20201123 | CITYWIDE | 042 | CITY UNIVERSITY | CA207-006 | CUNY Incubator Network | 6 | CONSTRUCTION TO 50% | 2011-01-20 | 2011-05-19 | 2023-02-21 | 2023-06-20
20201123 | CITYWIDE | 042 | CITY UNIVERSITY | CA207-006 | CUNY Incubator Network | 7 | CONSTRUCTION TO 75% | 2011-05-20 | 2011-09-16 | 2023-06-21 | 2023-10-18
20201123 | CITYWIDE | 042 | CITY UNIVERSITY | CA207-006 | CUNY Incubator Network | 8 | ORIGINAL EQUIP & FURNISHING | 2011-09-17 | 2011-12-15 | 2023-10-19 | 2024-01-16
20201123 | CITYWIDE | 042 | CITY UNIVERSITY | CA207-006 | CUNY Incubator Network | 9 | SUBSTANTIAL COMPLETION | 2011-12-16 | 2012-02-13 | 2024-01-17 | 2024-03-16
20201123 | CITYWIDE | 042 | CITY UNIVERSITY | CA207-006 | CUNY Incubator Network | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-02-14 | 2012-03-14 | 2024-03-17 | 2025-08-02
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79-ADA | ADA COMPLIANCE RENOVATIONS AT NYPD PRECINCTS | 1 | DESIGN | 2020-07-30 | 2021-01-25 | 2020-07-30 | 2021-01-25
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79-ADA | ADA COMPLIANCE RENOVATIONS AT NYPD PRECINCTS | 2 | BID AWARD AND REGISTER CONTRCT | 2021-01-26 | 2021-04-25 | 2021-01-26 | 2021-04-25
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79-ADA | ADA COMPLIANCE RENOVATIONS AT NYPD PRECINCTS | 3 | CONSTRUCTION | 2021-04-26 | 2022-04-25 | 2021-04-26 | 2022-04-25
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79-ADA | ADA COMPLIANCE RENOVATIONS AT NYPD PRECINCTS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-04-26 | 2022-10-22 | 2022-04-26 | 2022-10-22
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BATH | CITYWIDE BATHROOM RENOVATION | 1 | DEVELOP SCOPE | 2015-02-10 | 2015-05-10 | 2015-02-10 | 2015-05-10
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BATH | CITYWIDE BATHROOM RENOVATION | 2 | PRELIMINARY DESIGN | 2015-05-11 | 2015-09-07 | 2015-05-11 | 2015-09-07
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BATH | CITYWIDE BATHROOM RENOVATION | 3 | FINAL DESIGN | 2015-09-08 | 2016-03-05 | 2015-09-08 | 2016-03-05
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BATH | CITYWIDE BATHROOM RENOVATION | 4 | BID AWARD AND REGISTER CONTRCT | 2016-03-06 | 2016-06-03 | 2016-03-06 | 2016-06-03
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BATH | CITYWIDE BATHROOM RENOVATION | 5 | CONSTRUCTION TO 25% | 2016-06-04 | 2016-10-01 | 2016-06-04 | 2016-10-01
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BATH | CITYWIDE BATHROOM RENOVATION | 6 | CONSTRUCTION TO 50% | 2016-10-02 | 2017-01-29 | 2016-10-02 | 2017-01-29
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BATH | CITYWIDE BATHROOM RENOVATION | 7 | CONSTRUCTION TO 75% | 2017-01-30 | 2017-05-29 | 2017-01-30 | 2024-05-29
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BATH | CITYWIDE BATHROOM RENOVATION | 8 | ORIGINAL EQUIP & FURNISHING | 2017-05-30 | 2017-08-27 | 2024-05-30 | 2024-08-27
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BATH | CITYWIDE BATHROOM RENOVATION | 9 | SUBSTANTIAL COMPLETION | 2017-08-28 | 2017-10-26 | 2024-08-28 | 2024-10-26
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BATH | CITYWIDE BATHROOM RENOVATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-10-27 | 2017-11-25 | 2024-10-27 | 2024-11-25
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAHD | BATHROOM RENO AT 67TH, 77TH AND TRAFFIC CONTROL DIVISION | 1 | DEVELOP SCOPE | 2014-06-30 | 2014-09-27 | 2014-06-30 | 2014-09-27
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAHD | BATHROOM RENO AT 67TH, 77TH AND TRAFFIC CONTROL DIVISION | 2 | PRELIMINARY DESIGN | 2014-09-28 | 2015-01-25 | 2014-09-28 | 2015-01-25
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAHD | BATHROOM RENO AT 67TH, 77TH AND TRAFFIC CONTROL DIVISION | 3 | FINAL DESIGN | 2015-01-26 | 2015-07-24 | 2015-01-26 | 2015-07-24
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAHD | BATHROOM RENO AT 67TH, 77TH AND TRAFFIC CONTROL DIVISION | 4 | BID AWARD AND REGISTER CONTRCT | 2015-07-25 | 2015-10-22 | 2015-07-25 | 2015-10-22
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAHD | BATHROOM RENO AT 67TH, 77TH AND TRAFFIC CONTROL DIVISION | 5 | CONSTRUCTION TO 25% | 2015-10-23 | 2016-02-19 | 2015-10-23 | 2016-02-19
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAHD | BATHROOM RENO AT 67TH, 77TH AND TRAFFIC CONTROL DIVISION | 6 | CONSTRUCTION TO 50% | 2016-02-20 | 2016-06-18 | 2016-02-20 | 2016-06-18
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAHD | BATHROOM RENO AT 67TH, 77TH AND TRAFFIC CONTROL DIVISION | 7 | CONSTRUCTION TO 75% | 2016-06-19 | 2016-10-16 | 2016-06-19 | 2021-10-16
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAHD | BATHROOM RENO AT 67TH, 77TH AND TRAFFIC CONTROL DIVISION | 8 | ORIGINAL EQUIP & FURNISHING | 2016-10-17 | 2017-01-14 | 2021-10-17 | 2022-01-14
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAHD | BATHROOM RENO AT 67TH, 77TH AND TRAFFIC CONTROL DIVISION | 9 | SUBSTANTIAL COMPLETION | 2017-01-15 | 2017-03-15 | 2022-01-15 | 2022-03-15
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAHD | BATHROOM RENO AT 67TH, 77TH AND TRAFFIC CONTROL DIVISION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-16 | 2017-04-14 | 2022-03-16 | 2022-04-14
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAHG | ELEVATOR REHABILITATION FOR 20TH, 25TH | 9 | SUBSTANTIAL COMPLETION | 2017-01-15 | 2017-03-15 | 2021-01-15 | 2021-03-15
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAHG | ELEVATOR REHABILITATION FOR 20TH, 25TH | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-16 | 2017-04-14 | 2021-03-16 | 2021-04-14
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAHI | BOILER REPLACEMENT AT 68TH, 76TH AND 102ND PCTS | 1 | DEVELOP SCOPE | 2014-06-30 | 2014-09-27 | 2014-06-30 | 2014-09-27
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAHI | BOILER REPLACEMENT AT 68TH, 76TH AND 102ND PCTS | 2 | PRELIMINARY DESIGN | 2014-09-28 | 2015-01-25 | 2014-09-28 | 2015-01-25
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAHI | BOILER REPLACEMENT AT 68TH, 76TH AND 102ND PCTS | 3 | FINAL DESIGN | 2015-01-26 | 2015-07-24 | 2015-01-26 | 2015-07-24
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAHI | BOILER REPLACEMENT AT 68TH, 76TH AND 102ND PCTS | 4 | BID AWARD AND REGISTER CONTRCT | 2015-07-25 | 2015-10-22 | 2015-07-25 | 2015-10-22
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAHI | BOILER REPLACEMENT AT 68TH, 76TH AND 102ND PCTS | 5 | CONSTRUCTION TO 25% | 2015-10-23 | 2016-02-19 | 2015-10-23 | 2016-02-19
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAHI | BOILER REPLACEMENT AT 68TH, 76TH AND 102ND PCTS | 6 | CONSTRUCTION TO 50% | 2016-02-20 | 2016-06-18 | 2016-02-20 | 2016-06-18
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAHI | BOILER REPLACEMENT AT 68TH, 76TH AND 102ND PCTS | 7 | CONSTRUCTION TO 75% | 2016-06-19 | 2016-10-16 | 2016-06-19 | 2020-10-16
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAHI | BOILER REPLACEMENT AT 68TH, 76TH AND 102ND PCTS | 8 | ORIGINAL EQUIP & FURNISHING | 2016-10-17 | 2017-01-14 | 2020-10-17 | 2021-01-14
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAHI | BOILER REPLACEMENT AT 68TH, 76TH AND 102ND PCTS | 9 | SUBSTANTIAL COMPLETION | 2017-01-15 | 2017-03-15 | 2021-01-15 | 2021-03-15
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAHI | BOILER REPLACEMENT AT 68TH, 76TH AND 102ND PCTS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-16 | 2017-04-14 | 2021-03-16 | 2022-04-14
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAHY | BOILERS AT 26TH, 42ND & 46TH PRECINCTS | 1 | DEVELOP SCOPE | 2014-06-30 | 2014-09-27 | 2014-06-30 | 2014-09-27
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAHY | BOILERS AT 26TH, 42ND & 46TH PRECINCTS | 2 | PRELIMINARY DESIGN | 2014-09-28 | 2015-01-25 | 2014-09-28 | 2015-01-25
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAHY | BOILERS AT 26TH, 42ND & 46TH PRECINCTS | 3 | FINAL DESIGN | 2015-01-26 | 2015-07-24 | 2015-01-26 | 2015-07-24
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAHY | BOILERS AT 26TH, 42ND & 46TH PRECINCTS | 4 | BID AWARD AND REGISTER CONTRCT | 2015-07-25 | 2015-10-22 | 2015-07-25 | 2015-10-22
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAHY | BOILERS AT 26TH, 42ND & 46TH PRECINCTS | 5 | CONSTRUCTION TO 25% | 2015-10-23 | 2016-02-19 | 2015-10-23 | 2016-02-19
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAHY | BOILERS AT 26TH, 42ND & 46TH PRECINCTS | 6 | CONSTRUCTION TO 50% | 2016-02-20 | 2016-06-18 | 2016-02-20 | 2016-06-18
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAHY | BOILERS AT 26TH, 42ND & 46TH PRECINCTS | 7 | CONSTRUCTION TO 75% | 2016-06-19 | 2016-10-16 | 2016-06-19 | 2021-10-16
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAHY | BOILERS AT 26TH, 42ND & 46TH PRECINCTS | 8 | ORIGINAL EQUIP & FURNISHING | 2016-10-17 | 2017-01-14 | 2021-10-17 | 2022-01-14
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAHY | BOILERS AT 26TH, 42ND & 46TH PRECINCTS | 9 | SUBSTANTIAL COMPLETION | 2017-01-15 | 2017-03-15 | 2022-01-15 | 2022-03-15
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAHY | BOILERS AT 26TH, 42ND & 46TH PRECINCTS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-16 | 2017-04-14 | 2022-03-16 | 2022-04-14
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAJZ | 49TH & 115TH & MTN PCT HVAC REPLACEMENT | 1 | DESIGN | 2019-12-30 | 2020-06-26 | 2019-12-30 | 2020-06-26
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAJZ | 49TH & 115TH & MTN PCT HVAC REPLACEMENT | 2 | BID AWARD AND REGISTER CONTRCT | 2020-06-27 | 2020-09-24 | 2020-06-27 | 2020-09-24
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAJZ | 49TH & 115TH & MTN PCT HVAC REPLACEMENT | 3 | CONSTRUCTION | 2020-09-25 | 2021-09-24 | 2020-09-25 | 2021-09-24
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAJZ | 49TH & 115TH & MTN PCT HVAC REPLACEMENT | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-25 | 2022-03-23 | 2021-09-25 | 2022-03-23
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAKF | CAC BATHROOM RENOVATION | 1 | DEVELOP SCOPE | 2019-06-15 | 2019-09-12 | 2019-06-15 | 2019-09-12
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAKF | CAC BATHROOM RENOVATION | 2 | PRELIMINARY DESIGN | 2019-09-13 | 2020-01-10 | 2019-09-13 | 2020-01-10
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAKF | CAC BATHROOM RENOVATION | 3 | FINAL DESIGN | 2020-01-11 | 2020-05-09 | 2020-01-11 | 2020-05-09
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAKF | CAC BATHROOM RENOVATION | 4 | BID AWARD AND REGISTER CONTRCT | 2020-05-10 | 2020-11-05 | 2020-05-10 | 2020-11-05
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAKF | CAC BATHROOM RENOVATION | 5 | CONSTRUCTION TO 25% | 2020-11-06 | 2021-03-05 | 2020-11-06 | 2021-03-05
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAKF | CAC BATHROOM RENOVATION | 6 | CONSTRUCTION TO 50% | 2021-03-06 | 2021-07-03 | 2021-03-06 | 2021-07-03
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAKF | CAC BATHROOM RENOVATION | 7 | CONSTRUCTION TO 75% | 2021-07-04 | 2021-10-31 | 2021-07-04 | 2021-10-31
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAKF | CAC BATHROOM RENOVATION | 8 | ORIGINAL EQUIP & FURNISHING | 2021-11-01 | 2022-01-29 | 2021-11-01 | 2022-01-29
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAKF | CAC BATHROOM RENOVATION | 9 | SUBSTANTIAL COMPLETION | 2022-01-30 | 2022-03-30 | 2022-01-30 | 2022-03-30
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAKF | CAC BATHROOM RENOVATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-31 | 2022-04-29 | 2022-03-31 | 2022-04-29
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAKI | BOILERS AT MTS, HWY 3, 75 & 77 PRECINCTS | 1 | DESIGN | 2020-12-19 | 2021-06-16 | 2020-12-19 | 2021-06-16
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAKI | BOILERS AT MTS, HWY 3, 75 & 77 PRECINCTS | 2 | BID AWARD AND REGISTER CONTRCT | 2021-06-17 | 2021-09-14 | 2021-06-17 | 2021-09-14
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAKI | BOILERS AT MTS, HWY 3, 75 & 77 PRECINCTS | 3 | CONSTRUCTION | 2021-09-15 | 2022-09-14 | 2021-09-15 | 2022-09-14
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAKI | BOILERS AT MTS, HWY 3, 75 & 77 PRECINCTS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-15 | 2023-03-13 | 2022-09-15 | 2023-03-13
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAKM | PSA4 HVAC | 1 | DEVELOP SCOPE | 2020-12-10 | 2021-03-09 | 2020-12-10 | 2021-03-09
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAKM | PSA4 HVAC | 2 | PRELIMINARY DESIGN | 2021-03-10 | 2021-07-07 | 2021-03-10 | 2021-07-07
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAKM | PSA4 HVAC | 3 | FINAL DESIGN | 2021-07-08 | 2021-11-04 | 2021-07-08 | 2021-11-04
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAKM | PSA4 HVAC | 4 | BID AWARD AND REGISTER CONTRCT | 2021-11-05 | 2022-05-03 | 2021-11-05 | 2022-05-03
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAKM | PSA4 HVAC | 5 | CONSTRUCTION TO 25% | 2022-05-04 | 2022-08-31 | 2022-05-04 | 2022-08-31
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAKM | PSA4 HVAC | 6 | CONSTRUCTION TO 50% | 2022-09-01 | 2022-12-29 | 2022-09-01 | 2022-12-29
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAKM | PSA4 HVAC | 7 | CONSTRUCTION TO 75% | 2022-12-30 | 2023-04-28 | 2022-12-30 | 2023-04-28
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAKM | PSA4 HVAC | 8 | ORIGINAL EQUIP & FURNISHING | 2023-04-29 | 2023-07-27 | 2023-04-29 | 2023-07-27
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAKM | PSA4 HVAC | 9 | SUBSTANTIAL COMPLETION | 2023-07-28 | 2023-09-25 | 2023-07-28 | 2023-09-25
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAKM | PSA4 HVAC | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-26 | 2023-10-25 | 2023-09-26 | 2023-10-25
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAKN | BOILERS REPLACEMENT AT BMS & SRG4 | 1 | DEVELOP SCOPE | 2020-12-10 | 2021-03-09 | 2020-12-10 | 2021-03-09
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAKN | BOILERS REPLACEMENT AT BMS & SRG4 | 2 | PRELIMINARY DESIGN | 2021-03-10 | 2021-07-07 | 2021-03-10 | 2021-07-07
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAKN | BOILERS REPLACEMENT AT BMS & SRG4 | 3 | FINAL DESIGN | 2021-07-08 | 2021-11-04 | 2021-07-08 | 2021-11-04
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAKN | BOILERS REPLACEMENT AT BMS & SRG4 | 4 | BID AWARD AND REGISTER CONTRCT | 2021-11-05 | 2022-05-03 | 2021-11-05 | 2022-05-03
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAKN | BOILERS REPLACEMENT AT BMS & SRG4 | 5 | CONSTRUCTION TO 25% | 2022-05-04 | 2022-08-31 | 2022-05-04 | 2022-08-31
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAKN | BOILERS REPLACEMENT AT BMS & SRG4 | 6 | CONSTRUCTION TO 50% | 2022-09-01 | 2022-12-29 | 2022-09-01 | 2022-12-29
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAKN | BOILERS REPLACEMENT AT BMS & SRG4 | 7 | CONSTRUCTION TO 75% | 2022-12-30 | 2023-04-28 | 2022-12-30 | 2023-04-28
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAKN | BOILERS REPLACEMENT AT BMS & SRG4 | 8 | ORIGINAL EQUIP & FURNISHING | 2023-04-29 | 2023-07-27 | 2023-04-29 | 2023-07-27
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAKN | BOILERS REPLACEMENT AT BMS & SRG4 | 9 | SUBSTANTIAL COMPLETION | 2023-07-28 | 2023-09-25 | 2023-07-28 | 2023-09-25
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAKN | BOILERS REPLACEMENT AT BMS & SRG4 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-26 | 2023-10-25 | 2023-09-26 | 2023-10-25
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79CWAC | CITYWIDE HVAC PROGRAM | 1 | DESIGN | 2016-07-01 | 2016-12-27 | 2018-06-01 | 2018-11-27
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79CWAC | CITYWIDE HVAC PROGRAM | 2 | BID AWARD AND REGISTER CONTRCT | 2016-12-28 | 2017-03-27 | 2018-11-28 | 2019-02-25
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79CWAC | CITYWIDE HVAC PROGRAM | 3 | CONSTRUCTION | 2017-03-28 | 2018-03-27 | 2019-02-26 | 2022-02-25
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79CWAC | CITYWIDE HVAC PROGRAM | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-03-28 | 2018-09-23 | 2022-02-26 | 2022-08-24
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79FATS | FIREARMS TACTICAL TRAINING CENTERS | 1 | DEVELOP SCOPE | 2017-04-19 | 2017-07-17 | 2017-04-19 | 2017-07-17
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79FATS | FIREARMS TACTICAL TRAINING CENTERS | 2 | PRELIMINARY DESIGN | 2017-07-18 | 2017-11-14 | 2017-07-18 | 2017-11-14
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79FATS | FIREARMS TACTICAL TRAINING CENTERS | 3 | FINAL DESIGN | 2017-11-15 | 2018-05-13 | 2017-11-15 | 2018-05-13
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79FATS | FIREARMS TACTICAL TRAINING CENTERS | 4 | BID AWARD AND REGISTER CONTRCT | 2018-05-14 | 2018-08-11 | 2018-05-14 | 2018-08-11
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79FATS | FIREARMS TACTICAL TRAINING CENTERS | 5 | CONSTRUCTION TO 25% | 2018-08-12 | 2018-12-09 | 2018-08-12 | 2018-12-09
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79FATS | FIREARMS TACTICAL TRAINING CENTERS | 6 | CONSTRUCTION TO 50% | 2018-12-10 | 2019-04-08 | 2018-12-10 | 2019-04-08
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79FATS | FIREARMS TACTICAL TRAINING CENTERS | 7 | CONSTRUCTION TO 75% | 2019-04-09 | 2019-08-06 | 2019-04-09 | 2021-08-06
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79FATS | FIREARMS TACTICAL TRAINING CENTERS | 8 | ORIGINAL EQUIP & FURNISHING | 2019-08-07 | 2019-11-04 | 2021-08-07 | 2021-11-04
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79FATS | FIREARMS TACTICAL TRAINING CENTERS | 9 | SUBSTANTIAL COMPLETION | 2019-11-05 | 2020-01-03 | 2021-11-05 | 2022-01-03
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79FATS | FIREARMS TACTICAL TRAINING CENTERS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-01-04 | 2020-02-02 | 2022-01-04 | 2022-02-02
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79LOCK | CITYWIDE LOCKER ROOM RENOVATION | 1 | DEVELOP SCOPE | 2017-04-19 | 2017-07-17 | 2017-04-19 | 2017-07-17
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79LOCK | CITYWIDE LOCKER ROOM RENOVATION | 2 | PRELIMINARY DESIGN | 2017-07-18 | 2017-11-14 | 2017-07-18 | 2017-11-14
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79LOCK | CITYWIDE LOCKER ROOM RENOVATION | 3 | FINAL DESIGN | 2017-11-15 | 2018-05-13 | 2017-11-15 | 2018-05-13
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79LOCK | CITYWIDE LOCKER ROOM RENOVATION | 4 | BID AWARD AND REGISTER CONTRCT | 2018-05-14 | 2018-08-11 | 2018-05-14 | 2018-08-11
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79LOCK | CITYWIDE LOCKER ROOM RENOVATION | 5 | CONSTRUCTION TO 25% | 2018-08-12 | 2018-12-09 | 2018-08-12 | 2018-12-09
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79LOCK | CITYWIDE LOCKER ROOM RENOVATION | 6 | CONSTRUCTION TO 50% | 2018-12-10 | 2019-04-08 | 2018-12-10 | 2019-04-08
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79LOCK | CITYWIDE LOCKER ROOM RENOVATION | 7 | CONSTRUCTION TO 75% | 2019-04-09 | 2019-08-06 | 2019-04-09 | 2024-08-06
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79LOCK | CITYWIDE LOCKER ROOM RENOVATION | 8 | ORIGINAL EQUIP & FURNISHING | 2019-08-07 | 2019-11-04 | 2024-08-07 | 2024-11-04
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79LOCK | CITYWIDE LOCKER ROOM RENOVATION | 9 | SUBSTANTIAL COMPLETION | 2019-11-05 | 2020-01-03 | 2024-11-05 | 2025-01-03
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79LOCK | CITYWIDE LOCKER ROOM RENOVATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-01-04 | 2020-02-02 | 2025-01-04 | 2025-02-02
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79TIME | TIMES SQUARE STATION RENOVATION | 1 | DEVELOP SCOPE | 2016-06-01 | 2016-08-29 | 2016-06-01 | 2016-08-29
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79TIME | TIMES SQUARE STATION RENOVATION | 2 | PRELIMINARY DESIGN | 2016-08-30 | 2016-12-27 | 2016-08-30 | 2016-12-27
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79TIME | TIMES SQUARE STATION RENOVATION | 3 | FINAL DESIGN | 2016-12-28 | 2017-04-26 | 2016-12-28 | 2017-04-26
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79TIME | TIMES SQUARE STATION RENOVATION | 4 | BID AWARD AND REGISTER CONTRCT | 2017-04-27 | 2017-10-23 | 2017-04-27 | 2017-10-23
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79TIME | TIMES SQUARE STATION RENOVATION | 5 | CONSTRUCTION TO 25% | 2017-10-24 | 2018-02-20 | 2017-10-24 | 2018-02-20
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79TIME | TIMES SQUARE STATION RENOVATION | 6 | CONSTRUCTION TO 50% | 2018-02-21 | 2018-06-20 | 2018-02-21 | 2018-06-20
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79TIME | TIMES SQUARE STATION RENOVATION | 7 | CONSTRUCTION TO 75% | 2018-06-21 | 2018-10-18 | 2018-06-21 | 2021-12-18
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79TIME | TIMES SQUARE STATION RENOVATION | 8 | ORIGINAL EQUIP & FURNISHING | 2018-10-19 | 2019-01-16 | 2021-12-19 | 2022-03-18
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79TIME | TIMES SQUARE STATION RENOVATION | 9 | SUBSTANTIAL COMPLETION | 2019-01-17 | 2019-03-17 | 2022-03-19 | 2022-05-17
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79TIME | TIMES SQUARE STATION RENOVATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-03-18 | 2019-04-16 | 2022-05-18 | 2022-06-16
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | SANDCONDT | ELECTRICAL CONDUIT REPLACEMENT (SANDY) | 1 | DEVELOP SCOPE | 2015-02-10 | 2015-05-10 | 2019-01-20 | 2019-04-19
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | SANDCONDT | ELECTRICAL CONDUIT REPLACEMENT (SANDY) | 2 | PRELIMINARY DESIGN | 2015-05-11 | 2015-09-07 | 2019-04-20 | 2019-08-17
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | SANDCONDT | ELECTRICAL CONDUIT REPLACEMENT (SANDY) | 3 | FINAL DESIGN | 2015-09-08 | 2016-01-05 | 2019-08-18 | 2019-12-15
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | SANDCONDT | ELECTRICAL CONDUIT REPLACEMENT (SANDY) | 4 | BID AWARD AND REGISTER CONTRCT | 2016-01-06 | 2016-07-03 | 2019-12-16 | 2020-06-12
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | SANDCONDT | ELECTRICAL CONDUIT REPLACEMENT (SANDY) | 5 | CONSTRUCTION TO 25% | 2016-07-04 | 2016-10-31 | 2020-06-13 | 2020-10-10
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | SANDCONDT | ELECTRICAL CONDUIT REPLACEMENT (SANDY) | 6 | CONSTRUCTION TO 50% | 2016-11-01 | 2017-02-28 | 2020-10-11 | 2021-02-07
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | SANDCONDT | ELECTRICAL CONDUIT REPLACEMENT (SANDY) | 7 | CONSTRUCTION TO 75% | 2017-03-01 | 2017-06-28 | 2021-02-08 | 2021-06-07
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | SANDCONDT | ELECTRICAL CONDUIT REPLACEMENT (SANDY) | 8 | ORIGINAL EQUIP & FURNISHING | 2017-06-29 | 2017-09-26 | 2021-06-08 | 2021-09-05
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | SANDCONDT | ELECTRICAL CONDUIT REPLACEMENT (SANDY) | 9 | SUBSTANTIAL COMPLETION | 2017-09-27 | 2017-11-25 | 2021-09-06 | 2021-11-04
20201123 | CITYWIDE | 056 | POLICE DEPARTMENT | SANDCONDT | ELECTRICAL CONDUIT REPLACEMENT (SANDY) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-11-26 | 2017-12-25 | 2021-11-05 | 2021-12-04
20201123 | CITYWIDE | 057 | FIRE DEPARTMENT | F175EMS20 | EMS 20 EXPANSION AND RENOVATON | 1 | CONSTRUCTION | 2017-04-05 | 2018-04-04 | 2019-10-03 | 2020-10-01
20201123 | CITYWIDE | 057 | FIRE DEPARTMENT | F175EMS20 | EMS 20 EXPANSION AND RENOVATON | 2 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-04-05 | 2018-07-03 | 2020-01-01 | 2020-12-30
20201123 | CITYWIDE | 057 | FIRE DEPARTMENT | F175EMS4M | MULTI COMPONENT RENOVATIONS - EMS 4 | 1 | DESIGN | 2017-08-01 | 2018-01-27 | 2018-07-24 | 2019-01-19
20201123 | CITYWIDE | 057 | FIRE DEPARTMENT | F175EMS4M | MULTI COMPONENT RENOVATIONS - EMS 4 | 2 | CONSTRUCTION | 2018-01-28 | 2019-01-27 | 2019-01-20 | 2020-01-19
20201123 | CITYWIDE | 057 | FIRE DEPARTMENT | F175EMS4M | MULTI COMPONENT RENOVATIONS - EMS 4 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-01-28 | 2019-04-27 | 2020-01-20 | 2022-01-20
20201123 | CITYWIDE | 057 | FIRE DEPARTMENT | F175MC153 | MULTI COMPONENT RENOVATIONS - EC153 | 1 | DESIGN | 2018-02-22 | 2018-08-20 | 2020-06-04 | 2020-11-30
20201123 | CITYWIDE | 057 | FIRE DEPARTMENT | F175MC153 | MULTI COMPONENT RENOVATIONS - EC153 | 2 | CONSTRUCTION | 2018-08-21 | 2019-08-20 | 2020-12-01 | 2021-11-30
20201123 | CITYWIDE | 057 | FIRE DEPARTMENT | F175MC153 | MULTI COMPONENT RENOVATIONS - EC153 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-08-21 | 2019-11-18 | 2021-12-01 | 2022-02-28
20201123 | CITYWIDE | 057 | FIRE DEPARTMENT | F175MC253 | MULTI COMPONENT RENOVATIONS - EC253 | 1 | DESIGN | 2017-09-05 | 2018-03-03 | 2018-04-09 | 2018-10-05
20201123 | CITYWIDE | 057 | FIRE DEPARTMENT | F175MC253 | MULTI COMPONENT RENOVATIONS - EC253 | 2 | CONSTRUCTION | 2018-03-04 | 2019-03-03 | 2018-10-06 | 2019-10-05
20201123 | CITYWIDE | 057 | FIRE DEPARTMENT | F175MC253 | MULTI COMPONENT RENOVATIONS - EC253 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-03-04 | 2019-06-01 | 2019-10-06 | 2020-12-30
20201123 | CITYWIDE | 057 | FIRE DEPARTMENT | F175TOI24 | Female Firefighter Toilet Upgrade - EC24 | 1 | DESIGN | 2017-10-30 | 2018-04-27 | 2019-04-06 | 2019-10-02
20201123 | CITYWIDE | 057 | FIRE DEPARTMENT | F175TOI24 | Female Firefighter Toilet Upgrade - EC24 | 2 | CONSTRUCTION | 2018-04-28 | 2019-04-27 | 2019-10-03 | 2020-10-01
20201123 | CITYWIDE | 057 | FIRE DEPARTMENT | F175TOI24 | Female Firefighter Toilet Upgrade - EC24 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-04-28 | 2019-07-26 | 2020-10-02 | 2020-12-30
20201123 | CITYWIDE | 057 | FIRE DEPARTMENT | F175WPE46 | Roof and Waterproofing Project - EC46 | 1 | DESIGN | 2017-11-08 | 2018-05-06 | 2019-08-01 | 2020-01-27
20201123 | CITYWIDE | 057 | FIRE DEPARTMENT | F175WPE46 | Roof and Waterproofing Project - EC46 | 2 | CONSTRUCTION | 2018-05-07 | 2019-05-06 | 2020-01-28 | 2021-01-26
20201123 | CITYWIDE | 057 | FIRE DEPARTMENT | F175WPE46 | Roof and Waterproofing Project - EC46 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-05-07 | 2019-08-04 | 2021-01-27 | 2021-04-26
20201123 | CITYWIDE | 057 | FIRE DEPARTMENT | F175WU299 | Cellar Reconstruction - EC299 | 1 | DESIGN | 2020-01-17 | 2020-07-14 | 2020-01-17 | 2020-07-14
20201123 | CITYWIDE | 057 | FIRE DEPARTMENT | F175WU299 | Cellar Reconstruction - EC299 | 2 | CONSTRUCTION | 2020-07-15 | 2021-07-14 | 2020-07-15 | 2021-07-14
20201123 | CITYWIDE | 057 | FIRE DEPARTMENT | F175WU299 | Cellar Reconstruction - EC299 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-07-15 | 2021-10-12 | 2021-07-15 | 2021-10-12
20201123 | CITYWIDE | 057 | FIRE DEPARTMENT | F1GAZ2002 | Gazebo - Manholes Project at Ave. S & Haring St in Brooklyn | 1 | DESIGN | 2020-11-02 | 2021-04-30 | 2020-11-02 | 2021-04-30
20201123 | CITYWIDE | 057 | FIRE DEPARTMENT | F1GAZ2002 | Gazebo - Manholes Project at Ave. S & Haring St in Brooklyn | 2 | CONSTRUCTION | 2021-05-01 | 2022-04-30 | 2021-05-01 | 2022-04-30
20201123 | CITYWIDE | 057 | FIRE DEPARTMENT | F1GAZ2002 | Gazebo - Manholes Project at Ave. S & Haring St in Brooklyn | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-05-01 | 2022-07-29 | 2022-05-01 | 2022-07-29
20201123 | CITYWIDE | 057 | FIRE DEPARTMENT | F204-DEMO | FORT TOTEN DEMOLITION | 1 | CONSTRUCTION | 2018-11-01 | 2019-10-31 | 2019-10-03 | 2020-10-01
20201123 | CITYWIDE | 057 | FIRE DEPARTMENT | F204-DEMO | FORT TOTEN DEMOLITION | 2 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-11-01 | 2020-01-29 | 2020-10-02 | 2020-12-30
20201123 | CITYWIDE | 057 | FIRE DEPARTMENT | F204WATER | Randall's Island Water Tank Replacement | 1 | DESIGN | 2018-03-20 | 2018-09-15 | 2020-04-03 | 2020-09-29
20201123 | CITYWIDE | 057 | FIRE DEPARTMENT | F204WATER | Randall's Island Water Tank Replacement | 2 | CONSTRUCTION | 2018-09-16 | 2019-09-15 | 2020-09-30 | 2021-09-29
20201123 | CITYWIDE | 057 | FIRE DEPARTMENT | F204WATER | Randall's Island Water Tank Replacement | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-16 | 2019-12-14 | 2021-09-30 | 2021-12-28
20201123 | CITYWIDE | 057 | FIRE DEPARTMENT | F212-COOL | Power and Cooling for Data Center 11 MetroTech | 1 | CONSTRUCTION | 2020-06-30 | 2021-06-29 | 2020-06-30 | 2021-06-29
20201123 | CITYWIDE | 057 | FIRE DEPARTMENT | F212-COOL | Power and Cooling for Data Center 11 MetroTech | 2 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-06-30 | 2021-09-27 | 2021-06-30 | 2021-09-27
20201123 | CITYWIDE | 057 | FIRE DEPARTMENT | SANDHM265 | HURRICANE SANDY HAZMAT MITIGATION-EC265 | 1 | DESIGN | 2016-04-15 | 2016-10-11 | 2017-04-15 | 2017-10-11
20201123 | CITYWIDE | 057 | FIRE DEPARTMENT | SANDHM265 | HURRICANE SANDY HAZMAT MITIGATION-EC265 | 2 | CONSTRUCTION | 2016-10-12 | 2017-10-11 | 2017-10-12 | 2018-10-11
20201123 | CITYWIDE | 057 | FIRE DEPARTMENT | SANDHM265 | HURRICANE SANDY HAZMAT MITIGATION-EC265 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-10-12 | 2018-01-09 | 2018-10-12 | 2022-06-26
20201123 | CITYWIDE | 057 | FIRE DEPARTMENT | SANDHM266 | HURRICANE SANDY HAZMAT MITIGATION - EC266 | 1 | DESIGN | 2016-03-25 | 2016-09-20 | 2017-03-25 | 2017-09-20
20201123 | CITYWIDE | 057 | FIRE DEPARTMENT | SANDHM266 | HURRICANE SANDY HAZMAT MITIGATION - EC266 | 2 | CONSTRUCTION | 2016-09-21 | 2017-09-20 | 2017-09-21 | 2018-09-20
20201123 | CITYWIDE | 057 | FIRE DEPARTMENT | SANDHM266 | HURRICANE SANDY HAZMAT MITIGATION - EC266 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-09-21 | 2017-12-19 | 2018-09-21 | 2022-06-26
20201123 | CITYWIDE | 068 | ADMIN FOR CHILDREN'S SERVICES | ACSPDF | Renovation projects for field offices | 1 | DEVELOP SCOPE | 2018-06-30 | 2018-09-27 | 2020-06-30 | 2020-09-27
20201123 | CITYWIDE | 068 | ADMIN FOR CHILDREN'S SERVICES | ACSPDF | Renovation projects for field offices | 2 | PRELIMINARY DESIGN | 2018-09-28 | 2019-01-25 | 2020-09-28 | 2021-01-25
20201123 | CITYWIDE | 068 | ADMIN FOR CHILDREN'S SERVICES | ACSPDF | Renovation projects for field offices | 3 | FINAL DESIGN | 2019-01-26 | 2019-07-24 | 2021-01-26 | 2021-07-24
20201123 | CITYWIDE | 068 | ADMIN FOR CHILDREN'S SERVICES | ACSPDF | Renovation projects for field offices | 4 | BID AWARD AND REGISTER CONTRCT | 2019-07-25 | 2019-10-22 | 2021-07-25 | 2021-10-22
20201123 | CITYWIDE | 068 | ADMIN FOR CHILDREN'S SERVICES | ACSPDF | Renovation projects for field offices | 5 | CONSTRUCTION TO 25% | 2019-10-23 | 2020-02-19 | 2021-10-23 | 2022-02-19
20201123 | CITYWIDE | 068 | ADMIN FOR CHILDREN'S SERVICES | ACSPDF | Renovation projects for field offices | 6 | CONSTRUCTION TO 50% | 2020-02-20 | 2020-06-18 | 2022-02-20 | 2022-06-19
20201123 | CITYWIDE | 068 | ADMIN FOR CHILDREN'S SERVICES | ACSPDF | Renovation projects for field offices | 7 | CONSTRUCTION TO 75% | 2020-06-19 | 2020-10-16 | 2022-06-20 | 2022-10-17
20201123 | CITYWIDE | 068 | ADMIN FOR CHILDREN'S SERVICES | ACSPDF | Renovation projects for field offices | 8 | ORIGINAL EQUIP & FURNISHING | 2020-10-17 | 2021-01-14 | 2026-10-17 | 2027-01-14
20201123 | CITYWIDE | 068 | ADMIN FOR CHILDREN'S SERVICES | ACSPDF | Renovation projects for field offices | 9 | SUBSTANTIAL COMPLETION | 2021-01-15 | 2023-03-15 | 2027-01-15 | 2027-03-14
20201123 | CITYWIDE | 068 | ADMIN FOR CHILDREN'S SERVICES | ACSPDF | Renovation projects for field offices | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-03-16 | 2023-04-13 | 2027-03-15 | 2027-04-12
20201123 | CITYWIDE | 071 | DEPT OF HOMELESS SERVICES | HRCN100VA | Volunteers of America | 1 | DEVELOP SCOPE | 2014-08-16 | 2014-11-13 | 2019-08-16 | 2019-11-13
20201123 | CITYWIDE | 071 | DEPT OF HOMELESS SERVICES | HRCN100VA | Volunteers of America | 2 | PRELIMINARY DESIGN | 2014-11-14 | 2015-03-13 | 2019-11-14 | 2020-03-12
20201123 | CITYWIDE | 071 | DEPT OF HOMELESS SERVICES | HRCN100VA | Volunteers of America | 3 | FINAL DESIGN | 2015-03-14 | 2015-07-11 | 2020-03-13 | 2020-07-10
20201123 | CITYWIDE | 071 | DEPT OF HOMELESS SERVICES | HRCN100VA | Volunteers of America | 4 | BID AWARD AND REGISTER CONTRCT | 2015-07-12 | 2016-01-07 | 2020-07-11 | 2021-01-06
20201123 | CITYWIDE | 071 | DEPT OF HOMELESS SERVICES | HRCN100VA | Volunteers of America | 5 | CONSTRUCTION TO 25% | 2016-01-08 | 2016-05-06 | 2021-01-07 | 2021-05-06
20201123 | CITYWIDE | 071 | DEPT OF HOMELESS SERVICES | HRCN100VA | Volunteers of America | 6 | CONSTRUCTION TO 50% | 2016-05-07 | 2016-09-03 | 2021-05-07 | 2021-09-03
20201123 | CITYWIDE | 071 | DEPT OF HOMELESS SERVICES | HRCN100VA | Volunteers of America | 7 | CONSTRUCTION TO 75% | 2016-09-04 | 2017-01-01 | 2021-09-04 | 2022-01-01
20201123 | CITYWIDE | 071 | DEPT OF HOMELESS SERVICES | HRCN100VA | Volunteers of America | 8 | ORIGINAL EQUIP & FURNISHING | 2017-01-02 | 2017-04-01 | 2022-01-02 | 2022-04-01
20201123 | CITYWIDE | 071 | DEPT OF HOMELESS SERVICES | HRCN100VA | Volunteers of America | 9 | SUBSTANTIAL COMPLETION | 2017-04-02 | 2017-05-31 | 2022-04-02 | 2022-05-31
20201123 | CITYWIDE | 071 | DEPT OF HOMELESS SERVICES | HRCN100VA | Volunteers of America | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-06-01 | 2017-06-30 | 2022-06-01 | 2022-06-30
20201123 | CITYWIDE | 072 | DEPARTMENT OF CORRECTION | C114ACADY | Construction of a New Training Academy | 1 | DESIGN | 2017-09-01 | 2018-07-02 | 2017-09-01 | 2018-07-02
20201123 | CITYWIDE | 072 | DEPARTMENT OF CORRECTION | C114ACADY | Construction of a New Training Academy | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-03 | 2019-07-02 | 2018-07-03 | 2019-07-02
20201123 | CITYWIDE | 072 | DEPARTMENT OF CORRECTION | C114ACADY | Construction of a New Training Academy | 3 | CONSTRUCTION TO 75% | 2019-07-03 | 2021-02-14 | 2019-07-03 | 2021-02-14
20201123 | CITYWIDE | 072 | DEPARTMENT OF CORRECTION | C114ACADY | Construction of a New Training Academy | 4 | SUBSTANTIAL COMPLETION | 2021-02-15 | 2021-06-13 | 2021-02-15 | 2021-06-13
20201123 | CITYWIDE | 072 | DEPARTMENT OF CORRECTION | C114ACADY | Construction of a New Training Academy | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-06-14 | 2021-08-31 | 2021-06-14 | 2025-08-31
20201123 | CITYWIDE | 072 | DEPARTMENT OF CORRECTION | C75GENREP | Installation of Replacement Generators RNDC, EMTC,GMDC,RMSC | 1 | DESIGN | 2014-07-30 | 2014-08-28 | 2014-07-30 | 2014-08-28
20201123 | CITYWIDE | 072 | DEPARTMENT OF CORRECTION | C75GENREP | Installation of Replacement Generators RNDC, EMTC,GMDC,RMSC | 2 | BID AWARD AND REGISTER CONTRCT | 2014-08-29 | 2014-11-26 | 2014-08-29 | 2014-11-26
20201123 | CITYWIDE | 072 | DEPARTMENT OF CORRECTION | C75GENREP | Installation of Replacement Generators RNDC, EMTC,GMDC,RMSC | 3 | CONSTRUCTION | 2014-11-27 | 2015-05-25 | 2014-11-27 | 2015-05-25
20201123 | CITYWIDE | 072 | DEPARTMENT OF CORRECTION | C75GENREP | Installation of Replacement Generators RNDC, EMTC,GMDC,RMSC | 4 | ORIGINAL EQUIP & FURNISHING | 2015-05-26 | 2015-08-23 | 2015-05-26 | 2015-08-23
20201123 | CITYWIDE | 072 | DEPARTMENT OF CORRECTION | C75GENREP | Installation of Replacement Generators RNDC, EMTC,GMDC,RMSC | 5 | SUBSTANTIAL COMPLETION | 2015-08-24 | 2015-09-22 | 2015-08-24 | 2015-09-22
20201123 | CITYWIDE | 072 | DEPARTMENT OF CORRECTION | C75GENREP | Installation of Replacement Generators RNDC, EMTC,GMDC,RMSC | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-09-23 | 2015-10-22 | 2015-09-23 | 2026-06-30
20201123 | CITYWIDE | 072 | DEPARTMENT OF CORRECTION | C-75MISC | MISC INFRASTRUCTURE RECON | 1 | DEVELOP SCOPE | 2008-06-30 | 2010-06-29 | 2008-06-30 | 2010-06-29
20201123 | CITYWIDE | 072 | DEPARTMENT OF CORRECTION | C-75MISC | MISC INFRASTRUCTURE RECON | 2 | PRELIMINARY DESIGN | 2010-06-30 | 2012-06-28 | 2010-06-30 | 2012-06-28
20201123 | CITYWIDE | 072 | DEPARTMENT OF CORRECTION | C-75MISC | MISC INFRASTRUCTURE RECON | 3 | FINAL DESIGN | 2012-06-29 | 2014-06-28 | 2012-06-29 | 2014-06-28
20201123 | CITYWIDE | 072 | DEPARTMENT OF CORRECTION | C-75MISC | MISC INFRASTRUCTURE RECON | 4 | BID AWARD AND REGISTER CONTRCT | 2014-06-29 | 2016-06-27 | 2014-06-29 | 2016-06-27
20201123 | CITYWIDE | 072 | DEPARTMENT OF CORRECTION | C-75MISC | MISC INFRASTRUCTURE RECON | 5 | CONSTRUCTION TO 25% | 2016-06-28 | 2018-06-27 | 2016-06-28 | 2018-06-27
20201123 | CITYWIDE | 072 | DEPARTMENT OF CORRECTION | C-75MISC | MISC INFRASTRUCTURE RECON | 6 | CONSTRUCTION TO 50% | 2018-06-28 | 2020-06-26 | 2018-06-28 | 2020-06-26
20201123 | CITYWIDE | 072 | DEPARTMENT OF CORRECTION | C-75MISC | MISC INFRASTRUCTURE RECON | 7 | CONSTRUCTION TO 75% | 2020-06-27 | 2022-06-26 | 2020-06-27 | 2022-06-26
20201123 | CITYWIDE | 072 | DEPARTMENT OF CORRECTION | C-75MISC | MISC INFRASTRUCTURE RECON | 8 | ORIGINAL EQUIP & FURNISHING | 2022-06-27 | 2024-06-25 | 2022-06-27 | 2024-06-25
20201123 | CITYWIDE | 072 | DEPARTMENT OF CORRECTION | C-75MISC | MISC INFRASTRUCTURE RECON | 9 | SUBSTANTIAL COMPLETION | 2024-06-26 | 2026-06-25 | 2024-06-26 | 2026-06-25
20201123 | CITYWIDE | 072 | DEPARTMENT OF CORRECTION | C-75MISC | MISC INFRASTRUCTURE RECON | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2026-06-26 | 2028-06-24 | 2026-06-26 | 2028-06-24
20201123 | CITYWIDE | 072 | DEPARTMENT OF CORRECTION | C75POWRF | Replace 5 and 27 KV Feeders | 1 | DESIGN | 2015-12-01 | 2016-09-30 | 2018-06-01 | 2019-04-28
20201123 | CITYWIDE | 072 | DEPARTMENT OF CORRECTION | C75POWRF | Replace 5 and 27 KV Feeders | 2 | BID AWARD AND REGISTER CONTRCT | 2016-10-01 | 2017-09-30 | 2019-04-29 | 2020-03-27
20201123 | CITYWIDE | 072 | DEPARTMENT OF CORRECTION | C75POWRF | Replace 5 and 27 KV Feeders | 3 | CONSTRUCTION TO 75% | 2017-10-01 | 2019-05-16 | 2020-04-01 | 2021-01-30
20201123 | CITYWIDE | 072 | DEPARTMENT OF CORRECTION | C75POWRF | Replace 5 and 27 KV Feeders | 4 | SUBSTANTIAL COMPLETION | 2019-05-17 | 2019-09-12 | 2021-01-31 | 2021-02-28
20201123 | CITYWIDE | 072 | DEPARTMENT OF CORRECTION | C75POWRF | Replace 5 and 27 KV Feeders | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-13 | 2019-11-30 | 2021-03-01 | 2021-05-30
20201123 | CITYWIDE | 096 | HUMAN RESOURCES ADMINISTRATION | HR25EFOY | HRA FACILITIES & EQUIPMENT OUTYEARS FOR UPGRADES | 1 | DEVELOP SCOPE | 2008-01-01 | 2008-03-30 | 2018-06-01 | 2018-08-29
20201123 | CITYWIDE | 096 | HUMAN RESOURCES ADMINISTRATION | HR25EFOY | HRA FACILITIES & EQUIPMENT OUTYEARS FOR UPGRADES | 2 | PRELIMINARY DESIGN | 2008-03-31 | 2008-07-28 | 2018-08-30 | 2018-12-27
20201123 | CITYWIDE | 096 | HUMAN RESOURCES ADMINISTRATION | HR25EFOY | HRA FACILITIES & EQUIPMENT OUTYEARS FOR UPGRADES | 3 | FINAL DESIGN | 2008-07-29 | 2009-01-24 | 2018-12-28 | 2019-06-25
20201123 | CITYWIDE | 096 | HUMAN RESOURCES ADMINISTRATION | HR25EFOY | HRA FACILITIES & EQUIPMENT OUTYEARS FOR UPGRADES | 4 | BID AWARD AND REGISTER CONTRCT | 2009-01-25 | 2009-04-24 | 2019-06-26 | 2019-09-23
20201123 | CITYWIDE | 096 | HUMAN RESOURCES ADMINISTRATION | HR25EFOY | HRA FACILITIES & EQUIPMENT OUTYEARS FOR UPGRADES | 5 | CONSTRUCTION TO 25% | 2009-04-25 | 2009-08-22 | 2019-09-24 | 2020-01-21
20201123 | CITYWIDE | 096 | HUMAN RESOURCES ADMINISTRATION | HR25EFOY | HRA FACILITIES & EQUIPMENT OUTYEARS FOR UPGRADES | 6 | CONSTRUCTION TO 50% | 2009-08-23 | 2009-12-20 | 2020-01-22 | 2020-05-20
20201123 | CITYWIDE | 096 | HUMAN RESOURCES ADMINISTRATION | HR25EFOY | HRA FACILITIES & EQUIPMENT OUTYEARS FOR UPGRADES | 7 | CONSTRUCTION TO 75% | 2009-12-21 | 2010-04-19 | 2020-05-21 | 2020-09-17
20201123 | CITYWIDE | 096 | HUMAN RESOURCES ADMINISTRATION | HR25EFOY | HRA FACILITIES & EQUIPMENT OUTYEARS FOR UPGRADES | 8 | ORIGINAL EQUIP & FURNISHING | 2010-04-20 | 2010-07-18 | 2020-09-18 | 2020-12-16
20201123 | CITYWIDE | 096 | HUMAN RESOURCES ADMINISTRATION | HR25EFOY | HRA FACILITIES & EQUIPMENT OUTYEARS FOR UPGRADES | 9 | SUBSTANTIAL COMPLETION | 2010-07-19 | 2010-09-16 | 2020-12-17 | 2021-02-14
20201123 | CITYWIDE | 096 | HUMAN RESOURCES ADMINISTRATION | HR25EFOY | HRA FACILITIES & EQUIPMENT OUTYEARS FOR UPGRADES | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2010-09-17 | 2010-10-16 | 2021-02-15 | 2025-03-16
20201123 | CITYWIDE | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467-EMR | DCA - EMERGENCY CAPITAL FUND FOR DCA | 1 | DESIGN | 2015-04-09 | 2015-10-05 | 2022-04-09 | 2022-10-05
20201123 | CITYWIDE | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467-EMR | DCA - EMERGENCY CAPITAL FUND FOR DCA | 2 | BID AWARD AND REGISTER CONTRCT | 2015-10-06 | 2016-01-03 | 2022-10-06 | 2023-01-03
20201123 | CITYWIDE | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467-EMR | DCA - EMERGENCY CAPITAL FUND FOR DCA | 3 | CONSTRUCTION | 2016-01-04 | 2017-01-02 | 2023-01-04 | 2024-01-03
20201123 | CITYWIDE | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467-EMR | DCA - EMERGENCY CAPITAL FUND FOR DCA | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-01-03 | 2017-07-01 | 2024-01-04 | 2024-07-01
20201123 | CITYWIDE | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467-EMR | DCA - EMERGENCY CAPITAL FUND FOR DCA | 5 | DEVELOP SCOPE | 2017-01-03 | 2017-07-01 | 2024-07-02 | 2024-09-29
20201123 | CITYWIDE | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467-EMR | DCA - EMERGENCY CAPITAL FUND FOR DCA | 6 | PRELIMINARY DESIGN | 2017-01-03 | 2017-07-01 | 2024-09-30 | 2025-01-27
20201123 | CITYWIDE | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467-EMR | DCA - EMERGENCY CAPITAL FUND FOR DCA | 7 | FINAL DESIGN | 2017-01-03 | 2017-07-01 | 2025-01-28 | 2025-07-26
20201123 | CITYWIDE | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467-EMR | DCA - EMERGENCY CAPITAL FUND FOR DCA | 8 | BID AWARD AND REGISTER CONTRCT | 2017-01-03 | 2017-07-01 | 2025-07-27 | 2025-10-24
20201123 | CITYWIDE | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467-EMR | DCA - EMERGENCY CAPITAL FUND FOR DCA | 9 | CONSTRUCTION TO 25% | 2017-01-03 | 2017-07-01 | 2025-10-25 | 2026-02-21
20201123 | CITYWIDE | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467-EMR | DCA - EMERGENCY CAPITAL FUND FOR DCA | 10 | CONSTRUCTION TO 50% | 2017-01-03 | 2017-07-01 | 2026-02-22 | 2026-06-21
20201123 | CITYWIDE | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467-EMR | DCA - EMERGENCY CAPITAL FUND FOR DCA | 11 | CONSTRUCTION TO 75% | 2017-01-03 | 2017-07-01 | 2026-06-22 | 2026-10-19
20201123 | CITYWIDE | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467-EMR | DCA - EMERGENCY CAPITAL FUND FOR DCA | 12 | ORIGINAL EQUIP & FURNISHING | 2017-01-03 | 2017-07-01 | 2026-10-20 | 2027-01-17
20201123 | CITYWIDE | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467-EMR | DCA - EMERGENCY CAPITAL FUND FOR DCA | 13 | SUBSTANTIAL COMPLETION | 2017-01-03 | 2017-07-01 | 2027-01-18 | 2027-03-18
20201123 | CITYWIDE | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467-EMR | DCA - EMERGENCY CAPITAL FUND FOR DCA | 14 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-01-03 | 2017-07-01 | 2027-03-19 | 2027-04-17
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | ACQFUND | Acquistion Fund | 1 | DESIGN | 2016-07-01 | 2016-07-20 | 2017-07-20 | 2022-04-11
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | ACQFUND | Acquistion Fund | 2 | BID AWARD AND REGISTER CONTRCT | 2016-07-21 | 2016-08-04 | 2022-04-12 | 2022-04-26
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | ACQFUND | Acquistion Fund | 3 | CONSTRUCTION | 2016-08-05 | 2016-09-08 | 2022-04-27 | 2022-05-31
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | ACQFUND | Acquistion Fund | 4 | ORIGINAL EQUIP & FURNISHING | 2016-09-09 | 2016-09-18 | 2022-06-01 | 2022-06-10
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | ACQFUND | Acquistion Fund | 5 | SUBSTANTIAL COMPLETION | 2016-09-19 | 2016-10-03 | 2022-06-11 | 2022-06-25
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | ACQFUND | Acquistion Fund | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-10-04 | 2016-10-08 | 2022-06-26 | 2029-08-27
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | C5234 | Pier 11 Intermodal Ferry | 1 | DEVELOP SCOPE | 2003-04-01 | 2003-06-29 | 2006-03-27 | 2006-04-15
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | C5234 | Pier 11 Intermodal Ferry | 2 | PRELIMINARY DESIGN | 2003-06-30 | 2003-10-27 | 2006-04-16 | 2006-04-30
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | C5234 | Pier 11 Intermodal Ferry | 3 | FINAL DESIGN | 2003-10-28 | 2007-07-01 | 2006-05-01 | 2022-06-25
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | C5234 | Pier 11 Intermodal Ferry | 4 | BID AWARD AND REGISTER CONTRCT | 2007-07-02 | 2007-07-01 | 2022-06-26 | 2022-06-25
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | C5234 | Pier 11 Intermodal Ferry | 5 | CONSTRUCTION TO 25% | 2007-07-02 | 2007-07-01 | 2022-06-26 | 2022-06-25
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | C5234 | Pier 11 Intermodal Ferry | 6 | CONSTRUCTION TO 50% | 2007-07-02 | 2007-07-01 | 2022-06-26 | 2022-06-30
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | C5234 | Pier 11 Intermodal Ferry | 7 | CONSTRUCTION TO 75% | 2007-07-02 | 2007-07-01 | 2022-06-26 | 2022-06-30
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | C5234 | Pier 11 Intermodal Ferry | 8 | ORIGINAL EQUIP & FURNISHING | 2007-07-02 | 2007-07-01 | 2022-06-26 | 2022-06-30
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | C5234 | Pier 11 Intermodal Ferry | 9 | SUBSTANTIAL COMPLETION | 2007-07-02 | 2007-07-01 | 2022-06-26 | 2022-06-30
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | C5234 | Pier 11 Intermodal Ferry | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2007-07-02 | 2007-07-31 | 2022-06-26 | 2022-06-30
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | C5234A | Pier 11 Intermodal Ferry | 1 | DESIGN | 2005-01-01 | 2005-01-20 | 2007-12-28 | 2010-01-28
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | C5234A | Pier 11 Intermodal Ferry | 2 | BID AWARD AND REGISTER CONTRCT | 2005-01-21 | 2007-02-04 | 2010-01-29 | 2010-01-28
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | C5234A | Pier 11 Intermodal Ferry | 3 | CONSTRUCTION | 2007-02-05 | 2007-02-04 | 2010-01-29 | 2022-06-25
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | C5234A | Pier 11 Intermodal Ferry | 4 | ORIGINAL EQUIP & FURNISHING | 2007-02-05 | 2007-02-04 | 2022-06-26 | 2022-06-25
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | C5234A | Pier 11 Intermodal Ferry | 5 | SUBSTANTIAL COMPLETION | 2007-02-05 | 2007-02-04 | 2022-06-26 | 2022-06-25
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | C5234A | Pier 11 Intermodal Ferry | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2007-02-05 | 2007-02-09 | 2022-06-26 | 2022-06-30
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | CLEANYC | CleaNYC - Graffiti Free Trucks | 1 | DESIGN | 2016-07-01 | 2016-07-20 | 2016-07-01 | 2016-07-20
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | CLEANYC | CleaNYC - Graffiti Free Trucks | 2 | BID AWARD AND REGISTER CONTRCT | 2016-07-21 | 2016-08-04 | 2016-07-21 | 2016-08-04
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | CLEANYC | CleaNYC - Graffiti Free Trucks | 3 | CONSTRUCTION | 2016-08-05 | 2016-09-08 | 2016-08-05 | 2016-09-08
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | CLEANYC | CleaNYC - Graffiti Free Trucks | 4 | ORIGINAL EQUIP & FURNISHING | 2016-09-09 | 2016-09-18 | 2016-09-09 | 2016-09-18
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | CLEANYC | CleaNYC - Graffiti Free Trucks | 5 | SUBSTANTIAL COMPLETION | 2016-09-19 | 2016-10-03 | 2016-09-19 | 2016-10-03
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | CLEANYC | CleaNYC - Graffiti Free Trucks | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-10-04 | 2016-10-08 | 2016-10-04 | 2025-06-30
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | CWFSBARGE | New York City Ferry Barges | 1 | DESIGN | 2016-01-01 | 2018-06-30 | 2016-01-01 | 2018-06-30
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | CWFSBARGE | New York City Ferry Barges | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-01 | 2018-06-30 | 2018-07-01 | 2018-06-30
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | CWFSBARGE | New York City Ferry Barges | 3 | CONSTRUCTION | 2018-07-01 | 2021-06-30 | 2018-07-01 | 2021-06-30
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | CWFSBARGE | New York City Ferry Barges | 4 | ORIGINAL EQUIP & FURNISHING | 2021-07-01 | 2021-06-30 | 2021-07-01 | 2021-06-30
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | CWFSBARGE | New York City Ferry Barges | 5 | SUBSTANTIAL COMPLETION | 2021-07-01 | 2021-06-30 | 2021-07-01 | 2021-06-30
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | CWFSBARGE | New York City Ferry Barges | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-07-01 | 2021-07-05 | 2021-07-01 | 2021-07-05
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | CWFSFERRY | New York City Ferry - Ferry Purchase and Upgrade | 1 | DESIGN | 2016-07-01 | 2016-07-20 | 2019-03-23 | 2019-04-11
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | CWFSFERRY | New York City Ferry - Ferry Purchase and Upgrade | 2 | BID AWARD AND REGISTER CONTRCT | 2016-07-21 | 2016-08-04 | 2019-04-12 | 2019-04-26
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | CWFSFERRY | New York City Ferry - Ferry Purchase and Upgrade | 3 | CONSTRUCTION | 2016-08-05 | 2016-09-08 | 2019-04-27 | 2019-05-31
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | CWFSFERRY | New York City Ferry - Ferry Purchase and Upgrade | 4 | ORIGINAL EQUIP & FURNISHING | 2016-09-09 | 2016-09-18 | 2019-06-01 | 2019-06-10
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | CWFSFERRY | New York City Ferry - Ferry Purchase and Upgrade | 5 | SUBSTANTIAL COMPLETION | 2016-09-19 | 2016-10-03 | 2019-06-11 | 2019-06-25
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | CWFSFERRY | New York City Ferry - Ferry Purchase and Upgrade | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-10-04 | 2016-10-08 | 2019-06-26 | 2023-06-30
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | FSHELTER | East River Ferry Service Passenger Shelters | 1 | DESIGN | 2015-06-30 | 2015-07-19 | 2015-06-30 | 2015-07-19
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | FSHELTER | East River Ferry Service Passenger Shelters | 2 | BID AWARD AND REGISTER CONTRCT | 2015-07-20 | 2015-08-03 | 2015-07-20 | 2015-08-03
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | FSHELTER | East River Ferry Service Passenger Shelters | 3 | CONSTRUCTION | 2015-08-04 | 2015-09-07 | 2015-08-04 | 2015-09-07
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | FSHELTER | East River Ferry Service Passenger Shelters | 4 | ORIGINAL EQUIP & FURNISHING | 2015-09-08 | 2015-09-17 | 2015-09-08 | 2015-09-17
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | FSHELTER | East River Ferry Service Passenger Shelters | 5 | SUBSTANTIAL COMPLETION | 2015-09-18 | 2015-10-02 | 2015-09-18 | 2015-10-02
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | FSHELTER | East River Ferry Service Passenger Shelters | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-10-03 | 2015-10-07 | 2015-10-03 | 2022-10-07
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | HOMPORTDV | Homeport Redevelopment | 2 | BID AWARD AND REGISTER CONTRCT | 2005-01-21 | 2005-02-04 | 2005-03-04 | 2011-06-30
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | HOMPORTDV | Homeport Redevelopment | 3 | CONSTRUCTION | 2005-02-05 | 2007-07-01 | 2011-07-01 | 2011-06-30
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | HOMPORTDV | Homeport Redevelopment | 4 | ORIGINAL EQUIP & FURNISHING | 2007-07-02 | 2007-07-01 | 2011-07-01 | 2011-06-30
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | HOMPORTDV | Homeport Redevelopment | 5 | SUBSTANTIAL COMPLETION | 2007-07-02 | 2007-07-01 | 2011-07-01 | 2011-06-30
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | HOMPORTDV | Homeport Redevelopment | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2007-07-02 | 2007-07-06 | 2011-01-03 | 2018-06-30
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | IDF-SPOFF | Spofford Redevelopment | 1 | DESIGN | 2019-07-01 | 2019-07-20 | 2019-07-01 | 2019-07-20
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | IDF-SPOFF | Spofford Redevelopment | 2 | BID AWARD AND REGISTER CONTRCT | 2019-07-21 | 2019-08-04 | 2019-07-21 | 2019-08-04
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | IDF-SPOFF | Spofford Redevelopment | 3 | CONSTRUCTION | 2019-08-05 | 2019-09-08 | 2019-08-05 | 2019-09-08
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | IDF-SPOFF | Spofford Redevelopment | 4 | ORIGINAL EQUIP & FURNISHING | 2019-09-09 | 2019-09-18 | 2019-09-09 | 2019-09-18
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | IDF-SPOFF | Spofford Redevelopment | 5 | SUBSTANTIAL COMPLETION | 2019-09-19 | 2020-10-03 | 2019-09-19 | 2020-10-03
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | IDF-SPOFF | Spofford Redevelopment | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-10-04 | 2020-10-08 | 2020-10-04 | 2020-10-08
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | INDUSFUND | Industrial Fund | 1 | DESIGN | 2016-07-01 | 2016-07-20 | 2019-07-02 | 2022-04-11
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | INDUSFUND | Industrial Fund | 2 | BID AWARD AND REGISTER CONTRCT | 2016-07-21 | 2016-08-04 | 2022-04-12 | 2022-04-26
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | INDUSFUND | Industrial Fund | 3 | CONSTRUCTION | 2016-08-05 | 2016-09-08 | 2022-04-27 | 2022-05-31
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | INDUSFUND | Industrial Fund | 4 | ORIGINAL EQUIP & FURNISHING | 2016-09-09 | 2016-09-18 | 2022-06-01 | 2022-06-10
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | INDUSFUND | Industrial Fund | 5 | SUBSTANTIAL COMPLETION | 2016-09-19 | 2016-10-03 | 2022-06-11 | 2022-06-25
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | INDUSFUND | Industrial Fund | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-10-04 | 2016-10-08 | 2022-06-26 | 2028-06-30
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | INFRAHOUS | Housing Fund | 1 | DESIGN | 2016-07-01 | 2016-07-20 | 2016-07-01 | 2021-04-11
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | INFRAHOUS | Housing Fund | 2 | BID AWARD AND REGISTER CONTRCT | 2016-07-21 | 2016-08-04 | 2021-04-12 | 2021-04-26
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | INFRAHOUS | Housing Fund | 3 | CONSTRUCTION | 2016-08-05 | 2016-09-08 | 2021-04-27 | 2021-05-31
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | INFRAHOUS | Housing Fund | 4 | ORIGINAL EQUIP & FURNISHING | 2016-09-09 | 2016-09-18 | 2021-06-01 | 2021-06-10
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | INFRAHOUS | Housing Fund | 5 | SUBSTANTIAL COMPLETION | 2016-09-19 | 2016-10-03 | 2021-06-11 | 2021-06-25
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | INFRAHOUS | Housing Fund | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-10-04 | 2016-10-08 | 2021-06-26 | 2025-06-30
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | INFRANEIG | Neighborhood Fund | 1 | DESIGN | 2016-07-01 | 2016-07-20 | 2016-07-20 | 2024-04-11
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | INFRANEIG | Neighborhood Fund | 2 | BID AWARD AND REGISTER CONTRCT | 2016-07-21 | 2016-08-04 | 2024-04-12 | 2024-04-26
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | INFRANEIG | Neighborhood Fund | 3 | CONSTRUCTION | 2016-08-05 | 2016-09-08 | 2024-04-27 | 2024-05-31
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | INFRANEIG | Neighborhood Fund | 4 | ORIGINAL EQUIP & FURNISHING | 2016-09-09 | 2016-09-18 | 2024-06-01 | 2024-06-10
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | INFRANEIG | Neighborhood Fund | 5 | SUBSTANTIAL COMPLETION | 2016-09-19 | 2016-10-03 | 2024-06-11 | 2024-06-25
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | INFRANEIG | Neighborhood Fund | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-10-04 | 2016-10-08 | 2024-06-26 | 2029-06-24
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | LOWMANHUD | East River Waterfront | 1 | DESIGN | 2005-01-01 | 2005-01-20 | 2012-08-16 | 2014-08-17
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | LOWMANHUD | East River Waterfront | 2 | BID AWARD AND REGISTER CONTRCT | 2005-01-21 | 2007-02-04 | 2014-08-18 | 2016-05-01
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | LOWMANHUD | East River Waterfront | 3 | CONSTRUCTION | 2007-02-05 | 2007-02-04 | 2010-06-30 | 2011-06-30
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | LOWMANHUD | East River Waterfront | 4 | ORIGINAL EQUIP & FURNISHING | 2007-02-05 | 2007-02-04 | 2011-07-01 | 2011-06-30
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | LOWMANHUD | East River Waterfront | 5 | SUBSTANTIAL COMPLETION | 2007-02-05 | 2007-02-04 | 2011-07-01 | 2011-06-30
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | LOWMANHUD | East River Waterfront | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2007-02-05 | 2007-02-09 | 2014-05-31 | 2029-06-30
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | PASSSHIP2 | Passenger Ship Terminal - Cruise Industry Develp. | 1 | DESIGN | 2005-01-01 | 2005-01-20 | 2008-10-01 | 2008-10-20
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | PASSSHIP2 | Passenger Ship Terminal - Cruise Industry Develp. | 2 | BID AWARD AND REGISTER CONTRCT | 2005-01-21 | 2005-02-04 | 2008-10-21 | 2008-11-04
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | PASSSHIP2 | Passenger Ship Terminal - Cruise Industry Develp. | 3 | CONSTRUCTION | 2005-02-05 | 2007-07-01 | 2008-11-05 | 2011-03-31
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | PASSSHIP2 | Passenger Ship Terminal - Cruise Industry Develp. | 4 | ORIGINAL EQUIP & FURNISHING | 2007-07-02 | 2007-07-01 | 2011-04-01 | 2011-03-31
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | PASSSHIP2 | Passenger Ship Terminal - Cruise Industry Develp. | 5 | SUBSTANTIAL COMPLETION | 2007-07-02 | 2007-07-01 | 2011-04-01 | 2016-07-01
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | PASSSHIP2 | Passenger Ship Terminal - Cruise Industry Develp. | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2007-07-02 | 2007-07-06 | 2016-07-02 | 2020-06-30
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | PFLANDING | Rehabilitation of Ferry Landings | 1 | DEVELOP SCOPE | 2006-05-01 | 2007-04-30 | 2008-04-30 | 2009-04-29
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | PFLANDING | Rehabilitation of Ferry Landings | 2 | DESIGN START | 2007-05-01 | 2009-04-29 | 2009-04-30 | 2011-04-29
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | PFLANDING | Rehabilitation of Ferry Landings | 3 | CONSTRUCTION START | 2009-04-30 | 2011-04-29 | 2011-04-30 | 2013-04-28
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | PFLANDING | Rehabilitation of Ferry Landings | 4 | DESIGN | 2009-04-30 | 2011-04-29 | 2013-04-29 | 2013-05-18
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | PFLANDING | Rehabilitation of Ferry Landings | 5 | BID AWARD AND REGISTER CONTRCT | 2009-04-30 | 2011-04-29 | 2013-05-19 | 2013-06-02
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | PFLANDING | Rehabilitation of Ferry Landings | 6 | CONSTRUCTION | 2009-04-30 | 2011-04-29 | 2013-06-03 | 2013-07-07
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | PFLANDING | Rehabilitation of Ferry Landings | 7 | ORIGINAL EQUIP & FURNISHING | 2009-04-30 | 2011-04-29 | 2013-07-08 | 2013-07-17
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | PFLANDING | Rehabilitation of Ferry Landings | 8 | SUBSTANTIAL COMPLETION | 2009-04-30 | 2011-04-29 | 2013-07-18 | 2013-08-01
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | PFLANDING | Rehabilitation of Ferry Landings | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2009-04-30 | 2011-04-29 | 2013-08-02 | 2025-06-30
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | PSG6-7 | Port Security Grant Funds | 1 | DESIGN | 2008-04-01 | 2009-04-20 | 2010-04-01 | 2011-04-20
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | PSG6-7 | Port Security Grant Funds | 2 | BID AWARD AND REGISTER CONTRCT | 2009-04-21 | 2009-04-20 | 2009-04-20 | 2009-04-20
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | PSG6-7 | Port Security Grant Funds | 3 | CONSTRUCTION | 2009-04-21 | 2009-04-20 | 2009-04-21 | 2009-04-20
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | PSG6-7 | Port Security Grant Funds | 4 | ORIGINAL EQUIP & FURNISHING | 2009-04-21 | 2009-04-20 | 2009-04-21 | 2009-04-20
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | PSG6-7 | Port Security Grant Funds | 5 | SUBSTANTIAL COMPLETION | 2009-04-21 | 2009-04-20 | 2009-04-21 | 2009-04-20
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | PSG6-7 | Port Security Grant Funds | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2009-04-21 | 2009-04-25 | 2007-04-21 | 2020-06-30
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | RBWTRMAIN | Rockaway Boardwalk - Water Main Improvement | 1 | DESIGN | 2016-07-01 | 2016-07-20 | 2016-07-01 | 2020-07-20
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | RBWTRMAIN | Rockaway Boardwalk - Water Main Improvement | 2 | BID AWARD AND REGISTER CONTRCT | 2016-07-21 | 2016-08-04 | 2020-07-21 | 2020-08-04
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | RBWTRMAIN | Rockaway Boardwalk - Water Main Improvement | 3 | CONSTRUCTION | 2016-08-05 | 2016-09-08 | 2020-08-05 | 2020-09-08
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | RBWTRMAIN | Rockaway Boardwalk - Water Main Improvement | 4 | ORIGINAL EQUIP & FURNISHING | 2016-09-09 | 2016-09-18 | 2020-09-09 | 2020-09-18
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | RBWTRMAIN | Rockaway Boardwalk - Water Main Improvement | 5 | SUBSTANTIAL COMPLETION | 2016-09-19 | 2016-10-03 | 2020-09-19 | 2020-10-03
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | RBWTRMAIN | Rockaway Boardwalk - Water Main Improvement | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-10-04 | 2016-10-08 | 2020-10-04 | 2024-10-08
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | RS-PH1 | Raise Shoreline- Phase 1 | 1 | DESIGN | 2019-08-30 | 2019-09-18 | 2019-08-30 | 2019-09-18
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | RS-PH1 | Raise Shoreline- Phase 1 | 2 | BID AWARD AND REGISTER CONTRCT | 2019-09-19 | 2019-10-03 | 2019-09-19 | 2019-10-03
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | RS-PH1 | Raise Shoreline- Phase 1 | 3 | CONSTRUCTION | 2019-10-04 | 2019-11-07 | 2019-10-04 | 2019-11-07
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | RS-PH1 | Raise Shoreline- Phase 1 | 4 | ORIGINAL EQUIP & FURNISHING | 2019-11-08 | 2019-11-17 | 2019-11-08 | 2019-11-17
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | RS-PH1 | Raise Shoreline- Phase 1 | 5 | SUBSTANTIAL COMPLETION | 2019-11-18 | 2019-12-02 | 2019-11-18 | 2019-12-02
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | RS-PH1 | Raise Shoreline- Phase 1 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-03 | 2020-12-07 | 2019-12-03 | 2022-12-07
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND000 | Project Management for NYC Health + Hospitals Sandy Projects | 1 | DESIGN | 2015-07-01 | 2015-07-20 | 2015-07-01 | 2015-07-20
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND000 | Project Management for NYC Health + Hospitals Sandy Projects | 2 | BID AWARD AND REGISTER CONTRCT | 2015-07-21 | 2015-08-04 | 2015-07-21 | 2015-08-04
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND000 | Project Management for NYC Health + Hospitals Sandy Projects | 3 | CONSTRUCTION | 2015-08-05 | 2015-09-08 | 2015-08-05 | 2015-09-08
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND000 | Project Management for NYC Health + Hospitals Sandy Projects | 4 | ORIGINAL EQUIP & FURNISHING | 2015-09-09 | 2015-09-18 | 2015-09-09 | 2015-09-18
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND000 | Project Management for NYC Health + Hospitals Sandy Projects | 5 | SUBSTANTIAL COMPLETION | 2015-09-19 | 2015-10-03 | 2015-09-19 | 2015-10-03
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND000 | Project Management for NYC Health + Hospitals Sandy Projects | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-10-04 | 2019-10-08 | 2015-10-04 | 2024-10-08
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDEDCAM | EDC - Hurricane Sandy - Asset Management | 1 | DESIGN | 2016-01-01 | 2016-01-20 | 2016-01-01 | 2016-01-20
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDEDCAM | EDC - Hurricane Sandy - Asset Management | 2 | BID AWARD AND REGISTER CONTRCT | 2016-01-21 | 2016-06-30 | 2016-01-21 | 2016-06-30
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDEDCAM | EDC - Hurricane Sandy - Asset Management | 3 | CONSTRUCTION | 2016-07-01 | 2017-06-30 | 2016-07-01 | 2017-06-30
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDEDCAM | EDC - Hurricane Sandy - Asset Management | 4 | ORIGINAL EQUIP & FURNISHING | 2017-07-01 | 2020-06-30 | 2017-07-01 | 2020-06-30
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDEDCAM | EDC - Hurricane Sandy - Asset Management | 5 | SUBSTANTIAL COMPLETION | 2020-07-01 | 2020-06-30 | 2020-07-01 | 2020-06-30
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDEDCAM | EDC - Hurricane Sandy - Asset Management | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-07-01 | 2020-07-05 | 2020-07-01 | 2025-07-05
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDY4-03 | Sandy - Rockaway Beach: Long-Term RC | 1 | DESIGN | 2016-01-01 | 2016-01-20 | 2016-01-01 | 2016-01-20
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDY4-03 | Sandy - Rockaway Beach: Long-Term RC | 2 | BID AWARD AND REGISTER CONTRCT | 2016-01-21 | 2016-06-30 | 2016-01-21 | 2016-06-30
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDY4-03 | Sandy - Rockaway Beach: Long-Term RC | 3 | CONSTRUCTION | 2016-07-01 | 2017-06-30 | 2016-07-01 | 2017-06-30
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDY4-03 | Sandy - Rockaway Beach: Long-Term RC | 4 | ORIGINAL EQUIP & FURNISHING | 2017-07-01 | 2020-06-30 | 2017-07-01 | 2020-06-30
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDY4-03 | Sandy - Rockaway Beach: Long-Term RC | 5 | SUBSTANTIAL COMPLETION | 2020-07-01 | 2020-06-30 | 2020-07-01 | 2020-06-30
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDY4-03 | Sandy - Rockaway Beach: Long-Term RC | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-07-01 | 2020-07-05 | 2020-07-01 | 2024-07-05
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | TENANTIMP | Tenant Improvement Fund | 1 | DESIGN | 2017-07-01 | 2017-07-20 | 2020-03-23 | 2020-04-11
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | TENANTIMP | Tenant Improvement Fund | 2 | BID AWARD AND REGISTER CONTRCT | 2017-07-21 | 2017-08-04 | 2020-04-12 | 2020-04-26
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | TENANTIMP | Tenant Improvement Fund | 3 | CONSTRUCTION | 2017-08-05 | 2017-09-08 | 2020-04-27 | 2020-05-31
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | TENANTIMP | Tenant Improvement Fund | 4 | ORIGINAL EQUIP & FURNISHING | 2017-09-09 | 2017-09-18 | 2020-06-01 | 2020-06-10
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | TENANTIMP | Tenant Improvement Fund | 5 | SUBSTANTIAL COMPLETION | 2017-09-19 | 2017-10-03 | 2020-06-11 | 2020-06-25
20201123 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | TENANTIMP | Tenant Improvement Fund | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-10-04 | 2017-10-08 | 2020-06-26 | 2025-06-30
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM11IHWH | INSTANTANEOUS HOT WATER HEATERS | 1 | DESIGN | 2011-01-01 | 2011-06-29 | 2013-11-18 | 2014-04-11
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM11IHWH | INSTANTANEOUS HOT WATER HEATERS | 2 | BID AWARD AND REGISTER CONTRCT | 2011-06-30 | 2011-11-21 | 2014-04-12 | 2015-03-11
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM11IHWH | INSTANTANEOUS HOT WATER HEATERS | 3 | CONSTRUCTION | 2011-11-22 | 2012-11-20 | 2015-03-12 | 2017-03-25
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM11IHWH | INSTANTANEOUS HOT WATER HEATERS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-11-21 | 2013-05-19 | 2015-03-12 | 2017-03-25
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM11IHWH | INSTANTANEOUS HOT WATER HEATERS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-11-21 | 2013-05-19 | 2017-03-26 | 2021-03-24
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM13GCON | GENERAL CONSTRUCTION CITYWIDE | 1 | DESIGN | 2013-06-01 | 2013-11-27 | 2014-04-01 | 2019-09-01
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM13GCON | GENERAL CONSTRUCTION CITYWIDE | 2 | BID AWARD AND REGISTER CONTRCT | 2013-11-28 | 2014-04-21 | 2019-09-02 | 2020-01-24
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM13GCON | GENERAL CONSTRUCTION CITYWIDE | 3 | CONSTRUCTION | 2014-04-22 | 2015-04-21 | 2020-01-25 | 2021-01-23
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM13GCON | GENERAL CONSTRUCTION CITYWIDE | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-04-22 | 2015-10-18 | 2020-01-25 | 2021-01-23
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM13GCON | GENERAL CONSTRUCTION CITYWIDE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-04-22 | 2015-10-18 | 2021-01-24 | 2021-07-22
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM13GCON | GENERAL CONSTRUCTION CITYWIDE | 7 | DEVELOP SCOPE | 2015-04-22 | 2015-10-18 | 2021-07-23 | 2021-10-20
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM13GCON | GENERAL CONSTRUCTION CITYWIDE | 8 | PRELIMINARY DESIGN | 2015-04-22 | 2015-10-18 | 2021-10-21 | 2022-02-17
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM13GCON | GENERAL CONSTRUCTION CITYWIDE | 9 | FINAL DESIGN | 2015-04-22 | 2015-10-18 | 2022-02-18 | 2022-08-16
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM13GCON | GENERAL CONSTRUCTION CITYWIDE | 10 | BID AWARD AND REGISTER CONTRCT | 2015-04-22 | 2015-10-18 | 2022-08-17 | 2022-11-14
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM13GCON | GENERAL CONSTRUCTION CITYWIDE | 11 | CONSTRUCTION TO 25% | 2015-04-22 | 2015-10-18 | 2022-11-15 | 2023-03-14
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM13GCON | GENERAL CONSTRUCTION CITYWIDE | 12 | CONSTRUCTION TO 50% | 2015-04-22 | 2015-10-18 | 2023-03-15 | 2023-07-12
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM13GCON | GENERAL CONSTRUCTION CITYWIDE | 13 | CONSTRUCTION TO 75% | 2015-04-22 | 2015-10-18 | 2023-07-13 | 2023-11-09
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM13GCON | GENERAL CONSTRUCTION CITYWIDE | 14 | ORIGINAL EQUIP & FURNISHING | 2015-04-22 | 2015-10-18 | 2023-11-10 | 2024-02-07
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM13GCON | GENERAL CONSTRUCTION CITYWIDE | 15 | SUBSTANTIAL COMPLETION | 2015-04-22 | 2015-10-18 | 2024-02-08 | 2024-04-07
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM13GCON | GENERAL CONSTRUCTION CITYWIDE | 16 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-04-22 | 2015-10-18 | 2024-04-08 | 2024-05-07
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM13VAEL | CITYWIDE ELEVATOR REPAIRS | 1 | DESIGN | 2012-08-12 | 2013-02-07 | 2012-12-04 | 2014-02-05
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM13VAEL | CITYWIDE ELEVATOR REPAIRS | 2 | BID AWARD AND REGISTER CONTRCT | 2013-02-08 | 2013-07-02 | 2014-02-06 | 2014-07-31
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM13VAEL | CITYWIDE ELEVATOR REPAIRS | 3 | CONSTRUCTION | 2013-07-03 | 2014-07-02 | 2014-08-01 | 2015-07-31
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM13VAEL | CITYWIDE ELEVATOR REPAIRS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-07-03 | 2014-12-29 | 2014-08-01 | 2015-07-31
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM13VAEL | CITYWIDE ELEVATOR REPAIRS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-07-03 | 2014-12-29 | 2015-08-01 | 2020-07-29
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM14VAUP | Major Renovations-Brickwork and Roofs at Sotomayer Houses | 1 | DESIGN | 2014-01-01 | 2014-06-29 | 2012-08-01 | 2014-07-31
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM14VAUP | Major Renovations-Brickwork and Roofs at Sotomayer Houses | 2 | BID AWARD AND REGISTER CONTRCT | 2014-06-30 | 2014-11-21 | 2014-08-01 | 2015-05-31
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM14VAUP | Major Renovations-Brickwork and Roofs at Sotomayer Houses | 3 | CONSTRUCTION | 2014-11-22 | 2015-11-21 | 2015-06-01 | 2019-08-01
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM14VAUP | Major Renovations-Brickwork and Roofs at Sotomayer Houses | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-11-22 | 2016-05-19 | 2015-06-01 | 2019-08-01
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM14VAUP | Major Renovations-Brickwork and Roofs at Sotomayer Houses | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-11-22 | 2016-05-19 | 2019-08-02 | 2020-08-02
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM15HMLS | HOMELESS INITIATIVE | 1 | DESIGN | 2015-10-01 | 2016-03-28 | 2015-10-27 | 2016-05-13
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM15HMLS | HOMELESS INITIATIVE | 2 | BID AWARD AND REGISTER CONTRCT | 2016-03-29 | 2016-08-20 | 2016-05-14 | 2016-11-09
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM15HMLS | HOMELESS INITIATIVE | 3 | CONSTRUCTION | 2016-08-21 | 2017-08-20 | 2016-11-10 | 2019-11-09
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM15HMLS | HOMELESS INITIATIVE | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-08-21 | 2018-02-16 | 2016-11-10 | 2019-11-09
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM15HMLS | HOMELESS INITIATIVE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-08-21 | 2018-02-16 | 2019-11-10 | 2022-06-11
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM15SCVA | SECURITY ENHANCEMENTS AT VARIOUS LOCATIONS | 1 | DESIGN | 2015-01-02 | 2015-06-30 | 2015-01-02 | 2015-06-30
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM15SCVA | SECURITY ENHANCEMENTS AT VARIOUS LOCATIONS | 2 | BID AWARD AND REGISTER CONTRCT | 2015-07-01 | 2015-11-22 | 2015-07-01 | 2015-11-22
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM15SCVA | SECURITY ENHANCEMENTS AT VARIOUS LOCATIONS | 3 | CONSTRUCTION | 2015-11-23 | 2016-11-21 | 2015-11-23 | 2016-11-21
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM15SCVA | SECURITY ENHANCEMENTS AT VARIOUS LOCATIONS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-11-22 | 2017-05-20 | 2015-11-23 | 2016-11-21
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM15SCVA | SECURITY ENHANCEMENTS AT VARIOUS LOCATIONS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-11-22 | 2017-05-20 | 2016-11-22 | 2020-11-20
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM15SLVA | SECURITY INITIATIVES - LIGHTING AT VARIOUS DEVELOPMENTS | 1 | DESIGN | 2015-01-02 | 2015-06-30 | 2015-01-02 | 2015-06-30
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM15SLVA | SECURITY INITIATIVES - LIGHTING AT VARIOUS DEVELOPMENTS | 2 | BID AWARD AND REGISTER CONTRCT | 2015-07-01 | 2015-11-22 | 2015-07-01 | 2015-11-22
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM15SLVA | SECURITY INITIATIVES - LIGHTING AT VARIOUS DEVELOPMENTS | 3 | CONSTRUCTION | 2015-11-23 | 2016-11-21 | 2015-11-23 | 2016-11-21
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM15SLVA | SECURITY INITIATIVES - LIGHTING AT VARIOUS DEVELOPMENTS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-11-22 | 2017-05-20 | 2015-11-23 | 2016-11-21
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM15SLVA | SECURITY INITIATIVES - LIGHTING AT VARIOUS DEVELOPMENTS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-11-22 | 2017-05-20 | 2016-11-22 | 2021-11-20
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM16FACD | BUILDING FACADES | 1 | DESIGN | 2015-02-12 | 2015-08-10 | 2015-09-10 | 2015-10-30
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM16FACD | BUILDING FACADES | 2 | BID AWARD AND REGISTER CONTRCT | 2015-08-11 | 2016-01-02 | 2015-10-31 | 2016-04-27
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM16FACD | BUILDING FACADES | 3 | CONSTRUCTION | 2016-01-03 | 2017-01-01 | 2016-04-28 | 2019-01-01
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM16FACD | BUILDING FACADES | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-01-02 | 2017-06-30 | 2016-04-28 | 2019-01-01
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM16FACD | BUILDING FACADES | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-01-02 | 2017-06-30 | 2019-01-02 | 2020-01-01
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM16MRVR | ROOF WORK TO PREVENT MOLD AT VARIOUS DEVELOPMENTS | 1 | DESIGN | 2014-04-09 | 2014-10-05 | 2014-04-09 | 2014-10-05
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM16MRVR | ROOF WORK TO PREVENT MOLD AT VARIOUS DEVELOPMENTS | 2 | BID AWARD AND REGISTER CONTRCT | 2014-10-06 | 2015-05-11 | 2014-10-06 | 2015-05-11
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM16MRVR | ROOF WORK TO PREVENT MOLD AT VARIOUS DEVELOPMENTS | 3 | CONSTRUCTION | 2015-05-12 | 2020-12-31 | 2015-05-12 | 2020-12-31
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM16MRVR | ROOF WORK TO PREVENT MOLD AT VARIOUS DEVELOPMENTS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-01-01 | 2021-06-29 | 2015-05-12 | 2020-12-31
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM16MRVR | ROOF WORK TO PREVENT MOLD AT VARIOUS DEVELOPMENTS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-01-01 | 2021-06-29 | 2021-01-01 | 2021-06-29
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18BOIL | MOBLE BOILERS AT VARIOUS NYCHA DEVELOPMENTS | 1 | DESIGN | 2018-01-02 | 2018-06-30 | 2018-01-02 | 2018-06-30
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18BOIL | MOBLE BOILERS AT VARIOUS NYCHA DEVELOPMENTS | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18BOIL | MOBLE BOILERS AT VARIOUS NYCHA DEVELOPMENTS | 3 | CONSTRUCTION | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18BOIL | MOBLE BOILERS AT VARIOUS NYCHA DEVELOPMENTS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-28 | 2020-06-24 | 2018-12-28 | 2019-12-27
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18BOIL | MOBLE BOILERS AT VARIOUS NYCHA DEVELOPMENTS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-28 | 2020-06-24 | 2019-12-28 | 2020-06-24
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CDCP | BUILDING IMPROVEMENTS | 1 | DESIGN | 2018-02-05 | 2018-08-03 | 2018-02-05 | 2018-08-03
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CDCP | BUILDING IMPROVEMENTS | 2 | BID AWARD AND REGISTER CONTRCT | 2018-08-04 | 2019-01-30 | 2018-08-04 | 2019-01-30
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CDCP | BUILDING IMPROVEMENTS | 3 | CONSTRUCTION | 2019-01-31 | 2020-01-30 | 2019-01-31 | 2020-01-30
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CDCP | BUILDING IMPROVEMENTS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-01-31 | 2020-07-28 | 2019-01-31 | 2020-01-30
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CDCP | BUILDING IMPROVEMENTS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-01-31 | 2020-07-28 | 2020-01-31 | 2020-07-28
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CSVA | CONCRETE SLABS AT VARIOUS DEVELOPMENTS | 1 | DESIGN | 2017-03-15 | 2018-02-26 | 2017-03-15 | 2018-02-26
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CSVA | CONCRETE SLABS AT VARIOUS DEVELOPMENTS | 2 | BID AWARD AND REGISTER CONTRCT | 2018-02-27 | 2018-06-07 | 2018-02-27 | 2018-06-07
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CSVA | CONCRETE SLABS AT VARIOUS DEVELOPMENTS | 3 | CONSTRUCTION | 2018-06-08 | 2021-06-06 | 2018-06-08 | 2021-06-06
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CSVA | CONCRETE SLABS AT VARIOUS DEVELOPMENTS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-06-07 | 2021-12-03 | 2018-06-08 | 2021-06-06
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CSVA | CONCRETE SLABS AT VARIOUS DEVELOPMENTS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-06-07 | 2021-12-03 | 2021-06-07 | 2021-12-03
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18HEAT | HEATING SYSTEM IMPROVEMENTS AT NYCHA DEVELOPMENTS CITYWIDE | 1 | DESIGN | 2018-02-01 | 2018-09-30 | 2018-02-01 | 2018-09-30
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18HEAT | HEATING SYSTEM IMPROVEMENTS AT NYCHA DEVELOPMENTS CITYWIDE | 2 | BID AWARD AND REGISTER CONTRCT | 2018-10-01 | 2019-07-31 | 2018-10-01 | 2019-07-31
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18HEAT | HEATING SYSTEM IMPROVEMENTS AT NYCHA DEVELOPMENTS CITYWIDE | 3 | CONSTRUCTION | 2019-08-01 | 2020-07-30 | 2019-08-01 | 2020-07-30
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18HEAT | HEATING SYSTEM IMPROVEMENTS AT NYCHA DEVELOPMENTS CITYWIDE | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-07-31 | 2021-01-26 | 2019-08-01 | 2020-07-30
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18HEAT | HEATING SYSTEM IMPROVEMENTS AT NYCHA DEVELOPMENTS CITYWIDE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-07-31 | 2021-01-26 | 2020-07-31 | 2021-01-26
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18IHWH | INSTANTANEOUS HOT WATER HEATERS | 1 | DESIGN | 2018-06-01 | 2018-11-27 | 2018-06-01 | 2018-11-27
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18IHWH | INSTANTANEOUS HOT WATER HEATERS | 2 | BID AWARD AND REGISTER CONTRCT | 2018-11-28 | 2019-04-21 | 2018-11-28 | 2019-04-21
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18IHWH | INSTANTANEOUS HOT WATER HEATERS | 3 | CONSTRUCTION | 2019-04-22 | 2020-04-20 | 2019-04-22 | 2020-04-20
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18IHWH | INSTANTANEOUS HOT WATER HEATERS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-04-21 | 2020-10-17 | 2019-04-22 | 2020-04-20
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18IHWH | INSTANTANEOUS HOT WATER HEATERS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-04-21 | 2020-10-17 | 2020-04-21 | 2020-10-17
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18PNAP | Gas Risers | 1 | DESIGN | 2018-01-02 | 2018-06-30 | 2018-01-02 | 2018-06-30
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18PNAP | Gas Risers | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18PNAP | Gas Risers | 3 | CONSTRUCTION | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18PNAP | Gas Risers | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-28 | 2020-06-24 | 2018-12-28 | 2019-12-27
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18PNAP | Gas Risers | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-28 | 2020-06-24 | 2019-12-28 | 2020-06-24
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18RAEX | EXTERNAL COMPACTORS-BULK CRUSHERS | 1 | DESIGN | 2018-01-02 | 2018-06-30 | 2018-01-02 | 2018-06-30
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18RAEX | EXTERNAL COMPACTORS-BULK CRUSHERS | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18RAEX | EXTERNAL COMPACTORS-BULK CRUSHERS | 3 | CONSTRUCTION | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18RAEX | EXTERNAL COMPACTORS-BULK CRUSHERS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-28 | 2020-06-24 | 2018-12-28 | 2019-12-27
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18RAEX | EXTERNAL COMPACTORS-BULK CRUSHERS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-28 | 2020-06-24 | 2019-12-28 | 2020-06-24
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18RSPL | Citywide Gas Risers, Steam Distribution, Condensate Lines | 1 | DESIGN | 2018-01-02 | 2018-06-30 | 2018-01-02 | 2018-06-30
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18RSPL | Citywide Gas Risers, Steam Distribution, Condensate Lines | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18RSPL | Citywide Gas Risers, Steam Distribution, Condensate Lines | 3 | CONSTRUCTION | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18RSPL | Citywide Gas Risers, Steam Distribution, Condensate Lines | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-28 | 2020-06-24 | 2018-12-28 | 2019-12-27
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18RSPL | Citywide Gas Risers, Steam Distribution, Condensate Lines | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-28 | 2020-06-24 | 2019-12-28 | 2020-06-24
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM19DGV2 | DIGITAL VAN | 1 | DESIGN | 2018-01-02 | 2018-06-30 | 2018-01-02 | 2018-06-30
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM19DGV2 | DIGITAL VAN | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM19DGV2 | DIGITAL VAN | 3 | CONSTRUCTION | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM19DGV2 | DIGITAL VAN | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-28 | 2020-06-24 | 2018-12-28 | 2019-12-27
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM19DGV2 | DIGITAL VAN | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-28 | 2020-06-24 | 2019-12-28 | 2020-06-24
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM19MOCJ | Installation of LED Exterior Lighting Citywide | 1 | DESIGN | 2018-01-02 | 2018-06-30 | 2018-01-02 | 2018-06-30
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM19MOCJ | Installation of LED Exterior Lighting Citywide | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM19MOCJ | Installation of LED Exterior Lighting Citywide | 3 | CONSTRUCTION | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM19MOCJ | Installation of LED Exterior Lighting Citywide | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-28 | 2020-06-24 | 2018-12-28 | 2019-12-27
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM19MOCJ | Installation of LED Exterior Lighting Citywide | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-28 | 2020-06-24 | 2019-12-28 | 2020-06-24
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM20DMSC | SENIOR CENTER RENOVATION- DYCKMAN AND MARBLE HILL | 1 | DESIGN | 2019-09-01 | 2020-02-27 | 2019-09-01 | 2020-02-27
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM20DMSC | SENIOR CENTER RENOVATION- DYCKMAN AND MARBLE HILL | 2 | BID AWARD AND REGISTER CONTRCT | 2020-02-28 | 2020-08-25 | 2020-02-28 | 2020-08-25
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM20DMSC | SENIOR CENTER RENOVATION- DYCKMAN AND MARBLE HILL | 3 | CONSTRUCTION | 2020-08-26 | 2021-08-25 | 2020-08-26 | 2021-08-25
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM20DMSC | SENIOR CENTER RENOVATION- DYCKMAN AND MARBLE HILL | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-08-26 | 2022-02-21 | 2020-08-26 | 2021-08-25
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM20DMSC | SENIOR CENTER RENOVATION- DYCKMAN AND MARBLE HILL | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-08-26 | 2022-02-21 | 2021-08-26 | 2022-02-21
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM20ECFL | ELLIOTT CHELSEA AND FULTON LIGHTING FOR PARKS | 1 | DESIGN | 2019-09-01 | 2020-02-27 | 2019-09-01 | 2020-02-27
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM20ECFL | ELLIOTT CHELSEA AND FULTON LIGHTING FOR PARKS | 2 | BID AWARD AND REGISTER CONTRCT | 2020-02-28 | 2020-08-25 | 2020-02-28 | 2020-08-25
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM20ECFL | ELLIOTT CHELSEA AND FULTON LIGHTING FOR PARKS | 3 | CONSTRUCTION | 2020-08-26 | 2021-08-25 | 2020-08-26 | 2021-08-25
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM20ECFL | ELLIOTT CHELSEA AND FULTON LIGHTING FOR PARKS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-08-26 | 2022-02-21 | 2020-08-26 | 2021-08-25
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM20ECFL | ELLIOTT CHELSEA AND FULTON LIGHTING FOR PARKS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-08-26 | 2022-02-21 | 2021-08-26 | 2022-02-21
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM20QWGR | BEAUTIFICATION OF QUEENSBRIDGE HOUSES AND WOODSIDE HOUSES | 1 | DESIGN | 2019-09-01 | 2020-02-27 | 2019-09-01 | 2020-02-27
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM20QWGR | BEAUTIFICATION OF QUEENSBRIDGE HOUSES AND WOODSIDE HOUSES | 2 | BID AWARD AND REGISTER CONTRCT | 2020-02-28 | 2020-08-25 | 2020-02-28 | 2020-08-25
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM20QWGR | BEAUTIFICATION OF QUEENSBRIDGE HOUSES AND WOODSIDE HOUSES | 3 | CONSTRUCTION | 2020-08-26 | 2021-08-25 | 2020-08-26 | 2021-08-25
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM20QWGR | BEAUTIFICATION OF QUEENSBRIDGE HOUSES AND WOODSIDE HOUSES | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-08-26 | 2022-02-21 | 2020-08-26 | 2021-08-25
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM20QWGR | BEAUTIFICATION OF QUEENSBRIDGE HOUSES AND WOODSIDE HOUSES | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-08-26 | 2022-02-21 | 2021-08-26 | 2022-02-21
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM20WMEX | WASTE MANAGEMENT EXTERIOR COMPACTORS | 1 | DESIGN | 2019-09-01 | 2020-02-27 | 2019-09-01 | 2020-02-27
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM20WMEX | WASTE MANAGEMENT EXTERIOR COMPACTORS | 2 | BID AWARD AND REGISTER CONTRCT | 2020-02-28 | 2020-08-25 | 2020-02-28 | 2020-08-25
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM20WMEX | WASTE MANAGEMENT EXTERIOR COMPACTORS | 3 | CONSTRUCTION | 2020-08-26 | 2021-08-25 | 2020-08-26 | 2021-08-25
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM20WMEX | WASTE MANAGEMENT EXTERIOR COMPACTORS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-08-26 | 2022-02-21 | 2020-08-26 | 2021-08-25
20201123 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM20WMEX | WASTE MANAGEMENT EXTERIOR COMPACTORS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-08-26 | 2022-02-21 | 2021-08-26 | 2022-02-21
20201123 | CITYWIDE | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | CMESECURE | OCME - Agencywide Physical Security System Upgrades | 1 | DESIGN | 2020-09-01 | 2021-03-09 | 2020-09-01 | 2021-03-09
20201123 | CITYWIDE | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | CMESECURE | OCME - Agencywide Physical Security System Upgrades | 2 | BID AWARD AND REGISTER CONTRCT | 2021-03-10 | 2021-09-05 | 2021-03-10 | 2021-09-05
20201123 | CITYWIDE | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | CMESECURE | OCME - Agencywide Physical Security System Upgrades | 3 | CONSTRUCTION | 2021-09-06 | 2022-05-01 | 2021-09-06 | 2022-05-01
20201123 | CITYWIDE | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | CMESECURE | OCME - Agencywide Physical Security System Upgrades | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-05-02 | 2022-06-30 | 2022-05-02 | 2022-06-30
20201123 | CITYWIDE | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82VCLIN | EMERGENCY FUNDING FOR VARIOUS CLINICS | 1 | DEVELOP SCOPE | 2005-09-15 | 2005-12-13 | 2021-06-01 | 2021-11-27
20201123 | CITYWIDE | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82VCLIN | EMERGENCY FUNDING FOR VARIOUS CLINICS | 2 | PRELIMINARY DESIGN | 2005-12-14 | 2006-04-12 | 2021-11-28 | 2028-12-31
20201123 | CITYWIDE | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82VCLIN | EMERGENCY FUNDING FOR VARIOUS CLINICS | 3 | FINAL DESIGN | 2006-04-13 | 2006-10-09 | 2029-01-01 | 2029-06-29
20201123 | CITYWIDE | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82VCLIN | EMERGENCY FUNDING FOR VARIOUS CLINICS | 4 | BID AWARD AND REGISTER CONTRCT | 2006-10-10 | 2007-01-07 | 2029-01-01 | 2029-06-29
20201123 | CITYWIDE | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82VCLIN | EMERGENCY FUNDING FOR VARIOUS CLINICS | 5 | CONSTRUCTION TO 25% | 2007-01-08 | 2007-05-07 | 2029-01-01 | 2029-06-29
20201123 | CITYWIDE | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82VCLIN | EMERGENCY FUNDING FOR VARIOUS CLINICS | 6 | CONSTRUCTION TO 50% | 2007-05-08 | 2007-09-04 | 2029-01-01 | 2029-06-29
20201123 | CITYWIDE | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82VCLIN | EMERGENCY FUNDING FOR VARIOUS CLINICS | 7 | CONSTRUCTION TO 75% | 2007-09-05 | 2008-01-02 | 2029-01-01 | 2029-06-29
20201123 | CITYWIDE | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82VCLIN | EMERGENCY FUNDING FOR VARIOUS CLINICS | 8 | ORIGINAL EQUIP & FURNISHING | 2008-01-03 | 2008-04-01 | 2029-01-01 | 2029-06-29
20201123 | CITYWIDE | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82VCLIN | EMERGENCY FUNDING FOR VARIOUS CLINICS | 9 | SUBSTANTIAL COMPLETION | 2008-04-02 | 2008-05-31 | 2029-01-01 | 2029-06-29
20201123 | CITYWIDE | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82VCLIN | EMERGENCY FUNDING FOR VARIOUS CLINICS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-06-01 | 2008-06-30 | 2029-01-01 | 2029-06-29
20201123 | CITYWIDE | 819 | HEALTH AND HOSPITALS CORP | 02201601 | HHC PRIMARY HEALTH CLINICS | 1 | DESIGN | 2020-12-31 | 2022-05-24 | 2023-01-31 | 2025-05-24
20201123 | CITYWIDE | 819 | HEALTH AND HOSPITALS CORP | 02201602 | UPGRADE IDF AND MDF ROOMS (LAN ENVIRONMENTALS) | 1 | DESIGN | 2017-11-09 | 2019-04-02 | 2019-11-09 | 2021-04-01
20201123 | CITYWIDE | 819 | HEALTH AND HOSPITALS CORP | 02201602 | UPGRADE IDF AND MDF ROOMS (LAN ENVIRONMENTALS) | 2 | CONSTRUCTION | 2019-04-03 | 2021-04-01 | 2021-04-02 | 2023-04-01
20201123 | CITYWIDE | 819 | HEALTH AND HOSPITALS CORP | 02201602 | UPGRADE IDF AND MDF ROOMS (LAN ENVIRONMENTALS) | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-04-02 | 2021-06-30 | 2023-04-02 | 2023-06-30
20201123 | CITYWIDE | 819 | HEALTH AND HOSPITALS CORP | 02202101 | SYSTEM WIDE ELEVATOR DOOR LOCK MONITORING | 1 | DESIGN | 2020-03-06 | 2021-07-28 | 2020-03-06 | 2021-07-28
20201123 | CITYWIDE | 819 | HEALTH AND HOSPITALS CORP | 02202101 | SYSTEM WIDE ELEVATOR DOOR LOCK MONITORING | 2 | CONSTRUCTION | 2021-07-29 | 2023-07-28 | 2021-07-29 | 2023-07-28
20201123 | CITYWIDE | 819 | HEALTH AND HOSPITALS CORP | 02202101 | SYSTEM WIDE ELEVATOR DOOR LOCK MONITORING | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-07-29 | 2023-10-26 | 2023-07-29 | 2023-10-26
20201123 | CITYWIDE | 819 | HEALTH AND HOSPITALS CORP | 022021PM | PM/CM Services | 1 | DESIGN | 2021-03-06 | 2022-07-28 | 2021-03-06 | 2022-07-28
20201123 | CITYWIDE | 819 | HEALTH AND HOSPITALS CORP | 022021PM | PM/CM Services | 2 | CONSTRUCTION | 2022-07-29 | 2024-07-27 | 2022-07-29 | 2024-07-27
20201123 | CITYWIDE | 819 | HEALTH AND HOSPITALS CORP | 022021PM | PM/CM Services | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-07-28 | 2024-10-25 | 2024-07-28 | 2024-10-25
20201123 | CITYWIDE | 819 | HEALTH AND HOSPITALS CORP | 72201602 | CORRECTIONAL HEALTH: MINI CLINICS | 1 | DESIGN | 2016-05-13 | 2017-10-04 | 2016-05-13 | 2017-10-04
20201123 | CITYWIDE | 819 | HEALTH AND HOSPITALS CORP | 72201602 | CORRECTIONAL HEALTH: MINI CLINICS | 2 | CONSTRUCTION | 2017-10-05 | 2020-10-03 | 2017-10-05 | 2020-10-03
20201123 | CITYWIDE | 819 | HEALTH AND HOSPITALS CORP | 72201602 | CORRECTIONAL HEALTH: MINI CLINICS | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-10-04 | 2021-01-01 | 2020-10-04 | 2021-01-01
20201123 | CITYWIDE | 819 | HEALTH AND HOSPITALS CORP | HL82DISHC | DISTRICT HEALTH CENTER | 1 | DESIGN | 2019-05-12 | 2020-03-31 | 2019-05-12 | 2020-03-31
20201123 | CITYWIDE | 819 | HEALTH AND HOSPITALS CORP | HL82DISHC | DISTRICT HEALTH CENTER | 2 | CONSTRUCTION | 2020-04-01 | 2021-03-31 | 2020-04-01 | 2021-03-31
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | ACEDEP504 | HVAC Upgrades at Grahamsville WWTP | 1 | DEVELOP SCOPE | 2015-06-01 | 2015-08-29 | 2019-06-01 | 2019-08-29
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | ACEDEP504 | HVAC Upgrades at Grahamsville WWTP | 2 | PRELIMINARY DESIGN | 2015-08-30 | 2015-12-27 | 2019-08-30 | 2019-12-27
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | ACEDEP504 | HVAC Upgrades at Grahamsville WWTP | 3 | FINAL DESIGN | 2015-12-28 | 2016-06-24 | 2019-12-28 | 2020-06-24
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | ACEDEP504 | HVAC Upgrades at Grahamsville WWTP | 4 | BID AWARD AND REGISTER CONTRCT | 2016-06-25 | 2016-09-22 | 2020-06-25 | 2020-09-22
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | ACEDEP504 | HVAC Upgrades at Grahamsville WWTP | 5 | CONSTRUCTION TO 25% | 2016-09-23 | 2017-01-20 | 2020-09-23 | 2021-01-20
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | ACEDEP504 | HVAC Upgrades at Grahamsville WWTP | 6 | CONSTRUCTION TO 50% | 2017-01-21 | 2017-05-20 | 2021-01-21 | 2021-05-20
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | ACEDEP504 | HVAC Upgrades at Grahamsville WWTP | 7 | CONSTRUCTION TO 75% | 2017-05-21 | 2017-09-17 | 2021-05-21 | 2021-09-17
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | ACEDEP504 | HVAC Upgrades at Grahamsville WWTP | 8 | ORIGINAL EQUIP & FURNISHING | 2017-09-18 | 2017-12-16 | 2021-09-18 | 2021-12-16
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | ACEDEP504 | HVAC Upgrades at Grahamsville WWTP | 9 | SUBSTANTIAL COMPLETION | 2017-12-17 | 2018-02-14 | 2021-12-17 | 2022-02-14
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | ACEDEP504 | HVAC Upgrades at Grahamsville WWTP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-02-15 | 2018-03-16 | 2022-02-15 | 2022-03-16
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | ACEDEP505 | HVAC Upgrades at Margaretville WWTP | 1 | DEVELOP SCOPE | 2015-06-01 | 2015-08-29 | 2019-06-01 | 2019-08-29
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | ACEDEP505 | HVAC Upgrades at Margaretville WWTP | 2 | PRELIMINARY DESIGN | 2015-08-30 | 2015-12-27 | 2019-08-30 | 2019-12-27
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | ACEDEP505 | HVAC Upgrades at Margaretville WWTP | 3 | FINAL DESIGN | 2015-12-28 | 2016-06-24 | 2019-12-28 | 2020-06-24
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | ACEDEP505 | HVAC Upgrades at Margaretville WWTP | 4 | BID AWARD AND REGISTER CONTRCT | 2016-06-25 | 2016-09-22 | 2020-06-25 | 2020-09-22
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | ACEDEP505 | HVAC Upgrades at Margaretville WWTP | 5 | CONSTRUCTION TO 25% | 2016-09-23 | 2017-01-20 | 2020-09-23 | 2021-01-20
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | ACEDEP505 | HVAC Upgrades at Margaretville WWTP | 6 | CONSTRUCTION TO 50% | 2017-01-21 | 2017-05-20 | 2021-01-21 | 2021-05-20
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | ACEDEP505 | HVAC Upgrades at Margaretville WWTP | 7 | CONSTRUCTION TO 75% | 2017-05-21 | 2017-09-17 | 2021-05-21 | 2021-09-17
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | ACEDEP505 | HVAC Upgrades at Margaretville WWTP | 8 | ORIGINAL EQUIP & FURNISHING | 2017-09-18 | 2017-12-16 | 2021-09-18 | 2021-12-16
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | ACEDEP505 | HVAC Upgrades at Margaretville WWTP | 9 | SUBSTANTIAL COMPLETION | 2017-12-17 | 2018-02-14 | 2021-12-17 | 2022-02-14
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | ACEDEP505 | HVAC Upgrades at Margaretville WWTP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-02-15 | 2018-03-16 | 2022-02-15 | 2022-03-16
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | ACEDEP701 | DEP- DEMAND CONTROLLED VENTILATION UPGRADE | 1 | DEVELOP SCOPE | 2019-07-01 | 2020-06-29 | 2021-07-01 | 2022-06-30
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | AGRI-18 | FAD 18-22 WAP AND FORESTRY | 1 | DEVELOP SCOPE | 2018-06-15 | 2019-03-11 | 2018-06-15 | 2019-03-11
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | AGRI-18 | FAD 18-22 WAP AND FORESTRY | 2 | PRELIMINARY DESIGN | 2019-03-12 | 2020-03-05 | 2019-03-12 | 2020-03-05
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | AGRI-18 | FAD 18-22 WAP AND FORESTRY | 3 | FINAL DESIGN | 2020-03-06 | 2021-08-27 | 2020-03-06 | 2021-08-27
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | AGRI-18 | FAD 18-22 WAP AND FORESTRY | 4 | BID AWARD AND REGISTER CONTRCT | 2021-08-28 | 2022-05-24 | 2021-08-28 | 2022-05-24
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | AGRI-18 | FAD 18-22 WAP AND FORESTRY | 5 | CONSTRUCTION TO 25% | 2022-05-25 | 2023-05-19 | 2022-05-25 | 2023-05-19
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | AGRI-18 | FAD 18-22 WAP AND FORESTRY | 6 | CONSTRUCTION TO 50% | 2023-05-20 | 2024-05-13 | 2023-05-20 | 2024-05-13
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | AGRI-18 | FAD 18-22 WAP AND FORESTRY | 7 | CONSTRUCTION TO 75% | 2024-05-14 | 2025-05-08 | 2024-05-14 | 2025-05-08
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | AGRI-18 | FAD 18-22 WAP AND FORESTRY | 8 | ORIGINAL EQUIP & FURNISHING | 2025-05-09 | 2026-02-02 | 2025-05-09 | 2026-02-02
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | AGRI-18 | FAD 18-22 WAP AND FORESTRY | 9 | SUBSTANTIAL COMPLETION | 2026-02-03 | 2026-08-01 | 2026-02-03 | 2026-08-01
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | AGRI-18 | FAD 18-22 WAP AND FORESTRY | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2026-08-02 | 2026-10-30 | 2026-08-02 | 2026-10-30
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | AIR-MON1 | Air Monitoring Analysis | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-09-28 | 2018-07-01 | 2018-09-28
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | AIR-MON1 | Air Monitoring Analysis | 2 | PRELIMINARY DESIGN | 2018-09-29 | 2019-01-26 | 2018-09-29 | 2019-01-26
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | AIR-MON1 | Air Monitoring Analysis | 3 | FINAL DESIGN | 2019-01-27 | 2019-07-25 | 2019-01-27 | 2019-07-25
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | AIR-MON1 | Air Monitoring Analysis | 4 | BID AWARD AND REGISTER CONTRCT | 2019-07-26 | 2019-10-23 | 2019-07-26 | 2019-10-23
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | AIR-MON1 | Air Monitoring Analysis | 5 | CONSTRUCTION TO 25% | 2019-10-24 | 2020-02-20 | 2019-10-24 | 2020-02-20
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | AIR-MON1 | Air Monitoring Analysis | 6 | CONSTRUCTION TO 50% | 2020-02-21 | 2020-06-19 | 2020-02-21 | 2020-06-19
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | AIR-MON1 | Air Monitoring Analysis | 7 | CONSTRUCTION TO 75% | 2020-06-20 | 2020-10-17 | 2020-06-20 | 2020-10-17
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | AIR-MON1 | Air Monitoring Analysis | 8 | ORIGINAL EQUIP & FURNISHING | 2020-10-18 | 2021-01-15 | 2020-10-18 | 2021-01-15
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | AIR-MON1 | Air Monitoring Analysis | 9 | SUBSTANTIAL COMPLETION | 2021-01-16 | 2021-03-16 | 2021-01-16 | 2021-03-16
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | AIR-MON1 | Air Monitoring Analysis | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-17 | 2021-04-15 | 2021-03-17 | 2021-04-15
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | AIR-MON1 | Air Monitoring Analysis | 11 | PRE-CONSTRUCTION MOBILIZATION | 2021-04-16 | 2022-04-10 | 2021-04-16 | 2022-04-10
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | AIR-MON1 | Air Monitoring Analysis | 12 | ON-SITE CONSTRUCTION MANAGEMEN | 2022-04-11 | 2028-03-09 | 2022-04-11 | 2028-03-09
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | AIR-MON1 | Air Monitoring Analysis | 13 | POST-CONSTRUCTION CLOSE-OUT | 2028-03-10 | 2029-03-04 | 2028-03-10 | 2029-03-04
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | AIR-MON2 | Air Monitoring Analysis | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-08-29 | 2020-06-01 | 2020-08-29
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | AIR-MON2 | Air Monitoring Analysis | 2 | PRELIMINARY DESIGN | 2020-08-30 | 2020-12-27 | 2020-08-30 | 2020-12-27
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | AIR-MON2 | Air Monitoring Analysis | 3 | FINAL DESIGN | 2020-12-28 | 2021-06-25 | 2020-12-28 | 2021-06-25
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | AIR-MON2 | Air Monitoring Analysis | 4 | BID AWARD AND REGISTER CONTRCT | 2021-06-26 | 2021-09-23 | 2021-06-26 | 2021-09-23
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | AIR-MON2 | Air Monitoring Analysis | 5 | CONSTRUCTION TO 25% | 2021-09-24 | 2022-01-21 | 2021-09-24 | 2022-01-21
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | AIR-MON2 | Air Monitoring Analysis | 6 | CONSTRUCTION TO 50% | 2022-01-22 | 2022-05-21 | 2022-01-22 | 2022-05-21
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | AIR-MON2 | Air Monitoring Analysis | 7 | CONSTRUCTION TO 75% | 2022-05-22 | 2022-09-18 | 2022-05-22 | 2022-09-18
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | AIR-MON2 | Air Monitoring Analysis | 8 | ORIGINAL EQUIP & FURNISHING | 2022-09-19 | 2022-12-17 | 2022-09-19 | 2022-12-17
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | AIR-MON2 | Air Monitoring Analysis | 9 | SUBSTANTIAL COMPLETION | 2022-12-18 | 2023-02-15 | 2022-12-18 | 2023-02-15
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | AIR-MON2 | Air Monitoring Analysis | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-02-16 | 2023-03-17 | 2023-02-16 | 2023-03-17
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | AIR-MON2 | Air Monitoring Analysis | 11 | PRE-CONSTRUCTION MOBILIZATION | 2023-03-18 | 2024-03-11 | 2023-03-18 | 2024-03-11
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | AIR-MON2 | Air Monitoring Analysis | 12 | ON-SITE CONSTRUCTION MANAGEMEN | 2024-03-12 | 2030-02-08 | 2024-03-12 | 2030-02-08
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | AIR-MON2 | Air Monitoring Analysis | 13 | POST-CONSTRUCTION CLOSE-OUT | 2030-02-09 | 2031-02-03 | 2030-02-09 | 2031-02-03
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | ASB-REM | Asbestos Removal | 1 | DEVELOP SCOPE | 2013-03-27 | 2013-06-24 | 2014-08-27 | 2014-12-24
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | ASB-REM | Asbestos Removal | 2 | PRELIMINARY DESIGN | 2013-06-25 | 2013-10-22 | 2014-12-25 | 2015-06-22
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | ASB-REM | Asbestos Removal | 3 | FINAL DESIGN | 2013-10-23 | 2014-04-20 | 2015-06-23 | 2016-12-23
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | ASB-REM | Asbestos Removal | 4 | BID AWARD AND REGISTER CONTRCT | 2014-04-21 | 2014-07-19 | 2016-12-24 | 2017-06-21
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | ASB-REM | Asbestos Removal | 5 | CONSTRUCTION TO 25% | 2014-07-20 | 2014-11-16 | 2017-06-22 | 2018-03-28
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | ASB-REM | Asbestos Removal | 6 | CONSTRUCTION TO 50% | 2014-11-17 | 2015-03-16 | 2018-03-29 | 2019-01-02
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | ASB-REM | Asbestos Removal | 7 | CONSTRUCTION TO 75% | 2015-03-17 | 2015-07-14 | 2019-01-03 | 2019-10-09
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | ASB-REM | Asbestos Removal | 8 | ORIGINAL EQUIP & FURNISHING | 2015-07-15 | 2015-10-12 | 2019-10-10 | 2020-01-07
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | ASB-REM | Asbestos Removal | 9 | SUBSTANTIAL COMPLETION | 2015-10-13 | 2015-12-11 | 2020-01-08 | 2020-03-07
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | ASB-REM | Asbestos Removal | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-12-12 | 2016-01-10 | 2020-03-08 | 2020-06-05
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | ASB-REM | Asbestos Removal | 11 | PRE-CONSTRUCTION MOBILIZATION | 2015-12-12 | 2016-01-10 | 2020-06-06 | 2021-05-31
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | ASB-REM | Asbestos Removal | 12 | ON-SITE CONSTRUCTION MANAGEMEN | 2015-12-12 | 2016-01-10 | 2021-06-01 | 2027-04-30
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | ASB-REM | Asbestos Removal | 13 | POST-CONSTRUCTION CLOSE-OUT | 2015-12-12 | 2016-01-10 | 2027-05-01 | 2028-04-24
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | AWT2-CARB | CONSTRUCTION OF CARBON ADDITION FACILITY AT VARIOUS WWTPs | 1 | DEVELOP SCOPE | 2014-03-03 | 2014-05-31 | 2014-03-03 | 2014-11-27
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | AWT2-CARB | CONSTRUCTION OF CARBON ADDITION FACILITY AT VARIOUS WWTPs | 2 | PRELIMINARY DESIGN | 2014-06-01 | 2014-09-28 | 2014-11-28 | 2015-11-22
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | AWT2-CARB | CONSTRUCTION OF CARBON ADDITION FACILITY AT VARIOUS WWTPs | 3 | FINAL DESIGN | 2014-09-29 | 2015-03-27 | 2014-09-29 | 2015-03-27
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | AWT2-CARB | CONSTRUCTION OF CARBON ADDITION FACILITY AT VARIOUS WWTPs | 4 | BID AWARD AND REGISTER CONTRCT | 2015-03-28 | 2015-06-25 | 2017-05-16 | 2018-02-09
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | AWT2-CARB | CONSTRUCTION OF CARBON ADDITION FACILITY AT VARIOUS WWTPs | 5 | CONSTRUCTION TO 25% | 2015-06-26 | 2015-10-23 | 2018-02-10 | 2019-02-04
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | AWT2-CARB | CONSTRUCTION OF CARBON ADDITION FACILITY AT VARIOUS WWTPs | 6 | CONSTRUCTION TO 50% | 2015-10-24 | 2016-02-20 | 2019-02-05 | 2020-01-30
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | AWT2-CARB | CONSTRUCTION OF CARBON ADDITION FACILITY AT VARIOUS WWTPs | 7 | CONSTRUCTION TO 75% | 2016-02-21 | 2016-06-19 | 2020-01-31 | 2021-01-24
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | AWT2-CARB | CONSTRUCTION OF CARBON ADDITION FACILITY AT VARIOUS WWTPs | 8 | ORIGINAL EQUIP & FURNISHING | 2016-06-20 | 2016-09-17 | 2021-01-25 | 2021-10-21
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | AWT2-CARB | CONSTRUCTION OF CARBON ADDITION FACILITY AT VARIOUS WWTPs | 9 | SUBSTANTIAL COMPLETION | 2016-09-18 | 2016-11-16 | 2021-10-22 | 2022-04-19
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | AWT2-CARB | CONSTRUCTION OF CARBON ADDITION FACILITY AT VARIOUS WWTPs | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-11-17 | 2016-12-16 | 2022-04-20 | 2022-07-18
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | C519 | MODIFICATION OF CHAMBERS AT HILLVIEW | 1 | DEVELOP SCOPE | 1996-05-15 | 1997-02-08 | 2007-06-01 | 2008-02-25
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | C519 | MODIFICATION OF CHAMBERS AT HILLVIEW | 2 | PRELIMINARY DESIGN | 1997-02-09 | 1998-02-03 | 2008-02-26 | 2009-02-19
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | C519 | MODIFICATION OF CHAMBERS AT HILLVIEW | 3 | FINAL DESIGN | 1998-02-04 | 1999-07-28 | 2009-02-20 | 2010-08-13
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | C519 | MODIFICATION OF CHAMBERS AT HILLVIEW | 4 | BID AWARD AND REGISTER CONTRCT | 1999-07-29 | 2000-04-23 | 2010-08-14 | 2011-05-10
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | C519 | MODIFICATION OF CHAMBERS AT HILLVIEW | 5 | CONSTRUCTION TO 25% | 2000-04-24 | 2001-04-18 | 2011-05-11 | 2012-05-04
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | C519 | MODIFICATION OF CHAMBERS AT HILLVIEW | 6 | CONSTRUCTION TO 50% | 2001-04-19 | 2002-04-13 | 2012-05-05 | 2013-04-29
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | C519 | MODIFICATION OF CHAMBERS AT HILLVIEW | 7 | CONSTRUCTION TO 75% | 2002-04-14 | 2003-04-08 | 2013-04-30 | 2014-04-24
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | C519 | MODIFICATION OF CHAMBERS AT HILLVIEW | 8 | ORIGINAL EQUIP & FURNISHING | 2003-04-09 | 2004-01-03 | 2014-04-25 | 2015-01-19
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | C519 | MODIFICATION OF CHAMBERS AT HILLVIEW | 9 | SUBSTANTIAL COMPLETION | 2004-01-04 | 2004-07-01 | 2015-01-20 | 2027-07-15
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | C519 | MODIFICATION OF CHAMBERS AT HILLVIEW | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2004-07-02 | 2004-09-29 | 2027-07-16 | 2027-10-13
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | C529 | HILLVIEW CHLORINATION BLDG | 1 | DEVELOP SCOPE | 1996-03-15 | 1996-12-09 | 1996-03-15 | 1998-02-12
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | C529 | HILLVIEW CHLORINATION BLDG | 2 | PRELIMINARY DESIGN | 1996-12-10 | 1997-12-04 | 1998-02-13 | 2000-01-13
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | C529 | HILLVIEW CHLORINATION BLDG | 3 | FINAL DESIGN | 1997-12-05 | 1999-05-28 | 2000-01-14 | 2001-12-13
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | C529 | HILLVIEW CHLORINATION BLDG | 4 | BID AWARD AND REGISTER CONTRCT | 1999-05-29 | 2000-02-22 | 2001-12-14 | 2003-08-05
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | C529 | HILLVIEW CHLORINATION BLDG | 5 | CONSTRUCTION TO 25% | 2000-02-23 | 2001-02-16 | 2003-08-06 | 2005-10-13
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | C529 | HILLVIEW CHLORINATION BLDG | 6 | CONSTRUCTION TO 50% | 2001-02-17 | 2002-02-11 | 2005-10-14 | 2007-12-22
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | C529 | HILLVIEW CHLORINATION BLDG | 7 | CONSTRUCTION TO 75% | 2002-02-12 | 2003-02-06 | 2007-12-23 | 2010-03-01
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | C529 | HILLVIEW CHLORINATION BLDG | 8 | ORIGINAL EQUIP & FURNISHING | 2003-02-07 | 2003-11-03 | 2010-03-02 | 2011-02-24
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | C529 | HILLVIEW CHLORINATION BLDG | 9 | SUBSTANTIAL COMPLETION | 2003-11-04 | 2004-05-01 | 2011-04-26 | 2012-04-19
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | C529 | HILLVIEW CHLORINATION BLDG | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2004-05-02 | 2004-07-30 | 2012-04-20 | 2012-07-18
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | C529 | HILLVIEW CHLORINATION BLDG | 11 | DEVELOP SCOPE | 2004-05-02 | 2004-07-30 | 2012-07-19 | 2013-04-14
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | C529 | HILLVIEW CHLORINATION BLDG | 12 | PRELIMINARY DESIGN | 2004-05-02 | 2004-07-30 | 2013-04-15 | 2014-04-09
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | C529 | HILLVIEW CHLORINATION BLDG | 13 | FINAL DESIGN | 2004-05-02 | 2004-07-30 | 2014-04-10 | 2015-10-01
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | C529 | HILLVIEW CHLORINATION BLDG | 14 | BID AWARD AND REGISTER CONTRCT | 2004-05-02 | 2004-07-30 | 2015-10-02 | 2016-06-27
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | C529 | HILLVIEW CHLORINATION BLDG | 15 | CONSTRUCTION TO 25% | 2004-05-02 | 2004-07-30 | 2016-06-28 | 2017-06-22
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | C529 | HILLVIEW CHLORINATION BLDG | 16 | CONSTRUCTION TO 50% | 2004-05-02 | 2004-07-30 | 2017-06-23 | 2018-06-17
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | C529 | HILLVIEW CHLORINATION BLDG | 17 | CONSTRUCTION TO 75% | 2004-05-02 | 2004-07-30 | 2018-06-18 | 2019-06-12
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | C529 | HILLVIEW CHLORINATION BLDG | 18 | ORIGINAL EQUIP & FURNISHING | 2004-05-02 | 2004-07-30 | 2019-06-13 | 2020-03-08
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | C529 | HILLVIEW CHLORINATION BLDG | 19 | SUBSTANTIAL COMPLETION | 2004-05-02 | 2004-07-30 | 2020-03-09 | 2024-09-03
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | C529 | HILLVIEW CHLORINATION BLDG | 20 | PUNCHLIST COMPLETE, JOB CLOSED | 2004-05-02 | 2004-07-30 | 2024-09-04 | 2024-12-02
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAN-HYDRO | Development of Hydroelectric Cannonsville Dam. incl P'wrhse | 1 | DEVELOP SCOPE | 2018-06-01 | 2019-02-25 | 2021-06-01 | 2022-02-25
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAN-HYDRO | Development of Hydroelectric Cannonsville Dam. incl P'wrhse | 2 | PRELIMINARY DESIGN | 2019-02-26 | 2020-02-20 | 2022-02-26 | 2023-02-20
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAN-HYDRO | Development of Hydroelectric Cannonsville Dam. incl P'wrhse | 3 | FINAL DESIGN | 2020-02-21 | 2021-08-13 | 2023-02-21 | 2024-08-13
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAN-HYDRO | Development of Hydroelectric Cannonsville Dam. incl P'wrhse | 4 | BID AWARD AND REGISTER CONTRCT | 2021-08-14 | 2022-05-10 | 2024-08-14 | 2025-05-10
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAN-HYDRO | Development of Hydroelectric Cannonsville Dam. incl P'wrhse | 5 | CONSTRUCTION TO 25% | 2022-05-11 | 2023-05-05 | 2025-05-11 | 2026-05-05
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAN-HYDRO | Development of Hydroelectric Cannonsville Dam. incl P'wrhse | 6 | CONSTRUCTION TO 50% | 2023-05-06 | 2024-04-29 | 2026-05-06 | 2027-04-30
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAN-HYDRO | Development of Hydroelectric Cannonsville Dam. incl P'wrhse | 7 | CONSTRUCTION TO 75% | 2024-04-30 | 2025-04-24 | 2027-05-01 | 2028-04-24
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAN-HYDRO | Development of Hydroelectric Cannonsville Dam. incl P'wrhse | 8 | ORIGINAL EQUIP & FURNISHING | 2025-04-25 | 2026-01-19 | 2028-04-25 | 2029-01-19
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAN-HYDRO | Development of Hydroelectric Cannonsville Dam. incl P'wrhse | 9 | SUBSTANTIAL COMPLETION | 2026-01-20 | 2026-07-18 | 2029-01-20 | 2033-07-17
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAN-HYDRO | Development of Hydroelectric Cannonsville Dam. incl P'wrhse | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2026-07-19 | 2026-10-16 | 2033-07-18 | 2033-10-15
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-186 | RESURFACING SCHOHARIE ROADS WEST AND BEARKILL BRIDGE | 1 | DEVELOP SCOPE | 1998-05-28 | 1999-02-21 | 2004-11-27 | 2006-06-19
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-186 | RESURFACING SCHOHARIE ROADS WEST AND BEARKILL BRIDGE | 2 | PRELIMINARY DESIGN | 1999-02-22 | 2000-02-16 | 2006-06-20 | 2008-05-19
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-186 | RESURFACING SCHOHARIE ROADS WEST AND BEARKILL BRIDGE | 3 | FINAL DESIGN | 2000-02-17 | 2001-08-09 | 2008-05-20 | 2010-11-05
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-186 | RESURFACING SCHOHARIE ROADS WEST AND BEARKILL BRIDGE | 4 | BID AWARD AND REGISTER CONTRCT | 2001-08-10 | 2002-05-06 | 2010-11-06 | 2012-05-28
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-186 | RESURFACING SCHOHARIE ROADS WEST AND BEARKILL BRIDGE | 5 | CONSTRUCTION TO 25% | 2002-05-07 | 2003-05-01 | 2012-05-29 | 2014-04-28
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-186 | RESURFACING SCHOHARIE ROADS WEST AND BEARKILL BRIDGE | 6 | CONSTRUCTION TO 50% | 2003-05-02 | 2004-04-25 | 2014-04-29 | 2016-07-06
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-186 | RESURFACING SCHOHARIE ROADS WEST AND BEARKILL BRIDGE | 7 | CONSTRUCTION TO 75% | 2004-04-26 | 2005-04-20 | 2016-07-07 | 2018-09-14
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-186 | RESURFACING SCHOHARIE ROADS WEST AND BEARKILL BRIDGE | 8 | ORIGINAL EQUIP & FURNISHING | 2005-04-21 | 2006-01-15 | 2018-09-15 | 2019-10-19
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-186 | RESURFACING SCHOHARIE ROADS WEST AND BEARKILL BRIDGE | 9 | SUBSTANTIAL COMPLETION | 2006-01-16 | 2006-07-14 | 2019-10-20 | 2020-11-22
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-186 | RESURFACING SCHOHARIE ROADS WEST AND BEARKILL BRIDGE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2006-07-15 | 2006-10-12 | 2020-11-23 | 2021-06-30
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-210 | CAT/DEL UV LIGHT TREATMENT FACILITIES | 1 | DEVELOP SCOPE | 2006-06-12 | 2006-09-09 | 2006-06-12 | 2007-03-08
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-210 | CAT/DEL UV LIGHT TREATMENT FACILITIES | 2 | PRELIMINARY DESIGN | 2006-09-10 | 2007-01-07 | 2007-03-09 | 2008-03-02
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-210 | CAT/DEL UV LIGHT TREATMENT FACILITIES | 3 | FINAL DESIGN | 2007-01-08 | 2007-07-06 | 2008-03-03 | 2009-08-24
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-210 | CAT/DEL UV LIGHT TREATMENT FACILITIES | 4 | BID AWARD AND REGISTER CONTRCT | 2007-07-07 | 2007-10-04 | 2009-08-25 | 2010-05-21
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-210 | CAT/DEL UV LIGHT TREATMENT FACILITIES | 5 | CONSTRUCTION TO 25% | 2007-10-05 | 2008-02-01 | 2010-05-22 | 2011-05-16
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-210 | CAT/DEL UV LIGHT TREATMENT FACILITIES | 6 | CONSTRUCTION TO 50% | 2008-02-02 | 2008-05-31 | 2011-05-17 | 2012-05-10
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-210 | CAT/DEL UV LIGHT TREATMENT FACILITIES | 7 | CONSTRUCTION TO 75% | 2008-06-01 | 2008-09-28 | 2012-05-11 | 2013-05-05
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-210 | CAT/DEL UV LIGHT TREATMENT FACILITIES | 8 | ORIGINAL EQUIP & FURNISHING | 2008-09-29 | 2008-12-27 | 2013-05-06 | 2014-01-30
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-210 | CAT/DEL UV LIGHT TREATMENT FACILITIES | 9 | SUBSTANTIAL COMPLETION | 2008-12-28 | 2009-02-25 | 2014-01-31 | 2026-07-26
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-210 | CAT/DEL UV LIGHT TREATMENT FACILITIES | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2009-02-26 | 2009-03-27 | 2026-07-27 | 2026-10-24
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-212 | SCHOHARIE RESERVOIR/GILBOA DAM AND INTAKE/OUTLET CHAMBER | 1 | DEVELOP SCOPE | 2004-03-18 | 2004-12-12 | 2015-05-22 | 2016-02-15
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-212 | SCHOHARIE RESERVOIR/GILBOA DAM AND INTAKE/OUTLET CHAMBER | 2 | PRELIMINARY DESIGN | 2004-12-13 | 2005-12-07 | 2016-02-16 | 2017-02-09
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-212 | SCHOHARIE RESERVOIR/GILBOA DAM AND INTAKE/OUTLET CHAMBER | 3 | FINAL DESIGN | 2005-12-08 | 2007-05-31 | 2017-02-10 | 2018-08-03
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-212 | SCHOHARIE RESERVOIR/GILBOA DAM AND INTAKE/OUTLET CHAMBER | 4 | BID AWARD AND REGISTER CONTRCT | 2007-06-01 | 2008-02-25 | 2018-08-04 | 2019-04-30
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-212 | SCHOHARIE RESERVOIR/GILBOA DAM AND INTAKE/OUTLET CHAMBER | 5 | CONSTRUCTION TO 25% | 2008-02-26 | 2009-02-19 | 2019-05-01 | 2020-04-24
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-212 | SCHOHARIE RESERVOIR/GILBOA DAM AND INTAKE/OUTLET CHAMBER | 6 | CONSTRUCTION TO 50% | 2009-02-20 | 2010-02-14 | 2020-04-25 | 2021-04-19
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-212 | SCHOHARIE RESERVOIR/GILBOA DAM AND INTAKE/OUTLET CHAMBER | 7 | CONSTRUCTION TO 75% | 2010-02-15 | 2011-02-09 | 2021-04-20 | 2022-04-14
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-212 | SCHOHARIE RESERVOIR/GILBOA DAM AND INTAKE/OUTLET CHAMBER | 8 | ORIGINAL EQUIP & FURNISHING | 2011-02-10 | 2011-11-06 | 2022-04-15 | 2023-01-09
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-212 | SCHOHARIE RESERVOIR/GILBOA DAM AND INTAKE/OUTLET CHAMBER | 9 | SUBSTANTIAL COMPLETION | 2011-11-07 | 2012-05-04 | 2023-01-10 | 2023-07-08
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-212 | SCHOHARIE RESERVOIR/GILBOA DAM AND INTAKE/OUTLET CHAMBER | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-05-05 | 2012-08-02 | 2023-07-09 | 2023-10-06
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-213 | ASHOKAN RESERVOIR/OLIVE BRIDGE DAM & UPPER/LOWER OUTLET& SCR | 1 | DEVELOP SCOPE | 2008-06-15 | 2009-03-11 | 2008-06-15 | 2009-03-11
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-213 | ASHOKAN RESERVOIR/OLIVE BRIDGE DAM & UPPER/LOWER OUTLET& SCR | 2 | PRELIMINARY DESIGN | 2009-03-12 | 2010-03-06 | 2009-03-12 | 2010-03-06
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-213 | ASHOKAN RESERVOIR/OLIVE BRIDGE DAM & UPPER/LOWER OUTLET& SCR | 3 | FINAL DESIGN | 2010-03-07 | 2011-08-28 | 2010-03-07 | 2011-08-28
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-213 | ASHOKAN RESERVOIR/OLIVE BRIDGE DAM & UPPER/LOWER OUTLET& SCR | 4 | BID AWARD AND REGISTER CONTRCT | 2011-08-29 | 2012-05-24 | 2011-08-29 | 2012-05-24
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-213 | ASHOKAN RESERVOIR/OLIVE BRIDGE DAM & UPPER/LOWER OUTLET& SCR | 5 | CONSTRUCTION TO 25% | 2012-05-25 | 2013-05-19 | 2012-05-25 | 2013-05-19
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-213 | ASHOKAN RESERVOIR/OLIVE BRIDGE DAM & UPPER/LOWER OUTLET& SCR | 6 | CONSTRUCTION TO 50% | 2013-05-20 | 2014-05-14 | 2013-05-20 | 2014-05-14
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-213 | ASHOKAN RESERVOIR/OLIVE BRIDGE DAM & UPPER/LOWER OUTLET& SCR | 7 | CONSTRUCTION TO 75% | 2014-05-15 | 2015-05-09 | 2014-05-15 | 2015-05-09
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-213 | ASHOKAN RESERVOIR/OLIVE BRIDGE DAM & UPPER/LOWER OUTLET& SCR | 8 | ORIGINAL EQUIP & FURNISHING | 2015-05-10 | 2016-02-03 | 2015-05-10 | 2016-02-03
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-213 | ASHOKAN RESERVOIR/OLIVE BRIDGE DAM & UPPER/LOWER OUTLET& SCR | 9 | SUBSTANTIAL COMPLETION | 2016-02-04 | 2016-08-01 | 2016-02-04 | 2028-07-29
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-213 | ASHOKAN RESERVOIR/OLIVE BRIDGE DAM & UPPER/LOWER OUTLET& SCR | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-08-02 | 2016-10-30 | 2028-07-30 | 2028-10-27
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-234 | RECONSTRUCT CONCRETE BEAMS AND FLOORS, ASHOKAN GARAGE | 1 | DEVELOP SCOPE | 2007-02-15 | 2007-05-15 | 2009-06-01 | 2010-02-25
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-234 | RECONSTRUCT CONCRETE BEAMS AND FLOORS, ASHOKAN GARAGE | 2 | PRELIMINARY DESIGN | 2007-05-16 | 2007-09-12 | 2010-02-26 | 2011-02-20
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-234 | RECONSTRUCT CONCRETE BEAMS AND FLOORS, ASHOKAN GARAGE | 3 | FINAL DESIGN | 2007-09-13 | 2008-03-10 | 2011-02-21 | 2012-08-13
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-234 | RECONSTRUCT CONCRETE BEAMS AND FLOORS, ASHOKAN GARAGE | 4 | BID AWARD AND REGISTER CONTRCT | 2008-03-11 | 2008-06-08 | 2012-08-14 | 2013-05-10
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-234 | RECONSTRUCT CONCRETE BEAMS AND FLOORS, ASHOKAN GARAGE | 5 | CONSTRUCTION TO 25% | 2008-06-09 | 2008-10-06 | 2013-05-11 | 2014-05-05
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-234 | RECONSTRUCT CONCRETE BEAMS AND FLOORS, ASHOKAN GARAGE | 6 | CONSTRUCTION TO 50% | 2008-10-07 | 2009-02-03 | 2014-05-06 | 2015-04-30
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-234 | RECONSTRUCT CONCRETE BEAMS AND FLOORS, ASHOKAN GARAGE | 7 | CONSTRUCTION TO 75% | 2009-02-04 | 2009-06-03 | 2015-05-01 | 2016-04-24
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-234 | RECONSTRUCT CONCRETE BEAMS AND FLOORS, ASHOKAN GARAGE | 8 | ORIGINAL EQUIP & FURNISHING | 2009-06-04 | 2009-09-01 | 2016-04-25 | 2017-01-19
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-234 | RECONSTRUCT CONCRETE BEAMS AND FLOORS, ASHOKAN GARAGE | 9 | SUBSTANTIAL COMPLETION | 2009-09-02 | 2009-10-31 | 2017-01-20 | 2025-07-16
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-234 | RECONSTRUCT CONCRETE BEAMS AND FLOORS, ASHOKAN GARAGE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2009-11-01 | 2009-11-30 | 2025-07-17 | 2025-10-14
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-252 | REPLACEMENT OF ESOPUS AND ROUTE 28A RAILROAD BRIDGES | 1 | DEVELOP SCOPE | 2008-12-15 | 2009-09-10 | 2017-07-01 | 2018-03-27
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-252 | REPLACEMENT OF ESOPUS AND ROUTE 28A RAILROAD BRIDGES | 2 | PRELIMINARY DESIGN | 2009-09-11 | 2010-09-05 | 2018-03-28 | 2019-03-22
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-252 | REPLACEMENT OF ESOPUS AND ROUTE 28A RAILROAD BRIDGES | 3 | FINAL DESIGN | 2010-09-06 | 2012-02-27 | 2019-03-23 | 2020-09-12
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-252 | REPLACEMENT OF ESOPUS AND ROUTE 28A RAILROAD BRIDGES | 4 | BID AWARD AND REGISTER CONTRCT | 2012-02-28 | 2012-11-23 | 2020-09-13 | 2021-06-09
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-252 | REPLACEMENT OF ESOPUS AND ROUTE 28A RAILROAD BRIDGES | 5 | CONSTRUCTION TO 25% | 2012-11-24 | 2013-11-18 | 2021-06-10 | 2022-06-04
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-252 | REPLACEMENT OF ESOPUS AND ROUTE 28A RAILROAD BRIDGES | 6 | CONSTRUCTION TO 50% | 2013-11-19 | 2014-11-13 | 2022-06-05 | 2023-05-30
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-252 | REPLACEMENT OF ESOPUS AND ROUTE 28A RAILROAD BRIDGES | 7 | CONSTRUCTION TO 75% | 2014-11-14 | 2015-11-08 | 2023-05-31 | 2024-05-24
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-252 | REPLACEMENT OF ESOPUS AND ROUTE 28A RAILROAD BRIDGES | 8 | ORIGINAL EQUIP & FURNISHING | 2015-11-09 | 2016-08-04 | 2024-05-25 | 2025-02-18
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-252 | REPLACEMENT OF ESOPUS AND ROUTE 28A RAILROAD BRIDGES | 9 | SUBSTANTIAL COMPLETION | 2016-08-05 | 2017-01-31 | 2025-02-19 | 2025-08-17
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-252 | REPLACEMENT OF ESOPUS AND ROUTE 28A RAILROAD BRIDGES | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-02-01 | 2017-05-01 | 2025-08-18 | 2025-11-15
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-259 | BEN NESIN FACILITY/ASHOKAN RECONSTRUCTION | 1 | DEVELOP SCOPE | 2009-12-15 | 2010-03-14 | 2009-01-01 | 2009-09-27
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-259 | BEN NESIN FACILITY/ASHOKAN RECONSTRUCTION | 2 | PRELIMINARY DESIGN | 2010-03-15 | 2010-07-12 | 2009-09-28 | 2010-09-22
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-259 | BEN NESIN FACILITY/ASHOKAN RECONSTRUCTION | 3 | FINAL DESIGN | 2010-07-13 | 2011-01-08 | 2010-09-23 | 2012-03-15
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-259 | BEN NESIN FACILITY/ASHOKAN RECONSTRUCTION | 4 | BID AWARD AND REGISTER CONTRCT | 2011-01-09 | 2011-04-08 | 2012-03-16 | 2012-12-10
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-259 | BEN NESIN FACILITY/ASHOKAN RECONSTRUCTION | 5 | CONSTRUCTION TO 25% | 2011-04-09 | 2011-08-06 | 2012-12-11 | 2013-12-05
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-259 | BEN NESIN FACILITY/ASHOKAN RECONSTRUCTION | 6 | CONSTRUCTION TO 50% | 2011-08-07 | 2011-12-04 | 2013-12-06 | 2014-11-30
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-259 | BEN NESIN FACILITY/ASHOKAN RECONSTRUCTION | 7 | CONSTRUCTION TO 75% | 2011-12-05 | 2012-04-02 | 2014-12-01 | 2015-11-25
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-259 | BEN NESIN FACILITY/ASHOKAN RECONSTRUCTION | 8 | ORIGINAL EQUIP & FURNISHING | 2012-04-03 | 2012-07-01 | 2015-11-26 | 2016-08-21
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-259 | BEN NESIN FACILITY/ASHOKAN RECONSTRUCTION | 9 | SUBSTANTIAL COMPLETION | 2012-07-02 | 2012-08-30 | 2016-08-22 | 2021-02-16
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-259 | BEN NESIN FACILITY/ASHOKAN RECONSTRUCTION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-08-31 | 2012-09-29 | 2021-02-17 | 2021-05-17
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-379 | Bureau of Police & Security Academy Renovation, Kingston | 1 | DEVELOP SCOPE | 2017-07-01 | 2018-03-27 | 2017-07-01 | 2018-03-27
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-379 | Bureau of Police & Security Academy Renovation, Kingston | 2 | PRELIMINARY DESIGN | 2018-03-28 | 2019-03-22 | 2018-03-28 | 2019-03-22
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-379 | Bureau of Police & Security Academy Renovation, Kingston | 3 | FINAL DESIGN | 2019-03-23 | 2020-09-12 | 2019-03-23 | 2020-09-12
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-379 | Bureau of Police & Security Academy Renovation, Kingston | 4 | BID AWARD AND REGISTER CONTRCT | 2020-09-13 | 2021-06-09 | 2020-09-13 | 2021-06-09
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-379 | Bureau of Police & Security Academy Renovation, Kingston | 5 | CONSTRUCTION TO 25% | 2021-06-10 | 2022-06-04 | 2021-06-10 | 2022-06-04
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-379 | Bureau of Police & Security Academy Renovation, Kingston | 6 | CONSTRUCTION TO 50% | 2022-06-05 | 2023-05-30 | 2022-06-05 | 2023-05-30
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-379 | Bureau of Police & Security Academy Renovation, Kingston | 7 | CONSTRUCTION TO 75% | 2023-05-31 | 2024-05-24 | 2023-05-31 | 2024-05-24
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-379 | Bureau of Police & Security Academy Renovation, Kingston | 8 | ORIGINAL EQUIP & FURNISHING | 2024-05-25 | 2025-02-18 | 2024-05-25 | 2025-02-18
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-379 | Bureau of Police & Security Academy Renovation, Kingston | 9 | SUBSTANTIAL COMPLETION | 2025-02-19 | 2025-08-17 | 2025-02-19 | 2025-08-17
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-379 | Bureau of Police & Security Academy Renovation, Kingston | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-08-18 | 2025-11-15 | 2025-08-18 | 2025-11-15
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-390 | Schoharie Reservoir road improvement- NYS Rt. 990V | 1 | DEVELOP SCOPE | 2010-02-01 | 2010-05-01 | 2011-06-30 | 2012-03-25
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-390 | Schoharie Reservoir road improvement- NYS Rt. 990V | 2 | PRELIMINARY DESIGN | 2010-05-02 | 2010-08-29 | 2012-03-26 | 2013-03-20
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-390 | Schoharie Reservoir road improvement- NYS Rt. 990V | 3 | FINAL DESIGN | 2010-08-30 | 2011-02-25 | 2013-03-21 | 2014-09-11
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-390 | Schoharie Reservoir road improvement- NYS Rt. 990V | 4 | BID AWARD AND REGISTER CONTRCT | 2011-02-26 | 2011-05-26 | 2014-09-12 | 2015-06-08
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-390 | Schoharie Reservoir road improvement- NYS Rt. 990V | 5 | CONSTRUCTION TO 25% | 2011-05-27 | 2011-09-23 | 2015-06-09 | 2016-06-02
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-390 | Schoharie Reservoir road improvement- NYS Rt. 990V | 6 | CONSTRUCTION TO 50% | 2011-09-24 | 2012-01-21 | 2016-06-03 | 2017-05-28
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-390 | Schoharie Reservoir road improvement- NYS Rt. 990V | 7 | CONSTRUCTION TO 75% | 2012-01-22 | 2012-05-20 | 2017-05-29 | 2018-05-23
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-390 | Schoharie Reservoir road improvement- NYS Rt. 990V | 8 | ORIGINAL EQUIP & FURNISHING | 2012-05-21 | 2012-08-18 | 2018-05-24 | 2019-02-17
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-390 | Schoharie Reservoir road improvement- NYS Rt. 990V | 9 | SUBSTANTIAL COMPLETION | 2012-08-19 | 2012-10-17 | 2019-02-18 | 2027-08-14
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-390 | Schoharie Reservoir road improvement- NYS Rt. 990V | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-10-18 | 2012-11-16 | 2027-08-15 | 2027-11-12
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-392 | Energy Conservation Measures Improvement at Four WWTPs | 1 | DEVELOP SCOPE | 2011-03-01 | 2011-11-25 | 2011-03-01 | 2011-11-25
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-392 | Energy Conservation Measures Improvement at Four WWTPs | 2 | PRELIMINARY DESIGN | 2011-11-26 | 2012-11-19 | 2011-11-26 | 2012-11-19
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-392 | Energy Conservation Measures Improvement at Four WWTPs | 3 | FINAL DESIGN | 2012-11-20 | 2014-05-13 | 2012-11-20 | 2014-05-13
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-392 | Energy Conservation Measures Improvement at Four WWTPs | 4 | BID AWARD AND REGISTER CONTRCT | 2014-05-14 | 2015-02-07 | 2014-05-14 | 2015-02-07
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-392 | Energy Conservation Measures Improvement at Four WWTPs | 5 | CONSTRUCTION TO 25% | 2015-02-08 | 2016-02-02 | 2015-02-08 | 2016-02-02
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-392 | Energy Conservation Measures Improvement at Four WWTPs | 6 | CONSTRUCTION TO 50% | 2016-02-03 | 2017-01-27 | 2016-02-03 | 2017-01-27
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-392 | Energy Conservation Measures Improvement at Four WWTPs | 7 | CONSTRUCTION TO 75% | 2017-01-28 | 2018-01-22 | 2017-01-28 | 2018-01-22
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-392 | Energy Conservation Measures Improvement at Four WWTPs | 8 | ORIGINAL EQUIP & FURNISHING | 2018-01-23 | 2018-10-19 | 2018-01-23 | 2018-10-19
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-392 | Energy Conservation Measures Improvement at Four WWTPs | 9 | SUBSTANTIAL COMPLETION | 2018-10-20 | 2019-04-17 | 2018-10-20 | 2027-04-15
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-392 | Energy Conservation Measures Improvement at Four WWTPs | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-04-18 | 2019-07-16 | 2027-04-16 | 2027-07-14
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-399 | CA Hudson River Drainage Chamber | 1 | DEVELOP SCOPE | 2011-03-01 | 2011-11-25 | 2011-03-01 | 2011-11-25
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-399 | CA Hudson River Drainage Chamber | 2 | PRELIMINARY DESIGN | 2011-11-26 | 2012-11-19 | 2011-11-26 | 2012-11-19
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-399 | CA Hudson River Drainage Chamber | 3 | FINAL DESIGN | 2012-11-20 | 2014-05-13 | 2012-11-20 | 2014-05-13
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-399 | CA Hudson River Drainage Chamber | 4 | BID AWARD AND REGISTER CONTRCT | 2014-05-14 | 2015-02-07 | 2014-05-14 | 2015-02-07
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-399 | CA Hudson River Drainage Chamber | 5 | CONSTRUCTION TO 25% | 2015-02-08 | 2016-02-02 | 2015-02-08 | 2016-02-02
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-399 | CA Hudson River Drainage Chamber | 6 | CONSTRUCTION TO 50% | 2016-02-03 | 2017-01-27 | 2016-02-03 | 2017-01-27
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-399 | CA Hudson River Drainage Chamber | 7 | CONSTRUCTION TO 75% | 2017-01-28 | 2018-01-22 | 2017-01-28 | 2018-01-22
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-399 | CA Hudson River Drainage Chamber | 8 | ORIGINAL EQUIP & FURNISHING | 2018-01-23 | 2018-10-19 | 2018-01-23 | 2018-10-19
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-399 | CA Hudson River Drainage Chamber | 9 | SUBSTANTIAL COMPLETION | 2018-10-20 | 2019-04-17 | 2018-10-20 | 2027-04-15
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-399 | CA Hudson River Drainage Chamber | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-04-18 | 2019-07-16 | 2027-04-16 | 2027-07-14
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-431 | CATSKILL AQUEDUCT RECONST.-KENSICO TO HILVIEW | 1 | DEVELOP SCOPE | 2015-06-30 | 2015-09-27 | 2015-06-30 | 2016-03-25
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-431 | CATSKILL AQUEDUCT RECONST.-KENSICO TO HILVIEW | 2 | PRELIMINARY DESIGN | 2015-09-28 | 2016-01-25 | 2016-03-26 | 2017-03-20
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-431 | CATSKILL AQUEDUCT RECONST.-KENSICO TO HILVIEW | 3 | FINAL DESIGN | 2016-01-26 | 2016-07-23 | 2017-03-21 | 2018-09-11
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-431 | CATSKILL AQUEDUCT RECONST.-KENSICO TO HILVIEW | 4 | BID AWARD AND REGISTER CONTRCT | 2016-07-24 | 2016-10-21 | 2018-09-12 | 2019-06-08
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-431 | CATSKILL AQUEDUCT RECONST.-KENSICO TO HILVIEW | 5 | CONSTRUCTION TO 25% | 2016-10-22 | 2017-02-18 | 2019-06-09 | 2020-06-02
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-431 | CATSKILL AQUEDUCT RECONST.-KENSICO TO HILVIEW | 6 | CONSTRUCTION TO 50% | 2017-02-19 | 2017-06-18 | 2020-06-03 | 2021-05-28
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-431 | CATSKILL AQUEDUCT RECONST.-KENSICO TO HILVIEW | 7 | CONSTRUCTION TO 75% | 2017-06-19 | 2017-10-16 | 2021-05-29 | 2022-05-23
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-431 | CATSKILL AQUEDUCT RECONST.-KENSICO TO HILVIEW | 8 | ORIGINAL EQUIP & FURNISHING | 2017-10-17 | 2018-01-14 | 2022-05-24 | 2023-02-17
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-431 | CATSKILL AQUEDUCT RECONST.-KENSICO TO HILVIEW | 9 | SUBSTANTIAL COMPLETION | 2018-01-15 | 2018-03-15 | 2023-02-18 | 2031-08-14
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-431 | CATSKILL AQUEDUCT RECONST.-KENSICO TO HILVIEW | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-03-16 | 2018-04-14 | 2031-08-15 | 2031-11-12
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-452 | WOH Catskill Acqueduct Chambers Rehab & Restoration | 1 | DEVELOP SCOPE | 2019-07-01 | 2020-03-26 | 2019-07-01 | 2020-03-26
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-452 | WOH Catskill Acqueduct Chambers Rehab & Restoration | 2 | PRELIMINARY DESIGN | 2020-03-27 | 2021-03-21 | 2020-03-27 | 2021-03-21
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-452 | WOH Catskill Acqueduct Chambers Rehab & Restoration | 3 | FINAL DESIGN | 2021-03-22 | 2022-09-12 | 2021-03-22 | 2022-09-12
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-452 | WOH Catskill Acqueduct Chambers Rehab & Restoration | 4 | BID AWARD AND REGISTER CONTRCT | 2022-09-13 | 2023-06-09 | 2022-09-13 | 2023-06-09
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-452 | WOH Catskill Acqueduct Chambers Rehab & Restoration | 5 | CONSTRUCTION TO 25% | 2023-06-10 | 2024-06-03 | 2023-06-10 | 2024-06-03
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-452 | WOH Catskill Acqueduct Chambers Rehab & Restoration | 6 | CONSTRUCTION TO 50% | 2024-06-04 | 2025-05-29 | 2024-06-04 | 2025-05-29
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-452 | WOH Catskill Acqueduct Chambers Rehab & Restoration | 7 | CONSTRUCTION TO 75% | 2025-05-30 | 2026-05-24 | 2025-05-30 | 2026-05-24
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-452 | WOH Catskill Acqueduct Chambers Rehab & Restoration | 8 | ORIGINAL EQUIP & FURNISHING | 2026-05-25 | 2027-02-18 | 2026-05-25 | 2027-02-18
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-452 | WOH Catskill Acqueduct Chambers Rehab & Restoration | 9 | SUBSTANTIAL COMPLETION | 2027-02-19 | 2027-08-17 | 2027-02-19 | 2027-08-17
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-452 | WOH Catskill Acqueduct Chambers Rehab & Restoration | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2027-08-18 | 2027-11-15 | 2027-08-18 | 2027-11-15
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-454 | RECONSTRUCTION GRAND GORGE WWTP | 1 | DEVELOP SCOPE | 2018-06-30 | 2019-03-26 | 2018-06-30 | 2019-03-26
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-454 | RECONSTRUCTION GRAND GORGE WWTP | 2 | PRELIMINARY DESIGN | 2019-03-27 | 2020-03-20 | 2019-03-27 | 2020-03-20
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-454 | RECONSTRUCTION GRAND GORGE WWTP | 3 | FINAL DESIGN | 2020-03-21 | 2021-09-11 | 2020-03-21 | 2021-09-11
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-454 | RECONSTRUCTION GRAND GORGE WWTP | 4 | BID AWARD AND REGISTER CONTRCT | 2021-09-12 | 2022-06-08 | 2021-09-12 | 2022-06-08
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-454 | RECONSTRUCTION GRAND GORGE WWTP | 5 | CONSTRUCTION TO 25% | 2022-06-09 | 2023-06-03 | 2022-06-09 | 2023-06-03
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-454 | RECONSTRUCTION GRAND GORGE WWTP | 6 | CONSTRUCTION TO 50% | 2023-06-04 | 2024-05-28 | 2023-06-04 | 2024-05-28
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-454 | RECONSTRUCTION GRAND GORGE WWTP | 7 | CONSTRUCTION TO 75% | 2024-05-29 | 2025-05-23 | 2024-05-29 | 2025-05-23
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-454 | RECONSTRUCTION GRAND GORGE WWTP | 8 | ORIGINAL EQUIP & FURNISHING | 2025-05-24 | 2026-02-17 | 2025-05-24 | 2026-02-17
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-454 | RECONSTRUCTION GRAND GORGE WWTP | 9 | SUBSTANTIAL COMPLETION | 2026-02-18 | 2026-08-16 | 2026-02-18 | 2026-08-16
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-454 | RECONSTRUCTION GRAND GORGE WWTP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2026-08-17 | 2026-11-14 | 2026-08-17 | 2026-11-14
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-455 | RECONSTRUCTION TANNERSVILLE WWTP | 1 | DEVELOP SCOPE | 2019-06-30 | 2020-03-25 | 2019-06-30 | 2020-03-25
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-455 | RECONSTRUCTION TANNERSVILLE WWTP | 2 | PRELIMINARY DESIGN | 2020-03-26 | 2021-03-20 | 2020-03-26 | 2021-03-20
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-455 | RECONSTRUCTION TANNERSVILLE WWTP | 3 | FINAL DESIGN | 2021-03-21 | 2022-09-11 | 2021-03-21 | 2022-09-11
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-455 | RECONSTRUCTION TANNERSVILLE WWTP | 4 | BID AWARD AND REGISTER CONTRCT | 2022-09-12 | 2023-06-08 | 2022-09-12 | 2023-06-08
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-455 | RECONSTRUCTION TANNERSVILLE WWTP | 5 | CONSTRUCTION TO 25% | 2023-06-09 | 2024-06-02 | 2023-06-09 | 2024-06-02
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-455 | RECONSTRUCTION TANNERSVILLE WWTP | 6 | CONSTRUCTION TO 50% | 2024-06-03 | 2025-05-28 | 2024-06-03 | 2025-05-28
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-455 | RECONSTRUCTION TANNERSVILLE WWTP | 7 | CONSTRUCTION TO 75% | 2025-05-29 | 2026-05-23 | 2025-05-29 | 2026-05-23
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-455 | RECONSTRUCTION TANNERSVILLE WWTP | 8 | ORIGINAL EQUIP & FURNISHING | 2026-05-24 | 2027-02-17 | 2026-05-24 | 2027-02-17
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-455 | RECONSTRUCTION TANNERSVILLE WWTP | 9 | SUBSTANTIAL COMPLETION | 2027-02-18 | 2027-08-16 | 2027-02-18 | 2027-08-16
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-455 | RECONSTRUCTION TANNERSVILLE WWTP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2027-08-17 | 2027-11-14 | 2027-08-17 | 2027-11-14
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-475 | GILBOA HLO | 1 | DEVELOP SCOPE | 2019-06-30 | 2020-03-25 | 2019-06-30 | 2020-03-25
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-475 | GILBOA HLO | 2 | PRELIMINARY DESIGN | 2020-03-26 | 2021-03-20 | 2020-03-26 | 2021-03-20
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-475 | GILBOA HLO | 3 | FINAL DESIGN | 2021-03-21 | 2022-09-11 | 2021-03-21 | 2022-09-11
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-475 | GILBOA HLO | 4 | BID AWARD AND REGISTER CONTRCT | 2022-09-12 | 2023-06-08 | 2022-09-12 | 2023-06-08
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-475 | GILBOA HLO | 5 | CONSTRUCTION TO 25% | 2023-06-09 | 2024-06-02 | 2023-06-09 | 2024-06-02
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-475 | GILBOA HLO | 6 | CONSTRUCTION TO 50% | 2024-06-03 | 2025-05-28 | 2024-06-03 | 2025-05-28
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-475 | GILBOA HLO | 7 | CONSTRUCTION TO 75% | 2025-05-29 | 2026-05-23 | 2025-05-29 | 2026-05-23
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-475 | GILBOA HLO | 8 | ORIGINAL EQUIP & FURNISHING | 2026-05-24 | 2027-02-17 | 2026-05-24 | 2027-02-17
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-475 | GILBOA HLO | 9 | SUBSTANTIAL COMPLETION | 2027-02-18 | 2027-08-16 | 2027-02-18 | 2027-08-16
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-475 | GILBOA HLO | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2027-08-17 | 2027-11-14 | 2027-08-17 | 2027-11-14
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-477 | Catskill Acqueduct Pressure Tunnels | 1 | DEVELOP SCOPE | 2019-06-01 | 2020-02-25 | 2019-06-01 | 2020-02-25
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-477 | Catskill Acqueduct Pressure Tunnels | 2 | PRELIMINARY DESIGN | 2020-02-26 | 2021-02-19 | 2020-02-26 | 2021-02-19
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-477 | Catskill Acqueduct Pressure Tunnels | 3 | FINAL DESIGN | 2021-02-20 | 2022-08-13 | 2021-02-20 | 2022-08-13
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-477 | Catskill Acqueduct Pressure Tunnels | 4 | BID AWARD AND REGISTER CONTRCT | 2022-08-14 | 2023-05-10 | 2022-08-14 | 2023-05-10
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-477 | Catskill Acqueduct Pressure Tunnels | 5 | CONSTRUCTION TO 25% | 2023-05-11 | 2024-05-04 | 2023-05-11 | 2024-05-04
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-477 | Catskill Acqueduct Pressure Tunnels | 6 | CONSTRUCTION TO 50% | 2024-05-05 | 2025-04-29 | 2024-05-05 | 2025-04-29
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-477 | Catskill Acqueduct Pressure Tunnels | 7 | CONSTRUCTION TO 75% | 2025-04-30 | 2026-04-24 | 2025-04-30 | 2026-04-24
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-477 | Catskill Acqueduct Pressure Tunnels | 8 | ORIGINAL EQUIP & FURNISHING | 2026-04-25 | 2027-01-19 | 2026-04-25 | 2027-01-19
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-477 | Catskill Acqueduct Pressure Tunnels | 9 | SUBSTANTIAL COMPLETION | 2027-01-20 | 2027-07-18 | 2027-01-20 | 2027-07-18
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-477 | Catskill Acqueduct Pressure Tunnels | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2027-07-19 | 2027-10-16 | 2027-07-19 | 2027-10-16
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-508 | DR-30 Culvert Repair & Embankment Stabilization | 1 | DEVELOP SCOPE | 2019-07-01 | 2020-03-26 | 2019-07-01 | 2020-03-26
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-508 | DR-30 Culvert Repair & Embankment Stabilization | 2 | PRELIMINARY DESIGN | 2020-03-27 | 2021-03-21 | 2020-03-27 | 2021-03-21
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-508 | DR-30 Culvert Repair & Embankment Stabilization | 3 | FINAL DESIGN | 2021-03-22 | 2022-09-12 | 2021-03-22 | 2022-09-12
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-508 | DR-30 Culvert Repair & Embankment Stabilization | 4 | BID AWARD AND REGISTER CONTRCT | 2022-09-13 | 2023-06-09 | 2022-09-13 | 2023-06-09
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-508 | DR-30 Culvert Repair & Embankment Stabilization | 5 | CONSTRUCTION TO 25% | 2023-06-10 | 2024-06-03 | 2023-06-10 | 2024-06-03
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-508 | DR-30 Culvert Repair & Embankment Stabilization | 6 | CONSTRUCTION TO 50% | 2024-06-04 | 2025-05-29 | 2024-06-04 | 2025-05-29
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-508 | DR-30 Culvert Repair & Embankment Stabilization | 7 | CONSTRUCTION TO 75% | 2025-05-30 | 2026-05-24 | 2025-05-30 | 2026-05-24
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-508 | DR-30 Culvert Repair & Embankment Stabilization | 8 | ORIGINAL EQUIP & FURNISHING | 2026-05-25 | 2027-02-18 | 2026-05-25 | 2027-02-18
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-508 | DR-30 Culvert Repair & Embankment Stabilization | 9 | SUBSTANTIAL COMPLETION | 2027-02-19 | 2027-08-17 | 2027-02-19 | 2027-08-17
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-508 | DR-30 Culvert Repair & Embankment Stabilization | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2027-08-18 | 2027-11-15 | 2027-08-18 | 2027-11-15
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-511 | Grand Gorge and Tannersville WWTP Collection System Repairs | 1 | DEVELOP SCOPE | 2021-06-01 | 2022-02-25 | 2021-06-01 | 2022-02-25
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-511 | Grand Gorge and Tannersville WWTP Collection System Repairs | 2 | PRELIMINARY DESIGN | 2022-02-26 | 2023-02-20 | 2022-02-26 | 2023-02-20
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-511 | Grand Gorge and Tannersville WWTP Collection System Repairs | 3 | FINAL DESIGN | 2023-02-21 | 2024-08-13 | 2023-02-21 | 2024-08-13
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-511 | Grand Gorge and Tannersville WWTP Collection System Repairs | 4 | BID AWARD AND REGISTER CONTRCT | 2024-08-14 | 2025-05-10 | 2024-08-14 | 2025-05-10
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-511 | Grand Gorge and Tannersville WWTP Collection System Repairs | 5 | CONSTRUCTION TO 25% | 2025-05-11 | 2026-05-05 | 2025-05-11 | 2026-05-05
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-511 | Grand Gorge and Tannersville WWTP Collection System Repairs | 6 | CONSTRUCTION TO 50% | 2026-05-06 | 2027-04-30 | 2026-05-06 | 2027-04-30
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-511 | Grand Gorge and Tannersville WWTP Collection System Repairs | 7 | CONSTRUCTION TO 75% | 2027-05-01 | 2028-04-24 | 2027-05-01 | 2028-04-24
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-511 | Grand Gorge and Tannersville WWTP Collection System Repairs | 8 | ORIGINAL EQUIP & FURNISHING | 2028-04-25 | 2029-01-19 | 2028-04-25 | 2029-01-19
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-511 | Grand Gorge and Tannersville WWTP Collection System Repairs | 9 | SUBSTANTIAL COMPLETION | 2029-01-20 | 2037-07-16 | 2029-01-20 | 2037-07-16
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-511 | Grand Gorge and Tannersville WWTP Collection System Repairs | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2037-07-17 | 2037-10-14 | 2037-07-17 | 2037-10-14
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-OPTIM | To Increase the Capacity of Upper Catskill Aqueduct | 1 | DEVELOP SCOPE | 2011-01-01 | 2011-12-31 | 2013-07-01 | 2014-03-27
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-OPTIM | To Increase the Capacity of Upper Catskill Aqueduct | 2 | PRELIMINARY DESIGN | 2012-01-01 | 2012-05-29 | 2014-03-28 | 2015-03-22
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-OPTIM | To Increase the Capacity of Upper Catskill Aqueduct | 3 | FINAL DESIGN | 2012-05-30 | 2012-12-25 | 2015-03-23 | 2016-09-12
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-OPTIM | To Increase the Capacity of Upper Catskill Aqueduct | 4 | BID AWARD AND REGISTER CONTRCT | 2012-12-26 | 2013-09-21 | 2016-09-13 | 2017-06-09
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-OPTIM | To Increase the Capacity of Upper Catskill Aqueduct | 5 | CONSTRUCTION TO 25% | 2013-09-22 | 2014-03-20 | 2017-06-10 | 2018-06-04
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-OPTIM | To Increase the Capacity of Upper Catskill Aqueduct | 6 | CONSTRUCTION TO 50% | 2014-03-21 | 2014-12-15 | 2018-06-05 | 2019-05-30
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-OPTIM | To Increase the Capacity of Upper Catskill Aqueduct | 7 | CONSTRUCTION TO 75% | 2014-12-16 | 2015-03-15 | 2019-05-31 | 2020-05-24
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-OPTIM | To Increase the Capacity of Upper Catskill Aqueduct | 8 | ORIGINAL EQUIP & FURNISHING | 2015-03-16 | 2015-06-13 | 2020-05-25 | 2021-02-18
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-OPTIM | To Increase the Capacity of Upper Catskill Aqueduct | 9 | SUBSTANTIAL COMPLETION | 2015-06-14 | 2015-09-21 | 2021-02-19 | 2021-08-17
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-OPTIM | To Increase the Capacity of Upper Catskill Aqueduct | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-09-22 | 2015-12-30 | 2021-08-18 | 2021-11-15
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-208 | RECONSTRUCTION OF NEW CROTON DAM,EOH | 2 | PRELIMINARY DESIGN | 1992-09-10 | 1993-09-04 | 2013-06-15 | 2014-06-09
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-208 | RECONSTRUCTION OF NEW CROTON DAM,EOH | 3 | FINAL DESIGN | 1993-09-05 | 1995-02-26 | 2014-06-10 | 2015-12-01
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-208 | RECONSTRUCTION OF NEW CROTON DAM,EOH | 4 | BID AWARD AND REGISTER CONTRCT | 1995-02-27 | 1995-11-23 | 2015-12-02 | 2016-08-27
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-208 | RECONSTRUCTION OF NEW CROTON DAM,EOH | 5 | CONSTRUCTION TO 25% | 1995-11-24 | 1996-11-17 | 2016-08-28 | 2017-08-22
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-208 | RECONSTRUCTION OF NEW CROTON DAM,EOH | 6 | CONSTRUCTION TO 50% | 1996-11-18 | 1997-11-12 | 2017-08-23 | 2018-08-17
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-208 | RECONSTRUCTION OF NEW CROTON DAM,EOH | 7 | CONSTRUCTION TO 75% | 1997-11-13 | 1998-11-07 | 2018-08-18 | 2019-08-12
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-208 | RECONSTRUCTION OF NEW CROTON DAM,EOH | 8 | ORIGINAL EQUIP & FURNISHING | 1998-11-08 | 1999-08-04 | 2019-08-13 | 2020-05-08
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-208 | RECONSTRUCTION OF NEW CROTON DAM,EOH | 9 | SUBSTANTIAL COMPLETION | 1999-08-05 | 2000-01-31 | 2020-05-09 | 2024-11-03
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-208 | RECONSTRUCTION OF NEW CROTON DAM,EOH | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2000-02-01 | 2000-04-30 | 2024-11-04 | 2025-02-01
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-208B | NEW CROTON DAM RECONSTRUCTION | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-09-28 | 2016-07-01 | 2016-09-28
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-208B | NEW CROTON DAM RECONSTRUCTION | 2 | PRELIMINARY DESIGN | 2016-09-29 | 2017-01-26 | 2016-09-29 | 2017-06-05
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-208B | NEW CROTON DAM RECONSTRUCTION | 3 | FINAL DESIGN | 2017-01-27 | 2017-07-25 | 2017-06-06 | 2018-02-10
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-208B | NEW CROTON DAM RECONSTRUCTION | 4 | BID AWARD AND REGISTER CONTRCT | 2017-07-26 | 2017-10-23 | 2018-02-11 | 2018-05-21
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-208B | NEW CROTON DAM RECONSTRUCTION | 5 | CONSTRUCTION TO 25% | 2017-10-24 | 2018-02-20 | 2018-05-22 | 2018-09-18
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-208B | NEW CROTON DAM RECONSTRUCTION | 6 | CONSTRUCTION TO 50% | 2018-02-21 | 2018-06-20 | 2018-09-19 | 2019-01-16
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-208B | NEW CROTON DAM RECONSTRUCTION | 7 | CONSTRUCTION TO 75% | 2018-06-21 | 2018-10-18 | 2019-01-17 | 2019-05-16
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-208B | NEW CROTON DAM RECONSTRUCTION | 8 | ORIGINAL EQUIP & FURNISHING | 2018-10-19 | 2019-01-16 | 2019-05-17 | 2019-08-14
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-208B | NEW CROTON DAM RECONSTRUCTION | 9 | SUBSTANTIAL COMPLETION | 2019-01-17 | 2019-03-17 | 2019-08-15 | 2019-10-13
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-208B | NEW CROTON DAM RECONSTRUCTION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-03-18 | 2019-04-16 | 2019-10-14 | 2022-11-12
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-357 | INSTALLATION OF A TELEMETRY SYSTEM, EAST-OF-HUDSON DISTRICT | 1 | DEVELOP SCOPE | 2006-02-20 | 2006-05-20 | 2018-08-17 | 2018-11-14
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-357 | INSTALLATION OF A TELEMETRY SYSTEM, EAST-OF-HUDSON DISTRICT | 2 | PRELIMINARY DESIGN | 2006-05-21 | 2006-09-17 | 2018-11-15 | 2019-03-14
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-357 | INSTALLATION OF A TELEMETRY SYSTEM, EAST-OF-HUDSON DISTRICT | 3 | FINAL DESIGN | 2006-09-18 | 2007-03-16 | 2019-03-15 | 2019-09-10
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-357 | INSTALLATION OF A TELEMETRY SYSTEM, EAST-OF-HUDSON DISTRICT | 4 | BID AWARD AND REGISTER CONTRCT | 2007-03-17 | 2007-06-14 | 2019-09-11 | 2019-12-09
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-357 | INSTALLATION OF A TELEMETRY SYSTEM, EAST-OF-HUDSON DISTRICT | 5 | CONSTRUCTION TO 25% | 2007-06-15 | 2007-10-12 | 2019-12-10 | 2020-04-07
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-357 | INSTALLATION OF A TELEMETRY SYSTEM, EAST-OF-HUDSON DISTRICT | 6 | CONSTRUCTION TO 50% | 2007-10-13 | 2008-02-09 | 2020-04-08 | 2020-08-05
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-357 | INSTALLATION OF A TELEMETRY SYSTEM, EAST-OF-HUDSON DISTRICT | 7 | CONSTRUCTION TO 75% | 2008-02-10 | 2008-06-08 | 2020-08-06 | 2020-12-03
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-357 | INSTALLATION OF A TELEMETRY SYSTEM, EAST-OF-HUDSON DISTRICT | 8 | ORIGINAL EQUIP & FURNISHING | 2008-06-09 | 2008-09-06 | 2020-12-04 | 2021-03-03
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-357 | INSTALLATION OF A TELEMETRY SYSTEM, EAST-OF-HUDSON DISTRICT | 9 | SUBSTANTIAL COMPLETION | 2008-09-07 | 2008-11-05 | 2021-03-04 | 2021-05-02
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-357 | INSTALLATION OF A TELEMETRY SYSTEM, EAST-OF-HUDSON DISTRICT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-11-06 | 2008-12-05 | 2021-05-03 | 2021-06-01
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-366 | REPLACE DOORS, EAST-OF-HUDSON DISTRICT | 1 | DEVELOP SCOPE | 2007-03-01 | 2007-05-29 | 2005-08-01 | 2006-04-27
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-366 | REPLACE DOORS, EAST-OF-HUDSON DISTRICT | 2 | PRELIMINARY DESIGN | 2007-05-30 | 2007-09-26 | 2006-04-28 | 2007-04-22
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-366 | REPLACE DOORS, EAST-OF-HUDSON DISTRICT | 3 | FINAL DESIGN | 2007-09-27 | 2008-03-24 | 2007-04-23 | 2008-10-13
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-366 | REPLACE DOORS, EAST-OF-HUDSON DISTRICT | 4 | BID AWARD AND REGISTER CONTRCT | 2008-03-25 | 2008-06-22 | 2008-10-14 | 2009-07-10
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-366 | REPLACE DOORS, EAST-OF-HUDSON DISTRICT | 5 | CONSTRUCTION TO 25% | 2008-06-23 | 2008-10-20 | 2009-07-11 | 2010-07-05
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-366 | REPLACE DOORS, EAST-OF-HUDSON DISTRICT | 6 | CONSTRUCTION TO 50% | 2008-10-21 | 2009-02-17 | 2010-07-06 | 2011-06-30
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-366 | REPLACE DOORS, EAST-OF-HUDSON DISTRICT | 7 | CONSTRUCTION TO 75% | 2009-02-18 | 2009-06-17 | 2011-07-01 | 2012-06-24
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-366 | REPLACE DOORS, EAST-OF-HUDSON DISTRICT | 8 | ORIGINAL EQUIP & FURNISHING | 2009-06-18 | 2009-09-15 | 2012-06-25 | 2013-03-21
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-366 | REPLACE DOORS, EAST-OF-HUDSON DISTRICT | 9 | SUBSTANTIAL COMPLETION | 2009-09-16 | 2009-11-14 | 2013-03-22 | 2021-09-15
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-366 | REPLACE DOORS, EAST-OF-HUDSON DISTRICT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2009-11-15 | 2009-12-14 | 2021-09-16 | 2021-12-14
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-410 | NEW CROTON LAKE GATE HOUSE HVAC REHABILITATION | 1 | DEVELOP SCOPE | 2007-12-15 | 2008-03-13 | 2020-08-01 | 2020-10-29
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-410 | NEW CROTON LAKE GATE HOUSE HVAC REHABILITATION | 2 | PRELIMINARY DESIGN | 2008-03-14 | 2008-07-11 | 2020-10-30 | 2021-02-26
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-410 | NEW CROTON LAKE GATE HOUSE HVAC REHABILITATION | 3 | FINAL DESIGN | 2008-07-12 | 2009-01-07 | 2021-02-27 | 2021-08-25
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-410 | NEW CROTON LAKE GATE HOUSE HVAC REHABILITATION | 4 | BID AWARD AND REGISTER CONTRCT | 2009-01-08 | 2009-04-07 | 2021-08-26 | 2021-11-23
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-410 | NEW CROTON LAKE GATE HOUSE HVAC REHABILITATION | 5 | CONSTRUCTION TO 25% | 2009-04-08 | 2009-08-05 | 2021-11-24 | 2022-03-23
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-410 | NEW CROTON LAKE GATE HOUSE HVAC REHABILITATION | 6 | CONSTRUCTION TO 50% | 2009-08-06 | 2009-12-03 | 2022-03-24 | 2022-07-21
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-410 | NEW CROTON LAKE GATE HOUSE HVAC REHABILITATION | 7 | CONSTRUCTION TO 75% | 2009-12-04 | 2010-04-02 | 2022-07-22 | 2022-11-18
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-410 | NEW CROTON LAKE GATE HOUSE HVAC REHABILITATION | 8 | ORIGINAL EQUIP & FURNISHING | 2010-04-03 | 2010-07-01 | 2022-11-19 | 2023-02-16
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-410 | NEW CROTON LAKE GATE HOUSE HVAC REHABILITATION | 9 | SUBSTANTIAL COMPLETION | 2010-07-02 | 2010-08-30 | 2023-02-17 | 2023-04-17
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-410 | NEW CROTON LAKE GATE HOUSE HVAC REHABILITATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2010-08-31 | 2010-09-29 | 2023-04-18 | 2023-05-17
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-452 | WWTP - CYCLICAL EQUIPMENT REPLACEMENT | 1 | DEVELOP SCOPE | 2009-08-15 | 2009-11-12 | 2008-06-30 | 2009-03-26
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-452 | WWTP - CYCLICAL EQUIPMENT REPLACEMENT | 2 | PRELIMINARY DESIGN | 2009-11-13 | 2010-03-12 | 2009-03-27 | 2010-03-21
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-452 | WWTP - CYCLICAL EQUIPMENT REPLACEMENT | 3 | FINAL DESIGN | 2010-03-13 | 2010-09-08 | 2010-03-22 | 2011-09-12
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-452 | WWTP - CYCLICAL EQUIPMENT REPLACEMENT | 4 | BID AWARD AND REGISTER CONTRCT | 2010-09-09 | 2010-12-07 | 2011-09-13 | 2012-06-08
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-452 | WWTP - CYCLICAL EQUIPMENT REPLACEMENT | 5 | CONSTRUCTION TO 25% | 2010-12-08 | 2011-04-06 | 2012-06-09 | 2013-06-03
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-452 | WWTP - CYCLICAL EQUIPMENT REPLACEMENT | 6 | CONSTRUCTION TO 50% | 2011-04-07 | 2011-08-04 | 2013-06-04 | 2014-05-29
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-452 | WWTP - CYCLICAL EQUIPMENT REPLACEMENT | 7 | CONSTRUCTION TO 75% | 2011-08-05 | 2011-12-02 | 2014-05-30 | 2015-05-24
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-452 | WWTP - CYCLICAL EQUIPMENT REPLACEMENT | 8 | ORIGINAL EQUIP & FURNISHING | 2011-12-03 | 2012-03-01 | 2015-05-25 | 2016-02-18
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-452 | WWTP - CYCLICAL EQUIPMENT REPLACEMENT | 9 | SUBSTANTIAL COMPLETION | 2012-03-02 | 2012-04-30 | 2016-02-19 | 2028-08-13
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-452 | WWTP - CYCLICAL EQUIPMENT REPLACEMENT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-05-01 | 2012-05-30 | 2028-08-14 | 2028-11-11
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-497 | Aqueduct Erosion Restoration at EOH | 1 | DEVELOP SCOPE | 2009-08-01 | 2009-10-29 | 2018-06-30 | 2019-03-26
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-497 | Aqueduct Erosion Restoration at EOH | 2 | PRELIMINARY DESIGN | 2009-10-30 | 2010-02-26 | 2019-03-27 | 2020-03-20
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-497 | Aqueduct Erosion Restoration at EOH | 3 | FINAL DESIGN | 2010-02-27 | 2010-08-25 | 2020-03-21 | 2021-09-11
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-497 | Aqueduct Erosion Restoration at EOH | 4 | BID AWARD AND REGISTER CONTRCT | 2010-08-26 | 2010-11-23 | 2021-09-12 | 2022-06-08
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-497 | Aqueduct Erosion Restoration at EOH | 5 | CONSTRUCTION TO 25% | 2010-11-24 | 2011-03-23 | 2022-06-09 | 2023-06-03
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-497 | Aqueduct Erosion Restoration at EOH | 6 | CONSTRUCTION TO 50% | 2011-03-24 | 2011-07-21 | 2023-06-04 | 2024-05-28
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-497 | Aqueduct Erosion Restoration at EOH | 7 | CONSTRUCTION TO 75% | 2011-07-22 | 2011-11-18 | 2024-05-29 | 2025-05-23
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-497 | Aqueduct Erosion Restoration at EOH | 8 | ORIGINAL EQUIP & FURNISHING | 2011-11-19 | 2012-02-16 | 2025-05-24 | 2026-02-17
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-497 | Aqueduct Erosion Restoration at EOH | 9 | SUBSTANTIAL COMPLETION | 2012-02-17 | 2012-04-16 | 2026-02-18 | 2026-08-16
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-497 | Aqueduct Erosion Restoration at EOH | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-04-17 | 2012-05-16 | 2026-08-17 | 2026-11-14
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-502 | Road Improvement due to Kensico Dam Road Closure | 1 | DEVELOP SCOPE | 2009-09-01 | 2009-11-29 | 2009-09-01 | 2010-05-28
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-502 | Road Improvement due to Kensico Dam Road Closure | 2 | PRELIMINARY DESIGN | 2009-11-30 | 2010-03-29 | 2010-05-29 | 2011-05-23
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-502 | Road Improvement due to Kensico Dam Road Closure | 3 | FINAL DESIGN | 2010-03-30 | 2010-09-25 | 2011-05-24 | 2012-11-13
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-502 | Road Improvement due to Kensico Dam Road Closure | 4 | BID AWARD AND REGISTER CONTRCT | 2010-09-26 | 2010-12-24 | 2012-11-14 | 2013-08-10
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-502 | Road Improvement due to Kensico Dam Road Closure | 5 | CONSTRUCTION TO 25% | 2010-12-25 | 2011-04-23 | 2013-08-11 | 2014-08-05
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-502 | Road Improvement due to Kensico Dam Road Closure | 6 | CONSTRUCTION TO 50% | 2011-04-24 | 2011-08-21 | 2014-08-06 | 2015-07-31
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-502 | Road Improvement due to Kensico Dam Road Closure | 7 | CONSTRUCTION TO 75% | 2011-08-22 | 2011-12-19 | 2015-08-01 | 2016-07-25
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-502 | Road Improvement due to Kensico Dam Road Closure | 8 | ORIGINAL EQUIP & FURNISHING | 2011-12-20 | 2012-03-18 | 2016-07-26 | 2017-04-21
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-502 | Road Improvement due to Kensico Dam Road Closure | 9 | SUBSTANTIAL COMPLETION | 2012-03-19 | 2012-05-17 | 2017-04-22 | 2025-10-16
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-502 | Road Improvement due to Kensico Dam Road Closure | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-05-18 | 2012-06-16 | 2025-10-17 | 2026-01-14
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-509 | Arcady Road Reconstruction | 1 | DEVELOP SCOPE | 2016-07-01 | 2017-03-27 | 2016-07-01 | 2017-03-27
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-509 | Arcady Road Reconstruction | 2 | PRELIMINARY DESIGN | 2017-03-28 | 2018-03-22 | 2017-03-28 | 2018-03-22
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-509 | Arcady Road Reconstruction | 3 | FINAL DESIGN | 2018-03-23 | 2019-09-13 | 2018-03-23 | 2019-09-13
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-509 | Arcady Road Reconstruction | 4 | BID AWARD AND REGISTER CONTRCT | 2019-09-14 | 2020-06-09 | 2019-09-14 | 2020-06-09
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-509 | Arcady Road Reconstruction | 5 | CONSTRUCTION TO 25% | 2020-06-10 | 2021-06-04 | 2020-06-10 | 2021-06-04
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-509 | Arcady Road Reconstruction | 6 | CONSTRUCTION TO 50% | 2021-06-05 | 2022-05-30 | 2021-06-05 | 2022-05-30
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-509 | Arcady Road Reconstruction | 7 | CONSTRUCTION TO 75% | 2022-05-31 | 2023-05-25 | 2022-05-31 | 2023-05-25
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-509 | Arcady Road Reconstruction | 8 | ORIGINAL EQUIP & FURNISHING | 2023-05-26 | 2024-02-19 | 2023-05-26 | 2024-02-19
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-509 | Arcady Road Reconstruction | 9 | SUBSTANTIAL COMPLETION | 2024-02-20 | 2024-08-17 | 2024-02-20 | 2024-08-17
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-509 | Arcady Road Reconstruction | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-08-18 | 2024-11-15 | 2024-08-18 | 2024-11-15
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-530 | Removal and reconstruction of DEP bridges, upstate watershed | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-09-28 | 2016-07-01 | 2017-03-27
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-530 | Removal and reconstruction of DEP bridges, upstate watershed | 2 | PRELIMINARY DESIGN | 2016-09-29 | 2017-01-26 | 2017-03-28 | 2018-03-22
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-530 | Removal and reconstruction of DEP bridges, upstate watershed | 3 | FINAL DESIGN | 2017-01-27 | 2017-07-25 | 2018-03-23 | 2019-09-13
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-530 | Removal and reconstruction of DEP bridges, upstate watershed | 4 | BID AWARD AND REGISTER CONTRCT | 2017-07-26 | 2017-10-23 | 2019-09-14 | 2020-06-09
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-530 | Removal and reconstruction of DEP bridges, upstate watershed | 5 | CONSTRUCTION TO 25% | 2017-10-24 | 2018-02-20 | 2020-06-10 | 2021-06-04
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-530 | Removal and reconstruction of DEP bridges, upstate watershed | 6 | CONSTRUCTION TO 50% | 2018-02-21 | 2018-06-20 | 2021-06-05 | 2022-05-30
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-530 | Removal and reconstruction of DEP bridges, upstate watershed | 7 | CONSTRUCTION TO 75% | 2018-06-21 | 2018-10-18 | 2022-05-31 | 2023-05-25
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-530 | Removal and reconstruction of DEP bridges, upstate watershed | 8 | ORIGINAL EQUIP & FURNISHING | 2018-10-19 | 2019-01-16 | 2023-05-26 | 2024-02-19
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-530 | Removal and reconstruction of DEP bridges, upstate watershed | 9 | SUBSTANTIAL COMPLETION | 2019-01-17 | 2019-03-17 | 2024-02-20 | 2032-08-15
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-530 | Removal and reconstruction of DEP bridges, upstate watershed | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-03-18 | 2019-04-16 | 2032-08-16 | 2032-11-13
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-534 | WEST BRANCH AUXILIARY DAM-CREEP REMEDIATION | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-09-28 | 2018-06-30 | 2019-03-26
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-534 | WEST BRANCH AUXILIARY DAM-CREEP REMEDIATION | 2 | PRELIMINARY DESIGN | 2017-09-29 | 2018-01-26 | 2019-03-27 | 2020-03-20
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-534 | WEST BRANCH AUXILIARY DAM-CREEP REMEDIATION | 3 | FINAL DESIGN | 2018-01-27 | 2018-07-25 | 2020-03-21 | 2021-09-11
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-534 | WEST BRANCH AUXILIARY DAM-CREEP REMEDIATION | 4 | BID AWARD AND REGISTER CONTRCT | 2018-07-26 | 2018-10-23 | 2021-09-12 | 2022-06-08
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-534 | WEST BRANCH AUXILIARY DAM-CREEP REMEDIATION | 5 | CONSTRUCTION TO 25% | 2018-10-24 | 2019-02-20 | 2022-06-09 | 2023-06-03
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-534 | WEST BRANCH AUXILIARY DAM-CREEP REMEDIATION | 6 | CONSTRUCTION TO 50% | 2019-02-21 | 2019-06-20 | 2023-06-04 | 2024-05-28
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-534 | WEST BRANCH AUXILIARY DAM-CREEP REMEDIATION | 7 | CONSTRUCTION TO 75% | 2019-06-21 | 2019-10-18 | 2024-05-29 | 2025-05-23
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-534 | WEST BRANCH AUXILIARY DAM-CREEP REMEDIATION | 8 | ORIGINAL EQUIP & FURNISHING | 2019-10-19 | 2020-01-16 | 2025-05-24 | 2026-02-17
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-534 | WEST BRANCH AUXILIARY DAM-CREEP REMEDIATION | 9 | SUBSTANTIAL COMPLETION | 2020-01-17 | 2020-03-16 | 2026-02-18 | 2026-08-16
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-534 | WEST BRANCH AUXILIARY DAM-CREEP REMEDIATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-03-17 | 2020-04-15 | 2026-08-17 | 2026-11-14
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-536 | EOH Dam Facing | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-09-28 | 2016-07-01 | 2016-09-28
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-536 | EOH Dam Facing | 2 | PRELIMINARY DESIGN | 2017-09-29 | 2018-01-26 | 2016-09-29 | 2017-01-26
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-536 | EOH Dam Facing | 3 | FINAL DESIGN | 2018-01-27 | 2018-07-25 | 2017-01-27 | 2017-07-25
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-536 | EOH Dam Facing | 4 | BID AWARD AND REGISTER CONTRCT | 2018-07-26 | 2018-10-23 | 2017-07-26 | 2017-10-23
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-536 | EOH Dam Facing | 5 | CONSTRUCTION TO 25% | 2018-10-24 | 2019-02-20 | 2017-10-24 | 2018-02-20
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-536 | EOH Dam Facing | 6 | CONSTRUCTION TO 50% | 2019-02-21 | 2019-06-20 | 2018-02-21 | 2018-06-20
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-536 | EOH Dam Facing | 7 | CONSTRUCTION TO 75% | 2019-06-21 | 2019-10-18 | 2018-06-21 | 2018-10-18
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-536 | EOH Dam Facing | 8 | ORIGINAL EQUIP & FURNISHING | 2019-10-19 | 2020-01-16 | 2018-10-19 | 2019-01-16
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-536 | EOH Dam Facing | 9 | SUBSTANTIAL COMPLETION | 2020-01-17 | 2020-03-16 | 2019-01-17 | 2019-03-17
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-536 | EOH Dam Facing | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-03-17 | 2020-04-15 | 2019-03-18 | 2022-04-16
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-546 | Amawalk Dam Ogee Spillway Replacement | 1 | DEVELOP SCOPE | 2016-07-01 | 2017-03-27 | 2016-07-01 | 2017-03-27
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-546 | Amawalk Dam Ogee Spillway Replacement | 2 | PRELIMINARY DESIGN | 2017-03-28 | 2018-03-22 | 2017-03-28 | 2018-03-22
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-546 | Amawalk Dam Ogee Spillway Replacement | 3 | FINAL DESIGN | 2018-03-23 | 2019-09-13 | 2018-03-23 | 2019-09-13
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-546 | Amawalk Dam Ogee Spillway Replacement | 4 | BID AWARD AND REGISTER CONTRCT | 2019-09-14 | 2020-06-09 | 2019-09-14 | 2020-06-09
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-546 | Amawalk Dam Ogee Spillway Replacement | 5 | CONSTRUCTION TO 25% | 2020-06-10 | 2021-06-04 | 2020-06-10 | 2021-06-04
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-546 | Amawalk Dam Ogee Spillway Replacement | 6 | CONSTRUCTION TO 50% | 2021-06-05 | 2022-05-30 | 2021-06-05 | 2022-05-30
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-546 | Amawalk Dam Ogee Spillway Replacement | 7 | CONSTRUCTION TO 75% | 2022-05-31 | 2023-05-25 | 2022-05-31 | 2023-05-25
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-546 | Amawalk Dam Ogee Spillway Replacement | 8 | ORIGINAL EQUIP & FURNISHING | 2023-05-26 | 2024-02-19 | 2023-05-26 | 2024-02-19
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-546 | Amawalk Dam Ogee Spillway Replacement | 9 | SUBSTANTIAL COMPLETION | 2024-02-20 | 2024-08-17 | 2024-02-20 | 2024-08-17
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-546 | Amawalk Dam Ogee Spillway Replacement | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-08-18 | 2024-11-15 | 2024-08-18 | 2024-11-15
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-551 | Conversion of Kensico Lab to EOH Operations HQ | 1 | DEVELOP SCOPE | 2018-06-30 | 2019-03-26 | 2018-06-30 | 2019-03-26
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-551 | Conversion of Kensico Lab to EOH Operations HQ | 2 | PRELIMINARY DESIGN | 2019-03-27 | 2020-03-20 | 2019-03-27 | 2020-03-20
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-551 | Conversion of Kensico Lab to EOH Operations HQ | 3 | FINAL DESIGN | 2020-03-21 | 2021-09-11 | 2020-03-21 | 2021-09-11
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-551 | Conversion of Kensico Lab to EOH Operations HQ | 4 | BID AWARD AND REGISTER CONTRCT | 2021-09-12 | 2022-06-08 | 2021-09-12 | 2022-06-08
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-551 | Conversion of Kensico Lab to EOH Operations HQ | 5 | CONSTRUCTION TO 25% | 2022-06-09 | 2023-06-03 | 2022-06-09 | 2023-06-03
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-551 | Conversion of Kensico Lab to EOH Operations HQ | 6 | CONSTRUCTION TO 50% | 2023-06-04 | 2024-05-28 | 2023-06-04 | 2024-05-28
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-551 | Conversion of Kensico Lab to EOH Operations HQ | 7 | CONSTRUCTION TO 75% | 2024-05-29 | 2025-05-23 | 2024-05-29 | 2025-05-23
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-551 | Conversion of Kensico Lab to EOH Operations HQ | 8 | ORIGINAL EQUIP & FURNISHING | 2025-05-24 | 2026-02-17 | 2025-05-24 | 2026-02-17
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-551 | Conversion of Kensico Lab to EOH Operations HQ | 9 | SUBSTANTIAL COMPLETION | 2026-02-18 | 2026-08-16 | 2026-02-18 | 2026-08-16
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-551 | Conversion of Kensico Lab to EOH Operations HQ | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2026-08-17 | 2026-11-14 | 2026-08-17 | 2026-11-14
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-552 | Shaft 18 Traveling Screens & Other Work | 1 | DEVELOP SCOPE | 2020-06-30 | 2021-03-26 | 2020-06-30 | 2021-03-26
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-552 | Shaft 18 Traveling Screens & Other Work | 2 | PRELIMINARY DESIGN | 2021-03-27 | 2022-03-21 | 2021-03-27 | 2022-03-21
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-552 | Shaft 18 Traveling Screens & Other Work | 3 | FINAL DESIGN | 2022-03-22 | 2023-09-12 | 2022-03-22 | 2023-09-12
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-552 | Shaft 18 Traveling Screens & Other Work | 4 | BID AWARD AND REGISTER CONTRCT | 2023-09-13 | 2024-06-08 | 2023-09-13 | 2024-06-08
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-552 | Shaft 18 Traveling Screens & Other Work | 5 | CONSTRUCTION TO 25% | 2024-06-09 | 2025-06-03 | 2024-06-09 | 2025-06-03
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-552 | Shaft 18 Traveling Screens & Other Work | 6 | CONSTRUCTION TO 50% | 2025-06-04 | 2026-05-29 | 2025-06-04 | 2026-05-29
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-552 | Shaft 18 Traveling Screens & Other Work | 7 | CONSTRUCTION TO 75% | 2026-05-30 | 2027-05-24 | 2026-05-30 | 2027-05-24
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-552 | Shaft 18 Traveling Screens & Other Work | 8 | ORIGINAL EQUIP & FURNISHING | 2027-05-25 | 2028-02-18 | 2027-05-25 | 2028-02-18
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-552 | Shaft 18 Traveling Screens & Other Work | 9 | SUBSTANTIAL COMPLETION | 2028-02-19 | 2028-08-16 | 2028-02-19 | 2028-08-16
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-552 | Shaft 18 Traveling Screens & Other Work | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2028-08-17 | 2028-11-14 | 2028-08-17 | 2028-11-14
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-553 | KENSICO SPILLWAY CRACK RECONSTRUCTION | 1 | DEVELOP SCOPE | 2021-06-30 | 2022-03-26 | 2021-06-30 | 2022-03-26
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-553 | KENSICO SPILLWAY CRACK RECONSTRUCTION | 2 | PRELIMINARY DESIGN | 2022-03-27 | 2023-03-21 | 2022-03-27 | 2023-03-21
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-553 | KENSICO SPILLWAY CRACK RECONSTRUCTION | 3 | FINAL DESIGN | 2023-03-22 | 2024-09-11 | 2023-03-22 | 2024-09-11
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-553 | KENSICO SPILLWAY CRACK RECONSTRUCTION | 4 | BID AWARD AND REGISTER CONTRCT | 2024-09-12 | 2025-06-08 | 2024-09-12 | 2025-06-08
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-553 | KENSICO SPILLWAY CRACK RECONSTRUCTION | 5 | CONSTRUCTION TO 25% | 2025-06-09 | 2026-06-03 | 2025-06-09 | 2026-06-03
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-553 | KENSICO SPILLWAY CRACK RECONSTRUCTION | 6 | CONSTRUCTION TO 50% | 2026-06-04 | 2027-05-29 | 2026-06-04 | 2027-05-29
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-553 | KENSICO SPILLWAY CRACK RECONSTRUCTION | 7 | CONSTRUCTION TO 75% | 2027-05-30 | 2028-05-23 | 2027-05-30 | 2028-05-23
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-553 | KENSICO SPILLWAY CRACK RECONSTRUCTION | 8 | ORIGINAL EQUIP & FURNISHING | 2028-05-24 | 2029-02-17 | 2028-05-24 | 2029-02-17
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-553 | KENSICO SPILLWAY CRACK RECONSTRUCTION | 9 | SUBSTANTIAL COMPLETION | 2029-02-18 | 2029-08-16 | 2029-02-18 | 2029-08-16
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-553 | KENSICO SPILLWAY CRACK RECONSTRUCTION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2029-08-17 | 2029-11-14 | 2029-08-17 | 2029-11-14
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-557 | Kensico Waterfowl Facility Construction & Paving | 1 | DEVELOP SCOPE | 2019-06-01 | 2019-08-29 | 2019-06-01 | 2019-08-29
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-557 | Kensico Waterfowl Facility Construction & Paving | 2 | PRELIMINARY DESIGN | 2019-08-30 | 2019-12-27 | 2019-08-30 | 2019-12-27
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-557 | Kensico Waterfowl Facility Construction & Paving | 3 | FINAL DESIGN | 2019-12-28 | 2020-06-24 | 2019-12-28 | 2020-06-24
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-557 | Kensico Waterfowl Facility Construction & Paving | 4 | BID AWARD AND REGISTER CONTRCT | 2020-06-25 | 2020-09-22 | 2020-06-25 | 2020-09-22
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-557 | Kensico Waterfowl Facility Construction & Paving | 5 | CONSTRUCTION TO 25% | 2020-09-23 | 2021-01-20 | 2020-09-23 | 2021-01-20
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-557 | Kensico Waterfowl Facility Construction & Paving | 6 | CONSTRUCTION TO 50% | 2021-01-21 | 2021-05-20 | 2021-01-21 | 2021-05-20
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-557 | Kensico Waterfowl Facility Construction & Paving | 7 | CONSTRUCTION TO 75% | 2021-05-21 | 2021-09-17 | 2021-05-21 | 2021-09-17
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-557 | Kensico Waterfowl Facility Construction & Paving | 8 | ORIGINAL EQUIP & FURNISHING | 2021-09-18 | 2021-12-16 | 2021-09-18 | 2021-12-16
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-557 | Kensico Waterfowl Facility Construction & Paving | 9 | SUBSTANTIAL COMPLETION | 2021-12-17 | 2022-02-14 | 2021-12-17 | 2022-02-14
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-557 | Kensico Waterfowl Facility Construction & Paving | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-02-15 | 2022-03-16 | 2022-02-15 | 2022-03-16
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-558 | Aqueduct Restoration at Lake Street - EOH | 1 | DEVELOP SCOPE | 2020-06-30 | 2020-09-27 | 2024-06-30 | 2025-03-26
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-558 | Aqueduct Restoration at Lake Street - EOH | 2 | PRELIMINARY DESIGN | 2020-09-28 | 2021-01-25 | 2025-03-27 | 2026-03-21
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-558 | Aqueduct Restoration at Lake Street - EOH | 3 | FINAL DESIGN | 2021-01-26 | 2021-07-24 | 2026-03-22 | 2027-09-12
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-558 | Aqueduct Restoration at Lake Street - EOH | 4 | BID AWARD AND REGISTER CONTRCT | 2021-07-25 | 2021-10-22 | 2027-09-13 | 2028-06-08
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-558 | Aqueduct Restoration at Lake Street - EOH | 5 | CONSTRUCTION TO 25% | 2021-10-23 | 2022-02-19 | 2028-06-09 | 2029-06-03
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-558 | Aqueduct Restoration at Lake Street - EOH | 6 | CONSTRUCTION TO 50% | 2022-02-20 | 2022-06-19 | 2029-06-04 | 2030-05-29
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-558 | Aqueduct Restoration at Lake Street - EOH | 7 | CONSTRUCTION TO 75% | 2022-06-20 | 2022-10-17 | 2030-05-30 | 2031-05-24
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-558 | Aqueduct Restoration at Lake Street - EOH | 8 | ORIGINAL EQUIP & FURNISHING | 2022-10-18 | 2023-01-15 | 2031-05-25 | 2032-02-18
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-558 | Aqueduct Restoration at Lake Street - EOH | 9 | SUBSTANTIAL COMPLETION | 2023-01-16 | 2023-03-16 | 2032-02-19 | 2040-08-14
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-558 | Aqueduct Restoration at Lake Street - EOH | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-03-17 | 2023-04-15 | 2040-08-15 | 2040-11-12
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-570 | HILLVIEW MAINTENANCE SHOP | 1 | DEVELOP SCOPE | 2020-01-01 | 2020-03-30 | 2020-01-01 | 2020-03-30
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-570 | HILLVIEW MAINTENANCE SHOP | 2 | PRELIMINARY DESIGN | 2020-03-31 | 2020-07-28 | 2020-03-31 | 2020-07-28
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-570 | HILLVIEW MAINTENANCE SHOP | 3 | FINAL DESIGN | 2020-07-29 | 2021-01-24 | 2020-07-29 | 2021-01-24
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-570 | HILLVIEW MAINTENANCE SHOP | 4 | BID AWARD AND REGISTER CONTRCT | 2021-01-25 | 2021-04-24 | 2021-01-25 | 2021-04-24
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-570 | HILLVIEW MAINTENANCE SHOP | 5 | CONSTRUCTION TO 25% | 2021-04-25 | 2021-08-22 | 2021-04-25 | 2021-08-22
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-570 | HILLVIEW MAINTENANCE SHOP | 6 | CONSTRUCTION TO 50% | 2021-08-23 | 2021-12-20 | 2021-08-23 | 2021-12-20
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-570 | HILLVIEW MAINTENANCE SHOP | 7 | CONSTRUCTION TO 75% | 2021-12-21 | 2022-04-19 | 2021-12-21 | 2022-04-19
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-570 | HILLVIEW MAINTENANCE SHOP | 8 | ORIGINAL EQUIP & FURNISHING | 2022-04-20 | 2022-07-18 | 2022-04-20 | 2022-07-18
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-570 | HILLVIEW MAINTENANCE SHOP | 9 | SUBSTANTIAL COMPLETION | 2022-07-19 | 2022-09-16 | 2022-07-19 | 2022-09-16
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-570 | HILLVIEW MAINTENANCE SHOP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-17 | 2022-10-16 | 2022-09-17 | 2022-10-16
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-589 | EASTVIEW MAINTENANCE SHOP | 1 | DEVELOP SCOPE | 2022-06-01 | 2022-08-29 | 2026-06-01 | 2027-02-25
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-589 | EASTVIEW MAINTENANCE SHOP | 2 | PRELIMINARY DESIGN | 2022-08-30 | 2022-12-27 | 2027-02-26 | 2028-02-20
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-589 | EASTVIEW MAINTENANCE SHOP | 3 | FINAL DESIGN | 2022-12-28 | 2023-06-25 | 2028-02-21 | 2029-08-13
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-589 | EASTVIEW MAINTENANCE SHOP | 4 | BID AWARD AND REGISTER CONTRCT | 2023-06-26 | 2023-09-23 | 2029-08-14 | 2030-05-10
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-589 | EASTVIEW MAINTENANCE SHOP | 5 | CONSTRUCTION TO 25% | 2023-09-24 | 2024-01-21 | 2030-05-11 | 2031-05-05
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-589 | EASTVIEW MAINTENANCE SHOP | 6 | CONSTRUCTION TO 50% | 2024-01-22 | 2024-05-20 | 2031-05-06 | 2032-04-29
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-589 | EASTVIEW MAINTENANCE SHOP | 7 | CONSTRUCTION TO 75% | 2024-05-21 | 2024-09-17 | 2032-04-30 | 2033-04-24
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-589 | EASTVIEW MAINTENANCE SHOP | 8 | ORIGINAL EQUIP & FURNISHING | 2024-09-18 | 2024-12-16 | 2033-04-25 | 2034-01-19
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-589 | EASTVIEW MAINTENANCE SHOP | 9 | SUBSTANTIAL COMPLETION | 2024-12-17 | 2025-02-14 | 2034-01-20 | 2038-07-17
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-589 | EASTVIEW MAINTENANCE SHOP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-02-15 | 2025-03-16 | 2038-07-18 | 2038-10-15
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-594 | UV FOUNDATION DRAIN MH PHASE 2 | 1 | DEVELOP SCOPE | 2019-06-01 | 2019-08-29 | 2019-06-01 | 2019-08-29
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-594 | UV FOUNDATION DRAIN MH PHASE 2 | 2 | PRELIMINARY DESIGN | 2019-08-30 | 2019-12-27 | 2019-08-30 | 2019-12-27
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-594 | UV FOUNDATION DRAIN MH PHASE 2 | 3 | FINAL DESIGN | 2019-12-28 | 2020-06-24 | 2019-12-28 | 2020-06-24
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-594 | UV FOUNDATION DRAIN MH PHASE 2 | 4 | BID AWARD AND REGISTER CONTRCT | 2020-06-25 | 2020-09-22 | 2020-06-25 | 2020-09-22
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-594 | UV FOUNDATION DRAIN MH PHASE 2 | 5 | CONSTRUCTION TO 25% | 2020-09-23 | 2021-01-20 | 2020-09-23 | 2021-01-20
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-594 | UV FOUNDATION DRAIN MH PHASE 2 | 6 | CONSTRUCTION TO 50% | 2021-01-21 | 2021-05-20 | 2021-01-21 | 2021-05-20
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-594 | UV FOUNDATION DRAIN MH PHASE 2 | 7 | CONSTRUCTION TO 75% | 2021-05-21 | 2021-09-17 | 2021-05-21 | 2021-09-17
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-594 | UV FOUNDATION DRAIN MH PHASE 2 | 8 | ORIGINAL EQUIP & FURNISHING | 2021-09-18 | 2021-12-16 | 2021-09-18 | 2021-12-16
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-594 | UV FOUNDATION DRAIN MH PHASE 2 | 9 | SUBSTANTIAL COMPLETION | 2021-12-17 | 2022-02-14 | 2021-12-17 | 2022-02-14
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-594 | UV FOUNDATION DRAIN MH PHASE 2 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-02-15 | 2022-03-16 | 2022-02-15 | 2022-03-16
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-607 | Shaft 17 Elevator Replacement | 1 | DEVELOP SCOPE | 2019-03-20 | 2019-06-17 | 2019-03-20 | 2019-06-17
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-607 | Shaft 17 Elevator Replacement | 2 | PRELIMINARY DESIGN | 2019-06-18 | 2019-10-15 | 2019-06-18 | 2019-10-15
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-607 | Shaft 17 Elevator Replacement | 3 | FINAL DESIGN | 2019-10-16 | 2020-04-12 | 2019-10-16 | 2020-04-12
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-607 | Shaft 17 Elevator Replacement | 4 | BID AWARD AND REGISTER CONTRCT | 2020-04-13 | 2020-07-11 | 2020-04-13 | 2020-07-11
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-607 | Shaft 17 Elevator Replacement | 5 | CONSTRUCTION TO 25% | 2020-07-12 | 2020-11-08 | 2020-07-12 | 2020-11-08
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-607 | Shaft 17 Elevator Replacement | 6 | CONSTRUCTION TO 50% | 2020-11-09 | 2021-03-08 | 2020-11-09 | 2021-03-08
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-607 | Shaft 17 Elevator Replacement | 7 | CONSTRUCTION TO 75% | 2021-03-09 | 2021-07-06 | 2021-03-09 | 2021-07-06
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-607 | Shaft 17 Elevator Replacement | 8 | ORIGINAL EQUIP & FURNISHING | 2021-07-07 | 2021-10-04 | 2021-07-07 | 2021-10-04
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-607 | Shaft 17 Elevator Replacement | 9 | SUBSTANTIAL COMPLETION | 2021-10-05 | 2021-12-03 | 2021-10-05 | 2021-12-03
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-607 | Shaft 17 Elevator Replacement | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-12-04 | 2022-01-02 | 2021-12-04 | 2022-01-02
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-609 | Cyclic Equipment Replacement for WTO | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-08-29 | 2020-06-01 | 2020-08-29
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-609 | Cyclic Equipment Replacement for WTO | 2 | PRELIMINARY DESIGN | 2020-08-30 | 2020-12-27 | 2020-08-30 | 2020-12-27
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-609 | Cyclic Equipment Replacement for WTO | 3 | FINAL DESIGN | 2020-12-28 | 2021-06-25 | 2020-12-28 | 2021-06-25
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-609 | Cyclic Equipment Replacement for WTO | 4 | BID AWARD AND REGISTER CONTRCT | 2021-06-26 | 2021-09-23 | 2021-06-26 | 2021-09-23
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-609 | Cyclic Equipment Replacement for WTO | 5 | CONSTRUCTION TO 25% | 2021-09-24 | 2022-01-21 | 2021-09-24 | 2022-01-21
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-609 | Cyclic Equipment Replacement for WTO | 6 | CONSTRUCTION TO 50% | 2022-01-22 | 2022-05-21 | 2022-01-22 | 2022-05-21
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-609 | Cyclic Equipment Replacement for WTO | 7 | CONSTRUCTION TO 75% | 2022-05-22 | 2022-09-18 | 2022-05-22 | 2022-09-18
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-609 | Cyclic Equipment Replacement for WTO | 8 | ORIGINAL EQUIP & FURNISHING | 2022-09-19 | 2022-12-17 | 2022-09-19 | 2022-12-17
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-609 | Cyclic Equipment Replacement for WTO | 9 | SUBSTANTIAL COMPLETION | 2022-12-18 | 2023-02-15 | 2022-12-18 | 2023-02-15
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-609 | Cyclic Equipment Replacement for WTO | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-02-16 | 2023-03-17 | 2023-02-16 | 2023-03-17
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-610 | Paving of Roadway at Hillview Complex | 1 | DEVELOP SCOPE | 2022-06-30 | 2022-09-27 | 2022-06-30 | 2022-09-27
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-610 | Paving of Roadway at Hillview Complex | 2 | PRELIMINARY DESIGN | 2022-09-28 | 2023-01-25 | 2022-09-28 | 2023-01-25
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-610 | Paving of Roadway at Hillview Complex | 3 | FINAL DESIGN | 2023-01-26 | 2023-07-24 | 2023-01-26 | 2023-07-24
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-610 | Paving of Roadway at Hillview Complex | 4 | BID AWARD AND REGISTER CONTRCT | 2023-07-25 | 2023-10-22 | 2023-07-25 | 2023-10-22
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-610 | Paving of Roadway at Hillview Complex | 5 | CONSTRUCTION TO 25% | 2023-10-23 | 2024-02-19 | 2023-10-23 | 2024-02-19
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-610 | Paving of Roadway at Hillview Complex | 6 | CONSTRUCTION TO 50% | 2024-02-20 | 2024-06-18 | 2024-02-20 | 2024-06-18
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-610 | Paving of Roadway at Hillview Complex | 7 | CONSTRUCTION TO 75% | 2024-06-19 | 2024-10-16 | 2024-06-19 | 2024-10-16
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-610 | Paving of Roadway at Hillview Complex | 8 | ORIGINAL EQUIP & FURNISHING | 2024-10-17 | 2025-01-14 | 2024-10-17 | 2025-01-14
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-610 | Paving of Roadway at Hillview Complex | 9 | SUBSTANTIAL COMPLETION | 2025-01-15 | 2025-03-15 | 2025-01-15 | 2025-03-15
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-610 | Paving of Roadway at Hillview Complex | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-03-16 | 2025-04-14 | 2025-03-16 | 2025-04-14
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-611 | BWS Emergency Services Contract | 1 | DEVELOP SCOPE | 2020-06-01 | 2021-02-25 | 2020-06-01 | 2021-02-25
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-611 | BWS Emergency Services Contract | 2 | PRELIMINARY DESIGN | 2021-02-26 | 2022-02-20 | 2021-02-26 | 2022-02-20
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-611 | BWS Emergency Services Contract | 3 | FINAL DESIGN | 2022-02-21 | 2023-08-14 | 2022-02-21 | 2023-08-14
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-611 | BWS Emergency Services Contract | 4 | BID AWARD AND REGISTER CONTRCT | 2023-08-15 | 2024-05-10 | 2023-08-15 | 2024-05-10
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-611 | BWS Emergency Services Contract | 5 | CONSTRUCTION TO 25% | 2024-05-11 | 2025-05-05 | 2024-05-11 | 2025-05-05
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-611 | BWS Emergency Services Contract | 6 | CONSTRUCTION TO 50% | 2025-05-06 | 2026-04-30 | 2025-05-06 | 2026-04-30
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-611 | BWS Emergency Services Contract | 7 | CONSTRUCTION TO 75% | 2026-05-01 | 2027-04-25 | 2026-05-01 | 2027-04-25
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-611 | BWS Emergency Services Contract | 8 | ORIGINAL EQUIP & FURNISHING | 2027-04-26 | 2028-01-20 | 2027-04-26 | 2028-01-20
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-611 | BWS Emergency Services Contract | 9 | SUBSTANTIAL COMPLETION | 2028-01-21 | 2028-07-18 | 2028-01-21 | 2028-07-18
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-611 | BWS Emergency Services Contract | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2028-07-19 | 2028-10-16 | 2028-07-19 | 2028-10-16
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-LTCP2 | CITY-WIDE LONG TERM CONTROL PLAN FOR CSO ABATEMENT | 1 | DEVELOP SCOPE | 2012-07-16 | 2013-04-11 | 2012-07-16 | 2013-04-11
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-LTCP2 | CITY-WIDE LONG TERM CONTROL PLAN FOR CSO ABATEMENT | 2 | PRELIMINARY DESIGN | 2013-04-12 | 2014-04-06 | 2013-04-12 | 2014-04-06
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-LTCP2 | CITY-WIDE LONG TERM CONTROL PLAN FOR CSO ABATEMENT | 3 | FINAL DESIGN | 2014-04-07 | 2015-09-28 | 2014-04-07 | 2015-09-28
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-LTCP2 | CITY-WIDE LONG TERM CONTROL PLAN FOR CSO ABATEMENT | 4 | BID AWARD AND REGISTER CONTRCT | 2015-09-29 | 2016-06-24 | 2015-09-29 | 2016-06-24
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-LTCP2 | CITY-WIDE LONG TERM CONTROL PLAN FOR CSO ABATEMENT | 5 | CONSTRUCTION TO 25% | 2016-06-25 | 2017-06-19 | 2016-06-25 | 2017-06-19
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-LTCP2 | CITY-WIDE LONG TERM CONTROL PLAN FOR CSO ABATEMENT | 6 | CONSTRUCTION TO 50% | 2017-06-20 | 2018-06-14 | 2017-06-20 | 2018-06-14
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-LTCP2 | CITY-WIDE LONG TERM CONTROL PLAN FOR CSO ABATEMENT | 7 | CONSTRUCTION TO 75% | 2018-06-15 | 2019-06-09 | 2018-06-15 | 2019-06-09
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-LTCP2 | CITY-WIDE LONG TERM CONTROL PLAN FOR CSO ABATEMENT | 8 | ORIGINAL EQUIP & FURNISHING | 2019-06-10 | 2020-03-05 | 2019-06-10 | 2020-03-05
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-LTCP2 | CITY-WIDE LONG TERM CONTROL PLAN FOR CSO ABATEMENT | 9 | SUBSTANTIAL COMPLETION | 2020-03-06 | 2020-09-01 | 2020-03-06 | 2020-09-01
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-LTCP2 | CITY-WIDE LONG TERM CONTROL PLAN FOR CSO ABATEMENT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-02 | 2020-11-30 | 2020-09-02 | 2020-11-30
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-UPGRD | UPGRADES AT CSO FACILITIES | 1 | DEVELOP SCOPE | 2021-06-01 | 2022-02-25 | 2021-06-01 | 2022-02-25
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-UPGRD | UPGRADES AT CSO FACILITIES | 2 | PRELIMINARY DESIGN | 2022-02-26 | 2023-02-20 | 2022-02-26 | 2023-02-20
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-UPGRD | UPGRADES AT CSO FACILITIES | 3 | FINAL DESIGN | 2023-02-21 | 2024-08-13 | 2023-02-21 | 2024-08-13
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-UPGRD | UPGRADES AT CSO FACILITIES | 4 | BID AWARD AND REGISTER CONTRCT | 2024-08-14 | 2025-05-10 | 2024-08-14 | 2025-05-10
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-UPGRD | UPGRADES AT CSO FACILITIES | 5 | CONSTRUCTION TO 25% | 2025-05-11 | 2026-05-05 | 2025-05-11 | 2026-05-05
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-UPGRD | UPGRADES AT CSO FACILITIES | 6 | CONSTRUCTION TO 50% | 2026-05-06 | 2027-04-30 | 2026-05-06 | 2027-04-30
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-UPGRD | UPGRADES AT CSO FACILITIES | 7 | CONSTRUCTION TO 75% | 2027-05-01 | 2028-04-24 | 2027-05-01 | 2028-04-24
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-UPGRD | UPGRADES AT CSO FACILITIES | 8 | ORIGINAL EQUIP & FURNISHING | 2028-04-25 | 2029-01-19 | 2028-04-25 | 2029-01-19
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-UPGRD | UPGRADES AT CSO FACILITIES | 9 | SUBSTANTIAL COMPLETION | 2029-01-20 | 2029-07-18 | 2029-01-20 | 2029-07-18
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-UPGRD | UPGRADES AT CSO FACILITIES | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2029-07-19 | 2029-10-16 | 2029-07-19 | 2029-10-16
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CT12VENT | CITY TUNNELS1 & 2, REPLACE VENTURI LINES @ SHAFTS | 1 | DEVELOP SCOPE | 2013-06-30 | 2014-03-26 | 2013-06-30 | 2014-03-26
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CT12VENT | CITY TUNNELS1 & 2, REPLACE VENTURI LINES @ SHAFTS | 2 | PRELIMINARY DESIGN | 2014-03-27 | 2015-03-21 | 2014-03-27 | 2015-03-21
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CT12VENT | CITY TUNNELS1 & 2, REPLACE VENTURI LINES @ SHAFTS | 3 | FINAL DESIGN | 2015-03-22 | 2016-09-11 | 2015-03-22 | 2016-09-11
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CT12VENT | CITY TUNNELS1 & 2, REPLACE VENTURI LINES @ SHAFTS | 4 | BID AWARD AND REGISTER CONTRCT | 2016-09-12 | 2017-06-08 | 2016-09-12 | 2017-06-08
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CT12VENT | CITY TUNNELS1 & 2, REPLACE VENTURI LINES @ SHAFTS | 5 | CONSTRUCTION TO 25% | 2017-06-09 | 2018-06-03 | 2017-06-09 | 2018-06-03
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CT12VENT | CITY TUNNELS1 & 2, REPLACE VENTURI LINES @ SHAFTS | 6 | CONSTRUCTION TO 50% | 2018-06-04 | 2019-05-29 | 2018-06-04 | 2019-05-29
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CT12VENT | CITY TUNNELS1 & 2, REPLACE VENTURI LINES @ SHAFTS | 7 | CONSTRUCTION TO 75% | 2019-05-30 | 2020-05-23 | 2019-05-30 | 2020-05-23
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CT12VENT | CITY TUNNELS1 & 2, REPLACE VENTURI LINES @ SHAFTS | 8 | ORIGINAL EQUIP & FURNISHING | 2020-05-24 | 2021-02-17 | 2020-05-24 | 2021-02-17
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CT12VENT | CITY TUNNELS1 & 2, REPLACE VENTURI LINES @ SHAFTS | 9 | SUBSTANTIAL COMPLETION | 2021-02-18 | 2025-08-15 | 2021-02-18 | 2025-08-15
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CT12VENT | CITY TUNNELS1 & 2, REPLACE VENTURI LINES @ SHAFTS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-08-16 | 2025-11-13 | 2025-08-16 | 2025-11-13
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CT315B | CITY TUNNEL 3, REPAIR LEAK@ SHAFT 15B | 1 | DEVELOP SCOPE | 2016-03-14 | 2016-06-11 | 2016-03-14 | 2016-12-08
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CT315B | CITY TUNNEL 3, REPAIR LEAK@ SHAFT 15B | 2 | PRELIMINARY DESIGN | 2016-06-12 | 2016-10-09 | 2016-12-09 | 2017-12-03
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CT315B | CITY TUNNEL 3, REPAIR LEAK@ SHAFT 15B | 3 | FINAL DESIGN | 2016-10-10 | 2017-04-07 | 2017-12-04 | 2019-05-27
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CT315B | CITY TUNNEL 3, REPAIR LEAK@ SHAFT 15B | 4 | BID AWARD AND REGISTER CONTRCT | 2017-04-08 | 2017-07-06 | 2019-05-28 | 2020-02-21
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CT315B | CITY TUNNEL 3, REPAIR LEAK@ SHAFT 15B | 5 | CONSTRUCTION TO 25% | 2017-07-07 | 2017-11-03 | 2020-02-22 | 2021-02-15
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CT315B | CITY TUNNEL 3, REPAIR LEAK@ SHAFT 15B | 6 | CONSTRUCTION TO 50% | 2017-11-04 | 2018-03-03 | 2021-02-16 | 2022-02-10
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CT315B | CITY TUNNEL 3, REPAIR LEAK@ SHAFT 15B | 7 | CONSTRUCTION TO 75% | 2018-03-04 | 2018-07-01 | 2022-02-11 | 2023-02-05
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CT315B | CITY TUNNEL 3, REPAIR LEAK@ SHAFT 15B | 8 | ORIGINAL EQUIP & FURNISHING | 2018-07-02 | 2018-09-29 | 2023-02-06 | 2023-11-02
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CT315B | CITY TUNNEL 3, REPAIR LEAK@ SHAFT 15B | 9 | SUBSTANTIAL COMPLETION | 2018-09-30 | 2018-11-28 | 2023-11-03 | 2024-04-30
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CT315B | CITY TUNNEL 3, REPAIR LEAK@ SHAFT 15B | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-11-29 | 2018-12-28 | 2024-05-01 | 2024-07-29
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CT3CORR | Repairs & Remediate Corrosion Issues - CT 3 | 1 | DEVELOP SCOPE | 2017-08-01 | 2017-10-29 | 2016-07-01 | 2017-03-27
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CT3CORR | Repairs & Remediate Corrosion Issues - CT 3 | 2 | PRELIMINARY DESIGN | 2017-10-30 | 2018-02-26 | 2017-03-28 | 2018-03-22
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CT3CORR | Repairs & Remediate Corrosion Issues - CT 3 | 3 | FINAL DESIGN | 2018-02-27 | 2018-08-25 | 2018-03-23 | 2019-09-13
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CT3CORR | Repairs & Remediate Corrosion Issues - CT 3 | 4 | BID AWARD AND REGISTER CONTRCT | 2018-08-26 | 2018-11-23 | 2019-09-14 | 2020-06-09
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CT3CORR | Repairs & Remediate Corrosion Issues - CT 3 | 5 | CONSTRUCTION TO 25% | 2018-11-24 | 2019-03-23 | 2020-06-10 | 2021-06-04
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CT3CORR | Repairs & Remediate Corrosion Issues - CT 3 | 6 | CONSTRUCTION TO 50% | 2019-03-24 | 2019-07-21 | 2021-06-05 | 2022-05-30
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CT3CORR | Repairs & Remediate Corrosion Issues - CT 3 | 7 | CONSTRUCTION TO 75% | 2019-07-22 | 2019-11-18 | 2022-05-31 | 2023-05-25
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CT3CORR | Repairs & Remediate Corrosion Issues - CT 3 | 8 | ORIGINAL EQUIP & FURNISHING | 2019-11-19 | 2020-02-16 | 2023-05-26 | 2024-02-19
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CT3CORR | Repairs & Remediate Corrosion Issues - CT 3 | 9 | SUBSTANTIAL COMPLETION | 2020-02-17 | 2020-04-16 | 2024-02-20 | 2028-08-16
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CT3CORR | Repairs & Remediate Corrosion Issues - CT 3 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-04-17 | 2020-05-16 | 2028-08-17 | 2028-11-14
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-150 | Reconstruction of 2 Bridges & 9 Culverts (Dell. Watershed) | 2 | PRELIMINARY DESIGN | 2010-04-11 | 2011-04-05 | 2010-04-11 | 2011-04-05
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-150 | Reconstruction of 2 Bridges & 9 Culverts (Dell. Watershed) | 3 | FINAL DESIGN | 2011-04-06 | 2012-09-26 | 2011-04-06 | 2012-09-26
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-150 | Reconstruction of 2 Bridges & 9 Culverts (Dell. Watershed) | 4 | BID AWARD AND REGISTER CONTRCT | 2012-09-27 | 2013-06-23 | 2012-09-27 | 2013-06-23
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-150 | Reconstruction of 2 Bridges & 9 Culverts (Dell. Watershed) | 5 | CONSTRUCTION TO 25% | 2013-06-24 | 2014-06-18 | 2013-06-24 | 2014-06-18
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-150 | Reconstruction of 2 Bridges & 9 Culverts (Dell. Watershed) | 6 | CONSTRUCTION TO 50% | 2014-06-19 | 2015-06-13 | 2014-06-19 | 2015-06-13
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-150 | Reconstruction of 2 Bridges & 9 Culverts (Dell. Watershed) | 7 | CONSTRUCTION TO 75% | 2015-06-14 | 2016-06-07 | 2015-06-14 | 2016-06-07
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-150 | Reconstruction of 2 Bridges & 9 Culverts (Dell. Watershed) | 8 | ORIGINAL EQUIP & FURNISHING | 2016-06-08 | 2017-03-04 | 2016-06-08 | 2017-03-04
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-150 | Reconstruction of 2 Bridges & 9 Culverts (Dell. Watershed) | 9 | SUBSTANTIAL COMPLETION | 2017-03-05 | 2017-08-31 | 2017-03-05 | 2017-08-31
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-150 | Reconstruction of 2 Bridges & 9 Culverts (Dell. Watershed) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-09-01 | 2017-11-29 | 2017-09-01 | 2017-11-29
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-194 | Merriman Dam Spillway | 1 | DEVELOP SCOPE | 2008-06-15 | 2009-03-11 | 2015-06-15 | 2016-03-10
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-194 | Merriman Dam Spillway | 2 | PRELIMINARY DESIGN | 2009-03-12 | 2010-03-06 | 2016-03-11 | 2017-03-05
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-194 | Merriman Dam Spillway | 3 | FINAL DESIGN | 2010-03-07 | 2011-08-28 | 2017-03-06 | 2018-08-27
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-194 | Merriman Dam Spillway | 4 | BID AWARD AND REGISTER CONTRCT | 2011-08-29 | 2012-05-24 | 2018-08-28 | 2019-05-24
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-194 | Merriman Dam Spillway | 5 | CONSTRUCTION TO 25% | 2012-05-25 | 2013-05-19 | 2019-05-25 | 2020-05-18
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-194 | Merriman Dam Spillway | 6 | CONSTRUCTION TO 50% | 2013-05-20 | 2014-05-14 | 2020-05-19 | 2021-05-13
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-194 | Merriman Dam Spillway | 7 | CONSTRUCTION TO 75% | 2014-05-15 | 2015-05-09 | 2021-05-14 | 2022-05-08
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-194 | Merriman Dam Spillway | 8 | ORIGINAL EQUIP & FURNISHING | 2015-05-10 | 2016-02-03 | 2022-05-09 | 2023-02-02
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-194 | Merriman Dam Spillway | 9 | SUBSTANTIAL COMPLETION | 2016-02-04 | 2016-08-01 | 2023-02-03 | 2023-08-01
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-194 | Merriman Dam Spillway | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-08-02 | 2016-10-30 | 2023-08-02 | 2023-10-30
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-231 | CANNONSVILLE EMERGENCY GATE TOWER | 1 | DEVELOP SCOPE | 2011-03-01 | 2011-05-29 | 2018-07-01 | 2018-09-28
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-231 | CANNONSVILLE EMERGENCY GATE TOWER | 2 | PRELIMINARY DESIGN | 2011-05-30 | 2011-09-26 | 2018-09-29 | 2019-01-26
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-231 | CANNONSVILLE EMERGENCY GATE TOWER | 3 | FINAL DESIGN | 2011-09-27 | 2012-03-24 | 2019-01-27 | 2019-07-25
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-231 | CANNONSVILLE EMERGENCY GATE TOWER | 4 | BID AWARD AND REGISTER CONTRCT | 2012-03-25 | 2012-06-22 | 2019-07-26 | 2019-10-23
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-231 | CANNONSVILLE EMERGENCY GATE TOWER | 5 | CONSTRUCTION TO 25% | 2012-06-23 | 2012-10-20 | 2019-10-24 | 2020-02-20
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-231 | CANNONSVILLE EMERGENCY GATE TOWER | 6 | CONSTRUCTION TO 50% | 2012-10-21 | 2013-02-17 | 2020-02-21 | 2020-06-19
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-231 | CANNONSVILLE EMERGENCY GATE TOWER | 7 | CONSTRUCTION TO 75% | 2013-02-18 | 2013-06-17 | 2020-06-20 | 2020-10-17
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-231 | CANNONSVILLE EMERGENCY GATE TOWER | 8 | ORIGINAL EQUIP & FURNISHING | 2013-06-18 | 2013-09-15 | 2020-10-18 | 2021-01-15
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-231 | CANNONSVILLE EMERGENCY GATE TOWER | 9 | SUBSTANTIAL COMPLETION | 2013-09-16 | 2013-11-14 | 2021-01-16 | 2021-03-16
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-231 | CANNONSVILLE EMERGENCY GATE TOWER | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-11-15 | 2013-12-14 | 2021-03-17 | 2021-04-15
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-260 | DEL Shaft 18 Kensico Electrical Upgrade | 3 | FINAL DESIGN | 2009-08-30 | 2010-02-25 | 2010-10-24 | 2012-04-15
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-260 | DEL Shaft 18 Kensico Electrical Upgrade | 4 | BID AWARD AND REGISTER CONTRCT | 2010-02-26 | 2010-05-26 | 2012-04-16 | 2013-01-10
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-260 | DEL Shaft 18 Kensico Electrical Upgrade | 5 | CONSTRUCTION TO 25% | 2010-05-27 | 2010-09-23 | 2013-01-11 | 2014-01-05
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-260 | DEL Shaft 18 Kensico Electrical Upgrade | 6 | CONSTRUCTION TO 50% | 2010-09-24 | 2011-01-21 | 2014-01-06 | 2014-12-31
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-260 | DEL Shaft 18 Kensico Electrical Upgrade | 7 | CONSTRUCTION TO 75% | 2011-01-22 | 2011-05-21 | 2015-01-01 | 2015-12-26
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-260 | DEL Shaft 18 Kensico Electrical Upgrade | 8 | ORIGINAL EQUIP & FURNISHING | 2011-05-22 | 2011-08-19 | 2015-12-27 | 2016-09-21
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-260 | DEL Shaft 18 Kensico Electrical Upgrade | 9 | SUBSTANTIAL COMPLETION | 2011-08-20 | 2011-10-18 | 2016-09-22 | 2021-03-19
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-260 | DEL Shaft 18 Kensico Electrical Upgrade | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2011-10-19 | 2011-11-17 | 2021-03-20 | 2021-06-17
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-359V | Shaft 4 Gate Valve Replacements | 1 | DEVELOP SCOPE | 2020-06-01 | 2021-02-25 | 2020-06-01 | 2021-02-25
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-359V | Shaft 4 Gate Valve Replacements | 2 | PRELIMINARY DESIGN | 2021-02-26 | 2022-02-20 | 2021-02-26 | 2022-02-20
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-359V | Shaft 4 Gate Valve Replacements | 3 | FINAL DESIGN | 2022-02-21 | 2023-08-14 | 2022-02-21 | 2023-08-14
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-359V | Shaft 4 Gate Valve Replacements | 4 | BID AWARD AND REGISTER CONTRCT | 2023-08-15 | 2024-05-10 | 2023-08-15 | 2024-05-10
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-359V | Shaft 4 Gate Valve Replacements | 5 | CONSTRUCTION TO 25% | 2024-05-11 | 2025-05-05 | 2024-05-11 | 2025-05-05
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-359V | Shaft 4 Gate Valve Replacements | 6 | CONSTRUCTION TO 50% | 2025-05-06 | 2026-04-30 | 2025-05-06 | 2026-04-30
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-359V | Shaft 4 Gate Valve Replacements | 7 | CONSTRUCTION TO 75% | 2026-05-01 | 2027-04-25 | 2026-05-01 | 2027-04-25
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-359V | Shaft 4 Gate Valve Replacements | 8 | ORIGINAL EQUIP & FURNISHING | 2027-04-26 | 2028-01-20 | 2027-04-26 | 2028-01-20
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-359V | Shaft 4 Gate Valve Replacements | 9 | SUBSTANTIAL COMPLETION | 2028-01-21 | 2028-07-18 | 2028-01-21 | 2028-07-18
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-359V | Shaft 4 Gate Valve Replacements | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2028-07-19 | 2028-10-16 | 2028-07-19 | 2028-10-16
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-395 | DELAWARE CHAMBERS HVAC IMPROVEMENT | 1 | DEVELOP SCOPE | 2016-06-01 | 2017-02-25 | 2019-06-30 | 2019-09-27
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-395 | DELAWARE CHAMBERS HVAC IMPROVEMENT | 2 | PRELIMINARY DESIGN | 2017-02-26 | 2018-02-20 | 2019-09-28 | 2020-01-25
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-395 | DELAWARE CHAMBERS HVAC IMPROVEMENT | 3 | FINAL DESIGN | 2018-02-21 | 2019-08-14 | 2020-01-26 | 2020-07-23
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-395 | DELAWARE CHAMBERS HVAC IMPROVEMENT | 4 | BID AWARD AND REGISTER CONTRCT | 2019-08-15 | 2020-05-10 | 2020-07-24 | 2020-10-21
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-395 | DELAWARE CHAMBERS HVAC IMPROVEMENT | 5 | CONSTRUCTION TO 25% | 2020-05-11 | 2021-05-05 | 2020-10-22 | 2021-02-18
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-395 | DELAWARE CHAMBERS HVAC IMPROVEMENT | 6 | CONSTRUCTION TO 50% | 2021-05-06 | 2022-04-30 | 2021-02-19 | 2021-06-18
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-395 | DELAWARE CHAMBERS HVAC IMPROVEMENT | 7 | CONSTRUCTION TO 75% | 2022-05-01 | 2023-04-25 | 2021-06-19 | 2021-10-16
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-395 | DELAWARE CHAMBERS HVAC IMPROVEMENT | 8 | DEVELOP SCOPE | 2024-10-17 | 2025-01-14 | 2021-10-17 | 2022-01-14
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-395 | DELAWARE CHAMBERS HVAC IMPROVEMENT | 9 | PRELIMINARY DESIGN | 2025-01-15 | 2025-05-14 | 2022-01-15 | 2022-03-15
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-395 | DELAWARE CHAMBERS HVAC IMPROVEMENT | 10 | FINAL DESIGN | 2025-05-15 | 2025-11-10 | 2022-03-16 | 2022-04-14
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-395 | DELAWARE CHAMBERS HVAC IMPROVEMENT | 11 | BID AWARD AND REGISTER CONTRCT | 2025-11-11 | 2026-02-08 | 2022-03-16 | 2022-04-14
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-395 | DELAWARE CHAMBERS HVAC IMPROVEMENT | 12 | CONSTRUCTION TO 25% | 2026-02-09 | 2026-06-08 | 2022-03-16 | 2022-04-14
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-395 | DELAWARE CHAMBERS HVAC IMPROVEMENT | 13 | CONSTRUCTION TO 50% | 2026-06-09 | 2026-10-06 | 2022-03-16 | 2022-04-14
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-395 | DELAWARE CHAMBERS HVAC IMPROVEMENT | 14 | CONSTRUCTION TO 75% | 2026-10-07 | 2027-02-03 | 2022-03-16 | 2022-04-14
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-395 | DELAWARE CHAMBERS HVAC IMPROVEMENT | 15 | ORIGINAL EQUIP & FURNISHING | 2027-02-04 | 2027-05-04 | 2022-03-16 | 2022-04-14
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-395 | DELAWARE CHAMBERS HVAC IMPROVEMENT | 16 | SUBSTANTIAL COMPLETION | 2027-05-05 | 2027-07-03 | 2022-03-16 | 2022-04-14
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-395 | DELAWARE CHAMBERS HVAC IMPROVEMENT | 17 | PUNCHLIST COMPLETE, JOB CLOSED | 2027-07-04 | 2027-08-02 | 2022-03-16 | 2022-04-14
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-397 | Riser Valve Control Mechanism at DA Chambers | 1 | DEVELOP SCOPE | 2020-06-01 | 2021-02-25 | 2020-06-01 | 2021-02-25
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-397 | Riser Valve Control Mechanism at DA Chambers | 2 | PRELIMINARY DESIGN | 2021-02-26 | 2022-02-20 | 2021-02-26 | 2022-02-20
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-397 | Riser Valve Control Mechanism at DA Chambers | 3 | FINAL DESIGN | 2022-02-21 | 2023-08-14 | 2022-02-21 | 2023-08-14
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-397 | Riser Valve Control Mechanism at DA Chambers | 4 | BID AWARD AND REGISTER CONTRCT | 2023-08-15 | 2024-05-10 | 2023-08-15 | 2024-05-10
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-397 | Riser Valve Control Mechanism at DA Chambers | 5 | CONSTRUCTION TO 25% | 2024-05-11 | 2025-05-05 | 2024-05-11 | 2025-05-05
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-397 | Riser Valve Control Mechanism at DA Chambers | 6 | CONSTRUCTION TO 50% | 2025-05-06 | 2026-04-30 | 2025-05-06 | 2026-04-30
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-397 | Riser Valve Control Mechanism at DA Chambers | 7 | CONSTRUCTION TO 75% | 2026-05-01 | 2027-04-25 | 2026-05-01 | 2027-04-25
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-397 | Riser Valve Control Mechanism at DA Chambers | 8 | ORIGINAL EQUIP & FURNISHING | 2027-04-26 | 2028-01-20 | 2027-04-26 | 2028-01-20
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-397 | Riser Valve Control Mechanism at DA Chambers | 9 | SUBSTANTIAL COMPLETION | 2028-01-21 | 2028-07-18 | 2028-01-21 | 2028-07-18
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-397 | Riser Valve Control Mechanism at DA Chambers | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2028-07-19 | 2028-10-16 | 2028-07-19 | 2028-10-16
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-400 | Town fo Wawarsing Public Water Project | 1 | DEVELOP SCOPE | 2013-06-01 | 2014-02-25 | 2013-06-01 | 2014-02-25
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-400 | Town fo Wawarsing Public Water Project | 2 | PRELIMINARY DESIGN | 2014-02-26 | 2015-02-20 | 2014-02-26 | 2015-02-20
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-400 | Town fo Wawarsing Public Water Project | 3 | FINAL DESIGN | 2015-02-21 | 2016-08-13 | 2015-02-21 | 2016-08-13
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-400 | Town fo Wawarsing Public Water Project | 4 | BID AWARD AND REGISTER CONTRCT | 2016-08-14 | 2017-05-10 | 2016-08-14 | 2017-05-10
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-400 | Town fo Wawarsing Public Water Project | 5 | CONSTRUCTION TO 25% | 2017-05-11 | 2018-05-05 | 2017-05-11 | 2018-05-05
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-400 | Town fo Wawarsing Public Water Project | 6 | CONSTRUCTION TO 50% | 2018-05-06 | 2019-04-30 | 2018-05-06 | 2019-04-30
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-400 | Town fo Wawarsing Public Water Project | 7 | CONSTRUCTION TO 75% | 2019-05-01 | 2020-04-24 | 2019-05-01 | 2020-04-24
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-400 | Town fo Wawarsing Public Water Project | 8 | ORIGINAL EQUIP & FURNISHING | 2020-04-25 | 2021-01-19 | 2020-04-25 | 2021-01-19
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-400 | Town fo Wawarsing Public Water Project | 9 | SUBSTANTIAL COMPLETION | 2021-01-20 | 2029-07-16 | 2021-01-20 | 2029-07-16
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-400 | Town fo Wawarsing Public Water Project | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2029-07-17 | 2029-10-14 | 2029-07-17 | 2029-10-14
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-415 | EAST DELAWARE RELEASE CHAMBER VALVE REPLACEMENTS | 1 | DEVELOP SCOPE | 2019-04-01 | 2019-06-29 | 2019-04-01 | 2019-06-29
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-415 | EAST DELAWARE RELEASE CHAMBER VALVE REPLACEMENTS | 2 | PRELIMINARY DESIGN | 2019-06-30 | 2019-10-27 | 2019-06-30 | 2019-10-27
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-415 | EAST DELAWARE RELEASE CHAMBER VALVE REPLACEMENTS | 3 | FINAL DESIGN | 2019-10-28 | 2020-04-24 | 2019-10-28 | 2020-04-24
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-415 | EAST DELAWARE RELEASE CHAMBER VALVE REPLACEMENTS | 4 | BID AWARD AND REGISTER CONTRCT | 2020-04-25 | 2020-07-23 | 2020-04-25 | 2020-07-23
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-415 | EAST DELAWARE RELEASE CHAMBER VALVE REPLACEMENTS | 5 | CONSTRUCTION TO 25% | 2020-07-24 | 2020-11-20 | 2020-07-24 | 2020-11-20
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-415 | EAST DELAWARE RELEASE CHAMBER VALVE REPLACEMENTS | 6 | CONSTRUCTION TO 50% | 2020-11-21 | 2021-03-20 | 2020-11-21 | 2021-03-20
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-415 | EAST DELAWARE RELEASE CHAMBER VALVE REPLACEMENTS | 7 | CONSTRUCTION TO 75% | 2021-03-21 | 2021-07-18 | 2021-03-21 | 2021-07-18
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-415 | EAST DELAWARE RELEASE CHAMBER VALVE REPLACEMENTS | 8 | ORIGINAL EQUIP & FURNISHING | 2021-07-19 | 2021-10-16 | 2021-07-19 | 2021-10-16
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-415 | EAST DELAWARE RELEASE CHAMBER VALVE REPLACEMENTS | 9 | SUBSTANTIAL COMPLETION | 2021-10-17 | 2021-12-15 | 2021-10-17 | 2021-12-15
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-415 | EAST DELAWARE RELEASE CHAMBER VALVE REPLACEMENTS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-12-16 | 2022-01-14 | 2021-12-16 | 2022-01-14
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-424 | Replacement/Rehabilitation of Honk Falls Dam | 1 | PRE-CONSTRUCTION MOBILIZATION | 2016-07-01 | 2017-06-25 | 2016-07-01 | 2017-06-25
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-424 | Replacement/Rehabilitation of Honk Falls Dam | 2 | ON-SITE CONSTRUCTION MANAGEMEN | 2017-06-26 | 2023-05-25 | 2017-06-26 | 2023-05-25
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-424 | Replacement/Rehabilitation of Honk Falls Dam | 3 | POST-CONSTRUCTION CLOSE-OUT | 2023-05-26 | 2024-05-19 | 2023-05-26 | 2024-05-19
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-428 | EDTO VALVE | 1 | DEVELOP SCOPE | 2018-06-30 | 2019-03-26 | 2018-06-30 | 2019-03-26
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-428 | EDTO VALVE | 2 | PRELIMINARY DESIGN | 2019-03-27 | 2020-03-20 | 2019-03-27 | 2020-03-20
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-428 | EDTO VALVE | 3 | FINAL DESIGN | 2020-03-21 | 2021-09-11 | 2020-03-21 | 2021-09-11
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-428 | EDTO VALVE | 4 | BID AWARD AND REGISTER CONTRCT | 2021-09-12 | 2022-06-08 | 2021-09-12 | 2022-06-08
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-428 | EDTO VALVE | 5 | CONSTRUCTION TO 25% | 2022-06-09 | 2023-06-03 | 2022-06-09 | 2023-06-03
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-428 | EDTO VALVE | 6 | CONSTRUCTION TO 50% | 2023-06-04 | 2024-05-28 | 2023-06-04 | 2024-05-28
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-428 | EDTO VALVE | 7 | CONSTRUCTION TO 75% | 2024-05-29 | 2025-05-23 | 2024-05-29 | 2025-05-23
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-428 | EDTO VALVE | 8 | ORIGINAL EQUIP & FURNISHING | 2025-05-24 | 2026-02-17 | 2025-05-24 | 2026-02-17
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-428 | EDTO VALVE | 9 | SUBSTANTIAL COMPLETION | 2026-02-18 | 2026-08-16 | 2026-02-18 | 2026-08-16
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-428 | EDTO VALVE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2026-08-17 | 2026-11-14 | 2026-08-17 | 2026-11-14
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-434 | DAM STABILITY IMPROVEMENTS | 1 | DEVELOP SCOPE | 2018-06-30 | 2019-03-26 | 2018-06-30 | 2019-03-26
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-434 | DAM STABILITY IMPROVEMENTS | 2 | PRELIMINARY DESIGN | 2019-03-27 | 2020-03-20 | 2019-03-27 | 2020-03-20
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-434 | DAM STABILITY IMPROVEMENTS | 3 | FINAL DESIGN | 2020-03-21 | 2021-09-11 | 2020-03-21 | 2021-09-11
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-434 | DAM STABILITY IMPROVEMENTS | 4 | BID AWARD AND REGISTER CONTRCT | 2021-09-12 | 2022-06-08 | 2021-09-12 | 2022-06-08
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-434 | DAM STABILITY IMPROVEMENTS | 5 | CONSTRUCTION TO 25% | 2022-06-09 | 2023-06-03 | 2022-06-09 | 2023-06-03
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-434 | DAM STABILITY IMPROVEMENTS | 6 | CONSTRUCTION TO 50% | 2023-06-04 | 2024-05-28 | 2023-06-04 | 2024-05-28
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-434 | DAM STABILITY IMPROVEMENTS | 7 | CONSTRUCTION TO 75% | 2024-05-29 | 2025-05-23 | 2024-05-29 | 2025-05-23
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-434 | DAM STABILITY IMPROVEMENTS | 8 | ORIGINAL EQUIP & FURNISHING | 2025-05-24 | 2026-02-17 | 2025-05-24 | 2026-02-17
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-434 | DAM STABILITY IMPROVEMENTS | 9 | SUBSTANTIAL COMPLETION | 2026-02-18 | 2026-08-16 | 2026-02-18 | 2026-08-16
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-434 | DAM STABILITY IMPROVEMENTS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2026-08-17 | 2026-11-14 | 2026-08-17 | 2026-11-14
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-439 | Sludge Drying Greenhouse Recon. at Margaretville WWTP | 1 | DEVELOP SCOPE | 2019-06-01 | 2019-08-29 | 2019-06-01 | 2019-08-29
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-439 | Sludge Drying Greenhouse Recon. at Margaretville WWTP | 2 | PRELIMINARY DESIGN | 2019-08-30 | 2019-12-27 | 2019-08-30 | 2019-12-27
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-439 | Sludge Drying Greenhouse Recon. at Margaretville WWTP | 3 | FINAL DESIGN | 2019-12-28 | 2020-06-24 | 2019-12-28 | 2020-06-24
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-439 | Sludge Drying Greenhouse Recon. at Margaretville WWTP | 4 | BID AWARD AND REGISTER CONTRCT | 2020-06-25 | 2020-09-22 | 2020-06-25 | 2020-09-22
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-439 | Sludge Drying Greenhouse Recon. at Margaretville WWTP | 5 | CONSTRUCTION TO 25% | 2020-09-23 | 2021-01-20 | 2020-09-23 | 2021-01-20
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-439 | Sludge Drying Greenhouse Recon. at Margaretville WWTP | 6 | CONSTRUCTION TO 50% | 2021-01-21 | 2021-05-20 | 2021-01-21 | 2021-05-20
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-439 | Sludge Drying Greenhouse Recon. at Margaretville WWTP | 7 | CONSTRUCTION TO 75% | 2021-05-21 | 2021-09-17 | 2021-05-21 | 2021-09-17
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-439 | Sludge Drying Greenhouse Recon. at Margaretville WWTP | 8 | ORIGINAL EQUIP & FURNISHING | 2021-09-18 | 2021-12-16 | 2021-09-18 | 2021-12-16
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-439 | Sludge Drying Greenhouse Recon. at Margaretville WWTP | 9 | SUBSTANTIAL COMPLETION | 2021-12-17 | 2022-02-14 | 2021-12-17 | 2022-02-14
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-439 | Sludge Drying Greenhouse Recon. at Margaretville WWTP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-02-15 | 2022-03-16 | 2022-02-15 | 2022-03-16
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-450 | Downsville Water Connection | 1 | DEVELOP SCOPE | 2021-06-01 | 2022-02-25 | 2021-06-01 | 2022-02-25
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-450 | Downsville Water Connection | 2 | PRELIMINARY DESIGN | 2022-02-26 | 2023-02-20 | 2022-02-26 | 2023-02-20
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-450 | Downsville Water Connection | 3 | FINAL DESIGN | 2023-02-21 | 2024-08-13 | 2023-02-21 | 2024-08-13
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-450 | Downsville Water Connection | 4 | BID AWARD AND REGISTER CONTRCT | 2024-08-14 | 2025-05-10 | 2024-08-14 | 2025-05-10
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-450 | Downsville Water Connection | 5 | CONSTRUCTION TO 25% | 2025-05-11 | 2026-05-05 | 2025-05-11 | 2026-05-05
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-450 | Downsville Water Connection | 6 | CONSTRUCTION TO 50% | 2026-05-06 | 2027-04-30 | 2026-05-06 | 2027-04-30
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-450 | Downsville Water Connection | 7 | CONSTRUCTION TO 75% | 2027-05-01 | 2028-04-24 | 2027-05-01 | 2028-04-24
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-450 | Downsville Water Connection | 8 | ORIGINAL EQUIP & FURNISHING | 2028-04-25 | 2029-01-19 | 2028-04-25 | 2029-01-19
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-450 | Downsville Water Connection | 9 | SUBSTANTIAL COMPLETION | 2029-01-20 | 2029-07-18 | 2029-01-20 | 2029-07-18
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-450 | Downsville Water Connection | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2029-07-19 | 2029-10-16 | 2029-07-19 | 2029-10-16
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-SHFT4 | Dependability- Connection from Del Aqueduct to Cat Aqueduct | 1 | DEVELOP SCOPE | 2011-01-01 | 2011-03-31 | 2011-01-01 | 2011-09-27
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-SHFT4 | Dependability- Connection from Del Aqueduct to Cat Aqueduct | 2 | PRELIMINARY DESIGN | 2011-04-01 | 2011-07-29 | 2011-09-28 | 2012-09-21
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-SHFT4 | Dependability- Connection from Del Aqueduct to Cat Aqueduct | 3 | FINAL DESIGN | 2011-07-30 | 2012-01-25 | 2012-09-22 | 2014-03-15
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-SHFT4 | Dependability- Connection from Del Aqueduct to Cat Aqueduct | 4 | BID AWARD AND REGISTER CONTRCT | 2012-01-26 | 2012-04-24 | 2014-03-16 | 2014-12-10
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-SHFT4 | Dependability- Connection from Del Aqueduct to Cat Aqueduct | 5 | CONSTRUCTION TO 25% | 2012-04-25 | 2012-08-22 | 2014-12-11 | 2015-12-05
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-SHFT4 | Dependability- Connection from Del Aqueduct to Cat Aqueduct | 6 | CONSTRUCTION TO 50% | 2012-08-23 | 2012-12-20 | 2015-12-06 | 2016-11-29
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-SHFT4 | Dependability- Connection from Del Aqueduct to Cat Aqueduct | 7 | CONSTRUCTION TO 75% | 2012-12-21 | 2013-04-19 | 2016-11-30 | 2017-11-24
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-SHFT4 | Dependability- Connection from Del Aqueduct to Cat Aqueduct | 8 | ORIGINAL EQUIP & FURNISHING | 2013-04-20 | 2013-07-18 | 2017-11-25 | 2018-08-21
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-SHFT4 | Dependability- Connection from Del Aqueduct to Cat Aqueduct | 9 | SUBSTANTIAL COMPLETION | 2013-07-19 | 2013-09-16 | 2018-08-22 | 2027-02-15
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-SHFT4 | Dependability- Connection from Del Aqueduct to Cat Aqueduct | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-09-17 | 2013-10-16 | 2027-02-16 | 2027-05-16
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEP-DRA | DELAWARE-RONDOUT AQUEDUCT (PARALLEL TUNNEL TO RWBT) | 1 | DEVELOP SCOPE | 2008-09-01 | 2009-05-28 | 2008-09-01 | 2009-05-28
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEP-DRA | DELAWARE-RONDOUT AQUEDUCT (PARALLEL TUNNEL TO RWBT) | 2 | PRELIMINARY DESIGN | 2009-05-29 | 2010-05-23 | 2009-05-29 | 2010-05-23
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEP-DRA | DELAWARE-RONDOUT AQUEDUCT (PARALLEL TUNNEL TO RWBT) | 3 | FINAL DESIGN | 2010-05-24 | 2011-11-14 | 2010-05-24 | 2011-11-14
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEP-DRA | DELAWARE-RONDOUT AQUEDUCT (PARALLEL TUNNEL TO RWBT) | 4 | BID AWARD AND REGISTER CONTRCT | 2011-11-15 | 2012-08-10 | 2011-11-15 | 2012-08-10
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEP-DRA | DELAWARE-RONDOUT AQUEDUCT (PARALLEL TUNNEL TO RWBT) | 5 | CONSTRUCTION TO 25% | 2012-08-11 | 2013-08-05 | 2012-08-11 | 2013-08-05
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEP-DRA | DELAWARE-RONDOUT AQUEDUCT (PARALLEL TUNNEL TO RWBT) | 6 | CONSTRUCTION TO 50% | 2013-08-06 | 2014-07-31 | 2013-08-06 | 2014-07-31
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEP-DRA | DELAWARE-RONDOUT AQUEDUCT (PARALLEL TUNNEL TO RWBT) | 7 | CONSTRUCTION TO 75% | 2014-08-01 | 2015-07-26 | 2014-08-01 | 2015-07-26
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEP-DRA | DELAWARE-RONDOUT AQUEDUCT (PARALLEL TUNNEL TO RWBT) | 8 | ORIGINAL EQUIP & FURNISHING | 2015-07-27 | 2016-04-21 | 2015-07-27 | 2016-04-21
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEP-DRA | DELAWARE-RONDOUT AQUEDUCT (PARALLEL TUNNEL TO RWBT) | 9 | SUBSTANTIAL COMPLETION | 2016-04-22 | 2024-10-16 | 2016-04-22 | 2024-10-16
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEP-DRA | DELAWARE-RONDOUT AQUEDUCT (PARALLEL TUNNEL TO RWBT) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-10-17 | 2025-01-14 | 2024-10-17 | 2025-01-14
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DOERETRO | WATER EFFICIENCY UPGRADES AT DOE SCHOOLS | 1 | DEVELOP SCOPE | 2021-06-15 | 2021-10-12 | 2021-06-15 | 2021-10-12
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DOERETRO | WATER EFFICIENCY UPGRADES AT DOE SCHOOLS | 2 | PRELIMINARY DESIGN | 2021-10-13 | 2022-04-10 | 2021-10-13 | 2022-04-10
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DOERETRO | WATER EFFICIENCY UPGRADES AT DOE SCHOOLS | 3 | FINAL DESIGN | 2022-04-11 | 2023-10-12 | 2022-04-11 | 2023-10-12
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DOERETRO | WATER EFFICIENCY UPGRADES AT DOE SCHOOLS | 4 | BID AWARD AND REGISTER CONTRCT | 2023-10-13 | 2024-04-09 | 2023-10-13 | 2024-04-09
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DOERETRO | WATER EFFICIENCY UPGRADES AT DOE SCHOOLS | 5 | CONSTRUCTION TO 25% | 2024-04-10 | 2025-01-14 | 2024-04-10 | 2025-01-14
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DOERETRO | WATER EFFICIENCY UPGRADES AT DOE SCHOOLS | 6 | CONSTRUCTION TO 50% | 2025-01-15 | 2025-10-21 | 2025-01-15 | 2025-10-21
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DOERETRO | WATER EFFICIENCY UPGRADES AT DOE SCHOOLS | 7 | CONSTRUCTION TO 75% | 2025-10-22 | 2026-07-28 | 2025-10-22 | 2026-07-28
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DOERETRO | WATER EFFICIENCY UPGRADES AT DOE SCHOOLS | 8 | ORIGINAL EQUIP & FURNISHING | 2026-07-29 | 2026-10-26 | 2026-07-29 | 2026-10-26
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DOERETRO | WATER EFFICIENCY UPGRADES AT DOE SCHOOLS | 9 | SUBSTANTIAL COMPLETION | 2026-10-27 | 2026-12-25 | 2026-10-27 | 2026-12-25
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DOERETRO | WATER EFFICIENCY UPGRADES AT DOE SCHOOLS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2026-12-26 | 2027-03-25 | 2026-12-26 | 2027-03-25
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DSMNH | Deep Sewer Manholes | 1 | DEVELOP SCOPE | 2019-06-01 | 2019-08-29 | 2021-06-01 | 2021-08-29
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DSMNH | Deep Sewer Manholes | 2 | PRELIMINARY DESIGN | 2019-08-30 | 2019-12-27 | 2021-08-30 | 2021-12-27
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DSMNH | Deep Sewer Manholes | 3 | FINAL DESIGN | 2019-12-28 | 2020-06-24 | 2021-12-28 | 2022-06-25
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DSMNH | Deep Sewer Manholes | 4 | BID AWARD AND REGISTER CONTRCT | 2020-06-25 | 2020-09-22 | 2022-06-26 | 2022-09-23
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DSMNH | Deep Sewer Manholes | 5 | CONSTRUCTION TO 25% | 2020-09-23 | 2021-01-20 | 2022-09-24 | 2023-01-21
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DSMNH | Deep Sewer Manholes | 6 | CONSTRUCTION TO 50% | 2021-01-21 | 2021-05-20 | 2023-01-22 | 2023-05-21
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DSMNH | Deep Sewer Manholes | 7 | CONSTRUCTION TO 75% | 2021-05-21 | 2021-09-17 | 2023-05-22 | 2023-09-18
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DSMNH | Deep Sewer Manholes | 8 | ORIGINAL EQUIP & FURNISHING | 2021-09-18 | 2021-12-16 | 2023-09-19 | 2023-12-17
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DSMNH | Deep Sewer Manholes | 9 | SUBSTANTIAL COMPLETION | 2021-12-17 | 2022-02-14 | 2023-12-18 | 2024-02-15
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DSMNH | Deep Sewer Manholes | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-02-15 | 2022-03-16 | 2024-02-16 | 2024-03-16
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-GUN22 | Emergency Guniting of Sewers, Citywide | 1 | DEVELOP SCOPE | 2020-11-09 | 2021-02-06 | 2020-11-09 | 2021-02-06
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-GUN22 | Emergency Guniting of Sewers, Citywide | 2 | PRELIMINARY DESIGN | 2021-02-07 | 2021-06-06 | 2021-02-07 | 2021-06-06
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-GUN22 | Emergency Guniting of Sewers, Citywide | 3 | FINAL DESIGN | 2021-06-07 | 2021-12-03 | 2021-06-07 | 2021-12-03
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-GUN22 | Emergency Guniting of Sewers, Citywide | 4 | BID AWARD AND REGISTER CONTRCT | 2021-12-04 | 2022-03-03 | 2021-12-04 | 2022-03-03
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-GUN22 | Emergency Guniting of Sewers, Citywide | 5 | CONSTRUCTION TO 25% | 2022-03-04 | 2022-07-01 | 2022-03-04 | 2022-07-01
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-GUN22 | Emergency Guniting of Sewers, Citywide | 6 | CONSTRUCTION TO 50% | 2022-07-02 | 2022-10-29 | 2022-07-02 | 2022-10-29
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-GUN22 | Emergency Guniting of Sewers, Citywide | 7 | CONSTRUCTION TO 75% | 2022-10-30 | 2023-02-26 | 2022-10-30 | 2023-02-26
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-GUN22 | Emergency Guniting of Sewers, Citywide | 8 | ORIGINAL EQUIP & FURNISHING | 2023-02-27 | 2023-05-27 | 2023-02-27 | 2023-05-27
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-GUN22 | Emergency Guniting of Sewers, Citywide | 9 | SUBSTANTIAL COMPLETION | 2023-05-28 | 2023-07-26 | 2023-05-28 | 2023-07-26
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-GUN22 | Emergency Guniting of Sewers, Citywide | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-07-27 | 2023-08-25 | 2023-07-27 | 2023-08-25
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-LC22A | Emergency Sewer Lining | 1 | DEVELOP SCOPE | 2020-11-09 | 2021-02-06 | 2020-11-09 | 2021-02-06
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-LC22A | Emergency Sewer Lining | 2 | PRELIMINARY DESIGN | 2021-02-07 | 2021-06-06 | 2021-02-07 | 2021-06-06
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-LC22A | Emergency Sewer Lining | 3 | FINAL DESIGN | 2021-06-07 | 2021-12-03 | 2021-06-07 | 2021-12-03
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-LC22A | Emergency Sewer Lining | 4 | BID AWARD AND REGISTER CONTRCT | 2021-12-04 | 2022-03-03 | 2021-12-04 | 2022-03-03
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-LC22A | Emergency Sewer Lining | 5 | CONSTRUCTION TO 25% | 2022-03-04 | 2022-07-01 | 2022-03-04 | 2022-07-01
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-LC22A | Emergency Sewer Lining | 6 | CONSTRUCTION TO 50% | 2022-07-02 | 2022-10-29 | 2022-07-02 | 2022-10-29
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-LC22A | Emergency Sewer Lining | 7 | CONSTRUCTION TO 75% | 2022-10-30 | 2023-02-26 | 2022-10-30 | 2023-02-26
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-LC22A | Emergency Sewer Lining | 8 | ORIGINAL EQUIP & FURNISHING | 2023-02-27 | 2023-05-27 | 2023-02-27 | 2023-05-27
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-LC22A | Emergency Sewer Lining | 9 | SUBSTANTIAL COMPLETION | 2023-05-28 | 2023-07-26 | 2023-05-28 | 2023-07-26
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-LC22A | Emergency Sewer Lining | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-07-27 | 2023-08-25 | 2023-07-27 | 2023-08-25
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-WMC22 | Emergency Reconstruction of Water Mains, Citywide | 1 | DEVELOP SCOPE | 2020-11-09 | 2021-08-05 | 2020-11-09 | 2021-08-05
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-WMC22 | Emergency Reconstruction of Water Mains, Citywide | 2 | PRELIMINARY DESIGN | 2021-08-06 | 2022-07-31 | 2021-08-06 | 2022-07-31
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-WMC22 | Emergency Reconstruction of Water Mains, Citywide | 3 | FINAL DESIGN | 2022-08-01 | 2024-01-22 | 2022-08-01 | 2024-01-22
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-WMC22 | Emergency Reconstruction of Water Mains, Citywide | 4 | BID AWARD AND REGISTER CONTRCT | 2024-01-23 | 2024-10-18 | 2024-01-23 | 2024-10-18
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-WMC22 | Emergency Reconstruction of Water Mains, Citywide | 5 | CONSTRUCTION TO 25% | 2024-10-19 | 2025-10-13 | 2024-10-19 | 2025-10-13
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-WMC22 | Emergency Reconstruction of Water Mains, Citywide | 6 | CONSTRUCTION TO 50% | 2025-10-14 | 2026-10-08 | 2025-10-14 | 2026-10-08
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-WMC22 | Emergency Reconstruction of Water Mains, Citywide | 7 | CONSTRUCTION TO 75% | 2026-10-09 | 2027-10-03 | 2026-10-09 | 2027-10-03
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-WMC22 | Emergency Reconstruction of Water Mains, Citywide | 8 | ORIGINAL EQUIP & FURNISHING | 2027-10-04 | 2028-06-29 | 2027-10-04 | 2028-06-29
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-WMC22 | Emergency Reconstruction of Water Mains, Citywide | 9 | SUBSTANTIAL COMPLETION | 2028-06-30 | 2028-12-26 | 2028-06-30 | 2028-12-26
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-WMC22 | Emergency Reconstruction of Water Mains, Citywide | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2028-12-27 | 2029-03-26 | 2028-12-27 | 2029-03-26
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EE-RRC | TRC - RESIDUAL CHLORINE REDUCTION PROGRAM | 1 | DEVELOP SCOPE | 2007-03-01 | 2007-05-29 | 2007-03-01 | 2007-11-25
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EE-RRC | TRC - RESIDUAL CHLORINE REDUCTION PROGRAM | 2 | PRELIMINARY DESIGN | 2007-05-30 | 2007-09-26 | 2007-11-26 | 2008-11-19
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EE-RRC | TRC - RESIDUAL CHLORINE REDUCTION PROGRAM | 3 | FINAL DESIGN | 2007-09-27 | 2008-03-24 | 2008-11-20 | 2010-05-13
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EE-RRC | TRC - RESIDUAL CHLORINE REDUCTION PROGRAM | 4 | BID AWARD AND REGISTER CONTRCT | 2008-03-25 | 2008-06-22 | 2010-05-14 | 2011-02-07
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EE-RRC | TRC - RESIDUAL CHLORINE REDUCTION PROGRAM | 5 | CONSTRUCTION TO 25% | 2008-06-23 | 2008-10-20 | 2011-02-08 | 2012-02-02
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EE-RRC | TRC - RESIDUAL CHLORINE REDUCTION PROGRAM | 6 | CONSTRUCTION TO 50% | 2008-10-21 | 2009-02-17 | 2012-02-03 | 2013-01-27
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EE-RRC | TRC - RESIDUAL CHLORINE REDUCTION PROGRAM | 7 | CONSTRUCTION TO 75% | 2009-02-18 | 2009-06-17 | 2013-01-28 | 2014-01-22
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EE-RRC | TRC - RESIDUAL CHLORINE REDUCTION PROGRAM | 8 | ORIGINAL EQUIP & FURNISHING | 2009-06-18 | 2009-09-15 | 2014-01-23 | 2014-10-19
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EE-RRC | TRC - RESIDUAL CHLORINE REDUCTION PROGRAM | 9 | SUBSTANTIAL COMPLETION | 2009-09-16 | 2009-11-14 | 2014-10-20 | 2027-04-14
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EE-RRC | TRC - RESIDUAL CHLORINE REDUCTION PROGRAM | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2009-11-15 | 2009-12-14 | 2027-04-15 | 2027-07-13
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | FADFLOOD | FAD - FLOOD HAZARD MITIGATION | 1 | DEVELOP SCOPE | 2015-03-01 | 2015-11-25 | 2015-03-01 | 2015-11-25
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | FADFLOOD | FAD - FLOOD HAZARD MITIGATION | 2 | PRELIMINARY DESIGN | 2015-11-26 | 2016-11-19 | 2015-11-26 | 2016-11-19
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | FADFLOOD | FAD - FLOOD HAZARD MITIGATION | 3 | FINAL DESIGN | 2016-11-20 | 2018-05-13 | 2016-11-20 | 2018-05-13
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | FADFLOOD | FAD - FLOOD HAZARD MITIGATION | 4 | BID AWARD AND REGISTER CONTRCT | 2018-05-14 | 2019-02-07 | 2018-05-14 | 2019-02-07
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | FADFLOOD | FAD - FLOOD HAZARD MITIGATION | 5 | CONSTRUCTION TO 25% | 2019-02-08 | 2020-02-02 | 2019-02-08 | 2020-02-02
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | FADFLOOD | FAD - FLOOD HAZARD MITIGATION | 6 | CONSTRUCTION TO 50% | 2020-02-03 | 2021-01-27 | 2020-02-03 | 2021-01-27
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | FADFLOOD | FAD - FLOOD HAZARD MITIGATION | 7 | CONSTRUCTION TO 75% | 2021-01-28 | 2022-01-22 | 2021-01-28 | 2022-01-22
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | FADFLOOD | FAD - FLOOD HAZARD MITIGATION | 8 | ORIGINAL EQUIP & FURNISHING | 2022-01-23 | 2022-10-19 | 2022-01-23 | 2022-10-19
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | FADFLOOD | FAD - FLOOD HAZARD MITIGATION | 9 | SUBSTANTIAL COMPLETION | 2022-10-20 | 2023-04-17 | 2022-10-20 | 2023-04-17
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | FADFLOOD | FAD - FLOOD HAZARD MITIGATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-04-18 | 2023-07-16 | 2023-04-18 | 2023-07-16
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | FMC-LEAD | LEAD PAINT ABATEMENT & REMOVAL | 1 | DEVELOP SCOPE | 2010-10-30 | 2011-02-26 | 2018-10-30 | 2019-02-26
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | FMC-LEAD | LEAD PAINT ABATEMENT & REMOVAL | 2 | PRELIMINARY DESIGN | 2011-02-27 | 2011-08-25 | 2019-02-27 | 2019-08-25
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | FMC-LEAD | LEAD PAINT ABATEMENT & REMOVAL | 3 | FINAL DESIGN | 2011-08-26 | 2013-02-25 | 2019-08-26 | 2021-02-25
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | FMC-LEAD | LEAD PAINT ABATEMENT & REMOVAL | 4 | BID AWARD AND REGISTER CONTRCT | 2013-02-26 | 2013-08-24 | 2021-02-26 | 2021-08-24
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | FMC-LEAD | LEAD PAINT ABATEMENT & REMOVAL | 5 | CONSTRUCTION TO 25% | 2013-08-25 | 2014-05-31 | 2021-08-25 | 2022-05-31
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | FMC-LEAD | LEAD PAINT ABATEMENT & REMOVAL | 6 | CONSTRUCTION TO 50% | 2014-06-01 | 2015-03-07 | 2022-06-01 | 2023-03-07
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | FMC-LEAD | LEAD PAINT ABATEMENT & REMOVAL | 7 | CONSTRUCTION TO 75% | 2015-03-08 | 2015-12-12 | 2023-03-08 | 2023-12-12
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | FMC-LEAD | LEAD PAINT ABATEMENT & REMOVAL | 8 | ORIGINAL EQUIP & FURNISHING | 2015-12-13 | 2016-03-11 | 2024-12-13 | 2025-03-11
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | FMC-LEAD | LEAD PAINT ABATEMENT & REMOVAL | 9 | SUBSTANTIAL COMPLETION | 2016-03-12 | 2016-05-10 | 2025-03-12 | 2025-05-10
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | FMC-LEAD | LEAD PAINT ABATEMENT & REMOVAL | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-05-11 | 2016-08-08 | 2025-05-11 | 2025-08-08
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-CONS-1 | GI - GREEN INFRASTRUCTURE ONSITE CONSTRUCTION CONTRACTS | 1 | DEVELOP SCOPE | 2022-01-01 | 2022-03-31 | 2022-01-01 | 2022-03-31
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-CONS-1 | GI - GREEN INFRASTRUCTURE ONSITE CONSTRUCTION CONTRACTS | 2 | PRELIMINARY DESIGN | 2022-04-01 | 2022-07-29 | 2022-04-01 | 2022-07-29
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-CONS-1 | GI - GREEN INFRASTRUCTURE ONSITE CONSTRUCTION CONTRACTS | 3 | FINAL DESIGN | 2022-07-30 | 2023-01-25 | 2022-07-30 | 2023-01-25
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-CONS-1 | GI - GREEN INFRASTRUCTURE ONSITE CONSTRUCTION CONTRACTS | 4 | BID AWARD AND REGISTER CONTRCT | 2023-01-26 | 2023-04-25 | 2023-01-26 | 2023-04-25
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-CONS-1 | GI - GREEN INFRASTRUCTURE ONSITE CONSTRUCTION CONTRACTS | 5 | CONSTRUCTION TO 25% | 2023-04-26 | 2023-08-23 | 2023-04-26 | 2023-08-23
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-CONS-1 | GI - GREEN INFRASTRUCTURE ONSITE CONSTRUCTION CONTRACTS | 6 | CONSTRUCTION TO 50% | 2023-08-24 | 2023-12-21 | 2023-08-24 | 2023-12-21
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-CONS-1 | GI - GREEN INFRASTRUCTURE ONSITE CONSTRUCTION CONTRACTS | 7 | CONSTRUCTION TO 75% | 2023-12-22 | 2024-04-19 | 2023-12-22 | 2024-04-19
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-CONS-1 | GI - GREEN INFRASTRUCTURE ONSITE CONSTRUCTION CONTRACTS | 8 | ORIGINAL EQUIP & FURNISHING | 2024-04-20 | 2024-07-18 | 2024-04-20 | 2024-07-18
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-CONS-1 | GI - GREEN INFRASTRUCTURE ONSITE CONSTRUCTION CONTRACTS | 9 | SUBSTANTIAL COMPLETION | 2024-07-19 | 2024-09-16 | 2024-07-19 | 2024-09-16
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-CONS-1 | GI - GREEN INFRASTRUCTURE ONSITE CONSTRUCTION CONTRACTS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-09-17 | 2024-10-16 | 2024-09-17 | 2024-10-16
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-CONS-2 | GI - GREEN INFRASTRUCTURE ONSITE CONSTRUCTION CONTRACTS | 1 | DEVELOP SCOPE | 2022-07-01 | 2022-09-28 | 2022-07-01 | 2022-09-28
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-CONS-2 | GI - GREEN INFRASTRUCTURE ONSITE CONSTRUCTION CONTRACTS | 2 | PRELIMINARY DESIGN | 2022-09-29 | 2023-01-26 | 2022-09-29 | 2023-01-26
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-CONS-2 | GI - GREEN INFRASTRUCTURE ONSITE CONSTRUCTION CONTRACTS | 3 | FINAL DESIGN | 2023-01-27 | 2023-07-25 | 2023-01-27 | 2023-07-25
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-CONS-2 | GI - GREEN INFRASTRUCTURE ONSITE CONSTRUCTION CONTRACTS | 4 | BID AWARD AND REGISTER CONTRCT | 2023-07-26 | 2023-10-23 | 2023-07-26 | 2023-10-23
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-CONS-2 | GI - GREEN INFRASTRUCTURE ONSITE CONSTRUCTION CONTRACTS | 5 | CONSTRUCTION TO 25% | 2023-10-24 | 2024-02-20 | 2023-10-24 | 2024-02-20
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-CONS-2 | GI - GREEN INFRASTRUCTURE ONSITE CONSTRUCTION CONTRACTS | 6 | CONSTRUCTION TO 50% | 2024-02-21 | 2024-06-19 | 2024-02-21 | 2024-06-19
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-CONS-2 | GI - GREEN INFRASTRUCTURE ONSITE CONSTRUCTION CONTRACTS | 7 | CONSTRUCTION TO 75% | 2024-06-20 | 2024-10-17 | 2024-06-20 | 2024-10-17
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-CONS-2 | GI - GREEN INFRASTRUCTURE ONSITE CONSTRUCTION CONTRACTS | 8 | ORIGINAL EQUIP & FURNISHING | 2024-10-18 | 2025-01-15 | 2024-10-18 | 2025-01-15
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-CONS-2 | GI - GREEN INFRASTRUCTURE ONSITE CONSTRUCTION CONTRACTS | 9 | SUBSTANTIAL COMPLETION | 2025-01-16 | 2025-03-16 | 2025-01-16 | 2025-03-16
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-CONS-2 | GI - GREEN INFRASTRUCTURE ONSITE CONSTRUCTION CONTRACTS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-03-17 | 2025-04-15 | 2025-03-17 | 2025-04-15
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-DDC | GI - DDC PROJECTS-GREEN INFRASTRUCTURE AND PUBLIC BUILDINGS | 1 | DEVELOP SCOPE | 2011-08-01 | 2011-10-29 | 2012-04-01 | 2012-12-26
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-DDC | GI - DDC PROJECTS-GREEN INFRASTRUCTURE AND PUBLIC BUILDINGS | 2 | PRELIMINARY DESIGN | 2011-10-30 | 2012-02-26 | 2012-12-27 | 2013-12-21
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-DDC | GI - DDC PROJECTS-GREEN INFRASTRUCTURE AND PUBLIC BUILDINGS | 3 | FINAL DESIGN | 2012-02-27 | 2012-08-24 | 2013-12-22 | 2015-06-14
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-DDC | GI - DDC PROJECTS-GREEN INFRASTRUCTURE AND PUBLIC BUILDINGS | 4 | BID AWARD AND REGISTER CONTRCT | 2012-08-25 | 2012-11-22 | 2015-06-15 | 2016-03-10
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-DDC | GI - DDC PROJECTS-GREEN INFRASTRUCTURE AND PUBLIC BUILDINGS | 5 | CONSTRUCTION TO 25% | 2012-11-23 | 2013-03-22 | 2016-03-11 | 2017-03-05
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-DDC | GI - DDC PROJECTS-GREEN INFRASTRUCTURE AND PUBLIC BUILDINGS | 6 | CONSTRUCTION TO 50% | 2013-03-23 | 2013-07-20 | 2017-03-06 | 2018-02-28
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-DDC | GI - DDC PROJECTS-GREEN INFRASTRUCTURE AND PUBLIC BUILDINGS | 7 | CONSTRUCTION TO 75% | 2013-07-21 | 2013-11-17 | 2018-03-01 | 2019-02-23
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-DDC | GI - DDC PROJECTS-GREEN INFRASTRUCTURE AND PUBLIC BUILDINGS | 8 | ORIGINAL EQUIP & FURNISHING | 2013-11-18 | 2014-02-15 | 2019-02-24 | 2019-11-20
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-DDC | GI - DDC PROJECTS-GREEN INFRASTRUCTURE AND PUBLIC BUILDINGS | 9 | SUBSTANTIAL COMPLETION | 2014-02-16 | 2014-04-16 | 2019-11-21 | 2024-05-17
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-DDC | GI - DDC PROJECTS-GREEN INFRASTRUCTURE AND PUBLIC BUILDINGS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-04-17 | 2014-05-16 | 2024-05-18 | 2024-08-15
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-GRANT | GI - GREEN INFRASTRUCTURE GRANT PROGRAM | 1 | DEVELOP SCOPE | 2011-10-01 | 2011-12-29 | 2011-01-30 | 2011-10-26
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-GRANT | GI - GREEN INFRASTRUCTURE GRANT PROGRAM | 2 | PRELIMINARY DESIGN | 2011-12-30 | 2012-04-27 | 2011-10-27 | 2012-10-20
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-GRANT | GI - GREEN INFRASTRUCTURE GRANT PROGRAM | 3 | FINAL DESIGN | 2012-04-28 | 2012-10-24 | 2012-10-21 | 2014-04-13
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-GRANT | GI - GREEN INFRASTRUCTURE GRANT PROGRAM | 4 | BID AWARD AND REGISTER CONTRCT | 2012-10-25 | 2013-01-22 | 2014-04-14 | 2015-01-08
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-GRANT | GI - GREEN INFRASTRUCTURE GRANT PROGRAM | 5 | CONSTRUCTION TO 25% | 2013-01-23 | 2013-05-22 | 2015-01-09 | 2016-01-03
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-GRANT | GI - GREEN INFRASTRUCTURE GRANT PROGRAM | 6 | CONSTRUCTION TO 50% | 2013-05-23 | 2013-09-19 | 2016-01-04 | 2016-12-28
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-GRANT | GI - GREEN INFRASTRUCTURE GRANT PROGRAM | 7 | CONSTRUCTION TO 75% | 2013-09-20 | 2014-01-17 | 2016-12-29 | 2017-12-23
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-GRANT | GI - GREEN INFRASTRUCTURE GRANT PROGRAM | 8 | ORIGINAL EQUIP & FURNISHING | 2014-01-18 | 2014-04-17 | 2017-12-24 | 2018-09-19
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-GRANT | GI - GREEN INFRASTRUCTURE GRANT PROGRAM | 9 | SUBSTANTIAL COMPLETION | 2014-04-18 | 2014-06-16 | 2018-09-20 | 2023-03-17
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-GRANT | GI - GREEN INFRASTRUCTURE GRANT PROGRAM | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-06-17 | 2014-07-16 | 2023-03-18 | 2023-06-15
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-HPD | GI - FUNDING FOR HPD GREEN INFRASTRUCTURE PROJECTS | 1 | DEVELOP SCOPE | 2011-11-01 | 2012-01-29 | 2022-11-01 | 2023-01-29
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-HPD | GI - FUNDING FOR HPD GREEN INFRASTRUCTURE PROJECTS | 2 | PRELIMINARY DESIGN | 2012-01-30 | 2012-05-28 | 2023-01-30 | 2023-05-29
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-HPD | GI - FUNDING FOR HPD GREEN INFRASTRUCTURE PROJECTS | 3 | FINAL DESIGN | 2012-05-29 | 2012-11-24 | 2023-05-30 | 2023-11-25
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-HPD | GI - FUNDING FOR HPD GREEN INFRASTRUCTURE PROJECTS | 4 | BID AWARD AND REGISTER CONTRCT | 2012-11-25 | 2013-02-22 | 2023-11-26 | 2024-02-23
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-HPD | GI - FUNDING FOR HPD GREEN INFRASTRUCTURE PROJECTS | 5 | CONSTRUCTION TO 25% | 2013-02-23 | 2013-06-22 | 2024-02-24 | 2024-06-22
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-HPD | GI - FUNDING FOR HPD GREEN INFRASTRUCTURE PROJECTS | 6 | CONSTRUCTION TO 50% | 2013-06-23 | 2013-10-20 | 2024-06-23 | 2024-10-20
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-HPD | GI - FUNDING FOR HPD GREEN INFRASTRUCTURE PROJECTS | 7 | CONSTRUCTION TO 75% | 2013-10-21 | 2014-02-17 | 2024-10-21 | 2025-02-17
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-HPD | GI - FUNDING FOR HPD GREEN INFRASTRUCTURE PROJECTS | 8 | ORIGINAL EQUIP & FURNISHING | 2014-02-18 | 2014-05-18 | 2025-02-18 | 2025-05-18
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-HPD | GI - FUNDING FOR HPD GREEN INFRASTRUCTURE PROJECTS | 9 | SUBSTANTIAL COMPLETION | 2014-05-19 | 2014-07-17 | 2025-05-19 | 2025-07-17
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-HPD | GI - FUNDING FOR HPD GREEN INFRASTRUCTURE PROJECTS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-07-18 | 2014-08-16 | 2025-07-18 | 2025-08-16
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | HVR-500 | Hillview Police Precinct | 1 | DEVELOP SCOPE | 2021-06-01 | 2022-02-25 | 2021-06-01 | 2022-02-25
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | HVR-500 | Hillview Police Precinct | 2 | PRELIMINARY DESIGN | 2022-02-26 | 2023-02-20 | 2022-02-26 | 2023-02-20
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | HVR-500 | Hillview Police Precinct | 3 | FINAL DESIGN | 2023-02-21 | 2024-08-13 | 2023-02-21 | 2024-08-13
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | HVR-500 | Hillview Police Precinct | 4 | BID AWARD AND REGISTER CONTRCT | 2024-08-14 | 2025-05-10 | 2024-08-14 | 2025-05-10
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | HVR-500 | Hillview Police Precinct | 5 | CONSTRUCTION TO 25% | 2025-05-11 | 2026-05-05 | 2025-05-11 | 2026-05-05
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | HVR-500 | Hillview Police Precinct | 6 | CONSTRUCTION TO 50% | 2026-05-06 | 2027-04-30 | 2026-05-06 | 2027-04-30
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | HVR-500 | Hillview Police Precinct | 7 | CONSTRUCTION TO 75% | 2027-05-01 | 2028-04-24 | 2027-05-01 | 2028-04-24
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | HVR-500 | Hillview Police Precinct | 8 | ORIGINAL EQUIP & FURNISHING | 2028-04-25 | 2029-01-19 | 2028-04-25 | 2029-01-19
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | HVR-500 | Hillview Police Precinct | 9 | SUBSTANTIAL COMPLETION | 2029-01-20 | 2029-07-18 | 2029-01-20 | 2029-07-18
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | HVR-500 | Hillview Police Precinct | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2029-07-19 | 2029-10-16 | 2029-07-19 | 2029-10-16
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JFK-12 | WATER METER INSTALLATION AT JFK AIRPORT | 1 | PRE-CONSTRUCTION MOBILIZATION | 2016-07-01 | 2017-06-25 | 2016-07-01 | 2017-06-25
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JFK-12 | WATER METER INSTALLATION AT JFK AIRPORT | 2 | ON-SITE CONSTRUCTION MANAGEMEN | 2017-06-26 | 2023-05-25 | 2017-06-26 | 2023-05-25
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JFK-12 | WATER METER INSTALLATION AT JFK AIRPORT | 3 | POST-CONSTRUCTION CLOSE-OUT | 2023-05-26 | 2024-05-19 | 2023-05-26 | 2024-05-19
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-12-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH, & EAST | 1 | DEVELOP SCOPE | 2011-06-01 | 2012-02-25 | 2011-06-01 | 2012-02-25
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-12-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH, & EAST | 2 | PRELIMINARY DESIGN | 2012-02-26 | 2013-02-19 | 2012-02-26 | 2013-02-19
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-12-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH, & EAST | 3 | FINAL DESIGN | 2013-02-20 | 2014-08-13 | 2013-02-20 | 2014-08-13
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-12-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH, & EAST | 4 | BID AWARD AND REGISTER CONTRCT | 2014-08-14 | 2015-05-10 | 2014-08-14 | 2015-05-10
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-12-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH, & EAST | 5 | CONSTRUCTION TO 25% | 2015-05-11 | 2016-05-04 | 2015-05-11 | 2016-05-04
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-12-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH, & EAST | 6 | CONSTRUCTION TO 50% | 2016-05-05 | 2017-04-29 | 2016-05-05 | 2017-04-29
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-12-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH, & EAST | 7 | CONSTRUCTION TO 75% | 2017-04-30 | 2018-04-24 | 2017-04-30 | 2018-04-24
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-12-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH, & EAST | 8 | ORIGINAL EQUIP & FURNISHING | 2018-04-25 | 2019-01-19 | 2018-04-25 | 2019-01-19
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-12-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH, & EAST | 9 | SUBSTANTIAL COMPLETION | 2019-01-20 | 2019-07-18 | 2019-01-20 | 2023-07-17
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-12-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH, & EAST | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-07-19 | 2019-10-16 | 2023-07-18 | 2023-10-15
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-15BWS | Facilities Improvement Program | 1 | DEVELOP SCOPE | 2015-01-01 | 2015-03-31 | 2005-01-18 | 2005-10-14
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-15BWS | Facilities Improvement Program | 2 | PRELIMINARY DESIGN | 2015-04-01 | 2015-07-29 | 2005-10-15 | 2006-10-09
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-15BWS | Facilities Improvement Program | 3 | FINAL DESIGN | 2015-07-30 | 2016-01-25 | 2006-10-10 | 2008-04-01
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-15BWS | Facilities Improvement Program | 4 | BID AWARD AND REGISTER CONTRCT | 2016-01-26 | 2016-04-24 | 2008-04-02 | 2008-12-27
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-15BWS | Facilities Improvement Program | 5 | CONSTRUCTION TO 25% | 2016-04-25 | 2016-08-22 | 2008-12-28 | 2009-12-22
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-15BWS | Facilities Improvement Program | 6 | CONSTRUCTION TO 50% | 2016-08-23 | 2016-12-20 | 2009-12-23 | 2010-12-17
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-15BWS | Facilities Improvement Program | 7 | CONSTRUCTION TO 75% | 2016-12-21 | 2017-04-19 | 2010-12-18 | 2011-12-12
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-15BWS | Facilities Improvement Program | 8 | ORIGINAL EQUIP & FURNISHING | 2017-04-20 | 2017-07-18 | 2011-12-13 | 2012-09-07
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-15BWS | Facilities Improvement Program | 9 | SUBSTANTIAL COMPLETION | 2017-07-19 | 2017-09-16 | 2012-09-08 | 2025-03-03
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-15BWS | Facilities Improvement Program | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-09-17 | 2017-10-16 | 2025-03-04 | 2025-06-01
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-17-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 1 | FINAL DESIGN | 2017-06-01 | 2018-11-22 | 2017-06-01 | 2018-11-22
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-17-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 2 | CONSTRUCTION TO 25% | 2018-11-23 | 2019-07-20 | 2018-11-23 | 2019-07-20
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-17-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 3 | CONSTRUCTION TO 50% | 2019-07-21 | 2020-03-16 | 2019-07-21 | 2020-03-16
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-17-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 4 | CONSTRUCTION TO 75% | 2020-03-17 | 2020-11-11 | 2020-03-17 | 2020-11-11
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-18-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 1 | FINAL DESIGN | 2018-06-01 | 2019-11-22 | 2018-06-01 | 2019-11-22
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-18-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 2 | CONSTRUCTION TO 25% | 2019-11-23 | 2020-07-19 | 2019-11-23 | 2020-07-19
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-18-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 3 | CONSTRUCTION TO 50% | 2020-07-20 | 2021-03-16 | 2020-07-20 | 2021-03-16
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-18-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 4 | CONSTRUCTION TO 75% | 2021-03-17 | 2021-11-11 | 2021-03-17 | 2021-11-11
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-20-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 1 | FINAL DESIGN | 2020-06-01 | 2021-11-22 | 2021-06-01 | 2022-02-25
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-20-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 2 | CONSTRUCTION TO 25% | 2021-11-23 | 2022-07-20 | 2022-02-26 | 2023-02-20
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-20-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 3 | CONSTRUCTION TO 50% | 2022-07-21 | 2023-03-17 | 2023-02-21 | 2024-08-13
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-20-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 4 | CONSTRUCTION TO 75% | 2023-03-18 | 2023-11-12 | 2024-08-14 | 2025-05-10
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-20-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 5 | CONSTRUCTION TO 25% | 2023-03-18 | 2023-11-12 | 2025-05-11 | 2026-05-05
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-20-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 6 | CONSTRUCTION TO 50% | 2023-03-18 | 2023-11-12 | 2026-05-06 | 2027-04-30
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-20-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 7 | CONSTRUCTION TO 75% | 2023-03-18 | 2023-11-12 | 2027-05-01 | 2028-04-24
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-20-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 8 | ORIGINAL EQUIP & FURNISHING | 2023-03-18 | 2023-11-12 | 2028-04-25 | 2029-01-19
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-20-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 9 | SUBSTANTIAL COMPLETION | 2023-03-18 | 2023-11-12 | 2029-01-20 | 2029-07-18
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-20-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-03-18 | 2023-11-12 | 2029-07-19 | 2029-10-16
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-21-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 1 | FINAL DESIGN | 2021-06-01 | 2022-11-22 | 2021-06-01 | 2022-11-22
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-21-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 2 | CONSTRUCTION TO 25% | 2022-11-23 | 2023-07-20 | 2022-11-23 | 2023-07-20
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-21-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 3 | CONSTRUCTION TO 50% | 2023-07-21 | 2024-03-16 | 2023-07-21 | 2024-03-16
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-21-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 4 | CONSTRUCTION TO 75% | 2024-03-17 | 2024-11-11 | 2024-03-17 | 2024-11-11
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-22-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 1 | FINAL DESIGN | 2022-06-01 | 2023-11-22 | 2022-06-01 | 2023-11-22
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-22-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 2 | CONSTRUCTION TO 25% | 2023-11-23 | 2024-07-19 | 2023-11-23 | 2024-07-19
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-22-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 3 | CONSTRUCTION TO 50% | 2024-07-20 | 2025-03-16 | 2024-07-20 | 2025-03-16
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-22-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 4 | CONSTRUCTION TO 75% | 2025-03-17 | 2025-11-11 | 2025-03-17 | 2025-11-11
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-26-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 1 | FINAL DESIGN | 2026-06-01 | 2027-11-22 | 2026-06-01 | 2027-11-22
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-26-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 2 | CONSTRUCTION TO 25% | 2027-11-23 | 2028-07-19 | 2027-11-23 | 2028-07-19
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-26-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 3 | CONSTRUCTION TO 50% | 2028-07-20 | 2029-03-16 | 2028-07-20 | 2029-03-16
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-26-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 4 | CONSTRUCTION TO 75% | 2029-03-17 | 2029-11-11 | 2029-03-17 | 2029-11-11
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-27-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 1 | FINAL DESIGN | 2027-06-01 | 2028-11-21 | 2027-06-01 | 2028-11-21
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-27-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 2 | CONSTRUCTION TO 25% | 2028-11-22 | 2029-07-19 | 2028-11-22 | 2029-07-19
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-27-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 3 | CONSTRUCTION TO 50% | 2029-07-20 | 2030-03-16 | 2029-07-20 | 2030-03-16
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-27-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 4 | CONSTRUCTION TO 75% | 2030-03-17 | 2030-11-11 | 2030-03-17 | 2030-11-11
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-28-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 1 | FINAL DESIGN | 2027-07-01 | 2028-12-21 | 2027-07-01 | 2028-12-21
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-28-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 2 | CONSTRUCTION TO 25% | 2028-12-22 | 2029-08-18 | 2028-12-22 | 2029-08-18
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-28-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 3 | CONSTRUCTION TO 50% | 2029-08-19 | 2030-04-15 | 2029-08-19 | 2030-04-15
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-28-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 4 | CONSTRUCTION TO 75% | 2030-04-16 | 2030-12-11 | 2030-04-16 | 2030-12-11
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-29-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 1 | FINAL DESIGN | 2028-07-01 | 2029-12-22 | 2028-05-01 | 2029-10-22
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-29-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 2 | CONSTRUCTION TO 25% | 2029-12-23 | 2030-08-19 | 2029-10-23 | 2030-06-19
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-29-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 3 | CONSTRUCTION TO 50% | 2030-08-20 | 2031-04-16 | 2030-06-20 | 2031-02-14
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-29-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 4 | CONSTRUCTION TO 75% | 2031-04-17 | 2031-12-12 | 2031-02-15 | 2031-10-12
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-BWS | BWS JOC Contracts (E-O-H & W-O-H) | 1 | DEVELOP SCOPE | 2012-03-01 | 2012-11-25 | 2012-03-01 | 2012-11-25
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-BWS | BWS JOC Contracts (E-O-H & W-O-H) | 2 | PRELIMINARY DESIGN | 2012-11-26 | 2013-11-20 | 2012-11-26 | 2013-11-20
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-BWS | BWS JOC Contracts (E-O-H & W-O-H) | 3 | FINAL DESIGN | 2013-11-21 | 2015-05-14 | 2013-11-21 | 2015-05-14
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-BWS | BWS JOC Contracts (E-O-H & W-O-H) | 4 | BID AWARD AND REGISTER CONTRCT | 2015-05-15 | 2016-02-08 | 2015-05-15 | 2016-02-08
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-BWS | BWS JOC Contracts (E-O-H & W-O-H) | 5 | CONSTRUCTION TO 25% | 2016-02-09 | 2017-02-02 | 2016-02-09 | 2017-02-02
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-BWS | BWS JOC Contracts (E-O-H & W-O-H) | 6 | CONSTRUCTION TO 50% | 2017-02-03 | 2018-01-28 | 2017-02-03 | 2018-01-28
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-BWS | BWS JOC Contracts (E-O-H & W-O-H) | 7 | CONSTRUCTION TO 75% | 2018-01-29 | 2019-01-23 | 2018-01-29 | 2019-01-23
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-BWS | BWS JOC Contracts (E-O-H & W-O-H) | 8 | ORIGINAL EQUIP & FURNISHING | 2019-01-24 | 2019-10-20 | 2019-01-24 | 2019-10-20
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-BWS | BWS JOC Contracts (E-O-H & W-O-H) | 9 | SUBSTANTIAL COMPLETION | 2019-10-21 | 2020-04-17 | 2019-10-21 | 2025-04-17
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-BWS | BWS JOC Contracts (E-O-H & W-O-H) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-04-18 | 2020-07-16 | 2025-04-18 | 2025-07-16
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-BWSO | BWSO Facilities Improvement Program | 1 | DEVELOP SCOPE | 2019-06-01 | 2020-02-25 | 2019-06-01 | 2020-02-25
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-BWSO | BWSO Facilities Improvement Program | 2 | PRELIMINARY DESIGN | 2020-02-26 | 2021-02-19 | 2020-02-26 | 2021-02-19
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-BWSO | BWSO Facilities Improvement Program | 3 | FINAL DESIGN | 2021-02-20 | 2022-08-13 | 2021-02-20 | 2022-08-13
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-BWSO | BWSO Facilities Improvement Program | 4 | BID AWARD AND REGISTER CONTRCT | 2022-08-14 | 2023-05-10 | 2022-08-14 | 2023-05-10
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-BWSO | BWSO Facilities Improvement Program | 5 | CONSTRUCTION TO 25% | 2023-05-11 | 2024-05-04 | 2023-05-11 | 2024-05-04
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-BWSO | BWSO Facilities Improvement Program | 6 | CONSTRUCTION TO 50% | 2024-05-05 | 2025-04-29 | 2024-05-05 | 2025-04-29
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-BWSO | BWSO Facilities Improvement Program | 7 | CONSTRUCTION TO 75% | 2025-04-30 | 2026-04-24 | 2025-04-30 | 2026-04-24
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-BWSO | BWSO Facilities Improvement Program | 8 | ORIGINAL EQUIP & FURNISHING | 2026-04-25 | 2027-01-19 | 2026-04-25 | 2027-01-19
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-BWSO | BWSO Facilities Improvement Program | 9 | SUBSTANTIAL COMPLETION | 2027-01-20 | 2027-07-18 | 2027-01-20 | 2027-07-18
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-BWSO | BWSO Facilities Improvement Program | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2027-07-19 | 2027-10-16 | 2027-07-19 | 2027-10-16
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC3 | FMC Facilities Improvement Program | 1 | DEVELOP SCOPE | 2017-10-02 | 2018-01-29 | 2017-10-02 | 2018-01-29
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC3 | FMC Facilities Improvement Program | 2 | PRELIMINARY DESIGN | 2018-01-30 | 2018-07-28 | 2018-01-30 | 2018-07-28
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC3 | FMC Facilities Improvement Program | 3 | FINAL DESIGN | 2018-07-29 | 2020-01-29 | 2018-07-29 | 2020-01-29
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC3 | FMC Facilities Improvement Program | 4 | BID AWARD AND REGISTER CONTRCT | 2020-01-30 | 2020-07-27 | 2020-01-30 | 2020-07-27
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC3 | FMC Facilities Improvement Program | 5 | CONSTRUCTION TO 25% | 2020-07-28 | 2021-05-03 | 2020-07-28 | 2021-05-03
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC3 | FMC Facilities Improvement Program | 6 | CONSTRUCTION TO 50% | 2021-05-04 | 2022-02-07 | 2021-05-04 | 2022-02-07
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC3 | FMC Facilities Improvement Program | 7 | CONSTRUCTION TO 75% | 2022-02-08 | 2022-11-14 | 2022-02-08 | 2022-11-14
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC3 | FMC Facilities Improvement Program | 8 | ORIGINAL EQUIP & FURNISHING | 2022-11-15 | 2023-02-12 | 2022-11-15 | 2023-02-12
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC3 | FMC Facilities Improvement Program | 9 | SUBSTANTIAL COMPLETION | 2023-02-13 | 2023-04-13 | 2023-02-13 | 2023-04-13
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC3 | FMC Facilities Improvement Program | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-04-14 | 2023-07-12 | 2023-04-14 | 2023-07-12
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC4 | Job Order Contract 2 - CIitywide | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-10-28 | 2018-08-23 | 2018-12-20
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC4 | Job Order Contract 2 - CIitywide | 2 | PRELIMINARY DESIGN | 2016-10-29 | 2017-04-26 | 2018-12-21 | 2019-06-18
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC4 | Job Order Contract 2 - CIitywide | 3 | FINAL DESIGN | 2017-04-27 | 2018-10-28 | 2019-06-19 | 2020-12-19
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC4 | Job Order Contract 2 - CIitywide | 4 | BID AWARD AND REGISTER CONTRCT | 2018-10-29 | 2019-04-26 | 2020-12-20 | 2021-06-17
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC4 | Job Order Contract 2 - CIitywide | 5 | CONSTRUCTION TO 25% | 2019-04-27 | 2020-01-31 | 2021-06-18 | 2022-03-24
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC4 | Job Order Contract 2 - CIitywide | 6 | CONSTRUCTION TO 50% | 2020-02-01 | 2020-11-06 | 2022-03-25 | 2022-12-29
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC4 | Job Order Contract 2 - CIitywide | 7 | CONSTRUCTION TO 75% | 2020-11-07 | 2021-08-13 | 2022-12-30 | 2023-10-05
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC4 | Job Order Contract 2 - CIitywide | 8 | ORIGINAL EQUIP & FURNISHING | 2021-08-14 | 2021-11-11 | 2023-10-06 | 2024-01-03
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC4 | Job Order Contract 2 - CIitywide | 9 | SUBSTANTIAL COMPLETION | 2021-11-12 | 2022-01-10 | 2024-01-04 | 2024-03-03
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC4 | Job Order Contract 2 - CIitywide | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-01-11 | 2022-04-10 | 2024-03-04 | 2024-06-01
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC6 | FMC Facilities Improvement Program | 1 | DEVELOP SCOPE | 2021-01-01 | 2021-04-30 | 2021-01-01 | 2021-04-30
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC6 | FMC Facilities Improvement Program | 2 | PRELIMINARY DESIGN | 2021-05-01 | 2021-10-27 | 2021-05-01 | 2021-10-27
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC6 | FMC Facilities Improvement Program | 3 | FINAL DESIGN | 2021-10-28 | 2023-04-30 | 2021-10-28 | 2023-04-30
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC6 | FMC Facilities Improvement Program | 4 | BID AWARD AND REGISTER CONTRCT | 2023-05-01 | 2023-10-27 | 2023-05-01 | 2023-10-27
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC6 | FMC Facilities Improvement Program | 5 | CONSTRUCTION TO 25% | 2023-10-28 | 2024-08-02 | 2023-10-28 | 2024-08-02
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC6 | FMC Facilities Improvement Program | 6 | CONSTRUCTION TO 50% | 2024-08-03 | 2025-05-09 | 2024-08-03 | 2025-05-09
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC6 | FMC Facilities Improvement Program | 7 | CONSTRUCTION TO 75% | 2025-05-10 | 2026-02-13 | 2025-05-10 | 2026-02-13
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC6 | FMC Facilities Improvement Program | 8 | ORIGINAL EQUIP & FURNISHING | 2026-02-14 | 2026-05-14 | 2026-02-14 | 2026-05-14
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC6 | FMC Facilities Improvement Program | 9 | SUBSTANTIAL COMPLETION | 2026-05-15 | 2026-07-13 | 2026-05-15 | 2026-07-13
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC6 | FMC Facilities Improvement Program | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2026-07-14 | 2026-10-11 | 2026-07-14 | 2026-10-11
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC7 | Job Order Contract 2 - Citywide | 1 | DEVELOP SCOPE | 2021-01-01 | 2021-04-30 | 2021-01-01 | 2021-04-30
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC7 | Job Order Contract 2 - Citywide | 2 | PRELIMINARY DESIGN | 2021-05-01 | 2021-10-27 | 2021-05-01 | 2021-10-27
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC7 | Job Order Contract 2 - Citywide | 3 | FINAL DESIGN | 2021-10-28 | 2023-04-30 | 2021-10-28 | 2023-04-30
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC7 | Job Order Contract 2 - Citywide | 4 | BID AWARD AND REGISTER CONTRCT | 2023-05-01 | 2023-10-27 | 2023-05-01 | 2023-10-27
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC7 | Job Order Contract 2 - Citywide | 5 | CONSTRUCTION TO 25% | 2023-10-28 | 2024-08-02 | 2023-10-28 | 2024-08-02
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC7 | Job Order Contract 2 - Citywide | 6 | CONSTRUCTION TO 50% | 2024-08-03 | 2025-05-09 | 2024-08-03 | 2025-05-09
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC7 | Job Order Contract 2 - Citywide | 7 | CONSTRUCTION TO 75% | 2025-05-10 | 2026-02-13 | 2025-05-10 | 2026-02-13
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC7 | Job Order Contract 2 - Citywide | 8 | ORIGINAL EQUIP & FURNISHING | 2026-02-14 | 2026-05-14 | 2026-02-14 | 2026-05-14
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC7 | Job Order Contract 2 - Citywide | 9 | SUBSTANTIAL COMPLETION | 2026-05-15 | 2026-07-13 | 2026-05-15 | 2026-07-13
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC7 | Job Order Contract 2 - Citywide | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2026-07-14 | 2026-10-11 | 2026-07-14 | 2026-10-11
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC8 | FMC Facilities Improvement Program | 1 | DEVELOP SCOPE | 2023-01-01 | 2023-04-30 | 2023-01-01 | 2023-04-30
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC8 | FMC Facilities Improvement Program | 2 | PRELIMINARY DESIGN | 2023-05-01 | 2023-10-27 | 2023-05-01 | 2023-10-27
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC8 | FMC Facilities Improvement Program | 3 | FINAL DESIGN | 2023-10-28 | 2025-04-29 | 2023-10-28 | 2025-04-29
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC8 | FMC Facilities Improvement Program | 4 | BID AWARD AND REGISTER CONTRCT | 2025-04-30 | 2025-10-26 | 2025-04-30 | 2025-10-26
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC8 | FMC Facilities Improvement Program | 5 | CONSTRUCTION TO 25% | 2025-10-27 | 2026-08-02 | 2025-10-27 | 2026-08-02
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC8 | FMC Facilities Improvement Program | 6 | CONSTRUCTION TO 50% | 2026-08-03 | 2027-05-09 | 2026-08-03 | 2027-05-09
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC8 | FMC Facilities Improvement Program | 7 | CONSTRUCTION TO 75% | 2027-05-10 | 2028-02-13 | 2027-05-10 | 2028-02-13
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC8 | FMC Facilities Improvement Program | 8 | ORIGINAL EQUIP & FURNISHING | 2028-02-14 | 2028-05-13 | 2028-02-14 | 2028-05-13
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC8 | FMC Facilities Improvement Program | 9 | SUBSTANTIAL COMPLETION | 2028-05-14 | 2028-07-12 | 2028-05-14 | 2028-07-12
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC8 | FMC Facilities Improvement Program | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2028-07-13 | 2028-10-10 | 2028-07-13 | 2028-10-10
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC9 | Job Order Contract 2 - Citywide | 1 | DEVELOP SCOPE | 2023-01-01 | 2023-04-30 | 2023-01-01 | 2023-04-30
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC9 | Job Order Contract 2 - Citywide | 2 | PRELIMINARY DESIGN | 2023-05-01 | 2023-10-27 | 2023-05-01 | 2023-10-27
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC9 | Job Order Contract 2 - Citywide | 3 | FINAL DESIGN | 2023-10-28 | 2025-04-29 | 2023-10-28 | 2025-04-29
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC9 | Job Order Contract 2 - Citywide | 4 | BID AWARD AND REGISTER CONTRCT | 2025-04-30 | 2025-10-26 | 2025-04-30 | 2025-10-26
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC9 | Job Order Contract 2 - Citywide | 5 | CONSTRUCTION TO 25% | 2025-10-27 | 2026-08-02 | 2025-10-27 | 2026-08-02
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC9 | Job Order Contract 2 - Citywide | 6 | CONSTRUCTION TO 50% | 2026-08-03 | 2027-05-09 | 2026-08-03 | 2027-05-09
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC9 | Job Order Contract 2 - Citywide | 7 | CONSTRUCTION TO 75% | 2027-05-10 | 2028-02-13 | 2027-05-10 | 2028-02-13
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC9 | Job Order Contract 2 - Citywide | 8 | ORIGINAL EQUIP & FURNISHING | 2028-02-14 | 2028-05-13 | 2028-02-14 | 2028-05-13
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC9 | Job Order Contract 2 - Citywide | 9 | SUBSTANTIAL COMPLETION | 2028-05-14 | 2028-07-12 | 2028-05-14 | 2028-07-12
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC9 | Job Order Contract 2 - Citywide | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2028-07-13 | 2028-10-10 | 2028-07-13 | 2028-10-10
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JPSCOMPEH | JEROME PS ELECTRIC & HYDRAULIC SVC REPLAMNT | 1 | DEVELOP SCOPE | 2018-06-01 | 2018-08-29 | 2018-06-30 | 2019-03-26
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JPSCOMPEH | JEROME PS ELECTRIC & HYDRAULIC SVC REPLAMNT | 2 | PRELIMINARY DESIGN | 2018-08-30 | 2018-12-27 | 2019-03-27 | 2020-03-20
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JPSCOMPEH | JEROME PS ELECTRIC & HYDRAULIC SVC REPLAMNT | 3 | FINAL DESIGN | 2018-12-28 | 2019-06-25 | 2020-03-21 | 2021-09-11
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JPSCOMPEH | JEROME PS ELECTRIC & HYDRAULIC SVC REPLAMNT | 4 | BID AWARD AND REGISTER CONTRCT | 2019-06-26 | 2019-09-23 | 2021-09-12 | 2022-06-08
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JPSCOMPEH | JEROME PS ELECTRIC & HYDRAULIC SVC REPLAMNT | 5 | CONSTRUCTION TO 25% | 2019-09-24 | 2020-01-21 | 2022-06-09 | 2023-06-03
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JPSCOMPEH | JEROME PS ELECTRIC & HYDRAULIC SVC REPLAMNT | 6 | CONSTRUCTION TO 50% | 2020-01-22 | 2020-05-20 | 2023-06-04 | 2024-05-28
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JPSCOMPEH | JEROME PS ELECTRIC & HYDRAULIC SVC REPLAMNT | 7 | CONSTRUCTION TO 75% | 2020-05-21 | 2020-09-17 | 2024-05-29 | 2025-05-23
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JPSCOMPEH | JEROME PS ELECTRIC & HYDRAULIC SVC REPLAMNT | 8 | ORIGINAL EQUIP & FURNISHING | 2020-09-18 | 2020-12-16 | 2025-05-24 | 2026-02-17
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JPSCOMPEH | JEROME PS ELECTRIC & HYDRAULIC SVC REPLAMNT | 9 | SUBSTANTIAL COMPLETION | 2020-12-17 | 2021-02-14 | 2026-02-18 | 2026-08-16
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JPSCOMPEH | JEROME PS ELECTRIC & HYDRAULIC SVC REPLAMNT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-02-15 | 2021-03-16 | 2026-08-17 | 2026-11-14
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | KENS-EAST | KENSICO-EASTVIEW CONNECTION TUNNEL | 1 | DEVELOP SCOPE | 2016-07-01 | 2017-03-27 | 2016-07-01 | 2017-03-27
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | KENS-EAST | KENSICO-EASTVIEW CONNECTION TUNNEL | 2 | PRELIMINARY DESIGN | 2017-03-28 | 2018-03-22 | 2017-03-28 | 2018-03-22
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | KENS-EAST | KENSICO-EASTVIEW CONNECTION TUNNEL | 3 | FINAL DESIGN | 2018-03-23 | 2019-09-13 | 2018-03-23 | 2019-09-13
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | KENS-EAST | KENSICO-EASTVIEW CONNECTION TUNNEL | 4 | BID AWARD AND REGISTER CONTRCT | 2019-09-14 | 2020-06-09 | 2019-09-14 | 2020-06-09
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | KENS-EAST | KENSICO-EASTVIEW CONNECTION TUNNEL | 5 | CONSTRUCTION TO 25% | 2020-06-10 | 2021-06-04 | 2020-06-10 | 2021-06-04
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | KENS-EAST | KENSICO-EASTVIEW CONNECTION TUNNEL | 6 | CONSTRUCTION TO 50% | 2021-06-05 | 2022-05-30 | 2021-06-05 | 2022-05-30
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | KENS-EAST | KENSICO-EASTVIEW CONNECTION TUNNEL | 7 | CONSTRUCTION TO 75% | 2022-05-31 | 2023-05-25 | 2022-05-31 | 2023-05-25
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | KENS-EAST | KENSICO-EASTVIEW CONNECTION TUNNEL | 8 | ORIGINAL EQUIP & FURNISHING | 2023-05-26 | 2024-02-19 | 2023-05-26 | 2024-02-19
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | KENS-EAST | KENSICO-EASTVIEW CONNECTION TUNNEL | 9 | SUBSTANTIAL COMPLETION | 2024-02-20 | 2024-08-17 | 2024-02-20 | 2024-08-17
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | KENS-EAST | KENSICO-EASTVIEW CONNECTION TUNNEL | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-08-18 | 2024-11-15 | 2024-08-18 | 2024-11-15
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | LFK-RELO | Lefrak Relocation | 1 | DEVELOP SCOPE | 2016-06-01 | 2016-09-28 | 2020-08-22 | 2020-12-19
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | LFK-RELO | Lefrak Relocation | 2 | PRELIMINARY DESIGN | 2016-09-29 | 2017-03-27 | 2020-12-20 | 2021-06-17
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | LFK-RELO | Lefrak Relocation | 3 | FINAL DESIGN | 2017-03-28 | 2018-09-28 | 2021-06-18 | 2022-12-19
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | LFK-RELO | Lefrak Relocation | 4 | BID AWARD AND REGISTER CONTRCT | 2018-09-29 | 2019-03-27 | 2022-12-20 | 2023-06-17
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | LFK-RELO | Lefrak Relocation | 5 | CONSTRUCTION TO 25% | 2019-03-28 | 2020-01-01 | 2023-06-18 | 2024-03-23
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | LFK-RELO | Lefrak Relocation | 6 | CONSTRUCTION TO 50% | 2020-01-02 | 2020-10-07 | 2024-03-24 | 2024-12-28
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | LFK-RELO | Lefrak Relocation | 7 | CONSTRUCTION TO 75% | 2020-10-08 | 2021-07-14 | 2024-12-29 | 2025-10-04
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | LFK-RELO | Lefrak Relocation | 8 | ORIGINAL EQUIP & FURNISHING | 2021-07-15 | 2021-10-12 | 2025-10-05 | 2026-01-02
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | LFK-RELO | Lefrak Relocation | 9 | SUBSTANTIAL COMPLETION | 2021-10-13 | 2021-12-11 | 2026-01-03 | 2026-03-03
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | LFK-RELO | Lefrak Relocation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-12-12 | 2022-03-11 | 2026-03-04 | 2026-06-01
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | MARG-HEAT | Margaretville WWTP Heat Line | 9 | SUBSTANTIAL COMPLETION | 2028-01-21 | 2028-07-18 | 2028-01-21 | 2028-07-18
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | MARG-HEAT | Margaretville WWTP Heat Line | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2028-07-19 | 2028-10-16 | 2028-07-19 | 2028-10-16
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | MONIT-13 | FAD 13-17 Monitoring | 1 | DEVELOP SCOPE | 2013-01-01 | 2022-12-29 | 2013-01-01 | 2022-12-29
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | MS4-STORM | MS4 CITYWIDE STORMWATER MANAGEMENT PROGRAM | 1 | DEVELOP SCOPE | 2017-12-01 | 2018-08-27 | 2017-12-01 | 2018-08-27
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | MS4-STORM | MS4 CITYWIDE STORMWATER MANAGEMENT PROGRAM | 2 | PRELIMINARY DESIGN | 2018-08-28 | 2019-08-22 | 2018-08-28 | 2019-08-22
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | MS4-STORM | MS4 CITYWIDE STORMWATER MANAGEMENT PROGRAM | 3 | FINAL DESIGN | 2019-08-23 | 2021-02-12 | 2019-08-23 | 2021-02-12
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | MS4-STORM | MS4 CITYWIDE STORMWATER MANAGEMENT PROGRAM | 4 | BID AWARD AND REGISTER CONTRCT | 2021-02-13 | 2021-11-09 | 2021-02-13 | 2021-11-09
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | MS4-STORM | MS4 CITYWIDE STORMWATER MANAGEMENT PROGRAM | 5 | CONSTRUCTION TO 25% | 2021-11-10 | 2022-11-04 | 2021-11-10 | 2022-11-04
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | MS4-STORM | MS4 CITYWIDE STORMWATER MANAGEMENT PROGRAM | 6 | CONSTRUCTION TO 50% | 2022-11-05 | 2023-10-30 | 2022-11-05 | 2023-10-30
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | MS4-STORM | MS4 CITYWIDE STORMWATER MANAGEMENT PROGRAM | 7 | CONSTRUCTION TO 75% | 2023-10-31 | 2024-10-24 | 2023-10-31 | 2024-10-24
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | MS4-STORM | MS4 CITYWIDE STORMWATER MANAGEMENT PROGRAM | 8 | ORIGINAL EQUIP & FURNISHING | 2024-10-25 | 2025-07-21 | 2024-10-25 | 2025-07-21
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | MS4-STORM | MS4 CITYWIDE STORMWATER MANAGEMENT PROGRAM | 9 | SUBSTANTIAL COMPLETION | 2025-07-22 | 2030-01-16 | 2025-07-22 | 2030-01-16
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | MS4-STORM | MS4 CITYWIDE STORMWATER MANAGEMENT PROGRAM | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2030-01-17 | 2030-04-16 | 2030-01-17 | 2030-04-16
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | NYSDOTBRG | NYS DOT Bridges El Grant, Jesup, Nelson, Depot, Boston Road | 1 | DEVELOP SCOPE | 2019-06-01 | 2019-08-29 | 2019-06-01 | 2019-08-29
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | NYSDOTBRG | NYS DOT Bridges El Grant, Jesup, Nelson, Depot, Boston Road | 2 | PRELIMINARY DESIGN | 2019-08-30 | 2019-12-27 | 2019-08-30 | 2019-12-27
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | NYSDOTBRG | NYS DOT Bridges El Grant, Jesup, Nelson, Depot, Boston Road | 3 | FINAL DESIGN | 2019-12-28 | 2020-06-24 | 2019-12-28 | 2020-06-24
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | NYSDOTBRG | NYS DOT Bridges El Grant, Jesup, Nelson, Depot, Boston Road | 4 | BID AWARD AND REGISTER CONTRCT | 2020-06-25 | 2020-09-22 | 2020-06-25 | 2020-09-22
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | NYSDOTBRG | NYS DOT Bridges El Grant, Jesup, Nelson, Depot, Boston Road | 5 | CONSTRUCTION TO 25% | 2020-09-23 | 2021-01-20 | 2020-09-23 | 2021-01-20
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | NYSDOTBRG | NYS DOT Bridges El Grant, Jesup, Nelson, Depot, Boston Road | 6 | CONSTRUCTION TO 50% | 2021-01-21 | 2021-05-20 | 2021-01-21 | 2021-05-20
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | NYSDOTBRG | NYS DOT Bridges El Grant, Jesup, Nelson, Depot, Boston Road | 7 | CONSTRUCTION TO 75% | 2021-05-21 | 2021-09-17 | 2021-05-21 | 2021-09-17
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | NYSDOTBRG | NYS DOT Bridges El Grant, Jesup, Nelson, Depot, Boston Road | 8 | ORIGINAL EQUIP & FURNISHING | 2021-09-18 | 2021-12-16 | 2021-09-18 | 2021-12-16
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | NYSDOTBRG | NYS DOT Bridges El Grant, Jesup, Nelson, Depot, Boston Road | 9 | SUBSTANTIAL COMPLETION | 2021-12-17 | 2022-02-14 | 2021-12-17 | 2022-02-14
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | NYSDOTBRG | NYS DOT Bridges El Grant, Jesup, Nelson, Depot, Boston Road | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-02-15 | 2022-03-16 | 2022-02-15 | 2022-03-16
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PJ-PLNT | RECONSTRUCTION OF PORT JERVIS WPCP, DEL | 1 | DEVELOP SCOPE | 2003-11-12 | 2004-08-07 | 2005-01-18 | 2005-10-14
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PJ-PLNT | RECONSTRUCTION OF PORT JERVIS WPCP, DEL | 2 | PRELIMINARY DESIGN | 2004-08-08 | 2005-08-02 | 2005-10-15 | 2006-10-09
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PJ-PLNT | RECONSTRUCTION OF PORT JERVIS WPCP, DEL | 3 | FINAL DESIGN | 2005-08-03 | 2007-01-24 | 2006-10-10 | 2008-04-01
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PJ-PLNT | RECONSTRUCTION OF PORT JERVIS WPCP, DEL | 4 | BID AWARD AND REGISTER CONTRCT | 2007-01-25 | 2007-10-21 | 2008-04-02 | 2008-12-27
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PJ-PLNT | RECONSTRUCTION OF PORT JERVIS WPCP, DEL | 5 | CONSTRUCTION TO 25% | 2007-10-22 | 2008-10-15 | 2008-12-28 | 2009-12-22
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PJ-PLNT | RECONSTRUCTION OF PORT JERVIS WPCP, DEL | 6 | CONSTRUCTION TO 50% | 2008-10-16 | 2009-10-10 | 2009-12-23 | 2010-12-17
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PJ-PLNT | RECONSTRUCTION OF PORT JERVIS WPCP, DEL | 7 | CONSTRUCTION TO 75% | 2009-10-11 | 2010-10-05 | 2010-12-18 | 2011-12-12
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PJ-PLNT | RECONSTRUCTION OF PORT JERVIS WPCP, DEL | 8 | ORIGINAL EQUIP & FURNISHING | 2010-10-06 | 2011-07-02 | 2011-12-13 | 2012-09-07
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PJ-PLNT | RECONSTRUCTION OF PORT JERVIS WPCP, DEL | 9 | SUBSTANTIAL COMPLETION | 2011-07-03 | 2011-12-29 | 2012-09-08 | 2025-03-03
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PJ-PLNT | RECONSTRUCTION OF PORT JERVIS WPCP, DEL | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2011-12-30 | 2012-03-28 | 2025-03-04 | 2025-06-01
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PS179 | REHAB 179 ST PS/CONST MULTIPLE PS IN TOWER AREA | 1 | DEVELOP SCOPE | 2020-06-01 | 2021-02-25 | 2020-06-01 | 2021-02-25
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PS179 | REHAB 179 ST PS/CONST MULTIPLE PS IN TOWER AREA | 2 | PRELIMINARY DESIGN | 2021-02-26 | 2022-02-20 | 2021-02-26 | 2022-02-20
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PS179 | REHAB 179 ST PS/CONST MULTIPLE PS IN TOWER AREA | 3 | FINAL DESIGN | 2022-02-21 | 2023-08-14 | 2022-02-21 | 2023-08-14
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PS179 | REHAB 179 ST PS/CONST MULTIPLE PS IN TOWER AREA | 4 | BID AWARD AND REGISTER CONTRCT | 2023-08-15 | 2024-05-10 | 2023-08-15 | 2024-05-10
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PS179 | REHAB 179 ST PS/CONST MULTIPLE PS IN TOWER AREA | 5 | CONSTRUCTION TO 25% | 2024-05-11 | 2025-05-05 | 2024-05-11 | 2025-05-05
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PS179 | REHAB 179 ST PS/CONST MULTIPLE PS IN TOWER AREA | 6 | CONSTRUCTION TO 50% | 2025-05-06 | 2026-04-30 | 2025-05-06 | 2026-04-30
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PS179 | REHAB 179 ST PS/CONST MULTIPLE PS IN TOWER AREA | 7 | CONSTRUCTION TO 75% | 2026-05-01 | 2027-04-25 | 2026-05-01 | 2027-04-25
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PS179 | REHAB 179 ST PS/CONST MULTIPLE PS IN TOWER AREA | 8 | ORIGINAL EQUIP & FURNISHING | 2027-04-26 | 2028-01-20 | 2027-04-26 | 2028-01-20
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PS179 | REHAB 179 ST PS/CONST MULTIPLE PS IN TOWER AREA | 9 | SUBSTANTIAL COMPLETION | 2028-01-21 | 2028-07-18 | 2028-01-21 | 2028-07-18
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PS179 | REHAB 179 ST PS/CONST MULTIPLE PS IN TOWER AREA | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2028-07-19 | 2028-10-16 | 2028-07-19 | 2028-10-16
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PW-TOC3 | CONSULTANT DESIGN SVCS FOR ALL BWWT JOC & CAPITAL PROJECTS | 1 | DEVELOP SCOPE | 2029-06-01 | 2029-08-29 | 2027-06-01 | 2027-08-29
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PW-TOC3 | CONSULTANT DESIGN SVCS FOR ALL BWWT JOC & CAPITAL PROJECTS | 2 | PRELIMINARY DESIGN | 2029-08-30 | 2029-12-27 | 2027-08-30 | 2027-12-27
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PW-TOC3 | CONSULTANT DESIGN SVCS FOR ALL BWWT JOC & CAPITAL PROJECTS | 3 | FINAL DESIGN | 2029-12-28 | 2030-06-25 | 2027-12-28 | 2028-06-24
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PW-TOC3 | CONSULTANT DESIGN SVCS FOR ALL BWWT JOC & CAPITAL PROJECTS | 4 | BID AWARD AND REGISTER CONTRCT | 2030-06-26 | 2030-09-23 | 2028-06-25 | 2028-09-22
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PW-TOC3 | CONSULTANT DESIGN SVCS FOR ALL BWWT JOC & CAPITAL PROJECTS | 5 | CONSTRUCTION TO 25% | 2030-09-24 | 2031-01-21 | 2028-09-23 | 2029-01-20
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PW-TOC3 | CONSULTANT DESIGN SVCS FOR ALL BWWT JOC & CAPITAL PROJECTS | 6 | CONSTRUCTION TO 50% | 2031-01-22 | 2031-05-21 | 2029-01-21 | 2029-05-20
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PW-TOC3 | CONSULTANT DESIGN SVCS FOR ALL BWWT JOC & CAPITAL PROJECTS | 7 | CONSTRUCTION TO 75% | 2031-05-22 | 2031-09-18 | 2029-05-21 | 2029-09-17
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PW-TOC3 | CONSULTANT DESIGN SVCS FOR ALL BWWT JOC & CAPITAL PROJECTS | 8 | ORIGINAL EQUIP & FURNISHING | 2031-09-19 | 2031-12-17 | 2029-09-18 | 2029-12-16
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PW-TOC3 | CONSULTANT DESIGN SVCS FOR ALL BWWT JOC & CAPITAL PROJECTS | 9 | SUBSTANTIAL COMPLETION | 2031-12-18 | 2032-02-15 | 2029-12-17 | 2030-02-14
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PW-TOC3 | CONSULTANT DESIGN SVCS FOR ALL BWWT JOC & CAPITAL PROJECTS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2032-02-16 | 2032-03-16 | 2030-02-15 | 2030-03-16
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | RESAMSAF | DESIGN & CM FOR DAM SAFETY CONSTRUCTION | 1 | DEVELOP SCOPE | 2013-06-30 | 2014-03-26 | 2013-06-30 | 2014-03-26
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | RESAMSAF | DESIGN & CM FOR DAM SAFETY CONSTRUCTION | 2 | PRELIMINARY DESIGN | 2014-03-27 | 2015-03-21 | 2014-03-27 | 2015-03-21
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | RESAMSAF | DESIGN & CM FOR DAM SAFETY CONSTRUCTION | 3 | FINAL DESIGN | 2015-03-22 | 2016-09-11 | 2015-03-22 | 2016-09-11
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | RESAMSAF | DESIGN & CM FOR DAM SAFETY CONSTRUCTION | 4 | BID AWARD AND REGISTER CONTRCT | 2016-09-12 | 2017-06-08 | 2016-09-12 | 2017-06-08
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | RESAMSAF | DESIGN & CM FOR DAM SAFETY CONSTRUCTION | 5 | CONSTRUCTION TO 25% | 2017-06-09 | 2018-06-03 | 2017-06-09 | 2018-06-03
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | RESAMSAF | DESIGN & CM FOR DAM SAFETY CONSTRUCTION | 6 | CONSTRUCTION TO 50% | 2018-06-04 | 2019-05-29 | 2018-06-04 | 2019-05-29
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | RESAMSAF | DESIGN & CM FOR DAM SAFETY CONSTRUCTION | 7 | CONSTRUCTION TO 75% | 2019-05-30 | 2020-05-23 | 2019-05-30 | 2020-05-23
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | RESAMSAF | DESIGN & CM FOR DAM SAFETY CONSTRUCTION | 8 | ORIGINAL EQUIP & FURNISHING | 2020-05-24 | 2021-02-17 | 2020-05-24 | 2021-02-17
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | RESAMSAF | DESIGN & CM FOR DAM SAFETY CONSTRUCTION | 9 | SUBSTANTIAL COMPLETION | 2021-02-18 | 2021-08-16 | 2021-02-18 | 2029-08-14
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | RESAMSAF | DESIGN & CM FOR DAM SAFETY CONSTRUCTION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-08-17 | 2021-11-14 | 2029-08-15 | 2029-11-12
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | RIDGEPIPE | RIDGEWOOD RESERVOIR PIPE ABANDONMENT | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-08-29 | 2020-06-01 | 2020-08-29
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | RIDGEPIPE | RIDGEWOOD RESERVOIR PIPE ABANDONMENT | 2 | PRELIMINARY DESIGN | 2020-08-30 | 2020-12-27 | 2020-08-30 | 2020-12-27
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | RIDGEPIPE | RIDGEWOOD RESERVOIR PIPE ABANDONMENT | 3 | FINAL DESIGN | 2020-12-28 | 2021-06-25 | 2020-12-28 | 2021-06-25
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | RIDGEPIPE | RIDGEWOOD RESERVOIR PIPE ABANDONMENT | 4 | BID AWARD AND REGISTER CONTRCT | 2021-06-26 | 2021-09-23 | 2021-06-26 | 2021-09-23
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | RIDGEPIPE | RIDGEWOOD RESERVOIR PIPE ABANDONMENT | 5 | CONSTRUCTION TO 25% | 2021-09-24 | 2022-01-21 | 2021-09-24 | 2022-01-21
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | RIDGEPIPE | RIDGEWOOD RESERVOIR PIPE ABANDONMENT | 6 | CONSTRUCTION TO 50% | 2022-01-22 | 2022-05-21 | 2022-01-22 | 2022-05-21
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | RIDGEPIPE | RIDGEWOOD RESERVOIR PIPE ABANDONMENT | 7 | CONSTRUCTION TO 75% | 2022-05-22 | 2022-09-18 | 2022-05-22 | 2022-09-18
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | RIDGEPIPE | RIDGEWOOD RESERVOIR PIPE ABANDONMENT | 8 | ORIGINAL EQUIP & FURNISHING | 2022-09-19 | 2022-12-17 | 2022-09-19 | 2022-12-17
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | RIDGEPIPE | RIDGEWOOD RESERVOIR PIPE ABANDONMENT | 9 | SUBSTANTIAL COMPLETION | 2022-12-18 | 2023-02-15 | 2022-12-18 | 2023-02-15
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | RIDGEPIPE | RIDGEWOOD RESERVOIR PIPE ABANDONMENT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-02-16 | 2023-03-17 | 2023-02-16 | 2023-03-17
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | RLCY-WWT | FLOODWATER RESILIENCY AT BWT FACILITES | 1 | DEVELOP SCOPE | 2017-06-01 | 2018-02-25 | 2014-07-01 | 2015-03-27
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | RLCY-WWT | FLOODWATER RESILIENCY AT BWT FACILITES | 2 | PRELIMINARY DESIGN | 2018-02-26 | 2019-02-20 | 2015-03-28 | 2016-03-21
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | RLCY-WWT | FLOODWATER RESILIENCY AT BWT FACILITES | 3 | FINAL DESIGN | 2019-02-21 | 2020-08-13 | 2016-03-22 | 2017-09-12
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | RLCY-WWT | FLOODWATER RESILIENCY AT BWT FACILITES | 4 | BID AWARD AND REGISTER CONTRCT | 2020-08-14 | 2021-05-10 | 2017-09-13 | 2018-06-09
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | RLCY-WWT | FLOODWATER RESILIENCY AT BWT FACILITES | 5 | CONSTRUCTION TO 25% | 2021-05-11 | 2022-05-05 | 2018-06-10 | 2019-06-04
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | RLCY-WWT | FLOODWATER RESILIENCY AT BWT FACILITES | 6 | CONSTRUCTION TO 50% | 2022-05-06 | 2023-04-30 | 2019-06-05 | 2020-05-29
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | RLCY-WWT | FLOODWATER RESILIENCY AT BWT FACILITES | 7 | CONSTRUCTION TO 75% | 2023-05-01 | 2024-04-24 | 2020-05-30 | 2021-05-24
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | RLCY-WWT | FLOODWATER RESILIENCY AT BWT FACILITES | 8 | ORIGINAL EQUIP & FURNISHING | 2024-04-25 | 2025-01-19 | 2021-05-25 | 2022-02-18
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | RLCY-WWT | FLOODWATER RESILIENCY AT BWT FACILITES | 9 | SUBSTANTIAL COMPLETION | 2025-01-20 | 2025-07-18 | 2022-02-19 | 2022-08-17
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | RLCY-WWT | FLOODWATER RESILIENCY AT BWT FACILITES | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-07-19 | 2025-10-16 | 2022-08-18 | 2022-11-15
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | ROWGI-A | GI - CITYWIDE CONSTRUCTION OF ROW GREEN INFRASTRUCTURE | 1 | FINAL DESIGN | 2021-06-15 | 2022-12-06 | 2023-12-20 | 2025-06-11
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | ROWGI-A | GI - CITYWIDE CONSTRUCTION OF ROW GREEN INFRASTRUCTURE | 2 | CONSTRUCTION TO 25% | 2022-12-07 | 2023-08-03 | 2025-06-12 | 2026-02-06
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | ROWGI-A | GI - CITYWIDE CONSTRUCTION OF ROW GREEN INFRASTRUCTURE | 3 | CONSTRUCTION TO 50% | 2023-08-04 | 2024-03-30 | 2026-02-07 | 2026-10-04
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | ROWGI-A | GI - CITYWIDE CONSTRUCTION OF ROW GREEN INFRASTRUCTURE | 4 | CONSTRUCTION TO 75% | 2024-03-31 | 2024-11-25 | 2026-10-05 | 2027-06-01
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDHILLV | HILLVIEW RESERVOIR SECURITY FENCE IMPROVEMENTS | 1 | DEVELOP SCOPE | 2017-06-30 | 2017-10-27 | 2017-06-30 | 2017-10-27
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDHILLV | HILLVIEW RESERVOIR SECURITY FENCE IMPROVEMENTS | 2 | PRELIMINARY DESIGN | 2017-10-28 | 2018-04-25 | 2017-10-28 | 2018-04-25
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDHILLV | HILLVIEW RESERVOIR SECURITY FENCE IMPROVEMENTS | 3 | FINAL DESIGN | 2018-04-26 | 2019-10-27 | 2018-04-26 | 2019-10-27
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDHILLV | HILLVIEW RESERVOIR SECURITY FENCE IMPROVEMENTS | 4 | BID AWARD AND REGISTER CONTRCT | 2019-10-28 | 2020-04-24 | 2019-10-28 | 2020-04-24
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDHILLV | HILLVIEW RESERVOIR SECURITY FENCE IMPROVEMENTS | 5 | CONSTRUCTION TO 25% | 2020-04-25 | 2021-01-29 | 2020-04-25 | 2021-01-29
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDHILLV | HILLVIEW RESERVOIR SECURITY FENCE IMPROVEMENTS | 6 | CONSTRUCTION TO 50% | 2021-01-30 | 2021-11-05 | 2021-01-30 | 2021-11-05
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDHILLV | HILLVIEW RESERVOIR SECURITY FENCE IMPROVEMENTS | 7 | CONSTRUCTION TO 75% | 2021-11-06 | 2022-08-12 | 2021-11-06 | 2022-08-12
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDHILLV | HILLVIEW RESERVOIR SECURITY FENCE IMPROVEMENTS | 8 | ORIGINAL EQUIP & FURNISHING | 2022-08-13 | 2022-11-10 | 2022-08-13 | 2022-11-10
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDHILLV | HILLVIEW RESERVOIR SECURITY FENCE IMPROVEMENTS | 9 | SUBSTANTIAL COMPLETION | 2022-11-11 | 2023-01-09 | 2022-11-11 | 2023-01-09
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDHILLV | HILLVIEW RESERVOIR SECURITY FENCE IMPROVEMENTS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-01-10 | 2023-04-09 | 2023-01-10 | 2023-04-09
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDPUMP | RECONS OF VARIOUS PUMPING STATIONS DUE TO HURRICANE SANDY | 1 | DEVELOP SCOPE | 2012-10-01 | 2012-12-29 | 2012-10-01 | 2013-06-27
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDPUMP | RECONS OF VARIOUS PUMPING STATIONS DUE TO HURRICANE SANDY | 2 | PRELIMINARY DESIGN | 2012-12-30 | 2013-04-28 | 2013-06-28 | 2014-06-22
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDPUMP | RECONS OF VARIOUS PUMPING STATIONS DUE TO HURRICANE SANDY | 3 | FINAL DESIGN | 2013-04-29 | 2013-10-25 | 2014-06-23 | 2015-12-14
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDPUMP | RECONS OF VARIOUS PUMPING STATIONS DUE TO HURRICANE SANDY | 4 | BID AWARD AND REGISTER CONTRCT | 2013-10-26 | 2014-01-23 | 2015-12-15 | 2016-09-09
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDPUMP | RECONS OF VARIOUS PUMPING STATIONS DUE TO HURRICANE SANDY | 5 | CONSTRUCTION TO 25% | 2014-01-24 | 2014-05-23 | 2016-09-10 | 2017-09-04
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDPUMP | RECONS OF VARIOUS PUMPING STATIONS DUE TO HURRICANE SANDY | 6 | CONSTRUCTION TO 50% | 2014-05-24 | 2014-09-20 | 2017-09-05 | 2018-08-30
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDPUMP | RECONS OF VARIOUS PUMPING STATIONS DUE TO HURRICANE SANDY | 7 | CONSTRUCTION TO 75% | 2014-09-21 | 2015-01-18 | 2018-08-31 | 2019-08-25
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDPUMP | RECONS OF VARIOUS PUMPING STATIONS DUE TO HURRICANE SANDY | 8 | ORIGINAL EQUIP & FURNISHING | 2015-01-19 | 2015-04-18 | 2019-08-26 | 2020-05-21
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDPUMP | RECONS OF VARIOUS PUMPING STATIONS DUE TO HURRICANE SANDY | 9 | SUBSTANTIAL COMPLETION | 2015-04-19 | 2015-06-17 | 2020-05-22 | 2028-11-15
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDPUMP | RECONS OF VARIOUS PUMPING STATIONS DUE TO HURRICANE SANDY | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-06-18 | 2015-07-17 | 2028-11-16 | 2029-02-13
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDWM | RECONS OF WATER MAINS CITYWIDE DUE TO HURRICANE SANDY | 1 | DEVELOP SCOPE | 2019-06-01 | 2019-08-29 | 2023-06-01 | 2023-08-29
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDWM | RECONS OF WATER MAINS CITYWIDE DUE TO HURRICANE SANDY | 2 | PRELIMINARY DESIGN | 2019-08-30 | 2019-12-27 | 2023-08-30 | 2023-12-27
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDWM | RECONS OF WATER MAINS CITYWIDE DUE TO HURRICANE SANDY | 3 | FINAL DESIGN | 2019-12-28 | 2020-06-24 | 2023-12-28 | 2024-06-24
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDWM | RECONS OF WATER MAINS CITYWIDE DUE TO HURRICANE SANDY | 4 | BID AWARD AND REGISTER CONTRCT | 2020-06-25 | 2020-09-22 | 2024-06-25 | 2024-09-22
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDWM | RECONS OF WATER MAINS CITYWIDE DUE TO HURRICANE SANDY | 5 | CONSTRUCTION TO 25% | 2020-09-23 | 2021-01-20 | 2024-09-23 | 2025-01-20
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDWM | RECONS OF WATER MAINS CITYWIDE DUE TO HURRICANE SANDY | 6 | CONSTRUCTION TO 50% | 2021-01-21 | 2021-05-20 | 2025-01-21 | 2025-05-20
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDWM | RECONS OF WATER MAINS CITYWIDE DUE TO HURRICANE SANDY | 7 | CONSTRUCTION TO 75% | 2021-05-21 | 2021-09-17 | 2025-05-21 | 2025-09-17
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDWM | RECONS OF WATER MAINS CITYWIDE DUE TO HURRICANE SANDY | 8 | ORIGINAL EQUIP & FURNISHING | 2021-09-18 | 2021-12-16 | 2025-09-18 | 2025-12-16
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDWM | RECONS OF WATER MAINS CITYWIDE DUE TO HURRICANE SANDY | 9 | SUBSTANTIAL COMPLETION | 2021-12-17 | 2022-02-14 | 2025-12-17 | 2026-02-14
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDWM | RECONS OF WATER MAINS CITYWIDE DUE TO HURRICANE SANDY | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-02-15 | 2022-03-16 | 2026-02-15 | 2026-03-16
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDWPCPS | RECONS OF WPCPS AND PUMPING STATIONS DUE TO HURRICANE SANDY | 1 | DEVELOP SCOPE | 2015-12-01 | 2016-08-26 | 2015-12-01 | 2016-08-26
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDWPCPS | RECONS OF WPCPS AND PUMPING STATIONS DUE TO HURRICANE SANDY | 2 | PRELIMINARY DESIGN | 2016-08-27 | 2017-08-21 | 2016-08-27 | 2017-08-21
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDWPCPS | RECONS OF WPCPS AND PUMPING STATIONS DUE TO HURRICANE SANDY | 3 | FINAL DESIGN | 2017-08-22 | 2019-02-12 | 2017-08-22 | 2019-02-12
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDWPCPS | RECONS OF WPCPS AND PUMPING STATIONS DUE TO HURRICANE SANDY | 4 | BID AWARD AND REGISTER CONTRCT | 2019-02-13 | 2019-11-09 | 2019-02-13 | 2019-11-09
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDWPCPS | RECONS OF WPCPS AND PUMPING STATIONS DUE TO HURRICANE SANDY | 5 | CONSTRUCTION TO 25% | 2019-11-10 | 2020-11-03 | 2019-11-10 | 2020-11-03
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDWPCPS | RECONS OF WPCPS AND PUMPING STATIONS DUE TO HURRICANE SANDY | 6 | CONSTRUCTION TO 50% | 2020-11-04 | 2021-10-29 | 2020-11-04 | 2021-10-29
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDWPCPS | RECONS OF WPCPS AND PUMPING STATIONS DUE TO HURRICANE SANDY | 7 | CONSTRUCTION TO 75% | 2021-10-30 | 2022-10-24 | 2021-10-30 | 2022-10-24
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDWPCPS | RECONS OF WPCPS AND PUMPING STATIONS DUE TO HURRICANE SANDY | 8 | ORIGINAL EQUIP & FURNISHING | 2022-10-25 | 2023-07-21 | 2022-10-25 | 2023-07-21
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDWPCPS | RECONS OF WPCPS AND PUMPING STATIONS DUE TO HURRICANE SANDY | 9 | SUBSTANTIAL COMPLETION | 2023-07-22 | 2024-01-17 | 2023-07-22 | 2024-01-17
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDWPCPS | RECONS OF WPCPS AND PUMPING STATIONS DUE TO HURRICANE SANDY | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-01-18 | 2024-04-16 | 2024-01-18 | 2024-04-16
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SFM-1 | RECONS OF SLUDGE FORCEMAIN FROM JAMAICA TO 26TH WARD WPCP | 1 | DEVELOP SCOPE | 2024-06-01 | 2025-02-25 | 2024-06-01 | 2025-02-25
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SFM-1 | RECONS OF SLUDGE FORCEMAIN FROM JAMAICA TO 26TH WARD WPCP | 2 | PRELIMINARY DESIGN | 2025-02-26 | 2026-02-20 | 2025-02-26 | 2026-02-20
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SFM-1 | RECONS OF SLUDGE FORCEMAIN FROM JAMAICA TO 26TH WARD WPCP | 3 | FINAL DESIGN | 2026-02-21 | 2027-08-14 | 2026-02-21 | 2027-08-14
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SFM-1 | RECONS OF SLUDGE FORCEMAIN FROM JAMAICA TO 26TH WARD WPCP | 4 | BID AWARD AND REGISTER CONTRCT | 2027-08-15 | 2028-05-10 | 2027-08-15 | 2028-05-10
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SFM-1 | RECONS OF SLUDGE FORCEMAIN FROM JAMAICA TO 26TH WARD WPCP | 5 | CONSTRUCTION TO 25% | 2028-05-11 | 2029-05-05 | 2028-05-11 | 2029-05-05
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SFM-1 | RECONS OF SLUDGE FORCEMAIN FROM JAMAICA TO 26TH WARD WPCP | 6 | CONSTRUCTION TO 50% | 2029-05-06 | 2030-04-30 | 2029-05-06 | 2030-04-30
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SFM-1 | RECONS OF SLUDGE FORCEMAIN FROM JAMAICA TO 26TH WARD WPCP | 7 | CONSTRUCTION TO 75% | 2030-05-01 | 2031-04-25 | 2030-05-01 | 2031-04-25
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SFM-1 | RECONS OF SLUDGE FORCEMAIN FROM JAMAICA TO 26TH WARD WPCP | 8 | ORIGINAL EQUIP & FURNISHING | 2031-04-26 | 2032-01-20 | 2031-04-26 | 2032-01-20
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SFM-1 | RECONS OF SLUDGE FORCEMAIN FROM JAMAICA TO 26TH WARD WPCP | 9 | SUBSTANTIAL COMPLETION | 2032-01-21 | 2032-07-18 | 2032-01-21 | 2032-07-18
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SFM-1 | RECONS OF SLUDGE FORCEMAIN FROM JAMAICA TO 26TH WARD WPCP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2032-07-19 | 2032-10-16 | 2032-07-19 | 2032-10-16
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | STMEOH-18 | FAD 18-22 STORMWATER MGMT. (EOH) | 1 | DEVELOP SCOPE | 2019-12-01 | 2029-11-27 | 2019-12-01 | 2029-11-27
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | STMWOH-08 | FAD 08-12 - Stormwater Management-WOH | 1 | DEVELOP SCOPE | 2008-02-01 | 2018-01-28 | 2008-02-01 | 2018-01-28
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | STMWOH-13 | FAD 13-17 Stormwater Mgmt. (WOH) | 1 | DEVELOP SCOPE | 2013-01-01 | 2022-12-29 | 2018-06-05 | 2028-06-01
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | STMWOH-18 | FAD 18-22 STORMWATER MGMT. (WOH) | 1 | DEVELOP SCOPE | 2018-12-01 | 2028-11-27 | 2018-12-01 | 2028-11-27
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | STPUPG-18 | FAD 18-22 WWTP UPGRADE PROGRAM | 1 | DEVELOP SCOPE | 2018-12-01 | 2028-11-27 | 2018-12-01 | 2028-11-27
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | STREAM-18 | FAD 18-22 STREAM MANAGEMENT | 1 | DEVELOP SCOPE | 2019-05-01 | 2029-04-27 | 2019-05-01 | 2029-04-27
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | TOSC1 | TASK ORDER SERVICES | 1 | DEVELOP SCOPE | 1922-08-04 | 2022-07-08 | 1922-08-04 | 2022-07-08
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | TOSC1 | TASK ORDER SERVICES | 2 | ON-SITE CONSTRUCTION MANAGEMEN | 2022-07-09 | 2028-06-06 | 2022-07-09 | 2028-06-06
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | TOSC1 | TASK ORDER SERVICES | 3 | POST-CONSTRUCTION CLOSE-OUT | 2028-06-07 | 2029-06-01 | 2028-06-07 | 2029-06-01
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | UTIUTIL | UTILITY RELOCATION FOR SE AND WM PROJECTS | 1 | BID AWARD AND REGISTER CONTRCT | 2006-07-01 | 2025-06-24 | 0 | 0
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | UTIUTIL | UTILITY RELOCATION FOR SE AND WM PROJECTS | 2 | BID AWARD AND REGISTER CONTRCT | 2006-07-01 | 2025-06-24 | 2006-07-01 | 2025-06-24
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WEC-LGE16 | LARGE WATER METER PURCHASES, REPLACEMENTS AND INSTALLATIONS | 1 | DEVELOP SCOPE | 2016-01-29 | 2016-05-27 | 2021-08-22 | 2021-12-19
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WEC-LGE16 | LARGE WATER METER PURCHASES, REPLACEMENTS AND INSTALLATIONS | 2 | PRELIMINARY DESIGN | 2016-05-28 | 2016-11-23 | 2021-12-20 | 2022-06-17
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WEC-LGE16 | LARGE WATER METER PURCHASES, REPLACEMENTS AND INSTALLATIONS | 3 | FINAL DESIGN | 2016-11-24 | 2018-05-27 | 2022-06-18 | 2023-12-19
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WEC-LGE16 | LARGE WATER METER PURCHASES, REPLACEMENTS AND INSTALLATIONS | 4 | BID AWARD AND REGISTER CONTRCT | 2018-05-28 | 2018-11-23 | 2023-12-20 | 2024-06-16
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WEC-LGE16 | LARGE WATER METER PURCHASES, REPLACEMENTS AND INSTALLATIONS | 5 | CONSTRUCTION TO 25% | 2018-11-24 | 2019-08-30 | 2024-06-17 | 2025-03-23
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WEC-LGE16 | LARGE WATER METER PURCHASES, REPLACEMENTS AND INSTALLATIONS | 6 | CONSTRUCTION TO 50% | 2019-08-31 | 2020-06-05 | 2025-03-24 | 2025-12-28
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WEC-LGE16 | LARGE WATER METER PURCHASES, REPLACEMENTS AND INSTALLATIONS | 7 | CONSTRUCTION TO 75% | 2020-06-06 | 2021-03-12 | 2025-12-29 | 2026-10-04
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WEC-LGE16 | LARGE WATER METER PURCHASES, REPLACEMENTS AND INSTALLATIONS | 8 | ORIGINAL EQUIP & FURNISHING | 2021-03-13 | 2021-06-10 | 2026-10-05 | 2027-01-02
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WEC-LGE16 | LARGE WATER METER PURCHASES, REPLACEMENTS AND INSTALLATIONS | 9 | SUBSTANTIAL COMPLETION | 2021-06-11 | 2021-08-09 | 2027-01-03 | 2027-03-03
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WEC-LGE16 | LARGE WATER METER PURCHASES, REPLACEMENTS AND INSTALLATIONS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-08-10 | 2021-11-07 | 2027-03-04 | 2027-06-01
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WFF-CUNY | Water Efficiency Upgrades at CUNY Colleges | 1 | DEVELOP SCOPE | 2021-06-01 | 2021-08-29 | 2021-06-01 | 2021-08-29
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WFF-CUNY | Water Efficiency Upgrades at CUNY Colleges | 2 | PRELIMINARY DESIGN | 2021-08-30 | 2021-12-27 | 2021-08-30 | 2021-12-27
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WFF-CUNY | Water Efficiency Upgrades at CUNY Colleges | 3 | FINAL DESIGN | 2021-12-28 | 2022-06-25 | 2021-12-28 | 2022-06-25
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WFF-CUNY | Water Efficiency Upgrades at CUNY Colleges | 4 | BID AWARD AND REGISTER CONTRCT | 2022-06-26 | 2022-09-23 | 2022-06-26 | 2022-09-23
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WFF-CUNY | Water Efficiency Upgrades at CUNY Colleges | 5 | CONSTRUCTION TO 25% | 2022-09-24 | 2023-01-21 | 2022-09-24 | 2023-01-21
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WFF-CUNY | Water Efficiency Upgrades at CUNY Colleges | 6 | CONSTRUCTION TO 50% | 2023-01-22 | 2023-05-21 | 2023-01-22 | 2023-05-21
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WFF-CUNY | Water Efficiency Upgrades at CUNY Colleges | 7 | CONSTRUCTION TO 75% | 2023-05-22 | 2023-09-18 | 2023-05-22 | 2023-09-18
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WFF-CUNY | Water Efficiency Upgrades at CUNY Colleges | 8 | ORIGINAL EQUIP & FURNISHING | 2023-09-19 | 2023-12-17 | 2023-09-19 | 2023-12-17
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WFF-CUNY | Water Efficiency Upgrades at CUNY Colleges | 9 | SUBSTANTIAL COMPLETION | 2023-12-18 | 2024-02-15 | 2023-12-18 | 2024-02-15
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WFF-CUNY | Water Efficiency Upgrades at CUNY Colleges | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-02-16 | 2024-03-16 | 2024-02-16 | 2024-03-16
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WFF-HHC | HHC Fixture Replacement in City-owned Hospitals | 1 | DEVELOP SCOPE | 2020-06-15 | 2020-10-12 | 2020-06-15 | 2020-10-12
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WFF-HHC | HHC Fixture Replacement in City-owned Hospitals | 2 | PRELIMINARY DESIGN | 2020-10-13 | 2021-04-10 | 2020-10-13 | 2021-04-10
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WFF-HHC | HHC Fixture Replacement in City-owned Hospitals | 3 | FINAL DESIGN | 2021-04-11 | 2022-10-12 | 2021-04-11 | 2022-10-12
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WFF-HHC | HHC Fixture Replacement in City-owned Hospitals | 4 | BID AWARD AND REGISTER CONTRCT | 2022-10-13 | 2023-04-10 | 2022-10-13 | 2023-04-10
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WFF-HHC | HHC Fixture Replacement in City-owned Hospitals | 5 | CONSTRUCTION TO 25% | 2023-04-11 | 2024-01-15 | 2023-04-11 | 2024-01-15
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WFF-HHC | HHC Fixture Replacement in City-owned Hospitals | 6 | CONSTRUCTION TO 50% | 2024-01-16 | 2024-10-21 | 2024-01-16 | 2024-10-21
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WFF-HHC | HHC Fixture Replacement in City-owned Hospitals | 7 | CONSTRUCTION TO 75% | 2024-10-22 | 2025-07-28 | 2024-10-22 | 2025-07-28
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WFF-HHC | HHC Fixture Replacement in City-owned Hospitals | 8 | ORIGINAL EQUIP & FURNISHING | 2025-07-29 | 2025-10-26 | 2025-07-29 | 2025-10-26
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WFF-HHC | HHC Fixture Replacement in City-owned Hospitals | 9 | SUBSTANTIAL COMPLETION | 2025-10-27 | 2025-12-25 | 2025-10-27 | 2025-12-25
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WFF-HHC | HHC Fixture Replacement in City-owned Hospitals | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-12-26 | 2026-03-25 | 2025-12-26 | 2026-03-25
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WFF-IGAS | WFF-INTER-GOV'T AGREEMENT | 1 | DEVELOP SCOPE | 2015-03-01 | 2015-11-25 | 2015-03-01 | 2015-11-25
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WFF-IGAS | WFF-INTER-GOV'T AGREEMENT | 2 | PRELIMINARY DESIGN | 2015-11-26 | 2016-11-19 | 2015-11-26 | 2016-11-19
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WFF-IGAS | WFF-INTER-GOV'T AGREEMENT | 3 | FINAL DESIGN | 2016-11-20 | 2018-05-13 | 2016-11-20 | 2018-05-13
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WFF-IGAS | WFF-INTER-GOV'T AGREEMENT | 4 | BID AWARD AND REGISTER CONTRCT | 2018-05-14 | 2019-02-07 | 2018-05-14 | 2019-02-07
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WFF-IGAS | WFF-INTER-GOV'T AGREEMENT | 5 | CONSTRUCTION TO 25% | 2019-02-08 | 2020-02-02 | 2019-02-08 | 2020-02-02
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WFF-IGAS | WFF-INTER-GOV'T AGREEMENT | 6 | CONSTRUCTION TO 50% | 2020-02-03 | 2021-01-27 | 2020-02-03 | 2021-01-27
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WFF-IGAS | WFF-INTER-GOV'T AGREEMENT | 7 | CONSTRUCTION TO 75% | 2021-01-28 | 2022-01-22 | 2021-01-28 | 2022-01-22
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WFF-IGAS | WFF-INTER-GOV'T AGREEMENT | 8 | ORIGINAL EQUIP & FURNISHING | 2022-01-23 | 2022-10-19 | 2022-01-23 | 2022-10-19
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WFF-IGAS | WFF-INTER-GOV'T AGREEMENT | 9 | SUBSTANTIAL COMPLETION | 2022-10-20 | 2023-04-17 | 2022-10-20 | 2023-04-17
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WFF-IGAS | WFF-INTER-GOV'T AGREEMENT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-04-18 | 2023-07-16 | 2023-04-18 | 2023-07-16
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WFF-WWTP | WATER EFICIENCY UPGRADES AT DEP WASTEWATER TREATMENT PLANTS | 1 | DEVELOP SCOPE | 2020-06-15 | 2020-10-12 | 2020-06-15 | 2020-10-12
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WFF-WWTP | WATER EFICIENCY UPGRADES AT DEP WASTEWATER TREATMENT PLANTS | 2 | PRELIMINARY DESIGN | 2020-10-13 | 2021-04-10 | 2020-10-13 | 2021-04-10
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WFF-WWTP | WATER EFICIENCY UPGRADES AT DEP WASTEWATER TREATMENT PLANTS | 3 | FINAL DESIGN | 2021-04-11 | 2022-10-12 | 2021-04-11 | 2022-10-12
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WFF-WWTP | WATER EFICIENCY UPGRADES AT DEP WASTEWATER TREATMENT PLANTS | 4 | BID AWARD AND REGISTER CONTRCT | 2022-10-13 | 2023-04-10 | 2022-10-13 | 2023-04-10
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WFF-WWTP | WATER EFICIENCY UPGRADES AT DEP WASTEWATER TREATMENT PLANTS | 5 | CONSTRUCTION TO 25% | 2023-04-11 | 2024-01-15 | 2023-04-11 | 2024-01-15
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WFF-WWTP | WATER EFICIENCY UPGRADES AT DEP WASTEWATER TREATMENT PLANTS | 6 | CONSTRUCTION TO 50% | 2024-01-16 | 2024-10-21 | 2024-01-16 | 2024-10-21
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WFF-WWTP | WATER EFICIENCY UPGRADES AT DEP WASTEWATER TREATMENT PLANTS | 7 | CONSTRUCTION TO 75% | 2024-10-22 | 2025-07-28 | 2024-10-22 | 2025-07-28
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WFF-WWTP | WATER EFICIENCY UPGRADES AT DEP WASTEWATER TREATMENT PLANTS | 8 | ORIGINAL EQUIP & FURNISHING | 2025-07-29 | 2025-10-26 | 2025-07-29 | 2025-10-26
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WFF-WWTP | WATER EFICIENCY UPGRADES AT DEP WASTEWATER TREATMENT PLANTS | 9 | SUBSTANTIAL COMPLETION | 2025-10-27 | 2025-12-25 | 2025-10-27 | 2025-12-25
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WFF-WWTP | WATER EFICIENCY UPGRADES AT DEP WASTEWATER TREATMENT PLANTS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-12-26 | 2026-03-25 | 2025-12-26 | 2026-03-25
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WFINSP-SP | CITYWIDE WATERFRONT INSPECTIONS AT VARIOUS WPCPS | 1 | DEVELOP SCOPE | 2019-06-01 | 2019-08-29 | 2022-11-01 | 2023-01-29
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WFINSP-SP | CITYWIDE WATERFRONT INSPECTIONS AT VARIOUS WPCPS | 2 | PRELIMINARY DESIGN | 2019-08-30 | 2019-12-27 | 2023-01-30 | 2023-05-29
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WFINSP-SP | CITYWIDE WATERFRONT INSPECTIONS AT VARIOUS WPCPS | 3 | FINAL DESIGN | 2019-12-28 | 2020-06-24 | 2023-05-30 | 2023-11-25
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WFINSP-SP | CITYWIDE WATERFRONT INSPECTIONS AT VARIOUS WPCPS | 4 | BID AWARD AND REGISTER CONTRCT | 2020-06-25 | 2020-09-22 | 2023-11-26 | 2024-02-23
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WFINSP-SP | CITYWIDE WATERFRONT INSPECTIONS AT VARIOUS WPCPS | 5 | CONSTRUCTION TO 25% | 2020-09-23 | 2021-01-20 | 2024-02-24 | 2024-06-22
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WFINSP-SP | CITYWIDE WATERFRONT INSPECTIONS AT VARIOUS WPCPS | 6 | CONSTRUCTION TO 50% | 2021-01-21 | 2021-05-20 | 2024-06-23 | 2024-10-20
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WFINSP-SP | CITYWIDE WATERFRONT INSPECTIONS AT VARIOUS WPCPS | 7 | CONSTRUCTION TO 75% | 2021-05-21 | 2021-09-17 | 2024-10-21 | 2025-02-17
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WFINSP-SP | CITYWIDE WATERFRONT INSPECTIONS AT VARIOUS WPCPS | 8 | ORIGINAL EQUIP & FURNISHING | 2021-09-18 | 2021-12-16 | 2025-02-18 | 2025-05-18
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WFINSP-SP | CITYWIDE WATERFRONT INSPECTIONS AT VARIOUS WPCPS | 9 | SUBSTANTIAL COMPLETION | 2021-12-17 | 2022-02-14 | 2025-05-19 | 2025-07-17
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WFINSP-SP | CITYWIDE WATERFRONT INSPECTIONS AT VARIOUS WPCPS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-02-15 | 2022-03-16 | 2025-07-18 | 2025-08-16
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WQMON-ENT | Above ground monitoring stations | 1 | DEVELOP SCOPE | 2011-01-01 | 2011-03-31 | 2018-06-30 | 2019-03-26
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WQMON-ENT | Above ground monitoring stations | 2 | PRELIMINARY DESIGN | 2011-04-01 | 2011-07-29 | 2019-03-27 | 2020-03-20
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WQMON-ENT | Above ground monitoring stations | 3 | FINAL DESIGN | 2011-07-30 | 2012-01-25 | 2020-03-21 | 2021-09-11
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WQMON-ENT | Above ground monitoring stations | 4 | BID AWARD AND REGISTER CONTRCT | 2012-01-26 | 2012-04-24 | 2021-09-12 | 2022-06-08
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WQMON-ENT | Above ground monitoring stations | 5 | CONSTRUCTION TO 25% | 2012-04-25 | 2012-08-22 | 2022-06-09 | 2023-06-03
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WQMON-ENT | Above ground monitoring stations | 6 | CONSTRUCTION TO 50% | 2012-08-23 | 2012-12-20 | 2023-06-04 | 2024-05-28
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WQMON-ENT | Above ground monitoring stations | 7 | CONSTRUCTION TO 75% | 2012-12-21 | 2013-04-19 | 2024-05-29 | 2025-05-23
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WQMON-ENT | Above ground monitoring stations | 8 | ORIGINAL EQUIP & FURNISHING | 2013-04-20 | 2013-07-18 | 2025-05-24 | 2026-02-17
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WQMON-ENT | Above ground monitoring stations | 9 | SUBSTANTIAL COMPLETION | 2013-07-19 | 2013-09-16 | 2026-02-18 | 2026-08-16
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WQMON-ENT | Above ground monitoring stations | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-09-17 | 2013-10-16 | 2026-08-17 | 2026-11-14
20201123 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WWMGT-18 | FAD 18-22 COMMUNITY WASTEWATER MGMT. | 1 | DEVELOP SCOPE | 2019-05-01 | 2029-04-27 | 2019-05-01 | 2029-04-27
20201123 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-366C | COMPOSTING | 1 | DEVELOP SCOPE | 2007-04-01 | 2007-04-30 | 2007-04-01 | 2007-04-30
20201123 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-366C | COMPOSTING | 2 | PRELIMINARY DESIGN | 2007-05-01 | 2007-05-30 | 2007-05-01 | 2007-05-30
20201123 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-366C | COMPOSTING | 3 | FINAL DESIGN | 2007-05-01 | 2007-05-15 | 2007-05-01 | 2007-05-15
20201123 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-366C | COMPOSTING | 4 | BID AWARD AND REGISTER CONTRCT | 2007-05-16 | 2007-06-30 | 2007-05-16 | 2007-06-15
20201123 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-366C | COMPOSTING | 5 | CONSTRUCTION TO 25% | 2007-07-01 | 2009-06-29 | 2007-06-16 | 2009-08-03
20201123 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-366C | COMPOSTING | 6 | CONSTRUCTION TO 50% | 2009-06-30 | 2011-06-29 | 2009-08-04 | 2021-06-30
20201123 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-366C | COMPOSTING | 7 | CONSTRUCTION TO 75% | 2011-06-30 | 2013-06-28 | 2021-07-01 | 2023-08-19
20201123 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-366C | COMPOSTING | 8 | SUBSTANTIAL COMPLETION | 2013-06-29 | 2015-06-28 | 2023-08-20 | 2024-03-06
20201123 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-366C | COMPOSTING | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-06-29 | 2018-06-27 | 2024-03-07 | 2024-09-22
20201123 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-366D | Construct/Reconstruct composting sites Citywide | 1 | DEVELOP SCOPE | 2014-05-30 | 2014-07-13 | 2014-05-30 | 2014-07-13
20201123 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-366D | Construct/Reconstruct composting sites Citywide | 2 | PRELIMINARY DESIGN | 2014-07-14 | 2015-01-09 | 2014-07-14 | 2015-01-09
20201123 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-366D | Construct/Reconstruct composting sites Citywide | 3 | FINAL DESIGN | 2015-01-10 | 2016-01-09 | 2015-01-10 | 2016-01-09
20201123 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-366D | Construct/Reconstruct composting sites Citywide | 4 | BID AWARD AND REGISTER CONTRCT | 2016-01-10 | 2017-01-08 | 2016-01-10 | 2017-01-08
20201123 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-366D | Construct/Reconstruct composting sites Citywide | 5 | CONSTRUCTION TO 25% | 2017-01-09 | 2018-01-08 | 2017-01-09 | 2018-01-08
20201123 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-366D | Construct/Reconstruct composting sites Citywide | 6 | CONSTRUCTION TO 50% | 2018-01-09 | 2019-01-08 | 2018-01-09 | 2019-01-08
20201123 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-366D | Construct/Reconstruct composting sites Citywide | 7 | CONSTRUCTION TO 75% | 2019-01-09 | 2020-01-08 | 2019-01-09 | 2020-01-08
20201123 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-366D | Construct/Reconstruct composting sites Citywide | 8 | SUBSTANTIAL COMPLETION | 2020-01-09 | 2021-01-07 | 2020-01-09 | 2021-01-07
20201123 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-366D | Construct/Reconstruct composting sites Citywide | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-01-08 | 2022-01-07 | 2021-01-08 | 2022-01-07
20201123 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-383T | REPLACEMENT OF HVAC ROOF TOP UNITS CITYWIDE | 1 | DEVELOP SCOPE | 2016-02-01 | 2016-03-16 | 2016-02-01 | 2016-03-16
20201123 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-383T | REPLACEMENT OF HVAC ROOF TOP UNITS CITYWIDE | 2 | PRELIMINARY DESIGN | 2016-03-17 | 2016-10-02 | 2016-03-17 | 2016-10-02
20201123 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-383T | REPLACEMENT OF HVAC ROOF TOP UNITS CITYWIDE | 3 | FINAL DESIGN | 2016-10-03 | 2017-04-20 | 2016-10-03 | 2017-04-20
20201123 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-383T | REPLACEMENT OF HVAC ROOF TOP UNITS CITYWIDE | 4 | BID AWARD AND REGISTER CONTRCT | 2017-04-21 | 2017-11-06 | 2017-04-21 | 2017-11-06
20201123 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-383T | REPLACEMENT OF HVAC ROOF TOP UNITS CITYWIDE | 5 | CONSTRUCTION TO 25% | 2017-11-07 | 2018-09-02 | 2017-11-07 | 2018-09-02
20201123 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-383T | REPLACEMENT OF HVAC ROOF TOP UNITS CITYWIDE | 6 | CONSTRUCTION TO 50% | 2018-09-03 | 2019-06-29 | 2018-09-03 | 2019-06-29
20201123 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-383T | REPLACEMENT OF HVAC ROOF TOP UNITS CITYWIDE | 7 | CONSTRUCTION TO 75% | 2019-06-30 | 2020-04-24 | 2019-06-30 | 2020-04-24
20201123 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-383T | REPLACEMENT OF HVAC ROOF TOP UNITS CITYWIDE | 8 | SUBSTANTIAL COMPLETION | 2020-04-25 | 2023-01-19 | 2020-04-25 | 2023-01-19
20201123 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-383T | REPLACEMENT OF HVAC ROOF TOP UNITS CITYWIDE | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-01-20 | 2023-05-19 | 2023-01-20 | 2023-05-19
20201123 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-439 | DSNY FACILITY REHAB, CITYWIDE | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-09-28 | 2016-07-01 | 2016-09-28
20201123 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-439 | DSNY FACILITY REHAB, CITYWIDE | 2 | PRELIMINARY DESIGN | 2016-09-29 | 2016-09-28 | 2016-09-29 | 2016-09-28
20201123 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-439 | DSNY FACILITY REHAB, CITYWIDE | 3 | FINAL DESIGN | 2016-12-27 | 2017-04-25 | 2016-12-27 | 2017-04-25
20201123 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-439 | DSNY FACILITY REHAB, CITYWIDE | 4 | BID AWARD AND REGISTER CONTRCT | 2017-04-25 | 2018-04-24 | 2017-04-25 | 2018-04-24
20201123 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-439 | DSNY FACILITY REHAB, CITYWIDE | 5 | CONSTRUCTION TO 25% | 2018-04-25 | 2019-04-24 | 2018-04-25 | 2019-04-24
20201123 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-439 | DSNY FACILITY REHAB, CITYWIDE | 6 | CONSTRUCTION TO 50% | 2019-04-25 | 2020-04-23 | 2019-04-25 | 2020-04-23
20201123 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-439 | DSNY FACILITY REHAB, CITYWIDE | 7 | CONSTRUCTION TO 75% | 2020-04-25 | 2021-04-24 | 2020-04-25 | 2021-04-24
20201123 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-439 | DSNY FACILITY REHAB, CITYWIDE | 8 | SUBSTANTIAL COMPLETION | 2021-04-25 | 2023-07-03 | 2021-04-25 | 2023-07-03
20201123 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-439 | DSNY FACILITY REHAB, CITYWIDE | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-07-04 | 2025-02-22 | 2023-07-04 | 2025-02-22
20201123 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-440 | Sidewalks at DSNY Facilities, Citywide | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-08-29 | 2017-07-01 | 2017-08-29
20201123 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-440 | Sidewalks at DSNY Facilities, Citywide | 2 | PRELIMINARY DESIGN | 2017-08-30 | 2017-11-27 | 2017-08-30 | 2017-11-27
20201123 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-440 | Sidewalks at DSNY Facilities, Citywide | 3 | FINAL DESIGN | 2017-11-28 | 2018-02-25 | 2017-11-28 | 2018-02-25
20201123 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-440 | Sidewalks at DSNY Facilities, Citywide | 4 | BID AWARD AND REGISTER CONTRCT | 2018-02-26 | 2018-05-26 | 2018-02-26 | 2018-05-26
20201123 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-440 | Sidewalks at DSNY Facilities, Citywide | 5 | CONSTRUCTION TO 25% | 2018-05-27 | 2019-01-21 | 2018-05-27 | 2019-01-21
20201123 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-440 | Sidewalks at DSNY Facilities, Citywide | 6 | CONSTRUCTION TO 50% | 2019-01-22 | 2019-09-18 | 2019-01-22 | 2019-09-18
20201123 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-440 | Sidewalks at DSNY Facilities, Citywide | 7 | CONSTRUCTION TO 75% | 2019-09-19 | 2020-05-15 | 2019-09-19 | 2020-05-15
20201123 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-440 | Sidewalks at DSNY Facilities, Citywide | 8 | SUBSTANTIAL COMPLETION | 2020-05-16 | 2022-01-05 | 2020-05-16 | 2022-01-05
20201123 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-440 | Sidewalks at DSNY Facilities, Citywide | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-01-06 | 2024-06-23 | 2022-01-06 | 2024-06-23
20201123 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S216-235 | PIER WORK -- CITYWIDE | 1 | DEVELOP SCOPE | 1998-07-01 | 1998-08-14 | 1998-07-01 | 1998-08-14
20201123 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S216-235 | PIER WORK -- CITYWIDE | 2 | PRELIMINARY DESIGN | 1998-08-15 | 1999-02-10 | 1998-08-15 | 1999-02-10
20201123 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S216-235 | PIER WORK -- CITYWIDE | 3 | FINAL DESIGN | 1999-02-11 | 1999-08-09 | 1999-02-11 | 1999-08-09
20201123 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S216-235 | PIER WORK -- CITYWIDE | 4 | BID AWARD AND REGISTER CONTRCT | 1999-08-10 | 2000-02-05 | 1999-08-10 | 2000-02-05
20201123 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S216-235 | PIER WORK -- CITYWIDE | 5 | CONSTRUCTION TO 25% | 2000-02-06 | 2001-09-02 | 2000-02-06 | 2001-09-02
20201123 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S216-235 | PIER WORK -- CITYWIDE | 6 | CONSTRUCTION TO 50% | 2001-09-03 | 2003-03-31 | 2001-09-03 | 2003-03-31
20201123 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S216-235 | PIER WORK -- CITYWIDE | 7 | CONSTRUCTION TO 75% | 2003-04-01 | 2004-10-26 | 2003-04-01 | 2004-10-26
20201123 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S216-235 | PIER WORK -- CITYWIDE | 8 | SUBSTANTIAL COMPLETION | 2004-10-27 | 2006-05-24 | 2004-10-27 | 2006-05-24
20201123 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S216-235 | PIER WORK -- CITYWIDE | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2006-05-25 | 2007-12-20 | 2006-12-11 | 2029-06-30
20201123 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | SANDMTSAP | MTS HAZARD MITIGATION ALTERNATE PROJECT- SANDY RELATED WORK | 1 | DEVELOP SCOPE | 2017-07-31 | 2018-05-06 | 2017-07-31 | 2018-05-06
20201123 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | SANDMTSAP | MTS HAZARD MITIGATION ALTERNATE PROJECT- SANDY RELATED WORK | 2 | PRELIMINARY DESIGN | 2018-05-07 | 2019-02-10 | 2018-05-07 | 2019-02-10
20201123 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | SANDMTSAP | MTS HAZARD MITIGATION ALTERNATE PROJECT- SANDY RELATED WORK | 3 | FINAL DESIGN | 2019-02-11 | 2019-11-17 | 2019-02-11 | 2019-11-17
20201123 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | SANDMTSAP | MTS HAZARD MITIGATION ALTERNATE PROJECT- SANDY RELATED WORK | 4 | BID AWARD AND REGISTER CONTRCT | 2019-11-18 | 2020-11-16 | 2019-11-18 | 2020-11-16
20201123 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | SANDMTSAP | MTS HAZARD MITIGATION ALTERNATE PROJECT- SANDY RELATED WORK | 5 | CONSTRUCTION TO 25% | 2020-11-17 | 2021-11-16 | 2020-11-17 | 2021-11-16
20201123 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | SANDMTSAP | MTS HAZARD MITIGATION ALTERNATE PROJECT- SANDY RELATED WORK | 6 | CONSTRUCTION TO 50% | 2021-11-17 | 2023-02-09 | 2021-11-17 | 2023-02-09
20201123 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | SANDMTSAP | MTS HAZARD MITIGATION ALTERNATE PROJECT- SANDY RELATED WORK | 7 | CONSTRUCTION TO 75% | 2023-02-10 | 2024-05-04 | 2023-02-10 | 2024-05-04
20201123 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | SANDMTSAP | MTS HAZARD MITIGATION ALTERNATE PROJECT- SANDY RELATED WORK | 8 | SUBSTANTIAL COMPLETION | 2024-05-05 | 2025-12-25 | 2024-05-05 | 2025-12-25
20201123 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | SANDMTSAP | MTS HAZARD MITIGATION ALTERNATE PROJECT- SANDY RELATED WORK | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-12-26 | 2028-09-20 | 2025-12-26 | 2028-09-20
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT503 | DOT Replacement of Streetlight Fixtures to LED,Manh,BX,SI | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-09-28 | 2023-06-30 | 2023-09-27
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT503 | DOT Replacement of Streetlight Fixtures to LED,Manh,BX,SI | 2 | PRELIMINARY DESIGN | 2016-09-29 | 2017-01-26 | 2023-09-28 | 2024-01-25
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT503 | DOT Replacement of Streetlight Fixtures to LED,Manh,BX,SI | 3 | FINAL DESIGN | 2017-01-27 | 2017-07-25 | 2024-01-26 | 2024-07-23
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT503 | DOT Replacement of Streetlight Fixtures to LED,Manh,BX,SI | 4 | BID AWARD AND REGISTER CONTRCT | 2017-07-26 | 2017-10-23 | 2024-07-24 | 2024-10-21
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT503 | DOT Replacement of Streetlight Fixtures to LED,Manh,BX,SI | 5 | CONSTRUCTION TO 25% | 2017-10-24 | 2018-02-20 | 2024-10-22 | 2025-02-18
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT503 | DOT Replacement of Streetlight Fixtures to LED,Manh,BX,SI | 6 | CONSTRUCTION TO 50% | 2018-02-21 | 2018-06-20 | 2025-02-19 | 2025-06-18
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT503 | DOT Replacement of Streetlight Fixtures to LED,Manh,BX,SI | 7 | CONSTRUCTION TO 75% | 2018-06-21 | 2018-10-18 | 2025-06-19 | 2025-10-16
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT503 | DOT Replacement of Streetlight Fixtures to LED,Manh,BX,SI | 8 | ORIGINAL EQUIP & FURNISHING | 2018-10-19 | 2019-01-16 | 2025-10-17 | 2026-01-14
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT503 | DOT Replacement of Streetlight Fixtures to LED,Manh,BX,SI | 9 | SUBSTANTIAL COMPLETION | 2019-01-17 | 2019-03-17 | 2026-01-15 | 2027-11-15
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT503 | DOT Replacement of Streetlight Fixtures to LED,Manh,BX,SI | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-03-18 | 2019-04-16 | 2024-03-16 | 2024-04-14
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BIKE2030 | BIKE NETWORK DEVELOPMENT 2030 | 1 | BID AWARD AND REGISTER CONTRCT | 2008-06-30 | 2008-06-30 | 2011-06-30 | 2011-06-30
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BIKE2030 | BIKE NETWORK DEVELOPMENT 2030 | 2 | CONSTRUCTION START | 2008-07-01 | 2008-08-14 | 2011-07-01 | 2011-08-14
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BIKE2030 | BIKE NETWORK DEVELOPMENT 2030 | 3 | CONSTRUCTION COMPLETION | 2008-08-15 | 2010-03-07 | 2011-08-15 | 2030-06-30
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BR10YR15 | Waterway Bridges Ten Year Plan | 1 | DEVELOP SCOPE | 2019-06-30 | 2020-06-28 | 2019-06-30 | 2020-06-28
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BR10YR15 | Waterway Bridges Ten Year Plan | 2 | DESIGN START | 2020-06-29 | 2024-06-27 | 2020-06-29 | 2024-06-27
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BR10YR15 | Waterway Bridges Ten Year Plan | 3 | CONSTRUCTION START | 2024-06-28 | 2026-06-27 | 2024-06-28 | 2026-06-27
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BRC156F | MANHATTAN BRIDGE #15 | 1 | DEVELOP SCOPE | 2014-06-30 | 2015-06-29 | 2012-03-01 | 2012-05-02
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BRC156F | MANHATTAN BRIDGE #15 | 2 | DESIGN START | 2015-06-30 | 2019-06-28 | 2014-09-04 | 2017-03-10
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BRC156F | MANHATTAN BRIDGE #15 | 3 | CONSTRUCTION START | 2019-06-29 | 2021-06-27 | 2018-10-15 | 2021-10-23
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BRC231F | QUEENSBORO BRIDGE #10 OVER EAST RIVER | 1 | DEVELOP SCOPE | 2015-06-30 | 2016-06-28 | 2018-04-25 | 2018-04-25
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BRC231F | QUEENSBORO BRIDGE #10 OVER EAST RIVER | 2 | DESIGN START | 2016-06-29 | 2020-06-27 | 2016-04-01 | 2021-01-21
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BRC231F | QUEENSBORO BRIDGE #10 OVER EAST RIVER | 3 | CONSTRUCTION START | 2020-06-28 | 2022-06-27 | 2018-07-09 | 2023-06-30
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BRC253D | WILLIAMSBURG BRIDGE MISC REPAIRS AND PAINTING FY20 | 1 | DEVELOP SCOPE | 2016-07-01 | 2017-06-30 | 2016-08-22 | 2016-08-22
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BRC253D | WILLIAMSBURG BRIDGE MISC REPAIRS AND PAINTING FY20 | 2 | DESIGN START | 2017-07-01 | 2021-06-29 | 2018-08-15 | 2020-05-29
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BRC253D | WILLIAMSBURG BRIDGE MISC REPAIRS AND PAINTING FY20 | 3 | CONSTRUCTION START | 2021-06-30 | 2023-06-29 | 2022-07-05 | 2025-07-04
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BRC270D | BROOKLYN BRIDGE REHABILITATION OF APPOACH ARCHES FY19 | 1 | DEVELOP SCOPE | 2019-06-30 | 2020-06-28 | 2015-05-05 | 2015-07-06
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BRC270D | BROOKLYN BRIDGE REHABILITATION OF APPOACH ARCHES FY19 | 2 | DESIGN START | 2020-06-29 | 2024-06-27 | 2016-04-20 | 2018-08-03
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BRC270D | BROOKLYN BRIDGE REHABILITATION OF APPOACH ARCHES FY19 | 3 | CONSTRUCTION START | 2024-06-28 | 2026-06-27 | 2019-09-09 | 2023-03-12
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BRCHAZMIG | HAZARD MITIGATION (EAST RIVER BRIDGES - CITYWIDE) | 1 | DEVELOP SCOPE | 2009-07-01 | 2010-06-30 | 2018-06-30 | 2019-06-29
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BRCHAZMIG | HAZARD MITIGATION (EAST RIVER BRIDGES - CITYWIDE) | 2 | DESIGN START | 2010-07-01 | 2014-06-29 | 2019-06-30 | 2023-06-28
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BRCHAZMIG | HAZARD MITIGATION (EAST RIVER BRIDGES - CITYWIDE) | 3 | CONSTRUCTION START | 2014-06-30 | 2016-06-28 | 2023-06-29 | 2025-06-27
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BRKA24039 | GRAND STREET/ NEWTON CREEK BIN: 2240390 | 1 | DEVELOP SCOPE | 2018-06-30 | 2018-09-27 | 2018-02-27 | 2018-03-02
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BRKA24039 | GRAND STREET/ NEWTON CREEK BIN: 2240390 | 2 | PRELIMINARY DESIGN | 2018-09-28 | 2019-01-25 | 2019-07-15 | 2021-10-23
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BRKA24039 | GRAND STREET/ NEWTON CREEK BIN: 2240390 | 3 | FINAL DESIGN | 2019-01-26 | 2019-07-24 | 2021-10-24 | 2023-08-15
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BRKA24039 | GRAND STREET/ NEWTON CREEK BIN: 2240390 | 4 | BID AWARD AND REGISTER CONTRCT | 2019-07-25 | 2019-10-22 | 2023-07-16 | 2024-03-05
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BRKA24039 | GRAND STREET/ NEWTON CREEK BIN: 2240390 | 5 | CONSTRUCTION TO 25% | 2019-10-23 | 2020-02-19 | 2024-04-05 | 2025-01-24
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BRKA24039 | GRAND STREET/ NEWTON CREEK BIN: 2240390 | 6 | CONSTRUCTION TO 50% | 2020-02-20 | 2020-06-18 | 2025-01-24 | 2025-11-03
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BRKA24039 | GRAND STREET/ NEWTON CREEK BIN: 2240390 | 7 | CONSTRUCTION TO 75% | 2020-06-19 | 2020-10-16 | 2025-11-03 | 2026-08-14
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BRKA24039 | GRAND STREET/ NEWTON CREEK BIN: 2240390 | 8 | ORIGINAL EQUIP & FURNISHING | 2020-10-17 | 2021-01-14 | 2026-08-15 | 2026-11-12
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BRKA24039 | GRAND STREET/ NEWTON CREEK BIN: 2240390 | 9 | SUBSTANTIAL COMPLETION | 2021-01-15 | 2021-03-15 | 2027-09-14 | 2027-09-14
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BRKA24039 | GRAND STREET/ NEWTON CREEK BIN: 2240390 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-16 | 2021-04-14 | 2027-09-14 | 2027-12-13
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BRX287BS | Macombs Dam Bridge- Bus Stop | 1 | DEVELOP SCOPE | 2018-06-30 | 2019-06-29 | 2021-06-30 | 2023-01-09
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BRX287BS | Macombs Dam Bridge- Bus Stop | 2 | DESIGN START | 2019-06-30 | 2023-06-28 | 2018-02-16 | 2020-01-09
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BRX287BS | Macombs Dam Bridge- Bus Stop | 3 | CONSTRUCTION START | 2023-06-29 | 2025-06-27 | 2020-08-09 | 2025-10-22
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BRX287S | MACOMBS DAM BRIDGE - REHAB OF FENDER SYSTEM & 155TH VIA | 1 | DEVELOP SCOPE | 2009-07-01 | 2010-06-30 | 2017-06-29 | 2017-06-30
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BRX287S | MACOMBS DAM BRIDGE - REHAB OF FENDER SYSTEM & 155TH VIA | 2 | DESIGN START | 2010-07-01 | 2014-06-29 | 2017-07-01 | 2018-06-29
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BRX287S | MACOMBS DAM BRIDGE - REHAB OF FENDER SYSTEM & 155TH VIA | 3 | CONSTRUCTION START | 2014-06-30 | 2016-06-28 | 2018-06-30 | 2019-06-28
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BUS2030 | BUS INITIATIVES | 1 | BID AWARD AND REGISTER CONTRCT | 2008-06-30 | 2008-06-30 | 2023-06-30 | 2023-06-30
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BUS2030 | BUS INITIATIVES | 2 | CONSTRUCTION START | 2008-07-01 | 2008-08-14 | 2023-07-01 | 2023-08-14
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BUS2030 | BUS INITIATIVES | 3 | CONSTRUCTION COMPLETION | 2008-08-15 | 2010-03-07 | 2023-08-15 | 2028-06-29
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | C5447 | MISCELLANEOUS UPGRADES TO FERRYBOATS | 1 | DEVELOP SCOPE | 2008-06-30 | 2009-06-29 | 2017-06-30 | 2018-06-29
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | C5447 | MISCELLANEOUS UPGRADES TO FERRYBOATS | 2 | DESIGN START | 2009-06-30 | 2011-06-29 | 2018-06-30 | 2020-06-28
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | C5447 | MISCELLANEOUS UPGRADES TO FERRYBOATS | 3 | CONSTRUCTION START | 2011-06-30 | 2013-06-28 | 2020-06-29 | 2022-06-28
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | C5586 | REPLACEMENT OF COSGROVE FERRY BOAT | 1 | DEVELOP SCOPE | 2006-07-01 | 2007-06-30 | 2024-07-01 | 2025-06-30
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | C5586 | REPLACEMENT OF COSGROVE FERRY BOAT | 2 | DESIGN START | 2007-07-01 | 2009-06-29 | 2025-07-01 | 2027-06-30
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | C5586 | REPLACEMENT OF COSGROVE FERRY BOAT | 3 | CONSTRUCTION START | 2009-06-30 | 2011-06-29 | 2027-07-01 | 2029-06-29
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | C5589AUS | DRYDOCK AUSTEN CLASS FERRY BOATS | 1 | DEVELOP SCOPE | 2011-06-30 | 2012-06-28 | 2018-06-30 | 2019-06-29
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | C5589AUS | DRYDOCK AUSTEN CLASS FERRY BOATS | 2 | DESIGN START | 2012-06-29 | 2014-06-28 | 2019-06-30 | 2021-06-28
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | C5589AUS | DRYDOCK AUSTEN CLASS FERRY BOATS | 3 | CONSTRUCTION START | 2014-06-29 | 2016-06-27 | 2021-06-29 | 2023-06-28
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | C5BARBERI | RECON & DRYDOCKING OF BARBERI CLASS FERRY BOATS | 1 | DEVELOP SCOPE | 2010-06-30 | 2011-06-29 | 2013-06-30 | 2014-06-29
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | C5BARBERI | RECON & DRYDOCKING OF BARBERI CLASS FERRY BOATS | 2 | DESIGN START | 2011-06-30 | 2013-06-28 | 2014-06-30 | 2016-06-28
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | C5BARBERI | RECON & DRYDOCKING OF BARBERI CLASS FERRY BOATS | 3 | CONSTRUCTION START | 2013-06-29 | 2015-06-28 | 2016-06-29 | 2023-06-29
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | CONG2030 | CONGESTED CORRIDORS/ GROWTH AREAS | 1 | BID AWARD AND REGISTER CONTRCT | 2008-06-30 | 2008-06-30 | 2009-06-30 | 2009-06-30
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | CONG2030 | CONGESTED CORRIDORS/ GROWTH AREAS | 2 | CONSTRUCTION START | 2008-07-01 | 2008-08-14 | 2009-07-01 | 2009-08-14
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | CONG2030 | CONGESTED CORRIDORS/ GROWTH AREAS | 3 | CONSTRUCTION COMPLETION | 2008-08-15 | 2010-03-07 | 2009-08-15 | 2028-06-30
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | DECKSCRPL | Deck Scows Replacement | 1 | DEVELOP SCOPE | 2016-06-30 | 2017-06-29 | 2016-06-30 | 2017-06-29
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | DECKSCRPL | Deck Scows Replacement | 2 | DESIGN START | 2017-06-30 | 2019-06-29 | 2017-06-30 | 2019-06-29
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | DECKSCRPL | Deck Scows Replacement | 3 | CONSTRUCTION START | 2019-06-30 | 2021-06-28 | 2019-06-30 | 2026-06-30
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | FACLUMP | LUMP SUM FOR FACILITIES | 1 | DEVELOP SCOPE | 2010-06-01 | 2011-05-31 | 0 | 0
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | FACLUMP | LUMP SUM FOR FACILITIES | 2 | DESIGN START | 2011-06-01 | 2015-05-30 | 2022-06-01 | 2023-05-31
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | FACLUMP | LUMP SUM FOR FACILITIES | 3 | CONSTRUCTION START | 2015-05-31 | 2017-05-29 | 2023-06-01 | 2027-05-30
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | FACLUMP | LUMP SUM FOR FACILITIES | 5 | CONSTRUCTION START | 2015-05-31 | 2017-05-29 | 2027-05-31 | 2029-05-29
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | FARRSLIP | Arrestors for all slips | 1 | DEVELOP SCOPE | 2016-06-30 | 2017-06-29 | 2023-06-07 | 2023-11-30
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | FARRSLIP | Arrestors for all slips | 2 | DESIGN START | 2017-06-30 | 2019-06-29 | 2023-12-01 | 2025-11-29
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | FARRSLIP | Arrestors for all slips | 3 | CONSTRUCTION START | 2019-06-30 | 2021-06-28 | 2025-11-30 | 2029-11-29
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | FATERMTBC | STG & WHT Ferry Terminals Transfer Bridge Control Update | 1 | DEVELOP SCOPE | 2022-06-30 | 2023-06-29 | 2019-06-30 | 2020-06-28
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | FATERMTBC | STG & WHT Ferry Terminals Transfer Bridge Control Update | 2 | DESIGN START | 2023-06-30 | 2025-06-28 | 2020-06-29 | 2022-06-28
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | FATERMTBC | STG & WHT Ferry Terminals Transfer Bridge Control Update | 3 | CONSTRUCTION START | 2025-06-29 | 2027-06-28 | 2022-06-29 | 2024-06-27
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | FAVEHBARP | Vehicle Barrier Replacement Upgrade | 1 | DEVELOP SCOPE | 2022-06-30 | 2023-06-29 | 2022-06-30 | 2023-06-29
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | FAVEHBARP | Vehicle Barrier Replacement Upgrade | 2 | DESIGN START | 2023-06-30 | 2025-06-28 | 2023-06-30 | 2025-06-28
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | FAVEHBARP | Vehicle Barrier Replacement Upgrade | 3 | CONSTRUCTION START | 2025-06-29 | 2027-06-28 | 2025-06-29 | 2027-06-28
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | FAVESSPC | Ferry Terminals Vessel Passenger Counters | 1 | DEVELOP SCOPE | 2017-06-30 | 2018-06-29 | 2017-06-30 | 2018-06-29
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | FAVESSPC | Ferry Terminals Vessel Passenger Counters | 2 | DESIGN START | 2018-06-30 | 2020-06-28 | 2018-06-30 | 2020-06-28
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | FAVESSPC | Ferry Terminals Vessel Passenger Counters | 3 | CONSTRUCTION START | 2020-06-29 | 2022-06-28 | 2020-06-29 | 2022-06-28
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | GEAN-2013 | STREET LIGHTING ANNUAL CONSTRUCTION-FY14 | 1 | BID AWARD AND REGISTER CONTRCT | 2013-06-30 | 2013-06-30 | 2022-06-30 | 2022-06-30
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | GEAN-2013 | STREET LIGHTING ANNUAL CONSTRUCTION-FY14 | 2 | CONSTRUCTION START | 2013-07-01 | 2013-08-14 | 2022-07-01 | 2022-08-14
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | GEAN-2013 | STREET LIGHTING ANNUAL CONSTRUCTION-FY14 | 3 | CONSTRUCTION COMPLETION | 2013-08-15 | 2015-03-07 | 2022-08-15 | 2024-03-06
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | GEAN2017 | STREET LIGHTING ANNUAL CONSTRUCTION -FY17 | 1 | BID AWARD AND REGISTER CONTRCT | 2017-06-30 | 2017-06-30 | 2022-06-30 | 2022-06-30
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | GEAN2017 | STREET LIGHTING ANNUAL CONSTRUCTION -FY17 | 2 | CONSTRUCTION START | 2017-07-01 | 2017-08-14 | 2022-07-01 | 2022-08-14
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | GEAN2017 | STREET LIGHTING ANNUAL CONSTRUCTION -FY17 | 3 | CONSTRUCTION COMPLETION | 2017-08-15 | 2019-03-07 | 2022-08-15 | 2024-03-06
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | GEAN2019 | STREET LIGHTING ANNUAL CONSTRUCTION 2019 | 1 | BID AWARD AND REGISTER CONTRCT | 2018-06-30 | 2018-06-30 | 2021-06-30 | 2021-06-30
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | GEAN2019 | STREET LIGHTING ANNUAL CONSTRUCTION 2019 | 2 | CONSTRUCTION START | 2018-07-01 | 2018-08-14 | 2021-07-01 | 2021-08-14
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | GEAN2019 | STREET LIGHTING ANNUAL CONSTRUCTION 2019 | 3 | CONSTRUCTION COMPLETION | 2018-08-15 | 2020-03-06 | 2021-08-15 | 2022-03-07
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | GEHD-2013 | HIGHWAY & PARK DISTRIBUTION FY14 | 1 | BID AWARD AND REGISTER CONTRCT | 2013-06-30 | 2013-06-30 | 2022-06-30 | 2022-06-30
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | GEHD-2013 | HIGHWAY & PARK DISTRIBUTION FY14 | 2 | CONSTRUCTION START | 2013-07-01 | 2013-08-14 | 2022-07-01 | 2022-08-14
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | GEHD-2013 | HIGHWAY & PARK DISTRIBUTION FY14 | 3 | CONSTRUCTION COMPLETION | 2013-08-15 | 2015-03-07 | 2022-08-15 | 2024-03-06
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | GEHD2017 | HIGHWAYS & PARKS DISTRIBUTION -FY17 | 1 | BID AWARD AND REGISTER CONTRCT | 2015-06-30 | 2015-06-30 | 2022-06-30 | 2022-06-30
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | GEHD2017 | HIGHWAYS & PARKS DISTRIBUTION -FY17 | 2 | CONSTRUCTION START | 2015-07-01 | 2015-08-14 | 2022-07-01 | 2022-08-14
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | GEHD2017 | HIGHWAYS & PARKS DISTRIBUTION -FY17 | 3 | CONSTRUCTION COMPLETION | 2015-08-15 | 2017-03-06 | 2022-08-15 | 2024-03-06
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HB1014GP | Build-Out Cost for Greenpoint Yard New Trailers | 1 | DEVELOP SCOPE | 2020-06-30 | 2020-07-01 | 0 | 0
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HB1014GP | Build-Out Cost for Greenpoint Yard New Trailers | 2 | DESIGN START | 2020-07-02 | 2021-01-01 | 2020-06-30 | 2020-07-01
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HB1014GP | Build-Out Cost for Greenpoint Yard New Trailers | 3 | CONSTRUCTION START | 2021-01-02 | 2021-06-30 | 2020-07-02 | 2021-01-01
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HB1014GP | Build-Out Cost for Greenpoint Yard New Trailers | 5 | CONSTRUCTION START | 2021-01-02 | 2021-06-30 | 2021-01-02 | 2021-06-30
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HB1070ST | PROTECTIVE COATING OF VARIOUS BRIDGES IN STATEN ISLAND | 1 | DEVELOP SCOPE | 2018-06-30 | 2019-06-29 | 0 | 0
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HB1070ST | PROTECTIVE COATING OF VARIOUS BRIDGES IN STATEN ISLAND | 2 | DESIGN START | 2019-06-30 | 2023-06-28 | 2018-06-30 | 2019-06-29
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HB1070ST | PROTECTIVE COATING OF VARIOUS BRIDGES IN STATEN ISLAND | 3 | CONSTRUCTION START | 2023-06-29 | 2025-06-27 | 2019-06-30 | 2023-06-28
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HB1070ST | PROTECTIVE COATING OF VARIOUS BRIDGES IN STATEN ISLAND | 5 | CONSTRUCTION START | 2023-06-29 | 2025-06-27 | 2023-06-29 | 2025-06-27
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HB-BIDSAD | ADVERTISEMENT FOR CAPITAL BRIDGE PROJECTS | 1 | DEVELOP SCOPE | 2008-06-30 | 2009-06-29 | 0 | 0
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HB-BIDSAD | ADVERTISEMENT FOR CAPITAL BRIDGE PROJECTS | 2 | DESIGN START | 2009-06-30 | 2013-06-28 | 2017-06-30 | 2018-06-29
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HB-BIDSAD | ADVERTISEMENT FOR CAPITAL BRIDGE PROJECTS | 3 | CONSTRUCTION START | 2013-06-29 | 2015-06-28 | 2018-06-30 | 2022-06-28
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HB-BIDSAD | ADVERTISEMENT FOR CAPITAL BRIDGE PROJECTS | 5 | CONSTRUCTION START | 2013-06-29 | 2015-06-28 | 2022-06-29 | 2024-06-27
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBC1070 | BRIDGE PROTECTIVE COATING | 1 | DEVELOP SCOPE | 2012-06-30 | 2013-06-29 | 0 | 0
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBC1070 | BRIDGE PROTECTIVE COATING | 2 | DESIGN START | 2013-06-30 | 2017-06-28 | 2018-06-30 | 2019-06-29
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBC1070 | BRIDGE PROTECTIVE COATING | 3 | CONSTRUCTION START | 2017-06-29 | 2019-06-28 | 2019-06-30 | 2023-06-28
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBC1070 | BRIDGE PROTECTIVE COATING | 5 | CONSTRUCTION START | 2017-06-29 | 2019-06-28 | 2023-06-29 | 2025-06-27
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBC10YR20 | BRIDGE 10 YEAR PLAN FY 2020 | 1 | DEVELOP SCOPE | 2014-06-30 | 2015-06-29 | 0 | 0
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBC10YR20 | BRIDGE 10 YEAR PLAN FY 2020 | 2 | DESIGN START | 2015-06-30 | 2019-06-28 | 2016-06-30 | 2017-06-29
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBC10YR20 | BRIDGE 10 YEAR PLAN FY 2020 | 3 | CONSTRUCTION START | 2019-06-29 | 2021-06-27 | 2017-06-30 | 2021-06-28
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBC10YR20 | BRIDGE 10 YEAR PLAN FY 2020 | 5 | CONSTRUCTION START | 2019-06-29 | 2021-06-27 | 2021-06-29 | 2023-06-28
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD0011A | IN-PROCESS FAB INSPECTION STRUCTURAL STEEL IN NE USA | 1 | DEVELOP SCOPE | 2018-06-01 | 2019-05-31 | 0 | 0
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD0011A | IN-PROCESS FAB INSPECTION STRUCTURAL STEEL IN NE USA | 2 | DESIGN START | 2019-06-01 | 2023-05-30 | 2018-06-01 | 2019-05-31
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD0011A | IN-PROCESS FAB INSPECTION STRUCTURAL STEEL IN NE USA | 3 | CONSTRUCTION START | 2023-05-31 | 2025-05-29 | 2019-06-01 | 2023-05-30
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD0011A | IN-PROCESS FAB INSPECTION STRUCTURAL STEEL IN NE USA | 5 | CONSTRUCTION START | 2023-05-31 | 2025-05-29 | 2023-05-31 | 2025-05-29
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD0011B | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN US/CAN | 1 | DEVELOP SCOPE | 2018-06-01 | 2019-05-31 | 0 | 0
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD0011B | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN US/CAN | 2 | DESIGN START | 2019-06-01 | 2023-05-30 | 2018-06-01 | 2019-05-31
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD0011B | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN US/CAN | 3 | CONSTRUCTION START | 2023-05-31 | 2025-05-29 | 2019-06-01 | 2023-05-30
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD0011B | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN US/CAN | 5 | CONSTRUCTION START | 2023-05-31 | 2025-05-29 | 2023-05-31 | 2025-05-29
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD0011C | IN-PROCESS FAB INSPECTION OF PP CONCRETE IN NE USA | 1 | DEVELOP SCOPE | 2018-06-01 | 2019-05-31 | 0 | 0
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD0011C | IN-PROCESS FAB INSPECTION OF PP CONCRETE IN NE USA | 2 | DESIGN START | 2019-06-01 | 2023-05-30 | 2018-05-02 | 2018-10-26
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD0011C | IN-PROCESS FAB INSPECTION OF PP CONCRETE IN NE USA | 3 | CONSTRUCTION START | 2023-05-31 | 2025-05-29 | 2018-10-27 | 2020-05-09
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD0011C | IN-PROCESS FAB INSPECTION OF PP CONCRETE IN NE USA | 5 | CONSTRUCTION START | 2023-05-31 | 2025-05-29 | 2020-05-10 | 2022-05-09
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD0012 | TESTING AND SAMPLING OF MATERIAL (CITYWIDE) | 1 | DEVELOP SCOPE | 2019-06-01 | 2020-05-30 | 0 | 0
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD0012 | TESTING AND SAMPLING OF MATERIAL (CITYWIDE) | 2 | DESIGN START | 2020-05-31 | 2024-05-29 | 2018-05-02 | 2019-09-05
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD0012 | TESTING AND SAMPLING OF MATERIAL (CITYWIDE) | 3 | CONSTRUCTION START | 2024-05-30 | 2026-05-29 | 2019-09-06 | 2020-12-05
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD0012 | TESTING AND SAMPLING OF MATERIAL (CITYWIDE) | 5 | CONSTRUCTION START | 2024-05-30 | 2026-05-29 | 2020-12-06 | 2022-12-05
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD006P | Citywide Inspection/Monitoring of Bridge Paint Removal&Appli | 1 | DEVELOP SCOPE | 2019-06-01 | 2020-05-30 | 0 | 0
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD006P | Citywide Inspection/Monitoring of Bridge Paint Removal&Appli | 2 | DESIGN START | 2020-05-31 | 2024-05-29 | 2018-05-02 | 2019-04-18
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD006P | Citywide Inspection/Monitoring of Bridge Paint Removal&Appli | 3 | CONSTRUCTION START | 2024-05-30 | 2026-05-29 | 2019-04-19 | 2020-06-27
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD006P | Citywide Inspection/Monitoring of Bridge Paint Removal&Appli | 5 | CONSTRUCTION START | 2024-05-30 | 2026-05-29 | 2020-06-28 | 2022-04-08
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD007P | Citywide Inspection/Monitoring of Bridge Paint Removal & App | 1 | DEVELOP SCOPE | 2023-07-01 | 2024-06-29 | 0 | 0
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD007P | Citywide Inspection/Monitoring of Bridge Paint Removal & App | 2 | DESIGN START | 2024-06-30 | 2028-06-28 | 2016-05-02 | 2017-04-18
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD007P | Citywide Inspection/Monitoring of Bridge Paint Removal & App | 3 | CONSTRUCTION START | 2028-06-29 | 2030-06-28 | 2017-04-19 | 2017-08-27
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD007P | Citywide Inspection/Monitoring of Bridge Paint Removal & App | 5 | CONSTRUCTION START | 2028-06-29 | 2030-06-28 | 2017-08-28 | 2023-08-26
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD008P | Citywide Inspection/Monitoring of Bridge Paint Removal & App | 1 | DEVELOP SCOPE | 2017-06-30 | 2018-06-29 | 0 | 0
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD008P | Citywide Inspection/Monitoring of Bridge Paint Removal & App | 2 | DESIGN START | 2018-06-30 | 2022-06-28 | 2018-05-02 | 2025-06-29
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD008P | Citywide Inspection/Monitoring of Bridge Paint Removal & App | 3 | CONSTRUCTION START | 2022-06-29 | 2024-06-27 | 2025-06-30 | 2026-08-12
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD008P | Citywide Inspection/Monitoring of Bridge Paint Removal & App | 5 | CONSTRUCTION START | 2022-06-29 | 2024-06-27 | 2026-08-13 | 2027-08-11
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD013 | Inspection Services at Concrete & Asphalt Plants | 1 | DEVELOP SCOPE | 2023-07-01 | 2024-06-29 | 0 | 0
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD013 | Inspection Services at Concrete & Asphalt Plants | 2 | DESIGN START | 2024-06-30 | 2028-06-28 | 2018-05-02 | 2021-05-26
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD013 | Inspection Services at Concrete & Asphalt Plants | 3 | CONSTRUCTION START | 2028-06-29 | 2030-06-28 | 2021-05-27 | 2022-07-03
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD013 | Inspection Services at Concrete & Asphalt Plants | 5 | CONSTRUCTION START | 2028-06-29 | 2030-06-28 | 2022-07-04 | 2024-07-02
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD013A | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN NE US | 1 | DEVELOP SCOPE | 2023-07-01 | 2024-06-29 | 0 | 0
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD013A | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN NE US | 2 | DESIGN START | 2024-06-30 | 2028-06-28 | 2018-05-02 | 2021-05-26
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD013A | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN NE US | 3 | CONSTRUCTION START | 2028-06-29 | 2030-06-28 | 2021-05-27 | 2022-08-26
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD013A | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN NE US | 5 | CONSTRUCTION START | 2028-06-29 | 2030-06-28 | 2022-08-27 | 2024-08-25
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD013B | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN US | 1 | DEVELOP SCOPE | 2023-07-23 | 2024-07-21 | 0 | 0
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD013B | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN US | 2 | DESIGN START | 2024-07-22 | 2028-07-20 | 2016-07-23 | 2017-07-22
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD013B | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN US | 3 | CONSTRUCTION START | 2028-07-21 | 2030-07-20 | 2017-07-23 | 2022-08-26
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD013B | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN US | 5 | CONSTRUCTION START | 2028-07-21 | 2030-07-20 | 2022-08-27 | 2024-08-25
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD013C | IN-PROCESS FAB INSPECTION OF PP CONCRETE IN USA/CAN | 1 | DEVELOP SCOPE | 2023-07-01 | 2024-06-29 | 0 | 0
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD013C | IN-PROCESS FAB INSPECTION OF PP CONCRETE IN USA/CAN | 2 | DESIGN START | 2024-06-30 | 2028-06-28 | 2016-07-01 | 2017-06-30
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD013C | IN-PROCESS FAB INSPECTION OF PP CONCRETE IN USA/CAN | 3 | CONSTRUCTION START | 2028-06-29 | 2030-06-28 | 2017-07-01 | 2022-08-26
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD013C | IN-PROCESS FAB INSPECTION OF PP CONCRETE IN USA/CAN | 5 | CONSTRUCTION START | 2028-06-29 | 2030-06-28 | 2022-08-27 | 2024-08-25
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD014 | Testing and Sampling of Material (Citywide) | 1 | DEVELOP SCOPE | 2024-07-01 | 2025-06-30 | 0 | 0
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD014 | Testing and Sampling of Material (Citywide) | 2 | DESIGN START | 2025-07-01 | 2029-06-29 | 2017-07-01 | 2018-06-30
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD014 | Testing and Sampling of Material (Citywide) | 3 | CONSTRUCTION START | 2029-06-30 | 2031-06-29 | 2018-07-01 | 2023-07-03
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD014 | Testing and Sampling of Material (Citywide) | 5 | CONSTRUCTION START | 2029-06-30 | 2031-06-29 | 2023-07-04 | 2025-07-02
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD015 | INSPECTION SERVICES AT CONCRETE & ASPHALT PLANTS | 1 | DEVELOP SCOPE | 2017-06-30 | 2018-06-29 | 0 | 0
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD015 | INSPECTION SERVICES AT CONCRETE & ASPHALT PLANTS | 2 | DESIGN START | 2018-06-30 | 2022-06-28 | 2020-06-30 | 2021-06-29
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD015 | INSPECTION SERVICES AT CONCRETE & ASPHALT PLANTS | 3 | CONSTRUCTION START | 2022-06-29 | 2024-06-27 | 2021-06-30 | 2026-08-25
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD015 | INSPECTION SERVICES AT CONCRETE & ASPHALT PLANTS | 5 | CONSTRUCTION START | 2022-06-29 | 2024-06-27 | 2026-08-26 | 2027-08-25
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD015A | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN NE USA | 1 | DEVELOP SCOPE | 2025-07-01 | 2026-06-30 | 0 | 0
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD015A | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN NE USA | 2 | DESIGN START | 2026-07-01 | 2030-06-29 | 2025-07-01 | 2026-06-30
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD015A | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN NE USA | 3 | CONSTRUCTION START | 2030-06-30 | 2032-06-28 | 2026-07-01 | 2026-08-25
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD015A | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN NE USA | 5 | CONSTRUCTION START | 2030-06-30 | 2032-06-28 | 2026-08-26 | 2028-08-24
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD015B | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN US/CAN | 1 | DEVELOP SCOPE | 2025-07-01 | 2026-06-30 | 0 | 0
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD015B | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN US/CAN | 2 | DESIGN START | 2026-07-01 | 2030-06-29 | 2025-07-01 | 2025-07-01
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD015B | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN US/CAN | 3 | CONSTRUCTION START | 2030-06-30 | 2032-06-28 | 2025-07-02 | 2025-07-02
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD015B | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN US/CAN | 5 | CONSTRUCTION START | 2030-06-30 | 2032-06-28 | 2025-07-03 | 2027-07-02
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD015C | IN-PROCESS FAB INSPECTION OF PP CONCRETE IN USA/CAN | 1 | DEVELOP SCOPE | 2015-06-30 | 2016-06-28 | 0 | 0
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD015C | IN-PROCESS FAB INSPECTION OF PP CONCRETE IN USA/CAN | 2 | DESIGN START | 2016-06-29 | 2020-06-27 | 2011-06-30 | 2012-06-28
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD015C | IN-PROCESS FAB INSPECTION OF PP CONCRETE IN USA/CAN | 3 | CONSTRUCTION START | 2020-06-28 | 2022-06-27 | 2012-06-29 | 2025-07-02
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD015C | IN-PROCESS FAB INSPECTION OF PP CONCRETE IN USA/CAN | 5 | CONSTRUCTION START | 2020-06-28 | 2022-06-27 | 2025-07-03 | 2027-07-02
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD016 | TESTING AND SAMPLING OF MATERIAL (CITYWIDE) | 1 | DEVELOP SCOPE | 2017-06-30 | 2018-06-29 | 0 | 0
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD016 | TESTING AND SAMPLING OF MATERIAL (CITYWIDE) | 2 | DESIGN START | 2018-06-30 | 2022-06-28 | 2017-06-30 | 2018-06-29
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD016 | TESTING AND SAMPLING OF MATERIAL (CITYWIDE) | 3 | CONSTRUCTION START | 2022-06-29 | 2024-06-27 | 2018-06-30 | 2026-08-25
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD016 | TESTING AND SAMPLING OF MATERIAL (CITYWIDE) | 5 | CONSTRUCTION START | 2022-06-29 | 2024-06-27 | 2026-08-26 | 2031-08-24
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR02B | COMPONENT REHABILITATION 02B CONSTRUCTION | 1 | DEVELOP SCOPE | 2004-07-01 | 2005-06-30 | 0 | 0
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR02B | COMPONENT REHABILITATION 02B CONSTRUCTION | 2 | DESIGN START | 2005-07-01 | 2009-06-29 | 2011-01-13 | 2011-06-21
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR02B | COMPONENT REHABILITATION 02B CONSTRUCTION | 3 | CONSTRUCTION START | 2009-06-30 | 2011-06-29 | 2012-06-08 | 2014-06-06
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR02B | COMPONENT REHABILITATION 02B CONSTRUCTION | 5 | CONSTRUCTION START | 2009-06-30 | 2011-06-29 | 2014-07-10 | 2021-07-09
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR03A | COMPONENT REHABILITATION 03A CONSTRUCTION | 1 | DEVELOP SCOPE | 2005-07-01 | 2006-06-30 | 0 | 0
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR03A | COMPONENT REHABILITATION 03A CONSTRUCTION | 2 | DESIGN START | 2006-07-01 | 2010-06-29 | 2012-02-02 | 2012-05-08
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR03A | COMPONENT REHABILITATION 03A CONSTRUCTION | 3 | CONSTRUCTION START | 2010-06-30 | 2012-06-28 | 2013-01-28 | 2017-08-18
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR03A | COMPONENT REHABILITATION 03A CONSTRUCTION | 5 | CONSTRUCTION START | 2010-06-30 | 2012-06-28 | 2018-06-21 | 2021-10-07
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR03B | COMPONENT REHABILITATION 03B CONSTRUCTION | 1 | DEVELOP SCOPE | 2005-07-01 | 2006-06-30 | 0 | 0
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR03B | COMPONENT REHABILITATION 03B CONSTRUCTION | 2 | DESIGN START | 2006-07-01 | 2010-06-29 | 2015-05-10 | 2015-11-10
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR03B | COMPONENT REHABILITATION 03B CONSTRUCTION | 3 | CONSTRUCTION START | 2010-06-30 | 2012-06-28 | 2015-11-11 | 2019-11-09
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR03B | COMPONENT REHABILITATION 03B CONSTRUCTION | 5 | CONSTRUCTION START | 2010-06-30 | 2012-06-28 | 2019-11-10 | 2021-11-08
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR16 | COMPONENT REHAB OF BRIDGES CITYWIDE (8 BRIDGES) | 1 | DEVELOP SCOPE | 2015-06-30 | 2016-06-28 | 0 | 0
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR16 | COMPONENT REHAB OF BRIDGES CITYWIDE (8 BRIDGES) | 2 | DESIGN START | 2016-06-29 | 2020-06-27 | 2015-06-30 | 2016-06-28
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR16 | COMPONENT REHAB OF BRIDGES CITYWIDE (8 BRIDGES) | 3 | CONSTRUCTION START | 2020-06-28 | 2022-06-27 | 2017-06-15 | 2019-10-08
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR16 | COMPONENT REHAB OF BRIDGES CITYWIDE (8 BRIDGES) | 5 | CONSTRUCTION START | 2020-06-28 | 2022-06-27 | 2019-10-09 | 2021-10-07
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR21A | COMPONENT REHAB OF BRIDGES 21A | 1 | DEVELOP SCOPE | 2016-06-30 | 2017-06-29 | 0 | 0
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR21A | COMPONENT REHAB OF BRIDGES 21A | 2 | DESIGN START | 2017-06-30 | 2021-06-28 | 2017-01-26 | 2017-02-01
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR21A | COMPONENT REHAB OF BRIDGES 21A | 3 | CONSTRUCTION START | 2021-06-29 | 2023-06-28 | 2017-02-02 | 2021-01-31
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR21A | COMPONENT REHAB OF BRIDGES 21A | 5 | CONSTRUCTION START | 2021-06-29 | 2023-06-28 | 2021-02-01 | 2022-01-31
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR21B | COMPONENT REHAB OF BRIDGES 21B | 1 | DEVELOP SCOPE | 2016-06-30 | 2017-06-29 | 0 | 0
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR21B | COMPONENT REHAB OF BRIDGES 21B | 2 | DESIGN START | 2017-06-30 | 2021-06-28 | 2017-01-26 | 2017-02-15
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR21B | COMPONENT REHAB OF BRIDGES 21B | 3 | CONSTRUCTION START | 2021-06-29 | 2023-06-28 | 2017-02-16 | 2021-02-14
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR21B | COMPONENT REHAB OF BRIDGES 21B | 5 | CONSTRUCTION START | 2021-06-29 | 2023-06-28 | 2021-02-15 | 2023-02-14
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR22A | COMPONENT REHAB OF BRIDGES 22A | 1 | DEVELOP SCOPE | 2017-06-30 | 2018-06-29 | 0 | 0
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR22A | COMPONENT REHAB OF BRIDGES 22A | 2 | DESIGN START | 2018-06-30 | 2022-06-28 | 2017-10-08 | 2018-01-05
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR22A | COMPONENT REHAB OF BRIDGES 22A | 3 | CONSTRUCTION START | 2022-06-29 | 2024-06-27 | 2018-01-06 | 2022-01-04
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR22A | COMPONENT REHAB OF BRIDGES 22A | 5 | CONSTRUCTION START | 2022-06-29 | 2024-06-27 | 2022-01-05 | 2024-01-04
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR22B | COMPONENT REHAB OF BRIDGES 22B | 1 | DEVELOP SCOPE | 2017-06-30 | 2018-06-29 | 0 | 0
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR22B | COMPONENT REHAB OF BRIDGES 22B | 2 | DESIGN START | 2018-06-30 | 2022-06-28 | 2017-10-08 | 2018-01-05
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR22B | COMPONENT REHAB OF BRIDGES 22B | 3 | CONSTRUCTION START | 2022-06-29 | 2024-06-27 | 2018-01-06 | 2022-01-04
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR22B | COMPONENT REHAB OF BRIDGES 22B | 5 | CONSTRUCTION START | 2022-06-29 | 2024-06-27 | 2022-01-05 | 2024-01-04
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR23A | COMPONENT REHAB OF BRIDGES 23A | 1 | DEVELOP SCOPE | 2021-06-30 | 2021-09-27 | 2018-05-02 | 2019-04-10
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR23A | COMPONENT REHAB OF BRIDGES 23A | 2 | PRELIMINARY DESIGN | 2021-09-28 | 2022-01-25 | 2019-04-11 | 2019-08-08
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR23A | COMPONENT REHAB OF BRIDGES 23A | 3 | FINAL DESIGN | 2022-01-26 | 2022-07-24 | 2019-08-09 | 2020-02-04
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR23A | COMPONENT REHAB OF BRIDGES 23A | 4 | BID AWARD AND REGISTER CONTRCT | 2022-07-25 | 2022-10-22 | 2020-02-05 | 2020-05-04
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR23A | COMPONENT REHAB OF BRIDGES 23A | 5 | CONSTRUCTION TO 25% | 2022-10-23 | 2023-02-19 | 2020-05-05 | 2020-09-01
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR23A | COMPONENT REHAB OF BRIDGES 23A | 6 | CONSTRUCTION TO 50% | 2023-02-20 | 2023-06-19 | 2020-09-02 | 2020-12-30
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR23A | COMPONENT REHAB OF BRIDGES 23A | 7 | CONSTRUCTION TO 75% | 2023-06-20 | 2023-10-17 | 2020-12-31 | 2021-04-29
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR23A | COMPONENT REHAB OF BRIDGES 23A | 8 | ORIGINAL EQUIP & FURNISHING | 2023-10-18 | 2024-01-15 | 2021-04-30 | 2021-07-28
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR23A | COMPONENT REHAB OF BRIDGES 23A | 9 | SUBSTANTIAL COMPLETION | 2024-01-16 | 2024-03-15 | 2021-07-29 | 2021-09-26
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR23A | COMPONENT REHAB OF BRIDGES 23A | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-03-16 | 2024-04-14 | 2021-09-27 | 2023-10-26
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR23B | COMPONENT REHAB OF BRIDGES 23B | 1 | DEVELOP SCOPE | 2019-06-30 | 2020-06-28 | 0 | 0
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR23B | COMPONENT REHAB OF BRIDGES 23B | 2 | DESIGN START | 2020-06-29 | 2024-06-27 | 2015-05-02 | 2019-08-06
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR23B | COMPONENT REHAB OF BRIDGES 23B | 3 | CONSTRUCTION START | 2024-06-28 | 2026-06-27 | 2019-08-07 | 2023-08-05
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR23B | COMPONENT REHAB OF BRIDGES 23B | 5 | CONSTRUCTION START | 2024-06-28 | 2026-06-27 | 2023-08-06 | 2025-08-04
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR24A | COMPONENT REHAB OF BRIDGES 24A | 1 | DEVELOP SCOPE | 2022-06-30 | 2023-06-29 | 0 | 0
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR24A | COMPONENT REHAB OF BRIDGES 24A | 2 | DESIGN START | 2023-06-30 | 2027-06-28 | 2022-06-30 | 2023-06-29
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR24A | COMPONENT REHAB OF BRIDGES 24A | 3 | CONSTRUCTION START | 2027-06-29 | 2029-06-27 | 2023-06-30 | 2027-06-28
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR24A | COMPONENT REHAB OF BRIDGES 24A | 5 | CONSTRUCTION START | 2027-06-29 | 2029-06-27 | 2027-06-29 | 2029-06-27
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR24B | COMPONENT REHAB OF BRIDGES 24B | 1 | DEVELOP SCOPE | 2022-06-30 | 2023-06-29 | 0 | 0
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR24B | COMPONENT REHAB OF BRIDGES 24B | 2 | DESIGN START | 2023-06-30 | 2027-06-28 | 2022-06-30 | 2023-06-29
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR24B | COMPONENT REHAB OF BRIDGES 24B | 3 | CONSTRUCTION START | 2027-06-29 | 2029-06-27 | 2023-06-30 | 2027-06-28
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR24B | COMPONENT REHAB OF BRIDGES 24B | 5 | CONSTRUCTION START | 2027-06-29 | 2029-06-27 | 2027-06-29 | 2029-06-27
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBKBQE | Rehabilitation of BQE (I-278) from Sands St. to Atlantic Ave | 1 | DEVELOP SCOPE | 2022-06-30 | 2023-06-29 | 0 | 0
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBKBQE | Rehabilitation of BQE (I-278) from Sands St. to Atlantic Ave | 2 | DESIGN START | 2023-06-30 | 2027-06-28 | 2014-12-31 | 2015-04-15
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBKBQE | Rehabilitation of BQE (I-278) from Sands St. to Atlantic Ave | 3 | CONSTRUCTION START | 2027-06-29 | 2029-06-27 | 2017-03-21 | 2025-09-21
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBKBQE | Rehabilitation of BQE (I-278) from Sands St. to Atlantic Ave | 5 | CONSTRUCTION START | 2027-06-29 | 2029-06-27 | 2022-03-06 | 2027-03-06
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBR10COMP | TEN YR COMP | 1 | DEVELOP SCOPE | 2017-06-30 | 2018-06-29 | 0 | 0
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBR10COMP | TEN YR COMP | 2 | DESIGN START | 2018-06-30 | 2022-06-28 | 2016-06-30 | 2017-06-29
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBR10COMP | TEN YR COMP | 3 | CONSTRUCTION START | 2022-06-29 | 2024-06-27 | 2017-06-30 | 2021-06-28
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBR10COMP | TEN YR COMP | 5 | CONSTRUCTION START | 2022-06-29 | 2024-06-27 | 2021-06-29 | 2023-06-28
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBREP6919 | Emergency Contract for 181st (Washington Bridge) over Harlem | 1 | DEVELOP SCOPE | 2020-06-30 | 2021-06-29 | 0 | 0
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBREP6919 | Emergency Contract for 181st (Washington Bridge) over Harlem | 2 | DESIGN START | 2021-06-30 | 2025-06-28 | 2020-06-30 | 2021-06-29
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBREP6919 | Emergency Contract for 181st (Washington Bridge) over Harlem | 3 | CONSTRUCTION START | 2025-06-29 | 2027-06-28 | 2021-06-30 | 2025-06-28
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBREP6919 | Emergency Contract for 181st (Washington Bridge) over Harlem | 5 | CONSTRUCTION START | 2025-06-29 | 2027-06-28 | 2025-06-29 | 2027-06-28
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBX1670 | EAST 169TH STREET OVER METRO NORTH RR BIN: 2241670 | 1 | DEVELOP SCOPE | 2016-06-30 | 2017-06-29 | 0 | 0
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBX1670 | EAST 169TH STREET OVER METRO NORTH RR BIN: 2241670 | 2 | DESIGN START | 2017-06-30 | 2021-06-28 | 2014-06-01 | 2015-06-30
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBX1670 | EAST 169TH STREET OVER METRO NORTH RR BIN: 2241670 | 3 | CONSTRUCTION START | 2021-06-29 | 2023-06-28 | 2015-07-01 | 2019-06-29
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBX1670 | EAST 169TH STREET OVER METRO NORTH RR BIN: 2241670 | 5 | CONSTRUCTION START | 2021-06-29 | 2023-06-28 | 2019-06-30 | 2022-06-28
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW200IFA1 | In-House Pedestrian Ramp Rehabilitation - Crews | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-09-28 | 2019-07-01 | 2019-09-28
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW200IFA1 | In-House Pedestrian Ramp Rehabilitation - Crews | 2 | PRELIMINARY DESIGN | 2016-09-29 | 2017-01-26 | 2019-09-29 | 2020-01-26
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW200IFA1 | In-House Pedestrian Ramp Rehabilitation - Crews | 3 | FINAL DESIGN | 2017-01-27 | 2017-07-25 | 2020-01-27 | 2020-07-24
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW200IFA1 | In-House Pedestrian Ramp Rehabilitation - Crews | 4 | BID AWARD AND REGISTER CONTRCT | 2017-07-26 | 2017-10-23 | 2020-07-25 | 2020-10-22
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW200IFA1 | In-House Pedestrian Ramp Rehabilitation - Crews | 5 | CONSTRUCTION TO 25% | 2017-10-24 | 2018-02-20 | 2020-10-23 | 2021-02-19
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW200IFA1 | In-House Pedestrian Ramp Rehabilitation - Crews | 6 | CONSTRUCTION TO 50% | 2018-02-21 | 2018-06-20 | 2021-02-20 | 2021-06-19
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW200IFA1 | In-House Pedestrian Ramp Rehabilitation - Crews | 7 | CONSTRUCTION TO 75% | 2018-06-21 | 2018-10-18 | 2021-06-20 | 2021-10-17
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW200IFA1 | In-House Pedestrian Ramp Rehabilitation - Crews | 8 | ORIGINAL EQUIP & FURNISHING | 2018-10-19 | 2019-01-16 | 2021-10-18 | 2022-01-15
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW200IFA1 | In-House Pedestrian Ramp Rehabilitation - Crews | 9 | SUBSTANTIAL COMPLETION | 2019-01-17 | 2019-03-17 | 2022-01-16 | 2022-03-16
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW200IFA1 | In-House Pedestrian Ramp Rehabilitation - Crews | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-03-18 | 2019-04-16 | 2022-03-17 | 2022-04-15
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW200IFA2 | In-House Pedestrian Ramp Rehabilitation - OTPS | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-09-28 | 2019-07-01 | 2019-09-28
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW200IFA2 | In-House Pedestrian Ramp Rehabilitation - OTPS | 2 | PRELIMINARY DESIGN | 2016-09-29 | 2017-01-26 | 2019-09-29 | 2020-01-26
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW200IFA2 | In-House Pedestrian Ramp Rehabilitation - OTPS | 3 | FINAL DESIGN | 2017-01-27 | 2017-07-25 | 2020-01-27 | 2020-07-24
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW200IFA2 | In-House Pedestrian Ramp Rehabilitation - OTPS | 4 | BID AWARD AND REGISTER CONTRCT | 2017-07-26 | 2017-10-23 | 2020-07-25 | 2020-10-22
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW200IFA2 | In-House Pedestrian Ramp Rehabilitation - OTPS | 5 | CONSTRUCTION TO 25% | 2017-10-24 | 2018-02-20 | 2020-10-23 | 2021-02-19
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW200IFA2 | In-House Pedestrian Ramp Rehabilitation - OTPS | 6 | CONSTRUCTION TO 50% | 2018-02-21 | 2018-06-20 | 2021-02-20 | 2021-06-19
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW200IFA2 | In-House Pedestrian Ramp Rehabilitation - OTPS | 7 | CONSTRUCTION TO 75% | 2018-06-21 | 2018-10-18 | 2021-06-20 | 2021-10-17
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW200IFA2 | In-House Pedestrian Ramp Rehabilitation - OTPS | 8 | ORIGINAL EQUIP & FURNISHING | 2018-10-19 | 2019-01-16 | 2021-10-18 | 2022-01-15
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW200IFA2 | In-House Pedestrian Ramp Rehabilitation - OTPS | 9 | SUBSTANTIAL COMPLETION | 2019-01-17 | 2019-03-17 | 2022-01-16 | 2022-03-16
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW200IFA2 | In-House Pedestrian Ramp Rehabilitation - OTPS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-03-18 | 2019-04-16 | 2022-03-17 | 2022-04-15
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR06 | CITYWIDE MILLING | 1 | DEVELOP SCOPE | 2011-05-22 | 2011-08-19 | 2022-05-22 | 2022-08-19
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR06 | CITYWIDE MILLING | 2 | PRELIMINARY DESIGN | 2011-08-20 | 2011-12-17 | 2022-08-20 | 2022-12-17
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR06 | CITYWIDE MILLING | 3 | FINAL DESIGN | 2011-12-18 | 2012-06-14 | 2022-12-18 | 2023-06-15
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR06 | CITYWIDE MILLING | 4 | BID AWARD AND REGISTER CONTRCT | 2012-06-15 | 2012-09-12 | 2023-06-16 | 2023-09-13
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR06 | CITYWIDE MILLING | 5 | CONSTRUCTION TO 25% | 2012-09-13 | 2013-01-10 | 2023-09-14 | 2024-01-11
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR06 | CITYWIDE MILLING | 6 | CONSTRUCTION TO 50% | 2013-01-11 | 2013-05-10 | 2024-01-12 | 2024-05-10
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR06 | CITYWIDE MILLING | 7 | CONSTRUCTION TO 75% | 2013-05-11 | 2013-09-07 | 2024-05-11 | 2024-09-07
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR06 | CITYWIDE MILLING | 8 | ORIGINAL EQUIP & FURNISHING | 2013-09-08 | 2013-12-06 | 2024-09-08 | 2024-12-06
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR06 | CITYWIDE MILLING | 9 | SUBSTANTIAL COMPLETION | 2013-12-07 | 2014-02-04 | 2024-12-07 | 2025-02-04
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR06 | CITYWIDE MILLING | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-02-05 | 2014-03-06 | 2025-02-05 | 2025-03-06
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW34907 | IN-HOUSE RESURFACING - CREWS&OTHER NON-ASPHALT OTPS | 1 | DEVELOP SCOPE | 2007-06-01 | 2007-09-28 | 2007-06-01 | 2007-09-01
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW34907 | IN-HOUSE RESURFACING - CREWS&OTHER NON-ASPHALT OTPS | 2 | DESIGN START | 2007-09-29 | 2009-03-21 | 2007-09-02 | 2009-03-01
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW34907 | IN-HOUSE RESURFACING - CREWS&OTHER NON-ASPHALT OTPS | 3 | CONSTRUCTION START | 2009-03-22 | 2011-03-11 | 2009-03-02 | 2029-03-01
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWC349M03 | MANHOLE RINGS | 1 | DEVELOP SCOPE | 2010-05-21 | 2010-08-18 | 1997-05-20 | 1997-08-17
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWC349M03 | MANHOLE RINGS | 2 | PRELIMINARY DESIGN | 2010-08-19 | 2010-12-16 | 1997-08-18 | 1997-12-15
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWC349M03 | MANHOLE RINGS | 3 | FINAL DESIGN | 2010-12-17 | 2011-06-14 | 1997-12-16 | 1998-06-13
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWC349M03 | MANHOLE RINGS | 4 | BID AWARD AND REGISTER CONTRCT | 2011-06-15 | 2011-09-12 | 1998-06-14 | 2011-09-12
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWC349M03 | MANHOLE RINGS | 5 | CONSTRUCTION TO 25% | 2011-09-13 | 2012-01-10 | 2011-09-13 | 2024-01-10
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWC349M03 | MANHOLE RINGS | 6 | CONSTRUCTION TO 50% | 2012-01-11 | 2012-05-09 | 2024-01-11 | 2024-05-09
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWC349M03 | MANHOLE RINGS | 7 | CONSTRUCTION TO 75% | 2012-05-10 | 2012-09-06 | 2024-05-10 | 2024-09-06
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWC349M03 | MANHOLE RINGS | 8 | ORIGINAL EQUIP & FURNISHING | 2012-09-07 | 2012-12-05 | 2024-09-07 | 2024-12-05
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWC349M03 | MANHOLE RINGS | 9 | SUBSTANTIAL COMPLETION | 2012-12-06 | 2013-02-03 | 2024-12-06 | 2025-02-03
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWC349M03 | MANHOLE RINGS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-02-04 | 2013-03-05 | 2025-02-04 | 2025-03-05
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCFTRLR | Citywide Trailer Rehabilitation | 1 | DEVELOP SCOPE | 2017-06-30 | 2017-09-27 | 2018-06-30 | 2018-09-27
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCFTRLR | Citywide Trailer Rehabilitation | 2 | PRELIMINARY DESIGN | 2017-09-28 | 2018-01-25 | 2018-09-28 | 2019-01-25
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCFTRLR | Citywide Trailer Rehabilitation | 3 | FINAL DESIGN | 2018-01-26 | 2018-07-24 | 2019-01-26 | 2019-07-24
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCFTRLR | Citywide Trailer Rehabilitation | 4 | BID AWARD AND REGISTER CONTRCT | 2018-07-25 | 2018-10-22 | 2019-07-25 | 2019-10-22
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCFTRLR | Citywide Trailer Rehabilitation | 5 | CONSTRUCTION TO 25% | 2018-10-23 | 2019-02-19 | 2019-10-23 | 2020-02-19
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCFTRLR | Citywide Trailer Rehabilitation | 6 | CONSTRUCTION TO 50% | 2019-02-20 | 2019-06-19 | 2020-02-20 | 2020-06-18
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCFTRLR | Citywide Trailer Rehabilitation | 7 | CONSTRUCTION TO 75% | 2019-06-20 | 2019-10-17 | 2020-06-19 | 2020-10-16
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCFTRLR | Citywide Trailer Rehabilitation | 8 | ORIGINAL EQUIP & FURNISHING | 2019-10-18 | 2020-01-15 | 2020-10-17 | 2021-01-14
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCFTRLR | Citywide Trailer Rehabilitation | 9 | SUBSTANTIAL COMPLETION | 2020-01-16 | 2020-03-15 | 2021-01-15 | 2021-03-15
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCFTRLR | Citywide Trailer Rehabilitation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-03-16 | 2020-04-14 | 2021-03-16 | 2021-04-14
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWC-HDBP | High-Density Bike Parking | 1 | DEVELOP SCOPE | 2017-06-30 | 2017-09-27 | 2019-06-30 | 2019-09-27
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWC-HDBP | High-Density Bike Parking | 2 | PRELIMINARY DESIGN | 2017-09-28 | 2018-01-25 | 2019-09-28 | 2020-01-25
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWC-HDBP | High-Density Bike Parking | 3 | FINAL DESIGN | 2018-01-26 | 2018-07-24 | 2020-01-26 | 2020-07-23
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWC-HDBP | High-Density Bike Parking | 4 | BID AWARD AND REGISTER CONTRCT | 2018-07-25 | 2018-10-22 | 2020-07-24 | 2020-10-21
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWC-HDBP | High-Density Bike Parking | 5 | CONSTRUCTION TO 25% | 2018-10-23 | 2019-02-19 | 2020-10-22 | 2021-02-18
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWC-HDBP | High-Density Bike Parking | 6 | CONSTRUCTION TO 50% | 2019-02-20 | 2019-06-19 | 2021-02-19 | 2021-06-18
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWC-HDBP | High-Density Bike Parking | 7 | CONSTRUCTION TO 75% | 2019-06-20 | 2019-10-17 | 2021-06-19 | 2021-10-16
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWC-HDBP | High-Density Bike Parking | 8 | ORIGINAL EQUIP & FURNISHING | 2019-10-18 | 2020-01-15 | 2021-10-17 | 2022-01-14
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWC-HDBP | High-Density Bike Parking | 9 | SUBSTANTIAL COMPLETION | 2020-01-16 | 2020-03-15 | 2022-01-15 | 2022-03-15
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWC-HDBP | High-Density Bike Parking | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-03-16 | 2020-04-14 | 2022-03-16 | 2026-06-30
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCPDLOC2 | Perimeter Security Measures 2 | 1 | DEVELOP SCOPE | 2018-06-30 | 2018-09-27 | 2019-06-30 | 2019-09-27
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCPDLOC2 | Perimeter Security Measures 2 | 2 | PRELIMINARY DESIGN | 2018-09-28 | 2019-01-25 | 2019-09-28 | 2020-01-25
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCPDLOC2 | Perimeter Security Measures 2 | 3 | FINAL DESIGN | 2019-01-26 | 2019-07-24 | 2020-01-26 | 2020-07-23
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCPDLOC2 | Perimeter Security Measures 2 | 4 | BID AWARD AND REGISTER CONTRCT | 2019-07-25 | 2019-10-22 | 2020-07-24 | 2020-10-21
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCPDLOC2 | Perimeter Security Measures 2 | 5 | CONSTRUCTION TO 25% | 2019-10-23 | 2020-02-19 | 2020-10-22 | 2021-02-18
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCPDLOC2 | Perimeter Security Measures 2 | 6 | CONSTRUCTION TO 50% | 2020-02-20 | 2020-06-18 | 2021-02-19 | 2021-06-18
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCPDLOC2 | Perimeter Security Measures 2 | 7 | CONSTRUCTION TO 75% | 2020-06-19 | 2020-10-16 | 2021-06-19 | 2021-10-16
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCPDLOC2 | Perimeter Security Measures 2 | 8 | ORIGINAL EQUIP & FURNISHING | 2020-10-17 | 2021-01-14 | 2021-10-17 | 2022-01-14
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCPDLOC2 | Perimeter Security Measures 2 | 9 | SUBSTANTIAL COMPLETION | 2021-01-15 | 2021-03-15 | 2022-01-15 | 2022-03-15
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCPDLOC2 | Perimeter Security Measures 2 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-16 | 2021-04-14 | 2022-03-16 | 2028-06-14
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCWREC | CITYWIDE RECONSTRUCTION OF STREETS | 1 | DEVELOP SCOPE | 2010-06-30 | 2010-09-27 | 2022-06-30 | 2022-09-27
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCWREC | CITYWIDE RECONSTRUCTION OF STREETS | 2 | PRELIMINARY DESIGN | 2010-09-28 | 2011-01-25 | 2022-09-28 | 2023-01-25
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCWREC | CITYWIDE RECONSTRUCTION OF STREETS | 3 | FINAL DESIGN | 2011-01-26 | 2011-07-24 | 2023-01-26 | 2023-07-24
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCWREC | CITYWIDE RECONSTRUCTION OF STREETS | 4 | BID AWARD AND REGISTER CONTRCT | 2011-07-25 | 2011-10-22 | 2023-07-25 | 2023-10-22
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCWREC | CITYWIDE RECONSTRUCTION OF STREETS | 5 | CONSTRUCTION TO 25% | 2011-10-23 | 2012-02-19 | 2023-10-23 | 2024-02-19
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCWREC | CITYWIDE RECONSTRUCTION OF STREETS | 6 | CONSTRUCTION TO 50% | 2012-02-20 | 2012-06-18 | 2024-02-20 | 2024-06-18
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCWREC | CITYWIDE RECONSTRUCTION OF STREETS | 7 | CONSTRUCTION TO 75% | 2012-06-19 | 2012-10-16 | 2024-06-19 | 2024-10-16
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCWREC | CITYWIDE RECONSTRUCTION OF STREETS | 8 | ORIGINAL EQUIP & FURNISHING | 2012-10-17 | 2013-01-14 | 2024-10-17 | 2025-01-14
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCWREC | CITYWIDE RECONSTRUCTION OF STREETS | 9 | SUBSTANTIAL COMPLETION | 2013-01-15 | 2013-03-15 | 2025-01-15 | 2025-03-15
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCWREC | CITYWIDE RECONSTRUCTION OF STREETS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-03-16 | 2013-04-14 | 2025-03-16 | 2025-04-14
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCW-SOGR | Citywide Streets - 30-Year State of Good Repair | 1 | DEVELOP SCOPE | 2018-06-30 | 2018-09-27 | 2020-06-30 | 2020-09-27
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCW-SOGR | Citywide Streets - 30-Year State of Good Repair | 2 | PRELIMINARY DESIGN | 2018-09-28 | 2019-01-25 | 2020-09-28 | 2021-01-25
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCW-SOGR | Citywide Streets - 30-Year State of Good Repair | 3 | FINAL DESIGN | 2019-01-26 | 2019-07-24 | 2021-01-26 | 2021-07-24
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCW-SOGR | Citywide Streets - 30-Year State of Good Repair | 4 | BID AWARD AND REGISTER CONTRCT | 2019-07-25 | 2019-10-22 | 2021-07-25 | 2021-10-22
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCW-SOGR | Citywide Streets - 30-Year State of Good Repair | 5 | CONSTRUCTION TO 25% | 2019-10-23 | 2020-02-19 | 2021-10-23 | 2022-02-19
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCW-SOGR | Citywide Streets - 30-Year State of Good Repair | 6 | CONSTRUCTION TO 50% | 2020-02-20 | 2020-06-18 | 2022-02-20 | 2022-06-19
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCW-SOGR | Citywide Streets - 30-Year State of Good Repair | 7 | CONSTRUCTION TO 75% | 2020-06-19 | 2020-10-16 | 2022-06-20 | 2022-10-17
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCW-SOGR | Citywide Streets - 30-Year State of Good Repair | 8 | ORIGINAL EQUIP & FURNISHING | 2020-10-17 | 2021-01-14 | 2022-10-18 | 2023-01-15
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCW-SOGR | Citywide Streets - 30-Year State of Good Repair | 9 | SUBSTANTIAL COMPLETION | 2021-01-15 | 2021-03-15 | 2023-01-16 | 2023-03-16
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCW-SOGR | Citywide Streets - 30-Year State of Good Repair | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-16 | 2021-04-14 | 2023-03-17 | 2028-06-30
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCW-VZSR | Vision Zero Street Reconstuction | 1 | DEVELOP SCOPE | 2016-06-30 | 2016-09-27 | 2019-06-30 | 2019-09-27
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCW-VZSR | Vision Zero Street Reconstuction | 2 | PRELIMINARY DESIGN | 2016-09-28 | 2017-01-25 | 2019-09-28 | 2020-01-25
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCW-VZSR | Vision Zero Street Reconstuction | 3 | FINAL DESIGN | 2017-01-26 | 2017-07-24 | 2020-01-26 | 2020-07-23
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCW-VZSR | Vision Zero Street Reconstuction | 4 | BID AWARD AND REGISTER CONTRCT | 2017-07-25 | 2017-10-22 | 2020-07-24 | 2020-10-21
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCW-VZSR | Vision Zero Street Reconstuction | 5 | CONSTRUCTION TO 25% | 2017-10-23 | 2018-02-19 | 2020-10-22 | 2021-02-18
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCW-VZSR | Vision Zero Street Reconstuction | 6 | CONSTRUCTION TO 50% | 2018-02-20 | 2018-06-19 | 2021-02-19 | 2021-06-18
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCW-VZSR | Vision Zero Street Reconstuction | 7 | CONSTRUCTION TO 75% | 2018-06-20 | 2018-10-17 | 2021-06-19 | 2021-10-16
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCW-VZSR | Vision Zero Street Reconstuction | 8 | ORIGINAL EQUIP & FURNISHING | 2018-10-18 | 2019-01-15 | 2021-10-17 | 2022-01-14
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCW-VZSR | Vision Zero Street Reconstuction | 9 | SUBSTANTIAL COMPLETION | 2019-01-16 | 2019-03-16 | 2022-01-15 | 2022-03-15
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCW-VZSR | Vision Zero Street Reconstuction | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-03-17 | 2019-04-15 | 2022-03-16 | 2028-04-14
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWMMPEDSW | MULTI-MODAL #2 - 2000 PED RAMPS AND SIDEWALK | 1 | DEVELOP SCOPE | 2011-06-30 | 2011-09-27 | 2019-06-30 | 2019-09-27
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWMMPEDSW | MULTI-MODAL #2 - 2000 PED RAMPS AND SIDEWALK | 2 | PRELIMINARY DESIGN | 2011-09-28 | 2012-01-25 | 2019-09-28 | 2020-01-25
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWMMPEDSW | MULTI-MODAL #2 - 2000 PED RAMPS AND SIDEWALK | 3 | FINAL DESIGN | 2012-01-26 | 2012-07-23 | 2020-01-26 | 2020-07-23
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWMMPEDSW | MULTI-MODAL #2 - 2000 PED RAMPS AND SIDEWALK | 4 | BID AWARD AND REGISTER CONTRCT | 2012-07-24 | 2012-10-21 | 2020-07-24 | 2020-10-21
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWMMPEDSW | MULTI-MODAL #2 - 2000 PED RAMPS AND SIDEWALK | 5 | CONSTRUCTION TO 25% | 2012-10-22 | 2013-02-18 | 2020-10-22 | 2021-02-18
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWMMPEDSW | MULTI-MODAL #2 - 2000 PED RAMPS AND SIDEWALK | 6 | CONSTRUCTION TO 50% | 2013-02-19 | 2013-06-18 | 2021-02-19 | 2021-06-18
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWMMPEDSW | MULTI-MODAL #2 - 2000 PED RAMPS AND SIDEWALK | 7 | CONSTRUCTION TO 75% | 2013-06-19 | 2013-10-16 | 2021-06-19 | 2021-10-16
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWMMPEDSW | MULTI-MODAL #2 - 2000 PED RAMPS AND SIDEWALK | 8 | ORIGINAL EQUIP & FURNISHING | 2013-10-17 | 2014-01-14 | 2021-10-17 | 2022-01-14
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWMMPEDSW | MULTI-MODAL #2 - 2000 PED RAMPS AND SIDEWALK | 9 | SUBSTANTIAL COMPLETION | 2014-01-15 | 2014-03-15 | 2022-01-15 | 2022-03-15
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWMMPEDSW | MULTI-MODAL #2 - 2000 PED RAMPS AND SIDEWALK | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-03-16 | 2014-04-14 | 2022-03-16 | 2022-04-14
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWP19MKLM | COMPLEX PED RAMPS (LANDMARK) - MANHATTAN AND BROOKLYN | 1 | DEVELOP SCOPE | 2019-06-30 | 2019-09-27 | 2021-06-30 | 2021-09-27
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWP19MKLM | COMPLEX PED RAMPS (LANDMARK) - MANHATTAN AND BROOKLYN | 2 | PRELIMINARY DESIGN | 2019-09-28 | 2020-01-25 | 2021-09-28 | 2022-01-25
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWP19MKLM | COMPLEX PED RAMPS (LANDMARK) - MANHATTAN AND BROOKLYN | 3 | FINAL DESIGN | 2020-01-26 | 2020-07-23 | 2022-01-26 | 2022-07-24
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWP19MKLM | COMPLEX PED RAMPS (LANDMARK) - MANHATTAN AND BROOKLYN | 4 | BID AWARD AND REGISTER CONTRCT | 2020-07-24 | 2020-10-21 | 2022-07-25 | 2022-10-22
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWP19MKLM | COMPLEX PED RAMPS (LANDMARK) - MANHATTAN AND BROOKLYN | 5 | CONSTRUCTION TO 25% | 2020-10-22 | 2021-02-18 | 2022-10-23 | 2023-02-19
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWP19MKLM | COMPLEX PED RAMPS (LANDMARK) - MANHATTAN AND BROOKLYN | 6 | CONSTRUCTION TO 50% | 2021-02-19 | 2021-06-18 | 2023-02-20 | 2023-06-19
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWP19MKLM | COMPLEX PED RAMPS (LANDMARK) - MANHATTAN AND BROOKLYN | 7 | CONSTRUCTION TO 75% | 2021-06-19 | 2021-10-16 | 2023-06-20 | 2023-10-17
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWP19MKLM | COMPLEX PED RAMPS (LANDMARK) - MANHATTAN AND BROOKLYN | 8 | ORIGINAL EQUIP & FURNISHING | 2021-10-17 | 2022-01-14 | 2023-10-18 | 2024-01-15
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWP19MKLM | COMPLEX PED RAMPS (LANDMARK) - MANHATTAN AND BROOKLYN | 9 | SUBSTANTIAL COMPLETION | 2022-01-15 | 2022-03-15 | 2024-01-16 | 2024-03-15
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWP19MKLM | COMPLEX PED RAMPS (LANDMARK) - MANHATTAN AND BROOKLYN | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-16 | 2022-04-14 | 2024-03-16 | 2024-04-14
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWP19MXLM | COMPLEX PED RAMPS (LANDMARK) - MANHATTAN AND BRONX | 1 | DEVELOP SCOPE | 2019-06-30 | 2019-09-27 | 2021-06-30 | 2021-09-27
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWP19MXLM | COMPLEX PED RAMPS (LANDMARK) - MANHATTAN AND BRONX | 2 | PRELIMINARY DESIGN | 2019-09-28 | 2020-01-25 | 2021-09-28 | 2022-01-25
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWP19MXLM | COMPLEX PED RAMPS (LANDMARK) - MANHATTAN AND BRONX | 3 | FINAL DESIGN | 2020-01-26 | 2020-07-23 | 2022-01-26 | 2022-07-24
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWP19MXLM | COMPLEX PED RAMPS (LANDMARK) - MANHATTAN AND BRONX | 4 | BID AWARD AND REGISTER CONTRCT | 2020-07-24 | 2020-10-21 | 2022-07-25 | 2022-10-22
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWP19MXLM | COMPLEX PED RAMPS (LANDMARK) - MANHATTAN AND BRONX | 5 | CONSTRUCTION TO 25% | 2020-10-22 | 2021-02-18 | 2022-10-23 | 2023-02-19
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWP19MXLM | COMPLEX PED RAMPS (LANDMARK) - MANHATTAN AND BRONX | 6 | CONSTRUCTION TO 50% | 2021-02-19 | 2021-06-18 | 2023-02-20 | 2023-06-19
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWP19MXLM | COMPLEX PED RAMPS (LANDMARK) - MANHATTAN AND BRONX | 7 | CONSTRUCTION TO 75% | 2021-06-19 | 2021-10-16 | 2023-06-20 | 2023-10-17
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWP19MXLM | COMPLEX PED RAMPS (LANDMARK) - MANHATTAN AND BRONX | 8 | ORIGINAL EQUIP & FURNISHING | 2021-10-17 | 2022-01-14 | 2023-10-18 | 2024-01-15
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWP19MXLM | COMPLEX PED RAMPS (LANDMARK) - MANHATTAN AND BRONX | 9 | SUBSTANTIAL COMPLETION | 2022-01-15 | 2022-03-15 | 2024-01-16 | 2024-03-15
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWP19MXLM | COMPLEX PED RAMPS (LANDMARK) - MANHATTAN AND BRONX | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-16 | 2022-04-14 | 2024-03-16 | 2024-04-14
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPDRAPS | Pedestrian Ramps - Required APS add on | 1 | DEVELOP SCOPE | 2019-06-30 | 2019-09-27 | 2019-06-30 | 2019-09-27
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPDRAPS | Pedestrian Ramps - Required APS add on | 2 | PRELIMINARY DESIGN | 2019-09-28 | 2020-01-25 | 2019-09-28 | 2020-01-25
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPDRAPS | Pedestrian Ramps - Required APS add on | 3 | FINAL DESIGN | 2020-01-26 | 2020-07-23 | 2020-01-26 | 2020-07-23
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPDRAPS | Pedestrian Ramps - Required APS add on | 4 | BID AWARD AND REGISTER CONTRCT | 2020-07-24 | 2020-10-21 | 2020-07-24 | 2020-10-21
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPDRAPS | Pedestrian Ramps - Required APS add on | 5 | CONSTRUCTION TO 25% | 2020-10-22 | 2021-02-18 | 2020-10-22 | 2021-02-18
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPDRAPS | Pedestrian Ramps - Required APS add on | 6 | CONSTRUCTION TO 50% | 2021-02-19 | 2021-06-18 | 2021-02-19 | 2021-06-18
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPDRAPS | Pedestrian Ramps - Required APS add on | 7 | CONSTRUCTION TO 75% | 2021-06-19 | 2021-10-16 | 2021-06-19 | 2021-10-16
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPDRAPS | Pedestrian Ramps - Required APS add on | 8 | ORIGINAL EQUIP & FURNISHING | 2021-10-17 | 2022-01-14 | 2021-10-17 | 2022-01-14
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPDRAPS | Pedestrian Ramps - Required APS add on | 9 | SUBSTANTIAL COMPLETION | 2022-01-15 | 2022-03-15 | 2022-01-15 | 2022-03-15
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPDRAPS | Pedestrian Ramps - Required APS add on | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-16 | 2022-04-14 | 2022-03-16 | 2022-04-14
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPDRFORC | Pedestrian Ramps - Force Account | 1 | DEVELOP SCOPE | 2020-06-30 | 2020-09-27 | 2020-06-30 | 2020-09-27
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPDRFORC | Pedestrian Ramps - Force Account | 2 | PRELIMINARY DESIGN | 2020-09-28 | 2021-01-25 | 2020-09-28 | 2021-01-25
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPDRFORC | Pedestrian Ramps - Force Account | 3 | FINAL DESIGN | 2021-01-26 | 2021-07-24 | 2021-01-26 | 2021-07-24
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPDRFORC | Pedestrian Ramps - Force Account | 4 | BID AWARD AND REGISTER CONTRCT | 2021-07-25 | 2021-10-22 | 2021-07-25 | 2021-10-22
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPDRFORC | Pedestrian Ramps - Force Account | 5 | CONSTRUCTION TO 25% | 2021-10-23 | 2022-02-19 | 2021-10-23 | 2022-02-19
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPDRFORC | Pedestrian Ramps - Force Account | 6 | CONSTRUCTION TO 50% | 2022-02-20 | 2022-06-19 | 2022-02-20 | 2022-06-19
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPDRFORC | Pedestrian Ramps - Force Account | 7 | CONSTRUCTION TO 75% | 2022-06-20 | 2022-10-17 | 2022-06-20 | 2022-10-17
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPDRFORC | Pedestrian Ramps - Force Account | 8 | ORIGINAL EQUIP & FURNISHING | 2022-10-18 | 2023-01-15 | 2022-10-18 | 2023-01-15
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPDRFORC | Pedestrian Ramps - Force Account | 9 | SUBSTANTIAL COMPLETION | 2023-01-16 | 2023-03-16 | 2023-01-16 | 2023-03-16
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPDRFORC | Pedestrian Ramps - Force Account | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-03-17 | 2023-04-15 | 2023-03-17 | 2023-04-15
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPDRTREE | Pedestrian Ramps - Tree Replacement | 1 | DEVELOP SCOPE | 2019-06-30 | 2019-09-27 | 2021-06-30 | 2021-09-27
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPDRTREE | Pedestrian Ramps - Tree Replacement | 2 | PRELIMINARY DESIGN | 2019-09-28 | 2020-01-25 | 2021-09-28 | 2022-01-25
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPDRTREE | Pedestrian Ramps - Tree Replacement | 3 | FINAL DESIGN | 2020-01-26 | 2020-07-23 | 2022-01-26 | 2022-07-24
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPDRTREE | Pedestrian Ramps - Tree Replacement | 4 | BID AWARD AND REGISTER CONTRCT | 2020-07-24 | 2020-10-21 | 2022-07-25 | 2022-10-22
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPDRTREE | Pedestrian Ramps - Tree Replacement | 5 | CONSTRUCTION TO 25% | 2020-10-22 | 2021-02-18 | 2022-10-23 | 2023-02-19
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPDRTREE | Pedestrian Ramps - Tree Replacement | 6 | CONSTRUCTION TO 50% | 2021-02-19 | 2021-06-18 | 2023-02-20 | 2023-06-19
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPDRTREE | Pedestrian Ramps - Tree Replacement | 7 | CONSTRUCTION TO 75% | 2021-06-19 | 2021-10-16 | 2023-06-20 | 2023-10-17
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPDRTREE | Pedestrian Ramps - Tree Replacement | 8 | ORIGINAL EQUIP & FURNISHING | 2021-10-17 | 2022-01-14 | 2023-10-18 | 2024-01-15
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPDRTREE | Pedestrian Ramps - Tree Replacement | 9 | SUBSTANTIAL COMPLETION | 2022-01-15 | 2022-03-15 | 2024-01-16 | 2024-03-15
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPDRTREE | Pedestrian Ramps - Tree Replacement | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-16 | 2022-04-14 | 2024-03-16 | 2024-04-14
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPELIMLM | REPACKAGED COMPLEX PED RAMP INSTALL LANDMARK | 1 | DEVELOP SCOPE | 2022-06-30 | 2022-09-27 | 2022-06-30 | 2022-09-27
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPELIMLM | REPACKAGED COMPLEX PED RAMP INSTALL LANDMARK | 2 | PRELIMINARY DESIGN | 2022-09-28 | 2023-01-25 | 2022-09-28 | 2023-01-25
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPELIMLM | REPACKAGED COMPLEX PED RAMP INSTALL LANDMARK | 3 | FINAL DESIGN | 2023-01-26 | 2023-07-24 | 2023-01-26 | 2023-07-24
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPELIMLM | REPACKAGED COMPLEX PED RAMP INSTALL LANDMARK | 4 | BID AWARD AND REGISTER CONTRCT | 2023-07-25 | 2023-10-22 | 2023-07-25 | 2023-10-22
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPELIMLM | REPACKAGED COMPLEX PED RAMP INSTALL LANDMARK | 5 | CONSTRUCTION TO 25% | 2023-10-23 | 2024-02-19 | 2023-10-23 | 2024-02-19
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPELIMLM | REPACKAGED COMPLEX PED RAMP INSTALL LANDMARK | 6 | CONSTRUCTION TO 50% | 2024-02-20 | 2024-06-18 | 2024-02-20 | 2024-06-18
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPELIMLM | REPACKAGED COMPLEX PED RAMP INSTALL LANDMARK | 7 | CONSTRUCTION TO 75% | 2024-06-19 | 2024-10-16 | 2024-06-19 | 2024-10-16
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPELIMLM | REPACKAGED COMPLEX PED RAMP INSTALL LANDMARK | 8 | ORIGINAL EQUIP & FURNISHING | 2024-10-17 | 2025-01-14 | 2024-10-17 | 2025-01-14
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPELIMLM | REPACKAGED COMPLEX PED RAMP INSTALL LANDMARK | 9 | SUBSTANTIAL COMPLETION | 2025-01-15 | 2025-03-15 | 2025-01-15 | 2025-03-15
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPELIMLM | REPACKAGED COMPLEX PED RAMP INSTALL LANDMARK | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-03-16 | 2025-04-14 | 2025-03-16 | 2025-04-14
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPELIMMX | Repacked Complex Ped Ramps Installs - Manhattan & Bronx | 1 | DEVELOP SCOPE | 2022-06-30 | 2022-09-27 | 2022-06-30 | 2022-09-27
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPELIMMX | Repacked Complex Ped Ramps Installs - Manhattan & Bronx | 2 | PRELIMINARY DESIGN | 2022-09-28 | 2023-01-25 | 2022-09-28 | 2023-01-25
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPELIMMX | Repacked Complex Ped Ramps Installs - Manhattan & Bronx | 3 | FINAL DESIGN | 2023-01-26 | 2023-07-24 | 2023-01-26 | 2023-07-24
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPELIMMX | Repacked Complex Ped Ramps Installs - Manhattan & Bronx | 4 | BID AWARD AND REGISTER CONTRCT | 2023-07-25 | 2023-10-22 | 2023-07-25 | 2023-10-22
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPELIMMX | Repacked Complex Ped Ramps Installs - Manhattan & Bronx | 5 | CONSTRUCTION TO 25% | 2023-10-23 | 2024-02-19 | 2023-10-23 | 2024-02-19
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPELIMMX | Repacked Complex Ped Ramps Installs - Manhattan & Bronx | 6 | CONSTRUCTION TO 50% | 2024-02-20 | 2024-06-18 | 2024-02-20 | 2024-06-18
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPELIMMX | Repacked Complex Ped Ramps Installs - Manhattan & Bronx | 7 | CONSTRUCTION TO 75% | 2024-06-19 | 2024-10-16 | 2024-06-19 | 2024-10-16
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPELIMMX | Repacked Complex Ped Ramps Installs - Manhattan & Bronx | 8 | ORIGINAL EQUIP & FURNISHING | 2024-10-17 | 2025-01-14 | 2024-10-17 | 2025-01-14
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPELIMMX | Repacked Complex Ped Ramps Installs - Manhattan & Bronx | 9 | SUBSTANTIAL COMPLETION | 2025-01-15 | 2025-03-15 | 2025-01-15 | 2025-03-15
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPELIMMX | Repacked Complex Ped Ramps Installs - Manhattan & Bronx | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-03-16 | 2025-04-14 | 2025-03-16 | 2025-04-14
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPELIMQR | Repacked Complex Ped Ramp Installs - Queens, Mnhn, & SI | 1 | DEVELOP SCOPE | 2022-06-30 | 2022-09-27 | 2022-06-30 | 2022-09-27
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPELIMQR | Repacked Complex Ped Ramp Installs - Queens, Mnhn, & SI | 2 | PRELIMINARY DESIGN | 2022-09-28 | 2023-01-25 | 2022-09-28 | 2023-01-25
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPELIMQR | Repacked Complex Ped Ramp Installs - Queens, Mnhn, & SI | 3 | FINAL DESIGN | 2023-01-26 | 2023-07-24 | 2023-01-26 | 2023-07-24
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPELIMQR | Repacked Complex Ped Ramp Installs - Queens, Mnhn, & SI | 4 | BID AWARD AND REGISTER CONTRCT | 2023-07-25 | 2023-10-22 | 2023-07-25 | 2023-10-22
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPELIMQR | Repacked Complex Ped Ramp Installs - Queens, Mnhn, & SI | 5 | CONSTRUCTION TO 25% | 2023-10-23 | 2024-02-19 | 2023-10-23 | 2024-02-19
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPELIMQR | Repacked Complex Ped Ramp Installs - Queens, Mnhn, & SI | 6 | CONSTRUCTION TO 50% | 2024-02-20 | 2024-06-18 | 2024-02-20 | 2024-06-18
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPELIMQR | Repacked Complex Ped Ramp Installs - Queens, Mnhn, & SI | 7 | CONSTRUCTION TO 75% | 2024-06-19 | 2024-10-16 | 2024-06-19 | 2024-10-16
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPELIMQR | Repacked Complex Ped Ramp Installs - Queens, Mnhn, & SI | 8 | ORIGINAL EQUIP & FURNISHING | 2024-10-17 | 2025-01-14 | 2024-10-17 | 2025-01-14
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPELIMQR | Repacked Complex Ped Ramp Installs - Queens, Mnhn, & SI | 9 | SUBSTANTIAL COMPLETION | 2025-01-15 | 2025-03-15 | 2025-01-15 | 2025-03-15
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPELIMQR | Repacked Complex Ped Ramp Installs - Queens, Mnhn, & SI | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-03-16 | 2025-04-14 | 2025-03-16 | 2025-04-14
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPELIMTA | Repacked Complex Ped Ramps (TA) | 1 | DEVELOP SCOPE | 2022-06-30 | 2022-09-27 | 2022-06-30 | 2022-09-27
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPELIMTA | Repacked Complex Ped Ramps (TA) | 2 | PRELIMINARY DESIGN | 2022-09-28 | 2023-01-25 | 2022-09-28 | 2023-01-25
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPELIMTA | Repacked Complex Ped Ramps (TA) | 3 | FINAL DESIGN | 2023-01-26 | 2023-07-24 | 2023-01-26 | 2023-07-24
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPELIMTA | Repacked Complex Ped Ramps (TA) | 4 | BID AWARD AND REGISTER CONTRCT | 2023-07-25 | 2023-10-22 | 2023-07-25 | 2023-10-22
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPELIMTA | Repacked Complex Ped Ramps (TA) | 5 | CONSTRUCTION TO 25% | 2023-10-23 | 2024-02-19 | 2023-10-23 | 2024-02-19
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPELIMTA | Repacked Complex Ped Ramps (TA) | 6 | CONSTRUCTION TO 50% | 2024-02-20 | 2024-06-18 | 2024-02-20 | 2024-06-18
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPELIMTA | Repacked Complex Ped Ramps (TA) | 7 | CONSTRUCTION TO 75% | 2024-06-19 | 2024-10-16 | 2024-06-19 | 2024-10-16
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPELIMTA | Repacked Complex Ped Ramps (TA) | 8 | ORIGINAL EQUIP & FURNISHING | 2024-10-17 | 2025-01-14 | 2024-10-17 | 2025-01-14
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPELIMTA | Repacked Complex Ped Ramps (TA) | 9 | SUBSTANTIAL COMPLETION | 2025-01-15 | 2025-03-15 | 2025-01-15 | 2025-03-15
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPELIMTA | Repacked Complex Ped Ramps (TA) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-03-16 | 2025-04-14 | 2025-03-16 | 2025-04-14
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPL20006 | PRIOR NOTICE SIDEWALK(SIM) | 1 | DEVELOP SCOPE | 2012-06-30 | 2012-09-27 | 2020-06-30 | 2020-09-27
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPL20006 | PRIOR NOTICE SIDEWALK(SIM) | 2 | PRELIMINARY DESIGN | 2012-09-28 | 2013-01-25 | 2020-09-28 | 2021-01-25
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPL20006 | PRIOR NOTICE SIDEWALK(SIM) | 3 | FINAL DESIGN | 2013-01-26 | 2013-07-24 | 2021-01-26 | 2021-07-24
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPL20006 | PRIOR NOTICE SIDEWALK(SIM) | 4 | BID AWARD AND REGISTER CONTRCT | 2013-07-25 | 2013-10-22 | 2021-07-25 | 2021-10-22
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPL20006 | PRIOR NOTICE SIDEWALK(SIM) | 5 | CONSTRUCTION TO 25% | 2013-10-23 | 2014-02-19 | 2021-10-23 | 2022-02-19
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPL20006 | PRIOR NOTICE SIDEWALK(SIM) | 6 | CONSTRUCTION TO 50% | 2014-02-20 | 2014-06-19 | 2022-02-20 | 2022-06-19
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPL20006 | PRIOR NOTICE SIDEWALK(SIM) | 7 | CONSTRUCTION TO 75% | 2014-06-20 | 2014-10-17 | 2022-06-20 | 2022-10-17
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPL20006 | PRIOR NOTICE SIDEWALK(SIM) | 8 | ORIGINAL EQUIP & FURNISHING | 2014-10-18 | 2015-01-15 | 2022-10-18 | 2023-01-15
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPL20006 | PRIOR NOTICE SIDEWALK(SIM) | 9 | SUBSTANTIAL COMPLETION | 2015-01-16 | 2015-03-16 | 2023-01-16 | 2023-03-16
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPL20006 | PRIOR NOTICE SIDEWALK(SIM) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-17 | 2015-04-15 | 2023-03-17 | 2023-04-15
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ015Q | Ozone Park Plaza | 1 | DEVELOP SCOPE | 2016-06-30 | 2016-09-27 | 2018-08-01 | 2022-02-26
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ015Q | Ozone Park Plaza | 2 | PRELIMINARY DESIGN | 2016-09-28 | 2017-01-25 | 2022-02-27 | 2022-06-26
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ015Q | Ozone Park Plaza | 3 | FINAL DESIGN | 2017-01-26 | 2017-07-24 | 2022-06-27 | 2022-12-23
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ015Q | Ozone Park Plaza | 4 | BID AWARD AND REGISTER CONTRCT | 2017-07-25 | 2017-10-22 | 2022-12-24 | 2023-03-23
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ015Q | Ozone Park Plaza | 5 | CONSTRUCTION TO 25% | 2017-10-23 | 2018-02-19 | 2023-03-24 | 2023-07-21
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ015Q | Ozone Park Plaza | 6 | CONSTRUCTION TO 50% | 2018-02-20 | 2018-06-19 | 2023-07-22 | 2023-11-18
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ015Q | Ozone Park Plaza | 7 | CONSTRUCTION TO 75% | 2018-06-20 | 2018-10-17 | 2023-11-19 | 2024-03-17
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ015Q | Ozone Park Plaza | 8 | ORIGINAL EQUIP & FURNISHING | 2018-10-18 | 2019-01-15 | 2024-03-18 | 2024-06-15
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ015Q | Ozone Park Plaza | 9 | SUBSTANTIAL COMPLETION | 2019-01-16 | 2019-03-16 | 2024-06-16 | 2024-08-14
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ015Q | Ozone Park Plaza | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-03-17 | 2019-04-15 | 2024-08-15 | 2024-09-13
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPRINSTL | Pedestrian Ramps Installation - Lump Sum | 1 | DEVELOP SCOPE | 2025-06-30 | 2025-09-27 | 2020-06-30 | 2020-09-27
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPRINSTL | Pedestrian Ramps Installation - Lump Sum | 2 | PRELIMINARY DESIGN | 2025-09-28 | 2026-01-25 | 2020-09-28 | 2021-01-25
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPRINSTL | Pedestrian Ramps Installation - Lump Sum | 3 | FINAL DESIGN | 2026-01-26 | 2026-07-24 | 2021-01-26 | 2021-07-24
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPRINSTL | Pedestrian Ramps Installation - Lump Sum | 4 | BID AWARD AND REGISTER CONTRCT | 2026-07-25 | 2026-10-22 | 2021-07-25 | 2021-10-22
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPRINSTL | Pedestrian Ramps Installation - Lump Sum | 5 | CONSTRUCTION TO 25% | 2026-10-23 | 2027-02-19 | 2021-10-23 | 2022-02-19
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPRINSTL | Pedestrian Ramps Installation - Lump Sum | 6 | CONSTRUCTION TO 50% | 2027-02-20 | 2027-06-19 | 2022-02-20 | 2022-06-19
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPRINSTL | Pedestrian Ramps Installation - Lump Sum | 7 | CONSTRUCTION TO 75% | 2027-06-20 | 2027-10-17 | 2022-06-20 | 2024-10-17
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPRINSTL | Pedestrian Ramps Installation - Lump Sum | 8 | ORIGINAL EQUIP & FURNISHING | 2027-10-18 | 2028-01-15 | 2024-10-18 | 2025-01-15
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPRINSTL | Pedestrian Ramps Installation - Lump Sum | 9 | SUBSTANTIAL COMPLETION | 2028-01-16 | 2028-03-15 | 2025-01-16 | 2025-03-16
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPRINSTL | Pedestrian Ramps Installation - Lump Sum | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2028-03-16 | 2028-04-14 | 2025-03-17 | 2029-04-15
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPRREHAB | Pedestrian Ramps Rehabilitation - Lump Sum | 1 | DEVELOP SCOPE | 2025-06-30 | 2025-09-27 | 2020-06-30 | 2020-09-27
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPRREHAB | Pedestrian Ramps Rehabilitation - Lump Sum | 2 | PRELIMINARY DESIGN | 2025-09-28 | 2026-01-25 | 2020-09-28 | 2021-01-25
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPRREHAB | Pedestrian Ramps Rehabilitation - Lump Sum | 3 | FINAL DESIGN | 2026-01-26 | 2026-07-24 | 2021-01-26 | 2021-07-24
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPRREHAB | Pedestrian Ramps Rehabilitation - Lump Sum | 4 | BID AWARD AND REGISTER CONTRCT | 2026-07-25 | 2026-10-22 | 2020-07-25 | 2024-10-22
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPRREHAB | Pedestrian Ramps Rehabilitation - Lump Sum | 5 | CONSTRUCTION TO 25% | 2026-10-23 | 2027-02-19 | 2026-10-23 | 2027-02-19
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPRREHAB | Pedestrian Ramps Rehabilitation - Lump Sum | 6 | CONSTRUCTION TO 50% | 2027-02-20 | 2027-06-19 | 2027-02-20 | 2027-06-19
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPRREHAB | Pedestrian Ramps Rehabilitation - Lump Sum | 7 | CONSTRUCTION TO 75% | 2027-06-20 | 2027-10-17 | 2027-06-20 | 2027-10-17
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPRREHAB | Pedestrian Ramps Rehabilitation - Lump Sum | 8 | ORIGINAL EQUIP & FURNISHING | 2027-10-18 | 2028-01-15 | 2021-10-18 | 2022-01-15
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPRREHAB | Pedestrian Ramps Rehabilitation - Lump Sum | 9 | SUBSTANTIAL COMPLETION | 2028-01-16 | 2028-03-15 | 2022-01-16 | 2022-03-16
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPRREHAB | Pedestrian Ramps Rehabilitation - Lump Sum | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2028-03-16 | 2028-04-14 | 2022-03-17 | 2026-02-14
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWRAP07 | RAP HAULING | 1 | DEVELOP SCOPE | 2012-06-30 | 2012-09-27 | 2020-06-30 | 2020-09-27
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWRAP07 | RAP HAULING | 2 | PRELIMINARY DESIGN | 2012-09-28 | 2013-01-25 | 2020-09-28 | 2021-01-25
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWRAP07 | RAP HAULING | 3 | FINAL DESIGN | 2013-01-26 | 2013-07-24 | 2021-01-26 | 2021-07-24
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWRAP07 | RAP HAULING | 4 | BID AWARD AND REGISTER CONTRCT | 2013-07-25 | 2013-10-22 | 2021-07-25 | 2021-10-22
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWRAP07 | RAP HAULING | 5 | CONSTRUCTION TO 25% | 2013-10-23 | 2014-02-19 | 2021-10-23 | 2022-02-19
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWRAP07 | RAP HAULING | 6 | CONSTRUCTION TO 50% | 2014-02-20 | 2014-06-19 | 2022-02-20 | 2022-06-19
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWRAP07 | RAP HAULING | 7 | CONSTRUCTION TO 75% | 2014-06-20 | 2014-10-17 | 2022-06-20 | 2022-10-17
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWRAP07 | RAP HAULING | 8 | ORIGINAL EQUIP & FURNISHING | 2014-10-18 | 2015-01-15 | 2022-10-18 | 2023-01-15
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWRAP07 | RAP HAULING | 9 | SUBSTANTIAL COMPLETION | 2015-01-16 | 2015-03-16 | 2023-01-16 | 2023-03-16
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWRAP07 | RAP HAULING | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-17 | 2015-04-15 | 2023-03-17 | 2023-04-15
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWS2021XM | PRIOR NOTICE SIDEWALK - BRONX & MANHATTAN | 1 | DEVELOP SCOPE | 2020-02-24 | 2020-03-24 | 2020-02-24 | 2020-03-24
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWS2021XM | PRIOR NOTICE SIDEWALK - BRONX & MANHATTAN | 2 | DESIGN START | 2020-03-25 | 2020-06-30 | 2020-03-25 | 2020-06-30
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWS2021XM | PRIOR NOTICE SIDEWALK - BRONX & MANHATTAN | 3 | CONSTRUCTION START | 2020-07-01 | 2021-06-20 | 2020-07-01 | 2021-06-20
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWSAFTR | Safe Routes to Transit | 1 | DEVELOP SCOPE | 2008-06-30 | 2008-10-27 | 2009-07-01 | 2009-10-28
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWSAFTR | Safe Routes to Transit | 2 | DESIGN START | 2008-10-28 | 2010-04-20 | 2009-10-29 | 2011-04-21
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWSAFTR | Safe Routes to Transit | 3 | CONSTRUCTION START | 2010-04-21 | 2012-04-09 | 2011-04-22 | 2027-06-30
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWSTEP04 | STEP STREET REHABILITATION | 1 | DEVELOP SCOPE | 2003-05-22 | 2003-08-19 | 2023-05-22 | 2023-08-19
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWSTEP04 | STEP STREET REHABILITATION | 2 | PRELIMINARY DESIGN | 2003-08-20 | 2003-12-17 | 2023-08-20 | 2023-12-17
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWSTEP04 | STEP STREET REHABILITATION | 3 | FINAL DESIGN | 2003-12-18 | 2004-06-14 | 2023-12-18 | 2024-06-14
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWSTEP04 | STEP STREET REHABILITATION | 4 | BID AWARD AND REGISTER CONTRCT | 2004-06-15 | 2004-09-12 | 2024-06-15 | 2024-09-12
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWSTEP04 | STEP STREET REHABILITATION | 5 | CONSTRUCTION TO 25% | 2004-09-13 | 2005-01-10 | 2024-09-13 | 2025-01-10
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWSTEP04 | STEP STREET REHABILITATION | 6 | CONSTRUCTION TO 50% | 2005-01-11 | 2005-05-10 | 2025-01-11 | 2025-05-10
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWSTEP04 | STEP STREET REHABILITATION | 7 | CONSTRUCTION TO 75% | 2005-05-11 | 2005-09-07 | 2025-05-11 | 2025-09-07
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWSTEP04 | STEP STREET REHABILITATION | 8 | ORIGINAL EQUIP & FURNISHING | 2005-09-08 | 2005-12-06 | 2025-09-08 | 2025-12-06
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWSTEP04 | STEP STREET REHABILITATION | 9 | SUBSTANTIAL COMPLETION | 2005-12-07 | 2006-02-04 | 2025-12-07 | 2026-02-04
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWSTEP04 | STEP STREET REHABILITATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2006-02-05 | 2006-03-06 | 2026-02-05 | 2026-03-06
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWTSQI | Public Plaza Improvements | 1 | DEVELOP SCOPE | 2008-06-30 | 2008-10-27 | 1993-07-01 | 1993-10-28
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWTSQI | Public Plaza Improvements | 2 | DESIGN START | 2008-10-28 | 2010-04-20 | 1993-10-29 | 1995-04-21
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWTSQI | Public Plaza Improvements | 3 | CONSTRUCTION START | 2010-04-21 | 2012-04-09 | 2025-04-20 | 2027-04-09
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | ITSBELTPK | Intelligent Transportation Systems on Belt Parkway X501.62 | 1 | BID AWARD AND REGISTER CONTRCT | 2020-06-30 | 2020-06-30 | 2020-06-30 | 2020-06-30
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | ITSBELTPK | Intelligent Transportation Systems on Belt Parkway X501.62 | 2 | CONSTRUCTION START | 2020-07-01 | 2020-08-14 | 2020-07-01 | 2020-08-14
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | ITSBELTPK | Intelligent Transportation Systems on Belt Parkway X501.62 | 3 | CONSTRUCTION COMPLETION | 2020-08-15 | 2022-03-07 | 2020-08-15 | 2022-03-07
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | MOLRETROF | MOLINARI CLASS UPGRADES-RETRO FIT | 1 | DEVELOP SCOPE | 2015-06-30 | 2016-06-28 | 2018-06-30 | 2019-06-29
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | MOLRETROF | MOLINARI CLASS UPGRADES-RETRO FIT | 2 | DESIGN START | 2016-06-29 | 2018-06-28 | 2019-06-30 | 2021-06-28
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | MOLRETROF | MOLINARI CLASS UPGRADES-RETRO FIT | 3 | CONSTRUCTION START | 2018-06-29 | 2020-06-27 | 2021-06-29 | 2023-06-28
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | NYCWINRPL | NYCWIN Replacement | 1 | BID AWARD AND REGISTER CONTRCT | 2018-06-30 | 2018-06-30 | 2019-08-22 | 2019-08-23
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | NYCWINRPL | NYCWIN Replacement | 2 | CONSTRUCTION START | 2018-07-01 | 2018-08-14 | 2019-10-07 | 2020-10-08
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | NYCWINRPL | NYCWIN Replacement | 3 | CONSTRUCTION COMPLETION | 2018-08-15 | 2020-03-06 | 2021-06-30 | 2029-07-21
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | PLANTRANS | TRANSIT SIGNAL PRIORITY-2030 | 1 | BID AWARD AND REGISTER CONTRCT | 2008-06-30 | 2008-06-30 | 2020-06-30 | 2020-06-30
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | PLANTRANS | TRANSIT SIGNAL PRIORITY-2030 | 2 | CONSTRUCTION START | 2008-07-01 | 2008-08-14 | 2020-07-01 | 2020-08-14
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | PLANTRANS | TRANSIT SIGNAL PRIORITY-2030 | 3 | CONSTRUCTION COMPLETION | 2008-08-15 | 2010-03-07 | 2020-08-15 | 2022-03-07
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | RTPIFY19 | REAL TIME PASSENGER INFO SIGNS - FY19 | 1 | BID AWARD AND REGISTER CONTRCT | 2018-06-30 | 2018-06-30 | 2020-06-30 | 2020-06-30
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | RTPIFY19 | REAL TIME PASSENGER INFO SIGNS - FY19 | 2 | CONSTRUCTION START | 2018-07-01 | 2018-08-14 | 2020-07-01 | 2020-08-14
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | RTPIFY19 | REAL TIME PASSENGER INFO SIGNS - FY19 | 3 | CONSTRUCTION COMPLETION | 2018-08-15 | 2020-03-06 | 2020-08-15 | 2022-03-07
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | RTPIFY20 | Real Time Passenger Info Signs FY20ADOP | 1 | BID AWARD AND REGISTER CONTRCT | 2019-06-30 | 2019-06-30 | 2020-06-30 | 2020-06-30
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | RTPIFY20 | Real Time Passenger Info Signs FY20ADOP | 2 | CONSTRUCTION START | 2019-07-01 | 2019-08-14 | 2020-07-01 | 2020-08-14
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | RTPIFY20 | Real Time Passenger Info Signs FY20ADOP | 3 | CONSTRUCTION COMPLETION | 2019-08-15 | 2021-03-06 | 2020-08-15 | 2022-03-07
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SAND-349R | Citywide In-House Resurfacing - Hurricane Sandy Recovery | 1 | DEVELOP SCOPE | 2013-06-30 | 2013-09-27 | 2019-06-30 | 2019-09-27
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SAND-349R | Citywide In-House Resurfacing - Hurricane Sandy Recovery | 2 | PRELIMINARY DESIGN | 2013-09-28 | 2014-01-25 | 2019-09-28 | 2020-01-25
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SAND-349R | Citywide In-House Resurfacing - Hurricane Sandy Recovery | 3 | FINAL DESIGN | 2014-01-26 | 2014-07-24 | 2020-01-26 | 2020-07-23
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SAND-349R | Citywide In-House Resurfacing - Hurricane Sandy Recovery | 4 | BID AWARD AND REGISTER CONTRCT | 2014-07-25 | 2014-10-22 | 2020-07-24 | 2020-10-21
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SAND-349R | Citywide In-House Resurfacing - Hurricane Sandy Recovery | 5 | CONSTRUCTION TO 25% | 2014-10-23 | 2015-02-19 | 2020-10-22 | 2021-02-18
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SAND-349R | Citywide In-House Resurfacing - Hurricane Sandy Recovery | 6 | CONSTRUCTION TO 50% | 2015-02-20 | 2015-06-19 | 2021-02-19 | 2021-06-18
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SAND-349R | Citywide In-House Resurfacing - Hurricane Sandy Recovery | 7 | CONSTRUCTION TO 75% | 2015-06-20 | 2015-10-17 | 2021-06-19 | 2021-10-16
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SAND-349R | Citywide In-House Resurfacing - Hurricane Sandy Recovery | 8 | ORIGINAL EQUIP & FURNISHING | 2015-10-18 | 2016-01-15 | 2021-10-17 | 2022-01-14
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SAND-349R | Citywide In-House Resurfacing - Hurricane Sandy Recovery | 9 | SUBSTANTIAL COMPLETION | 2016-01-16 | 2016-03-15 | 2022-01-15 | 2022-03-15
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SAND-349R | Citywide In-House Resurfacing - Hurricane Sandy Recovery | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-16 | 2016-04-14 | 2022-03-16 | 2022-04-14
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SANDCONDU | SANDY CONDUIT ADDITIONAL CITY-WIDE WORK | 1 | BID AWARD AND REGISTER CONTRCT | 2015-06-30 | 2015-06-30 | 2020-06-30 | 2020-06-30
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SANDCONDU | SANDY CONDUIT ADDITIONAL CITY-WIDE WORK | 2 | CONSTRUCTION START | 2015-07-01 | 2015-08-14 | 2020-07-01 | 2020-08-14
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SANDCONDU | SANDY CONDUIT ADDITIONAL CITY-WIDE WORK | 3 | CONSTRUCTION COMPLETION | 2015-08-15 | 2017-03-06 | 2020-08-15 | 2022-03-07
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SANDHB002 | Rehab of Movable Bridges Citywide - Sandy | 1 | DEVELOP SCOPE | 2013-06-30 | 2014-06-29 | 0 | 0
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SANDHB002 | Rehab of Movable Bridges Citywide - Sandy | 2 | DEVELOP SCOPE | 2014-06-30 | 2018-06-28 | 2014-10-29 | 2014-10-30
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SANDHB002 | Rehab of Movable Bridges Citywide - Sandy | 3 | DESIGN START | 2018-06-29 | 2020-06-27 | 2014-10-31 | 2018-10-29
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SANDHB002 | Rehab of Movable Bridges Citywide - Sandy | 5 | CONSTRUCTION START | 2018-06-29 | 2020-06-27 | 2018-10-30 | 2020-10-28
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SANDRF05 | Construction of New Ferryboats | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-09-28 | 2011-05-31 | 2014-07-01
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SANDRF05 | Construction of New Ferryboats | 2 | PRELIMINARY DESIGN | 2016-09-29 | 2017-01-26 | 2014-10-16 | 2015-02-26
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SANDRF05 | Construction of New Ferryboats | 3 | FINAL DESIGN | 2017-01-27 | 2017-07-25 | 2015-08-31 | 2015-11-24
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SANDRF05 | Construction of New Ferryboats | 4 | BID AWARD AND REGISTER CONTRCT | 2017-07-26 | 2017-10-23 | 2016-05-18 | 2021-02-19
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SANDRF05 | Construction of New Ferryboats | 5 | CONSTRUCTION TO 25% | 2017-10-24 | 2018-02-20 | 2017-03-01 | 2018-01-15
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SANDRF05 | Construction of New Ferryboats | 6 | CONSTRUCTION TO 50% | 2018-02-21 | 2018-06-20 | 2018-01-15 | 2019-02-25
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SANDRF05 | Construction of New Ferryboats | 7 | CONSTRUCTION TO 75% | 2018-06-21 | 2018-10-18 | 2019-02-26 | 2020-01-15
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SANDRF05 | Construction of New Ferryboats | 8 | ORIGINAL EQUIP & FURNISHING | 2018-10-19 | 2019-01-16 | 2020-01-16 | 2020-04-14
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SANDRF05 | Construction of New Ferryboats | 9 | SUBSTANTIAL COMPLETION | 2019-01-17 | 2019-03-17 | 2021-08-26 | 2022-08-25
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SANDRF05 | Construction of New Ferryboats | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-03-18 | 2019-04-16 | 2025-02-17 | 2025-02-17
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SANDRF07 | SEVERE WEATHER MOORING UPGRADE | 1 | DEVELOP SCOPE | 2017-06-30 | 2018-06-29 | 2017-06-30 | 2018-06-29
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SANDRF07 | SEVERE WEATHER MOORING UPGRADE | 2 | DESIGN START | 2018-06-30 | 2020-06-28 | 2018-06-30 | 2020-06-28
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SANDRF07 | SEVERE WEATHER MOORING UPGRADE | 3 | CONSTRUCTION START | 2020-06-29 | 2022-06-28 | 2020-06-29 | 2022-06-28
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SANDRF10 | ROCK-SOCKETED STEEL MOORING PILES | 1 | DEVELOP SCOPE | 2018-06-30 | 2019-06-29 | 2018-06-30 | 2019-06-29
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SANDRF10 | ROCK-SOCKETED STEEL MOORING PILES | 2 | DESIGN START | 2019-06-30 | 2021-06-28 | 2019-06-30 | 2021-06-28
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SANDRF10 | ROCK-SOCKETED STEEL MOORING PILES | 3 | CONSTRUCTION START | 2021-06-29 | 2023-06-28 | 2021-06-29 | 2023-06-28
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SANDRF11 | Ferry Terminal Floodproofing | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-09-28 | 2018-11-25 | 2020-05-04
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SANDRF11 | Ferry Terminal Floodproofing | 2 | PRELIMINARY DESIGN | 2016-09-29 | 2017-01-26 | 2020-05-05 | 2020-09-01
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SANDRF11 | Ferry Terminal Floodproofing | 3 | FINAL DESIGN | 2017-01-27 | 2017-07-25 | 2020-09-02 | 2021-02-28
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SANDRF11 | Ferry Terminal Floodproofing | 4 | BID AWARD AND REGISTER CONTRCT | 2017-07-26 | 2017-10-23 | 2021-03-01 | 2021-05-29
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SANDRF11 | Ferry Terminal Floodproofing | 5 | CONSTRUCTION TO 25% | 2017-10-24 | 2018-02-20 | 2021-05-30 | 2021-09-26
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SANDRF11 | Ferry Terminal Floodproofing | 6 | CONSTRUCTION TO 50% | 2018-02-21 | 2018-06-20 | 2021-09-27 | 2022-01-24
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SANDRF11 | Ferry Terminal Floodproofing | 7 | CONSTRUCTION TO 75% | 2018-06-21 | 2018-10-18 | 2022-01-25 | 2022-05-24
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SANDRF11 | Ferry Terminal Floodproofing | 8 | ORIGINAL EQUIP & FURNISHING | 2018-10-19 | 2019-01-16 | 2022-05-25 | 2022-08-22
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SANDRF11 | Ferry Terminal Floodproofing | 9 | SUBSTANTIAL COMPLETION | 2019-01-17 | 2019-03-17 | 2022-08-23 | 2022-10-21
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SANDRF11 | Ferry Terminal Floodproofing | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-03-18 | 2019-04-16 | 2022-10-22 | 2022-11-20
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SEQUEENS | South East Queens Initiative | 1 | DEVELOP SCOPE | 2020-06-30 | 2020-09-27 | 2023-06-30 | 2023-09-27
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SEQUEENS | South East Queens Initiative | 2 | PRELIMINARY DESIGN | 2020-09-28 | 2021-01-25 | 2023-09-28 | 2024-01-25
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SEQUEENS | South East Queens Initiative | 3 | FINAL DESIGN | 2021-01-26 | 2021-07-24 | 2024-01-26 | 2024-07-23
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SEQUEENS | South East Queens Initiative | 4 | BID AWARD AND REGISTER CONTRCT | 2021-07-25 | 2021-10-22 | 2024-07-24 | 2024-10-21
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SEQUEENS | South East Queens Initiative | 5 | CONSTRUCTION TO 25% | 2021-10-23 | 2022-02-19 | 2024-10-22 | 2025-02-18
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SEQUEENS | South East Queens Initiative | 6 | CONSTRUCTION TO 50% | 2022-02-20 | 2022-06-19 | 2025-02-19 | 2025-06-18
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SEQUEENS | South East Queens Initiative | 7 | CONSTRUCTION TO 75% | 2022-06-20 | 2022-10-17 | 2025-06-19 | 2025-10-16
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SEQUEENS | South East Queens Initiative | 8 | ORIGINAL EQUIP & FURNISHING | 2022-10-18 | 2023-01-15 | 2025-10-17 | 2026-01-14
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SEQUEENS | South East Queens Initiative | 9 | SUBSTANTIAL COMPLETION | 2023-01-16 | 2023-03-16 | 2026-01-15 | 2026-03-15
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SEQUEENS | South East Queens Initiative | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-03-17 | 2023-04-15 | 2026-03-16 | 2028-06-29
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SIGNALSF2 | TRAFFIC SIGNAL SAFETY, CITYWIDE | 1 | BID AWARD AND REGISTER CONTRCT | 2019-06-30 | 2019-06-30 | 2020-06-30 | 2020-06-30
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SIGNALSF2 | TRAFFIC SIGNAL SAFETY, CITYWIDE | 2 | CONSTRUCTION START | 2019-07-01 | 2019-08-14 | 2020-07-01 | 2020-08-14
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SIGNALSF2 | TRAFFIC SIGNAL SAFETY, CITYWIDE | 3 | CONSTRUCTION COMPLETION | 2019-08-15 | 2021-03-06 | 2020-08-15 | 2022-03-07
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SLMNTLUMP | CAPITAL COMPONENT STREETLIGHT MAINTENANCE (TEN YR PLAN) | 1 | BID AWARD AND REGISTER CONTRCT | 2012-05-15 | 2012-05-15 | 2022-05-15 | 2022-05-15
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SLMNTLUMP | CAPITAL COMPONENT STREETLIGHT MAINTENANCE (TEN YR PLAN) | 2 | CONSTRUCTION START | 2012-05-16 | 2012-06-29 | 2022-05-16 | 2022-06-29
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SLMNTLUMP | CAPITAL COMPONENT STREETLIGHT MAINTENANCE (TEN YR PLAN) | 3 | CONSTRUCTION COMPLETION | 2012-06-30 | 2014-01-20 | 2022-06-30 | 2024-01-20
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | STEFFSCMV | NYC Street Efficiency Strategic Commercial Vehicle Monitorin | 1 | BID AWARD AND REGISTER CONTRCT | 2019-06-30 | 2019-06-30 | 2022-06-30 | 2022-06-30
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | STEFFSCMV | NYC Street Efficiency Strategic Commercial Vehicle Monitorin | 2 | CONSTRUCTION START | 2019-07-01 | 2019-08-14 | 2022-07-01 | 2022-08-14
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | STEFFSCMV | NYC Street Efficiency Strategic Commercial Vehicle Monitorin | 3 | CONSTRUCTION COMPLETION | 2019-08-15 | 2021-03-06 | 2022-08-15 | 2024-03-06
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TF012013 | NEW SIGNAL INSTALLATION REQUIREMENT CONTRACT FY13 | 1 | BID AWARD AND REGISTER CONTRCT | 2013-06-30 | 2013-06-30 | 2019-06-29 | 2019-06-30
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TF012013 | NEW SIGNAL INSTALLATION REQUIREMENT CONTRACT FY13 | 2 | CONSTRUCTION START | 2013-07-01 | 2013-08-14 | 2019-07-01 | 2019-08-14
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TF012013 | NEW SIGNAL INSTALLATION REQUIREMENT CONTRACT FY13 | 3 | CONSTRUCTION COMPLETION | 2013-08-15 | 2015-03-07 | 2019-08-15 | 2025-03-06
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TF012014 | NEW SIGNALS INSTALLATION REQUIREMENT | 1 | BID AWARD AND REGISTER CONTRCT | 2015-06-01 | 2015-06-01 | 2023-06-01 | 2023-06-03
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TF012014 | NEW SIGNALS INSTALLATION REQUIREMENT | 2 | CONSTRUCTION START | 2015-06-02 | 2015-07-16 | 2023-06-04 | 2023-07-18
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TF012014 | NEW SIGNALS INSTALLATION REQUIREMENT | 3 | CONSTRUCTION COMPLETION | 2015-07-17 | 2017-02-05 | 2023-07-19 | 2025-02-07
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TF012017 | NEW SIGNALS INSTALLATION REQUIREMENT FY17 | 1 | BID AWARD AND REGISTER CONTRCT | 2017-06-30 | 2017-06-30 | 2024-06-30 | 2024-07-01
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TF012017 | NEW SIGNALS INSTALLATION REQUIREMENT FY17 | 2 | CONSTRUCTION START | 2017-07-01 | 2017-08-14 | 2024-07-02 | 2024-08-15
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TF012017 | NEW SIGNALS INSTALLATION REQUIREMENT FY17 | 3 | CONSTRUCTION COMPLETION | 2017-08-15 | 2019-03-07 | 2024-08-16 | 2026-03-08
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TF012019 | NEW SIGNALS INSTALLATION REQUIREMENT 2019 | 1 | BID AWARD AND REGISTER CONTRCT | 2018-06-30 | 2018-06-30 | 2021-06-30 | 2021-06-30
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TF012019 | NEW SIGNALS INSTALLATION REQUIREMENT 2019 | 2 | CONSTRUCTION START | 2018-07-01 | 2018-08-14 | 2021-07-01 | 2021-08-14
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TF012019 | NEW SIGNALS INSTALLATION REQUIREMENT 2019 | 3 | CONSTRUCTION COMPLETION | 2018-08-15 | 2020-03-06 | 2021-08-15 | 2023-03-07
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TF01-9910 | LOCAL STREET NETWORK MGMT AND INCIDENT MGMT X500.94 | 1 | BID AWARD AND REGISTER CONTRCT | 2004-06-15 | 2004-06-15 | 2020-06-15 | 2020-06-15
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TF01-9910 | LOCAL STREET NETWORK MGMT AND INCIDENT MGMT X500.94 | 2 | CONSTRUCTION START | 2004-06-16 | 2004-07-30 | 2020-06-16 | 2020-07-30
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TF01-9910 | LOCAL STREET NETWORK MGMT AND INCIDENT MGMT X500.94 | 3 | CONSTRUCTION COMPLETION | 2004-07-31 | 2006-02-20 | 2020-07-31 | 2022-02-20
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TF01-9911 | Advance Travel Information System Upgrade | 1 | BID AWARD AND REGISTER CONTRCT | 2022-06-30 | 2022-06-30 | 2020-06-30 | 2020-06-30
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TF01-9911 | Advance Travel Information System Upgrade | 2 | CONSTRUCTION START | 2022-07-01 | 2022-08-14 | 2020-07-01 | 2020-08-14
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TF01-9911 | Advance Travel Information System Upgrade | 3 | CONSTRUCTION COMPLETION | 2022-08-15 | 2024-03-06 | 2020-08-15 | 2022-03-07
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TF01APS | Accessible Pedestrian System(AT 75 LOCATIONS PER YEAR) | 1 | BID AWARD AND REGISTER CONTRCT | 2019-06-30 | 2019-06-30 | 2022-06-30 | 2022-06-30
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TF01APS | Accessible Pedestrian System(AT 75 LOCATIONS PER YEAR) | 2 | CONSTRUCTION START | 2019-07-01 | 2019-08-14 | 2022-07-01 | 2022-08-14
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TF01APS | Accessible Pedestrian System(AT 75 LOCATIONS PER YEAR) | 3 | CONSTRUCTION COMPLETION | 2019-08-15 | 2021-03-06 | 2022-08-15 | 2024-03-06
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TF01RL5 | RED LIGHT CAMERAS | 1 | BID AWARD AND REGISTER CONTRCT | 2014-06-01 | 2014-06-01 | 2021-06-01 | 2021-06-01
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TF01RL5 | RED LIGHT CAMERAS | 2 | CONSTRUCTION START | 2014-06-02 | 2014-07-16 | 2021-06-02 | 2021-07-16
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TF01RL5 | RED LIGHT CAMERAS | 3 | CONSTRUCTION COMPLETION | 2014-07-17 | 2016-02-06 | 2021-07-17 | 2025-06-30
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TF01TPM18 | Thermoplastic Markings -FY18 | 1 | BID AWARD AND REGISTER CONTRCT | 2016-06-30 | 2016-06-30 | 2019-06-30 | 2019-06-30
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TF01TPM18 | Thermoplastic Markings -FY18 | 2 | CONSTRUCTION START | 2016-07-01 | 2016-08-14 | 2019-07-01 | 2019-08-14
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TF01TPM18 | Thermoplastic Markings -FY18 | 3 | CONSTRUCTION COMPLETION | 2016-08-15 | 2018-03-07 | 2019-08-15 | 2021-03-06
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TF01TPM21 | Thermoplastic Marking-FY21 | 1 | BID AWARD AND REGISTER CONTRCT | 2022-03-20 | 2022-03-20 | 2022-03-20 | 2022-03-20
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TF01TPM21 | Thermoplastic Marking-FY21 | 2 | CONSTRUCTION START | 2022-03-21 | 2022-05-04 | 2022-03-21 | 2022-05-04
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TF01TPM21 | Thermoplastic Marking-FY21 | 3 | CONSTRUCTION COMPLETION | 2022-05-05 | 2023-06-30 | 2022-05-05 | 2023-06-30
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TF01VARMS | Variable Message Signs Replacement, Citywide | 1 | BID AWARD AND REGISTER CONTRCT | 2020-06-30 | 2020-06-30 | 2020-06-30 | 2020-06-30
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TF01VARMS | Variable Message Signs Replacement, Citywide | 2 | CONSTRUCTION START | 2020-07-01 | 2020-08-14 | 2020-07-01 | 2020-08-14
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TF01VARMS | Variable Message Signs Replacement, Citywide | 3 | CONSTRUCTION COMPLETION | 2020-08-15 | 2022-03-07 | 2020-08-15 | 2022-03-07
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TF18-LUMP | LUMP SUM FOR PARKING RECONSTRUCTION | 1 | BID AWARD AND REGISTER CONTRCT | 2008-06-30 | 2008-06-30 | 2020-06-30 | 2020-06-30
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TF18-LUMP | LUMP SUM FOR PARKING RECONSTRUCTION | 2 | CONSTRUCTION START | 2008-07-01 | 2008-08-14 | 2020-07-01 | 2020-08-14
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TF18-LUMP | LUMP SUM FOR PARKING RECONSTRUCTION | 3 | CONSTRUCTION COMPLETION | 2008-08-15 | 2010-03-07 | 2020-08-15 | 2028-03-07
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFAPEDSY3 | Accessible Pedestrian System-Retrofit | 1 | BID AWARD AND REGISTER CONTRCT | 2019-06-30 | 2019-06-30 | 2019-06-30 | 2019-06-30
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFAPEDSY3 | Accessible Pedestrian System-Retrofit | 2 | CONSTRUCTION START | 2019-07-01 | 2019-08-14 | 2019-07-01 | 2019-08-14
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFAPEDSY3 | Accessible Pedestrian System-Retrofit | 3 | CONSTRUCTION COMPLETION | 2019-08-15 | 2021-03-06 | 2019-08-15 | 2022-04-12
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFAPSLUMP | Accessible Pedestrian Signals, TEN YEARS | 1 | BID AWARD AND REGISTER CONTRCT | 2019-06-30 | 2019-06-30 | 2019-06-30 | 2019-06-30
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFAPSLUMP | Accessible Pedestrian Signals, TEN YEARS | 2 | CONSTRUCTION START | 2019-07-01 | 2019-08-14 | 2019-07-01 | 2019-08-14
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFAPSLUMP | Accessible Pedestrian Signals, TEN YEARS | 3 | CONSTRUCTION COMPLETION | 2019-08-15 | 2021-03-06 | 2019-08-15 | 2023-06-30
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFCORRBAS | Replacement of Corroded Street light and Signal Poles | 1 | BID AWARD AND REGISTER CONTRCT | 2020-02-24 | 2020-02-24 | 2020-02-24 | 2020-02-24
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFCORRBAS | Replacement of Corroded Street light and Signal Poles | 2 | CONSTRUCTION START | 2020-02-25 | 2020-04-09 | 2020-02-25 | 2020-04-09
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFCORRBAS | Replacement of Corroded Street light and Signal Poles | 3 | CONSTRUCTION COMPLETION | 2020-04-10 | 2022-04-24 | 2020-04-10 | 2022-04-24
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFCWSBST | SBS-Citywide Real Time Totem System | 1 | DEVELOP SCOPE | 2017-06-30 | 2017-09-27 | 2017-06-30 | 2017-09-27
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFCWSBST | SBS-Citywide Real Time Totem System | 2 | PRELIMINARY DESIGN | 2017-09-28 | 2018-01-25 | 2017-09-28 | 2018-01-25
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFCWSBST | SBS-Citywide Real Time Totem System | 3 | FINAL DESIGN | 2018-01-26 | 2018-07-24 | 2018-01-26 | 2018-07-24
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFCWSBST | SBS-Citywide Real Time Totem System | 4 | BID AWARD AND REGISTER CONTRCT | 2018-07-25 | 2018-10-22 | 2018-07-25 | 2018-10-22
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFCWSBST | SBS-Citywide Real Time Totem System | 5 | CONSTRUCTION TO 25% | 2018-10-23 | 2019-02-19 | 2018-10-23 | 2019-02-19
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFCWSBST | SBS-Citywide Real Time Totem System | 6 | CONSTRUCTION TO 50% | 2019-02-20 | 2019-06-19 | 2019-02-20 | 2019-06-19
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFCWSBST | SBS-Citywide Real Time Totem System | 7 | CONSTRUCTION TO 75% | 2019-06-20 | 2019-10-17 | 2019-06-20 | 2019-10-17
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFCWSBST | SBS-Citywide Real Time Totem System | 8 | ORIGINAL EQUIP & FURNISHING | 2019-10-18 | 2020-01-15 | 2019-10-18 | 2020-01-15
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFCWSBST | SBS-Citywide Real Time Totem System | 9 | SUBSTANTIAL COMPLETION | 2020-01-16 | 2020-03-15 | 2020-01-16 | 2020-03-15
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFCWSBST | SBS-Citywide Real Time Totem System | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-03-16 | 2022-04-14 | 2020-03-16 | 2022-04-14
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFITSAMS | INTELLIGENT TRANSPORTATION SYSTEM(ITS) ON HIGHWAYS | 1 | BID AWARD AND REGISTER CONTRCT | 2009-06-30 | 2009-06-30 | 2020-06-30 | 2020-06-30
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFITSAMS | INTELLIGENT TRANSPORTATION SYSTEM(ITS) ON HIGHWAYS | 2 | CONSTRUCTION START | 2009-07-01 | 2009-08-14 | 2020-07-01 | 2020-08-14
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFITSAMS | INTELLIGENT TRANSPORTATION SYSTEM(ITS) ON HIGHWAYS | 3 | CONSTRUCTION COMPLETION | 2009-08-15 | 2011-03-07 | 2020-08-15 | 2022-03-07
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFLGUDECK | Lighting at underdeck Structure, citywide | 1 | BID AWARD AND REGISTER CONTRCT | 2020-06-30 | 2020-06-30 | 2022-06-30 | 2022-06-30
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFLGUDECK | Lighting at underdeck Structure, citywide | 2 | CONSTRUCTION START | 2020-07-01 | 2020-08-14 | 2022-07-01 | 2022-08-14
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFLGUDECK | Lighting at underdeck Structure, citywide | 3 | CONSTRUCTION COMPLETION | 2020-08-15 | 2022-03-07 | 2022-08-15 | 2024-03-06
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFLGUSBWY | Furnish and Install Lighting under elevated structures | 1 | BID AWARD AND REGISTER CONTRCT | 2020-06-30 | 2020-06-30 | 2018-10-12 | 2018-12-14
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFLGUSBWY | Furnish and Install Lighting under elevated structures | 2 | CONSTRUCTION START | 2020-07-01 | 2020-08-14 | 2018-12-15 | 2019-01-28
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFLGUSBWY | Furnish and Install Lighting under elevated structures | 3 | CONSTRUCTION COMPLETION | 2020-08-15 | 2022-03-07 | 2019-01-29 | 2024-08-20
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFMARKLMP | THERMOPLASTIC MARKINGS-TEN YEARS | 1 | BID AWARD AND REGISTER CONTRCT | 2013-06-30 | 2013-06-30 | 2021-06-30 | 2021-06-30
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFMARKLMP | THERMOPLASTIC MARKINGS-TEN YEARS | 2 | CONSTRUCTION START | 2013-07-01 | 2013-08-14 | 2021-07-01 | 2021-08-14
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFMARKLMP | THERMOPLASTIC MARKINGS-TEN YEARS | 3 | CONSTRUCTION COMPLETION | 2013-08-15 | 2015-03-07 | 2021-08-15 | 2023-03-06
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFPEDCDW3 | Furnish and install Pedestrian Countdown Clocks | 1 | BID AWARD AND REGISTER CONTRCT | 2020-06-30 | 2020-06-30 | 2019-08-22 | 2020-01-23
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFPEDCDW3 | Furnish and install Pedestrian Countdown Clocks | 2 | CONSTRUCTION START | 2020-07-01 | 2020-08-14 | 2020-03-21 | 2020-04-20
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFPEDCDW3 | Furnish and install Pedestrian Countdown Clocks | 3 | CONSTRUCTION COMPLETION | 2020-08-15 | 2022-03-07 | 2020-04-21 | 2026-06-30
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFPWSIGNL | PROACTIVE WARRANT NEW SIGNALS INSTALLATION | 1 | BID AWARD AND REGISTER CONTRCT | 2019-06-30 | 2019-06-30 | 2019-06-30 | 2019-06-30
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFPWSIGNL | PROACTIVE WARRANT NEW SIGNALS INSTALLATION | 2 | CONSTRUCTION START | 2019-07-01 | 2019-08-14 | 2019-07-01 | 2019-08-14
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFPWSIGNL | PROACTIVE WARRANT NEW SIGNALS INSTALLATION | 3 | CONSTRUCTION COMPLETION | 2019-08-15 | 2021-03-06 | 2019-08-15 | 2021-03-06
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFSPDCAM | Purchase and Install Speed Cameras in School Zones Areas | 1 | BID AWARD AND REGISTER CONTRCT | 2014-06-01 | 2014-06-01 | 2020-06-01 | 2020-06-01
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFSPDCAM | Purchase and Install Speed Cameras in School Zones Areas | 2 | CONSTRUCTION START | 2014-06-02 | 2014-07-16 | 2020-06-02 | 2020-07-16
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFSPDCAM | Purchase and Install Speed Cameras in School Zones Areas | 3 | CONSTRUCTION COMPLETION | 2014-07-17 | 2016-02-06 | 2020-07-17 | 2022-02-06
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFVISIONZ | Traffic Vision Zero projects-St Light Enhancement | 1 | BID AWARD AND REGISTER CONTRCT | 2016-06-30 | 2016-06-30 | 2019-06-30 | 2019-06-30
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFVISIONZ | Traffic Vision Zero projects-St Light Enhancement | 2 | CONSTRUCTION START | 2016-07-01 | 2016-08-14 | 2019-07-01 | 2019-08-14
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFVISIONZ | Traffic Vision Zero projects-St Light Enhancement | 3 | CONSTRUCTION COMPLETION | 2016-08-15 | 2018-03-07 | 2019-08-15 | 2027-03-06
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TRNCHREST | Trench Restoration | 1 | DEVELOP SCOPE | 2017-06-30 | 2017-09-27 | 2019-06-30 | 2019-09-27
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TRNCHREST | Trench Restoration | 2 | PRELIMINARY DESIGN | 2017-09-28 | 2018-01-25 | 2019-09-28 | 2020-01-25
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TRNCHREST | Trench Restoration | 3 | FINAL DESIGN | 2018-01-26 | 2018-07-24 | 2020-01-26 | 2020-07-23
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TRNCHREST | Trench Restoration | 4 | BID AWARD AND REGISTER CONTRCT | 2018-07-25 | 2018-10-22 | 2020-07-24 | 2020-10-21
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TRNCHREST | Trench Restoration | 5 | CONSTRUCTION TO 25% | 2018-10-23 | 2019-02-19 | 2020-10-22 | 2021-02-18
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TRNCHREST | Trench Restoration | 6 | CONSTRUCTION TO 50% | 2019-02-20 | 2019-06-19 | 2021-02-19 | 2021-06-18
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TRNCHREST | Trench Restoration | 7 | CONSTRUCTION TO 75% | 2019-06-20 | 2019-10-17 | 2021-06-19 | 2021-10-16
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TRNCHREST | Trench Restoration | 8 | ORIGINAL EQUIP & FURNISHING | 2019-10-18 | 2020-01-15 | 2021-10-17 | 2022-01-14
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TRNCHREST | Trench Restoration | 9 | SUBSTANTIAL COMPLETION | 2020-01-16 | 2020-03-15 | 2022-01-15 | 2022-03-15
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TRNCHREST | Trench Restoration | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-03-16 | 2020-04-14 | 2022-03-16 | 2026-04-14
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TYPLILL | STREET LIGHTING <TEN YEAR PLAN) | 1 | BID AWARD AND REGISTER CONTRCT | 2015-06-01 | 2015-06-01 | 2023-06-01 | 2023-06-01
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TYPLILL | STREET LIGHTING <TEN YEAR PLAN) | 2 | CONSTRUCTION START | 2015-06-02 | 2015-07-16 | 2023-06-02 | 2023-07-16
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TYPLILL | STREET LIGHTING <TEN YEAR PLAN) | 3 | CONSTRUCTION COMPLETION | 2015-07-17 | 2017-02-05 | 2023-07-17 | 2025-02-05
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TYPLREP | TRAFFIC PARK & HIGHWAY DISTRIBUTION(TEN YEAR PLAN) | 1 | BID AWARD AND REGISTER CONTRCT | 2019-06-01 | 2019-06-01 | 2022-06-01 | 2022-06-01
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TYPLREP | TRAFFIC PARK & HIGHWAY DISTRIBUTION(TEN YEAR PLAN) | 2 | CONSTRUCTION START | 2019-06-02 | 2019-07-16 | 2022-06-02 | 2022-07-16
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TYPLREP | TRAFFIC PARK & HIGHWAY DISTRIBUTION(TEN YEAR PLAN) | 3 | CONSTRUCTION COMPLETION | 2019-07-17 | 2021-02-05 | 2022-07-17 | 2024-02-06
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TYPLSGM | TRAFFIC SIGNALS (TEN YEAR PLAN) | 1 | BID AWARD AND REGISTER CONTRCT | 2015-06-01 | 2015-06-01 | 2021-06-01 | 2021-06-01
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TYPLSGM | TRAFFIC SIGNALS (TEN YEAR PLAN) | 2 | CONSTRUCTION START | 2015-06-02 | 2015-07-16 | 2021-06-02 | 2021-07-16
20201123 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TYPLSGM | TRAFFIC SIGNALS (TEN YEAR PLAN) | 3 | CONSTRUCTION COMPLETION | 2015-07-17 | 2017-02-05 | 2021-07-17 | 2023-02-06
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | ACEDPR402 | LIGHTING | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2013-09-28
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | ACEDPR402 | LIGHTING | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2013-09-29 | 2013-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | ACEDPR402 | LIGHTING | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2013-12-28 | 2014-03-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | ACEDPR402 | LIGHTING | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2014-03-28 | 2015-03-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | ACEDPR402 | LIGHTING | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2019-03-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | ACEDPR403 | DPR efficient lighting @various facilities 5bor CNYG-2415MA1 | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | ACEDPR403 | DPR efficient lighting @various facilities 5bor CNYG-2415MA1 | 2 | DESIGN | 2016-12-28 | 2018-06-25 | 2016-12-28 | 2018-06-25
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | ACEDPR403 | DPR efficient lighting @various facilities 5bor CNYG-2415MA1 | 3 | BID/ REGISTER CONTRACT | 2018-06-26 | 2019-03-22 | 2018-06-26 | 2019-03-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | ACEDPR403 | DPR efficient lighting @various facilities 5bor CNYG-2415MA1 | 4 | CONSTRUCTION | 2019-03-23 | 2020-09-17 | 2019-03-23 | 2020-09-17
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | ACEDPR403 | DPR efficient lighting @various facilities 5bor CNYG-2415MA1 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-18 | 2021-09-17 | 2020-09-18 | 2021-09-17
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | ACEDPR404 | DPR efficient lighting @ ballfields SI & Q CNYG-2815M | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2015-09-28
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | ACEDPR404 | DPR efficient lighting @ ballfields SI & Q CNYG-2815M | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2015-09-29 | 2015-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | ACEDPR404 | DPR efficient lighting @ ballfields SI & Q CNYG-2815M | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2015-12-28 | 2016-03-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | ACEDPR404 | DPR efficient lighting @ ballfields SI & Q CNYG-2815M | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | ACEDPR404 | DPR efficient lighting @ ballfields SI & Q CNYG-2815M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2017-03-27 | 2018-03-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | ACEDPR405 | DPR efficient lighting @ ballfields MN, BK & BX CNYG-2915 | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2015-09-28
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | ACEDPR405 | DPR efficient lighting @ ballfields MN, BK & BX CNYG-2915 | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2015-09-29 | 2015-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | ACEDPR405 | DPR efficient lighting @ ballfields MN, BK & BX CNYG-2915 | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2015-12-28 | 2016-03-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | ACEDPR405 | DPR efficient lighting @ ballfields MN, BK & BX CNYG-2915 | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | ACEDPR405 | DPR efficient lighting @ ballfields MN, BK & BX CNYG-2915 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2017-03-27 | 2018-03-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | GXBXBKQ1 | GI Citywide-Bioswales in Parks Bronx, Queens & Brooklyn | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | GXBXBKQ1 | GI Citywide-Bioswales in Parks Bronx, Queens & Brooklyn | 2 | DESIGN | 2017-12-28 | 2019-06-20 | 2017-12-28 | 2019-06-20
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | GXBXBKQ1 | GI Citywide-Bioswales in Parks Bronx, Queens & Brooklyn | 3 | BID/ REGISTER CONTRACT | 2019-06-21 | 2020-03-16 | 2019-06-21 | 2020-03-16
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | GXBXBKQ1 | GI Citywide-Bioswales in Parks Bronx, Queens & Brooklyn | 4 | CONSTRUCTION | 2020-03-17 | 2021-03-16 | 2020-03-17 | 2021-03-16
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | GXBXBKQ1 | GI Citywide-Bioswales in Parks Bronx, Queens & Brooklyn | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-17 | 2023-03-16 | 2021-03-17 | 2023-03-16
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-3ALRMMN | Manhattan - Fire Alarm | 1 | DEVELOP SCOPE | 2014-07-01 | 2014-09-28 | 2014-07-01 | 2014-09-28
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-3ALRMMN | Manhattan - Fire Alarm | 2 | DESIGN | 2014-09-29 | 2014-12-27 | 2014-09-29 | 2014-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-3ALRMMN | Manhattan - Fire Alarm | 3 | BID/ REGISTER CONTRACT | 2014-12-28 | 2015-03-27 | 2014-12-28 | 2015-03-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-3ALRMMN | Manhattan - Fire Alarm | 4 | CONSTRUCTION | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2016-03-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-3ALRMMN | Manhattan - Fire Alarm | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2019-03-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-600ZOO3 | Citywide Zoos - roof replacements at various buildings | 1 | DEVELOP SCOPE | 2014-07-01 | 2014-09-28 | 2014-07-01 | 2014-09-28
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-600ZOO3 | Citywide Zoos - roof replacements at various buildings | 2 | DESIGN | 2014-09-29 | 2014-12-27 | 2014-09-29 | 2014-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-600ZOO3 | Citywide Zoos - roof replacements at various buildings | 3 | BID/ REGISTER CONTRACT | 2014-12-28 | 2015-03-27 | 2014-12-28 | 2015-03-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-600ZOO3 | Citywide Zoos - roof replacements at various buildings | 4 | CONSTRUCTION | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2016-03-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-600ZOO3 | Citywide Zoos - roof replacements at various buildings | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2019-03-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-600ZOO4 | Citywide Zoos - HVAC replacements | 1 | DEVELOP SCOPE | 2014-07-01 | 2014-09-28 | 2014-07-01 | 2014-09-28
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-600ZOO4 | Citywide Zoos - HVAC replacements | 2 | DESIGN | 2014-09-29 | 2014-12-27 | 2014-09-29 | 2014-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-600ZOO4 | Citywide Zoos - HVAC replacements | 3 | BID/ REGISTER CONTRACT | 2014-12-28 | 2015-03-27 | 2014-12-28 | 2015-03-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-600ZOO4 | Citywide Zoos - HVAC replacements | 4 | CONSTRUCTION | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2016-03-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-600ZOO4 | Citywide Zoos - HVAC replacements | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2019-03-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-600ZOO5 | Citywide Zoos - HVAC at CPZ snow leopard & QZ concession | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-600ZOO5 | Citywide Zoos - HVAC at CPZ snow leopard & QZ concession | 2 | DESIGN | 2017-12-28 | 2019-03-27 | 2017-12-28 | 2019-03-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-600ZOO5 | Citywide Zoos - HVAC at CPZ snow leopard & QZ concession | 3 | BID/ REGISTER CONTRACT | 2019-03-28 | 2019-12-22 | 2019-03-28 | 2019-12-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-600ZOO5 | Citywide Zoos - HVAC at CPZ snow leopard & QZ concession | 4 | CONSTRUCTION | 2019-12-23 | 2020-12-21 | 2019-12-23 | 2020-12-21
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-600ZOO5 | Citywide Zoos - HVAC at CPZ snow leopard & QZ concession | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-12-22 | 2021-12-21 | 2020-12-22 | 2021-12-21
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-65BORO | 5 Boro Relocation - 850 East 138th street, Bronx | 1 | DEVELOP SCOPE | 2010-07-01 | 2010-09-28 | 2010-07-01 | 2010-09-28
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-65BORO | 5 Boro Relocation - 850 East 138th street, Bronx | 2 | DESIGN | 2010-09-29 | 2010-12-27 | 2010-09-29 | 2010-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-65BORO | 5 Boro Relocation - 850 East 138th street, Bronx | 3 | BID/ REGISTER CONTRACT | 2010-12-28 | 2011-03-27 | 2010-12-28 | 2011-03-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-65BORO | 5 Boro Relocation - 850 East 138th street, Bronx | 4 | CONSTRUCTION | 2011-03-28 | 2012-03-26 | 2011-03-28 | 2012-03-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-65BORO | 5 Boro Relocation - 850 East 138th street, Bronx | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-03-27 | 2013-03-26 | 2012-03-27 | 2019-04-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6ABLDG3 | REQUIREMENTS -BLDGS-ARCH CNYG-1503M, CNYG-1903M-OMBP | 1 | DEVELOP SCOPE | 2006-07-01 | 2006-09-28 | 2006-07-01 | 2006-09-28
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6ABLDG3 | REQUIREMENTS -BLDGS-ARCH CNYG-1503M, CNYG-1903M-OMBP | 2 | DESIGN | 2006-09-29 | 2006-12-27 | 2006-09-29 | 2006-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6ABLDG3 | REQUIREMENTS -BLDGS-ARCH CNYG-1503M, CNYG-1903M-OMBP | 3 | BID/ REGISTER CONTRACT | 2006-12-28 | 2007-03-27 | 2006-12-28 | 2007-03-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6ABLDG3 | REQUIREMENTS -BLDGS-ARCH CNYG-1503M, CNYG-1903M-OMBP | 4 | CONSTRUCTION | 2007-03-28 | 2008-03-26 | 2007-03-28 | 2008-03-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6ABLDG3 | REQUIREMENTS -BLDGS-ARCH CNYG-1503M, CNYG-1903M-OMBP | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-27 | 2009-03-26 | 2008-03-27 | 2009-03-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6BBLDG3 | REQUIREMENTS -BLDGS- ELEC CNYG-802MR | 3 | BID/ REGISTER CONTRACT | 2006-12-28 | 2007-03-27 | 2006-12-28 | 2007-03-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6BBLDG3 | REQUIREMENTS -BLDGS- ELEC CNYG-802MR | 4 | CONSTRUCTION | 2007-03-28 | 2008-03-26 | 2007-03-28 | 2008-03-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6BBLDG3 | REQUIREMENTS -BLDGS- ELEC CNYG-802MR | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-27 | 2009-03-26 | 2008-03-27 | 2009-03-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6BLDG9C | FY10 Building Requirements (CNYG-409M) | 1 | DEVELOP SCOPE | 2010-07-01 | 2010-09-28 | 2010-07-01 | 2010-09-28
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6BLDG9C | FY10 Building Requirements (CNYG-409M) | 2 | DESIGN | 2010-09-29 | 2010-12-27 | 2010-09-29 | 2010-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6BLDG9C | FY10 Building Requirements (CNYG-409M) | 3 | BID/ REGISTER CONTRACT | 2010-12-28 | 2011-03-27 | 2010-12-28 | 2011-03-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6BLDG9C | FY10 Building Requirements (CNYG-409M) | 4 | CONSTRUCTION | 2011-03-28 | 2012-03-26 | 2011-03-28 | 2012-03-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6BLDG9C | FY10 Building Requirements (CNYG-409M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-03-27 | 2013-03-26 | 2012-03-27 | 2019-04-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6BLGC15 | FY15 Citywide buildings (gen construction) CNYG-1615MA | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6BLGC15 | FY15 Citywide buildings (gen construction) CNYG-1615MA | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6BLGC15 | FY15 Citywide buildings (gen construction) CNYG-1615MA | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6BLGC15 | FY15 Citywide buildings (gen construction) CNYG-1615MA | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6BLGC15 | FY15 Citywide buildings (gen construction) CNYG-1615MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6BLRC14 | RC OF C/S & FACILITIES @ VARIOUS PKS MAYOR FUNDED CNYG-814MA | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2013-09-28
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6BLRC14 | RC OF C/S & FACILITIES @ VARIOUS PKS MAYOR FUNDED CNYG-814MA | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2013-09-29 | 2013-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6BLRC14 | RC OF C/S & FACILITIES @ VARIOUS PKS MAYOR FUNDED CNYG-814MA | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2013-12-28 | 2014-03-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6BLRC14 | RC OF C/S & FACILITIES @ VARIOUS PKS MAYOR FUNDED CNYG-814MA | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2014-03-28 | 2015-03-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6BLRC14 | RC OF C/S & FACILITIES @ VARIOUS PKS MAYOR FUNDED CNYG-814MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2019-03-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6BOIL15 | MOSHOLU PK CS, PROSPECT PK PAINT SHOP, BENSONHURST SR CTR | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2015-09-28
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6BOIL15 | MOSHOLU PK CS, PROSPECT PK PAINT SHOP, BENSONHURST SR CTR | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2015-09-29 | 2015-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6BOIL15 | MOSHOLU PK CS, PROSPECT PK PAINT SHOP, BENSONHURST SR CTR | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2015-12-28 | 2016-03-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6BOIL15 | MOSHOLU PK CS, PROSPECT PK PAINT SHOP, BENSONHURST SR CTR | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6BOIL15 | MOSHOLU PK CS, PROSPECT PK PAINT SHOP, BENSONHURST SR CTR | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2017-03-27 | 2018-03-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6BRIDGE | Citywide Flag Repairs | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2013-09-28
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6BRIDGE | Citywide Flag Repairs | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2013-09-29 | 2013-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6BRIDGE | Citywide Flag Repairs | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2013-12-28 | 2014-03-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6BRIDGE | Citywide Flag Repairs | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2014-03-28 | 2015-03-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6BRIDGE | Citywide Flag Repairs | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2019-03-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CBLDG4 | REQUIREMENTS - BLDGS - PLMB CNYG-404M | 1 | DEVELOP SCOPE | 2006-07-01 | 2006-09-28 | 2006-07-01 | 2006-09-28
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CBLDG4 | REQUIREMENTS - BLDGS - PLMB CNYG-404M | 2 | DESIGN | 2006-09-29 | 2006-12-27 | 2006-09-29 | 2006-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CBLDG4 | REQUIREMENTS - BLDGS - PLMB CNYG-404M | 3 | BID/ REGISTER CONTRACT | 2006-12-28 | 2007-03-27 | 2006-12-28 | 2007-03-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CBLDG4 | REQUIREMENTS - BLDGS - PLMB CNYG-404M | 4 | CONSTRUCTION | 2007-03-28 | 2008-03-26 | 2007-03-28 | 2008-03-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CBLDG4 | REQUIREMENTS - BLDGS - PLMB CNYG-404M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-27 | 2009-03-26 | 2008-03-27 | 2009-03-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6COMF18 | Recon citywide Comfort Stations $1 contract | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6COMF18 | Recon citywide Comfort Stations $1 contract | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6COMF18 | Recon citywide Comfort Stations $1 contract | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6COMF18 | Recon citywide Comfort Stations $1 contract | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6COMF18 | Recon citywide Comfort Stations $1 contract | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CPIBN3 | CPI PH1- Construction of CW C/S CNYG-3215M | 1 | DEVELOP SCOPE | 2014-07-01 | 2014-09-28 | 2014-07-01 | 2014-09-28
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CPIBN3 | CPI PH1- Construction of CW C/S CNYG-3215M | 2 | DESIGN | 2014-09-29 | 2014-12-27 | 2014-09-29 | 2014-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CPIBN3 | CPI PH1- Construction of CW C/S CNYG-3215M | 3 | BID/ REGISTER CONTRACT | 2014-12-28 | 2015-03-27 | 2014-12-28 | 2015-03-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CPIBN3 | CPI PH1- Construction of CW C/S CNYG-3215M | 4 | CONSTRUCTION | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2016-03-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CPIBN3 | CPI PH1- Construction of CW C/S CNYG-3215M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2019-03-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CPIBN4 | CPI PH1- Bx & Mn C/S-Bundle 4 CNYG-3315M | 1 | DEVELOP SCOPE | 2014-07-01 | 2014-09-28 | 2014-07-01 | 2014-09-28
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CPIBN4 | CPI PH1- Bx & Mn C/S-Bundle 4 CNYG-3315M | 2 | DESIGN | 2014-09-29 | 2014-12-27 | 2014-09-29 | 2014-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CPIBN4 | CPI PH1- Bx & Mn C/S-Bundle 4 CNYG-3315M | 3 | BID/ REGISTER CONTRACT | 2014-12-28 | 2015-03-27 | 2014-12-28 | 2015-03-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CPIBN4 | CPI PH1- Bx & Mn C/S-Bundle 4 CNYG-3315M | 4 | CONSTRUCTION | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2016-03-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CPIBN4 | CPI PH1- Bx & Mn C/S-Bundle 4 CNYG-3315M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CPIPH2 | Community Parks Initiative (CPI Ph. 2) | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2015-09-28
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CPIPH2 | Community Parks Initiative (CPI Ph. 2) | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2015-09-29 | 2015-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CPIPH2 | Community Parks Initiative (CPI Ph. 2) | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2015-12-28 | 2016-03-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CPIPH2 | Community Parks Initiative (CPI Ph. 2) | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CPIPH2 | Community Parks Initiative (CPI Ph. 2) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2017-03-27 | 2019-03-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CSBLDG | Reconst of Comfort Stations & Buildings Citywide CNYG-219M | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CSBLDG | Reconst of Comfort Stations & Buildings Citywide CNYG-219M | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CSBLDG | Reconst of Comfort Stations & Buildings Citywide CNYG-219M | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CSBLDG | Reconst of Comfort Stations & Buildings Citywide CNYG-219M | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CSBLDG | Reconst of Comfort Stations & Buildings Citywide CNYG-219M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CW1250 | BOILERS RECONSTRUCTION,CITYWIDE | 1 | DEVELOP SCOPE | 2006-07-01 | 2006-09-28 | 2006-07-01 | 2006-09-28
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CW1250 | BOILERS RECONSTRUCTION,CITYWIDE | 2 | DESIGN | 2006-09-29 | 2006-12-27 | 2006-09-29 | 2006-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CW1250 | BOILERS RECONSTRUCTION,CITYWIDE | 3 | BID/ REGISTER CONTRACT | 2006-12-28 | 2007-03-27 | 2006-12-28 | 2007-03-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CW1250 | BOILERS RECONSTRUCTION,CITYWIDE | 4 | CONSTRUCTION | 2007-03-28 | 2008-03-26 | 2007-03-28 | 2008-03-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CW1250 | BOILERS RECONSTRUCTION,CITYWIDE | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-27 | 2009-03-26 | 2008-03-27 | 2019-04-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CW5131 | NYS Law 5-1.31 Compliance/ Citywide Installation of Backflow | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CW5131 | NYS Law 5-1.31 Compliance/ Citywide Installation of Backflow | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CW5131 | NYS Law 5-1.31 Compliance/ Citywide Installation of Backflow | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CW5131 | NYS Law 5-1.31 Compliance/ Citywide Installation of Backflow | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CW5131 | NYS Law 5-1.31 Compliance/ Citywide Installation of Backflow | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWASBR | Citwide - HazMat Abatement & Borings | 1 | DEVELOP SCOPE | 2006-07-01 | 2006-09-28 | 2006-07-01 | 2006-09-28
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWASBR | Citwide - HazMat Abatement & Borings | 2 | DESIGN | 2006-09-29 | 2006-12-27 | 2006-09-29 | 2006-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWASBR | Citwide - HazMat Abatement & Borings | 3 | BID/ REGISTER CONTRACT | 2006-12-28 | 2007-03-27 | 2006-12-28 | 2007-03-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWASBR | Citwide - HazMat Abatement & Borings | 4 | CONSTRUCTION | 2007-03-28 | 2008-03-26 | 2007-03-28 | 2008-03-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWASBR | Citwide - HazMat Abatement & Borings | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-27 | 2009-03-26 | 2008-03-27 | 2019-07-01
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWBLDS | Citywide - Building Requirements Contract | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWBLDS | Citywide - Building Requirements Contract | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWBLDS | Citywide - Building Requirements Contract | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWBLDS | Citywide - Building Requirements Contract | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWBLDS | Citywide - Building Requirements Contract | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWCMVE | Citywide - Comfort Stations Standards Study | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWCMVE | Citywide - Comfort Stations Standards Study | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWCMVE | Citywide - Comfort Stations Standards Study | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWCMVE | Citywide - Comfort Stations Standards Study | 4 | CONSTRUCTION | 2019-09-24 | 2021-03-21 | 2019-09-24 | 2021-03-21
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWCMVE | Citywide - Comfort Stations Standards Study | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-22 | 2022-03-21 | 2021-03-22 | 2022-03-21
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWFALM | NATURE CTRS AND REC CTRS-FIRE ALARMS AND LIFE SAFETY | 1 | DEVELOP SCOPE | 2017-01-04 | 2017-07-02 | 2017-01-04 | 2017-07-02
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWFALM | NATURE CTRS AND REC CTRS-FIRE ALARMS AND LIFE SAFETY | 2 | DESIGN | 2017-07-03 | 2019-07-02 | 2017-07-03 | 2019-07-02
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWFALM | NATURE CTRS AND REC CTRS-FIRE ALARMS AND LIFE SAFETY | 3 | BID/ REGISTER CONTRACT | 2019-07-03 | 2020-03-28 | 2019-07-03 | 2020-03-28
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWFALM | NATURE CTRS AND REC CTRS-FIRE ALARMS AND LIFE SAFETY | 4 | CONSTRUCTION | 2020-03-29 | 2023-03-28 | 2020-03-29 | 2023-03-28
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWFALM | NATURE CTRS AND REC CTRS-FIRE ALARMS AND LIFE SAFETY | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-03-29 | 2025-03-27 | 2023-03-29 | 2025-03-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWGRNT | Hazardous Sidewalk Removal and Replacement | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWGRNT | Hazardous Sidewalk Removal and Replacement | 2 | DESIGN | 2018-12-28 | 2020-06-24 | 2018-12-28 | 2020-06-24
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWGRNT | Hazardous Sidewalk Removal and Replacement | 3 | BID/ REGISTER CONTRACT | 2020-06-25 | 2021-03-21 | 2020-06-25 | 2021-03-21
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWGRNT | Hazardous Sidewalk Removal and Replacement | 4 | CONSTRUCTION | 2021-03-22 | 2022-09-17 | 2021-03-22 | 2022-09-17
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWGRNT | Hazardous Sidewalk Removal and Replacement | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-18 | 2023-09-17 | 2022-09-18 | 2023-09-17
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWMARI | CITYWIDE - MARINAS | 1 | DEVELOP SCOPE | 2014-07-01 | 2014-09-28 | 2014-07-01 | 2014-09-28
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWMARI | CITYWIDE - MARINAS | 2 | DESIGN | 2014-09-29 | 2014-12-27 | 2014-09-29 | 2014-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWMARI | CITYWIDE - MARINAS | 3 | BID/ REGISTER CONTRACT | 2014-12-28 | 2015-03-27 | 2014-12-28 | 2015-03-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWMARI | CITYWIDE - MARINAS | 4 | CONSTRUCTION | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2016-03-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWMARI | CITYWIDE - MARINAS | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2019-03-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWMINI | MINI-POOLS - CITYWIDE CNYG-1601MA | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWMINI | MINI-POOLS - CITYWIDE CNYG-1601MA | 2 | DESIGN | 2016-12-28 | 2018-06-25 | 2016-12-28 | 2018-06-25
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWMINI | MINI-POOLS - CITYWIDE CNYG-1601MA | 3 | BID/ REGISTER CONTRACT | 2018-06-26 | 2019-03-22 | 2018-06-26 | 2019-03-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWMINI | MINI-POOLS - CITYWIDE CNYG-1601MA | 4 | CONSTRUCTION | 2019-03-23 | 2020-09-17 | 2019-03-23 | 2020-09-17
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWMINI | MINI-POOLS - CITYWIDE CNYG-1601MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-18 | 2021-09-17 | 2020-09-18 | 2021-09-17
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWNP | CPI - NEIGHBORHOOD PARKS | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2013-09-28
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWNP | CPI - NEIGHBORHOOD PARKS | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2013-09-29 | 2013-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWNP | CPI - NEIGHBORHOOD PARKS | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2013-12-28 | 2014-03-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWNP | CPI - NEIGHBORHOOD PARKS | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2014-03-28 | 2015-03-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWNP | CPI - NEIGHBORHOOD PARKS | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2017-03-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWPLE1 | Recon pool electrical systems, Citywide | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWPLE1 | Recon pool electrical systems, Citywide | 2 | DESIGN | 2019-12-28 | 2021-06-24 | 2019-12-28 | 2021-06-24
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWPLE1 | Recon pool electrical systems, Citywide | 3 | BID/ REGISTER CONTRACT | 2021-06-25 | 2022-03-21 | 2021-06-25 | 2022-03-21
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWPLE1 | Recon pool electrical systems, Citywide | 4 | CONSTRUCTION | 2022-03-22 | 2023-09-17 | 2022-03-22 | 2023-09-17
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWPLE1 | Recon pool electrical systems, Citywide | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-18 | 2024-09-16 | 2023-09-18 | 2024-09-16
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWPOOL | CITYWIDE - POOLS | 1 | DEVELOP SCOPE | 2006-07-01 | 2006-09-28 | 2006-07-01 | 2006-09-28
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWPOOL | CITYWIDE - POOLS | 2 | DESIGN | 2006-09-29 | 2006-12-27 | 2006-09-29 | 2006-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWPOOL | CITYWIDE - POOLS | 3 | BID/ REGISTER CONTRACT | 2006-12-28 | 2007-03-27 | 2006-12-28 | 2007-03-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWPOOL | CITYWIDE - POOLS | 4 | CONSTRUCTION | 2007-03-28 | 2008-03-26 | 2007-03-28 | 2008-03-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWPOOL | CITYWIDE - POOLS | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-27 | 2009-03-26 | 2008-03-27 | 2014-04-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWR22C | CityWide - HVAC R22 coolant retrofit | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWR22C | CityWide - HVAC R22 coolant retrofit | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWR22C | CityWide - HVAC R22 coolant retrofit | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWR22C | CityWide - HVAC R22 coolant retrofit | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWR22C | CityWide - HVAC R22 coolant retrofit | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWR23C | CityWide - HVAC R22 coolant retrofit (other facilities) | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWR23C | CityWide - HVAC R22 coolant retrofit (other facilities) | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWR23C | CityWide - HVAC R22 coolant retrofit (other facilities) | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWR23C | CityWide - HVAC R22 coolant retrofit (other facilities) | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWR23C | CityWide - HVAC R22 coolant retrofit (other facilities) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWRDIO | CITYWIDE - RUPS/ Radio System & Field equipment Revamp | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWRDIO | CITYWIDE - RUPS/ Radio System & Field equipment Revamp | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWRDIO | CITYWIDE - RUPS/ Radio System & Field equipment Revamp | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWRDIO | CITYWIDE - RUPS/ Radio System & Field equipment Revamp | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWRDIO | CITYWIDE - RUPS/ Radio System & Field equipment Revamp | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWREWA | Retaining Walls- Citywide-Man.-S.I. & BX | 1 | DEVELOP SCOPE | 2020-07-01 | 2020-12-27 | 2020-07-01 | 2020-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWREWA | Retaining Walls- Citywide-Man.-S.I. & BX | 2 | DESIGN | 2020-12-28 | 2022-06-25 | 2020-12-28 | 2022-06-25
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWREWA | Retaining Walls- Citywide-Man.-S.I. & BX | 3 | BID/ REGISTER CONTRACT | 2022-06-26 | 2023-03-22 | 2022-06-26 | 2023-03-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWREWA | Retaining Walls- Citywide-Man.-S.I. & BX | 4 | CONSTRUCTION | 2023-03-23 | 2024-09-17 | 2023-03-23 | 2024-09-17
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWREWA | Retaining Walls- Citywide-Man.-S.I. & BX | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-09-18 | 2025-09-17 | 2024-09-18 | 2025-09-17
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWROOF | CITYWIDE - ROOFING SYSTEMS RC | 1 | DEVELOP SCOPE | 2006-07-01 | 2006-09-28 | 2006-07-01 | 2006-09-28
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWROOF | CITYWIDE - ROOFING SYSTEMS RC | 2 | DESIGN | 2006-09-29 | 2006-12-27 | 2006-09-29 | 2006-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWROOF | CITYWIDE - ROOFING SYSTEMS RC | 3 | BID/ REGISTER CONTRACT | 2006-12-28 | 2007-03-27 | 2006-12-28 | 2007-03-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWROOF | CITYWIDE - ROOFING SYSTEMS RC | 4 | CONSTRUCTION | 2007-03-28 | 2008-03-26 | 2007-03-28 | 2008-03-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWROOF | CITYWIDE - ROOFING SYSTEMS RC | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-27 | 2009-03-26 | 2008-03-27 | 2014-04-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWRWAL | RETAINING WALLS - CITYWIDE | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-09-28 | 2016-07-01 | 2016-09-28
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWRWAL | RETAINING WALLS - CITYWIDE | 2 | DESIGN | 2016-09-29 | 2016-12-27 | 2016-09-29 | 2016-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWRWAL | RETAINING WALLS - CITYWIDE | 3 | BID/ REGISTER CONTRACT | 2016-12-28 | 2017-03-27 | 2016-12-28 | 2017-03-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWRWAL | RETAINING WALLS - CITYWIDE | 4 | CONSTRUCTION | 2017-03-28 | 2018-03-27 | 2017-03-28 | 2018-03-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWRWAL | RETAINING WALLS - CITYWIDE | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-03-28 | 2019-03-27 | 2018-03-28 | 2019-03-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWSSPE | REQUIREMENTS CONTRACTS- CITYWIDE | 1 | DEVELOP SCOPE | 2006-07-01 | 2006-09-28 | 2006-07-01 | 2006-09-28
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWSSPE | REQUIREMENTS CONTRACTS- CITYWIDE | 2 | DESIGN | 2006-09-29 | 2006-12-27 | 2006-09-29 | 2006-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWSSPE | REQUIREMENTS CONTRACTS- CITYWIDE | 3 | BID/ REGISTER CONTRACT | 2006-12-28 | 2007-03-27 | 2006-12-28 | 2007-03-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWSSPE | REQUIREMENTS CONTRACTS- CITYWIDE | 4 | CONSTRUCTION | 2007-03-28 | 2008-03-26 | 2007-03-28 | 2008-03-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWSSPE | REQUIREMENTS CONTRACTS- CITYWIDE | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-27 | 2009-03-26 | 2008-03-27 | 2017-04-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWSTF | CITYWIDE SYNTHETIC RC | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWSTF | CITYWIDE SYNTHETIC RC | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWSTF | CITYWIDE SYNTHETIC RC | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWSTF | CITYWIDE SYNTHETIC RC | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWSTF | CITYWIDE SYNTHETIC RC | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWWALK | BOARDWALKS - CITYWIDE | 1 | DEVELOP SCOPE | 2006-07-01 | 2006-09-28 | 2006-07-01 | 2006-09-28
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWWALK | BOARDWALKS - CITYWIDE | 2 | DESIGN | 2006-09-29 | 2006-12-27 | 2006-09-29 | 2006-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWWALK | BOARDWALKS - CITYWIDE | 3 | BID/ REGISTER CONTRACT | 2006-12-28 | 2007-03-27 | 2006-12-28 | 2007-03-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWWALK | BOARDWALKS - CITYWIDE | 4 | CONSTRUCTION | 2007-03-28 | 2008-03-26 | 2007-03-28 | 2008-03-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWWALK | BOARDWALKS - CITYWIDE | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-27 | 2009-03-26 | 2008-03-27 | 2014-04-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6DBLDG3 | REQUIREMENTS - BLDGS - HVAC CNYG-1002MR | 1 | DEVELOP SCOPE | 2006-07-01 | 2006-09-28 | 2006-07-01 | 2006-09-28
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6DBLDG3 | REQUIREMENTS - BLDGS - HVAC CNYG-1002MR | 2 | DESIGN | 2006-09-29 | 2006-12-27 | 2006-09-29 | 2006-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6DBLDG3 | REQUIREMENTS - BLDGS - HVAC CNYG-1002MR | 3 | BID/ REGISTER CONTRACT | 2006-12-28 | 2007-03-27 | 2006-12-28 | 2007-03-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6DBLDG3 | REQUIREMENTS - BLDGS - HVAC CNYG-1002MR | 4 | CONSTRUCTION | 2007-03-28 | 2008-03-26 | 2007-03-28 | 2008-03-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6DBLDG3 | REQUIREMENTS - BLDGS - HVAC CNYG-1002MR | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-27 | 2009-03-26 | 2008-03-27 | 2009-03-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6DEERFE | Citywide - Deer Fencing - SI ,BX | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6DEERFE | Citywide - Deer Fencing - SI ,BX | 2 | DESIGN | 2019-12-28 | 2021-06-19 | 2019-12-28 | 2021-06-19
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6DEERFE | Citywide - Deer Fencing - SI ,BX | 3 | BID/ REGISTER CONTRACT | 2021-06-20 | 2022-03-16 | 2021-06-20 | 2022-03-16
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6DEERFE | Citywide - Deer Fencing - SI ,BX | 4 | CONSTRUCTION | 2022-03-17 | 2024-03-15 | 2022-03-17 | 2024-03-15
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6DEERFE | Citywide - Deer Fencing - SI ,BX | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-03-16 | 2026-03-15 | 2024-03-16 | 2026-03-15
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6DTREE7 | Trees - FY07 Spring Trees (CNYG-407M) | 1 | DEVELOP SCOPE | 2007-07-01 | 2007-09-28 | 2007-07-01 | 2007-09-28
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6DTREE7 | Trees - FY07 Spring Trees (CNYG-407M) | 2 | DESIGN | 2007-09-29 | 2007-12-27 | 2007-09-29 | 2007-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6DTREE7 | Trees - FY07 Spring Trees (CNYG-407M) | 3 | BID/ REGISTER CONTRACT | 2007-12-28 | 2008-03-26 | 2007-12-28 | 2008-03-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6DTREE7 | Trees - FY07 Spring Trees (CNYG-407M) | 4 | CONSTRUCTION | 2008-03-27 | 2009-03-26 | 2008-03-27 | 2009-03-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6DTREE7 | Trees - FY07 Spring Trees (CNYG-407M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2009-03-27 | 2010-03-26 | 2009-03-27 | 2013-03-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6EABTRA | Emerald Ash Borer (EAB) Tree Remove BX & MN | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6EABTRA | Emerald Ash Borer (EAB) Tree Remove BX & MN | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6EABTRA | Emerald Ash Borer (EAB) Tree Remove BX & MN | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6EABTRA | Emerald Ash Borer (EAB) Tree Remove BX & MN | 4 | CONSTRUCTION | 2020-09-23 | 2022-09-22 | 2020-09-23 | 2022-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6EABTRA | Emerald Ash Borer (EAB) Tree Remove BX & MN | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6EABTRB | Emerald Ash Borer (EAB) Tree Remove BK &SI-CNYG-2319M | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6EABTRB | Emerald Ash Borer (EAB) Tree Remove BK &SI-CNYG-2319M | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6EABTRB | Emerald Ash Borer (EAB) Tree Remove BK &SI-CNYG-2319M | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6EABTRB | Emerald Ash Borer (EAB) Tree Remove BK &SI-CNYG-2319M | 4 | CONSTRUCTION | 2020-09-23 | 2022-09-22 | 2020-09-23 | 2022-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6EABTRB | Emerald Ash Borer (EAB) Tree Remove BK &SI-CNYG-2319M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6EABTRE | Emerald Ash Borer (EAB) Remove and Replace | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6EABTRE | Emerald Ash Borer (EAB) Remove and Replace | 2 | DESIGN | 2018-12-28 | 2019-06-25 | 2018-12-28 | 2019-06-25
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6EABTRE | Emerald Ash Borer (EAB) Remove and Replace | 3 | BID/ REGISTER CONTRACT | 2019-06-26 | 2019-12-22 | 2019-06-26 | 2019-12-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6EABTRE | Emerald Ash Borer (EAB) Remove and Replace | 4 | CONSTRUCTION | 2019-12-23 | 2028-12-19 | 2019-12-23 | 2028-12-19
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6EABTRE | Emerald Ash Borer (EAB) Remove and Replace | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2028-12-20 | 2029-02-17 | 2028-12-20 | 2029-02-17
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6ELBR15 | FY15 Recon electric system in bldg & pool CW CNYG-1315MA | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6ELBR15 | FY15 Recon electric system in bldg & pool CW CNYG-1315MA | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6ELBR15 | FY15 Recon electric system in bldg & pool CW CNYG-1315MA | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6ELBR15 | FY15 Recon electric system in bldg & pool CW CNYG-1315MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6ELUT15 | FY15 site utility (dig job) electric M104-219M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6ELUT15 | FY15 site utility (dig job) electric M104-219M | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6ELUT15 | FY15 site utility (dig job) electric M104-219M | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6ELUT15 | FY15 site utility (dig job) electric M104-219M | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6ELUT15 | FY15 site utility (dig job) electric M104-219M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6ENVTST | Citywide environment testing at DPR facilities CNYG-119M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6ENVTST | Citywide environment testing at DPR facilities CNYG-119M | 2 | DESIGN | 2017-12-28 | 2019-06-25 | 2017-12-28 | 2019-06-25
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6ENVTST | Citywide environment testing at DPR facilities CNYG-119M | 3 | BID/ REGISTER CONTRACT | 2019-06-26 | 2020-03-21 | 2019-06-26 | 2020-03-21
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6ENVTST | Citywide environment testing at DPR facilities CNYG-119M | 4 | CONSTRUCTION | 2020-03-22 | 2021-09-17 | 2020-03-22 | 2021-09-17
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6ENVTST | Citywide environment testing at DPR facilities CNYG-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-18 | 2022-09-17 | 2021-09-18 | 2022-09-17
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6FLMMUL | Fire Alarm - Rec Ctr & Nature Ctr Citywide CNYG-1217M | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6FLMMUL | Fire Alarm - Rec Ctr & Nature Ctr Citywide CNYG-1217M | 2 | DESIGN | 2016-12-28 | 2018-06-25 | 2016-12-28 | 2018-06-25
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6FLMMUL | Fire Alarm - Rec Ctr & Nature Ctr Citywide CNYG-1217M | 3 | BID/ REGISTER CONTRACT | 2018-06-26 | 2019-03-22 | 2018-06-26 | 2019-03-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6FLMMUL | Fire Alarm - Rec Ctr & Nature Ctr Citywide CNYG-1217M | 4 | CONSTRUCTION | 2019-03-23 | 2020-09-17 | 2019-03-23 | 2020-09-17
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6FLMMUL | Fire Alarm - Rec Ctr & Nature Ctr Citywide CNYG-1217M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-18 | 2021-09-17 | 2020-09-18 | 2021-09-17
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6GASBSI | CONVERSION OF OIL TO GAS BKLYN & SI CNYG-1914M | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2013-09-28
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6GASBSI | CONVERSION OF OIL TO GAS BKLYN & SI CNYG-1914M | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2013-09-29 | 2013-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6GASBSI | CONVERSION OF OIL TO GAS BKLYN & SI CNYG-1914M | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2013-12-28 | 2014-03-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6GASBSI | CONVERSION OF OIL TO GAS BKLYN & SI CNYG-1914M | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2014-03-28 | 2015-03-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6GASBSI | CONVERSION OF OIL TO GAS BKLYN & SI CNYG-1914M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2016-03-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6GASBXQ | CONVERSION OF OIL TO GAS BX & QNS CNYG-1814M | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2013-09-28
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6GASBXQ | CONVERSION OF OIL TO GAS BX & QNS CNYG-1814M | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2013-09-29 | 2013-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6GASBXQ | CONVERSION OF OIL TO GAS BX & QNS CNYG-1814M | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2013-12-28 | 2014-03-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6GASBXQ | CONVERSION OF OIL TO GAS BX & QNS CNYG-1814M | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2014-03-28 | 2015-03-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6GASBXQ | CONVERSION OF OIL TO GAS BX & QNS CNYG-1814M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2016-03-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6GASMAN | CONVERSION OF OIL TO GAS MANHATTAN MG-814M | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2013-09-28
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6GASMAN | CONVERSION OF OIL TO GAS MANHATTAN MG-814M | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2013-09-29 | 2013-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6GASMAN | CONVERSION OF OIL TO GAS MANHATTAN MG-814M | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2013-12-28 | 2014-03-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6GASMAN | CONVERSION OF OIL TO GAS MANHATTAN MG-814M | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2014-03-28 | 2015-03-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6GASMAN | CONVERSION OF OIL TO GAS MANHATTAN MG-814M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2016-03-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6GDRL15 | FY15 Citywide guiderail & fencing CNYG-2015M | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2015-09-28
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6GDRL15 | FY15 Citywide guiderail & fencing CNYG-2015M | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2015-09-29 | 2015-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6GDRL15 | FY15 Citywide guiderail & fencing CNYG-2015M | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2015-12-28 | 2016-03-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6GDRL15 | FY15 Citywide guiderail & fencing CNYG-2015M | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6GDRL15 | FY15 Citywide guiderail & fencing CNYG-2015M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2017-03-27 | 2018-03-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6GRST16 | FY16 Greenstreets - CITYWIDE | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2016-07-01 | 2016-09-28
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6GRST16 | FY16 Greenstreets - CITYWIDE | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2016-09-29 | 2016-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6GRST16 | FY16 Greenstreets - CITYWIDE | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2016-12-28 | 2017-03-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6GRST16 | FY16 Greenstreets - CITYWIDE | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2017-03-28 | 2019-03-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6GRST16 | FY16 Greenstreets - CITYWIDE | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2019-03-28 | 2021-03-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6LIGHT1 | Construction Of Multisite Path Lighting | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6LIGHT1 | Construction Of Multisite Path Lighting | 2 | DESIGN | 2018-12-28 | 2020-06-24 | 2018-12-28 | 2020-06-24
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6LIGHT1 | Construction Of Multisite Path Lighting | 3 | BID/ REGISTER CONTRACT | 2020-06-25 | 2021-03-21 | 2020-06-25 | 2021-03-21
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6LIGHT1 | Construction Of Multisite Path Lighting | 4 | CONSTRUCTION | 2021-03-22 | 2022-09-17 | 2021-03-22 | 2022-09-17
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6LIGHT1 | Construction Of Multisite Path Lighting | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-18 | 2023-09-17 | 2022-09-18 | 2023-09-17
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6MSHVAC | Recon HVAC at Greenbelt R/C & Queens Museum CNYG-1318M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6MSHVAC | Recon HVAC at Greenbelt R/C & Queens Museum CNYG-1318M | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6MSHVAC | Recon HVAC at Greenbelt R/C & Queens Museum CNYG-1318M | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6MSHVAC | Recon HVAC at Greenbelt R/C & Queens Museum CNYG-1318M | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6MSHVAC | Recon HVAC at Greenbelt R/C & Queens Museum CNYG-1318M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6NCRC15 | FY15 Citywide Nature & Rec Ctr CNYG-1215MA | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-12-27 | 2015-07-01 | 2015-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6NCRC15 | FY15 Citywide Nature & Rec Ctr CNYG-1215MA | 2 | DESIGN | 2015-12-28 | 2016-12-26 | 2015-12-28 | 2016-12-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6NCRC15 | FY15 Citywide Nature & Rec Ctr CNYG-1215MA | 3 | BID/ REGISTER CONTRACT | 2016-12-27 | 2017-09-22 | 2016-12-27 | 2017-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6NCRC15 | FY15 Citywide Nature & Rec Ctr CNYG-1215MA | 4 | CONSTRUCTION | 2017-09-23 | 2018-09-22 | 2017-09-23 | 2018-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6NCRC15 | FY15 Citywide Nature & Rec Ctr CNYG-1215MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-09-23 | 2019-09-22 | 2018-09-23 | 2019-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6OLYMPL | Citywide Olympic Pool Mechanical Systems Recon CNYG-2719M | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6OLYMPL | Citywide Olympic Pool Mechanical Systems Recon CNYG-2719M | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6OLYMPL | Citywide Olympic Pool Mechanical Systems Recon CNYG-2719M | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6OLYMPL | Citywide Olympic Pool Mechanical Systems Recon CNYG-2719M | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6OLYMPL | Citywide Olympic Pool Mechanical Systems Recon CNYG-2719M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6ORCAST | Recon Orchard Beach Nature Center | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6ORCAST | Recon Orchard Beach Nature Center | 2 | DESIGN | 2018-12-28 | 2020-06-24 | 2018-12-28 | 2020-06-24
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6ORCAST | Recon Orchard Beach Nature Center | 3 | BID/ REGISTER CONTRACT | 2020-06-25 | 2021-03-21 | 2020-06-25 | 2021-03-21
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6ORCAST | Recon Orchard Beach Nature Center | 4 | CONSTRUCTION | 2021-03-22 | 2022-09-17 | 2021-03-22 | 2022-09-17
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6ORCAST | Recon Orchard Beach Nature Center | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-18 | 2023-09-17 | 2022-09-18 | 2023-09-17
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PBBP15 | FY15 Recon plumbing system in bldg & pool CW CNYG-1415M | 1 | DEVELOP SCOPE | 2017-08-01 | 2018-01-27 | 2017-08-01 | 2018-01-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PBBP15 | FY15 Recon plumbing system in bldg & pool CW CNYG-1415M | 2 | DESIGN | 2018-01-28 | 2019-01-27 | 2018-01-28 | 2019-01-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PBBP15 | FY15 Recon plumbing system in bldg & pool CW CNYG-1415M | 3 | BID/ REGISTER CONTRACT | 2019-01-28 | 2019-10-24 | 2019-01-28 | 2019-10-24
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PBBP15 | FY15 Recon plumbing system in bldg & pool CW CNYG-1415M | 4 | CONSTRUCTION | 2019-10-25 | 2020-10-23 | 2019-10-25 | 2020-10-23
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PBBP15 | FY15 Recon plumbing system in bldg & pool CW CNYG-1415M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-10-24 | 2021-10-23 | 2020-10-24 | 2021-10-23
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PBUT15 | FY15 site utility (dig job) plumbing CNYG-1815M | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PBUT15 | FY15 site utility (dig job) plumbing CNYG-1815M | 2 | DESIGN | 2016-12-28 | 2018-06-25 | 2016-12-28 | 2018-06-25
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PBUT15 | FY15 site utility (dig job) plumbing CNYG-1815M | 3 | BID/ REGISTER CONTRACT | 2018-06-26 | 2019-03-22 | 2018-06-26 | 2019-03-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PBUT15 | FY15 site utility (dig job) plumbing CNYG-1815M | 4 | CONSTRUCTION | 2019-03-23 | 2020-09-17 | 2019-03-23 | 2020-09-17
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PBUT15 | FY15 site utility (dig job) plumbing CNYG-1815M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-18 | 2021-09-17 | 2020-09-18 | 2021-09-17
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PDBLPB | Recon plumbing & HVAC systems in C/S - Citywide CNYG-715MA1 | 1 | DEVELOP SCOPE | 2014-07-01 | 2014-09-28 | 2014-07-01 | 2014-09-28
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PDBLPB | Recon plumbing & HVAC systems in C/S - Citywide CNYG-715MA1 | 2 | DESIGN | 2014-09-29 | 2014-12-27 | 2014-09-29 | 2014-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PDBLPB | Recon plumbing & HVAC systems in C/S - Citywide CNYG-715MA1 | 3 | BID/ REGISTER CONTRACT | 2014-12-28 | 2015-03-27 | 2014-12-28 | 2015-03-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PDBLPB | Recon plumbing & HVAC systems in C/S - Citywide CNYG-715MA1 | 4 | CONSTRUCTION | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2016-03-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PDBLPB | Recon plumbing & HVAC systems in C/S - Citywide CNYG-715MA1 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PDPLGC | Recon of pool facilities - Citywide CNYG-1015M | 2 | DESIGN | 2014-09-29 | 2014-12-27 | 2014-09-29 | 2014-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PDPLGC | Recon of pool facilities - Citywide CNYG-1015M | 3 | BID/ REGISTER CONTRACT | 2014-12-28 | 2015-03-27 | 2014-12-28 | 2015-03-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PDPLGC | Recon of pool facilities - Citywide CNYG-1015M | 4 | CONSTRUCTION | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2016-03-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PDPLGC | Recon of pool facilities - Citywide CNYG-1015M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PDRFMN | Recon roofs at Parks facilities in Manhattan MG-215M | 1 | DEVELOP SCOPE | 2014-12-01 | 2015-02-28 | 2014-12-01 | 2015-02-28
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PDRFMN | Recon roofs at Parks facilities in Manhattan MG-215M | 2 | DESIGN | 2015-03-01 | 2015-05-29 | 2015-03-01 | 2015-05-29
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PDRFMN | Recon roofs at Parks facilities in Manhattan MG-215M | 3 | BID/ REGISTER CONTRACT | 2015-05-30 | 2015-08-27 | 2015-05-30 | 2015-08-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PDRFMN | Recon roofs at Parks facilities in Manhattan MG-215M | 4 | CONSTRUCTION | 2015-08-28 | 2016-08-26 | 2015-08-28 | 2016-08-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PDRFMN | Recon roofs at Parks facilities in Manhattan MG-215M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-08-27 | 2017-08-26 | 2016-08-27 | 2017-08-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PKTREE | Park Trees - Maintain Stem Count | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PKTREE | Park Trees - Maintain Stem Count | 2 | DESIGN | 2017-12-28 | 2019-03-27 | 2017-12-28 | 2019-03-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PKTREE | Park Trees - Maintain Stem Count | 3 | BID/ REGISTER CONTRACT | 2019-03-28 | 2019-12-22 | 2019-03-28 | 2019-12-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PKTREE | Park Trees - Maintain Stem Count | 4 | CONSTRUCTION | 2019-12-23 | 2020-12-21 | 2019-12-23 | 2020-12-21
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PKTREE | Park Trees - Maintain Stem Count | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-12-22 | 2021-12-21 | 2020-12-22 | 2021-12-21
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PLAYFA | PLAYFAIR CAPITAL WORK | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PLAYFA | PLAYFAIR CAPITAL WORK | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PLAYFA | PLAYFAIR CAPITAL WORK | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PLAYFA | PLAYFAIR CAPITAL WORK | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PLAYFA | PLAYFAIR CAPITAL WORK | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PLEL14 | RC OF ELECTRIC AT POOLS MAYOR FUNDED CNYG-614M | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2013-09-28
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PLEL14 | RC OF ELECTRIC AT POOLS MAYOR FUNDED CNYG-614M | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2013-09-29 | 2013-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PLEL14 | RC OF ELECTRIC AT POOLS MAYOR FUNDED CNYG-614M | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2013-12-28 | 2014-03-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PLEL14 | RC OF ELECTRIC AT POOLS MAYOR FUNDED CNYG-614M | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2014-03-28 | 2015-03-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PLEL14 | RC OF ELECTRIC AT POOLS MAYOR FUNDED CNYG-614M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2016-03-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PLFLTR | Recon of intermediate pool filter plants citywide CNYG-619M | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PLFLTR | Recon of intermediate pool filter plants citywide CNYG-619M | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PLFLTR | Recon of intermediate pool filter plants citywide CNYG-619M | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PLFLTR | Recon of intermediate pool filter plants citywide CNYG-619M | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PLFLTR | Recon of intermediate pool filter plants citywide CNYG-619M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PLHNGR | Recon of citywide pool piping hangers & supports CNYG-419M | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PLHNGR | Recon of citywide pool piping hangers & supports CNYG-419M | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PLHNGR | Recon of citywide pool piping hangers & supports CNYG-419M | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PLHNGR | Recon of citywide pool piping hangers & supports CNYG-419M | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PLHNGR | Recon of citywide pool piping hangers & supports CNYG-419M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PNYCST | PlaNYC 2030 Street Trees | 1 | DEVELOP SCOPE | 2007-07-01 | 2007-09-28 | 2007-07-01 | 2007-09-28
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PNYCST | PlaNYC 2030 Street Trees | 2 | DESIGN | 2007-09-29 | 2007-12-27 | 2007-09-29 | 2007-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PNYCST | PlaNYC 2030 Street Trees | 3 | BID/ REGISTER CONTRACT | 2007-12-28 | 2008-03-26 | 2007-12-28 | 2008-03-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PNYCST | PlaNYC 2030 Street Trees | 4 | CONSTRUCTION | 2008-03-27 | 2009-03-26 | 2008-03-27 | 2009-03-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PNYCST | PlaNYC 2030 Street Trees | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2009-03-27 | 2010-03-26 | 2009-03-27 | 2030-07-07
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PNYDOT | PlaNYC - Street Trees | 1 | DEVELOP SCOPE | 2008-07-01 | 2008-09-28 | 2008-07-01 | 2008-09-28
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PNYDOT | PlaNYC - Street Trees | 2 | DESIGN | 2008-09-29 | 2008-12-27 | 2008-09-29 | 2008-09-28
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PNYDOT | PlaNYC - Street Trees | 3 | BID/ REGISTER CONTRACT | 2008-12-28 | 2009-03-27 | 2008-09-29 | 2008-09-28
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PNYDOT | PlaNYC - Street Trees | 4 | CONSTRUCTION | 2009-03-28 | 2010-03-27 | 2008-09-29 | 2008-09-28
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PNYDOT | PlaNYC - Street Trees | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2010-03-28 | 2011-03-27 | 2008-09-29 | 2029-06-03
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PNYG05 | PlaNYC - FY09 Spring Greenstreets (CNYG-2109M) | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PNYG05 | PlaNYC - FY09 Spring Greenstreets (CNYG-2109M) | 2 | DESIGN | 2016-12-28 | 2018-06-20 | 2016-12-28 | 2018-06-20
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PNYG05 | PlaNYC - FY09 Spring Greenstreets (CNYG-2109M) | 3 | BID/ REGISTER CONTRACT | 2018-06-21 | 2019-03-17 | 2018-06-21 | 2019-03-17
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PNYG05 | PlaNYC - FY09 Spring Greenstreets (CNYG-2109M) | 4 | CONSTRUCTION | 2019-03-18 | 2020-09-07 | 2019-03-18 | 2020-09-07
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PNYG05 | PlaNYC - FY09 Spring Greenstreets (CNYG-2109M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-08 | 2022-09-07 | 2020-09-08 | 2022-09-07
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PNYR34 | PlaNYC - Reforestatiob Bk,Que,& SI FY17-25 (CNYG-3816M) | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PNYR34 | PlaNYC - Reforestatiob Bk,Que,& SI FY17-25 (CNYG-3816M) | 2 | DESIGN | 2016-12-28 | 2017-06-25 | 2016-12-28 | 2017-06-25
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PNYR34 | PlaNYC - Reforestatiob Bk,Que,& SI FY17-25 (CNYG-3816M) | 3 | BID/ REGISTER CONTRACT | 2017-06-26 | 2018-03-22 | 2017-06-26 | 2018-03-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PNYR34 | PlaNYC - Reforestatiob Bk,Que,& SI FY17-25 (CNYG-3816M) | 4 | CONSTRUCTION | 2018-03-23 | 2023-03-21 | 2018-03-23 | 2023-03-21
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PNYR34 | PlaNYC - Reforestatiob Bk,Que,& SI FY17-25 (CNYG-3816M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-03-22 | 2023-05-20 | 2023-03-22 | 2023-05-20
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PNYR35 | PlaNYC - Reforestation Bx,Mnt & Que FY17-25 (CNYG-3716M) | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PNYR35 | PlaNYC - Reforestation Bx,Mnt & Que FY17-25 (CNYG-3716M) | 2 | DESIGN | 2016-12-28 | 2017-06-25 | 2016-12-28 | 2017-06-25
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PNYR35 | PlaNYC - Reforestation Bx,Mnt & Que FY17-25 (CNYG-3716M) | 3 | BID/ REGISTER CONTRACT | 2017-06-26 | 2018-03-22 | 2017-06-26 | 2018-03-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PNYR35 | PlaNYC - Reforestation Bx,Mnt & Que FY17-25 (CNYG-3716M) | 4 | CONSTRUCTION | 2018-03-23 | 2023-03-21 | 2018-03-23 | 2023-03-21
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PNYR35 | PlaNYC - Reforestation Bx,Mnt & Que FY17-25 (CNYG-3716M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-03-22 | 2023-05-20 | 2023-03-22 | 2023-05-20
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PNYR36 | PlaNYC - FY18 Reforestation Br,Q &SI | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PNYR36 | PlaNYC - FY18 Reforestation Br,Q &SI | 2 | DESIGN | 2017-12-28 | 2018-09-23 | 2017-12-28 | 2018-09-23
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PNYR36 | PlaNYC - FY18 Reforestation Br,Q &SI | 3 | BID/ REGISTER CONTRACT | 2018-09-24 | 2019-06-20 | 2018-09-24 | 2019-06-20
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PNYR36 | PlaNYC - FY18 Reforestation Br,Q &SI | 4 | CONSTRUCTION | 2019-06-21 | 2021-12-16 | 2019-06-21 | 2021-12-16
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PNYR36 | PlaNYC - FY18 Reforestation Br,Q &SI | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-12-17 | 2023-12-16 | 2021-12-17 | 2023-12-16
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PNYR37 | PlaNYC - FY18 Reforestation Bx & Mnt | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PNYR37 | PlaNYC - FY18 Reforestation Bx & Mnt | 2 | DESIGN | 2017-12-28 | 2018-09-23 | 2017-12-28 | 2018-09-23
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PNYR37 | PlaNYC - FY18 Reforestation Bx & Mnt | 3 | BID/ REGISTER CONTRACT | 2018-09-24 | 2019-06-20 | 2018-09-24 | 2019-06-20
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PNYR37 | PlaNYC - FY18 Reforestation Bx & Mnt | 4 | CONSTRUCTION | 2019-06-21 | 2021-12-16 | 2019-06-21 | 2021-12-16
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PNYR37 | PlaNYC - FY18 Reforestation Bx & Mnt | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-12-17 | 2023-12-16 | 2021-12-17 | 2023-12-16
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PNYT25 | PlaNYC - FY21 Citiwide Tree Guard Installation | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PNYT25 | PlaNYC - FY21 Citiwide Tree Guard Installation | 2 | DESIGN | 2019-12-28 | 2021-06-19 | 2019-12-28 | 2021-06-19
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PNYT25 | PlaNYC - FY21 Citiwide Tree Guard Installation | 3 | BID/ REGISTER CONTRACT | 2021-06-20 | 2022-03-16 | 2021-06-20 | 2022-03-16
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PNYT25 | PlaNYC - FY21 Citiwide Tree Guard Installation | 4 | CONSTRUCTION | 2022-03-17 | 2024-03-15 | 2022-03-17 | 2024-03-15
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PNYT25 | PlaNYC - FY21 Citiwide Tree Guard Installation | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-03-16 | 2026-03-15 | 2024-03-16 | 2026-03-15
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6POGC15 | FY15 Citywide pool structure CNYG-1515M | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2015-09-28
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6POGC15 | FY15 Citywide pool structure CNYG-1515M | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2015-09-29 | 2015-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6POGC15 | FY15 Citywide pool structure CNYG-1515M | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2015-12-28 | 2016-03-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6POGC15 | FY15 Citywide pool structure CNYG-1515M | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6POGC15 | FY15 Citywide pool structure CNYG-1515M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2017-03-27 | 2018-03-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6POL11A | FY11 Recnstr of electrical system for pools CNYG-1611M | 1 | DEVELOP SCOPE | 2012-09-13 | 2012-12-11 | 2011-07-01 | 2011-09-28
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6POL11A | FY11 Recnstr of electrical system for pools CNYG-1611M | 2 | DESIGN | 2012-12-12 | 2013-03-11 | 2011-09-29 | 2011-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6POL11A | FY11 Recnstr of electrical system for pools CNYG-1611M | 3 | BID/ REGISTER CONTRACT | 2013-03-12 | 2013-06-09 | 2011-12-28 | 2012-03-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6POL11A | FY11 Recnstr of electrical system for pools CNYG-1611M | 4 | CONSTRUCTION | 2013-06-10 | 2014-06-09 | 2012-03-27 | 2013-03-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6POL11A | FY11 Recnstr of electrical system for pools CNYG-1611M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-06-10 | 2015-06-09 | 2013-03-27 | 2014-03-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6POOL18 | Recon Citywide pools $1 Contract CNYG-918M | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6POOL18 | Recon Citywide pools $1 Contract CNYG-918M | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6POOL18 | Recon Citywide pools $1 Contract CNYG-918M | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6POOL18 | Recon Citywide pools $1 Contract CNYG-918M | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6POOL18 | Recon Citywide pools $1 Contract CNYG-918M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PRKLOT | Recon 5Boro & Garage complex prkg lot M104-117M | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PRKLOT | Recon 5Boro & Garage complex prkg lot M104-117M | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2016-12-28 | 2017-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PRKLOT | Recon 5Boro & Garage complex prkg lot M104-117M | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2017-12-28 | 2018-09-23
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PRKLOT | Recon 5Boro & Garage complex prkg lot M104-117M | 4 | CONSTRUCTION | 2018-09-24 | 2019-09-23 | 2018-09-24 | 2019-09-23
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PRKLOT | Recon 5Boro & Garage complex prkg lot M104-117M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PVMNT1 | Reconstruct pavement various Parks CNYG-117MA | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PVMNT1 | Reconstruct pavement various Parks CNYG-117MA | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PVMNT1 | Reconstruct pavement various Parks CNYG-117MA | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PVMNT1 | Reconstruct pavement various Parks CNYG-117MA | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PVMNT1 | Reconstruct pavement various Parks CNYG-117MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PVMNT2 | Citywide Pavement Reconstruction 2 CNYG-1618M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PVMNT2 | Citywide Pavement Reconstruction 2 CNYG-1618M | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PVMNT2 | Citywide Pavement Reconstruction 2 CNYG-1618M | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PVMNT2 | Citywide Pavement Reconstruction 2 CNYG-1618M | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PVMNT2 | Citywide Pavement Reconstruction 2 CNYG-1618M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6REC07B | FY07 Recreation & Nature Centers (Elec) - CNYG-1807M | 1 | DEVELOP SCOPE | 2018-01-29 | 2018-07-27 | 2018-01-29 | 2018-07-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6REC07B | FY07 Recreation & Nature Centers (Elec) - CNYG-1807M | 2 | DESIGN | 2018-07-28 | 2019-07-27 | 2018-07-28 | 2019-07-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6REC07B | FY07 Recreation & Nature Centers (Elec) - CNYG-1807M | 3 | BID/ REGISTER CONTRACT | 2019-07-28 | 2020-04-22 | 2019-07-28 | 2020-04-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6REC07B | FY07 Recreation & Nature Centers (Elec) - CNYG-1807M | 4 | CONSTRUCTION | 2020-04-23 | 2021-04-22 | 2020-04-23 | 2021-04-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6REC07B | FY07 Recreation & Nature Centers (Elec) - CNYG-1807M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-04-23 | 2022-04-22 | 2021-04-23 | 2022-04-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6REC07D | FY07 Recreation & Nature Centers (HVAC) - CNYG-2007MA2 | 1 | DEVELOP SCOPE | 2008-07-01 | 2008-09-28 | 2008-07-01 | 2008-09-28
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6REC07D | FY07 Recreation & Nature Centers (HVAC) - CNYG-2007MA2 | 2 | DESIGN | 2008-09-29 | 2008-12-27 | 2008-09-29 | 2008-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6REC07D | FY07 Recreation & Nature Centers (HVAC) - CNYG-2007MA2 | 3 | BID/ REGISTER CONTRACT | 2008-12-28 | 2009-03-27 | 2008-12-28 | 2009-03-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6REC07D | FY07 Recreation & Nature Centers (HVAC) - CNYG-2007MA2 | 4 | CONSTRUCTION | 2009-03-28 | 2010-03-27 | 2009-03-28 | 2010-03-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6REC07D | FY07 Recreation & Nature Centers (HVAC) - CNYG-2007MA2 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2010-03-28 | 2011-03-27 | 2010-03-28 | 2014-04-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6REC11B | Queens, Brooklyn & SI HVAC systems CNYG-1910MA1 | 1 | DEVELOP SCOPE | 2010-01-01 | 2010-02-25 | 2009-12-26 | 2010-02-19
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6REC11B | Queens, Brooklyn & SI HVAC systems CNYG-1910MA1 | 2 | DESIGN | 2010-02-26 | 2010-03-03 | 2010-02-20 | 2010-02-25
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6REC11B | Queens, Brooklyn & SI HVAC systems CNYG-1910MA1 | 3 | BID/ REGISTER CONTRACT | 2010-03-04 | 2010-03-03 | 2010-02-26 | 2010-02-25
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6REC11B | Queens, Brooklyn & SI HVAC systems CNYG-1910MA1 | 4 | CONSTRUCTION | 2010-03-04 | 2010-03-03 | 2010-02-26 | 2010-02-25
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6REC11B | Queens, Brooklyn & SI HVAC systems CNYG-1910MA1 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2010-03-04 | 2011-03-03 | 2010-02-26 | 2014-04-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6REF20A | Reforestation FY20 Br & Que CB8-14 | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6REF20A | Reforestation FY20 Br & Que CB8-14 | 2 | DESIGN | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6REF20A | Reforestation FY20 Br & Que CB8-14 | 3 | BID/ REGISTER CONTRACT | 2019-09-24 | 2020-06-19 | 2019-09-24 | 2020-06-19
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6REF20A | Reforestation FY20 Br & Que CB8-14 | 4 | CONSTRUCTION | 2020-06-20 | 2022-12-16 | 2020-06-20 | 2022-12-16
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6REF20A | Reforestation FY20 Br & Que CB8-14 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-12-17 | 2024-12-15 | 2022-12-17 | 2024-12-15
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6REF20B | Reforestation FY20 BX & Que CB 1-7 | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6REF20B | Reforestation FY20 BX & Que CB 1-7 | 2 | DESIGN | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6REF20B | Reforestation FY20 BX & Que CB 1-7 | 3 | BID/ REGISTER CONTRACT | 2019-09-24 | 2020-06-19 | 2019-09-24 | 2020-06-19
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6REF20B | Reforestation FY20 BX & Que CB 1-7 | 4 | CONSTRUCTION | 2020-06-20 | 2022-12-16 | 2020-06-20 | 2022-12-16
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6REF20B | Reforestation FY20 BX & Que CB 1-7 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-12-17 | 2024-12-15 | 2022-12-17 | 2024-12-15
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6REMT35 | Non Sandy Tree Removal Bx, Mht, Qn | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6REMT35 | Non Sandy Tree Removal Bx, Mht, Qn | 2 | DESIGN | 2017-12-28 | 2018-06-25 | 2017-12-28 | 2018-06-25
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6REMT35 | Non Sandy Tree Removal Bx, Mht, Qn | 3 | BID/ REGISTER CONTRACT | 2018-06-26 | 2019-03-22 | 2018-06-26 | 2019-03-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6REMT35 | Non Sandy Tree Removal Bx, Mht, Qn | 4 | CONSTRUCTION | 2019-03-23 | 2020-09-12 | 2019-03-23 | 2020-09-12
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6REMT35 | Non Sandy Tree Removal Bx, Mht, Qn | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-13 | 2022-09-12 | 2020-09-13 | 2022-09-12
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6REMT37 | Tree Removal Bx, Mht, Qn FY19 | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6REMT37 | Tree Removal Bx, Mht, Qn FY19 | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6REMT37 | Tree Removal Bx, Mht, Qn FY19 | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6REMT37 | Tree Removal Bx, Mht, Qn FY19 | 4 | CONSTRUCTION | 2020-09-23 | 2022-09-22 | 2020-09-23 | 2022-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6REMT37 | Tree Removal Bx, Mht, Qn FY19 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6REQ1 | State of Good Repair - CW | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6REQ1 | State of Good Repair - CW | 2 | DESIGN | 2019-12-28 | 2021-06-24 | 2019-12-28 | 2021-06-24
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6REQ1 | State of Good Repair - CW | 3 | BID/ REGISTER CONTRACT | 2021-06-25 | 2022-03-21 | 2021-06-25 | 2022-03-21
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6REQ1 | State of Good Repair - CW | 4 | CONSTRUCTION | 2022-03-22 | 2023-09-17 | 2022-03-22 | 2023-09-17
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6REQ1 | State of Good Repair - CW | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-18 | 2024-09-16 | 2023-09-18 | 2024-09-16
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6REQU | State of Good Repair - CW | 1 | DEVELOP SCOPE | 2006-07-01 | 2006-09-28 | 2006-07-01 | 2006-09-28
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6REQU | State of Good Repair - CW | 2 | DESIGN | 2006-09-29 | 2006-12-27 | 2006-09-29 | 2006-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6REQU | State of Good Repair - CW | 3 | BID/ REGISTER CONTRACT | 2006-12-28 | 2007-03-27 | 2006-12-28 | 2007-03-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6REQU | State of Good Repair - CW | 4 | CONSTRUCTION | 2007-03-28 | 2008-03-26 | 2007-03-28 | 2008-03-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6REQU | State of Good Repair - CW | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-27 | 2009-03-26 | 2008-03-27 | 2017-03-01
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6RETW11 | FY11-Reconstr & stabilization of retaining walls CNYG-1511M | 1 | DEVELOP SCOPE | 2012-09-12 | 2012-12-10 | 2011-07-01 | 2011-09-28
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6RETW11 | FY11-Reconstr & stabilization of retaining walls CNYG-1511M | 2 | DESIGN | 2012-12-11 | 2013-03-10 | 2011-09-29 | 2011-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6RETW11 | FY11-Reconstr & stabilization of retaining walls CNYG-1511M | 3 | BID/ REGISTER CONTRACT | 2013-03-11 | 2013-06-08 | 2011-12-28 | 2012-03-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6RETW11 | FY11-Reconstr & stabilization of retaining walls CNYG-1511M | 4 | CONSTRUCTION | 2013-06-09 | 2014-06-08 | 2012-03-27 | 2013-03-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6RETW11 | FY11-Reconstr & stabilization of retaining walls CNYG-1511M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-06-09 | 2015-06-08 | 2013-03-27 | 2014-03-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6RETW14 | Retaining Wall R/C (CNYG-514M) | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2013-09-28
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6RETW14 | Retaining Wall R/C (CNYG-514M) | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2013-09-29 | 2013-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6RETW14 | Retaining Wall R/C (CNYG-514M) | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2013-12-28 | 2014-03-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6RETW14 | Retaining Wall R/C (CNYG-514M) | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2014-03-28 | 2015-03-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6RETW14 | Retaining Wall R/C (CNYG-514M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2019-03-30
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6RETW18 | Citywide Retaining Wall FY18 CNYG-1818M | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6RETW18 | Citywide Retaining Wall FY18 CNYG-1818M | 2 | DESIGN | 2018-12-28 | 2020-06-24 | 2018-12-28 | 2020-06-24
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6RETW18 | Citywide Retaining Wall FY18 CNYG-1818M | 3 | BID/ REGISTER CONTRACT | 2020-06-25 | 2021-03-21 | 2020-06-25 | 2021-03-21
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6RETW18 | Citywide Retaining Wall FY18 CNYG-1818M | 4 | CONSTRUCTION | 2021-03-22 | 2022-09-17 | 2021-03-22 | 2022-09-17
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6RETW18 | Citywide Retaining Wall FY18 CNYG-1818M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-18 | 2023-09-17 | 2022-09-18 | 2023-09-17
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6RFMN14 | FY14 RECON ROOFINGS IN MANHATTAN MG-614M | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2013-09-28
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6RFMN14 | FY14 RECON ROOFINGS IN MANHATTAN MG-614M | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2013-09-29 | 2013-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6RFMN14 | FY14 RECON ROOFINGS IN MANHATTAN MG-614M | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2013-12-28 | 2014-03-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6RFMN14 | FY14 RECON ROOFINGS IN MANHATTAN MG-614M | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2014-03-28 | 2015-03-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6RFMN14 | FY14 RECON ROOFINGS IN MANHATTAN MG-614M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2016-03-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6ROOF14 | FY14 Roof Requirements for Bronx & Queens CNYG-1114M | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2013-09-28
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6ROOF14 | FY14 Roof Requirements for Bronx & Queens CNYG-1114M | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2013-09-29 | 2013-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6ROOF14 | FY14 Roof Requirements for Bronx & Queens CNYG-1114M | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2013-12-28 | 2014-03-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6ROOF14 | FY14 Roof Requirements for Bronx & Queens CNYG-1114M | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2014-03-28 | 2015-03-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6ROOF14 | FY14 Roof Requirements for Bronx & Queens CNYG-1114M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2016-03-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6ROOF15 | FY15 Citywide roofing CNYG-1115M | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2015-09-28
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6ROOF15 | FY15 Citywide roofing CNYG-1115M | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2015-09-29 | 2015-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6ROOF15 | FY15 Citywide roofing CNYG-1115M | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2015-12-28 | 2016-03-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6ROOF15 | FY15 Citywide roofing CNYG-1115M | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6ROOF15 | FY15 Citywide roofing CNYG-1115M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2017-03-27 | 2018-03-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6ROOF9A | FY09 Roof Requirements QNS & BX (CNYG-3009M) | 1 | DEVELOP SCOPE | 2010-07-01 | 2010-09-28 | 2010-07-01 | 2010-09-28
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6ROOF9A | FY09 Roof Requirements QNS & BX (CNYG-3009M) | 2 | DESIGN | 2010-09-29 | 2010-12-27 | 2010-09-29 | 2010-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6ROOF9A | FY09 Roof Requirements QNS & BX (CNYG-3009M) | 3 | BID/ REGISTER CONTRACT | 2010-12-28 | 2011-03-27 | 2010-12-28 | 2011-03-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6ROOF9A | FY09 Roof Requirements QNS & BX (CNYG-3009M) | 4 | CONSTRUCTION | 2011-03-28 | 2012-03-26 | 2011-03-28 | 2012-03-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6ROOF9A | FY09 Roof Requirements QNS & BX (CNYG-3009M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-03-27 | 2013-03-26 | 2012-03-27 | 2014-04-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6RPZBKQ | Brooklyn & Queens Multi-Site RPZ Installation | 1 | DEVELOP SCOPE | 2020-07-01 | 2020-12-27 | 2020-07-01 | 2020-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6RPZBKQ | Brooklyn & Queens Multi-Site RPZ Installation | 2 | DESIGN | 2020-12-28 | 2021-12-27 | 2020-12-28 | 2021-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6RPZBKQ | Brooklyn & Queens Multi-Site RPZ Installation | 3 | BID/ REGISTER CONTRACT | 2021-12-28 | 2022-09-23 | 2021-12-28 | 2022-09-23
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6RPZBKQ | Brooklyn & Queens Multi-Site RPZ Installation | 4 | CONSTRUCTION | 2022-09-24 | 2023-09-23 | 2022-09-24 | 2023-09-23
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6RPZBKQ | Brooklyn & Queens Multi-Site RPZ Installation | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-24 | 2024-09-22 | 2023-09-24 | 2024-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6SANDT1 | FY18 Sandy Related Tree Replacement - Q, X, M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6SANDT1 | FY18 Sandy Related Tree Replacement - Q, X, M | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6SANDT1 | FY18 Sandy Related Tree Replacement - Q, X, M | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6SANDT1 | FY18 Sandy Related Tree Replacement - Q, X, M | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6SANDT1 | FY18 Sandy Related Tree Replacement - Q, X, M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6SECBOL | Parks Security Measures Citywide | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6SECBOL | Parks Security Measures Citywide | 2 | DESIGN | 2017-12-28 | 2019-06-25 | 2017-12-28 | 2019-06-25
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6SECBOL | Parks Security Measures Citywide | 3 | BID/ REGISTER CONTRACT | 2019-06-26 | 2020-03-21 | 2019-06-26 | 2020-03-21
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6SECBOL | Parks Security Measures Citywide | 4 | CONSTRUCTION | 2020-03-22 | 2021-09-17 | 2020-03-22 | 2021-09-17
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6SECBOL | Parks Security Measures Citywide | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-18 | 2022-09-17 | 2021-09-18 | 2022-09-17
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6SPCR15 | NRG - Spring Creek Salt Marsh Restoration CNYG-2715M | 1 | DEVELOP SCOPE | 2014-09-01 | 2014-11-29 | 2014-09-01 | 2014-11-29
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6SPCR15 | NRG - Spring Creek Salt Marsh Restoration CNYG-2715M | 2 | DESIGN | 2014-11-30 | 2015-02-27 | 2014-11-30 | 2016-05-31
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6SPCR15 | NRG - Spring Creek Salt Marsh Restoration CNYG-2715M | 3 | BID/ REGISTER CONTRACT | 2015-02-28 | 2015-05-28 | 2016-06-01 | 2016-08-29
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6SPCR15 | NRG - Spring Creek Salt Marsh Restoration CNYG-2715M | 4 | CONSTRUCTION | 2015-05-29 | 2016-05-27 | 2016-08-30 | 2020-08-29
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6SPCR15 | NRG - Spring Creek Salt Marsh Restoration CNYG-2715M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-05-28 | 2017-05-27 | 2020-08-30 | 2024-08-29
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6STRUC1 | Citywide structural stabilization - Multisite CNYG-1617M | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6STRUC1 | Citywide structural stabilization - Multisite CNYG-1617M | 2 | DESIGN | 2016-12-28 | 2018-06-25 | 2016-12-28 | 2018-06-25
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6STRUC1 | Citywide structural stabilization - Multisite CNYG-1617M | 3 | BID/ REGISTER CONTRACT | 2018-06-26 | 2019-03-22 | 2018-06-26 | 2019-03-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6STRUC1 | Citywide structural stabilization - Multisite CNYG-1617M | 4 | CONSTRUCTION | 2019-03-23 | 2020-09-17 | 2019-03-23 | 2020-09-17
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6STRUC1 | Citywide structural stabilization - Multisite CNYG-1617M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-18 | 2021-09-17 | 2020-09-18 | 2021-09-17
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6STURF1 | Reconstruction of Synthetic Turf Fields Citywide MG-718M | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6STURF1 | Reconstruction of Synthetic Turf Fields Citywide MG-718M | 2 | DESIGN | 2018-12-28 | 2020-06-24 | 2018-12-28 | 2020-06-24
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6STURF1 | Reconstruction of Synthetic Turf Fields Citywide MG-718M | 3 | BID/ REGISTER CONTRACT | 2020-06-25 | 2021-03-21 | 2020-06-25 | 2021-03-21
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6STURF1 | Reconstruction of Synthetic Turf Fields Citywide MG-718M | 4 | CONSTRUCTION | 2021-03-22 | 2022-09-17 | 2021-03-22 | 2022-09-17
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6STURF1 | Reconstruction of Synthetic Turf Fields Citywide MG-718M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-18 | 2023-09-17 | 2022-09-18 | 2023-09-17
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRAI20 | FY19 NRG Arden Woods Trail Construction | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRAI20 | FY19 NRG Arden Woods Trail Construction | 2 | DESIGN | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRAI20 | FY19 NRG Arden Woods Trail Construction | 3 | BID/ REGISTER CONTRACT | 2019-09-24 | 2020-06-19 | 2019-09-24 | 2020-06-19
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRAI20 | FY19 NRG Arden Woods Trail Construction | 4 | CONSTRUCTION | 2020-06-20 | 2022-12-16 | 2020-06-20 | 2022-12-16
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRAI20 | FY19 NRG Arden Woods Trail Construction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-12-17 | 2024-12-15 | 2022-12-17 | 2024-12-15
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRBRSI | Park Trees-Trees Replanting Brooklyn & SI | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRBRSI | Park Trees-Trees Replanting Brooklyn & SI | 2 | DESIGN | 2017-12-28 | 2018-06-25 | 2017-12-28 | 2018-06-25
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRBRSI | Park Trees-Trees Replanting Brooklyn & SI | 3 | BID/ REGISTER CONTRACT | 2018-06-26 | 2019-03-22 | 2018-06-26 | 2019-03-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRBRSI | Park Trees-Trees Replanting Brooklyn & SI | 4 | CONSTRUCTION | 2019-03-23 | 2020-09-12 | 2019-03-23 | 2020-09-12
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRBRSI | Park Trees-Trees Replanting Brooklyn & SI | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-13 | 2022-09-12 | 2020-09-13 | 2022-09-12
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRE18A | Street Trees Supervision FY18 | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRE18A | Street Trees Supervision FY18 | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRE18A | Street Trees Supervision FY18 | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRE18A | Street Trees Supervision FY18 | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRE18A | Street Trees Supervision FY18 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRE19A | Street Trees Supervision FY19 | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRE19A | Street Trees Supervision FY19 | 2 | DESIGN | 2018-12-28 | 2019-06-25 | 2018-12-28 | 2019-06-25
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRE19A | Street Trees Supervision FY19 | 3 | BID/ REGISTER CONTRACT | 2019-06-26 | 2019-12-22 | 2019-06-26 | 2019-12-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRE19A | Street Trees Supervision FY19 | 4 | CONSTRUCTION | 2019-12-23 | 2028-12-19 | 2019-12-23 | 2028-12-19
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRE19A | Street Trees Supervision FY19 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2028-12-20 | 2029-02-17 | 2028-12-20 | 2029-02-17
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRE21S | FY21 Street Trees Supervision | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRE21S | FY21 Street Trees Supervision | 2 | DESIGN | 2019-12-28 | 2020-06-24 | 2019-12-28 | 2020-06-24
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRE21S | FY21 Street Trees Supervision | 3 | BID/ REGISTER CONTRACT | 2020-06-25 | 2021-03-21 | 2020-06-25 | 2021-03-21
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRE21S | FY21 Street Trees Supervision | 4 | CONSTRUCTION | 2021-03-22 | 2022-09-12 | 2021-03-22 | 2022-09-12
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRE21S | FY21 Street Trees Supervision | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-13 | 2024-09-11 | 2022-09-13 | 2024-09-11
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TREEP1 | Procurement of Street Trees Region 1-CNYG-3916M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TREEP1 | Procurement of Street Trees Region 1-CNYG-3916M | 2 | DESIGN | 2017-12-28 | 2018-06-25 | 2017-12-28 | 2018-06-25
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TREEP1 | Procurement of Street Trees Region 1-CNYG-3916M | 3 | BID/ REGISTER CONTRACT | 2018-06-26 | 2018-12-22 | 2018-06-26 | 2018-12-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TREEP1 | Procurement of Street Trees Region 1-CNYG-3916M | 4 | CONSTRUCTION | 2018-12-23 | 2027-12-20 | 2018-12-23 | 2027-12-20
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TREEP1 | Procurement of Street Trees Region 1-CNYG-3916M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2027-12-21 | 2028-02-18 | 2027-12-21 | 2028-02-18
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TREEP2 | Procurement of Street Trees Region 2-CNYG-4016M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TREEP2 | Procurement of Street Trees Region 2-CNYG-4016M | 2 | DESIGN | 2017-12-28 | 2018-06-25 | 2017-12-28 | 2018-06-25
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TREEP2 | Procurement of Street Trees Region 2-CNYG-4016M | 3 | BID/ REGISTER CONTRACT | 2018-06-26 | 2018-12-22 | 2018-06-26 | 2018-12-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TREEP2 | Procurement of Street Trees Region 2-CNYG-4016M | 4 | CONSTRUCTION | 2018-12-23 | 2027-12-20 | 2018-12-23 | 2027-12-20
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TREEP2 | Procurement of Street Trees Region 2-CNYG-4016M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2027-12-21 | 2028-02-18 | 2027-12-21 | 2028-02-18
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TREES2 | RISK MANAGEMENT TREES | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2013-09-28
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TREES2 | RISK MANAGEMENT TREES | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2013-09-29 | 2016-09-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TREES2 | RISK MANAGEMENT TREES | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2016-09-28 | 2016-12-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TREES2 | RISK MANAGEMENT TREES | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2016-12-27 | 2019-12-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TREES2 | RISK MANAGEMENT TREES | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2019-12-27 | 2020-12-25
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TREESB | TREES - CITYWIDE | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TREESB | TREES - CITYWIDE | 2 | DESIGN | 2018-12-28 | 2019-06-25 | 2018-12-28 | 2019-06-25
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TREESB | TREES - CITYWIDE | 3 | BID/ REGISTER CONTRACT | 2019-06-26 | 2019-12-22 | 2019-06-26 | 2019-12-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TREESB | TREES - CITYWIDE | 4 | CONSTRUCTION | 2019-12-23 | 2028-12-19 | 2019-12-23 | 2028-12-19
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TREESB | TREES - CITYWIDE | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2028-12-20 | 2029-02-17 | 2028-12-20 | 2029-02-17
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TREGRD | FY21 CitywideTree Guards | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TREGRD | FY21 CitywideTree Guards | 2 | DESIGN | 2019-12-28 | 2021-06-19 | 2019-12-28 | 2021-06-19
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TREGRD | FY21 CitywideTree Guards | 3 | BID/ REGISTER CONTRACT | 2021-06-20 | 2022-03-16 | 2021-06-20 | 2022-03-16
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TREGRD | FY21 CitywideTree Guards | 4 | CONSTRUCTION | 2022-03-17 | 2025-03-15 | 2022-03-17 | 2025-03-15
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TREGRD | FY21 CitywideTree Guards | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-03-16 | 2027-03-15 | 2025-03-16 | 2027-03-15
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TREL21 | FY21 Street Tree Long Term Supervision | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TREL21 | FY21 Street Tree Long Term Supervision | 2 | DESIGN | 2019-12-28 | 2021-06-19 | 2019-12-28 | 2021-06-19
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TREL21 | FY21 Street Tree Long Term Supervision | 3 | BID/ REGISTER CONTRACT | 2021-06-20 | 2022-03-16 | 2021-06-20 | 2022-03-16
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TREL21 | FY21 Street Tree Long Term Supervision | 4 | CONSTRUCTION | 2022-03-17 | 2025-03-15 | 2022-03-17 | 2025-03-15
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TREL21 | FY21 Street Tree Long Term Supervision | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-03-16 | 2027-03-15 | 2025-03-16 | 2027-03-15
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TREPLN | Forest Replacement Planting | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TREPLN | Forest Replacement Planting | 2 | DESIGN | 2019-12-28 | 2021-06-19 | 2019-12-28 | 2021-06-19
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TREPLN | Forest Replacement Planting | 3 | BID/ REGISTER CONTRACT | 2021-06-20 | 2022-03-16 | 2021-06-20 | 2022-03-16
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TREPLN | Forest Replacement Planting | 4 | CONSTRUCTION | 2022-03-17 | 2025-03-15 | 2022-03-17 | 2025-03-15
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TREPLN | Forest Replacement Planting | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-03-16 | 2027-03-15 | 2025-03-16 | 2027-03-15
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TREPLS | Street & Park Tree Replacement Planting | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TREPLS | Street & Park Tree Replacement Planting | 2 | DESIGN | 2019-12-28 | 2021-06-19 | 2019-12-28 | 2021-06-19
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TREPLS | Street & Park Tree Replacement Planting | 3 | BID/ REGISTER CONTRACT | 2021-06-20 | 2022-03-16 | 2021-06-20 | 2022-03-16
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TREPLS | Street & Park Tree Replacement Planting | 4 | CONSTRUCTION | 2022-03-17 | 2025-03-15 | 2022-03-17 | 2025-03-15
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TREPLS | Street & Park Tree Replacement Planting | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-03-16 | 2027-03-15 | 2025-03-16 | 2027-03-15
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRREMD | TREE REMEDIATION- Sandy Damaged Trees | 1 | DEVELOP SCOPE | 2015-04-01 | 2015-06-29 | 2015-04-01 | 2015-06-29
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRREMD | TREE REMEDIATION- Sandy Damaged Trees | 2 | DESIGN | 2015-06-30 | 2015-09-27 | 2015-06-30 | 2018-06-28
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRREMD | TREE REMEDIATION- Sandy Damaged Trees | 3 | BID/ REGISTER CONTRACT | 2015-09-28 | 2015-12-26 | 2018-06-29 | 2021-06-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRREMD | TREE REMEDIATION- Sandy Damaged Trees | 4 | CONSTRUCTION | 2015-12-27 | 2016-12-25 | 2021-06-28 | 2022-06-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRREMD | TREE REMEDIATION- Sandy Damaged Trees | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-12-26 | 2017-12-25 | 2022-06-28 | 2025-06-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRS19A | Citywide- R/C Sidewalks Damaged by Trees Supervision | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRS19A | Citywide- R/C Sidewalks Damaged by Trees Supervision | 2 | DESIGN | 2018-12-28 | 2019-06-25 | 2018-12-28 | 2019-06-25
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRS19A | Citywide- R/C Sidewalks Damaged by Trees Supervision | 3 | BID/ REGISTER CONTRACT | 2019-06-26 | 2019-12-22 | 2019-06-26 | 2019-12-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRS19A | Citywide- R/C Sidewalks Damaged by Trees Supervision | 4 | CONSTRUCTION | 2019-12-23 | 2028-12-19 | 2019-12-23 | 2028-12-19
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRS19A | Citywide- R/C Sidewalks Damaged by Trees Supervision | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2028-12-20 | 2029-02-17 | 2028-12-20 | 2029-02-17
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRSD19 | Bronx & Mnht- R/C Sidewalks Damaged by Trees | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRSD19 | Bronx & Mnht- R/C Sidewalks Damaged by Trees | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRSD19 | Bronx & Mnht- R/C Sidewalks Damaged by Trees | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRSD19 | Bronx & Mnht- R/C Sidewalks Damaged by Trees | 4 | CONSTRUCTION | 2020-09-23 | 2022-09-22 | 2020-09-23 | 2022-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRSD19 | Bronx & Mnht- R/C Sidewalks Damaged by Trees | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRSDWK | Citywide- R/C Sidewalks Damaged by Trees | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRSDWK | Citywide- R/C Sidewalks Damaged by Trees | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRSDWK | Citywide- R/C Sidewalks Damaged by Trees | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRSDWK | Citywide- R/C Sidewalks Damaged by Trees | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRSDWK | Citywide- R/C Sidewalks Damaged by Trees | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6UTILCW | McKenna Park - Water Line CNYG-1418M | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6UTILCW | McKenna Park - Water Line CNYG-1418M | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6UTILCW | McKenna Park - Water Line CNYG-1418M | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6UTILCW | McKenna Park - Water Line CNYG-1418M | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6UTILCW | McKenna Park - Water Line CNYG-1418M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | SANDY4330 | NYC4330 Surplus | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | SANDY4330 | NYC4330 Surplus | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | SANDY4330 | NYC4330 Surplus | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | SANDY4330 | NYC4330 Surplus | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | SANDY4330 | NYC4330 Surplus | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | SANDY4371 | NYC4371 Surplus | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | SANDY4371 | NYC4371 Surplus | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | SANDY4371 | NYC4371 Surplus | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | SANDY4371 | NYC4371 Surplus | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | SANDY4371 | NYC4371 Surplus | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | SANDY6-06 | SANDY - S.I. Beaches Protective Measures North RG-813M | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2013-09-28
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | SANDY6-06 | SANDY - S.I. Beaches Protective Measures North RG-813M | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2013-09-29 | 2013-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | SANDY6-06 | SANDY - S.I. Beaches Protective Measures North RG-813M | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2013-12-28 | 2014-03-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | SANDY6-06 | SANDY - S.I. Beaches Protective Measures North RG-813M | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2014-03-28 | 2015-03-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | SANDY6-06 | SANDY - S.I. Beaches Protective Measures North RG-813M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2019-12-30
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | SANDY6-16 | For Flushing Meadow Conduit | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | SANDY6-16 | For Flushing Meadow Conduit | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | SANDY6-16 | For Flushing Meadow Conduit | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | SANDY6-16 | For Flushing Meadow Conduit | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | SANDY6-16 | For Flushing Meadow Conduit | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | SANDY6-17 | Sandy-Trees Removal in Bk & SI CNYG-3616M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | SANDY6-17 | Sandy-Trees Removal in Bk & SI CNYG-3616M | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | SANDY6-17 | Sandy-Trees Removal in Bk & SI CNYG-3616M | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | SANDY6-17 | Sandy-Trees Removal in Bk & SI CNYG-3616M | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | SANDY6-17 | Sandy-Trees Removal in Bk & SI CNYG-3616M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | SANDY6-18 | Sandy-Trees Removal in BX ,Mnht & Que CNYG-3516M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | SANDY6-18 | Sandy-Trees Removal in BX ,Mnht & Que CNYG-3516M | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | SANDY6-18 | Sandy-Trees Removal in BX ,Mnht & Que CNYG-3516M | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | SANDY6-18 | Sandy-Trees Removal in BX ,Mnht & Que CNYG-3516M | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | SANDY6-18 | Sandy-Trees Removal in BX ,Mnht & Que CNYG-3516M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | SANDY6-20 | Sandy Tree Planting and Replanting - BK & SI | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | SANDY6-20 | Sandy Tree Planting and Replanting - BK & SI | 2 | DESIGN | 2017-12-28 | 2018-06-25 | 2017-12-28 | 2018-06-25
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | SANDY6-20 | Sandy Tree Planting and Replanting - BK & SI | 3 | BID/ REGISTER CONTRACT | 2018-06-26 | 2019-03-22 | 2018-06-26 | 2019-03-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | SANDY6-20 | Sandy Tree Planting and Replanting - BK & SI | 4 | CONSTRUCTION | 2019-03-23 | 2020-09-12 | 2019-03-23 | 2020-09-12
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | SANDY6-20 | Sandy Tree Planting and Replanting - BK & SI | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-13 | 2022-09-12 | 2020-09-13 | 2022-09-12
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | SANDY6-21 | Sandy Tree Planting and Replanting - BX, Q, & M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | SANDY6-21 | Sandy Tree Planting and Replanting - BX, Q, & M | 2 | DESIGN | 2017-12-28 | 2018-06-25 | 2017-12-28 | 2018-06-25
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | SANDY6-21 | Sandy Tree Planting and Replanting - BX, Q, & M | 3 | BID/ REGISTER CONTRACT | 2018-06-26 | 2019-03-22 | 2018-06-26 | 2019-03-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | SANDY6-21 | Sandy Tree Planting and Replanting - BX, Q, & M | 4 | CONSTRUCTION | 2019-03-23 | 2020-09-12 | 2019-03-23 | 2020-09-12
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | SANDY6-21 | Sandy Tree Planting and Replanting - BX, Q, & M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-13 | 2022-09-12 | 2020-09-13 | 2022-09-12
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | SANDYCDUT | SANDY-NYC4371 Conduit Funding | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | SANDYCDUT | SANDY-NYC4371 Conduit Funding | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | SANDYCDUT | SANDY-NYC4371 Conduit Funding | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | SANDYCDUT | SANDY-NYC4371 Conduit Funding | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | SANDYCDUT | SANDY-NYC4371 Conduit Funding | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-827 | Regulator Chamber Roof Replacements | 1 | DEVELOP SCOPE | 2017-03-01 | 2017-05-29 | 2017-03-01 | 2017-05-29
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-827 | Regulator Chamber Roof Replacements | 2 | PRELIMINARY DESIGN | 2017-05-30 | 2017-09-26 | 2017-05-30 | 2017-09-26
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-827 | Regulator Chamber Roof Replacements | 3 | FINAL DESIGN | 2017-09-27 | 2018-03-25 | 2017-09-27 | 2018-03-25
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-827 | Regulator Chamber Roof Replacements | 4 | BID AWARD AND REGISTER CONTRCT | 2018-03-26 | 2018-06-23 | 2018-03-26 | 2018-06-23
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-827 | Regulator Chamber Roof Replacements | 5 | CONSTRUCTION TO 25% | 2018-06-24 | 2018-10-21 | 2018-06-24 | 2018-10-21
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-827 | Regulator Chamber Roof Replacements | 6 | CONSTRUCTION TO 50% | 2018-10-22 | 2019-02-18 | 2018-10-22 | 2019-02-18
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-827 | Regulator Chamber Roof Replacements | 7 | CONSTRUCTION TO 75% | 2019-02-19 | 2019-06-18 | 2019-02-19 | 2019-06-18
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-827 | Regulator Chamber Roof Replacements | 8 | ORIGINAL EQUIP & FURNISHING | 2019-06-19 | 2019-09-16 | 2019-06-19 | 2019-09-16
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-827 | Regulator Chamber Roof Replacements | 9 | SUBSTANTIAL COMPLETION | 2019-09-17 | 2019-11-15 | 2019-09-17 | 2019-11-15
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-827 | Regulator Chamber Roof Replacements | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-11-16 | 2019-12-15 | 2019-11-16 | 2026-02-07
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | CT2-INTER | CITY TUNNEL #2, REPLACE GUARD VALVES @ 16A | 1 | DEVELOP SCOPE | 2015-03-01 | 2015-05-29 | 2014-07-24 | 2014-12-15
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | CT2-INTER | CITY TUNNEL #2, REPLACE GUARD VALVES @ 16A | 2 | PRELIMINARY DESIGN | 2015-05-30 | 2015-09-26 | 2014-12-16 | 2015-09-04
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | CT2-INTER | CITY TUNNEL #2, REPLACE GUARD VALVES @ 16A | 3 | FINAL DESIGN | 2015-09-27 | 2018-03-24 | 2015-09-05 | 2018-06-28
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | CT2-INTER | CITY TUNNEL #2, REPLACE GUARD VALVES @ 16A | 4 | BID AWARD AND REGISTER CONTRCT | 2018-03-25 | 2018-06-22 | 2018-06-29 | 2018-09-26
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | CT2-INTER | CITY TUNNEL #2, REPLACE GUARD VALVES @ 16A | 5 | CONSTRUCTION TO 25% | 2018-06-23 | 2018-10-20 | 2018-09-27 | 2019-01-24
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | CT2-INTER | CITY TUNNEL #2, REPLACE GUARD VALVES @ 16A | 6 | CONSTRUCTION TO 50% | 2018-10-21 | 2019-02-17 | 2019-01-25 | 2019-05-24
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | CT2-INTER | CITY TUNNEL #2, REPLACE GUARD VALVES @ 16A | 7 | CONSTRUCTION TO 75% | 2019-02-18 | 2019-06-17 | 2019-05-25 | 2019-09-21
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | CT2-INTER | CITY TUNNEL #2, REPLACE GUARD VALVES @ 16A | 8 | ORIGINAL EQUIP & FURNISHING | 2019-06-18 | 2019-06-17 | 2019-09-22 | 2019-09-21
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | CT2-INTER | CITY TUNNEL #2, REPLACE GUARD VALVES @ 16A | 9 | SUBSTANTIAL COMPLETION | 2019-06-18 | 2019-09-15 | 2019-09-22 | 2019-12-20
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | CT2-INTER | CITY TUNNEL #2, REPLACE GUARD VALVES @ 16A | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-16 | 2019-10-15 | 2019-12-21 | 2024-06-30
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | F175EMS17 | EMS Station 17 - New Facility | 1 | PROJECT START | 2019-06-29 | 2019-06-29 | 2019-06-29 | 2019-06-29
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | F175EMS17 | EMS Station 17 - New Facility | 2 | DESIGN START | 2019-06-30 | 2019-06-30 | 2019-06-30 | 2019-06-30
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | F175EMS17 | EMS Station 17 - New Facility | 3 | DESIGN COMPLETION | 2019-07-01 | 2019-07-01 | 2019-07-01 | 2019-07-01
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | F175EMS17 | EMS Station 17 - New Facility | 4 | CONSTRUCTION START | 2019-07-02 | 2019-07-02 | 2019-07-02 | 2019-07-02
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | F175EMS17 | EMS Station 17 - New Facility | 5 | CONSTRUCTION COMPLETION | 2019-07-03 | 2019-07-03 | 2019-07-03 | 2019-07-03
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | F175EMS17 | EMS Station 17 - New Facility | 6 | DEVELOP SCOPE | 2019-07-04 | 2019-10-01 | 2019-07-04 | 2019-10-01
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | F175EMS17 | EMS Station 17 - New Facility | 7 | PRELIMINARY DESIGN | 2019-10-02 | 2020-01-29 | 2019-10-02 | 2020-01-29
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | F175EMS17 | EMS Station 17 - New Facility | 8 | FINAL DESIGN | 2020-01-30 | 2020-07-27 | 2020-01-30 | 2020-07-27
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | F175EMS17 | EMS Station 17 - New Facility | 9 | BID AWARD AND REGISTER CONTRCT | 2020-07-28 | 2020-10-25 | 2020-07-28 | 2020-10-25
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | F175EMS17 | EMS Station 17 - New Facility | 10 | CONSTRUCTION TO 25% | 2020-10-26 | 2021-02-22 | 2020-10-26 | 2021-02-22
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | F175EMS17 | EMS Station 17 - New Facility | 11 | CONSTRUCTION TO 50% | 2021-02-23 | 2021-06-22 | 2021-02-23 | 2021-06-22
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | F175EMS17 | EMS Station 17 - New Facility | 12 | CONSTRUCTION TO 75% | 2021-06-23 | 2021-10-20 | 2021-06-23 | 2021-10-20
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | F175EMS17 | EMS Station 17 - New Facility | 13 | ORIGINAL EQUIP & FURNISHING | 2021-10-21 | 2022-01-18 | 2021-10-21 | 2022-01-18
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | F175EMS17 | EMS Station 17 - New Facility | 14 | SUBSTANTIAL COMPLETION | 2022-01-19 | 2022-03-19 | 2022-01-19 | 2022-03-19
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | F175EMS17 | EMS Station 17 - New Facility | 15 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-20 | 2022-04-18 | 2022-03-20 | 2022-04-18
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | GE-353 | DIST. WM EXT/REPL; NEW BLDGS, ETC ADJ. TO T.A. FACILITIES | 1 | DEVELOP SCOPE | 2014-03-01 | 2014-05-29 | 2014-03-01 | 2014-05-29
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | GE-353 | DIST. WM EXT/REPL; NEW BLDGS, ETC ADJ. TO T.A. FACILITIES | 2 | PRELIMINARY DESIGN | 2014-05-30 | 2014-09-26 | 2014-05-30 | 2014-09-26
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | GE-353 | DIST. WM EXT/REPL; NEW BLDGS, ETC ADJ. TO T.A. FACILITIES | 3 | FINAL DESIGN | 2014-09-27 | 2015-03-25 | 2014-09-27 | 2015-03-25
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | GE-353 | DIST. WM EXT/REPL; NEW BLDGS, ETC ADJ. TO T.A. FACILITIES | 4 | BID AWARD AND REGISTER CONTRCT | 2015-03-26 | 2015-06-23 | 2015-03-26 | 2015-06-23
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | GE-353 | DIST. WM EXT/REPL; NEW BLDGS, ETC ADJ. TO T.A. FACILITIES | 5 | CONSTRUCTION TO 25% | 2015-06-24 | 2015-10-21 | 2015-06-24 | 2015-10-21
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | GE-353 | DIST. WM EXT/REPL; NEW BLDGS, ETC ADJ. TO T.A. FACILITIES | 6 | CONSTRUCTION TO 50% | 2015-10-22 | 2016-02-18 | 2015-10-22 | 2016-02-18
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | GE-353 | DIST. WM EXT/REPL; NEW BLDGS, ETC ADJ. TO T.A. FACILITIES | 7 | CONSTRUCTION TO 75% | 2016-02-19 | 2016-06-17 | 2016-02-19 | 2016-06-17
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | GE-353 | DIST. WM EXT/REPL; NEW BLDGS, ETC ADJ. TO T.A. FACILITIES | 8 | ORIGINAL EQUIP & FURNISHING | 2016-06-18 | 2016-09-15 | 2016-06-18 | 2018-09-15
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | GE-353 | DIST. WM EXT/REPL; NEW BLDGS, ETC ADJ. TO T.A. FACILITIES | 9 | SUBSTANTIAL COMPLETION | 2016-09-16 | 2016-11-14 | 2018-09-16 | 2018-11-14
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | GE-353 | DIST. WM EXT/REPL; NEW BLDGS, ETC ADJ. TO T.A. FACILITIES | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-11-15 | 2016-12-14 | 2018-11-15 | 2022-06-30
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | GE-359 | Area-wide Contract for Water Mains | 1 | DEVELOP SCOPE | 2017-03-01 | 2017-05-29 | 2017-03-01 | 2017-05-29
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | GE-359 | Area-wide Contract for Water Mains | 2 | PRELIMINARY DESIGN | 2017-05-30 | 2017-09-26 | 2017-05-30 | 2017-09-26
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | GE-359 | Area-wide Contract for Water Mains | 3 | FINAL DESIGN | 2017-09-27 | 2018-03-25 | 2017-09-27 | 2018-03-25
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | GE-359 | Area-wide Contract for Water Mains | 4 | BID AWARD AND REGISTER CONTRCT | 2018-03-26 | 2018-06-23 | 2018-03-26 | 2018-06-23
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | GE-359 | Area-wide Contract for Water Mains | 5 | CONSTRUCTION TO 25% | 2018-06-24 | 2018-10-21 | 2018-06-24 | 2018-10-21
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | GE-359 | Area-wide Contract for Water Mains | 6 | CONSTRUCTION TO 50% | 2018-10-22 | 2019-02-18 | 2018-10-22 | 2019-02-18
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | GE-359 | Area-wide Contract for Water Mains | 7 | CONSTRUCTION TO 75% | 2019-02-19 | 2019-06-18 | 2019-02-19 | 2019-06-18
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | GE-359 | Area-wide Contract for Water Mains | 8 | ORIGINAL EQUIP & FURNISHING | 2019-06-19 | 2019-09-16 | 2019-06-19 | 2019-09-16
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | GE-359 | Area-wide Contract for Water Mains | 9 | SUBSTANTIAL COMPLETION | 2019-09-17 | 2019-11-15 | 2019-09-17 | 2019-11-15
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | GE-359 | Area-wide Contract for Water Mains | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-11-16 | 2019-12-15 | 2019-11-16 | 2021-08-31
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | GE-363 | Energency Reconstruction of Water Mains, Citywide | 1 | DEVELOP SCOPE | 2020-03-19 | 2020-06-16 | 2020-03-19 | 2020-06-16
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | GE-363 | Energency Reconstruction of Water Mains, Citywide | 2 | PRELIMINARY DESIGN | 2020-06-17 | 2020-10-14 | 2020-06-17 | 2020-10-14
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | GE-363 | Energency Reconstruction of Water Mains, Citywide | 3 | FINAL DESIGN | 2020-10-15 | 2021-04-12 | 2020-10-15 | 2021-04-12
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | GE-363 | Energency Reconstruction of Water Mains, Citywide | 4 | BID AWARD AND REGISTER CONTRCT | 2021-04-13 | 2021-07-11 | 2021-04-13 | 2021-07-11
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | GE-363 | Energency Reconstruction of Water Mains, Citywide | 5 | CONSTRUCTION TO 25% | 2021-07-12 | 2021-11-08 | 2021-07-12 | 2021-11-08
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | GE-363 | Energency Reconstruction of Water Mains, Citywide | 6 | CONSTRUCTION TO 50% | 2021-11-09 | 2022-03-08 | 2021-11-09 | 2022-03-08
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | GE-363 | Energency Reconstruction of Water Mains, Citywide | 7 | CONSTRUCTION TO 75% | 2022-03-09 | 2022-07-06 | 2022-03-09 | 2022-07-06
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | GE-363 | Energency Reconstruction of Water Mains, Citywide | 8 | ORIGINAL EQUIP & FURNISHING | 2022-07-07 | 2022-10-04 | 2022-07-07 | 2022-10-04
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | GE-363 | Energency Reconstruction of Water Mains, Citywide | 9 | SUBSTANTIAL COMPLETION | 2022-10-05 | 2022-12-03 | 2022-10-05 | 2022-12-03
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | GE-363 | Energency Reconstruction of Water Mains, Citywide | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-12-04 | 2024-09-12 | 2022-12-04 | 2024-09-12
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HR25FACA | FACADE RESTORATION MULTIPLE SITES | 1 | PROJECT START | 2010-09-24 | 2010-09-24 | 2010-09-24 | 2010-09-24
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HR25FACA | FACADE RESTORATION MULTIPLE SITES | 2 | DESIGN START | 2011-05-20 | 2011-05-20 | 2011-05-20 | 2011-10-14
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HR25FACA | FACADE RESTORATION MULTIPLE SITES | 3 | DESIGN COMPLETION | 2012-03-15 | 2012-03-15 | 2012-03-15 | 2014-05-15
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HR25FACA | FACADE RESTORATION MULTIPLE SITES | 4 | CONSTRUCTION START | 2012-09-26 | 2012-09-26 | 2012-09-26 | 2014-11-26
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HR25FACA | FACADE RESTORATION MULTIPLE SITES | 5 | CONSTRUCTION COMPLETION | 2014-02-04 | 2014-02-04 | 2014-02-04 | 2020-08-30
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HR25FACA4 | FACADE RESTORATION MULTIPLE SITES | 1 | PROJECT START | 2018-09-29 | 2018-09-29 | 2018-09-29 | 2018-09-29
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HR25FACA4 | FACADE RESTORATION MULTIPLE SITES | 2 | DESIGN START | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HR25FACA4 | FACADE RESTORATION MULTIPLE SITES | 3 | DESIGN COMPLETION | 2018-10-01 | 2018-10-01 | 2018-10-01 | 2018-10-01
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HR25FACA4 | FACADE RESTORATION MULTIPLE SITES | 4 | CONSTRUCTION START | 2018-10-02 | 2020-08-01 | 2018-10-02 | 2020-08-01
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HR25FACA4 | FACADE RESTORATION MULTIPLE SITES | 5 | CONSTRUCTION COMPLETION | 2020-08-02 | 2022-08-01 | 2020-08-02 | 2022-08-01
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCPEDLOC | Perimeter Security Measures | 1 | DEVELOP SCOPE | 2017-06-30 | 2017-09-27 | 2017-06-30 | 2017-09-27
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCPEDLOC | Perimeter Security Measures | 2 | PRELIMINARY DESIGN | 2017-09-28 | 2018-01-25 | 2017-09-28 | 2018-01-25
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCPEDLOC | Perimeter Security Measures | 3 | FINAL DESIGN | 2018-01-26 | 2018-07-24 | 2018-01-26 | 2018-07-24
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCPEDLOC | Perimeter Security Measures | 4 | BID AWARD AND REGISTER CONTRCT | 2018-07-25 | 2018-10-22 | 2018-07-25 | 2018-10-22
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCPEDLOC | Perimeter Security Measures | 5 | CONSTRUCTION TO 25% | 2018-10-23 | 2019-02-19 | 2018-10-23 | 2019-02-19
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCPEDLOC | Perimeter Security Measures | 6 | CONSTRUCTION TO 50% | 2019-02-20 | 2019-06-19 | 2019-02-20 | 2019-06-19
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCPEDLOC | Perimeter Security Measures | 7 | CONSTRUCTION TO 75% | 2019-06-20 | 2019-10-17 | 2019-06-20 | 2019-10-17
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCPEDLOC | Perimeter Security Measures | 8 | ORIGINAL EQUIP & FURNISHING | 2019-10-18 | 2020-01-15 | 2019-10-18 | 2020-01-15
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCPEDLOC | Perimeter Security Measures | 9 | SUBSTANTIAL COMPLETION | 2020-01-16 | 2020-03-15 | 2020-01-16 | 2020-03-15
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCPEDLOC | Perimeter Security Measures | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-03-16 | 2020-04-14 | 2020-03-16 | 2025-06-30
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3E | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 1 | DEVELOP SCOPE | 2009-02-18 | 2009-05-18 | 2011-07-01 | 2011-09-28
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3E | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 2 | PRELIMINARY DESIGN | 2009-05-19 | 2009-09-15 | 2011-09-29 | 2012-01-26
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3E | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 3 | FINAL DESIGN | 2009-09-16 | 2010-03-14 | 2012-01-27 | 2013-09-02
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3E | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 4 | BID AWARD AND REGISTER CONTRCT | 2010-03-15 | 2010-06-12 | 2013-09-03 | 2013-12-01
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3E | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 5 | CONSTRUCTION TO 25% | 2010-06-13 | 2010-10-10 | 2013-12-02 | 2014-03-31
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3E | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 6 | CONSTRUCTION TO 50% | 2010-10-11 | 2011-02-07 | 2014-04-01 | 2014-07-29
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3E | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 7 | CONSTRUCTION TO 75% | 2011-02-08 | 2011-06-07 | 2014-07-30 | 2015-02-14
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3E | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 8 | ORIGINAL EQUIP & FURNISHING | 2011-06-08 | 2011-09-05 | 2015-02-15 | 2015-05-15
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3E | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 9 | SUBSTANTIAL COMPLETION | 2011-09-06 | 2011-11-04 | 2015-05-16 | 2015-07-14
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3E | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2011-11-05 | 2011-12-04 | 2015-07-15 | 2024-08-13
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3F1 | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 1 | DEVELOP SCOPE | 2014-02-16 | 2014-05-16 | 2014-02-16 | 2014-05-16
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3F1 | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 2 | PRELIMINARY DESIGN | 2014-05-17 | 2014-09-13 | 2014-05-17 | 2014-09-13
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3F1 | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 3 | FINAL DESIGN | 2014-09-14 | 2015-03-12 | 2014-09-14 | 2015-03-12
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3F1 | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 4 | BID AWARD AND REGISTER CONTRCT | 2015-03-13 | 2015-06-10 | 2015-03-13 | 2015-06-10
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3F1 | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 5 | CONSTRUCTION TO 25% | 2015-06-11 | 2015-10-08 | 2015-06-11 | 2015-10-08
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3F1 | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 6 | CONSTRUCTION TO 50% | 2015-10-09 | 2016-02-05 | 2015-10-09 | 2016-02-05
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3F1 | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 7 | CONSTRUCTION TO 75% | 2016-02-06 | 2016-06-04 | 2016-02-06 | 2016-06-04
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3F1 | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 8 | ORIGINAL EQUIP & FURNISHING | 2016-06-05 | 2016-09-02 | 2016-06-05 | 2016-09-02
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3F1 | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 9 | SUBSTANTIAL COMPLETION | 2016-09-03 | 2016-11-01 | 2016-09-03 | 2016-11-01
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3F1 | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-11-02 | 2016-12-01 | 2016-11-02 | 2022-06-29
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3G1 | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 1 | DEVELOP SCOPE | 2014-02-16 | 2014-05-16 | 2014-02-16 | 2014-05-16
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3G1 | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 2 | PRELIMINARY DESIGN | 2014-05-17 | 2014-09-13 | 2014-05-17 | 2014-09-13
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3G1 | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 3 | FINAL DESIGN | 2014-09-14 | 2015-03-12 | 2014-09-14 | 2015-03-12
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3G1 | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 4 | BID AWARD AND REGISTER CONTRCT | 2015-03-13 | 2015-06-10 | 2015-03-13 | 2015-06-10
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3G1 | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 5 | CONSTRUCTION TO 25% | 2015-06-11 | 2015-10-08 | 2015-06-11 | 2015-10-08
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3G1 | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 6 | CONSTRUCTION TO 50% | 2015-10-09 | 2016-02-05 | 2015-10-09 | 2016-02-05
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3G1 | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 7 | CONSTRUCTION TO 75% | 2016-02-06 | 2016-06-04 | 2016-02-06 | 2016-06-04
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3G1 | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 8 | ORIGINAL EQUIP & FURNISHING | 2016-06-05 | 2016-09-02 | 2016-06-05 | 2016-09-02
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3G1 | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 9 | SUBSTANTIAL COMPLETION | 2016-09-03 | 2016-11-01 | 2016-09-03 | 2016-11-01
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3G1 | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-11-02 | 2016-12-01 | 2016-11-02 | 2024-12-01
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3G2 | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 1 | DEVELOP SCOPE | 2014-02-16 | 2014-05-16 | 2014-02-16 | 2014-05-16
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3G2 | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 2 | PRELIMINARY DESIGN | 2014-05-17 | 2014-09-13 | 2014-05-17 | 2014-09-13
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3G2 | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 3 | FINAL DESIGN | 2014-09-14 | 2015-03-12 | 2014-09-14 | 2015-03-12
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3G2 | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 4 | BID AWARD AND REGISTER CONTRCT | 2015-03-13 | 2015-06-10 | 2015-03-13 | 2015-06-10
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3G2 | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 5 | CONSTRUCTION TO 25% | 2015-06-11 | 2015-10-08 | 2015-06-11 | 2015-10-08
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3G2 | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 6 | CONSTRUCTION TO 50% | 2015-10-09 | 2016-02-05 | 2015-10-09 | 2016-02-05
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3G2 | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 7 | CONSTRUCTION TO 75% | 2016-02-06 | 2016-06-04 | 2016-02-06 | 2016-06-04
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3G2 | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 8 | ORIGINAL EQUIP & FURNISHING | 2016-06-05 | 2016-09-02 | 2016-06-05 | 2016-09-02
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3G2 | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 9 | SUBSTANTIAL COMPLETION | 2016-09-03 | 2016-11-01 | 2016-09-03 | 2016-11-01
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3G2 | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-11-02 | 2016-12-01 | 2016-11-02 | 2024-12-01
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3H1 | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 1 | DEVELOP SCOPE | 2014-02-16 | 2014-05-16 | 2014-02-16 | 2014-05-16
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3H1 | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 2 | PRELIMINARY DESIGN | 2014-05-17 | 2014-09-13 | 2014-05-17 | 2014-09-13
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3H1 | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 3 | FINAL DESIGN | 2014-09-14 | 2015-03-12 | 2014-09-14 | 2015-03-12
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3H1 | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 4 | BID AWARD AND REGISTER CONTRCT | 2015-03-13 | 2015-06-10 | 2015-03-13 | 2015-06-10
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3H1 | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 5 | CONSTRUCTION TO 25% | 2015-06-11 | 2015-10-08 | 2015-06-11 | 2015-10-08
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3H1 | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 6 | CONSTRUCTION TO 50% | 2015-10-09 | 2016-02-05 | 2015-10-09 | 2016-02-05
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3H1 | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 7 | CONSTRUCTION TO 75% | 2016-02-06 | 2016-06-04 | 2016-02-06 | 2016-06-04
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3H1 | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 8 | ORIGINAL EQUIP & FURNISHING | 2016-06-05 | 2016-09-02 | 2016-06-05 | 2016-09-02
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3H1 | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 9 | SUBSTANTIAL COMPLETION | 2016-09-03 | 2016-11-01 | 2016-09-03 | 2016-11-01
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3H1 | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-11-02 | 2016-12-01 | 2016-11-02 | 2024-12-01
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3H2 | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 1 | DEVELOP SCOPE | 2014-08-17 | 2014-11-14 | 2008-08-20 | 2010-05-05
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3H2 | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 2 | PRELIMINARY DESIGN | 2014-11-15 | 2015-03-14 | 2010-05-06 | 2010-09-02
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3H2 | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 3 | FINAL DESIGN | 2015-03-15 | 2015-09-10 | 2010-09-03 | 2013-04-22
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3H2 | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 4 | BID AWARD AND REGISTER CONTRCT | 2015-09-11 | 2015-12-09 | 2013-04-23 | 2014-03-23
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3H2 | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 5 | CONSTRUCTION TO 25% | 2015-12-10 | 2016-04-07 | 2014-03-24 | 2014-07-21
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3H2 | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 6 | CONSTRUCTION TO 50% | 2016-04-08 | 2016-08-05 | 2014-07-22 | 2014-11-18
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3H2 | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 7 | CONSTRUCTION TO 75% | 2016-08-06 | 2016-12-03 | 2014-11-19 | 2015-03-18
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3H2 | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 8 | ORIGINAL EQUIP & FURNISHING | 2016-12-04 | 2017-03-03 | 2015-03-19 | 2015-06-19
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3H2 | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 9 | SUBSTANTIAL COMPLETION | 2017-03-04 | 2017-05-02 | 2015-06-20 | 2015-08-18
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3H2 | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-05-03 | 2017-06-01 | 2015-08-19 | 2024-06-30
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4A | Safe Route to Schools - Phase 4A (MED-635) | 1 | DEVELOP SCOPE | 2014-02-16 | 2014-05-16 | 2014-02-16 | 2014-05-16
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4A | Safe Route to Schools - Phase 4A (MED-635) | 2 | PRELIMINARY DESIGN | 2014-05-17 | 2014-09-13 | 2014-05-17 | 2014-09-13
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4A | Safe Route to Schools - Phase 4A (MED-635) | 3 | FINAL DESIGN | 2014-09-14 | 2015-03-12 | 2014-09-14 | 2015-03-12
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4A | Safe Route to Schools - Phase 4A (MED-635) | 4 | BID AWARD AND REGISTER CONTRCT | 2015-03-13 | 2015-06-10 | 2015-03-13 | 2015-06-10
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4A | Safe Route to Schools - Phase 4A (MED-635) | 5 | CONSTRUCTION TO 25% | 2015-06-11 | 2015-10-08 | 2015-06-11 | 2015-10-08
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4A | Safe Route to Schools - Phase 4A (MED-635) | 6 | CONSTRUCTION TO 50% | 2015-10-09 | 2016-02-05 | 2015-10-09 | 2016-02-05
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4A | Safe Route to Schools - Phase 4A (MED-635) | 7 | CONSTRUCTION TO 75% | 2016-02-06 | 2016-06-04 | 2016-02-06 | 2016-06-04
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4A | Safe Route to Schools - Phase 4A (MED-635) | 8 | ORIGINAL EQUIP & FURNISHING | 2016-06-05 | 2016-09-02 | 2016-06-05 | 2016-09-02
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4A | Safe Route to Schools - Phase 4A (MED-635) | 9 | SUBSTANTIAL COMPLETION | 2016-09-03 | 2016-11-01 | 2016-09-03 | 2016-11-01
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4A | Safe Route to Schools - Phase 4A (MED-635) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-11-02 | 2016-12-01 | 2016-11-02 | 2020-12-01
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4B1 | Safe Routes to Schools - Phase 4B1 | 1 | DEVELOP SCOPE | 2015-02-16 | 2015-05-16 | 2013-09-19 | 2013-12-19
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4B1 | Safe Routes to Schools - Phase 4B1 | 2 | PRELIMINARY DESIGN | 2015-05-17 | 2015-09-13 | 2013-12-20 | 2014-07-16
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4B1 | Safe Routes to Schools - Phase 4B1 | 3 | FINAL DESIGN | 2015-09-14 | 2016-03-11 | 2014-07-17 | 2015-10-08
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4B1 | Safe Routes to Schools - Phase 4B1 | 4 | BID AWARD AND REGISTER CONTRCT | 2016-03-12 | 2016-06-09 | 2015-10-09 | 2016-10-16
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4B1 | Safe Routes to Schools - Phase 4B1 | 5 | CONSTRUCTION TO 25% | 2016-06-10 | 2016-10-07 | 2016-10-17 | 2017-02-13
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4B1 | Safe Routes to Schools - Phase 4B1 | 6 | CONSTRUCTION TO 50% | 2016-10-08 | 2017-02-04 | 2017-02-14 | 2017-06-13
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4B1 | Safe Routes to Schools - Phase 4B1 | 7 | CONSTRUCTION TO 75% | 2017-02-05 | 2017-06-04 | 2017-06-14 | 2017-10-11
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4B1 | Safe Routes to Schools - Phase 4B1 | 8 | ORIGINAL EQUIP & FURNISHING | 2017-06-05 | 2017-09-02 | 2017-10-12 | 2018-04-21
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4B1 | Safe Routes to Schools - Phase 4B1 | 9 | SUBSTANTIAL COMPLETION | 2017-09-03 | 2017-11-01 | 2018-04-22 | 2018-06-20
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4B1 | Safe Routes to Schools - Phase 4B1 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-11-02 | 2017-12-01 | 2018-06-21 | 2021-06-30
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4C2 | Safe Routes to Schools - Phase 4C2 | 1 | DEVELOP SCOPE | 2017-06-30 | 2017-09-27 | 2017-06-30 | 2017-09-27
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4C2 | Safe Routes to Schools - Phase 4C2 | 2 | PRELIMINARY DESIGN | 2017-09-28 | 2018-01-25 | 2017-09-28 | 2018-01-25
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4C2 | Safe Routes to Schools - Phase 4C2 | 3 | FINAL DESIGN | 2018-01-26 | 2018-07-24 | 2018-01-26 | 2018-07-24
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4C2 | Safe Routes to Schools - Phase 4C2 | 4 | BID AWARD AND REGISTER CONTRCT | 2018-07-25 | 2018-10-22 | 2018-07-25 | 2018-10-22
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4C2 | Safe Routes to Schools - Phase 4C2 | 5 | CONSTRUCTION TO 25% | 2018-10-23 | 2019-02-19 | 2018-10-23 | 2019-02-19
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4C2 | Safe Routes to Schools - Phase 4C2 | 6 | CONSTRUCTION TO 50% | 2019-02-20 | 2019-06-19 | 2019-02-20 | 2019-06-19
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4C2 | Safe Routes to Schools - Phase 4C2 | 7 | CONSTRUCTION TO 75% | 2019-06-20 | 2019-10-17 | 2019-06-20 | 2019-10-17
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4C2 | Safe Routes to Schools - Phase 4C2 | 8 | ORIGINAL EQUIP & FURNISHING | 2019-10-18 | 2020-01-15 | 2019-10-18 | 2020-01-15
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4C2 | Safe Routes to Schools - Phase 4C2 | 9 | SUBSTANTIAL COMPLETION | 2020-01-16 | 2020-03-15 | 2020-01-16 | 2020-03-15
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4C2 | Safe Routes to Schools - Phase 4C2 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-03-16 | 2020-04-14 | 2020-03-16 | 2022-06-30
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4D | Safe Routes to Schools - Phase 4D | 1 | DEVELOP SCOPE | 2017-06-30 | 2017-09-27 | 2018-06-30 | 2018-09-27
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4D | Safe Routes to Schools - Phase 4D | 2 | PRELIMINARY DESIGN | 2017-09-28 | 2018-01-25 | 2018-09-28 | 2019-01-25
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4D | Safe Routes to Schools - Phase 4D | 3 | FINAL DESIGN | 2018-01-26 | 2018-07-24 | 2019-01-26 | 2019-07-24
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4D | Safe Routes to Schools - Phase 4D | 4 | BID AWARD AND REGISTER CONTRCT | 2018-07-25 | 2018-10-22 | 2019-07-25 | 2019-10-22
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4D | Safe Routes to Schools - Phase 4D | 5 | CONSTRUCTION TO 25% | 2018-10-23 | 2019-02-19 | 2019-10-23 | 2020-02-19
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4D | Safe Routes to Schools - Phase 4D | 6 | CONSTRUCTION TO 50% | 2019-02-20 | 2019-06-19 | 2020-02-20 | 2020-06-18
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4D | Safe Routes to Schools - Phase 4D | 7 | CONSTRUCTION TO 75% | 2019-06-20 | 2019-10-17 | 2020-06-19 | 2020-10-16
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4D | Safe Routes to Schools - Phase 4D | 8 | ORIGINAL EQUIP & FURNISHING | 2019-10-18 | 2020-01-15 | 2020-10-17 | 2021-01-14
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4D | Safe Routes to Schools - Phase 4D | 9 | SUBSTANTIAL COMPLETION | 2020-01-16 | 2020-03-15 | 2021-01-15 | 2021-03-15
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4D | Safe Routes to Schools - Phase 4D | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-03-16 | 2020-04-14 | 2021-03-16 | 2021-04-14
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPKR | Safe Routes to Schools - Brooklyn & Staten Island | 1 | DEVELOP SCOPE | 2017-03-01 | 2017-05-29 | 2017-03-01 | 2017-05-29
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPKR | Safe Routes to Schools - Brooklyn & Staten Island | 2 | PRELIMINARY DESIGN | 2017-05-30 | 2017-09-26 | 2017-05-30 | 2017-09-26
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPKR | Safe Routes to Schools - Brooklyn & Staten Island | 3 | FINAL DESIGN | 2017-09-27 | 2018-03-25 | 2017-09-27 | 2018-03-25
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPKR | Safe Routes to Schools - Brooklyn & Staten Island | 4 | BID AWARD AND REGISTER CONTRCT | 2018-03-26 | 2018-06-23 | 2018-03-26 | 2018-06-23
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPKR | Safe Routes to Schools - Brooklyn & Staten Island | 5 | CONSTRUCTION TO 25% | 2018-06-24 | 2018-10-21 | 2018-06-24 | 2018-10-21
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPKR | Safe Routes to Schools - Brooklyn & Staten Island | 6 | CONSTRUCTION TO 50% | 2018-10-22 | 2019-02-18 | 2018-10-22 | 2019-02-18
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPKR | Safe Routes to Schools - Brooklyn & Staten Island | 7 | CONSTRUCTION TO 75% | 2019-02-19 | 2019-06-18 | 2019-02-19 | 2019-06-18
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPKR | Safe Routes to Schools - Brooklyn & Staten Island | 8 | ORIGINAL EQUIP & FURNISHING | 2019-06-19 | 2019-09-16 | 2019-06-19 | 2019-09-16
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPKR | Safe Routes to Schools - Brooklyn & Staten Island | 9 | SUBSTANTIAL COMPLETION | 2019-09-17 | 2019-11-15 | 2019-09-17 | 2019-11-15
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPKR | Safe Routes to Schools - Brooklyn & Staten Island | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-11-16 | 2023-06-30 | 2019-11-16 | 2023-06-30
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPMN | SAFE ROUTES TO SCHOOLS- MANHATTAN | 1 | DEVELOP SCOPE | 2019-03-01 | 2019-05-29 | 2019-03-01 | 2019-05-29
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPMN | SAFE ROUTES TO SCHOOLS- MANHATTAN | 2 | PRELIMINARY DESIGN | 2019-05-30 | 2019-09-26 | 2019-05-30 | 2019-09-26
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPMN | SAFE ROUTES TO SCHOOLS- MANHATTAN | 3 | FINAL DESIGN | 2019-09-27 | 2020-03-24 | 2019-09-27 | 2020-03-24
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPMN | SAFE ROUTES TO SCHOOLS- MANHATTAN | 4 | BID AWARD AND REGISTER CONTRCT | 2020-03-25 | 2020-06-22 | 2020-03-25 | 2020-06-22
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPMN | SAFE ROUTES TO SCHOOLS- MANHATTAN | 5 | CONSTRUCTION TO 25% | 2020-06-23 | 2020-10-20 | 2020-06-23 | 2020-10-20
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPMN | SAFE ROUTES TO SCHOOLS- MANHATTAN | 6 | CONSTRUCTION TO 50% | 2020-10-21 | 2021-02-17 | 2020-10-21 | 2021-02-17
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPMN | SAFE ROUTES TO SCHOOLS- MANHATTAN | 7 | CONSTRUCTION TO 75% | 2021-02-18 | 2021-06-17 | 2021-02-18 | 2021-06-17
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPMN | SAFE ROUTES TO SCHOOLS- MANHATTAN | 8 | ORIGINAL EQUIP & FURNISHING | 2021-06-18 | 2021-09-15 | 2021-06-18 | 2021-09-15
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPMN | SAFE ROUTES TO SCHOOLS- MANHATTAN | 9 | SUBSTANTIAL COMPLETION | 2021-09-16 | 2021-11-14 | 2021-09-16 | 2021-11-14
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPMN | SAFE ROUTES TO SCHOOLS- MANHATTAN | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-11-15 | 2021-12-14 | 2021-11-15 | 2021-12-14
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP15XMCL | Simple, Complex & Landmark Ped Ramps - Bronx and Manhattan | 1 | DEVELOP SCOPE | 2015-02-16 | 2015-05-16 | 2014-06-11 | 2014-09-25
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP15XMCL | Simple, Complex & Landmark Ped Ramps - Bronx and Manhattan | 2 | PRELIMINARY DESIGN | 2015-05-17 | 2015-09-13 | 2014-09-26 | 2015-04-21
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP15XMCL | Simple, Complex & Landmark Ped Ramps - Bronx and Manhattan | 3 | FINAL DESIGN | 2015-09-14 | 2016-03-11 | 2015-04-22 | 2015-12-31
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP15XMCL | Simple, Complex & Landmark Ped Ramps - Bronx and Manhattan | 4 | BID AWARD AND REGISTER CONTRCT | 2016-03-12 | 2016-06-09 | 2016-01-01 | 2017-03-19
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP15XMCL | Simple, Complex & Landmark Ped Ramps - Bronx and Manhattan | 5 | CONSTRUCTION TO 25% | 2016-06-10 | 2016-10-07 | 2017-03-20 | 2017-07-17
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP15XMCL | Simple, Complex & Landmark Ped Ramps - Bronx and Manhattan | 6 | CONSTRUCTION TO 50% | 2016-10-08 | 2017-02-04 | 2017-07-18 | 2017-11-14
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP15XMCL | Simple, Complex & Landmark Ped Ramps - Bronx and Manhattan | 7 | CONSTRUCTION TO 75% | 2017-02-05 | 2017-06-04 | 2017-11-15 | 2018-03-14
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP15XMCL | Simple, Complex & Landmark Ped Ramps - Bronx and Manhattan | 8 | ORIGINAL EQUIP & FURNISHING | 2017-06-05 | 2017-09-02 | 2018-03-15 | 2018-06-12
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP15XMCL | Simple, Complex & Landmark Ped Ramps - Bronx and Manhattan | 9 | SUBSTANTIAL COMPLETION | 2017-09-03 | 2017-11-01 | 2018-06-13 | 2018-08-11
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP15XMCL | Simple, Complex & Landmark Ped Ramps - Bronx and Manhattan | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-11-02 | 2017-12-01 | 2018-08-12 | 2023-05-20
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19CWLM | CITYWIDE COMPLEX PED RAMPS (LANDMARK) - MANHATTAN AND BRONX | 1 | DEVELOP SCOPE | 2017-06-30 | 2017-09-27 | 2017-06-30 | 2017-09-27
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19CWLM | CITYWIDE COMPLEX PED RAMPS (LANDMARK) - MANHATTAN AND BRONX | 2 | PRELIMINARY DESIGN | 2017-09-28 | 2018-01-25 | 2017-09-28 | 2018-06-30
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19CWLM | CITYWIDE COMPLEX PED RAMPS (LANDMARK) - MANHATTAN AND BRONX | 3 | FINAL DESIGN | 2018-01-26 | 2018-07-24 | 2018-07-01 | 2019-06-30
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19CWLM | CITYWIDE COMPLEX PED RAMPS (LANDMARK) - MANHATTAN AND BRONX | 4 | BID AWARD AND REGISTER CONTRCT | 2018-07-25 | 2018-10-22 | 2019-07-01 | 2019-12-31
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19CWLM | CITYWIDE COMPLEX PED RAMPS (LANDMARK) - MANHATTAN AND BRONX | 5 | CONSTRUCTION TO 25% | 2018-10-23 | 2019-02-19 | 2020-01-01 | 2020-04-29
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19CWLM | CITYWIDE COMPLEX PED RAMPS (LANDMARK) - MANHATTAN AND BRONX | 6 | CONSTRUCTION TO 50% | 2019-02-20 | 2019-06-19 | 2020-04-30 | 2020-08-27
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19CWLM | CITYWIDE COMPLEX PED RAMPS (LANDMARK) - MANHATTAN AND BRONX | 7 | CONSTRUCTION TO 75% | 2019-06-20 | 2019-10-17 | 2020-08-28 | 2020-12-25
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19CWLM | CITYWIDE COMPLEX PED RAMPS (LANDMARK) - MANHATTAN AND BRONX | 8 | ORIGINAL EQUIP & FURNISHING | 2019-10-18 | 2020-01-15 | 2020-12-26 | 2021-03-25
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19CWLM | CITYWIDE COMPLEX PED RAMPS (LANDMARK) - MANHATTAN AND BRONX | 9 | SUBSTANTIAL COMPLETION | 2020-01-16 | 2020-03-15 | 2021-03-26 | 2021-05-24
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19CWLM | CITYWIDE COMPLEX PED RAMPS (LANDMARK) - MANHATTAN AND BRONX | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-03-16 | 2020-04-14 | 2021-05-25 | 2021-06-23
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19KQTA | CITYWIDE COMPLEX PED RAMPS (TA) - BROOKLYN AND QUEENS | 1 | DEVELOP SCOPE | 2017-06-30 | 2017-09-27 | 2017-06-30 | 2018-06-30
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19KQTA | CITYWIDE COMPLEX PED RAMPS (TA) - BROOKLYN AND QUEENS | 2 | PRELIMINARY DESIGN | 2017-09-28 | 2018-01-25 | 2018-07-01 | 2018-12-31
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19KQTA | CITYWIDE COMPLEX PED RAMPS (TA) - BROOKLYN AND QUEENS | 3 | FINAL DESIGN | 2018-01-26 | 2018-07-24 | 2019-01-01 | 2019-06-30
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19KQTA | CITYWIDE COMPLEX PED RAMPS (TA) - BROOKLYN AND QUEENS | 4 | BID AWARD AND REGISTER CONTRCT | 2018-07-25 | 2018-10-22 | 2019-07-01 | 2019-12-31
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19KQTA | CITYWIDE COMPLEX PED RAMPS (TA) - BROOKLYN AND QUEENS | 5 | CONSTRUCTION TO 25% | 2018-10-23 | 2019-02-19 | 2020-01-01 | 2020-04-29
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19KQTA | CITYWIDE COMPLEX PED RAMPS (TA) - BROOKLYN AND QUEENS | 6 | CONSTRUCTION TO 50% | 2019-02-20 | 2019-06-19 | 2020-04-30 | 2020-08-27
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19KQTA | CITYWIDE COMPLEX PED RAMPS (TA) - BROOKLYN AND QUEENS | 7 | CONSTRUCTION TO 75% | 2019-06-20 | 2019-10-17 | 2020-08-28 | 2020-12-25
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19KQTA | CITYWIDE COMPLEX PED RAMPS (TA) - BROOKLYN AND QUEENS | 8 | ORIGINAL EQUIP & FURNISHING | 2019-10-18 | 2020-01-15 | 2020-12-26 | 2021-03-25
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19KQTA | CITYWIDE COMPLEX PED RAMPS (TA) - BROOKLYN AND QUEENS | 9 | SUBSTANTIAL COMPLETION | 2020-01-16 | 2020-03-15 | 2021-03-26 | 2021-05-24
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19KQTA | CITYWIDE COMPLEX PED RAMPS (TA) - BROOKLYN AND QUEENS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-03-16 | 2020-04-14 | 2021-05-25 | 2022-06-30
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19QRC | Citywide Complex Pedestrian Ramps - Queens and Staten Island | 1 | DEVELOP SCOPE | 2017-06-30 | 2017-09-27 | 2017-06-30 | 2018-06-30
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19QRC | Citywide Complex Pedestrian Ramps - Queens and Staten Island | 2 | PRELIMINARY DESIGN | 2017-09-28 | 2018-01-25 | 2018-07-01 | 2018-12-31
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19QRC | Citywide Complex Pedestrian Ramps - Queens and Staten Island | 3 | FINAL DESIGN | 2018-01-26 | 2018-07-24 | 2019-01-01 | 2019-06-30
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19QRC | Citywide Complex Pedestrian Ramps - Queens and Staten Island | 4 | BID AWARD AND REGISTER CONTRCT | 2018-07-25 | 2018-10-22 | 2019-07-01 | 2019-12-31
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19QRC | Citywide Complex Pedestrian Ramps - Queens and Staten Island | 5 | CONSTRUCTION TO 25% | 2018-10-23 | 2019-02-19 | 2020-01-01 | 2020-04-29
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19QRC | Citywide Complex Pedestrian Ramps - Queens and Staten Island | 6 | CONSTRUCTION TO 50% | 2019-02-20 | 2019-06-19 | 2020-04-30 | 2020-08-27
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19QRC | Citywide Complex Pedestrian Ramps - Queens and Staten Island | 7 | CONSTRUCTION TO 75% | 2019-06-20 | 2019-10-17 | 2020-08-28 | 2020-12-25
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19QRC | Citywide Complex Pedestrian Ramps - Queens and Staten Island | 8 | ORIGINAL EQUIP & FURNISHING | 2019-10-18 | 2020-01-15 | 2020-12-26 | 2021-03-25
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19QRC | Citywide Complex Pedestrian Ramps - Queens and Staten Island | 9 | SUBSTANTIAL COMPLETION | 2020-01-16 | 2020-03-15 | 2021-03-26 | 2021-05-24
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19QRC | Citywide Complex Pedestrian Ramps - Queens and Staten Island | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-03-16 | 2020-04-14 | 2021-05-25 | 2021-06-23
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2002Q | CITYWIDE PED RAMPS - QUEENS | 1 | DEVELOP SCOPE | 2000-05-21 | 2000-08-18 | 2000-05-21 | 2000-08-18
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2002Q | CITYWIDE PED RAMPS - QUEENS | 2 | PRELIMINARY DESIGN | 2000-08-19 | 2000-12-16 | 2000-08-19 | 2000-12-16
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2002Q | CITYWIDE PED RAMPS - QUEENS | 3 | FINAL DESIGN | 2000-12-17 | 2001-06-14 | 2000-12-17 | 2001-06-14
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2002Q | CITYWIDE PED RAMPS - QUEENS | 4 | BID AWARD AND REGISTER CONTRCT | 2001-06-15 | 2001-09-12 | 2001-06-15 | 2001-09-12
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2002Q | CITYWIDE PED RAMPS - QUEENS | 5 | CONSTRUCTION TO 25% | 2001-09-13 | 2002-01-10 | 2001-09-13 | 2002-01-10
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2002Q | CITYWIDE PED RAMPS - QUEENS | 6 | CONSTRUCTION TO 50% | 2002-01-11 | 2002-05-10 | 2002-01-11 | 2002-05-10
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2002Q | CITYWIDE PED RAMPS - QUEENS | 7 | CONSTRUCTION TO 75% | 2002-05-11 | 2002-09-07 | 2002-05-11 | 2002-09-07
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2002Q | CITYWIDE PED RAMPS - QUEENS | 8 | ORIGINAL EQUIP & FURNISHING | 2002-09-08 | 2002-12-06 | 2002-09-08 | 2002-12-06
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2002Q | CITYWIDE PED RAMPS - QUEENS | 9 | SUBSTANTIAL COMPLETION | 2002-12-07 | 2003-02-04 | 2002-12-07 | 2003-02-04
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2002Q | CITYWIDE PED RAMPS - QUEENS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2003-02-05 | 2003-03-06 | 2003-02-05 | 2003-03-06
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2013MX | CITYWIDE PED RAMPS - MANHATTAN AND BRONX | 1 | DEVELOP SCOPE | 2012-02-16 | 2012-05-15 | 2012-02-16 | 2012-05-15
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2013MX | CITYWIDE PED RAMPS - MANHATTAN AND BRONX | 2 | PRELIMINARY DESIGN | 2012-05-16 | 2012-09-12 | 2012-05-16 | 2012-09-12
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2013MX | CITYWIDE PED RAMPS - MANHATTAN AND BRONX | 3 | FINAL DESIGN | 2012-09-13 | 2013-03-11 | 2012-09-13 | 2013-03-11
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2013MX | CITYWIDE PED RAMPS - MANHATTAN AND BRONX | 4 | BID AWARD AND REGISTER CONTRCT | 2013-03-12 | 2013-06-09 | 2013-03-12 | 2013-06-09
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2013MX | CITYWIDE PED RAMPS - MANHATTAN AND BRONX | 5 | CONSTRUCTION TO 25% | 2013-06-10 | 2014-02-04 | 2013-06-10 | 2014-02-04
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2013MX | CITYWIDE PED RAMPS - MANHATTAN AND BRONX | 6 | CONSTRUCTION TO 50% | 2014-02-05 | 2015-05-30 | 2014-02-05 | 2015-05-30
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2013MX | CITYWIDE PED RAMPS - MANHATTAN AND BRONX | 7 | CONSTRUCTION TO 75% | 2015-05-31 | 2016-09-21 | 2015-05-31 | 2016-09-21
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2013MX | CITYWIDE PED RAMPS - MANHATTAN AND BRONX | 8 | ORIGINAL EQUIP & FURNISHING | 2016-09-22 | 2016-09-21 | 2016-09-22 | 2016-09-21
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2013MX | CITYWIDE PED RAMPS - MANHATTAN AND BRONX | 9 | SUBSTANTIAL COMPLETION | 2016-09-22 | 2016-09-21 | 2016-09-22 | 2016-09-21
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2013MX | CITYWIDE PED RAMPS - MANHATTAN AND BRONX | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-09-22 | 2016-10-21 | 2016-09-22 | 2023-06-30
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2019S | Citywide Simple Pedestrian Ramps | 1 | DEVELOP SCOPE | 2017-06-30 | 2018-07-15 | 2017-06-30 | 2018-07-15
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2019S | Citywide Simple Pedestrian Ramps | 2 | PRELIMINARY DESIGN | 2018-07-16 | 2018-11-12 | 2018-07-16 | 2018-11-12
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2019S | Citywide Simple Pedestrian Ramps | 3 | FINAL DESIGN | 2018-11-13 | 2019-05-11 | 2018-11-13 | 2019-05-11
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2019S | Citywide Simple Pedestrian Ramps | 4 | BID AWARD AND REGISTER CONTRCT | 2019-05-12 | 2019-08-09 | 2019-05-12 | 2019-08-09
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2019S | Citywide Simple Pedestrian Ramps | 5 | CONSTRUCTION TO 25% | 2019-08-10 | 2019-12-07 | 2019-08-10 | 2019-12-07
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2019S | Citywide Simple Pedestrian Ramps | 6 | CONSTRUCTION TO 50% | 2019-12-08 | 2020-04-05 | 2019-12-08 | 2020-04-05
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2019S | Citywide Simple Pedestrian Ramps | 7 | CONSTRUCTION TO 75% | 2020-04-06 | 2020-08-03 | 2020-04-06 | 2020-08-03
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2019S | Citywide Simple Pedestrian Ramps | 8 | ORIGINAL EQUIP & FURNISHING | 2020-08-04 | 2020-11-01 | 2020-08-04 | 2020-11-01
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2019S | Citywide Simple Pedestrian Ramps | 9 | SUBSTANTIAL COMPLETION | 2020-11-02 | 2020-12-31 | 2020-11-02 | 2020-12-31
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2019S | Citywide Simple Pedestrian Ramps | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-01-01 | 2021-01-30 | 2021-01-01 | 2021-01-30
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2020LM | Non-Standard Ped Ramp Installs - Citywide Landmark Locations | 1 | DEVELOP SCOPE | 2019-06-30 | 2019-09-27 | 2019-06-30 | 2019-09-27
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2020LM | Non-Standard Ped Ramp Installs - Citywide Landmark Locations | 2 | PRELIMINARY DESIGN | 2019-09-28 | 2020-01-25 | 2019-09-28 | 2020-01-25
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2020LM | Non-Standard Ped Ramp Installs - Citywide Landmark Locations | 3 | FINAL DESIGN | 2020-01-26 | 2020-07-23 | 2020-01-26 | 2020-07-23
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2020LM | Non-Standard Ped Ramp Installs - Citywide Landmark Locations | 4 | BID AWARD AND REGISTER CONTRCT | 2020-07-24 | 2020-10-21 | 2020-07-24 | 2020-10-21
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2020LM | Non-Standard Ped Ramp Installs - Citywide Landmark Locations | 5 | CONSTRUCTION TO 25% | 2020-10-22 | 2021-02-18 | 2020-10-22 | 2021-02-18
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2020LM | Non-Standard Ped Ramp Installs - Citywide Landmark Locations | 6 | CONSTRUCTION TO 50% | 2021-02-19 | 2021-06-18 | 2021-02-19 | 2021-06-18
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2020LM | Non-Standard Ped Ramp Installs - Citywide Landmark Locations | 7 | CONSTRUCTION TO 75% | 2021-06-19 | 2021-10-16 | 2021-06-19 | 2021-10-16
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2020LM | Non-Standard Ped Ramp Installs - Citywide Landmark Locations | 8 | ORIGINAL EQUIP & FURNISHING | 2021-10-17 | 2022-01-14 | 2021-10-17 | 2022-01-14
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2020LM | Non-Standard Ped Ramp Installs - Citywide Landmark Locations | 9 | SUBSTANTIAL COMPLETION | 2022-01-15 | 2022-03-15 | 2022-01-15 | 2022-03-15
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2020LM | Non-Standard Ped Ramp Installs - Citywide Landmark Locations | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-16 | 2022-04-14 | 2022-03-16 | 2023-06-30
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2020TA | Non-Standard Ped Ramp Installs - Manh, Brnx, Bk, & Queens | 1 | DEVELOP SCOPE | 2019-06-30 | 2019-09-27 | 2019-06-30 | 2019-09-27
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2020TA | Non-Standard Ped Ramp Installs - Manh, Brnx, Bk, & Queens | 2 | PRELIMINARY DESIGN | 2019-09-28 | 2020-01-25 | 2019-09-28 | 2020-01-25
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2020TA | Non-Standard Ped Ramp Installs - Manh, Brnx, Bk, & Queens | 3 | FINAL DESIGN | 2020-01-26 | 2020-07-23 | 2020-01-26 | 2020-07-23
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2020TA | Non-Standard Ped Ramp Installs - Manh, Brnx, Bk, & Queens | 4 | BID AWARD AND REGISTER CONTRCT | 2020-07-24 | 2020-10-21 | 2020-07-24 | 2020-10-21
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2020TA | Non-Standard Ped Ramp Installs - Manh, Brnx, Bk, & Queens | 5 | CONSTRUCTION TO 25% | 2020-10-22 | 2021-02-18 | 2020-10-22 | 2021-02-18
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2020TA | Non-Standard Ped Ramp Installs - Manh, Brnx, Bk, & Queens | 6 | CONSTRUCTION TO 50% | 2021-02-19 | 2021-06-18 | 2021-02-19 | 2021-06-18
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2020TA | Non-Standard Ped Ramp Installs - Manh, Brnx, Bk, & Queens | 7 | CONSTRUCTION TO 75% | 2021-06-19 | 2021-10-16 | 2021-06-19 | 2021-10-16
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2020TA | Non-Standard Ped Ramp Installs - Manh, Brnx, Bk, & Queens | 8 | ORIGINAL EQUIP & FURNISHING | 2021-10-17 | 2022-01-14 | 2021-10-17 | 2022-01-14
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2020TA | Non-Standard Ped Ramp Installs - Manh, Brnx, Bk, & Queens | 9 | SUBSTANTIAL COMPLETION | 2022-01-15 | 2022-03-15 | 2022-01-15 | 2022-03-15
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2020TA | Non-Standard Ped Ramp Installs - Manh, Brnx, Bk, & Queens | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-16 | 2022-04-14 | 2022-03-16 | 2023-06-30
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP20KRC | Non-Standard Ped Ramp Installs - Brooklyn & Staten Island | 1 | DEVELOP SCOPE | 2019-06-30 | 2019-09-27 | 2019-06-30 | 2019-09-27
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP20KRC | Non-Standard Ped Ramp Installs - Brooklyn & Staten Island | 2 | PRELIMINARY DESIGN | 2019-09-28 | 2020-01-25 | 2019-09-28 | 2020-01-25
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP20KRC | Non-Standard Ped Ramp Installs - Brooklyn & Staten Island | 3 | FINAL DESIGN | 2020-01-26 | 2020-07-23 | 2020-01-26 | 2020-07-23
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP20KRC | Non-Standard Ped Ramp Installs - Brooklyn & Staten Island | 4 | BID AWARD AND REGISTER CONTRCT | 2020-07-24 | 2020-10-21 | 2020-07-24 | 2020-10-21
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP20KRC | Non-Standard Ped Ramp Installs - Brooklyn & Staten Island | 5 | CONSTRUCTION TO 25% | 2020-10-22 | 2021-02-18 | 2020-10-22 | 2021-02-18
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP20KRC | Non-Standard Ped Ramp Installs - Brooklyn & Staten Island | 6 | CONSTRUCTION TO 50% | 2021-02-19 | 2021-06-18 | 2021-02-19 | 2021-06-18
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP20KRC | Non-Standard Ped Ramp Installs - Brooklyn & Staten Island | 7 | CONSTRUCTION TO 75% | 2021-06-19 | 2021-10-16 | 2021-06-19 | 2021-10-16
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP20KRC | Non-Standard Ped Ramp Installs - Brooklyn & Staten Island | 8 | ORIGINAL EQUIP & FURNISHING | 2021-10-17 | 2022-01-14 | 2021-10-17 | 2022-01-14
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP20KRC | Non-Standard Ped Ramp Installs - Brooklyn & Staten Island | 9 | SUBSTANTIAL COMPLETION | 2022-01-15 | 2022-03-15 | 2022-01-15 | 2022-03-15
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP20KRC | Non-Standard Ped Ramp Installs - Brooklyn & Staten Island | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-16 | 2022-04-14 | 2022-03-16 | 2023-06-30
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP20MKC | Non-Standard Ped Ramp Installs - Manhattan & Brooklyn | 1 | DEVELOP SCOPE | 2019-06-30 | 2019-09-27 | 2019-06-30 | 2019-09-27
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP20MKC | Non-Standard Ped Ramp Installs - Manhattan & Brooklyn | 2 | PRELIMINARY DESIGN | 2019-09-28 | 2020-01-25 | 2019-09-28 | 2020-01-25
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP20MKC | Non-Standard Ped Ramp Installs - Manhattan & Brooklyn | 3 | FINAL DESIGN | 2020-01-26 | 2020-07-23 | 2020-01-26 | 2020-07-23
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP20MKC | Non-Standard Ped Ramp Installs - Manhattan & Brooklyn | 4 | BID AWARD AND REGISTER CONTRCT | 2020-07-24 | 2020-10-21 | 2020-07-24 | 2020-10-21
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP20MKC | Non-Standard Ped Ramp Installs - Manhattan & Brooklyn | 5 | CONSTRUCTION TO 25% | 2020-10-22 | 2021-02-18 | 2020-10-22 | 2021-02-18
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP20MKC | Non-Standard Ped Ramp Installs - Manhattan & Brooklyn | 6 | CONSTRUCTION TO 50% | 2021-02-19 | 2021-06-18 | 2021-02-19 | 2021-06-18
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP20MKC | Non-Standard Ped Ramp Installs - Manhattan & Brooklyn | 7 | CONSTRUCTION TO 75% | 2021-06-19 | 2021-10-16 | 2021-06-19 | 2021-10-16
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP20MKC | Non-Standard Ped Ramp Installs - Manhattan & Brooklyn | 8 | ORIGINAL EQUIP & FURNISHING | 2021-10-17 | 2022-01-14 | 2021-10-17 | 2022-01-14
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP20MKC | Non-Standard Ped Ramp Installs - Manhattan & Brooklyn | 9 | SUBSTANTIAL COMPLETION | 2022-01-15 | 2022-03-15 | 2022-01-15 | 2022-03-15
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP20MKC | Non-Standard Ped Ramp Installs - Manhattan & Brooklyn | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-16 | 2022-04-14 | 2022-03-16 | 2022-04-14
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP20MXQC | Non-Standard Ped Ramp Installs - Manhattan, Queens, & Bronx | 1 | DEVELOP SCOPE | 2019-06-30 | 2019-09-27 | 2019-06-30 | 2019-09-27
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP20MXQC | Non-Standard Ped Ramp Installs - Manhattan, Queens, & Bronx | 2 | PRELIMINARY DESIGN | 2019-09-28 | 2020-01-25 | 2019-09-28 | 2020-01-25
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP20MXQC | Non-Standard Ped Ramp Installs - Manhattan, Queens, & Bronx | 3 | FINAL DESIGN | 2020-01-26 | 2020-07-23 | 2020-01-26 | 2020-07-23
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP20MXQC | Non-Standard Ped Ramp Installs - Manhattan, Queens, & Bronx | 4 | BID AWARD AND REGISTER CONTRCT | 2020-07-24 | 2020-10-21 | 2020-07-24 | 2020-10-21
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP20MXQC | Non-Standard Ped Ramp Installs - Manhattan, Queens, & Bronx | 5 | CONSTRUCTION TO 25% | 2020-10-22 | 2021-02-18 | 2020-10-22 | 2021-02-18
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP20MXQC | Non-Standard Ped Ramp Installs - Manhattan, Queens, & Bronx | 6 | CONSTRUCTION TO 50% | 2021-02-19 | 2021-06-18 | 2021-02-19 | 2021-06-18
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP20MXQC | Non-Standard Ped Ramp Installs - Manhattan, Queens, & Bronx | 7 | CONSTRUCTION TO 75% | 2021-06-19 | 2021-10-16 | 2021-06-19 | 2021-10-16
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP20MXQC | Non-Standard Ped Ramp Installs - Manhattan, Queens, & Bronx | 8 | ORIGINAL EQUIP & FURNISHING | 2021-10-17 | 2022-01-14 | 2021-10-17 | 2022-01-14
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP20MXQC | Non-Standard Ped Ramp Installs - Manhattan, Queens, & Bronx | 9 | SUBSTANTIAL COMPLETION | 2022-01-15 | 2022-03-15 | 2022-01-15 | 2022-03-15
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP20MXQC | Non-Standard Ped Ramp Installs - Manhattan, Queens, & Bronx | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-16 | 2022-04-14 | 2022-03-16 | 2022-04-14
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF1 | Multi-Site Pedestrian Safety | 1 | DEVELOP SCOPE | 2011-06-30 | 2011-09-27 | 2011-06-03 | 2012-10-16
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF1 | Multi-Site Pedestrian Safety | 2 | PRELIMINARY DESIGN | 2011-09-28 | 2012-01-25 | 2012-10-17 | 2014-01-24
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF1 | Multi-Site Pedestrian Safety | 3 | FINAL DESIGN | 2012-01-26 | 2012-07-23 | 2014-01-25 | 2014-11-18
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF1 | Multi-Site Pedestrian Safety | 4 | BID AWARD AND REGISTER CONTRCT | 2012-07-24 | 2012-10-21 | 2014-11-19 | 2016-05-30
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF1 | Multi-Site Pedestrian Safety | 5 | CONSTRUCTION TO 25% | 2012-10-22 | 2013-02-18 | 2016-05-31 | 2016-10-27
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF1 | Multi-Site Pedestrian Safety | 6 | CONSTRUCTION TO 50% | 2013-02-19 | 2013-06-18 | 2016-10-28 | 2017-03-26
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF1 | Multi-Site Pedestrian Safety | 7 | CONSTRUCTION TO 75% | 2013-06-19 | 2013-10-16 | 2017-03-27 | 2017-08-23
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF1 | Multi-Site Pedestrian Safety | 8 | ORIGINAL EQUIP & FURNISHING | 2013-10-17 | 2014-01-14 | 2017-08-24 | 2019-08-31
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF1 | Multi-Site Pedestrian Safety | 9 | SUBSTANTIAL COMPLETION | 2014-01-15 | 2014-03-15 | 2019-09-01 | 2019-11-19
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF1 | Multi-Site Pedestrian Safety | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-03-16 | 2014-04-14 | 2019-11-20 | 2024-06-30
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF3A | MULTI-SITE PEDESTRIAN SAFETY - 7 LOCATIONS | 1 | DEVELOP SCOPE | 2015-02-16 | 2015-05-16 | 2015-02-16 | 2015-05-16
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF3A | MULTI-SITE PEDESTRIAN SAFETY - 7 LOCATIONS | 2 | PRELIMINARY DESIGN | 2015-05-17 | 2015-09-13 | 2015-05-17 | 2015-09-13
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF3A | MULTI-SITE PEDESTRIAN SAFETY - 7 LOCATIONS | 3 | FINAL DESIGN | 2015-09-14 | 2016-03-11 | 2015-09-14 | 2016-03-11
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF3A | MULTI-SITE PEDESTRIAN SAFETY - 7 LOCATIONS | 4 | BID AWARD AND REGISTER CONTRCT | 2016-03-12 | 2016-06-09 | 2016-03-12 | 2016-06-09
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF3A | MULTI-SITE PEDESTRIAN SAFETY - 7 LOCATIONS | 5 | CONSTRUCTION TO 25% | 2016-06-10 | 2016-10-07 | 2016-06-10 | 2016-10-07
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF3A | MULTI-SITE PEDESTRIAN SAFETY - 7 LOCATIONS | 6 | CONSTRUCTION TO 50% | 2016-10-08 | 2017-02-04 | 2016-10-08 | 2017-02-04
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF3A | MULTI-SITE PEDESTRIAN SAFETY - 7 LOCATIONS | 7 | CONSTRUCTION TO 75% | 2017-02-05 | 2017-06-04 | 2017-02-05 | 2017-06-04
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF3A | MULTI-SITE PEDESTRIAN SAFETY - 7 LOCATIONS | 8 | ORIGINAL EQUIP & FURNISHING | 2017-06-05 | 2017-09-02 | 2017-06-05 | 2017-09-02
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF3A | MULTI-SITE PEDESTRIAN SAFETY - 7 LOCATIONS | 9 | SUBSTANTIAL COMPLETION | 2017-09-03 | 2017-11-01 | 2017-09-03 | 2017-11-01
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF3A | MULTI-SITE PEDESTRIAN SAFETY - 7 LOCATIONS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-11-02 | 2017-12-01 | 2017-11-02 | 2022-06-13
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19MXC | Complex Upgrades Ped Ramps - Manhattan and the Bronx | 1 | DEVELOP SCOPE | 2019-06-30 | 2019-09-27 | 2019-06-30 | 2019-09-27
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19MXC | Complex Upgrades Ped Ramps - Manhattan and the Bronx | 2 | PRELIMINARY DESIGN | 2019-09-28 | 2020-01-25 | 2019-09-28 | 2020-01-25
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19MXC | Complex Upgrades Ped Ramps - Manhattan and the Bronx | 3 | FINAL DESIGN | 2020-01-26 | 2020-07-23 | 2020-01-26 | 2020-07-23
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19MXC | Complex Upgrades Ped Ramps - Manhattan and the Bronx | 4 | BID AWARD AND REGISTER CONTRCT | 2020-07-24 | 2020-10-21 | 2020-07-24 | 2020-10-21
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19MXC | Complex Upgrades Ped Ramps - Manhattan and the Bronx | 5 | CONSTRUCTION TO 25% | 2020-10-22 | 2021-02-18 | 2020-10-22 | 2021-02-18
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19MXC | Complex Upgrades Ped Ramps - Manhattan and the Bronx | 6 | CONSTRUCTION TO 50% | 2021-02-19 | 2021-06-18 | 2021-02-19 | 2021-06-18
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19MXC | Complex Upgrades Ped Ramps - Manhattan and the Bronx | 7 | CONSTRUCTION TO 75% | 2021-06-19 | 2021-10-16 | 2021-06-19 | 2021-10-16
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19MXC | Complex Upgrades Ped Ramps - Manhattan and the Bronx | 8 | ORIGINAL EQUIP & FURNISHING | 2021-10-17 | 2022-01-14 | 2021-10-17 | 2022-01-14
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19MXC | Complex Upgrades Ped Ramps - Manhattan and the Bronx | 9 | SUBSTANTIAL COMPLETION | 2022-01-15 | 2022-03-15 | 2022-01-15 | 2022-03-15
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19MXC | Complex Upgrades Ped Ramps - Manhattan and the Bronx | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-16 | 2022-04-14 | 2022-03-16 | 2022-04-14
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19QRC | Complex Upgrades Ped Ramps - Queens and Staten Island | 1 | DEVELOP SCOPE | 2019-06-30 | 2019-09-27 | 2019-06-30 | 2019-09-27
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19QRC | Complex Upgrades Ped Ramps - Queens and Staten Island | 2 | PRELIMINARY DESIGN | 2019-09-28 | 2020-01-25 | 2019-09-28 | 2020-01-25
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19QRC | Complex Upgrades Ped Ramps - Queens and Staten Island | 3 | FINAL DESIGN | 2020-01-26 | 2020-07-23 | 2020-01-26 | 2020-07-23
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19QRC | Complex Upgrades Ped Ramps - Queens and Staten Island | 4 | BID AWARD AND REGISTER CONTRCT | 2020-07-24 | 2020-10-21 | 2020-07-24 | 2020-10-21
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19QRC | Complex Upgrades Ped Ramps - Queens and Staten Island | 5 | CONSTRUCTION TO 25% | 2020-10-22 | 2021-02-18 | 2020-10-22 | 2021-02-18
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19QRC | Complex Upgrades Ped Ramps - Queens and Staten Island | 6 | CONSTRUCTION TO 50% | 2021-02-19 | 2021-06-18 | 2021-02-19 | 2021-06-18
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19QRC | Complex Upgrades Ped Ramps - Queens and Staten Island | 7 | CONSTRUCTION TO 75% | 2021-06-19 | 2021-10-16 | 2021-06-19 | 2021-10-16
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19QRC | Complex Upgrades Ped Ramps - Queens and Staten Island | 8 | ORIGINAL EQUIP & FURNISHING | 2021-10-17 | 2022-01-14 | 2021-10-17 | 2022-01-14
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19QRC | Complex Upgrades Ped Ramps - Queens and Staten Island | 9 | SUBSTANTIAL COMPLETION | 2022-01-15 | 2022-03-15 | 2022-01-15 | 2022-03-15
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19QRC | Complex Upgrades Ped Ramps - Queens and Staten Island | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-16 | 2022-04-14 | 2022-03-16 | 2022-04-14
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20KMC | Non-Standard Upgrades Ped Ramp - Manhattan & Brooklyn | 1 | DEVELOP SCOPE | 2019-06-30 | 2019-09-27 | 2019-06-30 | 2019-09-27
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20KMC | Non-Standard Upgrades Ped Ramp - Manhattan & Brooklyn | 2 | PRELIMINARY DESIGN | 2019-09-28 | 2020-01-25 | 2019-09-28 | 2020-01-25
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20KMC | Non-Standard Upgrades Ped Ramp - Manhattan & Brooklyn | 3 | FINAL DESIGN | 2020-01-26 | 2020-07-23 | 2020-01-26 | 2020-07-23
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20KMC | Non-Standard Upgrades Ped Ramp - Manhattan & Brooklyn | 4 | BID AWARD AND REGISTER CONTRCT | 2020-07-24 | 2020-10-21 | 2020-07-24 | 2020-10-21
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20KMC | Non-Standard Upgrades Ped Ramp - Manhattan & Brooklyn | 5 | CONSTRUCTION TO 25% | 2020-10-22 | 2021-02-18 | 2020-10-22 | 2021-02-18
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20KMC | Non-Standard Upgrades Ped Ramp - Manhattan & Brooklyn | 6 | CONSTRUCTION TO 50% | 2021-02-19 | 2021-06-18 | 2021-02-19 | 2021-06-18
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20KMC | Non-Standard Upgrades Ped Ramp - Manhattan & Brooklyn | 7 | CONSTRUCTION TO 75% | 2021-06-19 | 2021-10-16 | 2021-06-19 | 2021-10-16
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20KMC | Non-Standard Upgrades Ped Ramp - Manhattan & Brooklyn | 8 | ORIGINAL EQUIP & FURNISHING | 2021-10-17 | 2022-01-14 | 2021-10-17 | 2022-01-14
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20KMC | Non-Standard Upgrades Ped Ramp - Manhattan & Brooklyn | 9 | SUBSTANTIAL COMPLETION | 2022-01-15 | 2022-03-15 | 2022-01-15 | 2022-03-15
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20KMC | Non-Standard Upgrades Ped Ramp - Manhattan & Brooklyn | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-16 | 2022-04-14 | 2022-03-16 | 2022-04-14
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MKL | Non-Standard Upgrades Ped Ramp - Manhattan & Brooklyn | 1 | DEVELOP SCOPE | 2019-06-30 | 2019-09-27 | 2019-06-30 | 2019-09-27
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MKL | Non-Standard Upgrades Ped Ramp - Manhattan & Brooklyn | 2 | PRELIMINARY DESIGN | 2019-09-28 | 2020-01-25 | 2019-09-28 | 2020-01-25
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MKL | Non-Standard Upgrades Ped Ramp - Manhattan & Brooklyn | 3 | FINAL DESIGN | 2020-01-26 | 2020-07-23 | 2020-01-26 | 2020-07-23
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MKL | Non-Standard Upgrades Ped Ramp - Manhattan & Brooklyn | 4 | BID AWARD AND REGISTER CONTRCT | 2020-07-24 | 2020-10-21 | 2020-07-24 | 2020-10-21
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MKL | Non-Standard Upgrades Ped Ramp - Manhattan & Brooklyn | 5 | CONSTRUCTION TO 25% | 2020-10-22 | 2021-02-18 | 2020-10-22 | 2021-02-18
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MKL | Non-Standard Upgrades Ped Ramp - Manhattan & Brooklyn | 6 | CONSTRUCTION TO 50% | 2021-02-19 | 2021-06-18 | 2021-02-19 | 2021-06-18
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MKL | Non-Standard Upgrades Ped Ramp - Manhattan & Brooklyn | 7 | CONSTRUCTION TO 75% | 2021-06-19 | 2021-10-16 | 2021-06-19 | 2021-10-16
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MKL | Non-Standard Upgrades Ped Ramp - Manhattan & Brooklyn | 8 | ORIGINAL EQUIP & FURNISHING | 2021-10-17 | 2022-01-14 | 2021-10-17 | 2022-01-14
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MKL | Non-Standard Upgrades Ped Ramp - Manhattan & Brooklyn | 9 | SUBSTANTIAL COMPLETION | 2022-01-15 | 2022-03-15 | 2022-01-15 | 2022-03-15
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MKL | Non-Standard Upgrades Ped Ramp - Manhattan & Brooklyn | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-16 | 2022-04-14 | 2022-03-16 | 2022-04-14
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MKT | Non-Standard Upgrades Ped Ramp - TA Manhattan & Brooklyn | 1 | DEVELOP SCOPE | 2019-06-30 | 2019-09-27 | 2019-06-30 | 2019-09-27
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MKT | Non-Standard Upgrades Ped Ramp - TA Manhattan & Brooklyn | 2 | PRELIMINARY DESIGN | 2019-09-28 | 2020-01-25 | 2019-09-28 | 2020-01-25
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MKT | Non-Standard Upgrades Ped Ramp - TA Manhattan & Brooklyn | 3 | FINAL DESIGN | 2020-01-26 | 2020-07-23 | 2020-01-26 | 2020-07-23
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MKT | Non-Standard Upgrades Ped Ramp - TA Manhattan & Brooklyn | 4 | BID AWARD AND REGISTER CONTRCT | 2020-07-24 | 2020-10-21 | 2020-07-24 | 2020-10-21
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MKT | Non-Standard Upgrades Ped Ramp - TA Manhattan & Brooklyn | 5 | CONSTRUCTION TO 25% | 2020-10-22 | 2021-02-18 | 2020-10-22 | 2021-02-18
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MKT | Non-Standard Upgrades Ped Ramp - TA Manhattan & Brooklyn | 6 | CONSTRUCTION TO 50% | 2021-02-19 | 2021-06-18 | 2021-02-19 | 2021-06-18
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MKT | Non-Standard Upgrades Ped Ramp - TA Manhattan & Brooklyn | 7 | CONSTRUCTION TO 75% | 2021-06-19 | 2021-10-16 | 2021-06-19 | 2021-10-16
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MKT | Non-Standard Upgrades Ped Ramp - TA Manhattan & Brooklyn | 8 | ORIGINAL EQUIP & FURNISHING | 2021-10-17 | 2022-01-14 | 2021-10-17 | 2022-01-14
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MKT | Non-Standard Upgrades Ped Ramp - TA Manhattan & Brooklyn | 9 | SUBSTANTIAL COMPLETION | 2022-01-15 | 2022-03-15 | 2022-01-15 | 2022-03-15
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MKT | Non-Standard Upgrades Ped Ramp - TA Manhattan & Brooklyn | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-16 | 2022-04-14 | 2022-03-16 | 2023-06-30
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MQC | Non-Standard Upgrades Ped Ramp - Manhattan & Queens | 1 | DEVELOP SCOPE | 2019-06-30 | 2019-09-27 | 2019-06-30 | 2019-09-27
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MQC | Non-Standard Upgrades Ped Ramp - Manhattan & Queens | 2 | PRELIMINARY DESIGN | 2019-09-28 | 2020-01-25 | 2019-09-28 | 2020-01-25
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MQC | Non-Standard Upgrades Ped Ramp - Manhattan & Queens | 3 | FINAL DESIGN | 2020-01-26 | 2020-07-23 | 2020-01-26 | 2020-07-23
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MQC | Non-Standard Upgrades Ped Ramp - Manhattan & Queens | 4 | BID AWARD AND REGISTER CONTRCT | 2020-07-24 | 2020-10-21 | 2020-07-24 | 2020-10-21
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MQC | Non-Standard Upgrades Ped Ramp - Manhattan & Queens | 5 | CONSTRUCTION TO 25% | 2020-10-22 | 2021-02-18 | 2020-10-22 | 2021-02-18
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MQC | Non-Standard Upgrades Ped Ramp - Manhattan & Queens | 6 | CONSTRUCTION TO 50% | 2021-02-19 | 2021-06-18 | 2021-02-19 | 2021-06-18
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MQC | Non-Standard Upgrades Ped Ramp - Manhattan & Queens | 7 | CONSTRUCTION TO 75% | 2021-06-19 | 2021-10-16 | 2021-06-19 | 2021-10-16
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MQC | Non-Standard Upgrades Ped Ramp - Manhattan & Queens | 8 | ORIGINAL EQUIP & FURNISHING | 2021-10-17 | 2022-01-14 | 2021-10-17 | 2022-01-14
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MQC | Non-Standard Upgrades Ped Ramp - Manhattan & Queens | 9 | SUBSTANTIAL COMPLETION | 2022-01-15 | 2022-03-15 | 2022-01-15 | 2022-03-15
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MQC | Non-Standard Upgrades Ped Ramp - Manhattan & Queens | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-16 | 2022-04-14 | 2022-03-16 | 2022-04-14
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MQX | Non-Standard Upgrades Ped Ramp - TA Manhattan,Queens,&Bronx | 1 | DEVELOP SCOPE | 2019-06-30 | 2019-09-27 | 2019-06-30 | 2019-09-27
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MQX | Non-Standard Upgrades Ped Ramp - TA Manhattan,Queens,&Bronx | 2 | PRELIMINARY DESIGN | 2019-09-28 | 2020-01-25 | 2019-09-28 | 2020-01-25
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MQX | Non-Standard Upgrades Ped Ramp - TA Manhattan,Queens,&Bronx | 3 | FINAL DESIGN | 2020-01-26 | 2020-07-23 | 2020-01-26 | 2020-07-23
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MQX | Non-Standard Upgrades Ped Ramp - TA Manhattan,Queens,&Bronx | 4 | BID AWARD AND REGISTER CONTRCT | 2020-07-24 | 2020-10-21 | 2020-07-24 | 2020-10-21
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MQX | Non-Standard Upgrades Ped Ramp - TA Manhattan,Queens,&Bronx | 5 | CONSTRUCTION TO 25% | 2020-10-22 | 2021-02-18 | 2020-10-22 | 2021-02-18
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MQX | Non-Standard Upgrades Ped Ramp - TA Manhattan,Queens,&Bronx | 6 | CONSTRUCTION TO 50% | 2021-02-19 | 2021-06-18 | 2021-02-19 | 2021-06-18
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MQX | Non-Standard Upgrades Ped Ramp - TA Manhattan,Queens,&Bronx | 7 | CONSTRUCTION TO 75% | 2021-06-19 | 2021-10-16 | 2021-06-19 | 2021-10-16
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MQX | Non-Standard Upgrades Ped Ramp - TA Manhattan,Queens,&Bronx | 8 | ORIGINAL EQUIP & FURNISHING | 2021-10-17 | 2022-01-14 | 2021-10-17 | 2022-01-14
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MQX | Non-Standard Upgrades Ped Ramp - TA Manhattan,Queens,&Bronx | 9 | SUBSTANTIAL COMPLETION | 2022-01-15 | 2022-03-15 | 2022-01-15 | 2022-03-15
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MQX | Non-Standard Upgrades Ped Ramp - TA Manhattan,Queens,&Bronx | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-16 | 2022-04-14 | 2022-03-16 | 2022-04-14
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MX | Pedestrian Ramp Rehabilitation - Manhattan and Bronx | 1 | DEVELOP SCOPE | 2019-05-24 | 2019-08-21 | 2019-05-24 | 2019-08-21
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MX | Pedestrian Ramp Rehabilitation - Manhattan and Bronx | 2 | PRELIMINARY DESIGN | 2019-08-22 | 2019-12-19 | 2019-08-22 | 2019-12-19
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MX | Pedestrian Ramp Rehabilitation - Manhattan and Bronx | 3 | FINAL DESIGN | 2019-12-20 | 2020-06-16 | 2019-12-20 | 2020-06-16
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MX | Pedestrian Ramp Rehabilitation - Manhattan and Bronx | 4 | BID AWARD AND REGISTER CONTRCT | 2020-06-17 | 2020-09-14 | 2020-06-17 | 2020-09-14
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MX | Pedestrian Ramp Rehabilitation - Manhattan and Bronx | 5 | CONSTRUCTION TO 25% | 2020-09-15 | 2021-01-12 | 2020-09-15 | 2021-01-12
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MX | Pedestrian Ramp Rehabilitation - Manhattan and Bronx | 6 | CONSTRUCTION TO 50% | 2021-01-13 | 2021-05-12 | 2021-01-13 | 2021-05-12
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MX | Pedestrian Ramp Rehabilitation - Manhattan and Bronx | 7 | CONSTRUCTION TO 75% | 2021-05-13 | 2021-09-09 | 2021-05-13 | 2021-09-09
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MX | Pedestrian Ramp Rehabilitation - Manhattan and Bronx | 8 | ORIGINAL EQUIP & FURNISHING | 2021-09-10 | 2021-12-08 | 2021-09-10 | 2021-12-08
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MX | Pedestrian Ramp Rehabilitation - Manhattan and Bronx | 9 | SUBSTANTIAL COMPLETION | 2021-12-09 | 2022-02-06 | 2021-12-09 | 2022-02-06
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MX | Pedestrian Ramp Rehabilitation - Manhattan and Bronx | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-02-07 | 2025-07-25 | 2022-02-07 | 2025-07-25
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MXC | Non-Standard Upgrades Ped Ramp - Manhattan & Bronx | 1 | DEVELOP SCOPE | 2019-06-30 | 2019-09-27 | 2019-06-30 | 2019-09-27
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MXC | Non-Standard Upgrades Ped Ramp - Manhattan & Bronx | 2 | PRELIMINARY DESIGN | 2019-09-28 | 2020-01-25 | 2019-09-28 | 2020-01-25
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MXC | Non-Standard Upgrades Ped Ramp - Manhattan & Bronx | 3 | FINAL DESIGN | 2020-01-26 | 2020-07-23 | 2020-01-26 | 2020-07-23
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MXC | Non-Standard Upgrades Ped Ramp - Manhattan & Bronx | 4 | BID AWARD AND REGISTER CONTRCT | 2020-07-24 | 2020-10-21 | 2020-07-24 | 2020-10-21
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MXC | Non-Standard Upgrades Ped Ramp - Manhattan & Bronx | 5 | CONSTRUCTION TO 25% | 2020-10-22 | 2021-02-18 | 2020-10-22 | 2021-02-18
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MXC | Non-Standard Upgrades Ped Ramp - Manhattan & Bronx | 6 | CONSTRUCTION TO 50% | 2021-02-19 | 2021-06-18 | 2021-02-19 | 2021-06-18
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MXC | Non-Standard Upgrades Ped Ramp - Manhattan & Bronx | 7 | CONSTRUCTION TO 75% | 2021-06-19 | 2021-10-16 | 2021-06-19 | 2021-10-16
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MXC | Non-Standard Upgrades Ped Ramp - Manhattan & Bronx | 8 | ORIGINAL EQUIP & FURNISHING | 2021-10-17 | 2022-01-14 | 2021-10-17 | 2022-01-14
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MXC | Non-Standard Upgrades Ped Ramp - Manhattan & Bronx | 9 | SUBSTANTIAL COMPLETION | 2022-01-15 | 2022-03-15 | 2022-01-15 | 2022-03-15
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MXC | Non-Standard Upgrades Ped Ramp - Manhattan & Bronx | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-16 | 2022-04-14 | 2022-03-16 | 2022-04-14
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21KR | Rehabilitation of Standard Ped Ramps - Brooklyn&Staten Islan | 1 | DEVELOP SCOPE | 2021-06-30 | 2021-09-27 | 2021-06-30 | 2021-09-27
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21KR | Rehabilitation of Standard Ped Ramps - Brooklyn&Staten Islan | 2 | PRELIMINARY DESIGN | 2021-09-28 | 2022-01-25 | 2021-09-28 | 2022-01-25
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21KR | Rehabilitation of Standard Ped Ramps - Brooklyn&Staten Islan | 3 | FINAL DESIGN | 2022-01-26 | 2022-07-24 | 2022-01-26 | 2022-07-24
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21KR | Rehabilitation of Standard Ped Ramps - Brooklyn&Staten Islan | 4 | BID AWARD AND REGISTER CONTRCT | 2022-07-25 | 2022-10-22 | 2022-07-25 | 2022-10-22
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21KR | Rehabilitation of Standard Ped Ramps - Brooklyn&Staten Islan | 5 | CONSTRUCTION TO 25% | 2022-10-23 | 2023-02-19 | 2022-10-23 | 2023-02-19
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21KR | Rehabilitation of Standard Ped Ramps - Brooklyn&Staten Islan | 6 | CONSTRUCTION TO 50% | 2023-02-20 | 2023-06-19 | 2023-02-20 | 2023-06-19
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21KR | Rehabilitation of Standard Ped Ramps - Brooklyn&Staten Islan | 7 | CONSTRUCTION TO 75% | 2023-06-20 | 2023-10-17 | 2023-06-20 | 2023-10-17
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21KR | Rehabilitation of Standard Ped Ramps - Brooklyn&Staten Islan | 8 | ORIGINAL EQUIP & FURNISHING | 2023-10-18 | 2024-01-15 | 2023-10-18 | 2024-01-15
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21KR | Rehabilitation of Standard Ped Ramps - Brooklyn&Staten Islan | 9 | SUBSTANTIAL COMPLETION | 2024-01-16 | 2024-03-15 | 2024-01-16 | 2024-03-15
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21KR | Rehabilitation of Standard Ped Ramps - Brooklyn&Staten Islan | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-03-16 | 2024-04-14 | 2024-03-16 | 2024-04-14
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21MQ | Rehabilitation of Standard Ped Ramps - Queens & Manhattan | 1 | DEVELOP SCOPE | 2021-06-30 | 2021-09-27 | 2021-06-30 | 2021-09-27
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21MQ | Rehabilitation of Standard Ped Ramps - Queens & Manhattan | 2 | PRELIMINARY DESIGN | 2021-09-28 | 2022-01-25 | 2021-09-28 | 2022-01-25
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21MQ | Rehabilitation of Standard Ped Ramps - Queens & Manhattan | 3 | FINAL DESIGN | 2022-01-26 | 2022-07-24 | 2022-01-26 | 2022-07-24
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21MQ | Rehabilitation of Standard Ped Ramps - Queens & Manhattan | 4 | BID AWARD AND REGISTER CONTRCT | 2022-07-25 | 2022-10-22 | 2022-07-25 | 2022-10-22
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21MQ | Rehabilitation of Standard Ped Ramps - Queens & Manhattan | 5 | CONSTRUCTION TO 25% | 2022-10-23 | 2023-02-19 | 2022-10-23 | 2023-02-19
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21MQ | Rehabilitation of Standard Ped Ramps - Queens & Manhattan | 6 | CONSTRUCTION TO 50% | 2023-02-20 | 2023-06-19 | 2023-02-20 | 2023-06-19
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21MQ | Rehabilitation of Standard Ped Ramps - Queens & Manhattan | 7 | CONSTRUCTION TO 75% | 2023-06-20 | 2023-10-17 | 2023-06-20 | 2023-10-17
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21MQ | Rehabilitation of Standard Ped Ramps - Queens & Manhattan | 8 | ORIGINAL EQUIP & FURNISHING | 2023-10-18 | 2024-01-15 | 2023-10-18 | 2024-01-15
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21MQ | Rehabilitation of Standard Ped Ramps - Queens & Manhattan | 9 | SUBSTANTIAL COMPLETION | 2024-01-16 | 2024-03-15 | 2024-01-16 | 2024-03-15
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21MQ | Rehabilitation of Standard Ped Ramps - Queens & Manhattan | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-03-16 | 2024-04-14 | 2024-03-16 | 2024-04-14
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21QX | Rehabilitation of Standard Ped Ramps - Queens & Bronx | 1 | DEVELOP SCOPE | 2021-06-30 | 2021-09-27 | 2021-06-30 | 2021-09-27
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21QX | Rehabilitation of Standard Ped Ramps - Queens & Bronx | 2 | PRELIMINARY DESIGN | 2021-09-28 | 2022-01-25 | 2021-09-28 | 2022-01-25
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21QX | Rehabilitation of Standard Ped Ramps - Queens & Bronx | 3 | FINAL DESIGN | 2022-01-26 | 2022-07-24 | 2022-01-26 | 2022-07-24
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21QX | Rehabilitation of Standard Ped Ramps - Queens & Bronx | 4 | BID AWARD AND REGISTER CONTRCT | 2022-07-25 | 2022-10-22 | 2022-07-25 | 2022-10-22
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21QX | Rehabilitation of Standard Ped Ramps - Queens & Bronx | 5 | CONSTRUCTION TO 25% | 2022-10-23 | 2023-02-19 | 2022-10-23 | 2023-02-19
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21QX | Rehabilitation of Standard Ped Ramps - Queens & Bronx | 6 | CONSTRUCTION TO 50% | 2023-02-20 | 2023-06-19 | 2023-02-20 | 2023-06-19
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21QX | Rehabilitation of Standard Ped Ramps - Queens & Bronx | 7 | CONSTRUCTION TO 75% | 2023-06-20 | 2023-10-17 | 2023-06-20 | 2023-10-17
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21QX | Rehabilitation of Standard Ped Ramps - Queens & Bronx | 8 | ORIGINAL EQUIP & FURNISHING | 2023-10-18 | 2024-01-15 | 2023-10-18 | 2024-01-15
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21QX | Rehabilitation of Standard Ped Ramps - Queens & Bronx | 9 | SUBSTANTIAL COMPLETION | 2024-01-16 | 2024-03-15 | 2024-01-16 | 2024-03-15
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21QX | Rehabilitation of Standard Ped Ramps - Queens & Bronx | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-03-16 | 2024-04-14 | 2024-03-16 | 2024-04-14
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2006C | PRIOR NOTICE AND EMERGENCY SIDEWALKS - CW | 1 | DEVELOP SCOPE | 2005-03-30 | 2005-06-27 | 2005-03-30 | 2005-06-27
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2006C | PRIOR NOTICE AND EMERGENCY SIDEWALKS - CW | 2 | PRELIMINARY DESIGN | 2005-06-28 | 2005-10-25 | 2005-06-28 | 2005-10-25
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2006C | PRIOR NOTICE AND EMERGENCY SIDEWALKS - CW | 3 | FINAL DESIGN | 2005-10-26 | 2006-04-23 | 2005-10-26 | 2006-04-23
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2006C | PRIOR NOTICE AND EMERGENCY SIDEWALKS - CW | 4 | BID AWARD AND REGISTER CONTRCT | 2006-03-14 | 2006-12-01 | 2006-03-14 | 2006-12-01
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2006C | PRIOR NOTICE AND EMERGENCY SIDEWALKS - CW | 5 | CONSTRUCTION TO 25% | 2006-12-02 | 2006-12-01 | 2006-12-02 | 2006-12-01
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2006C | PRIOR NOTICE AND EMERGENCY SIDEWALKS - CW | 6 | CONSTRUCTION TO 50% | 2006-12-02 | 2006-12-01 | 2006-12-02 | 2006-12-01
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2006C | PRIOR NOTICE AND EMERGENCY SIDEWALKS - CW | 7 | CONSTRUCTION TO 75% | 2006-12-02 | 2006-12-01 | 2006-12-02 | 2006-12-01
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2006C | PRIOR NOTICE AND EMERGENCY SIDEWALKS - CW | 8 | ORIGINAL EQUIP & FURNISHING | 2006-12-02 | 2006-12-01 | 2006-12-02 | 2006-12-01
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2006C | PRIOR NOTICE AND EMERGENCY SIDEWALKS - CW | 9 | SUBSTANTIAL COMPLETION | 2006-12-02 | 2006-12-01 | 2006-12-02 | 2006-12-01
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2006C | PRIOR NOTICE AND EMERGENCY SIDEWALKS - CW | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2006-12-02 | 2006-12-31 | 2006-12-02 | 2029-06-30
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2011CW | PRIOR NOTICE SIDEWALKS - CITYWIDE (SIM) | 1 | DEVELOP SCOPE | 2009-12-07 | 2010-03-06 | 2009-12-07 | 2010-03-06
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2011CW | PRIOR NOTICE SIDEWALKS - CITYWIDE (SIM) | 2 | PRELIMINARY DESIGN | 2010-03-07 | 2010-07-04 | 2010-03-07 | 2010-07-04
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2011CW | PRIOR NOTICE SIDEWALKS - CITYWIDE (SIM) | 3 | FINAL DESIGN | 2010-07-05 | 2010-12-31 | 2010-07-05 | 2013-09-03
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2011CW | PRIOR NOTICE SIDEWALKS - CITYWIDE (SIM) | 4 | BID AWARD AND REGISTER CONTRCT | 2011-01-01 | 2011-03-31 | 2012-09-04 | 2012-12-02
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2011CW | PRIOR NOTICE SIDEWALKS - CITYWIDE (SIM) | 5 | CONSTRUCTION TO 25% | 2011-04-01 | 2011-07-29 | 2012-12-03 | 2013-04-01
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2011CW | PRIOR NOTICE SIDEWALKS - CITYWIDE (SIM) | 6 | CONSTRUCTION TO 50% | 2011-07-30 | 2011-11-26 | 2013-04-02 | 2013-07-30
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2011CW | PRIOR NOTICE SIDEWALKS - CITYWIDE (SIM) | 7 | CONSTRUCTION TO 75% | 2011-11-27 | 2012-03-25 | 2015-08-01 | 2015-12-08
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2011CW | PRIOR NOTICE SIDEWALKS - CITYWIDE (SIM) | 8 | ORIGINAL EQUIP & FURNISHING | 2012-03-26 | 2012-06-23 | 2015-11-03 | 2016-03-31
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2011CW | PRIOR NOTICE SIDEWALKS - CITYWIDE (SIM) | 9 | SUBSTANTIAL COMPLETION | 2012-06-24 | 2012-08-22 | 2016-04-01 | 2016-06-29
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2011CW | PRIOR NOTICE SIDEWALKS - CITYWIDE (SIM) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-08-23 | 2012-09-21 | 2016-06-30 | 2021-06-30
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2012CW | PRIOR NOTICE SIDEWALKS - CITYWIDE | 1 | DEVELOP SCOPE | 2010-07-01 | 2010-09-28 | 2010-07-01 | 2010-09-28
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2012CW | PRIOR NOTICE SIDEWALKS - CITYWIDE | 2 | PRELIMINARY DESIGN | 2010-09-29 | 2011-01-26 | 2010-09-29 | 2011-01-26
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2012CW | PRIOR NOTICE SIDEWALKS - CITYWIDE | 3 | FINAL DESIGN | 2011-01-27 | 2011-07-25 | 2011-01-27 | 2012-09-03
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2012CW | PRIOR NOTICE SIDEWALKS - CITYWIDE | 4 | BID AWARD AND REGISTER CONTRCT | 2011-07-26 | 2011-10-23 | 2012-09-04 | 2012-12-02
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2012CW | PRIOR NOTICE SIDEWALKS - CITYWIDE | 5 | CONSTRUCTION TO 25% | 2011-10-24 | 2012-02-20 | 2012-12-03 | 2013-05-31
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2012CW | PRIOR NOTICE SIDEWALKS - CITYWIDE | 6 | CONSTRUCTION TO 50% | 2012-02-21 | 2012-06-19 | 2013-06-01 | 2013-11-27
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2012CW | PRIOR NOTICE SIDEWALKS - CITYWIDE | 7 | CONSTRUCTION TO 75% | 2012-06-20 | 2012-10-17 | 2013-11-28 | 2015-12-02
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2012CW | PRIOR NOTICE SIDEWALKS - CITYWIDE | 8 | ORIGINAL EQUIP & FURNISHING | 2012-10-18 | 2013-01-15 | 2015-12-03 | 2016-03-01
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2012CW | PRIOR NOTICE SIDEWALKS - CITYWIDE | 9 | SUBSTANTIAL COMPLETION | 2013-01-16 | 2013-03-16 | 2016-03-02 | 2016-05-15
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2012CW | PRIOR NOTICE SIDEWALKS - CITYWIDE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-03-17 | 2013-04-15 | 2016-05-16 | 2029-06-30
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020XM | Prior Notice Sidewalks- Manhattan & Bronx | 1 | DEVELOP SCOPE | 2019-06-30 | 2019-09-27 | 2019-06-30 | 2019-09-27
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020XM | Prior Notice Sidewalks- Manhattan & Bronx | 2 | PRELIMINARY DESIGN | 2019-09-28 | 2020-01-25 | 2019-09-28 | 2020-01-25
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020XM | Prior Notice Sidewalks- Manhattan & Bronx | 3 | FINAL DESIGN | 2020-01-26 | 2020-07-23 | 2020-01-26 | 2020-07-23
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020XM | Prior Notice Sidewalks- Manhattan & Bronx | 4 | BID AWARD AND REGISTER CONTRCT | 2020-07-24 | 2020-10-21 | 2020-07-24 | 2020-10-21
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020XM | Prior Notice Sidewalks- Manhattan & Bronx | 5 | CONSTRUCTION TO 25% | 2020-10-22 | 2021-02-18 | 2020-10-22 | 2021-02-18
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020XM | Prior Notice Sidewalks- Manhattan & Bronx | 6 | CONSTRUCTION TO 50% | 2021-02-19 | 2021-06-18 | 2021-02-19 | 2021-06-18
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020XM | Prior Notice Sidewalks- Manhattan & Bronx | 7 | CONSTRUCTION TO 75% | 2021-06-19 | 2021-10-16 | 2021-06-19 | 2021-10-16
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020XM | Prior Notice Sidewalks- Manhattan & Bronx | 8 | ORIGINAL EQUIP & FURNISHING | 2021-10-17 | 2022-01-14 | 2021-10-17 | 2022-01-14
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020XM | Prior Notice Sidewalks- Manhattan & Bronx | 9 | SUBSTANTIAL COMPLETION | 2022-01-15 | 2022-03-15 | 2022-01-15 | 2022-03-15
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020XM | Prior Notice Sidewalks- Manhattan & Bronx | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-16 | 2022-04-14 | 2022-03-16 | 2022-04-14
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRQX1 | Trench Restoration - Queens and Bronx (SEX002271) | 1 | DEVELOP SCOPE | 2019-03-01 | 2019-05-29 | 2019-03-01 | 2019-05-29
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRQX1 | Trench Restoration - Queens and Bronx (SEX002271) | 2 | PRELIMINARY DESIGN | 2019-05-30 | 2019-09-26 | 2019-05-30 | 2019-09-26
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRQX1 | Trench Restoration - Queens and Bronx (SEX002271) | 3 | FINAL DESIGN | 2019-09-27 | 2020-07-01 | 2019-09-27 | 2020-07-01
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRQX1 | Trench Restoration - Queens and Bronx (SEX002271) | 4 | BID AWARD AND REGISTER CONTRCT | 2020-07-02 | 2020-09-29 | 2020-07-02 | 2020-09-29
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRQX1 | Trench Restoration - Queens and Bronx (SEX002271) | 5 | CONSTRUCTION TO 25% | 2020-09-30 | 2021-01-27 | 2020-09-30 | 2021-01-27
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRQX1 | Trench Restoration - Queens and Bronx (SEX002271) | 6 | CONSTRUCTION TO 50% | 2021-01-28 | 2021-05-27 | 2021-01-28 | 2021-05-27
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRQX1 | Trench Restoration - Queens and Bronx (SEX002271) | 7 | CONSTRUCTION TO 75% | 2021-05-28 | 2021-09-24 | 2021-05-28 | 2021-09-24
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRQX1 | Trench Restoration - Queens and Bronx (SEX002271) | 8 | ORIGINAL EQUIP & FURNISHING | 2021-09-25 | 2021-12-23 | 2021-09-25 | 2021-12-23
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRQX1 | Trench Restoration - Queens and Bronx (SEX002271) | 9 | SUBSTANTIAL COMPLETION | 2021-12-24 | 2022-02-21 | 2021-12-24 | 2022-02-21
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRQX1 | Trench Restoration - Queens and Bronx (SEX002271) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-02-22 | 2022-03-23 | 2022-02-22 | 2022-03-23
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | JJ1FACREN | FACILITIES RENOVATIONS | 1 | DESIGN | 2004-06-30 | 2004-12-26 | 2015-01-01 | 2015-06-29
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | JJ1FACREN | FACILITIES RENOVATIONS | 2 | BID AWARD AND REGISTER CONTRCT | 2004-12-27 | 2005-03-26 | 2015-06-30 | 2015-09-27
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | JJ1FACREN | FACILITIES RENOVATIONS | 3 | CONSTRUCTION | 2005-03-27 | 2015-03-24 | 2015-09-28 | 2018-09-24
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | JJ1FACREN | FACILITIES RENOVATIONS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-25 | 2015-09-20 | 2018-09-25 | 2019-03-23
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | JJ1FACREN | FACILITIES RENOVATIONS | 5 | PROJECT START | 2015-03-25 | 2015-09-20 | 2019-03-24 | 2019-03-24
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | JJ1FACREN | FACILITIES RENOVATIONS | 6 | DESIGN START | 2015-03-25 | 2015-09-20 | 2019-03-25 | 2019-03-25
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | JJ1FACREN | FACILITIES RENOVATIONS | 7 | DESIGN COMPLETION | 2015-03-25 | 2015-09-20 | 2019-03-26 | 2019-03-26
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | JJ1FACREN | FACILITIES RENOVATIONS | 8 | CONSTRUCTION START | 2015-03-25 | 2015-09-20 | 2019-03-27 | 2019-03-27
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | JJ1FACREN | FACILITIES RENOVATIONS | 9 | CONSTRUCTION COMPLETION | 2015-03-25 | 2015-09-20 | 2019-03-28 | 2025-03-28
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA16WH1 | Washington Heights - Third Floor Renovation | 1 | PROJECT START | 2016-10-26 | 2016-10-26 | 2016-10-26 | 2016-10-26
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA16WH1 | Washington Heights - Third Floor Renovation | 2 | DESIGN START | 2016-10-27 | 2016-10-27 | 2016-10-27 | 2017-12-30
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA16WH1 | Washington Heights - Third Floor Renovation | 3 | DESIGN COMPLETION | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2019-05-30
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA16WH1 | Washington Heights - Third Floor Renovation | 4 | CONSTRUCTION START | 2018-10-29 | 2018-10-29 | 2018-10-29 | 2020-01-30
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA16WH1 | Washington Heights - Third Floor Renovation | 5 | CONSTRUCTION COMPLETION | 2019-10-30 | 2019-10-30 | 2019-10-30 | 2022-12-30
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PO141-40P | NEW 40TH PRECINCT | 1 | PROJECT START | 2014-07-08 | 2014-07-08 | 2014-07-08 | 2014-07-08
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PO141-40P | NEW 40TH PRECINCT | 2 | DESIGN START | 2014-07-09 | 2015-01-05 | 2014-07-09 | 2015-01-05
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PO141-40P | NEW 40TH PRECINCT | 3 | DESIGN COMPLETION | 2015-01-06 | 2016-04-05 | 2015-01-06 | 2016-04-05
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PO141-40P | NEW 40TH PRECINCT | 4 | CONSTRUCTION START | 2016-04-06 | 2016-08-30 | 2016-04-06 | 2016-08-30
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PO141-40P | NEW 40TH PRECINCT | 5 | CONSTRUCTION COMPLETION | 2016-08-31 | 2018-09-24 | 2016-08-31 | 2023-06-25
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PO205-PA | CONSTRUCTION OF A NEW POLICE ACADEMY/TRAINING FACILITY | 1 | PROJECT START | 2007-02-19 | 2007-02-19 | 2007-02-19 | 2007-02-19
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PO205-PA | CONSTRUCTION OF A NEW POLICE ACADEMY/TRAINING FACILITY | 2 | DESIGN START | 2007-04-09 | 2008-09-08 | 2007-04-09 | 2008-04-01
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PO205-PA | CONSTRUCTION OF A NEW POLICE ACADEMY/TRAINING FACILITY | 3 | DESIGN COMPLETION | 2008-09-28 | 2008-09-28 | 2008-04-02 | 2011-02-28
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PO205-PA | CONSTRUCTION OF A NEW POLICE ACADEMY/TRAINING FACILITY | 4 | CONSTRUCTION START | 2008-09-28 | 2008-09-28 | 2008-09-28 | 2008-09-28
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PO205-PA | CONSTRUCTION OF A NEW POLICE ACADEMY/TRAINING FACILITY | 5 | CONSTRUCTION COMPLETION | 2008-09-29 | 2009-03-01 | 2008-09-29 | 2023-06-30
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79FDCW1 | Front Desk Renovations for 45th, 75th, 105th, 123rd PCTS | 1 | DESIGN | 2017-12-01 | 2018-05-29 | 2017-12-01 | 2021-02-20
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79FDCW1 | Front Desk Renovations for 45th, 75th, 105th, 123rd PCTS | 2 | BID AWARD AND REGISTER CONTRCT | 2018-05-30 | 2018-08-27 | 2021-02-21 | 2021-05-21
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79FDCW1 | Front Desk Renovations for 45th, 75th, 105th, 123rd PCTS | 3 | CONSTRUCTION | 2018-08-28 | 2019-08-27 | 2021-05-22 | 2022-05-21
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79FDCW1 | Front Desk Renovations for 45th, 75th, 105th, 123rd PCTS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-08-28 | 2020-02-23 | 2022-05-22 | 2022-11-17
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79FDCW1 | Front Desk Renovations for 45th, 75th, 105th, 123rd PCTS | 5 | PROJECT START | 2019-08-28 | 2020-02-23 | 2022-11-18 | 2022-11-18
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79FDCW1 | Front Desk Renovations for 45th, 75th, 105th, 123rd PCTS | 6 | DESIGN START | 2019-08-28 | 2020-02-23 | 2022-11-19 | 2022-11-19
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79FDCW1 | Front Desk Renovations for 45th, 75th, 105th, 123rd PCTS | 7 | DESIGN COMPLETION | 2019-08-28 | 2020-02-23 | 2022-11-20 | 2022-11-20
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79FDCW1 | Front Desk Renovations for 45th, 75th, 105th, 123rd PCTS | 8 | CONSTRUCTION START | 2019-08-28 | 2020-02-23 | 2022-11-21 | 2022-11-21
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79FDCW1 | Front Desk Renovations for 45th, 75th, 105th, 123rd PCTS | 9 | CONSTRUCTION COMPLETION | 2019-08-28 | 2020-02-23 | 2022-11-22 | 2022-11-22
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79GENER | GENERATOR REPLACEMENT AT VARIOUS PRECINCTS | 1 | DEVELOP SCOPE | 2015-02-10 | 2015-05-10 | 2015-02-10 | 2015-03-11
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79GENER | GENERATOR REPLACEMENT AT VARIOUS PRECINCTS | 2 | PRELIMINARY DESIGN | 2015-05-11 | 2015-09-07 | 2015-03-12 | 2016-03-10
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79GENER | GENERATOR REPLACEMENT AT VARIOUS PRECINCTS | 3 | FINAL DESIGN | 2015-09-08 | 2016-01-05 | 2016-03-11 | 2018-02-28
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79GENER | GENERATOR REPLACEMENT AT VARIOUS PRECINCTS | 4 | BID AWARD AND REGISTER CONTRCT | 2016-01-06 | 2016-07-03 | 2018-03-01 | 2020-06-30
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79GENER | GENERATOR REPLACEMENT AT VARIOUS PRECINCTS | 5 | CONSTRUCTION TO 25% | 2016-07-04 | 2016-10-31 | 2020-07-01 | 2022-06-20
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79GENER | GENERATOR REPLACEMENT AT VARIOUS PRECINCTS | 6 | CONSTRUCTION TO 50% | 2016-11-01 | 2017-02-28 | 2020-07-01 | 2022-06-20
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79GENER | GENERATOR REPLACEMENT AT VARIOUS PRECINCTS | 7 | CONSTRUCTION TO 75% | 2017-03-01 | 2017-06-28 | 2020-07-01 | 2022-06-20
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79GENER | GENERATOR REPLACEMENT AT VARIOUS PRECINCTS | 8 | ORIGINAL EQUIP & FURNISHING | 2017-06-29 | 2017-09-26 | 2020-07-01 | 2022-06-20
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79GENER | GENERATOR REPLACEMENT AT VARIOUS PRECINCTS | 9 | SUBSTANTIAL COMPLETION | 2017-09-27 | 2017-11-25 | 2020-07-01 | 2022-06-20
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79GENER | GENERATOR REPLACEMENT AT VARIOUS PRECINCTS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-11-26 | 2017-12-25 | 2020-07-01 | 2022-06-20
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79WNDWS | HWY UNIT 3, 67TH, 76TH, 111TH PCT WINDOW RPLCMNT | 1 | PROJECT START | 2013-03-28 | 2014-10-17 | 2013-03-28 | 2014-10-17
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79WNDWS | HWY UNIT 3, 67TH, 76TH, 111TH PCT WINDOW RPLCMNT | 2 | DESIGN START | 2014-10-18 | 2015-03-03 | 2014-10-18 | 2015-03-03
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79WNDWS | HWY UNIT 3, 67TH, 76TH, 111TH PCT WINDOW RPLCMNT | 3 | DESIGN COMPLETION | 2015-03-04 | 2015-09-04 | 2015-03-04 | 2015-09-04
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79WNDWS | HWY UNIT 3, 67TH, 76TH, 111TH PCT WINDOW RPLCMNT | 4 | CONSTRUCTION START | 2015-09-05 | 2016-02-25 | 2015-09-05 | 2016-02-25
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79WNDWS | HWY UNIT 3, 67TH, 76TH, 111TH PCT WINDOW RPLCMNT | 5 | CONSTRUCTION COMPLETION | 2016-02-26 | 2017-02-25 | 2016-02-26 | 2024-03-07
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PS-312CW | CITYWIDE REPAIRS & REHAB OF INTERCEPTING SEWERS - CITYWIDE | 1 | DEVELOP SCOPE | 2012-02-17 | 2012-05-16 | 2012-02-17 | 2012-05-16
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PS-312CW | CITYWIDE REPAIRS & REHAB OF INTERCEPTING SEWERS - CITYWIDE | 2 | PRELIMINARY DESIGN | 2012-05-17 | 2012-09-13 | 2012-05-17 | 2012-09-13
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PS-312CW | CITYWIDE REPAIRS & REHAB OF INTERCEPTING SEWERS - CITYWIDE | 3 | FINAL DESIGN | 2012-09-14 | 2013-03-12 | 2012-09-14 | 2013-03-12
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PS-312CW | CITYWIDE REPAIRS & REHAB OF INTERCEPTING SEWERS - CITYWIDE | 4 | BID AWARD AND REGISTER CONTRCT | 2013-03-13 | 2013-06-10 | 2013-03-13 | 2013-06-10
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PS-312CW | CITYWIDE REPAIRS & REHAB OF INTERCEPTING SEWERS - CITYWIDE | 5 | CONSTRUCTION TO 25% | 2013-06-11 | 2013-10-08 | 2013-06-11 | 2013-10-08
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PS-312CW | CITYWIDE REPAIRS & REHAB OF INTERCEPTING SEWERS - CITYWIDE | 6 | CONSTRUCTION TO 50% | 2013-10-09 | 2014-02-05 | 2013-10-09 | 2014-02-05
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PS-312CW | CITYWIDE REPAIRS & REHAB OF INTERCEPTING SEWERS - CITYWIDE | 7 | CONSTRUCTION TO 75% | 2014-02-06 | 2014-10-02 | 2014-02-06 | 2014-10-02
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PS-312CW | CITYWIDE REPAIRS & REHAB OF INTERCEPTING SEWERS - CITYWIDE | 8 | ORIGINAL EQUIP & FURNISHING | 2014-10-03 | 2015-01-01 | 2014-10-03 | 2015-01-01
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PS-312CW | CITYWIDE REPAIRS & REHAB OF INTERCEPTING SEWERS - CITYWIDE | 9 | SUBSTANTIAL COMPLETION | 2015-01-02 | 2015-03-02 | 2015-01-02 | 2015-03-02
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PS-312CW | CITYWIDE REPAIRS & REHAB OF INTERCEPTING SEWERS - CITYWIDE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-03 | 2015-04-01 | 2015-03-03 | 2022-06-30
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PS-312MX | CITYWIDE REPAIRS & REHAB OF INTERCEPTING SEWERS - MAN & BX | 1 | DEVELOP SCOPE | 2014-02-18 | 2014-05-18 | 2014-02-18 | 2014-05-18
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PS-312MX | CITYWIDE REPAIRS & REHAB OF INTERCEPTING SEWERS - MAN & BX | 2 | PRELIMINARY DESIGN | 2014-05-19 | 2014-09-15 | 2014-05-19 | 2014-09-15
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PS-312MX | CITYWIDE REPAIRS & REHAB OF INTERCEPTING SEWERS - MAN & BX | 3 | FINAL DESIGN | 2014-09-16 | 2015-03-14 | 2014-09-16 | 2015-03-14
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PS-312MX | CITYWIDE REPAIRS & REHAB OF INTERCEPTING SEWERS - MAN & BX | 4 | BID AWARD AND REGISTER CONTRCT | 2015-03-15 | 2015-06-12 | 2015-03-15 | 2015-06-12
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PS-312MX | CITYWIDE REPAIRS & REHAB OF INTERCEPTING SEWERS - MAN & BX | 5 | CONSTRUCTION TO 25% | 2015-06-13 | 2015-10-10 | 2015-06-13 | 2015-10-10
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PS-312MX | CITYWIDE REPAIRS & REHAB OF INTERCEPTING SEWERS - MAN & BX | 6 | CONSTRUCTION TO 50% | 2015-10-11 | 2016-02-07 | 2015-10-11 | 2016-02-07
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PS-312MX | CITYWIDE REPAIRS & REHAB OF INTERCEPTING SEWERS - MAN & BX | 7 | CONSTRUCTION TO 75% | 2016-02-08 | 2016-06-06 | 2016-02-08 | 2016-06-06
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PS-312MX | CITYWIDE REPAIRS & REHAB OF INTERCEPTING SEWERS - MAN & BX | 8 | ORIGINAL EQUIP & FURNISHING | 2016-06-07 | 2016-09-04 | 2016-06-07 | 2016-09-04
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PS-312MX | CITYWIDE REPAIRS & REHAB OF INTERCEPTING SEWERS - MAN & BX | 9 | SUBSTANTIAL COMPLETION | 2016-09-05 | 2016-11-03 | 2016-09-05 | 2016-11-03
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PS-312MX | CITYWIDE REPAIRS & REHAB OF INTERCEPTING SEWERS - MAN & BX | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-11-04 | 2016-12-03 | 2016-11-04 | 2016-12-03
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PS-312MX | CITYWIDE REPAIRS & REHAB OF INTERCEPTING SEWERS - MAN & BX | 11 | PROJECT START | 2016-11-04 | 2016-12-03 | 2016-12-04 | 2016-12-04
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PS-312MX | CITYWIDE REPAIRS & REHAB OF INTERCEPTING SEWERS - MAN & BX | 12 | DESIGN START | 2016-11-04 | 2016-12-03 | 2016-12-05 | 2016-12-05
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PS-312MX | CITYWIDE REPAIRS & REHAB OF INTERCEPTING SEWERS - MAN & BX | 13 | DESIGN COMPLETION | 2016-11-04 | 2016-12-03 | 2016-12-06 | 2016-12-06
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PS-312MX | CITYWIDE REPAIRS & REHAB OF INTERCEPTING SEWERS - MAN & BX | 14 | CONSTRUCTION START | 2016-11-04 | 2016-12-03 | 2016-12-07 | 2016-12-07
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PS-312MX | CITYWIDE REPAIRS & REHAB OF INTERCEPTING SEWERS - MAN & BX | 15 | CONSTRUCTION COMPLETION | 2016-11-04 | 2016-12-03 | 2016-12-08 | 2023-06-30
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW335ALLS | Asbestos and Lead Abatement Lump Sum | 1 | PROJECT START | 2009-04-15 | 2009-04-15 | 2009-04-15 | 2009-04-15
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW335ALLS | Asbestos and Lead Abatement Lump Sum | 2 | DESIGN START | 2009-04-16 | 2009-04-16 | 2009-04-16 | 2009-04-16
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW335ALLS | Asbestos and Lead Abatement Lump Sum | 3 | DESIGN COMPLETION | 2009-04-17 | 2009-04-17 | 2009-04-17 | 2009-04-17
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW335ALLS | Asbestos and Lead Abatement Lump Sum | 4 | CONSTRUCTION START | 2009-04-18 | 2009-04-18 | 2009-04-18 | 2009-04-18
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW335ALLS | Asbestos and Lead Abatement Lump Sum | 5 | CONSTRUCTION COMPLETION | 2009-04-19 | 2024-04-19 | 2009-04-19 | 2024-04-19
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW335BSLS | Bulk Sampling Lump Sum | 1 | PROJECT START | 2010-05-31 | 2010-05-31 | 2010-05-31 | 2010-05-31
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW335BSLS | Bulk Sampling Lump Sum | 2 | DESIGN START | 2010-06-01 | 2010-06-01 | 2010-06-01 | 2010-06-01
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW335BSLS | Bulk Sampling Lump Sum | 3 | DESIGN COMPLETION | 2010-06-02 | 2011-06-02 | 2010-06-02 | 2011-06-02
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW335BSLS | Bulk Sampling Lump Sum | 4 | CONSTRUCTION START | 2011-06-03 | 2013-06-03 | 2011-06-03 | 2013-06-03
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW335BSLS | Bulk Sampling Lump Sum | 5 | CONSTRUCTION COMPLETION | 2013-06-04 | 2019-06-04 | 2013-06-04 | 2021-06-04
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-71 | FUEL TANK REPLACEMENT | 1 | PROJECT START | 2017-07-01 | 2017-07-01 | 2017-07-01 | 2017-07-01
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-71 | FUEL TANK REPLACEMENT | 2 | DESIGN START | 2017-07-02 | 2017-07-02 | 2017-07-02 | 2017-07-02
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-71 | FUEL TANK REPLACEMENT | 3 | DESIGN COMPLETION | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-71 | FUEL TANK REPLACEMENT | 4 | CONSTRUCTION START | 2017-07-04 | 2017-07-04 | 2017-07-04 | 2017-07-04
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-71 | FUEL TANK REPLACEMENT | 5 | CONSTRUCTION COMPLETION | 2017-07-05 | 2019-07-05 | 2017-07-05 | 2022-06-30
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-72 | FUEL TANK REPLACEMENT | 1 | PROJECT START | 2017-07-01 | 2017-07-01 | 2017-07-01 | 2017-07-01
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-72 | FUEL TANK REPLACEMENT | 2 | DESIGN START | 2017-07-02 | 2017-07-02 | 2017-07-02 | 2017-07-02
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-72 | FUEL TANK REPLACEMENT | 3 | DESIGN COMPLETION | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-72 | FUEL TANK REPLACEMENT | 4 | CONSTRUCTION START | 2017-07-04 | 2017-07-04 | 2017-07-04 | 2017-07-04
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-72 | FUEL TANK REPLACEMENT | 5 | CONSTRUCTION COMPLETION | 2017-07-05 | 2019-07-05 | 2017-07-05 | 2025-11-23
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-73 | FUEL TANK REPLACEMENT | 1 | PROJECT START | 2017-07-01 | 2017-07-01 | 2017-07-01 | 2017-07-01
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-73 | FUEL TANK REPLACEMENT | 2 | DESIGN START | 2017-07-02 | 2017-07-02 | 2017-07-02 | 2017-07-02
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-73 | FUEL TANK REPLACEMENT | 3 | DESIGN COMPLETION | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-73 | FUEL TANK REPLACEMENT | 4 | CONSTRUCTION START | 2017-07-04 | 2017-07-04 | 2017-07-04 | 2017-07-04
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-73 | FUEL TANK REPLACEMENT | 5 | CONSTRUCTION COMPLETION | 2017-07-05 | 2019-07-05 | 2017-07-05 | 2022-06-30
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-81 | FUEL TANK REPLACEMENT | 1 | PROJECT START | 2018-07-01 | 2018-07-01 | 2018-07-01 | 2018-07-01
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-81 | FUEL TANK REPLACEMENT | 2 | DESIGN START | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-81 | FUEL TANK REPLACEMENT | 3 | DESIGN COMPLETION | 2018-07-03 | 2018-07-03 | 2018-07-03 | 2018-07-03
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-81 | FUEL TANK REPLACEMENT | 4 | CONSTRUCTION START | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-81 | FUEL TANK REPLACEMENT | 5 | CONSTRUCTION COMPLETION | 2018-07-05 | 2020-07-05 | 2018-07-05 | 2023-06-30
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-82 | FUEL TANK REPLACEMENT | 1 | PROJECT START | 2018-07-01 | 2018-07-01 | 2018-07-01 | 2018-07-01
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-82 | FUEL TANK REPLACEMENT | 2 | DESIGN START | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-82 | FUEL TANK REPLACEMENT | 3 | DESIGN COMPLETION | 2018-07-03 | 2018-07-03 | 2018-07-03 | 2018-07-03
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-82 | FUEL TANK REPLACEMENT | 4 | CONSTRUCTION START | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-82 | FUEL TANK REPLACEMENT | 5 | CONSTRUCTION COMPLETION | 2018-07-05 | 2020-07-05 | 2018-07-05 | 2023-06-30
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-83 | FUEL TANK REPLACEMENT | 1 | PROJECT START | 2018-07-01 | 2018-07-01 | 2018-07-01 | 2018-07-01
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-83 | FUEL TANK REPLACEMENT | 2 | DESIGN START | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-83 | FUEL TANK REPLACEMENT | 3 | DESIGN COMPLETION | 2018-07-03 | 2018-07-03 | 2018-07-03 | 2018-07-03
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-83 | FUEL TANK REPLACEMENT | 4 | CONSTRUCTION START | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-83 | FUEL TANK REPLACEMENT | 5 | CONSTRUCTION COMPLETION | 2018-07-05 | 2020-07-05 | 2018-07-05 | 2022-06-30
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-84 | FUEL TANK REPLACEMENT | 1 | PROJECT START | 2018-07-01 | 2018-07-01 | 2018-07-01 | 2018-07-01
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-84 | FUEL TANK REPLACEMENT | 2 | DESIGN START | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-84 | FUEL TANK REPLACEMENT | 3 | DESIGN COMPLETION | 2018-07-03 | 2018-07-03 | 2018-07-03 | 2018-07-03
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-84 | FUEL TANK REPLACEMENT | 4 | CONSTRUCTION START | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-84 | FUEL TANK REPLACEMENT | 5 | CONSTRUCTION COMPLETION | 2018-07-05 | 2020-07-05 | 2018-07-05 | 2023-06-30
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PWCOMPDAT | Comptroller's Office Data Center Replacement at 1 Centre St. | 1 | PROJECT START | 2018-03-26 | 2018-03-26 | 2018-03-26 | 2018-03-26
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PWCOMPDAT | Comptroller's Office Data Center Replacement at 1 Centre St. | 2 | DESIGN START | 2018-03-26 | 2018-06-27 | 2018-03-26 | 2018-06-27
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PWCOMPDAT | Comptroller's Office Data Center Replacement at 1 Centre St. | 3 | DESIGN COMPLETION | 2018-06-28 | 2019-07-03 | 2018-06-28 | 2019-07-03
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PWCOMPDAT | Comptroller's Office Data Center Replacement at 1 Centre St. | 4 | CONSTRUCTION START | 2019-07-04 | 2020-05-03 | 2019-07-04 | 2020-05-03
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PWCOMPDAT | Comptroller's Office Data Center Replacement at 1 Centre St. | 5 | CONSTRUCTION COMPLETION | 2020-05-04 | 2021-11-02 | 2020-05-04 | 2021-11-02
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1047 | Area Contract for Water Main Replacement, Queens & Bronx | 1 | DEVELOP SCOPE | 2017-03-01 | 2017-05-29 | 2017-05-31 | 2017-09-04
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1047 | Area Contract for Water Main Replacement, Queens & Bronx | 2 | PRELIMINARY DESIGN | 2017-05-30 | 2017-09-26 | 2017-09-05 | 2017-10-30
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1047 | Area Contract for Water Main Replacement, Queens & Bronx | 3 | FINAL DESIGN | 2017-09-27 | 2018-03-25 | 2017-10-31 | 2017-12-26
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1047 | Area Contract for Water Main Replacement, Queens & Bronx | 4 | BID AWARD AND REGISTER CONTRCT | 2018-03-26 | 2018-06-23 | 2017-12-27 | 2018-09-04
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1047 | Area Contract for Water Main Replacement, Queens & Bronx | 5 | CONSTRUCTION TO 25% | 2018-06-24 | 2018-10-21 | 2018-09-05 | 2019-01-02
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1047 | Area Contract for Water Main Replacement, Queens & Bronx | 6 | CONSTRUCTION TO 50% | 2018-10-22 | 2019-02-18 | 2019-01-03 | 2019-05-02
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1047 | Area Contract for Water Main Replacement, Queens & Bronx | 7 | CONSTRUCTION TO 75% | 2019-02-19 | 2019-06-18 | 2019-05-03 | 2019-08-30
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1047 | Area Contract for Water Main Replacement, Queens & Bronx | 8 | ORIGINAL EQUIP & FURNISHING | 2019-06-19 | 2019-09-16 | 2019-08-31 | 2019-11-28
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1047 | Area Contract for Water Main Replacement, Queens & Bronx | 9 | SUBSTANTIAL COMPLETION | 2019-09-17 | 2019-11-15 | 2019-11-29 | 2020-01-27
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1047 | Area Contract for Water Main Replacement, Queens & Bronx | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-11-16 | 2019-12-15 | 2020-01-28 | 2022-06-30
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1050 | Install Distribution WM throughout Bronx & Queens | 1 | DEVELOP SCOPE | 2019-08-23 | 2019-11-20 | 2019-08-23 | 2019-11-20
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1050 | Install Distribution WM throughout Bronx & Queens | 2 | PRELIMINARY DESIGN | 2019-11-21 | 2020-03-19 | 2019-11-21 | 2020-03-19
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1050 | Install Distribution WM throughout Bronx & Queens | 3 | FINAL DESIGN | 2020-03-20 | 2020-09-15 | 2020-03-20 | 2020-09-15
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1050 | Install Distribution WM throughout Bronx & Queens | 4 | BID AWARD AND REGISTER CONTRCT | 2020-09-16 | 2020-12-14 | 2020-09-16 | 2020-12-14
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1050 | Install Distribution WM throughout Bronx & Queens | 5 | CONSTRUCTION TO 25% | 2020-12-15 | 2021-04-13 | 2020-12-15 | 2021-04-13
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1050 | Install Distribution WM throughout Bronx & Queens | 6 | CONSTRUCTION TO 50% | 2021-04-14 | 2021-08-11 | 2021-04-14 | 2021-08-11
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1050 | Install Distribution WM throughout Bronx & Queens | 7 | CONSTRUCTION TO 75% | 2021-08-12 | 2021-12-09 | 2021-08-12 | 2021-12-09
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1050 | Install Distribution WM throughout Bronx & Queens | 8 | ORIGINAL EQUIP & FURNISHING | 2021-12-10 | 2022-03-09 | 2021-12-10 | 2022-03-09
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1050 | Install Distribution WM throughout Bronx & Queens | 9 | SUBSTANTIAL COMPLETION | 2022-03-10 | 2022-05-08 | 2022-03-10 | 2022-05-08
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1050 | Install Distribution WM throughout Bronx & Queens | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-05-09 | 2022-06-07 | 2022-05-09 | 2022-06-07
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-998 | WATER MAIN DISTRIBUTION EXTENSIONS (NEW BUILDINGS CITYWIDE | 6 | CONSTRUCTION TO 50% | 2010-02-20 | 2010-06-19 | 2010-02-20 | 2010-06-19
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-998 | WATER MAIN DISTRIBUTION EXTENSIONS (NEW BUILDINGS CITYWIDE | 7 | CONSTRUCTION TO 75% | 2010-06-20 | 2010-10-17 | 2010-06-20 | 2010-10-17
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-998 | WATER MAIN DISTRIBUTION EXTENSIONS (NEW BUILDINGS CITYWIDE | 8 | ORIGINAL EQUIP & FURNISHING | 2010-10-18 | 2011-01-15 | 2010-10-18 | 2011-01-15
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-998 | WATER MAIN DISTRIBUTION EXTENSIONS (NEW BUILDINGS CITYWIDE | 9 | SUBSTANTIAL COMPLETION | 2011-01-16 | 2011-03-16 | 2011-01-16 | 2011-03-16
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-998 | WATER MAIN DISTRIBUTION EXTENSIONS (NEW BUILDINGS CITYWIDE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2011-03-17 | 2011-04-15 | 2011-03-17 | 2011-04-15
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-385 | Area Contract for Water Main Replacement | 1 | DEVELOP SCOPE | 2017-03-01 | 2017-05-29 | 2017-03-01 | 2017-05-29
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-385 | Area Contract for Water Main Replacement | 2 | PRELIMINARY DESIGN | 2017-05-30 | 2017-09-26 | 2017-05-30 | 2017-09-26
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-385 | Area Contract for Water Main Replacement | 3 | FINAL DESIGN | 2017-09-27 | 2018-03-25 | 2017-09-27 | 2018-03-25
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-385 | Area Contract for Water Main Replacement | 4 | BID AWARD AND REGISTER CONTRCT | 2018-03-26 | 2018-06-23 | 2018-03-26 | 2018-06-23
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-385 | Area Contract for Water Main Replacement | 5 | CONSTRUCTION TO 25% | 2018-06-24 | 2018-10-21 | 2018-06-24 | 2018-10-21
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-385 | Area Contract for Water Main Replacement | 6 | CONSTRUCTION TO 50% | 2018-10-22 | 2019-02-18 | 2018-10-22 | 2019-02-18
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-385 | Area Contract for Water Main Replacement | 7 | CONSTRUCTION TO 75% | 2019-02-19 | 2019-06-18 | 2019-02-19 | 2019-06-18
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-385 | Area Contract for Water Main Replacement | 8 | ORIGINAL EQUIP & FURNISHING | 2019-06-19 | 2019-09-16 | 2019-06-19 | 2019-09-16
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-385 | Area Contract for Water Main Replacement | 9 | SUBSTANTIAL COMPLETION | 2019-09-17 | 2019-11-15 | 2019-09-17 | 2019-11-15
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-385 | Area Contract for Water Main Replacement | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-11-16 | 2019-12-15 | 2019-11-16 | 2022-12-23
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-388 | Install Distribution WM throughout Brooklyn & Staten Island | 1 | DEVELOP SCOPE | 2019-08-23 | 2019-11-20 | 2019-08-23 | 2019-11-20
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-388 | Install Distribution WM throughout Brooklyn & Staten Island | 2 | PRELIMINARY DESIGN | 2019-11-21 | 2020-03-19 | 2019-11-21 | 2020-03-19
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-388 | Install Distribution WM throughout Brooklyn & Staten Island | 3 | FINAL DESIGN | 2020-03-20 | 2020-09-15 | 2020-03-20 | 2020-09-15
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-388 | Install Distribution WM throughout Brooklyn & Staten Island | 4 | BID AWARD AND REGISTER CONTRCT | 2020-09-16 | 2020-12-14 | 2020-09-16 | 2020-12-14
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-388 | Install Distribution WM throughout Brooklyn & Staten Island | 5 | CONSTRUCTION TO 25% | 2020-12-15 | 2021-04-13 | 2020-12-15 | 2021-04-13
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-388 | Install Distribution WM throughout Brooklyn & Staten Island | 6 | CONSTRUCTION TO 50% | 2021-04-14 | 2021-08-11 | 2021-04-14 | 2021-08-11
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-388 | Install Distribution WM throughout Brooklyn & Staten Island | 7 | CONSTRUCTION TO 75% | 2021-08-12 | 2021-12-09 | 2021-08-12 | 2021-12-09
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-388 | Install Distribution WM throughout Brooklyn & Staten Island | 8 | ORIGINAL EQUIP & FURNISHING | 2021-12-10 | 2022-03-09 | 2021-12-10 | 2022-03-09
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-388 | Install Distribution WM throughout Brooklyn & Staten Island | 9 | SUBSTANTIAL COMPLETION | 2022-03-10 | 2022-05-08 | 2022-03-10 | 2022-05-08
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-388 | Install Distribution WM throughout Brooklyn & Staten Island | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-05-09 | 2022-06-07 | 2022-05-09 | 2022-06-07
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDCONDC | Sandy Conduit Replacement - Citywide | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-09-28 | 2016-07-01 | 2016-09-28
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDCONDC | Sandy Conduit Replacement - Citywide | 2 | PRELIMINARY DESIGN | 2016-09-29 | 2017-01-26 | 2016-09-29 | 2017-01-26
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDCONDC | Sandy Conduit Replacement - Citywide | 3 | FINAL DESIGN | 2017-01-27 | 2017-07-25 | 2017-01-27 | 2017-07-25
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDCONDC | Sandy Conduit Replacement - Citywide | 4 | BID AWARD AND REGISTER CONTRCT | 2017-07-26 | 2017-10-23 | 2017-07-26 | 2017-10-23
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDCONDC | Sandy Conduit Replacement - Citywide | 5 | CONSTRUCTION TO 25% | 2017-10-24 | 2018-02-20 | 2017-10-24 | 2018-02-20
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDCONDC | Sandy Conduit Replacement - Citywide | 6 | CONSTRUCTION TO 50% | 2018-02-21 | 2018-06-20 | 2018-02-21 | 2018-06-20
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDCONDC | Sandy Conduit Replacement - Citywide | 7 | CONSTRUCTION TO 75% | 2018-06-21 | 2018-10-18 | 2018-06-21 | 2018-10-18
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDCONDC | Sandy Conduit Replacement - Citywide | 8 | ORIGINAL EQUIP & FURNISHING | 2018-10-19 | 2019-01-16 | 2018-10-19 | 2019-01-16
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDCONDC | Sandy Conduit Replacement - Citywide | 9 | SUBSTANTIAL COMPLETION | 2019-01-17 | 2019-03-17 | 2019-01-17 | 2020-08-31
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDCONDC | Sandy Conduit Replacement - Citywide | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-03-18 | 2019-04-16 | 2020-09-01 | 2024-08-31
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW21 | WHEN AND WHERE HURRICANE SANDY - CITYWIDE | 1 | DEVELOP SCOPE | 2014-06-17 | 2014-09-14 | 2014-02-20 | 2014-02-28
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW21 | WHEN AND WHERE HURRICANE SANDY - CITYWIDE | 2 | PRELIMINARY DESIGN | 2014-09-15 | 2015-01-12 | 2014-03-01 | 2014-04-14
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW21 | WHEN AND WHERE HURRICANE SANDY - CITYWIDE | 3 | FINAL DESIGN | 2015-01-13 | 2015-07-11 | 2014-04-15 | 2014-06-20
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW21 | WHEN AND WHERE HURRICANE SANDY - CITYWIDE | 4 | BID AWARD AND REGISTER CONTRCT | 2015-07-12 | 2015-10-09 | 2014-06-21 | 2015-03-15
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW21 | WHEN AND WHERE HURRICANE SANDY - CITYWIDE | 5 | CONSTRUCTION TO 25% | 2015-04-13 | 2016-02-06 | 2015-03-16 | 2016-01-09
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW21 | WHEN AND WHERE HURRICANE SANDY - CITYWIDE | 6 | CONSTRUCTION TO 50% | 2016-02-07 | 2016-12-02 | 2016-01-10 | 2016-11-04
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW21 | WHEN AND WHERE HURRICANE SANDY - CITYWIDE | 7 | CONSTRUCTION TO 75% | 2016-12-03 | 2017-09-28 | 2016-11-05 | 2017-08-31
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW21 | WHEN AND WHERE HURRICANE SANDY - CITYWIDE | 8 | ORIGINAL EQUIP & FURNISHING | 2017-09-29 | 2017-12-27 | 2017-09-01 | 2017-11-29
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW21 | WHEN AND WHERE HURRICANE SANDY - CITYWIDE | 9 | SUBSTANTIAL COMPLETION | 2017-12-28 | 2018-02-25 | 2017-11-30 | 2018-01-28
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW21 | WHEN AND WHERE HURRICANE SANDY - CITYWIDE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-02-26 | 2018-03-27 | 2018-01-29 | 2021-06-30
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDISLND | HURRICANE SANDY DAMAGE ROCKAWAY BEACH ENTRY ISLANDS | 1 | PROJECT START | 2012-12-17 | 2012-12-17 | 2012-12-17 | 2012-12-17
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDISLND | HURRICANE SANDY DAMAGE ROCKAWAY BEACH ENTRY ISLANDS | 2 | DESIGN START | 2012-12-18 | 2012-12-20 | 2012-12-18 | 2012-12-20
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDISLND | HURRICANE SANDY DAMAGE ROCKAWAY BEACH ENTRY ISLANDS | 3 | DESIGN COMPLETION | 2012-12-21 | 2013-01-27 | 2012-12-21 | 2013-01-27
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDISLND | HURRICANE SANDY DAMAGE ROCKAWAY BEACH ENTRY ISLANDS | 4 | CONSTRUCTION START | 2013-01-28 | 2013-03-01 | 2013-01-28 | 2013-03-01
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDISLND | HURRICANE SANDY DAMAGE ROCKAWAY BEACH ENTRY ISLANDS | 5 | CONSTRUCTION COMPLETION | 2013-03-02 | 2015-08-24 | 2023-05-30 | 2024-05-31
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDPRFAB | HURRICANE SANDY DAMAGE BEACHFRONT RESTORATION PROJECT | 1 | PROJECT START | 2012-12-17 | 2012-12-17 | 2012-12-17 | 2012-12-17
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDPRFAB | HURRICANE SANDY DAMAGE BEACHFRONT RESTORATION PROJECT | 2 | DESIGN START | 2012-12-18 | 2012-12-20 | 2012-12-18 | 2012-12-20
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDPRFAB | HURRICANE SANDY DAMAGE BEACHFRONT RESTORATION PROJECT | 3 | DESIGN COMPLETION | 2012-12-21 | 2013-01-27 | 2012-12-21 | 2013-01-27
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDPRFAB | HURRICANE SANDY DAMAGE BEACHFRONT RESTORATION PROJECT | 4 | CONSTRUCTION START | 2013-01-28 | 2013-03-01 | 2013-01-28 | 2013-03-01
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDPRFAB | HURRICANE SANDY DAMAGE BEACHFRONT RESTORATION PROJECT | 5 | CONSTRUCTION COMPLETION | 2013-03-02 | 2015-08-30 | 2013-03-02 | 2026-06-30
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRENO | HURRCANE SANDY DAMAGE STATEN ISLAND BEACHES-VARIOUS | 1 | PROJECT START | 2012-12-17 | 2012-12-17 | 2012-12-17 | 2012-12-17
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRENO | HURRCANE SANDY DAMAGE STATEN ISLAND BEACHES-VARIOUS | 2 | DESIGN START | 2012-12-18 | 2012-12-20 | 2012-12-18 | 2012-12-20
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRENO | HURRCANE SANDY DAMAGE STATEN ISLAND BEACHES-VARIOUS | 3 | DESIGN COMPLETION | 2012-12-21 | 2013-01-27 | 2012-12-21 | 2013-01-27
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRENO | HURRCANE SANDY DAMAGE STATEN ISLAND BEACHES-VARIOUS | 4 | CONSTRUCTION START | 2013-01-28 | 2013-03-01 | 2013-01-28 | 2013-03-01
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRENO | HURRCANE SANDY DAMAGE STATEN ISLAND BEACHES-VARIOUS | 5 | CONSTRUCTION COMPLETION | 2013-03-02 | 2015-07-30 | 2022-12-14 | 2026-06-30
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRESEP | ESCR Early Package - Reconstruction of Lesec Composting Area | 1 | DEVELOP SCOPE | 2020-03-01 | 2020-05-29 | 2020-03-01 | 2020-05-29
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRESEP | ESCR Early Package - Reconstruction of Lesec Composting Area | 2 | PRELIMINARY DESIGN | 2020-05-30 | 2020-09-26 | 2020-05-30 | 2020-09-26
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRESEP | ESCR Early Package - Reconstruction of Lesec Composting Area | 3 | FINAL DESIGN | 2020-09-27 | 2021-03-25 | 2020-09-27 | 2021-03-25
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRESEP | ESCR Early Package - Reconstruction of Lesec Composting Area | 4 | BID AWARD AND REGISTER CONTRCT | 2021-03-26 | 2021-06-23 | 2021-03-26 | 2021-06-23
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRESEP | ESCR Early Package - Reconstruction of Lesec Composting Area | 5 | CONSTRUCTION TO 25% | 2021-06-24 | 2021-10-21 | 2021-06-24 | 2021-10-21
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRESEP | ESCR Early Package - Reconstruction of Lesec Composting Area | 6 | CONSTRUCTION TO 50% | 2021-10-22 | 2022-02-18 | 2021-10-22 | 2022-02-18
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRESEP | ESCR Early Package - Reconstruction of Lesec Composting Area | 7 | CONSTRUCTION TO 75% | 2022-02-19 | 2022-06-18 | 2022-02-19 | 2022-06-18
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRESEP | ESCR Early Package - Reconstruction of Lesec Composting Area | 8 | ORIGINAL EQUIP & FURNISHING | 2022-06-19 | 2022-09-16 | 2022-06-19 | 2022-09-16
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRESEP | ESCR Early Package - Reconstruction of Lesec Composting Area | 9 | SUBSTANTIAL COMPLETION | 2022-09-17 | 2022-11-15 | 2022-09-17 | 2022-11-15
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRESEP | ESCR Early Package - Reconstruction of Lesec Composting Area | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-11-16 | 2023-12-15 | 2022-11-16 | 2023-12-15
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRESM1 | Citywide Resiliency Measures, ESCR, Project Area 1 | 1 | DEVELOP SCOPE | 2018-03-01 | 2018-05-29 | 2018-03-01 | 2018-05-29
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRESM1 | Citywide Resiliency Measures, ESCR, Project Area 1 | 2 | PRELIMINARY DESIGN | 2018-05-30 | 2018-09-26 | 2018-05-30 | 2018-09-26
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRESM1 | Citywide Resiliency Measures, ESCR, Project Area 1 | 3 | FINAL DESIGN | 2018-09-27 | 2019-03-25 | 2018-09-27 | 2019-03-25
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRESM1 | Citywide Resiliency Measures, ESCR, Project Area 1 | 4 | BID AWARD AND REGISTER CONTRCT | 2019-03-26 | 2019-06-23 | 2019-03-26 | 2019-06-23
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRESM1 | Citywide Resiliency Measures, ESCR, Project Area 1 | 5 | CONSTRUCTION TO 25% | 2019-06-24 | 2019-10-21 | 2019-06-24 | 2019-10-21
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRESM1 | Citywide Resiliency Measures, ESCR, Project Area 1 | 6 | CONSTRUCTION TO 50% | 2019-10-22 | 2020-02-18 | 2019-10-22 | 2020-02-18
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRESM1 | Citywide Resiliency Measures, ESCR, Project Area 1 | 7 | CONSTRUCTION TO 75% | 2020-02-19 | 2020-06-17 | 2020-02-19 | 2020-06-17
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRESM1 | Citywide Resiliency Measures, ESCR, Project Area 1 | 8 | ORIGINAL EQUIP & FURNISHING | 2020-06-18 | 2020-09-15 | 2020-06-18 | 2020-09-15
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRESM1 | Citywide Resiliency Measures, ESCR, Project Area 1 | 9 | SUBSTANTIAL COMPLETION | 2020-09-16 | 2020-11-14 | 2020-09-16 | 2020-11-14
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRESM1 | Citywide Resiliency Measures, ESCR, Project Area 1 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-11-15 | 2020-12-14 | 2020-11-15 | 2025-06-30
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRESM2 | Citywide Reiliency Measures, ESCR, Project Area 2 | 1 | DEVELOP SCOPE | 2014-12-01 | 2015-02-28 | 2014-12-01 | 2015-02-28
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRESM2 | Citywide Reiliency Measures, ESCR, Project Area 2 | 2 | PRELIMINARY DESIGN | 2015-03-01 | 2015-06-28 | 2015-03-01 | 2015-06-28
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRESM2 | Citywide Reiliency Measures, ESCR, Project Area 2 | 3 | FINAL DESIGN | 2015-06-29 | 2015-12-25 | 2015-06-29 | 2015-12-25
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRESM2 | Citywide Reiliency Measures, ESCR, Project Area 2 | 4 | BID AWARD AND REGISTER CONTRCT | 2015-12-26 | 2016-03-24 | 2015-12-26 | 2016-03-24
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRESM2 | Citywide Reiliency Measures, ESCR, Project Area 2 | 5 | CONSTRUCTION TO 25% | 2016-03-25 | 2016-07-22 | 2016-03-25 | 2016-07-22
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRESM2 | Citywide Reiliency Measures, ESCR, Project Area 2 | 6 | CONSTRUCTION TO 50% | 2016-07-23 | 2016-11-19 | 2016-07-23 | 2016-11-19
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRESM2 | Citywide Reiliency Measures, ESCR, Project Area 2 | 7 | CONSTRUCTION TO 75% | 2016-11-20 | 2017-03-19 | 2016-11-20 | 2017-03-19
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRESM2 | Citywide Reiliency Measures, ESCR, Project Area 2 | 8 | ORIGINAL EQUIP & FURNISHING | 2017-03-20 | 2017-06-17 | 2017-03-20 | 2017-06-17
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRESM2 | Citywide Reiliency Measures, ESCR, Project Area 2 | 9 | SUBSTANTIAL COMPLETION | 2017-06-18 | 2017-08-16 | 2017-06-18 | 2017-08-16
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRESM2 | Citywide Reiliency Measures, ESCR, Project Area 2 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-08-17 | 2025-06-30 | 2017-08-17 | 2025-06-30
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRESPC | Citywide Reiliency Measures, ESCR, Parallel Conveyance | 1 | DEVELOP SCOPE | 2018-03-01 | 2018-05-29 | 2018-03-01 | 2018-05-29
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRESPC | Citywide Reiliency Measures, ESCR, Parallel Conveyance | 2 | PRELIMINARY DESIGN | 2018-05-30 | 2018-09-26 | 2018-05-30 | 2018-09-26
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRESPC | Citywide Reiliency Measures, ESCR, Parallel Conveyance | 3 | FINAL DESIGN | 2018-09-27 | 2019-03-25 | 2018-09-27 | 2019-03-25
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRESPC | Citywide Reiliency Measures, ESCR, Parallel Conveyance | 4 | BID AWARD AND REGISTER CONTRCT | 2019-03-26 | 2019-06-23 | 2019-03-26 | 2019-06-23
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRESPC | Citywide Reiliency Measures, ESCR, Parallel Conveyance | 5 | CONSTRUCTION TO 25% | 2019-06-24 | 2019-10-21 | 2019-06-24 | 2019-10-21
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRESPC | Citywide Reiliency Measures, ESCR, Parallel Conveyance | 6 | CONSTRUCTION TO 50% | 2019-10-22 | 2020-02-18 | 2019-10-22 | 2020-02-18
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRESPC | Citywide Reiliency Measures, ESCR, Parallel Conveyance | 7 | CONSTRUCTION TO 75% | 2020-02-19 | 2020-06-17 | 2020-02-19 | 2020-06-17
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRESPC | Citywide Reiliency Measures, ESCR, Parallel Conveyance | 8 | ORIGINAL EQUIP & FURNISHING | 2020-06-18 | 2020-09-15 | 2020-06-18 | 2020-09-15
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRESPC | Citywide Reiliency Measures, ESCR, Parallel Conveyance | 9 | SUBSTANTIAL COMPLETION | 2020-09-16 | 2020-11-14 | 2020-09-16 | 2020-11-14
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRESPC | Citywide Reiliency Measures, ESCR, Parallel Conveyance | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-11-15 | 2024-06-30 | 2020-11-15 | 2024-06-30
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDTWOBR | CITYWIDE RESILENCY MEASURES-Lower Manhattan Two Bridges SIRR | 1 | DEVELOP SCOPE | 2017-03-01 | 2017-05-29 | 2017-03-01 | 2017-05-29
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDTWOBR | CITYWIDE RESILENCY MEASURES-Lower Manhattan Two Bridges SIRR | 2 | PRELIMINARY DESIGN | 2017-05-30 | 2017-09-26 | 2017-05-30 | 2017-09-26
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDTWOBR | CITYWIDE RESILENCY MEASURES-Lower Manhattan Two Bridges SIRR | 3 | FINAL DESIGN | 2017-09-27 | 2018-03-25 | 2017-09-27 | 2018-03-25
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDTWOBR | CITYWIDE RESILENCY MEASURES-Lower Manhattan Two Bridges SIRR | 4 | BID AWARD AND REGISTER CONTRCT | 2018-03-26 | 2018-06-23 | 2018-03-26 | 2018-06-23
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDTWOBR | CITYWIDE RESILENCY MEASURES-Lower Manhattan Two Bridges SIRR | 5 | CONSTRUCTION TO 25% | 2018-06-24 | 2018-10-21 | 2018-06-24 | 2018-10-21
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDTWOBR | CITYWIDE RESILENCY MEASURES-Lower Manhattan Two Bridges SIRR | 6 | CONSTRUCTION TO 50% | 2018-10-22 | 2019-02-18 | 2018-10-22 | 2019-02-18
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDTWOBR | CITYWIDE RESILENCY MEASURES-Lower Manhattan Two Bridges SIRR | 7 | CONSTRUCTION TO 75% | 2019-02-19 | 2019-06-18 | 2019-02-19 | 2019-06-18
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDTWOBR | CITYWIDE RESILENCY MEASURES-Lower Manhattan Two Bridges SIRR | 8 | ORIGINAL EQUIP & FURNISHING | 2019-06-19 | 2019-09-16 | 2019-06-19 | 2019-09-16
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDTWOBR | CITYWIDE RESILENCY MEASURES-Lower Manhattan Two Bridges SIRR | 9 | SUBSTANTIAL COMPLETION | 2019-09-17 | 2019-11-15 | 2019-09-17 | 2019-11-15
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDTWOBR | CITYWIDE RESILENCY MEASURES-Lower Manhattan Two Bridges SIRR | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-11-16 | 2025-06-30 | 2019-11-16 | 2025-06-30
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-813 | WATER MAIN WORK IN JEWEL STREETS AREA | 1 | DEVELOP SCOPE | 2007-06-30 | 2008-03-25 | 2007-06-30 | 2007-09-27
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-813 | WATER MAIN WORK IN JEWEL STREETS AREA | 2 | PRELIMINARY DESIGN | 2008-03-26 | 2009-03-20 | 2007-09-28 | 2008-01-25
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-813 | WATER MAIN WORK IN JEWEL STREETS AREA | 3 | FINAL DESIGN | 2009-03-21 | 2010-09-11 | 2008-01-26 | 2008-07-23
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-813 | WATER MAIN WORK IN JEWEL STREETS AREA | 4 | BID AWARD AND REGISTER CONTRCT | 2010-09-12 | 2011-06-08 | 2022-03-28 | 2022-06-25
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-813 | WATER MAIN WORK IN JEWEL STREETS AREA | 5 | CONSTRUCTION TO 25% | 2011-06-09 | 2012-06-02 | 2022-06-26 | 2022-06-25
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-813 | WATER MAIN WORK IN JEWEL STREETS AREA | 6 | CONSTRUCTION TO 50% | 2012-06-03 | 2013-05-28 | 2022-06-26 | 2022-06-25
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-813 | WATER MAIN WORK IN JEWEL STREETS AREA | 7 | CONSTRUCTION TO 75% | 2013-05-29 | 2014-05-23 | 2022-06-26 | 2022-06-25
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-813 | WATER MAIN WORK IN JEWEL STREETS AREA | 8 | ORIGINAL EQUIP & FURNISHING | 2014-05-24 | 2015-02-17 | 2022-06-26 | 2022-06-25
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-813 | WATER MAIN WORK IN JEWEL STREETS AREA | 9 | SUBSTANTIAL COMPLETION | 2015-02-18 | 2015-08-16 | 2022-06-26 | 2022-06-25
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-813 | WATER MAIN WORK IN JEWEL STREETS AREA | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-08-17 | 2015-11-14 | 2024-05-27 | 2027-06-30
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SEBLQX01 | Reconstruction of existing sewers from back log QN & BX | 1 | DEVELOP SCOPE | 2022-06-01 | 2022-08-29 | 2022-06-01 | 2022-08-29
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SEBLQX01 | Reconstruction of existing sewers from back log QN & BX | 2 | PRELIMINARY DESIGN | 2022-08-30 | 2022-12-27 | 2022-08-30 | 2022-12-27
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SEBLQX01 | Reconstruction of existing sewers from back log QN & BX | 3 | FINAL DESIGN | 2022-12-28 | 2023-06-25 | 2022-12-28 | 2023-06-25
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SEBLQX01 | Reconstruction of existing sewers from back log QN & BX | 4 | BID AWARD AND REGISTER CONTRCT | 2023-06-26 | 2023-09-23 | 2023-06-26 | 2023-09-23
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SEBLQX01 | Reconstruction of existing sewers from back log QN & BX | 5 | CONSTRUCTION TO 25% | 2023-09-24 | 2024-01-21 | 2023-09-24 | 2024-01-21
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SEBLQX01 | Reconstruction of existing sewers from back log QN & BX | 6 | CONSTRUCTION TO 50% | 2024-01-22 | 2024-05-20 | 2024-01-22 | 2024-05-20
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SEBLQX01 | Reconstruction of existing sewers from back log QN & BX | 7 | CONSTRUCTION TO 75% | 2024-05-21 | 2024-09-17 | 2024-05-21 | 2024-09-17
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SEBLQX01 | Reconstruction of existing sewers from back log QN & BX | 8 | ORIGINAL EQUIP & FURNISHING | 2024-09-18 | 2024-12-16 | 2024-09-18 | 2024-12-16
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SEBLQX01 | Reconstruction of existing sewers from back log QN & BX | 9 | SUBSTANTIAL COMPLETION | 2024-12-17 | 2025-02-14 | 2024-12-17 | 2025-02-14
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SEBLQX01 | Reconstruction of existing sewers from back log QN & BX | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-02-15 | 2025-03-16 | 2025-02-15 | 2025-03-16
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SEC20004V | Emergency Reconstruction of Sewers | 1 | DEVELOP SCOPE | 2017-03-01 | 2017-05-29 | 2017-03-01 | 2017-05-29
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SEC20004V | Emergency Reconstruction of Sewers | 2 | PRELIMINARY DESIGN | 2017-05-30 | 2017-09-26 | 2017-05-30 | 2017-09-26
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SEC20004V | Emergency Reconstruction of Sewers | 3 | FINAL DESIGN | 2017-09-27 | 2018-03-25 | 2017-09-27 | 2018-03-25
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SEC20004V | Emergency Reconstruction of Sewers | 4 | BID AWARD AND REGISTER CONTRCT | 2018-03-26 | 2018-06-23 | 2018-03-26 | 2018-06-23
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SEC20004V | Emergency Reconstruction of Sewers | 5 | CONSTRUCTION TO 25% | 2018-06-24 | 2018-10-21 | 2018-06-24 | 2018-10-21
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SEC20004V | Emergency Reconstruction of Sewers | 6 | CONSTRUCTION TO 50% | 2018-10-22 | 2019-02-18 | 2018-10-22 | 2019-02-18
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SEC20004V | Emergency Reconstruction of Sewers | 7 | CONSTRUCTION TO 75% | 2019-02-19 | 2019-06-18 | 2019-02-19 | 2019-06-18
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SEC20004V | Emergency Reconstruction of Sewers | 8 | ORIGINAL EQUIP & FURNISHING | 2019-06-19 | 2019-09-16 | 2019-06-19 | 2019-09-16
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SEC20004V | Emergency Reconstruction of Sewers | 9 | SUBSTANTIAL COMPLETION | 2019-09-17 | 2019-11-15 | 2019-09-17 | 2019-11-15
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SEC20004V | Emergency Reconstruction of Sewers | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-11-16 | 2019-12-15 | 2019-11-16 | 2019-12-15
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SEC20004W | Emergency Reconstruction of Sewers, Citywide | 1 | DEVELOP SCOPE | 2020-03-09 | 2020-06-06 | 2020-03-09 | 2020-06-06
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SEC20004W | Emergency Reconstruction of Sewers, Citywide | 2 | PRELIMINARY DESIGN | 2020-06-07 | 2020-10-04 | 2020-06-07 | 2020-10-04
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SEC20004W | Emergency Reconstruction of Sewers, Citywide | 3 | FINAL DESIGN | 2020-10-05 | 2021-04-02 | 2020-10-05 | 2021-04-02
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SEC20004W | Emergency Reconstruction of Sewers, Citywide | 4 | BID AWARD AND REGISTER CONTRCT | 2021-04-03 | 2021-07-01 | 2021-04-03 | 2021-07-01
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SEC20004W | Emergency Reconstruction of Sewers, Citywide | 5 | CONSTRUCTION TO 25% | 2021-07-02 | 2021-10-29 | 2021-07-02 | 2021-10-29
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SEC20004W | Emergency Reconstruction of Sewers, Citywide | 6 | CONSTRUCTION TO 50% | 2021-10-30 | 2022-02-26 | 2021-10-30 | 2022-02-26
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SEC20004W | Emergency Reconstruction of Sewers, Citywide | 7 | CONSTRUCTION TO 75% | 2022-02-27 | 2022-06-26 | 2022-02-27 | 2022-06-26
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SEC20004W | Emergency Reconstruction of Sewers, Citywide | 8 | ORIGINAL EQUIP & FURNISHING | 2022-06-27 | 2022-09-24 | 2022-06-27 | 2022-09-24
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SEC20004W | Emergency Reconstruction of Sewers, Citywide | 9 | SUBSTANTIAL COMPLETION | 2022-09-25 | 2022-11-23 | 2022-09-25 | 2022-11-23
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SEC20004W | Emergency Reconstruction of Sewers, Citywide | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-11-24 | 2024-09-27 | 2022-11-24 | 2024-09-27
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-GUN-20 | Emergency Guniting of Sewers, Citywide | 1 | DEVELOP SCOPE | 2021-06-01 | 2021-08-29 | 2021-06-01 | 2021-08-29
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-GUN-20 | Emergency Guniting of Sewers, Citywide | 2 | PRELIMINARY DESIGN | 2021-08-30 | 2021-12-27 | 2021-08-30 | 2021-12-27
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-GUN-20 | Emergency Guniting of Sewers, Citywide | 3 | FINAL DESIGN | 2021-12-28 | 2022-06-25 | 2021-12-28 | 2022-06-25
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-GUN-20 | Emergency Guniting of Sewers, Citywide | 4 | BID AWARD AND REGISTER CONTRCT | 2022-06-26 | 2022-09-23 | 2022-06-26 | 2022-09-23
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-GUN-20 | Emergency Guniting of Sewers, Citywide | 5 | CONSTRUCTION TO 25% | 2022-09-24 | 2023-01-21 | 2022-09-24 | 2023-01-21
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-GUN-20 | Emergency Guniting of Sewers, Citywide | 6 | CONSTRUCTION TO 50% | 2023-01-22 | 2023-05-21 | 2023-01-22 | 2023-05-21
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-GUN-20 | Emergency Guniting of Sewers, Citywide | 7 | CONSTRUCTION TO 75% | 2023-05-22 | 2023-09-18 | 2023-05-22 | 2023-09-18
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-GUN-20 | Emergency Guniting of Sewers, Citywide | 8 | ORIGINAL EQUIP & FURNISHING | 2023-09-19 | 2023-12-17 | 2023-09-19 | 2023-12-17
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-GUN-20 | Emergency Guniting of Sewers, Citywide | 9 | SUBSTANTIAL COMPLETION | 2023-12-18 | 2024-02-15 | 2023-12-18 | 2024-02-15
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-GUN-20 | Emergency Guniting of Sewers, Citywide | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-02-16 | 2024-03-16 | 2024-02-16 | 2024-03-16
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SELCDDC09 | SEWER LINING CONTRACT, CITYWIDE | 1 | DEVELOP SCOPE | 2017-03-01 | 2017-05-29 | 2017-03-01 | 2017-05-29
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SELCDDC09 | SEWER LINING CONTRACT, CITYWIDE | 2 | PRELIMINARY DESIGN | 2017-05-30 | 2017-09-26 | 2017-05-30 | 2017-09-26
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SELCDDC09 | SEWER LINING CONTRACT, CITYWIDE | 3 | FINAL DESIGN | 2017-09-27 | 2018-03-25 | 2017-09-27 | 2018-03-25
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SELCDDC09 | SEWER LINING CONTRACT, CITYWIDE | 4 | BID AWARD AND REGISTER CONTRCT | 2018-03-26 | 2018-06-23 | 2018-03-26 | 2018-06-23
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SELCDDC09 | SEWER LINING CONTRACT, CITYWIDE | 5 | CONSTRUCTION TO 25% | 2018-06-24 | 2018-10-21 | 2018-06-24 | 2018-10-21
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SELCDDC09 | SEWER LINING CONTRACT, CITYWIDE | 6 | CONSTRUCTION TO 50% | 2018-10-22 | 2019-02-18 | 2018-10-22 | 2019-02-18
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SELCDDC09 | SEWER LINING CONTRACT, CITYWIDE | 7 | CONSTRUCTION TO 75% | 2019-02-19 | 2019-06-18 | 2019-02-19 | 2019-06-18
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SELCDDC09 | SEWER LINING CONTRACT, CITYWIDE | 8 | ORIGINAL EQUIP & FURNISHING | 2019-06-19 | 2019-09-16 | 2019-06-19 | 2019-09-16
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SELCDDC09 | SEWER LINING CONTRACT, CITYWIDE | 9 | SUBSTANTIAL COMPLETION | 2019-09-17 | 2019-11-15 | 2019-09-17 | 2019-11-15
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SELCDDC09 | SEWER LINING CONTRACT, CITYWIDE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-11-16 | 2019-12-15 | 2019-11-16 | 2022-06-30
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SELCDDC10 | SEWER LINING CONTRACT, CITYWIDE | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-08-29 | 2020-06-01 | 2020-08-29
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SELCDDC10 | SEWER LINING CONTRACT, CITYWIDE | 2 | PRELIMINARY DESIGN | 2020-08-30 | 2020-12-27 | 2020-08-30 | 2020-12-27
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SELCDDC10 | SEWER LINING CONTRACT, CITYWIDE | 3 | FINAL DESIGN | 2020-12-28 | 2021-06-25 | 2020-12-28 | 2021-06-25
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SELCDDC10 | SEWER LINING CONTRACT, CITYWIDE | 4 | BID AWARD AND REGISTER CONTRCT | 2021-06-26 | 2021-09-23 | 2021-06-26 | 2021-09-23
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SELCDDC10 | SEWER LINING CONTRACT, CITYWIDE | 5 | CONSTRUCTION TO 25% | 2021-09-24 | 2022-01-21 | 2021-09-24 | 2022-01-21
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SELCDDC10 | SEWER LINING CONTRACT, CITYWIDE | 6 | CONSTRUCTION TO 50% | 2022-01-22 | 2022-05-21 | 2022-01-22 | 2022-05-21
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SELCDDC10 | SEWER LINING CONTRACT, CITYWIDE | 7 | CONSTRUCTION TO 75% | 2022-05-22 | 2022-09-18 | 2022-05-22 | 2022-09-18
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SELCDDC10 | SEWER LINING CONTRACT, CITYWIDE | 8 | ORIGINAL EQUIP & FURNISHING | 2022-09-19 | 2022-12-17 | 2022-09-19 | 2022-12-17
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SELCDDC10 | SEWER LINING CONTRACT, CITYWIDE | 9 | SUBSTANTIAL COMPLETION | 2022-12-18 | 2023-02-15 | 2022-12-18 | 2023-02-15
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SELCDDC10 | SEWER LINING CONTRACT, CITYWIDE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-02-16 | 2023-03-17 | 2023-02-16 | 2023-03-17
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SETVDDC16 | CLEANING AND TELEVISING OF SEWERS BY DDC | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-08-29 | 2020-06-01 | 2020-08-29
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SETVDDC16 | CLEANING AND TELEVISING OF SEWERS BY DDC | 2 | PRELIMINARY DESIGN | 2020-08-30 | 2020-12-27 | 2020-08-30 | 2020-12-27
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SETVDDC16 | CLEANING AND TELEVISING OF SEWERS BY DDC | 3 | FINAL DESIGN | 2020-12-28 | 2021-06-25 | 2020-12-28 | 2021-06-25
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SETVDDC16 | CLEANING AND TELEVISING OF SEWERS BY DDC | 4 | BID AWARD AND REGISTER CONTRCT | 2021-06-26 | 2021-09-23 | 2021-06-26 | 2021-09-23
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SETVDDC16 | CLEANING AND TELEVISING OF SEWERS BY DDC | 5 | CONSTRUCTION TO 25% | 2021-09-24 | 2022-01-21 | 2021-09-24 | 2022-01-21
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SETVDDC16 | CLEANING AND TELEVISING OF SEWERS BY DDC | 6 | CONSTRUCTION TO 50% | 2022-01-22 | 2022-05-21 | 2022-01-22 | 2022-05-21
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SETVDDC16 | CLEANING AND TELEVISING OF SEWERS BY DDC | 7 | CONSTRUCTION TO 75% | 2022-05-22 | 2022-09-18 | 2022-05-22 | 2022-09-18
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SETVDDC16 | CLEANING AND TELEVISING OF SEWERS BY DDC | 8 | ORIGINAL EQUIP & FURNISHING | 2022-09-19 | 2022-12-17 | 2022-09-19 | 2022-12-17
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SETVDDC16 | CLEANING AND TELEVISING OF SEWERS BY DDC | 9 | SUBSTANTIAL COMPLETION | 2022-12-18 | 2023-02-15 | 2022-12-18 | 2023-02-15
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SETVDDC16 | CLEANING AND TELEVISING OF SEWERS BY DDC | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-02-16 | 2023-03-17 | 2023-02-16 | 2023-03-17
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | WM-LC-17 | Citywide Lining Contract for Water Mains | 1 | DEVELOP SCOPE | 2016-03-01 | 2016-05-29 | 2016-03-01 | 2016-05-29
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | WM-LC-17 | Citywide Lining Contract for Water Mains | 2 | PRELIMINARY DESIGN | 2016-05-30 | 2016-09-26 | 2016-05-30 | 2016-09-26
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | WM-LC-17 | Citywide Lining Contract for Water Mains | 3 | FINAL DESIGN | 2016-09-27 | 2017-03-25 | 2016-09-27 | 2017-03-25
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | WM-LC-17 | Citywide Lining Contract for Water Mains | 4 | BID AWARD AND REGISTER CONTRCT | 2017-03-26 | 2017-06-23 | 2017-03-26 | 2017-06-23
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | WM-LC-17 | Citywide Lining Contract for Water Mains | 5 | CONSTRUCTION TO 25% | 2017-06-24 | 2017-10-21 | 2017-06-24 | 2017-10-21
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | WM-LC-17 | Citywide Lining Contract for Water Mains | 6 | CONSTRUCTION TO 50% | 2017-10-22 | 2018-02-18 | 2017-10-22 | 2018-02-18
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | WM-LC-17 | Citywide Lining Contract for Water Mains | 7 | CONSTRUCTION TO 75% | 2018-02-19 | 2018-06-18 | 2018-02-19 | 2018-06-18
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | WM-LC-17 | Citywide Lining Contract for Water Mains | 8 | ORIGINAL EQUIP & FURNISHING | 2018-06-19 | 2018-09-16 | 2018-06-19 | 2018-09-16
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | WM-LC-17 | Citywide Lining Contract for Water Mains | 9 | SUBSTANTIAL COMPLETION | 2018-09-17 | 2018-11-15 | 2018-09-17 | 2018-11-15
20201123 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | WM-LC-17 | Citywide Lining Contract for Water Mains | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-11-16 | 2018-12-15 | 2018-11-16 | 2023-06-01
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264CADA | CITYWIDE COURTS ADA LUMP SUM | 1 | DEVELOP SCOPE | 2022-06-01 | 2022-08-29 | 2022-06-01 | 2022-08-29
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264CADA | CITYWIDE COURTS ADA LUMP SUM | 2 | PRELIMINARY DESIGN | 2022-08-30 | 2022-12-27 | 2022-08-30 | 2022-12-27
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264CADA | CITYWIDE COURTS ADA LUMP SUM | 3 | FINAL DESIGN | 2022-12-28 | 2023-06-25 | 2022-12-28 | 2023-06-25
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264CADA | CITYWIDE COURTS ADA LUMP SUM | 4 | BID AWARD AND REGISTER CONTRCT | 2023-06-26 | 2023-09-23 | 2023-06-26 | 2023-09-23
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264CADA | CITYWIDE COURTS ADA LUMP SUM | 5 | CONSTRUCTION TO 25% | 2024-09-24 | 2025-01-21 | 2024-09-24 | 2025-01-21
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264CADA | CITYWIDE COURTS ADA LUMP SUM | 6 | CONSTRUCTION TO 50% | 2026-01-22 | 2026-05-21 | 2026-01-22 | 2026-05-21
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264CADA | CITYWIDE COURTS ADA LUMP SUM | 7 | CONSTRUCTION TO 75% | 2027-05-22 | 2027-09-18 | 2027-05-22 | 2027-09-18
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264CADA | CITYWIDE COURTS ADA LUMP SUM | 8 | ORIGINAL EQUIP & FURNISHING | 2027-09-19 | 2027-12-17 | 2027-09-19 | 2027-12-17
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264CADA | CITYWIDE COURTS ADA LUMP SUM | 9 | SUBSTANTIAL COMPLETION | 2027-12-18 | 2028-02-15 | 2027-12-18 | 2028-02-15
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264CADA | CITYWIDE COURTS ADA LUMP SUM | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2028-02-16 | 2028-03-16 | 2028-02-16 | 2028-03-16
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264DCAS | REHABILITATION OF VARIOUS COURT FACILITES | 1 | DEVELOP SCOPE | 2011-03-18 | 2011-06-15 | 2011-03-18 | 2011-06-15
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264DCAS | REHABILITATION OF VARIOUS COURT FACILITES | 2 | PRELIMINARY DESIGN | 2011-06-16 | 2012-06-09 | 2011-06-16 | 2012-06-09
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264DCAS | REHABILITATION OF VARIOUS COURT FACILITES | 3 | FINAL DESIGN | 2012-06-10 | 2013-06-04 | 2012-06-10 | 2013-06-04
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264DCAS | REHABILITATION OF VARIOUS COURT FACILITES | 4 | BID AWARD AND REGISTER CONTRCT | 2013-06-05 | 2014-05-30 | 2013-06-05 | 2014-05-30
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264DCAS | REHABILITATION OF VARIOUS COURT FACILITES | 5 | CONSTRUCTION TO 25% | 2014-05-31 | 2015-05-25 | 2014-05-31 | 2015-05-25
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264DCAS | REHABILITATION OF VARIOUS COURT FACILITES | 6 | CONSTRUCTION TO 50% | 2015-05-26 | 2016-05-19 | 2015-05-26 | 2016-05-19
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264DCAS | REHABILITATION OF VARIOUS COURT FACILITES | 7 | CONSTRUCTION TO 75% | 2016-05-20 | 2017-05-14 | 2016-05-20 | 2017-05-14
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264DCAS | REHABILITATION OF VARIOUS COURT FACILITES | 8 | ORIGINAL EQUIP & FURNISHING | 2017-05-15 | 2018-05-09 | 2017-05-15 | 2018-05-09
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264DCAS | REHABILITATION OF VARIOUS COURT FACILITES | 9 | SUBSTANTIAL COMPLETION | 2018-05-10 | 2020-04-28 | 2018-05-10 | 2020-04-28
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264DCAS | REHABILITATION OF VARIOUS COURT FACILITES | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-04-29 | 2021-04-23 | 2020-04-29 | 2021-04-23
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-ADA | VARIOUS COURTS BUILDINGS - ADA WORK | 1 | DEVELOP SCOPE | 2022-06-01 | 2022-08-29 | 2022-06-01 | 2022-08-29
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-ADA | VARIOUS COURTS BUILDINGS - ADA WORK | 2 | PRELIMINARY DESIGN | 2022-08-30 | 2022-12-27 | 2022-08-30 | 2022-12-27
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-ADA | VARIOUS COURTS BUILDINGS - ADA WORK | 3 | FINAL DESIGN | 2022-12-28 | 2023-06-25 | 2022-12-28 | 2023-06-25
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-ADA | VARIOUS COURTS BUILDINGS - ADA WORK | 4 | BID AWARD AND REGISTER CONTRCT | 2023-06-26 | 2023-09-23 | 2023-06-26 | 2023-09-23
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-ADA | VARIOUS COURTS BUILDINGS - ADA WORK | 5 | CONSTRUCTION TO 25% | 2023-09-24 | 2024-01-21 | 2023-09-24 | 2024-01-21
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-ADA | VARIOUS COURTS BUILDINGS - ADA WORK | 6 | CONSTRUCTION TO 50% | 2024-01-22 | 2024-05-20 | 2024-01-22 | 2024-05-20
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-ADA | VARIOUS COURTS BUILDINGS - ADA WORK | 7 | CONSTRUCTION TO 75% | 2024-05-21 | 2024-09-17 | 2024-05-21 | 2024-09-17
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-ADA | VARIOUS COURTS BUILDINGS - ADA WORK | 8 | ORIGINAL EQUIP & FURNISHING | 2024-09-18 | 2024-12-16 | 2024-09-18 | 2024-12-16
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-ADA | VARIOUS COURTS BUILDINGS - ADA WORK | 9 | SUBSTANTIAL COMPLETION | 2024-12-17 | 2025-02-14 | 2024-12-17 | 2025-02-14
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-ADA | VARIOUS COURTS BUILDINGS - ADA WORK | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-02-15 | 2025-03-16 | 2025-02-15 | 2025-03-16
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-HVAC | VARIOUS PUBLIC BUILDINGS - COURTS HVAC UPGRADES | 1 | DEVELOP SCOPE | 2024-06-01 | 2024-08-29 | 2024-06-01 | 2024-08-29
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-HVAC | VARIOUS PUBLIC BUILDINGS - COURTS HVAC UPGRADES | 2 | PRELIMINARY DESIGN | 2024-08-30 | 2024-12-27 | 2024-08-30 | 2024-12-27
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-HVAC | VARIOUS PUBLIC BUILDINGS - COURTS HVAC UPGRADES | 3 | FINAL DESIGN | 2024-12-28 | 2025-06-25 | 2024-12-28 | 2025-06-25
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-HVAC | VARIOUS PUBLIC BUILDINGS - COURTS HVAC UPGRADES | 4 | BID AWARD AND REGISTER CONTRCT | 2025-06-26 | 2025-09-23 | 2025-06-26 | 2025-09-23
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-HVAC | VARIOUS PUBLIC BUILDINGS - COURTS HVAC UPGRADES | 5 | CONSTRUCTION TO 25% | 2025-09-24 | 2026-01-21 | 2025-09-24 | 2026-01-21
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-HVAC | VARIOUS PUBLIC BUILDINGS - COURTS HVAC UPGRADES | 6 | CONSTRUCTION TO 50% | 2026-01-22 | 2026-05-21 | 2026-01-22 | 2026-05-21
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-HVAC | VARIOUS PUBLIC BUILDINGS - COURTS HVAC UPGRADES | 7 | CONSTRUCTION TO 75% | 2026-05-22 | 2026-09-18 | 2026-05-22 | 2026-09-18
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-HVAC | VARIOUS PUBLIC BUILDINGS - COURTS HVAC UPGRADES | 8 | ORIGINAL EQUIP & FURNISHING | 2026-09-19 | 2026-12-17 | 2026-09-19 | 2026-12-17
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-HVAC | VARIOUS PUBLIC BUILDINGS - COURTS HVAC UPGRADES | 9 | SUBSTANTIAL COMPLETION | 2026-12-18 | 2027-02-15 | 2026-12-18 | 2027-02-15
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-HVAC | VARIOUS PUBLIC BUILDINGS - COURTS HVAC UPGRADES | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2027-02-16 | 2027-03-17 | 2027-02-16 | 2027-03-17
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-LL5 | VARIOUS PUBLIC BUILDINGS - COURTS FIRE/LIFE SAFETY | 1 | DEVELOP SCOPE | 2024-06-01 | 2024-08-29 | 2024-06-01 | 2024-08-29
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-LL5 | VARIOUS PUBLIC BUILDINGS - COURTS FIRE/LIFE SAFETY | 2 | PRELIMINARY DESIGN | 2024-08-30 | 2024-12-27 | 2024-08-30 | 2024-12-27
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-LL5 | VARIOUS PUBLIC BUILDINGS - COURTS FIRE/LIFE SAFETY | 3 | FINAL DESIGN | 2024-12-28 | 2025-06-25 | 2024-12-28 | 2025-06-25
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-LL5 | VARIOUS PUBLIC BUILDINGS - COURTS FIRE/LIFE SAFETY | 4 | BID AWARD AND REGISTER CONTRCT | 2025-06-26 | 2025-09-23 | 2025-06-26 | 2025-09-23
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-LL5 | VARIOUS PUBLIC BUILDINGS - COURTS FIRE/LIFE SAFETY | 5 | CONSTRUCTION TO 25% | 2025-09-24 | 2026-01-21 | 2025-09-24 | 2026-01-21
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-LL5 | VARIOUS PUBLIC BUILDINGS - COURTS FIRE/LIFE SAFETY | 6 | CONSTRUCTION TO 50% | 2026-01-22 | 2026-05-21 | 2026-01-22 | 2026-05-21
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-LL5 | VARIOUS PUBLIC BUILDINGS - COURTS FIRE/LIFE SAFETY | 7 | CONSTRUCTION TO 75% | 2026-05-22 | 2026-09-18 | 2026-05-22 | 2026-09-18
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-LL5 | VARIOUS PUBLIC BUILDINGS - COURTS FIRE/LIFE SAFETY | 8 | ORIGINAL EQUIP & FURNISHING | 2026-09-19 | 2026-12-17 | 2026-09-19 | 2026-12-17
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-LL5 | VARIOUS PUBLIC BUILDINGS - COURTS FIRE/LIFE SAFETY | 9 | SUBSTANTIAL COMPLETION | 2026-12-18 | 2027-02-15 | 2026-12-18 | 2027-02-15
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-LL5 | VARIOUS PUBLIC BUILDINGS - COURTS FIRE/LIFE SAFETY | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2027-02-16 | 2027-03-17 | 2027-02-16 | 2027-03-17
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-LL5FS | VARIOUS PUBLIC BUILDINGS - COURTS FIRE SUPPRESSION | 1 | DEVELOP SCOPE | 2024-06-01 | 2024-08-29 | 2024-06-01 | 2024-08-29
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-LL5FS | VARIOUS PUBLIC BUILDINGS - COURTS FIRE SUPPRESSION | 2 | PRELIMINARY DESIGN | 2024-08-30 | 2024-12-27 | 2024-08-30 | 2024-12-27
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-LL5FS | VARIOUS PUBLIC BUILDINGS - COURTS FIRE SUPPRESSION | 3 | FINAL DESIGN | 2024-12-28 | 2025-06-25 | 2024-12-28 | 2025-06-25
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-LL5FS | VARIOUS PUBLIC BUILDINGS - COURTS FIRE SUPPRESSION | 4 | BID AWARD AND REGISTER CONTRCT | 2025-06-26 | 2025-09-23 | 2025-06-26 | 2025-09-23
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-LL5FS | VARIOUS PUBLIC BUILDINGS - COURTS FIRE SUPPRESSION | 5 | CONSTRUCTION TO 25% | 2025-09-24 | 2026-01-21 | 2025-09-24 | 2026-01-21
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-LL5FS | VARIOUS PUBLIC BUILDINGS - COURTS FIRE SUPPRESSION | 6 | CONSTRUCTION TO 50% | 2026-01-22 | 2026-05-21 | 2026-01-22 | 2026-05-21
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-LL5FS | VARIOUS PUBLIC BUILDINGS - COURTS FIRE SUPPRESSION | 7 | CONSTRUCTION TO 75% | 2026-05-22 | 2026-09-18 | 2026-05-22 | 2026-09-18
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-LL5FS | VARIOUS PUBLIC BUILDINGS - COURTS FIRE SUPPRESSION | 8 | ORIGINAL EQUIP & FURNISHING | 2026-09-19 | 2026-12-17 | 2026-09-19 | 2026-12-17
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-LL5FS | VARIOUS PUBLIC BUILDINGS - COURTS FIRE SUPPRESSION | 9 | SUBSTANTIAL COMPLETION | 2026-12-18 | 2027-02-15 | 2026-12-18 | 2027-02-15
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-LL5FS | VARIOUS PUBLIC BUILDINGS - COURTS FIRE SUPPRESSION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2027-02-16 | 2027-03-17 | 2027-02-16 | 2027-03-17
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW335ASB4 | VARIOUS PUBLIC BUILDINGS- ENVIRONMENTAL REMEDIATION | 1 | DEVELOP SCOPE | 2005-10-01 | 2005-12-29 | 2005-10-01 | 2005-12-29
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW335ASB4 | VARIOUS PUBLIC BUILDINGS- ENVIRONMENTAL REMEDIATION | 2 | PRELIMINARY DESIGN | 2005-12-30 | 2006-04-28 | 2005-12-30 | 2006-04-28
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW335ASB4 | VARIOUS PUBLIC BUILDINGS- ENVIRONMENTAL REMEDIATION | 3 | FINAL DESIGN | 2006-04-29 | 2006-10-25 | 2006-04-29 | 2006-10-25
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW335ASB4 | VARIOUS PUBLIC BUILDINGS- ENVIRONMENTAL REMEDIATION | 4 | BID AWARD AND REGISTER CONTRCT | 2006-10-26 | 2007-01-23 | 2006-10-26 | 2007-01-23
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW335ASB4 | VARIOUS PUBLIC BUILDINGS- ENVIRONMENTAL REMEDIATION | 5 | CONSTRUCTION TO 25% | 2007-01-24 | 2009-09-09 | 2007-01-24 | 2009-09-09
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW335ASB4 | VARIOUS PUBLIC BUILDINGS- ENVIRONMENTAL REMEDIATION | 6 | CONSTRUCTION TO 50% | 2009-09-10 | 2012-04-26 | 2022-06-01 | 2022-10-29
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW335ASB4 | VARIOUS PUBLIC BUILDINGS- ENVIRONMENTAL REMEDIATION | 7 | CONSTRUCTION TO 75% | 2012-04-27 | 2014-12-12 | 2022-10-30 | 2025-06-15
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW335ASB4 | VARIOUS PUBLIC BUILDINGS- ENVIRONMENTAL REMEDIATION | 8 | ORIGINAL EQUIP & FURNISHING | 2014-12-13 | 2015-12-07 | 2025-06-16 | 2026-06-10
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW335ASB4 | VARIOUS PUBLIC BUILDINGS- ENVIRONMENTAL REMEDIATION | 9 | SUBSTANTIAL COMPLETION | 2015-12-08 | 2016-12-01 | 2026-06-11 | 2027-06-05
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW335ASB4 | VARIOUS PUBLIC BUILDINGS- ENVIRONMENTAL REMEDIATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-12-02 | 2016-12-31 | 2027-06-06 | 2027-07-05
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW340EMAC | BOARD OF ELECTIONS | 1 | DEVELOP SCOPE | 2019-06-01 | 2019-08-29 | 2019-06-01 | 2019-08-29
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW340EMAC | BOARD OF ELECTIONS | 2 | PRELIMINARY DESIGN | 2019-08-30 | 2019-12-27 | 2019-08-30 | 2019-12-27
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW340EMAC | BOARD OF ELECTIONS | 3 | FINAL DESIGN | 2019-12-28 | 2020-06-24 | 2019-12-28 | 2020-06-24
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW340EMAC | BOARD OF ELECTIONS | 4 | BID AWARD AND REGISTER CONTRCT | 2020-06-25 | 2020-09-22 | 2020-06-25 | 2020-09-22
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW340EMAC | BOARD OF ELECTIONS | 5 | CONSTRUCTION TO 25% | 2023-09-23 | 2026-05-24 | 2023-09-23 | 2026-05-24
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW340EMAC | BOARD OF ELECTIONS | 6 | CONSTRUCTION TO 50% | 2026-05-25 | 2026-09-21 | 2026-05-25 | 2026-09-21
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW340EMAC | BOARD OF ELECTIONS | 7 | CONSTRUCTION TO 75% | 2026-09-22 | 2027-01-19 | 2026-09-22 | 2027-01-19
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW340EMAC | BOARD OF ELECTIONS | 8 | ORIGINAL EQUIP & FURNISHING | 2027-01-20 | 2027-04-19 | 2027-01-20 | 2027-04-19
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW340EMAC | BOARD OF ELECTIONS | 9 | SUBSTANTIAL COMPLETION | 2027-04-20 | 2027-06-18 | 2027-04-20 | 2027-06-18
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW340EMAC | BOARD OF ELECTIONS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2027-06-19 | 2027-07-18 | 2027-06-19 | 2027-07-18
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77CJC | Community Justice Center | 1 | DEVELOP SCOPE | 2017-01-01 | 2017-03-31 | 2025-06-01 | 2025-08-29
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77CJC | Community Justice Center | 2 | PRELIMINARY DESIGN | 2017-04-01 | 2017-07-29 | 2025-08-30 | 2025-12-27
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77CJC | Community Justice Center | 3 | FINAL DESIGN | 2017-07-30 | 2018-01-25 | 2025-12-28 | 2026-06-25
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77CJC | Community Justice Center | 4 | BID AWARD AND REGISTER CONTRCT | 2018-01-26 | 2018-04-25 | 2026-06-26 | 2026-09-23
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77CJC | Community Justice Center | 5 | CONSTRUCTION TO 25% | 2018-04-26 | 2018-08-23 | 2026-09-24 | 2027-01-21
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77CJC | Community Justice Center | 6 | CONSTRUCTION TO 50% | 2018-08-24 | 2018-12-21 | 2027-01-22 | 2027-05-21
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77CJC | Community Justice Center | 7 | CONSTRUCTION TO 75% | 2018-12-22 | 2019-04-20 | 2027-05-22 | 2027-09-18
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77CJC | Community Justice Center | 8 | ORIGINAL EQUIP & FURNISHING | 2019-04-21 | 2019-07-19 | 2027-09-19 | 2027-12-17
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77CJC | Community Justice Center | 9 | SUBSTANTIAL COMPLETION | 2019-07-20 | 2019-09-17 | 2027-12-18 | 2028-02-15
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77CJC | Community Justice Center | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-18 | 2019-10-17 | 2028-02-16 | 2028-03-16
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77NG911 | DoITT Next Generation 911 and SDE Expansion | 1 | DEVELOP SCOPE | 2021-06-01 | 2021-08-29 | 2021-06-01 | 2021-08-29
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77NG911 | DoITT Next Generation 911 and SDE Expansion | 2 | PRELIMINARY DESIGN | 2021-08-30 | 2021-12-27 | 2021-08-30 | 2021-12-27
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77NG911 | DoITT Next Generation 911 and SDE Expansion | 3 | FINAL DESIGN | 2021-12-28 | 2022-06-25 | 2021-12-28 | 2022-06-25
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77NG911 | DoITT Next Generation 911 and SDE Expansion | 4 | BID AWARD AND REGISTER CONTRCT | 2022-06-26 | 2022-09-23 | 2022-06-26 | 2022-09-23
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77NG911 | DoITT Next Generation 911 and SDE Expansion | 5 | CONSTRUCTION TO 25% | 2022-09-24 | 2023-01-21 | 2022-09-24 | 2023-01-21
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77NG911 | DoITT Next Generation 911 and SDE Expansion | 6 | CONSTRUCTION TO 50% | 2023-01-22 | 2023-05-21 | 2023-01-22 | 2023-05-21
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77NG911 | DoITT Next Generation 911 and SDE Expansion | 7 | CONSTRUCTION TO 75% | 2023-05-22 | 2023-09-18 | 2023-05-22 | 2023-09-18
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77NG911 | DoITT Next Generation 911 and SDE Expansion | 8 | ORIGINAL EQUIP & FURNISHING | 2023-09-19 | 2023-12-17 | 2023-09-19 | 2023-12-17
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77NG911 | DoITT Next Generation 911 and SDE Expansion | 9 | SUBSTANTIAL COMPLETION | 2023-12-18 | 2024-02-15 | 2023-12-18 | 2024-02-15
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77NG911 | DoITT Next Generation 911 and SDE Expansion | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-02-16 | 2024-03-16 | 2024-02-16 | 2024-03-16
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SECAM | SECURITY CAMERAS - DCAS PUBLIC BUILDINGS | 1 | DEVELOP SCOPE | 2011-04-01 | 2011-06-29 | 2011-04-01 | 2011-06-29
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SECAM | SECURITY CAMERAS - DCAS PUBLIC BUILDINGS | 2 | PRELIMINARY DESIGN | 2011-06-30 | 2011-10-27 | 2011-06-30 | 2011-10-27
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SECAM | SECURITY CAMERAS - DCAS PUBLIC BUILDINGS | 3 | FINAL DESIGN | 2011-10-28 | 2012-04-24 | 2011-10-28 | 2012-04-24
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SECAM | SECURITY CAMERAS - DCAS PUBLIC BUILDINGS | 4 | BID AWARD AND REGISTER CONTRCT | 2012-04-25 | 2012-07-23 | 2012-04-25 | 2012-07-23
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SECAM | SECURITY CAMERAS - DCAS PUBLIC BUILDINGS | 5 | CONSTRUCTION TO 25% | 2012-07-24 | 2012-11-20 | 2022-06-01 | 2022-09-28
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SECAM | SECURITY CAMERAS - DCAS PUBLIC BUILDINGS | 6 | CONSTRUCTION TO 50% | 2012-11-21 | 2013-03-20 | 2022-09-29 | 2023-01-26
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SECAM | SECURITY CAMERAS - DCAS PUBLIC BUILDINGS | 7 | CONSTRUCTION TO 75% | 2013-03-21 | 2013-07-18 | 2023-01-27 | 2023-05-26
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SECAM | SECURITY CAMERAS - DCAS PUBLIC BUILDINGS | 8 | ORIGINAL EQUIP & FURNISHING | 2013-07-19 | 2013-10-16 | 2023-05-27 | 2023-08-24
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SECAM | SECURITY CAMERAS - DCAS PUBLIC BUILDINGS | 9 | SUBSTANTIAL COMPLETION | 2013-10-17 | 2014-10-11 | 2023-08-25 | 2024-08-18
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SECAM | SECURITY CAMERAS - DCAS PUBLIC BUILDINGS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-10-12 | 2015-10-06 | 2024-08-19 | 2025-08-13
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWCOMPDA2 | Comptroller's Office Data Center Replacement at 1 Centre St. | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-08-29 | 2020-06-01 | 2020-08-29
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWCOMPDA2 | Comptroller's Office Data Center Replacement at 1 Centre St. | 2 | PRELIMINARY DESIGN | 2020-08-30 | 2020-12-27 | 2020-08-30 | 2020-12-27
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWCOMPDA2 | Comptroller's Office Data Center Replacement at 1 Centre St. | 3 | FINAL DESIGN | 2020-12-28 | 2021-06-25 | 2020-12-28 | 2021-06-25
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWCOMPDA2 | Comptroller's Office Data Center Replacement at 1 Centre St. | 4 | BID AWARD AND REGISTER CONTRCT | 2021-06-26 | 2021-09-23 | 2021-06-26 | 2021-09-23
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWCOMPDA2 | Comptroller's Office Data Center Replacement at 1 Centre St. | 5 | CONSTRUCTION TO 25% | 2021-09-24 | 2022-01-21 | 2021-09-24 | 2022-01-21
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWCOMPDA2 | Comptroller's Office Data Center Replacement at 1 Centre St. | 6 | CONSTRUCTION TO 50% | 2022-01-22 | 2022-05-21 | 2022-01-22 | 2022-05-21
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWCOMPDA2 | Comptroller's Office Data Center Replacement at 1 Centre St. | 7 | CONSTRUCTION TO 75% | 2022-05-22 | 2022-09-18 | 2022-05-22 | 2022-09-18
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWCOMPDA2 | Comptroller's Office Data Center Replacement at 1 Centre St. | 8 | ORIGINAL EQUIP & FURNISHING | 2022-09-19 | 2022-12-17 | 2022-09-19 | 2022-12-17
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWCOMPDA2 | Comptroller's Office Data Center Replacement at 1 Centre St. | 9 | SUBSTANTIAL COMPLETION | 2022-12-18 | 2023-02-15 | 2022-12-18 | 2023-02-15
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWCOMPDA2 | Comptroller's Office Data Center Replacement at 1 Centre St. | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-02-16 | 2023-03-17 | 2023-02-16 | 2023-03-17
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | SOLARGR4 | NYPA - SOLAR PARKING | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-06-30 | 2020-06-01 | 2020-06-30
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | SOLARGR4 | NYPA - SOLAR PARKING | 2 | BID AWARD AND REGISTER CONTRCT | 2020-07-01 | 2020-08-29 | 2020-07-01 | 2020-08-29
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | SOLARGR4 | NYPA - SOLAR PARKING | 3 | CONSTRUCTION TO 50% | 2020-08-30 | 2021-02-25 | 2020-08-30 | 2021-02-25
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | SOLARGR4 | NYPA - SOLAR PARKING | 4 | CONSTRUCTION TO 75% | 2021-02-26 | 2023-06-30 | 2021-02-26 | 2023-06-30
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | SOLARGR4 | NYPA - SOLAR PARKING | 5 | SUBSTANTIAL COMPLETION | 2023-07-01 | 2023-08-29 | 2023-07-01 | 2023-08-29
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | SOLARGR4 | NYPA - SOLAR PARKING | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-08-30 | 2023-09-28 | 2023-08-30 | 2023-09-28
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | SOLARGR5 | NYPA - RESILIENT SOLAR | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-06-30 | 2020-06-01 | 2020-06-30
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | SOLARGR5 | NYPA - RESILIENT SOLAR | 2 | BID AWARD AND REGISTER CONTRCT | 2020-07-01 | 2020-08-29 | 2020-07-01 | 2020-08-29
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | SOLARGR5 | NYPA - RESILIENT SOLAR | 3 | CONSTRUCTION TO 50% | 2020-08-30 | 2021-02-25 | 2020-08-30 | 2021-02-25
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | SOLARGR5 | NYPA - RESILIENT SOLAR | 4 | CONSTRUCTION TO 75% | 2022-06-01 | 2023-06-30 | 2022-06-01 | 2023-06-30
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | SOLARGR5 | NYPA - RESILIENT SOLAR | 5 | SUBSTANTIAL COMPLETION | 2023-07-01 | 2023-08-29 | 2023-07-01 | 2023-08-29
20201123 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | SOLARGR5 | NYPA - RESILIENT SOLAR | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-08-30 | 2024-08-03 | 2023-08-30 | 2024-08-03
20201123 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LB20DUMBO | ADAMS STREET LIBRARY FIT OUT | 1 | DESIGN | 2019-01-01 | 2019-12-31 | 2021-01-01 | 2021-12-31
20201123 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LB20DUMBO | ADAMS STREET LIBRARY FIT OUT | 2 | CONSTRUCTION | 2020-01-01 | 2020-06-28 | 2020-01-01 | 2020-06-28
20201123 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBC17DRBR | DYKER INTERIOR RENOVATION | 1 | DESIGN | 2020-07-01 | 2021-06-30 | 2020-07-01 | 2021-06-30
20201123 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBC17DRBR | DYKER INTERIOR RENOVATION | 2 | CONSTRUCTION | 2021-07-01 | 2021-12-27 | 2021-07-01 | 2021-12-27
20201123 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBC18CTRF | CORTELYOU ROOF | 1 | DESIGN | 2019-07-01 | 2020-06-29 | 2022-06-01 | 2023-05-31
20201123 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBC18CTRF | CORTELYOU ROOF | 2 | CONSTRUCTION | 2020-06-30 | 2020-12-26 | 2023-06-01 | 2023-11-27
20201123 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBC18FHSG | FT HAMILTON ROOF | 1 | DESIGN | 2019-07-01 | 2020-06-29 | 2022-06-01 | 2023-05-31
20201123 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBC18FHSG | FT HAMILTON ROOF | 2 | CONSTRUCTION | 2020-06-30 | 2020-12-26 | 2023-06-01 | 2023-11-27
20201123 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBC18GSMR | GRAVESEND MEETING ROOM | 1 | DESIGN | 2019-07-01 | 2020-06-29 | 2022-06-30 | 2023-06-29
20201123 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBC18GSMR | GRAVESEND MEETING ROOM | 2 | CONSTRUCTION | 2020-06-30 | 2020-12-26 | 2023-06-30 | 2023-12-26
20201123 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBC18KBFS | KINGS BAY FIRE SAFETY | 1 | DESIGN | 2019-07-01 | 2020-06-29 | 2022-06-30 | 2023-06-29
20201123 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBC18KBFS | KINGS BAY FIRE SAFETY | 2 | CONSTRUCTION | 2020-06-30 | 2020-12-26 | 2023-06-30 | 2023-12-26
20201123 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBC18KBHC | KINGS BAY BOILER | 1 | DESIGN | 2019-07-01 | 2020-06-29 | 2021-07-01 | 2022-06-30
20201123 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBC18KBHC | KINGS BAY BOILER | 2 | CONSTRUCTION | 2020-06-30 | 2020-12-26 | 2022-07-01 | 2022-12-27
20201123 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBC19CHEL | Clinton Hill Wiring Upgrade | 1 | DESIGN | 2019-09-11 | 2021-06-30 | 2023-09-11 | 2025-06-30
20201123 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBC19CHEL | Clinton Hill Wiring Upgrade | 2 | CONSTRUCTION | 2021-07-01 | 2022-07-01 | 2025-07-01 | 2026-07-01
20201123 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBC20CTOP | CORTELYOU OUTDOOR PLAZA | 1 | DESIGN | 2020-07-01 | 2021-06-30 | 2022-07-01 | 2023-06-30
20201123 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBC20CTOP | CORTELYOU OUTDOOR PLAZA | 2 | CONSTRUCTION | 2021-07-01 | 2021-12-27 | 2023-07-01 | 2023-12-27
20201123 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBC20MPMR | MCKINLEY PARK MEETING ROOM | 1 | DESIGN | 2020-07-01 | 2021-06-30 | 2022-07-01 | 2023-06-30
20201123 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBC20MPMR | MCKINLEY PARK MEETING ROOM | 2 | CONSTRUCTION | 2021-07-01 | 2021-12-27 | 2023-07-01 | 2023-12-27
20201123 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBC20SAAD | STONE AVENUE ADA ACCESSIBILITY | 1 | DESIGN | 2020-07-01 | 2021-06-30 | 2020-07-01 | 2021-06-30
20201123 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBC20SAAD | STONE AVENUE ADA ACCESSIBILITY | 2 | CONSTRUCTION | 2021-07-01 | 2021-12-27 | 2021-07-01 | 2021-12-27
20201123 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBC20SCBM | SPRING CREEK BMS | 1 | DESIGN | 2020-07-01 | 2021-06-30 | 2020-07-01 | 2021-06-30
20201123 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBC20SCBM | SPRING CREEK BMS | 2 | CONSTRUCTION | 2021-07-01 | 2021-12-27 | 2021-07-01 | 2021-12-27
20201123 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBCENPH2 | CENTRAL RENOVATION - PHASE 2 | 1 | DESIGN | 2020-07-01 | 2021-06-30 | 2024-07-01 | 2025-06-30
20201123 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBCENPH2 | CENTRAL RENOVATION - PHASE 2 | 2 | CONSTRUCTION | 2021-07-01 | 2021-12-27 | 2025-07-01 | 2025-12-27
20201123 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBEM05SWR | SYSTEM-WIDE FUNDING | 1 | DESIGN | 2019-09-11 | 2020-09-09 | 2024-09-11 | 2025-09-10
20201123 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBEM05SWR | SYSTEM-WIDE FUNDING | 2 | CONSTRUCTION | 2020-09-10 | 2022-07-01 | 2025-09-11 | 2027-07-02
20201123 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBK16HLRF | Highlawn - Roof Replacement | 1 | DESIGN | 2019-09-11 | 2020-09-09 | 2021-09-11 | 2022-09-10
20201123 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBK16HLRF | Highlawn - Roof Replacement | 2 | CONSTRUCTION | 2020-09-10 | 2021-03-08 | 2022-09-11 | 2023-03-09
20201123 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBK16SCRF | SPRING CREEK ROOF REPLACEMENT | 1 | DESIGN | 2019-09-11 | 2020-09-09 | 2019-09-11 | 2020-09-09
20201123 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBK16SCRF | SPRING CREEK ROOF REPLACEMENT | 2 | CONSTRUCTION | 2020-09-10 | 2022-07-01 | 2020-09-10 | 2022-07-01
20201123 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBM18NLOH | NEW LOTS BRANCH OVERHAUL | 1 | DESIGN | 2020-01-01 | 2020-12-30 | 2020-01-01 | 2020-12-30
20201123 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBM18NLOH | NEW LOTS BRANCH OVERHAUL | 2 | CONSTRUCTION | 2020-12-31 | 2023-06-28 | 2020-12-31 | 2023-06-28
20201123 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBM19BPLB | Brower Park Library Fit Out | 1 | DESIGN | 2019-09-20 | 2021-06-30 | 2019-09-20 | 2021-06-30
20201123 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBM19BPLB | Brower Park Library Fit Out | 2 | CONSTRUCTION | 2021-07-01 | 2021-12-27 | 2021-07-01 | 2021-12-27
20201123 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBM19CAOH | CANARSIE BRANCH OVERHAUL | 1 | DESIGN | 2020-07-01 | 2021-06-30 | 2020-07-01 | 2021-06-30
20201123 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBM19CAOH | CANARSIE BRANCH OVERHAUL | 2 | CONSTRUCTION | 2021-07-01 | 2023-07-01 | 2021-07-01 | 2023-07-01
20201123 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBP18BHBR | BROOKLYN HEIGHTS BRANCH FIT OUT | 1 | DESIGN | 2020-07-01 | 2021-06-30 | 2020-07-01 | 2021-06-30
20201123 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBP18BHBR | BROOKLYN HEIGHTS BRANCH FIT OUT | 2 | CONSTRUCTION | 2021-07-01 | 2021-06-30 | 2021-07-01 | 2021-06-30
20201123 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBP18LDIN | LEONARD INFRASTRUCTURE UPGRADE | 1 | DESIGN | 2020-07-01 | 2021-06-30 | 2024-07-01 | 2025-06-30
20201123 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBP18LDIN | LEONARD INFRASTRUCTURE UPGRADE | 2 | CONSTRUCTION | 2021-07-01 | 2024-06-30 | 2025-07-01 | 2028-06-30
20201123 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBP18PCAD | PACIFIC ADA COMPLIANCE | 1 | DESIGN | 2020-07-01 | 2021-06-30 | 2024-06-30 | 2025-06-29
20201123 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBP18PCAD | PACIFIC ADA COMPLIANCE | 2 | CONSTRUCTION | 2021-07-01 | 2022-07-01 | 2025-06-30 | 2026-06-30
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY001-021 | Quad Rehab Project | 1 | DEVELOP SCOPE | 2021-06-30 | 2021-09-27 | 2021-06-30 | 2021-09-27
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY001-021 | Quad Rehab Project | 2 | PRELIMINARY DESIGN | 2021-09-28 | 2022-01-25 | 2021-09-28 | 2022-01-25
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY001-021 | Quad Rehab Project | 3 | FINAL DESIGN | 2022-01-26 | 2022-07-24 | 2022-01-26 | 2022-07-24
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY001-021 | Quad Rehab Project | 4 | BID AWARD AND REGISTER CONTRCT | 2022-07-25 | 2022-10-22 | 2022-07-25 | 2022-10-22
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY001-021 | Quad Rehab Project | 5 | CONSTRUCTION TO 25% | 2022-10-23 | 2023-02-19 | 2022-10-23 | 2023-02-19
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY001-021 | Quad Rehab Project | 6 | CONSTRUCTION TO 50% | 2023-02-20 | 2023-06-19 | 2023-02-20 | 2023-06-19
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY001-021 | Quad Rehab Project | 7 | CONSTRUCTION TO 75% | 2023-06-20 | 2023-10-17 | 2023-06-20 | 2023-10-17
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY001-021 | Quad Rehab Project | 8 | ORIGINAL EQUIP & FURNISHING | 2023-10-18 | 2024-01-15 | 2023-10-18 | 2024-01-15
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY001-021 | Quad Rehab Project | 9 | SUBSTANTIAL COMPLETION | 2024-01-16 | 2024-03-15 | 2024-01-16 | 2024-03-15
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY001-021 | Quad Rehab Project | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-03-16 | 2024-04-14 | 2024-03-16 | 2024-04-14
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY003-021 | Ingersoll Lecture Hall Upgrades | 1 | DEVELOP SCOPE | 2021-06-30 | 2021-09-27 | 2021-06-30 | 2021-09-27
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY003-021 | Ingersoll Lecture Hall Upgrades | 2 | PRELIMINARY DESIGN | 2021-09-28 | 2022-01-25 | 2021-09-28 | 2022-01-25
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY003-021 | Ingersoll Lecture Hall Upgrades | 3 | FINAL DESIGN | 2022-01-26 | 2022-07-24 | 2022-01-26 | 2022-07-24
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY003-021 | Ingersoll Lecture Hall Upgrades | 4 | BID AWARD AND REGISTER CONTRCT | 2022-07-25 | 2022-10-22 | 2022-07-25 | 2022-10-22
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY003-021 | Ingersoll Lecture Hall Upgrades | 5 | CONSTRUCTION TO 25% | 2022-10-23 | 2023-02-19 | 2022-10-23 | 2023-02-19
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY003-021 | Ingersoll Lecture Hall Upgrades | 6 | CONSTRUCTION TO 50% | 2023-02-20 | 2023-06-19 | 2023-02-20 | 2023-06-19
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY003-021 | Ingersoll Lecture Hall Upgrades | 7 | CONSTRUCTION TO 75% | 2023-06-20 | 2023-10-17 | 2023-06-20 | 2023-10-17
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY003-021 | Ingersoll Lecture Hall Upgrades | 8 | ORIGINAL EQUIP & FURNISHING | 2023-10-18 | 2024-01-15 | 2023-10-18 | 2024-01-15
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY003-021 | Ingersoll Lecture Hall Upgrades | 9 | SUBSTANTIAL COMPLETION | 2024-01-16 | 2024-03-15 | 2024-01-16 | 2024-03-15
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY003-021 | Ingersoll Lecture Hall Upgrades | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-03-16 | 2024-04-14 | 2024-03-16 | 2024-04-14
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY024-012 | Haitian Studies Institute Initial Outfitting | 1 | DEVELOP SCOPE | 2012-06-01 | 2012-08-29 | 2012-06-01 | 2012-08-29
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY024-012 | Haitian Studies Institute Initial Outfitting | 2 | PRELIMINARY DESIGN | 2012-08-30 | 2012-12-27 | 2012-08-30 | 2012-12-27
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY024-012 | Haitian Studies Institute Initial Outfitting | 3 | FINAL DESIGN | 2012-12-28 | 2013-06-25 | 2012-12-28 | 2013-06-25
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY024-012 | Haitian Studies Institute Initial Outfitting | 4 | BID AWARD AND REGISTER CONTRCT | 2013-06-26 | 2013-09-23 | 2013-06-26 | 2013-09-23
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY024-012 | Haitian Studies Institute Initial Outfitting | 5 | CONSTRUCTION TO 25% | 2013-09-24 | 2014-01-21 | 2013-09-24 | 2014-01-21
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY024-012 | Haitian Studies Institute Initial Outfitting | 6 | CONSTRUCTION TO 50% | 2014-01-22 | 2014-05-21 | 2014-01-22 | 2014-05-21
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY024-012 | Haitian Studies Institute Initial Outfitting | 7 | CONSTRUCTION TO 75% | 2014-05-22 | 2014-09-18 | 2014-05-22 | 2014-09-18
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY024-012 | Haitian Studies Institute Initial Outfitting | 8 | ORIGINAL EQUIP & FURNISHING | 2014-09-19 | 2014-12-17 | 2014-09-19 | 2014-12-17
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY024-012 | Haitian Studies Institute Initial Outfitting | 9 | SUBSTANTIAL COMPLETION | 2014-12-18 | 2015-02-15 | 2014-12-18 | 2015-02-15
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY024-012 | Haitian Studies Institute Initial Outfitting | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-02-16 | 2015-03-17 | 2015-02-16 | 2027-03-31
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY025-012 | Haitian Studies Institute Initial Outfitting | 1 | DEVELOP SCOPE | 2012-06-01 | 2012-08-29 | 2012-06-01 | 2012-08-29
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY025-012 | Haitian Studies Institute Initial Outfitting | 2 | PRELIMINARY DESIGN | 2012-08-30 | 2012-12-27 | 2012-08-30 | 2012-12-27
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY025-012 | Haitian Studies Institute Initial Outfitting | 3 | FINAL DESIGN | 2012-12-28 | 2013-06-25 | 2012-12-28 | 2013-06-25
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY025-012 | Haitian Studies Institute Initial Outfitting | 4 | BID AWARD AND REGISTER CONTRCT | 2013-06-26 | 2013-09-23 | 2013-06-26 | 2013-09-23
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY025-012 | Haitian Studies Institute Initial Outfitting | 5 | CONSTRUCTION TO 25% | 2013-09-24 | 2014-01-21 | 2013-09-24 | 2014-01-21
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY025-012 | Haitian Studies Institute Initial Outfitting | 6 | CONSTRUCTION TO 50% | 2014-01-22 | 2014-05-21 | 2014-01-22 | 2014-05-21
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY025-012 | Haitian Studies Institute Initial Outfitting | 7 | CONSTRUCTION TO 75% | 2014-05-22 | 2014-09-18 | 2014-05-22 | 2014-09-18
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY025-012 | Haitian Studies Institute Initial Outfitting | 8 | ORIGINAL EQUIP & FURNISHING | 2014-09-19 | 2014-12-17 | 2014-09-19 | 2014-12-17
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY025-012 | Haitian Studies Institute Initial Outfitting | 9 | SUBSTANTIAL COMPLETION | 2014-12-18 | 2015-02-15 | 2014-12-18 | 2015-02-15
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY025-012 | Haitian Studies Institute Initial Outfitting | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-02-16 | 2015-03-17 | 2015-02-16 | 2027-03-31
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY026-013 | Renovation of Ingersoll Extension | 1 | DEVELOP SCOPE | 2013-06-01 | 2013-08-29 | 2013-06-01 | 2013-08-29
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY026-013 | Renovation of Ingersoll Extension | 2 | PRELIMINARY DESIGN | 2013-08-30 | 2013-12-27 | 2013-08-30 | 2013-12-27
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY026-013 | Renovation of Ingersoll Extension | 3 | FINAL DESIGN | 2013-12-28 | 2014-06-25 | 2013-12-28 | 2014-06-25
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY026-013 | Renovation of Ingersoll Extension | 4 | BID AWARD AND REGISTER CONTRCT | 2014-06-26 | 2014-09-23 | 2014-06-26 | 2014-09-23
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY026-013 | Renovation of Ingersoll Extension | 5 | CONSTRUCTION TO 25% | 2014-09-24 | 2015-01-21 | 2014-09-24 | 2015-01-21
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY026-013 | Renovation of Ingersoll Extension | 6 | CONSTRUCTION TO 50% | 2015-01-22 | 2015-05-21 | 2015-01-22 | 2015-05-21
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY026-013 | Renovation of Ingersoll Extension | 7 | CONSTRUCTION TO 75% | 2015-05-22 | 2015-09-18 | 2015-05-22 | 2015-09-18
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY026-013 | Renovation of Ingersoll Extension | 8 | ORIGINAL EQUIP & FURNISHING | 2015-09-19 | 2015-12-17 | 2015-09-19 | 2015-12-17
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY026-013 | Renovation of Ingersoll Extension | 9 | SUBSTANTIAL COMPLETION | 2015-12-18 | 2016-02-15 | 2015-12-18 | 2016-02-15
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY026-013 | Renovation of Ingersoll Extension | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-02-16 | 2016-03-16 | 2016-02-16 | 2026-03-31
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY031-017 | Electrical Upgrades | 1 | DEVELOP SCOPE | 2017-06-01 | 2017-08-29 | 2021-07-01 | 2021-10-01
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY031-017 | Electrical Upgrades | 2 | PRELIMINARY DESIGN | 2017-08-30 | 2017-12-27 | 2021-10-02 | 2022-01-29
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY031-017 | Electrical Upgrades | 3 | FINAL DESIGN | 2017-12-28 | 2018-06-25 | 2022-01-30 | 2022-07-28
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY031-017 | Electrical Upgrades | 4 | BID AWARD AND REGISTER CONTRCT | 2018-06-26 | 2018-09-23 | 2022-07-29 | 2022-10-26
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY031-017 | Electrical Upgrades | 5 | CONSTRUCTION TO 25% | 2018-09-24 | 2019-01-21 | 2022-10-27 | 2023-02-23
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY031-017 | Electrical Upgrades | 6 | CONSTRUCTION TO 50% | 2019-01-22 | 2019-05-21 | 2023-02-24 | 2023-06-23
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY031-017 | Electrical Upgrades | 7 | CONSTRUCTION TO 75% | 2019-05-22 | 2019-09-18 | 2023-06-24 | 2023-10-21
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY031-017 | Electrical Upgrades | 8 | ORIGINAL EQUIP & FURNISHING | 2019-09-19 | 2019-12-17 | 2023-10-22 | 2024-01-19
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY031-017 | Electrical Upgrades | 9 | SUBSTANTIAL COMPLETION | 2019-12-18 | 2020-02-15 | 2024-01-20 | 2024-03-19
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY031-017 | Electrical Upgrades | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-02-16 | 2020-03-16 | 2024-03-20 | 2027-05-03
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY032-018 | ADA Upgrades for the Brooklyn College Student Center | 1 | DEVELOP SCOPE | 2018-06-01 | 2018-08-29 | 2021-07-01 | 2021-10-01
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY032-018 | ADA Upgrades for the Brooklyn College Student Center | 2 | PRELIMINARY DESIGN | 2018-08-30 | 2018-12-27 | 2021-10-02 | 2022-01-29
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY032-018 | ADA Upgrades for the Brooklyn College Student Center | 3 | FINAL DESIGN | 2018-12-28 | 2019-06-25 | 2022-01-30 | 2022-07-28
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY032-018 | ADA Upgrades for the Brooklyn College Student Center | 4 | BID AWARD AND REGISTER CONTRCT | 2019-06-26 | 2019-09-23 | 2022-07-29 | 2022-10-26
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY032-018 | ADA Upgrades for the Brooklyn College Student Center | 5 | CONSTRUCTION TO 25% | 2019-09-24 | 2020-01-21 | 2022-10-27 | 2023-02-23
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY032-018 | ADA Upgrades for the Brooklyn College Student Center | 6 | CONSTRUCTION TO 50% | 2020-01-22 | 2020-05-20 | 2023-02-24 | 2023-06-23
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY032-018 | ADA Upgrades for the Brooklyn College Student Center | 7 | CONSTRUCTION TO 75% | 2020-05-21 | 2020-09-17 | 2023-06-24 | 2023-10-21
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY032-018 | ADA Upgrades for the Brooklyn College Student Center | 8 | ORIGINAL EQUIP & FURNISHING | 2020-09-18 | 2020-12-16 | 2023-10-22 | 2024-01-19
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY032-018 | ADA Upgrades for the Brooklyn College Student Center | 9 | SUBSTANTIAL COMPLETION | 2020-12-17 | 2021-02-14 | 2024-01-20 | 2024-03-19
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY032-018 | ADA Upgrades for the Brooklyn College Student Center | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-02-15 | 2021-03-16 | 2024-03-20 | 2026-05-03
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY033-019 | Ingersoll Lecture Halls | 1 | DEVELOP SCOPE | 2019-06-01 | 2019-08-29 | 2021-07-01 | 2021-10-01
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY033-019 | Ingersoll Lecture Halls | 2 | PRELIMINARY DESIGN | 2019-08-30 | 2019-12-27 | 2021-10-02 | 2022-01-29
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY033-019 | Ingersoll Lecture Halls | 3 | FINAL DESIGN | 2019-12-28 | 2020-06-24 | 2022-01-30 | 2022-07-28
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY033-019 | Ingersoll Lecture Halls | 4 | BID AWARD AND REGISTER CONTRCT | 2020-06-25 | 2020-09-22 | 2022-07-29 | 2022-10-26
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY033-019 | Ingersoll Lecture Halls | 5 | CONSTRUCTION TO 25% | 2020-09-23 | 2021-01-20 | 2022-10-27 | 2023-02-23
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY033-019 | Ingersoll Lecture Halls | 6 | CONSTRUCTION TO 50% | 2021-01-21 | 2021-05-20 | 2023-02-24 | 2023-06-23
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY033-019 | Ingersoll Lecture Halls | 7 | CONSTRUCTION TO 75% | 2021-05-21 | 2021-09-17 | 2023-06-24 | 2023-10-21
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY033-019 | Ingersoll Lecture Halls | 8 | ORIGINAL EQUIP & FURNISHING | 2021-09-18 | 2021-12-16 | 2023-10-22 | 2024-01-19
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY033-019 | Ingersoll Lecture Halls | 9 | SUBSTANTIAL COMPLETION | 2021-12-17 | 2022-02-14 | 2024-01-20 | 2024-03-19
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY033-019 | Ingersoll Lecture Halls | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-02-15 | 2022-03-16 | 2024-03-20 | 2024-04-18
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY034-019 | Restoration of Main Quad | 1 | DEVELOP SCOPE | 2019-06-01 | 2019-08-29 | 2021-07-01 | 2021-09-29
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY034-019 | Restoration of Main Quad | 2 | PRELIMINARY DESIGN | 2019-08-30 | 2019-12-27 | 2021-09-30 | 2022-01-27
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY034-019 | Restoration of Main Quad | 3 | FINAL DESIGN | 2019-12-28 | 2020-06-24 | 2022-01-28 | 2022-07-26
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY034-019 | Restoration of Main Quad | 4 | BID AWARD AND REGISTER CONTRCT | 2020-06-25 | 2020-09-22 | 2022-07-27 | 2022-10-24
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY034-019 | Restoration of Main Quad | 5 | CONSTRUCTION TO 25% | 2020-09-23 | 2021-01-20 | 2022-10-25 | 2023-02-21
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY034-019 | Restoration of Main Quad | 6 | CONSTRUCTION TO 50% | 2021-01-21 | 2021-05-20 | 2023-02-22 | 2023-06-21
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY034-019 | Restoration of Main Quad | 7 | CONSTRUCTION TO 75% | 2021-05-21 | 2021-09-17 | 2023-06-22 | 2023-10-19
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY034-019 | Restoration of Main Quad | 8 | ORIGINAL EQUIP & FURNISHING | 2021-09-18 | 2021-12-16 | 2023-10-20 | 2024-01-17
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY034-019 | Restoration of Main Quad | 9 | SUBSTANTIAL COMPLETION | 2021-12-17 | 2022-02-14 | 2024-01-18 | 2024-03-17
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY034-019 | Restoration of Main Quad | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-02-15 | 2022-03-16 | 2024-03-18 | 2024-04-16
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY036-020 | Main Quad Restoration | 1 | DEVELOP SCOPE | 2021-07-01 | 2021-10-01 | 2021-07-01 | 2021-10-01
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY036-020 | Main Quad Restoration | 2 | PRELIMINARY DESIGN | 2021-10-02 | 2022-01-29 | 2021-10-02 | 2022-01-29
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY036-020 | Main Quad Restoration | 3 | FINAL DESIGN | 2022-01-30 | 2022-07-28 | 2022-01-30 | 2022-07-28
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY036-020 | Main Quad Restoration | 4 | BID AWARD AND REGISTER CONTRCT | 2022-07-29 | 2022-10-26 | 2022-07-29 | 2022-10-26
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY036-020 | Main Quad Restoration | 5 | CONSTRUCTION TO 25% | 2022-10-27 | 2023-02-23 | 2022-10-27 | 2023-02-23
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY036-020 | Main Quad Restoration | 6 | CONSTRUCTION TO 50% | 2023-02-24 | 2023-06-23 | 2023-02-24 | 2023-06-23
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY036-020 | Main Quad Restoration | 7 | CONSTRUCTION TO 75% | 2023-06-24 | 2023-10-21 | 2023-06-24 | 2023-10-21
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY036-020 | Main Quad Restoration | 8 | ORIGINAL EQUIP & FURNISHING | 2023-10-22 | 2024-01-19 | 2023-10-22 | 2024-01-19
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY036-020 | Main Quad Restoration | 9 | SUBSTANTIAL COMPLETION | 2024-01-20 | 2024-03-19 | 2024-01-20 | 2024-03-19
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY036-020 | Main Quad Restoration | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-03-20 | 2024-04-18 | 2024-03-20 | 2024-04-18
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY037-020 | Ingersoll Lecture Halls Upgrade | 1 | DEVELOP SCOPE | 2021-07-01 | 2021-09-28 | 2021-07-01 | 2021-09-28
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY037-020 | Ingersoll Lecture Halls Upgrade | 2 | PRELIMINARY DESIGN | 2021-09-29 | 2022-01-26 | 2021-09-29 | 2022-01-26
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY037-020 | Ingersoll Lecture Halls Upgrade | 3 | FINAL DESIGN | 2022-01-27 | 2022-07-25 | 2022-01-27 | 2022-07-25
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY037-020 | Ingersoll Lecture Halls Upgrade | 4 | BID AWARD AND REGISTER CONTRCT | 2022-07-26 | 2022-10-23 | 2022-07-26 | 2022-10-23
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY037-020 | Ingersoll Lecture Halls Upgrade | 5 | CONSTRUCTION TO 25% | 2022-10-24 | 2023-02-20 | 2022-10-24 | 2023-02-20
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY037-020 | Ingersoll Lecture Halls Upgrade | 6 | CONSTRUCTION TO 50% | 2023-02-21 | 2023-06-20 | 2023-02-21 | 2023-06-20
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY037-020 | Ingersoll Lecture Halls Upgrade | 7 | CONSTRUCTION TO 75% | 2023-06-21 | 2023-10-18 | 2023-06-21 | 2023-10-18
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY037-020 | Ingersoll Lecture Halls Upgrade | 8 | ORIGINAL EQUIP & FURNISHING | 2023-10-19 | 2024-01-16 | 2023-10-19 | 2024-01-16
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY037-020 | Ingersoll Lecture Halls Upgrade | 9 | SUBSTANTIAL COMPLETION | 2024-01-17 | 2024-03-16 | 2024-01-17 | 2024-03-16
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | BY037-020 | Ingersoll Lecture Halls Upgrade | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-03-17 | 2024-04-15 | 2024-03-17 | 2024-04-15
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | CA034KG13 | Gas Booster Pump Upgrade | 1 | DEVELOP SCOPE | 2018-06-01 | 2018-08-29 | 2018-06-01 | 2018-08-29
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | CA034KG13 | Gas Booster Pump Upgrade | 2 | PRELIMINARY DESIGN | 2018-08-30 | 2018-12-27 | 2018-08-30 | 2018-12-27
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | CA034KG13 | Gas Booster Pump Upgrade | 3 | FINAL DESIGN | 2018-12-28 | 2019-06-25 | 2018-12-28 | 2019-06-25
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | CA034KG13 | Gas Booster Pump Upgrade | 4 | BID AWARD AND REGISTER CONTRCT | 2019-06-26 | 2019-09-23 | 2019-06-26 | 2019-09-23
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | CA034KG13 | Gas Booster Pump Upgrade | 5 | CONSTRUCTION TO 25% | 2019-09-24 | 2020-01-21 | 2019-09-24 | 2020-01-21
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | CA034KG13 | Gas Booster Pump Upgrade | 6 | CONSTRUCTION TO 50% | 2020-01-22 | 2020-05-20 | 2020-01-22 | 2020-05-20
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | CA034KG13 | Gas Booster Pump Upgrade | 7 | CONSTRUCTION TO 75% | 2020-05-21 | 2020-09-17 | 2020-05-21 | 2020-09-17
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | CA034KG13 | Gas Booster Pump Upgrade | 8 | ORIGINAL EQUIP & FURNISHING | 2020-09-18 | 2020-12-16 | 2020-09-18 | 2020-12-16
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | CA034KG13 | Gas Booster Pump Upgrade | 9 | SUBSTANTIAL COMPLETION | 2020-12-17 | 2021-02-14 | 2020-12-17 | 2021-02-14
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | CA034KG13 | Gas Booster Pump Upgrade | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-02-15 | 2021-03-16 | 2021-02-15 | 2024-03-31
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | CA234KG13 | Library Roof Replacement | 1 | DEVELOP SCOPE | 2018-06-01 | 2018-08-29 | 2018-06-01 | 2018-08-29
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | CA234KG13 | Library Roof Replacement | 2 | PRELIMINARY DESIGN | 2018-08-30 | 2018-12-27 | 2018-08-30 | 2018-12-27
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | CA234KG13 | Library Roof Replacement | 3 | FINAL DESIGN | 2018-12-28 | 2019-06-25 | 2018-12-28 | 2019-06-25
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | CA234KG13 | Library Roof Replacement | 4 | BID AWARD AND REGISTER CONTRCT | 2019-06-26 | 2019-09-23 | 2019-06-26 | 2019-09-23
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | CA234KG13 | Library Roof Replacement | 5 | CONSTRUCTION TO 25% | 2019-09-24 | 2020-01-21 | 2019-09-24 | 2020-01-21
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | CA234KG13 | Library Roof Replacement | 6 | CONSTRUCTION TO 50% | 2020-01-22 | 2020-05-20 | 2020-01-22 | 2020-05-20
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | CA234KG13 | Library Roof Replacement | 7 | CONSTRUCTION TO 75% | 2020-05-21 | 2020-09-17 | 2020-05-21 | 2020-09-17
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | CA234KG13 | Library Roof Replacement | 8 | ORIGINAL EQUIP & FURNISHING | 2020-09-18 | 2020-12-16 | 2020-09-18 | 2020-12-16
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | CA234KG13 | Library Roof Replacement | 9 | SUBSTANTIAL COMPLETION | 2020-12-17 | 2021-02-14 | 2020-12-17 | 2021-02-14
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | CA234KG13 | Library Roof Replacement | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-02-15 | 2021-03-16 | 2021-02-15 | 2021-03-16
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG001-021 | LIbrary Building | 1 | DEVELOP SCOPE | 2021-06-30 | 2021-09-27 | 2021-06-30 | 2021-09-27
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG001-021 | LIbrary Building | 2 | PRELIMINARY DESIGN | 2021-09-28 | 2022-01-25 | 2021-09-28 | 2022-01-25
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG001-021 | LIbrary Building | 3 | FINAL DESIGN | 2022-01-26 | 2022-07-24 | 2022-01-26 | 2022-07-24
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG001-021 | LIbrary Building | 4 | BID AWARD AND REGISTER CONTRCT | 2022-07-25 | 2022-10-22 | 2022-07-25 | 2022-10-22
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG001-021 | LIbrary Building | 5 | CONSTRUCTION TO 25% | 2022-10-23 | 2023-02-19 | 2022-10-23 | 2023-02-19
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG001-021 | LIbrary Building | 6 | CONSTRUCTION TO 50% | 2023-02-20 | 2023-06-19 | 2023-02-20 | 2023-06-19
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG001-021 | LIbrary Building | 7 | CONSTRUCTION TO 75% | 2023-06-20 | 2023-10-17 | 2023-06-20 | 2023-10-17
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG001-021 | LIbrary Building | 8 | ORIGINAL EQUIP & FURNISHING | 2023-10-18 | 2024-01-15 | 2023-10-18 | 2024-01-15
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG001-021 | LIbrary Building | 9 | SUBSTANTIAL COMPLETION | 2024-01-16 | 2024-03-15 | 2024-01-16 | 2024-03-15
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG001-021 | LIbrary Building | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-03-16 | 2024-04-14 | 2024-03-16 | 2024-04-14
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG028-011 | Performing Arts Center Renovations | 1 | DEVELOP SCOPE | 2011-06-01 | 2011-08-29 | 2020-07-01 | 2020-09-29
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG028-011 | Performing Arts Center Renovations | 2 | PRELIMINARY DESIGN | 2011-08-30 | 2011-12-27 | 2020-09-30 | 2021-01-27
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG028-011 | Performing Arts Center Renovations | 3 | FINAL DESIGN | 2011-12-28 | 2012-06-24 | 2021-01-28 | 2021-07-26
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG028-011 | Performing Arts Center Renovations | 4 | BID AWARD AND REGISTER CONTRCT | 2012-06-25 | 2012-09-22 | 2021-07-27 | 2021-10-24
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG028-011 | Performing Arts Center Renovations | 5 | CONSTRUCTION TO 25% | 2012-09-23 | 2013-01-20 | 2021-10-25 | 2022-02-21
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG028-011 | Performing Arts Center Renovations | 6 | CONSTRUCTION TO 50% | 2013-01-21 | 2013-05-20 | 2022-02-22 | 2022-06-21
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG028-011 | Performing Arts Center Renovations | 7 | CONSTRUCTION TO 75% | 2013-05-21 | 2013-09-17 | 2022-06-22 | 2022-10-19
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG028-011 | Performing Arts Center Renovations | 8 | ORIGINAL EQUIP & FURNISHING | 2013-09-18 | 2013-12-16 | 2022-10-20 | 2023-01-17
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG028-011 | Performing Arts Center Renovations | 9 | SUBSTANTIAL COMPLETION | 2013-12-17 | 2014-02-14 | 2023-01-18 | 2023-03-18
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG028-011 | Performing Arts Center Renovations | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-02-15 | 2014-03-16 | 2023-03-19 | 2023-07-17
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG030-012 | Critical Maintenance A/P/U Buildings | 1 | DEVELOP SCOPE | 2012-06-01 | 2012-08-29 | 2012-06-01 | 2012-08-29
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG030-012 | Critical Maintenance A/P/U Buildings | 2 | PRELIMINARY DESIGN | 2012-08-30 | 2012-12-27 | 2012-08-30 | 2012-12-27
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG030-012 | Critical Maintenance A/P/U Buildings | 3 | FINAL DESIGN | 2012-12-28 | 2013-06-25 | 2012-12-28 | 2013-06-25
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG030-012 | Critical Maintenance A/P/U Buildings | 4 | BID AWARD AND REGISTER CONTRCT | 2013-06-26 | 2013-09-23 | 2013-06-26 | 2013-09-23
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG030-012 | Critical Maintenance A/P/U Buildings | 5 | CONSTRUCTION TO 25% | 2013-09-24 | 2014-01-21 | 2013-09-24 | 2014-01-21
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG030-012 | Critical Maintenance A/P/U Buildings | 6 | CONSTRUCTION TO 50% | 2014-01-22 | 2014-05-21 | 2014-01-22 | 2014-05-21
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG030-012 | Critical Maintenance A/P/U Buildings | 7 | CONSTRUCTION TO 75% | 2014-05-22 | 2014-09-18 | 2014-05-22 | 2014-09-18
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG030-012 | Critical Maintenance A/P/U Buildings | 8 | ORIGINAL EQUIP & FURNISHING | 2014-09-19 | 2014-12-17 | 2014-09-19 | 2014-12-17
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG030-012 | Critical Maintenance A/P/U Buildings | 9 | SUBSTANTIAL COMPLETION | 2014-12-18 | 2015-02-15 | 2014-12-18 | 2015-02-15
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG030-012 | Critical Maintenance A/P/U Buildings | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-02-16 | 2015-03-17 | 2015-02-16 | 2023-03-31
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG031-013 | Renovation of Pool Facilities | 1 | DEVELOP SCOPE | 2013-06-01 | 2013-08-29 | 2020-07-01 | 2020-09-28
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG031-013 | Renovation of Pool Facilities | 2 | PRELIMINARY DESIGN | 2013-08-30 | 2013-12-27 | 2020-09-29 | 2021-01-26
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG031-013 | Renovation of Pool Facilities | 3 | FINAL DESIGN | 2013-12-28 | 2014-06-25 | 2021-01-27 | 2021-07-25
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG031-013 | Renovation of Pool Facilities | 4 | BID AWARD AND REGISTER CONTRCT | 2014-06-26 | 2014-09-23 | 2021-07-26 | 2021-10-23
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG031-013 | Renovation of Pool Facilities | 5 | CONSTRUCTION TO 25% | 2014-09-24 | 2015-01-21 | 2021-10-24 | 2022-02-20
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG031-013 | Renovation of Pool Facilities | 6 | CONSTRUCTION TO 50% | 2015-01-22 | 2015-05-21 | 2022-02-21 | 2022-06-20
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG031-013 | Renovation of Pool Facilities | 7 | CONSTRUCTION TO 75% | 2015-05-22 | 2015-09-18 | 2022-06-21 | 2022-10-18
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG031-013 | Renovation of Pool Facilities | 8 | ORIGINAL EQUIP & FURNISHING | 2015-09-19 | 2015-12-17 | 2022-10-19 | 2023-01-16
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG031-013 | Renovation of Pool Facilities | 9 | SUBSTANTIAL COMPLETION | 2015-12-18 | 2016-02-15 | 2023-01-17 | 2023-03-17
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG031-013 | Renovation of Pool Facilities | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-02-16 | 2016-03-16 | 2023-03-18 | 2023-04-16
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG033-017 | Roof Replacements | 1 | DEVELOP SCOPE | 2017-06-01 | 2017-08-29 | 2019-07-01 | 2019-09-29
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG033-017 | Roof Replacements | 2 | PRELIMINARY DESIGN | 2017-08-30 | 2017-12-27 | 2019-09-30 | 2020-01-27
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG033-017 | Roof Replacements | 3 | FINAL DESIGN | 2017-12-28 | 2018-06-25 | 2020-01-28 | 2020-07-25
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG033-017 | Roof Replacements | 4 | BID AWARD AND REGISTER CONTRCT | 2018-06-26 | 2018-09-23 | 2020-07-26 | 2020-10-23
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG033-017 | Roof Replacements | 5 | CONSTRUCTION TO 25% | 2018-09-24 | 2019-01-21 | 2020-10-24 | 2021-02-20
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG033-017 | Roof Replacements | 6 | CONSTRUCTION TO 50% | 2019-01-22 | 2019-05-21 | 2021-02-21 | 2021-06-20
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG033-017 | Roof Replacements | 7 | CONSTRUCTION TO 75% | 2019-05-22 | 2019-09-18 | 2021-06-21 | 2021-10-18
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG033-017 | Roof Replacements | 8 | ORIGINAL EQUIP & FURNISHING | 2019-09-19 | 2019-12-17 | 2021-10-19 | 2022-01-16
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG033-017 | Roof Replacements | 9 | SUBSTANTIAL COMPLETION | 2019-12-18 | 2020-02-15 | 2022-01-17 | 2022-03-17
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG033-017 | Roof Replacements | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-02-16 | 2020-03-16 | 2022-03-18 | 2022-04-16
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG043-018 | Campus Roadway Improvements | 1 | DEVELOP SCOPE | 2018-06-01 | 2018-08-29 | 2021-07-01 | 2021-09-29
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG043-018 | Campus Roadway Improvements | 2 | PRELIMINARY DESIGN | 2018-08-30 | 2018-12-27 | 2021-09-30 | 2022-01-27
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG043-018 | Campus Roadway Improvements | 3 | FINAL DESIGN | 2018-12-28 | 2019-06-25 | 2022-01-28 | 2022-07-26
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG043-018 | Campus Roadway Improvements | 4 | BID AWARD AND REGISTER CONTRCT | 2019-06-26 | 2019-09-23 | 2022-07-27 | 2022-10-24
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG043-018 | Campus Roadway Improvements | 5 | CONSTRUCTION TO 25% | 2019-09-24 | 2020-01-21 | 2022-10-25 | 2023-02-21
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG043-018 | Campus Roadway Improvements | 6 | CONSTRUCTION TO 50% | 2020-01-22 | 2020-05-20 | 2023-02-22 | 2023-06-21
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG043-018 | Campus Roadway Improvements | 7 | CONSTRUCTION TO 75% | 2020-05-21 | 2020-09-17 | 2023-06-22 | 2023-10-19
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG043-018 | Campus Roadway Improvements | 8 | ORIGINAL EQUIP & FURNISHING | 2020-09-18 | 2020-12-16 | 2023-10-20 | 2024-01-17
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG043-018 | Campus Roadway Improvements | 9 | SUBSTANTIAL COMPLETION | 2020-12-17 | 2021-02-14 | 2024-01-18 | 2024-03-17
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG043-018 | Campus Roadway Improvements | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-02-15 | 2021-03-16 | 2024-03-18 | 2024-07-16
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG044-020 | Marina Rehabilitation | 1 | DEVELOP SCOPE | 2020-06-30 | 2020-09-27 | 2020-06-30 | 2020-09-27
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG044-020 | Marina Rehabilitation | 2 | PRELIMINARY DESIGN | 2020-09-28 | 2021-01-25 | 2020-09-28 | 2021-01-25
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG044-020 | Marina Rehabilitation | 3 | FINAL DESIGN | 2021-01-26 | 2021-07-24 | 2021-01-26 | 2021-07-24
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG044-020 | Marina Rehabilitation | 4 | BID AWARD AND REGISTER CONTRCT | 2021-07-25 | 2021-10-22 | 2021-07-25 | 2021-10-22
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG044-020 | Marina Rehabilitation | 5 | CONSTRUCTION TO 25% | 2021-10-23 | 2022-02-19 | 2021-10-23 | 2022-02-19
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG044-020 | Marina Rehabilitation | 6 | CONSTRUCTION TO 50% | 2022-02-20 | 2022-06-19 | 2022-02-20 | 2022-06-19
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG044-020 | Marina Rehabilitation | 7 | CONSTRUCTION TO 75% | 2022-06-20 | 2022-10-17 | 2022-06-20 | 2022-10-17
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG044-020 | Marina Rehabilitation | 8 | ORIGINAL EQUIP & FURNISHING | 2022-10-18 | 2023-01-15 | 2022-10-18 | 2023-01-15
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG044-020 | Marina Rehabilitation | 9 | SUBSTANTIAL COMPLETION | 2023-01-16 | 2023-03-16 | 2023-01-16 | 2023-03-16
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG044-020 | Marina Rehabilitation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-03-17 | 2023-04-15 | 2023-03-17 | 2023-04-15
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG045-020 | Performing Arts Center Upgrades | 1 | DEVELOP SCOPE | 2020-06-30 | 2020-09-27 | 2020-06-30 | 2020-09-27
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG045-020 | Performing Arts Center Upgrades | 2 | PRELIMINARY DESIGN | 2020-09-28 | 2021-01-25 | 2020-09-28 | 2021-01-25
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG045-020 | Performing Arts Center Upgrades | 3 | FINAL DESIGN | 2021-01-26 | 2021-07-24 | 2021-01-26 | 2021-07-24
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG045-020 | Performing Arts Center Upgrades | 4 | BID AWARD AND REGISTER CONTRCT | 2021-07-25 | 2021-10-22 | 2021-07-25 | 2021-10-22
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG045-020 | Performing Arts Center Upgrades | 5 | CONSTRUCTION TO 25% | 2021-10-23 | 2022-02-19 | 2021-10-23 | 2022-02-19
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG045-020 | Performing Arts Center Upgrades | 6 | CONSTRUCTION TO 50% | 2022-02-20 | 2022-06-19 | 2022-02-20 | 2022-06-19
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG045-020 | Performing Arts Center Upgrades | 7 | CONSTRUCTION TO 75% | 2022-06-20 | 2022-10-17 | 2022-06-20 | 2022-10-17
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG045-020 | Performing Arts Center Upgrades | 8 | ORIGINAL EQUIP & FURNISHING | 2022-10-18 | 2023-01-15 | 2022-10-18 | 2023-01-15
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG045-020 | Performing Arts Center Upgrades | 9 | SUBSTANTIAL COMPLETION | 2023-01-16 | 2023-03-16 | 2023-01-16 | 2023-03-16
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG045-020 | Performing Arts Center Upgrades | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-03-17 | 2023-04-15 | 2023-03-17 | 2027-04-30
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG201-006 | Additional Roof Replacement | 1 | DEVELOP SCOPE | 2009-05-30 | 2009-08-27 | 2009-05-30 | 2009-08-27
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG201-006 | Additional Roof Replacement | 2 | PRELIMINARY DESIGN | 2009-08-28 | 2009-12-25 | 2009-08-28 | 2009-12-25
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG201-006 | Additional Roof Replacement | 3 | FINAL DESIGN | 2009-12-26 | 2010-06-23 | 2009-12-26 | 2010-06-23
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG201-006 | Additional Roof Replacement | 4 | BID AWARD AND REGISTER CONTRCT | 2010-06-24 | 2010-09-21 | 2010-06-24 | 2010-09-21
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG201-006 | Additional Roof Replacement | 5 | CONSTRUCTION TO 25% | 2010-09-22 | 2011-01-19 | 2010-09-22 | 2011-01-19
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG201-006 | Additional Roof Replacement | 6 | CONSTRUCTION TO 50% | 2011-01-20 | 2011-05-19 | 2011-01-20 | 2011-05-19
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG201-006 | Additional Roof Replacement | 7 | CONSTRUCTION TO 75% | 2011-05-20 | 2011-09-16 | 2011-05-20 | 2011-09-16
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG201-006 | Additional Roof Replacement | 8 | ORIGINAL EQUIP & FURNISHING | 2011-09-17 | 2011-12-15 | 2011-09-17 | 2011-12-15
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG201-006 | Additional Roof Replacement | 9 | SUBSTANTIAL COMPLETION | 2011-12-16 | 2012-02-13 | 2011-12-16 | 2012-02-13
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG201-006 | Additional Roof Replacement | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-02-14 | 2012-03-14 | 2012-02-14 | 2022-12-30
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG203-006 | Gymnasium | 1 | DEVELOP SCOPE | 2007-03-01 | 2007-05-29 | 2007-03-01 | 2007-05-29
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG203-006 | Gymnasium | 2 | PRELIMINARY DESIGN | 2007-05-30 | 2007-09-26 | 2007-05-30 | 2007-09-26
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG203-006 | Gymnasium | 3 | FINAL DESIGN | 2007-09-27 | 2008-03-24 | 2007-09-27 | 2008-03-24
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG203-006 | Gymnasium | 4 | BID AWARD AND REGISTER CONTRCT | 2008-03-25 | 2008-06-22 | 2008-03-25 | 2008-06-22
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG203-006 | Gymnasium | 5 | CONSTRUCTION TO 25% | 2008-06-23 | 2008-10-20 | 2008-06-23 | 2008-10-20
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG203-006 | Gymnasium | 6 | CONSTRUCTION TO 50% | 2008-10-21 | 2009-02-17 | 2008-10-21 | 2009-02-17
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG203-006 | Gymnasium | 7 | CONSTRUCTION TO 75% | 2009-02-18 | 2009-06-17 | 2009-02-18 | 2009-06-17
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG203-006 | Gymnasium | 8 | ORIGINAL EQUIP & FURNISHING | 2009-06-18 | 2009-09-15 | 2009-06-18 | 2009-09-15
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG203-006 | Gymnasium | 9 | SUBSTANTIAL COMPLETION | 2009-09-16 | 2009-11-14 | 2009-09-16 | 2009-11-14
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | KG203-006 | Gymnasium | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2009-11-15 | 2009-12-14 | 2009-11-15 | 2024-06-30
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME001-021 | Athletic Center | 1 | DEVELOP SCOPE | 2021-06-30 | 2021-09-27 | 2021-06-30 | 2021-09-27
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME001-021 | Athletic Center | 2 | PRELIMINARY DESIGN | 2021-09-28 | 2022-01-25 | 2021-09-28 | 2022-01-25
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME001-021 | Athletic Center | 3 | FINAL DESIGN | 2022-01-26 | 2022-07-24 | 2022-01-26 | 2022-07-24
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME001-021 | Athletic Center | 4 | BID AWARD AND REGISTER CONTRCT | 2022-07-25 | 2022-10-22 | 2022-07-25 | 2022-10-22
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME001-021 | Athletic Center | 5 | CONSTRUCTION TO 25% | 2022-10-23 | 2023-02-19 | 2022-10-23 | 2023-02-19
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME001-021 | Athletic Center | 6 | CONSTRUCTION TO 50% | 2023-02-20 | 2023-06-19 | 2023-02-20 | 2023-06-19
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME001-021 | Athletic Center | 7 | CONSTRUCTION TO 75% | 2023-06-20 | 2023-10-17 | 2023-06-20 | 2023-10-17
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME001-021 | Athletic Center | 8 | ORIGINAL EQUIP & FURNISHING | 2023-10-18 | 2024-01-15 | 2023-10-18 | 2024-01-15
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME001-021 | Athletic Center | 9 | SUBSTANTIAL COMPLETION | 2024-01-16 | 2024-03-15 | 2024-01-16 | 2024-03-15
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME001-021 | Athletic Center | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-03-16 | 2024-04-14 | 2024-03-16 | 2024-04-14
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME018-005 | LIBRARY EXPANSION | 1 | DEVELOP SCOPE | 2010-05-30 | 2010-05-30 | 2010-05-30 | 2010-05-30
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME018-005 | LIBRARY EXPANSION | 2 | PRELIMINARY DESIGN | 2010-05-31 | 2010-05-30 | 2010-05-31 | 2010-05-30
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME018-005 | LIBRARY EXPANSION | 3 | FINAL DESIGN | 2010-05-31 | 2010-05-30 | 2010-05-31 | 2010-05-30
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME018-005 | LIBRARY EXPANSION | 4 | BID AWARD AND REGISTER CONTRCT | 2010-05-31 | 2010-05-30 | 2010-05-31 | 2010-05-30
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME018-005 | LIBRARY EXPANSION | 5 | CONSTRUCTION TO 25% | 2015-06-04 | 2015-06-03 | 2015-06-04 | 2015-06-03
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME018-005 | LIBRARY EXPANSION | 6 | CONSTRUCTION TO 50% | 2015-06-04 | 2015-06-03 | 2015-06-04 | 2015-06-03
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME018-005 | LIBRARY EXPANSION | 7 | CONSTRUCTION TO 75% | 2015-06-04 | 2015-06-03 | 2015-06-04 | 2015-06-03
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME018-005 | LIBRARY EXPANSION | 8 | ORIGINAL EQUIP & FURNISHING | 2015-06-04 | 2015-06-03 | 2015-06-04 | 2015-06-03
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME018-005 | LIBRARY EXPANSION | 9 | SUBSTANTIAL COMPLETION | 2015-06-04 | 2015-06-03 | 2015-06-04 | 2015-06-03
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME018-005 | LIBRARY EXPANSION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-06-04 | 2015-07-03 | 2015-06-04 | 2024-07-31
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME027-011 | Carroll Street Building Upgrade | 1 | DEVELOP SCOPE | 2011-06-01 | 2011-08-29 | 2020-07-01 | 2020-09-28
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME027-011 | Carroll Street Building Upgrade | 2 | PRELIMINARY DESIGN | 2011-08-30 | 2011-12-27 | 2020-09-29 | 2021-01-26
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME027-011 | Carroll Street Building Upgrade | 3 | FINAL DESIGN | 2011-12-28 | 2012-06-24 | 2021-01-27 | 2021-07-25
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME027-011 | Carroll Street Building Upgrade | 4 | BID AWARD AND REGISTER CONTRCT | 2012-06-25 | 2012-09-22 | 2021-07-26 | 2021-10-23
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME027-011 | Carroll Street Building Upgrade | 5 | CONSTRUCTION TO 25% | 2012-09-23 | 2013-01-20 | 2021-10-24 | 2022-02-20
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME027-011 | Carroll Street Building Upgrade | 6 | CONSTRUCTION TO 50% | 2013-01-21 | 2013-05-20 | 2022-02-21 | 2022-06-20
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME027-011 | Carroll Street Building Upgrade | 7 | CONSTRUCTION TO 75% | 2013-05-21 | 2013-09-17 | 2022-06-21 | 2022-10-18
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME027-011 | Carroll Street Building Upgrade | 8 | ORIGINAL EQUIP & FURNISHING | 2013-09-18 | 2013-12-16 | 2022-10-19 | 2023-01-16
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME027-011 | Carroll Street Building Upgrade | 9 | SUBSTANTIAL COMPLETION | 2013-12-17 | 2014-02-14 | 2023-01-17 | 2023-03-17
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME027-011 | Carroll Street Building Upgrade | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-02-15 | 2014-03-16 | 2023-03-18 | 2023-04-16
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME031-013 | Virtual Desktop Infrastructure | 1 | DEVELOP SCOPE | 2013-06-01 | 2013-08-29 | 2013-06-01 | 2013-08-29
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME031-013 | Virtual Desktop Infrastructure | 2 | PRELIMINARY DESIGN | 2013-08-30 | 2013-12-27 | 2013-08-30 | 2013-12-27
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME031-013 | Virtual Desktop Infrastructure | 3 | FINAL DESIGN | 2013-12-28 | 2014-06-25 | 2013-12-28 | 2014-06-25
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME031-013 | Virtual Desktop Infrastructure | 4 | BID AWARD AND REGISTER CONTRCT | 2014-06-26 | 2014-09-23 | 2014-06-26 | 2014-09-23
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME031-013 | Virtual Desktop Infrastructure | 5 | CONSTRUCTION TO 25% | 2014-09-24 | 2015-01-21 | 2014-09-24 | 2015-01-21
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME031-013 | Virtual Desktop Infrastructure | 6 | CONSTRUCTION TO 50% | 2015-01-22 | 2015-05-21 | 2015-01-22 | 2015-05-21
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME031-013 | Virtual Desktop Infrastructure | 7 | CONSTRUCTION TO 75% | 2015-05-22 | 2015-09-18 | 2015-05-22 | 2015-09-18
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME031-013 | Virtual Desktop Infrastructure | 8 | ORIGINAL EQUIP & FURNISHING | 2015-09-19 | 2015-12-17 | 2015-09-19 | 2015-12-17
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME031-013 | Virtual Desktop Infrastructure | 9 | SUBSTANTIAL COMPLETION | 2015-12-18 | 2016-02-15 | 2015-12-18 | 2016-02-15
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME031-013 | Virtual Desktop Infrastructure | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-02-16 | 2016-03-16 | 2016-02-16 | 2023-03-31
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME037-016 | College Prep School Classroom Improvements | 1 | DEVELOP SCOPE | 2016-06-30 | 2016-09-27 | 2016-06-30 | 2016-09-27
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME037-016 | College Prep School Classroom Improvements | 2 | PRELIMINARY DESIGN | 2016-09-28 | 2017-01-25 | 2016-09-28 | 2017-01-25
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME037-016 | College Prep School Classroom Improvements | 3 | FINAL DESIGN | 2017-01-26 | 2017-07-24 | 2017-01-26 | 2017-07-24
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME037-016 | College Prep School Classroom Improvements | 4 | BID AWARD AND REGISTER CONTRCT | 2017-07-25 | 2017-10-22 | 2017-07-25 | 2017-10-22
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME037-016 | College Prep School Classroom Improvements | 5 | CONSTRUCTION TO 25% | 2017-10-23 | 2018-02-19 | 2017-10-23 | 2018-02-19
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME037-016 | College Prep School Classroom Improvements | 6 | CONSTRUCTION TO 50% | 2018-02-20 | 2018-06-19 | 2018-02-20 | 2018-06-19
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME037-016 | College Prep School Classroom Improvements | 7 | CONSTRUCTION TO 75% | 2018-06-20 | 2018-10-17 | 2018-06-20 | 2018-10-17
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME037-016 | College Prep School Classroom Improvements | 8 | ORIGINAL EQUIP & FURNISHING | 2018-10-18 | 2019-01-15 | 2018-10-18 | 2019-01-15
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME037-016 | College Prep School Classroom Improvements | 9 | SUBSTANTIAL COMPLETION | 2019-01-16 | 2019-03-16 | 2019-01-16 | 2019-03-16
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME037-016 | College Prep School Classroom Improvements | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-03-17 | 2019-04-15 | 2019-03-17 | 2025-04-30
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME038-016 | Child Development Center Upgrades | 1 | DEVELOP SCOPE | 2016-06-30 | 2016-09-27 | 2021-07-01 | 2021-09-28
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME038-016 | Child Development Center Upgrades | 2 | PRELIMINARY DESIGN | 2016-09-28 | 2017-01-25 | 2021-09-29 | 2022-01-26
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME038-016 | Child Development Center Upgrades | 3 | FINAL DESIGN | 2017-01-26 | 2017-07-24 | 2022-01-27 | 2022-07-25
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME038-016 | Child Development Center Upgrades | 4 | BID AWARD AND REGISTER CONTRCT | 2017-07-25 | 2017-10-22 | 2022-07-26 | 2022-10-23
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME038-016 | Child Development Center Upgrades | 5 | CONSTRUCTION TO 25% | 2017-10-23 | 2018-02-19 | 2022-10-24 | 2023-02-20
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME038-016 | Child Development Center Upgrades | 6 | CONSTRUCTION TO 50% | 2018-02-20 | 2018-06-19 | 2023-02-21 | 2023-06-20
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME038-016 | Child Development Center Upgrades | 7 | CONSTRUCTION TO 75% | 2018-06-20 | 2018-10-17 | 2023-06-21 | 2023-10-18
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME038-016 | Child Development Center Upgrades | 8 | ORIGINAL EQUIP & FURNISHING | 2018-10-18 | 2019-01-15 | 2023-10-19 | 2024-01-16
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME038-016 | Child Development Center Upgrades | 9 | SUBSTANTIAL COMPLETION | 2019-01-16 | 2019-03-16 | 2024-01-17 | 2024-03-16
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME038-016 | Child Development Center Upgrades | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-03-17 | 2019-04-15 | 2024-03-17 | 2024-04-15
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME039-017 | Student Lounge Upgrades | 1 | DEVELOP SCOPE | 2017-06-01 | 2017-08-29 | 2019-07-01 | 2019-09-28
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME039-017 | Student Lounge Upgrades | 2 | PRELIMINARY DESIGN | 2017-08-30 | 2017-12-27 | 2019-09-29 | 2020-01-26
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME039-017 | Student Lounge Upgrades | 3 | FINAL DESIGN | 2017-12-28 | 2018-06-25 | 2020-01-27 | 2020-07-24
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME039-017 | Student Lounge Upgrades | 4 | BID AWARD AND REGISTER CONTRCT | 2018-06-26 | 2018-09-23 | 2020-07-25 | 2020-10-22
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME039-017 | Student Lounge Upgrades | 5 | CONSTRUCTION TO 25% | 2018-09-24 | 2019-01-21 | 2020-10-23 | 2021-02-19
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME039-017 | Student Lounge Upgrades | 6 | CONSTRUCTION TO 50% | 2019-01-22 | 2019-05-21 | 2021-02-20 | 2021-06-19
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME039-017 | Student Lounge Upgrades | 7 | CONSTRUCTION TO 75% | 2019-05-22 | 2019-09-18 | 2021-06-20 | 2021-10-17
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME039-017 | Student Lounge Upgrades | 8 | ORIGINAL EQUIP & FURNISHING | 2019-09-19 | 2019-12-17 | 2021-10-18 | 2022-01-15
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME039-017 | Student Lounge Upgrades | 9 | SUBSTANTIAL COMPLETION | 2019-12-18 | 2020-02-15 | 2022-01-16 | 2022-03-16
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME039-017 | Student Lounge Upgrades | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-02-16 | 2020-03-16 | 2022-03-17 | 2022-04-15
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME040-018 | Differently-Abled Lab | 1 | DEVELOP SCOPE | 2018-06-01 | 2018-08-29 | 2018-06-01 | 2018-08-29
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME040-018 | Differently-Abled Lab | 2 | PRELIMINARY DESIGN | 2018-08-30 | 2018-12-27 | 2018-08-30 | 2018-12-27
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME040-018 | Differently-Abled Lab | 3 | FINAL DESIGN | 2018-12-28 | 2019-06-25 | 2018-12-28 | 2019-06-25
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME040-018 | Differently-Abled Lab | 4 | BID AWARD AND REGISTER CONTRCT | 2019-06-26 | 2019-09-23 | 2019-06-26 | 2019-09-23
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME040-018 | Differently-Abled Lab | 5 | CONSTRUCTION TO 25% | 2019-09-24 | 2020-01-21 | 2019-09-24 | 2020-01-21
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME040-018 | Differently-Abled Lab | 6 | CONSTRUCTION TO 50% | 2020-01-22 | 2020-05-20 | 2020-01-22 | 2020-05-20
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME040-018 | Differently-Abled Lab | 7 | CONSTRUCTION TO 75% | 2020-05-21 | 2020-09-17 | 2020-05-21 | 2020-09-17
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME040-018 | Differently-Abled Lab | 8 | ORIGINAL EQUIP & FURNISHING | 2020-09-18 | 2020-12-16 | 2020-09-18 | 2020-12-16
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME040-018 | Differently-Abled Lab | 9 | SUBSTANTIAL COMPLETION | 2020-12-17 | 2021-02-14 | 2020-12-17 | 2021-02-14
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME040-018 | Differently-Abled Lab | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-02-15 | 2021-03-16 | 2021-02-15 | 2024-03-31
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME041-018 | Art and Historic Space Renovation | 1 | DEVELOP SCOPE | 2018-06-01 | 2018-08-29 | 2022-07-01 | 2022-09-28
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME041-018 | Art and Historic Space Renovation | 2 | PRELIMINARY DESIGN | 2018-08-30 | 2018-12-27 | 2022-09-29 | 2023-01-26
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME041-018 | Art and Historic Space Renovation | 3 | FINAL DESIGN | 2018-12-28 | 2019-06-25 | 2023-01-27 | 2023-07-25
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME041-018 | Art and Historic Space Renovation | 4 | BID AWARD AND REGISTER CONTRCT | 2019-06-26 | 2019-09-23 | 2023-07-26 | 2023-10-23
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME041-018 | Art and Historic Space Renovation | 5 | CONSTRUCTION TO 25% | 2019-09-24 | 2020-01-21 | 2023-10-24 | 2024-02-20
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME041-018 | Art and Historic Space Renovation | 6 | CONSTRUCTION TO 50% | 2020-01-22 | 2020-05-20 | 2024-02-21 | 2024-06-19
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME041-018 | Art and Historic Space Renovation | 7 | CONSTRUCTION TO 75% | 2020-05-21 | 2020-09-17 | 2024-06-20 | 2024-10-17
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME041-018 | Art and Historic Space Renovation | 8 | ORIGINAL EQUIP & FURNISHING | 2020-09-18 | 2020-12-16 | 2024-10-18 | 2025-01-15
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME041-018 | Art and Historic Space Renovation | 9 | SUBSTANTIAL COMPLETION | 2020-12-17 | 2021-02-14 | 2025-01-16 | 2025-03-16
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME041-018 | Art and Historic Space Renovation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-02-15 | 2021-03-16 | 2025-03-17 | 2025-04-15
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME042-019 | Founder's Auditorium Renovation & Upgrades | 1 | DEVELOP SCOPE | 2019-06-30 | 2019-09-27 | 2022-07-01 | 2022-09-28
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME042-019 | Founder's Auditorium Renovation & Upgrades | 2 | PRELIMINARY DESIGN | 2019-09-28 | 2020-01-25 | 2022-09-29 | 2023-01-26
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME042-019 | Founder's Auditorium Renovation & Upgrades | 3 | FINAL DESIGN | 2020-01-26 | 2020-07-23 | 2023-01-27 | 2023-07-25
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME042-019 | Founder's Auditorium Renovation & Upgrades | 4 | BID AWARD AND REGISTER CONTRCT | 2020-07-24 | 2020-10-21 | 2023-07-26 | 2023-10-23
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME042-019 | Founder's Auditorium Renovation & Upgrades | 5 | CONSTRUCTION TO 25% | 2020-10-22 | 2021-02-18 | 2023-10-24 | 2024-02-20
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME042-019 | Founder's Auditorium Renovation & Upgrades | 6 | CONSTRUCTION TO 50% | 2021-02-19 | 2021-06-18 | 2024-02-21 | 2024-06-19
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME042-019 | Founder's Auditorium Renovation & Upgrades | 7 | CONSTRUCTION TO 75% | 2021-06-19 | 2021-10-16 | 2024-06-20 | 2024-10-17
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME042-019 | Founder's Auditorium Renovation & Upgrades | 8 | ORIGINAL EQUIP & FURNISHING | 2021-10-17 | 2022-01-14 | 2024-10-18 | 2025-01-15
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME042-019 | Founder's Auditorium Renovation & Upgrades | 9 | SUBSTANTIAL COMPLETION | 2022-01-15 | 2022-03-15 | 2025-01-16 | 2025-03-16
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME042-019 | Founder's Auditorium Renovation & Upgrades | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-16 | 2022-04-14 | 2025-03-17 | 2025-04-15
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME043-020 | Open Computer and Lab Digital Interactive Learning Spaces | 1 | DEVELOP SCOPE | 2021-07-01 | 2021-09-28 | 2021-07-01 | 2021-09-28
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME043-020 | Open Computer and Lab Digital Interactive Learning Spaces | 2 | PRELIMINARY DESIGN | 2021-09-29 | 2022-01-26 | 2021-09-29 | 2022-01-26
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME043-020 | Open Computer and Lab Digital Interactive Learning Spaces | 3 | FINAL DESIGN | 2022-01-27 | 2022-07-25 | 2022-01-27 | 2022-07-25
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME043-020 | Open Computer and Lab Digital Interactive Learning Spaces | 4 | BID AWARD AND REGISTER CONTRCT | 2022-07-26 | 2022-10-23 | 2022-07-26 | 2022-10-23
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME043-020 | Open Computer and Lab Digital Interactive Learning Spaces | 5 | CONSTRUCTION TO 25% | 2022-10-24 | 2023-02-20 | 2022-10-24 | 2023-02-20
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME043-020 | Open Computer and Lab Digital Interactive Learning Spaces | 6 | CONSTRUCTION TO 50% | 2023-02-21 | 2023-06-20 | 2023-02-21 | 2023-06-20
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME043-020 | Open Computer and Lab Digital Interactive Learning Spaces | 7 | CONSTRUCTION TO 75% | 2023-06-21 | 2023-10-18 | 2023-06-21 | 2023-10-18
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME043-020 | Open Computer and Lab Digital Interactive Learning Spaces | 8 | ORIGINAL EQUIP & FURNISHING | 2023-10-19 | 2024-01-16 | 2023-10-19 | 2024-01-16
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME043-020 | Open Computer and Lab Digital Interactive Learning Spaces | 9 | SUBSTANTIAL COMPLETION | 2024-01-17 | 2024-03-16 | 2024-01-17 | 2024-03-16
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME043-020 | Open Computer and Lab Digital Interactive Learning Spaces | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-03-17 | 2024-04-15 | 2024-03-17 | 2024-04-15
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME044-020 | Athletic Center | 1 | DEVELOP SCOPE | 2020-07-01 | 2020-09-28 | 2020-06-01 | 2020-09-01
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME044-020 | Athletic Center | 2 | PRELIMINARY DESIGN | 2020-09-29 | 2021-01-26 | 2020-09-02 | 2020-12-30
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME044-020 | Athletic Center | 3 | FINAL DESIGN | 2021-01-27 | 2021-07-25 | 2020-12-31 | 2021-06-28
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME044-020 | Athletic Center | 4 | BID AWARD AND REGISTER CONTRCT | 2021-07-26 | 2021-10-23 | 2021-06-29 | 2021-09-26
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME044-020 | Athletic Center | 5 | CONSTRUCTION TO 25% | 2021-10-24 | 2022-02-20 | 2021-09-27 | 2022-01-24
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME044-020 | Athletic Center | 6 | CONSTRUCTION TO 50% | 2022-02-21 | 2022-06-20 | 2022-01-25 | 2022-05-24
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME044-020 | Athletic Center | 7 | CONSTRUCTION TO 75% | 2022-06-21 | 2022-10-18 | 2022-05-25 | 2022-09-21
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME044-020 | Athletic Center | 8 | ORIGINAL EQUIP & FURNISHING | 2022-10-19 | 2023-01-16 | 2022-09-22 | 2022-12-20
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME044-020 | Athletic Center | 9 | SUBSTANTIAL COMPLETION | 2023-01-17 | 2023-03-17 | 2022-12-21 | 2023-02-18
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | ME044-020 | Athletic Center | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-03-18 | 2023-04-16 | 2023-02-19 | 2023-03-20
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY006-009 | WELCOME CENTER AND ART GALLERY | 3 | FINAL DESIGN | 2009-12-28 | 2010-06-25 | 2009-12-28 | 2010-06-25
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY006-009 | WELCOME CENTER AND ART GALLERY | 4 | BID AWARD AND REGISTER CONTRCT | 2010-06-26 | 2010-09-23 | 2010-06-26 | 2010-09-23
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY006-009 | WELCOME CENTER AND ART GALLERY | 5 | CONSTRUCTION TO 25% | 2010-09-24 | 2011-01-21 | 2010-09-24 | 2011-01-21
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY006-009 | WELCOME CENTER AND ART GALLERY | 6 | CONSTRUCTION TO 50% | 2011-01-22 | 2011-05-21 | 2011-01-22 | 2011-05-21
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY006-009 | WELCOME CENTER AND ART GALLERY | 7 | CONSTRUCTION TO 75% | 2011-05-22 | 2011-09-18 | 2011-05-22 | 2011-09-18
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY006-009 | WELCOME CENTER AND ART GALLERY | 8 | ORIGINAL EQUIP & FURNISHING | 2011-09-19 | 2011-12-17 | 2011-09-19 | 2011-12-17
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY006-009 | WELCOME CENTER AND ART GALLERY | 9 | SUBSTANTIAL COMPLETION | 2011-12-18 | 2012-02-15 | 2011-12-18 | 2012-02-15
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY006-009 | WELCOME CENTER AND ART GALLERY | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-02-16 | 2012-03-16 | 2012-02-16 | 2021-06-30
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY008-010 | Student Lounge/Eating/Study Space Build-out | 1 | DEVELOP SCOPE | 2010-06-01 | 2010-08-29 | 2020-07-01 | 2020-09-28
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY008-010 | Student Lounge/Eating/Study Space Build-out | 2 | PRELIMINARY DESIGN | 2010-08-30 | 2010-12-27 | 2020-09-29 | 2021-01-26
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY008-010 | Student Lounge/Eating/Study Space Build-out | 3 | FINAL DESIGN | 2010-12-28 | 2011-06-25 | 2021-01-27 | 2021-07-25
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY008-010 | Student Lounge/Eating/Study Space Build-out | 4 | BID AWARD AND REGISTER CONTRCT | 2011-06-26 | 2011-09-23 | 2021-07-26 | 2021-10-23
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY008-010 | Student Lounge/Eating/Study Space Build-out | 5 | CONSTRUCTION TO 25% | 2011-09-24 | 2012-01-21 | 2021-10-24 | 2022-02-20
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY008-010 | Student Lounge/Eating/Study Space Build-out | 6 | CONSTRUCTION TO 50% | 2012-01-22 | 2012-05-20 | 2022-02-21 | 2022-06-20
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY008-010 | Student Lounge/Eating/Study Space Build-out | 7 | CONSTRUCTION TO 75% | 2012-05-21 | 2012-09-17 | 2022-06-21 | 2022-10-18
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY008-010 | Student Lounge/Eating/Study Space Build-out | 8 | ORIGINAL EQUIP & FURNISHING | 2012-09-18 | 2012-12-16 | 2022-10-19 | 2023-01-16
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY008-010 | Student Lounge/Eating/Study Space Build-out | 9 | SUBSTANTIAL COMPLETION | 2012-12-17 | 2013-02-14 | 2023-01-17 | 2023-03-17
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY008-010 | Student Lounge/Eating/Study Space Build-out | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-02-15 | 2013-03-16 | 2023-03-18 | 2027-04-16
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY010-011 | Library And Student Facilities Upgrade | 1 | DEVELOP SCOPE | 2011-06-01 | 2011-08-29 | 2020-07-01 | 2020-09-28
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY010-011 | Library And Student Facilities Upgrade | 2 | PRELIMINARY DESIGN | 2011-08-30 | 2011-12-27 | 2020-09-29 | 2021-01-26
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY010-011 | Library And Student Facilities Upgrade | 3 | FINAL DESIGN | 2011-12-28 | 2012-06-24 | 2021-01-27 | 2021-07-25
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY010-011 | Library And Student Facilities Upgrade | 4 | BID AWARD AND REGISTER CONTRCT | 2012-06-25 | 2012-09-22 | 2021-07-26 | 2021-10-23
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY010-011 | Library And Student Facilities Upgrade | 5 | CONSTRUCTION TO 25% | 2012-09-23 | 2013-01-20 | 2021-10-24 | 2022-02-20
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY010-011 | Library And Student Facilities Upgrade | 6 | CONSTRUCTION TO 50% | 2013-01-21 | 2013-05-20 | 2022-02-21 | 2022-06-20
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY010-011 | Library And Student Facilities Upgrade | 7 | CONSTRUCTION TO 75% | 2013-05-21 | 2013-09-17 | 2022-06-21 | 2022-10-18
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY010-011 | Library And Student Facilities Upgrade | 8 | ORIGINAL EQUIP & FURNISHING | 2013-09-18 | 2013-12-16 | 2022-10-19 | 2023-01-16
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY010-011 | Library And Student Facilities Upgrade | 9 | SUBSTANTIAL COMPLETION | 2013-12-17 | 2014-02-14 | 2023-01-17 | 2023-03-17
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY010-011 | Library And Student Facilities Upgrade | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-02-15 | 2014-03-16 | 2023-03-18 | 2023-04-16
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY012-011 | Initial Outfitting of the Biological Science Labs | 1 | DEVELOP SCOPE | 2018-06-01 | 2018-08-29 | 2018-06-01 | 2018-08-29
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY012-011 | Initial Outfitting of the Biological Science Labs | 2 | PRELIMINARY DESIGN | 2018-08-30 | 2018-12-27 | 2018-08-30 | 2018-12-27
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY012-011 | Initial Outfitting of the Biological Science Labs | 3 | FINAL DESIGN | 2018-12-28 | 2019-06-25 | 2018-12-28 | 2019-06-25
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY012-011 | Initial Outfitting of the Biological Science Labs | 4 | BID AWARD AND REGISTER CONTRCT | 2019-06-26 | 2019-09-23 | 2019-06-26 | 2019-09-23
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY012-011 | Initial Outfitting of the Biological Science Labs | 5 | CONSTRUCTION TO 25% | 2019-09-24 | 2020-01-21 | 2019-09-24 | 2020-01-21
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY012-011 | Initial Outfitting of the Biological Science Labs | 6 | CONSTRUCTION TO 50% | 2020-01-22 | 2020-05-20 | 2020-01-22 | 2020-05-20
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY012-011 | Initial Outfitting of the Biological Science Labs | 7 | CONSTRUCTION TO 75% | 2020-05-21 | 2020-09-17 | 2020-05-21 | 2020-09-17
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY012-011 | Initial Outfitting of the Biological Science Labs | 8 | ORIGINAL EQUIP & FURNISHING | 2020-09-18 | 2020-12-16 | 2020-09-18 | 2020-12-16
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY012-011 | Initial Outfitting of the Biological Science Labs | 9 | SUBSTANTIAL COMPLETION | 2020-12-17 | 2021-02-14 | 2020-12-17 | 2021-02-14
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY012-011 | Initial Outfitting of the Biological Science Labs | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-02-15 | 2021-03-16 | 2021-02-15 | 2027-03-31
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY013-012 | Network Upgrades | 1 | DEVELOP SCOPE | 2012-06-01 | 2012-08-29 | 2012-06-01 | 2012-08-29
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY013-012 | Network Upgrades | 2 | PRELIMINARY DESIGN | 2012-08-30 | 2012-12-27 | 2012-08-30 | 2012-12-27
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY013-012 | Network Upgrades | 3 | FINAL DESIGN | 2012-12-28 | 2013-06-25 | 2012-12-28 | 2013-06-25
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY013-012 | Network Upgrades | 4 | BID AWARD AND REGISTER CONTRCT | 2013-06-26 | 2013-09-23 | 2013-06-26 | 2013-09-23
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY013-012 | Network Upgrades | 5 | CONSTRUCTION TO 25% | 2013-09-24 | 2014-01-21 | 2013-09-24 | 2014-01-21
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY013-012 | Network Upgrades | 6 | CONSTRUCTION TO 50% | 2014-01-22 | 2014-05-21 | 2014-01-22 | 2014-05-21
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY013-012 | Network Upgrades | 7 | CONSTRUCTION TO 75% | 2014-05-22 | 2014-09-18 | 2014-05-22 | 2014-09-18
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY013-012 | Network Upgrades | 8 | ORIGINAL EQUIP & FURNISHING | 2014-09-19 | 2014-12-17 | 2014-09-19 | 2014-12-17
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY013-012 | Network Upgrades | 9 | SUBSTANTIAL COMPLETION | 2014-12-18 | 2015-02-15 | 2014-12-18 | 2015-02-15
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY013-012 | Network Upgrades | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-02-16 | 2015-03-17 | 2015-02-16 | 2024-12-30
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY014-013 | Upgrade of Hospitality and Culinary Arts Facilities | 1 | DEVELOP SCOPE | 2013-06-01 | 2013-08-29 | 2021-07-01 | 2021-09-28
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY014-013 | Upgrade of Hospitality and Culinary Arts Facilities | 2 | PRELIMINARY DESIGN | 2013-08-30 | 2013-12-27 | 2021-09-29 | 2022-01-26
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY014-013 | Upgrade of Hospitality and Culinary Arts Facilities | 3 | FINAL DESIGN | 2013-12-28 | 2014-06-25 | 2022-01-27 | 2022-07-25
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY014-013 | Upgrade of Hospitality and Culinary Arts Facilities | 4 | BID AWARD AND REGISTER CONTRCT | 2014-06-26 | 2014-09-23 | 2022-07-26 | 2022-10-23
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY014-013 | Upgrade of Hospitality and Culinary Arts Facilities | 5 | CONSTRUCTION TO 25% | 2014-09-24 | 2015-01-21 | 2022-10-24 | 2023-02-20
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY014-013 | Upgrade of Hospitality and Culinary Arts Facilities | 6 | CONSTRUCTION TO 50% | 2015-01-22 | 2015-05-21 | 2023-02-21 | 2023-06-20
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY014-013 | Upgrade of Hospitality and Culinary Arts Facilities | 7 | CONSTRUCTION TO 75% | 2015-05-22 | 2015-09-18 | 2023-06-21 | 2023-10-18
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY014-013 | Upgrade of Hospitality and Culinary Arts Facilities | 8 | ORIGINAL EQUIP & FURNISHING | 2015-09-19 | 2015-12-17 | 2023-10-19 | 2024-01-16
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY014-013 | Upgrade of Hospitality and Culinary Arts Facilities | 9 | SUBSTANTIAL COMPLETION | 2015-12-18 | 2016-02-15 | 2024-01-17 | 2024-03-16
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY014-013 | Upgrade of Hospitality and Culinary Arts Facilities | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-02-16 | 2016-03-16 | 2024-03-17 | 2024-04-15
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY018-014 | Dental Hygiene Facilities Upgrade | 1 | DEVELOP SCOPE | 2014-06-01 | 2014-08-29 | 2021-07-01 | 2021-09-28
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY018-014 | Dental Hygiene Facilities Upgrade | 2 | PRELIMINARY DESIGN | 2014-08-30 | 2014-12-27 | 2021-09-29 | 2022-01-26
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY018-014 | Dental Hygiene Facilities Upgrade | 3 | FINAL DESIGN | 2014-12-28 | 2015-06-25 | 2022-01-27 | 2022-07-25
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY018-014 | Dental Hygiene Facilities Upgrade | 4 | BID AWARD AND REGISTER CONTRCT | 2015-06-26 | 2015-09-23 | 2022-07-26 | 2022-10-23
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY018-014 | Dental Hygiene Facilities Upgrade | 5 | CONSTRUCTION TO 25% | 2015-09-24 | 2016-01-21 | 2022-10-24 | 2023-02-20
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY018-014 | Dental Hygiene Facilities Upgrade | 6 | CONSTRUCTION TO 50% | 2016-01-22 | 2016-05-20 | 2023-02-21 | 2023-06-20
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY018-014 | Dental Hygiene Facilities Upgrade | 7 | CONSTRUCTION TO 75% | 2016-05-21 | 2016-09-17 | 2023-06-21 | 2023-10-18
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY018-014 | Dental Hygiene Facilities Upgrade | 8 | ORIGINAL EQUIP & FURNISHING | 2016-09-18 | 2016-12-16 | 2023-10-19 | 2024-01-16
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY018-014 | Dental Hygiene Facilities Upgrade | 9 | SUBSTANTIAL COMPLETION | 2016-12-17 | 2017-02-14 | 2024-01-17 | 2024-03-16
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY018-014 | Dental Hygiene Facilities Upgrade | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-02-15 | 2017-03-16 | 2024-03-17 | 2027-04-30
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY019-015 | Fabrication Laboratory | 1 | DEVELOP SCOPE | 2015-03-01 | 2015-05-29 | 2020-07-01 | 2020-09-28
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY019-015 | Fabrication Laboratory | 2 | PRELIMINARY DESIGN | 2015-05-30 | 2015-09-26 | 2020-09-29 | 2021-01-26
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY019-015 | Fabrication Laboratory | 3 | FINAL DESIGN | 2015-09-27 | 2016-03-24 | 2021-01-27 | 2021-07-25
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY019-015 | Fabrication Laboratory | 4 | BID AWARD AND REGISTER CONTRCT | 2016-03-25 | 2016-06-22 | 2021-07-26 | 2021-10-23
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY019-015 | Fabrication Laboratory | 5 | CONSTRUCTION TO 25% | 2016-06-23 | 2016-10-20 | 2021-10-24 | 2022-02-20
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY019-015 | Fabrication Laboratory | 6 | CONSTRUCTION TO 50% | 2016-10-21 | 2017-02-17 | 2022-02-21 | 2022-06-20
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY019-015 | Fabrication Laboratory | 7 | CONSTRUCTION TO 75% | 2017-02-18 | 2017-06-17 | 2022-06-21 | 2022-10-18
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY019-015 | Fabrication Laboratory | 8 | ORIGINAL EQUIP & FURNISHING | 2017-06-18 | 2017-09-15 | 2022-10-19 | 2023-01-16
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY019-015 | Fabrication Laboratory | 9 | SUBSTANTIAL COMPLETION | 2017-09-16 | 2017-11-14 | 2023-01-17 | 2023-03-17
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY019-015 | Fabrication Laboratory | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-11-15 | 2017-12-14 | 2023-03-18 | 2027-04-30
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY020-015 | Academic Learning Center Renovations | 1 | DEVELOP SCOPE | 2014-10-01 | 2014-12-29 | 2014-10-01 | 2014-12-29
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY020-015 | Academic Learning Center Renovations | 2 | PRELIMINARY DESIGN | 2014-12-30 | 2015-04-28 | 2014-12-30 | 2015-04-28
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY020-015 | Academic Learning Center Renovations | 3 | FINAL DESIGN | 2015-04-29 | 2015-10-25 | 2015-04-29 | 2015-10-25
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY020-015 | Academic Learning Center Renovations | 4 | BID AWARD AND REGISTER CONTRCT | 2015-10-26 | 2016-01-23 | 2015-10-26 | 2016-01-23
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY020-015 | Academic Learning Center Renovations | 5 | CONSTRUCTION TO 25% | 2016-01-24 | 2016-05-22 | 2016-01-24 | 2016-05-22
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY020-015 | Academic Learning Center Renovations | 6 | CONSTRUCTION TO 50% | 2016-05-23 | 2016-09-19 | 2016-05-23 | 2016-09-19
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY020-015 | Academic Learning Center Renovations | 7 | CONSTRUCTION TO 75% | 2016-09-20 | 2017-01-17 | 2016-09-20 | 2017-01-17
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY020-015 | Academic Learning Center Renovations | 8 | ORIGINAL EQUIP & FURNISHING | 2017-01-18 | 2017-04-17 | 2017-01-18 | 2017-04-17
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY020-015 | Academic Learning Center Renovations | 9 | SUBSTANTIAL COMPLETION | 2017-04-18 | 2017-06-16 | 2017-04-18 | 2017-06-16
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY020-015 | Academic Learning Center Renovations | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-06-17 | 2017-07-16 | 2017-06-17 | 2027-07-31
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY021-016 | Academic Learning Center Renovations and Equipment | 1 | DEVELOP SCOPE | 2016-06-30 | 2016-09-27 | 2016-06-30 | 2016-09-27
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY021-016 | Academic Learning Center Renovations and Equipment | 2 | PRELIMINARY DESIGN | 2016-09-28 | 2017-01-25 | 2016-09-28 | 2017-01-25
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY021-016 | Academic Learning Center Renovations and Equipment | 3 | FINAL DESIGN | 2017-01-26 | 2017-07-24 | 2017-01-26 | 2017-07-24
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY021-016 | Academic Learning Center Renovations and Equipment | 4 | BID AWARD AND REGISTER CONTRCT | 2017-07-25 | 2017-10-22 | 2017-07-25 | 2017-10-22
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY021-016 | Academic Learning Center Renovations and Equipment | 5 | CONSTRUCTION TO 25% | 2017-10-23 | 2018-02-19 | 2017-10-23 | 2018-02-19
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY021-016 | Academic Learning Center Renovations and Equipment | 6 | CONSTRUCTION TO 50% | 2018-02-20 | 2018-06-19 | 2018-02-20 | 2018-06-19
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY021-016 | Academic Learning Center Renovations and Equipment | 7 | CONSTRUCTION TO 75% | 2018-06-20 | 2018-10-17 | 2018-06-20 | 2018-10-17
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY021-016 | Academic Learning Center Renovations and Equipment | 8 | ORIGINAL EQUIP & FURNISHING | 2018-10-18 | 2019-01-15 | 2018-10-18 | 2019-01-15
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY021-016 | Academic Learning Center Renovations and Equipment | 9 | SUBSTANTIAL COMPLETION | 2019-01-16 | 2019-03-16 | 2019-01-16 | 2019-03-16
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY021-016 | Academic Learning Center Renovations and Equipment | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-03-17 | 2019-04-15 | 2019-03-17 | 2027-06-30
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY023-017 | Science Lab Renovations | 1 | DEVELOP SCOPE | 2017-06-01 | 2017-08-29 | 2020-07-01 | 2020-09-28
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY023-017 | Science Lab Renovations | 2 | PRELIMINARY DESIGN | 2017-08-30 | 2017-12-27 | 2020-09-29 | 2021-01-26
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY023-017 | Science Lab Renovations | 3 | FINAL DESIGN | 2017-12-28 | 2018-06-25 | 2021-01-27 | 2021-07-25
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY023-017 | Science Lab Renovations | 4 | BID AWARD AND REGISTER CONTRCT | 2018-06-26 | 2018-09-23 | 2021-07-26 | 2021-10-23
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY023-017 | Science Lab Renovations | 5 | CONSTRUCTION TO 25% | 2018-09-24 | 2019-01-21 | 2021-10-24 | 2022-02-20
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY023-017 | Science Lab Renovations | 6 | CONSTRUCTION TO 50% | 2019-01-22 | 2019-05-21 | 2022-02-21 | 2022-06-20
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY023-017 | Science Lab Renovations | 7 | CONSTRUCTION TO 75% | 2019-05-22 | 2019-09-18 | 2022-06-21 | 2022-10-18
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY023-017 | Science Lab Renovations | 8 | ORIGINAL EQUIP & FURNISHING | 2019-09-19 | 2019-12-17 | 2022-10-19 | 2023-01-16
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY023-017 | Science Lab Renovations | 9 | SUBSTANTIAL COMPLETION | 2019-12-18 | 2020-02-15 | 2023-01-17 | 2023-03-17
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY023-017 | Science Lab Renovations | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-02-16 | 2020-03-16 | 2023-03-18 | 2023-04-16
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY024-018 | Exterior Space Improvements | 1 | DEVELOP SCOPE | 2018-06-01 | 2018-08-29 | 2020-07-30 | 2020-09-28
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY024-018 | Exterior Space Improvements | 2 | PRELIMINARY DESIGN | 2018-08-30 | 2018-12-27 | 2020-09-29 | 2021-01-26
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY024-018 | Exterior Space Improvements | 3 | FINAL DESIGN | 2018-12-28 | 2019-06-25 | 2021-01-27 | 2021-07-25
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY024-018 | Exterior Space Improvements | 4 | BID AWARD AND REGISTER CONTRCT | 2019-06-26 | 2019-09-23 | 2021-07-26 | 2021-10-23
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY024-018 | Exterior Space Improvements | 5 | CONSTRUCTION TO 25% | 2019-09-24 | 2020-01-21 | 2021-10-24 | 2022-02-20
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY024-018 | Exterior Space Improvements | 6 | CONSTRUCTION TO 50% | 2020-01-22 | 2020-05-20 | 2022-02-21 | 2022-06-20
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY024-018 | Exterior Space Improvements | 7 | CONSTRUCTION TO 75% | 2020-05-21 | 2020-09-17 | 2022-06-21 | 2022-10-18
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY024-018 | Exterior Space Improvements | 8 | ORIGINAL EQUIP & FURNISHING | 2020-09-18 | 2020-12-16 | 2022-10-19 | 2023-01-16
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY024-018 | Exterior Space Improvements | 9 | SUBSTANTIAL COMPLETION | 2020-12-17 | 2021-02-14 | 2023-01-17 | 2023-03-17
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY024-018 | Exterior Space Improvements | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-02-15 | 2021-03-16 | 2023-03-18 | 2023-04-17
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY025-018 | Pearl Street Building Renovation | 1 | DEVELOP SCOPE | 2018-06-01 | 2018-08-29 | 2018-07-01 | 2018-09-01
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY025-018 | Pearl Street Building Renovation | 2 | PRELIMINARY DESIGN | 2018-08-30 | 2018-12-27 | 2018-09-02 | 2018-12-30
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY025-018 | Pearl Street Building Renovation | 3 | FINAL DESIGN | 2018-12-28 | 2019-06-25 | 2018-12-31 | 2019-06-28
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY025-018 | Pearl Street Building Renovation | 4 | BID AWARD AND REGISTER CONTRCT | 2019-06-26 | 2019-09-23 | 2019-06-29 | 2019-09-26
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY025-018 | Pearl Street Building Renovation | 5 | CONSTRUCTION TO 25% | 2019-09-24 | 2020-01-21 | 2021-10-01 | 2022-04-01
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY025-018 | Pearl Street Building Renovation | 6 | CONSTRUCTION TO 50% | 2020-01-22 | 2020-05-20 | 2022-04-02 | 2022-07-30
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY025-018 | Pearl Street Building Renovation | 7 | CONSTRUCTION TO 75% | 2020-05-21 | 2020-09-17 | 2022-07-31 | 2022-11-27
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY025-018 | Pearl Street Building Renovation | 8 | ORIGINAL EQUIP & FURNISHING | 2020-09-18 | 2020-12-16 | 2022-11-28 | 2023-02-25
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY025-018 | Pearl Street Building Renovation | 9 | SUBSTANTIAL COMPLETION | 2020-12-17 | 2021-02-14 | 2023-02-26 | 2023-04-26
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY025-018 | Pearl Street Building Renovation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-02-15 | 2021-03-16 | 2023-04-27 | 2023-05-26
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY028-020 | Pearl Building Renovations | 1 | DEVELOP SCOPE | 2020-07-01 | 2020-09-29 | 2020-07-01 | 2020-09-29
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY028-020 | Pearl Building Renovations | 2 | PRELIMINARY DESIGN | 2020-09-30 | 2021-01-27 | 2020-09-30 | 2021-01-27
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY028-020 | Pearl Building Renovations | 3 | FINAL DESIGN | 2021-01-28 | 2021-07-26 | 2021-01-28 | 2021-07-26
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY028-020 | Pearl Building Renovations | 4 | BID AWARD AND REGISTER CONTRCT | 2021-07-27 | 2021-10-24 | 2021-07-27 | 2021-10-24
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY028-020 | Pearl Building Renovations | 5 | CONSTRUCTION TO 25% | 2021-10-25 | 2022-02-21 | 2021-10-25 | 2022-02-21
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY028-020 | Pearl Building Renovations | 6 | CONSTRUCTION TO 50% | 2022-02-22 | 2022-06-21 | 2022-02-22 | 2022-06-21
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY028-020 | Pearl Building Renovations | 7 | CONSTRUCTION TO 75% | 2022-06-22 | 2022-10-19 | 2022-06-22 | 2022-10-19
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY028-020 | Pearl Building Renovations | 8 | ORIGINAL EQUIP & FURNISHING | 2022-10-20 | 2023-01-17 | 2022-10-20 | 2023-01-17
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY028-020 | Pearl Building Renovations | 9 | SUBSTANTIAL COMPLETION | 2023-01-18 | 2023-03-18 | 2023-01-18 | 2023-03-18
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | NY028-020 | Pearl Building Renovations | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-03-19 | 2023-04-17 | 2023-03-19 | 2023-04-17
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | SAND-KG02 | HVAC Repair/Replacement - Sandy Related | 1 | DEVELOP SCOPE | 2014-06-01 | 2014-08-29 | 2014-06-01 | 2014-08-29
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | SAND-KG02 | HVAC Repair/Replacement - Sandy Related | 2 | PRELIMINARY DESIGN | 2014-08-30 | 2014-12-27 | 2014-08-30 | 2014-12-27
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | SAND-KG02 | HVAC Repair/Replacement - Sandy Related | 3 | FINAL DESIGN | 2014-12-28 | 2015-06-25 | 2014-12-28 | 2015-06-25
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | SAND-KG02 | HVAC Repair/Replacement - Sandy Related | 4 | BID AWARD AND REGISTER CONTRCT | 2015-06-26 | 2015-09-23 | 2015-06-26 | 2015-09-23
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | SAND-KG02 | HVAC Repair/Replacement - Sandy Related | 5 | CONSTRUCTION TO 25% | 2015-09-24 | 2016-01-21 | 2015-09-24 | 2016-01-21
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | SAND-KG02 | HVAC Repair/Replacement - Sandy Related | 6 | CONSTRUCTION TO 50% | 2016-01-22 | 2016-05-20 | 2016-01-22 | 2016-05-20
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | SAND-KG02 | HVAC Repair/Replacement - Sandy Related | 7 | CONSTRUCTION TO 75% | 2016-05-21 | 2016-09-17 | 2016-05-21 | 2016-09-17
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | SAND-KG02 | HVAC Repair/Replacement - Sandy Related | 8 | ORIGINAL EQUIP & FURNISHING | 2016-09-18 | 2016-12-16 | 2016-09-18 | 2016-12-16
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | SAND-KG02 | HVAC Repair/Replacement - Sandy Related | 9 | SUBSTANTIAL COMPLETION | 2016-12-17 | 2017-02-14 | 2016-12-17 | 2017-02-14
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | SAND-KG02 | HVAC Repair/Replacement - Sandy Related | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-02-15 | 2017-03-16 | 2017-02-15 | 2023-03-31
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | SAND-KG03 | Marina Reconstruction | 1 | DEVELOP SCOPE | 2015-03-01 | 2015-05-29 | 2014-06-03 | 2014-08-31
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | SAND-KG03 | Marina Reconstruction | 2 | PRELIMINARY DESIGN | 2015-05-30 | 2015-09-26 | 2014-09-01 | 2015-08-31
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | SAND-KG03 | Marina Reconstruction | 3 | FINAL DESIGN | 2015-09-27 | 2016-03-24 | 2015-09-01 | 2019-05-01
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | SAND-KG03 | Marina Reconstruction | 4 | BID AWARD AND REGISTER CONTRCT | 2016-03-25 | 2016-06-22 | 2019-05-02 | 2019-07-30
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | SAND-KG03 | Marina Reconstruction | 5 | CONSTRUCTION TO 25% | 2016-06-23 | 2016-10-20 | 2019-07-31 | 2019-11-27
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | SAND-KG03 | Marina Reconstruction | 6 | CONSTRUCTION TO 50% | 2016-10-21 | 2017-02-17 | 2019-11-28 | 2020-03-26
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | SAND-KG03 | Marina Reconstruction | 7 | CONSTRUCTION TO 75% | 2017-02-18 | 2017-06-17 | 2020-03-27 | 2020-07-24
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | SAND-KG03 | Marina Reconstruction | 8 | ORIGINAL EQUIP & FURNISHING | 2017-06-18 | 2017-09-15 | 2020-07-25 | 2020-10-22
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | SAND-KG03 | Marina Reconstruction | 9 | SUBSTANTIAL COMPLETION | 2017-09-16 | 2017-11-14 | 2020-10-23 | 2020-12-21
20201123 | BROOKLYN | 042 | CITY UNIVERSITY | SAND-KG03 | Marina Reconstruction | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-11-15 | 2017-12-14 | 2021-02-01 | 2024-06-01
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | NDF-PENN | NDF - 127 Pennsylvania Ave Community Center | 1 | DEVELOP SCOPE | 2017-04-19 | 2017-07-17 | 2017-04-19 | 2017-07-17
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | NDF-PENN | NDF - 127 Pennsylvania Ave Community Center | 2 | PRELIMINARY DESIGN | 2017-07-18 | 2017-11-14 | 2017-07-18 | 2017-11-14
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | NDF-PENN | NDF - 127 Pennsylvania Ave Community Center | 3 | FINAL DESIGN | 2017-11-15 | 2018-05-13 | 2017-11-15 | 2018-05-13
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | NDF-PENN | NDF - 127 Pennsylvania Ave Community Center | 4 | BID AWARD AND REGISTER CONTRCT | 2018-05-14 | 2018-08-11 | 2018-05-14 | 2018-08-11
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | NDF-PENN | NDF - 127 Pennsylvania Ave Community Center | 5 | CONSTRUCTION TO 25% | 2018-08-12 | 2018-12-09 | 2018-08-12 | 2018-12-09
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | NDF-PENN | NDF - 127 Pennsylvania Ave Community Center | 6 | CONSTRUCTION TO 50% | 2018-12-10 | 2019-04-08 | 2018-12-10 | 2019-04-08
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | NDF-PENN | NDF - 127 Pennsylvania Ave Community Center | 7 | CONSTRUCTION TO 75% | 2019-04-09 | 2019-08-06 | 2019-04-09 | 2021-08-06
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | NDF-PENN | NDF - 127 Pennsylvania Ave Community Center | 8 | ORIGINAL EQUIP & FURNISHING | 2019-08-07 | 2019-11-04 | 2021-08-07 | 2021-11-04
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | NDF-PENN | NDF - 127 Pennsylvania Ave Community Center | 9 | SUBSTANTIAL COMPLETION | 2019-11-05 | 2020-01-03 | 2021-11-05 | 2022-01-03
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | NDF-PENN | NDF - 127 Pennsylvania Ave Community Center | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-01-04 | 2020-02-02 | 2022-01-04 | 2022-02-02
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO7911FR | 11 FRONT STR RENOVATION | 1 | DEVELOP SCOPE | 2017-05-30 | 2017-08-27 | 2017-05-30 | 2017-08-27
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO7911FR | 11 FRONT STR RENOVATION | 2 | PRELIMINARY DESIGN | 2017-08-28 | 2017-12-25 | 2017-08-28 | 2017-12-25
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO7911FR | 11 FRONT STR RENOVATION | 3 | FINAL DESIGN | 2017-12-26 | 2018-04-24 | 2017-12-26 | 2018-04-24
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO7911FR | 11 FRONT STR RENOVATION | 4 | BID AWARD AND REGISTER CONTRCT | 2018-04-25 | 2018-10-21 | 2018-04-25 | 2018-10-21
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO7911FR | 11 FRONT STR RENOVATION | 5 | CONSTRUCTION TO 25% | 2018-10-22 | 2019-02-18 | 2018-10-22 | 2019-02-18
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO7911FR | 11 FRONT STR RENOVATION | 6 | CONSTRUCTION TO 50% | 2019-02-19 | 2019-06-18 | 2019-02-19 | 2019-06-18
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO7911FR | 11 FRONT STR RENOVATION | 7 | CONSTRUCTION TO 75% | 2019-06-19 | 2019-10-16 | 2019-06-19 | 2021-03-16
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO7911FR | 11 FRONT STR RENOVATION | 8 | ORIGINAL EQUIP & FURNISHING | 2019-10-17 | 2020-01-14 | 2021-03-17 | 2021-06-14
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO7911FR | 11 FRONT STR RENOVATION | 9 | SUBSTANTIAL COMPLETION | 2020-01-15 | 2020-03-14 | 2021-06-15 | 2021-08-13
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO7911FR | 11 FRONT STR RENOVATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-03-15 | 2020-04-13 | 2021-08-14 | 2021-09-12
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAHS | FIRING RANGE RECONSTRUCTION AT CONEY ISLAND | 1 | DEVELOP SCOPE | 2014-06-30 | 2014-09-27 | 2016-06-30 | 2016-09-27
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAHS | FIRING RANGE RECONSTRUCTION AT CONEY ISLAND | 2 | PRELIMINARY DESIGN | 2014-09-28 | 2015-01-25 | 2016-09-28 | 2017-01-25
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAHS | FIRING RANGE RECONSTRUCTION AT CONEY ISLAND | 3 | FINAL DESIGN | 2015-01-26 | 2015-07-24 | 2017-01-26 | 2017-07-24
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAHS | FIRING RANGE RECONSTRUCTION AT CONEY ISLAND | 4 | BID AWARD AND REGISTER CONTRCT | 2015-07-25 | 2015-10-22 | 2017-07-25 | 2017-10-22
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAHS | FIRING RANGE RECONSTRUCTION AT CONEY ISLAND | 5 | CONSTRUCTION TO 25% | 2015-10-23 | 2016-02-19 | 2017-10-23 | 2018-02-19
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAHS | FIRING RANGE RECONSTRUCTION AT CONEY ISLAND | 6 | CONSTRUCTION TO 50% | 2016-02-20 | 2016-06-18 | 2018-02-20 | 2018-06-19
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAHS | FIRING RANGE RECONSTRUCTION AT CONEY ISLAND | 7 | CONSTRUCTION TO 75% | 2016-06-19 | 2016-10-16 | 2018-06-20 | 2020-10-17
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAHS | FIRING RANGE RECONSTRUCTION AT CONEY ISLAND | 8 | ORIGINAL EQUIP & FURNISHING | 2016-10-17 | 2017-01-14 | 2020-10-18 | 2021-01-15
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAHS | FIRING RANGE RECONSTRUCTION AT CONEY ISLAND | 9 | SUBSTANTIAL COMPLETION | 2017-01-15 | 2017-03-15 | 2021-01-16 | 2021-03-16
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAHS | FIRING RANGE RECONSTRUCTION AT CONEY ISLAND | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-16 | 2017-04-14 | 2021-03-17 | 2021-04-15
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAHX | 63RD BATHROOM RENOVATION | 1 | DEVELOP SCOPE | 2014-06-30 | 2014-09-27 | 2014-06-30 | 2014-09-27
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAHX | 63RD BATHROOM RENOVATION | 2 | PRELIMINARY DESIGN | 2014-09-28 | 2015-01-25 | 2014-09-28 | 2015-01-25
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAHX | 63RD BATHROOM RENOVATION | 3 | FINAL DESIGN | 2015-01-26 | 2015-07-24 | 2015-01-26 | 2015-07-24
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAHX | 63RD BATHROOM RENOVATION | 4 | BID AWARD AND REGISTER CONTRCT | 2015-07-25 | 2015-10-22 | 2015-07-25 | 2015-10-22
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAHX | 63RD BATHROOM RENOVATION | 5 | CONSTRUCTION TO 25% | 2015-10-23 | 2016-02-19 | 2015-10-23 | 2016-02-19
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAHX | 63RD BATHROOM RENOVATION | 6 | CONSTRUCTION TO 50% | 2016-02-20 | 2016-06-18 | 2016-02-20 | 2016-06-18
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAHX | 63RD BATHROOM RENOVATION | 7 | CONSTRUCTION TO 75% | 2016-06-19 | 2016-10-16 | 2016-06-19 | 2021-10-16
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAHX | 63RD BATHROOM RENOVATION | 8 | ORIGINAL EQUIP & FURNISHING | 2016-10-17 | 2017-01-14 | 2021-10-17 | 2022-01-14
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAHX | 63RD BATHROOM RENOVATION | 9 | SUBSTANTIAL COMPLETION | 2017-01-15 | 2017-03-15 | 2022-01-15 | 2022-03-15
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAHX | 63RD BATHROOM RENOVATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-16 | 2017-04-14 | 2022-03-16 | 2022-04-14
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAKG | FBF AVIATION AND DRIVER TRAINING UNIT ROOF REHABILITATION | 1 | DESIGN | 2020-01-01 | 2020-06-28 | 2020-01-01 | 2020-06-28
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAKG | FBF AVIATION AND DRIVER TRAINING UNIT ROOF REHABILITATION | 2 | BID AWARD AND REGISTER CONTRCT | 2020-06-29 | 2020-09-26 | 2020-06-29 | 2020-09-26
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAKG | FBF AVIATION AND DRIVER TRAINING UNIT ROOF REHABILITATION | 3 | CONSTRUCTION | 2020-09-27 | 2021-09-26 | 2020-09-27 | 2021-09-26
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAKG | FBF AVIATION AND DRIVER TRAINING UNIT ROOF REHABILITATION | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-27 | 2022-03-25 | 2021-09-27 | 2022-03-25
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAKJ | REHABILITATION OF 67TH PCT ELEVATOR | 1 | DESIGN | 2020-07-30 | 2021-01-25 | 2020-07-30 | 2021-01-25
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAKJ | REHABILITATION OF 67TH PCT ELEVATOR | 2 | BID AWARD AND REGISTER CONTRCT | 2021-01-26 | 2021-04-25 | 2021-01-26 | 2021-04-25
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAKJ | REHABILITATION OF 67TH PCT ELEVATOR | 3 | CONSTRUCTION | 2021-04-26 | 2022-04-25 | 2021-04-26 | 2022-04-25
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAKJ | REHABILITATION OF 67TH PCT ELEVATOR | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-04-26 | 2022-10-22 | 2022-04-26 | 2022-10-22
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAKQ | 66TH PCT RENOVATION | 1 | DEVELOP SCOPE | 2020-06-30 | 2020-09-27 | 2020-06-30 | 2020-09-27
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAKQ | 66TH PCT RENOVATION | 2 | PRELIMINARY DESIGN | 2020-09-28 | 2021-01-25 | 2020-09-28 | 2021-01-25
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAKQ | 66TH PCT RENOVATION | 3 | FINAL DESIGN | 2021-01-26 | 2021-05-25 | 2021-01-26 | 2021-05-25
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAKQ | 66TH PCT RENOVATION | 4 | BID AWARD AND REGISTER CONTRCT | 2021-05-26 | 2021-11-21 | 2021-05-26 | 2021-11-21
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAKQ | 66TH PCT RENOVATION | 5 | CONSTRUCTION TO 25% | 2021-11-22 | 2022-03-21 | 2021-11-22 | 2022-03-21
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAKQ | 66TH PCT RENOVATION | 6 | CONSTRUCTION TO 50% | 2022-03-22 | 2022-07-19 | 2022-03-22 | 2022-07-19
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAKQ | 66TH PCT RENOVATION | 7 | CONSTRUCTION TO 75% | 2022-07-20 | 2022-11-16 | 2022-07-20 | 2022-11-16
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAKQ | 66TH PCT RENOVATION | 8 | ORIGINAL EQUIP & FURNISHING | 2022-11-17 | 2023-02-14 | 2022-11-17 | 2023-02-14
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAKQ | 66TH PCT RENOVATION | 9 | SUBSTANTIAL COMPLETION | 2023-02-15 | 2023-04-15 | 2023-02-15 | 2023-04-15
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAKQ | 66TH PCT RENOVATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-04-16 | 2023-05-15 | 2023-04-16 | 2023-05-15
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAKR | 88TH PCT ROOF REPLACEMENT | 1 | DEVELOP SCOPE | 2020-12-10 | 2021-03-09 | 2020-12-10 | 2021-03-09
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAKR | 88TH PCT ROOF REPLACEMENT | 2 | PRELIMINARY DESIGN | 2021-03-10 | 2021-07-07 | 2021-03-10 | 2021-07-07
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAKR | 88TH PCT ROOF REPLACEMENT | 3 | FINAL DESIGN | 2021-07-08 | 2021-11-04 | 2021-07-08 | 2021-11-04
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAKR | 88TH PCT ROOF REPLACEMENT | 4 | BID AWARD AND REGISTER CONTRCT | 2021-11-05 | 2022-05-03 | 2021-11-05 | 2022-05-03
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAKR | 88TH PCT ROOF REPLACEMENT | 5 | CONSTRUCTION TO 25% | 2022-05-04 | 2022-08-31 | 2022-05-04 | 2022-08-31
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAKR | 88TH PCT ROOF REPLACEMENT | 6 | CONSTRUCTION TO 50% | 2022-09-01 | 2022-12-29 | 2022-09-01 | 2022-12-29
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAKR | 88TH PCT ROOF REPLACEMENT | 7 | CONSTRUCTION TO 75% | 2022-12-30 | 2023-04-28 | 2022-12-30 | 2023-04-28
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAKR | 88TH PCT ROOF REPLACEMENT | 8 | ORIGINAL EQUIP & FURNISHING | 2023-04-29 | 2023-07-27 | 2023-04-29 | 2023-07-27
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAKR | 88TH PCT ROOF REPLACEMENT | 9 | SUBSTANTIAL COMPLETION | 2023-07-28 | 2023-09-25 | 2023-07-28 | 2023-09-25
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAKR | 88TH PCT ROOF REPLACEMENT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-26 | 2023-10-25 | 2023-09-26 | 2023-10-25
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAKS | 81ST PCT ROOF REPLACEMENT | 1 | DEVELOP SCOPE | 2020-12-10 | 2021-03-09 | 2020-12-10 | 2021-03-09
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAKS | 81ST PCT ROOF REPLACEMENT | 2 | PRELIMINARY DESIGN | 2021-03-10 | 2021-07-07 | 2021-03-10 | 2021-07-07
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAKS | 81ST PCT ROOF REPLACEMENT | 3 | FINAL DESIGN | 2021-07-08 | 2021-11-04 | 2021-07-08 | 2021-11-04
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAKS | 81ST PCT ROOF REPLACEMENT | 4 | BID AWARD AND REGISTER CONTRCT | 2021-11-05 | 2022-05-03 | 2021-11-05 | 2022-05-03
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAKS | 81ST PCT ROOF REPLACEMENT | 5 | CONSTRUCTION TO 25% | 2022-05-04 | 2022-08-31 | 2022-05-04 | 2022-08-31
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAKS | 81ST PCT ROOF REPLACEMENT | 6 | CONSTRUCTION TO 50% | 2022-09-01 | 2022-12-29 | 2022-09-01 | 2022-12-29
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAKS | 81ST PCT ROOF REPLACEMENT | 7 | CONSTRUCTION TO 75% | 2022-12-30 | 2023-04-28 | 2022-12-30 | 2023-04-28
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAKS | 81ST PCT ROOF REPLACEMENT | 8 | ORIGINAL EQUIP & FURNISHING | 2023-04-29 | 2023-07-27 | 2023-04-29 | 2023-07-27
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAKS | 81ST PCT ROOF REPLACEMENT | 9 | SUBSTANTIAL COMPLETION | 2023-07-28 | 2023-09-25 | 2023-07-28 | 2023-09-25
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAKS | 81ST PCT ROOF REPLACEMENT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-26 | 2023-10-25 | 2023-09-26 | 2023-10-25
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAKT | 60TH PCT ROOF REPLACEMENT | 1 | DEVELOP SCOPE | 2020-12-10 | 2021-03-09 | 2020-12-10 | 2021-03-09
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAKT | 60TH PCT ROOF REPLACEMENT | 2 | PRELIMINARY DESIGN | 2021-03-10 | 2021-07-07 | 2021-03-10 | 2021-07-07
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAKT | 60TH PCT ROOF REPLACEMENT | 3 | FINAL DESIGN | 2021-07-08 | 2021-11-04 | 2021-07-08 | 2021-11-04
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAKT | 60TH PCT ROOF REPLACEMENT | 4 | BID AWARD AND REGISTER CONTRCT | 2021-11-05 | 2022-05-03 | 2021-11-05 | 2022-05-03
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAKT | 60TH PCT ROOF REPLACEMENT | 5 | CONSTRUCTION TO 25% | 2022-05-04 | 2022-08-31 | 2022-05-04 | 2022-08-31
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAKT | 60TH PCT ROOF REPLACEMENT | 6 | CONSTRUCTION TO 50% | 2022-09-01 | 2022-12-29 | 2022-09-01 | 2022-12-29
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAKT | 60TH PCT ROOF REPLACEMENT | 7 | CONSTRUCTION TO 75% | 2022-12-30 | 2023-04-28 | 2022-12-30 | 2023-04-28
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAKT | 60TH PCT ROOF REPLACEMENT | 8 | ORIGINAL EQUIP & FURNISHING | 2023-04-29 | 2023-07-27 | 2023-04-29 | 2023-07-27
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAKT | 60TH PCT ROOF REPLACEMENT | 9 | SUBSTANTIAL COMPLETION | 2023-07-28 | 2023-09-25 | 2023-07-28 | 2023-09-25
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAKT | 60TH PCT ROOF REPLACEMENT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-26 | 2023-10-25 | 2023-09-26 | 2023-10-25
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAKW | 245 GLENMORE ROOF REPLACEMENT | 1 | DEVELOP SCOPE | 2020-12-10 | 2021-03-09 | 2020-12-10 | 2021-03-09
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAKW | 245 GLENMORE ROOF REPLACEMENT | 2 | PRELIMINARY DESIGN | 2021-03-10 | 2021-07-07 | 2021-03-10 | 2021-07-07
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAKW | 245 GLENMORE ROOF REPLACEMENT | 3 | FINAL DESIGN | 2021-07-08 | 2021-11-04 | 2021-07-08 | 2021-11-04
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAKW | 245 GLENMORE ROOF REPLACEMENT | 4 | BID AWARD AND REGISTER CONTRCT | 2021-11-05 | 2022-05-03 | 2021-11-05 | 2022-05-03
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAKW | 245 GLENMORE ROOF REPLACEMENT | 5 | CONSTRUCTION TO 25% | 2022-05-04 | 2022-08-31 | 2022-05-04 | 2022-08-31
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAKW | 245 GLENMORE ROOF REPLACEMENT | 6 | CONSTRUCTION TO 50% | 2022-09-01 | 2022-12-29 | 2022-09-01 | 2022-12-29
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAKW | 245 GLENMORE ROOF REPLACEMENT | 7 | CONSTRUCTION TO 75% | 2022-12-30 | 2023-04-28 | 2022-12-30 | 2023-04-28
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAKW | 245 GLENMORE ROOF REPLACEMENT | 8 | ORIGINAL EQUIP & FURNISHING | 2023-04-29 | 2023-07-27 | 2023-04-29 | 2023-07-27
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAKW | 245 GLENMORE ROOF REPLACEMENT | 9 | SUBSTANTIAL COMPLETION | 2023-07-28 | 2023-09-25 | 2023-07-28 | 2023-09-25
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAKW | 245 GLENMORE ROOF REPLACEMENT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-26 | 2023-10-25 | 2023-09-26 | 2023-10-25
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79TD32 | TRANSIT DISTRICT 32 ROOF RENOVATION | 1 | DEVELOP SCOPE | 2015-02-10 | 2015-05-10 | 2019-02-10 | 2019-05-10
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79TD32 | TRANSIT DISTRICT 32 ROOF RENOVATION | 2 | PRELIMINARY DESIGN | 2015-05-11 | 2015-09-07 | 2019-05-11 | 2019-09-07
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79TD32 | TRANSIT DISTRICT 32 ROOF RENOVATION | 3 | FINAL DESIGN | 2015-09-08 | 2016-01-05 | 2019-09-08 | 2020-01-05
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79TD32 | TRANSIT DISTRICT 32 ROOF RENOVATION | 4 | BID AWARD AND REGISTER CONTRCT | 2016-01-06 | 2016-07-03 | 2020-01-06 | 2020-07-03
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79TD32 | TRANSIT DISTRICT 32 ROOF RENOVATION | 5 | CONSTRUCTION TO 25% | 2016-07-04 | 2016-10-31 | 2020-07-04 | 2020-10-31
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79TD32 | TRANSIT DISTRICT 32 ROOF RENOVATION | 6 | CONSTRUCTION TO 50% | 2016-11-01 | 2017-02-28 | 2020-11-01 | 2021-02-28
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79TD32 | TRANSIT DISTRICT 32 ROOF RENOVATION | 7 | CONSTRUCTION TO 75% | 2017-03-01 | 2017-06-28 | 2021-03-01 | 2021-06-28
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79TD32 | TRANSIT DISTRICT 32 ROOF RENOVATION | 8 | ORIGINAL EQUIP & FURNISHING | 2017-06-29 | 2017-09-26 | 2021-06-29 | 2021-09-26
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79TD32 | TRANSIT DISTRICT 32 ROOF RENOVATION | 9 | SUBSTANTIAL COMPLETION | 2017-09-27 | 2017-11-25 | 2021-09-27 | 2021-11-25
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79TD32 | TRANSIT DISTRICT 32 ROOF RENOVATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-11-26 | 2017-12-25 | 2021-11-26 | 2021-12-25
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | POD73CMRM | 73RD PRECINCT COMMUNITY ROOM | 3 | CONSTRUCTION | 2019-10-04 | 2020-10-02 | 2019-10-04 | 2020-10-02
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | POD73CMRM | 73RD PRECINCT COMMUNITY ROOM | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-10-03 | 2021-03-31 | 2020-10-03 | 2021-03-31
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PODMTRPE | Mounted Unit facility betterment | 1 | DESIGN | 2019-12-30 | 2020-06-26 | 2019-12-30 | 2020-06-26
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PODMTRPE | Mounted Unit facility betterment | 2 | BID AWARD AND REGISTER CONTRCT | 2020-06-27 | 2020-09-24 | 2020-06-27 | 2020-09-24
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PODMTRPE | Mounted Unit facility betterment | 3 | CONSTRUCTION | 2020-09-25 | 2021-09-24 | 2020-09-25 | 2021-09-24
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PODMTRPE | Mounted Unit facility betterment | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-25 | 2022-03-23 | 2021-09-25 | 2022-03-23
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO-KVEST | PEOPLE'S PRECINCTS VESTIBULE REDESIGN | 1 | DESIGN | 2018-01-01 | 2018-06-29 | 2018-01-01 | 2018-06-29
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO-KVEST | PEOPLE'S PRECINCTS VESTIBULE REDESIGN | 2 | BID AWARD AND REGISTER CONTRCT | 2018-06-30 | 2018-09-27 | 2018-06-30 | 2018-09-27
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO-KVEST | PEOPLE'S PRECINCTS VESTIBULE REDESIGN | 3 | CONSTRUCTION | 2018-09-28 | 2019-09-27 | 2018-09-28 | 2019-09-27
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | PO-KVEST | PEOPLE'S PRECINCTS VESTIBULE REDESIGN | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-28 | 2020-03-25 | 2019-09-28 | 2022-03-25
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDCD13 | PROPERTY CLERK ELECTRICAL CONDUIT | 1 | DEVELOP SCOPE | 2016-06-30 | 2016-09-27 | 2016-06-30 | 2016-09-27
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDCD13 | PROPERTY CLERK ELECTRICAL CONDUIT | 2 | PRELIMINARY DESIGN | 2016-09-28 | 2017-01-25 | 2016-09-28 | 2017-01-25
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDCD13 | PROPERTY CLERK ELECTRICAL CONDUIT | 3 | FINAL DESIGN | 2017-01-26 | 2017-05-25 | 2017-01-26 | 2017-05-25
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDCD13 | PROPERTY CLERK ELECTRICAL CONDUIT | 4 | BID AWARD AND REGISTER CONTRCT | 2017-05-26 | 2017-11-21 | 2017-05-26 | 2017-11-21
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDCD13 | PROPERTY CLERK ELECTRICAL CONDUIT | 5 | CONSTRUCTION TO 25% | 2017-11-22 | 2018-03-21 | 2017-11-22 | 2018-03-21
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDCD13 | PROPERTY CLERK ELECTRICAL CONDUIT | 6 | CONSTRUCTION TO 50% | 2018-03-22 | 2018-07-19 | 2018-03-22 | 2018-07-19
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDCD13 | PROPERTY CLERK ELECTRICAL CONDUIT | 7 | CONSTRUCTION TO 75% | 2018-07-20 | 2018-11-16 | 2018-07-20 | 2021-11-16
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDCD13 | PROPERTY CLERK ELECTRICAL CONDUIT | 8 | ORIGINAL EQUIP & FURNISHING | 2018-11-17 | 2019-02-14 | 2021-11-17 | 2022-02-14
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDCD13 | PROPERTY CLERK ELECTRICAL CONDUIT | 9 | SUBSTANTIAL COMPLETION | 2019-02-15 | 2019-04-15 | 2022-02-15 | 2022-04-15
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDCD13 | PROPERTY CLERK ELECTRICAL CONDUIT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-04-16 | 2019-05-15 | 2022-04-16 | 2022-05-15
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDCD3 | POLICE SERVICE AREA 1 (PSA1) | 1 | DEVELOP SCOPE | 2016-09-10 | 2016-12-08 | 2016-06-10 | 2016-09-07
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDCD3 | POLICE SERVICE AREA 1 (PSA1) | 2 | PRELIMINARY DESIGN | 2016-12-09 | 2017-04-07 | 2016-09-08 | 2017-01-05
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDCD3 | POLICE SERVICE AREA 1 (PSA1) | 3 | FINAL DESIGN | 2017-04-08 | 2017-08-05 | 2017-01-06 | 2017-05-05
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDCD3 | POLICE SERVICE AREA 1 (PSA1) | 4 | BID AWARD AND REGISTER CONTRCT | 2017-08-06 | 2018-02-01 | 2017-05-06 | 2017-11-01
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDCD3 | POLICE SERVICE AREA 1 (PSA1) | 5 | CONSTRUCTION TO 25% | 2018-02-02 | 2018-06-01 | 2017-11-02 | 2018-03-01
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDCD3 | POLICE SERVICE AREA 1 (PSA1) | 6 | CONSTRUCTION TO 50% | 2018-06-02 | 2018-09-29 | 2018-03-02 | 2018-06-29
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDCD3 | POLICE SERVICE AREA 1 (PSA1) | 7 | CONSTRUCTION TO 75% | 2018-09-30 | 2019-01-27 | 2018-06-30 | 2021-10-27
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDCD3 | POLICE SERVICE AREA 1 (PSA1) | 8 | ORIGINAL EQUIP & FURNISHING | 2019-01-28 | 2019-04-27 | 2021-10-28 | 2022-01-25
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDCD3 | POLICE SERVICE AREA 1 (PSA1) | 9 | SUBSTANTIAL COMPLETION | 2019-04-28 | 2019-06-26 | 2022-01-26 | 2022-03-26
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDCD3 | POLICE SERVICE AREA 1 (PSA1) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-06-27 | 2019-07-26 | 2022-03-27 | 2022-04-25
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDCD4 | FLOYD BENNETT FIELD ELECTRICAL | 1 | DEVELOP SCOPE | 2016-06-30 | 2016-09-27 | 2016-06-30 | 2016-09-27
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDCD4 | FLOYD BENNETT FIELD ELECTRICAL | 2 | PRELIMINARY DESIGN | 2016-09-28 | 2017-01-25 | 2016-09-28 | 2017-01-25
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDCD4 | FLOYD BENNETT FIELD ELECTRICAL | 3 | FINAL DESIGN | 2017-01-26 | 2017-05-25 | 2017-01-26 | 2017-05-25
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDCD4 | FLOYD BENNETT FIELD ELECTRICAL | 4 | BID AWARD AND REGISTER CONTRCT | 2017-05-26 | 2017-11-21 | 2017-05-26 | 2017-11-21
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDCD4 | FLOYD BENNETT FIELD ELECTRICAL | 5 | CONSTRUCTION TO 25% | 2017-11-22 | 2018-03-21 | 2017-11-22 | 2018-03-21
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDCD4 | FLOYD BENNETT FIELD ELECTRICAL | 6 | CONSTRUCTION TO 50% | 2018-03-22 | 2018-07-19 | 2018-03-22 | 2018-07-19
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDCD4 | FLOYD BENNETT FIELD ELECTRICAL | 7 | CONSTRUCTION TO 75% | 2018-07-20 | 2018-11-16 | 2018-07-20 | 2021-11-16
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDCD4 | FLOYD BENNETT FIELD ELECTRICAL | 8 | ORIGINAL EQUIP & FURNISHING | 2018-11-17 | 2019-02-14 | 2021-11-17 | 2022-02-14
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDCD4 | FLOYD BENNETT FIELD ELECTRICAL | 9 | SUBSTANTIAL COMPLETION | 2019-02-15 | 2019-04-15 | 2022-02-15 | 2022-04-15
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDCD4 | FLOYD BENNETT FIELD ELECTRICAL | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-04-16 | 2019-05-15 | 2022-04-16 | 2022-05-15
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDCD5 | TRANSIT DISTRICT 34 ELECTRICAL | 1 | DEVELOP SCOPE | 2016-09-10 | 2016-12-08 | 2016-06-10 | 2016-09-07
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDCD5 | TRANSIT DISTRICT 34 ELECTRICAL | 2 | PRELIMINARY DESIGN | 2016-12-09 | 2017-04-07 | 2016-09-08 | 2017-01-05
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDCD5 | TRANSIT DISTRICT 34 ELECTRICAL | 3 | FINAL DESIGN | 2017-04-08 | 2017-08-05 | 2017-01-06 | 2017-05-05
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDCD5 | TRANSIT DISTRICT 34 ELECTRICAL | 4 | BID AWARD AND REGISTER CONTRCT | 2017-08-06 | 2018-02-01 | 2017-05-06 | 2017-11-01
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDCD5 | TRANSIT DISTRICT 34 ELECTRICAL | 5 | CONSTRUCTION TO 25% | 2018-02-02 | 2018-06-01 | 2017-11-02 | 2018-03-01
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDCD5 | TRANSIT DISTRICT 34 ELECTRICAL | 6 | CONSTRUCTION TO 50% | 2018-06-02 | 2018-09-29 | 2018-03-02 | 2018-06-29
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDCD5 | TRANSIT DISTRICT 34 ELECTRICAL | 7 | CONSTRUCTION TO 75% | 2018-09-30 | 2019-01-27 | 2018-06-30 | 2021-10-27
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDCD5 | TRANSIT DISTRICT 34 ELECTRICAL | 8 | ORIGINAL EQUIP & FURNISHING | 2019-01-28 | 2019-04-27 | 2021-10-28 | 2022-01-25
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDCD5 | TRANSIT DISTRICT 34 ELECTRICAL | 9 | SUBSTANTIAL COMPLETION | 2019-04-28 | 2019-06-26 | 2022-01-26 | 2022-03-26
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDCD5 | TRANSIT DISTRICT 34 ELECTRICAL | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-06-27 | 2019-07-26 | 2022-03-27 | 2022-04-25
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDWARE | 23RD STR WAREHOUSE RECONSTRUCTION | 1 | DEVELOP SCOPE | 2017-05-30 | 2017-08-27 | 2017-05-30 | 2017-08-27
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDWARE | 23RD STR WAREHOUSE RECONSTRUCTION | 2 | PRELIMINARY DESIGN | 2017-08-28 | 2017-12-25 | 2017-08-28 | 2017-12-25
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDWARE | 23RD STR WAREHOUSE RECONSTRUCTION | 3 | FINAL DESIGN | 2017-12-26 | 2018-04-24 | 2017-12-26 | 2018-04-24
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDWARE | 23RD STR WAREHOUSE RECONSTRUCTION | 4 | BID AWARD AND REGISTER CONTRCT | 2018-04-25 | 2018-10-21 | 2018-04-25 | 2018-10-21
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDWARE | 23RD STR WAREHOUSE RECONSTRUCTION | 5 | CONSTRUCTION TO 25% | 2018-10-22 | 2019-02-18 | 2018-10-22 | 2019-02-18
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDWARE | 23RD STR WAREHOUSE RECONSTRUCTION | 6 | CONSTRUCTION TO 50% | 2019-02-19 | 2019-06-18 | 2019-02-19 | 2019-06-18
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDWARE | 23RD STR WAREHOUSE RECONSTRUCTION | 7 | CONSTRUCTION TO 75% | 2019-06-19 | 2019-10-16 | 2019-06-19 | 2019-10-16
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDWARE | 23RD STR WAREHOUSE RECONSTRUCTION | 8 | ORIGINAL EQUIP & FURNISHING | 2019-10-17 | 2020-01-14 | 2019-10-17 | 2020-01-14
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDWARE | 23RD STR WAREHOUSE RECONSTRUCTION | 9 | SUBSTANTIAL COMPLETION | 2020-01-15 | 2020-03-14 | 2020-01-15 | 2020-03-14
20201123 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDWARE | 23RD STR WAREHOUSE RECONSTRUCTION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-03-15 | 2020-04-13 | 2020-03-15 | 2020-04-13
20201123 | BROOKLYN | 057 | FIRE DEPARTMENT | ACEFDN701 | FDNY - LED LIGHTING UPGRADE AT 14 FDNY FACILITIES | 1 | DEVELOP SCOPE | 2018-02-01 | 2018-05-01 | 2018-02-01 | 2018-05-01
20201123 | BROOKLYN | 057 | FIRE DEPARTMENT | ACEFDN701 | FDNY - LED LIGHTING UPGRADE AT 14 FDNY FACILITIES | 2 | PRELIMINARY DESIGN | 2018-05-02 | 2018-08-29 | 2018-05-02 | 2018-08-29
20201123 | BROOKLYN | 057 | FIRE DEPARTMENT | ACEFDN701 | FDNY - LED LIGHTING UPGRADE AT 14 FDNY FACILITIES | 3 | FINAL DESIGN | 2018-08-30 | 2019-02-25 | 2018-08-30 | 2019-02-25
20201123 | BROOKLYN | 057 | FIRE DEPARTMENT | ACEFDN701 | FDNY - LED LIGHTING UPGRADE AT 14 FDNY FACILITIES | 4 | BID AWARD AND REGISTER CONTRCT | 2019-02-26 | 2019-05-26 | 2019-02-26 | 2019-05-26
20201123 | BROOKLYN | 057 | FIRE DEPARTMENT | ACEFDN701 | FDNY - LED LIGHTING UPGRADE AT 14 FDNY FACILITIES | 5 | CONSTRUCTION TO 25% | 2019-05-27 | 2019-09-23 | 2019-05-27 | 2019-09-23
20201123 | BROOKLYN | 057 | FIRE DEPARTMENT | ACEFDN701 | FDNY - LED LIGHTING UPGRADE AT 14 FDNY FACILITIES | 6 | CONSTRUCTION TO 50% | 2019-09-24 | 2020-01-21 | 2019-09-24 | 2020-01-21
20201123 | BROOKLYN | 057 | FIRE DEPARTMENT | ACEFDN701 | FDNY - LED LIGHTING UPGRADE AT 14 FDNY FACILITIES | 7 | CONSTRUCTION TO 75% | 2020-01-22 | 2020-05-20 | 2020-01-22 | 2020-05-20
20201123 | BROOKLYN | 057 | FIRE DEPARTMENT | ACEFDN701 | FDNY - LED LIGHTING UPGRADE AT 14 FDNY FACILITIES | 8 | ORIGINAL EQUIP & FURNISHING | 2020-05-21 | 2020-08-18 | 2020-05-21 | 2020-08-18
20201123 | BROOKLYN | 057 | FIRE DEPARTMENT | ACEFDN701 | FDNY - LED LIGHTING UPGRADE AT 14 FDNY FACILITIES | 9 | SUBSTANTIAL COMPLETION | 2020-08-19 | 2020-10-17 | 2020-08-19 | 2020-10-17
20201123 | BROOKLYN | 057 | FIRE DEPARTMENT | ACEFDN701 | FDNY - LED LIGHTING UPGRADE AT 14 FDNY FACILITIES | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-10-18 | 2020-11-16 | 2020-10-18 | 2020-11-16
20201123 | BROOKLYN | 057 | FIRE DEPARTMENT | ACEFDN703 | FDNY - DESIGN & INSTALLATION OF 37 KW SOLAR SYSTEM AT EC332 | 1 | DEVELOP SCOPE | 2017-10-15 | 2018-01-12 | 2017-10-15 | 2018-01-12
20201123 | BROOKLYN | 057 | FIRE DEPARTMENT | ACEFDN703 | FDNY - DESIGN & INSTALLATION OF 37 KW SOLAR SYSTEM AT EC332 | 2 | PRELIMINARY DESIGN | 2018-01-13 | 2018-05-12 | 2018-01-13 | 2018-05-12
20201123 | BROOKLYN | 057 | FIRE DEPARTMENT | ACEFDN703 | FDNY - DESIGN & INSTALLATION OF 37 KW SOLAR SYSTEM AT EC332 | 3 | FINAL DESIGN | 2018-05-13 | 2018-11-08 | 2018-05-13 | 2018-11-08
20201123 | BROOKLYN | 057 | FIRE DEPARTMENT | ACEFDN703 | FDNY - DESIGN & INSTALLATION OF 37 KW SOLAR SYSTEM AT EC332 | 4 | BID AWARD AND REGISTER CONTRCT | 2018-11-09 | 2019-02-06 | 2018-11-09 | 2019-02-06
20201123 | BROOKLYN | 057 | FIRE DEPARTMENT | ACEFDN703 | FDNY - DESIGN & INSTALLATION OF 37 KW SOLAR SYSTEM AT EC332 | 5 | CONSTRUCTION TO 25% | 2019-02-07 | 2019-06-06 | 2019-02-07 | 2019-06-06
20201123 | BROOKLYN | 057 | FIRE DEPARTMENT | ACEFDN703 | FDNY - DESIGN & INSTALLATION OF 37 KW SOLAR SYSTEM AT EC332 | 6 | CONSTRUCTION TO 50% | 2019-06-07 | 2019-10-04 | 2019-06-07 | 2019-10-04
20201123 | BROOKLYN | 057 | FIRE DEPARTMENT | ACEFDN703 | FDNY - DESIGN & INSTALLATION OF 37 KW SOLAR SYSTEM AT EC332 | 7 | CONSTRUCTION TO 75% | 2019-10-05 | 2020-02-01 | 2019-10-05 | 2020-02-01
20201123 | BROOKLYN | 057 | FIRE DEPARTMENT | ACEFDN703 | FDNY - DESIGN & INSTALLATION OF 37 KW SOLAR SYSTEM AT EC332 | 8 | ORIGINAL EQUIP & FURNISHING | 2020-02-02 | 2020-05-01 | 2020-02-02 | 2020-05-01
20201123 | BROOKLYN | 057 | FIRE DEPARTMENT | ACEFDN703 | FDNY - DESIGN & INSTALLATION OF 37 KW SOLAR SYSTEM AT EC332 | 9 | SUBSTANTIAL COMPLETION | 2020-05-02 | 2020-06-30 | 2020-05-02 | 2020-06-30
20201123 | BROOKLYN | 057 | FIRE DEPARTMENT | ACEFDN703 | FDNY - DESIGN & INSTALLATION OF 37 KW SOLAR SYSTEM AT EC332 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-07-01 | 2020-07-30 | 2020-07-01 | 2020-07-30
20201123 | BROOKLYN | 057 | FIRE DEPARTMENT | ACEFDN801 | FDNY - Solar Photo-voltaic system at EMS 58 | 1 | DEVELOP SCOPE | 2018-09-01 | 2018-11-29 | 2018-09-01 | 2018-11-29
20201123 | BROOKLYN | 057 | FIRE DEPARTMENT | ACEFDN801 | FDNY - Solar Photo-voltaic system at EMS 58 | 2 | PRELIMINARY DESIGN | 2018-11-30 | 2019-03-29 | 2018-11-30 | 2019-03-29
20201123 | BROOKLYN | 057 | FIRE DEPARTMENT | ACEFDN801 | FDNY - Solar Photo-voltaic system at EMS 58 | 3 | FINAL DESIGN | 2019-03-30 | 2019-09-25 | 2019-03-30 | 2019-09-25
20201123 | BROOKLYN | 057 | FIRE DEPARTMENT | ACEFDN801 | FDNY - Solar Photo-voltaic system at EMS 58 | 4 | BID AWARD AND REGISTER CONTRCT | 2019-09-26 | 2019-12-24 | 2019-09-26 | 2019-12-24
20201123 | BROOKLYN | 057 | FIRE DEPARTMENT | ACEFDN801 | FDNY - Solar Photo-voltaic system at EMS 58 | 5 | CONSTRUCTION TO 25% | 2019-12-25 | 2020-04-22 | 2019-12-25 | 2020-04-22
20201123 | BROOKLYN | 057 | FIRE DEPARTMENT | ACEFDN801 | FDNY - Solar Photo-voltaic system at EMS 58 | 6 | CONSTRUCTION TO 50% | 2020-04-23 | 2020-08-20 | 2020-04-23 | 2020-08-20
20201123 | BROOKLYN | 057 | FIRE DEPARTMENT | ACEFDN801 | FDNY - Solar Photo-voltaic system at EMS 58 | 7 | CONSTRUCTION TO 75% | 2020-08-21 | 2020-12-18 | 2020-08-21 | 2020-12-18
20201123 | BROOKLYN | 057 | FIRE DEPARTMENT | ACEFDN801 | FDNY - Solar Photo-voltaic system at EMS 58 | 8 | ORIGINAL EQUIP & FURNISHING | 2020-12-19 | 2021-03-18 | 2020-12-19 | 2021-03-18
20201123 | BROOKLYN | 057 | FIRE DEPARTMENT | ACEFDN801 | FDNY - Solar Photo-voltaic system at EMS 58 | 9 | SUBSTANTIAL COMPLETION | 2021-03-19 | 2021-05-17 | 2021-03-19 | 2021-05-17
20201123 | BROOKLYN | 057 | FIRE DEPARTMENT | ACEFDN801 | FDNY - Solar Photo-voltaic system at EMS 58 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-05-18 | 2021-06-16 | 2021-05-18 | 2021-06-16
20201123 | BROOKLYN | 057 | FIRE DEPARTMENT | F175DR253 | Doors Replacements - EC 253 | 2 | CONSTRUCTION | 2019-03-12 | 2020-03-10 | 2019-03-12 | 2020-03-10
20201123 | BROOKLYN | 057 | FIRE DEPARTMENT | F175DR253 | Doors Replacements - EC 253 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-03-11 | 2020-06-08 | 2020-03-11 | 2020-06-08
20201123 | BROOKLYN | 057 | FIRE DEPARTMENT | F175MC218 | Multi-Component Renovations - EC218 | 1 | DESIGN | 2018-10-12 | 2019-01-09 | 2020-03-28 | 2020-06-25
20201123 | BROOKLYN | 057 | FIRE DEPARTMENT | F175MC218 | Multi-Component Renovations - EC218 | 2 | BID AWARD AND REGISTER CONTRCT | 2019-01-10 | 2019-10-06 | 2020-06-26 | 2021-03-22
20201123 | BROOKLYN | 057 | FIRE DEPARTMENT | F175MC218 | Multi-Component Renovations - EC218 | 3 | CONSTRUCTION | 2019-10-07 | 2020-11-09 | 2021-03-23 | 2022-04-26
20201123 | BROOKLYN | 057 | FIRE DEPARTMENT | F175MC218 | Multi-Component Renovations - EC218 | 4 | ORIGINAL EQUIP & FURNISHING | 2020-11-10 | 2020-12-24 | 2022-04-27 | 2022-06-10
20201123 | BROOKLYN | 057 | FIRE DEPARTMENT | F175MC218 | Multi-Component Renovations - EC218 | 5 | SUBSTANTIAL COMPLETION | 2020-12-25 | 2021-02-02 | 2022-06-11 | 2022-07-20
20201123 | BROOKLYN | 057 | FIRE DEPARTMENT | F175MC218 | Multi-Component Renovations - EC218 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-02-03 | 2021-04-03 | 2022-07-21 | 2022-09-18
20201123 | BROOKLYN | 057 | FIRE DEPARTMENT | F175MC224 | FLOOR, KITCHEN L-OHD - EC224 | 1 | DESIGN | 2013-08-16 | 2014-02-11 | 2015-12-15 | 2016-06-11
20201123 | BROOKLYN | 057 | FIRE DEPARTMENT | F175MC224 | FLOOR, KITCHEN L-OHD - EC224 | 2 | CONSTRUCTION | 2014-02-12 | 2015-02-11 | 2016-06-12 | 2017-06-11
20201123 | BROOKLYN | 057 | FIRE DEPARTMENT | F175MC224 | FLOOR, KITCHEN L-OHD - EC224 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-02-12 | 2015-05-12 | 2017-06-12 | 2021-12-30
20201123 | BROOKLYN | 057 | FIRE DEPARTMENT | FD175D214 | DOOR REPLACEMENT - EC214 | 1 | CONSTRUCTION | 2017-09-20 | 2018-09-19 | 2017-09-20 | 2018-09-19
20201123 | BROOKLYN | 057 | FIRE DEPARTMENT | FD175D214 | DOOR REPLACEMENT - EC214 | 2 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-09-20 | 2018-12-18 | 2018-09-20 | 2018-12-18
20201123 | BROOKLYN | 057 | FIRE DEPARTMENT | FD175D230 | DOOR REPLACEMENT - EC230 | 1 | CONSTRUCTION | 2017-09-20 | 2018-09-19 | 2017-09-20 | 2018-09-19
20201123 | BROOKLYN | 057 | FIRE DEPARTMENT | FD175D230 | DOOR REPLACEMENT - EC230 | 2 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-09-20 | 2018-12-18 | 2018-09-20 | 2018-12-18
20201123 | BROOKLYN | 057 | FIRE DEPARTMENT | FD175D241 | DOOR REPLACEMENT - EC241 | 2 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-09-20 | 2018-12-18 | 2018-09-20 | 2018-12-18
20201123 | BROOKLYN | 057 | FIRE DEPARTMENT | FD175D271 | Door Replacement - EC271 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-03-13 | 2020-06-10 | 2021-09-30 | 2021-12-28
20201123 | BROOKLYN | 057 | FIRE DEPARTMENT | FD175D281 | DOOR REPLACEMENT - EC281 | 1 | CONSTRUCTION | 2017-09-20 | 2018-09-19 | 2017-09-20 | 2018-09-19
20201123 | BROOKLYN | 057 | FIRE DEPARTMENT | FD175D281 | DOOR REPLACEMENT - EC281 | 2 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-09-20 | 2018-12-18 | 2018-09-20 | 2018-12-18
20201123 | BROOKLYN | 057 | FIRE DEPARTMENT | FD175E249 | ROOF REPLACEMENT - EC249 | 1 | DESIGN | 2018-09-15 | 2019-03-13 | 2019-04-04 | 2019-09-30
20201123 | BROOKLYN | 057 | FIRE DEPARTMENT | FD175E249 | ROOF REPLACEMENT - EC249 | 2 | CONSTRUCTION | 2019-03-14 | 2020-03-12 | 2019-10-01 | 2020-09-29
20201123 | BROOKLYN | 057 | FIRE DEPARTMENT | FD175E249 | ROOF REPLACEMENT - EC249 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-03-13 | 2020-06-10 | 2020-09-30 | 2020-12-28
20201123 | BROOKLYN | 057 | FIRE DEPARTMENT | FD175W245 | WINDOW REPLACEMENT - EC245 | 1 | CONSTRUCTION | 2018-03-01 | 2019-02-28 | 2018-03-30 | 2019-03-29
20201123 | BROOKLYN | 057 | FIRE DEPARTMENT | FD175W245 | WINDOW REPLACEMENT - EC245 | 2 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-03-01 | 2019-05-29 | 2019-03-30 | 2022-12-30
20201123 | BROOKLYN | 057 | FIRE DEPARTMENT | FD175W248 | WINDOW REPLACEMENT - EC248 | 1 | CONSTRUCTION | 2018-02-01 | 2019-01-31 | 2018-02-26 | 2022-09-29
20201123 | BROOKLYN | 057 | FIRE DEPARTMENT | FD175W248 | WINDOW REPLACEMENT - EC248 | 2 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-02-01 | 2019-05-01 | 2022-09-30 | 2022-12-28
20201123 | BROOKLYN | 057 | FIRE DEPARTMENT | FD175W330 | Window Replacement - EC330 | 1 | DESIGN | 2019-01-15 | 2019-07-13 | 2019-01-15 | 2019-07-13
20201123 | BROOKLYN | 057 | FIRE DEPARTMENT | FD175W330 | Window Replacement - EC330 | 2 | CONSTRUCTION | 2019-07-14 | 2020-07-12 | 2019-07-14 | 2020-07-12
20201123 | BROOKLYN | 057 | FIRE DEPARTMENT | FD175W330 | Window Replacement - EC330 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-07-13 | 2020-10-10 | 2020-07-13 | 2020-10-10
20201123 | BROOKLYN | 068 | ADMIN FOR CHILDREN'S SERVICES | HRC006KCH | LOTS FOR TOTS, KINGS COUNTY HOSPITAL (RESO A COUNCIL) | 1 | DESIGN | 2011-05-15 | 2011-05-15 | 2019-08-08 | 2020-02-03
20201123 | BROOKLYN | 068 | ADMIN FOR CHILDREN'S SERVICES | HRC006KCH | LOTS FOR TOTS, KINGS COUNTY HOSPITAL (RESO A COUNCIL) | 2 | BID AWARD AND REGISTER CONTRCT | 2011-05-16 | 2011-05-16 | 2020-02-04 | 2024-10-07
20201123 | BROOKLYN | 068 | ADMIN FOR CHILDREN'S SERVICES | HRC006KCH | LOTS FOR TOTS, KINGS COUNTY HOSPITAL (RESO A COUNCIL) | 3 | CONSTRUCTION | 2011-05-17 | 2011-05-17 | 2020-02-04 | 2024-10-07
20201123 | BROOKLYN | 068 | ADMIN FOR CHILDREN'S SERVICES | HRC006KCH | LOTS FOR TOTS, KINGS COUNTY HOSPITAL (RESO A COUNCIL) | 4 | ORIGINAL EQUIP & FURNISHING | 2011-05-18 | 2011-05-18 | 2020-02-04 | 2024-10-07
20201123 | BROOKLYN | 068 | ADMIN FOR CHILDREN'S SERVICES | HRC006KCH | LOTS FOR TOTS, KINGS COUNTY HOSPITAL (RESO A COUNCIL) | 5 | SUBSTANTIAL COMPLETION | 2011-05-19 | 2011-05-19 | 2020-02-04 | 2024-10-07
20201123 | BROOKLYN | 068 | ADMIN FOR CHILDREN'S SERVICES | HRC006KCH | LOTS FOR TOTS, KINGS COUNTY HOSPITAL (RESO A COUNCIL) | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2011-05-20 | 2011-05-20 | 2020-02-04 | 2024-10-07
20201123 | BROOKLYN | 068 | ADMIN FOR CHILDREN'S SERVICES | HRC006KCH | LOTS FOR TOTS, KINGS COUNTY HOSPITAL (RESO A COUNCIL) | 7 | DESIGN | 2011-05-21 | 2011-11-16 | 2020-02-04 | 2024-10-07
20201123 | BROOKLYN | 068 | ADMIN FOR CHILDREN'S SERVICES | HRC006KCH | LOTS FOR TOTS, KINGS COUNTY HOSPITAL (RESO A COUNCIL) | 8 | CONSTRUCTION | 2011-11-17 | 2012-05-14 | 2020-02-04 | 2024-10-07
20201123 | BROOKLYN | 068 | ADMIN FOR CHILDREN'S SERVICES | JJZROSSLB | THE CROSSROADS JUVENILE CENTER - LIBRARY RENOVATION | 1 | DESIGN | 2013-10-01 | 2014-03-29 | 2018-07-01 | 2018-12-31
20201123 | BROOKLYN | 068 | ADMIN FOR CHILDREN'S SERVICES | JJZROSSLB | THE CROSSROADS JUVENILE CENTER - LIBRARY RENOVATION | 2 | BID AWARD AND REGISTER CONTRCT | 2014-03-30 | 2014-06-27 | 2019-01-01 | 2019-02-28
20201123 | BROOKLYN | 068 | ADMIN FOR CHILDREN'S SERVICES | JJZROSSLB | THE CROSSROADS JUVENILE CENTER - LIBRARY RENOVATION | 3 | CONSTRUCTION | 2014-06-28 | 2015-06-27 | 2019-03-01 | 2019-05-31
20201123 | BROOKLYN | 068 | ADMIN FOR CHILDREN'S SERVICES | JJZROSSLB | THE CROSSROADS JUVENILE CENTER - LIBRARY RENOVATION | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-06-28 | 2015-06-30 | 2019-06-01 | 2020-07-30
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112AUBR | AUBURN ADULT RESIDENCE - BATHROOM UPGRADE | 1 | DEVELOP SCOPE | 2014-03-30 | 2014-06-27 | 2015-03-02 | 2015-11-26
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112AUBR | AUBURN ADULT RESIDENCE - BATHROOM UPGRADE | 2 | PRELIMINARY DESIGN | 2014-06-28 | 2014-10-25 | 2015-11-27 | 2016-05-24
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112AUBR | AUBURN ADULT RESIDENCE - BATHROOM UPGRADE | 3 | FINAL DESIGN | 2014-10-26 | 2015-04-23 | 2016-05-25 | 2021-02-27
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112AUBR | AUBURN ADULT RESIDENCE - BATHROOM UPGRADE | 4 | BID AWARD AND REGISTER CONTRCT | 2015-04-24 | 2015-07-22 | 2016-05-25 | 2021-02-27
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112AUBR | AUBURN ADULT RESIDENCE - BATHROOM UPGRADE | 5 | CONSTRUCTION TO 25% | 2015-07-23 | 2015-11-19 | 2016-05-25 | 2021-02-27
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112AUBR | AUBURN ADULT RESIDENCE - BATHROOM UPGRADE | 6 | CONSTRUCTION TO 50% | 2015-11-20 | 2016-03-18 | 2016-05-25 | 2021-02-27
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112AUBR | AUBURN ADULT RESIDENCE - BATHROOM UPGRADE | 7 | CONSTRUCTION TO 75% | 2016-03-19 | 2016-07-16 | 2016-05-25 | 2021-02-27
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112AUBR | AUBURN ADULT RESIDENCE - BATHROOM UPGRADE | 8 | ORIGINAL EQUIP & FURNISHING | 2016-07-17 | 2016-10-14 | 2016-05-25 | 2021-02-27
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112AUBR | AUBURN ADULT RESIDENCE - BATHROOM UPGRADE | 9 | SUBSTANTIAL COMPLETION | 2016-10-15 | 2016-12-13 | 2016-05-25 | 2021-02-27
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112AUBR | AUBURN ADULT RESIDENCE - BATHROOM UPGRADE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-12-14 | 2017-01-12 | 2016-05-25 | 2021-02-27
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112AUBR | AUBURN ADULT RESIDENCE - BATHROOM UPGRADE | 11 | DEVELOP SCOPE | 2017-01-13 | 2017-04-12 | 2016-05-25 | 2021-02-27
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112AUBR | AUBURN ADULT RESIDENCE - BATHROOM UPGRADE | 12 | PRELIMINARY DESIGN | 2017-04-13 | 2017-08-10 | 2016-05-25 | 2021-02-27
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112AUBR | AUBURN ADULT RESIDENCE - BATHROOM UPGRADE | 13 | FINAL DESIGN | 2017-08-11 | 2017-12-08 | 2016-05-25 | 2021-02-27
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112AUBR | AUBURN ADULT RESIDENCE - BATHROOM UPGRADE | 14 | BID AWARD AND REGISTER CONTRCT | 2017-12-09 | 2018-06-06 | 2016-05-25 | 2021-02-27
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112AUBR | AUBURN ADULT RESIDENCE - BATHROOM UPGRADE | 15 | CONSTRUCTION TO 25% | 2018-06-07 | 2018-10-04 | 2016-05-25 | 2021-02-27
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112AUBR | AUBURN ADULT RESIDENCE - BATHROOM UPGRADE | 16 | CONSTRUCTION TO 50% | 2018-10-05 | 2019-02-01 | 2016-05-25 | 2021-02-27
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112AUBR | AUBURN ADULT RESIDENCE - BATHROOM UPGRADE | 17 | CONSTRUCTION TO 75% | 2019-02-02 | 2019-06-01 | 2016-05-25 | 2021-02-27
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112AUBR | AUBURN ADULT RESIDENCE - BATHROOM UPGRADE | 18 | ORIGINAL EQUIP & FURNISHING | 2019-06-02 | 2019-08-30 | 2016-05-25 | 2021-02-27
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112AUBR | AUBURN ADULT RESIDENCE - BATHROOM UPGRADE | 19 | SUBSTANTIAL COMPLETION | 2019-08-31 | 2019-10-29 | 2016-05-25 | 2021-02-27
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112AUBR | AUBURN ADULT RESIDENCE - BATHROOM UPGRADE | 20 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-10-30 | 2019-11-28 | 2016-05-25 | 2021-02-27
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112HWCR | HELP WOMEN'S CENTER ROOF | 1 | DESIGN | 2022-01-01 | 2022-09-27 | 2022-01-01 | 2022-09-27
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112HWCR | HELP WOMEN'S CENTER ROOF | 2 | BID AWARD AND REGISTER CONTRCT | 2022-09-28 | 2023-03-26 | 2022-09-28 | 2023-03-26
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112HWCR | HELP WOMEN'S CENTER ROOF | 3 | CONSTRUCTION | 2023-03-27 | 2027-12-30 | 2023-03-27 | 2027-12-30
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112LFER | LINDEN MEN'S SHELTER - ELEVATOR REPLACEMENT | 1 | DESIGN | 2019-01-01 | 2019-09-27 | 2019-01-01 | 2019-09-27
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112LFER | LINDEN MEN'S SHELTER - ELEVATOR REPLACEMENT | 2 | BID AWARD AND REGISTER CONTRCT | 2019-09-28 | 2020-03-25 | 2019-09-28 | 2020-03-25
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112LFER | LINDEN MEN'S SHELTER - ELEVATOR REPLACEMENT | 3 | CONSTRUCTION | 2020-03-26 | 2024-12-29 | 2020-03-26 | 2024-12-29
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112LINT | 85 LEXINGTON AVE BATHROOM RECONSTRUCTION | 1 | DESIGN | 2022-01-01 | 2022-09-27 | 2022-01-01 | 2022-09-27
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112LINT | 85 LEXINGTON AVE BATHROOM RECONSTRUCTION | 2 | BID AWARD AND REGISTER CONTRCT | 2022-09-28 | 2023-03-26 | 2022-09-28 | 2023-03-26
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112LINT | 85 LEXINGTON AVE BATHROOM RECONSTRUCTION | 3 | CONSTRUCTION | 2023-03-27 | 2027-12-30 | 2023-03-27 | 2027-12-30
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112LMEP | LINDEN BOILER RECONSTRUCTION | 1 | DESIGN | 2020-01-01 | 2020-09-26 | 2020-01-01 | 2020-09-26
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112LMEP | LINDEN BOILER RECONSTRUCTION | 2 | BID AWARD AND REGISTER CONTRCT | 2020-09-27 | 2021-03-25 | 2020-09-27 | 2021-03-25
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112LMEP | LINDEN BOILER RECONSTRUCTION | 3 | CONSTRUCTION | 2021-03-26 | 2025-12-29 | 2021-03-26 | 2025-12-29
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112PAFL | PAMOJA HOUSE FLOOR | 1 | DESIGN | 2022-01-01 | 2022-09-27 | 2022-01-01 | 2022-09-27
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112PAFL | PAMOJA HOUSE FLOOR | 2 | BID AWARD AND REGISTER CONTRCT | 2022-09-28 | 2023-03-26 | 2022-09-28 | 2023-03-26
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112PAFL | PAMOJA HOUSE FLOOR | 3 | CONSTRUCTION | 2023-03-27 | 2027-12-30 | 2023-03-27 | 2027-12-30
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112PJBP | PAMOJA HOUSE INSTALLATION OF BLACK FLOW PREVENTER | 1 | DEVELOP SCOPE | 2013-07-16 | 2013-10-13 | 2021-07-01 | 2021-12-27
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112PJBP | PAMOJA HOUSE INSTALLATION OF BLACK FLOW PREVENTER | 2 | PRELIMINARY DESIGN | 2013-10-14 | 2014-02-10 | 2021-12-28 | 2022-06-25
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112PJBP | PAMOJA HOUSE INSTALLATION OF BLACK FLOW PREVENTER | 3 | FINAL DESIGN | 2014-02-11 | 2014-06-10 | 2021-12-28 | 2022-06-25
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112PJBP | PAMOJA HOUSE INSTALLATION OF BLACK FLOW PREVENTER | 4 | BID AWARD AND REGISTER CONTRCT | 2014-06-11 | 2014-12-07 | 2021-12-28 | 2022-06-25
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112PJBP | PAMOJA HOUSE INSTALLATION OF BLACK FLOW PREVENTER | 5 | CONSTRUCTION TO 25% | 2014-12-08 | 2015-04-06 | 2021-12-28 | 2022-06-25
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112PJBP | PAMOJA HOUSE INSTALLATION OF BLACK FLOW PREVENTER | 6 | CONSTRUCTION TO 50% | 2015-04-07 | 2015-08-04 | 2021-12-28 | 2022-06-25
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112PJBP | PAMOJA HOUSE INSTALLATION OF BLACK FLOW PREVENTER | 7 | CONSTRUCTION TO 75% | 2015-08-05 | 2015-12-02 | 2021-12-28 | 2022-06-25
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112PJBP | PAMOJA HOUSE INSTALLATION OF BLACK FLOW PREVENTER | 8 | ORIGINAL EQUIP & FURNISHING | 2015-12-03 | 2016-03-01 | 2021-12-28 | 2022-06-25
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112PJBP | PAMOJA HOUSE INSTALLATION OF BLACK FLOW PREVENTER | 9 | SUBSTANTIAL COMPLETION | 2016-03-02 | 2016-04-30 | 2021-12-28 | 2022-06-25
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112PJBP | PAMOJA HOUSE INSTALLATION OF BLACK FLOW PREVENTER | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-05-01 | 2016-05-30 | 2021-12-28 | 2022-06-25
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112PJRR | PAMOJA HOUSE - ROOF REPLACEMENT | 1 | DEVELOP SCOPE | 2013-08-16 | 2013-11-13 | 2017-06-30 | 2018-03-26
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112PJRR | PAMOJA HOUSE - ROOF REPLACEMENT | 2 | PRELIMINARY DESIGN | 2013-11-14 | 2014-03-13 | 2018-03-27 | 2018-09-22
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112PJRR | PAMOJA HOUSE - ROOF REPLACEMENT | 3 | FINAL DESIGN | 2014-03-14 | 2014-07-11 | 2018-09-23 | 2023-06-28
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112PJRR | PAMOJA HOUSE - ROOF REPLACEMENT | 4 | BID AWARD AND REGISTER CONTRCT | 2014-07-12 | 2015-01-07 | 2018-09-23 | 2023-06-28
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112PJRR | PAMOJA HOUSE - ROOF REPLACEMENT | 5 | CONSTRUCTION TO 25% | 2015-01-08 | 2015-05-07 | 2018-09-23 | 2023-06-28
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112PJRR | PAMOJA HOUSE - ROOF REPLACEMENT | 6 | CONSTRUCTION TO 50% | 2015-05-08 | 2015-09-04 | 2018-09-23 | 2023-06-28
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112PJRR | PAMOJA HOUSE - ROOF REPLACEMENT | 7 | CONSTRUCTION TO 75% | 2015-09-05 | 2016-01-02 | 2018-09-23 | 2023-06-28
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112PJRR | PAMOJA HOUSE - ROOF REPLACEMENT | 8 | ORIGINAL EQUIP & FURNISHING | 2016-01-03 | 2016-04-01 | 2018-09-23 | 2023-06-28
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112PJRR | PAMOJA HOUSE - ROOF REPLACEMENT | 9 | SUBSTANTIAL COMPLETION | 2016-04-02 | 2016-05-31 | 2018-09-23 | 2023-06-28
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112PJRR | PAMOJA HOUSE - ROOF REPLACEMENT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-06-01 | 2016-06-30 | 2018-09-23 | 2023-06-28
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112PREK | RENOVATION AND IMPROVEMENTS TO THE PARK SLOPE ARMORY | 1 | DEVELOP SCOPE | 2014-10-31 | 2015-01-28 | 2019-01-01 | 2019-03-31
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112PREK | RENOVATION AND IMPROVEMENTS TO THE PARK SLOPE ARMORY | 2 | PRELIMINARY DESIGN | 2015-01-29 | 2015-05-28 | 2019-04-01 | 2019-07-29
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112PREK | RENOVATION AND IMPROVEMENTS TO THE PARK SLOPE ARMORY | 3 | FINAL DESIGN | 2015-05-29 | 2015-09-25 | 2019-07-30 | 2019-11-26
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112PREK | RENOVATION AND IMPROVEMENTS TO THE PARK SLOPE ARMORY | 4 | BID AWARD AND REGISTER CONTRCT | 2015-09-26 | 2016-03-23 | 2019-11-27 | 2020-05-24
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112PREK | RENOVATION AND IMPROVEMENTS TO THE PARK SLOPE ARMORY | 5 | CONSTRUCTION TO 25% | 2016-03-24 | 2016-07-21 | 2020-05-25 | 2020-09-21
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112PREK | RENOVATION AND IMPROVEMENTS TO THE PARK SLOPE ARMORY | 6 | CONSTRUCTION TO 50% | 2016-07-22 | 2016-11-18 | 2020-09-22 | 2021-01-19
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112PREK | RENOVATION AND IMPROVEMENTS TO THE PARK SLOPE ARMORY | 7 | CONSTRUCTION TO 75% | 2016-11-19 | 2017-03-18 | 2021-01-20 | 2021-05-19
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112PREK | RENOVATION AND IMPROVEMENTS TO THE PARK SLOPE ARMORY | 8 | ORIGINAL EQUIP & FURNISHING | 2017-03-19 | 2017-06-16 | 2021-05-20 | 2021-08-17
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112PREK | RENOVATION AND IMPROVEMENTS TO THE PARK SLOPE ARMORY | 9 | SUBSTANTIAL COMPLETION | 2017-06-17 | 2017-08-15 | 2021-08-18 | 2021-10-16
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112PREK | RENOVATION AND IMPROVEMENTS TO THE PARK SLOPE ARMORY | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-08-16 | 2017-09-14 | 2021-10-17 | 2021-11-15
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112PSR1 | PARK SLOPE - ROOF REPLACEMENT | 1 | DESIGN | 2016-02-11 | 2016-11-06 | 2016-02-11 | 2016-11-06
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112PSR1 | PARK SLOPE - ROOF REPLACEMENT | 2 | BID AWARD AND REGISTER CONTRCT | 2016-11-07 | 2017-05-05 | 2016-11-07 | 2017-05-05
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112PSR1 | PARK SLOPE - ROOF REPLACEMENT | 3 | CONSTRUCTION | 2017-05-06 | 2022-02-08 | 2017-05-06 | 2022-02-08
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH115BFRR | Bushwick Family Roof Replacement | 1 | DESIGN | 2020-01-01 | 2020-09-26 | 2020-01-01 | 2020-09-26
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH115BFRR | Bushwick Family Roof Replacement | 2 | BID AWARD AND REGISTER CONTRCT | 2020-09-27 | 2021-03-25 | 2020-09-27 | 2021-03-25
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH115BFRR | Bushwick Family Roof Replacement | 3 | CONSTRUCTION | 2021-03-26 | 2025-12-29 | 2021-03-26 | 2025-12-29
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH115BINT | BUSHWICK FAMILY FACADE RECONSTRUCTION | 1 | DESIGN | 2022-01-01 | 2022-09-27 | 2022-01-01 | 2022-09-27
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH115BINT | BUSHWICK FAMILY FACADE RECONSTRUCTION | 2 | BID AWARD AND REGISTER CONTRCT | 2022-09-28 | 2023-03-26 | 2022-09-28 | 2023-03-26
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH115BINT | BUSHWICK FAMILY FACADE RECONSTRUCTION | 3 | CONSTRUCTION | 2023-03-27 | 2027-12-30 | 2023-03-27 | 2027-12-30
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH115FBME | FANNIE BARNES BOILER RECONSTRUCTION | 1 | DESIGN | 2021-05-30 | 2022-02-23 | 2021-05-30 | 2022-02-23
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH115FBME | FANNIE BARNES BOILER RECONSTRUCTION | 2 | BID AWARD AND REGISTER CONTRCT | 2022-02-24 | 2022-08-22 | 2022-02-24 | 2022-08-22
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH115FBME | FANNIE BARNES BOILER RECONSTRUCTION | 3 | CONSTRUCTION | 2022-08-23 | 2027-05-28 | 2022-08-23 | 2027-05-28
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH115FLRF | FLATLANDS ROOF REPLACEMENT | 1 | DESIGN | 2020-01-01 | 2020-09-26 | 2020-01-01 | 2020-09-26
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH115FLRF | FLATLANDS ROOF REPLACEMENT | 2 | BID AWARD AND REGISTER CONTRCT | 2020-09-27 | 2021-03-25 | 2020-09-27 | 2021-03-25
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH115FLRF | FLATLANDS ROOF REPLACEMENT | 3 | CONSTRUCTION | 2021-03-26 | 2025-12-29 | 2021-03-26 | 2025-12-29
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH115MMEP | WAYSIDE MACDONOUGH BOILER RECONS | 1 | DESIGN | 2019-01-01 | 2019-09-27 | 2019-01-01 | 2019-09-27
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH115MMEP | WAYSIDE MACDONOUGH BOILER RECONS | 2 | BID AWARD AND REGISTER CONTRCT | 2019-09-28 | 2020-03-25 | 2019-09-28 | 2020-03-25
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH115MMEP | WAYSIDE MACDONOUGH BOILER RECONS | 3 | CONSTRUCTION | 2020-03-26 | 2024-12-29 | 2020-03-26 | 2024-12-29
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH115RMCX | ROSE MCCARTHY - WINDOW REPLACEMENT AND EXTERIOR RECONSTRUCT | 1 | PROJECT START | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-09-27
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH115RMCX | ROSE MCCARTHY - WINDOW REPLACEMENT AND EXTERIOR RECONSTRUCT | 2 | DESIGN START | 2018-01-02 | 2018-07-01 | 2018-09-28 | 2019-03-26
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH115RMCX | ROSE MCCARTHY - WINDOW REPLACEMENT AND EXTERIOR RECONSTRUCT | 3 | DESIGN COMPLETION | 2018-07-02 | 2019-01-01 | 2019-03-27 | 2023-12-30
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH115RMCX | ROSE MCCARTHY - WINDOW REPLACEMENT AND EXTERIOR RECONSTRUCT | 4 | CONSTRUCTION START | 2019-01-02 | 2019-07-01 | 2019-03-27 | 2023-12-30
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH115RMCX | ROSE MCCARTHY - WINDOW REPLACEMENT AND EXTERIOR RECONSTRUCT | 5 | CONSTRUCTION COMPLETION | 2019-07-02 | 2020-12-31 | 2019-03-27 | 2023-12-30
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH115SAEU | FANNIE BARNES EXTERIOR UPGRADE | 1 | DESIGN | 2022-01-01 | 2022-09-27 | 2022-01-01 | 2022-09-27
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH115SAEU | FANNIE BARNES EXTERIOR UPGRADE | 2 | BID AWARD AND REGISTER CONTRCT | 2022-09-28 | 2023-03-26 | 2022-09-28 | 2023-03-26
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH115SAEU | FANNIE BARNES EXTERIOR UPGRADE | 3 | CONSTRUCTION | 2023-03-27 | 2027-12-30 | 2023-03-27 | 2027-12-30
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH115SEXT | STOCKHOLM FAMILY CENTER - ROOF AND FACADE RECONSTRUCTION | 1 | DESIGN | 2022-01-01 | 2022-09-27 | 2022-01-01 | 2022-09-27
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH115SEXT | STOCKHOLM FAMILY CENTER - ROOF AND FACADE RECONSTRUCTION | 2 | BID AWARD AND REGISTER CONTRCT | 2022-09-28 | 2023-03-26 | 2022-09-28 | 2023-03-26
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH115SEXT | STOCKHOLM FAMILY CENTER - ROOF AND FACADE RECONSTRUCTION | 3 | CONSTRUCTION | 2023-03-27 | 2027-12-30 | 2023-03-27 | 2027-12-30
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH115STEP | STOCKHOLM FAMILY CENTER -BOILER RECONSTRUCTION | 1 | DESIGN | 2019-07-03 | 2020-03-28 | 2019-07-03 | 2020-03-28
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH115STEP | STOCKHOLM FAMILY CENTER -BOILER RECONSTRUCTION | 2 | BID AWARD AND REGISTER CONTRCT | 2020-03-29 | 2020-09-24 | 2020-03-29 | 2020-09-24
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH115STEP | STOCKHOLM FAMILY CENTER -BOILER RECONSTRUCTION | 3 | CONSTRUCTION | 2020-09-25 | 2025-06-30 | 2020-09-25 | 2025-06-30
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HHCN001 | BROOKLYN NEIGHBORHOOD IMPROVEMENT DIST.-BEDFORD AVE. RENOVAT | 1 | DEVELOP SCOPE | 2014-01-02 | 2014-04-01 | 2019-08-16 | 2019-11-13
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HHCN001 | BROOKLYN NEIGHBORHOOD IMPROVEMENT DIST.-BEDFORD AVE. RENOVAT | 2 | PRELIMINARY DESIGN | 2014-04-02 | 2014-07-30 | 2019-11-14 | 2020-03-12
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HHCN001 | BROOKLYN NEIGHBORHOOD IMPROVEMENT DIST.-BEDFORD AVE. RENOVAT | 3 | FINAL DESIGN | 2014-07-31 | 2014-11-27 | 2020-03-13 | 2020-07-10
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HHCN001 | BROOKLYN NEIGHBORHOOD IMPROVEMENT DIST.-BEDFORD AVE. RENOVAT | 4 | BID AWARD AND REGISTER CONTRCT | 2014-11-28 | 2015-05-26 | 2020-07-11 | 2021-01-06
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HHCN001 | BROOKLYN NEIGHBORHOOD IMPROVEMENT DIST.-BEDFORD AVE. RENOVAT | 5 | CONSTRUCTION TO 25% | 2015-05-27 | 2015-09-23 | 2021-01-07 | 2021-05-06
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HHCN001 | BROOKLYN NEIGHBORHOOD IMPROVEMENT DIST.-BEDFORD AVE. RENOVAT | 6 | CONSTRUCTION TO 50% | 2015-09-24 | 2016-01-21 | 2021-05-07 | 2021-09-03
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HHCN001 | BROOKLYN NEIGHBORHOOD IMPROVEMENT DIST.-BEDFORD AVE. RENOVAT | 7 | CONSTRUCTION TO 75% | 2016-01-22 | 2016-05-20 | 2021-09-04 | 2022-01-01
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HHCN001 | BROOKLYN NEIGHBORHOOD IMPROVEMENT DIST.-BEDFORD AVE. RENOVAT | 8 | ORIGINAL EQUIP & FURNISHING | 2016-05-21 | 2016-08-18 | 2022-01-02 | 2022-04-01
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HHCN001 | BROOKLYN NEIGHBORHOOD IMPROVEMENT DIST.-BEDFORD AVE. RENOVAT | 9 | SUBSTANTIAL COMPLETION | 2016-08-19 | 2016-10-17 | 2022-04-02 | 2022-05-31
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HHCN001 | BROOKLYN NEIGHBORHOOD IMPROVEMENT DIST.-BEDFORD AVE. RENOVAT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-10-18 | 2016-11-16 | 2022-06-01 | 2022-06-30
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HHCN002 | RENOVATION OF BEDFORD ATLANTIC ARMORY INTO RECREATIONAL CTR. | 1 | DEVELOP SCOPE | 2017-01-13 | 2017-04-12 | 2019-01-13 | 2021-04-12
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HHCN002 | RENOVATION OF BEDFORD ATLANTIC ARMORY INTO RECREATIONAL CTR. | 2 | PRELIMINARY DESIGN | 2017-04-13 | 2017-08-10 | 2017-01-13 | 2017-04-12
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HHCN002 | RENOVATION OF BEDFORD ATLANTIC ARMORY INTO RECREATIONAL CTR. | 3 | FINAL DESIGN | 2017-08-11 | 2017-12-08 | 2017-04-13 | 2017-04-12
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HHCN002 | RENOVATION OF BEDFORD ATLANTIC ARMORY INTO RECREATIONAL CTR. | 4 | BID AWARD AND REGISTER CONTRCT | 2017-12-09 | 2018-06-06 | 2017-04-13 | 2017-04-12
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HHCN002 | RENOVATION OF BEDFORD ATLANTIC ARMORY INTO RECREATIONAL CTR. | 5 | CONSTRUCTION TO 25% | 2018-06-07 | 2018-10-04 | 2017-04-13 | 2017-04-12
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HHCN002 | RENOVATION OF BEDFORD ATLANTIC ARMORY INTO RECREATIONAL CTR. | 6 | CONSTRUCTION TO 50% | 2018-10-05 | 2019-02-01 | 2017-04-13 | 2017-04-12
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HHCN002 | RENOVATION OF BEDFORD ATLANTIC ARMORY INTO RECREATIONAL CTR. | 7 | CONSTRUCTION TO 75% | 2019-02-02 | 2019-06-01 | 2017-04-13 | 2027-04-12
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HHCN002 | RENOVATION OF BEDFORD ATLANTIC ARMORY INTO RECREATIONAL CTR. | 8 | ORIGINAL EQUIP & FURNISHING | 2019-06-02 | 2019-08-30 | 2027-04-13 | 2027-04-12
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HHCN002 | RENOVATION OF BEDFORD ATLANTIC ARMORY INTO RECREATIONAL CTR. | 9 | SUBSTANTIAL COMPLETION | 2019-08-31 | 2019-10-29 | 2027-04-13 | 2027-04-12
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HHCN002 | RENOVATION OF BEDFORD ATLANTIC ARMORY INTO RECREATIONAL CTR. | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-10-30 | 2019-11-28 | 2027-04-13 | 2027-05-12
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HHCN003 | BEDFORD ATLANTIC ARMORY ATHLETIC CENTER | 1 | DEVELOP SCOPE | 2017-01-13 | 2017-04-12 | 2022-01-13 | 2024-04-12
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HHCN003 | BEDFORD ATLANTIC ARMORY ATHLETIC CENTER | 2 | PRELIMINARY DESIGN | 2017-04-13 | 2017-08-10 | 2024-04-13 | 2024-04-12
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HHCN003 | BEDFORD ATLANTIC ARMORY ATHLETIC CENTER | 3 | FINAL DESIGN | 2017-08-11 | 2017-12-08 | 2024-04-13 | 2024-04-12
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HHCN003 | BEDFORD ATLANTIC ARMORY ATHLETIC CENTER | 4 | BID AWARD AND REGISTER CONTRCT | 2017-12-09 | 2018-06-06 | 2024-04-13 | 2024-04-12
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HHCN003 | BEDFORD ATLANTIC ARMORY ATHLETIC CENTER | 5 | CONSTRUCTION TO 25% | 2018-06-07 | 2018-10-04 | 2024-04-13 | 2024-04-12
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HHCN003 | BEDFORD ATLANTIC ARMORY ATHLETIC CENTER | 6 | CONSTRUCTION TO 50% | 2018-10-05 | 2019-02-01 | 2024-04-13 | 2024-04-12
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HHCN003 | BEDFORD ATLANTIC ARMORY ATHLETIC CENTER | 7 | CONSTRUCTION TO 75% | 2019-02-02 | 2019-06-01 | 2024-04-13 | 2024-04-12
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HHCN003 | BEDFORD ATLANTIC ARMORY ATHLETIC CENTER | 8 | ORIGINAL EQUIP & FURNISHING | 2019-06-02 | 2019-08-30 | 2024-04-13 | 2024-04-12
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HHCN003 | BEDFORD ATLANTIC ARMORY ATHLETIC CENTER | 9 | SUBSTANTIAL COMPLETION | 2019-08-31 | 2019-10-29 | 2024-04-13 | 2024-04-12
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HHCN003 | BEDFORD ATLANTIC ARMORY ATHLETIC CENTER | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-10-30 | 2019-11-28 | 2024-04-13 | 2024-05-12
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | SOLARDHS3 | Solar PV system - Flatlands Residence | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-06-30 | 2020-06-01 | 2020-06-30
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | SOLARDHS3 | Solar PV system - Flatlands Residence | 2 | BID AWARD AND REGISTER CONTRCT | 2020-07-01 | 2020-08-29 | 2020-07-01 | 2020-08-29
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | SOLARDHS3 | Solar PV system - Flatlands Residence | 3 | CONSTRUCTION TO 50% | 2020-08-30 | 2021-02-25 | 2020-08-30 | 2021-02-25
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | SOLARDHS3 | Solar PV system - Flatlands Residence | 4 | CONSTRUCTION TO 75% | 2021-02-26 | 2021-05-26 | 2021-02-26 | 2021-05-26
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | SOLARDHS3 | Solar PV system - Flatlands Residence | 5 | SUBSTANTIAL COMPLETION | 2021-05-27 | 2021-07-25 | 2021-05-27 | 2021-07-25
20201123 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | SOLARDHS3 | Solar PV system - Flatlands Residence | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-07-26 | 2021-08-24 | 2021-07-26 | 2021-08-24
20201123 | BROOKLYN | 096 | HUMAN RESOURCES ADMINISTRATION | HR25BRCS | Brownsville Community Center | 1 | DEVELOP SCOPE | 2020-06-30 | 2020-09-27 | 2020-06-30 | 2020-09-27
20201123 | BROOKLYN | 096 | HUMAN RESOURCES ADMINISTRATION | HR25BRCS | Brownsville Community Center | 2 | PRELIMINARY DESIGN | 2020-09-28 | 2021-01-25 | 2020-09-28 | 2021-01-25
20201123 | BROOKLYN | 096 | HUMAN RESOURCES ADMINISTRATION | HR25BRCS | Brownsville Community Center | 3 | FINAL DESIGN | 2021-01-26 | 2021-07-24 | 2021-01-26 | 2021-07-24
20201123 | BROOKLYN | 096 | HUMAN RESOURCES ADMINISTRATION | HR25BRCS | Brownsville Community Center | 4 | BID AWARD AND REGISTER CONTRCT | 2021-07-25 | 2021-10-22 | 2021-07-25 | 2021-10-22
20201123 | BROOKLYN | 096 | HUMAN RESOURCES ADMINISTRATION | HR25BRCS | Brownsville Community Center | 5 | CONSTRUCTION TO 25% | 2021-10-23 | 2022-02-19 | 2021-10-23 | 2022-02-19
20201123 | BROOKLYN | 096 | HUMAN RESOURCES ADMINISTRATION | HR25BRCS | Brownsville Community Center | 6 | CONSTRUCTION TO 50% | 2022-02-20 | 2022-06-19 | 2022-02-20 | 2022-06-19
20201123 | BROOKLYN | 096 | HUMAN RESOURCES ADMINISTRATION | HR25BRCS | Brownsville Community Center | 7 | CONSTRUCTION TO 75% | 2022-06-20 | 2022-10-17 | 2022-06-20 | 2022-10-17
20201123 | BROOKLYN | 096 | HUMAN RESOURCES ADMINISTRATION | HR25BRCS | Brownsville Community Center | 8 | ORIGINAL EQUIP & FURNISHING | 2022-10-18 | 2023-01-15 | 2022-10-18 | 2023-01-15
20201123 | BROOKLYN | 096 | HUMAN RESOURCES ADMINISTRATION | HR25BRCS | Brownsville Community Center | 9 | SUBSTANTIAL COMPLETION | 2023-01-16 | 2023-03-16 | 2023-01-16 | 2023-03-16
20201123 | BROOKLYN | 096 | HUMAN RESOURCES ADMINISTRATION | HR25BRCS | Brownsville Community Center | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-03-17 | 2023-04-15 | 2023-03-17 | 2023-04-15
20201123 | BROOKLYN | 096 | HUMAN RESOURCES ADMINISTRATION | HR25ENY | East New York Office, 2440 Fulton Street, Brooklyn | 1 | DESIGN | 2022-07-01 | 2022-12-27 | 2022-07-01 | 2022-12-27
20201123 | BROOKLYN | 096 | HUMAN RESOURCES ADMINISTRATION | HR25ENY | East New York Office, 2440 Fulton Street, Brooklyn | 2 | CONSTRUCTION | 2022-12-28 | 2023-06-25 | 2022-12-28 | 2023-06-25
20201123 | BROOKLYN | 096 | HUMAN RESOURCES ADMINISTRATION | HR25FOSF2 | Initial Outfitting of 102-50 Foster Avenue (Warehouse Space) | 1 | DESIGN | 2020-07-01 | 2020-12-27 | 2020-07-01 | 2020-12-27
20201123 | BROOKLYN | 096 | HUMAN RESOURCES ADMINISTRATION | HR25FOSF2 | Initial Outfitting of 102-50 Foster Avenue (Warehouse Space) | 2 | CONSTRUCTION | 2020-12-28 | 2021-06-25 | 2020-12-28 | 2021-06-25
20201123 | BROOKLYN | 096 | HUMAN RESOURCES ADMINISTRATION | HR25FOST2 | Construction at 102-50 Foster Ave to accomodate warehouses | 1 | DESIGN | 2019-10-01 | 2020-03-28 | 2019-10-01 | 2020-03-28
20201123 | BROOKLYN | 096 | HUMAN RESOURCES ADMINISTRATION | HR25FOST2 | Construction at 102-50 Foster Ave to accomodate warehouses | 2 | CONSTRUCTION | 2020-03-29 | 2020-09-24 | 2020-03-29 | 2020-09-24
20201123 | BROOKLYN | 096 | HUMAN RESOURCES ADMINISTRATION | HRCNBDST | Bedford Stuyvesant MSC Boiler Replacement, 1958 Fulton St | 1 | DESIGN | 2010-11-01 | 2011-02-15 | 2020-07-01 | 2020-12-27
20201123 | BROOKLYN | 096 | HUMAN RESOURCES ADMINISTRATION | HRCNBDST | Bedford Stuyvesant MSC Boiler Replacement, 1958 Fulton St | 2 | CONSTRUCTION | 2011-02-16 | 2011-08-14 | 2020-12-28 | 2021-06-25
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV230-SEA | WCS - New York Aquarium - Sea Cliffs Exhibit | 1 | DEVELOP SCOPE | 2015-08-15 | 2015-11-12 | 2022-09-09 | 2023-10-06
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV230-SEA | WCS - New York Aquarium - Sea Cliffs Exhibit | 2 | BID AWARD AND REGISTER CONTRCT | 2015-11-13 | 2016-02-10 | 2015-09-13 | 2015-12-11
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV230-SEA | WCS - New York Aquarium - Sea Cliffs Exhibit | 3 | CONSTRUCTION TO 50% | 2016-02-11 | 2016-06-09 | 2015-12-12 | 2016-04-09
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV230-SEA | WCS - New York Aquarium - Sea Cliffs Exhibit | 4 | CONSTRUCTION TO 75% | 2016-06-10 | 2016-08-08 | 2016-04-10 | 2016-06-08
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV230-SEA | WCS - New York Aquarium - Sea Cliffs Exhibit | 5 | SUBSTANTIAL COMPLETION | 2016-08-09 | 2016-10-07 | 2016-06-09 | 2016-08-07
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV230-SEA | WCS - New York Aquarium - Sea Cliffs Exhibit | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-10-08 | 2016-11-06 | 2016-08-08 | 2016-09-06
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV235AFAR | BMA - Brooklyn Museum - African Art Gallery Renovations | 1 | DEVELOP SCOPE | 2023-06-30 | 2023-09-27 | 2023-06-30 | 2023-09-27
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV235AFAR | BMA - Brooklyn Museum - African Art Gallery Renovations | 2 | BID AWARD AND REGISTER CONTRCT | 2023-09-28 | 2023-12-26 | 2023-09-28 | 2024-01-25
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV235AFAR | BMA - Brooklyn Museum - African Art Gallery Renovations | 3 | CONSTRUCTION TO 50% | 2023-12-27 | 2024-04-24 | 2024-01-26 | 2024-07-23
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV235AFAR | BMA - Brooklyn Museum - African Art Gallery Renovations | 4 | CONSTRUCTION TO 75% | 2024-04-25 | 2024-06-23 | 2024-07-24 | 2024-10-21
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV235AFAR | BMA - Brooklyn Museum - African Art Gallery Renovations | 5 | SUBSTANTIAL COMPLETION | 2024-06-24 | 2024-08-22 | 2024-10-22 | 2025-02-18
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV235AFAR | BMA - Brooklyn Museum - African Art Gallery Renovations | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-08-23 | 2024-09-21 | 2025-02-19 | 2025-06-18
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV235AFAR | BMA - Brooklyn Museum - African Art Gallery Renovations | 7 | DEVELOP SCOPE | 2024-09-22 | 2024-12-20 | 2025-06-19 | 2025-10-16
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV235AFAR | BMA - Brooklyn Museum - African Art Gallery Renovations | 8 | PRELIMINARY DESIGN | 2024-12-21 | 2025-04-19 | 2025-10-17 | 2026-01-14
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV235AFAR | BMA - Brooklyn Museum - African Art Gallery Renovations | 9 | FINAL DESIGN | 2025-04-20 | 2025-10-16 | 2026-01-15 | 2026-03-15
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV235AFAR | BMA - Brooklyn Museum - African Art Gallery Renovations | 10 | BID AWARD AND REGISTER CONTRCT | 2025-10-17 | 2026-01-14 | 2026-03-16 | 2026-04-14
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV235AFAR | BMA - Brooklyn Museum - African Art Gallery Renovations | 11 | CONSTRUCTION TO 25% | 2026-01-15 | 2026-05-14 | 2026-03-16 | 2026-04-14
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV235AFAR | BMA - Brooklyn Museum - African Art Gallery Renovations | 12 | CONSTRUCTION TO 50% | 2026-05-15 | 2026-09-11 | 2026-03-16 | 2026-04-14
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV235AFAR | BMA - Brooklyn Museum - African Art Gallery Renovations | 13 | CONSTRUCTION TO 75% | 2026-09-12 | 2027-01-09 | 2026-03-16 | 2026-04-14
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV235AFAR | BMA - Brooklyn Museum - African Art Gallery Renovations | 14 | ORIGINAL EQUIP & FURNISHING | 2027-01-10 | 2027-04-09 | 2026-03-16 | 2026-04-14
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV235AFAR | BMA - Brooklyn Museum - African Art Gallery Renovations | 15 | SUBSTANTIAL COMPLETION | 2027-04-10 | 2027-06-08 | 2026-03-16 | 2026-04-14
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV235AFAR | BMA - Brooklyn Museum - African Art Gallery Renovations | 16 | PUNCHLIST COMPLETE, JOB CLOSED | 2027-06-09 | 2027-07-08 | 2026-03-16 | 2026-04-14
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV235EDUC | BMA - Brooklyn Museum - Education Space | 1 | DEVELOP SCOPE | 2014-11-15 | 2015-02-12 | 2023-07-01 | 2024-07-01
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV235EDUC | BMA - Brooklyn Museum - Education Space | 2 | PRELIMINARY DESIGN | 2015-02-13 | 2015-06-12 | 2024-07-02 | 2024-10-29
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV235EDUC | BMA - Brooklyn Museum - Education Space | 3 | FINAL DESIGN | 2015-06-13 | 2015-12-09 | 2024-10-30 | 2025-04-27
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV235EDUC | BMA - Brooklyn Museum - Education Space | 4 | BID AWARD AND REGISTER CONTRCT | 2015-12-10 | 2016-03-08 | 2025-04-28 | 2025-07-26
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV235EDUC | BMA - Brooklyn Museum - Education Space | 5 | CONSTRUCTION TO 25% | 2016-03-09 | 2016-07-06 | 2025-07-27 | 2025-11-23
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV235EDUC | BMA - Brooklyn Museum - Education Space | 6 | CONSTRUCTION TO 50% | 2016-07-07 | 2016-11-03 | 2025-11-24 | 2026-03-23
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV235EDUC | BMA - Brooklyn Museum - Education Space | 7 | CONSTRUCTION TO 75% | 2016-11-04 | 2017-03-03 | 2026-03-24 | 2026-07-21
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV235EDUC | BMA - Brooklyn Museum - Education Space | 8 | ORIGINAL EQUIP & FURNISHING | 2017-03-04 | 2017-06-01 | 2026-07-22 | 2026-10-19
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV235EDUC | BMA - Brooklyn Museum - Education Space | 9 | SUBSTANTIAL COMPLETION | 2017-06-02 | 2017-07-31 | 2026-10-20 | 2026-12-18
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV235EDUC | BMA - Brooklyn Museum - Education Space | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-08-01 | 2017-08-30 | 2026-12-19 | 2027-01-17
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV236AUDI | BBG - Auditorium Renovations | 1 | DEVELOP SCOPE | 2010-12-01 | 2011-02-28 | 2023-06-30 | 2023-09-27
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV236AUDI | BBG - Auditorium Renovations | 2 | PRELIMINARY DESIGN | 2011-03-01 | 2011-06-28 | 2023-09-28 | 2024-01-25
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV236AUDI | BBG - Auditorium Renovations | 3 | FINAL DESIGN | 2011-06-29 | 2011-12-25 | 2024-01-26 | 2024-07-23
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV236AUDI | BBG - Auditorium Renovations | 4 | BID AWARD AND REGISTER CONTRCT | 2011-12-26 | 2012-03-24 | 2024-07-24 | 2024-10-21
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV236AUDI | BBG - Auditorium Renovations | 5 | CONSTRUCTION TO 25% | 2012-03-25 | 2012-07-22 | 2024-10-22 | 2025-02-18
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV236AUDI | BBG - Auditorium Renovations | 6 | CONSTRUCTION TO 50% | 2012-07-23 | 2012-11-19 | 2025-02-19 | 2025-06-18
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV236AUDI | BBG - Auditorium Renovations | 7 | CONSTRUCTION TO 75% | 2012-11-20 | 2013-03-19 | 2025-06-19 | 2025-10-16
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV236AUDI | BBG - Auditorium Renovations | 8 | ORIGINAL EQUIP & FURNISHING | 2013-03-20 | 2013-06-17 | 2025-10-17 | 2026-01-14
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV236AUDI | BBG - Auditorium Renovations | 9 | SUBSTANTIAL COMPLETION | 2013-06-18 | 2013-08-16 | 2026-01-15 | 2026-03-15
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV236AUDI | BBG - Auditorium Renovations | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-08-17 | 2013-09-15 | 2026-03-16 | 2026-04-14
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV236BCSG | BBG - Brooklyn Botanic Garden - Sustainable Gardening Center | 1 | CONSTRUCTION | 2016-09-28 | 2017-09-22 | 2023-06-30 | 2023-09-27
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV236BCSG | BBG - Brooklyn Botanic Garden - Sustainable Gardening Center | 2 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-09-23 | 2018-09-17 | 2023-09-28 | 2024-09-21
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV236BCSG | BBG - Brooklyn Botanic Garden - Sustainable Gardening Center | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-09-23 | 2018-09-17 | 2024-09-22 | 2025-09-16
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV236ROSE | BBG -Brooklyn Botanic Garden - Accessibility Improvements | 1 | DEVELOP SCOPE | 2021-06-30 | 2021-09-27 | 2024-06-30 | 2024-09-27
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV236ROSE | BBG -Brooklyn Botanic Garden - Accessibility Improvements | 2 | BID AWARD AND REGISTER CONTRCT | 2021-09-28 | 2021-12-26 | 2024-09-28 | 2024-12-26
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV236ROSE | BBG -Brooklyn Botanic Garden - Accessibility Improvements | 3 | CONSTRUCTION TO 50% | 2021-12-27 | 2022-04-25 | 2024-12-27 | 2025-04-25
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV236ROSE | BBG -Brooklyn Botanic Garden - Accessibility Improvements | 4 | CONSTRUCTION TO 75% | 2022-04-26 | 2022-06-24 | 2025-04-26 | 2025-06-24
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV236ROSE | BBG -Brooklyn Botanic Garden - Accessibility Improvements | 5 | SUBSTANTIAL COMPLETION | 2022-06-25 | 2022-08-23 | 2025-06-25 | 2025-08-23
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV236ROSE | BBG -Brooklyn Botanic Garden - Accessibility Improvements | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-08-24 | 2022-09-22 | 2025-08-24 | 2025-09-22
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV262HVAC | BCM - Brooklyn Children's Museum - HVAC | 1 | DEVELOP SCOPE | 2021-06-30 | 2021-09-27 | 2021-06-30 | 2021-09-27
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV262HVAC | BCM - Brooklyn Children's Museum - HVAC | 2 | PRELIMINARY DESIGN | 2021-09-28 | 2022-01-25 | 2021-09-28 | 2022-01-25
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV262HVAC | BCM - Brooklyn Children's Museum - HVAC | 3 | FINAL DESIGN | 2022-01-26 | 2022-07-24 | 2022-01-26 | 2022-07-24
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV262HVAC | BCM - Brooklyn Children's Museum - HVAC | 4 | BID AWARD AND REGISTER CONTRCT | 2022-07-25 | 2022-10-22 | 2022-07-25 | 2022-10-22
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV262HVAC | BCM - Brooklyn Children's Museum - HVAC | 5 | CONSTRUCTION TO 25% | 2022-10-23 | 2023-02-19 | 2022-10-23 | 2023-02-19
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV262HVAC | BCM - Brooklyn Children's Museum - HVAC | 6 | CONSTRUCTION TO 50% | 2023-02-20 | 2023-06-19 | 2023-02-20 | 2023-06-19
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV262HVAC | BCM - Brooklyn Children's Museum - HVAC | 7 | CONSTRUCTION TO 75% | 2023-06-20 | 2023-10-17 | 2023-06-20 | 2023-10-17
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV262HVAC | BCM - Brooklyn Children's Museum - HVAC | 8 | ORIGINAL EQUIP & FURNISHING | 2023-10-18 | 2024-01-15 | 2023-10-18 | 2024-01-15
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV262HVAC | BCM - Brooklyn Children's Museum - HVAC | 9 | SUBSTANTIAL COMPLETION | 2024-01-16 | 2024-03-15 | 2024-01-16 | 2024-03-15
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV262HVAC | BCM - Brooklyn Children's Museum - HVAC | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-03-16 | 2024-04-14 | 2024-03-16 | 2024-04-14
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV262PRNG | BCM - FHWA Parking Lot - 906 Prospect Place | 1 | DEVELOP SCOPE | 2012-06-30 | 2012-09-27 | 2023-06-30 | 2023-09-27
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV262PRNG | BCM - FHWA Parking Lot - 906 Prospect Place | 2 | PRELIMINARY DESIGN | 2012-09-28 | 2013-01-25 | 2023-09-28 | 2024-01-25
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV262PRNG | BCM - FHWA Parking Lot - 906 Prospect Place | 3 | FINAL DESIGN | 2013-01-26 | 2013-07-24 | 2024-01-26 | 2024-07-23
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV262PRNG | BCM - FHWA Parking Lot - 906 Prospect Place | 4 | BID AWARD AND REGISTER CONTRCT | 2013-07-25 | 2013-10-22 | 2024-07-24 | 2024-10-21
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV262PRNG | BCM - FHWA Parking Lot - 906 Prospect Place | 5 | CONSTRUCTION TO 25% | 2013-10-23 | 2014-02-19 | 2024-10-22 | 2025-02-18
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV262PRNG | BCM - FHWA Parking Lot - 906 Prospect Place | 6 | CONSTRUCTION TO 50% | 2014-02-20 | 2014-06-19 | 2025-02-19 | 2025-06-18
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV262PRNG | BCM - FHWA Parking Lot - 906 Prospect Place | 7 | CONSTRUCTION TO 75% | 2014-06-20 | 2014-10-17 | 2025-06-19 | 2025-10-16
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV262PRNG | BCM - FHWA Parking Lot - 906 Prospect Place | 8 | ORIGINAL EQUIP & FURNISHING | 2014-10-18 | 2015-01-15 | 2025-10-17 | 2026-01-14
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV262PRNG | BCM - FHWA Parking Lot - 906 Prospect Place | 9 | SUBSTANTIAL COMPLETION | 2015-01-16 | 2015-03-16 | 2026-01-15 | 2026-03-15
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV262PRNG | BCM - FHWA Parking Lot - 906 Prospect Place | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-17 | 2015-04-15 | 2026-03-16 | 2026-04-14
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV264ROSE | BAM - Rose Renovation | 1 | DEVELOP SCOPE | 2021-06-30 | 2021-09-27 | 2021-06-30 | 2021-09-27
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV264ROSE | BAM - Rose Renovation | 2 | PRELIMINARY DESIGN | 2021-09-28 | 2022-01-25 | 2021-09-28 | 2022-01-25
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV264ROSE | BAM - Rose Renovation | 3 | FINAL DESIGN | 2022-01-26 | 2022-07-24 | 2022-01-26 | 2022-07-24
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV264ROSE | BAM - Rose Renovation | 4 | BID AWARD AND REGISTER CONTRCT | 2022-07-25 | 2022-10-22 | 2022-07-25 | 2022-10-22
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV264ROSE | BAM - Rose Renovation | 5 | CONSTRUCTION TO 25% | 2022-10-23 | 2023-02-19 | 2022-10-23 | 2023-02-19
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV264ROSE | BAM - Rose Renovation | 6 | CONSTRUCTION TO 50% | 2023-02-20 | 2023-06-19 | 2023-02-20 | 2023-06-19
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV264ROSE | BAM - Rose Renovation | 7 | CONSTRUCTION TO 75% | 2023-06-20 | 2023-10-17 | 2023-06-20 | 2023-10-17
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV264ROSE | BAM - Rose Renovation | 8 | ORIGINAL EQUIP & FURNISHING | 2023-10-18 | 2024-01-15 | 2023-10-18 | 2024-01-15
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV264ROSE | BAM - Rose Renovation | 9 | SUBSTANTIAL COMPLETION | 2024-01-16 | 2024-03-15 | 2024-01-16 | 2024-03-15
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV264ROSE | BAM - Rose Renovation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-03-16 | 2024-04-14 | 2024-03-16 | 2024-04-14
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467BKLN | DCA - Brooklyn Fund | 1 | DEVELOP SCOPE | 2024-07-30 | 2024-10-27 | 2024-07-30 | 2024-10-27
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467BKLN | DCA - Brooklyn Fund | 2 | PRELIMINARY DESIGN | 2024-10-28 | 2025-02-24 | 2024-10-28 | 2025-02-24
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467BKLN | DCA - Brooklyn Fund | 3 | FINAL DESIGN | 2025-02-25 | 2025-08-23 | 2025-02-25 | 2025-08-23
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467BKLN | DCA - Brooklyn Fund | 4 | BID AWARD AND REGISTER CONTRCT | 2025-08-24 | 2025-11-21 | 2025-08-24 | 2025-11-21
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467BKLN | DCA - Brooklyn Fund | 5 | CONSTRUCTION TO 25% | 2025-11-22 | 2026-03-21 | 2025-11-22 | 2026-03-21
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467BKLN | DCA - Brooklyn Fund | 6 | CONSTRUCTION TO 50% | 2026-03-22 | 2026-07-19 | 2026-03-22 | 2026-07-19
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467BKLN | DCA - Brooklyn Fund | 7 | CONSTRUCTION TO 75% | 2026-07-20 | 2026-11-16 | 2026-07-20 | 2026-11-16
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467BKLN | DCA - Brooklyn Fund | 8 | ORIGINAL EQUIP & FURNISHING | 2026-11-17 | 2027-02-14 | 2026-11-17 | 2027-02-14
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467BKLN | DCA - Brooklyn Fund | 9 | SUBSTANTIAL COMPLETION | 2027-02-15 | 2027-04-15 | 2027-02-15 | 2027-04-15
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467BKLN | DCA - Brooklyn Fund | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2027-04-16 | 2027-05-15 | 2027-04-16 | 2027-05-15
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467SWBB | Spaceworks Brooklyn Bridge Park | 1 | DEVELOP SCOPE | 2017-12-15 | 2018-03-14 | 2024-06-30 | 2024-09-27
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467SWBB | Spaceworks Brooklyn Bridge Park | 2 | PRELIMINARY DESIGN | 2018-03-15 | 2018-07-12 | 2024-09-28 | 2025-01-25
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467SWBB | Spaceworks Brooklyn Bridge Park | 3 | FINAL DESIGN | 2018-07-13 | 2019-01-08 | 2025-01-26 | 2025-07-24
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467SWBB | Spaceworks Brooklyn Bridge Park | 4 | BID AWARD AND REGISTER CONTRCT | 2019-01-09 | 2019-04-08 | 2025-07-25 | 2025-10-22
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467SWBB | Spaceworks Brooklyn Bridge Park | 5 | CONSTRUCTION TO 25% | 2019-04-09 | 2019-08-06 | 2025-10-23 | 2026-02-19
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467SWBB | Spaceworks Brooklyn Bridge Park | 6 | CONSTRUCTION TO 50% | 2019-08-07 | 2019-12-04 | 2026-02-20 | 2026-06-19
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467SWBB | Spaceworks Brooklyn Bridge Park | 7 | CONSTRUCTION TO 75% | 2019-12-05 | 2020-04-02 | 2026-06-20 | 2026-10-17
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467SWBB | Spaceworks Brooklyn Bridge Park | 8 | ORIGINAL EQUIP & FURNISHING | 2020-04-03 | 2020-07-01 | 2026-10-18 | 2027-01-15
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467SWBB | Spaceworks Brooklyn Bridge Park | 9 | SUBSTANTIAL COMPLETION | 2020-07-02 | 2020-08-30 | 2027-01-16 | 2027-03-16
20201123 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467SWBB | Spaceworks Brooklyn Bridge Park | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-08-31 | 2020-09-29 | 2027-03-17 | 2027-04-15
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BAMNSITEA | BAM Cultural District - North Site Condemnation | 1 | DESIGN | 2010-01-01 | 2012-01-20 | 2010-01-01 | 2014-01-19
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BAMNSITEA | BAM Cultural District - North Site Condemnation | 2 | BID AWARD AND REGISTER CONTRCT | 2012-01-21 | 2012-01-20 | 2014-01-20 | 2014-01-19
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BAMNSITEA | BAM Cultural District - North Site Condemnation | 3 | CONSTRUCTION | 2012-01-21 | 2014-01-20 | 2014-01-20 | 2016-01-20
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BAMNSITEA | BAM Cultural District - North Site Condemnation | 4 | ORIGINAL EQUIP & FURNISHING | 2014-01-21 | 2014-01-20 | 2016-01-21 | 2016-01-20
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BAMNSITEA | BAM Cultural District - North Site Condemnation | 5 | SUBSTANTIAL COMPLETION | 2014-01-21 | 2014-01-20 | 2016-01-21 | 2016-01-20
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BAMNSITEA | BAM Cultural District - North Site Condemnation | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-01-21 | 2014-01-25 | 2016-01-21 | 2025-06-29
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BAMPARK | BAM Park Renovation | 1 | DESIGN | 2015-06-30 | 2015-07-19 | 2019-03-23 | 2019-04-11
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BAMPARK | BAM Park Renovation | 2 | BID AWARD AND REGISTER CONTRCT | 2015-07-20 | 2015-08-03 | 2019-04-12 | 2019-04-26
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BAMPARK | BAM Park Renovation | 3 | CONSTRUCTION | 2015-08-04 | 2015-09-07 | 2019-04-27 | 2019-05-31
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BAMPARK | BAM Park Renovation | 4 | ORIGINAL EQUIP & FURNISHING | 2015-09-08 | 2015-09-17 | 2019-06-01 | 2019-06-10
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BAMPARK | BAM Park Renovation | 5 | SUBSTANTIAL COMPLETION | 2015-09-18 | 2015-10-02 | 2019-06-11 | 2019-06-25
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BAMPARK | BAM Park Renovation | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-10-03 | 2015-10-07 | 2019-06-26 | 2023-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BAMSTRAND | BAM LDC - Strand Theatre Redevelopment | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2011-01-02 | 2011-01-06 | 2013-01-01 | 2019-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BAMSTRTS | BAM Cultural District Streetscapes | 1 | DESIGN | 2005-01-01 | 2005-01-20 | 2007-12-28 | 2024-06-25
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BAMSTRTS | BAM Cultural District Streetscapes | 2 | BID AWARD AND REGISTER CONTRCT | 2005-01-21 | 2005-02-04 | 2024-06-26 | 2024-06-25
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BAMSTRTS | BAM Cultural District Streetscapes | 3 | CONSTRUCTION | 2005-02-05 | 2008-06-30 | 2024-06-26 | 2024-06-25
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BAMSTRTS | BAM Cultural District Streetscapes | 4 | ORIGINAL EQUIP & FURNISHING | 2008-07-01 | 2008-06-30 | 2024-06-26 | 2024-06-25
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BAMSTRTS | BAM Cultural District Streetscapes | 5 | SUBSTANTIAL COMPLETION | 2008-07-01 | 2008-06-30 | 2024-06-26 | 2024-06-25
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BAMSTRTS | BAM Cultural District Streetscapes | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-07-01 | 2008-07-05 | 2024-06-26 | 2024-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BAMSTRTS | BAM Cultural District Streetscapes | 7 | DESIGN | 2008-07-06 | 2008-07-25 | 2024-06-26 | 2024-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BAMSTRTS | BAM Cultural District Streetscapes | 8 | BID AWARD AND REGISTER CONTRCT | 2008-07-26 | 2008-08-09 | 2024-06-26 | 2024-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BAMSTRTS | BAM Cultural District Streetscapes | 9 | CONSTRUCTION | 2008-08-10 | 2008-09-13 | 2024-06-26 | 2024-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BAMSTRTS | BAM Cultural District Streetscapes | 10 | ORIGINAL EQUIP & FURNISHING | 2008-09-14 | 2008-09-23 | 2024-06-26 | 2024-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BAMSTRTS | BAM Cultural District Streetscapes | 11 | SUBSTANTIAL COMPLETION | 2008-09-24 | 2008-10-08 | 2024-06-26 | 2024-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BAMSTRTS | BAM Cultural District Streetscapes | 12 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-10-09 | 2008-10-13 | 2024-06-26 | 2024-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BAT4LAN | BAT Pier 4: Ferry Landing Rehabilitation | 1 | DESIGN | 2006-08-01 | 2006-08-20 | 2006-08-01 | 2012-09-01
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BAT4LAN | BAT Pier 4: Ferry Landing Rehabilitation | 2 | BID AWARD AND REGISTER CONTRCT | 2006-08-21 | 2006-09-04 | 2012-09-02 | 2012-09-01
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BAT4LAN | BAT Pier 4: Ferry Landing Rehabilitation | 3 | CONSTRUCTION | 2006-09-05 | 2006-10-09 | 2007-05-01 | 2017-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BAT4LAN | BAT Pier 4: Ferry Landing Rehabilitation | 4 | ORIGINAL EQUIP & FURNISHING | 2006-10-10 | 2006-10-19 | 2017-07-01 | 2017-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BAT4LAN | BAT Pier 4: Ferry Landing Rehabilitation | 5 | SUBSTANTIAL COMPLETION | 2006-10-20 | 2006-11-03 | 2017-07-01 | 2017-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BAT4LAN | BAT Pier 4: Ferry Landing Rehabilitation | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2006-11-04 | 2006-11-08 | 2017-07-01 | 2027-07-10
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATANCHOR | BAT Anchor Tenant Strategy | 1 | DESIGN | 2018-07-01 | 2018-07-20 | 2020-03-23 | 2020-04-11
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATANCHOR | BAT Anchor Tenant Strategy | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-21 | 2018-08-04 | 2020-04-12 | 2020-04-26
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATANCHOR | BAT Anchor Tenant Strategy | 3 | CONSTRUCTION | 2018-08-05 | 2018-09-08 | 2020-04-27 | 2020-05-31
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATANCHOR | BAT Anchor Tenant Strategy | 4 | ORIGINAL EQUIP & FURNISHING | 2018-09-09 | 2018-09-18 | 2020-06-01 | 2020-06-10
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATANCHOR | BAT Anchor Tenant Strategy | 5 | SUBSTANTIAL COMPLETION | 2018-09-19 | 2018-10-03 | 2020-06-11 | 2020-06-25
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATANCHOR | BAT Anchor Tenant Strategy | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-10-04 | 2018-10-08 | 2020-06-26 | 2029-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATBEYOND | BAT New Needs | 1 | DESIGN | 2014-12-26 | 2015-01-14 | 2017-12-26 | 2018-01-14
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATBEYOND | BAT New Needs | 2 | BID AWARD AND REGISTER CONTRCT | 2015-01-15 | 2015-01-29 | 2018-01-15 | 2018-01-29
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATBEYOND | BAT New Needs | 3 | CONSTRUCTION | 2015-01-30 | 2015-03-05 | 2018-01-30 | 2018-03-05
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATBEYOND | BAT New Needs | 4 | ORIGINAL EQUIP & FURNISHING | 2015-03-06 | 2015-03-15 | 2018-03-06 | 2018-03-15
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATBEYOND | BAT New Needs | 5 | SUBSTANTIAL COMPLETION | 2015-03-16 | 2015-03-30 | 2018-03-16 | 2018-03-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATBEYOND | BAT New Needs | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-31 | 2015-04-04 | 2018-03-31 | 2024-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATIMPRO | BAT Improvements | 1 | DESIGN | 2007-07-01 | 2007-07-20 | 2009-06-30 | 2009-07-19
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATIMPRO | BAT Improvements | 2 | BID AWARD AND REGISTER CONTRCT | 2007-07-21 | 2007-08-04 | 2009-07-20 | 2009-08-03
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATIMPRO | BAT Improvements | 3 | CONSTRUCTION | 2007-08-05 | 2008-06-30 | 2009-08-04 | 2010-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATIMPRO | BAT Improvements | 4 | ORIGINAL EQUIP & FURNISHING | 2008-07-01 | 2008-06-30 | 2010-07-01 | 2010-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATIMPRO | BAT Improvements | 5 | SUBSTANTIAL COMPLETION | 2008-07-01 | 2008-06-30 | 2010-07-01 | 2010-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATIMPRO | BAT Improvements | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-07-01 | 2008-07-05 | 2010-07-01 | 2022-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATLOGIST | Brooklyn Army Terminal Logistics Center | 1 | DESIGN | 2018-07-01 | 2018-07-20 | 2018-03-23 | 2018-04-11
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATLOGIST | Brooklyn Army Terminal Logistics Center | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-21 | 2018-08-04 | 2018-04-12 | 2018-04-26
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATLOGIST | Brooklyn Army Terminal Logistics Center | 3 | CONSTRUCTION | 2018-08-05 | 2018-09-08 | 2018-04-27 | 2018-05-31
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATLOGIST | Brooklyn Army Terminal Logistics Center | 4 | ORIGINAL EQUIP & FURNISHING | 2018-09-09 | 2018-09-18 | 2018-06-01 | 2018-06-10
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATLOGIST | Brooklyn Army Terminal Logistics Center | 5 | SUBSTANTIAL COMPLETION | 2018-09-19 | 2018-10-03 | 2018-06-11 | 2018-06-25
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATLOGIST | Brooklyn Army Terminal Logistics Center | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-10-04 | 2018-10-08 | 2018-06-26 | 2026-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATPLUGIN | BAT Plug-In Industrial Strategy | 1 | DESIGN | 2018-07-01 | 2018-07-20 | 2020-03-23 | 2020-04-11
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATPLUGIN | BAT Plug-In Industrial Strategy | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-21 | 2018-08-04 | 2020-04-12 | 2020-04-26
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATPLUGIN | BAT Plug-In Industrial Strategy | 3 | CONSTRUCTION | 2018-08-05 | 2018-09-08 | 2020-04-27 | 2020-05-31
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATPLUGIN | BAT Plug-In Industrial Strategy | 4 | ORIGINAL EQUIP & FURNISHING | 2018-09-09 | 2018-09-18 | 2020-06-01 | 2020-06-10
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATPLUGIN | BAT Plug-In Industrial Strategy | 5 | SUBSTANTIAL COMPLETION | 2018-09-19 | 2018-10-03 | 2020-06-11 | 2020-06-25
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATPLUGIN | BAT Plug-In Industrial Strategy | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-10-04 | 2018-10-08 | 2020-06-26 | 2029-06-23
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BCTBERTH | Brooklyn Cruise Terminal - New Berth and Landside Redevelop | 1 | DESIGN | 2016-07-01 | 2016-07-20 | 2016-07-01 | 2016-07-20
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BCTBERTH | Brooklyn Cruise Terminal - New Berth and Landside Redevelop | 2 | BID AWARD AND REGISTER CONTRCT | 2016-07-21 | 2016-08-04 | 2016-07-21 | 2016-08-04
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BCTBERTH | Brooklyn Cruise Terminal - New Berth and Landside Redevelop | 3 | CONSTRUCTION | 2016-08-05 | 2016-09-08 | 2016-08-05 | 2016-09-08
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BCTBERTH | Brooklyn Cruise Terminal - New Berth and Landside Redevelop | 4 | ORIGINAL EQUIP & FURNISHING | 2016-09-09 | 2016-09-18 | 2016-09-09 | 2016-09-18
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BCTBERTH | Brooklyn Cruise Terminal - New Berth and Landside Redevelop | 5 | SUBSTANTIAL COMPLETION | 2016-09-19 | 2016-10-03 | 2016-09-19 | 2016-10-03
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BCTBERTH | Brooklyn Cruise Terminal - New Berth and Landside Redevelop | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-10-04 | 2016-10-08 | 2016-10-04 | 2024-10-08
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BCTPIER11 | Brooklyn Cruise Terminal Pier 11 | 1 | DESIGN | 2016-01-01 | 2018-06-30 | 2016-01-01 | 2018-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BCTPIER11 | Brooklyn Cruise Terminal Pier 11 | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-01 | 2018-06-30 | 2018-07-01 | 2018-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BCTPIER11 | Brooklyn Cruise Terminal Pier 11 | 3 | CONSTRUCTION | 2018-07-01 | 2021-06-30 | 2018-07-01 | 2021-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BCTPIER11 | Brooklyn Cruise Terminal Pier 11 | 4 | ORIGINAL EQUIP & FURNISHING | 2021-07-01 | 2021-06-30 | 2021-07-01 | 2021-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BCTPIER11 | Brooklyn Cruise Terminal Pier 11 | 5 | SUBSTANTIAL COMPLETION | 2021-07-01 | 2021-06-30 | 2021-07-01 | 2021-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BCTPIER11 | Brooklyn Cruise Terminal Pier 11 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-07-01 | 2021-07-05 | 2021-07-01 | 2024-07-05
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BKBRESP | Brooklyn Bridge Esplanade | 1 | DESIGN | 2019-07-01 | 2019-07-20 | 2019-07-01 | 2019-07-20
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BKBRESP | Brooklyn Bridge Esplanade | 2 | BID AWARD AND REGISTER CONTRCT | 2019-07-21 | 2019-08-04 | 2019-07-21 | 2019-08-04
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BKBRESP | Brooklyn Bridge Esplanade | 3 | CONSTRUCTION | 2019-08-05 | 2019-09-08 | 2019-08-05 | 2019-09-08
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BKBRESP | Brooklyn Bridge Esplanade | 4 | ORIGINAL EQUIP & FURNISHING | 2019-09-09 | 2019-09-18 | 2019-09-09 | 2019-09-18
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BKBRESP | Brooklyn Bridge Esplanade | 5 | SUBSTANTIAL COMPLETION | 2019-09-19 | 2021-10-03 | 2019-09-19 | 2021-10-03
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BKBRESP | Brooklyn Bridge Esplanade | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-10-04 | 2021-10-08 | 2021-10-04 | 2021-10-08
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BKCRUISE | Brooklyn Cruise Terminal Substructre Rehab | 1 | DESIGN | 2008-01-01 | 2009-01-01 | 2008-01-01 | 2023-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BKCRUISE | Brooklyn Cruise Terminal Substructre Rehab | 2 | BID AWARD AND REGISTER CONTRCT | 2009-01-02 | 2009-01-01 | 2023-07-01 | 2023-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BKCRUISE | Brooklyn Cruise Terminal Substructre Rehab | 3 | CONSTRUCTION | 2009-01-02 | 2011-01-01 | 2023-07-01 | 2023-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BKCRUISE | Brooklyn Cruise Terminal Substructre Rehab | 4 | ORIGINAL EQUIP & FURNISHING | 2011-01-02 | 2011-01-01 | 2023-07-01 | 2023-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BKCRUISE | Brooklyn Cruise Terminal Substructre Rehab | 5 | SUBSTANTIAL COMPLETION | 2011-01-02 | 2011-01-01 | 2023-07-01 | 2023-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BKCRUISE | Brooklyn Cruise Terminal Substructre Rehab | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2011-01-02 | 2011-01-06 | 2023-07-01 | 2028-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BKCRUISE | Brooklyn Cruise Terminal Substructre Rehab | 7 | DESIGN | 2011-01-07 | 2011-01-26 | 2023-07-01 | 2028-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BKCRUISE | Brooklyn Cruise Terminal Substructre Rehab | 8 | BID AWARD AND REGISTER CONTRCT | 2011-01-27 | 2011-02-10 | 2023-07-01 | 2028-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BKCRUISE | Brooklyn Cruise Terminal Substructre Rehab | 9 | CONSTRUCTION | 2011-02-11 | 2011-03-17 | 2023-07-01 | 2028-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BKCRUISE | Brooklyn Cruise Terminal Substructre Rehab | 10 | ORIGINAL EQUIP & FURNISHING | 2011-03-18 | 2011-03-27 | 2023-07-01 | 2028-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BKCRUISE | Brooklyn Cruise Terminal Substructre Rehab | 11 | SUBSTANTIAL COMPLETION | 2011-03-28 | 2011-04-11 | 2023-07-01 | 2028-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BKCRUISE | Brooklyn Cruise Terminal Substructre Rehab | 12 | PUNCHLIST COMPLETE, JOB CLOSED | 2011-04-12 | 2011-04-16 | 2023-07-01 | 2028-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BKCTPIER | Brooklyn Cruise Terminal Pier 12 Substructure Rehab | 1 | DESIGN | 2017-07-01 | 2017-07-20 | 2017-07-01 | 2017-07-20
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BKCTPIER | Brooklyn Cruise Terminal Pier 12 Substructure Rehab | 2 | BID AWARD AND REGISTER CONTRCT | 2017-07-21 | 2017-08-04 | 2017-07-21 | 2017-08-04
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BKCTPIER | Brooklyn Cruise Terminal Pier 12 Substructure Rehab | 3 | CONSTRUCTION | 2017-08-05 | 2017-09-08 | 2017-08-05 | 2017-09-08
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BKCTPIER | Brooklyn Cruise Terminal Pier 12 Substructure Rehab | 4 | ORIGINAL EQUIP & FURNISHING | 2017-09-09 | 2017-09-18 | 2017-09-09 | 2017-09-18
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BKCTPIER | Brooklyn Cruise Terminal Pier 12 Substructure Rehab | 5 | SUBSTANTIAL COMPLETION | 2017-09-19 | 2017-10-03 | 2017-09-19 | 2017-10-03
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BKCTPIER | Brooklyn Cruise Terminal Pier 12 Substructure Rehab | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-10-04 | 2017-10-08 | 2017-10-04 | 2023-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BKWMMIMP | Brooklyn Wholesale Meat Markets Building Improvement | 1 | DESIGN | 2016-07-01 | 2016-07-20 | 2018-07-01 | 2018-07-20
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BKWMMIMP | Brooklyn Wholesale Meat Markets Building Improvement | 2 | BID AWARD AND REGISTER CONTRCT | 2016-07-21 | 2016-08-04 | 2018-07-21 | 2018-08-04
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BKWMMIMP | Brooklyn Wholesale Meat Markets Building Improvement | 3 | CONSTRUCTION | 2016-08-05 | 2016-09-08 | 2018-08-05 | 2018-09-08
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BKWMMIMP | Brooklyn Wholesale Meat Markets Building Improvement | 4 | ORIGINAL EQUIP & FURNISHING | 2016-09-09 | 2016-09-18 | 2018-09-09 | 2018-09-18
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BKWMMIMP | Brooklyn Wholesale Meat Markets Building Improvement | 5 | SUBSTANTIAL COMPLETION | 2016-09-19 | 2016-10-03 | 2018-09-19 | 2018-10-03
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BKWMMIMP | Brooklyn Wholesale Meat Markets Building Improvement | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-10-04 | 2016-10-08 | 2018-10-04 | 2024-10-08
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNY5THST | BNYDC 5th Street Reconstruction | 1 | DESIGN | 2019-01-22 | 2019-02-20 | 2019-01-01 | 2020-02-20
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNY5THST | BNYDC 5th Street Reconstruction | 2 | CONSTRUCTION | 2019-02-21 | 2019-04-26 | 2019-01-01 | 2020-02-20
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNY5THST | BNYDC 5th Street Reconstruction | 3 | CONSTRUCTION | 2019-04-27 | 2019-06-25 | 2020-02-21 | 2020-04-25
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNY5THST | BNYDC 5th Street Reconstruction | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-06-26 | 2019-06-26 | 2020-02-21 | 2020-04-25
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNY5THST | BNYDC 5th Street Reconstruction | 5 | SUBSTANTIAL COMPLETION | 2019-06-26 | 2019-06-26 | 2020-04-26 | 2020-06-24
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNY5THST | BNYDC 5th Street Reconstruction | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-06-26 | 2019-06-26 | 2020-06-25 | 2022-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNY910SBB | BNYDC Berths 9, 10 and Small Boat Basin Structural Work | 1 | DESIGN | 2019-06-01 | 2020-10-12 | 2019-06-01 | 2020-10-12
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNY910SBB | BNYDC Berths 9, 10 and Small Boat Basin Structural Work | 2 | CONSTRUCTION | 2020-05-16 | 2023-02-09 | 2019-06-01 | 2020-10-12
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNY910SBB | BNYDC Berths 9, 10 and Small Boat Basin Structural Work | 3 | SUBSTANTIAL COMPLETION | 2022-11-17 | 2024-03-30 | 2020-05-16 | 2023-02-09
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNY910SBB | BNYDC Berths 9, 10 and Small Boat Basin Structural Work | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-03-31 | 2024-03-31 | 2020-05-16 | 2023-02-09
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNY910SBB | BNYDC Berths 9, 10 and Small Boat Basin Structural Work | 5 | SUBSTANTIAL COMPLETION | 2024-03-31 | 2024-03-31 | 2022-11-17 | 2024-03-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNY910SBB | BNYDC Berths 9, 10 and Small Boat Basin Structural Work | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-03-31 | 2024-03-31 | 2024-03-31 | 2024-03-31
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYB131RM | BNYDC Building 131 Asbestos and Mold Remediation - 1st Floor | 1 | DESIGN | 2019-12-01 | 2020-01-29 | 2019-12-01 | 2020-01-29
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYB131RM | BNYDC Building 131 Asbestos and Mold Remediation - 1st Floor | 2 | CONSTRUCTION | 2020-01-30 | 2020-05-28 | 2019-12-01 | 2020-01-29
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYB131RM | BNYDC Building 131 Asbestos and Mold Remediation - 1st Floor | 3 | SUBSTANTIAL COMPLETION | 2020-05-29 | 2020-07-27 | 2020-01-30 | 2020-05-28
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYB131RM | BNYDC Building 131 Asbestos and Mold Remediation - 1st Floor | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-07-28 | 2020-07-28 | 2020-01-30 | 2020-05-28
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYB131RM | BNYDC Building 131 Asbestos and Mold Remediation - 1st Floor | 5 | SUBSTANTIAL COMPLETION | 2020-07-28 | 2020-07-28 | 2020-05-29 | 2020-07-27
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYB131RM | BNYDC Building 131 Asbestos and Mold Remediation - 1st Floor | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-07-28 | 2020-07-28 | 2020-07-28 | 2020-07-28
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYB280RF | BNYDC Building 280 Roof | 1 | DESIGN | 2020-01-12 | 2020-03-11 | 2020-01-12 | 2020-03-11
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYB280RF | BNYDC Building 280 Roof | 2 | CONSTRUCTION | 2020-03-12 | 2020-07-09 | 2020-01-12 | 2020-03-11
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYB280RF | BNYDC Building 280 Roof | 3 | SUBSTANTIAL COMPLETION | 2020-07-10 | 2020-09-07 | 2020-03-12 | 2020-07-09
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYB280RF | BNYDC Building 280 Roof | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-08 | 2020-09-08 | 2020-03-12 | 2020-07-09
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYB280RF | BNYDC Building 280 Roof | 5 | SUBSTANTIAL COMPLETION | 2020-09-08 | 2020-09-08 | 2020-07-10 | 2020-09-07
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYB280RF | BNYDC Building 280 Roof | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-08 | 2020-09-08 | 2020-09-08 | 2020-09-08
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYB3SUBD | BNYDC Building 3 Subdivision | 1 | DESIGN | 2020-01-15 | 2020-03-14 | 2020-01-15 | 2020-03-14
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYB3SUBD | BNYDC Building 3 Subdivision | 2 | CONSTRUCTION | 2020-03-15 | 2020-07-12 | 2020-01-15 | 2020-03-14
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYB3SUBD | BNYDC Building 3 Subdivision | 3 | SUBSTANTIAL COMPLETION | 2020-07-13 | 2020-09-10 | 2020-03-15 | 2020-07-12
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYB3SUBD | BNYDC Building 3 Subdivision | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-11 | 2020-09-11 | 2020-03-15 | 2020-07-12
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYB3SUBD | BNYDC Building 3 Subdivision | 5 | SUBSTANTIAL COMPLETION | 2020-09-11 | 2020-09-11 | 2020-07-13 | 2020-09-10
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYB3SUBD | BNYDC Building 3 Subdivision | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-11 | 2020-09-11 | 2020-09-11 | 2020-09-11
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYB74DEM | BNYDC Demolition of Building 74 and Parking Lot | 1 | DESIGN | 2020-06-01 | 2020-07-30 | 2020-06-01 | 2020-07-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYB74DEM | BNYDC Demolition of Building 74 and Parking Lot | 2 | CONSTRUCTION | 2020-07-31 | 2021-06-30 | 2020-06-01 | 2020-07-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYB74DEM | BNYDC Demolition of Building 74 and Parking Lot | 3 | SUBSTANTIAL COMPLETION | 2021-07-01 | 2021-08-29 | 2020-07-31 | 2021-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYB74DEM | BNYDC Demolition of Building 74 and Parking Lot | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-08-30 | 2021-08-30 | 2020-07-31 | 2021-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYB74DEM | BNYDC Demolition of Building 74 and Parking Lot | 5 | SUBSTANTIAL COMPLETION | 2021-08-30 | 2021-08-30 | 2021-07-01 | 2021-08-29
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYB74DEM | BNYDC Demolition of Building 74 and Parking Lot | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-08-30 | 2021-08-30 | 2021-08-30 | 2021-08-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYBD132 | BNYDC Building 132 Roof Rehabilitation | 1 | DESIGN | 2018-12-27 | 2019-08-23 | 2018-12-27 | 2019-08-23
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYBD132 | BNYDC Building 132 Roof Rehabilitation | 2 | CONSTRUCTION | 2019-08-24 | 2020-12-15 | 2018-12-27 | 2019-08-23
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYBD132 | BNYDC Building 132 Roof Rehabilitation | 3 | SUBSTANTIAL COMPLETION | 2020-12-16 | 2021-07-03 | 2019-08-24 | 2020-12-15
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYBD132 | BNYDC Building 132 Roof Rehabilitation | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-07-04 | 2021-07-04 | 2019-08-24 | 2020-12-15
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYBD132 | BNYDC Building 132 Roof Rehabilitation | 5 | SUBSTANTIAL COMPLETION | 2021-07-04 | 2021-07-04 | 2020-12-16 | 2021-07-03
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYBD132 | BNYDC Building 132 Roof Rehabilitation | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-07-04 | 2021-07-04 | 2021-07-04 | 2021-07-04
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYBDELEV | BNYDC Elevator Reconstruction and Replacement | 1 | DESIGN | 2016-07-01 | 2016-07-20 | 2019-06-19 | 2020-01-04
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYBDELEV | BNYDC Elevator Reconstruction and Replacement | 2 | BID AWARD AND REGISTER CONTRCT | 2016-07-21 | 2016-08-04 | 2020-01-05 | 2020-04-13
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYBDELEV | BNYDC Elevator Reconstruction and Replacement | 3 | CONSTRUCTION | 2016-08-05 | 2016-09-08 | 2020-04-14 | 2022-03-14
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYBDELEV | BNYDC Elevator Reconstruction and Replacement | 4 | ORIGINAL EQUIP & FURNISHING | 2016-09-09 | 2016-09-18 | 2022-03-15 | 2022-06-12
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYBDELEV | BNYDC Elevator Reconstruction and Replacement | 5 | SUBSTANTIAL COMPLETION | 2016-09-19 | 2016-10-03 | 2022-06-13 | 2022-06-27
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYBDELEV | BNYDC Elevator Reconstruction and Replacement | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-10-04 | 2016-10-08 | 2022-06-28 | 2022-07-02
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYBLD292 | BNYDC Building 292 Roof Replacement | 1 | DESIGN | 2018-07-01 | 2018-07-20 | 2018-07-01 | 2018-07-20
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYBLD292 | BNYDC Building 292 Roof Replacement | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-21 | 2018-08-04 | 2018-07-21 | 2018-08-04
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYBLD292 | BNYDC Building 292 Roof Replacement | 3 | CONSTRUCTION | 2018-08-05 | 2018-09-08 | 2018-08-05 | 2019-09-08
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYBLD292 | BNYDC Building 292 Roof Replacement | 4 | ORIGINAL EQUIP & FURNISHING | 2018-09-09 | 2018-09-18 | 2019-09-09 | 2019-09-18
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYBLD292 | BNYDC Building 292 Roof Replacement | 5 | SUBSTANTIAL COMPLETION | 2018-09-19 | 2018-10-03 | 2019-09-19 | 2019-10-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYBLD292 | BNYDC Building 292 Roof Replacement | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-10-04 | 2018-10-08 | 2019-10-31 | 2021-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYBLDG50 | BNYDC Building 50 Roof Rehabilitation | 1 | DESIGN | 2018-12-27 | 2019-08-23 | 2018-12-27 | 2019-08-23
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYBLDG50 | BNYDC Building 50 Roof Rehabilitation | 2 | CONSTRUCTION | 2019-08-24 | 2020-12-15 | 2018-12-27 | 2019-08-23
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYBLDG50 | BNYDC Building 50 Roof Rehabilitation | 3 | SUBSTANTIAL COMPLETION | 2020-12-16 | 2021-07-03 | 2019-08-24 | 2020-12-15
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYBLDG50 | BNYDC Building 50 Roof Rehabilitation | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-07-04 | 2021-07-04 | 2019-08-24 | 2020-12-15
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYBLDG50 | BNYDC Building 50 Roof Rehabilitation | 5 | SUBSTANTIAL COMPLETION | 2021-07-04 | 2021-07-04 | 2020-12-16 | 2021-07-03
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYBLDG50 | BNYDC Building 50 Roof Rehabilitation | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-07-04 | 2021-07-04 | 2021-07-04 | 2021-07-04
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYDCSUBF | BNYDC Con Edison Substation F Upgrade | 1 | DESIGN | 2018-07-01 | 2018-07-20 | 2018-03-23 | 2019-01-16
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYDCSUBF | BNYDC Con Edison Substation F Upgrade | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-21 | 2018-08-04 | 2019-01-17 | 2019-04-26
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYDCSUBF | BNYDC Con Edison Substation F Upgrade | 3 | CONSTRUCTION | 2018-08-05 | 2018-09-08 | 2019-04-27 | 2021-07-04
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYDCSUBF | BNYDC Con Edison Substation F Upgrade | 4 | ORIGINAL EQUIP & FURNISHING | 2018-09-09 | 2018-09-18 | 2021-07-05 | 2022-01-20
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYDCSUBF | BNYDC Con Edison Substation F Upgrade | 5 | SUBSTANTIAL COMPLETION | 2018-09-19 | 2018-10-03 | 2022-01-21 | 2022-04-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYDCSUBF | BNYDC Con Edison Substation F Upgrade | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-10-04 | 2018-10-08 | 2022-05-01 | 2022-05-05
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYDCWELD | BNYDC Welding Lab | 1 | DESIGN | 2019-10-01 | 2019-11-29 | 2019-10-01 | 2019-11-29
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYDCWELD | BNYDC Welding Lab | 2 | CONSTRUCTION | 2019-11-30 | 2020-03-28 | 2019-10-01 | 2019-11-29
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYDCWELD | BNYDC Welding Lab | 3 | CONSTRUCTION | 2020-03-29 | 2020-05-27 | 2019-11-30 | 2020-03-28
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYDCWELD | BNYDC Welding Lab | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-05-28 | 2020-05-28 | 2019-11-30 | 2020-03-28
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYDCWELD | BNYDC Welding Lab | 5 | SUBSTANTIAL COMPLETION | 2020-05-28 | 2020-05-28 | 2020-03-29 | 2020-05-27
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYDCWELD | BNYDC Welding Lab | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-05-28 | 2020-05-28 | 2020-05-28 | 2021-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYELEV22 | BNYDC Building 22 Elevator Modernization | 1 | DESIGN | 2018-07-01 | 2018-07-20 | 2018-07-01 | 2018-07-20
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYELEV22 | BNYDC Building 22 Elevator Modernization | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-21 | 2018-08-04 | 2018-07-21 | 2018-08-04
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYELEV22 | BNYDC Building 22 Elevator Modernization | 3 | CONSTRUCTION | 2018-08-05 | 2018-09-08 | 2018-08-05 | 2018-09-08
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYELEV22 | BNYDC Building 22 Elevator Modernization | 4 | ORIGINAL EQUIP & FURNISHING | 2018-09-09 | 2018-09-18 | 2018-09-09 | 2019-10-18
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYELEV22 | BNYDC Building 22 Elevator Modernization | 5 | SUBSTANTIAL COMPLETION | 2018-09-19 | 2018-10-03 | 2019-10-19 | 2019-11-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYELEV22 | BNYDC Building 22 Elevator Modernization | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-10-04 | 2018-10-08 | 2019-12-01 | 2021-12-31
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYFNCLIN | BNYDC Fence Line Restructuring | 1 | DESIGN | 2018-07-01 | 2018-07-20 | 2018-07-01 | 2018-07-20
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYFNCLIN | BNYDC Fence Line Restructuring | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-21 | 2018-08-04 | 2018-07-21 | 2018-08-04
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYFNCLIN | BNYDC Fence Line Restructuring | 3 | CONSTRUCTION | 2018-08-05 | 2018-09-08 | 2018-08-05 | 2020-03-26
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYFNCLIN | BNYDC Fence Line Restructuring | 4 | ORIGINAL EQUIP & FURNISHING | 2018-09-09 | 2018-09-18 | 2020-03-27 | 2020-04-05
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYFNCLIN | BNYDC Fence Line Restructuring | 5 | SUBSTANTIAL COMPLETION | 2018-09-19 | 2018-10-03 | 2020-04-06 | 2020-04-20
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYFNCLIN | BNYDC Fence Line Restructuring | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-10-04 | 2018-10-08 | 2020-04-21 | 2024-04-25
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYHARBOR | BNYDC PS 331 NY Harbor School Trailer Installation | 1 | DESIGN | 2016-07-01 | 2016-07-20 | 2021-07-23 | 2021-08-11
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYHARBOR | BNYDC PS 331 NY Harbor School Trailer Installation | 2 | BID AWARD AND REGISTER CONTRCT | 2016-07-21 | 2016-08-04 | 2021-08-12 | 2021-08-26
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYHARBOR | BNYDC PS 331 NY Harbor School Trailer Installation | 3 | CONSTRUCTION | 2016-08-05 | 2016-09-08 | 2021-08-27 | 2021-09-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYHARBOR | BNYDC PS 331 NY Harbor School Trailer Installation | 4 | ORIGINAL EQUIP & FURNISHING | 2016-09-09 | 2016-09-18 | 2021-10-01 | 2021-10-10
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYHARBOR | BNYDC PS 331 NY Harbor School Trailer Installation | 5 | SUBSTANTIAL COMPLETION | 2016-09-19 | 2016-10-03 | 2021-10-11 | 2021-10-25
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYHARBOR | BNYDC PS 331 NY Harbor School Trailer Installation | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-10-04 | 2016-10-08 | 2021-10-26 | 2021-10-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYHITN | BNYDC HITN Eco-Rooftop Production Studio | 1 | DESIGN | 2018-07-01 | 2018-07-20 | 2018-07-01 | 2020-01-29
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYHITN | BNYDC HITN Eco-Rooftop Production Studio | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-21 | 2018-08-04 | 2020-01-30 | 2020-02-28
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYHITN | BNYDC HITN Eco-Rooftop Production Studio | 3 | CONSTRUCTION | 2018-08-05 | 2018-09-08 | 2020-02-29 | 2020-05-28
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYHITN | BNYDC HITN Eco-Rooftop Production Studio | 4 | ORIGINAL EQUIP & FURNISHING | 2018-09-09 | 2018-09-18 | 2020-05-29 | 2020-06-07
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYHITN | BNYDC HITN Eco-Rooftop Production Studio | 5 | SUBSTANTIAL COMPLETION | 2018-09-19 | 2018-10-03 | 2020-06-08 | 2020-06-15
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYHITN | BNYDC HITN Eco-Rooftop Production Studio | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-10-04 | 2018-10-08 | 2020-06-16 | 2021-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYINF-BD | BNYDC Infrastructure Building Rehab | 1 | DESIGN | 2010-07-01 | 2010-07-20 | 2010-07-01 | 2011-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYINF-BD | BNYDC Infrastructure Building Rehab | 2 | BID AWARD AND REGISTER CONTRCT | 2010-07-21 | 2010-08-04 | 2011-07-01 | 2012-01-01
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYINF-BD | BNYDC Infrastructure Building Rehab | 3 | CONSTRUCTION | 2010-08-05 | 2010-09-08 | 2010-07-01 | 2012-01-01
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYINF-BD | BNYDC Infrastructure Building Rehab | 4 | ORIGINAL EQUIP & FURNISHING | 2010-09-09 | 2010-09-18 | 2012-01-02 | 2012-01-01
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYINF-BD | BNYDC Infrastructure Building Rehab | 5 | SUBSTANTIAL COMPLETION | 2010-09-19 | 2010-10-03 | 2010-12-29 | 2012-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYINF-BD | BNYDC Infrastructure Building Rehab | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2010-10-04 | 2010-10-08 | 2012-07-01 | 2029-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYINFRAW | BNYDC Infrastructure - Water Projects | 1 | DESIGN | 2005-01-01 | 2005-01-20 | 2012-12-27 | 2013-01-15
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYINFRAW | BNYDC Infrastructure - Water Projects | 2 | BID AWARD AND REGISTER CONTRCT | 2005-01-21 | 2005-02-04 | 2013-01-16 | 2013-01-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYINFRAW | BNYDC Infrastructure - Water Projects | 3 | CONSTRUCTION | 2005-02-05 | 2008-06-30 | 2013-01-31 | 2022-06-25
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYINFRAW | BNYDC Infrastructure - Water Projects | 4 | ORIGINAL EQUIP & FURNISHING | 2008-07-01 | 2008-06-30 | 2022-06-26 | 2022-06-25
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYINFRAW | BNYDC Infrastructure - Water Projects | 5 | SUBSTANTIAL COMPLETION | 2008-07-01 | 2008-06-30 | 2022-06-26 | 2022-06-25
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYINFRAW | BNYDC Infrastructure - Water Projects | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-07-01 | 2008-07-05 | 2022-06-26 | 2022-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYINF-ST | BNYDC Infrastructure Steam | 1 | DESIGN | 2016-07-01 | 2016-07-20 | 2016-07-01 | 2016-07-20
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYINF-ST | BNYDC Infrastructure Steam | 2 | BID AWARD AND REGISTER CONTRCT | 2016-07-21 | 2016-08-04 | 2016-07-21 | 2016-08-04
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYINF-ST | BNYDC Infrastructure Steam | 3 | CONSTRUCTION | 2016-08-05 | 2016-09-08 | 2016-08-05 | 2016-09-08
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYINF-ST | BNYDC Infrastructure Steam | 4 | ORIGINAL EQUIP & FURNISHING | 2016-09-09 | 2016-09-18 | 2016-09-09 | 2016-09-18
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYINF-ST | BNYDC Infrastructure Steam | 5 | SUBSTANTIAL COMPLETION | 2016-09-19 | 2016-10-03 | 2016-09-19 | 2016-10-03
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYINF-ST | BNYDC Infrastructure Steam | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-10-04 | 2016-10-08 | 2016-10-04 | 2024-10-08
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYINF-WF | BNYDC Infrastructure Waterfront | 1 | DESIGN | 2010-08-01 | 2010-08-20 | 2010-08-01 | 2010-08-20
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYINF-WF | BNYDC Infrastructure Waterfront | 2 | BID AWARD AND REGISTER CONTRCT | 2010-08-21 | 2010-09-04 | 2010-08-21 | 2010-09-04
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYINF-WF | BNYDC Infrastructure Waterfront | 3 | CONSTRUCTION | 2010-09-05 | 2010-10-09 | 2010-09-05 | 2029-06-29
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYINF-WF | BNYDC Infrastructure Waterfront | 4 | ORIGINAL EQUIP & FURNISHING | 2010-10-10 | 2010-10-19 | 2029-06-30 | 2029-06-29
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYINF-WF | BNYDC Infrastructure Waterfront | 5 | SUBSTANTIAL COMPLETION | 2010-10-20 | 2010-11-03 | 2029-06-30 | 2029-06-29
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYINF-WF | BNYDC Infrastructure Waterfront | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2010-11-04 | 2010-11-08 | 2029-06-30 | 2029-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYLIGHT | BNYDC Lighting Replacement | 1 | DESIGN | 2020-06-01 | 2020-12-31 | 2020-06-01 | 2020-12-31
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYLIGHT | BNYDC Lighting Replacement | 2 | CONSTRUCTION | 2021-01-01 | 2022-03-01 | 2020-06-01 | 2020-12-31
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYLIGHT | BNYDC Lighting Replacement | 3 | SUBSTANTIAL COMPLETION | 2022-03-02 | 2022-05-30 | 2021-01-01 | 2022-03-01
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYLIGHT | BNYDC Lighting Replacement | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-05-31 | 2022-06-30 | 2021-01-01 | 2022-03-01
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYLIGHT | BNYDC Lighting Replacement | 5 | SUBSTANTIAL COMPLETION | 2022-05-31 | 2022-06-30 | 2022-03-02 | 2022-05-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYLIGHT | BNYDC Lighting Replacement | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-05-31 | 2022-06-30 | 2022-05-31 | 2022-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYLL11 | BNYDC Local Law 11 Compliance - Buildings 3 and 5 | 1 | DESIGN | 2019-02-19 | 2019-04-19 | 2019-11-01 | 2020-03-01
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYLL11 | BNYDC Local Law 11 Compliance - Buildings 3 and 5 | 2 | CONSTRUCTION | 2019-04-20 | 2019-08-17 | 2019-11-01 | 2020-03-01
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYLL11 | BNYDC Local Law 11 Compliance - Buildings 3 and 5 | 3 | SUBSTANTIAL COMPLETION | 2019-08-18 | 2019-10-16 | 2020-03-02 | 2021-06-29
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYLL11 | BNYDC Local Law 11 Compliance - Buildings 3 and 5 | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-10-17 | 2019-10-17 | 2020-03-02 | 2021-06-29
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYLL11 | BNYDC Local Law 11 Compliance - Buildings 3 and 5 | 5 | SUBSTANTIAL COMPLETION | 2019-10-17 | 2019-10-17 | 2021-06-30 | 2021-08-28
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYLL11 | BNYDC Local Law 11 Compliance - Buildings 3 and 5 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-10-17 | 2019-10-17 | 2021-08-29 | 2021-08-29
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYMACRO | BNYDC Macro Sea | 1 | DESIGN | 2016-07-01 | 2016-07-20 | 2016-07-01 | 2019-04-11
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYMACRO | BNYDC Macro Sea | 2 | BID AWARD AND REGISTER CONTRCT | 2016-07-21 | 2016-08-04 | 2019-04-12 | 2019-04-26
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYMACRO | BNYDC Macro Sea | 3 | CONSTRUCTION | 2016-08-05 | 2016-09-08 | 2019-04-27 | 2019-05-31
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYMACRO | BNYDC Macro Sea | 4 | ORIGINAL EQUIP & FURNISHING | 2016-09-09 | 2016-09-18 | 2019-06-01 | 2019-06-10
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYMACRO | BNYDC Macro Sea | 5 | SUBSTANTIAL COMPLETION | 2016-09-19 | 2016-10-03 | 2019-06-11 | 2019-06-25
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYMACRO | BNYDC Macro Sea | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-10-04 | 2016-10-08 | 2019-06-26 | 2028-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYMWBEEI | BNYDC MWBE Equity Incubator | 1 | DESIGN | 2020-07-01 | 2020-07-20 | 2020-07-01 | 2020-07-20
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYMWBEEI | BNYDC MWBE Equity Incubator | 2 | BID AWARD AND REGISTER CONTRCT | 2020-07-21 | 2020-08-04 | 2020-07-21 | 2020-08-04
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYMWBEEI | BNYDC MWBE Equity Incubator | 3 | CONSTRUCTION | 2020-08-05 | 2020-09-08 | 2020-08-05 | 2020-09-08
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYMWBEEI | BNYDC MWBE Equity Incubator | 4 | ORIGINAL EQUIP & FURNISHING | 2020-09-09 | 2020-09-18 | 2020-09-09 | 2020-09-18
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYMWBEEI | BNYDC MWBE Equity Incubator | 5 | SUBSTANTIAL COMPLETION | 2020-09-19 | 2020-10-03 | 2020-09-19 | 2020-10-03
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYMWBEEI | BNYDC MWBE Equity Incubator | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-10-04 | 2021-06-30 | 2020-10-04 | 2021-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYROOF77 | BNYDC - Building 77 Roof | 1 | DESIGN | 2019-07-01 | 2019-08-29 | 2022-07-01 | 2022-08-29
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYROOF77 | BNYDC - Building 77 Roof | 2 | CONSTRUCTION | 2019-08-30 | 2019-12-27 | 2022-07-01 | 2022-08-29
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYROOF77 | BNYDC - Building 77 Roof | 3 | SUBSTANTIAL COMPLETION | 2019-12-28 | 2020-02-25 | 2022-08-30 | 2022-12-27
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYROOF77 | BNYDC - Building 77 Roof | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-02-26 | 2020-02-26 | 2022-08-30 | 2022-12-27
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYROOF77 | BNYDC - Building 77 Roof | 5 | SUBSTANTIAL COMPLETION | 2020-02-26 | 2020-02-26 | 2022-12-28 | 2023-02-25
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYROOF77 | BNYDC - Building 77 Roof | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-02-26 | 2020-02-26 | 2023-02-26 | 2023-02-26
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYRPZBFL | BNYDC Installation of RPZ Backflow Devices | 1 | DESIGN | 2016-07-01 | 2016-07-20 | 2016-07-01 | 2018-04-12
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYRPZBFL | BNYDC Installation of RPZ Backflow Devices | 2 | BID AWARD AND REGISTER CONTRCT | 2016-07-21 | 2016-08-04 | 2018-04-13 | 2018-04-27
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYRPZBFL | BNYDC Installation of RPZ Backflow Devices | 3 | CONSTRUCTION | 2016-08-05 | 2016-09-08 | 2018-04-28 | 2018-06-01
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYRPZBFL | BNYDC Installation of RPZ Backflow Devices | 4 | ORIGINAL EQUIP & FURNISHING | 2016-09-09 | 2016-09-18 | 2018-06-02 | 2018-06-11
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYRPZBFL | BNYDC Installation of RPZ Backflow Devices | 5 | SUBSTANTIAL COMPLETION | 2016-09-19 | 2016-10-03 | 2018-06-12 | 2018-06-26
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYRPZBFL | BNYDC Installation of RPZ Backflow Devices | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-10-04 | 2016-10-08 | 2018-06-27 | 2021-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYSPKFIR | BNYDC Sprinkler and Fire Alarm System Upgrades | 1 | DESIGN | 2018-07-01 | 2018-07-20 | 2018-07-01 | 2019-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYSPKFIR | BNYDC Sprinkler and Fire Alarm System Upgrades | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-21 | 2018-08-04 | 2019-07-01 | 2019-09-28
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYSPKFIR | BNYDC Sprinkler and Fire Alarm System Upgrades | 3 | CONSTRUCTION | 2018-08-05 | 2018-09-08 | 2019-09-29 | 2023-04-25
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYSPKFIR | BNYDC Sprinkler and Fire Alarm System Upgrades | 4 | ORIGINAL EQUIP & FURNISHING | 2018-09-09 | 2018-09-18 | 2023-04-26 | 2023-05-05
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYSPKFIR | BNYDC Sprinkler and Fire Alarm System Upgrades | 5 | SUBSTANTIAL COMPLETION | 2018-09-19 | 2018-10-03 | 2023-05-06 | 2023-05-20
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYSPKFIR | BNYDC Sprinkler and Fire Alarm System Upgrades | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-10-04 | 2018-10-08 | 2023-05-21 | 2023-05-25
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYTIFUND | BNYDC Tenant Improvement Fund | 1 | DESIGN | 2018-07-01 | 2018-07-20 | 2018-07-01 | 2019-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYTIFUND | BNYDC Tenant Improvement Fund | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-21 | 2018-08-04 | 2019-07-01 | 2020-06-29
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYTIFUND | BNYDC Tenant Improvement Fund | 3 | CONSTRUCTION | 2018-08-05 | 2018-09-08 | 2020-06-30 | 2025-04-24
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYTIFUND | BNYDC Tenant Improvement Fund | 4 | ORIGINAL EQUIP & FURNISHING | 2018-09-09 | 2018-09-18 | 2025-04-25 | 2025-05-04
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYTIFUND | BNYDC Tenant Improvement Fund | 5 | SUBSTANTIAL COMPLETION | 2018-09-19 | 2018-10-03 | 2025-05-05 | 2025-05-19
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYTIFUND | BNYDC Tenant Improvement Fund | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-10-04 | 2018-10-08 | 2025-05-20 | 2025-05-24
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYUBFARM | BNYDC Urban Farm Incubator | 1 | DESIGN | 2018-07-01 | 2018-07-20 | 2020-07-01 | 2020-10-31
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYUBFARM | BNYDC Urban Farm Incubator | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-21 | 2018-08-04 | 2020-11-01 | 2021-01-31
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYUBFARM | BNYDC Urban Farm Incubator | 3 | CONSTRUCTION | 2018-08-05 | 2018-09-08 | 2021-02-01 | 2022-02-01
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYUBFARM | BNYDC Urban Farm Incubator | 4 | ORIGINAL EQUIP & FURNISHING | 2018-09-09 | 2018-09-18 | 2022-02-02 | 2022-02-11
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYUBFARM | BNYDC Urban Farm Incubator | 5 | SUBSTANTIAL COMPLETION | 2018-09-19 | 2018-10-03 | 2022-02-12 | 2022-02-26
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYUBFARM | BNYDC Urban Farm Incubator | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-10-04 | 2018-10-08 | 2022-02-27 | 2022-03-03
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYUPSTM | BNYDC Above Ground Steam Main | 1 | DESIGN | 2018-07-01 | 2018-07-20 | 2019-03-08 | 2019-07-05
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYUPSTM | BNYDC Above Ground Steam Main | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-21 | 2018-08-04 | 2019-07-06 | 2019-10-03
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYUPSTM | BNYDC Above Ground Steam Main | 3 | CONSTRUCTION | 2018-08-05 | 2018-09-08 | 2019-10-04 | 2022-05-05
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYUPSTM | BNYDC Above Ground Steam Main | 4 | ORIGINAL EQUIP & FURNISHING | 2018-09-09 | 2018-09-18 | 2022-05-06 | 2022-05-15
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYUPSTM | BNYDC Above Ground Steam Main | 5 | SUBSTANTIAL COMPLETION | 2018-09-19 | 2018-10-03 | 2022-05-16 | 2022-05-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYUPSTM | BNYDC Above Ground Steam Main | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-10-04 | 2018-10-08 | 2022-05-31 | 2022-06-04
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BUSHDEVSP | Bush Terminal Development Site Preparation | 1 | DESIGN | 2016-01-01 | 2018-06-30 | 2016-01-01 | 2018-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BUSHDEVSP | Bush Terminal Development Site Preparation | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-01 | 2018-06-30 | 2018-07-01 | 2018-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BUSHDEVSP | Bush Terminal Development Site Preparation | 3 | CONSTRUCTION | 2018-07-01 | 2021-06-30 | 2018-07-01 | 2021-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BUSHDEVSP | Bush Terminal Development Site Preparation | 4 | ORIGINAL EQUIP & FURNISHING | 2021-07-01 | 2021-06-30 | 2021-07-01 | 2021-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BUSHDEVSP | Bush Terminal Development Site Preparation | 5 | SUBSTANTIAL COMPLETION | 2021-07-01 | 2021-06-30 | 2021-07-01 | 2021-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BUSHDEVSP | Bush Terminal Development Site Preparation | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-07-01 | 2021-07-05 | 2021-07-01 | 2021-07-05
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BUSHTCAFE | Bush Terminal Cafe Building Improvements | 1 | DESIGN | 2017-07-01 | 2017-07-20 | 2017-07-01 | 2019-04-11
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BUSHTCAFE | Bush Terminal Cafe Building Improvements | 2 | BID AWARD AND REGISTER CONTRCT | 2017-07-21 | 2017-08-04 | 2019-04-12 | 2019-04-26
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BUSHTCAFE | Bush Terminal Cafe Building Improvements | 3 | CONSTRUCTION | 2017-08-05 | 2017-09-08 | 2019-04-27 | 2019-05-31
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BUSHTCAFE | Bush Terminal Cafe Building Improvements | 4 | ORIGINAL EQUIP & FURNISHING | 2017-09-09 | 2017-09-18 | 2019-06-01 | 2019-06-10
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BUSHTCAFE | Bush Terminal Cafe Building Improvements | 5 | SUBSTANTIAL COMPLETION | 2017-09-19 | 2017-10-03 | 2019-06-11 | 2019-06-25
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BUSHTCAFE | Bush Terminal Cafe Building Improvements | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-10-04 | 2017-10-08 | 2019-06-26 | 2026-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BUSHTPARK | Bush Terminal Park | 1 | DESIGN | 2016-01-01 | 2018-06-30 | 2016-01-01 | 2018-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BUSHTPARK | Bush Terminal Park | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-01 | 2018-06-30 | 2018-07-01 | 2018-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BUSHTPARK | Bush Terminal Park | 3 | CONSTRUCTION | 2018-07-01 | 2021-06-30 | 2018-07-01 | 2021-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BUSHTPARK | Bush Terminal Park | 4 | ORIGINAL EQUIP & FURNISHING | 2021-07-01 | 2021-06-30 | 2021-07-01 | 2021-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BUSHTPARK | Bush Terminal Park | 5 | SUBSTANTIAL COMPLETION | 2021-07-01 | 2021-06-30 | 2021-07-01 | 2021-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BUSHTPARK | Bush Terminal Park | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-07-01 | 2021-07-05 | 2021-07-01 | 2021-07-05
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BUSHUNTAC | Bush Terminal Made in NY Unit A and C | 1 | DESIGN | 2017-07-01 | 2017-07-20 | 2017-07-01 | 2020-04-11
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BUSHUNTAC | Bush Terminal Made in NY Unit A and C | 2 | BID AWARD AND REGISTER CONTRCT | 2017-07-21 | 2017-08-04 | 2020-04-12 | 2020-04-26
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BUSHUNTAC | Bush Terminal Made in NY Unit A and C | 3 | CONSTRUCTION | 2017-08-05 | 2017-09-08 | 2020-04-27 | 2020-05-31
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BUSHUNTAC | Bush Terminal Made in NY Unit A and C | 4 | ORIGINAL EQUIP & FURNISHING | 2017-09-09 | 2017-09-18 | 2020-06-01 | 2020-06-10
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BUSHUNTAC | Bush Terminal Made in NY Unit A and C | 5 | SUBSTANTIAL COMPLETION | 2017-09-19 | 2017-10-03 | 2020-06-11 | 2020-06-25
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BUSHUNTAC | Bush Terminal Made in NY Unit A and C | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-10-04 | 2017-10-08 | 2020-06-26 | 2023-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BUSHUNTBD | BUSH MINY--UNIT B & D | 1 | DESIGN | 2019-07-01 | 2019-07-20 | 2019-07-01 | 2019-07-20
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BUSHUNTBD | BUSH MINY--UNIT B & D | 2 | BID AWARD AND REGISTER CONTRCT | 2019-07-21 | 2019-08-04 | 2019-07-21 | 2019-08-04
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BUSHUNTBD | BUSH MINY--UNIT B & D | 3 | CONSTRUCTION | 2019-08-05 | 2019-09-08 | 2019-08-05 | 2019-09-08
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BUSHUNTBD | BUSH MINY--UNIT B & D | 4 | ORIGINAL EQUIP & FURNISHING | 2019-09-09 | 2019-09-18 | 2019-09-09 | 2019-09-18
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BUSHUNTBD | BUSH MINY--UNIT B & D | 5 | SUBSTANTIAL COMPLETION | 2019-09-19 | 2021-10-03 | 2019-09-19 | 2021-10-03
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BUSHUNTBD | BUSH MINY--UNIT B & D | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-10-04 | 2021-10-08 | 2021-10-04 | 2026-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BUSHUTIL | Bush Terminal Site and Utility Improvements | 1 | DESIGN | 2017-07-01 | 2017-07-20 | 2017-07-01 | 2020-04-11
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BUSHUTIL | Bush Terminal Site and Utility Improvements | 2 | BID AWARD AND REGISTER CONTRCT | 2017-07-21 | 2017-08-04 | 2020-04-12 | 2020-04-26
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BUSHUTIL | Bush Terminal Site and Utility Improvements | 3 | CONSTRUCTION | 2017-08-05 | 2017-09-08 | 2020-04-27 | 2020-05-31
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BUSHUTIL | Bush Terminal Site and Utility Improvements | 4 | ORIGINAL EQUIP & FURNISHING | 2017-09-09 | 2017-09-18 | 2020-06-01 | 2020-06-10
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BUSHUTIL | Bush Terminal Site and Utility Improvements | 5 | SUBSTANTIAL COMPLETION | 2017-09-19 | 2017-10-03 | 2020-06-11 | 2020-06-25
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BUSHUTIL | Bush Terminal Site and Utility Improvements | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-10-04 | 2017-10-08 | 2020-06-26 | 2023-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CANTONBLK | Canton Court Bulkhead Replacement | 1 | DESIGN | 2016-07-01 | 2016-07-20 | 2016-07-02 | 2016-07-21
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CANTONBLK | Canton Court Bulkhead Replacement | 2 | BID AWARD AND REGISTER CONTRCT | 2016-07-21 | 2016-08-04 | 2016-07-22 | 2016-08-05
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CANTONBLK | Canton Court Bulkhead Replacement | 3 | CONSTRUCTION | 2016-08-05 | 2016-09-08 | 2016-08-06 | 2016-09-09
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CANTONBLK | Canton Court Bulkhead Replacement | 4 | ORIGINAL EQUIP & FURNISHING | 2016-09-09 | 2016-09-18 | 2016-09-10 | 2016-09-19
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CANTONBLK | Canton Court Bulkhead Replacement | 5 | SUBSTANTIAL COMPLETION | 2016-09-19 | 2016-10-03 | 2016-09-20 | 2016-10-04
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CANTONBLK | Canton Court Bulkhead Replacement | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-10-04 | 2016-10-08 | 2016-10-05 | 2025-10-02
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CNEDST | CNED - Bedford Stuyvesant | 1 | DESIGN | 2000-07-01 | 2000-07-20 | 2000-07-01 | 2000-07-20
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CNEDST | CNED - Bedford Stuyvesant | 2 | BID AWARD AND REGISTER CONTRCT | 2000-07-21 | 2000-08-04 | 2000-07-21 | 2000-08-04
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CNEDST | CNED - Bedford Stuyvesant | 3 | CONSTRUCTION | 2000-08-05 | 2008-06-30 | 2000-08-05 | 2022-09-08
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CNEDST | CNED - Bedford Stuyvesant | 4 | ORIGINAL EQUIP & FURNISHING | 2008-07-01 | 2008-06-30 | 2022-09-09 | 2022-09-18
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CNEDST | CNED - Bedford Stuyvesant | 5 | SUBSTANTIAL COMPLETION | 2008-07-01 | 2008-06-30 | 2022-09-19 | 2022-10-03
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CNEDST | CNED - Bedford Stuyvesant | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-07-01 | 2008-07-05 | 2022-10-04 | 2029-10-08
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CNEDST | CNED - Bedford Stuyvesant | 7 | DEVELOP SCOPE | 2008-07-06 | 2008-10-03 | 2022-10-04 | 2029-10-08
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CNEDST | CNED - Bedford Stuyvesant | 8 | PRELIMINARY DESIGN | 2008-10-04 | 2009-01-31 | 2022-10-04 | 2029-10-08
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CNEDST | CNED - Bedford Stuyvesant | 9 | FINAL DESIGN | 2009-02-01 | 2009-07-30 | 2022-10-04 | 2029-10-08
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CNEDST | CNED - Bedford Stuyvesant | 10 | BID AWARD AND REGISTER CONTRCT | 2009-07-31 | 2009-10-28 | 2022-10-04 | 2029-10-08
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CNEDST | CNED - Bedford Stuyvesant | 11 | CONSTRUCTION TO 25% | 2009-10-29 | 2010-02-25 | 2022-10-04 | 2029-10-08
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CNEDST | CNED - Bedford Stuyvesant | 12 | CONSTRUCTION TO 50% | 2010-02-26 | 2010-06-25 | 2022-10-04 | 2029-10-08
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CNEDST | CNED - Bedford Stuyvesant | 13 | CONSTRUCTION TO 75% | 2010-06-26 | 2010-10-23 | 2022-10-04 | 2029-10-08
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CNEDST | CNED - Bedford Stuyvesant | 14 | ORIGINAL EQUIP & FURNISHING | 2010-10-24 | 2011-01-21 | 2022-10-04 | 2029-10-08
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CNEDST | CNED - Bedford Stuyvesant | 15 | SUBSTANTIAL COMPLETION | 2011-01-22 | 2011-03-22 | 2022-10-04 | 2029-10-08
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CNEDST | CNED - Bedford Stuyvesant | 16 | PUNCHLIST COMPLETE, JOB CLOSED | 2011-03-23 | 2011-04-21 | 2022-10-04 | 2029-10-08
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | COLUMBST | Columbia Street Platform Rehabilitation | 1 | DESIGN | 2017-07-01 | 2017-07-20 | 2017-07-01 | 2020-04-10
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | COLUMBST | Columbia Street Platform Rehabilitation | 2 | BID AWARD AND REGISTER CONTRCT | 2017-07-21 | 2017-08-04 | 2020-04-11 | 2020-04-25
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | COLUMBST | Columbia Street Platform Rehabilitation | 3 | CONSTRUCTION | 2017-08-05 | 2017-09-08 | 2020-04-26 | 2020-05-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | COLUMBST | Columbia Street Platform Rehabilitation | 4 | ORIGINAL EQUIP & FURNISHING | 2017-09-09 | 2017-09-18 | 2020-05-31 | 2020-06-09
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | COLUMBST | Columbia Street Platform Rehabilitation | 5 | SUBSTANTIAL COMPLETION | 2017-09-19 | 2017-10-03 | 2020-06-10 | 2020-06-24
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | COLUMBST | Columbia Street Platform Rehabilitation | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-10-04 | 2017-10-08 | 2020-06-25 | 2022-06-29
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CONEYPLAZ | Coney Island Steeplechase Plaza | 1 | DESIGN | 2008-01-01 | 2009-01-01 | 2007-07-01 | 2007-10-15
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CONEYPLAZ | Coney Island Steeplechase Plaza | 2 | BID AWARD AND REGISTER CONTRCT | 2009-01-02 | 2009-01-01 | 2007-10-16 | 2007-10-15
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CONEYPLAZ | Coney Island Steeplechase Plaza | 3 | CONSTRUCTION | 2009-01-02 | 2011-01-01 | 2007-10-16 | 2007-10-15
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CONEYPLAZ | Coney Island Steeplechase Plaza | 4 | ORIGINAL EQUIP & FURNISHING | 2011-01-02 | 2011-01-01 | 2007-10-16 | 2007-10-15
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CONEYPLAZ | Coney Island Steeplechase Plaza | 5 | SUBSTANTIAL COMPLETION | 2011-01-02 | 2011-01-01 | 2007-10-16 | 2017-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CONEYPLAZ | Coney Island Steeplechase Plaza | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2011-01-02 | 2011-01-06 | 2017-07-01 | 2022-03-16
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CONEYSIGN | Coney Island Signs | 1 | DESIGN | 2019-07-01 | 2019-07-20 | 2019-07-01 | 2019-07-20
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CONEYSIGN | Coney Island Signs | 2 | BID AWARD AND REGISTER CONTRCT | 2019-07-21 | 2019-08-04 | 2019-07-21 | 2019-08-04
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CONEYSIGN | Coney Island Signs | 3 | CONSTRUCTION | 2019-08-05 | 2019-09-08 | 2019-08-05 | 2019-09-08
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CONEYSIGN | Coney Island Signs | 4 | ORIGINAL EQUIP & FURNISHING | 2019-09-09 | 2019-09-18 | 2019-09-09 | 2019-09-18
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CONEYSIGN | Coney Island Signs | 5 | SUBSTANTIAL COMPLETION | 2019-09-19 | 2024-10-03 | 2019-09-19 | 2024-10-03
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CONEYSIGN | Coney Island Signs | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-10-04 | 2024-10-08 | 2024-10-04 | 2028-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CONEYTH | Coney Island Acquisition | 3 | CONSTRUCTION | 2011-01-21 | 2012-01-20 | 2011-01-21 | 2012-01-20
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CONEYTH | Coney Island Acquisition | 4 | ORIGINAL EQUIP & FURNISHING | 2012-01-21 | 2012-01-20 | 2012-01-21 | 2012-01-20
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CONEYTH | Coney Island Acquisition | 5 | SUBSTANTIAL COMPLETION | 2012-01-21 | 2012-01-20 | 2012-01-21 | 2012-01-20
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CONEYTH | Coney Island Acquisition | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-01-21 | 2012-01-25 | 2012-01-21 | 2012-01-25
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CONEYWEST | Coney Island West | 1 | DESIGN | 2018-03-23 | 2018-04-11 | 2015-04-01 | 2022-12-31
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CONEYWEST | Coney Island West | 2 | BID AWARD AND REGISTER CONTRCT | 2018-04-12 | 2018-04-26 | 2023-01-01 | 2022-12-31
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CONEYWEST | Coney Island West | 3 | CONSTRUCTION | 2018-04-27 | 2018-05-31 | 2023-01-01 | 2022-12-31
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CONEYWEST | Coney Island West | 4 | ORIGINAL EQUIP & FURNISHING | 2018-06-01 | 2018-06-10 | 2023-01-01 | 2022-12-31
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CONEYWEST | Coney Island West | 5 | SUBSTANTIAL COMPLETION | 2018-06-11 | 2018-06-25 | 2023-01-01 | 2022-12-31
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CONEYWEST | Coney Island West | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-06-26 | 2018-06-30 | 2023-01-01 | 2025-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CORTELYOU | FA - Cortelyou Rd. CR - Flatbush Development Corp. | 4 | ORIGINAL EQUIP & FURNISHING | 2005-07-01 | 2007-06-30 | 2005-07-01 | 2007-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CORTELYOU | FA - Cortelyou Rd. CR - Flatbush Development Corp. | 5 | SUBSTANTIAL COMPLETION | 2007-07-01 | 2007-06-30 | 2007-07-01 | 2007-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CORTELYOU | FA - Cortelyou Rd. CR - Flatbush Development Corp. | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2007-07-01 | 2007-07-05 | 2007-12-02 | 2007-12-06
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CWFSHOMEP | New York City Ferry - Homeport | 1 | DESIGN | 2016-07-01 | 2016-07-20 | 2016-07-01 | 2020-07-20
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CWFSHOMEP | New York City Ferry - Homeport | 2 | BID AWARD AND REGISTER CONTRCT | 2016-07-21 | 2016-08-04 | 2020-07-21 | 2020-08-04
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CWFSHOMEP | New York City Ferry - Homeport | 3 | CONSTRUCTION | 2016-08-05 | 2016-09-08 | 2020-08-05 | 2020-09-08
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CWFSHOMEP | New York City Ferry - Homeport | 4 | ORIGINAL EQUIP & FURNISHING | 2016-09-09 | 2016-09-18 | 2020-09-09 | 2020-09-18
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CWFSHOMEP | New York City Ferry - Homeport | 5 | SUBSTANTIAL COMPLETION | 2016-09-19 | 2016-10-03 | 2020-09-19 | 2020-10-03
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CWFSHOMEP | New York City Ferry - Homeport | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-10-04 | 2016-10-08 | 2020-10-04 | 2020-10-08
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | DEO-OWLS | Owls Head Pier Emergency Dredging | 1 | DESIGN | 2016-07-01 | 2016-07-20 | 2016-07-01 | 2016-07-20
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | DEO-OWLS | Owls Head Pier Emergency Dredging | 2 | BID AWARD AND REGISTER CONTRCT | 2016-07-21 | 2016-08-04 | 2016-07-21 | 2016-08-04
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | DEO-OWLS | Owls Head Pier Emergency Dredging | 3 | CONSTRUCTION | 2016-08-05 | 2016-09-08 | 2016-08-05 | 2016-09-08
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | DEO-OWLS | Owls Head Pier Emergency Dredging | 4 | ORIGINAL EQUIP & FURNISHING | 2016-09-09 | 2016-09-18 | 2016-09-09 | 2016-09-18
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | DEO-OWLS | Owls Head Pier Emergency Dredging | 5 | SUBSTANTIAL COMPLETION | 2016-09-19 | 2016-10-03 | 2016-09-19 | 2016-10-03
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | DEO-OWLS | Owls Head Pier Emergency Dredging | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-10-04 | 2016-10-08 | 2016-10-04 | 2029-10-08
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | DTBKFLATM | Downtown Brooklyn Redevelopment - Flatbush Myrtle Street | 1 | DESIGN | 2004-07-01 | 2004-07-20 | 2004-07-01 | 2008-08-27
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | DTBKFLATM | Downtown Brooklyn Redevelopment - Flatbush Myrtle Street | 2 | BID AWARD AND REGISTER CONTRCT | 2004-07-21 | 2004-08-04 | 2008-08-28 | 2014-12-25
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | DTBKFLATM | Downtown Brooklyn Redevelopment - Flatbush Myrtle Street | 3 | CONSTRUCTION | 2004-08-05 | 2007-06-30 | 2007-06-01 | 2024-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | DTBKFLATM | Downtown Brooklyn Redevelopment - Flatbush Myrtle Street | 4 | ORIGINAL EQUIP & FURNISHING | 2007-07-01 | 2007-06-30 | 2024-07-01 | 2024-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | DTBKFLATM | Downtown Brooklyn Redevelopment - Flatbush Myrtle Street | 5 | SUBSTANTIAL COMPLETION | 2007-07-01 | 2007-06-30 | 2024-07-01 | 2024-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | DTBKFLATM | Downtown Brooklyn Redevelopment - Flatbush Myrtle Street | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2007-07-01 | 2007-07-05 | 2024-07-01 | 2028-06-29
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | DTBKLYNDV | Downtown Brooklyn Redevelopment | 1 | DESIGN | 2004-07-01 | 2004-07-20 | 2021-02-23 | 2022-08-24
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | DTBKLYNDV | Downtown Brooklyn Redevelopment | 2 | BID AWARD AND REGISTER CONTRCT | 2004-07-21 | 2004-08-04 | 2022-08-25 | 2022-08-24
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | DTBKLYNDV | Downtown Brooklyn Redevelopment | 3 | CONSTRUCTION | 2004-08-05 | 2007-07-01 | 2007-09-01 | 2024-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | DTBKLYNDV | Downtown Brooklyn Redevelopment | 4 | ORIGINAL EQUIP & FURNISHING | 2007-07-02 | 2007-07-01 | 2024-07-01 | 2024-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | DTBKLYNDV | Downtown Brooklyn Redevelopment | 5 | SUBSTANTIAL COMPLETION | 2007-07-02 | 2007-07-01 | 2024-07-01 | 2024-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | DTBKLYNDV | Downtown Brooklyn Redevelopment | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2007-07-02 | 2007-07-06 | 2024-07-01 | 2029-06-29
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | DTBKLYNFM | Downtown Brooklyn Redevelopment - Fulton Mall | 1 | DESIGN | 2000-07-01 | 2000-07-20 | 2000-07-01 | 2005-07-20
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | DTBKLYNFM | Downtown Brooklyn Redevelopment - Fulton Mall | 2 | BID AWARD AND REGISTER CONTRCT | 2000-07-21 | 2000-08-04 | 2005-07-21 | 2005-08-04
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | DTBKLYNFM | Downtown Brooklyn Redevelopment - Fulton Mall | 3 | CONSTRUCTION | 2000-08-05 | 2007-06-30 | 2005-08-05 | 2005-09-08
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | DTBKLYNFM | Downtown Brooklyn Redevelopment - Fulton Mall | 4 | ORIGINAL EQUIP & FURNISHING | 2007-07-01 | 2007-06-30 | 2005-09-09 | 2024-09-18
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | DTBKLYNFM | Downtown Brooklyn Redevelopment - Fulton Mall | 5 | SUBSTANTIAL COMPLETION | 2007-07-01 | 2007-06-30 | 2024-09-19 | 2024-10-03
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | DTBKLYNFM | Downtown Brooklyn Redevelopment - Fulton Mall | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2007-07-01 | 2007-07-05 | 2024-10-04 | 2028-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | DTBKWSPK | Downtown Brooklyn - Willoughby Square Park | 1 | DESIGN | 2009-01-01 | 2010-01-01 | 2009-01-01 | 2011-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | DTBKWSPK | Downtown Brooklyn - Willoughby Square Park | 2 | BID AWARD AND REGISTER CONTRCT | 2010-01-02 | 2010-01-01 | 2011-07-01 | 2012-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | DTBKWSPK | Downtown Brooklyn - Willoughby Square Park | 3 | CONSTRUCTION | 2010-01-02 | 2011-01-01 | 2012-07-01 | 2012-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | DTBKWSPK | Downtown Brooklyn - Willoughby Square Park | 4 | ORIGINAL EQUIP & FURNISHING | 2011-01-02 | 2011-01-01 | 2012-07-01 | 2013-12-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | DTBKWSPK | Downtown Brooklyn - Willoughby Square Park | 5 | SUBSTANTIAL COMPLETION | 2011-01-02 | 2011-01-01 | 2013-12-31 | 2013-12-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | DTBKWSPK | Downtown Brooklyn - Willoughby Square Park | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2011-01-02 | 2011-01-06 | 2013-12-31 | 2024-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | EASTNYINC | East New York Incubator Improvements | 1 | DESIGN | 2015-06-30 | 2015-07-19 | 2015-06-30 | 2015-07-19
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | EASTNYINC | East New York Incubator Improvements | 2 | BID AWARD AND REGISTER CONTRCT | 2015-07-20 | 2015-08-03 | 2015-07-20 | 2015-08-03
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | EASTNYINC | East New York Incubator Improvements | 3 | CONSTRUCTION | 2015-08-04 | 2015-09-07 | 2015-08-04 | 2015-09-07
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | EASTNYINC | East New York Incubator Improvements | 4 | ORIGINAL EQUIP & FURNISHING | 2015-09-08 | 2015-09-17 | 2015-09-08 | 2015-09-17
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | EASTNYINC | East New York Incubator Improvements | 5 | SUBSTANTIAL COMPLETION | 2015-09-18 | 2015-10-02 | 2015-09-18 | 2015-10-02
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | EASTNYINC | East New York Incubator Improvements | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-10-03 | 2015-10-07 | 2015-10-03 | 2021-10-07
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | ERFERRY | East River Ferry Route | 1 | DESIGN | 2008-09-30 | 2010-10-19 | 2008-09-30 | 2010-10-19
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | ERFERRY | East River Ferry Route | 2 | BID AWARD AND REGISTER CONTRCT | 2010-10-20 | 2010-10-19 | 2010-10-20 | 2010-10-19
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | ERFERRY | East River Ferry Route | 3 | CONSTRUCTION | 2010-10-20 | 2012-10-19 | 2010-10-20 | 2020-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | ERFERRY | East River Ferry Route | 4 | ORIGINAL EQUIP & FURNISHING | 2012-10-20 | 2012-10-19 | 2020-07-01 | 2020-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | ERFERRY | East River Ferry Route | 5 | SUBSTANTIAL COMPLETION | 2012-10-20 | 2012-10-19 | 2020-07-01 | 2020-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | ERFERRY | East River Ferry Route | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-10-20 | 2012-10-24 | 2020-07-01 | 2024-07-05
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | FLATNOST | Flatbush - Nostrand Avenue Streetscapes | 1 | DESIGN | 2001-06-01 | 2001-06-20 | 2006-07-01 | 2006-07-20
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | FLATNOST | Flatbush - Nostrand Avenue Streetscapes | 2 | BID AWARD AND REGISTER CONTRCT | 2001-06-21 | 2001-07-05 | 2006-07-21 | 2006-08-04
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | FLATNOST | Flatbush - Nostrand Avenue Streetscapes | 3 | CONSTRUCTION | 2001-07-06 | 2008-06-30 | 2006-08-05 | 2024-09-08
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | FLATNOST | Flatbush - Nostrand Avenue Streetscapes | 4 | ORIGINAL EQUIP & FURNISHING | 2008-07-01 | 2008-06-30 | 2024-09-09 | 2024-09-18
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | FLATNOST | Flatbush - Nostrand Avenue Streetscapes | 5 | SUBSTANTIAL COMPLETION | 2008-07-01 | 2008-06-30 | 2024-09-19 | 2024-10-03
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | FLATNOST | Flatbush - Nostrand Avenue Streetscapes | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-07-01 | 2008-07-05 | 2024-10-04 | 2024-10-08
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | FLATREV | Flatbush Revitalization | 1 | DESIGN | 2001-06-01 | 2001-06-20 | 2015-09-28 | 2026-09-27
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | FLATREV | Flatbush Revitalization | 2 | BID AWARD AND REGISTER CONTRCT | 2001-06-21 | 2001-07-05 | 2012-03-02 | 2012-03-01
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | FLATREV | Flatbush Revitalization | 3 | CONSTRUCTION | 2001-07-06 | 2008-06-30 | 2012-10-01 | 2012-10-01
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | FLATREV | Flatbush Revitalization | 4 | ORIGINAL EQUIP & FURNISHING | 2008-07-01 | 2008-06-30 | 2012-10-02 | 2012-10-01
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | FLATREV | Flatbush Revitalization | 5 | SUBSTANTIAL COMPLETION | 2008-07-01 | 2008-06-30 | 2012-10-02 | 2015-10-01
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | FLATREV | Flatbush Revitalization | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-07-01 | 2008-07-05 | 2008-08-01 | 2029-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | FREIGHTSP | Freight NYC - Rail Transload | 1 | DESIGN | 2017-07-01 | 2017-07-20 | 2023-03-23 | 2023-04-11
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | FREIGHTSP | Freight NYC - Rail Transload | 2 | BID AWARD AND REGISTER CONTRCT | 2017-07-21 | 2017-08-04 | 2023-04-12 | 2023-04-26
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | FREIGHTSP | Freight NYC - Rail Transload | 3 | CONSTRUCTION | 2017-08-05 | 2017-09-08 | 2023-04-27 | 2023-05-31
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | FREIGHTSP | Freight NYC - Rail Transload | 4 | ORIGINAL EQUIP & FURNISHING | 2017-09-09 | 2017-09-18 | 2023-06-01 | 2023-06-10
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | FREIGHTSP | Freight NYC - Rail Transload | 5 | SUBSTANTIAL COMPLETION | 2017-09-19 | 2017-10-03 | 2023-06-11 | 2023-06-25
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | FREIGHTSP | Freight NYC - Rail Transload | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-10-04 | 2017-10-08 | 2023-06-26 | 2025-06-29
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | GK26W5-05 | DSGN & CONS OF ROW GI IN 26W-005 | 1 | DESIGN | 2015-02-01 | 2017-06-15 | 2016-02-02 | 2018-06-16
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | GK26W5-05 | DSGN & CONS OF ROW GI IN 26W-005 | 2 | BID AWARD AND REGISTER CONTRCT | 2017-06-16 | 2017-06-15 | 2018-06-17 | 2018-06-16
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | GK26W5-05 | DSGN & CONS OF ROW GI IN 26W-005 | 3 | CONSTRUCTION | 2017-06-16 | 2017-12-15 | 2018-06-17 | 2018-12-16
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | GK26W5-05 | DSGN & CONS OF ROW GI IN 26W-005 | 4 | ORIGINAL EQUIP & FURNISHING | 2017-12-16 | 2017-12-15 | 2018-12-17 | 2018-12-16
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | GK26W5-05 | DSGN & CONS OF ROW GI IN 26W-005 | 5 | SUBSTANTIAL COMPLETION | 2017-12-16 | 2017-12-15 | 2018-12-17 | 2018-12-16
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | GK26W5-05 | DSGN & CONS OF ROW GI IN 26W-005 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-12-16 | 2019-06-30 | 2018-12-17 | 2021-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | GKNC15-02 | GI - Green Infrastructure in Newtown Creek Drainage Area | 1 | DESIGN | 2013-04-01 | 2013-04-20 | 2013-04-01 | 2013-04-20
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | GKNC15-02 | GI - Green Infrastructure in Newtown Creek Drainage Area | 2 | BID AWARD AND REGISTER CONTRCT | 2013-04-21 | 2013-05-05 | 2013-04-21 | 2013-05-05
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | GKNC15-02 | GI - Green Infrastructure in Newtown Creek Drainage Area | 3 | CONSTRUCTION | 2013-05-06 | 2013-06-09 | 2013-05-06 | 2013-06-09
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | GKNC15-02 | GI - Green Infrastructure in Newtown Creek Drainage Area | 4 | ORIGINAL EQUIP & FURNISHING | 2013-06-10 | 2013-06-19 | 2013-06-10 | 2013-06-19
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | GKNC15-02 | GI - Green Infrastructure in Newtown Creek Drainage Area | 5 | SUBSTANTIAL COMPLETION | 2013-06-20 | 2013-07-04 | 2013-06-20 | 2013-07-04
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | GKNC15-02 | GI - Green Infrastructure in Newtown Creek Drainage Area | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-07-05 | 2013-07-09 | 2013-07-05 | 2020-07-09
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | GRAFNYC | Graffiti Free Customized Cargo Truck Purchase | 1 | DESIGN | 2017-07-01 | 2017-07-20 | 2019-03-23 | 2019-04-11
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | GRAFNYC | Graffiti Free Customized Cargo Truck Purchase | 2 | BID AWARD AND REGISTER CONTRCT | 2017-07-21 | 2017-08-04 | 2019-04-12 | 2019-04-26
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | GRAFNYC | Graffiti Free Customized Cargo Truck Purchase | 3 | CONSTRUCTION | 2017-08-05 | 2017-09-08 | 2019-04-27 | 2019-05-31
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | GRAFNYC | Graffiti Free Customized Cargo Truck Purchase | 4 | ORIGINAL EQUIP & FURNISHING | 2017-09-09 | 2017-09-18 | 2019-06-01 | 2019-06-10
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | GRAFNYC | Graffiti Free Customized Cargo Truck Purchase | 5 | SUBSTANTIAL COMPLETION | 2017-09-19 | 2017-10-03 | 2019-06-11 | 2019-06-25
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | GRAFNYC | Graffiti Free Customized Cargo Truck Purchase | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-10-04 | 2017-10-08 | 2019-06-26 | 2026-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | GREEN | Green Infrastructure 26W | 1 | DESIGN | 2013-04-24 | 2013-05-13 | 2016-04-24 | 2016-05-13
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | GREEN | Green Infrastructure 26W | 2 | BID AWARD AND REGISTER CONTRCT | 2013-05-14 | 2013-05-28 | 2016-05-14 | 2016-05-28
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | GREEN | Green Infrastructure 26W | 3 | CONSTRUCTION | 2013-05-29 | 2013-07-02 | 2016-05-29 | 2016-07-02
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | GREEN | Green Infrastructure 26W | 4 | ORIGINAL EQUIP & FURNISHING | 2013-07-03 | 2013-07-12 | 2016-07-03 | 2016-07-12
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | GREEN | Green Infrastructure 26W | 5 | SUBSTANTIAL COMPLETION | 2013-07-13 | 2013-07-27 | 2016-07-13 | 2016-07-27
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | GREEN | Green Infrastructure 26W | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-07-28 | 2013-08-01 | 2016-07-28 | 2021-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | GREENPNT | Greenpoint Waterfront Esplanade | 1 | DESIGN | 1996-07-01 | 1996-07-20 | 2003-06-02 | 2003-06-21
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | GREENPNT | Greenpoint Waterfront Esplanade | 2 | BID AWARD AND REGISTER CONTRCT | 1996-07-21 | 1996-08-04 | 2003-06-22 | 2003-07-06
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | GREENPNT | Greenpoint Waterfront Esplanade | 3 | CONSTRUCTION | 1996-08-05 | 2007-06-30 | 2003-07-07 | 2023-08-10
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | GREENPNT | Greenpoint Waterfront Esplanade | 4 | ORIGINAL EQUIP & FURNISHING | 2007-07-01 | 2007-06-30 | 2023-08-11 | 2023-08-20
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | GREENPNT | Greenpoint Waterfront Esplanade | 5 | SUBSTANTIAL COMPLETION | 2007-07-01 | 2007-06-30 | 2023-08-21 | 2023-09-04
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | GREENPNT | Greenpoint Waterfront Esplanade | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2007-07-01 | 2007-07-05 | 2023-09-05 | 2023-09-09
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | HBPD200KA | PED BRIDGE - WEST 8 ST (BIN 2269260) | 1 | DESIGN | 2014-06-30 | 2014-07-19 | 2017-06-30 | 2017-07-19
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | HBPD200KA | PED BRIDGE - WEST 8 ST (BIN 2269260) | 2 | BID AWARD AND REGISTER CONTRCT | 2014-07-20 | 2014-08-03 | 2017-07-20 | 2017-08-03
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | HBPD200KA | PED BRIDGE - WEST 8 ST (BIN 2269260) | 3 | CONSTRUCTION | 2014-08-04 | 2014-09-07 | 2017-08-04 | 2017-09-07
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | HBPD200KA | PED BRIDGE - WEST 8 ST (BIN 2269260) | 4 | ORIGINAL EQUIP & FURNISHING | 2014-09-08 | 2014-09-17 | 2017-09-08 | 2017-09-17
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | HBPD200KA | PED BRIDGE - WEST 8 ST (BIN 2269260) | 5 | SUBSTANTIAL COMPLETION | 2014-09-18 | 2014-10-02 | 2017-09-18 | 2017-10-02
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | HBPD200KA | PED BRIDGE - WEST 8 ST (BIN 2269260) | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-10-03 | 2014-10-07 | 2017-10-03 | 2029-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | HWKFHAWF | Hamilton Ave - DOT Asphalt Plant (Waterfront) | 1 | DEVELOP SCOPE | 2020-06-30 | 2020-09-27 | 2020-06-30 | 2020-09-27
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | HWKFHAWF | Hamilton Ave - DOT Asphalt Plant (Waterfront) | 2 | PRELIMINARY DESIGN | 2020-09-28 | 2021-01-25 | 2020-09-28 | 2021-01-25
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | HWKFHAWF | Hamilton Ave - DOT Asphalt Plant (Waterfront) | 3 | FINAL DESIGN | 2021-01-26 | 2021-07-24 | 2021-01-26 | 2021-07-24
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | HWKFHAWF | Hamilton Ave - DOT Asphalt Plant (Waterfront) | 4 | BID AWARD AND REGISTER CONTRCT | 2021-07-25 | 2021-10-22 | 2021-07-25 | 2021-10-22
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | HWKFHAWF | Hamilton Ave - DOT Asphalt Plant (Waterfront) | 5 | CONSTRUCTION TO 25% | 2021-10-23 | 2022-02-19 | 2021-10-23 | 2022-02-19
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | HWKFHAWF | Hamilton Ave - DOT Asphalt Plant (Waterfront) | 6 | CONSTRUCTION TO 50% | 2022-02-20 | 2022-06-19 | 2022-02-20 | 2022-06-19
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | HWKFHAWF | Hamilton Ave - DOT Asphalt Plant (Waterfront) | 7 | CONSTRUCTION TO 75% | 2022-06-20 | 2022-10-17 | 2022-06-20 | 2025-01-01
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | HWKFHAWF | Hamilton Ave - DOT Asphalt Plant (Waterfront) | 8 | ORIGINAL EQUIP & FURNISHING | 2022-10-18 | 2023-01-15 | 2025-01-02 | 2025-04-01
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | HWKFHAWF | Hamilton Ave - DOT Asphalt Plant (Waterfront) | 9 | SUBSTANTIAL COMPLETION | 2023-01-16 | 2023-03-16 | 2025-04-02 | 2025-05-31
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | HWKFHAWF | Hamilton Ave - DOT Asphalt Plant (Waterfront) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-03-17 | 2023-04-15 | 2025-06-01 | 2025-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | METBIDWAY | FA - Metrotech BID Wayfinding | 1 | DESIGN | 2010-01-01 | 2011-01-20 | 2005-05-30 | 2005-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | METBIDWAY | FA - Metrotech BID Wayfinding | 2 | BID AWARD AND REGISTER CONTRCT | 2011-01-21 | 2011-01-20 | 2005-07-01 | 2005-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | METBIDWAY | FA - Metrotech BID Wayfinding | 3 | CONSTRUCTION | 2011-01-21 | 2013-01-20 | 2005-07-01 | 2014-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | METBIDWAY | FA - Metrotech BID Wayfinding | 4 | ORIGINAL EQUIP & FURNISHING | 2013-01-21 | 2013-01-20 | 2014-07-01 | 2014-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | METBIDWAY | FA - Metrotech BID Wayfinding | 5 | SUBSTANTIAL COMPLETION | 2013-01-21 | 2013-01-20 | 2011-06-30 | 2017-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | METBIDWAY | FA - Metrotech BID Wayfinding | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-01-21 | 2013-01-25 | 2011-06-25 | 2023-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | MILLREHAB | Mill Basin - Waterfront Rehabilitation | 1 | DESIGN | 2016-07-01 | 2016-07-20 | 2018-07-01 | 2018-07-20
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | MILLREHAB | Mill Basin - Waterfront Rehabilitation | 2 | BID AWARD AND REGISTER CONTRCT | 2016-07-21 | 2016-08-04 | 2018-07-21 | 2018-08-04
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | MILLREHAB | Mill Basin - Waterfront Rehabilitation | 3 | CONSTRUCTION | 2016-08-05 | 2016-09-08 | 2018-08-05 | 2018-09-08
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | MILLREHAB | Mill Basin - Waterfront Rehabilitation | 4 | ORIGINAL EQUIP & FURNISHING | 2016-09-09 | 2016-09-18 | 2018-09-09 | 2018-09-18
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | MILLREHAB | Mill Basin - Waterfront Rehabilitation | 5 | SUBSTANTIAL COMPLETION | 2016-09-19 | 2016-10-03 | 2018-09-19 | 2018-10-03
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | MILLREHAB | Mill Basin - Waterfront Rehabilitation | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-10-04 | 2016-10-08 | 2018-10-04 | 2024-10-08
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | MOOREROOF | Moore Street Market Roof Rehabilitation | 1 | DESIGN | 2016-07-01 | 2016-07-20 | 2016-07-01 | 2016-07-20
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | MOOREROOF | Moore Street Market Roof Rehabilitation | 2 | BID AWARD AND REGISTER CONTRCT | 2016-07-21 | 2016-08-04 | 2016-07-21 | 2016-08-04
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | MOOREROOF | Moore Street Market Roof Rehabilitation | 3 | CONSTRUCTION | 2016-08-05 | 2016-09-08 | 2016-08-05 | 2016-09-08
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | MOOREROOF | Moore Street Market Roof Rehabilitation | 4 | ORIGINAL EQUIP & FURNISHING | 2016-09-09 | 2016-09-18 | 2016-09-09 | 2016-09-18
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | MOOREROOF | Moore Street Market Roof Rehabilitation | 5 | SUBSTANTIAL COMPLETION | 2016-09-19 | 2016-10-03 | 2016-09-19 | 2016-10-03
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | MOOREROOF | Moore Street Market Roof Rehabilitation | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-10-04 | 2016-10-08 | 2016-10-04 | 2025-10-08
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | MOOREST | Moore Street Market | 1 | DESIGN | 2005-01-01 | 2005-01-20 | 2006-10-01 | 2006-10-01
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | MOOREST | Moore Street Market | 2 | BID AWARD AND REGISTER CONTRCT | 2003-02-21 | 2005-02-04 | 2003-02-21 | 2005-02-04
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | MOOREST | Moore Street Market | 3 | CONSTRUCTION | 2005-02-05 | 2005-02-04 | 2006-10-01 | 2006-10-01
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | MOOREST | Moore Street Market | 4 | ORIGINAL EQUIP & FURNISHING | 2005-02-05 | 2005-02-04 | 2006-10-02 | 2017-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | MOOREST | Moore Street Market | 5 | SUBSTANTIAL COMPLETION | 2005-02-05 | 2005-02-04 | 2017-07-01 | 2017-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | MOOREST | Moore Street Market | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2005-02-05 | 2005-02-09 | 2017-07-01 | 2023-03-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | MYRTLEBK | Myrtle Ave Acquisition | 1 | DESIGN | 2012-06-01 | 2012-06-20 | 2014-05-27 | 2014-06-15
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | MYRTLEBK | Myrtle Ave Acquisition | 2 | BID AWARD AND REGISTER CONTRCT | 2012-06-21 | 2012-07-05 | 2014-06-16 | 2014-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | MYRTLEBK | Myrtle Ave Acquisition | 3 | CONSTRUCTION | 2012-07-06 | 2012-08-09 | 2014-07-01 | 2014-08-04
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | MYRTLEBK | Myrtle Ave Acquisition | 4 | ORIGINAL EQUIP & FURNISHING | 2012-08-10 | 2012-08-19 | 2014-08-05 | 2014-08-14
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | MYRTLEBK | Myrtle Ave Acquisition | 5 | SUBSTANTIAL COMPLETION | 2012-08-20 | 2012-09-03 | 2014-08-15 | 2021-06-25
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | MYRTLEBK | Myrtle Ave Acquisition | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-09-04 | 2012-09-08 | 2021-06-26 | 2025-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-BROAD | NDF - ENY IBZ Infrastructure - Broadband | 1 | DESIGN | 2016-07-01 | 2016-07-20 | 2019-07-01 | 2019-07-20
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-BROAD | NDF - ENY IBZ Infrastructure - Broadband | 2 | BID AWARD AND REGISTER CONTRCT | 2016-07-21 | 2016-08-04 | 2019-07-21 | 2019-08-04
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-BROAD | NDF - ENY IBZ Infrastructure - Broadband | 3 | CONSTRUCTION | 2016-08-05 | 2016-09-08 | 2019-08-05 | 2019-09-08
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-BROAD | NDF - ENY IBZ Infrastructure - Broadband | 4 | ORIGINAL EQUIP & FURNISHING | 2016-09-09 | 2016-09-18 | 2019-09-09 | 2019-09-18
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-BROAD | NDF - ENY IBZ Infrastructure - Broadband | 5 | SUBSTANTIAL COMPLETION | 2016-09-19 | 2016-10-03 | 2019-09-19 | 2019-10-03
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-BROAD | NDF - ENY IBZ Infrastructure - Broadband | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-10-04 | 2016-10-08 | 2019-10-04 | 2022-10-08
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-CCIMP | NDF - Commercial Corridor Improvements | 1 | DESIGN | 2016-07-01 | 2016-07-20 | 2018-07-01 | 2018-07-20
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-CCIMP | NDF - Commercial Corridor Improvements | 2 | BID AWARD AND REGISTER CONTRCT | 2016-07-21 | 2016-08-04 | 2018-07-21 | 2018-08-04
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-CCIMP | NDF - Commercial Corridor Improvements | 3 | CONSTRUCTION | 2016-08-05 | 2016-09-08 | 2018-08-05 | 2018-09-08
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-CCIMP | NDF - Commercial Corridor Improvements | 4 | ORIGINAL EQUIP & FURNISHING | 2016-09-09 | 2016-09-18 | 2018-09-09 | 2018-09-18
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-CCIMP | NDF - Commercial Corridor Improvements | 5 | SUBSTANTIAL COMPLETION | 2016-09-19 | 2016-10-03 | 2018-09-19 | 2018-10-03
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-CCIMP | NDF - Commercial Corridor Improvements | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-10-04 | 2016-10-08 | 2018-10-04 | 2026-10-08
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-IBMOD | NDF - ENY Industiral Buiding Modernization and Activation | 1 | DESIGN | 2016-07-01 | 2016-07-20 | 2019-03-23 | 2019-04-11
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-IBMOD | NDF - ENY Industiral Buiding Modernization and Activation | 2 | BID AWARD AND REGISTER CONTRCT | 2016-07-21 | 2016-08-04 | 2019-04-12 | 2019-04-26
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-IBMOD | NDF - ENY Industiral Buiding Modernization and Activation | 3 | CONSTRUCTION | 2016-08-05 | 2016-09-08 | 2019-04-27 | 2019-05-31
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-IBMOD | NDF - ENY Industiral Buiding Modernization and Activation | 4 | ORIGINAL EQUIP & FURNISHING | 2016-09-09 | 2016-09-18 | 2019-06-01 | 2019-06-10
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-IBMOD | NDF - ENY Industiral Buiding Modernization and Activation | 5 | SUBSTANTIAL COMPLETION | 2016-09-19 | 2016-10-03 | 2019-06-11 | 2019-06-25
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-IBMOD | NDF - ENY Industiral Buiding Modernization and Activation | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-10-04 | 2016-10-08 | 2019-06-26 | 2022-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | NEWKIRK | FA - Newkirk Plaza Reconstruction | 1 | DESIGN | 2000-07-01 | 2000-07-20 | 2015-06-02 | 2015-06-02
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | NEWKIRK | FA - Newkirk Plaza Reconstruction | 2 | BID AWARD AND REGISTER CONTRCT | 2000-07-21 | 2000-08-04 | 2015-06-03 | 2015-06-02
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | NEWKIRK | FA - Newkirk Plaza Reconstruction | 3 | CONSTRUCTION | 2000-08-05 | 2007-06-30 | 2015-06-03 | 2015-06-02
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | NEWKIRK | FA - Newkirk Plaza Reconstruction | 4 | ORIGINAL EQUIP & FURNISHING | 2007-07-01 | 2007-06-30 | 2015-06-03 | 2020-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | NEWKIRK | FA - Newkirk Plaza Reconstruction | 5 | SUBSTANTIAL COMPLETION | 2007-07-01 | 2007-06-30 | 2020-07-01 | 2020-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | NEWKIRK | FA - Newkirk Plaza Reconstruction | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2007-07-01 | 2007-07-05 | 2020-07-01 | 2023-07-05
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | NOSTRAND | FA - Nostrand Avenue Merchants Assoc. (Flatbush Gateway) | 1 | DESIGN | 2005-01-01 | 2005-01-20 | 2005-01-01 | 2005-01-20
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | NOSTRAND | FA - Nostrand Avenue Merchants Assoc. (Flatbush Gateway) | 2 | BID AWARD AND REGISTER CONTRCT | 2005-01-21 | 2005-02-04 | 2005-01-21 | 2005-02-04
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | NOSTRAND | FA - Nostrand Avenue Merchants Assoc. (Flatbush Gateway) | 3 | CONSTRUCTION | 2005-02-05 | 2007-06-30 | 2005-02-05 | 2007-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | NOSTRAND | FA - Nostrand Avenue Merchants Assoc. (Flatbush Gateway) | 4 | ORIGINAL EQUIP & FURNISHING | 2007-07-01 | 2007-06-30 | 2007-07-01 | 2017-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | NOSTRAND | FA - Nostrand Avenue Merchants Assoc. (Flatbush Gateway) | 5 | SUBSTANTIAL COMPLETION | 2007-07-01 | 2007-06-30 | 2017-07-01 | 2017-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | NOSTRAND | FA - Nostrand Avenue Merchants Assoc. (Flatbush Gateway) | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2007-07-01 | 2007-07-05 | 2017-07-01 | 2023-07-01
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | NWBURGFL | North Williamsburg Ferry Landing | 1 | DESIGN | 2010-01-01 | 2012-01-20 | 2012-05-25 | 2020-06-25
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | NWBURGFL | North Williamsburg Ferry Landing | 2 | BID AWARD AND REGISTER CONTRCT | 2012-01-21 | 2012-01-20 | 2020-06-26 | 2020-06-25
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | NWBURGFL | North Williamsburg Ferry Landing | 3 | CONSTRUCTION | 2012-01-21 | 2014-01-20 | 2020-06-26 | 2020-06-25
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | NWBURGFL | North Williamsburg Ferry Landing | 4 | ORIGINAL EQUIP & FURNISHING | 2014-01-21 | 2014-01-20 | 2020-06-26 | 2020-06-25
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | NWBURGFL | North Williamsburg Ferry Landing | 5 | SUBSTANTIAL COMPLETION | 2014-01-21 | 2014-01-20 | 2020-06-26 | 2020-06-25
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | NWBURGFL | North Williamsburg Ferry Landing | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-01-21 | 2014-01-25 | 2020-06-26 | 2022-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | NYCFHP2 | NYC Ferry Homeport 2 | 1 | DESIGN | 2019-07-01 | 2019-07-20 | 2019-07-01 | 2019-07-20
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | NYCFHP2 | NYC Ferry Homeport 2 | 2 | BID AWARD AND REGISTER CONTRCT | 2019-07-21 | 2019-08-04 | 2019-07-21 | 2019-08-04
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | NYCFHP2 | NYC Ferry Homeport 2 | 3 | CONSTRUCTION | 2019-08-05 | 2019-09-08 | 2019-08-05 | 2019-09-08
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | NYCFHP2 | NYC Ferry Homeport 2 | 4 | ORIGINAL EQUIP & FURNISHING | 2019-09-09 | 2019-09-18 | 2019-09-09 | 2019-09-18
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | NYCFHP2 | NYC Ferry Homeport 2 | 5 | SUBSTANTIAL COMPLETION | 2019-09-19 | 2021-10-03 | 2019-09-19 | 2021-10-03
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | NYCFHP2 | NYC Ferry Homeport 2 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-10-04 | 2021-10-08 | 2021-10-04 | 2021-10-08
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-213CNTR | Seaside Park and Community Arts Center Acquisitions | 1 | DESIGN | 2015-06-30 | 2015-07-19 | 2015-06-30 | 2015-07-19
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-213CNTR | Seaside Park and Community Arts Center Acquisitions | 2 | BID AWARD AND REGISTER CONTRCT | 2015-07-20 | 2015-08-03 | 2015-07-20 | 2015-08-03
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-213CNTR | Seaside Park and Community Arts Center Acquisitions | 3 | CONSTRUCTION | 2015-08-04 | 2015-09-07 | 2015-08-04 | 2015-09-07
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-213CNTR | Seaside Park and Community Arts Center Acquisitions | 4 | ORIGINAL EQUIP & FURNISHING | 2015-09-08 | 2015-09-17 | 2015-09-08 | 2015-09-17
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-213CNTR | Seaside Park and Community Arts Center Acquisitions | 5 | SUBSTANTIAL COMPLETION | 2015-09-18 | 2015-10-02 | 2015-09-18 | 2015-10-02
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-213CNTR | Seaside Park and Community Arts Center Acquisitions | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-10-03 | 2015-10-07 | 2015-10-03 | 2029-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-2GPWB07 | GPWB - Box Street and Newtown Barge Parks | 1 | DEVELOP SCOPE | 2008-07-01 | 2008-09-28 | 2007-10-05 | 2007-10-24
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-2GPWB07 | GPWB - Box Street and Newtown Barge Parks | 2 | DESIGN | 2008-09-29 | 2008-12-27 | 2007-10-25 | 2007-11-08
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-2GPWB07 | GPWB - Box Street and Newtown Barge Parks | 3 | BID/ REGISTER CONTRACT | 2008-12-28 | 2009-03-27 | 2007-11-09 | 2007-12-13
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-2GPWB07 | GPWB - Box Street and Newtown Barge Parks | 4 | CONSTRUCTION | 2009-03-28 | 2010-03-27 | 2007-12-14 | 2007-12-23
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-2GPWB07 | GPWB - Box Street and Newtown Barge Parks | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2010-03-28 | 2011-03-27 | 2007-12-24 | 2008-01-07
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-2GPWB07 | GPWB - Box Street and Newtown Barge Parks | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2010-03-28 | 2011-03-27 | 2008-01-08 | 2021-01-12
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-2GPWB08 | GPWB - 65 Commercial St Soccer Pk-MTA Reloc. & Park Develop. | 1 | DESIGN | 2008-07-01 | 2008-09-28 | 2008-07-01 | 2008-07-20
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-2GPWB08 | GPWB - 65 Commercial St Soccer Pk-MTA Reloc. & Park Develop. | 2 | DESIGN | 2008-09-29 | 2008-12-27 | 2008-07-21 | 2008-08-04
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-2GPWB08 | GPWB - 65 Commercial St Soccer Pk-MTA Reloc. & Park Develop. | 3 | BID/ REGISTER CONTRACT | 2008-12-28 | 2009-03-27 | 2008-08-05 | 2008-09-08
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-2GPWB08 | GPWB - 65 Commercial St Soccer Pk-MTA Reloc. & Park Develop. | 4 | CONSTRUCTION | 2009-03-28 | 2010-03-27 | 2008-09-09 | 2008-09-18
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-2GPWB08 | GPWB - 65 Commercial St Soccer Pk-MTA Reloc. & Park Develop. | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2010-03-28 | 2011-03-27 | 2008-09-19 | 2008-10-03
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-2GPWB08 | GPWB - 65 Commercial St Soccer Pk-MTA Reloc. & Park Develop. | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2010-03-28 | 2011-03-27 | 2008-10-04 | 2024-10-08
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-2GPWB24 | GPWB- Bayside Demolition | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2015-07-20
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-2GPWB24 | GPWB- Bayside Demolition | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2015-07-21 | 2015-08-04
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-2GPWB24 | GPWB- Bayside Demolition | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2015-08-05 | 2015-09-08
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-2GPWB24 | GPWB- Bayside Demolition | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2015-09-09 | 2015-09-18
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-2GPWB24 | GPWB- Bayside Demolition | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2015-09-19 | 2015-10-03
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-2GPWB24 | GPWB- Bayside Demolition | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2015-10-04 | 2024-10-08
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-2GPWBOX | GPWB - Box Street Park | 1 | DESIGN | 2016-07-01 | 2016-07-20 | 2016-07-01 | 2016-07-20
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-2GPWBOX | GPWB - Box Street Park | 2 | BID AWARD AND REGISTER CONTRCT | 2016-07-21 | 2016-08-04 | 2016-07-21 | 2016-08-04
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-2GPWBOX | GPWB - Box Street Park | 3 | CONSTRUCTION | 2016-08-05 | 2016-09-08 | 2016-08-05 | 2016-09-08
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-2GPWBOX | GPWB - Box Street Park | 4 | ORIGINAL EQUIP & FURNISHING | 2016-09-09 | 2016-09-18 | 2016-09-09 | 2016-09-18
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-2GPWBOX | GPWB - Box Street Park | 5 | SUBSTANTIAL COMPLETION | 2016-09-19 | 2016-10-03 | 2016-09-19 | 2016-10-03
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-2GPWBOX | GPWB - Box Street Park | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-10-04 | 2016-10-08 | 2016-10-04 | 2021-10-08
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-2GPWNB | GPWB - Newtown Barge Park | 1 | DESIGN | 2016-07-01 | 2016-07-20 | 2016-07-01 | 2016-07-20
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-2GPWNB | GPWB - Newtown Barge Park | 2 | BID AWARD AND REGISTER CONTRCT | 2016-07-21 | 2016-08-04 | 2016-07-21 | 2016-08-04
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-2GPWNB | GPWB - Newtown Barge Park | 3 | CONSTRUCTION | 2016-08-05 | 2016-09-08 | 2016-08-05 | 2016-09-08
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-2GPWNB | GPWB - Newtown Barge Park | 4 | ORIGINAL EQUIP & FURNISHING | 2016-09-09 | 2016-09-18 | 2016-09-09 | 2016-09-18
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-2GPWNB | GPWB - Newtown Barge Park | 5 | SUBSTANTIAL COMPLETION | 2016-09-19 | 2016-10-03 | 2016-09-19 | 2016-10-03
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-2GPWNB | GPWB - Newtown Barge Park | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-10-04 | 2016-10-08 | 2016-10-04 | 2020-10-08
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PARACHUT2 | Coney Island - Parachute Jump Lighting 2 | 4 | ORIGINAL EQUIP & FURNISHING | 2011-01-02 | 2011-01-01 | 2017-07-01 | 2017-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PARACHUT2 | Coney Island - Parachute Jump Lighting 2 | 5 | SUBSTANTIAL COMPLETION | 2011-01-02 | 2011-01-01 | 2017-07-01 | 2017-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PARACHUT2 | Coney Island - Parachute Jump Lighting 2 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2011-01-02 | 2011-01-06 | 2017-07-01 | 2017-07-05
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER69TH | Pier Substructure Rehabilitation - 69th St. Pier | 1 | DESIGN | 1998-01-01 | 1998-12-31 | 2003-12-16 | 2004-01-04
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER69TH | Pier Substructure Rehabilitation - 69th St. Pier | 2 | BID AWARD AND REGISTER CONTRCT | 1999-01-01 | 1999-03-01 | 2004-01-05 | 2004-01-19
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER69TH | Pier Substructure Rehabilitation - 69th St. Pier | 3 | CONSTRUCTION | 2000-03-02 | 2007-06-30 | 2004-01-20 | 2004-02-23
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER69TH | Pier Substructure Rehabilitation - 69th St. Pier | 4 | ORIGINAL EQUIP & FURNISHING | 2000-08-06 | 2007-06-30 | 2004-02-24 | 2004-03-04
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER69TH | Pier Substructure Rehabilitation - 69th St. Pier | 5 | SUBSTANTIAL COMPLETION | 2000-08-16 | 2007-06-30 | 2004-03-05 | 2004-03-19
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER69TH | Pier Substructure Rehabilitation - 69th St. Pier | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2007-07-01 | 2007-06-30 | 2004-03-20 | 2025-03-24
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER69TH | Pier Substructure Rehabilitation - 69th St. Pier | 7 | DESIGN | 2007-07-01 | 2007-06-30 | 2004-03-20 | 2025-03-24
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER69TH | Pier Substructure Rehabilitation - 69th St. Pier | 8 | BID AWARD AND REGISTER CONTRCT | 2007-07-01 | 2007-06-30 | 2004-03-20 | 2025-03-24
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER69TH | Pier Substructure Rehabilitation - 69th St. Pier | 9 | CONSTRUCTION | 2007-07-01 | 2007-06-30 | 2004-03-20 | 2025-03-24
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER69TH | Pier Substructure Rehabilitation - 69th St. Pier | 10 | ORIGINAL EQUIP & FURNISHING | 2007-07-01 | 2007-06-30 | 2004-03-20 | 2025-03-24
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER69TH | Pier Substructure Rehabilitation - 69th St. Pier | 11 | SUBSTANTIAL COMPLETION | 2007-07-01 | 2007-06-30 | 2004-03-20 | 2025-03-24
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER69TH | Pier Substructure Rehabilitation - 69th St. Pier | 12 | PUNCHLIST COMPLETE, JOB CLOSED | 2007-07-01 | 2007-07-05 | 2004-03-20 | 2025-03-24
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PROSPPLC | Prospect Park Lakeside Center | 1 | DESIGN | 2009-09-01 | 2010-07-01 | 2009-09-01 | 2010-07-01
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PROSPPLC | Prospect Park Lakeside Center | 2 | BID AWARD AND REGISTER CONTRCT | 2010-07-02 | 2010-07-01 | 2010-07-02 | 2010-07-01
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PROSPPLC | Prospect Park Lakeside Center | 3 | CONSTRUCTION | 2010-09-01 | 2011-12-31 | 2010-09-01 | 2011-12-31
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PROSPPLC | Prospect Park Lakeside Center | 4 | ORIGINAL EQUIP & FURNISHING | 2012-01-01 | 2011-12-31 | 2012-01-01 | 2017-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PROSPPLC | Prospect Park Lakeside Center | 5 | SUBSTANTIAL COMPLETION | 2012-01-01 | 2011-12-31 | 2017-07-01 | 2017-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PROSPPLC | Prospect Park Lakeside Center | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-01-01 | 2012-01-05 | 2017-07-01 | 2024-07-05
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV230-SHA | FA - WCS - New York Aquarium | 1 | DESIGN | 2005-01-01 | 2005-01-20 | 2005-01-01 | 2006-12-01
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV230-SHA | FA - WCS - New York Aquarium | 2 | BID AWARD AND REGISTER CONTRCT | 2005-01-21 | 2007-02-04 | 2006-12-02 | 2006-12-01
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV230-SHA | FA - WCS - New York Aquarium | 3 | CONSTRUCTION | 2007-02-05 | 2007-02-04 | 2007-01-01 | 2009-01-01
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV230-SHA | FA - WCS - New York Aquarium | 4 | ORIGINAL EQUIP & FURNISHING | 2007-02-05 | 2007-02-04 | 2009-01-02 | 2009-01-01
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV230-SHA | FA - WCS - New York Aquarium | 5 | SUBSTANTIAL COMPLETION | 2007-02-05 | 2007-02-04 | 2009-01-02 | 2016-02-28
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV230-SHA | FA - WCS - New York Aquarium | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2007-02-05 | 2007-02-09 | 2016-02-29 | 2025-08-26
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV264CINE | BAM - BAM South Site Theaters | 1 | DESIGN | 2014-12-31 | 2016-09-30 | 2014-12-31 | 2016-09-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV264CINE | BAM - BAM South Site Theaters | 2 | BID AWARD AND REGISTER CONTRCT | 2016-10-01 | 2016-09-30 | 2016-10-01 | 2016-09-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV264CINE | BAM - BAM South Site Theaters | 3 | CONSTRUCTION | 2016-10-01 | 2018-09-30 | 2016-10-01 | 2018-09-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV264CINE | BAM - BAM South Site Theaters | 4 | ORIGINAL EQUIP & FURNISHING | 2018-10-01 | 2018-09-30 | 2018-10-01 | 2018-09-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV264CINE | BAM - BAM South Site Theaters | 5 | SUBSTANTIAL COMPLETION | 2018-10-01 | 2018-09-30 | 2018-10-01 | 2018-09-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV264CINE | BAM - BAM South Site Theaters | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-10-01 | 2018-10-05 | 2018-10-01 | 2020-10-05
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV264HART | Brooklyn Academy of Music (BAM) | 1 | DESIGN | 2016-01-01 | 2016-01-20 | 2016-01-01 | 2016-01-20
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV264HART | Brooklyn Academy of Music (BAM) | 2 | BID AWARD AND REGISTER CONTRCT | 2016-01-21 | 2017-02-04 | 2016-01-21 | 2017-02-04
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV264HART | Brooklyn Academy of Music (BAM) | 3 | CONSTRUCTION | 2017-02-05 | 2017-06-04 | 2017-02-05 | 2017-06-04
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV264HART | Brooklyn Academy of Music (BAM) | 4 | ORIGINAL EQUIP & FURNISHING | 2017-06-05 | 2021-06-30 | 2017-06-05 | 2023-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV264HART | Brooklyn Academy of Music (BAM) | 5 | SUBSTANTIAL COMPLETION | 2021-07-01 | 2021-06-30 | 2023-07-01 | 2023-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV264HART | Brooklyn Academy of Music (BAM) | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-07-01 | 2021-07-05 | 2023-07-01 | 2023-07-05
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV467SOST | DBCD South Site Cultural Condo Fitout | 1 | CONSTRUCTION | 2013-09-29 | 2014-09-23 | 2013-07-01 | 2013-07-20
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV467SOST | DBCD South Site Cultural Condo Fitout | 2 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-09-24 | 2015-09-18 | 2013-07-21 | 2013-08-04
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV467SOST | DBCD South Site Cultural Condo Fitout | 3 | CONSTRUCTION | 2014-09-24 | 2015-09-18 | 2013-08-05 | 2013-09-08
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV467SOST | DBCD South Site Cultural Condo Fitout | 4 | ORIGINAL EQUIP & FURNISHING | 2014-09-24 | 2015-09-18 | 2013-09-09 | 2013-09-18
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV467SOST | DBCD South Site Cultural Condo Fitout | 5 | SUBSTANTIAL COMPLETION | 2014-09-24 | 2015-09-18 | 2013-09-19 | 2013-10-03
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV467SOST | DBCD South Site Cultural Condo Fitout | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-09-24 | 2015-09-18 | 2013-10-04 | 2020-10-08
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV467STFO | 651 Arts South Site Studios Fitout | 1 | DESIGN | 2015-06-30 | 2015-07-19 | 2015-06-30 | 2015-07-19
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV467STFO | 651 Arts South Site Studios Fitout | 2 | BID AWARD AND REGISTER CONTRCT | 2015-07-20 | 2015-08-03 | 2015-07-20 | 2015-08-03
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV467STFO | 651 Arts South Site Studios Fitout | 3 | CONSTRUCTION | 2015-08-04 | 2015-09-07 | 2015-08-04 | 2015-09-07
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV467STFO | 651 Arts South Site Studios Fitout | 4 | ORIGINAL EQUIP & FURNISHING | 2015-09-08 | 2015-09-17 | 2015-09-08 | 2015-09-17
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV467STFO | 651 Arts South Site Studios Fitout | 5 | SUBSTANTIAL COMPLETION | 2015-09-18 | 2015-10-02 | 2015-09-18 | 2015-10-02
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV467STFO | 651 Arts South Site Studios Fitout | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-10-03 | 2015-10-07 | 2015-10-03 | 2021-10-07
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PWKNTH | Northside Town Hall | 1 | DESIGN | 2019-08-30 | 2019-09-18 | 2019-08-30 | 2019-09-18
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PWKNTH | Northside Town Hall | 2 | BID AWARD AND REGISTER CONTRCT | 2019-09-19 | 2019-10-03 | 2019-09-19 | 2019-10-03
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PWKNTH | Northside Town Hall | 3 | CONSTRUCTION | 2019-10-04 | 2019-11-07 | 2019-10-04 | 2019-11-07
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PWKNTH | Northside Town Hall | 4 | ORIGINAL EQUIP & FURNISHING | 2019-11-08 | 2019-11-17 | 2019-11-08 | 2019-11-17
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PWKNTH | Northside Town Hall | 5 | SUBSTANTIAL COMPLETION | 2019-11-18 | 2019-12-02 | 2019-11-18 | 2019-12-02
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PWKNTH | Northside Town Hall | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-03 | 2020-12-07 | 2019-12-03 | 2022-12-07
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PWKNTH2 | Northside Town Hall - Renovations to Historic Firehouse | 1 | DESIGN | 2021-06-30 | 2022-09-19 | 2021-06-30 | 2022-09-19
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PWKNTH2 | Northside Town Hall - Renovations to Historic Firehouse | 2 | BID AWARD AND REGISTER CONTRCT | 2022-09-20 | 2022-10-04 | 2022-09-20 | 2022-10-04
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PWKNTH2 | Northside Town Hall - Renovations to Historic Firehouse | 3 | CONSTRUCTION | 2022-10-05 | 2022-11-08 | 2022-10-05 | 2022-11-08
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PWKNTH2 | Northside Town Hall - Renovations to Historic Firehouse | 4 | ORIGINAL EQUIP & FURNISHING | 2022-11-09 | 2022-11-18 | 2022-11-09 | 2022-11-18
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PWKNTH2 | Northside Town Hall - Renovations to Historic Firehouse | 5 | SUBSTANTIAL COMPLETION | 2022-11-19 | 2022-12-03 | 2022-11-19 | 2022-12-03
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PWKNTH2 | Northside Town Hall - Renovations to Historic Firehouse | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-12-04 | 2023-08-30 | 2022-12-04 | 2023-08-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | RE25HC | RECONSTRUCT BULKHEAD 1ST AVE AND 52ND ST, BKLYN | 1 | DESIGN | 2015-06-30 | 2015-07-19 | 2015-06-30 | 2015-07-19
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | RE25HC | RECONSTRUCT BULKHEAD 1ST AVE AND 52ND ST, BKLYN | 2 | BID AWARD AND REGISTER CONTRCT | 2015-07-20 | 2015-08-03 | 2015-07-20 | 2015-08-03
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | RE25HC | RECONSTRUCT BULKHEAD 1ST AVE AND 52ND ST, BKLYN | 3 | CONSTRUCTION | 2015-08-04 | 2015-09-07 | 2015-08-04 | 2015-09-07
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | RE25HC | RECONSTRUCT BULKHEAD 1ST AVE AND 52ND ST, BKLYN | 4 | ORIGINAL EQUIP & FURNISHING | 2015-09-08 | 2015-09-17 | 2015-09-08 | 2015-09-17
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | RE25HC | RECONSTRUCT BULKHEAD 1ST AVE AND 52ND ST, BKLYN | 5 | SUBSTANTIAL COMPLETION | 2015-09-18 | 2015-10-02 | 2015-09-18 | 2015-10-02
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | RE25HC | RECONSTRUCT BULKHEAD 1ST AVE AND 52ND ST, BKLYN | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-10-03 | 2015-10-07 | 2015-10-03 | 2024-10-07
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | REDHOOK | Red Hook Library | 1 | DESIGN | 2016-01-01 | 2016-01-20 | 2016-01-01 | 2016-01-20
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | REDHOOK | Red Hook Library | 2 | BID AWARD AND REGISTER CONTRCT | 2016-01-21 | 2016-06-30 | 2016-01-21 | 2016-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | REDHOOK | Red Hook Library | 3 | CONSTRUCTION | 2016-07-01 | 2017-06-30 | 2016-07-01 | 2017-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | REDHOOK | Red Hook Library | 4 | ORIGINAL EQUIP & FURNISHING | 2017-07-01 | 2021-06-30 | 2017-07-01 | 2021-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | REDHOOK | Red Hook Library | 5 | SUBSTANTIAL COMPLETION | 2021-07-01 | 2021-06-30 | 2021-07-01 | 2021-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | REDHOOK | Red Hook Library | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-07-01 | 2021-07-05 | 2021-07-01 | 2021-07-05
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | RS-CIC | Raise Shoreline - Coney Island Creek | 1 | DESIGN | 2019-08-30 | 2019-09-18 | 2019-08-30 | 2019-09-18
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | RS-CIC | Raise Shoreline - Coney Island Creek | 2 | BID AWARD AND REGISTER CONTRCT | 2019-09-19 | 2019-10-03 | 2019-09-19 | 2019-10-03
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | RS-CIC | Raise Shoreline - Coney Island Creek | 3 | CONSTRUCTION | 2019-10-04 | 2019-11-07 | 2019-10-04 | 2019-11-07
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | RS-CIC | Raise Shoreline - Coney Island Creek | 4 | ORIGINAL EQUIP & FURNISHING | 2019-11-08 | 2019-11-17 | 2019-11-08 | 2019-11-17
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | RS-CIC | Raise Shoreline - Coney Island Creek | 5 | SUBSTANTIAL COMPLETION | 2019-11-18 | 2019-12-02 | 2019-11-18 | 2019-12-02
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | RS-CIC | Raise Shoreline - Coney Island Creek | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-03 | 2020-12-07 | 2019-12-03 | 2025-12-07
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND2601C | CIH: RELOCATE OUTPATIENT RADIOLOGIC IMAGING SERVICES | 1 | DESIGN | 2015-10-01 | 2020-03-31 | 2015-10-01 | 2020-03-31
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND2601C | CIH: RELOCATE OUTPATIENT RADIOLOGIC IMAGING SERVICES | 2 | BID AWARD AND REGISTER CONTRCT | 2020-04-01 | 2020-03-31 | 2020-04-01 | 2020-03-31
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND2601C | CIH: RELOCATE OUTPATIENT RADIOLOGIC IMAGING SERVICES | 3 | CONSTRUCTION | 2020-04-01 | 2020-03-31 | 2020-04-01 | 2020-03-31
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND2601C | CIH: RELOCATE OUTPATIENT RADIOLOGIC IMAGING SERVICES | 4 | ORIGINAL EQUIP & FURNISHING | 2020-04-01 | 2020-03-31 | 2020-04-01 | 2020-03-31
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND2601C | CIH: RELOCATE OUTPATIENT RADIOLOGIC IMAGING SERVICES | 5 | SUBSTANTIAL COMPLETION | 2020-04-01 | 2020-03-31 | 2020-04-01 | 2020-03-31
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND2601C | CIH: RELOCATE OUTPATIENT RADIOLOGIC IMAGING SERVICES | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-04-01 | 2020-04-05 | 2020-04-01 | 2025-04-05
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND2603C | CIH: RENOVATE VACANT SPACE ON FIRST FL MAIN HOSPITAL BLG. | 1 | DESIGN | 2015-10-01 | 2020-03-31 | 2015-10-01 | 2020-03-31
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND2603C | CIH: RENOVATE VACANT SPACE ON FIRST FL MAIN HOSPITAL BLG. | 2 | BID AWARD AND REGISTER CONTRCT | 2020-04-01 | 2020-03-31 | 2020-04-01 | 2020-03-31
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND2603C | CIH: RENOVATE VACANT SPACE ON FIRST FL MAIN HOSPITAL BLG. | 3 | CONSTRUCTION | 2020-04-01 | 2020-03-31 | 2020-04-01 | 2020-03-31
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND2603C | CIH: RENOVATE VACANT SPACE ON FIRST FL MAIN HOSPITAL BLG. | 4 | ORIGINAL EQUIP & FURNISHING | 2020-04-01 | 2020-03-31 | 2020-04-01 | 2020-03-31
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND2603C | CIH: RENOVATE VACANT SPACE ON FIRST FL MAIN HOSPITAL BLG. | 5 | SUBSTANTIAL COMPLETION | 2020-04-01 | 2020-03-31 | 2020-04-01 | 2020-03-31
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND2603C | CIH: RENOVATE VACANT SPACE ON FIRST FL MAIN HOSPITAL BLG. | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-04-01 | 2020-04-05 | 2020-04-01 | 2025-04-05
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND2605 | CIH: DESIGN & CONSTRUCTION MANAGEMENT FOR HOSPITAL CAMPUS | 1 | DESIGN | 2017-07-01 | 2017-07-20 | 2018-03-23 | 2018-04-11
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND2605 | CIH: DESIGN & CONSTRUCTION MANAGEMENT FOR HOSPITAL CAMPUS | 2 | BID AWARD AND REGISTER CONTRCT | 2017-07-21 | 2017-08-04 | 2018-04-12 | 2018-04-26
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND2605 | CIH: DESIGN & CONSTRUCTION MANAGEMENT FOR HOSPITAL CAMPUS | 3 | CONSTRUCTION | 2017-08-05 | 2017-09-08 | 2018-04-27 | 2018-05-31
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND2605 | CIH: DESIGN & CONSTRUCTION MANAGEMENT FOR HOSPITAL CAMPUS | 4 | ORIGINAL EQUIP & FURNISHING | 2017-09-09 | 2017-09-18 | 2018-06-01 | 2018-06-10
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND2605 | CIH: DESIGN & CONSTRUCTION MANAGEMENT FOR HOSPITAL CAMPUS | 5 | SUBSTANTIAL COMPLETION | 2017-09-19 | 2017-10-03 | 2018-06-11 | 2018-06-25
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND2605 | CIH: DESIGN & CONSTRUCTION MANAGEMENT FOR HOSPITAL CAMPUS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-10-04 | 2017-10-08 | 2018-06-26 | 2023-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB3416 | BNYDC - PW 3416 - Berth 6 Concrete Slab | 1 | DESIGN | 2019-01-01 | 2019-07-29 | 2019-01-01 | 2020-07-29
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB3416 | BNYDC - PW 3416 - Berth 6 Concrete Slab | 2 | CONSTRUCTION | 2019-07-30 | 2020-11-10 | 2019-01-01 | 2020-07-29
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB3416 | BNYDC - PW 3416 - Berth 6 Concrete Slab | 3 | SUBSTANTIAL COMPLETION | 2020-11-11 | 2021-01-09 | 2020-07-30 | 2021-11-11
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB3416 | BNYDC - PW 3416 - Berth 6 Concrete Slab | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-01-10 | 2021-01-10 | 2020-07-30 | 2021-11-11
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB3416 | BNYDC - PW 3416 - Berth 6 Concrete Slab | 5 | SUBSTANTIAL COMPLETION | 2021-01-10 | 2021-01-10 | 2021-11-12 | 2022-01-10
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB3416 | BNYDC - PW 3416 - Berth 6 Concrete Slab | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-01-10 | 2021-01-10 | 2022-01-11 | 2022-01-11
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB3820 | BNYDC - PW 3820 - Substations - Buildings 127, 275, 293 | 1 | DESIGN | 2019-01-22 | 2019-04-21 | 2019-05-30 | 2020-08-27
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB3820 | BNYDC - PW 3820 - Substations - Buildings 127, 275, 293 | 2 | CONSTRUCTION | 2019-04-22 | 2020-04-20 | 2019-05-30 | 2020-08-27
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB3820 | BNYDC - PW 3820 - Substations - Buildings 127, 275, 293 | 3 | SUBSTANTIAL COMPLETION | 2020-04-21 | 2020-06-19 | 2020-08-28 | 2022-08-27
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB3820 | BNYDC - PW 3820 - Substations - Buildings 127, 275, 293 | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-06-20 | 2020-06-20 | 2020-08-28 | 2022-08-27
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB3820 | BNYDC - PW 3820 - Substations - Buildings 127, 275, 293 | 5 | SUBSTANTIAL COMPLETION | 2020-06-20 | 2020-06-20 | 2022-08-28 | 2022-10-26
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB3820 | BNYDC - PW 3820 - Substations - Buildings 127, 275, 293 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-06-20 | 2020-06-20 | 2022-10-27 | 2022-10-27
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4225 | BNYDC - PW 4225 Dry-Dock /Caisson Gate #5,#6, Pump Well #156 | 1 | DESIGN | 2019-01-22 | 2019-04-21 | 2019-01-22 | 2020-04-21
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4225 | BNYDC - PW 4225 Dry-Dock /Caisson Gate #5,#6, Pump Well #156 | 2 | CONSTRUCTION | 2019-04-22 | 2020-04-20 | 2019-01-22 | 2020-04-21
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4225 | BNYDC - PW 4225 Dry-Dock /Caisson Gate #5,#6, Pump Well #156 | 3 | SUBSTANTIAL COMPLETION | 2020-04-21 | 2020-06-19 | 2020-04-22 | 2022-04-21
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4225 | BNYDC - PW 4225 Dry-Dock /Caisson Gate #5,#6, Pump Well #156 | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-06-20 | 2020-06-20 | 2020-04-22 | 2022-04-21
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4225 | BNYDC - PW 4225 Dry-Dock /Caisson Gate #5,#6, Pump Well #156 | 5 | SUBSTANTIAL COMPLETION | 2020-06-20 | 2020-06-20 | 2022-04-22 | 2022-06-20
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4225 | BNYDC - PW 4225 Dry-Dock /Caisson Gate #5,#6, Pump Well #156 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-06-20 | 2020-06-20 | 2022-06-21 | 2022-06-21
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4270 | BNYDC - PW 4270 - BNYDC SITE-WIDE CONDUIT - PAAP | 1 | DESIGN | 2019-03-24 | 2019-07-21 | 2019-03-24 | 2020-07-21
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4270 | BNYDC - PW 4270 - BNYDC SITE-WIDE CONDUIT - PAAP | 2 | CONSTRUCTION | 2019-07-22 | 2020-04-16 | 2019-03-24 | 2020-07-21
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4270 | BNYDC - PW 4270 - BNYDC SITE-WIDE CONDUIT - PAAP | 3 | SUBSTANTIAL COMPLETION | 2020-04-17 | 2020-06-29 | 2020-07-22 | 2022-04-17
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4270 | BNYDC - PW 4270 - BNYDC SITE-WIDE CONDUIT - PAAP | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-06-30 | 2020-06-30 | 2020-07-22 | 2022-04-17
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4270 | BNYDC - PW 4270 - BNYDC SITE-WIDE CONDUIT - PAAP | 5 | SUBSTANTIAL COMPLETION | 2020-06-30 | 2020-06-30 | 2022-04-18 | 2022-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4270 | BNYDC - PW 4270 - BNYDC SITE-WIDE CONDUIT - PAAP | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-06-30 | 2020-06-30 | 2022-07-01 | 2022-07-01
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4271 | BNYDC - PW 4271 - Substations No. 292 and No. 542 | 1 | DESIGN | 2019-03-04 | 2019-07-01 | 2019-03-04 | 2020-07-01
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4271 | BNYDC - PW 4271 - Substations No. 292 and No. 542 | 2 | CONSTRUCTION | 2019-07-02 | 2020-03-31 | 2019-03-04 | 2020-07-01
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4271 | BNYDC - PW 4271 - Substations No. 292 and No. 542 | 3 | SUBSTANTIAL COMPLETION | 2020-04-01 | 2020-06-29 | 2020-07-02 | 2022-04-01
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4271 | BNYDC - PW 4271 - Substations No. 292 and No. 542 | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-06-30 | 2020-06-30 | 2020-07-02 | 2022-04-01
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4271 | BNYDC - PW 4271 - Substations No. 292 and No. 542 | 5 | SUBSTANTIAL COMPLETION | 2020-06-30 | 2020-06-30 | 2022-04-02 | 2022-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4271 | BNYDC - PW 4271 - Substations No. 292 and No. 542 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-06-30 | 2020-06-30 | 2022-07-01 | 2022-07-01
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4273 | BNYDC - PW 4273 - Steam Generating Back-Up Plant - Bldg #41A | 1 | DESIGN | 2019-03-04 | 2019-07-01 | 2019-03-04 | 2020-07-01
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4273 | BNYDC - PW 4273 - Steam Generating Back-Up Plant - Bldg #41A | 2 | CONSTRUCTION | 2019-07-02 | 2020-03-31 | 2019-03-04 | 2020-07-01
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4273 | BNYDC - PW 4273 - Steam Generating Back-Up Plant - Bldg #41A | 3 | SUBSTANTIAL COMPLETION | 2020-04-01 | 2020-06-29 | 2020-07-02 | 2022-04-01
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4273 | BNYDC - PW 4273 - Steam Generating Back-Up Plant - Bldg #41A | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-06-30 | 2020-06-30 | 2020-07-02 | 2022-04-01
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4273 | BNYDC - PW 4273 - Steam Generating Back-Up Plant - Bldg #41A | 5 | SUBSTANTIAL COMPLETION | 2020-06-30 | 2020-06-30 | 2022-04-02 | 2022-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4273 | BNYDC - PW 4273 - Steam Generating Back-Up Plant - Bldg #41A | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-06-30 | 2020-06-30 | 2022-07-01 | 2022-07-01
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4274 | BNYDC - PW 4274 - Dry Dock 1 | 1 | DESIGN | 2019-06-01 | 2019-07-30 | 2019-06-01 | 2020-07-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4274 | BNYDC - PW 4274 - Dry Dock 1 | 2 | CONSTRUCTION | 2019-07-31 | 2020-04-25 | 2019-06-01 | 2020-07-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4274 | BNYDC - PW 4274 - Dry Dock 1 | 3 | SUBSTANTIAL COMPLETION | 2020-04-26 | 2020-06-29 | 2020-07-31 | 2022-04-26
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4274 | BNYDC - PW 4274 - Dry Dock 1 | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-06-30 | 2020-06-30 | 2020-07-31 | 2022-04-26
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4274 | BNYDC - PW 4274 - Dry Dock 1 | 5 | SUBSTANTIAL COMPLETION | 2020-06-30 | 2020-06-30 | 2022-04-27 | 2022-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4274 | BNYDC - PW 4274 - Dry Dock 1 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-06-30 | 2020-06-30 | 2022-07-01 | 2022-07-01
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4275 | BNYDC - PW 4275 - SUB STATION G BUILDING 386 | 1 | DESIGN | 2019-03-04 | 2019-07-01 | 2019-03-04 | 2020-07-01
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4275 | BNYDC - PW 4275 - SUB STATION G BUILDING 386 | 2 | CONSTRUCTION | 2019-07-02 | 2020-03-31 | 2019-03-04 | 2020-07-01
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4275 | BNYDC - PW 4275 - SUB STATION G BUILDING 386 | 3 | SUBSTANTIAL COMPLETION | 2020-04-01 | 2020-06-29 | 2020-07-02 | 2022-04-01
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4275 | BNYDC - PW 4275 - SUB STATION G BUILDING 386 | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-06-30 | 2020-06-30 | 2020-07-02 | 2022-04-01
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4275 | BNYDC - PW 4275 - SUB STATION G BUILDING 386 | 5 | SUBSTANTIAL COMPLETION | 2020-06-30 | 2020-06-30 | 2022-04-02 | 2022-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4275 | BNYDC - PW 4275 - SUB STATION G BUILDING 386 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-06-30 | 2020-06-30 | 2022-07-01 | 2022-07-01
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4307 | BNYDC - PW 4307 Substation B | 1 | DESIGN | 2019-03-04 | 2019-07-01 | 2019-03-04 | 2020-07-01
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4307 | BNYDC - PW 4307 Substation B | 2 | CONSTRUCTION | 2019-07-02 | 2020-03-31 | 2019-03-04 | 2020-07-01
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4307 | BNYDC - PW 4307 Substation B | 3 | SUBSTANTIAL COMPLETION | 2020-04-01 | 2020-06-29 | 2020-07-02 | 2022-04-01
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4307 | BNYDC - PW 4307 Substation B | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-06-30 | 2020-06-30 | 2020-07-02 | 2022-04-01
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4307 | BNYDC - PW 4307 Substation B | 5 | SUBSTANTIAL COMPLETION | 2020-06-30 | 2020-06-30 | 2022-04-02 | 2022-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4307 | BNYDC - PW 4307 Substation B | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-06-30 | 2020-06-30 | 2022-07-01 | 2022-07-01
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4388 | BNYDC - PW 4388 - Boiler Replacement | 1 | DESIGN | 2019-03-04 | 2019-07-01 | 2019-03-04 | 2020-07-01
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4388 | BNYDC - PW 4388 - Boiler Replacement | 2 | CONSTRUCTION | 2019-07-02 | 2020-03-31 | 2019-03-04 | 2020-07-01
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4388 | BNYDC - PW 4388 - Boiler Replacement | 3 | SUBSTANTIAL COMPLETION | 2020-04-01 | 2020-06-29 | 2020-07-02 | 2022-04-01
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4388 | BNYDC - PW 4388 - Boiler Replacement | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-06-30 | 2020-06-30 | 2020-07-02 | 2022-04-01
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4388 | BNYDC - PW 4388 - Boiler Replacement | 5 | SUBSTANTIAL COMPLETION | 2020-06-30 | 2020-06-30 | 2022-04-02 | 2022-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4388 | BNYDC - PW 4388 - Boiler Replacement | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-06-30 | 2020-06-30 | 2022-07-01 | 2022-07-01
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4582 | BNYDC - PW 4582 - BERTH 9,9A | 1 | DESIGN | 2019-02-19 | 2019-06-18 | 2019-02-19 | 2021-06-18
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4582 | BNYDC - PW 4582 - BERTH 9,9A | 2 | CONSTRUCTION | 2019-06-19 | 2020-03-30 | 2019-02-19 | 2021-06-18
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4582 | BNYDC - PW 4582 - BERTH 9,9A | 3 | SUBSTANTIAL COMPLETION | 2020-03-31 | 2020-06-29 | 2021-06-19 | 2022-03-31
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4582 | BNYDC - PW 4582 - BERTH 9,9A | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-06-30 | 2020-06-30 | 2021-06-19 | 2022-03-31
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4582 | BNYDC - PW 4582 - BERTH 9,9A | 5 | SUBSTANTIAL COMPLETION | 2020-06-30 | 2020-06-30 | 2022-04-01 | 2022-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4582 | BNYDC - PW 4582 - BERTH 9,9A | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-06-30 | 2020-06-30 | 2022-07-01 | 2022-07-01
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4583 | BNYDC - PW 4583 - BERTH 10 & 10A | 1 | DESIGN | 2019-02-19 | 2019-06-18 | 2019-02-19 | 2020-06-18
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4583 | BNYDC - PW 4583 - BERTH 10 & 10A | 2 | CONSTRUCTION | 2019-06-19 | 2020-04-27 | 2019-02-19 | 2020-06-18
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4583 | BNYDC - PW 4583 - BERTH 10 & 10A | 3 | SUBSTANTIAL COMPLETION | 2020-04-28 | 2020-06-29 | 2020-06-19 | 2022-04-28
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4583 | BNYDC - PW 4583 - BERTH 10 & 10A | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-06-30 | 2020-06-30 | 2020-06-19 | 2022-04-28
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4583 | BNYDC - PW 4583 - BERTH 10 & 10A | 5 | SUBSTANTIAL COMPLETION | 2020-06-30 | 2020-06-30 | 2022-04-29 | 2022-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4583 | BNYDC - PW 4583 - BERTH 10 & 10A | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-06-30 | 2020-06-30 | 2022-07-01 | 2022-07-01
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDBCT | EDC - Hurricane Sandy - BCT Repairs | 1 | DESIGN | 2015-06-30 | 2015-07-19 | 2018-06-30 | 2018-07-19
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDBCT | EDC - Hurricane Sandy - BCT Repairs | 2 | BID AWARD AND REGISTER CONTRCT | 2015-07-20 | 2015-08-03 | 2018-07-20 | 2018-08-03
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDBCT | EDC - Hurricane Sandy - BCT Repairs | 3 | CONSTRUCTION | 2015-08-04 | 2015-09-07 | 2018-08-04 | 2018-09-07
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDBCT | EDC - Hurricane Sandy - BCT Repairs | 4 | ORIGINAL EQUIP & FURNISHING | 2015-09-08 | 2015-09-17 | 2018-09-08 | 2018-09-17
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDBCT | EDC - Hurricane Sandy - BCT Repairs | 5 | SUBSTANTIAL COMPLETION | 2015-09-18 | 2015-10-02 | 2018-09-18 | 2018-10-02
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDBCT | EDC - Hurricane Sandy - BCT Repairs | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-10-03 | 2015-10-07 | 2018-10-03 | 2023-10-07
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDBNYAM | BNYDC Hurricane Sandy Asset Management Repairs | 1 | DESIGN | 2017-06-30 | 2017-07-19 | 2017-06-30 | 2017-07-19
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDBNYAM | BNYDC Hurricane Sandy Asset Management Repairs | 2 | BID AWARD AND REGISTER CONTRCT | 2017-07-20 | 2017-08-03 | 2017-07-20 | 2017-08-03
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDBNYAM | BNYDC Hurricane Sandy Asset Management Repairs | 3 | CONSTRUCTION | 2017-08-04 | 2017-09-07 | 2017-08-04 | 2017-09-07
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDBNYAM | BNYDC Hurricane Sandy Asset Management Repairs | 4 | ORIGINAL EQUIP & FURNISHING | 2017-09-08 | 2017-09-17 | 2017-09-08 | 2017-09-17
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDBNYAM | BNYDC Hurricane Sandy Asset Management Repairs | 5 | SUBSTANTIAL COMPLETION | 2017-09-18 | 2017-10-02 | 2017-09-18 | 2017-10-02
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDBNYAM | BNYDC Hurricane Sandy Asset Management Repairs | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-10-03 | 2021-10-07 | 2017-10-03 | 2021-10-07
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDBNYEC | BNYDC Hurricane Sandy Electrical Repairs | 1 | DESIGN | 2016-01-01 | 2016-01-20 | 2016-01-01 | 2016-01-20
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDBNYEC | BNYDC Hurricane Sandy Electrical Repairs | 2 | BID AWARD AND REGISTER CONTRCT | 2016-01-21 | 2016-06-30 | 2016-01-21 | 2016-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDBNYEC | BNYDC Hurricane Sandy Electrical Repairs | 3 | CONSTRUCTION | 2016-07-01 | 2017-06-30 | 2016-07-01 | 2017-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDBNYEC | BNYDC Hurricane Sandy Electrical Repairs | 4 | ORIGINAL EQUIP & FURNISHING | 2017-07-01 | 2020-06-30 | 2017-07-01 | 2022-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDBNYEC | BNYDC Hurricane Sandy Electrical Repairs | 5 | SUBSTANTIAL COMPLETION | 2020-07-01 | 2020-06-30 | 2022-07-01 | 2022-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDBNYEC | BNYDC Hurricane Sandy Electrical Repairs | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-07-01 | 2020-07-05 | 2022-07-01 | 2022-07-05
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDBNYWF | BNYDC Hurricane Sandy Waterfront Repair | 1 | DESIGN | 2016-01-01 | 2016-01-20 | 2016-01-01 | 2016-01-20
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDBNYWF | BNYDC Hurricane Sandy Waterfront Repair | 2 | BID AWARD AND REGISTER CONTRCT | 2016-01-21 | 2016-06-30 | 2016-01-21 | 2016-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDBNYWF | BNYDC Hurricane Sandy Waterfront Repair | 3 | CONSTRUCTION | 2016-07-01 | 2017-06-30 | 2016-07-01 | 2017-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDBNYWF | BNYDC Hurricane Sandy Waterfront Repair | 4 | ORIGINAL EQUIP & FURNISHING | 2017-07-01 | 2020-06-30 | 2017-07-01 | 2022-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDBNYWF | BNYDC Hurricane Sandy Waterfront Repair | 5 | SUBSTANTIAL COMPLETION | 2020-07-01 | 2020-06-30 | 2022-07-01 | 2022-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDBNYWF | BNYDC Hurricane Sandy Waterfront Repair | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-07-01 | 2020-07-05 | 2022-07-01 | 2022-07-05
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDCD9 | HARBOR CHARLIE | 1 | DEVELOP SCOPE | 2016-06-30 | 2016-09-27 | 2016-02-24 | 2016-03-14
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDCD9 | HARBOR CHARLIE | 2 | PRELIMINARY DESIGN | 2016-09-28 | 2017-01-25 | 2016-03-15 | 2016-03-29
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDCD9 | HARBOR CHARLIE | 3 | FINAL DESIGN | 2017-01-26 | 2017-05-25 | 2016-03-30 | 2016-05-03
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDCD9 | HARBOR CHARLIE | 4 | BID AWARD AND REGISTER CONTRCT | 2017-05-26 | 2017-11-21 | 2016-05-04 | 2016-05-13
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDCD9 | HARBOR CHARLIE | 5 | CONSTRUCTION TO 25% | 2017-11-22 | 2018-03-21 | 2016-05-14 | 2016-05-28
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDCD9 | HARBOR CHARLIE | 6 | CONSTRUCTION TO 50% | 2018-03-22 | 2018-07-19 | 2016-05-29 | 2021-06-02
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDCD9 | HARBOR CHARLIE | 7 | CONSTRUCTION TO 75% | 2018-07-20 | 2018-11-16 | 2016-05-29 | 2021-06-02
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDCD9 | HARBOR CHARLIE | 8 | ORIGINAL EQUIP & FURNISHING | 2018-11-17 | 2019-02-14 | 2016-05-29 | 2021-06-02
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDCD9 | HARBOR CHARLIE | 9 | SUBSTANTIAL COMPLETION | 2019-02-15 | 2019-04-15 | 2016-05-29 | 2021-06-02
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDCD9 | HARBOR CHARLIE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-04-16 | 2019-05-15 | 2016-05-29 | 2021-06-02
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDG3BAT | FEMA 428 Projects - Group 3 - Brooklyn Army Terminal BAT | 1 | DESIGN | 2016-07-01 | 2016-07-20 | 2016-07-01 | 2021-07-20
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDG3BAT | FEMA 428 Projects - Group 3 - Brooklyn Army Terminal BAT | 2 | BID AWARD AND REGISTER CONTRCT | 2016-07-21 | 2016-08-04 | 2021-07-21 | 2021-08-04
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDG3BAT | FEMA 428 Projects - Group 3 - Brooklyn Army Terminal BAT | 3 | CONSTRUCTION | 2016-08-05 | 2016-09-08 | 2021-08-05 | 2021-09-08
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDG3BAT | FEMA 428 Projects - Group 3 - Brooklyn Army Terminal BAT | 4 | ORIGINAL EQUIP & FURNISHING | 2016-09-09 | 2016-09-18 | 2021-09-09 | 2021-09-18
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDG3BAT | FEMA 428 Projects - Group 3 - Brooklyn Army Terminal BAT | 5 | SUBSTANTIAL COMPLETION | 2016-09-19 | 2016-10-03 | 2021-09-19 | 2021-10-03
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDG3BAT | FEMA 428 Projects - Group 3 - Brooklyn Army Terminal BAT | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-10-04 | 2016-10-08 | 2021-10-04 | 2025-10-08
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDG3BSH | FEMA 428 Projects - Group 3 - BUSH Terminal | 1 | DESIGN | 2016-07-01 | 2016-07-20 | 2016-07-01 | 2016-07-20
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDG3BSH | FEMA 428 Projects - Group 3 - BUSH Terminal | 2 | BID AWARD AND REGISTER CONTRCT | 2016-07-21 | 2016-08-04 | 2016-07-21 | 2016-08-04
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDG3BSH | FEMA 428 Projects - Group 3 - BUSH Terminal | 3 | CONSTRUCTION | 2016-08-05 | 2016-09-08 | 2016-08-05 | 2016-09-08
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDG3BSH | FEMA 428 Projects - Group 3 - BUSH Terminal | 4 | ORIGINAL EQUIP & FURNISHING | 2016-09-09 | 2016-09-18 | 2016-09-09 | 2016-09-18
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDG3BSH | FEMA 428 Projects - Group 3 - BUSH Terminal | 5 | SUBSTANTIAL COMPLETION | 2016-09-19 | 2016-10-03 | 2016-09-19 | 2016-10-03
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDG3BSH | FEMA 428 Projects - Group 3 - BUSH Terminal | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-10-04 | 2016-10-08 | 2016-10-04 | 2025-10-08
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDRBCT | FA Resiliency - BCT | 1 | DESIGN | 2016-07-01 | 2016-07-20 | 2016-07-01 | 2016-07-20
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDRBCT | FA Resiliency - BCT | 2 | BID AWARD AND REGISTER CONTRCT | 2016-07-21 | 2016-08-04 | 2016-07-21 | 2016-08-04
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDRBCT | FA Resiliency - BCT | 3 | CONSTRUCTION | 2016-08-05 | 2016-09-08 | 2016-08-05 | 2016-09-08
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDRBCT | FA Resiliency - BCT | 4 | ORIGINAL EQUIP & FURNISHING | 2016-09-09 | 2016-09-18 | 2016-09-09 | 2016-09-18
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDRBCT | FA Resiliency - BCT | 5 | SUBSTANTIAL COMPLETION | 2016-09-19 | 2016-10-03 | 2016-09-19 | 2016-10-03
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDRBCT | FA Resiliency - BCT | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-10-04 | 2020-10-08 | 2016-10-04 | 2022-10-08
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDYNYA | WCS - New York Aquarium Sandy Renovation | 1 | DESIGN | 2016-01-01 | 2016-01-20 | 2016-01-01 | 2016-01-20
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDYNYA | WCS - New York Aquarium Sandy Renovation | 2 | BID AWARD AND REGISTER CONTRCT | 2016-01-21 | 2016-06-30 | 2016-01-21 | 2016-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDYNYA | WCS - New York Aquarium Sandy Renovation | 3 | CONSTRUCTION | 2016-07-01 | 2017-06-30 | 2016-07-01 | 2017-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDYNYA | WCS - New York Aquarium Sandy Renovation | 4 | ORIGINAL EQUIP & FURNISHING | 2017-07-01 | 2020-06-30 | 2017-07-01 | 2020-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDYNYA | WCS - New York Aquarium Sandy Renovation | 5 | SUBSTANTIAL COMPLETION | 2020-07-01 | 2020-06-30 | 2020-07-01 | 2020-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDYNYA | WCS - New York Aquarium Sandy Renovation | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-07-01 | 2020-07-05 | 2020-07-01 | 2020-07-05
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SBMT39P | South Brooklyn Marine Terminal 39th Street Pier Rehab | 1 | DESIGN | 2015-03-23 | 2015-04-11 | 2018-03-23 | 2018-04-11
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SBMT39P | South Brooklyn Marine Terminal 39th Street Pier Rehab | 2 | BID AWARD AND REGISTER CONTRCT | 2015-04-12 | 2015-04-26 | 2018-04-12 | 2018-04-26
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SBMT39P | South Brooklyn Marine Terminal 39th Street Pier Rehab | 3 | CONSTRUCTION | 2015-04-27 | 2015-05-31 | 2018-04-27 | 2018-05-31
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SBMT39P | South Brooklyn Marine Terminal 39th Street Pier Rehab | 4 | ORIGINAL EQUIP & FURNISHING | 2015-06-01 | 2015-06-10 | 2018-06-01 | 2018-06-10
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SBMT39P | South Brooklyn Marine Terminal 39th Street Pier Rehab | 5 | SUBSTANTIAL COMPLETION | 2015-06-11 | 2015-06-25 | 2018-06-11 | 2018-06-25
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SBMT39P | South Brooklyn Marine Terminal 39th Street Pier Rehab | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-06-26 | 2015-06-30 | 2018-06-26 | 2023-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SBMTAUTO | SBMT - Axis | 1 | DESIGN | 2006-01-01 | 2006-01-20 | 2016-01-01 | 2017-07-03
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SBMTAUTO | SBMT - Axis | 2 | BID AWARD AND REGISTER CONTRCT | 2006-01-21 | 2007-02-04 | 2007-01-01 | 2007-12-31
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SBMTAUTO | SBMT - Axis | 3 | CONSTRUCTION | 2007-02-05 | 2007-02-04 | 2007-03-01 | 2020-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SBMTAUTO | SBMT - Axis | 4 | ORIGINAL EQUIP & FURNISHING | 2007-02-05 | 2007-02-04 | 2020-07-01 | 2020-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SBMTAUTO | SBMT - Axis | 5 | SUBSTANTIAL COMPLETION | 2007-02-05 | 2007-02-04 | 2020-07-01 | 2020-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SBMTAUTO | SBMT - Axis | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2007-02-05 | 2007-02-09 | 2020-07-01 | 2024-12-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SBMTFRT | Freight - SBMT 33rd Street Pier | 1 | DESIGN | 2017-06-30 | 2017-07-19 | 2017-06-30 | 2017-07-19
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SBMTFRT | Freight - SBMT 33rd Street Pier | 2 | BID AWARD AND REGISTER CONTRCT | 2017-07-20 | 2017-08-03 | 2017-07-20 | 2017-08-03
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SBMTFRT | Freight - SBMT 33rd Street Pier | 3 | CONSTRUCTION | 2017-08-04 | 2017-09-07 | 2017-08-04 | 2017-09-07
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SBMTFRT | Freight - SBMT 33rd Street Pier | 4 | ORIGINAL EQUIP & FURNISHING | 2017-09-08 | 2017-09-17 | 2017-09-08 | 2017-09-17
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SBMTFRT | Freight - SBMT 33rd Street Pier | 5 | SUBSTANTIAL COMPLETION | 2017-09-18 | 2017-10-02 | 2017-09-18 | 2017-10-02
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SBMTFRT | Freight - SBMT 33rd Street Pier | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-10-03 | 2020-10-07 | 2017-10-03 | 2028-10-07
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SNSTFRGH2 | Sunset Park Areawide Infrastructure Improvements | 1 | DESIGN | 2016-01-01 | 2016-01-20 | 2016-01-01 | 2016-01-20
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SNSTFRGH2 | Sunset Park Areawide Infrastructure Improvements | 2 | BID AWARD AND REGISTER CONTRCT | 2016-01-21 | 2016-06-30 | 2016-01-21 | 2016-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SNSTFRGH2 | Sunset Park Areawide Infrastructure Improvements | 3 | CONSTRUCTION | 2016-07-01 | 2017-06-30 | 2016-07-01 | 2017-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SNSTFRGH2 | Sunset Park Areawide Infrastructure Improvements | 4 | ORIGINAL EQUIP & FURNISHING | 2017-07-01 | 2020-06-30 | 2017-07-01 | 2020-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SNSTFRGH2 | Sunset Park Areawide Infrastructure Improvements | 5 | SUBSTANTIAL COMPLETION | 2020-07-01 | 2020-06-30 | 2020-07-01 | 2020-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SNSTFRGH2 | Sunset Park Areawide Infrastructure Improvements | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-07-01 | 2020-07-05 | 2020-07-01 | 2025-07-05
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SPUDBARGE | 69th Street Pier Reconstruction - Spud Barge | 1 | DESIGN | 2005-01-01 | 2005-01-20 | 2013-12-15 | 2013-12-15
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SPUDBARGE | 69th Street Pier Reconstruction - Spud Barge | 2 | BID AWARD AND REGISTER CONTRCT | 2005-01-21 | 2005-02-04 | 2013-12-16 | 2013-12-15
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SPUDBARGE | 69th Street Pier Reconstruction - Spud Barge | 3 | CONSTRUCTION | 2005-02-05 | 2007-06-30 | 2013-06-30 | 2021-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SPUDBARGE | 69th Street Pier Reconstruction - Spud Barge | 4 | ORIGINAL EQUIP & FURNISHING | 2007-07-01 | 2007-06-30 | 2021-07-01 | 2021-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SPUDBARGE | 69th Street Pier Reconstruction - Spud Barge | 5 | SUBSTANTIAL COMPLETION | 2007-07-01 | 2007-06-30 | 2021-07-01 | 2021-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SPUDBARGE | 69th Street Pier Reconstruction - Spud Barge | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2007-07-01 | 2007-07-05 | 2021-07-01 | 2025-07-05
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | STRAND2 | Strand Theater Rehab | 1 | DESIGN | 2016-01-01 | 2016-01-20 | 2016-01-01 | 2016-01-20
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | STRAND2 | Strand Theater Rehab | 2 | BID AWARD AND REGISTER CONTRCT | 2016-01-21 | 2016-06-30 | 2016-01-21 | 2016-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | STRAND2 | Strand Theater Rehab | 3 | CONSTRUCTION | 2016-07-01 | 2017-06-30 | 2016-07-01 | 2017-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | STRAND2 | Strand Theater Rehab | 4 | ORIGINAL EQUIP & FURNISHING | 2017-07-01 | 2020-06-30 | 2017-07-01 | 2020-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | STRAND2 | Strand Theater Rehab | 5 | SUBSTANTIAL COMPLETION | 2020-07-01 | 2020-06-30 | 2020-07-01 | 2020-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | STRAND2 | Strand Theater Rehab | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-07-01 | 2020-07-05 | 2020-07-01 | 2028-07-05
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SUNSETPAR | Sunset Park Waterfront Redevelopment | 1 | DESIGN | 2000-07-01 | 2000-07-20 | 2000-07-01 | 2007-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SUNSETPAR | Sunset Park Waterfront Redevelopment | 2 | BID AWARD AND REGISTER CONTRCT | 2000-07-21 | 2000-08-04 | 2007-07-01 | 2007-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SUNSETPAR | Sunset Park Waterfront Redevelopment | 3 | CONSTRUCTION | 2000-08-05 | 2006-06-30 | 2007-07-01 | 2007-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SUNSETPAR | Sunset Park Waterfront Redevelopment | 4 | ORIGINAL EQUIP & FURNISHING | 2006-07-01 | 2006-06-30 | 2007-07-01 | 2007-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SUNSETPAR | Sunset Park Waterfront Redevelopment | 5 | SUBSTANTIAL COMPLETION | 2006-07-01 | 2006-06-30 | 2007-07-01 | 2007-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SUNSETPAR | Sunset Park Waterfront Redevelopment | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2006-07-01 | 2006-07-05 | 2004-01-04 | 2025-06-30
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SUNSETWIF | Sunset Park 5th Avenue Wired - Sunset Park BID Free WiFi | 1 | DESIGN | 2016-07-01 | 2016-07-20 | 2020-07-01 | 2020-07-20
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SUNSETWIF | Sunset Park 5th Avenue Wired - Sunset Park BID Free WiFi | 2 | BID AWARD AND REGISTER CONTRCT | 2016-07-21 | 2016-08-04 | 2020-07-21 | 2020-08-04
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SUNSETWIF | Sunset Park 5th Avenue Wired - Sunset Park BID Free WiFi | 3 | CONSTRUCTION | 2016-08-05 | 2016-09-08 | 2020-08-05 | 2020-09-08
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SUNSETWIF | Sunset Park 5th Avenue Wired - Sunset Park BID Free WiFi | 4 | ORIGINAL EQUIP & FURNISHING | 2016-09-09 | 2016-09-18 | 2020-09-09 | 2020-09-18
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SUNSETWIF | Sunset Park 5th Avenue Wired - Sunset Park BID Free WiFi | 5 | SUBSTANTIAL COMPLETION | 2016-09-19 | 2016-10-03 | 2020-09-19 | 2020-10-03
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SUNSETWIF | Sunset Park 5th Avenue Wired - Sunset Park BID Free WiFi | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-10-04 | 2016-10-08 | 2020-10-04 | 2020-10-08
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | TIMP-BRCS | Tenant Improvement Fund-Brooklyn Roasting Coffee Shop | 1 | DESIGN | 2020-06-30 | 2020-07-19 | 2020-06-30 | 2020-07-19
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | TIMP-BRCS | Tenant Improvement Fund-Brooklyn Roasting Coffee Shop | 2 | BID AWARD AND REGISTER CONTRCT | 2020-07-20 | 2020-08-03 | 2020-07-20 | 2020-08-03
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | TIMP-BRCS | Tenant Improvement Fund-Brooklyn Roasting Coffee Shop | 3 | CONSTRUCTION | 2020-08-04 | 2020-09-07 | 2020-08-04 | 2020-09-07
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | TIMP-BRCS | Tenant Improvement Fund-Brooklyn Roasting Coffee Shop | 4 | ORIGINAL EQUIP & FURNISHING | 2020-09-08 | 2020-09-17 | 2020-09-08 | 2020-09-17
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | TIMP-BRCS | Tenant Improvement Fund-Brooklyn Roasting Coffee Shop | 5 | SUBSTANTIAL COMPLETION | 2020-09-18 | 2020-10-02 | 2020-09-18 | 2020-10-02
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | TIMP-BRCS | Tenant Improvement Fund-Brooklyn Roasting Coffee Shop | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-10-03 | 2024-02-07 | 2020-10-03 | 2024-02-07
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | WCSNONPW | WCS - NYA Sandy Renovation Non FEMA Eligible | 1 | DESIGN | 2020-06-01 | 2020-06-20 | 2020-06-01 | 2020-06-20
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | WCSNONPW | WCS - NYA Sandy Renovation Non FEMA Eligible | 2 | BID AWARD AND REGISTER CONTRCT | 2020-06-21 | 2020-07-05 | 2020-06-21 | 2020-07-05
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | WCSNONPW | WCS - NYA Sandy Renovation Non FEMA Eligible | 3 | CONSTRUCTION | 2020-07-06 | 2020-08-09 | 2020-07-06 | 2020-08-09
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | WCSNONPW | WCS - NYA Sandy Renovation Non FEMA Eligible | 4 | ORIGINAL EQUIP & FURNISHING | 2020-08-10 | 2020-08-19 | 2020-08-10 | 2020-08-19
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | WCSNONPW | WCS - NYA Sandy Renovation Non FEMA Eligible | 5 | SUBSTANTIAL COMPLETION | 2020-08-20 | 2020-09-03 | 2020-08-20 | 2020-09-03
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | WCSNONPW | WCS - NYA Sandy Renovation Non FEMA Eligible | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-04 | 2020-09-08 | 2020-09-04 | 2020-09-08
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | WLBKWSMM | BROOKLYN WHOLESALE MEAT MARKET | 1 | DESIGN | 2020-07-01 | 2020-07-20 | 2020-07-01 | 2020-07-20
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | WLBKWSMM | BROOKLYN WHOLESALE MEAT MARKET | 2 | BID AWARD AND REGISTER CONTRCT | 2020-07-21 | 2020-08-04 | 2020-07-21 | 2020-08-04
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | WLBKWSMM | BROOKLYN WHOLESALE MEAT MARKET | 3 | CONSTRUCTION | 2020-08-05 | 2020-09-08 | 2020-08-05 | 2020-09-08
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | WLBKWSMM | BROOKLYN WHOLESALE MEAT MARKET | 4 | ORIGINAL EQUIP & FURNISHING | 2020-09-09 | 2020-09-18 | 2020-09-09 | 2020-09-18
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | WLBKWSMM | BROOKLYN WHOLESALE MEAT MARKET | 5 | SUBSTANTIAL COMPLETION | 2020-09-19 | 2020-10-03 | 2020-09-19 | 2020-10-03
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | WLBKWSMM | BROOKLYN WHOLESALE MEAT MARKET | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-10-04 | 2020-10-08 | 2020-10-04 | 2020-10-08
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | WLPIER6 | BUSH TERMINAL PIER 6 RECONSTRUCTION | 1 | DESIGN | 2020-07-01 | 2020-07-20 | 2020-07-01 | 2020-07-20
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | WLPIER6 | BUSH TERMINAL PIER 6 RECONSTRUCTION | 2 | BID AWARD AND REGISTER CONTRCT | 2020-07-21 | 2020-08-04 | 2020-07-21 | 2020-08-04
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | WLPIER6 | BUSH TERMINAL PIER 6 RECONSTRUCTION | 3 | CONSTRUCTION | 2020-08-05 | 2020-09-08 | 2020-08-05 | 2020-09-08
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | WLPIER6 | BUSH TERMINAL PIER 6 RECONSTRUCTION | 4 | ORIGINAL EQUIP & FURNISHING | 2020-09-09 | 2020-09-18 | 2020-09-09 | 2020-09-18
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | WLPIER6 | BUSH TERMINAL PIER 6 RECONSTRUCTION | 5 | SUBSTANTIAL COMPLETION | 2020-09-19 | 2020-10-03 | 2020-09-19 | 2020-10-03
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | WLPIER6 | BUSH TERMINAL PIER 6 RECONSTRUCTION | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-10-04 | 2020-10-08 | 2020-10-04 | 2020-10-08
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | WLPIER7 | BUSH TERMINAL PIER 7 DEMOLITION | 1 | DESIGN | 2020-07-01 | 2020-07-20 | 2020-07-01 | 2020-07-20
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | WLPIER7 | BUSH TERMINAL PIER 7 DEMOLITION | 2 | BID AWARD AND REGISTER CONTRCT | 2020-07-21 | 2020-08-04 | 2020-07-21 | 2020-08-04
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | WLPIER7 | BUSH TERMINAL PIER 7 DEMOLITION | 3 | CONSTRUCTION | 2020-08-05 | 2020-09-08 | 2020-08-05 | 2020-09-08
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | WLPIER7 | BUSH TERMINAL PIER 7 DEMOLITION | 4 | ORIGINAL EQUIP & FURNISHING | 2020-09-09 | 2020-09-18 | 2020-09-09 | 2020-09-18
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | WLPIER7 | BUSH TERMINAL PIER 7 DEMOLITION | 5 | SUBSTANTIAL COMPLETION | 2020-09-19 | 2020-10-03 | 2020-09-19 | 2020-10-03
20201123 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | WLPIER7 | BUSH TERMINAL PIER 7 DEMOLITION | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-10-04 | 2020-10-08 | 2020-10-04 | 2020-10-08
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM06BOBK | BOULEVARD BRICKWORK | 1 | DESIGN | 2019-09-01 | 2020-02-27 | 2019-09-01 | 2020-02-27
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM06BOBK | BOULEVARD BRICKWORK | 2 | BID AWARD AND REGISTER CONTRCT | 2020-02-28 | 2020-08-25 | 2020-02-28 | 2020-08-25
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM06BOBK | BOULEVARD BRICKWORK | 3 | CONSTRUCTION | 2020-08-26 | 2021-08-25 | 2020-08-26 | 2021-08-25
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM06BOBK | BOULEVARD BRICKWORK | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-08-26 | 2022-02-21 | 2020-08-26 | 2021-08-25
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM06BOBK | BOULEVARD BRICKWORK | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-08-26 | 2022-02-21 | 2021-08-26 | 2022-02-21
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM08WICC | SECURITY CAMERAS AT INDEPENDENCE TOWERS AND WILLIAMS PLAZA | 3 | CONSTRUCTION | 2008-11-21 | 2009-11-20 | 2008-11-21 | 2009-11-20
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM08WICC | SECURITY CAMERAS AT INDEPENDENCE TOWERS AND WILLIAMS PLAZA | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2009-11-21 | 2010-05-19 | 2008-11-21 | 2009-11-20
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM08WICC | SECURITY CAMERAS AT INDEPENDENCE TOWERS AND WILLIAMS PLAZA | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2009-11-21 | 2010-05-19 | 2009-11-21 | 2010-05-19
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM10WYCR | WYCKOFF GARDENS COMMUNITY ROOM | 1 | DESIGN | 2010-01-01 | 2010-06-29 | 2015-01-13 | 2015-07-11
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM10WYCR | WYCKOFF GARDENS COMMUNITY ROOM | 2 | BID AWARD AND REGISTER CONTRCT | 2010-06-30 | 2010-11-21 | 2015-07-12 | 2015-12-03
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM10WYCR | WYCKOFF GARDENS COMMUNITY ROOM | 3 | CONSTRUCTION | 2010-11-22 | 2011-11-21 | 2015-12-04 | 2016-12-02
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM10WYCR | WYCKOFF GARDENS COMMUNITY ROOM | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2011-11-22 | 2012-05-19 | 2015-12-04 | 2016-12-02
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM10WYCR | WYCKOFF GARDENS COMMUNITY ROOM | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2011-11-22 | 2012-05-19 | 2016-12-03 | 2020-12-01
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM12MCPL | MARCY HOUSES DAY CARE CENTER PLAYGROUND | 1 | DESIGN | 2012-01-01 | 2012-06-28 | 2014-04-20 | 2017-05-24
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM12MCPL | MARCY HOUSES DAY CARE CENTER PLAYGROUND | 2 | BID AWARD AND REGISTER CONTRCT | 2012-06-29 | 2012-11-20 | 2017-05-25 | 2017-05-24
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM12MCPL | MARCY HOUSES DAY CARE CENTER PLAYGROUND | 3 | CONSTRUCTION | 2012-11-21 | 2013-11-20 | 2017-05-25 | 2017-05-24
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM12MCPL | MARCY HOUSES DAY CARE CENTER PLAYGROUND | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-11-21 | 2014-05-19 | 2017-05-25 | 2017-05-24
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM12MCPL | MARCY HOUSES DAY CARE CENTER PLAYGROUND | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-11-21 | 2014-05-19 | 2017-05-25 | 2021-05-23
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM12UPDO | UNITY PLAZA COMMUNITY CENTER UPGRADE | 1 | DESIGN | 2012-01-01 | 2012-06-28 | 2017-10-15 | 2019-05-18
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM12UPDO | UNITY PLAZA COMMUNITY CENTER UPGRADE | 2 | BID AWARD AND REGISTER CONTRCT | 2012-06-29 | 2012-11-20 | 2019-05-19 | 2019-11-14
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM12UPDO | UNITY PLAZA COMMUNITY CENTER UPGRADE | 3 | CONSTRUCTION | 2012-11-21 | 2013-11-20 | 2019-11-15 | 2021-10-29
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM12UPDO | UNITY PLAZA COMMUNITY CENTER UPGRADE | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-11-21 | 2014-05-19 | 2019-11-15 | 2021-10-29
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM12UPDO | UNITY PLAZA COMMUNITY CENTER UPGRADE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-11-21 | 2014-05-19 | 2021-10-30 | 2022-04-27
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM12WYCC | WYCKOFF GARDENS COMMUNITY CENTER UPGRADE | 1 | DESIGN | 2012-01-01 | 2012-06-28 | 2015-01-30 | 2017-01-15
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM12WYCC | WYCKOFF GARDENS COMMUNITY CENTER UPGRADE | 2 | BID AWARD AND REGISTER CONTRCT | 2012-06-29 | 2012-11-20 | 2017-01-16 | 2017-07-14
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM12WYCC | WYCKOFF GARDENS COMMUNITY CENTER UPGRADE | 3 | CONSTRUCTION | 2012-11-21 | 2013-11-20 | 2017-07-15 | 2018-10-12
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM12WYCC | WYCKOFF GARDENS COMMUNITY CENTER UPGRADE | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-11-21 | 2014-05-19 | 2017-07-15 | 2018-10-12
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM12WYCC | WYCKOFF GARDENS COMMUNITY CENTER UPGRADE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-11-21 | 2014-05-19 | 2018-10-13 | 2020-10-11
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM13SURF | SUMNER HOUSES ROOF REPLACEMENT | 1 | DESIGN | 2013-01-18 | 2013-07-16 | 2012-03-30 | 2013-12-12
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM13SURF | SUMNER HOUSES ROOF REPLACEMENT | 2 | BID AWARD AND REGISTER CONTRCT | 2013-07-17 | 2013-12-08 | 2013-12-13 | 2014-06-16
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM13SURF | SUMNER HOUSES ROOF REPLACEMENT | 3 | CONSTRUCTION | 2013-12-09 | 2014-12-08 | 2014-06-17 | 2016-04-12
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM13SURF | SUMNER HOUSES ROOF REPLACEMENT | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-12-09 | 2015-06-06 | 2014-06-17 | 2016-04-12
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM13SURF | SUMNER HOUSES ROOF REPLACEMENT | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-12-09 | 2015-06-06 | 2016-04-13 | 2021-04-11
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM14KBEY | KINGSBOROUGH AND EXTENSION ENERGY IMPROVEMENTS | 1 | DESIGN | 2014-05-01 | 2014-10-27 | 2014-05-01 | 2014-10-27
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM14KBEY | KINGSBOROUGH AND EXTENSION ENERGY IMPROVEMENTS | 2 | BID AWARD AND REGISTER CONTRCT | 2014-10-28 | 2015-03-21 | 2014-10-28 | 2015-03-21
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM14KBEY | KINGSBOROUGH AND EXTENSION ENERGY IMPROVEMENTS | 3 | CONSTRUCTION | 2015-03-22 | 2016-03-20 | 2015-03-22 | 2016-03-20
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM14KBEY | KINGSBOROUGH AND EXTENSION ENERGY IMPROVEMENTS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-21 | 2016-09-16 | 2015-03-22 | 2016-03-20
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM14KBEY | KINGSBOROUGH AND EXTENSION ENERGY IMPROVEMENTS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-21 | 2016-09-16 | 2016-03-21 | 2020-03-19
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15COBC | CONEY ISLAND HOUSES I (SITE 4 & 5) BASKETBALL COURT RENO | 1 | DESIGN | 2015-01-02 | 2015-06-30 | 2019-05-30 | 2019-11-25
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15COBC | CONEY ISLAND HOUSES I (SITE 4 & 5) BASKETBALL COURT RENO | 2 | BID AWARD AND REGISTER CONTRCT | 2015-07-01 | 2015-11-22 | 2019-11-26 | 2020-04-18
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15COBC | CONEY ISLAND HOUSES I (SITE 4 & 5) BASKETBALL COURT RENO | 3 | CONSTRUCTION | 2015-11-23 | 2016-11-21 | 2020-04-19 | 2021-04-18
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15COBC | CONEY ISLAND HOUSES I (SITE 4 & 5) BASKETBALL COURT RENO | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-11-22 | 2017-05-20 | 2020-04-19 | 2021-04-18
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15COBC | CONEY ISLAND HOUSES I (SITE 4 & 5) BASKETBALL COURT RENO | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-11-22 | 2017-05-20 | 2021-04-19 | 2021-10-15
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15GOGR | GOWANUS HOUSES BASKETBALL COURT AND PLAY AREA | 1 | DESIGN | 2015-01-02 | 2015-06-30 | 2016-04-06 | 2017-01-07
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15GOGR | GOWANUS HOUSES BASKETBALL COURT AND PLAY AREA | 2 | BID AWARD AND REGISTER CONTRCT | 2015-07-01 | 2015-11-22 | 2017-01-08 | 2017-07-06
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15GOGR | GOWANUS HOUSES BASKETBALL COURT AND PLAY AREA | 3 | CONSTRUCTION | 2015-11-23 | 2016-11-21 | 2017-07-07 | 2018-04-02
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15GOGR | GOWANUS HOUSES BASKETBALL COURT AND PLAY AREA | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-11-22 | 2017-05-20 | 2017-07-07 | 2018-04-02
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15GOGR | GOWANUS HOUSES BASKETBALL COURT AND PLAY AREA | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-11-22 | 2017-05-20 | 2018-04-03 | 2020-04-01
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15HYGD | HYLAN PLAYGROUND IMPROVEMENTS | 1 | DESIGN | 2015-01-02 | 2015-06-30 | 2016-04-07 | 2017-03-17
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15HYGD | HYLAN PLAYGROUND IMPROVEMENTS | 2 | BID AWARD AND REGISTER CONTRCT | 2015-07-01 | 2015-11-22 | 2017-03-18 | 2017-09-12
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15HYGD | HYLAN PLAYGROUND IMPROVEMENTS | 3 | CONSTRUCTION | 2015-11-23 | 2016-11-21 | 2017-09-13 | 2019-02-10
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15HYGD | HYLAN PLAYGROUND IMPROVEMENTS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-11-22 | 2017-05-20 | 2017-09-13 | 2019-02-10
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15HYGD | HYLAN PLAYGROUND IMPROVEMENTS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-11-22 | 2017-05-20 | 2019-02-11 | 2019-08-09
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15ODPA | O'DWYER GARDENS PLAYGROUND UPGRADES | 1 | DESIGN | 2015-01-02 | 2015-06-30 | 2015-01-02 | 2015-06-30
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15ODPA | O'DWYER GARDENS PLAYGROUND UPGRADES | 2 | BID AWARD AND REGISTER CONTRCT | 2015-07-01 | 2015-11-22 | 2015-07-01 | 2015-11-22
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15ODPA | O'DWYER GARDENS PLAYGROUND UPGRADES | 3 | CONSTRUCTION | 2015-11-23 | 2016-11-21 | 2015-11-23 | 2016-11-21
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15ODPA | O'DWYER GARDENS PLAYGROUND UPGRADES | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-11-22 | 2017-05-20 | 2015-11-23 | 2016-11-21
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15ODPA | O'DWYER GARDENS PLAYGROUND UPGRADES | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-11-22 | 2017-05-20 | 2016-11-22 | 2020-11-20
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15WAPA | 572 WARREN STREET PLAY AREA UPGRADE | 2 | BID AWARD AND REGISTER CONTRCT | 2015-07-01 | 2015-11-22 | 2018-01-19 | 2018-12-21
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15WAPA | 572 WARREN STREET PLAY AREA UPGRADE | 3 | CONSTRUCTION | 2015-11-23 | 2016-11-21 | 2018-12-22 | 2019-09-17
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15WAPA | 572 WARREN STREET PLAY AREA UPGRADE | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-11-22 | 2017-05-20 | 2018-12-22 | 2019-09-17
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15WAPA | 572 WARREN STREET PLAY AREA UPGRADE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-11-22 | 2017-05-20 | 2019-09-18 | 2020-01-14
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15WYPA | WYCKOFF GARDENS TODDLER PLAY AREA UPGRADE | 1 | DESIGN | 2015-01-02 | 2015-06-30 | 2017-05-19 | 2018-03-21
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15WYPA | WYCKOFF GARDENS TODDLER PLAY AREA UPGRADE | 2 | BID AWARD AND REGISTER CONTRCT | 2015-07-01 | 2015-11-22 | 2018-03-22 | 2018-09-17
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15WYPA | WYCKOFF GARDENS TODDLER PLAY AREA UPGRADE | 3 | CONSTRUCTION | 2015-11-23 | 2016-11-21 | 2018-09-18 | 2019-06-21
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15WYPA | WYCKOFF GARDENS TODDLER PLAY AREA UPGRADE | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-11-22 | 2017-05-20 | 2018-09-18 | 2019-06-21
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15WYPA | WYCKOFF GARDENS TODDLER PLAY AREA UPGRADE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-11-22 | 2017-05-20 | 2019-06-22 | 2019-12-18
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16BES9 | BERRY STREET SOUTH 9TH STREET HOUSES SECURITY UPGRADES | 1 | DESIGN | 2016-03-02 | 2016-08-28 | 2016-03-02 | 2016-08-28
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16BES9 | BERRY STREET SOUTH 9TH STREET HOUSES SECURITY UPGRADES | 2 | BID AWARD AND REGISTER CONTRCT | 2016-08-29 | 2017-01-20 | 2016-08-29 | 2017-01-20
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16BES9 | BERRY STREET SOUTH 9TH STREET HOUSES SECURITY UPGRADES | 3 | CONSTRUCTION | 2017-01-21 | 2018-01-20 | 2017-01-21 | 2018-01-20
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16BES9 | BERRY STREET SOUTH 9TH STREET HOUSES SECURITY UPGRADES | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-01-21 | 2018-07-19 | 2017-01-21 | 2018-01-20
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16BES9 | BERRY STREET SOUTH 9TH STREET HOUSES SECURITY UPGRADES | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-01-21 | 2018-07-19 | 2018-01-21 | 2020-01-20
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16FPLI | FIORENTINO PLAZA LIGHTING INSTALLATION | 1 | DESIGN | 2016-01-04 | 2016-07-01 | 2016-01-04 | 2016-07-01
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16FPLI | FIORENTINO PLAZA LIGHTING INSTALLATION | 2 | BID AWARD AND REGISTER CONTRCT | 2016-07-02 | 2016-11-23 | 2016-07-02 | 2016-11-23
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16FPLI | FIORENTINO PLAZA LIGHTING INSTALLATION | 3 | CONSTRUCTION | 2016-11-24 | 2017-11-23 | 2016-11-24 | 2017-11-23
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16FPLI | FIORENTINO PLAZA LIGHTING INSTALLATION | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-11-24 | 2018-05-22 | 2016-11-24 | 2017-11-23
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16FPLI | FIORENTINO PLAZA LIGHTING INSTALLATION | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-11-24 | 2018-05-22 | 2017-11-24 | 2018-05-22
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16HPBR | HOPE GARDENS INSTALLATION OF BOILERS AND RELATED EQUIPMENT | 1 | DESIGN | 2016-01-04 | 2016-07-01 | 2016-11-01 | 2017-12-13
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16HPBR | HOPE GARDENS INSTALLATION OF BOILERS AND RELATED EQUIPMENT | 2 | BID AWARD AND REGISTER CONTRCT | 2016-07-02 | 2016-11-23 | 2017-12-14 | 2018-05-07
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16HPBR | HOPE GARDENS INSTALLATION OF BOILERS AND RELATED EQUIPMENT | 3 | CONSTRUCTION | 2016-11-24 | 2017-11-23 | 2018-05-08 | 2019-05-07
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16HPBR | HOPE GARDENS INSTALLATION OF BOILERS AND RELATED EQUIPMENT | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-11-24 | 2018-05-22 | 2018-05-08 | 2019-05-07
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16HPBR | HOPE GARDENS INSTALLATION OF BOILERS AND RELATED EQUIPMENT | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-11-24 | 2018-05-22 | 2019-05-08 | 2019-11-03
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16HWRD | HOWARD HOUSES TENANTS COUNCIL - SECURITY CAMERAS | 1 | DESIGN | 2016-03-02 | 2016-08-28 | 2016-03-02 | 2016-08-28
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16HWRD | HOWARD HOUSES TENANTS COUNCIL - SECURITY CAMERAS | 2 | BID AWARD AND REGISTER CONTRCT | 2016-08-29 | 2017-01-20 | 2016-08-29 | 2017-01-20
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16HWRD | HOWARD HOUSES TENANTS COUNCIL - SECURITY CAMERAS | 3 | CONSTRUCTION | 2017-01-21 | 2018-01-20 | 2017-01-21 | 2018-01-20
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16HWRD | HOWARD HOUSES TENANTS COUNCIL - SECURITY CAMERAS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-01-21 | 2018-07-19 | 2017-01-21 | 2018-01-20
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16HWRD | HOWARD HOUSES TENANTS COUNCIL - SECURITY CAMERAS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-01-21 | 2018-07-19 | 2018-01-21 | 2018-07-19
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16ITGR | INDEPENDENCE TOWERS GROUNDS IMPROVEMENTS | 1 | DESIGN | 2016-05-03 | 2016-10-29 | 2016-05-03 | 2016-10-29
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16ITGR | INDEPENDENCE TOWERS GROUNDS IMPROVEMENTS | 2 | BID AWARD AND REGISTER CONTRCT | 2016-10-30 | 2017-03-23 | 2016-10-30 | 2017-03-23
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16ITGR | INDEPENDENCE TOWERS GROUNDS IMPROVEMENTS | 3 | CONSTRUCTION | 2017-03-24 | 2018-03-23 | 2017-03-24 | 2018-03-23
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16ITGR | INDEPENDENCE TOWERS GROUNDS IMPROVEMENTS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-03-24 | 2018-09-19 | 2017-03-24 | 2018-03-23
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16ITGR | INDEPENDENCE TOWERS GROUNDS IMPROVEMENTS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-03-24 | 2018-09-19 | 2018-03-24 | 2020-03-22
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16NHGR | NOSTRAND HOUSES PLAYGROUND RENOVATION | 1 | DESIGN | 2016-05-03 | 2016-10-29 | 2016-05-03 | 2016-10-29
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16NHGR | NOSTRAND HOUSES PLAYGROUND RENOVATION | 2 | BID AWARD AND REGISTER CONTRCT | 2016-10-30 | 2017-03-23 | 2016-10-30 | 2017-03-23
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16NHGR | NOSTRAND HOUSES PLAYGROUND RENOVATION | 3 | CONSTRUCTION | 2017-03-24 | 2018-03-23 | 2017-03-24 | 2018-03-23
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16NHGR | NOSTRAND HOUSES PLAYGROUND RENOVATION | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-03-24 | 2018-09-19 | 2017-03-24 | 2018-03-23
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16NHGR | NOSTRAND HOUSES PLAYGROUND RENOVATION | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-03-24 | 2018-09-19 | 2018-03-24 | 2020-03-22
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16SURF | SURF GARDENS DEVELOPMENT - PLAYGROUND RENOVATION | 1 | DESIGN | 2016-01-04 | 2016-07-01 | 2016-01-04 | 2016-07-01
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16SURF | SURF GARDENS DEVELOPMENT - PLAYGROUND RENOVATION | 2 | BID AWARD AND REGISTER CONTRCT | 2016-07-02 | 2016-11-23 | 2016-07-02 | 2016-11-23
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16SURF | SURF GARDENS DEVELOPMENT - PLAYGROUND RENOVATION | 3 | CONSTRUCTION | 2016-11-24 | 2017-11-23 | 2016-11-24 | 2017-11-23
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16SURF | SURF GARDENS DEVELOPMENT - PLAYGROUND RENOVATION | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-11-24 | 2018-05-22 | 2016-11-24 | 2017-11-23
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16SURF | SURF GARDENS DEVELOPMENT - PLAYGROUND RENOVATION | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-11-24 | 2018-05-22 | 2017-11-24 | 2020-11-22
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16WIPL | WILLIAMSBURG HOUSES PLAYGROUND RENOVATION | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-11-24 | 2018-05-22 | 2016-11-24 | 2017-11-23
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16WIPL | WILLIAMSBURG HOUSES PLAYGROUND RENOVATION | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-11-24 | 2018-05-22 | 2017-11-24 | 2020-11-22
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM17BVTV | BAYVIEW HOUSES SECURITY CAMERAS | 1 | DESIGN | 2017-02-01 | 2017-07-30 | 2017-02-01 | 2017-07-30
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM17BVTV | BAYVIEW HOUSES SECURITY CAMERAS | 2 | BID AWARD AND REGISTER CONTRCT | 2017-07-31 | 2017-12-22 | 2017-07-31 | 2017-12-22
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM17BVTV | BAYVIEW HOUSES SECURITY CAMERAS | 3 | CONSTRUCTION | 2017-12-23 | 2018-12-22 | 2017-12-23 | 2018-12-22
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM17BVTV | BAYVIEW HOUSES SECURITY CAMERAS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-12-23 | 2019-06-20 | 2017-12-23 | 2018-12-22
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM17BVTV | BAYVIEW HOUSES SECURITY CAMERAS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-12-23 | 2019-06-20 | 2018-12-23 | 2019-06-20
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM17BYTV | Berry Street Houses (NYCHA) -- CCTV phase 1 | 2 | BID AWARD AND REGISTER CONTRCT | 2017-07-31 | 2017-12-22 | 2017-07-31 | 2017-12-22
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM17BYTV | Berry Street Houses (NYCHA) -- CCTV phase 1 | 3 | CONSTRUCTION | 2017-12-23 | 2018-12-22 | 2017-12-23 | 2018-12-22
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM17BYTV | Berry Street Houses (NYCHA) -- CCTV phase 1 | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-12-23 | 2019-06-20 | 2017-12-23 | 2018-12-22
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM17BYTV | Berry Street Houses (NYCHA) -- CCTV phase 1 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-12-23 | 2019-06-20 | 2018-12-23 | 2019-06-20
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM17FASE | Farragut Security Enhancements | 1 | DESIGN | 2017-02-01 | 2017-07-30 | 2017-02-01 | 2017-07-30
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM17FASE | Farragut Security Enhancements | 2 | BID AWARD AND REGISTER CONTRCT | 2017-07-31 | 2017-12-22 | 2017-07-31 | 2017-12-22
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM17FASE | Farragut Security Enhancements | 3 | CONSTRUCTION | 2017-12-23 | 2018-12-22 | 2017-12-23 | 2018-12-22
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM17FASE | Farragut Security Enhancements | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-12-23 | 2019-06-20 | 2017-12-23 | 2018-12-22
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM17FASE | Farragut Security Enhancements | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-12-23 | 2019-06-20 | 2018-12-23 | 2019-06-20
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM17INSS | INDEPENDENCE TOWERS COMMUNITY CENTER SOUND STUDIO | 1 | DESIGN | 2017-02-01 | 2017-07-30 | 2017-02-01 | 2017-07-30
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM17INSS | INDEPENDENCE TOWERS COMMUNITY CENTER SOUND STUDIO | 2 | BID AWARD AND REGISTER CONTRCT | 2017-07-31 | 2017-12-22 | 2017-07-31 | 2017-12-22
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM17INSS | INDEPENDENCE TOWERS COMMUNITY CENTER SOUND STUDIO | 3 | CONSTRUCTION | 2017-12-23 | 2018-12-22 | 2017-12-23 | 2018-12-22
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM17INSS | INDEPENDENCE TOWERS COMMUNITY CENTER SOUND STUDIO | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-12-23 | 2019-06-20 | 2017-12-23 | 2018-12-22
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM17INSS | INDEPENDENCE TOWERS COMMUNITY CENTER SOUND STUDIO | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-12-23 | 2019-06-20 | 2018-12-23 | 2020-12-21
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM17NSTV | NOSTRAND HOUSES SECURITY CAMERAS | 1 | DESIGN | 2017-02-01 | 2017-07-30 | 2017-02-01 | 2017-07-30
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM17NSTV | NOSTRAND HOUSES SECURITY CAMERAS | 2 | BID AWARD AND REGISTER CONTRCT | 2017-07-31 | 2017-12-22 | 2017-07-31 | 2017-12-22
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM17NSTV | NOSTRAND HOUSES SECURITY CAMERAS | 3 | CONSTRUCTION | 2017-12-23 | 2018-12-22 | 2017-12-23 | 2018-12-22
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM17NSTV | NOSTRAND HOUSES SECURITY CAMERAS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-12-23 | 2019-06-20 | 2017-12-23 | 2018-12-22
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM17NSTV | NOSTRAND HOUSES SECURITY CAMERAS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-12-23 | 2019-06-20 | 2018-12-23 | 2020-12-21
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18ATBC | ATLANTIC TERMINAL BASKETBALL COURT RENOVATION | 1 | DESIGN | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18ATBC | ATLANTIC TERMINAL BASKETBALL COURT RENOVATION | 2 | BID AWARD AND REGISTER CONTRCT | 2017-12-28 | 2018-06-25 | 2017-12-28 | 2018-06-25
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18ATBC | ATLANTIC TERMINAL BASKETBALL COURT RENOVATION | 3 | CONSTRUCTION | 2018-06-26 | 2019-06-25 | 2018-06-26 | 2019-06-25
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18ATBC | ATLANTIC TERMINAL BASKETBALL COURT RENOVATION | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-06-26 | 2019-12-22 | 2018-06-26 | 2019-06-25
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18ATBC | ATLANTIC TERMINAL BASKETBALL COURT RENOVATION | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-06-26 | 2019-12-22 | 2019-06-26 | 2019-12-22
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18BPBC | BORINQUEN PLAZA I BASKETBALL COURT UPGRADE | 1 | DESIGN | 2018-01-02 | 2018-06-30 | 2018-01-02 | 2018-06-30
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18BPBC | BORINQUEN PLAZA I BASKETBALL COURT UPGRADE | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18BPBC | BORINQUEN PLAZA I BASKETBALL COURT UPGRADE | 3 | CONSTRUCTION | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18BPBC | BORINQUEN PLAZA I BASKETBALL COURT UPGRADE | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-28 | 2020-06-24 | 2018-12-28 | 2019-12-27
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18BPBC | BORINQUEN PLAZA I BASKETBALL COURT UPGRADE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-28 | 2020-06-24 | 2019-12-28 | 2020-06-24
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18BREV | Brevoort Resident Association - Coliseum Repairs and CCTVs | 1 | DESIGN | 2018-01-02 | 2018-06-30 | 2018-01-02 | 2018-06-30
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18BREV | Brevoort Resident Association - Coliseum Repairs and CCTVs | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18BREV | Brevoort Resident Association - Coliseum Repairs and CCTVs | 3 | CONSTRUCTION | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18BREV | Brevoort Resident Association - Coliseum Repairs and CCTVs | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-28 | 2020-06-24 | 2018-12-28 | 2019-12-27
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18BREV | Brevoort Resident Association - Coliseum Repairs and CCTVs | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-28 | 2020-06-24 | 2019-12-28 | 2020-06-24
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18BSVB | BROWNSVILLE AND SARATOGA VILLAGE BOILER REPAIR | 1 | DESIGN | 2018-02-05 | 2018-08-03 | 2018-02-05 | 2018-08-03
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18BSVB | BROWNSVILLE AND SARATOGA VILLAGE BOILER REPAIR | 2 | BID AWARD AND REGISTER CONTRCT | 2018-08-04 | 2019-01-30 | 2018-08-04 | 2019-01-30
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18BSVB | BROWNSVILLE AND SARATOGA VILLAGE BOILER REPAIR | 3 | CONSTRUCTION | 2019-01-31 | 2020-01-30 | 2019-01-31 | 2020-01-30
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18BSVB | BROWNSVILLE AND SARATOGA VILLAGE BOILER REPAIR | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-01-31 | 2020-07-28 | 2019-01-31 | 2020-01-30
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18BSVB | BROWNSVILLE AND SARATOGA VILLAGE BOILER REPAIR | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-01-31 | 2020-07-28 | 2020-01-31 | 2020-07-28
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CHBW | CYPRESS HILLS BOILER WORK | 1 | DESIGN | 2018-02-05 | 2018-08-03 | 2018-02-05 | 2018-08-03
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CHBW | CYPRESS HILLS BOILER WORK | 2 | BID AWARD AND REGISTER CONTRCT | 2018-08-04 | 2019-01-30 | 2018-08-04 | 2019-01-30
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CHBW | CYPRESS HILLS BOILER WORK | 3 | CONSTRUCTION | 2019-01-31 | 2020-01-30 | 2019-01-31 | 2020-01-30
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CHBW | CYPRESS HILLS BOILER WORK | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-01-31 | 2020-07-28 | 2019-01-31 | 2020-01-30
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CHBW | CYPRESS HILLS BOILER WORK | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-01-31 | 2020-07-28 | 2020-01-31 | 2020-07-28
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18FGSI | FARRAGUT HOUSES SECURITY CAMERAS | 1 | DESIGN | 2018-01-02 | 2018-06-30 | 2018-01-02 | 2018-06-30
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18FGSI | FARRAGUT HOUSES SECURITY CAMERAS | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18FGSI | FARRAGUT HOUSES SECURITY CAMERAS | 3 | CONSTRUCTION | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18FGSI | FARRAGUT HOUSES SECURITY CAMERAS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-28 | 2020-06-24 | 2018-12-28 | 2019-12-27
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18FGSI | FARRAGUT HOUSES SECURITY CAMERAS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-28 | 2020-06-24 | 2019-12-28 | 2020-06-24
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18HGCC | HOPE GARDENS COMMUNITY CENTER--MODERNIZE GYM. | 1 | DESIGN | 2018-01-02 | 2018-06-30 | 2018-01-02 | 2018-06-30
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18HGCC | HOPE GARDENS COMMUNITY CENTER--MODERNIZE GYM. | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18HGCC | HOPE GARDENS COMMUNITY CENTER--MODERNIZE GYM. | 3 | CONSTRUCTION | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18HGCC | HOPE GARDENS COMMUNITY CENTER--MODERNIZE GYM. | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-28 | 2020-06-24 | 2018-12-28 | 2019-12-27
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18HGCC | HOPE GARDENS COMMUNITY CENTER--MODERNIZE GYM. | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-28 | 2020-06-24 | 2019-12-28 | 2020-06-24
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18HYEL | HYLAN ELEVATORS | 1 | DESIGN | 2018-04-01 | 2018-09-27 | 2018-04-01 | 2018-09-27
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18HYEL | HYLAN ELEVATORS | 2 | BID AWARD AND REGISTER CONTRCT | 2018-09-28 | 2019-03-26 | 2018-09-28 | 2019-03-26
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18HYEL | HYLAN ELEVATORS | 3 | CONSTRUCTION | 2019-03-27 | 2020-03-25 | 2019-03-27 | 2020-03-25
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18HYEL | HYLAN ELEVATORS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-03-26 | 2020-09-21 | 2019-03-27 | 2020-03-25
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18HYEL | HYLAN ELEVATORS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-03-26 | 2020-09-21 | 2020-03-26 | 2020-09-21
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18IGIR | INGERSOLL GARDENS INSTALLATION OF IRRIGATION | 1 | DESIGN | 2018-04-01 | 2018-09-27 | 2018-04-01 | 2018-09-27
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18IGIR | INGERSOLL GARDENS INSTALLATION OF IRRIGATION | 2 | BID AWARD AND REGISTER CONTRCT | 2018-09-28 | 2019-03-26 | 2018-09-28 | 2019-03-26
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18IGIR | INGERSOLL GARDENS INSTALLATION OF IRRIGATION | 3 | CONSTRUCTION | 2019-03-27 | 2020-03-25 | 2019-03-27 | 2020-03-25
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18IGIR | INGERSOLL GARDENS INSTALLATION OF IRRIGATION | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-03-26 | 2020-09-21 | 2019-03-27 | 2020-03-25
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18IGIR | INGERSOLL GARDENS INSTALLATION OF IRRIGATION | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-03-26 | 2020-09-21 | 2020-03-26 | 2020-09-21
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18INBC | INGERSOLL HOUSES BASKETBALL COURT RENOVATIONS | 1 | DESIGN | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18INBC | INGERSOLL HOUSES BASKETBALL COURT RENOVATIONS | 2 | BID AWARD AND REGISTER CONTRCT | 2018-12-28 | 2019-06-25 | 2018-12-28 | 2019-06-25
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18INBC | INGERSOLL HOUSES BASKETBALL COURT RENOVATIONS | 3 | CONSTRUCTION | 2019-06-26 | 2020-06-24 | 2019-06-26 | 2020-06-24
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18INBC | INGERSOLL HOUSES BASKETBALL COURT RENOVATIONS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-06-25 | 2020-12-21 | 2019-06-26 | 2020-06-24
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18INBC | INGERSOLL HOUSES BASKETBALL COURT RENOVATIONS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-06-25 | 2020-12-21 | 2020-06-25 | 2020-12-21
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18ITPG | RENOVATION OF PLAYGROUND AT INDEPENDENCE TOWERS | 1 | DESIGN | 2018-07-01 | 2018-12-27 | 2017-07-24 | 2018-01-19
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18ITPG | RENOVATION OF PLAYGROUND AT INDEPENDENCE TOWERS | 2 | BID AWARD AND REGISTER CONTRCT | 2018-12-28 | 2019-06-25 | 2018-01-20 | 2018-07-18
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18ITPG | RENOVATION OF PLAYGROUND AT INDEPENDENCE TOWERS | 3 | CONSTRUCTION | 2019-06-26 | 2020-06-24 | 2018-07-19 | 2019-07-18
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18ITPG | RENOVATION OF PLAYGROUND AT INDEPENDENCE TOWERS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-06-25 | 2020-12-21 | 2018-07-19 | 2019-07-18
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18ITPG | RENOVATION OF PLAYGROUND AT INDEPENDENCE TOWERS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-06-25 | 2020-12-21 | 2019-07-19 | 2021-01-13
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18LFSU | LAFAYETTE HOUSES SECURITY UPGRADES | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18LFSU | LAFAYETTE HOUSES SECURITY UPGRADES | 3 | CONSTRUCTION | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18LFSU | LAFAYETTE HOUSES SECURITY UPGRADES | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-28 | 2020-06-24 | 2018-12-28 | 2019-12-27
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18LFSU | LAFAYETTE HOUSES SECURITY UPGRADES | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-28 | 2020-06-24 | 2019-12-28 | 2020-06-24
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18OHPG | OCEAN HILL PLAYGROUND | 1 | DESIGN | 2018-01-02 | 2018-06-30 | 2018-01-02 | 2018-06-30
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18OHPG | OCEAN HILL PLAYGROUND | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18OHPG | OCEAN HILL PLAYGROUND | 3 | CONSTRUCTION | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18OHPG | OCEAN HILL PLAYGROUND | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-28 | 2020-06-24 | 2018-12-28 | 2019-12-27
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18OHPG | OCEAN HILL PLAYGROUND | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-28 | 2020-06-24 | 2019-12-28 | 2020-06-24
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18PKTV | PINK CCTV | 1 | DESIGN | 2019-02-18 | 2019-08-16 | 2019-02-18 | 2019-08-16
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18PKTV | PINK CCTV | 2 | BID AWARD AND REGISTER CONTRCT | 2019-08-17 | 2020-02-12 | 2019-08-17 | 2020-02-12
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18PKTV | PINK CCTV | 3 | CONSTRUCTION | 2020-02-13 | 2021-02-11 | 2020-02-13 | 2021-02-11
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18PKTV | PINK CCTV | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-02-12 | 2021-08-10 | 2020-02-13 | 2021-02-11
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18PKTV | PINK CCTV | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-02-12 | 2021-08-10 | 2021-02-12 | 2021-08-10
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18SUBC | RENOVATION OF A BASKETBALL COURT AT SUMNER HOUSES | 1 | DESIGN | 2018-01-02 | 2018-06-30 | 2018-01-02 | 2018-06-30
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18SUBC | RENOVATION OF A BASKETBALL COURT AT SUMNER HOUSES | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18SUBC | RENOVATION OF A BASKETBALL COURT AT SUMNER HOUSES | 3 | CONSTRUCTION | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18SUBC | RENOVATION OF A BASKETBALL COURT AT SUMNER HOUSES | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-28 | 2020-06-24 | 2018-12-28 | 2019-12-27
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18SUBC | RENOVATION OF A BASKETBALL COURT AT SUMNER HOUSES | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-28 | 2020-06-24 | 2019-12-28 | 2020-06-24
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WBCC | PLAYGROUND UPGRADES AT WILLIAMSBURG DAY CARE CENTER | 1 | DESIGN | 2018-02-01 | 2018-07-30 | 2018-02-01 | 2018-07-30
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WBCC | PLAYGROUND UPGRADES AT WILLIAMSBURG DAY CARE CENTER | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-31 | 2019-01-26 | 2018-07-31 | 2019-01-26
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WBCC | PLAYGROUND UPGRADES AT WILLIAMSBURG DAY CARE CENTER | 3 | CONSTRUCTION | 2019-01-27 | 2020-01-26 | 2019-01-27 | 2020-01-26
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WBCC | PLAYGROUND UPGRADES AT WILLIAMSBURG DAY CARE CENTER | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-01-27 | 2020-07-24 | 2019-01-27 | 2020-01-26
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WBCC | PLAYGROUND UPGRADES AT WILLIAMSBURG DAY CARE CENTER | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-01-27 | 2020-07-24 | 2020-01-27 | 2020-07-24
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WHIT | NYCHA WHITMAN/WILLOUGHBY SENIOR CENTER HVAC UPGRADE | 1 | DESIGN | 2018-01-02 | 2018-06-30 | 2018-01-02 | 2018-06-30
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WHIT | NYCHA WHITMAN/WILLOUGHBY SENIOR CENTER HVAC UPGRADE | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WHIT | NYCHA WHITMAN/WILLOUGHBY SENIOR CENTER HVAC UPGRADE | 3 | CONSTRUCTION | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WHIT | NYCHA WHITMAN/WILLOUGHBY SENIOR CENTER HVAC UPGRADE | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-28 | 2020-06-24 | 2018-12-28 | 2019-12-27
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WHIT | NYCHA WHITMAN/WILLOUGHBY SENIOR CENTER HVAC UPGRADE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-28 | 2020-06-24 | 2019-12-28 | 2020-06-24
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WIPG | WILLIAMSBURG HOUSES PLAYGROUND UPGRADE | 1 | DESIGN | 2018-02-01 | 2018-07-30 | 2018-02-01 | 2018-07-30
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WIPG | WILLIAMSBURG HOUSES PLAYGROUND UPGRADE | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-31 | 2019-01-26 | 2018-07-31 | 2019-01-26
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WIPG | WILLIAMSBURG HOUSES PLAYGROUND UPGRADE | 3 | CONSTRUCTION | 2019-01-27 | 2020-01-26 | 2019-01-27 | 2020-01-26
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WIPG | WILLIAMSBURG HOUSES PLAYGROUND UPGRADE | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-01-27 | 2020-07-24 | 2019-01-27 | 2020-01-26
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WIPG | WILLIAMSBURG HOUSES PLAYGROUND UPGRADE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-01-27 | 2020-07-24 | 2020-01-27 | 2020-07-24
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WKCC | WYCKOFF GARDENS COMMUNITY CENTER RENOVATION | 1 | DESIGN | 2018-01-02 | 2018-06-30 | 2018-01-02 | 2018-06-30
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WKCC | WYCKOFF GARDENS COMMUNITY CENTER RENOVATION | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WKCC | WYCKOFF GARDENS COMMUNITY CENTER RENOVATION | 3 | CONSTRUCTION | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WKCC | WYCKOFF GARDENS COMMUNITY CENTER RENOVATION | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-28 | 2020-06-24 | 2018-12-28 | 2019-12-27
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WKCC | WYCKOFF GARDENS COMMUNITY CENTER RENOVATION | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-28 | 2020-06-24 | 2019-12-28 | 2020-06-24
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WKLG | WYCKOFF GARDENS LIGHTING | 1 | DESIGN | 2018-01-02 | 2018-06-30 | 2018-01-02 | 2018-06-30
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WKLG | WYCKOFF GARDENS LIGHTING | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WKLG | WYCKOFF GARDENS LIGHTING | 3 | CONSTRUCTION | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WKLG | WYCKOFF GARDENS LIGHTING | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-28 | 2020-06-24 | 2018-12-28 | 2019-12-27
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WKLG | WYCKOFF GARDENS LIGHTING | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-28 | 2020-06-24 | 2019-12-28 | 2020-06-24
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WSEC | WHITMAN BASKETBALL COURT AND SECURITY UPGRADES | 1 | DESIGN | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WSEC | WHITMAN BASKETBALL COURT AND SECURITY UPGRADES | 2 | BID AWARD AND REGISTER CONTRCT | 2018-12-28 | 2019-06-25 | 2018-12-28 | 2019-06-25
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WSEC | WHITMAN BASKETBALL COURT AND SECURITY UPGRADES | 3 | CONSTRUCTION | 2019-06-26 | 2020-06-24 | 2019-06-26 | 2020-06-24
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WSEC | WHITMAN BASKETBALL COURT AND SECURITY UPGRADES | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-06-25 | 2020-12-21 | 2019-06-26 | 2020-06-24
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WSEC | WHITMAN BASKETBALL COURT AND SECURITY UPGRADES | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-06-25 | 2020-12-21 | 2020-06-25 | 2020-12-21
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WSWT | WOODSON WATER TANK | 1 | DESIGN | 2018-10-15 | 2019-04-12 | 2018-10-15 | 2019-04-12
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WSWT | WOODSON WATER TANK | 2 | BID AWARD AND REGISTER CONTRCT | 2019-04-13 | 2019-10-09 | 2019-04-13 | 2019-10-09
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WSWT | WOODSON WATER TANK | 3 | CONSTRUCTION | 2019-10-10 | 2020-10-08 | 2019-10-10 | 2020-10-08
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WSWT | WOODSON WATER TANK | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-10-09 | 2021-04-06 | 2019-10-10 | 2020-10-08
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WSWT | WOODSON WATER TANK | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-10-09 | 2021-04-06 | 2020-10-09 | 2021-04-06
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19ALPL | ALBANY HOUSES PLAYGROUND | 1 | DESIGN | 2019-03-15 | 2019-09-10 | 2019-03-15 | 2019-09-10
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19ALPL | ALBANY HOUSES PLAYGROUND | 2 | BID AWARD AND REGISTER CONTRCT | 2019-09-11 | 2020-03-08 | 2019-09-11 | 2020-03-08
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19ALPL | ALBANY HOUSES PLAYGROUND | 3 | CONSTRUCTION | 2020-03-09 | 2021-03-08 | 2020-03-09 | 2021-03-08
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19ALPL | ALBANY HOUSES PLAYGROUND | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-09 | 2021-09-04 | 2020-03-09 | 2021-03-08
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19ALPL | ALBANY HOUSES PLAYGROUND | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-09 | 2021-09-04 | 2021-03-09 | 2021-09-04
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19BVPU | BAYVIEW HOUSES PLAYGROUND UPGRADE | 1 | DESIGN | 2019-03-15 | 2019-09-10 | 2019-03-15 | 2019-09-10
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19BVPU | BAYVIEW HOUSES PLAYGROUND UPGRADE | 2 | BID AWARD AND REGISTER CONTRCT | 2019-09-11 | 2020-03-08 | 2019-09-11 | 2020-03-08
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19BVPU | BAYVIEW HOUSES PLAYGROUND UPGRADE | 3 | CONSTRUCTION | 2020-03-09 | 2021-03-08 | 2020-03-09 | 2021-03-08
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19BVPU | BAYVIEW HOUSES PLAYGROUND UPGRADE | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-09 | 2021-09-04 | 2020-03-09 | 2021-03-08
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19BVPU | BAYVIEW HOUSES PLAYGROUND UPGRADE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-09 | 2021-09-04 | 2021-03-09 | 2021-09-04
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19CSVE | SARATOGA VILLAGE ELEVATORS | 1 | DESIGN | 2019-02-15 | 2019-08-13 | 2019-02-15 | 2019-08-13
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19CSVE | SARATOGA VILLAGE ELEVATORS | 2 | BID AWARD AND REGISTER CONTRCT | 2019-08-14 | 2020-02-09 | 2019-08-14 | 2020-02-09
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19CSVE | SARATOGA VILLAGE ELEVATORS | 3 | CONSTRUCTION | 2020-02-10 | 2021-02-08 | 2020-02-10 | 2021-02-08
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19CSVE | SARATOGA VILLAGE ELEVATORS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-02-09 | 2021-08-07 | 2020-02-10 | 2021-02-08
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19CSVE | SARATOGA VILLAGE ELEVATORS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-02-09 | 2021-08-07 | 2021-02-09 | 2021-08-07
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19FHSE | FARRAGUT HOUSES SECURITY LIGHTING | 1 | DESIGN | 2019-01-15 | 2019-07-13 | 2019-01-15 | 2019-07-13
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19FHSE | FARRAGUT HOUSES SECURITY LIGHTING | 2 | BID AWARD AND REGISTER CONTRCT | 2019-07-14 | 2020-01-09 | 2019-07-14 | 2020-01-09
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19FHSE | FARRAGUT HOUSES SECURITY LIGHTING | 3 | CONSTRUCTION | 2020-01-10 | 2021-01-08 | 2020-01-10 | 2021-01-08
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19FHSE | FARRAGUT HOUSES SECURITY LIGHTING | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-01-09 | 2021-07-07 | 2020-01-10 | 2021-01-08
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19FHSE | FARRAGUT HOUSES SECURITY LIGHTING | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-01-09 | 2021-07-07 | 2021-01-09 | 2021-07-07
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19HHTV | HOWARD HOUSES CCTV | 1 | DESIGN | 2019-02-25 | 2019-08-23 | 2019-02-25 | 2019-08-23
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19HHTV | HOWARD HOUSES CCTV | 2 | BID AWARD AND REGISTER CONTRCT | 2019-08-24 | 2020-02-19 | 2019-08-24 | 2020-02-19
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19HHTV | HOWARD HOUSES CCTV | 3 | CONSTRUCTION | 2020-02-20 | 2021-02-18 | 2020-02-20 | 2021-02-18
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19HHTV | HOWARD HOUSES CCTV | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-02-19 | 2021-08-17 | 2020-02-20 | 2021-02-18
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19HHTV | HOWARD HOUSES CCTV | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-02-19 | 2021-08-17 | 2021-02-19 | 2021-08-17
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19SBPU | SHEEPSHEAD BAY HOUSES PLAYGROUND UPGRADE | 1 | DESIGN | 2019-04-15 | 2019-10-16 | 2019-04-15 | 2019-10-16
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19SBPU | SHEEPSHEAD BAY HOUSES PLAYGROUND UPGRADE | 2 | BID AWARD AND REGISTER CONTRCT | 2019-10-17 | 2020-05-04 | 2019-10-17 | 2020-05-04
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19SBPU | SHEEPSHEAD BAY HOUSES PLAYGROUND UPGRADE | 3 | CONSTRUCTION | 2020-05-05 | 2021-11-10 | 2020-05-05 | 2021-11-10
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19SBPU | SHEEPSHEAD BAY HOUSES PLAYGROUND UPGRADE | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-11-11 | 2022-05-09 | 2020-05-05 | 2021-11-10
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19SBPU | SHEEPSHEAD BAY HOUSES PLAYGROUND UPGRADE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-11-11 | 2022-05-09 | 2021-11-11 | 2022-05-09
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19TCPU | TOMPKINS HOUSES CHILDRENS PARK UPGRADE | 1 | DESIGN | 2019-03-15 | 2019-09-10 | 2019-03-15 | 2019-09-10
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19TCPU | TOMPKINS HOUSES CHILDRENS PARK UPGRADE | 2 | BID AWARD AND REGISTER CONTRCT | 2019-09-11 | 2020-03-08 | 2019-09-11 | 2020-03-08
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19TCPU | TOMPKINS HOUSES CHILDRENS PARK UPGRADE | 3 | CONSTRUCTION | 2020-03-09 | 2021-03-08 | 2020-03-09 | 2021-03-08
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19TCPU | TOMPKINS HOUSES CHILDRENS PARK UPGRADE | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-09 | 2021-09-04 | 2020-03-09 | 2021-03-08
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19TCPU | TOMPKINS HOUSES CHILDRENS PARK UPGRADE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-09 | 2021-09-04 | 2021-03-09 | 2021-09-04
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19WPLF | WILLIAMS PLAZA LIGHTING AND FENCING IMPROVEMENTS | 1 | DESIGN | 2019-04-17 | 2019-10-13 | 2019-04-17 | 2019-10-13
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19WPLF | WILLIAMS PLAZA LIGHTING AND FENCING IMPROVEMENTS | 2 | BID AWARD AND REGISTER CONTRCT | 2019-10-14 | 2020-04-10 | 2019-10-14 | 2020-04-10
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19WPLF | WILLIAMS PLAZA LIGHTING AND FENCING IMPROVEMENTS | 3 | CONSTRUCTION | 2020-04-11 | 2021-04-10 | 2020-04-11 | 2021-04-10
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19WPLF | WILLIAMS PLAZA LIGHTING AND FENCING IMPROVEMENTS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-04-11 | 2021-10-07 | 2020-04-11 | 2021-04-10
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19WPLF | WILLIAMS PLAZA LIGHTING AND FENCING IMPROVEMENTS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-04-11 | 2021-10-07 | 2021-04-11 | 2021-10-07
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20ALPU | PLAYGROUND RENOVATION- ALBANY HOUSES | 1 | DESIGN | 2018-01-02 | 2018-06-30 | 2018-01-02 | 2018-06-30
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20ALPU | PLAYGROUND RENOVATION- ALBANY HOUSES | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20ALPU | PLAYGROUND RENOVATION- ALBANY HOUSES | 3 | CONSTRUCTION | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20ALPU | PLAYGROUND RENOVATION- ALBANY HOUSES | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-28 | 2020-06-24 | 2018-12-28 | 2019-12-27
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20ALPU | PLAYGROUND RENOVATION- ALBANY HOUSES | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-28 | 2020-06-24 | 2019-12-28 | 2020-06-24
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20BCCG | BUSHWICK HOUSES UPGRADE COMMUNITY CENTER GYM | 1 | DESIGN | 2019-09-01 | 2019-09-01 | 2019-09-01 | 2019-09-01
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20BCCG | BUSHWICK HOUSES UPGRADE COMMUNITY CENTER GYM | 2 | BID AWARD AND REGISTER CONTRCT | 2019-09-02 | 2020-02-28 | 2019-09-02 | 2020-02-28
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20BCCG | BUSHWICK HOUSES UPGRADE COMMUNITY CENTER GYM | 3 | CONSTRUCTION | 2020-02-29 | 2021-02-27 | 2020-02-29 | 2021-02-27
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20BCCG | BUSHWICK HOUSES UPGRADE COMMUNITY CENTER GYM | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-02-28 | 2021-08-26 | 2020-02-29 | 2021-02-27
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20BCCG | BUSHWICK HOUSES UPGRADE COMMUNITY CENTER GYM | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-02-28 | 2021-08-26 | 2021-02-28 | 2021-08-26
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20BCCS | RECORDING STUDIO- BUSHWICK HOUSES COMMUNITY CENTER | 1 | DESIGN | 2018-01-02 | 2018-06-30 | 2018-01-02 | 2018-06-30
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20BCCS | RECORDING STUDIO- BUSHWICK HOUSES COMMUNITY CENTER | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20BCCS | RECORDING STUDIO- BUSHWICK HOUSES COMMUNITY CENTER | 3 | CONSTRUCTION | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20BCCS | RECORDING STUDIO- BUSHWICK HOUSES COMMUNITY CENTER | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-28 | 2020-06-24 | 2018-12-28 | 2019-12-27
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20BCCS | RECORDING STUDIO- BUSHWICK HOUSES COMMUNITY CENTER | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-28 | 2020-06-24 | 2019-12-28 | 2020-06-24
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20BHPU | BREVOORT UPGRADES TO PLAYGROUND | 1 | DESIGN | 2019-09-01 | 2020-02-27 | 2019-09-01 | 2020-02-27
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20BHPU | BREVOORT UPGRADES TO PLAYGROUND | 2 | BID AWARD AND REGISTER CONTRCT | 2020-02-28 | 2020-08-25 | 2020-02-28 | 2020-08-25
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20BHPU | BREVOORT UPGRADES TO PLAYGROUND | 3 | CONSTRUCTION | 2020-08-26 | 2021-08-25 | 2020-08-26 | 2021-08-25
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20BHPU | BREVOORT UPGRADES TO PLAYGROUND | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-08-26 | 2022-02-21 | 2020-08-26 | 2021-08-25
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20BHPU | BREVOORT UPGRADES TO PLAYGROUND | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-08-26 | 2022-02-21 | 2021-08-26 | 2022-02-21
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20BVBG | BROWNSVILLE BOXING GYM | 1 | DESIGN | 2019-09-01 | 2020-02-27 | 2019-09-01 | 2020-02-27
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20BVBG | BROWNSVILLE BOXING GYM | 2 | BID AWARD AND REGISTER CONTRCT | 2020-02-28 | 2020-08-25 | 2020-02-28 | 2020-08-25
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20BVBG | BROWNSVILLE BOXING GYM | 3 | CONSTRUCTION | 2020-08-26 | 2021-08-25 | 2020-08-26 | 2021-08-25
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20BVBG | BROWNSVILLE BOXING GYM | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-08-26 | 2022-02-21 | 2020-08-26 | 2021-08-25
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20BVBG | BROWNSVILLE BOXING GYM | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-08-26 | 2022-02-21 | 2021-08-26 | 2022-02-21
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20BVCC | BROWNSVILLE COMMUNITY CENTER | 1 | DESIGN | 2019-09-01 | 2020-02-27 | 2019-09-01 | 2020-02-27
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20BVCC | BROWNSVILLE COMMUNITY CENTER | 2 | BID AWARD AND REGISTER CONTRCT | 2020-02-28 | 2020-08-25 | 2020-02-28 | 2020-08-25
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20BVCC | BROWNSVILLE COMMUNITY CENTER | 3 | CONSTRUCTION | 2020-08-26 | 2021-08-25 | 2020-08-26 | 2021-08-25
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20BVCC | BROWNSVILLE COMMUNITY CENTER | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-08-26 | 2022-02-21 | 2020-08-26 | 2021-08-25
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20BVCC | BROWNSVILLE COMMUNITY CENTER | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-08-26 | 2022-02-21 | 2021-08-26 | 2022-02-21
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20BVPL | BAYVIEW HOUSES PLAYGROUND UPGRADE | 1 | DESIGN | 2019-09-01 | 2020-02-27 | 2019-09-01 | 2020-02-27
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20BVPL | BAYVIEW HOUSES PLAYGROUND UPGRADE | 2 | BID AWARD AND REGISTER CONTRCT | 2020-02-28 | 2020-08-25 | 2020-02-28 | 2020-08-25
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20BVPL | BAYVIEW HOUSES PLAYGROUND UPGRADE | 3 | CONSTRUCTION | 2020-08-26 | 2021-08-25 | 2020-08-26 | 2021-08-25
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20BVPL | BAYVIEW HOUSES PLAYGROUND UPGRADE | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-08-26 | 2022-02-21 | 2020-08-26 | 2021-08-25
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20BVPL | BAYVIEW HOUSES PLAYGROUND UPGRADE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-08-26 | 2022-02-21 | 2021-08-26 | 2022-02-21
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20CPPU | COOPER PARK PLAY GROUND UPGRADE | 1 | DESIGN | 2019-09-01 | 2020-02-27 | 2019-09-01 | 2020-02-27
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20CPPU | COOPER PARK PLAY GROUND UPGRADE | 2 | BID AWARD AND REGISTER CONTRCT | 2020-02-28 | 2020-08-25 | 2020-02-28 | 2020-08-25
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20CPPU | COOPER PARK PLAY GROUND UPGRADE | 3 | CONSTRUCTION | 2020-08-26 | 2021-08-25 | 2020-08-26 | 2021-08-25
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20CPPU | COOPER PARK PLAY GROUND UPGRADE | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-08-26 | 2022-02-21 | 2020-08-26 | 2021-08-25
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20CPPU | COOPER PARK PLAY GROUND UPGRADE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-08-26 | 2022-02-21 | 2021-08-26 | 2022-02-21
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20GCBR | GLENWOOD COMMUNITY CENTER RENOVATE BATHROOM | 1 | DESIGN | 2019-09-01 | 2020-02-27 | 2019-09-01 | 2020-02-27
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20GCBR | GLENWOOD COMMUNITY CENTER RENOVATE BATHROOM | 2 | BID AWARD AND REGISTER CONTRCT | 2020-02-28 | 2020-08-25 | 2020-02-28 | 2020-08-25
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20GCBR | GLENWOOD COMMUNITY CENTER RENOVATE BATHROOM | 3 | CONSTRUCTION | 2020-08-26 | 2021-08-25 | 2020-08-26 | 2021-08-25
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20GCBR | GLENWOOD COMMUNITY CENTER RENOVATE BATHROOM | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-08-26 | 2022-02-21 | 2020-08-26 | 2021-08-25
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20GCBR | GLENWOOD COMMUNITY CENTER RENOVATE BATHROOM | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-08-26 | 2022-02-21 | 2021-08-26 | 2022-02-21
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20GHLC | LED LIGHTING AND CAMERAS GOWANUS HOUSES | 1 | DESIGN | 2019-09-01 | 2020-02-27 | 2019-09-01 | 2020-02-27
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20GHLC | LED LIGHTING AND CAMERAS GOWANUS HOUSES | 2 | BID AWARD AND REGISTER CONTRCT | 2020-02-28 | 2020-08-25 | 2020-02-28 | 2020-08-25
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20GHLC | LED LIGHTING AND CAMERAS GOWANUS HOUSES | 3 | CONSTRUCTION | 2020-08-26 | 2021-08-25 | 2020-08-26 | 2021-08-25
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20GHLC | LED LIGHTING AND CAMERAS GOWANUS HOUSES | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-08-26 | 2022-02-21 | 2020-08-26 | 2021-08-25
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20GHLC | LED LIGHTING AND CAMERAS GOWANUS HOUSES | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-08-26 | 2022-02-21 | 2021-08-26 | 2022-02-21
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20HCAM | PHASE 2 CAMERAS AT LANGSTON HUGES HOUSES | 1 | DEVELOP SCOPE | 2019-09-01 | 2019-11-29 | 2019-09-01 | 2019-11-29
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20HCAM | PHASE 2 CAMERAS AT LANGSTON HUGES HOUSES | 2 | PRELIMINARY DESIGN | 2019-11-30 | 2020-03-28 | 2019-11-30 | 2020-03-28
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20HCAM | PHASE 2 CAMERAS AT LANGSTON HUGES HOUSES | 3 | FINAL DESIGN | 2020-03-29 | 2020-09-24 | 2020-03-29 | 2020-09-24
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20HCAM | PHASE 2 CAMERAS AT LANGSTON HUGES HOUSES | 4 | BID AWARD AND REGISTER CONTRCT | 2020-09-25 | 2020-12-23 | 2020-09-25 | 2020-12-23
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20HCAM | PHASE 2 CAMERAS AT LANGSTON HUGES HOUSES | 5 | CONSTRUCTION TO 25% | 2020-12-24 | 2021-04-22 | 2020-12-24 | 2021-04-22
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20HCAM | PHASE 2 CAMERAS AT LANGSTON HUGES HOUSES | 6 | CONSTRUCTION TO 50% | 2021-04-23 | 2021-08-20 | 2021-04-23 | 2021-08-20
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20HCAM | PHASE 2 CAMERAS AT LANGSTON HUGES HOUSES | 7 | CONSTRUCTION TO 75% | 2021-08-21 | 2021-12-18 | 2021-08-21 | 2021-12-18
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20HCAM | PHASE 2 CAMERAS AT LANGSTON HUGES HOUSES | 8 | ORIGINAL EQUIP & FURNISHING | 2021-12-19 | 2022-03-18 | 2021-12-19 | 2022-03-18
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20HCAM | PHASE 2 CAMERAS AT LANGSTON HUGES HOUSES | 9 | SUBSTANTIAL COMPLETION | 2022-03-19 | 2022-05-17 | 2022-03-19 | 2022-05-17
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20HCAM | PHASE 2 CAMERAS AT LANGSTON HUGES HOUSES | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-05-18 | 2022-06-16 | 2022-05-18 | 2022-06-16
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20KRWJ | KINGSBOROUGH DEVELOPMENT RESTORATION OF WALLS OF JERICHO | 1 | DEVELOP SCOPE | 2019-09-01 | 2019-11-29 | 2019-09-01 | 2019-11-29
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20KRWJ | KINGSBOROUGH DEVELOPMENT RESTORATION OF WALLS OF JERICHO | 2 | PRELIMINARY DESIGN | 2019-11-30 | 2020-03-28 | 2019-11-30 | 2020-03-28
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20KRWJ | KINGSBOROUGH DEVELOPMENT RESTORATION OF WALLS OF JERICHO | 3 | FINAL DESIGN | 2020-03-29 | 2020-09-24 | 2020-03-29 | 2020-09-24
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20KRWJ | KINGSBOROUGH DEVELOPMENT RESTORATION OF WALLS OF JERICHO | 4 | BID AWARD AND REGISTER CONTRCT | 2020-09-25 | 2020-12-23 | 2020-09-25 | 2020-12-23
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20KRWJ | KINGSBOROUGH DEVELOPMENT RESTORATION OF WALLS OF JERICHO | 5 | CONSTRUCTION TO 25% | 2020-12-24 | 2021-04-22 | 2020-12-24 | 2021-04-22
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20KRWJ | KINGSBOROUGH DEVELOPMENT RESTORATION OF WALLS OF JERICHO | 6 | CONSTRUCTION TO 50% | 2021-04-23 | 2021-08-20 | 2021-04-23 | 2021-08-20
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20KRWJ | KINGSBOROUGH DEVELOPMENT RESTORATION OF WALLS OF JERICHO | 7 | CONSTRUCTION TO 75% | 2021-08-21 | 2021-12-18 | 2021-08-21 | 2021-12-18
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20KRWJ | KINGSBOROUGH DEVELOPMENT RESTORATION OF WALLS OF JERICHO | 8 | ORIGINAL EQUIP & FURNISHING | 2021-12-19 | 2022-03-18 | 2021-12-19 | 2022-03-18
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20KRWJ | KINGSBOROUGH DEVELOPMENT RESTORATION OF WALLS OF JERICHO | 9 | SUBSTANTIAL COMPLETION | 2022-03-19 | 2022-05-17 | 2022-03-19 | 2022-05-17
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20KRWJ | KINGSBOROUGH DEVELOPMENT RESTORATION OF WALLS OF JERICHO | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-05-18 | 2022-06-16 | 2022-05-18 | 2022-06-16
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20MGSC | SECURITY CAMERAS MARCUS GARVEY | 1 | DESIGN | 2019-09-01 | 2020-02-27 | 2019-09-01 | 2020-02-27
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20MGSC | SECURITY CAMERAS MARCUS GARVEY | 2 | BID AWARD AND REGISTER CONTRCT | 2020-02-28 | 2020-08-25 | 2020-02-28 | 2020-08-25
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20MGSC | SECURITY CAMERAS MARCUS GARVEY | 3 | CONSTRUCTION | 2020-08-26 | 2021-08-25 | 2020-08-26 | 2021-08-25
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20MGSC | SECURITY CAMERAS MARCUS GARVEY | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-08-26 | 2022-02-21 | 2020-08-26 | 2021-08-25
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20MGSC | SECURITY CAMERAS MARCUS GARVEY | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-08-26 | 2022-02-21 | 2021-08-26 | 2022-02-21
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20SHEL | SHEEPSHEAD HOUSES-EXTERIOR LIGHTING UPGRADE | 1 | DESIGN | 2019-09-01 | 2020-02-27 | 2019-09-01 | 2020-02-27
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20SHEL | SHEEPSHEAD HOUSES-EXTERIOR LIGHTING UPGRADE | 2 | BID AWARD AND REGISTER CONTRCT | 2020-02-28 | 2020-08-25 | 2020-02-28 | 2020-08-25
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20SHEL | SHEEPSHEAD HOUSES-EXTERIOR LIGHTING UPGRADE | 3 | CONSTRUCTION | 2020-08-26 | 2021-08-25 | 2020-08-26 | 2021-08-25
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20SHEL | SHEEPSHEAD HOUSES-EXTERIOR LIGHTING UPGRADE | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-08-26 | 2022-02-21 | 2020-08-26 | 2021-08-25
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20SHEL | SHEEPSHEAD HOUSES-EXTERIOR LIGHTING UPGRADE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-08-26 | 2022-02-21 | 2021-08-26 | 2022-02-21
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20TCCU | TOMPKINS - UPGRADE THE SPACE IN THE COMMUNITY CENTER | 1 | DESIGN | 2019-09-01 | 2020-02-27 | 2019-09-01 | 2020-02-27
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20TCCU | TOMPKINS - UPGRADE THE SPACE IN THE COMMUNITY CENTER | 2 | BID AWARD AND REGISTER CONTRCT | 2020-02-28 | 2020-08-25 | 2020-02-28 | 2020-08-25
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20TCCU | TOMPKINS - UPGRADE THE SPACE IN THE COMMUNITY CENTER | 3 | CONSTRUCTION | 2020-08-26 | 2021-08-25 | 2020-08-26 | 2021-08-25
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20TCCU | TOMPKINS - UPGRADE THE SPACE IN THE COMMUNITY CENTER | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-08-26 | 2022-02-21 | 2020-08-26 | 2021-08-25
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20TCCU | TOMPKINS - UPGRADE THE SPACE IN THE COMMUNITY CENTER | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-08-26 | 2022-02-21 | 2021-08-26 | 2022-02-21
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20THRR | TOMPKINS HOUSES ROOF REPLACEMENT | 1 | DESIGN | 2019-09-01 | 2020-02-27 | 2019-09-01 | 2020-02-27
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20THRR | TOMPKINS HOUSES ROOF REPLACEMENT | 2 | BID AWARD AND REGISTER CONTRCT | 2020-02-28 | 2020-08-25 | 2020-02-28 | 2020-08-25
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20THRR | TOMPKINS HOUSES ROOF REPLACEMENT | 3 | CONSTRUCTION | 2020-08-26 | 2021-08-25 | 2020-08-26 | 2021-08-25
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20THRR | TOMPKINS HOUSES ROOF REPLACEMENT | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-08-26 | 2022-02-21 | 2020-08-26 | 2021-08-25
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20THRR | TOMPKINS HOUSES ROOF REPLACEMENT | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-08-26 | 2022-02-21 | 2021-08-26 | 2022-02-21
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20VDCC | VAN DYKE 1 HOUSES COMPUTERS FOR NEW DAY CARE CENTER | 1 | DESIGN | 2019-09-01 | 2020-02-27 | 2019-09-01 | 2020-02-27
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20VDCC | VAN DYKE 1 HOUSES COMPUTERS FOR NEW DAY CARE CENTER | 2 | BID AWARD AND REGISTER CONTRCT | 2020-02-28 | 2020-08-25 | 2020-02-28 | 2020-08-25
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20VDCC | VAN DYKE 1 HOUSES COMPUTERS FOR NEW DAY CARE CENTER | 3 | CONSTRUCTION | 2020-08-26 | 2021-08-25 | 2020-08-26 | 2021-08-25
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20VDCC | VAN DYKE 1 HOUSES COMPUTERS FOR NEW DAY CARE CENTER | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-08-26 | 2022-02-21 | 2020-08-26 | 2021-08-25
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20VDCC | VAN DYKE 1 HOUSES COMPUTERS FOR NEW DAY CARE CENTER | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-08-26 | 2022-02-21 | 2021-08-26 | 2022-02-21
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20WHPU | WILLIAMSBURG - PLAYGROUND UPGRADE | 1 | DESIGN | 2019-09-01 | 2020-02-27 | 2019-09-01 | 2020-02-27
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20WHPU | WILLIAMSBURG - PLAYGROUND UPGRADE | 2 | BID AWARD AND REGISTER CONTRCT | 2020-02-28 | 2020-08-25 | 2020-02-28 | 2020-08-25
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20WHPU | WILLIAMSBURG - PLAYGROUND UPGRADE | 3 | CONSTRUCTION | 2020-08-26 | 2021-08-25 | 2020-08-26 | 2021-08-25
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20WHPU | WILLIAMSBURG - PLAYGROUND UPGRADE | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-08-26 | 2022-02-21 | 2020-08-26 | 2021-08-25
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20WHPU | WILLIAMSBURG - PLAYGROUND UPGRADE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-08-26 | 2022-02-21 | 2021-08-26 | 2022-02-21
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20WRCS | WYCKOFF GARDENS - RENOVATION OF COMMUNITY SPACE | 1 | DESIGN | 2019-09-01 | 2020-02-27 | 2019-09-01 | 2020-02-27
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20WRCS | WYCKOFF GARDENS - RENOVATION OF COMMUNITY SPACE | 2 | BID AWARD AND REGISTER CONTRCT | 2020-02-28 | 2020-08-25 | 2020-02-28 | 2020-08-25
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20WRCS | WYCKOFF GARDENS - RENOVATION OF COMMUNITY SPACE | 3 | CONSTRUCTION | 2020-08-26 | 2021-08-25 | 2020-08-26 | 2021-08-25
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20WRCS | WYCKOFF GARDENS - RENOVATION OF COMMUNITY SPACE | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-08-26 | 2022-02-21 | 2020-08-26 | 2021-08-25
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20WRCS | WYCKOFF GARDENS - RENOVATION OF COMMUNITY SPACE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-08-26 | 2022-02-21 | 2021-08-26 | 2022-02-21
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM24VDGR | VAN DYKE I, II GAS RISERS #10 | 1 | DESIGN | 2023-07-01 | 2024-06-30 | 2023-07-01 | 2024-06-30
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM24VDGR | VAN DYKE I, II GAS RISERS #10 | 2 | BID AWARD AND REGISTER CONTRCT | 2024-07-01 | 2024-11-23 | 2024-07-01 | 2024-11-23
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM24VDGR | VAN DYKE I, II GAS RISERS #10 | 3 | CONSTRUCTION | 2024-11-24 | 2026-06-16 | 2024-11-24 | 2026-06-16
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM24VDGR | VAN DYKE I, II GAS RISERS #10 | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2026-06-17 | 2026-09-15 | 2024-11-24 | 2026-06-16
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM24VDGR | VAN DYKE I, II GAS RISERS #10 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2026-06-17 | 2026-09-15 | 2026-06-17 | 2026-09-15
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-FIOPL | NDF - Fiorentino Plaza Playground Improvements | 4 | ORIGINAL EQUIP & FURNISHING | 2016-09-09 | 2016-09-18 | 2016-09-09 | 2016-09-18
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-FIOPL | NDF - Fiorentino Plaza Playground Improvements | 5 | SUBSTANTIAL COMPLETION | 2016-09-19 | 2016-10-03 | 2016-09-19 | 2016-10-03
20201123 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-FIOPL | NDF - Fiorentino Plaza Playground Improvements | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-10-04 | 2016-10-08 | 2016-10-04 | 2016-10-08
20201123 | BROOKLYN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82BRNHC | Brownsville Health Center Renovation of interior space | 1 | DESIGN | 2020-01-01 | 2021-05-24 | 2025-06-01 | 2027-06-30
20201123 | BROOKLYN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82BRNHC | Brownsville Health Center Renovation of interior space | 2 | CONSTRUCTION | 2021-05-25 | 2026-05-23 | 2027-07-01 | 2030-02-28
20201123 | BROOKLYN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82BRNHC | Brownsville Health Center Renovation of interior space | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2026-05-24 | 2026-05-23 | 2030-03-01 | 2030-08-27
20201123 | BROOKLYN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82BRNHC | Brownsville Health Center Renovation of interior space | 4 | DEVELOP SCOPE | 2026-05-24 | 2026-05-23 | 2030-03-01 | 2030-08-27
20201123 | BROOKLYN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82BRNHC | Brownsville Health Center Renovation of interior space | 5 | PRELIMINARY DESIGN | 2026-05-24 | 2026-05-23 | 2030-03-01 | 2030-08-27
20201123 | BROOKLYN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82BRNHC | Brownsville Health Center Renovation of interior space | 6 | FINAL DESIGN | 2026-05-24 | 2026-05-23 | 2030-03-01 | 2030-08-27
20201123 | BROOKLYN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82BRNHC | Brownsville Health Center Renovation of interior space | 7 | BID AWARD AND REGISTER CONTRCT | 2026-05-24 | 2026-05-23 | 2030-03-01 | 2030-08-27
20201123 | BROOKLYN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82BRNHC | Brownsville Health Center Renovation of interior space | 8 | CONSTRUCTION TO 25% | 2026-05-24 | 2026-05-23 | 2030-03-01 | 2030-08-27
20201123 | BROOKLYN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82BRNHC | Brownsville Health Center Renovation of interior space | 9 | CONSTRUCTION TO 50% | 2026-05-24 | 2026-05-23 | 2030-03-01 | 2030-08-27
20201123 | BROOKLYN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82BRNHC | Brownsville Health Center Renovation of interior space | 10 | CONSTRUCTION TO 75% | 2026-05-24 | 2026-05-23 | 2030-03-01 | 2030-08-27
20201123 | BROOKLYN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82BRNHC | Brownsville Health Center Renovation of interior space | 11 | ORIGINAL EQUIP & FURNISHING | 2026-05-24 | 2026-05-23 | 2030-03-01 | 2030-08-27
20201123 | BROOKLYN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82BRNHC | Brownsville Health Center Renovation of interior space | 12 | SUBSTANTIAL COMPLETION | 2026-05-24 | 2026-05-23 | 2030-03-01 | 2030-08-27
20201123 | BROOKLYN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82BRNHC | Brownsville Health Center Renovation of interior space | 13 | PUNCHLIST COMPLETE, JOB CLOSED | 2026-05-24 | 2026-06-22 | 2030-03-01 | 2030-08-27
20201123 | BROOKLYN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82BUSHC | Bushwick Health Center exterior renovation/interior upgrades | 1 | DESIGN | 2016-01-01 | 2017-05-24 | 2022-01-07 | 2022-04-06
20201123 | BROOKLYN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82BUSHC | Bushwick Health Center exterior renovation/interior upgrades | 2 | CONSTRUCTION | 2017-05-25 | 2022-05-23 | 2022-04-07 | 2022-08-04
20201123 | BROOKLYN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82BUSHC | Bushwick Health Center exterior renovation/interior upgrades | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-05-24 | 2022-05-23 | 2022-08-05 | 2023-01-31
20201123 | BROOKLYN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82BUSHC | Bushwick Health Center exterior renovation/interior upgrades | 4 | DEVELOP SCOPE | 2022-05-24 | 2022-05-23 | 2023-02-01 | 2023-05-01
20201123 | BROOKLYN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82BUSHC | Bushwick Health Center exterior renovation/interior upgrades | 5 | PRELIMINARY DESIGN | 2022-05-24 | 2022-05-23 | 2023-05-02 | 2023-08-29
20201123 | BROOKLYN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82BUSHC | Bushwick Health Center exterior renovation/interior upgrades | 6 | FINAL DESIGN | 2022-05-24 | 2022-05-23 | 2023-08-30 | 2023-12-27
20201123 | BROOKLYN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82BUSHC | Bushwick Health Center exterior renovation/interior upgrades | 7 | BID AWARD AND REGISTER CONTRCT | 2022-05-24 | 2022-05-23 | 2023-12-28 | 2024-04-25
20201123 | BROOKLYN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82BUSHC | Bushwick Health Center exterior renovation/interior upgrades | 8 | CONSTRUCTION TO 25% | 2022-05-24 | 2022-05-23 | 2024-04-26 | 2024-07-24
20201123 | BROOKLYN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82BUSHC | Bushwick Health Center exterior renovation/interior upgrades | 9 | CONSTRUCTION TO 50% | 2022-05-24 | 2022-05-23 | 2024-07-25 | 2024-09-22
20201123 | BROOKLYN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82BUSHC | Bushwick Health Center exterior renovation/interior upgrades | 10 | CONSTRUCTION TO 75% | 2022-05-24 | 2022-05-23 | 2024-09-23 | 2024-10-22
20201123 | BROOKLYN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82BUSHC | Bushwick Health Center exterior renovation/interior upgrades | 11 | ORIGINAL EQUIP & FURNISHING | 2022-05-24 | 2022-05-23 | 2024-09-23 | 2024-10-22
20201123 | BROOKLYN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82BUSHC | Bushwick Health Center exterior renovation/interior upgrades | 12 | SUBSTANTIAL COMPLETION | 2022-05-24 | 2022-05-23 | 2024-09-23 | 2024-10-22
20201123 | BROOKLYN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82BUSHC | Bushwick Health Center exterior renovation/interior upgrades | 13 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-05-24 | 2022-06-22 | 2024-09-23 | 2024-10-22
20201123 | BROOKLYN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82CROWH | CROWN HEIGHTS EXPRESS CLINIC | 1 | DESIGN | 2020-09-15 | 2021-03-13 | 2020-09-15 | 2021-03-13
20201123 | BROOKLYN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82CROWH | CROWN HEIGHTS EXPRESS CLINIC | 2 | CONSTRUCTION | 2021-03-14 | 2021-09-09 | 2021-03-14 | 2021-09-09
20201123 | BROOKLYN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82WLSHC | Williamsburg Health Center Interior Renovation | 1 | DESIGN | 2020-01-01 | 2021-05-24 | 2017-08-14 | 2017-11-11
20201123 | BROOKLYN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82WLSHC | Williamsburg Health Center Interior Renovation | 2 | CONSTRUCTION | 2021-05-25 | 2026-05-23 | 2017-11-12 | 2018-03-11
20201123 | BROOKLYN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82WLSHC | Williamsburg Health Center Interior Renovation | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2026-05-24 | 2026-05-23 | 2018-03-12 | 2018-09-07
20201123 | BROOKLYN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82WLSHC | Williamsburg Health Center Interior Renovation | 4 | DEVELOP SCOPE | 2026-05-24 | 2026-05-23 | 2018-09-08 | 2018-12-06
20201123 | BROOKLYN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82WLSHC | Williamsburg Health Center Interior Renovation | 5 | PRELIMINARY DESIGN | 2026-05-24 | 2026-05-23 | 2018-12-07 | 2019-04-05
20201123 | BROOKLYN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82WLSHC | Williamsburg Health Center Interior Renovation | 6 | FINAL DESIGN | 2026-05-24 | 2026-05-23 | 2019-04-06 | 2019-08-03
20201123 | BROOKLYN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82WLSHC | Williamsburg Health Center Interior Renovation | 7 | BID AWARD AND REGISTER CONTRCT | 2026-05-24 | 2026-05-23 | 2019-08-04 | 2019-12-01
20201123 | BROOKLYN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82WLSHC | Williamsburg Health Center Interior Renovation | 8 | CONSTRUCTION TO 25% | 2026-05-24 | 2026-05-23 | 2019-12-02 | 2020-02-29
20201123 | BROOKLYN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82WLSHC | Williamsburg Health Center Interior Renovation | 9 | CONSTRUCTION TO 50% | 2026-05-24 | 2026-05-23 | 2020-03-01 | 2020-04-29
20201123 | BROOKLYN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82WLSHC | Williamsburg Health Center Interior Renovation | 10 | CONSTRUCTION TO 75% | 2026-05-24 | 2026-05-23 | 2020-04-30 | 2024-05-29
20201123 | BROOKLYN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82WLSHC | Williamsburg Health Center Interior Renovation | 11 | ORIGINAL EQUIP & FURNISHING | 2026-05-24 | 2026-05-23 | 2020-04-30 | 2024-05-29
20201123 | BROOKLYN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82WLSHC | Williamsburg Health Center Interior Renovation | 12 | SUBSTANTIAL COMPLETION | 2026-05-24 | 2026-05-23 | 2020-04-30 | 2024-05-29
20201123 | BROOKLYN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82WLSHC | Williamsburg Health Center Interior Renovation | 13 | PUNCHLIST COMPLETE, JOB CLOSED | 2026-05-24 | 2026-06-22 | 2020-04-30 | 2024-05-29
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 22200601 | ENY: CAPITAL IMPROVEMENTS | 1 | DESIGN | 2008-01-03 | 2009-01-01 | 2008-01-03 | 2009-01-01
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 22200601 | ENY: CAPITAL IMPROVEMENTS | 2 | CONSTRUCTION | 2009-01-02 | 2012-01-01 | 2009-01-02 | 2021-01-01
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 22200601 | ENY: CAPITAL IMPROVEMENTS | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-01-02 | 2012-03-31 | 2021-01-02 | 2021-04-01
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 22200801 | EAST NEW YORK: RENOVATE THIRD FLOOR CLINICAL AREAS | 1 | DESIGN | 2008-08-10 | 2009-06-30 | 2009-09-09 | 2010-07-30
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 22200801 | EAST NEW YORK: RENOVATE THIRD FLOOR CLINICAL AREAS | 2 | CONSTRUCTION | 2009-07-01 | 2010-06-30 | 2009-09-09 | 2010-07-30
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 22200801 | EAST NEW YORK: RENOVATE THIRD FLOOR CLINICAL AREAS | 3 | CONSTRUCTION | 2009-07-01 | 2010-06-30 | 2010-07-31 | 2021-07-30
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 22201610 | RENOVATE BROWNSVILLE CHILD HEALTH CLINIC | 1 | DESIGN | 2017-08-10 | 2018-06-30 | 2017-08-10 | 2018-06-30
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 22201610 | RENOVATE BROWNSVILLE CHILD HEALTH CLINIC | 2 | CONSTRUCTION | 2018-07-01 | 2019-06-30 | 2017-08-10 | 2018-06-30
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 22201610 | RENOVATE BROWNSVILLE CHILD HEALTH CLINIC | 3 | CONSTRUCTION | 2018-07-01 | 2019-06-30 | 2018-07-01 | 2022-06-30
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 22201611 | RENOVATE CROWN HEIGHTS CHILD HEALTH CLINIC | 1 | DESIGN | 2015-12-07 | 2016-06-03 | 2015-12-07 | 2016-06-03
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 22201611 | RENOVATE CROWN HEIGHTS CHILD HEALTH CLINIC | 2 | CONSTRUCTION | 2016-06-04 | 2016-11-30 | 2016-06-04 | 2016-11-30
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 22201611 | RENOVATE CROWN HEIGHTS CHILD HEALTH CLINIC | 3 | DESIGN | 2016-06-04 | 2016-11-30 | 2016-12-01 | 2018-04-24
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 22201611 | RENOVATE CROWN HEIGHTS CHILD HEALTH CLINIC | 4 | CONSTRUCTION | 2016-06-04 | 2016-11-30 | 2018-04-25 | 2021-07-30
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 22201611 | RENOVATE CROWN HEIGHTS CHILD HEALTH CLINIC | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-06-04 | 2016-11-30 | 2021-07-31 | 2021-10-28
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 22201901 | ENY: MODERNIZE 2 PASSENGER ELEVATORS | 1 | DESIGN | 2019-07-07 | 2020-01-02 | 2019-07-07 | 2020-01-02
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 22201901 | ENY: MODERNIZE 2 PASSENGER ELEVATORS | 2 | CONSTRUCTION | 2020-01-03 | 2020-06-30 | 2020-01-03 | 2022-06-30
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 22202001 | ENY WATER SYSTEM STRUCTURAL RESTORATION | 1 | DESIGN | 2020-04-20 | 2021-09-11 | 2020-04-20 | 2021-09-11
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 22202001 | ENY WATER SYSTEM STRUCTURAL RESTORATION | 2 | CONSTRUCTION | 2021-09-12 | 2023-09-11 | 2021-09-12 | 2023-09-11
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 22202001 | ENY WATER SYSTEM STRUCTURAL RESTORATION | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-12 | 2023-12-10 | 2023-09-12 | 2023-12-10
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 23201601 | DSSM: ROOF REPLACEMENT | 1 | DESIGN | 2019-12-07 | 2020-06-03 | 2019-12-07 | 2020-06-03
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 23201601 | DSSM: ROOF REPLACEMENT | 2 | CONSTRUCTION | 2020-06-04 | 2020-11-30 | 2020-06-04 | 2020-11-30
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 23201901 | DSSM: MODERNIZE 3 PASSENGER ELEVATORS | 1 | DESIGN | 2019-08-11 | 2020-06-30 | 2019-08-11 | 2020-06-30
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 23201901 | DSSM: MODERNIZE 3 PASSENGER ELEVATORS | 2 | CONSTRUCTION | 2020-07-01 | 2021-06-30 | 2019-08-11 | 2020-06-30
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 23201901 | DSSM: MODERNIZE 3 PASSENGER ELEVATORS | 3 | CONSTRUCTION | 2020-07-01 | 2021-06-30 | 2020-07-01 | 2021-06-30
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 23201901 | DSSM: MODERNIZE 3 PASSENGER ELEVATORS | 4 | DESIGN | 2020-07-01 | 2021-06-30 | 2021-07-01 | 2022-11-22
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 23201901 | DSSM: MODERNIZE 3 PASSENGER ELEVATORS | 5 | CONSTRUCTION | 2020-07-01 | 2021-06-30 | 2022-11-23 | 2024-11-21
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 23201901 | DSSM: MODERNIZE 3 PASSENGER ELEVATORS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-07-01 | 2021-06-30 | 2024-11-22 | 2025-02-19
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 23202001 | DSSM: FRONT LOBBY RENOVATIONS | 1 | DESIGN | 2020-09-30 | 2022-02-21 | 2020-09-30 | 2022-02-21
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 23202001 | DSSM: FRONT LOBBY RENOVATIONS | 2 | CONSTRUCTION | 2022-02-22 | 2025-02-20 | 2022-02-22 | 2025-02-20
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 23202001 | DSSM: FRONT LOBBY RENOVATIONS | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-02-21 | 2025-05-21 | 2025-02-21 | 2025-05-21
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 23202101 | MC KINNEY: FIRE ALARM | 1 | DESIGN | 2021-02-01 | 2022-06-25 | 2021-02-01 | 2022-06-25
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 23202101 | MC KINNEY: FIRE ALARM | 2 | CONSTRUCTION | 2022-06-26 | 2025-06-24 | 2022-06-26 | 2025-06-24
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 23202101 | MC KINNEY: FIRE ALARM | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-06-25 | 2025-09-22 | 2025-06-25 | 2025-09-22
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 26201101 | GOTHAM: CONSTRUCT VANDERBILT AVENUE HEALTH CENTER AT S.I. | 1 | DESIGN | 2009-05-12 | 2010-10-03 | 2009-05-12 | 2010-10-03
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 26201101 | GOTHAM: CONSTRUCT VANDERBILT AVENUE HEALTH CENTER AT S.I. | 2 | CONSTRUCTION | 2010-10-04 | 2012-10-02 | 2010-10-04 | 2023-10-02
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 26201101 | GOTHAM: CONSTRUCT VANDERBILT AVENUE HEALTH CENTER AT S.I. | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-10-03 | 2012-12-31 | 2023-10-03 | 2023-12-31
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 26201402 | CIH: ADD DEHUMIDICATION & ADD'L COOLING CAPACITY TO THE ORs | 1 | DESIGN | 2014-05-06 | 2014-11-01 | 2014-05-06 | 2014-11-01
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 26201402 | CIH: ADD DEHUMIDICATION & ADD'L COOLING CAPACITY TO THE ORs | 2 | CONSTRUCTION | 2014-11-02 | 2015-04-30 | 2014-11-02 | 2023-04-30
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 26201902 | CIH: UPGRADE FIRE ALARM SYSTEM | 1 | DESIGN | 2019-07-07 | 2020-01-02 | 2019-07-07 | 2020-01-02
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 26201902 | CIH: UPGRADE FIRE ALARM SYSTEM | 2 | CONSTRUCTION | 2020-01-03 | 2020-06-30 | 2020-01-03 | 2020-06-30
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 26202001 | CIH: Modernize 9 Elevators in Main Building | 1 | DESIGN | 2020-09-30 | 2022-02-21 | 2020-04-30 | 2021-09-21
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 26202001 | CIH: Modernize 9 Elevators in Main Building | 2 | CONSTRUCTION | 2022-02-22 | 2025-02-20 | 2021-09-22 | 2024-09-20
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 26202001 | CIH: Modernize 9 Elevators in Main Building | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-02-21 | 2025-05-21 | 2024-09-21 | 2024-12-19
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 26202101 | ROOF REPLACEMENT MAIN BUILDING | 1 | DESIGN | 2021-02-01 | 2022-06-25 | 2021-02-01 | 2022-06-25
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 26202101 | ROOF REPLACEMENT MAIN BUILDING | 2 | CONSTRUCTION | 2022-06-26 | 2025-06-24 | 2022-06-26 | 2025-06-24
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 26202101 | ROOF REPLACEMENT MAIN BUILDING | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-06-25 | 2025-09-22 | 2025-06-25 | 2025-09-22
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 27201201 | CUMBERLAND: RENOVATE CHEMICAL DEPENDENCY DEPARTMENT | 1 | DESIGN | 2019-07-07 | 2020-01-02 | 2019-07-07 | 2020-01-02
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 27201201 | CUMBERLAND: RENOVATE CHEMICAL DEPENDENCY DEPARTMENT | 2 | CONSTRUCTION | 2020-01-03 | 2020-06-30 | 2020-01-03 | 2020-06-30
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 27201301 | CUMBERLAND: RENOVATE PEDIATRIC PRACTICE DEPARTMENT | 1 | DESIGN | 2019-07-07 | 2020-01-02 | 2019-07-07 | 2020-01-02
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 27201301 | CUMBERLAND: RENOVATE PEDIATRIC PRACTICE DEPARTMENT | 2 | CONSTRUCTION | 2020-01-03 | 2020-06-30 | 2020-01-03 | 2020-06-30
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 27201515 | CUMBERLAND: RENOVATE WOMEN'S HEALTH SVCS DEPT. | 1 | DESIGN | 2015-01-06 | 2015-07-04 | 2015-01-06 | 2015-07-04
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 27201515 | CUMBERLAND: RENOVATE WOMEN'S HEALTH SVCS DEPT. | 2 | CONSTRUCTION | 2015-07-05 | 2015-12-31 | 2015-07-05 | 2021-12-31
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 27201610 | RENOVATE BEDFORD HEALTH CLINIC | 1 | DESIGN | 2017-08-10 | 2018-06-30 | 2017-08-10 | 2018-06-30
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 27201610 | RENOVATE BEDFORD HEALTH CLINIC | 2 | CONSTRUCTION | 2018-07-01 | 2019-06-30 | 2017-08-10 | 2018-06-30
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 27201610 | RENOVATE BEDFORD HEALTH CLINIC | 3 | CONSTRUCTION | 2018-07-01 | 2019-06-30 | 2018-07-01 | 2021-06-30
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 27201702 | CUMBERLAND: CONSTRUCT NEW DENTAL FACILITY | 1 | DESIGN | 2019-07-07 | 2020-01-02 | 2019-07-07 | 2020-01-02
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 27201702 | CUMBERLAND: CONSTRUCT NEW DENTAL FACILITY | 2 | CONSTRUCTION | 2020-01-03 | 2020-06-30 | 2020-01-03 | 2020-06-30
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 27201803 | CUMBERLAND: FACADE REHABILITATION BUILDING B & C | 1 | DESIGN | 2019-08-11 | 2020-06-30 | 2019-08-11 | 2020-06-30
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 27201803 | CUMBERLAND: FACADE REHABILITATION BUILDING B & C | 2 | CONSTRUCTION | 2020-07-01 | 2021-06-30 | 2019-08-11 | 2020-06-30
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 27201803 | CUMBERLAND: FACADE REHABILITATION BUILDING B & C | 3 | CONSTRUCTION | 2020-07-01 | 2021-06-30 | 2020-07-01 | 2021-06-30
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29201301 | KCHC: UPGRADE FIRE ALARM SYSTEM IN "ABC" & "T" BLDGS | 1 | DESIGN | 2018-08-11 | 2019-07-01 | 2018-08-11 | 2019-07-01
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29201301 | KCHC: UPGRADE FIRE ALARM SYSTEM IN "ABC" & "T" BLDGS | 2 | CONSTRUCTION | 2019-07-02 | 2020-06-30 | 2018-08-11 | 2019-07-01
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29201301 | KCHC: UPGRADE FIRE ALARM SYSTEM IN "ABC" & "T" BLDGS | 3 | CONSTRUCTION | 2019-07-02 | 2020-06-30 | 2019-07-02 | 2022-06-30
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29201501 | BED-STUY REHAB CTR: FIRE ALARM SYSTEM REPLACEMENT | 1 | DESIGN | 2016-02-11 | 2016-12-31 | 2016-02-11 | 2016-12-31
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29201501 | BED-STUY REHAB CTR: FIRE ALARM SYSTEM REPLACEMENT | 2 | CONSTRUCTION | 2017-01-01 | 2017-12-31 | 2016-02-11 | 2016-12-31
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29201501 | BED-STUY REHAB CTR: FIRE ALARM SYSTEM REPLACEMENT | 3 | CONSTRUCTION | 2017-01-01 | 2017-12-31 | 2017-01-01 | 2021-12-31
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29201610 | KCHC: LOCAL LAW -11 COMPLIANCE - BLDG T | 1 | DESIGN | 2017-08-10 | 2018-06-30 | 2017-08-10 | 2018-06-30
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29201610 | KCHC: LOCAL LAW -11 COMPLIANCE - BLDG T | 2 | CONSTRUCTION | 2018-07-01 | 2019-06-30 | 2017-08-10 | 2018-06-30
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29201610 | KCHC: LOCAL LAW -11 COMPLIANCE - BLDG T | 3 | CONSTRUCTION | 2018-07-01 | 2019-06-30 | 2018-07-01 | 2021-06-30
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29201611 | KCHC: LOCAL LAW 11 COMPLIANCE - BLDG ABC | 1 | DESIGN | 2017-08-10 | 2018-06-30 | 2017-08-10 | 2018-06-30
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29201611 | KCHC: LOCAL LAW 11 COMPLIANCE - BLDG ABC | 2 | CONSTRUCTION | 2018-07-01 | 2019-06-30 | 2017-08-10 | 2018-06-30
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29201611 | KCHC: LOCAL LAW 11 COMPLIANCE - BLDG ABC | 3 | CONSTRUCTION | 2018-07-01 | 2019-06-30 | 2018-07-01 | 2021-06-30
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29201612 | KCHC: BLDG "P" FACADE REMEDIATION - LOCAL LAW 11 COMPLIANCE | 1 | DESIGN | 2019-08-11 | 2020-06-30 | 2019-08-11 | 2020-06-30
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29201612 | KCHC: BLDG "P" FACADE REMEDIATION - LOCAL LAW 11 COMPLIANCE | 2 | CONSTRUCTION | 2020-07-01 | 2021-06-30 | 2019-08-11 | 2020-06-30
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29201612 | KCHC: BLDG "P" FACADE REMEDIATION - LOCAL LAW 11 COMPLIANCE | 3 | CONSTRUCTION | 2020-07-01 | 2021-06-30 | 2020-07-01 | 2021-06-30
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29201614 | KCHC: BOILER REPLACEMENT | 1 | DESIGN | 2018-08-11 | 2019-07-01 | 2018-08-11 | 2019-07-01
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29201614 | KCHC: BOILER REPLACEMENT | 2 | CONSTRUCTION | 2019-07-02 | 2020-06-30 | 2018-08-11 | 2019-07-01
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29201614 | KCHC: BOILER REPLACEMENT | 3 | CONSTRUCTION | 2019-07-02 | 2020-06-30 | 2019-07-02 | 2023-06-30
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29201802 | KCHC: REPLACEMENT OF C6 HEMODIALYSIS WATER TREATMENT SYSTEM | 1 | DESIGN | 2021-03-06 | 2022-07-28 | 2021-03-06 | 2022-07-28
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29201802 | KCHC: REPLACEMENT OF C6 HEMODIALYSIS WATER TREATMENT SYSTEM | 2 | CONSTRUCTION | 2022-07-29 | 2025-07-27 | 2022-07-29 | 2025-07-27
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29201802 | KCHC: REPLACEMENT OF C6 HEMODIALYSIS WATER TREATMENT SYSTEM | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-07-28 | 2025-10-25 | 2025-07-28 | 2025-10-25
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29201803 | KINGS, ABC BUILDING ELECTRICAL FEEDER REPLACEMENT | 1 | DESIGN | 2018-07-06 | 2019-01-01 | 2018-07-06 | 2019-01-01
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29201803 | KINGS, ABC BUILDING ELECTRICAL FEEDER REPLACEMENT | 2 | CONSTRUCTION | 2019-01-02 | 2019-06-30 | 2023-01-02 | 2026-07-05
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29202001 | KIN: REHABILITATE STEAM TUNNEL UNDER WINTHROP STREET | 1 | DESIGN | 2020-09-30 | 2022-02-21 | 2020-09-30 | 2022-02-21
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29202001 | KIN: REHABILITATE STEAM TUNNEL UNDER WINTHROP STREET | 2 | CONSTRUCTION | 2022-02-22 | 2025-02-20 | 2022-02-22 | 2025-02-20
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29202001 | KIN: REHABILITATE STEAM TUNNEL UNDER WINTHROP STREET | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-02-21 | 2025-05-21 | 2025-02-21 | 2025-05-21
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29202002 | KINGS BUILDING D ELEVATOR MODERNIZATION | 1 | DESIGN | 2020-04-20 | 2021-09-11 | 2020-04-20 | 2021-09-11
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29202002 | KINGS BUILDING D ELEVATOR MODERNIZATION | 2 | CONSTRUCTION | 2021-09-12 | 2023-09-11 | 2021-09-12 | 2023-09-11
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29202002 | KINGS BUILDING D ELEVATOR MODERNIZATION | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-12 | 2023-12-10 | 2023-09-12 | 2023-12-10
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29202101 | RESTORATION OF WEST SMOKE STACK | 1 | DESIGN | 2020-05-01 | 2021-09-22 | 2020-05-01 | 2021-09-22
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29202101 | RESTORATION OF WEST SMOKE STACK | 2 | CONSTRUCTION | 2021-09-23 | 2023-09-22 | 2021-09-23 | 2023-09-22
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29202101 | RESTORATION OF WEST SMOKE STACK | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-23 | 2023-12-21 | 2023-09-23 | 2023-12-21
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29202102 | KINGS: WELLNESS CENTER | 1 | DESIGN | 2020-05-01 | 2021-09-22 | 2020-05-01 | 2021-09-22
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29202102 | KINGS: WELLNESS CENTER | 2 | CONSTRUCTION | 2021-09-23 | 2023-09-22 | 2021-09-23 | 2023-09-22
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29202102 | KINGS: WELLNESS CENTER | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-23 | 2023-12-21 | 2023-09-23 | 2023-12-21
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29202103 | KIN: P BUILDING MORGUE | 1 | DESIGN | 2020-05-01 | 2021-09-22 | 2020-05-01 | 2021-09-22
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29202103 | KIN: P BUILDING MORGUE | 2 | CONSTRUCTION | 2021-09-23 | 2023-09-22 | 2021-09-23 | 2023-09-22
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29202103 | KIN: P BUILDING MORGUE | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-23 | 2023-12-21 | 2023-09-23 | 2023-12-21
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29202104 | KIN: Bldg D Electrical | 1 | DESIGN | 2020-05-01 | 2021-09-22 | 2020-05-01 | 2021-09-22
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29202104 | KIN: Bldg D Electrical | 2 | CONSTRUCTION | 2021-09-23 | 2023-09-22 | 2021-09-23 | 2023-09-22
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29202104 | KIN: Bldg D Electrical | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-23 | 2023-12-21 | 2023-09-23 | 2023-12-21
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29202105 | KIN: Bldg S Water Balancing | 1 | DESIGN | 2020-05-01 | 2021-09-22 | 2020-05-01 | 2021-09-22
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29202105 | KIN: Bldg S Water Balancing | 2 | CONSTRUCTION | 2021-09-23 | 2023-09-22 | 2021-09-23 | 2023-09-22
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29202105 | KIN: Bldg S Water Balancing | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-23 | 2023-12-21 | 2023-09-23 | 2023-12-21
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48200803 | WOODHULL: OB UNIT EXPANSION | 1 | DESIGN | 2013-04-10 | 2014-02-28 | 2013-04-10 | 2014-02-28
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48200803 | WOODHULL: OB UNIT EXPANSION | 2 | CONSTRUCTION | 2014-03-01 | 2015-02-28 | 2013-04-10 | 2014-02-28
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48200803 | WOODHULL: OB UNIT EXPANSION | 3 | CONSTRUCTION | 2014-03-01 | 2015-02-28 | 2014-03-01 | 2023-02-28
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48200903 | WOODHULL: EXPAND NEONATAL SPECIAL CARE UNIT (NICU) | 2 | CONSTRUCTION | 2014-02-01 | 2015-01-31 | 2013-03-13 | 2014-01-31
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48200903 | WOODHULL: EXPAND NEONATAL SPECIAL CARE UNIT (NICU) | 3 | CONSTRUCTION | 2014-02-01 | 2015-01-31 | 2014-02-01 | 2015-01-31
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48201402 | WOODHULL: ESTABLISH CPEP | 1 | DESIGN | 2013-06-06 | 2013-12-02 | 2017-06-06 | 2017-12-02
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48201402 | WOODHULL: ESTABLISH CPEP | 2 | CONSTRUCTION | 2013-12-03 | 2014-05-31 | 2017-12-03 | 2018-05-31
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48201402 | WOODHULL: ESTABLISH CPEP | 3 | DESIGN | 2013-12-03 | 2014-05-31 | 2018-06-01 | 2019-10-23
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48201402 | WOODHULL: ESTABLISH CPEP | 4 | CONSTRUCTION | 2013-12-03 | 2014-05-31 | 2019-10-24 | 2022-10-22
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48201402 | WOODHULL: ESTABLISH CPEP | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-12-03 | 2014-05-31 | 2022-10-23 | 2023-01-20
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48201505 | WOODHULL: INSTALL PERMANENT EMERGENCY POWER FEEDER | 3 | CONSTRUCTION | 2017-01-01 | 2017-12-31 | 2017-01-01 | 2017-12-31
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48201506 | WOODHULL: ESTABLISH BURN UNIT | 1 | DESIGN | 2020-08-10 | 2021-06-30 | 2021-08-01 | 2022-06-02
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48201506 | WOODHULL: ESTABLISH BURN UNIT | 2 | CONSTRUCTION | 2021-07-01 | 2022-06-30 | 2021-08-01 | 2022-06-02
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48201515 | WOODHULL: RENOVATE WOMEN'S HEALTH SVCS - RADIOLOGY | 2 | CONSTRUCTION | 2015-07-05 | 2015-12-31 | 2015-07-05 | 2015-12-31
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48201516 | WOODHULL: RENOVATE WOMEN'S HEALTH PAVILION | 1 | DESIGN | 2015-01-06 | 2015-07-04 | 2015-01-06 | 2015-07-04
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48201516 | WOODHULL: RENOVATE WOMEN'S HEALTH PAVILION | 2 | CONSTRUCTION | 2015-07-05 | 2015-12-31 | 2015-07-05 | 2022-12-31
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48201602 | WOODHULL: LOCAL LAW 11 COMPLIANCE | 1 | DESIGN | 2019-08-11 | 2020-06-30 | 2019-08-11 | 2020-06-30
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48201602 | WOODHULL: LOCAL LAW 11 COMPLIANCE | 2 | CONSTRUCTION | 2020-07-01 | 2021-06-30 | 2019-08-11 | 2020-06-30
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48201602 | WOODHULL: LOCAL LAW 11 COMPLIANCE | 3 | CONSTRUCTION | 2020-07-01 | 2021-06-30 | 2020-07-01 | 2021-06-30
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48201610 | RENOVATE BUSHWICK COMMUNICARE | 1 | DESIGN | 2015-12-07 | 2016-06-03 | 2015-12-07 | 2016-06-03
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48201610 | RENOVATE BUSHWICK COMMUNICARE | 2 | CONSTRUCTION | 2016-06-04 | 2016-11-30 | 2016-06-04 | 2022-11-30
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48201801 | WOODHULL: REPLACE MAIN SERVICE SWITCHES FOR ATS 1, 2 AND 5 | 1 | DESIGN | 2018-05-13 | 2019-10-04 | 2018-05-13 | 2019-10-04
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48201801 | WOODHULL: REPLACE MAIN SERVICE SWITCHES FOR ATS 1, 2 AND 5 | 2 | CONSTRUCTION | 2019-10-05 | 2022-10-03 | 2019-10-05 | 2022-10-03
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48201801 | WOODHULL: REPLACE MAIN SERVICE SWITCHES FOR ATS 1, 2 AND 5 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-10-04 | 2023-01-01 | 2022-10-04 | 2023-01-01
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48201901 | WOODHULL: CPEP RENOVATION | 1 | DESIGN | 2019-01-06 | 2019-07-04 | 2019-01-06 | 2019-07-04
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48201901 | WOODHULL: CPEP RENOVATION | 2 | CONSTRUCTION | 2019-07-05 | 2019-12-31 | 2019-07-05 | 2023-12-31
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48201902 | WOODHULL: EMERGENCY DEPARTMENT RENOVATION | 1 | DESIGN | 2018-08-11 | 2019-07-01 | 2018-08-11 | 2019-07-01
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48201902 | WOODHULL: EMERGENCY DEPARTMENT RENOVATION | 2 | CONSTRUCTION | 2019-07-02 | 2020-06-30 | 2018-08-11 | 2019-07-01
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48201902 | WOODHULL: EMERGENCY DEPARTMENT RENOVATION | 3 | CONSTRUCTION | 2019-07-02 | 2020-06-30 | 2019-07-02 | 2020-06-30
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48201903 | WOODHULL: RETAIL PHARMACY RENOVATION | 1 | DESIGN | 2019-05-13 | 2020-10-03 | 2019-05-13 | 2020-10-03
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48201903 | WOODHULL: RETAIL PHARMACY RENOVATION | 2 | CONSTRUCTION | 2020-10-04 | 2023-10-03 | 2020-10-04 | 2023-10-03
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48201903 | WOODHULL: RETAIL PHARMACY RENOVATION | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-10-04 | 2024-01-01 | 2023-10-04 | 2024-01-01
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48202001 | WOODHULL: CREATE 14 EXAM ROOMS FOR ADULT MEDICINE CLINIC | 1 | DESIGN | 2020-05-13 | 2021-10-04 | 2020-05-13 | 2021-10-04
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48202001 | WOODHULL: CREATE 14 EXAM ROOMS FOR ADULT MEDICINE CLINIC | 2 | CONSTRUCTION | 2021-10-05 | 2024-10-03 | 2021-10-05 | 2024-10-03
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48202001 | WOODHULL: CREATE 14 EXAM ROOMS FOR ADULT MEDICINE CLINIC | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-10-04 | 2025-01-01 | 2024-10-04 | 2025-01-01
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48202002 | WOODHULL: Modernize Elevators | 1 | DESIGN | 2020-05-13 | 2021-10-04 | 2020-05-13 | 2021-10-04
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48202002 | WOODHULL: Modernize Elevators | 2 | CONSTRUCTION | 2021-10-05 | 2024-10-03 | 2021-10-05 | 2024-10-03
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48202002 | WOODHULL: Modernize Elevators | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-10-04 | 2025-01-01 | 2024-10-04 | 2025-01-01
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48202003 | WOODHULL: Dinex Buildout and Installation | 1 | DESIGN | 2020-05-13 | 2021-10-04 | 2020-05-13 | 2021-10-04
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48202003 | WOODHULL: Dinex Buildout and Installation | 2 | CONSTRUCTION | 2021-10-05 | 2024-10-03 | 2021-10-05 | 2024-10-03
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48202003 | WOODHULL: Dinex Buildout and Installation | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-10-04 | 2025-01-01 | 2024-10-04 | 2025-01-01
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48202101 | WOODHULL: SURVEILLANCE MODERNIZATION | 1 | DESIGN | 2020-05-01 | 2021-09-22 | 2020-05-01 | 2021-09-22
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48202101 | WOODHULL: SURVEILLANCE MODERNIZATION | 2 | CONSTRUCTION | 2021-09-23 | 2023-09-22 | 2021-09-23 | 2023-09-22
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48202101 | WOODHULL: SURVEILLANCE MODERNIZATION | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-23 | 2023-12-21 | 2023-09-23 | 2023-12-21
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48202102 | WOO: Electrical Upgrades | 1 | DESIGN | 2020-05-01 | 2021-09-22 | 2020-05-01 | 2021-09-22
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48202102 | WOO: Electrical Upgrades | 2 | CONSTRUCTION | 2021-09-23 | 2023-09-22 | 2021-09-23 | 2023-09-22
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48202102 | WOO: Electrical Upgrades | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-23 | 2023-12-21 | 2023-09-23 | 2023-12-21
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | ACEHHC407 | Cumberland : Boiler Plant Replacement | 1 | DESIGN | 2017-05-13 | 2018-10-04 | 2017-05-13 | 2018-10-04
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | ACEHHC407 | Cumberland : Boiler Plant Replacement | 2 | CONSTRUCTION | 2018-10-05 | 2021-10-03 | 2018-10-05 | 2021-10-03
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | ACEHHC407 | Cumberland : Boiler Plant Replacement | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-10-04 | 2022-01-01 | 2021-10-04 | 2022-01-01
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | ACEHHC607 | KCHC: LIGHTING UPGRADES - PHASE 2 | 1 | DESIGN | 2019-08-11 | 2020-06-30 | 2019-08-11 | 2020-06-30
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | ACEHHC607 | KCHC: LIGHTING UPGRADES - PHASE 2 | 2 | CONSTRUCTION | 2020-07-01 | 2021-06-30 | 2019-08-11 | 2020-06-30
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | ACEHHC607 | KCHC: LIGHTING UPGRADES - PHASE 2 | 3 | CONSTRUCTION | 2020-07-01 | 2021-06-30 | 2020-07-01 | 2023-06-30
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | CIH1 | CIH: MODERNIZE GENERAL CARE INPATIENT/AMB CARE FACILITIES | 1 | DESIGN | 2000-10-24 | 2002-03-17 | 2008-10-23 | 2010-03-16
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | CIH1 | CIH: MODERNIZE GENERAL CARE INPATIENT/AMB CARE FACILITIES | 2 | CONSTRUCTION | 2002-03-18 | 2005-03-16 | 2022-03-18 | 2029-03-18
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | CIH1 | CIH: MODERNIZE GENERAL CARE INPATIENT/AMB CARE FACILITIES | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2005-03-17 | 2005-06-14 | 2029-03-19 | 2029-06-16
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | GABIHHC | GROUP ATTACHMENT BASED INTERVENTION | 1 | DESIGN | 2019-01-02 | 2019-03-31 | 2019-01-02 | 2019-03-31
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | GABIHHC | GROUP ATTACHMENT BASED INTERVENTION | 2 | CONSTRUCTION | 2019-04-01 | 2020-03-30 | 2019-04-01 | 2020-03-30
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | SAND2603 | CIH: RENOVATE VACANT SPACE ON FIRST FL MAIN HOSPITAL BLG. | 1 | DESIGN | 2018-05-13 | 2019-10-04 | 2018-05-13 | 2019-10-04
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | SAND2603 | CIH: RENOVATE VACANT SPACE ON FIRST FL MAIN HOSPITAL BLG. | 2 | CONSTRUCTION | 2019-10-05 | 2022-10-03 | 2019-10-05 | 2022-10-03
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | SAND2603 | CIH: RENOVATE VACANT SPACE ON FIRST FL MAIN HOSPITAL BLG. | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-10-04 | 2023-01-01 | 2022-10-04 | 2023-01-01
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | SAND2607 | CIH: REPLACEMENT OF BASEMENT LIGHTING IN THE MAIN BLDG. | 1 | DESIGN | 2020-07-06 | 2021-01-01 | 2019-07-06 | 2021-01-01
20201123 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | SAND2607 | CIH: REPLACEMENT OF BASEMENT LIGHTING IN THE MAIN BLDG. | 2 | CONSTRUCTION | 2021-01-02 | 2021-06-30 | 2021-01-02 | 2021-06-30
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26-STAB13 | 26th Ward - Emergency Generators | 1 | DEVELOP SCOPE | 2000-06-15 | 2001-03-11 | 2017-01-15 | 2017-10-11
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26-STAB13 | 26th Ward - Emergency Generators | 2 | PRELIMINARY DESIGN | 2001-03-12 | 2002-03-06 | 2017-10-12 | 2018-10-06
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26-STAB13 | 26th Ward - Emergency Generators | 3 | FINAL DESIGN | 2002-03-07 | 2003-08-28 | 2018-10-07 | 2020-03-29
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26-STAB13 | 26th Ward - Emergency Generators | 4 | BID AWARD AND REGISTER CONTRCT | 2003-08-29 | 2004-05-24 | 2020-03-30 | 2020-12-24
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26-STAB13 | 26th Ward - Emergency Generators | 5 | CONSTRUCTION TO 25% | 2004-05-25 | 2005-05-19 | 2020-12-25 | 2021-12-19
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26-STAB13 | 26th Ward - Emergency Generators | 6 | CONSTRUCTION TO 50% | 2005-05-20 | 2006-05-14 | 2021-12-20 | 2022-12-14
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26-STAB13 | 26th Ward - Emergency Generators | 7 | CONSTRUCTION TO 75% | 2006-05-15 | 2007-05-09 | 2022-12-15 | 2023-12-09
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26-STAB13 | 26th Ward - Emergency Generators | 8 | ORIGINAL EQUIP & FURNISHING | 2007-05-10 | 2008-02-03 | 2023-12-10 | 2024-09-04
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26-STAB13 | 26th Ward - Emergency Generators | 9 | SUBSTANTIAL COMPLETION | 2008-02-04 | 2008-08-01 | 2024-09-05 | 2025-03-03
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26-STAB13 | 26th Ward - Emergency Generators | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-08-02 | 2008-10-30 | 2025-03-04 | 2025-06-01
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26-STAB20 | 26th Ward Primary Settling Tank & Solid Handling | 1 | DEVELOP SCOPE | 2000-06-15 | 2001-03-11 | 2013-06-15 | 2014-03-11
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26-STAB20 | 26th Ward Primary Settling Tank & Solid Handling | 2 | PRELIMINARY DESIGN | 2001-03-12 | 2002-03-06 | 2014-03-12 | 2015-03-06
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26-STAB20 | 26th Ward Primary Settling Tank & Solid Handling | 3 | FINAL DESIGN | 2002-03-07 | 2003-08-28 | 2015-03-07 | 2016-08-27
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26-STAB20 | 26th Ward Primary Settling Tank & Solid Handling | 4 | BID AWARD AND REGISTER CONTRCT | 2003-08-29 | 2004-05-24 | 2016-08-28 | 2017-05-24
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26-STAB20 | 26th Ward Primary Settling Tank & Solid Handling | 5 | CONSTRUCTION TO 25% | 2004-05-25 | 2005-05-19 | 2017-05-25 | 2018-05-19
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26-STAB20 | 26th Ward Primary Settling Tank & Solid Handling | 6 | CONSTRUCTION TO 50% | 2005-05-20 | 2006-05-14 | 2018-05-20 | 2019-05-14
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26-STAB20 | 26th Ward Primary Settling Tank & Solid Handling | 7 | CONSTRUCTION TO 75% | 2006-05-15 | 2007-05-09 | 2019-05-15 | 2020-05-08
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26-STAB20 | 26th Ward Primary Settling Tank & Solid Handling | 8 | ORIGINAL EQUIP & FURNISHING | 2007-05-10 | 2008-02-03 | 2020-05-09 | 2021-02-02
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26-STAB20 | 26th Ward Primary Settling Tank & Solid Handling | 9 | SUBSTANTIAL COMPLETION | 2008-02-04 | 2008-08-01 | 2021-02-03 | 2021-08-01
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26-STAB20 | 26th Ward Primary Settling Tank & Solid Handling | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-08-02 | 2008-10-30 | 2021-08-02 | 2021-10-30
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-144-L | INSTALLATION OF (13) NEW CENTRIFUGES @ 26TH WARD WPCP | 1 | DEVELOP SCOPE | 2017-06-01 | 2018-02-25 | 2017-06-01 | 2018-02-25
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-144-L | INSTALLATION OF (13) NEW CENTRIFUGES @ 26TH WARD WPCP | 2 | PRELIMINARY DESIGN | 2018-02-26 | 2019-02-20 | 2018-02-26 | 2019-02-20
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-144-L | INSTALLATION OF (13) NEW CENTRIFUGES @ 26TH WARD WPCP | 3 | FINAL DESIGN | 2019-02-21 | 2020-08-13 | 2019-02-21 | 2020-08-13
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-144-L | INSTALLATION OF (13) NEW CENTRIFUGES @ 26TH WARD WPCP | 4 | BID AWARD AND REGISTER CONTRCT | 2020-08-14 | 2021-05-10 | 2020-08-14 | 2021-05-10
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-144-L | INSTALLATION OF (13) NEW CENTRIFUGES @ 26TH WARD WPCP | 5 | CONSTRUCTION TO 25% | 2021-05-11 | 2022-05-05 | 2021-05-11 | 2022-05-05
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-144-L | INSTALLATION OF (13) NEW CENTRIFUGES @ 26TH WARD WPCP | 6 | CONSTRUCTION TO 50% | 2022-05-06 | 2023-04-30 | 2022-05-06 | 2023-04-30
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-144-L | INSTALLATION OF (13) NEW CENTRIFUGES @ 26TH WARD WPCP | 7 | CONSTRUCTION TO 75% | 2023-05-01 | 2024-04-24 | 2023-05-01 | 2024-04-24
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-144-L | INSTALLATION OF (13) NEW CENTRIFUGES @ 26TH WARD WPCP | 8 | ORIGINAL EQUIP & FURNISHING | 2024-04-25 | 2025-01-19 | 2024-04-25 | 2025-01-19
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-144-L | INSTALLATION OF (13) NEW CENTRIFUGES @ 26TH WARD WPCP | 9 | SUBSTANTIAL COMPLETION | 2025-01-20 | 2025-07-18 | 2025-01-20 | 2025-07-18
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-144-L | INSTALLATION OF (13) NEW CENTRIFUGES @ 26TH WARD WPCP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-07-19 | 2025-10-16 | 2025-07-19 | 2025-10-16
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-147-L | LIGHTING UPGRADE AT THE 26TH WARD WPCP | 1 | DEVELOP SCOPE | 2014-11-09 | 2015-02-06 | 2020-06-01 | 2020-08-29
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-147-L | LIGHTING UPGRADE AT THE 26TH WARD WPCP | 2 | PRELIMINARY DESIGN | 2015-02-07 | 2015-06-06 | 2020-08-30 | 2020-12-27
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-147-L | LIGHTING UPGRADE AT THE 26TH WARD WPCP | 3 | FINAL DESIGN | 2015-06-07 | 2015-12-03 | 2020-12-28 | 2021-06-25
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-147-L | LIGHTING UPGRADE AT THE 26TH WARD WPCP | 4 | BID AWARD AND REGISTER CONTRCT | 2015-12-04 | 2016-03-02 | 2021-06-26 | 2021-09-23
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-147-L | LIGHTING UPGRADE AT THE 26TH WARD WPCP | 5 | CONSTRUCTION TO 25% | 2016-03-03 | 2016-06-30 | 2021-09-24 | 2022-01-21
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-147-L | LIGHTING UPGRADE AT THE 26TH WARD WPCP | 6 | CONSTRUCTION TO 50% | 2016-07-01 | 2016-10-28 | 2022-01-22 | 2022-05-21
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-147-L | LIGHTING UPGRADE AT THE 26TH WARD WPCP | 7 | CONSTRUCTION TO 75% | 2016-10-29 | 2017-02-25 | 2022-05-22 | 2022-09-18
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-147-L | LIGHTING UPGRADE AT THE 26TH WARD WPCP | 8 | ORIGINAL EQUIP & FURNISHING | 2017-02-26 | 2017-05-26 | 2022-09-19 | 2022-12-17
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-147-L | LIGHTING UPGRADE AT THE 26TH WARD WPCP | 9 | SUBSTANTIAL COMPLETION | 2017-05-27 | 2017-07-25 | 2022-12-18 | 2023-02-15
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-147-L | LIGHTING UPGRADE AT THE 26TH WARD WPCP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-07-26 | 2017-08-24 | 2023-02-16 | 2023-03-17
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-148-L | TRC - CONS OF DISINFECTION FACILITIES AT 26TH WARD WPCP | 1 | FINAL DESIGN | 2016-06-01 | 2017-11-22 | 2016-06-01 | 2017-02-25
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-148-L | TRC - CONS OF DISINFECTION FACILITIES AT 26TH WARD WPCP | 2 | CONSTRUCTION TO 25% | 2017-11-23 | 2018-07-20 | 2017-02-26 | 2018-02-20
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-148-L | TRC - CONS OF DISINFECTION FACILITIES AT 26TH WARD WPCP | 3 | CONSTRUCTION TO 50% | 2018-07-21 | 2019-03-17 | 2018-02-21 | 2019-08-14
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-148-L | TRC - CONS OF DISINFECTION FACILITIES AT 26TH WARD WPCP | 4 | CONSTRUCTION TO 75% | 2019-03-18 | 2019-11-12 | 2019-08-15 | 2020-05-10
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-148-L | TRC - CONS OF DISINFECTION FACILITIES AT 26TH WARD WPCP | 5 | CONSTRUCTION TO 25% | 2019-03-18 | 2019-11-12 | 2020-05-11 | 2021-05-05
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-148-L | TRC - CONS OF DISINFECTION FACILITIES AT 26TH WARD WPCP | 6 | CONSTRUCTION TO 50% | 2019-03-18 | 2019-11-12 | 2021-05-06 | 2022-04-30
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-148-L | TRC - CONS OF DISINFECTION FACILITIES AT 26TH WARD WPCP | 7 | CONSTRUCTION TO 75% | 2019-03-18 | 2019-11-12 | 2022-05-01 | 2023-04-25
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-148-L | TRC - CONS OF DISINFECTION FACILITIES AT 26TH WARD WPCP | 8 | ORIGINAL EQUIP & FURNISHING | 2019-03-18 | 2019-11-12 | 2023-04-26 | 2024-01-20
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-148-L | TRC - CONS OF DISINFECTION FACILITIES AT 26TH WARD WPCP | 9 | SUBSTANTIAL COMPLETION | 2019-03-18 | 2019-11-12 | 2024-01-21 | 2028-07-17
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-148-L | TRC - CONS OF DISINFECTION FACILITIES AT 26TH WARD WPCP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-03-18 | 2019-11-12 | 2028-07-18 | 2028-10-15
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-149 | RECONSTRUCT TIDE GATES/EFFLUENT CHAMBERS @ SPRING CREEK | 1 | DEVELOP SCOPE | 2019-06-01 | 2019-08-29 | 2019-06-01 | 2019-08-29
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-149 | RECONSTRUCT TIDE GATES/EFFLUENT CHAMBERS @ SPRING CREEK | 2 | PRELIMINARY DESIGN | 2019-08-30 | 2019-12-27 | 2019-08-30 | 2019-12-27
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-149 | RECONSTRUCT TIDE GATES/EFFLUENT CHAMBERS @ SPRING CREEK | 3 | FINAL DESIGN | 2019-12-28 | 2020-06-24 | 2019-12-28 | 2020-06-24
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-149 | RECONSTRUCT TIDE GATES/EFFLUENT CHAMBERS @ SPRING CREEK | 4 | BID AWARD AND REGISTER CONTRCT | 2020-06-25 | 2020-09-22 | 2020-06-25 | 2020-09-22
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-149 | RECONSTRUCT TIDE GATES/EFFLUENT CHAMBERS @ SPRING CREEK | 5 | CONSTRUCTION TO 25% | 2020-09-23 | 2021-01-20 | 2020-09-23 | 2021-01-20
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-149 | RECONSTRUCT TIDE GATES/EFFLUENT CHAMBERS @ SPRING CREEK | 6 | CONSTRUCTION TO 50% | 2021-01-21 | 2021-05-20 | 2021-01-21 | 2021-05-20
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-149 | RECONSTRUCT TIDE GATES/EFFLUENT CHAMBERS @ SPRING CREEK | 7 | CONSTRUCTION TO 75% | 2021-05-21 | 2021-09-17 | 2021-05-21 | 2021-09-17
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-149 | RECONSTRUCT TIDE GATES/EFFLUENT CHAMBERS @ SPRING CREEK | 8 | ORIGINAL EQUIP & FURNISHING | 2021-09-18 | 2021-12-16 | 2021-09-18 | 2021-12-16
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-149 | RECONSTRUCT TIDE GATES/EFFLUENT CHAMBERS @ SPRING CREEK | 9 | SUBSTANTIAL COMPLETION | 2021-12-17 | 2022-02-14 | 2021-12-17 | 2022-02-14
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-149 | RECONSTRUCT TIDE GATES/EFFLUENT CHAMBERS @ SPRING CREEK | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-02-15 | 2022-03-16 | 2022-02-15 | 2022-03-16
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-156-L | REPLACE WASTE ACTIVATED SLUDGE PIPING AT 26TH WARD WPCP | 1 | FINAL DESIGN | 2019-06-01 | 2020-11-21 | 2019-06-01 | 2020-11-21
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-156-L | REPLACE WASTE ACTIVATED SLUDGE PIPING AT 26TH WARD WPCP | 2 | CONSTRUCTION TO 25% | 2020-11-22 | 2021-07-19 | 2020-11-22 | 2021-07-19
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-156-L | REPLACE WASTE ACTIVATED SLUDGE PIPING AT 26TH WARD WPCP | 3 | CONSTRUCTION TO 50% | 2021-07-20 | 2022-03-16 | 2021-07-20 | 2022-03-16
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-156-L | REPLACE WASTE ACTIVATED SLUDGE PIPING AT 26TH WARD WPCP | 4 | CONSTRUCTION TO 75% | 2022-03-17 | 2022-11-11 | 2022-03-17 | 2022-11-11
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-21 | HIGH LEVEL MAIN SEWAGE PUMP IMPROVEMENTS AT 26TH WARD WPCP | 1 | DEVELOP SCOPE | 2015-06-15 | 2015-09-12 | 2015-06-15 | 2016-03-10
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-21 | HIGH LEVEL MAIN SEWAGE PUMP IMPROVEMENTS AT 26TH WARD WPCP | 2 | PRELIMINARY DESIGN | 2015-09-13 | 2016-01-10 | 2016-03-11 | 2017-03-05
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-21 | HIGH LEVEL MAIN SEWAGE PUMP IMPROVEMENTS AT 26TH WARD WPCP | 3 | FINAL DESIGN | 2016-01-11 | 2016-07-08 | 2017-03-06 | 2018-08-27
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-21 | HIGH LEVEL MAIN SEWAGE PUMP IMPROVEMENTS AT 26TH WARD WPCP | 4 | BID AWARD AND REGISTER CONTRCT | 2016-07-09 | 2016-10-06 | 2018-08-28 | 2019-05-24
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-21 | HIGH LEVEL MAIN SEWAGE PUMP IMPROVEMENTS AT 26TH WARD WPCP | 5 | CONSTRUCTION TO 25% | 2016-10-07 | 2017-02-03 | 2019-05-25 | 2020-05-18
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-21 | HIGH LEVEL MAIN SEWAGE PUMP IMPROVEMENTS AT 26TH WARD WPCP | 6 | CONSTRUCTION TO 50% | 2017-02-04 | 2017-06-03 | 2020-05-19 | 2021-05-13
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-21 | HIGH LEVEL MAIN SEWAGE PUMP IMPROVEMENTS AT 26TH WARD WPCP | 7 | CONSTRUCTION TO 75% | 2017-06-04 | 2017-10-01 | 2021-05-14 | 2022-05-08
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-21 | HIGH LEVEL MAIN SEWAGE PUMP IMPROVEMENTS AT 26TH WARD WPCP | 8 | ORIGINAL EQUIP & FURNISHING | 2017-10-02 | 2017-12-30 | 2022-05-09 | 2023-02-02
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-21 | HIGH LEVEL MAIN SEWAGE PUMP IMPROVEMENTS AT 26TH WARD WPCP | 9 | SUBSTANTIAL COMPLETION | 2017-12-31 | 2018-02-28 | 2023-02-03 | 2023-08-01
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-21 | HIGH LEVEL MAIN SEWAGE PUMP IMPROVEMENTS AT 26TH WARD WPCP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-03-01 | 2018-03-30 | 2023-08-02 | 2023-10-30
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | BED-828 | Dist WM work in 86th St between Bay 20th & 28th St, BKLYN | 1 | DEVELOP SCOPE | 2022-11-15 | 2023-02-12 | 2022-11-15 | 2023-02-12
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | BED-828 | Dist WM work in 86th St between Bay 20th & 28th St, BKLYN | 2 | PRELIMINARY DESIGN | 2023-02-13 | 2023-06-12 | 2023-02-13 | 2023-06-12
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | BED-828 | Dist WM work in 86th St between Bay 20th & 28th St, BKLYN | 3 | FINAL DESIGN | 2023-06-13 | 2023-12-09 | 2023-06-13 | 2023-12-09
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | BED-828 | Dist WM work in 86th St between Bay 20th & 28th St, BKLYN | 4 | BID AWARD AND REGISTER CONTRCT | 2023-12-10 | 2024-03-08 | 2023-12-10 | 2024-03-08
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | BED-828 | Dist WM work in 86th St between Bay 20th & 28th St, BKLYN | 5 | CONSTRUCTION TO 25% | 2024-03-09 | 2024-07-06 | 2024-03-09 | 2024-07-06
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | BED-828 | Dist WM work in 86th St between Bay 20th & 28th St, BKLYN | 6 | CONSTRUCTION TO 50% | 2024-07-07 | 2024-11-03 | 2024-07-07 | 2024-11-03
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | BED-828 | Dist WM work in 86th St between Bay 20th & 28th St, BKLYN | 7 | CONSTRUCTION TO 75% | 2024-11-04 | 2025-03-03 | 2024-11-04 | 2025-03-03
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | BED-828 | Dist WM work in 86th St between Bay 20th & 28th St, BKLYN | 8 | ORIGINAL EQUIP & FURNISHING | 2025-03-04 | 2025-06-01 | 2025-03-04 | 2025-06-01
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | BED-828 | Dist WM work in 86th St between Bay 20th & 28th St, BKLYN | 9 | SUBSTANTIAL COMPLETION | 2025-06-02 | 2025-07-31 | 2025-06-02 | 2025-07-31
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | BED-828 | Dist WM work in 86th St between Bay 20th & 28th St, BKLYN | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-08-01 | 2025-08-30 | 2025-08-01 | 2025-08-30
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | BED-833 | Rel.& Inst. WMs on Flatland Ave btwn Ralph Ave & E 76 St BKL | 1 | DEVELOP SCOPE | 2020-11-09 | 2021-08-05 | 2020-11-09 | 2021-08-05
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | BED-833 | Rel.& Inst. WMs on Flatland Ave btwn Ralph Ave & E 76 St BKL | 2 | PRELIMINARY DESIGN | 2021-08-06 | 2022-07-31 | 2021-08-06 | 2022-07-31
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | BED-833 | Rel.& Inst. WMs on Flatland Ave btwn Ralph Ave & E 76 St BKL | 3 | FINAL DESIGN | 2022-08-01 | 2024-01-22 | 2022-08-01 | 2024-01-22
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | BED-833 | Rel.& Inst. WMs on Flatland Ave btwn Ralph Ave & E 76 St BKL | 4 | BID AWARD AND REGISTER CONTRCT | 2024-01-23 | 2024-10-18 | 2024-01-23 | 2024-10-18
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | BED-833 | Rel.& Inst. WMs on Flatland Ave btwn Ralph Ave & E 76 St BKL | 5 | CONSTRUCTION TO 25% | 2024-10-19 | 2025-10-13 | 2024-10-19 | 2025-10-13
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | BED-833 | Rel.& Inst. WMs on Flatland Ave btwn Ralph Ave & E 76 St BKL | 6 | CONSTRUCTION TO 50% | 2025-10-14 | 2026-10-08 | 2025-10-14 | 2026-10-08
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | BED-833 | Rel.& Inst. WMs on Flatland Ave btwn Ralph Ave & E 76 St BKL | 7 | CONSTRUCTION TO 75% | 2026-10-09 | 2027-10-03 | 2026-10-09 | 2027-10-03
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | BED-833 | Rel.& Inst. WMs on Flatland Ave btwn Ralph Ave & E 76 St BKL | 8 | ORIGINAL EQUIP & FURNISHING | 2027-10-04 | 2028-06-29 | 2027-10-04 | 2028-06-29
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | BED-833 | Rel.& Inst. WMs on Flatland Ave btwn Ralph Ave & E 76 St BKL | 9 | SUBSTANTIAL COMPLETION | 2028-06-30 | 2028-12-26 | 2028-06-30 | 2028-12-26
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | BED-833 | Rel.& Inst. WMs on Flatland Ave btwn Ralph Ave & E 76 St BKL | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2028-12-27 | 2029-03-26 | 2028-12-27 | 2029-03-26
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CI-113-L | RECONSTRUCT (4) ENGINE GENERATOR CONTROL SYSTEM | 1 | DEVELOP SCOPE | 2016-06-01 | 2017-02-25 | 2016-06-01 | 2017-02-25
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CI-113-L | RECONSTRUCT (4) ENGINE GENERATOR CONTROL SYSTEM | 2 | PRELIMINARY DESIGN | 2017-02-26 | 2018-02-20 | 2017-02-26 | 2018-02-20
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CI-113-L | RECONSTRUCT (4) ENGINE GENERATOR CONTROL SYSTEM | 3 | FINAL DESIGN | 2018-02-21 | 2019-08-14 | 2018-02-21 | 2019-08-14
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CI-113-L | RECONSTRUCT (4) ENGINE GENERATOR CONTROL SYSTEM | 4 | BID AWARD AND REGISTER CONTRCT | 2019-08-15 | 2020-05-10 | 2019-08-15 | 2020-05-10
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CI-113-L | RECONSTRUCT (4) ENGINE GENERATOR CONTROL SYSTEM | 5 | CONSTRUCTION TO 25% | 2020-05-11 | 2021-05-05 | 2020-05-11 | 2021-05-05
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CI-113-L | RECONSTRUCT (4) ENGINE GENERATOR CONTROL SYSTEM | 6 | CONSTRUCTION TO 50% | 2021-05-06 | 2022-04-30 | 2021-05-06 | 2022-04-30
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CI-113-L | RECONSTRUCT (4) ENGINE GENERATOR CONTROL SYSTEM | 7 | CONSTRUCTION TO 75% | 2022-05-01 | 2023-04-25 | 2022-05-01 | 2023-04-25
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CI-113-L | RECONSTRUCT (4) ENGINE GENERATOR CONTROL SYSTEM | 8 | ORIGINAL EQUIP & FURNISHING | 2023-04-26 | 2024-01-20 | 2023-04-26 | 2024-01-20
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CI-113-L | RECONSTRUCT (4) ENGINE GENERATOR CONTROL SYSTEM | 9 | SUBSTANTIAL COMPLETION | 2024-01-21 | 2024-07-18 | 2024-01-21 | 2024-07-18
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CI-113-L | RECONSTRUCT (4) ENGINE GENERATOR CONTROL SYSTEM | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-07-19 | 2024-10-16 | 2024-07-19 | 2024-10-16
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CI-119-L | RECONSTRUCTION OF GATES & MSP MOTORS & CONTROLS @ C.I. | 1 | DEVELOP SCOPE | 2022-06-15 | 2023-03-11 | 2018-07-01 | 2019-03-27
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CI-119-L | RECONSTRUCTION OF GATES & MSP MOTORS & CONTROLS @ C.I. | 2 | PRELIMINARY DESIGN | 2023-03-12 | 2024-03-05 | 2019-03-28 | 2020-03-21
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CI-119-L | RECONSTRUCTION OF GATES & MSP MOTORS & CONTROLS @ C.I. | 3 | FINAL DESIGN | 2024-03-06 | 2025-08-27 | 2020-03-22 | 2021-09-12
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CI-119-L | RECONSTRUCTION OF GATES & MSP MOTORS & CONTROLS @ C.I. | 4 | BID AWARD AND REGISTER CONTRCT | 2025-08-28 | 2026-05-24 | 2021-09-13 | 2022-06-09
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CI-119-L | RECONSTRUCTION OF GATES & MSP MOTORS & CONTROLS @ C.I. | 5 | CONSTRUCTION TO 25% | 2026-05-25 | 2027-05-19 | 2022-06-10 | 2023-06-04
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CI-119-L | RECONSTRUCTION OF GATES & MSP MOTORS & CONTROLS @ C.I. | 6 | CONSTRUCTION TO 50% | 2027-05-20 | 2028-05-13 | 2023-06-05 | 2024-05-29
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CI-119-L | RECONSTRUCTION OF GATES & MSP MOTORS & CONTROLS @ C.I. | 7 | CONSTRUCTION TO 75% | 2028-05-14 | 2029-05-08 | 2024-05-30 | 2025-05-24
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CI-119-L | RECONSTRUCTION OF GATES & MSP MOTORS & CONTROLS @ C.I. | 8 | ORIGINAL EQUIP & FURNISHING | 2029-05-09 | 2030-02-02 | 2025-05-25 | 2026-02-18
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CI-119-L | RECONSTRUCTION OF GATES & MSP MOTORS & CONTROLS @ C.I. | 9 | SUBSTANTIAL COMPLETION | 2030-02-03 | 2030-08-01 | 2026-02-19 | 2026-08-17
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CI-119-L | RECONSTRUCTION OF GATES & MSP MOTORS & CONTROLS @ C.I. | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2030-08-02 | 2030-10-30 | 2026-08-18 | 2026-11-15
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CI-140-L | INSTALL ODOR CONTROL PANELS FOR AERATION SCRUBBER SYSTEM | 1 | FINAL DESIGN | 2027-06-01 | 2028-11-21 | 2027-06-01 | 2028-11-21
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CI-140-L | INSTALL ODOR CONTROL PANELS FOR AERATION SCRUBBER SYSTEM | 2 | CONSTRUCTION TO 25% | 2028-11-22 | 2029-07-19 | 2028-11-22 | 2029-07-19
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CI-140-L | INSTALL ODOR CONTROL PANELS FOR AERATION SCRUBBER SYSTEM | 3 | CONSTRUCTION TO 50% | 2029-07-20 | 2030-03-16 | 2029-07-20 | 2030-03-16
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CI-140-L | INSTALL ODOR CONTROL PANELS FOR AERATION SCRUBBER SYSTEM | 4 | CONSTRUCTION TO 75% | 2030-03-17 | 2030-11-11 | 2030-03-17 | 2030-11-11
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-GC-SFS | CONSTRUCTION OF GOWANUS CSO RETENTION FAC SUPERFUND SITE | 1 | DEVELOP SCOPE | 2015-07-01 | 2016-03-26 | 2015-07-01 | 2016-03-26
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-GC-SFS | CONSTRUCTION OF GOWANUS CSO RETENTION FAC SUPERFUND SITE | 2 | PRELIMINARY DESIGN | 2016-03-27 | 2017-03-21 | 2016-03-27 | 2017-03-21
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-GC-SFS | CONSTRUCTION OF GOWANUS CSO RETENTION FAC SUPERFUND SITE | 3 | FINAL DESIGN | 2017-03-22 | 2018-09-12 | 2017-03-22 | 2018-09-12
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-GC-SFS | CONSTRUCTION OF GOWANUS CSO RETENTION FAC SUPERFUND SITE | 4 | BID AWARD AND REGISTER CONTRCT | 2018-09-13 | 2019-06-09 | 2018-09-13 | 2019-06-09
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-GC-SFS | CONSTRUCTION OF GOWANUS CSO RETENTION FAC SUPERFUND SITE | 5 | CONSTRUCTION TO 25% | 2019-06-10 | 2020-06-03 | 2019-06-10 | 2020-06-03
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-GC-SFS | CONSTRUCTION OF GOWANUS CSO RETENTION FAC SUPERFUND SITE | 6 | CONSTRUCTION TO 50% | 2020-06-04 | 2021-05-29 | 2020-06-04 | 2021-05-29
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-GC-SFS | CONSTRUCTION OF GOWANUS CSO RETENTION FAC SUPERFUND SITE | 7 | CONSTRUCTION TO 75% | 2021-05-30 | 2022-05-24 | 2021-05-30 | 2022-05-24
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-GC-SFS | CONSTRUCTION OF GOWANUS CSO RETENTION FAC SUPERFUND SITE | 8 | ORIGINAL EQUIP & FURNISHING | 2022-05-25 | 2023-02-18 | 2022-05-25 | 2023-02-18
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-GC-SFS | CONSTRUCTION OF GOWANUS CSO RETENTION FAC SUPERFUND SITE | 9 | SUBSTANTIAL COMPLETION | 2023-02-19 | 2027-08-16 | 2023-02-19 | 2027-08-16
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-GC-SFS | CONSTRUCTION OF GOWANUS CSO RETENTION FAC SUPERFUND SITE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2027-08-17 | 2027-11-14 | 2027-08-17 | 2027-11-14
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-GC | FLUSHING TUNNEL REACTIVATION & GOWANUS CANAL FORCE MAIN | 1 | DEVELOP SCOPE | 2001-03-15 | 2001-12-09 | 2001-03-15 | 2001-12-09
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-GC | FLUSHING TUNNEL REACTIVATION & GOWANUS CANAL FORCE MAIN | 2 | PRELIMINARY DESIGN | 2001-12-10 | 2002-12-04 | 2001-12-10 | 2002-12-04
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-GC | FLUSHING TUNNEL REACTIVATION & GOWANUS CANAL FORCE MAIN | 3 | FINAL DESIGN | 2002-12-05 | 2004-05-27 | 2002-12-05 | 2004-05-27
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-GC | FLUSHING TUNNEL REACTIVATION & GOWANUS CANAL FORCE MAIN | 4 | BID AWARD AND REGISTER CONTRCT | 2004-05-28 | 2005-02-21 | 2004-05-28 | 2005-02-21
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-GC | FLUSHING TUNNEL REACTIVATION & GOWANUS CANAL FORCE MAIN | 5 | CONSTRUCTION TO 25% | 2005-02-22 | 2006-02-16 | 2005-02-22 | 2006-02-16
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-GC | FLUSHING TUNNEL REACTIVATION & GOWANUS CANAL FORCE MAIN | 6 | CONSTRUCTION TO 50% | 2006-02-17 | 2007-02-11 | 2006-02-17 | 2007-02-11
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-GC | FLUSHING TUNNEL REACTIVATION & GOWANUS CANAL FORCE MAIN | 7 | CONSTRUCTION TO 75% | 2007-02-12 | 2008-02-06 | 2007-02-12 | 2008-02-06
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-GC | FLUSHING TUNNEL REACTIVATION & GOWANUS CANAL FORCE MAIN | 8 | ORIGINAL EQUIP & FURNISHING | 2008-02-07 | 2008-11-02 | 2008-02-07 | 2008-11-02
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-GC | FLUSHING TUNNEL REACTIVATION & GOWANUS CANAL FORCE MAIN | 9 | SUBSTANTIAL COMPLETION | 2008-11-03 | 2009-05-01 | 2008-11-03 | 2021-04-28
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-GC | FLUSHING TUNNEL REACTIVATION & GOWANUS CANAL FORCE MAIN | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2009-05-02 | 2009-07-30 | 2021-04-29 | 2021-07-27
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-GC-SP | CONSTRUCTION OF GOWANUS CANAL PILOT SPONGE PARK | 1 | DEVELOP SCOPE | 2014-10-01 | 2014-12-29 | 2014-10-01 | 2014-12-29
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-GC-SP | CONSTRUCTION OF GOWANUS CANAL PILOT SPONGE PARK | 2 | PRELIMINARY DESIGN | 2014-12-30 | 2015-04-28 | 2014-12-30 | 2015-04-28
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-GC-SP | CONSTRUCTION OF GOWANUS CANAL PILOT SPONGE PARK | 3 | FINAL DESIGN | 2015-04-29 | 2015-10-25 | 2015-04-29 | 2015-10-25
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-GC-SP | CONSTRUCTION OF GOWANUS CANAL PILOT SPONGE PARK | 4 | BID AWARD AND REGISTER CONTRCT | 2015-10-26 | 2016-01-23 | 2015-10-26 | 2016-01-23
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-GC-SP | CONSTRUCTION OF GOWANUS CANAL PILOT SPONGE PARK | 5 | CONSTRUCTION TO 25% | 2016-01-24 | 2016-05-22 | 2016-01-24 | 2016-05-22
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-GC-SP | CONSTRUCTION OF GOWANUS CANAL PILOT SPONGE PARK | 6 | CONSTRUCTION TO 50% | 2016-05-23 | 2016-09-19 | 2016-05-23 | 2016-09-19
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-GC-SP | CONSTRUCTION OF GOWANUS CANAL PILOT SPONGE PARK | 7 | CONSTRUCTION TO 75% | 2016-09-20 | 2017-01-17 | 2016-09-20 | 2017-01-17
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-GC-SP | CONSTRUCTION OF GOWANUS CANAL PILOT SPONGE PARK | 8 | ORIGINAL EQUIP & FURNISHING | 2017-01-18 | 2017-04-17 | 2017-01-18 | 2017-04-17
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-GC-SP | CONSTRUCTION OF GOWANUS CANAL PILOT SPONGE PARK | 9 | SUBSTANTIAL COMPLETION | 2017-04-18 | 2017-06-16 | 2017-04-18 | 2017-06-16
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-GC-SP | CONSTRUCTION OF GOWANUS CANAL PILOT SPONGE PARK | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-06-17 | 2017-07-16 | 2020-06-17 | 2020-07-16
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-PA-ECR | ECOLOGICAL RESTORATION | 1 | DEVELOP SCOPE | 2009-01-01 | 2009-09-27 | 2014-01-15 | 2014-10-11
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-PA-ECR | ECOLOGICAL RESTORATION | 2 | PRELIMINARY DESIGN | 2009-09-28 | 2010-09-22 | 2014-10-12 | 2015-10-06
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-PA-ECR | ECOLOGICAL RESTORATION | 3 | FINAL DESIGN | 2010-09-23 | 2012-03-15 | 2015-10-07 | 2017-03-29
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-PA-ECR | ECOLOGICAL RESTORATION | 4 | BID AWARD AND REGISTER CONTRCT | 2012-03-16 | 2012-12-10 | 2017-03-30 | 2017-12-24
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-PA-ECR | ECOLOGICAL RESTORATION | 5 | CONSTRUCTION TO 25% | 2012-12-11 | 2013-12-05 | 2017-12-25 | 2018-12-19
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-PA-ECR | ECOLOGICAL RESTORATION | 6 | CONSTRUCTION TO 50% | 2013-12-06 | 2014-11-30 | 2018-12-20 | 2019-12-14
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-PA-ECR | ECOLOGICAL RESTORATION | 7 | CONSTRUCTION TO 75% | 2014-12-01 | 2015-11-25 | 2019-12-15 | 2020-12-08
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-PA-ECR | ECOLOGICAL RESTORATION | 8 | ORIGINAL EQUIP & FURNISHING | 2015-11-26 | 2016-08-21 | 2020-12-09 | 2021-09-04
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-PA-ECR | ECOLOGICAL RESTORATION | 9 | SUBSTANTIAL COMPLETION | 2016-08-22 | 2017-02-17 | 2021-09-05 | 2022-03-03
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-PA-ECR | ECOLOGICAL RESTORATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-02-18 | 2017-05-18 | 2022-03-04 | 2022-06-01
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SEKS22 | Reconstruction of Existing Sewers, South Brooklyn | 1 | DEVELOP SCOPE | 2020-11-09 | 2021-02-06 | 2020-11-09 | 2021-02-06
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SEKS22 | Reconstruction of Existing Sewers, South Brooklyn | 2 | PRELIMINARY DESIGN | 2021-02-07 | 2021-06-06 | 2021-02-07 | 2021-06-06
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SEKS22 | Reconstruction of Existing Sewers, South Brooklyn | 3 | FINAL DESIGN | 2021-06-07 | 2021-12-03 | 2021-06-07 | 2021-12-03
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SEKS22 | Reconstruction of Existing Sewers, South Brooklyn | 4 | BID AWARD AND REGISTER CONTRCT | 2021-12-04 | 2022-03-03 | 2021-12-04 | 2022-03-03
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SEKS22 | Reconstruction of Existing Sewers, South Brooklyn | 5 | CONSTRUCTION TO 25% | 2022-03-04 | 2022-07-01 | 2022-03-04 | 2022-07-01
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SEKS22 | Reconstruction of Existing Sewers, South Brooklyn | 6 | CONSTRUCTION TO 50% | 2022-07-02 | 2022-10-29 | 2022-07-02 | 2022-10-29
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SEKS22 | Reconstruction of Existing Sewers, South Brooklyn | 7 | CONSTRUCTION TO 75% | 2022-10-30 | 2023-02-26 | 2022-10-30 | 2023-02-26
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SEKS22 | Reconstruction of Existing Sewers, South Brooklyn | 8 | ORIGINAL EQUIP & FURNISHING | 2023-02-27 | 2023-05-27 | 2023-02-27 | 2023-05-27
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SEKS22 | Reconstruction of Existing Sewers, South Brooklyn | 9 | SUBSTANTIAL COMPLETION | 2023-05-28 | 2023-07-26 | 2023-05-28 | 2023-07-26
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SEKS22 | Reconstruction of Existing Sewers, South Brooklyn | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-07-27 | 2023-08-25 | 2023-07-27 | 2023-08-25
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-RH-GR | GI - GREEN ROOF INSTALLATION AT RED HOOK HOUSES IN BKLYN | 1 | DEVELOP SCOPE | 2022-01-01 | 2022-03-31 | 2022-01-01 | 2022-03-31
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-RH-GR | GI - GREEN ROOF INSTALLATION AT RED HOOK HOUSES IN BKLYN | 2 | PRELIMINARY DESIGN | 2022-04-01 | 2022-07-29 | 2022-04-01 | 2022-07-29
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-RH-GR | GI - GREEN ROOF INSTALLATION AT RED HOOK HOUSES IN BKLYN | 3 | FINAL DESIGN | 2022-07-30 | 2023-01-25 | 2022-07-30 | 2023-01-25
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-RH-GR | GI - GREEN ROOF INSTALLATION AT RED HOOK HOUSES IN BKLYN | 4 | BID AWARD AND REGISTER CONTRCT | 2023-01-26 | 2023-04-25 | 2023-01-26 | 2023-04-25
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-RH-GR | GI - GREEN ROOF INSTALLATION AT RED HOOK HOUSES IN BKLYN | 5 | CONSTRUCTION TO 25% | 2023-04-26 | 2023-08-23 | 2023-04-26 | 2023-08-23
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-RH-GR | GI - GREEN ROOF INSTALLATION AT RED HOOK HOUSES IN BKLYN | 6 | CONSTRUCTION TO 50% | 2023-08-24 | 2023-12-21 | 2023-08-24 | 2023-12-21
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-RH-GR | GI - GREEN ROOF INSTALLATION AT RED HOOK HOUSES IN BKLYN | 7 | CONSTRUCTION TO 75% | 2023-12-22 | 2024-04-19 | 2023-12-22 | 2024-04-19
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-RH-GR | GI - GREEN ROOF INSTALLATION AT RED HOOK HOUSES IN BKLYN | 8 | ORIGINAL EQUIP & FURNISHING | 2024-04-20 | 2024-07-18 | 2024-04-20 | 2024-07-18
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-RH-GR | GI - GREEN ROOF INSTALLATION AT RED HOOK HOUSES IN BKLYN | 9 | SUBSTANTIAL COMPLETION | 2024-07-19 | 2024-09-16 | 2024-07-19 | 2024-09-16
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-RH-GR | GI - GREEN ROOF INSTALLATION AT RED HOOK HOUSES IN BKLYN | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-09-17 | 2024-10-16 | 2024-09-17 | 2024-10-16
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | GK-PD-A | GI - INSTALL GI AT NYPD PCTS 75, 77 & 115 PARKING LOTS | 1 | FINAL DESIGN | 2019-06-30 | 2020-12-20 | 2019-06-30 | 2020-12-20
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | GK-PD-A | GI - INSTALL GI AT NYPD PCTS 75, 77 & 115 PARKING LOTS | 2 | CONSTRUCTION TO 25% | 2020-12-21 | 2021-08-17 | 2020-12-21 | 2021-08-17
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | GK-PD-A | GI - INSTALL GI AT NYPD PCTS 75, 77 & 115 PARKING LOTS | 3 | CONSTRUCTION TO 50% | 2021-08-18 | 2022-04-14 | 2021-08-18 | 2022-04-14
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | GK-PD-A | GI - INSTALL GI AT NYPD PCTS 75, 77 & 115 PARKING LOTS | 4 | CONSTRUCTION TO 75% | 2022-04-15 | 2022-12-10 | 2022-04-15 | 2022-12-10
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | GK-PD-B | GI - INSTALL GI AT NYPD PCTS 73, 79 & 81 PARKING LOTS | 1 | FINAL DESIGN | 2019-06-30 | 2020-12-20 | 2021-12-20 | 2023-06-12
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | GK-PD-B | GI - INSTALL GI AT NYPD PCTS 73, 79 & 81 PARKING LOTS | 2 | CONSTRUCTION TO 25% | 2020-12-21 | 2021-08-17 | 2023-06-13 | 2024-02-07
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | GK-PD-B | GI - INSTALL GI AT NYPD PCTS 73, 79 & 81 PARKING LOTS | 3 | CONSTRUCTION TO 50% | 2021-08-18 | 2022-04-14 | 2024-02-08 | 2024-10-04
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | GK-PD-B | GI - INSTALL GI AT NYPD PCTS 73, 79 & 81 PARKING LOTS | 4 | CONSTRUCTION TO 75% | 2022-04-15 | 2022-12-10 | 2024-10-05 | 2025-06-01
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | GK-PD-C | GI - INSTALL GI AT NYPD 83 PRECINCT PARKING LOTS | 1 | FINAL DESIGN | 2019-06-30 | 2020-12-20 | 2022-12-20 | 2024-06-11
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | GK-PD-C | GI - INSTALL GI AT NYPD 83 PRECINCT PARKING LOTS | 2 | CONSTRUCTION TO 25% | 2020-12-21 | 2021-08-17 | 2024-06-12 | 2025-02-06
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | GK-PD-C | GI - INSTALL GI AT NYPD 83 PRECINCT PARKING LOTS | 3 | CONSTRUCTION TO 50% | 2021-08-18 | 2022-04-14 | 2025-02-07 | 2025-10-04
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | GK-PD-C | GI - INSTALL GI AT NYPD 83 PRECINCT PARKING LOTS | 4 | CONSTRUCTION TO 75% | 2022-04-15 | 2022-12-10 | 2025-10-05 | 2026-06-01
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | GK-PD-D | GI - INSTALL GI AT NYPD PCTS 43, 71,107 & FLUSHING ARMORY | 1 | FINAL DESIGN | 2019-06-30 | 2020-12-20 | 2022-12-20 | 2024-06-11
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | GK-PD-D | GI - INSTALL GI AT NYPD PCTS 43, 71,107 & FLUSHING ARMORY | 2 | CONSTRUCTION TO 25% | 2020-12-21 | 2021-08-17 | 2024-06-12 | 2025-02-06
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | GK-PD-D | GI - INSTALL GI AT NYPD PCTS 43, 71,107 & FLUSHING ARMORY | 3 | CONSTRUCTION TO 50% | 2021-08-18 | 2022-04-14 | 2025-02-07 | 2025-10-04
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | GK-PD-D | GI - INSTALL GI AT NYPD PCTS 43, 71,107 & FLUSHING ARMORY | 4 | CONSTRUCTION TO 75% | 2022-04-15 | 2022-12-10 | 2025-10-05 | 2026-06-01
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-159 | TRC - NEWTOWN CREEK DECLORINATION FACILITY | 1 | DEVELOP SCOPE | 2015-07-01 | 2016-03-26 | 2015-07-01 | 2016-03-26
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-159 | TRC - NEWTOWN CREEK DECLORINATION FACILITY | 2 | PRELIMINARY DESIGN | 2016-03-27 | 2017-03-21 | 2016-03-27 | 2017-03-21
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-159 | TRC - NEWTOWN CREEK DECLORINATION FACILITY | 3 | FINAL DESIGN | 2017-03-22 | 2018-09-12 | 2017-03-22 | 2018-09-12
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-159 | TRC - NEWTOWN CREEK DECLORINATION FACILITY | 4 | BID AWARD AND REGISTER CONTRCT | 2018-09-13 | 2019-06-09 | 2018-09-13 | 2019-06-09
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-159 | TRC - NEWTOWN CREEK DECLORINATION FACILITY | 5 | CONSTRUCTION TO 25% | 2019-06-10 | 2020-06-03 | 2019-06-10 | 2020-06-03
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-159 | TRC - NEWTOWN CREEK DECLORINATION FACILITY | 6 | CONSTRUCTION TO 50% | 2020-06-04 | 2021-05-29 | 2020-06-04 | 2021-05-29
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-159 | TRC - NEWTOWN CREEK DECLORINATION FACILITY | 7 | CONSTRUCTION TO 75% | 2021-05-30 | 2022-05-24 | 2021-05-30 | 2022-05-24
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-159 | TRC - NEWTOWN CREEK DECLORINATION FACILITY | 8 | ORIGINAL EQUIP & FURNISHING | 2022-05-25 | 2023-02-18 | 2022-05-25 | 2023-02-18
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-159 | TRC - NEWTOWN CREEK DECLORINATION FACILITY | 9 | SUBSTANTIAL COMPLETION | 2023-02-19 | 2023-08-17 | 2023-02-19 | 2023-08-17
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-159 | TRC - NEWTOWN CREEK DECLORINATION FACILITY | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-08-18 | 2023-11-15 | 2023-08-18 | 2023-11-15
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-163 | CONSTRUCTION OF PERIMETER FENCE AT NEWTOWN CREEK WPCP | 1 | DEVELOP SCOPE | 2018-06-01 | 2019-02-25 | 2018-06-01 | 2019-02-25
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-163 | CONSTRUCTION OF PERIMETER FENCE AT NEWTOWN CREEK WPCP | 2 | PRELIMINARY DESIGN | 2019-02-26 | 2020-02-20 | 2019-02-26 | 2020-02-20
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-163 | CONSTRUCTION OF PERIMETER FENCE AT NEWTOWN CREEK WPCP | 3 | FINAL DESIGN | 2020-02-21 | 2021-08-13 | 2020-02-21 | 2021-08-13
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-163 | CONSTRUCTION OF PERIMETER FENCE AT NEWTOWN CREEK WPCP | 4 | BID AWARD AND REGISTER CONTRCT | 2021-08-14 | 2022-05-10 | 2021-08-14 | 2022-05-10
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-163 | CONSTRUCTION OF PERIMETER FENCE AT NEWTOWN CREEK WPCP | 5 | CONSTRUCTION TO 25% | 2022-05-11 | 2023-05-05 | 2022-05-11 | 2023-05-05
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-163 | CONSTRUCTION OF PERIMETER FENCE AT NEWTOWN CREEK WPCP | 6 | CONSTRUCTION TO 50% | 2023-05-06 | 2024-04-29 | 2023-05-06 | 2024-04-29
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-163 | CONSTRUCTION OF PERIMETER FENCE AT NEWTOWN CREEK WPCP | 7 | CONSTRUCTION TO 75% | 2024-04-30 | 2025-04-24 | 2024-04-30 | 2025-04-24
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-163 | CONSTRUCTION OF PERIMETER FENCE AT NEWTOWN CREEK WPCP | 8 | ORIGINAL EQUIP & FURNISHING | 2025-04-25 | 2026-01-19 | 2025-04-25 | 2026-01-19
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-163 | CONSTRUCTION OF PERIMETER FENCE AT NEWTOWN CREEK WPCP | 9 | SUBSTANTIAL COMPLETION | 2026-01-20 | 2026-07-18 | 2026-01-20 | 2026-07-18
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-163 | CONSTRUCTION OF PERIMETER FENCE AT NEWTOWN CREEK WPCP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2026-07-19 | 2026-10-16 | 2026-07-19 | 2026-10-16
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-176-L | RECONSTRUCTION OF CCTV SYSTEM @ THE NEWTOWN CREEK WWTP | 1 | DEVELOP SCOPE | 2019-06-01 | 2019-08-29 | 2019-06-01 | 2019-08-29
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-176-L | RECONSTRUCTION OF CCTV SYSTEM @ THE NEWTOWN CREEK WWTP | 2 | PRELIMINARY DESIGN | 2019-08-30 | 2019-12-27 | 2019-08-30 | 2019-12-27
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-176-L | RECONSTRUCTION OF CCTV SYSTEM @ THE NEWTOWN CREEK WWTP | 3 | FINAL DESIGN | 2019-12-28 | 2020-06-24 | 2019-12-28 | 2020-06-24
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-176-L | RECONSTRUCTION OF CCTV SYSTEM @ THE NEWTOWN CREEK WWTP | 4 | BID AWARD AND REGISTER CONTRCT | 2020-06-25 | 2020-09-22 | 2020-06-25 | 2020-09-22
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-176-L | RECONSTRUCTION OF CCTV SYSTEM @ THE NEWTOWN CREEK WWTP | 5 | CONSTRUCTION TO 25% | 2020-09-23 | 2021-01-20 | 2020-09-23 | 2021-01-20
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-176-L | RECONSTRUCTION OF CCTV SYSTEM @ THE NEWTOWN CREEK WWTP | 6 | CONSTRUCTION TO 50% | 2021-01-21 | 2021-05-20 | 2021-01-21 | 2021-05-20
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-176-L | RECONSTRUCTION OF CCTV SYSTEM @ THE NEWTOWN CREEK WWTP | 7 | CONSTRUCTION TO 75% | 2021-05-21 | 2021-09-17 | 2021-05-21 | 2021-09-17
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-176-L | RECONSTRUCTION OF CCTV SYSTEM @ THE NEWTOWN CREEK WWTP | 8 | ORIGINAL EQUIP & FURNISHING | 2021-09-18 | 2021-12-16 | 2021-09-18 | 2021-12-16
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-176-L | RECONSTRUCTION OF CCTV SYSTEM @ THE NEWTOWN CREEK WWTP | 9 | SUBSTANTIAL COMPLETION | 2021-12-17 | 2022-02-14 | 2021-12-17 | 2022-02-14
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-176-L | RECONSTRUCTION OF CCTV SYSTEM @ THE NEWTOWN CREEK WWTP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-02-15 | 2022-03-16 | 2022-02-15 | 2022-03-16
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-50 | NEWTOWN CREEK WPCP SLUDGE LOADING DOCKS | 1 | DEVELOP SCOPE | 1996-03-15 | 1996-12-09 | 2011-11-01 | 2012-07-27
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-50 | NEWTOWN CREEK WPCP SLUDGE LOADING DOCKS | 2 | PRELIMINARY DESIGN | 1996-12-10 | 1997-12-04 | 2012-07-28 | 2013-07-22
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-50 | NEWTOWN CREEK WPCP SLUDGE LOADING DOCKS | 3 | FINAL DESIGN | 1997-12-05 | 1999-05-28 | 2013-07-23 | 2015-01-13
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-50 | NEWTOWN CREEK WPCP SLUDGE LOADING DOCKS | 4 | BID AWARD AND REGISTER CONTRCT | 1999-05-29 | 2000-02-22 | 2015-01-14 | 2015-10-10
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-50 | NEWTOWN CREEK WPCP SLUDGE LOADING DOCKS | 5 | CONSTRUCTION TO 25% | 2000-02-23 | 2001-02-16 | 2015-10-11 | 2016-10-04
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-50 | NEWTOWN CREEK WPCP SLUDGE LOADING DOCKS | 6 | CONSTRUCTION TO 50% | 2001-02-17 | 2002-02-11 | 2016-10-05 | 2017-09-29
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-50 | NEWTOWN CREEK WPCP SLUDGE LOADING DOCKS | 7 | CONSTRUCTION TO 75% | 2002-02-12 | 2003-02-06 | 2017-09-30 | 2018-09-24
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-50 | NEWTOWN CREEK WPCP SLUDGE LOADING DOCKS | 8 | ORIGINAL EQUIP & FURNISHING | 2003-02-07 | 2003-11-03 | 2018-09-25 | 2019-06-21
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-50 | NEWTOWN CREEK WPCP SLUDGE LOADING DOCKS | 9 | SUBSTANTIAL COMPLETION | 2003-11-04 | 2004-05-01 | 2019-06-22 | 2023-12-17
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-50 | NEWTOWN CREEK WPCP SLUDGE LOADING DOCKS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2004-05-02 | 2004-07-30 | 2023-12-18 | 2024-03-16
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-52 | CONSTRUCTION OF WHALE CREEK FLOATING DOCK AT NEWTOWN CREEK | 1 | FINAL DESIGN | 2018-06-15 | 2019-12-06 | 2018-06-15 | 2019-12-06
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-52 | CONSTRUCTION OF WHALE CREEK FLOATING DOCK AT NEWTOWN CREEK | 2 | CONSTRUCTION TO 25% | 2019-12-07 | 2020-08-02 | 2019-12-07 | 2020-08-02
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-52 | CONSTRUCTION OF WHALE CREEK FLOATING DOCK AT NEWTOWN CREEK | 3 | CONSTRUCTION TO 50% | 2020-08-03 | 2021-03-30 | 2020-08-03 | 2021-03-30
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-52 | CONSTRUCTION OF WHALE CREEK FLOATING DOCK AT NEWTOWN CREEK | 4 | CONSTRUCTION TO 75% | 2021-03-31 | 2021-11-25 | 2021-03-31 | 2021-11-25
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-ASB-TB | NEWTOWN CREEK GRAVITY THICKENER BLDG ASBESTOS ABATEMENT | 1 | DEVELOP SCOPE | 2020-06-01 | 2021-02-25 | 2020-06-01 | 2021-02-25
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-ASB-TB | NEWTOWN CREEK GRAVITY THICKENER BLDG ASBESTOS ABATEMENT | 2 | PRELIMINARY DESIGN | 2021-02-26 | 2022-02-20 | 2021-02-26 | 2022-02-20
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-ASB-TB | NEWTOWN CREEK GRAVITY THICKENER BLDG ASBESTOS ABATEMENT | 3 | FINAL DESIGN | 2022-02-21 | 2023-08-14 | 2022-02-21 | 2023-08-14
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-ASB-TB | NEWTOWN CREEK GRAVITY THICKENER BLDG ASBESTOS ABATEMENT | 4 | BID AWARD AND REGISTER CONTRCT | 2023-08-15 | 2024-05-10 | 2023-08-15 | 2024-05-10
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-ASB-TB | NEWTOWN CREEK GRAVITY THICKENER BLDG ASBESTOS ABATEMENT | 5 | CONSTRUCTION TO 25% | 2024-05-11 | 2025-05-05 | 2024-05-11 | 2025-05-05
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-ASB-TB | NEWTOWN CREEK GRAVITY THICKENER BLDG ASBESTOS ABATEMENT | 6 | CONSTRUCTION TO 50% | 2025-05-06 | 2026-04-30 | 2025-05-06 | 2026-04-30
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-ASB-TB | NEWTOWN CREEK GRAVITY THICKENER BLDG ASBESTOS ABATEMENT | 7 | CONSTRUCTION TO 75% | 2026-05-01 | 2027-04-25 | 2026-05-01 | 2027-04-25
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-ASB-TB | NEWTOWN CREEK GRAVITY THICKENER BLDG ASBESTOS ABATEMENT | 8 | ORIGINAL EQUIP & FURNISHING | 2027-04-26 | 2028-01-20 | 2027-04-26 | 2028-01-20
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-ASB-TB | NEWTOWN CREEK GRAVITY THICKENER BLDG ASBESTOS ABATEMENT | 9 | SUBSTANTIAL COMPLETION | 2028-01-21 | 2028-07-18 | 2028-01-21 | 2028-07-18
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-ASB-TB | NEWTOWN CREEK GRAVITY THICKENER BLDG ASBESTOS ABATEMENT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2028-07-19 | 2028-10-16 | 2028-07-19 | 2028-10-16
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-112-L | REPLACE MAIN SEWAGE PUMPS & PIPING AT OWLS HEAD WPCP | 1 | DEVELOP SCOPE | 2019-07-01 | 2020-03-26 | 2019-07-01 | 2020-03-26
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-112-L | REPLACE MAIN SEWAGE PUMPS & PIPING AT OWLS HEAD WPCP | 2 | PRELIMINARY DESIGN | 2020-03-27 | 2021-03-21 | 2020-03-27 | 2021-03-21
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-112-L | REPLACE MAIN SEWAGE PUMPS & PIPING AT OWLS HEAD WPCP | 3 | FINAL DESIGN | 2021-03-22 | 2022-09-12 | 2021-03-22 | 2022-09-12
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-112-L | REPLACE MAIN SEWAGE PUMPS & PIPING AT OWLS HEAD WPCP | 4 | BID AWARD AND REGISTER CONTRCT | 2022-09-13 | 2023-06-09 | 2022-09-13 | 2023-06-09
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-112-L | REPLACE MAIN SEWAGE PUMPS & PIPING AT OWLS HEAD WPCP | 5 | CONSTRUCTION TO 25% | 2023-06-10 | 2024-06-03 | 2023-06-10 | 2024-06-03
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-112-L | REPLACE MAIN SEWAGE PUMPS & PIPING AT OWLS HEAD WPCP | 6 | CONSTRUCTION TO 50% | 2024-06-04 | 2025-05-29 | 2024-06-04 | 2025-05-29
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-112-L | REPLACE MAIN SEWAGE PUMPS & PIPING AT OWLS HEAD WPCP | 7 | CONSTRUCTION TO 75% | 2025-05-30 | 2026-05-24 | 2025-05-30 | 2026-05-24
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-112-L | REPLACE MAIN SEWAGE PUMPS & PIPING AT OWLS HEAD WPCP | 8 | ORIGINAL EQUIP & FURNISHING | 2026-05-25 | 2027-02-18 | 2026-05-25 | 2027-02-18
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-112-L | REPLACE MAIN SEWAGE PUMPS & PIPING AT OWLS HEAD WPCP | 9 | SUBSTANTIAL COMPLETION | 2027-02-19 | 2027-08-17 | 2027-02-19 | 2027-08-17
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-112-L | REPLACE MAIN SEWAGE PUMPS & PIPING AT OWLS HEAD WPCP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2027-08-18 | 2027-11-15 | 2027-08-18 | 2027-11-15
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-88-L | RECONSTRUCTION OF FINAL TANKS AT OWLS HEAD WPCP | 1 | DEVELOP SCOPE | 2017-10-15 | 2018-07-11 | 2016-01-17 | 2016-10-12
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-88-L | RECONSTRUCTION OF FINAL TANKS AT OWLS HEAD WPCP | 2 | PRELIMINARY DESIGN | 2018-07-12 | 2019-07-06 | 2016-10-13 | 2017-10-07
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-88-L | RECONSTRUCTION OF FINAL TANKS AT OWLS HEAD WPCP | 3 | FINAL DESIGN | 2019-07-07 | 2020-12-27 | 2017-10-08 | 2019-03-31
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-88-L | RECONSTRUCTION OF FINAL TANKS AT OWLS HEAD WPCP | 4 | BID AWARD AND REGISTER CONTRCT | 2020-12-28 | 2021-09-23 | 2019-04-01 | 2019-12-26
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-88-L | RECONSTRUCTION OF FINAL TANKS AT OWLS HEAD WPCP | 5 | CONSTRUCTION TO 25% | 2021-09-24 | 2022-09-18 | 2019-12-27 | 2020-12-20
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-88-L | RECONSTRUCTION OF FINAL TANKS AT OWLS HEAD WPCP | 6 | CONSTRUCTION TO 50% | 2022-09-19 | 2023-09-13 | 2020-12-21 | 2021-12-15
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-88-L | RECONSTRUCTION OF FINAL TANKS AT OWLS HEAD WPCP | 7 | CONSTRUCTION TO 75% | 2023-09-14 | 2024-09-07 | 2021-12-16 | 2022-12-10
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-88-L | RECONSTRUCTION OF FINAL TANKS AT OWLS HEAD WPCP | 8 | DEVELOP SCOPE | 2026-03-02 | 2026-05-30 | 2022-12-11 | 2023-09-06
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-88-L | RECONSTRUCTION OF FINAL TANKS AT OWLS HEAD WPCP | 9 | PRELIMINARY DESIGN | 2026-05-31 | 2026-09-27 | 2023-09-07 | 2028-03-03
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-88-L | RECONSTRUCTION OF FINAL TANKS AT OWLS HEAD WPCP | 10 | FINAL DESIGN | 2026-09-28 | 2027-03-26 | 2028-03-04 | 2028-06-01
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-88-L | RECONSTRUCTION OF FINAL TANKS AT OWLS HEAD WPCP | 11 | BID AWARD AND REGISTER CONTRCT | 2027-03-27 | 2027-06-24 | 2028-03-04 | 2028-06-01
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-88-L | RECONSTRUCTION OF FINAL TANKS AT OWLS HEAD WPCP | 12 | CONSTRUCTION TO 25% | 2027-06-25 | 2027-10-22 | 2028-03-04 | 2028-06-01
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-88-L | RECONSTRUCTION OF FINAL TANKS AT OWLS HEAD WPCP | 13 | CONSTRUCTION TO 50% | 2027-10-23 | 2028-02-19 | 2028-03-04 | 2028-06-01
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-88-L | RECONSTRUCTION OF FINAL TANKS AT OWLS HEAD WPCP | 14 | CONSTRUCTION TO 75% | 2028-02-20 | 2028-06-18 | 2028-03-04 | 2028-06-01
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-88-L | RECONSTRUCTION OF FINAL TANKS AT OWLS HEAD WPCP | 15 | ORIGINAL EQUIP & FURNISHING | 2028-06-19 | 2028-09-16 | 2028-03-04 | 2028-06-01
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-88-L | RECONSTRUCTION OF FINAL TANKS AT OWLS HEAD WPCP | 16 | SUBSTANTIAL COMPLETION | 2028-09-17 | 2028-11-15 | 2028-03-04 | 2028-06-01
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-88-L | RECONSTRUCTION OF FINAL TANKS AT OWLS HEAD WPCP | 17 | PUNCHLIST COMPLETE, JOB CLOSED | 2028-11-16 | 2028-12-15 | 2028-03-04 | 2028-06-01
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-91-L | RECONSTRUCTION OF SEA WALL AND DOCK @ OWLS HEAD WWTP | 1 | DEVELOP SCOPE | 2023-06-01 | 2023-08-29 | 2014-02-01 | 2014-10-28
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-91-L | RECONSTRUCTION OF SEA WALL AND DOCK @ OWLS HEAD WWTP | 2 | PRELIMINARY DESIGN | 2023-08-30 | 2023-12-27 | 2014-10-29 | 2015-10-23
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-91-L | RECONSTRUCTION OF SEA WALL AND DOCK @ OWLS HEAD WWTP | 3 | FINAL DESIGN | 2023-12-28 | 2024-06-24 | 2015-10-24 | 2017-04-15
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-91-L | RECONSTRUCTION OF SEA WALL AND DOCK @ OWLS HEAD WWTP | 4 | BID AWARD AND REGISTER CONTRCT | 2024-06-25 | 2024-09-22 | 2017-04-16 | 2018-01-10
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-91-L | RECONSTRUCTION OF SEA WALL AND DOCK @ OWLS HEAD WWTP | 5 | CONSTRUCTION TO 25% | 2024-09-23 | 2025-01-20 | 2018-01-11 | 2019-01-05
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-91-L | RECONSTRUCTION OF SEA WALL AND DOCK @ OWLS HEAD WWTP | 6 | CONSTRUCTION TO 50% | 2025-01-21 | 2025-05-20 | 2019-01-06 | 2019-12-31
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-91-L | RECONSTRUCTION OF SEA WALL AND DOCK @ OWLS HEAD WWTP | 7 | CONSTRUCTION TO 75% | 2025-05-21 | 2025-09-17 | 2020-01-01 | 2020-12-25
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-91-L | RECONSTRUCTION OF SEA WALL AND DOCK @ OWLS HEAD WWTP | 8 | ORIGINAL EQUIP & FURNISHING | 2025-09-18 | 2025-12-16 | 2020-12-26 | 2021-09-21
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-91-L | RECONSTRUCTION OF SEA WALL AND DOCK @ OWLS HEAD WWTP | 9 | SUBSTANTIAL COMPLETION | 2025-12-17 | 2026-02-14 | 2021-09-22 | 2022-03-20
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-91-L | RECONSTRUCTION OF SEA WALL AND DOCK @ OWLS HEAD WWTP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2026-02-15 | 2026-03-16 | 2022-03-21 | 2022-06-18
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-281 | PROSPECT EXPRESSWAY | 1 | DEVELOP SCOPE | 2016-07-01 | 2017-03-27 | 2016-07-01 | 2017-03-27
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-281 | PROSPECT EXPRESSWAY | 2 | PRELIMINARY DESIGN | 2017-03-28 | 2018-03-22 | 2017-03-28 | 2018-03-22
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-281 | PROSPECT EXPRESSWAY | 3 | FINAL DESIGN | 2018-03-23 | 2019-09-13 | 2018-03-23 | 2019-09-13
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-281 | PROSPECT EXPRESSWAY | 4 | BID AWARD AND REGISTER CONTRCT | 2019-09-14 | 2020-06-09 | 2019-09-14 | 2020-06-09
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-281 | PROSPECT EXPRESSWAY | 5 | CONSTRUCTION TO 25% | 2020-06-10 | 2021-06-04 | 2020-06-10 | 2021-06-04
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-281 | PROSPECT EXPRESSWAY | 6 | CONSTRUCTION TO 50% | 2021-06-05 | 2022-05-30 | 2021-06-05 | 2022-05-30
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-281 | PROSPECT EXPRESSWAY | 7 | CONSTRUCTION TO 75% | 2022-05-31 | 2023-05-25 | 2022-05-31 | 2023-05-25
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-281 | PROSPECT EXPRESSWAY | 8 | ORIGINAL EQUIP & FURNISHING | 2023-05-26 | 2024-02-19 | 2023-05-26 | 2024-02-19
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-281 | PROSPECT EXPRESSWAY | 9 | SUBSTANTIAL COMPLETION | 2024-02-20 | 2024-08-17 | 2024-02-20 | 2024-08-17
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-281 | PROSPECT EXPRESSWAY | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-08-18 | 2024-11-15 | 2024-08-18 | 2024-11-15
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-316 | RECONSTRUCTION OF AVENUE U PUMPING STATION BROOKLYN | 1 | DEVELOP SCOPE | 2017-07-01 | 2018-03-27 | 2017-07-01 | 2018-03-27
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-316 | RECONSTRUCTION OF AVENUE U PUMPING STATION BROOKLYN | 2 | PRELIMINARY DESIGN | 2018-03-28 | 2019-03-22 | 2018-03-28 | 2019-03-22
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-316 | RECONSTRUCTION OF AVENUE U PUMPING STATION BROOKLYN | 3 | FINAL DESIGN | 2019-03-23 | 2020-09-12 | 2019-03-23 | 2020-09-12
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-316 | RECONSTRUCTION OF AVENUE U PUMPING STATION BROOKLYN | 4 | BID AWARD AND REGISTER CONTRCT | 2020-09-13 | 2021-06-09 | 2020-09-13 | 2021-06-09
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-316 | RECONSTRUCTION OF AVENUE U PUMPING STATION BROOKLYN | 5 | CONSTRUCTION TO 25% | 2021-06-10 | 2022-06-04 | 2021-06-10 | 2022-06-04
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-316 | RECONSTRUCTION OF AVENUE U PUMPING STATION BROOKLYN | 6 | CONSTRUCTION TO 50% | 2022-06-05 | 2023-05-30 | 2022-06-05 | 2023-05-30
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-316 | RECONSTRUCTION OF AVENUE U PUMPING STATION BROOKLYN | 7 | CONSTRUCTION TO 75% | 2023-05-31 | 2024-05-24 | 2023-05-31 | 2024-05-24
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-316 | RECONSTRUCTION OF AVENUE U PUMPING STATION BROOKLYN | 8 | ORIGINAL EQUIP & FURNISHING | 2024-05-25 | 2025-02-18 | 2024-05-25 | 2025-02-18
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-316 | RECONSTRUCTION OF AVENUE U PUMPING STATION BROOKLYN | 9 | SUBSTANTIAL COMPLETION | 2025-02-19 | 2025-08-17 | 2025-02-19 | 2025-08-17
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-316 | RECONSTRUCTION OF AVENUE U PUMPING STATION BROOKLYN | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-08-18 | 2025-11-15 | 2025-08-18 | 2025-11-15
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-318 | RECONSTRUCTION OF PAERDEGAT PUMPING STATION, BROOKLYN, N.Y. | 1 | DEVELOP SCOPE | 2017-07-01 | 2018-03-27 | 2017-07-01 | 2018-03-27
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-318 | RECONSTRUCTION OF PAERDEGAT PUMPING STATION, BROOKLYN, N.Y. | 2 | PRELIMINARY DESIGN | 2018-03-28 | 2019-03-22 | 2018-03-28 | 2019-03-22
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-318 | RECONSTRUCTION OF PAERDEGAT PUMPING STATION, BROOKLYN, N.Y. | 3 | FINAL DESIGN | 2019-03-23 | 2020-09-12 | 2019-03-23 | 2020-09-12
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-318 | RECONSTRUCTION OF PAERDEGAT PUMPING STATION, BROOKLYN, N.Y. | 4 | BID AWARD AND REGISTER CONTRCT | 2020-09-13 | 2021-06-09 | 2020-09-13 | 2021-06-09
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-318 | RECONSTRUCTION OF PAERDEGAT PUMPING STATION, BROOKLYN, N.Y. | 5 | CONSTRUCTION TO 25% | 2021-06-10 | 2022-06-04 | 2021-06-10 | 2022-06-04
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-318 | RECONSTRUCTION OF PAERDEGAT PUMPING STATION, BROOKLYN, N.Y. | 6 | CONSTRUCTION TO 50% | 2022-06-05 | 2023-05-30 | 2022-06-05 | 2023-05-30
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-318 | RECONSTRUCTION OF PAERDEGAT PUMPING STATION, BROOKLYN, N.Y. | 7 | CONSTRUCTION TO 75% | 2023-05-31 | 2024-05-24 | 2023-05-31 | 2024-05-24
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-318 | RECONSTRUCTION OF PAERDEGAT PUMPING STATION, BROOKLYN, N.Y. | 8 | ORIGINAL EQUIP & FURNISHING | 2024-05-25 | 2025-02-18 | 2024-05-25 | 2025-02-18
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-318 | RECONSTRUCTION OF PAERDEGAT PUMPING STATION, BROOKLYN, N.Y. | 9 | SUBSTANTIAL COMPLETION | 2025-02-19 | 2025-08-17 | 2025-02-19 | 2025-08-17
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-318 | RECONSTRUCTION OF PAERDEGAT PUMPING STATION, BROOKLYN, N.Y. | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-08-18 | 2025-11-15 | 2025-08-18 | 2025-11-15
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-79 | RECONSTRUCT AVE "V" PUMPING STATION | 1 | DEVELOP SCOPE | 1997-07-15 | 1998-04-10 | 2012-07-01 | 2013-03-27
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-79 | RECONSTRUCT AVE "V" PUMPING STATION | 2 | PRELIMINARY DESIGN | 1998-04-11 | 1999-04-05 | 2013-03-28 | 2014-03-22
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-79 | RECONSTRUCT AVE "V" PUMPING STATION | 3 | FINAL DESIGN | 1999-04-06 | 2000-09-26 | 2014-03-23 | 2015-09-13
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-79 | RECONSTRUCT AVE "V" PUMPING STATION | 4 | BID AWARD AND REGISTER CONTRCT | 2000-09-27 | 2001-06-23 | 2015-09-14 | 2016-06-09
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-79 | RECONSTRUCT AVE "V" PUMPING STATION | 5 | CONSTRUCTION TO 25% | 2001-06-24 | 2002-06-18 | 2016-06-10 | 2017-06-04
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-79 | RECONSTRUCT AVE "V" PUMPING STATION | 6 | CONSTRUCTION TO 50% | 2002-06-19 | 2003-06-13 | 2017-06-05 | 2018-05-30
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-79 | RECONSTRUCT AVE "V" PUMPING STATION | 7 | CONSTRUCTION TO 75% | 2003-06-14 | 2004-06-07 | 2018-05-31 | 2019-05-25
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-79 | RECONSTRUCT AVE "V" PUMPING STATION | 8 | ORIGINAL EQUIP & FURNISHING | 2004-06-08 | 2005-03-04 | 2019-05-26 | 2020-02-19
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-79 | RECONSTRUCT AVE "V" PUMPING STATION | 9 | SUBSTANTIAL COMPLETION | 2005-03-05 | 2005-08-31 | 2020-02-20 | 2020-08-17
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-79 | RECONSTRUCT AVE "V" PUMPING STATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2005-09-01 | 2005-11-29 | 2020-08-18 | 2020-11-15
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | RH-80-L | TRC - DISINFECTION SYSTEM REHABILITATION AT RED HOOK WPCP | 1 | FINAL DESIGN | 2025-06-01 | 2026-11-22 | 2022-06-01 | 2023-11-22
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | RH-80-L | TRC - DISINFECTION SYSTEM REHABILITATION AT RED HOOK WPCP | 2 | CONSTRUCTION TO 25% | 2026-11-23 | 2027-07-20 | 2023-11-23 | 2024-07-19
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | RH-80-L | TRC - DISINFECTION SYSTEM REHABILITATION AT RED HOOK WPCP | 3 | CONSTRUCTION TO 50% | 2027-07-21 | 2028-03-16 | 2024-07-20 | 2025-03-16
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | RH-80-L | TRC - DISINFECTION SYSTEM REHABILITATION AT RED HOOK WPCP | 4 | CONSTRUCTION TO 75% | 2028-03-17 | 2028-11-11 | 2025-03-17 | 2025-11-11
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | RH-83 | REPLACE MAIN SEWAGE PUMPS AT RED HOOK WPCP | 1 | FINAL DESIGN | 2022-06-01 | 2023-11-22 | 2020-06-01 | 2021-02-25
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | RH-83 | REPLACE MAIN SEWAGE PUMPS AT RED HOOK WPCP | 2 | CONSTRUCTION TO 25% | 2023-11-23 | 2024-07-19 | 2021-02-26 | 2022-02-20
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | RH-83 | REPLACE MAIN SEWAGE PUMPS AT RED HOOK WPCP | 3 | CONSTRUCTION TO 50% | 2024-07-20 | 2025-03-16 | 2022-02-21 | 2023-08-14
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | RH-83 | REPLACE MAIN SEWAGE PUMPS AT RED HOOK WPCP | 4 | CONSTRUCTION TO 75% | 2025-03-17 | 2025-11-11 | 2023-08-15 | 2024-05-10
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | RH-83 | REPLACE MAIN SEWAGE PUMPS AT RED HOOK WPCP | 5 | CONSTRUCTION TO 25% | 2025-03-17 | 2025-11-11 | 2024-05-11 | 2025-05-05
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | RH-83 | REPLACE MAIN SEWAGE PUMPS AT RED HOOK WPCP | 6 | CONSTRUCTION TO 50% | 2025-03-17 | 2025-11-11 | 2025-05-06 | 2026-04-30
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | RH-83 | REPLACE MAIN SEWAGE PUMPS AT RED HOOK WPCP | 7 | CONSTRUCTION TO 75% | 2025-03-17 | 2025-11-11 | 2026-05-01 | 2027-04-25
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | RH-83 | REPLACE MAIN SEWAGE PUMPS AT RED HOOK WPCP | 8 | ORIGINAL EQUIP & FURNISHING | 2025-03-17 | 2025-11-11 | 2027-04-26 | 2028-01-20
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | RH-83 | REPLACE MAIN SEWAGE PUMPS AT RED HOOK WPCP | 9 | SUBSTANTIAL COMPLETION | 2025-03-17 | 2025-11-11 | 2028-01-21 | 2028-07-18
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | RH-83 | REPLACE MAIN SEWAGE PUMPS AT RED HOOK WPCP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-03-17 | 2025-11-11 | 2028-07-19 | 2028-10-16
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | RH-91-L | INSTALL ACCESS CONTROL & DIGITAL VIDEO SURVEILLANCE SYS @ RH | 1 | DEVELOP SCOPE | 2019-06-01 | 2019-08-29 | 2019-06-01 | 2019-08-29
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | RH-91-L | INSTALL ACCESS CONTROL & DIGITAL VIDEO SURVEILLANCE SYS @ RH | 2 | PRELIMINARY DESIGN | 2019-08-30 | 2019-12-27 | 2019-08-30 | 2019-12-27
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | RH-91-L | INSTALL ACCESS CONTROL & DIGITAL VIDEO SURVEILLANCE SYS @ RH | 3 | FINAL DESIGN | 2019-12-28 | 2020-06-24 | 2019-12-28 | 2020-06-24
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | RH-91-L | INSTALL ACCESS CONTROL & DIGITAL VIDEO SURVEILLANCE SYS @ RH | 4 | BID AWARD AND REGISTER CONTRCT | 2020-06-25 | 2020-09-22 | 2020-06-25 | 2020-09-22
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | RH-91-L | INSTALL ACCESS CONTROL & DIGITAL VIDEO SURVEILLANCE SYS @ RH | 5 | CONSTRUCTION TO 25% | 2020-09-23 | 2021-01-20 | 2020-09-23 | 2021-01-20
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | RH-91-L | INSTALL ACCESS CONTROL & DIGITAL VIDEO SURVEILLANCE SYS @ RH | 6 | CONSTRUCTION TO 50% | 2021-01-21 | 2021-05-20 | 2021-01-21 | 2021-05-20
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | RH-91-L | INSTALL ACCESS CONTROL & DIGITAL VIDEO SURVEILLANCE SYS @ RH | 7 | CONSTRUCTION TO 75% | 2021-05-21 | 2021-09-17 | 2021-05-21 | 2021-09-17
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | RH-91-L | INSTALL ACCESS CONTROL & DIGITAL VIDEO SURVEILLANCE SYS @ RH | 8 | ORIGINAL EQUIP & FURNISHING | 2021-09-18 | 2021-12-16 | 2021-09-18 | 2021-12-16
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | RH-91-L | INSTALL ACCESS CONTROL & DIGITAL VIDEO SURVEILLANCE SYS @ RH | 9 | SUBSTANTIAL COMPLETION | 2021-12-17 | 2022-02-14 | 2021-12-17 | 2022-02-14
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | RH-91-L | INSTALL ACCESS CONTROL & DIGITAL VIDEO SURVEILLANCE SYS @ RH | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-02-15 | 2022-03-16 | 2022-02-15 | 2022-03-16
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SAND26W | STORM MITIGATION WORK ATTHE 26TH WARD WPCP | 1 | DEVELOP SCOPE | 2020-06-01 | 2021-02-25 | 2020-06-01 | 2021-02-25
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SAND26W | STORM MITIGATION WORK ATTHE 26TH WARD WPCP | 2 | PRELIMINARY DESIGN | 2021-02-26 | 2022-02-20 | 2021-02-26 | 2022-02-20
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SAND26W | STORM MITIGATION WORK ATTHE 26TH WARD WPCP | 3 | FINAL DESIGN | 2022-02-21 | 2023-08-14 | 2022-02-21 | 2023-08-14
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SAND26W | STORM MITIGATION WORK ATTHE 26TH WARD WPCP | 4 | BID AWARD AND REGISTER CONTRCT | 2023-08-15 | 2024-05-10 | 2023-08-15 | 2024-05-10
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SAND26W | STORM MITIGATION WORK ATTHE 26TH WARD WPCP | 5 | CONSTRUCTION TO 25% | 2024-05-11 | 2025-05-05 | 2024-05-11 | 2025-05-05
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SAND26W | STORM MITIGATION WORK ATTHE 26TH WARD WPCP | 6 | CONSTRUCTION TO 50% | 2025-05-06 | 2026-04-30 | 2025-05-06 | 2026-04-30
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SAND26W | STORM MITIGATION WORK ATTHE 26TH WARD WPCP | 7 | CONSTRUCTION TO 75% | 2026-05-01 | 2027-04-25 | 2026-05-01 | 2027-04-25
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SAND26W | STORM MITIGATION WORK ATTHE 26TH WARD WPCP | 8 | ORIGINAL EQUIP & FURNISHING | 2027-04-26 | 2028-01-20 | 2027-04-26 | 2028-01-20
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SAND26W | STORM MITIGATION WORK ATTHE 26TH WARD WPCP | 9 | SUBSTANTIAL COMPLETION | 2028-01-21 | 2028-07-18 | 2028-01-21 | 2028-07-18
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SAND26W | STORM MITIGATION WORK ATTHE 26TH WARD WPCP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2028-07-19 | 2028-10-16 | 2028-07-19 | 2028-10-16
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDCI | STORM MITIGATION WORK ATTHE CONEY ISLAND WPCP | 1 | DEVELOP SCOPE | 2020-06-01 | 2021-02-25 | 2020-06-01 | 2021-02-25
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDCI | STORM MITIGATION WORK ATTHE CONEY ISLAND WPCP | 2 | PRELIMINARY DESIGN | 2021-02-26 | 2022-02-20 | 2021-02-26 | 2022-02-20
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDCI | STORM MITIGATION WORK ATTHE CONEY ISLAND WPCP | 3 | FINAL DESIGN | 2022-02-21 | 2023-08-14 | 2022-02-21 | 2023-08-14
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDCI | STORM MITIGATION WORK ATTHE CONEY ISLAND WPCP | 4 | BID AWARD AND REGISTER CONTRCT | 2023-08-15 | 2024-05-10 | 2023-08-15 | 2024-05-10
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDCI | STORM MITIGATION WORK ATTHE CONEY ISLAND WPCP | 5 | CONSTRUCTION TO 25% | 2024-05-11 | 2025-05-05 | 2024-05-11 | 2025-05-05
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDCI | STORM MITIGATION WORK ATTHE CONEY ISLAND WPCP | 6 | CONSTRUCTION TO 50% | 2025-05-06 | 2026-04-30 | 2025-05-06 | 2026-04-30
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDCI | STORM MITIGATION WORK ATTHE CONEY ISLAND WPCP | 7 | CONSTRUCTION TO 75% | 2026-05-01 | 2027-04-25 | 2026-05-01 | 2027-04-25
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDCI | STORM MITIGATION WORK ATTHE CONEY ISLAND WPCP | 8 | ORIGINAL EQUIP & FURNISHING | 2027-04-26 | 2028-01-20 | 2027-04-26 | 2028-01-20
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDCI | STORM MITIGATION WORK ATTHE CONEY ISLAND WPCP | 9 | SUBSTANTIAL COMPLETION | 2028-01-21 | 2028-07-18 | 2028-01-21 | 2028-07-18
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDCI | STORM MITIGATION WORK ATTHE CONEY ISLAND WPCP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2028-07-19 | 2028-10-16 | 2028-07-19 | 2028-10-16
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDOH | STORM MITIGATION WORK ATTHE OWLS HEAD WPCP (HMP) | 1 | DEVELOP SCOPE | 2020-10-01 | 2021-06-27 | 2020-10-01 | 2021-06-27
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDOH | STORM MITIGATION WORK ATTHE OWLS HEAD WPCP (HMP) | 2 | PRELIMINARY DESIGN | 2021-06-28 | 2022-06-22 | 2021-06-28 | 2022-06-22
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDOH | STORM MITIGATION WORK ATTHE OWLS HEAD WPCP (HMP) | 3 | FINAL DESIGN | 2022-06-23 | 2023-12-14 | 2022-06-23 | 2023-12-14
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDOH | STORM MITIGATION WORK ATTHE OWLS HEAD WPCP (HMP) | 4 | BID AWARD AND REGISTER CONTRCT | 2023-12-15 | 2024-09-09 | 2023-12-15 | 2024-09-09
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDOH | STORM MITIGATION WORK ATTHE OWLS HEAD WPCP (HMP) | 5 | CONSTRUCTION TO 25% | 2024-09-10 | 2025-09-04 | 2024-09-10 | 2025-09-04
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDOH | STORM MITIGATION WORK ATTHE OWLS HEAD WPCP (HMP) | 6 | CONSTRUCTION TO 50% | 2025-09-05 | 2026-08-30 | 2025-09-05 | 2026-08-30
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDOH | STORM MITIGATION WORK ATTHE OWLS HEAD WPCP (HMP) | 7 | CONSTRUCTION TO 75% | 2026-08-31 | 2027-08-25 | 2026-08-31 | 2027-08-25
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDOH | STORM MITIGATION WORK ATTHE OWLS HEAD WPCP (HMP) | 8 | ORIGINAL EQUIP & FURNISHING | 2027-08-26 | 2028-05-21 | 2027-08-26 | 2028-05-21
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDOH | STORM MITIGATION WORK ATTHE OWLS HEAD WPCP (HMP) | 9 | SUBSTANTIAL COMPLETION | 2028-05-22 | 2028-11-17 | 2028-05-22 | 2028-11-17
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDOH | STORM MITIGATION WORK ATTHE OWLS HEAD WPCP (HMP) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2028-11-18 | 2029-02-15 | 2028-11-18 | 2029-02-15
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK002385 | Rehab of Combined brick sewer via guniting 92st & 4 Ave, BK | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-08-29 | 2020-06-01 | 2020-08-29
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK002385 | Rehab of Combined brick sewer via guniting 92st & 4 Ave, BK | 2 | PRELIMINARY DESIGN | 2020-08-30 | 2020-12-27 | 2020-08-30 | 2020-12-27
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK002385 | Rehab of Combined brick sewer via guniting 92st & 4 Ave, BK | 3 | FINAL DESIGN | 2020-12-28 | 2021-06-25 | 2020-12-28 | 2021-06-25
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK002385 | Rehab of Combined brick sewer via guniting 92st & 4 Ave, BK | 4 | BID AWARD AND REGISTER CONTRCT | 2021-06-26 | 2021-09-23 | 2021-06-26 | 2021-09-23
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK002385 | Rehab of Combined brick sewer via guniting 92st & 4 Ave, BK | 5 | CONSTRUCTION TO 25% | 2021-09-24 | 2022-01-21 | 2021-09-24 | 2022-01-21
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK002385 | Rehab of Combined brick sewer via guniting 92st & 4 Ave, BK | 6 | CONSTRUCTION TO 50% | 2022-01-22 | 2022-05-21 | 2022-01-22 | 2022-05-21
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK002385 | Rehab of Combined brick sewer via guniting 92st & 4 Ave, BK | 7 | CONSTRUCTION TO 75% | 2022-05-22 | 2022-09-18 | 2022-05-22 | 2022-09-18
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK002385 | Rehab of Combined brick sewer via guniting 92st & 4 Ave, BK | 8 | ORIGINAL EQUIP & FURNISHING | 2022-09-19 | 2022-12-17 | 2022-09-19 | 2022-12-17
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK002385 | Rehab of Combined brick sewer via guniting 92st & 4 Ave, BK | 9 | SUBSTANTIAL COMPLETION | 2022-12-18 | 2023-02-15 | 2022-12-18 | 2023-02-15
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK002385 | Rehab of Combined brick sewer via guniting 92st & 4 Ave, BK | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-02-16 | 2023-03-17 | 2023-02-16 | 2023-03-17
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK002390 | Guniting of Outfall Sewers on Wolcott St BKLYN | 1 | DEVELOP SCOPE | 2022-12-09 | 2023-03-08 | 2022-12-09 | 2023-03-08
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK002390 | Guniting of Outfall Sewers on Wolcott St BKLYN | 2 | PRELIMINARY DESIGN | 2023-03-09 | 2023-07-06 | 2023-03-09 | 2023-07-06
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK002390 | Guniting of Outfall Sewers on Wolcott St BKLYN | 3 | FINAL DESIGN | 2023-07-07 | 2024-01-02 | 2023-07-07 | 2024-01-02
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK002390 | Guniting of Outfall Sewers on Wolcott St BKLYN | 4 | BID AWARD AND REGISTER CONTRCT | 2024-01-03 | 2024-04-01 | 2024-01-03 | 2024-04-01
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK002390 | Guniting of Outfall Sewers on Wolcott St BKLYN | 5 | CONSTRUCTION TO 25% | 2024-04-02 | 2024-07-30 | 2024-04-02 | 2024-07-30
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK002390 | Guniting of Outfall Sewers on Wolcott St BKLYN | 6 | CONSTRUCTION TO 50% | 2024-07-31 | 2024-11-27 | 2024-07-31 | 2024-11-27
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK002390 | Guniting of Outfall Sewers on Wolcott St BKLYN | 7 | CONSTRUCTION TO 75% | 2024-11-28 | 2025-03-27 | 2024-11-28 | 2025-03-27
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK002390 | Guniting of Outfall Sewers on Wolcott St BKLYN | 8 | ORIGINAL EQUIP & FURNISHING | 2025-03-28 | 2025-06-25 | 2025-03-28 | 2025-06-25
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK002390 | Guniting of Outfall Sewers on Wolcott St BKLYN | 9 | SUBSTANTIAL COMPLETION | 2025-06-26 | 2025-08-24 | 2025-06-26 | 2025-08-24
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK002390 | Guniting of Outfall Sewers on Wolcott St BKLYN | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-08-25 | 2025-09-23 | 2025-08-25 | 2025-09-23
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK20075 | NEW STORM SEWER IN INDIA ST. | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-08-29 | 2022-06-02 | 2022-08-30
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK20075 | NEW STORM SEWER IN INDIA ST. | 2 | PRELIMINARY DESIGN | 2020-08-30 | 2020-12-27 | 2022-08-31 | 2022-12-28
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK20075 | NEW STORM SEWER IN INDIA ST. | 3 | FINAL DESIGN | 2020-12-28 | 2021-06-25 | 2022-12-29 | 2023-06-26
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK20075 | NEW STORM SEWER IN INDIA ST. | 4 | BID AWARD AND REGISTER CONTRCT | 2021-06-26 | 2021-09-23 | 2023-06-27 | 2023-09-24
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK20075 | NEW STORM SEWER IN INDIA ST. | 5 | CONSTRUCTION TO 25% | 2021-09-24 | 2022-01-21 | 2023-09-25 | 2024-01-22
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK20075 | NEW STORM SEWER IN INDIA ST. | 6 | CONSTRUCTION TO 50% | 2022-01-22 | 2022-05-21 | 2024-01-23 | 2024-05-21
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK20075 | NEW STORM SEWER IN INDIA ST. | 7 | CONSTRUCTION TO 75% | 2022-05-22 | 2022-09-18 | 2024-05-22 | 2024-09-18
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK20075 | NEW STORM SEWER IN INDIA ST. | 8 | ORIGINAL EQUIP & FURNISHING | 2022-09-19 | 2022-12-17 | 2024-09-19 | 2024-12-17
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK20075 | NEW STORM SEWER IN INDIA ST. | 9 | SUBSTANTIAL COMPLETION | 2022-12-18 | 2023-02-15 | 2024-12-18 | 2025-02-15
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK20075 | NEW STORM SEWER IN INDIA ST. | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-02-16 | 2023-03-17 | 2025-02-16 | 2025-03-17
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SF-BNR-CI | STEP FEED BNR AT CONEY ISLAND & ROCKAWAY WPCPs | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-12-31 | 2013-07-01 | 2013-12-31
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SF-BNR-CI | STEP FEED BNR AT CONEY ISLAND & ROCKAWAY WPCPs | 2 | PRELIMINARY DESIGN | 2014-01-01 | 2016-11-30 | 2014-01-01 | 2016-11-30
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SF-BNR-CI | STEP FEED BNR AT CONEY ISLAND & ROCKAWAY WPCPs | 3 | FINAL DESIGN | 2016-12-01 | 2017-11-30 | 2016-12-01 | 2017-11-30
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SF-BNR-CI | STEP FEED BNR AT CONEY ISLAND & ROCKAWAY WPCPs | 4 | BID AWARD AND REGISTER CONTRCT | 2017-12-01 | 2018-10-01 | 2017-12-01 | 2018-10-01
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SF-BNR-CI | STEP FEED BNR AT CONEY ISLAND & ROCKAWAY WPCPs | 5 | CONSTRUCTION TO 25% | 2018-10-02 | 2019-06-03 | 2018-10-02 | 2019-06-03
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SF-BNR-CI | STEP FEED BNR AT CONEY ISLAND & ROCKAWAY WPCPs | 6 | CONSTRUCTION TO 50% | 2019-06-04 | 2020-03-04 | 2019-06-04 | 2020-03-04
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SF-BNR-CI | STEP FEED BNR AT CONEY ISLAND & ROCKAWAY WPCPs | 7 | CONSTRUCTION TO 75% | 2020-03-05 | 2020-12-04 | 2020-03-05 | 2020-12-04
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SF-BNR-CI | STEP FEED BNR AT CONEY ISLAND & ROCKAWAY WPCPs | 8 | ORIGINAL EQUIP & FURNISHING | 2020-12-05 | 2021-06-02 | 2020-12-05 | 2021-06-02
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SF-BNR-CI | STEP FEED BNR AT CONEY ISLAND & ROCKAWAY WPCPs | 9 | SUBSTANTIAL COMPLETION | 2021-06-03 | 2021-11-30 | 2021-06-03 | 2021-11-30
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SF-BNR-CI | STEP FEED BNR AT CONEY ISLAND & ROCKAWAY WPCPs | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-12-01 | 2022-12-25 | 2021-12-01 | 2022-12-25
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | WFF-DPR | WATER EFICIENCY UPGRADES AT PROSPECT PARK, BROOKLYN | 1 | DEVELOP SCOPE | 2020-06-15 | 2020-10-12 | 2020-06-15 | 2020-10-12
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | WFF-DPR | WATER EFICIENCY UPGRADES AT PROSPECT PARK, BROOKLYN | 2 | PRELIMINARY DESIGN | 2020-10-13 | 2021-04-10 | 2020-10-13 | 2021-04-10
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | WFF-DPR | WATER EFICIENCY UPGRADES AT PROSPECT PARK, BROOKLYN | 3 | FINAL DESIGN | 2021-04-11 | 2022-10-12 | 2021-04-11 | 2022-10-12
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | WFF-DPR | WATER EFICIENCY UPGRADES AT PROSPECT PARK, BROOKLYN | 4 | BID AWARD AND REGISTER CONTRCT | 2022-10-13 | 2023-04-10 | 2022-10-13 | 2023-04-10
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | WFF-DPR | WATER EFICIENCY UPGRADES AT PROSPECT PARK, BROOKLYN | 5 | CONSTRUCTION TO 25% | 2023-04-11 | 2024-01-15 | 2023-04-11 | 2024-01-15
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | WFF-DPR | WATER EFICIENCY UPGRADES AT PROSPECT PARK, BROOKLYN | 6 | CONSTRUCTION TO 50% | 2024-01-16 | 2024-10-21 | 2024-01-16 | 2024-10-21
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | WFF-DPR | WATER EFICIENCY UPGRADES AT PROSPECT PARK, BROOKLYN | 7 | CONSTRUCTION TO 75% | 2024-10-22 | 2025-07-28 | 2024-10-22 | 2025-07-28
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | WFF-DPR | WATER EFICIENCY UPGRADES AT PROSPECT PARK, BROOKLYN | 8 | ORIGINAL EQUIP & FURNISHING | 2025-07-29 | 2025-10-26 | 2025-07-29 | 2025-10-26
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | WFF-DPR | WATER EFICIENCY UPGRADES AT PROSPECT PARK, BROOKLYN | 9 | SUBSTANTIAL COMPLETION | 2025-10-27 | 2025-12-25 | 2025-10-27 | 2025-12-25
20201123 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | WFF-DPR | WATER EFICIENCY UPGRADES AT PROSPECT PARK, BROOKLYN | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-12-26 | 2026-03-25 | 2025-12-26 | 2026-03-25
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-264Y | Brooklyn Cioffe Borough Shop Roof Replacement | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-09-28 | 2016-07-01 | 2016-09-28
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-264Y | Brooklyn Cioffe Borough Shop Roof Replacement | 2 | PRELIMINARY DESIGN | 2016-09-29 | 2017-09-28 | 2016-09-29 | 2017-09-28
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-264Y | Brooklyn Cioffe Borough Shop Roof Replacement | 3 | FINAL DESIGN | 2017-09-29 | 2018-09-28 | 2017-09-29 | 2018-09-28
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-264Y | Brooklyn Cioffe Borough Shop Roof Replacement | 4 | BID AWARD AND REGISTER CONTRCT | 2018-09-29 | 2019-09-28 | 2018-09-29 | 2019-09-28
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-264Y | Brooklyn Cioffe Borough Shop Roof Replacement | 5 | CONSTRUCTION TO 25% | 2019-09-29 | 2020-09-27 | 2019-09-29 | 2020-09-27
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-264Y | Brooklyn Cioffe Borough Shop Roof Replacement | 6 | CONSTRUCTION TO 50% | 2020-09-28 | 2021-09-27 | 2020-09-28 | 2021-09-27
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-264Y | Brooklyn Cioffe Borough Shop Roof Replacement | 7 | CONSTRUCTION TO 75% | 2021-09-28 | 2022-09-27 | 2021-09-28 | 2022-09-27
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-264Y | Brooklyn Cioffe Borough Shop Roof Replacement | 8 | SUBSTANTIAL COMPLETION | 2022-09-28 | 2025-06-23 | 2022-09-28 | 2025-06-23
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-264Y | Brooklyn Cioffe Borough Shop Roof Replacement | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-06-09 | 2025-10-21 | 2024-06-09 | 2025-10-21
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-332K | Brooklyn Knapp St Facility Improvements | 1 | DEVELOP SCOPE | 2007-04-01 | 2007-06-29 | 2007-04-01 | 2007-06-29
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-332K | Brooklyn Knapp St Facility Improvements | 2 | PRELIMINARY DESIGN | 2007-06-30 | 2007-12-15 | 2007-06-30 | 2007-12-15
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-332K | Brooklyn Knapp St Facility Improvements | 3 | FINAL DESIGN | 2007-12-16 | 2008-05-08 | 2007-12-16 | 2009-12-09
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-332K | Brooklyn Knapp St Facility Improvements | 4 | BID AWARD AND REGISTER CONTRCT | 2008-05-09 | 2008-11-04 | 2009-12-10 | 2010-07-27
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-332K | Brooklyn Knapp St Facility Improvements | 5 | CONSTRUCTION TO 25% | 2008-11-05 | 2009-11-04 | 2010-07-28 | 2011-07-27
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-332K | Brooklyn Knapp St Facility Improvements | 6 | CONSTRUCTION TO 50% | 2009-11-05 | 2010-11-04 | 2011-07-28 | 2012-07-26
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-332K | Brooklyn Knapp St Facility Improvements | 7 | CONSTRUCTION TO 75% | 2010-11-05 | 2011-11-04 | 2012-07-27 | 2014-10-04
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-332K | Brooklyn Knapp St Facility Improvements | 8 | SUBSTANTIAL COMPLETION | 2011-11-05 | 2012-11-03 | 2014-10-05 | 2020-10-12
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-332K | Brooklyn Knapp St Facility Improvements | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-11-04 | 2014-12-11 | 2020-10-13 | 2021-10-12
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-374W | Brooklyn 11 Boiler Replacement | 1 | DEVELOP SCOPE | 2019-05-01 | 2020-01-05 | 2019-05-01 | 2020-01-05
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-374W | Brooklyn 11 Boiler Replacement | 2 | PRELIMINARY DESIGN | 2020-01-06 | 2020-06-28 | 2020-01-06 | 2020-06-28
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-374W | Brooklyn 11 Boiler Replacement | 3 | FINAL DESIGN | 2020-06-29 | 2020-12-20 | 2020-06-29 | 2020-12-20
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-374W | Brooklyn 11 Boiler Replacement | 4 | BID AWARD AND REGISTER CONTRCT | 2020-12-21 | 2021-06-30 | 2020-12-21 | 2021-06-30
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-374W | Brooklyn 11 Boiler Replacement | 5 | CONSTRUCTION TO 25% | 2021-07-01 | 2021-12-27 | 2021-07-01 | 2021-12-27
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-374W | Brooklyn 11 Boiler Replacement | 6 | CONSTRUCTION TO 50% | 2021-12-28 | 2022-06-25 | 2021-12-28 | 2022-06-25
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-374W | Brooklyn 11 Boiler Replacement | 7 | CONSTRUCTION TO 75% | 2022-06-26 | 2022-12-22 | 2022-06-26 | 2022-12-22
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-374W | Brooklyn 11 Boiler Replacement | 8 | SUBSTANTIAL COMPLETION | 2022-12-23 | 2023-12-22 | 2022-12-23 | 2023-12-22
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-374W | Brooklyn 11 Boiler Replacement | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-12-23 | 2024-04-20 | 2023-12-23 | 2024-04-20
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-380D | Brooklyn 14 Garage HVAC System Rehabilitation | 1 | DEVELOP SCOPE | 2018-09-01 | 2018-10-15 | 2018-09-01 | 2018-10-15
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-380D | Brooklyn 14 Garage HVAC System Rehabilitation | 2 | PRELIMINARY DESIGN | 2018-10-16 | 2018-12-14 | 2018-10-16 | 2018-12-14
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-380D | Brooklyn 14 Garage HVAC System Rehabilitation | 3 | FINAL DESIGN | 2018-12-15 | 2019-02-12 | 2018-12-15 | 2019-02-12
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-380D | Brooklyn 14 Garage HVAC System Rehabilitation | 4 | BID AWARD AND REGISTER CONTRCT | 2019-02-13 | 2019-05-13 | 2019-02-13 | 2019-05-13
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-380D | Brooklyn 14 Garage HVAC System Rehabilitation | 5 | CONSTRUCTION TO 25% | 2019-05-14 | 2019-11-09 | 2019-05-14 | 2019-11-09
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-380D | Brooklyn 14 Garage HVAC System Rehabilitation | 6 | CONSTRUCTION TO 50% | 2019-11-10 | 2020-05-17 | 2019-11-10 | 2020-05-17
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-380D | Brooklyn 14 Garage HVAC System Rehabilitation | 7 | CONSTRUCTION TO 75% | 2020-05-18 | 2020-11-23 | 2020-05-18 | 2020-11-23
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-380D | Brooklyn 14 Garage HVAC System Rehabilitation | 8 | SUBSTANTIAL COMPLETION | 2020-11-24 | 2021-05-22 | 2020-11-24 | 2021-05-22
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-380D | Brooklyn 14 Garage HVAC System Rehabilitation | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-05-23 | 2021-12-08 | 2021-05-23 | 2021-12-08
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-383G | BROOKLYN CIOFFE SHOP HVAC REPLACEMENT | 1 | DEVELOP SCOPE | 2008-08-01 | 2008-11-08 | 2008-08-01 | 2008-11-08
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-383G | BROOKLYN CIOFFE SHOP HVAC REPLACEMENT | 2 | PRELIMINARY DESIGN | 2008-11-09 | 2009-05-27 | 2008-11-09 | 2009-05-27
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-383G | BROOKLYN CIOFFE SHOP HVAC REPLACEMENT | 3 | FINAL DESIGN | 2009-05-28 | 2009-12-13 | 2009-05-28 | 2009-12-13
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-383G | BROOKLYN CIOFFE SHOP HVAC REPLACEMENT | 4 | BID AWARD AND REGISTER CONTRCT | 2009-12-14 | 2010-10-09 | 2009-12-14 | 2016-10-09
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-383G | BROOKLYN CIOFFE SHOP HVAC REPLACEMENT | 5 | CONSTRUCTION TO 25% | 2010-10-10 | 2011-10-09 | 2016-10-10 | 2016-10-09
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-383G | BROOKLYN CIOFFE SHOP HVAC REPLACEMENT | 6 | CONSTRUCTION TO 50% | 2011-10-10 | 2012-10-08 | 2016-10-10 | 2016-10-09
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-383G | BROOKLYN CIOFFE SHOP HVAC REPLACEMENT | 7 | CONSTRUCTION TO 75% | 2012-10-09 | 2013-10-08 | 2016-10-10 | 2016-10-09
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-383G | BROOKLYN CIOFFE SHOP HVAC REPLACEMENT | 8 | SUBSTANTIAL COMPLETION | 2013-10-09 | 2014-10-08 | 2016-10-10 | 2020-11-17
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-383G | BROOKLYN CIOFFE SHOP HVAC REPLACEMENT | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-10-09 | 2016-09-07 | 2020-11-18 | 2021-11-17
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-427 | Brooklyn 16 922 Georgia Ave Garage Rehabilitation | 1 | DEVELOP SCOPE | 2019-02-01 | 2020-07-04 | 2019-02-01 | 2020-07-04
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-427 | Brooklyn 16 922 Georgia Ave Garage Rehabilitation | 2 | PRELIMINARY DESIGN | 2020-07-05 | 2021-03-11 | 2020-07-05 | 2021-03-11
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-427 | Brooklyn 16 922 Georgia Ave Garage Rehabilitation | 3 | FINAL DESIGN | 2021-03-12 | 2021-11-16 | 2021-03-12 | 2021-11-16
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-427 | Brooklyn 16 922 Georgia Ave Garage Rehabilitation | 4 | BID AWARD AND REGISTER CONTRCT | 2021-11-17 | 2022-07-24 | 2021-11-17 | 2022-07-24
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-427 | Brooklyn 16 922 Georgia Ave Garage Rehabilitation | 5 | CONSTRUCTION TO 25% | 2022-07-25 | 2023-07-24 | 2022-07-25 | 2023-07-24
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-427 | Brooklyn 16 922 Georgia Ave Garage Rehabilitation | 6 | CONSTRUCTION TO 50% | 2023-07-25 | 2024-07-23 | 2023-07-25 | 2024-07-23
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-427 | Brooklyn 16 922 Georgia Ave Garage Rehabilitation | 7 | CONSTRUCTION TO 75% | 2024-07-24 | 2025-07-23 | 2024-07-24 | 2025-07-23
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-427 | Brooklyn 16 922 Georgia Ave Garage Rehabilitation | 8 | SUBSTANTIAL COMPLETION | 2025-07-24 | 2026-07-23 | 2025-07-24 | 2026-07-23
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-427 | Brooklyn 16 922 Georgia Ave Garage Rehabilitation | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2026-07-24 | 2027-07-23 | 2026-07-24 | 2027-07-23
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-433 | Brooklyn 10 Pier /53rd St Rehab | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-08-14 | 2016-07-01 | 2016-08-14
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-433 | Brooklyn 10 Pier /53rd St Rehab | 2 | PRELIMINARY DESIGN | 2016-08-15 | 2016-12-12 | 2016-08-15 | 2016-12-12
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-433 | Brooklyn 10 Pier /53rd St Rehab | 3 | FINAL DESIGN | 2016-12-13 | 2017-04-11 | 2016-12-13 | 2017-04-11
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-433 | Brooklyn 10 Pier /53rd St Rehab | 4 | BID AWARD AND REGISTER CONTRCT | 2017-04-12 | 2017-08-09 | 2017-04-12 | 2017-08-09
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-433 | Brooklyn 10 Pier /53rd St Rehab | 5 | CONSTRUCTION TO 25% | 2017-08-10 | 2018-08-09 | 2017-08-10 | 2018-08-09
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-433 | Brooklyn 10 Pier /53rd St Rehab | 6 | CONSTRUCTION TO 50% | 2018-08-10 | 2019-08-09 | 2018-08-10 | 2019-08-09
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-433 | Brooklyn 10 Pier /53rd St Rehab | 7 | CONSTRUCTION TO 75% | 2019-08-10 | 2020-08-08 | 2019-08-10 | 2020-08-08
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-433 | Brooklyn 10 Pier /53rd St Rehab | 8 | SUBSTANTIAL COMPLETION | 2020-08-09 | 2022-10-17 | 2020-08-09 | 2022-10-17
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-433 | Brooklyn 10 Pier /53rd St Rehab | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-10-18 | 2024-12-25 | 2022-10-18 | 2024-12-25
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-451 | Brooklyn Greenpoint Warehouse Pump Replacement | 1 | DEVELOP SCOPE | 2018-01-25 | 2018-03-10 | 2018-01-25 | 2018-03-10
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-451 | Brooklyn Greenpoint Warehouse Pump Replacement | 2 | PRELIMINARY DESIGN | 2018-03-11 | 2018-06-08 | 2018-03-11 | 2018-06-08
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-451 | Brooklyn Greenpoint Warehouse Pump Replacement | 3 | FINAL DESIGN | 2018-06-09 | 2018-09-06 | 2018-06-09 | 2018-09-06
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-451 | Brooklyn Greenpoint Warehouse Pump Replacement | 4 | BID AWARD AND REGISTER CONTRCT | 2018-09-07 | 2019-01-04 | 2018-09-07 | 2019-01-04
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-451 | Brooklyn Greenpoint Warehouse Pump Replacement | 5 | CONSTRUCTION TO 25% | 2019-01-05 | 2019-05-04 | 2019-01-05 | 2019-05-04
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-451 | Brooklyn Greenpoint Warehouse Pump Replacement | 6 | CONSTRUCTION TO 50% | 2019-05-05 | 2019-09-01 | 2019-05-05 | 2019-09-01
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-451 | Brooklyn Greenpoint Warehouse Pump Replacement | 7 | CONSTRUCTION TO 75% | 2019-09-02 | 2020-03-19 | 2019-09-02 | 2020-03-19
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-451 | Brooklyn Greenpoint Warehouse Pump Replacement | 8 | SUBSTANTIAL COMPLETION | 2020-03-20 | 2021-01-13 | 2020-03-20 | 2021-01-13
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-451 | Brooklyn Greenpoint Warehouse Pump Replacement | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-01-14 | 2023-10-10 | 2021-01-14 | 2023-10-10
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-464B | Brooklyn 8 Garage Roof and HVAC Replacement | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-09-28 | 2016-07-01 | 2016-09-28
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-464B | Brooklyn 8 Garage Roof and HVAC Replacement | 2 | PRELIMINARY DESIGN | 2016-09-29 | 2017-01-26 | 2016-09-29 | 2017-01-26
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-464B | Brooklyn 8 Garage Roof and HVAC Replacement | 3 | FINAL DESIGN | 2017-01-27 | 2017-05-26 | 2017-01-27 | 2017-05-26
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-464B | Brooklyn 8 Garage Roof and HVAC Replacement | 4 | BID AWARD AND REGISTER CONTRCT | 2017-05-27 | 2018-05-26 | 2017-05-27 | 2018-05-26
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-464B | Brooklyn 8 Garage Roof and HVAC Replacement | 5 | CONSTRUCTION TO 25% | 2018-05-27 | 2019-05-26 | 2018-05-27 | 2019-05-26
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-464B | Brooklyn 8 Garage Roof and HVAC Replacement | 6 | CONSTRUCTION TO 50% | 2019-05-27 | 2020-05-25 | 2019-05-27 | 2020-05-25
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-464B | Brooklyn 8 Garage Roof and HVAC Replacement | 7 | CONSTRUCTION TO 75% | 2020-05-26 | 2021-05-25 | 2020-05-26 | 2021-05-25
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-464B | Brooklyn 8 Garage Roof and HVAC Replacement | 8 | SUBSTANTIAL COMPLETION | 2021-05-26 | 2024-02-19 | 2021-05-26 | 2024-02-19
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-464B | Brooklyn 8 Garage Roof and HVAC Replacement | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2024-06-18 | 2021-09-23 | 2024-06-18
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-464F | Brooklyn 16 923 Georgia Ave Roof Replacement | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-08-14 | 2016-07-01 | 2016-08-14
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-464F | Brooklyn 16 923 Georgia Ave Roof Replacement | 2 | PRELIMINARY DESIGN | 2016-08-15 | 2017-08-14 | 2016-08-15 | 2017-08-14
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-464F | Brooklyn 16 923 Georgia Ave Roof Replacement | 3 | FINAL DESIGN | 2017-08-15 | 2018-08-14 | 2017-08-15 | 2018-08-14
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-464F | Brooklyn 16 923 Georgia Ave Roof Replacement | 4 | BID AWARD AND REGISTER CONTRCT | 2018-08-15 | 2019-08-14 | 2018-08-15 | 2019-08-14
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-464F | Brooklyn 16 923 Georgia Ave Roof Replacement | 5 | CONSTRUCTION TO 25% | 2019-08-15 | 2020-08-13 | 2019-08-15 | 2020-08-13
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-464F | Brooklyn 16 923 Georgia Ave Roof Replacement | 6 | CONSTRUCTION TO 50% | 2020-08-14 | 2021-08-13 | 2020-08-14 | 2021-08-13
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-464F | Brooklyn 16 923 Georgia Ave Roof Replacement | 7 | CONSTRUCTION TO 75% | 2021-08-14 | 2022-08-13 | 2021-08-14 | 2022-08-13
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-464F | Brooklyn 16 923 Georgia Ave Roof Replacement | 8 | SUBSTANTIAL COMPLETION | 2022-08-14 | 2023-08-13 | 2022-08-14 | 2023-08-13
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-464F | Brooklyn 16 923 Georgia Ave Roof Replacement | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-08-14 | 2024-08-12 | 2023-08-14 | 2024-08-12
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S186-224 | Brooklyn 3 Garage New Construction | 1 | DEVELOP SCOPE | 2004-01-31 | 2005-06-30 | 2004-01-31 | 2005-06-30
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S186-224 | Brooklyn 3 Garage New Construction | 2 | PRELIMINARY DESIGN | 2005-07-01 | 2007-01-30 | 2005-07-01 | 2007-01-30
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S186-224 | Brooklyn 3 Garage New Construction | 3 | FINAL DESIGN | 2007-01-31 | 2007-04-30 | 2007-01-31 | 2008-08-31
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S186-224 | Brooklyn 3 Garage New Construction | 4 | BID AWARD AND REGISTER CONTRCT | 2007-05-01 | 2007-06-30 | 2018-09-01 | 2019-06-30
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S186-224 | Brooklyn 3 Garage New Construction | 5 | CONSTRUCTION TO 25% | 2007-07-01 | 2008-12-31 | 2019-07-01 | 2020-04-25
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S186-224 | Brooklyn 3 Garage New Construction | 6 | CONSTRUCTION TO 50% | 2009-01-01 | 2009-12-31 | 2020-04-26 | 2021-02-19
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S186-224 | Brooklyn 3 Garage New Construction | 7 | CONSTRUCTION TO 75% | 2010-01-01 | 2010-12-31 | 2021-02-20 | 2021-12-16
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S186-224 | Brooklyn 3 Garage New Construction | 8 | SUBSTANTIAL COMPLETION | 2011-01-01 | 2011-12-31 | 2021-12-17 | 2022-10-12
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S186-224 | Brooklyn 3 Garage New Construction | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-01-01 | 2013-03-30 | 2022-10-13 | 2024-07-08
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S195-227K | BROOKLYN 7/10 SALT SHED REPLACEMENT | 1 | DEVELOP SCOPE | 2017-08-01 | 2018-02-06 | 2017-08-01 | 2018-02-06
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S195-227K | BROOKLYN 7/10 SALT SHED REPLACEMENT | 2 | PRELIMINARY DESIGN | 2018-02-07 | 2018-08-25 | 2018-02-07 | 2018-08-25
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S195-227K | BROOKLYN 7/10 SALT SHED REPLACEMENT | 3 | FINAL DESIGN | 2018-08-26 | 2019-03-13 | 2018-08-26 | 2019-03-13
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S195-227K | BROOKLYN 7/10 SALT SHED REPLACEMENT | 4 | BID AWARD AND REGISTER CONTRCT | 2019-03-14 | 2019-09-29 | 2019-03-14 | 2019-09-29
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S195-227K | BROOKLYN 7/10 SALT SHED REPLACEMENT | 5 | CONSTRUCTION TO 25% | 2019-09-30 | 2020-04-16 | 2019-09-30 | 2020-04-16
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S195-227K | BROOKLYN 7/10 SALT SHED REPLACEMENT | 6 | CONSTRUCTION TO 50% | 2020-04-17 | 2020-11-02 | 2020-04-17 | 2020-11-02
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S195-227K | BROOKLYN 7/10 SALT SHED REPLACEMENT | 7 | CONSTRUCTION TO 75% | 2020-11-03 | 2021-05-21 | 2020-11-03 | 2021-05-21
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S195-227K | BROOKLYN 7/10 SALT SHED REPLACEMENT | 8 | SUBSTANTIAL COMPLETION | 2021-05-22 | 2023-11-07 | 2021-05-22 | 2023-11-07
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S195-227K | BROOKLYN 7/10 SALT SHED REPLACEMENT | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-11-08 | 2026-04-25 | 2023-11-08 | 2026-04-25
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S195-228J | Brooklyn Navy Yard Salt Storage Facility Rehabilitation | 1 | DEVELOP SCOPE | 2018-02-01 | 2018-03-17 | 2018-02-01 | 2018-03-17
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S195-228J | Brooklyn Navy Yard Salt Storage Facility Rehabilitation | 2 | PRELIMINARY DESIGN | 2018-03-18 | 2018-05-16 | 2018-03-18 | 2018-05-16
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S195-228J | Brooklyn Navy Yard Salt Storage Facility Rehabilitation | 3 | FINAL DESIGN | 2018-05-17 | 2018-07-15 | 2018-05-17 | 2018-07-15
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S195-228J | Brooklyn Navy Yard Salt Storage Facility Rehabilitation | 4 | BID AWARD AND REGISTER CONTRCT | 2018-07-16 | 2019-01-11 | 2018-07-16 | 2019-01-11
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S195-228J | Brooklyn Navy Yard Salt Storage Facility Rehabilitation | 5 | CONSTRUCTION TO 25% | 2019-01-12 | 2019-09-08 | 2019-01-12 | 2019-09-08
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S195-228J | Brooklyn Navy Yard Salt Storage Facility Rehabilitation | 6 | CONSTRUCTION TO 50% | 2019-09-09 | 2020-05-05 | 2019-09-09 | 2020-05-05
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S195-228J | Brooklyn Navy Yard Salt Storage Facility Rehabilitation | 7 | CONSTRUCTION TO 75% | 2020-05-06 | 2020-09-02 | 2020-05-06 | 2020-09-02
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S195-228J | Brooklyn Navy Yard Salt Storage Facility Rehabilitation | 8 | SUBSTANTIAL COMPLETION | 2020-09-03 | 2021-03-21 | 2020-09-03 | 2021-03-21
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S195-228J | Brooklyn Navy Yard Salt Storage Facility Rehabilitation | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-22 | 2021-07-19 | 2021-03-22 | 2021-07-19
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S216-403A | Hamilton Avenue MTS Bulkhead | 1 | DEVELOP SCOPE | 2019-01-16 | 2019-04-15 | 2019-01-16 | 2019-04-15
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S216-403A | Hamilton Avenue MTS Bulkhead | 2 | PRELIMINARY DESIGN | 2019-04-16 | 2019-08-13 | 2019-04-16 | 2019-08-13
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S216-403A | Hamilton Avenue MTS Bulkhead | 3 | FINAL DESIGN | 2019-08-14 | 2020-02-09 | 2019-08-14 | 2020-02-09
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S216-403A | Hamilton Avenue MTS Bulkhead | 4 | BID AWARD AND REGISTER CONTRCT | 2020-02-10 | 2020-06-30 | 2020-02-10 | 2020-06-30
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S216-403A | Hamilton Avenue MTS Bulkhead | 5 | CONSTRUCTION TO 25% | 2020-07-01 | 2021-06-30 | 2020-07-01 | 2021-06-30
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S216-403A | Hamilton Avenue MTS Bulkhead | 6 | CONSTRUCTION TO 50% | 2021-07-01 | 2022-06-30 | 2021-07-01 | 2022-06-30
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S216-403A | Hamilton Avenue MTS Bulkhead | 7 | CONSTRUCTION TO 75% | 2022-07-01 | 2023-06-30 | 2022-07-01 | 2023-06-30
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S216-403A | Hamilton Avenue MTS Bulkhead | 8 | ORIGINAL EQUIP & FURNISHING | 2023-07-01 | 2024-06-29 | 2023-07-01 | 2024-06-29
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S216-403A | Hamilton Avenue MTS Bulkhead | 9 | SUBSTANTIAL COMPLETION | 2024-06-30 | 2025-06-29 | 2024-06-30 | 2025-06-29
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S216-403A | Hamilton Avenue MTS Bulkhead | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-06-30 | 2025-07-29 | 2025-06-30 | 2025-07-29
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S216-403C | Hamilton Avenue MTS Rehab | 1 | DEVELOP SCOPE | 2019-11-16 | 2020-02-13 | 2019-11-16 | 2020-02-13
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S216-403C | Hamilton Avenue MTS Rehab | 2 | PRELIMINARY DESIGN | 2020-02-14 | 2020-08-11 | 2020-02-14 | 2020-08-11
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S216-403C | Hamilton Avenue MTS Rehab | 3 | FINAL DESIGN | 2020-08-12 | 2021-02-07 | 2020-08-12 | 2021-02-07
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S216-403C | Hamilton Avenue MTS Rehab | 4 | BID AWARD AND REGISTER CONTRCT | 2021-02-08 | 2021-06-30 | 2021-02-08 | 2021-06-30
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S216-403C | Hamilton Avenue MTS Rehab | 5 | CONSTRUCTION TO 25% | 2021-07-01 | 2021-12-27 | 2021-07-01 | 2021-12-27
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S216-403C | Hamilton Avenue MTS Rehab | 6 | CONSTRUCTION TO 50% | 2021-12-28 | 2022-06-25 | 2021-12-28 | 2022-06-25
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S216-403C | Hamilton Avenue MTS Rehab | 7 | CONSTRUCTION TO 75% | 2022-06-26 | 2022-12-22 | 2022-06-26 | 2022-12-22
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S216-403C | Hamilton Avenue MTS Rehab | 8 | SUBSTANTIAL COMPLETION | 2022-12-23 | 2024-01-26 | 2022-12-23 | 2024-01-26
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S216-403C | Hamilton Avenue MTS Rehab | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-01-27 | 2025-03-01 | 2024-01-27 | 2025-03-01
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDBK11C | Hurricane Sandy Brooklyn 11 Conduit Replacement | 1 | DEVELOP SCOPE | 2015-08-25 | 2018-02-09 | 2015-08-25 | 2018-02-09
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDBK11C | Hurricane Sandy Brooklyn 11 Conduit Replacement | 2 | PRELIMINARY DESIGN | 2018-02-10 | 2018-04-10 | 2018-02-10 | 2018-04-10
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDBK11C | Hurricane Sandy Brooklyn 11 Conduit Replacement | 3 | FINAL DESIGN | 2018-04-11 | 2018-06-09 | 2018-04-11 | 2018-06-09
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDBK11C | Hurricane Sandy Brooklyn 11 Conduit Replacement | 4 | BID AWARD AND REGISTER CONTRCT | 2018-06-10 | 2018-09-07 | 2018-06-10 | 2018-09-07
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDBK11C | Hurricane Sandy Brooklyn 11 Conduit Replacement | 5 | CONSTRUCTION TO 25% | 2018-09-08 | 2019-03-26 | 2018-09-08 | 2019-03-26
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDBK11C | Hurricane Sandy Brooklyn 11 Conduit Replacement | 6 | CONSTRUCTION TO 50% | 2019-03-27 | 2019-10-12 | 2019-03-27 | 2019-10-12
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDBK11C | Hurricane Sandy Brooklyn 11 Conduit Replacement | 7 | CONSTRUCTION TO 75% | 2019-10-13 | 2020-04-29 | 2019-10-13 | 2020-04-29
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDBK11C | Hurricane Sandy Brooklyn 11 Conduit Replacement | 8 | SUBSTANTIAL COMPLETION | 2020-04-30 | 2021-09-11 | 2020-04-30 | 2021-09-11
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDBK11C | Hurricane Sandy Brooklyn 11 Conduit Replacement | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-12 | 2024-06-07 | 2021-09-12 | 2024-06-07
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDBK11G | Hurricane Sandy Brooklyn 11 R/R & Haz Mitigation | 1 | DEVELOP SCOPE | 2015-08-25 | 2018-02-09 | 2015-08-25 | 2018-02-09
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDBK11G | Hurricane Sandy Brooklyn 11 R/R & Haz Mitigation | 2 | PRELIMINARY DESIGN | 2018-02-10 | 2018-04-10 | 2018-02-10 | 2018-04-10
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDBK11G | Hurricane Sandy Brooklyn 11 R/R & Haz Mitigation | 3 | FINAL DESIGN | 2018-04-11 | 2018-06-09 | 2018-04-11 | 2018-06-09
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDBK11G | Hurricane Sandy Brooklyn 11 R/R & Haz Mitigation | 4 | BID AWARD AND REGISTER CONTRCT | 2018-06-10 | 2018-09-07 | 2018-06-10 | 2018-09-07
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDBK11G | Hurricane Sandy Brooklyn 11 R/R & Haz Mitigation | 5 | CONSTRUCTION TO 25% | 2018-09-08 | 2019-03-26 | 2018-09-08 | 2019-03-26
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDBK11G | Hurricane Sandy Brooklyn 11 R/R & Haz Mitigation | 6 | CONSTRUCTION TO 50% | 2019-03-27 | 2019-10-12 | 2019-03-27 | 2019-10-12
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDBK11G | Hurricane Sandy Brooklyn 11 R/R & Haz Mitigation | 7 | CONSTRUCTION TO 75% | 2019-10-13 | 2020-04-29 | 2019-10-13 | 2020-04-29
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDBK11G | Hurricane Sandy Brooklyn 11 R/R & Haz Mitigation | 8 | SUBSTANTIAL COMPLETION | 2020-04-30 | 2021-09-11 | 2020-04-30 | 2021-09-11
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDBK11G | Hurricane Sandy Brooklyn 11 R/R & Haz Mitigation | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-12 | 2024-06-07 | 2021-09-12 | 2024-06-07
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDBK4FA | Hurricane Sandy Brooklyn 1/4 Fire Alarm Replacement | 1 | DEVELOP SCOPE | 2015-08-25 | 2016-02-20 | 2015-08-25 | 2016-02-20
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDBK4FA | Hurricane Sandy Brooklyn 1/4 Fire Alarm Replacement | 2 | PRELIMINARY DESIGN | 2016-02-21 | 2016-08-18 | 2016-02-21 | 2016-08-18
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDBK4FA | Hurricane Sandy Brooklyn 1/4 Fire Alarm Replacement | 3 | FINAL DESIGN | 2016-08-19 | 2017-08-18 | 2016-08-19 | 2017-08-18
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDBK4FA | Hurricane Sandy Brooklyn 1/4 Fire Alarm Replacement | 4 | BID AWARD AND REGISTER CONTRCT | 2017-08-19 | 2018-08-18 | 2017-08-19 | 2018-08-18
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDBK4FA | Hurricane Sandy Brooklyn 1/4 Fire Alarm Replacement | 5 | CONSTRUCTION TO 25% | 2018-08-19 | 2019-08-18 | 2018-08-19 | 2019-08-18
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDBK4FA | Hurricane Sandy Brooklyn 1/4 Fire Alarm Replacement | 6 | CONSTRUCTION TO 50% | 2019-08-19 | 2020-08-17 | 2019-08-19 | 2020-08-17
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDBK4FA | Hurricane Sandy Brooklyn 1/4 Fire Alarm Replacement | 7 | CONSTRUCTION TO 75% | 2020-08-19 | 2021-08-18 | 2020-08-19 | 2021-08-18
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDBK4FA | Hurricane Sandy Brooklyn 1/4 Fire Alarm Replacement | 8 | SUBSTANTIAL COMPLETION | 2021-08-19 | 2024-05-14 | 2021-08-19 | 2024-05-14
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDBK4FA | Hurricane Sandy Brooklyn 1/4 Fire Alarm Replacement | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-12-17 | 2024-09-11 | 2021-12-17 | 2024-09-11
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDGPTWH | Hurricane Sandy GRNPT Warehouse R/R & Haz Mitigation | 1 | DEVELOP SCOPE | 2015-08-25 | 2015-12-22 | 2015-08-25 | 2015-12-22
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDGPTWH | Hurricane Sandy GRNPT Warehouse R/R & Haz Mitigation | 2 | PRELIMINARY DESIGN | 2015-12-23 | 2016-06-19 | 2015-12-23 | 2016-06-19
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDGPTWH | Hurricane Sandy GRNPT Warehouse R/R & Haz Mitigation | 3 | FINAL DESIGN | 2016-06-20 | 2017-06-19 | 2016-06-20 | 2017-06-19
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDGPTWH | Hurricane Sandy GRNPT Warehouse R/R & Haz Mitigation | 4 | BID AWARD AND REGISTER CONTRCT | 2017-06-20 | 2018-06-19 | 2017-06-20 | 2018-06-19
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDGPTWH | Hurricane Sandy GRNPT Warehouse R/R & Haz Mitigation | 5 | CONSTRUCTION TO 25% | 2018-06-20 | 2019-06-19 | 2018-06-20 | 2019-06-19
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDGPTWH | Hurricane Sandy GRNPT Warehouse R/R & Haz Mitigation | 6 | CONSTRUCTION TO 50% | 2019-06-20 | 2020-06-18 | 2019-06-20 | 2020-06-18
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDGPTWH | Hurricane Sandy GRNPT Warehouse R/R & Haz Mitigation | 7 | CONSTRUCTION TO 75% | 2020-06-19 | 2023-03-15 | 2020-06-19 | 2023-03-15
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDGPTWH | Hurricane Sandy GRNPT Warehouse R/R & Haz Mitigation | 8 | SUBSTANTIAL COMPLETION | 2023-03-16 | 2025-12-09 | 2023-03-16 | 2025-12-09
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDGPTWH | Hurricane Sandy GRNPT Warehouse R/R & Haz Mitigation | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-07-14 | 2026-04-08 | 2023-07-14 | 2026-04-08
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDGPWHC | Hurricane Sandy GRNPT Warehouse Conduit Replacement | 1 | DEVELOP SCOPE | 2017-08-25 | 2018-05-31 | 2017-08-25 | 2018-05-31
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDGPWHC | Hurricane Sandy GRNPT Warehouse Conduit Replacement | 2 | PRELIMINARY DESIGN | 2018-06-01 | 2019-03-07 | 2018-06-01 | 2019-03-07
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDGPWHC | Hurricane Sandy GRNPT Warehouse Conduit Replacement | 3 | FINAL DESIGN | 2019-03-08 | 2019-12-12 | 2019-03-08 | 2019-12-12
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDGPWHC | Hurricane Sandy GRNPT Warehouse Conduit Replacement | 4 | BID AWARD AND REGISTER CONTRCT | 2019-12-13 | 2020-09-17 | 2019-12-13 | 2020-09-17
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDGPWHC | Hurricane Sandy GRNPT Warehouse Conduit Replacement | 5 | CONSTRUCTION TO 25% | 2020-09-18 | 2021-06-24 | 2020-09-18 | 2021-06-24
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDGPWHC | Hurricane Sandy GRNPT Warehouse Conduit Replacement | 6 | CONSTRUCTION TO 50% | 2021-06-25 | 2022-03-31 | 2021-06-25 | 2022-03-31
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDGPWHC | Hurricane Sandy GRNPT Warehouse Conduit Replacement | 7 | CONSTRUCTION TO 75% | 2022-04-01 | 2023-01-05 | 2022-04-01 | 2023-01-05
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDGPWHC | Hurricane Sandy GRNPT Warehouse Conduit Replacement | 8 | SUBSTANTIAL COMPLETION | 2023-01-06 | 2025-06-23 | 2023-01-06 | 2025-06-23
20201123 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDGPWHC | Hurricane Sandy GRNPT Warehouse Conduit Replacement | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-06-24 | 2027-12-10 | 2025-06-24 | 2027-12-10
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT601 | DOT - Hamilton Administrative Building | 1 | DEVELOP SCOPE | 2018-06-30 | 2018-09-27 | 2019-06-30 | 2019-09-27
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT601 | DOT - Hamilton Administrative Building | 2 | PRELIMINARY DESIGN | 2018-09-28 | 2019-01-25 | 2019-09-28 | 2020-01-25
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT601 | DOT - Hamilton Administrative Building | 3 | FINAL DESIGN | 2019-01-26 | 2019-07-24 | 2020-01-26 | 2020-07-23
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT601 | DOT - Hamilton Administrative Building | 4 | BID AWARD AND REGISTER CONTRCT | 2019-07-25 | 2019-10-22 | 2020-07-24 | 2020-10-21
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT601 | DOT - Hamilton Administrative Building | 5 | CONSTRUCTION TO 25% | 2019-10-23 | 2020-02-19 | 2020-10-22 | 2021-02-18
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT601 | DOT - Hamilton Administrative Building | 6 | CONSTRUCTION TO 50% | 2020-02-20 | 2020-06-18 | 2021-02-19 | 2021-06-18
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT601 | DOT - Hamilton Administrative Building | 7 | CONSTRUCTION TO 75% | 2020-06-19 | 2020-10-16 | 2021-06-19 | 2021-10-16
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT601 | DOT - Hamilton Administrative Building | 8 | ORIGINAL EQUIP & FURNISHING | 2020-10-17 | 2021-01-14 | 2021-10-17 | 2022-01-14
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT601 | DOT - Hamilton Administrative Building | 9 | SUBSTANTIAL COMPLETION | 2021-01-15 | 2021-03-15 | 2022-01-15 | 2022-03-15
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT601 | DOT - Hamilton Administrative Building | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-16 | 2021-04-14 | 2022-03-16 | 2023-06-30
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT802 | DOT - Parking Garage LED Lighting Upgrade | 1 | DEVELOP SCOPE | 2018-06-30 | 2018-09-27 | 2018-06-30 | 2018-09-27
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT802 | DOT - Parking Garage LED Lighting Upgrade | 2 | PRELIMINARY DESIGN | 2018-09-28 | 2019-01-25 | 2018-09-28 | 2022-06-30
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT802 | DOT - Parking Garage LED Lighting Upgrade | 3 | FINAL DESIGN | 2019-01-26 | 2019-07-24 | 2019-01-26 | 2019-07-24
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT802 | DOT - Parking Garage LED Lighting Upgrade | 4 | BID AWARD AND REGISTER CONTRCT | 2019-07-25 | 2019-10-22 | 2019-07-25 | 2019-10-22
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT802 | DOT - Parking Garage LED Lighting Upgrade | 5 | CONSTRUCTION TO 25% | 2019-10-23 | 2020-02-19 | 2019-10-23 | 2020-02-19
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT802 | DOT - Parking Garage LED Lighting Upgrade | 6 | CONSTRUCTION TO 50% | 2020-02-20 | 2020-06-18 | 2020-02-20 | 2020-06-18
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT802 | DOT - Parking Garage LED Lighting Upgrade | 7 | CONSTRUCTION TO 75% | 2020-06-19 | 2020-10-16 | 2020-06-19 | 2020-06-20
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT802 | DOT - Parking Garage LED Lighting Upgrade | 8 | ORIGINAL EQUIP & FURNISHING | 2020-10-17 | 2021-01-14 | 2020-06-21 | 2020-06-22
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT802 | DOT - Parking Garage LED Lighting Upgrade | 9 | SUBSTANTIAL COMPLETION | 2021-01-15 | 2021-03-15 | 2020-06-23 | 2020-06-24
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT802 | DOT - Parking Garage LED Lighting Upgrade | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-16 | 2021-04-14 | 2020-06-25 | 2022-06-30
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | BEDSTLIG | DOT BEDFORD HISTORIC LIGHT RESTORATION | 1 | BID AWARD AND REGISTER CONTRCT | 2019-06-30 | 2019-06-30 | 2022-06-30 | 2022-06-30
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | BEDSTLIG | DOT BEDFORD HISTORIC LIGHT RESTORATION | 2 | CONSTRUCTION START | 2019-07-01 | 2019-08-14 | 2022-07-01 | 2022-08-14
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | BEDSTLIG | DOT BEDFORD HISTORIC LIGHT RESTORATION | 3 | CONSTRUCTION COMPLETION | 2019-08-15 | 2021-03-06 | 2022-08-15 | 2024-03-06
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | BKBRDGCAM | Brooklyn Bridge Surveillance Cameras | 1 | BID AWARD AND REGISTER CONTRCT | 2015-06-30 | 2015-06-30 | 2024-06-30 | 2024-06-30
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | BKBRDGCAM | Brooklyn Bridge Surveillance Cameras | 2 | CONSTRUCTION START | 2015-07-01 | 2015-08-14 | 2024-07-01 | 2024-08-14
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | BKBRDGCAM | Brooklyn Bridge Surveillance Cameras | 3 | CONSTRUCTION COMPLETION | 2015-08-15 | 2017-03-06 | 2024-08-15 | 2026-03-07
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | BKBRDGITS | Brooklyn Bridge Approaches-DOT ITS | 1 | BID AWARD AND REGISTER CONTRCT | 2016-07-01 | 2016-07-01 | 2020-07-01 | 2020-07-01
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | BKBRDGITS | Brooklyn Bridge Approaches-DOT ITS | 2 | CONSTRUCTION START | 2016-07-02 | 2016-08-15 | 2020-07-02 | 2020-08-15
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | BKBRDGITS | Brooklyn Bridge Approaches-DOT ITS | 3 | CONSTRUCTION COMPLETION | 2016-08-16 | 2018-03-08 | 2020-08-16 | 2022-03-08
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBK1023 | MILL BASIN BR / BELT PARKWAY #2-23147-9/TN | 1 | DEVELOP SCOPE | 2006-07-01 | 2007-06-30 | 0 | 0
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBK1023 | MILL BASIN BR / BELT PARKWAY #2-23147-9/TN | 2 | DESIGN START | 2007-07-01 | 2011-06-29 | 2023-08-25 | 2024-08-23
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBK1023 | MILL BASIN BR / BELT PARKWAY #2-23147-9/TN | 3 | CONSTRUCTION START | 2011-06-30 | 2013-06-28 | 2012-03-26 | 2014-08-26
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBK1023 | MILL BASIN BR / BELT PARKWAY #2-23147-9/TN | 5 | CONSTRUCTION START | 2011-06-30 | 2013-06-28 | 2014-08-27 | 2021-08-25
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBK1201 | ATLANTIC AVENUE/LIRR ATLANTIC AVENUE 2-243569 | 1 | DEVELOP SCOPE | 2002-07-01 | 2003-06-30 | 2011-02-18 | 2011-06-18
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBK1201 | ATLANTIC AVENUE/LIRR ATLANTIC AVENUE 2-243569 | 2 | DESIGN START | 2003-07-01 | 2007-06-29 | 2015-06-18 | 2016-11-16
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBK1201 | ATLANTIC AVENUE/LIRR ATLANTIC AVENUE 2-243569 | 3 | CONSTRUCTION START | 2007-06-30 | 2009-06-28 | 2017-07-24 | 2021-06-30
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBK1205 | RECON OF 5TH AVE BRIDGE OVER LIRR AND SEA BEACH, BR 2-243580 | 1 | DEVELOP SCOPE | 2004-06-30 | 2005-06-29 | 2015-11-06 | 2018-03-24
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBK1205 | RECON OF 5TH AVE BRIDGE OVER LIRR AND SEA BEACH, BR 2-243580 | 2 | DESIGN START | 2005-06-30 | 2009-06-28 | 2018-09-05 | 2020-07-28
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBK1205 | RECON OF 5TH AVE BRIDGE OVER LIRR AND SEA BEACH, BR 2-243580 | 3 | CONSTRUCTION START | 2009-06-29 | 2011-06-28 | 2021-07-21 | 2025-10-24
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBK1213 | RECON UNION ST BRIDGE OVER GOWANUS CANAL, BROOKLYN 2-24027-0 | 1 | DEVELOP SCOPE | 2006-04-06 | 2006-06-14 | 0 | 0
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBK1213 | RECON UNION ST BRIDGE OVER GOWANUS CANAL, BROOKLYN 2-24027-0 | 2 | DESIGN START | 2008-01-30 | 2021-04-28 | 2006-04-06 | 2006-06-14
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBK1213 | RECON UNION ST BRIDGE OVER GOWANUS CANAL, BROOKLYN 2-24027-0 | 3 | CONSTRUCTION START | 2022-04-28 | 2024-07-27 | 2008-01-30 | 2021-04-28
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBK1213 | RECON UNION ST BRIDGE OVER GOWANUS CANAL, BROOKLYN 2-24027-0 | 5 | CONSTRUCTION START | 2022-04-28 | 2024-07-27 | 2022-04-28 | 2029-06-30
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBK244120 | HILL DR (TERRACE BR) OVER PROSPECT PARK LAKE BIN:2244120 | 1 | DEVELOP SCOPE | 2017-06-30 | 2018-06-29 | 0 | 0
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBK244120 | HILL DR (TERRACE BR) OVER PROSPECT PARK LAKE BIN:2244120 | 2 | DESIGN START | 2018-06-30 | 2022-06-28 | 2017-06-30 | 2018-06-29
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBK244120 | HILL DR (TERRACE BR) OVER PROSPECT PARK LAKE BIN:2244120 | 3 | CONSTRUCTION START | 2022-06-29 | 2024-06-27 | 2018-06-30 | 2022-06-28
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBK244120 | HILL DR (TERRACE BR) OVER PROSPECT PARK LAKE BIN:2244120 | 5 | CONSTRUCTION START | 2022-06-29 | 2024-06-27 | 2022-06-29 | 2024-06-27
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBK4470 | SEELY STREET OVER PROSPECT AVENUE BIN: 2244470 | 1 | DEVELOP SCOPE | 2015-06-30 | 2016-06-28 | 0 | 0
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBK4470 | SEELY STREET OVER PROSPECT AVENUE BIN: 2244470 | 2 | DESIGN START | 2016-06-29 | 2020-06-27 | 2017-04-24 | 2017-09-20
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBK4470 | SEELY STREET OVER PROSPECT AVENUE BIN: 2244470 | 3 | CONSTRUCTION START | 2020-06-28 | 2022-06-27 | 2019-10-16 | 2022-10-14
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBK4470 | SEELY STREET OVER PROSPECT AVENUE BIN: 2244470 | 5 | CONSTRUCTION START | 2020-06-28 | 2022-06-27 | 2023-09-17 | 2025-11-15
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBK530 | PARKSIDE AVE AND OCEAN AVE RR BR #2-24302-0 | 1 | DEVELOP SCOPE | 2006-07-01 | 2007-06-30 | 2015-11-06 | 2016-02-23
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBK530 | PARKSIDE AVE AND OCEAN AVE RR BR #2-24302-0 | 2 | DESIGN START | 2007-07-01 | 2011-06-29 | 2018-01-04 | 2022-02-24
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBK530 | PARKSIDE AVE AND OCEAN AVE RR BR #2-24302-0 | 3 | CONSTRUCTION START | 2011-06-30 | 2013-06-28 | 2023-02-24 | 2026-11-28
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA23036 | UNION ST OVER 278I BQE BIN 2230360 | 1 | DEVELOP SCOPE | 2025-07-01 | 2026-06-30 | 0 | 0
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA23036 | UNION ST OVER 278I BQE BIN 2230360 | 2 | DEVELOP SCOPE | 2026-07-01 | 2030-06-29 | 2019-11-12 | 2020-11-06
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA23036 | UNION ST OVER 278I BQE BIN 2230360 | 3 | DESIGN START | 2030-06-30 | 2032-06-28 | 2021-10-20 | 2023-03-25
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA23036 | UNION ST OVER 278I BQE BIN 2230360 | 5 | CONSTRUCTION START | 2030-06-30 | 2032-06-28 | 2025-08-09 | 2027-07-10
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA23038 | KANE ST/ 278I (BQE) BIN# 2230380 | 1 | DEVELOP SCOPE | 2018-06-30 | 2018-09-27 | 2017-04-26 | 2017-06-19
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA23038 | KANE ST/ 278I (BQE) BIN# 2230380 | 2 | PRELIMINARY DESIGN | 2018-09-28 | 2019-01-25 | 2017-06-20 | 2017-10-17
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA23038 | KANE ST/ 278I (BQE) BIN# 2230380 | 3 | FINAL DESIGN | 2019-01-26 | 2019-07-24 | 2017-10-18 | 2018-04-15
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA23038 | KANE ST/ 278I (BQE) BIN# 2230380 | 4 | BID AWARD AND REGISTER CONTRCT | 2019-07-25 | 2019-10-22 | 2018-04-16 | 2018-07-14
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA23038 | KANE ST/ 278I (BQE) BIN# 2230380 | 5 | CONSTRUCTION TO 25% | 2019-10-23 | 2020-02-19 | 2018-07-15 | 2018-11-11
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA23038 | KANE ST/ 278I (BQE) BIN# 2230380 | 6 | CONSTRUCTION TO 50% | 2020-02-20 | 2020-06-18 | 2018-11-12 | 2019-03-11
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA23038 | KANE ST/ 278I (BQE) BIN# 2230380 | 7 | CONSTRUCTION TO 75% | 2020-06-19 | 2020-10-16 | 2019-03-12 | 2019-07-09
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA23038 | KANE ST/ 278I (BQE) BIN# 2230380 | 8 | ORIGINAL EQUIP & FURNISHING | 2020-10-17 | 2021-01-14 | 2019-07-10 | 2019-10-07
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA23038 | KANE ST/ 278I (BQE) BIN# 2230380 | 9 | SUBSTANTIAL COMPLETION | 2021-01-15 | 2021-03-15 | 2019-10-08 | 2019-12-06
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA23038 | KANE ST/ 278I (BQE) BIN# 2230380 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-16 | 2021-04-14 | 2019-12-07 | 2024-01-05
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA23140 | BSHP over Sheepshead Bay Road BIN 2231409 | 1 | DEVELOP SCOPE | 2023-06-30 | 2024-06-28 | 0 | 0
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA23140 | BSHP over Sheepshead Bay Road BIN 2231409 | 2 | DESIGN START | 2024-06-29 | 2028-06-27 | 2017-06-08 | 2017-08-04
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA23140 | BSHP over Sheepshead Bay Road BIN 2231409 | 3 | CONSTRUCTION START | 2028-06-28 | 2030-06-27 | 2020-07-22 | 2022-05-08
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA23140 | BSHP over Sheepshead Bay Road BIN 2231409 | 5 | CONSTRUCTION START | 2028-06-28 | 2030-06-27 | 2024-06-20 | 2027-06-19
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA23141 | BSHP over Ocean Ave BIN 2231419 | 1 | DEVELOP SCOPE | 2023-06-30 | 2024-06-28 | 0 | 0
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA23141 | BSHP over Ocean Ave BIN 2231419 | 2 | DESIGN START | 2024-06-29 | 2028-06-27 | 2017-06-08 | 2017-08-04
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA23141 | BSHP over Ocean Ave BIN 2231419 | 3 | CONSTRUCTION START | 2028-06-28 | 2030-06-27 | 2020-07-22 | 2023-07-21
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA23141 | BSHP over Ocean Ave BIN 2231419 | 5 | CONSTRUCTION START | 2028-06-28 | 2030-06-27 | 2024-06-22 | 2028-09-19
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA23142 | BSHP OVER BEDFORD AVE BIN 2231429 | 1 | DEVELOP SCOPE | 2021-06-30 | 2022-06-29 | 0 | 0
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA23142 | BSHP OVER BEDFORD AVE BIN 2231429 | 2 | DESIGN START | 2022-06-30 | 2026-06-28 | 2017-06-08 | 2017-08-04
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA23142 | BSHP OVER BEDFORD AVE BIN 2231429 | 3 | CONSTRUCTION START | 2026-06-29 | 2028-06-27 | 2020-07-22 | 2023-07-21
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA23142 | BSHP OVER BEDFORD AVE BIN 2231429 | 5 | CONSTRUCTION START | 2026-06-29 | 2028-06-27 | 2024-06-23 | 2026-09-20
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA23143 | Belt Shore Pkwy over Nostrand Ave 2231439 | 1 | DEVELOP SCOPE | 2016-06-30 | 2017-06-29 | 0 | 0
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA23143 | Belt Shore Pkwy over Nostrand Ave 2231439 | 2 | DESIGN START | 2017-06-30 | 2021-06-28 | 2016-06-30 | 2017-06-29
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA23143 | Belt Shore Pkwy over Nostrand Ave 2231439 | 3 | CONSTRUCTION START | 2021-06-29 | 2023-06-28 | 2017-06-30 | 2021-06-28
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA23143 | Belt Shore Pkwy over Nostrand Ave 2231439 | 5 | CONSTRUCTION START | 2021-06-29 | 2023-06-28 | 2021-06-29 | 2023-06-28
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA23308 | E 14TH ST PED BRIDGE BIN:2233080 | 1 | DEVELOP SCOPE | 2018-06-30 | 2019-06-29 | 0 | 0
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA23308 | E 14TH ST PED BRIDGE BIN:2233080 | 2 | DESIGN START | 2019-06-30 | 2023-06-28 | 2016-04-22 | 2016-09-21
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA23308 | E 14TH ST PED BRIDGE BIN:2233080 | 3 | CONSTRUCTION START | 2023-06-29 | 2025-06-27 | 2018-07-10 | 2021-09-26
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA23308 | E 14TH ST PED BRIDGE BIN:2233080 | 5 | CONSTRUCTION START | 2023-06-29 | 2025-06-27 | 2022-09-04 | 2024-11-12
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA24310 | Beverly Road over BMT Subway, Brighton BIN 2243100 | 1 | DEVELOP SCOPE | 2017-06-30 | 2018-06-29 | 0 | 0
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA24310 | Beverly Road over BMT Subway, Brighton BIN 2243100 | 2 | DESIGN START | 2018-06-30 | 2022-06-28 | 2017-08-08 | 2017-09-15
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA24310 | Beverly Road over BMT Subway, Brighton BIN 2243100 | 3 | CONSTRUCTION START | 2022-06-29 | 2024-06-27 | 2020-01-02 | 2022-12-31
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA24310 | Beverly Road over BMT Subway, Brighton BIN 2243100 | 5 | CONSTRUCTION START | 2022-06-29 | 2024-06-27 | 2023-10-25 | 2025-10-23
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA24382 | 21st Ave RR BR & 64th St #2-24382-1/TN35190 | 1 | DEVELOP SCOPE | 2017-06-30 | 2018-06-29 | 0 | 0
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA24382 | 21st Ave RR BR & 64th St #2-24382-1/TN35190 | 2 | DESIGN START | 2018-06-30 | 2022-06-28 | 2018-05-15 | 2019-11-28
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA24382 | 21st Ave RR BR & 64th St #2-24382-1/TN35190 | 3 | CONSTRUCTION START | 2022-06-29 | 2024-06-27 | 2021-03-04 | 2024-03-02
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA24382 | 21st Ave RR BR & 64th St #2-24382-1/TN35190 | 5 | CONSTRUCTION START | 2022-06-29 | 2024-06-27 | 2025-01-31 | 2027-04-01
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBPK17K | 17TH AVENUE PEDESTRIAN BRIDGE OVER BELT PARKWAY 2231300 | 1 | DEVELOP SCOPE | 2014-06-01 | 2015-05-31 | 0 | 0
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBPK17K | 17TH AVENUE PEDESTRIAN BRIDGE OVER BELT PARKWAY 2231300 | 2 | DESIGN START | 2015-06-01 | 2019-05-30 | 2015-06-01 | 2016-05-30
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBPK17K | 17TH AVENUE PEDESTRIAN BRIDGE OVER BELT PARKWAY 2231300 | 3 | CONSTRUCTION START | 2019-05-31 | 2021-05-29 | 2016-05-31 | 2020-05-29
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBPK17K | 17TH AVENUE PEDESTRIAN BRIDGE OVER BELT PARKWAY 2231300 | 5 | CONSTRUCTION START | 2019-05-31 | 2021-05-29 | 2020-05-30 | 2023-05-29
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBPK27K | 27TH AVENUE PEDESTRIAN BRIDGE OVER BELT PARKWAY | 1 | DEVELOP SCOPE | 2014-06-01 | 2015-05-31 | 0 | 0
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBPK27K | 27TH AVENUE PEDESTRIAN BRIDGE OVER BELT PARKWAY | 2 | DESIGN START | 2015-06-01 | 2019-05-30 | 2013-06-01 | 2014-05-31
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBPK27K | 27TH AVENUE PEDESTRIAN BRIDGE OVER BELT PARKWAY | 3 | CONSTRUCTION START | 2019-05-31 | 2021-05-29 | 2014-06-01 | 2018-05-30
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBPK27K | 27TH AVENUE PEDESTRIAN BRIDGE OVER BELT PARKWAY | 5 | CONSTRUCTION START | 2019-05-31 | 2021-05-29 | 2018-05-31 | 2023-05-29
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HW349LUM | IN-HOUSE RESURFACING LUMP SUM - ASPHALT | 1 | DEVELOP SCOPE | 2007-06-01 | 2007-09-28 | 2007-06-01 | 2007-09-01
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HW349LUM | IN-HOUSE RESURFACING LUMP SUM - ASPHALT | 2 | DESIGN START | 2007-09-29 | 2009-03-21 | 2007-09-02 | 2009-03-01
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HW349LUM | IN-HOUSE RESURFACING LUMP SUM - ASPHALT | 3 | CONSTRUCTION START | 2009-03-22 | 2011-03-11 | 2009-03-02 | 2029-06-30
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWCSCH98 | East 98th Street School Safety Improvements | 1 | DEVELOP SCOPE | 2020-06-30 | 2020-09-27 | 2019-08-12 | 2020-01-01
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWCSCH98 | East 98th Street School Safety Improvements | 2 | PRELIMINARY DESIGN | 2020-09-28 | 2021-01-25 | 2021-06-24 | 2022-09-29
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWCSCH98 | East 98th Street School Safety Improvements | 3 | FINAL DESIGN | 2021-01-26 | 2021-07-24 | 2022-09-30 | 2023-03-28
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWCSCH98 | East 98th Street School Safety Improvements | 4 | BID AWARD AND REGISTER CONTRCT | 2021-07-25 | 2021-10-22 | 2024-05-24 | 2024-07-19
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWCSCH98 | East 98th Street School Safety Improvements | 5 | CONSTRUCTION TO 25% | 2021-10-23 | 2022-02-19 | 2024-08-19 | 2025-03-08
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWCSCH98 | East 98th Street School Safety Improvements | 6 | CONSTRUCTION TO 50% | 2022-02-20 | 2022-06-19 | 2025-03-09 | 2025-09-27
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWCSCH98 | East 98th Street School Safety Improvements | 7 | CONSTRUCTION TO 75% | 2022-06-20 | 2022-10-17 | 2025-09-28 | 2026-04-17
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWCSCH98 | East 98th Street School Safety Improvements | 8 | ORIGINAL EQUIP & FURNISHING | 2022-10-18 | 2023-01-15 | 2026-04-18 | 2026-07-16
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWCSCH98 | East 98th Street School Safety Improvements | 9 | SUBSTANTIAL COMPLETION | 2023-01-16 | 2023-03-16 | 2026-07-17 | 2026-09-14
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWCSCH98 | East 98th Street School Safety Improvements | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-03-17 | 2023-04-15 | 2026-09-15 | 2026-10-14
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10109 | JORALEMON STREET IMPROVEMENTS | 1 | DEVELOP SCOPE | 2019-06-30 | 2019-09-27 | 2020-06-30 | 2020-09-27
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10109 | JORALEMON STREET IMPROVEMENTS | 2 | PRELIMINARY DESIGN | 2019-09-28 | 2020-01-25 | 2020-09-28 | 2021-01-25
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10109 | JORALEMON STREET IMPROVEMENTS | 3 | FINAL DESIGN | 2020-01-26 | 2020-07-23 | 2021-01-26 | 2021-07-24
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10109 | JORALEMON STREET IMPROVEMENTS | 4 | BID AWARD AND REGISTER CONTRCT | 2020-07-24 | 2020-10-21 | 2021-07-25 | 2021-10-22
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10109 | JORALEMON STREET IMPROVEMENTS | 5 | CONSTRUCTION TO 25% | 2020-10-22 | 2021-02-18 | 2021-10-23 | 2022-02-19
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10109 | JORALEMON STREET IMPROVEMENTS | 6 | CONSTRUCTION TO 50% | 2021-02-19 | 2021-06-18 | 2022-02-20 | 2022-06-19
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10109 | JORALEMON STREET IMPROVEMENTS | 7 | CONSTRUCTION TO 75% | 2021-06-19 | 2021-10-16 | 2022-06-20 | 2022-10-17
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10109 | JORALEMON STREET IMPROVEMENTS | 8 | ORIGINAL EQUIP & FURNISHING | 2021-10-17 | 2022-01-14 | 2022-10-18 | 2023-01-15
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10109 | JORALEMON STREET IMPROVEMENTS | 9 | SUBSTANTIAL COMPLETION | 2022-01-15 | 2022-03-15 | 2023-01-16 | 2023-03-16
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10109 | JORALEMON STREET IMPROVEMENTS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-16 | 2022-04-14 | 2023-03-17 | 2025-04-15
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10110 | Strickland Avenue - Reconstruction | 1 | DEVELOP SCOPE | 2019-06-30 | 2019-09-27 | 2021-06-30 | 2021-09-27
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10110 | Strickland Avenue - Reconstruction | 2 | PRELIMINARY DESIGN | 2019-09-28 | 2020-01-25 | 2021-09-28 | 2022-01-25
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10110 | Strickland Avenue - Reconstruction | 3 | FINAL DESIGN | 2020-01-26 | 2020-07-23 | 2022-01-26 | 2022-07-24
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10110 | Strickland Avenue - Reconstruction | 4 | BID AWARD AND REGISTER CONTRCT | 2020-07-24 | 2020-10-21 | 2022-07-25 | 2022-10-22
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10110 | Strickland Avenue - Reconstruction | 5 | CONSTRUCTION TO 25% | 2020-10-22 | 2021-02-18 | 2022-10-23 | 2023-02-19
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10110 | Strickland Avenue - Reconstruction | 6 | CONSTRUCTION TO 50% | 2021-02-19 | 2021-06-18 | 2023-02-20 | 2023-06-19
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10110 | Strickland Avenue - Reconstruction | 7 | CONSTRUCTION TO 75% | 2021-06-19 | 2021-10-16 | 2023-06-20 | 2023-10-17
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10110 | Strickland Avenue - Reconstruction | 8 | ORIGINAL EQUIP & FURNISHING | 2021-10-17 | 2022-01-14 | 2023-10-18 | 2024-01-15
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10110 | Strickland Avenue - Reconstruction | 9 | SUBSTANTIAL COMPLETION | 2022-01-15 | 2022-03-15 | 2024-01-16 | 2024-03-15
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10110 | Strickland Avenue - Reconstruction | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-16 | 2022-04-14 | 2024-03-16 | 2025-04-14
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10111 | Intersection Safety Improvements Ocean Parkway & Ave Z | 1 | DEVELOP SCOPE | 2019-06-30 | 2019-09-27 | 2020-06-30 | 2020-09-27
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10111 | Intersection Safety Improvements Ocean Parkway & Ave Z | 2 | PRELIMINARY DESIGN | 2019-09-28 | 2020-01-25 | 2020-09-28 | 2021-01-25
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10111 | Intersection Safety Improvements Ocean Parkway & Ave Z | 3 | FINAL DESIGN | 2020-01-26 | 2020-07-23 | 2021-01-26 | 2021-07-24
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10111 | Intersection Safety Improvements Ocean Parkway & Ave Z | 4 | BID AWARD AND REGISTER CONTRCT | 2020-07-24 | 2020-10-21 | 2021-07-25 | 2021-10-22
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10111 | Intersection Safety Improvements Ocean Parkway & Ave Z | 5 | CONSTRUCTION TO 25% | 2020-10-22 | 2021-02-18 | 2021-10-23 | 2022-02-19
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10111 | Intersection Safety Improvements Ocean Parkway & Ave Z | 6 | CONSTRUCTION TO 50% | 2021-02-19 | 2021-06-18 | 2022-02-20 | 2022-06-19
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10111 | Intersection Safety Improvements Ocean Parkway & Ave Z | 7 | CONSTRUCTION TO 75% | 2021-06-19 | 2021-10-16 | 2022-06-20 | 2022-10-17
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10111 | Intersection Safety Improvements Ocean Parkway & Ave Z | 8 | ORIGINAL EQUIP & FURNISHING | 2021-10-17 | 2022-01-14 | 2022-10-18 | 2023-01-15
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10111 | Intersection Safety Improvements Ocean Parkway & Ave Z | 9 | SUBSTANTIAL COMPLETION | 2022-01-15 | 2022-03-15 | 2023-01-16 | 2023-03-16
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10111 | Intersection Safety Improvements Ocean Parkway & Ave Z | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-16 | 2022-04-14 | 2023-03-17 | 2025-04-15
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10113 | Street Reconstruction in Community Board 14 | 1 | DEVELOP SCOPE | 2019-06-30 | 2019-09-27 | 2020-06-30 | 2020-09-27
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10113 | Street Reconstruction in Community Board 14 | 2 | PRELIMINARY DESIGN | 2019-09-28 | 2020-01-25 | 2020-09-28 | 2021-01-25
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10113 | Street Reconstruction in Community Board 14 | 3 | FINAL DESIGN | 2020-01-26 | 2020-07-23 | 2021-01-26 | 2021-07-24
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10113 | Street Reconstruction in Community Board 14 | 4 | BID AWARD AND REGISTER CONTRCT | 2020-07-24 | 2020-10-21 | 2021-07-25 | 2021-10-22
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10113 | Street Reconstruction in Community Board 14 | 5 | CONSTRUCTION TO 25% | 2020-10-22 | 2021-02-18 | 2021-10-23 | 2022-02-19
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10113 | Street Reconstruction in Community Board 14 | 6 | CONSTRUCTION TO 50% | 2021-02-19 | 2021-06-18 | 2022-02-20 | 2022-06-19
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10113 | Street Reconstruction in Community Board 14 | 7 | CONSTRUCTION TO 75% | 2021-06-19 | 2021-10-16 | 2022-06-20 | 2022-10-17
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10113 | Street Reconstruction in Community Board 14 | 8 | ORIGINAL EQUIP & FURNISHING | 2021-10-17 | 2022-01-14 | 2022-10-18 | 2023-01-15
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10113 | Street Reconstruction in Community Board 14 | 9 | SUBSTANTIAL COMPLETION | 2022-01-15 | 2022-03-15 | 2023-01-16 | 2023-03-16
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10113 | Street Reconstruction in Community Board 14 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-16 | 2022-04-14 | 2023-03-17 | 2025-04-15
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10115 | Safety Improvements Broadway Corridor | 1 | DEVELOP SCOPE | 2016-06-30 | 2016-09-27 | 2020-06-30 | 2020-09-27
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10115 | Safety Improvements Broadway Corridor | 2 | PRELIMINARY DESIGN | 2016-09-28 | 2017-01-25 | 2020-09-28 | 2021-01-25
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10115 | Safety Improvements Broadway Corridor | 3 | FINAL DESIGN | 2017-01-26 | 2017-07-24 | 2021-01-26 | 2021-07-24
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10115 | Safety Improvements Broadway Corridor | 4 | BID AWARD AND REGISTER CONTRCT | 2017-07-25 | 2017-10-22 | 2021-07-25 | 2021-10-22
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10115 | Safety Improvements Broadway Corridor | 5 | CONSTRUCTION TO 25% | 2017-10-23 | 2018-02-19 | 2021-10-23 | 2022-02-19
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10115 | Safety Improvements Broadway Corridor | 6 | CONSTRUCTION TO 50% | 2018-02-20 | 2018-06-19 | 2022-02-20 | 2022-06-19
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10115 | Safety Improvements Broadway Corridor | 7 | CONSTRUCTION TO 75% | 2018-06-20 | 2018-10-17 | 2022-06-20 | 2022-10-17
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10115 | Safety Improvements Broadway Corridor | 8 | ORIGINAL EQUIP & FURNISHING | 2018-10-18 | 2019-01-15 | 2022-10-18 | 2023-01-15
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10115 | Safety Improvements Broadway Corridor | 9 | SUBSTANTIAL COMPLETION | 2019-01-16 | 2019-03-16 | 2023-01-16 | 2023-03-16
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10115 | Safety Improvements Broadway Corridor | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-03-17 | 2019-04-15 | 2023-03-17 | 2025-04-15
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10119 | PS 92 SIDE WALK EXTENSION | 1 | DEVELOP SCOPE | 2021-06-30 | 2021-09-27 | 2021-06-30 | 2021-09-27
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10119 | PS 92 SIDE WALK EXTENSION | 2 | PRELIMINARY DESIGN | 2021-09-28 | 2022-01-25 | 2021-09-28 | 2022-01-25
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10119 | PS 92 SIDE WALK EXTENSION | 3 | FINAL DESIGN | 2022-01-26 | 2022-07-24 | 2022-01-26 | 2022-07-24
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10119 | PS 92 SIDE WALK EXTENSION | 4 | BID AWARD AND REGISTER CONTRCT | 2022-07-25 | 2022-10-22 | 2022-07-25 | 2022-10-22
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10119 | PS 92 SIDE WALK EXTENSION | 5 | CONSTRUCTION TO 25% | 2022-10-23 | 2023-02-19 | 2022-10-23 | 2023-02-19
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10119 | PS 92 SIDE WALK EXTENSION | 6 | CONSTRUCTION TO 50% | 2023-02-20 | 2023-06-19 | 2023-02-20 | 2023-06-19
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10119 | PS 92 SIDE WALK EXTENSION | 7 | CONSTRUCTION TO 75% | 2023-06-20 | 2023-10-17 | 2023-06-20 | 2023-10-17
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10119 | PS 92 SIDE WALK EXTENSION | 8 | ORIGINAL EQUIP & FURNISHING | 2023-10-18 | 2024-01-15 | 2023-10-18 | 2024-01-15
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10119 | PS 92 SIDE WALK EXTENSION | 9 | SUBSTANTIAL COMPLETION | 2024-01-16 | 2024-03-15 | 2024-01-16 | 2024-03-15
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10119 | PS 92 SIDE WALK EXTENSION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-03-16 | 2024-04-14 | 2024-03-16 | 2025-04-14
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK00502 | 8th Avenue Sunset Park Chinatown Archway | 1 | DEVELOP SCOPE | 2016-06-30 | 2016-10-27 | 2024-06-30 | 2024-10-27
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK00502 | 8th Avenue Sunset Park Chinatown Archway | 2 | DESIGN START | 2016-10-28 | 2018-04-20 | 2024-10-28 | 2026-04-20
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK00502 | 8th Avenue Sunset Park Chinatown Archway | 3 | CONSTRUCTION START | 2018-04-21 | 2020-04-09 | 2026-04-21 | 2029-04-09
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK00503 | BQ Green | 1 | DEVELOP SCOPE | 2015-06-30 | 2015-10-27 | 2020-06-30 | 2020-10-27
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK00503 | BQ Green | 2 | DESIGN START | 2015-10-28 | 2017-04-19 | 2020-10-28 | 2022-04-20
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK00503 | BQ Green | 3 | CONSTRUCTION START | 2017-04-20 | 2019-04-09 | 2022-04-21 | 2027-04-09
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK00504 | Atlantic Avenue - Purchase of WalkNYC Signs | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2019-07-01 | 2019-09-28
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK00504 | Atlantic Avenue - Purchase of WalkNYC Signs | 2 | PRELIMINARY DESIGN | 2015-09-29 | 2016-01-26 | 2019-09-29 | 2020-01-26
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK00504 | Atlantic Avenue - Purchase of WalkNYC Signs | 3 | FINAL DESIGN | 2016-01-27 | 2016-07-24 | 2020-01-27 | 2020-07-24
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK00504 | Atlantic Avenue - Purchase of WalkNYC Signs | 4 | BID AWARD AND REGISTER CONTRCT | 2016-07-25 | 2016-10-22 | 2020-07-25 | 2020-10-22
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK00504 | Atlantic Avenue - Purchase of WalkNYC Signs | 5 | CONSTRUCTION TO 25% | 2016-10-23 | 2017-02-19 | 2020-10-23 | 2021-02-19
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK00504 | Atlantic Avenue - Purchase of WalkNYC Signs | 6 | CONSTRUCTION TO 50% | 2017-02-20 | 2017-06-19 | 2021-02-20 | 2021-06-19
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK00504 | Atlantic Avenue - Purchase of WalkNYC Signs | 7 | CONSTRUCTION TO 75% | 2017-06-20 | 2017-10-17 | 2021-06-20 | 2021-10-17
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK00504 | Atlantic Avenue - Purchase of WalkNYC Signs | 8 | ORIGINAL EQUIP & FURNISHING | 2017-10-18 | 2018-01-15 | 2021-10-18 | 2022-01-15
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK00504 | Atlantic Avenue - Purchase of WalkNYC Signs | 9 | SUBSTANTIAL COMPLETION | 2018-01-16 | 2018-03-16 | 2022-01-16 | 2022-03-16
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK00504 | Atlantic Avenue - Purchase of WalkNYC Signs | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-03-17 | 2018-04-15 | 2022-03-17 | 2025-04-15
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK00512 | Little Red Riding Hood Pre-K Sidewalk Extension | 1 | DEVELOP SCOPE | 2016-06-30 | 2016-09-27 | 2019-06-30 | 2019-09-27
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK00512 | Little Red Riding Hood Pre-K Sidewalk Extension | 2 | PRELIMINARY DESIGN | 2016-09-28 | 2017-01-25 | 2019-09-28 | 2020-01-25
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK00512 | Little Red Riding Hood Pre-K Sidewalk Extension | 3 | FINAL DESIGN | 2017-01-26 | 2017-07-24 | 2020-01-26 | 2020-07-23
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK00512 | Little Red Riding Hood Pre-K Sidewalk Extension | 4 | BID AWARD AND REGISTER CONTRCT | 2017-07-25 | 2017-10-22 | 2020-07-24 | 2020-10-21
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK00512 | Little Red Riding Hood Pre-K Sidewalk Extension | 5 | CONSTRUCTION TO 25% | 2017-10-23 | 2018-02-19 | 2020-10-22 | 2021-02-18
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK00512 | Little Red Riding Hood Pre-K Sidewalk Extension | 6 | CONSTRUCTION TO 50% | 2018-02-20 | 2018-06-19 | 2021-02-19 | 2021-06-18
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK00512 | Little Red Riding Hood Pre-K Sidewalk Extension | 7 | CONSTRUCTION TO 75% | 2018-06-20 | 2018-10-17 | 2021-06-19 | 2021-10-16
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK00512 | Little Red Riding Hood Pre-K Sidewalk Extension | 8 | ORIGINAL EQUIP & FURNISHING | 2018-10-18 | 2019-01-15 | 2021-10-17 | 2022-01-14
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK00512 | Little Red Riding Hood Pre-K Sidewalk Extension | 9 | SUBSTANTIAL COMPLETION | 2019-01-16 | 2019-03-16 | 2022-01-15 | 2022-03-15
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK00512 | Little Red Riding Hood Pre-K Sidewalk Extension | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-03-17 | 2019-04-15 | 2022-03-16 | 2025-04-14
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK00514 | Brooklyn Greenway:Atlantic Avenue Connector | 1 | DEVELOP SCOPE | 2018-06-30 | 2018-09-27 | 2020-06-30 | 2020-09-27
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK00514 | Brooklyn Greenway:Atlantic Avenue Connector | 2 | PRELIMINARY DESIGN | 2018-09-28 | 2019-01-25 | 2020-09-28 | 2021-01-25
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK00514 | Brooklyn Greenway:Atlantic Avenue Connector | 3 | FINAL DESIGN | 2019-01-26 | 2019-07-24 | 2021-01-26 | 2021-07-24
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK00514 | Brooklyn Greenway:Atlantic Avenue Connector | 4 | BID AWARD AND REGISTER CONTRCT | 2019-07-25 | 2019-10-22 | 2021-07-25 | 2021-10-22
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK00514 | Brooklyn Greenway:Atlantic Avenue Connector | 5 | CONSTRUCTION TO 25% | 2019-10-23 | 2020-02-19 | 2021-10-23 | 2022-02-19
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK00514 | Brooklyn Greenway:Atlantic Avenue Connector | 6 | CONSTRUCTION TO 50% | 2020-02-20 | 2020-06-18 | 2022-02-20 | 2022-06-19
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK00514 | Brooklyn Greenway:Atlantic Avenue Connector | 7 | CONSTRUCTION TO 75% | 2020-06-19 | 2020-10-16 | 2022-06-20 | 2022-10-17
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK00514 | Brooklyn Greenway:Atlantic Avenue Connector | 8 | ORIGINAL EQUIP & FURNISHING | 2020-10-17 | 2021-01-14 | 2022-10-18 | 2023-01-15
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK00514 | Brooklyn Greenway:Atlantic Avenue Connector | 9 | SUBSTANTIAL COMPLETION | 2021-01-15 | 2021-03-15 | 2023-01-16 | 2023-03-16
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK00514 | Brooklyn Greenway:Atlantic Avenue Connector | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-16 | 2021-04-14 | 2023-03-17 | 2026-06-30
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK1669B | 4th Ave Safety Improvements - Phase B | 1 | DEVELOP SCOPE | 2021-06-30 | 2021-09-27 | 2017-04-24 | 2019-09-23
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK1669B | 4th Ave Safety Improvements - Phase B | 2 | PRELIMINARY DESIGN | 2021-09-28 | 2022-01-25 | 2020-02-25 | 2021-12-05
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK1669B | 4th Ave Safety Improvements - Phase B | 3 | FINAL DESIGN | 2022-01-26 | 2022-07-24 | 2021-09-22 | 2022-12-01
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK1669B | 4th Ave Safety Improvements - Phase B | 4 | BID AWARD AND REGISTER CONTRCT | 2022-07-25 | 2022-10-22 | 2022-12-22 | 2023-04-06
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK1669B | 4th Ave Safety Improvements - Phase B | 5 | CONSTRUCTION TO 25% | 2022-10-23 | 2023-02-19 | 2023-05-19 | 2024-01-01
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK1669B | 4th Ave Safety Improvements - Phase B | 6 | CONSTRUCTION TO 50% | 2023-02-20 | 2023-06-19 | 2024-01-01 | 2024-08-15
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK1669B | 4th Ave Safety Improvements - Phase B | 7 | CONSTRUCTION TO 75% | 2023-06-20 | 2023-10-17 | 2024-08-15 | 2025-03-30
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK1669B | 4th Ave Safety Improvements - Phase B | 8 | ORIGINAL EQUIP & FURNISHING | 2023-10-18 | 2024-01-15 | 2025-03-31 | 2025-06-28
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK1669B | 4th Ave Safety Improvements - Phase B | 9 | SUBSTANTIAL COMPLETION | 2024-01-16 | 2024-03-15 | 2025-03-30 | 2025-11-12
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK1669B | 4th Ave Safety Improvements - Phase B | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-03-16 | 2024-04-14 | 2025-11-12 | 2026-02-12
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK1673 | South Brooklyn Pedestrian and Bicycle Safety Improvements | 1 | DEVELOP SCOPE | 2020-06-30 | 2020-09-27 | 2027-06-30 | 2027-09-27
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK1673 | South Brooklyn Pedestrian and Bicycle Safety Improvements | 2 | PRELIMINARY DESIGN | 2020-09-28 | 2021-01-25 | 2027-09-28 | 2028-01-25
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK1673 | South Brooklyn Pedestrian and Bicycle Safety Improvements | 3 | FINAL DESIGN | 2021-01-26 | 2021-07-24 | 2028-01-26 | 2028-07-23
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK1673 | South Brooklyn Pedestrian and Bicycle Safety Improvements | 4 | BID AWARD AND REGISTER CONTRCT | 2021-07-25 | 2021-10-22 | 2028-07-24 | 2028-10-21
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK1673 | South Brooklyn Pedestrian and Bicycle Safety Improvements | 5 | CONSTRUCTION TO 25% | 2021-10-23 | 2022-02-19 | 2028-10-22 | 2029-02-18
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK1673 | South Brooklyn Pedestrian and Bicycle Safety Improvements | 6 | CONSTRUCTION TO 50% | 2022-02-20 | 2022-06-19 | 2029-02-19 | 2029-06-18
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK1673 | South Brooklyn Pedestrian and Bicycle Safety Improvements | 7 | CONSTRUCTION TO 75% | 2022-06-20 | 2022-10-17 | 2029-06-19 | 2029-10-16
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK1673 | South Brooklyn Pedestrian and Bicycle Safety Improvements | 8 | ORIGINAL EQUIP & FURNISHING | 2022-10-18 | 2023-01-15 | 2024-10-17 | 2025-01-14
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK1673 | South Brooklyn Pedestrian and Bicycle Safety Improvements | 9 | SUBSTANTIAL COMPLETION | 2023-01-16 | 2023-03-16 | 2025-01-15 | 2025-03-15
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK1673 | South Brooklyn Pedestrian and Bicycle Safety Improvements | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-03-17 | 2023-04-15 | 2025-03-16 | 2027-02-13
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK1674 | Flatbush Avenue Downtown Brooklyn Safety Improvements | 1 | DEVELOP SCOPE | 2020-06-30 | 2020-09-27 | 2020-05-07 | 2020-10-18
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK1674 | Flatbush Avenue Downtown Brooklyn Safety Improvements | 2 | PRELIMINARY DESIGN | 2020-09-28 | 2021-01-25 | 2020-10-19 | 2021-02-15
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK1674 | Flatbush Avenue Downtown Brooklyn Safety Improvements | 3 | FINAL DESIGN | 2021-01-26 | 2021-07-24 | 2021-02-16 | 2021-08-14
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK1674 | Flatbush Avenue Downtown Brooklyn Safety Improvements | 4 | BID AWARD AND REGISTER CONTRCT | 2021-07-25 | 2021-10-22 | 2021-08-15 | 2021-11-12
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK1674 | Flatbush Avenue Downtown Brooklyn Safety Improvements | 5 | CONSTRUCTION TO 25% | 2021-10-23 | 2022-02-19 | 2021-11-13 | 2022-03-12
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK1674 | Flatbush Avenue Downtown Brooklyn Safety Improvements | 6 | CONSTRUCTION TO 50% | 2022-02-20 | 2022-06-19 | 2022-03-13 | 2022-07-10
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK1674 | Flatbush Avenue Downtown Brooklyn Safety Improvements | 7 | CONSTRUCTION TO 75% | 2022-06-20 | 2022-10-17 | 2022-07-11 | 2025-11-07
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK1674 | Flatbush Avenue Downtown Brooklyn Safety Improvements | 8 | ORIGINAL EQUIP & FURNISHING | 2022-10-18 | 2023-01-15 | 2022-10-18 | 2023-01-15
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK1674 | Flatbush Avenue Downtown Brooklyn Safety Improvements | 9 | SUBSTANTIAL COMPLETION | 2023-01-16 | 2023-03-16 | 2022-02-05 | 2022-04-05
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK1674 | Flatbush Avenue Downtown Brooklyn Safety Improvements | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-03-17 | 2023-04-15 | 2022-04-06 | 2024-05-05
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKF029Z | FLATLANDS YARD AND STRUCTURES REHABILITATION | 1 | DEVELOP SCOPE | 2018-06-30 | 2018-09-27 | 2018-06-30 | 2018-09-27
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKF029Z | FLATLANDS YARD AND STRUCTURES REHABILITATION | 2 | PRELIMINARY DESIGN | 2018-09-28 | 2019-01-25 | 2018-09-28 | 2019-01-25
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKF029Z | FLATLANDS YARD AND STRUCTURES REHABILITATION | 3 | FINAL DESIGN | 2019-01-26 | 2019-07-24 | 2019-01-26 | 2019-07-24
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKF029Z | FLATLANDS YARD AND STRUCTURES REHABILITATION | 4 | BID AWARD AND REGISTER CONTRCT | 2019-07-25 | 2019-10-22 | 2019-07-25 | 2019-10-22
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKF029Z | FLATLANDS YARD AND STRUCTURES REHABILITATION | 5 | CONSTRUCTION TO 25% | 2019-10-23 | 2020-02-19 | 2019-10-23 | 2020-02-19
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKF029Z | FLATLANDS YARD AND STRUCTURES REHABILITATION | 6 | CONSTRUCTION TO 50% | 2020-02-20 | 2020-06-18 | 2020-02-20 | 2020-06-18
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKF029Z | FLATLANDS YARD AND STRUCTURES REHABILITATION | 7 | CONSTRUCTION TO 75% | 2020-06-19 | 2020-10-16 | 2020-06-19 | 2020-10-16
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKF029Z | FLATLANDS YARD AND STRUCTURES REHABILITATION | 8 | ORIGINAL EQUIP & FURNISHING | 2020-10-17 | 2021-01-14 | 2020-10-17 | 2021-01-14
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKF029Z | FLATLANDS YARD AND STRUCTURES REHABILITATION | 9 | SUBSTANTIAL COMPLETION | 2021-01-15 | 2021-03-15 | 2021-01-15 | 2021-03-15
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKF029Z | FLATLANDS YARD AND STRUCTURES REHABILITATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-16 | 2021-04-14 | 2021-03-16 | 2026-04-14
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKF2514 | 25 14th St Fleet Services Shop Rehabilitation | 1 | DEVELOP SCOPE | 2017-06-30 | 2017-09-27 | 2019-06-30 | 2019-09-27
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKF2514 | 25 14th St Fleet Services Shop Rehabilitation | 2 | PRELIMINARY DESIGN | 2017-09-28 | 2018-01-25 | 2019-09-28 | 2020-01-25
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKF2514 | 25 14th St Fleet Services Shop Rehabilitation | 3 | FINAL DESIGN | 2018-01-26 | 2018-07-24 | 2020-01-26 | 2020-07-23
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKF2514 | 25 14th St Fleet Services Shop Rehabilitation | 4 | BID AWARD AND REGISTER CONTRCT | 2018-07-25 | 2018-10-22 | 2020-07-24 | 2020-10-21
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKF2514 | 25 14th St Fleet Services Shop Rehabilitation | 5 | CONSTRUCTION TO 25% | 2018-10-23 | 2019-02-19 | 2020-10-22 | 2021-02-18
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKF2514 | 25 14th St Fleet Services Shop Rehabilitation | 6 | CONSTRUCTION TO 50% | 2019-02-20 | 2019-06-19 | 2021-02-19 | 2021-06-18
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKF2514 | 25 14th St Fleet Services Shop Rehabilitation | 7 | CONSTRUCTION TO 75% | 2019-06-20 | 2019-10-17 | 2021-06-19 | 2021-10-16
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKF2514 | 25 14th St Fleet Services Shop Rehabilitation | 8 | ORIGINAL EQUIP & FURNISHING | 2019-10-18 | 2020-01-15 | 2021-10-17 | 2022-01-14
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKF2514 | 25 14th St Fleet Services Shop Rehabilitation | 9 | SUBSTANTIAL COMPLETION | 2020-01-16 | 2020-03-15 | 2022-01-15 | 2022-03-15
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKF2514 | 25 14th St Fleet Services Shop Rehabilitation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-03-16 | 2020-04-14 | 2022-03-16 | 2022-04-14
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWP19KTA | Complex Pedestrian Ramps - Landmark Installation | 1 | DEVELOP SCOPE | 2020-06-30 | 2020-09-27 | 2021-06-30 | 2021-09-27
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWP19KTA | Complex Pedestrian Ramps - Landmark Installation | 2 | PRELIMINARY DESIGN | 2020-09-28 | 2021-01-25 | 2021-09-28 | 2022-01-25
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWP19KTA | Complex Pedestrian Ramps - Landmark Installation | 3 | FINAL DESIGN | 2021-01-26 | 2021-07-24 | 2022-01-26 | 2022-07-24
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWP19KTA | Complex Pedestrian Ramps - Landmark Installation | 4 | BID AWARD AND REGISTER CONTRCT | 2021-07-25 | 2021-10-22 | 2022-07-25 | 2022-10-22
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWP19KTA | Complex Pedestrian Ramps - Landmark Installation | 5 | CONSTRUCTION TO 25% | 2021-10-23 | 2022-02-19 | 2022-10-23 | 2023-02-19
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWP19KTA | Complex Pedestrian Ramps - Landmark Installation | 6 | CONSTRUCTION TO 50% | 2022-02-20 | 2022-06-19 | 2023-02-20 | 2023-06-19
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWP19KTA | Complex Pedestrian Ramps - Landmark Installation | 7 | CONSTRUCTION TO 75% | 2022-06-20 | 2022-10-17 | 2023-06-20 | 2023-10-17
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWP19KTA | Complex Pedestrian Ramps - Landmark Installation | 8 | ORIGINAL EQUIP & FURNISHING | 2022-10-18 | 2023-01-15 | 2023-10-18 | 2024-01-15
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWP19KTA | Complex Pedestrian Ramps - Landmark Installation | 9 | SUBSTANTIAL COMPLETION | 2023-01-16 | 2023-03-16 | 2024-01-16 | 2024-03-15
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWP19KTA | Complex Pedestrian Ramps - Landmark Installation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-03-17 | 2023-04-15 | 2024-03-16 | 2024-04-14
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWS2021K1 | PRIOR NOTICE SIDEWALK - BROOKLYN | 1 | DEVELOP SCOPE | 2020-02-04 | 2020-03-24 | 2020-02-04 | 2020-03-24
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWS2021K1 | PRIOR NOTICE SIDEWALK - BROOKLYN | 2 | DESIGN START | 2020-03-25 | 2020-08-28 | 2020-03-25 | 2020-08-28
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWS2021K1 | PRIOR NOTICE SIDEWALK - BROOKLYN | 3 | CONSTRUCTION START | 2021-01-19 | 2021-10-18 | 2021-01-19 | 2021-10-18
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWS2021K2 | PRIOR NOTICE SIDEWALK - BROOKLYN | 1 | DEVELOP SCOPE | 2020-02-04 | 2020-03-24 | 2020-02-04 | 2020-03-24
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWS2021K2 | PRIOR NOTICE SIDEWALK - BROOKLYN | 2 | DESIGN START | 2020-03-25 | 2020-06-30 | 2020-03-25 | 2020-06-30
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWS2021K2 | PRIOR NOTICE SIDEWALK - BROOKLYN | 3 | CONSTRUCTION START | 2020-07-01 | 2021-06-20 | 2020-07-01 | 2021-06-20
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | SANDBULK1 | Reconstruction of Bay & Corbin Bulkheads - Hurricane Sandy | 1 | DEVELOP SCOPE | 2017-06-01 | 2017-08-29 | 2021-06-01 | 2021-08-29
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | SANDBULK1 | Reconstruction of Bay & Corbin Bulkheads - Hurricane Sandy | 2 | PRELIMINARY DESIGN | 2017-08-30 | 2017-12-27 | 2021-08-30 | 2021-12-27
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | SANDBULK1 | Reconstruction of Bay & Corbin Bulkheads - Hurricane Sandy | 3 | FINAL DESIGN | 2017-12-28 | 2018-06-25 | 2021-12-28 | 2022-06-25
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | SANDBULK1 | Reconstruction of Bay & Corbin Bulkheads - Hurricane Sandy | 4 | BID AWARD AND REGISTER CONTRCT | 2018-06-26 | 2018-09-23 | 2022-06-26 | 2022-09-23
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | SANDBULK1 | Reconstruction of Bay & Corbin Bulkheads - Hurricane Sandy | 5 | CONSTRUCTION TO 25% | 2018-09-24 | 2019-01-21 | 2022-09-24 | 2023-01-21
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | SANDBULK1 | Reconstruction of Bay & Corbin Bulkheads - Hurricane Sandy | 6 | CONSTRUCTION TO 50% | 2019-01-22 | 2019-05-21 | 2023-01-22 | 2023-05-21
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | SANDBULK1 | Reconstruction of Bay & Corbin Bulkheads - Hurricane Sandy | 7 | CONSTRUCTION TO 75% | 2019-05-22 | 2019-09-18 | 2023-05-22 | 2023-09-18
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | SANDBULK1 | Reconstruction of Bay & Corbin Bulkheads - Hurricane Sandy | 8 | ORIGINAL EQUIP & FURNISHING | 2019-09-19 | 2019-12-17 | 2023-09-19 | 2023-12-17
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | SANDBULK1 | Reconstruction of Bay & Corbin Bulkheads - Hurricane Sandy | 9 | SUBSTANTIAL COMPLETION | 2019-12-18 | 2020-02-15 | 2023-12-18 | 2024-02-15
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | SANDBULK1 | Reconstruction of Bay & Corbin Bulkheads - Hurricane Sandy | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-02-16 | 2020-03-16 | 2024-02-16 | 2024-03-16
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TF18-2017 | AVENUE M MUNICIPAL PARKING FIELD | 1 | BID AWARD AND REGISTER CONTRCT | 2014-06-01 | 2014-06-01 | 2020-06-01 | 2020-06-01
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TF18-2017 | AVENUE M MUNICIPAL PARKING FIELD | 2 | CONSTRUCTION START | 2014-06-02 | 2014-07-16 | 2020-06-02 | 2020-07-16
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TF18-2017 | AVENUE M MUNICIPAL PARKING FIELD | 3 | CONSTRUCTION COMPLETION | 2014-07-17 | 2016-02-06 | 2020-07-17 | 2029-06-30
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TF50311 | Rpl St lg pl Bedford Ave fm Campus Rd to Foster Ave-XMA165.3 | 1 | DEVELOP SCOPE | 2017-06-30 | 2017-09-27 | 2018-06-30 | 2018-09-27
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TF50311 | Rpl St lg pl Bedford Ave fm Campus Rd to Foster Ave-XMA165.3 | 2 | PRELIMINARY DESIGN | 2017-09-28 | 2018-01-25 | 2018-09-28 | 2019-01-25
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TF50311 | Rpl St lg pl Bedford Ave fm Campus Rd to Foster Ave-XMA165.3 | 3 | FINAL DESIGN | 2018-01-26 | 2018-07-24 | 2019-01-26 | 2019-07-24
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TF50311 | Rpl St lg pl Bedford Ave fm Campus Rd to Foster Ave-XMA165.3 | 4 | BID AWARD AND REGISTER CONTRCT | 2018-07-25 | 2018-10-22 | 2019-07-25 | 2019-10-22
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TF50311 | Rpl St lg pl Bedford Ave fm Campus Rd to Foster Ave-XMA165.3 | 5 | CONSTRUCTION TO 25% | 2018-10-23 | 2019-02-19 | 2019-10-23 | 2020-02-19
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TF50311 | Rpl St lg pl Bedford Ave fm Campus Rd to Foster Ave-XMA165.3 | 6 | CONSTRUCTION TO 50% | 2019-02-20 | 2019-06-19 | 2020-02-20 | 2020-06-18
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TF50311 | Rpl St lg pl Bedford Ave fm Campus Rd to Foster Ave-XMA165.3 | 7 | CONSTRUCTION TO 75% | 2019-06-20 | 2019-10-17 | 2020-06-19 | 2020-10-16
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TF50311 | Rpl St lg pl Bedford Ave fm Campus Rd to Foster Ave-XMA165.3 | 8 | ORIGINAL EQUIP & FURNISHING | 2019-10-18 | 2020-01-15 | 2020-10-17 | 2021-01-14
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TF50311 | Rpl St lg pl Bedford Ave fm Campus Rd to Foster Ave-XMA165.3 | 9 | SUBSTANTIAL COMPLETION | 2020-01-16 | 2020-03-15 | 2021-01-15 | 2021-03-15
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TF50311 | Rpl St lg pl Bedford Ave fm Campus Rd to Foster Ave-XMA165.3 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-03-16 | 2020-04-14 | 2021-03-16 | 2021-07-13
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TF50313 | Instl lg on Cortelyou Rd&Newkirk XMA193.30 & A835 | 1 | BID AWARD AND REGISTER CONTRCT | 2019-06-30 | 2019-06-30 | 2020-06-30 | 2020-06-30
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TF50313 | Instl lg on Cortelyou Rd&Newkirk XMA193.30 & A835 | 2 | CONSTRUCTION START | 2019-07-01 | 2019-08-14 | 2020-07-01 | 2020-08-14
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TF50313 | Instl lg on Cortelyou Rd&Newkirk XMA193.30 & A835 | 3 | CONSTRUCTION COMPLETION | 2019-08-15 | 2021-03-06 | 2020-08-15 | 2022-03-07
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TF50315 | Historic St lg poles on Mermaid Avenue bet W21St &W29th St, | 1 | BID AWARD AND REGISTER CONTRCT | 2018-06-30 | 2018-06-30 | 2018-06-30 | 2018-06-30
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TF50315 | Historic St lg poles on Mermaid Avenue bet W21St &W29th St, | 2 | CONSTRUCTION START | 2018-07-01 | 2018-08-14 | 2018-07-01 | 2018-08-14
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TF50315 | Historic St lg poles on Mermaid Avenue bet W21St &W29th St, | 3 | CONSTRUCTION COMPLETION | 2018-08-15 | 2020-03-06 | 2018-08-15 | 2024-06-30
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TF50317 | Upgrade of poles & lg on McDonald Ave, bet Ave R&KingH | 1 | BID AWARD AND REGISTER CONTRCT | 2019-06-30 | 2019-06-30 | 2019-06-30 | 2019-06-30
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TF50317 | Upgrade of poles & lg on McDonald Ave, bet Ave R&KingH | 2 | CONSTRUCTION START | 2019-07-01 | 2019-08-14 | 2019-07-01 | 2019-08-14
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TF50317 | Upgrade of poles & lg on McDonald Ave, bet Ave R&KingH | 3 | CONSTRUCTION COMPLETION | 2019-08-15 | 2021-03-06 | 2019-08-15 | 2021-03-06
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503K23 | BROOKLYN HEIGHTS HISTORIC LIGHTING | 1 | BID AWARD AND REGISTER CONTRCT | 2011-06-30 | 2011-06-30 | 2019-06-30 | 2019-06-30
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503K23 | BROOKLYN HEIGHTS HISTORIC LIGHTING | 2 | CONSTRUCTION START | 2011-07-01 | 2011-08-14 | 2019-07-01 | 2019-08-14
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503K23 | BROOKLYN HEIGHTS HISTORIC LIGHTING | 3 | CONSTRUCTION COMPLETION | 2011-08-15 | 2013-03-06 | 2019-08-15 | 2025-03-06
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503K26 | FLATBUSH AVE. ST. PURCHASE AND INSTALLATION OF LAMP POST | 1 | BID AWARD AND REGISTER CONTRCT | 2011-06-30 | 2011-06-30 | 2018-06-30 | 2018-06-30
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503K26 | FLATBUSH AVE. ST. PURCHASE AND INSTALLATION OF LAMP POST | 2 | CONSTRUCTION START | 2011-07-01 | 2011-08-14 | 2018-07-01 | 2018-08-14
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503K26 | FLATBUSH AVE. ST. PURCHASE AND INSTALLATION OF LAMP POST | 3 | CONSTRUCTION COMPLETION | 2011-08-15 | 2013-03-06 | 2018-08-15 | 2024-03-06
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503KCD | COUNTDOWN CLOCKS INSTALLATION IN BENSONHURST, BKLYN | 3 | CONSTRUCTION COMPLETION | 2014-07-17 | 2016-02-06 | 2014-07-17 | 2016-02-06
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TFK50313 | Historic Lighting on Broadway btw Roebling and Bedford | 1 | BID AWARD AND REGISTER CONTRCT | 2013-06-30 | 2013-06-30 | 2019-06-30 | 2019-06-30
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TFK50313 | Historic Lighting on Broadway btw Roebling and Bedford | 2 | CONSTRUCTION START | 2013-07-01 | 2013-08-14 | 2019-07-01 | 2019-08-14
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TFK50313 | Historic Lighting on Broadway btw Roebling and Bedford | 3 | CONSTRUCTION COMPLETION | 2013-08-15 | 2015-03-07 | 2019-08-15 | 2024-03-06
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TFKVANDMD | VANDERBILT AVE MERCHANTS DISTRICT/PHNDC: ELEGANT STREET LIG | 1 | BID AWARD AND REGISTER CONTRCT | 2017-06-30 | 2017-06-30 | 2018-06-30 | 2018-06-30
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TFKVANDMD | VANDERBILT AVE MERCHANTS DISTRICT/PHNDC: ELEGANT STREET LIG | 2 | CONSTRUCTION START | 2017-07-01 | 2017-08-14 | 2018-07-01 | 2018-08-14
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TFKVANDMD | VANDERBILT AVE MERCHANTS DISTRICT/PHNDC: ELEGANT STREET LIG | 3 | CONSTRUCTION COMPLETION | 2017-08-15 | 2019-03-07 | 2018-08-15 | 2024-03-06
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TFLGAVEU | St Lg on Ave U from Ocean Pkwy to McDonald Ave XMA206.30A | 1 | BID AWARD AND REGISTER CONTRCT | 2017-06-30 | 2017-06-30 | 2022-06-30 | 2022-06-30
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TFLGAVEU | St Lg on Ave U from Ocean Pkwy to McDonald Ave XMA206.30A | 2 | CONSTRUCTION START | 2017-07-01 | 2017-08-14 | 2022-07-01 | 2022-08-14
20201123 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TFLGAVEU | St Lg on Ave U from Ocean Pkwy to McDonald Ave XMA206.30A | 3 | CONSTRUCTION COMPLETION | 2017-08-15 | 2019-03-07 | 2022-08-15 | 2024-03-06
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | ACEDPR702 | DPR - RTU (Roof Top Unit) UPGRADES | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | ACEDPR702 | DPR - RTU (Roof Top Unit) UPGRADES | 2 | DESIGN | 2017-12-28 | 2019-06-25 | 2017-12-28 | 2019-06-25
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | ACEDPR702 | DPR - RTU (Roof Top Unit) UPGRADES | 3 | BID/ REGISTER CONTRACT | 2019-06-26 | 2020-03-21 | 2019-06-26 | 2020-03-21
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | ACEDPR702 | DPR - RTU (Roof Top Unit) UPGRADES | 4 | CONSTRUCTION | 2020-03-22 | 2021-09-17 | 2020-03-22 | 2021-09-17
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | ACEDPR702 | DPR - RTU (Roof Top Unit) UPGRADES | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-18 | 2022-09-17 | 2021-09-18 | 2022-09-17
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | BKPARK | BROOKLYN BRIDGE PARK - PHASE I BG-38150-101M | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | BKPARK | BROOKLYN BRIDGE PARK - PHASE I BG-38150-101M | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | BKPARK | BROOKLYN BRIDGE PARK - PHASE I BG-38150-101M | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | BKPARK | BROOKLYN BRIDGE PARK - PHASE I BG-38150-101M | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | BKPARK | BROOKLYN BRIDGE PARK - PHASE I BG-38150-101M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | GKBKGI-01 | GI - DSGN & CONS OF PARKLAND RETROFITS IN BROOKLYN | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | GKBKGI-01 | GI - DSGN & CONS OF PARKLAND RETROFITS IN BROOKLYN | 2 | DESIGN | 2018-12-28 | 2020-06-19 | 2018-12-28 | 2020-06-19
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | GKBKGI-01 | GI - DSGN & CONS OF PARKLAND RETROFITS IN BROOKLYN | 3 | BID/ REGISTER CONTRACT | 2020-06-20 | 2021-03-16 | 2020-06-20 | 2021-03-16
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | GKBKGI-01 | GI - DSGN & CONS OF PARKLAND RETROFITS IN BROOKLYN | 4 | CONSTRUCTION | 2021-03-17 | 2024-03-15 | 2021-03-17 | 2024-03-15
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | GKBKGI-01 | GI - DSGN & CONS OF PARKLAND RETROFITS IN BROOKLYN | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-03-16 | 2026-03-15 | 2024-03-16 | 2026-03-15
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | GKBKGI-02 | GI - CONS OF BROOKLYN PARKLAND RETROFITS FY20RP | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2020-09-07
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-CLNE | NDF- East New York - City Line Park | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-CLNE | NDF- East New York - City Line Park | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2016-12-28 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-CLNE | NDF- East New York - City Line Park | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2017-12-28 | 2018-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-CLNE | NDF- East New York - City Line Park | 4 | CONSTRUCTION | 2018-09-24 | 2019-09-23 | 2018-09-24 | 2019-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-CLNE | NDF- East New York - City Line Park | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-CLNKY | NDF - Callahan-Kelly Park (B219-117M) | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-CLNKY | NDF - Callahan-Kelly Park (B219-117M) | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2016-12-28 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-CLNKY | NDF - Callahan-Kelly Park (B219-117M) | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2017-12-28 | 2018-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-CLNKY | NDF - Callahan-Kelly Park (B219-117M) | 4 | CONSTRUCTION | 2018-09-24 | 2019-09-23 | 2018-09-24 | 2019-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-CLNKY | NDF - Callahan-Kelly Park (B219-117M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-HLDN3 | NDF - Highland Park Eastern Playground R/C Q020-119M | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-HLDN3 | NDF - Highland Park Eastern Playground R/C Q020-119M | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-HLDN3 | NDF - Highland Park Eastern Playground R/C Q020-119M | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-HLDN3 | NDF - Highland Park Eastern Playground R/C Q020-119M | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-HLDN3 | NDF - Highland Park Eastern Playground R/C Q020-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-HLDN4 | NDF - Highland Park Comfort Station R/C Q020-219M | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-HLDN4 | NDF - Highland Park Comfort Station R/C Q020-219M | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-HLDN4 | NDF - Highland Park Comfort Station R/C Q020-219M | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-HLDN4 | NDF - Highland Park Comfort Station R/C Q020-219M | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-HLDN4 | NDF - Highland Park Comfort Station R/C Q020-219M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-HLDN5 | NDF - Highland Park Pedestrian Improvements Q020-118M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-HLDN5 | NDF - Highland Park Pedestrian Improvements Q020-118M | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-HLDN5 | NDF - Highland Park Pedestrian Improvements Q020-118M | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-HLDN5 | NDF - Highland Park Pedestrian Improvements Q020-118M | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-HLDN5 | NDF - Highland Park Pedestrian Improvements Q020-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-HLND | Neighborhood Dev. Fund - East NY - Highland Park Q020-216M | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-HLND | Neighborhood Dev. Fund - East NY - Highland Park Q020-216M | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2016-12-28 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-HLND | Neighborhood Dev. Fund - East NY - Highland Park Q020-216M | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2017-12-28 | 2018-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-HLND | Neighborhood Dev. Fund - East NY - Highland Park Q020-216M | 4 | CONSTRUCTION | 2018-09-24 | 2019-09-23 | 2018-09-24 | 2019-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-HLND | Neighborhood Dev. Fund - East NY - Highland Park Q020-216M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200884L | Prospect Park Zoo - Amur Leopard exhibit | 1 | DEVELOP SCOPE | 2006-07-01 | 2006-09-28 | 2006-07-01 | 2006-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200884L | Prospect Park Zoo - Amur Leopard exhibit | 2 | DESIGN | 2006-09-29 | 2006-12-27 | 2006-09-29 | 2006-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200884L | Prospect Park Zoo - Amur Leopard exhibit | 3 | BID/ REGISTER CONTRACT | 2006-12-28 | 2007-03-27 | 2006-12-28 | 2007-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200884L | Prospect Park Zoo - Amur Leopard exhibit | 4 | CONSTRUCTION | 2007-03-28 | 2008-03-26 | 2007-03-28 | 2008-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200884L | Prospect Park Zoo - Amur Leopard exhibit | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-27 | 2009-03-26 | 2008-03-27 | 2020-11-30
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200C64K | PROSPECT PARK LITCHFIELD VILLA RCNSTR&STBLZ; B073-700M | 4 | CONSTRUCTION | 2007-03-28 | 2008-03-26 | 2007-03-28 | 2008-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200C64K | PROSPECT PARK LITCHFIELD VILLA RCNSTR&STBLZ; B073-700M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-27 | 2009-03-26 | 2008-03-27 | 2009-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200CRSL | PPA- Recon. Carousel (B073-218M) | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200CRSL | PPA- Recon. Carousel (B073-218M) | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2016-12-28 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200CRSL | PPA- Recon. Carousel (B073-218M) | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2017-12-28 | 2018-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200CRSL | PPA- Recon. Carousel (B073-218M) | 4 | CONSTRUCTION | 2018-09-24 | 2020-03-21 | 2018-09-24 | 2020-03-21
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200CRSL | PPA- Recon. Carousel (B073-218M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-03-22 | 2021-03-21 | 2020-03-22 | 2021-03-21
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200FITS | PPA- Prospect Park Fitness Playground/Equipment (B068-119M) | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200FITS | PPA- Prospect Park Fitness Playground/Equipment (B068-119M) | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200FITS | PPA- Prospect Park Fitness Playground/Equipment (B068-119M) | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200FITS | PPA- Prospect Park Fitness Playground/Equipment (B068-119M) | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200FITS | PPA- Prospect Park Fitness Playground/Equipment (B068-119M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200HPPP | PPA - Harmony Playground Improvements B073-119M | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200HPPP | PPA - Harmony Playground Improvements B073-119M | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200HPPP | PPA - Harmony Playground Improvements B073-119M | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200HPPP | PPA - Harmony Playground Improvements B073-119M | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200HPPP | PPA - Harmony Playground Improvements B073-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200K01Q | PROSP PK BANDSHELL & LNDSCPE B073-598/898 & EQMPT OMBP 305M | 4 | CONSTRUCTION | 2007-03-28 | 2008-03-26 | 2007-03-28 | 2008-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200K01Q | PROSP PK BANDSHELL & LNDSCPE B073-598/898 & EQMPT OMBP 305M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-27 | 2009-03-26 | 2008-03-27 | 2009-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200LFHH | PPA- Restor. Lefferts Historic House | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200LFHH | PPA- Restor. Lefferts Historic House | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2016-12-28 | 2018-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200LFHH | PPA- Restor. Lefferts Historic House | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2018-12-28 | 2019-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200LFHH | PPA- Restor. Lefferts Historic House | 4 | CONSTRUCTION | 2018-09-24 | 2020-03-21 | 2019-09-24 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200LFHH | PPA- Restor. Lefferts Historic House | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-03-22 | 2021-03-21 | 2021-09-23 | 2022-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200LMBF | PPA Long Meadow Ballfields restoration 34 acre ballfield | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200LMBF | PPA Long Meadow Ballfields restoration 34 acre ballfield | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200LMBF | PPA Long Meadow Ballfields restoration 34 acre ballfield | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200LMBF | PPA Long Meadow Ballfields restoration 34 acre ballfield | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200LMBF | PPA Long Meadow Ballfields restoration 34 acre ballfield | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200LONG | PPA - LONG MEADOW BALLFIELDS RENOV, B073-214M | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2013-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200LONG | PPA - LONG MEADOW BALLFIELDS RENOV, B073-214M | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2013-09-29 | 2013-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200LONG | PPA - LONG MEADOW BALLFIELDS RENOV, B073-214M | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2013-12-28 | 2014-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200LONG | PPA - LONG MEADOW BALLFIELDS RENOV, B073-214M | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2014-03-28 | 2015-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200LONG | PPA - LONG MEADOW BALLFIELDS RENOV, B073-214M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2021-03-18
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPBF | PROSP. PK. BASEBALL FIELDS-LONG MEADOWS (B073-211M) | 1 | DEVELOP SCOPE | 2010-07-01 | 2010-09-28 | 2010-07-01 | 2010-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPBF | PROSP. PK. BASEBALL FIELDS-LONG MEADOWS (B073-211M) | 2 | DESIGN | 2010-09-29 | 2010-12-27 | 2010-09-29 | 2010-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPBF | PROSP. PK. BASEBALL FIELDS-LONG MEADOWS (B073-211M) | 3 | BID/ REGISTER CONTRACT | 2010-12-28 | 2011-03-27 | 2010-12-28 | 2011-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPBF | PROSP. PK. BASEBALL FIELDS-LONG MEADOWS (B073-211M) | 4 | CONSTRUCTION | 2011-03-28 | 2012-03-26 | 2011-03-28 | 2012-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPBF | PROSP. PK. BASEBALL FIELDS-LONG MEADOWS (B073-211M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-03-27 | 2013-03-26 | 2012-03-27 | 2024-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPBL | PPA- Long Meadow Ballfields 4-5 (B073-215M) | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPBL | PPA- Long Meadow Ballfields 4-5 (B073-215M) | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2016-12-28 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPBL | PPA- Long Meadow Ballfields 4-5 (B073-215M) | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2017-12-28 | 2018-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPBL | PPA- Long Meadow Ballfields 4-5 (B073-215M) | 4 | CONSTRUCTION | 2018-09-24 | 2019-09-23 | 2018-09-24 | 2019-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPBL | PPA- Long Meadow Ballfields 4-5 (B073-215M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPCS | Prospect Park: Reconstruction of Comfort Station | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPCS | Prospect Park: Reconstruction of Comfort Station | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPCS | Prospect Park: Reconstruction of Comfort Station | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPCS | Prospect Park: Reconstruction of Comfort Station | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPCS | Prospect Park: Reconstruction of Comfort Station | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPFB | PPA - Flatbush Avenue Park Perimeter B073-315M | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2015-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPFB | PPA - Flatbush Avenue Park Perimeter B073-315M | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2015-09-29 | 2015-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPFB | PPA - Flatbush Avenue Park Perimeter B073-315M | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2015-12-28 | 2016-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPFB | PPA - Flatbush Avenue Park Perimeter B073-315M | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPFB | PPA - Flatbush Avenue Park Perimeter B073-315M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2017-03-27 | 2022-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPMB | PPA-Building Reconstruction (B073-319M) | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPMB | PPA-Building Reconstruction (B073-319M) | 2 | DESIGN | 2017-12-28 | 2019-06-20 | 2017-12-28 | 2019-06-20
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPMB | PPA-Building Reconstruction (B073-319M) | 3 | BID/ REGISTER CONTRACT | 2019-06-21 | 2020-03-16 | 2019-06-21 | 2020-03-16
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPMB | PPA-Building Reconstruction (B073-319M) | 4 | CONSTRUCTION | 2020-03-17 | 2021-09-07 | 2020-03-17 | 2021-09-07
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPMB | PPA-Building Reconstruction (B073-319M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-08 | 2022-09-07 | 2021-09-08 | 2022-09-07
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPMO | PPA- New M&O Facility & Compound in Prospect Park B073-415M | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2015-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPMO | PPA- New M&O Facility & Compound in Prospect Park B073-415M | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2015-09-29 | 2015-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPMO | PPA- New M&O Facility & Compound in Prospect Park B073-415M | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2015-12-28 | 2016-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPMO | PPA- New M&O Facility & Compound in Prospect Park B073-415M | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPMO | PPA- New M&O Facility & Compound in Prospect Park B073-415M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2017-03-27 | 2022-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPNM | Prospect Park Nethermead - Repave Walking Path | 1 | DEVELOP SCOPE | 2020-07-01 | 2020-12-27 | 2020-07-01 | 2020-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPNM | Prospect Park Nethermead - Repave Walking Path | 2 | DESIGN | 2020-12-28 | 2021-12-27 | 2020-12-28 | 2021-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPNM | Prospect Park Nethermead - Repave Walking Path | 3 | BID/ REGISTER CONTRACT | 2021-12-28 | 2022-09-23 | 2021-12-28 | 2022-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPNM | Prospect Park Nethermead - Repave Walking Path | 4 | CONSTRUCTION | 2022-09-24 | 2023-09-23 | 2022-09-24 | 2023-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPNM | Prospect Park Nethermead - Repave Walking Path | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-24 | 2024-09-22 | 2023-09-24 | 2024-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPOC | PROSPECT PARK ALLIANCE: RESTORATION TO OCEAN AVE PERIMETER | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPOC | PROSPECT PARK ALLIANCE: RESTORATION TO OCEAN AVE PERIMETER | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2016-12-28 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPOC | PROSPECT PARK ALLIANCE: RESTORATION TO OCEAN AVE PERIMETER | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2017-12-28 | 2018-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPOC | PROSPECT PARK ALLIANCE: RESTORATION TO OCEAN AVE PERIMETER | 4 | CONSTRUCTION | 2018-09-24 | 2019-09-23 | 2018-09-24 | 2019-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPOC | PROSPECT PARK ALLIANCE: RESTORATION TO OCEAN AVE PERIMETER | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPOP | PPA - Prospect Park Oriental Pavilion B073-416M | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2015-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPOP | PPA - Prospect Park Oriental Pavilion B073-416M | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2015-09-29 | 2015-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPOP | PPA - Prospect Park Oriental Pavilion B073-416M | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2015-12-28 | 2016-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPOP | PPA - Prospect Park Oriental Pavilion B073-416M | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPOP | PPA - Prospect Park Oriental Pavilion B073-416M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2017-03-27 | 2022-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPPH | PPA- PROSPECT PARK PICNIC HOUSE RENOVATION B073-419M | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2013-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPPH | PPA- PROSPECT PARK PICNIC HOUSE RENOVATION B073-419M | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2013-09-29 | 2013-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPPH | PPA- PROSPECT PARK PICNIC HOUSE RENOVATION B073-419M | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2013-12-28 | 2014-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPPH | PPA- PROSPECT PARK PICNIC HOUSE RENOVATION B073-419M | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2014-03-28 | 2015-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPPH | PPA- PROSPECT PARK PICNIC HOUSE RENOVATION B073-419M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2021-04-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPXR | PPA- Creation of a Par Course (Parade Grounds) B068-115M | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPXR | PPA- Creation of a Par Course (Parade Grounds) B068-115M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2017-03-27 | 2018-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PRUN | PPA- Multiside, Drinking Fountain, BBQ Pits, Running Land | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PRUN | PPA- Multiside, Drinking Fountain, BBQ Pits, Running Land | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2016-12-28 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PRUN | PPA- Multiside, Drinking Fountain, BBQ Pits, Running Land | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2017-12-28 | 2018-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PRUN | PPA- Multiside, Drinking Fountain, BBQ Pits, Running Land | 4 | CONSTRUCTION | 2018-09-24 | 2020-03-21 | 2018-09-24 | 2019-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PRUN | PPA- Multiside, Drinking Fountain, BBQ Pits, Running Land | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-03-22 | 2021-03-21 | 2019-09-24 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200STFP | PPA - Parade Ground replace turf field 9 (B068-118M) | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200STFP | PPA - Parade Ground replace turf field 9 (B068-118M) | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200STFP | PPA - Parade Ground replace turf field 9 (B068-118M) | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200STFP | PPA - Parade Ground replace turf field 9 (B068-118M) | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200STFP | PPA - Parade Ground replace turf field 9 (B068-118M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200TNCR | PPA- Prospect Park Tennis Center | 1 | DEVELOP SCOPE | 2020-07-01 | 2020-12-27 | 2020-07-01 | 2020-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200TNCR | PPA- Prospect Park Tennis Center | 2 | DESIGN | 2020-12-28 | 2021-12-27 | 2020-12-28 | 2021-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200TNCR | PPA- Prospect Park Tennis Center | 3 | BID/ REGISTER CONTRACT | 2021-12-28 | 2022-09-23 | 2021-12-28 | 2022-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200TNCR | PPA- Prospect Park Tennis Center | 4 | CONSTRUCTION | 2022-09-24 | 2023-09-23 | 2022-09-24 | 2023-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200TNCR | PPA- Prospect Park Tennis Center | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-24 | 2024-09-22 | 2023-09-24 | 2024-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200WCST | PPA-WELLHOUSE COMFORT STATION RENOVATION - (B073-209M) | 1 | DEVELOP SCOPE | 2008-07-01 | 2008-09-28 | 2008-07-01 | 2008-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200WCST | PPA-WELLHOUSE COMFORT STATION RENOVATION - (B073-209M) | 2 | DESIGN | 2008-09-29 | 2008-12-27 | 2008-09-29 | 2008-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200WCST | PPA-WELLHOUSE COMFORT STATION RENOVATION - (B073-209M) | 3 | BID/ REGISTER CONTRACT | 2008-12-28 | 2009-03-27 | 2008-12-28 | 2009-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200WCST | PPA-WELLHOUSE COMFORT STATION RENOVATION - (B073-209M) | 4 | CONSTRUCTION | 2009-03-28 | 2010-03-27 | 2009-03-28 | 2010-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200WCST | PPA-WELLHOUSE COMFORT STATION RENOVATION - (B073-209M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2010-03-28 | 2011-03-27 | 2010-03-28 | 2022-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200ZO10 | Prospect Park Zoo - Renovation of Discovery Trail | 1 | DEVELOP SCOPE | 2009-07-01 | 2010-09-28 | 2009-07-01 | 2010-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200ZO10 | Prospect Park Zoo - Renovation of Discovery Trail | 2 | DESIGN | 2010-09-29 | 2010-09-28 | 2010-09-29 | 2010-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200ZO10 | Prospect Park Zoo - Renovation of Discovery Trail | 3 | BID/ REGISTER CONTRACT | 2010-09-29 | 2010-09-28 | 2010-09-29 | 2010-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200ZO10 | Prospect Park Zoo - Renovation of Discovery Trail | 4 | CONSTRUCTION | 2010-09-29 | 2010-09-28 | 2010-09-29 | 2010-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200ZO10 | Prospect Park Zoo - Renovation of Discovery Trail | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2010-09-29 | 2011-09-28 | 2010-09-29 | 2020-11-29
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200ZO17 | PPZ- Building "D" Dome Restoration | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200ZO17 | PPZ- Building "D" Dome Restoration | 2 | DESIGN | 2017-12-28 | 2019-03-27 | 2017-12-28 | 2019-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200ZO17 | PPZ- Building "D" Dome Restoration | 3 | BID/ REGISTER CONTRACT | 2019-03-28 | 2019-12-22 | 2019-03-28 | 2019-12-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200ZO17 | PPZ- Building "D" Dome Restoration | 4 | CONSTRUCTION | 2019-12-23 | 2020-12-21 | 2019-12-23 | 2020-12-21
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200ZO17 | PPZ- Building "D" Dome Restoration | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-12-22 | 2021-12-21 | 2020-12-22 | 2021-12-21
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200ZO18 | PPZ- Off exhibit primate holding expansion | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200ZO18 | PPZ- Off exhibit primate holding expansion | 2 | DESIGN | 2017-12-28 | 2019-03-27 | 2017-12-28 | 2019-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200ZO18 | PPZ- Off exhibit primate holding expansion | 3 | BID/ REGISTER CONTRACT | 2019-03-28 | 2019-12-22 | 2019-03-28 | 2019-12-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200ZO18 | PPZ- Off exhibit primate holding expansion | 4 | CONSTRUCTION | 2019-12-23 | 2020-12-21 | 2019-12-23 | 2020-12-21
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200ZO18 | PPZ- Off exhibit primate holding expansion | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-12-22 | 2021-12-21 | 2020-12-22 | 2021-12-21
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200ZO19 | PPZ- Central plaza stairs,benches reconstruction | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200ZO19 | PPZ- Central plaza stairs,benches reconstruction | 2 | DESIGN | 2017-12-28 | 2019-03-27 | 2017-12-28 | 2019-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200ZO19 | PPZ- Central plaza stairs,benches reconstruction | 3 | BID/ REGISTER CONTRACT | 2019-03-28 | 2019-12-22 | 2019-03-28 | 2019-12-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200ZO19 | PPZ- Central plaza stairs,benches reconstruction | 4 | CONSTRUCTION | 2019-12-23 | 2020-12-21 | 2019-12-23 | 2020-12-21
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200ZO19 | PPZ- Central plaza stairs,benches reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-12-22 | 2021-12-21 | 2020-12-22 | 2021-12-21
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201245E | WNYC TRANSMITTER TOWERS EMERGENCY DEMOLITION, B385-102M | 1 | DEVELOP SCOPE | 2006-07-01 | 2006-09-28 | 2006-07-01 | 2006-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201245E | WNYC TRANSMITTER TOWERS EMERGENCY DEMOLITION, B385-102M | 2 | DESIGN | 2006-09-29 | 2006-12-27 | 2006-09-29 | 2006-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201245E | WNYC TRANSMITTER TOWERS EMERGENCY DEMOLITION, B385-102M | 3 | BID/ REGISTER CONTRACT | 2006-12-28 | 2007-03-27 | 2006-12-28 | 2007-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201245E | WNYC TRANSMITTER TOWERS EMERGENCY DEMOLITION, B385-102M | 4 | CONSTRUCTION | 2007-03-28 | 2008-03-26 | 2007-03-28 | 2008-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201245E | WNYC TRANSMITTER TOWERS EMERGENCY DEMOLITION, B385-102M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-27 | 2009-03-26 | 2008-03-27 | 2009-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201D17B | F.H. STERNBERG PARK BALLFIELDS RECONSTRUCTION, B055-104M | 1 | DEVELOP SCOPE | 2003-07-01 | 2003-10-31 | 2003-07-01 | 2003-10-31
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201D17B | F.H. STERNBERG PARK BALLFIELDS RECONSTRUCTION, B055-104M | 2 | DESIGN | 2003-11-01 | 2004-03-31 | 2003-11-01 | 2004-03-31
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201D17B | F.H. STERNBERG PARK BALLFIELDS RECONSTRUCTION, B055-104M | 3 | BID/ REGISTER CONTRACT | 2004-04-01 | 2004-06-30 | 2004-04-01 | 2004-06-30
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201D17B | F.H. STERNBERG PARK BALLFIELDS RECONSTRUCTION, B055-104M | 4 | CONSTRUCTION | 2004-08-31 | 2005-05-31 | 2004-08-31 | 2005-05-31
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201D17B | F.H. STERNBERG PARK BALLFIELDS RECONSTRUCTION, B055-104M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2005-06-01 | 2006-05-31 | 2005-06-01 | 2022-05-31
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201EYCK | TEN EYCK PLAZA - RENOVATION OF THE PLAZA B386-119M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201EYCK | TEN EYCK PLAZA - RENOVATION OF THE PLAZA B386-119M | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201EYCK | TEN EYCK PLAZA - RENOVATION OF THE PLAZA B386-119M | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201EYCK | TEN EYCK PLAZA - RENOVATION OF THE PLAZA B386-119M | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201EYCK | TEN EYCK PLAZA - RENOVATION OF THE PLAZA B386-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2024-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201FROS | Frost Street Playground - Basketball Court Reconstruction | 1 | DEVELOP SCOPE | 2020-07-01 | 2020-12-27 | 2020-07-01 | 2020-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201FROS | Frost Street Playground - Basketball Court Reconstruction | 2 | DESIGN | 2020-12-28 | 2021-12-27 | 2020-12-28 | 2021-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201FROS | Frost Street Playground - Basketball Court Reconstruction | 3 | BID/ REGISTER CONTRACT | 2021-12-28 | 2022-09-23 | 2021-12-28 | 2022-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201FROS | Frost Street Playground - Basketball Court Reconstruction | 4 | CONSTRUCTION | 2022-09-24 | 2023-09-23 | 2022-09-24 | 2023-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201FROS | Frost Street Playground - Basketball Court Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-24 | 2024-09-22 | 2023-09-24 | 2024-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201GROV | Grove St. Community Garden - Upgrade Play Equipment | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201GROV | Grove St. Community Garden - Upgrade Play Equipment | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201GROV | Grove St. Community Garden - Upgrade Play Equipment | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201GROV | Grove St. Community Garden - Upgrade Play Equipment | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201GROV | Grove St. Community Garden - Upgrade Play Equipment | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201MCBH | McCarren -RC Bathhouse B058-117M | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201MCBH | McCarren -RC Bathhouse B058-117M | 2 | DESIGN | 2016-12-28 | 2018-12-27 | 2016-12-28 | 2018-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201MCBH | McCarren -RC Bathhouse B058-117M | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201MCBH | McCarren -RC Bathhouse B058-117M | 4 | CONSTRUCTION | 2019-09-24 | 2022-09-22 | 2019-09-24 | 2022-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201MCBH | McCarren -RC Bathhouse B058-117M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2024-09-21 | 2022-09-23 | 2024-09-21
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201MCC2 | McCarren Park - Brooklyn | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201MCC2 | McCarren Park - Brooklyn | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201MCC2 | McCarren Park - Brooklyn | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201MCC2 | McCarren Park - Brooklyn | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201MCC2 | McCarren Park - Brooklyn | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201MCGK | McGolrick Park - Sidewalk Replacement | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201MCGK | McGolrick Park - Sidewalk Replacement | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2016-12-28 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201MCGK | McGolrick Park - Sidewalk Replacement | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2017-12-28 | 2018-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201MCGK | McGolrick Park - Sidewalk Replacement | 4 | CONSTRUCTION | 2018-09-24 | 2019-09-23 | 2018-09-24 | 2019-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201MCGK | McGolrick Park - Sidewalk Replacement | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2024-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201MDLT | Middleton Playground - Phase 1 Renovations | 1 | DEVELOP SCOPE | 2020-07-01 | 2020-12-27 | 2020-07-01 | 2020-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201MDLT | Middleton Playground - Phase 1 Renovations | 2 | DESIGN | 2020-12-28 | 2021-12-27 | 2020-12-28 | 2021-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201MDLT | Middleton Playground - Phase 1 Renovations | 3 | BID/ REGISTER CONTRACT | 2021-12-28 | 2022-09-23 | 2021-12-28 | 2022-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201MDLT | Middleton Playground - Phase 1 Renovations | 4 | CONSTRUCTION | 2022-09-24 | 2023-09-23 | 2022-09-24 | 2023-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201MDLT | Middleton Playground - Phase 1 Renovations | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-24 | 2024-09-22 | 2023-09-24 | 2024-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201MPFA | Metropolitan Rec. Center: Fire Alarm Reconstruction | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201MPFA | Metropolitan Rec. Center: Fire Alarm Reconstruction | 2 | DESIGN | 2019-12-28 | 2021-12-26 | 2019-12-28 | 2021-12-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201MPFA | Metropolitan Rec. Center: Fire Alarm Reconstruction | 3 | BID/ REGISTER CONTRACT | 2021-12-27 | 2022-09-22 | 2021-12-27 | 2022-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201MPFA | Metropolitan Rec. Center: Fire Alarm Reconstruction | 4 | CONSTRUCTION | 2022-09-23 | 2025-09-21 | 2022-09-23 | 2025-09-21
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201MPFA | Metropolitan Rec. Center: Fire Alarm Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-09-22 | 2027-09-21 | 2025-09-22 | 2027-09-21
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201MRCY | Marcy Green Park-Reconstruction of Rec. Facilities BG-120M | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201MRCY | Marcy Green Park-Reconstruction of Rec. Facilities BG-120M | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201MRCY | Marcy Green Park-Reconstruction of Rec. Facilities BG-120M | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201MRCY | Marcy Green Park-Reconstruction of Rec. Facilities BG-120M | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201MRCY | Marcy Green Park-Reconstruction of Rec. Facilities BG-120M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201P245 | GRAND FERRY PARK (PRIVATE $ CITYREQMTS) B401-104MA | 2 | DESIGN | 2006-09-29 | 2006-12-27 | 2006-09-29 | 2006-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201P245 | GRAND FERRY PARK (PRIVATE $ CITYREQMTS) B401-104MA | 3 | BID/ REGISTER CONTRACT | 2006-12-28 | 2007-03-27 | 2006-12-28 | 2007-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201P245 | GRAND FERRY PARK (PRIVATE $ CITYREQMTS) B401-104MA | 4 | CONSTRUCTION | 2007-03-28 | 2008-03-26 | 2007-03-28 | 2008-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201P245 | GRAND FERRY PARK (PRIVATE $ CITYREQMTS) B401-104MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-27 | 2009-03-26 | 2008-03-27 | 2009-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201REIN | RIDGEWOOD BUSHW.- BEAVER NOLL PARK BG38500-113M | 1 | DEVELOP SCOPE | 2012-07-01 | 2012-09-28 | 2012-07-01 | 2012-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201REIN | RIDGEWOOD BUSHW.- BEAVER NOLL PARK BG38500-113M | 2 | DESIGN | 2012-09-29 | 2012-12-27 | 2012-09-29 | 2012-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201REIN | RIDGEWOOD BUSHW.- BEAVER NOLL PARK BG38500-113M | 3 | BID/ REGISTER CONTRACT | 2012-12-28 | 2013-03-27 | 2012-12-28 | 2013-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201REIN | RIDGEWOOD BUSHW.- BEAVER NOLL PARK BG38500-113M | 4 | CONSTRUCTION | 2013-03-28 | 2014-03-27 | 2013-03-28 | 2014-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201REIN | RIDGEWOOD BUSHW.- BEAVER NOLL PARK BG38500-113M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-03-28 | 2015-03-27 | 2014-03-28 | 2021-09-02
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201STRN | Sternberg Park Upgrades B055-117M | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201STRN | Sternberg Park Upgrades B055-117M | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2016-12-28 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201STRN | Sternberg Park Upgrades B055-117M | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2017-12-28 | 2018-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201STRN | Sternberg Park Upgrades B055-117M | 4 | CONSTRUCTION | 2018-09-24 | 2019-09-23 | 2018-09-24 | 2019-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201STRN | Sternberg Park Upgrades B055-117M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201TRNS | Transmitter Park - Shoreline Rehabilitation | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201TRNS | Transmitter Park - Shoreline Rehabilitation | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201TRNS | Transmitter Park - Shoreline Rehabilitation | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201TRNS | Transmitter Park - Shoreline Rehabilitation | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201TRNS | Transmitter Park - Shoreline Rehabilitation | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201WILL | William Sheridan - Brooklyn- B124-119M | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201WILL | William Sheridan - Brooklyn- B124-119M | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201WILL | William Sheridan - Brooklyn- B124-119M | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201WILL | William Sheridan - Brooklyn- B124-119M | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201WILL | William Sheridan - Brooklyn- B124-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202018A | Brooklyn Bridge Park | 1 | DEVELOP SCOPE | 2003-10-01 | 2004-01-01 | 2003-10-01 | 2004-01-01
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202018A | Brooklyn Bridge Park | 2 | DESIGN | 2004-01-02 | 2004-03-31 | 2004-01-02 | 2004-03-31
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202018A | Brooklyn Bridge Park | 3 | BID/ REGISTER CONTRACT | 2004-04-01 | 2004-06-30 | 2004-04-01 | 2004-06-30
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202018A | Brooklyn Bridge Park | 4 | CONSTRUCTION | 2004-07-31 | 2005-09-30 | 2004-07-31 | 2005-09-30
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202018A | Brooklyn Bridge Park | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2005-10-01 | 2006-09-30 | 2005-10-01 | 2022-07-01
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202BRDG | Bridge Park- Adult Fitness, Multi Purpose Play (B223J-118M) | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202BRDG | Bridge Park- Adult Fitness, Multi Purpose Play (B223J-118M) | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2016-12-28 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202BRDG | Bridge Park- Adult Fitness, Multi Purpose Play (B223J-118M) | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2017-12-28 | 2018-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202BRDG | Bridge Park- Adult Fitness, Multi Purpose Play (B223J-118M) | 4 | CONSTRUCTION | 2018-09-24 | 2019-09-23 | 2018-09-24 | 2019-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202BRDG | Bridge Park- Adult Fitness, Multi Purpose Play (B223J-118M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2023-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202C974 | FORT GREENE PK PRISONSH MARTYRS MONU&BR EAGL B32-103MA,203MA | 1 | DEVELOP SCOPE | 2002-07-01 | 2003-03-10 | 2002-07-01 | 2003-03-10
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202C974 | FORT GREENE PK PRISONSH MARTYRS MONU&BR EAGL B32-103MA,203MA | 2 | DESIGN | 2003-03-11 | 2004-03-31 | 2003-03-11 | 2005-01-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202C974 | FORT GREENE PK PRISONSH MARTYRS MONU&BR EAGL B32-103MA,203MA | 3 | BID/ REGISTER CONTRACT | 2004-04-01 | 2004-06-30 | 2005-03-09 | 2005-10-18
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202C974 | FORT GREENE PK PRISONSH MARTYRS MONU&BR EAGL B32-103MA,203MA | 4 | CONSTRUCTION | 2004-07-31 | 2005-12-27 | 2006-03-06 | 2007-10-17
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202C974 | FORT GREENE PK PRISONSH MARTYRS MONU&BR EAGL B32-103MA,203MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2005-12-28 | 2006-12-28 | 2007-10-18 | 2024-10-17
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202CAD2 | Cadman Plaza Park - Brooklyn (B113A-119M) | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202CAD2 | Cadman Plaza Park - Brooklyn (B113A-119M) | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202CAD2 | Cadman Plaza Park - Brooklyn (B113A-119M) | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202CAD2 | Cadman Plaza Park - Brooklyn (B113A-119M) | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202CAD2 | Cadman Plaza Park - Brooklyn (B113A-119M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202CADM | CADMAN PLAZA (RC L/S SURROND BKLN WAR MEM. BLDG ACCESS) | 1 | DEVELOP SCOPE | 2011-07-01 | 2011-09-28 | 2011-07-01 | 2011-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202CADM | CADMAN PLAZA (RC L/S SURROND BKLN WAR MEM. BLDG ACCESS) | 2 | DESIGN | 2011-09-29 | 2011-12-27 | 2011-09-29 | 2011-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202CADM | CADMAN PLAZA (RC L/S SURROND BKLN WAR MEM. BLDG ACCESS) | 3 | BID/ REGISTER CONTRACT | 2011-12-28 | 2012-03-26 | 2011-12-28 | 2012-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202CADM | CADMAN PLAZA (RC L/S SURROND BKLN WAR MEM. BLDG ACCESS) | 4 | CONSTRUCTION | 2012-03-27 | 2013-03-26 | 2012-03-27 | 2013-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202CADM | CADMAN PLAZA (RC L/S SURROND BKLN WAR MEM. BLDG ACCESS) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-03-27 | 2014-03-26 | 2013-03-27 | 2022-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202CBP1 | Commodore Barry Park - Continue Park Phase Renovations | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202CBP1 | Commodore Barry Park - Continue Park Phase Renovations | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202CBP1 | Commodore Barry Park - Continue Park Phase Renovations | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202CBP1 | Commodore Barry Park - Continue Park Phase Renovations | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202CBP1 | Commodore Barry Park - Continue Park Phase Renovations | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202CHAP | CHAPIN PLAYGROUND -RECON. SPRINKLER BG-311M | 1 | DEVELOP SCOPE | 2012-07-01 | 2012-09-28 | 2012-07-01 | 2012-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202CHAP | CHAPIN PLAYGROUND -RECON. SPRINKLER BG-311M | 2 | DESIGN | 2012-09-29 | 2012-12-27 | 2012-09-29 | 2012-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202CHAP | CHAPIN PLAYGROUND -RECON. SPRINKLER BG-311M | 3 | BID/ REGISTER CONTRACT | 2012-12-28 | 2013-03-27 | 2012-12-28 | 2013-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202CHAP | CHAPIN PLAYGROUND -RECON. SPRINKLER BG-311M | 4 | CONSTRUCTION | 2013-03-28 | 2014-03-27 | 2013-03-28 | 2014-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202CHAP | CHAPIN PLAYGROUND -RECON. SPRINKLER BG-311M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-03-28 | 2015-03-27 | 2014-03-28 | 2025-08-16
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202CUGP | Cuyler Gore Park Renovations | 1 | DEVELOP SCOPE | 2020-07-01 | 2020-12-27 | 2020-07-01 | 2020-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202CUGP | Cuyler Gore Park Renovations | 2 | DESIGN | 2020-12-28 | 2021-12-27 | 2020-12-28 | 2021-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202CUGP | Cuyler Gore Park Renovations | 3 | BID/ REGISTER CONTRACT | 2021-12-28 | 2022-09-23 | 2021-12-28 | 2022-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202CUGP | Cuyler Gore Park Renovations | 4 | CONSTRUCTION | 2022-09-24 | 2023-09-23 | 2022-09-24 | 2023-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202CUGP | Cuyler Gore Park Renovations | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-24 | 2024-09-22 | 2023-09-24 | 2024-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202D17B | MCLAUGHLIN PARK BALLFIELD,WDG POOL AREA,BSKTBL&HNDB,B61-105M | 1 | DEVELOP SCOPE | 2003-07-01 | 2003-10-31 | 2003-07-01 | 2003-10-31
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202D17B | MCLAUGHLIN PARK BALLFIELD,WDG POOL AREA,BSKTBL&HNDB,B61-105M | 2 | DESIGN | 2003-11-01 | 2003-12-31 | 2003-11-01 | 2003-12-31
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202D17B | MCLAUGHLIN PARK BALLFIELD,WDG POOL AREA,BSKTBL&HNDB,B61-105M | 3 | BID/ REGISTER CONTRACT | 2004-01-01 | 2004-03-31 | 2004-01-01 | 2004-03-31
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202D17B | MCLAUGHLIN PARK BALLFIELD,WDG POOL AREA,BSKTBL&HNDB,B61-105M | 4 | CONSTRUCTION | 2004-05-15 | 2005-05-15 | 2004-05-15 | 2005-05-15
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202D17B | MCLAUGHLIN PARK BALLFIELD,WDG POOL AREA,BSKTBL&HNDB,B61-105M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2005-05-16 | 2006-05-15 | 2005-05-16 | 2006-05-15
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202FTGN | Fort Grene Park - entrance & pass (B032-110M) | 1 | DEVELOP SCOPE | 2007-07-01 | 2007-09-28 | 2005-11-02 | 2006-01-30
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202FTGN | Fort Grene Park - entrance & pass (B032-110M) | 2 | DESIGN | 2007-09-29 | 2007-12-27 | 2006-01-31 | 2006-04-30
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202FTGN | Fort Grene Park - entrance & pass (B032-110M) | 3 | BID/ REGISTER CONTRACT | 2007-12-28 | 2008-03-26 | 2006-05-01 | 2006-07-29
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202FTGN | Fort Grene Park - entrance & pass (B032-110M) | 4 | CONSTRUCTION | 2008-03-27 | 2009-03-26 | 2006-07-30 | 2007-07-29
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202FTGN | Fort Grene Park - entrance & pass (B032-110M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2009-03-27 | 2010-03-26 | 2007-07-30 | 2022-11-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202FTGP | PWOB-FT. GREENE PK- PATHS,ENTRANCE RC & DRAINAGE B032-116M) | 1 | DEVELOP SCOPE | 2015-02-01 | 2015-05-01 | 2015-02-01 | 2015-05-01
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202FTGP | PWOB-FT. GREENE PK- PATHS,ENTRANCE RC & DRAINAGE B032-116M) | 2 | DESIGN | 2015-05-02 | 2015-07-30 | 2015-05-02 | 2015-07-30
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202FTGP | PWOB-FT. GREENE PK- PATHS,ENTRANCE RC & DRAINAGE B032-116M) | 3 | BID/ REGISTER CONTRACT | 2015-07-31 | 2015-10-28 | 2015-07-31 | 2015-10-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202FTGP | PWOB-FT. GREENE PK- PATHS,ENTRANCE RC & DRAINAGE B032-116M) | 4 | CONSTRUCTION | 2015-10-29 | 2016-10-27 | 2015-10-29 | 2016-10-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202FTGP | PWOB-FT. GREENE PK- PATHS,ENTRANCE RC & DRAINAGE B032-116M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-10-28 | 2017-10-27 | 2016-10-28 | 2022-10-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202GRPL | Greene Playground - Reconstruction of Playground | 1 | DEVELOP SCOPE | 2020-07-01 | 2020-12-27 | 2020-07-01 | 2020-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202GRPL | Greene Playground - Reconstruction of Playground | 2 | DESIGN | 2020-12-28 | 2021-12-27 | 2020-12-28 | 2021-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202GRPL | Greene Playground - Reconstruction of Playground | 3 | BID/ REGISTER CONTRACT | 2021-12-28 | 2022-09-23 | 2021-12-28 | 2022-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202GRPL | Greene Playground - Reconstruction of Playground | 4 | CONSTRUCTION | 2022-09-24 | 2023-09-23 | 2022-09-24 | 2023-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202GRPL | Greene Playground - Reconstruction of Playground | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-24 | 2024-09-22 | 2023-09-24 | 2024-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202WASH | Washington Hall Playground basketball courts, Brooklyn | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202WASH | Washington Hall Playground basketball courts, Brooklyn | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202WASH | Washington Hall Playground basketball courts, Brooklyn | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202WASH | Washington Hall Playground basketball courts, Brooklyn | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202WASH | Washington Hall Playground basketball courts, Brooklyn | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202WPDR | Washington Park Dog Run B111-118M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202WPDR | Washington Park Dog Run B111-118M | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202WPDR | Washington Park Dog Run B111-118M | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202WPDR | Washington Park Dog Run B111-118M | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202WPDR | Washington Park Dog Run B111-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203CHRL | Charlie's Place Reconstruction | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203CHRL | Charlie's Place Reconstruction | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203CHRL | Charlie's Place Reconstruction | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203CHRL | Charlie's Place Reconstruction | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203CHRL | Charlie's Place Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203D17C | SARATOGA SQUARE PARK MEMORIAL - B079-110M | 1 | DEVELOP SCOPE | 2006-07-01 | 2006-09-28 | 2006-02-02 | 2006-05-02
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203D17C | SARATOGA SQUARE PARK MEMORIAL - B079-110M | 2 | DESIGN | 2006-09-29 | 2006-12-27 | 2006-05-03 | 2011-09-06
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203D17C | SARATOGA SQUARE PARK MEMORIAL - B079-110M | 3 | BID/ REGISTER CONTRACT | 2006-12-28 | 2007-03-27 | 2011-09-07 | 2011-09-06
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203D17C | SARATOGA SQUARE PARK MEMORIAL - B079-110M | 4 | CONSTRUCTION | 2007-03-28 | 2008-03-26 | 2012-07-26 | 2013-07-25
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203D17C | SARATOGA SQUARE PARK MEMORIAL - B079-110M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-27 | 2009-03-26 | 2013-07-26 | 2014-07-25
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203D17E | Von King cultural arts center - phase 3 B088-111MA | 1 | DEVELOP SCOPE | 2006-07-01 | 2006-09-28 | 2011-05-28 | 2011-07-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203D17E | Von King cultural arts center - phase 3 B088-111MA | 2 | DESIGN | 2006-09-29 | 2006-12-27 | 2011-05-31 | 2012-01-31
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203D17E | Von King cultural arts center - phase 3 B088-111MA | 3 | BID/ REGISTER CONTRACT | 2006-12-28 | 2007-03-27 | 2012-06-01 | 2012-09-30
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203D17E | Von King cultural arts center - phase 3 B088-111MA | 4 | CONSTRUCTION | 2007-03-28 | 2008-03-26 | 2012-12-31 | 2013-12-31
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203D17E | Von King cultural arts center - phase 3 B088-111MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-27 | 2009-03-26 | 2013-07-05 | 2020-08-05
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203FULT | FULTON PARK - RESTORATION OF COMFORT STATION B038-116M | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2015-10-01
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203FULT | FULTON PARK - RESTORATION OF COMFORT STATION B038-116M | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2015-10-02 | 2015-12-31
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203FULT | FULTON PARK - RESTORATION OF COMFORT STATION B038-116M | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2016-01-01 | 2016-03-30
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203FULT | FULTON PARK - RESTORATION OF COMFORT STATION B038-116M | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2016-03-31 | 2017-03-30
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203FULT | FULTON PARK - RESTORATION OF COMFORT STATION B038-116M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2017-03-31 | 2023-03-30
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203HPUP | Harmony Park - Upgrades and Beautification | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203HPUP | Harmony Park - Upgrades and Beautification | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203HPUP | Harmony Park - Upgrades and Beautification | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203HPUP | Harmony Park - Upgrades and Beautification | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203HPUP | Harmony Park - Upgrades and Beautification | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203LFGP | Lafayette Gardens Playground Reconstruction | 1 | DEVELOP SCOPE | 2020-07-01 | 2020-12-27 | 2020-07-01 | 2020-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203LFGP | Lafayette Gardens Playground Reconstruction | 2 | DESIGN | 2020-12-28 | 2021-12-27 | 2020-12-28 | 2021-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203LFGP | Lafayette Gardens Playground Reconstruction | 3 | BID/ REGISTER CONTRACT | 2021-12-28 | 2022-09-23 | 2021-12-28 | 2022-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203LFGP | Lafayette Gardens Playground Reconstruction | 4 | CONSTRUCTION | 2022-09-24 | 2023-09-23 | 2022-09-24 | 2023-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203LFGP | Lafayette Gardens Playground Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-24 | 2024-09-22 | 2023-09-24 | 2024-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203SRTG | Saratoga Park - Playground Reconstruction (B079-119M) | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203SRTG | Saratoga Park - Playground Reconstruction (B079-119M) | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203SRTG | Saratoga Park - Playground Reconstruction (B079-119M) | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203SRTG | Saratoga Park - Playground Reconstruction (B079-119M) | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203SRTG | Saratoga Park - Playground Reconstruction (B079-119M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-204GRCK | Green Central Knoll - Comfort Station B395-115M | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2015-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-204GRCK | Green Central Knoll - Comfort Station B395-115M | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2015-09-29 | 2015-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-204GRCK | Green Central Knoll - Comfort Station B395-115M | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2015-12-28 | 2016-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-204GRCK | Green Central Knoll - Comfort Station B395-115M | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-204GRCK | Green Central Knoll - Comfort Station B395-115M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2017-03-27 | 2023-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-204HECK | Heckscher Playground (B139-115M) | 1 | DEVELOP SCOPE | 2014-07-01 | 2014-09-28 | 2014-07-01 | 2014-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-204HECK | Heckscher Playground (B139-115M) | 2 | DESIGN | 2014-09-29 | 2014-12-27 | 2014-09-29 | 2014-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-204HECK | Heckscher Playground (B139-115M) | 3 | BID/ REGISTER CONTRACT | 2014-12-28 | 2015-03-27 | 2014-12-28 | 2015-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-204HECK | Heckscher Playground (B139-115M) | 4 | CONSTRUCTION | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2016-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-204HECK | Heckscher Playground (B139-115M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2024-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-204HOPE | Hope Ballfields (B429-116M) | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-204HOPE | Hope Ballfields (B429-116M) | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2016-12-28 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-204HOPE | Hope Ballfields (B429-116M) | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2017-12-28 | 2018-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-204HOPE | Hope Ballfields (B429-116M) | 4 | CONSTRUCTION | 2018-09-24 | 2019-09-23 | 2018-09-24 | 2019-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-204HOPE | Hope Ballfields (B429-116M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2024-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-204RUDD | Rudd Play. - Con. Skate Park & Bask. ball cts (B131-117M) | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-204RUDD | Rudd Play. - Con. Skate Park & Bask. ball cts (B131-117M) | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2016-12-28 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-204RUDD | Rudd Play. - Con. Skate Park & Bask. ball cts (B131-117M) | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2017-12-28 | 2018-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-204RUDD | Rudd Play. - Con. Skate Park & Bask. ball cts (B131-117M) | 4 | CONSTRUCTION | 2018-09-24 | 2019-09-23 | 2018-09-24 | 2019-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-204RUDD | Rudd Play. - Con. Skate Park & Bask. ball cts (B131-117M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205CYPS | Cypress Park - Renovation of Cypress Park B103-116M | 1 | DEVELOP SCOPE | 2014-07-01 | 2014-09-28 | 2014-07-01 | 2014-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205CYPS | Cypress Park - Renovation of Cypress Park B103-116M | 2 | DESIGN | 2014-09-29 | 2014-12-27 | 2014-09-29 | 2014-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205CYPS | Cypress Park - Renovation of Cypress Park B103-116M | 3 | BID/ REGISTER CONTRACT | 2014-12-28 | 2015-03-27 | 2014-12-28 | 2015-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205CYPS | Cypress Park - Renovation of Cypress Park B103-116M | 4 | CONSTRUCTION | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2016-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205CYPS | Cypress Park - Renovation of Cypress Park B103-116M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2023-03-01
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205GRPG | Grace Playground Park Renovation Phase I B078-119M | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205GRPG | Grace Playground Park Renovation Phase I B078-119M | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205GRPG | Grace Playground Park Renovation Phase I B078-119M | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205GRPG | Grace Playground Park Renovation Phase I B078-119M | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205GRPG | Grace Playground Park Renovation Phase I B078-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205HLND | Highland Park Basketball Courts R/C Q020-116MA | 1 | DEVELOP SCOPE | 2014-07-01 | 2014-09-28 | 2015-07-01 | 2015-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205HLND | Highland Park Basketball Courts R/C Q020-116MA | 2 | DESIGN | 2014-09-29 | 2014-12-27 | 2015-09-29 | 2015-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205HLND | Highland Park Basketball Courts R/C Q020-116MA | 3 | BID/ REGISTER CONTRACT | 2014-12-28 | 2015-03-27 | 2015-12-28 | 2016-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205HLND | Highland Park Basketball Courts R/C Q020-116MA | 4 | CONSTRUCTION | 2015-03-28 | 2016-03-26 | 2016-03-27 | 2017-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205HLND | Highland Park Basketball Courts R/C Q020-116MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-27 | 2017-03-26 | 2017-03-27 | 2023-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205HPSB | Highland Park Stone Bridge Q020-418M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205HPSB | Highland Park Stone Bridge Q020-418M | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205HPSB | Highland Park Stone Bridge Q020-418M | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205HPSB | Highland Park Stone Bridge Q020-418M | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205HPSB | Highland Park Stone Bridge Q020-418M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205LIN1 | Linden Park:Phase 4-Playground,Spray Shower & Basketball crt | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205LIN1 | Linden Park:Phase 4-Playground,Spray Shower & Basketball crt | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205LIN1 | Linden Park:Phase 4-Playground,Spray Shower & Basketball crt | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205LIN1 | Linden Park:Phase 4-Playground,Spray Shower & Basketball crt | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205LIN1 | Linden Park:Phase 4-Playground,Spray Shower & Basketball crt | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205LIN2 | Linden Park: Phase 5 Area Renovation | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205LIN2 | Linden Park: Phase 5 Area Renovation | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205LIN2 | Linden Park: Phase 5 Area Renovation | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205LIN2 | Linden Park: Phase 5 Area Renovation | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205LIN2 | Linden Park: Phase 5 Area Renovation | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205LION | Lion's Pride Playground - B107-119M | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205LION | Lion's Pride Playground - B107-119M | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205LION | Lion's Pride Playground - B107-119M | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205LION | Lion's Pride Playground - B107-119M | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205LION | Lion's Pride Playground - B107-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205PPMT | Public Place - Monument Reconstruction | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205PPMT | Public Place - Monument Reconstruction | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205PPMT | Public Place - Monument Reconstruction | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205PPMT | Public Place - Monument Reconstruction | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205PPMT | Public Place - Monument Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205SBRO | Sperandeo Brothers playground B163-110M | 1 | DEVELOP SCOPE | 2009-07-01 | 2009-09-28 | 2009-07-01 | 2009-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205SBRO | Sperandeo Brothers playground B163-110M | 2 | DESIGN | 2009-09-29 | 2009-12-27 | 2009-09-29 | 2009-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205SBRO | Sperandeo Brothers playground B163-110M | 3 | BID/ REGISTER CONTRACT | 2009-12-28 | 2010-03-27 | 2009-12-28 | 2010-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205SBRO | Sperandeo Brothers playground B163-110M | 4 | CONSTRUCTION | 2010-03-28 | 2011-03-27 | 2010-03-28 | 2011-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205SBRO | Sperandeo Brothers playground B163-110M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2011-03-28 | 2012-03-26 | 2011-03-28 | 2024-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205SDFC | Sperandeo Playground - Fence RC. B163-215M | 4 | CONSTRUCTION | 2015-09-28 | 2016-09-26 | 2015-09-28 | 2016-09-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205SDFC | Sperandeo Playground - Fence RC. B163-215M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-09-27 | 2017-09-26 | 2016-09-27 | 2017-09-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205SHNK | Schenk Playground - B261 | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2015-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205SHNK | Schenk Playground - B261 | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2015-09-29 | 2015-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205SHNK | Schenk Playground - B261 | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2015-12-28 | 2016-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205SHNK | Schenk Playground - B261 | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205SHNK | Schenk Playground - B261 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2017-03-27 | 2026-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206ENIS | Ennis Playground - B095-116M | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2015-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206ENIS | Ennis Playground - B095-116M | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2015-09-29 | 2015-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206ENIS | Ennis Playground - B095-116M | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2015-12-28 | 2016-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206ENIS | Ennis Playground - B095-116M | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206ENIS | Ennis Playground - B095-116M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2017-03-27 | 2022-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206GDAM | Restoration of Grand Army Plaza Arch, Bailey Ftn, &SRND AREA | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206GDAM | Restoration of Grand Army Plaza Arch, Bailey Ftn, &SRND AREA | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206GDAM | Restoration of Grand Army Plaza Arch, Bailey Ftn, &SRND AREA | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206GDAM | Restoration of Grand Army Plaza Arch, Bailey Ftn, &SRND AREA | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206GDAM | Restoration of Grand Army Plaza Arch, Bailey Ftn, &SRND AREA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206GDAS | Grand Army Plaza - Site Restoration B040-120M | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206GDAS | Grand Army Plaza - Site Restoration B040-120M | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206GDAS | Grand Army Plaza - Site Restoration B040-120M | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206GDAS | Grand Army Plaza - Site Restoration B040-120M | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206GDAS | Grand Army Plaza - Site Restoration B040-120M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206ICKE | HAROLD ICKES PLGRD PH 1 | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206ICKE | HAROLD ICKES PLGRD PH 1 | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206ICKE | HAROLD ICKES PLGRD PH 1 | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206ICKE | HAROLD ICKES PLGRD PH 1 | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206ICKE | HAROLD ICKES PLGRD PH 1 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206MARY | St. Mary's Plgd. Play Equip. Recon. Safety Surf. B118-115M | 1 | DEVELOP SCOPE | 2014-07-01 | 2014-09-28 | 2014-07-01 | 2014-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206MARY | St. Mary's Plgd. Play Equip. Recon. Safety Surf. B118-115M | 2 | DESIGN | 2014-09-29 | 2014-12-27 | 2014-09-29 | 2014-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206MARY | St. Mary's Plgd. Play Equip. Recon. Safety Surf. B118-115M | 3 | BID/ REGISTER CONTRACT | 2014-12-28 | 2015-03-27 | 2014-12-28 | 2015-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206MARY | St. Mary's Plgd. Play Equip. Recon. Safety Surf. B118-115M | 4 | CONSTRUCTION | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2016-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206MARY | St. Mary's Plgd. Play Equip. Recon. Safety Surf. B118-115M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2023-04-16
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206PENN | William Penn Playground - Renovate P.S. 321 | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206PENN | William Penn Playground - Renovate P.S. 321 | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206PENN | William Penn Playground - Renovate P.S. 321 | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206PENN | William Penn Playground - Renovate P.S. 321 | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206PENN | William Penn Playground - Renovate P.S. 321 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206REDH | RC - PATHS AND BBQ AREA IN COFFEY PARK B077-112M | 1 | DEVELOP SCOPE | 2010-07-01 | 2010-09-28 | 2010-07-01 | 2010-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206REDH | RC - PATHS AND BBQ AREA IN COFFEY PARK B077-112M | 2 | DESIGN | 2010-09-29 | 2010-12-27 | 2010-09-29 | 2010-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206REDH | RC - PATHS AND BBQ AREA IN COFFEY PARK B077-112M | 3 | BID/ REGISTER CONTRACT | 2010-12-28 | 2011-03-27 | 2010-12-28 | 2011-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206REDH | RC - PATHS AND BBQ AREA IN COFFEY PARK B077-112M | 4 | CONSTRUCTION | 2011-03-28 | 2012-03-26 | 2011-03-28 | 2012-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206REDH | RC - PATHS AND BBQ AREA IN COFFEY PARK B077-112M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-03-27 | 2013-03-26 | 2012-03-27 | 2013-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206RH02 | Red Hook - Oversight 9 | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206RH02 | Red Hook - Oversight 9 | 2 | DESIGN | 2016-12-28 | 2018-06-25 | 2016-12-28 | 2018-06-25
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206RH02 | Red Hook - Oversight 9 | 3 | BID/ REGISTER CONTRACT | 2018-06-26 | 2019-03-22 | 2018-06-26 | 2019-03-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206RH02 | Red Hook - Oversight 9 | 4 | CONSTRUCTION | 2019-03-23 | 2020-09-17 | 2019-03-23 | 2020-09-17
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206RH02 | Red Hook - Oversight 9 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-18 | 2021-09-17 | 2020-09-18 | 2024-09-17
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206RHBF | Red Hook - Ball field 9/Soccer 2 (B126-117M) | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206RHBF | Red Hook - Ball field 9/Soccer 2 (B126-117M) | 2 | DESIGN | 2016-12-28 | 2018-06-25 | 2016-12-28 | 2018-06-25
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206RHBF | Red Hook - Ball field 9/Soccer 2 (B126-117M) | 3 | BID/ REGISTER CONTRACT | 2018-06-26 | 2019-03-22 | 2018-06-26 | 2019-03-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206RHBF | Red Hook - Ball field 9/Soccer 2 (B126-117M) | 4 | CONSTRUCTION | 2019-03-23 | 2020-09-17 | 2019-03-23 | 2020-09-17
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206RHBF | Red Hook - Ball field 9/Soccer 2 (B126-117M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-18 | 2021-09-17 | 2020-09-18 | 2021-09-17
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206RHBS | Red Hook Track 1/Soccer 3 & Ballfields 1-4 (B126-118M) | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206RHBS | Red Hook Track 1/Soccer 3 & Ballfields 1-4 (B126-118M) | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2016-12-28 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206RHBS | Red Hook Track 1/Soccer 3 & Ballfields 1-4 (B126-118M) | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2017-12-28 | 2018-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206RHBS | Red Hook Track 1/Soccer 3 & Ballfields 1-4 (B126-118M) | 4 | CONSTRUCTION | 2018-09-24 | 2019-09-23 | 2018-09-24 | 2019-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206RHBS | Red Hook Track 1/Soccer 3 & Ballfields 1-4 (B126-118M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2024-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206RHCF | Red Hook - Community Farm Upgrades | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206RHCF | Red Hook - Community Farm Upgrades | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206RHCF | Red Hook - Community Farm Upgrades | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206RHCF | Red Hook - Community Farm Upgrades | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206RHCF | Red Hook - Community Farm Upgrades | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206RHO1 | Red Hook- EPA Oversight 5-8 | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206RHO1 | Red Hook- EPA Oversight 5-8 | 2 | DESIGN | 2016-12-28 | 2018-06-25 | 2016-12-28 | 2018-06-25
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206RHO1 | Red Hook- EPA Oversight 5-8 | 3 | BID/ REGISTER CONTRACT | 2018-06-26 | 2019-03-22 | 2018-06-26 | 2019-03-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206RHO1 | Red Hook- EPA Oversight 5-8 | 4 | CONSTRUCTION | 2019-03-23 | 2020-09-17 | 2019-03-23 | 2020-09-17
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206RHO1 | Red Hook- EPA Oversight 5-8 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-18 | 2021-09-17 | 2020-09-18 | 2024-09-17
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206RHSF | Red Hook - Soccer 1 & 6 | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206RHSF | Red Hook - Soccer 1 & 6 | 2 | DESIGN | 2016-12-28 | 2018-06-25 | 2016-12-28 | 2018-06-25
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206RHSF | Red Hook - Soccer 1 & 6 | 3 | BID/ REGISTER CONTRACT | 2018-06-26 | 2019-03-22 | 2018-06-26 | 2019-03-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206RHSF | Red Hook - Soccer 1 & 6 | 4 | CONSTRUCTION | 2019-03-23 | 2020-09-17 | 2019-03-23 | 2020-09-17
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206RHSF | Red Hook - Soccer 1 & 6 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-18 | 2021-09-17 | 2020-09-18 | 2026-09-17
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206SMRY | St. Mary's Playground (B118-116M) | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2015-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206SMRY | St. Mary's Playground (B118-116M) | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2015-09-29 | 2015-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206SMRY | St. Mary's Playground (B118-116M) | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2015-12-28 | 2016-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206SMRY | St. Mary's Playground (B118-116M) | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206SMRY | St. Mary's Playground (B118-116M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2017-03-27 | 2023-07-29
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207BTFY | Butterfly Garden - B255G | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2015-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207BTFY | Butterfly Garden - B255G | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2015-09-23 | 2016-06-30
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207BTFY | Butterfly Garden - B255G | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2016-11-29 | 2017-08-18
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207BTFY | Butterfly Garden - B255G | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2017-09-18 | 2018-09-13
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207BTFY | Butterfly Garden - B255G | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2018-09-14 | 2021-09-13
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207JAPN | JOHN ALLEN PAYNE PLAYGROUND (B210-115M) | 2 | DESIGN | 2012-09-29 | 2012-12-27 | 2014-11-02 | 2016-04-25
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207JAPN | JOHN ALLEN PAYNE PLAYGROUND (B210-115M) | 3 | BID/ REGISTER CONTRACT | 2012-12-28 | 2013-03-27 | 2016-06-24 | 2017-02-10
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207JAPN | JOHN ALLEN PAYNE PLAYGROUND (B210-115M) | 4 | CONSTRUCTION | 2013-03-28 | 2014-03-27 | 2017-04-24 | 2018-07-18
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207JAPN | JOHN ALLEN PAYNE PLAYGROUND (B210-115M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-03-28 | 2015-03-27 | 2018-07-19 | 2024-08-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207OPML | Ocean Parkway Malls - RC B065-119M | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207OPML | Ocean Parkway Malls - RC B065-119M | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207OPML | Ocean Parkway Malls - RC B065-119M | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207OPML | Ocean Parkway Malls - RC B065-119M | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207OPML | Ocean Parkway Malls - RC B065-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207RAIN | Rainbow Playground - Playground Update B265 | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207RAIN | Rainbow Playground - Playground Update B265 | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207RAIN | Rainbow Playground - Playground Update B265 | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207RAIN | Rainbow Playground - Playground Update B265 | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207RAIN | Rainbow Playground - Playground Update B265 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207SNST | Sunset Park - Benches -B087-116M | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2015-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207SNST | Sunset Park - Benches -B087-116M | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2015-09-29 | 2015-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207SNST | Sunset Park - Benches -B087-116M | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2015-12-28 | 2016-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207SNST | Sunset Park - Benches -B087-116M | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207SNST | Sunset Park - Benches -B087-116M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2017-03-27 | 2022-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207SPHD | HANDBALL COURT RENOVATIONS AT SUNSET PARK (B087-119M) | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207SPHD | HANDBALL COURT RENOVATIONS AT SUNSET PARK (B087-119M) | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207SPHD | HANDBALL COURT RENOVATIONS AT SUNSET PARK (B087-119M) | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207SPHD | HANDBALL COURT RENOVATIONS AT SUNSET PARK (B087-119M) | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207SPHD | HANDBALL COURT RENOVATIONS AT SUNSET PARK (B087-119M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207SPOS | Sunset Park - Open Stage Creation | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207SPOS | Sunset Park - Open Stage Creation | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207SPOS | Sunset Park - Open Stage Creation | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207SPOS | Sunset Park - Open Stage Creation | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207SPOS | Sunset Park - Open Stage Creation | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207SSAF | Sunset Park - Adult Fitness | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2015-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207SSAF | Sunset Park - Adult Fitness | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2015-09-29 | 2015-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207SSAF | Sunset Park - Adult Fitness | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2015-12-28 | 2016-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207SSAF | Sunset Park - Adult Fitness | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207SSAF | Sunset Park - Adult Fitness | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2017-03-27 | 2022-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207SSPK | Sunset Park - Renovation - B087-117MA | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207SSPK | Sunset Park - Renovation - B087-117MA | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2016-12-28 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207SSPK | Sunset Park - Renovation - B087-117MA | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2017-12-28 | 2018-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207SSPK | Sunset Park - Renovation - B087-117MA | 4 | CONSTRUCTION | 2018-09-24 | 2019-09-23 | 2018-09-24 | 2019-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207SSPK | Sunset Park - Renovation - B087-117MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207SUNS | SUNSET PARK PLAYGROUND RC B087-112M | 2 | DESIGN | 2011-09-29 | 2011-12-27 | 2011-10-13 | 2013-12-12
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207SUNS | SUNSET PARK PLAYGROUND RC B087-112M | 3 | BID/ REGISTER CONTRACT | 2011-12-28 | 2012-03-26 | 2014-07-11 | 2015-10-06
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207SUNS | SUNSET PARK PLAYGROUND RC B087-112M | 4 | CONSTRUCTION | 2012-03-27 | 2013-03-26 | 2016-04-04 | 2017-07-31
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207SUNS | SUNSET PARK PLAYGROUND RC B087-112M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-03-27 | 2014-03-26 | 2017-08-01 | 2024-07-31
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208BROW | Brower Park - Reconstruction of basketball courts -B012-117M | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208BROW | Brower Park - Reconstruction of basketball courts -B012-117M | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2016-12-28 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208BROW | Brower Park - Reconstruction of basketball courts -B012-117M | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2017-12-28 | 2018-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208BROW | Brower Park - Reconstruction of basketball courts -B012-117M | 4 | CONSTRUCTION | 2018-09-24 | 2019-09-23 | 2018-09-24 | 2019-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208BROW | Brower Park - Reconstruction of basketball courts -B012-117M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208C17E | MT. PROSPECT PARK COMFORT STATION RECONSTR; B159-101M-D-301M | 1 | DEVELOP SCOPE | 2008-07-01 | 2008-09-28 | 2008-07-01 | 2008-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208C17E | MT. PROSPECT PARK COMFORT STATION RECONSTR; B159-101M-D-301M | 2 | DESIGN | 2008-09-29 | 2008-12-27 | 2008-09-29 | 2008-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208C17E | MT. PROSPECT PARK COMFORT STATION RECONSTR; B159-101M-D-301M | 3 | BID/ REGISTER CONTRACT | 2008-12-28 | 2009-03-27 | 2008-12-28 | 2009-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208C17E | MT. PROSPECT PARK COMFORT STATION RECONSTR; B159-101M-D-301M | 4 | CONSTRUCTION | 2009-03-28 | 2010-03-27 | 2009-03-28 | 2010-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208C17E | MT. PROSPECT PARK COMFORT STATION RECONSTR; B159-101M-D-301M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2010-03-28 | 2011-03-27 | 2010-03-28 | 2011-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208HVAC | ST. JOHNS HVAC UPGRADE-B245-114M | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2014-03-19
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208HVAC | ST. JOHNS HVAC UPGRADE-B245-114M | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2014-03-20 | 2015-02-17
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208HVAC | ST. JOHNS HVAC UPGRADE-B245-114M | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2015-02-18 | 2015-05-18
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208HVAC | ST. JOHNS HVAC UPGRADE-B245-114M | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2016-12-05 | 2017-12-04
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208HVAC | ST. JOHNS HVAC UPGRADE-B245-114M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2017-12-05 | 2023-12-04
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208K11A | ST. MARK'S AVE. STREETBED PARK RECONSTR; BG-38050-199 | 1 | DEVELOP SCOPE | 2006-07-01 | 2006-09-28 | 2006-07-01 | 2006-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208K11A | ST. MARK'S AVE. STREETBED PARK RECONSTR; BG-38050-199 | 2 | DESIGN | 2006-09-29 | 2006-12-27 | 2006-09-29 | 2006-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208K11A | ST. MARK'S AVE. STREETBED PARK RECONSTR; BG-38050-199 | 3 | BID/ REGISTER CONTRACT | 2006-12-28 | 2007-03-27 | 2006-12-28 | 2007-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208K11A | ST. MARK'S AVE. STREETBED PARK RECONSTR; BG-38050-199 | 4 | CONSTRUCTION | 2007-03-28 | 2008-03-26 | 2007-03-28 | 2008-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208K11A | ST. MARK'S AVE. STREETBED PARK RECONSTR; BG-38050-199 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-27 | 2009-03-26 | 2008-03-27 | 2022-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208K11E | St. John's Recreation Center - comfort station (B245-111M) | 1 | DEVELOP SCOPE | 2009-07-01 | 2009-09-28 | 2009-07-01 | 2009-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208K11E | St. John's Recreation Center - comfort station (B245-111M) | 2 | DESIGN | 2009-09-29 | 2009-12-27 | 2012-11-28 | 2013-02-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208K11E | St. John's Recreation Center - comfort station (B245-111M) | 3 | BID/ REGISTER CONTRACT | 2009-12-28 | 2010-03-27 | 2013-03-01 | 2013-09-01
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208K11E | St. John's Recreation Center - comfort station (B245-111M) | 4 | CONSTRUCTION | 2010-03-28 | 2011-03-27 | 2013-09-02 | 2013-09-01
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208K11E | St. John's Recreation Center - comfort station (B245-111M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2011-03-28 | 2012-03-26 | 2013-09-02 | 2023-12-18
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208LIN2 | Lincoln Terrace Park - Brooklyn (B054-119M) | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208LIN2 | Lincoln Terrace Park - Brooklyn (B054-119M) | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208LIN2 | Lincoln Terrace Park - Brooklyn (B054-119M) | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208LIN2 | Lincoln Terrace Park - Brooklyn (B054-119M) | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208LIN2 | Lincoln Terrace Park - Brooklyn (B054-119M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208LTCS | Lincoln Terrace- Comfort Station B054-115M | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2015-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208LTCS | Lincoln Terrace- Comfort Station B054-115M | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2015-09-29 | 2015-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208LTCS | Lincoln Terrace- Comfort Station B054-115M | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2015-12-28 | 2016-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208LTCS | Lincoln Terrace- Comfort Station B054-115M | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208LTCS | Lincoln Terrace- Comfort Station B054-115M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2017-03-27 | 2024-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208SJFA | ST. John's Rec. Center: Fire Alarm Reconstruction | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208SJFA | ST. John's Rec. Center: Fire Alarm Reconstruction | 2 | DESIGN | 2019-12-28 | 2021-12-26 | 2019-12-28 | 2021-12-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208SJFA | ST. John's Rec. Center: Fire Alarm Reconstruction | 3 | BID/ REGISTER CONTRACT | 2021-12-27 | 2022-09-22 | 2021-12-27 | 2022-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208SJFA | ST. John's Rec. Center: Fire Alarm Reconstruction | 4 | CONSTRUCTION | 2022-09-23 | 2025-09-21 | 2022-09-23 | 2025-09-21
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208SJFA | ST. John's Rec. Center: Fire Alarm Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-09-22 | 2027-09-21 | 2025-09-22 | 2027-09-21
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208STFE | ST. JOHNS REC CENTER - OUTDOOR FITNESS EQUIPMENT (B245-118M) | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208STFE | ST. JOHNS REC CENTER - OUTDOOR FITNESS EQUIPMENT (B245-118M) | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208STFE | ST. JOHNS REC CENTER - OUTDOOR FITNESS EQUIPMENT (B245-118M) | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208STFE | ST. JOHNS REC CENTER - OUTDOOR FITNESS EQUIPMENT (B245-118M) | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208STFE | ST. JOHNS REC CENTER - OUTDOOR FITNESS EQUIPMENT (B245-118M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208STUD | CPI PH 1- Stroud Playground (B350-115M) | 1 | DEVELOP SCOPE | 2012-07-01 | 2012-09-28 | 2012-07-01 | 2012-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208STUD | CPI PH 1- Stroud Playground (B350-115M) | 2 | DESIGN | 2012-09-29 | 2012-12-27 | 2012-09-29 | 2012-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208STUD | CPI PH 1- Stroud Playground (B350-115M) | 3 | BID/ REGISTER CONTRACT | 2012-12-28 | 2013-03-27 | 2012-12-28 | 2013-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208STUD | CPI PH 1- Stroud Playground (B350-115M) | 4 | CONSTRUCTION | 2013-03-28 | 2014-03-27 | 2013-03-28 | 2014-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208STUD | CPI PH 1- Stroud Playground (B350-115M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-03-28 | 2015-03-27 | 2014-03-28 | 2022-05-25
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-209D017 | PARKSIDE (P.S. 92) PLAYGROUND (B267-109M) | 1 | DEVELOP SCOPE | 2006-07-01 | 2006-09-28 | 2007-07-01 | 2008-09-30
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-209D017 | PARKSIDE (P.S. 92) PLAYGROUND (B267-109M) | 2 | DESIGN | 2006-09-29 | 2006-12-27 | 2008-10-01 | 2009-05-20
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-209D017 | PARKSIDE (P.S. 92) PLAYGROUND (B267-109M) | 3 | BID/ REGISTER CONTRACT | 2006-12-28 | 2007-03-27 | 2009-08-26 | 2011-02-01
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-209D017 | PARKSIDE (P.S. 92) PLAYGROUND (B267-109M) | 4 | CONSTRUCTION | 2007-03-28 | 2008-03-26 | 2011-02-02 | 2011-02-01
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-209D017 | PARKSIDE (P.S. 92) PLAYGROUND (B267-109M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-27 | 2009-03-26 | 2011-02-02 | 2024-09-12
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-209WNGE | Wingate Park - Basketball Courts | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-209WNGE | Wingate Park - Basketball Courts | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2016-12-28 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-209WNGE | Wingate Park - Basketball Courts | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2017-12-28 | 2018-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-209WNGE | Wingate Park - Basketball Courts | 4 | CONSTRUCTION | 2018-09-24 | 2019-09-23 | 2018-09-24 | 2019-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-209WNGE | Wingate Park - Basketball Courts | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210245A | OWL'S HEAD PK - GREENWAY CONNECTOR B066-108M | 1 | DEVELOP SCOPE | 2007-07-01 | 2007-09-28 | 2007-07-01 | 2007-10-03
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210245A | OWL'S HEAD PK - GREENWAY CONNECTOR B066-108M | 2 | DESIGN | 2007-09-29 | 2007-12-27 | 2007-10-04 | 2008-10-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210245A | OWL'S HEAD PK - GREENWAY CONNECTOR B066-108M | 3 | BID/ REGISTER CONTRACT | 2007-12-28 | 2008-03-26 | 2009-03-02 | 2009-07-10
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210245A | OWL'S HEAD PK - GREENWAY CONNECTOR B066-108M | 4 | CONSTRUCTION | 2008-03-27 | 2009-03-26 | 2010-03-01 | 2010-12-09
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210245A | OWL'S HEAD PK - GREENWAY CONNECTOR B066-108M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2009-03-27 | 2010-03-26 | 2010-12-10 | 2024-12-09
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210973G | SHORE ROAD PK DUGOUTS RECONSTR, FLD 3 @ 76TH ST, B082A-105M | 1 | DEVELOP SCOPE | 2006-07-01 | 2006-09-28 | 2006-07-01 | 2006-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210973G | SHORE ROAD PK DUGOUTS RECONSTR, FLD 3 @ 76TH ST, B082A-105M | 2 | DESIGN | 2006-09-29 | 2006-12-27 | 2006-09-29 | 2006-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210973G | SHORE ROAD PK DUGOUTS RECONSTR, FLD 3 @ 76TH ST, B082A-105M | 3 | BID/ REGISTER CONTRACT | 2006-12-28 | 2007-03-27 | 2006-12-28 | 2007-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210973G | SHORE ROAD PK DUGOUTS RECONSTR, FLD 3 @ 76TH ST, B082A-105M | 4 | CONSTRUCTION | 2007-03-28 | 2008-03-26 | 2007-03-28 | 2008-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210973G | SHORE ROAD PK DUGOUTS RECONSTR, FLD 3 @ 76TH ST, B082A-105M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-27 | 2009-03-26 | 2008-03-27 | 2009-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210C040 | MCKINLEY PARK PATHS&LDSCPE B060-101M (FORMER B060-196) | 1 | DEVELOP SCOPE | 2020-07-01 | 2020-12-27 | 2020-07-01 | 2020-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210C040 | MCKINLEY PARK PATHS&LDSCPE B060-101M (FORMER B060-196) | 2 | DESIGN | 2020-12-28 | 2021-12-27 | 2020-12-28 | 2021-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210C040 | MCKINLEY PARK PATHS&LDSCPE B060-101M (FORMER B060-196) | 3 | BID/ REGISTER CONTRACT | 2021-12-28 | 2022-09-23 | 2021-12-28 | 2022-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210C040 | MCKINLEY PARK PATHS&LDSCPE B060-101M (FORMER B060-196) | 4 | CONSTRUCTION | 2022-09-24 | 2023-09-23 | 2022-09-24 | 2023-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210C040 | MCKINLEY PARK PATHS&LDSCPE B060-101M (FORMER B060-196) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-24 | 2024-09-22 | 2023-09-24 | 2024-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210D17T | SHORE ROAD PATHWAY BICYCLE PATH | 1 | DEVELOP SCOPE | 2010-07-01 | 2010-09-28 | 2010-07-01 | 2010-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210D17T | SHORE ROAD PATHWAY BICYCLE PATH | 2 | DESIGN | 2010-09-29 | 2010-12-27 | 2010-09-29 | 2010-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210D17T | SHORE ROAD PATHWAY BICYCLE PATH | 3 | BID/ REGISTER CONTRACT | 2010-12-28 | 2011-03-27 | 2010-12-28 | 2011-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210D17T | SHORE ROAD PATHWAY BICYCLE PATH | 4 | CONSTRUCTION | 2011-03-28 | 2012-03-26 | 2011-03-28 | 2012-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210D17T | SHORE ROAD PATHWAY BICYCLE PATH | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-03-27 | 2013-03-26 | 2012-03-27 | 2023-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210DBSF | Dyker Beach Park- Soccer Field B028-116M | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2015-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210DBSF | Dyker Beach Park- Soccer Field B028-116M | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2015-09-29 | 2015-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210DBSF | Dyker Beach Park- Soccer Field B028-116M | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2015-12-28 | 2016-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210DBSF | Dyker Beach Park- Soccer Field B028-116M | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210DBSF | Dyker Beach Park- Soccer Field B028-116M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2017-03-27 | 2020-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210DOG | Shore Park - Shore Park Dog Run | 1 | DEVELOP SCOPE | 2019-09-24 | 2020-03-21 | 2019-09-24 | 2020-03-21
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210DOG | Shore Park - Shore Park Dog Run | 2 | DESIGN | 2020-03-22 | 2021-03-21 | 2020-03-22 | 2021-03-21
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210DOG | Shore Park - Shore Park Dog Run | 3 | BID/ REGISTER CONTRACT | 2021-03-22 | 2021-12-16 | 2021-03-22 | 2021-12-16
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210DOG | Shore Park - Shore Park Dog Run | 4 | CONSTRUCTION | 2021-12-17 | 2022-12-16 | 2021-12-17 | 2022-12-16
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210DOG | Shore Park - Shore Park Dog Run | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-12-17 | 2023-12-16 | 2022-12-17 | 2023-12-16
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210FTHM | Ft. Hamilton Courts - RC of Bsktball & Tennis Cts -B192A | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210FTHM | Ft. Hamilton Courts - RC of Bsktball & Tennis Cts -B192A | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210FTHM | Ft. Hamilton Courts - RC of Bsktball & Tennis Cts -B192A | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210FTHM | Ft. Hamilton Courts - RC of Bsktball & Tennis Cts -B192A | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210FTHM | Ft. Hamilton Courts - RC of Bsktball & Tennis Cts -B192A | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210JCAR | John J. Carty Tennis Courts B210-116M | 1 | DEVELOP SCOPE | 2014-07-01 | 2014-09-28 | 2014-07-01 | 2015-10-16
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210JCAR | John J. Carty Tennis Courts B210-116M | 2 | DESIGN | 2014-09-29 | 2014-12-27 | 2015-10-17 | 2017-05-24
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210JCAR | John J. Carty Tennis Courts B210-116M | 3 | BID/ REGISTER CONTRACT | 2014-12-28 | 2015-03-27 | 2017-09-27 | 2018-05-25
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210JCAR | John J. Carty Tennis Courts B210-116M | 4 | CONSTRUCTION | 2015-03-28 | 2016-03-26 | 2018-07-11 | 2019-07-11
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210JCAR | John J. Carty Tennis Courts B210-116M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-27 | 2017-03-26 | 2019-07-12 | 2022-07-10
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210JJCP | JJ Carty Park - Renovation of Playground | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210JJCP | JJ Carty Park - Renovation of Playground | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210JJCP | JJ Carty Park - Renovation of Playground | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210JJCP | JJ Carty Park - Renovation of Playground | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210JJCP | JJ Carty Park - Renovation of Playground | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210OWLH | Owl's Head Park - Reconstruction of Basketball Courts | 1 | DEVELOP SCOPE | 2020-07-01 | 2020-12-27 | 2020-07-01 | 2020-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210OWLH | Owl's Head Park - Reconstruction of Basketball Courts | 2 | DESIGN | 2020-12-28 | 2021-12-27 | 2020-12-28 | 2021-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210OWLH | Owl's Head Park - Reconstruction of Basketball Courts | 3 | BID/ REGISTER CONTRACT | 2021-12-28 | 2022-09-23 | 2021-12-28 | 2022-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210OWLH | Owl's Head Park - Reconstruction of Basketball Courts | 4 | CONSTRUCTION | 2022-09-24 | 2023-09-23 | 2022-09-24 | 2023-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210OWLH | Owl's Head Park - Reconstruction of Basketball Courts | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-24 | 2024-09-22 | 2023-09-24 | 2024-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210P972 | OWL'S HEAD PARK COMFORT STATION RECONSTR; B066-102M-402M | 1 | DEVELOP SCOPE | 2001-07-01 | 2002-03-31 | 2001-07-01 | 2002-07-30
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210P972 | OWL'S HEAD PARK COMFORT STATION RECONSTR; B066-102M-402M | 2 | DESIGN | 2002-04-01 | 2003-03-27 | 2002-07-31 | 2003-05-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210P972 | OWL'S HEAD PARK COMFORT STATION RECONSTR; B066-102M-402M | 3 | BID/ REGISTER CONTRACT | 2003-03-28 | 2004-01-31 | 2003-06-05 | 2003-12-09
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210P972 | OWL'S HEAD PARK COMFORT STATION RECONSTR; B066-102M-402M | 4 | CONSTRUCTION | 2004-02-28 | 2005-02-26 | 2004-03-01 | 2006-10-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210P972 | OWL'S HEAD PARK COMFORT STATION RECONSTR; B066-102M-402M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2005-02-27 | 2006-02-26 | 2006-10-28 | 2007-12-06
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210RUPP | Russell Pedersen Playground Reconstruction | 1 | DEVELOP SCOPE | 2020-07-01 | 2020-12-27 | 2020-07-01 | 2020-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210RUPP | Russell Pedersen Playground Reconstruction | 2 | DESIGN | 2020-12-28 | 2021-12-27 | 2020-12-28 | 2021-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210RUPP | Russell Pedersen Playground Reconstruction | 3 | BID/ REGISTER CONTRACT | 2021-12-28 | 2022-09-23 | 2021-12-28 | 2022-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210RUPP | Russell Pedersen Playground Reconstruction | 4 | CONSTRUCTION | 2022-09-24 | 2023-09-23 | 2022-09-24 | 2023-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210RUPP | Russell Pedersen Playground Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-24 | 2024-09-22 | 2023-09-24 | 2024-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210SHCP | Shore Road Park - Path Reconstruction (B082-220M) | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210SHCP | Shore Road Park - Path Reconstruction (B082-220M) | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210SHCP | Shore Road Park - Path Reconstruction (B082-220M) | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210SHCP | Shore Road Park - Path Reconstruction (B082-220M) | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210SHCP | Shore Road Park - Path Reconstruction (B082-220M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2024-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210SHOR | SHORE ROAD PK - PERIMETER SIDEWALKS (B082A-110M) | 1 | DEVELOP SCOPE | 2010-07-01 | 2010-09-28 | 2010-07-01 | 2010-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210SHOR | SHORE ROAD PK - PERIMETER SIDEWALKS (B082A-110M) | 2 | DESIGN | 2010-09-29 | 2010-12-27 | 2010-09-29 | 2010-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210SHOR | SHORE ROAD PK - PERIMETER SIDEWALKS (B082A-110M) | 3 | BID/ REGISTER CONTRACT | 2010-12-28 | 2011-03-27 | 2010-12-28 | 2011-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210SHOR | SHORE ROAD PK - PERIMETER SIDEWALKS (B082A-110M) | 4 | CONSTRUCTION | 2011-03-28 | 2012-03-26 | 2011-03-28 | 2012-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210SHOR | SHORE ROAD PK - PERIMETER SIDEWALKS (B082A-110M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-03-27 | 2013-03-26 | 2012-03-27 | 2024-01-25
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210SHRD | Shore Road Pk- Rehab C/S -Field House B082-116M | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2013-06-30 | 2013-09-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210SHRD | Shore Road Pk- Rehab C/S -Field House B082-116M | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2013-09-28 | 2013-12-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210SHRD | Shore Road Pk- Rehab C/S -Field House B082-116M | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2013-12-27 | 2014-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210SHRD | Shore Road Pk- Rehab C/S -Field House B082-116M | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2014-03-27 | 2015-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210SHRD | Shore Road Pk- Rehab C/S -Field House B082-116M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2015-03-27 | 2022-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210SHRE | Shore Road park- Install. fence erosion contrl. B082 | 1 | DEVELOP SCOPE | 2014-07-01 | 2014-09-28 | 2014-07-01 | 2014-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210SHRE | Shore Road park- Install. fence erosion contrl. B082 | 2 | DESIGN | 2014-09-29 | 2014-12-27 | 2014-09-29 | 2014-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210SHRE | Shore Road park- Install. fence erosion contrl. B082 | 3 | BID/ REGISTER CONTRACT | 2014-12-28 | 2015-03-27 | 2014-12-28 | 2015-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210SHRE | Shore Road park- Install. fence erosion contrl. B082 | 4 | CONSTRUCTION | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2016-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210SHRE | Shore Road park- Install. fence erosion contrl. B082 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2021-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210SHRS | Shore Park & Parkway - Bike Path Surface Repair BG-715MA | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210SHRS | Shore Park & Parkway - Bike Path Surface Repair BG-715MA | 2 | DESIGN | 2017-12-28 | 2019-12-27 | 2017-12-28 | 2019-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210SHRS | Shore Park & Parkway - Bike Path Surface Repair BG-715MA | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210SHRS | Shore Park & Parkway - Bike Path Surface Repair BG-715MA | 4 | CONSTRUCTION | 2020-09-23 | 2022-09-22 | 2020-09-23 | 2022-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210SHRS | Shore Park & Parkway - Bike Path Surface Repair BG-715MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210VINP | Shore Park & Parkway Vinland Playground Recon. B082-320M | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210VINP | Shore Park & Parkway Vinland Playground Recon. B082-320M | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210VINP | Shore Park & Parkway Vinland Playground Recon. B082-320M | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210VINP | Shore Park & Parkway Vinland Playground Recon. B082-320M | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210VINP | Shore Park & Parkway Vinland Playground Recon. B082-320M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-211245E | SETH LOW PLAYGROUND B100-106M | 1 | DEVELOP SCOPE | 2006-07-01 | 2006-09-28 | 2006-07-01 | 2006-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-211245E | SETH LOW PLAYGROUND B100-106M | 2 | DESIGN | 2006-09-29 | 2006-12-27 | 2006-09-29 | 2006-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-211245E | SETH LOW PLAYGROUND B100-106M | 3 | BID/ REGISTER CONTRACT | 2006-12-28 | 2007-03-27 | 2006-12-28 | 2007-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-211245E | SETH LOW PLAYGROUND B100-106M | 4 | CONSTRUCTION | 2007-03-28 | 2008-03-26 | 2007-03-28 | 2008-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-211245E | SETH LOW PLAYGROUND B100-106M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-27 | 2009-03-26 | 2008-03-27 | 2022-06-04
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-211BBCH | BATH BEACH PARK - PH2 and PH3 (B164-119M) | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-211BBCH | BATH BEACH PARK - PH2 and PH3 (B164-119M) | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-211BBCH | BATH BEACH PARK - PH2 and PH3 (B164-119M) | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-211BBCH | BATH BEACH PARK - PH2 and PH3 (B164-119M) | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-211BBCH | BATH BEACH PARK - PH2 and PH3 (B164-119M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2024-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-211BNHT | Bensonhurst Park - B007-118M | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2015-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-211BNHT | Bensonhurst Park - B007-118M | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2015-09-29 | 2015-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-211BNHT | Bensonhurst Park - B007-118M | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2015-12-28 | 2016-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-211BNHT | Bensonhurst Park - B007-118M | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-211BNHT | Bensonhurst Park - B007-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2017-03-27 | 2021-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-211SGBG | Samuel Goldberg Triangle - B231 | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2015-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-211SGBG | Samuel Goldberg Triangle - B231 | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2015-09-29 | 2015-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-211SGBG | Samuel Goldberg Triangle - B231 | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2015-12-28 | 2016-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-211SGBG | Samuel Goldberg Triangle - B231 | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-211SGBG | Samuel Goldberg Triangle - B231 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2017-03-27 | 2018-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-212ALBE | Albemarle Playground - Resurface Soccer Field (B297-119M) | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-212ALBE | Albemarle Playground - Resurface Soccer Field (B297-119M) | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-212ALBE | Albemarle Playground - Resurface Soccer Field (B297-119M) | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-212ALBE | Albemarle Playground - Resurface Soccer Field (B297-119M) | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-212ALBE | Albemarle Playground - Resurface Soccer Field (B297-119M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-212C17F | Gravesend Park (B042-109M) | 1 | DEVELOP SCOPE | 2007-07-01 | 2007-09-28 | 2007-07-01 | 2007-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-212C17F | Gravesend Park (B042-109M) | 2 | DESIGN | 2007-09-29 | 2007-12-27 | 2007-09-29 | 2007-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-212C17F | Gravesend Park (B042-109M) | 3 | BID/ REGISTER CONTRACT | 2007-12-28 | 2008-03-26 | 2007-12-28 | 2008-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-212C17F | Gravesend Park (B042-109M) | 4 | CONSTRUCTION | 2008-03-27 | 2009-03-26 | 2008-03-27 | 2009-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-212C17F | Gravesend Park (B042-109M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2009-03-27 | 2010-03-26 | 2009-03-27 | 2022-10-18
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-212CLDM | Colonel David Marcus playground - CS B128-115M | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2013-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-212CLDM | Colonel David Marcus playground - CS B128-115M | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2013-09-29 | 2013-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-212CLDM | Colonel David Marcus playground - CS B128-115M | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2013-12-28 | 2014-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-212CLDM | Colonel David Marcus playground - CS B128-115M | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2014-03-28 | 2015-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-212CLDM | Colonel David Marcus playground - CS B128-115M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2022-03-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-212D017 | FRIENDS FIELD PARK RECONSTR PRTN INCL PLGD B372-104M | 1 | DEVELOP SCOPE | 2003-07-01 | 2003-09-28 | 2003-07-01 | 2003-11-16
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-212D017 | FRIENDS FIELD PARK RECONSTR PRTN INCL PLGD B372-104M | 2 | DESIGN | 2003-09-29 | 2003-12-31 | 2003-11-17 | 2004-06-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-212D017 | FRIENDS FIELD PARK RECONSTR PRTN INCL PLGD B372-104M | 3 | BID/ REGISTER CONTRACT | 2004-01-01 | 2004-04-30 | 2004-11-29 | 2005-03-17
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-212D017 | FRIENDS FIELD PARK RECONSTR PRTN INCL PLGD B372-104M | 4 | CONSTRUCTION | 2004-05-31 | 2004-11-30 | 2005-04-25 | 2006-04-14
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-212D017 | FRIENDS FIELD PARK RECONSTR PRTN INCL PLGD B372-104M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2004-12-01 | 2005-05-30 | 2006-04-15 | 2008-11-14
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-212D17N | OCEAN PARKWAY MALLS -MALL RENOVATIONS B065-112M | 1 | DEVELOP SCOPE | 2010-07-01 | 2010-09-28 | 2010-07-01 | 2010-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-212D17N | OCEAN PARKWAY MALLS -MALL RENOVATIONS B065-112M | 2 | DESIGN | 2010-09-29 | 2010-12-27 | 2010-09-29 | 2010-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-212D17N | OCEAN PARKWAY MALLS -MALL RENOVATIONS B065-112M | 3 | BID/ REGISTER CONTRACT | 2010-12-28 | 2011-03-27 | 2010-12-28 | 2011-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-212D17N | OCEAN PARKWAY MALLS -MALL RENOVATIONS B065-112M | 4 | CONSTRUCTION | 2011-03-28 | 2012-03-26 | 2011-03-28 | 2012-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-212D17N | OCEAN PARKWAY MALLS -MALL RENOVATIONS B065-112M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-03-27 | 2013-03-26 | 2012-03-27 | 2022-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-212DOME | Dome Playground - phase I (B151-112M) | 1 | DEVELOP SCOPE | 2010-07-01 | 2010-09-28 | 2010-07-01 | 2010-11-10
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-212DOME | Dome Playground - phase I (B151-112M) | 2 | DESIGN | 2010-09-29 | 2010-12-27 | 2010-11-11 | 2014-05-29
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-212DOME | Dome Playground - phase I (B151-112M) | 3 | BID/ REGISTER CONTRACT | 2010-12-28 | 2011-03-27 | 2014-05-30 | 2014-08-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-212DOME | Dome Playground - phase I (B151-112M) | 4 | CONSTRUCTION | 2011-03-28 | 2012-03-26 | 2014-08-28 | 2015-08-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-212DOME | Dome Playground - phase I (B151-112M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-03-27 | 2013-03-26 | 2015-08-28 | 2023-04-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-212FRFD | Friends Field - B372-116M | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2015-09-18
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-212FRFD | Friends Field - B372-116M | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2015-09-19 | 2017-06-16
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-212FRFD | Friends Field - B372-116M | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2017-10-03 | 2018-06-25
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-212FRFD | Friends Field - B372-116M | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2018-09-20 | 2019-09-25
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-212FRFD | Friends Field - B372-116M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2019-09-26 | 2022-09-25
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-212GRVD | Gravesend Pk - RC parkhouse B042-112M | 1 | DEVELOP SCOPE | 2011-07-01 | 2011-09-28 | 2011-07-01 | 2011-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-212GRVD | Gravesend Pk - RC parkhouse B042-112M | 2 | DESIGN | 2011-09-29 | 2011-12-27 | 2011-09-29 | 2011-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-212GRVD | Gravesend Pk - RC parkhouse B042-112M | 3 | BID/ REGISTER CONTRACT | 2011-12-28 | 2012-03-26 | 2011-12-28 | 2012-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-212GRVD | Gravesend Pk - RC parkhouse B042-112M | 4 | CONSTRUCTION | 2012-03-27 | 2013-03-26 | 2017-04-17 | 2018-04-17
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-212GRVD | Gravesend Pk - RC parkhouse B042-112M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-03-27 | 2014-03-26 | 2018-04-18 | 2023-04-17
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213ALAE | Asser Levy Park - Adult Exercise Equipment (B080-118M) | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213ALAE | Asser Levy Park - Adult Exercise Equipment (B080-118M) | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213ALAE | Asser Levy Park - Adult Exercise Equipment (B080-118M) | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213ALAE | Asser Levy Park - Adult Exercise Equipment (B080-118M) | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213ALAE | Asser Levy Park - Adult Exercise Equipment (B080-118M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2024-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213ALVY | Asser Levy Park - B080 | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2015-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213ALVY | Asser Levy Park - B080 | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2015-09-29 | 2015-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213ALVY | Asser Levy Park - B080 | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2015-12-28 | 2016-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213ALVY | Asser Levy Park - B080 | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213ALVY | Asser Levy Park - B080 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2017-03-27 | 2023-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213BABI | BABI YAR Triangle - Reconstruction | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213BABI | BABI YAR Triangle - Reconstruction | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213BABI | BABI YAR Triangle - Reconstruction | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213BABI | BABI YAR Triangle - Reconstruction | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213BABI | BABI YAR Triangle - Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2024-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213BOIL | ABE STARK BOILERS AND CHILLERS (B169-111M) | 1 | DEVELOP SCOPE | 2010-07-01 | 2010-09-28 | 2010-07-01 | 2010-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213BOIL | ABE STARK BOILERS AND CHILLERS (B169-111M) | 2 | DESIGN | 2010-09-29 | 2010-12-27 | 2010-09-29 | 2010-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213BOIL | ABE STARK BOILERS AND CHILLERS (B169-111M) | 3 | BID/ REGISTER CONTRACT | 2010-12-28 | 2011-03-27 | 2010-12-28 | 2011-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213BOIL | ABE STARK BOILERS AND CHILLERS (B169-111M) | 4 | CONSTRUCTION | 2011-03-28 | 2012-03-26 | 2011-03-28 | 2012-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213BOIL | ABE STARK BOILERS AND CHILLERS (B169-111M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-03-27 | 2013-03-26 | 2012-03-27 | 2024-08-08
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213K11B | CONEY ISLAMD BWA;LK MISC RC W37-CORBIN B169-100MA | 1 | DEVELOP SCOPE | 2006-07-01 | 2006-09-28 | 2006-07-01 | 2006-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213K11B | CONEY ISLAMD BWA;LK MISC RC W37-CORBIN B169-100MA | 2 | DESIGN | 2006-09-29 | 2006-12-27 | 2006-09-29 | 2006-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213K11B | CONEY ISLAMD BWA;LK MISC RC W37-CORBIN B169-100MA | 3 | BID/ REGISTER CONTRACT | 2006-12-28 | 2007-03-27 | 2006-12-28 | 2007-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213K11B | CONEY ISLAMD BWA;LK MISC RC W37-CORBIN B169-100MA | 4 | CONSTRUCTION | 2007-03-28 | 2008-03-26 | 2007-03-28 | 2008-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213K11B | CONEY ISLAMD BWA;LK MISC RC W37-CORBIN B169-100MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-27 | 2009-03-26 | 2008-03-27 | 2022-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213SCRN | Scarangella Park C/S CONS B106-117M | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2015-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213SCRN | Scarangella Park C/S CONS B106-117M | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2015-09-29 | 2015-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213SCRN | Scarangella Park C/S CONS B106-117M | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2015-12-28 | 2016-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213SCRN | Scarangella Park C/S CONS B106-117M | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213SCRN | Scarangella Park C/S CONS B106-117M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2017-03-27 | 2024-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213SNPK | Scarangella Park - Reconstruction of Playground B106A-120M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213SNPK | Scarangella Park - Reconstruction of Playground B106A-120M | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213SNPK | Scarangella Park - Reconstruction of Playground B106A-120M | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213SNPK | Scarangella Park - Reconstruction of Playground B106A-120M | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213SNPK | Scarangella Park - Reconstruction of Playground B106A-120M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2024-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213SURF | SURF PLAYGROUND - PLAYGROUND RENOVATION (B315-118M) | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213SURF | SURF PLAYGROUND - PLAYGROUND RENOVATION (B315-118M) | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213SURF | SURF PLAYGROUND - PLAYGROUND RENOVATION (B315-118M) | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213SURF | SURF PLAYGROUND - PLAYGROUND RENOVATION (B315-118M) | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213SURF | SURF PLAYGROUND - PLAYGROUND RENOVATION (B315-118M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213WEST | West Playground CS B252-115M | 1 | DEVELOP SCOPE | 2014-07-01 | 2014-09-28 | 2014-07-01 | 2014-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213WEST | West Playground CS B252-115M | 2 | DESIGN | 2014-09-29 | 2014-12-27 | 2014-09-29 | 2014-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213WEST | West Playground CS B252-115M | 3 | BID/ REGISTER CONTRACT | 2014-12-28 | 2015-03-27 | 2014-12-28 | 2015-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213WEST | West Playground CS B252-115M | 4 | CONSTRUCTION | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2016-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213WEST | West Playground CS B252-115M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2024-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214ANDP | Andries Playground - Phase 1 & 2 Reconstruction | 1 | DEVELOP SCOPE | 2020-07-01 | 2020-12-27 | 2020-07-01 | 2020-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214ANDP | Andries Playground - Phase 1 & 2 Reconstruction | 2 | DESIGN | 2020-12-28 | 2021-12-27 | 2020-12-28 | 2021-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214ANDP | Andries Playground - Phase 1 & 2 Reconstruction | 3 | BID/ REGISTER CONTRACT | 2021-12-28 | 2022-09-23 | 2021-12-28 | 2022-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214ANDP | Andries Playground - Phase 1 & 2 Reconstruction | 4 | CONSTRUCTION | 2022-09-24 | 2023-09-23 | 2022-09-24 | 2023-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214ANDP | Andries Playground - Phase 1 & 2 Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-24 | 2024-09-22 | 2023-09-24 | 2024-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214CAVE | CATON AVE PERIMSIDEW PAR PLACE-ARGYLE@PARGDS NYSMM B068-105M | 3 | BID/ REGISTER CONTRACT | 2006-12-28 | 2007-03-27 | 2006-12-28 | 2007-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214CAVE | CATON AVE PERIMSIDEW PAR PLACE-ARGYLE@PARGDS NYSMM B068-105M | 4 | CONSTRUCTION | 2007-03-28 | 2008-03-26 | 2007-03-28 | 2008-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214CAVE | CATON AVE PERIMSIDEW PAR PLACE-ARGYLE@PARGDS NYSMM B068-105M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-27 | 2009-03-26 | 2008-03-27 | 2011-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214K001 | PROSPECT PARK PARADE GROUNDS BLFLDS RENOV B068-101M | 1 | DEVELOP SCOPE | 2000-07-01 | 2000-09-05 | 2000-07-01 | 2000-10-05
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214K001 | PROSPECT PARK PARADE GROUNDS BLFLDS RENOV B068-101M | 2 | DESIGN | 2000-09-06 | 2001-02-14 | 2001-01-21 | 2001-02-14
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214K001 | PROSPECT PARK PARADE GROUNDS BLFLDS RENOV B068-101M | 3 | BID/ REGISTER CONTRACT | 2001-02-21 | 2001-07-02 | 2001-03-12 | 2001-07-02
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214K001 | PROSPECT PARK PARADE GROUNDS BLFLDS RENOV B068-101M | 4 | CONSTRUCTION | 2001-08-06 | 2003-09-15 | 2001-08-06 | 2004-03-25
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214K001 | PROSPECT PARK PARADE GROUNDS BLFLDS RENOV B068-101M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2003-09-16 | 2004-09-16 | 2004-03-26 | 2005-04-15
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214KNDR | PPA-Kensington Dog Run in the Parade Grounds (B068-117M) | 2 | DESIGN | 2016-12-28 | 2018-06-25 | 2016-12-28 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214KNDR | PPA-Kensington Dog Run in the Parade Grounds (B068-117M) | 3 | BID/ REGISTER CONTRACT | 2018-06-26 | 2019-03-22 | 2017-12-28 | 2018-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214KNDR | PPA-Kensington Dog Run in the Parade Grounds (B068-117M) | 4 | CONSTRUCTION | 2019-03-23 | 2020-09-17 | 2018-09-24 | 2019-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214KNDR | PPA-Kensington Dog Run in the Parade Grounds (B068-117M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-18 | 2021-09-17 | 2019-09-24 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214KOLB | KOLBERT PLAYGROUND - RC (B150-115M) | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2013-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214KOLB | KOLBERT PLAYGROUND - RC (B150-115M) | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2013-09-29 | 2013-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214KOLB | KOLBERT PLAYGROUND - RC (B150-115M) | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2013-12-28 | 2014-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214KOLB | KOLBERT PLAYGROUND - RC (B150-115M) | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2014-03-28 | 2015-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214KOLB | KOLBERT PLAYGROUND - RC (B150-115M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2023-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214KPKP | Kolbert Park RC Perimeter B150 | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214KPKP | Kolbert Park RC Perimeter B150 | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214KPKP | Kolbert Park RC Perimeter B150 | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214KPKP | Kolbert Park RC Perimeter B150 | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214KPKP | Kolbert Park RC Perimeter B150 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214LTFN | Lt. Federico Navaez Tot Lot- RC B397-117M | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-10-19
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214LTFN | Lt. Federico Navaez Tot Lot- RC B397-117M | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2016-10-20 | 2017-11-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214LTFN | Lt. Federico Navaez Tot Lot- RC B397-117M | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2018-03-16 | 2018-12-13
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214LTFN | Lt. Federico Navaez Tot Lot- RC B397-117M | 4 | CONSTRUCTION | 2018-09-24 | 2019-09-23 | 2019-04-29 | 2019-12-13
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214LTFN | Lt. Federico Navaez Tot Lot- RC B397-117M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-24 | 2020-09-22 | 2019-12-14 | 2023-12-12
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214PARK | CD #44- New Park /Playground | 1 | DEVELOP SCOPE | 2020-07-01 | 2020-12-27 | 2020-07-01 | 2020-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214PARK | CD #44- New Park /Playground | 2 | DESIGN | 2020-12-28 | 2021-12-27 | 2020-12-28 | 2021-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214PARK | CD #44- New Park /Playground | 3 | BID/ REGISTER CONTRACT | 2021-12-28 | 2022-09-23 | 2021-12-28 | 2022-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214PARK | CD #44- New Park /Playground | 4 | CONSTRUCTION | 2022-09-24 | 2023-09-23 | 2022-09-24 | 2023-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214PARK | CD #44- New Park /Playground | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-24 | 2024-09-22 | 2023-09-24 | 2024-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214RIDE | PPA - GALLOPNYC- RIDING RING IN PROSP. PK | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2013-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214RIDE | PPA - GALLOPNYC- RIDING RING IN PROSP. PK | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2013-09-29 | 2013-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214RIDE | PPA - GALLOPNYC- RIDING RING IN PROSP. PK | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2013-12-28 | 2014-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214RIDE | PPA - GALLOPNYC- RIDING RING IN PROSP. PK | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2014-03-28 | 2015-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214RIDE | PPA - GALLOPNYC- RIDING RING IN PROSP. PK | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2022-10-20
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214UMMA | Umma Park & Plg Reconstruction | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214UMMA | Umma Park & Plg Reconstruction | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214UMMA | Umma Park & Plg Reconstruction | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214UMMA | Umma Park & Plg Reconstruction | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214UMMA | Umma Park & Plg Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215BBPG | BILL BROWN PLAYGROUND FLDHSE CMFT ST. FY'10 B109-112M | 1 | DEVELOP SCOPE | 2009-07-01 | 2009-09-28 | 2009-07-01 | 2013-10-02
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215BBPG | BILL BROWN PLAYGROUND FLDHSE CMFT ST. FY'10 B109-112M | 2 | DESIGN | 2009-09-29 | 2009-12-27 | 2012-11-28 | 2013-02-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215BBPG | BILL BROWN PLAYGROUND FLDHSE CMFT ST. FY'10 B109-112M | 3 | BID/ REGISTER CONTRACT | 2009-12-28 | 2010-03-27 | 2013-03-01 | 2013-09-01
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215BBPG | BILL BROWN PLAYGROUND FLDHSE CMFT ST. FY'10 B109-112M | 4 | CONSTRUCTION | 2010-03-28 | 2011-03-27 | 2013-10-01 | 2014-10-01
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215BBPG | BILL BROWN PLAYGROUND FLDHSE CMFT ST. FY'10 B109-112M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2011-03-28 | 2012-03-26 | 2014-10-02 | 2022-06-12
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215C17N | NORTON PLGD COMF STAT -B208-110M | 1 | DEVELOP SCOPE | 2006-07-01 | 2006-09-28 | 2006-07-01 | 2010-01-19
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215C17N | NORTON PLGD COMF STAT -B208-110M | 2 | DESIGN | 2006-09-29 | 2006-12-27 | 2010-01-20 | 2010-04-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215C17N | NORTON PLGD COMF STAT -B208-110M | 3 | BID/ REGISTER CONTRACT | 2006-12-28 | 2007-03-27 | 2010-05-24 | 2011-05-11
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215C17N | NORTON PLGD COMF STAT -B208-110M | 4 | CONSTRUCTION | 2007-03-28 | 2008-03-26 | 2011-06-15 | 2012-04-01
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215C17N | NORTON PLGD COMF STAT -B208-110M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-27 | 2009-03-26 | 2012-04-02 | 2013-05-01
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215HCPL | HOMECREST PLAYGROUND: RECONSTRUCT PLAYGROUND (B166B-118M) | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215HCPL | HOMECREST PLAYGROUND: RECONSTRUCT PLAYGROUND (B166B-118M) | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2016-12-28 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215HCPL | HOMECREST PLAYGROUND: RECONSTRUCT PLAYGROUND (B166B-118M) | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2017-12-28 | 2018-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215HCPL | HOMECREST PLAYGROUND: RECONSTRUCT PLAYGROUND (B166B-118M) | 4 | CONSTRUCTION | 2018-09-24 | 2019-09-23 | 2018-09-24 | 2019-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215HCPL | HOMECREST PLAYGROUND: RECONSTRUCT PLAYGROUND (B166B-118M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215KELL | Kelly Park Playground - Recon. of Playground (B051-120M) | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215KELL | Kelly Park Playground - Recon. of Playground (B051-120M) | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215KELL | Kelly Park Playground - Recon. of Playground (B051-120M) | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215KELL | Kelly Park Playground - Recon. of Playground (B051-120M) | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215KELL | Kelly Park Playground - Recon. of Playground (B051-120M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2025-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215KLCS | KELLY PARK COMFORT STATION | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215KLCS | KELLY PARK COMFORT STATION | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215KLCS | KELLY PARK COMFORT STATION | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215KLCS | KELLY PARK COMFORT STATION | 4 | CONSTRUCTION | 2021-09-23 | 2023-03-21 | 2021-09-23 | 2023-03-21
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215KLCS | KELLY PARK COMFORT STATION | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-03-22 | 2024-03-20 | 2023-03-22 | 2024-03-20
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215KLLY | Kelly Playground - Renovate | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215KLLY | Kelly Playground - Renovate | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215KLLY | Kelly Playground - Renovate | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215KLLY | Kelly Playground - Renovate | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215KLLY | Kelly Playground - Renovate | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215MBGD | MANHATTAN BCH. COMM. GARDEN & DOG RUN (B251-117M) | 1 | DEVELOP SCOPE | 2012-07-01 | 2012-09-28 | 2012-07-01 | 2012-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215MBGD | MANHATTAN BCH. COMM. GARDEN & DOG RUN (B251-117M) | 2 | DESIGN | 2012-09-29 | 2012-12-27 | 2012-09-29 | 2012-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215MBGD | MANHATTAN BCH. COMM. GARDEN & DOG RUN (B251-117M) | 3 | BID/ REGISTER CONTRACT | 2012-12-28 | 2013-03-27 | 2012-12-28 | 2013-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215MBGD | MANHATTAN BCH. COMM. GARDEN & DOG RUN (B251-117M) | 4 | CONSTRUCTION | 2013-03-28 | 2014-03-27 | 2013-03-28 | 2014-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215MBGD | MANHATTAN BCH. COMM. GARDEN & DOG RUN (B251-117M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-03-28 | 2015-03-27 | 2014-03-28 | 2021-04-18
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215MBP2 | Manhattan Beach Park - Ctr Promenade & Beach Entryway Recons | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215MBP2 | Manhattan Beach Park - Ctr Promenade & Beach Entryway Recons | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215MBP2 | Manhattan Beach Park - Ctr Promenade & Beach Entryway Recons | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215MBP2 | Manhattan Beach Park - Ctr Promenade & Beach Entryway Recons | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215MBP2 | Manhattan Beach Park - Ctr Promenade & Beach Entryway Recons | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215MBTC | Manhattan Beach Park:Tennis Courts New Drainage/Resurfacing | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215MBTC | Manhattan Beach Park:Tennis Courts New Drainage/Resurfacing | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215MBTC | Manhattan Beach Park:Tennis Courts New Drainage/Resurfacing | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215MBTC | Manhattan Beach Park:Tennis Courts New Drainage/Resurfacing | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215MBTC | Manhattan Beach Park:Tennis Courts New Drainage/Resurfacing | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215MCDD | McDonald Playground - RC Play Equipment Area B244-118M | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2015-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215MCDD | McDonald Playground - RC Play Equipment Area B244-118M | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2015-09-29 | 2015-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215MCDD | McDonald Playground - RC Play Equipment Area B244-118M | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2015-12-28 | 2016-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215MCDD | McDonald Playground - RC Play Equipment Area B244-118M | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215MCDD | McDonald Playground - RC Play Equipment Area B244-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2017-03-27 | 2024-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215MELL | MELLET PLAYGROUND- RECONSTRUCT PLAYGROUND (B197-118M) | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215MELL | MELLET PLAYGROUND- RECONSTRUCT PLAYGROUND (B197-118M) | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215MELL | MELLET PLAYGROUND- RECONSTRUCT PLAYGROUND (B197-118M) | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215MELL | MELLET PLAYGROUND- RECONSTRUCT PLAYGROUND (B197-118M) | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215MELL | MELLET PLAYGROUND- RECONSTRUCT PLAYGROUND (B197-118M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215MHAT | Manhattan Beach Park B251-115M | 1 | DEVELOP SCOPE | 2014-07-01 | 2014-09-28 | 2014-07-01 | 2015-02-17
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215MHAT | Manhattan Beach Park B251-115M | 2 | DESIGN | 2014-09-29 | 2014-12-27 | 2015-02-18 | 2016-03-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215MHAT | Manhattan Beach Park B251-115M | 3 | BID/ REGISTER CONTRACT | 2014-12-28 | 2015-03-27 | 2016-06-27 | 2017-01-25
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215MHAT | Manhattan Beach Park B251-115M | 4 | CONSTRUCTION | 2015-03-28 | 2016-03-26 | 2017-04-17 | 2018-04-09
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215MHAT | Manhattan Beach Park B251-115M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-27 | 2017-03-26 | 2018-04-10 | 2022-04-09
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215MHBP | Manhattan Beach promenade (B251-217M) | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215MHBP | Manhattan Beach promenade (B251-217M) | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2016-12-28 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215MHBP | Manhattan Beach promenade (B251-217M) | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2017-12-28 | 2018-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215MHBP | Manhattan Beach promenade (B251-217M) | 4 | CONSTRUCTION | 2018-09-24 | 2019-09-23 | 2018-09-24 | 2019-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215MHBP | Manhattan Beach promenade (B251-217M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215PB15 | EMMONS AVENUE SIDEWALKS & SHEEPSHEAD PIER RCNSTR NYSMMGRANTS | 1 | DEVELOP SCOPE | 2007-07-01 | 2007-09-28 | 2007-07-01 | 2008-05-20
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215PB15 | EMMONS AVENUE SIDEWALKS & SHEEPSHEAD PIER RCNSTR NYSMMGRANTS | 2 | DESIGN | 2007-09-29 | 2007-12-27 | 2008-05-21 | 2008-09-11
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215PB15 | EMMONS AVENUE SIDEWALKS & SHEEPSHEAD PIER RCNSTR NYSMMGRANTS | 3 | BID/ REGISTER CONTRACT | 2007-12-28 | 2008-03-26 | 2008-09-12 | 2008-09-11
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215PB15 | EMMONS AVENUE SIDEWALKS & SHEEPSHEAD PIER RCNSTR NYSMMGRANTS | 4 | CONSTRUCTION | 2008-03-27 | 2009-03-26 | 2008-09-12 | 2008-09-11
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215PB15 | EMMONS AVENUE SIDEWALKS & SHEEPSHEAD PIER RCNSTR NYSMMGRANTS | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2009-03-27 | 2010-03-26 | 2008-09-12 | 2021-05-17
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215PIER | SHEEPSHEAD BAY PIERS B393-118M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215PIER | SHEEPSHEAD BAY PIERS B393-118M | 2 | DESIGN | 2017-12-28 | 2019-12-27 | 2017-12-28 | 2019-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215PIER | SHEEPSHEAD BAY PIERS B393-118M | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215PIER | SHEEPSHEAD BAY PIERS B393-118M | 4 | CONSTRUCTION | 2020-09-23 | 2022-09-22 | 2020-09-23 | 2022-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215PIER | SHEEPSHEAD BAY PIERS B393-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216BHIP | BETSY HEAD - IMAGINATION PLGD CS B008 | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216BHIP | BETSY HEAD - IMAGINATION PLGD CS B008 | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2016-12-28 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216BHIP | BETSY HEAD - IMAGINATION PLGD CS B008 | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2017-12-28 | 2018-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216BHIP | BETSY HEAD - IMAGINATION PLGD CS B008 | 4 | CONSTRUCTION | 2018-09-24 | 2020-03-21 | 2018-09-24 | 2020-03-21
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216BHIP | BETSY HEAD - IMAGINATION PLGD CS B008 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-03-22 | 2021-03-21 | 2020-03-22 | 2021-03-21
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216BRWN | BROWNSVILLE RECREATION CENTER (B270-114M) | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2013-09-29 | 2013-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216BRWN | BROWNSVILLE RECREATION CENTER (B270-114M) | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2013-12-28 | 2014-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216BRWN | BROWNSVILLE RECREATION CENTER (B270-114M) | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2014-03-28 | 2015-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216BRWN | BROWNSVILLE RECREATION CENTER (B270-114M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2019-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216CHES | Chester Park - Playground Renovation Phase 1 | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216CHES | Chester Park - Playground Renovation Phase 1 | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216CHES | Chester Park - Playground Renovation Phase 1 | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216CHES | Chester Park - Playground Renovation Phase 1 | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216CHES | Chester Park - Playground Renovation Phase 1 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216D017 | MARION ST E OF HOPKINSON AVE PLGD, RCNSTR PORTION, B110-104M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2005-03-28 | 2006-03-27 | 2005-03-28 | 2006-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216K11A | KINGSBOROUGH (PACIFIC) PLGD RCNSTR PRTN B153-100M | 2 | DESIGN | 2006-09-29 | 2006-12-27 | 2006-09-29 | 2006-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216K11A | KINGSBOROUGH (PACIFIC) PLGD RCNSTR PRTN B153-100M | 3 | BID/ REGISTER CONTRACT | 2006-12-28 | 2007-03-27 | 2006-12-28 | 2007-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216K11A | KINGSBOROUGH (PACIFIC) PLGD RCNSTR PRTN B153-100M | 4 | CONSTRUCTION | 2007-03-28 | 2008-03-26 | 2007-03-28 | 2008-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216K11A | KINGSBOROUGH (PACIFIC) PLGD RCNSTR PRTN B153-100M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-27 | 2009-03-26 | 2008-03-27 | 2009-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216OCAN | Ocean Hill Playground - Brooklyn | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216OCAN | Ocean Hill Playground - Brooklyn | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216OCAN | Ocean Hill Playground - Brooklyn | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216OCAN | Ocean Hill Playground - Brooklyn | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216OCAN | Ocean Hill Playground - Brooklyn | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216OSBN | Osborn Playground - Park Renovation (B343-119M) | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216OSBN | Osborn Playground - Park Renovation (B343-119M) | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216OSBN | Osborn Playground - Park Renovation (B343-119M) | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216OSBN | Osborn Playground - Park Renovation (B343-119M) | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216OSBN | Osborn Playground - Park Renovation (B343-119M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216OSPL | Osborn Playground - Phase 2 Reconstruction | 1 | DEVELOP SCOPE | 2020-07-01 | 2020-12-27 | 2020-07-01 | 2020-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216OSPL | Osborn Playground - Phase 2 Reconstruction | 2 | DESIGN | 2020-12-28 | 2021-12-27 | 2020-12-28 | 2021-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216OSPL | Osborn Playground - Phase 2 Reconstruction | 3 | BID/ REGISTER CONTRACT | 2021-12-28 | 2022-09-23 | 2021-12-28 | 2022-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216OSPL | Osborn Playground - Phase 2 Reconstruction | 4 | CONSTRUCTION | 2022-09-24 | 2023-09-23 | 2022-09-24 | 2023-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216OSPL | Osborn Playground - Phase 2 Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-24 | 2024-09-22 | 2023-09-24 | 2024-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216PS25 | PS 125 Playground - Brooklyn | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216PS25 | PS 125 Playground - Brooklyn | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216PS25 | PS 125 Playground - Brooklyn | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216PS25 | PS 125 Playground - Brooklyn | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216PS25 | PS 125 Playground - Brooklyn | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217AQBO | Paerdegat Aquatic Center Boiler Reconstruction | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217AQBO | Paerdegat Aquatic Center Boiler Reconstruction | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217AQBO | Paerdegat Aquatic Center Boiler Reconstruction | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217AQBO | Paerdegat Aquatic Center Boiler Reconstruction | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217AQBO | Paerdegat Aquatic Center Boiler Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217C17F | HARRY MAZE MEMORIAL PARK RECONSTR PLGD AREA, B285-103M | 1 | DEVELOP SCOPE | 2002-07-01 | 2002-11-01 | 2002-07-01 | 2002-11-01
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217C17F | HARRY MAZE MEMORIAL PARK RECONSTR PLGD AREA, B285-103M | 2 | DESIGN | 2002-11-02 | 2003-03-17 | 2002-11-02 | 2003-03-17
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217C17F | HARRY MAZE MEMORIAL PARK RECONSTR PLGD AREA, B285-103M | 3 | BID/ REGISTER CONTRACT | 2003-03-18 | 2004-01-31 | 2003-04-17 | 2004-02-09
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217C17F | HARRY MAZE MEMORIAL PARK RECONSTR PLGD AREA, B285-103M | 4 | CONSTRUCTION | 2004-03-05 | 2004-11-29 | 2004-03-22 | 2005-05-19
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217C17F | HARRY MAZE MEMORIAL PARK RECONSTR PLGD AREA, B285-103M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2004-11-30 | 2005-11-29 | 2005-05-20 | 2022-05-24
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217C17H | WYCKOFF HOUSE PARK RECONSTR, B376-102MA1 & B376-104M OMBP | 1 | DEVELOP SCOPE | 2001-07-01 | 2002-04-14 | 2001-07-01 | 2003-12-24
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217C17H | WYCKOFF HOUSE PARK RECONSTR, B376-102MA1 & B376-104M OMBP | 2 | DESIGN | 2002-04-15 | 2003-06-04 | 2003-12-25 | 2003-12-24
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217C17H | WYCKOFF HOUSE PARK RECONSTR, B376-102MA1 & B376-104M OMBP | 3 | BID/ REGISTER CONTRACT | 2003-06-05 | 2004-01-31 | 2003-12-25 | 2003-12-24
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217C17H | WYCKOFF HOUSE PARK RECONSTR, B376-102MA1 & B376-104M OMBP | 4 | CONSTRUCTION | 2004-03-30 | 2004-12-24 | 2004-03-30 | 2004-12-24
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217C17H | WYCKOFF HOUSE PARK RECONSTR, B376-102MA1 & B376-104M OMBP | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2004-12-25 | 2005-12-24 | 2004-12-25 | 2022-12-24
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217D017 | WYCKOFF HOUSE PARK CULT. EDUC. COMPLX B376-113M | 1 | DEVELOP SCOPE | 2003-10-05 | 2004-01-02 | 2003-10-05 | 2008-08-18
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217D017 | WYCKOFF HOUSE PARK CULT. EDUC. COMPLX B376-113M | 2 | DESIGN | 2004-01-03 | 2004-04-01 | 2008-08-19 | 2009-09-14
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217D017 | WYCKOFF HOUSE PARK CULT. EDUC. COMPLX B376-113M | 3 | BID/ REGISTER CONTRACT | 2004-04-02 | 2004-06-30 | 2009-06-27 | 2009-09-14
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217D017 | WYCKOFF HOUSE PARK CULT. EDUC. COMPLX B376-113M | 4 | CONSTRUCTION | 2004-07-31 | 2005-07-30 | 2004-07-31 | 2005-07-30
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217D017 | WYCKOFF HOUSE PARK CULT. EDUC. COMPLX B376-113M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2005-07-31 | 2006-07-30 | 2005-07-31 | 2024-07-30
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217NOST | Nostrand Playground - B250-117M | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217NOST | Nostrand Playground - B250-117M | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2016-12-28 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217NOST | Nostrand Playground - B250-117M | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2017-12-28 | 2018-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217NOST | Nostrand Playground - B250-117M | 4 | CONSTRUCTION | 2018-09-24 | 2019-09-23 | 2018-09-24 | 2019-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217NOST | Nostrand Playground - B250-117M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2023-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217PAER | PAERDEGAT PK- RECON. BSKT BALL, SIDEWALKS, LIGHTS, B218-112M | 1 | DEVELOP SCOPE | 2010-07-01 | 2010-09-28 | 2010-07-01 | 2011-07-14
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217PAER | PAERDEGAT PK- RECON. BSKT BALL, SIDEWALKS, LIGHTS, B218-112M | 2 | DESIGN | 2010-09-29 | 2010-12-27 | 2011-07-15 | 2013-02-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217PAER | PAERDEGAT PK- RECON. BSKT BALL, SIDEWALKS, LIGHTS, B218-112M | 3 | BID/ REGISTER CONTRACT | 2010-12-28 | 2011-03-27 | 2013-02-24 | 2013-05-24
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217PAER | PAERDEGAT PK- RECON. BSKT BALL, SIDEWALKS, LIGHTS, B218-112M | 4 | CONSTRUCTION | 2011-03-28 | 2012-03-26 | 2013-05-25 | 2014-05-24
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217PAER | PAERDEGAT PK- RECON. BSKT BALL, SIDEWALKS, LIGHTS, B218-112M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-03-27 | 2013-03-26 | 2014-05-25 | 2023-05-24
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217PBYC | Paerdegat Basin Yacht Club | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217PBYC | Paerdegat Basin Yacht Club | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2016-12-28 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217PBYC | Paerdegat Basin Yacht Club | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2017-12-28 | 2018-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217PBYC | Paerdegat Basin Yacht Club | 4 | CONSTRUCTION | 2018-09-24 | 2019-09-23 | 2018-09-24 | 2019-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217PBYC | Paerdegat Basin Yacht Club | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217PDGT | PAERDEGAT ATHLETIC CLUB - HVAC WORK | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2014-03-04
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217PDGT | PAERDEGAT ATHLETIC CLUB - HVAC WORK | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2014-03-05 | 2015-04-13
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217PDGT | PAERDEGAT ATHLETIC CLUB - HVAC WORK | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2015-04-14 | 2017-07-12
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217PDGT | PAERDEGAT ATHLETIC CLUB - HVAC WORK | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2017-07-13 | 2018-07-12
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217PDGT | PAERDEGAT ATHLETIC CLUB - HVAC WORK | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2018-07-13 | 2023-07-12
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217TILD | TILDEN PLAYGROUND-SHIRLEY CHISHOLM COMM CTR B234 | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217TILD | TILDEN PLAYGROUND-SHIRLEY CHISHOLM COMM CTR B234 | 2 | DESIGN | 2016-12-28 | 2018-12-27 | 2016-12-28 | 2018-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217TILD | TILDEN PLAYGROUND-SHIRLEY CHISHOLM COMM CTR B234 | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217TILD | TILDEN PLAYGROUND-SHIRLEY CHISHOLM COMM CTR B234 | 4 | CONSTRUCTION | 2019-09-24 | 2022-09-22 | 2019-09-24 | 2022-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217TILD | TILDEN PLAYGROUND-SHIRLEY CHISHOLM COMM CTR B234 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2024-09-21 | 2022-09-23 | 2024-09-21
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217WYKF | WYCKOFF FARMHOUSE - ROOF RESTORATION B376-111M | 1 | DEVELOP SCOPE | 2010-07-01 | 2010-09-28 | 2010-07-01 | 2011-06-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217WYKF | WYCKOFF FARMHOUSE - ROOF RESTORATION B376-111M | 2 | DESIGN | 2010-09-29 | 2010-12-27 | 2011-06-29 | 2016-01-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217WYKF | WYCKOFF FARMHOUSE - ROOF RESTORATION B376-111M | 3 | BID/ REGISTER CONTRACT | 2010-12-28 | 2011-03-27 | 2016-01-27 | 2016-04-25
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217WYKF | WYCKOFF FARMHOUSE - ROOF RESTORATION B376-111M | 4 | CONSTRUCTION | 2011-03-28 | 2012-03-26 | 2016-04-26 | 2017-04-25
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217WYKF | WYCKOFF FARMHOUSE - ROOF RESTORATION B376-111M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-03-27 | 2013-03-26 | 2017-04-26 | 2022-04-30
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218BILD | Bildersee Playground (B335-116M) | 1 | DEVELOP SCOPE | 2014-07-01 | 2014-09-28 | 2014-07-01 | 2014-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218BILD | Bildersee Playground (B335-116M) | 2 | DESIGN | 2014-09-29 | 2014-12-27 | 2014-09-29 | 2014-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218BILD | Bildersee Playground (B335-116M) | 3 | BID/ REGISTER CONTRACT | 2014-12-28 | 2015-03-27 | 2014-12-28 | 2015-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218BILD | Bildersee Playground (B335-116M) | 4 | CONSTRUCTION | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2016-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218BILD | Bildersee Playground (B335-116M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2023-08-19
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218BPLG | Bildersee plgd-new plgd and ph2 | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218BPLG | Bildersee plgd-new plgd and ph2 | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218BPLG | Bildersee plgd-new plgd and ph2 | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218BPLG | Bildersee plgd-new plgd and ph2 | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218BPLG | Bildersee plgd-new plgd and ph2 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2025-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218CCMF | CANARSIE PARK PHASE V- COMFORT STATION B018-214M | 1 | DEVELOP SCOPE | 2012-07-01 | 2012-09-28 | 2012-07-01 | 2015-01-12
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218CCMF | CANARSIE PARK PHASE V- COMFORT STATION B018-214M | 2 | DESIGN | 2012-09-29 | 2012-12-27 | 2015-01-13 | 2017-02-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218CCMF | CANARSIE PARK PHASE V- COMFORT STATION B018-214M | 3 | BID/ REGISTER CONTRACT | 2012-12-28 | 2013-03-27 | 2017-03-01 | 2017-05-29
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218CCMF | CANARSIE PARK PHASE V- COMFORT STATION B018-214M | 4 | CONSTRUCTION | 2013-03-28 | 2014-03-27 | 2017-05-30 | 2018-05-29
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218CCMF | CANARSIE PARK PHASE V- COMFORT STATION B018-214M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-03-28 | 2015-03-27 | 2018-05-30 | 2022-05-29
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218D17L | LINDOWER (ALEX LINDOWER) PARK PLAYGROUND PH 1 B329-109M | 1 | DEVELOP SCOPE | 2007-07-01 | 2007-09-28 | 2007-07-01 | 2007-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218D17L | LINDOWER (ALEX LINDOWER) PARK PLAYGROUND PH 1 B329-109M | 2 | DESIGN | 2007-09-29 | 2007-12-27 | 2007-09-29 | 2010-11-10
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218D17L | LINDOWER (ALEX LINDOWER) PARK PLAYGROUND PH 1 B329-109M | 3 | BID/ REGISTER CONTRACT | 2007-12-28 | 2008-03-26 | 2011-03-04 | 2011-08-07
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218D17L | LINDOWER (ALEX LINDOWER) PARK PLAYGROUND PH 1 B329-109M | 4 | CONSTRUCTION | 2008-03-27 | 2009-03-26 | 2011-08-08 | 2012-08-06
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218D17L | LINDOWER (ALEX LINDOWER) PARK PLAYGROUND PH 1 B329-109M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2009-03-27 | 2010-03-26 | 2012-08-07 | 2022-01-25
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218D17S | DR. JOHN'S PLAYGROUND- MARINE PK (B057-114M) | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2013-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218D17S | DR. JOHN'S PLAYGROUND- MARINE PK (B057-114M) | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2013-09-29 | 2013-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218D17S | DR. JOHN'S PLAYGROUND- MARINE PK (B057-114M) | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2013-12-28 | 2014-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218D17S | DR. JOHN'S PLAYGROUND- MARINE PK (B057-114M) | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2014-03-28 | 2015-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218D17S | DR. JOHN'S PLAYGROUND- MARINE PK (B057-114M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2023-04-16
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218GERT | Marine Park - Gerritsen Ave. Ped. Path PH 2 (B057-117M) | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218GERT | Marine Park - Gerritsen Ave. Ped. Path PH 2 (B057-117M) | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2016-12-28 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218GERT | Marine Park - Gerritsen Ave. Ped. Path PH 2 (B057-117M) | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2017-12-28 | 2018-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218GERT | Marine Park - Gerritsen Ave. Ped. Path PH 2 (B057-117M) | 4 | CONSTRUCTION | 2018-09-24 | 2019-09-23 | 2018-09-24 | 2019-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218GERT | Marine Park - Gerritsen Ave. Ped. Path PH 2 (B057-117M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218GLEN | Glenwood Playground - recon. multi-purpose area B236-114M | 1 | DEVELOP SCOPE | 2012-07-01 | 2012-09-28 | 2012-07-01 | 2012-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218GLEN | Glenwood Playground - recon. multi-purpose area B236-114M | 2 | DESIGN | 2012-09-29 | 2012-12-27 | 2012-09-29 | 2012-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218GLEN | Glenwood Playground - recon. multi-purpose area B236-114M | 3 | BID/ REGISTER CONTRACT | 2012-12-28 | 2013-03-27 | 2012-12-28 | 2013-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218GLEN | Glenwood Playground - recon. multi-purpose area B236-114M | 4 | CONSTRUCTION | 2013-03-28 | 2014-03-27 | 2013-03-28 | 2014-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218GLEN | Glenwood Playground - recon. multi-purpose area B236-114M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-03-28 | 2015-03-27 | 2014-03-28 | 2024-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218GOLF | BK Golf Alliance - Marine Pk. Golf Course - B057-119M | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2013-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218GOLF | BK Golf Alliance - Marine Pk. Golf Course - B057-119M | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2013-09-29 | 2013-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218GOLF | BK Golf Alliance - Marine Pk. Golf Course - B057-119M | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2013-12-28 | 2014-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218GOLF | BK Golf Alliance - Marine Pk. Golf Course - B057-119M | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2014-03-28 | 2015-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218GOLF | BK Golf Alliance - Marine Pk. Golf Course - B057-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2024-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218JCOB | Jacob Joffe Playground - B324 | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2015-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218JCOB | Jacob Joffe Playground - B324 | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2015-09-29 | 2015-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218JCOB | Jacob Joffe Playground - B324 | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2015-12-28 | 2016-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218JCOB | Jacob Joffe Playground - B324 | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218JCOB | Jacob Joffe Playground - B324 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2017-03-27 | 2022-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218JFEE | Jacob Joffe Playground- Park Renovations | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218JFEE | Jacob Joffe Playground- Park Renovations | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2016-12-28 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218JFEE | Jacob Joffe Playground- Park Renovations | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2017-12-28 | 2018-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218JFEE | Jacob Joffe Playground- Park Renovations | 4 | CONSTRUCTION | 2018-09-24 | 2019-09-23 | 2018-09-24 | 2019-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218JFEE | Jacob Joffe Playground- Park Renovations | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218LOTT | HENDRICK I. LOTT HOUSE -INTERIOR RESTORATION | 1 | DEVELOP SCOPE | 2010-07-01 | 2010-09-28 | 2014-12-04 | 2015-03-04
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218LOTT | HENDRICK I. LOTT HOUSE -INTERIOR RESTORATION | 2 | DESIGN | 2010-09-29 | 2010-12-27 | 2015-03-05 | 2015-06-05
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218LOTT | HENDRICK I. LOTT HOUSE -INTERIOR RESTORATION | 3 | BID/ REGISTER CONTRACT | 2010-12-28 | 2011-03-27 | 2015-06-06 | 2015-09-05
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218LOTT | HENDRICK I. LOTT HOUSE -INTERIOR RESTORATION | 4 | CONSTRUCTION | 2011-03-28 | 2012-03-26 | 2015-09-06 | 2016-09-05
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218LOTT | HENDRICK I. LOTT HOUSE -INTERIOR RESTORATION | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-03-27 | 2013-03-26 | 2016-09-06 | 2023-09-07
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218MPOV | Marine Park:Bicycle/Pedestrian ovals,Resurface Asphalt Track | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218MPOV | Marine Park:Bicycle/Pedestrian ovals,Resurface Asphalt Track | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218MPOV | Marine Park:Bicycle/Pedestrian ovals,Resurface Asphalt Track | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218MPOV | Marine Park:Bicycle/Pedestrian ovals,Resurface Asphalt Track | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218MPOV | Marine Park:Bicycle/Pedestrian ovals,Resurface Asphalt Track | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2026-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218MPPG | Marine Park Playground - Reconstruction of Playground 278 | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218MPPG | Marine Park Playground - Reconstruction of Playground 278 | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218MPPG | Marine Park Playground - Reconstruction of Playground 278 | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218MPPG | Marine Park Playground - Reconstruction of Playground 278 | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218MPPG | Marine Park Playground - Reconstruction of Playground 278 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218MPRK | MARINE PARK- RC - Bocce Cts, Sports Cts & LandscapeB057-112M | 1 | DEVELOP SCOPE | 2011-07-01 | 2011-09-28 | 2012-07-01 | 2012-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218MPRK | MARINE PARK- RC - Bocce Cts, Sports Cts & LandscapeB057-112M | 2 | DESIGN | 2011-09-29 | 2011-12-27 | 2011-09-29 | 2011-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218MPRK | MARINE PARK- RC - Bocce Cts, Sports Cts & LandscapeB057-112M | 3 | BID/ REGISTER CONTRACT | 2011-12-28 | 2012-03-26 | 2011-12-28 | 2012-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218MPRK | MARINE PARK- RC - Bocce Cts, Sports Cts & LandscapeB057-112M | 4 | CONSTRUCTION | 2012-03-27 | 2013-03-26 | 2012-03-27 | 2013-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218MPRK | MARINE PARK- RC - Bocce Cts, Sports Cts & LandscapeB057-112M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-03-27 | 2014-03-26 | 2013-03-27 | 2017-08-10
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218PLMB | PLUMB BEACH STABILIZATION | 1 | DEVELOP SCOPE | 2011-07-01 | 2011-09-28 | 2011-07-01 | 2011-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218PLMB | PLUMB BEACH STABILIZATION | 2 | DESIGN | 2011-09-29 | 2011-12-27 | 2011-09-29 | 2011-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218PLMB | PLUMB BEACH STABILIZATION | 3 | BID/ REGISTER CONTRACT | 2011-12-28 | 2012-03-26 | 2011-12-28 | 2012-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218PLMB | PLUMB BEACH STABILIZATION | 4 | CONSTRUCTION | 2012-03-27 | 2013-03-26 | 2012-03-27 | 2013-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218PLMB | PLUMB BEACH STABILIZATION | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-03-27 | 2014-03-26 | 2013-03-27 | 2014-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218PWMP | Power-Memorial- Seating Area ( B219-120M) | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218PWMP | Power-Memorial- Seating Area ( B219-120M) | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2016-12-28 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218PWMP | Power-Memorial- Seating Area ( B219-120M) | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2017-12-28 | 2018-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218PWMP | Power-Memorial- Seating Area ( B219-120M) | 4 | CONSTRUCTION | 2018-09-24 | 2019-09-23 | 2018-09-24 | 2019-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218PWMP | Power-Memorial- Seating Area ( B219-120M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2024-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218SEBA | SEBA PLAYGROUND TODDLER LOT (B057-111M | 2 | DESIGN | 2008-09-29 | 2008-12-27 | 2008-09-29 | 2008-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218SEBA | SEBA PLAYGROUND TODDLER LOT (B057-111M | 3 | BID/ REGISTER CONTRACT | 2008-12-28 | 2009-03-27 | 2008-12-28 | 2009-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218SEBA | SEBA PLAYGROUND TODDLER LOT (B057-111M | 4 | CONSTRUCTION | 2009-03-28 | 2010-03-27 | 2009-03-28 | 2010-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218SEBA | SEBA PLAYGROUND TODDLER LOT (B057-111M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2010-03-28 | 2011-03-27 | 2010-03-28 | 2013-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218SUNN | Sunners Playground - Renovate Playground (B206-119M) | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218SUNN | Sunners Playground - Renovate Playground (B206-119M) | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218SUNN | Sunners Playground - Renovate Playground (B206-119M) | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218SUNN | Sunners Playground - Renovate Playground (B206-119M) | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218SUNN | Sunners Playground - Renovate Playground (B206-119M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2ANCH01 | ANCHOR PARK- Betsy Head (B008-) | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2ANCH01 | ANCHOR PARK- Betsy Head (B008-) | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2016-12-28 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2ANCH01 | ANCHOR PARK- Betsy Head (B008-) | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2017-12-28 | 2018-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2ANCH01 | ANCHOR PARK- Betsy Head (B008-) | 4 | CONSTRUCTION | 2018-09-24 | 2019-09-23 | 2018-09-24 | 2019-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2ANCH01 | ANCHOR PARK- Betsy Head (B008-) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2ANCH02 | Betsy Head Park Comfort Station Reconstruction (B008-218M) | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2ANCH02 | Betsy Head Park Comfort Station Reconstruction (B008-218M) | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2ANCH02 | Betsy Head Park Comfort Station Reconstruction (B008-218M) | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2ANCH02 | Betsy Head Park Comfort Station Reconstruction (B008-218M) | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2ANCH02 | Betsy Head Park Comfort Station Reconstruction (B008-218M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2ANCH03 | Betsy Head Park Syn. Turf, Field, Track, Sport Crts Ft Ctr | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2ANCH03 | Betsy Head Park Syn. Turf, Field, Track, Sport Crts Ft Ctr | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2ANCH03 | Betsy Head Park Syn. Turf, Field, Track, Sport Crts Ft Ctr | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2ANCH03 | Betsy Head Park Syn. Turf, Field, Track, Sport Crts Ft Ctr | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2ANCH03 | Betsy Head Park Syn. Turf, Field, Track, Sport Crts Ft Ctr | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2ANCH04 | ANCHOR PARK- Betsy Head Multi-Purpose Play Area Reconst. | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2ANCH04 | ANCHOR PARK- Betsy Head Multi-Purpose Play Area Reconst. | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2ANCH04 | ANCHOR PARK- Betsy Head Multi-Purpose Play Area Reconst. | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2ANCH04 | ANCHOR PARK- Betsy Head Multi-Purpose Play Area Reconst. | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2ANCH04 | ANCHOR PARK- Betsy Head Multi-Purpose Play Area Reconst. | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BELTPA | Belt Pkwy Lndscp Restoration & Tree Planting Ph2 B166-113M | 1 | DEVELOP SCOPE | 2012-07-01 | 2012-09-28 | 2012-07-01 | 2012-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BELTPA | Belt Pkwy Lndscp Restoration & Tree Planting Ph2 B166-113M | 2 | DESIGN | 2012-09-29 | 2012-12-27 | 2012-09-29 | 2012-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BELTPA | Belt Pkwy Lndscp Restoration & Tree Planting Ph2 B166-113M | 3 | BID/ REGISTER CONTRACT | 2012-12-28 | 2013-03-27 | 2012-12-28 | 2013-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BELTPA | Belt Pkwy Lndscp Restoration & Tree Planting Ph2 B166-113M | 4 | CONSTRUCTION | 2013-03-28 | 2014-03-27 | 2013-03-28 | 2014-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BELTPA | Belt Pkwy Lndscp Restoration & Tree Planting Ph2 B166-113M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-03-28 | 2015-03-27 | 2014-03-28 | 2021-06-12
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BELTPC | FY14 Belt Parkway Street Trees | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2013-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BELTPC | FY14 Belt Parkway Street Trees | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2013-09-29 | 2013-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BELTPC | FY14 Belt Parkway Street Trees | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2013-12-28 | 2014-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BELTPC | FY14 Belt Parkway Street Trees | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2014-03-28 | 2015-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BELTPC | FY14 Belt Parkway Street Trees | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2020-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BELTPD | CON - BIKE PATH THRU CANARSIE PARK WEST | 1 | DEVELOP SCOPE | 2013-03-01 | 2013-05-29 | 2013-03-01 | 2013-05-29
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BELTPD | CON - BIKE PATH THRU CANARSIE PARK WEST | 2 | DESIGN | 2013-05-30 | 2013-08-27 | 2013-05-30 | 2013-08-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BELTPD | CON - BIKE PATH THRU CANARSIE PARK WEST | 3 | BID/ REGISTER CONTRACT | 2013-08-28 | 2013-11-25 | 2013-08-28 | 2013-11-25
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BELTPD | CON - BIKE PATH THRU CANARSIE PARK WEST | 4 | CONSTRUCTION | 2013-11-26 | 2014-11-25 | 2013-11-26 | 2014-11-25
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BELTPD | CON - BIKE PATH THRU CANARSIE PARK WEST | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-11-26 | 2015-11-25 | 2014-11-26 | 2020-11-25
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BELTPE | Mill Basin Bridge Trees | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BELTPE | Mill Basin Bridge Trees | 2 | DESIGN | 2016-12-28 | 2018-12-27 | 2016-12-28 | 2018-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BELTPE | Mill Basin Bridge Trees | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BELTPE | Mill Basin Bridge Trees | 4 | CONSTRUCTION | 2019-09-24 | 2022-09-22 | 2019-09-24 | 2022-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BELTPE | Mill Basin Bridge Trees | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2024-09-21 | 2022-09-23 | 2024-09-21
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BKPAV1 | Brooklyn Multisite Pavement Reconstruction | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BKPAV1 | Brooklyn Multisite Pavement Reconstruction | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BKPAV1 | Brooklyn Multisite Pavement Reconstruction | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BKPAV1 | Brooklyn Multisite Pavement Reconstruction | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BKPAV1 | Brooklyn Multisite Pavement Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BKPLG1 | Brooklyn MPPA SOGR Reconstruction | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BKPLG1 | Brooklyn MPPA SOGR Reconstruction | 2 | DESIGN | 2019-12-28 | 2021-06-24 | 2019-12-28 | 2021-06-24
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BKPLG1 | Brooklyn MPPA SOGR Reconstruction | 3 | BID/ REGISTER CONTRACT | 2021-06-25 | 2022-03-21 | 2021-06-25 | 2022-03-21
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BKPLG1 | Brooklyn MPPA SOGR Reconstruction | 4 | CONSTRUCTION | 2022-03-22 | 2023-09-17 | 2022-03-22 | 2023-09-17
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BKPLG1 | Brooklyn MPPA SOGR Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-18 | 2024-09-16 | 2023-09-18 | 2024-09-16
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BOIL1A | BROOKLYN - BOILERS & HVAC SYSTEMS B073-111M | 4 | CONSTRUCTION | 2012-03-27 | 2013-03-26 | 2012-03-27 | 2013-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BOIL1A | BROOKLYN - BOILERS & HVAC SYSTEMS B073-111M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-03-27 | 2014-03-26 | 2013-03-27 | 2014-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BQGRN | BQ GREEN | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BQGRN | BQ GREEN | 2 | DESIGN | 2017-12-28 | 2019-06-20 | 2017-12-28 | 2019-06-20
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BQGRN | BQ GREEN | 3 | BID/ REGISTER CONTRACT | 2019-06-21 | 2020-03-16 | 2019-06-21 | 2020-03-16
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BQGRN | BQ GREEN | 4 | CONSTRUCTION | 2020-03-17 | 2021-09-07 | 2020-03-17 | 2021-09-07
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BQGRN | BQ GREEN | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-08 | 2022-09-07 | 2021-09-08 | 2025-09-25
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BRIGHM | Brigham Park - plgd & passive area B057-212M/512M | 1 | DEVELOP SCOPE | 2009-07-01 | 2009-09-28 | 2009-07-01 | 2009-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BRIGHM | Brigham Park - plgd & passive area B057-212M/512M | 2 | DESIGN | 2009-09-29 | 2009-12-27 | 2009-09-29 | 2009-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BRIGHM | Brigham Park - plgd & passive area B057-212M/512M | 3 | BID/ REGISTER CONTRACT | 2009-12-28 | 2010-03-27 | 2009-12-28 | 2010-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BRIGHM | Brigham Park - plgd & passive area B057-212M/512M | 4 | CONSTRUCTION | 2010-03-28 | 2011-03-27 | 2010-03-28 | 2011-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BRIGHM | Brigham Park - plgd & passive area B057-212M/512M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2011-03-28 | 2012-03-26 | 2011-03-28 | 2020-07-11
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BSKBL1 | Brooklyn Basketball Courts Reconstruction (SoGR) BG-320M | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BSKBL1 | Brooklyn Basketball Courts Reconstruction (SoGR) BG-320M | 2 | DESIGN | 2019-12-28 | 2021-06-24 | 2019-12-28 | 2021-06-24
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BSKBL1 | Brooklyn Basketball Courts Reconstruction (SoGR) BG-320M | 3 | BID/ REGISTER CONTRACT | 2021-06-25 | 2022-03-21 | 2021-06-25 | 2022-03-21
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BSKBL1 | Brooklyn Basketball Courts Reconstruction (SoGR) BG-320M | 4 | CONSTRUCTION | 2022-03-22 | 2023-09-17 | 2022-03-22 | 2023-09-17
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BSKBL1 | Brooklyn Basketball Courts Reconstruction (SoGR) BG-320M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-18 | 2024-09-16 | 2023-09-18 | 2024-09-16
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BWCC04 | BKLYN MULTISITE CMFT STA.- TILDEN & BANNEKER BG-111M | 1 | DEVELOP SCOPE | 2010-07-01 | 2010-09-28 | 2010-07-01 | 2010-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BWCC04 | BKLYN MULTISITE CMFT STA.- TILDEN & BANNEKER BG-111M | 2 | DESIGN | 2010-09-29 | 2010-12-27 | 2010-09-29 | 2010-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BWCC04 | BKLYN MULTISITE CMFT STA.- TILDEN & BANNEKER BG-111M | 3 | BID/ REGISTER CONTRACT | 2010-12-28 | 2011-03-27 | 2010-12-28 | 2011-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BWCC04 | BKLYN MULTISITE CMFT STA.- TILDEN & BANNEKER BG-111M | 4 | CONSTRUCTION | 2011-03-28 | 2012-03-26 | 2011-03-28 | 2012-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BWCC04 | BKLYN MULTISITE CMFT STA.- TILDEN & BANNEKER BG-111M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-03-27 | 2013-03-26 | 2012-03-27 | 2023-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BWD017 | PRATT, GREENWOOD,& ST ANDREW'S PLGDS; BG-304M | 2 | DESIGN | 2003-12-31 | 2004-03-31 | 2003-12-31 | 2004-03-31
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BWD017 | PRATT, GREENWOOD,& ST ANDREW'S PLGDS; BG-304M | 3 | BID/ REGISTER CONTRACT | 2004-04-01 | 2004-06-30 | 2004-04-01 | 2004-06-30
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BWD017 | PRATT, GREENWOOD,& ST ANDREW'S PLGDS; BG-304M | 4 | CONSTRUCTION | 2004-08-31 | 2005-08-30 | 2004-08-31 | 2005-08-30
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BWD017 | PRATT, GREENWOOD,& ST ANDREW'S PLGDS; BG-304M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2005-08-31 | 2006-08-30 | 2005-08-31 | 2006-08-30
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BWK11I | RQMT CNTR BKLYN BP FY00 PLEQ SFTYSRF PAV FNC GNLSW BG-300M | 1 | DEVELOP SCOPE | 2020-07-01 | 2020-12-27 | 2020-07-01 | 2020-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BWK11I | RQMT CNTR BKLYN BP FY00 PLEQ SFTYSRF PAV FNC GNLSW BG-300M | 2 | DESIGN | 2020-12-28 | 2021-12-27 | 2020-12-28 | 2021-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BWK11I | RQMT CNTR BKLYN BP FY00 PLEQ SFTYSRF PAV FNC GNLSW BG-300M | 3 | BID/ REGISTER CONTRACT | 2021-12-28 | 2022-09-23 | 2021-12-28 | 2022-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BWK11I | RQMT CNTR BKLYN BP FY00 PLEQ SFTYSRF PAV FNC GNLSW BG-300M | 4 | CONSTRUCTION | 2022-09-24 | 2023-09-23 | 2022-09-24 | 2023-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BWK11I | RQMT CNTR BKLYN BP FY00 PLEQ SFTYSRF PAV FNC GNLSW BG-300M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-24 | 2024-09-22 | 2023-09-24 | 2024-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BWK11J | BROOKLYN REQMT FY03/4 INCL OCEAN PKWY MALLS BENCHES BG-504M | 1 | DEVELOP SCOPE | 2003-07-01 | 2003-11-30 | 2003-07-01 | 2004-01-29
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BWK11J | BROOKLYN REQMT FY03/4 INCL OCEAN PKWY MALLS BENCHES BG-504M | 2 | DESIGN | 2003-12-01 | 2003-12-31 | 2004-01-30 | 2004-04-01
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BWK11J | BROOKLYN REQMT FY03/4 INCL OCEAN PKWY MALLS BENCHES BG-504M | 3 | BID/ REGISTER CONTRACT | 2004-01-01 | 2004-04-30 | 2004-04-27 | 2004-08-10
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BWK11J | BROOKLYN REQMT FY03/4 INCL OCEAN PKWY MALLS BENCHES BG-504M | 4 | CONSTRUCTION | 2004-05-31 | 2005-05-30 | 2004-12-06 | 2005-09-15
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BWK11J | BROOKLYN REQMT FY03/4 INCL OCEAN PKWY MALLS BENCHES BG-504M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2005-05-31 | 2006-05-30 | 2005-09-16 | 2022-07-01
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CIBBOL | Coney Island Boardwalk - Cons Security Measures B169-120M | 1 | DEVELOP SCOPE | 2018-05-29 | 2018-11-24 | 2018-05-29 | 2018-11-24
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CIBBOL | Coney Island Boardwalk - Cons Security Measures B169-120M | 2 | DESIGN | 2018-11-25 | 2019-11-24 | 2018-11-25 | 2019-11-24
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CIBBOL | Coney Island Boardwalk - Cons Security Measures B169-120M | 3 | BID/ REGISTER CONTRACT | 2019-11-25 | 2020-08-20 | 2019-11-25 | 2020-08-20
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CIBBOL | Coney Island Boardwalk - Cons Security Measures B169-120M | 4 | CONSTRUCTION | 2020-08-21 | 2021-08-20 | 2020-08-21 | 2021-08-20
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CIBBOL | Coney Island Boardwalk - Cons Security Measures B169-120M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-08-21 | 2022-08-20 | 2021-08-21 | 2022-08-20
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CIGNWY | CONEY ISLAND GREENWAY PROPOSED SAFETEA GRANT | 1 | DEVELOP SCOPE | 2011-07-01 | 2011-09-28 | 2011-07-01 | 2011-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CIGNWY | CONEY ISLAND GREENWAY PROPOSED SAFETEA GRANT | 2 | DESIGN | 2011-09-29 | 2011-12-27 | 2011-09-29 | 2011-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CIGNWY | CONEY ISLAND GREENWAY PROPOSED SAFETEA GRANT | 3 | BID/ REGISTER CONTRACT | 2011-12-28 | 2012-03-26 | 2011-12-28 | 2012-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CIGNWY | CONEY ISLAND GREENWAY PROPOSED SAFETEA GRANT | 4 | CONSTRUCTION | 2012-03-27 | 2013-03-26 | 2012-03-27 | 2013-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CIGNWY | CONEY ISLAND GREENWAY PROPOSED SAFETEA GRANT | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-03-27 | 2014-03-26 | 2013-03-27 | 2025-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CIWALK | CONEY ISLAND BWALK - RC OF VARIOUS SEGMENT B169-220M | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2013-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CIWALK | CONEY ISLAND BWALK - RC OF VARIOUS SEGMENT B169-220M | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2013-09-29 | 2013-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CIWALK | CONEY ISLAND BWALK - RC OF VARIOUS SEGMENT B169-220M | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2013-12-28 | 2014-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CIWALK | CONEY ISLAND BWALK - RC OF VARIOUS SEGMENT B169-220M | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2014-03-28 | 2015-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CIWALK | CONEY ISLAND BWALK - RC OF VARIOUS SEGMENT B169-220M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2016-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CONYGS | CONEY ISLAND COASTAL RESIL. GREENSTREETS BG-515MA | 1 | DEVELOP SCOPE | 2014-07-01 | 2014-09-28 | 2014-07-01 | 2014-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CONYGS | CONEY ISLAND COASTAL RESIL. GREENSTREETS BG-515MA | 2 | DESIGN | 2014-09-29 | 2014-12-27 | 2014-09-29 | 2017-09-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CONYGS | CONEY ISLAND COASTAL RESIL. GREENSTREETS BG-515MA | 3 | BID/ REGISTER CONTRACT | 2014-12-28 | 2015-03-27 | 2017-09-28 | 2017-12-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CONYGS | CONEY ISLAND COASTAL RESIL. GREENSTREETS BG-515MA | 4 | CONSTRUCTION | 2015-03-28 | 2016-03-26 | 2017-12-27 | 2018-12-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CONYGS | CONEY ISLAND COASTAL RESIL. GREENSTREETS BG-515MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-27 | 2017-03-26 | 2018-12-27 | 2021-12-25
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2COOPCS | Cooper Park-Reconstruction of Comfort Station | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2COOPCS | Cooper Park-Reconstruction of Comfort Station | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2COOPCS | Cooper Park-Reconstruction of Comfort Station | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2COOPCS | Cooper Park-Reconstruction of Comfort Station | 4 | CONSTRUCTION | 2019-09-24 | 2021-03-21 | 2019-09-24 | 2021-03-21
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2COOPCS | Cooper Park-Reconstruction of Comfort Station | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-22 | 2022-03-21 | 2021-03-22 | 2024-03-21
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIBN2 | CPI PH1- J. Owens, Stockton & Stroud C/S RC BG-815M | 1 | DEVELOP SCOPE | 2014-07-01 | 2014-09-28 | 2014-07-01 | 2014-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIBN2 | CPI PH1- J. Owens, Stockton & Stroud C/S RC BG-815M | 2 | DESIGN | 2014-09-29 | 2014-12-27 | 2014-09-29 | 2014-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIBN2 | CPI PH1- J. Owens, Stockton & Stroud C/S RC BG-815M | 3 | BID/ REGISTER CONTRACT | 2014-12-28 | 2015-03-27 | 2014-12-28 | 2015-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIBN2 | CPI PH1- J. Owens, Stockton & Stroud C/S RC BG-815M | 4 | CONSTRUCTION | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2016-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIBN2 | CPI PH1- J. Owens, Stockton & Stroud C/S RC BG-815M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2023-06-12
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIBPG | CPI PH2 - Bartlett Playground | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIBPG | CPI PH2 - Bartlett Playground | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIBPG | CPI PH2 - Bartlett Playground | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIBPG | CPI PH2 - Bartlett Playground | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIBPG | CPI PH2 - Bartlett Playground | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIEPP | CPI PH2 - R/C Epiphany Playground (B405 -116M) | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2015-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIEPP | CPI PH2 - R/C Epiphany Playground (B405 -116M) | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2015-09-29 | 2015-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIEPP | CPI PH2 - R/C Epiphany Playground (B405 -116M) | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2015-12-28 | 2016-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIEPP | CPI PH2 - R/C Epiphany Playground (B405 -116M) | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIEPP | CPI PH2 - R/C Epiphany Playground (B405 -116M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2017-03-27 | 2023-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIJOP | CPI Ph1- RC of Jesse Owens Play. B269-116M | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIJOP | CPI Ph1- RC of Jesse Owens Play. B269-116M | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2016-12-28 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIJOP | CPI Ph1- RC of Jesse Owens Play. B269-116M | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2017-12-28 | 2018-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIJOP | CPI Ph1- RC of Jesse Owens Play. B269-116M | 4 | CONSTRUCTION | 2018-09-24 | 2019-09-23 | 2018-09-24 | 2019-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIJOP | CPI Ph1- RC of Jesse Owens Play. B269-116M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2023-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPILAG | CPI ph2. - LaGuardia Playground Ph 2. (B167-217M) | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPILAG | CPI ph2. - LaGuardia Playground Ph 2. (B167-217M) | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPILAG | CPI ph2. - LaGuardia Playground Ph 2. (B167-217M) | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPILAG | CPI ph2. - LaGuardia Playground Ph 2. (B167-217M) | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPILAG | CPI ph2. - LaGuardia Playground Ph 2. (B167-217M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPILFT | CPI PH2 - Lafayette Playground Reconstruction (B106B-116M) | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPILFT | CPI PH2 - Lafayette Playground Reconstruction (B106B-116M) | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2016-12-28 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPILFT | CPI PH2 - Lafayette Playground Reconstruction (B106B-116M) | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2017-12-28 | 2018-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPILFT | CPI PH2 - Lafayette Playground Reconstruction (B106B-116M) | 4 | CONSTRUCTION | 2018-09-24 | 2019-09-23 | 2018-09-24 | 2019-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPILFT | CPI PH2 - Lafayette Playground Reconstruction (B106B-116M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2023-09-24
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPILGD | CPI PH2 - LaGuardia Playground (B167-117M) | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPILGD | CPI PH2 - LaGuardia Playground (B167-117M) | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2016-12-28 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPILGD | CPI PH2 - LaGuardia Playground (B167-117M) | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2017-12-28 | 2018-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPILGD | CPI PH2 - LaGuardia Playground (B167-117M) | 4 | CONSTRUCTION | 2018-09-24 | 2019-09-23 | 2018-09-24 | 2019-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPILGD | CPI PH2 - LaGuardia Playground (B167-117M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPILJP | CPI PH2 - RC- Lt. Joseph Petrosino Park (B099-) | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2016-04-19
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPILJP | CPI PH2 - RC- Lt. Joseph Petrosino Park (B099-) | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2016-04-20 | 2017-05-05
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPILJP | CPI PH2 - RC- Lt. Joseph Petrosino Park (B099-) | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2017-07-27 | 2017-11-30
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPILJP | CPI PH2 - RC- Lt. Joseph Petrosino Park (B099-) | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2018-01-29 | 2019-01-07
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPILJP | CPI PH2 - RC- Lt. Joseph Petrosino Park (B099-) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2019-01-08 | 2023-01-09
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPINEW | CPI Ph2.- Newport Comfort Station (B339-117M) | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPINEW | CPI Ph2.- Newport Comfort Station (B339-117M) | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2016-12-28 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPINEW | CPI Ph2.- Newport Comfort Station (B339-117M) | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2017-12-28 | 2018-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPINEW | CPI Ph2.- Newport Comfort Station (B339-117M) | 4 | CONSTRUCTION | 2018-09-24 | 2019-09-23 | 2018-09-24 | 2019-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPINEW | CPI Ph2.- Newport Comfort Station (B339-117M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2023-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPINPL | CPI-PH2. Newport playground (B339-216M) | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPINPL | CPI-PH2. Newport playground (B339-216M) | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2016-12-28 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPINPL | CPI-PH2. Newport playground (B339-216M) | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2017-12-28 | 2018-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPINPL | CPI-PH2. Newport playground (B339-216M) | 4 | CONSTRUCTION | 2018-09-24 | 2019-09-23 | 2018-09-24 | 2019-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPINPL | CPI-PH2. Newport playground (B339-216M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2023-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIPEN | CPI PHASE 2 - RC Penn Triangle and Playground B223NC-118M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIPEN | CPI PHASE 2 - RC Penn Triangle and Playground B223NC-118M | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIPEN | CPI PHASE 2 - RC Penn Triangle and Playground B223NC-118M | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIPEN | CPI PHASE 2 - RC Penn Triangle and Playground B223NC-118M | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIPEN | CPI PHASE 2 - RC Penn Triangle and Playground B223NC-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPISBF | CPI Ph1- RC Saratoga Ballfields (B387-116M) | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPISBF | CPI Ph1- RC Saratoga Ballfields (B387-116M) | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2016-12-28 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPISBF | CPI Ph1- RC Saratoga Ballfields (B387-116M) | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2017-12-28 | 2018-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPISBF | CPI Ph1- RC Saratoga Ballfields (B387-116M) | 4 | CONSTRUCTION | 2018-09-24 | 2019-09-23 | 2018-09-24 | 2019-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPISBF | CPI Ph1- RC Saratoga Ballfields (B387-116M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPITBP | CPI Ph1 - Thomas Boyland Park | 1 | DEVELOP SCOPE | 2014-07-01 | 2014-09-28 | 2014-07-01 | 2014-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPITBP | CPI Ph1 - Thomas Boyland Park | 2 | DESIGN | 2014-09-29 | 2014-12-27 | 2014-09-29 | 2014-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPITBP | CPI Ph1 - Thomas Boyland Park | 3 | BID/ REGISTER CONTRACT | 2014-12-28 | 2015-03-27 | 2014-12-28 | 2015-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPITBP | CPI Ph1 - Thomas Boyland Park | 4 | CONSTRUCTION | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2016-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPITBP | CPI Ph1 - Thomas Boyland Park | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2022-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPITEN | CPI Ph1.- Ten Eyck Play. (B311-116M) | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPITEN | CPI Ph1.- Ten Eyck Play. (B311-116M) | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2016-12-28 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPITEN | CPI Ph1.- Ten Eyck Play. (B311-116M) | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2017-12-28 | 2018-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPITEN | CPI Ph1.- Ten Eyck Play. (B311-116M) | 4 | CONSTRUCTION | 2018-09-24 | 2019-09-23 | 2018-09-24 | 2019-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPITEN | CPI Ph1.- Ten Eyck Play. (B311-116M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2023-09-24
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIWKS | CPI PH2- Weeksville Playground | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIWKS | CPI PH2- Weeksville Playground | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2016-12-28 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIWKS | CPI PH2- Weeksville Playground | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2017-12-28 | 2018-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIWKS | CPI PH2- Weeksville Playground | 4 | CONSTRUCTION | 2018-09-24 | 2019-09-23 | 2018-09-24 | 2019-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIWKS | CPI PH2- Weeksville Playground | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2023-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2DOGRUN | MULTI-DYKER HGTS, DIMATINA, & OWLS HEAD DOG RUN BG-712M | 1 | DEVELOP SCOPE | 2012-02-01 | 2012-04-30 | 2012-02-01 | 2012-04-30
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2DOGRUN | MULTI-DYKER HGTS, DIMATINA, & OWLS HEAD DOG RUN BG-712M | 2 | DESIGN | 2012-05-01 | 2012-07-29 | 2012-05-01 | 2012-07-29
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2DOGRUN | MULTI-DYKER HGTS, DIMATINA, & OWLS HEAD DOG RUN BG-712M | 3 | BID/ REGISTER CONTRACT | 2012-07-30 | 2012-10-27 | 2012-07-30 | 2012-10-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2DOGRUN | MULTI-DYKER HGTS, DIMATINA, & OWLS HEAD DOG RUN BG-712M | 4 | CONSTRUCTION | 2012-10-28 | 2013-10-27 | 2012-10-28 | 2013-10-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2DOGRUN | MULTI-DYKER HGTS, DIMATINA, & OWLS HEAD DOG RUN BG-712M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-10-28 | 2014-10-27 | 2013-10-28 | 2016-10-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GATE10 | Gateway Estates-Multi-purpose ballfield B548-118M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GATE10 | Gateway Estates-Multi-purpose ballfield B548-118M | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GATE10 | Gateway Estates-Multi-purpose ballfield B548-118M | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GATE10 | Gateway Estates-Multi-purpose ballfield B548-118M | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GATE10 | Gateway Estates-Multi-purpose ballfield B548-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2024-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GATEW2 | Gateway Estates - Constru. Plgd & comft. stat. B541-115M | 1 | DEVELOP SCOPE | 2007-07-01 | 2007-09-28 | 2011-07-01 | 2011-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GATEW2 | Gateway Estates - Constru. Plgd & comft. stat. B541-115M | 2 | DESIGN | 2007-09-29 | 2007-12-27 | 2011-09-29 | 2011-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GATEW2 | Gateway Estates - Constru. Plgd & comft. stat. B541-115M | 3 | BID/ REGISTER CONTRACT | 2007-12-28 | 2008-03-26 | 2011-12-28 | 2012-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GATEW2 | Gateway Estates - Constru. Plgd & comft. stat. B541-115M | 4 | CONSTRUCTION | 2008-03-27 | 2009-03-26 | 2012-03-27 | 2013-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GATEW2 | Gateway Estates - Constru. Plgd & comft. stat. B541-115M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2009-03-27 | 2010-03-26 | 2013-03-27 | 2022-02-11
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GATEW6 | Gateway Estates -Cleveland Pk playground (B547- 114M) | 1 | DEVELOP SCOPE | 2013-08-20 | 2013-11-17 | 2013-08-20 | 2013-11-17
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GATEW6 | Gateway Estates -Cleveland Pk playground (B547- 114M) | 2 | DESIGN | 2013-11-18 | 2014-02-15 | 2013-11-18 | 2014-02-15
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GATEW6 | Gateway Estates -Cleveland Pk playground (B547- 114M) | 3 | BID/ REGISTER CONTRACT | 2014-02-16 | 2014-05-16 | 2014-02-16 | 2014-05-16
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GATEW6 | Gateway Estates -Cleveland Pk playground (B547- 114M) | 4 | CONSTRUCTION | 2014-05-17 | 2015-05-16 | 2014-05-17 | 2015-05-16
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GATEW6 | Gateway Estates -Cleveland Pk playground (B547- 114M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-05-17 | 2016-05-15 | 2015-05-17 | 2025-09-16
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GATEWA | Gateway Estates- Plumbing B541-315M | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2015-09-29 | 2015-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GATEWA | Gateway Estates- Plumbing B541-315M | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2015-12-28 | 2016-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GATEWA | Gateway Estates- Plumbing B541-315M | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GATEWA | Gateway Estates- Plumbing B541-315M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2017-03-27 | 2018-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GPWB10 | GPWB - Sternberg Pk Dog Run - B055-108M | 1 | DEVELOP SCOPE | 2008-07-01 | 2008-09-28 | 2008-07-01 | 2008-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GPWB10 | GPWB - Sternberg Pk Dog Run - B055-108M | 2 | DESIGN | 2008-09-29 | 2008-12-27 | 2008-09-29 | 2008-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GPWB10 | GPWB - Sternberg Pk Dog Run - B055-108M | 3 | BID/ REGISTER CONTRACT | 2008-12-28 | 2009-03-27 | 2008-12-28 | 2009-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GPWB10 | GPWB - Sternberg Pk Dog Run - B055-108M | 4 | CONSTRUCTION | 2009-03-28 | 2010-03-27 | 2009-03-28 | 2010-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GPWB10 | GPWB - Sternberg Pk Dog Run - B055-108M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2010-03-28 | 2011-03-27 | 2010-03-28 | 2013-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GPWB25 | GPWB-Bushwick Inlet Park- Motiva Parcel Remediation | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GPWB25 | GPWB-Bushwick Inlet Park- Motiva Parcel Remediation | 2 | DESIGN | 2017-12-28 | 2019-03-22 | 2017-12-28 | 2019-03-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GPWB25 | GPWB-Bushwick Inlet Park- Motiva Parcel Remediation | 3 | BID/ REGISTER CONTRACT | 2019-03-23 | 2019-12-17 | 2019-03-23 | 2019-12-17
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GPWB25 | GPWB-Bushwick Inlet Park- Motiva Parcel Remediation | 4 | CONSTRUCTION | 2019-12-18 | 2021-12-16 | 2019-12-18 | 2021-12-16
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GPWB25 | GPWB-Bushwick Inlet Park- Motiva Parcel Remediation | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-12-17 | 2022-12-16 | 2021-12-17 | 2022-12-16
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GPWBKT | GPWB- 50 Kent Development | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GPWBKT | GPWB- 50 Kent Development | 2 | DESIGN | 2017-12-28 | 2019-03-22 | 2017-12-28 | 2019-03-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GPWBKT | GPWB- 50 Kent Development | 3 | BID/ REGISTER CONTRACT | 2019-03-23 | 2019-12-17 | 2019-03-23 | 2019-12-17
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GPWBKT | GPWB- 50 Kent Development | 4 | CONSTRUCTION | 2019-12-18 | 2021-12-16 | 2019-12-18 | 2021-12-16
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GPWBKT | GPWB- 50 Kent Development | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-12-17 | 2022-12-16 | 2021-12-17 | 2022-12-16
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GTGRDN | RPZ installation at various sites in Brooklyn BG-618M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GTGRDN | RPZ installation at various sites in Brooklyn BG-618M | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GTGRDN | RPZ installation at various sites in Brooklyn BG-618M | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GTGRDN | RPZ installation at various sites in Brooklyn BG-618M | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GTGRDN | RPZ installation at various sites in Brooklyn BG-618M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GTGRDN | RPZ installation at various sites in Brooklyn BG-618M | 6 | DEVELOP SCOPE | 2021-09-23 | 2022-03-21 | 2020-09-23 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GTGRDN | RPZ installation at various sites in Brooklyn BG-618M | 7 | DESIGN | 2022-03-22 | 2023-03-21 | 2020-09-23 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GTGRDN | RPZ installation at various sites in Brooklyn BG-618M | 8 | BID/ REGISTER CONTRACT | 2023-03-22 | 2023-12-16 | 2020-09-23 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GTGRDN | RPZ installation at various sites in Brooklyn BG-618M | 9 | CONSTRUCTION | 2023-12-17 | 2024-12-15 | 2020-09-23 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GTGRDN | RPZ installation at various sites in Brooklyn BG-618M | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-12-16 | 2025-12-15 | 2020-09-23 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2HOOPER | Hooper Street Grove - Install Perimeter Fence | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2HOOPER | Hooper Street Grove - Install Perimeter Fence | 2 | DESIGN | 2018-12-28 | 2020-06-24 | 2018-12-28 | 2020-06-24
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2HOOPER | Hooper Street Grove - Install Perimeter Fence | 3 | BID/ REGISTER CONTRACT | 2020-06-25 | 2021-03-21 | 2020-06-25 | 2021-03-21
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2HOOPER | Hooper Street Grove - Install Perimeter Fence | 4 | CONSTRUCTION | 2021-03-22 | 2022-09-17 | 2021-03-22 | 2022-09-17
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2HOOPER | Hooper Street Grove - Install Perimeter Fence | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-18 | 2023-09-17 | 2022-09-18 | 2023-09-17
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2HWRDPL | POOL | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2HWRDPL | POOL | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2HWRDPL | POOL | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2HWRDPL | POOL | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2HWRDPL | POOL | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2LINDTF | Linden Park Synthetic Turf Field and Track (B214-117M) | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2017-07-01 | 2017-10-11
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2LINDTF | Linden Park Synthetic Turf Field and Track (B214-117M) | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2017-10-12 | 2018-12-01
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2LINDTF | Linden Park Synthetic Turf Field and Track (B214-117M) | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2018-02-14 | 2018-07-11
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2LINDTF | Linden Park Synthetic Turf Field and Track (B214-117M) | 4 | CONSTRUCTION | 2018-09-24 | 2019-09-23 | 2018-10-15 | 2019-07-11
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2LINDTF | Linden Park Synthetic Turf Field and Track (B214-117M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-24 | 2020-09-22 | 2019-07-12 | 2023-07-10
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2LITCHF | Litchfield Villa - Renovations | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2LITCHF | Litchfield Villa - Renovations | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2LITCHF | Litchfield Villa - Renovations | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2LITCHF | Litchfield Villa - Renovations | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2LITCHF | Litchfield Villa - Renovations | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2MRNPRK | MARINE PARK PLAYGROUND | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2MRNPRK | MARINE PARK PLAYGROUND | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2MRNPRK | MARINE PARK PLAYGROUND | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2MRNPRK | MARINE PARK PLAYGROUND | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2MRNPRK | MARINE PARK PLAYGROUND | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2OWLHD1 | OWLS HEAD PARK - PLAYGROUND RECONSTRUCTION | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2OWLHD1 | OWLS HEAD PARK - PLAYGROUND RECONSTRUCTION | 2 | DESIGN | 2019-12-28 | 2021-12-26 | 2019-12-28 | 2021-12-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2OWLHD1 | OWLS HEAD PARK - PLAYGROUND RECONSTRUCTION | 3 | BID/ REGISTER CONTRACT | 2021-12-27 | 2022-09-22 | 2021-12-27 | 2022-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2OWLHD1 | OWLS HEAD PARK - PLAYGROUND RECONSTRUCTION | 4 | CONSTRUCTION | 2022-09-23 | 2024-09-21 | 2022-09-23 | 2024-09-21
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2OWLHD1 | OWLS HEAD PARK - PLAYGROUND RECONSTRUCTION | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-09-22 | 2025-09-21 | 2024-09-22 | 2025-09-21
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PDBRC2 | Brownsville Rec Ctr RC B270-214M | 1 | DEVELOP SCOPE | 2014-07-01 | 2014-09-28 | 2014-07-01 | 2014-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PDBRC2 | Brownsville Rec Ctr RC B270-214M | 2 | DESIGN | 2014-09-29 | 2014-12-27 | 2014-09-29 | 2014-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PDBRC2 | Brownsville Rec Ctr RC B270-214M | 3 | BID/ REGISTER CONTRACT | 2014-12-28 | 2015-03-27 | 2014-12-28 | 2015-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PDBRC2 | Brownsville Rec Ctr RC B270-214M | 4 | CONSTRUCTION | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2016-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PDBRC2 | Brownsville Rec Ctr RC B270-214M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2024-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PDSSRC | Sunset Pk Rec Ctr RC B087-115M | 1 | DEVELOP SCOPE | 2014-07-01 | 2014-09-28 | 2014-07-01 | 2014-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PDSSRC | Sunset Pk Rec Ctr RC B087-115M | 2 | DESIGN | 2014-09-29 | 2014-12-27 | 2014-09-29 | 2014-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PDSSRC | Sunset Pk Rec Ctr RC B087-115M | 3 | BID/ REGISTER CONTRACT | 2014-12-28 | 2015-03-27 | 2014-12-28 | 2015-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PDSSRC | Sunset Pk Rec Ctr RC B087-115M | 4 | CONSTRUCTION | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2016-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PDSSRC | Sunset Pk Rec Ctr RC B087-115M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2024-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PEDPLZ | Public Place -Pedestrian Plaza-Eldert & liberty | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PEDPLZ | Public Place -Pedestrian Plaza-Eldert & liberty | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2016-12-28 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PEDPLZ | Public Place -Pedestrian Plaza-Eldert & liberty | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2017-12-28 | 2018-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PEDPLZ | Public Place -Pedestrian Plaza-Eldert & liberty | 4 | CONSTRUCTION | 2018-09-24 | 2019-09-23 | 2018-09-24 | 2019-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PEDPLZ | Public Place -Pedestrian Plaza-Eldert & liberty | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2023-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PEPWIN | Prospect Park Parade Ground PEP HQ window replace | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PEPWIN | Prospect Park Parade Ground PEP HQ window replace | 2 | DESIGN | 2019-12-28 | 2021-12-26 | 2019-12-28 | 2021-12-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PEPWIN | Prospect Park Parade Ground PEP HQ window replace | 3 | BID/ REGISTER CONTRACT | 2021-12-27 | 2022-09-22 | 2021-12-27 | 2022-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PEPWIN | Prospect Park Parade Ground PEP HQ window replace | 4 | CONSTRUCTION | 2022-09-23 | 2024-09-21 | 2022-09-23 | 2024-09-21
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PEPWIN | Prospect Park Parade Ground PEP HQ window replace | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-09-22 | 2025-09-21 | 2024-09-22 | 2025-09-21
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PGRD11 | MULTISITE- PAVEMTS,TENNIS CTS, BB CTS, FENCING (BG-711M) | 1 | DEVELOP SCOPE | 2012-01-01 | 2012-03-30 | 2012-01-01 | 2012-03-30
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PGRD11 | MULTISITE- PAVEMTS,TENNIS CTS, BB CTS, FENCING (BG-711M) | 2 | DESIGN | 2012-03-31 | 2012-06-28 | 2012-03-31 | 2012-06-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PGRD11 | MULTISITE- PAVEMTS,TENNIS CTS, BB CTS, FENCING (BG-711M) | 3 | BID/ REGISTER CONTRACT | 2012-06-29 | 2012-09-26 | 2012-06-29 | 2012-09-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PGRD11 | MULTISITE- PAVEMTS,TENNIS CTS, BB CTS, FENCING (BG-711M) | 4 | CONSTRUCTION | 2012-09-27 | 2013-09-26 | 2012-09-27 | 2013-09-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PGRD11 | MULTISITE- PAVEMTS,TENNIS CTS, BB CTS, FENCING (BG-711M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-09-27 | 2014-09-26 | 2013-09-27 | 2024-06-02
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PKTR21 | FY21-Park Trees - Brooklyn | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PKTR21 | FY21-Park Trees - Brooklyn | 2 | DESIGN | 2019-12-28 | 2020-06-24 | 2019-12-28 | 2020-06-24
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PKTR21 | FY21-Park Trees - Brooklyn | 3 | BID/ REGISTER CONTRACT | 2020-06-25 | 2021-03-21 | 2020-06-25 | 2021-03-21
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PKTR21 | FY21-Park Trees - Brooklyn | 4 | CONSTRUCTION | 2021-03-22 | 2022-09-12 | 2021-03-22 | 2022-09-12
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PKTR21 | FY21-Park Trees - Brooklyn | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-13 | 2024-09-11 | 2022-09-13 | 2024-09-11
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PLAY13 | MULTISITE- OCEAN HILL PLGD, WINGATE, MLK SPRAY SHWER BG-114M | 1 | DEVELOP SCOPE | 2013-02-01 | 2013-05-01 | 2013-02-01 | 2013-05-01
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PLAY13 | MULTISITE- OCEAN HILL PLGD, WINGATE, MLK SPRAY SHWER BG-114M | 2 | DESIGN | 2013-05-02 | 2013-07-30 | 2013-05-02 | 2013-07-30
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PLAY13 | MULTISITE- OCEAN HILL PLGD, WINGATE, MLK SPRAY SHWER BG-114M | 3 | BID/ REGISTER CONTRACT | 2013-07-31 | 2013-10-28 | 2013-07-31 | 2013-10-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PLAY13 | MULTISITE- OCEAN HILL PLGD, WINGATE, MLK SPRAY SHWER BG-114M | 4 | CONSTRUCTION | 2013-10-29 | 2014-10-28 | 2013-10-29 | 2014-10-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PLAY13 | MULTISITE- OCEAN HILL PLGD, WINGATE, MLK SPRAY SHWER BG-114M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-10-29 | 2015-10-28 | 2014-10-29 | 2020-10-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PLG14D | RECON. CHARLES PINNTRIANGLE - PAVE. CURBS FENCING BG-613M | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2013-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PLG14D | RECON. CHARLES PINNTRIANGLE - PAVE. CURBS FENCING BG-613M | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2013-09-29 | 2013-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PLG14D | RECON. CHARLES PINNTRIANGLE - PAVE. CURBS FENCING BG-613M | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2013-12-28 | 2014-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PLG14D | RECON. CHARLES PINNTRIANGLE - PAVE. CURBS FENCING BG-613M | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2014-03-28 | 2015-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PLG14D | RECON. CHARLES PINNTRIANGLE - PAVE. CURBS FENCING BG-613M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2023-09-15
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PLG14F | Thomas Greene Plgrd R/C -BG-613M | 2 | DESIGN | 2014-09-29 | 2014-12-27 | 2014-09-29 | 2014-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PLG14F | Thomas Greene Plgrd R/C -BG-613M | 3 | BID/ REGISTER CONTRACT | 2014-12-28 | 2015-03-27 | 2014-12-28 | 2015-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PLG14F | Thomas Greene Plgrd R/C -BG-613M | 4 | CONSTRUCTION | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2016-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PLG14F | Thomas Greene Plgrd R/C -BG-613M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PLG15E | TAAFFE - Playground Reconstruction (BG-613M) | 2 | DESIGN | 2016-12-28 | 2018-06-25 | 2016-12-28 | 2018-06-25
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PLG15E | TAAFFE - Playground Reconstruction (BG-613M) | 3 | BID/ REGISTER CONTRACT | 2018-06-26 | 2019-03-22 | 2018-06-26 | 2019-03-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PLG15E | TAAFFE - Playground Reconstruction (BG-613M) | 4 | CONSTRUCTION | 2019-03-23 | 2020-09-17 | 2019-03-23 | 2020-09-17
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PLG15E | TAAFFE - Playground Reconstruction (BG-613M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-18 | 2021-09-17 | 2020-09-18 | 2021-09-17
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PLG15H | SPERANDEO PARK- RC the Courts B163-115M | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2015-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PLG15H | SPERANDEO PARK- RC the Courts B163-115M | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2015-09-29 | 2015-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PLG15H | SPERANDEO PARK- RC the Courts B163-115M | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2015-12-28 | 2016-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PLG15H | SPERANDEO PARK- RC the Courts B163-115M | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PLG15H | SPERANDEO PARK- RC the Courts B163-115M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2017-03-27 | 2018-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PLG17A | Sunset Park- RC Spray Show. Vaults-BG-715MA | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2016-12-28 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PLG17A | Sunset Park- RC Spray Show. Vaults-BG-715MA | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2017-12-28 | 2018-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PLG17A | Sunset Park- RC Spray Show. Vaults-BG-715MA | 4 | CONSTRUCTION | 2018-09-24 | 2019-09-23 | 2018-09-24 | 2019-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PLG17A | Sunset Park- RC Spray Show. Vaults-BG-715MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PLG17A | Sunset Park- RC Spray Show. Vaults-BG-715MA | 6 | DEVELOP SCOPE | 2019-09-24 | 2020-09-22 | 2020-09-23 | 2021-03-21
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PLG17A | Sunset Park- RC Spray Show. Vaults-BG-715MA | 7 | DESIGN | 2019-09-24 | 2020-09-22 | 2021-03-22 | 2022-06-19
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PLG17A | Sunset Park- RC Spray Show. Vaults-BG-715MA | 8 | BID/ REGISTER CONTRACT | 2019-09-24 | 2020-09-22 | 2022-06-20 | 2023-03-16
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PLG17A | Sunset Park- RC Spray Show. Vaults-BG-715MA | 9 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2023-03-17 | 2024-03-15
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PLG17A | Sunset Park- RC Spray Show. Vaults-BG-715MA | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-24 | 2020-09-22 | 2024-03-16 | 2025-03-15
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PNYC01 | PlaNYC - McCarren Pk Pool & Bathhouse RC - B058-108M/408M | 1 | DEVELOP SCOPE | 2007-07-01 | 2007-09-28 | 2006-10-04 | 2007-01-01
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PNYC01 | PlaNYC - McCarren Pk Pool & Bathhouse RC - B058-108M/408M | 2 | DESIGN | 2007-09-29 | 2007-12-27 | 2007-01-02 | 2007-04-01
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PNYC01 | PlaNYC - McCarren Pk Pool & Bathhouse RC - B058-108M/408M | 3 | BID/ REGISTER CONTRACT | 2007-12-28 | 2008-03-26 | 2007-04-02 | 2007-06-30
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PNYC01 | PlaNYC - McCarren Pk Pool & Bathhouse RC - B058-108M/408M | 4 | CONSTRUCTION | 2008-03-27 | 2009-03-26 | 2007-07-01 | 2008-06-29
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PNYC01 | PlaNYC - McCarren Pk Pool & Bathhouse RC - B058-108M/408M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2009-03-27 | 2010-03-26 | 2008-06-30 | 2021-12-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PNYC05 | PlaNYC - Calvert Vaux CS/M&O bldg (B125-112M) | 1 | DEVELOP SCOPE | 2012-03-01 | 2012-05-29 | 2012-03-01 | 2012-05-29
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PNYC05 | PlaNYC - Calvert Vaux CS/M&O bldg (B125-112M) | 2 | DESIGN | 2012-05-30 | 2012-08-27 | 2015-09-01 | 2016-03-31
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PNYC05 | PlaNYC - Calvert Vaux CS/M&O bldg (B125-112M) | 3 | BID/ REGISTER CONTRACT | 2012-08-28 | 2012-11-25 | 2016-04-01 | 2016-06-30
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PNYC05 | PlaNYC - Calvert Vaux CS/M&O bldg (B125-112M) | 4 | CONSTRUCTION | 2012-11-26 | 2013-11-25 | 2016-07-01 | 2017-06-30
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PNYC05 | PlaNYC - Calvert Vaux CS/M&O bldg (B125-112M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-11-26 | 2014-11-25 | 2017-07-01 | 2022-06-30
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PNYCB3 | PlaNYC-FY09 Playgrounds BG-2309M | 1 | DEVELOP SCOPE | 2011-07-01 | 2011-09-28 | 2011-07-01 | 2011-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PNYCB3 | PlaNYC-FY09 Playgrounds BG-2309M | 2 | DESIGN | 2011-09-29 | 2011-12-27 | 2011-09-29 | 2011-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PNYCB3 | PlaNYC-FY09 Playgrounds BG-2309M | 3 | BID/ REGISTER CONTRACT | 2011-12-28 | 2012-03-26 | 2011-12-28 | 2012-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PNYCB3 | PlaNYC-FY09 Playgrounds BG-2309M | 4 | CONSTRUCTION | 2012-03-27 | 2013-03-26 | 2012-03-27 | 2013-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PNYCB3 | PlaNYC-FY09 Playgrounds BG-2309M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-03-27 | 2014-03-26 | 2013-03-27 | 2022-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2POWPRK | POWELL PARK PLAYGROUND | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2POWPRK | POWELL PARK PLAYGROUND | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2POWPRK | POWELL PARK PLAYGROUND | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2POWPRK | POWELL PARK PLAYGROUND | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2POWPRK | POWELL PARK PLAYGROUND | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PPANEP | Northeast Paths - Prospect Park Alliance | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PPANEP | Northeast Paths - Prospect Park Alliance | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2016-12-28 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PPANEP | Northeast Paths - Prospect Park Alliance | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2017-12-28 | 2018-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PPANEP | Northeast Paths - Prospect Park Alliance | 4 | CONSTRUCTION | 2018-09-24 | 2019-09-23 | 2018-09-24 | 2019-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PPANEP | Northeast Paths - Prospect Park Alliance | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2023-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PPESIT | PROSPECT PARK EXPRESSWAY SITTING AREA RC | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PPESIT | PROSPECT PARK EXPRESSWAY SITTING AREA RC | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PPESIT | PROSPECT PARK EXPRESSWAY SITTING AREA RC | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PPESIT | PROSPECT PARK EXPRESSWAY SITTING AREA RC | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PPESIT | PROSPECT PARK EXPRESSWAY SITTING AREA RC | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PWBFTG | PWOB- Fort Greene (B032-117M) | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PWBFTG | PWOB- Fort Greene (B032-117M) | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2016-12-28 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PWBFTG | PWOB- Fort Greene (B032-117M) | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2017-12-28 | 2018-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PWBFTG | PWOB- Fort Greene (B032-117M) | 4 | CONSTRUCTION | 2018-09-24 | 2019-09-23 | 2018-09-24 | 2019-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PWBFTG | PWOB- Fort Greene (B032-117M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2023-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PWBPFB | PWOB- PP Flatbush Avenue (B073-117M) | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PWBPFB | PWOB- PP Flatbush Avenue (B073-117M) | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2016-12-28 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PWBPFB | PWOB- PP Flatbush Avenue (B073-117M) | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2017-12-28 | 2018-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PWBPFB | PWOB- PP Flatbush Avenue (B073-117M) | 4 | CONSTRUCTION | 2018-09-24 | 2019-09-23 | 2018-09-24 | 2019-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PWBPFB | PWOB- PP Flatbush Avenue (B073-117M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2REGION | REQUIREMENTS - LARGE PKS -BKLYN BG-799R | 1 | DEVELOP SCOPE | 2020-07-01 | 2020-12-27 | 2020-07-01 | 2020-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2REGION | REQUIREMENTS - LARGE PKS -BKLYN BG-799R | 2 | DESIGN | 2020-12-28 | 2021-12-27 | 2020-12-28 | 2021-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2REGION | REQUIREMENTS - LARGE PKS -BKLYN BG-799R | 3 | BID/ REGISTER CONTRACT | 2021-12-28 | 2022-09-23 | 2021-12-28 | 2022-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2REGION | REQUIREMENTS - LARGE PKS -BKLYN BG-799R | 4 | CONSTRUCTION | 2022-09-24 | 2023-09-23 | 2022-09-24 | 2023-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2REGION | REQUIREMENTS - LARGE PKS -BKLYN BG-799R | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-24 | 2024-09-22 | 2023-09-24 | 2024-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2RHBALL | Red Hook ball fields B126-116M | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2015-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2RHBALL | Red Hook ball fields B126-116M | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2015-09-29 | 2015-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2RHBALL | Red Hook ball fields B126-116M | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2015-12-28 | 2016-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2RHBALL | Red Hook ball fields B126-116M | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2RHBALL | Red Hook ball fields B126-116M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2017-03-27 | 2022-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2SEAGTE | SEAGATE SHORELINE REMEDIATION | 1 | DEVELOP SCOPE | 2011-07-01 | 2011-09-28 | 2011-07-01 | 2011-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2SEAGTE | SEAGATE SHORELINE REMEDIATION | 2 | DESIGN | 2011-09-29 | 2011-12-27 | 2011-09-29 | 2011-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2SEAGTE | SEAGATE SHORELINE REMEDIATION | 3 | BID/ REGISTER CONTRACT | 2011-12-28 | 2012-03-26 | 2011-12-28 | 2012-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2SEAGTE | SEAGATE SHORELINE REMEDIATION | 4 | CONSTRUCTION | 2012-03-27 | 2013-03-26 | 2012-03-27 | 2013-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2SEAGTE | SEAGATE SHORELINE REMEDIATION | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-03-27 | 2014-03-26 | 2013-03-27 | 2023-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2SNSTRW | Commodore Barry Park C.S | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2SNSTRW | Commodore Barry Park C.S | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2SNSTRW | Commodore Barry Park C.S | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2SNSTRW | Commodore Barry Park C.S | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2SNSTRW | Commodore Barry Park C.S | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2SNTGNS | Senerity Gardens | 1 | DEVELOP SCOPE | 2020-07-01 | 2020-12-27 | 2020-07-01 | 2020-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2SNTGNS | Senerity Gardens | 2 | DESIGN | 2020-12-28 | 2021-12-27 | 2020-12-28 | 2021-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2SNTGNS | Senerity Gardens | 3 | BID/ REGISTER CONTRACT | 2021-12-28 | 2022-09-23 | 2021-12-28 | 2022-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2SNTGNS | Senerity Gardens | 4 | CONSTRUCTION | 2022-09-24 | 2023-09-23 | 2022-09-24 | 2023-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2SNTGNS | Senerity Gardens | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-24 | 2024-09-22 | 2023-09-24 | 2024-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2STFBSH | Synthetic Turf Field Reconstruction at Bushwick Inlet Pk, BK | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2STFBSH | Synthetic Turf Field Reconstruction at Bushwick Inlet Pk, BK | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2STFBSH | Synthetic Turf Field Reconstruction at Bushwick Inlet Pk, BK | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2STFBSH | Synthetic Turf Field Reconstruction at Bushwick Inlet Pk, BK | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2STFBSH | Synthetic Turf Field Reconstruction at Bushwick Inlet Pk, BK | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2STFHM | Hamilton-Metz Field Synthetic Turf Field Reconstruction | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2STFHM | Hamilton-Metz Field Synthetic Turf Field Reconstruction | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2STFHM | Hamilton-Metz Field Synthetic Turf Field Reconstruction | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2STFHM | Hamilton-Metz Field Synthetic Turf Field Reconstruction | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2STFHM | Hamilton-Metz Field Synthetic Turf Field Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2STFLEF | Synthetic Turf Field Recon at Quaker Parrot Pk, BK | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2STFLEF | Synthetic Turf Field Recon at Quaker Parrot Pk, BK | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2STFLEF | Synthetic Turf Field Recon at Quaker Parrot Pk, BK | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2STFLEF | Synthetic Turf Field Recon at Quaker Parrot Pk, BK | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2STFLEF | Synthetic Turf Field Recon at Quaker Parrot Pk, BK | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2STFMH | Maria Hernandez Park - Synthetic Turf Field (B016-118M) | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2STFMH | Maria Hernandez Park - Synthetic Turf Field (B016-118M) | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2STFMH | Maria Hernandez Park - Synthetic Turf Field (B016-118M) | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2STFMH | Maria Hernandez Park - Synthetic Turf Field (B016-118M) | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2STFMH | Maria Hernandez Park - Synthetic Turf Field (B016-118M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2SUCSGN | Success Garden - Park Renovation | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2SUCSGN | Success Garden - Park Renovation | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2SUCSGN | Success Garden - Park Renovation | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2SUCSGN | Success Garden - Park Renovation | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2SUCSGN | Success Garden - Park Renovation | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE14A | FY14 Street Tree Planting, Brooklyn CB's 1 - 6 & 8 - BG-813M | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2013-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE14A | FY14 Street Tree Planting, Brooklyn CB's 1 - 6 & 8 - BG-813M | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2013-09-29 | 2013-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE14A | FY14 Street Tree Planting, Brooklyn CB's 1 - 6 & 8 - BG-813M | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2013-12-28 | 2014-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE14A | FY14 Street Tree Planting, Brooklyn CB's 1 - 6 & 8 - BG-813M | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2014-03-28 | 2015-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE14A | FY14 Street Tree Planting, Brooklyn CB's 1 - 6 & 8 - BG-813M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2022-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE15A | FY15 Street Tree Planting, Bkln CB 1-4, BG-115M | 2 | DESIGN | 2014-09-29 | 2014-12-27 | 2014-09-29 | 2014-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE15A | FY15 Street Tree Planting, Bkln CB 1-4, BG-115M | 3 | BID/ REGISTER CONTRACT | 2014-12-28 | 2015-03-27 | 2014-12-28 | 2015-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE15A | FY15 Street Tree Planting, Bkln CB 1-4, BG-115M | 4 | CONSTRUCTION | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2016-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE15A | FY15 Street Tree Planting, Bkln CB 1-4, BG-115M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE15B | FY 15 Street Tree Planting - Bkln CB 6,7,10,12, BG-315M | 1 | DEVELOP SCOPE | 2014-07-01 | 2014-09-28 | 2014-07-01 | 2014-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE15B | FY 15 Street Tree Planting - Bkln CB 6,7,10,12, BG-315M | 2 | DESIGN | 2014-09-29 | 2014-12-27 | 2014-09-29 | 2014-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE15B | FY 15 Street Tree Planting - Bkln CB 6,7,10,12, BG-315M | 3 | BID/ REGISTER CONTRACT | 2014-12-28 | 2015-03-27 | 2014-12-28 | 2015-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE15B | FY 15 Street Tree Planting - Bkln CB 6,7,10,12, BG-315M | 4 | CONSTRUCTION | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2016-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE15B | FY 15 Street Tree Planting - Bkln CB 6,7,10,12, BG-315M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2022-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE18A | FY18 Street Tree Brooklyn1,2,3,4,16, BG- | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE18A | FY18 Street Tree Brooklyn1,2,3,4,16, BG- | 2 | DESIGN | 2017-12-28 | 2018-06-25 | 2017-12-28 | 2018-06-25
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE18A | FY18 Street Tree Brooklyn1,2,3,4,16, BG- | 3 | BID/ REGISTER CONTRACT | 2018-06-26 | 2019-03-22 | 2018-06-26 | 2019-03-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE18A | FY18 Street Tree Brooklyn1,2,3,4,16, BG- | 4 | CONSTRUCTION | 2019-03-23 | 2020-09-12 | 2019-03-23 | 2020-09-12
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE18A | FY18 Street Tree Brooklyn1,2,3,4,16, BG- | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-13 | 2022-09-12 | 2020-09-13 | 2022-09-12
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE18B | FY18 Street Tree Brooklyn1,5,14,18 | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE18B | FY18 Street Tree Brooklyn1,5,14,18 | 2 | DESIGN | 2017-12-28 | 2018-06-25 | 2017-12-28 | 2018-06-25
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE18B | FY18 Street Tree Brooklyn1,5,14,18 | 3 | BID/ REGISTER CONTRACT | 2018-06-26 | 2019-03-22 | 2018-06-26 | 2019-03-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE18B | FY18 Street Tree Brooklyn1,5,14,18 | 4 | CONSTRUCTION | 2019-03-23 | 2020-09-12 | 2019-03-23 | 2020-09-12
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE18B | FY18 Street Tree Brooklyn1,5,14,18 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-13 | 2022-09-12 | 2020-09-13 | 2022-09-12
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE18C | FY18 Street Tree Brooklyn6,7,9,12 | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE18C | FY18 Street Tree Brooklyn6,7,9,12 | 2 | DESIGN | 2017-12-28 | 2018-06-25 | 2017-12-28 | 2018-06-25
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE18C | FY18 Street Tree Brooklyn6,7,9,12 | 3 | BID/ REGISTER CONTRACT | 2018-06-26 | 2019-03-22 | 2018-06-26 | 2019-03-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE18C | FY18 Street Tree Brooklyn6,7,9,12 | 4 | CONSTRUCTION | 2019-03-23 | 2020-09-12 | 2019-03-23 | 2020-09-12
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE18C | FY18 Street Tree Brooklyn6,7,9,12 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-13 | 2022-09-12 | 2020-09-13 | 2022-09-12
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE20A | FY20 Street Tree Brooklyn1,2,3,4,, BG-319M | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE20A | FY20 Street Tree Brooklyn1,2,3,4,, BG-319M | 2 | DESIGN | 2018-12-28 | 2019-06-25 | 2018-12-28 | 2019-06-25
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE20A | FY20 Street Tree Brooklyn1,2,3,4,, BG-319M | 3 | BID/ REGISTER CONTRACT | 2019-06-26 | 2020-03-21 | 2019-06-26 | 2020-03-21
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE20A | FY20 Street Tree Brooklyn1,2,3,4,, BG-319M | 4 | CONSTRUCTION | 2020-03-22 | 2021-09-12 | 2020-03-22 | 2021-09-12
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE20A | FY20 Street Tree Brooklyn1,2,3,4,, BG-319M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-13 | 2023-09-12 | 2021-09-13 | 2023-09-12
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE20C | FY20 Street Tree Brooklyn 6,7,10,12 BG-719M | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE20C | FY20 Street Tree Brooklyn 6,7,10,12 BG-719M | 2 | DESIGN | 2018-12-28 | 2019-06-25 | 2018-12-28 | 2019-06-25
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE20C | FY20 Street Tree Brooklyn 6,7,10,12 BG-719M | 3 | BID/ REGISTER CONTRACT | 2019-06-26 | 2020-03-21 | 2019-06-26 | 2020-03-21
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE20C | FY20 Street Tree Brooklyn 6,7,10,12 BG-719M | 4 | CONSTRUCTION | 2020-03-22 | 2021-09-12 | 2020-03-22 | 2021-09-12
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE20C | FY20 Street Tree Brooklyn 6,7,10,12 BG-719M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-13 | 2023-09-12 | 2021-09-13 | 2023-09-12
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE20E | FY20 Street Tree Brooklyn 11,13 BG-419M | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE20E | FY20 Street Tree Brooklyn 11,13 BG-419M | 2 | DESIGN | 2018-12-28 | 2019-06-25 | 2018-12-28 | 2019-06-25
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE20E | FY20 Street Tree Brooklyn 11,13 BG-419M | 3 | BID/ REGISTER CONTRACT | 2019-06-26 | 2020-03-21 | 2019-06-26 | 2020-03-21
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE20E | FY20 Street Tree Brooklyn 11,13 BG-419M | 4 | CONSTRUCTION | 2020-03-22 | 2021-09-12 | 2020-03-22 | 2021-09-12
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE20E | FY20 Street Tree Brooklyn 11,13 BG-419M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-13 | 2023-09-12 | 2021-09-13 | 2023-09-12
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE21A | FY21 Street Tree Brooklyn13,4,,5,16 BG- | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE21A | FY21 Street Tree Brooklyn13,4,,5,16 BG- | 2 | DESIGN | 2019-12-28 | 2020-06-24 | 2019-12-28 | 2020-06-24
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE21A | FY21 Street Tree Brooklyn13,4,,5,16 BG- | 3 | BID/ REGISTER CONTRACT | 2020-06-25 | 2021-03-21 | 2020-06-25 | 2021-03-21
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE21A | FY21 Street Tree Brooklyn13,4,,5,16 BG- | 4 | CONSTRUCTION | 2021-03-22 | 2022-09-12 | 2021-03-22 | 2022-09-12
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE21A | FY21 Street Tree Brooklyn13,4,,5,16 BG- | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-13 | 2024-09-11 | 2022-09-13 | 2024-09-11
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE21B | FY21 Street Tree Brooklyn2,6,7,10 BG- | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE21B | FY21 Street Tree Brooklyn2,6,7,10 BG- | 2 | DESIGN | 2019-12-28 | 2020-06-24 | 2019-12-28 | 2020-06-24
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE21B | FY21 Street Tree Brooklyn2,6,7,10 BG- | 3 | BID/ REGISTER CONTRACT | 2020-06-25 | 2021-03-21 | 2020-06-25 | 2021-03-21
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE21B | FY21 Street Tree Brooklyn2,6,7,10 BG- | 4 | CONSTRUCTION | 2021-03-22 | 2022-09-12 | 2021-03-22 | 2022-09-12
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE21B | FY21 Street Tree Brooklyn2,6,7,10 BG- | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-13 | 2024-09-11 | 2022-09-13 | 2024-09-11
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE21C | FY21 Street Tree Brooklyn11,13,15 BG- | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE21C | FY21 Street Tree Brooklyn11,13,15 BG- | 2 | DESIGN | 2019-12-28 | 2020-06-24 | 2019-12-28 | 2020-06-24
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE21C | FY21 Street Tree Brooklyn11,13,15 BG- | 3 | BID/ REGISTER CONTRACT | 2020-06-25 | 2021-03-21 | 2020-06-25 | 2021-03-21
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE21C | FY21 Street Tree Brooklyn11,13,15 BG- | 4 | CONSTRUCTION | 2021-03-22 | 2022-09-12 | 2021-03-22 | 2022-09-12
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE21C | FY21 Street Tree Brooklyn11,13,15 BG- | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-13 | 2024-09-11 | 2022-09-13 | 2024-09-11
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE21D | FY21 Street Tree Brooklyn12,14 BG- | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE21D | FY21 Street Tree Brooklyn12,14 BG- | 2 | DESIGN | 2019-12-28 | 2020-06-24 | 2019-12-28 | 2020-06-24
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE21D | FY21 Street Tree Brooklyn12,14 BG- | 3 | BID/ REGISTER CONTRACT | 2020-06-25 | 2021-03-21 | 2020-06-25 | 2021-03-21
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE21D | FY21 Street Tree Brooklyn12,14 BG- | 4 | CONSTRUCTION | 2021-03-22 | 2022-09-12 | 2021-03-22 | 2022-09-12
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE21D | FY21 Street Tree Brooklyn12,14 BG- | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-13 | 2024-09-11 | 2022-09-13 | 2024-09-11
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TREE22 | FY13 St Tree Planting in Bklyn CBs 1-6, 8, 9 &16 (BG-411MR) | 3 | BID/ REGISTER CONTRACT | 2012-12-28 | 2013-03-27 | 2012-12-28 | 2013-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TREE22 | FY13 St Tree Planting in Bklyn CBs 1-6, 8, 9 &16 (BG-411MR) | 4 | CONSTRUCTION | 2013-03-28 | 2014-03-27 | 2013-03-28 | 2014-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TREE22 | FY13 St Tree Planting in Bklyn CBs 1-6, 8, 9 &16 (BG-411MR) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-03-28 | 2015-03-27 | 2014-03-28 | 2015-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TREL21 | FY21 Street Trees BK CB's9,17,18 (3Y) | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TREL21 | FY21 Street Trees BK CB's9,17,18 (3Y) | 2 | DESIGN | 2019-12-28 | 2021-06-19 | 2019-12-28 | 2021-06-19
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TREL21 | FY21 Street Trees BK CB's9,17,18 (3Y) | 3 | BID/ REGISTER CONTRACT | 2021-06-20 | 2022-03-16 | 2021-06-20 | 2022-03-16
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TREL21 | FY21 Street Trees BK CB's9,17,18 (3Y) | 4 | CONSTRUCTION | 2022-03-17 | 2025-03-15 | 2022-03-17 | 2025-03-15
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TREL21 | FY21 Street Trees BK CB's9,17,18 (3Y) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-03-16 | 2027-03-15 | 2025-03-16 | 2027-03-15
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRS19A | BrooklynTree-Damaged Sidewalk R/C CB 7,10-13,15,18 | 1 | DEVELOP SCOPE | 2018-07-02 | 2018-12-28 | 2018-07-02 | 2018-12-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRS19A | BrooklynTree-Damaged Sidewalk R/C CB 7,10-13,15,18 | 2 | DESIGN | 2018-12-29 | 2019-12-28 | 2018-12-29 | 2019-12-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRS19A | BrooklynTree-Damaged Sidewalk R/C CB 7,10-13,15,18 | 3 | BID/ REGISTER CONTRACT | 2019-12-29 | 2020-09-23 | 2019-12-29 | 2020-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRS19A | BrooklynTree-Damaged Sidewalk R/C CB 7,10-13,15,18 | 4 | CONSTRUCTION | 2020-09-24 | 2022-09-23 | 2020-09-24 | 2022-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRS19A | BrooklynTree-Damaged Sidewalk R/C CB 7,10-13,15,18 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-24 | 2023-09-23 | 2022-09-24 | 2023-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRSD19 | BrooklynTree-Damaged Sidewalk R/C | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRSD19 | BrooklynTree-Damaged Sidewalk R/C | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRSD19 | BrooklynTree-Damaged Sidewalk R/C | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRSD19 | BrooklynTree-Damaged Sidewalk R/C | 4 | CONSTRUCTION | 2020-09-23 | 2022-09-22 | 2020-09-23 | 2022-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRSD19 | BrooklynTree-Damaged Sidewalk R/C | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2WPKBGH | NYCHA Kingsborough Houses Open Space Construction | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2WPKBGH | NYCHA Kingsborough Houses Open Space Construction | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2WPKBGH | NYCHA Kingsborough Houses Open Space Construction | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2WPKBGH | NYCHA Kingsborough Houses Open Space Construction | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2WPKBGH | NYCHA Kingsborough Houses Open Space Construction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2WPS228 | I.S. 228 Playground Reconstruction (BG-39100-117M) | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2WPS228 | I.S. 228 Playground Reconstruction (BG-39100-117M) | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2WPS228 | I.S. 228 Playground Reconstruction (BG-39100-117M) | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2WPS228 | I.S. 228 Playground Reconstruction (BG-39100-117M) | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2WPS228 | I.S. 228 Playground Reconstruction (BG-39100-117M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-6CADMAR | Recon Marlboro & Cadman Plaza CS | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-6CADMAR | Recon Marlboro & Cadman Plaza CS | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-6CADMAR | Recon Marlboro & Cadman Plaza CS | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-6CADMAR | Recon Marlboro & Cadman Plaza CS | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-6CADMAR | Recon Marlboro & Cadman Plaza CS | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-6PNYR01 | PlaNYC-Reforestation:Bklyn-N.Conduit/Atlantic/Sutter BG-608M | 1 | DEVELOP SCOPE | 2007-07-01 | 2007-09-28 | 2007-07-01 | 2007-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-6PNYR01 | PlaNYC-Reforestation:Bklyn-N.Conduit/Atlantic/Sutter BG-608M | 2 | DESIGN | 2007-09-29 | 2007-12-27 | 2007-09-29 | 2007-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-6PNYR01 | PlaNYC-Reforestation:Bklyn-N.Conduit/Atlantic/Sutter BG-608M | 3 | BID/ REGISTER CONTRACT | 2007-12-28 | 2008-03-26 | 2007-12-28 | 2008-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-6PNYR01 | PlaNYC-Reforestation:Bklyn-N.Conduit/Atlantic/Sutter BG-608M | 4 | CONSTRUCTION | 2008-03-27 | 2009-03-26 | 2008-03-27 | 2009-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-6PNYR01 | PlaNYC-Reforestation:Bklyn-N.Conduit/Atlantic/Sutter BG-608M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2009-03-27 | 2010-03-26 | 2009-03-27 | 2022-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-6WPEBCS | Recon War Mem bldg & Elenor Roosevelt CS | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-6WPEBCS | Recon War Mem bldg & Elenor Roosevelt CS | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-6WPEBCS | Recon War Mem bldg & Elenor Roosevelt CS | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-6WPEBCS | Recon War Mem bldg & Elenor Roosevelt CS | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-6WPEBCS | Recon War Mem bldg & Elenor Roosevelt CS | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-03 | SANDY-Emergency Clean up & Safe Up - Shore Pkway B166-313M | 1 | DEVELOP SCOPE | 2012-12-01 | 2013-02-28 | 2012-12-01 | 2013-02-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-03 | SANDY-Emergency Clean up & Safe Up - Shore Pkway B166-313M | 2 | DESIGN | 2013-03-01 | 2013-05-29 | 2013-03-01 | 2013-05-29
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-03 | SANDY-Emergency Clean up & Safe Up - Shore Pkway B166-313M | 3 | BID/ REGISTER CONTRACT | 2013-05-30 | 2013-08-27 | 2013-05-30 | 2013-08-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-03 | SANDY-Emergency Clean up & Safe Up - Shore Pkway B166-313M | 4 | CONSTRUCTION | 2013-08-28 | 2014-08-27 | 2013-08-28 | 2014-08-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-03 | SANDY-Emergency Clean up & Safe Up - Shore Pkway B166-313M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-08-28 | 2015-08-27 | 2014-08-28 | 2024-08-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-07 | SANDY- Emergency boiler work at Red Hook B126-113M | 2 | DESIGN | 2013-03-01 | 2013-05-29 | 2013-03-01 | 2013-05-29
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-07 | SANDY- Emergency boiler work at Red Hook B126-113M | 3 | BID/ REGISTER CONTRACT | 2013-05-30 | 2013-08-27 | 2013-05-30 | 2013-08-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-07 | SANDY- Emergency boiler work at Red Hook B126-113M | 4 | CONSTRUCTION | 2013-08-28 | 2014-08-27 | 2013-08-28 | 2014-08-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-07 | SANDY- Emergency boiler work at Red Hook B126-113M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-08-28 | 2015-08-27 | 2014-08-28 | 2015-08-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-12 | SANDY - Brooklyn Plgd requirements (Type 2) BG-1113M | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2013-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-12 | SANDY - Brooklyn Plgd requirements (Type 2) BG-1113M | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2013-09-29 | 2013-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-12 | SANDY - Brooklyn Plgd requirements (Type 2) BG-1113M | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2013-12-28 | 2014-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-12 | SANDY - Brooklyn Plgd requirements (Type 2) BG-1113M | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2014-03-28 | 2015-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-12 | SANDY - Brooklyn Plgd requirements (Type 2) BG-1113M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2023-05-16
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-13 | SANDY - PNP Prospect Park Alliance | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2013-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-13 | SANDY - PNP Prospect Park Alliance | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2013-09-29 | 2013-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-13 | SANDY - PNP Prospect Park Alliance | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2013-12-28 | 2014-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-13 | SANDY - PNP Prospect Park Alliance | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2014-03-28 | 2015-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-13 | SANDY - PNP Prospect Park Alliance | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2022-04-20
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-14 | SANDY- Abe Stark boilers and chillers (B169-111M) | 1 | DEVELOP SCOPE | 2013-05-14 | 2013-08-11 | 2013-05-14 | 2013-08-11
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-14 | SANDY- Abe Stark boilers and chillers (B169-111M) | 2 | DESIGN | 2013-08-12 | 2013-11-09 | 2013-08-12 | 2013-11-09
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-14 | SANDY- Abe Stark boilers and chillers (B169-111M) | 3 | BID/ REGISTER CONTRACT | 2013-11-10 | 2014-02-07 | 2013-11-10 | 2014-02-07
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-14 | SANDY- Abe Stark boilers and chillers (B169-111M) | 4 | CONSTRUCTION | 2014-02-08 | 2015-02-07 | 2014-02-08 | 2015-02-07
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-14 | SANDY- Abe Stark boilers and chillers (B169-111M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-02-08 | 2016-02-07 | 2015-02-08 | 2024-02-07
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-15 | SANDY-Nautilus Playground (Type 3 ) | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2013-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-15 | SANDY-Nautilus Playground (Type 3 ) | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2013-09-29 | 2013-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-15 | SANDY-Nautilus Playground (Type 3 ) | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2013-12-28 | 2014-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-15 | SANDY-Nautilus Playground (Type 3 ) | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2014-03-28 | 2015-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-15 | SANDY-Nautilus Playground (Type 3 ) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2025-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-16 | SANDY-Sheepshead Bay Piers Type 3 | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2013-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-16 | SANDY-Sheepshead Bay Piers Type 3 | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2013-09-29 | 2013-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-16 | SANDY-Sheepshead Bay Piers Type 3 | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2013-12-28 | 2014-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-16 | SANDY-Sheepshead Bay Piers Type 3 | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2014-03-28 | 2015-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-16 | SANDY-Sheepshead Bay Piers Type 3 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2023-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-17 | SRU-TYPE 3-MCGUIRE FIELDS SCOREBOARDS | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2013-09-28
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-17 | SRU-TYPE 3-MCGUIRE FIELDS SCOREBOARDS | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2013-09-29 | 2013-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-17 | SRU-TYPE 3-MCGUIRE FIELDS SCOREBOARDS | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2013-12-28 | 2014-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-17 | SRU-TYPE 3-MCGUIRE FIELDS SCOREBOARDS | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2014-03-28 | 2015-03-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-17 | SRU-TYPE 3-MCGUIRE FIELDS SCOREBOARDS | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2019-03-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-21 | SANDY - Tree removals -Brooklyn CB 7-18 BG-614M | 1 | DEVELOP SCOPE | 2014-01-01 | 2014-03-31 | 2014-01-01 | 2014-03-31
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-21 | SANDY - Tree removals -Brooklyn CB 7-18 BG-614M | 2 | DESIGN | 2014-04-01 | 2014-06-29 | 2014-04-01 | 2014-06-29
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-21 | SANDY - Tree removals -Brooklyn CB 7-18 BG-614M | 3 | BID/ REGISTER CONTRACT | 2014-06-30 | 2014-09-27 | 2014-06-30 | 2014-09-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-21 | SANDY - Tree removals -Brooklyn CB 7-18 BG-614M | 4 | CONSTRUCTION | 2014-09-28 | 2015-09-27 | 2014-09-28 | 2015-09-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-21 | SANDY - Tree removals -Brooklyn CB 7-18 BG-614M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-09-28 | 2016-09-26 | 2015-09-28 | 2023-09-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-25 | Abe Stark - Non-Boiler Repair | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-25 | Abe Stark - Non-Boiler Repair | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-25 | Abe Stark - Non-Boiler Repair | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-25 | Abe Stark - Non-Boiler Repair | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-25 | Abe Stark - Non-Boiler Repair | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2024-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-26 | Prospect Pk - Lily Pond & Pool Viewing Platform Repair | 1 | DEVELOP SCOPE | 2016-08-01 | 2017-01-27 | 2016-08-01 | 2017-01-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-26 | Prospect Pk - Lily Pond & Pool Viewing Platform Repair | 2 | DESIGN | 2017-01-28 | 2018-01-27 | 2017-01-28 | 2018-01-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-26 | Prospect Pk - Lily Pond & Pool Viewing Platform Repair | 3 | BID/ REGISTER CONTRACT | 2018-01-28 | 2018-10-24 | 2018-01-28 | 2018-10-24
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-26 | Prospect Pk - Lily Pond & Pool Viewing Platform Repair | 4 | CONSTRUCTION | 2018-10-25 | 2019-10-24 | 2018-10-25 | 2019-10-24
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-26 | Prospect Pk - Lily Pond & Pool Viewing Platform Repair | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-10-25 | 2020-10-23 | 2019-10-25 | 2025-10-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-27 | CI Beach & Boardwalk - West 25 ST Maint Office Boiler | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-27 | CI Beach & Boardwalk - West 25 ST Maint Office Boiler | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-27 | CI Beach & Boardwalk - West 25 ST Maint Office Boiler | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-27 | CI Beach & Boardwalk - West 25 ST Maint Office Boiler | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-27 | CI Beach & Boardwalk - West 25 ST Maint Office Boiler | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2025-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-28 | Red Hook Recreation Center | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-28 | Red Hook Recreation Center | 2 | DESIGN | 2017-12-28 | 2019-12-27 | 2017-12-28 | 2019-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-28 | Red Hook Recreation Center | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-28 | Red Hook Recreation Center | 4 | CONSTRUCTION | 2020-09-23 | 2022-09-22 | 2020-09-23 | 2022-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-28 | Red Hook Recreation Center | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-30 | Hudson River Yacht Club | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-30 | Hudson River Yacht Club | 2 | DESIGN | 2017-12-28 | 2019-12-27 | 2017-12-28 | 2019-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-30 | Hudson River Yacht Club | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-30 | Hudson River Yacht Club | 4 | CONSTRUCTION | 2020-09-23 | 2022-09-22 | 2020-09-23 | 2022-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-30 | Hudson River Yacht Club | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-31 | Diamond Point Yacht Club | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-31 | Diamond Point Yacht Club | 2 | DESIGN | 2017-12-28 | 2019-12-27 | 2017-12-28 | 2019-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-31 | Diamond Point Yacht Club | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-31 | Diamond Point Yacht Club | 4 | CONSTRUCTION | 2020-09-23 | 2022-09-22 | 2020-09-23 | 2022-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-31 | Diamond Point Yacht Club | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-32 | Paerdegat Squadron Yacht Club | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-32 | Paerdegat Squadron Yacht Club | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2016-12-28 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-32 | Paerdegat Squadron Yacht Club | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2017-12-28 | 2018-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-32 | Paerdegat Squadron Yacht Club | 4 | CONSTRUCTION | 2018-09-24 | 2019-09-23 | 2018-09-24 | 2019-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-32 | Paerdegat Squadron Yacht Club | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2025-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-33 | Sandy - Midget Squadron Yacht Club | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-33 | Sandy - Midget Squadron Yacht Club | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2016-12-28 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-33 | Sandy - Midget Squadron Yacht Club | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2017-12-28 | 2018-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-33 | Sandy - Midget Squadron Yacht Club | 4 | CONSTRUCTION | 2018-09-24 | 2019-09-23 | 2018-09-24 | 2019-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-33 | Sandy - Midget Squadron Yacht Club | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2025-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-34 | Paerdegat Athletic Center HVAC recon. B406-114M | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-34 | Paerdegat Athletic Center HVAC recon. B406-114M | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2016-12-28 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-34 | Paerdegat Athletic Center HVAC recon. B406-114M | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2017-12-28 | 2018-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-34 | Paerdegat Athletic Center HVAC recon. B406-114M | 4 | CONSTRUCTION | 2018-09-24 | 2019-09-23 | 2018-09-24 | 2019-09-23
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-34 | Paerdegat Athletic Center HVAC recon. B406-114M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-35 | Paerdegat Athletic Center - Remaining Scope | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-35 | Paerdegat Athletic Center - Remaining Scope | 2 | DESIGN | 2017-12-28 | 2019-12-27 | 2017-12-28 | 2019-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-35 | Paerdegat Athletic Center - Remaining Scope | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-35 | Paerdegat Athletic Center - Remaining Scope | 4 | CONSTRUCTION | 2020-09-23 | 2022-09-22 | 2020-09-23 | 2022-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-35 | Paerdegat Athletic Center - Remaining Scope | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-36 | SANDY-BK | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-36 | SANDY-BK | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-36 | SANDY-BK | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-36 | SANDY-BK | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-36 | SANDY-BK | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-37 | SANDY-John Malone Community Center | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-37 | SANDY-John Malone Community Center | 2 | DESIGN | 2019-12-28 | 2021-12-26 | 2019-12-28 | 2021-12-26
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-37 | SANDY-John Malone Community Center | 3 | BID/ REGISTER CONTRACT | 2021-12-27 | 2022-09-22 | 2021-12-27 | 2022-09-22
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-37 | SANDY-John Malone Community Center | 4 | CONSTRUCTION | 2022-09-23 | 2024-09-21 | 2022-09-23 | 2024-09-21
20201123 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-37 | SANDY-John Malone Community Center | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-09-22 | 2025-09-21 | 2024-09-22 | 2025-09-21
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-768B | WATER MAIN CONNECTIONS TO SHAFT 23B - PHASE II (HWK700B) | 1 | DEVELOP SCOPE | 2009-08-18 | 2011-11-15 | 2009-08-18 | 2024-05-08
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-768B | WATER MAIN CONNECTIONS TO SHAFT 23B - PHASE II (HWK700B) | 2 | PRELIMINARY DESIGN | 2011-11-16 | 2011-11-15 | 2024-05-09 | 2024-05-08
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-768B | WATER MAIN CONNECTIONS TO SHAFT 23B - PHASE II (HWK700B) | 3 | FINAL DESIGN | 2011-11-16 | 2011-11-15 | 2023-09-06 | 2024-03-03
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-768B | WATER MAIN CONNECTIONS TO SHAFT 23B - PHASE II (HWK700B) | 4 | BID AWARD AND REGISTER CONTRCT | 2011-11-16 | 2011-11-15 | 2024-03-04 | 2024-06-01
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-768B | WATER MAIN CONNECTIONS TO SHAFT 23B - PHASE II (HWK700B) | 5 | CONSTRUCTION TO 25% | 2011-11-16 | 2011-11-15 | 2024-06-02 | 2025-06-01
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-768B | WATER MAIN CONNECTIONS TO SHAFT 23B - PHASE II (HWK700B) | 6 | CONSTRUCTION TO 50% | 2011-11-16 | 2011-11-15 | 2025-06-02 | 2026-06-01
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-768B | WATER MAIN CONNECTIONS TO SHAFT 23B - PHASE II (HWK700B) | 7 | CONSTRUCTION TO 75% | 2011-11-16 | 2011-11-15 | 2026-06-02 | 2027-06-01
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-768B | WATER MAIN CONNECTIONS TO SHAFT 23B - PHASE II (HWK700B) | 8 | ORIGINAL EQUIP & FURNISHING | 2011-11-16 | 2011-11-15 | 2027-06-02 | 2027-08-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-768B | WATER MAIN CONNECTIONS TO SHAFT 23B - PHASE II (HWK700B) | 9 | SUBSTANTIAL COMPLETION | 2011-11-16 | 2011-11-15 | 2027-08-31 | 2027-10-29
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-768B | WATER MAIN CONNECTIONS TO SHAFT 23B - PHASE II (HWK700B) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2011-11-16 | 2011-12-15 | 2027-10-30 | 2027-11-28
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-776 | WM REPLMT EAST NEW YORK AVE B/T HOWARD AV & PACIFIC ST, ETC | 1 | DEVELOP SCOPE | 2011-03-18 | 2011-06-15 | 2011-03-18 | 2011-06-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-776 | WM REPLMT EAST NEW YORK AVE B/T HOWARD AV & PACIFIC ST, ETC | 2 | PRELIMINARY DESIGN | 2011-06-16 | 2011-10-13 | 2011-06-16 | 2011-10-13
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-776 | WM REPLMT EAST NEW YORK AVE B/T HOWARD AV & PACIFIC ST, ETC | 3 | FINAL DESIGN | 2011-10-14 | 2012-04-10 | 2011-10-14 | 2012-04-10
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-776 | WM REPLMT EAST NEW YORK AVE B/T HOWARD AV & PACIFIC ST, ETC | 4 | BID AWARD AND REGISTER CONTRCT | 2012-04-11 | 2012-07-09 | 2018-03-27 | 2018-06-24
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-776 | WM REPLMT EAST NEW YORK AVE B/T HOWARD AV & PACIFIC ST, ETC | 5 | CONSTRUCTION TO 25% | 2012-07-10 | 2012-11-06 | 2018-06-25 | 2018-06-24
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-776 | WM REPLMT EAST NEW YORK AVE B/T HOWARD AV & PACIFIC ST, ETC | 6 | CONSTRUCTION TO 50% | 2012-11-07 | 2013-03-06 | 2018-06-25 | 2018-06-24
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-776 | WM REPLMT EAST NEW YORK AVE B/T HOWARD AV & PACIFIC ST, ETC | 7 | CONSTRUCTION TO 75% | 2013-03-07 | 2013-07-04 | 2018-06-25 | 2018-06-24
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-776 | WM REPLMT EAST NEW YORK AVE B/T HOWARD AV & PACIFIC ST, ETC | 8 | ORIGINAL EQUIP & FURNISHING | 2013-07-05 | 2013-10-02 | 2018-06-25 | 2018-06-24
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-776 | WM REPLMT EAST NEW YORK AVE B/T HOWARD AV & PACIFIC ST, ETC | 9 | SUBSTANTIAL COMPLETION | 2013-10-03 | 2013-12-01 | 2018-06-25 | 2018-06-24
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-776 | WM REPLMT EAST NEW YORK AVE B/T HOWARD AV & PACIFIC ST, ETC | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-12-02 | 2013-12-31 | 2020-01-26 | 2022-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-777 | WM REPLMT IN LEONARD STRET B/T DRIGGS AV AND MAUJER ST | 1 | DEVELOP SCOPE | 2010-03-18 | 2010-06-15 | 2010-03-18 | 2010-06-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-777 | WM REPLMT IN LEONARD STRET B/T DRIGGS AV AND MAUJER ST | 2 | PRELIMINARY DESIGN | 2010-06-16 | 2010-10-13 | 2010-06-16 | 2010-10-13
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-777 | WM REPLMT IN LEONARD STRET B/T DRIGGS AV AND MAUJER ST | 3 | FINAL DESIGN | 2010-10-14 | 2011-04-11 | 2010-10-14 | 2011-04-11
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-777 | WM REPLMT IN LEONARD STRET B/T DRIGGS AV AND MAUJER ST | 4 | BID AWARD AND REGISTER CONTRCT | 2011-04-12 | 2011-07-10 | 2014-03-28 | 2014-06-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-777 | WM REPLMT IN LEONARD STRET B/T DRIGGS AV AND MAUJER ST | 5 | CONSTRUCTION TO 25% | 2011-07-11 | 2011-11-07 | 2014-06-26 | 2014-06-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-777 | WM REPLMT IN LEONARD STRET B/T DRIGGS AV AND MAUJER ST | 6 | CONSTRUCTION TO 50% | 2011-11-08 | 2012-03-06 | 2014-06-26 | 2014-06-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-777 | WM REPLMT IN LEONARD STRET B/T DRIGGS AV AND MAUJER ST | 7 | CONSTRUCTION TO 75% | 2012-03-07 | 2012-07-04 | 2014-06-26 | 2014-06-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-777 | WM REPLMT IN LEONARD STRET B/T DRIGGS AV AND MAUJER ST | 8 | ORIGINAL EQUIP & FURNISHING | 2012-07-05 | 2012-10-02 | 2014-06-26 | 2014-06-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-777 | WM REPLMT IN LEONARD STRET B/T DRIGGS AV AND MAUJER ST | 9 | SUBSTANTIAL COMPLETION | 2012-10-03 | 2012-12-01 | 2014-06-26 | 2014-06-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-777 | WM REPLMT IN LEONARD STRET B/T DRIGGS AV AND MAUJER ST | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-12-02 | 2012-12-31 | 2015-12-17 | 2022-11-26
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-780 | RECON OF WM & SWR IN 5 AVE B/T 65 ST & 34 ST | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-09-28 | 2017-07-01 | 2017-09-28
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-780 | RECON OF WM & SWR IN 5 AVE B/T 65 ST & 34 ST | 2 | PRELIMINARY DESIGN | 2017-09-29 | 2018-01-26 | 2017-09-29 | 2018-01-26
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-780 | RECON OF WM & SWR IN 5 AVE B/T 65 ST & 34 ST | 3 | FINAL DESIGN | 2018-01-27 | 2018-07-25 | 2018-01-27 | 2018-07-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-780 | RECON OF WM & SWR IN 5 AVE B/T 65 ST & 34 ST | 4 | BID AWARD AND REGISTER CONTRCT | 2018-07-26 | 2018-10-23 | 2018-07-26 | 2018-10-23
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-780 | RECON OF WM & SWR IN 5 AVE B/T 65 ST & 34 ST | 5 | CONSTRUCTION TO 25% | 2018-10-24 | 2019-02-20 | 2018-10-24 | 2019-02-20
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-780 | RECON OF WM & SWR IN 5 AVE B/T 65 ST & 34 ST | 6 | CONSTRUCTION TO 50% | 2019-02-21 | 2019-06-20 | 2019-02-21 | 2019-06-20
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-780 | RECON OF WM & SWR IN 5 AVE B/T 65 ST & 34 ST | 7 | CONSTRUCTION TO 75% | 2019-06-21 | 2019-10-18 | 2019-06-21 | 2019-10-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-780 | RECON OF WM & SWR IN 5 AVE B/T 65 ST & 34 ST | 8 | ORIGINAL EQUIP & FURNISHING | 2019-10-19 | 2020-01-16 | 2019-10-19 | 2020-01-16
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-780 | RECON OF WM & SWR IN 5 AVE B/T 65 ST & 34 ST | 9 | SUBSTANTIAL COMPLETION | 2020-01-17 | 2020-03-16 | 2020-01-17 | 2020-03-16
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-780 | RECON OF WM & SWR IN 5 AVE B/T 65 ST & 34 ST | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-03-17 | 2020-04-15 | 2020-03-17 | 2027-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-782A | Reconstuction of water main & combined sewer,Tillary st. PH2 | 1 | DEVELOP SCOPE | 2017-03-01 | 2017-05-29 | 2017-03-01 | 2017-05-29
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-782A | Reconstuction of water main & combined sewer,Tillary st. PH2 | 2 | PRELIMINARY DESIGN | 2017-05-30 | 2017-09-26 | 2017-05-30 | 2017-09-26
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-782A | Reconstuction of water main & combined sewer,Tillary st. PH2 | 3 | FINAL DESIGN | 2017-09-27 | 2018-03-25 | 2017-09-27 | 2018-03-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-782A | Reconstuction of water main & combined sewer,Tillary st. PH2 | 4 | BID AWARD AND REGISTER CONTRCT | 2018-03-26 | 2018-06-23 | 2018-03-26 | 2018-06-23
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-782A | Reconstuction of water main & combined sewer,Tillary st. PH2 | 5 | CONSTRUCTION TO 25% | 2018-06-24 | 2018-10-21 | 2018-06-24 | 2018-10-21
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-782A | Reconstuction of water main & combined sewer,Tillary st. PH2 | 6 | CONSTRUCTION TO 50% | 2018-10-22 | 2019-02-18 | 2018-10-22 | 2019-02-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-782A | Reconstuction of water main & combined sewer,Tillary st. PH2 | 7 | CONSTRUCTION TO 75% | 2019-02-19 | 2019-06-18 | 2019-02-19 | 2019-06-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-782A | Reconstuction of water main & combined sewer,Tillary st. PH2 | 8 | ORIGINAL EQUIP & FURNISHING | 2019-06-19 | 2019-09-16 | 2019-06-19 | 2019-09-16
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-782A | Reconstuction of water main & combined sewer,Tillary st. PH2 | 9 | SUBSTANTIAL COMPLETION | 2019-09-17 | 2019-11-15 | 2019-09-17 | 2019-11-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-782A | Reconstuction of water main & combined sewer,Tillary st. PH2 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-11-16 | 2019-12-15 | 2019-11-16 | 2022-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-784 | RECON OF WM I& STORM SWR IN BERGEN AVE AREA | 1 | DEVELOP SCOPE | 2014-02-27 | 2014-05-27 | 2014-02-27 | 2023-05-19
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-784 | RECON OF WM I& STORM SWR IN BERGEN AVE AREA | 2 | PRELIMINARY DESIGN | 2014-05-28 | 2014-09-24 | 2023-05-20 | 2023-09-16
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-784 | RECON OF WM I& STORM SWR IN BERGEN AVE AREA | 3 | FINAL DESIGN | 2014-09-25 | 2015-03-23 | 2023-09-17 | 2024-03-14
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-784 | RECON OF WM I& STORM SWR IN BERGEN AVE AREA | 4 | BID AWARD AND REGISTER CONTRCT | 2015-03-24 | 2015-06-21 | 2024-03-15 | 2024-06-12
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-784 | RECON OF WM I& STORM SWR IN BERGEN AVE AREA | 5 | CONSTRUCTION TO 25% | 2015-06-22 | 2015-10-19 | 2024-06-13 | 2025-06-12
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-784 | RECON OF WM I& STORM SWR IN BERGEN AVE AREA | 6 | CONSTRUCTION TO 50% | 2015-10-20 | 2016-02-16 | 2025-06-13 | 2026-06-12
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-784 | RECON OF WM I& STORM SWR IN BERGEN AVE AREA | 7 | CONSTRUCTION TO 75% | 2016-02-17 | 2016-06-15 | 2026-06-13 | 2027-06-12
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-784 | RECON OF WM I& STORM SWR IN BERGEN AVE AREA | 8 | ORIGINAL EQUIP & FURNISHING | 2016-06-16 | 2016-09-13 | 2027-06-13 | 2027-09-10
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-784 | RECON OF WM I& STORM SWR IN BERGEN AVE AREA | 9 | SUBSTANTIAL COMPLETION | 2016-09-14 | 2016-11-12 | 2027-09-11 | 2027-11-09
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-784 | RECON OF WM I& STORM SWR IN BERGEN AVE AREA | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-11-13 | 2016-12-12 | 2027-11-10 | 2027-12-09
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-785B | Recon WM, Comb & San Swrs in Atlantic Ave, Ph 2 (HWD10105A) | 1 | DEVELOP SCOPE | 2017-03-01 | 2017-05-29 | 2017-03-01 | 2017-05-29
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-785B | Recon WM, Comb & San Swrs in Atlantic Ave, Ph 2 (HWD10105A) | 2 | PRELIMINARY DESIGN | 2017-05-30 | 2017-09-26 | 2017-05-30 | 2017-09-26
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-785B | Recon WM, Comb & San Swrs in Atlantic Ave, Ph 2 (HWD10105A) | 3 | FINAL DESIGN | 2017-09-27 | 2018-03-25 | 2017-09-27 | 2018-03-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-785B | Recon WM, Comb & San Swrs in Atlantic Ave, Ph 2 (HWD10105A) | 4 | BID AWARD AND REGISTER CONTRCT | 2018-03-26 | 2018-06-23 | 2018-03-26 | 2018-06-23
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-785B | Recon WM, Comb & San Swrs in Atlantic Ave, Ph 2 (HWD10105A) | 5 | CONSTRUCTION TO 25% | 2018-06-24 | 2018-10-21 | 2018-06-24 | 2018-10-21
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-785B | Recon WM, Comb & San Swrs in Atlantic Ave, Ph 2 (HWD10105A) | 6 | CONSTRUCTION TO 50% | 2018-10-22 | 2019-02-18 | 2018-10-22 | 2019-02-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-785B | Recon WM, Comb & San Swrs in Atlantic Ave, Ph 2 (HWD10105A) | 7 | CONSTRUCTION TO 75% | 2019-02-19 | 2019-06-18 | 2019-02-19 | 2019-06-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-785B | Recon WM, Comb & San Swrs in Atlantic Ave, Ph 2 (HWD10105A) | 8 | ORIGINAL EQUIP & FURNISHING | 2019-06-19 | 2019-09-16 | 2019-06-19 | 2019-09-16
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-785B | Recon WM, Comb & San Swrs in Atlantic Ave, Ph 2 (HWD10105A) | 9 | SUBSTANTIAL COMPLETION | 2019-09-17 | 2019-11-15 | 2019-09-17 | 2019-11-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-785B | Recon WM, Comb & San Swrs in Atlantic Ave, Ph 2 (HWD10105A) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-11-16 | 2019-12-15 | 2019-11-16 | 2022-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-794 | DUMBO/Vinegar Hill Area Reconstruction & Plaza. | 1 | DEVELOP SCOPE | 2014-03-01 | 2014-05-29 | 2014-03-01 | 2014-05-29
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-794 | DUMBO/Vinegar Hill Area Reconstruction & Plaza. | 2 | PRELIMINARY DESIGN | 2014-05-30 | 2014-09-26 | 2014-05-30 | 2014-09-26
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-794 | DUMBO/Vinegar Hill Area Reconstruction & Plaza. | 3 | FINAL DESIGN | 2014-09-27 | 2015-03-25 | 2014-09-27 | 2017-03-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-794 | DUMBO/Vinegar Hill Area Reconstruction & Plaza. | 4 | BID AWARD AND REGISTER CONTRCT | 2015-03-26 | 2015-06-23 | 2017-03-26 | 2017-06-23
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-794 | DUMBO/Vinegar Hill Area Reconstruction & Plaza. | 5 | CONSTRUCTION TO 25% | 2015-06-24 | 2015-10-21 | 2017-06-24 | 2017-10-21
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-794 | DUMBO/Vinegar Hill Area Reconstruction & Plaza. | 6 | CONSTRUCTION TO 50% | 2015-10-22 | 2016-02-18 | 2017-10-22 | 2018-02-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-794 | DUMBO/Vinegar Hill Area Reconstruction & Plaza. | 7 | CONSTRUCTION TO 75% | 2016-02-19 | 2016-06-17 | 2018-02-19 | 2018-06-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-794 | DUMBO/Vinegar Hill Area Reconstruction & Plaza. | 8 | ORIGINAL EQUIP & FURNISHING | 2016-06-18 | 2016-09-15 | 2018-06-19 | 2018-09-16
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-794 | DUMBO/Vinegar Hill Area Reconstruction & Plaza. | 9 | SUBSTANTIAL COMPLETION | 2016-09-16 | 2016-11-14 | 2018-09-17 | 2018-11-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-794 | DUMBO/Vinegar Hill Area Reconstruction & Plaza. | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-11-15 | 2016-12-14 | 2018-11-16 | 2023-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED798 | 72" Replacement in Flatbush Avenue between Sterling Pl & 8th | 1 | DEVELOP SCOPE | 2015-03-01 | 2015-05-29 | 2015-03-01 | 2015-05-29
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED798 | 72" Replacement in Flatbush Avenue between Sterling Pl & 8th | 2 | PRELIMINARY DESIGN | 2015-05-30 | 2015-09-26 | 2015-05-30 | 2015-09-26
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED798 | 72" Replacement in Flatbush Avenue between Sterling Pl & 8th | 3 | FINAL DESIGN | 2015-09-27 | 2016-03-24 | 2015-09-27 | 2016-03-24
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED798 | 72" Replacement in Flatbush Avenue between Sterling Pl & 8th | 4 | BID AWARD AND REGISTER CONTRCT | 2016-03-25 | 2016-06-22 | 2016-03-25 | 2016-06-22
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED798 | 72" Replacement in Flatbush Avenue between Sterling Pl & 8th | 5 | CONSTRUCTION TO 25% | 2016-06-23 | 2016-10-20 | 2016-06-23 | 2016-10-20
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED798 | 72" Replacement in Flatbush Avenue between Sterling Pl & 8th | 6 | CONSTRUCTION TO 50% | 2016-10-21 | 2017-02-17 | 2016-10-21 | 2017-02-17
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED798 | 72" Replacement in Flatbush Avenue between Sterling Pl & 8th | 7 | CONSTRUCTION TO 75% | 2017-02-18 | 2017-06-17 | 2017-02-18 | 2017-06-17
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED798 | 72" Replacement in Flatbush Avenue between Sterling Pl & 8th | 8 | ORIGINAL EQUIP & FURNISHING | 2017-06-18 | 2017-09-15 | 2017-06-18 | 2017-09-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED798 | 72" Replacement in Flatbush Avenue between Sterling Pl & 8th | 9 | SUBSTANTIAL COMPLETION | 2017-09-16 | 2017-11-14 | 2017-09-16 | 2017-11-14
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED798 | 72" Replacement in Flatbush Avenue between Sterling Pl & 8th | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-11-15 | 2017-12-14 | 2017-11-15 | 2023-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-802 | WM Replacement Hamilton Ave Gowanus Connector, BK HWK1048D | 1 | DEVELOP SCOPE | 2016-03-01 | 2016-05-29 | 2016-03-01 | 2016-05-29
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-802 | WM Replacement Hamilton Ave Gowanus Connector, BK HWK1048D | 2 | PRELIMINARY DESIGN | 2016-05-30 | 2016-09-26 | 2016-05-30 | 2016-09-26
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-802 | WM Replacement Hamilton Ave Gowanus Connector, BK HWK1048D | 3 | FINAL DESIGN | 2016-09-27 | 2017-03-25 | 2016-09-27 | 2017-03-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-802 | WM Replacement Hamilton Ave Gowanus Connector, BK HWK1048D | 4 | BID AWARD AND REGISTER CONTRCT | 2017-03-26 | 2017-06-23 | 2017-03-26 | 2017-06-23
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-802 | WM Replacement Hamilton Ave Gowanus Connector, BK HWK1048D | 5 | CONSTRUCTION TO 25% | 2017-06-24 | 2017-10-21 | 2017-06-24 | 2017-10-21
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-802 | WM Replacement Hamilton Ave Gowanus Connector, BK HWK1048D | 6 | CONSTRUCTION TO 50% | 2017-10-22 | 2018-02-18 | 2017-10-22 | 2018-02-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-802 | WM Replacement Hamilton Ave Gowanus Connector, BK HWK1048D | 7 | CONSTRUCTION TO 75% | 2018-02-19 | 2018-06-18 | 2018-02-19 | 2018-06-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-802 | WM Replacement Hamilton Ave Gowanus Connector, BK HWK1048D | 8 | ORIGINAL EQUIP & FURNISHING | 2018-06-19 | 2018-09-16 | 2018-06-19 | 2018-09-16
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-802 | WM Replacement Hamilton Ave Gowanus Connector, BK HWK1048D | 9 | SUBSTANTIAL COMPLETION | 2018-09-17 | 2018-11-15 | 2018-09-17 | 2018-11-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-802 | WM Replacement Hamilton Ave Gowanus Connector, BK HWK1048D | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-11-16 | 2018-12-15 | 2018-11-16 | 2022-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-803 | WM Replacment in Schenck Ave b/t Flatlands & Jamaica Ave, Bk | 1 | DEVELOP SCOPE | 2013-06-01 | 2014-02-25 | 0 | 0
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-803 | WM Replacment in Schenck Ave b/t Flatlands & Jamaica Ave, Bk | 2 | PRELIMINARY DESIGN | 2014-02-26 | 2015-02-20 | 0 | 0
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-803 | WM Replacment in Schenck Ave b/t Flatlands & Jamaica Ave, Bk | 3 | FINAL DESIGN | 2015-02-21 | 2016-08-13 | 0 | 0
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-803 | WM Replacment in Schenck Ave b/t Flatlands & Jamaica Ave, Bk | 4 | BID AWARD AND REGISTER CONTRCT | 2016-08-14 | 2017-05-10 | 0 | 0
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-803 | WM Replacment in Schenck Ave b/t Flatlands & Jamaica Ave, Bk | 5 | CONSTRUCTION TO 25% | 2017-05-11 | 2018-05-05 | 0 | 0
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-803 | WM Replacment in Schenck Ave b/t Flatlands & Jamaica Ave, Bk | 6 | CONSTRUCTION TO 50% | 2018-05-06 | 2019-04-30 | 0 | 0
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-803 | WM Replacment in Schenck Ave b/t Flatlands & Jamaica Ave, Bk | 7 | CONSTRUCTION TO 75% | 2019-05-01 | 2020-04-24 | 0 | 0
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-803 | WM Replacment in Schenck Ave b/t Flatlands & Jamaica Ave, Bk | 8 | ORIGINAL EQUIP & FURNISHING | 2020-04-25 | 2021-01-19 | 0 | 0
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-803 | WM Replacment in Schenck Ave b/t Flatlands & Jamaica Ave, Bk | 9 | SUBSTANTIAL COMPLETION | 2021-01-20 | 2021-07-18 | 0 | 0
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-803 | WM Replacment in Schenck Ave b/t Flatlands & Jamaica Ave, Bk | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-07-19 | 2021-10-16 | 0 | 0
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-805 | New Storm & San Swrs & WM-Gateway Estates, Phase E (HD-161E) | 1 | DEVELOP SCOPE | 2013-06-30 | 2013-09-27 | 2013-06-30 | 2013-09-27
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-805 | New Storm & San Swrs & WM-Gateway Estates, Phase E (HD-161E) | 2 | PRELIMINARY DESIGN | 2013-09-28 | 2014-01-25 | 2013-09-28 | 2014-01-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-805 | New Storm & San Swrs & WM-Gateway Estates, Phase E (HD-161E) | 3 | FINAL DESIGN | 2014-01-26 | 2014-07-24 | 2014-01-26 | 2015-07-24
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-805 | New Storm & San Swrs & WM-Gateway Estates, Phase E (HD-161E) | 4 | BID AWARD AND REGISTER CONTRCT | 2014-07-25 | 2014-10-22 | 2015-07-25 | 2015-10-22
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-805 | New Storm & San Swrs & WM-Gateway Estates, Phase E (HD-161E) | 5 | CONSTRUCTION TO 25% | 2014-10-23 | 2015-02-19 | 2015-10-23 | 2016-02-19
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-805 | New Storm & San Swrs & WM-Gateway Estates, Phase E (HD-161E) | 6 | CONSTRUCTION TO 50% | 2015-02-20 | 2015-06-19 | 2016-02-20 | 2016-06-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-805 | New Storm & San Swrs & WM-Gateway Estates, Phase E (HD-161E) | 7 | CONSTRUCTION TO 75% | 2015-06-20 | 2015-10-17 | 2016-06-19 | 2017-02-13
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-805 | New Storm & San Swrs & WM-Gateway Estates, Phase E (HD-161E) | 8 | ORIGINAL EQUIP & FURNISHING | 2015-10-18 | 2016-01-15 | 2017-02-14 | 2017-02-13
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-805 | New Storm & San Swrs & WM-Gateway Estates, Phase E (HD-161E) | 9 | SUBSTANTIAL COMPLETION | 2016-01-16 | 2016-03-15 | 2017-02-14 | 2017-04-14
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-805 | New Storm & San Swrs & WM-Gateway Estates, Phase E (HD-161E) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-16 | 2016-04-14 | 2017-04-15 | 2023-04-23
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-806 | Water Main work in Brooklyn Waterfront Greenway | 1 | DEVELOP SCOPE | 2013-06-01 | 2013-08-29 | 2017-03-01 | 2017-05-29
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-806 | Water Main work in Brooklyn Waterfront Greenway | 2 | PRELIMINARY DESIGN | 2013-08-30 | 2013-12-27 | 2017-05-30 | 2017-09-26
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-806 | Water Main work in Brooklyn Waterfront Greenway | 3 | FINAL DESIGN | 2013-12-28 | 2014-06-25 | 2017-09-27 | 2018-03-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-806 | Water Main work in Brooklyn Waterfront Greenway | 4 | BID AWARD AND REGISTER CONTRCT | 2014-06-26 | 2014-09-23 | 2018-03-26 | 2018-06-23
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-806 | Water Main work in Brooklyn Waterfront Greenway | 5 | CONSTRUCTION TO 25% | 2014-09-24 | 2015-01-21 | 2018-06-24 | 2019-02-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-806 | Water Main work in Brooklyn Waterfront Greenway | 6 | CONSTRUCTION TO 50% | 2015-01-22 | 2015-05-21 | 2019-02-19 | 2019-10-16
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-806 | Water Main work in Brooklyn Waterfront Greenway | 7 | CONSTRUCTION TO 75% | 2015-05-22 | 2015-09-18 | 2019-10-17 | 2020-06-12
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-806 | Water Main work in Brooklyn Waterfront Greenway | 8 | ORIGINAL EQUIP & FURNISHING | 2015-09-19 | 2015-12-17 | 2020-06-13 | 2020-09-10
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-806 | Water Main work in Brooklyn Waterfront Greenway | 9 | SUBSTANTIAL COMPLETION | 2015-12-18 | 2016-02-15 | 2020-09-11 | 2020-11-09
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-806 | Water Main work in Brooklyn Waterfront Greenway | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-02-16 | 2016-03-16 | 2020-11-10 | 2023-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-806 | Water Main work in Brooklyn Waterfront Greenway | 11 | DEVELOP SCOPE | 2016-03-17 | 2016-12-11 | 2020-11-10 | 2023-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-806 | Water Main work in Brooklyn Waterfront Greenway | 12 | PRELIMINARY DESIGN | 2016-12-12 | 2017-12-06 | 2020-11-10 | 2023-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-806 | Water Main work in Brooklyn Waterfront Greenway | 13 | FINAL DESIGN | 2017-12-07 | 2019-05-30 | 2020-11-10 | 2023-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-806 | Water Main work in Brooklyn Waterfront Greenway | 14 | BID AWARD AND REGISTER CONTRCT | 2019-05-31 | 2020-02-24 | 2020-11-10 | 2023-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-806 | Water Main work in Brooklyn Waterfront Greenway | 15 | CONSTRUCTION TO 25% | 2020-02-25 | 2021-02-18 | 2020-11-10 | 2023-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-806 | Water Main work in Brooklyn Waterfront Greenway | 16 | CONSTRUCTION TO 50% | 2021-02-19 | 2022-02-13 | 2020-11-10 | 2023-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-806 | Water Main work in Brooklyn Waterfront Greenway | 17 | CONSTRUCTION TO 75% | 2022-02-14 | 2023-02-08 | 2020-11-10 | 2023-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-806 | Water Main work in Brooklyn Waterfront Greenway | 18 | ORIGINAL EQUIP & FURNISHING | 2023-02-09 | 2023-11-05 | 2020-11-10 | 2023-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-806 | Water Main work in Brooklyn Waterfront Greenway | 19 | SUBSTANTIAL COMPLETION | 2023-11-06 | 2024-05-03 | 2020-11-10 | 2023-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-806 | Water Main work in Brooklyn Waterfront Greenway | 20 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-05-04 | 2024-08-01 | 2020-11-10 | 2023-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-807 | WM work in Brooklyn Waterfront Greenway. SAND1048 | 1 | DEVELOP SCOPE | 2013-06-30 | 2013-09-27 | 2013-06-30 | 2013-09-27
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-807 | WM work in Brooklyn Waterfront Greenway. SAND1048 | 2 | PRELIMINARY DESIGN | 2013-09-28 | 2014-01-25 | 2013-09-28 | 2014-01-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-807 | WM work in Brooklyn Waterfront Greenway. SAND1048 | 3 | FINAL DESIGN | 2014-01-26 | 2014-07-24 | 2014-01-26 | 2014-07-24
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-807 | WM work in Brooklyn Waterfront Greenway. SAND1048 | 4 | BID AWARD AND REGISTER CONTRCT | 2014-07-25 | 2014-10-22 | 2014-07-25 | 2014-10-22
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-807 | WM work in Brooklyn Waterfront Greenway. SAND1048 | 5 | CONSTRUCTION TO 25% | 2014-10-23 | 2015-02-19 | 2014-10-23 | 2015-02-19
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-807 | WM work in Brooklyn Waterfront Greenway. SAND1048 | 6 | CONSTRUCTION TO 50% | 2015-02-20 | 2015-06-19 | 2015-02-20 | 2015-06-19
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-807 | WM work in Brooklyn Waterfront Greenway. SAND1048 | 7 | CONSTRUCTION TO 75% | 2015-06-20 | 2015-10-17 | 2015-06-20 | 2015-10-17
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-807 | WM work in Brooklyn Waterfront Greenway. SAND1048 | 8 | ORIGINAL EQUIP & FURNISHING | 2015-10-18 | 2016-01-15 | 2015-10-18 | 2016-01-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-807 | WM work in Brooklyn Waterfront Greenway. SAND1048 | 9 | SUBSTANTIAL COMPLETION | 2016-01-16 | 2016-03-15 | 2016-01-16 | 2016-03-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-807 | WM work in Brooklyn Waterfront Greenway. SAND1048 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-16 | 2016-04-14 | 2016-03-16 | 2022-08-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-809 | Replacement of Water Mains in Avenue S | 1 | DEVELOP SCOPE | 2013-06-30 | 2014-03-26 | 2013-06-30 | 2014-03-26
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-809 | Replacement of Water Mains in Avenue S | 2 | PRELIMINARY DESIGN | 2014-03-27 | 2015-03-21 | 2014-03-27 | 2015-03-21
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-809 | Replacement of Water Mains in Avenue S | 3 | FINAL DESIGN | 2015-03-22 | 2016-09-11 | 2015-03-22 | 2016-09-11
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-809 | Replacement of Water Mains in Avenue S | 4 | BID AWARD AND REGISTER CONTRCT | 2016-09-12 | 2017-06-08 | 2016-09-12 | 2017-06-08
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-809 | Replacement of Water Mains in Avenue S | 5 | CONSTRUCTION TO 25% | 2017-06-09 | 2018-06-03 | 2017-06-09 | 2018-06-03
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-809 | Replacement of Water Mains in Avenue S | 6 | CONSTRUCTION TO 50% | 2018-06-04 | 2019-05-29 | 2018-06-04 | 2019-05-29
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-809 | Replacement of Water Mains in Avenue S | 7 | CONSTRUCTION TO 75% | 2019-05-30 | 2020-05-23 | 2019-05-30 | 2020-05-23
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-809 | Replacement of Water Mains in Avenue S | 8 | ORIGINAL EQUIP & FURNISHING | 2020-05-24 | 2021-02-17 | 2020-05-24 | 2021-02-17
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-809 | Replacement of Water Mains in Avenue S | 9 | SUBSTANTIAL COMPLETION | 2021-02-18 | 2025-08-15 | 2021-02-18 | 2025-08-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-809 | Replacement of Water Mains in Avenue S | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-08-16 | 2025-11-13 | 2025-08-16 | 2025-11-13
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-810 | Water Main work in Brooklyn Waterfront Gateway | 1 | DEVELOP SCOPE | 2016-06-01 | 2016-08-29 | 2016-06-01 | 2016-08-29
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-810 | Water Main work in Brooklyn Waterfront Gateway | 2 | PRELIMINARY DESIGN | 2016-08-30 | 2016-12-27 | 2016-08-30 | 2016-12-27
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-810 | Water Main work in Brooklyn Waterfront Gateway | 3 | FINAL DESIGN | 2016-12-28 | 2017-06-25 | 2016-12-28 | 2017-06-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-810 | Water Main work in Brooklyn Waterfront Gateway | 4 | BID AWARD AND REGISTER CONTRCT | 2017-06-26 | 2017-09-23 | 2017-06-26 | 2017-09-23
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-810 | Water Main work in Brooklyn Waterfront Gateway | 5 | CONSTRUCTION TO 25% | 2017-09-24 | 2018-01-21 | 2017-09-24 | 2018-01-21
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-810 | Water Main work in Brooklyn Waterfront Gateway | 6 | CONSTRUCTION TO 50% | 2018-01-22 | 2018-05-21 | 2018-01-22 | 2018-05-21
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-810 | Water Main work in Brooklyn Waterfront Gateway | 7 | CONSTRUCTION TO 75% | 2018-05-22 | 2018-09-18 | 2018-05-22 | 2018-09-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-810 | Water Main work in Brooklyn Waterfront Gateway | 8 | ORIGINAL EQUIP & FURNISHING | 2018-09-19 | 2018-12-17 | 2018-09-19 | 2018-12-17
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-810 | Water Main work in Brooklyn Waterfront Gateway | 9 | SUBSTANTIAL COMPLETION | 2018-12-18 | 2019-02-15 | 2018-12-18 | 2019-02-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-810 | Water Main work in Brooklyn Waterfront Gateway | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-02-16 | 2019-03-17 | 2019-02-16 | 2021-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-819 | WM replacement in Oriental Blvd | 1 | DEVELOP SCOPE | 2018-03-01 | 2018-05-29 | 2018-03-01 | 2018-05-29
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-819 | WM replacement in Oriental Blvd | 2 | PRELIMINARY DESIGN | 2018-05-30 | 2018-09-26 | 2018-05-30 | 2018-09-26
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-819 | WM replacement in Oriental Blvd | 3 | FINAL DESIGN | 2018-09-27 | 2019-03-25 | 2018-09-27 | 2019-03-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-819 | WM replacement in Oriental Blvd | 4 | BID AWARD AND REGISTER CONTRCT | 2019-03-26 | 2019-06-23 | 2019-03-26 | 2019-06-23
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-819 | WM replacement in Oriental Blvd | 5 | CONSTRUCTION TO 25% | 2019-06-24 | 2019-10-21 | 2019-06-24 | 2019-10-21
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-819 | WM replacement in Oriental Blvd | 6 | CONSTRUCTION TO 50% | 2019-10-22 | 2020-02-18 | 2019-10-22 | 2020-02-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-819 | WM replacement in Oriental Blvd | 7 | CONSTRUCTION TO 75% | 2020-02-19 | 2020-06-17 | 2020-02-19 | 2020-06-17
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-819 | WM replacement in Oriental Blvd | 8 | ORIGINAL EQUIP & FURNISHING | 2020-06-18 | 2020-09-15 | 2020-06-18 | 2020-09-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-819 | WM replacement in Oriental Blvd | 9 | SUBSTANTIAL COMPLETION | 2020-09-16 | 2020-11-14 | 2020-09-16 | 2020-11-14
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-819 | WM replacement in Oriental Blvd | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-11-15 | 2020-12-14 | 2020-11-15 | 2027-01-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-830 | Rplment WM Park Ave btw Classon Ave & Ryerson (HWD007K03) | 1 | DEVELOP SCOPE | 2022-06-01 | 2022-08-29 | 2022-06-01 | 2022-08-29
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-830 | Rplment WM Park Ave btw Classon Ave & Ryerson (HWD007K03) | 2 | PRELIMINARY DESIGN | 2022-08-30 | 2022-12-27 | 2022-08-30 | 2022-12-27
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-830 | Rplment WM Park Ave btw Classon Ave & Ryerson (HWD007K03) | 3 | FINAL DESIGN | 2022-12-28 | 2023-06-25 | 2022-12-28 | 2023-06-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-830 | Rplment WM Park Ave btw Classon Ave & Ryerson (HWD007K03) | 4 | BID AWARD AND REGISTER CONTRCT | 2023-06-26 | 2023-09-23 | 2023-06-26 | 2023-09-23
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-830 | Rplment WM Park Ave btw Classon Ave & Ryerson (HWD007K03) | 5 | CONSTRUCTION TO 25% | 2023-09-24 | 2024-01-21 | 2023-09-24 | 2024-01-21
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-830 | Rplment WM Park Ave btw Classon Ave & Ryerson (HWD007K03) | 6 | CONSTRUCTION TO 50% | 2024-01-22 | 2024-05-20 | 2024-01-22 | 2024-05-20
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-830 | Rplment WM Park Ave btw Classon Ave & Ryerson (HWD007K03) | 7 | CONSTRUCTION TO 75% | 2024-05-21 | 2024-09-17 | 2024-05-21 | 2024-09-17
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-830 | Rplment WM Park Ave btw Classon Ave & Ryerson (HWD007K03) | 8 | ORIGINAL EQUIP & FURNISHING | 2024-09-18 | 2024-12-16 | 2024-09-18 | 2024-12-16
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-830 | Rplment WM Park Ave btw Classon Ave & Ryerson (HWD007K03) | 9 | SUBSTANTIAL COMPLETION | 2024-12-17 | 2025-02-14 | 2024-12-17 | 2025-02-14
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-830 | Rplment WM Park Ave btw Classon Ave & Ryerson (HWD007K03) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-02-15 | 2025-03-16 | 2025-02-15 | 2025-03-16
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BEDA-001 | Accelerated Distribution WM replcmnt & sewer rehab- BKLYN | 1 | DEVELOP SCOPE | 2014-04-30 | 2014-07-28 | 2014-04-30 | 2014-07-28
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BEDA-001 | Accelerated Distribution WM replcmnt & sewer rehab- BKLYN | 2 | PRELIMINARY DESIGN | 2014-07-29 | 2014-11-25 | 2014-07-29 | 2014-11-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BEDA-001 | Accelerated Distribution WM replcmnt & sewer rehab- BKLYN | 3 | FINAL DESIGN | 2014-11-26 | 2015-05-24 | 2014-11-26 | 2015-05-24
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BEDA-001 | Accelerated Distribution WM replcmnt & sewer rehab- BKLYN | 4 | BID AWARD AND REGISTER CONTRCT | 2015-05-25 | 2015-08-22 | 2015-05-25 | 2015-08-22
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BEDA-001 | Accelerated Distribution WM replcmnt & sewer rehab- BKLYN | 5 | CONSTRUCTION TO 25% | 2015-08-23 | 2015-12-20 | 2015-08-23 | 2015-12-20
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BEDA-001 | Accelerated Distribution WM replcmnt & sewer rehab- BKLYN | 6 | CONSTRUCTION TO 50% | 2015-12-21 | 2016-04-18 | 2015-12-21 | 2016-04-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BEDA-001 | Accelerated Distribution WM replcmnt & sewer rehab- BKLYN | 7 | CONSTRUCTION TO 75% | 2016-04-19 | 2016-08-16 | 2016-04-19 | 2016-08-16
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BEDA-001 | Accelerated Distribution WM replcmnt & sewer rehab- BKLYN | 8 | ORIGINAL EQUIP & FURNISHING | 2016-08-17 | 2016-11-14 | 2016-08-17 | 2016-11-14
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BEDA-001 | Accelerated Distribution WM replcmnt & sewer rehab- BKLYN | 9 | SUBSTANTIAL COMPLETION | 2016-11-15 | 2017-01-13 | 2016-11-15 | 2017-01-13
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BEDA-001 | Accelerated Distribution WM replcmnt & sewer rehab- BKLYN | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-01-14 | 2017-02-12 | 2017-01-14 | 2021-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BEDA-003 | Accelerated Distribution WM replcmnt & sewer rehab- BKLYN | 1 | DEVELOP SCOPE | 2016-03-01 | 2016-05-29 | 2016-03-01 | 2016-05-29
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BEDA-003 | Accelerated Distribution WM replcmnt & sewer rehab- BKLYN | 2 | PRELIMINARY DESIGN | 2016-05-30 | 2016-09-26 | 2016-05-30 | 2016-09-26
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BEDA-003 | Accelerated Distribution WM replcmnt & sewer rehab- BKLYN | 3 | FINAL DESIGN | 2016-09-27 | 2017-03-25 | 2016-09-27 | 2017-03-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BEDA-003 | Accelerated Distribution WM replcmnt & sewer rehab- BKLYN | 4 | BID AWARD AND REGISTER CONTRCT | 2017-03-26 | 2017-06-23 | 2017-03-26 | 2017-06-23
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BEDA-003 | Accelerated Distribution WM replcmnt & sewer rehab- BKLYN | 5 | CONSTRUCTION TO 25% | 2017-06-24 | 2017-10-21 | 2017-06-24 | 2017-10-21
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BEDA-003 | Accelerated Distribution WM replcmnt & sewer rehab- BKLYN | 6 | CONSTRUCTION TO 50% | 2017-10-22 | 2018-02-18 | 2017-10-22 | 2018-02-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BEDA-003 | Accelerated Distribution WM replcmnt & sewer rehab- BKLYN | 7 | CONSTRUCTION TO 75% | 2018-02-19 | 2018-06-18 | 2018-02-19 | 2018-06-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BEDA-003 | Accelerated Distribution WM replcmnt & sewer rehab- BKLYN | 8 | ORIGINAL EQUIP & FURNISHING | 2018-06-19 | 2018-09-16 | 2018-06-19 | 2018-09-16
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BEDA-003 | Accelerated Distribution WM replcmnt & sewer rehab- BKLYN | 9 | SUBSTANTIAL COMPLETION | 2018-09-17 | 2018-11-15 | 2018-09-17 | 2018-11-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BEDA-003 | Accelerated Distribution WM replcmnt & sewer rehab- BKLYN | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-11-16 | 2018-12-15 | 2018-11-16 | 2025-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CJCREN | FACIILITY RENOVATIONS AT CROSSROADS JC | 1 | DEVELOP SCOPE | 2015-08-27 | 2015-11-24 | 2015-08-27 | 2015-11-24
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CJCREN | FACIILITY RENOVATIONS AT CROSSROADS JC | 2 | BID AWARD AND REGISTER CONTRCT | 2015-11-25 | 2016-02-22 | 2015-11-25 | 2016-02-22
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CJCREN | FACIILITY RENOVATIONS AT CROSSROADS JC | 3 | CONSTRUCTION TO 50% | 2016-02-23 | 2016-06-21 | 2016-02-23 | 2016-06-21
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CJCREN | FACIILITY RENOVATIONS AT CROSSROADS JC | 4 | CONSTRUCTION TO 75% | 2016-06-22 | 2016-08-20 | 2016-06-22 | 2016-08-20
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CJCREN | FACIILITY RENOVATIONS AT CROSSROADS JC | 5 | SUBSTANTIAL COMPLETION | 2016-08-21 | 2016-10-19 | 2016-08-21 | 2016-10-19
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CJCREN | FACIILITY RENOVATIONS AT CROSSROADS JC | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-10-20 | 2020-11-18 | 2016-10-20 | 2020-11-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CJCREN | FACIILITY RENOVATIONS AT CROSSROADS JC | 7 | PROJECT START | 2016-10-20 | 2020-11-18 | 2020-11-19 | 2020-11-19
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CJCREN | FACIILITY RENOVATIONS AT CROSSROADS JC | 8 | DESIGN START | 2016-10-20 | 2020-11-18 | 2020-11-20 | 2020-11-20
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CJCREN | FACIILITY RENOVATIONS AT CROSSROADS JC | 9 | DESIGN COMPLETION | 2016-10-20 | 2020-11-18 | 2020-11-21 | 2020-11-21
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CJCREN | FACIILITY RENOVATIONS AT CROSSROADS JC | 10 | CONSTRUCTION START | 2016-10-20 | 2020-11-18 | 2020-11-22 | 2020-11-22
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CJCREN | FACIILITY RENOVATIONS AT CROSSROADS JC | 11 | CONSTRUCTION COMPLETION | 2016-10-20 | 2020-11-18 | 2020-11-23 | 2022-11-23
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO272ELC2 | 45 MONROE PL - ELECTRICAL / FA UPGRADE | 1 | DEVELOP SCOPE | 2012-09-01 | 2012-11-29 | 2012-09-01 | 2012-11-29
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO272ELC2 | 45 MONROE PL - ELECTRICAL / FA UPGRADE | 2 | PRELIMINARY DESIGN | 2012-11-30 | 2013-03-31 | 2012-11-30 | 2013-03-31
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO272ELC2 | 45 MONROE PL - ELECTRICAL / FA UPGRADE | 3 | FINAL DESIGN | 2013-04-01 | 2013-09-27 | 2013-04-01 | 2013-09-27
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO272ELC2 | 45 MONROE PL - ELECTRICAL / FA UPGRADE | 4 | BID AWARD AND REGISTER CONTRCT | 2013-09-28 | 2013-12-26 | 2013-09-28 | 2013-12-26
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO272ELC2 | 45 MONROE PL - ELECTRICAL / FA UPGRADE | 5 | CONSTRUCTION TO 25% | 2013-12-27 | 2014-04-25 | 2013-12-27 | 2014-04-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO272ELC2 | 45 MONROE PL - ELECTRICAL / FA UPGRADE | 6 | CONSTRUCTION TO 50% | 2014-04-26 | 2014-08-23 | 2014-04-26 | 2014-08-23
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO272ELC2 | 45 MONROE PL - ELECTRICAL / FA UPGRADE | 7 | CONSTRUCTION TO 75% | 2014-08-24 | 2014-12-21 | 2014-08-24 | 2014-12-21
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO272ELC2 | 45 MONROE PL - ELECTRICAL / FA UPGRADE | 8 | ORIGINAL EQUIP & FURNISHING | 2014-12-22 | 2015-03-26 | 2014-12-22 | 2015-03-26
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO272ELC2 | 45 MONROE PL - ELECTRICAL / FA UPGRADE | 9 | SUBSTANTIAL COMPLETION | 2015-03-27 | 2015-05-30 | 2015-03-27 | 2015-05-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO272ELC2 | 45 MONROE PL - ELECTRICAL / FA UPGRADE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-05-31 | 2015-06-30 | 2015-05-31 | 2020-06-08
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO272ELC2 | 45 MONROE PL - ELECTRICAL / FA UPGRADE | 11 | PROJECT START | 2015-05-31 | 2015-06-30 | 2020-06-09 | 2020-06-09
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO272ELC2 | 45 MONROE PL - ELECTRICAL / FA UPGRADE | 12 | DESIGN START | 2015-05-31 | 2015-06-30 | 2020-06-10 | 2020-06-10
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO272ELC2 | 45 MONROE PL - ELECTRICAL / FA UPGRADE | 13 | DESIGN COMPLETION | 2015-05-31 | 2015-06-30 | 2020-06-11 | 2020-06-11
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO272ELC2 | 45 MONROE PL - ELECTRICAL / FA UPGRADE | 14 | CONSTRUCTION START | 2015-05-31 | 2015-06-30 | 2020-06-12 | 2020-06-12
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO272ELC2 | 45 MONROE PL - ELECTRICAL / FA UPGRADE | 15 | CONSTRUCTION COMPLETION | 2015-05-31 | 2015-06-30 | 2020-06-13 | 2022-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO272ELV2 | 45 MONROE PL. - ELEVATOR | 1 | PROJECT START | 2014-09-18 | 2014-09-18 | 2012-07-08 | 2012-07-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO272ELV2 | 45 MONROE PL. - ELEVATOR | 2 | DESIGN START | 2014-09-19 | 2014-09-19 | 2012-07-26 | 2016-01-06
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO272ELV2 | 45 MONROE PL. - ELEVATOR | 3 | DESIGN COMPLETION | 2014-09-20 | 2014-09-20 | 2016-01-07 | 2017-04-17
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO272ELV2 | 45 MONROE PL. - ELEVATOR | 4 | CONSTRUCTION START | 2014-09-21 | 2014-09-21 | 2017-04-18 | 2019-03-31
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO272ELV2 | 45 MONROE PL. - ELEVATOR | 5 | CONSTRUCTION COMPLETION | 2014-09-22 | 2014-09-22 | 2019-04-01 | 2023-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO278EXT2 | 360 ADAMS ST. - EXTERIOR | 1 | DEVELOP SCOPE | 2020-03-01 | 2020-05-29 | 2020-03-01 | 2020-05-29
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO278EXT2 | 360 ADAMS ST. - EXTERIOR | 2 | PRELIMINARY DESIGN | 2020-05-30 | 2020-09-26 | 2020-05-30 | 2020-09-26
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO278EXT2 | 360 ADAMS ST. - EXTERIOR | 3 | FINAL DESIGN | 2020-09-27 | 2021-03-25 | 2020-09-27 | 2021-03-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO278EXT2 | 360 ADAMS ST. - EXTERIOR | 4 | BID AWARD AND REGISTER CONTRCT | 2021-03-26 | 2021-06-23 | 2021-03-26 | 2021-06-23
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO278EXT2 | 360 ADAMS ST. - EXTERIOR | 5 | CONSTRUCTION TO 25% | 2021-06-24 | 2021-10-21 | 2021-06-24 | 2021-10-21
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO278EXT2 | 360 ADAMS ST. - EXTERIOR | 6 | CONSTRUCTION TO 50% | 2021-10-22 | 2022-02-18 | 2021-10-22 | 2022-02-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO278EXT2 | 360 ADAMS ST. - EXTERIOR | 7 | CONSTRUCTION TO 75% | 2022-02-19 | 2022-06-18 | 2022-02-19 | 2022-06-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO278EXT2 | 360 ADAMS ST. - EXTERIOR | 8 | ORIGINAL EQUIP & FURNISHING | 2022-06-19 | 2022-09-16 | 2022-06-19 | 2022-09-16
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO278EXT2 | 360 ADAMS ST. - EXTERIOR | 9 | SUBSTANTIAL COMPLETION | 2022-09-17 | 2022-11-15 | 2022-09-17 | 2022-11-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO278EXT2 | 360 ADAMS ST. - EXTERIOR | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-11-16 | 2022-12-15 | 2022-11-16 | 2022-12-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO278EXT2 | 360 ADAMS ST. - EXTERIOR | 11 | PROJECT START | 2022-12-16 | 2022-12-16 | 2022-12-16 | 2022-12-16
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO278EXT2 | 360 ADAMS ST. - EXTERIOR | 12 | DESIGN START | 2022-12-17 | 2022-12-17 | 2022-12-17 | 2022-12-17
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO278EXT2 | 360 ADAMS ST. - EXTERIOR | 13 | DESIGN COMPLETION | 2022-12-18 | 2022-12-18 | 2022-12-18 | 2022-12-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO278EXT2 | 360 ADAMS ST. - EXTERIOR | 14 | CONSTRUCTION START | 2022-12-19 | 2022-12-19 | 2022-12-19 | 2022-12-19
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO278EXT2 | 360 ADAMS ST. - EXTERIOR | 15 | CONSTRUCTION COMPLETION | 2022-12-20 | 2022-12-20 | 2022-12-20 | 2022-12-20
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO278FA3 | 360 ADAMS STREET - FIRE ALARM SYSTEM & SPRINKLER UPGRADE | 1 | DEVELOP SCOPE | 2014-12-01 | 2015-02-28 | 2014-12-01 | 2015-02-28
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO278FA3 | 360 ADAMS STREET - FIRE ALARM SYSTEM & SPRINKLER UPGRADE | 2 | PRELIMINARY DESIGN | 2015-03-01 | 2015-06-28 | 2015-03-01 | 2015-06-28
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO278FA3 | 360 ADAMS STREET - FIRE ALARM SYSTEM & SPRINKLER UPGRADE | 3 | FINAL DESIGN | 2015-06-29 | 2015-12-25 | 2015-06-29 | 2018-07-13
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO278FA3 | 360 ADAMS STREET - FIRE ALARM SYSTEM & SPRINKLER UPGRADE | 4 | BID AWARD AND REGISTER CONTRCT | 2015-12-26 | 2016-03-24 | 2018-07-14 | 2018-10-11
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO278FA3 | 360 ADAMS STREET - FIRE ALARM SYSTEM & SPRINKLER UPGRADE | 5 | CONSTRUCTION TO 25% | 2016-03-25 | 2016-07-22 | 2018-10-12 | 2019-02-08
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO278FA3 | 360 ADAMS STREET - FIRE ALARM SYSTEM & SPRINKLER UPGRADE | 6 | CONSTRUCTION TO 50% | 2016-07-23 | 2016-11-19 | 2019-02-09 | 2019-06-08
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO278FA3 | 360 ADAMS STREET - FIRE ALARM SYSTEM & SPRINKLER UPGRADE | 7 | CONSTRUCTION TO 75% | 2016-11-20 | 2017-03-19 | 2019-06-09 | 2019-10-06
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO278FA3 | 360 ADAMS STREET - FIRE ALARM SYSTEM & SPRINKLER UPGRADE | 8 | ORIGINAL EQUIP & FURNISHING | 2017-03-20 | 2017-06-17 | 2019-10-07 | 2020-01-04
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO278FA3 | 360 ADAMS STREET - FIRE ALARM SYSTEM & SPRINKLER UPGRADE | 9 | SUBSTANTIAL COMPLETION | 2017-06-18 | 2017-08-16 | 2020-01-05 | 2020-03-04
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO278FA3 | 360 ADAMS STREET - FIRE ALARM SYSTEM & SPRINKLER UPGRADE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-08-17 | 2017-09-15 | 2020-03-05 | 2020-04-03
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO278FA3 | 360 ADAMS STREET - FIRE ALARM SYSTEM & SPRINKLER UPGRADE | 11 | PROJECT START | 2017-08-17 | 2017-09-15 | 2020-04-04 | 2020-04-04
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO278FA3 | 360 ADAMS STREET - FIRE ALARM SYSTEM & SPRINKLER UPGRADE | 12 | DESIGN START | 2017-08-17 | 2017-09-15 | 2020-04-05 | 2020-04-05
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO278FA3 | 360 ADAMS STREET - FIRE ALARM SYSTEM & SPRINKLER UPGRADE | 13 | DESIGN COMPLETION | 2017-08-17 | 2017-09-15 | 2020-04-06 | 2020-04-06
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO278FA3 | 360 ADAMS STREET - FIRE ALARM SYSTEM & SPRINKLER UPGRADE | 14 | CONSTRUCTION START | 2017-08-17 | 2017-09-15 | 2020-04-07 | 2020-04-07
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO278FA3 | 360 ADAMS STREET - FIRE ALARM SYSTEM & SPRINKLER UPGRADE | 15 | CONSTRUCTION COMPLETION | 2017-08-17 | 2017-09-15 | 2020-04-08 | 2023-08-28
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO281LL11 | 120 SCHERMERHORN ST - FACADE REPAIRS LOCAL LAW 11 | 1 | DEVELOP SCOPE | 2019-03-01 | 2019-05-29 | 2023-03-01 | 2023-05-29
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO281LL11 | 120 SCHERMERHORN ST - FACADE REPAIRS LOCAL LAW 11 | 2 | PRELIMINARY DESIGN | 2019-05-30 | 2019-09-26 | 2023-05-30 | 2023-09-26
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO281LL11 | 120 SCHERMERHORN ST - FACADE REPAIRS LOCAL LAW 11 | 3 | FINAL DESIGN | 2019-09-27 | 2020-03-24 | 2023-09-27 | 2023-09-28
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO281LL11 | 120 SCHERMERHORN ST - FACADE REPAIRS LOCAL LAW 11 | 4 | BID AWARD AND REGISTER CONTRCT | 2020-03-25 | 2020-06-22 | 2023-09-29 | 2023-09-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO281LL11 | 120 SCHERMERHORN ST - FACADE REPAIRS LOCAL LAW 11 | 5 | CONSTRUCTION TO 25% | 2020-06-23 | 2020-10-20 | 2023-10-01 | 2024-01-28
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO281LL11 | 120 SCHERMERHORN ST - FACADE REPAIRS LOCAL LAW 11 | 6 | CONSTRUCTION TO 50% | 2020-10-21 | 2021-02-17 | 2024-01-29 | 2024-10-01
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO281LL11 | 120 SCHERMERHORN ST - FACADE REPAIRS LOCAL LAW 11 | 7 | CONSTRUCTION TO 75% | 2021-02-18 | 2021-06-17 | 2024-12-30 | 2024-12-31
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO281LL11 | 120 SCHERMERHORN ST - FACADE REPAIRS LOCAL LAW 11 | 8 | ORIGINAL EQUIP & FURNISHING | 2021-06-18 | 2021-09-15 | 2024-12-29 | 2024-12-29
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO281LL11 | 120 SCHERMERHORN ST - FACADE REPAIRS LOCAL LAW 11 | 9 | SUBSTANTIAL COMPLETION | 2021-09-16 | 2021-11-14 | 2025-03-29 | 2025-03-29
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO281LL11 | 120 SCHERMERHORN ST - FACADE REPAIRS LOCAL LAW 11 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-11-15 | 2021-12-14 | 2025-06-29 | 2025-06-29
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO281LL11 | 120 SCHERMERHORN ST - FACADE REPAIRS LOCAL LAW 11 | 11 | PROJECT START | 2021-11-15 | 2021-12-14 | 2025-06-30 | 2025-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO281LL11 | 120 SCHERMERHORN ST - FACADE REPAIRS LOCAL LAW 11 | 12 | DESIGN START | 2021-11-15 | 2021-12-14 | 2025-07-01 | 2025-07-01
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO281LL11 | 120 SCHERMERHORN ST - FACADE REPAIRS LOCAL LAW 11 | 13 | DESIGN COMPLETION | 2021-11-15 | 2021-12-14 | 2025-07-02 | 2025-07-02
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO281LL11 | 120 SCHERMERHORN ST - FACADE REPAIRS LOCAL LAW 11 | 14 | CONSTRUCTION START | 2021-11-15 | 2021-12-14 | 2025-07-03 | 2025-07-03
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO281LL11 | 120 SCHERMERHORN ST - FACADE REPAIRS LOCAL LAW 11 | 15 | CONSTRUCTION COMPLETION | 2021-11-15 | 2021-12-14 | 2025-07-04 | 2025-07-04
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO281TOIL | 120 SCHERMERHORN ST.- CODE COMPLIANT TOILET UPGRADE | 1 | DEVELOP SCOPE | 2015-05-01 | 2015-07-29 | 2015-05-01 | 2015-07-29
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO281TOIL | 120 SCHERMERHORN ST.- CODE COMPLIANT TOILET UPGRADE | 2 | PRELIMINARY DESIGN | 2015-07-30 | 2015-11-26 | 2015-07-30 | 2015-11-26
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO281TOIL | 120 SCHERMERHORN ST.- CODE COMPLIANT TOILET UPGRADE | 3 | FINAL DESIGN | 2015-11-27 | 2016-05-24 | 2015-11-27 | 2020-01-09
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO281TOIL | 120 SCHERMERHORN ST.- CODE COMPLIANT TOILET UPGRADE | 4 | BID AWARD AND REGISTER CONTRCT | 2016-05-25 | 2016-08-22 | 2020-01-10 | 2020-04-08
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO281TOIL | 120 SCHERMERHORN ST.- CODE COMPLIANT TOILET UPGRADE | 5 | CONSTRUCTION TO 25% | 2016-08-23 | 2016-12-20 | 2020-04-09 | 2020-08-06
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO281TOIL | 120 SCHERMERHORN ST.- CODE COMPLIANT TOILET UPGRADE | 6 | CONSTRUCTION TO 50% | 2016-12-21 | 2017-04-19 | 2020-08-07 | 2020-12-04
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO281TOIL | 120 SCHERMERHORN ST.- CODE COMPLIANT TOILET UPGRADE | 7 | CONSTRUCTION TO 75% | 2017-04-20 | 2017-08-17 | 2020-12-05 | 2021-04-03
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO281TOIL | 120 SCHERMERHORN ST.- CODE COMPLIANT TOILET UPGRADE | 8 | ORIGINAL EQUIP & FURNISHING | 2017-08-18 | 2017-11-15 | 2021-04-04 | 2021-07-02
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO281TOIL | 120 SCHERMERHORN ST.- CODE COMPLIANT TOILET UPGRADE | 9 | SUBSTANTIAL COMPLETION | 2017-11-16 | 2018-01-14 | 2021-07-03 | 2021-08-31
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO281TOIL | 120 SCHERMERHORN ST.- CODE COMPLIANT TOILET UPGRADE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-01-15 | 2018-02-13 | 2021-09-01 | 2023-02-14
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO281TOIL | 120 SCHERMERHORN ST.- CODE COMPLIANT TOILET UPGRADE | 11 | PROJECT START | 2018-01-15 | 2018-02-13 | 2023-02-15 | 2023-02-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO281TOIL | 120 SCHERMERHORN ST.- CODE COMPLIANT TOILET UPGRADE | 12 | DESIGN START | 2018-01-15 | 2018-02-13 | 2023-02-16 | 2023-02-16
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO281TOIL | 120 SCHERMERHORN ST.- CODE COMPLIANT TOILET UPGRADE | 13 | DESIGN COMPLETION | 2018-01-15 | 2018-02-13 | 2023-02-17 | 2023-02-17
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO281TOIL | 120 SCHERMERHORN ST.- CODE COMPLIANT TOILET UPGRADE | 14 | CONSTRUCTION START | 2018-01-15 | 2018-02-13 | 2023-02-18 | 2023-02-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO281TOIL | 120 SCHERMERHORN ST.- CODE COMPLIANT TOILET UPGRADE | 15 | CONSTRUCTION COMPLETION | 2018-01-15 | 2018-02-13 | 2023-02-19 | 2023-02-19
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CONISPH01 | SAN & STRM SWR, WM1, WM6 IN CONEY ISL AREA, PH 1 | 1 | DEVELOP SCOPE | 2011-02-23 | 2011-05-23 | 2011-02-23 | 2011-05-23
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CONISPH01 | SAN & STRM SWR, WM1, WM6 IN CONEY ISL AREA, PH 1 | 2 | PRELIMINARY DESIGN | 2011-05-24 | 2011-09-20 | 2011-05-24 | 2011-09-20
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CONISPH01 | SAN & STRM SWR, WM1, WM6 IN CONEY ISL AREA, PH 1 | 3 | FINAL DESIGN | 2011-09-21 | 2012-03-18 | 2011-09-21 | 2012-03-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CONISPH01 | SAN & STRM SWR, WM1, WM6 IN CONEY ISL AREA, PH 1 | 4 | BID AWARD AND REGISTER CONTRCT | 2012-03-19 | 2012-06-16 | 2012-03-19 | 2012-06-16
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CONISPH01 | SAN & STRM SWR, WM1, WM6 IN CONEY ISL AREA, PH 1 | 5 | CONSTRUCTION TO 25% | 2012-06-17 | 2012-10-14 | 2012-06-17 | 2012-10-14
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CONISPH01 | SAN & STRM SWR, WM1, WM6 IN CONEY ISL AREA, PH 1 | 6 | CONSTRUCTION TO 50% | 2012-10-15 | 2013-02-11 | 2012-10-15 | 2013-02-11
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CONISPH01 | SAN & STRM SWR, WM1, WM6 IN CONEY ISL AREA, PH 1 | 7 | CONSTRUCTION TO 75% | 2013-02-12 | 2013-06-11 | 2013-02-12 | 2013-06-11
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CONISPH01 | SAN & STRM SWR, WM1, WM6 IN CONEY ISL AREA, PH 1 | 8 | ORIGINAL EQUIP & FURNISHING | 2013-06-12 | 2013-09-09 | 2013-06-12 | 2013-09-09
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CONISPH01 | SAN & STRM SWR, WM1, WM6 IN CONEY ISL AREA, PH 1 | 9 | SUBSTANTIAL COMPLETION | 2013-09-10 | 2013-11-08 | 2013-09-10 | 2013-11-08
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CONISPH01 | SAN & STRM SWR, WM1, WM6 IN CONEY ISL AREA, PH 1 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-11-09 | 2013-12-08 | 2013-11-09 | 2024-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CONISPH04 | SAN & STRM SWR, WM1, IN CONEY ISL AREA, PH 4 | 1 | DEVELOP SCOPE | 2017-03-01 | 2017-05-29 | 2017-03-01 | 2017-05-29
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CONISPH04 | SAN & STRM SWR, WM1, IN CONEY ISL AREA, PH 4 | 2 | PRELIMINARY DESIGN | 2017-05-30 | 2017-09-26 | 2017-05-30 | 2017-09-26
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CONISPH04 | SAN & STRM SWR, WM1, IN CONEY ISL AREA, PH 4 | 3 | FINAL DESIGN | 2017-09-27 | 2018-03-25 | 2017-09-27 | 2018-03-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CONISPH04 | SAN & STRM SWR, WM1, IN CONEY ISL AREA, PH 4 | 4 | BID AWARD AND REGISTER CONTRCT | 2018-03-26 | 2018-06-23 | 2018-03-26 | 2018-06-23
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CONISPH04 | SAN & STRM SWR, WM1, IN CONEY ISL AREA, PH 4 | 5 | CONSTRUCTION TO 25% | 2018-06-24 | 2018-10-21 | 2018-06-24 | 2018-10-21
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CONISPH04 | SAN & STRM SWR, WM1, IN CONEY ISL AREA, PH 4 | 6 | CONSTRUCTION TO 50% | 2018-10-22 | 2019-02-18 | 2018-10-22 | 2019-02-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CONISPH04 | SAN & STRM SWR, WM1, IN CONEY ISL AREA, PH 4 | 7 | CONSTRUCTION TO 75% | 2019-02-19 | 2019-06-18 | 2019-02-19 | 2019-06-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CONISPH04 | SAN & STRM SWR, WM1, IN CONEY ISL AREA, PH 4 | 8 | ORIGINAL EQUIP & FURNISHING | 2019-06-19 | 2019-09-16 | 2019-06-19 | 2019-09-16
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CONISPH04 | SAN & STRM SWR, WM1, IN CONEY ISL AREA, PH 4 | 9 | SUBSTANTIAL COMPLETION | 2019-09-17 | 2019-11-15 | 2019-09-17 | 2019-11-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CONISPH04 | SAN & STRM SWR, WM1, IN CONEY ISL AREA, PH 4 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-11-16 | 2019-12-15 | 2019-11-16 | 2024-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CONISPH2B | SAN & STRM SWR, WM1, WM6 IN CONEY ISL AREA, PH 2B | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2013-09-28
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CONISPH2B | SAN & STRM SWR, WM1, WM6 IN CONEY ISL AREA, PH 2B | 2 | PRELIMINARY DESIGN | 2013-09-29 | 2014-01-26 | 2013-09-29 | 2014-01-26
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CONISPH2B | SAN & STRM SWR, WM1, WM6 IN CONEY ISL AREA, PH 2B | 3 | FINAL DESIGN | 2014-01-27 | 2014-07-25 | 2014-01-27 | 2015-07-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CONISPH2B | SAN & STRM SWR, WM1, WM6 IN CONEY ISL AREA, PH 2B | 4 | BID AWARD AND REGISTER CONTRCT | 2014-07-26 | 2014-10-23 | 2015-07-26 | 2015-10-23
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CONISPH2B | SAN & STRM SWR, WM1, WM6 IN CONEY ISL AREA, PH 2B | 5 | CONSTRUCTION TO 25% | 2014-10-24 | 2015-02-20 | 2015-10-24 | 2016-02-20
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CONISPH2B | SAN & STRM SWR, WM1, WM6 IN CONEY ISL AREA, PH 2B | 6 | CONSTRUCTION TO 50% | 2015-02-21 | 2015-06-20 | 2016-02-21 | 2016-06-19
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CONISPH2B | SAN & STRM SWR, WM1, WM6 IN CONEY ISL AREA, PH 2B | 7 | CONSTRUCTION TO 75% | 2015-06-21 | 2015-10-18 | 2016-06-20 | 2017-02-14
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CONISPH2B | SAN & STRM SWR, WM1, WM6 IN CONEY ISL AREA, PH 2B | 8 | ORIGINAL EQUIP & FURNISHING | 2015-10-19 | 2016-01-16 | 2017-02-15 | 2017-02-14
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CONISPH2B | SAN & STRM SWR, WM1, WM6 IN CONEY ISL AREA, PH 2B | 9 | SUBSTANTIAL COMPLETION | 2016-01-17 | 2016-03-16 | 2017-02-15 | 2017-02-14
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CONISPH2B | SAN & STRM SWR, WM1, WM6 IN CONEY ISL AREA, PH 2B | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-17 | 2016-04-15 | 2017-02-15 | 2025-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CONISPH3A | Storm and Sanitary Sewer, Trunk and Distribution Water Main | 1 | DEVELOP SCOPE | 2016-03-01 | 2016-05-29 | 2016-03-01 | 2016-05-29
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CONISPH3A | Storm and Sanitary Sewer, Trunk and Distribution Water Main | 2 | PRELIMINARY DESIGN | 2016-05-30 | 2016-09-26 | 2016-05-30 | 2016-09-26
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CONISPH3A | Storm and Sanitary Sewer, Trunk and Distribution Water Main | 3 | FINAL DESIGN | 2016-09-27 | 2017-03-25 | 2016-09-27 | 2017-03-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CONISPH3A | Storm and Sanitary Sewer, Trunk and Distribution Water Main | 4 | BID AWARD AND REGISTER CONTRCT | 2017-03-26 | 2017-06-23 | 2017-03-26 | 2017-06-23
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CONISPH3A | Storm and Sanitary Sewer, Trunk and Distribution Water Main | 5 | CONSTRUCTION TO 25% | 2017-06-24 | 2017-10-21 | 2017-06-24 | 2017-10-21
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CONISPH3A | Storm and Sanitary Sewer, Trunk and Distribution Water Main | 6 | CONSTRUCTION TO 50% | 2017-10-22 | 2018-02-18 | 2017-10-22 | 2018-02-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CONISPH3A | Storm and Sanitary Sewer, Trunk and Distribution Water Main | 7 | CONSTRUCTION TO 75% | 2018-02-19 | 2018-06-18 | 2018-02-19 | 2018-06-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CONISPH3A | Storm and Sanitary Sewer, Trunk and Distribution Water Main | 8 | ORIGINAL EQUIP & FURNISHING | 2018-06-19 | 2018-09-16 | 2018-06-19 | 2018-09-16
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CONISPH3A | Storm and Sanitary Sewer, Trunk and Distribution Water Main | 9 | SUBSTANTIAL COMPLETION | 2018-09-17 | 2018-11-15 | 2018-09-17 | 2018-11-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CONISPH3A | Storm and Sanitary Sewer, Trunk and Distribution Water Main | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-11-16 | 2018-12-15 | 2018-11-16 | 2026-03-12
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CV19COEBU | Centers of Excellence: Bushiwick | 1 | PROJECT START | 2020-05-01 | 2020-05-01 | 2020-05-01 | 2020-05-01
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CV19COEBU | Centers of Excellence: Bushiwick | 2 | DESIGN START | 2020-05-02 | 2020-05-02 | 2020-05-02 | 2020-05-02
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CV19COEBU | Centers of Excellence: Bushiwick | 3 | DESIGN COMPLETION | 2020-05-03 | 2020-05-03 | 2020-05-03 | 2020-05-03
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CV19COEBU | Centers of Excellence: Bushiwick | 4 | CONSTRUCTION START | 2020-05-04 | 2020-06-30 | 2020-05-04 | 2020-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CV19COEBU | Centers of Excellence: Bushiwick | 5 | CONSTRUCTION COMPLETION | 2020-07-01 | 2021-07-01 | 2020-07-01 | 2021-07-01
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | E12-0023 | DCLA: Brooklyn Museum, and Brooklyn Central Libr- EE Upgrade | 1 | DEVELOP SCOPE | 2012-06-01 | 2012-06-30 | 2012-06-01 | 2012-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | E12-0023 | DCLA: Brooklyn Museum, and Brooklyn Central Libr- EE Upgrade | 2 | BID AWARD AND REGISTER CONTRCT | 2012-07-01 | 2012-08-29 | 2012-07-01 | 2012-08-29
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | E12-0023 | DCLA: Brooklyn Museum, and Brooklyn Central Libr- EE Upgrade | 3 | CONSTRUCTION TO 50% | 2012-08-30 | 2013-02-25 | 2012-08-30 | 2013-02-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | E12-0023 | DCLA: Brooklyn Museum, and Brooklyn Central Libr- EE Upgrade | 4 | CONSTRUCTION TO 75% | 2013-02-26 | 2013-05-26 | 2013-02-26 | 2013-05-26
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | E12-0023 | DCLA: Brooklyn Museum, and Brooklyn Central Libr- EE Upgrade | 5 | SUBSTANTIAL COMPLETION | 2013-05-27 | 2013-07-25 | 2013-05-27 | 2013-07-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | E12-0023 | DCLA: Brooklyn Museum, and Brooklyn Central Libr- EE Upgrade | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-07-26 | 2013-08-24 | 2013-07-26 | 2013-08-24
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | E12-0023 | DCLA: Brooklyn Museum, and Brooklyn Central Libr- EE Upgrade | 7 | PROJECT START | 2013-07-26 | 2013-08-24 | 2013-08-25 | 2013-08-26
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | E12-0023 | DCLA: Brooklyn Museum, and Brooklyn Central Libr- EE Upgrade | 8 | DESIGN START | 2013-07-26 | 2013-08-24 | 2012-10-16 | 2013-10-16
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | E12-0023 | DCLA: Brooklyn Museum, and Brooklyn Central Libr- EE Upgrade | 9 | DESIGN COMPLETION | 2013-07-26 | 2013-08-24 | 2013-10-17 | 2014-02-28
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | E12-0023 | DCLA: Brooklyn Museum, and Brooklyn Central Libr- EE Upgrade | 10 | CONSTRUCTION START | 2013-07-26 | 2013-08-24 | 2014-03-01 | 2015-08-12
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | E12-0023 | DCLA: Brooklyn Museum, and Brooklyn Central Libr- EE Upgrade | 11 | CONSTRUCTION COMPLETION | 2013-07-26 | 2013-08-24 | 2014-08-29 | 2026-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | E12-0043 | NYPD 84th Precinct - EE Upgrade | 1 | PROJECT START | 2012-06-01 | 2012-06-01 | 2012-10-15 | 2012-10-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | E12-0043 | NYPD 84th Precinct - EE Upgrade | 2 | DESIGN START | 2012-06-02 | 2012-06-02 | 2013-06-28 | 2013-10-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | E12-0043 | NYPD 84th Precinct - EE Upgrade | 3 | DESIGN COMPLETION | 2012-06-03 | 2012-06-04 | 2014-07-22 | 2015-01-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | E12-0043 | NYPD 84th Precinct - EE Upgrade | 4 | CONSTRUCTION START | 2012-06-05 | 2013-06-04 | 2015-01-19 | 2015-07-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | E12-0043 | NYPD 84th Precinct - EE Upgrade | 5 | CONSTRUCTION COMPLETION | 2013-06-05 | 2014-06-05 | 2015-10-19 | 2022-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | E14-0001 | NYPD-FDNY - 67 PCT AND EC248 ENERGY UPGRADE | 1 | PROJECT START | 2014-01-06 | 2014-01-06 | 2014-01-06 | 2014-01-06
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | E14-0001 | NYPD-FDNY - 67 PCT AND EC248 ENERGY UPGRADE | 2 | DESIGN START | 2014-07-13 | 2014-07-16 | 2014-07-13 | 2014-07-16
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | E14-0001 | NYPD-FDNY - 67 PCT AND EC248 ENERGY UPGRADE | 3 | DESIGN COMPLETION | 2015-07-03 | 2015-07-16 | 2015-07-03 | 2015-07-16
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | E14-0001 | NYPD-FDNY - 67 PCT AND EC248 ENERGY UPGRADE | 4 | CONSTRUCTION START | 2016-01-16 | 2016-01-16 | 2016-01-16 | 2016-01-16
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | E14-0001 | NYPD-FDNY - 67 PCT AND EC248 ENERGY UPGRADE | 5 | CONSTRUCTION COMPLETION | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2022-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | E17-0006 | DSNY - BROOKLYN NORTH 1 DISTRICT &4 DISTRICT GARAGE | 1 | DEVELOP SCOPE | 2019-03-01 | 2019-05-29 | 2019-03-01 | 2019-05-29
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | E17-0006 | DSNY - BROOKLYN NORTH 1 DISTRICT &4 DISTRICT GARAGE | 2 | PRELIMINARY DESIGN | 2019-05-30 | 2019-09-26 | 2019-05-30 | 2019-09-26
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | E17-0006 | DSNY - BROOKLYN NORTH 1 DISTRICT &4 DISTRICT GARAGE | 3 | FINAL DESIGN | 2019-09-27 | 2020-03-24 | 2019-09-27 | 2020-03-24
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | E17-0006 | DSNY - BROOKLYN NORTH 1 DISTRICT &4 DISTRICT GARAGE | 4 | BID AWARD AND REGISTER CONTRCT | 2020-03-25 | 2020-06-22 | 2020-03-25 | 2020-06-22
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | E17-0006 | DSNY - BROOKLYN NORTH 1 DISTRICT &4 DISTRICT GARAGE | 5 | CONSTRUCTION TO 25% | 2020-06-23 | 2020-10-20 | 2020-06-23 | 2020-10-20
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | E17-0006 | DSNY - BROOKLYN NORTH 1 DISTRICT &4 DISTRICT GARAGE | 6 | CONSTRUCTION TO 50% | 2020-10-21 | 2021-02-17 | 2020-10-21 | 2021-02-17
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | E17-0006 | DSNY - BROOKLYN NORTH 1 DISTRICT &4 DISTRICT GARAGE | 7 | CONSTRUCTION TO 75% | 2021-02-18 | 2021-06-17 | 2021-02-18 | 2021-06-17
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | E17-0006 | DSNY - BROOKLYN NORTH 1 DISTRICT &4 DISTRICT GARAGE | 8 | ORIGINAL EQUIP & FURNISHING | 2021-06-18 | 2021-09-15 | 2021-06-18 | 2021-09-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | E17-0006 | DSNY - BROOKLYN NORTH 1 DISTRICT &4 DISTRICT GARAGE | 9 | SUBSTANTIAL COMPLETION | 2021-09-16 | 2021-11-14 | 2021-09-16 | 2021-11-14
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | E17-0006 | DSNY - BROOKLYN NORTH 1 DISTRICT &4 DISTRICT GARAGE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-11-15 | 2021-12-14 | 2021-11-15 | 2021-12-14
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0013 | DCLA -New York Aquarium Campus: Aquatic Animal Health Center | 1 | DEVELOP SCOPE | 2019-03-01 | 2019-05-29 | 2019-03-01 | 2019-05-29
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0013 | DCLA -New York Aquarium Campus: Aquatic Animal Health Center | 2 | PRELIMINARY DESIGN | 2019-05-30 | 2019-09-26 | 2019-05-30 | 2019-09-26
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0013 | DCLA -New York Aquarium Campus: Aquatic Animal Health Center | 3 | FINAL DESIGN | 2019-09-27 | 2020-03-24 | 2019-09-27 | 2020-03-24
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0013 | DCLA -New York Aquarium Campus: Aquatic Animal Health Center | 4 | BID AWARD AND REGISTER CONTRCT | 2020-03-25 | 2020-06-22 | 2020-03-25 | 2020-06-22
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0013 | DCLA -New York Aquarium Campus: Aquatic Animal Health Center | 5 | CONSTRUCTION TO 25% | 2020-06-23 | 2020-10-20 | 2020-06-23 | 2020-10-20
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0013 | DCLA -New York Aquarium Campus: Aquatic Animal Health Center | 6 | CONSTRUCTION TO 50% | 2020-10-21 | 2021-02-17 | 2020-10-21 | 2021-02-17
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0013 | DCLA -New York Aquarium Campus: Aquatic Animal Health Center | 7 | CONSTRUCTION TO 75% | 2021-02-18 | 2021-06-17 | 2021-02-18 | 2021-06-17
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0013 | DCLA -New York Aquarium Campus: Aquatic Animal Health Center | 8 | ORIGINAL EQUIP & FURNISHING | 2021-06-18 | 2021-09-15 | 2021-06-18 | 2021-09-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0013 | DCLA -New York Aquarium Campus: Aquatic Animal Health Center | 9 | SUBSTANTIAL COMPLETION | 2021-09-16 | 2021-11-14 | 2021-09-16 | 2021-11-14
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0013 | DCLA -New York Aquarium Campus: Aquatic Animal Health Center | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-11-15 | 2021-12-14 | 2021-11-15 | 2021-12-14
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0014 | DCLA - New York Aquarium Campus: Aqua Theater Pump Room | 1 | DEVELOP SCOPE | 2019-03-01 | 2019-05-29 | 2019-03-01 | 2019-05-29
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0014 | DCLA - New York Aquarium Campus: Aqua Theater Pump Room | 2 | PRELIMINARY DESIGN | 2019-05-30 | 2019-09-26 | 2019-05-30 | 2019-09-26
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0014 | DCLA - New York Aquarium Campus: Aqua Theater Pump Room | 3 | FINAL DESIGN | 2019-09-27 | 2020-03-24 | 2019-09-27 | 2020-03-24
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0014 | DCLA - New York Aquarium Campus: Aqua Theater Pump Room | 4 | BID AWARD AND REGISTER CONTRCT | 2020-03-25 | 2020-06-22 | 2020-03-25 | 2020-06-22
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0014 | DCLA - New York Aquarium Campus: Aqua Theater Pump Room | 5 | CONSTRUCTION TO 25% | 2020-06-23 | 2020-10-20 | 2020-06-23 | 2020-10-20
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0014 | DCLA - New York Aquarium Campus: Aqua Theater Pump Room | 6 | CONSTRUCTION TO 50% | 2020-10-21 | 2021-02-17 | 2020-10-21 | 2021-02-17
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0014 | DCLA - New York Aquarium Campus: Aqua Theater Pump Room | 7 | CONSTRUCTION TO 75% | 2021-02-18 | 2021-06-17 | 2021-02-18 | 2021-06-17
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0014 | DCLA - New York Aquarium Campus: Aqua Theater Pump Room | 8 | ORIGINAL EQUIP & FURNISHING | 2021-06-18 | 2021-09-15 | 2021-06-18 | 2021-09-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0014 | DCLA - New York Aquarium Campus: Aqua Theater Pump Room | 9 | SUBSTANTIAL COMPLETION | 2021-09-16 | 2021-11-14 | 2021-09-16 | 2021-11-14
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0014 | DCLA - New York Aquarium Campus: Aqua Theater Pump Room | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-11-15 | 2021-12-14 | 2021-11-15 | 2021-12-14
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | EP6-KENT2 | 356 FLUSING, BUILDING REPAIR/UPGRADE | 1 | PROJECT START | 2003-09-06 | 2003-09-06 | 2006-09-06 | 2006-09-06
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | EP6-KENT2 | 356 FLUSING, BUILDING REPAIR/UPGRADE | 2 | DESIGN START | 2003-09-07 | 2005-06-22 | 2006-09-07 | 2008-06-22
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | EP6-KENT2 | 356 FLUSING, BUILDING REPAIR/UPGRADE | 3 | DESIGN COMPLETION | 2005-06-23 | 2006-09-15 | 2008-06-23 | 2010-01-05
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | EP6-KENT2 | 356 FLUSING, BUILDING REPAIR/UPGRADE | 4 | CONSTRUCTION START | 2006-09-16 | 2006-09-15 | 2010-01-06 | 2014-08-21
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | EP6-KENT2 | 356 FLUSING, BUILDING REPAIR/UPGRADE | 5 | CONSTRUCTION COMPLETION | 2006-09-16 | 2006-09-16 | 2014-08-22 | 2022-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | F175RES2 | NEW FIREHOUSE - RESCUE 2 | 1 | PROJECT START | 2013-12-15 | 2013-12-16 | 2013-12-15 | 2013-12-16
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | F175RES2 | NEW FIREHOUSE - RESCUE 2 | 2 | DESIGN START | 2013-12-17 | 2014-04-10 | 2013-12-17 | 2014-04-10
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | F175RES2 | NEW FIREHOUSE - RESCUE 2 | 3 | DESIGN COMPLETION | 2014-04-11 | 2015-07-10 | 2014-04-11 | 2015-07-10
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | F175RES2 | NEW FIREHOUSE - RESCUE 2 | 4 | CONSTRUCTION START | 2015-07-11 | 2016-05-02 | 2015-07-11 | 2016-05-02
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | F175RES2 | NEW FIREHOUSE - RESCUE 2 | 5 | CONSTRUCTION COMPLETION | 2016-05-03 | 2018-03-01 | 2016-05-03 | 2022-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GCNC77-PA | GI - PERMEABLE ASPHALT PAVEMENT PILOT & GI IN CSO AREA NC-77 | 1 | DEVELOP SCOPE | 2017-03-01 | 2017-05-29 | 2017-03-01 | 2017-05-29
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GCNC77-PA | GI - PERMEABLE ASPHALT PAVEMENT PILOT & GI IN CSO AREA NC-77 | 2 | PRELIMINARY DESIGN | 2017-05-30 | 2017-09-26 | 2017-05-30 | 2017-09-26
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GCNC77-PA | GI - PERMEABLE ASPHALT PAVEMENT PILOT & GI IN CSO AREA NC-77 | 3 | FINAL DESIGN | 2017-09-27 | 2018-03-25 | 2017-09-27 | 2018-03-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GCNC77-PA | GI - PERMEABLE ASPHALT PAVEMENT PILOT & GI IN CSO AREA NC-77 | 4 | BID AWARD AND REGISTER CONTRCT | 2018-03-26 | 2018-06-23 | 2018-03-26 | 2018-06-23
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GCNC77-PA | GI - PERMEABLE ASPHALT PAVEMENT PILOT & GI IN CSO AREA NC-77 | 5 | CONSTRUCTION TO 25% | 2018-06-24 | 2018-10-21 | 2018-06-24 | 2018-10-21
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GCNC77-PA | GI - PERMEABLE ASPHALT PAVEMENT PILOT & GI IN CSO AREA NC-77 | 6 | CONSTRUCTION TO 50% | 2018-10-22 | 2019-02-18 | 2018-10-22 | 2019-02-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GCNC77-PA | GI - PERMEABLE ASPHALT PAVEMENT PILOT & GI IN CSO AREA NC-77 | 7 | CONSTRUCTION TO 75% | 2019-02-19 | 2019-06-18 | 2019-02-19 | 2019-06-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GCNC77-PA | GI - PERMEABLE ASPHALT PAVEMENT PILOT & GI IN CSO AREA NC-77 | 8 | ORIGINAL EQUIP & FURNISHING | 2019-06-19 | 2019-09-16 | 2019-06-19 | 2019-09-16
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GCNC77-PA | GI - PERMEABLE ASPHALT PAVEMENT PILOT & GI IN CSO AREA NC-77 | 9 | SUBSTANTIAL COMPLETION | 2019-09-17 | 2019-11-15 | 2019-09-17 | 2019-11-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GCNC77-PA | GI - PERMEABLE ASPHALT PAVEMENT PILOT & GI IN CSO AREA NC-77 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-11-16 | 2019-12-15 | 2019-11-16 | 2023-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-01 | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO PH 1 | 1 | DEVELOP SCOPE | 2016-03-01 | 2016-05-29 | 2016-03-01 | 2016-05-29
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-01 | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO PH 1 | 2 | PRELIMINARY DESIGN | 2016-05-30 | 2016-09-26 | 2016-05-30 | 2016-09-26
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-01 | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO PH 1 | 3 | FINAL DESIGN | 2016-09-27 | 2017-03-25 | 2016-09-27 | 2017-03-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-01 | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO PH 1 | 4 | BID AWARD AND REGISTER CONTRCT | 2017-03-26 | 2017-06-23 | 2017-03-26 | 2017-06-23
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-01 | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO PH 1 | 5 | CONSTRUCTION TO 25% | 2017-06-24 | 2017-10-21 | 2017-06-24 | 2017-10-21
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-01 | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO PH 1 | 6 | CONSTRUCTION TO 50% | 2017-10-22 | 2018-02-18 | 2017-10-22 | 2018-02-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-01 | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO PH 1 | 7 | CONSTRUCTION TO 75% | 2018-02-19 | 2018-06-18 | 2018-02-19 | 2018-06-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-01 | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO PH 1 | 8 | ORIGINAL EQUIP & FURNISHING | 2018-06-19 | 2018-09-16 | 2018-06-19 | 2018-09-16
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-01 | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO PH 1 | 9 | SUBSTANTIAL COMPLETION | 2018-09-17 | 2018-11-15 | 2018-09-17 | 2018-11-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-01 | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO PH 1 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-11-16 | 2018-12-15 | 2018-11-16 | 2024-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-02 | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO PH 2 | 1 | DEVELOP SCOPE | 2016-03-01 | 2016-05-29 | 2016-03-01 | 2016-05-29
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-02 | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO PH 2 | 2 | PRELIMINARY DESIGN | 2016-05-30 | 2016-09-26 | 2016-05-30 | 2016-09-26
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-02 | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO PH 2 | 3 | FINAL DESIGN | 2016-09-27 | 2017-03-25 | 2016-09-27 | 2017-03-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-02 | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO PH 2 | 4 | BID AWARD AND REGISTER CONTRCT | 2017-03-26 | 2017-06-23 | 2017-03-26 | 2017-06-23
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-02 | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO PH 2 | 5 | CONSTRUCTION TO 25% | 2017-06-24 | 2017-10-21 | 2017-06-24 | 2017-10-21
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-02 | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO PH 2 | 6 | CONSTRUCTION TO 50% | 2017-10-22 | 2018-02-18 | 2017-10-22 | 2018-02-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-02 | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO PH 2 | 7 | CONSTRUCTION TO 75% | 2018-02-19 | 2018-06-18 | 2018-02-19 | 2018-06-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-02 | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO PH 2 | 8 | ORIGINAL EQUIP & FURNISHING | 2018-06-19 | 2018-09-16 | 2018-06-19 | 2018-09-16
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-02 | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO PH 2 | 9 | SUBSTANTIAL COMPLETION | 2018-09-17 | 2018-11-15 | 2018-09-17 | 2018-11-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-02 | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO PH 2 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-11-16 | 2018-12-15 | 2018-11-16 | 2025-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-03 | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO PH 3 | 1 | DEVELOP SCOPE | 2017-03-01 | 2017-05-29 | 2016-07-02 | 2016-09-29
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-03 | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO PH 3 | 2 | PRELIMINARY DESIGN | 2017-05-30 | 2017-09-26 | 2016-09-30 | 2017-01-27
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-03 | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO PH 3 | 3 | FINAL DESIGN | 2017-09-27 | 2018-03-25 | 2017-01-28 | 2019-07-27
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-03 | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO PH 3 | 4 | BID AWARD AND REGISTER CONTRCT | 2018-03-26 | 2018-06-23 | 2019-07-28 | 2019-10-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-03 | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO PH 3 | 5 | CONSTRUCTION TO 25% | 2018-06-24 | 2018-10-21 | 2019-10-26 | 2020-02-22
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-03 | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO PH 3 | 6 | CONSTRUCTION TO 50% | 2018-10-22 | 2019-02-18 | 2020-02-23 | 2020-06-21
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-03 | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO PH 3 | 7 | CONSTRUCTION TO 75% | 2019-02-19 | 2019-06-18 | 2020-06-22 | 2020-10-19
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-03 | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO PH 3 | 8 | ORIGINAL EQUIP & FURNISHING | 2019-06-19 | 2019-09-16 | 2020-10-20 | 2021-01-17
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-03 | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO PH 3 | 9 | SUBSTANTIAL COMPLETION | 2019-09-17 | 2019-11-15 | 2021-01-18 | 2021-03-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-03 | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO PH 3 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-11-16 | 2019-12-15 | 2021-03-19 | 2021-12-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-04 | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO PH 4 | 1 | DEVELOP SCOPE | 2018-06-15 | 2019-03-11 | 2018-06-15 | 2019-03-11
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-04 | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO PH 4 | 2 | PRELIMINARY DESIGN | 2019-03-12 | 2020-03-05 | 2019-03-12 | 2020-03-05
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-04 | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO PH 4 | 3 | FINAL DESIGN | 2020-03-06 | 2021-08-27 | 2020-03-06 | 2021-08-27
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-04 | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO PH 4 | 4 | BID AWARD AND REGISTER CONTRCT | 2021-08-28 | 2022-05-24 | 2021-08-28 | 2022-05-24
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-04 | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO PH 4 | 5 | CONSTRUCTION TO 25% | 2022-05-25 | 2023-05-19 | 2022-05-25 | 2023-05-19
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-04 | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO PH 4 | 6 | CONSTRUCTION TO 50% | 2023-05-20 | 2024-05-13 | 2023-05-20 | 2024-05-13
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-04 | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO PH 4 | 7 | CONSTRUCTION TO 75% | 2024-05-14 | 2025-05-08 | 2024-05-14 | 2025-05-08
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-04 | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO PH 4 | 8 | ORIGINAL EQUIP & FURNISHING | 2025-05-09 | 2026-02-02 | 2025-05-09 | 2026-02-02
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-04 | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO PH 4 | 9 | SUBSTANTIAL COMPLETION | 2026-02-03 | 2026-08-01 | 2026-02-03 | 2026-08-01
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-04 | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO PH 4 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2026-08-02 | 2026-10-30 | 2026-08-02 | 2026-10-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GNCB14-2A | GI-CONSTRUCTION OF GI NIN NCB-014, PHASE II | 1 | DEVELOP SCOPE | 2017-03-01 | 2017-05-29 | 2017-03-01 | 2017-05-29
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GNCB14-2A | GI-CONSTRUCTION OF GI NIN NCB-014, PHASE II | 2 | PRELIMINARY DESIGN | 2017-05-30 | 2017-09-26 | 2017-05-30 | 2017-09-26
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GNCB14-2A | GI-CONSTRUCTION OF GI NIN NCB-014, PHASE II | 3 | FINAL DESIGN | 2017-09-27 | 2018-03-25 | 2017-09-27 | 2018-03-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GNCB14-2A | GI-CONSTRUCTION OF GI NIN NCB-014, PHASE II | 4 | BID AWARD AND REGISTER CONTRCT | 2018-03-26 | 2018-06-23 | 2018-03-26 | 2018-06-23
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GNCB14-2A | GI-CONSTRUCTION OF GI NIN NCB-014, PHASE II | 5 | CONSTRUCTION TO 25% | 2018-06-24 | 2018-10-21 | 2018-06-24 | 2018-10-21
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GNCB14-2A | GI-CONSTRUCTION OF GI NIN NCB-014, PHASE II | 6 | CONSTRUCTION TO 50% | 2018-10-22 | 2019-02-18 | 2018-10-22 | 2019-02-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GNCB14-2A | GI-CONSTRUCTION OF GI NIN NCB-014, PHASE II | 7 | CONSTRUCTION TO 75% | 2019-02-19 | 2019-06-18 | 2019-02-19 | 2019-06-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GNCB14-2A | GI-CONSTRUCTION OF GI NIN NCB-014, PHASE II | 8 | ORIGINAL EQUIP & FURNISHING | 2019-06-19 | 2019-09-16 | 2019-06-19 | 2019-09-16
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GNCB14-2A | GI-CONSTRUCTION OF GI NIN NCB-014, PHASE II | 9 | SUBSTANTIAL COMPLETION | 2019-09-17 | 2019-11-15 | 2019-09-17 | 2019-11-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GNCB14-2A | GI-CONSTRUCTION OF GI NIN NCB-014, PHASE II | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-11-16 | 2019-12-15 | 2019-11-16 | 2024-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM14GOCC | GOWANUS COMMUNITY CENTER RENOVATIONS | 1 | DESIGN | 2014-01-01 | 2014-06-29 | 2014-01-01 | 2014-06-29
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM14GOCC | GOWANUS COMMUNITY CENTER RENOVATIONS | 2 | BID AWARD AND REGISTER CONTRCT | 2014-06-30 | 2014-11-21 | 2014-06-30 | 2014-11-21
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM14GOCC | GOWANUS COMMUNITY CENTER RENOVATIONS | 3 | CONSTRUCTION | 2014-11-22 | 2015-11-21 | 2014-11-22 | 2015-11-21
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM14GOCC | GOWANUS COMMUNITY CENTER RENOVATIONS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-11-22 | 2016-05-19 | 2014-11-22 | 2015-11-21
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM14GOCC | GOWANUS COMMUNITY CENTER RENOVATIONS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-11-22 | 2016-05-19 | 2015-11-22 | 2020-11-19
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM17GHSE | MARLBOROUGH HOUSES BSCAH GREENHOUSE | 1 | DESIGN | 2017-02-01 | 2017-07-30 | 2019-07-01 | 2019-07-01
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM17GHSE | MARLBOROUGH HOUSES BSCAH GREENHOUSE | 2 | BID AWARD AND REGISTER CONTRCT | 2017-07-31 | 2017-12-22 | 2019-07-01 | 2019-07-01
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM17GHSE | MARLBOROUGH HOUSES BSCAH GREENHOUSE | 3 | CONSTRUCTION | 2017-12-23 | 2018-12-22 | 2019-07-01 | 2019-07-01
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM17GHSE | MARLBOROUGH HOUSES BSCAH GREENHOUSE | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-12-23 | 2019-06-20 | 2019-07-01 | 2019-07-01
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM17GHSE | MARLBOROUGH HOUSES BSCAH GREENHOUSE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-12-23 | 2019-06-20 | 2019-07-01 | 2019-07-01
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM17GHSE | MARLBOROUGH HOUSES BSCAH GREENHOUSE | 7 | PROJECT START | 2018-12-23 | 2019-06-20 | 2019-07-01 | 2019-07-01
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM17GHSE | MARLBOROUGH HOUSES BSCAH GREENHOUSE | 8 | DESIGN START | 2018-12-23 | 2019-06-20 | 2019-07-01 | 2019-07-01
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM17GHSE | MARLBOROUGH HOUSES BSCAH GREENHOUSE | 9 | DESIGN COMPLETION | 2018-12-23 | 2019-06-20 | 2019-07-02 | 2021-01-21
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM17GHSE | MARLBOROUGH HOUSES BSCAH GREENHOUSE | 10 | CONSTRUCTION START | 2018-12-23 | 2019-06-20 | 2021-01-22 | 2021-10-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM17GHSE | MARLBOROUGH HOUSES BSCAH GREENHOUSE | 11 | CONSTRUCTION COMPLETION | 2018-12-23 | 2019-06-20 | 2021-10-19 | 2023-10-06
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM17MRCC | MARCY HOUSES - RENOVATE 492 MARCY AVE INTO A COMM CENTER | 1 | DESIGN | 2017-02-01 | 2017-07-30 | 2017-02-01 | 2017-02-01
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM17MRCC | MARCY HOUSES - RENOVATE 492 MARCY AVE INTO A COMM CENTER | 2 | BID AWARD AND REGISTER CONTRCT | 2017-07-31 | 2017-12-22 | 2017-02-01 | 2017-02-01
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM17MRCC | MARCY HOUSES - RENOVATE 492 MARCY AVE INTO A COMM CENTER | 3 | CONSTRUCTION | 2017-12-23 | 2018-12-22 | 2017-02-01 | 2017-02-01
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM17MRCC | MARCY HOUSES - RENOVATE 492 MARCY AVE INTO A COMM CENTER | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-12-23 | 2019-06-20 | 2017-02-01 | 2017-02-01
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM17MRCC | MARCY HOUSES - RENOVATE 492 MARCY AVE INTO A COMM CENTER | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-12-23 | 2019-06-20 | 2017-02-01 | 2017-02-01
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM17MRCC | MARCY HOUSES - RENOVATE 492 MARCY AVE INTO A COMM CENTER | 7 | PROJECT START | 2018-12-23 | 2019-06-20 | 2017-02-01 | 2017-02-01
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM17MRCC | MARCY HOUSES - RENOVATE 492 MARCY AVE INTO A COMM CENTER | 8 | DESIGN START | 2018-12-23 | 2019-06-20 | 2017-02-02 | 2017-11-06
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM17MRCC | MARCY HOUSES - RENOVATE 492 MARCY AVE INTO A COMM CENTER | 9 | DESIGN COMPLETION | 2018-12-23 | 2019-06-20 | 2017-11-07 | 2018-04-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM17MRCC | MARCY HOUSES - RENOVATE 492 MARCY AVE INTO A COMM CENTER | 10 | CONSTRUCTION START | 2018-12-23 | 2019-06-20 | 2018-05-01 | 2018-06-29
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM17MRCC | MARCY HOUSES - RENOVATE 492 MARCY AVE INTO A COMM CENTER | 11 | CONSTRUCTION COMPLETION | 2018-12-23 | 2019-06-20 | 2018-06-30 | 2021-07-05
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HD-161C | GATEWAY ESTATE - PHASE C (SEK20056) | 1 | DEVELOP SCOPE | 2007-03-02 | 2007-05-30 | 2005-04-15 | 2011-05-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HD-161C | GATEWAY ESTATE - PHASE C (SEK20056) | 2 | PRELIMINARY DESIGN | 2007-05-31 | 2007-09-27 | 2011-05-31 | 2011-09-27
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HD-161C | GATEWAY ESTATE - PHASE C (SEK20056) | 3 | FINAL DESIGN | 2007-09-28 | 2008-03-25 | 2011-09-28 | 2012-03-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HD-161C | GATEWAY ESTATE - PHASE C (SEK20056) | 4 | BID AWARD AND REGISTER CONTRCT | 2008-03-26 | 2008-06-23 | 2012-03-26 | 2016-06-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HD-161C | GATEWAY ESTATE - PHASE C (SEK20056) | 5 | CONSTRUCTION TO 25% | 2008-06-24 | 2008-10-21 | 2016-06-16 | 2016-06-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HD-161C | GATEWAY ESTATE - PHASE C (SEK20056) | 6 | CONSTRUCTION TO 50% | 2008-10-22 | 2009-02-18 | 2016-06-16 | 2016-06-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HD-161C | GATEWAY ESTATE - PHASE C (SEK20056) | 7 | CONSTRUCTION TO 75% | 2009-02-19 | 2009-06-18 | 2016-06-16 | 2016-06-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HD-161C | GATEWAY ESTATE - PHASE C (SEK20056) | 8 | ORIGINAL EQUIP & FURNISHING | 2009-06-19 | 2009-09-16 | 2016-06-16 | 2016-06-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HD-161C | GATEWAY ESTATE - PHASE C (SEK20056) | 9 | SUBSTANTIAL COMPLETION | 2009-09-17 | 2009-11-15 | 2016-06-16 | 2016-06-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HD-161C | GATEWAY ESTATE - PHASE C (SEK20056) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2009-11-16 | 2009-12-15 | 2016-06-16 | 2021-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HD-161D | GATEWAY ESTATE - PHASE D (SEK002354/SEK20057) | 1 | DEVELOP SCOPE | 2007-04-02 | 2007-06-30 | 2007-04-02 | 2007-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HD-161D | GATEWAY ESTATE - PHASE D (SEK002354/SEK20057) | 2 | PRELIMINARY DESIGN | 2007-07-01 | 2007-10-28 | 2007-07-01 | 2007-10-28
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HD-161D | GATEWAY ESTATE - PHASE D (SEK002354/SEK20057) | 3 | FINAL DESIGN | 2007-10-29 | 2008-04-25 | 2007-10-29 | 2008-04-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HD-161D | GATEWAY ESTATE - PHASE D (SEK002354/SEK20057) | 4 | BID AWARD AND REGISTER CONTRCT | 2008-04-26 | 2008-07-24 | 2008-04-26 | 2012-06-16
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HD-161D | GATEWAY ESTATE - PHASE D (SEK002354/SEK20057) | 5 | CONSTRUCTION TO 25% | 2008-07-25 | 2008-11-21 | 2012-06-17 | 2012-06-16
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HD-161D | GATEWAY ESTATE - PHASE D (SEK002354/SEK20057) | 6 | CONSTRUCTION TO 50% | 2008-11-22 | 2009-03-21 | 2012-06-17 | 2012-06-16
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HD-161D | GATEWAY ESTATE - PHASE D (SEK002354/SEK20057) | 7 | CONSTRUCTION TO 75% | 2009-03-22 | 2009-07-19 | 2012-06-17 | 2012-06-16
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HD-161D | GATEWAY ESTATE - PHASE D (SEK002354/SEK20057) | 8 | ORIGINAL EQUIP & FURNISHING | 2009-07-20 | 2009-10-17 | 2012-06-17 | 2012-06-16
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HD-161D | GATEWAY ESTATE - PHASE D (SEK002354/SEK20057) | 9 | SUBSTANTIAL COMPLETION | 2009-10-18 | 2009-12-16 | 2012-06-17 | 2012-06-16
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HD-161D | GATEWAY ESTATE - PHASE D (SEK002354/SEK20057) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2009-12-17 | 2010-01-15 | 2012-06-17 | 2023-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112AAFS | ATLANTIC ARMORY FIRE SAFETY | 1 | PROJECT START | 2017-04-28 | 2017-04-28 | 2017-04-28 | 2017-04-28
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112AAFS | ATLANTIC ARMORY FIRE SAFETY | 2 | DESIGN START | 2017-04-29 | 2017-04-28 | 2017-04-29 | 2017-04-28
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112AAFS | ATLANTIC ARMORY FIRE SAFETY | 3 | DESIGN COMPLETION | 2017-04-29 | 2018-01-17 | 2017-04-29 | 2018-09-19
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112AAFS | ATLANTIC ARMORY FIRE SAFETY | 4 | CONSTRUCTION START | 2018-01-18 | 2018-09-16 | 2018-09-20 | 2019-05-19
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112AAFS | ATLANTIC ARMORY FIRE SAFETY | 5 | CONSTRUCTION COMPLETION | 2018-09-17 | 2019-05-19 | 2019-05-20 | 2025-01-19
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BVFA | BROWNSVILLE WOMEN FIRE SAFETY | 1 | PROJECT START | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BVFA | BROWNSVILLE WOMEN FIRE SAFETY | 2 | DESIGN START | 2016-07-02 | 2017-11-09 | 2016-07-02 | 2017-11-09
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BVFA | BROWNSVILLE WOMEN FIRE SAFETY | 3 | DESIGN COMPLETION | 2017-11-10 | 2018-08-15 | 2017-11-10 | 2018-08-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BVFA | BROWNSVILLE WOMEN FIRE SAFETY | 4 | CONSTRUCTION START | 2018-08-16 | 2019-03-22 | 2018-08-16 | 2021-03-22
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BVFA | BROWNSVILLE WOMEN FIRE SAFETY | 5 | CONSTRUCTION COMPLETION | 2019-03-23 | 2020-03-20 | 2021-03-23 | 2023-03-21
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112FBFS | FANNIE BARNES FIRE SAFETY | 1 | PROJECT START | 2016-07-26 | 2016-07-26 | 2016-07-26 | 2016-07-26
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112FBFS | FANNIE BARNES FIRE SAFETY | 2 | DESIGN START | 2016-07-27 | 2017-11-09 | 2016-07-27 | 2017-11-09
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112FBFS | FANNIE BARNES FIRE SAFETY | 3 | DESIGN COMPLETION | 2017-11-10 | 2018-08-15 | 2017-11-10 | 2019-08-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112FBFS | FANNIE BARNES FIRE SAFETY | 4 | CONSTRUCTION START | 2018-08-16 | 2019-05-15 | 2019-08-16 | 2021-05-14
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112FBFS | FANNIE BARNES FIRE SAFETY | 5 | CONSTRUCTION COMPLETION | 2019-05-16 | 2020-05-15 | 2021-05-15 | 2023-05-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112HWFS | HELP WOMEN'S CENTER FIRE SAFETY | 1 | PROJECT START | 2016-07-26 | 2016-07-26 | 2016-07-26 | 2016-07-26
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112HWFS | HELP WOMEN'S CENTER FIRE SAFETY | 2 | DESIGN START | 2016-07-27 | 2017-09-26 | 2016-07-27 | 2017-09-26
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112HWFS | HELP WOMEN'S CENTER FIRE SAFETY | 3 | DESIGN COMPLETION | 2017-09-27 | 2018-03-26 | 2017-09-27 | 2018-03-26
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112HWFS | HELP WOMEN'S CENTER FIRE SAFETY | 4 | CONSTRUCTION START | 2018-03-27 | 2019-05-17 | 2018-03-27 | 2019-05-17
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112HWFS | HELP WOMEN'S CENTER FIRE SAFETY | 5 | CONSTRUCTION COMPLETION | 2019-05-18 | 2020-04-17 | 2019-05-18 | 2023-04-17
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112LXEP | 85 LEXINGTON AVE BOILER RECONSTRUCTION | 1 | DESIGN | 2020-01-01 | 2020-09-26 | 2020-01-01 | 2020-09-26
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112LXEP | 85 LEXINGTON AVE BOILER RECONSTRUCTION | 2 | BID AWARD AND REGISTER CONTRCT | 2020-09-27 | 2021-03-25 | 2020-09-27 | 2021-03-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112LXEP | 85 LEXINGTON AVE BOILER RECONSTRUCTION | 3 | CONSTRUCTION | 2021-03-26 | 2025-12-29 | 2021-03-26 | 2025-12-29
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112PJBO | PAMOJA - BOILER | 1 | PROJECT START | 2016-03-30 | 2016-03-31 | 2016-03-30 | 2016-03-31
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112PJBO | PAMOJA - BOILER | 2 | DESIGN START | 2016-04-01 | 2016-07-01 | 2016-04-01 | 2016-07-01
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112PJBO | PAMOJA - BOILER | 3 | DESIGN COMPLETION | 2016-07-02 | 2017-06-30 | 2016-07-02 | 2017-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112PJBO | PAMOJA - BOILER | 4 | CONSTRUCTION START | 2017-07-01 | 2017-10-31 | 2017-07-01 | 2017-10-31
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112PJBO | PAMOJA - BOILER | 5 | CONSTRUCTION COMPLETION | 2017-11-01 | 2023-06-30 | 2017-11-01 | 2023-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112PJFC | PAMOJA HOUSE - FACADE REHABILITATION/RESTORATION | 1 | PROJECT START | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112PJFC | PAMOJA HOUSE - FACADE REHABILITATION/RESTORATION | 2 | DESIGN START | 2018-01-02 | 2018-07-01 | 2018-01-02 | 2018-07-01
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112PJFC | PAMOJA HOUSE - FACADE REHABILITATION/RESTORATION | 3 | DESIGN COMPLETION | 2018-07-02 | 2019-01-01 | 2018-07-02 | 2020-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112PJFC | PAMOJA HOUSE - FACADE REHABILITATION/RESTORATION | 4 | CONSTRUCTION START | 2019-01-02 | 2019-07-01 | 2020-07-01 | 2020-12-28
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112PJFC | PAMOJA HOUSE - FACADE REHABILITATION/RESTORATION | 5 | CONSTRUCTION COMPLETION | 2019-07-02 | 2020-12-31 | 2020-12-29 | 2024-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112PJPL | PAMOJA HOUSE - PLUMBING UPGRADE | 1 | PROJECT START | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112PJPL | PAMOJA HOUSE - PLUMBING UPGRADE | 2 | DESIGN START | 2018-01-02 | 2018-07-01 | 2018-01-02 | 2019-06-26
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112PJPL | PAMOJA HOUSE - PLUMBING UPGRADE | 3 | DESIGN COMPLETION | 2018-07-02 | 2019-01-01 | 2019-06-27 | 2021-06-11
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112PJPL | PAMOJA HOUSE - PLUMBING UPGRADE | 4 | CONSTRUCTION START | 2019-01-02 | 2019-07-01 | 2021-06-12 | 2021-10-08
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112PJPL | PAMOJA HOUSE - PLUMBING UPGRADE | 5 | CONSTRUCTION COMPLETION | 2019-07-02 | 2020-12-31 | 2021-10-09 | 2024-01-09
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112PJRC | PAMOJA HOUSE FIRE SAFETY | 1 | PROJECT START | 2016-07-26 | 2016-07-26 | 2016-07-26 | 2016-07-26
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112PJRC | PAMOJA HOUSE FIRE SAFETY | 2 | DESIGN START | 2016-07-27 | 2017-11-09 | 2016-07-27 | 2017-11-09
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112PJRC | PAMOJA HOUSE FIRE SAFETY | 3 | DESIGN COMPLETION | 2017-11-10 | 2019-07-01 | 2017-11-10 | 2019-07-01
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112PJRC | PAMOJA HOUSE FIRE SAFETY | 4 | CONSTRUCTION START | 2019-07-02 | 2020-03-02 | 2019-07-02 | 2020-03-02
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112PJRC | PAMOJA HOUSE FIRE SAFETY | 5 | CONSTRUCTION COMPLETION | 2020-03-03 | 2022-08-02 | 2020-03-03 | 2022-08-02
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115BMEP | BUSHWICK FAMILY BOILER RECONSTRUCTION | 1 | DESIGN | 2020-01-01 | 2020-09-26 | 2020-01-01 | 2020-09-26
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115BMEP | BUSHWICK FAMILY BOILER RECONSTRUCTION | 2 | BID AWARD AND REGISTER CONTRCT | 2020-09-27 | 2021-03-25 | 2020-09-27 | 2021-03-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115BMEP | BUSHWICK FAMILY BOILER RECONSTRUCTION | 3 | CONSTRUCTION | 2021-03-26 | 2025-12-29 | 2021-03-26 | 2025-12-29
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115DSFA | DEAN STREET FIRE SAFETY | 1 | PROJECT START | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115DSFA | DEAN STREET FIRE SAFETY | 2 | DESIGN START | 2016-07-13 | 2017-11-09 | 2016-07-13 | 2017-11-09
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115DSFA | DEAN STREET FIRE SAFETY | 3 | DESIGN COMPLETION | 2017-11-10 | 2018-08-15 | 2017-11-10 | 2018-08-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115DSFA | DEAN STREET FIRE SAFETY | 4 | CONSTRUCTION START | 2018-08-16 | 2019-04-19 | 2018-08-16 | 2020-04-19
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115DSFA | DEAN STREET FIRE SAFETY | 5 | CONSTRUCTION COMPLETION | 2019-04-20 | 2020-04-17 | 2020-04-20 | 2025-04-17
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115LFAU | LINDEN FIRE ALARM UPGRADE | 1 | PROJECT START | 2016-07-26 | 2016-07-26 | 2016-07-26 | 2016-07-26
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115LFAU | LINDEN FIRE ALARM UPGRADE | 2 | DESIGN START | 2016-07-27 | 2017-09-26 | 2016-07-27 | 2017-09-26
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115LFAU | LINDEN FIRE ALARM UPGRADE | 3 | DESIGN COMPLETION | 2017-09-27 | 2018-09-21 | 2017-09-27 | 2018-10-05
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115LFAU | LINDEN FIRE ALARM UPGRADE | 4 | CONSTRUCTION START | 2018-09-22 | 2019-05-17 | 2018-10-06 | 2021-05-20
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115LFAU | LINDEN FIRE ALARM UPGRADE | 5 | CONSTRUCTION COMPLETION | 2018-05-18 | 2020-05-15 | 2018-05-18 | 2022-11-17
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115SFFA | Stockholm at 99-103 Stockholm St, 11221 - Fire Alarm Upgrade | 1 | PROJECT START | 2016-03-30 | 2016-03-31 | 2016-03-30 | 2016-03-31
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115SFFA | Stockholm at 99-103 Stockholm St, 11221 - Fire Alarm Upgrade | 2 | DESIGN START | 2016-04-01 | 2016-07-01 | 2016-04-01 | 2016-07-01
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115SFFA | Stockholm at 99-103 Stockholm St, 11221 - Fire Alarm Upgrade | 3 | DESIGN COMPLETION | 2016-07-02 | 2017-06-30 | 2016-07-02 | 2017-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115SFFA | Stockholm at 99-103 Stockholm St, 11221 - Fire Alarm Upgrade | 4 | CONSTRUCTION START | 2017-07-01 | 2017-10-31 | 2017-07-01 | 2017-10-31
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115SFFA | Stockholm at 99-103 Stockholm St, 11221 - Fire Alarm Upgrade | 5 | CONSTRUCTION COMPLETION | 2017-11-01 | 2023-06-30 | 2017-11-01 | 2023-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115SRFA | ROSE MCCARTHY - FIRE ALARM SYSTEM UPGRADE | 1 | PROJECT START | 2016-03-30 | 2016-03-31 | 2016-03-30 | 2016-03-31
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115SRFA | ROSE MCCARTHY - FIRE ALARM SYSTEM UPGRADE | 2 | DESIGN START | 2016-04-01 | 2016-07-01 | 2016-04-01 | 2016-07-01
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115SRFA | ROSE MCCARTHY - FIRE ALARM SYSTEM UPGRADE | 3 | DESIGN COMPLETION | 2016-07-02 | 2017-06-30 | 2016-07-02 | 2017-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115SRFA | ROSE MCCARTHY - FIRE ALARM SYSTEM UPGRADE | 4 | CONSTRUCTION START | 2017-07-01 | 2017-10-31 | 2017-07-01 | 2017-10-31
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115SRFA | ROSE MCCARTHY - FIRE ALARM SYSTEM UPGRADE | 5 | CONSTRUCTION COMPLETION | 2017-11-01 | 2023-06-30 | 2017-11-01 | 2023-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HIFHPD | Housing Infrastructure Fund for HPD Projects | 1 | DEVELOP SCOPE | 2018-03-01 | 2018-05-29 | 2018-03-01 | 2018-05-29
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HIFHPD | Housing Infrastructure Fund for HPD Projects | 2 | PRELIMINARY DESIGN | 2018-05-30 | 2018-09-26 | 2018-05-30 | 2018-09-26
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HIFHPD | Housing Infrastructure Fund for HPD Projects | 3 | FINAL DESIGN | 2018-09-27 | 2019-03-25 | 2018-09-27 | 2019-03-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HIFHPD | Housing Infrastructure Fund for HPD Projects | 4 | BID AWARD AND REGISTER CONTRCT | 2019-03-26 | 2019-06-23 | 2019-03-26 | 2019-06-23
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HIFHPD | Housing Infrastructure Fund for HPD Projects | 5 | CONSTRUCTION TO 25% | 2019-06-24 | 2019-10-21 | 2019-06-24 | 2019-10-21
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HIFHPD | Housing Infrastructure Fund for HPD Projects | 6 | CONSTRUCTION TO 50% | 2019-10-22 | 2020-02-18 | 2019-10-22 | 2020-02-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HIFHPD | Housing Infrastructure Fund for HPD Projects | 7 | CONSTRUCTION TO 75% | 2020-02-19 | 2020-06-17 | 2020-02-19 | 2020-06-17
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HIFHPD | Housing Infrastructure Fund for HPD Projects | 8 | ORIGINAL EQUIP & FURNISHING | 2020-06-18 | 2020-09-15 | 2020-06-18 | 2020-09-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HIFHPD | Housing Infrastructure Fund for HPD Projects | 9 | SUBSTANTIAL COMPLETION | 2020-09-16 | 2020-11-14 | 2020-09-16 | 2020-11-14
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HIFHPD | Housing Infrastructure Fund for HPD Projects | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-11-15 | 2020-12-14 | 2020-11-15 | 2020-12-14
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82BRKLN | Brooklyn Animal Care Center Upgrade | 1 | PROJECT START | 2016-01-01 | 2016-01-01 | 2016-01-01 | 2016-01-01
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82BRKLN | Brooklyn Animal Care Center Upgrade | 2 | DESIGN START | 2016-01-02 | 2016-01-02 | 2016-01-02 | 2016-01-02
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82BRKLN | Brooklyn Animal Care Center Upgrade | 3 | DESIGN COMPLETION | 2016-01-03 | 2016-01-03 | 2016-01-03 | 2016-01-03
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82BRKLN | Brooklyn Animal Care Center Upgrade | 4 | CONSTRUCTION START | 2016-01-04 | 2016-01-04 | 2016-01-04 | 2016-01-04
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82BRKLN | Brooklyn Animal Care Center Upgrade | 5 | CONSTRUCTION COMPLETION | 2016-01-05 | 2022-06-30 | 2016-01-05 | 2022-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82BUSHX | BUSHWICK HEALTH CENTER - EXTERIOR RENOVATION | 1 | PROJECT START | 2004-08-03 | 2004-08-03 | 2008-08-05 | 2008-08-05
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82BUSHX | BUSHWICK HEALTH CENTER - EXTERIOR RENOVATION | 2 | DESIGN START | 2004-08-04 | 2009-05-22 | 2008-08-06 | 2016-01-12
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82BUSHX | BUSHWICK HEALTH CENTER - EXTERIOR RENOVATION | 3 | DESIGN COMPLETION | 2009-05-23 | 2009-05-22 | 2016-01-13 | 2018-11-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82BUSHX | BUSHWICK HEALTH CENTER - EXTERIOR RENOVATION | 4 | CONSTRUCTION START | 2009-05-23 | 2009-05-22 | 2018-12-01 | 2019-08-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82BUSHX | BUSHWICK HEALTH CENTER - EXTERIOR RENOVATION | 5 | CONSTRUCTION COMPLETION | 2009-05-23 | 2012-06-30 | 2019-08-31 | 2021-08-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD005K01 | FULTON ST IMPROVEMENTS AT GREEN AV, HANSEN PL & GATES AV | 1 | DEVELOP SCOPE | 2010-06-30 | 2010-09-27 | 2011-06-30 | 2011-09-27
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD005K01 | FULTON ST IMPROVEMENTS AT GREEN AV, HANSEN PL & GATES AV | 2 | PRELIMINARY DESIGN | 2010-09-28 | 2011-01-25 | 2011-09-28 | 2012-01-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD005K01 | FULTON ST IMPROVEMENTS AT GREEN AV, HANSEN PL & GATES AV | 3 | FINAL DESIGN | 2011-01-26 | 2011-07-24 | 2012-01-26 | 2015-05-03
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD005K01 | FULTON ST IMPROVEMENTS AT GREEN AV, HANSEN PL & GATES AV | 4 | BID AWARD AND REGISTER CONTRCT | 2011-07-25 | 2011-10-22 | 2015-05-04 | 2015-08-01
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD005K01 | FULTON ST IMPROVEMENTS AT GREEN AV, HANSEN PL & GATES AV | 5 | CONSTRUCTION TO 25% | 2011-10-23 | 2012-02-19 | 2015-08-02 | 2015-11-29
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD005K01 | FULTON ST IMPROVEMENTS AT GREEN AV, HANSEN PL & GATES AV | 6 | CONSTRUCTION TO 50% | 2012-02-20 | 2012-06-18 | 2015-11-30 | 2016-07-26
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD005K01 | FULTON ST IMPROVEMENTS AT GREEN AV, HANSEN PL & GATES AV | 7 | CONSTRUCTION TO 75% | 2012-06-19 | 2012-10-16 | 2016-07-27 | 2017-03-23
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD005K01 | FULTON ST IMPROVEMENTS AT GREEN AV, HANSEN PL & GATES AV | 8 | ORIGINAL EQUIP & FURNISHING | 2012-10-17 | 2013-01-14 | 2017-03-24 | 2017-06-21
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD005K01 | FULTON ST IMPROVEMENTS AT GREEN AV, HANSEN PL & GATES AV | 9 | SUBSTANTIAL COMPLETION | 2013-01-15 | 2013-03-15 | 2017-04-23 | 2017-06-21
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD005K01 | FULTON ST IMPROVEMENTS AT GREEN AV, HANSEN PL & GATES AV | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-03-16 | 2013-04-14 | 2017-06-22 | 2030-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD007K03 | Park Avenue Ped Safety Improvement at the Crossover,BED-830 | 1 | DEVELOP SCOPE | 2013-06-30 | 2013-09-27 | 2016-06-30 | 2019-03-24
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD007K03 | Park Avenue Ped Safety Improvement at the Crossover,BED-830 | 2 | PRELIMINARY DESIGN | 2013-09-28 | 2014-01-25 | 2019-03-25 | 2019-12-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD007K03 | Park Avenue Ped Safety Improvement at the Crossover,BED-830 | 3 | FINAL DESIGN | 2014-01-26 | 2014-07-24 | 2019-12-31 | 2021-09-20
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD007K03 | Park Avenue Ped Safety Improvement at the Crossover,BED-830 | 4 | BID AWARD AND REGISTER CONTRCT | 2014-07-25 | 2014-10-22 | 2021-09-21 | 2022-07-17
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD007K03 | Park Avenue Ped Safety Improvement at the Crossover,BED-830 | 5 | CONSTRUCTION TO 25% | 2014-10-23 | 2015-02-19 | 2022-07-18 | 2022-11-14
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD007K03 | Park Avenue Ped Safety Improvement at the Crossover,BED-830 | 6 | CONSTRUCTION TO 50% | 2015-02-20 | 2015-06-19 | 2022-11-15 | 2023-03-14
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD007K03 | Park Avenue Ped Safety Improvement at the Crossover,BED-830 | 7 | CONSTRUCTION TO 75% | 2015-06-20 | 2015-10-17 | 2023-03-15 | 2023-07-12
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD007K03 | Park Avenue Ped Safety Improvement at the Crossover,BED-830 | 8 | ORIGINAL EQUIP & FURNISHING | 2015-10-18 | 2016-01-15 | 2023-07-13 | 2023-10-10
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD007K03 | Park Avenue Ped Safety Improvement at the Crossover,BED-830 | 9 | SUBSTANTIAL COMPLETION | 2016-01-16 | 2016-03-15 | 2023-10-11 | 2023-12-09
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD007K03 | Park Avenue Ped Safety Improvement at the Crossover,BED-830 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-16 | 2016-04-14 | 2023-12-10 | 2024-01-08
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD10105 | Ped Safety Upgrades on Atlantic Ave (BED-785A, NDF-ATLAV) | 1 | DEVELOP SCOPE | 2017-06-01 | 2017-09-28 | 2017-01-01 | 2017-01-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD10105 | Ped Safety Upgrades on Atlantic Ave (BED-785A, NDF-ATLAV) | 2 | DESIGN START | 2017-09-29 | 2019-03-22 | 2017-04-01 | 2017-07-29
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD10105 | Ped Safety Upgrades on Atlantic Ave (BED-785A, NDF-ATLAV) | 3 | CONSTRUCTION START | 2019-03-23 | 2021-03-11 | 2017-07-30 | 2017-11-26
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD10105 | Ped Safety Upgrades on Atlantic Ave (BED-785A, NDF-ATLAV) | 4 | BID AWARD AND REGISTER CONTRCT | 2019-03-23 | 2021-03-11 | 2017-11-27 | 2018-02-24
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD10105 | Ped Safety Upgrades on Atlantic Ave (BED-785A, NDF-ATLAV) | 5 | CONSTRUCTION TO 25% | 2019-03-23 | 2021-03-11 | 2018-02-25 | 2018-10-22
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD10105 | Ped Safety Upgrades on Atlantic Ave (BED-785A, NDF-ATLAV) | 6 | CONSTRUCTION TO 50% | 2019-03-23 | 2021-03-11 | 2018-10-23 | 2019-06-19
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD10105 | Ped Safety Upgrades on Atlantic Ave (BED-785A, NDF-ATLAV) | 7 | CONSTRUCTION TO 75% | 2019-03-23 | 2021-03-11 | 2019-06-20 | 2020-02-14
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD10105 | Ped Safety Upgrades on Atlantic Ave (BED-785A, NDF-ATLAV) | 8 | ORIGINAL EQUIP & FURNISHING | 2019-03-23 | 2021-03-11 | 2020-02-15 | 2020-05-14
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD10105 | Ped Safety Upgrades on Atlantic Ave (BED-785A, NDF-ATLAV) | 9 | SUBSTANTIAL COMPLETION | 2019-03-23 | 2021-03-11 | 2020-05-15 | 2020-07-13
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD10105 | Ped Safety Upgrades on Atlantic Ave (BED-785A, NDF-ATLAV) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-03-23 | 2021-03-11 | 2020-07-14 | 2022-11-23
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD10105A | Ped Safety Upgrades on Atlantic Ave - Phase 2 (BED-785B) | 1 | DEVELOP SCOPE | 2018-06-30 | 2018-09-27 | 2017-03-03 | 2017-05-31
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD10105A | Ped Safety Upgrades on Atlantic Ave - Phase 2 (BED-785B) | 2 | PRELIMINARY DESIGN | 2018-09-28 | 2019-01-25 | 2017-06-01 | 2017-11-27
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD10105A | Ped Safety Upgrades on Atlantic Ave - Phase 2 (BED-785B) | 3 | FINAL DESIGN | 2019-01-26 | 2019-07-24 | 2017-11-28 | 2018-07-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD10105A | Ped Safety Upgrades on Atlantic Ave - Phase 2 (BED-785B) | 4 | BID AWARD AND REGISTER CONTRCT | 2019-07-25 | 2019-10-22 | 2018-07-26 | 2018-10-23
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD10105A | Ped Safety Upgrades on Atlantic Ave - Phase 2 (BED-785B) | 5 | CONSTRUCTION TO 25% | 2019-10-23 | 2020-02-19 | 2018-10-24 | 2019-02-20
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD10105A | Ped Safety Upgrades on Atlantic Ave - Phase 2 (BED-785B) | 6 | CONSTRUCTION TO 50% | 2020-02-20 | 2020-06-18 | 2019-02-21 | 2019-06-20
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD10105A | Ped Safety Upgrades on Atlantic Ave - Phase 2 (BED-785B) | 7 | CONSTRUCTION TO 75% | 2020-06-19 | 2020-10-16 | 2019-06-21 | 2019-10-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD10105A | Ped Safety Upgrades on Atlantic Ave - Phase 2 (BED-785B) | 8 | ORIGINAL EQUIP & FURNISHING | 2020-10-17 | 2021-01-14 | 2019-10-19 | 2020-01-16
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD10105A | Ped Safety Upgrades on Atlantic Ave - Phase 2 (BED-785B) | 9 | SUBSTANTIAL COMPLETION | 2021-01-15 | 2021-03-15 | 2020-01-17 | 2020-03-16
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD10105A | Ped Safety Upgrades on Atlantic Ave - Phase 2 (BED-785B) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-16 | 2021-04-14 | 2020-03-17 | 2023-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK002377 | East 72nd Street Reconstruction Brooklyn | 1 | DEVELOP SCOPE | 2012-09-30 | 2012-12-28 | 2012-09-30 | 2012-12-28
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK002377 | East 72nd Street Reconstruction Brooklyn | 2 | PRELIMINARY DESIGN | 2012-12-29 | 2013-04-27 | 2012-12-29 | 2013-04-27
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK002377 | East 72nd Street Reconstruction Brooklyn | 3 | FINAL DESIGN | 2013-04-28 | 2013-10-24 | 2013-04-28 | 2013-10-24
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK002377 | East 72nd Street Reconstruction Brooklyn | 4 | BID AWARD AND REGISTER CONTRCT | 2013-10-25 | 2014-01-22 | 2013-10-25 | 2014-01-22
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK002377 | East 72nd Street Reconstruction Brooklyn | 5 | CONSTRUCTION TO 25% | 2014-01-23 | 2014-05-22 | 2014-01-23 | 2014-05-22
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK002377 | East 72nd Street Reconstruction Brooklyn | 6 | CONSTRUCTION TO 50% | 2014-05-23 | 2014-09-19 | 2014-05-23 | 2014-09-19
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK002377 | East 72nd Street Reconstruction Brooklyn | 7 | CONSTRUCTION TO 75% | 2014-09-20 | 2015-01-17 | 2014-09-20 | 2015-01-17
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK002377 | East 72nd Street Reconstruction Brooklyn | 8 | ORIGINAL EQUIP & FURNISHING | 2015-01-18 | 2015-04-17 | 2015-01-18 | 2015-04-17
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK002377 | East 72nd Street Reconstruction Brooklyn | 9 | SUBSTANTIAL COMPLETION | 2015-04-18 | 2015-06-16 | 2015-04-18 | 2015-06-16
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK002377 | East 72nd Street Reconstruction Brooklyn | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-06-17 | 2022-07-16 | 2015-06-17 | 2030-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK100BUS | Utica Ave Bus Priority | 1 | DEVELOP SCOPE | 2013-06-30 | 2013-09-27 | 2013-06-30 | 2013-09-27
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK100BUS | Utica Ave Bus Priority | 2 | PRELIMINARY DESIGN | 2013-09-28 | 2014-01-25 | 2013-09-28 | 2014-01-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK100BUS | Utica Ave Bus Priority | 3 | FINAL DESIGN | 2014-01-26 | 2014-07-24 | 2014-01-26 | 2016-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK100BUS | Utica Ave Bus Priority | 4 | BID AWARD AND REGISTER CONTRCT | 2014-07-25 | 2014-10-22 | 2016-07-01 | 2016-09-28
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK100BUS | Utica Ave Bus Priority | 5 | CONSTRUCTION TO 25% | 2014-10-23 | 2015-02-19 | 2016-09-29 | 2017-01-26
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK100BUS | Utica Ave Bus Priority | 6 | CONSTRUCTION TO 50% | 2015-02-20 | 2015-06-19 | 2017-01-27 | 2017-05-26
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK100BUS | Utica Ave Bus Priority | 7 | CONSTRUCTION TO 75% | 2015-06-20 | 2015-10-17 | 2017-05-27 | 2017-09-23
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK100BUS | Utica Ave Bus Priority | 8 | ORIGINAL EQUIP & FURNISHING | 2015-10-18 | 2016-01-15 | 2017-09-24 | 2017-09-23
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK100BUS | Utica Ave Bus Priority | 9 | SUBSTANTIAL COMPLETION | 2016-01-16 | 2016-03-15 | 2017-09-24 | 2017-09-23
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK100BUS | Utica Ave Bus Priority | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-16 | 2016-04-14 | 2017-09-24 | 2022-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK100SBC | South Brooklyn Crosstown SBS | 1 | DEVELOP SCOPE | 2017-06-30 | 2017-09-27 | 2017-06-30 | 2017-09-27
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK100SBC | South Brooklyn Crosstown SBS | 2 | PRELIMINARY DESIGN | 2017-09-28 | 2018-01-25 | 2017-09-28 | 2019-01-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK100SBC | South Brooklyn Crosstown SBS | 3 | FINAL DESIGN | 2018-01-26 | 2018-07-24 | 2019-01-26 | 2020-01-07
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK100SBC | South Brooklyn Crosstown SBS | 4 | BID AWARD AND REGISTER CONTRCT | 2018-07-25 | 2018-10-22 | 2020-01-08 | 2021-08-02
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK100SBC | South Brooklyn Crosstown SBS | 5 | CONSTRUCTION TO 25% | 2018-10-23 | 2019-02-19 | 2021-08-03 | 2021-11-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK100SBC | South Brooklyn Crosstown SBS | 6 | CONSTRUCTION TO 50% | 2019-02-20 | 2019-06-19 | 2021-12-01 | 2022-03-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK100SBC | South Brooklyn Crosstown SBS | 7 | CONSTRUCTION TO 75% | 2019-06-20 | 2019-10-17 | 2022-03-31 | 2022-07-28
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK100SBC | South Brooklyn Crosstown SBS | 8 | ORIGINAL EQUIP & FURNISHING | 2019-10-18 | 2020-01-15 | 2022-07-29 | 2022-10-26
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK100SBC | South Brooklyn Crosstown SBS | 9 | SUBSTANTIAL COMPLETION | 2020-01-16 | 2020-03-15 | 2022-10-27 | 2022-12-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK100SBC | South Brooklyn Crosstown SBS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-03-16 | 2020-04-14 | 2022-12-26 | 2024-06-22
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1048C | KENT AVE | 1 | DEVELOP SCOPE | 2017-03-01 | 2017-05-29 | 2017-03-01 | 2017-05-29
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1048C | KENT AVE | 2 | PRELIMINARY DESIGN | 2017-05-30 | 2017-09-26 | 2017-05-30 | 2017-09-26
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1048C | KENT AVE | 3 | FINAL DESIGN | 2017-09-27 | 2018-03-25 | 2017-09-27 | 2018-03-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1048C | KENT AVE | 4 | BID AWARD AND REGISTER CONTRCT | 2018-03-26 | 2018-06-23 | 2018-03-26 | 2018-06-23
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1048C | KENT AVE | 5 | CONSTRUCTION TO 25% | 2018-06-24 | 2018-10-21 | 2018-06-24 | 2018-10-21
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1048C | KENT AVE | 6 | CONSTRUCTION TO 50% | 2018-10-22 | 2019-02-18 | 2018-10-22 | 2019-02-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1048C | KENT AVE | 7 | CONSTRUCTION TO 75% | 2019-02-19 | 2019-06-18 | 2019-02-19 | 2019-06-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1048C | KENT AVE | 8 | ORIGINAL EQUIP & FURNISHING | 2019-06-19 | 2019-09-16 | 2019-06-19 | 2019-09-16
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1048C | KENT AVE | 9 | SUBSTANTIAL COMPLETION | 2019-09-17 | 2019-11-15 | 2019-09-17 | 2019-11-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1048C | KENT AVE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-11-16 | 2019-12-15 | 2019-11-16 | 2022-11-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1048D | BK Waterfront Greenway:Sunset Pk Gowanus Connect BED-802 | 1 | DEVELOP SCOPE | 2015-02-16 | 2015-05-16 | 2015-02-16 | 2015-05-16
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1048D | BK Waterfront Greenway:Sunset Pk Gowanus Connect BED-802 | 2 | PRELIMINARY DESIGN | 2015-05-17 | 2015-09-13 | 2015-05-17 | 2015-09-13
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1048D | BK Waterfront Greenway:Sunset Pk Gowanus Connect BED-802 | 3 | FINAL DESIGN | 2015-09-14 | 2016-03-11 | 2015-09-14 | 2016-03-11
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1048D | BK Waterfront Greenway:Sunset Pk Gowanus Connect BED-802 | 4 | BID AWARD AND REGISTER CONTRCT | 2016-03-12 | 2016-06-09 | 2016-03-12 | 2016-06-09
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1048D | BK Waterfront Greenway:Sunset Pk Gowanus Connect BED-802 | 5 | CONSTRUCTION TO 25% | 2016-06-10 | 2016-10-07 | 2016-06-10 | 2016-10-07
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1048D | BK Waterfront Greenway:Sunset Pk Gowanus Connect BED-802 | 6 | CONSTRUCTION TO 50% | 2016-10-08 | 2017-02-04 | 2016-10-08 | 2017-02-04
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1048D | BK Waterfront Greenway:Sunset Pk Gowanus Connect BED-802 | 7 | CONSTRUCTION TO 75% | 2017-02-05 | 2017-06-04 | 2017-02-05 | 2017-06-04
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1048D | BK Waterfront Greenway:Sunset Pk Gowanus Connect BED-802 | 8 | ORIGINAL EQUIP & FURNISHING | 2017-06-05 | 2017-09-02 | 2017-06-05 | 2017-09-02
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1048D | BK Waterfront Greenway:Sunset Pk Gowanus Connect BED-802 | 9 | SUBSTANTIAL COMPLETION | 2017-09-03 | 2017-11-01 | 2017-09-03 | 2017-11-01
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1048D | BK Waterfront Greenway:Sunset Pk Gowanus Connect BED-802 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-11-02 | 2017-12-01 | 2017-11-02 | 2024-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1048E | Brooklyn Waterfront Greenway - Commercial Street/Ash Street | 1 | DEVELOP SCOPE | 2022-06-30 | 2022-09-27 | 2022-06-30 | 2022-09-27
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1048E | Brooklyn Waterfront Greenway - Commercial Street/Ash Street | 2 | PRELIMINARY DESIGN | 2022-09-28 | 2023-01-25 | 2022-09-28 | 2023-01-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1048E | Brooklyn Waterfront Greenway - Commercial Street/Ash Street | 3 | FINAL DESIGN | 2023-01-26 | 2023-07-24 | 2023-01-26 | 2023-07-24
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1048E | Brooklyn Waterfront Greenway - Commercial Street/Ash Street | 4 | BID AWARD AND REGISTER CONTRCT | 2023-07-25 | 2023-10-22 | 2023-07-25 | 2023-10-22
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1048E | Brooklyn Waterfront Greenway - Commercial Street/Ash Street | 5 | CONSTRUCTION TO 25% | 2023-10-23 | 2024-02-19 | 2023-10-23 | 2024-02-19
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1048E | Brooklyn Waterfront Greenway - Commercial Street/Ash Street | 6 | CONSTRUCTION TO 50% | 2024-02-20 | 2024-06-18 | 2024-02-20 | 2024-06-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1048E | Brooklyn Waterfront Greenway - Commercial Street/Ash Street | 7 | CONSTRUCTION TO 75% | 2024-06-19 | 2024-10-16 | 2024-06-19 | 2024-10-16
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1048E | Brooklyn Waterfront Greenway - Commercial Street/Ash Street | 8 | ORIGINAL EQUIP & FURNISHING | 2024-10-17 | 2025-01-14 | 2024-10-17 | 2025-01-14
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1048E | Brooklyn Waterfront Greenway - Commercial Street/Ash Street | 9 | SUBSTANTIAL COMPLETION | 2025-01-15 | 2025-03-15 | 2025-01-15 | 2025-03-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1048E | Brooklyn Waterfront Greenway - Commercial Street/Ash Street | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-03-16 | 2025-04-14 | 2025-03-16 | 2025-04-14
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1048G | OWL'S HEAD-BROOKLYN GREENWAY (SEK002378) | 1 | DEVELOP SCOPE | 2016-06-30 | 2016-09-27 | 2016-06-30 | 2016-09-27
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1048G | OWL'S HEAD-BROOKLYN GREENWAY (SEK002378) | 2 | PRELIMINARY DESIGN | 2016-09-28 | 2017-01-25 | 2016-09-28 | 2017-01-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1048G | OWL'S HEAD-BROOKLYN GREENWAY (SEK002378) | 3 | FINAL DESIGN | 2017-01-26 | 2017-07-24 | 2017-01-26 | 2017-07-24
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1048G | OWL'S HEAD-BROOKLYN GREENWAY (SEK002378) | 4 | BID AWARD AND REGISTER CONTRCT | 2017-07-25 | 2017-10-22 | 2017-07-25 | 2017-10-22
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1048G | OWL'S HEAD-BROOKLYN GREENWAY (SEK002378) | 5 | CONSTRUCTION TO 25% | 2017-10-23 | 2018-02-19 | 2017-10-23 | 2018-02-19
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1048G | OWL'S HEAD-BROOKLYN GREENWAY (SEK002378) | 6 | CONSTRUCTION TO 50% | 2018-02-20 | 2018-06-19 | 2018-02-20 | 2018-06-19
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1048G | OWL'S HEAD-BROOKLYN GREENWAY (SEK002378) | 7 | CONSTRUCTION TO 75% | 2018-06-20 | 2018-10-17 | 2018-06-20 | 2018-10-17
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1048G | OWL'S HEAD-BROOKLYN GREENWAY (SEK002378) | 8 | ORIGINAL EQUIP & FURNISHING | 2018-10-18 | 2019-01-15 | 2018-10-18 | 2019-01-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1048G | OWL'S HEAD-BROOKLYN GREENWAY (SEK002378) | 9 | SUBSTANTIAL COMPLETION | 2019-01-16 | 2019-03-16 | 2019-01-16 | 2019-03-16
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1048G | OWL'S HEAD-BROOKLYN GREENWAY (SEK002378) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-03-17 | 2019-04-15 | 2019-03-17 | 2023-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1148 | JEWEL STREET AREA | 1 | DEVELOP SCOPE | 2003-05-22 | 2003-08-19 | 2003-05-22 | 2003-08-19
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1148 | JEWEL STREET AREA | 2 | PRELIMINARY DESIGN | 2003-08-20 | 2003-12-17 | 2003-08-20 | 2003-12-17
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1148 | JEWEL STREET AREA | 3 | FINAL DESIGN | 2003-12-18 | 2004-06-14 | 2003-12-18 | 2004-06-14
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1148 | JEWEL STREET AREA | 4 | BID AWARD AND REGISTER CONTRCT | 2004-06-15 | 2004-09-12 | 2004-06-15 | 2022-06-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1148 | JEWEL STREET AREA | 5 | CONSTRUCTION TO 25% | 2004-09-13 | 2005-01-10 | 2022-06-16 | 2022-06-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1148 | JEWEL STREET AREA | 6 | CONSTRUCTION TO 50% | 2005-01-11 | 2005-05-10 | 2022-06-16 | 2022-06-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1148 | JEWEL STREET AREA | 7 | CONSTRUCTION TO 75% | 2005-05-11 | 2005-09-07 | 2022-06-16 | 2022-06-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1148 | JEWEL STREET AREA | 8 | ORIGINAL EQUIP & FURNISHING | 2005-09-08 | 2005-12-06 | 2022-06-16 | 2022-06-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1148 | JEWEL STREET AREA | 9 | SUBSTANTIAL COMPLETION | 2005-12-07 | 2006-02-04 | 2022-06-16 | 2022-06-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1148 | JEWEL STREET AREA | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2006-02-05 | 2006-03-06 | 2022-06-16 | 2027-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1170 | Willoughby Street Plaza Reconstruction PINX550.59 | 1 | DEVELOP SCOPE | 2009-06-30 | 2009-10-27 | 2009-06-30 | 2009-10-27
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1170 | Willoughby Street Plaza Reconstruction PINX550.59 | 2 | DESIGN START | 2009-10-28 | 2011-04-20 | 2009-10-28 | 2010-08-26
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1170 | Willoughby Street Plaza Reconstruction PINX550.59 | 3 | CONSTRUCTION START | 2011-04-21 | 2013-04-09 | 2010-08-27 | 2011-01-07
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1170 | Willoughby Street Plaza Reconstruction PINX550.59 | 4 | BID AWARD AND REGISTER CONTRCT | 2011-04-21 | 2013-04-09 | 2011-01-08 | 2011-09-11
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1170 | Willoughby Street Plaza Reconstruction PINX550.59 | 5 | CONSTRUCTION TO 25% | 2011-04-21 | 2013-04-09 | 2011-09-12 | 2012-05-24
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1170 | Willoughby Street Plaza Reconstruction PINX550.59 | 6 | CONSTRUCTION TO 50% | 2011-04-21 | 2013-04-09 | 2012-05-25 | 2013-02-04
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1170 | Willoughby Street Plaza Reconstruction PINX550.59 | 7 | CONSTRUCTION TO 75% | 2011-04-21 | 2013-04-09 | 2013-02-05 | 2016-03-02
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1170 | Willoughby Street Plaza Reconstruction PINX550.59 | 8 | ORIGINAL EQUIP & FURNISHING | 2011-04-21 | 2013-04-09 | 2016-03-03 | 2016-03-02
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1170 | Willoughby Street Plaza Reconstruction PINX550.59 | 9 | SUBSTANTIAL COMPLETION | 2011-04-21 | 2013-04-09 | 2016-03-03 | 2016-03-02
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1170 | Willoughby Street Plaza Reconstruction PINX550.59 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2011-04-21 | 2013-04-09 | 2016-03-03 | 2026-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1182 | Belt Parkway Guardrails | 1 | DEVELOP SCOPE | 2019-03-01 | 2019-05-29 | 2019-03-01 | 2019-05-29
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1182 | Belt Parkway Guardrails | 2 | PRELIMINARY DESIGN | 2019-05-30 | 2019-09-26 | 2019-05-30 | 2019-09-26
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1182 | Belt Parkway Guardrails | 3 | FINAL DESIGN | 2019-09-27 | 2020-03-24 | 2019-09-27 | 2020-03-24
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1182 | Belt Parkway Guardrails | 4 | BID AWARD AND REGISTER CONTRCT | 2020-03-25 | 2020-06-22 | 2020-03-25 | 2020-06-22
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1182 | Belt Parkway Guardrails | 5 | CONSTRUCTION TO 25% | 2020-06-23 | 2020-10-20 | 2020-06-23 | 2020-10-20
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1182 | Belt Parkway Guardrails | 6 | CONSTRUCTION TO 50% | 2020-10-21 | 2021-02-17 | 2020-10-21 | 2021-02-17
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1182 | Belt Parkway Guardrails | 7 | CONSTRUCTION TO 75% | 2021-02-18 | 2021-06-17 | 2021-02-18 | 2021-06-17
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1182 | Belt Parkway Guardrails | 8 | ORIGINAL EQUIP & FURNISHING | 2021-06-18 | 2021-09-15 | 2021-06-18 | 2021-09-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1182 | Belt Parkway Guardrails | 9 | SUBSTANTIAL COMPLETION | 2021-09-16 | 2021-11-14 | 2021-09-16 | 2021-11-14
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1182 | Belt Parkway Guardrails | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-11-15 | 2023-06-30 | 2021-11-15 | 2025-12-27
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1310 | Broadway Junction | 2 | PRELIMINARY DESIGN | 2012-09-28 | 2013-01-25 | 2012-09-28 | 2013-01-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1310 | Broadway Junction | 3 | FINAL DESIGN | 2013-01-26 | 2013-07-24 | 2013-01-26 | 2014-06-03
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1310 | Broadway Junction | 4 | BID AWARD AND REGISTER CONTRCT | 2013-07-25 | 2013-10-22 | 2014-06-04 | 2014-09-01
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1310 | Broadway Junction | 5 | CONSTRUCTION TO 25% | 2013-10-23 | 2014-02-19 | 2014-09-02 | 2015-01-29
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1310 | Broadway Junction | 6 | CONSTRUCTION TO 50% | 2014-02-20 | 2014-06-19 | 2015-01-30 | 2015-06-28
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1310 | Broadway Junction | 7 | CONSTRUCTION TO 75% | 2014-06-20 | 2014-10-17 | 2015-06-29 | 2015-12-01
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1310 | Broadway Junction | 8 | ORIGINAL EQUIP & FURNISHING | 2014-10-18 | 2015-01-15 | 2015-12-02 | 2016-02-29
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1310 | Broadway Junction | 9 | SUBSTANTIAL COMPLETION | 2015-01-16 | 2015-03-16 | 2016-03-01 | 2016-04-29
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1310 | Broadway Junction | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-17 | 2015-04-15 | 2016-04-30 | 2020-05-29
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1669A | 4th Ave Safety Improvements - Phase A | 1 | DEVELOP SCOPE | 2019-03-01 | 2019-05-29 | 2019-03-01 | 2019-05-29
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1669A | 4th Ave Safety Improvements - Phase A | 2 | PRELIMINARY DESIGN | 2019-05-30 | 2019-09-26 | 2019-05-30 | 2019-09-26
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1669A | 4th Ave Safety Improvements - Phase A | 3 | FINAL DESIGN | 2019-09-27 | 2020-03-24 | 2019-09-27 | 2020-03-24
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1669A | 4th Ave Safety Improvements - Phase A | 4 | BID AWARD AND REGISTER CONTRCT | 2020-03-25 | 2020-06-22 | 2020-03-25 | 2020-06-22
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1669A | 4th Ave Safety Improvements - Phase A | 5 | CONSTRUCTION TO 25% | 2020-06-23 | 2020-10-20 | 2020-06-23 | 2020-10-20
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1669A | 4th Ave Safety Improvements - Phase A | 6 | CONSTRUCTION TO 50% | 2020-10-21 | 2021-02-17 | 2020-10-21 | 2021-02-17
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1669A | 4th Ave Safety Improvements - Phase A | 7 | CONSTRUCTION TO 75% | 2021-02-18 | 2021-06-17 | 2021-02-18 | 2021-06-17
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1669A | 4th Ave Safety Improvements - Phase A | 8 | ORIGINAL EQUIP & FURNISHING | 2021-06-18 | 2021-09-15 | 2021-06-18 | 2021-09-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1669A | 4th Ave Safety Improvements - Phase A | 9 | SUBSTANTIAL COMPLETION | 2021-09-16 | 2021-11-14 | 2021-09-16 | 2021-11-14
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1669A | 4th Ave Safety Improvements - Phase A | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-11-15 | 2021-12-14 | 2021-11-15 | 2025-12-01
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1672 | WASHINGTON AVENUE SAFETY IMPROVEMENTS | 1 | DEVELOP SCOPE | 2020-03-01 | 2020-05-29 | 2020-03-01 | 2020-05-29
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1672 | WASHINGTON AVENUE SAFETY IMPROVEMENTS | 2 | PRELIMINARY DESIGN | 2020-05-30 | 2020-09-26 | 2020-05-30 | 2020-09-26
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1672 | WASHINGTON AVENUE SAFETY IMPROVEMENTS | 3 | FINAL DESIGN | 2020-09-27 | 2021-03-25 | 2020-09-27 | 2021-03-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1672 | WASHINGTON AVENUE SAFETY IMPROVEMENTS | 4 | BID AWARD AND REGISTER CONTRCT | 2021-03-26 | 2021-06-23 | 2021-03-26 | 2021-06-23
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1672 | WASHINGTON AVENUE SAFETY IMPROVEMENTS | 5 | CONSTRUCTION TO 25% | 2021-06-24 | 2021-10-21 | 2021-06-24 | 2021-10-21
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1672 | WASHINGTON AVENUE SAFETY IMPROVEMENTS | 6 | CONSTRUCTION TO 50% | 2021-10-22 | 2022-02-18 | 2021-10-22 | 2022-02-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1672 | WASHINGTON AVENUE SAFETY IMPROVEMENTS | 7 | CONSTRUCTION TO 75% | 2022-02-19 | 2022-06-18 | 2022-02-19 | 2022-06-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1672 | WASHINGTON AVENUE SAFETY IMPROVEMENTS | 8 | ORIGINAL EQUIP & FURNISHING | 2022-06-19 | 2022-09-16 | 2022-06-19 | 2022-09-16
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1672 | WASHINGTON AVENUE SAFETY IMPROVEMENTS | 9 | SUBSTANTIAL COMPLETION | 2022-09-17 | 2022-11-15 | 2022-09-17 | 2022-11-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1672 | WASHINGTON AVENUE SAFETY IMPROVEMENTS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-11-16 | 2022-12-15 | 2022-11-16 | 2022-12-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK2048 | Jamaica Bay Greenway - Paerdegat Ave.North Connector BED-883 | 1 | DEVELOP SCOPE | 2016-06-30 | 2016-09-27 | 2016-06-30 | 2016-09-27
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK2048 | Jamaica Bay Greenway - Paerdegat Ave.North Connector BED-883 | 2 | PRELIMINARY DESIGN | 2016-09-28 | 2017-01-25 | 2016-09-28 | 2017-01-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK2048 | Jamaica Bay Greenway - Paerdegat Ave.North Connector BED-883 | 3 | FINAL DESIGN | 2017-01-26 | 2017-07-24 | 2017-01-26 | 2017-07-24
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK2048 | Jamaica Bay Greenway - Paerdegat Ave.North Connector BED-883 | 4 | BID AWARD AND REGISTER CONTRCT | 2017-07-25 | 2017-10-22 | 2017-07-25 | 2017-10-22
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK2048 | Jamaica Bay Greenway - Paerdegat Ave.North Connector BED-883 | 5 | CONSTRUCTION TO 25% | 2017-10-23 | 2018-02-19 | 2017-10-23 | 2018-02-19
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK2048 | Jamaica Bay Greenway - Paerdegat Ave.North Connector BED-883 | 6 | CONSTRUCTION TO 50% | 2018-02-20 | 2018-06-19 | 2018-02-20 | 2018-06-19
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK2048 | Jamaica Bay Greenway - Paerdegat Ave.North Connector BED-883 | 7 | CONSTRUCTION TO 75% | 2018-06-20 | 2018-10-17 | 2018-06-20 | 2018-10-17
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK2048 | Jamaica Bay Greenway - Paerdegat Ave.North Connector BED-883 | 8 | ORIGINAL EQUIP & FURNISHING | 2018-10-18 | 2019-01-15 | 2018-10-18 | 2019-01-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK2048 | Jamaica Bay Greenway - Paerdegat Ave.North Connector BED-883 | 9 | SUBSTANTIAL COMPLETION | 2019-01-16 | 2019-03-16 | 2019-01-16 | 2019-03-16
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK2048 | Jamaica Bay Greenway - Paerdegat Ave.North Connector BED-883 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-03-17 | 2019-04-15 | 2019-03-17 | 2024-10-17
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK614D | RECONSTRUCTION OF BERGEN AVENUE AREA, BKLYN /BED-784 | 1 | DEVELOP SCOPE | 2005-05-21 | 2005-08-18 | 2005-05-21 | 2005-08-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK614D | RECONSTRUCTION OF BERGEN AVENUE AREA, BKLYN /BED-784 | 2 | PRELIMINARY DESIGN | 2005-08-19 | 2005-12-16 | 2005-08-19 | 2005-12-16
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK614D | RECONSTRUCTION OF BERGEN AVENUE AREA, BKLYN /BED-784 | 3 | FINAL DESIGN | 2005-12-17 | 2006-06-14 | 2005-12-17 | 2006-06-14
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK614D | RECONSTRUCTION OF BERGEN AVENUE AREA, BKLYN /BED-784 | 4 | BID AWARD AND REGISTER CONTRCT | 2006-06-15 | 2006-09-12 | 2006-06-15 | 2022-09-12
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK614D | RECONSTRUCTION OF BERGEN AVENUE AREA, BKLYN /BED-784 | 5 | CONSTRUCTION TO 25% | 2006-09-13 | 2007-01-10 | 2022-09-13 | 2022-09-12
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK614D | RECONSTRUCTION OF BERGEN AVENUE AREA, BKLYN /BED-784 | 6 | CONSTRUCTION TO 50% | 2007-01-11 | 2007-05-10 | 2022-09-13 | 2022-09-12
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK614D | RECONSTRUCTION OF BERGEN AVENUE AREA, BKLYN /BED-784 | 7 | CONSTRUCTION TO 75% | 2007-05-11 | 2007-09-07 | 2022-09-13 | 2022-09-12
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK614D | RECONSTRUCTION OF BERGEN AVENUE AREA, BKLYN /BED-784 | 8 | ORIGINAL EQUIP & FURNISHING | 2007-09-08 | 2007-12-06 | 2022-09-13 | 2022-09-12
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK614D | RECONSTRUCTION OF BERGEN AVENUE AREA, BKLYN /BED-784 | 9 | SUBSTANTIAL COMPLETION | 2007-12-07 | 2008-02-04 | 2022-09-13 | 2022-09-12
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK614D | RECONSTRUCTION OF BERGEN AVENUE AREA, BKLYN /BED-784 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-02-05 | 2008-03-05 | 2022-09-13 | 2025-10-12
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK639W | RECON: TILLARY STREET | 1 | DEVELOP SCOPE | 2005-05-21 | 2005-08-18 | 2012-03-01 | 2012-05-29
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK639W | RECON: TILLARY STREET | 2 | PRELIMINARY DESIGN | 2005-08-19 | 2005-12-16 | 2012-05-30 | 2012-09-26
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK639W | RECON: TILLARY STREET | 3 | FINAL DESIGN | 2005-12-17 | 2006-06-14 | 2012-09-27 | 2015-05-03
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK639W | RECON: TILLARY STREET | 4 | BID AWARD AND REGISTER CONTRCT | 2006-06-15 | 2006-09-12 | 2015-05-04 | 2015-08-01
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK639W | RECON: TILLARY STREET | 5 | CONSTRUCTION TO 25% | 2006-09-13 | 2007-01-10 | 2015-08-02 | 2016-04-07
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK639W | RECON: TILLARY STREET | 6 | CONSTRUCTION TO 50% | 2007-01-11 | 2007-05-10 | 2016-04-08 | 2017-03-23
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK639W | RECON: TILLARY STREET | 7 | CONSTRUCTION TO 75% | 2007-05-11 | 2007-09-07 | 2017-03-24 | 2018-03-08
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK639W | RECON: TILLARY STREET | 8 | ORIGINAL EQUIP & FURNISHING | 2007-09-08 | 2007-12-06 | 2018-03-09 | 2018-06-06
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK639W | RECON: TILLARY STREET | 9 | SUBSTANTIAL COMPLETION | 2007-12-07 | 2008-02-04 | 2018-06-07 | 2018-08-05
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK639W | RECON: TILLARY STREET | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-02-05 | 2008-03-05 | 2018-08-06 | 2022-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK639WA | RECON: TILLARY STREET PHASE 2 | 1 | DEVELOP SCOPE | 2017-05-21 | 2017-08-18 | 2017-05-21 | 2017-08-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK639WA | RECON: TILLARY STREET PHASE 2 | 2 | PRELIMINARY DESIGN | 2017-08-19 | 2017-12-16 | 2017-08-19 | 2017-12-16
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK639WA | RECON: TILLARY STREET PHASE 2 | 3 | FINAL DESIGN | 2017-12-17 | 2018-06-14 | 2017-12-17 | 2018-06-14
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK639WA | RECON: TILLARY STREET PHASE 2 | 4 | BID AWARD AND REGISTER CONTRCT | 2018-06-15 | 2018-09-12 | 2018-06-15 | 2018-09-12
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK639WA | RECON: TILLARY STREET PHASE 2 | 5 | CONSTRUCTION TO 25% | 2018-09-13 | 2019-01-10 | 2018-09-13 | 2019-01-10
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK639WA | RECON: TILLARY STREET PHASE 2 | 6 | CONSTRUCTION TO 50% | 2019-01-11 | 2019-05-10 | 2019-01-11 | 2019-05-10
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK639WA | RECON: TILLARY STREET PHASE 2 | 7 | CONSTRUCTION TO 75% | 2019-05-11 | 2019-09-07 | 2019-05-11 | 2019-09-07
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK639WA | RECON: TILLARY STREET PHASE 2 | 8 | ORIGINAL EQUIP & FURNISHING | 2019-09-08 | 2019-12-06 | 2019-09-08 | 2019-12-06
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK639WA | RECON: TILLARY STREET PHASE 2 | 9 | SUBSTANTIAL COMPLETION | 2019-12-07 | 2020-02-04 | 2019-12-07 | 2020-02-04
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK639WA | RECON: TILLARY STREET PHASE 2 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-02-05 | 2020-03-05 | 2020-02-05 | 2023-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK700B | Reconstruction of Columbia Street Area Phase II (BED-768B) | 1 | DEVELOP SCOPE | 2003-05-22 | 2003-08-19 | 2003-05-22 | 2003-08-19
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK700B | Reconstruction of Columbia Street Area Phase II (BED-768B) | 2 | PRELIMINARY DESIGN | 2003-08-20 | 2003-12-17 | 2003-08-20 | 2003-12-17
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK700B | Reconstruction of Columbia Street Area Phase II (BED-768B) | 3 | FINAL DESIGN | 2003-12-18 | 2004-06-14 | 2003-12-18 | 2004-06-14
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK700B | Reconstruction of Columbia Street Area Phase II (BED-768B) | 4 | BID AWARD AND REGISTER CONTRCT | 2004-06-15 | 2004-09-12 | 2004-06-15 | 2022-06-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK700B | Reconstruction of Columbia Street Area Phase II (BED-768B) | 5 | CONSTRUCTION TO 25% | 2004-09-13 | 2005-01-10 | 2022-06-26 | 2022-06-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK700B | Reconstruction of Columbia Street Area Phase II (BED-768B) | 6 | CONSTRUCTION TO 50% | 2005-01-11 | 2005-05-10 | 2022-06-26 | 2022-06-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK700B | Reconstruction of Columbia Street Area Phase II (BED-768B) | 7 | CONSTRUCTION TO 75% | 2005-05-11 | 2005-09-07 | 2022-06-26 | 2022-06-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK700B | Reconstruction of Columbia Street Area Phase II (BED-768B) | 8 | ORIGINAL EQUIP & FURNISHING | 2005-09-08 | 2005-12-06 | 2022-06-26 | 2022-06-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK700B | Reconstruction of Columbia Street Area Phase II (BED-768B) | 9 | SUBSTANTIAL COMPLETION | 2005-12-07 | 2006-02-04 | 2022-06-26 | 2022-06-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK700B | Reconstruction of Columbia Street Area Phase II (BED-768B) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2006-02-05 | 2006-03-06 | 2022-06-26 | 2025-07-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK779W | EMPIRE BOULEVARD | 9 | SUBSTANTIAL COMPLETION | 2007-12-07 | 2008-02-04 | 2018-07-03 | 2018-08-31
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK779W | EMPIRE BOULEVARD | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-02-05 | 2008-03-05 | 2018-09-01 | 2024-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK797W | Schenck Avenue | 1 | DEVELOP SCOPE | 2015-02-16 | 2015-05-16 | 2015-02-16 | 2016-08-23
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK797W | Schenck Avenue | 2 | PRELIMINARY DESIGN | 2015-05-17 | 2015-09-13 | 2016-08-24 | 2016-12-21
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK797W | Schenck Avenue | 3 | FINAL DESIGN | 2015-09-14 | 2016-03-11 | 2016-12-22 | 2019-04-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK797W | Schenck Avenue | 4 | BID AWARD AND REGISTER CONTRCT | 2016-03-12 | 2016-06-09 | 2019-04-26 | 2019-07-24
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK797W | Schenck Avenue | 5 | CONSTRUCTION TO 25% | 2016-06-10 | 2016-10-07 | 2019-07-25 | 2019-11-21
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK797W | Schenck Avenue | 6 | CONSTRUCTION TO 50% | 2016-10-08 | 2017-02-04 | 2019-11-22 | 2020-03-20
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK797W | Schenck Avenue | 7 | CONSTRUCTION TO 75% | 2017-02-05 | 2017-06-04 | 2020-03-21 | 2020-07-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK797W | Schenck Avenue | 8 | ORIGINAL EQUIP & FURNISHING | 2017-06-05 | 2017-09-02 | 2020-07-19 | 2020-10-16
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK797W | Schenck Avenue | 9 | SUBSTANTIAL COMPLETION | 2017-09-03 | 2017-11-01 | 2020-10-17 | 2020-12-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK797W | Schenck Avenue | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-11-02 | 2017-12-01 | 2020-12-16 | 2024-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK876 | RECONSTRUCTION OF WYCKOFF AVENUE, BROOKLYN | 1 | DEVELOP SCOPE | 2004-05-21 | 2004-08-18 | 2004-05-21 | 2004-08-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK876 | RECONSTRUCTION OF WYCKOFF AVENUE, BROOKLYN | 2 | PRELIMINARY DESIGN | 2004-08-19 | 2004-12-16 | 2004-08-19 | 2004-12-16
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK876 | RECONSTRUCTION OF WYCKOFF AVENUE, BROOKLYN | 3 | FINAL DESIGN | 2004-12-17 | 2005-06-14 | 2004-12-17 | 2005-06-14
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK876 | RECONSTRUCTION OF WYCKOFF AVENUE, BROOKLYN | 4 | BID AWARD AND REGISTER CONTRCT | 2005-06-15 | 2005-09-12 | 2005-06-15 | 2022-06-12
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK876 | RECONSTRUCTION OF WYCKOFF AVENUE, BROOKLYN | 5 | CONSTRUCTION TO 25% | 2005-09-13 | 2006-01-10 | 2022-06-13 | 2022-06-12
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK876 | RECONSTRUCTION OF WYCKOFF AVENUE, BROOKLYN | 6 | CONSTRUCTION TO 50% | 2006-01-11 | 2006-05-10 | 2022-06-13 | 2022-06-12
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK876 | RECONSTRUCTION OF WYCKOFF AVENUE, BROOKLYN | 7 | CONSTRUCTION TO 75% | 2006-05-11 | 2006-09-07 | 2022-06-13 | 2022-06-12
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK876 | RECONSTRUCTION OF WYCKOFF AVENUE, BROOKLYN | 8 | ORIGINAL EQUIP & FURNISHING | 2006-09-08 | 2006-12-06 | 2022-06-13 | 2022-06-12
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK876 | RECONSTRUCTION OF WYCKOFF AVENUE, BROOKLYN | 9 | SUBSTANTIAL COMPLETION | 2006-12-07 | 2007-02-04 | 2022-06-13 | 2022-06-12
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK876 | RECONSTRUCTION OF WYCKOFF AVENUE, BROOKLYN | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2007-02-05 | 2007-03-06 | 2022-06-13 | 2025-07-12
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK900 | Brownsville Pedestrian Safety Improvements | 1 | DEVELOP SCOPE | 2022-06-30 | 2022-09-27 | 2017-06-12 | 2019-07-26
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK900 | Brownsville Pedestrian Safety Improvements | 2 | PRELIMINARY DESIGN | 2022-09-28 | 2023-01-25 | 2019-11-19 | 2021-04-04
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK900 | Brownsville Pedestrian Safety Improvements | 3 | FINAL DESIGN | 2023-01-26 | 2023-07-24 | 2021-04-05 | 2021-10-01
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK900 | Brownsville Pedestrian Safety Improvements | 4 | BID AWARD AND REGISTER CONTRCT | 2023-07-25 | 2023-10-22 | 2021-10-02 | 2021-12-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK900 | Brownsville Pedestrian Safety Improvements | 5 | CONSTRUCTION TO 25% | 2023-10-23 | 2024-02-19 | 2021-12-31 | 2022-04-29
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK900 | Brownsville Pedestrian Safety Improvements | 6 | CONSTRUCTION TO 50% | 2024-02-20 | 2024-06-18 | 2022-04-30 | 2022-08-27
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK900 | Brownsville Pedestrian Safety Improvements | 7 | CONSTRUCTION TO 75% | 2024-06-19 | 2024-10-16 | 2022-08-28 | 2022-12-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK900 | Brownsville Pedestrian Safety Improvements | 8 | ORIGINAL EQUIP & FURNISHING | 2024-10-17 | 2025-01-14 | 2023-03-15 | 2025-03-03
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK900 | Brownsville Pedestrian Safety Improvements | 9 | SUBSTANTIAL COMPLETION | 2025-01-15 | 2025-03-15 | 2025-03-04 | 2025-05-02
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK900 | Brownsville Pedestrian Safety Improvements | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-03-16 | 2025-04-14 | 2025-05-03 | 2025-06-01
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWKDTBK | Park Avenue - Ingersoll Safety Improvements | 1 | DEVELOP SCOPE | 2019-06-30 | 2019-09-27 | 2019-08-06 | 2020-01-14
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWKDTBK | Park Avenue - Ingersoll Safety Improvements | 2 | PRELIMINARY DESIGN | 2019-09-28 | 2020-01-25 | 2020-01-15 | 2020-05-13
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWKDTBK | Park Avenue - Ingersoll Safety Improvements | 3 | FINAL DESIGN | 2020-01-26 | 2020-07-23 | 2020-05-14 | 2020-11-09
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWKDTBK | Park Avenue - Ingersoll Safety Improvements | 4 | BID AWARD AND REGISTER CONTRCT | 2020-07-24 | 2020-10-21 | 2020-11-10 | 2021-02-07
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWKDTBK | Park Avenue - Ingersoll Safety Improvements | 5 | CONSTRUCTION TO 25% | 2020-10-22 | 2021-02-18 | 2021-02-08 | 2021-06-07
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWKDTBK | Park Avenue - Ingersoll Safety Improvements | 6 | CONSTRUCTION TO 50% | 2021-02-19 | 2021-06-18 | 2021-06-08 | 2021-10-05
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWKDTBK | Park Avenue - Ingersoll Safety Improvements | 7 | CONSTRUCTION TO 75% | 2021-06-19 | 2021-10-16 | 2021-10-06 | 2022-02-02
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWKDTBK | Park Avenue - Ingersoll Safety Improvements | 8 | ORIGINAL EQUIP & FURNISHING | 2021-10-17 | 2022-01-14 | 2022-02-03 | 2022-05-03
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWKDTBK | Park Avenue - Ingersoll Safety Improvements | 9 | SUBSTANTIAL COMPLETION | 2022-01-15 | 2022-03-15 | 2022-05-04 | 2022-07-02
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWKDTBK | Park Avenue - Ingersoll Safety Improvements | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-16 | 2022-04-14 | 2022-07-03 | 2026-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWKF488R | Hamilton Asphalt Plant Roof Replacement | 1 | DEVELOP SCOPE | 2016-06-30 | 2016-10-27 | 2015-06-30 | 2017-07-04
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWKF488R | Hamilton Asphalt Plant Roof Replacement | 2 | DESIGN START | 2016-10-28 | 2018-04-20 | 2017-07-05 | 2017-12-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWKF488R | Hamilton Asphalt Plant Roof Replacement | 3 | CONSTRUCTION START | 2018-04-21 | 2020-04-09 | 2017-12-19 | 2020-05-11
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWKF488R | Hamilton Asphalt Plant Roof Replacement | 4 | BID AWARD AND REGISTER CONTRCT | 2018-04-21 | 2020-04-09 | 2020-05-12 | 2020-12-02
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWKF488R | Hamilton Asphalt Plant Roof Replacement | 5 | CONSTRUCTION TO 25% | 2018-04-21 | 2020-04-09 | 2020-12-03 | 2021-04-01
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWKF488R | Hamilton Asphalt Plant Roof Replacement | 6 | CONSTRUCTION TO 50% | 2018-04-21 | 2020-04-09 | 2021-04-02 | 2021-07-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWKF488R | Hamilton Asphalt Plant Roof Replacement | 7 | CONSTRUCTION TO 75% | 2018-04-21 | 2020-04-09 | 2021-07-31 | 2021-10-28
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWKF488R | Hamilton Asphalt Plant Roof Replacement | 8 | ORIGINAL EQUIP & FURNISHING | 2018-04-21 | 2020-04-09 | 2021-10-29 | 2021-11-01
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWKF488R | Hamilton Asphalt Plant Roof Replacement | 9 | SUBSTANTIAL COMPLETION | 2018-04-21 | 2020-04-09 | 2021-11-02 | 2021-12-02
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWKF488R | Hamilton Asphalt Plant Roof Replacement | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-04-21 | 2020-04-09 | 2021-12-03 | 2022-07-14
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWKKP005 | DUMBO D.M.A. - VINEGAR HILL AREA | 1 | DEVELOP SCOPE | 2012-06-30 | 2012-09-27 | 2011-09-12 | 2012-06-06
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWKKP005 | DUMBO D.M.A. - VINEGAR HILL AREA | 2 | PRELIMINARY DESIGN | 2012-09-28 | 2013-01-25 | 2012-06-07 | 2015-06-04
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWKKP005 | DUMBO D.M.A. - VINEGAR HILL AREA | 3 | FINAL DESIGN | 2013-01-26 | 2013-07-24 | 2015-06-05 | 2015-12-01
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWKKP005 | DUMBO D.M.A. - VINEGAR HILL AREA | 4 | BID AWARD AND REGISTER CONTRCT | 2013-07-25 | 2013-10-22 | 2015-12-02 | 2016-02-29
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWKKP005 | DUMBO D.M.A. - VINEGAR HILL AREA | 5 | CONSTRUCTION TO 25% | 2013-10-23 | 2014-02-19 | 2016-03-01 | 2016-06-28
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWKKP005 | DUMBO D.M.A. - VINEGAR HILL AREA | 6 | CONSTRUCTION TO 50% | 2014-02-20 | 2014-06-19 | 2016-06-29 | 2016-10-26
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWKKP005 | DUMBO D.M.A. - VINEGAR HILL AREA | 7 | CONSTRUCTION TO 75% | 2014-06-20 | 2014-10-17 | 2016-10-27 | 2017-02-23
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWKKP005 | DUMBO D.M.A. - VINEGAR HILL AREA | 8 | ORIGINAL EQUIP & FURNISHING | 2014-10-18 | 2015-01-15 | 2017-02-24 | 2017-05-24
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWKKP005 | DUMBO D.M.A. - VINEGAR HILL AREA | 9 | SUBSTANTIAL COMPLETION | 2015-01-16 | 2015-03-16 | 2017-05-25 | 2017-07-23
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWKKP005 | DUMBO D.M.A. - VINEGAR HILL AREA | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-17 | 2015-04-15 | 2017-07-24 | 2027-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19KC1 | Citywide Complex Pedestrian Ramps - Brooklyn | 1 | DEVELOP SCOPE | 2017-06-30 | 2017-09-27 | 2017-06-30 | 2017-09-27
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19KC1 | Citywide Complex Pedestrian Ramps - Brooklyn | 2 | PRELIMINARY DESIGN | 2017-09-28 | 2018-01-25 | 2017-09-28 | 2018-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19KC1 | Citywide Complex Pedestrian Ramps - Brooklyn | 3 | FINAL DESIGN | 2018-01-26 | 2018-07-24 | 2018-07-01 | 2019-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19KC1 | Citywide Complex Pedestrian Ramps - Brooklyn | 4 | BID AWARD AND REGISTER CONTRCT | 2018-07-25 | 2018-10-22 | 2019-07-01 | 2019-12-31
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19KC1 | Citywide Complex Pedestrian Ramps - Brooklyn | 5 | CONSTRUCTION TO 25% | 2018-10-23 | 2019-02-19 | 2020-01-01 | 2020-04-29
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19KC1 | Citywide Complex Pedestrian Ramps - Brooklyn | 6 | CONSTRUCTION TO 50% | 2019-02-20 | 2019-06-19 | 2020-04-30 | 2020-08-27
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19KC1 | Citywide Complex Pedestrian Ramps - Brooklyn | 7 | CONSTRUCTION TO 75% | 2019-06-20 | 2019-10-17 | 2020-08-28 | 2020-12-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19KC1 | Citywide Complex Pedestrian Ramps - Brooklyn | 8 | ORIGINAL EQUIP & FURNISHING | 2019-10-18 | 2020-01-15 | 2020-12-26 | 2021-03-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19KC1 | Citywide Complex Pedestrian Ramps - Brooklyn | 9 | SUBSTANTIAL COMPLETION | 2020-01-16 | 2020-03-15 | 2021-03-26 | 2021-05-24
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19KC1 | Citywide Complex Pedestrian Ramps - Brooklyn | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-03-16 | 2020-04-14 | 2021-05-25 | 2022-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19KC2 | Citywide Complex Pedestrian Ramps - Brooklyn | 1 | DEVELOP SCOPE | 2017-06-30 | 2017-09-27 | 2017-06-30 | 2017-09-27
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19KC2 | Citywide Complex Pedestrian Ramps - Brooklyn | 2 | PRELIMINARY DESIGN | 2017-09-28 | 2018-01-25 | 2017-09-28 | 2018-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19KC2 | Citywide Complex Pedestrian Ramps - Brooklyn | 3 | FINAL DESIGN | 2018-01-26 | 2018-07-24 | 2018-07-01 | 2019-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19KC2 | Citywide Complex Pedestrian Ramps - Brooklyn | 4 | BID AWARD AND REGISTER CONTRCT | 2018-07-25 | 2018-10-22 | 2019-07-01 | 2019-12-31
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19KC2 | Citywide Complex Pedestrian Ramps - Brooklyn | 5 | CONSTRUCTION TO 25% | 2018-10-23 | 2019-02-19 | 2020-01-01 | 2020-04-29
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19KC2 | Citywide Complex Pedestrian Ramps - Brooklyn | 6 | CONSTRUCTION TO 50% | 2019-02-20 | 2019-06-19 | 2020-04-30 | 2020-08-27
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19KC2 | Citywide Complex Pedestrian Ramps - Brooklyn | 7 | CONSTRUCTION TO 75% | 2019-06-20 | 2019-10-17 | 2020-08-28 | 2020-12-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19KC2 | Citywide Complex Pedestrian Ramps - Brooklyn | 8 | ORIGINAL EQUIP & FURNISHING | 2019-10-18 | 2020-01-15 | 2020-12-26 | 2021-03-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19KC2 | Citywide Complex Pedestrian Ramps - Brooklyn | 9 | SUBSTANTIAL COMPLETION | 2020-01-16 | 2020-03-15 | 2021-03-26 | 2021-05-24
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19KC2 | Citywide Complex Pedestrian Ramps - Brooklyn | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-03-16 | 2020-04-14 | 2021-05-25 | 2021-06-23
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19KC3 | Citywide Complex Pedestrian Ramps - Brooklyn | 1 | DEVELOP SCOPE | 2017-06-30 | 2017-09-27 | 2017-06-30 | 2017-09-27
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19KC3 | Citywide Complex Pedestrian Ramps - Brooklyn | 2 | PRELIMINARY DESIGN | 2017-09-28 | 2018-01-25 | 2017-09-28 | 2018-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19KC3 | Citywide Complex Pedestrian Ramps - Brooklyn | 3 | FINAL DESIGN | 2018-01-26 | 2018-07-24 | 2018-07-01 | 2019-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19KC3 | Citywide Complex Pedestrian Ramps - Brooklyn | 4 | BID AWARD AND REGISTER CONTRCT | 2018-07-25 | 2018-10-22 | 2019-07-01 | 2019-12-31
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19KC3 | Citywide Complex Pedestrian Ramps - Brooklyn | 5 | CONSTRUCTION TO 25% | 2018-10-23 | 2019-02-19 | 2020-01-01 | 2020-04-29
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19KC3 | Citywide Complex Pedestrian Ramps - Brooklyn | 6 | CONSTRUCTION TO 50% | 2019-02-20 | 2019-06-19 | 2020-04-30 | 2020-08-27
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19KC3 | Citywide Complex Pedestrian Ramps - Brooklyn | 7 | CONSTRUCTION TO 75% | 2019-06-20 | 2019-10-17 | 2020-08-28 | 2020-12-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19KC3 | Citywide Complex Pedestrian Ramps - Brooklyn | 8 | ORIGINAL EQUIP & FURNISHING | 2019-10-18 | 2020-01-15 | 2020-12-26 | 2021-03-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19KC3 | Citywide Complex Pedestrian Ramps - Brooklyn | 9 | SUBSTANTIAL COMPLETION | 2020-01-16 | 2020-03-15 | 2021-03-26 | 2021-05-24
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19KC3 | Citywide Complex Pedestrian Ramps - Brooklyn | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-03-16 | 2020-04-14 | 2021-05-25 | 2021-06-23
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2020KC | Non-Standard Ped Ramp Installs - Brooklyn | 1 | DEVELOP SCOPE | 2019-06-30 | 2019-09-27 | 2019-06-30 | 2019-09-27
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2020KC | Non-Standard Ped Ramp Installs - Brooklyn | 2 | PRELIMINARY DESIGN | 2019-09-28 | 2020-01-25 | 2019-09-28 | 2020-01-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2020KC | Non-Standard Ped Ramp Installs - Brooklyn | 3 | FINAL DESIGN | 2020-01-26 | 2020-07-23 | 2020-01-26 | 2020-07-23
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2020KC | Non-Standard Ped Ramp Installs - Brooklyn | 4 | BID AWARD AND REGISTER CONTRCT | 2020-07-24 | 2020-10-21 | 2020-07-24 | 2020-10-21
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2020KC | Non-Standard Ped Ramp Installs - Brooklyn | 5 | CONSTRUCTION TO 25% | 2020-10-22 | 2021-02-18 | 2020-10-22 | 2021-02-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2020KC | Non-Standard Ped Ramp Installs - Brooklyn | 6 | CONSTRUCTION TO 50% | 2021-02-19 | 2021-06-18 | 2021-02-19 | 2021-06-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2020KC | Non-Standard Ped Ramp Installs - Brooklyn | 7 | CONSTRUCTION TO 75% | 2021-06-19 | 2021-10-16 | 2021-06-19 | 2021-10-16
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2020KC | Non-Standard Ped Ramp Installs - Brooklyn | 8 | ORIGINAL EQUIP & FURNISHING | 2021-10-17 | 2022-01-14 | 2021-10-17 | 2022-01-14
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2020KC | Non-Standard Ped Ramp Installs - Brooklyn | 9 | SUBSTANTIAL COMPLETION | 2022-01-15 | 2022-03-15 | 2022-01-15 | 2022-03-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2020KC | Non-Standard Ped Ramp Installs - Brooklyn | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-16 | 2022-04-14 | 2022-03-16 | 2023-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF4 | Multi-Site Pedestrian Safety | 1 | DEVELOP SCOPE | 2011-07-01 | 2011-09-28 | 2011-07-01 | 2011-09-28
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF4 | Multi-Site Pedestrian Safety | 2 | PRELIMINARY DESIGN | 2011-09-29 | 2012-01-26 | 2011-09-29 | 2012-01-26
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF4 | Multi-Site Pedestrian Safety | 3 | FINAL DESIGN | 2012-01-27 | 2012-07-24 | 2012-01-27 | 2017-03-27
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF4 | Multi-Site Pedestrian Safety | 4 | BID AWARD AND REGISTER CONTRCT | 2012-07-25 | 2012-10-22 | 2017-03-28 | 2017-06-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF4 | Multi-Site Pedestrian Safety | 5 | CONSTRUCTION TO 25% | 2012-10-23 | 2013-02-19 | 2017-06-26 | 2017-11-22
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF4 | Multi-Site Pedestrian Safety | 6 | CONSTRUCTION TO 50% | 2013-02-20 | 2013-06-19 | 2017-11-23 | 2018-04-21
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF4 | Multi-Site Pedestrian Safety | 7 | CONSTRUCTION TO 75% | 2013-06-20 | 2013-10-17 | 2018-04-22 | 2018-09-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF4 | Multi-Site Pedestrian Safety | 8 | ORIGINAL EQUIP & FURNISHING | 2013-10-18 | 2014-01-15 | 2018-06-21 | 2018-09-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF4 | Multi-Site Pedestrian Safety | 9 | SUBSTANTIAL COMPLETION | 2014-01-16 | 2014-03-16 | 2018-09-19 | 2018-11-17
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF4 | Multi-Site Pedestrian Safety | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-03-17 | 2014-04-15 | 2018-11-18 | 2022-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF4A | Multi-Site Pedestrian Safety - Phase 4A | 1 | DEVELOP SCOPE | 2017-06-30 | 2017-09-27 | 2017-06-30 | 2017-09-27
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF4A | Multi-Site Pedestrian Safety - Phase 4A | 2 | PRELIMINARY DESIGN | 2017-09-28 | 2018-01-25 | 2017-09-28 | 2018-01-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF4A | Multi-Site Pedestrian Safety - Phase 4A | 3 | FINAL DESIGN | 2018-01-26 | 2018-07-24 | 2018-01-26 | 2018-07-24
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF4A | Multi-Site Pedestrian Safety - Phase 4A | 4 | BID AWARD AND REGISTER CONTRCT | 2018-07-25 | 2018-10-22 | 2018-07-25 | 2018-10-22
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF4A | Multi-Site Pedestrian Safety - Phase 4A | 5 | CONSTRUCTION TO 25% | 2018-10-23 | 2019-02-19 | 2018-10-23 | 2019-02-19
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF4A | Multi-Site Pedestrian Safety - Phase 4A | 6 | CONSTRUCTION TO 50% | 2019-02-20 | 2019-06-19 | 2019-02-20 | 2019-06-19
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF4A | Multi-Site Pedestrian Safety - Phase 4A | 7 | CONSTRUCTION TO 75% | 2019-06-20 | 2019-10-17 | 2019-06-20 | 2019-10-17
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF4A | Multi-Site Pedestrian Safety - Phase 4A | 8 | ORIGINAL EQUIP & FURNISHING | 2019-10-18 | 2020-01-15 | 2019-10-18 | 2020-01-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF4A | Multi-Site Pedestrian Safety - Phase 4A | 9 | SUBSTANTIAL COMPLETION | 2020-01-16 | 2020-03-15 | 2020-01-16 | 2020-03-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF4A | Multi-Site Pedestrian Safety - Phase 4A | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-03-16 | 2020-04-14 | 2020-03-16 | 2022-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF5 | Multi-Site Pedestrian Safety Phase 5 | 1 | DEVELOP SCOPE | 2016-06-30 | 2016-09-27 | 2016-06-30 | 2017-07-31
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF5 | Multi-Site Pedestrian Safety Phase 5 | 2 | PRELIMINARY DESIGN | 2016-09-28 | 2017-01-25 | 2017-08-01 | 2018-08-17
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF5 | Multi-Site Pedestrian Safety Phase 5 | 3 | FINAL DESIGN | 2017-01-26 | 2017-07-24 | 2018-08-18 | 2019-02-13
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF5 | Multi-Site Pedestrian Safety Phase 5 | 4 | BID AWARD AND REGISTER CONTRCT | 2017-07-25 | 2017-10-22 | 2019-02-14 | 2019-05-14
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF5 | Multi-Site Pedestrian Safety Phase 5 | 5 | CONSTRUCTION TO 25% | 2017-10-23 | 2018-02-19 | 2019-05-15 | 2019-09-11
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF5 | Multi-Site Pedestrian Safety Phase 5 | 6 | CONSTRUCTION TO 50% | 2018-02-20 | 2018-06-19 | 2019-09-12 | 2020-01-09
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF5 | Multi-Site Pedestrian Safety Phase 5 | 7 | CONSTRUCTION TO 75% | 2018-06-20 | 2018-10-17 | 2020-01-10 | 2020-05-08
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF5 | Multi-Site Pedestrian Safety Phase 5 | 8 | ORIGINAL EQUIP & FURNISHING | 2018-10-18 | 2019-01-15 | 2020-05-09 | 2020-08-06
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF5 | Multi-Site Pedestrian Safety Phase 5 | 9 | SUBSTANTIAL COMPLETION | 2019-01-16 | 2019-03-16 | 2020-08-07 | 2020-10-05
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF5 | Multi-Site Pedestrian Safety Phase 5 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-03-17 | 2019-04-15 | 2020-10-06 | 2025-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ017K | Osborn Street Plaza | 1 | DEVELOP SCOPE | 2016-06-30 | 2016-09-27 | 2016-06-30 | 2016-09-27
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ017K | Osborn Street Plaza | 2 | PRELIMINARY DESIGN | 2016-09-28 | 2017-01-25 | 2016-09-28 | 2017-01-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ017K | Osborn Street Plaza | 3 | FINAL DESIGN | 2017-01-26 | 2017-07-24 | 2017-01-26 | 2017-07-24
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ017K | Osborn Street Plaza | 4 | BID AWARD AND REGISTER CONTRCT | 2017-07-25 | 2017-10-22 | 2017-07-25 | 2017-10-22
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ017K | Osborn Street Plaza | 5 | CONSTRUCTION TO 25% | 2017-10-23 | 2018-02-19 | 2017-10-23 | 2018-02-19
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ017K | Osborn Street Plaza | 6 | CONSTRUCTION TO 50% | 2018-02-20 | 2018-06-19 | 2018-02-20 | 2018-06-19
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ017K | Osborn Street Plaza | 7 | CONSTRUCTION TO 75% | 2018-06-20 | 2018-10-17 | 2018-06-20 | 2018-10-17
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ017K | Osborn Street Plaza | 8 | ORIGINAL EQUIP & FURNISHING | 2018-10-18 | 2019-01-15 | 2018-10-18 | 2019-01-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ017K | Osborn Street Plaza | 9 | SUBSTANTIAL COMPLETION | 2019-01-16 | 2019-03-16 | 2019-01-16 | 2019-03-16
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ017K | Osborn Street Plaza | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-03-17 | 2019-04-15 | 2019-03-17 | 2025-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19K1 | Pedestrian Ramp Rehabilitation - Brooklyn | 1 | DEVELOP SCOPE | 2017-06-30 | 2017-09-27 | 2017-06-30 | 2017-09-27
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19K1 | Pedestrian Ramp Rehabilitation - Brooklyn | 2 | PRELIMINARY DESIGN | 2017-09-28 | 2018-01-25 | 2017-09-28 | 2018-01-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19K1 | Pedestrian Ramp Rehabilitation - Brooklyn | 3 | FINAL DESIGN | 2018-01-26 | 2018-07-24 | 2018-01-26 | 2018-07-24
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19K1 | Pedestrian Ramp Rehabilitation - Brooklyn | 4 | BID AWARD AND REGISTER CONTRCT | 2018-07-25 | 2018-10-22 | 2018-07-25 | 2018-10-22
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19K1 | Pedestrian Ramp Rehabilitation - Brooklyn | 5 | CONSTRUCTION TO 25% | 2018-10-23 | 2019-02-19 | 2018-10-23 | 2019-02-19
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19K1 | Pedestrian Ramp Rehabilitation - Brooklyn | 6 | CONSTRUCTION TO 50% | 2019-02-20 | 2019-06-19 | 2019-02-20 | 2019-06-19
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19K1 | Pedestrian Ramp Rehabilitation - Brooklyn | 7 | CONSTRUCTION TO 75% | 2019-06-20 | 2019-10-17 | 2019-06-20 | 2019-10-17
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19K1 | Pedestrian Ramp Rehabilitation - Brooklyn | 8 | ORIGINAL EQUIP & FURNISHING | 2019-10-18 | 2020-01-15 | 2019-10-18 | 2020-01-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19K1 | Pedestrian Ramp Rehabilitation - Brooklyn | 9 | SUBSTANTIAL COMPLETION | 2020-01-16 | 2020-03-15 | 2020-01-16 | 2020-03-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19K1 | Pedestrian Ramp Rehabilitation - Brooklyn | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-03-16 | 2020-04-14 | 2020-03-16 | 2024-01-29
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19K2 | Pedestrian Ramp Rehabilitation - Brooklyn | 1 | DEVELOP SCOPE | 2017-06-30 | 2017-09-27 | 2017-06-30 | 2017-09-27
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19K2 | Pedestrian Ramp Rehabilitation - Brooklyn | 2 | PRELIMINARY DESIGN | 2017-09-28 | 2018-01-25 | 2017-09-28 | 2018-01-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19K2 | Pedestrian Ramp Rehabilitation - Brooklyn | 3 | FINAL DESIGN | 2018-01-26 | 2018-07-24 | 2018-01-26 | 2018-07-24
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19K2 | Pedestrian Ramp Rehabilitation - Brooklyn | 4 | BID AWARD AND REGISTER CONTRCT | 2018-07-25 | 2018-10-22 | 2018-07-25 | 2018-10-22
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19K2 | Pedestrian Ramp Rehabilitation - Brooklyn | 5 | CONSTRUCTION TO 25% | 2018-10-23 | 2019-02-19 | 2018-10-23 | 2019-02-19
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19K2 | Pedestrian Ramp Rehabilitation - Brooklyn | 6 | CONSTRUCTION TO 50% | 2019-02-20 | 2019-06-19 | 2019-02-20 | 2019-06-19
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19K2 | Pedestrian Ramp Rehabilitation - Brooklyn | 7 | CONSTRUCTION TO 75% | 2019-06-20 | 2019-10-17 | 2019-06-20 | 2019-10-17
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19K2 | Pedestrian Ramp Rehabilitation - Brooklyn | 8 | ORIGINAL EQUIP & FURNISHING | 2019-10-18 | 2020-01-15 | 2019-10-18 | 2020-01-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19K2 | Pedestrian Ramp Rehabilitation - Brooklyn | 9 | SUBSTANTIAL COMPLETION | 2020-01-16 | 2020-03-15 | 2020-01-16 | 2020-03-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19K2 | Pedestrian Ramp Rehabilitation - Brooklyn | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-03-16 | 2020-04-14 | 2020-03-16 | 2024-03-06
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19KC | Complex Upgrades Ped Ramp - Brooklyn | 1 | DEVELOP SCOPE | 2019-06-30 | 2019-09-27 | 2019-06-30 | 2019-09-27
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19KC | Complex Upgrades Ped Ramp - Brooklyn | 2 | PRELIMINARY DESIGN | 2019-09-28 | 2020-01-25 | 2019-09-28 | 2020-01-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19KC | Complex Upgrades Ped Ramp - Brooklyn | 3 | FINAL DESIGN | 2020-01-26 | 2020-07-23 | 2020-01-26 | 2020-07-23
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19KC | Complex Upgrades Ped Ramp - Brooklyn | 4 | BID AWARD AND REGISTER CONTRCT | 2020-07-24 | 2020-10-21 | 2020-07-24 | 2020-10-21
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19KC | Complex Upgrades Ped Ramp - Brooklyn | 5 | CONSTRUCTION TO 25% | 2020-10-22 | 2021-02-18 | 2020-10-22 | 2021-02-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19KC | Complex Upgrades Ped Ramp - Brooklyn | 6 | CONSTRUCTION TO 50% | 2021-02-19 | 2021-06-18 | 2021-02-19 | 2021-06-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19KC | Complex Upgrades Ped Ramp - Brooklyn | 7 | CONSTRUCTION TO 75% | 2021-06-19 | 2021-10-16 | 2021-06-19 | 2021-10-16
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19KC | Complex Upgrades Ped Ramp - Brooklyn | 8 | ORIGINAL EQUIP & FURNISHING | 2021-10-17 | 2022-01-14 | 2021-10-17 | 2022-01-14
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19KC | Complex Upgrades Ped Ramp - Brooklyn | 9 | SUBSTANTIAL COMPLETION | 2022-01-15 | 2022-03-15 | 2022-01-15 | 2022-03-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19KC | Complex Upgrades Ped Ramp - Brooklyn | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-16 | 2022-04-14 | 2022-03-16 | 2022-04-14
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20K1 | Pedestrian Ramps Rehabilitation - Brooklyn | 1 | DEVELOP SCOPE | 2019-05-23 | 2019-08-20 | 2019-05-23 | 2019-08-20
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20K1 | Pedestrian Ramps Rehabilitation - Brooklyn | 2 | PRELIMINARY DESIGN | 2019-08-21 | 2019-12-18 | 2019-08-21 | 2019-12-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20K1 | Pedestrian Ramps Rehabilitation - Brooklyn | 3 | FINAL DESIGN | 2019-12-19 | 2020-06-15 | 2019-12-19 | 2020-06-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20K1 | Pedestrian Ramps Rehabilitation - Brooklyn | 4 | BID AWARD AND REGISTER CONTRCT | 2020-06-16 | 2020-09-13 | 2020-06-16 | 2020-09-13
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20K1 | Pedestrian Ramps Rehabilitation - Brooklyn | 5 | CONSTRUCTION TO 25% | 2020-09-14 | 2021-01-11 | 2020-09-14 | 2021-01-11
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20K1 | Pedestrian Ramps Rehabilitation - Brooklyn | 6 | CONSTRUCTION TO 50% | 2021-01-12 | 2021-05-11 | 2021-01-12 | 2021-05-11
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20K1 | Pedestrian Ramps Rehabilitation - Brooklyn | 7 | CONSTRUCTION TO 75% | 2021-05-12 | 2021-09-08 | 2021-05-12 | 2021-09-08
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20K1 | Pedestrian Ramps Rehabilitation - Brooklyn | 8 | ORIGINAL EQUIP & FURNISHING | 2021-09-09 | 2021-12-07 | 2021-09-09 | 2021-12-07
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20K1 | Pedestrian Ramps Rehabilitation - Brooklyn | 9 | SUBSTANTIAL COMPLETION | 2021-12-08 | 2022-02-05 | 2021-12-08 | 2022-02-05
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20K1 | Pedestrian Ramps Rehabilitation - Brooklyn | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-02-06 | 2025-07-06 | 2022-02-06 | 2025-07-06
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20K2 | Pedestrian Ramp Rehabilitation - Brooklyn | 1 | DEVELOP SCOPE | 2019-05-23 | 2019-08-20 | 2019-05-23 | 2019-08-20
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20K2 | Pedestrian Ramp Rehabilitation - Brooklyn | 2 | PRELIMINARY DESIGN | 2019-08-21 | 2019-12-18 | 2019-08-21 | 2019-12-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20K2 | Pedestrian Ramp Rehabilitation - Brooklyn | 3 | FINAL DESIGN | 2019-12-19 | 2020-06-15 | 2019-12-19 | 2020-06-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20K2 | Pedestrian Ramp Rehabilitation - Brooklyn | 4 | BID AWARD AND REGISTER CONTRCT | 2020-06-16 | 2020-09-13 | 2020-06-16 | 2020-09-13
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20K2 | Pedestrian Ramp Rehabilitation - Brooklyn | 5 | CONSTRUCTION TO 25% | 2020-09-14 | 2021-01-11 | 2020-09-14 | 2021-01-11
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20K2 | Pedestrian Ramp Rehabilitation - Brooklyn | 6 | CONSTRUCTION TO 50% | 2021-01-12 | 2021-05-11 | 2021-01-12 | 2021-05-11
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20K2 | Pedestrian Ramp Rehabilitation - Brooklyn | 7 | CONSTRUCTION TO 75% | 2021-05-12 | 2021-09-08 | 2021-05-12 | 2021-09-08
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20K2 | Pedestrian Ramp Rehabilitation - Brooklyn | 8 | ORIGINAL EQUIP & FURNISHING | 2021-09-09 | 2021-12-07 | 2021-09-09 | 2021-12-07
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20K2 | Pedestrian Ramp Rehabilitation - Brooklyn | 9 | SUBSTANTIAL COMPLETION | 2021-12-08 | 2022-02-05 | 2021-12-08 | 2022-02-05
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20K2 | Pedestrian Ramp Rehabilitation - Brooklyn | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-02-06 | 2024-11-04 | 2022-02-06 | 2024-11-04
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20K3 | Pedestrian Ramp Rehabilitation - Brooklyn | 1 | DEVELOP SCOPE | 2019-05-23 | 2019-08-20 | 2019-05-23 | 2019-08-20
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20K3 | Pedestrian Ramp Rehabilitation - Brooklyn | 2 | PRELIMINARY DESIGN | 2019-08-21 | 2019-12-18 | 2019-08-21 | 2019-12-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20K3 | Pedestrian Ramp Rehabilitation - Brooklyn | 3 | FINAL DESIGN | 2019-12-19 | 2020-06-15 | 2019-12-19 | 2020-06-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20K3 | Pedestrian Ramp Rehabilitation - Brooklyn | 4 | BID AWARD AND REGISTER CONTRCT | 2020-06-16 | 2020-09-13 | 2020-06-16 | 2020-09-13
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20K3 | Pedestrian Ramp Rehabilitation - Brooklyn | 5 | CONSTRUCTION TO 25% | 2020-09-14 | 2021-01-11 | 2020-09-14 | 2021-01-11
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20K3 | Pedestrian Ramp Rehabilitation - Brooklyn | 6 | CONSTRUCTION TO 50% | 2021-01-12 | 2021-05-11 | 2021-01-12 | 2021-05-11
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20K3 | Pedestrian Ramp Rehabilitation - Brooklyn | 7 | CONSTRUCTION TO 75% | 2021-05-12 | 2021-09-08 | 2021-05-12 | 2021-09-08
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20K3 | Pedestrian Ramp Rehabilitation - Brooklyn | 8 | ORIGINAL EQUIP & FURNISHING | 2021-09-09 | 2021-12-07 | 2021-09-09 | 2021-12-07
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20K3 | Pedestrian Ramp Rehabilitation - Brooklyn | 9 | SUBSTANTIAL COMPLETION | 2021-12-08 | 2022-02-05 | 2021-12-08 | 2022-02-05
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20K3 | Pedestrian Ramp Rehabilitation - Brooklyn | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-02-06 | 2024-07-04 | 2022-02-06 | 2024-07-04
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20KC | Non-Standard Upgrades Ped Ramp - Brooklyn | 1 | DEVELOP SCOPE | 2019-06-30 | 2019-09-27 | 2019-06-30 | 2019-09-27
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20KC | Non-Standard Upgrades Ped Ramp - Brooklyn | 2 | PRELIMINARY DESIGN | 2019-09-28 | 2020-01-25 | 2019-09-28 | 2020-01-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20KC | Non-Standard Upgrades Ped Ramp - Brooklyn | 3 | FINAL DESIGN | 2020-01-26 | 2020-07-23 | 2020-01-26 | 2020-07-23
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20KC | Non-Standard Upgrades Ped Ramp - Brooklyn | 4 | BID AWARD AND REGISTER CONTRCT | 2020-07-24 | 2020-10-21 | 2020-07-24 | 2020-10-21
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20KC | Non-Standard Upgrades Ped Ramp - Brooklyn | 5 | CONSTRUCTION TO 25% | 2020-10-22 | 2021-02-18 | 2020-10-22 | 2021-02-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20KC | Non-Standard Upgrades Ped Ramp - Brooklyn | 6 | CONSTRUCTION TO 50% | 2021-02-19 | 2021-06-18 | 2021-02-19 | 2021-06-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20KC | Non-Standard Upgrades Ped Ramp - Brooklyn | 7 | CONSTRUCTION TO 75% | 2021-06-19 | 2021-10-16 | 2021-06-19 | 2021-10-16
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20KC | Non-Standard Upgrades Ped Ramp - Brooklyn | 8 | ORIGINAL EQUIP & FURNISHING | 2021-10-17 | 2022-01-14 | 2021-10-17 | 2022-01-14
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20KC | Non-Standard Upgrades Ped Ramp - Brooklyn | 9 | SUBSTANTIAL COMPLETION | 2022-01-15 | 2022-03-15 | 2022-01-15 | 2022-03-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20KC | Non-Standard Upgrades Ped Ramp - Brooklyn | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-16 | 2022-04-14 | 2022-03-16 | 2022-04-14
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21K1 | Rehabilitation of Standard Ped Ramps - Brooklyn | 1 | DEVELOP SCOPE | 2021-06-30 | 2021-09-27 | 2021-06-30 | 2021-09-27
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21K1 | Rehabilitation of Standard Ped Ramps - Brooklyn | 2 | PRELIMINARY DESIGN | 2021-09-28 | 2022-01-25 | 2021-09-28 | 2022-01-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21K1 | Rehabilitation of Standard Ped Ramps - Brooklyn | 3 | FINAL DESIGN | 2022-01-26 | 2022-07-24 | 2022-01-26 | 2022-07-24
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21K1 | Rehabilitation of Standard Ped Ramps - Brooklyn | 4 | BID AWARD AND REGISTER CONTRCT | 2022-07-25 | 2022-10-22 | 2022-07-25 | 2022-10-22
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21K1 | Rehabilitation of Standard Ped Ramps - Brooklyn | 5 | CONSTRUCTION TO 25% | 2022-10-23 | 2023-02-19 | 2022-10-23 | 2023-02-19
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21K1 | Rehabilitation of Standard Ped Ramps - Brooklyn | 6 | CONSTRUCTION TO 50% | 2023-02-20 | 2023-06-19 | 2023-02-20 | 2023-06-19
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21K1 | Rehabilitation of Standard Ped Ramps - Brooklyn | 7 | CONSTRUCTION TO 75% | 2023-06-20 | 2023-10-17 | 2023-06-20 | 2023-10-17
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21K1 | Rehabilitation of Standard Ped Ramps - Brooklyn | 8 | ORIGINAL EQUIP & FURNISHING | 2023-10-18 | 2024-01-15 | 2023-10-18 | 2024-01-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21K1 | Rehabilitation of Standard Ped Ramps - Brooklyn | 9 | SUBSTANTIAL COMPLETION | 2024-01-16 | 2024-03-15 | 2024-01-16 | 2024-03-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21K1 | Rehabilitation of Standard Ped Ramps - Brooklyn | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-03-16 | 2024-04-14 | 2024-03-16 | 2024-04-14
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2007K2 | PRIOR NOTICE SIDEWALKS - BROOKLYN (2)(SIM) | 1 | DEVELOP SCOPE | 2005-12-03 | 2006-03-02 | 2005-12-03 | 2006-03-02
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2007K2 | PRIOR NOTICE SIDEWALKS - BROOKLYN (2)(SIM) | 2 | PRELIMINARY DESIGN | 2006-03-03 | 2006-06-30 | 2006-03-03 | 2006-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2007K2 | PRIOR NOTICE SIDEWALKS - BROOKLYN (2)(SIM) | 3 | FINAL DESIGN | 2006-07-01 | 2006-12-27 | 2006-07-01 | 2006-12-27
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2007K2 | PRIOR NOTICE SIDEWALKS - BROOKLYN (2)(SIM) | 4 | BID AWARD AND REGISTER CONTRCT | 2007-01-19 | 2007-04-25 | 2007-01-19 | 2007-04-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2007K2 | PRIOR NOTICE SIDEWALKS - BROOKLYN (2)(SIM) | 5 | CONSTRUCTION TO 25% | 2007-04-26 | 2007-04-25 | 2007-04-26 | 2007-04-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2007K2 | PRIOR NOTICE SIDEWALKS - BROOKLYN (2)(SIM) | 6 | CONSTRUCTION TO 50% | 2007-04-26 | 2007-04-25 | 2007-04-26 | 2007-04-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2007K2 | PRIOR NOTICE SIDEWALKS - BROOKLYN (2)(SIM) | 7 | CONSTRUCTION TO 75% | 2007-04-26 | 2007-04-25 | 2007-04-26 | 2007-04-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2007K2 | PRIOR NOTICE SIDEWALKS - BROOKLYN (2)(SIM) | 8 | ORIGINAL EQUIP & FURNISHING | 2007-04-26 | 2007-04-25 | 2007-04-26 | 2007-04-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2007K2 | PRIOR NOTICE SIDEWALKS - BROOKLYN (2)(SIM) | 9 | SUBSTANTIAL COMPLETION | 2007-04-26 | 2007-04-25 | 2007-04-26 | 2007-04-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2007K2 | PRIOR NOTICE SIDEWALKS - BROOKLYN (2)(SIM) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2007-04-26 | 2007-05-25 | 2007-04-26 | 2007-05-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2009K | PRIOR NOTICE SIDEWALKS - BROOKLYN(SIM) | 1 | DEVELOP SCOPE | 2007-09-23 | 2007-12-21 | 2008-05-21 | 2008-08-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2009K | PRIOR NOTICE SIDEWALKS - BROOKLYN(SIM) | 2 | PRELIMINARY DESIGN | 2007-12-22 | 2008-04-19 | 2008-08-19 | 2008-12-16
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2009K | PRIOR NOTICE SIDEWALKS - BROOKLYN(SIM) | 3 | FINAL DESIGN | 2008-04-20 | 2008-10-16 | 2008-12-17 | 2009-06-14
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2009K | PRIOR NOTICE SIDEWALKS - BROOKLYN(SIM) | 4 | BID AWARD AND REGISTER CONTRCT | 2008-10-17 | 2009-01-14 | 2009-06-15 | 2009-09-12
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2009K | PRIOR NOTICE SIDEWALKS - BROOKLYN(SIM) | 5 | CONSTRUCTION TO 25% | 2009-01-15 | 2009-05-14 | 2009-09-13 | 2010-01-10
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2009K | PRIOR NOTICE SIDEWALKS - BROOKLYN(SIM) | 6 | CONSTRUCTION TO 50% | 2009-05-15 | 2009-09-11 | 2010-01-11 | 2010-05-10
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2009K | PRIOR NOTICE SIDEWALKS - BROOKLYN(SIM) | 7 | CONSTRUCTION TO 75% | 2009-09-12 | 2010-01-09 | 2010-05-11 | 2010-09-07
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2009K | PRIOR NOTICE SIDEWALKS - BROOKLYN(SIM) | 8 | ORIGINAL EQUIP & FURNISHING | 2010-01-10 | 2010-04-09 | 2010-09-08 | 2010-12-06
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2009K | PRIOR NOTICE SIDEWALKS - BROOKLYN(SIM) | 9 | SUBSTANTIAL COMPLETION | 2010-04-10 | 2010-06-08 | 2010-12-07 | 2011-02-04
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2009K | PRIOR NOTICE SIDEWALKS - BROOKLYN(SIM) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2010-06-09 | 2010-07-08 | 2011-02-05 | 2029-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020K1 | Prior Notice Sidewalks- Brooklyn | 1 | DEVELOP SCOPE | 2019-06-30 | 2019-09-27 | 2019-06-30 | 2019-09-27
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020K1 | Prior Notice Sidewalks- Brooklyn | 2 | PRELIMINARY DESIGN | 2019-09-28 | 2020-01-25 | 2019-09-28 | 2020-01-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020K1 | Prior Notice Sidewalks- Brooklyn | 3 | FINAL DESIGN | 2020-01-26 | 2020-07-23 | 2020-01-26 | 2020-07-23
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020K1 | Prior Notice Sidewalks- Brooklyn | 4 | BID AWARD AND REGISTER CONTRCT | 2020-07-24 | 2020-10-21 | 2020-07-24 | 2020-10-21
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020K1 | Prior Notice Sidewalks- Brooklyn | 5 | CONSTRUCTION TO 25% | 2020-10-22 | 2021-02-18 | 2020-10-22 | 2021-02-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020K1 | Prior Notice Sidewalks- Brooklyn | 6 | CONSTRUCTION TO 50% | 2021-02-19 | 2021-06-18 | 2021-02-19 | 2021-06-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020K1 | Prior Notice Sidewalks- Brooklyn | 7 | CONSTRUCTION TO 75% | 2021-06-19 | 2021-10-16 | 2021-06-19 | 2021-10-16
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020K1 | Prior Notice Sidewalks- Brooklyn | 8 | ORIGINAL EQUIP & FURNISHING | 2021-10-17 | 2022-01-14 | 2021-10-17 | 2022-01-14
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020K1 | Prior Notice Sidewalks- Brooklyn | 9 | SUBSTANTIAL COMPLETION | 2022-01-15 | 2022-03-15 | 2022-01-15 | 2022-03-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020K1 | Prior Notice Sidewalks- Brooklyn | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-16 | 2022-04-14 | 2022-03-16 | 2022-04-14
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020K2 | Prior Notice Sidewalks- Brooklyn | 1 | DEVELOP SCOPE | 2019-06-30 | 2019-09-27 | 2019-06-30 | 2019-09-27
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020K2 | Prior Notice Sidewalks- Brooklyn | 2 | PRELIMINARY DESIGN | 2019-09-28 | 2020-01-25 | 2019-09-28 | 2020-01-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020K2 | Prior Notice Sidewalks- Brooklyn | 3 | FINAL DESIGN | 2020-01-26 | 2020-07-23 | 2020-01-26 | 2020-07-23
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020K2 | Prior Notice Sidewalks- Brooklyn | 4 | BID AWARD AND REGISTER CONTRCT | 2020-07-24 | 2020-10-21 | 2020-07-24 | 2020-10-21
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020K2 | Prior Notice Sidewalks- Brooklyn | 5 | CONSTRUCTION TO 25% | 2020-10-22 | 2021-02-18 | 2020-10-22 | 2021-02-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020K2 | Prior Notice Sidewalks- Brooklyn | 6 | CONSTRUCTION TO 50% | 2021-02-19 | 2021-06-18 | 2021-02-19 | 2021-06-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020K2 | Prior Notice Sidewalks- Brooklyn | 7 | CONSTRUCTION TO 75% | 2021-06-19 | 2021-10-16 | 2021-06-19 | 2021-10-16
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020K2 | Prior Notice Sidewalks- Brooklyn | 8 | ORIGINAL EQUIP & FURNISHING | 2021-10-17 | 2022-01-14 | 2021-10-17 | 2022-01-14
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020K2 | Prior Notice Sidewalks- Brooklyn | 9 | SUBSTANTIAL COMPLETION | 2022-01-15 | 2022-03-15 | 2022-01-15 | 2022-03-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020K2 | Prior Notice Sidewalks- Brooklyn | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-16 | 2022-04-14 | 2022-03-16 | 2022-04-14
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWSRT200E | Safe Routes to Transit: 86th Street | 1 | DEVELOP SCOPE | 2022-06-30 | 2022-09-27 | 2020-06-30 | 2020-09-27
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWSRT200E | Safe Routes to Transit: 86th Street | 2 | PRELIMINARY DESIGN | 2022-09-28 | 2023-01-25 | 2020-09-28 | 2021-01-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWSRT200E | Safe Routes to Transit: 86th Street | 3 | FINAL DESIGN | 2023-01-26 | 2023-07-24 | 2021-01-26 | 2021-07-24
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWSRT200E | Safe Routes to Transit: 86th Street | 4 | BID AWARD AND REGISTER CONTRCT | 2023-07-25 | 2023-10-22 | 2021-07-25 | 2021-10-22
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWSRT200E | Safe Routes to Transit: 86th Street | 5 | CONSTRUCTION TO 25% | 2023-10-23 | 2024-02-19 | 2021-10-23 | 2022-02-19
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWSRT200E | Safe Routes to Transit: 86th Street | 6 | CONSTRUCTION TO 50% | 2024-02-20 | 2024-06-18 | 2022-02-20 | 2022-06-19
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWSRT200E | Safe Routes to Transit: 86th Street | 7 | CONSTRUCTION TO 75% | 2024-06-19 | 2024-10-16 | 2022-06-20 | 2022-10-17
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWSRT200E | Safe Routes to Transit: 86th Street | 8 | ORIGINAL EQUIP & FURNISHING | 2024-10-17 | 2025-01-14 | 2022-10-18 | 2023-01-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWSRT200E | Safe Routes to Transit: 86th Street | 9 | SUBSTANTIAL COMPLETION | 2025-01-15 | 2025-03-15 | 2023-01-16 | 2023-03-16
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWSRT200E | Safe Routes to Transit: 86th Street | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-03-16 | 2025-04-14 | 2023-03-17 | 2023-04-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRK1 | Trench Restoration - Brooklyn | 1 | DEVELOP SCOPE | 2017-03-01 | 2017-05-29 | 2017-03-01 | 2017-05-29
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRK1 | Trench Restoration - Brooklyn | 2 | PRELIMINARY DESIGN | 2017-05-30 | 2017-09-26 | 2017-05-30 | 2017-09-26
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRK1 | Trench Restoration - Brooklyn | 3 | FINAL DESIGN | 2017-09-27 | 2020-04-25 | 2017-09-27 | 2020-04-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRK1 | Trench Restoration - Brooklyn | 4 | BID AWARD AND REGISTER CONTRCT | 2020-04-26 | 2020-07-24 | 2020-04-26 | 2020-07-24
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRK1 | Trench Restoration - Brooklyn | 5 | CONSTRUCTION TO 25% | 2020-07-25 | 2020-11-21 | 2020-07-25 | 2020-11-21
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRK1 | Trench Restoration - Brooklyn | 6 | CONSTRUCTION TO 50% | 2020-11-22 | 2021-03-21 | 2020-11-22 | 2021-03-21
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRK1 | Trench Restoration - Brooklyn | 7 | CONSTRUCTION TO 75% | 2021-03-22 | 2021-07-19 | 2021-03-22 | 2021-07-19
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRK1 | Trench Restoration - Brooklyn | 8 | ORIGINAL EQUIP & FURNISHING | 2021-07-20 | 2021-10-17 | 2021-07-20 | 2021-10-17
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRK1 | Trench Restoration - Brooklyn | 9 | SUBSTANTIAL COMPLETION | 2021-10-18 | 2021-12-16 | 2021-10-18 | 2021-12-16
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRK1 | Trench Restoration - Brooklyn | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-12-17 | 2022-01-15 | 2021-12-17 | 2022-01-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRK883 | Trench Restoration -- Bay Parkway, Brooklyn, SE-883 | 1 | DEVELOP SCOPE | 2020-03-03 | 2020-05-31 | 2020-03-03 | 2020-05-31
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRK883 | Trench Restoration -- Bay Parkway, Brooklyn, SE-883 | 2 | PRELIMINARY DESIGN | 2020-06-01 | 2020-09-28 | 2020-06-01 | 2020-09-28
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRK883 | Trench Restoration -- Bay Parkway, Brooklyn, SE-883 | 3 | FINAL DESIGN | 2020-09-29 | 2021-03-27 | 2020-09-29 | 2021-03-27
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRK883 | Trench Restoration -- Bay Parkway, Brooklyn, SE-883 | 4 | BID AWARD AND REGISTER CONTRCT | 2021-03-28 | 2021-06-25 | 2021-03-28 | 2021-06-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRK883 | Trench Restoration -- Bay Parkway, Brooklyn, SE-883 | 5 | CONSTRUCTION TO 25% | 2021-06-26 | 2021-10-23 | 2021-06-26 | 2021-10-23
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRK883 | Trench Restoration -- Bay Parkway, Brooklyn, SE-883 | 6 | CONSTRUCTION TO 50% | 2021-10-24 | 2022-02-20 | 2021-10-24 | 2022-02-20
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRK883 | Trench Restoration -- Bay Parkway, Brooklyn, SE-883 | 7 | CONSTRUCTION TO 75% | 2022-02-21 | 2022-06-20 | 2022-02-21 | 2022-06-20
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRK883 | Trench Restoration -- Bay Parkway, Brooklyn, SE-883 | 8 | ORIGINAL EQUIP & FURNISHING | 2022-06-21 | 2022-09-18 | 2022-06-21 | 2022-09-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRK883 | Trench Restoration -- Bay Parkway, Brooklyn, SE-883 | 9 | SUBSTANTIAL COMPLETION | 2022-09-19 | 2022-11-17 | 2022-09-19 | 2022-11-17
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRK883 | Trench Restoration -- Bay Parkway, Brooklyn, SE-883 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-11-18 | 2022-12-17 | 2022-11-18 | 2022-12-17
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LB-104KEN | KENSINGTON - Replacement Facility | 1 | PROJECT START | 1997-03-18 | 1997-03-18 | 2005-07-20 | 2005-07-20
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LB-104KEN | KENSINGTON - Replacement Facility | 2 | DESIGN START | 2006-10-22 | 2006-10-23 | 2006-08-10 | 2008-11-03
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LB-104KEN | KENSINGTON - Replacement Facility | 3 | DESIGN COMPLETION | 2006-10-24 | 2007-04-09 | 2008-11-04 | 2009-10-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LB-104KEN | KENSINGTON - Replacement Facility | 4 | CONSTRUCTION START | 2007-04-10 | 2008-02-01 | 2009-10-26 | 2021-06-26
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LB-104KEN | KENSINGTON - Replacement Facility | 5 | CONSTRUCTION COMPLETION | 2008-02-02 | 2009-08-01 | 2021-06-27 | 2027-06-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC10CDHC | CLARENDON HVAC Replacement | 1 | PROJECT START | 2009-11-09 | 2010-10-24 | 2009-11-09 | 2009-11-09
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC10CDHC | CLARENDON HVAC Replacement | 2 | DESIGN START | 2010-10-25 | 2011-08-22 | 2015-10-19 | 2020-01-24
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC10CDHC | CLARENDON HVAC Replacement | 3 | DESIGN COMPLETION | 2011-08-23 | 2011-11-24 | 2020-01-25 | 2020-11-17
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC10CDHC | CLARENDON HVAC Replacement | 4 | CONSTRUCTION START | 2011-11-25 | 2013-06-06 | 2020-11-18 | 2022-04-22
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC10CDHC | CLARENDON HVAC Replacement | 5 | CONSTRUCTION COMPLETION | 2013-06-07 | 2013-06-07 | 2022-04-23 | 2023-04-23
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC12STHC | SARATOGA BOILER AND HVAC REPLACEMENT | 1 | PROJECT START | 2012-02-13 | 2012-02-13 | 2006-01-08 | 2006-01-08
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC12STHC | SARATOGA BOILER AND HVAC REPLACEMENT | 2 | DESIGN START | 2012-02-14 | 2013-03-30 | 2014-09-25 | 2018-04-28
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC12STHC | SARATOGA BOILER AND HVAC REPLACEMENT | 3 | DESIGN COMPLETION | 2013-04-01 | 2014-02-12 | 2018-04-29 | 2020-03-19
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC12STHC | SARATOGA BOILER AND HVAC REPLACEMENT | 4 | CONSTRUCTION START | 2014-02-13 | 2014-10-24 | 2020-03-20 | 2020-11-28
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC12STHC | SARATOGA BOILER AND HVAC REPLACEMENT | 5 | CONSTRUCTION COMPLETION | 2014-10-25 | 2015-08-15 | 2020-11-29 | 2024-09-19
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC13BPRF | BOROUGH PARK INTERIOR AND EXTERIOR REHABILITATION | 1 | PROJECT START | 2013-04-25 | 2014-07-24 | 2013-04-25 | 2014-07-24
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC13BPRF | BOROUGH PARK INTERIOR AND EXTERIOR REHABILITATION | 2 | DESIGN START | 2014-07-25 | 2015-10-19 | 2014-09-10 | 2016-12-19
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC13BPRF | BOROUGH PARK INTERIOR AND EXTERIOR REHABILITATION | 3 | DESIGN COMPLETION | 2015-10-20 | 2016-05-25 | 2016-12-20 | 2017-07-26
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC13BPRF | BOROUGH PARK INTERIOR AND EXTERIOR REHABILITATION | 4 | CONSTRUCTION START | 2016-05-26 | 2017-11-17 | 2017-07-27 | 2025-01-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC13BPRF | BOROUGH PARK INTERIOR AND EXTERIOR REHABILITATION | 5 | CONSTRUCTION COMPLETION | 2017-11-18 | 2017-11-18 | 2025-01-19 | 2025-01-19
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC14CYHC | CYPRESS HILLS HVAC REPLACEMENT | 1 | PROJECT START | 2013-08-29 | 2013-08-29 | 2013-08-29 | 2013-08-29
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC14CYHC | CYPRESS HILLS HVAC REPLACEMENT | 2 | DESIGN START | 2015-03-31 | 2015-11-26 | 2015-06-02 | 2017-07-29
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC14CYHC | CYPRESS HILLS HVAC REPLACEMENT | 3 | DESIGN COMPLETION | 2015-11-27 | 2016-07-20 | 2017-07-30 | 2020-03-23
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC14CYHC | CYPRESS HILLS HVAC REPLACEMENT | 4 | CONSTRUCTION START | 2016-07-21 | 2017-01-31 | 2020-03-24 | 2025-10-04
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC14CYHC | CYPRESS HILLS HVAC REPLACEMENT | 5 | CONSTRUCTION COMPLETION | 2017-02-01 | 2017-02-01 | 2025-10-05 | 2025-10-05
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC14LDRF | LEONARD ROOF REPLACEMENT | 1 | PROJECT START | 2013-08-29 | 2013-08-29 | 2013-08-29 | 2013-08-29
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC14LDRF | LEONARD ROOF REPLACEMENT | 2 | DESIGN START | 2015-01-28 | 2015-11-24 | 2015-03-17 | 2019-05-27
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC14LDRF | LEONARD ROOF REPLACEMENT | 3 | DESIGN COMPLETION | 2015-11-25 | 2016-07-22 | 2019-05-28 | 2020-01-23
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC14LDRF | LEONARD ROOF REPLACEMENT | 4 | CONSTRUCTION START | 2016-07-23 | 2017-04-16 | 2020-01-24 | 2020-10-17
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC14LDRF | LEONARD ROOF REPLACEMENT | 5 | CONSTRUCTION COMPLETION | 2017-04-17 | 2017-04-17 | 2020-10-18 | 2022-09-17
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC15BWHC | Bushwick Heating & Cooling | 1 | PROJECT START | 2014-10-02 | 2014-10-02 | 2014-10-02 | 2014-10-02
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC15BWHC | Bushwick Heating & Cooling | 2 | DESIGN START | 2014-05-20 | 2015-12-24 | 2016-01-03 | 2019-09-19
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC15BWHC | Bushwick Heating & Cooling | 3 | DESIGN COMPLETION | 2015-12-25 | 2016-05-23 | 2019-09-20 | 2020-02-17
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC15BWHC | Bushwick Heating & Cooling | 4 | CONSTRUCTION START | 2016-05-24 | 2016-10-09 | 2020-02-18 | 2020-07-05
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC15BWHC | Bushwick Heating & Cooling | 5 | CONSTRUCTION COMPLETION | 2016-10-10 | 2016-10-10 | 2022-10-21 | 2022-10-21
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC15FLRF | Flatlands Envelope Rehabilitation | 1 | PROJECT START | 2014-12-03 | 2014-12-03 | 2014-12-03 | 2014-12-03
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC15FLRF | Flatlands Envelope Rehabilitation | 2 | DESIGN START | 2015-07-11 | 2015-11-05 | 2015-10-20 | 2021-02-21
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC15FLRF | Flatlands Envelope Rehabilitation | 3 | DESIGN COMPLETION | 2015-11-06 | 2016-03-06 | 2021-02-22 | 2021-06-23
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC15FLRF | Flatlands Envelope Rehabilitation | 4 | CONSTRUCTION START | 2016-03-07 | 2016-10-02 | 2021-06-24 | 2022-01-19
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC15FLRF | Flatlands Envelope Rehabilitation | 5 | CONSTRUCTION COMPLETION | 2016-10-03 | 2016-10-03 | 2022-01-20 | 2022-01-20
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC16MD2F | MIDWOOD 2ND FLOOR RENOVATIONS | 1 | PROJECT START | 2015-10-13 | 2015-10-13 | 2015-10-13 | 2015-10-13
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC16MD2F | MIDWOOD 2ND FLOOR RENOVATIONS | 2 | DESIGN START | 2016-07-15 | 2017-10-11 | 2016-07-15 | 2017-10-12
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC16MD2F | MIDWOOD 2ND FLOOR RENOVATIONS | 3 | DESIGN COMPLETION | 2017-10-12 | 2017-10-12 | 2017-10-13 | 2021-07-05
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC16MD2F | MIDWOOD 2ND FLOOR RENOVATIONS | 4 | CONSTRUCTION START | 2018-09-02 | 2019-08-31 | 2021-07-06 | 2022-12-27
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC16MD2F | MIDWOOD 2ND FLOOR RENOVATIONS | 5 | CONSTRUCTION COMPLETION | 2019-09-01 | 2019-09-01 | 2022-12-28 | 2025-10-22
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC16MPHC | MAPLETON HVAC REPLACEMENT | 1 | PROJECT START | 2015-08-20 | 2015-08-20 | 2015-08-20 | 2015-08-20
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC16MPHC | MAPLETON HVAC REPLACEMENT | 2 | DESIGN START | 2015-12-31 | 2016-05-15 | 2016-04-12 | 2018-10-21
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC16MPHC | MAPLETON HVAC REPLACEMENT | 3 | DESIGN COMPLETION | 2016-05-16 | 2016-05-15 | 2018-10-22 | 2019-07-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC16MPHC | MAPLETON HVAC REPLACEMENT | 4 | CONSTRUCTION START | 2016-10-23 | 2017-04-29 | 2019-07-26 | 2021-02-04
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC16MPHC | MAPLETON HVAC REPLACEMENT | 5 | CONSTRUCTION COMPLETION | 2017-04-30 | 2017-04-30 | 2021-02-05 | 2022-10-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC17CDOP | CLARENDON OUTDOOR PLAZA | 1 | PROJECT START | 2018-10-04 | 2018-10-04 | 2018-10-04 | 2018-10-04
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC17CDOP | CLARENDON OUTDOOR PLAZA | 2 | DESIGN START | 2019-10-04 | 2020-04-06 | 2019-10-04 | 2020-04-06
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC17CDOP | CLARENDON OUTDOOR PLAZA | 3 | DESIGN COMPLETION | 2020-04-07 | 2021-05-10 | 2020-04-07 | 2021-05-10
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC17CDOP | CLARENDON OUTDOOR PLAZA | 4 | CONSTRUCTION START | 2021-05-11 | 2022-02-08 | 2021-05-11 | 2022-02-08
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC17CDOP | CLARENDON OUTDOOR PLAZA | 5 | CONSTRUCTION COMPLETION | 2022-02-09 | 2022-02-09 | 2022-02-09 | 2022-02-09
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC17MPGD | MAPLETON GARDEN RENOVATION | 1 | PROJECT START | 2017-01-13 | 2017-01-13 | 2017-01-13 | 2017-07-04
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC17MPGD | MAPLETON GARDEN RENOVATION | 2 | DESIGN START | 2017-07-05 | 2018-09-14 | 2017-07-05 | 2019-10-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC17MPGD | MAPLETON GARDEN RENOVATION | 3 | DESIGN COMPLETION | 2018-09-15 | 2019-04-14 | 2019-10-19 | 2020-05-22
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC17MPGD | MAPLETON GARDEN RENOVATION | 4 | CONSTRUCTION START | 2019-04-15 | 2020-04-14 | 2021-01-22 | 2022-01-21
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC17MPGD | MAPLETON GARDEN RENOVATION | 5 | CONSTRUCTION COMPLETION | 2020-04-15 | 2020-04-15 | 2022-01-22 | 2023-01-20
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC17MRAD | MARCY AUDITORIUM REHABILITATION | 1 | PROJECT START | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC17MRAD | MARCY AUDITORIUM REHABILITATION | 2 | DESIGN START | 2017-07-11 | 2018-09-27 | 2017-07-11 | 2018-09-27
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC17MRAD | MARCY AUDITORIUM REHABILITATION | 3 | DESIGN COMPLETION | 2018-09-28 | 2019-03-28 | 2018-09-28 | 2019-03-28
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC17MRAD | MARCY AUDITORIUM REHABILITATION | 4 | CONSTRUCTION START | 2019-03-29 | 2019-09-26 | 2019-03-29 | 2019-09-26
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC17MRAD | MARCY AUDITORIUM REHABILITATION | 5 | CONSTRUCTION COMPLETION | 2019-09-27 | 2019-09-27 | 2019-09-27 | 2022-09-27
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC17PCFS | PACIFIC LIFE & FIRE SAFETY | 1 | PROJECT START | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC17PCFS | PACIFIC LIFE & FIRE SAFETY | 2 | DESIGN START | 2018-04-23 | 2018-11-29 | 2018-04-23 | 2021-11-29
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC17PCFS | PACIFIC LIFE & FIRE SAFETY | 3 | DESIGN COMPLETION | 2018-11-30 | 2019-12-30 | 2021-11-30 | 2022-12-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC17PCFS | PACIFIC LIFE & FIRE SAFETY | 4 | CONSTRUCTION START | 2019-12-31 | 2020-07-29 | 2022-12-31 | 2023-07-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC17PCFS | PACIFIC LIFE & FIRE SAFETY | 5 | CONSTRUCTION COMPLETION | 2020-07-30 | 2020-07-30 | 2023-07-31 | 2023-07-31
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBCA06SPK | SUNSET PARK - Partial Interior Renovation | 1 | PROJECT START | 2005-09-26 | 2005-09-26 | 2005-09-26 | 2005-09-26
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBCA06SPK | SUNSET PARK - Partial Interior Renovation | 2 | DESIGN START | 2005-09-27 | 2006-05-03 | 2005-09-27 | 2006-05-03
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBCA06SPK | SUNSET PARK - Partial Interior Renovation | 3 | DESIGN COMPLETION | 2006-05-04 | 2007-02-05 | 2006-05-04 | 2021-07-23
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBCA06SPK | SUNSET PARK - Partial Interior Renovation | 4 | CONSTRUCTION START | 2007-02-06 | 2007-06-03 | 2021-07-24 | 2021-07-23
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBCA06SPK | SUNSET PARK - Partial Interior Renovation | 5 | CONSTRUCTION COMPLETION | 2007-06-04 | 2008-02-28 | 2021-07-24 | 2026-07-22
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBCA07FBH | FLATBUSH - Roof and Boiler Replacement | 1 | PROJECT START | 2007-07-31 | 2007-07-31 | 2007-07-31 | 2007-07-31
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBCA07FBH | FLATBUSH - Roof and Boiler Replacement | 2 | DESIGN START | 2007-08-01 | 2008-02-08 | 2008-09-22 | 2009-04-13
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBCA07FBH | FLATBUSH - Roof and Boiler Replacement | 3 | DESIGN COMPLETION | 2008-02-09 | 2008-04-14 | 2009-04-14 | 2011-10-10
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBCA07FBH | FLATBUSH - Roof and Boiler Replacement | 4 | CONSTRUCTION START | 2008-04-15 | 2008-06-21 | 2011-10-11 | 2019-01-03
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBCA07FBH | FLATBUSH - Roof and Boiler Replacement | 5 | CONSTRUCTION COMPLETION | 2008-06-22 | 2008-11-24 | 2019-01-04 | 2022-09-29
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBK13EFBR | EAST FLATBUSH - BRANCH RENOVATION | 1 | PROJECT START | 2013-07-15 | 2014-08-18 | 2013-07-15 | 2013-07-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBK13EFBR | EAST FLATBUSH - BRANCH RENOVATION | 2 | DESIGN START | 2014-08-19 | 2015-09-25 | 2014-09-15 | 2014-09-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBK13EFBR | EAST FLATBUSH - BRANCH RENOVATION | 3 | DESIGN COMPLETION | 2015-09-26 | 2016-03-16 | 2015-09-16 | 2017-12-22
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBK13EFBR | EAST FLATBUSH - BRANCH RENOVATION | 4 | CONSTRUCTION START | 2016-03-17 | 2018-03-08 | 2017-12-23 | 2018-08-28
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBK13EFBR | EAST FLATBUSH - BRANCH RENOVATION | 5 | CONSTRUCTION COMPLETION | 2018-03-09 | 2018-03-09 | 2018-08-29 | 2022-08-02
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBK14DRRF | DYKER ROOF REPLACEMENT | 2 | DESIGN START | 2014-04-08 | 2014-10-12 | 2014-04-08 | 2014-09-19
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBK14DRRF | DYKER ROOF REPLACEMENT | 3 | DESIGN COMPLETION | 2014-10-13 | 2015-04-21 | 2014-09-20 | 2016-06-20
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBK14DRRF | DYKER ROOF REPLACEMENT | 4 | CONSTRUCTION START | 2015-04-22 | 2015-09-13 | 2016-06-21 | 2018-06-20
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBK14DRRF | DYKER ROOF REPLACEMENT | 5 | CONSTRUCTION COMPLETION | 2015-09-14 | 2015-09-14 | 2018-06-21 | 2021-06-21
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBK15BDHC | BEDFORD HEATING & COOLING REPLACEMENT | 1 | PROJECT START | 2015-01-02 | 2015-01-02 | 2015-01-02 | 2015-01-02
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBK15BDHC | BEDFORD HEATING & COOLING REPLACEMENT | 2 | DESIGN START | 2015-10-19 | 2016-06-30 | 2015-12-14 | 2020-12-27
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBK15BDHC | BEDFORD HEATING & COOLING REPLACEMENT | 3 | DESIGN COMPLETION | 2016-07-01 | 2016-11-25 | 2020-12-28 | 2021-05-24
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBK15BDHC | BEDFORD HEATING & COOLING REPLACEMENT | 4 | CONSTRUCTION START | 2016-11-26 | 2017-05-25 | 2021-05-25 | 2021-11-21
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBK15BDHC | BEDFORD HEATING & COOLING REPLACEMENT | 5 | CONSTRUCTION COMPLETION | 2017-05-26 | 2017-05-26 | 2021-11-22 | 2021-11-22
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBK15BRRF | BAY RIDGE ENVELOPE REHAB | 1 | PROJECT START | 2014-12-30 | 2014-12-30 | 2014-12-30 | 2014-12-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBK15BRRF | BAY RIDGE ENVELOPE REHAB | 2 | DESIGN START | 2015-04-30 | 2016-01-25 | 2015-04-30 | 2015-08-14
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBK15BRRF | BAY RIDGE ENVELOPE REHAB | 3 | DESIGN COMPLETION | 2016-01-26 | 2016-06-30 | 2015-01-14 | 2017-02-28
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBK15BRRF | BAY RIDGE ENVELOPE REHAB | 4 | CONSTRUCTION START | 2016-07-01 | 2016-12-18 | 2017-03-01 | 2019-09-29
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBK15BRRF | BAY RIDGE ENVELOPE REHAB | 5 | CONSTRUCTION COMPLETION | 2016-12-19 | 2016-12-19 | 2019-09-30 | 2022-09-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBK15WTHC | WINDSOR TERRACE HEATING & COOLING REPLACEMENT | 1 | PROJECT START | 2014-11-10 | 2014-11-10 | 2014-11-10 | 2014-11-10
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBK15WTHC | WINDSOR TERRACE HEATING & COOLING REPLACEMENT | 2 | DESIGN START | 2015-06-24 | 2016-02-09 | 2015-12-15 | 2021-03-22
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBK15WTHC | WINDSOR TERRACE HEATING & COOLING REPLACEMENT | 3 | DESIGN COMPLETION | 2016-02-10 | 2016-07-09 | 2021-03-23 | 2021-06-21
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBK15WTHC | WINDSOR TERRACE HEATING & COOLING REPLACEMENT | 4 | CONSTRUCTION START | 2016-07-10 | 2017-05-11 | 2021-06-22 | 2023-02-28
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBK15WTHC | WINDSOR TERRACE HEATING & COOLING REPLACEMENT | 5 | CONSTRUCTION COMPLETION | 2017-05-12 | 2017-05-12 | 2023-03-01 | 2023-03-01
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBK16CIBR | Coney Island - 2nd Floor Renovation | 1 | PROJECT START | 2015-10-13 | 2015-10-13 | 2015-10-13 | 2015-10-13
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBK16CIBR | Coney Island - 2nd Floor Renovation | 2 | DESIGN START | 2016-06-13 | 2017-07-10 | 2016-06-13 | 2021-07-10
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBK16CIBR | Coney Island - 2nd Floor Renovation | 3 | DESIGN COMPLETION | 2018-08-05 | 2018-08-05 | 2021-07-11 | 2022-08-05
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBK16CIBR | Coney Island - 2nd Floor Renovation | 4 | CONSTRUCTION START | 2018-08-06 | 2019-08-18 | 2022-08-06 | 2023-08-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBK16CIBR | Coney Island - 2nd Floor Renovation | 5 | CONSTRUCTION COMPLETION | 2019-08-19 | 2019-08-19 | 2023-08-19 | 2023-08-19
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBK16STRF | SARATOGA ENVELOPE REHABILITATION | 1 | PROJECT START | 2017-09-14 | 2017-09-14 | 2017-09-14 | 2017-09-14
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBK16STRF | SARATOGA ENVELOPE REHABILITATION | 2 | DESIGN START | 2018-11-30 | 2019-11-18 | 2018-11-30 | 2019-11-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBK16STRF | SARATOGA ENVELOPE REHABILITATION | 3 | DESIGN COMPLETION | 2019-11-19 | 2020-05-19 | 2019-11-19 | 2020-05-19
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBK16STRF | SARATOGA ENVELOPE REHABILITATION | 4 | CONSTRUCTION START | 2020-05-20 | 2021-10-19 | 2020-05-20 | 2021-10-19
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBK16STRF | SARATOGA ENVELOPE REHABILITATION | 5 | CONSTRUCTION COMPLETION | 2021-10-20 | 2021-10-20 | 2021-10-20 | 2021-10-20
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBKA05RUG | Rugby - Branch Renovation | 1 | PROJECT START | 2004-10-14 | 2004-10-14 | 2004-10-14 | 2004-10-14
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBKA05RUG | Rugby - Branch Renovation | 2 | DESIGN START | 2004-10-15 | 2005-07-15 | 2005-07-15 | 2015-11-22
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBKA05RUG | Rugby - Branch Renovation | 3 | DESIGN COMPLETION | 2005-07-16 | 2006-11-23 | 2015-11-23 | 2016-08-22
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBKA05RUG | Rugby - Branch Renovation | 4 | CONSTRUCTION START | 2006-11-24 | 2007-04-25 | 2016-08-23 | 2024-06-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBKA05RUG | Rugby - Branch Renovation | 5 | CONSTRUCTION COMPLETION | 2007-04-26 | 2008-01-23 | 2024-06-26 | 2024-06-26
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM08WBRF | WILLIAMSBURG - Roof Replacment | 1 | PROJECT START | 2007-10-31 | 2009-04-09 | 2007-10-31 | 2007-10-31
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM08WBRF | WILLIAMSBURG - Roof Replacment | 2 | DESIGN START | 2009-04-10 | 2009-06-04 | 2009-04-10 | 2009-06-04
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM08WBRF | WILLIAMSBURG - Roof Replacment | 3 | DESIGN COMPLETION | 2009-06-05 | 2011-06-30 | 2009-06-05 | 2012-04-23
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM08WBRF | WILLIAMSBURG - Roof Replacment | 4 | CONSTRUCTION START | 2011-07-01 | 2011-12-03 | 2012-04-24 | 2019-12-27
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM08WBRF | WILLIAMSBURG - Roof Replacment | 5 | CONSTRUCTION COMPLETION | 2011-12-04 | 2012-06-30 | 2019-12-28 | 2023-01-01
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM13CGHC | CARROLL GARDENS HVAC REPLACEMENT | 1 | PROJECT START | 2013-07-02 | 2013-07-02 | 2013-07-02 | 2013-07-02
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM13CGHC | CARROLL GARDENS HVAC REPLACEMENT | 2 | DESIGN START | 2014-07-30 | 2015-04-26 | 2014-10-17 | 2016-09-02
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM13CGHC | CARROLL GARDENS HVAC REPLACEMENT | 3 | DESIGN COMPLETION | 2015-04-27 | 2015-08-24 | 2016-09-03 | 2018-09-12
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM13CGHC | CARROLL GARDENS HVAC REPLACEMENT | 4 | CONSTRUCTION START | 2015-08-25 | 2016-06-03 | 2018-09-13 | 2023-12-20
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM13CGHC | CARROLL GARDENS HVAC REPLACEMENT | 5 | CONSTRUCTION COMPLETION | 2016-06-04 | 2016-06-04 | 2023-12-21 | 2023-12-21
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM13FLHC | FLATLANDS BOILER , HVAC, BMS, FIRE SAFETY REPLACEMENT | 1 | PROJECT START | 2013-07-15 | 2013-07-15 | 2013-07-15 | 2013-07-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM13FLHC | FLATLANDS BOILER , HVAC, BMS, FIRE SAFETY REPLACEMENT | 2 | DESIGN START | 2014-09-09 | 2015-04-07 | 2014-12-22 | 2022-04-28
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM13FLHC | FLATLANDS BOILER , HVAC, BMS, FIRE SAFETY REPLACEMENT | 3 | DESIGN COMPLETION | 2015-04-08 | 2015-12-24 | 2022-04-29 | 2023-01-14
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM13FLHC | FLATLANDS BOILER , HVAC, BMS, FIRE SAFETY REPLACEMENT | 4 | CONSTRUCTION START | 2015-12-25 | 2016-09-03 | 2023-01-15 | 2023-09-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM13FLHC | FLATLANDS BOILER , HVAC, BMS, FIRE SAFETY REPLACEMENT | 5 | CONSTRUCTION COMPLETION | 2016-09-04 | 2016-09-04 | 2023-09-26 | 2023-09-26
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM13LDHC | LEONARD HVAC REPLACEMENT | 1 | PROJECT START | 2013-07-12 | 2013-07-12 | 2013-07-12 | 2013-07-12
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM13LDHC | LEONARD HVAC REPLACEMENT | 2 | DESIGN START | 2014-11-04 | 2015-07-12 | 2015-03-17 | 2017-09-16
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM13LDHC | LEONARD HVAC REPLACEMENT | 3 | DESIGN COMPLETION | 2015-07-13 | 2015-11-10 | 2017-09-17 | 2020-01-31
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM13LDHC | LEONARD HVAC REPLACEMENT | 4 | CONSTRUCTION START | 2015-11-11 | 2016-08-04 | 2020-02-01 | 2021-01-31
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM13LDHC | LEONARD HVAC REPLACEMENT | 5 | CONSTRUCTION COMPLETION | 2016-08-05 | 2016-08-05 | 2021-02-01 | 2023-02-01
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM14BWRF | BUSHWICK ROOF REPLACEMENT | 1 | PROJECT START | 2014-02-14 | 2014-02-14 | 2014-02-14 | 2014-02-14
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM14BWRF | BUSHWICK ROOF REPLACEMENT | 2 | DESIGN START | 2015-03-01 | 2016-02-27 | 2015-10-05 | 2020-01-21
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM14BWRF | BUSHWICK ROOF REPLACEMENT | 3 | DESIGN COMPLETION | 2016-02-28 | 2016-05-02 | 2020-01-22 | 2020-03-26
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM14BWRF | BUSHWICK ROOF REPLACEMENT | 4 | CONSTRUCTION START | 2016-05-03 | 2017-07-11 | 2020-03-27 | 2021-06-04
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM14BWRF | BUSHWICK ROOF REPLACEMENT | 5 | CONSTRUCTION COMPLETION | 2017-07-12 | 2017-07-12 | 2021-06-05 | 2022-06-04
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM14WTRF | WINDSOR TERRACE ROOF REPLACEMENT | 1 | PROJECT START | 2014-03-14 | 2014-03-14 | 2014-03-14 | 2014-03-14
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM14WTRF | WINDSOR TERRACE ROOF REPLACEMENT | 2 | DESIGN START | 2014-06-09 | 2015-05-17 | 2014-06-09 | 2015-05-03
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM14WTRF | WINDSOR TERRACE ROOF REPLACEMENT | 3 | DESIGN COMPLETION | 2015-05-18 | 2015-06-01 | 2015-05-04 | 2016-08-04
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM14WTRF | WINDSOR TERRACE ROOF REPLACEMENT | 4 | CONSTRUCTION START | 2015-06-02 | 2016-01-29 | 2016-08-05 | 2022-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM14WTRF | WINDSOR TERRACE ROOF REPLACEMENT | 5 | CONSTRUCTION COMPLETION | 2016-01-30 | 2016-01-30 | 2022-07-01 | 2022-07-01
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM14WWRF | WALT WHITMAN ROOF REPLACEMENT | 1 | PROJECT START | 2014-03-15 | 2014-03-15 | 2014-03-15 | 2014-03-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM14WWRF | WALT WHITMAN ROOF REPLACEMENT | 2 | DESIGN START | 2015-01-06 | 2015-10-15 | 2015-09-16 | 2017-06-22
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM14WWRF | WALT WHITMAN ROOF REPLACEMENT | 3 | DESIGN COMPLETION | 2014-08-10 | 2015-03-13 | 2017-06-23 | 2018-07-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM14WWRF | WALT WHITMAN ROOF REPLACEMENT | 4 | CONSTRUCTION START | 2015-03-14 | 2016-11-16 | 2018-07-31 | 2020-10-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM14WWRF | WALT WHITMAN ROOF REPLACEMENT | 5 | CONSTRUCTION COMPLETION | 2016-11-17 | 2016-11-17 | 2020-10-26 | 2025-10-24
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM15GBRF | GERRITSEN BEACH ENVELOPE REHAB | 1 | PROJECT START | 2014-12-03 | 2014-12-03 | 2014-12-03 | 2014-12-03
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM15GBRF | GERRITSEN BEACH ENVELOPE REHAB | 2 | DESIGN START | 2015-05-02 | 2015-08-27 | 2016-03-01 | 2022-11-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM15GBRF | GERRITSEN BEACH ENVELOPE REHAB | 3 | DESIGN COMPLETION | 2015-08-28 | 2015-12-27 | 2022-12-01 | 2023-04-01
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM15GBRF | GERRITSEN BEACH ENVELOPE REHAB | 4 | CONSTRUCTION START | 2015-12-28 | 2016-07-24 | 2023-04-02 | 2023-10-28
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM15GBRF | GERRITSEN BEACH ENVELOPE REHAB | 5 | CONSTRUCTION COMPLETION | 2016-07-25 | 2016-07-25 | 2023-10-29 | 2023-10-29
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM15MPRF | Mapleton Envelope Rehabilitation | 1 | PROJECT START | 2014-11-14 | 2014-11-14 | 2014-11-14 | 2014-11-14
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM15MPRF | Mapleton Envelope Rehabilitation | 2 | DESIGN START | 2015-06-24 | 2015-10-22 | 2015-06-24 | 2018-03-16
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM15MPRF | Mapleton Envelope Rehabilitation | 3 | DESIGN COMPLETION | 2015-10-23 | 2016-07-05 | 2018-03-17 | 2020-11-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM15MPRF | Mapleton Envelope Rehabilitation | 4 | CONSTRUCTION START | 2016-07-06 | 2017-07-16 | 2020-12-01 | 2023-04-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM15MPRF | Mapleton Envelope Rehabilitation | 5 | CONSTRUCTION COMPLETION | 2017-07-17 | 2017-07-17 | 2023-05-01 | 2023-05-01
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM15RDHC | Ryder Heating & Cooling | 1 | PROJECT START | 2014-12-04 | 2014-12-04 | 2013-12-04 | 2013-12-04
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM15RDHC | Ryder Heating & Cooling | 2 | DESIGN START | 2014-08-07 | 2016-03-28 | 2015-11-24 | 2020-01-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM15RDHC | Ryder Heating & Cooling | 3 | DESIGN COMPLETION | 2016-03-29 | 2016-07-14 | 2020-01-31 | 2020-05-17
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM15RDHC | Ryder Heating & Cooling | 4 | CONSTRUCTION START | 2016-07-15 | 2017-05-29 | 2020-05-18 | 2021-04-01
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM15RDHC | Ryder Heating & Cooling | 5 | CONSTRUCTION COMPLETION | 2017-05-30 | 2017-05-30 | 2021-04-02 | 2022-04-02
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM15RDRF | Ryder Envelope Rehabilitation | 1 | PROJECT START | 2014-10-16 | 2014-10-16 | 2014-10-16 | 2014-10-16
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM15RDRF | Ryder Envelope Rehabilitation | 2 | DESIGN START | 2016-01-16 | 2016-09-06 | 2015-11-23 | 2019-02-14
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM15RDRF | Ryder Envelope Rehabilitation | 3 | DESIGN COMPLETION | 2016-09-07 | 2017-07-02 | 2019-02-15 | 2019-12-10
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM15RDRF | Ryder Envelope Rehabilitation | 4 | CONSTRUCTION START | 2017-07-03 | 2018-05-17 | 2019-12-11 | 2020-10-24
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM15RDRF | Ryder Envelope Rehabilitation | 5 | CONSTRUCTION COMPLETION | 2018-05-18 | 2018-05-18 | 2020-10-25 | 2023-10-24
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM15WTFS | WINDSOR TERRACE FIRE SAFETY | 1 | PROJECT START | 2008-01-14 | 2008-01-14 | 2008-01-14 | 2008-01-14
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM15WTFS | WINDSOR TERRACE FIRE SAFETY | 2 | DESIGN START | 2008-01-15 | 2008-01-15 | 2015-12-23 | 2016-05-13
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM15WTFS | WINDSOR TERRACE FIRE SAFETY | 3 | DESIGN COMPLETION | 2008-01-16 | 2008-01-16 | 2016-05-14 | 2017-02-27
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM15WTFS | WINDSOR TERRACE FIRE SAFETY | 4 | CONSTRUCTION START | 2008-01-17 | 2008-01-17 | 2017-02-28 | 2019-05-16
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM15WTFS | WINDSOR TERRACE FIRE SAFETY | 5 | CONSTRUCTION COMPLETION | 2008-01-18 | 2008-01-18 | 2019-05-17 | 2019-05-17
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM16GSFC | GRAVESEND FACADE REHAB | 1 | PROJECT START | 2008-01-14 | 2008-01-14 | 2008-01-14 | 2008-01-14
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM16GSFC | GRAVESEND FACADE REHAB | 2 | DESIGN START | 2008-01-15 | 2008-01-15 | 2016-09-30 | 2017-11-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM16GSFC | GRAVESEND FACADE REHAB | 3 | DESIGN COMPLETION | 2008-01-16 | 2008-01-16 | 2017-11-19 | 2020-07-02
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM16GSFC | GRAVESEND FACADE REHAB | 4 | CONSTRUCTION START | 2008-01-17 | 2008-01-17 | 2020-07-03 | 2021-07-01
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM16GSFC | GRAVESEND FACADE REHAB | 5 | CONSTRUCTION COMPLETION | 2008-01-18 | 2008-01-18 | 2021-07-02 | 2024-02-28
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM17ARBR | ARLINGTON BRANCH RENOVATION | 1 | PROJECT START | 2018-01-08 | 2018-01-08 | 2018-01-08 | 2018-01-08
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM17ARBR | ARLINGTON BRANCH RENOVATION | 2 | DESIGN START | 2019-02-01 | 2020-09-28 | 2019-02-01 | 2020-09-28
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM17ARBR | ARLINGTON BRANCH RENOVATION | 3 | DESIGN COMPLETION | 2020-09-29 | 2021-07-16 | 2020-09-29 | 2021-07-16
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM17ARBR | ARLINGTON BRANCH RENOVATION | 4 | CONSTRUCTION START | 2021-07-17 | 2023-07-02 | 2021-07-17 | 2023-07-02
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM17ARBR | ARLINGTON BRANCH RENOVATION | 5 | CONSTRUCTION COMPLETION | 2023-07-03 | 2023-07-03 | 2023-07-03 | 2023-07-03
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM17NUOH | NEW UTRECHT BRANCH OVERHAUL | 1 | PROJECT START | 2017-09-26 | 2017-09-26 | 2017-09-26 | 2017-09-26
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM17NUOH | NEW UTRECHT BRANCH OVERHAUL | 2 | DESIGN START | 2018-07-27 | 2020-06-25 | 2018-07-27 | 2020-06-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM17NUOH | NEW UTRECHT BRANCH OVERHAUL | 3 | DESIGN COMPLETION | 2020-06-26 | 2021-03-18 | 2020-06-26 | 2021-03-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM17NUOH | NEW UTRECHT BRANCH OVERHAUL | 4 | CONSTRUCTION START | 2021-03-19 | 2024-03-14 | 2021-03-19 | 2024-03-14
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM17NUOH | NEW UTRECHT BRANCH OVERHAUL | 5 | CONSTRUCTION COMPLETION | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2024-03-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM18BVOH | BROWNSVILLE BRANCH OVERHAUL | 1 | PROJECT START | 2017-09-22 | 2017-09-22 | 2017-09-22 | 2017-09-22
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM18BVOH | BROWNSVILLE BRANCH OVERHAUL | 2 | DESIGN START | 2018-07-27 | 2020-06-25 | 2018-07-27 | 2020-06-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM18BVOH | BROWNSVILLE BRANCH OVERHAUL | 3 | DESIGN COMPLETION | 2020-06-26 | 2021-03-18 | 2020-06-26 | 2021-03-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM18BVOH | BROWNSVILLE BRANCH OVERHAUL | 4 | CONSTRUCTION START | 2021-03-19 | 2024-03-14 | 2021-03-19 | 2024-03-14
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM18BVOH | BROWNSVILLE BRANCH OVERHAUL | 5 | CONSTRUCTION COMPLETION | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2024-03-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM18EPOH | EASTERN PARKWAY BRANCH OVERHAUL | 1 | PROJECT START | 2017-11-30 | 2017-11-30 | 2017-11-30 | 2017-11-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM18EPOH | EASTERN PARKWAY BRANCH OVERHAUL | 2 | DESIGN START | 2018-07-31 | 2020-11-29 | 2018-07-31 | 2020-11-29
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM18EPOH | EASTERN PARKWAY BRANCH OVERHAUL | 3 | DESIGN COMPLETION | 2020-11-30 | 2021-03-30 | 2020-11-30 | 2021-03-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM18EPOH | EASTERN PARKWAY BRANCH OVERHAUL | 4 | CONSTRUCTION START | 2021-03-31 | 2024-03-30 | 2021-03-31 | 2025-03-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM18EPOH | EASTERN PARKWAY BRANCH OVERHAUL | 5 | CONSTRUCTION COMPLETION | 2024-03-31 | 2024-03-31 | 2025-03-31 | 2025-03-31
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBP18WIBR | WASHINGTON IRVING BRANCH RENOVATION | 1 | PROJECT START | 2018-11-07 | 2018-11-07 | 2018-11-07 | 2018-11-07
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBP18WIBR | WASHINGTON IRVING BRANCH RENOVATION | 2 | DESIGN START | 2019-06-21 | 2021-03-04 | 2019-06-21 | 2021-03-04
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBP18WIBR | WASHINGTON IRVING BRANCH RENOVATION | 3 | DESIGN COMPLETION | 2021-03-05 | 2021-11-25 | 2021-03-05 | 2021-11-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBP18WIBR | WASHINGTON IRVING BRANCH RENOVATION | 4 | CONSTRUCTION START | 2021-11-26 | 2023-11-29 | 2021-11-26 | 2023-11-29
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBP18WIBR | WASHINGTON IRVING BRANCH RENOVATION | 5 | CONSTRUCTION COMPLETION | 2023-11-30 | 2023-11-30 | 2023-11-30 | 2023-11-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBP18WWBR | WALT WHITMAN BRANCH RENOVATION | 1 | PROJECT START | 2018-10-04 | 2018-10-04 | 2018-10-04 | 2018-10-04
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBP18WWBR | WALT WHITMAN BRANCH RENOVATION | 2 | DESIGN START | 2018-09-30 | 2021-01-27 | 2018-09-30 | 2021-01-27
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBP18WWBR | WALT WHITMAN BRANCH RENOVATION | 3 | DESIGN COMPLETION | 2021-01-28 | 2021-09-27 | 2021-01-28 | 2021-09-27
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBP18WWBR | WALT WHITMAN BRANCH RENOVATION | 4 | CONSTRUCTION START | 2021-09-28 | 2022-09-29 | 2021-09-28 | 2022-09-29
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBP18WWBR | WALT WHITMAN BRANCH RENOVATION | 5 | CONSTRUCTION COMPLETION | 2022-09-30 | 2022-09-30 | 2022-09-30 | 2022-09-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | NC-61 | NEWTOWN CREEK NATURE WALK PHASE 2 | 1 | DEVELOP SCOPE | 2010-02-01 | 2010-05-01 | 2010-02-01 | 2010-05-01
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | NC-61 | NEWTOWN CREEK NATURE WALK PHASE 2 | 2 | PRELIMINARY DESIGN | 2010-05-02 | 2011-07-01 | 2010-05-02 | 2011-07-01
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | NC-61 | NEWTOWN CREEK NATURE WALK PHASE 2 | 3 | FINAL DESIGN | 2011-07-02 | 2013-01-01 | 2011-07-02 | 2013-01-01
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | NC-61 | NEWTOWN CREEK NATURE WALK PHASE 2 | 4 | BID AWARD AND REGISTER CONTRCT | 2013-01-02 | 2013-10-01 | 2013-01-02 | 2013-10-01
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | NC-61 | NEWTOWN CREEK NATURE WALK PHASE 2 | 5 | CONSTRUCTION TO 25% | 2013-10-02 | 2014-01-31 | 2013-10-02 | 2014-01-31
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | NC-61 | NEWTOWN CREEK NATURE WALK PHASE 2 | 6 | CONSTRUCTION TO 50% | 2014-02-01 | 2014-06-02 | 2014-02-01 | 2014-06-02
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | NC-61 | NEWTOWN CREEK NATURE WALK PHASE 2 | 7 | CONSTRUCTION TO 75% | 2014-06-03 | 2014-10-02 | 2014-06-03 | 2014-10-02
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | NC-61 | NEWTOWN CREEK NATURE WALK PHASE 2 | 8 | ORIGINAL EQUIP & FURNISHING | 2014-10-03 | 2014-11-01 | 2014-10-03 | 2014-11-01
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | NC-61 | NEWTOWN CREEK NATURE WALK PHASE 2 | 9 | SUBSTANTIAL COMPLETION | 2014-11-02 | 2015-02-01 | 2014-11-02 | 2015-02-01
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | NC-61 | NEWTOWN CREEK NATURE WALK PHASE 2 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-02-02 | 2016-02-01 | 2015-02-02 | 2016-02-01
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | NC-61 | NEWTOWN CREEK NATURE WALK PHASE 2 | 11 | PROJECT START | 2015-02-02 | 2016-02-01 | 2016-02-02 | 2016-02-02
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | NC-61 | NEWTOWN CREEK NATURE WALK PHASE 2 | 12 | DESIGN START | 2015-02-02 | 2016-02-01 | 2016-02-03 | 2016-02-03
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | NC-61 | NEWTOWN CREEK NATURE WALK PHASE 2 | 13 | DESIGN COMPLETION | 2015-02-02 | 2016-02-01 | 2016-02-04 | 2016-02-04
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | NC-61 | NEWTOWN CREEK NATURE WALK PHASE 2 | 14 | CONSTRUCTION START | 2015-02-02 | 2016-02-01 | 2016-02-05 | 2016-02-05
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | NC-61 | NEWTOWN CREEK NATURE WALK PHASE 2 | 15 | CONSTRUCTION COMPLETION | 2015-02-02 | 2016-02-01 | 2016-02-06 | 2022-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | NC-61A | NEWTON CREEK NATURE WALK - PHSE 3 | 1 | PROJECT START | 2011-04-14 | 2011-04-14 | 2011-04-14 | 2011-04-14
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | NC-61A | NEWTON CREEK NATURE WALK - PHSE 3 | 2 | DESIGN START | 2011-04-15 | 2012-09-07 | 2011-04-15 | 2012-09-07
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | NC-61A | NEWTON CREEK NATURE WALK - PHSE 3 | 3 | DESIGN COMPLETION | 2012-09-08 | 2013-04-27 | 2012-09-08 | 2013-04-27
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | NC-61A | NEWTON CREEK NATURE WALK - PHSE 3 | 4 | CONSTRUCTION START | 2013-04-28 | 2015-07-05 | 2013-04-28 | 2015-07-05
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | NC-61A | NEWTON CREEK NATURE WALK - PHSE 3 | 5 | CONSTRUCTION COMPLETION | 2015-07-06 | 2016-12-29 | 2015-07-06 | 2021-08-20
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | NDF-ATLBB | NDF - Atlantic Avenue Broadband Conduit (HWD10105) | 1 | DESIGN | 2016-07-01 | 2016-07-20 | 2016-07-01 | 2016-07-20
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | NDF-ATLBB | NDF - Atlantic Avenue Broadband Conduit (HWD10105) | 2 | BID AWARD AND REGISTER CONTRCT | 2016-07-21 | 2016-08-04 | 2016-07-21 | 2016-08-04
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | NDF-ATLBB | NDF - Atlantic Avenue Broadband Conduit (HWD10105) | 3 | CONSTRUCTION | 2016-08-05 | 2016-09-08 | 2016-08-05 | 2016-09-08
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | NDF-ATLBB | NDF - Atlantic Avenue Broadband Conduit (HWD10105) | 4 | ORIGINAL EQUIP & FURNISHING | 2016-09-09 | 2016-09-18 | 2016-09-09 | 2016-09-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | NDF-ATLBB | NDF - Atlantic Avenue Broadband Conduit (HWD10105) | 5 | SUBSTANTIAL COMPLETION | 2016-09-19 | 2016-10-03 | 2016-09-19 | 2016-10-03
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | NDF-ATLBB | NDF - Atlantic Avenue Broadband Conduit (HWD10105) | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-10-04 | 2016-10-08 | 2016-10-04 | 2022-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | NDF-IBZ | NDF - ENY IBZ Improvements | 1 | DESIGN | 2016-07-01 | 2016-07-20 | 2016-07-01 | 2016-07-20
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | NDF-IBZ | NDF - ENY IBZ Improvements | 2 | BID AWARD AND REGISTER CONTRCT | 2016-07-21 | 2016-08-04 | 2016-07-21 | 2016-08-04
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | NDF-IBZ | NDF - ENY IBZ Improvements | 3 | CONSTRUCTION | 2016-08-05 | 2016-09-08 | 2016-08-05 | 2016-09-08
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | NDF-IBZ | NDF - ENY IBZ Improvements | 4 | ORIGINAL EQUIP & FURNISHING | 2016-09-09 | 2016-09-18 | 2016-09-09 | 2016-09-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | NDF-IBZ | NDF - ENY IBZ Improvements | 5 | SUBSTANTIAL COMPLETION | 2016-09-19 | 2016-10-03 | 2016-09-19 | 2016-10-03
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | NDF-IBZ | NDF - ENY IBZ Improvements | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-10-04 | 2016-10-08 | 2016-10-04 | 2022-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | P-213CNTR | Asser Levy Park Reconstruction | 1 | PROJECT START | 2007-05-15 | 2007-05-15 | 2006-05-15 | 2006-05-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | P-213CNTR | Asser Levy Park Reconstruction | 2 | DESIGN START | 2007-12-12 | 2007-12-13 | 2007-12-12 | 2011-12-28
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | P-213CNTR | Asser Levy Park Reconstruction | 3 | DESIGN COMPLETION | 2007-12-13 | 2009-02-13 | 2011-12-28 | 2011-12-28
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | P-213CNTR | Asser Levy Park Reconstruction | 4 | CONSTRUCTION START | 2009-02-03 | 2009-07-29 | 2010-10-11 | 2012-05-13
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | P-213CNTR | Asser Levy Park Reconstruction | 5 | CONSTRUCTION COMPLETION | 2011-07-20 | 2011-07-20 | 2012-05-13 | 2025-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | P-2CIB1HQ | Coney Island Beach Operations HQ at West 25th Street | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | P-2CIB1HQ | Coney Island Beach Operations HQ at West 25th Street | 2 | DESIGN | 2019-12-28 | 2021-12-26 | 2019-12-28 | 2021-12-26
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | P-2CIB1HQ | Coney Island Beach Operations HQ at West 25th Street | 3 | BID/ REGISTER CONTRACT | 2021-12-27 | 2022-09-22 | 2021-12-27 | 2022-09-22
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | P-2CIB1HQ | Coney Island Beach Operations HQ at West 25th Street | 4 | CONSTRUCTION | 2022-09-23 | 2024-09-21 | 2022-09-23 | 2024-09-21
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | P-2CIB1HQ | Coney Island Beach Operations HQ at West 25th Street | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-09-22 | 2025-09-21 | 2024-09-22 | 2025-09-21
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79-77AX | 77TH PRECINCT ANNEX RENOVATION | 1 | DEVELOP SCOPE | 2013-05-31 | 2013-08-28 | 2013-05-31 | 2013-08-28
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79-77AX | 77TH PRECINCT ANNEX RENOVATION | 2 | PRELIMINARY DESIGN | 2013-08-29 | 2013-12-26 | 2013-08-29 | 2013-12-26
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79-77AX | 77TH PRECINCT ANNEX RENOVATION | 3 | FINAL DESIGN | 2013-12-27 | 2014-06-24 | 2013-12-27 | 2014-06-24
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79-77AX | 77TH PRECINCT ANNEX RENOVATION | 4 | BID AWARD AND REGISTER CONTRCT | 2014-06-25 | 2014-09-22 | 2014-06-25 | 2014-09-22
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79-77AX | 77TH PRECINCT ANNEX RENOVATION | 5 | CONSTRUCTION TO 25% | 2014-09-23 | 2015-01-20 | 2014-09-23 | 2015-01-20
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79-77AX | 77TH PRECINCT ANNEX RENOVATION | 6 | CONSTRUCTION TO 50% | 2015-01-21 | 2015-05-20 | 2015-01-21 | 2015-05-20
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79-77AX | 77TH PRECINCT ANNEX RENOVATION | 7 | CONSTRUCTION TO 75% | 2015-05-21 | 2015-09-17 | 2015-05-21 | 2015-09-17
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79-77AX | 77TH PRECINCT ANNEX RENOVATION | 8 | ORIGINAL EQUIP & FURNISHING | 2015-09-18 | 2015-12-16 | 2015-09-18 | 2015-12-16
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79-77AX | 77TH PRECINCT ANNEX RENOVATION | 9 | SUBSTANTIAL COMPLETION | 2015-12-17 | 2016-02-14 | 2015-12-17 | 2016-02-14
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79-77AX | 77TH PRECINCT ANNEX RENOVATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-02-15 | 2016-03-15 | 2016-02-15 | 2021-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79-77FA | 77TH PRECINCT FIRE ALARM SYSTEM | 1 | PROJECT START | 2018-03-01 | 2018-03-01 | 2018-03-01 | 2018-03-01
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79-77FA | 77TH PRECINCT FIRE ALARM SYSTEM | 2 | DESIGN START | 2018-03-02 | 2018-03-02 | 2018-03-02 | 2019-06-04
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79-77FA | 77TH PRECINCT FIRE ALARM SYSTEM | 3 | DESIGN COMPLETION | 2018-03-03 | 2018-03-03 | 2019-06-05 | 2020-12-20
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79-77FA | 77TH PRECINCT FIRE ALARM SYSTEM | 4 | CONSTRUCTION START | 2018-03-04 | 2018-03-04 | 2020-12-21 | 2021-10-19
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79-77FA | 77TH PRECINCT FIRE ALARM SYSTEM | 5 | CONSTRUCTION COMPLETION | 2018-03-05 | 2018-03-05 | 2021-10-20 | 2023-10-20
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79SHOPR | SERVICE SHOP #6 ROOF RENOVATION | 1 | PROJECT START | 2016-05-23 | 2016-05-23 | 2016-05-23 | 2016-05-23
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79SHOPR | SERVICE SHOP #6 ROOF RENOVATION | 2 | DESIGN START | 2016-05-24 | 2016-05-24 | 2016-05-24 | 2016-05-24
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79SHOPR | SERVICE SHOP #6 ROOF RENOVATION | 3 | DESIGN COMPLETION | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79SHOPR | SERVICE SHOP #6 ROOF RENOVATION | 4 | CONSTRUCTION START | 2016-05-26 | 2016-05-26 | 2016-05-26 | 2016-05-26
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79SHOPR | SERVICE SHOP #6 ROOF RENOVATION | 5 | CONSTRUCTION COMPLETION | 2016-05-27 | 2016-05-27 | 2016-05-27 | 2016-05-27
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79SHOPR | SERVICE SHOP #6 ROOF RENOVATION | 6 | DEVELOP SCOPE | 2016-05-28 | 2016-08-25 | 2016-05-28 | 2016-08-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79SHOPR | SERVICE SHOP #6 ROOF RENOVATION | 7 | PRELIMINARY DESIGN | 2016-08-26 | 2016-12-23 | 2016-08-26 | 2016-12-23
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79SHOPR | SERVICE SHOP #6 ROOF RENOVATION | 8 | FINAL DESIGN | 2016-12-24 | 2017-06-21 | 2016-12-24 | 2017-06-21
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79SHOPR | SERVICE SHOP #6 ROOF RENOVATION | 9 | BID AWARD AND REGISTER CONTRCT | 2017-06-22 | 2017-09-19 | 2017-06-22 | 2017-09-19
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79SHOPR | SERVICE SHOP #6 ROOF RENOVATION | 10 | CONSTRUCTION TO 25% | 2017-09-20 | 2018-01-17 | 2017-09-20 | 2018-01-17
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79SHOPR | SERVICE SHOP #6 ROOF RENOVATION | 11 | CONSTRUCTION TO 50% | 2018-01-18 | 2018-05-17 | 2018-01-18 | 2018-05-17
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79SHOPR | SERVICE SHOP #6 ROOF RENOVATION | 12 | CONSTRUCTION TO 75% | 2018-05-18 | 2018-09-14 | 2018-05-18 | 2018-09-14
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79SHOPR | SERVICE SHOP #6 ROOF RENOVATION | 13 | ORIGINAL EQUIP & FURNISHING | 2018-09-15 | 2018-12-13 | 2018-09-15 | 2018-12-13
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79SHOPR | SERVICE SHOP #6 ROOF RENOVATION | 14 | SUBSTANTIAL COMPLETION | 2018-12-14 | 2019-02-11 | 2018-12-14 | 2019-02-11
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79SHOPR | SERVICE SHOP #6 ROOF RENOVATION | 15 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-02-12 | 2019-03-13 | 2019-02-12 | 2022-10-29
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV235BDEV | BMA - Brooklyn Museum - Building Envelope Renovation | 1 | DEVELOP SCOPE | 2019-10-01 | 2020-04-30 | 2019-10-01 | 2020-04-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV235BDEV | BMA - Brooklyn Museum - Building Envelope Renovation | 2 | PRELIMINARY DESIGN | 2020-05-01 | 2020-08-28 | 2020-05-01 | 2020-08-28
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV235BDEV | BMA - Brooklyn Museum - Building Envelope Renovation | 3 | FINAL DESIGN | 2020-08-29 | 2021-02-24 | 2020-08-29 | 2021-02-24
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV235BDEV | BMA - Brooklyn Museum - Building Envelope Renovation | 4 | BID AWARD AND REGISTER CONTRCT | 2021-02-25 | 2021-05-25 | 2021-02-25 | 2021-05-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV235BDEV | BMA - Brooklyn Museum - Building Envelope Renovation | 5 | CONSTRUCTION TO 25% | 2021-05-26 | 2021-09-22 | 2021-05-26 | 2021-09-22
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV235BDEV | BMA - Brooklyn Museum - Building Envelope Renovation | 6 | CONSTRUCTION TO 50% | 2021-09-23 | 2022-01-20 | 2021-09-23 | 2022-01-20
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV235BDEV | BMA - Brooklyn Museum - Building Envelope Renovation | 7 | CONSTRUCTION TO 75% | 2022-01-21 | 2022-05-20 | 2022-01-21 | 2022-05-20
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV235BDEV | BMA - Brooklyn Museum - Building Envelope Renovation | 8 | ORIGINAL EQUIP & FURNISHING | 2022-05-21 | 2022-08-18 | 2022-05-21 | 2022-08-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV235BDEV | BMA - Brooklyn Museum - Building Envelope Renovation | 9 | SUBSTANTIAL COMPLETION | 2022-08-19 | 2022-10-17 | 2022-08-19 | 2022-10-17
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV235BDEV | BMA - Brooklyn Museum - Building Envelope Renovation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-10-18 | 2022-11-16 | 2022-10-18 | 2022-11-16
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV236SGD2 | BBG - Brooklyn Botanic Garden - South Garden Dev. Phase 2 | 1 | PROJECT START | 2003-05-27 | 2003-05-27 | 2015-06-01 | 2016-06-19
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV236SGD2 | BBG - Brooklyn Botanic Garden - South Garden Dev. Phase 2 | 2 | DESIGN START | 2003-05-28 | 2003-05-28 | 2016-06-20 | 2017-06-20
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV236SGD2 | BBG - Brooklyn Botanic Garden - South Garden Dev. Phase 2 | 3 | DESIGN COMPLETION | 2003-05-29 | 2003-05-29 | 2017-06-21 | 2018-06-27
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV236SGD2 | BBG - Brooklyn Botanic Garden - South Garden Dev. Phase 2 | 4 | CONSTRUCTION START | 2003-05-30 | 2003-05-30 | 2020-06-28 | 2022-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV236SGD2 | BBG - Brooklyn Botanic Garden - South Garden Dev. Phase 2 | 5 | CONSTRUCTION COMPLETION | 2003-05-31 | 2003-05-31 | 2022-07-01 | 2026-07-01
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV262-AUD | Brooklyn Children's Museum Auditorium | 1 | DEVELOP SCOPE | 2012-07-01 | 2012-09-28 | 2012-07-01 | 2012-09-28
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV262-AUD | Brooklyn Children's Museum Auditorium | 2 | PRELIMINARY DESIGN | 2012-09-29 | 2013-01-26 | 2012-09-29 | 2013-01-26
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV262-AUD | Brooklyn Children's Museum Auditorium | 3 | FINAL DESIGN | 2013-01-27 | 2013-07-25 | 2013-01-27 | 2013-07-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV262-AUD | Brooklyn Children's Museum Auditorium | 4 | BID AWARD AND REGISTER CONTRCT | 2013-07-26 | 2013-10-23 | 2013-07-26 | 2013-10-23
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV262-AUD | Brooklyn Children's Museum Auditorium | 5 | CONSTRUCTION TO 25% | 2013-10-24 | 2014-02-20 | 2013-10-24 | 2014-02-20
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV262-AUD | Brooklyn Children's Museum Auditorium | 6 | CONSTRUCTION TO 50% | 2014-02-21 | 2014-06-20 | 2014-02-21 | 2014-06-20
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV262-AUD | Brooklyn Children's Museum Auditorium | 7 | CONSTRUCTION TO 75% | 2014-06-21 | 2014-10-18 | 2014-06-21 | 2014-10-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV262-AUD | Brooklyn Children's Museum Auditorium | 8 | ORIGINAL EQUIP & FURNISHING | 2014-10-19 | 2015-01-16 | 2014-10-19 | 2015-01-16
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV262-AUD | Brooklyn Children's Museum Auditorium | 9 | SUBSTANTIAL COMPLETION | 2015-01-17 | 2015-03-17 | 2015-01-17 | 2015-03-17
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV262-AUD | Brooklyn Children's Museum Auditorium | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-18 | 2015-04-16 | 2017-03-18 | 2017-04-16
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV262-AUD | Brooklyn Children's Museum Auditorium | 11 | PROJECT START | 2015-03-18 | 2015-04-16 | 2017-04-17 | 2017-04-17
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV262-AUD | Brooklyn Children's Museum Auditorium | 12 | DESIGN START | 2015-03-18 | 2015-04-16 | 2017-04-18 | 2017-04-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV262-AUD | Brooklyn Children's Museum Auditorium | 13 | DESIGN COMPLETION | 2015-03-18 | 2015-04-16 | 2017-04-19 | 2017-04-19
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV262-AUD | Brooklyn Children's Museum Auditorium | 14 | CONSTRUCTION START | 2015-03-18 | 2015-04-16 | 2017-04-20 | 2017-04-20
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV262-AUD | Brooklyn Children's Museum Auditorium | 15 | CONSTRUCTION COMPLETION | 2015-03-18 | 2015-04-16 | 2017-04-21 | 2024-04-21
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV262-RTW | BCM - Brooklyn Children's Museum Retaining Wall | 1 | PROJECT START | 2017-07-11 | 2017-07-11 | 2017-07-11 | 2017-07-11
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV262-RTW | BCM - Brooklyn Children's Museum Retaining Wall | 2 | DESIGN START | 2018-01-11 | 2019-02-21 | 2018-01-11 | 2019-02-21
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV262-RTW | BCM - Brooklyn Children's Museum Retaining Wall | 3 | DESIGN COMPLETION | 2019-02-22 | 2019-02-22 | 2019-02-22 | 2019-02-22
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV262-RTW | BCM - Brooklyn Children's Museum Retaining Wall | 4 | CONSTRUCTION START | 2019-02-23 | 2019-02-23 | 2019-02-23 | 2019-02-23
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV262-RTW | BCM - Brooklyn Children's Museum Retaining Wall | 5 | CONSTRUCTION COMPLETION | 2019-02-24 | 2024-07-29 | 2019-02-24 | 2024-07-29
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW322X7 | 345 ADAMS ST. - LL 11 CYCLE 7 FACADE REPAIRS | 1 | DEVELOP SCOPE | 2015-01-01 | 2015-03-31 | 2015-01-01 | 2015-03-31
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW322X7 | 345 ADAMS ST. - LL 11 CYCLE 7 FACADE REPAIRS | 2 | PRELIMINARY DESIGN | 2015-04-01 | 2015-07-29 | 2015-04-01 | 2015-07-29
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW322X7 | 345 ADAMS ST. - LL 11 CYCLE 7 FACADE REPAIRS | 3 | FINAL DESIGN | 2015-07-30 | 2016-01-25 | 2015-07-30 | 2016-01-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW322X7 | 345 ADAMS ST. - LL 11 CYCLE 7 FACADE REPAIRS | 4 | BID AWARD AND REGISTER CONTRCT | 2016-01-26 | 2016-04-24 | 2016-01-26 | 2016-04-24
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW322X7 | 345 ADAMS ST. - LL 11 CYCLE 7 FACADE REPAIRS | 5 | CONSTRUCTION TO 25% | 2016-04-25 | 2016-08-22 | 2016-04-25 | 2016-08-22
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW322X7 | 345 ADAMS ST. - LL 11 CYCLE 7 FACADE REPAIRS | 6 | CONSTRUCTION TO 50% | 2016-08-23 | 2016-12-20 | 2016-08-23 | 2016-12-20
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW322X7 | 345 ADAMS ST. - LL 11 CYCLE 7 FACADE REPAIRS | 7 | CONSTRUCTION TO 75% | 2016-12-21 | 2017-04-19 | 2016-12-21 | 2017-04-19
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW322X7 | 345 ADAMS ST. - LL 11 CYCLE 7 FACADE REPAIRS | 8 | ORIGINAL EQUIP & FURNISHING | 2017-04-20 | 2017-07-18 | 2017-04-20 | 2017-07-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW322X7 | 345 ADAMS ST. - LL 11 CYCLE 7 FACADE REPAIRS | 9 | SUBSTANTIAL COMPLETION | 2017-07-19 | 2017-09-16 | 2017-07-19 | 2017-09-16
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW322X7 | 345 ADAMS ST. - LL 11 CYCLE 7 FACADE REPAIRS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-09-17 | 2017-10-16 | 2017-09-17 | 2018-10-16
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW322X7 | 345 ADAMS ST. - LL 11 CYCLE 7 FACADE REPAIRS | 11 | PROJECT START | 2017-09-17 | 2017-10-16 | 2018-10-17 | 2018-10-17
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW322X7 | 345 ADAMS ST. - LL 11 CYCLE 7 FACADE REPAIRS | 12 | DESIGN START | 2017-09-17 | 2017-10-16 | 2018-10-18 | 2018-10-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW322X7 | 345 ADAMS ST. - LL 11 CYCLE 7 FACADE REPAIRS | 13 | DESIGN COMPLETION | 2017-09-17 | 2017-10-16 | 2018-10-19 | 2018-10-19
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW322X7 | 345 ADAMS ST. - LL 11 CYCLE 7 FACADE REPAIRS | 14 | CONSTRUCTION START | 2017-09-17 | 2017-10-16 | 2018-10-20 | 2018-10-20
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW322X7 | 345 ADAMS ST. - LL 11 CYCLE 7 FACADE REPAIRS | 15 | CONSTRUCTION COMPLETION | 2017-09-17 | 2017-10-16 | 2018-10-21 | 2023-10-21
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77DCA | 245 MESEROLE ST. - DCA TEST STATION REHABILITATION | 1 | DEVELOP SCOPE | 2012-06-14 | 2012-09-11 | 2012-02-22 | 2012-02-22
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77DCA | 245 MESEROLE ST. - DCA TEST STATION REHABILITATION | 2 | PRELIMINARY DESIGN | 2012-09-12 | 2013-01-09 | 2012-02-23 | 2013-11-04
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77DCA | 245 MESEROLE ST. - DCA TEST STATION REHABILITATION | 3 | FINAL DESIGN | 2013-01-10 | 2013-07-08 | 2013-11-05 | 2019-03-13
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77DCA | 245 MESEROLE ST. - DCA TEST STATION REHABILITATION | 4 | BID AWARD AND REGISTER CONTRCT | 2013-07-09 | 2013-10-06 | 2019-03-14 | 2019-11-24
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77DCA | 245 MESEROLE ST. - DCA TEST STATION REHABILITATION | 5 | CONSTRUCTION TO 25% | 2013-10-07 | 2014-02-03 | 2019-11-25 | 2021-04-02
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77DCA | 245 MESEROLE ST. - DCA TEST STATION REHABILITATION | 6 | CONSTRUCTION TO 50% | 2014-02-04 | 2014-06-03 | 2021-04-03 | 2021-07-31
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77DCA | 245 MESEROLE ST. - DCA TEST STATION REHABILITATION | 7 | CONSTRUCTION TO 75% | 2014-06-04 | 2014-10-01 | 2021-08-01 | 2021-11-28
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77DCA | 245 MESEROLE ST. - DCA TEST STATION REHABILITATION | 8 | ORIGINAL EQUIP & FURNISHING | 2014-10-02 | 2014-12-30 | 2021-11-29 | 2022-02-26
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77DCA | 245 MESEROLE ST. - DCA TEST STATION REHABILITATION | 9 | SUBSTANTIAL COMPLETION | 2014-12-31 | 2015-02-28 | 2022-02-27 | 2023-03-26
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77DCA | 245 MESEROLE ST. - DCA TEST STATION REHABILITATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-01 | 2015-03-30 | 2023-03-27 | 2024-03-24
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77DCA | 245 MESEROLE ST. - DCA TEST STATION REHABILITATION | 11 | PROJECT START | 2015-03-01 | 2015-03-30 | 2024-03-25 | 2024-03-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77DCA | 245 MESEROLE ST. - DCA TEST STATION REHABILITATION | 12 | DESIGN START | 2015-03-01 | 2015-03-30 | 2024-03-26 | 2024-03-26
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77DCA | 245 MESEROLE ST. - DCA TEST STATION REHABILITATION | 13 | DESIGN COMPLETION | 2015-03-01 | 2015-03-30 | 2024-03-27 | 2024-03-27
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77DCA | 245 MESEROLE ST. - DCA TEST STATION REHABILITATION | 14 | CONSTRUCTION START | 2015-03-01 | 2015-03-30 | 2024-03-28 | 2024-03-28
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77DCA | 245 MESEROLE ST. - DCA TEST STATION REHABILITATION | 15 | CONSTRUCTION COMPLETION | 2015-03-01 | 2015-03-30 | 2024-03-29 | 2024-03-29
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77DCA2 | 245 MESEROLE ST. - DCA STORM SEWER REHAB | 1 | DEVELOP SCOPE | 2016-06-01 | 2016-08-29 | 2016-06-01 | 2016-08-29
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77DCA2 | 245 MESEROLE ST. - DCA STORM SEWER REHAB | 2 | PRELIMINARY DESIGN | 2016-08-30 | 2016-12-27 | 2016-08-30 | 2016-12-27
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77DCA2 | 245 MESEROLE ST. - DCA STORM SEWER REHAB | 3 | FINAL DESIGN | 2016-12-28 | 2017-06-25 | 2016-12-28 | 2017-06-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77DCA2 | 245 MESEROLE ST. - DCA STORM SEWER REHAB | 4 | BID AWARD AND REGISTER CONTRCT | 2017-06-26 | 2017-09-23 | 2017-06-26 | 2017-09-23
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77DCA2 | 245 MESEROLE ST. - DCA STORM SEWER REHAB | 5 | CONSTRUCTION TO 25% | 2017-09-24 | 2018-01-21 | 2017-09-24 | 2018-01-21
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77DCA2 | 245 MESEROLE ST. - DCA STORM SEWER REHAB | 6 | CONSTRUCTION TO 50% | 2018-01-22 | 2018-05-21 | 2018-01-22 | 2018-05-21
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77DCA2 | 245 MESEROLE ST. - DCA STORM SEWER REHAB | 7 | CONSTRUCTION TO 75% | 2018-05-22 | 2018-09-18 | 2018-05-22 | 2021-09-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77DCA2 | 245 MESEROLE ST. - DCA STORM SEWER REHAB | 8 | ORIGINAL EQUIP & FURNISHING | 2018-09-19 | 2018-12-17 | 2021-09-19 | 2021-12-17
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77DCA2 | 245 MESEROLE ST. - DCA STORM SEWER REHAB | 9 | SUBSTANTIAL COMPLETION | 2018-12-18 | 2019-02-15 | 2021-12-18 | 2022-02-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77DCA2 | 245 MESEROLE ST. - DCA STORM SEWER REHAB | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-02-16 | 2019-03-17 | 2022-02-16 | 2022-03-17
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77GOWAN | GOWANUS CANAL 1 ST TURNING BASIN | 1 | DEVELOP SCOPE | 2016-12-01 | 2017-02-28 | 2014-10-02 | 2015-08-16
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77GOWAN | GOWANUS CANAL 1 ST TURNING BASIN | 2 | PRELIMINARY DESIGN | 2017-03-01 | 2017-06-28 | 2015-08-17 | 2016-01-11
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77GOWAN | GOWANUS CANAL 1 ST TURNING BASIN | 3 | FINAL DESIGN | 2017-06-29 | 2017-12-25 | 2016-01-12 | 2019-08-17
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77GOWAN | GOWANUS CANAL 1 ST TURNING BASIN | 4 | BID AWARD AND REGISTER CONTRCT | 2017-12-26 | 2018-03-25 | 2019-08-18 | 2019-11-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77GOWAN | GOWANUS CANAL 1 ST TURNING BASIN | 5 | CONSTRUCTION TO 25% | 2018-03-26 | 2018-07-23 | 2019-11-16 | 2020-03-14
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77GOWAN | GOWANUS CANAL 1 ST TURNING BASIN | 6 | CONSTRUCTION TO 50% | 2018-07-24 | 2018-11-20 | 2020-03-15 | 2020-07-12
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77GOWAN | GOWANUS CANAL 1 ST TURNING BASIN | 7 | CONSTRUCTION TO 75% | 2018-11-21 | 2019-03-20 | 2020-07-13 | 2020-11-09
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77GOWAN | GOWANUS CANAL 1 ST TURNING BASIN | 8 | ORIGINAL EQUIP & FURNISHING | 2019-03-21 | 2019-06-18 | 2020-11-10 | 2021-02-07
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77GOWAN | GOWANUS CANAL 1 ST TURNING BASIN | 9 | SUBSTANTIAL COMPLETION | 2019-06-19 | 2019-08-17 | 2021-02-08 | 2021-04-08
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77GOWAN | GOWANUS CANAL 1 ST TURNING BASIN | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-08-18 | 2019-09-16 | 2021-04-09 | 2024-09-27
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77OEMS2 | 165 CADMAN PLAZA - CATWALK 3RD FLOOR | 1 | PROJECT START | 2014-01-01 | 2014-01-01 | 2019-01-01 | 2019-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77OEMS2 | 165 CADMAN PLAZA - CATWALK 3RD FLOOR | 2 | DESIGN START | 2015-03-15 | 2015-03-15 | 2019-07-01 | 2020-01-03
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77OEMS2 | 165 CADMAN PLAZA - CATWALK 3RD FLOOR | 3 | DESIGN COMPLETION | 2015-06-30 | 2015-06-30 | 2020-01-04 | 2020-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77OEMS2 | 165 CADMAN PLAZA - CATWALK 3RD FLOOR | 4 | CONSTRUCTION START | 2015-11-01 | 2015-11-01 | 2020-07-01 | 2021-01-03
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77OEMS2 | 165 CADMAN PLAZA - CATWALK 3RD FLOOR | 5 | CONSTRUCTION COMPLETION | 2016-06-15 | 2016-06-15 | 2021-01-04 | 2022-08-31
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PWD308JCI | JCC OF GREATER CONEY ISLAND | 1 | PROJECT START | 2010-07-01 | 2010-07-01 | 2008-09-30 | 2009-09-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PWD308JCI | JCC OF GREATER CONEY ISLAND | 2 | DESIGN START | 2010-07-01 | 2010-07-01 | 2010-09-30 | 2011-09-28
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PWD308JCI | JCC OF GREATER CONEY ISLAND | 3 | DESIGN COMPLETION | 2010-07-01 | 2010-07-01 | 2012-09-29 | 2014-10-01
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PWD308JCI | JCC OF GREATER CONEY ISLAND | 4 | CONSTRUCTION START | 2010-07-01 | 2010-07-01 | 2014-10-02 | 2016-10-01
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PWD308JCI | JCC OF GREATER CONEY ISLAND | 5 | CONSTRUCTION COMPLETION | 2010-07-01 | 2010-07-01 | 2016-10-02 | 2024-10-01
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PWKBEFORD | BEDFORD ATLANTIC ARMORY - NENOVATIONS BEDFORD ATLANTIC ARMOR | 1 | PROJECT START | 2010-05-07 | 2010-05-07 | 2011-05-07 | 2011-05-07
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PWKBEFORD | BEDFORD ATLANTIC ARMORY - NENOVATIONS BEDFORD ATLANTIC ARMOR | 2 | DESIGN START | 2010-10-05 | 2010-10-05 | 2011-05-07 | 2011-05-07
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PWKBEFORD | BEDFORD ATLANTIC ARMORY - NENOVATIONS BEDFORD ATLANTIC ARMOR | 3 | DESIGN COMPLETION | 2011-01-18 | 2011-01-18 | 2013-05-07 | 2015-05-07
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PWKBEFORD | BEDFORD ATLANTIC ARMORY - NENOVATIONS BEDFORD ATLANTIC ARMOR | 4 | CONSTRUCTION START | 2012-06-01 | 2012-06-01 | 2016-07-01 | 2018-07-01
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PWKBEFORD | BEDFORD ATLANTIC ARMORY - NENOVATIONS BEDFORD ATLANTIC ARMOR | 5 | CONSTRUCTION COMPLETION | 2014-05-04 | 2014-05-04 | 2018-07-02 | 2026-08-31
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | REMPIV | Remsen Yard Reconstruction Phase IV | 1 | DEVELOP SCOPE | 2018-06-01 | 2018-08-29 | 2018-06-01 | 2018-08-29
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | REMPIV | Remsen Yard Reconstruction Phase IV | 2 | PRELIMINARY DESIGN | 2018-08-30 | 2018-12-27 | 2018-08-30 | 2018-12-27
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | REMPIV | Remsen Yard Reconstruction Phase IV | 3 | FINAL DESIGN | 2018-12-28 | 2019-06-25 | 2018-12-28 | 2019-06-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | REMPIV | Remsen Yard Reconstruction Phase IV | 4 | BID AWARD AND REGISTER CONTRCT | 2019-06-26 | 2019-09-23 | 2019-06-26 | 2019-09-23
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | REMPIV | Remsen Yard Reconstruction Phase IV | 5 | CONSTRUCTION TO 25% | 2019-09-24 | 2020-01-21 | 2019-09-24 | 2020-01-21
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | REMPIV | Remsen Yard Reconstruction Phase IV | 6 | CONSTRUCTION TO 50% | 2020-01-22 | 2020-05-20 | 2020-01-22 | 2020-05-20
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | REMPIV | Remsen Yard Reconstruction Phase IV | 7 | CONSTRUCTION TO 75% | 2020-05-21 | 2020-09-17 | 2020-05-21 | 2020-09-17
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | REMPIV | Remsen Yard Reconstruction Phase IV | 8 | ORIGINAL EQUIP & FURNISHING | 2020-09-18 | 2020-12-16 | 2020-09-18 | 2020-12-16
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | REMPIV | Remsen Yard Reconstruction Phase IV | 9 | SUBSTANTIAL COMPLETION | 2020-12-17 | 2021-02-14 | 2020-12-17 | 2021-02-14
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | REMPIV | Remsen Yard Reconstruction Phase IV | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-02-15 | 2021-03-16 | 2021-02-15 | 2021-03-16
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-383N | Brooklyn 17/18 HVAC and Roof Replacement | 1 | PROJECT START | 2015-07-01 | 2015-07-01 | 2015-09-22 | 2016-09-06
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-383N | Brooklyn 17/18 HVAC and Roof Replacement | 2 | DESIGN START | 2015-07-02 | 2015-07-02 | 2016-09-10 | 2017-05-11
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-383N | Brooklyn 17/18 HVAC and Roof Replacement | 3 | DESIGN COMPLETION | 2015-07-03 | 2015-07-03 | 2017-05-12 | 2019-09-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-383N | Brooklyn 17/18 HVAC and Roof Replacement | 4 | CONSTRUCTION START | 2015-07-04 | 2015-07-04 | 2019-10-01 | 2020-05-01
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-383N | Brooklyn 17/18 HVAC and Roof Replacement | 5 | CONSTRUCTION COMPLETION | 2015-07-05 | 2017-07-05 | 2020-05-02 | 2022-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-436 | Brooklyn 6 Garage Rehabilitation | 1 | DEVELOP SCOPE | 2015-05-01 | 2016-07-23 | 2015-05-01 | 2015-10-20
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-436 | Brooklyn 6 Garage Rehabilitation | 2 | PRELIMINARY DESIGN | 2016-07-24 | 2017-10-16 | 2015-10-21 | 2016-12-14
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-436 | Brooklyn 6 Garage Rehabilitation | 3 | FINAL DESIGN | 2017-10-17 | 2019-01-09 | 2016-12-15 | 2018-01-22
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-436 | Brooklyn 6 Garage Rehabilitation | 4 | BID AWARD AND REGISTER CONTRCT | 2019-01-10 | 2020-01-09 | 2018-01-23 | 2020-06-01
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-436 | Brooklyn 6 Garage Rehabilitation | 5 | CONSTRUCTION TO 25% | 2020-01-10 | 2021-05-23 | 2020-06-02 | 2020-10-14
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-436 | Brooklyn 6 Garage Rehabilitation | 6 | CONSTRUCTION TO 50% | 2021-05-24 | 2022-10-05 | 2020-10-15 | 2020-12-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-436 | Brooklyn 6 Garage Rehabilitation | 7 | CONSTRUCTION TO 75% | 2022-10-06 | 2024-02-17 | 2020-12-16 | 2021-06-16
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-436 | Brooklyn 6 Garage Rehabilitation | 8 | SUBSTANTIAL COMPLETION | 2024-02-18 | 2025-07-01 | 2021-06-17 | 2022-10-31
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-436 | Brooklyn 6 Garage Rehabilitation | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-07-02 | 2026-11-13 | 2022-11-01 | 2023-09-29
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SAND1048 | BWG - Sunset Park North | 1 | DEVELOP SCOPE | 2019-06-30 | 2019-09-27 | 2019-06-30 | 2019-09-27
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SAND1048 | BWG - Sunset Park North | 2 | PRELIMINARY DESIGN | 2019-09-28 | 2020-01-25 | 2019-09-28 | 2020-01-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SAND1048 | BWG - Sunset Park North | 3 | FINAL DESIGN | 2020-01-26 | 2020-07-23 | 2020-01-26 | 2020-07-23
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SAND1048 | BWG - Sunset Park North | 4 | BID AWARD AND REGISTER CONTRCT | 2020-07-24 | 2020-10-21 | 2020-07-24 | 2020-10-21
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SAND1048 | BWG - Sunset Park North | 5 | CONSTRUCTION TO 25% | 2020-10-22 | 2021-02-18 | 2020-10-22 | 2021-02-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SAND1048 | BWG - Sunset Park North | 6 | CONSTRUCTION TO 50% | 2021-02-19 | 2021-06-18 | 2021-02-19 | 2021-06-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SAND1048 | BWG - Sunset Park North | 7 | CONSTRUCTION TO 75% | 2021-06-19 | 2021-10-16 | 2021-06-19 | 2021-10-16
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SAND1048 | BWG - Sunset Park North | 8 | ORIGINAL EQUIP & FURNISHING | 2021-10-17 | 2022-01-14 | 2021-10-17 | 2022-01-14
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SAND1048 | BWG - Sunset Park North | 9 | SUBSTANTIAL COMPLETION | 2022-01-15 | 2022-03-15 | 2022-01-15 | 2022-03-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SAND1048 | BWG - Sunset Park North | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-16 | 2022-04-14 | 2022-03-16 | 2022-04-14
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBRIGH | SANDY - NEW BRIGHTON COMFORT STATION RECONSTRUCTION | 1 | DEVELOP SCOPE | 2017-11-01 | 2018-01-29 | 2017-11-01 | 2018-01-29
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBRIGH | SANDY - NEW BRIGHTON COMFORT STATION RECONSTRUCTION | 2 | PRELIMINARY DESIGN | 2018-01-30 | 2018-05-29 | 2018-01-30 | 2018-05-29
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBRIGH | SANDY - NEW BRIGHTON COMFORT STATION RECONSTRUCTION | 3 | FINAL DESIGN | 2018-05-30 | 2018-11-25 | 2018-05-30 | 2018-11-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBRIGH | SANDY - NEW BRIGHTON COMFORT STATION RECONSTRUCTION | 4 | BID AWARD AND REGISTER CONTRCT | 2018-11-26 | 2019-02-23 | 2018-11-26 | 2019-02-23
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBRIGH | SANDY - NEW BRIGHTON COMFORT STATION RECONSTRUCTION | 5 | CONSTRUCTION TO 25% | 2019-02-24 | 2019-06-23 | 2019-02-24 | 2019-06-23
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBRIGH | SANDY - NEW BRIGHTON COMFORT STATION RECONSTRUCTION | 6 | CONSTRUCTION TO 50% | 2019-06-24 | 2019-10-21 | 2019-06-24 | 2019-10-21
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBRIGH | SANDY - NEW BRIGHTON COMFORT STATION RECONSTRUCTION | 7 | CONSTRUCTION TO 75% | 2019-10-22 | 2020-02-18 | 2019-10-22 | 2024-02-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBRIGH | SANDY - NEW BRIGHTON COMFORT STATION RECONSTRUCTION | 8 | ORIGINAL EQUIP & FURNISHING | 2020-02-19 | 2020-05-18 | 2024-02-19 | 2024-05-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBRIGH | SANDY - NEW BRIGHTON COMFORT STATION RECONSTRUCTION | 9 | SUBSTANTIAL COMPLETION | 2020-05-19 | 2020-07-17 | 2024-05-19 | 2024-07-17
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBRIGH | SANDY - NEW BRIGHTON COMFORT STATION RECONSTRUCTION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-07-18 | 2020-08-16 | 2024-07-18 | 2025-08-16
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDELEC4 | 60TH PRECINCT ELECTRICAL SYSTEM REPLACEMENT( SANDY) | 1 | PROJECT START | 2012-12-21 | 2012-12-21 | 2012-12-21 | 2012-12-21
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDELEC4 | 60TH PRECINCT ELECTRICAL SYSTEM REPLACEMENT( SANDY) | 2 | DESIGN START | 2012-12-22 | 2012-12-28 | 2012-12-22 | 2012-12-28
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDELEC4 | 60TH PRECINCT ELECTRICAL SYSTEM REPLACEMENT( SANDY) | 3 | DESIGN COMPLETION | 2012-12-29 | 2013-03-29 | 2012-12-29 | 2013-03-29
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDELEC4 | 60TH PRECINCT ELECTRICAL SYSTEM REPLACEMENT( SANDY) | 4 | CONSTRUCTION START | 2013-03-30 | 2014-02-28 | 2013-03-30 | 2014-02-28
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDELEC4 | 60TH PRECINCT ELECTRICAL SYSTEM REPLACEMENT( SANDY) | 5 | CONSTRUCTION COMPLETION | 2014-03-01 | 2014-10-31 | 2014-03-01 | 2021-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDELEC7 | AVIATION ELECTRICAL (SANDY) | 1 | DEVELOP SCOPE | 2013-03-25 | 2013-06-22 | 2013-03-25 | 2013-06-22
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDELEC7 | AVIATION ELECTRICAL (SANDY) | 2 | PRELIMINARY DESIGN | 2013-06-23 | 2013-10-20 | 2013-06-23 | 2013-10-20
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDELEC7 | AVIATION ELECTRICAL (SANDY) | 3 | FINAL DESIGN | 2013-10-21 | 2014-04-18 | 2013-10-21 | 2014-04-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDELEC7 | AVIATION ELECTRICAL (SANDY) | 4 | BID AWARD AND REGISTER CONTRCT | 2014-04-19 | 2014-07-17 | 2014-04-19 | 2014-07-17
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDELEC7 | AVIATION ELECTRICAL (SANDY) | 5 | CONSTRUCTION TO 25% | 2014-07-18 | 2014-11-14 | 2014-07-18 | 2014-11-14
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDELEC7 | AVIATION ELECTRICAL (SANDY) | 6 | CONSTRUCTION TO 50% | 2014-11-15 | 2015-03-14 | 2014-11-15 | 2015-03-14
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDELEC7 | AVIATION ELECTRICAL (SANDY) | 7 | CONSTRUCTION TO 75% | 2015-03-15 | 2015-07-12 | 2015-03-15 | 2015-07-12
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDELEC7 | AVIATION ELECTRICAL (SANDY) | 8 | ORIGINAL EQUIP & FURNISHING | 2015-07-13 | 2015-10-10 | 2015-07-13 | 2015-10-10
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDELEC7 | AVIATION ELECTRICAL (SANDY) | 9 | SUBSTANTIAL COMPLETION | 2015-10-11 | 2015-12-09 | 2015-10-11 | 2015-12-09
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDELEC7 | AVIATION ELECTRICAL (SANDY) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-12-10 | 2016-01-08 | 2015-12-10 | 2021-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDELEC8 | ERIE BASIN TOW POUND ELECTRICAL (SANDY) | 1 | PROJECT START | 2013-11-14 | 2013-11-14 | 2013-11-14 | 2013-11-14
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDELEC8 | ERIE BASIN TOW POUND ELECTRICAL (SANDY) | 2 | DESIGN START | 2013-11-15 | 2014-02-28 | 2013-11-15 | 2013-11-16
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDELEC8 | ERIE BASIN TOW POUND ELECTRICAL (SANDY) | 3 | DESIGN COMPLETION | 2014-03-01 | 2014-06-27 | 2013-11-17 | 2017-03-01
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDELEC8 | ERIE BASIN TOW POUND ELECTRICAL (SANDY) | 4 | CONSTRUCTION START | 2014-06-28 | 2014-09-05 | 2017-03-02 | 2017-05-10
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDELEC8 | ERIE BASIN TOW POUND ELECTRICAL (SANDY) | 5 | CONSTRUCTION COMPLETION | 2014-09-06 | 2015-02-21 | 2017-05-11 | 2022-11-28
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW19 | Reconstruction of Downtown Brooklyn - Hurricane Sandy | 1 | DEVELOP SCOPE | 2016-02-16 | 2016-05-15 | 2016-02-16 | 2018-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW19 | Reconstruction of Downtown Brooklyn - Hurricane Sandy | 2 | PRELIMINARY DESIGN | 2016-05-16 | 2016-09-12 | 2018-07-01 | 2018-12-31
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW19 | Reconstruction of Downtown Brooklyn - Hurricane Sandy | 3 | FINAL DESIGN | 2016-09-13 | 2017-03-11 | 2019-01-01 | 2019-12-31
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW19 | Reconstruction of Downtown Brooklyn - Hurricane Sandy | 4 | BID AWARD AND REGISTER CONTRCT | 2017-03-12 | 2017-06-09 | 2020-01-01 | 2020-12-31
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW19 | Reconstruction of Downtown Brooklyn - Hurricane Sandy | 5 | CONSTRUCTION TO 25% | 2017-06-10 | 2017-10-07 | 2021-01-01 | 2021-04-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW19 | Reconstruction of Downtown Brooklyn - Hurricane Sandy | 6 | CONSTRUCTION TO 50% | 2017-10-08 | 2018-02-04 | 2021-05-01 | 2021-08-28
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW19 | Reconstruction of Downtown Brooklyn - Hurricane Sandy | 7 | CONSTRUCTION TO 75% | 2018-02-05 | 2018-06-04 | 2021-08-29 | 2021-12-26
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW19 | Reconstruction of Downtown Brooklyn - Hurricane Sandy | 8 | ORIGINAL EQUIP & FURNISHING | 2018-06-05 | 2018-09-02 | 2021-12-27 | 2022-03-26
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW19 | Reconstruction of Downtown Brooklyn - Hurricane Sandy | 9 | SUBSTANTIAL COMPLETION | 2018-09-03 | 2018-11-01 | 2022-03-27 | 2022-05-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW19 | Reconstruction of Downtown Brooklyn - Hurricane Sandy | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-11-02 | 2018-12-01 | 2022-05-26 | 2022-06-24
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR03 | Jamaica Bay Greenway - Canarsie Pier Connector | 1 | DEVELOP SCOPE | 2019-06-30 | 2019-09-27 | 2019-06-30 | 2019-09-27
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR03 | Jamaica Bay Greenway - Canarsie Pier Connector | 2 | PRELIMINARY DESIGN | 2019-09-28 | 2020-01-25 | 2019-09-28 | 2020-01-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR03 | Jamaica Bay Greenway - Canarsie Pier Connector | 3 | FINAL DESIGN | 2020-01-26 | 2020-07-23 | 2020-01-26 | 2020-07-23
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR03 | Jamaica Bay Greenway - Canarsie Pier Connector | 4 | BID AWARD AND REGISTER CONTRCT | 2020-07-24 | 2020-10-21 | 2020-07-24 | 2020-10-21
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR03 | Jamaica Bay Greenway - Canarsie Pier Connector | 5 | CONSTRUCTION TO 25% | 2020-10-22 | 2021-02-18 | 2020-10-22 | 2021-02-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR03 | Jamaica Bay Greenway - Canarsie Pier Connector | 6 | CONSTRUCTION TO 50% | 2021-02-19 | 2021-06-18 | 2021-02-19 | 2021-06-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR03 | Jamaica Bay Greenway - Canarsie Pier Connector | 7 | CONSTRUCTION TO 75% | 2021-06-19 | 2021-10-16 | 2021-06-19 | 2021-10-16
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR03 | Jamaica Bay Greenway - Canarsie Pier Connector | 8 | ORIGINAL EQUIP & FURNISHING | 2021-10-17 | 2022-01-14 | 2021-10-17 | 2022-01-14
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR03 | Jamaica Bay Greenway - Canarsie Pier Connector | 9 | SUBSTANTIAL COMPLETION | 2022-01-15 | 2022-03-15 | 2022-01-15 | 2022-03-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR03 | Jamaica Bay Greenway - Canarsie Pier Connector | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-16 | 2022-04-14 | 2022-03-16 | 2022-04-14
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRDHK | Red Hook HMGP | 1 | DESIGN | 2016-07-01 | 2016-07-20 | 2016-07-01 | 2016-07-20
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRDHK | Red Hook HMGP | 2 | BID AWARD AND REGISTER CONTRCT | 2016-07-21 | 2016-08-04 | 2016-07-21 | 2016-08-04
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRDHK | Red Hook HMGP | 3 | CONSTRUCTION | 2016-08-05 | 2016-09-08 | 2016-08-05 | 2016-09-08
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRDHK | Red Hook HMGP | 4 | ORIGINAL EQUIP & FURNISHING | 2016-09-09 | 2016-09-18 | 2016-09-09 | 2016-09-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRDHK | Red Hook HMGP | 5 | SUBSTANTIAL COMPLETION | 2016-09-19 | 2016-10-03 | 2016-09-19 | 2016-10-03
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRDHK | Red Hook HMGP | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-10-04 | 2016-10-08 | 2016-10-04 | 2023-06-20
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-851 | HLSS , STRM, SAN & COMB SWERS & WM IN FRESH CREEK BASIN AREA | 1 | DEVELOP SCOPE | 2014-02-17 | 2014-05-17 | 2012-12-07 | 2014-01-26
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-851 | HLSS , STRM, SAN & COMB SWERS & WM IN FRESH CREEK BASIN AREA | 2 | PRELIMINARY DESIGN | 2014-05-18 | 2014-09-14 | 2014-01-27 | 2014-07-14
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-851 | HLSS , STRM, SAN & COMB SWERS & WM IN FRESH CREEK BASIN AREA | 3 | FINAL DESIGN | 2014-09-15 | 2015-03-13 | 2014-07-15 | 2015-06-23
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-851 | HLSS , STRM, SAN & COMB SWERS & WM IN FRESH CREEK BASIN AREA | 4 | BID AWARD AND REGISTER CONTRCT | 2015-03-14 | 2015-06-11 | 2015-06-24 | 2016-03-27
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-851 | HLSS , STRM, SAN & COMB SWERS & WM IN FRESH CREEK BASIN AREA | 5 | CONSTRUCTION TO 25% | 2015-06-12 | 2016-02-06 | 2016-03-28 | 2016-11-22
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-851 | HLSS , STRM, SAN & COMB SWERS & WM IN FRESH CREEK BASIN AREA | 6 | CONSTRUCTION TO 50% | 2016-02-07 | 2016-10-03 | 2016-11-23 | 2017-07-20
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-851 | HLSS , STRM, SAN & COMB SWERS & WM IN FRESH CREEK BASIN AREA | 7 | CONSTRUCTION TO 75% | 2016-10-04 | 2017-05-31 | 2017-07-21 | 2018-03-17
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-851 | HLSS , STRM, SAN & COMB SWERS & WM IN FRESH CREEK BASIN AREA | 8 | ORIGINAL EQUIP & FURNISHING | 2017-06-01 | 2017-08-29 | 2018-03-18 | 2018-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-851 | HLSS , STRM, SAN & COMB SWERS & WM IN FRESH CREEK BASIN AREA | 9 | SUBSTANTIAL COMPLETION | 2017-08-30 | 2017-10-28 | 2018-07-01 | 2018-08-29
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-851 | HLSS , STRM, SAN & COMB SWERS & WM IN FRESH CREEK BASIN AREA | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-10-29 | 2017-11-27 | 2018-08-30 | 2024-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-853 | HLSS, Strm, San & Comb Swrs, & WM Fresh Creek Basin, Ph 2A | 1 | DEVELOP SCOPE | 2013-04-23 | 2014-01-17 | 2013-04-23 | 2014-01-17
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-853 | HLSS, Strm, San & Comb Swrs, & WM Fresh Creek Basin, Ph 2A | 2 | PRELIMINARY DESIGN | 2014-01-18 | 2015-01-12 | 2014-01-18 | 2015-01-12
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-853 | HLSS, Strm, San & Comb Swrs, & WM Fresh Creek Basin, Ph 2A | 3 | FINAL DESIGN | 2015-01-13 | 2016-07-05 | 2015-01-13 | 2016-07-05
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-853 | HLSS, Strm, San & Comb Swrs, & WM Fresh Creek Basin, Ph 2A | 4 | BID AWARD AND REGISTER CONTRCT | 2016-07-06 | 2017-04-01 | 2016-07-06 | 2017-04-01
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-853 | HLSS, Strm, San & Comb Swrs, & WM Fresh Creek Basin, Ph 2A | 5 | CONSTRUCTION TO 25% | 2017-04-02 | 2018-03-27 | 2017-04-02 | 2018-03-27
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-853 | HLSS, Strm, San & Comb Swrs, & WM Fresh Creek Basin, Ph 2A | 6 | CONSTRUCTION TO 50% | 2018-03-28 | 2019-03-22 | 2018-03-28 | 2019-03-22
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-853 | HLSS, Strm, San & Comb Swrs, & WM Fresh Creek Basin, Ph 2A | 7 | CONSTRUCTION TO 75% | 2019-03-23 | 2020-03-16 | 2019-03-23 | 2020-03-16
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-853 | HLSS, Strm, San & Comb Swrs, & WM Fresh Creek Basin, Ph 2A | 8 | ORIGINAL EQUIP & FURNISHING | 2020-03-17 | 2020-12-11 | 2020-03-17 | 2020-12-11
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-853 | HLSS, Strm, San & Comb Swrs, & WM Fresh Creek Basin, Ph 2A | 9 | SUBSTANTIAL COMPLETION | 2020-12-12 | 2021-06-09 | 2020-12-12 | 2021-06-09
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-853 | HLSS, Strm, San & Comb Swrs, & WM Fresh Creek Basin, Ph 2A | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-06-10 | 2021-09-07 | 2021-06-10 | 2021-09-07
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-855 | HLSS, Strm, San & Comb Swrs, & WM Fresh Creek Basin, Ph 2B | 1 | DEVELOP SCOPE | 2016-03-01 | 2016-05-29 | 2016-03-01 | 2016-05-29
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-855 | HLSS, Strm, San & Comb Swrs, & WM Fresh Creek Basin, Ph 2B | 2 | PRELIMINARY DESIGN | 2016-05-30 | 2016-09-26 | 2016-05-30 | 2016-09-26
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-855 | HLSS, Strm, San & Comb Swrs, & WM Fresh Creek Basin, Ph 2B | 3 | FINAL DESIGN | 2016-09-27 | 2017-03-25 | 2016-09-27 | 2017-03-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-855 | HLSS, Strm, San & Comb Swrs, & WM Fresh Creek Basin, Ph 2B | 4 | BID AWARD AND REGISTER CONTRCT | 2017-03-26 | 2017-06-23 | 2017-03-26 | 2017-06-23
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-855 | HLSS, Strm, San & Comb Swrs, & WM Fresh Creek Basin, Ph 2B | 5 | CONSTRUCTION TO 25% | 2017-06-24 | 2017-10-21 | 2017-06-24 | 2017-10-21
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-855 | HLSS, Strm, San & Comb Swrs, & WM Fresh Creek Basin, Ph 2B | 6 | CONSTRUCTION TO 50% | 2017-10-22 | 2018-02-18 | 2017-10-22 | 2018-02-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-855 | HLSS, Strm, San & Comb Swrs, & WM Fresh Creek Basin, Ph 2B | 7 | CONSTRUCTION TO 75% | 2018-02-19 | 2018-06-18 | 2018-02-19 | 2018-06-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-855 | HLSS, Strm, San & Comb Swrs, & WM Fresh Creek Basin, Ph 2B | 8 | ORIGINAL EQUIP & FURNISHING | 2018-06-19 | 2018-09-16 | 2018-06-19 | 2018-09-16
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-855 | HLSS, Strm, San & Comb Swrs, & WM Fresh Creek Basin, Ph 2B | 9 | SUBSTANTIAL COMPLETION | 2018-09-17 | 2018-11-15 | 2018-09-17 | 2018-11-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-855 | HLSS, Strm, San & Comb Swrs, & WM Fresh Creek Basin, Ph 2B | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-11-16 | 2018-12-15 | 2018-11-16 | 2024-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-856 | HLSS, Strm, San & Comb Swrs, & WM Fresh Creek Basin ,Ph 3A | 1 | DEVELOP SCOPE | 2013-05-21 | 2014-02-14 | 2013-05-21 | 2014-02-14
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-856 | HLSS, Strm, San & Comb Swrs, & WM Fresh Creek Basin ,Ph 3A | 2 | PRELIMINARY DESIGN | 2014-02-15 | 2015-02-09 | 2014-02-15 | 2015-02-09
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-856 | HLSS, Strm, San & Comb Swrs, & WM Fresh Creek Basin ,Ph 3A | 3 | FINAL DESIGN | 2015-02-10 | 2016-08-02 | 2015-02-10 | 2016-08-02
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-856 | HLSS, Strm, San & Comb Swrs, & WM Fresh Creek Basin ,Ph 3A | 4 | BID AWARD AND REGISTER CONTRCT | 2016-08-03 | 2017-04-29 | 2016-08-03 | 2017-04-29
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-856 | HLSS, Strm, San & Comb Swrs, & WM Fresh Creek Basin ,Ph 3A | 5 | CONSTRUCTION TO 25% | 2017-04-30 | 2018-04-24 | 2017-04-30 | 2018-04-24
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-856 | HLSS, Strm, San & Comb Swrs, & WM Fresh Creek Basin ,Ph 3A | 6 | CONSTRUCTION TO 50% | 2018-04-25 | 2019-04-19 | 2018-04-25 | 2019-04-19
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-856 | HLSS, Strm, San & Comb Swrs, & WM Fresh Creek Basin ,Ph 3A | 7 | CONSTRUCTION TO 75% | 2019-04-20 | 2020-04-13 | 2019-04-20 | 2020-04-13
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-856 | HLSS, Strm, San & Comb Swrs, & WM Fresh Creek Basin ,Ph 3A | 8 | ORIGINAL EQUIP & FURNISHING | 2020-04-14 | 2021-01-08 | 2020-04-14 | 2021-01-08
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-856 | HLSS, Strm, San & Comb Swrs, & WM Fresh Creek Basin ,Ph 3A | 9 | SUBSTANTIAL COMPLETION | 2021-01-09 | 2021-07-07 | 2021-01-09 | 2021-07-07
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-856 | HLSS, Strm, San & Comb Swrs, & WM Fresh Creek Basin ,Ph 3A | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-07-08 | 2021-10-05 | 2021-07-08 | 2021-10-05
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-857 | HLSS, Strm, San & Comb Swrs, & WM Fresh Creek Basin ,Ph 3B | 1 | DEVELOP SCOPE | 2018-03-01 | 2018-05-29 | 2018-03-01 | 2018-05-29
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-857 | HLSS, Strm, San & Comb Swrs, & WM Fresh Creek Basin ,Ph 3B | 2 | PRELIMINARY DESIGN | 2018-05-30 | 2018-09-26 | 2018-05-30 | 2018-09-26
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-857 | HLSS, Strm, San & Comb Swrs, & WM Fresh Creek Basin ,Ph 3B | 3 | FINAL DESIGN | 2018-09-27 | 2019-03-25 | 2018-09-27 | 2019-03-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-857 | HLSS, Strm, San & Comb Swrs, & WM Fresh Creek Basin ,Ph 3B | 4 | BID AWARD AND REGISTER CONTRCT | 2019-03-26 | 2019-06-23 | 2019-03-26 | 2019-06-23
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-857 | HLSS, Strm, San & Comb Swrs, & WM Fresh Creek Basin ,Ph 3B | 5 | CONSTRUCTION TO 25% | 2019-06-24 | 2019-10-21 | 2019-06-24 | 2019-10-21
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-857 | HLSS, Strm, San & Comb Swrs, & WM Fresh Creek Basin ,Ph 3B | 6 | CONSTRUCTION TO 50% | 2019-10-22 | 2020-02-18 | 2019-10-22 | 2020-02-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-857 | HLSS, Strm, San & Comb Swrs, & WM Fresh Creek Basin ,Ph 3B | 7 | CONSTRUCTION TO 75% | 2020-02-19 | 2020-06-17 | 2020-02-19 | 2020-06-17
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-857 | HLSS, Strm, San & Comb Swrs, & WM Fresh Creek Basin ,Ph 3B | 8 | ORIGINAL EQUIP & FURNISHING | 2020-06-18 | 2020-09-15 | 2020-06-18 | 2020-09-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-857 | HLSS, Strm, San & Comb Swrs, & WM Fresh Creek Basin ,Ph 3B | 9 | SUBSTANTIAL COMPLETION | 2020-09-16 | 2020-11-14 | 2020-09-16 | 2020-11-14
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-857 | HLSS, Strm, San & Comb Swrs, & WM Fresh Creek Basin ,Ph 3B | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-11-15 | 2020-12-14 | 2020-11-15 | 2027-06-28
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-858 | HLSS Installation, Combined Sewer Replmnt (HWK1048A) | 1 | DEVELOP SCOPE | 2014-02-17 | 2014-05-17 | 2014-02-17 | 2014-05-17
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-858 | HLSS Installation, Combined Sewer Replmnt (HWK1048A) | 2 | PRELIMINARY DESIGN | 2014-05-18 | 2014-09-14 | 2014-05-18 | 2014-09-14
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-858 | HLSS Installation, Combined Sewer Replmnt (HWK1048A) | 3 | FINAL DESIGN | 2014-09-15 | 2015-03-13 | 2014-09-15 | 2015-03-13
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-858 | HLSS Installation, Combined Sewer Replmnt (HWK1048A) | 4 | BID AWARD AND REGISTER CONTRCT | 2015-03-14 | 2015-06-11 | 2015-03-14 | 2015-06-11
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-858 | HLSS Installation, Combined Sewer Replmnt (HWK1048A) | 5 | CONSTRUCTION TO 25% | 2015-06-12 | 2016-02-16 | 2015-06-12 | 2016-02-16
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-858 | HLSS Installation, Combined Sewer Replmnt (HWK1048A) | 6 | CONSTRUCTION TO 50% | 2016-02-17 | 2016-10-23 | 2016-02-17 | 2016-10-23
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-858 | HLSS Installation, Combined Sewer Replmnt (HWK1048A) | 7 | CONSTRUCTION TO 75% | 2016-10-24 | 2017-06-30 | 2016-10-24 | 2017-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-858 | HLSS Installation, Combined Sewer Replmnt (HWK1048A) | 8 | ORIGINAL EQUIP & FURNISHING | 2017-07-01 | 2017-09-28 | 2017-07-01 | 2017-09-28
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-858 | HLSS Installation, Combined Sewer Replmnt (HWK1048A) | 9 | SUBSTANTIAL COMPLETION | 2017-09-29 | 2017-11-27 | 2017-09-29 | 2017-11-27
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-858 | HLSS Installation, Combined Sewer Replmnt (HWK1048A) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-11-28 | 2017-12-27 | 2017-11-28 | 2022-08-26
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002351 | Rehab of Comb swrs &w/m in Wycoff Av bet Cooper &Flushing Av | 1 | DEVELOP SCOPE | 2010-06-30 | 2010-09-27 | 2010-06-30 | 2010-09-27
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002351 | Rehab of Comb swrs &w/m in Wycoff Av bet Cooper &Flushing Av | 2 | PRELIMINARY DESIGN | 2010-09-28 | 2011-01-25 | 2010-09-28 | 2011-01-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002351 | Rehab of Comb swrs &w/m in Wycoff Av bet Cooper &Flushing Av | 3 | FINAL DESIGN | 2011-01-26 | 2011-07-24 | 2011-01-26 | 2011-07-24
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002351 | Rehab of Comb swrs &w/m in Wycoff Av bet Cooper &Flushing Av | 4 | BID AWARD AND REGISTER CONTRCT | 2011-07-25 | 2011-10-22 | 2022-03-26 | 2022-06-23
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002351 | Rehab of Comb swrs &w/m in Wycoff Av bet Cooper &Flushing Av | 5 | CONSTRUCTION TO 25% | 2011-10-23 | 2012-02-19 | 2022-06-24 | 2022-06-23
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002351 | Rehab of Comb swrs &w/m in Wycoff Av bet Cooper &Flushing Av | 6 | CONSTRUCTION TO 50% | 2012-02-20 | 2012-06-18 | 2022-06-24 | 2022-06-23
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002351 | Rehab of Comb swrs &w/m in Wycoff Av bet Cooper &Flushing Av | 7 | CONSTRUCTION TO 75% | 2012-06-19 | 2012-10-16 | 2022-06-24 | 2022-06-23
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002351 | Rehab of Comb swrs &w/m in Wycoff Av bet Cooper &Flushing Av | 8 | ORIGINAL EQUIP & FURNISHING | 2012-10-17 | 2013-01-14 | 2022-06-24 | 2022-06-23
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002351 | Rehab of Comb swrs &w/m in Wycoff Av bet Cooper &Flushing Av | 9 | SUBSTANTIAL COMPLETION | 2013-01-15 | 2013-03-15 | 2022-06-24 | 2022-06-23
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002351 | Rehab of Comb swrs &w/m in Wycoff Av bet Cooper &Flushing Av | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-03-16 | 2013-04-14 | 2024-06-24 | 2024-07-23
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002354 | SAN SWRS-GATEWAY ESTATES - PHASE D (HD-161D/SEK20057) | 1 | DEVELOP SCOPE | 2009-02-27 | 2009-05-27 | 2009-02-27 | 2009-05-27
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002354 | SAN SWRS-GATEWAY ESTATES - PHASE D (HD-161D/SEK20057) | 2 | PRELIMINARY DESIGN | 2009-05-28 | 2009-09-24 | 2009-05-28 | 2012-11-16
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002354 | SAN SWRS-GATEWAY ESTATES - PHASE D (HD-161D/SEK20057) | 3 | FINAL DESIGN | 2009-09-25 | 2010-03-23 | 2012-11-17 | 2013-05-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002354 | SAN SWRS-GATEWAY ESTATES - PHASE D (HD-161D/SEK20057) | 4 | BID AWARD AND REGISTER CONTRCT | 2010-03-24 | 2010-06-21 | 2013-05-16 | 2016-01-05
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002354 | SAN SWRS-GATEWAY ESTATES - PHASE D (HD-161D/SEK20057) | 5 | CONSTRUCTION TO 25% | 2010-06-22 | 2010-10-19 | 2016-01-06 | 2016-05-04
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002354 | SAN SWRS-GATEWAY ESTATES - PHASE D (HD-161D/SEK20057) | 6 | CONSTRUCTION TO 50% | 2010-10-20 | 2011-02-16 | 2016-05-05 | 2016-09-01
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002354 | SAN SWRS-GATEWAY ESTATES - PHASE D (HD-161D/SEK20057) | 7 | CONSTRUCTION TO 75% | 2011-02-17 | 2011-06-16 | 2016-09-02 | 2016-12-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002354 | SAN SWRS-GATEWAY ESTATES - PHASE D (HD-161D/SEK20057) | 8 | ORIGINAL EQUIP & FURNISHING | 2011-06-17 | 2011-09-14 | 2016-12-31 | 2018-12-31
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002354 | SAN SWRS-GATEWAY ESTATES - PHASE D (HD-161D/SEK20057) | 9 | SUBSTANTIAL COMPLETION | 2011-09-15 | 2011-11-13 | 2019-01-01 | 2019-03-01
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002354 | SAN SWRS-GATEWAY ESTATES - PHASE D (HD-161D/SEK20057) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2011-11-14 | 2011-12-13 | 2019-03-02 | 2024-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002376 | COMB SWR REPLCMNT & WM WORK IN PRESIDENT ST | 1 | DEVELOP SCOPE | 2017-03-01 | 2017-05-29 | 2017-03-01 | 2017-05-29
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002376 | COMB SWR REPLCMNT & WM WORK IN PRESIDENT ST | 2 | PRELIMINARY DESIGN | 2017-05-30 | 2017-09-26 | 2017-05-30 | 2017-09-26
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002376 | COMB SWR REPLCMNT & WM WORK IN PRESIDENT ST | 3 | FINAL DESIGN | 2017-09-27 | 2018-03-25 | 2017-09-27 | 2018-03-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002376 | COMB SWR REPLCMNT & WM WORK IN PRESIDENT ST | 4 | BID AWARD AND REGISTER CONTRCT | 2018-03-26 | 2018-06-23 | 2018-03-26 | 2018-06-23
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002376 | COMB SWR REPLCMNT & WM WORK IN PRESIDENT ST | 5 | CONSTRUCTION TO 25% | 2018-06-24 | 2018-10-21 | 2018-06-24 | 2018-10-21
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002376 | COMB SWR REPLCMNT & WM WORK IN PRESIDENT ST | 6 | CONSTRUCTION TO 50% | 2018-10-22 | 2019-02-18 | 2018-10-22 | 2019-02-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002376 | COMB SWR REPLCMNT & WM WORK IN PRESIDENT ST | 7 | CONSTRUCTION TO 75% | 2019-02-19 | 2019-06-18 | 2019-02-19 | 2019-06-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002376 | COMB SWR REPLCMNT & WM WORK IN PRESIDENT ST | 8 | ORIGINAL EQUIP & FURNISHING | 2019-06-19 | 2019-09-16 | 2019-06-19 | 2019-09-16
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002376 | COMB SWR REPLCMNT & WM WORK IN PRESIDENT ST | 9 | SUBSTANTIAL COMPLETION | 2019-09-17 | 2019-11-15 | 2019-09-17 | 2019-11-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002376 | COMB SWR REPLCMNT & WM WORK IN PRESIDENT ST | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-11-16 | 2019-12-15 | 2019-11-16 | 2022-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002377 | Santy sewer & WM replmnt in E 72nd St btwn Ave L & Royce Pl | 1 | DEVELOP SCOPE | 2018-06-01 | 2018-08-29 | 2018-06-01 | 2018-08-29
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002377 | Santy sewer & WM replmnt in E 72nd St btwn Ave L & Royce Pl | 2 | PRELIMINARY DESIGN | 2018-08-30 | 2018-12-27 | 2018-08-30 | 2018-12-27
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002377 | Santy sewer & WM replmnt in E 72nd St btwn Ave L & Royce Pl | 3 | FINAL DESIGN | 2018-12-28 | 2019-06-25 | 2018-12-28 | 2019-06-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002377 | Santy sewer & WM replmnt in E 72nd St btwn Ave L & Royce Pl | 4 | BID AWARD AND REGISTER CONTRCT | 2019-06-26 | 2019-09-23 | 2019-06-26 | 2019-09-23
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002377 | Santy sewer & WM replmnt in E 72nd St btwn Ave L & Royce Pl | 5 | CONSTRUCTION TO 25% | 2019-09-24 | 2020-01-21 | 2019-09-24 | 2020-01-21
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002377 | Santy sewer & WM replmnt in E 72nd St btwn Ave L & Royce Pl | 6 | CONSTRUCTION TO 50% | 2020-01-22 | 2020-05-20 | 2020-01-22 | 2020-05-20
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002377 | Santy sewer & WM replmnt in E 72nd St btwn Ave L & Royce Pl | 7 | CONSTRUCTION TO 75% | 2020-05-21 | 2020-09-17 | 2020-05-21 | 2020-09-17
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002377 | Santy sewer & WM replmnt in E 72nd St btwn Ave L & Royce Pl | 8 | ORIGINAL EQUIP & FURNISHING | 2020-09-18 | 2020-12-16 | 2020-09-18 | 2020-12-16
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002377 | Santy sewer & WM replmnt in E 72nd St btwn Ave L & Royce Pl | 9 | SUBSTANTIAL COMPLETION | 2020-12-17 | 2021-02-14 | 2020-12-17 | 2021-02-14
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002377 | Santy sewer & WM replmnt in E 72nd St btwn Ave L & Royce Pl | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-02-15 | 2021-03-16 | 2021-02-15 | 2026-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002380 | Combined relief sewer & WM replac. at 7ST B/T 3 & 4 AV, BKL | 1 | DEVELOP SCOPE | 2016-10-10 | 2017-01-07 | 2016-10-10 | 2017-01-07
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002380 | Combined relief sewer & WM replac. at 7ST B/T 3 & 4 AV, BKL | 2 | PRELIMINARY DESIGN | 2017-01-08 | 2017-05-07 | 2017-01-08 | 2017-05-07
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002380 | Combined relief sewer & WM replac. at 7ST B/T 3 & 4 AV, BKL | 3 | FINAL DESIGN | 2017-05-08 | 2017-11-03 | 2017-05-08 | 2017-11-03
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002380 | Combined relief sewer & WM replac. at 7ST B/T 3 & 4 AV, BKL | 4 | BID AWARD AND REGISTER CONTRCT | 2017-11-04 | 2018-02-01 | 2017-11-04 | 2018-02-01
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002380 | Combined relief sewer & WM replac. at 7ST B/T 3 & 4 AV, BKL | 5 | CONSTRUCTION TO 25% | 2018-02-02 | 2018-06-01 | 2018-02-02 | 2018-06-01
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002380 | Combined relief sewer & WM replac. at 7ST B/T 3 & 4 AV, BKL | 6 | CONSTRUCTION TO 50% | 2018-06-02 | 2018-09-29 | 2018-06-02 | 2018-09-29
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002380 | Combined relief sewer & WM replac. at 7ST B/T 3 & 4 AV, BKL | 7 | CONSTRUCTION TO 75% | 2018-09-30 | 2019-01-27 | 2018-09-30 | 2019-01-27
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002380 | Combined relief sewer & WM replac. at 7ST B/T 3 & 4 AV, BKL | 8 | ORIGINAL EQUIP & FURNISHING | 2019-01-28 | 2019-04-27 | 2019-01-28 | 2019-04-27
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002380 | Combined relief sewer & WM replac. at 7ST B/T 3 & 4 AV, BKL | 9 | SUBSTANTIAL COMPLETION | 2019-04-28 | 2019-06-26 | 2019-04-28 | 2019-06-26
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002380 | Combined relief sewer & WM replac. at 7ST B/T 3 & 4 AV, BKL | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-06-27 | 2019-07-26 | 2019-06-27 | 2023-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002383 | Combined SE installation & WM replacement in Dean Street | 1 | DEVELOP SCOPE | 2018-08-08 | 2018-11-05 | 2018-08-08 | 2018-11-05
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002383 | Combined SE installation & WM replacement in Dean Street | 2 | PRELIMINARY DESIGN | 2018-11-06 | 2019-03-05 | 2018-11-06 | 2019-03-05
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002383 | Combined SE installation & WM replacement in Dean Street | 3 | FINAL DESIGN | 2019-03-06 | 2019-09-01 | 2019-03-06 | 2019-09-01
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002383 | Combined SE installation & WM replacement in Dean Street | 4 | BID AWARD AND REGISTER CONTRCT | 2019-09-02 | 2019-11-30 | 2019-09-02 | 2019-11-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002383 | Combined SE installation & WM replacement in Dean Street | 5 | CONSTRUCTION TO 25% | 2019-12-01 | 2020-03-29 | 2019-12-01 | 2020-03-29
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002383 | Combined SE installation & WM replacement in Dean Street | 6 | CONSTRUCTION TO 50% | 2020-03-30 | 2020-07-27 | 2020-03-30 | 2020-07-27
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002383 | Combined SE installation & WM replacement in Dean Street | 7 | CONSTRUCTION TO 75% | 2020-07-28 | 2020-11-24 | 2020-07-28 | 2020-11-24
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002383 | Combined SE installation & WM replacement in Dean Street | 8 | ORIGINAL EQUIP & FURNISHING | 2020-11-25 | 2021-02-22 | 2020-11-25 | 2021-02-22
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002383 | Combined SE installation & WM replacement in Dean Street | 9 | SUBSTANTIAL COMPLETION | 2021-02-23 | 2021-04-23 | 2021-02-23 | 2021-04-23
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002383 | Combined SE installation & WM replacement in Dean Street | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-04-24 | 2021-05-23 | 2021-04-24 | 2026-07-16
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002384 | Combined SE rplcmt & dist WM install on Van Sinderen Ave BK | 1 | DEVELOP SCOPE | 2019-12-09 | 2020-03-07 | 2019-12-09 | 2020-03-07
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002384 | Combined SE rplcmt & dist WM install on Van Sinderen Ave BK | 2 | PRELIMINARY DESIGN | 2020-03-08 | 2020-07-05 | 2020-03-08 | 2020-07-05
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002384 | Combined SE rplcmt & dist WM install on Van Sinderen Ave BK | 3 | FINAL DESIGN | 2020-07-06 | 2021-01-01 | 2020-07-06 | 2021-01-01
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002384 | Combined SE rplcmt & dist WM install on Van Sinderen Ave BK | 4 | BID AWARD AND REGISTER CONTRCT | 2021-01-02 | 2021-04-01 | 2021-01-02 | 2021-04-01
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002384 | Combined SE rplcmt & dist WM install on Van Sinderen Ave BK | 5 | CONSTRUCTION TO 25% | 2021-04-02 | 2021-07-30 | 2021-04-02 | 2021-07-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002384 | Combined SE rplcmt & dist WM install on Van Sinderen Ave BK | 6 | CONSTRUCTION TO 50% | 2021-07-31 | 2021-11-27 | 2021-07-31 | 2021-11-27
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002384 | Combined SE rplcmt & dist WM install on Van Sinderen Ave BK | 7 | CONSTRUCTION TO 75% | 2021-11-28 | 2022-03-27 | 2021-11-28 | 2022-03-27
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002384 | Combined SE rplcmt & dist WM install on Van Sinderen Ave BK | 8 | ORIGINAL EQUIP & FURNISHING | 2022-03-28 | 2022-06-25 | 2022-03-28 | 2022-06-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002384 | Combined SE rplcmt & dist WM install on Van Sinderen Ave BK | 9 | SUBSTANTIAL COMPLETION | 2022-06-26 | 2022-08-24 | 2022-06-26 | 2022-08-24
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002384 | Combined SE rplcmt & dist WM install on Van Sinderen Ave BK | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-08-25 | 2022-09-23 | 2022-08-25 | 2022-09-23
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002386 | Replace combined sewer & WM work,Park Pl & Underhill Ave, BK | 1 | DEVELOP SCOPE | 2017-03-01 | 2017-05-29 | 2017-03-01 | 2017-05-29
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002386 | Replace combined sewer & WM work,Park Pl & Underhill Ave, BK | 2 | PRELIMINARY DESIGN | 2017-05-30 | 2017-09-26 | 2017-05-30 | 2017-09-26
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002386 | Replace combined sewer & WM work,Park Pl & Underhill Ave, BK | 3 | FINAL DESIGN | 2017-09-27 | 2018-03-25 | 2017-09-27 | 2018-03-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002386 | Replace combined sewer & WM work,Park Pl & Underhill Ave, BK | 4 | BID AWARD AND REGISTER CONTRCT | 2018-03-26 | 2018-06-23 | 2018-03-26 | 2018-06-23
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002386 | Replace combined sewer & WM work,Park Pl & Underhill Ave, BK | 5 | CONSTRUCTION TO 25% | 2018-06-24 | 2018-10-21 | 2018-06-24 | 2018-10-21
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002386 | Replace combined sewer & WM work,Park Pl & Underhill Ave, BK | 6 | CONSTRUCTION TO 50% | 2018-10-22 | 2019-02-18 | 2018-10-22 | 2019-02-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002386 | Replace combined sewer & WM work,Park Pl & Underhill Ave, BK | 7 | CONSTRUCTION TO 75% | 2019-02-19 | 2019-06-18 | 2019-02-19 | 2019-06-18
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002386 | Replace combined sewer & WM work,Park Pl & Underhill Ave, BK | 8 | ORIGINAL EQUIP & FURNISHING | 2019-06-19 | 2019-09-16 | 2019-06-19 | 2019-09-16
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002386 | Replace combined sewer & WM work,Park Pl & Underhill Ave, BK | 9 | SUBSTANTIAL COMPLETION | 2019-09-17 | 2019-11-15 | 2019-09-17 | 2019-11-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002386 | Replace combined sewer & WM work,Park Pl & Underhill Ave, BK | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-11-16 | 2019-12-15 | 2019-11-16 | 2023-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20056 | STORM SEWERS-GATEWAY ESTATES - PHASE C (HD-161C) | 1 | DEVELOP SCOPE | 2006-03-15 | 2006-06-12 | 2006-03-15 | 2006-06-12
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20056 | STORM SEWERS-GATEWAY ESTATES - PHASE C (HD-161C) | 2 | PRELIMINARY DESIGN | 2006-06-13 | 2006-10-10 | 2006-06-13 | 2006-10-10
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20056 | STORM SEWERS-GATEWAY ESTATES - PHASE C (HD-161C) | 3 | FINAL DESIGN | 2006-10-11 | 2007-04-08 | 2006-10-11 | 2007-04-08
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20056 | STORM SEWERS-GATEWAY ESTATES - PHASE C (HD-161C) | 4 | BID AWARD AND REGISTER CONTRCT | 2007-04-09 | 2007-07-07 | 2012-03-08 | 2012-06-05
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20056 | STORM SEWERS-GATEWAY ESTATES - PHASE C (HD-161C) | 5 | CONSTRUCTION TO 25% | 2007-07-08 | 2007-11-04 | 2012-06-06 | 2012-06-05
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20056 | STORM SEWERS-GATEWAY ESTATES - PHASE C (HD-161C) | 6 | CONSTRUCTION TO 50% | 2007-11-05 | 2008-03-03 | 2012-06-06 | 2012-06-05
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20056 | STORM SEWERS-GATEWAY ESTATES - PHASE C (HD-161C) | 7 | CONSTRUCTION TO 75% | 2008-03-04 | 2008-07-01 | 2012-06-06 | 2012-06-05
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20056 | STORM SEWERS-GATEWAY ESTATES - PHASE C (HD-161C) | 8 | ORIGINAL EQUIP & FURNISHING | 2008-07-02 | 2008-09-29 | 2012-06-06 | 2012-06-05
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20056 | STORM SEWERS-GATEWAY ESTATES - PHASE C (HD-161C) | 9 | SUBSTANTIAL COMPLETION | 2008-09-30 | 2008-11-28 | 2012-06-06 | 2012-06-05
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20056 | STORM SEWERS-GATEWAY ESTATES - PHASE C (HD-161C) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-11-29 | 2008-12-28 | 2012-06-06 | 2022-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20065 | High level storm sewer Gowanus Canal Area | 1 | DEVELOP SCOPE | 2012-03-01 | 2012-05-29 | 2011-04-04 | 2012-02-14
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20065 | High level storm sewer Gowanus Canal Area | 2 | PRELIMINARY DESIGN | 2012-05-30 | 2012-09-26 | 2012-02-15 | 2012-08-13
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20065 | High level storm sewer Gowanus Canal Area | 3 | FINAL DESIGN | 2012-09-27 | 2013-03-25 | 2012-08-14 | 2015-02-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20065 | High level storm sewer Gowanus Canal Area | 4 | BID AWARD AND REGISTER CONTRCT | 2013-03-26 | 2013-06-23 | 2015-02-26 | 2016-03-27
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20065 | High level storm sewer Gowanus Canal Area | 5 | CONSTRUCTION TO 25% | 2013-06-24 | 2013-10-21 | 2016-03-28 | 2016-07-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20065 | High level storm sewer Gowanus Canal Area | 6 | CONSTRUCTION TO 50% | 2013-10-22 | 2014-02-18 | 2016-07-26 | 2016-11-22
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20065 | High level storm sewer Gowanus Canal Area | 7 | CONSTRUCTION TO 75% | 2014-02-19 | 2014-06-18 | 2016-11-23 | 2017-03-22
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20065 | High level storm sewer Gowanus Canal Area | 8 | ORIGINAL EQUIP & FURNISHING | 2014-06-19 | 2014-09-16 | 2017-03-23 | 2018-11-22
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20065 | High level storm sewer Gowanus Canal Area | 9 | SUBSTANTIAL COMPLETION | 2014-09-17 | 2014-11-15 | 2018-11-23 | 2019-01-21
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20065 | High level storm sewer Gowanus Canal Area | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-11-16 | 2014-12-15 | 2019-01-22 | 2024-06-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20067 | High level storm sewer Gowanus Canal Area. Phase 2. | 1 | DEVELOP SCOPE | 2019-03-05 | 2019-06-02 | 2015-02-07 | 2017-05-07
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20067 | High level storm sewer Gowanus Canal Area. Phase 2. | 2 | PRELIMINARY DESIGN | 2019-06-03 | 2019-09-30 | 2017-05-08 | 2017-09-04
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20067 | High level storm sewer Gowanus Canal Area. Phase 2. | 3 | FINAL DESIGN | 2019-10-01 | 2020-03-28 | 2017-09-05 | 2018-03-03
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20067 | High level storm sewer Gowanus Canal Area. Phase 2. | 4 | BID AWARD AND REGISTER CONTRCT | 2020-03-29 | 2020-06-26 | 2018-03-04 | 2018-06-01
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20067 | High level storm sewer Gowanus Canal Area. Phase 2. | 5 | CONSTRUCTION TO 25% | 2020-06-27 | 2020-10-24 | 2018-06-02 | 2018-09-29
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20067 | High level storm sewer Gowanus Canal Area. Phase 2. | 6 | CONSTRUCTION TO 50% | 2020-10-25 | 2021-02-21 | 2018-09-30 | 2019-01-27
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20067 | High level storm sewer Gowanus Canal Area. Phase 2. | 7 | CONSTRUCTION TO 75% | 2021-02-22 | 2021-06-21 | 2019-01-28 | 2020-06-10
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20067 | High level storm sewer Gowanus Canal Area. Phase 2. | 8 | ORIGINAL EQUIP & FURNISHING | 2021-06-22 | 2021-09-19 | 2020-06-11 | 2020-09-08
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20067 | High level storm sewer Gowanus Canal Area. Phase 2. | 9 | SUBSTANTIAL COMPLETION | 2021-09-20 | 2021-11-18 | 2020-09-09 | 2020-11-07
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20067 | High level storm sewer Gowanus Canal Area. Phase 2. | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-11-19 | 2021-12-18 | 2020-11-08 | 2024-09-28
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20069 | Storm Sewer installation, & WM replacement, Gerritsen Beach, | 2 | PRELIMINARY DESIGN | 2014-03-27 | 2015-03-21 | 2014-03-27 | 2015-03-21
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20069 | Storm Sewer installation, & WM replacement, Gerritsen Beach, | 3 | FINAL DESIGN | 2015-03-22 | 2016-09-11 | 2015-03-22 | 2016-09-11
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20069 | Storm Sewer installation, & WM replacement, Gerritsen Beach, | 4 | BID AWARD AND REGISTER CONTRCT | 2016-09-12 | 2017-06-08 | 2016-09-12 | 2017-06-08
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20069 | Storm Sewer installation, & WM replacement, Gerritsen Beach, | 5 | CONSTRUCTION TO 25% | 2017-06-09 | 2018-06-03 | 2017-06-09 | 2018-06-03
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20069 | Storm Sewer installation, & WM replacement, Gerritsen Beach, | 6 | CONSTRUCTION TO 50% | 2018-06-04 | 2019-05-29 | 2018-06-04 | 2019-05-29
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20069 | Storm Sewer installation, & WM replacement, Gerritsen Beach, | 7 | CONSTRUCTION TO 75% | 2019-05-30 | 2020-05-23 | 2019-05-30 | 2020-05-23
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20069 | Storm Sewer installation, & WM replacement, Gerritsen Beach, | 8 | ORIGINAL EQUIP & FURNISHING | 2020-05-24 | 2021-02-17 | 2020-05-24 | 2021-02-17
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20069 | Storm Sewer installation, & WM replacement, Gerritsen Beach, | 9 | SUBSTANTIAL COMPLETION | 2021-02-18 | 2021-08-16 | 2021-02-18 | 2021-08-16
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20069 | Storm Sewer installation, & WM replacement, Gerritsen Beach, | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-08-17 | 2021-11-14 | 2021-08-17 | 2021-11-14
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20070 | Guniting & exterior repair of the 25th Ave outfall sewer | 1 | DEVELOP SCOPE | 2013-10-03 | 2014-06-29 | 2013-10-03 | 2014-06-29
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20070 | Guniting & exterior repair of the 25th Ave outfall sewer | 2 | PRELIMINARY DESIGN | 2014-06-30 | 2015-06-24 | 2014-06-30 | 2015-06-24
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20070 | Guniting & exterior repair of the 25th Ave outfall sewer | 3 | FINAL DESIGN | 2015-06-25 | 2016-12-15 | 2015-06-25 | 2016-12-15
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20070 | Guniting & exterior repair of the 25th Ave outfall sewer | 4 | BID AWARD AND REGISTER CONTRCT | 2016-12-16 | 2017-09-11 | 2016-12-16 | 2017-09-11
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20070 | Guniting & exterior repair of the 25th Ave outfall sewer | 5 | CONSTRUCTION TO 25% | 2017-09-12 | 2018-09-06 | 2017-09-12 | 2018-09-06
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20070 | Guniting & exterior repair of the 25th Ave outfall sewer | 6 | CONSTRUCTION TO 50% | 2018-09-07 | 2019-09-01 | 2018-09-07 | 2019-09-01
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20070 | Guniting & exterior repair of the 25th Ave outfall sewer | 7 | CONSTRUCTION TO 75% | 2019-09-02 | 2020-08-26 | 2019-09-02 | 2020-08-26
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20070 | Guniting & exterior repair of the 25th Ave outfall sewer | 8 | ORIGINAL EQUIP & FURNISHING | 2020-08-27 | 2021-05-23 | 2020-08-27 | 2021-05-23
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20070 | Guniting & exterior repair of the 25th Ave outfall sewer | 9 | SUBSTANTIAL COMPLETION | 2021-05-24 | 2021-11-19 | 2021-05-24 | 2021-11-19
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20070 | Guniting & exterior repair of the 25th Ave outfall sewer | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-11-20 | 2022-02-17 | 2021-11-20 | 2022-02-17
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20076 | Replace deficient combined sewers and WM in East 80 St | 1 | DEVELOP SCOPE | 2019-12-09 | 2020-03-07 | 2019-12-09 | 2020-03-07
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20076 | Replace deficient combined sewers and WM in East 80 St | 2 | PRELIMINARY DESIGN | 2020-03-08 | 2020-07-05 | 2020-03-08 | 2020-07-05
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20076 | Replace deficient combined sewers and WM in East 80 St | 3 | FINAL DESIGN | 2020-07-06 | 2021-01-01 | 2020-07-06 | 2021-01-01
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20076 | Replace deficient combined sewers and WM in East 80 St | 4 | BID AWARD AND REGISTER CONTRCT | 2021-01-02 | 2021-04-01 | 2021-01-02 | 2021-04-01
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20076 | Replace deficient combined sewers and WM in East 80 St | 5 | CONSTRUCTION TO 25% | 2021-04-02 | 2021-07-30 | 2021-04-02 | 2021-07-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20076 | Replace deficient combined sewers and WM in East 80 St | 6 | CONSTRUCTION TO 50% | 2021-07-31 | 2021-11-27 | 2021-07-31 | 2021-11-27
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20076 | Replace deficient combined sewers and WM in East 80 St | 7 | CONSTRUCTION TO 75% | 2021-11-28 | 2022-03-27 | 2021-11-28 | 2022-03-27
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20076 | Replace deficient combined sewers and WM in East 80 St | 8 | ORIGINAL EQUIP & FURNISHING | 2022-03-28 | 2022-06-25 | 2022-03-28 | 2022-06-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20076 | Replace deficient combined sewers and WM in East 80 St | 9 | SUBSTANTIAL COMPLETION | 2022-06-26 | 2022-08-24 | 2022-06-26 | 2022-08-24
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20076 | Replace deficient combined sewers and WM in East 80 St | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-08-25 | 2022-09-23 | 2022-08-25 | 2022-09-23
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEKBS8 | Reconstruction of Existing Sewers, South Brooklyn | 1 | DEVELOP SCOPE | 2022-06-01 | 2022-08-29 | 2019-06-01 | 2022-08-29
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEKBS8 | Reconstruction of Existing Sewers, South Brooklyn | 2 | PRELIMINARY DESIGN | 2022-08-30 | 2022-12-27 | 2022-08-30 | 2022-12-27
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEKBS8 | Reconstruction of Existing Sewers, South Brooklyn | 3 | FINAL DESIGN | 2022-12-28 | 2023-06-25 | 2022-12-28 | 2023-06-25
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEKBS8 | Reconstruction of Existing Sewers, South Brooklyn | 4 | BID AWARD AND REGISTER CONTRCT | 2023-06-26 | 2023-09-23 | 2023-06-26 | 2023-09-23
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEKBS8 | Reconstruction of Existing Sewers, South Brooklyn | 5 | CONSTRUCTION TO 25% | 2023-09-24 | 2024-01-21 | 2023-09-24 | 2024-01-21
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEKBS8 | Reconstruction of Existing Sewers, South Brooklyn | 6 | CONSTRUCTION TO 50% | 2024-01-22 | 2024-05-20 | 2024-01-22 | 2024-05-20
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEKBS8 | Reconstruction of Existing Sewers, South Brooklyn | 7 | CONSTRUCTION TO 75% | 2024-05-21 | 2024-09-17 | 2024-05-21 | 2024-09-17
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEKBS8 | Reconstruction of Existing Sewers, South Brooklyn | 8 | ORIGINAL EQUIP & FURNISHING | 2024-09-18 | 2024-12-16 | 2024-09-18 | 2024-12-16
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEKBS8 | Reconstruction of Existing Sewers, South Brooklyn | 9 | SUBSTANTIAL COMPLETION | 2024-12-17 | 2025-02-14 | 2024-12-17 | 2025-02-14
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEKBS8 | Reconstruction of Existing Sewers, South Brooklyn | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-02-15 | 2025-03-16 | 2025-02-15 | 2025-12-30
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SOLARDOS1 | Brooklyn 17/18 HVAC AND ROOF REPLACEMENT | 1 | PROJECT START | 2018-03-01 | 2018-03-01 | 2016-09-08 | 2016-09-09
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SOLARDOS1 | Brooklyn 17/18 HVAC AND ROOF REPLACEMENT | 2 | DESIGN START | 2018-03-02 | 2018-03-02 | 2016-09-10 | 2017-05-11
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SOLARDOS1 | Brooklyn 17/18 HVAC AND ROOF REPLACEMENT | 3 | DESIGN COMPLETION | 2018-03-03 | 2018-03-03 | 2017-05-12 | 2019-06-28
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SOLARDOS1 | Brooklyn 17/18 HVAC AND ROOF REPLACEMENT | 4 | CONSTRUCTION START | 2018-03-04 | 2018-03-04 | 2019-06-29 | 2020-02-03
20201123 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SOLARDOS1 | Brooklyn 17/18 HVAC AND ROOF REPLACEMENT | 5 | CONSTRUCTION COMPLETION | 2018-03-05 | 2018-03-05 | 2020-02-04 | 2022-12-30
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEBPL901 | BPL - AHU Replacement at New Brower Park Branch | 1 | DEVELOP SCOPE | 2020-01-15 | 2020-02-13 | 2022-06-01 | 2024-04-30
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEBPL901 | BPL - AHU Replacement at New Brower Park Branch | 2 | BID AWARD AND REGISTER CONTRCT | 2020-02-14 | 2020-04-13 | 2024-05-01 | 2024-06-29
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEBPL901 | BPL - AHU Replacement at New Brower Park Branch | 3 | CONSTRUCTION TO 50% | 2020-04-14 | 2020-10-10 | 2024-06-30 | 2024-12-26
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEBPL901 | BPL - AHU Replacement at New Brower Park Branch | 4 | CONSTRUCTION TO 75% | 2020-10-11 | 2021-01-08 | 2024-12-27 | 2025-03-26
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEBPL901 | BPL - AHU Replacement at New Brower Park Branch | 5 | SUBSTANTIAL COMPLETION | 2021-01-09 | 2021-03-09 | 2025-03-27 | 2025-05-25
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEBPL901 | BPL - AHU Replacement at New Brower Park Branch | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-10 | 2021-04-08 | 2025-05-26 | 2025-06-24
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDEP901 | DEP - Gravity Belt Thickener (GBT) at Newtown Creek WRRF | 1 | DEVELOP SCOPE | 2020-04-15 | 2020-05-14 | 2021-06-01 | 2021-06-30
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDEP901 | DEP - Gravity Belt Thickener (GBT) at Newtown Creek WRRF | 2 | BID AWARD AND REGISTER CONTRCT | 2020-05-15 | 2020-07-13 | 2023-07-01 | 2023-08-29
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDEP901 | DEP - Gravity Belt Thickener (GBT) at Newtown Creek WRRF | 3 | CONSTRUCTION TO 50% | 2020-07-14 | 2021-01-09 | 2023-08-30 | 2024-02-25
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDEP901 | DEP - Gravity Belt Thickener (GBT) at Newtown Creek WRRF | 4 | CONSTRUCTION TO 75% | 2021-01-10 | 2021-04-09 | 2024-02-26 | 2024-05-25
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDEP901 | DEP - Gravity Belt Thickener (GBT) at Newtown Creek WRRF | 5 | SUBSTANTIAL COMPLETION | 2021-04-10 | 2021-06-08 | 2024-05-26 | 2024-07-24
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDEP901 | DEP - Gravity Belt Thickener (GBT) at Newtown Creek WRRF | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-06-09 | 2021-07-08 | 2024-07-25 | 2024-08-23
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOE607 | DOE - LIGHTING UPGRADES | 1 | DEVELOP SCOPE | 2019-06-01 | 2019-06-30 | 2019-06-01 | 2019-06-30
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOE607 | DOE - LIGHTING UPGRADES | 2 | BID AWARD AND REGISTER CONTRCT | 2019-07-01 | 2019-08-29 | 2019-07-01 | 2019-08-29
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOE607 | DOE - LIGHTING UPGRADES | 3 | CONSTRUCTION TO 50% | 2019-08-30 | 2020-02-25 | 2022-06-01 | 2024-09-03
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOE607 | DOE - LIGHTING UPGRADES | 4 | CONSTRUCTION TO 75% | 2020-02-26 | 2020-05-25 | 2024-09-04 | 2024-12-02
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOE607 | DOE - LIGHTING UPGRADES | 5 | SUBSTANTIAL COMPLETION | 2020-05-26 | 2020-07-24 | 2024-12-03 | 2025-01-31
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOE607 | DOE - LIGHTING UPGRADES | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-07-25 | 2020-08-23 | 2025-02-01 | 2025-03-02
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOE702 | DOE - VACANCY SENSORS | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-06-30 | 2020-06-01 | 2020-06-30
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOE702 | DOE - VACANCY SENSORS | 2 | BID AWARD AND REGISTER CONTRCT | 2020-07-01 | 2020-08-29 | 2020-07-01 | 2020-08-29
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOE702 | DOE - VACANCY SENSORS | 3 | CONSTRUCTION TO 50% | 2020-08-30 | 2021-02-25 | 2020-08-30 | 2021-02-25
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOE702 | DOE - VACANCY SENSORS | 4 | CONSTRUCTION TO 75% | 2021-02-26 | 2021-05-26 | 2021-02-26 | 2021-05-26
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOE702 | DOE - VACANCY SENSORS | 5 | SUBSTANTIAL COMPLETION | 2021-05-27 | 2021-07-25 | 2021-05-27 | 2021-07-25
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOE702 | DOE - VACANCY SENSORS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-07-26 | 2021-08-24 | 2021-07-26 | 2021-08-24
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | BKLYNMTC | Consolidation of four Bklyn DCP offices into one at 12 MTC | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-08-29 | 2020-06-01 | 2020-08-29
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | BKLYNMTC | Consolidation of four Bklyn DCP offices into one at 12 MTC | 2 | PRELIMINARY DESIGN | 2020-08-30 | 2020-12-27 | 2020-08-30 | 2020-12-27
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | BKLYNMTC | Consolidation of four Bklyn DCP offices into one at 12 MTC | 3 | FINAL DESIGN | 2020-12-28 | 2021-06-25 | 2020-12-28 | 2021-06-25
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | BKLYNMTC | Consolidation of four Bklyn DCP offices into one at 12 MTC | 4 | BID AWARD AND REGISTER CONTRCT | 2021-06-26 | 2021-09-23 | 2021-06-26 | 2021-09-23
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | BKLYNMTC | Consolidation of four Bklyn DCP offices into one at 12 MTC | 5 | CONSTRUCTION TO 25% | 2021-09-24 | 2022-01-21 | 2021-09-24 | 2022-01-21
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | BKLYNMTC | Consolidation of four Bklyn DCP offices into one at 12 MTC | 6 | CONSTRUCTION TO 50% | 2022-01-22 | 2022-05-21 | 2022-01-22 | 2022-05-21
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | BKLYNMTC | Consolidation of four Bklyn DCP offices into one at 12 MTC | 7 | CONSTRUCTION TO 75% | 2022-05-22 | 2022-09-18 | 2022-05-22 | 2022-09-18
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | BKLYNMTC | Consolidation of four Bklyn DCP offices into one at 12 MTC | 8 | ORIGINAL EQUIP & FURNISHING | 2022-09-19 | 2022-12-17 | 2022-09-19 | 2022-12-17
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | BKLYNMTC | Consolidation of four Bklyn DCP offices into one at 12 MTC | 9 | SUBSTANTIAL COMPLETION | 2022-12-18 | 2023-02-15 | 2022-12-18 | 2023-02-15
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | BKLYNMTC | Consolidation of four Bklyn DCP offices into one at 12 MTC | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-02-16 | 2023-06-30 | 2023-02-16 | 2023-06-30
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264BKCV | 210 JORALEMON ST. OCA RELOCATION | 1 | DEVELOP SCOPE | 2016-08-22 | 2016-11-19 | 2016-08-22 | 2016-11-19
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264BKCV | 210 JORALEMON ST. OCA RELOCATION | 2 | PRELIMINARY DESIGN | 2016-11-20 | 2017-03-19 | 2016-11-20 | 2017-03-19
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264BKCV | 210 JORALEMON ST. OCA RELOCATION | 3 | FINAL DESIGN | 2017-03-20 | 2017-09-15 | 2017-03-20 | 2017-09-15
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264BKCV | 210 JORALEMON ST. OCA RELOCATION | 4 | BID AWARD AND REGISTER CONTRCT | 2017-09-16 | 2017-12-14 | 2017-09-16 | 2017-12-14
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264BKCV | 210 JORALEMON ST. OCA RELOCATION | 5 | CONSTRUCTION TO 25% | 2017-12-15 | 2018-04-13 | 2017-12-15 | 2018-04-13
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264BKCV | 210 JORALEMON ST. OCA RELOCATION | 6 | CONSTRUCTION TO 50% | 2018-04-14 | 2018-08-11 | 2018-04-14 | 2018-08-11
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264BKCV | 210 JORALEMON ST. OCA RELOCATION | 7 | CONSTRUCTION TO 75% | 2018-08-12 | 2018-12-09 | 2018-08-12 | 2018-12-09
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264BKCV | 210 JORALEMON ST. OCA RELOCATION | 8 | ORIGINAL EQUIP & FURNISHING | 2018-12-10 | 2019-03-09 | 2018-12-10 | 2019-03-09
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264BKCV | 210 JORALEMON ST. OCA RELOCATION | 9 | SUBSTANTIAL COMPLETION | 2019-03-10 | 2019-05-08 | 2019-03-10 | 2019-05-08
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264BKCV | 210 JORALEMON ST. OCA RELOCATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-05-09 | 2023-05-05 | 2019-05-09 | 2023-05-05
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO272BLR | 45 MONROE PL - BOILER PLANT UPGRADE | 1 | DEVELOP SCOPE | 2021-06-01 | 2021-08-29 | 2021-06-01 | 2021-08-29
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO272BLR | 45 MONROE PL - BOILER PLANT UPGRADE | 2 | PRELIMINARY DESIGN | 2021-08-30 | 2021-12-27 | 2021-08-30 | 2021-12-27
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO272BLR | 45 MONROE PL - BOILER PLANT UPGRADE | 3 | FINAL DESIGN | 2021-12-28 | 2022-06-25 | 2021-12-28 | 2022-06-25
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO272BLR | 45 MONROE PL - BOILER PLANT UPGRADE | 4 | BID AWARD AND REGISTER CONTRCT | 2022-06-26 | 2022-09-23 | 2022-06-26 | 2022-09-23
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO272BLR | 45 MONROE PL - BOILER PLANT UPGRADE | 5 | CONSTRUCTION TO 25% | 2024-06-01 | 2025-10-09 | 2024-06-01 | 2025-10-09
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO272BLR | 45 MONROE PL - BOILER PLANT UPGRADE | 6 | CONSTRUCTION TO 50% | 2025-10-10 | 2026-02-06 | 2025-10-10 | 2026-02-06
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO272BLR | 45 MONROE PL - BOILER PLANT UPGRADE | 7 | CONSTRUCTION TO 75% | 2026-02-07 | 2026-06-06 | 2026-02-07 | 2026-06-06
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO272BLR | 45 MONROE PL - BOILER PLANT UPGRADE | 8 | ORIGINAL EQUIP & FURNISHING | 2026-06-07 | 2026-09-04 | 2026-06-07 | 2026-09-04
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO272BLR | 45 MONROE PL - BOILER PLANT UPGRADE | 9 | SUBSTANTIAL COMPLETION | 2026-09-05 | 2026-11-03 | 2026-09-05 | 2026-11-03
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO272BLR | 45 MONROE PL - BOILER PLANT UPGRADE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2026-11-04 | 2026-12-03 | 2026-11-04 | 2026-12-03
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO272CHIL | 45 MONROE PL CHILLER REPLACEMENT | 1 | DEVELOP SCOPE | 2019-06-01 | 2019-08-29 | 2019-06-01 | 2019-08-29
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO272CHIL | 45 MONROE PL CHILLER REPLACEMENT | 2 | PRELIMINARY DESIGN | 2019-08-30 | 2019-12-27 | 2019-08-30 | 2019-12-27
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO272CHIL | 45 MONROE PL CHILLER REPLACEMENT | 3 | FINAL DESIGN | 2019-12-28 | 2020-06-24 | 2019-12-28 | 2020-06-24
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO272CHIL | 45 MONROE PL CHILLER REPLACEMENT | 4 | BID AWARD AND REGISTER CONTRCT | 2020-06-25 | 2020-09-22 | 2020-06-25 | 2020-09-22
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO272CHIL | 45 MONROE PL CHILLER REPLACEMENT | 5 | CONSTRUCTION TO 25% | 2020-09-23 | 2021-01-20 | 2020-09-23 | 2021-01-20
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO272CHIL | 45 MONROE PL CHILLER REPLACEMENT | 6 | CONSTRUCTION TO 50% | 2021-01-21 | 2021-05-20 | 2021-01-21 | 2021-05-20
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO272CHIL | 45 MONROE PL CHILLER REPLACEMENT | 7 | CONSTRUCTION TO 75% | 2021-05-21 | 2021-09-17 | 2021-05-21 | 2021-09-17
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO272CHIL | 45 MONROE PL CHILLER REPLACEMENT | 8 | ORIGINAL EQUIP & FURNISHING | 2021-09-18 | 2021-12-16 | 2021-09-18 | 2021-12-16
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO272CHIL | 45 MONROE PL CHILLER REPLACEMENT | 9 | SUBSTANTIAL COMPLETION | 2021-12-17 | 2022-02-14 | 2021-12-17 | 2022-02-14
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO272CHIL | 45 MONROE PL CHILLER REPLACEMENT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-02-15 | 2022-03-16 | 2022-02-15 | 2022-03-16
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO272DW2 | 45 MONROE PL- DRIVEWAY PLACEMENT | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-08-29 | 2020-06-01 | 2020-08-29
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO272DW2 | 45 MONROE PL- DRIVEWAY PLACEMENT | 2 | PRELIMINARY DESIGN | 2020-08-30 | 2020-12-27 | 2020-08-30 | 2020-12-27
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO272DW2 | 45 MONROE PL- DRIVEWAY PLACEMENT | 3 | FINAL DESIGN | 2020-12-28 | 2021-06-25 | 2020-12-28 | 2021-06-25
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO272DW2 | 45 MONROE PL- DRIVEWAY PLACEMENT | 4 | BID AWARD AND REGISTER CONTRCT | 2021-06-26 | 2021-09-23 | 2021-06-26 | 2021-09-23
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO272DW2 | 45 MONROE PL- DRIVEWAY PLACEMENT | 5 | CONSTRUCTION TO 25% | 2021-09-24 | 2022-01-21 | 2021-09-24 | 2022-01-21
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO272DW2 | 45 MONROE PL- DRIVEWAY PLACEMENT | 6 | CONSTRUCTION TO 50% | 2022-01-22 | 2022-05-21 | 2022-01-22 | 2022-05-21
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO272DW2 | 45 MONROE PL- DRIVEWAY PLACEMENT | 7 | CONSTRUCTION TO 75% | 2022-05-22 | 2022-09-18 | 2022-05-22 | 2022-09-18
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO272DW2 | 45 MONROE PL- DRIVEWAY PLACEMENT | 8 | ORIGINAL EQUIP & FURNISHING | 2022-09-19 | 2022-12-17 | 2022-09-19 | 2022-12-17
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO272DW2 | 45 MONROE PL- DRIVEWAY PLACEMENT | 9 | SUBSTANTIAL COMPLETION | 2022-12-18 | 2023-02-15 | 2022-12-18 | 2023-02-15
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO272DW2 | 45 MONROE PL- DRIVEWAY PLACEMENT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-02-16 | 2023-03-17 | 2023-02-16 | 2023-03-17
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO278ADA1 | 360 ADAMS ST - ADA IMPROVEMENTS | 1 | DEVELOP SCOPE | 2021-06-01 | 2021-08-29 | 2021-06-01 | 2021-08-29
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO278ADA1 | 360 ADAMS ST - ADA IMPROVEMENTS | 2 | PRELIMINARY DESIGN | 2021-08-30 | 2021-12-27 | 2021-08-30 | 2021-12-27
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO278ADA1 | 360 ADAMS ST - ADA IMPROVEMENTS | 3 | FINAL DESIGN | 2021-12-28 | 2022-06-25 | 2021-12-28 | 2022-06-25
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO278ADA1 | 360 ADAMS ST - ADA IMPROVEMENTS | 4 | BID AWARD AND REGISTER CONTRCT | 2022-06-26 | 2022-09-23 | 2022-06-26 | 2022-09-23
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO278ADA1 | 360 ADAMS ST - ADA IMPROVEMENTS | 5 | CONSTRUCTION TO 25% | 2024-06-01 | 2024-09-28 | 2024-06-01 | 2024-09-28
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO278ADA1 | 360 ADAMS ST - ADA IMPROVEMENTS | 6 | CONSTRUCTION TO 50% | 2024-09-29 | 2025-01-26 | 2024-09-29 | 2025-01-26
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO278ADA1 | 360 ADAMS ST - ADA IMPROVEMENTS | 7 | CONSTRUCTION TO 75% | 2025-01-27 | 2025-05-26 | 2025-01-27 | 2025-05-26
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO278ADA1 | 360 ADAMS ST - ADA IMPROVEMENTS | 8 | ORIGINAL EQUIP & FURNISHING | 2025-05-27 | 2025-08-24 | 2025-05-27 | 2025-08-24
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO278ADA1 | 360 ADAMS ST - ADA IMPROVEMENTS | 9 | SUBSTANTIAL COMPLETION | 2025-08-25 | 2025-10-23 | 2025-08-25 | 2025-10-23
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO278ADA1 | 360 ADAMS ST - ADA IMPROVEMENTS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-10-24 | 2025-11-22 | 2025-10-24 | 2025-11-22
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO278ELV | 360 ADAMS ST.- ELEVATOR MODERNIZATION | 1 | DEVELOP SCOPE | 2022-06-01 | 2022-08-29 | 2022-06-01 | 2022-08-29
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO278ELV | 360 ADAMS ST.- ELEVATOR MODERNIZATION | 2 | PRELIMINARY DESIGN | 2022-08-30 | 2022-12-27 | 2022-08-30 | 2022-12-27
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO278ELV | 360 ADAMS ST.- ELEVATOR MODERNIZATION | 3 | FINAL DESIGN | 2022-12-28 | 2023-06-25 | 2022-12-28 | 2023-06-25
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO278ELV | 360 ADAMS ST.- ELEVATOR MODERNIZATION | 4 | BID AWARD AND REGISTER CONTRCT | 2023-06-26 | 2023-09-23 | 2023-06-26 | 2023-09-23
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO278ELV | 360 ADAMS ST.- ELEVATOR MODERNIZATION | 5 | CONSTRUCTION TO 25% | 2023-09-24 | 2024-01-21 | 2023-09-24 | 2024-01-21
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO278ELV | 360 ADAMS ST.- ELEVATOR MODERNIZATION | 6 | CONSTRUCTION TO 50% | 2024-01-22 | 2024-05-20 | 2024-01-22 | 2024-05-20
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO278ELV | 360 ADAMS ST.- ELEVATOR MODERNIZATION | 7 | CONSTRUCTION TO 75% | 2024-05-21 | 2024-09-17 | 2024-05-21 | 2024-09-17
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO278ELV | 360 ADAMS ST.- ELEVATOR MODERNIZATION | 8 | ORIGINAL EQUIP & FURNISHING | 2024-09-18 | 2024-12-16 | 2024-09-18 | 2024-12-16
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO278ELV | 360 ADAMS ST.- ELEVATOR MODERNIZATION | 9 | SUBSTANTIAL COMPLETION | 2024-12-17 | 2025-02-14 | 2024-12-17 | 2025-02-14
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO278ELV | 360 ADAMS ST.- ELEVATOR MODERNIZATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-02-15 | 2026-06-30 | 2025-02-15 | 2026-06-30
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO278RF | 360 ADAMS STREET - ROOF | 1 | DEVELOP SCOPE | 2022-02-01 | 2022-05-01 | 2022-02-01 | 2022-05-01
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO278RF | 360 ADAMS STREET - ROOF | 2 | PRELIMINARY DESIGN | 2022-05-02 | 2022-08-29 | 2022-05-02 | 2022-08-29
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO278RF | 360 ADAMS STREET - ROOF | 3 | FINAL DESIGN | 2022-08-30 | 2023-02-25 | 2022-08-30 | 2023-02-25
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO278RF | 360 ADAMS STREET - ROOF | 4 | BID AWARD AND REGISTER CONTRCT | 2023-02-26 | 2023-05-26 | 2023-02-26 | 2023-05-26
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO278RF | 360 ADAMS STREET - ROOF | 5 | CONSTRUCTION TO 25% | 2023-05-27 | 2023-09-23 | 2023-05-27 | 2023-09-23
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO278RF | 360 ADAMS STREET - ROOF | 6 | CONSTRUCTION TO 50% | 2023-09-24 | 2024-01-21 | 2023-09-24 | 2024-01-21
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO278RF | 360 ADAMS STREET - ROOF | 7 | CONSTRUCTION TO 75% | 2024-01-22 | 2024-05-20 | 2024-01-22 | 2024-05-20
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO278RF | 360 ADAMS STREET - ROOF | 8 | ORIGINAL EQUIP & FURNISHING | 2024-05-21 | 2024-08-18 | 2024-05-21 | 2024-08-18
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO278RF | 360 ADAMS STREET - ROOF | 9 | SUBSTANTIAL COMPLETION | 2024-08-19 | 2024-10-17 | 2024-08-19 | 2024-10-17
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO278RF | 360 ADAMS STREET - ROOF | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-10-18 | 2024-11-16 | 2024-10-18 | 2024-11-16
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO278TOIL | 360 ADAMS ST. - CODE COMPLIANT TOILET UPGRADE | 1 | DEVELOP SCOPE | 2016-01-01 | 2016-03-30 | 2022-06-30 | 2022-09-27
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO278TOIL | 360 ADAMS ST. - CODE COMPLIANT TOILET UPGRADE | 2 | PRELIMINARY DESIGN | 2016-03-31 | 2016-07-28 | 2022-09-28 | 2023-01-25
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO278TOIL | 360 ADAMS ST. - CODE COMPLIANT TOILET UPGRADE | 3 | FINAL DESIGN | 2016-07-29 | 2017-01-24 | 2023-01-26 | 2023-07-24
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO278TOIL | 360 ADAMS ST. - CODE COMPLIANT TOILET UPGRADE | 4 | BID AWARD AND REGISTER CONTRCT | 2017-01-25 | 2017-04-24 | 2023-07-25 | 2023-10-22
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO278TOIL | 360 ADAMS ST. - CODE COMPLIANT TOILET UPGRADE | 5 | CONSTRUCTION TO 25% | 2017-04-25 | 2017-08-22 | 2023-10-23 | 2024-02-19
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO278TOIL | 360 ADAMS ST. - CODE COMPLIANT TOILET UPGRADE | 6 | CONSTRUCTION TO 50% | 2017-08-23 | 2017-12-20 | 2024-02-20 | 2024-06-18
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO278TOIL | 360 ADAMS ST. - CODE COMPLIANT TOILET UPGRADE | 7 | CONSTRUCTION TO 75% | 2017-12-21 | 2018-04-19 | 2024-06-19 | 2024-10-16
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO278TOIL | 360 ADAMS ST. - CODE COMPLIANT TOILET UPGRADE | 8 | ORIGINAL EQUIP & FURNISHING | 2018-04-20 | 2018-07-18 | 2024-10-17 | 2025-01-14
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO278TOIL | 360 ADAMS ST. - CODE COMPLIANT TOILET UPGRADE | 9 | SUBSTANTIAL COMPLETION | 2018-07-19 | 2018-09-16 | 2025-01-15 | 2025-03-15
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO278TOIL | 360 ADAMS ST. - CODE COMPLIANT TOILET UPGRADE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-09-17 | 2018-10-16 | 2025-03-16 | 2025-04-14
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E09-00030 | NYPD - 09-064; 69th Precinct; 9720 Foster Avenue | 1 | DEVELOP SCOPE | 2011-01-01 | 2011-01-30 | 2020-06-01 | 2020-06-30
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E09-00030 | NYPD - 09-064; 69th Precinct; 9720 Foster Avenue | 2 | BID AWARD AND REGISTER CONTRCT | 2011-01-31 | 2011-03-01 | 2020-07-01 | 2020-07-30
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E09-00030 | NYPD - 09-064; 69th Precinct; 9720 Foster Avenue | 3 | CONSTRUCTION TO 50% | 2011-03-02 | 2011-05-30 | 2020-07-31 | 2020-10-28
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E09-00030 | NYPD - 09-064; 69th Precinct; 9720 Foster Avenue | 4 | CONSTRUCTION TO 75% | 2011-05-31 | 2011-07-14 | 2020-10-29 | 2020-12-12
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E09-00030 | NYPD - 09-064; 69th Precinct; 9720 Foster Avenue | 5 | SUBSTANTIAL COMPLETION | 2011-07-15 | 2011-07-24 | 2020-12-13 | 2020-12-22
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E09-00030 | NYPD - 09-064; 69th Precinct; 9720 Foster Avenue | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2011-07-25 | 2011-08-01 | 2020-12-23 | 2022-06-30
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E19-0003 | DOHMH - Bushwick Health Center | 1 | DEVELOP SCOPE | 2019-06-01 | 2019-06-30 | 2019-06-01 | 2019-06-30
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E19-0003 | DOHMH - Bushwick Health Center | 2 | BID AWARD AND REGISTER CONTRCT | 2019-07-01 | 2019-08-29 | 2019-07-01 | 2019-08-29
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E19-0003 | DOHMH - Bushwick Health Center | 3 | CONSTRUCTION TO 50% | 2019-08-30 | 2020-02-25 | 2019-08-30 | 2020-02-25
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E19-0003 | DOHMH - Bushwick Health Center | 4 | CONSTRUCTION TO 75% | 2020-02-26 | 2020-05-25 | 2020-02-26 | 2020-05-25
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E19-0003 | DOHMH - Bushwick Health Center | 5 | SUBSTANTIAL COMPLETION | 2020-05-26 | 2020-07-24 | 2020-05-26 | 2020-07-24
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E19-0003 | DOHMH - Bushwick Health Center | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-07-25 | 2020-08-23 | 2020-07-25 | 2020-08-23
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E19-0004 | DOHMH - Crown Heights Health Center | 2 | BID AWARD AND REGISTER CONTRCT | 2019-07-01 | 2019-08-29 | 2019-07-01 | 2019-08-29
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E19-0004 | DOHMH - Crown Heights Health Center | 3 | CONSTRUCTION TO 50% | 2019-08-30 | 2020-02-25 | 2019-08-30 | 2020-02-25
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E19-0004 | DOHMH - Crown Heights Health Center | 4 | CONSTRUCTION TO 75% | 2020-02-26 | 2020-05-25 | 2020-02-26 | 2020-05-25
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E19-0004 | DOHMH - Crown Heights Health Center | 5 | SUBSTANTIAL COMPLETION | 2020-05-26 | 2020-07-24 | 2020-05-26 | 2020-07-24
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E19-0004 | DOHMH - Crown Heights Health Center | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-07-25 | 2020-08-23 | 2020-07-25 | 2020-08-23
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E19-0007 | NYPD - 77th Precinct | 1 | DEVELOP SCOPE | 2019-06-01 | 2019-06-30 | 2019-06-01 | 2019-06-30
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E19-0007 | NYPD - 77th Precinct | 2 | BID AWARD AND REGISTER CONTRCT | 2019-07-01 | 2019-08-29 | 2019-07-01 | 2019-08-29
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E19-0007 | NYPD - 77th Precinct | 3 | CONSTRUCTION TO 50% | 2019-08-30 | 2020-02-25 | 2019-08-30 | 2020-02-25
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E19-0007 | NYPD - 77th Precinct | 4 | CONSTRUCTION TO 75% | 2020-02-26 | 2020-05-25 | 2020-02-26 | 2020-05-25
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E19-0007 | NYPD - 77th Precinct | 5 | SUBSTANTIAL COMPLETION | 2020-05-26 | 2020-07-24 | 2020-05-26 | 2020-07-24
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E19-0007 | NYPD - 77th Precinct | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-07-25 | 2020-08-23 | 2020-07-25 | 2020-08-23
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E19-0008 | NYPD - Brooklyn North Boro Command | 2 | BID AWARD AND REGISTER CONTRCT | 2019-07-01 | 2019-08-29 | 2019-07-01 | 2019-08-29
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E19-0008 | NYPD - Brooklyn North Boro Command | 3 | CONSTRUCTION TO 50% | 2019-08-30 | 2020-02-25 | 2019-08-30 | 2020-02-25
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E19-0008 | NYPD - Brooklyn North Boro Command | 4 | CONSTRUCTION TO 75% | 2020-02-26 | 2020-05-25 | 2020-02-26 | 2020-05-25
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E19-0008 | NYPD - Brooklyn North Boro Command | 5 | SUBSTANTIAL COMPLETION | 2020-05-26 | 2020-07-24 | 2020-05-26 | 2020-07-24
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E19-0008 | NYPD - Brooklyn North Boro Command | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-07-25 | 2020-08-23 | 2020-07-25 | 2020-08-23
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0017 | BPL - Bushwick Branch Library | 3 | CONSTRUCTION TO 50% | 2019-08-30 | 2020-02-25 | 2019-08-30 | 2020-02-25
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0017 | BPL - Bushwick Branch Library | 4 | CONSTRUCTION TO 75% | 2020-02-26 | 2020-05-25 | 2020-02-26 | 2020-05-25
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0017 | BPL - Bushwick Branch Library | 5 | SUBSTANTIAL COMPLETION | 2020-05-26 | 2020-07-24 | 2020-05-26 | 2020-07-24
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0017 | BPL - Bushwick Branch Library | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-07-25 | 2020-08-23 | 2020-07-25 | 2020-08-23
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0020 | NYPD - 71st Precinct | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-06-30 | 2020-06-01 | 2020-06-30
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0020 | NYPD - 71st Precinct | 2 | BID AWARD AND REGISTER CONTRCT | 2020-07-01 | 2020-08-29 | 2020-07-01 | 2020-08-29
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0020 | NYPD - 71st Precinct | 3 | CONSTRUCTION TO 50% | 2020-08-30 | 2021-02-25 | 2020-08-30 | 2021-02-25
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0020 | NYPD - 71st Precinct | 4 | CONSTRUCTION TO 75% | 2021-02-26 | 2021-05-26 | 2021-02-26 | 2021-05-26
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0020 | NYPD - 71st Precinct | 5 | SUBSTANTIAL COMPLETION | 2021-05-27 | 2021-07-25 | 2021-05-27 | 2021-07-25
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0020 | NYPD - 71st Precinct | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-07-26 | 2021-08-24 | 2021-07-26 | 2021-08-24
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0027 | DSNY - Cioffe Borough Repair Shop | 1 | DEVELOP SCOPE | 2019-06-01 | 2019-06-30 | 2019-06-01 | 2019-06-30
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0027 | DSNY - Cioffe Borough Repair Shop | 2 | BID AWARD AND REGISTER CONTRCT | 2019-07-01 | 2019-08-29 | 2019-07-01 | 2019-08-29
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0027 | DSNY - Cioffe Borough Repair Shop | 3 | CONSTRUCTION TO 50% | 2019-08-30 | 2020-02-25 | 2019-08-30 | 2020-02-25
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0027 | DSNY - Cioffe Borough Repair Shop | 4 | CONSTRUCTION TO 75% | 2020-02-26 | 2020-05-25 | 2020-02-26 | 2020-05-25
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0027 | DSNY - Cioffe Borough Repair Shop | 5 | SUBSTANTIAL COMPLETION | 2020-05-26 | 2020-07-24 | 2020-05-26 | 2020-07-24
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0027 | DSNY - Cioffe Borough Repair Shop | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-07-25 | 2020-08-23 | 2020-07-25 | 2020-08-23
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0037 | DOHMH - Fort Greene Health Center | 1 | DEVELOP SCOPE | 2019-06-01 | 2019-06-30 | 2019-06-01 | 2019-06-30
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0037 | DOHMH - Fort Greene Health Center | 2 | BID AWARD AND REGISTER CONTRCT | 2019-07-01 | 2019-08-29 | 2019-07-01 | 2019-08-29
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0037 | DOHMH - Fort Greene Health Center | 3 | CONSTRUCTION TO 50% | 2019-08-30 | 2020-02-25 | 2019-08-30 | 2020-02-25
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0037 | DOHMH - Fort Greene Health Center | 4 | CONSTRUCTION TO 75% | 2020-02-26 | 2020-05-25 | 2020-02-26 | 2020-05-25
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0037 | DOHMH - Fort Greene Health Center | 5 | SUBSTANTIAL COMPLETION | 2020-05-26 | 2020-07-24 | 2020-05-26 | 2020-07-24
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0037 | DOHMH - Fort Greene Health Center | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-07-25 | 2020-08-23 | 2020-07-25 | 2020-08-23
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0057 | NYPD - 62nd Precinct | 1 | DEVELOP SCOPE | 2020-03-01 | 2020-03-30 | 2020-03-01 | 2020-03-30
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0057 | NYPD - 62nd Precinct | 2 | BID AWARD AND REGISTER CONTRCT | 2020-03-31 | 2020-05-29 | 2020-03-31 | 2020-05-29
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0057 | NYPD - 62nd Precinct | 3 | CONSTRUCTION TO 50% | 2020-05-30 | 2020-11-25 | 2022-06-01 | 2022-11-27
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0057 | NYPD - 62nd Precinct | 4 | CONSTRUCTION TO 75% | 2020-11-26 | 2021-02-23 | 2022-11-28 | 2023-02-25
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0057 | NYPD - 62nd Precinct | 5 | SUBSTANTIAL COMPLETION | 2021-02-24 | 2021-04-24 | 2023-02-26 | 2023-04-26
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0057 | NYPD - 62nd Precinct | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-04-25 | 2021-05-24 | 2023-04-27 | 2023-05-26
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0058 | NYPD - 63rd Precinct | 1 | DEVELOP SCOPE | 2020-01-05 | 2020-02-03 | 2020-06-01 | 2020-06-30
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0058 | NYPD - 63rd Precinct | 2 | BID AWARD AND REGISTER CONTRCT | 2020-02-04 | 2020-04-03 | 2020-07-01 | 2020-08-29
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0058 | NYPD - 63rd Precinct | 3 | CONSTRUCTION TO 50% | 2020-04-04 | 2020-09-30 | 2022-06-01 | 2022-11-27
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0058 | NYPD - 63rd Precinct | 4 | CONSTRUCTION TO 75% | 2020-10-01 | 2020-12-29 | 2022-11-28 | 2023-02-25
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0058 | NYPD - 63rd Precinct | 5 | SUBSTANTIAL COMPLETION | 2020-12-30 | 2021-02-27 | 2023-02-26 | 2023-04-26
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0058 | NYPD - 63rd Precinct | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-02-28 | 2021-03-29 | 2023-04-27 | 2023-05-26
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0059 | NYPD - 66th Precinct | 1 | DEVELOP SCOPE | 2020-01-15 | 2020-02-13 | 2021-06-01 | 2021-06-30
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0059 | NYPD - 66th Precinct | 2 | BID AWARD AND REGISTER CONTRCT | 2020-02-14 | 2020-04-13 | 2021-07-01 | 2021-08-29
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0059 | NYPD - 66th Precinct | 3 | CONSTRUCTION TO 50% | 2020-04-14 | 2020-10-10 | 2021-08-30 | 2022-02-25
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0059 | NYPD - 66th Precinct | 4 | CONSTRUCTION TO 75% | 2020-10-11 | 2021-01-08 | 2022-02-26 | 2022-05-26
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0059 | NYPD - 66th Precinct | 5 | SUBSTANTIAL COMPLETION | 2021-01-09 | 2021-03-09 | 2022-05-27 | 2022-07-25
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0059 | NYPD - 66th Precinct | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-10 | 2021-04-08 | 2022-07-26 | 2022-08-24
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0060 | NYPD - 70th Precinct | 1 | DEVELOP SCOPE | 2020-02-01 | 2020-03-01 | 2022-06-01 | 2022-06-30
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0060 | NYPD - 70th Precinct | 2 | BID AWARD AND REGISTER CONTRCT | 2020-03-02 | 2020-04-30 | 2022-07-01 | 2022-08-29
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0060 | NYPD - 70th Precinct | 3 | CONSTRUCTION TO 50% | 2020-05-01 | 2020-10-27 | 2022-08-30 | 2023-02-25
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0060 | NYPD - 70th Precinct | 4 | CONSTRUCTION TO 75% | 2020-10-28 | 2021-01-25 | 2023-02-26 | 2023-05-26
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0060 | NYPD - 70th Precinct | 5 | SUBSTANTIAL COMPLETION | 2021-01-26 | 2021-03-26 | 2023-05-27 | 2023-07-25
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0060 | NYPD - 70th Precinct | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-27 | 2021-04-25 | 2023-07-26 | 2023-08-24
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0061 | NYPD - 88th Precinct | 1 | DEVELOP SCOPE | 2020-02-01 | 2020-03-01 | 2022-06-01 | 2022-06-30
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0061 | NYPD - 88th Precinct | 2 | BID AWARD AND REGISTER CONTRCT | 2020-03-02 | 2020-04-30 | 2022-07-01 | 2022-08-29
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0061 | NYPD - 88th Precinct | 3 | CONSTRUCTION TO 50% | 2020-05-01 | 2020-10-27 | 2022-08-30 | 2023-02-25
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0061 | NYPD - 88th Precinct | 4 | CONSTRUCTION TO 75% | 2020-10-28 | 2021-01-25 | 2023-02-26 | 2023-05-26
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0061 | NYPD - 88th Precinct | 5 | SUBSTANTIAL COMPLETION | 2021-01-26 | 2021-03-26 | 2023-05-27 | 2023-07-25
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0061 | NYPD - 88th Precinct | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-27 | 2021-04-25 | 2023-07-26 | 2023-08-24
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0062 | NYPD - 94th Precinct | 1 | DEVELOP SCOPE | 2020-02-01 | 2020-03-01 | 2022-06-01 | 2022-06-30
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0062 | NYPD - 94th Precinct | 2 | BID AWARD AND REGISTER CONTRCT | 2020-03-02 | 2020-04-30 | 2022-07-01 | 2022-08-29
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0062 | NYPD - 94th Precinct | 3 | CONSTRUCTION TO 50% | 2020-05-01 | 2020-10-27 | 2022-08-30 | 2023-02-25
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0062 | NYPD - 94th Precinct | 4 | CONSTRUCTION TO 75% | 2020-10-28 | 2021-01-25 | 2023-02-26 | 2023-05-26
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0062 | NYPD - 94th Precinct | 5 | SUBSTANTIAL COMPLETION | 2021-01-26 | 2021-03-26 | 2023-05-27 | 2023-07-25
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0062 | NYPD - 94th Precinct | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-27 | 2021-04-25 | 2023-07-26 | 2023-08-24
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0073 | NYPD - 77TH PRECINCT ANNEX | 1 | DEVELOP SCOPE | 2020-02-15 | 2020-03-15 | 2022-06-01 | 2022-06-30
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0073 | NYPD - 77TH PRECINCT ANNEX | 2 | BID AWARD AND REGISTER CONTRCT | 2020-03-16 | 2020-05-14 | 2022-07-01 | 2022-08-29
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0073 | NYPD - 77TH PRECINCT ANNEX | 3 | CONSTRUCTION TO 50% | 2020-05-15 | 2020-11-10 | 2022-08-30 | 2023-02-25
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0073 | NYPD - 77TH PRECINCT ANNEX | 4 | CONSTRUCTION TO 75% | 2020-11-11 | 2021-02-08 | 2023-02-26 | 2023-05-26
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0073 | NYPD - 77TH PRECINCT ANNEX | 5 | SUBSTANTIAL COMPLETION | 2021-02-09 | 2021-04-09 | 2023-05-27 | 2023-07-25
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0073 | NYPD - 77TH PRECINCT ANNEX | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-04-10 | 2021-05-09 | 2023-07-26 | 2023-08-24
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0074 | NYPD - HARBOR UNIT CHARLIE | 1 | DEVELOP SCOPE | 2020-01-15 | 2020-02-13 | 2022-06-01 | 2022-06-30
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0074 | NYPD - HARBOR UNIT CHARLIE | 2 | BID AWARD AND REGISTER CONTRCT | 2020-02-14 | 2020-04-13 | 2022-07-01 | 2022-08-29
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0074 | NYPD - HARBOR UNIT CHARLIE | 3 | CONSTRUCTION TO 50% | 2020-04-14 | 2020-10-10 | 2022-08-30 | 2023-02-25
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0074 | NYPD - HARBOR UNIT CHARLIE | 4 | CONSTRUCTION TO 75% | 2020-10-11 | 2021-01-08 | 2023-02-26 | 2023-05-26
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0074 | NYPD - HARBOR UNIT CHARLIE | 5 | SUBSTANTIAL COMPLETION | 2021-01-09 | 2021-03-09 | 2023-05-27 | 2023-07-25
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0074 | NYPD - HARBOR UNIT CHARLIE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-10 | 2021-04-08 | 2023-07-26 | 2023-08-24
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0077 | NYPD - 75TH PRECINCT | 1 | DEVELOP SCOPE | 2020-02-01 | 2020-03-01 | 2022-06-01 | 2022-06-30
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0077 | NYPD - 75TH PRECINCT | 2 | BID AWARD AND REGISTER CONTRCT | 2020-03-02 | 2020-04-30 | 2022-07-01 | 2022-08-29
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0077 | NYPD - 75TH PRECINCT | 3 | CONSTRUCTION TO 50% | 2020-05-01 | 2020-10-27 | 2022-08-30 | 2023-02-25
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0077 | NYPD - 75TH PRECINCT | 4 | CONSTRUCTION TO 75% | 2020-10-28 | 2021-01-25 | 2023-02-26 | 2023-05-26
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0077 | NYPD - 75TH PRECINCT | 5 | SUBSTANTIAL COMPLETION | 2021-01-26 | 2021-03-26 | 2023-05-27 | 2023-07-25
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0077 | NYPD - 75TH PRECINCT | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-27 | 2021-04-25 | 2023-07-26 | 2023-08-24
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0079 | HHC/DHS - AUBURN FAMILY RESIDENCE (CUMBERLAND DIAGNOSTIC) | 1 | DEVELOP SCOPE | 2020-02-15 | 2020-03-15 | 2022-06-01 | 2022-06-30
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0079 | HHC/DHS - AUBURN FAMILY RESIDENCE (CUMBERLAND DIAGNOSTIC) | 2 | BID AWARD AND REGISTER CONTRCT | 2020-03-16 | 2020-05-14 | 2022-07-01 | 2022-08-29
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0079 | HHC/DHS - AUBURN FAMILY RESIDENCE (CUMBERLAND DIAGNOSTIC) | 3 | CONSTRUCTION TO 50% | 2020-05-15 | 2020-11-10 | 2022-08-30 | 2023-02-25
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0079 | HHC/DHS - AUBURN FAMILY RESIDENCE (CUMBERLAND DIAGNOSTIC) | 4 | CONSTRUCTION TO 75% | 2020-11-11 | 2021-02-08 | 2023-02-26 | 2023-05-26
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0079 | HHC/DHS - AUBURN FAMILY RESIDENCE (CUMBERLAND DIAGNOSTIC) | 5 | SUBSTANTIAL COMPLETION | 2021-02-09 | 2021-04-09 | 2023-05-27 | 2023-07-25
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0079 | HHC/DHS - AUBURN FAMILY RESIDENCE (CUMBERLAND DIAGNOSTIC) | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-04-10 | 2021-05-09 | 2023-07-26 | 2023-08-24
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0082 | DHS - FANNIE BARNES (URBAN TRANSITIONAL HOUSING) | 1 | DEVELOP SCOPE | 2020-02-15 | 2020-03-15 | 2022-06-01 | 2022-06-30
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0082 | DHS - FANNIE BARNES (URBAN TRANSITIONAL HOUSING) | 2 | BID AWARD AND REGISTER CONTRCT | 2020-03-16 | 2020-05-14 | 2022-07-01 | 2022-08-29
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0082 | DHS - FANNIE BARNES (URBAN TRANSITIONAL HOUSING) | 3 | CONSTRUCTION TO 50% | 2020-05-15 | 2020-11-10 | 2022-08-30 | 2023-02-25
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0082 | DHS - FANNIE BARNES (URBAN TRANSITIONAL HOUSING) | 4 | CONSTRUCTION TO 75% | 2020-11-11 | 2021-02-08 | 2023-02-26 | 2023-05-26
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0082 | DHS - FANNIE BARNES (URBAN TRANSITIONAL HOUSING) | 5 | SUBSTANTIAL COMPLETION | 2021-02-09 | 2021-04-09 | 2023-05-27 | 2023-07-25
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0082 | DHS - FANNIE BARNES (URBAN TRANSITIONAL HOUSING) | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-04-10 | 2021-05-09 | 2023-07-26 | 2023-08-24
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0083 | DHS - PARK SLOPE ARMORY SHELTER | 1 | DEVELOP SCOPE | 2020-02-15 | 2020-03-15 | 2020-02-15 | 2020-03-15
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0083 | DHS - PARK SLOPE ARMORY SHELTER | 2 | BID AWARD AND REGISTER CONTRCT | 2020-03-16 | 2020-05-14 | 2020-03-16 | 2020-05-14
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0083 | DHS - PARK SLOPE ARMORY SHELTER | 3 | CONSTRUCTION TO 50% | 2020-05-15 | 2020-11-10 | 2022-06-01 | 2022-11-27
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0083 | DHS - PARK SLOPE ARMORY SHELTER | 4 | CONSTRUCTION TO 75% | 2020-11-11 | 2021-02-08 | 2022-11-28 | 2023-02-25
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0083 | DHS - PARK SLOPE ARMORY SHELTER | 5 | SUBSTANTIAL COMPLETION | 2021-02-09 | 2021-04-09 | 2023-02-26 | 2023-04-26
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0083 | DHS - PARK SLOPE ARMORY SHELTER | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-04-10 | 2021-05-09 | 2023-04-27 | 2023-05-26
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0084 | DHS - ROSE McCARTHY FAMILY RESIDENCE CAMPUS (1) | 1 | DEVELOP SCOPE | 2020-02-15 | 2020-03-15 | 2020-02-15 | 2020-03-15
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0084 | DHS - ROSE McCARTHY FAMILY RESIDENCE CAMPUS (1) | 2 | BID AWARD AND REGISTER CONTRCT | 2020-03-16 | 2020-05-14 | 2020-03-16 | 2020-05-14
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0084 | DHS - ROSE McCARTHY FAMILY RESIDENCE CAMPUS (1) | 3 | CONSTRUCTION TO 50% | 2020-05-15 | 2020-11-10 | 2022-06-01 | 2022-11-27
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0084 | DHS - ROSE McCARTHY FAMILY RESIDENCE CAMPUS (1) | 4 | CONSTRUCTION TO 75% | 2020-11-11 | 2021-02-08 | 2022-11-28 | 2023-02-25
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0084 | DHS - ROSE McCARTHY FAMILY RESIDENCE CAMPUS (1) | 5 | SUBSTANTIAL COMPLETION | 2021-02-09 | 2021-04-09 | 2023-02-26 | 2023-04-26
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0084 | DHS - ROSE McCARTHY FAMILY RESIDENCE CAMPUS (1) | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-04-10 | 2021-05-09 | 2023-04-27 | 2023-05-26
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0085 | DHS - ROSE McCARTHY FAMILY RESIDENCE CAMPUS (2) | 1 | DEVELOP SCOPE | 2020-02-15 | 2020-03-15 | 2021-06-01 | 2022-08-16
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0085 | DHS - ROSE McCARTHY FAMILY RESIDENCE CAMPUS (2) | 2 | BID AWARD AND REGISTER CONTRCT | 2020-03-16 | 2020-05-14 | 2022-08-17 | 2022-10-15
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0085 | DHS - ROSE McCARTHY FAMILY RESIDENCE CAMPUS (2) | 3 | CONSTRUCTION TO 50% | 2020-05-15 | 2020-11-10 | 2022-06-01 | 2022-11-27
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0085 | DHS - ROSE McCARTHY FAMILY RESIDENCE CAMPUS (2) | 4 | CONSTRUCTION TO 75% | 2020-11-11 | 2021-02-08 | 2022-11-28 | 2023-02-25
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0085 | DHS - ROSE McCARTHY FAMILY RESIDENCE CAMPUS (2) | 5 | SUBSTANTIAL COMPLETION | 2021-02-09 | 2021-04-09 | 2023-02-26 | 2023-04-26
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0085 | DHS - ROSE McCARTHY FAMILY RESIDENCE CAMPUS (2) | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-04-10 | 2021-05-09 | 2023-04-27 | 2023-05-26
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0086 | HRA - BUSHWICK JOB CENTER (FLSUHING) (LEASED IN) | 1 | DEVELOP SCOPE | 2020-01-15 | 2020-02-13 | 2022-06-01 | 2022-06-30
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0086 | HRA - BUSHWICK JOB CENTER (FLSUHING) (LEASED IN) | 2 | BID AWARD AND REGISTER CONTRCT | 2020-02-14 | 2020-04-13 | 2022-07-01 | 2022-08-29
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0086 | HRA - BUSHWICK JOB CENTER (FLSUHING) (LEASED IN) | 3 | CONSTRUCTION TO 50% | 2020-04-14 | 2020-10-10 | 2022-08-30 | 2023-02-25
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0086 | HRA - BUSHWICK JOB CENTER (FLSUHING) (LEASED IN) | 4 | CONSTRUCTION TO 75% | 2020-10-11 | 2021-01-08 | 2023-02-26 | 2023-05-26
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0086 | HRA - BUSHWICK JOB CENTER (FLSUHING) (LEASED IN) | 5 | SUBSTANTIAL COMPLETION | 2021-01-09 | 2021-03-09 | 2023-05-27 | 2023-07-25
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0086 | HRA - BUSHWICK JOB CENTER (FLSUHING) (LEASED IN) | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-10 | 2021-04-08 | 2023-07-26 | 2023-08-24
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0088 | DPR - McCARREN PARK RECREATION CENTER | 1 | DEVELOP SCOPE | 2020-02-15 | 2020-03-15 | 2022-06-01 | 2022-06-30
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0088 | DPR - McCARREN PARK RECREATION CENTER | 2 | BID AWARD AND REGISTER CONTRCT | 2020-03-16 | 2020-05-14 | 2022-07-01 | 2022-08-29
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0088 | DPR - McCARREN PARK RECREATION CENTER | 3 | CONSTRUCTION TO 50% | 2020-05-15 | 2020-11-10 | 2022-08-30 | 2023-02-25
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0088 | DPR - McCARREN PARK RECREATION CENTER | 4 | CONSTRUCTION TO 75% | 2020-11-11 | 2021-02-08 | 2023-02-26 | 2023-05-26
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0088 | DPR - McCARREN PARK RECREATION CENTER | 5 | SUBSTANTIAL COMPLETION | 2021-02-09 | 2021-04-09 | 2023-05-27 | 2023-07-25
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0088 | DPR - McCARREN PARK RECREATION CENTER | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-04-10 | 2021-05-09 | 2023-07-26 | 2023-08-24
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0096 | BPL - RED HOOK | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-06-30 | 2020-06-01 | 2020-06-30
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0096 | BPL - RED HOOK | 2 | BID AWARD AND REGISTER CONTRCT | 2020-07-01 | 2020-08-29 | 2020-07-01 | 2020-08-29
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0096 | BPL - RED HOOK | 3 | CONSTRUCTION TO 50% | 2020-08-30 | 2021-02-25 | 2020-08-30 | 2021-02-25
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0096 | BPL - RED HOOK | 4 | CONSTRUCTION TO 75% | 2021-02-26 | 2021-05-26 | 2021-02-26 | 2021-05-26
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0096 | BPL - RED HOOK | 5 | SUBSTANTIAL COMPLETION | 2021-05-27 | 2021-07-25 | 2021-05-27 | 2021-07-25
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0096 | BPL - RED HOOK | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-07-26 | 2021-08-24 | 2021-07-26 | 2021-08-24
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79540K | RELOCATION FROM 540 KINGSLAND AVE | 1 | DEVELOP SCOPE | 2019-01-19 | 2019-04-18 | 2019-01-19 | 2019-04-18
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79540K | RELOCATION FROM 540 KINGSLAND AVE | 2 | PRELIMINARY DESIGN | 2019-04-19 | 2019-08-16 | 2019-04-19 | 2019-08-16
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79540K | RELOCATION FROM 540 KINGSLAND AVE | 3 | FINAL DESIGN | 2019-08-17 | 2020-02-12 | 2019-08-17 | 2020-02-12
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79540K | RELOCATION FROM 540 KINGSLAND AVE | 4 | BID AWARD AND REGISTER CONTRCT | 2020-02-13 | 2020-05-12 | 2020-02-13 | 2020-05-12
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79540K | RELOCATION FROM 540 KINGSLAND AVE | 5 | CONSTRUCTION TO 25% | 2020-05-13 | 2020-09-09 | 2020-05-13 | 2020-09-09
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79540K | RELOCATION FROM 540 KINGSLAND AVE | 6 | CONSTRUCTION TO 50% | 2020-09-10 | 2021-01-07 | 2020-09-10 | 2021-01-07
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79540K | RELOCATION FROM 540 KINGSLAND AVE | 7 | CONSTRUCTION TO 75% | 2021-01-08 | 2021-05-07 | 2021-01-08 | 2021-05-07
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79540K | RELOCATION FROM 540 KINGSLAND AVE | 8 | ORIGINAL EQUIP & FURNISHING | 2021-05-08 | 2021-08-05 | 2021-05-08 | 2021-08-05
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79540K | RELOCATION FROM 540 KINGSLAND AVE | 9 | SUBSTANTIAL COMPLETION | 2021-08-06 | 2021-10-04 | 2021-08-06 | 2021-10-04
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79540K | RELOCATION FROM 540 KINGSLAND AVE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-10-05 | 2021-11-03 | 2021-10-05 | 2021-11-03
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW291EV | 209 JORALEMON ST.- ELEVATOR UPGRADE | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-08-29 | 2020-06-01 | 2020-08-29
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW291EV | 209 JORALEMON ST.- ELEVATOR UPGRADE | 2 | PRELIMINARY DESIGN | 2020-08-30 | 2020-12-27 | 2020-08-30 | 2020-12-27
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW291EV | 209 JORALEMON ST.- ELEVATOR UPGRADE | 3 | FINAL DESIGN | 2020-12-28 | 2021-06-25 | 2020-12-28 | 2021-06-25
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW291EV | 209 JORALEMON ST.- ELEVATOR UPGRADE | 4 | BID AWARD AND REGISTER CONTRCT | 2021-06-26 | 2021-09-23 | 2021-06-26 | 2021-09-23
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW291EV | 209 JORALEMON ST.- ELEVATOR UPGRADE | 5 | CONSTRUCTION TO 25% | 2022-06-01 | 2022-09-28 | 2022-06-01 | 2022-09-28
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW291EV | 209 JORALEMON ST.- ELEVATOR UPGRADE | 6 | CONSTRUCTION TO 50% | 2022-09-29 | 2023-01-26 | 2022-09-29 | 2023-01-26
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW291EV | 209 JORALEMON ST.- ELEVATOR UPGRADE | 7 | CONSTRUCTION TO 75% | 2023-01-27 | 2023-05-26 | 2023-01-27 | 2023-05-26
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW291EV | 209 JORALEMON ST.- ELEVATOR UPGRADE | 8 | ORIGINAL EQUIP & FURNISHING | 2023-05-27 | 2023-08-24 | 2023-05-27 | 2023-08-24
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW291EV | 209 JORALEMON ST.- ELEVATOR UPGRADE | 9 | SUBSTANTIAL COMPLETION | 2023-08-25 | 2023-10-23 | 2023-08-25 | 2023-10-23
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW291EV | 209 JORALEMON ST.- ELEVATOR UPGRADE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-10-24 | 2023-11-22 | 2023-10-24 | 2023-11-22
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW322PLAN | 345 ADAMS RESTACKING PLAN | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-08-29 | 2020-06-01 | 2020-08-29
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW322PLAN | 345 ADAMS RESTACKING PLAN | 2 | PRELIMINARY DESIGN | 2020-08-30 | 2020-12-27 | 2020-08-30 | 2020-12-27
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW322PLAN | 345 ADAMS RESTACKING PLAN | 3 | FINAL DESIGN | 2020-12-28 | 2021-06-25 | 2020-12-28 | 2021-06-25
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW322PLAN | 345 ADAMS RESTACKING PLAN | 4 | BID AWARD AND REGISTER CONTRCT | 2021-06-26 | 2021-09-23 | 2021-06-26 | 2021-09-23
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW322PLAN | 345 ADAMS RESTACKING PLAN | 5 | CONSTRUCTION TO 25% | 2021-09-24 | 2022-01-21 | 2021-09-24 | 2022-01-21
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW322PLAN | 345 ADAMS RESTACKING PLAN | 6 | CONSTRUCTION TO 50% | 2022-01-22 | 2022-05-21 | 2022-01-22 | 2022-05-21
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW322PLAN | 345 ADAMS RESTACKING PLAN | 7 | CONSTRUCTION TO 75% | 2022-05-22 | 2022-09-18 | 2022-05-22 | 2022-09-18
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW322PLAN | 345 ADAMS RESTACKING PLAN | 8 | ORIGINAL EQUIP & FURNISHING | 2022-09-19 | 2022-12-17 | 2022-09-19 | 2022-12-17
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW322PLAN | 345 ADAMS RESTACKING PLAN | 9 | SUBSTANTIAL COMPLETION | 2022-12-18 | 2023-02-15 | 2022-12-18 | 2023-02-15
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW322PLAN | 345 ADAMS RESTACKING PLAN | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-02-16 | 2023-03-17 | 2023-02-16 | 2023-03-17
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW325ELC3 | 210 JORALEMON ST. ELECTRICAL UPGRADE AND EMERGENCY GENERATOR | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-08-29 | 2020-06-01 | 2020-08-29
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW325ELC3 | 210 JORALEMON ST. ELECTRICAL UPGRADE AND EMERGENCY GENERATOR | 2 | PRELIMINARY DESIGN | 2020-08-30 | 2020-12-27 | 2020-08-30 | 2020-12-27
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW325ELC3 | 210 JORALEMON ST. ELECTRICAL UPGRADE AND EMERGENCY GENERATOR | 3 | FINAL DESIGN | 2020-12-28 | 2021-06-25 | 2020-12-28 | 2021-06-25
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW325ELC3 | 210 JORALEMON ST. ELECTRICAL UPGRADE AND EMERGENCY GENERATOR | 4 | BID AWARD AND REGISTER CONTRCT | 2021-06-26 | 2021-09-23 | 2021-06-26 | 2021-09-23
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW325ELC3 | 210 JORALEMON ST. ELECTRICAL UPGRADE AND EMERGENCY GENERATOR | 5 | CONSTRUCTION TO 25% | 2021-09-24 | 2022-01-21 | 2021-09-24 | 2022-01-21
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW325ELC3 | 210 JORALEMON ST. ELECTRICAL UPGRADE AND EMERGENCY GENERATOR | 6 | CONSTRUCTION TO 50% | 2022-01-22 | 2022-05-21 | 2022-01-22 | 2022-05-21
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW325ELC3 | 210 JORALEMON ST. ELECTRICAL UPGRADE AND EMERGENCY GENERATOR | 7 | CONSTRUCTION TO 75% | 2022-05-22 | 2022-09-18 | 2022-05-22 | 2022-09-18
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW325ELC3 | 210 JORALEMON ST. ELECTRICAL UPGRADE AND EMERGENCY GENERATOR | 8 | ORIGINAL EQUIP & FURNISHING | 2022-09-19 | 2022-12-17 | 2022-09-19 | 2022-12-17
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW325ELC3 | 210 JORALEMON ST. ELECTRICAL UPGRADE AND EMERGENCY GENERATOR | 9 | SUBSTANTIAL COMPLETION | 2022-12-18 | 2023-02-15 | 2022-12-18 | 2023-02-15
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW325ELC3 | 210 JORALEMON ST. ELECTRICAL UPGRADE AND EMERGENCY GENERATOR | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-02-16 | 2023-03-17 | 2023-02-16 | 2023-03-17
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW325STA3 | 210 JORALEMON STREET STABILIZATION | 1 | DEVELOP SCOPE | 2019-06-01 | 2019-08-29 | 2019-06-01 | 2019-08-29
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW325STA3 | 210 JORALEMON STREET STABILIZATION | 2 | PRELIMINARY DESIGN | 2019-08-30 | 2019-12-27 | 2019-08-30 | 2019-12-27
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW325STA3 | 210 JORALEMON STREET STABILIZATION | 3 | FINAL DESIGN | 2019-12-28 | 2020-06-24 | 2019-12-28 | 2020-06-24
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW325STA3 | 210 JORALEMON STREET STABILIZATION | 4 | BID AWARD AND REGISTER CONTRCT | 2020-06-25 | 2020-09-22 | 2020-06-25 | 2020-09-22
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW325STA3 | 210 JORALEMON STREET STABILIZATION | 5 | CONSTRUCTION TO 25% | 2020-09-23 | 2021-01-20 | 2020-09-23 | 2021-01-20
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW325STA3 | 210 JORALEMON STREET STABILIZATION | 6 | CONSTRUCTION TO 50% | 2021-01-21 | 2021-05-20 | 2021-01-21 | 2021-05-20
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW325STA3 | 210 JORALEMON STREET STABILIZATION | 7 | CONSTRUCTION TO 75% | 2021-05-21 | 2021-09-17 | 2021-05-21 | 2021-09-17
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW325STA3 | 210 JORALEMON STREET STABILIZATION | 8 | ORIGINAL EQUIP & FURNISHING | 2021-09-18 | 2021-12-16 | 2021-09-18 | 2021-12-16
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW325STA3 | 210 JORALEMON STREET STABILIZATION | 9 | SUBSTANTIAL COMPLETION | 2021-12-17 | 2022-02-14 | 2021-12-17 | 2022-02-14
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW325STA3 | 210 JORALEMON STREET STABILIZATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-02-15 | 2022-03-16 | 2022-02-15 | 2022-03-16
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DCPK | DCP - 16 COURT ST RENOVATION | 1 | DEVELOP SCOPE | 2020-01-15 | 2020-05-13 | 2020-06-01 | 2020-08-29
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DCPK | DCP - 16 COURT ST RENOVATION | 2 | BID AWARD AND REGISTER CONTRCT | 2020-05-14 | 2020-11-09 | 2020-08-30 | 2020-12-27
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DCPK | DCP - 16 COURT ST RENOVATION | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-11-10 | 2022-06-30 | 2020-12-28 | 2021-06-25
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DCPK | DCP - 16 COURT ST RENOVATION | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-07-31 | 2022-08-29 | 2021-06-26 | 2021-09-23
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DCPK | DCP - 16 COURT ST RENOVATION | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-07-01 | 2022-07-30 | 2021-09-24 | 2022-01-21
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DCPK | DCP - 16 COURT ST RENOVATION | 6 | CONSTRUCTION TO 50% | 2022-07-01 | 2022-07-30 | 2022-01-22 | 2022-05-21
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DCPK | DCP - 16 COURT ST RENOVATION | 7 | CONSTRUCTION TO 75% | 2022-07-01 | 2022-07-30 | 2022-05-22 | 2022-09-18
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DCPK | DCP - 16 COURT ST RENOVATION | 8 | ORIGINAL EQUIP & FURNISHING | 2022-07-01 | 2022-07-30 | 2022-09-19 | 2022-12-17
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DCPK | DCP - 16 COURT ST RENOVATION | 9 | SUBSTANTIAL COMPLETION | 2022-07-01 | 2022-07-30 | 2022-12-18 | 2023-02-15
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DCPK | DCP - 16 COURT ST RENOVATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-07-01 | 2022-07-30 | 2023-02-16 | 2023-03-17
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326LAW7 | LAW - 167 41ST - LAW DEPT CONSOLIDATION | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-09-28 | 2020-06-01 | 2020-08-29
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326LAW7 | LAW - 167 41ST - LAW DEPT CONSOLIDATION | 2 | BID AWARD AND REGISTER CONTRCT | 2020-09-29 | 2021-03-27 | 2020-08-30 | 2020-12-27
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326LAW7 | LAW - 167 41ST - LAW DEPT CONSOLIDATION | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-28 | 2022-06-30 | 2020-12-28 | 2021-06-25
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326LAW7 | LAW - 167 41ST - LAW DEPT CONSOLIDATION | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-07-31 | 2022-08-29 | 2021-06-26 | 2021-09-23
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326LAW7 | LAW - 167 41ST - LAW DEPT CONSOLIDATION | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-07-01 | 2022-07-30 | 2021-09-24 | 2022-01-21
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326LAW7 | LAW - 167 41ST - LAW DEPT CONSOLIDATION | 6 | CONSTRUCTION TO 50% | 2022-07-01 | 2022-07-30 | 2022-01-22 | 2022-05-21
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326LAW7 | LAW - 167 41ST - LAW DEPT CONSOLIDATION | 7 | CONSTRUCTION TO 75% | 2022-07-01 | 2022-07-30 | 2022-05-22 | 2022-09-18
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326LAW7 | LAW - 167 41ST - LAW DEPT CONSOLIDATION | 8 | ORIGINAL EQUIP & FURNISHING | 2022-07-01 | 2022-07-30 | 2022-09-19 | 2022-12-17
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326LAW7 | LAW - 167 41ST - LAW DEPT CONSOLIDATION | 9 | SUBSTANTIAL COMPLETION | 2022-07-01 | 2022-07-30 | 2022-12-18 | 2023-02-15
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326LAW7 | LAW - 167 41ST - LAW DEPT CONSOLIDATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-07-01 | 2022-07-30 | 2023-02-16 | 2023-03-17
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326OEM3 | OEM Expansion of Leased Space 930 Flushing Avenue | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-08-29 | 2023-06-01 | 2023-08-29
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326OEM3 | OEM Expansion of Leased Space 930 Flushing Avenue | 2 | PRELIMINARY DESIGN | 2020-08-30 | 2020-12-27 | 2023-08-30 | 2023-12-27
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326OEM3 | OEM Expansion of Leased Space 930 Flushing Avenue | 3 | FINAL DESIGN | 2020-12-28 | 2021-06-25 | 2023-12-28 | 2024-06-24
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326OEM3 | OEM Expansion of Leased Space 930 Flushing Avenue | 4 | BID AWARD AND REGISTER CONTRCT | 2021-06-26 | 2021-09-23 | 2024-06-25 | 2024-09-22
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326OEM3 | OEM Expansion of Leased Space 930 Flushing Avenue | 5 | CONSTRUCTION TO 25% | 2021-09-24 | 2022-01-21 | 2024-09-23 | 2025-01-20
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326OEM3 | OEM Expansion of Leased Space 930 Flushing Avenue | 6 | CONSTRUCTION TO 50% | 2022-01-22 | 2022-05-21 | 2025-01-21 | 2025-05-20
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326OEM3 | OEM Expansion of Leased Space 930 Flushing Avenue | 7 | CONSTRUCTION TO 75% | 2022-05-22 | 2022-09-18 | 2025-05-21 | 2025-09-17
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326OEM3 | OEM Expansion of Leased Space 930 Flushing Avenue | 8 | ORIGINAL EQUIP & FURNISHING | 2022-09-19 | 2022-12-17 | 2025-09-18 | 2025-12-16
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326OEM3 | OEM Expansion of Leased Space 930 Flushing Avenue | 9 | SUBSTANTIAL COMPLETION | 2022-12-18 | 2023-02-15 | 2025-12-17 | 2026-02-14
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326OEM3 | OEM Expansion of Leased Space 930 Flushing Avenue | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-02-16 | 2023-03-17 | 2026-02-15 | 2026-03-16
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RAK | LAW DEPT - RAISE THE AGE - BROOKLYN | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-08-29 | 2020-06-01 | 2020-08-29
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RAK | LAW DEPT - RAISE THE AGE - BROOKLYN | 2 | PRELIMINARY DESIGN | 2020-08-30 | 2020-12-27 | 2020-08-30 | 2020-12-27
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RAK | LAW DEPT - RAISE THE AGE - BROOKLYN | 3 | FINAL DESIGN | 2020-12-28 | 2021-06-25 | 2020-12-28 | 2021-06-25
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RAK | LAW DEPT - RAISE THE AGE - BROOKLYN | 4 | BID AWARD AND REGISTER CONTRCT | 2021-06-26 | 2021-09-23 | 2021-06-26 | 2021-09-23
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RAK | LAW DEPT - RAISE THE AGE - BROOKLYN | 5 | CONSTRUCTION TO 25% | 2021-09-24 | 2022-01-21 | 2021-09-24 | 2022-01-21
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RAK | LAW DEPT - RAISE THE AGE - BROOKLYN | 6 | CONSTRUCTION TO 50% | 2022-01-22 | 2022-05-21 | 2022-01-22 | 2022-05-21
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RAK | LAW DEPT - RAISE THE AGE - BROOKLYN | 7 | CONSTRUCTION TO 75% | 2022-05-22 | 2022-09-18 | 2022-05-22 | 2022-09-18
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RAK | LAW DEPT - RAISE THE AGE - BROOKLYN | 8 | ORIGINAL EQUIP & FURNISHING | 2022-09-19 | 2022-12-17 | 2022-09-19 | 2022-12-17
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RAK | LAW DEPT - RAISE THE AGE - BROOKLYN | 9 | SUBSTANTIAL COMPLETION | 2022-12-18 | 2023-02-15 | 2022-12-18 | 2023-02-15
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RAK | LAW DEPT - RAISE THE AGE - BROOKLYN | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-02-16 | 2023-03-17 | 2023-02-16 | 2023-03-17
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW340BOE | BOE - 345 ADAMS ST.- BATHROOMS RENOVATION | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-08-29 | 2020-06-01 | 2020-08-29
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW340BOE | BOE - 345 ADAMS ST.- BATHROOMS RENOVATION | 2 | PRELIMINARY DESIGN | 2020-08-30 | 2020-12-27 | 2020-08-30 | 2020-12-27
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW340BOE | BOE - 345 ADAMS ST.- BATHROOMS RENOVATION | 3 | FINAL DESIGN | 2020-12-28 | 2021-06-25 | 2020-12-28 | 2021-06-25
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW340BOE | BOE - 345 ADAMS ST.- BATHROOMS RENOVATION | 4 | BID AWARD AND REGISTER CONTRCT | 2021-06-26 | 2021-09-23 | 2021-06-26 | 2021-09-23
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW340BOE | BOE - 345 ADAMS ST.- BATHROOMS RENOVATION | 5 | CONSTRUCTION TO 25% | 2021-09-24 | 2022-01-21 | 2021-09-24 | 2022-01-21
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW340BOE | BOE - 345 ADAMS ST.- BATHROOMS RENOVATION | 6 | CONSTRUCTION TO 50% | 2022-01-22 | 2022-05-21 | 2022-01-22 | 2022-05-21
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW340BOE | BOE - 345 ADAMS ST.- BATHROOMS RENOVATION | 7 | CONSTRUCTION TO 75% | 2022-05-22 | 2022-09-18 | 2022-05-22 | 2022-09-18
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW340BOE | BOE - 345 ADAMS ST.- BATHROOMS RENOVATION | 8 | ORIGINAL EQUIP & FURNISHING | 2022-09-19 | 2022-12-17 | 2022-09-19 | 2022-12-17
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW340BOE | BOE - 345 ADAMS ST.- BATHROOMS RENOVATION | 9 | SUBSTANTIAL COMPLETION | 2022-12-18 | 2023-02-15 | 2022-12-18 | 2023-02-15
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW340BOE | BOE - 345 ADAMS ST.- BATHROOMS RENOVATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-02-16 | 2023-03-17 | 2023-02-16 | 2023-03-17
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW340KEXP | BOE - 5112 2nd AVE, BROOKLYN EXPANSION | 1 | DEVELOP SCOPE | 2021-06-01 | 2021-08-29 | 2021-06-01 | 2021-08-29
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW340KEXP | BOE - 5112 2nd AVE, BROOKLYN EXPANSION | 2 | PRELIMINARY DESIGN | 2021-08-30 | 2021-12-27 | 2021-08-30 | 2021-12-27
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW340KEXP | BOE - 5112 2nd AVE, BROOKLYN EXPANSION | 3 | FINAL DESIGN | 2021-12-28 | 2022-06-25 | 2021-12-28 | 2022-06-25
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW340KEXP | BOE - 5112 2nd AVE, BROOKLYN EXPANSION | 4 | BID AWARD AND REGISTER CONTRCT | 2022-06-26 | 2022-09-23 | 2022-06-26 | 2022-09-23
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW340KEXP | BOE - 5112 2nd AVE, BROOKLYN EXPANSION | 5 | CONSTRUCTION TO 25% | 2022-09-24 | 2023-01-21 | 2022-09-24 | 2023-01-21
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW340KEXP | BOE - 5112 2nd AVE, BROOKLYN EXPANSION | 6 | CONSTRUCTION TO 50% | 2023-01-22 | 2023-05-21 | 2023-01-22 | 2023-05-21
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW340KEXP | BOE - 5112 2nd AVE, BROOKLYN EXPANSION | 7 | CONSTRUCTION TO 75% | 2023-05-22 | 2023-09-18 | 2023-05-22 | 2023-09-18
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW340KEXP | BOE - 5112 2nd AVE, BROOKLYN EXPANSION | 8 | ORIGINAL EQUIP & FURNISHING | 2023-09-19 | 2023-12-17 | 2023-09-19 | 2023-12-17
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW340KEXP | BOE - 5112 2nd AVE, BROOKLYN EXPANSION | 9 | SUBSTANTIAL COMPLETION | 2023-12-18 | 2024-02-15 | 2023-12-18 | 2024-02-15
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW340KEXP | BOE - 5112 2nd AVE, BROOKLYN EXPANSION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-02-16 | 2024-03-16 | 2024-02-16 | 2024-03-16
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77BHCAM | 209 JORALEMON STREET - CCTV | 1 | DEVELOP SCOPE | 2019-06-01 | 2019-08-29 | 2019-06-01 | 2019-08-29
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77BHCAM | 209 JORALEMON STREET - CCTV | 2 | PRELIMINARY DESIGN | 2019-08-30 | 2019-12-27 | 2019-08-30 | 2019-12-27
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77BHCAM | 209 JORALEMON STREET - CCTV | 3 | FINAL DESIGN | 2019-12-28 | 2020-06-24 | 2019-12-28 | 2020-06-24
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77BHCAM | 209 JORALEMON STREET - CCTV | 4 | BID AWARD AND REGISTER CONTRCT | 2020-06-25 | 2020-09-22 | 2020-06-25 | 2020-09-22
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77BHCAM | 209 JORALEMON STREET - CCTV | 5 | CONSTRUCTION TO 25% | 2020-09-23 | 2021-01-20 | 2020-09-23 | 2021-01-20
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77BHCAM | 209 JORALEMON STREET - CCTV | 6 | CONSTRUCTION TO 50% | 2021-01-21 | 2021-05-20 | 2021-01-21 | 2021-05-20
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77BHCAM | 209 JORALEMON STREET - CCTV | 7 | CONSTRUCTION TO 75% | 2021-05-21 | 2021-09-17 | 2021-05-21 | 2021-09-17
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77BHCAM | 209 JORALEMON STREET - CCTV | 8 | ORIGINAL EQUIP & FURNISHING | 2021-09-18 | 2021-12-16 | 2021-09-18 | 2021-12-16
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77BHCAM | 209 JORALEMON STREET - CCTV | 9 | SUBSTANTIAL COMPLETION | 2021-12-17 | 2022-02-14 | 2021-12-17 | 2022-02-14
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77BHCAM | 209 JORALEMON STREET - CCTV | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-02-15 | 2022-03-16 | 2022-02-15 | 2022-03-16
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77ZK07 | BROOKLYN COMMUNITY BOARD 7- 4201 4TH AVENUE | 1 | DEVELOP SCOPE | 2016-05-15 | 2016-08-12 | 2022-06-01 | 2022-08-29
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77ZK07 | BROOKLYN COMMUNITY BOARD 7- 4201 4TH AVENUE | 2 | PRELIMINARY DESIGN | 2016-08-13 | 2016-12-10 | 2022-08-30 | 2022-12-27
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77ZK07 | BROOKLYN COMMUNITY BOARD 7- 4201 4TH AVENUE | 3 | FINAL DESIGN | 2016-12-11 | 2017-06-08 | 2022-12-28 | 2023-06-25
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77ZK07 | BROOKLYN COMMUNITY BOARD 7- 4201 4TH AVENUE | 4 | BID AWARD AND REGISTER CONTRCT | 2017-06-09 | 2017-09-06 | 2024-06-09 | 2024-09-06
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77ZK07 | BROOKLYN COMMUNITY BOARD 7- 4201 4TH AVENUE | 5 | CONSTRUCTION TO 25% | 2017-09-07 | 2018-01-04 | 2024-09-07 | 2025-01-04
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77ZK07 | BROOKLYN COMMUNITY BOARD 7- 4201 4TH AVENUE | 6 | CONSTRUCTION TO 50% | 2018-01-05 | 2018-05-04 | 2025-01-05 | 2025-05-04
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77ZK07 | BROOKLYN COMMUNITY BOARD 7- 4201 4TH AVENUE | 7 | CONSTRUCTION TO 75% | 2018-05-05 | 2018-09-01 | 2025-05-05 | 2025-09-01
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77ZK07 | BROOKLYN COMMUNITY BOARD 7- 4201 4TH AVENUE | 8 | ORIGINAL EQUIP & FURNISHING | 2018-09-02 | 2018-11-30 | 2025-09-02 | 2025-11-30
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77ZK07 | BROOKLYN COMMUNITY BOARD 7- 4201 4TH AVENUE | 9 | SUBSTANTIAL COMPLETION | 2018-12-01 | 2019-01-29 | 2025-12-01 | 2026-01-29
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77ZK07 | BROOKLYN COMMUNITY BOARD 7- 4201 4TH AVENUE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-01-30 | 2019-02-28 | 2026-01-30 | 2026-02-28
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD007HPD | HPD - CONSTRUCTION AND RENOVATION OF NORTHSIDE TOWN HALL | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-08-29 | 2022-06-01 | 2022-08-29
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD007HPD | HPD - CONSTRUCTION AND RENOVATION OF NORTHSIDE TOWN HALL | 2 | PRELIMINARY DESIGN | 2020-08-30 | 2020-12-27 | 2022-08-30 | 2022-12-27
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD007HPD | HPD - CONSTRUCTION AND RENOVATION OF NORTHSIDE TOWN HALL | 3 | FINAL DESIGN | 2020-12-28 | 2021-06-25 | 2022-12-28 | 2023-06-25
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD007HPD | HPD - CONSTRUCTION AND RENOVATION OF NORTHSIDE TOWN HALL | 4 | BID AWARD AND REGISTER CONTRCT | 2021-06-26 | 2021-09-23 | 2023-06-26 | 2023-09-23
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD007HPD | HPD - CONSTRUCTION AND RENOVATION OF NORTHSIDE TOWN HALL | 5 | CONSTRUCTION TO 25% | 2021-09-24 | 2022-01-21 | 2023-09-24 | 2024-01-21
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD007HPD | HPD - CONSTRUCTION AND RENOVATION OF NORTHSIDE TOWN HALL | 6 | CONSTRUCTION TO 50% | 2022-01-22 | 2022-05-21 | 2024-01-22 | 2024-05-20
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD007HPD | HPD - CONSTRUCTION AND RENOVATION OF NORTHSIDE TOWN HALL | 7 | CONSTRUCTION TO 75% | 2022-05-22 | 2022-09-18 | 2024-05-21 | 2024-09-17
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD007HPD | HPD - CONSTRUCTION AND RENOVATION OF NORTHSIDE TOWN HALL | 8 | ORIGINAL EQUIP & FURNISHING | 2022-09-19 | 2022-12-17 | 2024-09-18 | 2024-12-16
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD007HPD | HPD - CONSTRUCTION AND RENOVATION OF NORTHSIDE TOWN HALL | 9 | SUBSTANTIAL COMPLETION | 2022-12-18 | 2023-02-15 | 2024-12-17 | 2025-02-14
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD007HPD | HPD - CONSTRUCTION AND RENOVATION OF NORTHSIDE TOWN HALL | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-02-16 | 2023-03-17 | 2025-02-15 | 2025-03-16
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD30BENC | BENJAMIN BANNEKER ACADEMY FOR COMMUNITY DEVELOPMENT | 1 | PROJECT START | 2018-03-16 | 2018-03-16 | 2018-03-16 | 2018-03-16
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD30BENC | BENJAMIN BANNEKER ACADEMY FOR COMMUNITY DEVELOPMENT | 2 | DESIGN START | 2018-03-17 | 2018-03-17 | 2018-03-17 | 2019-03-17
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD30BENC | BENJAMIN BANNEKER ACADEMY FOR COMMUNITY DEVELOPMENT | 3 | DESIGN COMPLETION | 2018-03-18 | 2018-09-18 | 2019-03-18 | 2019-12-18
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD30BENC | BENJAMIN BANNEKER ACADEMY FOR COMMUNITY DEVELOPMENT | 4 | CONSTRUCTION START | 2018-09-19 | 2019-03-19 | 2019-12-19 | 2020-06-17
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD30BENC | BENJAMIN BANNEKER ACADEMY FOR COMMUNITY DEVELOPMENT | 5 | CONSTRUCTION COMPLETION | 2019-03-20 | 2019-09-20 | 2020-06-18 | 2021-07-05
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD78BLL | 360 ADAMS STREET- BROOKLYN SUPREME COURT LAW LIBRARY | 1 | DEVELOP SCOPE | 2024-06-01 | 2024-08-29 | 2024-06-01 | 2024-08-29
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD78BLL | 360 ADAMS STREET- BROOKLYN SUPREME COURT LAW LIBRARY | 2 | PRELIMINARY DESIGN | 2024-08-30 | 2024-12-27 | 2024-08-30 | 2024-12-27
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD78BLL | 360 ADAMS STREET- BROOKLYN SUPREME COURT LAW LIBRARY | 3 | FINAL DESIGN | 2024-12-28 | 2025-06-25 | 2024-12-28 | 2025-06-25
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD78BLL | 360 ADAMS STREET- BROOKLYN SUPREME COURT LAW LIBRARY | 4 | BID AWARD AND REGISTER CONTRCT | 2025-06-26 | 2025-09-23 | 2025-06-26 | 2025-09-23
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD78BLL | 360 ADAMS STREET- BROOKLYN SUPREME COURT LAW LIBRARY | 5 | CONSTRUCTION TO 25% | 2025-09-24 | 2026-01-21 | 2025-09-24 | 2026-01-21
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD78BLL | 360 ADAMS STREET- BROOKLYN SUPREME COURT LAW LIBRARY | 6 | CONSTRUCTION TO 50% | 2026-01-22 | 2026-05-21 | 2026-01-22 | 2026-05-21
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD78BLL | 360 ADAMS STREET- BROOKLYN SUPREME COURT LAW LIBRARY | 7 | CONSTRUCTION TO 75% | 2026-05-22 | 2026-09-18 | 2026-05-22 | 2026-09-18
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD78BLL | 360 ADAMS STREET- BROOKLYN SUPREME COURT LAW LIBRARY | 8 | ORIGINAL EQUIP & FURNISHING | 2026-09-19 | 2026-12-17 | 2026-09-19 | 2026-12-17
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD78BLL | 360 ADAMS STREET- BROOKLYN SUPREME COURT LAW LIBRARY | 9 | SUBSTANTIAL COMPLETION | 2026-12-18 | 2027-02-15 | 2026-12-18 | 2027-02-15
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD78BLL | 360 ADAMS STREET- BROOKLYN SUPREME COURT LAW LIBRARY | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2027-02-16 | 2027-03-17 | 2027-02-16 | 2027-03-17
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD78SSCT | 360 ADAMS ST.- HVAC STATE SUPREME COURT | 1 | DEVELOP SCOPE | 2013-04-01 | 2013-06-29 | 2026-06-01 | 2026-08-29
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD78SSCT | 360 ADAMS ST.- HVAC STATE SUPREME COURT | 2 | PRELIMINARY DESIGN | 2013-06-30 | 2013-10-27 | 2026-08-30 | 2026-12-27
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD78SSCT | 360 ADAMS ST.- HVAC STATE SUPREME COURT | 3 | FINAL DESIGN | 2013-10-28 | 2014-04-25 | 2026-12-28 | 2027-06-25
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD78SSCT | 360 ADAMS ST.- HVAC STATE SUPREME COURT | 4 | BID AWARD AND REGISTER CONTRCT | 2014-04-26 | 2014-07-24 | 2027-06-26 | 2027-09-23
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD78SSCT | 360 ADAMS ST.- HVAC STATE SUPREME COURT | 5 | CONSTRUCTION TO 25% | 2014-07-25 | 2014-11-21 | 2027-09-24 | 2028-01-21
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD78SSCT | 360 ADAMS ST.- HVAC STATE SUPREME COURT | 6 | CONSTRUCTION TO 50% | 2014-11-22 | 2015-03-21 | 2028-01-22 | 2028-05-20
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD78SSCT | 360 ADAMS ST.- HVAC STATE SUPREME COURT | 7 | CONSTRUCTION TO 75% | 2015-03-22 | 2015-07-19 | 2028-05-21 | 2028-09-17
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD78SSCT | 360 ADAMS ST.- HVAC STATE SUPREME COURT | 8 | ORIGINAL EQUIP & FURNISHING | 2015-07-20 | 2015-10-17 | 2028-09-18 | 2028-12-16
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD78SSCT | 360 ADAMS ST.- HVAC STATE SUPREME COURT | 9 | SUBSTANTIAL COMPLETION | 2015-10-18 | 2015-12-16 | 2028-12-17 | 2029-02-14
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD78SSCT | 360 ADAMS ST.- HVAC STATE SUPREME COURT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-12-17 | 2016-01-15 | 2029-02-15 | 2029-03-16
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWK2LEED | Brooklyn Borough Hall - LEED- Funding for LEED | 1 | DEVELOP SCOPE | 2021-06-01 | 2021-08-29 | 2021-06-01 | 2021-08-29
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWK2LEED | Brooklyn Borough Hall - LEED- Funding for LEED | 2 | PRELIMINARY DESIGN | 2021-08-30 | 2021-12-27 | 2021-08-30 | 2021-12-27
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWK2LEED | Brooklyn Borough Hall - LEED- Funding for LEED | 3 | FINAL DESIGN | 2021-12-28 | 2022-06-25 | 2021-12-28 | 2022-06-25
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWK2LEED | Brooklyn Borough Hall - LEED- Funding for LEED | 4 | BID AWARD AND REGISTER CONTRCT | 2022-06-26 | 2022-09-23 | 2022-06-26 | 2022-09-23
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWK2LEED | Brooklyn Borough Hall - LEED- Funding for LEED | 5 | CONSTRUCTION TO 25% | 2022-09-24 | 2023-01-21 | 2022-09-24 | 2023-01-21
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWK2LEED | Brooklyn Borough Hall - LEED- Funding for LEED | 6 | CONSTRUCTION TO 50% | 2023-01-22 | 2023-05-21 | 2023-01-22 | 2023-05-21
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWK2LEED | Brooklyn Borough Hall - LEED- Funding for LEED | 7 | CONSTRUCTION TO 75% | 2023-05-22 | 2023-09-18 | 2023-05-22 | 2023-09-18
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWK2LEED | Brooklyn Borough Hall - LEED- Funding for LEED | 8 | ORIGINAL EQUIP & FURNISHING | 2023-09-19 | 2023-12-17 | 2023-09-19 | 2023-12-17
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWK2LEED | Brooklyn Borough Hall - LEED- Funding for LEED | 9 | SUBSTANTIAL COMPLETION | 2023-12-18 | 2024-02-15 | 2023-12-18 | 2024-02-15
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWK2LEED | Brooklyn Borough Hall - LEED- Funding for LEED | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-02-16 | 2024-03-16 | 2024-02-16 | 2024-03-16
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWK2MEDIA | 209 JORALEMON ST.- BKLYN BORO HALL MEDIA ROOM | 1 | DEVELOP SCOPE | 2009-01-01 | 2009-03-31 | 2023-06-01 | 2023-08-29
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWK2MEDIA | 209 JORALEMON ST.- BKLYN BORO HALL MEDIA ROOM | 2 | PRELIMINARY DESIGN | 2009-04-01 | 2009-07-29 | 2023-08-30 | 2023-12-27
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWK2MEDIA | 209 JORALEMON ST.- BKLYN BORO HALL MEDIA ROOM | 3 | FINAL DESIGN | 2009-07-30 | 2010-01-25 | 2023-12-28 | 2024-06-24
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWK2MEDIA | 209 JORALEMON ST.- BKLYN BORO HALL MEDIA ROOM | 4 | BID AWARD AND REGISTER CONTRCT | 2010-01-26 | 2010-04-25 | 2024-06-25 | 2024-09-22
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWK2MEDIA | 209 JORALEMON ST.- BKLYN BORO HALL MEDIA ROOM | 5 | CONSTRUCTION TO 25% | 2010-04-26 | 2010-08-23 | 2024-09-23 | 2025-09-17
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWK2MEDIA | 209 JORALEMON ST.- BKLYN BORO HALL MEDIA ROOM | 6 | CONSTRUCTION TO 50% | 2010-08-24 | 2010-12-21 | 2025-09-18 | 2026-09-12
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWK2MEDIA | 209 JORALEMON ST.- BKLYN BORO HALL MEDIA ROOM | 7 | CONSTRUCTION TO 75% | 2010-12-22 | 2011-04-20 | 2026-09-13 | 2027-09-07
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWK2MEDIA | 209 JORALEMON ST.- BKLYN BORO HALL MEDIA ROOM | 8 | ORIGINAL EQUIP & FURNISHING | 2011-04-21 | 2011-07-19 | 2027-09-08 | 2027-10-07
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWK2MEDIA | 209 JORALEMON ST.- BKLYN BORO HALL MEDIA ROOM | 9 | SUBSTANTIAL COMPLETION | 2011-07-20 | 2011-09-17 | 2027-10-08 | 2027-11-06
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWK2MEDIA | 209 JORALEMON ST.- BKLYN BORO HALL MEDIA ROOM | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2011-09-18 | 2011-10-17 | 2027-11-07 | 2027-11-21
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | RE25LL | LOTTS LANE REPAIRING | 1 | DEVELOP SCOPE | 2021-06-01 | 2021-08-29 | 2021-06-01 | 2021-08-29
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | RE25LL | LOTTS LANE REPAIRING | 2 | PRELIMINARY DESIGN | 2021-08-30 | 2021-12-27 | 2021-08-30 | 2021-12-27
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | RE25LL | LOTTS LANE REPAIRING | 3 | FINAL DESIGN | 2021-12-28 | 2022-06-25 | 2021-12-28 | 2022-06-25
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | RE25LL | LOTTS LANE REPAIRING | 4 | BID AWARD AND REGISTER CONTRCT | 2023-06-01 | 2023-08-29 | 2023-06-01 | 2023-08-29
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | RE25LL | LOTTS LANE REPAIRING | 5 | CONSTRUCTION TO 25% | 2023-08-30 | 2023-12-27 | 2023-08-30 | 2023-12-27
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | RE25LL | LOTTS LANE REPAIRING | 6 | CONSTRUCTION TO 50% | 2023-12-28 | 2024-04-25 | 2023-12-28 | 2024-04-25
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | RE25LL | LOTTS LANE REPAIRING | 7 | CONSTRUCTION TO 75% | 2024-04-26 | 2024-08-23 | 2024-04-26 | 2024-08-23
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | RE25LL | LOTTS LANE REPAIRING | 8 | ORIGINAL EQUIP & FURNISHING | 2024-08-24 | 2024-11-21 | 2024-08-24 | 2024-11-21
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | RE25LL | LOTTS LANE REPAIRING | 9 | SUBSTANTIAL COMPLETION | 2024-11-22 | 2025-01-20 | 2024-11-22 | 2025-01-20
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | RE25LL | LOTTS LANE REPAIRING | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-01-21 | 2025-02-19 | 2025-01-21 | 2025-02-19
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | RE25QR | QUENTIN ROAD BROOKLYN STREET RECONSTRUCTION | 1 | DEVELOP SCOPE | 2021-06-01 | 2021-08-29 | 2021-06-01 | 2021-08-29
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | RE25QR | QUENTIN ROAD BROOKLYN STREET RECONSTRUCTION | 2 | PRELIMINARY DESIGN | 2021-08-30 | 2021-12-27 | 2021-08-30 | 2021-12-27
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | RE25QR | QUENTIN ROAD BROOKLYN STREET RECONSTRUCTION | 3 | FINAL DESIGN | 2021-12-28 | 2022-06-25 | 2021-12-28 | 2022-06-25
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | RE25QR | QUENTIN ROAD BROOKLYN STREET RECONSTRUCTION | 4 | BID AWARD AND REGISTER CONTRCT | 2022-06-26 | 2022-09-23 | 2022-06-26 | 2022-09-23
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | RE25QR | QUENTIN ROAD BROOKLYN STREET RECONSTRUCTION | 5 | CONSTRUCTION TO 25% | 2023-06-01 | 2023-09-28 | 2023-06-01 | 2023-09-28
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | RE25QR | QUENTIN ROAD BROOKLYN STREET RECONSTRUCTION | 6 | CONSTRUCTION TO 50% | 2023-09-29 | 2024-01-26 | 2023-09-29 | 2024-01-26
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | RE25QR | QUENTIN ROAD BROOKLYN STREET RECONSTRUCTION | 7 | CONSTRUCTION TO 75% | 2024-01-27 | 2024-05-25 | 2024-01-27 | 2024-05-25
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | RE25QR | QUENTIN ROAD BROOKLYN STREET RECONSTRUCTION | 8 | ORIGINAL EQUIP & FURNISHING | 2024-05-26 | 2024-08-23 | 2024-05-26 | 2024-08-23
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | RE25QR | QUENTIN ROAD BROOKLYN STREET RECONSTRUCTION | 9 | SUBSTANTIAL COMPLETION | 2024-08-24 | 2024-10-22 | 2024-08-24 | 2024-10-22
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | RE25QR | QUENTIN ROAD BROOKLYN STREET RECONSTRUCTION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-10-23 | 2024-11-21 | 2024-10-23 | 2024-11-21
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCACIP05 | K061 - SYSTEM REPLACEMENT | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-06-30 | 2020-06-01 | 2020-06-30
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCACIP05 | K061 - SYSTEM REPLACEMENT | 2 | BID AWARD AND REGISTER CONTRCT | 2020-07-01 | 2020-08-29 | 2020-07-01 | 2020-08-29
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCACIP05 | K061 - SYSTEM REPLACEMENT | 3 | CONSTRUCTION TO 50% | 2020-08-30 | 2021-02-25 | 2020-08-30 | 2021-02-25
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCACIP05 | K061 - SYSTEM REPLACEMENT | 4 | CONSTRUCTION TO 75% | 2021-02-26 | 2021-05-26 | 2021-02-26 | 2021-05-26
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCACIP05 | K061 - SYSTEM REPLACEMENT | 5 | SUBSTANTIAL COMPLETION | 2021-05-27 | 2021-07-25 | 2021-05-27 | 2021-07-25
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCACIP05 | K061 - SYSTEM REPLACEMENT | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-07-26 | 2021-08-24 | 2021-07-26 | 2021-08-24
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | SOLARGR20 | NYPA - Capital 02 Rooftop Solar PV | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-06-30 | 2020-06-01 | 2020-06-30
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | SOLARGR20 | NYPA - Capital 02 Rooftop Solar PV | 2 | BID AWARD AND REGISTER CONTRCT | 2020-07-01 | 2020-08-29 | 2020-07-01 | 2020-08-29
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | SOLARGR20 | NYPA - Capital 02 Rooftop Solar PV | 3 | CONSTRUCTION TO 50% | 2020-08-30 | 2021-02-25 | 2020-08-30 | 2021-02-25
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | SOLARGR20 | NYPA - Capital 02 Rooftop Solar PV | 4 | CONSTRUCTION TO 75% | 2021-02-26 | 2021-05-26 | 2021-02-26 | 2021-05-26
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | SOLARGR20 | NYPA - Capital 02 Rooftop Solar PV | 5 | SUBSTANTIAL COMPLETION | 2021-05-27 | 2021-07-25 | 2021-05-27 | 2021-07-25
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | SOLARGR20 | NYPA - Capital 02 Rooftop Solar PV | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-07-26 | 2021-08-24 | 2021-07-26 | 2021-08-24
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | WD77STAR | STAR ENGINEERING LAB | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-09-28 | 2024-06-01 | 2024-08-29
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | WD77STAR | STAR ENGINEERING LAB | 2 | PRELIMINARY DESIGN | 2016-09-29 | 2017-01-26 | 2024-08-30 | 2024-12-27
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | WD77STAR | STAR ENGINEERING LAB | 3 | FINAL DESIGN | 2017-01-27 | 2017-07-25 | 2024-12-28 | 2025-06-25
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | WD77STAR | STAR ENGINEERING LAB | 4 | BID AWARD AND REGISTER CONTRCT | 2017-07-26 | 2017-10-23 | 2025-06-26 | 2025-09-23
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | WD77STAR | STAR ENGINEERING LAB | 5 | CONSTRUCTION TO 25% | 2017-10-24 | 2018-02-20 | 2025-09-24 | 2026-01-21
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | WD77STAR | STAR ENGINEERING LAB | 6 | CONSTRUCTION TO 50% | 2018-02-21 | 2018-06-20 | 2026-01-22 | 2026-05-21
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | WD77STAR | STAR ENGINEERING LAB | 7 | CONSTRUCTION TO 75% | 2018-06-21 | 2018-10-18 | 2026-05-22 | 2026-09-18
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | WD77STAR | STAR ENGINEERING LAB | 8 | ORIGINAL EQUIP & FURNISHING | 2018-10-19 | 2019-01-16 | 2026-09-19 | 2026-12-17
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | WD77STAR | STAR ENGINEERING LAB | 9 | SUBSTANTIAL COMPLETION | 2019-01-17 | 2019-03-17 | 2026-12-18 | 2027-02-15
20201123 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | WD77STAR | STAR ENGINEERING LAB | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-03-18 | 2019-04-16 | 2027-02-16 | 2027-03-17
20201123 | MANHATTAN | 035 | NEW YORK RESEARCH LIBRARY | LRCE12DOT | SASB:Improvements to the NYPL Vicinity | 1 | DEVELOP SCOPE | 2012-09-30 | 2012-12-28 | 2023-09-30 | 2023-12-28
20201123 | MANHATTAN | 035 | NEW YORK RESEARCH LIBRARY | LRCE12DOT | SASB:Improvements to the NYPL Vicinity | 2 | PRELIMINARY DESIGN | 2012-12-29 | 2013-04-27 | 2023-12-29 | 2024-04-26
20201123 | MANHATTAN | 035 | NEW YORK RESEARCH LIBRARY | LRCE12DOT | SASB:Improvements to the NYPL Vicinity | 3 | FINAL DESIGN | 2013-04-28 | 2013-10-24 | 2024-04-27 | 2024-10-23
20201123 | MANHATTAN | 035 | NEW YORK RESEARCH LIBRARY | LRCE12DOT | SASB:Improvements to the NYPL Vicinity | 4 | BID AWARD AND REGISTER CONTRCT | 2013-10-25 | 2014-01-22 | 2024-10-24 | 2025-01-21
20201123 | MANHATTAN | 035 | NEW YORK RESEARCH LIBRARY | LRCE12DOT | SASB:Improvements to the NYPL Vicinity | 5 | CONSTRUCTION TO 25% | 2014-01-23 | 2014-05-22 | 2025-01-22 | 2025-05-21
20201123 | MANHATTAN | 035 | NEW YORK RESEARCH LIBRARY | LRCE12DOT | SASB:Improvements to the NYPL Vicinity | 6 | CONSTRUCTION TO 50% | 2014-05-23 | 2014-09-19 | 2025-05-22 | 2025-09-18
20201123 | MANHATTAN | 035 | NEW YORK RESEARCH LIBRARY | LRCE12DOT | SASB:Improvements to the NYPL Vicinity | 7 | CONSTRUCTION TO 75% | 2014-09-20 | 2015-01-17 | 2025-09-19 | 2026-01-16
20201123 | MANHATTAN | 035 | NEW YORK RESEARCH LIBRARY | LRCE12DOT | SASB:Improvements to the NYPL Vicinity | 8 | ORIGINAL EQUIP & FURNISHING | 2015-01-18 | 2015-04-17 | 2026-01-17 | 2026-04-16
20201123 | MANHATTAN | 035 | NEW YORK RESEARCH LIBRARY | LRCE12DOT | SASB:Improvements to the NYPL Vicinity | 9 | SUBSTANTIAL COMPLETION | 2015-04-18 | 2015-06-16 | 2026-04-17 | 2030-06-29
20201123 | MANHATTAN | 035 | NEW YORK RESEARCH LIBRARY | LRCE12DOT | SASB:Improvements to the NYPL Vicinity | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-06-17 | 2015-07-16 | 2019-07-30 | 2022-07-14
20201123 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LN18FEEL | 58th Street - New Elevator (ADA Compliance) | 1 | DEVELOP SCOPE | 2021-07-01 | 2021-10-28 | 2021-07-01 | 2021-10-28
20201123 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LN18FEEL | 58th Street - New Elevator (ADA Compliance) | 2 | DESIGN | 2021-10-29 | 2022-10-28 | 2021-10-29 | 2022-10-28
20201123 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LN18FEEL | 58th Street - New Elevator (ADA Compliance) | 3 | BID/ REGISTER CONTRACT | 2022-10-29 | 2023-07-25 | 2022-10-29 | 2023-07-25
20201123 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LN18FEEL | 58th Street - New Elevator (ADA Compliance) | 4 | CONSTRUCTION | 2023-07-26 | 2025-07-24 | 2023-07-26 | 2025-07-24
20201123 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LN18FEEL | 58th Street - New Elevator (ADA Compliance) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-07-25 | 2026-07-24 | 2025-07-25 | 2026-07-24
20201123 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LN18HGHVA | HAMILTON GRANGE - HVAC System Replacement | 1 | DEVELOP SCOPE | 2022-07-01 | 2022-09-28 | 2022-07-01 | 2022-09-28
20201123 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LN18HGHVA | HAMILTON GRANGE - HVAC System Replacement | 2 | DESIGN | 2022-09-29 | 2023-09-28 | 2022-09-29 | 2023-09-28
20201123 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LN18HGHVA | HAMILTON GRANGE - HVAC System Replacement | 3 | BID/ REGISTER CONTRACT | 2023-09-29 | 2024-06-24 | 2023-09-29 | 2024-06-24
20201123 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LN18HGHVA | HAMILTON GRANGE - HVAC System Replacement | 4 | CONSTRUCTION | 2024-06-25 | 2025-06-24 | 2024-06-25 | 2025-06-24
20201123 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LN18HGHVA | HAMILTON GRANGE - HVAC System Replacement | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-06-25 | 2026-06-24 | 2025-06-25 | 2026-06-24
20201123 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LN18LBBOI | HEISKELL - Boilers (5) and HVAC replacement (11 units) | 1 | DEVELOP SCOPE | 2020-07-01 | 2020-10-28 | 2020-07-01 | 2020-10-28
20201123 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LN18LBBOI | HEISKELL - Boilers (5) and HVAC replacement (11 units) | 2 | DESIGN | 2020-10-29 | 2021-10-28 | 2020-10-29 | 2021-10-28
20201123 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LN18LBBOI | HEISKELL - Boilers (5) and HVAC replacement (11 units) | 3 | BID/ REGISTER CONTRACT | 2021-10-29 | 2022-07-25 | 2021-10-29 | 2022-07-25
20201123 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LN18LBBOI | HEISKELL - Boilers (5) and HVAC replacement (11 units) | 4 | CONSTRUCTION | 2022-07-26 | 2024-07-24 | 2022-07-26 | 2024-07-24
20201123 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LN18LBBOI | HEISKELL - Boilers (5) and HVAC replacement (11 units) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-07-25 | 2025-07-24 | 2024-07-25 | 2025-07-24
20201123 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LN18TSHVA | TOMPKINS SQUARE - HVAC System Upgrade | 1 | DEVELOP SCOPE | 2023-07-01 | 2023-09-28 | 2023-07-01 | 2023-09-28
20201123 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LN18TSHVA | TOMPKINS SQUARE - HVAC System Upgrade | 2 | DESIGN | 2023-09-29 | 2024-09-27 | 2023-09-29 | 2024-09-27
20201123 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LN18TSHVA | TOMPKINS SQUARE - HVAC System Upgrade | 3 | BID/ REGISTER CONTRACT | 2024-09-28 | 2025-06-24 | 2024-09-28 | 2025-06-24
20201123 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LN18TSHVA | TOMPKINS SQUARE - HVAC System Upgrade | 4 | CONSTRUCTION | 2025-06-25 | 2026-06-24 | 2025-06-25 | 2026-06-24
20201123 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LN18TSHVA | TOMPKINS SQUARE - HVAC System Upgrade | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2026-06-25 | 2027-06-24 | 2026-06-25 | 2027-06-24
20201123 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LN2058FPS | 58th St - New Fire Protection Sprinkler System | 1 | DEVELOP SCOPE | 2019-08-01 | 2019-10-29 | 2019-08-01 | 2019-10-29
20201123 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LN2058FPS | 58th St - New Fire Protection Sprinkler System | 2 | DESIGN | 2019-10-30 | 2020-10-28 | 2019-10-30 | 2020-10-28
20201123 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LN2058FPS | 58th St - New Fire Protection Sprinkler System | 3 | BID/ REGISTER CONTRACT | 2020-10-29 | 2021-07-25 | 2020-10-29 | 2021-07-25
20201123 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LN2058FPS | 58th St - New Fire Protection Sprinkler System | 4 | CONSTRUCTION | 2021-07-26 | 2022-07-25 | 2021-07-26 | 2022-07-25
20201123 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LN2058FPS | 58th St - New Fire Protection Sprinkler System | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-07-26 | 2023-07-25 | 2022-07-26 | 2023-07-25
20201123 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LNCA16INW | Inwood - Elevator | 1 | DEVELOP SCOPE | 2022-07-01 | 2022-09-28 | 2023-07-01 | 2023-09-28
20201123 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LNCA16INW | Inwood - Elevator | 2 | DESIGN | 2022-09-29 | 2023-09-28 | 2023-09-29 | 2024-09-27
20201123 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LNCA16INW | Inwood - Elevator | 3 | BID/ REGISTER CONTRACT | 2023-09-29 | 2024-06-24 | 2024-09-28 | 2025-06-24
20201123 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LNCA16INW | Inwood - Elevator | 4 | CONSTRUCTION | 2024-06-25 | 2025-06-24 | 2025-06-25 | 2026-06-24
20201123 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LNCA16INW | Inwood - Elevator | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-06-25 | 2026-06-24 | 2026-06-25 | 2027-06-24
20201123 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LNMA16BLD | Bloomingdale - Roof Renovation | 1 | DEVELOP SCOPE | 2020-07-01 | 2020-09-28 | 2020-07-01 | 2020-09-28
20201123 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LNMA16BLD | Bloomingdale - Roof Renovation | 2 | DESIGN | 2020-09-29 | 2021-09-28 | 2020-09-29 | 2021-09-28
20201123 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LNMA16BLD | Bloomingdale - Roof Renovation | 3 | BID/ REGISTER CONTRACT | 2021-09-29 | 2022-06-25 | 2021-09-29 | 2022-06-25
20201123 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LNMA16BLD | Bloomingdale - Roof Renovation | 4 | CONSTRUCTION | 2022-06-26 | 2023-06-25 | 2022-06-26 | 2023-06-25
20201123 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LNMA16BLD | Bloomingdale - Roof Renovation | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-06-26 | 2024-06-24 | 2023-06-26 | 2024-06-24
20201123 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LNMA17CSQ | CHATHAM SQUARE - Boiler Replacement | 1 | DEVELOP SCOPE | 2017-01-30 | 2017-04-29 | 2021-01-30 | 2021-04-29
20201123 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LNMA17CSQ | CHATHAM SQUARE - Boiler Replacement | 2 | PRELIMINARY DESIGN | 2017-04-30 | 2017-08-27 | 2021-04-30 | 2021-08-27
20201123 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LNMA17CSQ | CHATHAM SQUARE - Boiler Replacement | 3 | FINAL DESIGN | 2017-08-28 | 2018-02-23 | 2021-08-28 | 2022-02-23
20201123 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LNMA17CSQ | CHATHAM SQUARE - Boiler Replacement | 4 | BID AWARD AND REGISTER CONTRCT | 2018-02-24 | 2018-05-24 | 2022-02-24 | 2022-05-24
20201123 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LNMA17CSQ | CHATHAM SQUARE - Boiler Replacement | 5 | CONSTRUCTION TO 25% | 2018-05-25 | 2018-09-21 | 2022-05-25 | 2022-09-21
20201123 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LNMA17CSQ | CHATHAM SQUARE - Boiler Replacement | 6 | CONSTRUCTION TO 50% | 2018-09-22 | 2019-01-19 | 2022-09-22 | 2023-01-19
20201123 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LNMA17CSQ | CHATHAM SQUARE - Boiler Replacement | 7 | CONSTRUCTION TO 75% | 2019-01-20 | 2019-05-19 | 2023-01-20 | 2023-05-19
20201123 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LNMA17CSQ | CHATHAM SQUARE - Boiler Replacement | 8 | ORIGINAL EQUIP & FURNISHING | 2019-05-20 | 2019-08-17 | 2023-05-20 | 2023-08-17
20201123 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LNMA17CSQ | CHATHAM SQUARE - Boiler Replacement | 9 | SUBSTANTIAL COMPLETION | 2019-08-18 | 2019-10-16 | 2023-08-18 | 2023-10-16
20201123 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LNMA17CSQ | CHATHAM SQUARE - Boiler Replacement | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-10-17 | 2019-11-15 | 2023-10-17 | 2023-11-15
20201123 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LNSSEXTFW | 67th St - Building Envelope - Facade & Window Restoration | 1 | DEVELOP SCOPE | 2021-01-01 | 2021-03-31 | 2021-01-01 | 2021-03-31
20201123 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LNSSEXTFW | 67th St - Building Envelope - Facade & Window Restoration | 2 | DESIGN | 2021-04-01 | 2022-03-31 | 2021-04-01 | 2022-03-31
20201123 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LNSSEXTFW | 67th St - Building Envelope - Facade & Window Restoration | 3 | BID/ REGISTER CONTRACT | 2022-04-01 | 2022-12-26 | 2022-04-01 | 2022-12-26
20201123 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LNSSEXTFW | 67th St - Building Envelope - Facade & Window Restoration | 4 | CONSTRUCTION | 2022-12-27 | 2023-12-26 | 2022-12-27 | 2023-12-26
20201123 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LNSSEXTFW | 67th St - Building Envelope - Facade & Window Restoration | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-12-27 | 2024-12-25 | 2023-12-27 | 2024-12-25
20201123 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LNWBEXTFA | Webster - Building Envelope, Facade Restoration | 1 | DEVELOP SCOPE | 2021-01-01 | 2021-03-31 | 2021-01-01 | 2021-03-31
20201123 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LNWBEXTFA | Webster - Building Envelope, Facade Restoration | 2 | DESIGN | 2021-04-01 | 2022-03-31 | 2021-04-01 | 2022-03-31
20201123 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LNWBEXTFA | Webster - Building Envelope, Facade Restoration | 3 | BID/ REGISTER CONTRACT | 2022-04-01 | 2022-12-26 | 2022-04-01 | 2022-12-26
20201123 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LNWBEXTFA | Webster - Building Envelope, Facade Restoration | 4 | CONSTRUCTION | 2022-12-27 | 2023-12-26 | 2022-12-27 | 2023-12-26
20201123 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LNWBEXTFA | Webster - Building Envelope, Facade Restoration | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-12-27 | 2024-12-25 | 2023-12-27 | 2024-12-25
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | BA001-021 | Bathroom Upgrades | 1 | DEVELOP SCOPE | 2021-06-30 | 2021-09-27 | 2021-06-30 | 2021-09-27
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | BA001-021 | Bathroom Upgrades | 2 | PRELIMINARY DESIGN | 2021-09-28 | 2022-01-25 | 2021-09-28 | 2022-01-25
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | BA001-021 | Bathroom Upgrades | 3 | FINAL DESIGN | 2022-01-26 | 2022-07-24 | 2022-01-26 | 2022-07-24
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | BA001-021 | Bathroom Upgrades | 4 | BID AWARD AND REGISTER CONTRCT | 2022-07-25 | 2022-10-22 | 2022-07-25 | 2022-10-22
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | BA001-021 | Bathroom Upgrades | 5 | CONSTRUCTION TO 25% | 2022-10-23 | 2023-02-19 | 2022-10-23 | 2023-02-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | BA001-021 | Bathroom Upgrades | 6 | CONSTRUCTION TO 50% | 2023-02-20 | 2023-06-19 | 2023-02-20 | 2023-06-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | BA001-021 | Bathroom Upgrades | 7 | CONSTRUCTION TO 75% | 2023-06-20 | 2023-10-17 | 2023-06-20 | 2023-10-17
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | BA001-021 | Bathroom Upgrades | 8 | ORIGINAL EQUIP & FURNISHING | 2023-10-18 | 2024-01-15 | 2023-10-18 | 2024-01-15
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | BA001-021 | Bathroom Upgrades | 9 | SUBSTANTIAL COMPLETION | 2024-01-16 | 2024-03-15 | 2024-01-16 | 2024-03-15
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | BA001-021 | Bathroom Upgrades | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-03-16 | 2024-04-14 | 2024-03-16 | 2024-04-14
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | BA013-013 | Data Center, UPS, and Cooling | 1 | DEVELOP SCOPE | 2013-06-01 | 2013-08-29 | 2013-06-01 | 2013-08-29
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | BA013-013 | Data Center, UPS, and Cooling | 2 | PRELIMINARY DESIGN | 2013-08-30 | 2013-12-27 | 2013-08-30 | 2013-12-27
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | BA013-013 | Data Center, UPS, and Cooling | 3 | FINAL DESIGN | 2013-12-28 | 2014-06-25 | 2013-12-28 | 2014-06-25
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | BA013-013 | Data Center, UPS, and Cooling | 4 | BID AWARD AND REGISTER CONTRCT | 2014-06-26 | 2014-09-23 | 2014-06-26 | 2014-09-23
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | BA013-013 | Data Center, UPS, and Cooling | 5 | CONSTRUCTION TO 25% | 2014-09-24 | 2015-01-21 | 2014-09-24 | 2015-01-21
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | BA013-013 | Data Center, UPS, and Cooling | 6 | CONSTRUCTION TO 50% | 2015-01-22 | 2015-05-21 | 2015-01-22 | 2015-05-21
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | BA013-013 | Data Center, UPS, and Cooling | 7 | CONSTRUCTION TO 75% | 2015-05-22 | 2015-09-18 | 2015-05-22 | 2015-09-18
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | BA013-013 | Data Center, UPS, and Cooling | 8 | ORIGINAL EQUIP & FURNISHING | 2015-09-19 | 2015-12-17 | 2015-09-19 | 2015-12-17
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | BA013-013 | Data Center, UPS, and Cooling | 9 | SUBSTANTIAL COMPLETION | 2015-12-18 | 2016-02-15 | 2015-12-18 | 2016-02-15
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | BA013-013 | Data Center, UPS, and Cooling | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-02-16 | 2016-03-16 | 2016-02-16 | 2022-03-30
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | BA019-016 | Library Modernization | 1 | DEVELOP SCOPE | 2015-06-01 | 2015-08-29 | 2015-06-01 | 2015-08-29
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | BA019-016 | Library Modernization | 2 | PRELIMINARY DESIGN | 2015-08-30 | 2015-12-27 | 2015-08-30 | 2015-12-27
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | BA019-016 | Library Modernization | 3 | FINAL DESIGN | 2015-12-28 | 2016-06-24 | 2015-12-28 | 2016-06-24
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | BA019-016 | Library Modernization | 4 | BID AWARD AND REGISTER CONTRCT | 2016-06-25 | 2016-09-22 | 2016-06-25 | 2016-09-22
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | BA019-016 | Library Modernization | 5 | CONSTRUCTION TO 25% | 2016-09-23 | 2017-01-20 | 2016-09-23 | 2017-01-20
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | BA019-016 | Library Modernization | 6 | CONSTRUCTION TO 50% | 2017-01-21 | 2017-05-20 | 2017-01-21 | 2017-05-20
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | BA019-016 | Library Modernization | 7 | CONSTRUCTION TO 75% | 2017-05-21 | 2017-09-17 | 2017-05-21 | 2017-09-17
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | BA019-016 | Library Modernization | 8 | ORIGINAL EQUIP & FURNISHING | 2017-09-18 | 2017-12-16 | 2017-09-18 | 2017-12-16
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | BA019-016 | Library Modernization | 9 | SUBSTANTIAL COMPLETION | 2017-12-17 | 2018-02-14 | 2017-12-17 | 2018-02-14
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | BA019-016 | Library Modernization | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-02-15 | 2018-03-16 | 2018-02-15 | 2025-03-30
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | BA024-018 | Modification of Main Entrance at 17 Lexington Avenue | 1 | DEVELOP SCOPE | 2018-06-01 | 2018-08-29 | 2021-07-01 | 2021-09-29
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | BA024-018 | Modification of Main Entrance at 17 Lexington Avenue | 2 | PRELIMINARY DESIGN | 2018-08-30 | 2018-12-27 | 2021-09-30 | 2022-01-27
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | BA024-018 | Modification of Main Entrance at 17 Lexington Avenue | 3 | FINAL DESIGN | 2018-12-28 | 2019-06-25 | 2022-01-28 | 2022-07-26
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | BA024-018 | Modification of Main Entrance at 17 Lexington Avenue | 4 | BID AWARD AND REGISTER CONTRCT | 2019-06-26 | 2019-09-23 | 2022-07-27 | 2022-10-24
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | BA024-018 | Modification of Main Entrance at 17 Lexington Avenue | 5 | CONSTRUCTION TO 25% | 2019-09-24 | 2020-01-21 | 2022-10-25 | 2023-02-21
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | BA024-018 | Modification of Main Entrance at 17 Lexington Avenue | 6 | CONSTRUCTION TO 50% | 2020-01-22 | 2020-05-20 | 2023-02-22 | 2023-06-21
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | BA024-018 | Modification of Main Entrance at 17 Lexington Avenue | 7 | CONSTRUCTION TO 75% | 2020-05-21 | 2020-09-17 | 2023-06-22 | 2023-10-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | BA024-018 | Modification of Main Entrance at 17 Lexington Avenue | 8 | ORIGINAL EQUIP & FURNISHING | 2020-09-18 | 2020-12-16 | 2023-10-20 | 2024-01-17
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | BA024-018 | Modification of Main Entrance at 17 Lexington Avenue | 9 | SUBSTANTIAL COMPLETION | 2020-12-17 | 2021-02-14 | 2024-01-18 | 2024-03-17
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | BA024-018 | Modification of Main Entrance at 17 Lexington Avenue | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-02-15 | 2021-03-16 | 2024-03-18 | 2024-04-16
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | BA025-018 | Marxe Lab/Public Space Upgrades for School of Public Affairs | 1 | DEVELOP SCOPE | 2018-06-01 | 2018-08-29 | 2021-07-01 | 2021-09-29
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | BA025-018 | Marxe Lab/Public Space Upgrades for School of Public Affairs | 2 | PRELIMINARY DESIGN | 2018-08-30 | 2018-12-27 | 2021-09-30 | 2022-01-27
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | BA025-018 | Marxe Lab/Public Space Upgrades for School of Public Affairs | 3 | FINAL DESIGN | 2018-12-28 | 2019-06-25 | 2022-01-28 | 2022-07-26
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | BA025-018 | Marxe Lab/Public Space Upgrades for School of Public Affairs | 4 | BID AWARD AND REGISTER CONTRCT | 2019-06-26 | 2019-09-23 | 2022-07-27 | 2022-10-24
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | BA025-018 | Marxe Lab/Public Space Upgrades for School of Public Affairs | 5 | CONSTRUCTION TO 25% | 2019-09-24 | 2020-01-21 | 2022-10-25 | 2023-02-21
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | BA025-018 | Marxe Lab/Public Space Upgrades for School of Public Affairs | 6 | CONSTRUCTION TO 50% | 2020-01-22 | 2020-05-20 | 2023-02-22 | 2023-06-21
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | BA025-018 | Marxe Lab/Public Space Upgrades for School of Public Affairs | 7 | CONSTRUCTION TO 75% | 2020-05-21 | 2020-09-17 | 2023-06-22 | 2023-10-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | BA025-018 | Marxe Lab/Public Space Upgrades for School of Public Affairs | 8 | ORIGINAL EQUIP & FURNISHING | 2020-09-18 | 2020-12-16 | 2023-10-20 | 2024-01-17
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | BA025-018 | Marxe Lab/Public Space Upgrades for School of Public Affairs | 9 | SUBSTANTIAL COMPLETION | 2020-12-17 | 2021-02-14 | 2024-01-18 | 2024-03-17
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | BA025-018 | Marxe Lab/Public Space Upgrades for School of Public Affairs | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-02-15 | 2021-03-16 | 2024-03-18 | 2026-04-16
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | BA030-020 | Mason Hall A/V System | 1 | DEVELOP SCOPE | 2020-06-30 | 2020-09-27 | 2020-06-30 | 2020-09-27
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | BA030-020 | Mason Hall A/V System | 2 | PRELIMINARY DESIGN | 2020-09-28 | 2021-01-25 | 2020-09-28 | 2021-01-25
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | BA030-020 | Mason Hall A/V System | 3 | FINAL DESIGN | 2021-01-26 | 2021-07-24 | 2021-01-26 | 2021-07-24
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | BA030-020 | Mason Hall A/V System | 4 | BID AWARD AND REGISTER CONTRCT | 2021-07-25 | 2021-10-22 | 2021-07-25 | 2021-10-22
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | BA030-020 | Mason Hall A/V System | 5 | CONSTRUCTION TO 25% | 2021-10-23 | 2022-02-19 | 2021-10-23 | 2022-02-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | BA030-020 | Mason Hall A/V System | 6 | CONSTRUCTION TO 50% | 2022-02-20 | 2022-06-19 | 2022-02-20 | 2022-06-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | BA030-020 | Mason Hall A/V System | 7 | CONSTRUCTION TO 75% | 2022-06-20 | 2022-10-17 | 2022-06-20 | 2022-10-17
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | BA030-020 | Mason Hall A/V System | 8 | ORIGINAL EQUIP & FURNISHING | 2022-10-18 | 2023-01-15 | 2022-10-18 | 2023-01-15
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | BA030-020 | Mason Hall A/V System | 9 | SUBSTANTIAL COMPLETION | 2023-01-16 | 2023-03-16 | 2023-01-16 | 2023-03-16
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | BA030-020 | Mason Hall A/V System | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-03-17 | 2023-04-15 | 2023-03-17 | 2023-04-15
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA001-021 | SLUS - Facility Upgrades | 1 | DEVELOP SCOPE | 2021-06-30 | 2021-09-27 | 2021-06-30 | 2021-09-27
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA001-021 | SLUS - Facility Upgrades | 2 | PRELIMINARY DESIGN | 2021-09-28 | 2022-01-25 | 2021-09-28 | 2022-01-25
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA001-021 | SLUS - Facility Upgrades | 3 | FINAL DESIGN | 2022-01-26 | 2022-07-24 | 2022-01-26 | 2022-07-24
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA001-021 | SLUS - Facility Upgrades | 4 | BID AWARD AND REGISTER CONTRCT | 2022-07-25 | 2022-10-22 | 2022-07-25 | 2022-10-22
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA001-021 | SLUS - Facility Upgrades | 5 | CONSTRUCTION TO 25% | 2022-10-23 | 2023-02-19 | 2022-10-23 | 2023-02-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA001-021 | SLUS - Facility Upgrades | 6 | CONSTRUCTION TO 50% | 2023-02-20 | 2023-06-19 | 2023-02-20 | 2023-06-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA001-021 | SLUS - Facility Upgrades | 7 | CONSTRUCTION TO 75% | 2023-06-20 | 2023-10-17 | 2023-06-20 | 2023-10-17
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA001-021 | SLUS - Facility Upgrades | 8 | ORIGINAL EQUIP & FURNISHING | 2023-10-18 | 2024-01-15 | 2023-10-18 | 2024-01-15
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA001-021 | SLUS - Facility Upgrades | 9 | SUBSTANTIAL COMPLETION | 2024-01-16 | 2024-03-15 | 2024-01-16 | 2024-03-15
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA001-021 | SLUS - Facility Upgrades | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-03-16 | 2024-04-14 | 2024-03-16 | 2024-04-14
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA002-021 | SPS - Virtual Online Desktop - Informatics & Data Analytics | 1 | DEVELOP SCOPE | 2021-06-30 | 2021-09-27 | 2021-06-30 | 2021-09-27
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA002-021 | SPS - Virtual Online Desktop - Informatics & Data Analytics | 2 | PRELIMINARY DESIGN | 2021-09-28 | 2022-01-25 | 2021-09-28 | 2022-01-25
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA002-021 | SPS - Virtual Online Desktop - Informatics & Data Analytics | 3 | FINAL DESIGN | 2022-01-26 | 2022-07-24 | 2022-01-26 | 2022-07-24
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA002-021 | SPS - Virtual Online Desktop - Informatics & Data Analytics | 4 | BID AWARD AND REGISTER CONTRCT | 2022-07-25 | 2022-10-22 | 2022-07-25 | 2022-10-22
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA002-021 | SPS - Virtual Online Desktop - Informatics & Data Analytics | 5 | CONSTRUCTION TO 25% | 2022-10-23 | 2023-02-19 | 2022-10-23 | 2023-02-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA002-021 | SPS - Virtual Online Desktop - Informatics & Data Analytics | 6 | CONSTRUCTION TO 50% | 2023-02-20 | 2023-06-19 | 2023-02-20 | 2023-06-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA002-021 | SPS - Virtual Online Desktop - Informatics & Data Analytics | 7 | CONSTRUCTION TO 75% | 2023-06-20 | 2023-10-17 | 2023-06-20 | 2023-10-17
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA002-021 | SPS - Virtual Online Desktop - Informatics & Data Analytics | 8 | ORIGINAL EQUIP & FURNISHING | 2023-10-18 | 2024-01-15 | 2023-10-18 | 2024-01-15
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA002-021 | SPS - Virtual Online Desktop - Informatics & Data Analytics | 9 | SUBSTANTIAL COMPLETION | 2024-01-16 | 2024-03-15 | 2024-01-16 | 2024-03-15
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA002-021 | SPS - Virtual Online Desktop - Informatics & Data Analytics | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-03-16 | 2024-04-14 | 2024-03-16 | 2024-04-14
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA003-021 | Critical Maintenance | 1 | DEVELOP SCOPE | 2021-06-30 | 2021-09-27 | 2021-06-30 | 2021-09-27
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA003-021 | Critical Maintenance | 2 | PRELIMINARY DESIGN | 2021-09-28 | 2022-01-25 | 2021-09-28 | 2022-01-25
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA003-021 | Critical Maintenance | 3 | FINAL DESIGN | 2022-01-26 | 2022-07-24 | 2022-01-26 | 2022-07-24
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA003-021 | Critical Maintenance | 4 | BID AWARD AND REGISTER CONTRCT | 2022-07-25 | 2022-10-22 | 2022-07-25 | 2022-10-22
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA003-021 | Critical Maintenance | 5 | CONSTRUCTION TO 25% | 2022-10-23 | 2023-02-19 | 2022-10-23 | 2023-02-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA003-021 | Critical Maintenance | 6 | CONSTRUCTION TO 50% | 2023-02-20 | 2023-06-19 | 2023-02-20 | 2023-06-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA003-021 | Critical Maintenance | 7 | CONSTRUCTION TO 75% | 2023-06-20 | 2023-10-17 | 2023-06-20 | 2023-10-17
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA003-021 | Critical Maintenance | 8 | ORIGINAL EQUIP & FURNISHING | 2023-10-18 | 2024-01-15 | 2023-10-18 | 2024-01-15
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA003-021 | Critical Maintenance | 9 | SUBSTANTIAL COMPLETION | 2024-01-16 | 2024-03-15 | 2024-01-16 | 2024-03-15
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA003-021 | Critical Maintenance | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-03-16 | 2024-04-14 | 2024-03-16 | 2024-04-14
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA004-021 | CUNY STEM Institute | 1 | DEVELOP SCOPE | 2021-06-30 | 2021-09-27 | 2021-06-30 | 2021-09-27
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA004-021 | CUNY STEM Institute | 2 | PRELIMINARY DESIGN | 2021-09-28 | 2022-01-25 | 2021-09-28 | 2022-01-25
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA004-021 | CUNY STEM Institute | 3 | FINAL DESIGN | 2022-01-26 | 2022-07-24 | 2022-01-26 | 2022-07-24
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA004-021 | CUNY STEM Institute | 4 | BID AWARD AND REGISTER CONTRCT | 2022-07-25 | 2022-10-22 | 2022-07-25 | 2022-10-22
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA004-021 | CUNY STEM Institute | 5 | CONSTRUCTION TO 25% | 2022-10-23 | 2023-02-19 | 2022-10-23 | 2023-02-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA004-021 | CUNY STEM Institute | 6 | CONSTRUCTION TO 50% | 2023-02-20 | 2023-06-19 | 2023-02-20 | 2023-06-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA004-021 | CUNY STEM Institute | 7 | CONSTRUCTION TO 75% | 2023-06-20 | 2023-10-17 | 2023-06-20 | 2023-10-17
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA004-021 | CUNY STEM Institute | 8 | ORIGINAL EQUIP & FURNISHING | 2023-10-18 | 2024-01-15 | 2023-10-18 | 2024-01-15
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA004-021 | CUNY STEM Institute | 9 | SUBSTANTIAL COMPLETION | 2024-01-16 | 2024-03-15 | 2024-01-16 | 2024-03-15
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA004-021 | CUNY STEM Institute | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-03-16 | 2024-04-14 | 2024-03-16 | 2024-04-14
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA005-021 | CUNY SPH Renovation | 1 | DEVELOP SCOPE | 2021-06-30 | 2021-09-27 | 2021-06-30 | 2021-09-27
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA005-021 | CUNY SPH Renovation | 2 | PRELIMINARY DESIGN | 2021-09-28 | 2022-01-25 | 2021-09-28 | 2022-01-25
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA005-021 | CUNY SPH Renovation | 3 | FINAL DESIGN | 2022-01-26 | 2022-07-24 | 2022-01-26 | 2022-07-24
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA005-021 | CUNY SPH Renovation | 4 | BID AWARD AND REGISTER CONTRCT | 2022-07-25 | 2022-10-22 | 2022-07-25 | 2022-10-22
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA005-021 | CUNY SPH Renovation | 5 | CONSTRUCTION TO 25% | 2022-10-23 | 2023-02-19 | 2022-10-23 | 2023-02-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA005-021 | CUNY SPH Renovation | 6 | CONSTRUCTION TO 50% | 2023-02-20 | 2023-06-19 | 2023-02-20 | 2023-06-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA005-021 | CUNY SPH Renovation | 7 | CONSTRUCTION TO 75% | 2023-06-20 | 2023-10-17 | 2023-06-20 | 2023-10-17
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA005-021 | CUNY SPH Renovation | 8 | ORIGINAL EQUIP & FURNISHING | 2023-10-18 | 2024-01-15 | 2023-10-18 | 2024-01-15
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA005-021 | CUNY SPH Renovation | 9 | SUBSTANTIAL COMPLETION | 2024-01-16 | 2024-03-15 | 2024-01-16 | 2024-03-15
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA005-021 | CUNY SPH Renovation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-03-16 | 2024-04-14 | 2024-03-16 | 2024-04-14
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA013-008 | WEB VIDEO SYSTEMS FOR HANDICAPPED STUDENTS, CUNYWIDE | 1 | DEVELOP SCOPE | 2010-06-01 | 2010-08-29 | 2010-06-01 | 2010-08-29
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA013-008 | WEB VIDEO SYSTEMS FOR HANDICAPPED STUDENTS, CUNYWIDE | 2 | PRELIMINARY DESIGN | 2010-08-30 | 2010-12-27 | 2010-08-30 | 2010-12-27
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA013-008 | WEB VIDEO SYSTEMS FOR HANDICAPPED STUDENTS, CUNYWIDE | 3 | FINAL DESIGN | 2010-12-28 | 2011-06-25 | 2010-12-28 | 2011-06-25
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA013-008 | WEB VIDEO SYSTEMS FOR HANDICAPPED STUDENTS, CUNYWIDE | 4 | BID AWARD AND REGISTER CONTRCT | 2011-06-26 | 2011-09-23 | 2011-06-26 | 2011-09-23
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA013-008 | WEB VIDEO SYSTEMS FOR HANDICAPPED STUDENTS, CUNYWIDE | 5 | CONSTRUCTION TO 25% | 2011-09-24 | 2012-01-21 | 2011-09-24 | 2012-01-21
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA013-008 | WEB VIDEO SYSTEMS FOR HANDICAPPED STUDENTS, CUNYWIDE | 6 | CONSTRUCTION TO 50% | 2012-01-22 | 2012-05-20 | 2012-01-22 | 2012-05-20
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA013-008 | WEB VIDEO SYSTEMS FOR HANDICAPPED STUDENTS, CUNYWIDE | 7 | CONSTRUCTION TO 75% | 2012-05-21 | 2012-09-17 | 2012-05-21 | 2012-09-17
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA013-008 | WEB VIDEO SYSTEMS FOR HANDICAPPED STUDENTS, CUNYWIDE | 8 | ORIGINAL EQUIP & FURNISHING | 2012-09-18 | 2012-12-16 | 2012-09-18 | 2012-12-16
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA013-008 | WEB VIDEO SYSTEMS FOR HANDICAPPED STUDENTS, CUNYWIDE | 9 | SUBSTANTIAL COMPLETION | 2012-12-17 | 2013-02-14 | 2012-12-17 | 2013-02-14
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA013-008 | WEB VIDEO SYSTEMS FOR HANDICAPPED STUDENTS, CUNYWIDE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-02-15 | 2013-03-16 | 2013-02-15 | 2026-03-31
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA027-012 | Community College Laboratories | 1 | DEVELOP SCOPE | 2012-06-01 | 2012-08-29 | 2012-06-01 | 2012-08-29
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA027-012 | Community College Laboratories | 2 | PRELIMINARY DESIGN | 2012-08-30 | 2012-12-27 | 2012-08-30 | 2012-12-27
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA027-012 | Community College Laboratories | 3 | FINAL DESIGN | 2012-12-28 | 2013-06-25 | 2012-12-28 | 2013-06-25
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA027-012 | Community College Laboratories | 4 | BID AWARD AND REGISTER CONTRCT | 2013-06-26 | 2013-09-23 | 2013-06-26 | 2013-09-23
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA027-012 | Community College Laboratories | 5 | CONSTRUCTION TO 25% | 2013-09-24 | 2014-01-21 | 2013-09-24 | 2014-01-21
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA027-012 | Community College Laboratories | 6 | CONSTRUCTION TO 50% | 2014-01-22 | 2014-05-21 | 2014-01-22 | 2014-05-21
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA027-012 | Community College Laboratories | 7 | CONSTRUCTION TO 75% | 2014-05-22 | 2014-09-18 | 2014-05-22 | 2014-09-18
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA027-012 | Community College Laboratories | 8 | ORIGINAL EQUIP & FURNISHING | 2014-09-19 | 2014-12-17 | 2014-09-19 | 2014-12-17
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA027-012 | Community College Laboratories | 9 | SUBSTANTIAL COMPLETION | 2014-12-18 | 2015-02-15 | 2014-12-18 | 2015-02-15
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA027-012 | Community College Laboratories | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-02-16 | 2015-03-17 | 2015-02-16 | 2027-03-15
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA032-013 | Center for Innovation and Entrepreneurship | 1 | DEVELOP SCOPE | 2013-06-01 | 2013-08-29 | 2013-06-01 | 2013-08-29
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA032-013 | Center for Innovation and Entrepreneurship | 2 | PRELIMINARY DESIGN | 2013-08-30 | 2013-12-27 | 2013-08-30 | 2013-12-27
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA032-013 | Center for Innovation and Entrepreneurship | 3 | FINAL DESIGN | 2013-12-28 | 2014-06-25 | 2013-12-28 | 2014-06-25
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA032-013 | Center for Innovation and Entrepreneurship | 4 | BID AWARD AND REGISTER CONTRCT | 2014-06-26 | 2014-09-23 | 2014-06-26 | 2014-09-23
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA032-013 | Center for Innovation and Entrepreneurship | 5 | CONSTRUCTION TO 25% | 2014-09-24 | 2015-01-21 | 2014-09-24 | 2015-01-21
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA032-013 | Center for Innovation and Entrepreneurship | 6 | CONSTRUCTION TO 50% | 2015-01-22 | 2015-05-21 | 2015-01-22 | 2015-05-21
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA032-013 | Center for Innovation and Entrepreneurship | 7 | CONSTRUCTION TO 75% | 2015-05-22 | 2015-09-18 | 2015-05-22 | 2015-09-18
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA032-013 | Center for Innovation and Entrepreneurship | 8 | ORIGINAL EQUIP & FURNISHING | 2015-09-19 | 2015-12-17 | 2015-09-19 | 2015-12-17
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA032-013 | Center for Innovation and Entrepreneurship | 9 | SUBSTANTIAL COMPLETION | 2015-12-18 | 2016-02-15 | 2015-12-18 | 2016-02-15
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA032-013 | Center for Innovation and Entrepreneurship | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-02-16 | 2016-03-16 | 2016-02-16 | 2026-03-31
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA049-019 | CUNY In The Heights | 1 | DEVELOP SCOPE | 2018-06-30 | 2018-09-27 | 2019-06-30 | 2019-09-28
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA049-019 | CUNY In The Heights | 2 | PRELIMINARY DESIGN | 2018-09-28 | 2019-01-25 | 2019-09-29 | 2020-01-26
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA049-019 | CUNY In The Heights | 3 | FINAL DESIGN | 2019-01-26 | 2019-07-24 | 2020-01-27 | 2020-07-24
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA049-019 | CUNY In The Heights | 4 | BID AWARD AND REGISTER CONTRCT | 2019-07-25 | 2019-10-22 | 2020-07-25 | 2020-10-22
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA049-019 | CUNY In The Heights | 5 | CONSTRUCTION TO 25% | 2019-10-23 | 2020-02-19 | 2020-10-23 | 2021-02-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA049-019 | CUNY In The Heights | 6 | CONSTRUCTION TO 50% | 2020-02-20 | 2020-06-18 | 2021-02-20 | 2021-06-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA049-019 | CUNY In The Heights | 7 | CONSTRUCTION TO 75% | 2020-06-19 | 2020-10-16 | 2021-06-20 | 2021-10-17
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA049-019 | CUNY In The Heights | 8 | ORIGINAL EQUIP & FURNISHING | 2020-10-17 | 2021-01-14 | 2021-10-18 | 2022-01-15
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA049-019 | CUNY In The Heights | 9 | SUBSTANTIAL COMPLETION | 2021-01-15 | 2021-03-15 | 2022-01-16 | 2022-03-16
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA049-019 | CUNY In The Heights | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-16 | 2021-04-14 | 2022-03-17 | 2022-04-15
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA050-017 | Health, Safety & ADA Projects | 1 | DEVELOP SCOPE | 2017-06-01 | 2017-08-29 | 2017-06-01 | 2017-08-29
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA050-017 | Health, Safety & ADA Projects | 2 | PRELIMINARY DESIGN | 2017-08-30 | 2017-12-27 | 2017-08-30 | 2017-12-27
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA050-017 | Health, Safety & ADA Projects | 3 | FINAL DESIGN | 2017-12-28 | 2018-06-25 | 2017-12-28 | 2018-06-25
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA050-017 | Health, Safety & ADA Projects | 4 | BID AWARD AND REGISTER CONTRCT | 2018-06-26 | 2018-09-23 | 2018-06-26 | 2018-09-23
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA050-017 | Health, Safety & ADA Projects | 5 | CONSTRUCTION TO 25% | 2018-09-24 | 2019-01-21 | 2018-09-24 | 2019-01-21
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA050-017 | Health, Safety & ADA Projects | 6 | CONSTRUCTION TO 50% | 2019-01-22 | 2019-05-21 | 2019-01-22 | 2019-05-21
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA050-017 | Health, Safety & ADA Projects | 7 | CONSTRUCTION TO 75% | 2019-05-22 | 2019-09-18 | 2019-05-22 | 2019-09-18
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA050-017 | Health, Safety & ADA Projects | 8 | ORIGINAL EQUIP & FURNISHING | 2019-09-19 | 2019-12-17 | 2019-09-19 | 2019-12-17
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA050-017 | Health, Safety & ADA Projects | 9 | SUBSTANTIAL COMPLETION | 2019-12-18 | 2020-02-15 | 2019-12-18 | 2020-02-15
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA050-017 | Health, Safety & ADA Projects | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-02-16 | 2020-03-16 | 2020-02-16 | 2023-03-30
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA050-019 | CUNY-Wide Community College Health, Safety & ADA Projects | 1 | DEVELOP SCOPE | 2019-06-01 | 2019-08-29 | 2019-06-01 | 2019-08-29
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA050-019 | CUNY-Wide Community College Health, Safety & ADA Projects | 2 | PRELIMINARY DESIGN | 2019-08-30 | 2019-12-27 | 2019-08-30 | 2019-12-27
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA050-019 | CUNY-Wide Community College Health, Safety & ADA Projects | 3 | FINAL DESIGN | 2019-12-28 | 2020-06-24 | 2019-12-28 | 2020-06-24
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA050-019 | CUNY-Wide Community College Health, Safety & ADA Projects | 4 | BID AWARD AND REGISTER CONTRCT | 2020-06-25 | 2020-09-22 | 2020-06-25 | 2020-09-22
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA050-019 | CUNY-Wide Community College Health, Safety & ADA Projects | 5 | CONSTRUCTION TO 25% | 2020-09-23 | 2021-01-20 | 2020-09-23 | 2021-01-20
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA050-019 | CUNY-Wide Community College Health, Safety & ADA Projects | 6 | CONSTRUCTION TO 50% | 2021-01-21 | 2021-05-20 | 2021-01-21 | 2021-05-20
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA050-019 | CUNY-Wide Community College Health, Safety & ADA Projects | 7 | CONSTRUCTION TO 75% | 2021-05-21 | 2021-09-17 | 2021-05-21 | 2021-09-17
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA050-019 | CUNY-Wide Community College Health, Safety & ADA Projects | 8 | ORIGINAL EQUIP & FURNISHING | 2021-09-18 | 2021-12-16 | 2021-09-18 | 2021-12-16
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA050-019 | CUNY-Wide Community College Health, Safety & ADA Projects | 9 | SUBSTANTIAL COMPLETION | 2021-12-17 | 2022-02-14 | 2021-12-17 | 2022-02-14
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA050-019 | CUNY-Wide Community College Health, Safety & ADA Projects | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-02-15 | 2022-03-16 | 2022-02-15 | 2022-03-16
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA054-017 | CUNY Accelerated Study in Associate Programs Expansion | 1 | DEVELOP SCOPE | 2017-06-30 | 2017-09-27 | 2017-06-30 | 2017-09-27
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA054-017 | CUNY Accelerated Study in Associate Programs Expansion | 2 | PRELIMINARY DESIGN | 2017-09-28 | 2018-01-25 | 2017-09-28 | 2018-01-25
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA054-017 | CUNY Accelerated Study in Associate Programs Expansion | 3 | FINAL DESIGN | 2018-01-26 | 2018-07-24 | 2018-01-26 | 2018-07-24
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA054-017 | CUNY Accelerated Study in Associate Programs Expansion | 4 | BID AWARD AND REGISTER CONTRCT | 2018-07-25 | 2018-10-22 | 2018-07-25 | 2018-10-22
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA054-017 | CUNY Accelerated Study in Associate Programs Expansion | 5 | CONSTRUCTION TO 25% | 2018-10-23 | 2019-02-19 | 2018-10-23 | 2019-02-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA054-017 | CUNY Accelerated Study in Associate Programs Expansion | 6 | CONSTRUCTION TO 50% | 2019-02-20 | 2019-06-19 | 2019-02-20 | 2019-06-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA054-017 | CUNY Accelerated Study in Associate Programs Expansion | 7 | CONSTRUCTION TO 75% | 2019-06-20 | 2019-10-17 | 2019-06-20 | 2019-10-17
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA054-017 | CUNY Accelerated Study in Associate Programs Expansion | 8 | ORIGINAL EQUIP & FURNISHING | 2019-10-18 | 2020-01-15 | 2019-10-18 | 2020-01-15
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA054-017 | CUNY Accelerated Study in Associate Programs Expansion | 9 | SUBSTANTIAL COMPLETION | 2020-01-16 | 2020-03-15 | 2020-01-16 | 2020-03-15
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA054-017 | CUNY Accelerated Study in Associate Programs Expansion | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-03-16 | 2020-04-14 | 2020-03-16 | 2020-04-14
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA054-018 | CUNY Community College Health, Safety and ADA Projects | 1 | DEVELOP SCOPE | 2018-06-01 | 2018-08-29 | 2018-06-01 | 2018-08-29
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA054-018 | CUNY Community College Health, Safety and ADA Projects | 2 | PRELIMINARY DESIGN | 2018-08-30 | 2018-12-27 | 2018-08-30 | 2018-12-27
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA054-018 | CUNY Community College Health, Safety and ADA Projects | 3 | FINAL DESIGN | 2018-12-28 | 2019-06-25 | 2018-12-28 | 2019-06-25
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA054-018 | CUNY Community College Health, Safety and ADA Projects | 4 | BID AWARD AND REGISTER CONTRCT | 2019-06-26 | 2019-09-23 | 2019-06-26 | 2019-09-23
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA054-018 | CUNY Community College Health, Safety and ADA Projects | 5 | CONSTRUCTION TO 25% | 2019-09-24 | 2020-01-21 | 2019-09-24 | 2020-01-21
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA054-018 | CUNY Community College Health, Safety and ADA Projects | 6 | CONSTRUCTION TO 50% | 2020-01-22 | 2020-05-20 | 2020-01-22 | 2020-05-20
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA054-018 | CUNY Community College Health, Safety and ADA Projects | 7 | CONSTRUCTION TO 75% | 2020-05-21 | 2020-09-17 | 2020-05-21 | 2020-09-17
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA054-018 | CUNY Community College Health, Safety and ADA Projects | 8 | ORIGINAL EQUIP & FURNISHING | 2020-09-18 | 2020-12-16 | 2020-09-18 | 2020-12-16
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA054-018 | CUNY Community College Health, Safety and ADA Projects | 9 | SUBSTANTIAL COMPLETION | 2020-12-17 | 2021-02-14 | 2020-12-17 | 2021-02-14
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA054-018 | CUNY Community College Health, Safety and ADA Projects | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-02-15 | 2021-03-16 | 2021-02-15 | 2023-03-30
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA054-020 | Health, Safety, and ADA Projects | 1 | DEVELOP SCOPE | 2020-06-30 | 2020-09-27 | 2020-06-30 | 2020-09-27
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA054-020 | Health, Safety, and ADA Projects | 2 | PRELIMINARY DESIGN | 2020-09-28 | 2021-01-25 | 2020-09-28 | 2021-01-25
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA054-020 | Health, Safety, and ADA Projects | 3 | FINAL DESIGN | 2021-01-26 | 2021-07-24 | 2021-01-26 | 2021-07-24
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA054-020 | Health, Safety, and ADA Projects | 4 | BID AWARD AND REGISTER CONTRCT | 2021-07-25 | 2021-10-22 | 2021-07-25 | 2021-10-22
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA054-020 | Health, Safety, and ADA Projects | 5 | CONSTRUCTION TO 25% | 2021-10-23 | 2022-02-19 | 2021-10-23 | 2022-02-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA054-020 | Health, Safety, and ADA Projects | 6 | CONSTRUCTION TO 50% | 2022-02-20 | 2022-06-19 | 2022-02-20 | 2022-06-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA054-020 | Health, Safety, and ADA Projects | 7 | CONSTRUCTION TO 75% | 2022-06-20 | 2022-10-17 | 2022-06-20 | 2022-10-17
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA054-020 | Health, Safety, and ADA Projects | 8 | ORIGINAL EQUIP & FURNISHING | 2022-10-18 | 2023-01-15 | 2022-10-18 | 2023-01-15
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA054-020 | Health, Safety, and ADA Projects | 9 | SUBSTANTIAL COMPLETION | 2023-01-16 | 2023-03-16 | 2023-01-16 | 2023-03-16
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA054-020 | Health, Safety, and ADA Projects | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-03-17 | 2023-04-15 | 2023-03-17 | 2023-04-15
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA056-020 | John Jay School of Law | 1 | DEVELOP SCOPE | 2020-06-30 | 2020-09-27 | 2020-06-30 | 2020-09-27
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA056-020 | John Jay School of Law | 2 | PRELIMINARY DESIGN | 2020-09-28 | 2021-01-25 | 2020-09-28 | 2021-01-25
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA056-020 | John Jay School of Law | 3 | FINAL DESIGN | 2021-01-26 | 2021-07-24 | 2021-01-26 | 2021-07-24
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA056-020 | John Jay School of Law | 4 | BID AWARD AND REGISTER CONTRCT | 2021-07-25 | 2021-10-22 | 2021-07-25 | 2021-10-22
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA056-020 | John Jay School of Law | 5 | CONSTRUCTION TO 25% | 2021-10-23 | 2022-02-19 | 2021-10-23 | 2022-02-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA056-020 | John Jay School of Law | 6 | CONSTRUCTION TO 50% | 2022-02-20 | 2022-06-19 | 2022-02-20 | 2022-06-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA056-020 | John Jay School of Law | 7 | CONSTRUCTION TO 75% | 2022-06-20 | 2022-10-17 | 2022-06-20 | 2022-10-17
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA056-020 | John Jay School of Law | 8 | ORIGINAL EQUIP & FURNISHING | 2022-10-18 | 2023-01-15 | 2022-10-18 | 2023-01-15
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA056-020 | John Jay School of Law | 9 | SUBSTANTIAL COMPLETION | 2023-01-16 | 2023-03-16 | 2023-01-16 | 2023-03-16
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA056-020 | John Jay School of Law | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-03-17 | 2023-04-15 | 2023-03-17 | 2026-04-30
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA200MC02 | Pedestrian Plaza and Roof Replacement | 1 | DEVELOP SCOPE | 2007-05-30 | 2007-08-27 | 2007-05-30 | 2007-08-27
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA200MC02 | Pedestrian Plaza and Roof Replacement | 2 | PRELIMINARY DESIGN | 2007-08-28 | 2007-12-25 | 2007-08-28 | 2007-12-25
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA200MC02 | Pedestrian Plaza and Roof Replacement | 3 | FINAL DESIGN | 2007-12-26 | 2008-06-22 | 2007-12-26 | 2008-06-22
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA200MC02 | Pedestrian Plaza and Roof Replacement | 4 | BID AWARD AND REGISTER CONTRCT | 2008-06-23 | 2008-09-20 | 2008-06-23 | 2008-09-20
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA200MC02 | Pedestrian Plaza and Roof Replacement | 5 | CONSTRUCTION TO 25% | 2008-09-21 | 2009-01-18 | 2008-09-21 | 2009-01-18
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA200MC02 | Pedestrian Plaza and Roof Replacement | 6 | CONSTRUCTION TO 50% | 2009-01-19 | 2009-05-18 | 2009-01-19 | 2009-05-18
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA200MC02 | Pedestrian Plaza and Roof Replacement | 7 | CONSTRUCTION TO 75% | 2009-05-19 | 2009-09-15 | 2009-05-19 | 2009-09-15
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA200MC02 | Pedestrian Plaza and Roof Replacement | 8 | ORIGINAL EQUIP & FURNISHING | 2009-09-16 | 2009-12-14 | 2009-09-16 | 2009-12-14
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA200MC02 | Pedestrian Plaza and Roof Replacement | 9 | SUBSTANTIAL COMPLETION | 2009-12-15 | 2010-02-12 | 2009-12-15 | 2010-02-12
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA200MC02 | Pedestrian Plaza and Roof Replacement | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2010-02-13 | 2010-03-14 | 2010-02-13 | 2022-03-14
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA201MC04 | BMCC RAMP & PLAZA PEDESTAL REPAIRS | 1 | DEVELOP SCOPE | 2009-06-01 | 2009-08-29 | 2009-06-01 | 2009-08-29
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA201MC04 | BMCC RAMP & PLAZA PEDESTAL REPAIRS | 2 | PRELIMINARY DESIGN | 2009-08-30 | 2009-12-27 | 2009-08-30 | 2009-12-27
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA201MC04 | BMCC RAMP & PLAZA PEDESTAL REPAIRS | 3 | FINAL DESIGN | 2009-12-28 | 2010-06-25 | 2009-12-28 | 2010-06-25
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA201MC04 | BMCC RAMP & PLAZA PEDESTAL REPAIRS | 4 | BID AWARD AND REGISTER CONTRCT | 2010-06-26 | 2010-09-23 | 2010-06-26 | 2010-09-23
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA201MC04 | BMCC RAMP & PLAZA PEDESTAL REPAIRS | 5 | CONSTRUCTION TO 25% | 2010-09-24 | 2011-01-21 | 2010-09-24 | 2011-01-21
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA201MC04 | BMCC RAMP & PLAZA PEDESTAL REPAIRS | 6 | CONSTRUCTION TO 50% | 2011-01-22 | 2011-05-21 | 2011-01-22 | 2011-05-21
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA201MC04 | BMCC RAMP & PLAZA PEDESTAL REPAIRS | 7 | CONSTRUCTION TO 75% | 2011-05-22 | 2011-09-18 | 2011-05-22 | 2011-09-18
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA201MC04 | BMCC RAMP & PLAZA PEDESTAL REPAIRS | 8 | ORIGINAL EQUIP & FURNISHING | 2011-09-19 | 2011-12-17 | 2011-09-19 | 2011-12-17
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA201MC04 | BMCC RAMP & PLAZA PEDESTAL REPAIRS | 9 | SUBSTANTIAL COMPLETION | 2011-12-18 | 2012-02-15 | 2011-12-18 | 2012-02-15
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA201MC04 | BMCC RAMP & PLAZA PEDESTAL REPAIRS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-02-16 | 2012-03-16 | 2012-02-16 | 2022-06-30
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA202MC01 | ADA BATHROOM UPGRADES FOR BMCC | 1 | DEVELOP SCOPE | 2009-06-01 | 2009-08-29 | 2009-06-01 | 2009-08-29
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA202MC01 | ADA BATHROOM UPGRADES FOR BMCC | 2 | PRELIMINARY DESIGN | 2009-08-30 | 2009-12-27 | 2009-08-30 | 2009-12-27
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA202MC01 | ADA BATHROOM UPGRADES FOR BMCC | 3 | FINAL DESIGN | 2009-12-28 | 2010-06-25 | 2009-12-28 | 2010-06-25
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA202MC01 | ADA BATHROOM UPGRADES FOR BMCC | 4 | BID AWARD AND REGISTER CONTRCT | 2010-06-26 | 2010-09-23 | 2010-06-26 | 2010-09-23
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA202MC01 | ADA BATHROOM UPGRADES FOR BMCC | 5 | CONSTRUCTION TO 25% | 2010-09-24 | 2011-01-21 | 2010-09-24 | 2011-01-21
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA202MC01 | ADA BATHROOM UPGRADES FOR BMCC | 6 | CONSTRUCTION TO 50% | 2011-01-22 | 2011-05-21 | 2011-01-22 | 2011-05-21
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA202MC01 | ADA BATHROOM UPGRADES FOR BMCC | 7 | CONSTRUCTION TO 75% | 2011-05-22 | 2011-09-18 | 2011-05-22 | 2011-09-18
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA202MC01 | ADA BATHROOM UPGRADES FOR BMCC | 8 | ORIGINAL EQUIP & FURNISHING | 2011-09-19 | 2011-12-17 | 2011-09-19 | 2011-12-17
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA202MC01 | ADA BATHROOM UPGRADES FOR BMCC | 9 | SUBSTANTIAL COMPLETION | 2011-12-18 | 2012-02-15 | 2011-12-18 | 2012-02-15
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CA202MC01 | ADA BATHROOM UPGRADES FOR BMCC | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-02-16 | 2012-03-16 | 2012-02-16 | 2026-03-30
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC008-005 | Dominican Studies Institute Library and Archive | 5 | CONSTRUCTION TO 25% | 2006-06-25 | 2006-10-22 | 2006-06-25 | 2006-10-22
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC008-005 | Dominican Studies Institute Library and Archive | 6 | CONSTRUCTION TO 50% | 2006-10-23 | 2007-02-19 | 2006-10-23 | 2007-02-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC008-005 | Dominican Studies Institute Library and Archive | 7 | CONSTRUCTION TO 75% | 2007-02-20 | 2007-06-19 | 2007-02-20 | 2007-06-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC008-005 | Dominican Studies Institute Library and Archive | 8 | ORIGINAL EQUIP & FURNISHING | 2007-06-20 | 2007-09-17 | 2007-06-20 | 2007-09-17
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC008-005 | Dominican Studies Institute Library and Archive | 9 | SUBSTANTIAL COMPLETION | 2007-09-18 | 2007-11-16 | 2007-09-18 | 2007-11-16
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC008-005 | Dominican Studies Institute Library and Archive | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2007-11-17 | 2007-12-16 | 2007-11-17 | 2011-07-16
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC009-007 | Upgrade North Academic Center Classrooms | 1 | DEVELOP SCOPE | 2007-01-14 | 2007-04-13 | 2007-01-14 | 2007-04-13
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC009-007 | Upgrade North Academic Center Classrooms | 2 | PRELIMINARY DESIGN | 2007-04-14 | 2007-08-11 | 2007-04-14 | 2007-08-11
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC009-007 | Upgrade North Academic Center Classrooms | 3 | FINAL DESIGN | 2007-08-12 | 2008-02-07 | 2007-08-12 | 2008-02-07
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC009-007 | Upgrade North Academic Center Classrooms | 4 | BID AWARD AND REGISTER CONTRCT | 2008-02-08 | 2008-05-07 | 2008-02-08 | 2008-05-07
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC009-007 | Upgrade North Academic Center Classrooms | 5 | CONSTRUCTION TO 25% | 2008-05-08 | 2008-09-04 | 2008-05-08 | 2008-09-04
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC009-007 | Upgrade North Academic Center Classrooms | 6 | CONSTRUCTION TO 50% | 2008-09-05 | 2009-01-02 | 2008-09-05 | 2009-01-02
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC009-007 | Upgrade North Academic Center Classrooms | 7 | CONSTRUCTION TO 75% | 2009-01-03 | 2009-05-02 | 2009-01-03 | 2009-05-02
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC009-007 | Upgrade North Academic Center Classrooms | 8 | ORIGINAL EQUIP & FURNISHING | 2009-05-03 | 2009-07-31 | 2009-05-03 | 2009-07-31
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC009-007 | Upgrade North Academic Center Classrooms | 9 | SUBSTANTIAL COMPLETION | 2009-08-01 | 2009-09-29 | 2009-08-01 | 2009-09-29
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC009-007 | Upgrade North Academic Center Classrooms | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2009-09-30 | 2009-10-29 | 2009-09-30 | 2027-06-30
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC012-008 | RESTORATION OF LIBRARY AND BLDG, RANGEL CTR FOR PUBLIC SERV | 1 | DEVELOP SCOPE | 2009-06-01 | 2009-08-29 | 2009-06-01 | 2009-08-29
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC012-008 | RESTORATION OF LIBRARY AND BLDG, RANGEL CTR FOR PUBLIC SERV | 2 | PRELIMINARY DESIGN | 2009-08-30 | 2009-12-27 | 2009-08-30 | 2009-12-27
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC012-008 | RESTORATION OF LIBRARY AND BLDG, RANGEL CTR FOR PUBLIC SERV | 3 | FINAL DESIGN | 2009-12-28 | 2010-06-25 | 2009-12-28 | 2010-06-25
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC012-008 | RESTORATION OF LIBRARY AND BLDG, RANGEL CTR FOR PUBLIC SERV | 4 | BID AWARD AND REGISTER CONTRCT | 2010-06-26 | 2010-09-23 | 2010-06-26 | 2010-09-23
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC012-008 | RESTORATION OF LIBRARY AND BLDG, RANGEL CTR FOR PUBLIC SERV | 5 | CONSTRUCTION TO 25% | 2010-09-24 | 2011-01-21 | 2010-09-24 | 2011-01-21
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC012-008 | RESTORATION OF LIBRARY AND BLDG, RANGEL CTR FOR PUBLIC SERV | 6 | CONSTRUCTION TO 50% | 2011-01-22 | 2011-05-21 | 2011-01-22 | 2011-05-21
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC012-008 | RESTORATION OF LIBRARY AND BLDG, RANGEL CTR FOR PUBLIC SERV | 7 | CONSTRUCTION TO 75% | 2011-05-22 | 2011-09-18 | 2011-05-22 | 2011-09-18
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC012-008 | RESTORATION OF LIBRARY AND BLDG, RANGEL CTR FOR PUBLIC SERV | 8 | ORIGINAL EQUIP & FURNISHING | 2011-09-19 | 2011-12-17 | 2011-09-19 | 2011-12-17
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC012-008 | RESTORATION OF LIBRARY AND BLDG, RANGEL CTR FOR PUBLIC SERV | 9 | SUBSTANTIAL COMPLETION | 2011-12-18 | 2012-02-15 | 2011-12-18 | 2012-02-15
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC012-008 | RESTORATION OF LIBRARY AND BLDG, RANGEL CTR FOR PUBLIC SERV | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-02-16 | 2012-03-16 | 2012-02-16 | 2024-12-31
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC018-009 | ARONOW THEATER UPGRADE | 1 | DEVELOP SCOPE | 2009-06-01 | 2009-08-29 | 2020-07-01 | 2020-09-29
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC018-009 | ARONOW THEATER UPGRADE | 2 | PRELIMINARY DESIGN | 2009-08-30 | 2009-12-27 | 2020-09-30 | 2021-01-27
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC018-009 | ARONOW THEATER UPGRADE | 3 | FINAL DESIGN | 2009-12-28 | 2010-06-25 | 2021-01-28 | 2021-07-26
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC018-009 | ARONOW THEATER UPGRADE | 4 | BID AWARD AND REGISTER CONTRCT | 2010-06-26 | 2010-09-23 | 2021-07-27 | 2021-10-24
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC018-009 | ARONOW THEATER UPGRADE | 5 | CONSTRUCTION TO 25% | 2010-09-24 | 2011-01-21 | 2021-10-25 | 2022-02-21
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC018-009 | ARONOW THEATER UPGRADE | 6 | CONSTRUCTION TO 50% | 2011-01-22 | 2011-05-21 | 2022-02-22 | 2022-06-21
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC018-009 | ARONOW THEATER UPGRADE | 7 | CONSTRUCTION TO 75% | 2011-05-22 | 2011-09-18 | 2022-06-22 | 2022-10-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC018-009 | ARONOW THEATER UPGRADE | 8 | ORIGINAL EQUIP & FURNISHING | 2011-09-19 | 2011-12-17 | 2022-10-20 | 2023-01-17
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC018-009 | ARONOW THEATER UPGRADE | 9 | SUBSTANTIAL COMPLETION | 2011-12-18 | 2012-02-15 | 2023-01-18 | 2023-03-18
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC018-009 | ARONOW THEATER UPGRADE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-02-16 | 2012-03-16 | 2023-03-19 | 2026-04-30
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC022-012 | Schiff House Day Care Center Upgrades | 1 | DEVELOP SCOPE | 2012-06-01 | 2012-08-29 | 2012-06-01 | 2012-08-29
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC022-012 | Schiff House Day Care Center Upgrades | 2 | PRELIMINARY DESIGN | 2012-08-30 | 2012-12-27 | 2012-08-30 | 2012-12-27
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC022-012 | Schiff House Day Care Center Upgrades | 3 | FINAL DESIGN | 2012-12-28 | 2013-06-25 | 2012-12-28 | 2013-06-25
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC022-012 | Schiff House Day Care Center Upgrades | 4 | BID AWARD AND REGISTER CONTRCT | 2013-06-26 | 2013-09-23 | 2013-06-26 | 2013-09-23
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC022-012 | Schiff House Day Care Center Upgrades | 5 | CONSTRUCTION TO 25% | 2013-09-24 | 2014-01-21 | 2013-09-24 | 2014-01-21
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC022-012 | Schiff House Day Care Center Upgrades | 6 | CONSTRUCTION TO 50% | 2014-01-22 | 2014-05-21 | 2014-01-22 | 2014-05-21
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC022-012 | Schiff House Day Care Center Upgrades | 7 | CONSTRUCTION TO 75% | 2014-05-22 | 2014-09-18 | 2014-05-22 | 2014-09-18
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC022-012 | Schiff House Day Care Center Upgrades | 8 | ORIGINAL EQUIP & FURNISHING | 2014-09-19 | 2014-12-17 | 2014-09-19 | 2014-12-17
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC022-012 | Schiff House Day Care Center Upgrades | 9 | SUBSTANTIAL COMPLETION | 2014-12-18 | 2015-02-15 | 2014-12-18 | 2015-02-15
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC022-012 | Schiff House Day Care Center Upgrades | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-02-16 | 2015-03-17 | 2015-02-16 | 2026-03-30
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC025-013 | Dominican Studies Institute | 1 | DEVELOP SCOPE | 2013-06-01 | 2013-08-29 | 2021-07-01 | 2021-09-29
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC025-013 | Dominican Studies Institute | 2 | PRELIMINARY DESIGN | 2013-08-30 | 2013-12-27 | 2021-09-30 | 2022-01-27
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC025-013 | Dominican Studies Institute | 3 | FINAL DESIGN | 2013-12-28 | 2014-06-25 | 2022-01-28 | 2022-07-26
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC025-013 | Dominican Studies Institute | 4 | BID AWARD AND REGISTER CONTRCT | 2014-06-26 | 2014-09-23 | 2022-07-27 | 2022-10-24
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC025-013 | Dominican Studies Institute | 5 | CONSTRUCTION TO 25% | 2014-09-24 | 2015-01-21 | 2022-10-25 | 2023-02-21
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC025-013 | Dominican Studies Institute | 6 | CONSTRUCTION TO 50% | 2015-01-22 | 2015-05-21 | 2023-02-22 | 2023-06-21
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC025-013 | Dominican Studies Institute | 7 | CONSTRUCTION TO 75% | 2015-05-22 | 2015-09-18 | 2023-06-22 | 2023-10-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC025-013 | Dominican Studies Institute | 8 | ORIGINAL EQUIP & FURNISHING | 2015-09-19 | 2015-12-17 | 2023-10-20 | 2024-01-17
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC025-013 | Dominican Studies Institute | 9 | SUBSTANTIAL COMPLETION | 2015-12-18 | 2016-02-15 | 2024-01-18 | 2024-03-17
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC025-013 | Dominican Studies Institute | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-02-16 | 2016-03-16 | 2024-03-18 | 2024-04-17
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC026-013 | Aaron Davis Hall | 1 | DEVELOP SCOPE | 2013-06-01 | 2013-08-29 | 2021-07-01 | 2021-10-01
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC026-013 | Aaron Davis Hall | 2 | PRELIMINARY DESIGN | 2013-08-30 | 2013-12-27 | 2021-10-02 | 2022-01-29
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC026-013 | Aaron Davis Hall | 3 | FINAL DESIGN | 2013-12-28 | 2014-06-25 | 2022-01-30 | 2022-07-28
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC026-013 | Aaron Davis Hall | 4 | BID AWARD AND REGISTER CONTRCT | 2014-06-26 | 2014-09-23 | 2022-07-29 | 2022-10-26
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC026-013 | Aaron Davis Hall | 5 | CONSTRUCTION TO 25% | 2014-09-24 | 2015-01-21 | 2022-10-27 | 2023-02-23
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC026-013 | Aaron Davis Hall | 6 | CONSTRUCTION TO 50% | 2015-01-22 | 2015-05-21 | 2023-02-24 | 2023-06-23
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC026-013 | Aaron Davis Hall | 7 | CONSTRUCTION TO 75% | 2015-05-22 | 2015-09-18 | 2023-06-24 | 2023-10-21
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC026-013 | Aaron Davis Hall | 8 | ORIGINAL EQUIP & FURNISHING | 2015-09-19 | 2015-12-17 | 2023-10-22 | 2024-01-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC026-013 | Aaron Davis Hall | 9 | SUBSTANTIAL COMPLETION | 2015-12-18 | 2016-02-15 | 2024-01-20 | 2024-03-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC026-013 | Aaron Davis Hall | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-02-16 | 2016-03-16 | 2025-05-19 | 2025-08-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC027-014 | Max Bond Center | 1 | DEVELOP SCOPE | 2014-06-01 | 2014-08-29 | 2021-07-01 | 2021-10-01
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC027-014 | Max Bond Center | 2 | PRELIMINARY DESIGN | 2014-08-30 | 2014-12-27 | 2021-10-02 | 2022-01-29
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC027-014 | Max Bond Center | 3 | FINAL DESIGN | 2014-12-28 | 2015-06-25 | 2022-01-30 | 2022-07-28
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC027-014 | Max Bond Center | 4 | BID AWARD AND REGISTER CONTRCT | 2015-06-26 | 2015-09-23 | 2022-07-29 | 2022-10-26
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC027-014 | Max Bond Center | 5 | CONSTRUCTION TO 25% | 2015-09-24 | 2016-01-21 | 2022-10-27 | 2023-02-23
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC027-014 | Max Bond Center | 6 | CONSTRUCTION TO 50% | 2016-01-22 | 2016-05-20 | 2023-02-24 | 2023-06-23
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC027-014 | Max Bond Center | 7 | CONSTRUCTION TO 75% | 2016-05-21 | 2016-09-17 | 2023-06-24 | 2023-10-21
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC027-014 | Max Bond Center | 8 | ORIGINAL EQUIP & FURNISHING | 2016-09-18 | 2016-12-16 | 2023-10-22 | 2024-01-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC027-014 | Max Bond Center | 9 | SUBSTANTIAL COMPLETION | 2016-12-17 | 2017-02-14 | 2024-01-20 | 2024-03-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC027-014 | Max Bond Center | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-02-15 | 2017-03-16 | 2024-03-20 | 2030-05-02
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC029-014 | Network Infrastructure Modernization | 1 | DEVELOP SCOPE | 2014-06-01 | 2014-08-29 | 2014-06-01 | 2014-08-29
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC029-014 | Network Infrastructure Modernization | 2 | PRELIMINARY DESIGN | 2014-08-30 | 2014-12-27 | 2014-08-30 | 2014-12-27
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC029-014 | Network Infrastructure Modernization | 3 | FINAL DESIGN | 2014-12-28 | 2015-06-25 | 2014-12-28 | 2015-06-25
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC029-014 | Network Infrastructure Modernization | 4 | BID AWARD AND REGISTER CONTRCT | 2015-06-26 | 2015-09-23 | 2015-06-26 | 2015-09-23
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC029-014 | Network Infrastructure Modernization | 5 | CONSTRUCTION TO 25% | 2015-09-24 | 2016-01-21 | 2015-09-24 | 2016-01-21
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC029-014 | Network Infrastructure Modernization | 6 | CONSTRUCTION TO 50% | 2016-01-22 | 2016-05-20 | 2016-01-22 | 2016-05-20
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC029-014 | Network Infrastructure Modernization | 7 | CONSTRUCTION TO 75% | 2016-05-21 | 2016-09-17 | 2016-05-21 | 2016-09-17
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC029-014 | Network Infrastructure Modernization | 8 | ORIGINAL EQUIP & FURNISHING | 2016-09-18 | 2016-12-16 | 2016-09-18 | 2016-12-16
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC029-014 | Network Infrastructure Modernization | 9 | SUBSTANTIAL COMPLETION | 2016-12-17 | 2017-02-14 | 2016-12-17 | 2017-02-14
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC029-014 | Network Infrastructure Modernization | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-02-15 | 2017-03-16 | 2017-02-15 | 2026-03-31
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC032-015 | City College Computer Lab | 1 | DEVELOP SCOPE | 2015-03-01 | 2015-05-29 | 2015-03-01 | 2015-05-29
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC032-015 | City College Computer Lab | 2 | PRELIMINARY DESIGN | 2015-05-30 | 2015-09-26 | 2015-05-30 | 2015-09-26
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC032-015 | City College Computer Lab | 3 | FINAL DESIGN | 2015-09-27 | 2016-03-24 | 2015-09-27 | 2016-03-24
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC032-015 | City College Computer Lab | 4 | BID AWARD AND REGISTER CONTRCT | 2016-03-25 | 2016-06-22 | 2016-03-25 | 2016-06-22
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC032-015 | City College Computer Lab | 5 | CONSTRUCTION TO 25% | 2016-06-23 | 2016-10-20 | 2016-06-23 | 2016-10-20
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC032-015 | City College Computer Lab | 6 | CONSTRUCTION TO 50% | 2016-10-21 | 2017-02-17 | 2016-10-21 | 2017-02-17
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC032-015 | City College Computer Lab | 7 | CONSTRUCTION TO 75% | 2017-02-18 | 2017-06-17 | 2017-02-18 | 2017-06-17
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC032-015 | City College Computer Lab | 8 | ORIGINAL EQUIP & FURNISHING | 2017-06-18 | 2017-09-15 | 2017-06-18 | 2017-09-15
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC032-015 | City College Computer Lab | 9 | SUBSTANTIAL COMPLETION | 2017-09-16 | 2017-11-14 | 2017-09-16 | 2017-11-14
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC032-015 | City College Computer Lab | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-11-15 | 2017-12-14 | 2017-11-15 | 2026-12-31
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC034-016 | Computer Lab Renovation | 1 | DEVELOP SCOPE | 2015-06-01 | 2015-08-29 | 2015-06-01 | 2015-08-29
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC034-016 | Computer Lab Renovation | 2 | PRELIMINARY DESIGN | 2015-08-30 | 2015-12-27 | 2015-08-30 | 2015-12-27
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC034-016 | Computer Lab Renovation | 3 | FINAL DESIGN | 2015-12-28 | 2016-06-24 | 2015-12-28 | 2016-06-24
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC034-016 | Computer Lab Renovation | 4 | BID AWARD AND REGISTER CONTRCT | 2016-06-25 | 2016-09-22 | 2016-06-25 | 2016-09-22
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC034-016 | Computer Lab Renovation | 5 | CONSTRUCTION TO 25% | 2016-09-23 | 2017-01-20 | 2016-09-23 | 2017-01-20
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC034-016 | Computer Lab Renovation | 6 | CONSTRUCTION TO 50% | 2017-01-21 | 2017-05-20 | 2017-01-21 | 2017-05-20
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC034-016 | Computer Lab Renovation | 7 | CONSTRUCTION TO 75% | 2017-05-21 | 2017-09-17 | 2017-05-21 | 2017-09-17
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC034-016 | Computer Lab Renovation | 8 | ORIGINAL EQUIP & FURNISHING | 2017-09-18 | 2017-12-16 | 2017-09-18 | 2017-12-16
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC034-016 | Computer Lab Renovation | 9 | SUBSTANTIAL COMPLETION | 2017-12-17 | 2018-02-14 | 2017-12-17 | 2018-02-14
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC034-016 | Computer Lab Renovation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-02-15 | 2018-03-16 | 2018-02-15 | 2026-03-31
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC037-017 | Harlem Rooftop Garden | 1 | DEVELOP SCOPE | 2017-06-01 | 2017-08-29 | 2021-07-01 | 2021-10-01
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC037-017 | Harlem Rooftop Garden | 2 | PRELIMINARY DESIGN | 2017-08-30 | 2017-12-27 | 2021-10-02 | 2022-01-29
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC037-017 | Harlem Rooftop Garden | 3 | FINAL DESIGN | 2017-12-28 | 2018-06-25 | 2022-01-30 | 2022-07-28
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC037-017 | Harlem Rooftop Garden | 4 | BID AWARD AND REGISTER CONTRCT | 2018-06-26 | 2018-09-23 | 2022-07-29 | 2022-10-26
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC037-017 | Harlem Rooftop Garden | 5 | CONSTRUCTION TO 25% | 2018-09-24 | 2019-01-21 | 2022-10-27 | 2023-02-23
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC037-017 | Harlem Rooftop Garden | 6 | CONSTRUCTION TO 50% | 2019-01-22 | 2019-05-21 | 2023-02-24 | 2023-06-23
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC037-017 | Harlem Rooftop Garden | 7 | CONSTRUCTION TO 75% | 2019-05-22 | 2019-09-18 | 2023-06-24 | 2023-10-21
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC037-017 | Harlem Rooftop Garden | 8 | ORIGINAL EQUIP & FURNISHING | 2019-09-19 | 2019-12-17 | 2023-10-22 | 2024-01-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC037-017 | Harlem Rooftop Garden | 9 | SUBSTANTIAL COMPLETION | 2019-12-18 | 2020-02-15 | 2024-01-20 | 2024-03-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC037-017 | Harlem Rooftop Garden | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-02-16 | 2020-03-16 | 2024-03-20 | 2027-05-02
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC039-017 | Street Improvements | 1 | DEVELOP SCOPE | 2017-06-01 | 2017-08-29 | 2022-07-01 | 2022-10-01
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC039-017 | Street Improvements | 2 | PRELIMINARY DESIGN | 2017-08-30 | 2017-12-27 | 2022-10-02 | 2023-01-29
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC039-017 | Street Improvements | 3 | FINAL DESIGN | 2017-12-28 | 2018-06-25 | 2023-01-30 | 2023-07-28
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC039-017 | Street Improvements | 4 | BID AWARD AND REGISTER CONTRCT | 2018-06-26 | 2018-09-23 | 2023-07-29 | 2023-10-26
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC039-017 | Street Improvements | 5 | CONSTRUCTION TO 25% | 2018-09-24 | 2019-01-21 | 2023-10-27 | 2024-02-23
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC039-017 | Street Improvements | 6 | CONSTRUCTION TO 50% | 2019-01-22 | 2019-05-21 | 2024-02-24 | 2024-06-22
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC039-017 | Street Improvements | 7 | CONSTRUCTION TO 75% | 2019-05-22 | 2019-09-18 | 2024-06-23 | 2024-10-20
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC039-017 | Street Improvements | 8 | ORIGINAL EQUIP & FURNISHING | 2019-09-19 | 2019-12-17 | 2024-10-21 | 2025-01-18
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC039-017 | Street Improvements | 9 | SUBSTANTIAL COMPLETION | 2019-12-18 | 2020-02-15 | 2025-01-19 | 2025-03-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC039-017 | Street Improvements | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-02-16 | 2020-03-16 | 2025-03-20 | 2029-05-03
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC041-018 | Wireless Network Upgrade Expansion | 1 | DEVELOP SCOPE | 2018-06-01 | 2018-08-29 | 2018-06-01 | 2018-08-29
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC041-018 | Wireless Network Upgrade Expansion | 2 | PRELIMINARY DESIGN | 2018-08-30 | 2018-12-27 | 2018-08-30 | 2018-12-27
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC041-018 | Wireless Network Upgrade Expansion | 3 | FINAL DESIGN | 2018-12-28 | 2019-06-25 | 2018-12-28 | 2019-06-25
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC041-018 | Wireless Network Upgrade Expansion | 4 | BID AWARD AND REGISTER CONTRCT | 2019-06-26 | 2019-09-23 | 2019-06-26 | 2019-09-23
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC041-018 | Wireless Network Upgrade Expansion | 5 | CONSTRUCTION TO 25% | 2019-09-24 | 2020-01-21 | 2019-09-24 | 2020-01-21
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC041-018 | Wireless Network Upgrade Expansion | 6 | CONSTRUCTION TO 50% | 2020-01-22 | 2020-05-20 | 2020-01-22 | 2020-05-20
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC041-018 | Wireless Network Upgrade Expansion | 7 | CONSTRUCTION TO 75% | 2020-05-21 | 2020-09-17 | 2020-05-21 | 2020-09-17
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC041-018 | Wireless Network Upgrade Expansion | 8 | ORIGINAL EQUIP & FURNISHING | 2020-09-18 | 2020-12-16 | 2020-09-18 | 2020-12-16
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC041-018 | Wireless Network Upgrade Expansion | 9 | SUBSTANTIAL COMPLETION | 2020-12-17 | 2021-02-14 | 2020-12-17 | 2021-02-14
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC041-018 | Wireless Network Upgrade Expansion | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-02-15 | 2021-03-16 | 2021-02-15 | 2024-03-31
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC042-018 | Facility Upgrades | 1 | DEVELOP SCOPE | 2018-06-01 | 2018-08-29 | 2021-07-01 | 2021-10-01
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC042-018 | Facility Upgrades | 2 | PRELIMINARY DESIGN | 2018-08-30 | 2018-12-27 | 2021-10-02 | 2022-01-29
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC042-018 | Facility Upgrades | 3 | FINAL DESIGN | 2018-12-28 | 2019-06-25 | 2022-01-30 | 2022-07-28
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC042-018 | Facility Upgrades | 4 | BID AWARD AND REGISTER CONTRCT | 2019-06-26 | 2019-09-23 | 2022-07-29 | 2022-10-26
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC042-018 | Facility Upgrades | 5 | CONSTRUCTION TO 25% | 2019-09-24 | 2020-01-21 | 2022-10-27 | 2023-02-23
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC042-018 | Facility Upgrades | 6 | CONSTRUCTION TO 50% | 2020-01-22 | 2020-05-20 | 2023-02-24 | 2023-06-23
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC042-018 | Facility Upgrades | 7 | CONSTRUCTION TO 75% | 2020-05-21 | 2020-09-17 | 2023-06-24 | 2023-10-21
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC042-018 | Facility Upgrades | 8 | ORIGINAL EQUIP & FURNISHING | 2020-09-18 | 2020-12-16 | 2023-10-22 | 2024-01-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC042-018 | Facility Upgrades | 9 | SUBSTANTIAL COMPLETION | 2020-12-17 | 2021-02-14 | 2024-01-20 | 2024-03-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC042-018 | Facility Upgrades | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-02-15 | 2021-03-16 | 2024-03-20 | 2027-05-04
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC045-019 | Kitchen Upgrade for the Culinary Program | 1 | DEVELOP SCOPE | 2019-06-01 | 2019-08-29 | 2020-07-01 | 2020-10-01
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC045-019 | Kitchen Upgrade for the Culinary Program | 2 | PRELIMINARY DESIGN | 2019-08-30 | 2019-12-27 | 2020-10-02 | 2021-01-29
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC045-019 | Kitchen Upgrade for the Culinary Program | 3 | FINAL DESIGN | 2019-12-28 | 2020-06-24 | 2021-01-30 | 2021-07-28
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC045-019 | Kitchen Upgrade for the Culinary Program | 4 | BID AWARD AND REGISTER CONTRCT | 2020-06-25 | 2020-09-22 | 2021-07-29 | 2021-10-26
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC045-019 | Kitchen Upgrade for the Culinary Program | 5 | CONSTRUCTION TO 25% | 2020-09-23 | 2021-01-20 | 2021-10-27 | 2022-02-23
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC045-019 | Kitchen Upgrade for the Culinary Program | 6 | CONSTRUCTION TO 50% | 2021-01-21 | 2021-05-20 | 2022-02-24 | 2022-06-23
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC045-019 | Kitchen Upgrade for the Culinary Program | 7 | CONSTRUCTION TO 75% | 2021-05-21 | 2021-09-17 | 2022-06-24 | 2022-10-21
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC045-019 | Kitchen Upgrade for the Culinary Program | 8 | ORIGINAL EQUIP & FURNISHING | 2021-09-18 | 2021-12-16 | 2022-10-22 | 2023-01-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC045-019 | Kitchen Upgrade for the Culinary Program | 9 | SUBSTANTIAL COMPLETION | 2021-12-17 | 2022-02-14 | 2023-01-20 | 2023-03-20
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | CC045-019 | Kitchen Upgrade for the Culinary Program | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-02-15 | 2022-03-16 | 2023-03-21 | 2026-04-30
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR009-009 | CLASSROOM EXPANSION PROJECT | 1 | DEVELOP SCOPE | 2009-06-01 | 2009-08-29 | 2009-06-01 | 2009-08-29
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR009-009 | CLASSROOM EXPANSION PROJECT | 2 | PRELIMINARY DESIGN | 2009-08-30 | 2009-12-27 | 2009-08-30 | 2009-12-27
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR009-009 | CLASSROOM EXPANSION PROJECT | 3 | FINAL DESIGN | 2009-12-28 | 2010-06-25 | 2009-12-28 | 2010-06-25
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR009-009 | CLASSROOM EXPANSION PROJECT | 4 | BID AWARD AND REGISTER CONTRCT | 2010-06-26 | 2010-09-23 | 2010-06-26 | 2010-09-23
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR009-009 | CLASSROOM EXPANSION PROJECT | 5 | CONSTRUCTION TO 25% | 2010-09-24 | 2011-01-21 | 2010-09-24 | 2011-01-21
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR009-009 | CLASSROOM EXPANSION PROJECT | 6 | CONSTRUCTION TO 50% | 2011-01-22 | 2011-05-21 | 2011-01-22 | 2011-05-21
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR009-009 | CLASSROOM EXPANSION PROJECT | 7 | CONSTRUCTION TO 75% | 2011-05-22 | 2011-09-18 | 2011-05-22 | 2011-09-18
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR009-009 | CLASSROOM EXPANSION PROJECT | 8 | ORIGINAL EQUIP & FURNISHING | 2011-09-19 | 2011-12-17 | 2011-09-19 | 2011-12-17
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR009-009 | CLASSROOM EXPANSION PROJECT | 9 | SUBSTANTIAL COMPLETION | 2011-12-18 | 2012-02-15 | 2011-12-18 | 2012-02-15
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR009-009 | CLASSROOM EXPANSION PROJECT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-02-16 | 2012-03-16 | 2012-02-16 | 2026-06-30
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR012-011 | Green Roof / Space Conversion | 1 | DEVELOP SCOPE | 2011-06-01 | 2011-08-29 | 2020-07-01 | 2020-09-29
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR012-011 | Green Roof / Space Conversion | 2 | PRELIMINARY DESIGN | 2011-08-30 | 2011-12-27 | 2020-09-30 | 2021-01-27
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR012-011 | Green Roof / Space Conversion | 3 | FINAL DESIGN | 2011-12-28 | 2012-06-24 | 2021-01-28 | 2021-07-26
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR012-011 | Green Roof / Space Conversion | 4 | BID AWARD AND REGISTER CONTRCT | 2012-06-25 | 2012-09-22 | 2021-07-27 | 2021-10-24
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR012-011 | Green Roof / Space Conversion | 5 | CONSTRUCTION TO 25% | 2012-09-23 | 2013-01-20 | 2021-10-25 | 2022-02-21
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR012-011 | Green Roof / Space Conversion | 6 | CONSTRUCTION TO 50% | 2013-01-21 | 2013-05-20 | 2022-02-22 | 2022-06-21
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR012-011 | Green Roof / Space Conversion | 7 | CONSTRUCTION TO 75% | 2013-05-21 | 2013-09-17 | 2022-06-22 | 2022-10-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR012-011 | Green Roof / Space Conversion | 8 | ORIGINAL EQUIP & FURNISHING | 2013-09-18 | 2013-12-16 | 2022-10-20 | 2023-01-17
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR012-011 | Green Roof / Space Conversion | 9 | SUBSTANTIAL COMPLETION | 2013-12-17 | 2014-02-14 | 2023-01-18 | 2023-03-18
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR012-011 | Green Roof / Space Conversion | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-02-15 | 2014-03-16 | 2023-03-19 | 2026-06-30
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR013-012 | Classroom Expansion Project - Roof | 1 | DEVELOP SCOPE | 2012-06-01 | 2012-08-29 | 2020-07-01 | 2020-09-29
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR013-012 | Classroom Expansion Project - Roof | 2 | PRELIMINARY DESIGN | 2012-08-30 | 2012-12-27 | 2020-09-30 | 2021-01-27
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR013-012 | Classroom Expansion Project - Roof | 3 | FINAL DESIGN | 2012-12-28 | 2013-06-25 | 2021-01-28 | 2021-07-26
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR013-012 | Classroom Expansion Project - Roof | 4 | BID AWARD AND REGISTER CONTRCT | 2013-06-26 | 2013-09-23 | 2021-07-27 | 2021-10-24
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR013-012 | Classroom Expansion Project - Roof | 5 | CONSTRUCTION TO 25% | 2013-09-24 | 2014-01-21 | 2021-10-25 | 2022-02-21
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR013-012 | Classroom Expansion Project - Roof | 6 | CONSTRUCTION TO 50% | 2014-01-22 | 2014-05-21 | 2022-02-22 | 2022-06-21
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR013-012 | Classroom Expansion Project - Roof | 7 | CONSTRUCTION TO 75% | 2014-05-22 | 2014-09-18 | 2022-06-22 | 2022-10-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR013-012 | Classroom Expansion Project - Roof | 8 | ORIGINAL EQUIP & FURNISHING | 2014-09-19 | 2014-12-17 | 2022-10-20 | 2023-01-17
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR013-012 | Classroom Expansion Project - Roof | 9 | SUBSTANTIAL COMPLETION | 2014-12-18 | 2015-02-15 | 2023-01-18 | 2023-03-18
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR013-012 | Classroom Expansion Project - Roof | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-02-16 | 2015-03-17 | 2023-03-19 | 2026-04-30
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR014-013 | Classroom Development Project (9th Floor) | 1 | DEVELOP SCOPE | 2013-06-01 | 2013-08-29 | 2020-07-01 | 2020-09-28
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR014-013 | Classroom Development Project (9th Floor) | 2 | PRELIMINARY DESIGN | 2013-08-30 | 2013-12-27 | 2020-09-29 | 2021-01-26
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR014-013 | Classroom Development Project (9th Floor) | 3 | FINAL DESIGN | 2013-12-28 | 2014-06-25 | 2021-01-27 | 2021-07-25
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR014-013 | Classroom Development Project (9th Floor) | 4 | BID AWARD AND REGISTER CONTRCT | 2014-06-26 | 2014-09-23 | 2021-07-26 | 2021-10-23
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR014-013 | Classroom Development Project (9th Floor) | 5 | CONSTRUCTION TO 25% | 2014-09-24 | 2015-01-21 | 2021-10-24 | 2022-02-20
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR014-013 | Classroom Development Project (9th Floor) | 6 | CONSTRUCTION TO 50% | 2015-01-22 | 2015-05-21 | 2022-02-21 | 2022-06-20
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR014-013 | Classroom Development Project (9th Floor) | 7 | CONSTRUCTION TO 75% | 2015-05-22 | 2015-09-18 | 2022-06-21 | 2022-10-18
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR014-013 | Classroom Development Project (9th Floor) | 8 | ORIGINAL EQUIP & FURNISHING | 2015-09-19 | 2015-12-17 | 2022-10-19 | 2023-01-16
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR014-013 | Classroom Development Project (9th Floor) | 9 | SUBSTANTIAL COMPLETION | 2015-12-18 | 2016-02-15 | 2023-01-17 | 2023-03-17
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR014-013 | Classroom Development Project (9th Floor) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-02-16 | 2016-03-16 | 2023-03-18 | 2026-04-30
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR017-014 | Bathroom and HVAC Upgrades | 1 | DEVELOP SCOPE | 2014-06-01 | 2014-08-29 | 2014-06-01 | 2014-08-29
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR017-014 | Bathroom and HVAC Upgrades | 2 | PRELIMINARY DESIGN | 2014-08-30 | 2014-12-27 | 2014-08-30 | 2014-12-27
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR017-014 | Bathroom and HVAC Upgrades | 3 | FINAL DESIGN | 2014-12-28 | 2015-06-25 | 2014-12-28 | 2015-06-25
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR017-014 | Bathroom and HVAC Upgrades | 4 | BID AWARD AND REGISTER CONTRCT | 2015-06-26 | 2015-09-23 | 2015-06-26 | 2015-09-23
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR017-014 | Bathroom and HVAC Upgrades | 5 | CONSTRUCTION TO 25% | 2015-09-24 | 2016-01-21 | 2015-09-24 | 2016-01-21
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR017-014 | Bathroom and HVAC Upgrades | 6 | CONSTRUCTION TO 50% | 2016-01-22 | 2016-05-20 | 2016-01-22 | 2016-05-20
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR017-014 | Bathroom and HVAC Upgrades | 7 | CONSTRUCTION TO 75% | 2016-05-21 | 2016-09-17 | 2016-05-21 | 2016-09-17
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR017-014 | Bathroom and HVAC Upgrades | 8 | ORIGINAL EQUIP & FURNISHING | 2016-09-18 | 2016-12-16 | 2016-09-18 | 2016-12-16
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR017-014 | Bathroom and HVAC Upgrades | 9 | SUBSTANTIAL COMPLETION | 2016-12-17 | 2017-02-14 | 2016-12-17 | 2017-02-14
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR017-014 | Bathroom and HVAC Upgrades | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-02-15 | 2017-03-16 | 2017-02-15 | 2027-03-31
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR018-015 | Library Renovations | 1 | DEVELOP SCOPE | 2014-10-01 | 2014-12-29 | 2020-07-01 | 2020-10-01
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR018-015 | Library Renovations | 2 | PRELIMINARY DESIGN | 2014-12-30 | 2015-04-28 | 2020-10-02 | 2021-01-29
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR018-015 | Library Renovations | 3 | FINAL DESIGN | 2015-04-29 | 2015-10-25 | 2021-01-30 | 2021-07-28
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR018-015 | Library Renovations | 4 | BID AWARD AND REGISTER CONTRCT | 2015-10-26 | 2016-01-23 | 2021-07-29 | 2021-10-26
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR018-015 | Library Renovations | 5 | CONSTRUCTION TO 25% | 2016-01-24 | 2016-05-22 | 2021-10-27 | 2022-02-23
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR018-015 | Library Renovations | 6 | CONSTRUCTION TO 50% | 2016-05-23 | 2016-09-19 | 2022-02-24 | 2022-06-23
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR018-015 | Library Renovations | 7 | CONSTRUCTION TO 75% | 2016-09-20 | 2017-01-17 | 2022-06-24 | 2022-10-21
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR018-015 | Library Renovations | 8 | ORIGINAL EQUIP & FURNISHING | 2017-01-18 | 2017-04-17 | 2022-10-22 | 2023-01-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR018-015 | Library Renovations | 9 | SUBSTANTIAL COMPLETION | 2017-04-18 | 2017-06-16 | 2023-01-20 | 2023-03-20
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR018-015 | Library Renovations | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-06-17 | 2017-07-16 | 2023-03-21 | 2028-05-03
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR023-017 | Improvement of Public Spaces | 1 | DEVELOP SCOPE | 2017-06-01 | 2017-08-29 | 2022-07-01 | 2022-10-01
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR023-017 | Improvement of Public Spaces | 2 | PRELIMINARY DESIGN | 2017-08-30 | 2017-12-27 | 2022-10-02 | 2023-01-29
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR023-017 | Improvement of Public Spaces | 3 | FINAL DESIGN | 2017-12-28 | 2018-06-25 | 2023-01-30 | 2023-07-28
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR023-017 | Improvement of Public Spaces | 4 | BID AWARD AND REGISTER CONTRCT | 2018-06-26 | 2018-09-23 | 2023-07-29 | 2023-10-26
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR023-017 | Improvement of Public Spaces | 5 | CONSTRUCTION TO 25% | 2018-09-24 | 2019-01-21 | 2023-10-27 | 2024-02-23
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR023-017 | Improvement of Public Spaces | 6 | CONSTRUCTION TO 50% | 2019-01-22 | 2019-05-21 | 2024-02-24 | 2024-06-22
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR023-017 | Improvement of Public Spaces | 7 | CONSTRUCTION TO 75% | 2019-05-22 | 2019-09-18 | 2024-06-23 | 2024-10-20
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR023-017 | Improvement of Public Spaces | 8 | ORIGINAL EQUIP & FURNISHING | 2019-09-19 | 2019-12-17 | 2024-10-21 | 2025-01-18
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR023-017 | Improvement of Public Spaces | 9 | SUBSTANTIAL COMPLETION | 2019-12-18 | 2020-02-15 | 2025-01-19 | 2025-03-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR023-017 | Improvement of Public Spaces | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-02-16 | 2020-03-16 | 2025-03-20 | 2030-05-03
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR029-020 | AUDITORIUM SOUND SYSTEM | 1 | DEVELOP SCOPE | 2020-06-30 | 2020-09-27 | 2020-06-30 | 2020-09-27
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR029-020 | AUDITORIUM SOUND SYSTEM | 2 | PRELIMINARY DESIGN | 2020-09-28 | 2021-01-25 | 2020-09-28 | 2021-01-25
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR029-020 | AUDITORIUM SOUND SYSTEM | 3 | FINAL DESIGN | 2021-01-26 | 2021-07-24 | 2021-01-26 | 2021-07-24
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR029-020 | AUDITORIUM SOUND SYSTEM | 4 | BID AWARD AND REGISTER CONTRCT | 2021-07-25 | 2021-10-22 | 2021-07-25 | 2021-10-22
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR029-020 | AUDITORIUM SOUND SYSTEM | 5 | CONSTRUCTION TO 25% | 2021-10-23 | 2022-02-19 | 2021-10-23 | 2022-02-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR029-020 | AUDITORIUM SOUND SYSTEM | 6 | CONSTRUCTION TO 50% | 2022-02-20 | 2022-06-19 | 2022-02-20 | 2022-06-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR029-020 | AUDITORIUM SOUND SYSTEM | 7 | CONSTRUCTION TO 75% | 2022-06-20 | 2022-10-17 | 2022-06-20 | 2022-10-17
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR029-020 | AUDITORIUM SOUND SYSTEM | 8 | ORIGINAL EQUIP & FURNISHING | 2022-10-18 | 2023-01-15 | 2022-10-18 | 2023-01-15
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR029-020 | AUDITORIUM SOUND SYSTEM | 9 | SUBSTANTIAL COMPLETION | 2023-01-16 | 2023-03-16 | 2023-01-16 | 2023-03-16
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR029-020 | AUDITORIUM SOUND SYSTEM | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-03-17 | 2023-04-15 | 2023-03-17 | 2027-04-30
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR030-020 | Feminist Institute Lounge | 1 | DEVELOP SCOPE | 2020-06-30 | 2020-09-27 | 2020-06-30 | 2020-09-27
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR030-020 | Feminist Institute Lounge | 2 | PRELIMINARY DESIGN | 2020-09-28 | 2021-01-25 | 2020-09-28 | 2021-01-25
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR030-020 | Feminist Institute Lounge | 3 | FINAL DESIGN | 2021-01-26 | 2021-07-24 | 2021-01-26 | 2021-07-24
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR030-020 | Feminist Institute Lounge | 4 | BID AWARD AND REGISTER CONTRCT | 2021-07-25 | 2021-10-22 | 2021-07-25 | 2021-10-22
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR030-020 | Feminist Institute Lounge | 5 | CONSTRUCTION TO 25% | 2021-10-23 | 2022-02-19 | 2021-10-23 | 2022-02-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR030-020 | Feminist Institute Lounge | 6 | CONSTRUCTION TO 50% | 2022-02-20 | 2022-06-19 | 2022-02-20 | 2022-06-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR030-020 | Feminist Institute Lounge | 7 | CONSTRUCTION TO 75% | 2022-06-20 | 2022-10-17 | 2022-06-20 | 2022-10-17
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR030-020 | Feminist Institute Lounge | 8 | ORIGINAL EQUIP & FURNISHING | 2022-10-18 | 2023-01-15 | 2022-10-18 | 2023-01-15
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR030-020 | Feminist Institute Lounge | 9 | SUBSTANTIAL COMPLETION | 2023-01-16 | 2023-03-16 | 2023-01-16 | 2023-03-16
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GR030-020 | Feminist Institute Lounge | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-03-17 | 2023-04-15 | 2023-03-17 | 2027-04-30
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GU031-013 | New Community College Student Lab Renovations | 1 | DEVELOP SCOPE | 2013-06-01 | 2013-08-29 | 2022-07-01 | 2022-09-28
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GU031-013 | New Community College Student Lab Renovations | 2 | PRELIMINARY DESIGN | 2013-08-30 | 2013-12-27 | 2022-09-29 | 2023-01-26
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GU031-013 | New Community College Student Lab Renovations | 3 | FINAL DESIGN | 2013-12-28 | 2014-06-25 | 2023-01-27 | 2023-07-25
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GU031-013 | New Community College Student Lab Renovations | 4 | BID AWARD AND REGISTER CONTRCT | 2014-06-26 | 2014-09-23 | 2023-07-26 | 2023-10-23
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GU031-013 | New Community College Student Lab Renovations | 5 | CONSTRUCTION TO 25% | 2014-09-24 | 2015-01-21 | 2023-10-24 | 2024-02-20
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GU031-013 | New Community College Student Lab Renovations | 6 | CONSTRUCTION TO 50% | 2015-01-22 | 2015-05-21 | 2024-02-21 | 2024-06-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GU031-013 | New Community College Student Lab Renovations | 7 | CONSTRUCTION TO 75% | 2015-05-22 | 2015-09-18 | 2024-06-20 | 2024-10-17
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GU031-013 | New Community College Student Lab Renovations | 8 | ORIGINAL EQUIP & FURNISHING | 2015-09-19 | 2015-12-17 | 2024-10-18 | 2025-01-15
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GU031-013 | New Community College Student Lab Renovations | 9 | SUBSTANTIAL COMPLETION | 2015-12-18 | 2016-02-15 | 2025-01-16 | 2025-03-16
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GU031-013 | New Community College Student Lab Renovations | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-02-16 | 2016-03-16 | 2025-03-17 | 2025-04-16
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GU051-015 | Guttman Comm. Coll. Building Canopy | 1 | DEVELOP SCOPE | 2014-10-01 | 2014-12-29 | 2014-10-01 | 2014-12-29
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GU051-015 | Guttman Comm. Coll. Building Canopy | 2 | PRELIMINARY DESIGN | 2014-12-30 | 2015-04-28 | 2014-12-30 | 2015-04-28
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GU051-015 | Guttman Comm. Coll. Building Canopy | 3 | FINAL DESIGN | 2015-04-29 | 2015-10-25 | 2015-04-29 | 2015-10-25
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GU051-015 | Guttman Comm. Coll. Building Canopy | 4 | BID AWARD AND REGISTER CONTRCT | 2015-10-26 | 2016-01-23 | 2015-10-26 | 2016-01-23
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GU051-015 | Guttman Comm. Coll. Building Canopy | 5 | CONSTRUCTION TO 25% | 2016-01-24 | 2016-05-22 | 2016-01-24 | 2016-05-22
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GU051-015 | Guttman Comm. Coll. Building Canopy | 6 | CONSTRUCTION TO 50% | 2016-05-23 | 2016-09-19 | 2016-05-23 | 2016-09-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GU051-015 | Guttman Comm. Coll. Building Canopy | 7 | CONSTRUCTION TO 75% | 2016-09-20 | 2017-01-17 | 2016-09-20 | 2017-01-17
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GU051-015 | Guttman Comm. Coll. Building Canopy | 8 | ORIGINAL EQUIP & FURNISHING | 2017-01-18 | 2017-04-17 | 2017-01-18 | 2017-04-17
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GU051-015 | Guttman Comm. Coll. Building Canopy | 9 | SUBSTANTIAL COMPLETION | 2017-04-18 | 2017-06-16 | 2017-04-18 | 2017-06-16
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | GU051-015 | Guttman Comm. Coll. Building Canopy | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-06-17 | 2017-07-16 | 2017-06-17 | 2024-07-31
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HC001-021 | Athletic Facility Renovation | 1 | DEVELOP SCOPE | 2021-06-30 | 2021-09-27 | 2021-06-30 | 2021-09-27
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HC001-021 | Athletic Facility Renovation | 2 | PRELIMINARY DESIGN | 2021-09-28 | 2022-01-25 | 2021-09-28 | 2022-01-25
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HC001-021 | Athletic Facility Renovation | 3 | FINAL DESIGN | 2022-01-26 | 2022-07-24 | 2022-01-26 | 2022-07-24
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HC001-021 | Athletic Facility Renovation | 4 | BID AWARD AND REGISTER CONTRCT | 2022-07-25 | 2022-10-22 | 2022-07-25 | 2022-10-22
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HC001-021 | Athletic Facility Renovation | 5 | CONSTRUCTION TO 25% | 2022-10-23 | 2023-02-19 | 2022-10-23 | 2023-02-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HC001-021 | Athletic Facility Renovation | 6 | CONSTRUCTION TO 50% | 2023-02-20 | 2023-06-19 | 2023-02-20 | 2023-06-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HC001-021 | Athletic Facility Renovation | 7 | CONSTRUCTION TO 75% | 2023-06-20 | 2023-10-17 | 2023-06-20 | 2023-10-17
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HC001-021 | Athletic Facility Renovation | 8 | ORIGINAL EQUIP & FURNISHING | 2023-10-18 | 2024-01-15 | 2023-10-18 | 2024-01-15
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HC001-021 | Athletic Facility Renovation | 9 | SUBSTANTIAL COMPLETION | 2024-01-16 | 2024-03-15 | 2024-01-16 | 2024-03-15
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HC001-021 | Athletic Facility Renovation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-03-16 | 2024-04-14 | 2024-03-16 | 2024-04-14
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HC026-011 | Phone System Upgrade And Expansion | 1 | DEVELOP SCOPE | 2011-06-01 | 2011-08-29 | 2011-06-01 | 2011-08-29
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HC026-011 | Phone System Upgrade And Expansion | 2 | PRELIMINARY DESIGN | 2011-08-30 | 2011-12-27 | 2011-08-30 | 2011-12-27
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HC026-011 | Phone System Upgrade And Expansion | 3 | FINAL DESIGN | 2011-12-28 | 2012-06-24 | 2011-12-28 | 2012-06-24
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HC026-011 | Phone System Upgrade And Expansion | 4 | BID AWARD AND REGISTER CONTRCT | 2012-06-25 | 2012-09-22 | 2012-06-25 | 2012-09-22
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HC026-011 | Phone System Upgrade And Expansion | 5 | CONSTRUCTION TO 25% | 2012-09-23 | 2013-01-20 | 2012-09-23 | 2013-01-20
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HC026-011 | Phone System Upgrade And Expansion | 6 | CONSTRUCTION TO 50% | 2013-01-21 | 2013-05-20 | 2013-01-21 | 2013-05-20
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HC026-011 | Phone System Upgrade And Expansion | 7 | CONSTRUCTION TO 75% | 2013-05-21 | 2013-09-17 | 2013-05-21 | 2013-09-17
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HC026-011 | Phone System Upgrade And Expansion | 8 | ORIGINAL EQUIP & FURNISHING | 2013-09-18 | 2013-12-16 | 2013-09-18 | 2013-12-16
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HC026-011 | Phone System Upgrade And Expansion | 9 | SUBSTANTIAL COMPLETION | 2013-12-17 | 2014-02-14 | 2013-12-17 | 2014-02-14
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HC026-011 | Phone System Upgrade And Expansion | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-02-15 | 2014-03-16 | 2014-02-15 | 2023-03-30
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HC032-017 | Athletic Facilities Renovation | 1 | DEVELOP SCOPE | 2017-06-01 | 2017-08-29 | 2017-06-01 | 2017-08-29
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HC032-017 | Athletic Facilities Renovation | 2 | PRELIMINARY DESIGN | 2017-08-30 | 2017-12-27 | 2017-08-30 | 2017-12-27
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HC032-017 | Athletic Facilities Renovation | 3 | FINAL DESIGN | 2017-12-28 | 2018-06-25 | 2017-12-28 | 2018-06-25
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HC032-017 | Athletic Facilities Renovation | 4 | BID AWARD AND REGISTER CONTRCT | 2018-06-26 | 2018-09-23 | 2018-06-26 | 2018-09-23
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HC032-017 | Athletic Facilities Renovation | 5 | CONSTRUCTION TO 25% | 2018-09-24 | 2019-01-21 | 2018-09-24 | 2019-01-21
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HC032-017 | Athletic Facilities Renovation | 6 | CONSTRUCTION TO 50% | 2019-01-22 | 2019-05-21 | 2019-01-22 | 2019-05-21
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HC032-017 | Athletic Facilities Renovation | 7 | CONSTRUCTION TO 75% | 2019-05-22 | 2019-09-18 | 2019-05-22 | 2019-09-18
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HC032-017 | Athletic Facilities Renovation | 8 | ORIGINAL EQUIP & FURNISHING | 2019-09-19 | 2019-12-17 | 2019-09-19 | 2019-12-17
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HC032-017 | Athletic Facilities Renovation | 9 | SUBSTANTIAL COMPLETION | 2019-12-18 | 2020-02-15 | 2019-12-18 | 2020-02-15
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HC032-017 | Athletic Facilities Renovation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-02-16 | 2020-03-16 | 2020-02-16 | 2023-03-31
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HC033-019 | Expansive Glass Addition to the Building Facing West | 1 | DEVELOP SCOPE | 2018-06-30 | 2018-09-27 | 2020-07-01 | 2020-10-01
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HC033-019 | Expansive Glass Addition to the Building Facing West | 2 | PRELIMINARY DESIGN | 2018-09-28 | 2019-01-25 | 2020-10-02 | 2021-01-29
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HC033-019 | Expansive Glass Addition to the Building Facing West | 3 | FINAL DESIGN | 2019-01-26 | 2019-07-24 | 2021-01-30 | 2021-07-28
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HC033-019 | Expansive Glass Addition to the Building Facing West | 4 | BID AWARD AND REGISTER CONTRCT | 2019-07-25 | 2019-10-22 | 2021-07-29 | 2021-10-26
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HC033-019 | Expansive Glass Addition to the Building Facing West | 5 | CONSTRUCTION TO 25% | 2019-10-23 | 2020-02-19 | 2021-10-27 | 2022-02-23
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HC033-019 | Expansive Glass Addition to the Building Facing West | 6 | CONSTRUCTION TO 50% | 2020-02-20 | 2020-06-18 | 2022-02-24 | 2022-06-23
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HC033-019 | Expansive Glass Addition to the Building Facing West | 7 | CONSTRUCTION TO 75% | 2020-06-19 | 2020-10-16 | 2022-06-24 | 2022-10-21
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HC033-019 | Expansive Glass Addition to the Building Facing West | 8 | ORIGINAL EQUIP & FURNISHING | 2020-10-17 | 2021-01-14 | 2022-10-22 | 2023-01-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HC033-019 | Expansive Glass Addition to the Building Facing West | 9 | SUBSTANTIAL COMPLETION | 2021-01-15 | 2021-03-15 | 2023-01-20 | 2023-03-20
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HC033-019 | Expansive Glass Addition to the Building Facing West | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-16 | 2021-04-14 | 2023-03-21 | 2023-04-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HC034-018 | Hunter Campus Atrium | 1 | DEVELOP SCOPE | 2018-06-01 | 2018-08-29 | 2018-06-01 | 2018-08-29
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HC034-018 | Hunter Campus Atrium | 2 | PRELIMINARY DESIGN | 2018-08-30 | 2018-12-27 | 2018-08-30 | 2018-12-27
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HC034-018 | Hunter Campus Atrium | 3 | FINAL DESIGN | 2018-12-28 | 2019-06-25 | 2018-12-28 | 2019-06-25
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HC034-018 | Hunter Campus Atrium | 4 | BID AWARD AND REGISTER CONTRCT | 2019-06-26 | 2019-09-23 | 2019-06-26 | 2019-09-23
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HC034-018 | Hunter Campus Atrium | 5 | CONSTRUCTION TO 25% | 2019-09-24 | 2020-01-21 | 2019-09-24 | 2020-01-21
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HC034-018 | Hunter Campus Atrium | 6 | CONSTRUCTION TO 50% | 2020-01-22 | 2020-05-20 | 2020-01-22 | 2020-05-20
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HC034-018 | Hunter Campus Atrium | 7 | CONSTRUCTION TO 75% | 2020-05-21 | 2020-09-17 | 2020-05-21 | 2020-09-17
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HC034-018 | Hunter Campus Atrium | 8 | ORIGINAL EQUIP & FURNISHING | 2020-09-18 | 2020-12-16 | 2020-09-18 | 2020-12-16
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HC034-018 | Hunter Campus Atrium | 9 | SUBSTANTIAL COMPLETION | 2020-12-17 | 2021-02-14 | 2020-12-17 | 2021-02-14
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HC034-018 | Hunter Campus Atrium | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-02-15 | 2021-03-16 | 2021-02-15 | 2026-03-31
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HC036-020 | GLASS BOX | 1 | DEVELOP SCOPE | 2020-06-30 | 2020-09-27 | 2020-06-30 | 2020-09-27
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HC036-020 | GLASS BOX | 2 | PRELIMINARY DESIGN | 2020-09-28 | 2021-01-25 | 2020-09-28 | 2021-01-25
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HC036-020 | GLASS BOX | 3 | FINAL DESIGN | 2021-01-26 | 2021-07-24 | 2021-01-26 | 2021-07-24
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HC036-020 | GLASS BOX | 4 | BID AWARD AND REGISTER CONTRCT | 2021-07-25 | 2021-10-22 | 2021-07-25 | 2021-10-22
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HC036-020 | GLASS BOX | 5 | CONSTRUCTION TO 25% | 2021-10-23 | 2022-02-19 | 2021-10-23 | 2022-02-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HC036-020 | GLASS BOX | 6 | CONSTRUCTION TO 50% | 2022-02-20 | 2022-06-19 | 2022-02-20 | 2022-06-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HC036-020 | GLASS BOX | 7 | CONSTRUCTION TO 75% | 2022-06-20 | 2022-10-17 | 2022-06-20 | 2022-10-17
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HC036-020 | GLASS BOX | 8 | ORIGINAL EQUIP & FURNISHING | 2022-10-18 | 2023-01-15 | 2022-10-18 | 2023-01-15
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HC036-020 | GLASS BOX | 9 | SUBSTANTIAL COMPLETION | 2023-01-16 | 2023-03-16 | 2023-01-16 | 2023-03-16
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HC036-020 | GLASS BOX | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-03-17 | 2023-04-15 | 2023-03-17 | 2023-04-15
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HC073-094 | Elevator Upgrade | 2 | PRELIMINARY DESIGN | 2009-12-28 | 2010-04-26 | 2009-12-28 | 2010-04-26
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HC073-094 | Elevator Upgrade | 3 | FINAL DESIGN | 2010-04-27 | 2010-08-24 | 2010-04-27 | 2010-08-24
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HC073-094 | Elevator Upgrade | 4 | BID AWARD AND REGISTER CONTRCT | 2010-08-25 | 2010-11-22 | 2010-08-25 | 2010-11-22
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HC073-094 | Elevator Upgrade | 5 | CONSTRUCTION TO 25% | 2010-11-22 | 2010-11-22 | 2010-11-22 | 2010-11-22
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HC073-094 | Elevator Upgrade | 6 | CONSTRUCTION TO 50% | 2010-11-23 | 2010-12-22 | 2010-11-23 | 2010-12-22
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HC073-094 | Elevator Upgrade | 7 | CONSTRUCTION TO 75% | 2010-11-23 | 2010-12-22 | 2010-11-23 | 2010-12-22
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HC073-094 | Elevator Upgrade | 8 | ORIGINAL EQUIP & FURNISHING | 2010-12-23 | 2010-12-22 | 2010-12-23 | 2010-12-22
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HC073-094 | Elevator Upgrade | 9 | SUBSTANTIAL COMPLETION | 2010-12-23 | 2010-12-22 | 2010-12-23 | 2010-12-22
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HC073-094 | Elevator Upgrade | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2010-12-23 | 2011-01-21 | 2010-12-23 | 2014-01-30
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HC075-098 | HVAC Improvements | 1 | DEVELOP SCOPE | 2001-06-18 | 2001-09-15 | 2001-06-18 | 2001-09-15
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HC075-098 | HVAC Improvements | 2 | PRELIMINARY DESIGN | 2001-09-15 | 2002-03-06 | 2001-09-15 | 2002-03-06
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HC075-098 | HVAC Improvements | 3 | FINAL DESIGN | 2002-03-07 | 2003-03-06 | 2002-03-07 | 2003-03-06
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HC075-098 | HVAC Improvements | 4 | BID AWARD AND REGISTER CONTRCT | 2003-03-07 | 2004-03-06 | 2003-03-07 | 2004-03-06
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HC075-098 | HVAC Improvements | 5 | CONSTRUCTION TO 25% | 2004-03-07 | 2005-03-06 | 2004-03-07 | 2005-03-06
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HC075-098 | HVAC Improvements | 6 | CONSTRUCTION TO 50% | 2005-03-07 | 2006-03-06 | 2005-03-07 | 2006-03-06
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HC075-098 | HVAC Improvements | 7 | CONSTRUCTION TO 75% | 2006-03-07 | 2007-05-30 | 2006-03-07 | 2007-05-30
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HC075-098 | HVAC Improvements | 8 | ORIGINAL EQUIP & FURNISHING | 2007-05-31 | 2007-05-30 | 2007-05-31 | 2007-05-30
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HC075-098 | HVAC Improvements | 9 | SUBSTANTIAL COMPLETION | 2007-05-31 | 2007-05-30 | 2007-05-31 | 2007-05-30
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HC075-098 | HVAC Improvements | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2007-05-31 | 2007-06-29 | 2007-05-31 | 2022-06-30
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU001-021 | EQFN for the Welcome Center at the School of Education | 1 | DEVELOP SCOPE | 2021-06-30 | 2021-09-27 | 2021-06-30 | 2021-09-27
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU001-021 | EQFN for the Welcome Center at the School of Education | 2 | PRELIMINARY DESIGN | 2021-09-28 | 2022-01-25 | 2021-09-28 | 2022-01-25
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU001-021 | EQFN for the Welcome Center at the School of Education | 3 | FINAL DESIGN | 2022-01-26 | 2022-07-24 | 2022-01-26 | 2022-07-24
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU001-021 | EQFN for the Welcome Center at the School of Education | 4 | BID AWARD AND REGISTER CONTRCT | 2022-07-25 | 2022-10-22 | 2022-07-25 | 2022-10-22
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU001-021 | EQFN for the Welcome Center at the School of Education | 5 | CONSTRUCTION TO 25% | 2022-10-23 | 2023-02-19 | 2022-10-23 | 2023-02-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU001-021 | EQFN for the Welcome Center at the School of Education | 6 | CONSTRUCTION TO 50% | 2023-02-20 | 2023-06-19 | 2023-02-20 | 2023-06-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU001-021 | EQFN for the Welcome Center at the School of Education | 7 | CONSTRUCTION TO 75% | 2023-06-20 | 2023-10-17 | 2023-06-20 | 2023-10-17
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU001-021 | EQFN for the Welcome Center at the School of Education | 8 | ORIGINAL EQUIP & FURNISHING | 2023-10-18 | 2024-01-15 | 2023-10-18 | 2024-01-15
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU001-021 | EQFN for the Welcome Center at the School of Education | 9 | SUBSTANTIAL COMPLETION | 2024-01-16 | 2024-03-15 | 2024-01-16 | 2024-03-15
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU001-021 | EQFN for the Welcome Center at the School of Education | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-03-16 | 2024-04-14 | 2024-03-16 | 2024-04-14
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU002-021 | Construction of a Teaching Kitchen | 1 | DEVELOP SCOPE | 2021-06-30 | 2021-09-27 | 2021-06-30 | 2021-09-27
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU002-021 | Construction of a Teaching Kitchen | 2 | PRELIMINARY DESIGN | 2021-09-28 | 2022-01-25 | 2021-09-28 | 2022-01-25
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU002-021 | Construction of a Teaching Kitchen | 3 | FINAL DESIGN | 2022-01-26 | 2022-07-24 | 2022-01-26 | 2022-07-24
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU002-021 | Construction of a Teaching Kitchen | 4 | BID AWARD AND REGISTER CONTRCT | 2022-07-25 | 2022-10-22 | 2022-07-25 | 2022-10-22
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU002-021 | Construction of a Teaching Kitchen | 5 | CONSTRUCTION TO 25% | 2022-10-23 | 2023-02-19 | 2022-10-23 | 2023-02-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU002-021 | Construction of a Teaching Kitchen | 6 | CONSTRUCTION TO 50% | 2023-02-20 | 2023-06-19 | 2023-02-20 | 2023-06-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU002-021 | Construction of a Teaching Kitchen | 7 | CONSTRUCTION TO 75% | 2023-06-20 | 2023-10-17 | 2023-06-20 | 2023-10-17
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU002-021 | Construction of a Teaching Kitchen | 8 | ORIGINAL EQUIP & FURNISHING | 2023-10-18 | 2024-01-15 | 2023-10-18 | 2024-01-15
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU002-021 | Construction of a Teaching Kitchen | 9 | SUBSTANTIAL COMPLETION | 2024-01-16 | 2024-03-15 | 2024-01-16 | 2024-03-15
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU002-021 | Construction of a Teaching Kitchen | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-03-16 | 2024-04-14 | 2024-03-16 | 2024-04-14
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU003-021 | Auditorium Renovation | 1 | DEVELOP SCOPE | 2021-06-30 | 2021-09-27 | 2021-06-30 | 2021-09-27
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU003-021 | Auditorium Renovation | 2 | PRELIMINARY DESIGN | 2021-09-28 | 2022-01-25 | 2021-09-28 | 2022-01-25
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU003-021 | Auditorium Renovation | 3 | FINAL DESIGN | 2022-01-26 | 2022-07-24 | 2022-01-26 | 2022-07-24
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU003-021 | Auditorium Renovation | 4 | BID AWARD AND REGISTER CONTRCT | 2022-07-25 | 2022-10-22 | 2022-07-25 | 2022-10-22
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU003-021 | Auditorium Renovation | 5 | CONSTRUCTION TO 25% | 2022-10-23 | 2023-02-19 | 2022-10-23 | 2023-02-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU003-021 | Auditorium Renovation | 6 | CONSTRUCTION TO 50% | 2023-02-20 | 2023-06-19 | 2023-02-20 | 2023-06-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU003-021 | Auditorium Renovation | 7 | CONSTRUCTION TO 75% | 2023-06-20 | 2023-10-17 | 2023-06-20 | 2023-10-17
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU003-021 | Auditorium Renovation | 8 | ORIGINAL EQUIP & FURNISHING | 2023-10-18 | 2024-01-15 | 2023-10-18 | 2024-01-15
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU003-021 | Auditorium Renovation | 9 | SUBSTANTIAL COMPLETION | 2024-01-16 | 2024-03-15 | 2024-01-16 | 2024-03-15
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU003-021 | Auditorium Renovation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-03-16 | 2024-04-14 | 2024-03-16 | 2024-04-14
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU004-021 | School of Education Renovation | 1 | DEVELOP SCOPE | 2021-06-30 | 2021-09-27 | 2021-06-30 | 2021-09-27
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU004-021 | School of Education Renovation | 2 | PRELIMINARY DESIGN | 2021-09-28 | 2022-01-25 | 2021-09-28 | 2022-01-25
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU004-021 | School of Education Renovation | 3 | FINAL DESIGN | 2022-01-26 | 2022-07-24 | 2022-01-26 | 2022-07-24
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU004-021 | School of Education Renovation | 4 | BID AWARD AND REGISTER CONTRCT | 2022-07-25 | 2022-10-22 | 2022-07-25 | 2022-10-22
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU004-021 | School of Education Renovation | 5 | CONSTRUCTION TO 25% | 2022-10-23 | 2023-02-19 | 2022-10-23 | 2023-02-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU004-021 | School of Education Renovation | 6 | CONSTRUCTION TO 50% | 2023-02-20 | 2023-06-19 | 2023-02-20 | 2023-06-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU004-021 | School of Education Renovation | 7 | CONSTRUCTION TO 75% | 2023-06-20 | 2023-10-17 | 2023-06-20 | 2023-10-17
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU004-021 | School of Education Renovation | 8 | ORIGINAL EQUIP & FURNISHING | 2023-10-18 | 2024-01-15 | 2023-10-18 | 2024-01-15
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU004-021 | School of Education Renovation | 9 | SUBSTANTIAL COMPLETION | 2024-01-16 | 2024-03-15 | 2024-01-16 | 2024-03-15
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU004-021 | School of Education Renovation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-03-16 | 2024-04-14 | 2024-03-16 | 2024-04-14
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU007-004 | Restore Roosevelt House | 1 | DEVELOP SCOPE | 2004-05-30 | 2004-08-27 | 2004-05-30 | 2004-08-27
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU007-004 | Restore Roosevelt House | 2 | PRELIMINARY DESIGN | 2004-08-28 | 2004-12-25 | 2004-08-28 | 2004-12-25
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU007-004 | Restore Roosevelt House | 3 | FINAL DESIGN | 2004-12-26 | 2005-06-23 | 2004-12-26 | 2005-06-23
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU007-004 | Restore Roosevelt House | 4 | BID AWARD AND REGISTER CONTRCT | 2005-06-24 | 2005-09-21 | 2005-06-24 | 2005-09-21
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU007-004 | Restore Roosevelt House | 5 | CONSTRUCTION TO 25% | 2005-09-22 | 2006-01-19 | 2005-09-22 | 2006-01-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU007-004 | Restore Roosevelt House | 6 | CONSTRUCTION TO 50% | 2006-01-20 | 2006-05-19 | 2006-01-20 | 2006-05-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU007-004 | Restore Roosevelt House | 7 | CONSTRUCTION TO 75% | 2006-05-20 | 2006-09-16 | 2006-05-20 | 2006-09-16
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU007-004 | Restore Roosevelt House | 8 | ORIGINAL EQUIP & FURNISHING | 2006-09-17 | 2006-12-15 | 2006-09-17 | 2006-12-15
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU007-004 | Restore Roosevelt House | 9 | SUBSTANTIAL COMPLETION | 2006-12-16 | 2007-02-13 | 2006-12-16 | 2007-02-13
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU007-004 | Restore Roosevelt House | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2007-02-14 | 2007-03-15 | 2007-02-14 | 2026-06-30
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU022-009 | EXPERIMENTAL PSYCHOLOGY LAB BUILDOUT | 1 | DEVELOP SCOPE | 2009-06-01 | 2009-08-29 | 2009-06-01 | 2009-08-29
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU022-009 | EXPERIMENTAL PSYCHOLOGY LAB BUILDOUT | 2 | PRELIMINARY DESIGN | 2009-08-30 | 2009-12-27 | 2009-08-30 | 2009-12-27
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU022-009 | EXPERIMENTAL PSYCHOLOGY LAB BUILDOUT | 3 | FINAL DESIGN | 2009-12-28 | 2010-06-25 | 2009-12-28 | 2010-06-25
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU022-009 | EXPERIMENTAL PSYCHOLOGY LAB BUILDOUT | 4 | BID AWARD AND REGISTER CONTRCT | 2010-06-26 | 2010-09-23 | 2010-06-26 | 2010-09-23
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU022-009 | EXPERIMENTAL PSYCHOLOGY LAB BUILDOUT | 5 | CONSTRUCTION TO 25% | 2010-09-24 | 2011-01-21 | 2010-09-24 | 2011-01-21
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU022-009 | EXPERIMENTAL PSYCHOLOGY LAB BUILDOUT | 6 | CONSTRUCTION TO 50% | 2011-01-22 | 2011-05-21 | 2011-01-22 | 2011-05-21
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU022-009 | EXPERIMENTAL PSYCHOLOGY LAB BUILDOUT | 7 | CONSTRUCTION TO 75% | 2011-05-22 | 2011-09-18 | 2011-05-22 | 2011-09-18
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU022-009 | EXPERIMENTAL PSYCHOLOGY LAB BUILDOUT | 8 | ORIGINAL EQUIP & FURNISHING | 2011-09-19 | 2011-12-17 | 2011-09-19 | 2011-12-17
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU022-009 | EXPERIMENTAL PSYCHOLOGY LAB BUILDOUT | 9 | SUBSTANTIAL COMPLETION | 2011-12-18 | 2012-02-15 | 2011-12-18 | 2012-02-15
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU022-009 | EXPERIMENTAL PSYCHOLOGY LAB BUILDOUT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-02-16 | 2012-03-16 | 2012-02-16 | 2026-06-30
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU023-011 | Wexler Library Renovations | 1 | DEVELOP SCOPE | 2011-06-01 | 2011-08-29 | 2011-06-01 | 2011-08-29
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU023-011 | Wexler Library Renovations | 2 | PRELIMINARY DESIGN | 2011-08-30 | 2011-12-27 | 2011-08-30 | 2011-12-27
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU023-011 | Wexler Library Renovations | 3 | FINAL DESIGN | 2011-12-28 | 2012-06-24 | 2011-12-28 | 2012-06-24
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU023-011 | Wexler Library Renovations | 4 | BID AWARD AND REGISTER CONTRCT | 2012-06-25 | 2012-09-22 | 2012-06-25 | 2012-09-22
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU023-011 | Wexler Library Renovations | 5 | CONSTRUCTION TO 25% | 2012-09-23 | 2013-01-20 | 2012-09-23 | 2013-01-20
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU023-011 | Wexler Library Renovations | 6 | CONSTRUCTION TO 50% | 2013-01-21 | 2013-05-20 | 2013-01-21 | 2013-05-20
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU023-011 | Wexler Library Renovations | 7 | CONSTRUCTION TO 75% | 2013-05-21 | 2013-09-17 | 2013-05-21 | 2013-09-17
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU023-011 | Wexler Library Renovations | 8 | ORIGINAL EQUIP & FURNISHING | 2013-09-18 | 2013-12-16 | 2013-09-18 | 2013-12-16
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU023-011 | Wexler Library Renovations | 9 | SUBSTANTIAL COMPLETION | 2013-12-17 | 2014-02-14 | 2013-12-17 | 2014-02-14
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU023-011 | Wexler Library Renovations | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-02-15 | 2014-03-16 | 2014-02-15 | 2018-03-30
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU026-013 | Science and Health Professions Building | 1 | DEVELOP SCOPE | 2013-06-01 | 2013-08-29 | 2021-07-01 | 2021-09-28
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU026-013 | Science and Health Professions Building | 2 | PRELIMINARY DESIGN | 2013-08-30 | 2013-12-27 | 2021-09-29 | 2022-01-26
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU026-013 | Science and Health Professions Building | 3 | FINAL DESIGN | 2013-12-28 | 2014-06-25 | 2022-01-27 | 2022-07-25
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU026-013 | Science and Health Professions Building | 4 | BID AWARD AND REGISTER CONTRCT | 2014-06-26 | 2014-09-23 | 2022-07-26 | 2022-10-23
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU026-013 | Science and Health Professions Building | 5 | CONSTRUCTION TO 25% | 2014-09-24 | 2015-01-21 | 2022-10-24 | 2023-02-20
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU026-013 | Science and Health Professions Building | 6 | CONSTRUCTION TO 50% | 2015-01-22 | 2015-05-21 | 2023-02-21 | 2023-06-20
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU026-013 | Science and Health Professions Building | 7 | CONSTRUCTION TO 75% | 2015-05-22 | 2015-09-18 | 2023-06-21 | 2023-10-18
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU026-013 | Science and Health Professions Building | 8 | ORIGINAL EQUIP & FURNISHING | 2015-09-19 | 2015-12-17 | 2023-10-19 | 2024-01-16
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU026-013 | Science and Health Professions Building | 9 | SUBSTANTIAL COMPLETION | 2015-12-18 | 2016-02-15 | 2024-01-17 | 2024-03-16
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU026-013 | Science and Health Professions Building | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-02-16 | 2016-03-16 | 2024-03-17 | 2026-06-26
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU027-013 | SCHOOL OF NURSING/HEALTH SCIENCE RELOCATION TO C3 | 1 | DEVELOP SCOPE | 2015-06-01 | 2015-08-29 | 2022-07-01 | 2022-09-29
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU027-013 | SCHOOL OF NURSING/HEALTH SCIENCE RELOCATION TO C3 | 2 | PRELIMINARY DESIGN | 2015-08-30 | 2015-12-27 | 2022-09-30 | 2023-01-27
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU027-013 | SCHOOL OF NURSING/HEALTH SCIENCE RELOCATION TO C3 | 3 | FINAL DESIGN | 2015-12-28 | 2016-06-24 | 2023-01-28 | 2023-07-26
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU027-013 | SCHOOL OF NURSING/HEALTH SCIENCE RELOCATION TO C3 | 4 | BID AWARD AND REGISTER CONTRCT | 2016-06-25 | 2016-09-22 | 2023-07-27 | 2023-10-24
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU027-013 | SCHOOL OF NURSING/HEALTH SCIENCE RELOCATION TO C3 | 5 | CONSTRUCTION TO 25% | 2016-09-23 | 2017-01-20 | 2023-10-25 | 2024-02-21
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU027-013 | SCHOOL OF NURSING/HEALTH SCIENCE RELOCATION TO C3 | 6 | CONSTRUCTION TO 50% | 2017-01-21 | 2017-05-20 | 2024-02-22 | 2024-06-20
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU027-013 | SCHOOL OF NURSING/HEALTH SCIENCE RELOCATION TO C3 | 7 | CONSTRUCTION TO 75% | 2017-05-21 | 2017-09-17 | 2024-06-21 | 2024-10-18
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU027-013 | SCHOOL OF NURSING/HEALTH SCIENCE RELOCATION TO C3 | 8 | ORIGINAL EQUIP & FURNISHING | 2017-09-18 | 2017-12-16 | 2024-10-19 | 2025-01-16
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU027-013 | SCHOOL OF NURSING/HEALTH SCIENCE RELOCATION TO C3 | 9 | SUBSTANTIAL COMPLETION | 2017-12-17 | 2018-02-14 | 2025-01-17 | 2025-03-17
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU027-013 | SCHOOL OF NURSING/HEALTH SCIENCE RELOCATION TO C3 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-02-15 | 2019-06-30 | 2025-03-18 | 2025-04-16
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU028-015 | Black Box Performance Space | 1 | DEVELOP SCOPE | 2015-03-01 | 2015-05-29 | 2021-07-01 | 2021-10-01
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU028-015 | Black Box Performance Space | 2 | PRELIMINARY DESIGN | 2015-05-30 | 2015-09-26 | 2021-10-02 | 2022-01-29
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU028-015 | Black Box Performance Space | 3 | FINAL DESIGN | 2015-09-27 | 2016-03-24 | 2022-01-30 | 2022-07-28
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU028-015 | Black Box Performance Space | 4 | BID AWARD AND REGISTER CONTRCT | 2016-03-25 | 2016-06-22 | 2022-07-29 | 2022-10-26
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU028-015 | Black Box Performance Space | 5 | CONSTRUCTION TO 25% | 2016-06-23 | 2016-10-20 | 2022-10-27 | 2023-02-23
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU028-015 | Black Box Performance Space | 6 | CONSTRUCTION TO 50% | 2016-10-21 | 2017-02-17 | 2023-02-24 | 2023-06-23
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU028-015 | Black Box Performance Space | 7 | CONSTRUCTION TO 75% | 2017-02-18 | 2017-06-17 | 2023-06-24 | 2023-10-21
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU028-015 | Black Box Performance Space | 8 | ORIGINAL EQUIP & FURNISHING | 2017-06-18 | 2017-09-15 | 2023-10-22 | 2024-01-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU028-015 | Black Box Performance Space | 9 | SUBSTANTIAL COMPLETION | 2017-09-16 | 2017-11-14 | 2024-01-20 | 2024-03-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU028-015 | Black Box Performance Space | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-11-15 | 2017-12-14 | 2024-03-20 | 2029-05-05
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU029-015 | Black Box Media & Arts Flex Space Improvements | 1 | DEVELOP SCOPE | 2014-10-01 | 2014-12-29 | 2021-07-01 | 2021-10-03
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU029-015 | Black Box Media & Arts Flex Space Improvements | 2 | PRELIMINARY DESIGN | 2014-12-30 | 2015-04-28 | 2021-10-04 | 2022-01-31
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU029-015 | Black Box Media & Arts Flex Space Improvements | 3 | FINAL DESIGN | 2015-04-29 | 2015-10-25 | 2022-02-01 | 2022-07-30
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU029-015 | Black Box Media & Arts Flex Space Improvements | 4 | BID AWARD AND REGISTER CONTRCT | 2015-10-26 | 2016-01-23 | 2022-07-31 | 2022-10-28
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU029-015 | Black Box Media & Arts Flex Space Improvements | 5 | CONSTRUCTION TO 25% | 2016-01-24 | 2016-05-22 | 2022-10-29 | 2023-02-25
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU029-015 | Black Box Media & Arts Flex Space Improvements | 6 | CONSTRUCTION TO 50% | 2016-05-23 | 2016-09-19 | 2023-02-26 | 2023-06-25
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU029-015 | Black Box Media & Arts Flex Space Improvements | 7 | CONSTRUCTION TO 75% | 2016-09-20 | 2017-01-17 | 2023-06-26 | 2023-10-23
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU029-015 | Black Box Media & Arts Flex Space Improvements | 8 | ORIGINAL EQUIP & FURNISHING | 2017-01-18 | 2017-04-17 | 2023-10-24 | 2024-01-21
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU029-015 | Black Box Media & Arts Flex Space Improvements | 9 | SUBSTANTIAL COMPLETION | 2017-04-18 | 2017-06-16 | 2024-01-22 | 2024-03-21
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU029-015 | Black Box Media & Arts Flex Space Improvements | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-06-17 | 2017-07-16 | 2024-03-22 | 2029-05-05
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU035-016 | Black Box Theater Renovation Black Box Theater Renovation | 1 | DEVELOP SCOPE | 2015-06-01 | 2015-08-29 | 2021-07-01 | 2021-10-01
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU035-016 | Black Box Theater Renovation Black Box Theater Renovation | 2 | PRELIMINARY DESIGN | 2015-08-30 | 2015-12-27 | 2021-10-02 | 2022-01-29
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU035-016 | Black Box Theater Renovation Black Box Theater Renovation | 3 | FINAL DESIGN | 2015-12-28 | 2016-06-24 | 2022-01-30 | 2022-07-28
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU035-016 | Black Box Theater Renovation Black Box Theater Renovation | 4 | BID AWARD AND REGISTER CONTRCT | 2016-06-25 | 2016-09-22 | 2022-07-29 | 2022-10-26
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU035-016 | Black Box Theater Renovation Black Box Theater Renovation | 5 | CONSTRUCTION TO 25% | 2016-09-23 | 2017-01-20 | 2022-10-27 | 2023-02-23
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU035-016 | Black Box Theater Renovation Black Box Theater Renovation | 6 | CONSTRUCTION TO 50% | 2017-01-21 | 2017-05-20 | 2023-02-24 | 2023-06-23
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU035-016 | Black Box Theater Renovation Black Box Theater Renovation | 7 | CONSTRUCTION TO 75% | 2017-05-21 | 2017-09-17 | 2023-06-24 | 2023-10-21
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU035-016 | Black Box Theater Renovation Black Box Theater Renovation | 8 | ORIGINAL EQUIP & FURNISHING | 2017-09-18 | 2017-12-16 | 2023-10-22 | 2024-01-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU035-016 | Black Box Theater Renovation Black Box Theater Renovation | 9 | SUBSTANTIAL COMPLETION | 2017-12-17 | 2018-02-14 | 2024-01-20 | 2024-03-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU035-016 | Black Box Theater Renovation Black Box Theater Renovation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-02-15 | 2018-03-16 | 2024-03-20 | 2030-05-04
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU036-017 | Black Box Renovation | 1 | DEVELOP SCOPE | 2017-06-01 | 2017-08-29 | 2021-07-01 | 2021-10-01
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU036-017 | Black Box Renovation | 2 | PRELIMINARY DESIGN | 2017-08-30 | 2017-12-27 | 2021-10-02 | 2022-01-29
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU036-017 | Black Box Renovation | 3 | FINAL DESIGN | 2017-12-28 | 2018-06-25 | 2022-01-30 | 2022-07-28
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU036-017 | Black Box Renovation | 4 | BID AWARD AND REGISTER CONTRCT | 2018-06-26 | 2018-09-23 | 2022-07-29 | 2022-10-26
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU036-017 | Black Box Renovation | 5 | CONSTRUCTION TO 25% | 2018-09-24 | 2019-01-21 | 2022-10-27 | 2023-02-23
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU036-017 | Black Box Renovation | 6 | CONSTRUCTION TO 50% | 2019-01-22 | 2019-05-21 | 2023-02-24 | 2023-06-23
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU036-017 | Black Box Renovation | 7 | CONSTRUCTION TO 75% | 2019-05-22 | 2019-09-18 | 2023-06-24 | 2023-10-21
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU036-017 | Black Box Renovation | 8 | ORIGINAL EQUIP & FURNISHING | 2019-09-19 | 2019-12-17 | 2023-10-22 | 2024-01-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU036-017 | Black Box Renovation | 9 | SUBSTANTIAL COMPLETION | 2019-12-18 | 2020-02-15 | 2024-01-20 | 2024-03-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU036-017 | Black Box Renovation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-02-16 | 2020-03-16 | 2024-03-20 | 2028-05-03
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU037-017 | CUNY Performing Arts Hub | 1 | DEVELOP SCOPE | 2017-06-01 | 2017-08-29 | 2021-07-01 | 2021-10-01
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU037-017 | CUNY Performing Arts Hub | 2 | PRELIMINARY DESIGN | 2017-08-30 | 2017-12-27 | 2021-10-02 | 2022-01-29
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU037-017 | CUNY Performing Arts Hub | 3 | FINAL DESIGN | 2017-12-28 | 2018-06-25 | 2022-01-30 | 2022-07-28
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU037-017 | CUNY Performing Arts Hub | 4 | BID AWARD AND REGISTER CONTRCT | 2018-06-26 | 2018-09-23 | 2022-07-29 | 2022-10-26
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU037-017 | CUNY Performing Arts Hub | 5 | CONSTRUCTION TO 25% | 2018-09-24 | 2019-01-21 | 2022-10-27 | 2023-02-23
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU037-017 | CUNY Performing Arts Hub | 6 | CONSTRUCTION TO 50% | 2019-01-22 | 2019-05-21 | 2023-02-24 | 2023-06-23
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU037-017 | CUNY Performing Arts Hub | 7 | CONSTRUCTION TO 75% | 2019-05-22 | 2019-09-18 | 2023-06-24 | 2023-10-21
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU037-017 | CUNY Performing Arts Hub | 8 | ORIGINAL EQUIP & FURNISHING | 2019-09-19 | 2019-12-17 | 2023-10-22 | 2024-01-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU037-017 | CUNY Performing Arts Hub | 9 | SUBSTANTIAL COMPLETION | 2019-12-18 | 2020-02-15 | 2024-01-20 | 2024-03-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU037-017 | CUNY Performing Arts Hub | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-02-16 | 2020-03-16 | 2024-03-20 | 2029-05-03
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU039-018 | Performing Arts Hub - Renovate N Building Auditorium | 1 | DEVELOP SCOPE | 2018-06-01 | 2018-08-29 | 2021-07-01 | 2021-10-01
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU039-018 | Performing Arts Hub - Renovate N Building Auditorium | 2 | PRELIMINARY DESIGN | 2018-08-30 | 2018-12-27 | 2021-10-02 | 2022-01-29
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU039-018 | Performing Arts Hub - Renovate N Building Auditorium | 3 | FINAL DESIGN | 2018-12-28 | 2019-06-25 | 2022-01-30 | 2022-07-28
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU039-018 | Performing Arts Hub - Renovate N Building Auditorium | 4 | BID AWARD AND REGISTER CONTRCT | 2019-06-26 | 2019-09-23 | 2022-07-29 | 2022-10-26
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU039-018 | Performing Arts Hub - Renovate N Building Auditorium | 5 | CONSTRUCTION TO 25% | 2019-09-24 | 2020-01-21 | 2022-10-27 | 2023-02-23
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU039-018 | Performing Arts Hub - Renovate N Building Auditorium | 6 | CONSTRUCTION TO 50% | 2020-01-22 | 2020-05-20 | 2023-02-24 | 2023-06-23
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU039-018 | Performing Arts Hub - Renovate N Building Auditorium | 7 | CONSTRUCTION TO 75% | 2020-05-21 | 2020-09-17 | 2023-06-24 | 2023-10-21
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU039-018 | Performing Arts Hub - Renovate N Building Auditorium | 8 | ORIGINAL EQUIP & FURNISHING | 2020-09-18 | 2020-12-16 | 2023-10-22 | 2024-01-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU039-018 | Performing Arts Hub - Renovate N Building Auditorium | 9 | SUBSTANTIAL COMPLETION | 2020-12-17 | 2021-02-14 | 2024-01-20 | 2024-03-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU039-018 | Performing Arts Hub - Renovate N Building Auditorium | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-02-15 | 2021-03-16 | 2024-03-20 | 2027-05-04
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU040-018 | Renovate Performing Arts Hub in North Building | 1 | DEVELOP SCOPE | 2018-06-01 | 2018-08-29 | 2021-07-01 | 2021-10-01
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU040-018 | Renovate Performing Arts Hub in North Building | 2 | PRELIMINARY DESIGN | 2018-08-30 | 2018-12-27 | 2021-10-02 | 2022-01-29
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU040-018 | Renovate Performing Arts Hub in North Building | 3 | FINAL DESIGN | 2018-12-28 | 2019-06-25 | 2022-01-30 | 2022-07-28
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU040-018 | Renovate Performing Arts Hub in North Building | 4 | BID AWARD AND REGISTER CONTRCT | 2019-06-26 | 2019-09-23 | 2022-07-29 | 2022-10-26
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU040-018 | Renovate Performing Arts Hub in North Building | 5 | CONSTRUCTION TO 25% | 2019-09-24 | 2020-01-21 | 2022-10-27 | 2023-02-23
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU040-018 | Renovate Performing Arts Hub in North Building | 6 | CONSTRUCTION TO 50% | 2020-01-22 | 2020-05-20 | 2023-02-24 | 2023-06-23
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU040-018 | Renovate Performing Arts Hub in North Building | 7 | CONSTRUCTION TO 75% | 2020-05-21 | 2020-09-17 | 2023-06-24 | 2023-10-21
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU040-018 | Renovate Performing Arts Hub in North Building | 8 | ORIGINAL EQUIP & FURNISHING | 2020-09-18 | 2020-12-16 | 2023-10-22 | 2024-01-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU040-018 | Renovate Performing Arts Hub in North Building | 9 | SUBSTANTIAL COMPLETION | 2020-12-17 | 2021-02-14 | 2024-01-20 | 2024-03-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU040-018 | Renovate Performing Arts Hub in North Building | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-02-15 | 2021-03-16 | 2024-03-20 | 2027-05-04
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU040-019 | Computer Science 10th FL. North Expansion | 1 | DEVELOP SCOPE | 2018-06-30 | 2018-09-27 | 2020-07-01 | 2020-10-01
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU040-019 | Computer Science 10th FL. North Expansion | 2 | PRELIMINARY DESIGN | 2018-09-28 | 2019-01-25 | 2020-10-02 | 2021-01-29
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU040-019 | Computer Science 10th FL. North Expansion | 3 | FINAL DESIGN | 2019-01-26 | 2019-07-24 | 2021-01-30 | 2021-07-28
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU040-019 | Computer Science 10th FL. North Expansion | 4 | BID AWARD AND REGISTER CONTRCT | 2019-07-25 | 2019-10-22 | 2021-07-29 | 2021-10-26
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU040-019 | Computer Science 10th FL. North Expansion | 5 | CONSTRUCTION TO 25% | 2019-10-23 | 2020-02-19 | 2021-10-27 | 2022-02-23
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU040-019 | Computer Science 10th FL. North Expansion | 6 | CONSTRUCTION TO 50% | 2020-02-20 | 2020-06-18 | 2022-02-24 | 2022-06-23
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU040-019 | Computer Science 10th FL. North Expansion | 7 | CONSTRUCTION TO 75% | 2020-06-19 | 2020-10-16 | 2022-06-24 | 2022-10-21
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU040-019 | Computer Science 10th FL. North Expansion | 8 | ORIGINAL EQUIP & FURNISHING | 2020-10-17 | 2021-01-14 | 2022-10-22 | 2023-01-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU040-019 | Computer Science 10th FL. North Expansion | 9 | SUBSTANTIAL COMPLETION | 2021-01-15 | 2021-03-15 | 2023-01-20 | 2023-03-20
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU040-019 | Computer Science 10th FL. North Expansion | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-16 | 2021-04-14 | 2023-03-21 | 2023-04-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU041-019 | Black Box Media Flex Space | 1 | DEVELOP SCOPE | 2019-06-30 | 2019-09-27 | 2021-07-01 | 2021-10-01
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU041-019 | Black Box Media Flex Space | 2 | PRELIMINARY DESIGN | 2019-09-28 | 2020-01-25 | 2021-10-02 | 2022-01-29
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU041-019 | Black Box Media Flex Space | 3 | FINAL DESIGN | 2020-01-26 | 2020-07-23 | 2022-01-30 | 2022-07-28
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU041-019 | Black Box Media Flex Space | 4 | BID AWARD AND REGISTER CONTRCT | 2020-07-24 | 2020-10-21 | 2022-07-29 | 2022-10-26
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU041-019 | Black Box Media Flex Space | 5 | CONSTRUCTION TO 25% | 2020-10-22 | 2021-02-18 | 2022-10-27 | 2023-02-23
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU041-019 | Black Box Media Flex Space | 6 | CONSTRUCTION TO 50% | 2021-02-19 | 2021-06-18 | 2023-02-24 | 2023-06-23
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU041-019 | Black Box Media Flex Space | 7 | CONSTRUCTION TO 75% | 2021-06-19 | 2021-10-16 | 2023-06-24 | 2023-10-21
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU041-019 | Black Box Media Flex Space | 8 | ORIGINAL EQUIP & FURNISHING | 2021-10-17 | 2022-01-14 | 2023-10-22 | 2024-01-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU041-019 | Black Box Media Flex Space | 9 | SUBSTANTIAL COMPLETION | 2022-01-15 | 2022-03-15 | 2024-01-20 | 2024-03-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU041-019 | Black Box Media Flex Space | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-16 | 2022-04-14 | 2024-03-20 | 2024-04-18
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU042-019 | Thomas Hunter Hall Upgrades | 1 | DEVELOP SCOPE | 2019-06-30 | 2019-09-27 | 2019-06-30 | 2019-09-27
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU042-019 | Thomas Hunter Hall Upgrades | 2 | PRELIMINARY DESIGN | 2019-09-28 | 2020-01-25 | 2019-09-28 | 2020-01-25
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU042-019 | Thomas Hunter Hall Upgrades | 3 | FINAL DESIGN | 2020-01-26 | 2020-07-23 | 2020-01-26 | 2020-07-23
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU042-019 | Thomas Hunter Hall Upgrades | 4 | BID AWARD AND REGISTER CONTRCT | 2020-07-24 | 2020-10-21 | 2020-07-24 | 2020-10-21
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU042-019 | Thomas Hunter Hall Upgrades | 5 | CONSTRUCTION TO 25% | 2020-10-22 | 2021-02-18 | 2020-10-22 | 2021-02-18
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU042-019 | Thomas Hunter Hall Upgrades | 6 | CONSTRUCTION TO 50% | 2021-02-19 | 2021-06-18 | 2021-02-19 | 2021-06-18
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU042-019 | Thomas Hunter Hall Upgrades | 7 | CONSTRUCTION TO 75% | 2021-06-19 | 2021-10-16 | 2021-06-19 | 2021-10-16
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU042-019 | Thomas Hunter Hall Upgrades | 8 | ORIGINAL EQUIP & FURNISHING | 2021-10-17 | 2022-01-14 | 2021-10-17 | 2022-01-14
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU042-019 | Thomas Hunter Hall Upgrades | 9 | SUBSTANTIAL COMPLETION | 2022-01-15 | 2022-03-15 | 2022-01-15 | 2022-03-15
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU042-019 | Thomas Hunter Hall Upgrades | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-16 | 2022-04-14 | 2022-03-16 | 2022-04-14
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU043-020 | Auditorium Renovation in North Building | 1 | DEVELOP SCOPE | 2021-07-01 | 2021-09-28 | 2021-07-01 | 2021-09-28
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU043-020 | Auditorium Renovation in North Building | 2 | PRELIMINARY DESIGN | 2021-09-29 | 2022-01-26 | 2021-09-29 | 2022-01-26
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU043-020 | Auditorium Renovation in North Building | 3 | FINAL DESIGN | 2022-01-27 | 2022-07-25 | 2022-01-27 | 2022-07-25
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU043-020 | Auditorium Renovation in North Building | 4 | BID AWARD AND REGISTER CONTRCT | 2022-07-26 | 2022-10-23 | 2022-07-26 | 2022-10-23
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU043-020 | Auditorium Renovation in North Building | 5 | CONSTRUCTION TO 25% | 2022-10-24 | 2023-02-20 | 2022-10-24 | 2023-02-20
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU043-020 | Auditorium Renovation in North Building | 6 | CONSTRUCTION TO 50% | 2023-02-21 | 2023-06-20 | 2023-02-21 | 2023-06-20
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU043-020 | Auditorium Renovation in North Building | 7 | CONSTRUCTION TO 75% | 2023-06-21 | 2023-10-18 | 2023-06-21 | 2023-10-18
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU043-020 | Auditorium Renovation in North Building | 8 | ORIGINAL EQUIP & FURNISHING | 2023-10-19 | 2024-01-16 | 2023-10-19 | 2024-01-16
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU043-020 | Auditorium Renovation in North Building | 9 | SUBSTANTIAL COMPLETION | 2024-01-17 | 2024-03-16 | 2024-01-17 | 2024-03-16
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU043-020 | Auditorium Renovation in North Building | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-03-17 | 2024-04-16 | 2024-03-17 | 2027-04-30
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU044-020 | Dance Department Lobby Renovation | 1 | DEVELOP SCOPE | 2020-06-30 | 2020-09-27 | 2020-06-30 | 2020-09-27
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU044-020 | Dance Department Lobby Renovation | 2 | PRELIMINARY DESIGN | 2020-09-28 | 2021-01-25 | 2020-09-28 | 2021-01-25
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU044-020 | Dance Department Lobby Renovation | 3 | FINAL DESIGN | 2021-01-26 | 2021-07-24 | 2021-01-26 | 2021-07-24
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU044-020 | Dance Department Lobby Renovation | 4 | BID AWARD AND REGISTER CONTRCT | 2021-07-25 | 2021-10-22 | 2021-07-25 | 2021-10-22
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU044-020 | Dance Department Lobby Renovation | 5 | CONSTRUCTION TO 25% | 2021-10-23 | 2022-02-19 | 2021-10-23 | 2022-02-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU044-020 | Dance Department Lobby Renovation | 6 | CONSTRUCTION TO 50% | 2022-02-20 | 2022-06-19 | 2022-02-20 | 2022-06-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU044-020 | Dance Department Lobby Renovation | 7 | CONSTRUCTION TO 75% | 2022-06-20 | 2022-10-17 | 2022-06-20 | 2022-10-17
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU044-020 | Dance Department Lobby Renovation | 8 | ORIGINAL EQUIP & FURNISHING | 2022-10-18 | 2023-01-15 | 2022-10-18 | 2023-01-15
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU044-020 | Dance Department Lobby Renovation | 9 | SUBSTANTIAL COMPLETION | 2023-01-16 | 2023-03-16 | 2023-01-16 | 2023-03-16
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | HU044-020 | Dance Department Lobby Renovation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-03-17 | 2023-04-15 | 2023-03-17 | 2023-04-15
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | JJ001-021 | Multimedia Distribution System | 1 | DEVELOP SCOPE | 2021-06-30 | 2021-09-27 | 2021-06-30 | 2021-09-27
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | JJ001-021 | Multimedia Distribution System | 2 | PRELIMINARY DESIGN | 2021-09-28 | 2022-01-25 | 2021-09-28 | 2022-01-25
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | JJ001-021 | Multimedia Distribution System | 3 | FINAL DESIGN | 2022-01-26 | 2022-07-24 | 2022-01-26 | 2022-07-24
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | JJ001-021 | Multimedia Distribution System | 4 | BID AWARD AND REGISTER CONTRCT | 2022-07-25 | 2022-10-22 | 2022-07-25 | 2022-10-22
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | JJ001-021 | Multimedia Distribution System | 5 | CONSTRUCTION TO 25% | 2022-10-23 | 2023-02-19 | 2022-10-23 | 2023-02-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | JJ001-021 | Multimedia Distribution System | 6 | CONSTRUCTION TO 50% | 2023-02-20 | 2023-06-19 | 2023-02-20 | 2023-06-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | JJ001-021 | Multimedia Distribution System | 7 | CONSTRUCTION TO 75% | 2023-06-20 | 2023-10-17 | 2023-06-20 | 2023-10-17
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | JJ001-021 | Multimedia Distribution System | 8 | ORIGINAL EQUIP & FURNISHING | 2023-10-18 | 2024-01-15 | 2023-10-18 | 2024-01-15
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | JJ001-021 | Multimedia Distribution System | 9 | SUBSTANTIAL COMPLETION | 2024-01-16 | 2024-03-15 | 2024-01-16 | 2024-03-15
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | JJ001-021 | Multimedia Distribution System | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-03-16 | 2024-04-14 | 2024-03-16 | 2024-04-14
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | JJ018-014 | Green IT | 6 | CONSTRUCTION TO 50% | 2016-01-22 | 2016-05-20 | 2016-01-22 | 2016-05-20
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | JJ018-014 | Green IT | 7 | CONSTRUCTION TO 75% | 2016-05-21 | 2016-09-17 | 2016-05-21 | 2016-09-17
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | JJ018-014 | Green IT | 8 | ORIGINAL EQUIP & FURNISHING | 2016-09-18 | 2016-12-16 | 2016-09-18 | 2016-12-16
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | JJ018-014 | Green IT | 9 | SUBSTANTIAL COMPLETION | 2016-12-17 | 2017-02-14 | 2016-12-17 | 2017-02-14
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | JJ018-014 | Green IT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-02-15 | 2017-03-16 | 2017-02-15 | 2023-03-31
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | JJ021-015 | Lloyd Sealy Library Upgrade | 1 | DEVELOP SCOPE | 2014-10-01 | 2014-12-29 | 2014-10-01 | 2014-12-29
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | JJ021-015 | Lloyd Sealy Library Upgrade | 2 | PRELIMINARY DESIGN | 2014-12-30 | 2015-04-28 | 2014-12-30 | 2015-04-28
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | JJ021-015 | Lloyd Sealy Library Upgrade | 3 | FINAL DESIGN | 2015-04-29 | 2015-10-25 | 2015-04-29 | 2015-10-25
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | JJ021-015 | Lloyd Sealy Library Upgrade | 4 | BID AWARD AND REGISTER CONTRCT | 2015-10-26 | 2016-01-23 | 2015-10-26 | 2016-01-23
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | JJ021-015 | Lloyd Sealy Library Upgrade | 5 | CONSTRUCTION TO 25% | 2016-01-24 | 2016-05-22 | 2016-01-24 | 2016-05-22
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | JJ021-015 | Lloyd Sealy Library Upgrade | 6 | CONSTRUCTION TO 50% | 2016-05-23 | 2016-09-19 | 2016-05-23 | 2016-09-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | JJ021-015 | Lloyd Sealy Library Upgrade | 7 | CONSTRUCTION TO 75% | 2016-09-20 | 2017-01-17 | 2016-09-20 | 2017-01-17
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | JJ021-015 | Lloyd Sealy Library Upgrade | 8 | ORIGINAL EQUIP & FURNISHING | 2017-01-18 | 2017-04-17 | 2017-01-18 | 2017-04-17
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | JJ021-015 | Lloyd Sealy Library Upgrade | 9 | SUBSTANTIAL COMPLETION | 2017-04-18 | 2017-06-16 | 2017-04-18 | 2017-06-16
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | JJ021-015 | Lloyd Sealy Library Upgrade | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-06-17 | 2017-07-16 | 2017-06-17 | 2027-03-30
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | JJ024-017 | Locker Rooms and Gym Entrance | 1 | DEVELOP SCOPE | 2017-06-01 | 2017-08-29 | 2021-07-01 | 2021-10-01
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | JJ024-017 | Locker Rooms and Gym Entrance | 2 | PRELIMINARY DESIGN | 2017-08-30 | 2017-12-27 | 2021-10-02 | 2022-01-29
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | JJ024-017 | Locker Rooms and Gym Entrance | 3 | FINAL DESIGN | 2017-12-28 | 2018-06-25 | 2022-01-30 | 2022-07-28
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | JJ024-017 | Locker Rooms and Gym Entrance | 4 | BID AWARD AND REGISTER CONTRCT | 2018-06-26 | 2018-09-23 | 2022-07-29 | 2022-10-26
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | JJ024-017 | Locker Rooms and Gym Entrance | 5 | CONSTRUCTION TO 25% | 2018-09-24 | 2019-01-21 | 2022-10-27 | 2023-02-23
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | JJ024-017 | Locker Rooms and Gym Entrance | 6 | CONSTRUCTION TO 50% | 2019-01-22 | 2019-05-21 | 2023-02-24 | 2023-06-23
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | JJ024-017 | Locker Rooms and Gym Entrance | 7 | CONSTRUCTION TO 75% | 2019-05-22 | 2019-09-18 | 2023-06-24 | 2023-10-21
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | JJ024-017 | Locker Rooms and Gym Entrance | 8 | ORIGINAL EQUIP & FURNISHING | 2019-09-19 | 2019-12-17 | 2023-10-22 | 2024-01-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | JJ024-017 | Locker Rooms and Gym Entrance | 9 | SUBSTANTIAL COMPLETION | 2019-12-18 | 2020-02-15 | 2024-01-20 | 2024-03-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | JJ024-017 | Locker Rooms and Gym Entrance | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-02-16 | 2020-03-16 | 2024-03-20 | 2027-05-03
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | JJ029-018 | Theater ADA Upgrades | 1 | DEVELOP SCOPE | 2018-06-01 | 2018-08-29 | 2021-07-01 | 2021-09-29
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | JJ029-018 | Theater ADA Upgrades | 2 | PRELIMINARY DESIGN | 2018-08-30 | 2018-12-27 | 2021-09-30 | 2022-01-27
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | JJ029-018 | Theater ADA Upgrades | 3 | FINAL DESIGN | 2018-12-28 | 2019-06-25 | 2022-01-28 | 2022-07-26
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | JJ029-018 | Theater ADA Upgrades | 4 | BID AWARD AND REGISTER CONTRCT | 2019-06-26 | 2019-09-23 | 2022-07-27 | 2022-10-24
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | JJ029-018 | Theater ADA Upgrades | 5 | CONSTRUCTION TO 25% | 2019-09-24 | 2020-01-21 | 2022-10-25 | 2023-02-21
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | JJ029-018 | Theater ADA Upgrades | 6 | CONSTRUCTION TO 50% | 2020-01-22 | 2020-05-20 | 2023-02-22 | 2023-06-21
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | JJ029-018 | Theater ADA Upgrades | 7 | CONSTRUCTION TO 75% | 2020-05-21 | 2020-09-17 | 2023-06-22 | 2023-10-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | JJ029-018 | Theater ADA Upgrades | 8 | ORIGINAL EQUIP & FURNISHING | 2020-09-18 | 2020-12-16 | 2023-10-20 | 2024-01-17
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | JJ029-018 | Theater ADA Upgrades | 9 | SUBSTANTIAL COMPLETION | 2020-12-17 | 2021-02-14 | 2024-01-18 | 2024-03-17
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | JJ029-018 | Theater ADA Upgrades | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-02-15 | 2021-03-16 | 2024-03-18 | 2024-04-16
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MC001-021 | Library Interior Renovation | 1 | DEVELOP SCOPE | 2021-06-30 | 2021-09-27 | 2021-06-30 | 2021-09-27
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MC001-021 | Library Interior Renovation | 2 | PRELIMINARY DESIGN | 2021-09-28 | 2022-01-25 | 2021-09-28 | 2022-01-25
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MC001-021 | Library Interior Renovation | 3 | FINAL DESIGN | 2022-01-26 | 2022-07-24 | 2022-01-26 | 2022-07-24
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MC001-021 | Library Interior Renovation | 4 | BID AWARD AND REGISTER CONTRCT | 2022-07-25 | 2022-10-22 | 2022-07-25 | 2022-10-22
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MC001-021 | Library Interior Renovation | 5 | CONSTRUCTION TO 25% | 2022-10-23 | 2023-02-19 | 2022-10-23 | 2023-02-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MC001-021 | Library Interior Renovation | 6 | CONSTRUCTION TO 50% | 2023-02-20 | 2023-06-19 | 2023-02-20 | 2023-06-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MC001-021 | Library Interior Renovation | 7 | CONSTRUCTION TO 75% | 2023-06-20 | 2023-10-17 | 2023-06-20 | 2023-10-17
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MC001-021 | Library Interior Renovation | 8 | ORIGINAL EQUIP & FURNISHING | 2023-10-18 | 2024-01-15 | 2023-10-18 | 2024-01-15
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MC001-021 | Library Interior Renovation | 9 | SUBSTANTIAL COMPLETION | 2024-01-16 | 2024-03-15 | 2024-01-16 | 2024-03-15
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MC001-021 | Library Interior Renovation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-03-16 | 2024-04-14 | 2024-03-16 | 2024-04-14
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MC028-010 | CUNY: BMCC, 199 Chambers Street - EE Upgrade | 1 | DEVELOP SCOPE | 2010-06-01 | 2010-08-29 | 2019-07-01 | 2019-09-28
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MC028-010 | CUNY: BMCC, 199 Chambers Street - EE Upgrade | 2 | PRELIMINARY DESIGN | 2010-08-30 | 2010-12-27 | 2019-09-29 | 2020-01-26
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MC028-010 | CUNY: BMCC, 199 Chambers Street - EE Upgrade | 3 | FINAL DESIGN | 2010-12-28 | 2011-06-25 | 2020-01-27 | 2020-07-24
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MC028-010 | CUNY: BMCC, 199 Chambers Street - EE Upgrade | 4 | BID AWARD AND REGISTER CONTRCT | 2011-06-26 | 2011-09-23 | 2020-07-25 | 2020-10-22
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MC028-010 | CUNY: BMCC, 199 Chambers Street - EE Upgrade | 5 | CONSTRUCTION TO 25% | 2011-09-24 | 2012-01-21 | 2020-10-23 | 2021-02-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MC028-010 | CUNY: BMCC, 199 Chambers Street - EE Upgrade | 6 | CONSTRUCTION TO 50% | 2012-01-22 | 2012-05-20 | 2021-02-20 | 2021-06-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MC028-010 | CUNY: BMCC, 199 Chambers Street - EE Upgrade | 7 | CONSTRUCTION TO 75% | 2012-05-21 | 2012-09-17 | 2021-06-20 | 2021-10-17
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MC028-010 | CUNY: BMCC, 199 Chambers Street - EE Upgrade | 8 | ORIGINAL EQUIP & FURNISHING | 2012-09-18 | 2012-12-16 | 2021-10-18 | 2022-01-15
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MC028-010 | CUNY: BMCC, 199 Chambers Street - EE Upgrade | 9 | SUBSTANTIAL COMPLETION | 2012-12-17 | 2013-02-14 | 2022-01-16 | 2022-03-16
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MC028-010 | CUNY: BMCC, 199 Chambers Street - EE Upgrade | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-02-15 | 2013-03-16 | 2022-03-17 | 2023-06-30
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MC029-012 | Gymnasium Air Conditioning System | 1 | DEVELOP SCOPE | 2012-06-01 | 2012-08-29 | 2012-06-01 | 2012-08-29
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MC029-012 | Gymnasium Air Conditioning System | 2 | PRELIMINARY DESIGN | 2012-08-30 | 2012-12-27 | 2012-08-30 | 2012-12-27
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MC029-012 | Gymnasium Air Conditioning System | 3 | FINAL DESIGN | 2012-12-28 | 2013-06-25 | 2012-12-28 | 2013-06-25
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MC029-012 | Gymnasium Air Conditioning System | 4 | BID AWARD AND REGISTER CONTRCT | 2013-06-26 | 2013-09-23 | 2013-06-26 | 2013-09-23
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MC029-012 | Gymnasium Air Conditioning System | 5 | CONSTRUCTION TO 25% | 2013-09-24 | 2014-01-21 | 2013-09-24 | 2014-01-21
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MC029-012 | Gymnasium Air Conditioning System | 6 | CONSTRUCTION TO 50% | 2014-01-22 | 2014-05-21 | 2014-01-22 | 2014-05-21
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MC029-012 | Gymnasium Air Conditioning System | 7 | CONSTRUCTION TO 75% | 2014-05-22 | 2014-09-18 | 2014-05-22 | 2014-09-18
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MC029-012 | Gymnasium Air Conditioning System | 8 | ORIGINAL EQUIP & FURNISHING | 2014-09-19 | 2014-12-17 | 2014-09-19 | 2014-12-17
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MC029-012 | Gymnasium Air Conditioning System | 9 | SUBSTANTIAL COMPLETION | 2014-12-18 | 2015-02-15 | 2014-12-18 | 2015-02-15
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MC029-012 | Gymnasium Air Conditioning System | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-02-16 | 2015-03-17 | 2015-02-16 | 2024-12-30
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MC036-016 | Perimeter Security Lighting | 1 | DEVELOP SCOPE | 2016-06-30 | 2016-09-27 | 2021-07-01 | 2021-09-28
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MC036-016 | Perimeter Security Lighting | 2 | PRELIMINARY DESIGN | 2016-09-28 | 2017-01-25 | 2021-09-29 | 2022-01-26
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MC036-016 | Perimeter Security Lighting | 3 | FINAL DESIGN | 2017-01-26 | 2017-07-24 | 2022-01-27 | 2022-07-25
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MC036-016 | Perimeter Security Lighting | 4 | BID AWARD AND REGISTER CONTRCT | 2017-07-25 | 2017-10-22 | 2022-07-26 | 2022-10-23
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MC036-016 | Perimeter Security Lighting | 5 | CONSTRUCTION TO 25% | 2017-10-23 | 2018-02-19 | 2022-10-24 | 2023-02-20
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MC036-016 | Perimeter Security Lighting | 6 | CONSTRUCTION TO 50% | 2018-02-20 | 2018-06-19 | 2023-02-21 | 2023-06-20
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MC036-016 | Perimeter Security Lighting | 7 | CONSTRUCTION TO 75% | 2018-06-20 | 2018-10-17 | 2023-06-21 | 2023-10-18
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MC036-016 | Perimeter Security Lighting | 8 | ORIGINAL EQUIP & FURNISHING | 2018-10-18 | 2019-01-15 | 2023-10-19 | 2024-01-16
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MC036-016 | Perimeter Security Lighting | 9 | SUBSTANTIAL COMPLETION | 2019-01-16 | 2019-03-16 | 2024-01-17 | 2024-03-16
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MC036-016 | Perimeter Security Lighting | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-03-17 | 2019-04-15 | 2024-03-17 | 2027-04-30
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MC040-018 | LED Conversion in Public Areas | 1 | DEVELOP SCOPE | 2018-06-01 | 2018-08-29 | 2020-07-01 | 2020-09-28
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MC040-018 | LED Conversion in Public Areas | 2 | PRELIMINARY DESIGN | 2018-08-30 | 2018-12-27 | 2020-09-29 | 2021-01-26
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MC040-018 | LED Conversion in Public Areas | 3 | FINAL DESIGN | 2018-12-28 | 2019-06-25 | 2021-01-27 | 2021-07-25
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MC040-018 | LED Conversion in Public Areas | 4 | BID AWARD AND REGISTER CONTRCT | 2019-06-26 | 2019-09-23 | 2021-07-26 | 2021-10-23
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MC040-018 | LED Conversion in Public Areas | 5 | CONSTRUCTION TO 25% | 2019-09-24 | 2020-01-21 | 2021-10-24 | 2022-02-20
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MC040-018 | LED Conversion in Public Areas | 6 | CONSTRUCTION TO 50% | 2020-01-22 | 2020-05-20 | 2022-02-21 | 2022-06-20
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MC040-018 | LED Conversion in Public Areas | 7 | CONSTRUCTION TO 75% | 2020-05-21 | 2020-09-17 | 2022-06-21 | 2022-10-18
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MC040-018 | LED Conversion in Public Areas | 8 | ORIGINAL EQUIP & FURNISHING | 2020-09-18 | 2020-12-16 | 2022-10-19 | 2023-01-16
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MC040-018 | LED Conversion in Public Areas | 9 | SUBSTANTIAL COMPLETION | 2020-12-17 | 2021-02-14 | 2023-01-17 | 2023-03-17
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MC040-018 | LED Conversion in Public Areas | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-02-15 | 2021-03-16 | 2023-03-18 | 2023-04-16
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MC042-018 | BMCC Pedestrian Enclosed Extension | 1 | DEVELOP SCOPE | 2018-06-01 | 2018-08-29 | 2020-07-01 | 2020-09-28
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MC042-018 | BMCC Pedestrian Enclosed Extension | 2 | PRELIMINARY DESIGN | 2018-08-30 | 2018-12-27 | 2020-09-29 | 2021-01-26
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MC042-018 | BMCC Pedestrian Enclosed Extension | 3 | FINAL DESIGN | 2018-12-28 | 2019-06-25 | 2021-01-27 | 2021-07-25
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MC042-018 | BMCC Pedestrian Enclosed Extension | 4 | BID AWARD AND REGISTER CONTRCT | 2019-06-26 | 2019-09-23 | 2021-07-26 | 2021-10-23
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MC042-018 | BMCC Pedestrian Enclosed Extension | 5 | CONSTRUCTION TO 25% | 2019-09-24 | 2020-01-21 | 2021-10-24 | 2022-02-20
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MC042-018 | BMCC Pedestrian Enclosed Extension | 6 | CONSTRUCTION TO 50% | 2020-01-22 | 2020-05-20 | 2022-02-21 | 2022-06-20
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MC042-018 | BMCC Pedestrian Enclosed Extension | 7 | CONSTRUCTION TO 75% | 2020-05-21 | 2020-09-17 | 2022-06-21 | 2022-10-18
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MC042-018 | BMCC Pedestrian Enclosed Extension | 8 | ORIGINAL EQUIP & FURNISHING | 2020-09-18 | 2020-12-16 | 2022-10-19 | 2023-01-16
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MC042-018 | BMCC Pedestrian Enclosed Extension | 9 | SUBSTANTIAL COMPLETION | 2020-12-17 | 2021-02-14 | 2023-01-17 | 2023-03-17
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MC042-018 | BMCC Pedestrian Enclosed Extension | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-02-15 | 2021-03-16 | 2023-03-18 | 2023-04-16
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MC044-019 | New Corridor Access Controls and Doors | 1 | DEVELOP SCOPE | 2019-06-30 | 2019-09-27 | 2020-07-01 | 2020-09-28
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MC044-019 | New Corridor Access Controls and Doors | 2 | PRELIMINARY DESIGN | 2019-09-28 | 2020-01-25 | 2020-09-29 | 2021-01-26
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MC044-019 | New Corridor Access Controls and Doors | 3 | FINAL DESIGN | 2020-01-26 | 2020-07-23 | 2021-01-27 | 2021-07-25
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MC044-019 | New Corridor Access Controls and Doors | 4 | BID AWARD AND REGISTER CONTRCT | 2020-07-24 | 2020-10-21 | 2021-07-26 | 2021-10-23
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MC044-019 | New Corridor Access Controls and Doors | 5 | CONSTRUCTION TO 25% | 2020-10-22 | 2021-02-18 | 2021-10-24 | 2022-02-20
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MC044-019 | New Corridor Access Controls and Doors | 6 | CONSTRUCTION TO 50% | 2021-02-19 | 2021-06-18 | 2022-02-21 | 2022-06-20
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MC044-019 | New Corridor Access Controls and Doors | 7 | CONSTRUCTION TO 75% | 2021-06-19 | 2021-10-16 | 2022-06-21 | 2022-10-18
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MC044-019 | New Corridor Access Controls and Doors | 8 | ORIGINAL EQUIP & FURNISHING | 2021-10-17 | 2022-01-14 | 2022-10-19 | 2023-01-16
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MC044-019 | New Corridor Access Controls and Doors | 9 | SUBSTANTIAL COMPLETION | 2022-01-15 | 2022-03-15 | 2023-01-17 | 2023-03-17
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MC044-019 | New Corridor Access Controls and Doors | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-16 | 2022-04-14 | 2023-03-18 | 2027-04-30
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MC045-020 | Tribeca Performing Arts Center Theater 1 & 2 Lighting Upgra | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-09-28 | 2019-07-01 | 2019-09-28
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MC045-020 | Tribeca Performing Arts Center Theater 1 & 2 Lighting Upgra | 2 | PRELIMINARY DESIGN | 2019-09-29 | 2020-01-26 | 2019-09-29 | 2020-01-26
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MC045-020 | Tribeca Performing Arts Center Theater 1 & 2 Lighting Upgra | 3 | FINAL DESIGN | 2020-01-27 | 2020-07-24 | 2020-01-27 | 2020-07-24
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MC045-020 | Tribeca Performing Arts Center Theater 1 & 2 Lighting Upgra | 4 | BID AWARD AND REGISTER CONTRCT | 2020-07-25 | 2020-10-22 | 2020-07-25 | 2020-10-22
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MC045-020 | Tribeca Performing Arts Center Theater 1 & 2 Lighting Upgra | 5 | CONSTRUCTION TO 25% | 2020-10-23 | 2021-02-19 | 2020-10-23 | 2021-02-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MC045-020 | Tribeca Performing Arts Center Theater 1 & 2 Lighting Upgra | 6 | CONSTRUCTION TO 50% | 2021-02-20 | 2021-06-19 | 2021-02-20 | 2021-06-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MC045-020 | Tribeca Performing Arts Center Theater 1 & 2 Lighting Upgra | 7 | CONSTRUCTION TO 75% | 2021-06-20 | 2021-10-17 | 2021-06-20 | 2021-10-17
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MC045-020 | Tribeca Performing Arts Center Theater 1 & 2 Lighting Upgra | 8 | ORIGINAL EQUIP & FURNISHING | 2021-10-18 | 2022-01-15 | 2021-10-18 | 2022-01-15
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MC045-020 | Tribeca Performing Arts Center Theater 1 & 2 Lighting Upgra | 9 | SUBSTANTIAL COMPLETION | 2022-01-16 | 2022-03-16 | 2022-01-16 | 2022-03-16
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MC045-020 | Tribeca Performing Arts Center Theater 1 & 2 Lighting Upgra | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-17 | 2022-04-15 | 2022-03-17 | 2025-04-15
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MH040-014 | Macaulay Honors College Classroom Upgrades | 1 | DEVELOP SCOPE | 2014-06-01 | 2014-08-29 | 2021-07-01 | 2021-09-28
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MH040-014 | Macaulay Honors College Classroom Upgrades | 2 | PRELIMINARY DESIGN | 2014-08-30 | 2014-12-27 | 2021-09-29 | 2022-01-26
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MH040-014 | Macaulay Honors College Classroom Upgrades | 3 | FINAL DESIGN | 2014-12-28 | 2015-06-25 | 2022-01-27 | 2022-07-25
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MH040-014 | Macaulay Honors College Classroom Upgrades | 4 | BID AWARD AND REGISTER CONTRCT | 2015-06-26 | 2015-09-23 | 2022-07-26 | 2022-10-23
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MH040-014 | Macaulay Honors College Classroom Upgrades | 5 | CONSTRUCTION TO 25% | 2015-09-24 | 2016-01-21 | 2022-10-24 | 2023-02-20
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MH040-014 | Macaulay Honors College Classroom Upgrades | 6 | CONSTRUCTION TO 50% | 2016-01-22 | 2016-05-20 | 2023-02-21 | 2023-06-20
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MH040-014 | Macaulay Honors College Classroom Upgrades | 7 | CONSTRUCTION TO 75% | 2016-05-21 | 2016-09-17 | 2023-06-21 | 2023-10-18
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MH040-014 | Macaulay Honors College Classroom Upgrades | 8 | ORIGINAL EQUIP & FURNISHING | 2016-09-18 | 2016-12-16 | 2023-10-19 | 2024-01-16
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MH040-014 | Macaulay Honors College Classroom Upgrades | 9 | SUBSTANTIAL COMPLETION | 2016-12-17 | 2017-02-14 | 2024-01-17 | 2024-03-16
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MH040-014 | Macaulay Honors College Classroom Upgrades | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-02-15 | 2017-03-16 | 2024-03-17 | 2026-04-30
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MH053-016 | Macaulay Honors College - New Media Lab | 1 | DEVELOP SCOPE | 2015-06-01 | 2015-08-29 | 2015-06-01 | 2015-08-29
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MH053-016 | Macaulay Honors College - New Media Lab | 2 | PRELIMINARY DESIGN | 2015-08-30 | 2015-12-27 | 2015-08-30 | 2015-12-27
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MH053-016 | Macaulay Honors College - New Media Lab | 3 | FINAL DESIGN | 2015-12-28 | 2016-06-24 | 2015-12-28 | 2016-06-24
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MH053-016 | Macaulay Honors College - New Media Lab | 4 | BID AWARD AND REGISTER CONTRCT | 2016-06-25 | 2016-09-22 | 2016-06-25 | 2016-09-22
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MH053-016 | Macaulay Honors College - New Media Lab | 5 | CONSTRUCTION TO 25% | 2016-09-23 | 2017-01-20 | 2016-09-23 | 2017-01-20
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MH053-016 | Macaulay Honors College - New Media Lab | 6 | CONSTRUCTION TO 50% | 2017-01-21 | 2017-05-20 | 2017-01-21 | 2017-05-20
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MH053-016 | Macaulay Honors College - New Media Lab | 7 | CONSTRUCTION TO 75% | 2017-05-21 | 2017-09-17 | 2017-05-21 | 2017-09-17
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MH053-016 | Macaulay Honors College - New Media Lab | 8 | ORIGINAL EQUIP & FURNISHING | 2017-09-18 | 2017-12-16 | 2017-09-18 | 2017-12-16
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MH053-016 | Macaulay Honors College - New Media Lab | 9 | SUBSTANTIAL COMPLETION | 2017-12-17 | 2018-02-14 | 2017-12-17 | 2018-02-14
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MH053-016 | Macaulay Honors College - New Media Lab | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-02-15 | 2018-03-16 | 2018-02-15 | 2025-06-30
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MH059-017 | Macaulay Honors College Data Science Lab | 1 | DEVELOP SCOPE | 2017-06-01 | 2017-08-29 | 2021-07-01 | 2021-09-28
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MH059-017 | Macaulay Honors College Data Science Lab | 2 | PRELIMINARY DESIGN | 2017-08-30 | 2017-12-27 | 2021-09-29 | 2022-01-26
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MH059-017 | Macaulay Honors College Data Science Lab | 3 | FINAL DESIGN | 2017-12-28 | 2018-06-25 | 2022-01-27 | 2022-07-25
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MH059-017 | Macaulay Honors College Data Science Lab | 4 | BID AWARD AND REGISTER CONTRCT | 2018-06-26 | 2018-09-23 | 2022-07-26 | 2022-10-23
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MH059-017 | Macaulay Honors College Data Science Lab | 5 | CONSTRUCTION TO 25% | 2018-09-24 | 2019-01-21 | 2022-10-24 | 2023-02-20
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MH059-017 | Macaulay Honors College Data Science Lab | 6 | CONSTRUCTION TO 50% | 2019-01-22 | 2019-05-21 | 2023-02-21 | 2023-06-20
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MH059-017 | Macaulay Honors College Data Science Lab | 7 | CONSTRUCTION TO 75% | 2019-05-22 | 2019-09-18 | 2023-06-21 | 2023-10-18
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MH059-017 | Macaulay Honors College Data Science Lab | 8 | ORIGINAL EQUIP & FURNISHING | 2019-09-19 | 2019-12-17 | 2023-10-19 | 2024-01-16
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MH059-017 | Macaulay Honors College Data Science Lab | 9 | SUBSTANTIAL COMPLETION | 2019-12-18 | 2020-02-15 | 2024-01-17 | 2024-03-16
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MH059-017 | Macaulay Honors College Data Science Lab | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-02-16 | 2020-03-16 | 2024-03-17 | 2027-04-30
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MH060-020 | New Media/Data Science Lab | 1 | DEVELOP SCOPE | 2020-06-30 | 2020-09-27 | 2020-06-30 | 2020-09-27
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MH060-020 | New Media/Data Science Lab | 2 | PRELIMINARY DESIGN | 2020-09-28 | 2021-01-25 | 2020-09-28 | 2021-01-25
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MH060-020 | New Media/Data Science Lab | 3 | FINAL DESIGN | 2021-01-26 | 2021-07-24 | 2021-01-26 | 2021-07-24
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MH060-020 | New Media/Data Science Lab | 4 | BID AWARD AND REGISTER CONTRCT | 2021-07-25 | 2021-10-22 | 2021-07-25 | 2021-10-22
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MH060-020 | New Media/Data Science Lab | 5 | CONSTRUCTION TO 25% | 2021-10-23 | 2022-02-19 | 2021-10-23 | 2022-02-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MH060-020 | New Media/Data Science Lab | 6 | CONSTRUCTION TO 50% | 2022-02-20 | 2022-06-19 | 2022-02-20 | 2022-06-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MH060-020 | New Media/Data Science Lab | 7 | CONSTRUCTION TO 75% | 2022-06-20 | 2022-10-17 | 2022-06-20 | 2022-10-17
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MH060-020 | New Media/Data Science Lab | 8 | ORIGINAL EQUIP & FURNISHING | 2022-10-18 | 2023-01-15 | 2022-10-18 | 2023-01-15
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MH060-020 | New Media/Data Science Lab | 9 | SUBSTANTIAL COMPLETION | 2023-01-16 | 2023-03-16 | 2023-01-16 | 2023-03-16
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | MH060-020 | New Media/Data Science Lab | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-03-17 | 2023-04-15 | 2023-03-17 | 2027-04-30
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | SAND-MC01 | Rehabilitation and Improvements due to Hurricane Sandy | 1 | DEVELOP SCOPE | 2013-06-30 | 2013-09-27 | 2013-06-30 | 2013-09-27
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | SAND-MC01 | Rehabilitation and Improvements due to Hurricane Sandy | 2 | PRELIMINARY DESIGN | 2013-09-28 | 2014-01-25 | 2013-09-28 | 2014-01-25
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | SAND-MC01 | Rehabilitation and Improvements due to Hurricane Sandy | 3 | FINAL DESIGN | 2014-01-26 | 2014-07-24 | 2014-01-26 | 2014-07-24
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | SAND-MC01 | Rehabilitation and Improvements due to Hurricane Sandy | 4 | BID AWARD AND REGISTER CONTRCT | 2014-07-25 | 2014-10-22 | 2014-07-25 | 2014-10-22
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | SAND-MC01 | Rehabilitation and Improvements due to Hurricane Sandy | 5 | CONSTRUCTION TO 25% | 2014-10-23 | 2015-02-19 | 2014-10-23 | 2015-02-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | SAND-MC01 | Rehabilitation and Improvements due to Hurricane Sandy | 6 | CONSTRUCTION TO 50% | 2015-02-20 | 2015-06-19 | 2015-02-20 | 2015-06-19
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | SAND-MC01 | Rehabilitation and Improvements due to Hurricane Sandy | 7 | CONSTRUCTION TO 75% | 2015-06-20 | 2015-10-17 | 2015-06-20 | 2015-10-17
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | SAND-MC01 | Rehabilitation and Improvements due to Hurricane Sandy | 8 | ORIGINAL EQUIP & FURNISHING | 2015-10-18 | 2016-01-15 | 2015-10-18 | 2016-01-15
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | SAND-MC01 | Rehabilitation and Improvements due to Hurricane Sandy | 9 | SUBSTANTIAL COMPLETION | 2016-01-16 | 2016-03-15 | 2016-01-16 | 2016-03-15
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | SAND-MC01 | Rehabilitation and Improvements due to Hurricane Sandy | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-16 | 2016-04-14 | 2016-03-16 | 2024-04-30
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | SJ049-015 | School of Journalism - Space Upgrades | 1 | DEVELOP SCOPE | 2014-10-01 | 2014-12-29 | 2020-07-01 | 2020-09-28
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | SJ049-015 | School of Journalism - Space Upgrades | 2 | PRELIMINARY DESIGN | 2014-12-30 | 2015-04-28 | 2020-09-29 | 2021-01-26
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | SJ049-015 | School of Journalism - Space Upgrades | 3 | FINAL DESIGN | 2015-04-29 | 2015-10-25 | 2021-01-27 | 2021-07-25
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | SJ049-015 | School of Journalism - Space Upgrades | 4 | BID AWARD AND REGISTER CONTRCT | 2015-10-26 | 2016-01-23 | 2021-07-26 | 2021-10-23
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | SJ049-015 | School of Journalism - Space Upgrades | 5 | CONSTRUCTION TO 25% | 2016-01-24 | 2016-05-22 | 2021-10-24 | 2022-02-20
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | SJ049-015 | School of Journalism - Space Upgrades | 6 | CONSTRUCTION TO 50% | 2016-05-23 | 2016-09-19 | 2022-02-21 | 2022-06-20
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | SJ049-015 | School of Journalism - Space Upgrades | 7 | CONSTRUCTION TO 75% | 2016-09-20 | 2017-01-17 | 2022-06-21 | 2022-10-18
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | SJ049-015 | School of Journalism - Space Upgrades | 8 | ORIGINAL EQUIP & FURNISHING | 2017-01-18 | 2017-04-17 | 2022-10-19 | 2023-01-16
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | SJ049-015 | School of Journalism - Space Upgrades | 9 | SUBSTANTIAL COMPLETION | 2017-04-18 | 2017-06-16 | 2023-01-17 | 2023-03-17
20201123 | MANHATTAN | 042 | CITY UNIVERSITY | SJ049-015 | School of Journalism - Space Upgrades | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-06-17 | 2017-07-16 | 2023-03-18 | 2026-04-16
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79 PAL | POLICE ATHLETIC LEAGUE MASONRY | 1 | DESIGN | 2009-12-31 | 2010-06-28 | 2012-12-31 | 2013-06-28
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79 PAL | POLICE ATHLETIC LEAGUE MASONRY | 2 | BID AWARD AND REGISTER CONTRCT | 2010-06-29 | 2010-09-26 | 2013-06-29 | 2013-09-26
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79 PAL | POLICE ATHLETIC LEAGUE MASONRY | 3 | CONSTRUCTION | 2010-09-27 | 2011-09-26 | 2013-09-27 | 2020-09-01
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79 PAL | POLICE ATHLETIC LEAGUE MASONRY | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2011-09-27 | 2012-03-24 | 2020-09-02 | 2024-02-29
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79137CS | 137 centre street renovation | 1 | DESIGN | 2020-07-30 | 2021-01-25 | 2020-07-30 | 2021-01-25
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79137CS | 137 centre street renovation | 2 | BID AWARD AND REGISTER CONTRCT | 2021-01-26 | 2021-04-25 | 2021-01-26 | 2021-04-25
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79137CS | 137 centre street renovation | 3 | CONSTRUCTION | 2021-04-26 | 2022-04-25 | 2021-04-26 | 2022-04-25
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79137CS | 137 centre street renovation | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-04-26 | 2022-10-22 | 2022-04-26 | 2022-10-22
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO791PPDR | One Police Plaza Doors | 1 | DESIGN | 2019-12-15 | 2020-06-11 | 2019-12-15 | 2020-06-11
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO791PPDR | One Police Plaza Doors | 2 | BID AWARD AND REGISTER CONTRCT | 2020-06-12 | 2020-09-09 | 2020-06-12 | 2020-09-09
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO791PPDR | One Police Plaza Doors | 3 | CONSTRUCTION | 2020-09-10 | 2021-09-09 | 2021-09-10 | 2022-09-09
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO791PPDR | One Police Plaza Doors | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-10 | 2022-03-08 | 2022-09-10 | 2024-03-07
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO791PPR2 | ONE POLICE PLAZA & POLICE LAB ROOFS | 1 | DESIGN | 2019-08-15 | 2020-02-10 | 2019-08-15 | 2020-02-10
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO791PPR2 | ONE POLICE PLAZA & POLICE LAB ROOFS | 2 | BID AWARD AND REGISTER CONTRCT | 2020-02-11 | 2020-05-10 | 2020-02-11 | 2020-05-10
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO791PPR2 | ONE POLICE PLAZA & POLICE LAB ROOFS | 3 | CONSTRUCTION | 2020-05-11 | 2021-05-10 | 2020-05-11 | 2021-05-10
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO791PPR2 | ONE POLICE PLAZA & POLICE LAB ROOFS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-05-11 | 2021-11-06 | 2021-05-11 | 2021-11-06
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAHO | HVAC REPLACEMENT FOR 20TH, 24TH AND 25TH PCTS | 1 | DEVELOP SCOPE | 2014-06-30 | 2014-09-27 | 2014-06-30 | 2014-09-27
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAHO | HVAC REPLACEMENT FOR 20TH, 24TH AND 25TH PCTS | 2 | PRELIMINARY DESIGN | 2014-09-28 | 2015-01-25 | 2014-09-28 | 2015-01-25
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAHO | HVAC REPLACEMENT FOR 20TH, 24TH AND 25TH PCTS | 3 | FINAL DESIGN | 2015-01-26 | 2015-07-24 | 2015-01-26 | 2015-07-24
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAHO | HVAC REPLACEMENT FOR 20TH, 24TH AND 25TH PCTS | 4 | BID AWARD AND REGISTER CONTRCT | 2015-07-25 | 2015-10-22 | 2015-07-25 | 2015-10-22
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAHO | HVAC REPLACEMENT FOR 20TH, 24TH AND 25TH PCTS | 5 | CONSTRUCTION TO 25% | 2015-10-23 | 2016-02-19 | 2015-10-23 | 2016-02-19
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAHO | HVAC REPLACEMENT FOR 20TH, 24TH AND 25TH PCTS | 6 | CONSTRUCTION TO 50% | 2016-02-20 | 2016-06-18 | 2016-02-20 | 2016-06-18
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAHO | HVAC REPLACEMENT FOR 20TH, 24TH AND 25TH PCTS | 7 | CONSTRUCTION TO 75% | 2016-06-19 | 2016-10-16 | 2016-06-19 | 2020-10-16
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAHO | HVAC REPLACEMENT FOR 20TH, 24TH AND 25TH PCTS | 8 | ORIGINAL EQUIP & FURNISHING | 2016-10-17 | 2017-01-14 | 2020-10-17 | 2021-01-14
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAHO | HVAC REPLACEMENT FOR 20TH, 24TH AND 25TH PCTS | 9 | SUBSTANTIAL COMPLETION | 2017-01-15 | 2017-03-15 | 2021-01-15 | 2021-03-15
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAHO | HVAC REPLACEMENT FOR 20TH, 24TH AND 25TH PCTS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-16 | 2017-04-14 | 2021-03-16 | 2022-04-14
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAIZ | 24th Precinct Facade | 1 | DEVELOP SCOPE | 2016-06-30 | 2016-09-27 | 2016-06-30 | 2016-09-27
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAIZ | 24th Precinct Facade | 2 | PRELIMINARY DESIGN | 2016-09-28 | 2017-01-25 | 2016-09-28 | 2017-01-25
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAIZ | 24th Precinct Facade | 3 | FINAL DESIGN | 2017-01-26 | 2017-05-25 | 2017-01-26 | 2017-05-25
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAIZ | 24th Precinct Facade | 4 | BID AWARD AND REGISTER CONTRCT | 2017-05-26 | 2017-11-21 | 2017-05-26 | 2017-11-21
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAIZ | 24th Precinct Facade | 5 | CONSTRUCTION TO 25% | 2017-11-22 | 2018-03-21 | 2017-11-22 | 2018-03-21
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAIZ | 24th Precinct Facade | 6 | CONSTRUCTION TO 50% | 2018-03-22 | 2018-07-19 | 2018-03-22 | 2018-07-19
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAIZ | 24th Precinct Facade | 7 | CONSTRUCTION TO 75% | 2018-07-20 | 2018-11-16 | 2018-07-20 | 2021-11-16
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAIZ | 24th Precinct Facade | 8 | ORIGINAL EQUIP & FURNISHING | 2018-11-17 | 2019-02-14 | 2021-11-17 | 2022-02-14
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAIZ | 24th Precinct Facade | 9 | SUBSTANTIAL COMPLETION | 2019-02-15 | 2019-04-15 | 2022-02-15 | 2022-04-15
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAIZ | 24th Precinct Facade | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-04-16 | 2019-05-15 | 2022-04-16 | 2022-05-15
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAJF | 32ND PCT PARKING LOT | 1 | DEVELOP SCOPE | 2017-04-19 | 2017-07-17 | 2017-04-19 | 2017-07-17
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAJF | 32ND PCT PARKING LOT | 2 | PRELIMINARY DESIGN | 2017-07-18 | 2017-11-14 | 2017-07-18 | 2017-11-14
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAJF | 32ND PCT PARKING LOT | 3 | FINAL DESIGN | 2017-11-15 | 2018-05-13 | 2017-11-15 | 2018-05-13
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAJF | 32ND PCT PARKING LOT | 4 | BID AWARD AND REGISTER CONTRCT | 2018-05-14 | 2018-08-11 | 2018-05-14 | 2018-08-11
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAJF | 32ND PCT PARKING LOT | 5 | CONSTRUCTION TO 25% | 2018-08-12 | 2018-12-09 | 2018-08-12 | 2018-12-09
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAJF | 32ND PCT PARKING LOT | 6 | CONSTRUCTION TO 50% | 2018-12-10 | 2019-04-08 | 2018-12-10 | 2019-04-08
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAJF | 32ND PCT PARKING LOT | 7 | CONSTRUCTION TO 75% | 2019-04-09 | 2019-08-06 | 2019-04-09 | 2021-08-06
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAJF | 32ND PCT PARKING LOT | 8 | ORIGINAL EQUIP & FURNISHING | 2019-08-07 | 2019-11-04 | 2021-08-07 | 2021-11-04
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAJF | 32ND PCT PARKING LOT | 9 | SUBSTANTIAL COMPLETION | 2019-11-05 | 2020-01-03 | 2021-11-05 | 2022-01-03
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAJF | 32ND PCT PARKING LOT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-01-04 | 2020-02-02 | 2022-01-04 | 2022-02-02
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAJQ | 1 Police Plaza Auditorium | 1 | DEVELOP SCOPE | 2017-06-10 | 2017-09-07 | 2016-06-09 | 2016-09-06
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAJQ | 1 Police Plaza Auditorium | 2 | PRELIMINARY DESIGN | 2017-09-08 | 2018-01-05 | 2016-09-07 | 2017-01-04
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAJQ | 1 Police Plaza Auditorium | 3 | FINAL DESIGN | 2018-01-06 | 2018-05-05 | 2017-01-05 | 2017-05-04
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAJQ | 1 Police Plaza Auditorium | 4 | BID AWARD AND REGISTER CONTRCT | 2018-05-06 | 2018-11-01 | 2017-05-05 | 2017-10-31
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAJQ | 1 Police Plaza Auditorium | 5 | CONSTRUCTION TO 25% | 2018-11-02 | 2019-03-01 | 2017-11-01 | 2018-02-28
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAJQ | 1 Police Plaza Auditorium | 6 | CONSTRUCTION TO 50% | 2019-03-02 | 2019-06-29 | 2018-03-01 | 2018-06-28
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAJQ | 1 Police Plaza Auditorium | 7 | CONSTRUCTION TO 75% | 2019-06-30 | 2019-10-27 | 2021-06-29 | 2022-02-27
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAJQ | 1 Police Plaza Auditorium | 8 | ORIGINAL EQUIP & FURNISHING | 2019-10-28 | 2020-01-25 | 2022-02-28 | 2022-05-28
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAJQ | 1 Police Plaza Auditorium | 9 | SUBSTANTIAL COMPLETION | 2020-01-26 | 2020-03-25 | 2022-05-29 | 2022-07-27
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAJQ | 1 Police Plaza Auditorium | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-03-26 | 2020-04-24 | 2022-07-28 | 2022-08-26
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAKC | ELEVATOR REHABILITATION FOR MIDTOWN NORTH PCT | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-08-29 | 2020-06-01 | 2020-08-29
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAKC | ELEVATOR REHABILITATION FOR MIDTOWN NORTH PCT | 2 | PRELIMINARY DESIGN | 2020-08-30 | 2020-12-27 | 2020-08-30 | 2020-12-27
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAKC | ELEVATOR REHABILITATION FOR MIDTOWN NORTH PCT | 3 | FINAL DESIGN | 2020-12-28 | 2021-04-26 | 2020-12-28 | 2021-04-26
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAKC | ELEVATOR REHABILITATION FOR MIDTOWN NORTH PCT | 4 | BID AWARD AND REGISTER CONTRCT | 2021-04-27 | 2021-10-23 | 2021-04-27 | 2021-10-23
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAKC | ELEVATOR REHABILITATION FOR MIDTOWN NORTH PCT | 5 | CONSTRUCTION TO 25% | 2021-10-24 | 2022-02-20 | 2021-10-24 | 2022-02-20
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAKC | ELEVATOR REHABILITATION FOR MIDTOWN NORTH PCT | 6 | CONSTRUCTION TO 50% | 2022-02-21 | 2022-06-20 | 2022-02-21 | 2022-06-20
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAKC | ELEVATOR REHABILITATION FOR MIDTOWN NORTH PCT | 7 | CONSTRUCTION TO 75% | 2022-06-21 | 2022-10-18 | 2022-06-21 | 2022-10-18
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAKC | ELEVATOR REHABILITATION FOR MIDTOWN NORTH PCT | 8 | ORIGINAL EQUIP & FURNISHING | 2022-10-19 | 2023-01-16 | 2022-10-19 | 2023-01-16
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAKC | ELEVATOR REHABILITATION FOR MIDTOWN NORTH PCT | 9 | SUBSTANTIAL COMPLETION | 2023-01-17 | 2023-03-17 | 2023-01-17 | 2023-03-17
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAKC | ELEVATOR REHABILITATION FOR MIDTOWN NORTH PCT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-03-18 | 2023-04-16 | 2023-03-18 | 2023-04-16
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAKP | 1PP STORM DRAIN | 1 | DEVELOP SCOPE | 2020-06-30 | 2020-09-27 | 2020-06-30 | 2020-09-27
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAKP | 1PP STORM DRAIN | 2 | PRELIMINARY DESIGN | 2020-09-28 | 2021-01-25 | 2020-09-28 | 2021-01-25
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAKP | 1PP STORM DRAIN | 3 | FINAL DESIGN | 2021-01-26 | 2021-05-25 | 2021-01-26 | 2021-05-25
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAKP | 1PP STORM DRAIN | 4 | BID AWARD AND REGISTER CONTRCT | 2021-05-26 | 2021-11-21 | 2021-05-26 | 2021-11-21
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAKP | 1PP STORM DRAIN | 5 | CONSTRUCTION TO 25% | 2021-11-22 | 2022-03-21 | 2021-11-22 | 2022-03-21
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAKP | 1PP STORM DRAIN | 6 | CONSTRUCTION TO 50% | 2022-03-22 | 2022-07-19 | 2022-03-22 | 2022-07-19
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAKP | 1PP STORM DRAIN | 7 | CONSTRUCTION TO 75% | 2022-07-20 | 2022-11-16 | 2022-07-20 | 2022-11-16
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAKP | 1PP STORM DRAIN | 8 | ORIGINAL EQUIP & FURNISHING | 2022-11-17 | 2023-02-14 | 2022-11-17 | 2023-02-14
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAKP | 1PP STORM DRAIN | 9 | SUBSTANTIAL COMPLETION | 2023-02-15 | 2023-04-15 | 2023-02-15 | 2023-04-15
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAKP | 1PP STORM DRAIN | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-04-16 | 2023-05-15 | 2023-04-16 | 2023-05-15
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAKX | IAB HVAC REPLACEMENT | 1 | DEVELOP SCOPE | 2020-12-10 | 2021-03-09 | 2020-12-10 | 2021-03-09
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAKX | IAB HVAC REPLACEMENT | 2 | PRELIMINARY DESIGN | 2021-03-10 | 2021-07-07 | 2021-03-10 | 2021-07-07
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAKX | IAB HVAC REPLACEMENT | 3 | FINAL DESIGN | 2021-07-08 | 2021-11-04 | 2021-07-08 | 2021-11-04
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAKX | IAB HVAC REPLACEMENT | 4 | BID AWARD AND REGISTER CONTRCT | 2021-11-05 | 2022-05-03 | 2021-11-05 | 2022-05-03
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAKX | IAB HVAC REPLACEMENT | 5 | CONSTRUCTION TO 25% | 2022-05-04 | 2022-08-31 | 2022-05-04 | 2022-08-31
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAKX | IAB HVAC REPLACEMENT | 6 | CONSTRUCTION TO 50% | 2022-09-01 | 2022-12-29 | 2022-09-01 | 2022-12-29
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAKX | IAB HVAC REPLACEMENT | 7 | CONSTRUCTION TO 75% | 2022-12-30 | 2023-04-28 | 2022-12-30 | 2023-04-28
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAKX | IAB HVAC REPLACEMENT | 8 | ORIGINAL EQUIP & FURNISHING | 2023-04-29 | 2023-07-27 | 2023-04-29 | 2023-07-27
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAKX | IAB HVAC REPLACEMENT | 9 | SUBSTANTIAL COMPLETION | 2023-07-28 | 2023-09-25 | 2023-07-28 | 2023-09-25
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAKX | IAB HVAC REPLACEMENT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-26 | 2023-10-25 | 2023-09-26 | 2023-10-25
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAKY | 1PP SUMP PUMP | 1 | DEVELOP SCOPE | 2020-06-10 | 2020-09-07 | 2020-06-10 | 2020-09-07
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAKY | 1PP SUMP PUMP | 2 | PRELIMINARY DESIGN | 2020-09-08 | 2021-01-05 | 2020-09-08 | 2021-01-05
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAKY | 1PP SUMP PUMP | 3 | FINAL DESIGN | 2021-01-06 | 2021-05-05 | 2021-01-06 | 2021-05-05
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAKY | 1PP SUMP PUMP | 4 | BID AWARD AND REGISTER CONTRCT | 2021-05-06 | 2021-11-01 | 2021-05-06 | 2021-11-01
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAKY | 1PP SUMP PUMP | 5 | CONSTRUCTION TO 25% | 2021-11-02 | 2022-03-01 | 2021-11-02 | 2022-03-01
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAKY | 1PP SUMP PUMP | 6 | CONSTRUCTION TO 50% | 2022-03-02 | 2022-06-29 | 2022-03-02 | 2022-06-29
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAKY | 1PP SUMP PUMP | 7 | CONSTRUCTION TO 75% | 2022-06-30 | 2022-10-27 | 2022-06-30 | 2022-10-27
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAKY | 1PP SUMP PUMP | 8 | ORIGINAL EQUIP & FURNISHING | 2022-10-28 | 2023-01-25 | 2022-10-28 | 2023-01-25
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAKY | 1PP SUMP PUMP | 9 | SUBSTANTIAL COMPLETION | 2023-01-26 | 2023-03-26 | 2023-01-26 | 2023-03-26
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAKY | 1PP SUMP PUMP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-03-27 | 2023-04-25 | 2023-03-27 | 2023-04-25
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79-BMS | BMS PROJECTS | 1 | DESIGN | 2010-07-01 | 2010-12-27 | 2016-09-10 | 2017-03-08
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79-BMS | BMS PROJECTS | 2 | BID AWARD AND REGISTER CONTRCT | 2010-12-28 | 2011-03-27 | 2017-03-09 | 2017-06-06
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79-BMS | BMS PROJECTS | 3 | CONSTRUCTION | 2011-03-28 | 2012-03-26 | 2017-06-07 | 2020-06-06
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79-BMS | BMS PROJECTS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-03-27 | 2012-09-22 | 2020-06-07 | 2020-12-03
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMUPS | ONE POLICE PLAZA UPS | 1 | DESIGN | 2019-08-15 | 2020-02-10 | 2019-08-15 | 2020-02-10
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMUPS | ONE POLICE PLAZA UPS | 2 | BID AWARD AND REGISTER CONTRCT | 2020-02-11 | 2020-05-10 | 2020-02-11 | 2020-05-10
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMUPS | ONE POLICE PLAZA UPS | 3 | CONSTRUCTION | 2020-05-11 | 2021-05-10 | 2020-05-11 | 2021-05-10
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMUPS | ONE POLICE PLAZA UPS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-05-11 | 2021-11-06 | 2021-05-11 | 2021-11-06
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79CAFE | RENOVATION AND UPGRADE OF ONE POLICE PLAZA CAFETERIA | 1 | DESIGN | 2019-06-15 | 2019-12-11 | 2019-06-15 | 2019-12-11
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79CAFE | RENOVATION AND UPGRADE OF ONE POLICE PLAZA CAFETERIA | 2 | BID AWARD AND REGISTER CONTRCT | 2019-12-12 | 2020-03-10 | 2019-12-12 | 2020-03-10
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79CAFE | RENOVATION AND UPGRADE OF ONE POLICE PLAZA CAFETERIA | 3 | CONSTRUCTION | 2020-03-11 | 2021-03-10 | 2020-03-11 | 2021-03-10
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79CAFE | RENOVATION AND UPGRADE OF ONE POLICE PLAZA CAFETERIA | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-11 | 2021-09-06 | 2021-03-11 | 2021-09-06
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79-FMS | FMS PROJECTS | 1 | DEVELOP SCOPE | 2019-06-15 | 2019-09-12 | 2019-06-15 | 2019-09-12
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79-FMS | FMS PROJECTS | 2 | PRELIMINARY DESIGN | 2019-09-13 | 2020-01-10 | 2019-09-13 | 2020-01-10
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79-FMS | FMS PROJECTS | 3 | FINAL DESIGN | 2020-01-11 | 2020-05-09 | 2020-01-11 | 2020-05-09
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79-FMS | FMS PROJECTS | 4 | BID AWARD AND REGISTER CONTRCT | 2020-05-10 | 2020-11-05 | 2020-05-10 | 2020-11-05
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79-FMS | FMS PROJECTS | 5 | CONSTRUCTION TO 25% | 2020-11-06 | 2021-03-05 | 2020-11-06 | 2021-03-05
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79-FMS | FMS PROJECTS | 6 | CONSTRUCTION TO 50% | 2021-03-06 | 2021-07-03 | 2021-03-06 | 2021-07-03
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79-FMS | FMS PROJECTS | 7 | CONSTRUCTION TO 75% | 2021-07-04 | 2022-04-29 | 2021-07-04 | 2022-04-29
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79-FMS | FMS PROJECTS | 8 | ORIGINAL EQUIP & FURNISHING | 2022-04-30 | 2022-07-28 | 2022-04-30 | 2022-07-28
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79-FMS | FMS PROJECTS | 9 | SUBSTANTIAL COMPLETION | 2022-07-29 | 2022-09-26 | 2022-07-29 | 2022-09-26
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79-FMS | FMS PROJECTS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-27 | 2022-10-26 | 2022-09-27 | 2022-10-26
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79PA13 | RENOVATION OF OLD POLICE ACADEMY/13TH PCT | 1 | DEVELOP SCOPE | 2014-06-30 | 2014-09-27 | 2019-06-30 | 2019-09-27
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79PA13 | RENOVATION OF OLD POLICE ACADEMY/13TH PCT | 2 | PRELIMINARY DESIGN | 2014-09-28 | 2015-01-25 | 2019-09-28 | 2020-01-25
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79PA13 | RENOVATION OF OLD POLICE ACADEMY/13TH PCT | 3 | FINAL DESIGN | 2015-01-26 | 2015-07-24 | 2020-01-26 | 2020-07-23
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79PA13 | RENOVATION OF OLD POLICE ACADEMY/13TH PCT | 4 | BID AWARD AND REGISTER CONTRCT | 2015-07-25 | 2015-10-22 | 2020-07-24 | 2020-10-21
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79PA13 | RENOVATION OF OLD POLICE ACADEMY/13TH PCT | 5 | CONSTRUCTION TO 25% | 2015-10-23 | 2016-02-19 | 2020-10-22 | 2021-02-18
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79PA13 | RENOVATION OF OLD POLICE ACADEMY/13TH PCT | 6 | CONSTRUCTION TO 50% | 2016-02-20 | 2016-06-18 | 2021-02-19 | 2021-06-18
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79PA13 | RENOVATION OF OLD POLICE ACADEMY/13TH PCT | 7 | CONSTRUCTION TO 75% | 2016-06-19 | 2016-10-16 | 2021-06-19 | 2021-10-16
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79PA13 | RENOVATION OF OLD POLICE ACADEMY/13TH PCT | 8 | ORIGINAL EQUIP & FURNISHING | 2016-10-17 | 2017-01-14 | 2021-10-17 | 2022-01-14
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79PA13 | RENOVATION OF OLD POLICE ACADEMY/13TH PCT | 9 | SUBSTANTIAL COMPLETION | 2017-01-15 | 2017-03-15 | 2022-01-15 | 2022-03-15
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79PA13 | RENOVATION OF OLD POLICE ACADEMY/13TH PCT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-16 | 2017-04-14 | 2022-03-16 | 2022-04-14
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79PAAUD | OLD POLICE ACADEMY AUDITORIUM RENOVATION | 1 | DEVELOP SCOPE | 2016-06-10 | 2016-09-07 | 2016-06-10 | 2016-09-07
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79PAAUD | OLD POLICE ACADEMY AUDITORIUM RENOVATION | 2 | PRELIMINARY DESIGN | 2016-09-08 | 2017-01-05 | 2016-09-08 | 2017-01-05
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79PAAUD | OLD POLICE ACADEMY AUDITORIUM RENOVATION | 3 | FINAL DESIGN | 2017-01-06 | 2017-05-05 | 2017-01-06 | 2017-05-05
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79PAAUD | OLD POLICE ACADEMY AUDITORIUM RENOVATION | 4 | BID AWARD AND REGISTER CONTRCT | 2017-05-06 | 2017-11-01 | 2017-05-06 | 2017-11-01
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79PAAUD | OLD POLICE ACADEMY AUDITORIUM RENOVATION | 5 | CONSTRUCTION TO 25% | 2017-11-02 | 2018-03-01 | 2017-11-02 | 2018-03-01
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79PAAUD | OLD POLICE ACADEMY AUDITORIUM RENOVATION | 6 | CONSTRUCTION TO 50% | 2018-03-02 | 2018-06-29 | 2018-03-02 | 2018-06-29
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79PAAUD | OLD POLICE ACADEMY AUDITORIUM RENOVATION | 7 | CONSTRUCTION TO 75% | 2018-06-30 | 2018-10-27 | 2018-06-30 | 2021-10-27
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79PAAUD | OLD POLICE ACADEMY AUDITORIUM RENOVATION | 8 | ORIGINAL EQUIP & FURNISHING | 2018-10-28 | 2019-01-25 | 2021-10-28 | 2022-01-25
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79PAAUD | OLD POLICE ACADEMY AUDITORIUM RENOVATION | 9 | SUBSTANTIAL COMPLETION | 2019-01-26 | 2019-03-26 | 2022-01-26 | 2022-03-26
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79PAAUD | OLD POLICE ACADEMY AUDITORIUM RENOVATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-03-27 | 2019-04-25 | 2022-03-27 | 2022-04-25
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79PCEL | REHABILITATION OF PC ELEVATOR AT 1PP | 1 | DESIGN | 2019-06-30 | 2019-12-26 | 2019-06-30 | 2019-12-26
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79PCEL | REHABILITATION OF PC ELEVATOR AT 1PP | 2 | BID AWARD AND REGISTER CONTRCT | 2019-12-27 | 2020-03-25 | 2019-12-27 | 2020-03-25
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79PCEL | REHABILITATION OF PC ELEVATOR AT 1PP | 3 | CONSTRUCTION | 2020-03-26 | 2021-03-25 | 2020-03-26 | 2021-03-25
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79PCEL | REHABILITATION OF PC ELEVATOR AT 1PP | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-26 | 2021-09-21 | 2021-03-26 | 2021-09-21
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79SCIF | UPGRADE OF SCIF AC UNIT AT ONE POLICE PLAZA | 1 | DESIGN | 2019-08-15 | 2020-02-10 | 2019-08-15 | 2020-02-10
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79SCIF | UPGRADE OF SCIF AC UNIT AT ONE POLICE PLAZA | 2 | BID AWARD AND REGISTER CONTRCT | 2020-02-11 | 2020-05-10 | 2020-02-11 | 2020-05-10
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79SCIF | UPGRADE OF SCIF AC UNIT AT ONE POLICE PLAZA | 3 | CONSTRUCTION | 2020-05-11 | 2021-05-10 | 2020-05-11 | 2021-05-10
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79SCIF | UPGRADE OF SCIF AC UNIT AT ONE POLICE PLAZA | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-05-11 | 2021-11-06 | 2021-05-11 | 2021-11-06
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | SANDCD6 | HARBOR LAUNCH RANDALL'S ISLAND ELECTRICAL | 1 | DEVELOP SCOPE | 2016-09-10 | 2016-12-08 | 2016-06-10 | 2016-09-07
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | SANDCD6 | HARBOR LAUNCH RANDALL'S ISLAND ELECTRICAL | 2 | PRELIMINARY DESIGN | 2016-12-09 | 2017-04-07 | 2016-09-08 | 2017-01-05
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | SANDCD6 | HARBOR LAUNCH RANDALL'S ISLAND ELECTRICAL | 3 | FINAL DESIGN | 2017-04-08 | 2017-08-05 | 2017-01-06 | 2017-05-05
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | SANDCD6 | HARBOR LAUNCH RANDALL'S ISLAND ELECTRICAL | 4 | BID AWARD AND REGISTER CONTRCT | 2017-08-06 | 2018-02-01 | 2017-05-06 | 2017-11-01
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | SANDCD6 | HARBOR LAUNCH RANDALL'S ISLAND ELECTRICAL | 5 | CONSTRUCTION TO 25% | 2018-02-02 | 2018-06-01 | 2017-11-02 | 2018-03-01
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | SANDCD6 | HARBOR LAUNCH RANDALL'S ISLAND ELECTRICAL | 6 | CONSTRUCTION TO 50% | 2018-06-02 | 2018-09-29 | 2018-03-02 | 2018-06-29
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | SANDCD6 | HARBOR LAUNCH RANDALL'S ISLAND ELECTRICAL | 7 | CONSTRUCTION TO 75% | 2018-09-30 | 2019-01-27 | 2018-06-30 | 2021-10-27
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | SANDCD6 | HARBOR LAUNCH RANDALL'S ISLAND ELECTRICAL | 8 | ORIGINAL EQUIP & FURNISHING | 2019-01-28 | 2019-04-27 | 2021-10-28 | 2022-01-25
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | SANDCD6 | HARBOR LAUNCH RANDALL'S ISLAND ELECTRICAL | 9 | SUBSTANTIAL COMPLETION | 2019-04-28 | 2019-06-26 | 2022-01-26 | 2022-03-26
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | SANDCD6 | HARBOR LAUNCH RANDALL'S ISLAND ELECTRICAL | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-06-27 | 2019-07-26 | 2022-03-27 | 2022-04-25
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | SANDCD7 | POLICE SERVICE AREA 4 (PSA4) | 1 | DEVELOP SCOPE | 2016-09-10 | 2016-12-08 | 2016-06-10 | 2016-09-07
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | SANDCD7 | POLICE SERVICE AREA 4 (PSA4) | 2 | PRELIMINARY DESIGN | 2016-12-09 | 2017-04-07 | 2016-09-08 | 2017-01-05
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | SANDCD7 | POLICE SERVICE AREA 4 (PSA4) | 3 | FINAL DESIGN | 2017-04-08 | 2017-08-05 | 2017-01-06 | 2017-05-05
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | SANDCD7 | POLICE SERVICE AREA 4 (PSA4) | 4 | BID AWARD AND REGISTER CONTRCT | 2017-08-06 | 2018-02-01 | 2017-05-06 | 2017-11-01
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | SANDCD7 | POLICE SERVICE AREA 4 (PSA4) | 5 | CONSTRUCTION TO 25% | 2018-02-02 | 2018-06-01 | 2017-11-02 | 2018-03-01
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | SANDCD7 | POLICE SERVICE AREA 4 (PSA4) | 6 | CONSTRUCTION TO 50% | 2018-06-02 | 2018-09-29 | 2018-03-02 | 2018-06-29
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | SANDCD7 | POLICE SERVICE AREA 4 (PSA4) | 7 | CONSTRUCTION TO 75% | 2018-09-30 | 2019-01-27 | 2018-06-30 | 2021-10-27
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | SANDCD7 | POLICE SERVICE AREA 4 (PSA4) | 8 | ORIGINAL EQUIP & FURNISHING | 2019-01-28 | 2019-04-27 | 2021-10-28 | 2022-01-25
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | SANDCD7 | POLICE SERVICE AREA 4 (PSA4) | 9 | SUBSTANTIAL COMPLETION | 2019-04-28 | 2019-06-26 | 2022-01-26 | 2022-03-26
20201123 | MANHATTAN | 056 | POLICE DEPARTMENT | SANDCD7 | POLICE SERVICE AREA 4 (PSA4) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-06-27 | 2019-07-26 | 2022-03-27 | 2022-04-25
20201123 | MANHATTAN | 057 | FIRE DEPARTMENT | ACEFDN803 | FDNY - Solar photo-voltaic system at SOC | 1 | DEVELOP SCOPE | 2018-09-05 | 2018-12-03 | 2018-09-05 | 2018-12-03
20201123 | MANHATTAN | 057 | FIRE DEPARTMENT | ACEFDN803 | FDNY - Solar photo-voltaic system at SOC | 2 | PRELIMINARY DESIGN | 2018-12-04 | 2019-04-02 | 2018-12-04 | 2019-04-02
20201123 | MANHATTAN | 057 | FIRE DEPARTMENT | ACEFDN803 | FDNY - Solar photo-voltaic system at SOC | 3 | FINAL DESIGN | 2019-04-03 | 2019-09-29 | 2019-04-03 | 2019-09-29
20201123 | MANHATTAN | 057 | FIRE DEPARTMENT | ACEFDN803 | FDNY - Solar photo-voltaic system at SOC | 4 | BID AWARD AND REGISTER CONTRCT | 2019-09-30 | 2019-12-28 | 2019-09-30 | 2019-12-28
20201123 | MANHATTAN | 057 | FIRE DEPARTMENT | ACEFDN803 | FDNY - Solar photo-voltaic system at SOC | 5 | CONSTRUCTION TO 25% | 2019-12-29 | 2020-04-26 | 2019-12-29 | 2020-04-26
20201123 | MANHATTAN | 057 | FIRE DEPARTMENT | ACEFDN803 | FDNY - Solar photo-voltaic system at SOC | 6 | CONSTRUCTION TO 50% | 2020-04-27 | 2020-08-24 | 2020-04-27 | 2020-08-24
20201123 | MANHATTAN | 057 | FIRE DEPARTMENT | ACEFDN803 | FDNY - Solar photo-voltaic system at SOC | 7 | CONSTRUCTION TO 75% | 2020-08-25 | 2020-12-22 | 2020-08-25 | 2020-12-22
20201123 | MANHATTAN | 057 | FIRE DEPARTMENT | ACEFDN803 | FDNY - Solar photo-voltaic system at SOC | 8 | ORIGINAL EQUIP & FURNISHING | 2020-12-23 | 2021-03-22 | 2020-12-23 | 2021-03-22
20201123 | MANHATTAN | 057 | FIRE DEPARTMENT | ACEFDN803 | FDNY - Solar photo-voltaic system at SOC | 9 | SUBSTANTIAL COMPLETION | 2021-03-23 | 2021-05-21 | 2021-03-23 | 2021-05-21
20201123 | MANHATTAN | 057 | FIRE DEPARTMENT | ACEFDN803 | FDNY - Solar photo-voltaic system at SOC | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-05-22 | 2021-06-20 | 2021-05-22 | 2021-06-20
20201123 | MANHATTAN | 057 | FIRE DEPARTMENT | ACEFDN901 | FDNY- Solar PV at FDNY Academy Building 12 | 1 | DEVELOP SCOPE | 2019-12-30 | 2020-03-28 | 2019-12-30 | 2020-03-28
20201123 | MANHATTAN | 057 | FIRE DEPARTMENT | ACEFDN901 | FDNY- Solar PV at FDNY Academy Building 12 | 2 | PRELIMINARY DESIGN | 2020-03-29 | 2020-07-26 | 2020-03-29 | 2020-07-26
20201123 | MANHATTAN | 057 | FIRE DEPARTMENT | ACEFDN901 | FDNY- Solar PV at FDNY Academy Building 12 | 3 | FINAL DESIGN | 2020-07-27 | 2021-01-22 | 2020-07-27 | 2021-01-22
20201123 | MANHATTAN | 057 | FIRE DEPARTMENT | ACEFDN901 | FDNY- Solar PV at FDNY Academy Building 12 | 4 | BID AWARD AND REGISTER CONTRCT | 2021-01-23 | 2021-04-22 | 2021-01-23 | 2021-04-22
20201123 | MANHATTAN | 057 | FIRE DEPARTMENT | ACEFDN901 | FDNY- Solar PV at FDNY Academy Building 12 | 5 | CONSTRUCTION TO 25% | 2021-04-23 | 2021-08-20 | 2021-04-23 | 2021-08-20
20201123 | MANHATTAN | 057 | FIRE DEPARTMENT | ACEFDN901 | FDNY- Solar PV at FDNY Academy Building 12 | 6 | CONSTRUCTION TO 50% | 2021-08-21 | 2021-12-18 | 2021-08-21 | 2021-12-18
20201123 | MANHATTAN | 057 | FIRE DEPARTMENT | ACEFDN901 | FDNY- Solar PV at FDNY Academy Building 12 | 7 | CONSTRUCTION TO 75% | 2021-12-19 | 2022-04-17 | 2021-12-19 | 2022-04-17
20201123 | MANHATTAN | 057 | FIRE DEPARTMENT | ACEFDN901 | FDNY- Solar PV at FDNY Academy Building 12 | 8 | ORIGINAL EQUIP & FURNISHING | 2022-04-18 | 2022-07-16 | 2022-04-18 | 2022-07-16
20201123 | MANHATTAN | 057 | FIRE DEPARTMENT | ACEFDN901 | FDNY- Solar PV at FDNY Academy Building 12 | 9 | SUBSTANTIAL COMPLETION | 2022-07-17 | 2022-09-14 | 2022-07-17 | 2022-09-14
20201123 | MANHATTAN | 057 | FIRE DEPARTMENT | ACEFDN901 | FDNY- Solar PV at FDNY Academy Building 12 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-15 | 2022-10-14 | 2022-09-15 | 2022-10-14
20201123 | MANHATTAN | 057 | FIRE DEPARTMENT | F175KTE22 | KITCHENT RENOVATION - EC22 | 1 | DESIGN | 2018-11-01 | 2019-04-29 | 2019-11-01 | 2020-04-28
20201123 | MANHATTAN | 057 | FIRE DEPARTMENT | F175KTE22 | KITCHENT RENOVATION - EC22 | 2 | CONSTRUCTION | 2019-04-30 | 2020-04-28 | 2020-04-29 | 2021-04-28
20201123 | MANHATTAN | 057 | FIRE DEPARTMENT | F175KTE22 | KITCHENT RENOVATION - EC22 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-04-29 | 2020-07-27 | 2021-04-29 | 2021-07-27
20201123 | MANHATTAN | 057 | FIRE DEPARTMENT | F175MCE33 | Multi-Component Renovations - EC33 | 1 | DESIGN | 2013-08-15 | 2014-02-10 | 2018-09-26 | 2018-12-24
20201123 | MANHATTAN | 057 | FIRE DEPARTMENT | F175MCE33 | Multi-Component Renovations - EC33 | 2 | CONSTRUCTION | 2014-02-11 | 2015-02-10 | 2018-12-25 | 2019-09-20
20201123 | MANHATTAN | 057 | FIRE DEPARTMENT | F175MCE33 | Multi-Component Renovations - EC33 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-02-11 | 2015-05-11 | 2019-09-21 | 2020-10-24
20201123 | MANHATTAN | 057 | FIRE DEPARTMENT | F175MCE33 | Multi-Component Renovations - EC33 | 4 | ORIGINAL EQUIP & FURNISHING | 2015-02-11 | 2015-05-11 | 2020-10-25 | 2020-12-08
20201123 | MANHATTAN | 057 | FIRE DEPARTMENT | F175MCE33 | Multi-Component Renovations - EC33 | 5 | SUBSTANTIAL COMPLETION | 2015-02-11 | 2015-05-11 | 2020-12-09 | 2021-01-17
20201123 | MANHATTAN | 057 | FIRE DEPARTMENT | F175MCE33 | Multi-Component Renovations - EC33 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-02-11 | 2015-05-11 | 2021-01-18 | 2023-11-18
20201123 | MANHATTAN | 057 | FIRE DEPARTMENT | F175MCE74 | Multi-Component Renovations - EC74 | 1 | DESIGN | 2018-11-01 | 2019-01-29 | 2020-04-02 | 2020-06-30
20201123 | MANHATTAN | 057 | FIRE DEPARTMENT | F175MCE74 | Multi-Component Renovations - EC74 | 2 | BID AWARD AND REGISTER CONTRCT | 2019-01-30 | 2019-10-26 | 2020-07-01 | 2021-03-27
20201123 | MANHATTAN | 057 | FIRE DEPARTMENT | F175MCE74 | Multi-Component Renovations - EC74 | 3 | CONSTRUCTION | 2019-10-27 | 2020-11-29 | 2021-03-28 | 2022-05-01
20201123 | MANHATTAN | 057 | FIRE DEPARTMENT | F175MCE74 | Multi-Component Renovations - EC74 | 4 | ORIGINAL EQUIP & FURNISHING | 2020-11-30 | 2021-01-13 | 2022-05-02 | 2022-06-15
20201123 | MANHATTAN | 057 | FIRE DEPARTMENT | F175MCE74 | Multi-Component Renovations - EC74 | 5 | SUBSTANTIAL COMPLETION | 2021-01-14 | 2021-02-22 | 2022-06-16 | 2022-07-25
20201123 | MANHATTAN | 057 | FIRE DEPARTMENT | F175MCE74 | Multi-Component Renovations - EC74 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-02-23 | 2021-04-23 | 2022-07-26 | 2022-09-23
20201123 | MANHATTAN | 057 | FIRE DEPARTMENT | F175MCE91 | Multi-Component Renovations - EC91 | 1 | DESIGN | 2018-11-01 | 2019-01-29 | 2018-11-01 | 2019-01-29
20201123 | MANHATTAN | 057 | FIRE DEPARTMENT | F175MCE91 | Multi-Component Renovations - EC91 | 2 | BID AWARD AND REGISTER CONTRCT | 2019-01-30 | 2019-10-26 | 2019-01-30 | 2019-10-26
20201123 | MANHATTAN | 057 | FIRE DEPARTMENT | F175MCE91 | Multi-Component Renovations - EC91 | 3 | CONSTRUCTION | 2019-10-27 | 2020-11-29 | 2019-10-27 | 2020-11-29
20201123 | MANHATTAN | 057 | FIRE DEPARTMENT | F175MCE91 | Multi-Component Renovations - EC91 | 4 | ORIGINAL EQUIP & FURNISHING | 2020-11-30 | 2021-01-13 | 2020-11-30 | 2021-01-13
20201123 | MANHATTAN | 057 | FIRE DEPARTMENT | F175MCE91 | Multi-Component Renovations - EC91 | 5 | SUBSTANTIAL COMPLETION | 2021-01-14 | 2021-02-22 | 2021-01-14 | 2021-02-22
20201123 | MANHATTAN | 057 | FIRE DEPARTMENT | F175MCE91 | Multi-Component Renovations - EC91 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-02-23 | 2021-04-23 | 2021-02-23 | 2023-12-23
20201123 | MANHATTAN | 057 | FIRE DEPARTMENT | F175MCL20 | FIREHOUSE RENOVATIONS - LC20 | 1 | DESIGN | 2012-12-18 | 2013-06-15 | 2018-09-26 | 2018-12-24
20201123 | MANHATTAN | 057 | FIRE DEPARTMENT | F175MCL20 | FIREHOUSE RENOVATIONS - LC20 | 2 | CONSTRUCTION | 2013-06-16 | 2014-06-15 | 2018-12-25 | 2019-09-20
20201123 | MANHATTAN | 057 | FIRE DEPARTMENT | F175MCL20 | FIREHOUSE RENOVATIONS - LC20 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-06-16 | 2014-09-13 | 2019-09-21 | 2020-10-24
20201123 | MANHATTAN | 057 | FIRE DEPARTMENT | F175MCL20 | FIREHOUSE RENOVATIONS - LC20 | 4 | ORIGINAL EQUIP & FURNISHING | 2014-06-16 | 2014-09-13 | 2020-10-25 | 2020-12-08
20201123 | MANHATTAN | 057 | FIRE DEPARTMENT | F175MCL20 | FIREHOUSE RENOVATIONS - LC20 | 5 | SUBSTANTIAL COMPLETION | 2014-06-16 | 2014-09-13 | 2020-12-09 | 2021-01-17
20201123 | MANHATTAN | 057 | FIRE DEPARTMENT | F175MCL20 | FIREHOUSE RENOVATIONS - LC20 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-06-16 | 2014-09-13 | 2021-01-18 | 2024-01-18
20201123 | MANHATTAN | 057 | FIRE DEPARTMENT | F175RFE54 | ROOF AND WATERPROOFING - EC54 | 1 | DESIGN | 2018-11-01 | 2019-04-29 | 2018-11-01 | 2019-04-29
20201123 | MANHATTAN | 057 | FIRE DEPARTMENT | F175RFE54 | ROOF AND WATERPROOFING - EC54 | 2 | CONSTRUCTION | 2019-04-30 | 2020-04-28 | 2019-04-30 | 2020-04-28
20201123 | MANHATTAN | 057 | FIRE DEPARTMENT | F175RFE54 | ROOF AND WATERPROOFING - EC54 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-04-29 | 2020-07-27 | 2020-04-29 | 2020-07-27
20201123 | MANHATTAN | 057 | FIRE DEPARTMENT | FD175DE15 | DOOR REPLACEMENT - EC15 | 1 | CONSTRUCTION | 2018-07-17 | 2019-07-16 | 2018-07-17 | 2019-07-16
20201123 | MANHATTAN | 057 | FIRE DEPARTMENT | FD175DE15 | DOOR REPLACEMENT - EC15 | 2 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-07-17 | 2019-10-14 | 2019-07-17 | 2019-10-14
20201123 | MANHATTAN | 057 | FIRE DEPARTMENT | FD175DE22 | Door Replacement - EC22 | 2 | CONSTRUCTION | 2019-03-14 | 2020-03-12 | 2020-09-30 | 2021-09-29
20201123 | MANHATTAN | 057 | FIRE DEPARTMENT | FD175DE22 | Door Replacement - EC22 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-03-13 | 2020-06-10 | 2021-09-30 | 2021-12-28
20201123 | MANHATTAN | 057 | FIRE DEPARTMENT | FD175DE95 | Door Replacement - EC95 | 1 | DESIGN | 2018-09-15 | 2019-03-13 | 2020-04-04 | 2020-09-30
20201123 | MANHATTAN | 057 | FIRE DEPARTMENT | FD175DE95 | Door Replacement - EC95 | 2 | CONSTRUCTION | 2019-03-14 | 2020-03-12 | 2020-10-01 | 2021-09-30
20201123 | MANHATTAN | 057 | FIRE DEPARTMENT | FD175DE95 | Door Replacement - EC95 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-03-13 | 2020-06-10 | 2021-10-01 | 2021-12-29
20201123 | MANHATTAN | 057 | FIRE DEPARTMENT | FD175DRE5 | Door Replacement - EC5 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-03-13 | 2020-06-10 | 2021-10-01 | 2021-12-29
20201123 | MANHATTAN | 057 | FIRE DEPARTMENT | FD175GE95 | Generator - EC95 | 1 | DESIGN | 2019-01-15 | 2019-07-13 | 2020-01-15 | 2020-07-12
20201123 | MANHATTAN | 057 | FIRE DEPARTMENT | FD175GE95 | Generator - EC95 | 2 | CONSTRUCTION | 2019-07-14 | 2020-07-12 | 2020-07-13 | 2021-07-12
20201123 | MANHATTAN | 057 | FIRE DEPARTMENT | FD175GE95 | Generator - EC95 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-07-13 | 2020-10-10 | 2021-07-13 | 2021-10-10
20201123 | MANHATTAN | 057 | FIRE DEPARTMENT | FD175WN22 | Windown Replacement - EC22 | 1 | DESIGN | 2019-01-15 | 2019-07-13 | 2020-01-15 | 2020-07-12
20201123 | MANHATTAN | 057 | FIRE DEPARTMENT | FD175WN22 | Windown Replacement - EC22 | 2 | CONSTRUCTION | 2019-07-14 | 2020-07-12 | 2020-07-13 | 2021-07-12
20201123 | MANHATTAN | 057 | FIRE DEPARTMENT | FD175WN22 | Windown Replacement - EC22 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-07-13 | 2020-10-10 | 2021-07-13 | 2021-10-10
20201123 | MANHATTAN | 057 | FIRE DEPARTMENT | FD175WN28 | Window Replacement - EC28 | 1 | DESIGN | 2019-01-15 | 2019-07-13 | 2019-01-15 | 2019-07-13
20201123 | MANHATTAN | 057 | FIRE DEPARTMENT | FD175WN28 | Window Replacement - EC28 | 2 | CONSTRUCTION | 2019-07-14 | 2020-07-12 | 2019-07-14 | 2020-07-12
20201123 | MANHATTAN | 057 | FIRE DEPARTMENT | FD175WN28 | Window Replacement - EC28 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-07-13 | 2020-10-10 | 2020-07-13 | 2020-10-10
20201123 | MANHATTAN | 057 | FIRE DEPARTMENT | FD175WN74 | Window Replacement - EC74 | 1 | DESIGN | 2018-11-01 | 2019-04-29 | 2018-11-01 | 2019-04-29
20201123 | MANHATTAN | 057 | FIRE DEPARTMENT | FD175WN74 | Window Replacement - EC74 | 2 | CONSTRUCTION | 2019-04-30 | 2020-04-28 | 2019-04-30 | 2020-04-28
20201123 | MANHATTAN | 057 | FIRE DEPARTMENT | FD175WN74 | Window Replacement - EC74 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-04-29 | 2020-07-27 | 2020-04-29 | 2020-07-27
20201123 | MANHATTAN | 057 | FIRE DEPARTMENT | FM175WN76 | Window Replacement EC76 | 2 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-04-01 | 2019-06-29 | 2022-10-01 | 2022-12-29
20201123 | MANHATTAN | 068 | ADMIN FOR CHILDREN'S SERVICES | CAPC | CHINESE AMERICAN PLANNING COUNCIL | 1 | DESIGN | 2011-05-30 | 2011-11-25 | 2018-07-06 | 2020-01-01
20201123 | MANHATTAN | 068 | ADMIN FOR CHILDREN'S SERVICES | CAPC | CHINESE AMERICAN PLANNING COUNCIL | 2 | CONSTRUCTION | 2011-11-26 | 2012-05-23 | 2020-01-02 | 2020-06-29
20201123 | MANHATTAN | 068 | ADMIN FOR CHILDREN'S SERVICES | JSA61BWYY | JSA RELOCATION TO 61 BROADWAY | 1 | DEVELOP SCOPE | 2019-12-01 | 2020-06-30 | 2019-12-01 | 2020-06-30
20201123 | MANHATTAN | 068 | ADMIN FOR CHILDREN'S SERVICES | JSA61BWYY | JSA RELOCATION TO 61 BROADWAY | 2 | BID AWARD AND REGISTER CONTRCT | 2020-07-01 | 2020-09-28 | 2020-07-01 | 2020-09-28
20201123 | MANHATTAN | 068 | ADMIN FOR CHILDREN'S SERVICES | JSA61BWYY | JSA RELOCATION TO 61 BROADWAY | 3 | CONSTRUCTION TO 50% | 2020-09-29 | 2021-01-26 | 2020-09-29 | 2021-01-26
20201123 | MANHATTAN | 068 | ADMIN FOR CHILDREN'S SERVICES | JSA61BWYY | JSA RELOCATION TO 61 BROADWAY | 4 | CONSTRUCTION TO 75% | 2021-01-27 | 2021-03-27 | 2021-01-27 | 2021-03-27
20201123 | MANHATTAN | 068 | ADMIN FOR CHILDREN'S SERVICES | JSA61BWYY | JSA RELOCATION TO 61 BROADWAY | 5 | SUBSTANTIAL COMPLETION | 2021-03-28 | 2021-05-26 | 2021-03-28 | 2021-05-26
20201123 | MANHATTAN | 068 | ADMIN FOR CHILDREN'S SERVICES | JSA61BWYY | JSA RELOCATION TO 61 BROADWAY | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-05-27 | 2021-06-25 | 2021-05-27 | 2021-06-25
20201123 | MANHATTAN | 068 | ADMIN FOR CHILDREN'S SERVICES | NSCC | Children's Center High Needs Unit | 1 | DESIGN | 2014-10-01 | 2015-03-29 | 2020-07-01 | 2022-06-30
20201123 | MANHATTAN | 068 | ADMIN FOR CHILDREN'S SERVICES | NSCC | Children's Center High Needs Unit | 2 | CONSTRUCTION | 2015-03-30 | 2016-03-28 | 2022-07-01 | 2023-07-02
20201123 | MANHATTAN | 068 | ADMIN FOR CHILDREN'S SERVICES | NSCC | Children's Center High Needs Unit | 3 | DEVELOP SCOPE | 2015-03-30 | 2016-03-28 | 2023-07-03 | 2023-09-30
20201123 | MANHATTAN | 068 | ADMIN FOR CHILDREN'S SERVICES | NSCC | Children's Center High Needs Unit | 4 | BID AWARD AND REGISTER CONTRCT | 2015-03-30 | 2016-03-28 | 2023-10-01 | 2023-12-29
20201123 | MANHATTAN | 068 | ADMIN FOR CHILDREN'S SERVICES | NSCC | Children's Center High Needs Unit | 5 | CONSTRUCTION TO 50% | 2015-03-30 | 2016-03-28 | 2023-12-30 | 2024-04-27
20201123 | MANHATTAN | 068 | ADMIN FOR CHILDREN'S SERVICES | NSCC | Children's Center High Needs Unit | 6 | CONSTRUCTION TO 75% | 2015-03-30 | 2016-03-28 | 2024-04-28 | 2024-06-26
20201123 | MANHATTAN | 068 | ADMIN FOR CHILDREN'S SERVICES | NSCC | Children's Center High Needs Unit | 7 | SUBSTANTIAL COMPLETION | 2015-03-30 | 2016-03-28 | 2024-06-27 | 2024-08-25
20201123 | MANHATTAN | 068 | ADMIN FOR CHILDREN'S SERVICES | NSCC | Children's Center High Needs Unit | 8 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-30 | 2016-03-28 | 2024-08-26 | 2024-09-24
20201123 | MANHATTAN | 068 | ADMIN FOR CHILDREN'S SERVICES | SYSUPGRAD | SYSTEM UPGRADES AT HORIZON AND CROSSROADS JUVENILE CENTERS | 1 | DEVELOP SCOPE | 2024-08-28 | 2024-11-25 | 2024-08-28 | 2025-11-25
20201123 | MANHATTAN | 068 | ADMIN FOR CHILDREN'S SERVICES | SYSUPGRAD | SYSTEM UPGRADES AT HORIZON AND CROSSROADS JUVENILE CENTERS | 2 | BID AWARD AND REGISTER CONTRCT | 2024-11-26 | 2025-02-23 | 2025-11-26 | 2026-11-25
20201123 | MANHATTAN | 068 | ADMIN FOR CHILDREN'S SERVICES | SYSUPGRAD | SYSTEM UPGRADES AT HORIZON AND CROSSROADS JUVENILE CENTERS | 3 | CONSTRUCTION TO 50% | 2025-02-24 | 2025-06-23 | 2026-11-26 | 2027-06-30
20201123 | MANHATTAN | 068 | ADMIN FOR CHILDREN'S SERVICES | SYSUPGRAD | SYSTEM UPGRADES AT HORIZON AND CROSSROADS JUVENILE CENTERS | 4 | CONSTRUCTION TO 75% | 2025-06-24 | 2025-08-22 | 2027-07-01 | 2027-12-31
20201123 | MANHATTAN | 068 | ADMIN FOR CHILDREN'S SERVICES | SYSUPGRAD | SYSTEM UPGRADES AT HORIZON AND CROSSROADS JUVENILE CENTERS | 5 | SUBSTANTIAL COMPLETION | 2025-08-23 | 2025-10-21 | 2028-01-01 | 2028-12-31
20201123 | MANHATTAN | 068 | ADMIN FOR CHILDREN'S SERVICES | SYSUPGRAD | SYSTEM UPGRADES AT HORIZON AND CROSSROADS JUVENILE CENTERS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-10-22 | 2025-11-20 | 2029-01-01 | 2029-06-30
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | DHS-LIGHT | DEPT OF HOMELESS SVCS: INSTALL LIGHTING AT 30TH STR SHELTER | 1 | DESIGN | 2019-08-01 | 2020-04-26 | 2019-08-01 | 2020-04-26
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | DHS-LIGHT | DEPT OF HOMELESS SVCS: INSTALL LIGHTING AT 30TH STR SHELTER | 2 | BID AWARD AND REGISTER CONTRCT | 2020-04-27 | 2020-10-23 | 2020-04-27 | 2020-10-23
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | DHS-LIGHT | DEPT OF HOMELESS SVCS: INSTALL LIGHTING AT 30TH STR SHELTER | 3 | CONSTRUCTION | 2020-10-24 | 2025-07-29 | 2020-10-24 | 2025-07-29
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112BLSB | BELLEVUE BASEMENT STRUCTURAL RECONSTRUCTION | 1 | DESIGN | 2019-08-01 | 2020-04-26 | 2019-08-01 | 2020-04-26
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112BLSB | BELLEVUE BASEMENT STRUCTURAL RECONSTRUCTION | 2 | BID AWARD AND REGISTER CONTRCT | 2020-04-27 | 2020-10-23 | 2020-04-27 | 2020-10-23
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112BLSB | BELLEVUE BASEMENT STRUCTURAL RECONSTRUCTION | 3 | CONSTRUCTION | 2020-10-24 | 2025-07-29 | 2020-10-24 | 2025-07-29
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112BLWB | BELLEVUE WEST BANK ELEVATORS | 1 | DESIGN | 2023-05-30 | 2024-02-23 | 2023-05-30 | 2024-02-23
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112BLWB | BELLEVUE WEST BANK ELEVATORS | 2 | BID AWARD AND REGISTER CONTRCT | 2024-02-24 | 2024-08-21 | 2024-02-24 | 2024-08-21
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112BLWB | BELLEVUE WEST BANK ELEVATORS | 3 | CONSTRUCTION | 2024-08-22 | 2029-05-27 | 2024-08-22 | 2029-05-27
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112ETEU | 282 East 3rd Street, 10009 - Exterior Upgrade | 1 | DESIGN | 2021-01-01 | 2021-09-27 | 2021-01-01 | 2021-09-27
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112ETEU | 282 East 3rd Street, 10009 - Exterior Upgrade | 2 | BID AWARD AND REGISTER CONTRCT | 2021-09-28 | 2022-03-26 | 2021-09-28 | 2022-03-26
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112ETEU | 282 East 3rd Street, 10009 - Exterior Upgrade | 3 | CONSTRUCTION | 2022-03-27 | 2026-12-30 | 2022-03-27 | 2026-12-30
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112FWBO | FT. WASHINGTON ARMORY - BOILER UPGRADE | 1 | DESIGN | 2016-02-11 | 2016-11-06 | 2016-02-11 | 2016-11-06
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112FWBO | FT. WASHINGTON ARMORY - BOILER UPGRADE | 2 | BID AWARD AND REGISTER CONTRCT | 2016-11-07 | 2017-05-05 | 2016-11-07 | 2017-05-05
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112FWBO | FT. WASHINGTON ARMORY - BOILER UPGRADE | 3 | CONSTRUCTION | 2017-05-06 | 2022-02-08 | 2017-05-06 | 2022-02-08
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112FWFR | FORT WASHINGTON ARMORY-DORMITORIES FLOOR REPLACEMENT | 1 | DESIGN | 2016-01-04 | 2016-09-29 | 2019-08-01 | 2020-04-26
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112FWFR | FORT WASHINGTON ARMORY-DORMITORIES FLOOR REPLACEMENT | 2 | BID AWARD AND REGISTER CONTRCT | 2016-09-30 | 2017-03-28 | 2020-04-27 | 2020-10-23
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112FWFR | FORT WASHINGTON ARMORY-DORMITORIES FLOOR REPLACEMENT | 3 | CONSTRUCTION | 2017-03-29 | 2021-01-01 | 2020-10-24 | 2024-07-29
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112GDFC | GEORGE DALY FACADE AND WINDOWS | 1 | DESIGN | 2025-05-30 | 2026-02-23 | 2025-05-30 | 2026-02-23
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112GDFC | GEORGE DALY FACADE AND WINDOWS | 2 | BID AWARD AND REGISTER CONTRCT | 2026-02-24 | 2026-08-22 | 2026-02-24 | 2026-08-22
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112GDFC | GEORGE DALY FACADE AND WINDOWS | 3 | CONSTRUCTION | 2026-08-23 | 2031-05-28 | 2026-08-23 | 2031-05-28
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112HBAT | HARLEM 1 BATHROOM RECONSTRUCTION | 1 | DESIGN | 2019-01-01 | 2019-09-27 | 2019-01-01 | 2019-09-27
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112HBAT | HARLEM 1 BATHROOM RECONSTRUCTION | 2 | BID AWARD AND REGISTER CONTRCT | 2019-09-28 | 2020-03-25 | 2019-09-28 | 2020-03-25
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112HBAT | HARLEM 1 BATHROOM RECONSTRUCTION | 3 | CONSTRUCTION | 2020-03-26 | 2024-12-29 | 2020-03-26 | 2024-12-29
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112HHAC | HARLEM 1 ROOF AND VENTILATION SYSTEM | 1 | DESIGN | 2020-01-01 | 2020-09-26 | 2020-01-01 | 2020-09-26
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112HHAC | HARLEM 1 ROOF AND VENTILATION SYSTEM | 2 | BID AWARD AND REGISTER CONTRCT | 2020-09-27 | 2021-03-25 | 2020-09-27 | 2021-03-25
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112HHAC | HARLEM 1 ROOF AND VENTILATION SYSTEM | 3 | CONSTRUCTION | 2021-03-26 | 2025-12-29 | 2021-03-26 | 2025-12-29
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112HINT | HARLEM 1 iNTERIOR RECONSTRUCTION | 1 | DESIGN | 2020-01-01 | 2020-09-26 | 2020-01-01 | 2020-09-26
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112HINT | HARLEM 1 iNTERIOR RECONSTRUCTION | 2 | BID AWARD AND REGISTER CONTRCT | 2020-09-27 | 2021-03-25 | 2020-09-27 | 2021-03-25
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112HINT | HARLEM 1 iNTERIOR RECONSTRUCTION | 3 | CONSTRUCTION | 2021-03-26 | 2025-12-29 | 2021-03-26 | 2025-12-29
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112HLET | HARLEM 1 ELECTRICAL UPGRADE | 1 | DESIGN | 2020-01-01 | 2020-09-26 | 2020-01-01 | 2020-09-26
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112HLET | HARLEM 1 ELECTRICAL UPGRADE | 2 | BID AWARD AND REGISTER CONTRCT | 2020-09-27 | 2021-03-25 | 2020-09-27 | 2021-03-25
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112HLET | HARLEM 1 ELECTRICAL UPGRADE | 3 | CONSTRUCTION | 2021-03-26 | 2025-12-29 | 2021-03-26 | 2025-12-29
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112HMBL | HARLEM 1 BOILER REPLACEMENT | 1 | DESIGN | 2020-01-01 | 2020-09-26 | 2020-01-01 | 2020-09-26
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112HMBL | HARLEM 1 BOILER REPLACEMENT | 2 | BID AWARD AND REGISTER CONTRCT | 2020-09-27 | 2021-03-25 | 2020-09-27 | 2021-03-25
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112HMBL | HARLEM 1 BOILER REPLACEMENT | 3 | CONSTRUCTION | 2021-03-26 | 2025-12-29 | 2021-03-26 | 2025-12-29
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112HMED | HARLEM 1 - ELECTRICAL PANEL UPGRADE | 1 | DESIGN | 2020-01-01 | 2020-09-26 | 2020-01-01 | 2020-09-26
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112HMED | HARLEM 1 - ELECTRICAL PANEL UPGRADE | 2 | BID AWARD AND REGISTER CONTRCT | 2020-09-27 | 2021-03-25 | 2020-09-27 | 2021-03-25
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112HMED | HARLEM 1 - ELECTRICAL PANEL UPGRADE | 3 | CONSTRUCTION | 2021-03-26 | 2025-12-29 | 2021-03-26 | 2025-12-29
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112HSCR | HELP SEC-COTTAGE ROOF REPLACEMENT | 1 | DESIGN | 2019-01-01 | 2019-09-27 | 2019-01-01 | 2019-09-27
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112HSCR | HELP SEC-COTTAGE ROOF REPLACEMENT | 2 | BID AWARD AND REGISTER CONTRCT | 2019-09-28 | 2020-03-25 | 2019-09-28 | 2020-03-25
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112HSCR | HELP SEC-COTTAGE ROOF REPLACEMENT | 3 | CONSTRUCTION | 2020-03-26 | 2024-12-29 | 2020-03-26 | 2024-12-29
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112HSMR | HELP SEC.-MIAN BLDG.ROOF REPLACEMENT | 1 | DESIGN | 2019-01-01 | 2019-09-27 | 2019-01-01 | 2019-09-27
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112HSMR | HELP SEC.-MIAN BLDG.ROOF REPLACEMENT | 2 | BID AWARD AND REGISTER CONTRCT | 2019-09-28 | 2020-03-25 | 2019-09-28 | 2020-03-25
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112HSMR | HELP SEC.-MIAN BLDG.ROOF REPLACEMENT | 3 | CONSTRUCTION | 2020-03-26 | 2024-12-29 | 2020-03-26 | 2024-12-29
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112HSSF | HELP SEC FENCE REPLACEMENT | 1 | DESIGN | 2019-08-23 | 2020-05-18 | 2019-08-23 | 2020-05-18
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112HSSF | HELP SEC FENCE REPLACEMENT | 2 | BID AWARD AND REGISTER CONTRCT | 2020-05-19 | 2020-11-14 | 2020-05-19 | 2020-11-14
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112HSSF | HELP SEC FENCE REPLACEMENT | 3 | CONSTRUCTION | 2020-11-15 | 2025-08-20 | 2020-11-15 | 2025-08-20
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112KITC | PROJECT RENEWAL-EAST 3RD STREET KITCHEN NC#13-260288T82144 | 1 | DEVELOP SCOPE | 2013-01-11 | 2013-04-10 | 2015-05-18 | 2015-08-15
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112KITC | PROJECT RENEWAL-EAST 3RD STREET KITCHEN NC#13-260288T82144 | 2 | PRELIMINARY DESIGN | 2013-04-11 | 2013-08-08 | 2013-04-11 | 2013-08-08
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112KITC | PROJECT RENEWAL-EAST 3RD STREET KITCHEN NC#13-260288T82144 | 3 | FINAL DESIGN | 2013-08-09 | 2013-12-06 | 2013-08-09 | 2013-08-08
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112KITC | PROJECT RENEWAL-EAST 3RD STREET KITCHEN NC#13-260288T82144 | 4 | BID AWARD AND REGISTER CONTRCT | 2013-12-07 | 2014-06-04 | 2013-08-09 | 2013-08-08
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112KITC | PROJECT RENEWAL-EAST 3RD STREET KITCHEN NC#13-260288T82144 | 5 | CONSTRUCTION TO 25% | 2014-06-05 | 2014-10-02 | 2013-08-09 | 2013-08-08
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112KITC | PROJECT RENEWAL-EAST 3RD STREET KITCHEN NC#13-260288T82144 | 6 | CONSTRUCTION TO 50% | 2014-10-03 | 2015-01-30 | 2013-08-09 | 2013-08-08
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112KITC | PROJECT RENEWAL-EAST 3RD STREET KITCHEN NC#13-260288T82144 | 7 | CONSTRUCTION TO 75% | 2015-01-31 | 2015-05-30 | 2013-08-09 | 2027-04-17
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112KITC | PROJECT RENEWAL-EAST 3RD STREET KITCHEN NC#13-260288T82144 | 8 | ORIGINAL EQUIP & FURNISHING | 2015-05-31 | 2015-08-28 | 2027-04-18 | 2027-04-17
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112KITC | PROJECT RENEWAL-EAST 3RD STREET KITCHEN NC#13-260288T82144 | 9 | SUBSTANTIAL COMPLETION | 2015-08-29 | 2015-10-27 | 2027-04-18 | 2027-04-17
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112KITC | PROJECT RENEWAL-EAST 3RD STREET KITCHEN NC#13-260288T82144 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-10-28 | 2015-11-26 | 2027-04-18 | 2027-05-17
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112KNUG | KEENER ASSESSMENT SHELTER - BUILDING UPGRADE | 1 | DESIGN | 2023-01-01 | 2023-09-27 | 2023-01-01 | 2023-09-27
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112KNUG | KEENER ASSESSMENT SHELTER - BUILDING UPGRADE | 2 | BID AWARD AND REGISTER CONTRCT | 2023-09-28 | 2024-03-25 | 2023-09-28 | 2024-03-25
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112KNUG | KEENER ASSESSMENT SHELTER - BUILDING UPGRADE | 3 | CONSTRUCTION | 2024-03-26 | 2028-12-29 | 2024-03-26 | 2028-12-29
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112KTEX | KENTON HALL - FACADE RECONSTRUCTION | 1 | DESIGN | 2024-05-30 | 2025-02-23 | 2024-05-30 | 2025-02-23
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112KTEX | KENTON HALL - FACADE RECONSTRUCTION | 2 | BID AWARD AND REGISTER CONTRCT | 2025-02-24 | 2025-08-22 | 2025-02-24 | 2025-08-22
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112KTEX | KENTON HALL - FACADE RECONSTRUCTION | 3 | CONSTRUCTION | 2025-08-23 | 2030-05-28 | 2025-08-23 | 2030-05-28
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112KTFR | FLUE REPLACEMENT AT KENTON HALL | 1 | CONSTRUCTION | 2020-01-01 | 2021-01-09 | 2020-01-01 | 2021-01-09
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112KTFR | FLUE REPLACEMENT AT KENTON HALL | 2 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-01-10 | 2021-04-09 | 2021-01-10 | 2021-04-09
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112SWBU | Schwartz Homeless Shelter | 1 | DESIGN | 2022-01-01 | 2022-09-27 | 2022-01-01 | 2022-09-27
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112SWBU | Schwartz Homeless Shelter | 2 | BID AWARD AND REGISTER CONTRCT | 2022-09-28 | 2023-03-26 | 2022-09-28 | 2023-03-26
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112SWBU | Schwartz Homeless Shelter | 3 | CONSTRUCTION | 2023-03-27 | 2027-12-30 | 2023-03-27 | 2027-12-30
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112THBH | 8 EAST THIRD ST BATHROOM RECONSTRUCTION | 1 | DESIGN | 2018-06-01 | 2019-02-25 | 2018-06-01 | 2019-02-25
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112THBH | 8 EAST THIRD ST BATHROOM RECONSTRUCTION | 2 | BID AWARD AND REGISTER CONTRCT | 2019-02-26 | 2019-08-24 | 2019-02-26 | 2019-08-24
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112THBH | 8 EAST THIRD ST BATHROOM RECONSTRUCTION | 3 | CONSTRUCTION | 2019-08-25 | 2024-05-29 | 2019-08-25 | 2024-05-29
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112THBR | 282 EAST THIRD ST BOILER RECONSTRUCTION | 1 | DESIGN | 2020-07-01 | 2020-12-27 | 2020-07-01 | 2020-12-27
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112THBR | 282 EAST THIRD ST BOILER RECONSTRUCTION | 2 | CONSTRUCTION | 2020-12-28 | 2021-12-27 | 2020-12-28 | 2021-12-27
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112THFC | 8 EAST THIRD ST SHELTER FACADE AND STAIRS | 1 | DESIGN | 2021-05-30 | 2022-02-23 | 2021-05-30 | 2022-02-23
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112THFC | 8 EAST THIRD ST SHELTER FACADE AND STAIRS | 2 | BID AWARD AND REGISTER CONTRCT | 2022-02-24 | 2022-08-22 | 2022-02-24 | 2022-08-22
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112THFC | 8 EAST THIRD ST SHELTER FACADE AND STAIRS | 3 | CONSTRUCTION | 2022-08-23 | 2027-05-28 | 2022-08-23 | 2027-05-28
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112THKS | 8 EAST THIRD STREET KITCHEN STRUCTURE REHABILITATION | 1 | DESIGN | 2020-06-01 | 2020-11-27 | 2020-06-01 | 2020-11-27
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112THKS | 8 EAST THIRD STREET KITCHEN STRUCTURE REHABILITATION | 2 | CONSTRUCTION | 2020-11-28 | 2021-11-27 | 2020-11-28 | 2021-11-27
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH115CTBU | 78 CATHERINE STREET - BATHROOM UPGRADE | 1 | DESIGN | 2016-08-03 | 2017-04-29 | 2016-08-03 | 2017-04-29
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH115CTBU | 78 CATHERINE STREET - BATHROOM UPGRADE | 2 | BID AWARD AND REGISTER CONTRCT | 2017-04-30 | 2017-10-26 | 2017-04-30 | 2017-10-26
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH115CTBU | 78 CATHERINE STREET - BATHROOM UPGRADE | 3 | CONSTRUCTION | 2017-10-27 | 2022-08-01 | 2017-10-27 | 2022-08-01
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH115CTEF | CATHERINE STREET ELECTRICAL UPGRADE | 1 | DESIGN | 2019-01-01 | 2019-09-27 | 2019-01-01 | 2019-09-27
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH115CTEF | CATHERINE STREET ELECTRICAL UPGRADE | 2 | BID AWARD AND REGISTER CONTRCT | 2019-09-28 | 2020-03-25 | 2019-09-28 | 2020-03-25
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH115CTEF | CATHERINE STREET ELECTRICAL UPGRADE | 3 | CONSTRUCTION | 2020-03-26 | 2024-12-29 | 2020-03-26 | 2024-12-29
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH115JCFA | JENNIE CLARKE BACKFLOW PREVENTER | 1 | DESIGN | 2022-01-01 | 2022-09-27 | 2022-01-01 | 2022-09-27
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH115JCFA | JENNIE CLARKE BACKFLOW PREVENTER | 2 | BID AWARD AND REGISTER CONTRCT | 2022-09-28 | 2023-03-26 | 2022-09-28 | 2023-03-26
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH115JCFA | JENNIE CLARKE BACKFLOW PREVENTER | 3 | CONSTRUCTION | 2023-03-27 | 2027-12-30 | 2023-03-27 | 2027-12-30
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH115REBO | REGENT BOILER | 1 | DESIGN | 2020-01-01 | 2020-09-26 | 2020-01-01 | 2020-09-26
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH115REBO | REGENT BOILER | 2 | BID AWARD AND REGISTER CONTRCT | 2020-09-27 | 2021-03-25 | 2020-09-27 | 2021-03-25
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH115REBO | REGENT BOILER | 3 | CONSTRUCTION | 2021-03-26 | 2025-12-29 | 2021-03-26 | 2025-12-29
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH115RECL | REGENT CEILINGS | 1 | DESIGN | 2016-08-03 | 2017-04-29 | 2016-08-03 | 2017-04-29
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH115RECL | REGENT CEILINGS | 2 | BID AWARD AND REGISTER CONTRCT | 2017-04-30 | 2017-10-26 | 2017-04-30 | 2017-10-26
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH115RECL | REGENT CEILINGS | 3 | CONSTRUCTION | 2017-10-27 | 2022-08-01 | 2017-10-27 | 2022-08-01
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH115RFRE | REGENT FAMILY RESIDENCE LIFE SAFETY UPGRADE, FIRE SAFETY | 1 | DEVELOP SCOPE | 2013-01-14 | 2013-04-13 | 2019-01-15 | 2019-04-14
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH115RFRE | REGENT FAMILY RESIDENCE LIFE SAFETY UPGRADE, FIRE SAFETY | 2 | PRELIMINARY DESIGN | 2013-04-14 | 2013-08-11 | 2019-04-15 | 2019-08-12
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH115RFRE | REGENT FAMILY RESIDENCE LIFE SAFETY UPGRADE, FIRE SAFETY | 3 | FINAL DESIGN | 2013-08-12 | 2013-12-09 | 2019-08-13 | 2019-12-10
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH115RFRE | REGENT FAMILY RESIDENCE LIFE SAFETY UPGRADE, FIRE SAFETY | 4 | BID AWARD AND REGISTER CONTRCT | 2013-12-10 | 2014-06-07 | 2019-12-11 | 2020-06-07
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH115RFRE | REGENT FAMILY RESIDENCE LIFE SAFETY UPGRADE, FIRE SAFETY | 5 | CONSTRUCTION TO 25% | 2014-06-08 | 2014-10-05 | 2020-06-08 | 2020-10-05
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH115RFRE | REGENT FAMILY RESIDENCE LIFE SAFETY UPGRADE, FIRE SAFETY | 6 | CONSTRUCTION TO 50% | 2014-10-06 | 2015-02-02 | 2020-10-06 | 2021-02-02
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH115RFRE | REGENT FAMILY RESIDENCE LIFE SAFETY UPGRADE, FIRE SAFETY | 7 | CONSTRUCTION TO 75% | 2015-02-03 | 2015-06-02 | 2021-02-03 | 2021-06-02
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH115RFRE | REGENT FAMILY RESIDENCE LIFE SAFETY UPGRADE, FIRE SAFETY | 8 | ORIGINAL EQUIP & FURNISHING | 2015-06-03 | 2015-08-31 | 2021-06-03 | 2021-08-31
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH115RFRE | REGENT FAMILY RESIDENCE LIFE SAFETY UPGRADE, FIRE SAFETY | 9 | SUBSTANTIAL COMPLETION | 2015-09-01 | 2015-10-30 | 2021-09-01 | 2021-10-30
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH115RFRE | REGENT FAMILY RESIDENCE LIFE SAFETY UPGRADE, FIRE SAFETY | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-10-31 | 2015-11-29 | 2021-10-31 | 2021-11-29
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH115RGST | REGENT - STAIR B | 1 | DESIGN | 2016-01-04 | 2016-09-29 | 2016-01-04 | 2016-09-29
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH115RGST | REGENT - STAIR B | 2 | BID AWARD AND REGISTER CONTRCT | 2016-09-30 | 2017-03-28 | 2016-09-30 | 2017-03-28
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH115RGST | REGENT - STAIR B | 3 | CONSTRUCTION | 2017-03-29 | 2021-01-01 | 2017-03-29 | 2021-01-01
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HHCN007 | INSTALLATION OF BACKUP GENERATOR | 1 | DEVELOP SCOPE | 2016-07-03 | 2016-09-30 | 2022-07-01 | 2022-12-27
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HHCN007 | INSTALLATION OF BACKUP GENERATOR | 2 | PRELIMINARY DESIGN | 2016-10-01 | 2017-01-28 | 2022-12-28 | 2023-12-27
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HHCN007 | INSTALLATION OF BACKUP GENERATOR | 3 | FINAL DESIGN | 2017-01-29 | 2017-05-28 | 2022-12-28 | 2023-12-27
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HHCN007 | INSTALLATION OF BACKUP GENERATOR | 4 | BID AWARD AND REGISTER CONTRCT | 2017-05-29 | 2017-11-24 | 2022-12-28 | 2023-12-27
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HHCN007 | INSTALLATION OF BACKUP GENERATOR | 5 | CONSTRUCTION TO 25% | 2017-11-25 | 2018-03-24 | 2022-12-28 | 2023-12-27
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HHCN007 | INSTALLATION OF BACKUP GENERATOR | 6 | CONSTRUCTION TO 50% | 2018-03-25 | 2018-07-22 | 2022-12-28 | 2023-12-27
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HHCN007 | INSTALLATION OF BACKUP GENERATOR | 7 | CONSTRUCTION TO 75% | 2018-07-23 | 2018-11-19 | 2022-12-28 | 2023-12-27
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HHCN007 | INSTALLATION OF BACKUP GENERATOR | 8 | ORIGINAL EQUIP & FURNISHING | 2018-11-20 | 2019-02-17 | 2022-12-28 | 2023-12-27
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HHCN007 | INSTALLATION OF BACKUP GENERATOR | 9 | SUBSTANTIAL COMPLETION | 2019-02-18 | 2019-04-18 | 2022-12-28 | 2023-12-27
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HHCN007 | INSTALLATION OF BACKUP GENERATOR | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-04-19 | 2019-05-18 | 2022-12-28 | 2023-12-27
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HHMNEW1 | PROJECT RENEWAL - RENOVATE FT. WASH. ARMORY | 1 | DESIGN | 2019-07-03 | 2020-03-28 | 2019-07-03 | 2020-03-28
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HHMNEW1 | PROJECT RENEWAL - RENOVATE FT. WASH. ARMORY | 2 | BID AWARD AND REGISTER CONTRCT | 2020-03-29 | 2020-09-24 | 2020-03-29 | 2020-09-24
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HHMNEW1 | PROJECT RENEWAL - RENOVATE FT. WASH. ARMORY | 3 | CONSTRUCTION | 2020-09-25 | 2025-06-30 | 2020-09-25 | 2025-06-30
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HHNC005 | KITCHEN RENOVATION AT 8 EAST THIRD STREET HOMELESS SHELTER | 1 | DESIGN | 2019-07-03 | 2020-03-28 | 2019-07-03 | 2020-03-28
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HHNC005 | KITCHEN RENOVATION AT 8 EAST THIRD STREET HOMELESS SHELTER | 2 | BID AWARD AND REGISTER CONTRCT | 2020-03-29 | 2020-09-24 | 2020-03-29 | 2020-09-24
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HHNC005 | KITCHEN RENOVATION AT 8 EAST THIRD STREET HOMELESS SHELTER | 3 | CONSTRUCTION | 2020-09-25 | 2025-06-30 | 2020-09-25 | 2025-06-30
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HHNC006 | FORT WASHINGTON ARMORY - ENTRYWAY REPAIR | 1 | DESIGN | 2019-07-03 | 2020-03-28 | 2019-07-03 | 2020-03-28
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HHNC006 | FORT WASHINGTON ARMORY - ENTRYWAY REPAIR | 2 | BID AWARD AND REGISTER CONTRCT | 2020-03-29 | 2020-09-24 | 2020-03-29 | 2020-09-24
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HHNC006 | FORT WASHINGTON ARMORY - ENTRYWAY REPAIR | 3 | CONSTRUCTION | 2020-09-25 | 2025-06-30 | 2020-09-25 | 2025-06-30
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HLCN014 | PROJECT RENEWAL , INC. - NEW PROVIDENCE BACKUP GENERATOR | 1 | DESIGN | 2016-12-12 | 2017-09-07 | 2016-12-12 | 2017-09-07
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HLCN014 | PROJECT RENEWAL , INC. - NEW PROVIDENCE BACKUP GENERATOR | 2 | BID AWARD AND REGISTER CONTRCT | 2017-09-08 | 2018-03-06 | 2017-09-08 | 2018-03-06
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HLCN014 | PROJECT RENEWAL , INC. - NEW PROVIDENCE BACKUP GENERATOR | 3 | CONSTRUCTION | 2018-03-07 | 2022-12-10 | 2018-03-07 | 2022-12-10
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | SOLARDHS1 | Solar PV system - HELP SEC at 111 Sunken Garden Loop | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-06-30 | 2020-06-01 | 2020-06-30
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | SOLARDHS1 | Solar PV system - HELP SEC at 111 Sunken Garden Loop | 2 | BID AWARD AND REGISTER CONTRCT | 2020-07-01 | 2020-08-29 | 2020-07-01 | 2020-08-29
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | SOLARDHS1 | Solar PV system - HELP SEC at 111 Sunken Garden Loop | 3 | CONSTRUCTION TO 50% | 2020-08-30 | 2021-02-25 | 2020-08-30 | 2021-02-25
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | SOLARDHS1 | Solar PV system - HELP SEC at 111 Sunken Garden Loop | 4 | CONSTRUCTION TO 75% | 2021-02-26 | 2021-05-26 | 2021-02-26 | 2021-05-26
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | SOLARDHS1 | Solar PV system - HELP SEC at 111 Sunken Garden Loop | 5 | SUBSTANTIAL COMPLETION | 2021-05-27 | 2021-07-25 | 2021-05-27 | 2021-07-25
20201123 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | SOLARDHS1 | Solar PV system - HELP SEC at 111 Sunken Garden Loop | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-07-26 | 2021-08-24 | 2021-07-26 | 2021-08-24
20201123 | MANHATTAN | 072 | DEPARTMENT OF CORRECTION | C75WTRMN | Replace Water Mains on Rikers Island | 1 | DESIGN | 2015-12-01 | 2016-09-30 | 2015-12-01 | 2016-09-30
20201123 | MANHATTAN | 072 | DEPARTMENT OF CORRECTION | C75WTRMN | Replace Water Mains on Rikers Island | 2 | BID AWARD AND REGISTER CONTRCT | 2016-10-01 | 2017-09-30 | 2016-10-01 | 2017-09-30
20201123 | MANHATTAN | 072 | DEPARTMENT OF CORRECTION | C75WTRMN | Replace Water Mains on Rikers Island | 3 | CONSTRUCTION TO 75% | 2017-10-01 | 2019-05-16 | 2017-10-01 | 2019-05-16
20201123 | MANHATTAN | 072 | DEPARTMENT OF CORRECTION | C75WTRMN | Replace Water Mains on Rikers Island | 4 | SUBSTANTIAL COMPLETION | 2019-05-17 | 2019-09-12 | 2019-05-17 | 2019-09-12
20201123 | MANHATTAN | 072 | DEPARTMENT OF CORRECTION | C75WTRMN | Replace Water Mains on Rikers Island | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-13 | 2019-11-30 | 2019-09-13 | 2025-11-30
20201123 | MANHATTAN | 096 | HUMAN RESOURCES ADMINISTRATION | HR2560LAC | 60 Lafayette Street Construction | 1 | DESIGN | 2020-07-01 | 2020-12-26 | 2021-07-01 | 2021-12-27
20201123 | MANHATTAN | 096 | HUMAN RESOURCES ADMINISTRATION | HR2560LAC | 60 Lafayette Street Construction | 2 | CONSTRUCTION | 2020-12-27 | 2021-06-24 | 2021-12-28 | 2022-06-25
20201123 | MANHATTAN | 096 | HUMAN RESOURCES ADMINISTRATION | HR25CHRYC | 115 Chrystie Street Construction | 1 | DESIGN | 2019-11-01 | 2020-04-28 | 2019-11-01 | 2020-04-28
20201123 | MANHATTAN | 096 | HUMAN RESOURCES ADMINISTRATION | HR25CHRYC | 115 Chrystie Street Construction | 2 | CONSTRUCTION | 2020-04-29 | 2020-10-25 | 2020-04-29 | 2020-10-25
20201123 | MANHATTAN | 096 | HUMAN RESOURCES ADMINISTRATION | HR25E162C | 109 East 16th Street Construction | 1 | DESIGN | 2020-07-01 | 2020-12-27 | 2020-07-01 | 2020-12-27
20201123 | MANHATTAN | 096 | HUMAN RESOURCES ADMINISTRATION | HR25E162C | 109 East 16th Street Construction | 2 | CONSTRUCTION | 2020-12-28 | 2021-06-25 | 2020-12-28 | 2021-06-25
20201123 | MANHATTAN | 096 | HUMAN RESOURCES ADMINISTRATION | HR25W125C | 132 W 125th St Construction | 1 | DESIGN | 2019-10-01 | 2020-03-28 | 2019-10-01 | 2020-03-28
20201123 | MANHATTAN | 096 | HUMAN RESOURCES ADMINISTRATION | HR25W125C | 132 W 125th St Construction | 2 | CONSTRUCTION | 2020-03-29 | 2020-09-24 | 2020-03-29 | 2020-09-24
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | ACEDCA434 | DCLA: AMNH - Lighting Control Upgrade, Rd 4 & Garage Rd 5 | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-09-28 | 2020-07-01 | 2020-09-28
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | ACEDCA434 | DCLA: AMNH - Lighting Control Upgrade, Rd 4 & Garage Rd 5 | 2 | PRELIMINARY DESIGN | 2016-09-29 | 2017-01-26 | 2020-09-29 | 2021-01-26
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | ACEDCA434 | DCLA: AMNH - Lighting Control Upgrade, Rd 4 & Garage Rd 5 | 3 | FINAL DESIGN | 2017-01-27 | 2017-07-25 | 2021-01-27 | 2021-07-25
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | ACEDCA434 | DCLA: AMNH - Lighting Control Upgrade, Rd 4 & Garage Rd 5 | 4 | BID AWARD AND REGISTER CONTRCT | 2017-07-26 | 2017-10-23 | 2021-07-26 | 2021-10-23
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | ACEDCA434 | DCLA: AMNH - Lighting Control Upgrade, Rd 4 & Garage Rd 5 | 5 | CONSTRUCTION TO 25% | 2017-10-24 | 2018-02-20 | 2021-10-24 | 2022-02-20
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | ACEDCA434 | DCLA: AMNH - Lighting Control Upgrade, Rd 4 & Garage Rd 5 | 6 | CONSTRUCTION TO 50% | 2018-02-21 | 2018-06-20 | 2022-02-21 | 2022-06-20
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | ACEDCA434 | DCLA: AMNH - Lighting Control Upgrade, Rd 4 & Garage Rd 5 | 7 | CONSTRUCTION TO 75% | 2018-06-21 | 2018-10-18 | 2022-06-21 | 2022-10-18
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | ACEDCA434 | DCLA: AMNH - Lighting Control Upgrade, Rd 4 & Garage Rd 5 | 8 | ORIGINAL EQUIP & FURNISHING | 2018-10-19 | 2019-01-16 | 2022-10-19 | 2023-01-16
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | ACEDCA434 | DCLA: AMNH - Lighting Control Upgrade, Rd 4 & Garage Rd 5 | 9 | SUBSTANTIAL COMPLETION | 2019-01-17 | 2019-03-17 | 2023-01-17 | 2023-03-17
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | ACEDCA434 | DCLA: AMNH - Lighting Control Upgrade, Rd 4 & Garage Rd 5 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-03-18 | 2019-04-16 | 2023-03-18 | 2023-04-16
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV022ANEG | MMA -Ancient Near East Gallery Renovation | 1 | DEVELOP SCOPE | 2021-06-30 | 2021-09-27 | 2021-06-30 | 2021-09-27
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV022ANEG | MMA -Ancient Near East Gallery Renovation | 2 | PRELIMINARY DESIGN | 2021-09-28 | 2022-01-25 | 2021-09-28 | 2022-01-25
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV022ANEG | MMA -Ancient Near East Gallery Renovation | 3 | FINAL DESIGN | 2022-01-26 | 2022-07-24 | 2022-01-26 | 2022-07-24
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV022ANEG | MMA -Ancient Near East Gallery Renovation | 4 | BID AWARD AND REGISTER CONTRCT | 2022-07-25 | 2022-10-22 | 2022-07-25 | 2022-10-22
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV022ANEG | MMA -Ancient Near East Gallery Renovation | 5 | CONSTRUCTION TO 25% | 2022-10-23 | 2023-02-19 | 2022-10-23 | 2023-02-19
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV022ANEG | MMA -Ancient Near East Gallery Renovation | 6 | CONSTRUCTION TO 50% | 2023-02-20 | 2023-06-19 | 2023-02-20 | 2023-06-19
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV022ANEG | MMA -Ancient Near East Gallery Renovation | 7 | CONSTRUCTION TO 75% | 2023-06-20 | 2023-10-17 | 2023-06-20 | 2023-10-17
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV022ANEG | MMA -Ancient Near East Gallery Renovation | 8 | ORIGINAL EQUIP & FURNISHING | 2023-10-18 | 2024-01-15 | 2023-10-18 | 2024-01-15
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV022ANEG | MMA -Ancient Near East Gallery Renovation | 9 | SUBSTANTIAL COMPLETION | 2024-01-16 | 2024-03-15 | 2024-01-16 | 2024-03-15
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV022ANEG | MMA -Ancient Near East Gallery Renovation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-03-16 | 2024-04-14 | 2024-03-16 | 2024-04-14
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV022-SKY | MMA - Metropolitan Museum Skylight Replacement for A, B, C W | 1 | DEVELOP SCOPE | 2022-04-07 | 2022-07-05 | 2022-04-07 | 2022-07-05
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV022-SKY | MMA - Metropolitan Museum Skylight Replacement for A, B, C W | 2 | BID AWARD AND REGISTER CONTRCT | 2022-07-06 | 2022-10-03 | 2022-07-06 | 2022-10-03
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV022-SKY | MMA - Metropolitan Museum Skylight Replacement for A, B, C W | 3 | CONSTRUCTION TO 50% | 2022-10-04 | 2023-01-31 | 2022-10-04 | 2023-01-31
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV022-SKY | MMA - Metropolitan Museum Skylight Replacement for A, B, C W | 4 | CONSTRUCTION TO 75% | 2023-02-01 | 2023-04-01 | 2023-02-01 | 2023-04-01
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV022-SKY | MMA - Metropolitan Museum Skylight Replacement for A, B, C W | 5 | SUBSTANTIAL COMPLETION | 2023-04-02 | 2023-05-31 | 2023-04-02 | 2023-05-31
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV022-SKY | MMA - Metropolitan Museum Skylight Replacement for A, B, C W | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-06-01 | 2023-06-30 | 2023-06-01 | 2023-06-30
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV034ELEV | AMNH - Elevator Upgrade | 1 | DEVELOP SCOPE | 2021-06-30 | 2021-09-27 | 2021-06-30 | 2021-09-27
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV034ELEV | AMNH - Elevator Upgrade | 2 | BID AWARD AND REGISTER CONTRCT | 2021-09-28 | 2021-12-26 | 2021-09-28 | 2021-12-26
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV034ELEV | AMNH - Elevator Upgrade | 3 | CONSTRUCTION TO 50% | 2021-12-27 | 2022-04-25 | 2021-12-27 | 2022-04-25
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV034ELEV | AMNH - Elevator Upgrade | 4 | CONSTRUCTION TO 75% | 2022-04-26 | 2022-06-24 | 2022-04-26 | 2022-06-24
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV034ELEV | AMNH - Elevator Upgrade | 5 | SUBSTANTIAL COMPLETION | 2022-06-25 | 2022-08-23 | 2022-06-25 | 2022-08-23
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV034ELEV | AMNH - Elevator Upgrade | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-08-24 | 2022-09-22 | 2022-08-24 | 2022-09-22
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV034-INF | AMNH - Security & Infrastructure Upgrade | 1 | DESIGN | 2003-06-30 | 2003-12-26 | 2021-06-30 | 2021-12-26
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV034-INF | AMNH - Security & Infrastructure Upgrade | 2 | BID AWARD AND REGISTER CONTRCT | 2003-12-27 | 2004-03-25 | 2021-12-27 | 2022-03-26
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV034-INF | AMNH - Security & Infrastructure Upgrade | 3 | CONSTRUCTION | 2004-03-26 | 2005-03-25 | 2022-03-27 | 2023-03-26
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV034-INF | AMNH - Security & Infrastructure Upgrade | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2005-03-26 | 2005-09-21 | 2023-03-27 | 2023-09-22
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV101HVAC | MJH - Museum HVAC | 1 | DEVELOP SCOPE | 2023-06-30 | 2023-09-27 | 2023-06-30 | 2023-09-27
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV101HVAC | MJH - Museum HVAC | 2 | PRELIMINARY DESIGN | 2023-09-28 | 2024-01-25 | 2023-09-28 | 2024-01-25
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV101HVAC | MJH - Museum HVAC | 3 | FINAL DESIGN | 2024-01-26 | 2024-07-23 | 2024-01-26 | 2024-07-23
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV101HVAC | MJH - Museum HVAC | 4 | BID AWARD AND REGISTER CONTRCT | 2024-07-24 | 2024-10-21 | 2024-07-24 | 2024-10-21
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV101HVAC | MJH - Museum HVAC | 5 | CONSTRUCTION TO 25% | 2024-10-22 | 2025-02-18 | 2024-10-22 | 2025-02-18
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV101HVAC | MJH - Museum HVAC | 6 | CONSTRUCTION TO 50% | 2025-02-19 | 2025-06-18 | 2025-02-19 | 2025-06-18
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV101HVAC | MJH - Museum HVAC | 7 | CONSTRUCTION TO 75% | 2025-06-19 | 2025-10-16 | 2025-06-19 | 2025-10-16
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV101HVAC | MJH - Museum HVAC | 8 | ORIGINAL EQUIP & FURNISHING | 2025-10-17 | 2026-01-14 | 2025-10-17 | 2026-01-14
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV101HVAC | MJH - Museum HVAC | 9 | SUBSTANTIAL COMPLETION | 2026-01-15 | 2026-03-15 | 2026-01-15 | 2026-03-15
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV101HVAC | MJH - Museum HVAC | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2026-03-16 | 2026-04-14 | 2026-03-16 | 2026-04-14
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV241BOIL | MCNY - Boiler Replacement | 1 | DEVELOP SCOPE | 2011-01-01 | 2011-03-31 | 2020-06-30 | 2020-09-27
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV241BOIL | MCNY - Boiler Replacement | 2 | PRELIMINARY DESIGN | 2011-04-01 | 2011-07-29 | 2020-09-28 | 2021-01-25
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV241BOIL | MCNY - Boiler Replacement | 3 | FINAL DESIGN | 2011-07-30 | 2012-01-25 | 2021-01-26 | 2021-07-24
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV241BOIL | MCNY - Boiler Replacement | 4 | BID AWARD AND REGISTER CONTRCT | 2012-01-26 | 2012-04-24 | 2021-07-25 | 2021-10-22
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV241BOIL | MCNY - Boiler Replacement | 5 | CONSTRUCTION TO 25% | 2012-04-25 | 2012-08-22 | 2021-10-23 | 2022-02-19
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV241BOIL | MCNY - Boiler Replacement | 6 | CONSTRUCTION TO 50% | 2012-08-23 | 2012-12-20 | 2022-02-20 | 2022-06-19
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV241BOIL | MCNY - Boiler Replacement | 7 | CONSTRUCTION TO 75% | 2012-12-21 | 2013-04-19 | 2022-06-20 | 2022-10-17
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV241BOIL | MCNY - Boiler Replacement | 8 | ORIGINAL EQUIP & FURNISHING | 2013-04-20 | 2013-07-18 | 2022-10-18 | 2023-01-15
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV241BOIL | MCNY - Boiler Replacement | 9 | SUBSTANTIAL COMPLETION | 2013-07-19 | 2013-09-16 | 2023-01-16 | 2023-03-16
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV241BOIL | MCNY - Boiler Replacement | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-09-17 | 2013-10-16 | 2023-03-17 | 2023-04-15
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV241-STL | MCNY -South Terrace Lighting | 1 | DEVELOP SCOPE | 2021-06-30 | 2021-09-27 | 2021-06-30 | 2021-09-27
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV241-STL | MCNY -South Terrace Lighting | 2 | PRELIMINARY DESIGN | 2021-09-28 | 2022-01-25 | 2021-09-28 | 2022-01-25
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV241-STL | MCNY -South Terrace Lighting | 3 | FINAL DESIGN | 2022-01-26 | 2022-07-24 | 2022-01-26 | 2022-07-24
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV241-STL | MCNY -South Terrace Lighting | 4 | BID AWARD AND REGISTER CONTRCT | 2022-07-25 | 2022-10-22 | 2022-07-25 | 2022-10-22
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV241-STL | MCNY -South Terrace Lighting | 5 | CONSTRUCTION TO 25% | 2022-10-23 | 2023-02-19 | 2022-10-23 | 2023-02-19
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV241-STL | MCNY -South Terrace Lighting | 6 | CONSTRUCTION TO 50% | 2023-02-20 | 2023-06-19 | 2023-02-20 | 2023-06-19
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV241-STL | MCNY -South Terrace Lighting | 7 | CONSTRUCTION TO 75% | 2023-06-20 | 2023-10-17 | 2023-06-20 | 2023-10-17
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV241-STL | MCNY -South Terrace Lighting | 8 | ORIGINAL EQUIP & FURNISHING | 2023-10-18 | 2024-01-15 | 2023-10-18 | 2024-01-15
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV241-STL | MCNY -South Terrace Lighting | 9 | SUBSTANTIAL COMPLETION | 2024-01-16 | 2024-03-15 | 2024-01-16 | 2024-03-15
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV241-STL | MCNY -South Terrace Lighting | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-03-16 | 2024-04-14 | 2024-03-16 | 2024-04-14
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV279ACON | NYCC - NY City Center Chiller Replacement | 1 | DEVELOP SCOPE | 2022-06-30 | 2022-09-27 | 2021-06-30 | 2021-09-27
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV279ACON | NYCC - NY City Center Chiller Replacement | 2 | PRELIMINARY DESIGN | 2022-09-28 | 2023-01-25 | 2021-09-28 | 2022-01-25
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV279ACON | NYCC - NY City Center Chiller Replacement | 3 | FINAL DESIGN | 2023-01-26 | 2023-07-24 | 2022-01-26 | 2022-07-24
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV279ACON | NYCC - NY City Center Chiller Replacement | 4 | BID AWARD AND REGISTER CONTRCT | 2023-07-25 | 2023-10-22 | 2022-07-25 | 2022-10-22
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV279ACON | NYCC - NY City Center Chiller Replacement | 5 | CONSTRUCTION TO 25% | 2023-10-23 | 2024-02-19 | 2022-10-23 | 2023-02-19
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV279ACON | NYCC - NY City Center Chiller Replacement | 6 | CONSTRUCTION TO 50% | 2024-02-20 | 2024-06-18 | 2023-02-20 | 2023-06-19
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV279ACON | NYCC - NY City Center Chiller Replacement | 7 | CONSTRUCTION TO 75% | 2024-06-19 | 2024-10-16 | 2023-06-20 | 2023-10-17
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV279ACON | NYCC - NY City Center Chiller Replacement | 8 | ORIGINAL EQUIP & FURNISHING | 2024-10-17 | 2025-01-14 | 2023-10-18 | 2024-01-15
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV279ACON | NYCC - NY City Center Chiller Replacement | 9 | SUBSTANTIAL COMPLETION | 2025-01-15 | 2025-03-15 | 2024-01-16 | 2024-03-15
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV279ACON | NYCC - NY City Center Chiller Replacement | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-03-16 | 2025-04-14 | 2024-03-16 | 2024-04-14
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV279ELEV | NYCC - New York City Center Materials Elevator | 1 | CONSTRUCTION | 2020-09-28 | 2021-09-22 | 2020-06-30 | 2020-09-27
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV279ELEV | NYCC - New York City Center Materials Elevator | 2 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-17 | 2020-09-28 | 2021-09-22
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV279ELEV | NYCC - New York City Center Materials Elevator | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-17 | 2021-09-23 | 2022-09-17
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV289-DEL | NYSF - DELACORTE Theater Renovation | 1 | DEVELOP SCOPE | 2022-06-30 | 2022-09-27 | 2021-06-30 | 2021-09-27
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV289-DEL | NYSF - DELACORTE Theater Renovation | 2 | BID AWARD AND REGISTER CONTRCT | 2022-09-28 | 2022-12-26 | 2021-09-28 | 2021-12-26
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV289-DEL | NYSF - DELACORTE Theater Renovation | 3 | CONSTRUCTION TO 50% | 2022-12-27 | 2023-04-25 | 2021-12-27 | 2022-04-25
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV289-DEL | NYSF - DELACORTE Theater Renovation | 4 | CONSTRUCTION TO 75% | 2023-04-26 | 2023-06-24 | 2022-04-26 | 2022-06-24
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV289-DEL | NYSF - DELACORTE Theater Renovation | 5 | SUBSTANTIAL COMPLETION | 2023-06-25 | 2023-08-23 | 2022-06-25 | 2022-08-23
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV289-DEL | NYSF - DELACORTE Theater Renovation | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-08-24 | 2023-09-22 | 2022-08-24 | 2022-09-22
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467PCTS | DCA PFA - Percent for Art Conservation of Public Art | 1 | CONSTRUCTION | 2024-09-28 | 2025-09-22 | 2024-06-30 | 2024-09-27
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467PCTS | DCA PFA - Percent for Art Conservation of Public Art | 2 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-09-23 | 2026-09-17 | 2024-09-28 | 2025-09-22
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467PCTS | DCA PFA - Percent for Art Conservation of Public Art | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-09-23 | 2026-09-17 | 2025-09-23 | 2026-09-17
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV475ROOF | NYST - NYC Ballet Roof Replacement | 1 | DEVELOP SCOPE | 2023-06-30 | 2023-09-27 | 2021-05-30 | 2021-08-27
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV475ROOF | NYST - NYC Ballet Roof Replacement | 2 | PRELIMINARY DESIGN | 2023-09-28 | 2024-01-25 | 2021-08-28 | 2021-12-25
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV475ROOF | NYST - NYC Ballet Roof Replacement | 3 | FINAL DESIGN | 2024-01-26 | 2024-07-23 | 2021-12-26 | 2022-06-23
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV475ROOF | NYST - NYC Ballet Roof Replacement | 4 | BID AWARD AND REGISTER CONTRCT | 2024-07-24 | 2024-10-21 | 2022-06-24 | 2022-09-21
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV475ROOF | NYST - NYC Ballet Roof Replacement | 5 | CONSTRUCTION TO 25% | 2024-10-22 | 2025-02-18 | 2022-09-22 | 2023-01-19
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV475ROOF | NYST - NYC Ballet Roof Replacement | 6 | CONSTRUCTION TO 50% | 2025-02-19 | 2025-06-18 | 2023-01-20 | 2023-05-19
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV475ROOF | NYST - NYC Ballet Roof Replacement | 7 | CONSTRUCTION TO 75% | 2025-06-19 | 2025-10-16 | 2023-05-20 | 2023-09-16
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV475ROOF | NYST - NYC Ballet Roof Replacement | 8 | ORIGINAL EQUIP & FURNISHING | 2025-10-17 | 2026-01-14 | 2023-09-17 | 2023-12-15
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV475ROOF | NYST - NYC Ballet Roof Replacement | 9 | SUBSTANTIAL COMPLETION | 2026-01-15 | 2026-03-15 | 2023-12-16 | 2024-02-13
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV475ROOF | NYST - NYC Ballet Roof Replacement | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2026-03-16 | 2026-04-14 | 2024-02-14 | 2024-03-14
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV489FTA | LCPA - FTA | 1 | DEVELOP SCOPE | 2019-06-30 | 2019-09-27 | 2019-06-30 | 2019-09-27
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV489FTA | LCPA - FTA | 2 | PRELIMINARY DESIGN | 2019-09-28 | 2020-01-25 | 2019-09-28 | 2020-01-25
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV489FTA | LCPA - FTA | 3 | FINAL DESIGN | 2020-01-26 | 2020-07-23 | 2020-01-26 | 2020-07-23
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV489FTA | LCPA - FTA | 4 | BID AWARD AND REGISTER CONTRCT | 2020-07-24 | 2020-10-21 | 2020-07-24 | 2020-10-21
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV489FTA | LCPA - FTA | 5 | CONSTRUCTION TO 25% | 2020-10-22 | 2021-02-18 | 2020-10-22 | 2021-02-18
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV489FTA | LCPA - FTA | 6 | CONSTRUCTION TO 50% | 2021-02-19 | 2021-06-18 | 2021-02-19 | 2021-06-18
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV489FTA | LCPA - FTA | 7 | CONSTRUCTION TO 75% | 2021-06-19 | 2021-10-16 | 2021-06-19 | 2021-10-16
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV489FTA | LCPA - FTA | 8 | ORIGINAL EQUIP & FURNISHING | 2021-10-17 | 2022-01-14 | 2021-10-17 | 2022-01-14
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV489FTA | LCPA - FTA | 9 | SUBSTANTIAL COMPLETION | 2022-01-15 | 2022-03-15 | 2022-01-15 | 2022-03-15
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV489FTA | LCPA - FTA | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-16 | 2022-04-14 | 2022-03-16 | 2022-04-14
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV503ELEV | CH- Carnegie Hall Elevators | 1 | DEVELOP SCOPE | 2023-06-30 | 2023-09-27 | 2022-06-30 | 2022-09-27
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV503ELEV | CH- Carnegie Hall Elevators | 2 | PRELIMINARY DESIGN | 2023-09-28 | 2024-01-25 | 2022-09-28 | 2023-01-25
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV503ELEV | CH- Carnegie Hall Elevators | 3 | FINAL DESIGN | 2024-01-26 | 2024-07-23 | 2023-01-26 | 2023-07-24
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV503ELEV | CH- Carnegie Hall Elevators | 4 | BID AWARD AND REGISTER CONTRCT | 2024-07-24 | 2024-10-21 | 2023-07-25 | 2023-10-22
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV503ELEV | CH- Carnegie Hall Elevators | 5 | CONSTRUCTION TO 25% | 2024-10-22 | 2025-02-18 | 2023-10-23 | 2024-02-19
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV503ELEV | CH- Carnegie Hall Elevators | 6 | CONSTRUCTION TO 50% | 2025-02-19 | 2025-06-18 | 2024-02-20 | 2024-06-18
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV503ELEV | CH- Carnegie Hall Elevators | 7 | CONSTRUCTION TO 75% | 2025-06-19 | 2025-10-16 | 2024-06-19 | 2024-10-16
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV503ELEV | CH- Carnegie Hall Elevators | 8 | ORIGINAL EQUIP & FURNISHING | 2025-10-17 | 2026-01-14 | 2024-10-17 | 2025-01-14
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV503ELEV | CH- Carnegie Hall Elevators | 9 | SUBSTANTIAL COMPLETION | 2026-01-15 | 2026-03-15 | 2025-01-15 | 2025-03-15
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV503ELEV | CH- Carnegie Hall Elevators | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2026-03-16 | 2026-04-14 | 2025-03-16 | 2025-04-14
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV503SDWK | CH - Carnegie Sidewalk Restoration | 1 | DEVELOP SCOPE | 2023-06-30 | 2023-09-27 | 2023-06-30 | 2023-09-27
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV503SDWK | CH - Carnegie Sidewalk Restoration | 2 | PRELIMINARY DESIGN | 2023-09-28 | 2024-01-25 | 2023-09-28 | 2024-01-25
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV503SDWK | CH - Carnegie Sidewalk Restoration | 3 | FINAL DESIGN | 2024-01-26 | 2024-07-23 | 2024-01-26 | 2024-07-23
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV503SDWK | CH - Carnegie Sidewalk Restoration | 4 | BID AWARD AND REGISTER CONTRCT | 2024-07-24 | 2024-10-21 | 2024-07-24 | 2024-10-21
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV503SDWK | CH - Carnegie Sidewalk Restoration | 5 | CONSTRUCTION TO 25% | 2024-10-22 | 2025-02-18 | 2024-10-22 | 2025-02-18
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV503SDWK | CH - Carnegie Sidewalk Restoration | 6 | CONSTRUCTION TO 50% | 2025-02-19 | 2025-06-18 | 2025-02-19 | 2025-06-18
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV503SDWK | CH - Carnegie Sidewalk Restoration | 7 | CONSTRUCTION TO 75% | 2025-06-19 | 2025-10-16 | 2025-06-19 | 2025-10-16
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV503SDWK | CH - Carnegie Sidewalk Restoration | 8 | ORIGINAL EQUIP & FURNISHING | 2025-10-17 | 2026-01-14 | 2025-10-17 | 2026-01-14
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV503SDWK | CH - Carnegie Sidewalk Restoration | 9 | SUBSTANTIAL COMPLETION | 2026-01-15 | 2026-03-15 | 2026-01-15 | 2026-03-15
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV503SDWK | CH - Carnegie Sidewalk Restoration | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2026-03-16 | 2026-04-14 | 2026-03-16 | 2026-04-14
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV788-FAC | 122C - 122 CC Facade Reconstruction | 1 | DEVELOP SCOPE | 2020-06-30 | 2020-09-27 | 2020-06-30 | 2020-09-27
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV788-FAC | 122C - 122 CC Facade Reconstruction | 2 | PRELIMINARY DESIGN | 2020-09-28 | 2021-01-25 | 2020-09-28 | 2021-01-25
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV788-FAC | 122C - 122 CC Facade Reconstruction | 3 | FINAL DESIGN | 2021-01-26 | 2021-07-24 | 2021-01-26 | 2021-07-24
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV788-FAC | 122C - 122 CC Facade Reconstruction | 4 | BID AWARD AND REGISTER CONTRCT | 2021-07-25 | 2021-10-22 | 2021-07-25 | 2021-10-22
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV788-FAC | 122C - 122 CC Facade Reconstruction | 5 | CONSTRUCTION TO 25% | 2021-10-23 | 2022-02-19 | 2021-10-23 | 2022-02-19
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV788-FAC | 122C - 122 CC Facade Reconstruction | 6 | CONSTRUCTION TO 50% | 2022-02-20 | 2022-06-19 | 2022-02-20 | 2022-06-19
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV788-FAC | 122C - 122 CC Facade Reconstruction | 7 | CONSTRUCTION TO 75% | 2022-06-20 | 2022-10-17 | 2022-06-20 | 2022-10-17
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV788-FAC | 122C - 122 CC Facade Reconstruction | 8 | ORIGINAL EQUIP & FURNISHING | 2022-10-18 | 2023-01-15 | 2022-10-18 | 2023-01-15
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV788-FAC | 122C - 122 CC Facade Reconstruction | 9 | SUBSTANTIAL COMPLETION | 2023-01-16 | 2023-03-16 | 2023-01-16 | 2023-03-16
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV788-FAC | 122C - 122 CC Facade Reconstruction | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-03-17 | 2023-04-15 | 2023-03-17 | 2023-04-15
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV788-TER | 122C - 122 Community Center Roof Terrace | 1 | DEVELOP SCOPE | 2022-06-30 | 2022-09-27 | 2022-06-30 | 2022-09-27
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV788-TER | 122C - 122 Community Center Roof Terrace | 2 | PRELIMINARY DESIGN | 2022-09-28 | 2023-01-25 | 2022-09-28 | 2023-01-25
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV788-TER | 122C - 122 Community Center Roof Terrace | 3 | FINAL DESIGN | 2023-01-26 | 2023-07-24 | 2023-01-26 | 2023-07-24
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV788-TER | 122C - 122 Community Center Roof Terrace | 4 | BID AWARD AND REGISTER CONTRCT | 2023-07-25 | 2023-10-22 | 2023-07-25 | 2023-10-22
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV788-TER | 122C - 122 Community Center Roof Terrace | 5 | CONSTRUCTION TO 25% | 2023-10-23 | 2024-02-19 | 2023-10-23 | 2024-02-19
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV788-TER | 122C - 122 Community Center Roof Terrace | 6 | CONSTRUCTION TO 50% | 2024-02-20 | 2024-06-18 | 2024-02-20 | 2024-06-18
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV788-TER | 122C - 122 Community Center Roof Terrace | 7 | CONSTRUCTION TO 75% | 2024-06-19 | 2024-10-16 | 2024-06-19 | 2024-10-16
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV788-TER | 122C - 122 Community Center Roof Terrace | 8 | ORIGINAL EQUIP & FURNISHING | 2024-10-17 | 2025-01-14 | 2024-10-17 | 2025-01-14
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV788-TER | 122C - 122 Community Center Roof Terrace | 9 | SUBSTANTIAL COMPLETION | 2025-01-15 | 2025-03-15 | 2025-01-15 | 2025-03-15
20201123 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV788-TER | 122C - 122 Community Center Roof Terrace | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-03-16 | 2025-04-14 | 2025-03-16 | 2025-04-14
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 125THPDIM | 125th St & Park Ave - Pedestrian Improvements | 1 | DESIGN | 2005-02-15 | 2005-03-06 | 2007-02-15 | 2007-03-06
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 125THPDIM | 125th St & Park Ave - Pedestrian Improvements | 2 | BID AWARD AND REGISTER CONTRCT | 2005-03-07 | 2005-03-21 | 2007-03-07 | 2007-03-21
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 125THPDIM | 125th St & Park Ave - Pedestrian Improvements | 3 | CONSTRUCTION | 2005-03-22 | 2005-04-25 | 2007-03-22 | 2007-04-25
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 125THPDIM | 125th St & Park Ave - Pedestrian Improvements | 4 | ORIGINAL EQUIP & FURNISHING | 2005-04-26 | 2005-05-05 | 2007-04-26 | 2007-05-05
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 125THPDIM | 125th St & Park Ave - Pedestrian Improvements | 5 | SUBSTANTIAL COMPLETION | 2005-05-06 | 2005-05-20 | 2007-05-06 | 2007-05-20
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 125THPDIM | 125th St & Park Ave - Pedestrian Improvements | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2005-05-21 | 2016-06-30 | 2007-05-21 | 2024-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 1680LEXAV | 1680 Lexington Avenue - Ventiliation | 1 | DESIGN | 2000-06-01 | 2000-06-20 | 2000-06-01 | 2000-06-20
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 1680LEXAV | 1680 Lexington Avenue - Ventiliation | 2 | BID AWARD AND REGISTER CONTRCT | 2000-06-21 | 2000-07-05 | 2000-06-21 | 2000-07-05
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 1680LEXAV | 1680 Lexington Avenue - Ventiliation | 3 | CONSTRUCTION | 2000-07-06 | 2008-06-30 | 2000-07-06 | 2008-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 1680LEXAV | 1680 Lexington Avenue - Ventiliation | 4 | ORIGINAL EQUIP & FURNISHING | 2008-07-01 | 2008-06-30 | 2008-07-01 | 2008-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 1680LEXAV | 1680 Lexington Avenue - Ventiliation | 5 | SUBSTANTIAL COMPLETION | 2008-07-01 | 2008-06-30 | 2008-07-01 | 2008-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 1680LEXAV | 1680 Lexington Avenue - Ventiliation | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-07-01 | 2008-07-05 | 2010-07-01 | 2011-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 1680LEXSP | 1680 Lexington Sound Proofing | 1 | DESIGN | 2015-06-30 | 2015-07-19 | 2019-03-23 | 2019-04-11
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 1680LEXSP | 1680 Lexington Sound Proofing | 2 | BID AWARD AND REGISTER CONTRCT | 2015-07-20 | 2015-08-03 | 2019-04-12 | 2019-04-26
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 1680LEXSP | 1680 Lexington Sound Proofing | 3 | CONSTRUCTION | 2015-08-04 | 2015-09-07 | 2019-04-27 | 2019-05-31
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 1680LEXSP | 1680 Lexington Sound Proofing | 4 | ORIGINAL EQUIP & FURNISHING | 2015-09-08 | 2015-09-17 | 2019-06-01 | 2019-06-10
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 1680LEXSP | 1680 Lexington Sound Proofing | 5 | SUBSTANTIAL COMPLETION | 2015-09-18 | 2015-10-02 | 2019-06-11 | 2019-06-25
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 1680LEXSP | 1680 Lexington Sound Proofing | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-10-03 | 2015-10-07 | 2019-06-26 | 2029-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 34STHELI | E. 34th Street Heliport Rehabilitation | 1 | DESIGN | 2010-01-01 | 2012-01-20 | 2010-01-01 | 2015-01-19
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 34STHELI | E. 34th Street Heliport Rehabilitation | 2 | BID AWARD AND REGISTER CONTRCT | 2012-01-21 | 2012-01-20 | 2015-01-20 | 2015-01-19
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 34STHELI | E. 34th Street Heliport Rehabilitation | 3 | CONSTRUCTION | 2012-01-21 | 2014-01-20 | 2015-01-20 | 2017-01-19
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 34STHELI | E. 34th Street Heliport Rehabilitation | 4 | ORIGINAL EQUIP & FURNISHING | 2014-01-21 | 2014-01-20 | 2017-01-20 | 2017-01-19
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 34STHELI | E. 34th Street Heliport Rehabilitation | 5 | SUBSTANTIAL COMPLETION | 2014-01-21 | 2014-01-20 | 2017-01-20 | 2017-01-19
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 34STHELI | E. 34th Street Heliport Rehabilitation | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-01-21 | 2014-01-25 | 2017-01-20 | 2025-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 68201101 | RENOVATION AND CONSTRUCTION OF NEW GOLDWATER NORTH LTACH | 1 | DESIGN | 2012-06-01 | 2012-06-20 | 2007-06-01 | 2007-06-20
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 68201101 | RENOVATION AND CONSTRUCTION OF NEW GOLDWATER NORTH LTACH | 2 | BID AWARD AND REGISTER CONTRCT | 2012-06-21 | 2012-07-05 | 2007-06-21 | 2007-07-05
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 68201101 | RENOVATION AND CONSTRUCTION OF NEW GOLDWATER NORTH LTACH | 3 | CONSTRUCTION | 2012-07-06 | 2012-08-09 | 2007-07-06 | 2007-08-09
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 68201101 | RENOVATION AND CONSTRUCTION OF NEW GOLDWATER NORTH LTACH | 4 | ORIGINAL EQUIP & FURNISHING | 2012-08-10 | 2012-08-19 | 2007-08-10 | 2007-08-19
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 68201101 | RENOVATION AND CONSTRUCTION OF NEW GOLDWATER NORTH LTACH | 5 | SUBSTANTIAL COMPLETION | 2012-08-20 | 2012-09-03 | 2007-08-20 | 2007-09-03
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 68201101 | RENOVATION AND CONSTRUCTION OF NEW GOLDWATER NORTH LTACH | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-09-04 | 2012-09-08 | 2007-09-04 | 2029-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 68201102 | CONSTRUCTION OF NEW GOLDWATER NORTH SNF | 1 | DESIGN | 2013-06-01 | 2013-06-20 | 2012-06-01 | 2012-06-20
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 68201102 | CONSTRUCTION OF NEW GOLDWATER NORTH SNF | 2 | BID AWARD AND REGISTER CONTRCT | 2013-06-21 | 2013-07-05 | 2013-06-21 | 2013-07-05
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 68201102 | CONSTRUCTION OF NEW GOLDWATER NORTH SNF | 3 | CONSTRUCTION | 2013-07-06 | 2013-08-09 | 2013-07-06 | 2013-08-09
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 68201102 | CONSTRUCTION OF NEW GOLDWATER NORTH SNF | 4 | ORIGINAL EQUIP & FURNISHING | 2013-08-10 | 2013-08-19 | 2013-08-10 | 2013-08-19
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 68201102 | CONSTRUCTION OF NEW GOLDWATER NORTH SNF | 5 | SUBSTANTIAL COMPLETION | 2013-08-20 | 2013-09-03 | 2013-08-20 | 2013-11-23
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 68201102 | CONSTRUCTION OF NEW GOLDWATER NORTH SNF | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-09-04 | 2013-09-08 | 2013-11-24 | 2029-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 8890PHA3 | Piers 88 & 90 Cluster Encapsulation Project Phase 3 | 1 | DESIGN | 2015-06-30 | 2015-07-19 | 2018-06-30 | 2018-07-19
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 8890PHA3 | Piers 88 & 90 Cluster Encapsulation Project Phase 3 | 2 | BID AWARD AND REGISTER CONTRCT | 2015-07-20 | 2015-08-03 | 2018-07-20 | 2018-08-03
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 8890PHA3 | Piers 88 & 90 Cluster Encapsulation Project Phase 3 | 3 | CONSTRUCTION | 2015-08-04 | 2015-09-07 | 2018-08-04 | 2018-09-07
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 8890PHA3 | Piers 88 & 90 Cluster Encapsulation Project Phase 3 | 4 | ORIGINAL EQUIP & FURNISHING | 2015-09-08 | 2015-09-17 | 2018-09-08 | 2018-09-17
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 8890PHA3 | Piers 88 & 90 Cluster Encapsulation Project Phase 3 | 5 | SUBSTANTIAL COMPLETION | 2015-09-18 | 2015-10-02 | 2018-09-18 | 2018-10-02
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 8890PHA3 | Piers 88 & 90 Cluster Encapsulation Project Phase 3 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-10-03 | 2015-10-07 | 2018-10-03 | 2023-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 8THSTPAVE | 8th St Bluestone Pavement Replacement | 1 | DESIGN | 2010-01-01 | 2012-01-20 | 2013-01-01 | 2015-01-20
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 8THSTPAVE | 8th St Bluestone Pavement Replacement | 2 | BID AWARD AND REGISTER CONTRCT | 2012-01-21 | 2012-01-20 | 2015-01-21 | 2015-01-20
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 8THSTPAVE | 8th St Bluestone Pavement Replacement | 3 | CONSTRUCTION | 2012-01-21 | 2014-01-20 | 2015-01-21 | 2017-01-20
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 8THSTPAVE | 8th St Bluestone Pavement Replacement | 4 | ORIGINAL EQUIP & FURNISHING | 2014-01-21 | 2014-01-20 | 2017-01-21 | 2017-01-20
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 8THSTPAVE | 8th St Bluestone Pavement Replacement | 5 | SUBSTANTIAL COMPLETION | 2014-01-21 | 2014-01-20 | 2017-01-21 | 2017-01-20
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 8THSTPAVE | 8th St Bluestone Pavement Replacement | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-01-21 | 2014-01-25 | 2017-01-21 | 2029-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 8THSTREET | FA - Village Alliance - Reconstruction of St. & Sidewalks | 1 | DESIGN | 1999-12-31 | 2000-01-19 | 2002-12-26 | 2003-01-14
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 8THSTREET | FA - Village Alliance - Reconstruction of St. & Sidewalks | 2 | BID AWARD AND REGISTER CONTRCT | 2000-01-20 | 2000-02-03 | 2003-01-15 | 2003-01-29
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 8THSTREET | FA - Village Alliance - Reconstruction of St. & Sidewalks | 3 | CONSTRUCTION | 2000-02-04 | 2007-06-30 | 2003-01-30 | 2023-06-25
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 8THSTREET | FA - Village Alliance - Reconstruction of St. & Sidewalks | 4 | ORIGINAL EQUIP & FURNISHING | 2007-07-01 | 2007-06-30 | 2023-06-26 | 2023-06-25
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 8THSTREET | FA - Village Alliance - Reconstruction of St. & Sidewalks | 5 | SUBSTANTIAL COMPLETION | 2007-07-01 | 2007-06-30 | 2023-06-26 | 2023-06-25
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 8THSTREET | FA - Village Alliance - Reconstruction of St. & Sidewalks | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2007-07-01 | 2007-07-05 | 2023-06-26 | 2023-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | AHGREEN | Andrew Haswell Green Park - Phase 2B | 1 | DESIGN | 2015-09-01 | 2017-03-30 | 2015-09-01 | 2017-03-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | AHGREEN | Andrew Haswell Green Park - Phase 2B | 2 | BID AWARD AND REGISTER CONTRCT | 2017-03-31 | 2017-03-30 | 2017-03-31 | 2017-03-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | AHGREEN | Andrew Haswell Green Park - Phase 2B | 3 | CONSTRUCTION | 2017-04-01 | 2019-04-30 | 2017-04-01 | 2019-04-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | AHGREEN | Andrew Haswell Green Park - Phase 2B | 4 | ORIGINAL EQUIP & FURNISHING | 2019-05-01 | 2019-04-30 | 2019-05-01 | 2019-04-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | AHGREEN | Andrew Haswell Green Park - Phase 2B | 5 | SUBSTANTIAL COMPLETION | 2019-05-01 | 2019-04-30 | 2019-05-01 | 2019-04-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | AHGREEN | Andrew Haswell Green Park - Phase 2B | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-05-01 | 2019-05-05 | 2019-05-01 | 2024-05-05
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | AMSTCORNR | LPCA Redevelopment Final Phase -Amsterdam Corner | 1 | DESIGN | 2022-01-01 | 2022-01-20 | 2022-01-01 | 2022-01-20
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | AMSTCORNR | LPCA Redevelopment Final Phase -Amsterdam Corner | 2 | BID AWARD AND REGISTER CONTRCT | 2022-01-21 | 2022-02-04 | 2022-01-21 | 2022-02-04
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | AMSTCORNR | LPCA Redevelopment Final Phase -Amsterdam Corner | 3 | CONSTRUCTION | 2022-02-05 | 2022-03-11 | 2022-02-05 | 2022-03-11
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | AMSTCORNR | LPCA Redevelopment Final Phase -Amsterdam Corner | 4 | ORIGINAL EQUIP & FURNISHING | 2022-03-12 | 2022-03-21 | 2022-03-12 | 2022-03-21
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | AMSTCORNR | LPCA Redevelopment Final Phase -Amsterdam Corner | 5 | SUBSTANTIAL COMPLETION | 2022-03-22 | 2022-04-05 | 2022-03-22 | 2022-04-05
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | AMSTCORNR | LPCA Redevelopment Final Phase -Amsterdam Corner | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-04-06 | 2024-04-10 | 2022-04-06 | 2024-04-10
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | C5232 | 34th Street Ferry Landing | 1 | DEVELOP SCOPE | 2003-11-01 | 2007-07-01 | 2017-11-04 | 2020-07-02
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | C5232 | 34th Street Ferry Landing | 2 | PRELIMINARY DESIGN | 2007-07-02 | 2007-07-01 | 2020-07-03 | 2020-07-02
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | C5232 | 34th Street Ferry Landing | 3 | FINAL DESIGN | 2007-07-02 | 2007-07-01 | 2020-07-03 | 2020-07-02
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | C5232 | 34th Street Ferry Landing | 4 | BID AWARD AND REGISTER CONTRCT | 2007-07-02 | 2007-07-01 | 2020-07-03 | 2020-07-02
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | C5232 | 34th Street Ferry Landing | 5 | CONSTRUCTION TO 25% | 2007-07-02 | 2007-07-01 | 2020-07-03 | 2020-07-02
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | C5232 | 34th Street Ferry Landing | 6 | CONSTRUCTION TO 50% | 2007-07-02 | 2007-07-01 | 2020-07-03 | 2020-07-02
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | C5232 | 34th Street Ferry Landing | 7 | CONSTRUCTION TO 75% | 2007-07-02 | 2007-07-01 | 2017-11-04 | 2020-07-02
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | C5232 | 34th Street Ferry Landing | 8 | ORIGINAL EQUIP & FURNISHING | 2007-07-02 | 2007-07-01 | 2025-07-03 | 2025-07-02
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | C5232 | 34th Street Ferry Landing | 9 | SUBSTANTIAL COMPLETION | 2005-06-01 | 2008-08-01 | 2005-06-01 | 2017-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | C5232 | 34th Street Ferry Landing | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-08-02 | 2008-08-06 | 2017-07-01 | 2017-07-05
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | CMPRENO | Chinatown Manpower Project - 4th Floor Renovation | 1 | DESIGN | 2015-06-30 | 2015-07-19 | 2015-06-30 | 2017-07-19
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | CMPRENO | Chinatown Manpower Project - 4th Floor Renovation | 2 | BID AWARD AND REGISTER CONTRCT | 2015-07-20 | 2015-08-03 | 2017-07-20 | 2017-07-19
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | CMPRENO | Chinatown Manpower Project - 4th Floor Renovation | 3 | CONSTRUCTION | 2015-08-04 | 2015-09-07 | 2017-07-20 | 2017-07-19
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | CMPRENO | Chinatown Manpower Project - 4th Floor Renovation | 4 | ORIGINAL EQUIP & FURNISHING | 2015-09-08 | 2015-09-17 | 2017-07-20 | 2017-07-19
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | CMPRENO | Chinatown Manpower Project - 4th Floor Renovation | 5 | SUBSTANTIAL COMPLETION | 2015-09-18 | 2015-10-02 | 2017-07-20 | 2017-07-19
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | CMPRENO | Chinatown Manpower Project - 4th Floor Renovation | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-10-03 | 2015-10-07 | 2017-07-20 | 2023-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | CWFSFERY2 | New York City Ferry - Infrastructure | 1 | DESIGN | 2018-07-01 | 2018-07-20 | 2018-07-01 | 2021-04-11
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | CWFSFERY2 | New York City Ferry - Infrastructure | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-21 | 2018-08-04 | 2021-04-12 | 2021-04-26
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | CWFSFERY2 | New York City Ferry - Infrastructure | 3 | CONSTRUCTION | 2018-08-05 | 2018-09-08 | 2021-04-27 | 2021-05-31
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | CWFSFERY2 | New York City Ferry - Infrastructure | 4 | ORIGINAL EQUIP & FURNISHING | 2018-09-09 | 2018-09-18 | 2021-06-01 | 2021-06-10
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | CWFSFERY2 | New York City Ferry - Infrastructure | 5 | SUBSTANTIAL COMPLETION | 2018-09-19 | 2018-10-03 | 2021-06-11 | 2021-06-25
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | CWFSFERY2 | New York City Ferry - Infrastructure | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-10-04 | 2018-10-08 | 2021-06-26 | 2027-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | DMECODOCK | Dyckman Pier -- Ferry Access to Eco-Dock | 1 | DESIGN | 2015-06-30 | 2021-06-30 | 2015-06-30 | 2021-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | DMECODOCK | Dyckman Pier -- Ferry Access to Eco-Dock | 2 | BID AWARD AND REGISTER CONTRCT | 2021-07-01 | 2021-06-30 | 2021-07-01 | 2021-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | DMECODOCK | Dyckman Pier -- Ferry Access to Eco-Dock | 3 | CONSTRUCTION | 2021-07-01 | 2021-06-30 | 2021-07-01 | 2021-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | DMECODOCK | Dyckman Pier -- Ferry Access to Eco-Dock | 4 | ORIGINAL EQUIP & FURNISHING | 2021-07-01 | 2021-06-30 | 2021-07-01 | 2021-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | DMECODOCK | Dyckman Pier -- Ferry Access to Eco-Dock | 5 | SUBSTANTIAL COMPLETION | 2021-07-01 | 2021-06-30 | 2021-07-01 | 2021-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | DMECODOCK | Dyckman Pier -- Ferry Access to Eco-Dock | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-07-01 | 2021-07-05 | 2021-07-01 | 2021-07-05
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | E34THPIER | EAST 34TH STREET PIER- NYU PARKING LOT REHAB | 1 | DEVELOP SCOPE | 2012-06-08 | 2012-09-05 | 2014-06-03 | 2014-06-22
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | E34THPIER | EAST 34TH STREET PIER- NYU PARKING LOT REHAB | 2 | PRELIMINARY DESIGN | 2012-09-06 | 2013-01-03 | 2014-06-23 | 2014-07-07
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | E34THPIER | EAST 34TH STREET PIER- NYU PARKING LOT REHAB | 3 | FINAL DESIGN | 2013-01-04 | 2013-07-02 | 2014-07-08 | 2022-06-25
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | E34THPIER | EAST 34TH STREET PIER- NYU PARKING LOT REHAB | 4 | BID AWARD AND REGISTER CONTRCT | 2013-07-03 | 2013-09-30 | 2022-06-26 | 2022-06-25
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | E34THPIER | EAST 34TH STREET PIER- NYU PARKING LOT REHAB | 5 | CONSTRUCTION TO 25% | 2013-10-01 | 2014-01-28 | 2022-06-26 | 2022-06-25
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | E34THPIER | EAST 34TH STREET PIER- NYU PARKING LOT REHAB | 6 | CONSTRUCTION TO 50% | 2014-01-29 | 2014-05-28 | 2022-06-26 | 2029-06-23
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | E34THPIER | EAST 34TH STREET PIER- NYU PARKING LOT REHAB | 7 | CONSTRUCTION TO 75% | 2014-05-29 | 2014-09-25 | 2022-06-26 | 2029-06-23
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | E34THPIER | EAST 34TH STREET PIER- NYU PARKING LOT REHAB | 8 | ORIGINAL EQUIP & FURNISHING | 2014-09-26 | 2014-12-24 | 2022-06-26 | 2029-06-23
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | E34THPIER | EAST 34TH STREET PIER- NYU PARKING LOT REHAB | 9 | SUBSTANTIAL COMPLETION | 2014-12-25 | 2015-02-22 | 2022-06-26 | 2029-06-23
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | E34THPIER | EAST 34TH STREET PIER- NYU PARKING LOT REHAB | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-02-23 | 2015-03-24 | 2022-06-26 | 2029-06-23
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | EASTPLAZA | East River Plaza | 1 | DESIGN | 2005-01-01 | 2005-01-20 | 2009-01-01 | 2009-01-20
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | EASTPLAZA | East River Plaza | 2 | BID AWARD AND REGISTER CONTRCT | 2005-01-21 | 2005-02-04 | 2009-01-21 | 2009-02-04
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | EASTPLAZA | East River Plaza | 3 | CONSTRUCTION | 2005-02-05 | 2007-06-30 | 2009-02-05 | 2020-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | EASTPLAZA | East River Plaza | 4 | ORIGINAL EQUIP & FURNISHING | 2007-07-01 | 2007-06-30 | 2020-07-01 | 2020-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | EASTPLAZA | East River Plaza | 5 | SUBSTANTIAL COMPLETION | 2007-07-01 | 2007-06-30 | 2020-07-01 | 2020-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | EASTPLAZA | East River Plaza | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2007-07-01 | 2007-07-05 | 2020-07-01 | 2029-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | EDCLUMP | EDC Lump Sum | 1 | DESIGN | 2019-07-01 | 2019-07-20 | 2019-07-01 | 2019-07-20
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | EDCLUMP | EDC Lump Sum | 2 | BID AWARD AND REGISTER CONTRCT | 2019-07-21 | 2019-08-04 | 2019-07-21 | 2019-08-04
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | EDCLUMP | EDC Lump Sum | 3 | CONSTRUCTION | 2019-08-05 | 2019-09-08 | 2019-08-05 | 2019-09-08
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | EDCLUMP | EDC Lump Sum | 4 | ORIGINAL EQUIP & FURNISHING | 2019-09-09 | 2019-09-18 | 2019-09-09 | 2019-09-18
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | EDCLUMP | EDC Lump Sum | 5 | SUBSTANTIAL COMPLETION | 2019-09-19 | 2019-10-03 | 2019-09-19 | 2019-10-03
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | EDCLUMP | EDC Lump Sum | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-10-04 | 2024-10-08 | 2019-10-04 | 2024-10-08
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | EDMFPM | FERRY PIER AT DYCKMAN MARINA | 1 | DESIGN | 2017-06-30 | 2017-07-19 | 2017-06-30 | 2017-07-19
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | EDMFPM | FERRY PIER AT DYCKMAN MARINA | 2 | BID AWARD AND REGISTER CONTRCT | 2017-07-20 | 2017-08-03 | 2017-07-20 | 2017-08-03
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | EDMFPM | FERRY PIER AT DYCKMAN MARINA | 3 | CONSTRUCTION | 2017-08-04 | 2017-09-07 | 2017-08-04 | 2017-09-07
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | EDMFPM | FERRY PIER AT DYCKMAN MARINA | 4 | ORIGINAL EQUIP & FURNISHING | 2017-09-08 | 2017-09-17 | 2017-09-08 | 2017-09-17
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | EDMFPM | FERRY PIER AT DYCKMAN MARINA | 5 | SUBSTANTIAL COMPLETION | 2017-09-18 | 2017-10-02 | 2017-09-18 | 2017-10-02
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | EDMFPM | FERRY PIER AT DYCKMAN MARINA | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-10-03 | 2020-06-30 | 2017-10-03 | 2028-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | ERIVERSPS | East River Science Park - Street work | 1 | DESIGN | 2008-04-01 | 2009-04-20 | 2011-06-18 | 2011-11-18
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | ERIVERSPS | East River Science Park - Street work | 2 | BID AWARD AND REGISTER CONTRCT | 2009-04-21 | 2009-04-20 | 2011-11-19 | 2012-02-17
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | ERIVERSPS | East River Science Park - Street work | 3 | CONSTRUCTION | 2009-04-21 | 2009-04-20 | 2012-02-18 | 2022-03-02
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | ERIVERSPS | East River Science Park - Street work | 4 | ORIGINAL EQUIP & FURNISHING | 2009-04-21 | 2009-04-20 | 2022-03-03 | 2022-03-02
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | ERIVERSPS | East River Science Park - Street work | 5 | SUBSTANTIAL COMPLETION | 2009-04-21 | 2009-04-20 | 2022-03-03 | 2022-03-02
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | ERIVERSPS | East River Science Park - Street work | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2009-04-21 | 2009-04-25 | 2022-03-03 | 2029-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | ERVRWALL | East River Seawall Rehabilitation (BMB to Pier 16) | 1 | DESIGN | 2016-01-01 | 2018-06-30 | 2016-01-01 | 2018-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | ERVRWALL | East River Seawall Rehabilitation (BMB to Pier 16) | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-01 | 2018-06-30 | 2018-07-01 | 2018-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | ERVRWALL | East River Seawall Rehabilitation (BMB to Pier 16) | 3 | CONSTRUCTION | 2018-07-01 | 2021-06-30 | 2018-07-01 | 2021-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | ERVRWALL | East River Seawall Rehabilitation (BMB to Pier 16) | 4 | ORIGINAL EQUIP & FURNISHING | 2021-07-01 | 2021-06-30 | 2021-07-01 | 2021-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | ERVRWALL | East River Seawall Rehabilitation (BMB to Pier 16) | 5 | SUBSTANTIAL COMPLETION | 2021-07-01 | 2021-06-30 | 2021-07-01 | 2021-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | ERVRWALL | East River Seawall Rehabilitation (BMB to Pier 16) | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-07-01 | 2021-07-05 | 2021-07-01 | 2029-06-28
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISBL20 | Governors Island - Building 20 Nolan Park Renovation | 1 | DEVELOP SCOPE | 2018-10-01 | 2019-08-31 | 2018-10-01 | 2019-08-31
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISBL20 | Governors Island - Building 20 Nolan Park Renovation | 2 | PRELIMINARY DESIGN | 2018-10-01 | 2019-08-31 | 2018-10-01 | 2019-08-31
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISBL20 | Governors Island - Building 20 Nolan Park Renovation | 3 | FINAL DESIGN | 2018-10-01 | 2019-08-31 | 2018-10-01 | 2019-08-31
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISBL20 | Governors Island - Building 20 Nolan Park Renovation | 4 | BID AWARD AND REGISTER CONTRCT | 2019-09-01 | 2019-10-31 | 2019-09-01 | 2019-10-31
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISBL20 | Governors Island - Building 20 Nolan Park Renovation | 5 | CONSTRUCTION TO 25% | 2019-11-01 | 2020-01-31 | 2019-11-01 | 2020-01-31
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISBL20 | Governors Island - Building 20 Nolan Park Renovation | 6 | CONSTRUCTION TO 50% | 2020-02-01 | 2020-03-31 | 2020-02-01 | 2020-03-31
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISBL20 | Governors Island - Building 20 Nolan Park Renovation | 7 | CONSTRUCTION TO 75% | 2020-04-01 | 2020-05-31 | 2020-04-01 | 2022-05-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISBL20 | Governors Island - Building 20 Nolan Park Renovation | 8 | ORIGINAL EQUIP & FURNISHING | 2020-06-01 | 2020-06-30 | 2022-05-31 | 2022-06-29
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISBL20 | Governors Island - Building 20 Nolan Park Renovation | 9 | SUBSTANTIAL COMPLETION | 2020-07-01 | 2020-07-31 | 2022-06-30 | 2022-07-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISBL20 | Governors Island - Building 20 Nolan Park Renovation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-08-01 | 2020-08-31 | 2022-07-31 | 2022-08-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISBLD2 | Governors Island Building Stabilization | 1 | DESIGN | 2016-07-01 | 2016-07-20 | 2019-07-02 | 2019-07-21
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISBLD2 | Governors Island Building Stabilization | 2 | BID AWARD AND REGISTER CONTRCT | 2016-07-21 | 2016-08-04 | 2019-07-22 | 2019-08-05
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISBLD2 | Governors Island Building Stabilization | 3 | CONSTRUCTION | 2016-08-05 | 2016-09-08 | 2019-08-06 | 2019-09-09
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISBLD2 | Governors Island Building Stabilization | 4 | ORIGINAL EQUIP & FURNISHING | 2016-09-09 | 2016-09-18 | 2019-09-10 | 2019-09-19
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISBLD2 | Governors Island Building Stabilization | 5 | SUBSTANTIAL COMPLETION | 2016-09-19 | 2016-10-03 | 2019-09-20 | 2019-10-04
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISBLD2 | Governors Island Building Stabilization | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-10-04 | 2016-10-08 | 2019-10-05 | 2021-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISBLDG | Governors Island Building Stabilization | 1 | DESIGN | 2016-07-01 | 2016-07-20 | 2016-09-01 | 2017-10-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISBLDG | Governors Island Building Stabilization | 2 | BID AWARD AND REGISTER CONTRCT | 2016-07-21 | 2016-08-04 | 2017-11-01 | 2018-01-31
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISBLDG | Governors Island Building Stabilization | 3 | CONSTRUCTION | 2016-08-05 | 2016-09-08 | 2018-02-01 | 2019-08-31
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISBLDG | Governors Island Building Stabilization | 4 | ORIGINAL EQUIP & FURNISHING | 2016-09-09 | 2016-09-18 | 2019-09-01 | 2019-09-02
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISBLDG | Governors Island Building Stabilization | 5 | SUBSTANTIAL COMPLETION | 2016-09-19 | 2016-10-03 | 2019-09-01 | 2019-09-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISBLDG | Governors Island Building Stabilization | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-10-04 | 2016-10-08 | 2019-10-01 | 2021-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISBMB2 | Governors Island BMB Slip5/6 Pile Cluster&Slip 6/7FenderRack | 1 | DESIGN | 2018-07-01 | 2018-07-20 | 2018-07-01 | 2019-03-31
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISBMB2 | Governors Island BMB Slip5/6 Pile Cluster&Slip 6/7FenderRack | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-21 | 2018-08-04 | 2019-04-01 | 2019-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISBMB2 | Governors Island BMB Slip5/6 Pile Cluster&Slip 6/7FenderRack | 3 | CONSTRUCTION | 2018-08-05 | 2018-09-08 | 2019-07-01 | 2020-01-31
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISBMB2 | Governors Island BMB Slip5/6 Pile Cluster&Slip 6/7FenderRack | 4 | ORIGINAL EQUIP & FURNISHING | 2018-09-09 | 2018-09-18 | 2019-08-01 | 2020-01-31
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISBMB2 | Governors Island BMB Slip5/6 Pile Cluster&Slip 6/7FenderRack | 5 | SUBSTANTIAL COMPLETION | 2018-09-19 | 2018-10-03 | 2020-02-01 | 2021-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISBMB2 | Governors Island BMB Slip5/6 Pile Cluster&Slip 6/7FenderRack | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-10-04 | 2018-10-08 | 2020-02-01 | 2021-02-01
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISBMBG | Governors Island BMB SLIP 6 & SLIP 7 GANTRIES | 1 | DESIGN | 2019-07-01 | 2019-08-31 | 2019-07-01 | 2019-08-31
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISBMBG | Governors Island BMB SLIP 6 & SLIP 7 GANTRIES | 2 | BID AWARD AND REGISTER CONTRCT | 2019-09-01 | 2019-12-31 | 2019-09-01 | 2019-12-31
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISBMBG | Governors Island BMB SLIP 6 & SLIP 7 GANTRIES | 3 | CONSTRUCTION | 2020-02-01 | 2020-05-31 | 2020-02-01 | 2020-05-31
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISBMBG | Governors Island BMB SLIP 6 & SLIP 7 GANTRIES | 4 | ORIGINAL EQUIP & FURNISHING | 2020-02-01 | 2020-05-31 | 2020-02-01 | 2020-05-31
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISBMBG | Governors Island BMB SLIP 6 & SLIP 7 GANTRIES | 5 | SUBSTANTIAL COMPLETION | 2020-06-01 | 2020-06-30 | 2020-06-01 | 2020-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISBMBG | Governors Island BMB SLIP 6 & SLIP 7 GANTRIES | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-07-01 | 2020-08-31 | 2020-07-01 | 2020-08-31
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISBTRL | Governors Island Trailer Bathroom | 2 | BID AWARD AND REGISTER CONTRCT | 2018-09-01 | 2018-11-30 | 2018-09-01 | 2018-11-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISBTRL | Governors Island Trailer Bathroom | 3 | CONSTRUCTION | 2018-12-01 | 2019-03-31 | 2018-12-01 | 2019-03-31
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISBTRL | Governors Island Trailer Bathroom | 4 | ORIGINAL EQUIP & FURNISHING | 2018-12-01 | 2019-03-31 | 2018-12-01 | 2019-03-31
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISBTRL | Governors Island Trailer Bathroom | 5 | SUBSTANTIAL COMPLETION | 2019-04-01 | 2019-06-30 | 2019-04-01 | 2019-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISBTRL | Governors Island Trailer Bathroom | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-05-01 | 2019-06-30 | 2019-05-01 | 2019-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISELE2 | Governors Island Electric Projects | 1 | DESIGN | 2017-10-01 | 2018-02-28 | 2017-10-01 | 2018-02-28
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISELE2 | Governors Island Electric Projects | 2 | BID AWARD AND REGISTER CONTRCT | 2018-03-01 | 2019-05-31 | 2018-03-01 | 2019-05-31
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISELE2 | Governors Island Electric Projects | 3 | CONSTRUCTION | 2019-06-01 | 2020-06-30 | 2019-06-01 | 2020-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISELE2 | Governors Island Electric Projects | 4 | ORIGINAL EQUIP & FURNISHING | 2019-06-01 | 2020-06-30 | 2019-06-01 | 2020-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISELE2 | Governors Island Electric Projects | 5 | SUBSTANTIAL COMPLETION | 2020-07-01 | 2020-07-31 | 2020-07-01 | 2020-07-31
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISELE2 | Governors Island Electric Projects | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-08-01 | 2020-10-31 | 2020-08-01 | 2023-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISELEC | Governors Island Electrical Infrastructure | 2 | BID AWARD AND REGISTER CONTRCT | 2014-07-20 | 2014-08-03 | 2014-07-20 | 2014-08-03
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISELEC | Governors Island Electrical Infrastructure | 3 | CONSTRUCTION | 2014-08-04 | 2014-09-07 | 2014-08-04 | 2014-09-07
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISELEC | Governors Island Electrical Infrastructure | 4 | ORIGINAL EQUIP & FURNISHING | 2014-09-08 | 2014-09-17 | 2014-09-08 | 2014-09-17
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISELEC | Governors Island Electrical Infrastructure | 5 | SUBSTANTIAL COMPLETION | 2014-09-18 | 2014-10-02 | 2014-09-18 | 2014-10-02
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISELEC | Governors Island Electrical Infrastructure | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-10-03 | 2014-10-07 | 2018-07-01 | 2019-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISLND2 | Governors Island Infrastructure Improvements | 1 | DESIGN | 2016-07-01 | 2016-07-20 | 2016-07-01 | 2021-04-11
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISLND2 | Governors Island Infrastructure Improvements | 2 | BID AWARD AND REGISTER CONTRCT | 2016-07-21 | 2016-08-04 | 2021-04-12 | 2021-04-26
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISLND2 | Governors Island Infrastructure Improvements | 3 | CONSTRUCTION | 2016-08-05 | 2016-09-08 | 2021-04-27 | 2021-05-31
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISLND2 | Governors Island Infrastructure Improvements | 4 | ORIGINAL EQUIP & FURNISHING | 2016-09-09 | 2016-09-18 | 2021-06-01 | 2021-06-10
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISLND2 | Governors Island Infrastructure Improvements | 5 | SUBSTANTIAL COMPLETION | 2016-09-19 | 2016-10-03 | 2021-06-11 | 2021-06-25
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISLND2 | Governors Island Infrastructure Improvements | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-10-04 | 2016-10-08 | 2021-06-26 | 2029-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISPUMP | Governors Island Sewage Pump House | 1 | DESIGN | 2016-07-01 | 2016-07-20 | 2017-07-01 | 2018-07-31
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISPUMP | Governors Island Sewage Pump House | 2 | BID AWARD AND REGISTER CONTRCT | 2016-07-21 | 2016-08-04 | 2019-02-01 | 2019-12-01
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISPUMP | Governors Island Sewage Pump House | 3 | CONSTRUCTION | 2016-08-05 | 2016-09-08 | 2020-01-01 | 2020-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISPUMP | Governors Island Sewage Pump House | 4 | ORIGINAL EQUIP & FURNISHING | 2016-09-09 | 2016-09-18 | 2020-06-01 | 2020-07-31
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISPUMP | Governors Island Sewage Pump House | 5 | SUBSTANTIAL COMPLETION | 2016-09-19 | 2016-10-03 | 2020-07-01 | 2020-08-31
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISPUMP | Governors Island Sewage Pump House | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-10-04 | 2016-10-08 | 2020-08-01 | 2020-09-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISSSN2 | Governors Island Soissons Dock 2 | 1 | DESIGN | 2016-07-01 | 2016-07-20 | 2019-03-01 | 2019-04-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISSSN2 | Governors Island Soissons Dock 2 | 2 | BID AWARD AND REGISTER CONTRCT | 2016-07-21 | 2016-08-04 | 2019-05-01 | 2019-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISSSN2 | Governors Island Soissons Dock 2 | 3 | CONSTRUCTION | 2016-08-05 | 2016-09-08 | 2019-10-01 | 2020-05-31
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISSSN2 | Governors Island Soissons Dock 2 | 4 | ORIGINAL EQUIP & FURNISHING | 2016-09-09 | 2016-09-18 | 2019-11-01 | 2020-05-31
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISSSN2 | Governors Island Soissons Dock 2 | 5 | SUBSTANTIAL COMPLETION | 2016-09-19 | 2016-10-03 | 2020-06-01 | 2020-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISSSN2 | Governors Island Soissons Dock 2 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-10-04 | 2016-10-08 | 2020-07-01 | 2020-08-31
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISUNUT | Governors Island Underground Utilities | 1 | DESIGN | 2017-06-30 | 2017-07-19 | 2017-06-30 | 2017-07-19
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISUNUT | Governors Island Underground Utilities | 2 | BID AWARD AND REGISTER CONTRCT | 2017-07-20 | 2017-08-03 | 2017-07-20 | 2017-08-03
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISUNUT | Governors Island Underground Utilities | 3 | CONSTRUCTION | 2017-08-04 | 2017-09-07 | 2017-08-04 | 2017-09-07
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISUNUT | Governors Island Underground Utilities | 4 | ORIGINAL EQUIP & FURNISHING | 2017-09-08 | 2017-09-17 | 2017-09-08 | 2017-09-17
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISUNUT | Governors Island Underground Utilities | 5 | SUBSTANTIAL COMPLETION | 2017-09-18 | 2017-10-02 | 2017-09-18 | 2017-10-02
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISUNUT | Governors Island Underground Utilities | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-10-03 | 2019-10-07 | 2017-10-03 | 2024-10-07
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISWLL2 | Governors Island Seawall Rehabilitation | 1 | DESIGN | 2016-07-01 | 2016-07-20 | 2021-07-01 | 2021-12-31
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISWLL2 | Governors Island Seawall Rehabilitation | 2 | BID AWARD AND REGISTER CONTRCT | 2016-07-21 | 2016-08-04 | 2022-01-01 | 2022-03-31
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISWLL2 | Governors Island Seawall Rehabilitation | 3 | CONSTRUCTION | 2016-08-05 | 2016-09-08 | 2022-04-01 | 2022-12-31
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISWLL2 | Governors Island Seawall Rehabilitation | 4 | ORIGINAL EQUIP & FURNISHING | 2016-09-09 | 2016-09-18 | 2022-04-01 | 2022-12-31
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISWLL2 | Governors Island Seawall Rehabilitation | 5 | SUBSTANTIAL COMPLETION | 2016-09-19 | 2016-10-03 | 2023-01-01 | 2023-04-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISWLL2 | Governors Island Seawall Rehabilitation | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-10-04 | 2016-10-08 | 2023-05-01 | 2023-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HARLEMRY | Harlem River Yards | 1 | DESIGN | 2015-06-30 | 2015-07-19 | 2013-06-30 | 2015-07-19
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HARLEMRY | Harlem River Yards | 2 | BID AWARD AND REGISTER CONTRCT | 2015-07-20 | 2015-08-03 | 2015-07-20 | 2015-08-03
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HARLEMRY | Harlem River Yards | 3 | CONSTRUCTION | 2015-08-04 | 2015-09-07 | 2015-08-04 | 2015-09-07
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HARLEMRY | Harlem River Yards | 4 | ORIGINAL EQUIP & FURNISHING | 2015-09-08 | 2015-09-17 | 2015-09-08 | 2015-09-17
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HARLEMRY | Harlem River Yards | 5 | SUBSTANTIAL COMPLETION | 2015-09-18 | 2015-10-02 | 2015-09-18 | 2015-10-02
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HARLEMRY | Harlem River Yards | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-10-03 | 2015-10-07 | 2017-06-26 | 2026-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HARLESPL | Harlem River Esplanade | 1 | DESIGN | 2005-01-01 | 2005-01-20 | 2011-05-31 | 2012-09-29
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HARLESPL | Harlem River Esplanade | 2 | BID AWARD AND REGISTER CONTRCT | 2005-01-21 | 2005-02-04 | 2012-09-30 | 2012-09-29
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HARLESPL | Harlem River Esplanade | 3 | CONSTRUCTION | 2005-02-05 | 2007-06-30 | 2007-01-01 | 2020-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HARLESPL | Harlem River Esplanade | 4 | ORIGINAL EQUIP & FURNISHING | 2007-07-01 | 2007-06-30 | 2020-07-01 | 2020-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HARLESPL | Harlem River Esplanade | 5 | SUBSTANTIAL COMPLETION | 2007-07-01 | 2007-06-30 | 2020-07-01 | 2020-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HARLESPL | Harlem River Esplanade | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2007-07-01 | 2007-07-05 | 2020-07-01 | 2024-07-05
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HARLMPIER | Harlem Area Piers & Bulkhead Stabilization | 1 | DESIGN | 1996-07-01 | 1996-07-20 | 2012-01-02 | 2013-10-01
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HARLMPIER | Harlem Area Piers & Bulkhead Stabilization | 2 | BID AWARD AND REGISTER CONTRCT | 1996-07-21 | 1996-08-04 | 2013-10-02 | 2013-10-01
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HARLMPIER | Harlem Area Piers & Bulkhead Stabilization | 3 | CONSTRUCTION | 1996-08-05 | 2007-06-30 | 2006-03-01 | 2007-10-01
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HARLMPIER | Harlem Area Piers & Bulkhead Stabilization | 4 | ORIGINAL EQUIP & FURNISHING | 2007-07-01 | 2007-06-30 | 2007-10-02 | 2020-10-01
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HARLMPIER | Harlem Area Piers & Bulkhead Stabilization | 5 | SUBSTANTIAL COMPLETION | 2007-07-01 | 2007-06-30 | 2020-10-02 | 2030-07-01
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HARLMPIER | Harlem Area Piers & Bulkhead Stabilization | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2007-07-01 | 2007-07-05 | 2030-07-02 | 2030-07-06
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HBMA4501B | 33rd Street West of 11th Avenue (Hudson Yards) | 1 | DEVELOP SCOPE | 2017-06-30 | 2018-06-29 | 0 | 0
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HBMA4501B | 33rd Street West of 11th Avenue (Hudson Yards) | 2 | DESIGN START | 2018-06-30 | 2022-06-28 | 2017-06-30 | 2018-06-29
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HBMA4501B | 33rd Street West of 11th Avenue (Hudson Yards) | 3 | CONSTRUCTION START | 2022-06-29 | 2024-06-27 | 2018-06-30 | 2022-06-28
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HBMA4501B | 33rd Street West of 11th Avenue (Hudson Yards) | 5 | CONSTRUCTION START | 2022-06-29 | 2024-06-27 | 2022-06-29 | 2024-06-27
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HBMA4501B | 33rd Street West of 11th Avenue (Hudson Yards) | 6 | DESIGN | 2022-06-29 | 2024-06-27 | 2024-06-28 | 2024-07-17
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HBMA4501B | 33rd Street West of 11th Avenue (Hudson Yards) | 7 | BID AWARD AND REGISTER CONTRCT | 2022-06-29 | 2024-06-27 | 2024-07-18 | 2024-08-01
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HBMA4501B | 33rd Street West of 11th Avenue (Hudson Yards) | 8 | CONSTRUCTION | 2022-06-29 | 2024-06-27 | 2024-08-02 | 2024-09-05
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HBMA4501B | 33rd Street West of 11th Avenue (Hudson Yards) | 9 | ORIGINAL EQUIP & FURNISHING | 2022-06-29 | 2024-06-27 | 2024-09-06 | 2024-09-15
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HBMA4501B | 33rd Street West of 11th Avenue (Hudson Yards) | 10 | SUBSTANTIAL COMPLETION | 2022-06-29 | 2024-06-27 | 2024-09-16 | 2024-09-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HBMA4501B | 33rd Street West of 11th Avenue (Hudson Yards) | 11 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-06-29 | 2024-06-27 | 2024-10-01 | 2024-10-05
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HIGHLINE | High Line | 1 | DEVELOP SCOPE | 2003-07-01 | 2003-09-28 | 2006-07-01 | 2006-07-20
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HIGHLINE | High Line | 2 | DESIGN | 2003-09-29 | 2003-12-27 | 2006-07-21 | 2006-08-04
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HIGHLINE | High Line | 3 | BID/ REGISTER CONTRACT | 2003-12-28 | 2004-03-26 | 2006-08-05 | 2024-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HIGHLINE | High Line | 4 | CONSTRUCTION | 2004-03-27 | 2005-03-26 | 2024-07-01 | 2024-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HIGHLINE | High Line | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2005-03-27 | 2006-03-26 | 2024-07-01 | 2024-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HIGHLINE | High Line | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2005-03-27 | 2006-03-26 | 2024-07-01 | 2024-07-05
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HIGHLINE2 | High Line - Section 2 | 1 | DESIGN | 2003-09-01 | 2003-09-20 | 2010-06-30 | 2010-12-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HIGHLINE2 | High Line - Section 2 | 2 | BID AWARD AND REGISTER CONTRCT | 2003-09-21 | 2003-10-05 | 2010-12-30 | 2011-03-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HIGHLINE2 | High Line - Section 2 | 3 | CONSTRUCTION | 2003-10-06 | 2008-07-30 | 2011-03-30 | 2011-12-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HIGHLINE2 | High Line - Section 2 | 4 | ORIGINAL EQUIP & FURNISHING | 2008-07-31 | 2008-07-30 | 2011-03-30 | 2011-12-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HIGHLINE2 | High Line - Section 2 | 5 | SUBSTANTIAL COMPLETION | 2008-07-31 | 2008-07-30 | 2011-03-30 | 2011-12-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HIGHLINE2 | High Line - Section 2 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-07-31 | 2008-08-04 | 2011-03-30 | 2024-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HILINEM&O | WHIT - High Line M&O Facility | 1 | DESIGN | 2010-01-01 | 2011-01-20 | 2010-01-01 | 2013-01-02
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HILINEM&O | WHIT - High Line M&O Facility | 2 | BID AWARD AND REGISTER CONTRCT | 2011-01-21 | 2011-01-20 | 2013-01-03 | 2013-01-02
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HILINEM&O | WHIT - High Line M&O Facility | 3 | CONSTRUCTION | 2011-01-21 | 2013-01-20 | 2013-01-03 | 2013-01-02
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HILINEM&O | WHIT - High Line M&O Facility | 4 | ORIGINAL EQUIP & FURNISHING | 2013-01-21 | 2013-01-20 | 2013-01-03 | 2013-01-02
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HILINEM&O | WHIT - High Line M&O Facility | 5 | SUBSTANTIAL COMPLETION | 2013-01-21 | 2013-01-20 | 2013-01-03 | 2013-01-02
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HILINEM&O | WHIT - High Line M&O Facility | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-01-21 | 2013-01-25 | 2013-01-03 | 2024-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HL82PHL | DOHMH PHL BUILDING CONSTRUCTION | 1 | DESIGN | 2018-06-10 | 2019-11-01 | 2018-06-10 | 2019-11-01
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HL82PHL | DOHMH PHL BUILDING CONSTRUCTION | 2 | CONSTRUCTION | 2019-11-02 | 2024-10-30 | 2019-11-02 | 2024-10-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HL82PHL | DOHMH PHL BUILDING CONSTRUCTION | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-10-31 | 2025-01-28 | 2024-10-31 | 2025-01-28
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HWD10214 | Hudson Sq Streetscape Improvements | 1 | DEVELOP SCOPE | 2015-06-01 | 2015-08-29 | 2016-06-01 | 2016-06-20
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HWD10214 | Hudson Sq Streetscape Improvements | 2 | PRELIMINARY DESIGN | 2015-08-30 | 2015-12-27 | 2016-06-21 | 2016-07-05
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HWD10214 | Hudson Sq Streetscape Improvements | 3 | FINAL DESIGN | 2015-12-28 | 2016-06-24 | 2016-07-06 | 2016-08-09
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HWD10214 | Hudson Sq Streetscape Improvements | 4 | BID AWARD AND REGISTER CONTRCT | 2016-06-25 | 2016-09-22 | 2016-08-10 | 2022-08-19
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HWD10214 | Hudson Sq Streetscape Improvements | 5 | CONSTRUCTION TO 25% | 2016-09-23 | 2017-01-20 | 2022-08-20 | 2022-09-03
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HWD10214 | Hudson Sq Streetscape Improvements | 6 | CONSTRUCTION TO 50% | 2017-01-21 | 2017-05-20 | 2022-09-04 | 2022-09-08
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HWD10214 | Hudson Sq Streetscape Improvements | 7 | CONSTRUCTION TO 75% | 2017-05-21 | 2017-09-17 | 2022-09-04 | 2022-09-08
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HWD10214 | Hudson Sq Streetscape Improvements | 8 | ORIGINAL EQUIP & FURNISHING | 2017-09-18 | 2017-12-16 | 2022-09-04 | 2022-09-08
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HWD10214 | Hudson Sq Streetscape Improvements | 9 | SUBSTANTIAL COMPLETION | 2017-12-17 | 2018-02-14 | 2022-09-04 | 2022-09-08
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HWD10214 | Hudson Sq Streetscape Improvements | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-02-15 | 2018-03-16 | 2022-09-04 | 2022-09-08
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HYDCBLVD | HYDC - MID-BLOCK BLVD AND CROSS STREETS-HUDSON YARD VICINITY | 1 | DESIGN | 2010-06-30 | 2010-07-19 | 2010-06-01 | 2013-07-14
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HYDCBLVD | HYDC - MID-BLOCK BLVD AND CROSS STREETS-HUDSON YARD VICINITY | 2 | BID AWARD AND REGISTER CONTRCT | 2010-07-20 | 2010-08-03 | 2013-07-15 | 2013-07-29
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HYDCBLVD | HYDC - MID-BLOCK BLVD AND CROSS STREETS-HUDSON YARD VICINITY | 3 | CONSTRUCTION | 2010-08-04 | 2013-06-30 | 2013-07-30 | 2020-06-25
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HYDCBLVD | HYDC - MID-BLOCK BLVD AND CROSS STREETS-HUDSON YARD VICINITY | 4 | ORIGINAL EQUIP & FURNISHING | 2013-07-01 | 2013-06-30 | 2020-06-26 | 2020-06-25
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HYDCBLVD | HYDC - MID-BLOCK BLVD AND CROSS STREETS-HUDSON YARD VICINITY | 5 | SUBSTANTIAL COMPLETION | 2013-07-01 | 2013-06-30 | 2020-06-26 | 2020-06-25
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HYDCBLVD | HYDC - MID-BLOCK BLVD AND CROSS STREETS-HUDSON YARD VICINITY | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-07-01 | 2013-07-05 | 2020-06-26 | 2029-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | INTREPIDC | FA - Intrepid Museum Foundation - cooling tower | 1 | DESIGN | 2015-06-30 | 2015-07-19 | 2019-03-23 | 2019-04-11
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | INTREPIDC | FA - Intrepid Museum Foundation - cooling tower | 2 | BID AWARD AND REGISTER CONTRCT | 2015-07-20 | 2015-08-03 | 2019-04-12 | 2019-04-26
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | INTREPIDC | FA - Intrepid Museum Foundation - cooling tower | 3 | CONSTRUCTION | 2015-08-04 | 2015-09-07 | 2019-04-27 | 2019-05-31
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | INTREPIDC | FA - Intrepid Museum Foundation - cooling tower | 4 | ORIGINAL EQUIP & FURNISHING | 2015-09-08 | 2015-09-17 | 2019-06-01 | 2019-06-10
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | INTREPIDC | FA - Intrepid Museum Foundation - cooling tower | 5 | SUBSTANTIAL COMPLETION | 2015-09-18 | 2015-10-02 | 2019-06-11 | 2019-06-25
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | INTREPIDC | FA - Intrepid Museum Foundation - cooling tower | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-10-03 | 2015-10-07 | 2019-06-26 | 2029-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | JULIABLCC | Julia de Burgos Latino Cultural Center | 1 | DESIGN | 2005-01-01 | 2005-01-20 | 2001-12-08 | 2002-03-10
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | JULIABLCC | Julia de Burgos Latino Cultural Center | 2 | BID AWARD AND REGISTER CONTRCT | 2005-01-21 | 2007-02-04 | 2002-03-11 | 2002-03-10
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | JULIABLCC | Julia de Burgos Latino Cultural Center | 3 | CONSTRUCTION | 2007-02-05 | 2007-02-04 | 2006-09-01 | 2017-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | JULIABLCC | Julia de Burgos Latino Cultural Center | 4 | ORIGINAL EQUIP & FURNISHING | 2007-02-05 | 2007-02-04 | 2017-07-01 | 2017-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | JULIABLCC | Julia de Burgos Latino Cultural Center | 5 | SUBSTANTIAL COMPLETION | 2007-02-05 | 2007-02-04 | 2017-07-01 | 2017-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | JULIABLCC | Julia de Burgos Latino Cultural Center | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2007-02-05 | 2007-02-09 | 2017-07-01 | 2024-11-27
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | JULIABREN | JULIA DE BURGOS CULTURAL CENTER RENOVATIONS | 1 | DESIGN | 2016-01-01 | 2018-06-30 | 2016-01-01 | 2018-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | JULIABREN | JULIA DE BURGOS CULTURAL CENTER RENOVATIONS | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-01 | 2018-06-30 | 2018-07-01 | 2018-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | JULIABREN | JULIA DE BURGOS CULTURAL CENTER RENOVATIONS | 3 | CONSTRUCTION | 2018-07-01 | 2021-06-30 | 2018-07-01 | 2021-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | JULIABREN | JULIA DE BURGOS CULTURAL CENTER RENOVATIONS | 4 | ORIGINAL EQUIP & FURNISHING | 2021-07-01 | 2021-06-30 | 2021-07-01 | 2021-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | JULIABREN | JULIA DE BURGOS CULTURAL CENTER RENOVATIONS | 5 | SUBSTANTIAL COMPLETION | 2021-07-01 | 2021-06-30 | 2021-07-01 | 2021-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | JULIABREN | JULIA DE BURGOS CULTURAL CENTER RENOVATIONS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-07-01 | 2021-07-05 | 2021-07-01 | 2025-06-29
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LAMARQPLZ | La Marqueta Plaza Rehabilitation | 1 | DESIGN | 2017-07-01 | 2017-07-20 | 2017-07-01 | 2017-07-20
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LAMARQPLZ | La Marqueta Plaza Rehabilitation | 2 | BID AWARD AND REGISTER CONTRCT | 2017-07-21 | 2017-08-04 | 2017-07-21 | 2017-08-04
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LAMARQPLZ | La Marqueta Plaza Rehabilitation | 3 | CONSTRUCTION | 2017-08-05 | 2017-09-08 | 2017-08-05 | 2017-09-08
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LAMARQPLZ | La Marqueta Plaza Rehabilitation | 4 | ORIGINAL EQUIP & FURNISHING | 2017-09-09 | 2017-09-18 | 2017-09-09 | 2017-09-18
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LAMARQPLZ | La Marqueta Plaza Rehabilitation | 5 | SUBSTANTIAL COMPLETION | 2017-09-19 | 2017-10-03 | 2017-09-19 | 2017-10-03
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LAMARQPLZ | La Marqueta Plaza Rehabilitation | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-10-04 | 2017-10-08 | 2017-10-04 | 2020-10-08
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LAMARQUE2 | La Marqueta - Kitchen Incubator | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-01-21 | 2014-01-25 | 2014-01-21 | 2014-01-25
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LAMARQUE3 | La Marqueta (Hot Bread Kitchen) | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-01 | 2018-06-30 | 2018-07-01 | 2018-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LAMARQUE3 | La Marqueta (Hot Bread Kitchen) | 3 | CONSTRUCTION | 2018-07-01 | 2021-06-30 | 2018-07-01 | 2021-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LAMARQUE3 | La Marqueta (Hot Bread Kitchen) | 4 | ORIGINAL EQUIP & FURNISHING | 2021-07-01 | 2021-06-30 | 2021-07-01 | 2021-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LAMARQUE3 | La Marqueta (Hot Bread Kitchen) | 5 | SUBSTANTIAL COMPLETION | 2021-07-01 | 2021-06-30 | 2021-07-01 | 2021-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LAMARQUE3 | La Marqueta (Hot Bread Kitchen) | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-07-01 | 2021-07-05 | 2021-07-01 | 2021-07-05
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LAMARQUE4 | La Marqueta Building 4 Exterior Envelope Rehab | 1 | DESIGN | 2015-06-24 | 2015-07-13 | 2019-03-23 | 2019-04-11
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LAMARQUE4 | La Marqueta Building 4 Exterior Envelope Rehab | 2 | BID AWARD AND REGISTER CONTRCT | 2015-07-14 | 2015-07-28 | 2019-04-12 | 2019-04-26
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LAMARQUE4 | La Marqueta Building 4 Exterior Envelope Rehab | 3 | CONSTRUCTION | 2015-07-29 | 2015-09-01 | 2019-04-27 | 2019-05-31
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LAMARQUE4 | La Marqueta Building 4 Exterior Envelope Rehab | 4 | ORIGINAL EQUIP & FURNISHING | 2015-09-02 | 2015-09-11 | 2019-06-01 | 2019-06-10
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LAMARQUE4 | La Marqueta Building 4 Exterior Envelope Rehab | 5 | SUBSTANTIAL COMPLETION | 2015-09-12 | 2015-09-26 | 2019-06-11 | 2019-06-25
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LAMARQUE4 | La Marqueta Building 4 Exterior Envelope Rehab | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-09-27 | 2015-10-01 | 2019-06-26 | 2025-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LAMARQUET | La Marqueta | 2 | BID AWARD AND REGISTER CONTRCT | 2005-01-21 | 2007-02-04 | 2005-01-21 | 2007-02-04
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LAMARQUET | La Marqueta | 3 | CONSTRUCTION | 2007-02-05 | 2007-02-04 | 2007-02-05 | 2007-02-04
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LAMARQUET | La Marqueta | 4 | ORIGINAL EQUIP & FURNISHING | 2007-02-05 | 2007-02-04 | 2007-02-05 | 2007-02-04
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LAMARQUET | La Marqueta | 5 | SUBSTANTIAL COMPLETION | 2007-02-05 | 2007-02-04 | 2007-02-05 | 2007-02-04
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LAMARQUET | La Marqueta | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2007-02-05 | 2007-02-09 | 2007-02-05 | 2017-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LCNPARK | Lower Concourse Park | 1 | DESIGN | 2019-07-01 | 2019-07-20 | 2019-07-01 | 2019-07-20
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LCNPARK | Lower Concourse Park | 2 | BID AWARD AND REGISTER CONTRCT | 2019-07-21 | 2019-08-04 | 2019-07-21 | 2019-08-04
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LCNPARK | Lower Concourse Park | 3 | CONSTRUCTION | 2019-08-05 | 2019-09-08 | 2019-08-05 | 2019-09-08
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LCNPARK | Lower Concourse Park | 4 | ORIGINAL EQUIP & FURNISHING | 2019-09-09 | 2019-09-18 | 2019-09-09 | 2019-09-18
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LCNPARK | Lower Concourse Park | 5 | SUBSTANTIAL COMPLETION | 2019-09-19 | 2019-10-03 | 2019-09-19 | 2019-10-03
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LCNPARK | Lower Concourse Park | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-10-04 | 2022-10-08 | 2019-10-04 | 2025-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LIFESCIEN | LIFE SCIENCES HUB | 1 | DESIGN | 2017-07-01 | 2017-07-20 | 2021-03-23 | 2021-04-11
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LIFESCIEN | LIFE SCIENCES HUB | 2 | BID AWARD AND REGISTER CONTRCT | 2017-07-21 | 2017-08-04 | 2021-04-12 | 2021-04-26
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LIFESCIEN | LIFE SCIENCES HUB | 3 | CONSTRUCTION | 2017-08-05 | 2017-09-08 | 2021-04-27 | 2021-05-31
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LIFESCIEN | LIFE SCIENCES HUB | 4 | ORIGINAL EQUIP & FURNISHING | 2017-09-09 | 2017-09-18 | 2021-06-01 | 2021-06-10
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LIFESCIEN | LIFE SCIENCES HUB | 5 | SUBSTANTIAL COMPLETION | 2017-09-19 | 2017-10-03 | 2021-06-11 | 2021-06-25
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LIFESCIEN | LIFE SCIENCES HUB | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-10-04 | 2017-10-08 | 2021-06-26 | 2022-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LMAQFACIL | La Marqueta GFNYC, IBZ & NYCEDC Operations Facility | 1 | DESIGN | 2014-11-13 | 2015-04-30 | 2014-11-13 | 2015-04-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LMAQFACIL | La Marqueta GFNYC, IBZ & NYCEDC Operations Facility | 2 | BID AWARD AND REGISTER CONTRCT | 2015-05-01 | 2015-04-30 | 2015-05-01 | 2015-04-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LMAQFACIL | La Marqueta GFNYC, IBZ & NYCEDC Operations Facility | 3 | CONSTRUCTION | 2015-05-01 | 2015-12-31 | 2015-05-01 | 2015-12-31
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LMAQFACIL | La Marqueta GFNYC, IBZ & NYCEDC Operations Facility | 4 | ORIGINAL EQUIP & FURNISHING | 2016-01-01 | 2015-12-31 | 2016-01-01 | 2015-12-31
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LMAQFACIL | La Marqueta GFNYC, IBZ & NYCEDC Operations Facility | 5 | SUBSTANTIAL COMPLETION | 2016-01-01 | 2015-12-31 | 2016-01-01 | 2015-12-31
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LMAQFACIL | La Marqueta GFNYC, IBZ & NYCEDC Operations Facility | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-01-01 | 2016-01-05 | 2016-01-01 | 2029-01-05
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LNEA16125 | 125th St: Interior and Exterior Comprehensive Renovation | 1 | DESIGN | 2016-08-01 | 2017-01-27 | 2016-08-01 | 2017-01-27
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LNEA16125 | 125th St: Interior and Exterior Comprehensive Renovation | 2 | BID AWARD AND REGISTER CONTRCT | 2017-01-28 | 2017-04-27 | 2017-01-28 | 2017-04-27
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LNEA16125 | 125th St: Interior and Exterior Comprehensive Renovation | 3 | CONSTRUCTION | 2017-04-28 | 2018-04-27 | 2017-04-28 | 2020-04-27
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LNEA16125 | 125th St: Interior and Exterior Comprehensive Renovation | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-04-28 | 2019-02-21 | 2020-04-28 | 2022-02-21
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LNEA16FWT | FORT WASHINGTON: MAJOR RENOVATION | 1 | DESIGN | 2016-08-01 | 2017-01-27 | 2016-08-01 | 2017-01-27
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LNEA16FWT | FORT WASHINGTON: MAJOR RENOVATION | 2 | BID AWARD AND REGISTER CONTRCT | 2017-01-28 | 2017-04-27 | 2017-01-28 | 2017-04-27
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LNEA16FWT | FORT WASHINGTON: MAJOR RENOVATION | 3 | CONSTRUCTION | 2017-04-28 | 2018-04-27 | 2017-04-28 | 2020-04-27
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LNEA16FWT | FORT WASHINGTON: MAJOR RENOVATION | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-04-28 | 2019-02-21 | 2020-04-28 | 2022-02-21
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | MANHGREEN | Manhattan Greenway | 1 | DESIGN | 2017-06-30 | 2017-07-19 | 2017-06-30 | 2017-07-19
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | MANHGREEN | Manhattan Greenway | 2 | BID AWARD AND REGISTER CONTRCT | 2017-07-20 | 2017-08-03 | 2017-07-20 | 2017-08-03
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | MANHGREEN | Manhattan Greenway | 3 | CONSTRUCTION | 2017-08-04 | 2017-09-07 | 2017-08-04 | 2017-09-07
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | MANHGREEN | Manhattan Greenway | 4 | ORIGINAL EQUIP & FURNISHING | 2017-09-08 | 2017-09-17 | 2017-09-08 | 2017-09-17
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | MANHGREEN | Manhattan Greenway | 5 | SUBSTANTIAL COMPLETION | 2017-09-18 | 2017-10-02 | 2017-09-18 | 2017-10-02
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | MANHGREEN | Manhattan Greenway | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-10-03 | 2019-10-07 | 2017-10-03 | 2028-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | MCRUISE | Manhattan Cruise Terminal Improvements to Pier 88, 90 | 1 | DESIGN | 2017-06-30 | 2017-07-19 | 2017-06-30 | 2017-07-19
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | MCRUISE | Manhattan Cruise Terminal Improvements to Pier 88, 90 | 2 | BID AWARD AND REGISTER CONTRCT | 2017-07-20 | 2017-08-03 | 2017-07-20 | 2017-08-03
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | MCRUISE | Manhattan Cruise Terminal Improvements to Pier 88, 90 | 3 | CONSTRUCTION | 2017-08-04 | 2017-09-07 | 2017-08-04 | 2017-09-07
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | MCRUISE | Manhattan Cruise Terminal Improvements to Pier 88, 90 | 4 | ORIGINAL EQUIP & FURNISHING | 2017-09-08 | 2017-09-17 | 2017-09-08 | 2017-09-17
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | MCRUISE | Manhattan Cruise Terminal Improvements to Pier 88, 90 | 5 | SUBSTANTIAL COMPLETION | 2017-09-18 | 2017-10-02 | 2017-09-18 | 2017-10-02
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | MCRUISE | Manhattan Cruise Terminal Improvements to Pier 88, 90 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-10-03 | 2018-10-07 | 2017-10-03 | 2027-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | MCTFEND | MCT PIER 90 FENDERING | 1 | DESIGN | 2019-07-01 | 2019-07-20 | 2023-07-01 | 2023-07-20
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | MCTFEND | MCT PIER 90 FENDERING | 2 | BID AWARD AND REGISTER CONTRCT | 2019-07-21 | 2019-08-04 | 2023-07-21 | 2023-08-04
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | MCTFEND | MCT PIER 90 FENDERING | 3 | CONSTRUCTION | 2019-08-05 | 2019-09-08 | 2023-08-05 | 2023-09-08
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | MCTFEND | MCT PIER 90 FENDERING | 4 | ORIGINAL EQUIP & FURNISHING | 2019-09-09 | 2019-09-18 | 2023-09-09 | 2023-09-18
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | MCTFEND | MCT PIER 90 FENDERING | 5 | SUBSTANTIAL COMPLETION | 2019-09-19 | 2019-10-03 | 2023-09-19 | 2023-10-03
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | MCTFEND | MCT PIER 90 FENDERING | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-10-04 | 2023-10-08 | 2023-10-04 | 2029-10-08
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | MCTPLAT | Manhattan Cruise Terminal Inshore Platform Rehabilitation | 1 | DESIGN | 2016-01-01 | 2018-06-30 | 2016-01-01 | 2018-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | MCTPLAT | Manhattan Cruise Terminal Inshore Platform Rehabilitation | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-01 | 2018-06-30 | 2018-07-01 | 2018-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | MCTPLAT | Manhattan Cruise Terminal Inshore Platform Rehabilitation | 3 | CONSTRUCTION | 2018-07-01 | 2021-06-30 | 2018-07-01 | 2021-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | MCTPLAT | Manhattan Cruise Terminal Inshore Platform Rehabilitation | 4 | ORIGINAL EQUIP & FURNISHING | 2021-07-01 | 2021-06-30 | 2021-07-01 | 2021-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | MCTPLAT | Manhattan Cruise Terminal Inshore Platform Rehabilitation | 5 | SUBSTANTIAL COMPLETION | 2021-07-01 | 2021-06-30 | 2021-07-01 | 2021-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | MCTPLAT | Manhattan Cruise Terminal Inshore Platform Rehabilitation | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-07-01 | 2021-07-05 | 2021-07-01 | 2029-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | MCTROOF | Manhattan Cruise Terminal Roof and Viaduct Traffic Topping | 1 | DESIGN | 2016-01-01 | 2018-06-30 | 2016-01-01 | 2018-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | MCTROOF | Manhattan Cruise Terminal Roof and Viaduct Traffic Topping | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-01 | 2018-06-30 | 2018-07-01 | 2018-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | MCTROOF | Manhattan Cruise Terminal Roof and Viaduct Traffic Topping | 3 | CONSTRUCTION | 2018-07-01 | 2021-06-30 | 2018-07-01 | 2021-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | MCTROOF | Manhattan Cruise Terminal Roof and Viaduct Traffic Topping | 4 | ORIGINAL EQUIP & FURNISHING | 2021-07-01 | 2021-06-30 | 2021-07-01 | 2021-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | MCTROOF | Manhattan Cruise Terminal Roof and Viaduct Traffic Topping | 5 | SUBSTANTIAL COMPLETION | 2021-07-01 | 2021-06-30 | 2021-07-01 | 2021-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | MCTROOF | Manhattan Cruise Terminal Roof and Viaduct Traffic Topping | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-07-01 | 2021-07-05 | 2021-07-01 | 2024-07-05
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | MCTROOF2 | Manhattan Cruise Terminal Roof - Phase 2 - Pier 88 | 1 | DESIGN | 2016-01-01 | 2018-06-30 | 2016-01-01 | 2018-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | MCTROOF2 | Manhattan Cruise Terminal Roof - Phase 2 - Pier 88 | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-01 | 2018-06-30 | 2018-07-01 | 2018-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | MCTROOF2 | Manhattan Cruise Terminal Roof - Phase 2 - Pier 88 | 3 | CONSTRUCTION | 2018-07-01 | 2021-06-30 | 2018-07-01 | 2021-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | MCTROOF2 | Manhattan Cruise Terminal Roof - Phase 2 - Pier 88 | 4 | ORIGINAL EQUIP & FURNISHING | 2021-07-01 | 2021-06-30 | 2021-07-01 | 2021-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | MCTROOF2 | Manhattan Cruise Terminal Roof - Phase 2 - Pier 88 | 5 | SUBSTANTIAL COMPLETION | 2021-07-01 | 2021-06-30 | 2021-07-01 | 2021-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | MCTROOF2 | Manhattan Cruise Terminal Roof - Phase 2 - Pier 88 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-07-01 | 2021-07-05 | 2021-07-01 | 2024-07-05
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | MECAFIT | MECA FITNESS CENTER RENOVATION--FITNESS CENTER RENOVATION | 1 | DESIGN | 2017-07-01 | 2017-07-20 | 2019-03-23 | 2019-04-11
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | MECAFIT | MECA FITNESS CENTER RENOVATION--FITNESS CENTER RENOVATION | 2 | BID AWARD AND REGISTER CONTRCT | 2017-07-21 | 2017-08-04 | 2019-04-12 | 2019-04-26
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | MECAFIT | MECA FITNESS CENTER RENOVATION--FITNESS CENTER RENOVATION | 3 | CONSTRUCTION | 2017-08-05 | 2017-09-08 | 2019-04-27 | 2019-05-31
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | MECAFIT | MECA FITNESS CENTER RENOVATION--FITNESS CENTER RENOVATION | 4 | ORIGINAL EQUIP & FURNISHING | 2017-09-09 | 2017-09-18 | 2019-06-01 | 2019-06-10
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | MECAFIT | MECA FITNESS CENTER RENOVATION--FITNESS CENTER RENOVATION | 5 | SUBSTANTIAL COMPLETION | 2017-09-19 | 2017-10-03 | 2019-06-11 | 2019-06-25
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | MECAFIT | MECA FITNESS CENTER RENOVATION--FITNESS CENTER RENOVATION | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-10-04 | 2017-10-08 | 2019-06-26 | 2022-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-3HRGL | NDF - Harlem River Greenway Link - New Park Development | 1 | DESIGN | 2019-07-01 | 2019-07-20 | 2019-07-01 | 2019-07-20
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-3HRGL | NDF - Harlem River Greenway Link - New Park Development | 2 | BID AWARD AND REGISTER CONTRCT | 2019-07-21 | 2019-08-04 | 2019-07-21 | 2019-08-04
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-3HRGL | NDF - Harlem River Greenway Link - New Park Development | 3 | CONSTRUCTION | 2019-08-05 | 2019-09-08 | 2019-08-05 | 2019-09-08
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-3HRGL | NDF - Harlem River Greenway Link - New Park Development | 4 | ORIGINAL EQUIP & FURNISHING | 2019-09-09 | 2019-09-18 | 2019-09-09 | 2019-09-18
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-3HRGL | NDF - Harlem River Greenway Link - New Park Development | 5 | SUBSTANTIAL COMPLETION | 2019-09-19 | 2019-10-03 | 2019-09-19 | 2019-10-03
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-3HRGL | NDF - Harlem River Greenway Link - New Park Development | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-10-04 | 2019-10-08 | 2019-10-04 | 2023-10-08
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-LAMAR | La Marqueta Redevelopment | 1 | DESIGN | 2019-07-01 | 2019-07-20 | 2019-07-01 | 2019-07-20
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-LAMAR | La Marqueta Redevelopment | 2 | BID AWARD AND REGISTER CONTRCT | 2019-07-21 | 2019-08-04 | 2019-07-21 | 2019-08-04
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-LAMAR | La Marqueta Redevelopment | 3 | CONSTRUCTION | 2019-08-05 | 2019-09-08 | 2019-08-05 | 2019-09-08
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-LAMAR | La Marqueta Redevelopment | 4 | ORIGINAL EQUIP & FURNISHING | 2019-09-09 | 2019-09-18 | 2019-09-09 | 2019-09-18
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-LAMAR | La Marqueta Redevelopment | 5 | SUBSTANTIAL COMPLETION | 2019-09-19 | 2019-10-03 | 2019-09-19 | 2019-10-03
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-LAMAR | La Marqueta Redevelopment | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-10-04 | 2022-10-08 | 2019-10-04 | 2028-10-08
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-NWOOD | NDF - Inwood Greenway and New Parks Development | 1 | DESIGN | 2019-07-01 | 2019-07-20 | 2019-07-01 | 2019-07-20
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-NWOOD | NDF - Inwood Greenway and New Parks Development | 2 | BID AWARD AND REGISTER CONTRCT | 2019-07-21 | 2019-08-04 | 2019-07-21 | 2019-08-04
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-NWOOD | NDF - Inwood Greenway and New Parks Development | 3 | CONSTRUCTION | 2019-08-05 | 2019-09-08 | 2019-08-05 | 2019-09-08
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-NWOOD | NDF - Inwood Greenway and New Parks Development | 4 | ORIGINAL EQUIP & FURNISHING | 2019-09-09 | 2019-09-18 | 2019-09-09 | 2019-09-18
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-NWOOD | NDF - Inwood Greenway and New Parks Development | 5 | SUBSTANTIAL COMPLETION | 2019-09-19 | 2019-10-03 | 2019-09-19 | 2019-10-03
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-NWOOD | NDF - Inwood Greenway and New Parks Development | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-10-04 | 2021-10-08 | 2019-10-04 | 2028-10-08
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NONTDW | Nontraditional Employment for Women - Renovation of HQ | 1 | DESIGN | 2016-07-01 | 2016-07-20 | 2021-07-01 | 2021-07-20
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NONTDW | Nontraditional Employment for Women - Renovation of HQ | 2 | BID AWARD AND REGISTER CONTRCT | 2016-07-21 | 2016-08-04 | 2021-07-21 | 2021-08-04
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NONTDW | Nontraditional Employment for Women - Renovation of HQ | 3 | CONSTRUCTION | 2016-08-05 | 2016-09-08 | 2021-08-05 | 2021-09-08
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NONTDW | Nontraditional Employment for Women - Renovation of HQ | 4 | ORIGINAL EQUIP & FURNISHING | 2016-09-09 | 2016-09-18 | 2021-09-09 | 2021-09-18
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NONTDW | Nontraditional Employment for Women - Renovation of HQ | 5 | SUBSTANTIAL COMPLETION | 2016-09-19 | 2016-10-03 | 2021-09-19 | 2021-10-03
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NONTDW | Nontraditional Employment for Women - Renovation of HQ | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-10-04 | 2016-10-08 | 2021-10-04 | 2024-10-08
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NR COGEN | DEP: North River Cogeneration Plant, Hudson River Greenway | 1 | DESIGN | 2019-07-01 | 2019-07-20 | 2019-07-01 | 2019-07-20
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NR COGEN | DEP: North River Cogeneration Plant, Hudson River Greenway | 2 | BID AWARD AND REGISTER CONTRCT | 2019-07-21 | 2019-08-04 | 2019-07-21 | 2019-08-04
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NR COGEN | DEP: North River Cogeneration Plant, Hudson River Greenway | 3 | CONSTRUCTION | 2019-08-05 | 2019-09-08 | 2019-08-05 | 2019-09-08
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NR COGEN | DEP: North River Cogeneration Plant, Hudson River Greenway | 4 | ORIGINAL EQUIP & FURNISHING | 2019-09-09 | 2019-09-18 | 2019-09-09 | 2019-09-18
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NR COGEN | DEP: North River Cogeneration Plant, Hudson River Greenway | 5 | SUBSTANTIAL COMPLETION | 2019-09-19 | 2020-10-03 | 2019-09-19 | 2020-10-03
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NR COGEN | DEP: North River Cogeneration Plant, Hudson River Greenway | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-10-04 | 2020-10-08 | 2020-10-04 | 2022-10-08
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NYCFBARGE | New York City Ferry - Barge Expansion | 1 | DESIGN | 2019-07-01 | 2019-07-20 | 2019-07-01 | 2019-07-20
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NYCFBARGE | New York City Ferry - Barge Expansion | 2 | BID AWARD AND REGISTER CONTRCT | 2019-07-21 | 2019-08-04 | 2019-07-21 | 2019-08-04
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NYCFBARGE | New York City Ferry - Barge Expansion | 3 | CONSTRUCTION | 2019-08-05 | 2019-09-08 | 2019-08-05 | 2019-09-08
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NYCFBARGE | New York City Ferry - Barge Expansion | 4 | ORIGINAL EQUIP & FURNISHING | 2019-09-09 | 2019-09-18 | 2019-09-09 | 2019-09-18
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NYCFBARGE | New York City Ferry - Barge Expansion | 5 | SUBSTANTIAL COMPLETION | 2019-09-19 | 2021-10-03 | 2019-09-19 | 2021-10-03
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NYCFBARGE | New York City Ferry - Barge Expansion | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-10-04 | 2021-10-08 | 2021-10-04 | 2021-10-08
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NYCFVAPEX | New York City Ferry - VAP3 Expansion Vessels | 1 | DESIGN | 2019-07-01 | 2019-07-20 | 2019-07-01 | 2019-07-20
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NYCFVAPEX | New York City Ferry - VAP3 Expansion Vessels | 2 | BID AWARD AND REGISTER CONTRCT | 2019-07-21 | 2019-08-04 | 2019-07-21 | 2019-08-04
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NYCFVAPEX | New York City Ferry - VAP3 Expansion Vessels | 3 | CONSTRUCTION | 2019-08-05 | 2019-09-08 | 2019-08-05 | 2019-09-08
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NYCFVAPEX | New York City Ferry - VAP3 Expansion Vessels | 4 | ORIGINAL EQUIP & FURNISHING | 2019-09-09 | 2019-09-18 | 2019-09-09 | 2019-09-18
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NYCFVAPEX | New York City Ferry - VAP3 Expansion Vessels | 5 | SUBSTANTIAL COMPLETION | 2019-09-19 | 2021-10-03 | 2019-09-19 | 2021-10-03
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NYCFVAPEX | New York City Ferry - VAP3 Expansion Vessels | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-10-04 | 2021-10-08 | 2021-10-04 | 2021-10-08
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NYPDHRP76 | Hudson River Park- Segment 6- Pier 76 | 1 | DESIGN | 2018-07-01 | 2018-07-20 | 2018-07-01 | 2018-07-20
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NYPDHRP76 | Hudson River Park- Segment 6- Pier 76 | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-21 | 2018-08-04 | 2018-07-21 | 2018-08-04
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NYPDHRP76 | Hudson River Park- Segment 6- Pier 76 | 3 | CONSTRUCTION | 2018-08-05 | 2018-09-08 | 2018-08-05 | 2018-09-08
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NYPDHRP76 | Hudson River Park- Segment 6- Pier 76 | 4 | ORIGINAL EQUIP & FURNISHING | 2018-09-09 | 2018-09-18 | 2018-09-09 | 2018-09-18
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NYPDHRP76 | Hudson River Park- Segment 6- Pier 76 | 5 | SUBSTANTIAL COMPLETION | 2018-09-19 | 2018-10-03 | 2018-09-19 | 2018-10-03
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NYPDHRP76 | Hudson River Park- Segment 6- Pier 76 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-10-04 | 2018-10-08 | 2018-10-04 | 2028-10-08
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-301BATW | Battery Park - Wharf | 1 | DESIGN | 2015-07-01 | 2015-07-20 | 2015-07-01 | 2015-07-20
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-301BATW | Battery Park - Wharf | 2 | BID AWARD AND REGISTER CONTRCT | 2015-07-21 | 2015-08-04 | 2015-07-21 | 2015-08-04
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-301BATW | Battery Park - Wharf | 3 | CONSTRUCTION | 2015-08-05 | 2015-09-08 | 2015-08-05 | 2015-09-08
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-301BATW | Battery Park - Wharf | 4 | ORIGINAL EQUIP & FURNISHING | 2015-09-09 | 2015-09-18 | 2015-09-09 | 2015-09-18
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-301BATW | Battery Park - Wharf | 5 | SUBSTANTIAL COMPLETION | 2015-09-19 | 2015-10-03 | 2015-09-19 | 2015-10-03
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-301BATW | Battery Park - Wharf | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-10-04 | 2019-10-08 | 2015-10-04 | 2024-10-08
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-309RVP2 | RIVERSIDE PARK 79 ST BOAT BASIN: C DOCK | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-309RVP2 | RIVERSIDE PARK 79 ST BOAT BASIN: C DOCK | 2 | DESIGN | 2017-12-28 | 2019-12-27 | 2017-12-28 | 2019-12-27
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-309RVP2 | RIVERSIDE PARK 79 ST BOAT BASIN: C DOCK | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-309RVP2 | RIVERSIDE PARK 79 ST BOAT BASIN: C DOCK | 4 | CONSTRUCTION | 2020-09-23 | 2023-09-22 | 2020-09-23 | 2023-09-22
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-309RVP2 | RIVERSIDE PARK 79 ST BOAT BASIN: C DOCK | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-23 | 2025-09-21 | 2023-09-23 | 2025-09-21
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-311RAND | Randall's Island New Track and Field Center | 2 | BID AWARD AND REGISTER CONTRCT | 2000-09-21 | 2000-10-05 | 2001-10-02 | 2001-10-01
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-311RAND | Randall's Island New Track and Field Center | 3 | CONSTRUCTION | 2000-10-06 | 2007-07-01 | 2002-04-01 | 2011-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-311RAND | Randall's Island New Track and Field Center | 4 | ORIGINAL EQUIP & FURNISHING | 2007-07-02 | 2007-07-01 | 2011-07-01 | 2011-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-311RAND | Randall's Island New Track and Field Center | 5 | SUBSTANTIAL COMPLETION | 2007-07-02 | 2007-07-01 | 2011-07-01 | 2011-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-311RAND | Randall's Island New Track and Field Center | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2007-07-02 | 2007-07-06 | 2011-07-01 | 2011-07-05
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-3E103CG | FA - East 103rd street community garden | 1 | DEVELOP SCOPE | 2003-07-01 | 2003-09-28 | 2003-07-01 | 2003-07-20
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-3E103CG | FA - East 103rd street community garden | 2 | DESIGN | 2003-09-29 | 2003-12-27 | 2003-07-21 | 2003-08-04
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-3E103CG | FA - East 103rd street community garden | 3 | BID/ REGISTER CONTRACT | 2003-12-28 | 2004-03-26 | 2003-08-05 | 2003-09-08
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-3E103CG | FA - East 103rd street community garden | 4 | CONSTRUCTION | 2004-03-27 | 2005-03-26 | 2003-09-09 | 2003-09-18
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-3E103CG | FA - East 103rd street community garden | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2005-03-27 | 2006-03-26 | 2003-09-19 | 2003-10-03
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-3E103CG | FA - East 103rd street community garden | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2005-03-27 | 2006-03-26 | 2003-10-04 | 2023-10-08
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-3HIGHLL | FRIENDS OF THE HIGH LINE-LIFE SAFETY UPGRADES & CIRCULATION | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-3HIGHLL | FRIENDS OF THE HIGH LINE-LIFE SAFETY UPGRADES & CIRCULATION | 2 | DESIGN | 2017-12-28 | 2019-03-22 | 2017-12-28 | 2019-03-22
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-3HIGHLL | FRIENDS OF THE HIGH LINE-LIFE SAFETY UPGRADES & CIRCULATION | 3 | BID/ REGISTER CONTRACT | 2019-03-23 | 2019-12-17 | 2019-03-23 | 2019-12-17
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-3HIGHLL | FRIENDS OF THE HIGH LINE-LIFE SAFETY UPGRADES & CIRCULATION | 4 | CONSTRUCTION | 2019-12-18 | 2021-12-16 | 2019-12-18 | 2021-12-16
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-3HIGHLL | FRIENDS OF THE HIGH LINE-LIFE SAFETY UPGRADES & CIRCULATION | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-12-17 | 2022-12-16 | 2021-12-17 | 2022-12-16
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-3HILIN3 | Highline Phase 3 | 1 | DESIGN | 2016-01-01 | 2018-06-30 | 2016-01-01 | 2018-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-3HILIN3 | Highline Phase 3 | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-01 | 2018-06-30 | 2018-07-01 | 2018-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-3HILIN3 | Highline Phase 3 | 3 | CONSTRUCTION | 2018-07-01 | 2021-06-30 | 2018-07-01 | 2021-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-3HILIN3 | Highline Phase 3 | 4 | ORIGINAL EQUIP & FURNISHING | 2021-07-01 | 2021-06-30 | 2021-07-01 | 2021-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-3HILIN3 | Highline Phase 3 | 5 | SUBSTANTIAL COMPLETION | 2021-07-01 | 2021-06-30 | 2021-07-01 | 2021-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-3HILIN3 | Highline Phase 3 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-07-01 | 2021-07-05 | 2021-07-01 | 2021-07-05
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-3HRP132 | Harlem River Park 132-135 | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-3HRP132 | Harlem River Park 132-135 | 2 | DESIGN | 2017-12-28 | 2019-12-27 | 2017-12-28 | 2019-12-27
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-3HRP132 | Harlem River Park 132-135 | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-3HRP132 | Harlem River Park 132-135 | 4 | CONSTRUCTION | 2020-09-23 | 2022-09-22 | 2020-09-23 | 2022-09-22
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-3HRP132 | Harlem River Park 132-135 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-3RETWAL | Seawall and Henry Hudson Parkway | 1 | DESIGN | 2015-06-30 | 2015-07-19 | 2015-06-30 | 2015-07-19
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-3RETWAL | Seawall and Henry Hudson Parkway | 2 | BID AWARD AND REGISTER CONTRCT | 2015-07-20 | 2015-08-03 | 2015-07-20 | 2015-08-03
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-3RETWAL | Seawall and Henry Hudson Parkway | 3 | CONSTRUCTION | 2015-08-04 | 2015-09-07 | 2015-08-04 | 2015-09-07
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-3RETWAL | Seawall and Henry Hudson Parkway | 4 | ORIGINAL EQUIP & FURNISHING | 2015-09-08 | 2015-09-17 | 2015-09-08 | 2015-09-17
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-3RETWAL | Seawall and Henry Hudson Parkway | 5 | SUBSTANTIAL COMPLETION | 2015-09-18 | 2015-10-02 | 2015-09-18 | 2015-10-02
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-3RETWAL | Seawall and Henry Hudson Parkway | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-10-03 | 2015-10-07 | 2015-10-03 | 2020-10-07
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PASSSHIP4 | Manhattan Cruise Terminal - Viaduct Concrete Rehabilitation | 1 | DESIGN | 2016-01-01 | 2018-06-30 | 2016-01-01 | 2018-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PASSSHIP4 | Manhattan Cruise Terminal - Viaduct Concrete Rehabilitation | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-01 | 2018-06-30 | 2018-07-01 | 2018-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PASSSHIP4 | Manhattan Cruise Terminal - Viaduct Concrete Rehabilitation | 3 | CONSTRUCTION | 2018-07-01 | 2021-06-30 | 2018-07-01 | 2021-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PASSSHIP4 | Manhattan Cruise Terminal - Viaduct Concrete Rehabilitation | 4 | ORIGINAL EQUIP & FURNISHING | 2021-07-01 | 2021-06-30 | 2021-07-01 | 2021-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PASSSHIP4 | Manhattan Cruise Terminal - Viaduct Concrete Rehabilitation | 5 | SUBSTANTIAL COMPLETION | 2021-07-01 | 2021-06-30 | 2021-07-01 | 2021-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PASSSHIP4 | Manhattan Cruise Terminal - Viaduct Concrete Rehabilitation | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-07-01 | 2021-07-05 | 2021-07-01 | 2024-07-05
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER11DOT | Pier 11 | 1 | DESIGN | 2016-01-01 | 2018-06-30 | 2016-01-01 | 2018-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER11DOT | Pier 11 | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-01 | 2018-06-30 | 2018-07-01 | 2018-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER11DOT | Pier 11 | 3 | CONSTRUCTION | 2018-07-01 | 2021-06-30 | 2018-07-01 | 2021-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER11DOT | Pier 11 | 4 | ORIGINAL EQUIP & FURNISHING | 2021-07-01 | 2021-06-30 | 2021-07-01 | 2021-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER11DOT | Pier 11 | 5 | SUBSTANTIAL COMPLETION | 2021-07-01 | 2021-06-30 | 2021-07-01 | 2021-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER11DOT | Pier 11 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-07-01 | 2021-07-05 | 2021-07-01 | 2025-07-05
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER35-36 | Pier 35 and 36 Rehabilitation | 1 | DESIGN | 2008-01-01 | 2009-01-01 | 2012-01-01 | 2013-01-01
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER35-36 | Pier 35 and 36 Rehabilitation | 2 | BID AWARD AND REGISTER CONTRCT | 2009-01-02 | 2009-01-01 | 2013-01-02 | 2013-01-01
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER35-36 | Pier 35 and 36 Rehabilitation | 3 | CONSTRUCTION | 2009-01-02 | 2011-01-01 | 2013-01-02 | 2020-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER35-36 | Pier 35 and 36 Rehabilitation | 4 | ORIGINAL EQUIP & FURNISHING | 2011-01-02 | 2011-01-01 | 2020-07-01 | 2020-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER35-36 | Pier 35 and 36 Rehabilitation | 5 | SUBSTANTIAL COMPLETION | 2011-01-02 | 2011-01-01 | 2020-07-01 | 2020-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER35-36 | Pier 35 and 36 Rehabilitation | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2011-01-02 | 2011-01-06 | 2020-07-01 | 2023-07-05
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER36 | Pier 36 Structural Rehab | 1 | DEVELOP SCOPE | 2019-05-25 | 2019-07-08 | 2019-05-25 | 2019-07-08
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER36 | Pier 36 Structural Rehab | 2 | PRELIMINARY DESIGN | 2019-07-09 | 2019-11-05 | 2019-07-09 | 2019-11-05
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER36 | Pier 36 Structural Rehab | 3 | FINAL DESIGN | 2019-11-06 | 2020-03-04 | 2019-11-06 | 2020-03-04
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER36 | Pier 36 Structural Rehab | 4 | BID AWARD AND REGISTER CONTRCT | 2020-03-05 | 2020-06-30 | 2020-03-05 | 2020-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER36 | Pier 36 Structural Rehab | 5 | CONSTRUCTION TO 25% | 2020-07-01 | 2021-06-30 | 2020-07-01 | 2021-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER36 | Pier 36 Structural Rehab | 6 | CONSTRUCTION TO 50% | 2021-07-01 | 2022-06-30 | 2021-07-01 | 2022-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER36 | Pier 36 Structural Rehab | 7 | CONSTRUCTION TO 75% | 2022-07-01 | 2023-06-30 | 2022-07-01 | 2023-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER36 | Pier 36 Structural Rehab | 8 | SUBSTANTIAL COMPLETION | 2023-07-01 | 2023-11-27 | 2023-07-01 | 2023-11-27
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER36 | Pier 36 Structural Rehab | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-11-28 | 2024-03-26 | 2023-11-28 | 2024-03-26
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER36STR | Pier 36 Structural Rehab | 1 | DESIGN | 2018-07-01 | 2018-07-20 | 2018-07-01 | 2018-07-20
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER36STR | Pier 36 Structural Rehab | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-21 | 2018-08-04 | 2018-07-21 | 2018-08-04
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER36STR | Pier 36 Structural Rehab | 3 | CONSTRUCTION | 2018-08-05 | 2018-09-08 | 2018-08-05 | 2018-09-08
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER36STR | Pier 36 Structural Rehab | 4 | ORIGINAL EQUIP & FURNISHING | 2018-09-09 | 2018-09-18 | 2018-09-09 | 2018-09-18
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER36STR | Pier 36 Structural Rehab | 5 | SUBSTANTIAL COMPLETION | 2018-09-19 | 2018-10-03 | 2018-09-19 | 2018-10-03
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER36STR | Pier 36 Structural Rehab | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-10-04 | 2018-10-08 | 2018-10-04 | 2020-10-08
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER38 | DPR-CON ED Pier-Rehab Pier on East River from 38th to 44th S | 1 | DESIGN | 2013-03-15 | 2013-06-01 | 2013-03-15 | 2013-06-01
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER38 | DPR-CON ED Pier-Rehab Pier on East River from 38th to 44th S | 2 | BID AWARD AND REGISTER CONTRCT | 2013-06-02 | 2013-06-01 | 2013-06-02 | 2013-06-01
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER38 | DPR-CON ED Pier-Rehab Pier on East River from 38th to 44th S | 3 | CONSTRUCTION | 2013-06-02 | 2013-06-01 | 2013-06-02 | 2013-06-01
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER38 | DPR-CON ED Pier-Rehab Pier on East River from 38th to 44th S | 4 | ORIGINAL EQUIP & FURNISHING | 2013-06-02 | 2013-06-01 | 2013-06-02 | 2021-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER38 | DPR-CON ED Pier-Rehab Pier on East River from 38th to 44th S | 5 | SUBSTANTIAL COMPLETION | 2013-06-02 | 2013-06-01 | 2021-07-01 | 2021-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER38 | DPR-CON ED Pier-Rehab Pier on East River from 38th to 44th S | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-06-02 | 2013-06-06 | 2021-07-01 | 2021-07-05
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER4 | PIER 4 Rehabilitation | 1 | DESIGN | 2016-07-01 | 2016-07-20 | 2018-07-01 | 2018-07-20
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER4 | PIER 4 Rehabilitation | 2 | BID AWARD AND REGISTER CONTRCT | 2016-07-21 | 2016-08-04 | 2018-07-21 | 2018-08-04
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER4 | PIER 4 Rehabilitation | 3 | CONSTRUCTION | 2016-08-05 | 2016-09-08 | 2018-08-05 | 2018-09-08
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER4 | PIER 4 Rehabilitation | 4 | ORIGINAL EQUIP & FURNISHING | 2016-09-09 | 2016-09-18 | 2018-09-09 | 2018-09-18
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER4 | PIER 4 Rehabilitation | 5 | SUBSTANTIAL COMPLETION | 2016-09-19 | 2016-10-03 | 2018-09-19 | 2018-10-03
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER4 | PIER 4 Rehabilitation | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-10-04 | 2016-10-08 | 2018-10-04 | 2025-10-08
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER42CNT | Pier 42 and East River Park Connector Program | 1 | DESIGN | 2019-01-30 | 2019-02-18 | 2019-01-30 | 2019-02-18
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER42CNT | Pier 42 and East River Park Connector Program | 2 | BID AWARD AND REGISTER CONTRCT | 2019-02-19 | 2019-03-05 | 2019-02-19 | 2019-03-05
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER42CNT | Pier 42 and East River Park Connector Program | 3 | CONSTRUCTION | 2019-03-06 | 2019-04-09 | 2019-03-06 | 2019-04-09
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER42CNT | Pier 42 and East River Park Connector Program | 4 | ORIGINAL EQUIP & FURNISHING | 2019-04-10 | 2019-04-19 | 2019-04-10 | 2019-04-19
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER42CNT | Pier 42 and East River Park Connector Program | 5 | SUBSTANTIAL COMPLETION | 2019-04-20 | 2021-05-04 | 2019-04-20 | 2021-05-04
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER42CNT | Pier 42 and East River Park Connector Program | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-05-05 | 2021-05-09 | 2021-05-05 | 2022-05-09
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER6PILE | Pier 6 Pile Rehabilitation | 1 | DESIGN | 2015-03-02 | 2015-09-30 | 2017-03-02 | 2017-09-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER6PILE | Pier 6 Pile Rehabilitation | 2 | BID AWARD AND REGISTER CONTRCT | 2015-10-01 | 2015-09-30 | 2017-10-01 | 2017-09-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER6PILE | Pier 6 Pile Rehabilitation | 3 | CONSTRUCTION | 2015-10-01 | 2016-10-01 | 2017-10-01 | 2018-10-02
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER6PILE | Pier 6 Pile Rehabilitation | 4 | ORIGINAL EQUIP & FURNISHING | 2016-10-02 | 2016-10-01 | 2018-10-03 | 2018-10-02
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER6PILE | Pier 6 Pile Rehabilitation | 5 | SUBSTANTIAL COMPLETION | 2016-10-02 | 2016-10-01 | 2018-10-03 | 2018-10-02
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER6PILE | Pier 6 Pile Rehabilitation | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-10-02 | 2016-10-06 | 2018-10-03 | 2025-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER79DOT | Pier 79 | 1 | DESIGN | 2016-01-01 | 2018-06-30 | 2016-01-01 | 2018-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER79DOT | Pier 79 | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-01 | 2018-06-30 | 2018-07-01 | 2018-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER79DOT | Pier 79 | 3 | CONSTRUCTION | 2018-07-01 | 2021-06-30 | 2018-07-01 | 2021-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER79DOT | Pier 79 | 4 | ORIGINAL EQUIP & FURNISHING | 2021-07-01 | 2021-06-30 | 2021-07-01 | 2021-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER79DOT | Pier 79 | 5 | SUBSTANTIAL COMPLETION | 2021-07-01 | 2021-06-30 | 2021-07-01 | 2021-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER79DOT | Pier 79 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-07-01 | 2021-07-05 | 2021-07-01 | 2025-07-05
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER94RH | Pier 94 Rehabilitation | 4 | ORIGINAL EQUIP & FURNISHING | 2012-10-20 | 2012-10-19 | 2015-10-21 | 2015-10-20
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER94RH | Pier 94 Rehabilitation | 5 | SUBSTANTIAL COMPLETION | 2012-10-20 | 2012-10-19 | 2015-10-21 | 2015-10-20
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER94RH | Pier 94 Rehabilitation | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-10-20 | 2012-10-24 | 2015-10-21 | 2020-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIERS35N6 | Pier 35 & 36 Substructure Rehabilitation | 1 | DESIGN | 2016-07-01 | 2016-07-20 | 2018-07-01 | 2018-07-20
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIERS35N6 | Pier 35 & 36 Substructure Rehabilitation | 2 | BID AWARD AND REGISTER CONTRCT | 2016-07-21 | 2016-08-04 | 2018-07-21 | 2018-08-04
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIERS35N6 | Pier 35 & 36 Substructure Rehabilitation | 3 | CONSTRUCTION | 2016-08-05 | 2016-09-08 | 2018-08-05 | 2018-09-08
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIERS35N6 | Pier 35 & 36 Substructure Rehabilitation | 4 | ORIGINAL EQUIP & FURNISHING | 2016-09-09 | 2016-09-18 | 2018-09-09 | 2018-09-18
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIERS35N6 | Pier 35 & 36 Substructure Rehabilitation | 5 | SUBSTANTIAL COMPLETION | 2016-09-19 | 2016-10-03 | 2018-09-19 | 2020-10-03
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIERS35N6 | Pier 35 & 36 Substructure Rehabilitation | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-10-04 | 2016-10-08 | 2020-10-04 | 2020-10-08
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIERS8890 | Piers 88 & 90 Cluster Encapsulation Project | 1 | DESIGN | 2015-06-30 | 2015-07-19 | 2018-06-30 | 2018-07-19
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIERS8890 | Piers 88 & 90 Cluster Encapsulation Project | 2 | BID AWARD AND REGISTER CONTRCT | 2015-07-20 | 2015-08-03 | 2018-07-20 | 2018-08-03
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIERS8890 | Piers 88 & 90 Cluster Encapsulation Project | 3 | CONSTRUCTION | 2015-08-04 | 2015-09-07 | 2018-08-04 | 2018-09-07
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIERS8890 | Piers 88 & 90 Cluster Encapsulation Project | 4 | ORIGINAL EQUIP & FURNISHING | 2015-09-08 | 2015-09-17 | 2018-09-08 | 2018-09-17
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIERS8890 | Piers 88 & 90 Cluster Encapsulation Project | 5 | SUBSTANTIAL COMPLETION | 2015-09-18 | 2015-10-02 | 2018-09-18 | 2018-10-02
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIERS8890 | Piers 88 & 90 Cluster Encapsulation Project | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-10-03 | 2015-10-07 | 2018-10-03 | 2023-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PROGDOMIN | COMMUNITY ASSOCIATION OF PROGRESSIVE DOMINICANS | 1 | DESIGN | 2016-01-01 | 2018-06-30 | 2016-01-01 | 2018-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PROGDOMIN | COMMUNITY ASSOCIATION OF PROGRESSIVE DOMINICANS | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-01 | 2018-06-30 | 2018-07-01 | 2018-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PROGDOMIN | COMMUNITY ASSOCIATION OF PROGRESSIVE DOMINICANS | 3 | CONSTRUCTION | 2018-07-01 | 2021-06-30 | 2018-07-01 | 2021-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PROGDOMIN | COMMUNITY ASSOCIATION OF PROGRESSIVE DOMINICANS | 4 | ORIGINAL EQUIP & FURNISHING | 2021-07-01 | 2021-06-30 | 2021-07-01 | 2021-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PROGDOMIN | COMMUNITY ASSOCIATION OF PROGRESSIVE DOMINICANS | 5 | SUBSTANTIAL COMPLETION | 2021-07-01 | 2021-06-30 | 2021-07-01 | 2021-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PROGDOMIN | COMMUNITY ASSOCIATION OF PROGRESSIVE DOMINICANS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-07-01 | 2021-07-05 | 2021-07-01 | 2021-07-05
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV279-STU | NYCC - New York City Center Studios Renovation | 1 | DEVELOP SCOPE | 2015-06-15 | 2015-09-12 | 2015-06-15 | 2015-07-04
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV279-STU | NYCC - New York City Center Studios Renovation | 2 | PRELIMINARY DESIGN | 2015-09-13 | 2016-01-10 | 2015-07-05 | 2015-07-19
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV279-STU | NYCC - New York City Center Studios Renovation | 3 | FINAL DESIGN | 2016-01-11 | 2016-07-08 | 2015-07-20 | 2015-08-23
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV279-STU | NYCC - New York City Center Studios Renovation | 4 | BID AWARD AND REGISTER CONTRCT | 2016-07-09 | 2016-10-06 | 2015-08-24 | 2015-09-02
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV279-STU | NYCC - New York City Center Studios Renovation | 5 | CONSTRUCTION TO 25% | 2016-10-07 | 2017-02-03 | 2015-09-03 | 2015-09-17
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV279-STU | NYCC - New York City Center Studios Renovation | 6 | CONSTRUCTION TO 50% | 2017-02-04 | 2017-06-03 | 2015-09-18 | 2022-09-22
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV279-STU | NYCC - New York City Center Studios Renovation | 7 | CONSTRUCTION TO 75% | 2017-06-04 | 2017-10-01 | 2015-09-18 | 2022-09-22
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV279-STU | NYCC - New York City Center Studios Renovation | 8 | ORIGINAL EQUIP & FURNISHING | 2017-10-02 | 2017-12-30 | 2015-09-18 | 2022-09-22
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV279-STU | NYCC - New York City Center Studios Renovation | 9 | SUBSTANTIAL COMPLETION | 2017-12-31 | 2018-02-28 | 2015-09-18 | 2022-09-22
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV279-STU | NYCC - New York City Center Studios Renovation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-03-01 | 2018-03-30 | 2015-09-18 | 2022-09-22
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV467-BEY | DCA PFA - Percent for Art Beyond Sims | 1 | DESIGN | 2019-06-30 | 2019-07-19 | 2019-06-30 | 2019-07-19
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV467-BEY | DCA PFA - Percent for Art Beyond Sims | 2 | BID AWARD AND REGISTER CONTRCT | 2019-07-20 | 2019-08-03 | 2019-07-20 | 2019-08-03
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV467-BEY | DCA PFA - Percent for Art Beyond Sims | 3 | CONSTRUCTION | 2019-08-04 | 2019-09-07 | 2019-08-04 | 2019-09-07
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV467-BEY | DCA PFA - Percent for Art Beyond Sims | 4 | ORIGINAL EQUIP & FURNISHING | 2019-09-08 | 2019-09-17 | 2019-09-08 | 2019-09-17
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV467-BEY | DCA PFA - Percent for Art Beyond Sims | 5 | SUBSTANTIAL COMPLETION | 2019-09-18 | 2021-10-02 | 2019-09-18 | 2021-10-02
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV467-BEY | DCA PFA - Percent for Art Beyond Sims | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-10-03 | 2021-10-07 | 2021-10-03 | 2021-10-07
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV467ELMB | ELM- El Museo - Gallery Environmental Stabilzation Project | 1 | DESIGN | 2015-05-24 | 2015-06-12 | 2015-05-24 | 2015-06-12
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV467ELMB | ELM- El Museo - Gallery Environmental Stabilzation Project | 2 | BID AWARD AND REGISTER CONTRCT | 2015-06-13 | 2015-06-27 | 2015-06-13 | 2015-06-27
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV467ELMB | ELM- El Museo - Gallery Environmental Stabilzation Project | 3 | CONSTRUCTION | 2015-06-28 | 2015-08-01 | 2015-06-28 | 2015-08-01
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV467ELMB | ELM- El Museo - Gallery Environmental Stabilzation Project | 4 | ORIGINAL EQUIP & FURNISHING | 2015-08-02 | 2015-08-11 | 2015-08-02 | 2015-08-11
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV467ELMB | ELM- El Museo - Gallery Environmental Stabilzation Project | 5 | SUBSTANTIAL COMPLETION | 2015-08-12 | 2015-08-26 | 2015-08-12 | 2015-08-26
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV467ELMB | ELM- El Museo - Gallery Environmental Stabilzation Project | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-08-27 | 2015-08-31 | 2015-08-27 | 2023-08-31
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV467M125 | Mart 125 Development | 1 | DEVELOP SCOPE | 2011-09-01 | 2011-11-29 | 2011-09-01 | 2011-09-20
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV467M125 | Mart 125 Development | 2 | PRELIMINARY DESIGN | 2011-11-30 | 2012-03-28 | 2011-09-21 | 2011-10-05
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV467M125 | Mart 125 Development | 3 | FINAL DESIGN | 2012-03-29 | 2012-09-24 | 2011-10-06 | 2011-11-09
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV467M125 | Mart 125 Development | 4 | BID AWARD AND REGISTER CONTRCT | 2012-09-25 | 2012-12-23 | 2011-11-10 | 2011-11-19
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV467M125 | Mart 125 Development | 5 | CONSTRUCTION TO 25% | 2012-12-24 | 2013-04-22 | 2011-11-20 | 2011-12-04
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV467M125 | Mart 125 Development | 6 | CONSTRUCTION TO 50% | 2013-04-23 | 2013-08-20 | 2011-12-05 | 2022-12-09
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV467M125 | Mart 125 Development | 7 | CONSTRUCTION TO 75% | 2013-08-21 | 2013-12-18 | 2011-12-05 | 2022-12-09
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV467M125 | Mart 125 Development | 8 | ORIGINAL EQUIP & FURNISHING | 2013-12-19 | 2014-03-18 | 2011-12-05 | 2022-12-09
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV467M125 | Mart 125 Development | 9 | SUBSTANTIAL COMPLETION | 2014-03-19 | 2014-05-17 | 2011-12-05 | 2022-12-09
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV467M125 | Mart 125 Development | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-05-18 | 2014-06-16 | 2011-12-05 | 2022-12-09
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV467-PCT | DCA PFA - Percent for Art Tito P. | 1 | DEVELOP SCOPE | 2008-04-01 | 2008-06-29 | 2016-02-28 | 2016-03-18
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV467-PCT | DCA PFA - Percent for Art Tito P. | 2 | PRELIMINARY DESIGN | 2008-06-30 | 2008-10-27 | 2016-03-19 | 2016-04-02
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV467-PCT | DCA PFA - Percent for Art Tito P. | 3 | FINAL DESIGN | 2008-10-28 | 2009-04-25 | 2016-04-03 | 2016-05-07
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV467-PCT | DCA PFA - Percent for Art Tito P. | 4 | BID AWARD AND REGISTER CONTRCT | 2009-04-26 | 2009-07-24 | 2016-05-08 | 2016-05-17
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV467-PCT | DCA PFA - Percent for Art Tito P. | 5 | CONSTRUCTION TO 25% | 2009-07-25 | 2009-11-21 | 2016-05-18 | 2016-06-01
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV467-PCT | DCA PFA - Percent for Art Tito P. | 6 | CONSTRUCTION TO 50% | 2009-11-22 | 2010-03-21 | 2016-06-02 | 2025-06-06
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV467-PCT | DCA PFA - Percent for Art Tito P. | 7 | CONSTRUCTION TO 75% | 2010-03-22 | 2010-07-19 | 2016-06-02 | 2025-06-06
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV467-PCT | DCA PFA - Percent for Art Tito P. | 8 | ORIGINAL EQUIP & FURNISHING | 2010-07-20 | 2010-10-17 | 2016-06-02 | 2025-06-06
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV467-PCT | DCA PFA - Percent for Art Tito P. | 9 | SUBSTANTIAL COMPLETION | 2010-10-18 | 2010-12-16 | 2016-06-02 | 2025-06-06
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV467-PCT | DCA PFA - Percent for Art Tito P. | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2010-12-17 | 2011-01-15 | 2016-06-02 | 2025-06-06
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PWD5CFTH | FA - Coalition for the Homeless | 4 | ORIGINAL EQUIP & FURNISHING | 2007-09-08 | 2007-09-07 | 2007-09-08 | 2007-09-07
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PWD5CFTH | FA - Coalition for the Homeless | 5 | SUBSTANTIAL COMPLETION | 2007-09-08 | 2007-09-07 | 2007-09-08 | 2007-09-07
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PWD5CFTH | FA - Coalition for the Homeless | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2007-09-08 | 2007-09-12 | 2007-09-08 | 2011-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | RANDBXSHO | Randall's Island - Bronx Shore Fields | 3 | CONSTRUCTION | 2012-01-21 | 2014-01-20 | 2014-01-15 | 2019-06-25
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | RANDBXSHO | Randall's Island - Bronx Shore Fields | 4 | ORIGINAL EQUIP & FURNISHING | 2014-01-21 | 2014-01-20 | 2019-06-26 | 2019-06-25
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | RANDBXSHO | Randall's Island - Bronx Shore Fields | 5 | SUBSTANTIAL COMPLETION | 2014-01-21 | 2014-01-20 | 2019-06-26 | 2019-06-25
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | RANDBXSHO | Randall's Island - Bronx Shore Fields | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-01-21 | 2014-01-25 | 2019-06-26 | 2019-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | RANDISSF | Randall's Island Sports Fields | 1 | DESIGN | 2006-01-01 | 2006-01-20 | 2017-04-02 | 2023-07-01
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | RANDISSF | Randall's Island Sports Fields | 2 | BID AWARD AND REGISTER CONTRCT | 2006-01-21 | 2007-02-04 | 2023-07-02 | 2023-07-01
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | RANDISSF | Randall's Island Sports Fields | 3 | CONSTRUCTION | 2007-02-05 | 2007-02-04 | 2007-04-01 | 2020-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | RANDISSF | Randall's Island Sports Fields | 4 | ORIGINAL EQUIP & FURNISHING | 2007-02-05 | 2007-02-04 | 2020-07-01 | 2020-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | RANDISSF | Randall's Island Sports Fields | 5 | SUBSTANTIAL COMPLETION | 2007-02-05 | 2007-02-04 | 2020-07-01 | 2020-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | RANDISSF | Randall's Island Sports Fields | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2007-02-05 | 2007-02-09 | 2020-07-01 | 2029-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | RE25-004 | FA - Courts & Sports at Pier 36 | 1 | DESIGN | 1999-07-01 | 1999-07-20 | 2006-12-01 | 2009-01-01
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | RE25-004 | FA - Courts & Sports at Pier 36 | 2 | BID AWARD AND REGISTER CONTRCT | 1999-07-21 | 1999-08-04 | 2009-01-02 | 2010-08-01
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | RE25-004 | FA - Courts & Sports at Pier 36 | 3 | CONSTRUCTION | 1999-08-05 | 2007-06-30 | 2007-06-01 | 2011-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | RE25-004 | FA - Courts & Sports at Pier 36 | 4 | ORIGINAL EQUIP & FURNISHING | 2007-07-01 | 2007-06-30 | 2011-07-01 | 2011-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | RE25-004 | FA - Courts & Sports at Pier 36 | 5 | SUBSTANTIAL COMPLETION | 2007-07-01 | 2007-06-30 | 2011-07-01 | 2011-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | RE25-004 | FA - Courts & Sports at Pier 36 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2007-07-01 | 2007-07-05 | 2011-07-01 | 2011-07-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | RISALTMAR | Randall's Island Salt Marsh | 1 | DESIGN | 1899-12-31 | 1900-01-19 | 1908-01-02 | 2025-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | RISALTMAR | Randall's Island Salt Marsh | 2 | BID AWARD AND REGISTER CONTRCT | 1900-01-20 | 1900-02-03 | 2025-07-01 | 2025-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | RISALTMAR | Randall's Island Salt Marsh | 3 | CONSTRUCTION | 2006-10-01 | 2008-08-31 | 2006-10-01 | 2008-08-31
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | RISALTMAR | Randall's Island Salt Marsh | 4 | ORIGINAL EQUIP & FURNISHING | 2008-09-01 | 2008-08-31 | 2008-09-01 | 2008-08-31
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | RISALTMAR | Randall's Island Salt Marsh | 5 | SUBSTANTIAL COMPLETION | 2008-09-01 | 2008-08-31 | 2008-09-01 | 2008-08-31
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | RISALTMAR | Randall's Island Salt Marsh | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-09-01 | 2008-09-05 | 2008-09-01 | 2029-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | ROOSEDOCK | Roosevelt Island Dock | 1 | DESIGN | 2006-08-01 | 2006-08-20 | 2018-08-02 | 2018-08-21
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | ROOSEDOCK | Roosevelt Island Dock | 2 | BID AWARD AND REGISTER CONTRCT | 2006-08-21 | 2006-09-04 | 2018-08-22 | 2018-09-05
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | ROOSEDOCK | Roosevelt Island Dock | 3 | CONSTRUCTION | 2006-09-05 | 2006-10-09 | 2011-05-30 | 2017-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | ROOSEDOCK | Roosevelt Island Dock | 4 | ORIGINAL EQUIP & FURNISHING | 2006-10-10 | 2006-10-19 | 2017-07-01 | 2017-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | ROOSEDOCK | Roosevelt Island Dock | 5 | SUBSTANTIAL COMPLETION | 2006-10-20 | 2006-11-03 | 2017-07-01 | 2017-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | ROOSEDOCK | Roosevelt Island Dock | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2006-11-04 | 2006-11-08 | 2018-12-01 | 2025-12-05
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | ROOSEOPER | Roosevelt Island Operating Corp - Blackwell House | 1 | DESIGN | 2019-07-01 | 2019-07-20 | 2019-07-01 | 2019-07-20
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | ROOSEOPER | Roosevelt Island Operating Corp - Blackwell House | 2 | BID AWARD AND REGISTER CONTRCT | 2019-07-21 | 2019-08-04 | 2019-07-21 | 2019-08-04
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | ROOSEOPER | Roosevelt Island Operating Corp - Blackwell House | 3 | CONSTRUCTION | 2019-08-05 | 2019-09-08 | 2019-08-05 | 2019-09-08
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | ROOSEOPER | Roosevelt Island Operating Corp - Blackwell House | 4 | ORIGINAL EQUIP & FURNISHING | 2019-09-09 | 2019-09-18 | 2019-09-09 | 2019-09-18
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | ROOSEOPER | Roosevelt Island Operating Corp - Blackwell House | 5 | SUBSTANTIAL COMPLETION | 2019-09-19 | 2021-10-03 | 2019-09-19 | 2021-10-03
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | ROOSEOPER | Roosevelt Island Operating Corp - Blackwell House | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-10-04 | 2021-10-08 | 2021-10-04 | 2021-10-08
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | ROOSISLTH | ROOSEVELT ISLAND LIGHTHOUSE | 1 | DESIGN | 2019-07-01 | 2019-07-20 | 2016-06-30 | 2016-07-19
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | ROOSISLTH | ROOSEVELT ISLAND LIGHTHOUSE | 2 | BID AWARD AND REGISTER CONTRCT | 2019-07-21 | 2019-08-04 | 2016-07-20 | 2016-08-03
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | ROOSISLTH | ROOSEVELT ISLAND LIGHTHOUSE | 3 | CONSTRUCTION | 2019-08-05 | 2019-09-08 | 2016-08-04 | 2016-09-07
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | ROOSISLTH | ROOSEVELT ISLAND LIGHTHOUSE | 4 | ORIGINAL EQUIP & FURNISHING | 2019-09-09 | 2019-09-18 | 2016-09-08 | 2016-09-17
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | ROOSISLTH | ROOSEVELT ISLAND LIGHTHOUSE | 5 | SUBSTANTIAL COMPLETION | 2019-09-19 | 2021-10-03 | 2016-09-18 | 2018-10-03
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | ROOSISLTH | ROOSEVELT ISLAND LIGHTHOUSE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-10-04 | 2021-10-08 | 2018-10-04 | 2024-10-08
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND1101 | HHC FEMA PMP BELLEVUE: WATER REDUNDANCY A4 | 1 | DESIGN | 2016-07-01 | 2016-07-20 | 2016-07-01 | 2016-07-20
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND1101 | HHC FEMA PMP BELLEVUE: WATER REDUNDANCY A4 | 2 | BID AWARD AND REGISTER CONTRCT | 2016-07-21 | 2016-08-04 | 2016-07-21 | 2016-08-04
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND1101 | HHC FEMA PMP BELLEVUE: WATER REDUNDANCY A4 | 3 | CONSTRUCTION | 2016-08-05 | 2016-09-08 | 2016-08-05 | 2016-09-08
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND1101 | HHC FEMA PMP BELLEVUE: WATER REDUNDANCY A4 | 4 | ORIGINAL EQUIP & FURNISHING | 2016-09-09 | 2016-09-18 | 2016-09-09 | 2016-09-18
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND1101 | HHC FEMA PMP BELLEVUE: WATER REDUNDANCY A4 | 5 | SUBSTANTIAL COMPLETION | 2016-09-19 | 2016-10-03 | 2016-09-19 | 2016-10-03
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND1101 | HHC FEMA PMP BELLEVUE: WATER REDUNDANCY A4 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-10-04 | 2019-10-08 | 2016-10-04 | 2021-10-08
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND1102 | HHC FEMA PMP BELLEVUE: MEDICAL GAS SYSTEM MITIGATION A5 | 1 | DESIGN | 2015-07-01 | 2015-07-20 | 2015-07-01 | 2015-07-20
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND1102 | HHC FEMA PMP BELLEVUE: MEDICAL GAS SYSTEM MITIGATION A5 | 2 | BID AWARD AND REGISTER CONTRCT | 2015-07-21 | 2015-08-04 | 2015-07-21 | 2015-08-04
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND1102 | HHC FEMA PMP BELLEVUE: MEDICAL GAS SYSTEM MITIGATION A5 | 3 | CONSTRUCTION | 2015-08-05 | 2015-09-08 | 2015-08-05 | 2015-09-08
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND1102 | HHC FEMA PMP BELLEVUE: MEDICAL GAS SYSTEM MITIGATION A5 | 4 | ORIGINAL EQUIP & FURNISHING | 2015-09-09 | 2015-09-18 | 2015-09-09 | 2015-09-18
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND1102 | HHC FEMA PMP BELLEVUE: MEDICAL GAS SYSTEM MITIGATION A5 | 5 | SUBSTANTIAL COMPLETION | 2015-09-19 | 2015-10-03 | 2015-09-19 | 2015-10-03
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND1102 | HHC FEMA PMP BELLEVUE: MEDICAL GAS SYSTEM MITIGATION A5 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-10-04 | 2019-10-08 | 2015-10-04 | 2019-10-08
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND1103 | HHC FEMA PMP BELLEVUE: Pipe and Basement Tank Insulation A7 | 1 | DESIGN | 2015-07-01 | 2015-07-20 | 2015-07-01 | 2015-07-20
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND1103 | HHC FEMA PMP BELLEVUE: Pipe and Basement Tank Insulation A7 | 2 | BID AWARD AND REGISTER CONTRCT | 2015-07-21 | 2015-08-04 | 2015-07-21 | 2015-08-04
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND1103 | HHC FEMA PMP BELLEVUE: Pipe and Basement Tank Insulation A7 | 3 | CONSTRUCTION | 2015-08-05 | 2015-09-08 | 2015-08-05 | 2015-09-08
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND1103 | HHC FEMA PMP BELLEVUE: Pipe and Basement Tank Insulation A7 | 4 | ORIGINAL EQUIP & FURNISHING | 2015-09-09 | 2015-09-18 | 2015-09-09 | 2015-09-18
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND1103 | HHC FEMA PMP BELLEVUE: Pipe and Basement Tank Insulation A7 | 5 | SUBSTANTIAL COMPLETION | 2015-09-19 | 2015-10-03 | 2015-09-19 | 2015-10-03
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND1103 | HHC FEMA PMP BELLEVUE: Pipe and Basement Tank Insulation A7 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-10-04 | 2019-10-08 | 2015-10-04 | 2025-10-08
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND1104 | HHC FEMA Bellevue Hospital Center Flood Protection Barrier | 1 | DESIGN | 2016-07-01 | 2016-07-20 | 2018-07-01 | 2018-07-20
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND1104 | HHC FEMA Bellevue Hospital Center Flood Protection Barrier | 2 | BID AWARD AND REGISTER CONTRCT | 2016-07-21 | 2016-08-04 | 2018-07-21 | 2018-08-04
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND1104 | HHC FEMA Bellevue Hospital Center Flood Protection Barrier | 3 | CONSTRUCTION | 2016-08-05 | 2016-09-08 | 2018-08-05 | 2018-09-08
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND1104 | HHC FEMA Bellevue Hospital Center Flood Protection Barrier | 4 | ORIGINAL EQUIP & FURNISHING | 2016-09-09 | 2016-09-18 | 2018-09-09 | 2018-09-18
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND1104 | HHC FEMA Bellevue Hospital Center Flood Protection Barrier | 5 | SUBSTANTIAL COMPLETION | 2016-09-19 | 2016-10-03 | 2018-09-19 | 2018-10-03
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND1104 | HHC FEMA Bellevue Hospital Center Flood Protection Barrier | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-10-04 | 2016-10-08 | 2018-10-04 | 2024-10-08
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND1105 | HHC FEMA BELLEVUE HOSPITAL REPLACEMENT GENERATOR | 1 | DESIGN | 2016-07-01 | 2016-07-20 | 2019-07-01 | 2019-07-20
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND1105 | HHC FEMA BELLEVUE HOSPITAL REPLACEMENT GENERATOR | 2 | BID AWARD AND REGISTER CONTRCT | 2016-07-21 | 2016-08-04 | 2019-07-21 | 2019-08-04
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND1105 | HHC FEMA BELLEVUE HOSPITAL REPLACEMENT GENERATOR | 3 | CONSTRUCTION | 2016-08-05 | 2016-09-08 | 2019-08-05 | 2019-09-08
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND1105 | HHC FEMA BELLEVUE HOSPITAL REPLACEMENT GENERATOR | 4 | ORIGINAL EQUIP & FURNISHING | 2016-09-09 | 2016-09-18 | 2019-09-09 | 2019-09-18
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND1105 | HHC FEMA BELLEVUE HOSPITAL REPLACEMENT GENERATOR | 5 | SUBSTANTIAL COMPLETION | 2016-09-19 | 2016-10-03 | 2019-09-19 | 2019-10-03
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND1105 | HHC FEMA BELLEVUE HOSPITAL REPLACEMENT GENERATOR | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-10-04 | 2016-10-08 | 2019-10-04 | 2019-10-08
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND1106 | HHC FEMA BELLEVUE HOSPITAL Civil Roadway | 1 | DESIGN | 2016-07-01 | 2016-07-20 | 2019-07-01 | 2019-07-20
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND1106 | HHC FEMA BELLEVUE HOSPITAL Civil Roadway | 2 | BID AWARD AND REGISTER CONTRCT | 2016-07-21 | 2016-08-04 | 2019-07-21 | 2019-08-04
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND1106 | HHC FEMA BELLEVUE HOSPITAL Civil Roadway | 3 | CONSTRUCTION | 2016-08-05 | 2016-09-08 | 2019-08-05 | 2019-09-08
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND1106 | HHC FEMA BELLEVUE HOSPITAL Civil Roadway | 4 | ORIGINAL EQUIP & FURNISHING | 2016-09-09 | 2016-09-18 | 2019-09-09 | 2019-09-18
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND1106 | HHC FEMA BELLEVUE HOSPITAL Civil Roadway | 5 | SUBSTANTIAL COMPLETION | 2016-09-19 | 2016-10-03 | 2019-09-19 | 2019-10-03
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND1106 | HHC FEMA BELLEVUE HOSPITAL Civil Roadway | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-10-04 | 2016-10-08 | 2019-10-04 | 2019-10-08
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND1108 | HHC FEMA BELLEVUE HOSPITAL PARKING LOT LIFTS | 1 | DESIGN | 2016-07-01 | 2016-07-20 | 2019-07-01 | 2019-07-20
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND1108 | HHC FEMA BELLEVUE HOSPITAL PARKING LOT LIFTS | 2 | BID AWARD AND REGISTER CONTRCT | 2016-07-21 | 2016-08-04 | 2019-07-21 | 2019-08-04
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND1108 | HHC FEMA BELLEVUE HOSPITAL PARKING LOT LIFTS | 3 | CONSTRUCTION | 2016-08-05 | 2016-09-08 | 2019-08-05 | 2019-09-08
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND1108 | HHC FEMA BELLEVUE HOSPITAL PARKING LOT LIFTS | 4 | ORIGINAL EQUIP & FURNISHING | 2016-09-09 | 2016-09-18 | 2019-09-09 | 2019-09-18
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND1108 | HHC FEMA BELLEVUE HOSPITAL PARKING LOT LIFTS | 5 | SUBSTANTIAL COMPLETION | 2016-09-19 | 2016-10-03 | 2019-09-19 | 2019-10-03
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND1108 | HHC FEMA BELLEVUE HOSPITAL PARKING LOT LIFTS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-10-04 | 2016-10-08 | 2019-10-04 | 2025-10-08
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND1110 | HHC FEMA BELLEVUE (MEP/VT | 1 | DESIGN | 2018-07-01 | 2018-07-20 | 2018-07-01 | 2018-07-20
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND1110 | HHC FEMA BELLEVUE (MEP/VT | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-21 | 2018-08-04 | 2018-07-21 | 2018-08-04
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND1110 | HHC FEMA BELLEVUE (MEP/VT | 3 | CONSTRUCTION | 2018-08-05 | 2018-09-08 | 2018-08-05 | 2018-09-08
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND1110 | HHC FEMA BELLEVUE (MEP/VT | 4 | ORIGINAL EQUIP & FURNISHING | 2018-09-09 | 2018-09-18 | 2018-09-09 | 2018-09-18
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND1110 | HHC FEMA BELLEVUE (MEP/VT | 5 | SUBSTANTIAL COMPLETION | 2018-09-19 | 2018-10-03 | 2018-09-19 | 2018-10-03
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND1110 | HHC FEMA BELLEVUE (MEP/VT | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-10-04 | 2018-10-08 | 2018-10-04 | 2025-10-08
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND1112 | HHC FEMA BELLEVUE BASEMENT GENERAL CONSTRUCTION | 1 | DESIGN | 2016-07-01 | 2016-07-20 | 2019-07-01 | 2019-07-20
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND1112 | HHC FEMA BELLEVUE BASEMENT GENERAL CONSTRUCTION | 2 | BID AWARD AND REGISTER CONTRCT | 2016-07-21 | 2016-08-04 | 2019-07-21 | 2019-08-04
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND1112 | HHC FEMA BELLEVUE BASEMENT GENERAL CONSTRUCTION | 3 | CONSTRUCTION | 2016-08-05 | 2016-09-08 | 2019-08-05 | 2019-09-08
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND1112 | HHC FEMA BELLEVUE BASEMENT GENERAL CONSTRUCTION | 4 | ORIGINAL EQUIP & FURNISHING | 2016-09-09 | 2016-09-18 | 2019-09-09 | 2019-09-18
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND1112 | HHC FEMA BELLEVUE BASEMENT GENERAL CONSTRUCTION | 5 | SUBSTANTIAL COMPLETION | 2016-09-19 | 2016-10-03 | 2019-09-19 | 2019-10-03
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND1112 | HHC FEMA BELLEVUE BASEMENT GENERAL CONSTRUCTION | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-10-04 | 2016-10-08 | 2019-10-04 | 2025-10-08
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND1113 | HHC FEMA PMP BELLEVUE EXISTING VERTICAL TRANSPORTATION | 1 | DESIGN | 2017-07-01 | 2017-07-20 | 2017-07-01 | 2017-07-20
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND1113 | HHC FEMA PMP BELLEVUE EXISTING VERTICAL TRANSPORTATION | 2 | BID AWARD AND REGISTER CONTRCT | 2017-07-21 | 2017-08-04 | 2017-07-21 | 2017-08-04
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND1113 | HHC FEMA PMP BELLEVUE EXISTING VERTICAL TRANSPORTATION | 3 | CONSTRUCTION | 2017-08-05 | 2017-09-08 | 2017-08-05 | 2017-09-08
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND1113 | HHC FEMA PMP BELLEVUE EXISTING VERTICAL TRANSPORTATION | 4 | ORIGINAL EQUIP & FURNISHING | 2017-09-09 | 2017-09-18 | 2017-09-09 | 2017-09-18
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND1113 | HHC FEMA PMP BELLEVUE EXISTING VERTICAL TRANSPORTATION | 5 | SUBSTANTIAL COMPLETION | 2017-09-19 | 2017-10-03 | 2017-09-19 | 2017-10-03
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND1113 | HHC FEMA PMP BELLEVUE EXISTING VERTICAL TRANSPORTATION | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-10-04 | 2017-10-08 | 2017-10-04 | 2021-10-08
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND3702 | MHC: REPLACE SWITCHGEAR, PANEL BOXES & ATS - SANDY CTGY E | 1 | DESIGN | 2015-07-01 | 2015-07-20 | 2018-03-23 | 2018-04-11
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND3702 | MHC: REPLACE SWITCHGEAR, PANEL BOXES & ATS - SANDY CTGY E | 2 | BID AWARD AND REGISTER CONTRCT | 2015-07-21 | 2015-08-04 | 2018-04-12 | 2018-04-26
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND3702 | MHC: REPLACE SWITCHGEAR, PANEL BOXES & ATS - SANDY CTGY E | 3 | CONSTRUCTION | 2015-08-05 | 2015-09-08 | 2018-04-27 | 2018-05-31
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND3702 | MHC: REPLACE SWITCHGEAR, PANEL BOXES & ATS - SANDY CTGY E | 4 | ORIGINAL EQUIP & FURNISHING | 2015-09-09 | 2015-09-18 | 2018-06-01 | 2018-06-10
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND3702 | MHC: REPLACE SWITCHGEAR, PANEL BOXES & ATS - SANDY CTGY E | 5 | SUBSTANTIAL COMPLETION | 2015-09-19 | 2015-10-03 | 2018-06-11 | 2018-06-25
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND3702 | MHC: REPLACE SWITCHGEAR, PANEL BOXES & ATS - SANDY CTGY E | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-10-04 | 2019-10-08 | 2018-06-26 | 2025-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND3703 | MHC: REPLACE SRVC ENTRANCE CABLES & DUCTBANK - SANDY CTRY E | 1 | DESIGN | 2015-07-01 | 2015-07-20 | 2015-07-01 | 2015-07-20
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND3703 | MHC: REPLACE SRVC ENTRANCE CABLES & DUCTBANK - SANDY CTRY E | 2 | BID AWARD AND REGISTER CONTRCT | 2015-07-21 | 2015-08-04 | 2015-07-21 | 2015-08-04
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND3703 | MHC: REPLACE SRVC ENTRANCE CABLES & DUCTBANK - SANDY CTRY E | 3 | CONSTRUCTION | 2015-08-05 | 2015-09-08 | 2015-08-05 | 2015-09-08
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND3703 | MHC: REPLACE SRVC ENTRANCE CABLES & DUCTBANK - SANDY CTRY E | 4 | ORIGINAL EQUIP & FURNISHING | 2015-09-09 | 2015-09-18 | 2015-09-09 | 2015-09-18
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND3703 | MHC: REPLACE SRVC ENTRANCE CABLES & DUCTBANK - SANDY CTRY E | 5 | SUBSTANTIAL COMPLETION | 2015-09-19 | 2015-10-03 | 2015-09-19 | 2015-10-03
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND3703 | MHC: REPLACE SRVC ENTRANCE CABLES & DUCTBANK - SANDY CTRY E | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-10-04 | 2019-10-08 | 2015-10-04 | 2019-10-08
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND3705 | METROPOLITAN HOSPITAL FLOOD MITIGATION SYSTEM | 1 | DESIGN | 2016-07-01 | 2016-07-20 | 2020-03-23 | 2023-04-11
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND3705 | METROPOLITAN HOSPITAL FLOOD MITIGATION SYSTEM | 2 | BID AWARD AND REGISTER CONTRCT | 2016-07-21 | 2016-08-04 | 2023-04-12 | 2023-04-26
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND3705 | METROPOLITAN HOSPITAL FLOOD MITIGATION SYSTEM | 3 | CONSTRUCTION | 2016-08-05 | 2016-09-08 | 2023-04-27 | 2023-05-31
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND3705 | METROPOLITAN HOSPITAL FLOOD MITIGATION SYSTEM | 4 | ORIGINAL EQUIP & FURNISHING | 2016-09-09 | 2016-09-18 | 2023-06-01 | 2023-06-10
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND3705 | METROPOLITAN HOSPITAL FLOOD MITIGATION SYSTEM | 5 | SUBSTANTIAL COMPLETION | 2016-09-19 | 2016-10-03 | 2023-06-11 | 2023-06-25
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND3705 | METROPOLITAN HOSPITAL FLOOD MITIGATION SYSTEM | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-10-04 | 2016-10-08 | 2023-06-26 | 2023-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND6701 | COLER : DESIGN & CONSTRUCTION FOR NEW GENERATOR | 1 | DESIGN | 2016-01-01 | 2016-01-20 | 2016-01-01 | 2016-01-20
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND6701 | COLER : DESIGN & CONSTRUCTION FOR NEW GENERATOR | 2 | BID AWARD AND REGISTER CONTRCT | 2015-09-12 | 2016-06-30 | 2015-09-12 | 2016-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND6701 | COLER : DESIGN & CONSTRUCTION FOR NEW GENERATOR | 3 | CONSTRUCTION | 2016-07-01 | 2017-06-30 | 2016-07-01 | 2017-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND6701 | COLER : DESIGN & CONSTRUCTION FOR NEW GENERATOR | 4 | ORIGINAL EQUIP & FURNISHING | 2017-07-01 | 2020-06-30 | 2017-07-01 | 2020-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND6701 | COLER : DESIGN & CONSTRUCTION FOR NEW GENERATOR | 5 | SUBSTANTIAL COMPLETION | 2020-07-01 | 2020-06-30 | 2020-07-01 | 2020-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND6701 | COLER : DESIGN & CONSTRUCTION FOR NEW GENERATOR | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-07-01 | 2020-07-05 | 2020-07-01 | 2029-06-28
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND6702 | COLER : DESIGN & CONSTRUCTION OF NEW LIGHTING | 1 | DESIGN | 2016-01-01 | 2016-01-20 | 2016-01-01 | 2016-01-20
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND6702 | COLER : DESIGN & CONSTRUCTION OF NEW LIGHTING | 2 | BID AWARD AND REGISTER CONTRCT | 2016-01-21 | 2016-06-30 | 2016-01-21 | 2016-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND6702 | COLER : DESIGN & CONSTRUCTION OF NEW LIGHTING | 3 | CONSTRUCTION | 2016-07-01 | 2017-06-30 | 2016-07-01 | 2017-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND6702 | COLER : DESIGN & CONSTRUCTION OF NEW LIGHTING | 4 | ORIGINAL EQUIP & FURNISHING | 2017-07-01 | 2020-06-30 | 2017-07-01 | 2020-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND6702 | COLER : DESIGN & CONSTRUCTION OF NEW LIGHTING | 5 | SUBSTANTIAL COMPLETION | 2020-07-01 | 2020-06-30 | 2020-07-01 | 2020-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND6702 | COLER : DESIGN & CONSTRUCTION OF NEW LIGHTING | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-07-01 | 2020-07-05 | 2020-07-01 | 2029-06-28
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND6703 | COLER : DESIGN & CONSTRUCTION OF ELECTRICAL PANELS | 1 | DESIGN | 2016-01-01 | 2016-01-20 | 2016-01-01 | 2016-01-20
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND6703 | COLER : DESIGN & CONSTRUCTION OF ELECTRICAL PANELS | 2 | BID AWARD AND REGISTER CONTRCT | 2016-01-21 | 2016-06-30 | 2016-01-21 | 2016-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND6703 | COLER : DESIGN & CONSTRUCTION OF ELECTRICAL PANELS | 3 | CONSTRUCTION | 2016-07-01 | 2017-06-30 | 2016-07-01 | 2017-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND6703 | COLER : DESIGN & CONSTRUCTION OF ELECTRICAL PANELS | 4 | ORIGINAL EQUIP & FURNISHING | 2017-07-01 | 2020-06-30 | 2017-07-01 | 2020-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND6703 | COLER : DESIGN & CONSTRUCTION OF ELECTRICAL PANELS | 5 | SUBSTANTIAL COMPLETION | 2020-07-01 | 2020-06-30 | 2020-07-01 | 2020-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND6703 | COLER : DESIGN & CONSTRUCTION OF ELECTRICAL PANELS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-07-01 | 2020-07-05 | 2020-07-01 | 2029-06-28
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND6704 | COLER : AUDITORIUM DESIGN AND CONSTRUCTION MANAGEMENT | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-09-28 | 2016-07-01 | 2016-09-28
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND6704 | COLER : AUDITORIUM DESIGN AND CONSTRUCTION MANAGEMENT | 2 | PRELIMINARY DESIGN | 2016-09-29 | 2017-01-26 | 2016-09-29 | 2017-01-26
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND6704 | COLER : AUDITORIUM DESIGN AND CONSTRUCTION MANAGEMENT | 3 | FINAL DESIGN | 2017-01-27 | 2017-07-25 | 2017-01-27 | 2017-07-25
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND6704 | COLER : AUDITORIUM DESIGN AND CONSTRUCTION MANAGEMENT | 4 | BID AWARD AND REGISTER CONTRCT | 2017-07-26 | 2017-10-23 | 2017-07-26 | 2017-10-23
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND6704 | COLER : AUDITORIUM DESIGN AND CONSTRUCTION MANAGEMENT | 5 | CONSTRUCTION TO 25% | 2017-10-24 | 2018-02-20 | 2017-10-24 | 2018-02-20
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND6704 | COLER : AUDITORIUM DESIGN AND CONSTRUCTION MANAGEMENT | 6 | CONSTRUCTION TO 50% | 2018-02-21 | 2018-06-20 | 2018-02-21 | 2018-06-20
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND6704 | COLER : AUDITORIUM DESIGN AND CONSTRUCTION MANAGEMENT | 7 | CONSTRUCTION TO 75% | 2018-06-21 | 2018-10-18 | 2018-06-21 | 2018-10-18
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND6704 | COLER : AUDITORIUM DESIGN AND CONSTRUCTION MANAGEMENT | 8 | ORIGINAL EQUIP & FURNISHING | 2018-10-19 | 2019-01-16 | 2018-10-19 | 2020-01-16
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND6704 | COLER : AUDITORIUM DESIGN AND CONSTRUCTION MANAGEMENT | 9 | SUBSTANTIAL COMPLETION | 2019-01-17 | 2019-03-17 | 2020-01-17 | 2020-03-16
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND6704 | COLER : AUDITORIUM DESIGN AND CONSTRUCTION MANAGEMENT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-03-18 | 2019-04-16 | 2020-03-17 | 2020-04-16
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND6705 | COLER : Specialty Hospital First Floor Design | 1 | DESIGN | 2016-07-01 | 2016-07-20 | 2019-07-01 | 2019-07-20
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND6705 | COLER : Specialty Hospital First Floor Design | 2 | BID AWARD AND REGISTER CONTRCT | 2016-07-21 | 2016-08-04 | 2019-07-21 | 2019-08-04
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND6705 | COLER : Specialty Hospital First Floor Design | 3 | CONSTRUCTION | 2016-08-05 | 2016-09-08 | 2019-08-05 | 2019-09-08
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND6705 | COLER : Specialty Hospital First Floor Design | 4 | ORIGINAL EQUIP & FURNISHING | 2016-09-09 | 2016-09-18 | 2019-09-09 | 2019-09-18
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND6705 | COLER : Specialty Hospital First Floor Design | 5 | SUBSTANTIAL COMPLETION | 2016-09-19 | 2016-10-03 | 2019-09-19 | 2019-10-03
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND6705 | COLER : Specialty Hospital First Floor Design | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-10-04 | 2016-10-08 | 2019-10-04 | 2025-10-08
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND6706 | COLER : DESIGN & CONSTRUCTION FOR FIRE PUMP | 1 | DESIGN | 2016-07-01 | 2016-07-20 | 2019-07-01 | 2019-07-20
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND6706 | COLER : DESIGN & CONSTRUCTION FOR FIRE PUMP | 2 | BID AWARD AND REGISTER CONTRCT | 2016-07-21 | 2016-08-04 | 2019-07-21 | 2019-08-04
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND6706 | COLER : DESIGN & CONSTRUCTION FOR FIRE PUMP | 3 | CONSTRUCTION | 2016-08-05 | 2016-09-08 | 2019-08-05 | 2019-09-08
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND6706 | COLER : DESIGN & CONSTRUCTION FOR FIRE PUMP | 4 | ORIGINAL EQUIP & FURNISHING | 2016-09-09 | 2016-09-18 | 2019-09-09 | 2019-09-18
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND6706 | COLER : DESIGN & CONSTRUCTION FOR FIRE PUMP | 5 | SUBSTANTIAL COMPLETION | 2016-09-19 | 2016-10-03 | 2019-09-19 | 2019-10-03
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND6706 | COLER : DESIGN & CONSTRUCTION FOR FIRE PUMP | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-10-04 | 2016-10-08 | 2019-10-04 | 2025-10-08
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDCD14 | PIER 76 ELECTRICAL CONDUIT | 1 | DEVELOP SCOPE | 2016-06-30 | 2016-09-27 | 2016-06-30 | 2020-07-19
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDCD14 | PIER 76 ELECTRICAL CONDUIT | 2 | PRELIMINARY DESIGN | 2016-09-28 | 2017-01-25 | 2020-07-20 | 2020-08-03
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDCD14 | PIER 76 ELECTRICAL CONDUIT | 3 | FINAL DESIGN | 2017-01-26 | 2017-05-25 | 2020-08-04 | 2020-09-07
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDCD14 | PIER 76 ELECTRICAL CONDUIT | 4 | BID AWARD AND REGISTER CONTRCT | 2017-05-26 | 2017-11-21 | 2020-09-08 | 2020-09-17
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDCD14 | PIER 76 ELECTRICAL CONDUIT | 5 | CONSTRUCTION TO 25% | 2017-11-22 | 2018-03-21 | 2020-09-18 | 2020-10-02
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDCD14 | PIER 76 ELECTRICAL CONDUIT | 6 | CONSTRUCTION TO 50% | 2018-03-22 | 2018-07-19 | 2020-10-03 | 2020-10-07
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDCD14 | PIER 76 ELECTRICAL CONDUIT | 7 | CONSTRUCTION TO 75% | 2018-07-20 | 2018-11-16 | 2020-10-03 | 2020-10-07
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDCD14 | PIER 76 ELECTRICAL CONDUIT | 8 | ORIGINAL EQUIP & FURNISHING | 2018-11-17 | 2019-02-14 | 2020-10-03 | 2020-10-07
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDCD14 | PIER 76 ELECTRICAL CONDUIT | 9 | SUBSTANTIAL COMPLETION | 2019-02-15 | 2019-04-15 | 2020-10-03 | 2020-10-07
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDCD14 | PIER 76 ELECTRICAL CONDUIT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-04-16 | 2019-05-15 | 2020-10-03 | 2020-10-07
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDCD15 | PIER 36 ELECTRICAL CONDUIT | 1 | DEVELOP SCOPE | 2016-06-30 | 2016-09-27 | 2016-06-30 | 2020-07-19
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDCD15 | PIER 36 ELECTRICAL CONDUIT | 2 | PRELIMINARY DESIGN | 2016-09-28 | 2017-01-25 | 2020-07-20 | 2020-08-03
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDCD15 | PIER 36 ELECTRICAL CONDUIT | 3 | FINAL DESIGN | 2017-01-26 | 2017-05-25 | 2020-08-04 | 2020-09-07
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDCD15 | PIER 36 ELECTRICAL CONDUIT | 4 | BID AWARD AND REGISTER CONTRCT | 2017-05-26 | 2017-11-21 | 2020-09-08 | 2020-09-17
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDCD15 | PIER 36 ELECTRICAL CONDUIT | 5 | CONSTRUCTION TO 25% | 2017-11-22 | 2018-03-21 | 2020-09-18 | 2020-10-02
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDCD15 | PIER 36 ELECTRICAL CONDUIT | 6 | CONSTRUCTION TO 50% | 2018-03-22 | 2018-07-19 | 2020-10-03 | 2020-10-07
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDCD15 | PIER 36 ELECTRICAL CONDUIT | 7 | CONSTRUCTION TO 75% | 2018-07-20 | 2018-11-16 | 2020-10-03 | 2020-10-07
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDCD15 | PIER 36 ELECTRICAL CONDUIT | 8 | ORIGINAL EQUIP & FURNISHING | 2018-11-17 | 2019-02-14 | 2020-10-03 | 2020-10-07
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDCD15 | PIER 36 ELECTRICAL CONDUIT | 9 | SUBSTANTIAL COMPLETION | 2019-02-15 | 2019-04-15 | 2020-10-03 | 2020-10-07
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDCD15 | PIER 36 ELECTRICAL CONDUIT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-04-16 | 2019-05-15 | 2020-10-03 | 2020-10-07
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDHWMO | Reconstruction of Moore Street- Hurricane Sandy | 1 | DEVELOP SCOPE | 2014-06-01 | 2014-08-29 | 2014-06-01 | 2014-08-29
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDHWMO | Reconstruction of Moore Street- Hurricane Sandy | 2 | PRELIMINARY DESIGN | 2014-08-30 | 2014-12-27 | 2014-08-30 | 2014-12-27
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDHWMO | Reconstruction of Moore Street- Hurricane Sandy | 3 | FINAL DESIGN | 2014-12-28 | 2015-06-25 | 2014-12-28 | 2015-06-25
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDHWMO | Reconstruction of Moore Street- Hurricane Sandy | 4 | BID AWARD AND REGISTER CONTRCT | 2015-06-26 | 2015-09-23 | 2015-06-26 | 2015-09-23
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDHWMO | Reconstruction of Moore Street- Hurricane Sandy | 5 | CONSTRUCTION TO 25% | 2015-09-24 | 2016-01-21 | 2015-09-24 | 2016-01-21
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDHWMO | Reconstruction of Moore Street- Hurricane Sandy | 6 | CONSTRUCTION TO 50% | 2016-01-22 | 2016-05-20 | 2016-01-22 | 2016-05-20
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDHWMO | Reconstruction of Moore Street- Hurricane Sandy | 7 | CONSTRUCTION TO 75% | 2016-05-21 | 2016-09-17 | 2016-05-21 | 2016-09-17
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDHWMO | Reconstruction of Moore Street- Hurricane Sandy | 8 | ORIGINAL EQUIP & FURNISHING | 2016-09-18 | 2016-12-16 | 2016-09-18 | 2016-12-16
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDHWMO | Reconstruction of Moore Street- Hurricane Sandy | 9 | SUBSTANTIAL COMPLETION | 2016-12-17 | 2017-02-14 | 2016-12-17 | 2017-02-14
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDHWMO | Reconstruction of Moore Street- Hurricane Sandy | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-02-15 | 2017-03-16 | 2017-02-15 | 2022-03-16
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDR2BRG | Construction of Flex Barges | 1 | DESIGN | 2016-07-01 | 2016-07-20 | 2016-07-01 | 2016-07-20
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDR2BRG | Construction of Flex Barges | 2 | BID AWARD AND REGISTER CONTRCT | 2016-07-21 | 2016-08-04 | 2016-07-21 | 2016-08-04
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDR2BRG | Construction of Flex Barges | 3 | CONSTRUCTION | 2016-08-05 | 2016-09-08 | 2016-08-05 | 2016-09-08
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDR2BRG | Construction of Flex Barges | 4 | ORIGINAL EQUIP & FURNISHING | 2016-09-09 | 2016-09-18 | 2016-09-09 | 2016-09-18
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDR2BRG | Construction of Flex Barges | 5 | SUBSTANTIAL COMPLETION | 2016-09-19 | 2016-10-03 | 2016-09-19 | 2016-10-03
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDR2BRG | Construction of Flex Barges | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-10-04 | 2020-10-08 | 2016-10-04 | 2022-10-08
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDRLE34 | FA Resiliency - Land Hardening E 34 street | 1 | DESIGN | 2016-07-01 | 2016-07-20 | 2016-07-01 | 2016-07-20
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDRLE34 | FA Resiliency - Land Hardening E 34 street | 2 | BID AWARD AND REGISTER CONTRCT | 2016-07-21 | 2016-08-04 | 2016-07-21 | 2016-08-04
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDRLE34 | FA Resiliency - Land Hardening E 34 street | 3 | CONSTRUCTION | 2016-08-05 | 2016-09-08 | 2016-08-05 | 2016-09-08
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDRLE34 | FA Resiliency - Land Hardening E 34 street | 4 | ORIGINAL EQUIP & FURNISHING | 2016-09-09 | 2016-09-18 | 2016-09-09 | 2016-09-18
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDRLE34 | FA Resiliency - Land Hardening E 34 street | 5 | SUBSTANTIAL COMPLETION | 2016-09-19 | 2016-10-03 | 2016-09-19 | 2016-10-03
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDRLE34 | FA Resiliency - Land Hardening E 34 street | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-10-04 | 2020-10-08 | 2016-10-04 | 2022-10-08
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDTGI | Governors Island Hurricane Sandy Repairs | 1 | DESIGN | 2016-01-01 | 2016-01-20 | 2016-01-01 | 2016-01-20
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDTGI | Governors Island Hurricane Sandy Repairs | 2 | BID AWARD AND REGISTER CONTRCT | 2016-01-21 | 2016-06-30 | 2016-01-21 | 2016-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDTGI | Governors Island Hurricane Sandy Repairs | 3 | CONSTRUCTION | 2016-07-01 | 2017-06-30 | 2016-07-01 | 2017-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDTGI | Governors Island Hurricane Sandy Repairs | 4 | ORIGINAL EQUIP & FURNISHING | 2017-07-01 | 2020-06-30 | 2017-07-01 | 2020-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDTGI | Governors Island Hurricane Sandy Repairs | 5 | SUBSTANTIAL COMPLETION | 2020-07-01 | 2020-06-30 | 2020-07-01 | 2020-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDTGI | Governors Island Hurricane Sandy Repairs | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-07-01 | 2020-07-05 | 2020-07-01 | 2020-07-05
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDTGIBS | Governors Island - Hurricane Sandy Building 110 Restoration | 1 | DESIGN | 2016-01-01 | 2016-01-20 | 2016-01-01 | 2016-01-20
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDTGIBS | Governors Island - Hurricane Sandy Building 110 Restoration | 2 | BID AWARD AND REGISTER CONTRCT | 2016-01-21 | 2016-06-30 | 2016-01-21 | 2016-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDTGIBS | Governors Island - Hurricane Sandy Building 110 Restoration | 3 | CONSTRUCTION | 2016-07-01 | 2017-06-30 | 2016-07-01 | 2017-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDTGIBS | Governors Island - Hurricane Sandy Building 110 Restoration | 4 | ORIGINAL EQUIP & FURNISHING | 2017-07-01 | 2020-06-30 | 2017-07-01 | 2020-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDTGIBS | Governors Island - Hurricane Sandy Building 110 Restoration | 5 | SUBSTANTIAL COMPLETION | 2020-07-01 | 2020-06-30 | 2020-07-01 | 2020-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDTGIBS | Governors Island - Hurricane Sandy Building 110 Restoration | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-07-01 | 2020-07-05 | 2020-07-01 | 2020-07-05
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDTGIEL | Governors Island - Hurricane Sandy Electrical Repairs | 1 | DESIGN | 2016-01-01 | 2016-01-20 | 2016-01-01 | 2016-01-20
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDTGIEL | Governors Island - Hurricane Sandy Electrical Repairs | 2 | BID AWARD AND REGISTER CONTRCT | 2016-01-21 | 2016-06-30 | 2016-01-21 | 2016-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDTGIEL | Governors Island - Hurricane Sandy Electrical Repairs | 3 | CONSTRUCTION | 2016-07-01 | 2017-06-30 | 2016-07-01 | 2017-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDTGIEL | Governors Island - Hurricane Sandy Electrical Repairs | 4 | ORIGINAL EQUIP & FURNISHING | 2017-07-01 | 2020-06-30 | 2017-07-01 | 2020-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDTGIEL | Governors Island - Hurricane Sandy Electrical Repairs | 5 | SUBSTANTIAL COMPLETION | 2020-07-01 | 2020-06-30 | 2020-07-01 | 2020-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDTGIEL | Governors Island - Hurricane Sandy Electrical Repairs | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-07-01 | 2020-07-05 | 2020-07-01 | 2020-07-05
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDY3-01 | HIghline M&O Facility Sandy Repairs | 1 | DESIGN | 2016-01-01 | 2016-01-20 | 2016-01-01 | 2016-01-20
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDY3-01 | HIghline M&O Facility Sandy Repairs | 2 | BID AWARD AND REGISTER CONTRCT | 2016-01-21 | 2016-06-30 | 2016-01-21 | 2016-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDY3-01 | HIghline M&O Facility Sandy Repairs | 3 | CONSTRUCTION | 2016-07-01 | 2017-06-30 | 2016-07-01 | 2017-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDY3-01 | HIghline M&O Facility Sandy Repairs | 4 | ORIGINAL EQUIP & FURNISHING | 2017-07-01 | 2020-06-30 | 2017-07-01 | 2020-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDY3-01 | HIghline M&O Facility Sandy Repairs | 5 | SUBSTANTIAL COMPLETION | 2020-07-01 | 2020-06-30 | 2020-07-01 | 2020-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDY3-01 | HIghline M&O Facility Sandy Repairs | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-07-01 | 2020-07-05 | 2020-07-01 | 2024-07-05
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SBSRELOCA | SBS FY18 Relocation to 1 Liberty Plaza | 1 | DESIGN | 2017-07-01 | 2017-07-20 | 2017-07-01 | 2020-07-20
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SBSRELOCA | SBS FY18 Relocation to 1 Liberty Plaza | 2 | BID AWARD AND REGISTER CONTRCT | 2017-07-21 | 2017-08-04 | 2020-07-21 | 2020-08-04
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SBSRELOCA | SBS FY18 Relocation to 1 Liberty Plaza | 3 | CONSTRUCTION | 2017-08-05 | 2017-09-08 | 2020-08-05 | 2020-09-08
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SBSRELOCA | SBS FY18 Relocation to 1 Liberty Plaza | 4 | ORIGINAL EQUIP & FURNISHING | 2017-09-09 | 2017-09-18 | 2020-09-09 | 2020-09-18
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SBSRELOCA | SBS FY18 Relocation to 1 Liberty Plaza | 5 | SUBSTANTIAL COMPLETION | 2017-09-19 | 2017-10-03 | 2020-09-19 | 2020-10-03
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SBSRELOCA | SBS FY18 Relocation to 1 Liberty Plaza | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-10-04 | 2017-10-08 | 2020-10-04 | 2020-10-08
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SKYPORT | Skyport Garage and Marina Rehabilitation | 1 | DESIGN | 2017-07-01 | 2017-07-20 | 2019-03-23 | 2019-04-11
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SKYPORT | Skyport Garage and Marina Rehabilitation | 2 | BID AWARD AND REGISTER CONTRCT | 2017-07-21 | 2017-08-04 | 2019-04-12 | 2019-04-26
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SKYPORT | Skyport Garage and Marina Rehabilitation | 3 | CONSTRUCTION | 2017-08-05 | 2017-09-08 | 2019-04-27 | 2019-05-31
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SKYPORT | Skyport Garage and Marina Rehabilitation | 4 | ORIGINAL EQUIP & FURNISHING | 2017-09-09 | 2017-09-18 | 2019-06-01 | 2019-06-10
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SKYPORT | Skyport Garage and Marina Rehabilitation | 5 | SUBSTANTIAL COMPLETION | 2017-09-19 | 2017-10-03 | 2019-06-11 | 2019-06-25
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SKYPORT | Skyport Garage and Marina Rehabilitation | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-10-04 | 2017-10-08 | 2019-06-26 | 2023-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SOLAR2 | CEC Stuyvesant Cove Inc.-Construction of Solar 2 | 1 | DESIGN | 2015-06-30 | 2015-07-19 | 2015-06-30 | 2015-07-19
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SOLAR2 | CEC Stuyvesant Cove Inc.-Construction of Solar 2 | 2 | BID AWARD AND REGISTER CONTRCT | 2015-07-20 | 2015-08-03 | 2015-07-20 | 2015-08-03
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SOLAR2 | CEC Stuyvesant Cove Inc.-Construction of Solar 2 | 3 | CONSTRUCTION | 2015-08-04 | 2015-09-07 | 2015-08-04 | 2015-09-07
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SOLAR2 | CEC Stuyvesant Cove Inc.-Construction of Solar 2 | 4 | ORIGINAL EQUIP & FURNISHING | 2015-09-08 | 2015-09-17 | 2015-09-08 | 2015-09-17
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SOLAR2 | CEC Stuyvesant Cove Inc.-Construction of Solar 2 | 5 | SUBSTANTIAL COMPLETION | 2015-09-18 | 2015-10-02 | 2015-09-18 | 2015-10-02
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SOLAR2 | CEC Stuyvesant Cove Inc.-Construction of Solar 2 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-10-03 | 2015-10-07 | 2015-10-03 | 2025-10-07
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SSRECON | South Street Reconstruction | 1 | DESIGN | 2015-06-30 | 2015-07-19 | 2015-06-30 | 2020-07-19
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SSRECON | South Street Reconstruction | 2 | BID AWARD AND REGISTER CONTRCT | 2015-07-20 | 2015-08-03 | 2020-07-20 | 2020-08-03
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SSRECON | South Street Reconstruction | 3 | CONSTRUCTION | 2015-08-04 | 2015-09-07 | 2020-08-04 | 2023-07-01
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SSRECON | South Street Reconstruction | 4 | ORIGINAL EQUIP & FURNISHING | 2015-09-08 | 2015-09-17 | 2023-07-02 | 2023-07-01
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SSRECON | South Street Reconstruction | 5 | SUBSTANTIAL COMPLETION | 2015-09-18 | 2015-10-02 | 2023-07-02 | 2023-07-01
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SSRECON | South Street Reconstruction | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-10-03 | 2015-10-07 | 2023-07-02 | 2028-07-06
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SSSPIER16 | South Street Seaport - Pier 16 Rehab | 1 | DESIGN | 2010-01-01 | 2012-01-20 | 2010-01-01 | 2012-01-20
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SSSPIER16 | South Street Seaport - Pier 16 Rehab | 2 | BID AWARD AND REGISTER CONTRCT | 2012-01-21 | 2012-01-20 | 2012-01-21 | 2012-01-20
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SSSPIER16 | South Street Seaport - Pier 16 Rehab | 3 | CONSTRUCTION | 2012-01-21 | 2014-01-20 | 2012-01-21 | 2014-01-20
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SSSPIER16 | South Street Seaport - Pier 16 Rehab | 4 | ORIGINAL EQUIP & FURNISHING | 2014-01-21 | 2014-01-20 | 2014-01-21 | 2014-01-20
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SSSPIER16 | South Street Seaport - Pier 16 Rehab | 5 | SUBSTANTIAL COMPLETION | 2014-01-21 | 2014-01-20 | 2014-01-21 | 2020-01-20
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SSSPIER16 | South Street Seaport - Pier 16 Rehab | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-01-21 | 2014-01-25 | 2020-01-21 | 2025-06-29
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | STUYBULK2 | Stuyvesant Cove Park Bulkhead Park Repair | 1 | DESIGN | 2018-07-01 | 2018-07-20 | 2018-07-01 | 2018-07-20
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | STUYBULK2 | Stuyvesant Cove Park Bulkhead Park Repair | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-21 | 2018-08-04 | 2018-07-21 | 2018-08-04
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | STUYBULK2 | Stuyvesant Cove Park Bulkhead Park Repair | 3 | CONSTRUCTION | 2018-08-05 | 2018-09-08 | 2018-08-05 | 2018-09-08
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | STUYBULK2 | Stuyvesant Cove Park Bulkhead Park Repair | 4 | ORIGINAL EQUIP & FURNISHING | 2018-09-09 | 2018-09-18 | 2018-09-09 | 2018-09-18
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | STUYBULK2 | Stuyvesant Cove Park Bulkhead Park Repair | 5 | SUBSTANTIAL COMPLETION | 2018-09-19 | 2021-10-03 | 2018-09-19 | 2021-10-03
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | STUYBULK2 | Stuyvesant Cove Park Bulkhead Park Repair | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-10-04 | 2021-10-08 | 2021-10-04 | 2021-10-08
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | TINMARKET | New Market Tin Building Demolition | 1 | DESIGN | 2017-07-01 | 2017-07-20 | 2019-03-23 | 2020-04-11
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | TINMARKET | New Market Tin Building Demolition | 2 | BID AWARD AND REGISTER CONTRCT | 2017-07-21 | 2017-08-04 | 2020-04-12 | 2020-04-26
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | TINMARKET | New Market Tin Building Demolition | 3 | CONSTRUCTION | 2017-08-05 | 2017-09-08 | 2020-04-27 | 2020-05-31
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | TINMARKET | New Market Tin Building Demolition | 4 | ORIGINAL EQUIP & FURNISHING | 2017-09-09 | 2017-09-18 | 2020-06-01 | 2020-06-10
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | TINMARKET | New Market Tin Building Demolition | 5 | SUBSTANTIAL COMPLETION | 2017-09-19 | 2017-10-03 | 2020-06-11 | 2020-06-25
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | TINMARKET | New Market Tin Building Demolition | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-10-04 | 2017-10-08 | 2020-06-26 | 2026-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | W125TRANS | West 125th Street/Manhattanville | 1 | DESIGN | 2004-11-01 | 2004-11-20 | 2007-11-02 | 2007-11-21
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | W125TRANS | West 125th Street/Manhattanville | 2 | BID AWARD AND REGISTER CONTRCT | 2004-11-21 | 2004-12-05 | 2007-11-22 | 2007-12-06
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | W125TRANS | West 125th Street/Manhattanville | 3 | CONSTRUCTION | 2004-12-06 | 2008-06-30 | 2007-12-07 | 2020-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | W125TRANS | West 125th Street/Manhattanville | 4 | ORIGINAL EQUIP & FURNISHING | 2008-07-01 | 2008-06-30 | 2020-07-01 | 2020-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | W125TRANS | West 125th Street/Manhattanville | 5 | SUBSTANTIAL COMPLETION | 2008-07-01 | 2008-06-30 | 2020-07-01 | 2020-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | W125TRANS | West 125th Street/Manhattanville | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-07-01 | 2008-07-05 | 2020-07-01 | 2020-07-05
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | WATERSIDE | WATERSIDE PIER & STUYVESANT COVE AMENITIES | 1 | DESIGN | 2016-01-01 | 2016-01-20 | 2016-01-01 | 2016-01-20
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | WATERSIDE | WATERSIDE PIER & STUYVESANT COVE AMENITIES | 2 | BID AWARD AND REGISTER CONTRCT | 2016-01-21 | 2016-06-30 | 2016-01-21 | 2016-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | WATERSIDE | WATERSIDE PIER & STUYVESANT COVE AMENITIES | 3 | CONSTRUCTION | 2016-07-01 | 2017-06-30 | 2016-07-01 | 2017-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | WATERSIDE | WATERSIDE PIER & STUYVESANT COVE AMENITIES | 4 | ORIGINAL EQUIP & FURNISHING | 2017-07-01 | 2020-06-30 | 2017-07-01 | 2020-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | WATERSIDE | WATERSIDE PIER & STUYVESANT COVE AMENITIES | 5 | SUBSTANTIAL COMPLETION | 2020-07-01 | 2020-06-30 | 2020-07-01 | 2020-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | WATERSIDE | WATERSIDE PIER & STUYVESANT COVE AMENITIES | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-07-01 | 2020-07-05 | 2020-07-01 | 2026-07-05
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | WATERST | Water Street Corridor Streetscape Improvements | 1 | DESIGN | 2016-01-01 | 2016-01-20 | 2016-01-01 | 2016-01-20
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | WATERST | Water Street Corridor Streetscape Improvements | 2 | BID AWARD AND REGISTER CONTRCT | 2016-01-21 | 2016-06-30 | 2016-01-21 | 2016-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | WATERST | Water Street Corridor Streetscape Improvements | 3 | CONSTRUCTION | 2016-07-01 | 2017-06-30 | 2016-07-01 | 2017-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | WATERST | Water Street Corridor Streetscape Improvements | 4 | ORIGINAL EQUIP & FURNISHING | 2017-07-01 | 2020-06-30 | 2017-07-01 | 2020-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | WATERST | Water Street Corridor Streetscape Improvements | 5 | SUBSTANTIAL COMPLETION | 2020-07-01 | 2020-06-30 | 2020-07-01 | 2020-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | WATERST | Water Street Corridor Streetscape Improvements | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-07-01 | 2020-07-05 | 2020-07-01 | 2020-07-05
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | WHARLMPK | West Harlem Piers Park | 1 | DESIGN | 2019-07-01 | 2019-07-20 | 2018-07-01 | 2018-07-20
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | WHARLMPK | West Harlem Piers Park | 2 | BID AWARD AND REGISTER CONTRCT | 2019-07-21 | 2019-08-04 | 2018-07-21 | 2018-08-04
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | WHARLMPK | West Harlem Piers Park | 3 | CONSTRUCTION | 2019-08-05 | 2019-09-08 | 2018-08-05 | 2018-09-08
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | WHARLMPK | West Harlem Piers Park | 4 | ORIGINAL EQUIP & FURNISHING | 2019-09-09 | 2019-09-18 | 2018-09-09 | 2018-09-18
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | WHARLMPK | West Harlem Piers Park | 5 | SUBSTANTIAL COMPLETION | 2019-09-19 | 2019-10-03 | 2018-09-19 | 2018-10-03
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | WHARLMPK | West Harlem Piers Park | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-10-04 | 2019-10-08 | 2022-10-04 | 2025-11-01
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | WHITEHALL | Whitehall Terminal Reconstruction, Manhattan | 1 | DESIGN | 2000-09-02 | 2007-07-01 | 2004-03-01 | 2004-04-01
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | WHITEHALL | Whitehall Terminal Reconstruction, Manhattan | 2 | BID AWARD AND REGISTER CONTRCT | 2007-07-02 | 2007-07-01 | 2004-04-02 | 2004-04-01
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | WHITEHALL | Whitehall Terminal Reconstruction, Manhattan | 3 | CONSTRUCTION | 2007-07-02 | 2007-07-01 | 2004-09-01 | 2006-09-01
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | WHITEHALL | Whitehall Terminal Reconstruction, Manhattan | 4 | ORIGINAL EQUIP & FURNISHING | 1999-09-01 | 2007-09-01 | 1999-09-01 | 2017-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | WHITEHALL | Whitehall Terminal Reconstruction, Manhattan | 5 | SUBSTANTIAL COMPLETION | 2007-09-02 | 2007-09-01 | 2017-07-01 | 2017-06-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | WHITEHALL | Whitehall Terminal Reconstruction, Manhattan | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2007-09-02 | 2013-12-31 | 2017-07-01 | 2023-10-30
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | WL34STHL | EAST 34TH STREET HELIPORT SUBSTRUCTURE | 1 | DESIGN | 2020-07-01 | 2020-07-20 | 2020-07-01 | 2020-07-20
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | WL34STHL | EAST 34TH STREET HELIPORT SUBSTRUCTURE | 2 | BID AWARD AND REGISTER CONTRCT | 2020-07-21 | 2020-08-04 | 2020-07-21 | 2020-08-04
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | WL34STHL | EAST 34TH STREET HELIPORT SUBSTRUCTURE | 3 | CONSTRUCTION | 2020-08-05 | 2020-09-08 | 2020-08-05 | 2020-09-08
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | WL34STHL | EAST 34TH STREET HELIPORT SUBSTRUCTURE | 4 | ORIGINAL EQUIP & FURNISHING | 2020-09-09 | 2020-09-18 | 2020-09-09 | 2020-09-18
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | WL34STHL | EAST 34TH STREET HELIPORT SUBSTRUCTURE | 5 | SUBSTANTIAL COMPLETION | 2020-09-19 | 2020-10-03 | 2020-09-19 | 2020-10-03
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | WL34STHL | EAST 34TH STREET HELIPORT SUBSTRUCTURE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-10-04 | 2020-10-08 | 2020-10-04 | 2020-10-08
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | WLWCLBWF | WATER CLUB WHARF | 1 | DESIGN | 2020-07-01 | 2020-07-20 | 2020-07-01 | 2020-07-20
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | WLWCLBWF | WATER CLUB WHARF | 2 | BID AWARD AND REGISTER CONTRCT | 2020-07-21 | 2020-08-04 | 2020-07-21 | 2020-08-04
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | WLWCLBWF | WATER CLUB WHARF | 3 | CONSTRUCTION | 2020-08-05 | 2020-09-08 | 2020-08-05 | 2020-09-08
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | WLWCLBWF | WATER CLUB WHARF | 4 | ORIGINAL EQUIP & FURNISHING | 2020-09-09 | 2020-09-18 | 2020-09-09 | 2020-09-18
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | WLWCLBWF | WATER CLUB WHARF | 5 | SUBSTANTIAL COMPLETION | 2020-09-19 | 2020-10-03 | 2020-09-19 | 2020-10-03
20201123 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | WLWCLBWF | WATER CLUB WHARF | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-10-04 | 2020-10-08 | 2020-10-04 | 2020-10-08
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM02USCC | (WHITE) UNION SETTLEMENT ASSOC. - COMM. CTR. RENOVATION | 1 | DESIGN | 2007-01-01 | 2007-06-29 | 2013-02-08 | 2017-05-08
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM02USCC | (WHITE) UNION SETTLEMENT ASSOC. - COMM. CTR. RENOVATION | 2 | BID AWARD AND REGISTER CONTRCT | 2007-06-30 | 2007-11-21 | 2017-05-09 | 2017-12-18
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM02USCC | (WHITE) UNION SETTLEMENT ASSOC. - COMM. CTR. RENOVATION | 3 | CONSTRUCTION | 2007-11-22 | 2008-11-20 | 2017-12-19 | 2018-11-29
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM02USCC | (WHITE) UNION SETTLEMENT ASSOC. - COMM. CTR. RENOVATION | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-11-21 | 2009-05-19 | 2017-12-19 | 2018-11-29
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM02USCC | (WHITE) UNION SETTLEMENT ASSOC. - COMM. CTR. RENOVATION | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-11-21 | 2009-05-19 | 2018-11-30 | 2021-06-21
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM06MHEL | Manhattanville Houses Elevators | 1 | DESIGN | 2007-01-01 | 2007-06-29 | 1995-07-03 | 1995-12-29
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM06MHEL | Manhattanville Houses Elevators | 2 | BID AWARD AND REGISTER CONTRCT | 2007-06-30 | 2007-11-21 | 1995-12-30 | 1996-05-22
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM06MHEL | Manhattanville Houses Elevators | 3 | CONSTRUCTION | 2007-11-22 | 2008-11-20 | 1996-05-23 | 1997-05-22
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM06MHEL | Manhattanville Houses Elevators | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-11-21 | 2009-05-19 | 1996-05-23 | 1997-05-22
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM06MHEL | Manhattanville Houses Elevators | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-11-21 | 2009-05-19 | 1997-05-23 | 2021-05-16
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM07CIDC | CITIZENS CARE DAY CARE - PLAYGROUND EQUIPMENT AND MATTING | 1 | DESIGN | 2007-01-01 | 2007-06-29 | 2007-01-01 | 2007-06-29
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM07CIDC | CITIZENS CARE DAY CARE - PLAYGROUND EQUIPMENT AND MATTING | 2 | BID AWARD AND REGISTER CONTRCT | 2007-06-30 | 2007-11-21 | 2007-06-30 | 2007-11-21
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM07CIDC | CITIZENS CARE DAY CARE - PLAYGROUND EQUIPMENT AND MATTING | 3 | CONSTRUCTION | 2007-11-22 | 2008-11-20 | 2007-11-22 | 2008-11-20
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM07CIDC | CITIZENS CARE DAY CARE - PLAYGROUND EQUIPMENT AND MATTING | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-11-21 | 2009-05-19 | 2007-11-22 | 2008-11-20
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM07CIDC | CITIZENS CARE DAY CARE - PLAYGROUND EQUIPMENT AND MATTING | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-11-21 | 2009-05-19 | 2008-11-21 | 2020-11-17
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM08HSST | HENRY STREET SETTLEMENT - GOOD COMPANIONS SR CTR RENOVATIONS | 1 | DESIGN | 2011-01-01 | 2011-06-29 | 2011-03-17 | 2017-12-07
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM08HSST | HENRY STREET SETTLEMENT - GOOD COMPANIONS SR CTR RENOVATIONS | 2 | BID AWARD AND REGISTER CONTRCT | 2011-06-30 | 2011-11-21 | 2017-12-08 | 2018-05-01
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM08HSST | HENRY STREET SETTLEMENT - GOOD COMPANIONS SR CTR RENOVATIONS | 3 | CONSTRUCTION | 2011-11-22 | 2012-11-20 | 2018-05-02 | 2019-05-01
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM08HSST | HENRY STREET SETTLEMENT - GOOD COMPANIONS SR CTR RENOVATIONS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-11-21 | 2013-05-19 | 2018-05-02 | 2019-05-01
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM08HSST | HENRY STREET SETTLEMENT - GOOD COMPANIONS SR CTR RENOVATIONS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-11-21 | 2013-05-19 | 2019-05-02 | 2021-04-30
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM08RUHI | RUTGERS HOUSES ENERGY INITIATIVES | 1 | DESIGN | 2008-03-01 | 2008-08-27 | 2008-03-01 | 2008-08-27
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM08RUHI | RUTGERS HOUSES ENERGY INITIATIVES | 2 | BID AWARD AND REGISTER CONTRCT | 2008-08-28 | 2009-01-19 | 2008-08-28 | 2009-01-19
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM08RUHI | RUTGERS HOUSES ENERGY INITIATIVES | 3 | CONSTRUCTION | 2009-01-20 | 2010-01-19 | 2009-01-20 | 2010-01-19
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM08RUHI | RUTGERS HOUSES ENERGY INITIATIVES | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2010-01-20 | 2010-07-18 | 2009-01-20 | 2010-01-19
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM08RUHI | RUTGERS HOUSES ENERGY INITIATIVES | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2010-01-20 | 2010-07-18 | 2010-01-20 | 2021-01-16
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM09FWSR | FT WASHINGTON SER FOR THE ELDERLY OFFICES, CLASSRM, COMP RM | 1 | DESIGN | 2009-01-01 | 2009-06-29 | 2015-10-19 | 2017-01-04
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM09FWSR | FT WASHINGTON SER FOR THE ELDERLY OFFICES, CLASSRM, COMP RM | 2 | BID AWARD AND REGISTER CONTRCT | 2009-06-30 | 2009-11-21 | 2017-01-05 | 2017-08-16
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM09FWSR | FT WASHINGTON SER FOR THE ELDERLY OFFICES, CLASSRM, COMP RM | 3 | CONSTRUCTION | 2009-11-22 | 2010-11-21 | 2017-08-17 | 2019-03-31
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM09FWSR | FT WASHINGTON SER FOR THE ELDERLY OFFICES, CLASSRM, COMP RM | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2010-11-22 | 2011-05-20 | 2017-08-17 | 2019-03-31
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM09FWSR | FT WASHINGTON SER FOR THE ELDERLY OFFICES, CLASSRM, COMP RM | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2010-11-22 | 2011-05-20 | 2019-04-01 | 2021-09-26
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM09SINB | STANLEY ISAACS NEIGHBORHOOD CENTER SENIOR CENTER KITCHEN | 2 | BID AWARD AND REGISTER CONTRCT | 2009-06-30 | 2009-11-21 | 2017-02-26 | 2017-07-15
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM09SINB | STANLEY ISAACS NEIGHBORHOOD CENTER SENIOR CENTER KITCHEN | 3 | CONSTRUCTION | 2009-11-22 | 2010-11-21 | 2017-07-16 | 2018-07-25
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM09SINB | STANLEY ISAACS NEIGHBORHOOD CENTER SENIOR CENTER KITCHEN | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2010-11-22 | 2011-05-20 | 2017-07-16 | 2018-07-25
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM09SINB | STANLEY ISAACS NEIGHBORHOOD CENTER SENIOR CENTER KITCHEN | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2010-11-22 | 2011-05-20 | 2018-07-26 | 2018-12-12
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM11VLFA | VLADECK HOUSES- GOOD COMPANIONS/HENRY ST, FIRE ALARM SYSTEM | 1 | DESIGN | 2011-01-01 | 2011-06-29 | 2011-03-17 | 2016-12-15
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM11VLFA | VLADECK HOUSES- GOOD COMPANIONS/HENRY ST, FIRE ALARM SYSTEM | 2 | BID AWARD AND REGISTER CONTRCT | 2011-06-30 | 2011-11-21 | 2016-12-16 | 2017-03-31
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM11VLFA | VLADECK HOUSES- GOOD COMPANIONS/HENRY ST, FIRE ALARM SYSTEM | 3 | CONSTRUCTION | 2011-11-22 | 2012-11-20 | 2017-04-01 | 2018-03-25
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM11VLFA | VLADECK HOUSES- GOOD COMPANIONS/HENRY ST, FIRE ALARM SYSTEM | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-11-21 | 2013-05-19 | 2017-04-01 | 2018-03-25
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM11VLFA | VLADECK HOUSES- GOOD COMPANIONS/HENRY ST, FIRE ALARM SYSTEM | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-11-21 | 2013-05-19 | 2018-03-26 | 2021-03-24
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM13CLEV | CLINTON HOUSES ELEVATOR REHABILITATION | 1 | DESIGN | 2013-01-01 | 2013-06-29 | 2012-09-01 | 2013-12-20
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM13CLEV | CLINTON HOUSES ELEVATOR REHABILITATION | 2 | BID AWARD AND REGISTER CONTRCT | 2013-06-30 | 2013-11-21 | 2013-12-21 | 2014-06-13
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM13CLEV | CLINTON HOUSES ELEVATOR REHABILITATION | 3 | CONSTRUCTION | 2013-11-22 | 2014-11-21 | 2014-06-14 | 2016-07-22
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM13CLEV | CLINTON HOUSES ELEVATOR REHABILITATION | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-11-22 | 2015-05-20 | 2014-06-14 | 2016-07-22
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM13CLEV | CLINTON HOUSES ELEVATOR REHABILITATION | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-11-22 | 2015-05-20 | 2016-07-23 | 2020-07-21
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM13DGPE | DOUGLASS HOUSES PLAYGROUND EQUIPMENT | 1 | DESIGN | 2013-01-01 | 2013-06-29 | 2013-09-04 | 2016-01-31
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM13DGPE | DOUGLASS HOUSES PLAYGROUND EQUIPMENT | 2 | BID AWARD AND REGISTER CONTRCT | 2013-06-30 | 2013-11-21 | 2016-02-01 | 2016-07-01
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM13DGPE | DOUGLASS HOUSES PLAYGROUND EQUIPMENT | 3 | CONSTRUCTION | 2013-11-22 | 2014-11-21 | 2016-07-02 | 2017-07-02
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM13DGPE | DOUGLASS HOUSES PLAYGROUND EQUIPMENT | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-11-22 | 2015-05-20 | 2016-07-02 | 2017-07-02
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM13DGPE | DOUGLASS HOUSES PLAYGROUND EQUIPMENT | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-11-22 | 2015-05-20 | 2017-07-03 | 2017-12-29
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM13HTET | HOLMES TOWER ENTRANCES AND LAYERED ACCESS CONTROLS | 1 | DESIGN | 2012-10-19 | 2013-04-16 | 2015-11-09 | 2016-05-06
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM13HTET | HOLMES TOWER ENTRANCES AND LAYERED ACCESS CONTROLS | 2 | BID AWARD AND REGISTER CONTRCT | 2013-04-17 | 2013-09-08 | 2016-05-07 | 2016-09-28
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM13HTET | HOLMES TOWER ENTRANCES AND LAYERED ACCESS CONTROLS | 3 | CONSTRUCTION | 2013-09-09 | 2014-09-08 | 2016-09-29 | 2017-09-28
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM13HTET | HOLMES TOWER ENTRANCES AND LAYERED ACCESS CONTROLS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-09-09 | 2015-03-07 | 2016-09-29 | 2017-09-28
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM13HTET | HOLMES TOWER ENTRANCES AND LAYERED ACCESS CONTROLS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-09-09 | 2015-03-07 | 2017-09-29 | 2020-09-27
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM14MNSE | METRO NORTH PLAZA SECURITY UPGRADES | 1 | DESIGN | 2013-10-31 | 2014-04-28 | 2013-10-31 | 2014-04-28
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM14MNSE | METRO NORTH PLAZA SECURITY UPGRADES | 2 | BID AWARD AND REGISTER CONTRCT | 2014-04-29 | 2014-09-20 | 2014-04-29 | 2014-09-20
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM14MNSE | METRO NORTH PLAZA SECURITY UPGRADES | 3 | CONSTRUCTION | 2014-09-21 | 2015-09-20 | 2014-09-21 | 2015-09-20
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM14MNSE | METRO NORTH PLAZA SECURITY UPGRADES | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-09-21 | 2016-03-18 | 2014-09-21 | 2015-09-20
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM14MNSE | METRO NORTH PLAZA SECURITY UPGRADES | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-09-21 | 2016-03-18 | 2015-09-21 | 2020-09-18
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15AMGD | 830 AMSTERDAM AVENUE PLAY AREAS | 2 | BID AWARD AND REGISTER CONTRCT | 2015-07-01 | 2015-11-22 | 2018-01-12 | 2018-06-05
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15AMGD | 830 AMSTERDAM AVENUE PLAY AREAS | 3 | CONSTRUCTION | 2015-11-23 | 2016-11-21 | 2018-06-06 | 2018-12-10
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15AMGD | 830 AMSTERDAM AVENUE PLAY AREAS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-11-22 | 2017-05-20 | 2018-06-06 | 2018-12-10
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15AMGD | 830 AMSTERDAM AVENUE PLAY AREAS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-11-22 | 2017-05-20 | 2018-12-11 | 2019-06-08
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15CVGR | CARVER GARDENS DAY CARE CENTER PLAYGROUND | 1 | DESIGN | 2015-01-02 | 2015-06-30 | 2015-08-14 | 2017-04-06
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15CVGR | CARVER GARDENS DAY CARE CENTER PLAYGROUND | 2 | BID AWARD AND REGISTER CONTRCT | 2015-07-01 | 2015-11-22 | 2017-04-07 | 2019-05-12
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15CVGR | CARVER GARDENS DAY CARE CENTER PLAYGROUND | 3 | CONSTRUCTION | 2015-11-23 | 2016-11-21 | 2019-05-13 | 2020-02-06
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15CVGR | CARVER GARDENS DAY CARE CENTER PLAYGROUND | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-11-22 | 2017-05-20 | 2019-05-13 | 2020-02-06
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15CVGR | CARVER GARDENS DAY CARE CENTER PLAYGROUND | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-11-22 | 2017-05-20 | 2020-02-07 | 2020-08-04
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15ICNB | STANLEY ISAACS UPGRADE OF SENIOR AND YOUTH CENTER COMP. UPGR | 1 | DESIGN | 2015-01-02 | 2015-06-30 | 2013-12-03 | 2016-12-18
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15ICNB | STANLEY ISAACS UPGRADE OF SENIOR AND YOUTH CENTER COMP. UPGR | 2 | BID AWARD AND REGISTER CONTRCT | 2015-07-01 | 2015-11-22 | 2016-12-19 | 2018-03-14
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15ICNB | STANLEY ISAACS UPGRADE OF SENIOR AND YOUTH CENTER COMP. UPGR | 3 | CONSTRUCTION | 2015-11-23 | 2016-11-21 | 2018-03-15 | 2019-03-24
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15ICNB | STANLEY ISAACS UPGRADE OF SENIOR AND YOUTH CENTER COMP. UPGR | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-11-22 | 2017-05-20 | 2018-03-15 | 2019-03-24
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15ICNB | STANLEY ISAACS UPGRADE OF SENIOR AND YOUTH CENTER COMP. UPGR | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-11-22 | 2017-05-20 | 2019-03-25 | 2020-03-23
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15JFSR | JEFFERSON SENIOR CENTER UPGRADE | 1 | DESIGN | 2015-09-21 | 2016-03-18 | 2015-02-04 | 2018-04-09
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15JFSR | JEFFERSON SENIOR CENTER UPGRADE | 2 | BID AWARD AND REGISTER CONTRCT | 2016-03-19 | 2016-06-16 | 2018-04-10 | 2018-07-08
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15JFSR | JEFFERSON SENIOR CENTER UPGRADE | 3 | CONSTRUCTION | 2016-06-17 | 2017-06-16 | 2018-07-09 | 2019-07-08
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15JFSR | JEFFERSON SENIOR CENTER UPGRADE | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-06-17 | 2017-12-13 | 2019-07-09 | 2020-01-04
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15MOGD | METRO NORTH PLAZA DAY CARE CENTER PLAYGROUND RENOVATION | 1 | DESIGN | 2015-01-02 | 2015-06-30 | 2016-09-03 | 2017-05-31
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15MOGD | METRO NORTH PLAZA DAY CARE CENTER PLAYGROUND RENOVATION | 2 | BID AWARD AND REGISTER CONTRCT | 2015-07-01 | 2015-11-22 | 2017-06-01 | 2017-11-27
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15MOGD | METRO NORTH PLAZA DAY CARE CENTER PLAYGROUND RENOVATION | 3 | CONSTRUCTION | 2015-11-23 | 2016-11-21 | 2017-11-28 | 2018-11-23
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15MOGD | METRO NORTH PLAZA DAY CARE CENTER PLAYGROUND RENOVATION | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-11-22 | 2017-05-20 | 2017-11-28 | 2018-11-23
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15MOGD | METRO NORTH PLAZA DAY CARE CENTER PLAYGROUND RENOVATION | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-11-22 | 2017-05-20 | 2018-11-24 | 2019-11-23
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15WSPL | WASHINGTON HOUSES DAY CARE CENTER PLAYGROUND UPGRADE | 1 | DESIGN | 2015-01-02 | 2015-06-30 | 2015-08-15 | 2017-04-06
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15WSPL | WASHINGTON HOUSES DAY CARE CENTER PLAYGROUND UPGRADE | 2 | BID AWARD AND REGISTER CONTRCT | 2015-07-01 | 2015-11-22 | 2017-04-07 | 2018-12-07
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15WSPL | WASHINGTON HOUSES DAY CARE CENTER PLAYGROUND UPGRADE | 3 | CONSTRUCTION | 2015-11-23 | 2016-11-21 | 2018-12-08 | 2019-09-03
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15WSPL | WASHINGTON HOUSES DAY CARE CENTER PLAYGROUND UPGRADE | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-11-22 | 2017-05-20 | 2018-12-08 | 2019-09-03
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15WSPL | WASHINGTON HOUSES DAY CARE CENTER PLAYGROUND UPGRADE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-11-22 | 2017-05-20 | 2019-09-04 | 2020-09-02
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16AMBL | AMSTERDAM HOUSES BARRELS PLAYGROUND RENO | 1 | DESIGN | 2016-01-04 | 2016-07-01 | 2016-01-04 | 2016-07-01
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16AMBL | AMSTERDAM HOUSES BARRELS PLAYGROUND RENO | 2 | BID AWARD AND REGISTER CONTRCT | 2016-07-02 | 2016-11-23 | 2016-07-02 | 2016-11-23
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16AMBL | AMSTERDAM HOUSES BARRELS PLAYGROUND RENO | 3 | CONSTRUCTION | 2016-11-24 | 2017-11-23 | 2016-11-24 | 2017-11-23
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16AMBL | AMSTERDAM HOUSES BARRELS PLAYGROUND RENO | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-11-24 | 2018-05-22 | 2016-11-24 | 2017-11-23
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16AMBL | AMSTERDAM HOUSES BARRELS PLAYGROUND RENO | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-11-24 | 2018-05-22 | 2017-11-24 | 2020-11-22
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16AMUP | AMSTERDAM HOUSES NYCHA-UPGRADES | 1 | DESIGN | 2016-01-04 | 2016-07-01 | 2016-01-04 | 2016-07-01
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16AMUP | AMSTERDAM HOUSES NYCHA-UPGRADES | 2 | BID AWARD AND REGISTER CONTRCT | 2016-07-02 | 2016-11-23 | 2016-07-02 | 2016-11-23
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16AMUP | AMSTERDAM HOUSES NYCHA-UPGRADES | 3 | CONSTRUCTION | 2016-11-24 | 2017-11-23 | 2016-11-24 | 2017-11-23
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16AMUP | AMSTERDAM HOUSES NYCHA-UPGRADES | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-11-24 | 2018-05-22 | 2016-11-24 | 2017-11-23
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16AMUP | AMSTERDAM HOUSES NYCHA-UPGRADES | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-11-24 | 2018-05-22 | 2017-11-24 | 2020-11-22
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16CRCC | CORSI HOUSES UPGRADES TO LAGUARDIA COMMUNITY CENTER | 1 | DESIGN | 2016-01-04 | 2016-07-01 | 2016-01-04 | 2016-07-01
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16CRCC | CORSI HOUSES UPGRADES TO LAGUARDIA COMMUNITY CENTER | 2 | BID AWARD AND REGISTER CONTRCT | 2016-07-02 | 2016-11-23 | 2016-07-02 | 2016-11-23
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16CRCC | CORSI HOUSES UPGRADES TO LAGUARDIA COMMUNITY CENTER | 3 | CONSTRUCTION | 2016-11-24 | 2017-11-23 | 2016-11-24 | 2017-11-23
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16CRCC | CORSI HOUSES UPGRADES TO LAGUARDIA COMMUNITY CENTER | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-11-24 | 2018-05-22 | 2016-11-24 | 2017-11-23
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16CRCC | CORSI HOUSES UPGRADES TO LAGUARDIA COMMUNITY CENTER | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-11-24 | 2018-05-22 | 2017-11-24 | 2021-11-22
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16GHPL | GRANT HOUSES MAJOR PLAYGROUND RENOVATIONS-PLAYGROUND REPAIRS | 1 | DESIGN | 2016-01-04 | 2016-07-01 | 2016-01-04 | 2016-07-01
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16GHPL | GRANT HOUSES MAJOR PLAYGROUND RENOVATIONS-PLAYGROUND REPAIRS | 2 | BID AWARD AND REGISTER CONTRCT | 2016-07-02 | 2016-11-23 | 2016-07-02 | 2016-11-23
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16GHPL | GRANT HOUSES MAJOR PLAYGROUND RENOVATIONS-PLAYGROUND REPAIRS | 3 | CONSTRUCTION | 2016-11-24 | 2017-11-23 | 2016-11-24 | 2017-11-23
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16GHPL | GRANT HOUSES MAJOR PLAYGROUND RENOVATIONS-PLAYGROUND REPAIRS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-11-24 | 2018-05-22 | 2016-11-24 | 2017-11-23
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16GHPL | GRANT HOUSES MAJOR PLAYGROUND RENOVATIONS-PLAYGROUND REPAIRS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-11-24 | 2018-05-22 | 2017-11-24 | 2020-11-22
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16LGSC | 282 CHERRY STREET SECURITY CAMERAS | 1 | DESIGN | 2016-03-02 | 2016-08-28 | 2016-03-02 | 2016-08-28
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16LGSC | 282 CHERRY STREET SECURITY CAMERAS | 2 | BID AWARD AND REGISTER CONTRCT | 2016-08-29 | 2017-01-20 | 2016-08-29 | 2019-08-28
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16LGSC | 282 CHERRY STREET SECURITY CAMERAS | 3 | CONSTRUCTION | 2017-01-21 | 2018-01-20 | 2019-08-29 | 2020-08-27
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16LGSC | 282 CHERRY STREET SECURITY CAMERAS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-01-21 | 2018-07-19 | 2019-08-29 | 2020-08-27
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16LGSC | 282 CHERRY STREET SECURITY CAMERAS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-01-21 | 2018-07-19 | 2020-08-28 | 2021-02-23
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16LXCG | LEXINGTON HOUSES GROUND UPGRADE COMMUNITY GARDEN | 1 | DESIGN | 2016-01-04 | 2016-07-01 | 2016-01-04 | 2016-07-01
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16LXCG | LEXINGTON HOUSES GROUND UPGRADE COMMUNITY GARDEN | 2 | BID AWARD AND REGISTER CONTRCT | 2016-07-02 | 2016-11-23 | 2016-07-02 | 2016-11-23
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16LXCG | LEXINGTON HOUSES GROUND UPGRADE COMMUNITY GARDEN | 3 | CONSTRUCTION | 2016-11-24 | 2017-11-23 | 2016-11-24 | 2017-11-23
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16LXCG | LEXINGTON HOUSES GROUND UPGRADE COMMUNITY GARDEN | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-11-24 | 2018-05-22 | 2016-11-24 | 2017-11-23
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16LXCG | LEXINGTON HOUSES GROUND UPGRADE COMMUNITY GARDEN | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-11-24 | 2018-05-22 | 2017-11-24 | 2020-11-22
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16RPEU | ROBBINS PLAZA EQUIPMENT UPGRADE | 3 | CONSTRUCTION | 2016-11-21 | 2017-11-20 | 2016-11-21 | 2017-11-20
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16RPEU | ROBBINS PLAZA EQUIPMENT UPGRADE | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-11-21 | 2018-05-19 | 2016-11-21 | 2017-11-20
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16RPEU | ROBBINS PLAZA EQUIPMENT UPGRADE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-11-21 | 2018-05-19 | 2017-11-21 | 2018-05-19
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16UPGI | UNDERGROUND WATER AND FIRE DISTRIBUTION PIPING | 1 | DESIGN | 2017-03-01 | 2017-08-27 | 2017-03-01 | 2017-08-27
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16UPGI | UNDERGROUND WATER AND FIRE DISTRIBUTION PIPING | 2 | BID AWARD AND REGISTER CONTRCT | 2017-08-28 | 2018-01-19 | 2017-08-28 | 2018-01-19
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16UPGI | UNDERGROUND WATER AND FIRE DISTRIBUTION PIPING | 3 | CONSTRUCTION | 2018-01-20 | 2019-01-19 | 2018-01-20 | 2019-01-19
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16UPGI | UNDERGROUND WATER AND FIRE DISTRIBUTION PIPING | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-01-20 | 2019-07-18 | 2018-01-20 | 2019-01-19
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16UPGI | UNDERGROUND WATER AND FIRE DISTRIBUTION PIPING | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-01-20 | 2019-07-18 | 2019-01-20 | 2019-07-18
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16WIBU | WILSON HOUSES BASKETBALL COURT UPGRADE | 2 | BID AWARD AND REGISTER CONTRCT | 2016-07-02 | 2016-11-23 | 2016-07-02 | 2016-11-23
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16WIBU | WILSON HOUSES BASKETBALL COURT UPGRADE | 3 | CONSTRUCTION | 2016-11-24 | 2017-11-23 | 2016-11-24 | 2017-11-23
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16WIBU | WILSON HOUSES BASKETBALL COURT UPGRADE | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-11-24 | 2018-05-22 | 2016-11-24 | 2017-11-23
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16WIBU | WILSON HOUSES BASKETBALL COURT UPGRADE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-11-24 | 2018-05-22 | 2017-11-24 | 2018-05-22
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16WRSC | WISE REHAB 54 W. 94TH STREET SECURITY CAMERAS | 1 | DESIGN | 2016-03-02 | 2016-08-28 | 2016-03-02 | 2016-08-28
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16WRSC | WISE REHAB 54 W. 94TH STREET SECURITY CAMERAS | 2 | BID AWARD AND REGISTER CONTRCT | 2016-08-29 | 2017-01-20 | 2016-08-29 | 2017-01-20
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16WRSC | WISE REHAB 54 W. 94TH STREET SECURITY CAMERAS | 3 | CONSTRUCTION | 2017-01-21 | 2018-01-20 | 2017-01-21 | 2018-01-20
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16WRSC | WISE REHAB 54 W. 94TH STREET SECURITY CAMERAS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-01-21 | 2018-07-19 | 2017-01-21 | 2018-01-20
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16WRSC | WISE REHAB 54 W. 94TH STREET SECURITY CAMERAS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-01-21 | 2018-07-19 | 2018-01-21 | 2020-01-20
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM17CRGR | CORSI HOUSES SITTING AREA FOR SENIORS | 1 | DESIGN | 2017-02-01 | 2017-07-30 | 2017-02-01 | 2017-07-30
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM17CRGR | CORSI HOUSES SITTING AREA FOR SENIORS | 2 | BID AWARD AND REGISTER CONTRCT | 2017-07-31 | 2017-12-22 | 2017-07-31 | 2017-12-22
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM17CRGR | CORSI HOUSES SITTING AREA FOR SENIORS | 3 | CONSTRUCTION | 2017-12-23 | 2018-12-22 | 2017-12-23 | 2018-12-22
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM17CRGR | CORSI HOUSES SITTING AREA FOR SENIORS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-12-23 | 2019-06-20 | 2017-12-23 | 2018-12-22
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM17CRGR | CORSI HOUSES SITTING AREA FOR SENIORS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-12-23 | 2019-06-20 | 2018-12-23 | 2020-12-21
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM17HRPL | HERNANDEZ PLAYGROUND RENOVATION AY 189 ALLEN STREET | 1 | DESIGN | 2017-02-01 | 2017-07-30 | 2018-12-17 | 2019-06-14
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM17HRPL | HERNANDEZ PLAYGROUND RENOVATION AY 189 ALLEN STREET | 2 | BID AWARD AND REGISTER CONTRCT | 2017-07-31 | 2017-12-22 | 2019-06-15 | 2019-11-06
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM17HRPL | HERNANDEZ PLAYGROUND RENOVATION AY 189 ALLEN STREET | 3 | CONSTRUCTION | 2017-12-23 | 2018-12-22 | 2019-11-07 | 2020-11-05
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM17HRPL | HERNANDEZ PLAYGROUND RENOVATION AY 189 ALLEN STREET | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-12-23 | 2019-06-20 | 2019-11-07 | 2020-11-05
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM17HRPL | HERNANDEZ PLAYGROUND RENOVATION AY 189 ALLEN STREET | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-12-23 | 2019-06-20 | 2020-11-06 | 2021-05-04
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18DIGV | DIGITAL VAN | 1 | DESIGN | 2018-06-01 | 2018-11-27 | 2018-06-01 | 2018-11-27
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18DIGV | DIGITAL VAN | 2 | BID AWARD AND REGISTER CONTRCT | 2018-11-28 | 2019-05-26 | 2018-11-28 | 2019-05-26
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18DIGV | DIGITAL VAN | 3 | CONSTRUCTION | 2019-05-27 | 2020-05-25 | 2019-05-27 | 2020-05-25
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18DIGV | DIGITAL VAN | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-05-26 | 2020-11-21 | 2019-05-27 | 2020-05-25
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18DIGV | DIGITAL VAN | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-05-26 | 2020-11-21 | 2020-05-26 | 2020-11-21
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18ECGR | GROUNDS RENOVATION AT ELLIOT - CHELSEA HOUSES | 1 | DESIGN | 2018-03-15 | 2018-09-10 | 2018-03-15 | 2018-09-10
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18ECGR | GROUNDS RENOVATION AT ELLIOT - CHELSEA HOUSES | 2 | BID AWARD AND REGISTER CONTRCT | 2018-09-11 | 2019-03-09 | 2018-09-11 | 2019-03-09
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18ECGR | GROUNDS RENOVATION AT ELLIOT - CHELSEA HOUSES | 3 | CONSTRUCTION | 2019-03-10 | 2020-03-08 | 2019-03-10 | 2020-03-08
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18ECGR | GROUNDS RENOVATION AT ELLIOT - CHELSEA HOUSES | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-03-09 | 2020-09-04 | 2019-03-10 | 2020-03-08
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18ECGR | GROUNDS RENOVATION AT ELLIOT - CHELSEA HOUSES | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-03-09 | 2020-09-04 | 2020-03-09 | 2020-09-04
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18GOBR | GOMPERS BOILER REPAIR | 1 | DESIGN | 2017-09-16 | 2018-03-14 | 2017-09-16 | 2018-03-14
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18GOBR | GOMPERS BOILER REPAIR | 2 | BID AWARD AND REGISTER CONTRCT | 2018-03-15 | 2018-09-10 | 2018-03-15 | 2018-09-10
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18GOBR | GOMPERS BOILER REPAIR | 3 | CONSTRUCTION | 2018-09-11 | 2019-09-10 | 2018-09-11 | 2019-09-10
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18GOBR | GOMPERS BOILER REPAIR | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-11 | 2020-03-08 | 2018-09-11 | 2019-09-10
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18GOBR | GOMPERS BOILER REPAIR | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-11 | 2020-03-08 | 2019-09-11 | 2020-03-08
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18GRLM | GRANT HOUSES LAUNDROMAT RENOVATION | 1 | DESIGN | 2017-09-16 | 2018-03-14 | 2017-09-16 | 2018-03-14
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18GRLM | GRANT HOUSES LAUNDROMAT RENOVATION | 2 | BID AWARD AND REGISTER CONTRCT | 2018-03-15 | 2018-09-10 | 2018-03-15 | 2018-09-10
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18GRLM | GRANT HOUSES LAUNDROMAT RENOVATION | 3 | CONSTRUCTION | 2018-09-11 | 2019-09-10 | 2018-09-11 | 2019-09-10
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18GRLM | GRANT HOUSES LAUNDROMAT RENOVATION | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-11 | 2020-03-08 | 2018-09-11 | 2019-09-10
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18GRLM | GRANT HOUSES LAUNDROMAT RENOVATION | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-11 | 2020-03-08 | 2019-09-11 | 2020-03-08
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18JFBC | JEFFERSON HOUSES BASKETBALL COURT | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-03-09 | 2020-09-04 | 2019-03-10 | 2020-03-08
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18JFBC | JEFFERSON HOUSES BASKETBALL COURT | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-03-09 | 2020-09-04 | 2020-03-09 | 2021-09-04
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18JFTV | INSTALLATION OF SECURITY CAMERAS AT JEFFERSON HOUSES | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18JFTV | INSTALLATION OF SECURITY CAMERAS AT JEFFERSON HOUSES | 3 | CONSTRUCTION | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18JFTV | INSTALLATION OF SECURITY CAMERAS AT JEFFERSON HOUSES | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-28 | 2020-06-24 | 2018-12-28 | 2019-12-27
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18JFTV | INSTALLATION OF SECURITY CAMERAS AT JEFFERSON HOUSES | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-28 | 2020-06-24 | 2019-12-28 | 2020-06-24
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18JOCC | JOHNSON COMM. CTR. STANLEY ISACCS NBRHD ROOF GLASS PANES | 1 | DESIGN | 2018-03-01 | 2018-08-27 | 2018-03-01 | 2018-08-27
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18JOCC | JOHNSON COMM. CTR. STANLEY ISACCS NBRHD ROOF GLASS PANES | 2 | BID AWARD AND REGISTER CONTRCT | 2018-08-28 | 2019-02-23 | 2018-08-28 | 2019-02-23
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18JOCC | JOHNSON COMM. CTR. STANLEY ISACCS NBRHD ROOF GLASS PANES | 3 | CONSTRUCTION | 2019-02-24 | 2020-02-23 | 2019-02-24 | 2020-02-23
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18JOCC | JOHNSON COMM. CTR. STANLEY ISACCS NBRHD ROOF GLASS PANES | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-02-24 | 2020-08-21 | 2019-02-24 | 2020-02-23
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18JOCC | JOHNSON COMM. CTR. STANLEY ISACCS NBRHD ROOF GLASS PANES | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-02-24 | 2020-08-21 | 2020-02-24 | 2020-08-21
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18LIPG | RENOVATION OF A PLAYGROUND AT LOWER EAST SIDE I INFILL | 1 | DESIGN | 2018-03-05 | 2018-08-31 | 2018-03-05 | 2018-08-31
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18LIPG | RENOVATION OF A PLAYGROUND AT LOWER EAST SIDE I INFILL | 2 | BID AWARD AND REGISTER CONTRCT | 2018-09-01 | 2019-02-27 | 2018-09-01 | 2019-02-27
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18LIPG | RENOVATION OF A PLAYGROUND AT LOWER EAST SIDE I INFILL | 3 | CONSTRUCTION | 2019-02-28 | 2020-02-27 | 2019-02-28 | 2020-02-27
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18LIPG | RENOVATION OF A PLAYGROUND AT LOWER EAST SIDE I INFILL | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-02-28 | 2020-08-25 | 2019-02-28 | 2020-02-27
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18LIPG | RENOVATION OF A PLAYGROUND AT LOWER EAST SIDE I INFILL | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-02-28 | 2020-08-25 | 2020-02-28 | 2020-08-25
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18URBF | URBAN FARMS | 1 | DESIGN | 2018-01-02 | 2018-06-30 | 2018-01-02 | 2018-06-30
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18URBF | URBAN FARMS | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18URBF | URBAN FARMS | 3 | CONSTRUCTION | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18URBF | URBAN FARMS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-28 | 2020-06-24 | 2018-12-28 | 2019-12-27
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18URBF | URBAN FARMS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-28 | 2020-06-24 | 2019-12-28 | 2020-06-24
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18VLPG | VLADECK HOUSES PLAYGROUND UPGRADE | 1 | DESIGN | 2017-10-01 | 2018-03-29 | 2017-10-01 | 2018-03-29
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18VLPG | VLADECK HOUSES PLAYGROUND UPGRADE | 2 | BID AWARD AND REGISTER CONTRCT | 2018-03-30 | 2018-09-25 | 2018-03-30 | 2018-09-25
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18VLPG | VLADECK HOUSES PLAYGROUND UPGRADE | 3 | CONSTRUCTION | 2018-09-26 | 2019-09-25 | 2018-09-26 | 2019-09-25
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18VLPG | VLADECK HOUSES PLAYGROUND UPGRADE | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-26 | 2020-03-23 | 2018-09-26 | 2019-09-25
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18VLPG | VLADECK HOUSES PLAYGROUND UPGRADE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-26 | 2020-03-23 | 2019-09-26 | 2020-03-23
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WAGD | WASHINGTON HOUSES MAKE PLAYGROUND ADA ACCESSIBLE | 1 | DESIGN | 2018-03-15 | 2018-09-10 | 2018-03-15 | 2018-09-10
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WAGD | WASHINGTON HOUSES MAKE PLAYGROUND ADA ACCESSIBLE | 2 | BID AWARD AND REGISTER CONTRCT | 2018-09-11 | 2019-03-09 | 2018-09-11 | 2019-03-09
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WAGD | WASHINGTON HOUSES MAKE PLAYGROUND ADA ACCESSIBLE | 3 | CONSTRUCTION | 2019-03-10 | 2020-03-08 | 2019-03-10 | 2020-03-08
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WAGD | WASHINGTON HOUSES MAKE PLAYGROUND ADA ACCESSIBLE | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-03-09 | 2020-09-04 | 2019-03-10 | 2020-03-08
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WAGD | WASHINGTON HOUSES MAKE PLAYGROUND ADA ACCESSIBLE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-03-09 | 2020-09-04 | 2020-03-09 | 2020-09-04
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WHTV | WHITE HOUSES SECURITY CAMERAS AND NEW DOOR | 1 | DESIGN | 2018-01-02 | 2018-06-30 | 2018-01-02 | 2018-06-30
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WHTV | WHITE HOUSES SECURITY CAMERAS AND NEW DOOR | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WHTV | WHITE HOUSES SECURITY CAMERAS AND NEW DOOR | 3 | CONSTRUCTION | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WHTV | WHITE HOUSES SECURITY CAMERAS AND NEW DOOR | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-28 | 2020-06-24 | 2018-12-28 | 2019-12-27
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WHTV | WHITE HOUSES SECURITY CAMERAS AND NEW DOOR | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-28 | 2020-06-24 | 2019-12-28 | 2020-06-24
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19AMEL | AMSTERDAM HOUSES ELEVATOR UPGRADE | 1 | DESIGN | 2019-06-30 | 2020-12-31 | 2019-06-30 | 2020-12-31
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19AMEL | AMSTERDAM HOUSES ELEVATOR UPGRADE | 2 | BID AWARD AND REGISTER CONTRCT | 2021-01-01 | 2021-07-01 | 2021-01-01 | 2021-07-01
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19AMEL | AMSTERDAM HOUSES ELEVATOR UPGRADE | 3 | CONSTRUCTION | 2021-07-02 | 2023-01-22 | 2021-07-02 | 2023-01-22
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19AMEL | AMSTERDAM HOUSES ELEVATOR UPGRADE | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-01-23 | 2023-04-23 | 2021-07-02 | 2023-01-22
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19AMEL | AMSTERDAM HOUSES ELEVATOR UPGRADE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-01-23 | 2023-04-23 | 2023-01-23 | 2023-04-23
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19DCCR | DYCKMAN HOUSES COMMUNITY CENTER RAMP | 1 | DESIGN | 2019-02-15 | 2019-08-13 | 2019-02-15 | 2019-08-13
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19DCCR | DYCKMAN HOUSES COMMUNITY CENTER RAMP | 2 | BID AWARD AND REGISTER CONTRCT | 2019-08-14 | 2020-02-09 | 2019-08-14 | 2020-02-09
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19DCCR | DYCKMAN HOUSES COMMUNITY CENTER RAMP | 3 | CONSTRUCTION | 2020-02-10 | 2021-02-08 | 2020-02-10 | 2021-02-08
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19DCCR | DYCKMAN HOUSES COMMUNITY CENTER RAMP | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-02-09 | 2021-08-07 | 2020-02-10 | 2021-02-08
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19DCCR | DYCKMAN HOUSES COMMUNITY CENTER RAMP | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-02-09 | 2021-08-07 | 2021-02-09 | 2021-08-07
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19DHPR | DYCKMAN HOUSES PLAYGROUND RENOVATION | 1 | DESIGN | 2019-02-15 | 2019-08-13 | 2019-02-15 | 2019-08-13
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19DHPR | DYCKMAN HOUSES PLAYGROUND RENOVATION | 2 | BID AWARD AND REGISTER CONTRCT | 2019-08-14 | 2020-02-09 | 2019-08-14 | 2020-02-09
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19DHPR | DYCKMAN HOUSES PLAYGROUND RENOVATION | 3 | CONSTRUCTION | 2020-02-10 | 2021-02-08 | 2020-02-10 | 2021-02-08
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19DHPR | DYCKMAN HOUSES PLAYGROUND RENOVATION | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-02-09 | 2021-08-07 | 2020-02-10 | 2021-02-08
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19DHPR | DYCKMAN HOUSES PLAYGROUND RENOVATION | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-02-09 | 2021-08-07 | 2021-02-09 | 2021-08-07
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19ECSC | ELLIOTT-CHELSEA HOUSES SECURITY CAMERAS | 1 | DESIGN | 2019-03-04 | 2019-08-30 | 2019-03-04 | 2019-08-30
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19ECSC | ELLIOTT-CHELSEA HOUSES SECURITY CAMERAS | 2 | BID AWARD AND REGISTER CONTRCT | 2019-08-31 | 2020-02-26 | 2019-08-31 | 2020-02-26
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19ECSC | ELLIOTT-CHELSEA HOUSES SECURITY CAMERAS | 3 | CONSTRUCTION | 2020-02-27 | 2021-02-25 | 2020-02-27 | 2021-02-25
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19ECSC | ELLIOTT-CHELSEA HOUSES SECURITY CAMERAS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-02-26 | 2021-08-24 | 2020-02-27 | 2021-02-25
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19ECSC | ELLIOTT-CHELSEA HOUSES SECURITY CAMERAS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-02-26 | 2021-08-24 | 2021-02-26 | 2021-08-24
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19FHSC | FULTON HOUSES SECURITY CAMERAS | 1 | DESIGN | 2019-03-11 | 2019-09-06 | 2019-03-11 | 2019-09-06
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19FHSC | FULTON HOUSES SECURITY CAMERAS | 2 | BID AWARD AND REGISTER CONTRCT | 2019-09-07 | 2020-03-04 | 2019-09-07 | 2020-03-04
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19FHSC | FULTON HOUSES SECURITY CAMERAS | 3 | CONSTRUCTION | 2020-03-05 | 2021-03-04 | 2020-03-05 | 2021-03-04
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19FHSC | FULTON HOUSES SECURITY CAMERAS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-05 | 2021-08-31 | 2020-03-05 | 2021-03-04
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19FHSC | FULTON HOUSES SECURITY CAMERAS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-05 | 2021-08-31 | 2021-03-05 | 2021-08-31
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19GHEL | GRANT HOUSES EXTERNAL LIGHTING UPGRADES | 1 | DESIGN | 2019-01-15 | 2019-07-13 | 2019-01-15 | 2019-07-13
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19GHEL | GRANT HOUSES EXTERNAL LIGHTING UPGRADES | 2 | BID AWARD AND REGISTER CONTRCT | 2019-07-14 | 2020-01-09 | 2019-07-14 | 2020-01-09
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19GHEL | GRANT HOUSES EXTERNAL LIGHTING UPGRADES | 3 | CONSTRUCTION | 2020-01-10 | 2021-01-08 | 2020-01-10 | 2021-01-08
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19GHEL | GRANT HOUSES EXTERNAL LIGHTING UPGRADES | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-01-09 | 2021-07-07 | 2020-01-10 | 2021-01-08
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19GHEL | GRANT HOUSES EXTERNAL LIGHTING UPGRADES | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-01-09 | 2021-07-07 | 2021-01-09 | 2021-07-07
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19HBBR | HARBORVIEW COMMUNITY/SENIOR CENTER BATHROOM RENOVATIONS | 1 | DESIGN | 2018-01-02 | 2018-06-30 | 2018-01-02 | 2018-06-30
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19HBBR | HARBORVIEW COMMUNITY/SENIOR CENTER BATHROOM RENOVATIONS | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19HBBR | HARBORVIEW COMMUNITY/SENIOR CENTER BATHROOM RENOVATIONS | 3 | CONSTRUCTION | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19HBBR | HARBORVIEW COMMUNITY/SENIOR CENTER BATHROOM RENOVATIONS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-28 | 2020-06-24 | 2018-12-28 | 2019-12-27
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19HBBR | HARBORVIEW COMMUNITY/SENIOR CENTER BATHROOM RENOVATIONS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-28 | 2020-06-24 | 2019-12-28 | 2020-06-24
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19RCCK | RUTGERS COMMUNITY CENTER KITCHEN RENOVATION | 1 | DESIGN | 2018-01-02 | 2018-06-30 | 2018-01-02 | 2018-06-30
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19RCCK | RUTGERS COMMUNITY CENTER KITCHEN RENOVATION | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19RCCK | RUTGERS COMMUNITY CENTER KITCHEN RENOVATION | 3 | CONSTRUCTION | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19RCCK | RUTGERS COMMUNITY CENTER KITCHEN RENOVATION | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-28 | 2020-06-24 | 2018-12-28 | 2019-12-27
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19RCCK | RUTGERS COMMUNITY CENTER KITCHEN RENOVATION | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-28 | 2020-06-24 | 2019-12-28 | 2020-06-24
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19RLTV | RANGEL HOUSES SAFE GROUNDS SECURITY INITIATIVE - CCTV | 1 | DESIGN | 2019-03-18 | 2019-09-13 | 2019-03-18 | 2019-09-13
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19RLTV | RANGEL HOUSES SAFE GROUNDS SECURITY INITIATIVE - CCTV | 2 | BID AWARD AND REGISTER CONTRCT | 2019-09-14 | 2020-03-11 | 2019-09-14 | 2020-03-11
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19RLTV | RANGEL HOUSES SAFE GROUNDS SECURITY INITIATIVE - CCTV | 3 | CONSTRUCTION | 2020-03-12 | 2021-03-11 | 2020-03-12 | 2021-03-11
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19RLTV | RANGEL HOUSES SAFE GROUNDS SECURITY INITIATIVE - CCTV | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-12 | 2021-09-07 | 2020-03-12 | 2021-03-11
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19RLTV | RANGEL HOUSES SAFE GROUNDS SECURITY INITIATIVE - CCTV | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-12 | 2021-09-07 | 2021-03-12 | 2021-09-07
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19STEL | ST NICHOLAS HOUSES ELEVATOR UPGRADE | 1 | DESIGN | 2019-06-30 | 2019-12-31 | 2019-06-30 | 2019-12-31
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19STEL | ST NICHOLAS HOUSES ELEVATOR UPGRADE | 2 | BID AWARD AND REGISTER CONTRCT | 2020-01-01 | 2022-06-30 | 2020-01-01 | 2022-06-30
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19STEL | ST NICHOLAS HOUSES ELEVATOR UPGRADE | 3 | CONSTRUCTION | 2022-07-01 | 2024-01-21 | 2022-07-01 | 2024-01-21
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19STEL | ST NICHOLAS HOUSES ELEVATOR UPGRADE | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-01-22 | 2024-04-21 | 2022-07-01 | 2024-01-21
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19STEL | ST NICHOLAS HOUSES ELEVATOR UPGRADE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-01-22 | 2024-04-21 | 2024-01-22 | 2024-04-21
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19VLPR | VLADECK HOUSES: PLAYGROUND REPAVING | 1 | DESIGN | 2019-04-15 | 2019-10-11 | 2019-04-15 | 2019-10-11
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19VLPR | VLADECK HOUSES: PLAYGROUND REPAVING | 2 | BID AWARD AND REGISTER CONTRCT | 2019-10-12 | 2020-04-08 | 2019-10-12 | 2020-04-08
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19VLPR | VLADECK HOUSES: PLAYGROUND REPAVING | 3 | CONSTRUCTION | 2020-04-09 | 2021-04-08 | 2020-04-09 | 2021-04-08
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19VLPR | VLADECK HOUSES: PLAYGROUND REPAVING | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-04-09 | 2021-10-05 | 2020-04-09 | 2021-04-08
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19VLPR | VLADECK HOUSES: PLAYGROUND REPAVING | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-04-09 | 2021-10-05 | 2021-04-09 | 2021-10-05
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19WTOC | WISE HOUSES OUTDOOR PLAZA CAMERAS | 1 | DESIGN | 2019-03-18 | 2019-09-13 | 2019-03-18 | 2019-09-13
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19WTOC | WISE HOUSES OUTDOOR PLAZA CAMERAS | 2 | BID AWARD AND REGISTER CONTRCT | 2019-09-14 | 2020-03-11 | 2019-09-14 | 2020-03-11
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19WTOC | WISE HOUSES OUTDOOR PLAZA CAMERAS | 3 | CONSTRUCTION | 2020-03-12 | 2021-03-11 | 2020-03-12 | 2021-03-11
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19WTOC | WISE HOUSES OUTDOOR PLAZA CAMERAS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-12 | 2021-09-07 | 2020-03-12 | 2021-03-11
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19WTOC | WISE HOUSES OUTDOOR PLAZA CAMERAS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-12 | 2021-09-07 | 2021-03-12 | 2021-09-07
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20BHNE | BARUCH HOUSES NEW ELEVATOR | 1 | DESIGN | 2018-01-02 | 2018-06-30 | 2018-01-02 | 2018-06-30
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20BHNE | BARUCH HOUSES NEW ELEVATOR | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20BHNE | BARUCH HOUSES NEW ELEVATOR | 3 | CONSTRUCTION | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20BHNE | BARUCH HOUSES NEW ELEVATOR | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-28 | 2020-06-24 | 2018-12-28 | 2019-12-27
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20BHNE | BARUCH HOUSES NEW ELEVATOR | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-28 | 2020-06-24 | 2019-12-28 | 2020-06-24
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20CHHT | HEATING UPGRADES- CHELSEA HOUSES | 1 | DESIGN | 2019-09-01 | 2020-02-27 | 2019-09-01 | 2020-02-27
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20CHHT | HEATING UPGRADES- CHELSEA HOUSES | 2 | BID AWARD AND REGISTER CONTRCT | 2020-02-28 | 2020-08-25 | 2020-02-28 | 2020-08-25
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20CHHT | HEATING UPGRADES- CHELSEA HOUSES | 3 | CONSTRUCTION | 2020-08-26 | 2021-08-25 | 2020-08-26 | 2021-08-25
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20CHHT | HEATING UPGRADES- CHELSEA HOUSES | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-08-26 | 2022-02-21 | 2020-08-26 | 2021-08-25
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20CHHT | HEATING UPGRADES- CHELSEA HOUSES | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-08-26 | 2022-02-21 | 2021-08-26 | 2022-02-21
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20CSKR | CARVER HOUSES KITCHEN RENOVATION IN SENIOR CENTER | 1 | DESIGN | 2019-09-01 | 2020-02-27 | 2019-09-01 | 2020-02-27
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20CSKR | CARVER HOUSES KITCHEN RENOVATION IN SENIOR CENTER | 2 | BID AWARD AND REGISTER CONTRCT | 2020-02-28 | 2020-08-25 | 2020-02-28 | 2020-08-25
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20CSKR | CARVER HOUSES KITCHEN RENOVATION IN SENIOR CENTER | 3 | CONSTRUCTION | 2020-08-26 | 2021-08-25 | 2020-08-26 | 2021-08-25
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20CSKR | CARVER HOUSES KITCHEN RENOVATION IN SENIOR CENTER | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-08-26 | 2022-02-21 | 2020-08-26 | 2021-08-25
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20CSKR | CARVER HOUSES KITCHEN RENOVATION IN SENIOR CENTER | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-08-26 | 2022-02-21 | 2021-08-26 | 2022-02-21
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20CUSD | CARVER UNDERGROUND STEAM DISTRIBUTION | 1 | DESIGN | 2020-09-01 | 2021-02-27 | 2020-09-01 | 2021-02-27
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20CUSD | CARVER UNDERGROUND STEAM DISTRIBUTION | 2 | BID AWARD AND REGISTER CONTRCT | 2021-02-28 | 2021-08-26 | 2021-02-28 | 2021-08-26
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20CUSD | CARVER UNDERGROUND STEAM DISTRIBUTION | 3 | CONSTRUCTION | 2021-08-27 | 2022-08-26 | 2021-08-27 | 2022-08-26
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20CUSD | CARVER UNDERGROUND STEAM DISTRIBUTION | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-08-27 | 2023-02-22 | 2021-08-27 | 2022-08-26
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20CUSD | CARVER UNDERGROUND STEAM DISTRIBUTION | 5 | DEVELOP SCOPE | 2023-02-23 | 2023-05-23 | 2021-08-27 | 2022-08-26
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20CUSD | CARVER UNDERGROUND STEAM DISTRIBUTION | 6 | PRELIMINARY DESIGN | 2023-05-24 | 2023-09-20 | 2022-08-27 | 2023-02-22
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20CUSD | CARVER UNDERGROUND STEAM DISTRIBUTION | 7 | FINAL DESIGN | 2023-09-21 | 2024-03-18 | 2023-02-23 | 2023-05-23
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20CUSD | CARVER UNDERGROUND STEAM DISTRIBUTION | 8 | BID AWARD AND REGISTER CONTRCT | 2024-03-19 | 2024-06-16 | 2023-05-24 | 2023-09-20
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20CUSD | CARVER UNDERGROUND STEAM DISTRIBUTION | 9 | CONSTRUCTION TO 25% | 2024-06-17 | 2024-10-14 | 2023-09-21 | 2024-03-18
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20CUSD | CARVER UNDERGROUND STEAM DISTRIBUTION | 10 | CONSTRUCTION TO 50% | 2024-10-15 | 2025-02-11 | 2024-03-19 | 2024-06-16
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20CUSD | CARVER UNDERGROUND STEAM DISTRIBUTION | 11 | CONSTRUCTION TO 75% | 2025-02-12 | 2025-06-11 | 2024-06-17 | 2024-10-14
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20CUSD | CARVER UNDERGROUND STEAM DISTRIBUTION | 12 | ORIGINAL EQUIP & FURNISHING | 2025-06-12 | 2025-09-09 | 2024-10-15 | 2025-02-11
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20CUSD | CARVER UNDERGROUND STEAM DISTRIBUTION | 13 | SUBSTANTIAL COMPLETION | 2025-09-10 | 2025-11-08 | 2025-02-12 | 2025-06-11
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20CUSD | CARVER UNDERGROUND STEAM DISTRIBUTION | 14 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-11-09 | 2025-12-08 | 2025-06-12 | 2025-09-09
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20CUSD | CARVER UNDERGROUND STEAM DISTRIBUTION | 15 | SUBSTANTIAL COMPLETION | 2025-11-09 | 2025-12-08 | 2025-09-10 | 2025-11-08
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20CUSD | CARVER UNDERGROUND STEAM DISTRIBUTION | 16 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-11-09 | 2025-12-08 | 2025-11-09 | 2025-12-08
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20ELHU | HEATING UPGRADES- ELLIOTT HOUSES | 1 | DESIGN | 2019-09-01 | 2020-02-27 | 2019-09-01 | 2020-02-27
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20ELHU | HEATING UPGRADES- ELLIOTT HOUSES | 2 | BID AWARD AND REGISTER CONTRCT | 2020-02-28 | 2020-08-25 | 2020-02-28 | 2020-08-25
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20ELHU | HEATING UPGRADES- ELLIOTT HOUSES | 3 | CONSTRUCTION | 2020-08-26 | 2021-08-25 | 2020-08-26 | 2021-08-25
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20ELHU | HEATING UPGRADES- ELLIOTT HOUSES | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-08-26 | 2022-02-21 | 2020-08-26 | 2021-08-25
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20ELHU | HEATING UPGRADES- ELLIOTT HOUSES | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-08-26 | 2022-02-21 | 2021-08-26 | 2022-02-21
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20FSHL | FULTON HOUSES STAIRWAY AND HALL LIGHTING | 1 | DESIGN | 2019-09-01 | 2020-02-27 | 2019-09-01 | 2020-02-27
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20FSHL | FULTON HOUSES STAIRWAY AND HALL LIGHTING | 2 | BID AWARD AND REGISTER CONTRCT | 2020-02-28 | 2020-08-25 | 2020-02-28 | 2020-08-25
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20FSHL | FULTON HOUSES STAIRWAY AND HALL LIGHTING | 3 | CONSTRUCTION | 2020-08-26 | 2021-08-25 | 2020-08-26 | 2021-08-25
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20FSHL | FULTON HOUSES STAIRWAY AND HALL LIGHTING | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-08-26 | 2022-02-21 | 2020-08-26 | 2021-08-25
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20FSHL | FULTON HOUSES STAIRWAY AND HALL LIGHTING | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-08-26 | 2022-02-21 | 2021-08-26 | 2022-02-21
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20FUHU | FULTON HOUSES HEATING UPGRADES | 1 | DESIGN | 2019-09-01 | 2020-02-27 | 2019-09-01 | 2020-02-27
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20FUHU | FULTON HOUSES HEATING UPGRADES | 2 | BID AWARD AND REGISTER CONTRCT | 2020-02-28 | 2020-08-25 | 2020-02-28 | 2020-08-25
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20FUHU | FULTON HOUSES HEATING UPGRADES | 3 | CONSTRUCTION | 2020-08-26 | 2021-08-25 | 2020-08-26 | 2021-08-25
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20FUHU | FULTON HOUSES HEATING UPGRADES | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-08-26 | 2022-02-21 | 2020-08-26 | 2021-08-25
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20FUHU | FULTON HOUSES HEATING UPGRADES | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-08-26 | 2022-02-21 | 2021-08-26 | 2022-02-21
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20GHCL | GRANT - LAUNDROMART CONSTRUCTION | 1 | DESIGN | 2019-09-01 | 2020-02-27 | 2019-09-01 | 2020-02-27
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20GHCL | GRANT - LAUNDROMART CONSTRUCTION | 2 | BID AWARD AND REGISTER CONTRCT | 2020-02-28 | 2020-08-25 | 2020-02-28 | 2020-08-25
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20GHCL | GRANT - LAUNDROMART CONSTRUCTION | 3 | CONSTRUCTION | 2020-08-26 | 2021-08-25 | 2020-08-26 | 2021-08-25
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20GHCL | GRANT - LAUNDROMART CONSTRUCTION | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-08-26 | 2022-02-21 | 2020-08-26 | 2021-08-25
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20GHCL | GRANT - LAUNDROMART CONSTRUCTION | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-08-26 | 2022-02-21 | 2021-08-26 | 2022-02-21
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20JFPG | JEFFERSON HOUSES PLAYGROUND RENOVATION | 1 | DEVELOP SCOPE | 2020-09-01 | 2020-11-29 | 2020-09-01 | 2020-11-29
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20JFPG | JEFFERSON HOUSES PLAYGROUND RENOVATION | 2 | PRELIMINARY DESIGN | 2020-11-30 | 2021-03-29 | 2020-11-30 | 2021-03-29
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20JFPG | JEFFERSON HOUSES PLAYGROUND RENOVATION | 3 | FINAL DESIGN | 2021-03-30 | 2021-09-25 | 2021-03-30 | 2021-09-25
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20JFPG | JEFFERSON HOUSES PLAYGROUND RENOVATION | 4 | BID AWARD AND REGISTER CONTRCT | 2021-09-26 | 2021-12-24 | 2021-09-26 | 2021-12-24
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20JFPG | JEFFERSON HOUSES PLAYGROUND RENOVATION | 5 | CONSTRUCTION TO 25% | 2021-12-25 | 2022-04-23 | 2021-12-25 | 2022-04-23
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20JFPG | JEFFERSON HOUSES PLAYGROUND RENOVATION | 6 | CONSTRUCTION TO 50% | 2022-04-24 | 2022-08-21 | 2022-04-24 | 2022-08-21
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20JFPG | JEFFERSON HOUSES PLAYGROUND RENOVATION | 7 | CONSTRUCTION TO 75% | 2022-08-22 | 2022-12-19 | 2022-08-22 | 2022-12-19
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20JFPG | JEFFERSON HOUSES PLAYGROUND RENOVATION | 8 | ORIGINAL EQUIP & FURNISHING | 2022-12-20 | 2023-03-19 | 2022-12-20 | 2023-03-19
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20JFPG | JEFFERSON HOUSES PLAYGROUND RENOVATION | 9 | SUBSTANTIAL COMPLETION | 2023-03-20 | 2023-05-18 | 2023-03-20 | 2023-05-18
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20JFPG | JEFFERSON HOUSES PLAYGROUND RENOVATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-05-19 | 2023-06-17 | 2023-05-19 | 2023-06-17
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20LESD | LES INFILL 1 NEW LAYERED ACCESS DOORS | 1 | DEVELOP SCOPE | 2020-09-01 | 2020-11-29 | 2020-09-01 | 2020-11-29
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20LESD | LES INFILL 1 NEW LAYERED ACCESS DOORS | 2 | PRELIMINARY DESIGN | 2020-11-30 | 2021-03-29 | 2020-11-30 | 2021-03-29
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20LESD | LES INFILL 1 NEW LAYERED ACCESS DOORS | 3 | FINAL DESIGN | 2021-03-30 | 2021-09-25 | 2021-03-30 | 2021-09-25
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20LESD | LES INFILL 1 NEW LAYERED ACCESS DOORS | 4 | BID AWARD AND REGISTER CONTRCT | 2021-09-26 | 2021-12-24 | 2021-09-26 | 2021-12-24
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20LESD | LES INFILL 1 NEW LAYERED ACCESS DOORS | 5 | CONSTRUCTION TO 25% | 2021-12-25 | 2022-04-23 | 2021-12-25 | 2022-04-23
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20LESD | LES INFILL 1 NEW LAYERED ACCESS DOORS | 6 | CONSTRUCTION TO 50% | 2022-04-24 | 2022-08-21 | 2022-04-24 | 2022-08-21
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20LESD | LES INFILL 1 NEW LAYERED ACCESS DOORS | 7 | CONSTRUCTION TO 75% | 2022-08-22 | 2022-12-19 | 2022-08-22 | 2022-12-19
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20LESD | LES INFILL 1 NEW LAYERED ACCESS DOORS | 8 | ORIGINAL EQUIP & FURNISHING | 2022-12-20 | 2023-03-19 | 2022-12-20 | 2023-03-19
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20LESD | LES INFILL 1 NEW LAYERED ACCESS DOORS | 9 | SUBSTANTIAL COMPLETION | 2023-03-20 | 2023-05-18 | 2023-03-20 | 2023-05-18
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20LESD | LES INFILL 1 NEW LAYERED ACCESS DOORS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-05-19 | 2023-06-17 | 2023-05-19 | 2023-06-17
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20SGCU | STRAUS HOUSES GARBAGE COMPACTOR | 1 | DESIGN | 2019-09-01 | 2020-02-27 | 2019-09-01 | 2020-02-27
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20SGCU | STRAUS HOUSES GARBAGE COMPACTOR | 2 | BID AWARD AND REGISTER CONTRCT | 2020-02-28 | 2020-08-25 | 2020-02-28 | 2020-08-25
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20SGCU | STRAUS HOUSES GARBAGE COMPACTOR | 3 | CONSTRUCTION | 2020-08-26 | 2021-08-25 | 2020-08-26 | 2021-08-25
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20SGCU | STRAUS HOUSES GARBAGE COMPACTOR | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-08-26 | 2022-02-21 | 2020-08-26 | 2021-08-25
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20SGCU | STRAUS HOUSES GARBAGE COMPACTOR | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-08-26 | 2022-02-21 | 2021-08-26 | 2022-02-21
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20SHDR | ALFRED SMITH -DOG RUN FOR 10 CATHERINE SLIP | 1 | DESIGN | 2019-09-01 | 2020-02-27 | 2019-09-01 | 2020-02-27
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20SHDR | ALFRED SMITH -DOG RUN FOR 10 CATHERINE SLIP | 2 | BID AWARD AND REGISTER CONTRCT | 2020-02-28 | 2020-08-25 | 2020-02-28 | 2020-08-25
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20SHDR | ALFRED SMITH -DOG RUN FOR 10 CATHERINE SLIP | 3 | CONSTRUCTION | 2020-08-26 | 2021-08-25 | 2020-08-26 | 2021-08-25
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20SHDR | ALFRED SMITH -DOG RUN FOR 10 CATHERINE SLIP | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-08-26 | 2022-02-21 | 2020-08-26 | 2021-08-25
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20SHDR | ALFRED SMITH -DOG RUN FOR 10 CATHERINE SLIP | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-08-26 | 2022-02-21 | 2021-08-26 | 2022-02-21
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20SISC | STANLEY ISAACS SENIOR CENTER BATHROOM ADA UPGRADE | 1 | DESIGN | 2013-12-30 | 2017-12-01 | 2013-12-30 | 2017-12-01
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20SISC | STANLEY ISAACS SENIOR CENTER BATHROOM ADA UPGRADE | 2 | BID AWARD AND REGISTER CONTRCT | 2017-01-01 | 2017-06-29 | 2017-01-01 | 2017-06-29
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20SISC | STANLEY ISAACS SENIOR CENTER BATHROOM ADA UPGRADE | 3 | CONSTRUCTION | 2017-06-30 | 2018-06-29 | 2017-06-30 | 2018-06-29
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20SISC | STANLEY ISAACS SENIOR CENTER BATHROOM ADA UPGRADE | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-07-05 | 2019-12-31 | 2017-06-30 | 2018-06-29
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20SISC | STANLEY ISAACS SENIOR CENTER BATHROOM ADA UPGRADE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-07-05 | 2019-12-31 | 2018-07-05 | 2019-12-31
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20SPER | SEWARD PARK EXTENSION RENOVATIONS | 1 | DESIGN | 2019-09-01 | 2020-02-27 | 2019-09-01 | 2020-02-27
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20SPER | SEWARD PARK EXTENSION RENOVATIONS | 2 | BID AWARD AND REGISTER CONTRCT | 2020-02-28 | 2020-08-25 | 2020-02-28 | 2020-08-25
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20SPER | SEWARD PARK EXTENSION RENOVATIONS | 3 | CONSTRUCTION | 2020-08-26 | 2021-08-25 | 2020-08-26 | 2021-08-25
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20SPER | SEWARD PARK EXTENSION RENOVATIONS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-08-26 | 2022-02-21 | 2020-08-26 | 2021-08-25
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20SPER | SEWARD PARK EXTENSION RENOVATIONS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-08-26 | 2022-02-21 | 2021-08-26 | 2022-02-21
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20TUSD | TAFT UNDERGROUND STEAM DISTRIBUTION | 1 | DESIGN | 2020-09-01 | 2021-02-27 | 2020-09-01 | 2021-02-27
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20TUSD | TAFT UNDERGROUND STEAM DISTRIBUTION | 2 | BID AWARD AND REGISTER CONTRCT | 2021-02-28 | 2021-08-26 | 2021-02-28 | 2021-08-26
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20TUSD | TAFT UNDERGROUND STEAM DISTRIBUTION | 3 | CONSTRUCTION | 2021-08-27 | 2022-08-26 | 2021-08-27 | 2022-08-26
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20TUSD | TAFT UNDERGROUND STEAM DISTRIBUTION | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-08-27 | 2023-02-22 | 2021-08-27 | 2022-08-26
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20TUSD | TAFT UNDERGROUND STEAM DISTRIBUTION | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-08-27 | 2023-02-22 | 2022-08-27 | 2023-02-22
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20WSCC | WOODSON CCTV | 1 | DESIGN | 2019-06-30 | 2019-12-26 | 2019-06-30 | 2019-12-26
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20WSCC | WOODSON CCTV | 2 | BID AWARD AND REGISTER CONTRCT | 2019-12-27 | 2020-06-23 | 2019-12-27 | 2020-06-23
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20WSCC | WOODSON CCTV | 3 | CONSTRUCTION | 2020-06-24 | 2021-06-23 | 2020-06-24 | 2021-06-23
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20WSCC | WOODSON CCTV | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-06-24 | 2021-12-20 | 2020-06-24 | 2021-06-23
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20WSCC | WOODSON CCTV | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-06-24 | 2021-12-20 | 2021-06-24 | 2021-12-20
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20WSLP | WOODSON LIGHT POLES | 1 | DESIGN | 2019-06-30 | 2019-12-26 | 2019-06-30 | 2019-12-26
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20WSLP | WOODSON LIGHT POLES | 2 | BID AWARD AND REGISTER CONTRCT | 2019-12-27 | 2020-06-23 | 2019-12-27 | 2020-06-23
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20WSLP | WOODSON LIGHT POLES | 3 | CONSTRUCTION | 2020-06-24 | 2021-06-23 | 2020-06-24 | 2021-06-23
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20WSLP | WOODSON LIGHT POLES | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-06-24 | 2021-12-20 | 2020-06-24 | 2021-06-23
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20WSLP | WOODSON LIGHT POLES | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-06-24 | 2021-12-20 | 2021-06-24 | 2021-12-20
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21DYEL | DYCKMAN HOUSES ELEVATOR REPLACEMENT | 1 | DESIGN | 2021-06-01 | 2021-11-27 | 2019-06-30 | 2020-06-29
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21DYEL | DYCKMAN HOUSES ELEVATOR REPLACEMENT | 2 | BID AWARD AND REGISTER CONTRCT | 2021-11-28 | 2022-04-21 | 2020-06-30 | 2020-11-21
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21DYEL | DYCKMAN HOUSES ELEVATOR REPLACEMENT | 3 | CONSTRUCTION | 2022-04-22 | 2023-04-21 | 2020-11-22 | 2022-06-15
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21DYEL | DYCKMAN HOUSES ELEVATOR REPLACEMENT | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-04-22 | 2023-10-18 | 2020-11-22 | 2022-06-15
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21DYEL | DYCKMAN HOUSES ELEVATOR REPLACEMENT | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-04-22 | 2023-10-18 | 2022-06-16 | 2022-09-14
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21MHEL | MELTZER HERNANDEZ HOUSES ELEVATOR REPLACEMENT | 1 | DESIGN | 2021-06-01 | 2021-11-27 | 2019-12-15 | 2020-12-13
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21MHEL | MELTZER HERNANDEZ HOUSES ELEVATOR REPLACEMENT | 2 | BID AWARD AND REGISTER CONTRCT | 2021-11-28 | 2022-04-21 | 2020-12-14 | 2021-05-08
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21MHEL | MELTZER HERNANDEZ HOUSES ELEVATOR REPLACEMENT | 3 | CONSTRUCTION | 2022-04-22 | 2023-04-21 | 2021-05-09 | 2022-11-29
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21MHEL | MELTZER HERNANDEZ HOUSES ELEVATOR REPLACEMENT | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-04-22 | 2023-10-18 | 2021-05-09 | 2022-11-29
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21MHEL | MELTZER HERNANDEZ HOUSES ELEVATOR REPLACEMENT | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-04-22 | 2023-10-18 | 2022-11-30 | 2023-02-28
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22SMGR | SMITH HOUSES INSTALLATION OF GAS RISERS #7 | 1 | DESIGN | 2022-06-30 | 2023-12-31 | 2022-06-30 | 2023-12-31
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22SMGR | SMITH HOUSES INSTALLATION OF GAS RISERS #7 | 2 | BID AWARD AND REGISTER CONTRCT | 2024-01-01 | 2024-07-01 | 2024-01-01 | 2024-07-01
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22SMGR | SMITH HOUSES INSTALLATION OF GAS RISERS #7 | 3 | CONSTRUCTION | 2024-07-02 | 2026-01-22 | 2024-07-02 | 2026-01-22
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22SMGR | SMITH HOUSES INSTALLATION OF GAS RISERS #7 | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2026-01-23 | 2026-04-23 | 2024-07-02 | 2026-01-22
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22SMGR | SMITH HOUSES INSTALLATION OF GAS RISERS #7 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2026-01-23 | 2026-04-23 | 2026-01-23 | 2026-04-23
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22TAEL | TAFT HOUSES ELEVATOR REHABILITATION | 1 | DESIGN | 2022-06-30 | 2023-06-30 | 2022-06-30 | 2023-06-30
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22TAEL | TAFT HOUSES ELEVATOR REHABILITATION | 2 | BID AWARD AND REGISTER CONTRCT | 2023-07-01 | 2023-11-22 | 2023-07-01 | 2023-11-22
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22TAEL | TAFT HOUSES ELEVATOR REHABILITATION | 3 | CONSTRUCTION | 2023-11-23 | 2025-06-15 | 2023-11-23 | 2025-06-15
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22TAEL | TAFT HOUSES ELEVATOR REHABILITATION | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-06-16 | 2025-09-14 | 2023-11-23 | 2025-06-15
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22TAEL | TAFT HOUSES ELEVATOR REHABILITATION | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-06-16 | 2025-09-14 | 2025-06-16 | 2025-09-14
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22WAGR | WAGNER HOUSES GAS RISER REPLACEMENTS | 1 | DESIGN | 2021-07-01 | 2022-06-30 | 2021-07-01 | 2022-06-30
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22WAGR | WAGNER HOUSES GAS RISER REPLACEMENTS | 2 | BID AWARD AND REGISTER CONTRCT | 2022-07-01 | 2022-11-22 | 2022-07-01 | 2022-11-22
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22WAGR | WAGNER HOUSES GAS RISER REPLACEMENTS | 3 | CONSTRUCTION | 2022-11-23 | 2024-06-15 | 2022-11-23 | 2024-06-15
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22WAGR | WAGNER HOUSES GAS RISER REPLACEMENTS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-06-16 | 2024-09-14 | 2022-11-23 | 2024-06-15
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22WAGR | WAGNER HOUSES GAS RISER REPLACEMENTS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-06-16 | 2024-09-14 | 2024-06-16 | 2024-09-14
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18BOI | Replace boilers at Lehman Village and Wilson Houses | 1 | DEVELOP SCOPE | 2020-07-01 | 2020-09-28 | 2020-07-01 | 2020-09-28
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18BOI | Replace boilers at Lehman Village and Wilson Houses | 2 | PRELIMINARY DESIGN | 2020-09-29 | 2021-01-26 | 2020-09-29 | 2021-01-26
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18BOI | Replace boilers at Lehman Village and Wilson Houses | 3 | FINAL DESIGN | 2021-01-27 | 2021-07-25 | 2021-01-27 | 2021-07-25
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18BOI | Replace boilers at Lehman Village and Wilson Houses | 4 | BID AWARD AND REGISTER CONTRCT | 2021-07-26 | 2021-10-23 | 2021-07-26 | 2021-10-23
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18BOI | Replace boilers at Lehman Village and Wilson Houses | 5 | CONSTRUCTION TO 25% | 2021-10-24 | 2022-02-20 | 2021-10-24 | 2022-02-20
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18BOI | Replace boilers at Lehman Village and Wilson Houses | 6 | CONSTRUCTION TO 50% | 2022-02-21 | 2022-06-20 | 2022-02-21 | 2022-06-20
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18BOI | Replace boilers at Lehman Village and Wilson Houses | 7 | CONSTRUCTION TO 75% | 2022-06-21 | 2022-10-18 | 2022-06-21 | 2022-10-18
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18BOI | Replace boilers at Lehman Village and Wilson Houses | 8 | ORIGINAL EQUIP & FURNISHING | 2022-10-19 | 2023-01-16 | 2022-10-19 | 2023-01-16
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18BOI | Replace boilers at Lehman Village and Wilson Houses | 9 | SUBSTANTIAL COMPLETION | 2023-01-17 | 2023-03-17 | 2023-01-17 | 2023-03-17
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18BOI | Replace boilers at Lehman Village and Wilson Houses | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-03-18 | 2023-04-16 | 2023-03-18 | 2023-04-16
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18ECC | Renovations at Early Childhood Centers in East Harlem | 1 | DEVELOP SCOPE | 2020-07-01 | 2020-09-28 | 2020-07-01 | 2020-09-28
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18ECC | Renovations at Early Childhood Centers in East Harlem | 2 | PRELIMINARY DESIGN | 2020-09-29 | 2021-01-26 | 2020-09-29 | 2021-01-26
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18ECC | Renovations at Early Childhood Centers in East Harlem | 3 | FINAL DESIGN | 2021-01-27 | 2021-07-25 | 2021-01-27 | 2021-07-25
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18ECC | Renovations at Early Childhood Centers in East Harlem | 4 | BID AWARD AND REGISTER CONTRCT | 2021-07-26 | 2021-10-23 | 2021-07-26 | 2021-10-23
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18ECC | Renovations at Early Childhood Centers in East Harlem | 5 | CONSTRUCTION TO 25% | 2021-10-24 | 2022-02-20 | 2021-10-24 | 2022-02-20
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18ECC | Renovations at Early Childhood Centers in East Harlem | 6 | CONSTRUCTION TO 50% | 2022-02-21 | 2022-06-20 | 2022-02-21 | 2022-06-20
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18ECC | Renovations at Early Childhood Centers in East Harlem | 7 | CONSTRUCTION TO 75% | 2022-06-21 | 2022-10-18 | 2022-06-21 | 2022-10-18
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18ECC | Renovations at Early Childhood Centers in East Harlem | 8 | ORIGINAL EQUIP & FURNISHING | 2022-10-19 | 2023-01-16 | 2022-10-19 | 2023-01-16
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18ECC | Renovations at Early Childhood Centers in East Harlem | 9 | SUBSTANTIAL COMPLETION | 2023-01-17 | 2023-03-17 | 2023-01-17 | 2023-03-17
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18ECC | Renovations at Early Childhood Centers in East Harlem | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-03-18 | 2023-04-16 | 2023-03-18 | 2023-04-16
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18ELV | New Elevators at 335 East 111th Street | 1 | DEVELOP SCOPE | 2020-09-30 | 2020-12-28 | 2020-09-30 | 2020-12-28
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18ELV | New Elevators at 335 East 111th Street | 2 | PRELIMINARY DESIGN | 2020-12-29 | 2021-04-27 | 2020-12-29 | 2021-04-27
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18ELV | New Elevators at 335 East 111th Street | 3 | FINAL DESIGN | 2021-04-28 | 2021-10-24 | 2021-04-28 | 2021-10-24
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18ELV | New Elevators at 335 East 111th Street | 4 | BID AWARD AND REGISTER CONTRCT | 2021-10-25 | 2022-01-22 | 2021-10-25 | 2022-01-22
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18ELV | New Elevators at 335 East 111th Street | 5 | CONSTRUCTION TO 25% | 2022-01-23 | 2022-05-22 | 2022-01-23 | 2022-05-22
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18ELV | New Elevators at 335 East 111th Street | 6 | CONSTRUCTION TO 50% | 2022-05-23 | 2022-09-19 | 2022-05-23 | 2022-09-19
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18ELV | New Elevators at 335 East 111th Street | 7 | CONSTRUCTION TO 75% | 2022-09-20 | 2023-01-17 | 2022-09-20 | 2023-01-17
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18ELV | New Elevators at 335 East 111th Street | 8 | ORIGINAL EQUIP & FURNISHING | 2023-01-18 | 2023-04-17 | 2023-01-18 | 2023-04-17
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18ELV | New Elevators at 335 East 111th Street | 9 | SUBSTANTIAL COMPLETION | 2023-04-18 | 2023-06-16 | 2023-04-18 | 2023-06-16
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18ELV | New Elevators at 335 East 111th Street | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-06-17 | 2023-07-16 | 2023-06-17 | 2023-07-16
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18GAS | Install new gas risers at Johnson Houses Install new gas ris | 1 | DEVELOP SCOPE | 2020-07-01 | 2020-09-28 | 2020-07-01 | 2020-09-28
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18GAS | Install new gas risers at Johnson Houses Install new gas ris | 2 | PRELIMINARY DESIGN | 2020-09-29 | 2021-01-26 | 2020-09-29 | 2021-01-26
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18GAS | Install new gas risers at Johnson Houses Install new gas ris | 3 | FINAL DESIGN | 2021-01-27 | 2021-07-25 | 2021-01-27 | 2021-07-25
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18GAS | Install new gas risers at Johnson Houses Install new gas ris | 4 | BID AWARD AND REGISTER CONTRCT | 2021-07-26 | 2021-10-23 | 2021-07-26 | 2021-10-23
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18GAS | Install new gas risers at Johnson Houses Install new gas ris | 5 | CONSTRUCTION TO 25% | 2021-10-24 | 2022-02-20 | 2021-10-24 | 2022-02-20
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18GAS | Install new gas risers at Johnson Houses Install new gas ris | 6 | CONSTRUCTION TO 50% | 2022-02-21 | 2022-06-20 | 2022-02-21 | 2022-06-20
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18GAS | Install new gas risers at Johnson Houses Install new gas ris | 7 | CONSTRUCTION TO 75% | 2022-06-21 | 2022-10-18 | 2022-06-21 | 2022-10-18
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18GAS | Install new gas risers at Johnson Houses Install new gas ris | 8 | ORIGINAL EQUIP & FURNISHING | 2022-10-19 | 2023-01-16 | 2022-10-19 | 2023-01-16
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18GAS | Install new gas risers at Johnson Houses Install new gas ris | 9 | SUBSTANTIAL COMPLETION | 2023-01-17 | 2023-03-17 | 2023-01-17 | 2023-03-17
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18GAS | Install new gas risers at Johnson Houses Install new gas ris | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-03-18 | 2023-04-16 | 2023-03-18 | 2023-04-16
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18ROF | Conduct roof and parapet work at UPACA (Site 5) | 1 | DEVELOP SCOPE | 2020-09-30 | 2020-12-28 | 2020-09-30 | 2020-12-28
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18ROF | Conduct roof and parapet work at UPACA (Site 5) | 2 | PRELIMINARY DESIGN | 2020-12-29 | 2021-04-27 | 2020-12-29 | 2021-04-27
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18ROF | Conduct roof and parapet work at UPACA (Site 5) | 3 | FINAL DESIGN | 2021-04-28 | 2021-10-24 | 2021-04-28 | 2021-10-24
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18ROF | Conduct roof and parapet work at UPACA (Site 5) | 4 | BID AWARD AND REGISTER CONTRCT | 2021-10-25 | 2022-01-22 | 2021-10-25 | 2022-01-22
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18ROF | Conduct roof and parapet work at UPACA (Site 5) | 5 | CONSTRUCTION TO 25% | 2022-01-23 | 2022-05-22 | 2022-01-23 | 2022-05-22
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18ROF | Conduct roof and parapet work at UPACA (Site 5) | 6 | CONSTRUCTION TO 50% | 2022-05-23 | 2022-09-19 | 2022-05-23 | 2022-09-19
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18ROF | Conduct roof and parapet work at UPACA (Site 5) | 7 | CONSTRUCTION TO 75% | 2022-09-20 | 2023-01-17 | 2022-09-20 | 2023-01-17
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18ROF | Conduct roof and parapet work at UPACA (Site 5) | 8 | ORIGINAL EQUIP & FURNISHING | 2023-01-18 | 2023-04-17 | 2023-01-18 | 2023-04-17
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18ROF | Conduct roof and parapet work at UPACA (Site 5) | 9 | SUBSTANTIAL COMPLETION | 2023-04-18 | 2023-06-16 | 2023-04-18 | 2023-06-16
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18ROF | Conduct roof and parapet work at UPACA (Site 5) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-06-17 | 2023-07-16 | 2023-06-17 | 2023-07-16
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18VNT | Modernize ventilation systems in 17 East Harlem Developments | 1 | DEVELOP SCOPE | 2020-07-01 | 2020-09-28 | 2020-07-01 | 2020-09-28
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18VNT | Modernize ventilation systems in 17 East Harlem Developments | 2 | PRELIMINARY DESIGN | 2020-09-29 | 2021-01-26 | 2020-09-29 | 2021-01-26
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18VNT | Modernize ventilation systems in 17 East Harlem Developments | 3 | FINAL DESIGN | 2021-01-27 | 2021-07-25 | 2021-01-27 | 2021-07-25
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18VNT | Modernize ventilation systems in 17 East Harlem Developments | 4 | BID AWARD AND REGISTER CONTRCT | 2021-07-26 | 2021-10-23 | 2021-07-26 | 2021-10-23
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18VNT | Modernize ventilation systems in 17 East Harlem Developments | 5 | CONSTRUCTION TO 25% | 2021-10-24 | 2022-02-20 | 2021-10-24 | 2022-02-20
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18VNT | Modernize ventilation systems in 17 East Harlem Developments | 6 | CONSTRUCTION TO 50% | 2022-02-21 | 2022-06-20 | 2022-02-21 | 2022-06-20
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18VNT | Modernize ventilation systems in 17 East Harlem Developments | 7 | CONSTRUCTION TO 75% | 2022-06-21 | 2022-10-18 | 2022-06-21 | 2022-10-18
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18VNT | Modernize ventilation systems in 17 East Harlem Developments | 8 | ORIGINAL EQUIP & FURNISHING | 2022-10-19 | 2023-01-16 | 2022-10-19 | 2023-01-16
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18VNT | Modernize ventilation systems in 17 East Harlem Developments | 9 | SUBSTANTIAL COMPLETION | 2023-01-17 | 2023-03-17 | 2023-01-17 | 2023-03-17
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18VNT | Modernize ventilation systems in 17 East Harlem Developments | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-03-18 | 2023-04-16 | 2023-03-18 | 2023-04-16
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | P-3WAGNER | Wagner Playground, Manhattan | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | P-3WAGNER | Wagner Playground, Manhattan | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2016-12-28 | 2017-12-27
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | P-3WAGNER | Wagner Playground, Manhattan | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2017-12-28 | 2018-09-23
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | P-3WAGNER | Wagner Playground, Manhattan | 4 | CONSTRUCTION | 2018-09-24 | 2019-09-23 | 2018-09-24 | 2019-09-23
20201123 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | P-3WAGNER | Wagner Playground, Manhattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | ACEDOH501 | DOHMH - LIGHTING UPGRADES | 1 | DEVELOP SCOPE | 2015-01-01 | 2015-03-31 | 2015-01-01 | 2015-03-31
20201123 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | ACEDOH501 | DOHMH - LIGHTING UPGRADES | 2 | PRELIMINARY DESIGN | 2015-04-01 | 2015-07-29 | 2015-04-01 | 2015-07-29
20201123 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | ACEDOH501 | DOHMH - LIGHTING UPGRADES | 3 | FINAL DESIGN | 2015-07-30 | 2016-01-25 | 2015-07-30 | 2016-01-25
20201123 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | ACEDOH501 | DOHMH - LIGHTING UPGRADES | 4 | BID AWARD AND REGISTER CONTRCT | 2016-01-26 | 2016-04-24 | 2016-01-26 | 2016-04-24
20201123 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | ACEDOH501 | DOHMH - LIGHTING UPGRADES | 5 | CONSTRUCTION TO 25% | 2016-04-25 | 2016-08-22 | 2016-04-25 | 2016-08-22
20201123 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | ACEDOH501 | DOHMH - LIGHTING UPGRADES | 6 | CONSTRUCTION TO 50% | 2016-08-23 | 2016-12-20 | 2016-08-23 | 2016-12-20
20201123 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | ACEDOH501 | DOHMH - LIGHTING UPGRADES | 7 | CONSTRUCTION TO 75% | 2016-12-21 | 2017-04-19 | 2016-12-21 | 2017-04-19
20201123 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | ACEDOH501 | DOHMH - LIGHTING UPGRADES | 8 | ORIGINAL EQUIP & FURNISHING | 2017-04-20 | 2017-07-18 | 2017-04-20 | 2017-07-18
20201123 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | ACEDOH501 | DOHMH - LIGHTING UPGRADES | 9 | SUBSTANTIAL COMPLETION | 2017-07-19 | 2017-09-16 | 2017-07-19 | 2017-09-16
20201123 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | ACEDOH501 | DOHMH - LIGHTING UPGRADES | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-09-17 | 2017-10-16 | 2017-09-17 | 2020-12-20
20201123 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | ACEDOH502 | DOHMH - LED LIGHTING UPGRADE | 1 | DESIGN | 2017-01-01 | 2017-03-31 | 2017-07-01 | 2017-09-28
20201123 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | ACEDOH502 | DOHMH - LED LIGHTING UPGRADE | 2 | CONSTRUCTION | 2017-04-01 | 2017-06-29 | 2017-09-29 | 2020-12-20
20201123 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82ACDOG | DOHMH ANIMAL CARE CENTERS - RECONSTRUCTION OF DOG KENNELS | 1 | DESIGN | 2018-04-01 | 2018-09-27 | 2018-04-01 | 2018-09-27
20201123 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82ACDOG | DOHMH ANIMAL CARE CENTERS - RECONSTRUCTION OF DOG KENNELS | 2 | CONSTRUCTION | 2018-09-28 | 2019-03-26 | 2018-09-28 | 2021-06-20
20201123 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82CHRHC | Central Harlem Health Center interior renovation | 1 | DESIGN | 2019-01-01 | 2020-05-24 | 2019-01-01 | 2019-03-31
20201123 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82CHRHC | Central Harlem Health Center interior renovation | 2 | CONSTRUCTION | 2020-05-25 | 2025-05-23 | 2019-04-01 | 2019-07-29
20201123 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82CHRHC | Central Harlem Health Center interior renovation | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-05-24 | 2025-05-23 | 2019-07-30 | 2020-01-25
20201123 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82CHRHC | Central Harlem Health Center interior renovation | 4 | DEVELOP SCOPE | 2025-05-24 | 2025-05-23 | 2020-01-26 | 2020-04-24
20201123 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82CHRHC | Central Harlem Health Center interior renovation | 5 | PRELIMINARY DESIGN | 2025-05-24 | 2025-05-23 | 2020-04-25 | 2020-08-22
20201123 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82CHRHC | Central Harlem Health Center interior renovation | 6 | FINAL DESIGN | 2025-05-24 | 2025-05-23 | 2020-08-23 | 2020-12-20
20201123 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82CHRHC | Central Harlem Health Center interior renovation | 7 | BID AWARD AND REGISTER CONTRCT | 2025-05-24 | 2025-05-23 | 2020-12-21 | 2021-04-19
20201123 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82CHRHC | Central Harlem Health Center interior renovation | 8 | CONSTRUCTION TO 25% | 2025-05-24 | 2025-05-23 | 2021-04-20 | 2021-07-18
20201123 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82CHRHC | Central Harlem Health Center interior renovation | 9 | CONSTRUCTION TO 50% | 2025-05-24 | 2025-05-23 | 2021-07-19 | 2021-09-16
20201123 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82CHRHC | Central Harlem Health Center interior renovation | 10 | CONSTRUCTION TO 75% | 2025-05-24 | 2025-05-23 | 2021-09-17 | 2025-10-16
20201123 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82CHRHC | Central Harlem Health Center interior renovation | 11 | ORIGINAL EQUIP & FURNISHING | 2025-05-24 | 2025-05-23 | 2021-09-17 | 2025-10-16
20201123 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82CHRHC | Central Harlem Health Center interior renovation | 12 | SUBSTANTIAL COMPLETION | 2025-05-24 | 2025-05-23 | 2021-09-17 | 2025-10-16
20201123 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82CHRHC | Central Harlem Health Center interior renovation | 13 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-05-24 | 2025-06-22 | 2021-09-17 | 2025-10-16
20201123 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82EASTH | EAST HARLEM HEALTH HUB | 1 | DESIGN | 2017-02-01 | 2017-03-02 | 2017-02-01 | 2017-03-02
20201123 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82EASTH | EAST HARLEM HEALTH HUB | 2 | CONSTRUCTION | 2017-03-03 | 2017-03-02 | 2017-03-03 | 2018-03-02
20201123 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82EASTH | EAST HARLEM HEALTH HUB | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-03 | 2017-05-01 | 2018-03-03 | 2021-06-28
20201123 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82EHREL | EAST HARLEM HEALTH CENTER ELEVATOR MODERNIZATION | 1 | DESIGN | 2020-07-01 | 2020-12-27 | 2020-07-01 | 2020-12-27
20201123 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82EHREL | EAST HARLEM HEALTH CENTER ELEVATOR MODERNIZATION | 2 | CONSTRUCTION | 2020-12-28 | 2021-06-25 | 2020-12-28 | 2021-06-25
20201123 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82EHRHC | East Harlem Health Center interior renovation | 1 | DESIGN | 2015-06-01 | 2016-10-22 | 2016-07-01 | 2016-12-27
20201123 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82EHRHC | East Harlem Health Center interior renovation | 2 | CONSTRUCTION | 2016-10-23 | 2021-10-21 | 2016-12-28 | 2018-01-01
20201123 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82EHRHC | East Harlem Health Center interior renovation | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-10-22 | 2021-10-21 | 2018-01-02 | 2022-12-28
20201123 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82EHRHC | East Harlem Health Center interior renovation | 4 | DEVELOP SCOPE | 2021-10-22 | 2021-10-21 | 2018-01-02 | 2022-12-28
20201123 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82EHRHC | East Harlem Health Center interior renovation | 5 | PRELIMINARY DESIGN | 2021-10-22 | 2021-10-21 | 2018-01-02 | 2022-12-28
20201123 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82EHRHC | East Harlem Health Center interior renovation | 6 | FINAL DESIGN | 2021-10-22 | 2021-10-21 | 2018-01-02 | 2022-12-28
20201123 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82EHRHC | East Harlem Health Center interior renovation | 7 | BID AWARD AND REGISTER CONTRCT | 2021-10-22 | 2021-10-21 | 2018-01-02 | 2022-12-28
20201123 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82EHRHC | East Harlem Health Center interior renovation | 8 | CONSTRUCTION TO 25% | 2021-10-22 | 2021-10-21 | 2018-01-02 | 2022-12-28
20201123 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82EHRHC | East Harlem Health Center interior renovation | 9 | CONSTRUCTION TO 50% | 2021-10-22 | 2021-10-21 | 2018-01-02 | 2022-12-28
20201123 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82EHRHC | East Harlem Health Center interior renovation | 10 | CONSTRUCTION TO 75% | 2021-10-22 | 2021-10-21 | 2018-01-02 | 2022-12-28
20201123 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82EHRHC | East Harlem Health Center interior renovation | 11 | ORIGINAL EQUIP & FURNISHING | 2021-10-22 | 2021-10-21 | 2018-01-02 | 2022-12-28
20201123 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82EHRHC | East Harlem Health Center interior renovation | 12 | SUBSTANTIAL COMPLETION | 2021-10-22 | 2021-10-21 | 2018-01-02 | 2022-12-28
20201123 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82EHRHC | East Harlem Health Center interior renovation | 13 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-10-22 | 2021-11-20 | 2018-01-02 | 2022-12-28
20201123 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82OCMEX | OCME - New Medical Examiner Facility | 1 | DEVELOP SCOPE | 2007-04-01 | 2007-06-29 | 2016-07-01 | 2016-09-28
20201123 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82OCMEX | OCME - New Medical Examiner Facility | 2 | PRELIMINARY DESIGN | 2007-06-30 | 2007-10-27 | 2016-09-29 | 2017-01-26
20201123 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82OCMEX | OCME - New Medical Examiner Facility | 3 | FINAL DESIGN | 2007-10-28 | 2008-04-24 | 2017-01-27 | 2017-07-25
20201123 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82OCMEX | OCME - New Medical Examiner Facility | 4 | BID AWARD AND REGISTER CONTRCT | 2008-04-25 | 2008-07-23 | 2017-07-26 | 2017-10-23
20201123 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82OCMEX | OCME - New Medical Examiner Facility | 5 | CONSTRUCTION TO 25% | 2008-07-24 | 2008-11-20 | 2017-10-24 | 2018-02-20
20201123 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82OCMEX | OCME - New Medical Examiner Facility | 6 | CONSTRUCTION TO 50% | 2008-11-21 | 2009-03-20 | 2018-02-21 | 2018-06-20
20201123 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82OCMEX | OCME - New Medical Examiner Facility | 7 | CONSTRUCTION TO 75% | 2009-03-21 | 2009-07-18 | 2018-06-21 | 2018-10-18
20201123 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82OCMEX | OCME - New Medical Examiner Facility | 8 | ORIGINAL EQUIP & FURNISHING | 2009-07-19 | 2009-10-16 | 2018-10-19 | 2019-01-16
20201123 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82OCMEX | OCME - New Medical Examiner Facility | 9 | SUBSTANTIAL COMPLETION | 2009-10-17 | 2009-12-15 | 2019-01-17 | 2019-03-17
20201123 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82OCMEX | OCME - New Medical Examiner Facility | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2009-12-16 | 2010-01-14 | 2019-03-18 | 2023-07-31
20201123 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82PHLNB | DOHMH FACILITIES | 1 | DESIGN | 2011-03-01 | 2012-07-22 | 2013-11-08 | 2015-04-01
20201123 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82PHLNB | DOHMH FACILITIES | 2 | CONSTRUCTION | 2012-07-23 | 2017-07-21 | 2015-04-02 | 2020-03-30
20201123 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82PHLNB | DOHMH FACILITIES | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-07-22 | 2017-10-19 | 2020-03-31 | 2023-06-28
20201123 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82WASHT | WASHINGTON HEIGHTS HEALTH CENTER FACADE RENOVATION | 1 | DESIGN | 2018-06-05 | 2018-12-01 | 2018-06-05 | 2018-12-01
20201123 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82WASHT | WASHINGTON HEIGHTS HEALTH CENTER FACADE RENOVATION | 2 | CONSTRUCTION | 2018-12-02 | 2019-05-30 | 2018-12-02 | 2025-06-28
20201123 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL99ANIC1 | ANIMAL CARE & CONTROL OF NEW YORK CITY | 1 | DESIGN | 2005-10-10 | 2007-03-03 | 2016-07-01 | 2016-09-28
20201123 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL99ANIC1 | ANIMAL CARE & CONTROL OF NEW YORK CITY | 2 | CONSTRUCTION | 2007-03-04 | 2012-03-01 | 2016-09-29 | 2017-05-01
20201123 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL99ANIC1 | ANIMAL CARE & CONTROL OF NEW YORK CITY | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-03-02 | 2012-05-30 | 2017-05-02 | 2021-06-28
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 02200901 | CENTRAL OFFICE: PRIMARY CARE INITIATIVE | 1 | DESIGN | 2019-02-11 | 2020-01-01 | 2022-02-11 | 2022-04-11
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 02200901 | CENTRAL OFFICE: PRIMARY CARE INITIATIVE | 2 | CONSTRUCTION | 2020-01-02 | 2020-12-31 | 2022-02-11 | 2022-04-11
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 02200901 | CENTRAL OFFICE: PRIMARY CARE INITIATIVE | 3 | CONSTRUCTION | 2020-01-02 | 2020-12-31 | 2022-04-12 | 2023-04-11
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 02201805 | LWH: REPLACE COOLING TOWER AND UPGRADES TO CHILLER & BOILER | 1 | DESIGN | 2019-01-06 | 2019-07-04 | 2021-01-06 | 2021-07-04
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 02201805 | LWH: REPLACE COOLING TOWER AND UPGRADES TO CHILLER & BOILER | 2 | CONSTRUCTION | 2019-07-05 | 2019-12-31 | 2021-07-05 | 2021-12-31
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 02201901 | H+H: RENOVATE AND OUTFIT OFFICES AT 50 WATER STREET | 1 | DESIGN | 2019-08-11 | 2020-06-30 | 2019-08-11 | 2020-06-30
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 02201901 | H+H: RENOVATE AND OUTFIT OFFICES AT 50 WATER STREET | 2 | CONSTRUCTION | 2020-07-01 | 2021-06-30 | 2019-08-11 | 2020-06-30
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 02201901 | H+H: RENOVATE AND OUTFIT OFFICES AT 50 WATER STREET | 3 | CONSTRUCTION | 2020-07-01 | 2021-06-30 | 2020-07-01 | 2023-10-13
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 11200912 | BELLEVUE: EMERGENCY PIPE INSTALLATION, 22ND FLOOR | 1 | DESIGN | 2009-05-06 | 2009-11-01 | 2009-09-01 | 2009-11-29
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 11200912 | BELLEVUE: EMERGENCY PIPE INSTALLATION, 22ND FLOOR | 2 | CONSTRUCTION | 2009-11-02 | 2010-04-30 | 2009-11-02 | 2021-04-30
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 11201001 | BHC: OR UPGRADE | 1 | DESIGN | 2014-02-10 | 2014-12-31 | 2014-02-10 | 2014-12-31
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 11201001 | BHC: OR UPGRADE | 2 | CONSTRUCTION | 2015-01-01 | 2015-12-31 | 2014-02-10 | 2014-12-31
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 11201001 | BHC: OR UPGRADE | 3 | CONSTRUCTION | 2015-01-01 | 2015-12-31 | 2015-01-01 | 2020-12-31
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 11201601 | BELLEVUE: REPLACE TWO INDOOR COOLING TOWERS | 1 | DESIGN | 2019-02-11 | 2020-01-01 | 2019-02-11 | 2020-01-01
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 11201601 | BELLEVUE: REPLACE TWO INDOOR COOLING TOWERS | 2 | CONSTRUCTION | 2020-01-02 | 2020-12-31 | 2019-02-11 | 2020-01-01
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 11201601 | BELLEVUE: REPLACE TWO INDOOR COOLING TOWERS | 3 | CONSTRUCTION | 2020-01-02 | 2020-12-31 | 2020-01-02 | 2023-12-31
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 11201705 | BHC: CONSTRUCT NEW CHEMISTRY LABORATORY | 1 | DESIGN | 2019-02-11 | 2020-01-01 | 2019-02-11 | 2020-01-01
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 11201705 | BHC: CONSTRUCT NEW CHEMISTRY LABORATORY | 2 | CONSTRUCTION | 2020-01-02 | 2020-12-31 | 2019-02-11 | 2020-01-01
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 11201705 | BHC: CONSTRUCT NEW CHEMISTRY LABORATORY | 3 | CONSTRUCTION | 2020-01-02 | 2020-12-31 | 2020-01-02 | 2020-12-31
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 11201803 | BHC: EXPAND HEIGHT OF GUARDRAILS IN THE ACB ATRIUM | 1 | DESIGN | 2019-08-11 | 2020-06-30 | 2019-08-11 | 2020-06-30
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 11201803 | BHC: EXPAND HEIGHT OF GUARDRAILS IN THE ACB ATRIUM | 2 | CONSTRUCTION | 2020-07-01 | 2021-06-30 | 2019-08-11 | 2020-06-30
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 11201803 | BHC: EXPAND HEIGHT OF GUARDRAILS IN THE ACB ATRIUM | 3 | CONSTRUCTION | 2020-07-01 | 2021-06-30 | 2020-07-01 | 2021-06-30
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 11201901 | BHC: CONVERT SPACE TO CREATE 4 PYXIS MEDICATION ROOMS | 1 | DESIGN | 2019-07-07 | 2020-01-02 | 2019-07-07 | 2020-01-02
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 11201901 | BHC: CONVERT SPACE TO CREATE 4 PYXIS MEDICATION ROOMS | 2 | CONSTRUCTION | 2020-01-03 | 2020-06-30 | 2020-01-03 | 2022-06-30
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 11201903 | BELLEVUE: RENOVATION AND UPGRADE OF TRAUMA SLOTS IN ADULT ED | 1 | DESIGN | 2019-12-31 | 2021-05-23 | 2019-12-31 | 2021-05-23
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 11201903 | BELLEVUE: RENOVATION AND UPGRADE OF TRAUMA SLOTS IN ADULT ED | 2 | CONSTRUCTION | 2021-05-24 | 2024-05-22 | 2021-05-24 | 2024-05-22
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 11201903 | BELLEVUE: RENOVATION AND UPGRADE OF TRAUMA SLOTS IN ADULT ED | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-05-23 | 2024-08-20 | 2024-05-23 | 2024-08-20
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 11201904 | BHC: UNDERGROUND STORAGE TANK SUMP UPGRADES | 1 | DESIGN | 2019-02-11 | 2020-01-01 | 2019-02-11 | 2020-01-01
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 11201904 | BHC: UNDERGROUND STORAGE TANK SUMP UPGRADES | 2 | CONSTRUCTION | 2020-01-02 | 2020-12-31 | 2019-02-11 | 2020-01-01
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 11201904 | BHC: UNDERGROUND STORAGE TANK SUMP UPGRADES | 3 | CONSTRUCTION | 2020-01-02 | 2020-12-31 | 2020-01-02 | 2020-12-31
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 11202001 | BELLEVUE: ELEVATOR DOOR LOCK MONITORING | 1 | DESIGN | 2021-03-06 | 2022-07-28 | 2021-03-06 | 2022-07-28
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 11202001 | BELLEVUE: ELEVATOR DOOR LOCK MONITORING | 2 | CONSTRUCTION | 2022-07-29 | 2025-07-27 | 2022-07-29 | 2025-07-27
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 11202001 | BELLEVUE: ELEVATOR DOOR LOCK MONITORING | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-07-28 | 2025-10-25 | 2025-07-28 | 2025-10-25
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 11202101 | BELLEVUE: REPLACE EMERGENCY DEPT NURSES STATION | 1 | DESIGN | 2020-11-11 | 2021-02-01 | 2020-11-11 | 2021-02-01
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 11202101 | BELLEVUE: REPLACE EMERGENCY DEPT NURSES STATION | 2 | CONSTRUCTION | 2021-02-02 | 2021-06-02 | 2021-02-02 | 2021-06-02
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 11202101 | BELLEVUE: REPLACE EMERGENCY DEPT NURSES STATION | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-06-03 | 2021-08-31 | 2021-06-03 | 2021-08-31
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 12201501 | GOUVERNEUR: ROBERTO CLEMENTE CENTER RENOVATION | 1 | DESIGN | 2014-11-09 | 2016-04-01 | 2014-11-09 | 2016-04-01
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 12201501 | GOUVERNEUR: ROBERTO CLEMENTE CENTER RENOVATION | 2 | CONSTRUCTION | 2016-04-02 | 2018-04-01 | 2016-04-02 | 2021-07-30
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 12201501 | GOUVERNEUR: ROBERTO CLEMENTE CENTER RENOVATION | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-04-02 | 2018-06-30 | 2021-07-31 | 2021-10-28
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 12201702 | GHS: INSTALL SECONDARY WATER DISINFECTION SYS-LTACH & SNF | 2 | CONSTRUCTION | 2019-01-02 | 2019-06-30 | 2019-01-02 | 2019-06-30
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 12201801 | GHS: REHABILITATE FACADE - CYCLE 7B AMENDED AND CYCLE 8B | 1 | DESIGN | 2019-01-06 | 2019-07-04 | 2019-01-06 | 2019-07-04
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 12201801 | GHS: REHABILITATE FACADE - CYCLE 7B AMENDED AND CYCLE 8B | 2 | CONSTRUCTION | 2019-07-05 | 2019-12-31 | 2019-07-05 | 2020-10-30
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 12201804 | JUDSON, REMOVE AND REPLACE FIRE LINE | 1 | DESIGN | 2019-01-06 | 2019-07-04 | 2019-01-06 | 2019-07-04
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 12201804 | JUDSON, REMOVE AND REPLACE FIRE LINE | 2 | CONSTRUCTION | 2019-07-05 | 2019-12-31 | 2019-07-05 | 2019-12-31
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 12201902 | GOUVERNEUR: RENOVATE COURTYARD | 1 | DESIGN | 2020-01-07 | 2020-07-04 | 2020-07-01 | 2020-09-01
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 12201902 | GOUVERNEUR: RENOVATE COURTYARD | 2 | CONSTRUCTION | 2020-07-05 | 2020-12-31 | 2020-09-02 | 2021-02-28
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 12201903 | GHS: INSTALL CHIMNEY LINER AT JUDSON | 1 | DESIGN | 2020-01-07 | 2020-07-04 | 2021-01-07 | 2021-04-30
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 12201903 | GHS: INSTALL CHIMNEY LINER AT JUDSON | 2 | CONSTRUCTION | 2020-07-05 | 2020-12-31 | 2021-05-01 | 2021-10-27
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 12202001 | GOUVERNEUR:DIESEL GENERATOR PIPE REPLACEMENT | 1 | DESIGN | 2021-02-01 | 2022-06-25 | 2021-02-01 | 2022-06-25
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 12202001 | GOUVERNEUR:DIESEL GENERATOR PIPE REPLACEMENT | 2 | CONSTRUCTION | 2022-06-26 | 2025-06-24 | 2022-06-26 | 2025-06-24
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 12202001 | GOUVERNEUR:DIESEL GENERATOR PIPE REPLACEMENT | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-06-25 | 2025-09-22 | 2025-06-25 | 2025-09-22
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 12202101 | EXPRESS CARE | 1 | DESIGN | 2021-02-01 | 2022-06-25 | 2021-02-01 | 2022-06-25
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 12202101 | EXPRESS CARE | 2 | CONSTRUCTION | 2022-06-26 | 2025-06-24 | 2022-06-26 | 2025-06-24
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 12202101 | EXPRESS CARE | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-06-25 | 2025-09-22 | 2025-06-25 | 2025-09-22
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13200571 | HARLEM: MURALS REMOVAL AND PRESERVATION | 1 | DESIGN | 2007-10-11 | 2009-03-03 | 2007-10-11 | 2009-03-03
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13200571 | HARLEM: MURALS REMOVAL AND PRESERVATION | 2 | CONSTRUCTION | 2009-03-04 | 2014-03-02 | 2009-03-04 | 2023-03-02
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13200571 | HARLEM: MURALS REMOVAL AND PRESERVATION | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-03-03 | 2014-05-31 | 2023-03-03 | 2023-05-31
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13200573 | HARLEM: CONSTRUCT NEW PARKING FACILITY | 1 | DESIGN | 2017-02-10 | 2017-12-31 | 2017-02-10 | 2017-12-31
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13200573 | HARLEM: CONSTRUCT NEW PARKING FACILITY | 2 | CONSTRUCTION | 2018-01-01 | 2018-12-31 | 2017-02-10 | 2017-12-31
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13200573 | HARLEM: CONSTRUCT NEW PARKING FACILITY | 3 | CONSTRUCTION | 2018-01-01 | 2018-12-31 | 2018-01-01 | 2023-12-31
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13200601 | HARLEM HOUSE RELOCATION AND RENOVATION | 1 | DESIGN | 2005-11-06 | 2006-05-04 | 2005-11-06 | 2006-05-04
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13200601 | HARLEM HOUSE RELOCATION AND RENOVATION | 2 | CONSTRUCTION | 2006-05-05 | 2006-10-31 | 2006-05-05 | 2006-10-31
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13200601 | HARLEM HOUSE RELOCATION AND RENOVATION | 3 | DESIGN | 2006-05-05 | 2006-10-31 | 2006-11-01 | 2008-03-24
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13200601 | HARLEM HOUSE RELOCATION AND RENOVATION | 4 | CONSTRUCTION | 2006-05-05 | 2006-10-31 | 2008-03-25 | 2023-03-23
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13200601 | HARLEM HOUSE RELOCATION AND RENOVATION | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2006-05-05 | 2006-10-31 | 2023-03-24 | 2023-06-21
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13201101 | HARLEM: RELOCATE SYDENHAM CLINIC FROM 125TH TO 118TH STREET | 1 | DESIGN | 2010-05-12 | 2011-04-01 | 2010-05-12 | 2011-04-01
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13201101 | HARLEM: RELOCATE SYDENHAM CLINIC FROM 125TH TO 118TH STREET | 2 | CONSTRUCTION | 2011-04-02 | 2012-03-31 | 2010-05-12 | 2011-04-01
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13201101 | HARLEM: RELOCATE SYDENHAM CLINIC FROM 125TH TO 118TH STREET | 3 | CONSTRUCTION | 2011-04-02 | 2012-03-31 | 2011-04-02 | 2023-03-31
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13201301 | HARLEM: RENOVATE POST PARTUM UNIT | 1 | DESIGN | 2014-05-12 | 2015-04-01 | 2014-05-12 | 2015-04-01
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13201301 | HARLEM: RENOVATE POST PARTUM UNIT | 2 | CONSTRUCTION | 2015-04-02 | 2016-03-31 | 2014-05-12 | 2015-04-01
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13201301 | HARLEM: RENOVATE POST PARTUM UNIT | 3 | CONSTRUCTION | 2015-04-02 | 2016-03-31 | 2015-04-02 | 2021-03-31
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13201401 | HARLEM: CONSTRUCT GERIATRICS CENTER | 1 | DESIGN | 2014-10-06 | 2015-04-03 | 2014-10-06 | 2015-04-03
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13201401 | HARLEM: CONSTRUCT GERIATRICS CENTER | 2 | CONSTRUCTION | 2015-04-04 | 2015-09-30 | 2015-04-04 | 2021-09-30
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13201501 | HARLEM: UPGRADE VENTILATION SYSTEM IN THE BOILER ROOM | 1 | DESIGN | 2015-12-12 | 2016-10-31 | 2015-12-12 | 2016-10-31
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13201501 | HARLEM: UPGRADE VENTILATION SYSTEM IN THE BOILER ROOM | 2 | CONSTRUCTION | 2016-11-01 | 2017-10-31 | 2015-12-12 | 2016-10-31
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13201501 | HARLEM: UPGRADE VENTILATION SYSTEM IN THE BOILER ROOM | 3 | CONSTRUCTION | 2016-11-01 | 2017-10-31 | 2016-11-01 | 2021-10-31
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13201502 | HARLEM: UPGRADE ELECTRICAL SYSTEM | 1 | DESIGN | 2016-05-11 | 2017-03-31 | 2015-12-12 | 2016-10-31
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13201502 | HARLEM: UPGRADE ELECTRICAL SYSTEM | 2 | CONSTRUCTION | 2017-04-01 | 2018-03-31 | 2015-12-12 | 2016-10-31
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13201502 | HARLEM: UPGRADE ELECTRICAL SYSTEM | 3 | CONSTRUCTION | 2017-04-01 | 2018-03-31 | 2017-04-01 | 2022-03-31
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13201602 | HARLEM: REHABILITATE THE EXTERIOR FACADE OF MLK BLG - LL 11 | 1 | DESIGN | 2018-05-12 | 2019-10-03 | 2018-05-12 | 2019-10-03
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13201602 | HARLEM: REHABILITATE THE EXTERIOR FACADE OF MLK BLG - LL 11 | 2 | CONSTRUCTION | 2019-10-04 | 2021-10-02 | 2019-10-04 | 2021-10-02
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13201602 | HARLEM: REHABILITATE THE EXTERIOR FACADE OF MLK BLG - LL 11 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-10-03 | 2021-12-31 | 2021-10-03 | 2021-12-31
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13201603 | HARLEM: WP DECANTING, ONR DEMOLITION, & NEW DATA CENTER | 1 | DESIGN | 2018-11-09 | 2020-04-01 | 2018-11-09 | 2020-04-01
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13201603 | HARLEM: WP DECANTING, ONR DEMOLITION, & NEW DATA CENTER | 2 | CONSTRUCTION | 2020-04-02 | 2022-04-01 | 2020-04-02 | 2022-04-01
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13201603 | HARLEM: WP DECANTING, ONR DEMOLITION, & NEW DATA CENTER | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-04-02 | 2022-06-30 | 2022-04-02 | 2022-06-30
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13201701 | HARLEM: CONSTRUCT RESPITE CENTER | 1 | DESIGN | 2019-02-11 | 2020-01-01 | 2019-02-11 | 2020-01-01
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13201701 | HARLEM: CONSTRUCT RESPITE CENTER | 2 | CONSTRUCTION | 2020-01-02 | 2020-12-31 | 2019-02-11 | 2020-01-01
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13201701 | HARLEM: CONSTRUCT RESPITE CENTER | 3 | CONSTRUCTION | 2020-01-02 | 2020-12-31 | 2020-01-02 | 2023-12-31
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13201803 | HARLEM: KOUNTZ PAVILION STAIRWELL REHABILITATION | 1 | DESIGN | 2019-07-07 | 2020-01-02 | 2019-07-07 | 2020-01-02
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13201803 | HARLEM: KOUNTZ PAVILION STAIRWELL REHABILITATION | 2 | CONSTRUCTION | 2020-01-03 | 2020-06-30 | 2020-01-03 | 2022-06-30
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13201901 | HARLEM: RENOVATE MP4 SPACE TO CREATE A DIALYSIS UNIT | 1 | DESIGN | 2019-02-11 | 2020-01-01 | 2019-02-11 | 2020-01-01
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13201901 | HARLEM: RENOVATE MP4 SPACE TO CREATE A DIALYSIS UNIT | 2 | CONSTRUCTION | 2020-01-02 | 2020-12-31 | 2019-02-11 | 2020-01-01
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13201901 | HARLEM: RENOVATE MP4 SPACE TO CREATE A DIALYSIS UNIT | 3 | CONSTRUCTION | 2020-01-02 | 2020-12-31 | 2020-01-02 | 2020-12-31
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13202001 | HARLEM: RELOCATE VARIOUS DEPARTMENTS FROM THE WP | 1 | DESIGN | 2020-02-11 | 2020-12-31 | 2020-02-11 | 2020-12-31
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13202001 | HARLEM: RELOCATE VARIOUS DEPARTMENTS FROM THE WP | 2 | CONSTRUCTION | 2021-01-01 | 2021-12-31 | 2020-02-11 | 2020-12-31
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13202001 | HARLEM: RELOCATE VARIOUS DEPARTMENTS FROM THE WP | 3 | CONSTRUCTION | 2021-01-01 | 2021-12-31 | 2021-01-01 | 2021-12-31
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13202101 | ELEVATOR MER HVAC UPGRADE | 1 | DESIGN | 2021-02-01 | 2022-06-25 | 2021-02-01 | 2022-06-25
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13202101 | ELEVATOR MER HVAC UPGRADE | 2 | CONSTRUCTION | 2022-06-26 | 2025-06-24 | 2022-06-26 | 2025-06-24
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13202101 | ELEVATOR MER HVAC UPGRADE | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-06-25 | 2025-09-22 | 2025-06-25 | 2025-09-22
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 18201515 | SYDENHAM: RENOVATE WOMEN'S HEALTH SERVICES - MAMMOGRAPHY | 1 | DESIGN | 2015-01-06 | 2015-07-04 | 2015-01-06 | 2015-07-04
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 18201515 | SYDENHAM: RENOVATE WOMEN'S HEALTH SERVICES - MAMMOGRAPHY | 2 | CONSTRUCTION | 2015-07-05 | 2015-12-31 | 2015-07-05 | 2015-12-31
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 18201801 | SYDENHAM: ERODED WALL REPLACEMENT | 3 | CONSTRUCTION | 2019-07-02 | 2020-06-30 | 2019-07-02 | 2020-06-30
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 18202001 | SYDENHAM: RETAIL PHARMACY RENOVATION | 1 | DESIGN | 2019-09-30 | 2021-02-20 | 2019-09-30 | 2021-02-20
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 18202001 | SYDENHAM: RETAIL PHARMACY RENOVATION | 2 | CONSTRUCTION | 2021-02-21 | 2024-02-20 | 2021-02-21 | 2024-02-20
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 18202001 | SYDENHAM: RETAIL PHARMACY RENOVATION | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-02-21 | 2024-05-20 | 2024-02-21 | 2024-05-20
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37201301 | MHC: COMPLETE RENOVATION OF SIXTH FLOOR 6C MAIN BLDG | 1 | DESIGN | 2018-08-11 | 2019-07-01 | 2018-08-11 | 2019-07-01
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37201301 | MHC: COMPLETE RENOVATION OF SIXTH FLOOR 6C MAIN BLDG | 2 | CONSTRUCTION | 2019-07-02 | 2020-06-30 | 2018-08-11 | 2019-07-01
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37201301 | MHC: COMPLETE RENOVATION OF SIXTH FLOOR 6C MAIN BLDG | 3 | CONSTRUCTION | 2019-07-02 | 2020-06-30 | 2019-07-02 | 2020-06-30
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37201401 | MHC: INSTALL PERIMETER GATE/FENCING & SIGNAGE-LANDSCAPING | 1 | DESIGN | 2017-08-10 | 2018-06-30 | 2017-08-10 | 2018-06-30
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37201401 | MHC: INSTALL PERIMETER GATE/FENCING & SIGNAGE-LANDSCAPING | 2 | CONSTRUCTION | 2018-07-01 | 2019-06-30 | 2017-08-10 | 2018-06-30
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37201401 | MHC: INSTALL PERIMETER GATE/FENCING & SIGNAGE-LANDSCAPING | 3 | CONSTRUCTION | 2018-07-01 | 2019-06-30 | 2018-07-01 | 2021-06-30
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37201501 | MHC: ESTABLISH A COMPREHENSIVE LBGT FAMILY HEALTH CENTER | 1 | DESIGN | 2018-08-11 | 2019-07-01 | 2018-08-11 | 2019-07-01
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37201501 | MHC: ESTABLISH A COMPREHENSIVE LBGT FAMILY HEALTH CENTER | 2 | CONSTRUCTION | 2019-07-02 | 2020-06-30 | 2018-08-11 | 2019-07-01
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37201501 | MHC: ESTABLISH A COMPREHENSIVE LBGT FAMILY HEALTH CENTER | 3 | CONSTRUCTION | 2019-07-02 | 2020-06-30 | 2019-07-02 | 2022-06-30
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37201601 | MHC: EXTERIOR FACADE RESTORATION CAMPUS-WIDE | 1 | DESIGN | 2018-07-06 | 2019-01-01 | 2018-07-06 | 2019-01-01
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37201601 | MHC: EXTERIOR FACADE RESTORATION CAMPUS-WIDE | 2 | CONSTRUCTION | 2019-01-02 | 2019-06-30 | 2019-01-02 | 2020-06-30
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37201901 | MHC: REPLACE MEDIUM PRESSURE STEAM CONDENSATE RETURN RISER | 1 | DESIGN | 2020-01-07 | 2020-07-04 | 2020-01-07 | 2020-07-04
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37201901 | MHC: REPLACE MEDIUM PRESSURE STEAM CONDENSATE RETURN RISER | 2 | CONSTRUCTION | 2020-07-05 | 2020-12-31 | 2020-07-05 | 2020-12-31
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37202001 | METROPOLITAN : REPLACE MRI AT MODULAR MRI BUILDING | 1 | DESIGN | 2020-05-13 | 2021-10-04 | 2020-05-13 | 2021-10-04
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37202001 | METROPOLITAN : REPLACE MRI AT MODULAR MRI BUILDING | 2 | CONSTRUCTION | 2021-10-05 | 2024-10-03 | 2021-10-05 | 2024-10-03
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37202001 | METROPOLITAN : REPLACE MRI AT MODULAR MRI BUILDING | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-10-04 | 2025-01-01 | 2024-10-04 | 2025-01-01
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37202002 | METROPOLITAN: WINDOW REPLACEMENT | 1 | DESIGN | 2020-05-13 | 2021-10-04 | 2020-05-13 | 2021-10-04
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37202002 | METROPOLITAN: WINDOW REPLACEMENT | 2 | CONSTRUCTION | 2021-10-05 | 2024-10-03 | 2021-10-05 | 2024-10-03
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37202002 | METROPOLITAN: WINDOW REPLACEMENT | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-10-04 | 2025-01-01 | 2024-10-04 | 2025-01-01
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37202003 | MET: EMERGENCY POWER SEPARATION AND UPGRADES | 1 | DESIGN | 2020-05-13 | 2021-10-04 | 2020-05-13 | 2021-10-04
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37202003 | MET: EMERGENCY POWER SEPARATION AND UPGRADES | 2 | CONSTRUCTION | 2021-10-05 | 2024-10-03 | 2021-10-05 | 2024-10-03
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37202003 | MET: EMERGENCY POWER SEPARATION AND UPGRADES | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-10-04 | 2025-01-01 | 2024-10-04 | 2025-01-01
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37202004 | METROPOLITAN: CREATE URGENT CARE CENTER | 1 | DESIGN | 2020-05-13 | 2021-10-04 | 2020-05-13 | 2021-10-04
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37202004 | METROPOLITAN: CREATE URGENT CARE CENTER | 2 | CONSTRUCTION | 2021-10-05 | 2024-10-03 | 2021-10-05 | 2024-10-03
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37202004 | METROPOLITAN: CREATE URGENT CARE CENTER | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-10-04 | 2025-01-01 | 2024-10-04 | 2025-01-01
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37202005 | METROPOLITAN: Roof Replacement at OPD & Mental Health Bldgs | 1 | DESIGN | 2020-05-13 | 2021-10-04 | 2020-05-13 | 2021-10-04
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37202005 | METROPOLITAN: Roof Replacement at OPD & Mental Health Bldgs | 2 | CONSTRUCTION | 2021-10-05 | 2024-10-03 | 2021-10-05 | 2024-10-03
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37202005 | METROPOLITAN: Roof Replacement at OPD & Mental Health Bldgs | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-10-04 | 2025-01-01 | 2024-10-04 | 2025-01-01
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37202101 | METROPOLITAN: RENOVATION OF INFUSION CENTER | 1 | DESIGN | 2020-05-01 | 2021-09-22 | 2020-05-01 | 2021-09-22
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37202101 | METROPOLITAN: RENOVATION OF INFUSION CENTER | 2 | CONSTRUCTION | 2021-09-23 | 2023-09-22 | 2021-09-23 | 2023-09-22
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37202101 | METROPOLITAN: RENOVATION OF INFUSION CENTER | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-23 | 2023-12-21 | 2023-09-23 | 2023-12-21
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37202102 | CHILLER PLANT UPGRADE | 1 | DESIGN | 2020-05-01 | 2021-09-22 | 2020-05-01 | 2021-09-22
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37202102 | CHILLER PLANT UPGRADE | 2 | CONSTRUCTION | 2021-09-23 | 2023-09-22 | 2021-09-23 | 2023-09-22
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37202102 | CHILLER PLANT UPGRADE | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-23 | 2023-12-21 | 2023-09-23 | 2023-12-21
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37202103 | FIRE PROTECTION UPGRADES | 1 | DESIGN | 2020-05-01 | 2021-09-22 | 2020-05-01 | 2021-09-22
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37202103 | FIRE PROTECTION UPGRADES | 2 | CONSTRUCTION | 2021-09-23 | 2023-09-22 | 2021-09-23 | 2023-09-22
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37202103 | FIRE PROTECTION UPGRADES | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-23 | 2023-12-21 | 2023-09-23 | 2023-12-21
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37202104 | FACADE RESTORATION CYCLE 9 | 1 | DESIGN | 2020-05-01 | 2021-09-22 | 2020-05-01 | 2021-09-22
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37202104 | FACADE RESTORATION CYCLE 9 | 2 | CONSTRUCTION | 2021-09-23 | 2023-09-22 | 2021-09-23 | 2023-09-22
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37202104 | FACADE RESTORATION CYCLE 9 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-23 | 2023-12-21 | 2023-09-23 | 2023-12-21
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 67200901 | COLER: RENOVATE THE NURSING FACILITY DAY ROOM | 1 | DESIGN | 2019-07-07 | 2020-01-02 | 2019-07-07 | 2020-01-02
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 67200901 | COLER: RENOVATE THE NURSING FACILITY DAY ROOM | 2 | CONSTRUCTION | 2020-01-03 | 2020-06-30 | 2020-01-03 | 2023-06-30
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 67201170 | COLER: WINDOW REPLACEMENT AND ROOF/FACADE REHABILITATION | 1 | DESIGN | 2020-05-01 | 2021-09-22 | 2020-05-01 | 2021-09-22
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 67201170 | COLER: WINDOW REPLACEMENT AND ROOF/FACADE REHABILITATION | 2 | CONSTRUCTION | 2021-09-23 | 2023-09-22 | 2021-09-23 | 2023-09-22
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 67201170 | COLER: WINDOW REPLACEMENT AND ROOF/FACADE REHABILITATION | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-23 | 2023-12-21 | 2023-09-23 | 2023-12-21
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | ACEHHC403 | HARLEM HOSPITAL CENTER ENERGY UPGRADE | 1 | DEVELOP SCOPE | 2013-03-17 | 2013-06-14 | 2013-03-17 | 2013-06-14
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | ACEHHC403 | HARLEM HOSPITAL CENTER ENERGY UPGRADE | 2 | PRELIMINARY DESIGN | 2013-06-15 | 2013-10-12 | 2013-06-15 | 2013-10-12
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | ACEHHC403 | HARLEM HOSPITAL CENTER ENERGY UPGRADE | 3 | FINAL DESIGN | 2013-10-13 | 2014-04-10 | 2013-10-13 | 2014-04-10
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | ACEHHC403 | HARLEM HOSPITAL CENTER ENERGY UPGRADE | 4 | BID AWARD AND REGISTER CONTRCT | 2014-04-11 | 2014-07-09 | 2014-04-11 | 2014-07-09
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | ACEHHC403 | HARLEM HOSPITAL CENTER ENERGY UPGRADE | 5 | CONSTRUCTION TO 25% | 2014-07-10 | 2014-11-06 | 2014-07-10 | 2014-11-06
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | ACEHHC403 | HARLEM HOSPITAL CENTER ENERGY UPGRADE | 6 | CONSTRUCTION TO 50% | 2014-11-07 | 2015-03-06 | 2014-11-07 | 2015-03-06
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | ACEHHC403 | HARLEM HOSPITAL CENTER ENERGY UPGRADE | 7 | CONSTRUCTION TO 75% | 2015-03-07 | 2015-07-04 | 2015-03-07 | 2015-07-04
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | ACEHHC403 | HARLEM HOSPITAL CENTER ENERGY UPGRADE | 8 | ORIGINAL EQUIP & FURNISHING | 2015-07-05 | 2015-10-02 | 2015-07-05 | 2015-10-02
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | ACEHHC403 | HARLEM HOSPITAL CENTER ENERGY UPGRADE | 9 | SUBSTANTIAL COMPLETION | 2015-10-03 | 2015-12-01 | 2015-10-03 | 2021-12-01
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | ACEHHC403 | HARLEM HOSPITAL CENTER ENERGY UPGRADE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-12-02 | 2015-12-31 | 2021-12-02 | 2021-12-31
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | ACEHHC406 | HHC- BELLEVUE HOSPITAL CHILLERS | 1 | DESIGN | 2015-11-10 | 2017-04-02 | 2015-11-10 | 2017-04-02
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | ACEHHC406 | HHC- BELLEVUE HOSPITAL CHILLERS | 2 | CONSTRUCTION | 2017-04-03 | 2020-04-01 | 2017-04-03 | 2021-04-01
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | ACEHHC406 | HHC- BELLEVUE HOSPITAL CHILLERS | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-04-02 | 2020-06-30 | 2021-04-02 | 2021-06-30
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | ACEHHC408 | HHC Coler Hospital Boiler Replacement | 1 | DESIGN | 2016-11-09 | 2018-04-02 | 2016-11-09 | 2018-04-02
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | ACEHHC408 | HHC Coler Hospital Boiler Replacement | 2 | CONSTRUCTION | 2018-04-03 | 2020-04-01 | 2018-04-03 | 2022-04-01
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | ACEHHC408 | HHC Coler Hospital Boiler Replacement | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-04-02 | 2020-06-30 | 2022-04-02 | 2022-06-30
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | ACEHHC602 | BHC LIGHTTING AND CONTROLS UPGRADE | 1 | DESIGN | 2015-11-10 | 2017-04-02 | 2015-11-10 | 2017-04-02
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | ACEHHC602 | BHC LIGHTTING AND CONTROLS UPGRADE | 2 | CONSTRUCTION | 2017-04-03 | 2020-04-01 | 2017-04-03 | 2021-04-01
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | ACEHHC602 | BHC LIGHTTING AND CONTROLS UPGRADE | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-04-02 | 2020-06-30 | 2021-04-02 | 2021-06-30
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | SAND1117 | BHC: MEP MITIGATION | 1 | DESIGN | 2019-02-11 | 2020-01-01 | 2019-02-11 | 2020-01-01
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | SAND1117 | BHC: MEP MITIGATION | 2 | CONSTRUCTION | 2020-01-02 | 2020-12-31 | 2019-02-11 | 2020-01-01
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | SAND1117 | BHC: MEP MITIGATION | 3 | CONSTRUCTION | 2020-01-02 | 2020-12-31 | 2020-01-02 | 2020-12-31
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | SAND1121 | BHC: Elevate Security Systems | 1 | DESIGN | 2020-05-01 | 2021-09-22 | 2020-05-01 | 2021-09-22
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | SAND1121 | BHC: Elevate Security Systems | 2 | CONSTRUCTION | 2021-09-23 | 2023-09-22 | 2021-09-23 | 2023-09-22
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | SAND1121 | BHC: Elevate Security Systems | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-23 | 2023-12-21 | 2023-09-23 | 2023-12-21
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | SAND11B | BELLEVUE RECONSTRUCTION AS A RESULT OF SANDY | 1 | DESIGN | 2013-05-06 | 2013-11-01 | 2013-05-06 | 2013-11-01
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | SAND11B | BELLEVUE RECONSTRUCTION AS A RESULT OF SANDY | 2 | CONSTRUCTION | 2013-11-02 | 2014-04-30 | 2013-11-02 | 2022-04-30
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | SAND3706 | MHC: INSTALL ELECTRIC AND CHILLER QUICK CONNECTS | 1 | DESIGN | 2018-05-12 | 2019-10-03 | 2018-05-12 | 2019-10-03
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | SAND3706 | MHC: INSTALL ELECTRIC AND CHILLER QUICK CONNECTS | 2 | CONSTRUCTION | 2019-10-04 | 2021-10-02 | 2019-10-04 | 2021-10-02
20201123 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | SAND3706 | MHC: INSTALL ELECTRIC AND CHILLER QUICK CONNECTS | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-10-03 | 2021-12-31 | 2021-10-03 | 2021-12-31
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | ACEDEP502 | DEP - WARDS ISLAND SHAFT MIXERS | 1 | DEVELOP SCOPE | 2015-06-01 | 2015-08-29 | 2015-06-01 | 2016-11-21
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | ACEDEP502 | DEP - WARDS ISLAND SHAFT MIXERS | 2 | PRELIMINARY DESIGN | 2015-08-30 | 2015-12-27 | 2016-11-22 | 2017-11-21
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | ACEDEP502 | DEP - WARDS ISLAND SHAFT MIXERS | 3 | FINAL DESIGN | 2015-12-28 | 2016-06-24 | 2017-11-22 | 2018-11-21
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | ACEDEP502 | DEP - WARDS ISLAND SHAFT MIXERS | 4 | BID AWARD AND REGISTER CONTRCT | 2016-06-25 | 2016-09-22 | 2018-11-22 | 2020-11-20
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | ACEDEP502 | DEP - WARDS ISLAND SHAFT MIXERS | 5 | CONSTRUCTION TO 25% | 2016-09-23 | 2017-01-20 | 2018-11-22 | 2020-11-20
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | ACEDEP502 | DEP - WARDS ISLAND SHAFT MIXERS | 6 | CONSTRUCTION TO 50% | 2017-01-21 | 2017-05-20 | 2018-11-22 | 2020-11-20
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | ACEDEP502 | DEP - WARDS ISLAND SHAFT MIXERS | 7 | CONSTRUCTION TO 75% | 2017-05-21 | 2017-09-17 | 2018-11-22 | 2020-11-20
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | ACEDEP502 | DEP - WARDS ISLAND SHAFT MIXERS | 8 | ORIGINAL EQUIP & FURNISHING | 2017-09-18 | 2017-12-16 | 2018-11-22 | 2020-11-20
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | ACEDEP502 | DEP - WARDS ISLAND SHAFT MIXERS | 9 | SUBSTANTIAL COMPLETION | 2017-12-17 | 2018-02-14 | 2018-11-22 | 2020-11-20
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | ACEDEP502 | DEP - WARDS ISLAND SHAFT MIXERS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-02-15 | 2018-03-16 | 2018-11-22 | 2020-11-20
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | MED669 | Dist. WM work in 7th Ave between W 14th & W 34th Street, MN | 1 | DEVELOP SCOPE | 2020-11-09 | 2021-08-05 | 2020-11-09 | 2021-08-05
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | MED669 | Dist. WM work in 7th Ave between W 14th & W 34th Street, MN | 2 | PRELIMINARY DESIGN | 2021-08-06 | 2022-07-31 | 2021-08-06 | 2022-07-31
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | MED669 | Dist. WM work in 7th Ave between W 14th & W 34th Street, MN | 3 | FINAL DESIGN | 2022-08-01 | 2024-01-22 | 2022-08-01 | 2024-01-22
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | MED669 | Dist. WM work in 7th Ave between W 14th & W 34th Street, MN | 4 | BID AWARD AND REGISTER CONTRCT | 2024-01-23 | 2024-10-18 | 2024-01-23 | 2024-10-18
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | MED669 | Dist. WM work in 7th Ave between W 14th & W 34th Street, MN | 5 | CONSTRUCTION TO 25% | 2024-10-19 | 2025-10-13 | 2024-10-19 | 2025-10-13
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | MED669 | Dist. WM work in 7th Ave between W 14th & W 34th Street, MN | 6 | CONSTRUCTION TO 50% | 2025-10-14 | 2026-10-08 | 2025-10-14 | 2026-10-08
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | MED669 | Dist. WM work in 7th Ave between W 14th & W 34th Street, MN | 7 | CONSTRUCTION TO 75% | 2026-10-09 | 2027-10-03 | 2026-10-09 | 2027-10-03
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | MED669 | Dist. WM work in 7th Ave between W 14th & W 34th Street, MN | 8 | ORIGINAL EQUIP & FURNISHING | 2027-10-04 | 2028-06-29 | 2027-10-04 | 2028-06-29
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | MED669 | Dist. WM work in 7th Ave between W 14th & W 34th Street, MN | 9 | SUBSTANTIAL COMPLETION | 2028-06-30 | 2028-12-26 | 2028-06-30 | 2028-12-26
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | MED669 | Dist. WM work in 7th Ave between W 14th & W 34th Street, MN | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2028-12-27 | 2029-03-26 | 2028-12-27 | 2029-03-26
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | MED-672 | Install Distribution Water mains throughout Manhattan | 1 | DEVELOP SCOPE | 2019-12-09 | 2020-03-07 | 2022-12-09 | 2023-03-08
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | MED-672 | Install Distribution Water mains throughout Manhattan | 2 | PRELIMINARY DESIGN | 2020-03-08 | 2020-07-05 | 2023-03-09 | 2023-07-06
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | MED-672 | Install Distribution Water mains throughout Manhattan | 3 | FINAL DESIGN | 2020-07-06 | 2021-01-01 | 2023-07-07 | 2024-01-02
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | MED-672 | Install Distribution Water mains throughout Manhattan | 4 | BID AWARD AND REGISTER CONTRCT | 2021-01-02 | 2021-04-01 | 2024-01-03 | 2024-04-01
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | MED-672 | Install Distribution Water mains throughout Manhattan | 5 | CONSTRUCTION TO 25% | 2021-04-02 | 2021-07-30 | 2024-04-02 | 2024-07-30
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | MED-672 | Install Distribution Water mains throughout Manhattan | 6 | CONSTRUCTION TO 50% | 2021-07-31 | 2021-11-27 | 2024-07-31 | 2024-11-27
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | MED-672 | Install Distribution Water mains throughout Manhattan | 7 | CONSTRUCTION TO 75% | 2021-11-28 | 2022-03-27 | 2024-11-28 | 2025-03-27
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | MED-672 | Install Distribution Water mains throughout Manhattan | 8 | ORIGINAL EQUIP & FURNISHING | 2022-03-28 | 2022-06-25 | 2025-03-28 | 2025-06-25
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | MED-672 | Install Distribution Water mains throughout Manhattan | 9 | SUBSTANTIAL COMPLETION | 2022-06-26 | 2022-08-24 | 2025-06-26 | 2025-08-24
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | MED-672 | Install Distribution Water mains throughout Manhattan | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-08-25 | 2022-09-23 | 2025-08-25 | 2025-09-23
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-111-L | RECONSTRUCTION OF PRIMARY TANKS AT NORTH RIVER WPCP | 1 | DEVELOP SCOPE | 2018-03-01 | 2018-05-29 | 2018-06-01 | 2019-02-25
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-111-L | RECONSTRUCTION OF PRIMARY TANKS AT NORTH RIVER WPCP | 2 | PRELIMINARY DESIGN | 2018-05-30 | 2018-09-26 | 2019-02-26 | 2020-02-20
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-111-L | RECONSTRUCTION OF PRIMARY TANKS AT NORTH RIVER WPCP | 3 | FINAL DESIGN | 2018-09-27 | 2019-03-25 | 2020-02-21 | 2021-08-13
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-111-L | RECONSTRUCTION OF PRIMARY TANKS AT NORTH RIVER WPCP | 4 | BID AWARD AND REGISTER CONTRCT | 2019-03-26 | 2019-06-23 | 2021-08-14 | 2022-05-10
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-111-L | RECONSTRUCTION OF PRIMARY TANKS AT NORTH RIVER WPCP | 5 | CONSTRUCTION TO 25% | 2019-06-24 | 2019-10-21 | 2022-05-11 | 2023-05-05
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-111-L | RECONSTRUCTION OF PRIMARY TANKS AT NORTH RIVER WPCP | 6 | CONSTRUCTION TO 50% | 2019-10-22 | 2020-02-18 | 2023-05-06 | 2024-04-29
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-111-L | RECONSTRUCTION OF PRIMARY TANKS AT NORTH RIVER WPCP | 7 | CONSTRUCTION TO 75% | 2020-02-19 | 2020-06-17 | 2024-04-30 | 2025-04-24
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-111-L | RECONSTRUCTION OF PRIMARY TANKS AT NORTH RIVER WPCP | 8 | ORIGINAL EQUIP & FURNISHING | 2020-06-18 | 2020-09-15 | 2025-04-25 | 2026-01-19
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-111-L | RECONSTRUCTION OF PRIMARY TANKS AT NORTH RIVER WPCP | 9 | SUBSTANTIAL COMPLETION | 2020-09-16 | 2020-11-14 | 2026-01-20 | 2034-07-16
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-111-L | RECONSTRUCTION OF PRIMARY TANKS AT NORTH RIVER WPCP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-11-15 | 2020-12-14 | 2034-07-17 | 2034-10-14
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-115-L | RECONSTRUCT POWER DISTRIBUTION EQUIPMENT @ NORTH RIVER WWTP | 1 | DEVELOP SCOPE | 2017-07-01 | 2018-03-27 | 2016-07-01 | 2017-03-27
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-115-L | RECONSTRUCT POWER DISTRIBUTION EQUIPMENT @ NORTH RIVER WWTP | 2 | PRELIMINARY DESIGN | 2018-03-28 | 2019-03-22 | 2017-03-28 | 2018-03-22
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-115-L | RECONSTRUCT POWER DISTRIBUTION EQUIPMENT @ NORTH RIVER WWTP | 3 | FINAL DESIGN | 2019-03-23 | 2020-09-12 | 2018-03-23 | 2019-09-13
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-115-L | RECONSTRUCT POWER DISTRIBUTION EQUIPMENT @ NORTH RIVER WWTP | 4 | BID AWARD AND REGISTER CONTRCT | 2020-09-13 | 2021-06-09 | 2019-09-14 | 2020-06-09
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-115-L | RECONSTRUCT POWER DISTRIBUTION EQUIPMENT @ NORTH RIVER WWTP | 5 | CONSTRUCTION TO 25% | 2021-06-10 | 2022-06-04 | 2020-06-10 | 2021-06-04
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-115-L | RECONSTRUCT POWER DISTRIBUTION EQUIPMENT @ NORTH RIVER WWTP | 6 | CONSTRUCTION TO 50% | 2022-06-05 | 2023-05-30 | 2021-06-05 | 2022-05-30
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-115-L | RECONSTRUCT POWER DISTRIBUTION EQUIPMENT @ NORTH RIVER WWTP | 7 | CONSTRUCTION TO 75% | 2023-05-31 | 2024-05-24 | 2022-05-31 | 2023-05-25
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-115-L | RECONSTRUCT POWER DISTRIBUTION EQUIPMENT @ NORTH RIVER WWTP | 8 | ORIGINAL EQUIP & FURNISHING | 2024-05-25 | 2025-02-18 | 2023-05-26 | 2024-02-19
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-115-L | RECONSTRUCT POWER DISTRIBUTION EQUIPMENT @ NORTH RIVER WWTP | 9 | SUBSTANTIAL COMPLETION | 2025-02-19 | 2025-08-17 | 2024-02-20 | 2024-08-17
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-115-L | RECONSTRUCT POWER DISTRIBUTION EQUIPMENT @ NORTH RIVER WWTP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-08-18 | 2025-11-15 | 2024-08-18 | 2024-11-15
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-124 | RECONSTRUCT DIGESTER GAS SYSTEM AT NORTH RIVER WPCP | 1 | FINAL DESIGN | 2022-06-15 | 2023-12-06 | 2019-06-15 | 2020-12-05
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-124 | RECONSTRUCT DIGESTER GAS SYSTEM AT NORTH RIVER WPCP | 2 | CONSTRUCTION TO 25% | 2023-12-07 | 2024-08-02 | 2020-12-06 | 2021-08-02
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-124 | RECONSTRUCT DIGESTER GAS SYSTEM AT NORTH RIVER WPCP | 3 | CONSTRUCTION TO 50% | 2024-08-03 | 2025-03-30 | 2021-08-03 | 2022-03-30
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-124 | RECONSTRUCT DIGESTER GAS SYSTEM AT NORTH RIVER WPCP | 4 | CONSTRUCTION TO 75% | 2025-03-31 | 2025-11-25 | 2022-03-31 | 2022-11-25
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-131-L | RECONSTRUCTION OF MAIN HYDRAULIC SYSTEM @ NORTH RIVER WWTP | 1 | DEVELOP SCOPE | 2019-06-01 | 2019-08-29 | 2019-06-01 | 2019-08-29
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-131-L | RECONSTRUCTION OF MAIN HYDRAULIC SYSTEM @ NORTH RIVER WWTP | 2 | PRELIMINARY DESIGN | 2019-08-30 | 2019-12-27 | 2019-08-30 | 2019-12-27
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-131-L | RECONSTRUCTION OF MAIN HYDRAULIC SYSTEM @ NORTH RIVER WWTP | 3 | FINAL DESIGN | 2019-12-28 | 2020-06-24 | 2019-12-28 | 2020-06-24
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-131-L | RECONSTRUCTION OF MAIN HYDRAULIC SYSTEM @ NORTH RIVER WWTP | 4 | BID AWARD AND REGISTER CONTRCT | 2020-06-25 | 2020-09-22 | 2020-06-25 | 2020-09-22
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-131-L | RECONSTRUCTION OF MAIN HYDRAULIC SYSTEM @ NORTH RIVER WWTP | 5 | CONSTRUCTION TO 25% | 2020-09-23 | 2021-01-20 | 2020-09-23 | 2021-01-20
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-131-L | RECONSTRUCTION OF MAIN HYDRAULIC SYSTEM @ NORTH RIVER WWTP | 6 | CONSTRUCTION TO 50% | 2021-01-21 | 2021-05-20 | 2021-01-21 | 2021-05-20
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-131-L | RECONSTRUCTION OF MAIN HYDRAULIC SYSTEM @ NORTH RIVER WWTP | 7 | CONSTRUCTION TO 75% | 2021-05-21 | 2021-09-17 | 2021-05-21 | 2021-09-17
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-131-L | RECONSTRUCTION OF MAIN HYDRAULIC SYSTEM @ NORTH RIVER WWTP | 8 | ORIGINAL EQUIP & FURNISHING | 2021-09-18 | 2021-12-16 | 2021-09-18 | 2021-12-16
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-131-L | RECONSTRUCTION OF MAIN HYDRAULIC SYSTEM @ NORTH RIVER WWTP | 9 | SUBSTANTIAL COMPLETION | 2021-12-17 | 2022-02-14 | 2021-12-17 | 2022-02-14
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-131-L | RECONSTRUCTION OF MAIN HYDRAULIC SYSTEM @ NORTH RIVER WWTP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-02-15 | 2022-03-16 | 2022-02-15 | 2022-03-16
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-33 | PROCESS CONTROL | 1 | DEVELOP SCOPE | 2000-05-15 | 2001-02-08 | 2003-01-15 | 2003-10-11
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-33 | PROCESS CONTROL | 2 | PRELIMINARY DESIGN | 2000-05-15 | 2001-05-09 | 2003-10-12 | 2004-10-05
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-33 | PROCESS CONTROL | 3 | FINAL DESIGN | 2001-05-10 | 2002-10-31 | 2004-10-06 | 2006-03-29
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-33 | PROCESS CONTROL | 4 | BID AWARD AND REGISTER CONTRCT | 2002-10-31 | 2003-07-27 | 2006-03-30 | 2006-12-24
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-33 | PROCESS CONTROL | 5 | CONSTRUCTION TO 25% | 2003-07-27 | 2004-07-20 | 2006-12-25 | 2007-12-19
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-33 | PROCESS CONTROL | 6 | CONSTRUCTION TO 50% | 2004-07-20 | 2005-07-14 | 2007-12-20 | 2008-12-13
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-33 | PROCESS CONTROL | 7 | CONSTRUCTION TO 75% | 2005-07-14 | 2006-07-08 | 2008-12-14 | 2009-12-08
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-33 | PROCESS CONTROL | 8 | ORIGINAL EQUIP & FURNISHING | 2006-07-08 | 2007-04-03 | 2009-12-09 | 2010-09-04
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-33 | PROCESS CONTROL | 9 | SUBSTANTIAL COMPLETION | 2007-04-03 | 2007-09-29 | 2010-09-05 | 2019-03-03
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-33 | PROCESS CONTROL | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2007-09-29 | 2007-12-27 | 2019-03-04 | 2021-11-27
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-96-L | INSTALL ATION OF A MOBILE CENTRIFUGE AT NORTH RIVER WPCP | 3 | FINAL DESIGN | 2009-09-27 | 2010-03-25 | 2009-09-27 | 2010-03-25
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-96-L | INSTALL ATION OF A MOBILE CENTRIFUGE AT NORTH RIVER WPCP | 4 | BID AWARD AND REGISTER CONTRCT | 2010-03-26 | 2010-06-23 | 2010-03-26 | 2010-06-23
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-96-L | INSTALL ATION OF A MOBILE CENTRIFUGE AT NORTH RIVER WPCP | 5 | CONSTRUCTION TO 25% | 2010-06-24 | 2010-10-21 | 2010-06-24 | 2010-10-21
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-96-L | INSTALL ATION OF A MOBILE CENTRIFUGE AT NORTH RIVER WPCP | 6 | CONSTRUCTION TO 50% | 2010-10-22 | 2011-02-18 | 2010-10-22 | 2011-02-18
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-96-L | INSTALL ATION OF A MOBILE CENTRIFUGE AT NORTH RIVER WPCP | 7 | CONSTRUCTION TO 75% | 2011-02-19 | 2011-06-18 | 2011-02-19 | 2011-06-18
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-96-L | INSTALL ATION OF A MOBILE CENTRIFUGE AT NORTH RIVER WPCP | 8 | ORIGINAL EQUIP & FURNISHING | 2011-06-19 | 2011-09-16 | 2011-06-19 | 2011-09-16
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-96-L | INSTALL ATION OF A MOBILE CENTRIFUGE AT NORTH RIVER WPCP | 9 | SUBSTANTIAL COMPLETION | 2011-09-17 | 2011-11-15 | 2011-09-17 | 2011-11-15
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-96-L | INSTALL ATION OF A MOBILE CENTRIFUGE AT NORTH RIVER WPCP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2011-11-16 | 2011-12-15 | 2011-11-16 | 2011-12-15
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-COGEN | NORTH RIVER WWTP COGENERATION AND ELECTRIFICATION | 1 | DEVELOP SCOPE | 2013-06-28 | 2014-03-24 | 2013-06-28 | 2014-03-24
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-COGEN | NORTH RIVER WWTP COGENERATION AND ELECTRIFICATION | 2 | PRELIMINARY DESIGN | 2014-03-25 | 2015-03-19 | 2014-03-25 | 2015-03-19
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-COGEN | NORTH RIVER WWTP COGENERATION AND ELECTRIFICATION | 3 | FINAL DESIGN | 2015-03-20 | 2016-09-09 | 2015-03-20 | 2016-09-09
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-COGEN | NORTH RIVER WWTP COGENERATION AND ELECTRIFICATION | 4 | BID AWARD AND REGISTER CONTRCT | 2016-09-10 | 2017-06-06 | 2016-09-10 | 2017-06-06
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-COGEN | NORTH RIVER WWTP COGENERATION AND ELECTRIFICATION | 5 | CONSTRUCTION TO 25% | 2017-06-07 | 2018-06-01 | 2017-06-07 | 2018-06-01
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-COGEN | NORTH RIVER WWTP COGENERATION AND ELECTRIFICATION | 6 | CONSTRUCTION TO 50% | 2018-06-02 | 2019-05-27 | 2018-06-02 | 2019-05-27
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-COGEN | NORTH RIVER WWTP COGENERATION AND ELECTRIFICATION | 7 | CONSTRUCTION TO 75% | 2019-05-28 | 2020-05-21 | 2019-05-28 | 2020-05-21
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-COGEN | NORTH RIVER WWTP COGENERATION AND ELECTRIFICATION | 8 | ORIGINAL EQUIP & FURNISHING | 2020-05-22 | 2021-02-15 | 2020-05-22 | 2021-02-15
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-COGEN | NORTH RIVER WWTP COGENERATION AND ELECTRIFICATION | 9 | SUBSTANTIAL COMPLETION | 2021-02-16 | 2021-08-14 | 2021-02-16 | 2021-08-14
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-COGEN | NORTH RIVER WWTP COGENERATION AND ELECTRIFICATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-08-15 | 2021-11-12 | 2021-08-15 | 2021-11-12
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-ER-003 | NORTH RIVER W.P.C.P. EMERGENCY FIRE SUPPRESSION SYSTEM | 3 | FINAL DESIGN | 2016-12-28 | 2017-06-25 | 2016-12-28 | 2017-06-25
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-ER-003 | NORTH RIVER W.P.C.P. EMERGENCY FIRE SUPPRESSION SYSTEM | 4 | BID AWARD AND REGISTER CONTRCT | 2017-06-26 | 2017-09-23 | 2017-06-26 | 2017-09-23
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-ER-003 | NORTH RIVER W.P.C.P. EMERGENCY FIRE SUPPRESSION SYSTEM | 5 | CONSTRUCTION TO 25% | 2017-09-24 | 2018-01-21 | 2017-09-24 | 2018-01-21
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-ER-003 | NORTH RIVER W.P.C.P. EMERGENCY FIRE SUPPRESSION SYSTEM | 6 | CONSTRUCTION TO 50% | 2018-01-22 | 2018-05-21 | 2018-01-22 | 2018-05-21
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-ER-003 | NORTH RIVER W.P.C.P. EMERGENCY FIRE SUPPRESSION SYSTEM | 7 | CONSTRUCTION TO 75% | 2018-05-22 | 2018-09-18 | 2018-05-22 | 2018-09-18
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-ER-003 | NORTH RIVER W.P.C.P. EMERGENCY FIRE SUPPRESSION SYSTEM | 8 | ORIGINAL EQUIP & FURNISHING | 2018-09-19 | 2018-12-17 | 2018-09-19 | 2018-12-17
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-ER-003 | NORTH RIVER W.P.C.P. EMERGENCY FIRE SUPPRESSION SYSTEM | 9 | SUBSTANTIAL COMPLETION | 2018-12-18 | 2019-02-15 | 2018-12-18 | 2019-02-15
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-ER-003 | NORTH RIVER W.P.C.P. EMERGENCY FIRE SUPPRESSION SYSTEM | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-02-16 | 2019-03-17 | 2019-02-16 | 2019-03-17
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-STRUCT | STRUCTURAL IMPROVEMENTS AT NORTH RIVER WPCP | 1 | DEVELOP SCOPE | 2017-06-01 | 2018-02-25 | 2017-06-01 | 2018-02-25
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-STRUCT | STRUCTURAL IMPROVEMENTS AT NORTH RIVER WPCP | 2 | PRELIMINARY DESIGN | 2018-02-26 | 2019-02-20 | 2018-02-26 | 2019-02-20
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-STRUCT | STRUCTURAL IMPROVEMENTS AT NORTH RIVER WPCP | 3 | FINAL DESIGN | 2019-02-21 | 2020-08-13 | 2019-02-21 | 2020-08-13
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-STRUCT | STRUCTURAL IMPROVEMENTS AT NORTH RIVER WPCP | 4 | BID AWARD AND REGISTER CONTRCT | 2020-08-14 | 2021-05-10 | 2020-08-14 | 2021-05-10
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-STRUCT | STRUCTURAL IMPROVEMENTS AT NORTH RIVER WPCP | 5 | CONSTRUCTION TO 25% | 2021-05-11 | 2022-05-05 | 2021-05-11 | 2022-05-05
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-STRUCT | STRUCTURAL IMPROVEMENTS AT NORTH RIVER WPCP | 6 | CONSTRUCTION TO 50% | 2022-05-06 | 2023-04-30 | 2022-05-06 | 2023-04-30
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-STRUCT | STRUCTURAL IMPROVEMENTS AT NORTH RIVER WPCP | 7 | CONSTRUCTION TO 75% | 2023-05-01 | 2024-04-24 | 2023-05-01 | 2024-04-24
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-STRUCT | STRUCTURAL IMPROVEMENTS AT NORTH RIVER WPCP | 8 | ORIGINAL EQUIP & FURNISHING | 2024-04-25 | 2025-01-19 | 2024-04-25 | 2025-01-19
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-STRUCT | STRUCTURAL IMPROVEMENTS AT NORTH RIVER WPCP | 9 | SUBSTANTIAL COMPLETION | 2025-01-20 | 2025-07-18 | 2025-01-20 | 2025-07-18
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-STRUCT | STRUCTURAL IMPROVEMENTS AT NORTH RIVER WPCP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-07-19 | 2025-10-16 | 2025-07-19 | 2025-10-16
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-278 | PARK DRIVE EAST | 1 | DEVELOP SCOPE | 2016-07-01 | 2017-03-27 | 2016-07-01 | 2017-03-27
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-278 | PARK DRIVE EAST | 2 | PRELIMINARY DESIGN | 2017-03-28 | 2018-03-22 | 2017-03-28 | 2018-03-22
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-278 | PARK DRIVE EAST | 3 | FINAL DESIGN | 2018-03-23 | 2019-09-13 | 2018-03-23 | 2019-09-13
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-278 | PARK DRIVE EAST | 4 | BID AWARD AND REGISTER CONTRCT | 2019-09-14 | 2020-06-09 | 2019-09-14 | 2020-06-09
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-278 | PARK DRIVE EAST | 5 | CONSTRUCTION TO 25% | 2020-06-10 | 2021-06-04 | 2020-06-10 | 2021-06-04
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-278 | PARK DRIVE EAST | 6 | CONSTRUCTION TO 50% | 2021-06-05 | 2022-05-30 | 2021-06-05 | 2022-05-30
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-278 | PARK DRIVE EAST | 7 | CONSTRUCTION TO 75% | 2022-05-31 | 2023-05-25 | 2022-05-31 | 2023-05-25
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-278 | PARK DRIVE EAST | 8 | ORIGINAL EQUIP & FURNISHING | 2023-05-26 | 2024-02-19 | 2023-05-26 | 2024-02-19
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-278 | PARK DRIVE EAST | 9 | SUBSTANTIAL COMPLETION | 2024-02-20 | 2024-08-17 | 2024-02-20 | 2024-08-17
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-278 | PARK DRIVE EAST | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-08-18 | 2024-11-15 | 2024-08-18 | 2024-11-15
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-289 | 19TH STREET PUMPING STATION | 1 | DEVELOP SCOPE | 2020-06-01 | 2021-02-25 | 2020-06-01 | 2021-02-25
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-289 | 19TH STREET PUMPING STATION | 2 | PRELIMINARY DESIGN | 2021-02-26 | 2022-02-20 | 2021-02-26 | 2022-02-20
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-289 | 19TH STREET PUMPING STATION | 3 | FINAL DESIGN | 2022-02-21 | 2023-08-14 | 2022-02-21 | 2023-08-14
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-289 | 19TH STREET PUMPING STATION | 4 | BID AWARD AND REGISTER CONTRCT | 2023-08-15 | 2024-05-10 | 2023-08-15 | 2024-05-10
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-289 | 19TH STREET PUMPING STATION | 5 | CONSTRUCTION TO 25% | 2024-05-11 | 2025-05-05 | 2024-05-11 | 2025-05-05
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-289 | 19TH STREET PUMPING STATION | 6 | CONSTRUCTION TO 50% | 2025-05-06 | 2026-04-30 | 2025-05-06 | 2026-04-30
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-289 | 19TH STREET PUMPING STATION | 7 | CONSTRUCTION TO 75% | 2026-05-01 | 2027-04-25 | 2026-05-01 | 2027-04-25
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-289 | 19TH STREET PUMPING STATION | 8 | ORIGINAL EQUIP & FURNISHING | 2027-04-26 | 2028-01-20 | 2027-04-26 | 2028-01-20
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-289 | 19TH STREET PUMPING STATION | 9 | SUBSTANTIAL COMPLETION | 2028-01-21 | 2028-07-18 | 2028-01-21 | 2028-07-18
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-289 | 19TH STREET PUMPING STATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2028-07-19 | 2028-10-16 | 2028-07-19 | 2028-10-16
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-313 | RECONSTRUCTION OF 235TH STREET PUMPING STATION | 1 | DEVELOP SCOPE | 2016-07-01 | 2017-03-27 | 2016-07-01 | 2017-03-27
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-313 | RECONSTRUCTION OF 235TH STREET PUMPING STATION | 2 | PRELIMINARY DESIGN | 2017-03-28 | 2018-03-22 | 2017-03-28 | 2018-03-22
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-313 | RECONSTRUCTION OF 235TH STREET PUMPING STATION | 3 | FINAL DESIGN | 2018-03-23 | 2019-09-13 | 2018-03-23 | 2019-09-13
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-313 | RECONSTRUCTION OF 235TH STREET PUMPING STATION | 4 | BID AWARD AND REGISTER CONTRCT | 2019-09-14 | 2020-06-09 | 2019-09-14 | 2020-06-09
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-313 | RECONSTRUCTION OF 235TH STREET PUMPING STATION | 5 | CONSTRUCTION TO 25% | 2020-06-10 | 2021-06-04 | 2020-06-10 | 2021-06-04
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-313 | RECONSTRUCTION OF 235TH STREET PUMPING STATION | 6 | CONSTRUCTION TO 50% | 2021-06-05 | 2022-05-30 | 2021-06-05 | 2022-05-30
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-313 | RECONSTRUCTION OF 235TH STREET PUMPING STATION | 7 | CONSTRUCTION TO 75% | 2022-05-31 | 2023-05-25 | 2022-05-31 | 2023-05-25
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-313 | RECONSTRUCTION OF 235TH STREET PUMPING STATION | 8 | ORIGINAL EQUIP & FURNISHING | 2023-05-26 | 2024-02-19 | 2023-05-26 | 2024-02-19
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-313 | RECONSTRUCTION OF 235TH STREET PUMPING STATION | 9 | SUBSTANTIAL COMPLETION | 2024-02-20 | 2024-08-17 | 2024-02-20 | 2024-08-17
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-313 | RECONSTRUCTION OF 235TH STREET PUMPING STATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-08-18 | 2024-11-15 | 2024-08-18 | 2024-11-15
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-348 | REHABILITATION OF DAMAGED NORTH RIVER INTERCEPTOR | 1 | FINAL DESIGN | 2021-06-01 | 2022-11-22 | 2021-06-01 | 2022-11-22
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-348 | REHABILITATION OF DAMAGED NORTH RIVER INTERCEPTOR | 2 | CONSTRUCTION TO 25% | 2022-11-23 | 2023-07-20 | 2022-11-23 | 2023-07-20
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-348 | REHABILITATION OF DAMAGED NORTH RIVER INTERCEPTOR | 3 | CONSTRUCTION TO 50% | 2023-07-21 | 2024-03-16 | 2023-07-21 | 2024-03-16
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-348 | REHABILITATION OF DAMAGED NORTH RIVER INTERCEPTOR | 4 | CONSTRUCTION TO 75% | 2024-03-17 | 2024-11-11 | 2024-03-17 | 2024-11-11
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDNR | STORM MITIGATION WORK ATTHE NORTH RIVER WPCP | 1 | DEVELOP SCOPE | 2014-06-01 | 2015-02-25 | 2014-06-30 | 2015-03-26
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDNR | STORM MITIGATION WORK ATTHE NORTH RIVER WPCP | 2 | PRELIMINARY DESIGN | 2015-02-26 | 2016-02-20 | 2015-03-27 | 2016-03-20
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDNR | STORM MITIGATION WORK ATTHE NORTH RIVER WPCP | 3 | FINAL DESIGN | 2016-02-21 | 2017-08-13 | 2016-03-21 | 2017-09-11
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDNR | STORM MITIGATION WORK ATTHE NORTH RIVER WPCP | 4 | BID AWARD AND REGISTER CONTRCT | 2017-08-14 | 2018-05-10 | 2017-09-12 | 2018-06-08
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDNR | STORM MITIGATION WORK ATTHE NORTH RIVER WPCP | 5 | CONSTRUCTION TO 25% | 2018-05-11 | 2019-05-05 | 2018-06-09 | 2019-06-03
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDNR | STORM MITIGATION WORK ATTHE NORTH RIVER WPCP | 6 | CONSTRUCTION TO 50% | 2019-05-06 | 2020-04-29 | 2019-06-04 | 2020-05-28
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDNR | STORM MITIGATION WORK ATTHE NORTH RIVER WPCP | 7 | CONSTRUCTION TO 75% | 2020-04-30 | 2021-04-24 | 2020-05-29 | 2021-05-23
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDNR | STORM MITIGATION WORK ATTHE NORTH RIVER WPCP | 8 | ORIGINAL EQUIP & FURNISHING | 2021-04-25 | 2022-01-19 | 2021-05-24 | 2022-02-17
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDNR | STORM MITIGATION WORK ATTHE NORTH RIVER WPCP | 9 | SUBSTANTIAL COMPLETION | 2022-01-20 | 2022-07-18 | 2022-02-18 | 2030-08-14
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDNR | STORM MITIGATION WORK ATTHE NORTH RIVER WPCP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-07-19 | 2022-10-16 | 2030-08-15 | 2030-11-12
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEN002180 | Replcmt of combined sewers & dist WM in West 33 St MH | 1 | DEVELOP SCOPE | 2020-11-09 | 2021-02-06 | 2020-11-09 | 2021-02-06
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEN002180 | Replcmt of combined sewers & dist WM in West 33 St MH | 2 | PRELIMINARY DESIGN | 2021-02-07 | 2021-06-06 | 2021-02-07 | 2021-06-06
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEN002180 | Replcmt of combined sewers & dist WM in West 33 St MH | 3 | FINAL DESIGN | 2021-06-07 | 2021-12-03 | 2021-06-07 | 2021-12-03
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEN002180 | Replcmt of combined sewers & dist WM in West 33 St MH | 4 | BID AWARD AND REGISTER CONTRCT | 2021-12-04 | 2022-03-03 | 2021-12-04 | 2022-03-03
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEN002180 | Replcmt of combined sewers & dist WM in West 33 St MH | 5 | CONSTRUCTION TO 25% | 2022-03-04 | 2022-07-01 | 2022-03-04 | 2022-07-01
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEN002180 | Replcmt of combined sewers & dist WM in West 33 St MH | 6 | CONSTRUCTION TO 50% | 2022-07-02 | 2022-10-29 | 2022-07-02 | 2022-10-29
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEN002180 | Replcmt of combined sewers & dist WM in West 33 St MH | 7 | CONSTRUCTION TO 75% | 2022-10-30 | 2023-02-26 | 2022-10-30 | 2023-02-26
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEN002180 | Replcmt of combined sewers & dist WM in West 33 St MH | 8 | ORIGINAL EQUIP & FURNISHING | 2023-02-27 | 2023-05-27 | 2023-02-27 | 2023-05-27
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEN002180 | Replcmt of combined sewers & dist WM in West 33 St MH | 9 | SUBSTANTIAL COMPLETION | 2023-05-28 | 2023-07-26 | 2023-05-28 | 2023-07-26
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEN002180 | Replcmt of combined sewers & dist WM in West 33 St MH | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-07-27 | 2023-08-25 | 2023-07-27 | 2023-08-25
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | SHAFT21 | RECONSTRUCTION OF SHAFT 21, MANHATTAN, Cont., 602 | 1 | DEVELOP SCOPE | 2002-06-15 | 2002-10-12 | 2002-06-15 | 2002-10-12
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | SHAFT21 | RECONSTRUCTION OF SHAFT 21, MANHATTAN, Cont., 602 | 2 | PRELIMINARY DESIGN | 2002-10-13 | 2003-04-10 | 2002-10-13 | 2003-04-10
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | SHAFT21 | RECONSTRUCTION OF SHAFT 21, MANHATTAN, Cont., 602 | 3 | FINAL DESIGN | 2003-04-11 | 2004-10-11 | 2003-04-11 | 2004-10-11
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | SHAFT21 | RECONSTRUCTION OF SHAFT 21, MANHATTAN, Cont., 602 | 4 | BID AWARD AND REGISTER CONTRCT | 2004-10-12 | 2005-04-09 | 2004-10-12 | 2005-04-09
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | SHAFT21 | RECONSTRUCTION OF SHAFT 21, MANHATTAN, Cont., 602 | 5 | CONSTRUCTION TO 25% | 2005-04-10 | 2006-01-14 | 2005-04-10 | 2006-01-14
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | SHAFT21 | RECONSTRUCTION OF SHAFT 21, MANHATTAN, Cont., 602 | 6 | CONSTRUCTION TO 50% | 2006-01-15 | 2006-10-21 | 2006-01-15 | 2006-10-21
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | SHAFT21 | RECONSTRUCTION OF SHAFT 21, MANHATTAN, Cont., 602 | 7 | CONSTRUCTION TO 75% | 2006-10-22 | 2007-07-28 | 2006-10-22 | 2007-07-28
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | SHAFT21 | RECONSTRUCTION OF SHAFT 21, MANHATTAN, Cont., 602 | 8 | ORIGINAL EQUIP & FURNISHING | 2007-07-29 | 2007-10-26 | 2007-07-29 | 2007-10-26
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | SHAFT21 | RECONSTRUCTION OF SHAFT 21, MANHATTAN, Cont., 602 | 9 | SUBSTANTIAL COMPLETION | 2007-10-27 | 2007-12-25 | 2023-10-27 | 2023-12-25
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | SHAFT21 | RECONSTRUCTION OF SHAFT 21, MANHATTAN, Cont., 602 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2007-12-26 | 2008-03-24 | 2023-12-26 | 2024-03-24
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WFF-CPR | WATER EFICIENCY UPGRADES AT CENTRAL PARK RECIRCULATION | 1 | DEVELOP SCOPE | 2020-06-15 | 2020-10-12 | 2020-06-15 | 2020-10-12
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WFF-CPR | WATER EFICIENCY UPGRADES AT CENTRAL PARK RECIRCULATION | 2 | PRELIMINARY DESIGN | 2020-10-13 | 2021-04-10 | 2020-10-13 | 2021-04-10
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WFF-CPR | WATER EFICIENCY UPGRADES AT CENTRAL PARK RECIRCULATION | 3 | FINAL DESIGN | 2021-04-11 | 2022-10-12 | 2021-04-11 | 2022-10-12
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WFF-CPR | WATER EFICIENCY UPGRADES AT CENTRAL PARK RECIRCULATION | 4 | BID AWARD AND REGISTER CONTRCT | 2022-10-13 | 2023-04-10 | 2022-10-13 | 2023-04-10
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WFF-CPR | WATER EFICIENCY UPGRADES AT CENTRAL PARK RECIRCULATION | 5 | CONSTRUCTION TO 25% | 2023-04-11 | 2024-01-15 | 2023-04-11 | 2024-01-15
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WFF-CPR | WATER EFICIENCY UPGRADES AT CENTRAL PARK RECIRCULATION | 6 | CONSTRUCTION TO 50% | 2024-01-16 | 2024-10-21 | 2024-01-16 | 2024-10-21
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WFF-CPR | WATER EFICIENCY UPGRADES AT CENTRAL PARK RECIRCULATION | 7 | CONSTRUCTION TO 75% | 2024-10-22 | 2025-07-28 | 2024-10-22 | 2025-07-28
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WFF-CPR | WATER EFICIENCY UPGRADES AT CENTRAL PARK RECIRCULATION | 8 | ORIGINAL EQUIP & FURNISHING | 2025-07-29 | 2025-10-26 | 2025-07-29 | 2025-10-26
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WFF-CPR | WATER EFICIENCY UPGRADES AT CENTRAL PARK RECIRCULATION | 9 | SUBSTANTIAL COMPLETION | 2025-10-27 | 2025-12-25 | 2025-10-27 | 2025-12-25
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WFF-CPR | WATER EFICIENCY UPGRADES AT CENTRAL PARK RECIRCULATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-12-26 | 2026-03-25 | 2025-12-26 | 2026-03-25
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-279-L | INSTALLATION OF EMERGENCY GENERATORS AT WARDS ISAND WPCP | 1 | DEVELOP SCOPE | 2016-06-01 | 2017-02-25 | 2016-06-01 | 2017-02-25
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-279-L | INSTALLATION OF EMERGENCY GENERATORS AT WARDS ISAND WPCP | 2 | PRELIMINARY DESIGN | 2017-02-26 | 2018-02-20 | 2017-02-26 | 2018-02-20
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-279-L | INSTALLATION OF EMERGENCY GENERATORS AT WARDS ISAND WPCP | 3 | FINAL DESIGN | 2018-02-21 | 2019-08-14 | 2018-02-21 | 2019-08-14
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-279-L | INSTALLATION OF EMERGENCY GENERATORS AT WARDS ISAND WPCP | 4 | BID AWARD AND REGISTER CONTRCT | 2019-08-15 | 2020-05-10 | 2019-08-15 | 2020-05-10
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-279-L | INSTALLATION OF EMERGENCY GENERATORS AT WARDS ISAND WPCP | 5 | CONSTRUCTION TO 25% | 2020-05-11 | 2021-05-05 | 2020-05-11 | 2021-05-05
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-279-L | INSTALLATION OF EMERGENCY GENERATORS AT WARDS ISAND WPCP | 6 | CONSTRUCTION TO 50% | 2021-05-06 | 2022-04-30 | 2021-05-06 | 2022-04-30
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-279-L | INSTALLATION OF EMERGENCY GENERATORS AT WARDS ISAND WPCP | 7 | CONSTRUCTION TO 75% | 2022-05-01 | 2023-04-25 | 2022-05-01 | 2023-04-25
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-279-L | INSTALLATION OF EMERGENCY GENERATORS AT WARDS ISAND WPCP | 8 | ORIGINAL EQUIP & FURNISHING | 2023-04-26 | 2024-01-20 | 2023-04-26 | 2024-01-20
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-279-L | INSTALLATION OF EMERGENCY GENERATORS AT WARDS ISAND WPCP | 9 | SUBSTANTIAL COMPLETION | 2024-01-21 | 2024-07-18 | 2024-01-21 | 2024-07-18
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-279-L | INSTALLATION OF EMERGENCY GENERATORS AT WARDS ISAND WPCP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-07-19 | 2024-10-16 | 2024-07-19 | 2024-10-16
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-280-L | RECONSTRUCTION OF MAN/BR GRIT SCREENS AT WARDS ISLAND WPCP | 1 | DEVELOP SCOPE | 2012-07-18 | 2013-04-13 | 2012-07-18 | 2013-04-13
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-280-L | RECONSTRUCTION OF MAN/BR GRIT SCREENS AT WARDS ISLAND WPCP | 2 | PRELIMINARY DESIGN | 2013-04-14 | 2014-04-08 | 2013-04-14 | 2014-04-08
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-280-L | RECONSTRUCTION OF MAN/BR GRIT SCREENS AT WARDS ISLAND WPCP | 3 | FINAL DESIGN | 2014-04-09 | 2015-09-30 | 2014-04-09 | 2015-09-30
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-280-L | RECONSTRUCTION OF MAN/BR GRIT SCREENS AT WARDS ISLAND WPCP | 4 | BID AWARD AND REGISTER CONTRCT | 2015-10-01 | 2016-06-26 | 2015-10-01 | 2016-06-26
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-280-L | RECONSTRUCTION OF MAN/BR GRIT SCREENS AT WARDS ISLAND WPCP | 5 | CONSTRUCTION TO 25% | 2016-06-27 | 2017-06-21 | 2016-06-27 | 2017-06-21
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-280-L | RECONSTRUCTION OF MAN/BR GRIT SCREENS AT WARDS ISLAND WPCP | 6 | CONSTRUCTION TO 50% | 2017-06-22 | 2018-06-16 | 2017-06-22 | 2018-06-16
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-280-L | RECONSTRUCTION OF MAN/BR GRIT SCREENS AT WARDS ISLAND WPCP | 7 | CONSTRUCTION TO 75% | 2018-06-17 | 2019-06-11 | 2018-06-17 | 2019-06-11
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-280-L | RECONSTRUCTION OF MAN/BR GRIT SCREENS AT WARDS ISLAND WPCP | 8 | ORIGINAL EQUIP & FURNISHING | 2019-06-12 | 2020-03-07 | 2019-06-12 | 2020-03-07
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-280-L | RECONSTRUCTION OF MAN/BR GRIT SCREENS AT WARDS ISLAND WPCP | 9 | SUBSTANTIAL COMPLETION | 2020-03-08 | 2020-09-03 | 2020-03-08 | 2020-09-03
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-280-L | RECONSTRUCTION OF MAN/BR GRIT SCREENS AT WARDS ISLAND WPCP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-04 | 2020-12-02 | 2020-09-04 | 2020-12-02
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-281-L | RECONSTRUCTION OF (39) FINAL TANKS AT WARDS ISLAND | 1 | DEVELOP SCOPE | 2014-12-01 | 2015-08-27 | 2014-12-01 | 2015-08-27
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-281-L | RECONSTRUCTION OF (39) FINAL TANKS AT WARDS ISLAND | 2 | PRELIMINARY DESIGN | 2015-08-28 | 2016-08-21 | 2015-08-28 | 2016-08-21
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-281-L | RECONSTRUCTION OF (39) FINAL TANKS AT WARDS ISLAND | 3 | FINAL DESIGN | 2016-08-22 | 2018-02-12 | 2016-08-22 | 2018-02-12
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-281-L | RECONSTRUCTION OF (39) FINAL TANKS AT WARDS ISLAND | 4 | BID AWARD AND REGISTER CONTRCT | 2018-02-13 | 2018-11-09 | 2018-02-13 | 2018-11-09
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-281-L | RECONSTRUCTION OF (39) FINAL TANKS AT WARDS ISLAND | 5 | CONSTRUCTION TO 25% | 2018-11-10 | 2019-11-04 | 2018-11-10 | 2019-11-04
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-281-L | RECONSTRUCTION OF (39) FINAL TANKS AT WARDS ISLAND | 6 | CONSTRUCTION TO 50% | 2019-11-05 | 2020-10-29 | 2019-11-05 | 2020-10-29
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-281-L | RECONSTRUCTION OF (39) FINAL TANKS AT WARDS ISLAND | 7 | CONSTRUCTION TO 75% | 2020-10-30 | 2021-10-24 | 2020-10-30 | 2021-10-24
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-281-L | RECONSTRUCTION OF (39) FINAL TANKS AT WARDS ISLAND | 8 | ORIGINAL EQUIP & FURNISHING | 2021-10-25 | 2022-07-21 | 2021-10-25 | 2022-07-21
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-281-L | RECONSTRUCTION OF (39) FINAL TANKS AT WARDS ISLAND | 9 | SUBSTANTIAL COMPLETION | 2022-07-22 | 2023-01-17 | 2022-07-22 | 2023-01-17
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-281-L | RECONSTRUCTION OF (39) FINAL TANKS AT WARDS ISLAND | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-01-18 | 2023-04-17 | 2023-01-18 | 2023-04-17
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-284-L | RECONSTRUCTION OF PRIMARY TANKS AT WARDS ISLAND WPCP | 1 | DEVELOP SCOPE | 2015-07-01 | 2016-03-26 | 2015-07-01 | 2016-03-26
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-284-L | RECONSTRUCTION OF PRIMARY TANKS AT WARDS ISLAND WPCP | 2 | PRELIMINARY DESIGN | 2016-03-27 | 2017-03-21 | 2016-03-27 | 2017-03-21
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-284-L | RECONSTRUCTION OF PRIMARY TANKS AT WARDS ISLAND WPCP | 3 | FINAL DESIGN | 2017-03-22 | 2018-09-12 | 2017-03-22 | 2018-09-12
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-284-L | RECONSTRUCTION OF PRIMARY TANKS AT WARDS ISLAND WPCP | 4 | BID AWARD AND REGISTER CONTRCT | 2018-09-13 | 2019-06-09 | 2018-09-13 | 2019-06-09
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-284-L | RECONSTRUCTION OF PRIMARY TANKS AT WARDS ISLAND WPCP | 5 | CONSTRUCTION TO 25% | 2019-06-10 | 2020-06-03 | 2019-06-10 | 2020-06-03
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-284-L | RECONSTRUCTION OF PRIMARY TANKS AT WARDS ISLAND WPCP | 6 | CONSTRUCTION TO 50% | 2020-06-04 | 2021-05-29 | 2020-06-04 | 2021-05-29
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-284-L | RECONSTRUCTION OF PRIMARY TANKS AT WARDS ISLAND WPCP | 7 | CONSTRUCTION TO 75% | 2021-05-30 | 2022-05-24 | 2021-05-30 | 2022-05-24
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-284-L | RECONSTRUCTION OF PRIMARY TANKS AT WARDS ISLAND WPCP | 8 | ORIGINAL EQUIP & FURNISHING | 2022-05-25 | 2023-02-18 | 2022-05-25 | 2023-02-18
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-284-L | RECONSTRUCTION OF PRIMARY TANKS AT WARDS ISLAND WPCP | 9 | SUBSTANTIAL COMPLETION | 2023-02-19 | 2023-08-17 | 2023-02-19 | 2023-08-17
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-284-L | RECONSTRUCTION OF PRIMARY TANKS AT WARDS ISLAND WPCP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-08-18 | 2023-11-15 | 2023-08-18 | 2023-11-15
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-292-L | RECONSTRUCTION OF POWER DISTRIBUTION @ THE WARDS ISLAND WWTP | 1 | DEVELOP SCOPE | 2017-06-01 | 2017-08-29 | 2017-06-01 | 2018-02-25
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-292-L | RECONSTRUCTION OF POWER DISTRIBUTION @ THE WARDS ISLAND WWTP | 2 | PRELIMINARY DESIGN | 2017-08-30 | 2017-12-27 | 2018-02-26 | 2019-02-20
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-292-L | RECONSTRUCTION OF POWER DISTRIBUTION @ THE WARDS ISLAND WWTP | 3 | FINAL DESIGN | 2017-12-28 | 2018-06-25 | 2019-02-21 | 2020-08-13
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-292-L | RECONSTRUCTION OF POWER DISTRIBUTION @ THE WARDS ISLAND WWTP | 4 | BID AWARD AND REGISTER CONTRCT | 2018-06-26 | 2018-09-23 | 2020-08-14 | 2021-05-10
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-292-L | RECONSTRUCTION OF POWER DISTRIBUTION @ THE WARDS ISLAND WWTP | 5 | CONSTRUCTION TO 25% | 2018-09-24 | 2019-01-21 | 2021-05-11 | 2022-05-05
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-292-L | RECONSTRUCTION OF POWER DISTRIBUTION @ THE WARDS ISLAND WWTP | 6 | CONSTRUCTION TO 50% | 2019-01-22 | 2019-05-21 | 2022-05-06 | 2023-04-30
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-292-L | RECONSTRUCTION OF POWER DISTRIBUTION @ THE WARDS ISLAND WWTP | 7 | CONSTRUCTION TO 75% | 2019-05-22 | 2019-09-18 | 2023-05-01 | 2024-04-24
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-292-L | RECONSTRUCTION OF POWER DISTRIBUTION @ THE WARDS ISLAND WWTP | 8 | ORIGINAL EQUIP & FURNISHING | 2019-09-19 | 2019-12-17 | 2024-04-25 | 2025-01-19
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-292-L | RECONSTRUCTION OF POWER DISTRIBUTION @ THE WARDS ISLAND WWTP | 9 | SUBSTANTIAL COMPLETION | 2019-12-18 | 2020-02-15 | 2025-01-20 | 2033-07-16
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-292-L | RECONSTRUCTION OF POWER DISTRIBUTION @ THE WARDS ISLAND WWTP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-02-16 | 2020-03-16 | 2033-07-17 | 2033-10-14
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-298-B | CONSULTANT DESIGN FOR CONVERSION OF SHARON DEMO @ WARDS ISL | 1 | DEVELOP SCOPE | 2015-06-30 | 2016-03-25 | 2015-06-30 | 2016-03-25
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-298-B | CONSULTANT DESIGN FOR CONVERSION OF SHARON DEMO @ WARDS ISL | 2 | PRELIMINARY DESIGN | 2016-03-26 | 2017-03-20 | 2016-03-26 | 2017-03-20
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-298-B | CONSULTANT DESIGN FOR CONVERSION OF SHARON DEMO @ WARDS ISL | 3 | FINAL DESIGN | 2017-03-21 | 2018-09-11 | 2017-03-21 | 2018-09-11
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-298-B | CONSULTANT DESIGN FOR CONVERSION OF SHARON DEMO @ WARDS ISL | 4 | BID AWARD AND REGISTER CONTRCT | 2018-09-12 | 2019-06-08 | 2018-09-12 | 2019-06-08
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-298-B | CONSULTANT DESIGN FOR CONVERSION OF SHARON DEMO @ WARDS ISL | 5 | CONSTRUCTION TO 25% | 2019-06-09 | 2020-06-02 | 2019-06-09 | 2020-06-02
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-298-B | CONSULTANT DESIGN FOR CONVERSION OF SHARON DEMO @ WARDS ISL | 6 | CONSTRUCTION TO 50% | 2020-06-03 | 2021-05-28 | 2020-06-03 | 2021-05-28
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-298-B | CONSULTANT DESIGN FOR CONVERSION OF SHARON DEMO @ WARDS ISL | 7 | CONSTRUCTION TO 75% | 2021-05-29 | 2022-05-23 | 2021-05-29 | 2022-05-23
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-298-B | CONSULTANT DESIGN FOR CONVERSION OF SHARON DEMO @ WARDS ISL | 8 | ORIGINAL EQUIP & FURNISHING | 2022-05-24 | 2023-02-17 | 2022-05-24 | 2023-02-17
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-298-B | CONSULTANT DESIGN FOR CONVERSION OF SHARON DEMO @ WARDS ISL | 9 | SUBSTANTIAL COMPLETION | 2023-02-18 | 2023-08-16 | 2023-02-18 | 2023-08-16
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-298-B | CONSULTANT DESIGN FOR CONVERSION OF SHARON DEMO @ WARDS ISL | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-08-17 | 2023-11-14 | 2023-08-17 | 2023-11-14
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-305 | RECONSTRUCTION OF FENDER @ WARDS ISLAND WPCP | 1 | FINAL DESIGN | 2022-06-01 | 2023-11-22 | 2027-06-01 | 2028-11-21
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-305 | RECONSTRUCTION OF FENDER @ WARDS ISLAND WPCP | 2 | CONSTRUCTION TO 25% | 2023-11-23 | 2024-07-19 | 2028-11-22 | 2029-07-19
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-305 | RECONSTRUCTION OF FENDER @ WARDS ISLAND WPCP | 3 | CONSTRUCTION TO 50% | 2024-07-20 | 2025-03-16 | 2029-07-20 | 2030-03-16
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-305 | RECONSTRUCTION OF FENDER @ WARDS ISLAND WPCP | 4 | CONSTRUCTION TO 75% | 2025-03-17 | 2025-11-11 | 2030-03-17 | 2030-11-11
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-307-L | RECONSTRUCTION OF SLUDGE FEED LINES @ WARDS ISLAND WWTP | 1 | FINAL DESIGN | 2018-08-01 | 2020-01-22 | 2018-08-01 | 2020-01-22
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-307-L | RECONSTRUCTION OF SLUDGE FEED LINES @ WARDS ISLAND WWTP | 2 | CONSTRUCTION TO 25% | 2020-01-23 | 2020-09-18 | 2020-01-23 | 2020-09-18
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-307-L | RECONSTRUCTION OF SLUDGE FEED LINES @ WARDS ISLAND WWTP | 3 | CONSTRUCTION TO 50% | 2020-09-19 | 2021-05-16 | 2020-09-19 | 2021-05-16
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-307-L | RECONSTRUCTION OF SLUDGE FEED LINES @ WARDS ISLAND WWTP | 4 | CONSTRUCTION TO 75% | 2021-05-17 | 2022-01-11 | 2021-05-17 | 2022-01-11
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-308-L | INSTALLATION OF CITY WATER LINES @ WARDS ISLAND WWTP | 1 | DEVELOP SCOPE | 2019-11-01 | 2020-01-29 | 2019-11-01 | 2020-01-29
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-308-L | INSTALLATION OF CITY WATER LINES @ WARDS ISLAND WWTP | 2 | PRELIMINARY DESIGN | 2020-01-30 | 2020-05-28 | 2020-01-30 | 2020-05-28
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-308-L | INSTALLATION OF CITY WATER LINES @ WARDS ISLAND WWTP | 3 | FINAL DESIGN | 2020-05-29 | 2020-11-24 | 2020-05-29 | 2020-11-24
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-308-L | INSTALLATION OF CITY WATER LINES @ WARDS ISLAND WWTP | 4 | BID AWARD AND REGISTER CONTRCT | 2020-11-25 | 2021-02-22 | 2020-11-25 | 2021-02-22
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-308-L | INSTALLATION OF CITY WATER LINES @ WARDS ISLAND WWTP | 5 | CONSTRUCTION TO 25% | 2021-02-23 | 2021-06-22 | 2021-02-23 | 2021-06-22
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-308-L | INSTALLATION OF CITY WATER LINES @ WARDS ISLAND WWTP | 6 | CONSTRUCTION TO 50% | 2021-06-23 | 2021-10-20 | 2021-06-23 | 2021-10-20
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-308-L | INSTALLATION OF CITY WATER LINES @ WARDS ISLAND WWTP | 7 | CONSTRUCTION TO 75% | 2021-10-21 | 2022-02-17 | 2021-10-21 | 2022-02-17
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-308-L | INSTALLATION OF CITY WATER LINES @ WARDS ISLAND WWTP | 8 | ORIGINAL EQUIP & FURNISHING | 2022-02-18 | 2022-05-18 | 2022-02-18 | 2022-05-18
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-308-L | INSTALLATION OF CITY WATER LINES @ WARDS ISLAND WWTP | 9 | SUBSTANTIAL COMPLETION | 2022-05-19 | 2022-07-17 | 2022-05-19 | 2022-07-17
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-308-L | INSTALLATION OF CITY WATER LINES @ WARDS ISLAND WWTP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-07-18 | 2022-08-16 | 2022-07-18 | 2022-08-16
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-309-L | RECONSTRUCTION OF NEW ADMINISTRATION BLDG @ WARDS ISLAND | 1 | DEVELOP SCOPE | 2022-11-01 | 2023-01-29 | 2027-06-01 | 2027-08-29
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-309-L | RECONSTRUCTION OF NEW ADMINISTRATION BLDG @ WARDS ISLAND | 2 | PRELIMINARY DESIGN | 2023-01-30 | 2023-05-29 | 2027-08-30 | 2027-12-27
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-309-L | RECONSTRUCTION OF NEW ADMINISTRATION BLDG @ WARDS ISLAND | 3 | FINAL DESIGN | 2023-05-30 | 2023-11-25 | 2027-12-28 | 2028-06-24
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-309-L | RECONSTRUCTION OF NEW ADMINISTRATION BLDG @ WARDS ISLAND | 4 | BID AWARD AND REGISTER CONTRCT | 2023-11-26 | 2024-02-23 | 2028-06-25 | 2028-09-22
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-309-L | RECONSTRUCTION OF NEW ADMINISTRATION BLDG @ WARDS ISLAND | 5 | CONSTRUCTION TO 25% | 2024-02-24 | 2024-06-22 | 2028-09-23 | 2029-01-20
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-309-L | RECONSTRUCTION OF NEW ADMINISTRATION BLDG @ WARDS ISLAND | 6 | CONSTRUCTION TO 50% | 2024-06-23 | 2024-10-20 | 2029-01-21 | 2029-05-20
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-309-L | RECONSTRUCTION OF NEW ADMINISTRATION BLDG @ WARDS ISLAND | 7 | CONSTRUCTION TO 75% | 2024-10-21 | 2025-02-17 | 2029-05-21 | 2029-09-17
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-309-L | RECONSTRUCTION OF NEW ADMINISTRATION BLDG @ WARDS ISLAND | 8 | ORIGINAL EQUIP & FURNISHING | 2025-02-18 | 2025-05-18 | 2029-09-18 | 2029-12-16
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-309-L | RECONSTRUCTION OF NEW ADMINISTRATION BLDG @ WARDS ISLAND | 9 | SUBSTANTIAL COMPLETION | 2025-05-19 | 2025-07-17 | 2029-12-17 | 2030-02-14
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-309-L | RECONSTRUCTION OF NEW ADMINISTRATION BLDG @ WARDS ISLAND | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-07-18 | 2025-08-16 | 2030-02-15 | 2030-03-16
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-311-L | REHAB DIGAS LEAKS AT WARDS ISLAND WPCP | 1 | DEVELOP SCOPE | 2019-11-01 | 2020-01-29 | 2019-11-01 | 2020-01-29
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-311-L | REHAB DIGAS LEAKS AT WARDS ISLAND WPCP | 2 | PRELIMINARY DESIGN | 2020-01-30 | 2020-05-28 | 2020-01-30 | 2020-05-28
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-311-L | REHAB DIGAS LEAKS AT WARDS ISLAND WPCP | 3 | FINAL DESIGN | 2020-05-29 | 2020-11-24 | 2020-05-29 | 2020-11-24
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-311-L | REHAB DIGAS LEAKS AT WARDS ISLAND WPCP | 4 | BID AWARD AND REGISTER CONTRCT | 2020-11-25 | 2021-02-22 | 2020-11-25 | 2021-02-22
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-311-L | REHAB DIGAS LEAKS AT WARDS ISLAND WPCP | 5 | CONSTRUCTION TO 25% | 2021-02-23 | 2021-06-22 | 2021-02-23 | 2021-06-22
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-311-L | REHAB DIGAS LEAKS AT WARDS ISLAND WPCP | 6 | CONSTRUCTION TO 50% | 2021-06-23 | 2021-10-20 | 2021-06-23 | 2021-10-20
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-311-L | REHAB DIGAS LEAKS AT WARDS ISLAND WPCP | 7 | CONSTRUCTION TO 75% | 2021-10-21 | 2022-02-17 | 2021-10-21 | 2022-02-17
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-311-L | REHAB DIGAS LEAKS AT WARDS ISLAND WPCP | 8 | ORIGINAL EQUIP & FURNISHING | 2022-02-18 | 2022-05-18 | 2022-02-18 | 2022-05-18
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-311-L | REHAB DIGAS LEAKS AT WARDS ISLAND WPCP | 9 | SUBSTANTIAL COMPLETION | 2022-05-19 | 2022-07-17 | 2022-05-19 | 2022-07-17
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-311-L | REHAB DIGAS LEAKS AT WARDS ISLAND WPCP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-07-18 | 2022-08-16 | 2022-07-18 | 2022-08-16
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-312-L | CONSTRUC STORM DRAINS AROUND DIGESTER COMPLEX TO PLANT DRAIN | 1 | DEVELOP SCOPE | 2022-11-01 | 2023-01-29 | 2022-04-01 | 2022-06-29
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-312-L | CONSTRUC STORM DRAINS AROUND DIGESTER COMPLEX TO PLANT DRAIN | 2 | PRELIMINARY DESIGN | 2023-01-30 | 2023-05-29 | 2022-06-30 | 2022-10-27
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-312-L | CONSTRUC STORM DRAINS AROUND DIGESTER COMPLEX TO PLANT DRAIN | 3 | FINAL DESIGN | 2023-05-30 | 2023-11-25 | 2022-10-28 | 2023-04-25
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-312-L | CONSTRUC STORM DRAINS AROUND DIGESTER COMPLEX TO PLANT DRAIN | 4 | BID AWARD AND REGISTER CONTRCT | 2023-11-26 | 2024-02-23 | 2023-04-26 | 2023-07-24
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-312-L | CONSTRUC STORM DRAINS AROUND DIGESTER COMPLEX TO PLANT DRAIN | 5 | CONSTRUCTION TO 25% | 2024-02-24 | 2024-06-22 | 2023-07-25 | 2023-11-21
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-312-L | CONSTRUC STORM DRAINS AROUND DIGESTER COMPLEX TO PLANT DRAIN | 6 | CONSTRUCTION TO 50% | 2024-06-23 | 2024-10-20 | 2023-11-22 | 2024-03-20
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-312-L | CONSTRUC STORM DRAINS AROUND DIGESTER COMPLEX TO PLANT DRAIN | 7 | CONSTRUCTION TO 75% | 2024-10-21 | 2025-02-17 | 2024-03-21 | 2024-07-18
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-312-L | CONSTRUC STORM DRAINS AROUND DIGESTER COMPLEX TO PLANT DRAIN | 8 | ORIGINAL EQUIP & FURNISHING | 2025-02-18 | 2025-05-18 | 2024-07-19 | 2024-10-16
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-312-L | CONSTRUC STORM DRAINS AROUND DIGESTER COMPLEX TO PLANT DRAIN | 9 | SUBSTANTIAL COMPLETION | 2025-05-19 | 2025-07-17 | 2024-10-17 | 2024-12-15
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-312-L | CONSTRUC STORM DRAINS AROUND DIGESTER COMPLEX TO PLANT DRAIN | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-07-18 | 2025-08-16 | 2024-12-16 | 2025-01-14
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-318-L | RECONSTRUCT TWO MAIN SEWAGE PUMP RESISTOR BANKS @ WARDS ISL | 1 | FINAL DESIGN | 2021-06-01 | 2022-11-22 | 2021-06-01 | 2022-11-22
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-318-L | RECONSTRUCT TWO MAIN SEWAGE PUMP RESISTOR BANKS @ WARDS ISL | 2 | CONSTRUCTION TO 25% | 2022-11-23 | 2023-07-20 | 2022-11-23 | 2023-07-20
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-318-L | RECONSTRUCT TWO MAIN SEWAGE PUMP RESISTOR BANKS @ WARDS ISL | 3 | CONSTRUCTION TO 50% | 2023-07-21 | 2024-03-16 | 2023-07-21 | 2024-03-16
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-318-L | RECONSTRUCT TWO MAIN SEWAGE PUMP RESISTOR BANKS @ WARDS ISL | 4 | CONSTRUCTION TO 75% | 2024-03-17 | 2024-11-11 | 2024-03-17 | 2024-11-11
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-323-L | UPGRADE MSP CC VALVE,ACTUATORS,DISCHARGE PIP REPL @ WI WRRF | 1 | FINAL DESIGN | 2022-06-01 | 2023-11-22 | 2022-06-01 | 2023-11-22
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-323-L | UPGRADE MSP CC VALVE,ACTUATORS,DISCHARGE PIP REPL @ WI WRRF | 2 | CONSTRUCTION TO 25% | 2023-11-23 | 2024-07-19 | 2023-11-23 | 2024-07-19
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-323-L | UPGRADE MSP CC VALVE,ACTUATORS,DISCHARGE PIP REPL @ WI WRRF | 3 | CONSTRUCTION TO 50% | 2024-07-20 | 2025-03-16 | 2024-07-20 | 2025-03-16
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-323-L | UPGRADE MSP CC VALVE,ACTUATORS,DISCHARGE PIP REPL @ WI WRRF | 4 | CONSTRUCTION TO 75% | 2025-03-17 | 2025-11-11 | 2025-03-17 | 2025-11-11
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-EXP | INTERIM FAC & UPGRADING AT WARDS ISLAND WPCP | 1 | DEVELOP SCOPE | 1993-06-03 | 1993-08-31 | 2000-02-18 | 2000-11-13
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-EXP | INTERIM FAC & UPGRADING AT WARDS ISLAND WPCP | 2 | PRELIMINARY DESIGN | 1993-09-01 | 1993-12-29 | 2000-11-14 | 2001-11-08
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-EXP | INTERIM FAC & UPGRADING AT WARDS ISLAND WPCP | 3 | FINAL DESIGN | 1993-12-30 | 1994-06-27 | 2001-11-09 | 2003-05-02
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-EXP | INTERIM FAC & UPGRADING AT WARDS ISLAND WPCP | 4 | BID AWARD AND REGISTER CONTRCT | 1994-06-28 | 1994-09-25 | 2003-05-03 | 2004-01-27
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-EXP | INTERIM FAC & UPGRADING AT WARDS ISLAND WPCP | 5 | CONSTRUCTION TO 25% | 1994-09-26 | 1995-01-23 | 2004-01-28 | 2005-01-21
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-EXP | INTERIM FAC & UPGRADING AT WARDS ISLAND WPCP | 6 | CONSTRUCTION TO 50% | 1995-01-24 | 1995-05-23 | 2005-01-22 | 2006-01-16
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-EXP | INTERIM FAC & UPGRADING AT WARDS ISLAND WPCP | 7 | CONSTRUCTION TO 75% | 1995-05-24 | 1995-09-20 | 2006-01-17 | 2007-01-11
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-EXP | INTERIM FAC & UPGRADING AT WARDS ISLAND WPCP | 8 | ORIGINAL EQUIP & FURNISHING | 1995-09-21 | 1995-12-19 | 2007-01-12 | 2007-10-08
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-EXP | INTERIM FAC & UPGRADING AT WARDS ISLAND WPCP | 9 | SUBSTANTIAL COMPLETION | 1995-12-20 | 1996-02-17 | 2007-10-09 | 2020-04-02
20201123 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-EXP | INTERIM FAC & UPGRADING AT WARDS ISLAND WPCP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 1996-02-18 | 1996-03-18 | 2020-04-03 | 2020-07-01
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | P-300HRP2 | HUDSON RIVER PARK - Gansevoort MOU | 1 | DEVELOP SCOPE | 2014-07-01 | 2014-09-28 | 2014-07-01 | 2014-09-28
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | P-300HRP2 | HUDSON RIVER PARK - Gansevoort MOU | 2 | PRELIMINARY DESIGN | 2014-09-29 | 2014-12-27 | 2014-09-29 | 2014-12-27
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | P-300HRP2 | HUDSON RIVER PARK - Gansevoort MOU | 3 | FINAL DESIGN | 2014-12-28 | 2015-03-27 | 2014-12-28 | 2015-03-27
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | P-300HRP2 | HUDSON RIVER PARK - Gansevoort MOU | 4 | BID AWARD AND REGISTER CONTRCT | 2015-03-28 | 2015-06-30 | 2015-03-28 | 2015-06-30
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | P-300HRP2 | HUDSON RIVER PARK - Gansevoort MOU | 5 | CONSTRUCTION TO 25% | 2015-07-01 | 2015-12-31 | 2015-07-01 | 2015-12-31
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | P-300HRP2 | HUDSON RIVER PARK - Gansevoort MOU | 6 | CONSTRUCTION TO 50% | 2016-01-01 | 2016-06-30 | 2016-01-01 | 2016-06-30
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | P-300HRP2 | HUDSON RIVER PARK - Gansevoort MOU | 7 | CONSTRUCTION TO 75% | 2016-07-01 | 2016-12-31 | 2016-07-01 | 2024-09-16
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | P-300HRP2 | HUDSON RIVER PARK - Gansevoort MOU | 8 | ORIGINAL EQUIP & FURNISHING | 2017-01-01 | 2017-01-01 | 2024-09-17 | 2025-09-16
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | P-300HRP2 | HUDSON RIVER PARK - Gansevoort MOU | 9 | SUBSTANTIAL COMPLETION | 2017-01-01 | 2017-06-30 | 2025-09-17 | 2028-06-12
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | P-300HRP2 | HUDSON RIVER PARK - Gansevoort MOU | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-07-01 | 2018-06-30 | 2028-06-13 | 2029-06-12
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-264M | Manhattan 26th St Manhattan Borough Shop Roof Replacement | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-09-28 | 2016-07-01 | 2016-09-28
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-264M | Manhattan 26th St Manhattan Borough Shop Roof Replacement | 2 | PRELIMINARY DESIGN | 2016-09-29 | 2017-07-15 | 2016-09-29 | 2017-07-15
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-264M | Manhattan 26th St Manhattan Borough Shop Roof Replacement | 3 | FINAL DESIGN | 2017-07-16 | 2018-05-01 | 2017-07-16 | 2018-05-01
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-264M | Manhattan 26th St Manhattan Borough Shop Roof Replacement | 4 | BID AWARD AND REGISTER CONTRCT | 2018-05-02 | 2019-02-15 | 2018-05-02 | 2019-02-15
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-264M | Manhattan 26th St Manhattan Borough Shop Roof Replacement | 5 | CONSTRUCTION TO 25% | 2019-02-16 | 2020-02-15 | 2019-02-16 | 2020-02-15
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-264M | Manhattan 26th St Manhattan Borough Shop Roof Replacement | 6 | CONSTRUCTION TO 50% | 2020-02-16 | 2021-02-14 | 2020-02-16 | 2021-02-14
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-264M | Manhattan 26th St Manhattan Borough Shop Roof Replacement | 7 | CONSTRUCTION TO 75% | 2021-02-15 | 2022-02-14 | 2021-02-15 | 2022-02-14
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-264M | Manhattan 26th St Manhattan Borough Shop Roof Replacement | 8 | SUBSTANTIAL COMPLETION | 2022-02-15 | 2024-11-10 | 2022-02-15 | 2024-11-10
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-264M | Manhattan 26th St Manhattan Borough Shop Roof Replacement | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-10-28 | 2025-03-10 | 2023-10-28 | 2025-03-10
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-374R | MANHATTAN 12 HV UNITS & BOILER REPLACEMENT | 1 | DEVELOP SCOPE | 2019-05-01 | 2020-01-05 | 2019-05-01 | 2020-01-05
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-374R | MANHATTAN 12 HV UNITS & BOILER REPLACEMENT | 2 | PRELIMINARY DESIGN | 2020-01-06 | 2020-06-28 | 2020-01-06 | 2020-06-28
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-374R | MANHATTAN 12 HV UNITS & BOILER REPLACEMENT | 3 | FINAL DESIGN | 2020-06-29 | 2020-12-20 | 2020-06-29 | 2020-12-20
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-374R | MANHATTAN 12 HV UNITS & BOILER REPLACEMENT | 4 | BID AWARD AND REGISTER CONTRCT | 2020-12-21 | 2021-06-30 | 2020-12-21 | 2021-06-30
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-374R | MANHATTAN 12 HV UNITS & BOILER REPLACEMENT | 5 | CONSTRUCTION TO 25% | 2021-07-01 | 2021-12-27 | 2021-07-01 | 2021-12-27
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-374R | MANHATTAN 12 HV UNITS & BOILER REPLACEMENT | 6 | CONSTRUCTION TO 50% | 2021-12-28 | 2022-06-25 | 2021-12-28 | 2022-06-25
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-374R | MANHATTAN 12 HV UNITS & BOILER REPLACEMENT | 7 | CONSTRUCTION TO 75% | 2022-06-26 | 2022-12-22 | 2022-06-26 | 2022-12-22
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-374R | MANHATTAN 12 HV UNITS & BOILER REPLACEMENT | 8 | SUBSTANTIAL COMPLETION | 2022-12-23 | 2023-12-22 | 2022-12-23 | 2023-12-22
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-374R | MANHATTAN 12 HV UNITS & BOILER REPLACEMENT | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-12-23 | 2024-04-20 | 2023-12-23 | 2024-04-20
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-380C | Bronx 7/8 Garage Boiler Replacement | 1 | DEVELOP SCOPE | 2018-06-01 | 2018-07-15 | 2018-06-01 | 2018-07-15
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-380C | Bronx 7/8 Garage Boiler Replacement | 2 | PRELIMINARY DESIGN | 2018-07-16 | 2018-09-13 | 2018-07-16 | 2018-09-13
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-380C | Bronx 7/8 Garage Boiler Replacement | 3 | FINAL DESIGN | 2018-09-14 | 2018-11-12 | 2018-09-14 | 2018-11-12
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-380C | Bronx 7/8 Garage Boiler Replacement | 4 | BID AWARD AND REGISTER CONTRCT | 2018-11-13 | 2019-02-10 | 2018-11-13 | 2019-02-10
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-380C | Bronx 7/8 Garage Boiler Replacement | 5 | CONSTRUCTION TO 25% | 2019-02-11 | 2019-12-07 | 2019-02-11 | 2019-12-07
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-380C | Bronx 7/8 Garage Boiler Replacement | 6 | CONSTRUCTION TO 50% | 2019-12-08 | 2020-10-02 | 2019-12-08 | 2020-10-02
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-380C | Bronx 7/8 Garage Boiler Replacement | 7 | CONSTRUCTION TO 75% | 2020-10-03 | 2021-07-29 | 2020-10-03 | 2021-07-29
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-380C | Bronx 7/8 Garage Boiler Replacement | 8 | SUBSTANTIAL COMPLETION | 2021-07-30 | 2021-12-26 | 2021-07-30 | 2021-12-26
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-380C | Bronx 7/8 Garage Boiler Replacement | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-12-27 | 2022-04-25 | 2021-12-27 | 2022-04-25
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-380E | Manhattan 3 Garage HVAC System Rehabilitation | 1 | DEVELOP SCOPE | 2018-09-01 | 2018-10-15 | 2018-09-01 | 2018-10-15
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-380E | Manhattan 3 Garage HVAC System Rehabilitation | 2 | PRELIMINARY DESIGN | 2018-10-16 | 2018-12-14 | 2018-10-16 | 2018-12-14
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-380E | Manhattan 3 Garage HVAC System Rehabilitation | 3 | FINAL DESIGN | 2018-12-15 | 2019-02-12 | 2018-12-15 | 2019-02-12
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-380E | Manhattan 3 Garage HVAC System Rehabilitation | 4 | BID AWARD AND REGISTER CONTRCT | 2019-02-13 | 2019-05-13 | 2019-02-13 | 2019-05-13
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-380E | Manhattan 3 Garage HVAC System Rehabilitation | 5 | CONSTRUCTION TO 25% | 2019-05-14 | 2019-11-09 | 2019-05-14 | 2019-11-09
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-380E | Manhattan 3 Garage HVAC System Rehabilitation | 6 | CONSTRUCTION TO 50% | 2019-11-10 | 2020-05-07 | 2019-11-10 | 2020-05-07
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-380E | Manhattan 3 Garage HVAC System Rehabilitation | 7 | CONSTRUCTION TO 75% | 2020-05-08 | 2020-11-03 | 2020-05-08 | 2020-11-03
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-380E | Manhattan 3 Garage HVAC System Rehabilitation | 8 | SUBSTANTIAL COMPLETION | 2020-11-04 | 2021-05-02 | 2020-11-04 | 2021-05-02
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-380E | Manhattan 3 Garage HVAC System Rehabilitation | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-05-03 | 2021-11-18 | 2021-05-03 | 2021-11-18
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-385E | MANHATTAN 4/4A/7 GARAGE GLASS FACADE REHABILITATION | 1 | DEVELOP SCOPE | 2015-07-01 | 2016-06-29 | 2015-07-01 | 2016-06-29
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-385E | MANHATTAN 4/4A/7 GARAGE GLASS FACADE REHABILITATION | 2 | PRELIMINARY DESIGN | 2016-06-30 | 2017-06-29 | 2016-06-30 | 2017-06-29
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-385E | MANHATTAN 4/4A/7 GARAGE GLASS FACADE REHABILITATION | 3 | FINAL DESIGN | 2017-06-30 | 2018-06-29 | 2017-06-30 | 2018-06-29
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-385E | MANHATTAN 4/4A/7 GARAGE GLASS FACADE REHABILITATION | 4 | BID AWARD AND REGISTER CONTRCT | 2018-06-30 | 2019-06-29 | 2018-06-30 | 2019-06-29
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-385E | MANHATTAN 4/4A/7 GARAGE GLASS FACADE REHABILITATION | 5 | CONSTRUCTION TO 25% | 2019-06-30 | 2020-06-28 | 2019-06-30 | 2020-06-28
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-385E | MANHATTAN 4/4A/7 GARAGE GLASS FACADE REHABILITATION | 6 | CONSTRUCTION TO 50% | 2020-06-29 | 2021-06-28 | 2020-06-29 | 2021-06-28
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-385E | MANHATTAN 4/4A/7 GARAGE GLASS FACADE REHABILITATION | 7 | CONSTRUCTION TO 75% | 2021-06-29 | 2022-06-28 | 2021-06-29 | 2022-06-28
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-385E | MANHATTAN 4/4A/7 GARAGE GLASS FACADE REHABILITATION | 8 | SUBSTANTIAL COMPLETION | 2022-06-29 | 2024-05-28 | 2022-06-29 | 2024-05-28
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-385E | MANHATTAN 4/4A/7 GARAGE GLASS FACADE REHABILITATION | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-05-29 | 2026-04-28 | 2024-05-29 | 2026-04-28
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-430 | Manhattan 4039 9th Ave/W 215th St garage Rehab | 1 | DEVELOP SCOPE | 2018-12-01 | 2019-01-14 | 2018-12-01 | 2019-01-14
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-430 | Manhattan 4039 9th Ave/W 215th St garage Rehab | 2 | PRELIMINARY DESIGN | 2019-01-15 | 2019-03-15 | 2019-01-15 | 2019-03-15
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-430 | Manhattan 4039 9th Ave/W 215th St garage Rehab | 3 | FINAL DESIGN | 2019-03-16 | 2019-06-13 | 2019-03-16 | 2019-06-13
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-430 | Manhattan 4039 9th Ave/W 215th St garage Rehab | 4 | BID AWARD AND REGISTER CONTRCT | 2019-06-14 | 2019-12-10 | 2019-06-14 | 2019-12-10
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-430 | Manhattan 4039 9th Ave/W 215th St garage Rehab | 5 | CONSTRUCTION TO 25% | 2019-12-11 | 2020-06-27 | 2019-12-11 | 2020-06-27
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-430 | Manhattan 4039 9th Ave/W 215th St garage Rehab | 6 | CONSTRUCTION TO 50% | 2020-06-28 | 2021-01-13 | 2020-06-28 | 2021-01-13
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-430 | Manhattan 4039 9th Ave/W 215th St garage Rehab | 7 | CONSTRUCTION TO 75% | 2021-01-14 | 2021-08-01 | 2021-01-14 | 2021-08-01
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-430 | Manhattan 4039 9th Ave/W 215th St garage Rehab | 8 | SUBSTANTIAL COMPLETION | 2021-08-02 | 2022-05-28 | 2021-08-02 | 2022-05-28
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-430 | Manhattan 4039 9th Ave/W 215th St garage Rehab | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-05-29 | 2023-03-24 | 2022-05-29 | 2023-03-24
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-430A | Manhattan 8 Smokestacks Demolition 4039 9th Ave/W 215th St | 1 | DEVELOP SCOPE | 2020-05-01 | 2020-06-14 | 2020-05-01 | 2020-06-14
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-430A | Manhattan 8 Smokestacks Demolition 4039 9th Ave/W 215th St | 2 | PRELIMINARY DESIGN | 2020-06-15 | 2020-08-13 | 2020-06-15 | 2020-08-13
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-430A | Manhattan 8 Smokestacks Demolition 4039 9th Ave/W 215th St | 3 | FINAL DESIGN | 2020-08-14 | 2020-12-11 | 2020-08-14 | 2020-12-11
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-430A | Manhattan 8 Smokestacks Demolition 4039 9th Ave/W 215th St | 4 | BID AWARD AND REGISTER CONTRCT | 2020-12-12 | 2021-03-11 | 2020-12-12 | 2021-03-11
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-430A | Manhattan 8 Smokestacks Demolition 4039 9th Ave/W 215th St | 5 | CONSTRUCTION TO 25% | 2021-03-12 | 2021-06-09 | 2021-03-12 | 2021-06-09
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-430A | Manhattan 8 Smokestacks Demolition 4039 9th Ave/W 215th St | 6 | CONSTRUCTION TO 50% | 2021-06-10 | 2021-09-07 | 2021-06-10 | 2021-09-07
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-430A | Manhattan 8 Smokestacks Demolition 4039 9th Ave/W 215th St | 7 | CONSTRUCTION TO 75% | 2021-09-08 | 2022-01-05 | 2021-09-08 | 2022-01-05
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-430A | Manhattan 8 Smokestacks Demolition 4039 9th Ave/W 215th St | 8 | SUBSTANTIAL COMPLETION | 2022-01-06 | 2022-06-04 | 2022-01-06 | 2022-06-04
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-430A | Manhattan 8 Smokestacks Demolition 4039 9th Ave/W 215th St | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-06-05 | 2023-06-04 | 2022-06-05 | 2023-06-04
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-432 | MANHATTAN 44 BEAVER ST REHABILITATION | 1 | DEVELOP SCOPE | 2016-05-01 | 2016-08-28 | 2016-05-01 | 2016-08-28
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-432 | MANHATTAN 44 BEAVER ST REHABILITATION | 2 | PRELIMINARY DESIGN | 2016-08-29 | 2017-05-15 | 2016-08-29 | 2017-05-15
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-432 | MANHATTAN 44 BEAVER ST REHABILITATION | 3 | FINAL DESIGN | 2017-05-16 | 2018-01-30 | 2017-05-16 | 2018-01-30
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-432 | MANHATTAN 44 BEAVER ST REHABILITATION | 4 | BID AWARD AND REGISTER CONTRCT | 2018-01-31 | 2018-10-17 | 2018-01-31 | 2018-10-17
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-432 | MANHATTAN 44 BEAVER ST REHABILITATION | 5 | CONSTRUCTION TO 25% | 2018-10-18 | 2019-07-04 | 2018-10-18 | 2019-07-04
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-432 | MANHATTAN 44 BEAVER ST REHABILITATION | 6 | CONSTRUCTION TO 50% | 2019-07-05 | 2020-03-20 | 2019-07-05 | 2020-03-20
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-432 | MANHATTAN 44 BEAVER ST REHABILITATION | 7 | CONSTRUCTION TO 75% | 2020-03-21 | 2020-12-05 | 2020-03-21 | 2020-12-05
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-432 | MANHATTAN 44 BEAVER ST REHABILITATION | 8 | SUBSTANTIAL COMPLETION | 2020-12-06 | 2023-09-01 | 2020-12-06 | 2023-09-01
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-432 | MANHATTAN 44 BEAVER ST REHABILITATION | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-04-05 | 2023-12-30 | 2021-04-05 | 2023-12-30
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-435 | Manhattan 11 2496 Second Ave Rehab & Building Addition | 1 | DEVELOP SCOPE | 2015-05-01 | 2016-04-29 | 2015-05-01 | 2016-04-29
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-435 | Manhattan 11 2496 Second Ave Rehab & Building Addition | 2 | PRELIMINARY DESIGN | 2016-04-30 | 2016-10-26 | 2016-04-30 | 2016-10-26
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-435 | Manhattan 11 2496 Second Ave Rehab & Building Addition | 3 | FINAL DESIGN | 2016-10-27 | 2017-04-24 | 2016-10-27 | 2019-06-28
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-435 | Manhattan 11 2496 Second Ave Rehab & Building Addition | 4 | BID AWARD AND REGISTER CONTRCT | 2017-04-25 | 2017-10-21 | 2019-06-29 | 2020-11-30
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-435 | Manhattan 11 2496 Second Ave Rehab & Building Addition | 5 | CONSTRUCTION TO 25% | 2017-10-22 | 2018-04-19 | 2020-12-01 | 2021-05-29
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-435 | Manhattan 11 2496 Second Ave Rehab & Building Addition | 6 | CONSTRUCTION TO 50% | 2018-04-20 | 2018-10-16 | 2021-05-30 | 2021-11-25
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-435 | Manhattan 11 2496 Second Ave Rehab & Building Addition | 7 | CONSTRUCTION TO 75% | 2018-10-17 | 2019-04-14 | 2021-11-26 | 2022-05-24
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-435 | Manhattan 11 2496 Second Ave Rehab & Building Addition | 8 | SUBSTANTIAL COMPLETION | 2019-04-15 | 2019-10-11 | 2022-05-25 | 2022-11-20
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-435 | Manhattan 11 2496 Second Ave Rehab & Building Addition | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-10-12 | 2021-02-22 | 2022-11-21 | 2024-06-30
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-437 | MANHATTAN 44 BEAVER ST SPRINKLER SYSTEM REPLACEMENT | 1 | DEVELOP SCOPE | 2016-05-01 | 2016-06-14 | 2016-05-01 | 2016-06-14
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-437 | MANHATTAN 44 BEAVER ST SPRINKLER SYSTEM REPLACEMENT | 2 | PRELIMINARY DESIGN | 2016-06-15 | 2016-10-12 | 2016-06-15 | 2016-10-12
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-437 | MANHATTAN 44 BEAVER ST SPRINKLER SYSTEM REPLACEMENT | 3 | FINAL DESIGN | 2016-10-13 | 2017-02-09 | 2016-10-13 | 2017-02-09
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-437 | MANHATTAN 44 BEAVER ST SPRINKLER SYSTEM REPLACEMENT | 4 | BID AWARD AND REGISTER CONTRCT | 2017-02-10 | 2018-02-09 | 2017-02-10 | 2018-02-09
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-437 | MANHATTAN 44 BEAVER ST SPRINKLER SYSTEM REPLACEMENT | 5 | CONSTRUCTION TO 25% | 2018-02-10 | 2019-02-09 | 2018-02-10 | 2019-02-09
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-437 | MANHATTAN 44 BEAVER ST SPRINKLER SYSTEM REPLACEMENT | 6 | CONSTRUCTION TO 50% | 2019-02-10 | 2020-02-09 | 2019-02-10 | 2020-02-09
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-437 | MANHATTAN 44 BEAVER ST SPRINKLER SYSTEM REPLACEMENT | 7 | CONSTRUCTION TO 75% | 2020-02-10 | 2021-02-08 | 2020-02-10 | 2021-02-08
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-437 | MANHATTAN 44 BEAVER ST SPRINKLER SYSTEM REPLACEMENT | 8 | SUBSTANTIAL COMPLETION | 2021-02-09 | 2023-04-19 | 2021-02-09 | 2023-04-19
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-437 | MANHATTAN 44 BEAVER ST SPRINKLER SYSTEM REPLACEMENT | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-04-20 | 2025-06-27 | 2023-04-20 | 2025-06-27
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-440B | Bronx 7/8 Garage Slab Replacement | 1 | DEVELOP SCOPE | 2019-08-01 | 2019-09-14 | 2019-08-01 | 2019-09-14
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-440B | Bronx 7/8 Garage Slab Replacement | 2 | PRELIMINARY DESIGN | 2019-09-15 | 2019-12-31 | 2019-09-15 | 2019-12-31
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-440B | Bronx 7/8 Garage Slab Replacement | 3 | FINAL DESIGN | 2020-01-01 | 2020-06-30 | 2020-01-01 | 2020-06-30
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-440B | Bronx 7/8 Garage Slab Replacement | 4 | BID AWARD AND REGISTER CONTRCT | 2020-07-01 | 2021-03-31 | 2020-07-01 | 2021-03-31
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-440B | Bronx 7/8 Garage Slab Replacement | 5 | CONSTRUCTION TO 25% | 2021-04-01 | 2021-06-29 | 2021-04-01 | 2021-06-29
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-440B | Bronx 7/8 Garage Slab Replacement | 6 | CONSTRUCTION TO 50% | 2021-06-30 | 2021-09-27 | 2021-06-30 | 2021-09-27
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-440B | Bronx 7/8 Garage Slab Replacement | 7 | CONSTRUCTION TO 75% | 2021-09-28 | 2022-01-25 | 2021-09-28 | 2022-01-25
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-440B | Bronx 7/8 Garage Slab Replacement | 8 | SUBSTANTIAL COMPLETION | 2022-01-26 | 2022-06-30 | 2022-01-26 | 2022-06-30
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-440B | Bronx 7/8 Garage Slab Replacement | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-07-01 | 2023-11-12 | 2022-07-01 | 2023-11-12
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-441B | Manhattan 4/4A/7 Garage Broom Wash Drainage | 1 | DEVELOP SCOPE | 2018-01-02 | 2018-03-02 | 2018-01-02 | 2018-03-02
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-441B | Manhattan 4/4A/7 Garage Broom Wash Drainage | 2 | PRELIMINARY DESIGN | 2018-03-03 | 2018-05-31 | 2018-03-03 | 2018-05-31
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-441B | Manhattan 4/4A/7 Garage Broom Wash Drainage | 3 | FINAL DESIGN | 2018-06-01 | 2019-02-05 | 2018-06-01 | 2019-02-05
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-441B | Manhattan 4/4A/7 Garage Broom Wash Drainage | 4 | BID AWARD AND REGISTER CONTRCT | 2019-02-06 | 2019-10-13 | 2019-02-06 | 2020-01-21
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-441B | Manhattan 4/4A/7 Garage Broom Wash Drainage | 5 | CONSTRUCTION TO 25% | 2019-10-14 | 2020-06-09 | 2020-01-22 | 2020-09-17
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-441B | Manhattan 4/4A/7 Garage Broom Wash Drainage | 6 | CONSTRUCTION TO 50% | 2020-06-10 | 2021-02-04 | 2020-09-18 | 2021-05-15
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-441B | Manhattan 4/4A/7 Garage Broom Wash Drainage | 7 | CONSTRUCTION TO 75% | 2021-02-05 | 2021-10-02 | 2021-05-16 | 2022-01-10
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-441B | Manhattan 4/4A/7 Garage Broom Wash Drainage | 8 | SUBSTANTIAL COMPLETION | 2021-10-03 | 2022-10-02 | 2022-01-11 | 2022-10-07
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-441B | Manhattan 4/4A/7 Garage Broom Wash Drainage | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-10-03 | 2023-10-02 | 2022-10-08 | 2023-10-02
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-441S | Manhattan 4/4A/7 Garage Sprinkler System Upgrades | 1 | DEVELOP SCOPE | 2016-01-01 | 2017-09-21 | 2016-01-01 | 2017-09-21
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-441S | Manhattan 4/4A/7 Garage Sprinkler System Upgrades | 2 | PRELIMINARY DESIGN | 2017-09-22 | 2017-12-20 | 2017-09-22 | 2017-12-20
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-441S | Manhattan 4/4A/7 Garage Sprinkler System Upgrades | 3 | FINAL DESIGN | 2017-12-21 | 2018-06-18 | 2017-12-21 | 2018-06-18
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-441S | Manhattan 4/4A/7 Garage Sprinkler System Upgrades | 4 | BID AWARD AND REGISTER CONTRCT | 2018-06-19 | 2018-12-15 | 2018-06-19 | 2018-12-15
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-441S | Manhattan 4/4A/7 Garage Sprinkler System Upgrades | 5 | CONSTRUCTION TO 25% | 2018-12-16 | 2019-12-15 | 2018-12-16 | 2019-12-15
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-441S | Manhattan 4/4A/7 Garage Sprinkler System Upgrades | 6 | CONSTRUCTION TO 50% | 2019-12-16 | 2020-08-11 | 2019-12-16 | 2020-08-11
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-441S | Manhattan 4/4A/7 Garage Sprinkler System Upgrades | 7 | CONSTRUCTION TO 75% | 2020-08-12 | 2021-04-08 | 2020-08-12 | 2021-04-08
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-441S | Manhattan 4/4A/7 Garage Sprinkler System Upgrades | 8 | SUBSTANTIAL COMPLETION | 2021-04-09 | 2022-11-29 | 2021-04-09 | 2022-11-29
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-441S | Manhattan 4/4A/7 Garage Sprinkler System Upgrades | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-11-30 | 2024-07-21 | 2022-11-30 | 2024-07-21
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-447 | Manhattan 44 Beaver St Elevators | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-447 | Manhattan 44 Beaver St Elevators | 2 | PRELIMINARY DESIGN | 2017-12-28 | 2018-06-25 | 2017-12-28 | 2018-06-25
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-447 | Manhattan 44 Beaver St Elevators | 3 | FINAL DESIGN | 2018-06-26 | 2019-06-20 | 2018-06-26 | 2019-06-20
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-447 | Manhattan 44 Beaver St Elevators | 4 | BID AWARD AND REGISTER CONTRCT | 2019-06-21 | 2020-06-14 | 2019-06-21 | 2020-06-14
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-447 | Manhattan 44 Beaver St Elevators | 5 | CONSTRUCTION TO 25% | 2020-06-15 | 2021-06-09 | 2020-06-15 | 2021-06-09
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-447 | Manhattan 44 Beaver St Elevators | 6 | CONSTRUCTION TO 50% | 2021-06-10 | 2022-06-04 | 2021-06-10 | 2022-06-04
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-447 | Manhattan 44 Beaver St Elevators | 7 | CONSTRUCTION TO 75% | 2022-06-05 | 2023-05-30 | 2022-06-05 | 2023-05-30
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-447 | Manhattan 44 Beaver St Elevators | 8 | SUBSTANTIAL COMPLETION | 2023-05-31 | 2025-01-19 | 2023-05-31 | 2025-01-19
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-447 | Manhattan 44 Beaver St Elevators | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-01-20 | 2027-03-30 | 2025-01-20 | 2027-03-30
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-464 | Manhattan 132 Madison St Garage Roof Replacement | 2 | PRELIMINARY DESIGN | 2016-08-15 | 2017-05-31 | 2016-08-15 | 2017-05-31
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-464 | Manhattan 132 Madison St Garage Roof Replacement | 3 | FINAL DESIGN | 2017-06-01 | 2018-03-17 | 2017-06-01 | 2018-03-17
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-464 | Manhattan 132 Madison St Garage Roof Replacement | 4 | BID AWARD AND REGISTER CONTRCT | 2018-03-18 | 2019-01-01 | 2018-03-18 | 2019-01-01
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-464 | Manhattan 132 Madison St Garage Roof Replacement | 5 | CONSTRUCTION TO 25% | 2019-01-02 | 2019-10-18 | 2019-01-02 | 2019-10-18
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-464 | Manhattan 132 Madison St Garage Roof Replacement | 6 | CONSTRUCTION TO 50% | 2019-10-19 | 2020-10-17 | 2019-10-19 | 2020-10-17
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-464 | Manhattan 132 Madison St Garage Roof Replacement | 7 | CONSTRUCTION TO 75% | 2020-10-18 | 2021-10-17 | 2020-10-18 | 2021-10-17
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-464 | Manhattan 132 Madison St Garage Roof Replacement | 8 | SUBSTANTIAL COMPLETION | 2021-10-18 | 2024-07-13 | 2021-10-18 | 2024-07-13
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-464 | Manhattan 132 Madison St Garage Roof Replacement | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-02-15 | 2024-11-10 | 2022-02-15 | 2024-11-10
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-464A | Bronx 7/8 Garage Roof Replacement | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-09-28 | 2016-07-01 | 2016-09-28
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-464A | Bronx 7/8 Garage Roof Replacement | 2 | PRELIMINARY DESIGN | 2016-09-29 | 2017-01-26 | 2016-09-29 | 2017-01-26
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-464A | Bronx 7/8 Garage Roof Replacement | 3 | FINAL DESIGN | 2017-01-27 | 2017-05-26 | 2017-01-27 | 2017-05-26
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-464A | Bronx 7/8 Garage Roof Replacement | 4 | BID AWARD AND REGISTER CONTRCT | 2017-05-27 | 2018-05-26 | 2017-05-27 | 2018-05-26
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-464A | Bronx 7/8 Garage Roof Replacement | 5 | CONSTRUCTION TO 25% | 2018-05-27 | 2019-05-26 | 2018-05-27 | 2019-05-26
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-464A | Bronx 7/8 Garage Roof Replacement | 6 | CONSTRUCTION TO 50% | 2019-05-27 | 2020-05-25 | 2019-05-27 | 2020-05-25
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-464A | Bronx 7/8 Garage Roof Replacement | 7 | CONSTRUCTION TO 75% | 2020-05-26 | 2021-05-25 | 2020-05-26 | 2021-05-25
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-464A | Bronx 7/8 Garage Roof Replacement | 8 | SUBSTANTIAL COMPLETION | 2021-05-26 | 2023-08-03 | 2021-05-26 | 2023-08-03
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-464A | Bronx 7/8 Garage Roof Replacement | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-08-04 | 2025-10-11 | 2023-08-04 | 2025-10-11
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-464D | Manhattan Henry St Roof Replacement | 1 | DEVELOP SCOPE | 2016-12-01 | 2017-08-07 | 2016-12-01 | 2017-08-07
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-464D | Manhattan Henry St Roof Replacement | 2 | PRELIMINARY DESIGN | 2017-08-08 | 2018-02-03 | 2017-08-08 | 2018-02-03
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-464D | Manhattan Henry St Roof Replacement | 3 | FINAL DESIGN | 2018-02-04 | 2018-08-17 | 2018-02-04 | 2018-08-17
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-464D | Manhattan Henry St Roof Replacement | 4 | BID AWARD AND REGISTER CONTRCT | 2018-08-18 | 2019-08-17 | 2018-08-18 | 2019-08-17
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-464D | Manhattan Henry St Roof Replacement | 5 | CONSTRUCTION TO 25% | 2019-08-18 | 2020-08-16 | 2019-08-18 | 2020-08-16
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-464D | Manhattan Henry St Roof Replacement | 6 | CONSTRUCTION TO 50% | 2020-08-17 | 2021-08-16 | 2020-08-17 | 2021-08-16
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-464D | Manhattan Henry St Roof Replacement | 7 | CONSTRUCTION TO 75% | 2021-08-17 | 2022-08-16 | 2021-08-17 | 2022-08-16
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-464D | Manhattan Henry St Roof Replacement | 8 | SUBSTANTIAL COMPLETION | 2022-08-17 | 2024-07-16 | 2022-08-17 | 2024-07-16
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-464D | Manhattan Henry St Roof Replacement | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-07-17 | 2026-06-16 | 2024-07-17 | 2026-06-16
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-464E | Manhattan 8 215th St Garage Roof and Masonry Replacement | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-08-14 | 2016-07-01 | 2016-08-14
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-464E | Manhattan 8 215th St Garage Roof and Masonry Replacement | 2 | PRELIMINARY DESIGN | 2016-08-15 | 2017-08-14 | 2016-08-15 | 2017-08-14
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-464E | Manhattan 8 215th St Garage Roof and Masonry Replacement | 3 | FINAL DESIGN | 2017-08-15 | 2018-08-14 | 2017-08-15 | 2018-08-14
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-464E | Manhattan 8 215th St Garage Roof and Masonry Replacement | 4 | BID AWARD AND REGISTER CONTRCT | 2018-08-15 | 2019-08-14 | 2018-08-15 | 2019-08-14
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-464E | Manhattan 8 215th St Garage Roof and Masonry Replacement | 5 | CONSTRUCTION TO 25% | 2019-08-15 | 2020-08-13 | 2019-08-15 | 2020-08-13
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-464E | Manhattan 8 215th St Garage Roof and Masonry Replacement | 6 | CONSTRUCTION TO 50% | 2020-08-14 | 2021-08-13 | 2020-08-14 | 2021-08-13
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-464E | Manhattan 8 215th St Garage Roof and Masonry Replacement | 7 | CONSTRUCTION TO 75% | 2021-08-14 | 2022-08-13 | 2021-08-14 | 2022-08-13
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-464E | Manhattan 8 215th St Garage Roof and Masonry Replacement | 8 | SUBSTANTIAL COMPLETION | 2022-08-14 | 2023-08-13 | 2022-08-14 | 2023-08-13
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-464E | Manhattan 8 215th St Garage Roof and Masonry Replacement | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-08-14 | 2026-01-29 | 2023-08-14 | 2026-01-29
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S195-228E | Manhattan West 55th Salt Shed gate and related work | 1 | DEVELOP SCOPE | 2017-02-01 | 2017-03-02 | 2017-02-01 | 2017-03-02
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S195-228E | Manhattan West 55th Salt Shed gate and related work | 2 | PRELIMINARY DESIGN | 2017-03-03 | 2017-08-29 | 2017-03-03 | 2017-08-29
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S195-228E | Manhattan West 55th Salt Shed gate and related work | 3 | FINAL DESIGN | 2017-08-30 | 2018-02-25 | 2017-08-30 | 2018-02-25
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S195-228E | Manhattan West 55th Salt Shed gate and related work | 4 | BID AWARD AND REGISTER CONTRCT | 2018-02-26 | 2018-11-22 | 2018-02-26 | 2018-11-22
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S195-228E | Manhattan West 55th Salt Shed gate and related work | 5 | CONSTRUCTION TO 25% | 2018-11-23 | 2019-08-19 | 2018-11-23 | 2019-08-19
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S195-228E | Manhattan West 55th Salt Shed gate and related work | 6 | CONSTRUCTION TO 50% | 2019-08-20 | 2020-05-15 | 2019-08-20 | 2020-05-15
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S195-228E | Manhattan West 55th Salt Shed gate and related work | 7 | CONSTRUCTION TO 75% | 2020-05-16 | 2021-02-09 | 2020-05-16 | 2021-02-09
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S195-228E | Manhattan West 55th Salt Shed gate and related work | 8 | SUBSTANTIAL COMPLETION | 2021-02-10 | 2023-01-10 | 2021-02-10 | 2023-01-10
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S195-228E | Manhattan West 55th Salt Shed gate and related work | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-01-11 | 2024-12-10 | 2023-01-11 | 2024-12-10
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S216-415C | West 59th street MTS Dredging | 1 | DEVELOP SCOPE | 2019-01-16 | 2019-09-22 | 2019-01-16 | 2019-09-22
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S216-415C | West 59th street MTS Dredging | 2 | PRELIMINARY DESIGN | 2019-09-23 | 2020-01-30 | 2019-09-23 | 2020-01-30
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S216-415C | West 59th street MTS Dredging | 3 | FINAL DESIGN | 2020-01-31 | 2020-03-30 | 2020-01-31 | 2020-03-30
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S216-415C | West 59th street MTS Dredging | 4 | BID AWARD AND REGISTER CONTRCT | 2020-03-31 | 2020-06-28 | 2020-03-31 | 2020-06-28
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S216-415C | West 59th street MTS Dredging | 5 | CONSTRUCTION TO 25% | 2020-06-29 | 2021-04-14 | 2020-06-29 | 2021-04-14
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S216-415C | West 59th street MTS Dredging | 6 | CONSTRUCTION TO 50% | 2021-04-15 | 2021-10-21 | 2021-04-15 | 2021-10-21
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S216-415C | West 59th street MTS Dredging | 7 | CONSTRUCTION TO 75% | 2021-10-22 | 2022-02-18 | 2021-10-22 | 2022-02-18
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S216-415C | West 59th street MTS Dredging | 8 | SUBSTANTIAL COMPLETION | 2022-02-19 | 2022-07-18 | 2022-02-19 | 2022-07-18
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S216-415C | West 59th street MTS Dredging | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-07-19 | 2022-11-15 | 2022-07-19 | 2022-11-15
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S236-335A | Manhattan 6/6A/8 Garage Construction | 1 | DEVELOP SCOPE | 2013-01-02 | 2013-03-02 | 2013-01-02 | 2013-03-02
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S236-335A | Manhattan 6/6A/8 Garage Construction | 2 | PRELIMINARY DESIGN | 2013-03-03 | 2014-03-02 | 2013-03-03 | 2014-03-02
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S236-335A | Manhattan 6/6A/8 Garage Construction | 3 | FINAL DESIGN | 2014-03-03 | 2015-03-02 | 2014-03-03 | 2023-06-30
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S236-335A | Manhattan 6/6A/8 Garage Construction | 4 | BID AWARD AND REGISTER CONTRCT | 2015-03-03 | 2016-03-01 | 2023-07-01 | 2024-06-29
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S236-335A | Manhattan 6/6A/8 Garage Construction | 5 | CONSTRUCTION TO 25% | 2016-03-02 | 2017-03-01 | 2024-06-30 | 2025-06-29
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S236-335A | Manhattan 6/6A/8 Garage Construction | 6 | CONSTRUCTION TO 50% | 2017-03-02 | 2018-03-01 | 2025-06-30 | 2026-06-29
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S236-335A | Manhattan 6/6A/8 Garage Construction | 7 | CONSTRUCTION TO 75% | 2018-03-02 | 2019-03-01 | 2026-06-30 | 2027-06-29
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S236-335A | Manhattan 6/6A/8 Garage Construction | 8 | SUBSTANTIAL COMPLETION | 2019-03-02 | 2021-01-29 | 2027-06-30 | 2028-01-15
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S236-335A | Manhattan 6/6A/8 Garage Construction | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-01-30 | 2022-12-30 | 2028-01-16 | 2028-08-02
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SAND26MBC | Hurricane Sandy 26 St Manh Boro Rpr Shop Conduit Work | 1 | DEVELOP SCOPE | 2017-08-25 | 2018-05-31 | 2017-08-25 | 2018-05-31
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SAND26MBC | Hurricane Sandy 26 St Manh Boro Rpr Shop Conduit Work | 2 | PRELIMINARY DESIGN | 2018-06-01 | 2019-03-07 | 2018-06-01 | 2019-03-07
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SAND26MBC | Hurricane Sandy 26 St Manh Boro Rpr Shop Conduit Work | 3 | FINAL DESIGN | 2019-03-08 | 2020-03-06 | 2019-03-08 | 2020-03-06
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SAND26MBC | Hurricane Sandy 26 St Manh Boro Rpr Shop Conduit Work | 4 | BID AWARD AND REGISTER CONTRCT | 2020-03-07 | 2021-03-06 | 2020-03-07 | 2021-03-06
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SAND26MBC | Hurricane Sandy 26 St Manh Boro Rpr Shop Conduit Work | 5 | CONSTRUCTION TO 25% | 2021-03-07 | 2022-03-06 | 2021-03-07 | 2022-03-06
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SAND26MBC | Hurricane Sandy 26 St Manh Boro Rpr Shop Conduit Work | 6 | CONSTRUCTION TO 50% | 2022-03-07 | 2023-03-06 | 2022-03-07 | 2023-03-06
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SAND26MBC | Hurricane Sandy 26 St Manh Boro Rpr Shop Conduit Work | 7 | CONSTRUCTION TO 75% | 2023-03-07 | 2024-03-05 | 2023-03-07 | 2024-03-05
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SAND26MBC | Hurricane Sandy 26 St Manh Boro Rpr Shop Conduit Work | 8 | SUBSTANTIAL COMPLETION | 2024-03-06 | 2025-10-26 | 2024-03-06 | 2025-10-26
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SAND26MBC | Hurricane Sandy 26 St Manh Boro Rpr Shop Conduit Work | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-10-27 | 2026-02-23 | 2025-10-27 | 2026-02-23
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SAND26MBS | Hurricane Sandy 26 St Manh Boro R/R & Haz Mitigation | 1 | DEVELOP SCOPE | 2015-08-25 | 2016-02-20 | 2015-08-25 | 2016-02-20
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SAND26MBS | Hurricane Sandy 26 St Manh Boro R/R & Haz Mitigation | 2 | PRELIMINARY DESIGN | 2016-02-21 | 2017-02-19 | 2016-02-21 | 2017-02-19
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SAND26MBS | Hurricane Sandy 26 St Manh Boro R/R & Haz Mitigation | 3 | FINAL DESIGN | 2017-02-20 | 2018-02-19 | 2017-02-20 | 2018-02-19
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SAND26MBS | Hurricane Sandy 26 St Manh Boro R/R & Haz Mitigation | 4 | BID AWARD AND REGISTER CONTRCT | 2018-02-20 | 2019-02-19 | 2018-02-20 | 2019-02-19
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SAND26MBS | Hurricane Sandy 26 St Manh Boro R/R & Haz Mitigation | 5 | CONSTRUCTION TO 25% | 2019-02-20 | 2020-02-19 | 2019-02-20 | 2020-02-19
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SAND26MBS | Hurricane Sandy 26 St Manh Boro R/R & Haz Mitigation | 6 | CONSTRUCTION TO 50% | 2020-02-20 | 2021-02-18 | 2020-02-20 | 2021-02-18
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SAND26MBS | Hurricane Sandy 26 St Manh Boro R/R & Haz Mitigation | 7 | CONSTRUCTION TO 75% | 2021-02-19 | 2022-02-18 | 2021-02-19 | 2022-02-18
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SAND26MBS | Hurricane Sandy 26 St Manh Boro R/R & Haz Mitigation | 8 | SUBSTANTIAL COMPLETION | 2022-02-19 | 2023-02-18 | 2022-02-19 | 2023-02-18
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SAND26MBS | Hurricane Sandy 26 St Manh Boro R/R & Haz Mitigation | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-02-19 | 2025-11-14 | 2023-02-19 | 2025-11-14
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SAND44BVC | Hurricane Sandy 44 Beaver Street Conduit Replacement | 1 | DEVELOP SCOPE | 2017-08-25 | 2018-05-31 | 2017-08-25 | 2018-05-31
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SAND44BVC | Hurricane Sandy 44 Beaver Street Conduit Replacement | 2 | PRELIMINARY DESIGN | 2018-06-01 | 2019-03-07 | 2018-06-01 | 2019-03-07
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SAND44BVC | Hurricane Sandy 44 Beaver Street Conduit Replacement | 3 | FINAL DESIGN | 2019-03-08 | 2019-12-12 | 2019-03-08 | 2019-12-12
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SAND44BVC | Hurricane Sandy 44 Beaver Street Conduit Replacement | 4 | BID AWARD AND REGISTER CONTRCT | 2019-12-13 | 2020-09-17 | 2019-12-13 | 2020-09-17
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SAND44BVC | Hurricane Sandy 44 Beaver Street Conduit Replacement | 5 | CONSTRUCTION TO 25% | 2020-09-18 | 2021-06-24 | 2020-09-18 | 2021-06-24
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SAND44BVC | Hurricane Sandy 44 Beaver Street Conduit Replacement | 6 | CONSTRUCTION TO 50% | 2021-06-25 | 2022-03-31 | 2021-06-25 | 2022-03-31
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SAND44BVC | Hurricane Sandy 44 Beaver Street Conduit Replacement | 7 | CONSTRUCTION TO 75% | 2022-04-01 | 2023-01-05 | 2022-04-01 | 2023-01-05
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SAND44BVC | Hurricane Sandy 44 Beaver Street Conduit Replacement | 8 | SUBSTANTIAL COMPLETION | 2023-01-06 | 2024-08-27 | 2023-01-06 | 2024-08-27
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SAND44BVC | Hurricane Sandy 44 Beaver Street Conduit Replacement | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-08-28 | 2026-04-19 | 2024-08-28 | 2026-04-19
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SAND44BVR | Hurricane Sandy 44 Beaver St System Replacement | 1 | DEVELOP SCOPE | 2015-08-25 | 2016-02-20 | 2015-08-25 | 2016-02-20
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SAND44BVR | Hurricane Sandy 44 Beaver St System Replacement | 2 | PRELIMINARY DESIGN | 2016-02-21 | 2017-02-19 | 2016-02-21 | 2017-02-19
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SAND44BVR | Hurricane Sandy 44 Beaver St System Replacement | 3 | FINAL DESIGN | 2017-02-20 | 2018-02-19 | 2017-02-20 | 2018-02-19
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SAND44BVR | Hurricane Sandy 44 Beaver St System Replacement | 4 | BID AWARD AND REGISTER CONTRCT | 2018-02-20 | 2019-02-19 | 2018-02-20 | 2019-02-19
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SAND44BVR | Hurricane Sandy 44 Beaver St System Replacement | 5 | CONSTRUCTION TO 25% | 2019-02-20 | 2020-02-19 | 2019-02-20 | 2020-02-19
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SAND44BVR | Hurricane Sandy 44 Beaver St System Replacement | 6 | CONSTRUCTION TO 50% | 2020-02-20 | 2021-02-18 | 2020-02-20 | 2021-02-18
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SAND44BVR | Hurricane Sandy 44 Beaver St System Replacement | 7 | CONSTRUCTION TO 75% | 2021-02-19 | 2022-02-18 | 2021-02-19 | 2022-02-18
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SAND44BVR | Hurricane Sandy 44 Beaver St System Replacement | 8 | SUBSTANTIAL COMPLETION | 2022-02-19 | 2024-11-14 | 2022-02-19 | 2024-11-14
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SAND44BVR | Hurricane Sandy 44 Beaver St System Replacement | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-06-19 | 2025-03-14 | 2022-06-19 | 2025-03-14
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SANDMAN3C | Hurricane Sandy Manh 3 Garage Conduit Replacement | 1 | DEVELOP SCOPE | 2017-08-25 | 2018-02-20 | 2017-08-25 | 2018-02-20
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SANDMAN3C | Hurricane Sandy Manh 3 Garage Conduit Replacement | 2 | PRELIMINARY DESIGN | 2018-02-21 | 2018-11-07 | 2018-02-21 | 2018-11-07
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SANDMAN3C | Hurricane Sandy Manh 3 Garage Conduit Replacement | 3 | FINAL DESIGN | 2018-11-08 | 2019-08-24 | 2018-11-08 | 2019-08-24
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SANDMAN3C | Hurricane Sandy Manh 3 Garage Conduit Replacement | 4 | BID AWARD AND REGISTER CONTRCT | 2019-08-25 | 2020-06-09 | 2019-08-25 | 2020-06-09
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SANDMAN3C | Hurricane Sandy Manh 3 Garage Conduit Replacement | 5 | CONSTRUCTION TO 25% | 2020-06-10 | 2021-03-26 | 2020-06-10 | 2021-03-26
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SANDMAN3C | Hurricane Sandy Manh 3 Garage Conduit Replacement | 6 | CONSTRUCTION TO 50% | 2021-03-27 | 2022-03-26 | 2021-03-27 | 2022-03-26
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SANDMAN3C | Hurricane Sandy Manh 3 Garage Conduit Replacement | 7 | CONSTRUCTION TO 75% | 2022-03-27 | 2023-03-26 | 2022-03-27 | 2023-03-26
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SANDMAN3C | Hurricane Sandy Manh 3 Garage Conduit Replacement | 8 | SUBSTANTIAL COMPLETION | 2023-03-27 | 2025-09-11 | 2023-03-27 | 2025-09-11
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SANDMAN3C | Hurricane Sandy Manh 3 Garage Conduit Replacement | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-09-12 | 2028-02-28 | 2025-09-12 | 2028-02-28
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SANDMAN3G | Hurricane Sandy Manh 3 Garage Repl & Haz Mitigation | 1 | DEVELOP SCOPE | 2015-08-25 | 2016-02-20 | 2015-08-25 | 2016-02-20
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SANDMAN3G | Hurricane Sandy Manh 3 Garage Repl & Haz Mitigation | 2 | PRELIMINARY DESIGN | 2016-02-21 | 2017-02-19 | 2016-02-21 | 2017-02-19
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SANDMAN3G | Hurricane Sandy Manh 3 Garage Repl & Haz Mitigation | 3 | FINAL DESIGN | 2017-02-20 | 2018-02-19 | 2017-02-20 | 2018-02-19
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SANDMAN3G | Hurricane Sandy Manh 3 Garage Repl & Haz Mitigation | 4 | BID AWARD AND REGISTER CONTRCT | 2018-02-20 | 2019-02-19 | 2018-02-20 | 2019-02-19
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SANDMAN3G | Hurricane Sandy Manh 3 Garage Repl & Haz Mitigation | 5 | CONSTRUCTION TO 25% | 2019-02-20 | 2020-02-19 | 2019-02-20 | 2020-02-19
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SANDMAN3G | Hurricane Sandy Manh 3 Garage Repl & Haz Mitigation | 6 | CONSTRUCTION TO 50% | 2020-02-20 | 2021-02-18 | 2020-02-20 | 2021-02-18
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SANDMAN3G | Hurricane Sandy Manh 3 Garage Repl & Haz Mitigation | 7 | CONSTRUCTION TO 75% | 2021-02-19 | 2022-02-18 | 2021-02-19 | 2022-02-18
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SANDMAN3G | Hurricane Sandy Manh 3 Garage Repl & Haz Mitigation | 8 | SUBSTANTIAL COMPLETION | 2022-02-19 | 2024-11-14 | 2022-02-19 | 2024-11-14
20201123 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SANDMAN3G | Hurricane Sandy Manh 3 Garage Repl & Haz Mitigation | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-06-19 | 2025-03-14 | 2022-06-19 | 2025-03-14
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT504 | Replacement of Park, Highway and Flood Lights with LEDs | 1 | DEVELOP SCOPE | 2018-06-30 | 2018-09-27 | 2020-06-30 | 2020-09-27
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT504 | Replacement of Park, Highway and Flood Lights with LEDs | 2 | PRELIMINARY DESIGN | 2018-09-28 | 2019-01-25 | 2020-09-28 | 2021-01-25
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT504 | Replacement of Park, Highway and Flood Lights with LEDs | 3 | FINAL DESIGN | 2019-01-26 | 2019-07-24 | 2021-01-26 | 2021-07-24
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT504 | Replacement of Park, Highway and Flood Lights with LEDs | 4 | BID AWARD AND REGISTER CONTRCT | 2019-07-25 | 2019-10-22 | 2021-07-25 | 2021-10-22
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT504 | Replacement of Park, Highway and Flood Lights with LEDs | 5 | CONSTRUCTION TO 25% | 2019-10-23 | 2020-02-19 | 2021-10-23 | 2022-02-19
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT504 | Replacement of Park, Highway and Flood Lights with LEDs | 6 | CONSTRUCTION TO 50% | 2020-02-20 | 2020-06-18 | 2022-02-20 | 2022-06-19
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT504 | Replacement of Park, Highway and Flood Lights with LEDs | 7 | CONSTRUCTION TO 75% | 2020-06-19 | 2020-10-16 | 2022-06-20 | 2022-10-17
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT504 | Replacement of Park, Highway and Flood Lights with LEDs | 8 | ORIGINAL EQUIP & FURNISHING | 2020-10-17 | 2021-01-14 | 2022-10-18 | 2023-01-15
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT504 | Replacement of Park, Highway and Flood Lights with LEDs | 9 | SUBSTANTIAL COMPLETION | 2021-01-15 | 2021-03-15 | 2023-01-16 | 2023-03-16
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT504 | Replacement of Park, Highway and Flood Lights with LEDs | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-16 | 2021-04-14 | 2023-03-17 | 2026-04-15
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT602 | DOT - Various locations- Rooftop Solar | 1 | DEVELOP SCOPE | 2018-06-30 | 2018-09-27 | 2018-06-30 | 2018-09-27
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT602 | DOT - Various locations- Rooftop Solar | 2 | PRELIMINARY DESIGN | 2018-09-28 | 2019-01-25 | 2018-09-28 | 2019-01-25
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT602 | DOT - Various locations- Rooftop Solar | 3 | FINAL DESIGN | 2019-01-26 | 2019-07-24 | 2019-01-26 | 2019-07-24
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT602 | DOT - Various locations- Rooftop Solar | 4 | BID AWARD AND REGISTER CONTRCT | 2019-07-25 | 2019-10-22 | 2019-07-25 | 2019-10-22
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT602 | DOT - Various locations- Rooftop Solar | 5 | CONSTRUCTION TO 25% | 2019-10-23 | 2020-02-19 | 2019-10-23 | 2020-02-19
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT602 | DOT - Various locations- Rooftop Solar | 6 | CONSTRUCTION TO 50% | 2020-02-20 | 2020-06-18 | 2020-02-20 | 2020-06-18
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT602 | DOT - Various locations- Rooftop Solar | 7 | CONSTRUCTION TO 75% | 2020-06-19 | 2020-10-16 | 2020-06-19 | 2020-10-16
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT602 | DOT - Various locations- Rooftop Solar | 8 | ORIGINAL EQUIP & FURNISHING | 2020-10-17 | 2021-01-14 | 2020-10-17 | 2021-01-14
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT602 | DOT - Various locations- Rooftop Solar | 9 | SUBSTANTIAL COMPLETION | 2021-01-15 | 2021-03-15 | 2021-01-15 | 2021-03-15
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT602 | DOT - Various locations- Rooftop Solar | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-16 | 2021-04-14 | 2021-03-16 | 2021-04-14
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | E34CCTV | East 34th St Ferry Landing CCTV upgrade | 1 | DEVELOP SCOPE | 2016-06-30 | 2017-06-29 | 2018-06-30 | 2019-06-29
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | E34CCTV | East 34th St Ferry Landing CCTV upgrade | 2 | DESIGN START | 2017-06-30 | 2019-06-29 | 2019-06-30 | 2021-06-28
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | E34CCTV | East 34th St Ferry Landing CCTV upgrade | 3 | CONSTRUCTION START | 2019-06-30 | 2021-06-28 | 2021-06-29 | 2023-06-28
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | EMIDTWNRZ | East Midtown Rezoning | 1 | DEVELOP SCOPE | 2018-06-30 | 2018-09-27 | 2020-06-30 | 2020-09-27
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | EMIDTWNRZ | East Midtown Rezoning | 2 | PRELIMINARY DESIGN | 2018-09-28 | 2019-01-25 | 2020-09-28 | 2021-01-25
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | EMIDTWNRZ | East Midtown Rezoning | 3 | FINAL DESIGN | 2019-01-26 | 2019-07-24 | 2021-01-26 | 2021-07-24
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | EMIDTWNRZ | East Midtown Rezoning | 4 | BID AWARD AND REGISTER CONTRCT | 2019-07-25 | 2019-10-22 | 2021-07-25 | 2021-10-22
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | EMIDTWNRZ | East Midtown Rezoning | 5 | CONSTRUCTION TO 25% | 2019-10-23 | 2020-02-19 | 2021-10-23 | 2022-02-19
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | EMIDTWNRZ | East Midtown Rezoning | 6 | CONSTRUCTION TO 50% | 2020-02-20 | 2020-06-18 | 2022-02-20 | 2022-06-19
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | EMIDTWNRZ | East Midtown Rezoning | 7 | CONSTRUCTION TO 75% | 2020-06-19 | 2020-10-16 | 2022-06-20 | 2022-10-17
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | EMIDTWNRZ | East Midtown Rezoning | 8 | ORIGINAL EQUIP & FURNISHING | 2020-10-17 | 2021-01-14 | 2022-10-18 | 2023-01-15
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | EMIDTWNRZ | East Midtown Rezoning | 9 | SUBSTANTIAL COMPLETION | 2021-01-15 | 2021-03-15 | 2023-01-16 | 2023-03-16
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | EMIDTWNRZ | East Midtown Rezoning | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-16 | 2021-04-14 | 2023-03-17 | 2025-06-30
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | FAWTCCTV | WHT Terminal CCTV Upgrades | 1 | DEVELOP SCOPE | 2017-06-30 | 2018-06-29 | 2018-06-30 | 2019-06-29
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | FAWTCCTV | WHT Terminal CCTV Upgrades | 2 | DESIGN START | 2018-06-30 | 2020-06-28 | 2019-06-30 | 2021-06-28
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | FAWTCCTV | WHT Terminal CCTV Upgrades | 3 | CONSTRUCTION START | 2020-06-29 | 2022-06-28 | 2021-06-29 | 2023-06-28
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBFDR14BP | East 14th St (near ConEd Plant) Bike Path | 1 | DEVELOP SCOPE | 2023-06-30 | 2024-06-28 | 0 | 0
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBFDR14BP | East 14th St (near ConEd Plant) Bike Path | 2 | DESIGN START | 2024-06-29 | 2028-06-27 | 2017-06-30 | 2018-06-29
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBFDR14BP | East 14th St (near ConEd Plant) Bike Path | 3 | CONSTRUCTION START | 2028-06-28 | 2030-06-27 | 2018-06-30 | 2022-06-28
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBFDR14BP | East 14th St (near ConEd Plant) Bike Path | 5 | CONSTRUCTION START | 2028-06-28 | 2030-06-27 | 2022-06-29 | 2024-06-27
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBINSPSSC | South Stuy Cove - Captain Brown Walk | 1 | DEVELOP SCOPE | 2017-06-30 | 2017-09-27 | 2018-06-30 | 2018-09-27
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBINSPSSC | South Stuy Cove - Captain Brown Walk | 2 | PRELIMINARY DESIGN | 2017-09-28 | 2018-01-25 | 2018-09-28 | 2019-01-25
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBINSPSSC | South Stuy Cove - Captain Brown Walk | 3 | FINAL DESIGN | 2018-01-26 | 2018-07-24 | 2019-01-26 | 2019-07-24
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBINSPSSC | South Stuy Cove - Captain Brown Walk | 4 | BID AWARD AND REGISTER CONTRCT | 2018-07-25 | 2018-10-22 | 2019-07-25 | 2019-10-22
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBINSPSSC | South Stuy Cove - Captain Brown Walk | 5 | CONSTRUCTION TO 25% | 2018-10-23 | 2019-02-19 | 2019-10-23 | 2020-02-19
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBINSPSSC | South Stuy Cove - Captain Brown Walk | 6 | CONSTRUCTION TO 50% | 2019-02-20 | 2019-06-19 | 2020-02-20 | 2020-06-18
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBINSPSSC | South Stuy Cove - Captain Brown Walk | 7 | CONSTRUCTION TO 75% | 2019-06-20 | 2019-10-17 | 2020-06-19 | 2020-10-16
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBINSPSSC | South Stuy Cove - Captain Brown Walk | 8 | ORIGINAL EQUIP & FURNISHING | 2019-10-18 | 2020-01-15 | 2020-10-17 | 2021-01-14
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBINSPSSC | South Stuy Cove - Captain Brown Walk | 9 | SUBSTANTIAL COMPLETION | 2020-01-16 | 2020-03-15 | 2021-01-15 | 2021-03-15
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBINSPSSC | South Stuy Cove - Captain Brown Walk | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-03-16 | 2020-04-14 | 2021-03-16 | 2024-04-14
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM1027 | HARLEM RV DRIVE VIADUCT: 127TH ST - 2ND AVE #2-23305-9/TN,,, | 1 | DEVELOP SCOPE | 2004-07-01 | 2005-06-30 | 0 | 0
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM1027 | HARLEM RV DRIVE VIADUCT: 127TH ST - 2ND AVE #2-23305-9/TN,,, | 2 | DEVELOP SCOPE | 2005-07-01 | 2009-06-29 | 2007-10-05 | 2011-12-04
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM1027 | HARLEM RV DRIVE VIADUCT: 127TH ST - 2ND AVE #2-23305-9/TN,,, | 3 | DESIGN START | 2009-06-30 | 2011-06-29 | 2008-02-07 | 2014-09-12
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM1027 | HARLEM RV DRIVE VIADUCT: 127TH ST - 2ND AVE #2-23305-9/TN,,, | 5 | CONSTRUCTION START | 2009-06-30 | 2011-06-29 | 2018-11-10 | 2019-07-31
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM1120B | 11TH AVENUE VIADUCT NORTH SECTION - 33 ST to 35 ST #2245010 | 1 | DEVELOP SCOPE | 2013-06-30 | 2014-06-29 | 0 | 0
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM1120B | 11TH AVENUE VIADUCT NORTH SECTION - 33 ST to 35 ST #2245010 | 2 | DESIGN START | 2014-06-30 | 2018-06-28 | 2017-06-30 | 2018-06-29
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM1120B | 11TH AVENUE VIADUCT NORTH SECTION - 33 ST to 35 ST #2245010 | 3 | CONSTRUCTION START | 2018-06-29 | 2020-06-27 | 2018-06-30 | 2022-06-28
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM1120B | 11TH AVENUE VIADUCT NORTH SECTION - 33 ST to 35 ST #2245010 | 5 | CONSTRUCTION START | 2018-06-29 | 2020-06-27 | 2022-06-29 | 2024-06-27
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM1147 | BROADWAY BRIDGE/HARLEM RIVER (BIN 2-24013-7) | 1 | DEVELOP SCOPE | 2006-07-02 | 2007-07-01 | 2003-02-06 | 2005-03-31
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM1147 | BROADWAY BRIDGE/HARLEM RIVER (BIN 2-24013-7) | 2 | DESIGN START | 2007-07-02 | 2011-06-30 | 2006-06-26 | 2017-09-15
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM1147 | BROADWAY BRIDGE/HARLEM RIVER (BIN 2-24013-7) | 3 | CONSTRUCTION START | 2011-07-01 | 2013-06-29 | 2018-09-04 | 2021-10-17
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM1165 | RIVERSIDE DRIVE BR/WEST 158TH 2-24672-0 | 1 | DEVELOP SCOPE | 2010-07-01 | 2011-06-30 | 0 | 0
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM1165 | RIVERSIDE DRIVE BR/WEST 158TH 2-24672-0 | 2 | DESIGN START | 2011-07-01 | 2015-06-29 | 2011-12-23 | 2013-03-26
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM1165 | RIVERSIDE DRIVE BR/WEST 158TH 2-24672-0 | 3 | CONSTRUCTION START | 2015-06-30 | 2017-06-28 | 2014-10-22 | 2017-09-14
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM1165 | RIVERSIDE DRIVE BR/WEST 158TH 2-24672-0 | 5 | CONSTRUCTION START | 2015-06-30 | 2017-06-28 | 2018-10-29 | 2022-09-25
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM1173 | HENRY HUDSON PKWY 94-98TH ST VIADUCT 2-26725-0 | 1 | DEVELOP SCOPE | 2014-06-01 | 2014-08-29 | 2018-06-01 | 2018-08-29
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM1173 | HENRY HUDSON PKWY 94-98TH ST VIADUCT 2-26725-0 | 2 | PRELIMINARY DESIGN | 2014-08-30 | 2014-12-27 | 2018-08-30 | 2018-12-27
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM1173 | HENRY HUDSON PKWY 94-98TH ST VIADUCT 2-26725-0 | 3 | FINAL DESIGN | 2014-12-28 | 2015-06-25 | 2018-12-28 | 2019-06-25
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM1173 | HENRY HUDSON PKWY 94-98TH ST VIADUCT 2-26725-0 | 4 | BID AWARD AND REGISTER CONTRCT | 2015-06-26 | 2015-09-23 | 2019-06-26 | 2019-09-23
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM1173 | HENRY HUDSON PKWY 94-98TH ST VIADUCT 2-26725-0 | 5 | CONSTRUCTION TO 25% | 2015-09-24 | 2016-01-21 | 2019-09-24 | 2020-01-21
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM1173 | HENRY HUDSON PKWY 94-98TH ST VIADUCT 2-26725-0 | 6 | CONSTRUCTION TO 50% | 2016-01-22 | 2016-05-20 | 2020-01-22 | 2020-05-20
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM1173 | HENRY HUDSON PKWY 94-98TH ST VIADUCT 2-26725-0 | 7 | CONSTRUCTION TO 75% | 2016-05-21 | 2016-09-17 | 2020-05-21 | 2020-09-17
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM1173 | HENRY HUDSON PKWY 94-98TH ST VIADUCT 2-26725-0 | 8 | ORIGINAL EQUIP & FURNISHING | 2016-09-18 | 2016-12-16 | 2020-09-18 | 2020-12-16
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM1173 | HENRY HUDSON PKWY 94-98TH ST VIADUCT 2-26725-0 | 9 | SUBSTANTIAL COMPLETION | 2016-12-17 | 2017-02-14 | 2021-04-21 | 2021-04-21
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM1173 | HENRY HUDSON PKWY 94-98TH ST VIADUCT 2-26725-0 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-02-15 | 2017-03-16 | 2021-04-22 | 2021-07-21
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM1189 | WEST 79TH STREET/ AMTRAK (7 BIN#'S) | 1 | DEVELOP SCOPE | 2007-07-01 | 2008-06-29 | 0 | 0
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM1189 | WEST 79TH STREET/ AMTRAK (7 BIN#'S) | 2 | DESIGN START | 2008-06-30 | 2012-06-28 | 2015-10-15 | 2016-05-31
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM1189 | WEST 79TH STREET/ AMTRAK (7 BIN#'S) | 3 | CONSTRUCTION START | 2012-06-29 | 2014-06-28 | 2000-07-06 | 2019-09-17
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM1189 | WEST 79TH STREET/ AMTRAK (7 BIN#'S) | 5 | CONSTRUCTION START | 2012-06-29 | 2014-06-28 | 2020-08-25 | 2024-11-23
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM1212 | REHAB OF PARK AVE VIADUCT, NORTH SIDE OF EAST 42ND STREET | 1 | DEVELOP SCOPE | 2000-07-01 | 2001-06-30 | 0 | 0
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM1212 | REHAB OF PARK AVE VIADUCT, NORTH SIDE OF EAST 42ND STREET | 2 | DEVELOP SCOPE | 2001-07-01 | 2005-06-29 | 2011-07-01 | 2012-06-29
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM1212 | REHAB OF PARK AVE VIADUCT, NORTH SIDE OF EAST 42ND STREET | 3 | DESIGN START | 2005-06-30 | 2007-06-29 | 2012-06-30 | 2016-06-28
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM1212 | REHAB OF PARK AVE VIADUCT, NORTH SIDE OF EAST 42ND STREET | 5 | CONSTRUCTION START | 2005-06-30 | 2007-06-29 | 2016-06-29 | 2018-11-19
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM1221 | E25TH STREET PEDESTRIAN BRIDGE OVER FDR | 1 | DEVELOP SCOPE | 2008-06-30 | 2015-06-28 | 0 | 0
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM1221 | E25TH STREET PEDESTRIAN BRIDGE OVER FDR | 2 | DESIGN START | 2015-06-29 | 2015-06-28 | 2008-06-30 | 2009-06-29
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM1221 | E25TH STREET PEDESTRIAN BRIDGE OVER FDR | 3 | CONSTRUCTION START | 2015-06-29 | 2017-06-27 | 2009-06-30 | 2013-06-28
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM1221 | E25TH STREET PEDESTRIAN BRIDGE OVER FDR | 5 | CONSTRUCTION START | 2015-06-29 | 2017-06-27 | 2020-06-29 | 2022-06-28
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM191TUN | 191st St Pedestrian Tunnel over Broadway & IRT #1 Subway | 1 | DEVELOP SCOPE | 2017-06-30 | 2018-06-29 | 0 | 0
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM191TUN | 191st St Pedestrian Tunnel over Broadway & IRT #1 Subway | 2 | DESIGN START | 2018-06-30 | 2022-06-28 | 2017-07-01 | 2017-10-26
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM191TUN | 191st St Pedestrian Tunnel over Broadway & IRT #1 Subway | 3 | CONSTRUCTION START | 2022-06-29 | 2024-06-27 | 2019-10-13 | 2022-10-11
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM191TUN | 191st St Pedestrian Tunnel over Broadway & IRT #1 Subway | 5 | CONSTRUCTION START | 2022-06-29 | 2024-06-27 | 2023-09-14 | 2027-12-12
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM245070 | West 38th St over Amtrak 30 St Branch BIN 2245070 | 1 | DEVELOP SCOPE | 2019-06-30 | 2020-06-28 | 0 | 0
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM245070 | West 38th St over Amtrak 30 St Branch BIN 2245070 | 2 | DESIGN START | 2020-06-29 | 2024-06-27 | 2019-06-30 | 2020-06-28
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM245070 | West 38th St over Amtrak 30 St Branch BIN 2245070 | 3 | CONSTRUCTION START | 2024-06-28 | 2026-06-27 | 2020-06-29 | 2024-06-27
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM245070 | West 38th St over Amtrak 30 St Branch BIN 2245070 | 5 | CONSTRUCTION START | 2024-06-28 | 2026-06-27 | 2024-06-28 | 2026-06-27
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM245080 | West 39th St over Amtrak 30 St Branch BIN 2245080 | 1 | DEVELOP SCOPE | 2019-06-30 | 2020-06-28 | 0 | 0
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM245080 | West 39th St over Amtrak 30 St Branch BIN 2245080 | 2 | DESIGN START | 2020-06-29 | 2024-06-27 | 2019-06-30 | 2020-06-28
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM245080 | West 39th St over Amtrak 30 St Branch BIN 2245080 | 3 | CONSTRUCTION START | 2024-06-28 | 2026-06-27 | 2020-06-29 | 2024-06-27
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM245080 | West 39th St over Amtrak 30 St Branch BIN 2245080 | 5 | CONSTRUCTION START | 2024-06-28 | 2026-06-27 | 2024-06-28 | 2026-06-27
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM246350 | EAST DR OVER PED PATH OPP EAST 80TH ST BIN 2246350 | 1 | DEVELOP SCOPE | 2018-06-30 | 2019-06-29 | 0 | 0
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM246350 | EAST DR OVER PED PATH OPP EAST 80TH ST BIN 2246350 | 2 | DESIGN START | 2019-06-30 | 2023-06-28 | 2018-06-30 | 2019-06-29
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM246350 | EAST DR OVER PED PATH OPP EAST 80TH ST BIN 2246350 | 3 | CONSTRUCTION START | 2023-06-29 | 2025-06-27 | 2019-06-30 | 2023-06-28
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM246350 | EAST DR OVER PED PATH OPP EAST 80TH ST BIN 2246350 | 5 | CONSTRUCTION START | 2023-06-29 | 2025-06-27 | 2023-06-29 | 2025-06-27
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM551 | PARK AVE TUNNEL FROM E34TH TO E39TH ST'S #2-24654-0/TN61420 | 1 | DEVELOP SCOPE | 2005-07-01 | 2006-06-30 | 0 | 0
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM551 | PARK AVE TUNNEL FROM E34TH TO E39TH ST'S #2-24654-0/TN61420 | 2 | DESIGN START | 2006-07-01 | 2010-06-29 | 2004-07-13 | 2004-07-13
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM551 | PARK AVE TUNNEL FROM E34TH TO E39TH ST'S #2-24654-0/TN61420 | 3 | CONSTRUCTION START | 2010-06-30 | 2012-06-28 | 2006-07-01 | 2015-12-14
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM551 | PARK AVE TUNNEL FROM E34TH TO E39TH ST'S #2-24654-0/TN61420 | 5 | CONSTRUCTION START | 2010-06-30 | 2012-06-28 | 2016-07-25 | 2021-09-07
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM702990 | Rehabilitation of Fort Washington Pedestrian Bridge over AMT | 1 | DEVELOP SCOPE | 2019-06-30 | 2020-06-28 | 0 | 0
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM702990 | Rehabilitation of Fort Washington Pedestrian Bridge over AMT | 2 | DESIGN START | 2020-06-29 | 2024-06-27 | 2019-06-30 | 2020-06-28
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM702990 | Rehabilitation of Fort Washington Pedestrian Bridge over AMT | 3 | CONSTRUCTION START | 2024-06-28 | 2026-06-27 | 2020-06-29 | 2024-06-27
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM702990 | Rehabilitation of Fort Washington Pedestrian Bridge over AMT | 5 | CONSTRUCTION START | 2024-06-28 | 2026-06-27 | 2024-06-28 | 2026-06-27
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM8650 | REHAB FDR NORTHBOUND FROM EAST 42-49TH ST BIN: 2268650 | 1 | DEVELOP SCOPE | 2015-06-30 | 2016-06-28 | 0 | 0
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM8650 | REHAB FDR NORTHBOUND FROM EAST 42-49TH ST BIN: 2268650 | 2 | DESIGN START | 2016-06-29 | 2020-06-27 | 2014-09-30 | 2015-01-05
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM8650 | REHAB FDR NORTHBOUND FROM EAST 42-49TH ST BIN: 2268650 | 3 | CONSTRUCTION START | 2020-06-28 | 2022-06-27 | 2016-08-18 | 2020-06-30
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM8650 | REHAB FDR NORTHBOUND FROM EAST 42-49TH ST BIN: 2268650 | 5 | CONSTRUCTION START | 2020-06-28 | 2022-06-27 | 2021-05-14 | 2024-08-16
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA22934 | RAMP TO NB HHP OVER AMTRAK WEST SIDE BIN 222934A | 1 | DEVELOP SCOPE | 2020-06-30 | 2021-06-29 | 0 | 0
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA22934 | RAMP TO NB HHP OVER AMTRAK WEST SIDE BIN 222934A | 2 | DESIGN START | 2021-06-30 | 2025-06-28 | 2017-09-14 | 2018-08-07
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA22934 | RAMP TO NB HHP OVER AMTRAK WEST SIDE BIN 222934A | 3 | CONSTRUCTION START | 2025-06-29 | 2027-06-28 | 2020-01-05 | 2023-01-03
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA22934 | RAMP TO NB HHP OVER AMTRAK WEST SIDE BIN 222934A | 5 | CONSTRUCTION START | 2025-06-29 | 2027-06-28 | 2023-12-06 | 2028-03-04
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA23216 | Promenade over FDR E81st - 90th St Bin 2232167 | 1 | DEVELOP SCOPE | 2022-06-30 | 2023-06-29 | 0 | 0
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA23216 | Promenade over FDR E81st - 90th St Bin 2232167 | 2 | DESIGN START | 2023-06-30 | 2027-06-28 | 2015-11-05 | 2016-02-23
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA23216 | Promenade over FDR E81st - 90th St Bin 2232167 | 3 | CONSTRUCTION START | 2027-06-29 | 2029-06-27 | 2017-05-06 | 2022-03-01
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA23216 | Promenade over FDR E81st - 90th St Bin 2232167 | 5 | CONSTRUCTION START | 2027-06-29 | 2029-06-27 | 2023-02-01 | 2027-05-07
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA24501 | WEST 35TH ST/ AMTRAK 30ST BRANCH BIN# 224501E | 1 | DEVELOP SCOPE | 2016-07-01 | 2017-06-30 | 0 | 0
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA24501 | WEST 35TH ST/ AMTRAK 30ST BRANCH BIN# 224501E | 2 | DESIGN START | 2017-07-01 | 2021-06-29 | 2017-01-16 | 2017-06-13
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA24501 | WEST 35TH ST/ AMTRAK 30ST BRANCH BIN# 224501E | 3 | CONSTRUCTION START | 2021-06-30 | 2023-06-29 | 2018-11-18 | 2022-05-07
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA24501 | WEST 35TH ST/ AMTRAK 30ST BRANCH BIN# 224501E | 5 | CONSTRUCTION START | 2021-06-30 | 2023-06-29 | 2023-03-02 | 2026-06-04
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA24544 | WEST 40TH ST / AMTRAK 30ST BRANCH BIN# 2245440 | 1 | DEVELOP SCOPE | 2016-07-01 | 2017-06-30 | 0 | 0
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA24544 | WEST 40TH ST / AMTRAK 30ST BRANCH BIN# 2245440 | 2 | DESIGN START | 2017-07-01 | 2021-06-29 | 2017-04-19 | 2017-06-19
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA24544 | WEST 40TH ST / AMTRAK 30ST BRANCH BIN# 2245440 | 3 | CONSTRUCTION START | 2021-06-30 | 2023-06-29 | 2018-11-15 | 2022-07-15
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA24544 | WEST 40TH ST / AMTRAK 30ST BRANCH BIN# 2245440 | 5 | CONSTRUCTION START | 2021-06-30 | 2023-06-29 | 2023-07-15 | 2027-10-14
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA24613 | East Dr (Willowdell Arch) over Ped Path Opp East 67th st | 1 | DEVELOP SCOPE | 2017-06-30 | 2018-06-29 | 0 | 0
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA24613 | East Dr (Willowdell Arch) over Ped Path Opp East 67th st | 2 | DESIGN START | 2018-06-30 | 2022-06-28 | 2017-06-30 | 2018-06-29
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA24613 | East Dr (Willowdell Arch) over Ped Path Opp East 67th st | 3 | CONSTRUCTION START | 2022-06-29 | 2024-06-27 | 2018-06-30 | 2022-06-28
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA24613 | East Dr (Willowdell Arch) over Ped Path Opp East 67th st | 5 | CONSTRUCTION START | 2022-06-29 | 2024-06-27 | 2022-06-29 | 2024-06-27
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA26724 | Trans-Manhattan Expressway BIN 2267240 | 1 | DEVELOP SCOPE | 2017-06-30 | 2018-06-29 | 0 | 0
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA26724 | Trans-Manhattan Expressway BIN 2267240 | 2 | DESIGN START | 2018-06-30 | 2022-06-28 | 2017-06-05 | 2017-10-19
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA26724 | Trans-Manhattan Expressway BIN 2267240 | 3 | CONSTRUCTION START | 2022-06-29 | 2024-06-27 | 2019-02-14 | 2022-11-19
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA26724 | Trans-Manhattan Expressway BIN 2267240 | 5 | CONSTRUCTION START | 2022-06-29 | 2024-06-27 | 2024-01-25 | 2028-04-28
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMFDNY20 | FDNY/NFPA CODE UPDATE HHP VARIOUS AND PARK AVE TUNNEL | 1 | DEVELOP SCOPE | 2020-06-30 | 2021-06-29 | 0 | 0
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMFDNY20 | FDNY/NFPA CODE UPDATE HHP VARIOUS AND PARK AVE TUNNEL | 2 | DESIGN START | 2021-06-30 | 2025-06-28 | 2016-08-01 | 2017-05-24
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMFDNY20 | FDNY/NFPA CODE UPDATE HHP VARIOUS AND PARK AVE TUNNEL | 3 | CONSTRUCTION START | 2025-06-29 | 2027-06-28 | 2019-07-08 | 2023-04-02
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMFDNY20 | FDNY/NFPA CODE UPDATE HHP VARIOUS AND PARK AVE TUNNEL | 5 | CONSTRUCTION START | 2025-06-29 | 2027-06-28 | 2024-01-25 | 2028-04-28
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10216 | Walk of Fame -- Walk of Fame installation in CD 8 | 1 | DEVELOP SCOPE | 2019-06-30 | 2019-09-27 | 2021-06-30 | 2021-09-27
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10216 | Walk of Fame -- Walk of Fame installation in CD 8 | 2 | PRELIMINARY DESIGN | 2019-09-28 | 2020-01-25 | 2021-09-28 | 2022-01-25
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10216 | Walk of Fame -- Walk of Fame installation in CD 8 | 3 | FINAL DESIGN | 2020-01-26 | 2020-07-23 | 2022-01-26 | 2022-07-24
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10216 | Walk of Fame -- Walk of Fame installation in CD 8 | 4 | BID AWARD AND REGISTER CONTRCT | 2020-07-24 | 2020-10-21 | 2022-07-25 | 2022-10-22
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10216 | Walk of Fame -- Walk of Fame installation in CD 8 | 5 | CONSTRUCTION TO 25% | 2020-10-22 | 2021-02-18 | 2022-10-23 | 2023-02-19
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10216 | Walk of Fame -- Walk of Fame installation in CD 8 | 6 | CONSTRUCTION TO 50% | 2021-02-19 | 2021-06-18 | 2023-02-20 | 2023-06-19
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10216 | Walk of Fame -- Walk of Fame installation in CD 8 | 7 | CONSTRUCTION TO 75% | 2021-06-19 | 2021-10-16 | 2023-06-20 | 2023-10-17
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10216 | Walk of Fame -- Walk of Fame installation in CD 8 | 8 | ORIGINAL EQUIP & FURNISHING | 2021-10-17 | 2022-01-14 | 2023-10-18 | 2024-01-15
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10216 | Walk of Fame -- Walk of Fame installation in CD 8 | 9 | SUBSTANTIAL COMPLETION | 2022-01-15 | 2022-03-15 | 2024-01-16 | 2024-03-15
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10216 | Walk of Fame -- Walk of Fame installation in CD 8 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-16 | 2022-04-14 | 2024-03-16 | 2025-06-14
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10217 | SAFETY IMPROVEMENTS | 1 | DEVELOP SCOPE | 2016-06-30 | 2016-09-27 | 2020-06-30 | 2020-09-27
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10217 | SAFETY IMPROVEMENTS | 2 | PRELIMINARY DESIGN | 2016-09-28 | 2017-01-25 | 2020-09-28 | 2021-01-25
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10217 | SAFETY IMPROVEMENTS | 3 | FINAL DESIGN | 2017-01-26 | 2017-07-24 | 2021-01-26 | 2021-07-24
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10217 | SAFETY IMPROVEMENTS | 4 | BID AWARD AND REGISTER CONTRCT | 2017-07-25 | 2017-10-22 | 2021-07-25 | 2021-10-22
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10217 | SAFETY IMPROVEMENTS | 5 | CONSTRUCTION TO 25% | 2017-10-23 | 2018-02-19 | 2021-10-23 | 2022-02-19
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10217 | SAFETY IMPROVEMENTS | 6 | CONSTRUCTION TO 50% | 2018-02-20 | 2018-06-19 | 2022-02-20 | 2022-06-19
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10217 | SAFETY IMPROVEMENTS | 7 | CONSTRUCTION TO 75% | 2018-06-20 | 2018-10-17 | 2022-06-20 | 2022-10-17
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10217 | SAFETY IMPROVEMENTS | 8 | ORIGINAL EQUIP & FURNISHING | 2018-10-18 | 2019-01-15 | 2022-10-18 | 2023-01-15
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10217 | SAFETY IMPROVEMENTS | 9 | SUBSTANTIAL COMPLETION | 2019-01-16 | 2019-03-16 | 2023-01-16 | 2023-03-16
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10217 | SAFETY IMPROVEMENTS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-03-17 | 2019-04-15 | 2023-03-17 | 2025-06-30
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10220 | DOT - 3rd Avenue Sidewalks | 1 | DEVELOP SCOPE | 2021-06-30 | 2021-09-27 | 2020-08-28 | 2020-11-25
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10220 | DOT - 3rd Avenue Sidewalks | 2 | PRELIMINARY DESIGN | 2021-09-28 | 2022-01-25 | 2020-11-26 | 2021-03-25
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10220 | DOT - 3rd Avenue Sidewalks | 3 | FINAL DESIGN | 2022-01-26 | 2022-07-24 | 2021-03-26 | 2021-09-21
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10220 | DOT - 3rd Avenue Sidewalks | 4 | BID AWARD AND REGISTER CONTRCT | 2022-07-25 | 2022-10-22 | 2021-09-22 | 2021-12-20
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10220 | DOT - 3rd Avenue Sidewalks | 5 | CONSTRUCTION TO 25% | 2022-10-23 | 2023-02-19 | 2021-12-21 | 2022-04-19
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10220 | DOT - 3rd Avenue Sidewalks | 6 | CONSTRUCTION TO 50% | 2023-02-20 | 2023-06-19 | 2022-04-20 | 2022-08-17
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10220 | DOT - 3rd Avenue Sidewalks | 7 | CONSTRUCTION TO 75% | 2023-06-20 | 2023-10-17 | 2022-08-18 | 2022-12-15
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10220 | DOT - 3rd Avenue Sidewalks | 8 | ORIGINAL EQUIP & FURNISHING | 2023-10-18 | 2024-01-15 | 2022-12-16 | 2023-03-15
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10220 | DOT - 3rd Avenue Sidewalks | 9 | SUBSTANTIAL COMPLETION | 2024-01-16 | 2024-03-15 | 2023-03-16 | 2023-05-14
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10220 | DOT - 3rd Avenue Sidewalks | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-03-16 | 2024-04-14 | 2023-05-15 | 2025-06-30
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD200-05 | Sidewalk Reconstruction, 125th St & Lexington | 1 | DEVELOP SCOPE | 2017-06-30 | 2017-09-27 | 2020-06-30 | 2020-09-27
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD200-05 | Sidewalk Reconstruction, 125th St & Lexington | 2 | PRELIMINARY DESIGN | 2017-09-28 | 2018-01-25 | 2020-09-28 | 2021-01-25
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD200-05 | Sidewalk Reconstruction, 125th St & Lexington | 3 | FINAL DESIGN | 2018-01-26 | 2018-07-24 | 2021-01-26 | 2021-07-24
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD200-05 | Sidewalk Reconstruction, 125th St & Lexington | 4 | BID AWARD AND REGISTER CONTRCT | 2018-07-25 | 2018-10-22 | 2021-07-25 | 2021-10-22
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD200-05 | Sidewalk Reconstruction, 125th St & Lexington | 5 | CONSTRUCTION TO 25% | 2018-10-23 | 2019-02-19 | 2021-10-23 | 2022-02-19
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD200-05 | Sidewalk Reconstruction, 125th St & Lexington | 6 | CONSTRUCTION TO 50% | 2019-02-20 | 2019-06-19 | 2022-02-20 | 2022-06-19
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD200-05 | Sidewalk Reconstruction, 125th St & Lexington | 7 | CONSTRUCTION TO 75% | 2019-06-20 | 2019-10-17 | 2022-06-20 | 2022-10-17
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD200-05 | Sidewalk Reconstruction, 125th St & Lexington | 8 | ORIGINAL EQUIP & FURNISHING | 2019-10-18 | 2020-01-15 | 2022-10-18 | 2023-01-15
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD200-05 | Sidewalk Reconstruction, 125th St & Lexington | 9 | SUBSTANTIAL COMPLETION | 2020-01-16 | 2020-03-15 | 2023-01-16 | 2023-03-16
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD200-05 | Sidewalk Reconstruction, 125th St & Lexington | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-03-16 | 2020-04-14 | 2023-03-17 | 2025-04-15
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM100CTN | 23rd St Crosstown SBS | 1 | DEVELOP SCOPE | 2016-06-30 | 2016-09-27 | 2016-01-04 | 2020-03-20
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM100CTN | 23rd St Crosstown SBS | 2 | PRELIMINARY DESIGN | 2016-09-28 | 2017-01-25 | 2021-01-12 | 2021-03-15
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM100CTN | 23rd St Crosstown SBS | 3 | FINAL DESIGN | 2017-01-26 | 2017-07-24 | 2020-07-24 | 2021-11-03
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM100CTN | 23rd St Crosstown SBS | 4 | BID AWARD AND REGISTER CONTRCT | 2017-07-25 | 2017-10-22 | 2021-07-29 | 2021-11-25
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM100CTN | 23rd St Crosstown SBS | 5 | CONSTRUCTION TO 25% | 2017-10-23 | 2018-02-19 | 2022-03-15 | 2022-08-26
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM100CTN | 23rd St Crosstown SBS | 6 | CONSTRUCTION TO 50% | 2018-02-20 | 2018-06-19 | 2022-08-26 | 2023-02-08
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM100CTN | 23rd St Crosstown SBS | 7 | CONSTRUCTION TO 75% | 2018-06-20 | 2018-10-17 | 2023-02-08 | 2023-07-25
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM100CTN | 23rd St Crosstown SBS | 8 | ORIGINAL EQUIP & FURNISHING | 2018-10-18 | 2019-01-15 | 2023-07-26 | 2023-10-23
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM100CTN | 23rd St Crosstown SBS | 9 | SUBSTANTIAL COMPLETION | 2019-01-16 | 2019-03-16 | 2023-07-24 | 2023-09-15
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM100CTN | 23rd St Crosstown SBS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-03-17 | 2019-04-15 | 2022-09-13 | 2026-06-30
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM1684 | Allen & Pike Street Malls Phase 2 | 1 | DEVELOP SCOPE | 2018-06-30 | 2018-09-27 | 2025-06-30 | 2025-09-27
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM1684 | Allen & Pike Street Malls Phase 2 | 2 | PRELIMINARY DESIGN | 2018-09-28 | 2019-01-25 | 2025-09-28 | 2026-01-25
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM1684 | Allen & Pike Street Malls Phase 2 | 3 | FINAL DESIGN | 2019-01-26 | 2019-07-24 | 2026-01-26 | 2026-07-24
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM1684 | Allen & Pike Street Malls Phase 2 | 4 | BID AWARD AND REGISTER CONTRCT | 2019-07-25 | 2019-10-22 | 2026-07-25 | 2026-10-22
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM1684 | Allen & Pike Street Malls Phase 2 | 5 | CONSTRUCTION TO 25% | 2019-10-23 | 2020-02-19 | 2026-10-23 | 2027-02-19
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM1684 | Allen & Pike Street Malls Phase 2 | 6 | CONSTRUCTION TO 50% | 2020-02-20 | 2020-06-18 | 2027-02-20 | 2027-06-19
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM1684 | Allen & Pike Street Malls Phase 2 | 7 | CONSTRUCTION TO 75% | 2020-06-19 | 2020-10-16 | 2027-06-20 | 2027-10-17
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM1684 | Allen & Pike Street Malls Phase 2 | 8 | ORIGINAL EQUIP & FURNISHING | 2020-10-17 | 2021-01-14 | 2027-10-18 | 2028-01-15
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM1684 | Allen & Pike Street Malls Phase 2 | 9 | SUBSTANTIAL COMPLETION | 2021-01-15 | 2021-03-15 | 2028-01-16 | 2028-03-15
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM1684 | Allen & Pike Street Malls Phase 2 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-16 | 2021-04-14 | 2028-03-16 | 2028-04-14
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM1687 | Holland Tunnel Area Pedestrian Safety Improvements & Public | 1 | DEVELOP SCOPE | 2020-06-30 | 2020-09-27 | 2019-02-01 | 2019-12-22
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM1687 | Holland Tunnel Area Pedestrian Safety Improvements & Public | 2 | PRELIMINARY DESIGN | 2020-09-28 | 2021-01-25 | 2019-12-23 | 2020-04-20
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM1687 | Holland Tunnel Area Pedestrian Safety Improvements & Public | 3 | FINAL DESIGN | 2021-01-26 | 2021-07-24 | 2020-04-21 | 2020-10-17
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM1687 | Holland Tunnel Area Pedestrian Safety Improvements & Public | 4 | BID AWARD AND REGISTER CONTRCT | 2021-07-25 | 2021-10-22 | 2020-10-18 | 2021-01-15
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM1687 | Holland Tunnel Area Pedestrian Safety Improvements & Public | 5 | CONSTRUCTION TO 25% | 2021-10-23 | 2022-02-19 | 2021-01-16 | 2021-05-15
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM1687 | Holland Tunnel Area Pedestrian Safety Improvements & Public | 6 | CONSTRUCTION TO 50% | 2022-02-20 | 2022-06-19 | 2021-05-16 | 2021-09-12
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM1687 | Holland Tunnel Area Pedestrian Safety Improvements & Public | 7 | CONSTRUCTION TO 75% | 2022-06-20 | 2022-10-17 | 2021-09-13 | 2022-01-10
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM1687 | Holland Tunnel Area Pedestrian Safety Improvements & Public | 8 | ORIGINAL EQUIP & FURNISHING | 2022-10-18 | 2023-01-15 | 2022-01-11 | 2022-04-10
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM1687 | Holland Tunnel Area Pedestrian Safety Improvements & Public | 9 | SUBSTANTIAL COMPLETION | 2023-01-16 | 2023-03-16 | 2022-04-11 | 2022-06-09
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM1687 | Holland Tunnel Area Pedestrian Safety Improvements & Public | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-03-17 | 2023-04-15 | 2022-06-10 | 2024-07-09
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM1688 | Harlem Multi-Site | 1 | DEVELOP SCOPE | 2020-06-30 | 2020-09-27 | 2023-06-30 | 2023-09-27
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM1688 | Harlem Multi-Site | 2 | PRELIMINARY DESIGN | 2020-09-28 | 2021-01-25 | 2023-09-28 | 2024-01-25
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM1688 | Harlem Multi-Site | 3 | FINAL DESIGN | 2021-01-26 | 2021-07-24 | 2024-01-26 | 2024-07-23
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM1688 | Harlem Multi-Site | 4 | BID AWARD AND REGISTER CONTRCT | 2021-07-25 | 2021-10-22 | 2024-07-24 | 2024-10-21
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM1688 | Harlem Multi-Site | 5 | CONSTRUCTION TO 25% | 2021-10-23 | 2022-02-19 | 2024-10-22 | 2025-02-18
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM1688 | Harlem Multi-Site | 6 | CONSTRUCTION TO 50% | 2022-02-20 | 2022-06-19 | 2025-02-19 | 2025-06-18
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM1688 | Harlem Multi-Site | 7 | CONSTRUCTION TO 75% | 2022-06-20 | 2022-10-17 | 2025-06-19 | 2025-10-16
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM1688 | Harlem Multi-Site | 8 | ORIGINAL EQUIP & FURNISHING | 2022-10-18 | 2023-01-15 | 2025-10-17 | 2026-01-14
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM1688 | Harlem Multi-Site | 9 | SUBSTANTIAL COMPLETION | 2023-01-16 | 2023-03-16 | 2026-01-15 | 2026-03-15
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM1688 | Harlem Multi-Site | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-03-17 | 2023-04-15 | 2026-03-16 | 2026-04-14
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM2026 | YESHIVA UNIVERSITY AMSTERDAM AVENUE PUBLIC PLAZA | 1 | DESIGN | 2021-06-20 | 2021-12-16 | 2021-06-20 | 2021-12-16
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM2026 | YESHIVA UNIVERSITY AMSTERDAM AVENUE PUBLIC PLAZA | 2 | CONSTRUCTION | 2021-12-17 | 2024-06-20 | 2021-12-17 | 2024-06-20
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM300 | BLEECKER ST. | 1 | DEVELOP SCOPE | 2012-06-30 | 2012-09-27 | 2017-06-29 | 2017-09-26
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM300 | BLEECKER ST. | 2 | PRELIMINARY DESIGN | 2012-09-28 | 2013-01-25 | 2017-09-27 | 2018-01-24
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM300 | BLEECKER ST. | 3 | FINAL DESIGN | 2013-01-26 | 2013-07-24 | 2018-01-25 | 2018-07-23
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM300 | BLEECKER ST. | 4 | BID AWARD AND REGISTER CONTRCT | 2013-07-25 | 2013-10-22 | 2018-07-24 | 2018-10-21
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM300 | BLEECKER ST. | 5 | CONSTRUCTION TO 25% | 2013-10-23 | 2014-02-19 | 2018-10-22 | 2019-02-18
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM300 | BLEECKER ST. | 6 | CONSTRUCTION TO 50% | 2014-02-20 | 2014-06-19 | 2019-02-19 | 2019-06-18
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM300 | BLEECKER ST. | 7 | CONSTRUCTION TO 75% | 2014-06-20 | 2014-10-17 | 2019-06-19 | 2019-10-16
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM300 | BLEECKER ST. | 8 | ORIGINAL EQUIP & FURNISHING | 2014-10-18 | 2015-01-15 | 2019-10-17 | 2020-01-14
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM300 | BLEECKER ST. | 9 | SUBSTANTIAL COMPLETION | 2015-01-16 | 2015-03-16 | 2020-01-15 | 2020-03-14
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM300 | BLEECKER ST. | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-17 | 2015-04-15 | 2020-03-15 | 2024-04-14
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMBRT5 | 34th STREET | 1 | BID AWARD AND REGISTER CONTRCT | 2010-06-01 | 2010-06-01 | 2022-06-01 | 2022-06-01
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMBRT5 | 34th STREET | 2 | CONSTRUCTION START | 2010-06-02 | 2010-07-16 | 2022-06-02 | 2023-06-30
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMBRT5 | 34th STREET | 3 | CONSTRUCTION COMPLETION | 2010-07-17 | 2012-02-06 | 2023-07-01 | 2027-06-30
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMBRT6 | 1st & 2nd Avenue | 1 | BID AWARD AND REGISTER CONTRCT | 2010-06-01 | 2010-06-01 | 2022-06-01 | 2022-06-01
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMBRT6 | 1st & 2nd Avenue | 2 | CONSTRUCTION START | 2010-06-02 | 2010-07-16 | 2022-06-02 | 2022-07-16
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMBRT6 | 1st & 2nd Avenue | 3 | CONSTRUCTION COMPLETION | 2010-07-17 | 2012-02-06 | 2022-07-17 | 2027-06-30
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMM009 | GATEWAYS TO CHINATOWN | 1 | DEVELOP SCOPE | 2009-06-01 | 2009-09-28 | 2011-04-01 | 2011-06-14
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMM009 | GATEWAYS TO CHINATOWN | 2 | DESIGN START | 2009-09-29 | 2011-03-22 | 2019-04-01 | 2020-02-01
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMM009 | GATEWAYS TO CHINATOWN | 3 | CONSTRUCTION START | 2011-03-23 | 2013-03-11 | 2020-11-01 | 2021-08-01
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMMLEXAV | Lexington Avenue Pedestrian Safety Improvements | 1 | DESIGN | 2021-06-04 | 2023-10-27 | 2021-06-04 | 2023-10-27
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMMLEXAV | Lexington Avenue Pedestrian Safety Improvements | 2 | CONSTRUCTION | 2024-06-21 | 2026-06-05 | 2024-06-21 | 2026-06-05
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMMLEXAV | Lexington Avenue Pedestrian Safety Improvements | 3 | ORIGINAL EQUIP & FURNISHING | 2026-06-06 | 2026-06-06 | 2026-06-06 | 2026-06-06
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMMLEXAV | Lexington Avenue Pedestrian Safety Improvements | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2026-03-13 | 2026-06-05 | 2026-03-13 | 2026-06-05
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTC A8 | WORLD TRADE CENTER AREA 8 | 1 | DEVELOP SCOPE | 2009-06-30 | 2009-09-27 | 2017-06-30 | 2017-09-27
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTC A8 | WORLD TRADE CENTER AREA 8 | 2 | PRELIMINARY DESIGN | 2009-09-28 | 2010-01-25 | 2017-09-28 | 2018-01-25
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTC A8 | WORLD TRADE CENTER AREA 8 | 3 | FINAL DESIGN | 2010-01-26 | 2010-07-24 | 2018-01-26 | 2018-07-24
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTC A8 | WORLD TRADE CENTER AREA 8 | 4 | BID AWARD AND REGISTER CONTRCT | 2010-07-25 | 2010-10-22 | 2018-07-25 | 2026-10-22
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTC A8 | WORLD TRADE CENTER AREA 8 | 5 | CONSTRUCTION TO 25% | 2010-10-23 | 2011-02-19 | 2026-10-23 | 2027-02-19
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTC A8 | WORLD TRADE CENTER AREA 8 | 6 | CONSTRUCTION TO 50% | 2011-02-20 | 2011-06-19 | 2027-02-20 | 2027-06-19
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTC A8 | WORLD TRADE CENTER AREA 8 | 7 | CONSTRUCTION TO 75% | 2011-06-20 | 2011-10-17 | 2027-06-20 | 2027-10-17
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTC A8 | WORLD TRADE CENTER AREA 8 | 8 | ORIGINAL EQUIP & FURNISHING | 2011-10-18 | 2012-01-15 | 2027-10-18 | 2028-01-15
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTC A8 | WORLD TRADE CENTER AREA 8 | 9 | SUBSTANTIAL COMPLETION | 2012-01-16 | 2012-03-15 | 2028-01-16 | 2028-03-15
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTC A8 | WORLD TRADE CENTER AREA 8 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-03-16 | 2012-04-14 | 2028-03-16 | 2028-04-14
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTC A9 | WORLD TRADE CENTER AREA 9. | 1 | DEVELOP SCOPE | 2009-06-30 | 2009-09-27 | 2017-06-30 | 2017-09-27
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTC A9 | WORLD TRADE CENTER AREA 9. | 2 | PRELIMINARY DESIGN | 2009-09-28 | 2010-01-25 | 2017-09-28 | 2018-01-25
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTC A9 | WORLD TRADE CENTER AREA 9. | 3 | FINAL DESIGN | 2010-01-26 | 2010-07-24 | 2018-01-26 | 2018-07-24
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTC A9 | WORLD TRADE CENTER AREA 9. | 4 | BID AWARD AND REGISTER CONTRCT | 2010-07-25 | 2010-10-22 | 2018-07-25 | 2026-10-22
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTC A9 | WORLD TRADE CENTER AREA 9. | 5 | CONSTRUCTION TO 25% | 2010-10-23 | 2011-02-19 | 2026-10-23 | 2027-02-19
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTC A9 | WORLD TRADE CENTER AREA 9. | 6 | CONSTRUCTION TO 50% | 2011-02-20 | 2011-06-19 | 2027-02-20 | 2027-06-19
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTC A9 | WORLD TRADE CENTER AREA 9. | 7 | CONSTRUCTION TO 75% | 2011-06-20 | 2011-10-17 | 2027-06-20 | 2027-10-17
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTC A9 | WORLD TRADE CENTER AREA 9. | 8 | ORIGINAL EQUIP & FURNISHING | 2011-10-18 | 2012-01-15 | 2027-10-18 | 2028-01-15
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTC A9 | WORLD TRADE CENTER AREA 9. | 9 | SUBSTANTIAL COMPLETION | 2012-01-16 | 2012-03-15 | 2028-01-16 | 2028-03-15
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTC A9 | WORLD TRADE CENTER AREA 9. | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-03-16 | 2012-04-14 | 2028-03-16 | 2030-04-14
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTC11 | WORLD TRADE CENTER AREA 11 | 1 | DEVELOP SCOPE | 2010-06-30 | 2010-09-27 | 2017-06-30 | 2017-09-27
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTC11 | WORLD TRADE CENTER AREA 11 | 2 | PRELIMINARY DESIGN | 2010-09-28 | 2011-01-25 | 2017-09-28 | 2018-01-25
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTC11 | WORLD TRADE CENTER AREA 11 | 3 | FINAL DESIGN | 2011-01-26 | 2011-07-24 | 2018-01-26 | 2018-07-24
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTC11 | WORLD TRADE CENTER AREA 11 | 4 | BID AWARD AND REGISTER CONTRCT | 2011-07-25 | 2011-10-22 | 2018-07-25 | 2018-10-22
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTC11 | WORLD TRADE CENTER AREA 11 | 5 | CONSTRUCTION TO 25% | 2011-10-23 | 2012-02-19 | 2018-10-23 | 2019-02-19
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTC11 | WORLD TRADE CENTER AREA 11 | 6 | CONSTRUCTION TO 50% | 2012-02-20 | 2012-06-18 | 2019-02-20 | 2019-06-19
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTC11 | WORLD TRADE CENTER AREA 11 | 7 | CONSTRUCTION TO 75% | 2012-06-19 | 2012-10-16 | 2019-06-20 | 2019-10-17
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTC11 | WORLD TRADE CENTER AREA 11 | 8 | ORIGINAL EQUIP & FURNISHING | 2012-10-17 | 2013-01-14 | 2019-10-18 | 2020-01-15
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTC11 | WORLD TRADE CENTER AREA 11 | 9 | SUBSTANTIAL COMPLETION | 2013-01-15 | 2013-03-15 | 2020-01-16 | 2020-03-15
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTC11 | WORLD TRADE CENTER AREA 11 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-03-16 | 2013-04-14 | 2020-03-16 | 2027-06-30
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTCA10 | WORLD TRADE CENTER AREA 10 | 1 | DEVELOP SCOPE | 2010-06-30 | 2010-09-27 | 2017-06-30 | 2017-09-27
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTCA10 | WORLD TRADE CENTER AREA 10 | 2 | PRELIMINARY DESIGN | 2010-09-28 | 2011-01-25 | 2017-09-28 | 2018-01-25
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTCA10 | WORLD TRADE CENTER AREA 10 | 3 | FINAL DESIGN | 2011-01-26 | 2011-07-24 | 2018-01-26 | 2018-07-24
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTCA10 | WORLD TRADE CENTER AREA 10 | 4 | BID AWARD AND REGISTER CONTRCT | 2011-07-25 | 2011-10-22 | 2018-07-25 | 2018-10-22
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTCA10 | WORLD TRADE CENTER AREA 10 | 5 | CONSTRUCTION TO 25% | 2011-10-23 | 2012-02-19 | 2018-10-23 | 2019-02-19
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTCA10 | WORLD TRADE CENTER AREA 10 | 6 | CONSTRUCTION TO 50% | 2012-02-20 | 2012-06-18 | 2019-02-20 | 2019-06-19
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTCA10 | WORLD TRADE CENTER AREA 10 | 7 | CONSTRUCTION TO 75% | 2012-06-19 | 2012-10-16 | 2019-06-20 | 2019-10-17
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTCA10 | WORLD TRADE CENTER AREA 10 | 8 | ORIGINAL EQUIP & FURNISHING | 2012-10-17 | 2013-01-14 | 2019-10-18 | 2020-01-15
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTCA10 | WORLD TRADE CENTER AREA 10 | 9 | SUBSTANTIAL COMPLETION | 2013-01-15 | 2013-03-15 | 2020-01-16 | 2020-03-15
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTCA10 | WORLD TRADE CENTER AREA 10 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-03-16 | 2013-04-14 | 2020-03-16 | 2027-06-30
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTCB3 | Reconstruction of Broadway | 1 | DEVELOP SCOPE | 2021-06-30 | 2021-09-27 | 2016-10-12 | 2017-01-26
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTCB3 | Reconstruction of Broadway | 2 | PRELIMINARY DESIGN | 2021-09-28 | 2022-01-25 | 2017-04-18 | 2018-01-24
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTCB3 | Reconstruction of Broadway | 3 | FINAL DESIGN | 2022-01-26 | 2022-07-24 | 2018-01-16 | 2018-08-06
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTCB3 | Reconstruction of Broadway | 4 | BID AWARD AND REGISTER CONTRCT | 2022-07-25 | 2022-10-22 | 2019-02-11 | 2019-03-28
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTCB3 | Reconstruction of Broadway | 5 | CONSTRUCTION TO 25% | 2022-10-23 | 2023-02-19 | 2019-03-27 | 2019-06-13
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTCB3 | Reconstruction of Broadway | 6 | CONSTRUCTION TO 50% | 2023-02-20 | 2023-06-19 | 2019-06-06 | 2019-08-17
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTCB3 | Reconstruction of Broadway | 7 | CONSTRUCTION TO 75% | 2023-06-20 | 2023-10-17 | 2019-08-17 | 2019-10-27
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTCB3 | Reconstruction of Broadway | 8 | ORIGINAL EQUIP & FURNISHING | 2023-10-18 | 2024-01-15 | 2019-10-28 | 2020-01-25
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTCB3 | Reconstruction of Broadway | 9 | SUBSTANTIAL COMPLETION | 2024-01-16 | 2024-03-15 | 2019-10-15 | 2020-01-07
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTCB3 | Reconstruction of Broadway | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-03-16 | 2024-04-14 | 2020-01-08 | 2028-06-30
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTCB4 | Reconstruction of Varick St | 1 | DEVELOP SCOPE | 2021-06-30 | 2021-09-27 | 2020-10-01 | 2021-01-04
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTCB4 | Reconstruction of Varick St | 2 | PRELIMINARY DESIGN | 2021-09-28 | 2022-01-25 | 2021-04-02 | 2022-01-10
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTCB4 | Reconstruction of Varick St | 3 | FINAL DESIGN | 2022-01-26 | 2022-07-24 | 2022-01-01 | 2022-07-27
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTCB4 | Reconstruction of Varick St | 4 | BID AWARD AND REGISTER CONTRCT | 2022-07-25 | 2022-10-22 | 2023-02-03 | 2023-03-18
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTCB4 | Reconstruction of Varick St | 5 | CONSTRUCTION TO 25% | 2022-10-23 | 2023-02-19 | 2023-03-18 | 2023-09-03
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTCB4 | Reconstruction of Varick St | 6 | CONSTRUCTION TO 50% | 2023-02-20 | 2023-06-19 | 2023-09-03 | 2024-02-20
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTCB4 | Reconstruction of Varick St | 7 | CONSTRUCTION TO 75% | 2023-06-20 | 2023-10-17 | 2024-02-20 | 2024-08-07
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTCB4 | Reconstruction of Varick St | 8 | ORIGINAL EQUIP & FURNISHING | 2023-10-18 | 2024-01-15 | 2024-08-08 | 2024-11-05
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTCB4 | Reconstruction of Varick St | 9 | SUBSTANTIAL COMPLETION | 2024-01-16 | 2024-03-15 | 2024-08-11 | 2025-01-24
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTCB4 | Reconstruction of Varick St | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-03-16 | 2024-04-14 | 2025-01-25 | 2028-06-30
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ010M | Flatiron Plaza Reconstruction | 1 | DEVELOP SCOPE | 2013-06-30 | 2013-09-27 | 2024-06-30 | 2024-09-27
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ010M | Flatiron Plaza Reconstruction | 2 | PRELIMINARY DESIGN | 2013-09-28 | 2014-01-25 | 2024-09-28 | 2025-01-25
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ010M | Flatiron Plaza Reconstruction | 3 | FINAL DESIGN | 2014-01-26 | 2014-07-24 | 2025-01-26 | 2025-07-24
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ010M | Flatiron Plaza Reconstruction | 4 | BID AWARD AND REGISTER CONTRCT | 2014-07-25 | 2014-10-22 | 2025-07-25 | 2025-10-22
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ010M | Flatiron Plaza Reconstruction | 5 | CONSTRUCTION TO 25% | 2014-10-23 | 2015-02-19 | 2025-10-23 | 2026-02-19
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ010M | Flatiron Plaza Reconstruction | 6 | CONSTRUCTION TO 50% | 2015-02-20 | 2015-06-19 | 2026-02-20 | 2026-06-19
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ010M | Flatiron Plaza Reconstruction | 7 | CONSTRUCTION TO 75% | 2015-06-20 | 2015-10-17 | 2026-06-20 | 2026-10-17
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ010M | Flatiron Plaza Reconstruction | 8 | ORIGINAL EQUIP & FURNISHING | 2015-10-18 | 2016-01-15 | 2026-10-18 | 2027-01-15
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ010M | Flatiron Plaza Reconstruction | 9 | SUBSTANTIAL COMPLETION | 2016-01-16 | 2016-03-15 | 2027-01-16 | 2027-03-16
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ010M | Flatiron Plaza Reconstruction | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-16 | 2016-04-14 | 2027-03-17 | 2027-04-15
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ014M | Broadway Boulevard | 1 | DEVELOP SCOPE | 2020-06-30 | 2020-09-27 | 2022-07-22 | 2022-10-20
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ014M | Broadway Boulevard | 2 | PRELIMINARY DESIGN | 2020-09-28 | 2021-01-25 | 2022-10-21 | 2023-02-17
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ014M | Broadway Boulevard | 3 | FINAL DESIGN | 2021-01-26 | 2021-07-24 | 2023-02-18 | 2023-08-16
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ014M | Broadway Boulevard | 4 | BID AWARD AND REGISTER CONTRCT | 2021-07-25 | 2021-10-22 | 2023-08-17 | 2023-11-14
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ014M | Broadway Boulevard | 5 | CONSTRUCTION TO 25% | 2021-10-23 | 2022-02-19 | 2023-11-15 | 2024-03-13
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ014M | Broadway Boulevard | 6 | CONSTRUCTION TO 50% | 2022-02-20 | 2022-06-19 | 2024-03-14 | 2024-07-11
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ014M | Broadway Boulevard | 7 | CONSTRUCTION TO 75% | 2022-06-20 | 2022-10-17 | 2024-07-12 | 2027-11-09
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ014M | Broadway Boulevard | 8 | ORIGINAL EQUIP & FURNISHING | 2022-10-18 | 2023-01-15 | 2020-10-17 | 2021-01-14
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ014M | Broadway Boulevard | 9 | SUBSTANTIAL COMPLETION | 2023-01-16 | 2023-03-16 | 2022-02-07 | 2022-04-07
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ014M | Broadway Boulevard | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-03-17 | 2023-04-15 | 2022-04-08 | 2027-05-07
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWPSMGANS | Gansevoort/Astor Planters | 1 | DEVELOP SCOPE | 2019-06-30 | 2019-09-27 | 2019-06-30 | 2019-09-27
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWPSMGANS | Gansevoort/Astor Planters | 2 | PRELIMINARY DESIGN | 2019-09-28 | 2020-01-25 | 2019-09-28 | 2020-01-25
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWPSMGANS | Gansevoort/Astor Planters | 3 | FINAL DESIGN | 2020-01-26 | 2020-07-23 | 2020-01-26 | 2020-07-23
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWPSMGANS | Gansevoort/Astor Planters | 4 | BID AWARD AND REGISTER CONTRCT | 2020-07-24 | 2020-10-21 | 2020-07-24 | 2020-10-21
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWPSMGANS | Gansevoort/Astor Planters | 5 | CONSTRUCTION TO 25% | 2020-10-22 | 2021-02-18 | 2020-10-22 | 2021-02-18
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWPSMGANS | Gansevoort/Astor Planters | 6 | CONSTRUCTION TO 50% | 2021-02-19 | 2021-06-18 | 2021-02-19 | 2021-06-18
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWPSMGANS | Gansevoort/Astor Planters | 7 | CONSTRUCTION TO 75% | 2021-06-19 | 2021-10-16 | 2021-06-19 | 2021-10-16
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWPSMGANS | Gansevoort/Astor Planters | 8 | ORIGINAL EQUIP & FURNISHING | 2021-10-17 | 2022-01-14 | 2021-10-17 | 2022-01-14
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWPSMGANS | Gansevoort/Astor Planters | 9 | SUBSTANTIAL COMPLETION | 2022-01-15 | 2022-03-15 | 2022-01-15 | 2022-03-15
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWPSMGANS | Gansevoort/Astor Planters | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-16 | 2022-04-14 | 2022-03-16 | 2022-04-14
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWTFLMAD | Street Lamp Posts on Madison Avenue | 1 | DEVELOP SCOPE | 2020-06-30 | 2020-09-27 | 2021-06-30 | 2021-09-27
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWTFLMAD | Street Lamp Posts on Madison Avenue | 2 | PRELIMINARY DESIGN | 2020-09-28 | 2021-01-25 | 2021-09-28 | 2022-01-25
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWTFLMAD | Street Lamp Posts on Madison Avenue | 3 | FINAL DESIGN | 2021-01-26 | 2021-07-24 | 2022-01-26 | 2022-07-24
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWTFLMAD | Street Lamp Posts on Madison Avenue | 4 | BID AWARD AND REGISTER CONTRCT | 2021-07-25 | 2021-10-22 | 2022-07-25 | 2022-10-22
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWTFLMAD | Street Lamp Posts on Madison Avenue | 5 | CONSTRUCTION TO 25% | 2021-10-23 | 2022-02-19 | 2022-10-23 | 2023-02-19
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWTFLMAD | Street Lamp Posts on Madison Avenue | 6 | CONSTRUCTION TO 50% | 2022-02-20 | 2022-06-19 | 2023-02-20 | 2023-06-19
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWTFLMAD | Street Lamp Posts on Madison Avenue | 7 | CONSTRUCTION TO 75% | 2022-06-20 | 2022-10-17 | 2023-06-20 | 2023-10-17
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWTFLMAD | Street Lamp Posts on Madison Avenue | 8 | ORIGINAL EQUIP & FURNISHING | 2022-10-18 | 2023-01-15 | 2023-10-18 | 2024-01-15
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWTFLMAD | Street Lamp Posts on Madison Avenue | 9 | SUBSTANTIAL COMPLETION | 2023-01-16 | 2023-03-16 | 2024-01-16 | 2024-03-15
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWTFLMAD | Street Lamp Posts on Madison Avenue | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-03-17 | 2023-04-15 | 2024-03-16 | 2024-04-14
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWWTCLUMP | World Trade Center - Lump Sum | 1 | DEVELOP SCOPE | 2018-06-30 | 2018-09-27 | 2020-06-30 | 2020-09-27
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWWTCLUMP | World Trade Center - Lump Sum | 2 | PRELIMINARY DESIGN | 2018-09-28 | 2019-01-25 | 2020-09-28 | 2021-01-25
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWWTCLUMP | World Trade Center - Lump Sum | 3 | FINAL DESIGN | 2019-01-26 | 2019-07-24 | 2021-01-26 | 2021-07-24
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWWTCLUMP | World Trade Center - Lump Sum | 4 | BID AWARD AND REGISTER CONTRCT | 2019-07-25 | 2019-10-22 | 2021-07-25 | 2021-10-22
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWWTCLUMP | World Trade Center - Lump Sum | 5 | CONSTRUCTION TO 25% | 2019-10-23 | 2020-02-19 | 2021-10-23 | 2022-02-19
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWWTCLUMP | World Trade Center - Lump Sum | 6 | CONSTRUCTION TO 50% | 2020-02-20 | 2020-06-18 | 2022-02-20 | 2022-06-19
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWWTCLUMP | World Trade Center - Lump Sum | 7 | CONSTRUCTION TO 75% | 2020-06-19 | 2020-10-16 | 2022-06-20 | 2022-10-17
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWWTCLUMP | World Trade Center - Lump Sum | 8 | ORIGINAL EQUIP & FURNISHING | 2020-10-17 | 2021-01-14 | 2022-10-18 | 2023-01-15
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWWTCLUMP | World Trade Center - Lump Sum | 9 | SUBSTANTIAL COMPLETION | 2021-01-15 | 2021-03-15 | 2023-01-16 | 2023-03-16
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWWTCLUMP | World Trade Center - Lump Sum | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-16 | 2021-04-14 | 2023-03-17 | 2029-07-01
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | PIER11CTV | Pier 11 CCTV upgrade | 3 | CONSTRUCTION START | 2019-06-30 | 2021-06-28 | 2018-06-29 | 2020-06-27
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | REALTIMEM | Real Time Traffic Monitoring in Lower Manhattan | 1 | BID AWARD AND REGISTER CONTRCT | 2019-06-30 | 2019-06-30 | 2022-06-30 | 2022-06-30
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | REALTIMEM | Real Time Traffic Monitoring in Lower Manhattan | 2 | CONSTRUCTION START | 2019-07-01 | 2019-08-14 | 2022-07-01 | 2022-08-14
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | REALTIMEM | Real Time Traffic Monitoring in Lower Manhattan | 3 | CONSTRUCTION COMPLETION | 2019-08-15 | 2021-03-06 | 2022-08-15 | 2024-03-06
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | REALTMIDM | Expand Real Time Traffic Monitoring in Midtown Manhattan | 1 | BID AWARD AND REGISTER CONTRCT | 2019-06-30 | 2019-06-30 | 2019-06-01 | 2019-06-30
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | REALTMIDM | Expand Real Time Traffic Monitoring in Midtown Manhattan | 2 | CONSTRUCTION START | 2019-07-01 | 2019-08-14 | 2019-07-01 | 2019-08-14
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | REALTMIDM | Expand Real Time Traffic Monitoring in Midtown Manhattan | 3 | CONSTRUCTION COMPLETION | 2019-08-15 | 2021-03-06 | 2019-08-15 | 2027-03-06
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | SANDHB001 | Battery Park 2-23200 & West St 2-26738 Underpasses- Sandy | 1 | DEVELOP SCOPE | 2013-06-30 | 2014-06-29 | 0 | 0
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | SANDHB001 | Battery Park 2-23200 & West St 2-26738 Underpasses- Sandy | 2 | DESIGN START | 2014-06-30 | 2018-06-28 | 2015-11-18 | 2015-11-18
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | SANDHB001 | Battery Park 2-23200 & West St 2-26738 Underpasses- Sandy | 3 | CONSTRUCTION START | 2018-06-29 | 2020-06-27 | 2015-11-19 | 2019-11-17
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | SANDHB001 | Battery Park 2-23200 & West St 2-26738 Underpasses- Sandy | 5 | CONSTRUCTION START | 2018-06-29 | 2020-06-27 | 2019-11-18 | 2021-11-16
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | SANDHB2U | SANDY ER BETTERMENTS FOR BATTERY PARK & WEST ST UNDERPASSES | 1 | DEVELOP SCOPE | 2020-06-30 | 2021-06-29 | 0 | 0
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | SANDHB2U | SANDY ER BETTERMENTS FOR BATTERY PARK & WEST ST UNDERPASSES | 2 | DESIGN START | 2021-06-30 | 2025-06-28 | 2017-11-01 | 2018-07-13
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | SANDHB2U | SANDY ER BETTERMENTS FOR BATTERY PARK & WEST ST UNDERPASSES | 3 | CONSTRUCTION START | 2025-06-29 | 2027-06-28 | 2018-07-14 | 2022-07-12
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | SANDHB2U | SANDY ER BETTERMENTS FOR BATTERY PARK & WEST ST UNDERPASSES | 5 | CONSTRUCTION START | 2025-06-29 | 2027-06-28 | 2022-07-13 | 2024-07-11
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | SANDHBFDR | SANDY ER FOR FDR 18TH TO 25TH STREET | 1 | DEVELOP SCOPE | 2020-06-30 | 2021-06-29 | 0 | 0
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | SANDHBFDR | SANDY ER FOR FDR 18TH TO 25TH STREET | 2 | DESIGN START | 2021-06-30 | 2025-06-28 | 2015-10-06 | 2016-03-03
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | SANDHBFDR | SANDY ER FOR FDR 18TH TO 25TH STREET | 3 | CONSTRUCTION START | 2025-06-29 | 2027-06-28 | 2016-03-04 | 2020-03-02
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | SANDHBFDR | SANDY ER FOR FDR 18TH TO 25TH STREET | 5 | CONSTRUCTION START | 2025-06-29 | 2027-06-28 | 2020-03-03 | 2022-03-02
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | SANDHW27 | Montgomery to 15th Street - Hurricane Sandy | 1 | DEVELOP SCOPE | 2019-06-30 | 2019-09-27 | 2018-08-02 | 2021-01-13
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | SANDHW27 | Montgomery to 15th Street - Hurricane Sandy | 2 | PRELIMINARY DESIGN | 2019-09-28 | 2020-01-25 | 2021-06-30 | 2021-10-04
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | SANDHW27 | Montgomery to 15th Street - Hurricane Sandy | 3 | FINAL DESIGN | 2020-01-26 | 2020-07-23 | 2021-03-25 | 2021-09-20
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | SANDHW27 | Montgomery to 15th Street - Hurricane Sandy | 4 | BID AWARD AND REGISTER CONTRCT | 2020-07-24 | 2020-10-21 | 2023-08-02 | 2024-01-06
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | SANDHW27 | Montgomery to 15th Street - Hurricane Sandy | 5 | CONSTRUCTION TO 25% | 2020-10-22 | 2021-02-18 | 2024-01-07 | 2024-05-05
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | SANDHW27 | Montgomery to 15th Street - Hurricane Sandy | 6 | CONSTRUCTION TO 50% | 2021-02-19 | 2021-06-18 | 2024-01-13 | 2024-06-13
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | SANDHW27 | Montgomery to 15th Street - Hurricane Sandy | 7 | CONSTRUCTION TO 75% | 2021-06-19 | 2021-10-16 | 2024-06-14 | 2024-11-19
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | SANDHW27 | Montgomery to 15th Street - Hurricane Sandy | 8 | ORIGINAL EQUIP & FURNISHING | 2021-10-17 | 2022-01-14 | 2024-11-20 | 2025-02-17
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | SANDHW27 | Montgomery to 15th Street - Hurricane Sandy | 9 | SUBSTANTIAL COMPLETION | 2022-01-15 | 2022-03-15 | 2025-02-18 | 2025-04-18
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | SANDHW27 | Montgomery to 15th Street - Hurricane Sandy | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-16 | 2022-04-14 | 2025-04-19 | 2027-06-30
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TF50316 | Decor Historic lg on W13th St, from 7th Ave to XMA418.30A | 1 | BID AWARD AND REGISTER CONTRCT | 2019-06-30 | 2019-06-30 | 2019-06-30 | 2019-06-30
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TF50316 | Decor Historic lg on W13th St, from 7th Ave to XMA418.30A | 2 | CONSTRUCTION START | 2019-07-01 | 2019-08-14 | 2019-07-01 | 2019-08-14
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TF50316 | Decor Historic lg on W13th St, from 7th Ave to XMA418.30A | 3 | CONSTRUCTION COMPLETION | 2019-08-15 | 2021-03-06 | 2019-08-15 | 2021-03-06
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFCPARKLG | Central Park Light Infrastructure | 1 | BID AWARD AND REGISTER CONTRCT | 2015-06-01 | 2015-06-01 | 2020-03-03 | 2020-04-30
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFCPARKLG | Central Park Light Infrastructure | 2 | CONSTRUCTION START | 2015-06-02 | 2015-07-16 | 2020-05-20 | 2020-05-20
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFCPARKLG | Central Park Light Infrastructure | 3 | CONSTRUCTION COMPLETION | 2015-07-17 | 2017-02-05 | 2021-05-25 | 2023-06-30
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503-20 | DOWNTOWN ALLIANCE-HISTORIC LIGHTPOLES | 1 | BID AWARD AND REGISTER CONTRCT | 2009-06-01 | 2009-06-01 | 2020-06-01 | 2020-06-01
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503-20 | DOWNTOWN ALLIANCE-HISTORIC LIGHTPOLES | 2 | CONSTRUCTION START | 2009-06-02 | 2009-07-16 | 2020-06-02 | 2020-07-16
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503-20 | DOWNTOWN ALLIANCE-HISTORIC LIGHTPOLES | 3 | CONSTRUCTION COMPLETION | 2009-07-17 | 2011-02-06 | 2020-07-17 | 2024-02-06
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M24 | FLATIRON DISTINCTIVE LIGHTING ALONG 23rd ST. 3rd to 6th AV. | 3 | CONSTRUCTION COMPLETION | 2011-08-15 | 2013-03-06 | 2014-08-15 | 2016-03-06
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M27 | REPLACE AND INSTALL ST LG IN FASHION CENTER BUSINESS IMPRV | 3 | CONSTRUCTION COMPLETION | 2015-07-17 | 2017-02-05 | 2015-07-17 | 2017-02-05
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M29 | Second Avenue Street lights | 1 | DEVELOP SCOPE | 2018-06-30 | 2018-09-27 | 2018-06-30 | 2018-09-27
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M29 | Second Avenue Street lights | 2 | PRELIMINARY DESIGN | 2018-09-28 | 2019-01-25 | 2018-09-28 | 2019-01-25
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M29 | Second Avenue Street lights | 3 | FINAL DESIGN | 2019-01-26 | 2019-07-24 | 2019-01-26 | 2019-07-24
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M29 | Second Avenue Street lights | 4 | BID AWARD AND REGISTER CONTRCT | 2019-07-25 | 2019-10-22 | 2019-07-25 | 2019-10-22
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M29 | Second Avenue Street lights | 5 | CONSTRUCTION TO 25% | 2019-10-23 | 2020-02-19 | 2019-10-23 | 2020-02-19
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M29 | Second Avenue Street lights | 6 | CONSTRUCTION TO 50% | 2020-02-20 | 2020-06-18 | 2020-02-20 | 2020-06-18
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M29 | Second Avenue Street lights | 7 | CONSTRUCTION TO 75% | 2020-06-19 | 2020-10-16 | 2020-06-19 | 2020-10-16
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M29 | Second Avenue Street lights | 8 | ORIGINAL EQUIP & FURNISHING | 2020-10-17 | 2021-01-14 | 2020-10-17 | 2021-01-14
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M29 | Second Avenue Street lights | 9 | SUBSTANTIAL COMPLETION | 2021-01-15 | 2021-03-15 | 2021-01-15 | 2021-03-15
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M29 | Second Avenue Street lights | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-16 | 2021-04-14 | 2021-03-16 | 2024-04-14
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M30 | Garment District street light | 1 | DEVELOP SCOPE | 2018-06-30 | 2018-09-27 | 2018-06-30 | 2018-09-27
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M30 | Garment District street light | 2 | PRELIMINARY DESIGN | 2018-09-28 | 2019-01-25 | 2018-09-28 | 2019-01-25
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M30 | Garment District street light | 3 | FINAL DESIGN | 2019-01-26 | 2019-07-24 | 2019-01-26 | 2019-07-24
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M30 | Garment District street light | 4 | BID AWARD AND REGISTER CONTRCT | 2019-07-25 | 2019-10-22 | 2019-07-25 | 2019-10-22
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M30 | Garment District street light | 5 | CONSTRUCTION TO 25% | 2019-10-23 | 2020-02-19 | 2019-10-23 | 2020-02-19
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M30 | Garment District street light | 6 | CONSTRUCTION TO 50% | 2020-02-20 | 2020-06-18 | 2020-02-20 | 2020-06-18
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M30 | Garment District street light | 7 | CONSTRUCTION TO 75% | 2020-06-19 | 2020-10-16 | 2020-06-19 | 2020-10-16
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M30 | Garment District street light | 8 | ORIGINAL EQUIP & FURNISHING | 2020-10-17 | 2021-01-14 | 2020-10-17 | 2021-01-14
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M30 | Garment District street light | 9 | SUBSTANTIAL COMPLETION | 2021-01-15 | 2021-03-15 | 2021-01-15 | 2021-03-15
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M30 | Garment District street light | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-16 | 2021-04-14 | 2021-03-16 | 2024-04-14
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M31 | Historic St lg on 11th St and on 12th St, Manhattan | 1 | DEVELOP SCOPE | 2018-06-30 | 2018-09-27 | 2018-06-30 | 2018-09-27
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M31 | Historic St lg on 11th St and on 12th St, Manhattan | 2 | PRELIMINARY DESIGN | 2018-09-28 | 2019-01-25 | 2018-09-28 | 2019-01-25
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M31 | Historic St lg on 11th St and on 12th St, Manhattan | 3 | FINAL DESIGN | 2019-01-26 | 2019-07-24 | 2019-01-26 | 2019-07-24
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M31 | Historic St lg on 11th St and on 12th St, Manhattan | 4 | BID AWARD AND REGISTER CONTRCT | 2019-07-25 | 2019-10-22 | 2019-07-25 | 2019-10-22
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M31 | Historic St lg on 11th St and on 12th St, Manhattan | 5 | CONSTRUCTION TO 25% | 2019-10-23 | 2020-02-19 | 2019-10-23 | 2020-02-19
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M31 | Historic St lg on 11th St and on 12th St, Manhattan | 6 | CONSTRUCTION TO 50% | 2020-02-20 | 2020-06-18 | 2020-02-20 | 2020-06-18
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M31 | Historic St lg on 11th St and on 12th St, Manhattan | 7 | CONSTRUCTION TO 75% | 2020-06-19 | 2020-10-16 | 2020-06-19 | 2020-10-16
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M31 | Historic St lg on 11th St and on 12th St, Manhattan | 8 | ORIGINAL EQUIP & FURNISHING | 2020-10-17 | 2021-01-14 | 2020-10-17 | 2021-01-14
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M31 | Historic St lg on 11th St and on 12th St, Manhattan | 9 | SUBSTANTIAL COMPLETION | 2021-01-15 | 2021-03-15 | 2021-01-15 | 2021-03-15
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M31 | Historic St lg on 11th St and on 12th St, Manhattan | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-16 | 2021-04-14 | 2021-03-16 | 2024-04-14
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M33 | GREENWICH VILLAGE DECORATIVE LIGHTING | 1 | DEVELOP SCOPE | 2017-06-30 | 2017-09-27 | 2018-06-30 | 2018-09-27
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M33 | GREENWICH VILLAGE DECORATIVE LIGHTING | 2 | PRELIMINARY DESIGN | 2017-09-28 | 2018-01-25 | 2018-09-28 | 2019-01-25
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M33 | GREENWICH VILLAGE DECORATIVE LIGHTING | 3 | FINAL DESIGN | 2018-01-26 | 2018-07-24 | 2019-01-26 | 2019-07-24
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M33 | GREENWICH VILLAGE DECORATIVE LIGHTING | 4 | BID AWARD AND REGISTER CONTRCT | 2018-07-25 | 2018-10-22 | 2019-07-25 | 2019-10-22
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M33 | GREENWICH VILLAGE DECORATIVE LIGHTING | 5 | CONSTRUCTION TO 25% | 2018-10-23 | 2019-02-19 | 2019-10-23 | 2020-02-19
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M33 | GREENWICH VILLAGE DECORATIVE LIGHTING | 6 | CONSTRUCTION TO 50% | 2019-02-20 | 2019-06-19 | 2020-02-20 | 2020-06-18
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M33 | GREENWICH VILLAGE DECORATIVE LIGHTING | 7 | CONSTRUCTION TO 75% | 2019-06-20 | 2019-10-17 | 2020-06-19 | 2020-10-16
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M33 | GREENWICH VILLAGE DECORATIVE LIGHTING | 8 | ORIGINAL EQUIP & FURNISHING | 2019-10-18 | 2020-01-15 | 2020-10-17 | 2021-01-14
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M33 | GREENWICH VILLAGE DECORATIVE LIGHTING | 9 | SUBSTANTIAL COMPLETION | 2020-01-16 | 2020-03-15 | 2021-01-15 | 2021-03-15
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M33 | GREENWICH VILLAGE DECORATIVE LIGHTING | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-03-16 | 2020-04-14 | 2021-03-16 | 2024-04-14
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M34 | Lg Poles on Crosby and Bleecker- NOHO, Manhattan | 1 | BID AWARD AND REGISTER CONTRCT | 2021-06-01 | 2021-06-01 | 2021-06-01 | 2021-06-01
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M34 | Lg Poles on Crosby and Bleecker- NOHO, Manhattan | 2 | CONSTRUCTION START | 2021-06-02 | 2021-06-20 | 2021-06-02 | 2021-06-20
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M34 | Lg Poles on Crosby and Bleecker- NOHO, Manhattan | 3 | CONSTRUCTION COMPLETION | 2021-06-21 | 2021-06-30 | 2021-06-21 | 2021-06-30
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFM503-09 | COOPER SQUARE(61 EAST 4TH STREET)STREETSCAPE-LIGHTING | 1 | BID AWARD AND REGISTER CONTRCT | 2009-06-30 | 2009-06-30 | 2022-06-30 | 2022-06-30
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFM503-09 | COOPER SQUARE(61 EAST 4TH STREET)STREETSCAPE-LIGHTING | 2 | CONSTRUCTION START | 2009-07-01 | 2009-08-14 | 2022-07-01 | 2022-08-14
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFM503-09 | COOPER SQUARE(61 EAST 4TH STREET)STREETSCAPE-LIGHTING | 3 | CONSTRUCTION COMPLETION | 2009-08-15 | 2011-03-07 | 2022-08-15 | 2024-03-06
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFM50311 | INSTALL S-POLE LIGHTING- VARIOUS STREETS WEST OF BROADWAY | 1 | BID AWARD AND REGISTER CONTRCT | 2009-06-01 | 2009-06-01 | 2020-06-01 | 2020-06-01
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFM50311 | INSTALL S-POLE LIGHTING- VARIOUS STREETS WEST OF BROADWAY | 2 | CONSTRUCTION START | 2009-06-02 | 2009-07-16 | 2020-06-02 | 2020-07-16
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFM50311 | INSTALL S-POLE LIGHTING- VARIOUS STREETS WEST OF BROADWAY | 3 | CONSTRUCTION COMPLETION | 2009-07-17 | 2011-02-06 | 2020-07-17 | 2024-02-06
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFM50316 | Frederick Douglas Blvd Street Lamps | 1 | BID AWARD AND REGISTER CONTRCT | 2013-06-30 | 2013-06-30 | 2022-06-30 | 2022-06-30
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFM50316 | Frederick Douglas Blvd Street Lamps | 2 | CONSTRUCTION START | 2013-07-01 | 2013-08-14 | 2022-07-01 | 2022-08-14
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFM50316 | Frederick Douglas Blvd Street Lamps | 3 | CONSTRUCTION COMPLETION | 2013-08-15 | 2015-03-07 | 2022-08-15 | 2024-03-06
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | W125STLG | W 125TH ST LG & SIGNAL-5TH AVE TO MORNINGSIDE AVE, MA2288.3 | 1 | BID AWARD AND REGISTER CONTRCT | 2012-06-30 | 2012-06-30 | 2022-06-30 | 2022-06-30
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | W125STLG | W 125TH ST LG & SIGNAL-5TH AVE TO MORNINGSIDE AVE, MA2288.3 | 2 | CONSTRUCTION START | 2012-07-01 | 2012-08-14 | 2022-07-01 | 2022-08-14
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | W125STLG | W 125TH ST LG & SIGNAL-5TH AVE TO MORNINGSIDE AVE, MA2288.3 | 3 | CONSTRUCTION COMPLETION | 2012-08-15 | 2014-03-07 | 2022-08-15 | 2024-03-06
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | W147LIGH | West 147th Street Sugar Hill Historical Street Lights | 1 | BID AWARD AND REGISTER CONTRCT | 2019-06-30 | 2019-06-30 | 2021-06-30 | 2021-06-30
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | W147LIGH | West 147th Street Sugar Hill Historical Street Lights | 2 | CONSTRUCTION START | 2019-07-01 | 2019-08-14 | 2021-07-01 | 2021-08-14
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | W147LIGH | West 147th Street Sugar Hill Historical Street Lights | 3 | CONSTRUCTION COMPLETION | 2019-08-15 | 2021-03-06 | 2021-08-15 | 2023-03-07
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | WHTGIRDS2 | Whitehall Ferry Terminal-Slip2 Girder Reconstruction | 1 | DEVELOP SCOPE | 2019-06-30 | 2020-06-28 | 2019-06-30 | 2020-06-28
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | WHTGIRDS2 | Whitehall Ferry Terminal-Slip2 Girder Reconstruction | 2 | DESIGN START | 2020-06-29 | 2022-06-28 | 2020-06-29 | 2022-06-28
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | WHTGIRDS2 | Whitehall Ferry Terminal-Slip2 Girder Reconstruction | 3 | CONSTRUCTION START | 2022-06-29 | 2024-06-27 | 2022-06-29 | 2024-06-27
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | WHTGIRDS3 | Whitehall Ferry Terminal-Slip3 Girder Reconstruction | 1 | DEVELOP SCOPE | 2019-06-30 | 2020-06-28 | 2019-06-30 | 2020-06-28
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | WHTGIRDS3 | Whitehall Ferry Terminal-Slip3 Girder Reconstruction | 2 | DESIGN START | 2020-06-29 | 2022-06-28 | 2020-06-29 | 2022-06-28
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | WHTGIRDS3 | Whitehall Ferry Terminal-Slip3 Girder Reconstruction | 3 | CONSTRUCTION START | 2022-06-29 | 2024-06-27 | 2022-06-29 | 2024-06-27
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | WHTLBRIDG | Whitehall Slips 1,2,3 Bridge Reconstruction | 1 | DEVELOP SCOPE | 2019-06-30 | 2020-06-28 | 2019-06-30 | 2020-06-28
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | WHTLBRIDG | Whitehall Slips 1,2,3 Bridge Reconstruction | 2 | DESIGN START | 2020-06-29 | 2022-06-28 | 2020-06-29 | 2022-06-28
20201123 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | WHTLBRIDG | Whitehall Slips 1,2,3 Bridge Reconstruction | 3 | CONSTRUCTION START | 2022-06-29 | 2024-06-27 | 2022-06-29 | 2024-06-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | ACEDPR408 | Centralized HVAC Controls | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | ACEDPR704 | DPR - BMS (Building Management System) INSTALLATION | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | ACEDPR704 | DPR - BMS (Building Management System) INSTALLATION | 2 | DESIGN | 2019-12-28 | 2021-06-24 | 2019-12-28 | 2021-06-24
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | ACEDPR704 | DPR - BMS (Building Management System) INSTALLATION | 3 | BID/ REGISTER CONTRACT | 2021-06-25 | 2022-03-21 | 2021-06-25 | 2022-03-21
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | ACEDPR704 | DPR - BMS (Building Management System) INSTALLATION | 4 | CONSTRUCTION | 2022-03-22 | 2023-09-17 | 2022-03-22 | 2023-09-17
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | ACEDPR704 | DPR - BMS (Building Management System) INSTALLATION | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-18 | 2024-09-16 | 2023-09-18 | 2024-09-16
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | NDF-DYMAN | NDF - Dyckman Sitting Area in Highbridge Park R/C | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | NDF-DYMAN | NDF - Dyckman Sitting Area in Highbridge Park R/C | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | NDF-DYMAN | NDF - Dyckman Sitting Area in Highbridge Park R/C | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | NDF-DYMAN | NDF - Dyckman Sitting Area in Highbridge Park R/C | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | NDF-DYMAN | NDF - Dyckman Sitting Area in Highbridge Park R/C | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | NDF-HRPCS | NDF Harlem River Park (M208D) - New Comfort Station | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | NDF-HRPCS | NDF Harlem River Park (M208D) - New Comfort Station | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | NDF-HRPCS | NDF Harlem River Park (M208D) - New Comfort Station | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | NDF-HRPCS | NDF Harlem River Park (M208D) - New Comfort Station | 4 | CONSTRUCTION | 2019-09-24 | 2021-03-21 | 2019-09-24 | 2021-03-21
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | NDF-HRPCS | NDF Harlem River Park (M208D) - New Comfort Station | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-22 | 2022-03-21 | 2021-03-22 | 2022-03-21
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | NDF-IWOOD | NDF - Inwood Hill Park Soccer Field #1 R/C | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | NDF-IWOOD | NDF - Inwood Hill Park Soccer Field #1 R/C | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | NDF-IWOOD | NDF - Inwood Hill Park Soccer Field #1 R/C | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | NDF-IWOOD | NDF - Inwood Hill Park Soccer Field #1 R/C | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | NDF-IWOOD | NDF - Inwood Hill Park Soccer Field #1 R/C | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | NDF-MKECS | NDF-Monsignor Kett Playground Comfort Station RC M199-119M | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | NDF-MKECS | NDF-Monsignor Kett Playground Comfort Station RC M199-119M | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | NDF-MKECS | NDF-Monsignor Kett Playground Comfort Station RC M199-119M | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | NDF-MKECS | NDF-Monsignor Kett Playground Comfort Station RC M199-119M | 4 | CONSTRUCTION | 2021-09-23 | 2023-03-21 | 2021-09-23 | 2023-03-21
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | NDF-MKECS | NDF-Monsignor Kett Playground Comfort Station RC M199-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-03-22 | 2024-03-20 | 2023-03-22 | 2024-03-20
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | NDF-MKETT | NDF - Monsignor Kett Playground R/C, M199-219M | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | NDF-MKETT | NDF - Monsignor Kett Playground R/C, M199-219M | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | NDF-MKETT | NDF - Monsignor Kett Playground R/C, M199-219M | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | NDF-MKETT | NDF - Monsignor Kett Playground R/C, M199-219M | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | NDF-MKETT | NDF - Monsignor Kett Playground R/C, M199-219M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-300EAST | East River Esplanade Projects - M108-119M | 1 | DEVELOP SCOPE | 2014-07-01 | 2014-09-28 | 2014-07-01 | 2017-09-28
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-300EAST | East River Esplanade Projects - M108-119M | 2 | DESIGN | 2014-09-29 | 2014-12-27 | 2017-09-29 | 2017-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-300EAST | East River Esplanade Projects - M108-119M | 3 | BID/ REGISTER CONTRACT | 2014-12-28 | 2015-03-27 | 2017-12-28 | 2018-03-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-300EAST | East River Esplanade Projects - M108-119M | 4 | CONSTRUCTION | 2015-03-28 | 2016-03-26 | 2018-03-28 | 2019-03-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-300EAST | East River Esplanade Projects - M108-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-27 | 2017-03-26 | 2019-03-28 | 2020-03-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-300ERES | East River Esplanade GLICK PK RC | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-300ERES | East River Esplanade GLICK PK RC | 2 | DESIGN | 2017-12-28 | 2019-06-20 | 2017-12-28 | 2019-06-20
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-300ERES | East River Esplanade GLICK PK RC | 3 | BID/ REGISTER CONTRACT | 2019-06-21 | 2020-03-16 | 2019-06-21 | 2020-03-16
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-300ERES | East River Esplanade GLICK PK RC | 4 | CONSTRUCTION | 2020-03-17 | 2021-09-07 | 2020-03-17 | 2021-09-07
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-300ERES | East River Esplanade GLICK PK RC | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-08 | 2022-09-07 | 2021-09-08 | 2022-09-07
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-300FDCG | Frederick Douglass Boulevard Community Garden Restoration | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-300FDCG | Frederick Douglass Boulevard Community Garden Restoration | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-300FDCG | Frederick Douglass Boulevard Community Garden Restoration | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-300FDCG | Frederick Douglass Boulevard Community Garden Restoration | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-300LMDC | LMDC-(BUNDLED) PROJECTS MG-703M | 1 | DEVELOP SCOPE | 2003-07-01 | 2003-07-06 | 2008-06-30 | 2008-11-05
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-300LMDC | LMDC-(BUNDLED) PROJECTS MG-703M | 2 | DESIGN | 2003-07-07 | 2003-07-17 | 2003-03-28 | 2003-07-17
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-300LMDC | LMDC-(BUNDLED) PROJECTS MG-703M | 3 | BID/ REGISTER CONTRACT | 2003-08-28 | 2003-10-15 | 2003-08-28 | 2004-01-15
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-300LMDC | LMDC-(BUNDLED) PROJECTS MG-703M | 4 | CONSTRUCTION | 2003-11-07 | 2004-11-17 | 2003-11-19 | 2005-11-01
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-300LMDC | LMDC-(BUNDLED) PROJECTS MG-703M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2004-11-18 | 2005-11-17 | 2005-11-02 | 2006-11-01
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-300ZO18 | Central Park Zoo - Sea Lion Exhibit Renovation | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-300ZO18 | Central Park Zoo - Sea Lion Exhibit Renovation | 2 | DESIGN | 2017-12-28 | 2019-03-27 | 2017-12-28 | 2019-03-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-300ZO18 | Central Park Zoo - Sea Lion Exhibit Renovation | 3 | BID/ REGISTER CONTRACT | 2019-03-28 | 2019-12-22 | 2019-03-28 | 2019-12-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-300ZO18 | Central Park Zoo - Sea Lion Exhibit Renovation | 4 | CONSTRUCTION | 2019-12-23 | 2020-12-21 | 2019-12-23 | 2020-12-21
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-300ZO18 | Central Park Zoo - Sea Lion Exhibit Renovation | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-12-22 | 2021-12-21 | 2020-12-22 | 2021-12-21
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-300ZO19 | Central Park Zoo - Roofs | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-300ZO19 | Central Park Zoo - Roofs | 2 | DESIGN | 2017-12-28 | 2019-03-27 | 2017-12-28 | 2019-03-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-300ZO19 | Central Park Zoo - Roofs | 3 | BID/ REGISTER CONTRACT | 2019-03-28 | 2019-12-22 | 2019-03-28 | 2019-12-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-300ZO19 | Central Park Zoo - Roofs | 4 | CONSTRUCTION | 2019-12-23 | 2020-12-21 | 2019-12-23 | 2020-12-21
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-300ZO19 | Central Park Zoo - Roofs | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-12-22 | 2021-12-21 | 2020-12-22 | 2021-12-21
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-300ZO20 | Central Park Zoo - Tractor and attachments | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-300ZO20 | Central Park Zoo - Tractor and attachments | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-300ZO20 | Central Park Zoo - Tractor and attachments | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-300ZO20 | Central Park Zoo - Tractor and attachments | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-300ZO20 | Central Park Zoo - Tractor and attachments | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301BPBP | BATTERY PARK BIKEWAY PERIMETER M005-111M (SUPERCEDES 308M) | 1 | DEVELOP SCOPE | 2004-07-01 | 2004-09-28 | 2007-07-01 | 2008-12-18
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301BPBP | BATTERY PARK BIKEWAY PERIMETER M005-111M (SUPERCEDES 308M) | 2 | DESIGN | 2004-09-29 | 2004-12-27 | 2008-12-19 | 2011-09-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301BPBP | BATTERY PARK BIKEWAY PERIMETER M005-111M (SUPERCEDES 308M) | 3 | BID/ REGISTER CONTRACT | 2004-12-28 | 2005-03-27 | 2012-01-20 | 2012-07-06
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301BPBP | BATTERY PARK BIKEWAY PERIMETER M005-111M (SUPERCEDES 308M) | 4 | CONSTRUCTION | 2005-03-28 | 2006-03-27 | 2012-09-17 | 2015-10-30
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301BPBP | BATTERY PARK BIKEWAY PERIMETER M005-111M (SUPERCEDES 308M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2006-03-28 | 2007-03-27 | 2015-10-30 | 2016-10-29
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301BPCG | Battery Park Coast Guard Memorial Relocation (M005-217M) | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301BPCG | Battery Park Coast Guard Memorial Relocation (M005-217M) | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2016-12-28 | 2017-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301BPCG | Battery Park Coast Guard Memorial Relocation (M005-217M) | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2017-12-28 | 2018-09-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301BPCG | Battery Park Coast Guard Memorial Relocation (M005-217M) | 4 | CONSTRUCTION | 2018-09-24 | 2019-09-23 | 2018-09-24 | 2019-09-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301BPCG | Battery Park Coast Guard Memorial Relocation (M005-217M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301BPOC | Battery Park Office convert to Comfort station M005 | 1 | DEVELOP SCOPE | 2012-07-01 | 2012-09-28 | 2012-07-01 | 2012-09-28
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301BPOC | Battery Park Office convert to Comfort station M005 | 2 | DESIGN | 2012-09-29 | 2012-12-27 | 2012-09-29 | 2012-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301BPOC | Battery Park Office convert to Comfort station M005 | 3 | BID/ REGISTER CONTRACT | 2012-12-28 | 2013-03-27 | 2012-12-28 | 2013-03-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301BPOC | Battery Park Office convert to Comfort station M005 | 4 | CONSTRUCTION | 2013-03-28 | 2014-03-27 | 2013-03-28 | 2014-03-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301BPOC | Battery Park Office convert to Comfort station M005 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-03-28 | 2015-03-27 | 2014-03-28 | 2015-03-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301BURL | LMDC-BURLING SLIP - IMAGINATION PLGD MG-41100-107M | 1 | DEVELOP SCOPE | 2006-07-04 | 2006-10-01 | 2006-07-04 | 2008-03-03
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301BURL | LMDC-BURLING SLIP - IMAGINATION PLGD MG-41100-107M | 2 | DESIGN | 2006-10-02 | 2006-12-30 | 2008-03-04 | 2008-09-19
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301BURL | LMDC-BURLING SLIP - IMAGINATION PLGD MG-41100-107M | 3 | BID/ REGISTER CONTRACT | 2006-12-31 | 2007-03-30 | 2008-11-20 | 2009-04-08
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301BURL | LMDC-BURLING SLIP - IMAGINATION PLGD MG-41100-107M | 4 | CONSTRUCTION | 2007-03-31 | 2008-03-29 | 2009-04-27 | 2010-07-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301BURL | LMDC-BURLING SLIP - IMAGINATION PLGD MG-41100-107M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-30 | 2009-03-29 | 2010-07-26 | 2011-07-25
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301EPPK | Elizabeth H. Berger Plaza, Manhattan | 1 | DEVELOP SCOPE | 2011-07-01 | 2011-09-28 | 2011-07-01 | 2012-10-05
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301EPPK | Elizabeth H. Berger Plaza, Manhattan | 2 | DESIGN | 2011-09-29 | 2011-12-27 | 2012-10-06 | 2019-04-07
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301EPPK | Elizabeth H. Berger Plaza, Manhattan | 3 | BID/ REGISTER CONTRACT | 2011-12-28 | 2012-03-26 | 2018-08-12 | 2019-04-25
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301EPPK | Elizabeth H. Berger Plaza, Manhattan | 4 | CONSTRUCTION | 2012-03-27 | 2013-03-26 | 2019-08-19 | 2021-01-15
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301EPPK | Elizabeth H. Berger Plaza, Manhattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-03-27 | 2014-03-26 | 2021-01-15 | 2022-01-15
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301PEAR | LMDC-PEARL ST PLGD MG-41000-107M | 1 | DEVELOP SCOPE | 2006-07-01 | 2006-09-28 | 2003-03-01 | 2003-09-05
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301PEAR | LMDC-PEARL ST PLGD MG-41000-107M | 2 | DESIGN | 2006-09-29 | 2006-12-27 | 2003-09-06 | 2009-07-02
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301PEAR | LMDC-PEARL ST PLGD MG-41000-107M | 3 | BID/ REGISTER CONTRACT | 2006-12-28 | 2007-03-27 | 2009-09-29 | 2011-04-06
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301PEAR | LMDC-PEARL ST PLGD MG-41000-107M | 4 | CONSTRUCTION | 2007-03-28 | 2008-03-26 | 2011-06-06 | 2012-05-31
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301PEAR | LMDC-PEARL ST PLGD MG-41000-107M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-27 | 2009-03-26 | 2012-05-31 | 2013-05-30
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301PECK | LMDC-PECK SLIP RECONSTRUCTION M167-106M | 1 | DEVELOP SCOPE | 2006-07-01 | 2006-09-28 | 2004-09-14 | 2004-12-12
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301PECK | LMDC-PECK SLIP RECONSTRUCTION M167-106M | 2 | DESIGN | 2006-09-29 | 2006-12-27 | 2006-12-29 | 2018-12-20
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301PECK | LMDC-PECK SLIP RECONSTRUCTION M167-106M | 3 | BID/ REGISTER CONTRACT | 2006-12-28 | 2007-03-27 | 2019-03-30 | 2019-05-25
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301PECK | LMDC-PECK SLIP RECONSTRUCTION M167-106M | 4 | CONSTRUCTION | 2007-03-28 | 2008-03-26 | 2019-08-30 | 2020-08-29
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301PECK | LMDC-PECK SLIP RECONSTRUCTION M167-106M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-27 | 2009-03-26 | 2020-08-30 | 2021-08-29
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-302AIDM | NYC AIDS Memorial -- Capital Refurbishment to Memorial | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2020-01-20
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-302AIDM | NYC AIDS Memorial -- Capital Refurbishment to Memorial | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2020-01-21 | 2021-04-20
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-302AIDM | NYC AIDS Memorial -- Capital Refurbishment to Memorial | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2020-12-28 | 2021-09-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-302AIDM | NYC AIDS Memorial -- Capital Refurbishment to Memorial | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2021-09-24 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-302AIDM | NYC AIDS Memorial -- Capital Refurbishment to Memorial | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2022-09-23 | 2023-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-302CJSC | CORPORAL JOHN A SERAVALLI PLGD CS RC M237-116M | 1 | DEVELOP SCOPE | 2012-07-01 | 2012-09-28 | 2012-07-01 | 2014-10-17
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-302CJSC | CORPORAL JOHN A SERAVALLI PLGD CS RC M237-116M | 2 | DESIGN | 2012-09-29 | 2012-12-27 | 2014-10-18 | 2016-08-01
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-302CJSC | CORPORAL JOHN A SERAVALLI PLGD CS RC M237-116M | 3 | BID/ REGISTER CONTRACT | 2012-12-28 | 2013-03-27 | 2016-08-02 | 2017-05-02
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-302CJSC | CORPORAL JOHN A SERAVALLI PLGD CS RC M237-116M | 4 | CONSTRUCTION | 2013-03-28 | 2014-03-27 | 2017-05-03 | 2018-05-03
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-302CJSC | CORPORAL JOHN A SERAVALLI PLGD CS RC M237-116M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-03-28 | 2015-03-27 | 2018-05-04 | 2019-05-03
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-302DPCA | DESALVIO PLGD RECON - ADULT USE & KID PLAY AREAS M218 | 1 | DEVELOP SCOPE | 2011-07-01 | 2011-09-28 | 2011-07-01 | 2013-10-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-302DPCA | DESALVIO PLGD RECON - ADULT USE & KID PLAY AREAS M218 | 2 | DESIGN | 2011-09-29 | 2011-12-27 | 2013-10-22 | 2015-06-30
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-302DPCA | DESALVIO PLGD RECON - ADULT USE & KID PLAY AREAS M218 | 3 | BID/ REGISTER CONTRACT | 2011-12-28 | 2012-03-26 | 2016-03-03 | 2016-12-13
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-302DPCA | DESALVIO PLGD RECON - ADULT USE & KID PLAY AREAS M218 | 4 | CONSTRUCTION | 2012-03-27 | 2013-03-26 | 2017-07-17 | 2019-02-14
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-302DPCA | DESALVIO PLGD RECON - ADULT USE & KID PLAY AREAS M218 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-03-27 | 2014-03-26 | 2019-02-15 | 2020-02-14
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-302DRYD | DRY DOCK PLAYGROUND RECON M270-110M | 1 | DEVELOP SCOPE | 2009-07-01 | 2009-09-28 | 2009-07-01 | 2010-11-16
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-302DRYD | DRY DOCK PLAYGROUND RECON M270-110M | 2 | DESIGN | 2009-09-29 | 2009-12-27 | 2010-11-17 | 2013-02-03
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-302DRYD | DRY DOCK PLAYGROUND RECON M270-110M | 3 | BID/ REGISTER CONTRACT | 2009-12-28 | 2010-03-27 | 2014-05-15 | 2014-11-10
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-302DRYD | DRY DOCK PLAYGROUND RECON M270-110M | 4 | CONSTRUCTION | 2010-03-28 | 2011-03-27 | 2015-04-06 | 2015-12-16
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-302DRYD | DRY DOCK PLAYGROUND RECON M270-110M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2011-03-28 | 2012-03-26 | 2015-12-17 | 2016-12-16
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-302GLAF | DEP Shaft Site -- Grand & Lafayette Streets | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2017-10-30
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-302GLAF | DEP Shaft Site -- Grand & Lafayette Streets | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2017-10-31 | 2019-10-25
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-302GLAF | DEP Shaft Site -- Grand & Lafayette Streets | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2020-06-25 | 2020-08-30
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-302GLAF | DEP Shaft Site -- Grand & Lafayette Streets | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2020-09-01 | 2021-08-31
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-302GLAF | DEP Shaft Site -- Grand & Lafayette Streets | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2021-09-01 | 2022-08-31
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-302HUHO | DEP shaft site 28B - Hudson and West Houston | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-302HUHO | DEP shaft site 28B - Hudson and West Houston | 2 | DESIGN | 2017-12-28 | 2019-03-27 | 2017-12-28 | 2019-03-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-302HUHO | DEP shaft site 28B - Hudson and West Houston | 3 | BID/ REGISTER CONTRACT | 2019-03-28 | 2019-12-22 | 2019-03-28 | 2019-12-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-302HUHO | DEP shaft site 28B - Hudson and West Houston | 4 | CONSTRUCTION | 2019-12-23 | 2020-12-21 | 2019-12-23 | 2020-12-21
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-302HUHO | DEP shaft site 28B - Hudson and West Houston | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-12-22 | 2021-12-21 | 2020-12-22 | 2021-12-21
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-302MHSA | DEP Shaft Site 31B at Bowery and East 4th Street | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-302MHSA | DEP Shaft Site 31B at Bowery and East 4th Street | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-302MHSA | DEP Shaft Site 31B at Bowery and East 4th Street | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-302MHSA | DEP Shaft Site 31B at Bowery and East 4th Street | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-302MHSA | DEP Shaft Site 31B at Bowery and East 4th Street | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303ASRC | Al Smith Rec Cntr-replace a/c & new windows | 1 | DEVELOP SCOPE | 2014-07-01 | 2014-09-28 | 2014-07-01 | 2014-09-28
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303ASRC | Al Smith Rec Cntr-replace a/c & new windows | 2 | DESIGN | 2014-09-29 | 2014-12-27 | 2014-09-29 | 2014-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303ASRC | Al Smith Rec Cntr-replace a/c & new windows | 3 | BID/ REGISTER CONTRACT | 2014-12-28 | 2015-03-27 | 2014-12-28 | 2015-03-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303ASRC | Al Smith Rec Cntr-replace a/c & new windows | 4 | CONSTRUCTION | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2016-03-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303ASRC | Al Smith Rec Cntr-replace a/c & new windows | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303BPCS | Baruch Playground C/S Renovations M165A-116M | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2015-12-09
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303BPCS | Baruch Playground C/S Renovations M165A-116M | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2015-12-10 | 2016-03-08
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303BPCS | Baruch Playground C/S Renovations M165A-116M | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2016-03-09 | 2017-10-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303BPCS | Baruch Playground C/S Renovations M165A-116M | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2017-10-28 | 2018-10-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303BPCS | Baruch Playground C/S Renovations M165A-116M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2018-10-28 | 2019-10-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303CRH2 | Corlears Hook Playground, Manhattan | 1 | DEVELOP SCOPE | 2020-07-01 | 2020-12-27 | 2020-07-01 | 2020-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303CRH2 | Corlears Hook Playground, Manhattan | 2 | DESIGN | 2020-12-28 | 2021-12-27 | 2020-12-28 | 2021-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303CRH2 | Corlears Hook Playground, Manhattan | 3 | BID/ REGISTER CONTRACT | 2021-12-28 | 2022-09-23 | 2021-12-28 | 2022-09-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303CRH2 | Corlears Hook Playground, Manhattan | 4 | CONSTRUCTION | 2022-09-24 | 2023-09-23 | 2022-09-24 | 2023-09-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303CRH2 | Corlears Hook Playground, Manhattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-24 | 2024-09-22 | 2023-09-24 | 2024-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303CRHP | Corlear's Hook Park- Dod Run, M017-118M | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2015-09-28
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303CRHP | Corlear's Hook Park- Dod Run, M017-118M | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2015-09-29 | 2015-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303CRHP | Corlear's Hook Park- Dod Run, M017-118M | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2015-12-28 | 2016-03-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303CRHP | Corlear's Hook Park- Dod Run, M017-118M | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2019-09-30 | 2020-09-29
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303CRHP | Corlear's Hook Park- Dod Run, M017-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2020-09-30 | 2021-09-29
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303ERBH | EAST RIVER PK - FIRE BOAT HOUSE PARTIAL RECON M144-204M/504M | 4 | CONSTRUCTION | 2007-03-28 | 2008-03-26 | 2007-03-28 | 2008-03-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303ERBH | EAST RIVER PK - FIRE BOAT HOUSE PARTIAL RECON M144-204M/504M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-27 | 2009-03-26 | 2008-03-27 | 2011-11-30
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303ERSF | ERP - E 6TH ST SOCCER FLD NEW TURF M144-214m | 1 | DEVELOP SCOPE | 2011-07-01 | 2011-09-28 | 2011-07-01 | 2013-11-13
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303ERSF | ERP - E 6TH ST SOCCER FLD NEW TURF M144-214m | 2 | DESIGN | 2011-09-29 | 2011-12-27 | 2013-11-14 | 2016-11-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303ERSF | ERP - E 6TH ST SOCCER FLD NEW TURF M144-214m | 3 | BID/ REGISTER CONTRACT | 2011-12-28 | 2012-03-26 | 2017-02-28 | 2017-07-19
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303ERSF | ERP - E 6TH ST SOCCER FLD NEW TURF M144-214m | 4 | CONSTRUCTION | 2012-03-27 | 2013-03-26 | 2017-09-11 | 2018-09-07
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303ERSF | ERP - E 6TH ST SOCCER FLD NEW TURF M144-214m | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-03-27 | 2014-03-26 | 2018-09-08 | 2019-09-07
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303ERWE | ERP-Composting Facility & Wetland R/C M144-116M | 1 | DEVELOP SCOPE | 2014-07-01 | 2014-09-28 | 2010-09-25 | 2015-07-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303ERWE | ERP-Composting Facility & Wetland R/C M144-116M | 2 | DESIGN | 2014-09-29 | 2014-12-27 | 2015-07-24 | 2022-07-12
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303ERWE | ERP-Composting Facility & Wetland R/C M144-116M | 3 | BID/ REGISTER CONTRACT | 2014-12-28 | 2015-03-27 | 2019-02-15 | 2019-06-01
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303ERWE | ERP-Composting Facility & Wetland R/C M144-116M | 4 | CONSTRUCTION | 2015-03-28 | 2016-03-26 | 2019-06-20 | 2020-06-19
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303ERWE | ERP-Composting Facility & Wetland R/C M144-116M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-27 | 2017-03-26 | 2020-06-10 | 2021-06-19
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303HFFA | Hamilton Fish Rec. Center: Fire Alarm Reconstruction | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303HFFA | Hamilton Fish Rec. Center: Fire Alarm Reconstruction | 2 | DESIGN | 2019-12-28 | 2021-12-26 | 2019-12-28 | 2021-12-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303HFFA | Hamilton Fish Rec. Center: Fire Alarm Reconstruction | 3 | BID/ REGISTER CONTRACT | 2021-12-27 | 2022-09-22 | 2021-12-27 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303HFFA | Hamilton Fish Rec. Center: Fire Alarm Reconstruction | 4 | CONSTRUCTION | 2022-09-23 | 2025-09-21 | 2022-09-23 | 2025-09-21
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303HFFA | Hamilton Fish Rec. Center: Fire Alarm Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-09-22 | 2027-09-21 | 2025-09-22 | 2027-09-21
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303HFRC | Hamilton Fish Rec.Ctr-replace roof & alarm system | 1 | DEVELOP SCOPE | 2014-07-01 | 2014-09-28 | 2014-07-01 | 2014-09-28
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303HFRC | Hamilton Fish Rec.Ctr-replace roof & alarm system | 2 | DESIGN | 2014-09-29 | 2014-12-27 | 2014-09-29 | 2014-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303HFRC | Hamilton Fish Rec.Ctr-replace roof & alarm system | 3 | BID/ REGISTER CONTRACT | 2014-12-28 | 2015-03-27 | 2014-12-28 | 2015-03-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303HFRC | Hamilton Fish Rec.Ctr-replace roof & alarm system | 4 | CONSTRUCTION | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2016-03-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303HFRC | Hamilton Fish Rec.Ctr-replace roof & alarm system | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303JACK | Jackie Robinson Rec Center Facades M014-114M | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2013-09-28
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303JACK | Jackie Robinson Rec Center Facades M014-114M | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2013-09-29 | 2013-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303JACK | Jackie Robinson Rec Center Facades M014-114M | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2013-12-28 | 2014-03-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303JACK | Jackie Robinson Rec Center Facades M014-114M | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2014-03-28 | 2015-03-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303JACK | Jackie Robinson Rec Center Facades M014-114M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2016-03-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303KLSQ | Kim Lau Square | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2015-09-28
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303KLSQ | Kim Lau Square | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2015-09-29 | 2015-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303KLSQ | Kim Lau Square | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2015-12-28 | 2016-03-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303KLSQ | Kim Lau Square | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303KLSQ | Kim Lau Square | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2017-03-27 | 2021-03-28
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303LGPK | CPI PH1 - LUTHER GULICK PARK - RECON WEST PORTION | 1 | DEVELOP SCOPE | 2009-07-01 | 2009-09-28 | 2009-07-01 | 2011-06-15
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303LGPK | CPI PH1 - LUTHER GULICK PARK - RECON WEST PORTION | 2 | DESIGN | 2009-09-29 | 2009-12-27 | 2011-06-16 | 2019-01-13
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303LGPK | CPI PH1 - LUTHER GULICK PARK - RECON WEST PORTION | 3 | BID/ REGISTER CONTRACT | 2009-12-28 | 2010-03-27 | 2018-02-27 | 2019-01-14
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303LGPK | CPI PH1 - LUTHER GULICK PARK - RECON WEST PORTION | 4 | CONSTRUCTION | 2010-03-28 | 2011-03-27 | 2019-03-18 | 2020-09-12
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303LGPK | CPI PH1 - LUTHER GULICK PARK - RECON WEST PORTION | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2011-03-28 | 2012-03-26 | 2020-09-13 | 2021-09-12
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303MCKY | McKinley Playground renovation, M259-118M | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303MCKY | McKinley Playground renovation, M259-118M | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2016-12-28 | 2017-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303MCKY | McKinley Playground renovation, M259-118M | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2017-12-28 | 2018-09-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303MCKY | McKinley Playground renovation, M259-118M | 4 | CONSTRUCTION | 2018-09-24 | 2019-09-23 | 2018-09-24 | 2019-09-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303MCKY | McKinley Playground renovation, M259-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303SARD | S.D. Roosevelt Pk-plgd&restrooms(Bldg D) M105-107M,108M/208M | 1 | DEVELOP SCOPE | 2006-07-01 | 2006-09-28 | 2006-07-01 | 2008-03-21
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303SARD | S.D. Roosevelt Pk-plgd&restrooms(Bldg D) M105-107M,108M/208M | 2 | DESIGN | 2006-09-29 | 2006-12-27 | 2008-03-22 | 2008-04-01
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303SARD | S.D. Roosevelt Pk-plgd&restrooms(Bldg D) M105-107M,108M/208M | 3 | BID/ REGISTER CONTRACT | 2006-12-28 | 2007-03-27 | 2008-04-24 | 2009-04-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303SARD | S.D. Roosevelt Pk-plgd&restrooms(Bldg D) M105-107M,108M/208M | 4 | CONSTRUCTION | 2007-03-28 | 2008-03-26 | 2009-05-04 | 2010-05-28
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303SARD | S.D. Roosevelt Pk-plgd&restrooms(Bldg D) M105-107M,108M/208M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-27 | 2009-03-26 | 2010-05-29 | 2011-05-28
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303SDRB | Sara D. Roosevelt PK Store room convert to bathroom M105 | 1 | DEVELOP SCOPE | 2012-07-01 | 2012-09-28 | 2012-07-01 | 2016-06-01
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303SDRB | Sara D. Roosevelt PK Store room convert to bathroom M105 | 2 | DESIGN | 2012-09-29 | 2012-12-27 | 2016-06-02 | 2016-06-01
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303SDRB | Sara D. Roosevelt PK Store room convert to bathroom M105 | 3 | BID/ REGISTER CONTRACT | 2012-12-28 | 2013-03-27 | 2016-06-02 | 2016-06-01
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303SDRB | Sara D. Roosevelt PK Store room convert to bathroom M105 | 4 | CONSTRUCTION | 2013-03-28 | 2014-03-27 | 2016-06-02 | 2016-06-01
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303SDRB | Sara D. Roosevelt PK Store room convert to bathroom M105 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-03-28 | 2015-03-27 | 2016-06-02 | 2017-06-01
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303SDRP | Sara D. Roosevelt Park - Pathways, sidewalks, exterior walls | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2020-12-21
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303SDRP | Sara D. Roosevelt Park - Pathways, sidewalks, exterior walls | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2020-12-22 | 2022-03-21
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303SDRP | Sara D. Roosevelt Park - Pathways, sidewalks, exterior walls | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2022-03-22 | 2022-12-16
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303SDRP | Sara D. Roosevelt Park - Pathways, sidewalks, exterior walls | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2022-12-17 | 2023-12-16
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303SDRP | Sara D. Roosevelt Park - Pathways, sidewalks, exterior walls | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2023-12-17 | 2024-12-15
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303TPSQ | Tompkin's Square Park - Manhattan M088-119M | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303TPSQ | Tompkin's Square Park - Manhattan M088-119M | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303TPSQ | Tompkin's Square Park - Manhattan M088-119M | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303TPSQ | Tompkin's Square Park - Manhattan M088-119M | 4 | CONSTRUCTION | 2020-09-23 | 2022-03-21 | 2020-09-23 | 2022-03-21
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303TPSQ | Tompkin's Square Park - Manhattan M088-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-22 | 2023-03-21 | 2022-03-22 | 2023-03-21
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303TSPL | PWOB-Tompkins Square Plgr-R/c at Ave B/E7 | 1 | DEVELOP SCOPE | 2014-07-01 | 2014-09-28 | 2014-07-01 | 2014-09-28
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303TSPL | PWOB-Tompkins Square Plgr-R/c at Ave B/E7 | 2 | DESIGN | 2014-09-29 | 2014-12-27 | 2014-09-29 | 2017-05-31
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303TSPL | PWOB-Tompkins Square Plgr-R/c at Ave B/E7 | 3 | BID/ REGISTER CONTRACT | 2014-12-28 | 2015-03-27 | 2017-11-09 | 2018-07-12
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303TSPL | PWOB-Tompkins Square Plgr-R/c at Ave B/E7 | 4 | CONSTRUCTION | 2015-03-28 | 2016-03-26 | 2018-09-24 | 2019-09-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303TSPL | PWOB-Tompkins Square Plgr-R/c at Ave B/E7 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-27 | 2017-03-26 | 2019-09-24 | 2020-09-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-30420S2 | West 20th St. Park Construction, M402-116M, Manhattan | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-30420S2 | West 20th St. Park Construction, M402-116M, Manhattan | 2 | DESIGN | 2016-12-28 | 2018-06-20 | 2016-12-28 | 2018-06-20
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-30420S2 | West 20th St. Park Construction, M402-116M, Manhattan | 3 | BID/ REGISTER CONTRACT | 2018-06-21 | 2019-03-17 | 2018-06-21 | 2019-03-17
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-30420S2 | West 20th St. Park Construction, M402-116M, Manhattan | 4 | CONSTRUCTION | 2019-03-18 | 2020-09-07 | 2019-03-18 | 2020-09-07
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-30420S2 | West 20th St. Park Construction, M402-116M, Manhattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-08 | 2021-09-07 | 2020-09-08 | 2021-09-07
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-304CBBC | Chelsea Basketball Court Renovation, Manhattan | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-304CBBC | Chelsea Basketball Court Renovation, Manhattan | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-304CBBC | Chelsea Basketball Court Renovation, Manhattan | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-304CBBC | Chelsea Basketball Court Renovation, Manhattan | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-304CBBC | Chelsea Basketball Court Renovation, Manhattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-304CCMP | Clement Clarke Moore Pk R/c of sitting area | 1 | DEVELOP SCOPE | 2014-07-01 | 2014-09-28 | 2014-07-01 | 2015-07-10
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-304CCMP | Clement Clarke Moore Pk R/c of sitting area | 2 | DESIGN | 2014-09-29 | 2014-12-27 | 2015-07-11 | 2017-04-28
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-304CCMP | Clement Clarke Moore Pk R/c of sitting area | 3 | BID/ REGISTER CONTRACT | 2014-12-28 | 2015-03-27 | 2017-08-14 | 2018-04-11
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-304CCMP | Clement Clarke Moore Pk R/c of sitting area | 4 | CONSTRUCTION | 2015-03-28 | 2016-03-26 | 2018-07-23 | 2019-06-28
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-304CCMP | Clement Clarke Moore Pk R/c of sitting area | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-27 | 2017-03-26 | 2019-06-29 | 2020-06-28
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-304CRLB | CHELSEA REC CTR ROOF DECK, LOCKER RM & BTHRM M260-114M | 1 | DEVELOP SCOPE | 2010-07-01 | 2010-09-28 | 2010-07-01 | 2014-10-06
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-304CRLB | CHELSEA REC CTR ROOF DECK, LOCKER RM & BTHRM M260-114M | 2 | DESIGN | 2010-09-29 | 2010-12-27 | 2014-10-07 | 2014-10-06
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-304CRLB | CHELSEA REC CTR ROOF DECK, LOCKER RM & BTHRM M260-114M | 3 | BID/ REGISTER CONTRACT | 2010-12-28 | 2011-03-27 | 2014-10-07 | 2014-10-06
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-304CRLB | CHELSEA REC CTR ROOF DECK, LOCKER RM & BTHRM M260-114M | 4 | CONSTRUCTION | 2011-03-28 | 2012-03-26 | 2014-10-07 | 2014-10-06
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-304CRLB | CHELSEA REC CTR ROOF DECK, LOCKER RM & BTHRM M260-114M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-03-27 | 2013-03-26 | 2014-10-07 | 2015-10-06
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-304DWIT | De Witt Clinton Park- Staircase Recons, M022-118M | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-304DWIT | De Witt Clinton Park- Staircase Recons, M022-118M | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2016-12-28 | 2019-05-17
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-304DWIT | De Witt Clinton Park- Staircase Recons, M022-118M | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2019-10-15 | 2020-02-11
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-304DWIT | De Witt Clinton Park- Staircase Recons, M022-118M | 4 | CONSTRUCTION | 2018-09-24 | 2019-09-23 | 2020-02-12 | 2021-02-10
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-304DWIT | De Witt Clinton Park- Staircase Recons, M022-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-24 | 2020-09-22 | 2021-02-11 | 2022-02-10
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-304HELK | Hell's Kitchen Park -Surface Renovation, Manhattan | 1 | DEVELOP SCOPE | 2020-07-01 | 2020-12-27 | 2020-07-01 | 2020-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-304HELK | Hell's Kitchen Park -Surface Renovation, Manhattan | 2 | DESIGN | 2020-12-28 | 2021-12-27 | 2020-12-28 | 2021-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-304HELK | Hell's Kitchen Park -Surface Renovation, Manhattan | 3 | BID/ REGISTER CONTRACT | 2021-12-28 | 2022-09-23 | 2021-12-28 | 2022-09-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-304HELK | Hell's Kitchen Park -Surface Renovation, Manhattan | 4 | CONSTRUCTION | 2022-09-24 | 2023-09-23 | 2022-09-24 | 2023-09-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-304HELK | Hell's Kitchen Park -Surface Renovation, Manhattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-24 | 2024-09-22 | 2023-09-24 | 2024-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-304LRSQ | Little Red Square, Manhattan, MG-41350-115M | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2014-01-16
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-304LRSQ | Little Red Square, Manhattan, MG-41350-115M | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2014-01-17 | 2017-05-25
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-304LRSQ | Little Red Square, Manhattan, MG-41350-115M | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2017-09-18 | 2018-08-10
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-304LRSQ | Little Red Square, Manhattan, MG-41350-115M | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2019-03-04 | 2020-03-03
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-304LRSQ | Little Red Square, Manhattan, MG-41350-115M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2020-03-04 | 2021-03-04
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-304MPPR | Mathews-Palmer Plgr-R/C North Side of Pk (M154-114M) | 1 | DEVELOP SCOPE | 2012-07-01 | 2012-09-28 | 2012-07-01 | 2013-03-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-304MPPR | Mathews-Palmer Plgr-R/C North Side of Pk (M154-114M) | 2 | DESIGN | 2012-09-29 | 2012-12-27 | 2013-03-23 | 2016-07-25
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-304MPPR | Mathews-Palmer Plgr-R/C North Side of Pk (M154-114M) | 3 | BID/ REGISTER CONTRACT | 2012-12-28 | 2013-03-27 | 2016-10-17 | 2017-02-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-304MPPR | Mathews-Palmer Plgr-R/C North Side of Pk (M154-114M) | 4 | CONSTRUCTION | 2013-03-28 | 2014-03-27 | 2017-04-24 | 2018-04-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-304MPPR | Mathews-Palmer Plgr-R/C North Side of Pk (M154-114M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-03-28 | 2015-03-27 | 2018-04-24 | 2019-04-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-304PENN | Penn South Playground, Manhattan | 1 | DEVELOP SCOPE | 2020-07-01 | 2020-12-27 | 2020-07-01 | 2020-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-304PENN | Penn South Playground, Manhattan | 2 | DESIGN | 2020-12-28 | 2021-12-27 | 2020-12-28 | 2021-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-304PENN | Penn South Playground, Manhattan | 3 | BID/ REGISTER CONTRACT | 2021-12-28 | 2022-09-23 | 2021-12-28 | 2022-09-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-304PENN | Penn South Playground, Manhattan | 4 | CONSTRUCTION | 2022-09-24 | 2023-09-23 | 2022-09-24 | 2023-09-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-304PENN | Penn South Playground, Manhattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-24 | 2024-09-22 | 2023-09-24 | 2024-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-305MSEL | Madison Square Park Pavement Reconstruction Manhattan | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2019-03-18
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-305MSEL | Madison Square Park Pavement Reconstruction Manhattan | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2019-03-19 | 2020-04-10
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-305MSEL | Madison Square Park Pavement Reconstruction Manhattan | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2020-12-20 | 2021-01-04
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-305MSEL | Madison Square Park Pavement Reconstruction Manhattan | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2021-01-30 | 2022-01-31
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-305MSEL | Madison Square Park Pavement Reconstruction Manhattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2022-02-01 | 2023-01-31
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-305MSPK | Madison Square Park Improvements,Manhattan | 1 | DEVELOP SCOPE | 2020-07-01 | 2020-12-27 | 2020-07-01 | 2020-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-305MSPK | Madison Square Park Improvements,Manhattan | 2 | DESIGN | 2020-12-28 | 2021-12-27 | 2020-12-28 | 2021-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-305MSPK | Madison Square Park Improvements,Manhattan | 3 | BID/ REGISTER CONTRACT | 2021-12-28 | 2022-09-23 | 2021-12-28 | 2022-09-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-305MSPK | Madison Square Park Improvements,Manhattan | 4 | CONSTRUCTION | 2022-09-24 | 2023-09-23 | 2022-09-24 | 2023-09-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-305MSPK | Madison Square Park Improvements,Manhattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-24 | 2024-09-22 | 2023-09-24 | 2024-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-305UNIO | UNION SQUARE RECONSTRUCTION M089-198 | 1 | DEVELOP SCOPE | 1998-08-11 | 1998-09-30 | 1998-08-11 | 1998-09-30
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-305UNIO | UNION SQUARE RECONSTRUCTION M089-198 | 2 | DESIGN | 1998-05-25 | 2000-03-30 | 1998-05-25 | 2000-03-30
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-305UNIO | UNION SQUARE RECONSTRUCTION M089-198 | 3 | BID/ REGISTER CONTRACT | 2000-05-10 | 2000-10-03 | 2000-04-17 | 2000-10-03
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-305UNIO | UNION SQUARE RECONSTRUCTION M089-198 | 4 | CONSTRUCTION | 2000-10-02 | 2002-10-09 | 2000-10-04 | 2002-10-09
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-305UNIO | UNION SQUARE RECONSTRUCTION M089-198 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2002-10-10 | 2003-11-06 | 2002-10-10 | 2003-10-09
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306ALFA | Asser Levy Rec. Center: Fire Alarm Reconstruction | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306ALFA | Asser Levy Rec. Center: Fire Alarm Reconstruction | 2 | DESIGN | 2019-12-28 | 2021-12-26 | 2019-12-28 | 2021-12-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306ALFA | Asser Levy Rec. Center: Fire Alarm Reconstruction | 3 | BID/ REGISTER CONTRACT | 2021-12-27 | 2022-09-22 | 2021-12-27 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306ALFA | Asser Levy Rec. Center: Fire Alarm Reconstruction | 4 | CONSTRUCTION | 2022-09-23 | 2025-09-21 | 2022-09-23 | 2025-09-21
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306ALFA | Asser Levy Rec. Center: Fire Alarm Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-09-22 | 2027-09-21 | 2025-09-22 | 2027-09-21
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306APMU | Albano Playground Handball Court Multi-use Conve M265-117M | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2015-09-09
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306APMU | Albano Playground Handball Court Multi-use Conve M265-117M | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2015-09-10 | 2019-07-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306APMU | Albano Playground Handball Court Multi-use Conve M265-117M | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2017-12-12 | 2021-08-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306APMU | Albano Playground Handball Court Multi-use Conve M265-117M | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2021-08-28 | 2022-08-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306APMU | Albano Playground Handball Court Multi-use Conve M265-117M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2022-08-28 | 2028-01-01
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306ASEQ | Asser Levy Fitness Equipment, Manhattan | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306ASEQ | Asser Levy Fitness Equipment, Manhattan | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306ASEQ | Asser Levy Fitness Equipment, Manhattan | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306ASEQ | Asser Levy Fitness Equipment, Manhattan | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306ASEQ | Asser Levy Fitness Equipment, Manhattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306ASLV | Asser Levy Recreation Center | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2015-09-28
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306ASLV | Asser Levy Recreation Center | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2015-09-29 | 2015-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306ASLV | Asser Levy Recreation Center | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2015-12-28 | 2016-03-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306ASLV | Asser Levy Recreation Center | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306ASLV | Asser Levy Recreation Center | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2017-03-27 | 2018-03-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306GLIC | Glick Park | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306GLIC | Glick Park | 2 | DESIGN | 2017-12-28 | 2019-12-27 | 2017-12-28 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306GLIC | Glick Park | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306GLIC | Glick Park | 4 | CONSTRUCTION | 2020-09-23 | 2022-09-22 | 2020-09-23 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306GLIC | Glick Park | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306PETD | Peter Detmold Park, Manhattan | 1 | DEVELOP SCOPE | 2020-07-01 | 2020-12-27 | 2020-07-01 | 2020-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306PETD | Peter Detmold Park, Manhattan | 2 | DESIGN | 2020-12-28 | 2021-12-27 | 2020-12-28 | 2021-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306PETD | Peter Detmold Park, Manhattan | 3 | BID/ REGISTER CONTRACT | 2021-12-28 | 2022-09-23 | 2021-12-28 | 2022-09-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306PETD | Peter Detmold Park, Manhattan | 4 | CONSTRUCTION | 2022-09-24 | 2023-09-23 | 2022-09-24 | 2023-09-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306PETD | Peter Detmold Park, Manhattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-24 | 2024-09-22 | 2023-09-24 | 2024-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306STVA | St. Vartan Park - Manhattan | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306STVA | St. Vartan Park - Manhattan | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306STVA | St. Vartan Park - Manhattan | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306STVA | St. Vartan Park - Manhattan | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306STVA | St. Vartan Park - Manhattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306TRPL | Tramway Plaza Irrigation | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2014-02-12
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306TRPL | Tramway Plaza Irrigation | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2014-02-13 | 2020-12-15
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306TRPL | Tramway Plaza Irrigation | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2021-07-29 | 2021-11-20
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306TRPL | Tramway Plaza Irrigation | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2021-12-31 | 2022-12-30
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306TRPL | Tramway Plaza Irrigation | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2022-12-31 | 2023-12-30
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306TUDO | Tudor Grove Playground - Manhattan | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306TUDO | Tudor Grove Playground - Manhattan | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306TUDO | Tudor Grove Playground - Manhattan | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306TUDO | Tudor Grove Playground - Manhattan | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306TUDO | Tudor Grove Playground - Manhattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307BLOC | CPI PH2 - Bloomingdale Comfort Station (CONS) | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307BLOC | CPI PH2 - Bloomingdale Comfort Station (CONS) | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307BLOC | CPI PH2 - Bloomingdale Comfort Station (CONS) | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307BLOC | CPI PH2 - Bloomingdale Comfort Station (CONS) | 4 | CONSTRUCTION | 2019-09-24 | 2021-03-21 | 2019-09-24 | 2021-03-21
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307BLOC | CPI PH2 - Bloomingdale Comfort Station (CONS) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-22 | 2022-03-21 | 2021-03-22 | 2022-03-21
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307BLOP | CPI PH2 - Bloomingdale Playground (construction)- M238-217M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307BLOP | CPI PH2 - Bloomingdale Playground (construction)- M238-217M | 2 | DESIGN | 2017-12-28 | 2019-06-20 | 2017-12-28 | 2019-06-20
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307BLOP | CPI PH2 - Bloomingdale Playground (construction)- M238-217M | 3 | BID/ REGISTER CONTRACT | 2019-06-21 | 2020-03-16 | 2019-06-21 | 2020-03-16
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307BLOP | CPI PH2 - Bloomingdale Playground (construction)- M238-217M | 4 | CONSTRUCTION | 2020-03-17 | 2021-09-07 | 2020-03-17 | 2021-09-07
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307BLOP | CPI PH2 - Bloomingdale Playground (construction)- M238-217M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-08 | 2022-09-07 | 2021-09-08 | 2022-09-07
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307BMAP | BROADWAY MALLS - RECON & UPGRADE BROADWAY MALLS | 1 | DEVELOP SCOPE | 2012-07-01 | 2012-09-28 | 2012-07-01 | 2015-11-30
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307BMAP | BROADWAY MALLS - RECON & UPGRADE BROADWAY MALLS | 2 | DESIGN | 2012-09-29 | 2012-12-27 | 2015-12-01 | 2020-08-31
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307BMAP | BROADWAY MALLS - RECON & UPGRADE BROADWAY MALLS | 3 | BID/ REGISTER CONTRACT | 2012-12-28 | 2013-03-27 | 2017-12-13 | 2018-06-29
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307BMAP | BROADWAY MALLS - RECON & UPGRADE BROADWAY MALLS | 4 | CONSTRUCTION | 2013-03-28 | 2014-03-27 | 2018-08-13 | 2019-08-12
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307BMAP | BROADWAY MALLS - RECON & UPGRADE BROADWAY MALLS | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-03-28 | 2015-03-27 | 2019-08-13 | 2020-08-12
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307RPKS | RIVERSIDE PARK SOUTH - PHASE 5 M353-112M | 1 | DEVELOP SCOPE | 2012-09-13 | 2012-12-11 | 2012-09-13 | 2013-05-16
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307RPKS | RIVERSIDE PARK SOUTH - PHASE 5 M353-112M | 2 | DESIGN | 2012-12-12 | 2013-03-11 | 2013-05-17 | 2014-12-24
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307RPKS | RIVERSIDE PARK SOUTH - PHASE 5 M353-112M | 3 | BID/ REGISTER CONTRACT | 2013-03-12 | 2013-06-09 | 2015-06-26 | 2016-06-14
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307RPKS | RIVERSIDE PARK SOUTH - PHASE 5 M353-112M | 4 | CONSTRUCTION | 2013-06-10 | 2014-06-09 | 2016-08-29 | 2019-08-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307RPKS | RIVERSIDE PARK SOUTH - PHASE 5 M353-112M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-06-10 | 2015-06-09 | 2019-08-28 | 2020-08-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307RPPI | RVSD PK SOUTH-SHADE STRUCTURES, SOCCER FIELD, REC AREA M071 | 1 | DEVELOP SCOPE | 2012-07-01 | 2012-09-28 | 2012-07-01 | 2013-03-07
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307RPPI | RVSD PK SOUTH-SHADE STRUCTURES, SOCCER FIELD, REC AREA M071 | 2 | DESIGN | 2012-09-29 | 2012-12-27 | 2013-03-08 | 2018-11-21
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307RPPI | RVSD PK SOUTH-SHADE STRUCTURES, SOCCER FIELD, REC AREA M071 | 3 | BID/ REGISTER CONTRACT | 2012-12-28 | 2013-03-27 | 2018-11-22 | 2019-02-19
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307RPPI | RVSD PK SOUTH-SHADE STRUCTURES, SOCCER FIELD, REC AREA M071 | 4 | CONSTRUCTION | 2013-03-28 | 2014-03-27 | 2019-09-01 | 2020-08-31
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307RPPI | RVSD PK SOUTH-SHADE STRUCTURES, SOCCER FIELD, REC AREA M071 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-03-28 | 2015-03-27 | 2020-09-01 | 2021-08-31
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307RPSB | Riverside Park South Ph. 5 Building | 1 | DEVELOP SCOPE | 2012-07-01 | 2012-09-28 | 2012-07-01 | 2012-09-28
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307RPSB | Riverside Park South Ph. 5 Building | 2 | DESIGN | 2012-09-29 | 2012-12-27 | 2012-09-29 | 2017-02-17
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307RPSB | Riverside Park South Ph. 5 Building | 3 | BID/ REGISTER CONTRACT | 2012-12-28 | 2013-03-27 | 2019-01-05 | 2019-05-01
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307RPSB | Riverside Park South Ph. 5 Building | 4 | CONSTRUCTION | 2013-03-28 | 2014-03-27 | 2019-06-30 | 2020-06-29
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307RPSB | Riverside Park South Ph. 5 Building | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-03-28 | 2015-03-27 | 2019-06-30 | 2021-06-29
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307RPTH | Riverside Park RC Pathways 91st-95th Streets | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2016-01-11
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307RPTH | Riverside Park RC Pathways 91st-95th Streets | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2016-01-12 | 2017-06-28
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307RPTH | Riverside Park RC Pathways 91st-95th Streets | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2017-09-21 | 2018-04-24
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307RPTH | Riverside Park RC Pathways 91st-95th Streets | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2018-06-18 | 2019-06-17
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307RPTH | Riverside Park RC Pathways 91st-95th Streets | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2019-06-18 | 2020-06-17
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307RVSD | RIVERSIDE PK- CANTILEVER 83RD-91ST M071-297A | 1 | DEVELOP SCOPE | 1999-07-01 | 1999-09-28 | 1999-07-02 | 2005-01-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307RVSD | RIVERSIDE PK- CANTILEVER 83RD-91ST M071-297A | 2 | DESIGN | 1999-09-29 | 1999-12-27 | 2005-01-23 | 2007-04-05
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307RVSD | RIVERSIDE PK- CANTILEVER 83RD-91ST M071-297A | 3 | BID/ REGISTER CONTRACT | 1999-12-28 | 2000-03-26 | 2007-04-16 | 2007-07-25
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307RVSD | RIVERSIDE PK- CANTILEVER 83RD-91ST M071-297A | 4 | CONSTRUCTION | 2000-03-27 | 2001-03-26 | 2007-10-15 | 2010-05-07
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307RVSD | RIVERSIDE PK- CANTILEVER 83RD-91ST M071-297A | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2001-03-27 | 2002-03-26 | 2010-05-08 | 2011-05-07
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307SAPO | MATTHEW P. SAPOLIN PARK PLAYGROUND: PLAYGROUND EQUIPMENT | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307SAPO | MATTHEW P. SAPOLIN PARK PLAYGROUND: PLAYGROUND EQUIPMENT | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307SAPO | MATTHEW P. SAPOLIN PARK PLAYGROUND: PLAYGROUND EQUIPMENT | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307SAPO | MATTHEW P. SAPOLIN PARK PLAYGROUND: PLAYGROUND EQUIPMENT | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307SAPO | MATTHEW P. SAPOLIN PARK PLAYGROUND: PLAYGROUND EQUIPMENT | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307SOLB | Sol Bloom Playground Improvements, Manhattan | 1 | DEVELOP SCOPE | 2020-07-01 | 2020-12-27 | 2020-07-01 | 2020-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307SOLB | Sol Bloom Playground Improvements, Manhattan | 2 | DESIGN | 2020-12-28 | 2021-12-27 | 2020-12-28 | 2021-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307SOLB | Sol Bloom Playground Improvements, Manhattan | 3 | BID/ REGISTER CONTRACT | 2021-12-28 | 2022-09-23 | 2021-12-28 | 2022-09-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307SOLB | Sol Bloom Playground Improvements, Manhattan | 4 | CONSTRUCTION | 2022-09-24 | 2023-09-23 | 2022-09-24 | 2023-09-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307SOLB | Sol Bloom Playground Improvements, Manhattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-24 | 2024-09-22 | 2023-09-24 | 2024-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307STGR | PWOB-St. Gregory's Park Reconstruction (M301-114M) | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2015-10-05
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307STGR | PWOB-St. Gregory's Park Reconstruction (M301-114M) | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2015-10-06 | 2019-06-16
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307STGR | PWOB-St. Gregory's Park Reconstruction (M301-114M) | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2017-12-22 | 2018-07-11
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307STGR | PWOB-St. Gregory's Park Reconstruction (M301-114M) | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2018-08-20 | 2019-08-19
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307STGR | PWOB-St. Gregory's Park Reconstruction (M301-114M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2019-08-20 | 2020-08-19
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307TRDR | Theodore Roosevelt Park Dog Run Renovation | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2017-07-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307TRDR | Theodore Roosevelt Park Dog Run Renovation | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2017-07-28 | 2017-10-25
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307TRDR | Theodore Roosevelt Park Dog Run Renovation | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2019-01-04 | 2019-04-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307TRDR | Theodore Roosevelt Park Dog Run Renovation | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2019-04-25 | 2020-04-25
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307TRDR | Theodore Roosevelt Park Dog Run Renovation | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2020-04-26 | 2021-04-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308AG02 | Asphalt Green- Pool Filter Upgrades | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2015-09-28
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308AG02 | Asphalt Green- Pool Filter Upgrades | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2015-09-29 | 2015-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308AG02 | Asphalt Green- Pool Filter Upgrades | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2015-12-28 | 2016-03-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308AG02 | Asphalt Green- Pool Filter Upgrades | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2021-03-27 | 2022-03-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308AG02 | Asphalt Green- Pool Filter Upgrades | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2022-03-27 | 2023-03-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308AG03 | ASPHALT GREEN LOBBY EXPANSION & LOCKER UPGRADES | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308AG03 | ASPHALT GREEN LOBBY EXPANSION & LOCKER UPGRADES | 2 | DESIGN | 2016-12-28 | 2018-12-27 | 2016-12-28 | 2018-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308AG03 | ASPHALT GREEN LOBBY EXPANSION & LOCKER UPGRADES | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308AG03 | ASPHALT GREEN LOBBY EXPANSION & LOCKER UPGRADES | 4 | CONSTRUCTION | 2019-09-24 | 2022-09-22 | 2019-09-24 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308AG03 | ASPHALT GREEN LOBBY EXPANSION & LOCKER UPGRADES | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2024-09-21 | 2022-09-23 | 2024-09-21
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308AGDO | Ashphalt Green: Exterior Pedestrian Corridor, Manhattan | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308AGDO | Ashphalt Green: Exterior Pedestrian Corridor, Manhattan | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308AGDO | Ashphalt Green: Exterior Pedestrian Corridor, Manhattan | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308AGDO | Ashphalt Green: Exterior Pedestrian Corridor, Manhattan | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308AGDO | Ashphalt Green: Exterior Pedestrian Corridor, Manhattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308AGEE | Asphalt Green- Energy Efficiency, Manhattan | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308AGEE | Asphalt Green- Energy Efficiency, Manhattan | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308AGEE | Asphalt Green- Energy Efficiency, Manhattan | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308AGEE | Asphalt Green- Energy Efficiency, Manhattan | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308AGEE | Asphalt Green- Energy Efficiency, Manhattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308AGFB | ASPHALT GREEN BOILER M286-114M | 1 | DEVELOP SCOPE | 2012-07-01 | 2012-09-28 | 2012-07-01 | 2012-09-28
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308AGFB | ASPHALT GREEN BOILER M286-114M | 2 | DESIGN | 2012-09-29 | 2012-12-27 | 2012-09-29 | 2014-01-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308AGFB | ASPHALT GREEN BOILER M286-114M | 3 | BID/ REGISTER CONTRACT | 2012-12-28 | 2013-03-27 | 2014-05-25 | 2014-10-19
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308AGFB | ASPHALT GREEN BOILER M286-114M | 4 | CONSTRUCTION | 2013-03-28 | 2014-03-27 | 2013-08-23 | 2015-08-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308AGFB | ASPHALT GREEN BOILER M286-114M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-03-28 | 2015-03-27 | 2015-08-27 | 2016-08-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308AGMC | ASPHALT GREEN- MURPHY CENTER ELEVATION RESTORATION | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2013-12-28 | 2014-03-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308AGMC | ASPHALT GREEN- MURPHY CENTER ELEVATION RESTORATION | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2014-03-28 | 2015-03-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308AGMC | ASPHALT GREEN- MURPHY CENTER ELEVATION RESTORATION | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2019-12-30 | 2020-12-30
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308AGPF | Asphalt Green Pool Filtration | 1 | DEVELOP SCOPE | 2014-07-01 | 2014-09-28 | 2014-07-01 | 2014-09-28
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308AGPF | Asphalt Green Pool Filtration | 2 | DESIGN | 2014-09-29 | 2014-12-27 | 2014-09-29 | 2014-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308AGPF | Asphalt Green Pool Filtration | 3 | BID/ REGISTER CONTRACT | 2014-12-28 | 2015-03-27 | 2014-12-28 | 2015-03-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308AGPF | Asphalt Green Pool Filtration | 4 | CONSTRUCTION | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2016-03-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308AGPF | Asphalt Green Pool Filtration | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-27 | 2017-03-26 | 2019-12-30 | 2020-12-30
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308CSPG | Carl Schurz Playground Reconstruction | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308CSPG | Carl Schurz Playground Reconstruction | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2016-12-28 | 2017-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308CSPG | Carl Schurz Playground Reconstruction | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2017-12-28 | 2018-09-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308CSPG | Carl Schurz Playground Reconstruction | 4 | CONSTRUCTION | 2018-09-24 | 2019-09-23 | 2018-09-24 | 2019-09-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308CSPG | Carl Schurz Playground Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308EPOA | POA East River Esplanade Improvements, Manhattan | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308EPOA | POA East River Esplanade Improvements, Manhattan | 2 | DESIGN | 2018-12-28 | 2020-12-26 | 2018-12-28 | 2020-12-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308EPOA | POA East River Esplanade Improvements, Manhattan | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308EPOA | POA East River Esplanade Improvements, Manhattan | 4 | CONSTRUCTION | 2021-09-23 | 2023-09-22 | 2021-09-23 | 2023-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308EPOA | POA East River Esplanade Improvements, Manhattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-23 | 2024-09-21 | 2023-09-23 | 2024-09-21
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308EREI | ERP- East River Esplanade Improvements | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2017-05-08
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308EREI | ERP- East River Esplanade Improvements | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2017-05-09 | 2019-12-02
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308EREI | ERP- East River Esplanade Improvements | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2019-11-14 | 2020-04-15
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308EREI | ERP- East River Esplanade Improvements | 4 | CONSTRUCTION | 2018-09-24 | 2019-09-23 | 2020-07-15 | 2021-07-14
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308EREI | ERP- East River Esplanade Improvements | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-24 | 2020-09-22 | 2021-07-15 | 2022-07-14
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308ERP2 | East River Esplanade Stabilization And Reconstruction PHASE | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308ERP2 | East River Esplanade Stabilization And Reconstruction PHASE | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308ERP2 | East River Esplanade Stabilization And Reconstruction PHASE | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308ERP2 | East River Esplanade Stabilization And Reconstruction PHASE | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308ERP2 | East River Esplanade Stabilization And Reconstruction PHASE | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308ERP3 | EAST RIVER ESPLANADE PHASE 3+ | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308ERP3 | EAST RIVER ESPLANADE PHASE 3+ | 2 | DESIGN | 2018-12-28 | 2020-12-26 | 2018-12-28 | 2020-12-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308ERP3 | EAST RIVER ESPLANADE PHASE 3+ | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308ERP3 | EAST RIVER ESPLANADE PHASE 3+ | 4 | CONSTRUCTION | 2021-09-23 | 2023-09-22 | 2021-09-23 | 2023-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308ERP3 | EAST RIVER ESPLANADE PHASE 3+ | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-23 | 2024-09-21 | 2023-09-23 | 2024-09-21
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308GRA1 | GRACIE MANSION CHILLER RC M081 | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308GRA1 | GRACIE MANSION CHILLER RC M081 | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308GRA1 | GRACIE MANSION CHILLER RC M081 | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308GRA1 | GRACIE MANSION CHILLER RC M081 | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308GRA1 | GRACIE MANSION CHILLER RC M081 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308HNYL | 14 HONEY LOCUSTS PARK, Manhattan, M177-119M | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308HNYL | 14 HONEY LOCUSTS PARK, Manhattan, M177-119M | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308HNYL | 14 HONEY LOCUSTS PARK, Manhattan, M177-119M | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308HNYL | 14 HONEY LOCUSTS PARK, Manhattan, M177-119M | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308HNYL | 14 HONEY LOCUSTS PARK, Manhattan, M177-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308JJPB | JOHN JAY PARK BATHHOUSE RENOVATION M045-105M/405M | 3 | BID/ REGISTER CONTRACT | 2004-12-28 | 2005-03-27 | 2006-12-19 | 2007-05-21
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308JJPB | JOHN JAY PARK BATHHOUSE RENOVATION M045-105M/405M | 4 | CONSTRUCTION | 2005-03-28 | 2006-03-27 | 2007-09-24 | 2012-06-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308JJPB | JOHN JAY PARK BATHHOUSE RENOVATION M045-105M/405M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2006-03-28 | 2007-03-27 | 2012-06-23 | 2013-06-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308JJPK | John Jay Park Reconstruction, M045-118M | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2018-03-08
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308JJPK | John Jay Park Reconstruction, M045-118M | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2018-03-09 | 2019-03-31
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308JJPK | John Jay Park Reconstruction, M045-118M | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2019-04-01 | 2019-11-30
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308JJPK | John Jay Park Reconstruction, M045-118M | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2019-12-01 | 2020-11-30
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308JJPK | John Jay Park Reconstruction, M045-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2020-12-01 | 2021-11-30
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308MHM2 | MERCHANT HOUSE MUSEUM- EAST FACADE & SHUTTER RESTO M318 | 1 | DEVELOP SCOPE | 2011-07-01 | 2011-09-28 | 2011-07-01 | 2011-09-28
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308MHM2 | MERCHANT HOUSE MUSEUM- EAST FACADE & SHUTTER RESTO M318 | 2 | DESIGN | 2011-09-29 | 2011-12-27 | 2011-09-29 | 2011-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308MHM2 | MERCHANT HOUSE MUSEUM- EAST FACADE & SHUTTER RESTO M318 | 3 | BID/ REGISTER CONTRACT | 2011-12-28 | 2012-03-26 | 2011-12-28 | 2012-03-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308MHM2 | MERCHANT HOUSE MUSEUM- EAST FACADE & SHUTTER RESTO M318 | 4 | CONSTRUCTION | 2012-03-27 | 2013-03-26 | 2012-03-27 | 2013-03-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308MHM2 | MERCHANT HOUSE MUSEUM- EAST FACADE & SHUTTER RESTO M318 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-03-27 | 2014-03-26 | 2013-03-27 | 2014-03-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308SPCS | 24 Sycamores Park C/S Renovation M108-116M | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2013-09-28
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308SPCS | 24 Sycamores Park C/S Renovation M108-116M | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2013-09-29 | 2013-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308SPCS | 24 Sycamores Park C/S Renovation M108-116M | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2013-12-28 | 2014-03-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308SPCS | 24 Sycamores Park C/S Renovation M108-116M | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2014-03-28 | 2015-03-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308SPCS | 24 Sycamores Park C/S Renovation M108-116M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2016-03-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308STCP | St. Catherine's Park -- sportscoating iin the children's p | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308STCP | St. Catherine's Park -- sportscoating iin the children's p | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2020-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308STCP | St. Catherine's Park -- sportscoating iin the children's p | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2021-12-28 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308STCP | St. Catherine's Park -- sportscoating iin the children's p | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2022-09-23 | 2023-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308STCP | St. Catherine's Park -- sportscoating iin the children's p | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2023-09-23 | 2024-09-21
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309JRFA | Jackie Robinson Rec. Center: Fire Alarm Reconstruction | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309JRFA | Jackie Robinson Rec. Center: Fire Alarm Reconstruction | 2 | DESIGN | 2019-12-28 | 2021-12-26 | 2019-12-28 | 2021-12-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309JRFA | Jackie Robinson Rec. Center: Fire Alarm Reconstruction | 3 | BID/ REGISTER CONTRACT | 2021-12-27 | 2022-09-22 | 2021-12-27 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309JRFA | Jackie Robinson Rec. Center: Fire Alarm Reconstruction | 4 | CONSTRUCTION | 2022-09-23 | 2025-09-21 | 2022-09-23 | 2025-09-21
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309JRFA | Jackie Robinson Rec. Center: Fire Alarm Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-09-22 | 2027-09-21 | 2025-09-22 | 2027-09-21
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309JRRC | Jackie Robinson Recreation Center HVAC System Reconstruction | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309JRRC | Jackie Robinson Recreation Center HVAC System Reconstruction | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309JRRC | Jackie Robinson Recreation Center HVAC System Reconstruction | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309JRRC | Jackie Robinson Recreation Center HVAC System Reconstruction | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309JRRC | Jackie Robinson Recreation Center HVAC System Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309JSPL | Jacob Schiff Playground Reconstruction | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2015-09-28
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309JSPL | Jacob Schiff Playground Reconstruction | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2015-09-29 | 2015-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309JSPL | Jacob Schiff Playground Reconstruction | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2015-12-28 | 2016-03-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309JSPL | Jacob Schiff Playground Reconstruction | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309JSPL | Jacob Schiff Playground Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2017-03-27 | 2021-05-31
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309JSST | Jacob Schiff Park- Recons of Seating area, Manhattan | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309JSST | Jacob Schiff Park- Recons of Seating area, Manhattan | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309JSST | Jacob Schiff Park- Recons of Seating area, Manhattan | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309JSST | Jacob Schiff Park- Recons of Seating area, Manhattan | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309JSST | Jacob Schiff Park- Recons of Seating area, Manhattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309MOR2 | Morninside Pk- R/C of Plgr Phase 2 M056-116m | 1 | DEVELOP SCOPE | 2012-07-01 | 2012-09-28 | 2012-07-01 | 2015-10-19
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309MOR2 | Morninside Pk- R/C of Plgr Phase 2 M056-116m | 2 | DESIGN | 2012-09-29 | 2012-12-27 | 2015-10-20 | 2017-04-24
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309MOR2 | Morninside Pk- R/C of Plgr Phase 2 M056-116m | 3 | BID/ REGISTER CONTRACT | 2012-12-28 | 2013-03-27 | 2017-07-21 | 2017-12-13
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309MOR2 | Morninside Pk- R/C of Plgr Phase 2 M056-116m | 4 | CONSTRUCTION | 2013-03-28 | 2014-03-27 | 2018-03-05 | 2019-03-04
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309MOR2 | Morninside Pk- R/C of Plgr Phase 2 M056-116m | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-03-28 | 2015-03-27 | 2019-03-05 | 2020-03-04
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309MPMP | Morningside Park: Renovation of Middle Playground | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2017-07-20
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309MPMP | Morningside Park: Renovation of Middle Playground | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2017-07-21 | 2018-10-02
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309MPMP | Morningside Park: Renovation of Middle Playground | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2019-03-20 | 2019-10-28
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309MPMP | Morningside Park: Renovation of Middle Playground | 4 | CONSTRUCTION | 2018-09-24 | 2019-09-23 | 2019-12-09 | 2021-03-05
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309MPMP | Morningside Park: Renovation of Middle Playground | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-24 | 2020-09-22 | 2021-03-06 | 2022-03-05
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309RBUS | RVSD DR -TIEMANN PL TO 97TH ST | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2005-12-22 | 2015-07-15
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309RBUS | RVSD DR -TIEMANN PL TO 97TH ST | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2015-07-16 | 2027-02-12
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309RBUS | RVSD DR -TIEMANN PL TO 97TH ST | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2018-03-02 | 2019-01-25
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309RBUS | RVSD DR -TIEMANN PL TO 97TH ST | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2019-03-04 | 2020-05-31
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309RBUS | RVSD DR -TIEMANN PL TO 97TH ST | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2020-06-01 | 2021-05-31
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309RTIE | RVSD - TIEMAN PL TO 120TH STAIRS & SDWKS M071-112M | 2 | DESIGN | 2012-09-29 | 2012-12-27 | 2012-09-29 | 2012-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309RTIE | RVSD - TIEMAN PL TO 120TH STAIRS & SDWKS M071-112M | 3 | BID/ REGISTER CONTRACT | 2012-12-28 | 2013-03-27 | 2012-12-28 | 2013-03-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309RTIE | RVSD - TIEMAN PL TO 120TH STAIRS & SDWKS M071-112M | 4 | CONSTRUCTION | 2013-03-28 | 2014-03-27 | 2013-03-28 | 2014-03-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309RTIE | RVSD - TIEMAN PL TO 120TH STAIRS & SDWKS M071-112M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-03-28 | 2015-03-27 | 2014-03-28 | 2016-06-24
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309SKRP | Sakura Park - Reconstruction of the Staircase | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2017-05-04
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309SKRP | Sakura Park - Reconstruction of the Staircase | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2017-05-05 | 2018-08-31
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309SKRP | Sakura Park - Reconstruction of the Staircase | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2019-04-25 | 2019-10-28
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309SKRP | Sakura Park - Reconstruction of the Staircase | 4 | CONSTRUCTION | 2018-09-24 | 2019-09-23 | 2019-10-29 | 2020-10-30
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309SKRP | Sakura Park - Reconstruction of the Staircase | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-24 | 2020-09-22 | 2020-10-31 | 2021-10-30
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309SSTF | Jacob Schiff Playground Synthetic Turf Field Recon,Manhattan | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309SSTF | Jacob Schiff Playground Synthetic Turf Field Recon,Manhattan | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309SSTF | Jacob Schiff Playground Synthetic Turf Field Recon,Manhattan | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309SSTF | Jacob Schiff Playground Synthetic Turf Field Recon,Manhattan | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309SSTF | Jacob Schiff Playground Synthetic Turf Field Recon,Manhattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309STNC | ST NICHOLAS NORTH COMFORT STATION M211-110MA2 | 1 | DEVELOP SCOPE | 2006-07-01 | 2006-09-28 | 2006-07-01 | 2011-08-24
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309STNC | ST NICHOLAS NORTH COMFORT STATION M211-110MA2 | 2 | DESIGN | 2006-09-29 | 2006-12-27 | 2011-08-25 | 2011-08-24
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309STNC | ST NICHOLAS NORTH COMFORT STATION M211-110MA2 | 3 | BID/ REGISTER CONTRACT | 2006-12-28 | 2007-03-27 | 2010-12-29 | 2012-02-28
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309STNC | ST NICHOLAS NORTH COMFORT STATION M211-110MA2 | 4 | CONSTRUCTION | 2007-03-28 | 2008-03-26 | 2016-10-03 | 2017-10-09
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309STNC | ST NICHOLAS NORTH COMFORT STATION M211-110MA2 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-27 | 2009-03-26 | 2017-10-10 | 2018-10-09
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3107STP | 107TH Street Pier Renovation M108-216M | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2015-09-28
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3107STP | 107TH Street Pier Renovation M108-216M | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2015-09-29 | 2015-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3107STP | 107TH Street Pier Renovation M108-216M | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2015-12-28 | 2016-03-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3107STP | 107TH Street Pier Renovation M108-216M | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3107STP | 107TH Street Pier Renovation M108-216M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2017-03-27 | 2018-03-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-310ARFA | The Arsenal: Fire Alarm Reconstruction | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-310ARFA | The Arsenal: Fire Alarm Reconstruction | 2 | DESIGN | 2019-12-28 | 2021-12-26 | 2019-12-28 | 2021-12-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-310ARFA | The Arsenal: Fire Alarm Reconstruction | 3 | BID/ REGISTER CONTRACT | 2021-12-27 | 2022-09-22 | 2021-12-27 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-310ARFA | The Arsenal: Fire Alarm Reconstruction | 4 | CONSTRUCTION | 2022-09-23 | 2025-09-21 | 2022-09-23 | 2025-09-21
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-310ARFA | The Arsenal: Fire Alarm Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-09-22 | 2027-09-21 | 2025-09-22 | 2027-09-21
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-310CCPG | Courtney Callendar Playground-handball court | 1 | DEVELOP SCOPE | 2014-07-01 | 2014-09-28 | 2014-07-01 | 2014-09-28
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-310CCPG | Courtney Callendar Playground-handball court | 2 | DESIGN | 2014-09-29 | 2014-12-27 | 2014-09-29 | 2014-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-310CCPG | Courtney Callendar Playground-handball court | 3 | BID/ REGISTER CONTRACT | 2014-12-28 | 2015-03-27 | 2014-12-28 | 2015-03-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-310CCPG | Courtney Callendar Playground-handball court | 4 | CONSTRUCTION | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2016-03-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-310CCPG | Courtney Callendar Playground-handball court | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2021-03-31
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-310CCYB | COLONEL CHARLES YOUNG PK - BASEBALL FLDS RENOVATION M186 | 1 | DEVELOP SCOPE | 2010-07-01 | 2010-09-28 | 2010-07-01 | 2023-12-31
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-310CCYB | COLONEL CHARLES YOUNG PK - BASEBALL FLDS RENOVATION M186 | 2 | DESIGN | 2010-09-29 | 2010-12-27 | 2005-10-17 | 2024-12-01
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-310CCYB | COLONEL CHARLES YOUNG PK - BASEBALL FLDS RENOVATION M186 | 3 | BID/ REGISTER CONTRACT | 2010-12-28 | 2011-03-27 | 2025-09-01 | 2026-05-31
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-310CCYB | COLONEL CHARLES YOUNG PK - BASEBALL FLDS RENOVATION M186 | 4 | CONSTRUCTION | 2011-03-28 | 2012-03-26 | 2026-06-30 | 2027-06-29
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-310CCYB | COLONEL CHARLES YOUNG PK - BASEBALL FLDS RENOVATION M186 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-03-27 | 2013-03-26 | 2027-06-30 | 2028-06-28
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-310HCOM | HANSBOROUGH REC CTR COMPUTER PURCHASE M131 | 1 | DEVELOP SCOPE | 2006-07-01 | 2006-09-28 | 2006-07-01 | 2006-09-28
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-310HCOM | HANSBOROUGH REC CTR COMPUTER PURCHASE M131 | 2 | DESIGN | 2006-09-29 | 2006-12-27 | 2006-09-29 | 2006-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-310HCOM | HANSBOROUGH REC CTR COMPUTER PURCHASE M131 | 3 | BID/ REGISTER CONTRACT | 2006-12-28 | 2007-03-27 | 2006-12-28 | 2007-03-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-310HCOM | HANSBOROUGH REC CTR COMPUTER PURCHASE M131 | 4 | CONSTRUCTION | 2007-03-28 | 2008-03-26 | 2007-03-28 | 2008-03-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-310HCOM | HANSBOROUGH REC CTR COMPUTER PURCHASE M131 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-27 | 2009-03-26 | 2008-03-27 | 2013-07-01
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-310HRFT | HANSBORO RC CTR REFURB GYM FL & TRACK SURFACE M131-114M | 1 | DEVELOP SCOPE | 2012-07-01 | 2012-09-28 | 2012-07-01 | 2012-09-28
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-310HRFT | HANSBORO RC CTR REFURB GYM FL & TRACK SURFACE M131-114M | 2 | DESIGN | 2012-09-29 | 2012-12-27 | 2012-09-29 | 2012-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-310HRFT | HANSBORO RC CTR REFURB GYM FL & TRACK SURFACE M131-114M | 3 | BID/ REGISTER CONTRACT | 2012-12-28 | 2013-03-27 | 2012-12-28 | 2013-03-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-310HRFT | HANSBORO RC CTR REFURB GYM FL & TRACK SURFACE M131-114M | 4 | CONSTRUCTION | 2013-03-28 | 2014-03-27 | 2013-03-28 | 2014-03-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-310HRFT | HANSBORO RC CTR REFURB GYM FL & TRACK SURFACE M131-114M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-03-28 | 2015-03-27 | 2014-03-28 | 2015-03-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-310JROB | JACKIE ROBINSON REC CTR - PH II M014-102M/103M | 1 | DEVELOP SCOPE | 1999-07-01 | 2001-07-30 | 1999-07-01 | 2001-07-30
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-310JROB | JACKIE ROBINSON REC CTR - PH II M014-102M/103M | 2 | DESIGN | 2001-07-31 | 2002-11-18 | 2001-07-31 | 2002-11-18
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-310JROB | JACKIE ROBINSON REC CTR - PH II M014-102M/103M | 3 | BID/ REGISTER CONTRACT | 2003-01-22 | 2003-02-16 | 2003-01-22 | 2003-02-16
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-310JROB | JACKIE ROBINSON REC CTR - PH II M014-102M/103M | 4 | CONSTRUCTION | 2003-09-08 | 2004-09-01 | 2003-09-08 | 2004-09-01
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-310JROB | JACKIE ROBINSON REC CTR - PH II M014-102M/103M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2004-09-02 | 2005-09-01 | 2004-09-02 | 2005-09-01
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-310MCCY | McCray Playground , Manhattan | 1 | DEVELOP SCOPE | 2020-07-01 | 2020-12-27 | 2020-07-01 | 2020-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-310MCCY | McCray Playground , Manhattan | 2 | DESIGN | 2020-12-28 | 2021-12-27 | 2020-12-28 | 2021-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-310MCCY | McCray Playground , Manhattan | 3 | BID/ REGISTER CONTRACT | 2021-12-28 | 2022-09-23 | 2021-12-28 | 2022-09-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-310MCCY | McCray Playground , Manhattan | 4 | CONSTRUCTION | 2022-09-24 | 2023-09-23 | 2022-09-24 | 2023-09-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-310MCCY | McCray Playground , Manhattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-24 | 2024-09-22 | 2023-09-24 | 2024-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311HCTR | HIGHBRIDGE RECREATION CTR -RC BOILERS AND HVAC - M037-217M | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311HCTR | HIGHBRIDGE RECREATION CTR -RC BOILERS AND HVAC - M037-217M | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2016-12-28 | 2017-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311HCTR | HIGHBRIDGE RECREATION CTR -RC BOILERS AND HVAC - M037-217M | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2017-12-28 | 2018-09-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311HCTR | HIGHBRIDGE RECREATION CTR -RC BOILERS AND HVAC - M037-217M | 4 | CONSTRUCTION | 2018-09-24 | 2019-09-23 | 2018-09-24 | 2019-09-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311HCTR | HIGHBRIDGE RECREATION CTR -RC BOILERS AND HVAC - M037-217M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311HEL3 | Phase 3 of Hell Gate Pathway, below Viaduct Randalls Island | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2015-02-11 | 2018-05-18
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311HEL3 | Phase 3 of Hell Gate Pathway, below Viaduct Randalls Island | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2018-05-19 | 2020-10-04
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311HEL3 | Phase 3 of Hell Gate Pathway, below Viaduct Randalls Island | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2019-11-20 | 2020-02-11
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311HEL3 | Phase 3 of Hell Gate Pathway, below Viaduct Randalls Island | 4 | CONSTRUCTION | 2018-09-24 | 2019-09-23 | 2020-02-12 | 2021-02-10
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311HEL3 | Phase 3 of Hell Gate Pathway, below Viaduct Randalls Island | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-24 | 2020-09-22 | 2021-02-11 | 2022-02-10
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311HWTR | HIGHBRIDGE AQUEDUCT WATER TOWER RESTORATION M037-113M | 1 | DEVELOP SCOPE | 2012-02-09 | 2012-05-08 | 2012-02-09 | 2012-05-08
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311HWTR | HIGHBRIDGE AQUEDUCT WATER TOWER RESTORATION M037-113M | 2 | DESIGN | 2012-05-09 | 2012-08-06 | 2012-05-09 | 2012-08-06
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311HWTR | HIGHBRIDGE AQUEDUCT WATER TOWER RESTORATION M037-113M | 3 | BID/ REGISTER CONTRACT | 2012-08-07 | 2012-11-04 | 2012-08-07 | 2012-11-04
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311HWTR | HIGHBRIDGE AQUEDUCT WATER TOWER RESTORATION M037-113M | 4 | CONSTRUCTION | 2012-11-05 | 2013-11-04 | 2012-11-05 | 2013-11-04
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311HWTR | HIGHBRIDGE AQUEDUCT WATER TOWER RESTORATION M037-113M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-11-05 | 2014-11-04 | 2013-11-05 | 2019-04-01
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311MGFI | MARCUS GARVEY PK FIRE WATCHTOWER RESTORATION M058-115M | 1 | DEVELOP SCOPE | 2014-07-01 | 2014-09-28 | 2014-07-01 | 2014-09-28
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311MGFI | MARCUS GARVEY PK FIRE WATCHTOWER RESTORATION M058-115M | 2 | DESIGN | 2014-09-29 | 2014-12-27 | 2014-09-29 | 2014-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311MGFI | MARCUS GARVEY PK FIRE WATCHTOWER RESTORATION M058-115M | 3 | BID/ REGISTER CONTRACT | 2014-12-28 | 2015-03-27 | 2014-12-28 | 2015-03-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311MGFI | MARCUS GARVEY PK FIRE WATCHTOWER RESTORATION M058-115M | 4 | CONSTRUCTION | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2016-03-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311MGFI | MARCUS GARVEY PK FIRE WATCHTOWER RESTORATION M058-115M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311MGLL | MARCUS GARVEY CS LITTLE LEAGUE FACILTY M058-116M | 1 | DEVELOP SCOPE | 2006-07-01 | 2006-09-28 | 2006-07-01 | 2009-01-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311MGLL | MARCUS GARVEY CS LITTLE LEAGUE FACILTY M058-116M | 2 | DESIGN | 2006-09-29 | 2006-12-27 | 2009-01-27 | 2011-02-28
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311MGLL | MARCUS GARVEY CS LITTLE LEAGUE FACILTY M058-116M | 3 | BID/ REGISTER CONTRACT | 2006-12-28 | 2007-03-27 | 2011-05-26 | 2011-10-14
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311MGLL | MARCUS GARVEY CS LITTLE LEAGUE FACILTY M058-116M | 4 | CONSTRUCTION | 2007-03-28 | 2008-03-26 | 2011-10-15 | 2012-09-01
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311MGLL | MARCUS GARVEY CS LITTLE LEAGUE FACILTY M058-116M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-27 | 2009-03-26 | 2012-09-02 | 2013-09-01
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311MGPF | PELHAM FRITZ REC CTR BOILER M058-112M | 2 | DESIGN | 2011-09-29 | 2011-12-27 | 2011-09-29 | 2011-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311MGPF | PELHAM FRITZ REC CTR BOILER M058-112M | 3 | BID/ REGISTER CONTRACT | 2011-12-28 | 2012-03-26 | 2011-12-28 | 2012-03-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311MGPF | PELHAM FRITZ REC CTR BOILER M058-112M | 4 | CONSTRUCTION | 2012-03-27 | 2013-03-26 | 2012-03-27 | 2013-03-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311MGPF | PELHAM FRITZ REC CTR BOILER M058-112M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-03-27 | 2014-03-26 | 2013-03-27 | 2014-03-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311PFFA | Pelham Fritz Rec. Center: Fire Alarm Reconstruction | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311PFFA | Pelham Fritz Rec. Center: Fire Alarm Reconstruction | 2 | DESIGN | 2019-12-28 | 2021-12-26 | 2019-12-28 | 2021-12-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311PFFA | Pelham Fritz Rec. Center: Fire Alarm Reconstruction | 3 | BID/ REGISTER CONTRACT | 2021-12-27 | 2022-09-22 | 2021-12-27 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311PFFA | Pelham Fritz Rec. Center: Fire Alarm Reconstruction | 4 | CONSTRUCTION | 2022-09-23 | 2025-09-21 | 2022-09-23 | 2025-09-21
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311PFFA | Pelham Fritz Rec. Center: Fire Alarm Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-09-22 | 2027-09-21 | 2025-09-22 | 2027-09-21
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311PFRI | MARCUS GARVEY PK -PELHAM FRITZ RECREATION CTR CONS M058-118M | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311PFRI | MARCUS GARVEY PK -PELHAM FRITZ RECREATION CTR CONS M058-118M | 2 | DESIGN | 2016-12-28 | 2018-12-27 | 2016-12-28 | 2018-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311PFRI | MARCUS GARVEY PK -PELHAM FRITZ RECREATION CTR CONS M058-118M | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311PFRI | MARCUS GARVEY PK -PELHAM FRITZ RECREATION CTR CONS M058-118M | 4 | CONSTRUCTION | 2019-09-24 | 2022-09-22 | 2019-09-24 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311PFRI | MARCUS GARVEY PK -PELHAM FRITZ RECREATION CTR CONS M058-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2024-09-21 | 2022-09-23 | 2024-09-21
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311PRPL | Poor Richard's Playground Renovations | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2016-01-13
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311PRPL | Poor Richard's Playground Renovations | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2016-01-14 | 2017-03-31
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311PRPL | Poor Richard's Playground Renovations | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2017-07-25 | 2018-01-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311PRPL | Poor Richard's Playground Renovations | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2018-08-06 | 2019-08-05
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311PRPL | Poor Richard's Playground Renovations | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2019-08-06 | 2020-08-05
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311RIFW | RANDALL'S ISLAND FRESHWATER WETLANDS PATHWAY M104 M107 111M | 1 | DEVELOP SCOPE | 2012-09-13 | 2012-12-11 | 2011-07-01 | 2012-08-07
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311RIFW | RANDALL'S ISLAND FRESHWATER WETLANDS PATHWAY M104 M107 111M | 2 | DESIGN | 2012-12-12 | 2013-03-11 | 2012-08-08 | 2013-10-29
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311RIFW | RANDALL'S ISLAND FRESHWATER WETLANDS PATHWAY M104 M107 111M | 3 | BID/ REGISTER CONTRACT | 2013-03-12 | 2013-06-09 | 2014-06-05 | 2015-05-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311RIFW | RANDALL'S ISLAND FRESHWATER WETLANDS PATHWAY M104 M107 111M | 4 | CONSTRUCTION | 2013-06-10 | 2014-06-09 | 2015-07-13 | 2016-08-09
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311RIFW | RANDALL'S ISLAND FRESHWATER WETLANDS PATHWAY M104 M107 111M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-06-10 | 2015-06-09 | 2016-08-10 | 2017-08-09
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311RILS | RANDALLS ISLAND LIVING SHORELINE M104-116M | 1 | DEVELOP SCOPE | 2012-09-13 | 2012-12-11 | 2011-07-01 | 2011-09-28
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311RILS | RANDALLS ISLAND LIVING SHORELINE M104-116M | 2 | DESIGN | 2012-12-12 | 2013-03-11 | 2011-09-29 | 2011-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311RILS | RANDALLS ISLAND LIVING SHORELINE M104-116M | 3 | BID/ REGISTER CONTRACT | 2013-03-12 | 2013-06-09 | 2011-12-28 | 2012-03-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311RILS | RANDALLS ISLAND LIVING SHORELINE M104-116M | 4 | CONSTRUCTION | 2013-06-10 | 2014-06-09 | 2012-03-27 | 2013-03-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311RILS | RANDALLS ISLAND LIVING SHORELINE M104-116M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-06-10 | 2015-06-09 | 2013-03-27 | 2020-03-12
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311TJFA | Thomas Jefferson Rec. Center: Fire Alarm Reconstruction | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311TJFA | Thomas Jefferson Rec. Center: Fire Alarm Reconstruction | 2 | DESIGN | 2019-12-28 | 2021-12-26 | 2019-12-28 | 2021-12-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311TJFA | Thomas Jefferson Rec. Center: Fire Alarm Reconstruction | 3 | BID/ REGISTER CONTRACT | 2021-12-27 | 2022-09-22 | 2021-12-27 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311TJFA | Thomas Jefferson Rec. Center: Fire Alarm Reconstruction | 4 | CONSTRUCTION | 2022-09-23 | 2025-09-21 | 2022-09-23 | 2025-09-21
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311TJFA | Thomas Jefferson Rec. Center: Fire Alarm Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-09-22 | 2027-09-21 | 2025-09-22 | 2027-09-21
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311TJHV | THOMAS JEFFERSON PARK REC CTR HVAC M047-109M | 1 | DEVELOP SCOPE | 2007-07-01 | 2007-09-28 | 2007-07-01 | 2008-07-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311TJHV | THOMAS JEFFERSON PARK REC CTR HVAC M047-109M | 2 | DESIGN | 2007-09-29 | 2007-12-27 | 2008-07-23 | 2009-01-20
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311TJHV | THOMAS JEFFERSON PARK REC CTR HVAC M047-109M | 3 | BID/ REGISTER CONTRACT | 2007-12-28 | 2008-03-26 | 2009-03-18 | 2009-07-21
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311TJHV | THOMAS JEFFERSON PARK REC CTR HVAC M047-109M | 4 | CONSTRUCTION | 2008-03-27 | 2009-03-26 | 2009-07-22 | 2010-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311TJHV | THOMAS JEFFERSON PARK REC CTR HVAC M047-109M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2009-03-27 | 2010-03-26 | 2010-09-23 | 2011-09-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311TJPK | Thomas Jefferson Park Renovations | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2016-02-17
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311TJPK | Thomas Jefferson Park Renovations | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2016-02-18 | 2018-11-01
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311TJPK | Thomas Jefferson Park Renovations | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2018-11-13 | 2019-03-24
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311TJPK | Thomas Jefferson Park Renovations | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2019-03-30 | 2020-03-30
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311TJPK | Thomas Jefferson Park Renovations | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2020-04-01 | 2021-03-30
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311TURF | Harlem River Park Synthetic Turf, Manhattan M208D-219M | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311TURF | Harlem River Park Synthetic Turf, Manhattan M208D-219M | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311TURF | Harlem River Park Synthetic Turf, Manhattan M208D-219M | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311TURF | Harlem River Park Synthetic Turf, Manhattan M208D-219M | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311TURF | Harlem River Park Synthetic Turf, Manhattan M208D-219M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312DFAR | DYCKMAN FARMHOUSE : ADA RAMP AND BATHROOM RENOVATION | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312DFAR | DYCKMAN FARMHOUSE : ADA RAMP AND BATHROOM RENOVATION | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2016-12-28 | 2017-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312DFAR | DYCKMAN FARMHOUSE : ADA RAMP AND BATHROOM RENOVATION | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2017-12-28 | 2018-09-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312DFAR | DYCKMAN FARMHOUSE : ADA RAMP AND BATHROOM RENOVATION | 4 | CONSTRUCTION | 2018-09-24 | 2019-09-23 | 2018-09-24 | 2019-09-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312DFAR | DYCKMAN FARMHOUSE : ADA RAMP AND BATHROOM RENOVATION | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312IHB6 | INWOOD HILL PARK BALLFIELD # 6 REGRADE & RESOD M042-110MA | 1 | DEVELOP SCOPE | 2009-07-01 | 2009-09-28 | 2009-07-01 | 2010-04-02
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312IHB6 | INWOOD HILL PARK BALLFIELD # 6 REGRADE & RESOD M042-110MA | 2 | DESIGN | 2009-09-29 | 2009-12-27 | 2010-04-03 | 2012-05-15
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312IHB6 | INWOOD HILL PARK BALLFIELD # 6 REGRADE & RESOD M042-110MA | 3 | BID/ REGISTER CONTRACT | 2009-12-28 | 2010-03-27 | 2012-10-09 | 2013-08-28
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312IHB6 | INWOOD HILL PARK BALLFIELD # 6 REGRADE & RESOD M042-110MA | 4 | CONSTRUCTION | 2010-03-28 | 2011-03-27 | 2013-09-23 | 2014-05-13
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312IHB6 | INWOOD HILL PARK BALLFIELD # 6 REGRADE & RESOD M042-110MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2011-03-28 | 2012-03-26 | 2014-05-13 | 2015-05-13
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312IHPB | INWOOD HILL PK SANITARY SEWER FOR NATURE CTR M042-115M | 1 | DEVELOP SCOPE | 2012-07-01 | 2012-09-28 | 2012-07-01 | 2014-10-30
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312IHPB | INWOOD HILL PK SANITARY SEWER FOR NATURE CTR M042-115M | 2 | DESIGN | 2012-09-29 | 2012-12-27 | 2014-10-31 | 2015-10-04
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312IHPB | INWOOD HILL PK SANITARY SEWER FOR NATURE CTR M042-115M | 3 | BID/ REGISTER CONTRACT | 2012-12-28 | 2013-03-27 | 2016-09-01 | 2017-03-29
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312IHPB | INWOOD HILL PK SANITARY SEWER FOR NATURE CTR M042-115M | 4 | CONSTRUCTION | 2013-03-28 | 2014-03-27 | 2017-07-10 | 2018-07-09
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312IHPB | INWOOD HILL PK SANITARY SEWER FOR NATURE CTR M042-115M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-03-28 | 2015-03-27 | 2018-07-10 | 2019-07-09
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312INNC | Inwood Hill Nature Center M042 -116M | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2015-09-28
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312INNC | Inwood Hill Nature Center M042 -116M | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2015-09-29 | 2015-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312INNC | Inwood Hill Nature Center M042 -116M | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2015-12-28 | 2016-03-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312INNC | Inwood Hill Nature Center M042 -116M | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312INNC | Inwood Hill Nature Center M042 -116M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2017-03-27 | 2018-03-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312INNG | RIVERSIDE-INWOOD NEIGHBORHOOD GARDENS, INC. | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2020-11-07
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312INNG | RIVERSIDE-INWOOD NEIGHBORHOOD GARDENS, INC. | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2020-11-08 | 2024-11-07
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312INNG | RIVERSIDE-INWOOD NEIGHBORHOOD GARDENS, INC. | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2024-11-08 | 2025-08-04
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312INNG | RIVERSIDE-INWOOD NEIGHBORHOOD GARDENS, INC. | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2025-08-05 | 2026-08-03
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312INNG | RIVERSIDE-INWOOD NEIGHBORHOOD GARDENS, INC. | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2026-08-04 | 2027-08-03
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312INWD | Inwood Hill Nature Center- Exhibit Display Reconstruction | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312INWD | Inwood Hill Nature Center- Exhibit Display Reconstruction | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312INWD | Inwood Hill Nature Center- Exhibit Display Reconstruction | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312INWD | Inwood Hill Nature Center- Exhibit Display Reconstruction | 4 | CONSTRUCTION | 2019-09-24 | 2021-03-21 | 2019-09-24 | 2021-03-21
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312INWD | Inwood Hill Nature Center- Exhibit Display Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-22 | 2022-03-21 | 2021-03-22 | 2022-03-21
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312ISA2 | ISHAM PARK IRRIGATION & DRINK FOUNTAINS M043 M43112 | 1 | DEVELOP SCOPE | 2011-07-01 | 2011-09-28 | 2011-07-01 | 2011-09-28
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312ISA2 | ISHAM PARK IRRIGATION & DRINK FOUNTAINS M043 M43112 | 2 | DESIGN | 2011-09-29 | 2011-12-27 | 2011-09-29 | 2011-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312ISA2 | ISHAM PARK IRRIGATION & DRINK FOUNTAINS M043 M43112 | 3 | BID/ REGISTER CONTRACT | 2011-12-28 | 2012-03-26 | 2011-12-28 | 2012-03-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312ISA2 | ISHAM PARK IRRIGATION & DRINK FOUNTAINS M043 M43112 | 4 | CONSTRUCTION | 2012-03-27 | 2013-03-26 | 2012-03-27 | 2013-03-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312ISA2 | ISHAM PARK IRRIGATION & DRINK FOUNTAINS M043 M43112 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-03-27 | 2014-03-26 | 2013-03-27 | 2014-05-31
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312JHFA | J. Hood Wright Rec. Center: Fire Alarm Reconstruction | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312JHFA | J. Hood Wright Rec. Center: Fire Alarm Reconstruction | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312JHFA | J. Hood Wright Rec. Center: Fire Alarm Reconstruction | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312JHFA | J. Hood Wright Rec. Center: Fire Alarm Reconstruction | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312JHFA | J. Hood Wright Rec. Center: Fire Alarm Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312JHRW | J HOOD WRIGHT PARK REC CTR WINDOWS M099 | 1 | DEVELOP SCOPE | 2012-07-01 | 2012-09-28 | 2012-07-01 | 2012-09-28
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312JHRW | J HOOD WRIGHT PARK REC CTR WINDOWS M099 | 2 | DESIGN | 2012-09-29 | 2012-12-27 | 2012-09-29 | 2012-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312JHRW | J HOOD WRIGHT PARK REC CTR WINDOWS M099 | 3 | BID/ REGISTER CONTRACT | 2012-12-28 | 2013-03-27 | 2012-12-28 | 2013-03-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312JHRW | J HOOD WRIGHT PARK REC CTR WINDOWS M099 | 4 | CONSTRUCTION | 2013-03-28 | 2014-03-27 | 2013-03-28 | 2014-03-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312JHRW | J HOOD WRIGHT PARK REC CTR WINDOWS M099 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-03-28 | 2015-03-27 | 2014-03-28 | 2015-03-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312JJPG | Jacob Javits Plgr-renovation | 1 | DEVELOP SCOPE | 2014-07-01 | 2014-09-28 | 2014-07-01 | 2015-02-11
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312JJPG | Jacob Javits Plgr-renovation | 2 | DESIGN | 2014-09-29 | 2014-12-27 | 2015-02-12 | 2017-05-24
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312JJPG | Jacob Javits Plgr-renovation | 3 | BID/ REGISTER CONTRACT | 2014-12-28 | 2015-03-27 | 2017-09-19 | 2018-06-01
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312JJPG | Jacob Javits Plgr-renovation | 4 | CONSTRUCTION | 2015-03-28 | 2016-03-26 | 2018-07-09 | 2019-11-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312JJPG | Jacob Javits Plgr-renovation | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-27 | 2017-03-26 | 2019-11-27 | 2020-11-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312MJM2 | Morris Jumel mansion - exterior renovation- ph II M073 | 1 | DEVELOP SCOPE | 2011-07-01 | 2011-09-28 | 2011-07-01 | 2011-09-28
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312MJM2 | Morris Jumel mansion - exterior renovation- ph II M073 | 2 | DESIGN | 2011-09-29 | 2011-12-27 | 2006-06-05 | 2013-07-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312MJM2 | Morris Jumel mansion - exterior renovation- ph II M073 | 3 | BID/ REGISTER CONTRACT | 2011-12-28 | 2012-03-26 | 2013-10-25 | 2014-06-17
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312MJM2 | Morris Jumel mansion - exterior renovation- ph II M073 | 4 | CONSTRUCTION | 2012-03-27 | 2013-03-26 | 2014-07-21 | 2016-02-09
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312MJM2 | Morris Jumel mansion - exterior renovation- ph II M073 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-03-27 | 2014-03-26 | 2016-02-10 | 2017-02-09
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312PLAY | HIGHBRIDGE BATHHSE M037-200M/400M | 3 | BID/ REGISTER CONTRACT | 2000-04-14 | 2000-08-01 | 2000-04-14 | 2000-08-01
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312PLAY | HIGHBRIDGE BATHHSE M037-200M/400M | 4 | CONSTRUCTION | 2000-09-18 | 2001-06-22 | 2000-09-18 | 2001-06-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312PLAY | HIGHBRIDGE BATHHSE M037-200M/400M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2001-06-23 | 2002-06-22 | 2001-06-23 | 2002-06-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312SWIN | NYRP - SWINDLER COVE PARK(Sherman Creek)M300-106MA | 3 | BID/ REGISTER CONTRACT | 2008-12-28 | 2009-03-27 | 2013-03-04 | 2013-06-13
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312SWIN | NYRP - SWINDLER COVE PARK(Sherman Creek)M300-106MA | 4 | CONSTRUCTION | 2009-03-28 | 2010-03-27 | 2013-09-09 | 2014-09-15
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312SWIN | NYRP - SWINDLER COVE PARK(Sherman Creek)M300-106MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2010-03-28 | 2011-03-27 | 2014-09-16 | 2015-05-20
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-313CPA2 | CENTRAL PARK - ARSENAL ELEVATOR RC M010-616M | 1 | DEVELOP SCOPE | 2016-08-01 | 2017-01-27 | 2016-08-01 | 2017-01-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-313CPA2 | CENTRAL PARK - ARSENAL ELEVATOR RC M010-616M | 2 | DESIGN | 2017-01-28 | 2018-01-27 | 2017-01-28 | 2018-01-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-313CPA2 | CENTRAL PARK - ARSENAL ELEVATOR RC M010-616M | 3 | BID/ REGISTER CONTRACT | 2018-01-28 | 2018-10-24 | 2018-01-28 | 2018-10-24
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-313CPA2 | CENTRAL PARK - ARSENAL ELEVATOR RC M010-616M | 4 | CONSTRUCTION | 2018-10-25 | 2019-10-24 | 2018-10-25 | 2019-10-24
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-313CPA2 | CENTRAL PARK - ARSENAL ELEVATOR RC M010-616M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-10-25 | 2020-10-23 | 2019-10-25 | 2020-10-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-313CPAB | CENTRAL PARK - ARSENAL BRICK FACADE M010-214M | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2013-09-28
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-313CPAB | CENTRAL PARK - ARSENAL BRICK FACADE M010-214M | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2013-09-29 | 2013-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-313CPAB | CENTRAL PARK - ARSENAL BRICK FACADE M010-214M | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2013-12-28 | 2014-03-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-313CPAB | CENTRAL PARK - ARSENAL BRICK FACADE M010-214M | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2014-03-28 | 2015-03-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-313CPAB | CENTRAL PARK - ARSENAL BRICK FACADE M010-214M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2016-03-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-313CPSW | Central Park - Swedish Cottage M010-116M | 1 | DEVELOP SCOPE | 2008-07-01 | 2008-09-28 | 2008-07-01 | 2008-09-28
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-313CPSW | Central Park - Swedish Cottage M010-116M | 2 | DESIGN | 2008-09-29 | 2008-12-27 | 2008-09-29 | 2008-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-313CPSW | Central Park - Swedish Cottage M010-116M | 3 | BID/ REGISTER CONTRACT | 2008-12-28 | 2009-03-27 | 2008-12-28 | 2009-03-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-313CPSW | Central Park - Swedish Cottage M010-116M | 4 | CONSTRUCTION | 2009-03-28 | 2010-03-27 | 2009-03-28 | 2010-03-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-313CPSW | Central Park - Swedish Cottage M010-116M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2010-03-28 | 2011-03-27 | 2010-03-28 | 2013-03-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-314RPDR | RIVERSIDE PARK DOG RUN M071 | 1 | DEVELOP SCOPE | 2003-07-01 | 2003-09-28 | 2003-07-01 | 2020-01-17
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-314RPDR | RIVERSIDE PARK DOG RUN M071 | 2 | DESIGN | 2003-09-29 | 2003-12-27 | 2020-01-18 | 2038-06-16
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-314RPDR | RIVERSIDE PARK DOG RUN M071 | 3 | BID/ REGISTER CONTRACT | 2003-12-28 | 2004-03-26 | 2021-06-30 | 2021-10-01
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-314RPDR | RIVERSIDE PARK DOG RUN M071 | 4 | CONSTRUCTION | 2004-03-27 | 2005-03-26 | 2021-10-31 | 2022-10-30
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-314RPDR | RIVERSIDE PARK DOG RUN M071 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2005-03-27 | 2006-03-26 | 2022-10-30 | 2023-10-29
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ANCH02 | Highbridge Anchor Park Phase II- Manhattan M037-118M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ANCH02 | Highbridge Anchor Park Phase II- Manhattan M037-118M | 2 | DESIGN | 2017-12-28 | 2019-06-20 | 2017-12-28 | 2019-06-20
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ANCH02 | Highbridge Anchor Park Phase II- Manhattan M037-118M | 3 | BID/ REGISTER CONTRACT | 2019-06-21 | 2020-03-16 | 2019-06-21 | 2020-03-16
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ANCH02 | Highbridge Anchor Park Phase II- Manhattan M037-118M | 4 | CONSTRUCTION | 2020-03-17 | 2021-09-07 | 2020-03-17 | 2021-09-07
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ANCH02 | Highbridge Anchor Park Phase II- Manhattan M037-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-08 | 2022-09-07 | 2021-09-08 | 2022-09-07
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ANCH03 | Highbridge Anchor Park Phase III- COMFORT STATION, M037-218M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ANCH03 | Highbridge Anchor Park Phase III- COMFORT STATION, M037-218M | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ANCH03 | Highbridge Anchor Park Phase III- COMFORT STATION, M037-218M | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ANCH03 | Highbridge Anchor Park Phase III- COMFORT STATION, M037-218M | 4 | CONSTRUCTION | 2019-09-24 | 2021-03-21 | 2019-09-24 | 2021-03-21
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ANCH03 | Highbridge Anchor Park Phase III- COMFORT STATION, M037-218M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-22 | 2022-03-21 | 2021-03-22 | 2022-03-21
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ANCH04 | Highbridge Anchor Park Reconstruction Phase I, Manhattan | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ANCH04 | Highbridge Anchor Park Reconstruction Phase I, Manhattan | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ANCH04 | Highbridge Anchor Park Reconstruction Phase I, Manhattan | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ANCH04 | Highbridge Anchor Park Reconstruction Phase I, Manhattan | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ANCH04 | Highbridge Anchor Park Reconstruction Phase I, Manhattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ANNEPG | ANNE LOFTUS PLAYGROUND//WATER PARK, M029-118M, Mahattan | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ANNEPG | ANNE LOFTUS PLAYGROUND//WATER PARK, M029-118M, Mahattan | 2 | DESIGN | 2017-12-28 | 2019-06-20 | 2017-12-28 | 2019-06-20
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ANNEPG | ANNE LOFTUS PLAYGROUND//WATER PARK, M029-118M, Mahattan | 3 | BID/ REGISTER CONTRACT | 2019-06-21 | 2020-03-16 | 2019-06-21 | 2020-03-16
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ANNEPG | ANNE LOFTUS PLAYGROUND//WATER PARK, M029-118M, Mahattan | 4 | CONSTRUCTION | 2020-03-17 | 2021-09-07 | 2020-03-17 | 2021-09-07
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ANNEPG | ANNE LOFTUS PLAYGROUND//WATER PARK, M029-118M, Mahattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-08 | 2022-09-07 | 2021-09-08 | 2022-09-07
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ASGRGN | ASPHALT GREEN: EMERGENCY GENERATOR PROJECT | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ASGRGN | ASPHALT GREEN: EMERGENCY GENERATOR PROJECT | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ASGRGN | ASPHALT GREEN: EMERGENCY GENERATOR PROJECT | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ASGRGN | ASPHALT GREEN: EMERGENCY GENERATOR PROJECT | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ASGRGN | ASPHALT GREEN: EMERGENCY GENERATOR PROJECT | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ASRRMP | Asser Levy Recreation Center Ramp Reconstruction | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ASRRMP | Asser Levy Recreation Center Ramp Reconstruction | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ASRRMP | Asser Levy Recreation Center Ramp Reconstruction | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ASRRMP | Asser Levy Recreation Center Ramp Reconstruction | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ASRRMP | Asser Levy Recreation Center Ramp Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BBASIN | Riverside Park- Moving Costs Associated With The 79th Street | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BBASIN | Riverside Park- Moving Costs Associated With The 79th Street | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BBASIN | Riverside Park- Moving Costs Associated With The 79th Street | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BBASIN | Riverside Park- Moving Costs Associated With The 79th Street | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BBASIN | Riverside Park- Moving Costs Associated With The 79th Street | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BBGARD | BATTERY PARK SEAGLASS CAROUSEL M005-208M | 1 | DEVELOP SCOPE | 2007-07-01 | 2007-09-28 | 2007-07-01 | 2007-09-28
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BBGARD | BATTERY PARK SEAGLASS CAROUSEL M005-208M | 2 | DESIGN | 2007-09-29 | 2007-12-27 | 2007-09-29 | 2009-10-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BBGARD | BATTERY PARK SEAGLASS CAROUSEL M005-208M | 3 | BID/ REGISTER CONTRACT | 2007-12-28 | 2008-03-26 | 2010-02-10 | 2010-07-14
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BBGARD | BATTERY PARK SEAGLASS CAROUSEL M005-208M | 4 | CONSTRUCTION | 2008-03-27 | 2009-03-26 | 2010-09-13 | 2015-06-25
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BBGARD | BATTERY PARK SEAGLASS CAROUSEL M005-208M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2009-03-27 | 2010-03-26 | 2015-06-26 | 2016-06-25
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BDREQ6 | REQUIREMENTS - MANHATTAN MG-106M | 1 | DEVELOP SCOPE | 2006-07-01 | 2006-09-28 | 2003-10-16 | 2004-01-13
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BDREQ6 | REQUIREMENTS - MANHATTAN MG-106M | 2 | DESIGN | 2006-09-29 | 2006-12-27 | 2004-01-14 | 2004-04-12
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BDREQ6 | REQUIREMENTS - MANHATTAN MG-106M | 3 | BID/ REGISTER CONTRACT | 2006-12-28 | 2007-03-27 | 2004-04-13 | 2004-07-11
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BDREQ6 | REQUIREMENTS - MANHATTAN MG-106M | 4 | CONSTRUCTION | 2007-03-28 | 2008-03-26 | 2004-07-12 | 2005-07-11
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BDREQ6 | REQUIREMENTS - MANHATTAN MG-106M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-27 | 2009-03-26 | 2005-07-12 | 2011-11-30
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BELLVU | BELLEVUE PARK SOUTH, RECONS Mahattan | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2018-07-19
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BELLVU | BELLEVUE PARK SOUTH, RECONS Mahattan | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2018-07-20 | 2019-12-13
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BELLVU | BELLEVUE PARK SOUTH, RECONS Mahattan | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2020-12-30 | 2021-03-01
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BELLVU | BELLEVUE PARK SOUTH, RECONS Mahattan | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2021-05-17 | 2022-05-16
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BELLVU | BELLEVUE PARK SOUTH, RECONS Mahattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2022-05-16 | 2023-05-15
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BENNSF | BENNETT PARK SYNTHETIC FIELD | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BENNSF | BENNETT PARK SYNTHETIC FIELD | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BENNSF | BENNETT PARK SYNTHETIC FIELD | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BENNSF | BENNETT PARK SYNTHETIC FIELD | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BENNSF | BENNETT PARK SYNTHETIC FIELD | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BOOKTW | BOOKER T WASHINGTON Plg Synthetic Turf Rpl, Mahattan | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BOOKTW | BOOKER T WASHINGTON Plg Synthetic Turf Rpl, Mahattan | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BOOKTW | BOOKER T WASHINGTON Plg Synthetic Turf Rpl, Mahattan | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BOOKTW | BOOKER T WASHINGTON Plg Synthetic Turf Rpl, Mahattan | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BOOKTW | BOOKER T WASHINGTON Plg Synthetic Turf Rpl, Mahattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BOTWAT | 6BC Botanical Garden:Garden Water Source | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BOTWAT | 6BC Botanical Garden:Garden Water Source | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BOTWAT | 6BC Botanical Garden:Garden Water Source | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BOTWAT | 6BC Botanical Garden:Garden Water Source | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BOTWAT | 6BC Botanical Garden:Garden Water Source | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BPPLGD | BATTERY PARK Plg (SOUTH FERRY-MTA) M005-117M | 1 | DEVELOP SCOPE | 2006-07-01 | 2006-09-28 | 2006-07-01 | 2006-09-28
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BPPLGD | BATTERY PARK Plg (SOUTH FERRY-MTA) M005-117M | 2 | DESIGN | 2006-09-29 | 2006-12-27 | 2006-09-29 | 2014-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BPPLGD | BATTERY PARK Plg (SOUTH FERRY-MTA) M005-117M | 3 | BID/ REGISTER CONTRACT | 2006-12-28 | 2007-03-27 | 2015-03-31 | 2015-10-01
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BPPLGD | BATTERY PARK Plg (SOUTH FERRY-MTA) M005-117M | 4 | CONSTRUCTION | 2007-03-28 | 2008-03-26 | 2015-10-17 | 2016-10-16
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BPPLGD | BATTERY PARK Plg (SOUTH FERRY-MTA) M005-117M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-27 | 2009-03-26 | 2016-10-17 | 2020-12-30
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BWWATE | RPZ - WATER SERVICE INSTALLATION MG-518M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BWWATE | RPZ - WATER SERVICE INSTALLATION MG-518M | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BWWATE | RPZ - WATER SERVICE INSTALLATION MG-518M | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BWWATE | RPZ - WATER SERVICE INSTALLATION MG-518M | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BWWATE | RPZ - WATER SERVICE INSTALLATION MG-518M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CENBOL | Central Park - Construction Security Measures | 1 | DEVELOP SCOPE | 2018-05-29 | 2018-11-24 | 2018-05-29 | 2018-11-24
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CENBOL | Central Park - Construction Security Measures | 2 | DESIGN | 2018-11-25 | 2020-11-23 | 2018-11-25 | 2020-11-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CENBOL | Central Park - Construction Security Measures | 3 | BID/ REGISTER CONTRACT | 2020-11-24 | 2021-08-20 | 2020-11-24 | 2021-08-20
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CENBOL | Central Park - Construction Security Measures | 4 | CONSTRUCTION | 2021-08-21 | 2023-08-20 | 2021-08-21 | 2023-08-20
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CENBOL | Central Park - Construction Security Measures | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-08-21 | 2024-08-19 | 2023-08-21 | 2024-08-19
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CENT04 | Central Park - Recon West Side Landscape M010-614M WO# 4 | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2020-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CENT04 | Central Park - Recon West Side Landscape M010-614M WO# 4 | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2020-12-28 | 2026-01-20
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CENT04 | Central Park - Recon West Side Landscape M010-614M WO# 4 | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2022-05-08 | 2022-09-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CENT04 | Central Park - Recon West Side Landscape M010-614M WO# 4 | 4 | CONSTRUCTION | 2018-09-24 | 2019-09-23 | 2022-09-24 | 2023-09-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CENT04 | Central Park - Recon West Side Landscape M010-614M WO# 4 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-24 | 2020-09-22 | 2023-09-24 | 2024-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CENT05 | Central Park - Recon of CPW Perimeter M010-614M WO# 5 | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2020-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CENT05 | Central Park - Recon of CPW Perimeter M010-614M WO# 5 | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2020-12-28 | 2024-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CENT05 | Central Park - Recon of CPW Perimeter M010-614M WO# 5 | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2024-12-28 | 2025-09-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CENT05 | Central Park - Recon of CPW Perimeter M010-614M WO# 5 | 4 | CONSTRUCTION | 2018-09-24 | 2019-09-23 | 2025-09-24 | 2026-09-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CENT05 | Central Park - Recon of CPW Perimeter M010-614M WO# 5 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-24 | 2020-09-22 | 2026-09-24 | 2027-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CENT08 | Central Park - Recons of Perimeter E84-E108ST WO# 8 | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CENT08 | Central Park - Recons of Perimeter E84-E108ST WO# 8 | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CENT08 | Central Park - Recons of Perimeter E84-E108ST WO# 8 | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CENT08 | Central Park - Recons of Perimeter E84-E108ST WO# 8 | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CENT08 | Central Park - Recons of Perimeter E84-E108ST WO# 8 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CENT13 | Recon. of Naumburg Bandshell in Central Park, WO#13, | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CENT13 | Recon. of Naumburg Bandshell in Central Park, WO#13, | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CENT13 | Recon. of Naumburg Bandshell in Central Park, WO#13, | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CENT13 | Recon. of Naumburg Bandshell in Central Park, WO#13, | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CENT13 | Recon. of Naumburg Bandshell in Central Park, WO#13, | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CENTA | Central Park - Construction for Maintanence & Operation | 1 | DEVELOP SCOPE | 2014-07-01 | 2014-09-28 | 2014-07-01 | 2014-09-28
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CENTA | Central Park - Construction for Maintanence & Operation | 2 | DESIGN | 2014-09-29 | 2014-12-27 | 2014-09-29 | 2015-01-06
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CENTA | Central Park - Construction for Maintanence & Operation | 3 | BID/ REGISTER CONTRACT | 2014-12-28 | 2015-03-27 | 2013-05-17 | 2013-07-03
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CENTA | Central Park - Construction for Maintanence & Operation | 4 | CONSTRUCTION | 2015-03-28 | 2016-03-26 | 2013-07-01 | 2023-06-30
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CENTA | Central Park - Construction for Maintanence & Operation | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-27 | 2017-03-26 | 2023-07-01 | 2024-06-29
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CHELPK | CHELSEA WATERSIDE PARK | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CHELPK | CHELSEA WATERSIDE PARK | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CHELPK | CHELSEA WATERSIDE PARK | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CHELPK | CHELSEA WATERSIDE PARK | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CHELPK | CHELSEA WATERSIDE PARK | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CHLENT | Chelsea Recreation Center Entrance Lobby Recon | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CHLENT | Chelsea Recreation Center Entrance Lobby Recon | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CHLENT | Chelsea Recreation Center Entrance Lobby Recon | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CHLENT | Chelsea Recreation Center Entrance Lobby Recon | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CHLENT | Chelsea Recreation Center Entrance Lobby Recon | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CMGWAT | Childrens Magical Garden:Drinking Fountain/Water Spigot | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CMGWAT | Childrens Magical Garden:Drinking Fountain/Water Spigot | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CMGWAT | Childrens Magical Garden:Drinking Fountain/Water Spigot | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CMGWAT | Childrens Magical Garden:Drinking Fountain/Water Spigot | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CMGWAT | Childrens Magical Garden:Drinking Fountain/Water Spigot | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3COLPCS | COLUMBUS PARK -RENOVATE COMFORT STATION ON WORTH STREET | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3COLPCS | COLUMBUS PARK -RENOVATE COMFORT STATION ON WORTH STREET | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3COLPCS | COLUMBUS PARK -RENOVATE COMFORT STATION ON WORTH STREET | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3COLPCS | COLUMBUS PARK -RENOVATE COMFORT STATION ON WORTH STREET | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3COLPCS | COLUMBUS PARK -RENOVATE COMFORT STATION ON WORTH STREET | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3COLUBT | COLUMBUS PARK - COLUMBUS PARK NEW TURF, Manhattan | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3COLUBT | COLUMBUS PARK - COLUMBUS PARK NEW TURF, Manhattan | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3COLUBT | COLUMBUS PARK - COLUMBUS PARK NEW TURF, Manhattan | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3COLUBT | COLUMBUS PARK - COLUMBUS PARK NEW TURF, Manhattan | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3COLUBT | COLUMBUS PARK - COLUMBUS PARK NEW TURF, Manhattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3COLUMB | COLUMBUS PARK - Entrance Renovation, Manhattan | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3COLUMB | COLUMBUS PARK - Entrance Renovation, Manhattan | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2016-12-28 | 2017-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3COLUMB | COLUMBUS PARK - Entrance Renovation, Manhattan | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2017-12-28 | 2018-09-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3COLUMB | COLUMBUS PARK - Entrance Renovation, Manhattan | 4 | CONSTRUCTION | 2018-09-24 | 2019-09-23 | 2018-09-24 | 2019-09-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3COLUMB | COLUMBUS PARK - Entrance Renovation, Manhattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPI3A2 | CPI PH2 - ABRAHAM LINCOLN CS RC | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPI3A2 | CPI PH2 - ABRAHAM LINCOLN CS RC | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPI3A2 | CPI PH2 - ABRAHAM LINCOLN CS RC | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPI3A2 | CPI PH2 - ABRAHAM LINCOLN CS RC | 4 | CONSTRUCTION | 2019-09-24 | 2021-03-21 | 2019-09-24 | 2021-03-21
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPI3A2 | CPI PH2 - ABRAHAM LINCOLN CS RC | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-22 | 2022-03-21 | 2021-03-22 | 2022-03-21
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPI3AB | CPI PH2 - Audubon Plg & Comf Reconstruction (DESIGN) | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPI3AB | CPI PH2 - Audubon Plg & Comf Reconstruction (DESIGN) | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPI3AB | CPI PH2 - Audubon Plg & Comf Reconstruction (DESIGN) | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPI3AB | CPI PH2 - Audubon Plg & Comf Reconstruction (DESIGN) | 4 | CONSTRUCTION | 2019-09-24 | 2021-03-21 | 2019-09-24 | 2021-03-21
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPI3AB | CPI PH2 - Audubon Plg & Comf Reconstruction (DESIGN) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-22 | 2022-03-21 | 2021-03-22 | 2022-03-21
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPI3AC | CPI PH2 - Audubon Comfort Station Recons M240-218M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPI3AC | CPI PH2 - Audubon Comfort Station Recons M240-218M | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPI3AC | CPI PH2 - Audubon Comfort Station Recons M240-218M | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPI3AC | CPI PH2 - Audubon Comfort Station Recons M240-218M | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPI3AC | CPI PH2 - Audubon Comfort Station Recons M240-218M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPI3AL | CPI PH2 - Abraham Lincoln plg .... | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPI3AL | CPI PH2 - Abraham Lincoln plg .... | 2 | DESIGN | 2017-12-28 | 2019-06-20 | 2017-12-28 | 2019-06-20
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPI3AL | CPI PH2 - Abraham Lincoln plg .... | 3 | BID/ REGISTER CONTRACT | 2019-06-21 | 2020-03-16 | 2019-06-21 | 2020-03-16
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPI3AL | CPI PH2 - Abraham Lincoln plg .... | 4 | CONSTRUCTION | 2020-03-17 | 2021-09-07 | 2020-03-17 | 2021-09-07
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPI3AL | CPI PH2 - Abraham Lincoln plg .... | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-08 | 2022-09-07 | 2021-09-08 | 2022-09-07
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPI3AP | CPI PH2 - Audubon Playground Reconst M240-118M | 1 | DEVELOP SCOPE | 2017-08-01 | 2018-01-27 | 2017-08-01 | 2018-01-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPI3AP | CPI PH2 - Audubon Playground Reconst M240-118M | 2 | DESIGN | 2018-01-28 | 2019-01-27 | 2018-01-28 | 2019-01-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPI3AP | CPI PH2 - Audubon Playground Reconst M240-118M | 3 | BID/ REGISTER CONTRACT | 2019-01-28 | 2019-10-24 | 2019-01-28 | 2019-10-24
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPI3AP | CPI PH2 - Audubon Playground Reconst M240-118M | 4 | CONSTRUCTION | 2019-10-25 | 2020-10-23 | 2019-10-25 | 2020-10-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPI3AP | CPI PH2 - Audubon Playground Reconst M240-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-10-24 | 2021-10-23 | 2020-10-24 | 2021-10-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIBBJ | CPI PH2 - Bill Bojangles Playground | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIBBJ | CPI PH2 - Bill Bojangles Playground | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIBBJ | CPI PH2 - Bill Bojangles Playground | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIBBJ | CPI PH2 - Bill Bojangles Playground | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIBBJ | CPI PH2 - Bill Bojangles Playground | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIBN9 | CPI PH1 Plg 103 and St Nicholas North Plg Recons (MG-216M) | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIBN9 | CPI PH1 Plg 103 and St Nicholas North Plg Recons (MG-216M) | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2016-12-28 | 2017-12-25
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIBN9 | CPI PH1 Plg 103 and St Nicholas North Plg Recons (MG-216M) | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2016-02-19 | 2016-10-24
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIBN9 | CPI PH1 Plg 103 and St Nicholas North Plg Recons (MG-216M) | 4 | CONSTRUCTION | 2018-09-24 | 2019-09-23 | 2016-11-28 | 2018-05-25
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIBN9 | CPI PH1 Plg 103 and St Nicholas North Plg Recons (MG-216M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-24 | 2020-09-22 | 2018-05-25 | 2019-05-24
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIFGC | CPI PH2 - Frederick Johnson Comfort Station, M141-418M | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIFGC | CPI PH2 - Frederick Johnson Comfort Station, M141-418M | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIFGC | CPI PH2 - Frederick Johnson Comfort Station, M141-418M | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIFGC | CPI PH2 - Frederick Johnson Comfort Station, M141-418M | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIFGC | CPI PH2 - Frederick Johnson Comfort Station, M141-418M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIFJP | CPI PH2 -Frederick Johnson Playground M159-219M | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIFJP | CPI PH2 -Frederick Johnson Playground M159-219M | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIFJP | CPI PH2 -Frederick Johnson Playground M159-219M | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIFJP | CPI PH2 -Frederick Johnson Playground M159-219M | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIFJP | CPI PH2 -Frederick Johnson Playground M159-219M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIHLP | CPI PH2 - Harlem Lane Playground, MG-119M | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIHLP | CPI PH2 - Harlem Lane Playground, MG-119M | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIHLP | CPI PH2 - Harlem Lane Playground, MG-119M | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIHLP | CPI PH2 - Harlem Lane Playground, MG-119M | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIHLP | CPI PH2 - Harlem Lane Playground, MG-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIJWJ | CPI - James Weldon Johnson Play (M111-115M) | 1 | DEVELOP SCOPE | 2014-07-01 | 2014-09-28 | 2014-07-01 | 2015-01-06
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIJWJ | CPI - James Weldon Johnson Play (M111-115M) | 2 | DESIGN | 2014-09-29 | 2014-12-27 | 2015-01-07 | 2016-04-15
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIJWJ | CPI - James Weldon Johnson Play (M111-115M) | 3 | BID/ REGISTER CONTRACT | 2014-12-28 | 2015-03-27 | 2016-03-29 | 2016-09-14
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIJWJ | CPI - James Weldon Johnson Play (M111-115M) | 4 | CONSTRUCTION | 2015-03-28 | 2016-03-26 | 2016-11-21 | 2018-02-16
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIJWJ | CPI - James Weldon Johnson Play (M111-115M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-27 | 2017-03-26 | 2018-02-16 | 2019-02-15
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIMLK | CPI - Phase 1-Martin L.King Plgr, Manhattan | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIMLK | CPI - Phase 1-Martin L.King Plgr, Manhattan | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2016-12-28 | 2017-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIMLK | CPI - Phase 1-Martin L.King Plgr, Manhattan | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2017-12-28 | 2018-09-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIMLK | CPI - Phase 1-Martin L.King Plgr, Manhattan | 4 | CONSTRUCTION | 2018-09-24 | 2019-09-23 | 2018-09-24 | 2019-09-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIMLK | CPI - Phase 1-Martin L.King Plgr, Manhattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIPGI | CPI PH2 -Playground One, M196-118M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIPGI | CPI PH2 -Playground One, M196-118M | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIPGI | CPI PH2 -Playground One, M196-118M | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIPGI | CPI PH2 -Playground One, M196-118M | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIPGI | CPI PH2 -Playground One, M196-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPISUR | CPI PH2 - Sauer Playground | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPISUR | CPI PH2 - Sauer Playground | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPISUR | CPI PH2 - Sauer Playground | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPISUR | CPI PH2 - Sauer Playground | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPISUR | CPI PH2 - Sauer Playground | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CSPBOL | Carl Schulz Pk- Construction Security Measures M081-120M | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CSPBOL | Carl Schulz Pk- Construction Security Measures M081-120M | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CSPBOL | Carl Schulz Pk- Construction Security Measures M081-120M | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CSPBOL | Carl Schulz Pk- Construction Security Measures M081-120M | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CSPBOL | Carl Schulz Pk- Construction Security Measures M081-120M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3DAGHAM | Dag Hammarskjold Plaza, Manhattan | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2017-05-31
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3DAGHAM | Dag Hammarskjold Plaza, Manhattan | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2017-06-01 | 2019-07-30
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3DAGHAM | Dag Hammarskjold Plaza, Manhattan | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2019-12-20 | 2020-03-30
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3DAGHAM | Dag Hammarskjold Plaza, Manhattan | 4 | CONSTRUCTION | 2018-09-24 | 2019-09-23 | 2020-09-25 | 2021-09-24
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3DAGHAM | Dag Hammarskjold Plaza, Manhattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-24 | 2020-09-22 | 2021-09-25 | 2022-09-24
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3DDOKPL | Recon pool deck at Dry Dock Pool, Manhattan | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3DDOKPL | Recon pool deck at Dry Dock Pool, Manhattan | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3DDOKPL | Recon pool deck at Dry Dock Pool, Manhattan | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3DDOKPL | Recon pool deck at Dry Dock Pool, Manhattan | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3DDOKPL | Recon pool deck at Dry Dock Pool, Manhattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3DELURY | Delury Square Renovation- Manhattan | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2017-11-03
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3DELURY | Delury Square Renovation- Manhattan | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2017-11-04 | 2018-11-16
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3DELURY | Delury Square Renovation- Manhattan | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2019-03-25 | 2019-08-13
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3DELURY | Delury Square Renovation- Manhattan | 4 | CONSTRUCTION | 2018-09-24 | 2019-09-23 | 2019-09-05 | 2020-09-04
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3DELURY | Delury Square Renovation- Manhattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-24 | 2020-09-22 | 2020-09-05 | 2021-09-04
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3DIRVPK | Riverside Park-Critical Drainage Infrastructure | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3DIRVPK | Riverside Park-Critical Drainage Infrastructure | 2 | DESIGN | 2019-12-28 | 2021-12-26 | 2019-12-28 | 2021-12-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3DIRVPK | Riverside Park-Critical Drainage Infrastructure | 3 | BID/ REGISTER CONTRACT | 2021-12-27 | 2022-09-22 | 2021-12-27 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3DIRVPK | Riverside Park-Critical Drainage Infrastructure | 4 | CONSTRUCTION | 2022-09-23 | 2024-09-21 | 2022-09-23 | 2024-09-21
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3DIRVPK | Riverside Park-Critical Drainage Infrastructure | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-09-22 | 2025-09-21 | 2024-09-22 | 2025-09-21
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3EAST54 | East 54th St Rec Ctr - Natatorium Ceiling/Men' locker FC R | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3EAST54 | East 54th St Rec Ctr - Natatorium Ceiling/Men' locker FC R | 2 | DESIGN | 2019-12-28 | 2021-12-26 | 2019-12-28 | 2021-12-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3EAST54 | East 54th St Rec Ctr - Natatorium Ceiling/Men' locker FC R | 3 | BID/ REGISTER CONTRACT | 2021-12-27 | 2022-09-22 | 2021-12-27 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3EAST54 | East 54th St Rec Ctr - Natatorium Ceiling/Men' locker FC R | 4 | CONSTRUCTION | 2022-09-23 | 2024-09-21 | 2022-09-23 | 2024-09-21
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3EAST54 | East 54th St Rec Ctr - Natatorium Ceiling/Men' locker FC R | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-09-22 | 2025-09-21 | 2024-09-22 | 2025-09-21
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3EHSKAT | EAST HARLEM SKATE PARK CONSTRUCTION (M047-116M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-03-27 | 2014-03-26 | 2018-03-05 | 2019-03-05
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3EMRTRN | Emergency replace of Randalls Island transformer M104-118M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3EMRTRN | Emergency replace of Randalls Island transformer M104-118M | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3EMRTRN | Emergency replace of Randalls Island transformer M104-118M | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3EMRTRN | Emergency replace of Randalls Island transformer M104-118M | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3EMRTRN | Emergency replace of Randalls Island transformer M104-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ESSTAT | ELIZABETH CADY STANTON AND SUSAN B. ANTHONY STATUE FUND INC | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ESSTAT | ELIZABETH CADY STANTON AND SUSAN B. ANTHONY STATUE FUND INC | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ESSTAT | ELIZABETH CADY STANTON AND SUSAN B. ANTHONY STATUE FUND INC | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ESSTAT | ELIZABETH CADY STANTON AND SUSAN B. ANTHONY STATUE FUND INC | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ESSTAT | ELIZABETH CADY STANTON AND SUSAN B. ANTHONY STATUE FUND INC | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3EXPENS | COLUMBUS PK BASEBALL FIELD SYNTHETIC TURF RECON M015-104M | 2 | DESIGN | 2006-09-29 | 2006-12-27 | 2006-09-29 | 2006-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3EXPENS | COLUMBUS PK BASEBALL FIELD SYNTHETIC TURF RECON M015-104M | 3 | BID/ REGISTER CONTRACT | 2006-12-28 | 2007-03-27 | 2006-12-28 | 2007-03-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3EXPENS | COLUMBUS PK BASEBALL FIELD SYNTHETIC TURF RECON M015-104M | 4 | CONSTRUCTION | 2007-03-28 | 2008-03-26 | 2007-03-28 | 2008-03-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3EXPENS | COLUMBUS PK BASEBALL FIELD SYNTHETIC TURF RECON M015-104M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-27 | 2009-03-26 | 2008-03-27 | 2009-03-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3FFAGAN | FATHER FAGAN PK LANDSCAPE RECON, MG-512M | 1 | DEVELOP SCOPE | 2011-07-01 | 2011-09-28 | 2011-07-01 | 2012-03-07
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3FFAGAN | FATHER FAGAN PK LANDSCAPE RECON, MG-512M | 2 | DESIGN | 2011-09-29 | 2011-12-27 | 2012-03-08 | 2016-01-14
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3FFAGAN | FATHER FAGAN PK LANDSCAPE RECON, MG-512M | 3 | BID/ REGISTER CONTRACT | 2011-12-28 | 2012-03-26 | 2016-05-17 | 2017-02-03
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3FFAGAN | FATHER FAGAN PK LANDSCAPE RECON, MG-512M | 4 | CONSTRUCTION | 2012-03-27 | 2013-03-26 | 2017-06-05 | 2018-05-08
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3FFAGAN | FATHER FAGAN PK LANDSCAPE RECON, MG-512M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-03-27 | 2014-03-26 | 2018-05-09 | 2019-05-08
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3FTRYON | Fort Tryon Park | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3FTRYON | Fort Tryon Park | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3FTRYON | Fort Tryon Park | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3FTRYON | Fort Tryon Park | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3FTRYON | Fort Tryon Park | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3GARVRF | Recon of Roofing systems at Marcus Garvey | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3GARVRF | Recon of Roofing systems at Marcus Garvey | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3GARVRF | Recon of Roofing systems at Marcus Garvey | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3GARVRF | Recon of Roofing systems at Marcus Garvey | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3GARVRF | Recon of Roofing systems at Marcus Garvey | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3GERCTE | GERTRUDE EDERLE RECREATION CENTER -- EQUIPMENT REPLACEMENT | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3GERCTE | GERTRUDE EDERLE RECREATION CENTER -- EQUIPMENT REPLACEMENT | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3GERCTE | GERTRUDE EDERLE RECREATION CENTER -- EQUIPMENT REPLACEMENT | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3GERCTE | GERTRUDE EDERLE RECREATION CENTER -- EQUIPMENT REPLACEMENT | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3GERCTE | GERTRUDE EDERLE RECREATION CENTER -- EQUIPMENT REPLACEMENT | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3GMHVAC | Gracie Mansion Improvements | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3GMHVAC | Gracie Mansion Improvements | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3GMHVAC | Gracie Mansion Improvements | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3GMHVAC | Gracie Mansion Improvements | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3GMHVAC | Gracie Mansion Improvements | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3GTACQM | Land Acuisition: Green Thumb on 143rd ST, Manhattan | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3GTACQM | Land Acuisition: Green Thumb on 143rd ST, Manhattan | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3GTACQM | Land Acuisition: Green Thumb on 143rd ST, Manhattan | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3GTACQM | Land Acuisition: Green Thumb on 143rd ST, Manhattan | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3GTACQM | Land Acuisition: Green Thumb on 143rd ST, Manhattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HBCGRD | Highbridge Community Garden | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2015-09-28
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HBCGRD | Highbridge Community Garden | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2015-09-29 | 2022-09-15
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HBCGRD | Highbridge Community Garden | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2022-12-28 | 2023-10-24
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HBCGRD | Highbridge Community Garden | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2022-03-26 | 2024-03-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HBCGRD | Highbridge Community Garden | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2024-03-28 | 2025-03-28
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HELIP2 | Heliport(Andrew Haswell) Park - phase 2 M108-109M | 1 | DEVELOP SCOPE | 2007-07-01 | 2007-09-28 | 2003-06-30 | 2004-04-14
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HELIP2 | Heliport(Andrew Haswell) Park - phase 2 M108-109M | 2 | DESIGN | 2007-09-29 | 2007-12-27 | 2004-04-15 | 2013-12-04
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HELIP2 | Heliport(Andrew Haswell) Park - phase 2 M108-109M | 3 | BID/ REGISTER CONTRACT | 2007-12-28 | 2008-03-26 | 2014-06-19 | 2015-06-02
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HELIP2 | Heliport(Andrew Haswell) Park - phase 2 M108-109M | 4 | CONSTRUCTION | 2008-03-27 | 2009-03-26 | 2015-08-05 | 2017-01-30
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HELIP2 | Heliport(Andrew Haswell) Park - phase 2 M108-109M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2009-03-27 | 2010-03-26 | 2017-02-01 | 2018-01-30
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HELLKT | DEP Shaft Site - Hell's Kitchen Park Construction | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HELLKT | DEP Shaft Site - Hell's Kitchen Park Construction | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HELLKT | DEP Shaft Site - Hell's Kitchen Park Construction | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HELLKT | DEP Shaft Site - Hell's Kitchen Park Construction | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HELLKT | DEP Shaft Site - Hell's Kitchen Park Construction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2022-10-20
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HGLNPH | HIGHLINE-Path replace Rail Track Rehab, Lead Paint, light | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HGLNPH | HIGHLINE-Path replace Rail Track Rehab, Lead Paint, light | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HGLNPH | HIGHLINE-Path replace Rail Track Rehab, Lead Paint, light | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HGLNPH | HIGHLINE-Path replace Rail Track Rehab, Lead Paint, light | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HGLNPH | HIGHLINE-Path replace Rail Track Rehab, Lead Paint, light | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HGLNRC | HIGHLINE Reconstruction, Misc Park & Playground., | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HGLNRC | HIGHLINE Reconstruction, Misc Park & Playground., | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HGLNRC | HIGHLINE Reconstruction, Misc Park & Playground., | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HGLNRC | HIGHLINE Reconstruction, Misc Park & Playground., | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HGLNRC | HIGHLINE Reconstruction, Misc Park & Playground., | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HIGHL3 | FRIENDS OF THE HIGH LINE- Western Rail Yards, Manhattan | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HIGHL3 | FRIENDS OF THE HIGH LINE- Western Rail Yards, Manhattan | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HIGHL3 | FRIENDS OF THE HIGH LINE- Western Rail Yards, Manhattan | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HIGHL3 | FRIENDS OF THE HIGH LINE- Western Rail Yards, Manhattan | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HIGHL3 | FRIENDS OF THE HIGH LINE- Western Rail Yards, Manhattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HLNSTR | FRIENDS OF THE HIGHLINE: HIGH LINE STAIR RECONSTRUCTION | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HLNSTR | FRIENDS OF THE HIGHLINE: HIGH LINE STAIR RECONSTRUCTION | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HLNSTR | FRIENDS OF THE HIGHLINE: HIGH LINE STAIR RECONSTRUCTION | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HLNSTR | FRIENDS OF THE HIGHLINE: HIGH LINE STAIR RECONSTRUCTION | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HLNSTR | FRIENDS OF THE HIGHLINE: HIGH LINE STAIR RECONSTRUCTION | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HMFISH | Hamilton Fish Park Basketball Courts and Adult Fitness | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HMFISH | Hamilton Fish Park Basketball Courts and Adult Fitness | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HMFISH | Hamilton Fish Park Basketball Courts and Adult Fitness | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HMFISH | Hamilton Fish Park Basketball Courts and Adult Fitness | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HMFISH | Hamilton Fish Park Basketball Courts and Adult Fitness | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HR2944 | HRPT - 29th to 44th Sts. Construction, Manhattan | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HR2944 | HRPT - 29th to 44th Sts. Construction, Manhattan | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HR2944 | HRPT - 29th to 44th Sts. Construction, Manhattan | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HR2944 | HRPT - 29th to 44th Sts. Construction, Manhattan | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HR2944 | HRPT - 29th to 44th Sts. Construction, Manhattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRP26U | HRPT: Pier 26 Upland Construction | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRP26U | HRPT: Pier 26 Upland Construction | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRP26U | HRPT: Pier 26 Upland Construction | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRP26U | HRPT: Pier 26 Upland Construction | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRP26U | HRPT: Pier 26 Upland Construction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRP40F | Pier 40 Athletic Fields Reconstruction | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRP40F | Pier 40 Athletic Fields Reconstruction | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRP40F | Pier 40 Athletic Fields Reconstruction | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRP40F | Pier 40 Athletic Fields Reconstruction | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRP40F | Pier 40 Athletic Fields Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRP40W | HRPT: Pier 40 Elevated Walkway Reconstruction | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRP40W | HRPT: Pier 40 Elevated Walkway Reconstruction | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRP40W | HRPT: Pier 40 Elevated Walkway Reconstruction | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRP40W | HRPT: Pier 40 Elevated Walkway Reconstruction | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRP40W | HRPT: Pier 40 Elevated Walkway Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRP54A | HRPT - Pier 54 Arch Restoration, Manhattan | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRP54A | HRPT - Pier 54 Arch Restoration, Manhattan | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRP54A | HRPT - Pier 54 Arch Restoration, Manhattan | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRP54A | HRPT - Pier 54 Arch Restoration, Manhattan | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRP54A | HRPT - Pier 54 Arch Restoration, Manhattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPCCV | HRPT-Clinton Cove Sculpture/Landscaping | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPCCV | HRPT-Clinton Cove Sculpture/Landscaping | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2016-12-28 | 2017-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPCCV | HRPT-Clinton Cove Sculpture/Landscaping | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2017-12-28 | 2018-09-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPCCV | HRPT-Clinton Cove Sculpture/Landscaping | 4 | CONSTRUCTION | 2018-09-24 | 2019-09-23 | 2018-09-24 | 2019-09-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPCCV | HRPT-Clinton Cove Sculpture/Landscaping | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPCW1 | HARRIET TUBMAN MEMORIAL BEAUTIFICATION, Manhattan | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPCW1 | HARRIET TUBMAN MEMORIAL BEAUTIFICATION, Manhattan | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPCW1 | HARRIET TUBMAN MEMORIAL BEAUTIFICATION, Manhattan | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPCW1 | HARRIET TUBMAN MEMORIAL BEAUTIFICATION, Manhattan | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPCW1 | HARRIET TUBMAN MEMORIAL BEAUTIFICATION, Manhattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPCWP | HRPT - Chelsea Waterside Park Phase 2 | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPCWP | HRPT - Chelsea Waterside Park Phase 2 | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2016-12-28 | 2017-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPCWP | HRPT - Chelsea Waterside Park Phase 2 | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2017-12-28 | 2018-09-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPCWP | HRPT - Chelsea Waterside Park Phase 2 | 4 | CONSTRUCTION | 2018-09-24 | 2019-09-23 | 2018-09-24 | 2019-09-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPCWP | HRPT - Chelsea Waterside Park Phase 2 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPDG8 | HUDSON RIVER PARK TRUST PIER 84 DOG RUN | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPDG8 | HUDSON RIVER PARK TRUST PIER 84 DOG RUN | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPDG8 | HUDSON RIVER PARK TRUST PIER 84 DOG RUN | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPDG8 | HUDSON RIVER PARK TRUST PIER 84 DOG RUN | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPDG8 | HUDSON RIVER PARK TRUST PIER 84 DOG RUN | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPP40 | Hudson River Park Trust - Pier 40 Repairs | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPP40 | Hudson River Park Trust - Pier 40 Repairs | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPP40 | Hudson River Park Trust - Pier 40 Repairs | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPP40 | Hudson River Park Trust - Pier 40 Repairs | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPP40 | Hudson River Park Trust - Pier 40 Repairs | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPT34 | HUDSON RIVER PARK | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPT34 | HUDSON RIVER PARK | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPT34 | HUDSON RIVER PARK | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPT34 | HUDSON RIVER PARK | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPT34 | HUDSON RIVER PARK | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPTPK | HRPT- Gansevoort Peninsula Park Construction., Manhattan | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPTPK | HRPT- Gansevoort Peninsula Park Construction., Manhattan | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPTPK | HRPT- Gansevoort Peninsula Park Construction., Manhattan | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPTPK | HRPT- Gansevoort Peninsula Park Construction., Manhattan | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPTPK | HRPT- Gansevoort Peninsula Park Construction., Manhattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3INHILL | Inwood Hill Park - Baseball fields,Manhattan | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2020-01-06
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3INHILL | Inwood Hill Park - Baseball fields,Manhattan | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2020-01-07 | 2021-01-14
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3INHILL | Inwood Hill Park - Baseball fields,Manhattan | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2021-04-30 | 2021-09-30
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3INHILL | Inwood Hill Park - Baseball fields,Manhattan | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2021-10-30 | 2022-10-31
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3INHILL | Inwood Hill Park - Baseball fields,Manhattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2022-10-31 | 2023-10-31
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3INWDPK | Inwood Hill Park | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3INWDPK | Inwood Hill Park | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3INWDPK | Inwood Hill Park | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3INWDPK | Inwood Hill Park | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3INWDPK | Inwood Hill Park | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3JHOODW | J. Hood Wright Park - Exer. Equip. Manhattan. | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2016-12-28 | 2017-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3JHOODW | J. Hood Wright Park - Exer. Equip. Manhattan. | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2017-12-28 | 2018-09-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3JHOODW | J. Hood Wright Park - Exer. Equip. Manhattan. | 4 | CONSTRUCTION | 2018-09-24 | 2019-09-23 | 2018-09-24 | 2019-09-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3JHOODW | J. Hood Wright Park - Exer. Equip. Manhattan. | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3LGGRDN | LAGUARDIA CORNER GARDEN FENCE, Mahattan | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3LGGRDN | LAGUARDIA CORNER GARDEN FENCE, Mahattan | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3LGGRDN | LAGUARDIA CORNER GARDEN FENCE, Mahattan | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3LGGRDN | LAGUARDIA CORNER GARDEN FENCE, Mahattan | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3LGGRDN | LAGUARDIA CORNER GARDEN FENCE, Mahattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3LGTURF | Little Flower Plg Synth. Turf Field Cons, Manhattan MG-316MA | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3LGTURF | Little Flower Plg Synth. Turf Field Cons, Manhattan MG-316MA | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3LGTURF | Little Flower Plg Synth. Turf Field Cons, Manhattan MG-316MA | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3LGTURF | Little Flower Plg Synth. Turf Field Cons, Manhattan MG-316MA | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3LGTURF | Little Flower Plg Synth. Turf Field Cons, Manhattan MG-316MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3LMDCCH | LMDC - Corlear's Hook Comfort Station M017-216M | 1 | DEVELOP SCOPE | 2014-07-01 | 2014-09-28 | 2014-07-01 | 2016-01-15
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3LMDCCH | LMDC - Corlear's Hook Comfort Station M017-216M | 2 | DESIGN | 2014-09-29 | 2014-12-27 | 2016-01-16 | 2017-04-14
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3LMDCCH | LMDC - Corlear's Hook Comfort Station M017-216M | 3 | BID/ REGISTER CONTRACT | 2014-12-28 | 2015-03-27 | 2017-04-15 | 2017-07-13
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3LMDCCH | LMDC - Corlear's Hook Comfort Station M017-216M | 4 | CONSTRUCTION | 2015-03-28 | 2016-03-26 | 2017-07-14 | 2018-07-13
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3LMDCCH | LMDC - Corlear's Hook Comfort Station M017-216M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-27 | 2017-03-26 | 2018-07-14 | 2019-07-13
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3MORJUM | MORRIS-JUMEL MANSION: TECHNOLOGY/ELECTRICAL UPGRADE | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3MORJUM | MORRIS-JUMEL MANSION: TECHNOLOGY/ELECTRICAL UPGRADE | 2 | DESIGN | 2019-12-28 | 2021-12-26 | 2019-12-28 | 2021-12-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3MORJUM | MORRIS-JUMEL MANSION: TECHNOLOGY/ELECTRICAL UPGRADE | 3 | BID/ REGISTER CONTRACT | 2021-12-27 | 2022-09-22 | 2021-12-27 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3MORJUM | MORRIS-JUMEL MANSION: TECHNOLOGY/ELECTRICAL UPGRADE | 4 | CONSTRUCTION | 2022-09-23 | 2024-09-21 | 2022-09-23 | 2024-09-21
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3MORJUM | MORRIS-JUMEL MANSION: TECHNOLOGY/ELECTRICAL UPGRADE | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-09-22 | 2025-09-21 | 2024-09-22 | 2025-09-21
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3MORNHR | MORNINGSIDE PARK HANDRAILS | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3MORNHR | MORNINGSIDE PARK HANDRAILS | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3MORNHR | MORNINGSIDE PARK HANDRAILS | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3MORNHR | MORNINGSIDE PARK HANDRAILS | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3MORNHR | MORNINGSIDE PARK HANDRAILS | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3MRNGPK | Morningstar Park | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3MRNGPK | Morningstar Park | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3MRNGPK | Morningstar Park | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3MRNGPK | Morningstar Park | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3MRNGPK | Morningstar Park | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3NRGF01 | NRG- Manhattan Reforestation FY 20- MG-619MA | 1 | DEVELOP SCOPE | 2020-07-01 | 2020-12-27 | 2020-07-01 | 2020-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3NRGF01 | NRG- Manhattan Reforestation FY 20- MG-619MA | 2 | DESIGN | 2020-12-28 | 2021-09-23 | 2020-12-28 | 2021-09-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3NRGF01 | NRG- Manhattan Reforestation FY 20- MG-619MA | 3 | BID/ REGISTER CONTRACT | 2021-09-24 | 2022-06-20 | 2021-09-24 | 2022-06-20
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3NRGF01 | NRG- Manhattan Reforestation FY 20- MG-619MA | 4 | CONSTRUCTION | 2022-06-21 | 2024-12-16 | 2022-06-21 | 2024-12-16
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3NRGF01 | NRG- Manhattan Reforestation FY 20- MG-619MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-12-17 | 2026-12-16 | 2024-12-17 | 2026-12-16
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3NYRS01 | ERP-Composting Facility & Wetland R/C M144-116M | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3NYRS01 | ERP-Composting Facility & Wetland R/C M144-116M | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3NYRS01 | ERP-Composting Facility & Wetland R/C M144-116M | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3NYRS01 | ERP-Composting Facility & Wetland R/C M144-116M | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3NYRS01 | ERP-Composting Facility & Wetland R/C M144-116M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3P40SPR | Hudson River Park Pier 40 Fire Sprinkler Recon | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3P40SPR | Hudson River Park Pier 40 Fire Sprinkler Recon | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3P40SPR | Hudson River Park Pier 40 Fire Sprinkler Recon | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3P40SPR | Hudson River Park Pier 40 Fire Sprinkler Recon | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3P40SPR | Hudson River Park Pier 40 Fire Sprinkler Recon | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PAVRSP | Riverside Park Pavement Path Reconstruction MG-519M | 4 | CONSTRUCTION | 2022-09-23 | 2024-09-21 | 2022-09-23 | 2024-09-21
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PAVRSP | Riverside Park Pavement Path Reconstruction MG-519M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-09-22 | 2025-09-21 | 2024-09-22 | 2025-09-21
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PAVTMK | Tompkins Sq Park Paths & Multi-Purpose Play Area Pave Recon | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PAVTMK | Tompkins Sq Park Paths & Multi-Purpose Play Area Pave Recon | 2 | DESIGN | 2019-12-28 | 2021-12-26 | 2019-12-28 | 2021-12-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PAVTMK | Tompkins Sq Park Paths & Multi-Purpose Play Area Pave Recon | 3 | BID/ REGISTER CONTRACT | 2021-12-27 | 2022-09-22 | 2021-12-27 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PAVTMK | Tompkins Sq Park Paths & Multi-Purpose Play Area Pave Recon | 4 | CONSTRUCTION | 2022-09-23 | 2024-09-21 | 2022-09-23 | 2024-09-21
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PAVTMK | Tompkins Sq Park Paths & Multi-Purpose Play Area Pave Recon | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-09-22 | 2025-09-21 | 2024-09-22 | 2025-09-21
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PBGHD7 | Public Greenhouse for District 7, Manhattan | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2015-12-28 | 2016-03-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PBGHD7 | Public Greenhouse for District 7, Manhattan | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PBGHD7 | Public Greenhouse for District 7, Manhattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2017-03-27 | 2018-03-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PDHBRC | Hansborough Rec Ctr M131-115M | 1 | DEVELOP SCOPE | 2014-07-01 | 2014-09-28 | 2014-07-01 | 2014-09-28
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PDHBRC | Hansborough Rec Ctr M131-115M | 2 | DESIGN | 2014-09-29 | 2014-12-27 | 2014-09-29 | 2014-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PDHBRC | Hansborough Rec Ctr M131-115M | 3 | BID/ REGISTER CONTRACT | 2014-12-28 | 2015-03-27 | 2014-12-28 | 2015-03-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PDHBRC | Hansborough Rec Ctr M131-115M | 4 | CONSTRUCTION | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2016-03-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PDHBRC | Hansborough Rec Ctr M131-115M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PDTDRC | Tony Dapolito Rec Ctr RC M103-115M | 1 | DEVELOP SCOPE | 2014-07-01 | 2014-09-28 | 2014-07-01 | 2014-09-28
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PDTDRC | Tony Dapolito Rec Ctr RC M103-115M | 2 | DESIGN | 2014-09-29 | 2014-12-27 | 2014-09-29 | 2014-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PDTDRC | Tony Dapolito Rec Ctr RC M103-115M | 3 | BID/ REGISTER CONTRACT | 2014-12-28 | 2015-03-27 | 2014-12-28 | 2015-03-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PDTDRC | Tony Dapolito Rec Ctr RC M103-115M | 4 | CONSTRUCTION | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2016-03-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PDTDRC | Tony Dapolito Rec Ctr RC M103-115M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PEDB81 | JOHN FINLEY WALK (EAST RIVER ESPLANADE), MG-316MA | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PEDB81 | JOHN FINLEY WALK (EAST RIVER ESPLANADE), MG-316MA | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PEDB81 | JOHN FINLEY WALK (EAST RIVER ESPLANADE), MG-316MA | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PEDB81 | JOHN FINLEY WALK (EAST RIVER ESPLANADE), MG-316MA | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PEDB81 | JOHN FINLEY WALK (EAST RIVER ESPLANADE), MG-316MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PGRGYM | Parks Green Gym | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2016-01-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PGRGYM | Parks Green Gym | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2016-01-23 | 2017-06-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PGRGYM | Parks Green Gym | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2017-10-04 | 2018-04-24
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PGRGYM | Parks Green Gym | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2018-05-14 | 2018-10-04
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PGRGYM | Parks Green Gym | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2018-10-05 | 2019-10-04
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PHILSQ | A. PHILLIP RANDOLPH SQUARE RENOVATION Manhattan | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PHILSQ | A. PHILLIP RANDOLPH SQUARE RENOVATION Manhattan | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PHILSQ | A. PHILLIP RANDOLPH SQUARE RENOVATION Manhattan | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PHILSQ | A. PHILLIP RANDOLPH SQUARE RENOVATION Manhattan | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PHILSQ | A. PHILLIP RANDOLPH SQUARE RENOVATION Manhattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PIN181 | PINEHURST AV/181ST - STAIRCASE/GARDEN UPGRADES | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PIN181 | PINEHURST AV/181ST - STAIRCASE/GARDEN UPGRADES | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PIN181 | PINEHURST AV/181ST - STAIRCASE/GARDEN UPGRADES | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PIN181 | PINEHURST AV/181ST - STAIRCASE/GARDEN UPGRADES | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PIN181 | PINEHURST AV/181ST - STAIRCASE/GARDEN UPGRADES | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PL12A1 | Reconstruction of plgr(Dante & Tucker Sqr), MG-112M | 1 | DEVELOP SCOPE | 2011-07-01 | 2011-09-28 | 2011-07-01 | 2011-09-28
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PL12A1 | Reconstruction of plgr(Dante & Tucker Sqr), MG-112M | 2 | DESIGN | 2011-09-29 | 2011-12-27 | 2011-09-29 | 2011-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PL12A1 | Reconstruction of plgr(Dante & Tucker Sqr), MG-112M | 3 | BID/ REGISTER CONTRACT | 2011-12-28 | 2012-03-26 | 2011-12-28 | 2012-03-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PL12A1 | Reconstruction of plgr(Dante & Tucker Sqr), MG-112M | 4 | CONSTRUCTION | 2012-03-27 | 2013-03-26 | 2012-03-27 | 2013-03-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PL12A1 | Reconstruction of plgr(Dante & Tucker Sqr), MG-112M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-03-27 | 2014-03-26 | 2013-03-27 | 2014-03-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PL12A4 | Gertrude Kelly Pk RC (MG-112M) WO#7 | 1 | DEVELOP SCOPE | 2012-07-01 | 2012-09-28 | 2012-07-01 | 2012-09-28
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PL12A4 | Gertrude Kelly Pk RC (MG-112M) WO#7 | 2 | DESIGN | 2012-09-29 | 2012-12-27 | 2012-09-29 | 2012-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PL12A4 | Gertrude Kelly Pk RC (MG-112M) WO#7 | 3 | BID/ REGISTER CONTRACT | 2012-12-28 | 2013-03-27 | 2012-12-28 | 2013-03-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PL12A4 | Gertrude Kelly Pk RC (MG-112M) WO#7 | 4 | CONSTRUCTION | 2013-03-28 | 2014-03-27 | 2013-03-28 | 2014-03-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PL12A4 | Gertrude Kelly Pk RC (MG-112M) WO#7 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-03-28 | 2015-03-27 | 2014-03-28 | 2015-03-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PL12A7 | Theodore Roosevelt Pk R/C, MG-112M | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2013-09-28
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PL12A7 | Theodore Roosevelt Pk R/C, MG-112M | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2013-09-29 | 2013-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PL12A7 | Theodore Roosevelt Pk R/C, MG-112M | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2013-12-28 | 2014-03-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PL12A7 | Theodore Roosevelt Pk R/C, MG-112M | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2014-03-28 | 2015-03-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PL12A7 | Theodore Roosevelt Pk R/C, MG-112M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2016-03-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PL14A6 | Ruppert Park-Install New Irrig.System MG-314M WO6 | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2020-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PL14A6 | Ruppert Park-Install New Irrig.System MG-314M WO6 | 2 | DESIGN | 2016-12-28 | 2018-06-25 | 2020-12-28 | 2026-06-25
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PL14A6 | Ruppert Park-Install New Irrig.System MG-314M WO6 | 3 | BID/ REGISTER CONTRACT | 2018-06-26 | 2019-03-22 | 2026-06-26 | 2026-09-05
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PL14A6 | Ruppert Park-Install New Irrig.System MG-314M WO6 | 4 | CONSTRUCTION | 2019-03-23 | 2020-09-17 | 2022-09-15 | 2023-09-17
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PL14A6 | Ruppert Park-Install New Irrig.System MG-314M WO6 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-18 | 2021-09-17 | 2023-09-18 | 2024-09-16
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PL16A1 | Reconstruction of Dekovats, Manhattan | 1 | DEVELOP SCOPE | 2018-05-22 | 2018-11-17 | 2018-05-22 | 2018-11-17
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PL16A1 | Reconstruction of Dekovats, Manhattan | 2 | DESIGN | 2018-11-18 | 2020-05-15 | 2018-11-18 | 2020-05-15
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PL16A1 | Reconstruction of Dekovats, Manhattan | 3 | BID/ REGISTER CONTRACT | 2020-05-16 | 2021-02-09 | 2020-05-16 | 2021-02-09
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PL16A1 | Reconstruction of Dekovats, Manhattan | 4 | CONSTRUCTION | 2021-02-10 | 2022-08-08 | 2021-02-10 | 2022-08-08
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PL16A1 | Reconstruction of Dekovats, Manhattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-08-09 | 2023-08-08 | 2022-08-09 | 2023-08-08
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PL16A2 | East River Esplanade Con Edison East 74th Street Reconstruct | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PL16A2 | East River Esplanade Con Edison East 74th Street Reconstruct | 2 | DESIGN | 2018-12-28 | 2020-06-24 | 2018-12-28 | 2020-06-24
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PL16A2 | East River Esplanade Con Edison East 74th Street Reconstruct | 3 | BID/ REGISTER CONTRACT | 2020-06-25 | 2021-03-21 | 2020-06-25 | 2021-03-21
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PL16A2 | East River Esplanade Con Edison East 74th Street Reconstruct | 4 | CONSTRUCTION | 2021-03-22 | 2022-09-17 | 2021-03-22 | 2022-09-17
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PL16A2 | East River Esplanade Con Edison East 74th Street Reconstruct | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-18 | 2023-09-17 | 2022-09-18 | 2023-09-17
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PLG12B | Sherman Creek Plyg, RC Manhattan(MG-112M) WO#8B | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2013-09-29 | 2013-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PLG12B | Sherman Creek Plyg, RC Manhattan(MG-112M) WO#8B | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2013-12-28 | 2014-03-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PLG12B | Sherman Creek Plyg, RC Manhattan(MG-112M) WO#8B | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2014-03-28 | 2015-03-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PLG12B | Sherman Creek Plyg, RC Manhattan(MG-112M) WO#8B | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2016-03-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PLG13B | Reconstruction of plgr, Borough of Manhattan MG-213M | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2013-09-28
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PLG13B | Reconstruction of plgr, Borough of Manhattan MG-213M | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2013-09-29 | 2014-05-30
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PLG13B | Reconstruction of plgr, Borough of Manhattan MG-213M | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2014-09-04 | 2015-06-01
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PLG13B | Reconstruction of plgr, Borough of Manhattan MG-213M | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2015-06-22 | 2016-12-15
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PLG13B | Reconstruction of plgr, Borough of Manhattan MG-213M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2016-12-16 | 2017-12-15
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PLG14B | R/C OF Playgrounds multisites FY14 Manhattan (MG-914MA) | 1 | DEVELOP SCOPE | 2014-07-01 | 2014-09-28 | 2014-07-01 | 2014-09-28
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PLG14B | R/C OF Playgrounds multisites FY14 Manhattan (MG-914MA) | 2 | DESIGN | 2014-09-29 | 2014-12-27 | 2014-09-29 | 2016-03-01
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PLG14B | R/C OF Playgrounds multisites FY14 Manhattan (MG-914MA) | 3 | BID/ REGISTER CONTRACT | 2014-12-28 | 2015-03-27 | 2016-08-17 | 2017-06-20
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PLG14B | R/C OF Playgrounds multisites FY14 Manhattan (MG-914MA) | 4 | CONSTRUCTION | 2015-03-28 | 2016-03-26 | 2017-07-17 | 2018-09-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PLG14B | R/C OF Playgrounds multisites FY14 Manhattan (MG-914MA) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-27 | 2017-03-26 | 2018-09-27 | 2019-09-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PLG155 | PS 155 PLAYGROUND | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PLG155 | PS 155 PLAYGROUND | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PLG155 | PS 155 PLAYGROUND | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PLG155 | PS 155 PLAYGROUND | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PLG155 | PS 155 PLAYGROUND | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PLG15B | Playground Requirements MG-714M | 1 | DEVELOP SCOPE | 2014-07-01 | 2014-09-28 | 2014-07-01 | 2014-09-28
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PLG15B | Playground Requirements MG-714M | 2 | DESIGN | 2014-09-29 | 2014-12-27 | 2014-09-29 | 2017-03-03
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PLG15B | Playground Requirements MG-714M | 3 | BID/ REGISTER CONTRACT | 2014-12-28 | 2015-03-27 | 2017-05-24 | 2017-12-13
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PLG15B | Playground Requirements MG-714M | 4 | CONSTRUCTION | 2015-03-28 | 2016-03-26 | 2018-03-05 | 2019-02-25
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PLG15B | Playground Requirements MG-714M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-27 | 2017-03-26 | 2019-02-26 | 2020-02-25
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PNYC04 | PlaNYC - Ft. Washington HRVG / Dyckman ADA Ramp (MG-609M) | 2 | DESIGN | 2009-09-29 | 2009-12-27 | 2007-09-22 | 2012-01-04
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PNYC04 | PlaNYC - Ft. Washington HRVG / Dyckman ADA Ramp (MG-609M) | 3 | BID/ REGISTER CONTRACT | 2009-12-28 | 2010-03-27 | 2012-04-16 | 2012-10-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PNYC04 | PlaNYC - Ft. Washington HRVG / Dyckman ADA Ramp (MG-609M) | 4 | CONSTRUCTION | 2010-03-28 | 2011-03-27 | 2012-12-10 | 2014-09-30
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PNYC04 | PlaNYC - Ft. Washington HRVG / Dyckman ADA Ramp (MG-609M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2011-03-28 | 2012-03-26 | 2014-09-29 | 2016-09-02
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3POORRD | POOR RICHARD'S PLAYGROUND RENOVATIONS, Mahattan | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2018-04-25
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3POORRD | POOR RICHARD'S PLAYGROUND RENOVATIONS, Mahattan | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2018-04-26 | 2020-04-30
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3POORRD | POOR RICHARD'S PLAYGROUND RENOVATIONS, Mahattan | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2021-01-06 | 2021-01-30
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3POORRD | POOR RICHARD'S PLAYGROUND RENOVATIONS, Mahattan | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2021-02-15 | 2022-02-14
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3POORRD | POOR RICHARD'S PLAYGROUND RENOVATIONS, Mahattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2022-02-14 | 2023-02-14
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PS155M | PS155M Playground , Manhattan | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PS155M | PS155M Playground , Manhattan | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2019-12-28 | 2025-01-19
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PS155M | PS155M Playground , Manhattan | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2022-05-25 | 2022-09-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PS155M | PS155M Playground , Manhattan | 4 | CONSTRUCTION | 2018-09-24 | 2019-09-23 | 2022-09-24 | 2023-09-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PS155M | PS155M Playground , Manhattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-24 | 2020-09-22 | 2023-09-24 | 2024-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PWBJRP | PWOB - Jackie Robinson Pk stairways, fencing, sidewalks, (M | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PWBJRP | PWOB - Jackie Robinson Pk stairways, fencing, sidewalks, (M | 2 | DESIGN | 2016-12-28 | 2018-03-22 | 2016-12-28 | 2018-03-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PWBJRP | PWOB - Jackie Robinson Pk stairways, fencing, sidewalks, (M | 3 | BID/ REGISTER CONTRACT | 2018-03-23 | 2018-12-17 | 2018-03-23 | 2018-12-17
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PWBJRP | PWOB - Jackie Robinson Pk stairways, fencing, sidewalks, (M | 4 | CONSTRUCTION | 2018-12-18 | 2020-12-16 | 2018-12-18 | 2020-12-16
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PWBJRP | PWOB - Jackie Robinson Pk stairways, fencing, sidewalks, (M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-12-17 | 2021-12-16 | 2020-12-17 | 2021-12-16
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PWBSEP | PWB - Seward Park (Manhattan), M082-117M | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-11-14
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PWBSEP | PWB - Seward Park (Manhattan), M082-117M | 2 | DESIGN | 2016-12-28 | 2018-03-22 | 2016-11-15 | 2017-12-28
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PWBSEP | PWB - Seward Park (Manhattan), M082-117M | 3 | BID/ REGISTER CONTRACT | 2018-03-23 | 2018-12-17 | 2018-04-25 | 2018-10-10
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PWBSEP | PWB - Seward Park (Manhattan), M082-117M | 4 | CONSTRUCTION | 2018-12-18 | 2020-12-16 | 2018-11-26 | 2019-11-25
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PWBSEP | PWB - Seward Park (Manhattan), M082-117M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-12-17 | 2021-12-16 | 2019-11-26 | 2020-11-25
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3QUISCS | Quisqueya Playground-Reconstruction of Comfort Station | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3QUISCS | Quisqueya Playground-Reconstruction of Comfort Station | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3QUISCS | Quisqueya Playground-Reconstruction of Comfort Station | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3QUISCS | Quisqueya Playground-Reconstruction of Comfort Station | 4 | CONSTRUCTION | 2019-09-24 | 2021-03-21 | 2019-09-24 | 2021-03-21
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3QUISCS | Quisqueya Playground-Reconstruction of Comfort Station | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-22 | 2022-03-21 | 2021-03-22 | 2022-03-21
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RANDSC | Randall's Island Sunken Garden Connector | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RANDSC | Randall's Island Sunken Garden Connector | 2 | DESIGN | 2019-12-28 | 2021-12-26 | 2019-12-28 | 2021-12-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RANDSC | Randall's Island Sunken Garden Connector | 3 | BID/ REGISTER CONTRACT | 2021-12-27 | 2022-09-22 | 2021-12-27 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RANDSC | Randall's Island Sunken Garden Connector | 4 | CONSTRUCTION | 2022-09-23 | 2024-09-21 | 2022-09-23 | 2024-09-21
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RANDSC | Randall's Island Sunken Garden Connector | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-09-22 | 2025-09-21 | 2024-09-22 | 2025-09-21
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RANDVC | RANDALL'S ISLAND VIISITOR CENTER | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RANDVC | RANDALL'S ISLAND VIISITOR CENTER | 2 | DESIGN | 2019-12-28 | 2021-12-26 | 2019-12-28 | 2021-12-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RANDVC | RANDALL'S ISLAND VIISITOR CENTER | 3 | BID/ REGISTER CONTRACT | 2021-12-27 | 2022-09-22 | 2021-12-27 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RANDVC | RANDALL'S ISLAND VIISITOR CENTER | 4 | CONSTRUCTION | 2022-09-23 | 2024-09-21 | 2022-09-23 | 2024-09-21
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RANDVC | RANDALL'S ISLAND VIISITOR CENTER | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-09-22 | 2025-09-21 | 2024-09-22 | 2025-09-21
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3REC54E | RECREATION CTR 54 FITNESS EQUIPMENT-FUNDING FOR NEW FITNESS | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3REC54E | RECREATION CTR 54 FITNESS EQUIPMENT-FUNDING FOR NEW FITNESS | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3REC54E | RECREATION CTR 54 FITNESS EQUIPMENT-FUNDING FOR NEW FITNESS | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3REC54E | RECREATION CTR 54 FITNESS EQUIPMENT-FUNDING FOR NEW FITNESS | 4 | CONSTRUCTION | 2021-09-23 | 2023-03-21 | 2021-09-23 | 2023-03-21
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3REC54E | RECREATION CTR 54 FITNESS EQUIPMENT-FUNDING FOR NEW FITNESS | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-03-22 | 2024-03-20 | 2023-03-22 | 2024-03-20
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RIV105 | Riversidw Park, 105Street | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RIV105 | Riversidw Park, 105Street | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RIV105 | Riversidw Park, 105Street | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RIV105 | Riversidw Park, 105Street | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RIV105 | Riversidw Park, 105Street | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RIV110 | Riverside Park, 110 Street | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RIV110 | Riverside Park, 110 Street | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RIV110 | Riverside Park, 110 Street | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RIV110 | Riverside Park, 110 Street | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RIV110 | Riverside Park, 110 Street | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RIV148 | Riverside Park, 148 Street | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RIV148 | Riverside Park, 148 Street | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RIV148 | Riverside Park, 148 Street | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RIV148 | Riverside Park, 148 Street | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RIV148 | Riverside Park, 148 Street | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RIVFTW | Shoreline Work in Riverside and Fort Washington Parks | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-18 | 2023-09-17 | 2022-09-18 | 2023-09-17
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RIVJOA | Riverside Park - Joan of Arc Island, Manhattan ( MG-318M) | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RIVJOA | Riverside Park - Joan of Arc Island, Manhattan ( MG-318M) | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2016-12-28 | 2017-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RIVJOA | Riverside Park - Joan of Arc Island, Manhattan ( MG-318M) | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2017-12-28 | 2018-09-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RIVJOA | Riverside Park - Joan of Arc Island, Manhattan ( MG-318M) | 4 | CONSTRUCTION | 2018-09-24 | 2019-09-23 | 2018-09-24 | 2019-09-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RIVJOA | Riverside Park - Joan of Arc Island, Manhattan ( MG-318M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RIVS83 | Riverside Park, 83rd Street | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RIVS83 | Riverside Park, 83rd Street | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RIVS83 | Riverside Park, 83rd Street | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RIVS83 | Riverside Park, 83rd Street | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RIVS83 | Riverside Park, 83rd Street | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RIVS97 | Riverside Park, 97th Street | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RIVS97 | Riverside Park, 97th Street | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RIVS97 | Riverside Park, 97th Street | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RIVS97 | Riverside Park, 97th Street | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RIVS97 | Riverside Park, 97th Street | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RIVSTR | RIVERSIDE PARK--102nd ST Staircase, Manhattan | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2018-10-01
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RIVSTR | RIVERSIDE PARK--102nd ST Staircase, Manhattan | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2018-10-02 | 2020-01-30
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RIVSTR | RIVERSIDE PARK--102nd ST Staircase, Manhattan | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2020-08-30 | 2020-12-30
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RIVSTR | RIVERSIDE PARK--102nd ST Staircase, Manhattan | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2021-02-28 | 2022-02-28
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RIVSTR | RIVERSIDE PARK--102nd ST Staircase, Manhattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2022-02-28 | 2023-03-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RNDLGL | Recon gas line at Randalls Island | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RNDLGL | Recon gas line at Randalls Island | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RNDLGL | Recon gas line at Randalls Island | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RNDLGL | Recon gas line at Randalls Island | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RNDLGL | Recon gas line at Randalls Island | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RNDLOT | Randall's Island PEP Office Trailer Parking Lot M104-118M | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RNDLOT | Randall's Island PEP Office Trailer Parking Lot M104-118M | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RNDLOT | Randall's Island PEP Office Trailer Parking Lot M104-118M | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RNDLOT | Randall's Island PEP Office Trailer Parking Lot M104-118M | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RNDLOT | Randall's Island PEP Office Trailer Parking Lot M104-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RSOVAL | Riverside Oval: Water Line Hookup | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RSOVAL | Riverside Oval: Water Line Hookup | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RSOVAL | Riverside Oval: Water Line Hookup | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RSOVAL | Riverside Oval: Water Line Hookup | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RSOVAL | Riverside Oval: Water Line Hookup | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RVPFWP | Riverside Park and Fort Washington Park Greenway Reconstruct | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RVPFWP | Riverside Park and Fort Washington Park Greenway Reconstruct | 2 | DESIGN | 2019-12-28 | 2021-06-24 | 2019-12-28 | 2021-06-24
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RVPFWP | Riverside Park and Fort Washington Park Greenway Reconstruct | 3 | BID/ REGISTER CONTRACT | 2021-06-25 | 2022-03-21 | 2021-06-25 | 2022-03-21
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RVPFWP | Riverside Park and Fort Washington Park Greenway Reconstruct | 4 | CONSTRUCTION | 2022-03-22 | 2023-09-17 | 2022-03-22 | 2023-09-17
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RVPFWP | Riverside Park and Fort Washington Park Greenway Reconstruct | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-18 | 2024-09-16 | 2023-09-18 | 2024-09-16
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RVSSCA | Riverside Pk-Skate park at 109 St., M071-115MA | 1 | DEVELOP SCOPE | 2014-07-01 | 2014-09-28 | 2014-07-01 | 2014-09-28
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RVSSCA | Riverside Pk-Skate park at 109 St., M071-115MA | 2 | DESIGN | 2014-09-29 | 2014-12-27 | 2014-09-29 | 2014-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RVSSCA | Riverside Pk-Skate park at 109 St., M071-115MA | 3 | BID/ REGISTER CONTRACT | 2014-12-28 | 2015-03-27 | 2014-12-28 | 2015-03-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RVSSCA | Riverside Pk-Skate park at 109 St., M071-115MA | 4 | CONSTRUCTION | 2015-03-28 | 2016-03-26 | 2018-02-01 | 2019-02-01
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RVSSCA | Riverside Pk-Skate park at 109 St., M071-115MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-27 | 2017-03-26 | 2019-02-01 | 2021-02-28
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SEWARD | SEWARD PARK- RESTORATION OF SCHIFF FOUNTAIN | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2020-06-20
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SEWARD | SEWARD PARK- RESTORATION OF SCHIFF FOUNTAIN | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2020-06-21 | 2024-06-20
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SEWARD | SEWARD PARK- RESTORATION OF SCHIFF FOUNTAIN | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2022-05-24 | 2022-09-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SEWARD | SEWARD PARK- RESTORATION OF SCHIFF FOUNTAIN | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2022-09-24 | 2023-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SEWARD | SEWARD PARK- RESTORATION OF SCHIFF FOUNTAIN | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2023-09-23 | 2024-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SHARCS | Sheltering Arms Playgound Comfort Station | 1 | DEVELOP SCOPE | 2019-02-01 | 2019-07-30 | 2019-02-01 | 2019-07-30
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SHARCS | Sheltering Arms Playgound Comfort Station | 2 | DESIGN | 2019-07-31 | 2020-07-29 | 2019-07-31 | 2020-07-29
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SHARCS | Sheltering Arms Playgound Comfort Station | 3 | BID/ REGISTER CONTRACT | 2020-07-30 | 2021-04-25 | 2020-07-30 | 2021-04-25
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SHARCS | Sheltering Arms Playgound Comfort Station | 4 | CONSTRUCTION | 2021-04-26 | 2022-10-22 | 2021-04-26 | 2022-10-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SHARCS | Sheltering Arms Playgound Comfort Station | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-10-23 | 2023-10-22 | 2022-10-23 | 2023-10-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SHERMC | SHERMAN CREEK PARK | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SHERMC | SHERMAN CREEK PARK | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SHERMC | SHERMAN CREEK PARK | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SHERMC | SHERMAN CREEK PARK | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SHERMC | SHERMAN CREEK PARK | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SOHAGS | Green Street Fencing - Amsterdam Ave and 126th St. | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SOHAGS | Green Street Fencing - Amsterdam Ave and 126th St. | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SOHAGS | Green Street Fencing - Amsterdam Ave and 126th St. | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SOHAGS | Green Street Fencing - Amsterdam Ave and 126th St. | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SOHAGS | Green Street Fencing - Amsterdam Ave and 126th St. | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SRAWIN | BRC Senior Center in Sara D., Park (MN) window replace | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SRAWIN | BRC Senior Center in Sara D., Park (MN) window replace | 2 | DESIGN | 2019-12-28 | 2021-12-26 | 2019-12-28 | 2021-12-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SRAWIN | BRC Senior Center in Sara D., Park (MN) window replace | 3 | BID/ REGISTER CONTRACT | 2021-12-27 | 2022-09-22 | 2021-12-27 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SRAWIN | BRC Senior Center in Sara D., Park (MN) window replace | 4 | CONSTRUCTION | 2022-09-23 | 2024-09-21 | 2022-09-23 | 2024-09-21
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SRAWIN | BRC Senior Center in Sara D., Park (MN) window replace | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-09-22 | 2025-09-21 | 2024-09-22 | 2025-09-21
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3STFWAG | STF - Wagner Playground Synthetic turf field, Manhattan | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2017-09-12
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3STFWAG | STF - Wagner Playground Synthetic turf field, Manhattan | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2017-09-13 | 2019-05-24
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3STFWAG | STF - Wagner Playground Synthetic turf field, Manhattan | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2019-05-08 | 2019-12-12
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3STFWAG | STF - Wagner Playground Synthetic turf field, Manhattan | 4 | CONSTRUCTION | 2018-09-24 | 2019-09-23 | 2020-03-20 | 2021-03-19
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3STFWAG | STF - Wagner Playground Synthetic turf field, Manhattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-24 | 2020-09-22 | 2021-03-20 | 2022-03-19
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3STNICK | St. Nicholas Park | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3STNICK | St. Nicholas Park | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3STNICK | St. Nicholas Park | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3STNICK | St. Nicholas Park | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3STNICK | St. Nicholas Park | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SUTTON | ONE SUTTON PLACE PARK CONSTRUCTION (M108-111M) | 1 | DEVELOP SCOPE | 2008-07-01 | 2008-09-28 | 2008-07-01 | 2008-09-28
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SUTTON | ONE SUTTON PLACE PARK CONSTRUCTION (M108-111M) | 2 | DESIGN | 2008-09-29 | 2008-12-27 | 2012-03-31 | 2013-06-30
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SUTTON | ONE SUTTON PLACE PARK CONSTRUCTION (M108-111M) | 3 | BID/ REGISTER CONTRACT | 2008-12-28 | 2009-03-27 | 2013-07-01 | 2013-12-01
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SUTTON | ONE SUTTON PLACE PARK CONSTRUCTION (M108-111M) | 4 | CONSTRUCTION | 2009-03-28 | 2010-03-27 | 2017-03-14 | 2018-03-15
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SUTTON | ONE SUTTON PLACE PARK CONSTRUCTION (M108-111M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2010-03-28 | 2011-03-27 | 2018-03-16 | 2019-06-30
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SUTTPK | SUTTON PLACE PARK.- Fountain & Spray Shower, Mahattan | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SUTTPK | SUTTON PLACE PARK.- Fountain & Spray Shower, Mahattan | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2019-12-28 | 2023-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SUTTPK | SUTTON PLACE PARK.- Fountain & Spray Shower, Mahattan | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2023-12-28 | 2024-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SUTTPK | SUTTON PLACE PARK.- Fountain & Spray Shower, Mahattan | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2024-09-23 | 2025-09-21
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SUTTPK | SUTTON PLACE PARK.- Fountain & Spray Shower, Mahattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2025-09-22 | 2026-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TOMJPK | Thomas Jefferson Park Plg Reconst. Mahattan (M047-118M) | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TOMJPK | Thomas Jefferson Park Plg Reconst. Mahattan (M047-118M) | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TOMJPK | Thomas Jefferson Park Plg Reconst. Mahattan (M047-118M) | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TOMJPK | Thomas Jefferson Park Plg Reconst. Mahattan (M047-118M) | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TOMJPK | Thomas Jefferson Park Plg Reconst. Mahattan (M047-118M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TONYDL | Tony Dapolito RC Ctr 7th Ave Sidewalk Vault & Pool Stb rest | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TONYDL | Tony Dapolito RC Ctr 7th Ave Sidewalk Vault & Pool Stb rest | 2 | DESIGN | 2019-12-28 | 2021-12-26 | 2019-12-28 | 2021-12-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TONYDL | Tony Dapolito RC Ctr 7th Ave Sidewalk Vault & Pool Stb rest | 3 | BID/ REGISTER CONTRACT | 2021-12-27 | 2022-09-22 | 2021-12-27 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TONYDL | Tony Dapolito RC Ctr 7th Ave Sidewalk Vault & Pool Stb rest | 4 | CONSTRUCTION | 2022-09-23 | 2024-09-21 | 2022-09-23 | 2024-09-21
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TONYDL | Tony Dapolito RC Ctr 7th Ave Sidewalk Vault & Pool Stb rest | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-09-22 | 2025-09-21 | 2024-09-22 | 2025-09-21
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TRE18A | FY 18 Street Tree Mnht CB 2,4,7,9,10,12 | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TRE18A | FY 18 Street Tree Mnht CB 2,4,7,9,10,12 | 2 | DESIGN | 2017-12-28 | 2018-06-25 | 2017-12-28 | 2018-06-25
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TRE18A | FY 18 Street Tree Mnht CB 2,4,7,9,10,12 | 3 | BID/ REGISTER CONTRACT | 2018-06-26 | 2019-03-22 | 2018-06-26 | 2019-03-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TRE18A | FY 18 Street Tree Mnht CB 2,4,7,9,10,12 | 4 | CONSTRUCTION | 2019-03-23 | 2020-09-12 | 2019-03-23 | 2020-09-12
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TRE18A | FY 18 Street Tree Mnht CB 2,4,7,9,10,12 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-13 | 2022-09-12 | 2020-09-13 | 2022-09-12
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TRE18B | FY 18 Street Tree Mnht CB 1,3,5,6,8,11 | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TRE18B | FY 18 Street Tree Mnht CB 1,3,5,6,8,11 | 2 | DESIGN | 2017-12-28 | 2018-06-25 | 2017-12-28 | 2018-06-25
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TRE18B | FY 18 Street Tree Mnht CB 1,3,5,6,8,11 | 3 | BID/ REGISTER CONTRACT | 2018-06-26 | 2019-03-22 | 2018-06-26 | 2019-03-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TRE18B | FY 18 Street Tree Mnht CB 1,3,5,6,8,11 | 4 | CONSTRUCTION | 2019-03-23 | 2020-09-12 | 2019-03-23 | 2020-09-12
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TRE18B | FY 18 Street Tree Mnht CB 1,3,5,6,8,11 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-13 | 2022-09-12 | 2020-09-13 | 2022-09-12
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TRE20A | FY 20 Street Tree Mnht CB 1,3,5,6,8,11 MG-319M | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TRE20A | FY 20 Street Tree Mnht CB 1,3,5,6,8,11 MG-319M | 2 | DESIGN | 2018-12-28 | 2019-06-25 | 2018-12-28 | 2019-06-25
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TRE20A | FY 20 Street Tree Mnht CB 1,3,5,6,8,11 MG-319M | 3 | BID/ REGISTER CONTRACT | 2019-06-26 | 2020-03-21 | 2019-06-26 | 2020-03-21
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TRE20A | FY 20 Street Tree Mnht CB 1,3,5,6,8,11 MG-319M | 4 | CONSTRUCTION | 2020-03-22 | 2021-09-12 | 2020-03-22 | 2021-09-12
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TRE20A | FY 20 Street Tree Mnht CB 1,3,5,6,8,11 MG-319M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-13 | 2023-09-12 | 2021-09-13 | 2023-09-12
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TREL21 | FY21 Street Trees MN CB's 1,2,4,5,,7-12 (3Y) | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TREL21 | FY21 Street Trees MN CB's 1,2,4,5,,7-12 (3Y) | 2 | DESIGN | 2019-12-28 | 2021-06-19 | 2019-12-28 | 2021-06-19
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TREL21 | FY21 Street Trees MN CB's 1,2,4,5,,7-12 (3Y) | 3 | BID/ REGISTER CONTRACT | 2021-06-20 | 2022-03-16 | 2021-06-20 | 2022-03-16
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TREL21 | FY21 Street Trees MN CB's 1,2,4,5,,7-12 (3Y) | 4 | CONSTRUCTION | 2022-03-17 | 2025-03-15 | 2022-03-17 | 2025-03-15
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TREL21 | FY21 Street Trees MN CB's 1,2,4,5,,7-12 (3Y) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-03-16 | 2027-03-15 | 2025-03-16 | 2027-03-15
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TRESM2 | Manhattan-Street trees CB2 MG-919M | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TRESM2 | Manhattan-Street trees CB2 MG-919M | 2 | DESIGN | 2019-12-28 | 2020-06-24 | 2019-12-28 | 2020-06-24
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TRESM2 | Manhattan-Street trees CB2 MG-919M | 3 | BID/ REGISTER CONTRACT | 2020-06-25 | 2021-03-21 | 2020-06-25 | 2021-03-21
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TRESM2 | Manhattan-Street trees CB2 MG-919M | 4 | CONSTRUCTION | 2021-03-22 | 2022-09-12 | 2021-03-22 | 2022-09-12
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TRESM2 | Manhattan-Street trees CB2 MG-919M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-13 | 2024-09-11 | 2022-09-13 | 2024-09-11
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TRESM3 | Manhattan-Street trees CB3 - MG-1019M | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TRESM3 | Manhattan-Street trees CB3 - MG-1019M | 2 | DESIGN | 2019-12-28 | 2020-06-24 | 2019-12-28 | 2020-06-24
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TRESM3 | Manhattan-Street trees CB3 - MG-1019M | 3 | BID/ REGISTER CONTRACT | 2020-06-25 | 2021-03-21 | 2020-06-25 | 2021-03-21
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TRESM3 | Manhattan-Street trees CB3 - MG-1019M | 4 | CONSTRUCTION | 2021-03-22 | 2022-09-12 | 2021-03-22 | 2022-09-12
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TRESM3 | Manhattan-Street trees CB3 - MG-1019M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-13 | 2024-09-11 | 2022-09-13 | 2024-09-11
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TRESM4 | Manhattan-Street trees CB4 - MG-1119M | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TRESM4 | Manhattan-Street trees CB4 - MG-1119M | 2 | DESIGN | 2019-12-28 | 2020-06-24 | 2019-12-28 | 2020-06-24
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TRESM4 | Manhattan-Street trees CB4 - MG-1119M | 3 | BID/ REGISTER CONTRACT | 2020-06-25 | 2021-03-21 | 2020-06-25 | 2021-03-21
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TRESM4 | Manhattan-Street trees CB4 - MG-1119M | 4 | CONSTRUCTION | 2021-03-22 | 2022-09-12 | 2021-03-22 | 2022-09-12
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TRESM4 | Manhattan-Street trees CB4 - MG-1119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-13 | 2024-09-11 | 2022-09-13 | 2024-09-11
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3W185BC | WEST 186TH ST BASKEBALL COURTS, Manhattan | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3W185BC | WEST 186TH ST BASKEBALL COURTS, Manhattan | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3W185BC | WEST 186TH ST BASKEBALL COURTS, Manhattan | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3W185BC | WEST 186TH ST BASKEBALL COURTS, Manhattan | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3W185BC | WEST 186TH ST BASKEBALL COURTS, Manhattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3W69SB2 | West 69th Street transverse bridge - phase 2 M353-212M | 1 | DEVELOP SCOPE | 2006-07-01 | 2006-09-28 | 2006-07-01 | 2007-08-29
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3W69SB2 | West 69th Street transverse bridge - phase 2 M353-212M | 2 | DESIGN | 2006-09-29 | 2006-12-27 | 2007-08-30 | 2019-05-24
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3W69SB2 | West 69th Street transverse bridge - phase 2 M353-212M | 3 | BID/ REGISTER CONTRACT | 2006-12-28 | 2007-03-27 | 2019-12-20 | 2020-08-05
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3W69SB2 | West 69th Street transverse bridge - phase 2 M353-212M | 4 | CONSTRUCTION | 2007-03-28 | 2008-03-26 | 2020-09-10 | 2021-09-21
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3W69SB2 | West 69th Street transverse bridge - phase 2 M353-212M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-27 | 2009-03-26 | 2021-09-22 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-5STFMHN | Synthetic Turf Field Reconstruction at Mahoney Park, SI | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-5STFMHN | Synthetic Turf Field Reconstruction at Mahoney Park, SI | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-5STFMHN | Synthetic Turf Field Reconstruction at Mahoney Park, SI | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-5STFMHN | Synthetic Turf Field Reconstruction at Mahoney Park, SI | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-5STFMHN | Synthetic Turf Field Reconstruction at Mahoney Park, SI | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-6STFMAT | Purchase syn turf materials to recon fields in Manhattan | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-6STFMAT | Purchase syn turf materials to recon fields in Manhattan | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-6STFMAT | Purchase syn turf materials to recon fields in Manhattan | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-6STFMAT | Purchase syn turf materials to recon fields in Manhattan | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-6STFMAT | Purchase syn turf materials to recon fields in Manhattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SAND3TREE | FY21- ESCR Tree Planting, Manhattan MG-1219M | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SAND3TREE | FY21- ESCR Tree Planting, Manhattan MG-1219M | 2 | DESIGN | 2019-12-28 | 2021-06-19 | 2019-12-28 | 2021-06-19
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SAND3TREE | FY21- ESCR Tree Planting, Manhattan MG-1219M | 3 | BID/ REGISTER CONTRACT | 2021-06-20 | 2022-03-16 | 2021-06-20 | 2022-03-16
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SAND3TREE | FY21- ESCR Tree Planting, Manhattan MG-1219M | 4 | CONSTRUCTION | 2022-03-17 | 2024-03-15 | 2022-03-17 | 2024-03-15
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SAND3TREE | FY21- ESCR Tree Planting, Manhattan MG-1219M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-03-16 | 2026-03-15 | 2024-03-16 | 2026-03-15
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-02 | SANDY - Manhattan Plgd requirements (Type 1) MG-112M | 1 | DEVELOP SCOPE | 2012-12-01 | 2013-02-28 | 2012-12-01 | 2013-02-28
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-02 | SANDY - Manhattan Plgd requirements (Type 1) MG-112M | 2 | DESIGN | 2013-03-01 | 2013-05-29 | 2013-03-01 | 2013-05-29
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-02 | SANDY - Manhattan Plgd requirements (Type 1) MG-112M | 3 | BID/ REGISTER CONTRACT | 2013-05-30 | 2013-08-27 | 2013-05-30 | 2013-08-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-02 | SANDY - Manhattan Plgd requirements (Type 1) MG-112M | 4 | CONSTRUCTION | 2013-08-28 | 2014-08-27 | 2013-08-28 | 2014-08-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-02 | SANDY - Manhattan Plgd requirements (Type 1) MG-112M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-08-28 | 2015-08-27 | 2014-08-28 | 2022-08-29
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-03 | SANDY - John Jay & Tony Dapolito - boilers (MG-113M) | 1 | DEVELOP SCOPE | 2012-12-01 | 2013-02-28 | 2012-12-01 | 2013-02-28
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-03 | SANDY - John Jay & Tony Dapolito - boilers (MG-113M) | 2 | DESIGN | 2013-03-01 | 2013-05-29 | 2013-03-01 | 2013-05-29
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-03 | SANDY - John Jay & Tony Dapolito - boilers (MG-113M) | 3 | BID/ REGISTER CONTRACT | 2013-05-30 | 2013-08-27 | 2013-05-30 | 2013-08-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-03 | SANDY - John Jay & Tony Dapolito - boilers (MG-113M) | 4 | CONSTRUCTION | 2013-08-28 | 2014-08-27 | 2013-08-28 | 2014-08-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-03 | SANDY - John Jay & Tony Dapolito - boilers (MG-113M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-08-28 | 2015-08-27 | 2014-08-28 | 2015-08-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-06 | SANDY - PNP Friends of the Highline | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2020-09-28
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-06 | SANDY - PNP Friends of the Highline | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2020-09-29 | 2029-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-06 | SANDY - PNP Friends of the Highline | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2023-10-19 | 2024-03-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-06 | SANDY - PNP Friends of the Highline | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2024-03-28 | 2025-03-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-06 | SANDY - PNP Friends of the Highline | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2025-03-28 | 2026-03-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-07 | SANDY - PNP Asphalt Green | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2018-02-15
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-07 | SANDY - PNP Asphalt Green | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2013-09-29 | 2013-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-07 | SANDY - PNP Asphalt Green | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2020-12-28 | 2021-03-25
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-07 | SANDY - PNP Asphalt Green | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2021-03-27 | 2022-03-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-07 | SANDY - PNP Asphalt Green | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2022-03-25 | 2023-03-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-08 | SANDY - PNP Battery Conservancy | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2007-06-29 | 2019-09-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-08 | SANDY - PNP Battery Conservancy | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2019-09-27 | 2032-12-25
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-08 | SANDY - PNP Battery Conservancy | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2021-06-25 | 2022-03-03
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-08 | SANDY - PNP Battery Conservancy | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2022-03-25 | 2023-03-24
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-08 | SANDY - PNP Battery Conservancy | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2023-03-25 | 2023-03-24
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-09 | SANDY - PNP Riverside Park Conservancy | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2013-09-28
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-09 | SANDY - PNP Riverside Park Conservancy | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2013-09-29 | 2022-01-25
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-09 | SANDY - PNP Riverside Park Conservancy | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2022-05-28 | 2022-09-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-09 | SANDY - PNP Riverside Park Conservancy | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2022-09-28 | 2023-09-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-09 | SANDY - PNP Riverside Park Conservancy | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2023-09-28 | 2024-09-28
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-11 | Vietnam Vet. Memorial Lighting (M046-114M) | 1 | DEVELOP SCOPE | 2013-01-01 | 2013-03-31 | 2013-01-01 | 2015-06-19
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-11 | Vietnam Vet. Memorial Lighting (M046-114M) | 2 | DESIGN | 2013-04-01 | 2013-06-29 | 2015-06-20 | 2021-04-20
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-11 | Vietnam Vet. Memorial Lighting (M046-114M) | 3 | BID/ REGISTER CONTRACT | 2013-06-30 | 2013-09-27 | 2019-05-30 | 2019-09-30
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-11 | Vietnam Vet. Memorial Lighting (M046-114M) | 4 | CONSTRUCTION | 2013-09-28 | 2014-09-27 | 2019-10-20 | 2020-10-19
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-11 | Vietnam Vet. Memorial Lighting (M046-114M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-09-28 | 2015-09-27 | 2020-10-20 | 2021-10-19
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-12 | SANDY-Inwood Hill Nature Center (Type 3) | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2013-09-28
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-12 | SANDY-Inwood Hill Nature Center (Type 3) | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2013-09-29 | 2013-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-12 | SANDY-Inwood Hill Nature Center (Type 3) | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2013-12-28 | 2014-03-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-12 | SANDY-Inwood Hill Nature Center (Type 3) | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2014-03-28 | 2015-03-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-12 | SANDY-Inwood Hill Nature Center (Type 3) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2016-03-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-13 | SANDY-Riverside & F. Washington Pk Shoreline (Type 3 ) | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2013-09-28
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-13 | SANDY-Riverside & F. Washington Pk Shoreline (Type 3 ) | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2013-09-29 | 2018-06-12
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-13 | SANDY-Riverside & F. Washington Pk Shoreline (Type 3 ) | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2019-01-02 | 2019-06-25
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-13 | SANDY-Riverside & F. Washington Pk Shoreline (Type 3 ) | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2019-10-21 | 2021-01-20
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-13 | SANDY-Riverside & F. Washington Pk Shoreline (Type 3 ) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2020-01-21 | 2022-01-20
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-14 | SANDY-Dock at 79 Street Boat Basin M071-310M | 1 | DEVELOP SCOPE | 2014-01-01 | 2014-03-31 | 2014-01-01 | 2014-03-31
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-14 | SANDY-Dock at 79 Street Boat Basin M071-310M | 2 | DESIGN | 2014-04-01 | 2014-06-29 | 2014-04-01 | 2014-06-29
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-14 | SANDY-Dock at 79 Street Boat Basin M071-310M | 3 | BID/ REGISTER CONTRACT | 2014-06-30 | 2014-09-27 | 2014-06-30 | 2014-09-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-14 | SANDY-Dock at 79 Street Boat Basin M071-310M | 4 | CONSTRUCTION | 2014-09-28 | 2015-09-27 | 2014-09-28 | 2015-09-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-14 | SANDY-Dock at 79 Street Boat Basin M071-310M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-09-28 | 2016-09-26 | 2015-09-28 | 2016-09-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-17 | SANDY- E.River Esplanade (Glick Park)-Elec (Type 3) | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2013-09-28
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-17 | SANDY- E.River Esplanade (Glick Park)-Elec (Type 3) | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2013-09-29 | 2013-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-17 | SANDY- E.River Esplanade (Glick Park)-Elec (Type 3) | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2013-12-28 | 2014-03-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-17 | SANDY- E.River Esplanade (Glick Park)-Elec (Type 3) | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2014-03-28 | 2015-03-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-17 | SANDY- E.River Esplanade (Glick Park)-Elec (Type 3) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2016-03-26
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-18 | SANDY - Mannahatta Fountains RC (Type 3) | 1 | DEVELOP SCOPE | 2014-07-01 | 2014-09-28 | 2014-07-01 | 2016-06-15
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-18 | SANDY - Mannahatta Fountains RC (Type 3) | 2 | DESIGN | 2014-09-29 | 2014-12-27 | 2016-06-16 | 2019-12-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-18 | SANDY - Mannahatta Fountains RC (Type 3) | 3 | BID/ REGISTER CONTRACT | 2014-12-28 | 2015-03-27 | 2019-10-16 | 2021-04-15
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-18 | SANDY - Mannahatta Fountains RC (Type 3) | 4 | CONSTRUCTION | 2015-03-28 | 2016-03-26 | 2022-06-15 | 2022-06-14
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-18 | SANDY - Mannahatta Fountains RC (Type 3) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-27 | 2017-03-26 | 2022-06-14 | 2022-06-13
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-19 | SANDY - John Jay & Tony Dapolito - Electrical (Balance) | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-19 | SANDY - John Jay & Tony Dapolito - Electrical (Balance) | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-19 | SANDY - John Jay & Tony Dapolito - Electrical (Balance) | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-19 | SANDY - John Jay & Tony Dapolito - Electrical (Balance) | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-19 | SANDY - John Jay & Tony Dapolito - Electrical (Balance) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-20 | Playground 103 (CIII) | 1 | DEVELOP SCOPE | 2016-08-01 | 2017-01-27 | 2016-08-01 | 2017-01-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-20 | Playground 103 (CIII) | 2 | DESIGN | 2017-01-28 | 2018-01-27 | 2017-01-28 | 2018-01-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-20 | Playground 103 (CIII) | 3 | BID/ REGISTER CONTRACT | 2018-01-28 | 2018-10-24 | 2018-01-28 | 2018-10-24
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-20 | Playground 103 (CIII) | 4 | CONSTRUCTION | 2018-10-25 | 2019-10-24 | 2018-10-25 | 2019-10-24
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-20 | Playground 103 (CIII) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-10-25 | 2020-10-23 | 2019-10-25 | 2020-10-23
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-21 | Four Parks Safety Surface | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-21 | Four Parks Safety Surface | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-21 | Four Parks Safety Surface | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-21 | Four Parks Safety Surface | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-21 | Four Parks Safety Surface | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-23 | Manhattan B | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-23 | Manhattan B | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-23 | Manhattan B | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-23 | Manhattan B | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-23 | Manhattan B | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-24 | SANDY-Inwood Nature Center Exhibit Displays | 1 | DEVELOP SCOPE | 2018-01-08 | 2018-07-06 | 2018-01-08 | 2018-07-06
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-24 | SANDY-Inwood Nature Center Exhibit Displays | 2 | DESIGN | 2018-07-07 | 2019-07-06 | 2018-07-07 | 2019-07-06
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-24 | SANDY-Inwood Nature Center Exhibit Displays | 3 | BID/ REGISTER CONTRACT | 2019-07-07 | 2020-04-01 | 2019-07-07 | 2020-04-01
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-24 | SANDY-Inwood Nature Center Exhibit Displays | 4 | CONSTRUCTION | 2020-04-02 | 2021-09-28 | 2020-04-02 | 2021-09-28
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-24 | SANDY-Inwood Nature Center Exhibit Displays | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-29 | 2022-09-28 | 2021-09-29 | 2022-09-28
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-25 | Riverside Park Electrical Repairs | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-25 | Riverside Park Electrical Repairs | 2 | DESIGN | 2019-12-28 | 2021-06-24 | 2019-12-28 | 2021-06-24
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-25 | Riverside Park Electrical Repairs | 3 | BID/ REGISTER CONTRACT | 2021-06-25 | 2022-03-21 | 2021-06-25 | 2022-03-21
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-25 | Riverside Park Electrical Repairs | 4 | CONSTRUCTION | 2022-03-22 | 2023-09-17 | 2022-03-22 | 2023-09-17
20201123 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-25 | Riverside Park Electrical Repairs | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-18 | 2024-09-16 | 2023-09-18 | 2024-09-16
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | AGNYCHANG | NYCHANGE PROJECT WITH DFTA | 1 | DEVELOP SCOPE | 2011-09-01 | 2011-11-29 | 2013-03-15 | 2015-03-15
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | AGNYCHANG | NYCHANGE PROJECT WITH DFTA | 2 | DESIGN START | 2011-11-30 | 2012-03-28 | 2015-03-16 | 2017-01-15
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | AGNYCHANG | NYCHANGE PROJECT WITH DFTA | 3 | FINAL DESIGN | 2012-03-29 | 2012-09-24 | 2017-01-16 | 2019-01-15
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | AGNYCHANG | NYCHANGE PROJECT WITH DFTA | 4 | CONSTRUCTION START | 2012-09-25 | 2012-12-23 | 2019-01-16 | 2019-11-02
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | AGNYCHANG | NYCHANGE PROJECT WITH DFTA | 5 | CONSTRUCTION TO 25% | 2012-12-24 | 2013-04-22 | 2019-11-03 | 2024-07-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | AGNYCHANG | NYCHANGE PROJECT WITH DFTA | 6 | CONSTRUCTION TO 50% | 2013-04-23 | 2013-08-20 | 2019-11-03 | 2024-07-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | AGNYCHANG | NYCHANGE PROJECT WITH DFTA | 7 | CONSTRUCTION TO 75% | 2013-08-21 | 2013-12-18 | 2019-11-03 | 2024-07-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | AGNYCHANG | NYCHANGE PROJECT WITH DFTA | 8 | ORIGINAL EQUIP & FURNISHING | 2013-12-19 | 2014-03-18 | 2019-11-03 | 2024-07-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | AGNYCHANG | NYCHANGE PROJECT WITH DFTA | 9 | SUBSTANTIAL COMPLETION | 2014-03-19 | 2014-05-17 | 2019-11-03 | 2024-07-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | AGNYCHANG | NYCHANGE PROJECT WITH DFTA | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-05-18 | 2014-06-16 | 2019-11-03 | 2024-07-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CC1C3 | 1 CENTRE ST.- OFFICES FROM 49-51 CHAMBERS ST. - 21C3 | 1 | DEVELOP SCOPE | 2012-06-01 | 2012-08-29 | 2012-06-01 | 2012-08-29
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CC1C3 | 1 CENTRE ST.- OFFICES FROM 49-51 CHAMBERS ST. - 21C3 | 2 | PRELIMINARY DESIGN | 2012-08-30 | 2012-12-27 | 2012-08-30 | 2012-12-27
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CC1C3 | 1 CENTRE ST.- OFFICES FROM 49-51 CHAMBERS ST. - 21C3 | 3 | FINAL DESIGN | 2012-12-28 | 2013-06-25 | 2012-12-28 | 2013-06-25
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CC1C3 | 1 CENTRE ST.- OFFICES FROM 49-51 CHAMBERS ST. - 21C3 | 4 | BID AWARD AND REGISTER CONTRCT | 2013-06-26 | 2013-09-23 | 2013-06-26 | 2013-09-23
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CC1C3 | 1 CENTRE ST.- OFFICES FROM 49-51 CHAMBERS ST. - 21C3 | 5 | CONSTRUCTION TO 25% | 2013-09-24 | 2014-01-21 | 2013-09-24 | 2014-01-21
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CC1C3 | 1 CENTRE ST.- OFFICES FROM 49-51 CHAMBERS ST. - 21C3 | 6 | CONSTRUCTION TO 50% | 2014-01-22 | 2014-05-21 | 2014-01-22 | 2014-05-21
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CC1C3 | 1 CENTRE ST.- OFFICES FROM 49-51 CHAMBERS ST. - 21C3 | 7 | CONSTRUCTION TO 75% | 2014-05-22 | 2014-09-18 | 2014-05-22 | 2014-09-18
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CC1C3 | 1 CENTRE ST.- OFFICES FROM 49-51 CHAMBERS ST. - 21C3 | 8 | ORIGINAL EQUIP & FURNISHING | 2014-09-19 | 2014-12-17 | 2014-09-19 | 2014-12-17
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CC1C3 | 1 CENTRE ST.- OFFICES FROM 49-51 CHAMBERS ST. - 21C3 | 9 | SUBSTANTIAL COMPLETION | 2014-12-18 | 2015-02-15 | 2016-12-18 | 2018-05-25
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CC1C3 | 1 CENTRE ST.- OFFICES FROM 49-51 CHAMBERS ST. - 21C3 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-02-16 | 2015-03-17 | 2018-05-26 | 2022-09-21
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CC1C3 | 1 CENTRE ST.- OFFICES FROM 49-51 CHAMBERS ST. - 21C3 | 11 | PROJECT START | 2015-02-16 | 2015-03-17 | 2022-09-22 | 2022-09-22
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CC1C3 | 1 CENTRE ST.- OFFICES FROM 49-51 CHAMBERS ST. - 21C3 | 12 | DESIGN START | 2015-02-16 | 2015-03-17 | 2022-09-23 | 2022-09-23
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CC1C3 | 1 CENTRE ST.- OFFICES FROM 49-51 CHAMBERS ST. - 21C3 | 13 | DESIGN COMPLETION | 2015-02-16 | 2015-03-17 | 2022-09-24 | 2022-09-24
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CC1C3 | 1 CENTRE ST.- OFFICES FROM 49-51 CHAMBERS ST. - 21C3 | 14 | CONSTRUCTION START | 2015-02-16 | 2015-03-17 | 2022-09-25 | 2022-09-25
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CC1C3 | 1 CENTRE ST.- OFFICES FROM 49-51 CHAMBERS ST. - 21C3 | 15 | CONSTRUCTION COMPLETION | 2015-02-16 | 2015-03-17 | 2022-09-26 | 2022-09-26
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CC253B | 100 GOLD- 21C3 | 1 | DEVELOP SCOPE | 2012-06-02 | 2012-08-30 | 2014-04-07 | 2014-04-07
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CC253B | 100 GOLD- 21C3 | 2 | PRELIMINARY DESIGN | 2012-08-31 | 2012-12-28 | 2014-04-07 | 2014-05-15
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CC253B | 100 GOLD- 21C3 | 3 | FINAL DESIGN | 2012-12-29 | 2013-06-26 | 2014-05-16 | 2014-06-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CC253B | 100 GOLD- 21C3 | 4 | BID AWARD AND REGISTER CONTRCT | 2013-06-27 | 2013-09-24 | 2014-07-27 | 2014-07-28
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CC253B | 100 GOLD- 21C3 | 5 | CONSTRUCTION TO 25% | 2013-09-25 | 2014-01-22 | 2014-07-29 | 2020-07-31
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CC253B | 100 GOLD- 21C3 | 6 | CONSTRUCTION TO 50% | 2014-01-23 | 2014-05-22 | 2014-07-29 | 2020-07-31
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CC253B | 100 GOLD- 21C3 | 7 | CONSTRUCTION TO 75% | 2014-05-23 | 2014-09-19 | 2014-07-29 | 2020-07-31
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CC253B | 100 GOLD- 21C3 | 8 | ORIGINAL EQUIP & FURNISHING | 2014-09-20 | 2014-12-18 | 2014-07-29 | 2020-07-31
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CC253B | 100 GOLD- 21C3 | 9 | SUBSTANTIAL COMPLETION | 2014-12-19 | 2015-02-16 | 2014-07-29 | 2020-07-31
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CC253B | 100 GOLD- 21C3 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-02-17 | 2015-03-18 | 2014-07-29 | 2020-07-31
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CMEHVAC | OCME - Evidence Unit HVAC Upgrades at 421 E. 26th St, Manh | 2 | CONSTRUCTION | 2016-09-29 | 2017-05-01 | 2016-03-01 | 2018-08-15
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CMEHVAC | OCME - Evidence Unit HVAC Upgrades at 421 E. 26th St, Manh | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-05-02 | 2017-06-30 | 2018-08-16 | 2019-08-15
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CMEHVAC | OCME - Evidence Unit HVAC Upgrades at 421 E. 26th St, Manh | 4 | PROJECT START | 2017-05-02 | 2017-06-30 | 2016-02-29 | 2016-02-29
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CMEHVAC | OCME - Evidence Unit HVAC Upgrades at 421 E. 26th St, Manh | 5 | DESIGN START | 2017-05-02 | 2017-06-30 | 2016-03-01 | 2016-05-26
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CMEHVAC | OCME - Evidence Unit HVAC Upgrades at 421 E. 26th St, Manh | 6 | DESIGN COMPLETION | 2017-05-02 | 2017-06-30 | 2016-05-27 | 2018-02-16
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CMEHVAC | OCME - Evidence Unit HVAC Upgrades at 421 E. 26th St, Manh | 7 | CONSTRUCTION START | 2017-05-02 | 2017-06-30 | 2018-02-17 | 2018-08-05
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CMEHVAC | OCME - Evidence Unit HVAC Upgrades at 421 E. 26th St, Manh | 8 | CONSTRUCTION COMPLETION | 2017-05-02 | 2017-06-30 | 2018-08-06 | 2020-08-15
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO283SID2 | 100 CENTRE STREET - SIDEWALK REPLACEMENT | 1 | PROJECT START | 2014-09-25 | 2014-09-25 | 2014-09-25 | 2014-09-25
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO283SID2 | 100 CENTRE STREET - SIDEWALK REPLACEMENT | 2 | DESIGN START | 2014-09-26 | 2014-09-26 | 2014-09-26 | 2014-09-26
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO283SID2 | 100 CENTRE STREET - SIDEWALK REPLACEMENT | 3 | DESIGN COMPLETION | 2014-09-27 | 2014-09-27 | 2014-09-27 | 2014-09-27
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO283SID2 | 100 CENTRE STREET - SIDEWALK REPLACEMENT | 4 | CONSTRUCTION START | 2014-09-28 | 2014-09-28 | 2014-09-28 | 2014-09-28
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO283SID2 | 100 CENTRE STREET - SIDEWALK REPLACEMENT | 5 | CONSTRUCTION COMPLETION | 2014-09-29 | 2014-09-29 | 2014-09-29 | 2021-06-25
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO283TOIL | 100 CENTRE ST.- CODE COMPLIANT TOILET UPGRADE | 1 | DEVELOP SCOPE | 2014-10-01 | 2014-10-30 | 2014-10-01 | 2014-10-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO283TOIL | 100 CENTRE ST.- CODE COMPLIANT TOILET UPGRADE | 2 | PRELIMINARY DESIGN | 2014-10-31 | 2014-12-29 | 2014-10-31 | 2014-12-29
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO283TOIL | 100 CENTRE ST.- CODE COMPLIANT TOILET UPGRADE | 3 | FINAL DESIGN | 2014-12-30 | 2015-02-27 | 2014-12-30 | 2019-06-18
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO283TOIL | 100 CENTRE ST.- CODE COMPLIANT TOILET UPGRADE | 4 | BID AWARD AND REGISTER CONTRCT | 2015-02-28 | 2015-03-29 | 2019-06-19 | 2019-07-18
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO283TOIL | 100 CENTRE ST.- CODE COMPLIANT TOILET UPGRADE | 5 | CONSTRUCTION TO 25% | 2015-03-30 | 2015-05-28 | 2019-07-19 | 2019-09-16
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO283TOIL | 100 CENTRE ST.- CODE COMPLIANT TOILET UPGRADE | 6 | CONSTRUCTION TO 50% | 2015-05-29 | 2015-06-27 | 2019-09-17 | 2019-10-16
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO283TOIL | 100 CENTRE ST.- CODE COMPLIANT TOILET UPGRADE | 7 | CONSTRUCTION TO 75% | 2015-06-28 | 2015-07-27 | 2019-10-17 | 2019-11-15
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO283TOIL | 100 CENTRE ST.- CODE COMPLIANT TOILET UPGRADE | 8 | ORIGINAL EQUIP & FURNISHING | 2015-07-28 | 2015-07-27 | 2019-11-16 | 2019-11-15
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO283TOIL | 100 CENTRE ST.- CODE COMPLIANT TOILET UPGRADE | 9 | SUBSTANTIAL COMPLETION | 2015-07-28 | 2015-07-27 | 2019-11-16 | 2019-11-15
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO283TOIL | 100 CENTRE ST.- CODE COMPLIANT TOILET UPGRADE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-07-28 | 2015-08-26 | 2019-11-16 | 2023-10-14
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO283TOIL | 100 CENTRE ST.- CODE COMPLIANT TOILET UPGRADE | 11 | PROJECT START | 2015-07-28 | 2015-08-26 | 2023-10-15 | 2023-10-15
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO283TOIL | 100 CENTRE ST.- CODE COMPLIANT TOILET UPGRADE | 12 | DESIGN START | 2015-07-28 | 2015-08-26 | 2023-10-16 | 2023-10-16
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO283TOIL | 100 CENTRE ST.- CODE COMPLIANT TOILET UPGRADE | 13 | DESIGN COMPLETION | 2015-07-28 | 2015-08-26 | 2023-10-17 | 2023-10-17
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO283TOIL | 100 CENTRE ST.- CODE COMPLIANT TOILET UPGRADE | 14 | CONSTRUCTION START | 2015-07-28 | 2015-08-26 | 2023-10-18 | 2023-10-18
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO283TOIL | 100 CENTRE ST.- CODE COMPLIANT TOILET UPGRADE | 15 | CONSTRUCTION COMPLETION | 2015-07-28 | 2015-08-26 | 2023-10-19 | 2023-10-19
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO283WT | 100 CENTRE STREET - WATER TANK | 1 | DEVELOP SCOPE | 2022-06-01 | 2022-08-29 | 2022-06-01 | 2022-08-29
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO283WT | 100 CENTRE STREET - WATER TANK | 2 | PRELIMINARY DESIGN | 2022-08-30 | 2022-12-27 | 2022-08-30 | 2022-12-27
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO283WT | 100 CENTRE STREET - WATER TANK | 3 | FINAL DESIGN | 2022-12-28 | 2023-06-25 | 2022-12-28 | 2023-06-25
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO283WT | 100 CENTRE STREET - WATER TANK | 4 | BID AWARD AND REGISTER CONTRCT | 2023-06-26 | 2023-09-23 | 2023-06-26 | 2023-09-23
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO283WT | 100 CENTRE STREET - WATER TANK | 5 | CONSTRUCTION TO 25% | 2023-09-24 | 2024-01-21 | 2023-09-24 | 2024-01-21
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO283WT | 100 CENTRE STREET - WATER TANK | 6 | CONSTRUCTION TO 50% | 2024-01-22 | 2024-05-20 | 2024-01-22 | 2024-05-20
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO283WT | 100 CENTRE STREET - WATER TANK | 7 | CONSTRUCTION TO 75% | 2024-05-21 | 2024-09-17 | 2024-05-21 | 2024-09-17
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO283WT | 100 CENTRE STREET - WATER TANK | 8 | ORIGINAL EQUIP & FURNISHING | 2024-09-18 | 2024-12-16 | 2024-09-18 | 2024-12-16
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO283WT | 100 CENTRE STREET - WATER TANK | 9 | SUBSTANTIAL COMPLETION | 2024-12-17 | 2025-02-14 | 2024-12-17 | 2025-02-14
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO283WT | 100 CENTRE STREET - WATER TANK | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-02-15 | 2025-03-16 | 2025-02-15 | 2025-03-16
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO285FIRE | 60 LAFAYETTE ST - FIRE ALARM UPGRADE | 1 | PROJECT START | 2022-07-01 | 2022-07-02 | 2022-07-01 | 2022-07-02
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO285FIRE | 60 LAFAYETTE ST - FIRE ALARM UPGRADE | 2 | DESIGN START | 2022-07-03 | 2023-07-03 | 2022-07-03 | 2023-07-03
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO285FIRE | 60 LAFAYETTE ST - FIRE ALARM UPGRADE | 3 | DESIGN COMPLETION | 2023-07-04 | 2024-07-04 | 2023-07-04 | 2024-07-04
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO285FIRE | 60 LAFAYETTE ST - FIRE ALARM UPGRADE | 4 | CONSTRUCTION START | 2024-07-05 | 2026-07-05 | 2024-07-05 | 2026-07-05
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO285FIRE | 60 LAFAYETTE ST - FIRE ALARM UPGRADE | 5 | CONSTRUCTION COMPLETION | 2026-07-06 | 2027-07-06 | 2026-07-06 | 2027-07-06
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO304REHB | 60 CENTRE ST. - RECONSTRUCTION | 1 | DEVELOP SCOPE | 2018-03-01 | 2018-05-29 | 2017-05-29 | 2018-06-28
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO304REHB | 60 CENTRE ST. - RECONSTRUCTION | 2 | PRELIMINARY DESIGN | 2018-05-30 | 2018-09-26 | 2018-06-29 | 2020-01-06
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO304REHB | 60 CENTRE ST. - RECONSTRUCTION | 3 | FINAL DESIGN | 2018-09-27 | 2019-03-25 | 2020-01-07 | 2021-01-05
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO304REHB | 60 CENTRE ST. - RECONSTRUCTION | 4 | BID AWARD AND REGISTER CONTRCT | 2019-03-26 | 2019-06-23 | 2021-01-06 | 2021-10-05
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO304REHB | 60 CENTRE ST. - RECONSTRUCTION | 5 | CONSTRUCTION TO 25% | 2019-06-24 | 2019-10-21 | 2021-10-06 | 2022-06-02
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO304REHB | 60 CENTRE ST. - RECONSTRUCTION | 6 | CONSTRUCTION TO 50% | 2019-10-22 | 2020-02-18 | 2022-06-03 | 2023-01-28
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO304REHB | 60 CENTRE ST. - RECONSTRUCTION | 7 | CONSTRUCTION TO 75% | 2020-02-19 | 2020-06-17 | 2023-01-29 | 2023-09-25
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO304REHB | 60 CENTRE ST. - RECONSTRUCTION | 8 | ORIGINAL EQUIP & FURNISHING | 2020-06-18 | 2020-09-15 | 2023-09-26 | 2023-12-24
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO304REHB | 60 CENTRE ST. - RECONSTRUCTION | 9 | SUBSTANTIAL COMPLETION | 2020-09-16 | 2020-11-14 | 2023-12-25 | 2024-07-17
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO304REHB | 60 CENTRE ST. - RECONSTRUCTION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-11-15 | 2020-12-14 | 2024-07-18 | 2025-06-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO306EXT2 | 170 E121 ST. EXTERIOR - LL11 | 1 | DEVELOP SCOPE | 2016-02-01 | 2016-04-30 | 2022-06-01 | 2022-08-29
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO306EXT2 | 170 E121 ST. EXTERIOR - LL11 | 2 | PRELIMINARY DESIGN | 2016-05-01 | 2016-08-28 | 2022-08-30 | 2022-12-27
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO306EXT2 | 170 E121 ST. EXTERIOR - LL11 | 3 | FINAL DESIGN | 2016-08-29 | 2017-02-24 | 2022-12-28 | 2023-06-25
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO306EXT2 | 170 E121 ST. EXTERIOR - LL11 | 4 | BID AWARD AND REGISTER CONTRCT | 2017-02-25 | 2017-05-25 | 2023-06-26 | 2023-09-23
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO306EXT2 | 170 E121 ST. EXTERIOR - LL11 | 5 | CONSTRUCTION TO 25% | 2017-05-26 | 2017-09-22 | 2023-09-24 | 2024-01-21
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO306EXT2 | 170 E121 ST. EXTERIOR - LL11 | 6 | CONSTRUCTION TO 50% | 2017-09-23 | 2018-01-20 | 2024-01-22 | 2024-05-20
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO306EXT2 | 170 E121 ST. EXTERIOR - LL11 | 7 | CONSTRUCTION TO 75% | 2018-01-21 | 2018-05-20 | 2024-05-21 | 2024-09-17
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO306EXT2 | 170 E121 ST. EXTERIOR - LL11 | 8 | ORIGINAL EQUIP & FURNISHING | 2018-05-21 | 2018-08-18 | 2024-09-18 | 2024-12-16
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO306EXT2 | 170 E121 ST. EXTERIOR - LL11 | 9 | SUBSTANTIAL COMPLETION | 2018-08-19 | 2018-10-17 | 2024-12-17 | 2025-02-14
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO306EXT2 | 170 E121 ST. EXTERIOR - LL11 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-10-18 | 2018-11-16 | 2025-02-15 | 2025-03-16
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO80ROOF2 | 27 MADISON AVE - ROOF & MISC. OPERATIONS SPACES UPGRADE | 1 | PROJECT START | 2014-09-14 | 2014-09-14 | 2013-01-27 | 2013-01-27
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO80ROOF2 | 27 MADISON AVE - ROOF & MISC. OPERATIONS SPACES UPGRADE | 2 | DESIGN START | 2014-09-15 | 2014-09-15 | 2015-04-30 | 2017-07-28
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO80ROOF2 | 27 MADISON AVE - ROOF & MISC. OPERATIONS SPACES UPGRADE | 3 | DESIGN COMPLETION | 2014-09-16 | 2014-09-16 | 2017-07-29 | 2017-07-29
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO80ROOF2 | 27 MADISON AVE - ROOF & MISC. OPERATIONS SPACES UPGRADE | 4 | CONSTRUCTION START | 2014-09-17 | 2014-09-17 | 2016-08-15 | 2017-12-08
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO80ROOF2 | 27 MADISON AVE - ROOF & MISC. OPERATIONS SPACES UPGRADE | 5 | CONSTRUCTION COMPLETION | 2014-09-18 | 2014-09-18 | 2016-04-18 | 2022-04-13
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO81ELEC | 31 CHAMBERS ST. - ELECTRICAL AND FA SYSTEM UPGRADE | 1 | DEVELOP SCOPE | 2019-03-01 | 2019-05-29 | 2024-03-01 | 2024-05-29
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO81ELEC | 31 CHAMBERS ST. - ELECTRICAL AND FA SYSTEM UPGRADE | 2 | PRELIMINARY DESIGN | 2019-05-30 | 2019-09-26 | 2024-05-30 | 2024-09-26
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO81ELEC | 31 CHAMBERS ST. - ELECTRICAL AND FA SYSTEM UPGRADE | 3 | FINAL DESIGN | 2019-09-27 | 2020-03-24 | 2024-09-27 | 2025-03-31
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO81ELEC | 31 CHAMBERS ST. - ELECTRICAL AND FA SYSTEM UPGRADE | 4 | BID AWARD AND REGISTER CONTRCT | 2020-03-25 | 2020-06-22 | 2025-03-25 | 2025-06-22
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO81ELEC | 31 CHAMBERS ST. - ELECTRICAL AND FA SYSTEM UPGRADE | 5 | CONSTRUCTION TO 25% | 2020-06-23 | 2020-10-20 | 2026-06-23 | 2026-10-20
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO81ELEC | 31 CHAMBERS ST. - ELECTRICAL AND FA SYSTEM UPGRADE | 6 | CONSTRUCTION TO 50% | 2020-10-21 | 2021-02-17 | 2026-10-21 | 2027-02-17
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO81ELEC | 31 CHAMBERS ST. - ELECTRICAL AND FA SYSTEM UPGRADE | 7 | CONSTRUCTION TO 75% | 2021-02-18 | 2021-06-17 | 2027-02-18 | 2027-06-17
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO81ELEC | 31 CHAMBERS ST. - ELECTRICAL AND FA SYSTEM UPGRADE | 8 | ORIGINAL EQUIP & FURNISHING | 2021-06-18 | 2021-09-15 | 2027-06-18 | 2027-09-15
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO81ELEC | 31 CHAMBERS ST. - ELECTRICAL AND FA SYSTEM UPGRADE | 9 | SUBSTANTIAL COMPLETION | 2021-09-16 | 2021-11-14 | 2027-09-16 | 2027-11-14
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO81ELEC | 31 CHAMBERS ST. - ELECTRICAL AND FA SYSTEM UPGRADE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-11-15 | 2021-12-14 | 2027-11-15 | 2027-12-14
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO81ELEC | 31 CHAMBERS ST. - ELECTRICAL AND FA SYSTEM UPGRADE | 11 | PROJECT START | 2021-11-15 | 2021-12-14 | 2024-03-01 | 2024-03-02
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO81ELEC | 31 CHAMBERS ST. - ELECTRICAL AND FA SYSTEM UPGRADE | 12 | DESIGN START | 2021-11-15 | 2021-12-14 | 2024-03-03 | 2024-03-04
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO81ELEC | 31 CHAMBERS ST. - ELECTRICAL AND FA SYSTEM UPGRADE | 13 | DESIGN COMPLETION | 2021-11-15 | 2021-12-14 | 2024-03-05 | 2026-03-05
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO81ELEC | 31 CHAMBERS ST. - ELECTRICAL AND FA SYSTEM UPGRADE | 14 | CONSTRUCTION START | 2021-11-15 | 2021-12-14 | 2026-03-06 | 2026-03-07
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO81ELEC | 31 CHAMBERS ST. - ELECTRICAL AND FA SYSTEM UPGRADE | 15 | CONSTRUCTION COMPLETION | 2021-11-15 | 2021-12-14 | 2026-03-08 | 2026-03-08
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO81SKY2 | 31 CHAMBERST ST.- RENOVATE SKYLIGHT | 1 | PROJECT START | 2013-06-01 | 2013-06-01 | 2013-07-01 | 2013-07-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO81SKY2 | 31 CHAMBERST ST.- RENOVATE SKYLIGHT | 2 | DESIGN START | 2013-06-02 | 2013-06-02 | 2013-07-02 | 2013-07-02
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO81SKY2 | 31 CHAMBERST ST.- RENOVATE SKYLIGHT | 3 | DESIGN COMPLETION | 2013-06-03 | 2013-06-03 | 2014-09-26 | 2014-12-27
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO81SKY2 | 31 CHAMBERST ST.- RENOVATE SKYLIGHT | 4 | CONSTRUCTION START | 2013-06-04 | 2013-06-04 | 2015-10-26 | 2015-10-26
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO81SKY2 | 31 CHAMBERST ST.- RENOVATE SKYLIGHT | 5 | CONSTRUCTION COMPLETION | 2014-12-01 | 2016-06-30 | 2018-06-12 | 2023-06-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E14-0008 | DCAS - MANHATTAN SUPREME COURT COMP ENERGY UPGRADE | 1 | PROJECT START | 2014-01-06 | 2014-01-06 | 2014-01-06 | 2014-01-06
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E14-0008 | DCAS - MANHATTAN SUPREME COURT COMP ENERGY UPGRADE | 2 | DESIGN START | 2014-01-07 | 2014-07-17 | 2014-01-07 | 2014-07-17
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E14-0008 | DCAS - MANHATTAN SUPREME COURT COMP ENERGY UPGRADE | 3 | DESIGN COMPLETION | 2014-07-18 | 2015-07-31 | 2014-07-18 | 2015-07-31
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E14-0008 | DCAS - MANHATTAN SUPREME COURT COMP ENERGY UPGRADE | 4 | CONSTRUCTION START | 2015-08-01 | 2016-01-17 | 2015-08-01 | 2016-01-17
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E14-0008 | DCAS - MANHATTAN SUPREME COURT COMP ENERGY UPGRADE | 5 | CONSTRUCTION COMPLETION | 2016-01-18 | 2017-01-17 | 2016-01-18 | 2022-06-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E14-0017 | DHS - Bellevue Men's Shelter | 1 | PROJECT START | 2014-01-06 | 2014-01-06 | 2014-01-06 | 2014-01-06
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E14-0017 | DHS - Bellevue Men's Shelter | 2 | DESIGN START | 2014-01-07 | 2014-07-16 | 2014-01-07 | 2014-07-16
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E14-0017 | DHS - Bellevue Men's Shelter | 3 | DESIGN COMPLETION | 2014-07-17 | 2015-07-15 | 2014-07-17 | 2016-01-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E14-0017 | DHS - Bellevue Men's Shelter | 4 | CONSTRUCTION START | 2015-07-16 | 2016-01-16 | 2016-01-02 | 2017-03-29
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E14-0017 | DHS - Bellevue Men's Shelter | 5 | CONSTRUCTION COMPLETION | 2016-01-17 | 2017-01-16 | 2019-07-31 | 2021-07-31
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0003 | DCAS - Manhattan Civil Court | 1 | PROJECT START | 2018-03-01 | 2018-03-01 | 2018-03-01 | 2018-03-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0003 | DCAS - Manhattan Civil Court | 2 | DESIGN START | 2018-03-02 | 2018-03-02 | 2018-03-02 | 2018-03-02
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0003 | DCAS - Manhattan Civil Court | 3 | DESIGN COMPLETION | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0003 | DCAS - Manhattan Civil Court | 4 | CONSTRUCTION START | 2018-03-04 | 2018-03-04 | 2018-03-04 | 2018-03-04
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0003 | DCAS - Manhattan Civil Court | 5 | CONSTRUCTION COMPLETION | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0003 | DCAS - Manhattan Civil Court | 6 | DEVELOP SCOPE | 2018-03-05 | 2018-03-05 | 2018-03-06 | 2018-06-03
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0003 | DCAS - Manhattan Civil Court | 7 | PRELIMINARY DESIGN | 2018-03-05 | 2018-03-05 | 2018-06-04 | 2018-10-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0003 | DCAS - Manhattan Civil Court | 8 | FINAL DESIGN | 2018-03-05 | 2018-03-05 | 2018-10-02 | 2019-03-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0003 | DCAS - Manhattan Civil Court | 9 | BID AWARD AND REGISTER CONTRCT | 2018-03-05 | 2018-03-05 | 2019-03-31 | 2019-06-28
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0003 | DCAS - Manhattan Civil Court | 10 | CONSTRUCTION TO 25% | 2018-03-05 | 2018-03-05 | 2019-06-29 | 2019-10-26
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0003 | DCAS - Manhattan Civil Court | 11 | CONSTRUCTION TO 50% | 2018-03-05 | 2018-03-05 | 2019-10-27 | 2020-02-23
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0003 | DCAS - Manhattan Civil Court | 12 | CONSTRUCTION TO 75% | 2018-03-05 | 2018-03-05 | 2020-02-24 | 2020-06-22
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0003 | DCAS - Manhattan Civil Court | 13 | ORIGINAL EQUIP & FURNISHING | 2018-03-05 | 2018-03-05 | 2020-06-23 | 2020-09-20
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0003 | DCAS - Manhattan Civil Court | 14 | SUBSTANTIAL COMPLETION | 2018-03-05 | 2018-03-05 | 2020-09-21 | 2022-05-27
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0003 | DCAS - Manhattan Civil Court | 15 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-03-05 | 2018-03-05 | 2022-05-28 | 2023-05-26
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0005 | DSNY -Manhattan 3 District Garage | 1 | PROJECT START | 2018-03-01 | 2018-03-01 | 2018-03-01 | 2018-03-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0005 | DSNY -Manhattan 3 District Garage | 2 | DESIGN START | 2018-03-02 | 2018-03-02 | 2018-03-02 | 2018-03-02
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0005 | DSNY -Manhattan 3 District Garage | 3 | DESIGN COMPLETION | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0005 | DSNY -Manhattan 3 District Garage | 4 | CONSTRUCTION START | 2018-03-04 | 2018-03-04 | 2018-03-04 | 2018-03-04
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0005 | DSNY -Manhattan 3 District Garage | 5 | CONSTRUCTION COMPLETION | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0005 | DSNY -Manhattan 3 District Garage | 6 | DEVELOP SCOPE | 2018-03-05 | 2018-03-05 | 2018-03-06 | 2018-06-03
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0005 | DSNY -Manhattan 3 District Garage | 7 | PRELIMINARY DESIGN | 2018-03-05 | 2018-03-05 | 2018-06-04 | 2018-10-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0005 | DSNY -Manhattan 3 District Garage | 8 | FINAL DESIGN | 2018-03-05 | 2018-03-05 | 2018-10-02 | 2019-03-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0005 | DSNY -Manhattan 3 District Garage | 9 | BID AWARD AND REGISTER CONTRCT | 2018-03-05 | 2018-03-05 | 2019-03-31 | 2019-06-28
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0005 | DSNY -Manhattan 3 District Garage | 10 | CONSTRUCTION TO 25% | 2018-03-05 | 2018-03-05 | 2019-06-29 | 2019-10-26
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0005 | DSNY -Manhattan 3 District Garage | 11 | CONSTRUCTION TO 50% | 2018-03-05 | 2018-03-05 | 2019-10-27 | 2020-02-23
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0005 | DSNY -Manhattan 3 District Garage | 12 | CONSTRUCTION TO 75% | 2018-03-05 | 2018-03-05 | 2020-02-24 | 2020-06-22
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0005 | DSNY -Manhattan 3 District Garage | 13 | ORIGINAL EQUIP & FURNISHING | 2018-03-05 | 2018-03-05 | 2020-06-23 | 2020-09-20
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0005 | DSNY -Manhattan 3 District Garage | 14 | SUBSTANTIAL COMPLETION | 2018-03-05 | 2018-03-05 | 2020-09-21 | 2021-09-15
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0005 | DSNY -Manhattan 3 District Garage | 15 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-03-05 | 2018-03-05 | 2021-09-16 | 2022-09-14
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E17-0001 | DCAS - LOUIS J LEFKOWITZ - ENERGY EFFICIENCY UPGRADE | 1 | DEVELOP SCOPE | 2019-03-01 | 2019-05-29 | 2019-03-01 | 2019-05-29
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E17-0001 | DCAS - LOUIS J LEFKOWITZ - ENERGY EFFICIENCY UPGRADE | 2 | PRELIMINARY DESIGN | 2019-05-30 | 2019-09-26 | 2019-05-30 | 2019-09-26
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E17-0001 | DCAS - LOUIS J LEFKOWITZ - ENERGY EFFICIENCY UPGRADE | 3 | FINAL DESIGN | 2019-09-27 | 2020-03-24 | 2019-09-27 | 2020-03-24
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E17-0001 | DCAS - LOUIS J LEFKOWITZ - ENERGY EFFICIENCY UPGRADE | 4 | BID AWARD AND REGISTER CONTRCT | 2020-03-25 | 2020-06-22 | 2020-03-25 | 2020-06-22
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E17-0001 | DCAS - LOUIS J LEFKOWITZ - ENERGY EFFICIENCY UPGRADE | 5 | CONSTRUCTION TO 25% | 2020-06-23 | 2020-10-20 | 2020-06-23 | 2020-10-20
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E17-0001 | DCAS - LOUIS J LEFKOWITZ - ENERGY EFFICIENCY UPGRADE | 6 | CONSTRUCTION TO 50% | 2020-10-21 | 2021-02-17 | 2020-10-21 | 2021-02-17
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E17-0001 | DCAS - LOUIS J LEFKOWITZ - ENERGY EFFICIENCY UPGRADE | 7 | CONSTRUCTION TO 75% | 2021-02-18 | 2021-06-17 | 2021-02-18 | 2021-06-17
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E17-0001 | DCAS - LOUIS J LEFKOWITZ - ENERGY EFFICIENCY UPGRADE | 8 | ORIGINAL EQUIP & FURNISHING | 2021-06-18 | 2021-09-15 | 2021-06-18 | 2021-09-15
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E17-0001 | DCAS - LOUIS J LEFKOWITZ - ENERGY EFFICIENCY UPGRADE | 9 | SUBSTANTIAL COMPLETION | 2021-09-16 | 2021-11-14 | 2021-09-16 | 2021-11-14
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E17-0001 | DCAS - LOUIS J LEFKOWITZ - ENERGY EFFICIENCY UPGRADE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-11-15 | 2021-12-14 | 2021-11-15 | 2021-12-14
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0002 | DCAS-Manhattan Municipal Building - Heat Light Installation | 1 | DEVELOP SCOPE | 2019-03-01 | 2019-05-29 | 2019-03-01 | 2019-05-29
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0002 | DCAS-Manhattan Municipal Building - Heat Light Installation | 2 | PRELIMINARY DESIGN | 2019-05-30 | 2019-09-26 | 2019-05-30 | 2019-09-26
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0002 | DCAS-Manhattan Municipal Building - Heat Light Installation | 3 | FINAL DESIGN | 2019-09-27 | 2020-03-24 | 2019-09-27 | 2020-03-24
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0002 | DCAS-Manhattan Municipal Building - Heat Light Installation | 4 | BID AWARD AND REGISTER CONTRCT | 2020-03-25 | 2020-06-22 | 2020-03-25 | 2020-06-22
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0002 | DCAS-Manhattan Municipal Building - Heat Light Installation | 5 | CONSTRUCTION TO 25% | 2020-06-23 | 2020-10-20 | 2020-06-23 | 2020-10-20
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0002 | DCAS-Manhattan Municipal Building - Heat Light Installation | 6 | CONSTRUCTION TO 50% | 2020-10-21 | 2021-02-17 | 2020-10-21 | 2021-02-17
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0002 | DCAS-Manhattan Municipal Building - Heat Light Installation | 7 | CONSTRUCTION TO 75% | 2021-02-18 | 2021-06-17 | 2021-02-18 | 2021-06-17
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0002 | DCAS-Manhattan Municipal Building - Heat Light Installation | 8 | ORIGINAL EQUIP & FURNISHING | 2021-06-18 | 2021-09-15 | 2021-06-18 | 2021-09-15
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0002 | DCAS-Manhattan Municipal Building - Heat Light Installation | 9 | SUBSTANTIAL COMPLETION | 2021-09-16 | 2021-11-14 | 2021-09-16 | 2021-11-14
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0002 | DCAS-Manhattan Municipal Building - Heat Light Installation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-11-15 | 2021-12-14 | 2021-11-15 | 2021-12-14
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0003 | DFTA-Cypress Hills Senior Center - Lighting Upgrade | 1 | DEVELOP SCOPE | 2019-03-01 | 2019-05-29 | 2019-03-01 | 2019-05-29
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0003 | DFTA-Cypress Hills Senior Center - Lighting Upgrade | 2 | PRELIMINARY DESIGN | 2019-05-30 | 2019-09-26 | 2019-05-30 | 2019-09-26
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0003 | DFTA-Cypress Hills Senior Center - Lighting Upgrade | 3 | FINAL DESIGN | 2019-09-27 | 2020-03-24 | 2019-09-27 | 2020-03-24
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0003 | DFTA-Cypress Hills Senior Center - Lighting Upgrade | 4 | BID AWARD AND REGISTER CONTRCT | 2020-03-25 | 2020-06-22 | 2020-03-25 | 2020-06-22
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0003 | DFTA-Cypress Hills Senior Center - Lighting Upgrade | 5 | CONSTRUCTION TO 25% | 2020-06-23 | 2020-10-20 | 2020-06-23 | 2020-10-20
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0003 | DFTA-Cypress Hills Senior Center - Lighting Upgrade | 6 | CONSTRUCTION TO 50% | 2020-10-21 | 2021-02-17 | 2020-10-21 | 2021-02-17
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0003 | DFTA-Cypress Hills Senior Center - Lighting Upgrade | 7 | CONSTRUCTION TO 75% | 2021-02-18 | 2021-06-17 | 2021-02-18 | 2021-06-17
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0003 | DFTA-Cypress Hills Senior Center - Lighting Upgrade | 8 | ORIGINAL EQUIP & FURNISHING | 2021-06-18 | 2021-09-15 | 2021-06-18 | 2021-09-15
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0003 | DFTA-Cypress Hills Senior Center - Lighting Upgrade | 9 | SUBSTANTIAL COMPLETION | 2021-09-16 | 2021-11-14 | 2021-09-16 | 2021-11-14
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0003 | DFTA-Cypress Hills Senior Center - Lighting Upgrade | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-11-15 | 2021-12-14 | 2021-11-15 | 2021-12-14
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | F175LC8 | RENOVATION L8 | 1 | PROJECT START | 2005-06-27 | 2005-06-27 | 2005-06-27 | 2005-06-27
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | F175LC8 | RENOVATION L8 | 2 | DESIGN START | 2005-06-28 | 2005-11-24 | 2005-06-28 | 2005-11-24
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | F175LC8 | RENOVATION L8 | 3 | DESIGN COMPLETION | 2005-11-25 | 2007-01-23 | 2005-11-25 | 2008-02-04
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | F175LC8 | RENOVATION L8 | 4 | CONSTRUCTION START | 2007-01-24 | 2007-06-03 | 2015-11-23 | 2018-05-22
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | F175LC8 | RENOVATION L8 | 5 | CONSTRUCTION COMPLETION | 2007-06-04 | 2008-10-04 | 2018-05-23 | 2022-06-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | F175MCE23 | ELECTRIC & TOILETS - EC23 | 1 | DESIGN | 2013-08-15 | 2014-02-10 | 2013-10-24 | 2013-10-24
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | F175MCE23 | ELECTRIC & TOILETS - EC23 | 2 | CONSTRUCTION | 2014-02-11 | 2015-02-10 | 2013-10-25 | 2015-11-29
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | F175MCE23 | ELECTRIC & TOILETS - EC23 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-02-11 | 2015-05-11 | 2015-11-30 | 2017-02-24
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | F175MCE23 | ELECTRIC & TOILETS - EC23 | 4 | PROJECT START | 2015-02-11 | 2015-05-11 | 2013-10-24 | 2013-10-24
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | F175MCE23 | ELECTRIC & TOILETS - EC23 | 5 | DESIGN START | 2015-02-11 | 2015-05-11 | 2014-05-12 | 2015-05-11
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | F175MCE23 | ELECTRIC & TOILETS - EC23 | 6 | DESIGN COMPLETION | 2015-02-11 | 2015-05-11 | 2015-05-12 | 2015-08-07
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | F175MCE23 | ELECTRIC & TOILETS - EC23 | 7 | CONSTRUCTION START | 2015-02-11 | 2015-05-11 | 2017-06-13 | 2018-06-12
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | F175MCE23 | ELECTRIC & TOILETS - EC23 | 8 | CONSTRUCTION COMPLETION | 2015-02-11 | 2015-05-11 | 2018-03-12 | 2021-06-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HBMA24662 | W 128TH ST PED BRIDGE BIN:2246620 | 1 | DEVELOP SCOPE | 2018-06-30 | 2019-06-29 | 0 | 0
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HBMA24662 | W 128TH ST PED BRIDGE BIN:2246620 | 2 | DESIGN START | 2019-06-30 | 2023-06-28 | 2018-06-30 | 2019-06-29
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HBMA24662 | W 128TH ST PED BRIDGE BIN:2246620 | 3 | CONSTRUCTION START | 2023-06-29 | 2025-06-27 | 2019-06-30 | 2023-06-28
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HBMA24662 | W 128TH ST PED BRIDGE BIN:2246620 | 5 | CONSTRUCTION START | 2023-06-29 | 2025-06-27 | 2023-06-29 | 2025-06-27
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HBPED100M | PED BRIDGE - E 81 ST (M) | 1 | DEVELOP SCOPE | 2013-05-20 | 2013-08-17 | 2013-05-20 | 2013-08-17
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HBPED100M | PED BRIDGE - E 81 ST (M) | 2 | PRELIMINARY DESIGN | 2013-08-18 | 2013-12-15 | 2013-08-18 | 2013-12-15
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HBPED100M | PED BRIDGE - E 81 ST (M) | 3 | FINAL DESIGN | 2013-12-16 | 2014-06-13 | 2013-12-16 | 2014-06-13
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HBPED100M | PED BRIDGE - E 81 ST (M) | 4 | BID AWARD AND REGISTER CONTRCT | 2014-06-14 | 2014-09-11 | 2014-06-14 | 2014-09-11
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HBPED100M | PED BRIDGE - E 81 ST (M) | 5 | CONSTRUCTION TO 25% | 2014-09-12 | 2015-01-09 | 2014-09-12 | 2015-01-09
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HBPED100M | PED BRIDGE - E 81 ST (M) | 6 | CONSTRUCTION TO 50% | 2015-01-10 | 2015-05-09 | 2015-01-10 | 2015-05-09
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HBPED100M | PED BRIDGE - E 81 ST (M) | 7 | CONSTRUCTION TO 75% | 2015-05-10 | 2015-09-06 | 2015-05-10 | 2016-01-04
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HBPED100M | PED BRIDGE - E 81 ST (M) | 8 | ORIGINAL EQUIP & FURNISHING | 2015-09-07 | 2015-12-05 | 2016-01-05 | 2016-01-04
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HBPED100M | PED BRIDGE - E 81 ST (M) | 9 | SUBSTANTIAL COMPLETION | 2015-12-06 | 2016-02-03 | 2016-01-05 | 2016-05-03
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HBPED100M | PED BRIDGE - E 81 ST (M) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-02-04 | 2016-03-04 | 2016-05-04 | 2021-12-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BEES | BELLEVUE - ELECT SVC UPGRADE | 1 | PROJECT START | 2016-01-22 | 2016-01-22 | 2016-01-22 | 2016-01-22
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BEES | BELLEVUE - ELECT SVC UPGRADE | 2 | DESIGN START | 2016-01-23 | 2016-07-22 | 2016-01-23 | 2016-07-22
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BEES | BELLEVUE - ELECT SVC UPGRADE | 3 | DESIGN COMPLETION | 2016-07-23 | 2018-07-05 | 2016-07-23 | 2018-07-05
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BEES | BELLEVUE - ELECT SVC UPGRADE | 4 | CONSTRUCTION START | 2018-07-06 | 2020-01-16 | 2018-07-06 | 2020-01-16
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BEES | BELLEVUE - ELECT SVC UPGRADE | 5 | CONSTRUCTION COMPLETION | 2012-01-29 | 2016-01-22 | 2020-01-17 | 2022-01-22
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BLBR | BELLEVUE BATHROOMS RECONSTRUCTION | 1 | PROJECT START | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BLBR | BELLEVUE BATHROOMS RECONSTRUCTION | 2 | DESIGN START | 2016-09-27 | 2018-01-29 | 2016-09-27 | 2018-01-29
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BLBR | BELLEVUE BATHROOMS RECONSTRUCTION | 3 | DESIGN COMPLETION | 2018-01-30 | 2019-01-29 | 2018-01-30 | 2019-01-29
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BLBR | BELLEVUE BATHROOMS RECONSTRUCTION | 4 | CONSTRUCTION START | 2019-01-30 | 2019-10-25 | 2019-01-30 | 2019-10-25
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BLBR | BELLEVUE BATHROOMS RECONSTRUCTION | 5 | CONSTRUCTION COMPLETION | 2019-10-26 | 2023-07-28 | 2019-10-26 | 2023-07-28
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BLCY | BELLEVUE COURTYARD | 1 | PROJECT START | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BLCY | BELLEVUE COURTYARD | 2 | DESIGN START | 2016-09-24 | 2018-08-24 | 2016-09-24 | 2018-08-24
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BLCY | BELLEVUE COURTYARD | 3 | DESIGN COMPLETION | 2018-08-25 | 2019-08-30 | 2018-08-25 | 2019-08-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BLCY | BELLEVUE COURTYARD | 4 | CONSTRUCTION START | 2019-08-31 | 2020-04-17 | 2019-08-31 | 2020-04-17
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BLCY | BELLEVUE COURTYARD | 5 | CONSTRUCTION COMPLETION | 2020-04-18 | 2022-10-21 | 2020-04-18 | 2026-06-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BLEN | BELLEVUE MAIN ATRIUM | 1 | PROJECT START | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BLEN | BELLEVUE MAIN ATRIUM | 2 | DESIGN START | 2016-09-24 | 2018-08-24 | 2016-09-24 | 2018-08-24
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BLEN | BELLEVUE MAIN ATRIUM | 3 | DESIGN COMPLETION | 2018-08-25 | 2019-08-23 | 2018-08-25 | 2019-08-23
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BLEN | BELLEVUE MAIN ATRIUM | 4 | CONSTRUCTION START | 2019-08-24 | 2020-04-17 | 2019-08-24 | 2020-04-17
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BLEN | BELLEVUE MAIN ATRIUM | 5 | CONSTRUCTION COMPLETION | 2020-04-18 | 2021-12-17 | 2020-04-18 | 2026-12-31
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BLFS | BELLEVUE MEN'S RESIDENCE- FIRE SAFETY | 1 | PROJECT START | 2016-08-31 | 2016-08-31 | 2016-08-31 | 2016-08-31
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BLFS | BELLEVUE MEN'S RESIDENCE- FIRE SAFETY | 2 | DESIGN START | 2016-09-01 | 2018-05-21 | 2016-09-01 | 2018-05-21
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BLFS | BELLEVUE MEN'S RESIDENCE- FIRE SAFETY | 3 | DESIGN COMPLETION | 2018-05-22 | 2019-05-10 | 2018-05-22 | 2019-05-10
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BLFS | BELLEVUE MEN'S RESIDENCE- FIRE SAFETY | 4 | CONSTRUCTION START | 2019-05-11 | 2020-01-31 | 2019-05-11 | 2020-01-31
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BLFS | BELLEVUE MEN'S RESIDENCE- FIRE SAFETY | 5 | CONSTRUCTION COMPLETION | 2020-02-01 | 2021-11-28 | 2020-02-01 | 2021-11-28
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BLRR | BELLEVUE ROOF/ FACADE | 1 | PROJECT START | 2016-01-22 | 2016-01-22 | 2016-01-22 | 2016-01-22
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BLRR | BELLEVUE ROOF/ FACADE | 2 | DESIGN START | 2016-01-23 | 2016-07-05 | 2016-01-23 | 2016-07-05
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BLRR | BELLEVUE ROOF/ FACADE | 3 | DESIGN COMPLETION | 2016-07-06 | 2017-12-14 | 2016-07-06 | 2017-12-14
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BLRR | BELLEVUE ROOF/ FACADE | 4 | CONSTRUCTION START | 2017-12-15 | 2018-09-05 | 2017-12-15 | 2018-09-05
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BLRR | BELLEVUE ROOF/ FACADE | 5 | CONSTRUCTION COMPLETION | 2018-09-06 | 2021-08-31 | 2018-09-06 | 2021-08-31
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BVDV | BELLEVUE DIVERSION INTERIOR RENOVATION | 1 | PROJECT START | 2015-10-23 | 2015-10-23 | 2015-10-23 | 2015-10-23
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BVDV | BELLEVUE DIVERSION INTERIOR RENOVATION | 2 | DESIGN START | 2015-10-24 | 2015-10-26 | 2015-10-24 | 2015-10-26
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BVDV | BELLEVUE DIVERSION INTERIOR RENOVATION | 3 | DESIGN COMPLETION | 2015-10-27 | 2016-10-25 | 2015-10-27 | 2016-10-25
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BVDV | BELLEVUE DIVERSION INTERIOR RENOVATION | 4 | CONSTRUCTION START | 2016-10-26 | 2017-05-01 | 2016-10-26 | 2017-05-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BVDV | BELLEVUE DIVERSION INTERIOR RENOVATION | 5 | CONSTRUCTION COMPLETION | 2017-05-02 | 2018-08-24 | 2017-05-02 | 2021-06-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112CGIU | Keener Assessment Shelter - Fire Alarm Upgrade | 1 | PROJECT START | 2016-09-28 | 2016-09-28 | 2016-09-28 | 2016-09-28
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112CGIU | Keener Assessment Shelter - Fire Alarm Upgrade | 2 | DESIGN START | 2017-11-15 | 2018-01-05 | 2017-11-15 | 2018-01-05
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112CGIU | Keener Assessment Shelter - Fire Alarm Upgrade | 3 | DESIGN COMPLETION | 2018-11-16 | 2019-04-26 | 2018-11-16 | 2019-04-26
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112CGIU | Keener Assessment Shelter - Fire Alarm Upgrade | 4 | CONSTRUCTION START | 2019-07-19 | 2024-07-19 | 2019-07-19 | 2024-07-19
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112CGIU | Keener Assessment Shelter - Fire Alarm Upgrade | 5 | CONSTRUCTION COMPLETION | 2024-07-20 | 2026-01-23 | 2024-07-20 | 2026-01-23
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112CTFS | CLARKE THOMAS FIRE SAFETY | 1 | PROJECT START | 2016-07-26 | 2016-07-26 | 2016-07-26 | 2016-07-26
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112CTFS | CLARKE THOMAS FIRE SAFETY | 2 | DESIGN START | 2016-07-27 | 2018-01-03 | 2016-07-27 | 2018-01-03
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112CTFS | CLARKE THOMAS FIRE SAFETY | 3 | DESIGN COMPLETION | 2018-01-04 | 2018-11-16 | 2018-01-04 | 2018-11-16
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112CTFS | CLARKE THOMAS FIRE SAFETY | 4 | CONSTRUCTION START | 2018-11-17 | 2019-07-19 | 2018-11-17 | 2021-07-19
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112CTFS | CLARKE THOMAS FIRE SAFETY | 5 | CONSTRUCTION COMPLETION | 2019-07-20 | 2020-07-24 | 2021-07-20 | 2023-07-25
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112FTRF | FT. WASHINGTON ARMORY ROOF REPLACEMENT | 1 | PROJECT START | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112FTRF | FT. WASHINGTON ARMORY ROOF REPLACEMENT | 2 | DESIGN START | 2018-01-02 | 2018-07-01 | 2018-01-02 | 2018-07-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112FTRF | FT. WASHINGTON ARMORY ROOF REPLACEMENT | 3 | DESIGN COMPLETION | 2018-07-02 | 2019-01-31 | 2018-07-02 | 2019-01-31
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112FTRF | FT. WASHINGTON ARMORY ROOF REPLACEMENT | 4 | CONSTRUCTION START | 2019-02-01 | 2019-07-01 | 2019-02-01 | 2019-07-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112FTRF | FT. WASHINGTON ARMORY ROOF REPLACEMENT | 5 | CONSTRUCTION COMPLETION | 2019-07-02 | 2020-12-31 | 2019-07-02 | 2024-02-04
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112FWFA | FT. WASHINGTON - FIRE ALARM | 1 | PROJECT START | 2016-03-30 | 2016-03-31 | 2016-03-30 | 2016-03-31
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112FWFA | FT. WASHINGTON - FIRE ALARM | 2 | DESIGN START | 2016-04-01 | 2016-07-01 | 2016-04-01 | 2016-07-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112FWFA | FT. WASHINGTON - FIRE ALARM | 3 | DESIGN COMPLETION | 2016-07-02 | 2017-06-30 | 2016-07-02 | 2017-06-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112FWFA | FT. WASHINGTON - FIRE ALARM | 4 | CONSTRUCTION START | 2017-07-01 | 2017-10-31 | 2017-07-01 | 2017-10-31
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112FWFA | FT. WASHINGTON - FIRE ALARM | 5 | CONSTRUCTION COMPLETION | 2017-11-01 | 2023-06-30 | 2017-11-01 | 2023-06-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112HMFA | HARLEM 1 FIRE SAFETY | 1 | PROJECT START | 2016-07-26 | 2016-07-26 | 2016-07-26 | 2016-07-26
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112HMFA | HARLEM 1 FIRE SAFETY | 2 | DESIGN START | 2016-07-27 | 2017-05-24 | 2016-07-27 | 2017-05-24
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112HMFA | HARLEM 1 FIRE SAFETY | 3 | DESIGN COMPLETION | 2017-05-25 | 2017-12-27 | 2017-05-25 | 2017-12-27
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112HMFA | HARLEM 1 FIRE SAFETY | 4 | CONSTRUCTION START | 2017-12-28 | 2018-07-16 | 2017-12-28 | 2018-07-16
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112HMFA | HARLEM 1 FIRE SAFETY | 5 | CONSTRUCTION COMPLETION | 2018-07-17 | 2019-07-15 | 2018-07-17 | 2022-06-09
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112HSFA | HELP SEC - FIRE SAFETY | 1 | PROJECT START | 2016-07-26 | 2016-07-26 | 2016-07-26 | 2016-07-26
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112HSFA | HELP SEC - FIRE SAFETY | 2 | DESIGN START | 2016-07-27 | 2018-01-03 | 2016-07-27 | 2018-01-03
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112HSFA | HELP SEC - FIRE SAFETY | 3 | DESIGN COMPLETION | 2018-01-04 | 2018-11-16 | 2018-01-04 | 2018-11-16
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112HSFA | HELP SEC - FIRE SAFETY | 4 | CONSTRUCTION START | 2018-11-17 | 2019-07-19 | 2018-11-17 | 2019-07-19
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112HSFA | HELP SEC - FIRE SAFETY | 5 | CONSTRUCTION COMPLETION | 2019-07-20 | 2020-07-24 | 2019-07-20 | 2023-07-24
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112KEFA | Kenton Hall Fire Safety | 1 | PROJECT START | 2016-07-26 | 2016-07-26 | 2016-07-26 | 2016-07-26
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112KEFA | Kenton Hall Fire Safety | 2 | DESIGN START | 2016-07-27 | 2017-12-28 | 2016-07-27 | 2017-12-28
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112KEFA | Kenton Hall Fire Safety | 3 | DESIGN COMPLETION | 2017-12-29 | 2018-11-23 | 2017-12-29 | 2018-11-23
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112KEFA | Kenton Hall Fire Safety | 4 | CONSTRUCTION START | 2018-11-24 | 2019-07-26 | 2018-11-24 | 2019-07-26
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112KEFA | Kenton Hall Fire Safety | 5 | CONSTRUCTION COMPLETION | 2019-07-27 | 2021-01-22 | 2019-07-27 | 2023-01-22
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112KELC | 282 EAST 3RD STREET - ELECTRICAL UPGRADE | 1 | PROJECT START | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112KELC | 282 EAST 3RD STREET - ELECTRICAL UPGRADE | 2 | DESIGN START | 2018-01-02 | 2018-07-01 | 2018-01-02 | 2018-07-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112KELC | 282 EAST 3RD STREET - ELECTRICAL UPGRADE | 3 | DESIGN COMPLETION | 2018-07-02 | 2019-01-01 | 2018-07-02 | 2019-01-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112KELC | 282 EAST 3RD STREET - ELECTRICAL UPGRADE | 4 | CONSTRUCTION START | 2019-01-02 | 2019-07-01 | 2019-01-02 | 2019-07-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112KELC | 282 EAST 3RD STREET - ELECTRICAL UPGRADE | 5 | CONSTRUCTION COMPLETION | 2019-07-02 | 2020-12-31 | 2019-07-02 | 2024-08-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112SWFA | SCHWARTZ WARDS ISLAND FIRE SAFETY | 1 | PROJECT START | 2016-07-26 | 2016-07-26 | 2016-07-26 | 2016-07-26
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112SWFA | SCHWARTZ WARDS ISLAND FIRE SAFETY | 2 | DESIGN START | 2016-07-27 | 2018-01-03 | 2016-07-27 | 2018-01-03
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112SWFA | SCHWARTZ WARDS ISLAND FIRE SAFETY | 3 | DESIGN COMPLETION | 2018-01-04 | 2018-11-16 | 2018-01-04 | 2018-11-16
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112SWFA | SCHWARTZ WARDS ISLAND FIRE SAFETY | 4 | CONSTRUCTION START | 2018-11-17 | 2019-07-19 | 2018-11-17 | 2019-07-19
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112SWFA | SCHWARTZ WARDS ISLAND FIRE SAFETY | 5 | CONSTRUCTION COMPLETION | 2019-07-20 | 2020-07-24 | 2019-07-20 | 2024-07-24
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112THFA | 8 EAST THIRD ST SHELTER FIRE SAFETY | 1 | PROJECT START | 2016-07-26 | 2016-07-26 | 2016-07-26 | 2016-07-26
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112THFA | 8 EAST THIRD ST SHELTER FIRE SAFETY | 2 | DESIGN START | 2016-07-27 | 2017-05-24 | 2016-07-27 | 2017-05-24
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112THFA | 8 EAST THIRD ST SHELTER FIRE SAFETY | 3 | DESIGN COMPLETION | 2017-05-25 | 2018-11-16 | 2017-05-25 | 2018-11-16
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112THFA | 8 EAST THIRD ST SHELTER FIRE SAFETY | 4 | CONSTRUCTION START | 2018-11-17 | 2019-03-15 | 2018-11-17 | 2019-03-15
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112THFA | 8 EAST THIRD ST SHELTER FIRE SAFETY | 5 | CONSTRUCTION COMPLETION | 2019-03-16 | 2020-09-18 | 2019-03-16 | 2024-09-18
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112VEFP | VETERAN SRO FIRE PANEL | 2 | DESIGN START | 2016-07-27 | 2017-12-28 | 2016-07-27 | 2017-12-28
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112VEFP | VETERAN SRO FIRE PANEL | 3 | DESIGN COMPLETION | 2017-12-29 | 2018-11-16 | 2017-12-29 | 2018-11-16
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112VEFP | VETERAN SRO FIRE PANEL | 4 | CONSTRUCTION START | 2018-11-17 | 2019-07-19 | 2018-11-17 | 2019-07-19
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112VEFP | VETERAN SRO FIRE PANEL | 5 | CONSTRUCTION COMPLETION | 2019-07-20 | 2020-07-17 | 2024-07-20 | 2024-07-21
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112WBLR | WARDS ISLAND COMPLEX - BOILERS AND FUEL STORAGE TANKS | 1 | PROJECT START | 2012-03-15 | 2012-03-15 | 2012-03-15 | 2012-03-15
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112WBLR | WARDS ISLAND COMPLEX - BOILERS AND FUEL STORAGE TANKS | 2 | DESIGN START | 2012-03-16 | 2012-06-18 | 2012-03-16 | 2012-06-18
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112WBLR | WARDS ISLAND COMPLEX - BOILERS AND FUEL STORAGE TANKS | 3 | DESIGN COMPLETION | 2012-06-19 | 2013-02-21 | 2012-06-19 | 2013-02-21
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112WBLR | WARDS ISLAND COMPLEX - BOILERS AND FUEL STORAGE TANKS | 4 | CONSTRUCTION START | 2013-02-22 | 2013-10-24 | 2013-02-22 | 2013-10-24
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112WBLR | WARDS ISLAND COMPLEX - BOILERS AND FUEL STORAGE TANKS | 5 | CONSTRUCTION COMPLETION | 2013-10-25 | 2015-02-24 | 2013-10-25 | 2024-06-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115JCEK | Jennie Clarke Elec and Kitchen | 1 | PROJECT START | 2018-01-01 | 2018-07-01 | 2018-01-01 | 2018-07-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115JCEK | Jennie Clarke Elec and Kitchen | 2 | DESIGN START | 2018-07-02 | 2019-01-01 | 2018-07-02 | 2019-01-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115JCEK | Jennie Clarke Elec and Kitchen | 3 | DESIGN COMPLETION | 2019-01-02 | 2019-07-01 | 2019-01-02 | 2020-07-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115JCEK | Jennie Clarke Elec and Kitchen | 4 | CONSTRUCTION START | 2019-07-02 | 2020-01-01 | 2020-07-02 | 2022-01-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115JCEK | Jennie Clarke Elec and Kitchen | 5 | CONSTRUCTION COMPLETION | 2020-01-02 | 2020-07-01 | 2022-01-02 | 2024-07-02
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115JCFB | JENNIE CLARK RESIDENCE - FIRE ALARM UPGRADE | 1 | PROJECT START | 2016-03-30 | 2016-03-31 | 2016-03-30 | 2016-03-31
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115JCFB | JENNIE CLARK RESIDENCE - FIRE ALARM UPGRADE | 2 | DESIGN START | 2016-04-01 | 2016-07-01 | 2016-04-01 | 2016-07-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115JCFB | JENNIE CLARK RESIDENCE - FIRE ALARM UPGRADE | 3 | DESIGN COMPLETION | 2016-07-02 | 2017-06-30 | 2016-07-02 | 2017-06-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115JCFB | JENNIE CLARK RESIDENCE - FIRE ALARM UPGRADE | 4 | CONSTRUCTION START | 2017-07-01 | 2017-10-31 | 2017-07-01 | 2018-06-28
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115JCFB | JENNIE CLARK RESIDENCE - FIRE ALARM UPGRADE | 5 | CONSTRUCTION COMPLETION | 2017-11-01 | 2023-06-30 | 2018-06-29 | 2022-08-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115REGX | REGENT FAMILY RESIDENCE EXTERIOR UPGRADE | 1 | PROJECT START | 2007-08-15 | 2007-08-15 | 2007-08-15 | 2007-08-15
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115REGX | REGENT FAMILY RESIDENCE EXTERIOR UPGRADE | 2 | DESIGN START | 2007-08-16 | 2008-04-15 | 2007-08-16 | 2008-04-15
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115REGX | REGENT FAMILY RESIDENCE EXTERIOR UPGRADE | 3 | DESIGN COMPLETION | 2008-04-16 | 2009-04-26 | 2008-04-16 | 2009-04-26
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115REGX | REGENT FAMILY RESIDENCE EXTERIOR UPGRADE | 4 | CONSTRUCTION START | 2009-04-27 | 2009-09-20 | 2009-04-27 | 2009-09-20
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115REGX | REGENT FAMILY RESIDENCE EXTERIOR UPGRADE | 5 | CONSTRUCTION COMPLETION | 2009-09-21 | 2011-06-30 | 2009-09-21 | 2020-12-19
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115RFEU | REGENT FAMILY APT. ELEC UPGRADE | 1 | PROJECT START | 2016-03-30 | 2016-03-31 | 2016-03-30 | 2016-03-31
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115RFEU | REGENT FAMILY APT. ELEC UPGRADE | 2 | DESIGN START | 2016-04-01 | 2016-07-01 | 2016-04-01 | 2016-07-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115RFEU | REGENT FAMILY APT. ELEC UPGRADE | 3 | DESIGN COMPLETION | 2016-07-02 | 2017-06-30 | 2016-07-02 | 2017-06-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115RFEU | REGENT FAMILY APT. ELEC UPGRADE | 4 | CONSTRUCTION START | 2017-07-01 | 2017-10-31 | 2017-07-01 | 2017-10-31
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115RFEU | REGENT FAMILY APT. ELEC UPGRADE | 5 | CONSTRUCTION COMPLETION | 2017-11-01 | 2023-06-30 | 2017-11-01 | 2023-06-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82125VR | 125 WORTH ST. - OFFICE OF VITAL RECORDS 1ST FLOOR (LVL 3B) | 1 | PROJECT START | 2013-04-04 | 2013-04-04 | 2013-04-04 | 2013-04-04
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82125VR | 125 WORTH ST. - OFFICE OF VITAL RECORDS 1ST FLOOR (LVL 3B) | 2 | DESIGN START | 2013-04-05 | 2013-08-30 | 2013-04-05 | 2013-08-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82125VR | 125 WORTH ST. - OFFICE OF VITAL RECORDS 1ST FLOOR (LVL 3B) | 3 | DESIGN COMPLETION | 2013-08-31 | 2014-06-30 | 2013-08-31 | 2014-06-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82125VR | 125 WORTH ST. - OFFICE OF VITAL RECORDS 1ST FLOOR (LVL 3B) | 4 | CONSTRUCTION START | 2014-07-01 | 2014-08-25 | 2014-07-01 | 2014-08-25
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82125VR | 125 WORTH ST. - OFFICE OF VITAL RECORDS 1ST FLOOR (LVL 3B) | 5 | CONSTRUCTION COMPLETION | 2014-08-26 | 2015-08-31 | 2014-08-26 | 2022-06-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82CHNWH | COMMUNITY HEALTHCARE NETWORK-WASHINGTON HEIGHTS | 1 | PROJECT START | 2008-04-01 | 2008-04-01 | 2011-07-01 | 2012-12-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82CHNWH | COMMUNITY HEALTHCARE NETWORK-WASHINGTON HEIGHTS | 2 | DESIGN START | 2008-04-02 | 2008-04-02 | 2012-12-31 | 2013-12-31
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82CHNWH | COMMUNITY HEALTHCARE NETWORK-WASHINGTON HEIGHTS | 3 | DESIGN COMPLETION | 2008-04-03 | 2008-04-03 | 2014-01-01 | 2015-01-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82CHNWH | COMMUNITY HEALTHCARE NETWORK-WASHINGTON HEIGHTS | 4 | CONSTRUCTION START | 2008-04-04 | 2008-04-04 | 2015-01-02 | 2016-01-02
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82CHNWH | COMMUNITY HEALTHCARE NETWORK-WASHINGTON HEIGHTS | 5 | CONSTRUCTION COMPLETION | 2008-04-05 | 2008-04-05 | 2016-01-03 | 2021-01-03
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82DNA9F | INITIAL OUTFITTING FOR THE NEW DNA LAB 9TH FLOOR- OCME | 1 | PROJECT START | 2000-02-01 | 2000-02-01 | 2000-02-01 | 2001-01-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82DNA9F | INITIAL OUTFITTING FOR THE NEW DNA LAB 9TH FLOOR- OCME | 2 | DESIGN START | 2000-02-01 | 2000-02-01 | 2001-02-01 | 2002-01-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82DNA9F | INITIAL OUTFITTING FOR THE NEW DNA LAB 9TH FLOOR- OCME | 3 | DESIGN COMPLETION | 2000-02-02 | 2000-02-01 | 2002-02-02 | 2003-01-31
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82DNA9F | INITIAL OUTFITTING FOR THE NEW DNA LAB 9TH FLOOR- OCME | 4 | CONSTRUCTION START | 2000-02-02 | 2000-02-01 | 2003-02-02 | 2004-01-31
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82DNA9F | INITIAL OUTFITTING FOR THE NEW DNA LAB 9TH FLOOR- OCME | 5 | CONSTRUCTION COMPLETION | 2000-02-02 | 2003-08-04 | 2004-02-02 | 2026-08-04
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82MANAT | Manhattan Animal Care Center Upgrade | 1 | DESIGN | 2018-01-01 | 2019-05-25 | 2018-01-18 | 2018-04-17
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82MANAT | Manhattan Animal Care Center Upgrade | 2 | CONSTRUCTION | 2019-05-26 | 2024-05-23 | 2018-04-18 | 2018-08-15
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82MANAT | Manhattan Animal Care Center Upgrade | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-05-24 | 2024-05-23 | 2018-08-16 | 2019-02-11
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82MANAT | Manhattan Animal Care Center Upgrade | 4 | DEVELOP SCOPE | 2024-05-24 | 2024-05-23 | 2019-02-12 | 2019-05-12
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82MANAT | Manhattan Animal Care Center Upgrade | 5 | PRELIMINARY DESIGN | 2024-05-24 | 2024-05-23 | 2019-05-13 | 2019-09-09
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82MANAT | Manhattan Animal Care Center Upgrade | 6 | FINAL DESIGN | 2024-05-24 | 2024-05-23 | 2019-09-10 | 2020-01-07
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82MANAT | Manhattan Animal Care Center Upgrade | 7 | BID AWARD AND REGISTER CONTRCT | 2024-05-24 | 2024-05-23 | 2020-01-08 | 2020-05-06
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82MANAT | Manhattan Animal Care Center Upgrade | 8 | CONSTRUCTION TO 25% | 2024-05-24 | 2024-05-23 | 2020-05-07 | 2020-08-04
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82MANAT | Manhattan Animal Care Center Upgrade | 9 | CONSTRUCTION TO 50% | 2024-05-24 | 2024-05-23 | 2020-08-05 | 2020-10-03
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82MANAT | Manhattan Animal Care Center Upgrade | 10 | CONSTRUCTION TO 75% | 2024-05-24 | 2024-05-23 | 2020-10-04 | 2024-06-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82MANAT | Manhattan Animal Care Center Upgrade | 11 | ORIGINAL EQUIP & FURNISHING | 2024-05-24 | 2024-05-23 | 2020-10-04 | 2024-06-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82MANAT | Manhattan Animal Care Center Upgrade | 12 | SUBSTANTIAL COMPLETION | 2024-05-24 | 2024-05-23 | 2020-10-04 | 2024-06-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82MANAT | Manhattan Animal Care Center Upgrade | 13 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-05-24 | 2024-06-22 | 2020-10-04 | 2024-06-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWBARUCH | Baruch College - 25th Street Plaza (MED-634) | 1 | DEVELOP SCOPE | 2015-03-01 | 2015-05-29 | 2013-07-30 | 2014-03-09
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWBARUCH | Baruch College - 25th Street Plaza (MED-634) | 2 | PRELIMINARY DESIGN | 2015-05-30 | 2015-09-26 | 2014-03-10 | 2015-11-17
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWBARUCH | Baruch College - 25th Street Plaza (MED-634) | 3 | FINAL DESIGN | 2015-09-27 | 2016-03-24 | 2015-11-18 | 2016-09-16
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWBARUCH | Baruch College - 25th Street Plaza (MED-634) | 4 | BID AWARD AND REGISTER CONTRCT | 2016-03-25 | 2016-06-22 | 2016-09-17 | 2018-06-17
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWBARUCH | Baruch College - 25th Street Plaza (MED-634) | 5 | CONSTRUCTION TO 25% | 2016-06-23 | 2016-10-20 | 2018-06-18 | 2018-10-15
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWBARUCH | Baruch College - 25th Street Plaza (MED-634) | 6 | CONSTRUCTION TO 50% | 2016-10-21 | 2017-02-17 | 2018-10-16 | 2019-02-12
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWBARUCH | Baruch College - 25th Street Plaza (MED-634) | 7 | CONSTRUCTION TO 75% | 2017-02-18 | 2017-06-17 | 2019-02-13 | 2019-06-12
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWBARUCH | Baruch College - 25th Street Plaza (MED-634) | 8 | ORIGINAL EQUIP & FURNISHING | 2017-06-18 | 2017-09-15 | 2019-06-13 | 2019-09-10
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWBARUCH | Baruch College - 25th Street Plaza (MED-634) | 9 | SUBSTANTIAL COMPLETION | 2017-09-16 | 2017-11-14 | 2019-09-11 | 2019-11-09
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWBARUCH | Baruch College - 25th Street Plaza (MED-634) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-11-15 | 2017-12-14 | 2019-11-10 | 2023-06-16
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD10211 | 185th St. - Streetscape Improvements | 1 | DEVELOP SCOPE | 2012-06-30 | 2013-09-28 | 2011-10-14 | 2012-04-17
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD10211 | 185th St. - Streetscape Improvements | 2 | PRELIMINARY DESIGN | 2013-09-29 | 2013-09-28 | 2012-04-18 | 2014-01-07
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD10211 | 185th St. - Streetscape Improvements | 3 | FINAL DESIGN | 2013-09-29 | 2013-09-28 | 2014-01-08 | 2014-12-26
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD10211 | 185th St. - Streetscape Improvements | 4 | BID AWARD AND REGISTER CONTRCT | 2013-09-29 | 2013-09-28 | 2014-12-27 | 2016-05-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD10211 | 185th St. - Streetscape Improvements | 5 | CONSTRUCTION TO 25% | 2013-09-29 | 2013-09-28 | 2016-05-31 | 2016-10-27
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD10211 | 185th St. - Streetscape Improvements | 6 | CONSTRUCTION TO 50% | 2013-09-29 | 2013-09-28 | 2016-10-28 | 2017-03-26
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD10211 | 185th St. - Streetscape Improvements | 7 | CONSTRUCTION TO 75% | 2013-09-29 | 2013-09-28 | 2017-03-27 | 2017-08-23
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD10211 | 185th St. - Streetscape Improvements | 8 | ORIGINAL EQUIP & FURNISHING | 2013-09-29 | 2013-09-28 | 2017-08-24 | 2017-12-21
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD10211 | 185th St. - Streetscape Improvements | 9 | SUBSTANTIAL COMPLETION | 2013-09-29 | 2013-09-28 | 2017-12-22 | 2018-03-21
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD10211 | 185th St. - Streetscape Improvements | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-09-29 | 2013-10-28 | 2018-03-22 | 2026-06-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM100SNC | 79TH STREET SBS, MED-673 | 1 | DEVELOP SCOPE | 2018-06-30 | 2018-09-27 | 2019-06-30 | 2019-09-27
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM100SNC | 79TH STREET SBS, MED-673 | 2 | PRELIMINARY DESIGN | 2018-09-28 | 2019-01-25 | 2019-09-28 | 2020-01-25
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM100SNC | 79TH STREET SBS, MED-673 | 3 | FINAL DESIGN | 2019-01-26 | 2019-07-24 | 2020-01-26 | 2020-07-23
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM100SNC | 79TH STREET SBS, MED-673 | 4 | BID AWARD AND REGISTER CONTRCT | 2019-07-25 | 2019-10-22 | 2020-07-24 | 2020-10-21
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM100SNC | 79TH STREET SBS, MED-673 | 5 | CONSTRUCTION TO 25% | 2019-10-23 | 2020-02-19 | 2020-10-22 | 2021-02-18
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM100SNC | 79TH STREET SBS, MED-673 | 6 | CONSTRUCTION TO 50% | 2020-02-20 | 2020-06-18 | 2021-02-19 | 2021-06-18
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM100SNC | 79TH STREET SBS, MED-673 | 7 | CONSTRUCTION TO 75% | 2020-06-19 | 2020-10-16 | 2021-06-19 | 2021-10-16
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM100SNC | 79TH STREET SBS, MED-673 | 8 | ORIGINAL EQUIP & FURNISHING | 2020-10-17 | 2021-01-14 | 2021-10-17 | 2022-01-14
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM100SNC | 79TH STREET SBS, MED-673 | 9 | SUBSTANTIAL COMPLETION | 2021-01-15 | 2021-03-15 | 2022-01-15 | 2022-03-15
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM100SNC | 79TH STREET SBS, MED-673 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-16 | 2021-04-14 | 2022-03-16 | 2028-09-11
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM1159 | REHABILITATION OF PECK SLIP | 1 | DEVELOP SCOPE | 2001-05-21 | 2001-08-18 | 2001-05-21 | 2001-08-18
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM1159 | REHABILITATION OF PECK SLIP | 2 | PRELIMINARY DESIGN | 2001-08-19 | 2001-12-16 | 2001-08-19 | 2001-12-16
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM1159 | REHABILITATION OF PECK SLIP | 3 | FINAL DESIGN | 2001-12-17 | 2002-06-14 | 2001-12-17 | 2002-06-14
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM1159 | REHABILITATION OF PECK SLIP | 4 | BID AWARD AND REGISTER CONTRCT | 2007-03-01 | 2007-06-01 | 2007-03-01 | 2011-06-25
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM1159 | REHABILITATION OF PECK SLIP | 5 | CONSTRUCTION TO 25% | 2007-06-02 | 2007-06-01 | 2011-06-26 | 2011-06-25
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM1159 | REHABILITATION OF PECK SLIP | 6 | CONSTRUCTION TO 50% | 2007-06-02 | 2007-06-01 | 2011-06-26 | 2011-06-25
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM1159 | REHABILITATION OF PECK SLIP | 7 | CONSTRUCTION TO 75% | 2007-06-02 | 2007-06-01 | 2011-06-26 | 2011-06-25
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM1159 | REHABILITATION OF PECK SLIP | 8 | ORIGINAL EQUIP & FURNISHING | 2007-06-02 | 2007-06-01 | 2011-06-26 | 2011-06-25
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM1159 | REHABILITATION OF PECK SLIP | 9 | SUBSTANTIAL COMPLETION | 2007-06-02 | 2007-06-01 | 2011-06-26 | 2011-06-25
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM1159 | REHABILITATION OF PECK SLIP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2007-06-02 | 2007-07-01 | 2011-06-26 | 2022-06-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM12AVE | 12th Avenue Accessibility Improvements | 1 | DEVELOP SCOPE | 2020-06-30 | 2020-09-27 | 2019-01-07 | 2019-10-08
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM12AVE | 12th Avenue Accessibility Improvements | 2 | PRELIMINARY DESIGN | 2020-09-28 | 2021-01-25 | 2019-10-09 | 2020-02-05
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM12AVE | 12th Avenue Accessibility Improvements | 3 | FINAL DESIGN | 2021-01-26 | 2021-07-24 | 2020-02-06 | 2020-08-03
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM12AVE | 12th Avenue Accessibility Improvements | 4 | BID AWARD AND REGISTER CONTRCT | 2021-07-25 | 2021-10-22 | 2020-08-04 | 2020-11-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM12AVE | 12th Avenue Accessibility Improvements | 5 | CONSTRUCTION TO 25% | 2021-10-23 | 2022-02-19 | 2020-11-02 | 2021-03-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM12AVE | 12th Avenue Accessibility Improvements | 6 | CONSTRUCTION TO 50% | 2022-02-20 | 2022-06-19 | 2021-03-02 | 2021-06-29
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM12AVE | 12th Avenue Accessibility Improvements | 7 | CONSTRUCTION TO 75% | 2022-06-20 | 2022-10-17 | 2021-06-30 | 2021-10-27
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM12AVE | 12th Avenue Accessibility Improvements | 8 | ORIGINAL EQUIP & FURNISHING | 2022-10-18 | 2023-01-15 | 2023-09-12 | 2025-03-05
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM12AVE | 12th Avenue Accessibility Improvements | 9 | SUBSTANTIAL COMPLETION | 2023-01-16 | 2023-03-16 | 2025-03-06 | 2025-05-04
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM12AVE | 12th Avenue Accessibility Improvements | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-03-17 | 2023-04-15 | 2025-05-05 | 2037-03-14
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM2025 | Delancey Street Safety Improvements (MED-667) | 1 | DEVELOP SCOPE | 2017-03-01 | 2017-05-29 | 2017-03-01 | 2017-05-29
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM2025 | Delancey Street Safety Improvements (MED-667) | 2 | PRELIMINARY DESIGN | 2017-05-30 | 2017-09-26 | 2017-05-30 | 2017-09-26
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM2025 | Delancey Street Safety Improvements (MED-667) | 3 | FINAL DESIGN | 2017-09-27 | 2018-03-25 | 2017-09-27 | 2018-03-25
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM2025 | Delancey Street Safety Improvements (MED-667) | 4 | BID AWARD AND REGISTER CONTRCT | 2018-03-26 | 2018-06-23 | 2018-03-26 | 2018-06-23
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM2025 | Delancey Street Safety Improvements (MED-667) | 5 | CONSTRUCTION TO 25% | 2018-06-24 | 2018-10-21 | 2018-06-24 | 2018-10-21
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM2025 | Delancey Street Safety Improvements (MED-667) | 6 | CONSTRUCTION TO 50% | 2018-10-22 | 2019-02-18 | 2018-10-22 | 2019-02-18
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM2025 | Delancey Street Safety Improvements (MED-667) | 7 | CONSTRUCTION TO 75% | 2019-02-19 | 2019-06-18 | 2019-02-19 | 2019-06-18
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM2025 | Delancey Street Safety Improvements (MED-667) | 8 | ORIGINAL EQUIP & FURNISHING | 2019-06-19 | 2019-09-16 | 2019-06-19 | 2019-09-16
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM2025 | Delancey Street Safety Improvements (MED-667) | 9 | SUBSTANTIAL COMPLETION | 2019-09-17 | 2019-11-15 | 2019-09-17 | 2019-11-15
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM2025 | Delancey Street Safety Improvements (MED-667) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-11-16 | 2019-12-15 | 2019-11-16 | 2025-06-14
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMM008 | EAST 86TH ST STREETSCAPE-225 EAST 79TH ,MADISON TO YORK AVE | 1 | DEVELOP SCOPE | 2009-06-01 | 2009-09-28 | 2009-06-01 | 2009-08-29
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMM008 | EAST 86TH ST STREETSCAPE-225 EAST 79TH ,MADISON TO YORK AVE | 2 | DESIGN START | 2009-09-29 | 2011-03-22 | 2009-08-30 | 2009-12-27
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMM008 | EAST 86TH ST STREETSCAPE-225 EAST 79TH ,MADISON TO YORK AVE | 3 | CONSTRUCTION START | 2011-03-23 | 2013-03-11 | 2009-12-28 | 2016-03-24
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMM008 | EAST 86TH ST STREETSCAPE-225 EAST 79TH ,MADISON TO YORK AVE | 4 | BID AWARD AND REGISTER CONTRCT | 2011-03-23 | 2013-03-11 | 2016-03-25 | 2016-06-22
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMM008 | EAST 86TH ST STREETSCAPE-225 EAST 79TH ,MADISON TO YORK AVE | 5 | CONSTRUCTION TO 25% | 2011-03-23 | 2013-03-11 | 2016-06-23 | 2017-02-17
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMM008 | EAST 86TH ST STREETSCAPE-225 EAST 79TH ,MADISON TO YORK AVE | 6 | CONSTRUCTION TO 50% | 2011-03-23 | 2013-03-11 | 2017-02-18 | 2017-10-15
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMM008 | EAST 86TH ST STREETSCAPE-225 EAST 79TH ,MADISON TO YORK AVE | 7 | CONSTRUCTION TO 75% | 2011-03-23 | 2013-03-11 | 2017-10-16 | 2018-06-12
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMM008 | EAST 86TH ST STREETSCAPE-225 EAST 79TH ,MADISON TO YORK AVE | 8 | ORIGINAL EQUIP & FURNISHING | 2011-03-23 | 2013-03-11 | 2018-06-13 | 2018-09-10
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMM008 | EAST 86TH ST STREETSCAPE-225 EAST 79TH ,MADISON TO YORK AVE | 9 | SUBSTANTIAL COMPLETION | 2011-03-23 | 2013-03-11 | 2018-09-11 | 2018-11-09
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMM008 | EAST 86TH ST STREETSCAPE-225 EAST 79TH ,MADISON TO YORK AVE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2011-03-23 | 2013-03-11 | 2018-11-10 | 2026-06-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMME43ST | 43rd Street Shared Street, MED-670 | 1 | DEVELOP SCOPE | 2020-03-01 | 2020-05-29 | 2020-03-01 | 2020-05-29
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMME43ST | 43rd Street Shared Street, MED-670 | 2 | PRELIMINARY DESIGN | 2020-05-30 | 2020-09-26 | 2020-05-30 | 2020-09-26
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMME43ST | 43rd Street Shared Street, MED-670 | 3 | FINAL DESIGN | 2020-09-27 | 2021-03-25 | 2020-09-27 | 2021-03-25
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMME43ST | 43rd Street Shared Street, MED-670 | 4 | BID AWARD AND REGISTER CONTRCT | 2021-03-26 | 2021-06-23 | 2021-03-26 | 2021-06-23
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMME43ST | 43rd Street Shared Street, MED-670 | 5 | CONSTRUCTION TO 25% | 2021-06-24 | 2021-10-21 | 2021-06-24 | 2021-10-21
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMME43ST | 43rd Street Shared Street, MED-670 | 6 | CONSTRUCTION TO 50% | 2021-10-22 | 2022-02-18 | 2021-10-22 | 2022-02-18
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMME43ST | 43rd Street Shared Street, MED-670 | 7 | CONSTRUCTION TO 75% | 2022-02-19 | 2022-06-18 | 2022-02-19 | 2022-06-18
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMME43ST | 43rd Street Shared Street, MED-670 | 8 | ORIGINAL EQUIP & FURNISHING | 2022-06-19 | 2022-09-16 | 2022-06-19 | 2022-09-16
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMME43ST | 43rd Street Shared Street, MED-670 | 9 | SUBSTANTIAL COMPLETION | 2022-09-17 | 2022-11-15 | 2022-09-17 | 2022-11-15
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMME43ST | 43rd Street Shared Street, MED-670 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-11-16 | 2022-12-15 | 2022-11-16 | 2022-12-15
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMNYPL | New York Public Library Pedestrian Improvements | 1 | DEVELOP SCOPE | 2017-03-01 | 2017-05-29 | 2017-03-01 | 2017-05-29
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMNYPL | New York Public Library Pedestrian Improvements | 2 | PRELIMINARY DESIGN | 2017-05-30 | 2017-09-26 | 2017-05-30 | 2017-09-26
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMNYPL | New York Public Library Pedestrian Improvements | 3 | FINAL DESIGN | 2017-09-27 | 2018-03-25 | 2017-09-27 | 2018-03-25
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMNYPL | New York Public Library Pedestrian Improvements | 4 | BID AWARD AND REGISTER CONTRCT | 2018-03-26 | 2018-06-23 | 2018-03-26 | 2018-06-23
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMNYPL | New York Public Library Pedestrian Improvements | 5 | CONSTRUCTION TO 25% | 2018-06-24 | 2018-10-21 | 2018-06-24 | 2018-10-21
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMNYPL | New York Public Library Pedestrian Improvements | 6 | CONSTRUCTION TO 50% | 2018-10-22 | 2019-02-18 | 2018-10-22 | 2019-02-18
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMNYPL | New York Public Library Pedestrian Improvements | 7 | CONSTRUCTION TO 75% | 2019-02-19 | 2019-06-18 | 2019-02-19 | 2019-06-18
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMNYPL | New York Public Library Pedestrian Improvements | 8 | ORIGINAL EQUIP & FURNISHING | 2019-06-19 | 2019-09-16 | 2019-06-19 | 2019-09-16
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMNYPL | New York Public Library Pedestrian Improvements | 9 | SUBSTANTIAL COMPLETION | 2019-09-17 | 2019-11-15 | 2019-09-17 | 2019-11-15
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMNYPL | New York Public Library Pedestrian Improvements | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-11-16 | 2019-12-15 | 2019-11-16 | 2026-02-19
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMP116 | RECON OF ASTOR PLACE AND COOPER SQUARE | 1 | DEVELOP SCOPE | 2003-05-22 | 2003-08-19 | 2003-05-22 | 2006-07-24
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMP116 | RECON OF ASTOR PLACE AND COOPER SQUARE | 2 | PRELIMINARY DESIGN | 2003-08-20 | 2003-12-17 | 2006-07-25 | 2010-11-23
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMP116 | RECON OF ASTOR PLACE AND COOPER SQUARE | 3 | FINAL DESIGN | 2003-12-18 | 2004-06-14 | 2010-11-24 | 2011-05-22
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMP116 | RECON OF ASTOR PLACE AND COOPER SQUARE | 4 | BID AWARD AND REGISTER CONTRCT | 2004-06-15 | 2004-09-12 | 2011-05-23 | 2011-08-20
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMP116 | RECON OF ASTOR PLACE AND COOPER SQUARE | 5 | CONSTRUCTION TO 25% | 2004-09-13 | 2005-01-10 | 2011-08-21 | 2011-12-18
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMP116 | RECON OF ASTOR PLACE AND COOPER SQUARE | 6 | CONSTRUCTION TO 50% | 2005-01-11 | 2005-05-10 | 2011-12-19 | 2012-04-16
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMP116 | RECON OF ASTOR PLACE AND COOPER SQUARE | 7 | CONSTRUCTION TO 75% | 2005-05-11 | 2005-09-07 | 2012-04-17 | 2012-08-14
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMP116 | RECON OF ASTOR PLACE AND COOPER SQUARE | 8 | ORIGINAL EQUIP & FURNISHING | 2005-09-08 | 2005-12-06 | 2012-08-15 | 2012-11-12
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMP116 | RECON OF ASTOR PLACE AND COOPER SQUARE | 9 | SUBSTANTIAL COMPLETION | 2005-12-07 | 2006-02-04 | 2012-11-13 | 2013-01-11
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMP116 | RECON OF ASTOR PLACE AND COOPER SQUARE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2006-02-05 | 2006-03-06 | 2013-01-12 | 2024-06-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMP2012 | TIMES SQUARE (SEN002160) | 1 | DEVELOP SCOPE | 2005-05-21 | 2005-08-18 | 2005-05-21 | 2005-08-18
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMP2012 | TIMES SQUARE (SEN002160) | 2 | PRELIMINARY DESIGN | 2005-08-19 | 2005-12-16 | 2005-08-19 | 2005-12-16
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMP2012 | TIMES SQUARE (SEN002160) | 3 | FINAL DESIGN | 2005-12-17 | 2006-06-14 | 2005-12-17 | 2006-06-14
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMP2012 | TIMES SQUARE (SEN002160) | 4 | BID AWARD AND REGISTER CONTRCT | 2007-03-01 | 2007-06-01 | 2007-03-01 | 2012-06-25
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMP2012 | TIMES SQUARE (SEN002160) | 5 | CONSTRUCTION TO 25% | 2007-06-02 | 2007-06-01 | 2012-06-26 | 2012-06-25
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMP2012 | TIMES SQUARE (SEN002160) | 6 | CONSTRUCTION TO 50% | 2007-06-02 | 2007-06-01 | 2012-06-26 | 2012-06-25
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMP2012 | TIMES SQUARE (SEN002160) | 7 | CONSTRUCTION TO 75% | 2007-06-02 | 2007-06-01 | 2012-06-26 | 2012-06-25
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMP2012 | TIMES SQUARE (SEN002160) | 8 | ORIGINAL EQUIP & FURNISHING | 2007-06-02 | 2007-06-01 | 2012-06-26 | 2012-06-25
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMP2012 | TIMES SQUARE (SEN002160) | 9 | SUBSTANTIAL COMPLETION | 2007-06-02 | 2007-06-01 | 2012-06-26 | 2012-06-25
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMP2012 | TIMES SQUARE (SEN002160) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2007-06-02 | 2007-07-01 | 2012-06-26 | 2021-12-19
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMP2019 | RECONSTRUCTION OF EAST HOUSTON STREET (MED-604) | 1 | DEVELOP SCOPE | 2008-03-01 | 2008-05-29 | 2007-07-02 | 2007-09-29
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMP2019 | RECONSTRUCTION OF EAST HOUSTON STREET (MED-604) | 2 | PRELIMINARY DESIGN | 2008-05-30 | 2008-09-26 | 2007-09-30 | 2008-01-27
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMP2019 | RECONSTRUCTION OF EAST HOUSTON STREET (MED-604) | 3 | FINAL DESIGN | 2008-09-27 | 2009-03-25 | 2008-01-28 | 2008-07-25
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMP2019 | RECONSTRUCTION OF EAST HOUSTON STREET (MED-604) | 4 | BID AWARD AND REGISTER CONTRCT | 2009-03-26 | 2009-06-23 | 2008-07-26 | 2008-10-23
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMP2019 | RECONSTRUCTION OF EAST HOUSTON STREET (MED-604) | 5 | CONSTRUCTION TO 25% | 2009-06-24 | 2009-10-21 | 2008-10-24 | 2009-02-20
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMP2019 | RECONSTRUCTION OF EAST HOUSTON STREET (MED-604) | 6 | CONSTRUCTION TO 50% | 2009-10-22 | 2010-02-18 | 2009-02-21 | 2009-06-20
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMP2019 | RECONSTRUCTION OF EAST HOUSTON STREET (MED-604) | 7 | CONSTRUCTION TO 75% | 2010-02-19 | 2010-06-18 | 2009-06-21 | 2009-10-18
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMP2019 | RECONSTRUCTION OF EAST HOUSTON STREET (MED-604) | 8 | ORIGINAL EQUIP & FURNISHING | 2010-06-19 | 2010-09-16 | 2009-10-19 | 2010-01-16
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMP2019 | RECONSTRUCTION OF EAST HOUSTON STREET (MED-604) | 9 | SUBSTANTIAL COMPLETION | 2010-09-17 | 2010-11-15 | 2010-01-17 | 2010-09-13
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMP2019 | RECONSTRUCTION OF EAST HOUSTON STREET (MED-604) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2010-11-16 | 2010-12-15 | 2010-09-14 | 2026-06-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMP2020 | Reconstruction of Gansevoort Area, Manhattan | 1 | DEVELOP SCOPE | 2009-06-30 | 2009-09-27 | 2009-06-30 | 2009-09-27
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMP2020 | Reconstruction of Gansevoort Area, Manhattan | 2 | PRELIMINARY DESIGN | 2009-09-28 | 2010-01-25 | 2009-09-28 | 2010-01-25
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMP2020 | Reconstruction of Gansevoort Area, Manhattan | 3 | FINAL DESIGN | 2010-01-26 | 2010-07-24 | 2010-01-26 | 2012-02-20
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMP2020 | Reconstruction of Gansevoort Area, Manhattan | 4 | BID AWARD AND REGISTER CONTRCT | 2010-07-25 | 2010-10-22 | 2012-02-21 | 2012-05-20
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMP2020 | Reconstruction of Gansevoort Area, Manhattan | 5 | CONSTRUCTION TO 25% | 2010-10-23 | 2011-02-19 | 2012-05-21 | 2012-12-06
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMP2020 | Reconstruction of Gansevoort Area, Manhattan | 6 | CONSTRUCTION TO 50% | 2011-02-20 | 2011-06-19 | 2012-12-07 | 2013-06-24
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMP2020 | Reconstruction of Gansevoort Area, Manhattan | 7 | CONSTRUCTION TO 75% | 2011-06-20 | 2011-10-17 | 2013-06-25 | 2015-12-28
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMP2020 | Reconstruction of Gansevoort Area, Manhattan | 8 | ORIGINAL EQUIP & FURNISHING | 2011-10-18 | 2012-01-15 | 2015-10-30 | 2016-03-27
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMP2020 | Reconstruction of Gansevoort Area, Manhattan | 9 | SUBSTANTIAL COMPLETION | 2012-01-16 | 2012-03-15 | 2016-03-28 | 2016-06-25
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMP2020 | Reconstruction of Gansevoort Area, Manhattan | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-03-16 | 2012-04-14 | 2016-06-26 | 2023-12-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCA7A | RECONSTRUCTION OF GREENWICH ST, HARRISON ST & LEONARD ST | 1 | DEVELOP SCOPE | 2007-03-02 | 2007-05-30 | 2007-03-02 | 2007-05-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCA7A | RECONSTRUCTION OF GREENWICH ST, HARRISON ST & LEONARD ST | 2 | PRELIMINARY DESIGN | 2007-05-31 | 2007-09-27 | 2007-05-31 | 2007-09-27
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCA7A | RECONSTRUCTION OF GREENWICH ST, HARRISON ST & LEONARD ST | 3 | FINAL DESIGN | 2007-09-28 | 2008-03-25 | 2007-09-28 | 2008-04-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCA7A | RECONSTRUCTION OF GREENWICH ST, HARRISON ST & LEONARD ST | 4 | BID AWARD AND REGISTER CONTRCT | 2008-03-26 | 2008-06-23 | 2008-04-02 | 2008-06-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCA7A | RECONSTRUCTION OF GREENWICH ST, HARRISON ST & LEONARD ST | 5 | CONSTRUCTION TO 25% | 2008-06-24 | 2008-10-21 | 2008-07-01 | 2009-06-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCA7A | RECONSTRUCTION OF GREENWICH ST, HARRISON ST & LEONARD ST | 6 | CONSTRUCTION TO 50% | 2008-10-22 | 2009-02-18 | 2009-07-01 | 2011-06-20
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCA7A | RECONSTRUCTION OF GREENWICH ST, HARRISON ST & LEONARD ST | 7 | CONSTRUCTION TO 75% | 2009-02-19 | 2009-06-18 | 2011-06-21 | 2015-12-18
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCA7A | RECONSTRUCTION OF GREENWICH ST, HARRISON ST & LEONARD ST | 8 | ORIGINAL EQUIP & FURNISHING | 2009-06-19 | 2009-09-16 | 2015-12-19 | 2016-03-17
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCA7A | RECONSTRUCTION OF GREENWICH ST, HARRISON ST & LEONARD ST | 9 | SUBSTANTIAL COMPLETION | 2009-09-17 | 2009-11-15 | 2016-03-18 | 2016-05-16
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCA7A | RECONSTRUCTION OF GREENWICH ST, HARRISON ST & LEONARD ST | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2009-11-16 | 2009-12-15 | 2016-05-17 | 2024-06-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCA7D | RECONSTRUCTION OF PECK SLIP - FRONT ST TO PEARL ST | 1 | DEVELOP SCOPE | 2004-01-16 | 2004-04-14 | 2004-01-16 | 2004-04-14
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCA7D | RECONSTRUCTION OF PECK SLIP - FRONT ST TO PEARL ST | 2 | PRELIMINARY DESIGN | 2004-04-15 | 2004-08-12 | 2004-04-15 | 2004-08-12
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCA7D | RECONSTRUCTION OF PECK SLIP - FRONT ST TO PEARL ST | 3 | FINAL DESIGN | 2004-08-13 | 2005-02-08 | 2004-08-13 | 2005-02-08
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCA7D | RECONSTRUCTION OF PECK SLIP - FRONT ST TO PEARL ST | 4 | BID AWARD AND REGISTER CONTRCT | 2007-03-01 | 2007-06-01 | 2007-03-01 | 2011-06-12
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCA7D | RECONSTRUCTION OF PECK SLIP - FRONT ST TO PEARL ST | 5 | CONSTRUCTION TO 25% | 2007-06-02 | 2007-06-01 | 2011-06-13 | 2011-06-12
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCA7D | RECONSTRUCTION OF PECK SLIP - FRONT ST TO PEARL ST | 6 | CONSTRUCTION TO 50% | 2007-06-02 | 2007-06-01 | 2011-06-13 | 2011-06-12
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCA7D | RECONSTRUCTION OF PECK SLIP - FRONT ST TO PEARL ST | 7 | CONSTRUCTION TO 75% | 2007-06-02 | 2007-06-01 | 2011-06-13 | 2011-06-12
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCA7D | RECONSTRUCTION OF PECK SLIP - FRONT ST TO PEARL ST | 8 | ORIGINAL EQUIP & FURNISHING | 2007-06-02 | 2007-06-01 | 2011-06-13 | 2011-06-12
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCA7D | RECONSTRUCTION OF PECK SLIP - FRONT ST TO PEARL ST | 9 | SUBSTANTIAL COMPLETION | 2007-06-02 | 2007-06-01 | 2011-06-13 | 2011-06-12
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCA7D | RECONSTRUCTION OF PECK SLIP - FRONT ST TO PEARL ST | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2007-06-02 | 2007-07-01 | 2011-06-13 | 2022-06-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCA7E | RECONSTRUCTION OF WORTH ST - HUDSON ST TO EAST BROADWAY | 1 | DEVELOP SCOPE | 2009-03-05 | 2009-06-02 | 2009-03-05 | 2009-06-02
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCA7E | RECONSTRUCTION OF WORTH ST - HUDSON ST TO EAST BROADWAY | 2 | PRELIMINARY DESIGN | 2009-06-03 | 2009-09-30 | 2009-06-03 | 2009-09-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCA7E | RECONSTRUCTION OF WORTH ST - HUDSON ST TO EAST BROADWAY | 3 | FINAL DESIGN | 2009-10-01 | 2010-03-29 | 2009-10-01 | 2014-03-29
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCA7E | RECONSTRUCTION OF WORTH ST - HUDSON ST TO EAST BROADWAY | 4 | BID AWARD AND REGISTER CONTRCT | 2010-03-30 | 2010-06-27 | 2013-03-16 | 2016-06-13
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCA7E | RECONSTRUCTION OF WORTH ST - HUDSON ST TO EAST BROADWAY | 5 | CONSTRUCTION TO 25% | 2010-06-28 | 2010-10-25 | 2016-06-14 | 2016-06-13
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCA7E | RECONSTRUCTION OF WORTH ST - HUDSON ST TO EAST BROADWAY | 6 | CONSTRUCTION TO 50% | 2010-10-26 | 2011-02-22 | 2016-06-14 | 2016-06-13
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCA7E | RECONSTRUCTION OF WORTH ST - HUDSON ST TO EAST BROADWAY | 7 | CONSTRUCTION TO 75% | 2011-02-23 | 2011-06-22 | 2016-06-14 | 2016-06-13
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCA7E | RECONSTRUCTION OF WORTH ST - HUDSON ST TO EAST BROADWAY | 8 | ORIGINAL EQUIP & FURNISHING | 2011-06-23 | 2011-09-20 | 2016-06-14 | 2016-06-13
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCA7E | RECONSTRUCTION OF WORTH ST - HUDSON ST TO EAST BROADWAY | 9 | SUBSTANTIAL COMPLETION | 2011-09-21 | 2011-11-19 | 2016-06-14 | 2017-06-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCA7E | RECONSTRUCTION OF WORTH ST - HUDSON ST TO EAST BROADWAY | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2011-11-20 | 2011-12-19 | 2017-07-01 | 2020-07-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCA7F | RECONSTRUCTION OF WARREN ST - WEST ST TO BROADWAY | 1 | DEVELOP SCOPE | 2011-12-18 | 2012-03-16 | 2011-12-18 | 2012-03-16
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCA7F | RECONSTRUCTION OF WARREN ST - WEST ST TO BROADWAY | 2 | PRELIMINARY DESIGN | 2012-03-17 | 2012-07-14 | 2012-03-17 | 2012-07-14
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCA7F | RECONSTRUCTION OF WARREN ST - WEST ST TO BROADWAY | 3 | FINAL DESIGN | 2012-07-15 | 2013-01-10 | 2012-07-15 | 2013-01-10
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCA7F | RECONSTRUCTION OF WARREN ST - WEST ST TO BROADWAY | 4 | BID AWARD AND REGISTER CONTRCT | 2013-01-11 | 2013-04-10 | 2013-01-11 | 2013-04-10
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCA7F | RECONSTRUCTION OF WARREN ST - WEST ST TO BROADWAY | 5 | CONSTRUCTION TO 25% | 2013-04-11 | 2013-08-08 | 2013-04-11 | 2013-08-08
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCA7F | RECONSTRUCTION OF WARREN ST - WEST ST TO BROADWAY | 6 | CONSTRUCTION TO 50% | 2013-08-09 | 2013-12-06 | 2013-08-09 | 2013-12-06
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCA7F | RECONSTRUCTION OF WARREN ST - WEST ST TO BROADWAY | 7 | CONSTRUCTION TO 75% | 2013-12-07 | 2014-04-05 | 2013-12-07 | 2014-04-05
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCA7F | RECONSTRUCTION OF WARREN ST - WEST ST TO BROADWAY | 8 | ORIGINAL EQUIP & FURNISHING | 2014-04-06 | 2014-07-04 | 2014-04-06 | 2014-07-04
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCA7F | RECONSTRUCTION OF WARREN ST - WEST ST TO BROADWAY | 9 | SUBSTANTIAL COMPLETION | 2014-07-05 | 2014-09-02 | 2014-07-05 | 2014-09-02
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCA7F | RECONSTRUCTION OF WARREN ST - WEST ST TO BROADWAY | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-09-03 | 2014-10-02 | 2014-09-03 | 2023-03-06
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCA8B | RECONSTRUCTION OF FULTON ST & ANCILLARY STREETSCAPE, MED-601 | 1 | DEVELOP SCOPE | 2007-05-28 | 2007-08-25 | 2007-05-28 | 2007-08-25
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCA8B | RECONSTRUCTION OF FULTON ST & ANCILLARY STREETSCAPE, MED-601 | 2 | PRELIMINARY DESIGN | 2007-08-26 | 2007-12-23 | 2007-08-26 | 2007-12-23
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCA8B | RECONSTRUCTION OF FULTON ST & ANCILLARY STREETSCAPE, MED-601 | 3 | FINAL DESIGN | 2007-12-24 | 2008-06-20 | 2007-12-24 | 2008-06-20
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCA8B | RECONSTRUCTION OF FULTON ST & ANCILLARY STREETSCAPE, MED-601 | 4 | BID AWARD AND REGISTER CONTRCT | 2008-06-21 | 2008-09-18 | 2008-06-21 | 2008-12-17
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCA8B | RECONSTRUCTION OF FULTON ST & ANCILLARY STREETSCAPE, MED-601 | 5 | CONSTRUCTION TO 25% | 2008-09-19 | 2009-01-16 | 2008-12-18 | 2009-12-17
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCA8B | RECONSTRUCTION OF FULTON ST & ANCILLARY STREETSCAPE, MED-601 | 6 | CONSTRUCTION TO 50% | 2009-01-17 | 2009-05-16 | 2009-12-18 | 2011-12-07
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCA8B | RECONSTRUCTION OF FULTON ST & ANCILLARY STREETSCAPE, MED-601 | 7 | CONSTRUCTION TO 75% | 2009-05-17 | 2009-09-13 | 2011-12-08 | 2015-12-28
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCA8B | RECONSTRUCTION OF FULTON ST & ANCILLARY STREETSCAPE, MED-601 | 8 | ORIGINAL EQUIP & FURNISHING | 2009-09-14 | 2009-12-12 | 2015-12-29 | 2016-03-27
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCA8B | RECONSTRUCTION OF FULTON ST & ANCILLARY STREETSCAPE, MED-601 | 9 | SUBSTANTIAL COMPLETION | 2009-12-13 | 2010-02-10 | 2016-03-28 | 2016-05-26
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCA8B | RECONSTRUCTION OF FULTON ST & ANCILLARY STREETSCAPE, MED-601 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2010-02-11 | 2010-03-12 | 2016-05-27 | 2024-06-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB1 | Reconstruction of Nassau St | 1 | DEVELOP SCOPE | 2017-03-01 | 2017-05-29 | 2017-03-01 | 2017-05-29
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB1 | Reconstruction of Nassau St | 2 | PRELIMINARY DESIGN | 2017-05-30 | 2017-09-26 | 2017-05-30 | 2017-09-26
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB1 | Reconstruction of Nassau St | 3 | FINAL DESIGN | 2017-09-27 | 2018-03-25 | 2017-09-27 | 2018-03-25
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB1 | Reconstruction of Nassau St | 4 | BID AWARD AND REGISTER CONTRCT | 2018-03-26 | 2018-06-23 | 2018-03-26 | 2018-06-23
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB1 | Reconstruction of Nassau St | 5 | CONSTRUCTION TO 25% | 2018-06-24 | 2018-10-21 | 2018-06-24 | 2018-10-21
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB1 | Reconstruction of Nassau St | 6 | CONSTRUCTION TO 50% | 2018-10-22 | 2019-02-18 | 2018-10-22 | 2019-02-18
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB1 | Reconstruction of Nassau St | 7 | CONSTRUCTION TO 75% | 2019-02-19 | 2019-06-18 | 2019-02-19 | 2019-06-18
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB1 | Reconstruction of Nassau St | 8 | ORIGINAL EQUIP & FURNISHING | 2019-06-19 | 2019-09-16 | 2019-06-19 | 2019-09-16
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB1 | Reconstruction of Nassau St | 9 | SUBSTANTIAL COMPLETION | 2019-09-17 | 2019-11-15 | 2019-09-17 | 2019-11-15
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB1 | Reconstruction of Nassau St | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-11-16 | 2019-12-15 | 2019-11-16 | 2023-10-07
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB2 | Reconstruction of Greenwich | 1 | DEVELOP SCOPE | 2017-03-01 | 2017-05-29 | 2017-03-01 | 2017-05-29
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB2 | Reconstruction of Greenwich | 2 | PRELIMINARY DESIGN | 2017-05-30 | 2017-09-26 | 2017-05-30 | 2017-09-26
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB2 | Reconstruction of Greenwich | 3 | FINAL DESIGN | 2017-09-27 | 2018-03-25 | 2017-09-27 | 2018-03-25
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB2 | Reconstruction of Greenwich | 4 | BID AWARD AND REGISTER CONTRCT | 2018-03-26 | 2018-06-23 | 2018-03-26 | 2018-06-23
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB2 | Reconstruction of Greenwich | 5 | CONSTRUCTION TO 25% | 2018-06-24 | 2018-10-21 | 2018-06-24 | 2018-10-21
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB2 | Reconstruction of Greenwich | 6 | CONSTRUCTION TO 50% | 2018-10-22 | 2019-02-18 | 2018-10-22 | 2019-02-18
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB2 | Reconstruction of Greenwich | 7 | CONSTRUCTION TO 75% | 2019-02-19 | 2019-06-18 | 2019-02-19 | 2019-06-18
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB2 | Reconstruction of Greenwich | 8 | ORIGINAL EQUIP & FURNISHING | 2019-06-19 | 2019-09-16 | 2019-06-19 | 2019-09-16
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB2 | Reconstruction of Greenwich | 9 | SUBSTANTIAL COMPLETION | 2019-09-17 | 2019-11-15 | 2019-09-17 | 2019-11-15
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB2 | Reconstruction of Greenwich | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-11-16 | 2019-12-15 | 2019-11-16 | 2026-09-13
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB6 | Reconstruction of Vesey St, MED-668 | 1 | DEVELOP SCOPE | 2021-06-30 | 2021-09-27 | 2021-06-30 | 2021-09-27
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB6 | Reconstruction of Vesey St, MED-668 | 2 | PRELIMINARY DESIGN | 2021-09-28 | 2022-01-25 | 2021-09-28 | 2022-01-25
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB6 | Reconstruction of Vesey St, MED-668 | 3 | FINAL DESIGN | 2022-01-26 | 2022-07-24 | 2022-01-26 | 2022-07-24
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB6 | Reconstruction of Vesey St, MED-668 | 4 | BID AWARD AND REGISTER CONTRCT | 2022-07-25 | 2022-10-22 | 2022-07-25 | 2022-10-22
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB6 | Reconstruction of Vesey St, MED-668 | 5 | CONSTRUCTION TO 25% | 2022-10-23 | 2023-02-19 | 2022-10-23 | 2023-02-19
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB6 | Reconstruction of Vesey St, MED-668 | 6 | CONSTRUCTION TO 50% | 2023-02-20 | 2023-06-19 | 2023-02-20 | 2023-06-19
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB6 | Reconstruction of Vesey St, MED-668 | 7 | CONSTRUCTION TO 75% | 2023-06-20 | 2023-10-17 | 2023-06-20 | 2023-10-17
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB6 | Reconstruction of Vesey St, MED-668 | 8 | ORIGINAL EQUIP & FURNISHING | 2023-10-18 | 2024-01-15 | 2023-10-18 | 2024-01-15
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB6 | Reconstruction of Vesey St, MED-668 | 9 | SUBSTANTIAL COMPLETION | 2024-01-16 | 2024-03-15 | 2024-01-16 | 2024-03-15
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB6 | Reconstruction of Vesey St, MED-668 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-03-16 | 2024-04-14 | 2024-03-16 | 2024-04-14
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB7 | Reconstruction of Trinity Pl | 1 | DEVELOP SCOPE | 2021-06-30 | 2021-09-27 | 2019-06-30 | 2019-09-27
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB7 | Reconstruction of Trinity Pl | 2 | PRELIMINARY DESIGN | 2021-09-28 | 2022-01-25 | 2019-09-28 | 2020-01-25
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB7 | Reconstruction of Trinity Pl | 3 | FINAL DESIGN | 2022-01-26 | 2022-07-24 | 2020-01-26 | 2020-07-23
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB7 | Reconstruction of Trinity Pl | 4 | BID AWARD AND REGISTER CONTRCT | 2022-07-25 | 2022-10-22 | 2020-07-24 | 2020-10-21
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB7 | Reconstruction of Trinity Pl | 5 | CONSTRUCTION TO 25% | 2022-10-23 | 2023-02-19 | 2020-10-22 | 2021-02-18
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB7 | Reconstruction of Trinity Pl | 6 | CONSTRUCTION TO 50% | 2023-02-20 | 2023-06-19 | 2021-02-19 | 2021-06-18
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB7 | Reconstruction of Trinity Pl | 7 | CONSTRUCTION TO 75% | 2023-06-20 | 2023-10-17 | 2021-06-19 | 2021-10-16
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB7 | Reconstruction of Trinity Pl | 8 | ORIGINAL EQUIP & FURNISHING | 2023-10-18 | 2024-01-15 | 2021-10-17 | 2022-01-14
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB7 | Reconstruction of Trinity Pl | 9 | SUBSTANTIAL COMPLETION | 2024-01-16 | 2024-03-15 | 2022-01-15 | 2022-03-15
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB7 | Reconstruction of Trinity Pl | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-03-16 | 2024-04-14 | 2022-03-16 | 2022-04-14
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB8 | Reconstruction of Broadway Phase 2 | 1 | DEVELOP SCOPE | 2019-06-30 | 2019-09-27 | 2019-06-30 | 2019-09-27
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB8 | Reconstruction of Broadway Phase 2 | 2 | PRELIMINARY DESIGN | 2019-09-28 | 2020-01-25 | 2019-09-28 | 2020-01-25
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB8 | Reconstruction of Broadway Phase 2 | 3 | FINAL DESIGN | 2020-01-26 | 2020-07-23 | 2020-01-26 | 2020-07-23
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB8 | Reconstruction of Broadway Phase 2 | 4 | BID AWARD AND REGISTER CONTRCT | 2020-07-24 | 2020-10-21 | 2020-07-24 | 2020-10-21
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB8 | Reconstruction of Broadway Phase 2 | 5 | CONSTRUCTION TO 25% | 2020-10-22 | 2021-02-18 | 2020-10-22 | 2021-02-18
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB8 | Reconstruction of Broadway Phase 2 | 6 | CONSTRUCTION TO 50% | 2021-02-19 | 2021-06-18 | 2021-02-19 | 2021-06-18
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB8 | Reconstruction of Broadway Phase 2 | 7 | CONSTRUCTION TO 75% | 2021-06-19 | 2021-10-16 | 2021-06-19 | 2021-10-16
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB8 | Reconstruction of Broadway Phase 2 | 8 | ORIGINAL EQUIP & FURNISHING | 2021-10-17 | 2022-01-14 | 2021-10-17 | 2022-01-14
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB8 | Reconstruction of Broadway Phase 2 | 9 | SUBSTANTIAL COMPLETION | 2022-01-15 | 2022-03-15 | 2022-01-15 | 2022-03-15
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB8 | Reconstruction of Broadway Phase 2 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-16 | 2022-04-14 | 2022-03-16 | 2029-07-15
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ003M | Montefiore Park and Plaza Reconstruction/Improvement | 1 | DEVELOP SCOPE | 2011-07-01 | 2011-09-28 | 2011-07-01 | 2011-09-28
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ003M | Montefiore Park and Plaza Reconstruction/Improvement | 2 | PRELIMINARY DESIGN | 2011-09-29 | 2012-01-26 | 2011-09-29 | 2012-01-26
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ003M | Montefiore Park and Plaza Reconstruction/Improvement | 3 | FINAL DESIGN | 2012-01-27 | 2012-07-24 | 2012-01-27 | 2016-03-27
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ003M | Montefiore Park and Plaza Reconstruction/Improvement | 4 | BID AWARD AND REGISTER CONTRCT | 2012-07-25 | 2012-10-22 | 2016-03-28 | 2016-06-25
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ003M | Montefiore Park and Plaza Reconstruction/Improvement | 5 | CONSTRUCTION TO 25% | 2012-10-23 | 2013-02-19 | 2016-06-26 | 2016-11-22
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ003M | Montefiore Park and Plaza Reconstruction/Improvement | 6 | CONSTRUCTION TO 50% | 2013-02-20 | 2013-06-19 | 2016-11-23 | 2017-04-21
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ003M | Montefiore Park and Plaza Reconstruction/Improvement | 7 | CONSTRUCTION TO 75% | 2013-06-20 | 2013-10-17 | 2017-04-22 | 2017-09-18
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ003M | Montefiore Park and Plaza Reconstruction/Improvement | 8 | ORIGINAL EQUIP & FURNISHING | 2013-10-18 | 2014-01-15 | 2017-09-19 | 2017-12-17
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ003M | Montefiore Park and Plaza Reconstruction/Improvement | 9 | SUBSTANTIAL COMPLETION | 2014-01-16 | 2014-03-16 | 2017-12-18 | 2018-02-15
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ003M | Montefiore Park and Plaza Reconstruction/Improvement | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-03-17 | 2014-04-15 | 2018-02-16 | 2023-04-23
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ012M | Bogardus Plaza Clock Tower | 1 | DEVELOP SCOPE | 2013-06-30 | 2013-09-27 | 2013-06-30 | 2013-09-27
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ012M | Bogardus Plaza Clock Tower | 2 | PRELIMINARY DESIGN | 2013-09-28 | 2014-01-25 | 2013-09-28 | 2014-01-25
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ012M | Bogardus Plaza Clock Tower | 3 | FINAL DESIGN | 2014-01-26 | 2014-07-24 | 2014-01-26 | 2014-07-24
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ012M | Bogardus Plaza Clock Tower | 4 | BID AWARD AND REGISTER CONTRCT | 2014-07-25 | 2014-10-22 | 2014-07-25 | 2014-10-22
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ012M | Bogardus Plaza Clock Tower | 5 | CONSTRUCTION TO 25% | 2014-10-23 | 2015-02-19 | 2014-10-23 | 2015-02-19
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ012M | Bogardus Plaza Clock Tower | 6 | CONSTRUCTION TO 50% | 2015-02-20 | 2015-06-19 | 2015-02-20 | 2015-06-19
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ012M | Bogardus Plaza Clock Tower | 7 | CONSTRUCTION TO 75% | 2015-06-20 | 2015-10-17 | 2015-06-20 | 2015-10-17
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ012M | Bogardus Plaza Clock Tower | 8 | ORIGINAL EQUIP & FURNISHING | 2015-10-18 | 2016-01-15 | 2015-10-18 | 2016-01-15
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ012M | Bogardus Plaza Clock Tower | 9 | SUBSTANTIAL COMPLETION | 2016-01-16 | 2016-03-15 | 2016-01-16 | 2016-03-15
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ012M | Bogardus Plaza Clock Tower | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-16 | 2016-04-14 | 2016-03-16 | 2023-08-21
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ015M | Pershing Square East Plaza/Streetscape Reconstruction | 1 | DEVELOP SCOPE | 2018-06-30 | 2018-09-27 | 2018-06-30 | 2018-09-27
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ015M | Pershing Square East Plaza/Streetscape Reconstruction | 2 | PRELIMINARY DESIGN | 2018-09-28 | 2019-01-25 | 2018-09-28 | 2019-01-25
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ015M | Pershing Square East Plaza/Streetscape Reconstruction | 3 | FINAL DESIGN | 2019-01-26 | 2019-07-24 | 2019-01-26 | 2019-07-24
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ015M | Pershing Square East Plaza/Streetscape Reconstruction | 4 | BID AWARD AND REGISTER CONTRCT | 2019-07-25 | 2019-10-22 | 2019-07-25 | 2019-10-22
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ015M | Pershing Square East Plaza/Streetscape Reconstruction | 5 | CONSTRUCTION TO 25% | 2019-10-23 | 2020-02-19 | 2019-10-23 | 2020-02-19
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ015M | Pershing Square East Plaza/Streetscape Reconstruction | 6 | CONSTRUCTION TO 50% | 2020-02-20 | 2020-06-18 | 2020-02-20 | 2020-06-18
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ015M | Pershing Square East Plaza/Streetscape Reconstruction | 7 | CONSTRUCTION TO 75% | 2020-06-19 | 2020-10-16 | 2020-06-19 | 2020-10-16
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ015M | Pershing Square East Plaza/Streetscape Reconstruction | 8 | ORIGINAL EQUIP & FURNISHING | 2020-10-17 | 2021-01-14 | 2020-10-17 | 2021-01-14
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ015M | Pershing Square East Plaza/Streetscape Reconstruction | 9 | SUBSTANTIAL COMPLETION | 2021-01-15 | 2021-03-15 | 2021-01-15 | 2021-03-15
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ015M | Pershing Square East Plaza/Streetscape Reconstruction | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-16 | 2021-04-14 | 2021-03-16 | 2023-04-04
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR16M | Rehabilitation of Pedestrian Ramps - Manhattan | 5 | CONSTRUCTION TO 25% | 2018-06-24 | 2018-10-21 | 2018-06-24 | 2018-10-21
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR16M | Rehabilitation of Pedestrian Ramps - Manhattan | 6 | CONSTRUCTION TO 50% | 2018-10-22 | 2019-02-18 | 2018-10-22 | 2019-02-18
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR16M | Rehabilitation of Pedestrian Ramps - Manhattan | 7 | CONSTRUCTION TO 75% | 2019-02-19 | 2019-06-18 | 2019-02-19 | 2019-06-18
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR16M | Rehabilitation of Pedestrian Ramps - Manhattan | 8 | ORIGINAL EQUIP & FURNISHING | 2019-06-19 | 2019-09-16 | 2019-06-19 | 2019-09-16
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR16M | Rehabilitation of Pedestrian Ramps - Manhattan | 9 | SUBSTANTIAL COMPLETION | 2019-09-17 | 2019-11-15 | 2019-09-17 | 2019-11-15
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR16M | Rehabilitation of Pedestrian Ramps - Manhattan | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-11-16 | 2019-12-15 | 2019-11-16 | 2019-12-15
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19M | Pedestrian Ramp Rehabilitation - Manhattan | 1 | DEVELOP SCOPE | 2017-06-30 | 2017-09-27 | 2017-06-30 | 2017-09-27
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19M | Pedestrian Ramp Rehabilitation - Manhattan | 2 | PRELIMINARY DESIGN | 2017-09-28 | 2018-01-25 | 2017-09-28 | 2018-01-25
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19M | Pedestrian Ramp Rehabilitation - Manhattan | 3 | FINAL DESIGN | 2018-01-26 | 2018-07-24 | 2018-01-26 | 2018-07-24
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19M | Pedestrian Ramp Rehabilitation - Manhattan | 4 | BID AWARD AND REGISTER CONTRCT | 2018-07-25 | 2018-10-22 | 2018-07-25 | 2018-10-22
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19M | Pedestrian Ramp Rehabilitation - Manhattan | 5 | CONSTRUCTION TO 25% | 2018-10-23 | 2019-02-19 | 2018-10-23 | 2019-02-19
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19M | Pedestrian Ramp Rehabilitation - Manhattan | 6 | CONSTRUCTION TO 50% | 2019-02-20 | 2019-06-19 | 2019-02-20 | 2019-06-19
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19M | Pedestrian Ramp Rehabilitation - Manhattan | 7 | CONSTRUCTION TO 75% | 2019-06-20 | 2019-10-17 | 2019-06-20 | 2019-10-17
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19M | Pedestrian Ramp Rehabilitation - Manhattan | 8 | ORIGINAL EQUIP & FURNISHING | 2019-10-18 | 2020-01-15 | 2019-10-18 | 2020-01-15
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19M | Pedestrian Ramp Rehabilitation - Manhattan | 9 | SUBSTANTIAL COMPLETION | 2020-01-16 | 2020-03-15 | 2020-01-16 | 2020-03-15
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19M | Pedestrian Ramp Rehabilitation - Manhattan | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-03-16 | 2020-04-14 | 2020-03-16 | 2024-08-12
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19MC1 | Complex Upgrades Ped Ramps - Manhattan | 1 | DEVELOP SCOPE | 2019-06-30 | 2019-09-27 | 2019-06-30 | 2019-09-27
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19MC1 | Complex Upgrades Ped Ramps - Manhattan | 2 | PRELIMINARY DESIGN | 2019-09-28 | 2020-01-25 | 2019-09-28 | 2020-01-25
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19MC1 | Complex Upgrades Ped Ramps - Manhattan | 3 | FINAL DESIGN | 2020-01-26 | 2020-07-23 | 2020-01-26 | 2020-07-23
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19MC1 | Complex Upgrades Ped Ramps - Manhattan | 4 | BID AWARD AND REGISTER CONTRCT | 2020-07-24 | 2020-10-21 | 2020-07-24 | 2020-10-21
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19MC1 | Complex Upgrades Ped Ramps - Manhattan | 5 | CONSTRUCTION TO 25% | 2020-10-22 | 2021-02-18 | 2020-10-22 | 2021-02-18
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19MC1 | Complex Upgrades Ped Ramps - Manhattan | 6 | CONSTRUCTION TO 50% | 2021-02-19 | 2021-06-18 | 2021-02-19 | 2021-06-18
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19MC1 | Complex Upgrades Ped Ramps - Manhattan | 7 | CONSTRUCTION TO 75% | 2021-06-19 | 2021-10-16 | 2021-06-19 | 2021-10-16
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19MC1 | Complex Upgrades Ped Ramps - Manhattan | 8 | ORIGINAL EQUIP & FURNISHING | 2021-10-17 | 2022-01-14 | 2021-10-17 | 2022-01-14
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19MC1 | Complex Upgrades Ped Ramps - Manhattan | 9 | SUBSTANTIAL COMPLETION | 2022-01-15 | 2022-03-15 | 2022-01-15 | 2022-03-15
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19MC1 | Complex Upgrades Ped Ramps - Manhattan | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-16 | 2022-04-14 | 2022-03-16 | 2022-04-14
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19MC2 | Complex Upgrades Ped Ramps - Manhattan | 1 | DEVELOP SCOPE | 2019-06-30 | 2019-09-27 | 2019-06-30 | 2019-09-27
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19MC2 | Complex Upgrades Ped Ramps - Manhattan | 2 | PRELIMINARY DESIGN | 2019-09-28 | 2020-01-25 | 2019-09-28 | 2020-01-25
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19MC2 | Complex Upgrades Ped Ramps - Manhattan | 3 | FINAL DESIGN | 2020-01-26 | 2020-07-23 | 2020-01-26 | 2020-07-23
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19MC2 | Complex Upgrades Ped Ramps - Manhattan | 4 | BID AWARD AND REGISTER CONTRCT | 2020-07-24 | 2020-10-21 | 2020-07-24 | 2020-10-21
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19MC2 | Complex Upgrades Ped Ramps - Manhattan | 5 | CONSTRUCTION TO 25% | 2020-10-22 | 2021-02-18 | 2020-10-22 | 2021-02-18
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19MC2 | Complex Upgrades Ped Ramps - Manhattan | 6 | CONSTRUCTION TO 50% | 2021-02-19 | 2021-06-18 | 2021-02-19 | 2021-06-18
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19MC2 | Complex Upgrades Ped Ramps - Manhattan | 7 | CONSTRUCTION TO 75% | 2021-06-19 | 2021-10-16 | 2021-06-19 | 2021-10-16
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19MC2 | Complex Upgrades Ped Ramps - Manhattan | 8 | ORIGINAL EQUIP & FURNISHING | 2021-10-17 | 2022-01-14 | 2021-10-17 | 2022-01-14
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19MC2 | Complex Upgrades Ped Ramps - Manhattan | 9 | SUBSTANTIAL COMPLETION | 2022-01-15 | 2022-03-15 | 2022-01-15 | 2022-03-15
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19MC2 | Complex Upgrades Ped Ramps - Manhattan | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-16 | 2022-04-14 | 2022-03-16 | 2022-04-14
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MCL | Non-Standard Upgrades Ped Ramp - Manhattan Landmark | 1 | DEVELOP SCOPE | 2019-06-30 | 2019-09-27 | 2019-06-30 | 2019-09-27
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MCL | Non-Standard Upgrades Ped Ramp - Manhattan Landmark | 2 | PRELIMINARY DESIGN | 2019-09-28 | 2020-01-25 | 2019-09-28 | 2020-01-25
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MCL | Non-Standard Upgrades Ped Ramp - Manhattan Landmark | 3 | FINAL DESIGN | 2020-01-26 | 2020-07-23 | 2020-01-26 | 2020-07-23
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MCL | Non-Standard Upgrades Ped Ramp - Manhattan Landmark | 4 | BID AWARD AND REGISTER CONTRCT | 2020-07-24 | 2020-10-21 | 2020-07-24 | 2020-10-21
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MCL | Non-Standard Upgrades Ped Ramp - Manhattan Landmark | 5 | CONSTRUCTION TO 25% | 2020-10-22 | 2021-02-18 | 2020-10-22 | 2021-02-18
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MCL | Non-Standard Upgrades Ped Ramp - Manhattan Landmark | 6 | CONSTRUCTION TO 50% | 2021-02-19 | 2021-06-18 | 2021-02-19 | 2021-06-18
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MCL | Non-Standard Upgrades Ped Ramp - Manhattan Landmark | 7 | CONSTRUCTION TO 75% | 2021-06-19 | 2021-10-16 | 2021-06-19 | 2021-10-16
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MCL | Non-Standard Upgrades Ped Ramp - Manhattan Landmark | 8 | ORIGINAL EQUIP & FURNISHING | 2021-10-17 | 2022-01-14 | 2021-10-17 | 2022-01-14
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MCL | Non-Standard Upgrades Ped Ramp - Manhattan Landmark | 9 | SUBSTANTIAL COMPLETION | 2022-01-15 | 2022-03-15 | 2022-01-15 | 2022-03-15
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MCL | Non-Standard Upgrades Ped Ramp - Manhattan Landmark | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-16 | 2022-04-14 | 2022-03-16 | 2022-04-14
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2008M | PRIOR NOTICE SIDEWALKS - MANHATTAN(SIM) | 2 | PRELIMINARY DESIGN | 2007-05-02 | 2007-08-29 | 2008-09-16 | 2009-01-13
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2008M | PRIOR NOTICE SIDEWALKS - MANHATTAN(SIM) | 3 | FINAL DESIGN | 2007-08-30 | 2008-02-25 | 2009-01-14 | 2009-07-12
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2008M | PRIOR NOTICE SIDEWALKS - MANHATTAN(SIM) | 4 | BID AWARD AND REGISTER CONTRCT | 2008-02-26 | 2008-06-01 | 2009-07-13 | 2009-10-17
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2008M | PRIOR NOTICE SIDEWALKS - MANHATTAN(SIM) | 5 | CONSTRUCTION TO 25% | 2008-06-02 | 2008-06-01 | 2009-10-18 | 2009-10-17
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2008M | PRIOR NOTICE SIDEWALKS - MANHATTAN(SIM) | 6 | CONSTRUCTION TO 50% | 2008-06-02 | 2008-06-01 | 2009-10-18 | 2009-10-17
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2008M | PRIOR NOTICE SIDEWALKS - MANHATTAN(SIM) | 7 | CONSTRUCTION TO 75% | 2008-06-02 | 2008-06-01 | 2009-10-18 | 2009-10-17
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2008M | PRIOR NOTICE SIDEWALKS - MANHATTAN(SIM) | 8 | ORIGINAL EQUIP & FURNISHING | 2008-06-02 | 2008-06-01 | 2009-10-18 | 2009-10-17
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2008M | PRIOR NOTICE SIDEWALKS - MANHATTAN(SIM) | 9 | SUBSTANTIAL COMPLETION | 2008-06-02 | 2008-06-01 | 2009-10-18 | 2009-10-17
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2008M | PRIOR NOTICE SIDEWALKS - MANHATTAN(SIM) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-06-02 | 2008-07-01 | 2011-10-18 | 2011-11-16
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2011M | PRIOR NOTICE SIDEWALKS - MANHATTAN (SIM) | 1 | DEVELOP SCOPE | 2009-12-11 | 2010-03-10 | 2009-12-11 | 2010-03-10
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2011M | PRIOR NOTICE SIDEWALKS - MANHATTAN (SIM) | 2 | PRELIMINARY DESIGN | 2010-03-11 | 2010-07-08 | 2010-03-11 | 2010-07-08
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2011M | PRIOR NOTICE SIDEWALKS - MANHATTAN (SIM) | 3 | FINAL DESIGN | 2010-07-09 | 2011-01-04 | 2010-07-09 | 2011-01-04
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2011M | PRIOR NOTICE SIDEWALKS - MANHATTAN (SIM) | 4 | BID AWARD AND REGISTER CONTRCT | 2011-01-05 | 2011-04-04 | 2011-01-05 | 2011-04-04
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2011M | PRIOR NOTICE SIDEWALKS - MANHATTAN (SIM) | 5 | CONSTRUCTION TO 25% | 2011-04-05 | 2011-08-02 | 2011-04-05 | 2011-08-02
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2011M | PRIOR NOTICE SIDEWALKS - MANHATTAN (SIM) | 6 | CONSTRUCTION TO 50% | 2011-08-03 | 2011-11-30 | 2011-08-03 | 2011-11-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2011M | PRIOR NOTICE SIDEWALKS - MANHATTAN (SIM) | 7 | CONSTRUCTION TO 75% | 2011-12-01 | 2012-03-29 | 2011-12-01 | 2012-03-29
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2011M | PRIOR NOTICE SIDEWALKS - MANHATTAN (SIM) | 8 | ORIGINAL EQUIP & FURNISHING | 2012-03-30 | 2012-06-27 | 2012-03-30 | 2012-06-27
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2011M | PRIOR NOTICE SIDEWALKS - MANHATTAN (SIM) | 9 | SUBSTANTIAL COMPLETION | 2012-06-28 | 2012-08-26 | 2012-06-28 | 2012-08-26
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2011M | PRIOR NOTICE SIDEWALKS - MANHATTAN (SIM) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-08-27 | 2012-09-25 | 2012-08-27 | 2012-09-25
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2018M | Prior Notice Sidewalks - Manhattan | 1 | DEVELOP SCOPE | 2017-03-01 | 2017-05-29 | 2017-03-01 | 2017-05-29
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2018M | Prior Notice Sidewalks - Manhattan | 2 | PRELIMINARY DESIGN | 2017-05-30 | 2017-09-26 | 2017-05-30 | 2017-09-26
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2018M | Prior Notice Sidewalks - Manhattan | 3 | FINAL DESIGN | 2017-09-27 | 2018-03-25 | 2017-09-27 | 2018-03-25
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2018M | Prior Notice Sidewalks - Manhattan | 4 | BID AWARD AND REGISTER CONTRCT | 2018-03-26 | 2018-06-23 | 2018-03-26 | 2018-06-23
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2018M | Prior Notice Sidewalks - Manhattan | 5 | CONSTRUCTION TO 25% | 2018-06-24 | 2018-10-21 | 2018-06-24 | 2018-10-21
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2018M | Prior Notice Sidewalks - Manhattan | 6 | CONSTRUCTION TO 50% | 2018-10-22 | 2019-02-18 | 2018-10-22 | 2019-02-18
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2018M | Prior Notice Sidewalks - Manhattan | 7 | CONSTRUCTION TO 75% | 2019-02-19 | 2019-06-18 | 2019-02-19 | 2019-06-18
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2018M | Prior Notice Sidewalks - Manhattan | 8 | ORIGINAL EQUIP & FURNISHING | 2019-06-19 | 2019-09-16 | 2019-06-19 | 2019-09-16
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2018M | Prior Notice Sidewalks - Manhattan | 9 | SUBSTANTIAL COMPLETION | 2019-09-17 | 2019-11-15 | 2019-09-17 | 2019-11-15
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2018M | Prior Notice Sidewalks - Manhattan | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-11-16 | 2019-12-15 | 2019-11-16 | 2019-12-15
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA0996S | 96TH STREET - Exterior Rehabilitation | 1 | PROJECT START | 2009-03-09 | 2009-03-09 | 2009-03-09 | 2009-03-09
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA0996S | 96TH STREET - Exterior Rehabilitation | 2 | DESIGN START | 2009-03-10 | 2010-09-02 | 2009-03-10 | 2010-09-02
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA0996S | 96TH STREET - Exterior Rehabilitation | 3 | DESIGN COMPLETION | 2010-09-03 | 2011-09-03 | 2010-09-03 | 2011-09-03
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA0996S | 96TH STREET - Exterior Rehabilitation | 4 | CONSTRUCTION START | 2011-09-04 | 2011-09-03 | 2011-09-04 | 2011-12-02
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA0996S | 96TH STREET - Exterior Rehabilitation | 5 | CONSTRUCTION COMPLETION | 2011-09-04 | 2012-09-04 | 2016-06-04 | 2022-09-04
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA09KIP | KIPS BAY - Exterior Rehabilitation | 1 | PROJECT START | 2009-06-22 | 2009-06-22 | 2009-04-23 | 2010-04-23
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA09KIP | KIPS BAY - Exterior Rehabilitation | 2 | DESIGN START | 2009-06-23 | 2009-11-20 | 2010-04-14 | 2012-04-14
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA09KIP | KIPS BAY - Exterior Rehabilitation | 3 | DESIGN COMPLETION | 2009-11-21 | 2010-06-20 | 2011-12-21 | 2014-12-21
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA09KIP | KIPS BAY - Exterior Rehabilitation | 4 | CONSTRUCTION START | 2010-06-21 | 2010-08-20 | 2015-03-26 | 2018-04-26
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA09KIP | KIPS BAY - Exterior Rehabilitation | 5 | CONSTRUCTION COMPLETION | 2010-08-21 | 2013-08-21 | 2016-12-10 | 2026-12-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA10115 | 115TH STREET - Removal and Replacement of Floors | 1 | DESIGN | 2010-10-01 | 2011-03-29 | 2008-07-03 | 2013-08-22
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA10115 | 115TH STREET - Removal and Replacement of Floors | 2 | BID AWARD AND REGISTER CONTRCT | 2011-03-30 | 2011-06-27 | 2013-08-23 | 2018-08-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA10115 | 115TH STREET - Removal and Replacement of Floors | 3 | CONSTRUCTION | 2011-06-28 | 2012-06-26 | 2018-08-31 | 2019-08-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA10115 | 115TH STREET - Removal and Replacement of Floors | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-06-27 | 2014-12-23 | 2019-08-31 | 2022-02-25
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA10115 | 115TH STREET - Removal and Replacement of Floors | 5 | PROJECT START | 2014-12-24 | 2014-12-24 | 2022-02-26 | 2023-05-23
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA10115 | 115TH STREET - Removal and Replacement of Floors | 6 | DESIGN START | 2014-12-25 | 2014-12-25 | 2011-07-01 | 2013-08-22
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA10115 | 115TH STREET - Removal and Replacement of Floors | 7 | DESIGN COMPLETION | 2014-12-26 | 2014-12-26 | 2017-05-15 | 2018-06-26
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA10115 | 115TH STREET - Removal and Replacement of Floors | 8 | CONSTRUCTION START | 2014-12-27 | 2014-12-27 | 2018-06-27 | 2018-08-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA10115 | 115TH STREET - Removal and Replacement of Floors | 9 | CONSTRUCTION COMPLETION | 2014-12-28 | 2014-12-28 | 2018-08-31 | 2019-08-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA10AGL | AGUILAR - Facade Restoration | 1 | PROJECT START | 2010-05-22 | 2010-05-22 | 2010-05-22 | 2010-05-22
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA10AGL | AGUILAR - Facade Restoration | 2 | DESIGN START | 2010-05-23 | 2010-11-23 | 2010-05-23 | 2011-12-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA10AGL | AGUILAR - Facade Restoration | 3 | DESIGN COMPLETION | 2010-11-24 | 2011-05-23 | 2011-12-02 | 2014-06-29
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA10AGL | AGUILAR - Facade Restoration | 4 | CONSTRUCTION START | 2011-05-24 | 2011-06-22 | 2014-06-30 | 2019-06-28
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA10AGL | AGUILAR - Facade Restoration | 5 | CONSTRUCTION COMPLETION | 2011-06-23 | 2012-08-22 | 2019-06-29 | 2023-09-21
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA10JMB | JEFFERSON MARKET - ADA Accessibility | 1 | PROJECT START | 2009-08-08 | 2010-02-02 | 2009-08-08 | 2009-11-03
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA10JMB | JEFFERSON MARKET - ADA Accessibility | 2 | DESIGN START | 2010-02-03 | 2010-05-02 | 2009-11-04 | 2010-07-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA10JMB | JEFFERSON MARKET - ADA Accessibility | 3 | DESIGN COMPLETION | 2010-05-03 | 2011-05-02 | 2010-07-02 | 2017-12-05
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA10JMB | JEFFERSON MARKET - ADA Accessibility | 4 | CONSTRUCTION START | 2011-05-03 | 2011-07-07 | 2017-12-06 | 2018-02-09
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA10JMB | JEFFERSON MARKET - ADA Accessibility | 5 | CONSTRUCTION COMPLETION | 2011-07-08 | 2012-07-07 | 2018-02-10 | 2023-02-11
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA10RIS | ROOSEVELT ISLAND - NEW BRANCH LIBRARY | 1 | PROJECT START | 2013-07-15 | 2013-07-15 | 2013-07-15 | 2013-07-15
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA10RIS | ROOSEVELT ISLAND - NEW BRANCH LIBRARY | 2 | DESIGN START | 2015-05-15 | 2015-05-15 | 2015-05-15 | 2015-05-15
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA10RIS | ROOSEVELT ISLAND - NEW BRANCH LIBRARY | 3 | DESIGN COMPLETION | 2017-07-04 | 2017-07-04 | 2017-07-04 | 2017-07-04
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA10RIS | ROOSEVELT ISLAND - NEW BRANCH LIBRARY | 4 | CONSTRUCTION START | 2018-02-01 | 2018-02-01 | 2018-02-01 | 2018-02-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA10RIS | ROOSEVELT ISLAND - NEW BRANCH LIBRARY | 5 | CONSTRUCTION COMPLETION | 2020-03-06 | 2020-03-06 | 2020-03-06 | 2023-06-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA1167S | 67TH STREET - Partial Interior Renovation | 1 | DESIGN | 2010-10-01 | 2011-03-29 | 2013-06-30 | 2014-07-29
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA1167S | 67TH STREET - Partial Interior Renovation | 2 | BID AWARD AND REGISTER CONTRCT | 2011-03-30 | 2011-06-27 | 2016-07-30 | 2019-08-31
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA1167S | 67TH STREET - Partial Interior Renovation | 3 | CONSTRUCTION | 2011-06-28 | 2012-06-26 | 2019-09-01 | 2020-08-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA1167S | 67TH STREET - Partial Interior Renovation | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-06-27 | 2012-12-23 | 2020-08-31 | 2024-03-22
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA1167S | 67TH STREET - Partial Interior Renovation | 5 | PROJECT START | 2012-06-27 | 2012-12-23 | 2024-03-23 | 2024-03-23
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA1167S | 67TH STREET - Partial Interior Renovation | 6 | DESIGN START | 2012-06-27 | 2012-12-23 | 2024-03-24 | 2024-03-24
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA1167S | 67TH STREET - Partial Interior Renovation | 7 | DESIGN COMPLETION | 2012-06-27 | 2012-12-23 | 2024-03-25 | 2024-03-25
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA1167S | 67TH STREET - Partial Interior Renovation | 8 | CONSTRUCTION START | 2012-06-27 | 2012-12-23 | 2024-03-26 | 2024-03-26
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA1167S | 67TH STREET - Partial Interior Renovation | 9 | CONSTRUCTION COMPLETION | 2012-06-27 | 2012-12-23 | 2024-03-27 | 2024-03-27
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA11BLD | BLOOMINGDALE - Interior Renovation | 1 | DESIGN | 2010-10-01 | 2011-03-29 | 2010-10-10 | 2010-10-10
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA11BLD | BLOOMINGDALE - Interior Renovation | 2 | BID AWARD AND REGISTER CONTRCT | 2011-03-30 | 2011-06-27 | 2010-10-11 | 2010-10-11
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA11BLD | BLOOMINGDALE - Interior Renovation | 3 | CONSTRUCTION | 2011-06-28 | 2012-06-26 | 2010-10-12 | 2010-10-12
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA11BLD | BLOOMINGDALE - Interior Renovation | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-06-27 | 2012-12-23 | 2010-10-13 | 2010-10-13
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA11BLD | BLOOMINGDALE - Interior Renovation | 5 | CONSTRUCTION COMPLETION | 2012-06-27 | 2012-12-23 | 2016-06-30 | 2022-12-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA12EPH | EPIPHANY - FACADE RESTORATION | 1 | DEVELOP SCOPE | 2012-09-30 | 2012-12-28 | 2012-09-30 | 2014-12-28
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA12EPH | EPIPHANY - FACADE RESTORATION | 2 | PRELIMINARY DESIGN | 2012-12-29 | 2013-04-27 | 2014-12-29 | 2016-09-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA12EPH | EPIPHANY - FACADE RESTORATION | 3 | FINAL DESIGN | 2013-04-28 | 2013-10-24 | 2016-10-01 | 2018-06-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA12EPH | EPIPHANY - FACADE RESTORATION | 4 | BID AWARD AND REGISTER CONTRCT | 2013-10-25 | 2014-01-22 | 2018-07-01 | 2020-07-15
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA12EPH | EPIPHANY - FACADE RESTORATION | 5 | CONSTRUCTION TO 25% | 2014-01-23 | 2014-05-22 | 2020-07-16 | 2020-11-12
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA12EPH | EPIPHANY - FACADE RESTORATION | 6 | CONSTRUCTION TO 50% | 2014-05-23 | 2014-09-19 | 2020-11-13 | 2021-03-12
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA12EPH | EPIPHANY - FACADE RESTORATION | 7 | CONSTRUCTION TO 75% | 2014-09-20 | 2015-01-17 | 2021-03-13 | 2021-07-10
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA12EPH | EPIPHANY - FACADE RESTORATION | 8 | ORIGINAL EQUIP & FURNISHING | 2015-01-18 | 2015-04-17 | 2021-07-11 | 2021-10-08
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA12EPH | EPIPHANY - FACADE RESTORATION | 9 | SUBSTANTIAL COMPLETION | 2015-04-18 | 2015-06-16 | 2021-10-09 | 2022-12-07
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA12EPH | EPIPHANY - FACADE RESTORATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-06-17 | 2015-07-16 | 2016-06-30 | 2023-12-29
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA12SWP | SEWARD PARK - Replace sidealk over vault and waterproof | 1 | DEVELOP SCOPE | 2012-09-30 | 2012-12-28 | 2012-09-30 | 2012-12-28
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA12SWP | SEWARD PARK - Replace sidealk over vault and waterproof | 2 | PRELIMINARY DESIGN | 2012-12-29 | 2013-04-27 | 2012-12-29 | 2013-04-27
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA12SWP | SEWARD PARK - Replace sidealk over vault and waterproof | 3 | FINAL DESIGN | 2013-04-28 | 2013-10-24 | 2013-04-28 | 2013-10-24
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA12SWP | SEWARD PARK - Replace sidealk over vault and waterproof | 4 | BID AWARD AND REGISTER CONTRCT | 2013-10-25 | 2014-01-22 | 2013-10-25 | 2014-01-22
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA12SWP | SEWARD PARK - Replace sidealk over vault and waterproof | 5 | CONSTRUCTION TO 25% | 2014-01-23 | 2014-05-22 | 2014-01-23 | 2014-05-22
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA12SWP | SEWARD PARK - Replace sidealk over vault and waterproof | 6 | CONSTRUCTION TO 50% | 2014-05-23 | 2014-09-19 | 2014-05-23 | 2014-09-19
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA12SWP | SEWARD PARK - Replace sidealk over vault and waterproof | 7 | CONSTRUCTION TO 75% | 2014-09-20 | 2015-01-17 | 2014-09-20 | 2015-01-17
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA12SWP | SEWARD PARK - Replace sidealk over vault and waterproof | 8 | ORIGINAL EQUIP & FURNISHING | 2015-01-18 | 2015-04-17 | 2015-01-18 | 2015-04-17
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA12SWP | SEWARD PARK - Replace sidealk over vault and waterproof | 9 | SUBSTANTIAL COMPLETION | 2015-04-18 | 2015-06-16 | 2015-04-18 | 2015-06-16
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA12SWP | SEWARD PARK - Replace sidealk over vault and waterproof | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-06-17 | 2015-07-16 | 2016-06-17 | 2022-07-16
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13CCL | COUNTEE CULLEN: Boiler | 1 | PROJECT START | 2013-04-01 | 2014-11-13 | 2013-04-01 | 2013-04-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13CCL | COUNTEE CULLEN: Boiler | 2 | DESIGN START | 2014-11-14 | 2015-08-15 | 2013-04-02 | 2014-12-23
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13CCL | COUNTEE CULLEN: Boiler | 3 | DESIGN COMPLETION | 2015-08-16 | 2016-01-14 | 2014-12-24 | 2016-07-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13CCL | COUNTEE CULLEN: Boiler | 4 | CONSTRUCTION START | 2016-01-15 | 2016-09-07 | 2016-07-02 | 2017-06-13
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13CCL | COUNTEE CULLEN: Boiler | 5 | CONSTRUCTION COMPLETION | 2016-09-08 | 2016-09-08 | 2017-06-14 | 2022-06-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13GBR | GEORGE BRUCE: Partial Interior/Exterior,/ Roof / Boiler | 1 | PROJECT START | 2014-03-28 | 2014-03-28 | 2014-03-28 | 2014-03-28
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13GBR | GEORGE BRUCE: Partial Interior/Exterior,/ Roof / Boiler | 2 | DESIGN START | 2014-03-29 | 2014-03-29 | 2014-03-29 | 2014-03-29
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13GBR | GEORGE BRUCE: Partial Interior/Exterior,/ Roof / Boiler | 3 | DESIGN COMPLETION | 2014-03-30 | 2014-03-30 | 2014-03-30 | 2014-03-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13GBR | GEORGE BRUCE: Partial Interior/Exterior,/ Roof / Boiler | 4 | CONSTRUCTION START | 2014-03-31 | 2014-03-31 | 2014-03-31 | 2014-03-31
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13GBR | GEORGE BRUCE: Partial Interior/Exterior,/ Roof / Boiler | 5 | CONSTRUCTION COMPLETION | 2014-04-01 | 2017-03-14 | 2016-04-01 | 2021-12-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13HAM | HAMILTON FISH: REHABILITATION | 1 | PROJECT START | 2013-03-18 | 2013-03-18 | 2013-03-18 | 2013-03-18
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13HAM | HAMILTON FISH: REHABILITATION | 2 | DESIGN START | 2013-03-19 | 2013-03-19 | 2013-03-19 | 2013-03-19
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13HAM | HAMILTON FISH: REHABILITATION | 3 | DESIGN COMPLETION | 2013-03-20 | 2013-03-20 | 2013-03-20 | 2013-03-20
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13HAM | HAMILTON FISH: REHABILITATION | 4 | CONSTRUCTION START | 2013-03-21 | 2013-03-21 | 2013-03-21 | 2013-03-21
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13HAM | HAMILTON FISH: REHABILITATION | 5 | CONSTRUCTION COMPLETION | 2013-03-22 | 2017-02-13 | 2016-06-30 | 2022-12-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13HUD | HUDSON PARK: Renovation | 1 | PROJECT START | 2013-04-02 | 2014-11-13 | 2013-04-02 | 2014-11-13
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13HUD | HUDSON PARK: Renovation | 2 | DESIGN START | 2014-11-14 | 2014-11-22 | 2014-11-14 | 2014-11-22
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13HUD | HUDSON PARK: Renovation | 3 | DESIGN COMPLETION | 2014-11-23 | 2016-06-11 | 2014-11-23 | 2016-06-11
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13HUD | HUDSON PARK: Renovation | 4 | CONSTRUCTION START | 2016-06-12 | 2017-05-11 | 2016-06-12 | 2018-05-11
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13HUD | HUDSON PARK: Renovation | 5 | CONSTRUCTION COMPLETION | 2017-05-12 | 2017-05-12 | 2017-06-30 | 2026-06-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13MLB | MUHLENBERG: Elevator | 1 | PROJECT START | 2013-02-07 | 2013-02-07 | 2013-02-07 | 2013-02-07
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13MLB | MUHLENBERG: Elevator | 2 | DESIGN START | 2013-02-08 | 2015-02-15 | 2013-02-08 | 2015-02-15
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13MLB | MUHLENBERG: Elevator | 3 | DESIGN COMPLETION | 2015-02-16 | 2015-09-30 | 2015-02-16 | 2015-09-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13MLB | MUHLENBERG: Elevator | 4 | CONSTRUCTION START | 2015-10-01 | 2016-02-28 | 2015-10-01 | 2016-02-28
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13MLB | MUHLENBERG: Elevator | 5 | CONSTRUCTION COMPLETION | 2016-02-29 | 2016-10-09 | 2016-02-29 | 2022-10-09
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13NAM | NEW AMSTERDAM - HVAC and Cooling Tower | 1 | PROJECT START | 2013-01-07 | 2015-02-15 | 2013-01-07 | 2013-01-07
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13NAM | NEW AMSTERDAM - HVAC and Cooling Tower | 2 | DESIGN START | 2015-02-16 | 2015-11-22 | 2013-01-08 | 2015-03-17
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13NAM | NEW AMSTERDAM - HVAC and Cooling Tower | 3 | DESIGN COMPLETION | 2015-11-23 | 2016-07-15 | 2015-03-18 | 2016-12-20
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13NAM | NEW AMSTERDAM - HVAC and Cooling Tower | 4 | CONSTRUCTION START | 2016-07-16 | 2016-07-15 | 2016-12-21 | 2018-10-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13NAM | NEW AMSTERDAM - HVAC and Cooling Tower | 5 | CONSTRUCTION COMPLETION | 2016-07-16 | 2017-06-05 | 2018-10-16 | 2022-01-24
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA14MBG | HVAC and Related Work | 1 | PROJECT START | 2014-09-08 | 2014-09-08 | 2014-09-08 | 2014-09-08
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA14MBG | HVAC and Related Work | 2 | DESIGN START | 2015-06-06 | 2015-06-06 | 2015-06-06 | 2015-08-24
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA14MBG | HVAC and Related Work | 3 | DESIGN COMPLETION | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2019-06-04
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA14MBG | HVAC and Related Work | 4 | CONSTRUCTION START | 2016-06-23 | 2016-06-23 | 2016-06-23 | 2020-02-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA14MBG | HVAC and Related Work | 5 | CONSTRUCTION COMPLETION | 2017-04-01 | 2017-04-01 | 2017-06-30 | 2021-06-13
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA15SPK | New Boiler | 1 | PROJECT START | 2014-11-15 | 2014-11-15 | 2014-11-15 | 2014-11-15
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA15SPK | New Boiler | 2 | DESIGN START | 2014-11-16 | 2014-11-16 | 2014-11-16 | 2014-11-16
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA15SPK | New Boiler | 3 | DESIGN COMPLETION | 2014-11-17 | 2014-11-17 | 2014-11-17 | 2014-11-17
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA15SPK | New Boiler | 4 | CONSTRUCTION START | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA15SPK | New Boiler | 5 | CONSTRUCTION COMPLETION | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2022-12-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCAL15CC | Countee Cullen:Exterior Renovation | 1 | PROJECT START | 2016-03-31 | 2016-03-31 | 2016-03-31 | 2016-03-31
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCAL15CC | Countee Cullen:Exterior Renovation | 2 | DESIGN START | 2016-04-04 | 2016-04-04 | 2016-04-04 | 2016-04-04
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCAL15CC | Countee Cullen:Exterior Renovation | 3 | DESIGN COMPLETION | 2016-04-06 | 2016-04-06 | 2016-04-06 | 2016-04-06
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCAL15CC | Countee Cullen:Exterior Renovation | 4 | CONSTRUCTION START | 2016-06-04 | 2016-06-04 | 2016-06-04 | 2016-06-04
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCAL15CC | Countee Cullen:Exterior Renovation | 5 | CONSTRUCTION COMPLETION | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2022-12-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEA08MHV | MANHATTAN (Northern) - HVAC @ Four Branch Libraries | 1 | PROJECT START | 2007-10-12 | 2007-10-12 | 2007-10-12 | 2007-10-12
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEA08MHV | MANHATTAN (Northern) - HVAC @ Four Branch Libraries | 2 | DESIGN START | 2009-04-07 | 2009-04-08 | 2009-10-20 | 2009-10-20
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEA08MHV | MANHATTAN (Northern) - HVAC @ Four Branch Libraries | 3 | DESIGN COMPLETION | 2010-03-14 | 2010-07-10 | 2011-01-29 | 2011-01-29
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEA08MHV | MANHATTAN (Northern) - HVAC @ Four Branch Libraries | 4 | CONSTRUCTION START | 2010-07-13 | 2012-01-10 | 2013-07-24 | 2013-07-24
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEA08MHV | MANHATTAN (Northern) - HVAC @ Four Branch Libraries | 5 | CONSTRUCTION COMPLETION | 2012-01-25 | 2012-03-19 | 2017-09-30 | 2022-09-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEA13HGR | HAMILTON GRANGE:Exterior Rehabiliation/ Window | 1 | PROJECT START | 2013-03-18 | 2013-03-18 | 2008-03-18 | 2008-03-18
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEA13HGR | HAMILTON GRANGE:Exterior Rehabiliation/ Window | 2 | DESIGN START | 2014-05-12 | 2014-05-12 | 2014-05-12 | 2014-05-12
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEA13HGR | HAMILTON GRANGE:Exterior Rehabiliation/ Window | 3 | DESIGN COMPLETION | 2015-07-15 | 2015-07-15 | 2015-07-15 | 2015-07-15
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEA13HGR | HAMILTON GRANGE:Exterior Rehabiliation/ Window | 4 | CONSTRUCTION START | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEA13HGR | HAMILTON GRANGE:Exterior Rehabiliation/ Window | 5 | CONSTRUCTION COMPLETION | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2022-03-14
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEM12MLB | MUHLENBERG - Sidewalk Vault | 1 | DESIGN | 2012-02-01 | 2012-02-01 | 2012-02-01 | 2013-04-23
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEM12MLB | MUHLENBERG - Sidewalk Vault | 2 | CONSTRUCTION | 2015-07-29 | 2015-07-29 | 2015-07-29 | 2019-09-17
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEM12MLB | MUHLENBERG - Sidewalk Vault | 3 | ORIGINAL EQUIP & FURNISHING | 2015-08-15 | 2015-08-15 | 2015-08-15 | 2020-09-17
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEM12MLB | MUHLENBERG - Sidewalk Vault | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2021-10-15
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEM13JMK | JEFFERSON MARKET: Fire Safety | 1 | DESIGN | 2013-05-30 | 2013-05-30 | 2013-05-30 | 2013-05-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEM13JMK | JEFFERSON MARKET: Fire Safety | 2 | CONSTRUCTION | 2016-08-28 | 2016-08-28 | 2016-08-28 | 2017-11-06
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEM13JMK | JEFFERSON MARKET: Fire Safety | 3 | ORIGINAL EQUIP & FURNISHING | 2016-08-29 | 2016-08-28 | 2017-11-07 | 2018-08-25
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEM13JMK | JEFFERSON MARKET: Fire Safety | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-10-07 | 2017-10-07 | 2018-10-07 | 2022-02-04
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNMNA08LS | MANHATTAN - Life Safety Projects @ 17 Branch Libraries | 1 | PROJECT START | 2010-01-31 | 2010-01-31 | 2008-01-07 | 2008-01-07
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNMNA08LS | MANHATTAN - Life Safety Projects @ 17 Branch Libraries | 2 | DESIGN START | 2010-02-01 | 2010-02-01 | 2009-10-27 | 2009-10-27
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNMNA08LS | MANHATTAN - Life Safety Projects @ 17 Branch Libraries | 3 | DESIGN COMPLETION | 2010-02-02 | 2010-02-02 | 2013-05-17 | 2015-05-17
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNMNA08LS | MANHATTAN - Life Safety Projects @ 17 Branch Libraries | 4 | CONSTRUCTION START | 2010-02-03 | 2010-02-03 | 2015-04-30 | 2018-04-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNMNA08LS | MANHATTAN - Life Safety Projects @ 17 Branch Libraries | 5 | CONSTRUCTION COMPLETION | 2010-02-04 | 2010-02-04 | 2017-10-01 | 2021-10-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LRCA17SCH | SCHOMBURG - Renovation Phase II Passthrough | 1 | PROJECT START | 2016-04-08 | 2016-04-08 | 2016-04-08 | 2016-04-08
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LRCA17SCH | SCHOMBURG - Renovation Phase II Passthrough | 2 | DESIGN START | 2016-04-09 | 2016-07-05 | 2016-04-09 | 2016-07-05
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LRCA17SCH | SCHOMBURG - Renovation Phase II Passthrough | 3 | DESIGN COMPLETION | 2016-07-06 | 2017-11-01 | 2016-07-06 | 2017-11-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LRCA17SCH | SCHOMBURG - Renovation Phase II Passthrough | 4 | CONSTRUCTION START | 2017-11-02 | 2019-12-31 | 2017-11-02 | 2019-12-31
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LRCA17SCH | SCHOMBURG - Renovation Phase II Passthrough | 5 | CONSTRUCTION COMPLETION | 2020-01-01 | 2022-12-31 | 2020-01-01 | 2025-12-31
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-594 | WM RPLMT IN E 46 ST & E 47 ST B/T MADISON AV & LEXINGTON AV | 1 | DEVELOP SCOPE | 2007-07-30 | 2007-10-27 | 2011-07-01 | 2012-08-21
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-594 | WM RPLMT IN E 46 ST & E 47 ST B/T MADISON AV & LEXINGTON AV | 2 | PRELIMINARY DESIGN | 2007-10-28 | 2008-02-24 | 2012-08-22 | 2014-07-25
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-594 | WM RPLMT IN E 46 ST & E 47 ST B/T MADISON AV & LEXINGTON AV | 3 | FINAL DESIGN | 2008-02-25 | 2008-08-22 | 2014-07-26 | 2019-11-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-594 | WM RPLMT IN E 46 ST & E 47 ST B/T MADISON AV & LEXINGTON AV | 4 | BID AWARD AND REGISTER CONTRCT | 2008-08-23 | 2008-11-20 | 2019-12-01 | 2020-03-06
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-594 | WM RPLMT IN E 46 ST & E 47 ST B/T MADISON AV & LEXINGTON AV | 5 | CONSTRUCTION TO 25% | 2008-11-21 | 2009-03-20 | 2020-03-07 | 2020-09-02
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-594 | WM RPLMT IN E 46 ST & E 47 ST B/T MADISON AV & LEXINGTON AV | 6 | CONSTRUCTION TO 50% | 2009-03-21 | 2009-07-18 | 2020-09-03 | 2021-03-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-594 | WM RPLMT IN E 46 ST & E 47 ST B/T MADISON AV & LEXINGTON AV | 7 | CONSTRUCTION TO 75% | 2009-07-19 | 2009-11-15 | 2021-03-02 | 2021-08-28
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-594 | WM RPLMT IN E 46 ST & E 47 ST B/T MADISON AV & LEXINGTON AV | 8 | ORIGINAL EQUIP & FURNISHING | 2009-11-16 | 2010-02-13 | 2021-08-29 | 2021-11-26
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-594 | WM RPLMT IN E 46 ST & E 47 ST B/T MADISON AV & LEXINGTON AV | 9 | SUBSTANTIAL COMPLETION | 2010-02-14 | 2010-04-14 | 2021-11-27 | 2022-01-25
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-594 | WM RPLMT IN E 46 ST & E 47 ST B/T MADISON AV & LEXINGTON AV | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2010-04-15 | 2010-05-14 | 2022-01-26 | 2024-06-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-596 | TRUNK WM IN HUDSON ST FRM LAIGHT ST TO WORTH ST | 1 | DEVELOP SCOPE | 2009-07-30 | 2009-10-27 | 2009-03-04 | 2009-06-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-596 | TRUNK WM IN HUDSON ST FRM LAIGHT ST TO WORTH ST | 2 | PRELIMINARY DESIGN | 2009-10-28 | 2010-02-24 | 2009-06-02 | 2009-09-29
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-596 | TRUNK WM IN HUDSON ST FRM LAIGHT ST TO WORTH ST | 3 | FINAL DESIGN | 2010-02-25 | 2010-08-23 | 2009-09-30 | 2010-03-28
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-596 | TRUNK WM IN HUDSON ST FRM LAIGHT ST TO WORTH ST | 4 | BID AWARD AND REGISTER CONTRCT | 2010-08-24 | 2010-11-21 | 2010-03-29 | 2010-06-26
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-596 | TRUNK WM IN HUDSON ST FRM LAIGHT ST TO WORTH ST | 5 | CONSTRUCTION TO 25% | 2010-11-22 | 2011-03-21 | 2010-06-27 | 2010-12-23
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-596 | TRUNK WM IN HUDSON ST FRM LAIGHT ST TO WORTH ST | 6 | CONSTRUCTION TO 50% | 2011-03-22 | 2011-07-19 | 2010-12-24 | 2012-12-22
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-596 | TRUNK WM IN HUDSON ST FRM LAIGHT ST TO WORTH ST | 7 | CONSTRUCTION TO 75% | 2011-07-20 | 2011-11-16 | 2012-12-23 | 2014-12-22
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-596 | TRUNK WM IN HUDSON ST FRM LAIGHT ST TO WORTH ST | 8 | ORIGINAL EQUIP & FURNISHING | 2011-11-17 | 2012-02-14 | 2014-12-23 | 2015-03-22
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-596 | TRUNK WM IN HUDSON ST FRM LAIGHT ST TO WORTH ST | 9 | SUBSTANTIAL COMPLETION | 2012-02-15 | 2012-04-14 | 2015-03-23 | 2015-09-18
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-596 | TRUNK WM IN HUDSON ST FRM LAIGHT ST TO WORTH ST | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-04-15 | 2012-05-14 | 2015-09-19 | 2023-06-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-597 | TRUNK WM IN EAST 31 STREET FRM 5TH AV TO 2ND AV | 1 | DEVELOP SCOPE | 2011-07-30 | 2011-10-27 | 2011-07-30 | 2011-10-27
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-597 | TRUNK WM IN EAST 31 STREET FRM 5TH AV TO 2ND AV | 2 | PRELIMINARY DESIGN | 2011-10-28 | 2012-02-24 | 2011-10-28 | 2012-02-24
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-597 | TRUNK WM IN EAST 31 STREET FRM 5TH AV TO 2ND AV | 3 | FINAL DESIGN | 2012-02-25 | 2012-08-22 | 2012-02-25 | 2012-08-22
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-597 | TRUNK WM IN EAST 31 STREET FRM 5TH AV TO 2ND AV | 4 | BID AWARD AND REGISTER CONTRCT | 2012-08-23 | 2012-11-20 | 2022-03-04 | 2022-06-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-597 | TRUNK WM IN EAST 31 STREET FRM 5TH AV TO 2ND AV | 5 | CONSTRUCTION TO 25% | 2012-11-21 | 2013-03-20 | 2022-06-02 | 2022-06-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-597 | TRUNK WM IN EAST 31 STREET FRM 5TH AV TO 2ND AV | 6 | CONSTRUCTION TO 50% | 2013-03-21 | 2013-07-18 | 2022-06-02 | 2022-06-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-597 | TRUNK WM IN EAST 31 STREET FRM 5TH AV TO 2ND AV | 7 | CONSTRUCTION TO 75% | 2013-07-19 | 2013-11-15 | 2022-06-02 | 2022-06-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-597 | TRUNK WM IN EAST 31 STREET FRM 5TH AV TO 2ND AV | 8 | ORIGINAL EQUIP & FURNISHING | 2013-11-16 | 2014-02-13 | 2022-06-02 | 2022-06-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-597 | TRUNK WM IN EAST 31 STREET FRM 5TH AV TO 2ND AV | 9 | SUBSTANTIAL COMPLETION | 2014-02-14 | 2014-04-14 | 2022-06-02 | 2022-06-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-597 | TRUNK WM IN EAST 31 STREET FRM 5TH AV TO 2ND AV | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-04-15 | 2014-05-14 | 2024-11-17 | 2024-12-16
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-598B | TRUNK WM IN W 30 ST - 9 AV TO 10 AV (SHAFT 26B) - PHASE B | 1 | DEVELOP SCOPE | 2012-07-01 | 2012-09-28 | 2017-03-01 | 2017-05-29
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-598B | TRUNK WM IN W 30 ST - 9 AV TO 10 AV (SHAFT 26B) - PHASE B | 2 | PRELIMINARY DESIGN | 2012-09-29 | 2013-01-26 | 2017-05-30 | 2017-09-26
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-598B | TRUNK WM IN W 30 ST - 9 AV TO 10 AV (SHAFT 26B) - PHASE B | 3 | FINAL DESIGN | 2013-01-27 | 2013-07-25 | 2017-09-27 | 2019-12-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-598B | TRUNK WM IN W 30 ST - 9 AV TO 10 AV (SHAFT 26B) - PHASE B | 4 | BID AWARD AND REGISTER CONTRCT | 2013-07-26 | 2013-10-23 | 2019-12-02 | 2020-02-29
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-598B | TRUNK WM IN W 30 ST - 9 AV TO 10 AV (SHAFT 26B) - PHASE B | 5 | CONSTRUCTION TO 25% | 2013-10-24 | 2014-02-20 | 2020-03-01 | 2020-06-28
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-598B | TRUNK WM IN W 30 ST - 9 AV TO 10 AV (SHAFT 26B) - PHASE B | 6 | CONSTRUCTION TO 50% | 2014-02-21 | 2014-06-20 | 2020-06-29 | 2020-10-26
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-598B | TRUNK WM IN W 30 ST - 9 AV TO 10 AV (SHAFT 26B) - PHASE B | 7 | CONSTRUCTION TO 75% | 2014-06-21 | 2014-10-18 | 2020-10-27 | 2021-02-23
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-598B | TRUNK WM IN W 30 ST - 9 AV TO 10 AV (SHAFT 26B) - PHASE B | 8 | ORIGINAL EQUIP & FURNISHING | 2014-10-19 | 2015-01-16 | 2021-02-24 | 2021-02-23
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-598B | TRUNK WM IN W 30 ST - 9 AV TO 10 AV (SHAFT 26B) - PHASE B | 9 | SUBSTANTIAL COMPLETION | 2015-01-17 | 2015-03-17 | 2021-02-24 | 2021-05-24
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-598B | TRUNK WM IN W 30 ST - 9 AV TO 10 AV (SHAFT 26B) - PHASE B | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-18 | 2015-04-16 | 2021-05-25 | 2022-06-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-604 | TRUNK & DIS WM IN EAST HOUSTONS ST (HWMP2019) | 1 | DEVELOP SCOPE | 2009-08-17 | 2009-11-14 | 2009-08-17 | 2009-11-14
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-604 | TRUNK & DIS WM IN EAST HOUSTONS ST (HWMP2019) | 2 | PRELIMINARY DESIGN | 2009-11-15 | 2010-03-14 | 2009-11-15 | 2010-03-14
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-604 | TRUNK & DIS WM IN EAST HOUSTONS ST (HWMP2019) | 3 | FINAL DESIGN | 2010-03-15 | 2012-02-14 | 2010-03-15 | 2011-10-16
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-604 | TRUNK & DIS WM IN EAST HOUSTONS ST (HWMP2019) | 4 | BID AWARD AND REGISTER CONTRCT | 2012-02-15 | 2012-06-01 | 2011-10-17 | 2012-02-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-604 | TRUNK & DIS WM IN EAST HOUSTONS ST (HWMP2019) | 5 | CONSTRUCTION TO 25% | 2012-06-02 | 2012-06-01 | 2012-02-02 | 2013-01-31
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-604 | TRUNK & DIS WM IN EAST HOUSTONS ST (HWMP2019) | 6 | CONSTRUCTION TO 50% | 2012-06-02 | 2012-06-01 | 2013-02-01 | 2014-01-31
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-604 | TRUNK & DIS WM IN EAST HOUSTONS ST (HWMP2019) | 7 | CONSTRUCTION TO 75% | 2012-06-02 | 2012-06-01 | 2014-02-01 | 2015-12-02
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-604 | TRUNK & DIS WM IN EAST HOUSTONS ST (HWMP2019) | 8 | ORIGINAL EQUIP & FURNISHING | 2012-06-02 | 2012-06-01 | 2015-12-03 | 2016-03-11
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-604 | TRUNK & DIS WM IN EAST HOUSTONS ST (HWMP2019) | 9 | SUBSTANTIAL COMPLETION | 2012-06-02 | 2012-06-01 | 2016-03-12 | 2016-06-09
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-604 | TRUNK & DIS WM IN EAST HOUSTONS ST (HWMP2019) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-06-02 | 2012-07-01 | 2016-06-10 | 2021-12-25
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-607 | TRUNK MAIN CONN TO SHAFT 32B IN 2ND AVE. INTER. OF E. 35ST. | 1 | DEVELOP SCOPE | 2010-02-15 | 2010-05-15 | 2010-03-02 | 2010-05-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-607 | TRUNK MAIN CONN TO SHAFT 32B IN 2ND AVE. INTER. OF E. 35ST. | 2 | PRELIMINARY DESIGN | 2010-05-16 | 2010-09-12 | 2010-05-31 | 2010-09-27
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-607 | TRUNK MAIN CONN TO SHAFT 32B IN 2ND AVE. INTER. OF E. 35ST. | 3 | FINAL DESIGN | 2010-09-13 | 2011-03-11 | 2010-09-28 | 2011-03-26
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-607 | TRUNK MAIN CONN TO SHAFT 32B IN 2ND AVE. INTER. OF E. 35ST. | 4 | BID AWARD AND REGISTER CONTRCT | 2011-03-12 | 2011-06-09 | 2016-03-28 | 2016-06-25
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-607 | TRUNK MAIN CONN TO SHAFT 32B IN 2ND AVE. INTER. OF E. 35ST. | 5 | CONSTRUCTION TO 25% | 2011-06-10 | 2011-10-07 | 2016-06-26 | 2016-06-25
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-607 | TRUNK MAIN CONN TO SHAFT 32B IN 2ND AVE. INTER. OF E. 35ST. | 6 | CONSTRUCTION TO 50% | 2011-10-08 | 2012-02-04 | 2016-06-26 | 2016-06-25
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-607 | TRUNK MAIN CONN TO SHAFT 32B IN 2ND AVE. INTER. OF E. 35ST. | 7 | CONSTRUCTION TO 75% | 2012-02-05 | 2012-06-03 | 2016-06-26 | 2016-06-25
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-607 | TRUNK MAIN CONN TO SHAFT 32B IN 2ND AVE. INTER. OF E. 35ST. | 8 | ORIGINAL EQUIP & FURNISHING | 2012-06-04 | 2012-09-01 | 2016-06-26 | 2016-06-25
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-607 | TRUNK MAIN CONN TO SHAFT 32B IN 2ND AVE. INTER. OF E. 35ST. | 9 | SUBSTANTIAL COMPLETION | 2012-09-02 | 2012-10-31 | 2016-06-26 | 2016-06-25
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-607 | TRUNK MAIN CONN TO SHAFT 32B IN 2ND AVE. INTER. OF E. 35ST. | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-11-01 | 2012-11-30 | 2017-11-22 | 2024-06-02
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-608 | WASHINGTON SQUARE PARK | 2 | PRELIMINARY DESIGN | 2011-04-01 | 2011-07-29 | 2013-01-29 | 2013-05-28
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-608 | WASHINGTON SQUARE PARK | 3 | FINAL DESIGN | 2011-07-30 | 2012-01-25 | 2013-05-29 | 2013-11-24
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-608 | WASHINGTON SQUARE PARK | 4 | BID AWARD AND REGISTER CONTRCT | 2012-01-26 | 2012-04-24 | 2013-11-25 | 2015-09-07
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-608 | WASHINGTON SQUARE PARK | 5 | CONSTRUCTION TO 25% | 2012-04-25 | 2012-08-22 | 2015-09-08 | 2016-01-05
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-608 | WASHINGTON SQUARE PARK | 6 | CONSTRUCTION TO 50% | 2012-08-23 | 2012-12-20 | 2016-01-06 | 2016-05-04
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-608 | WASHINGTON SQUARE PARK | 7 | CONSTRUCTION TO 75% | 2012-12-21 | 2013-04-19 | 2016-05-05 | 2016-09-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-608 | WASHINGTON SQUARE PARK | 8 | ORIGINAL EQUIP & FURNISHING | 2013-04-20 | 2013-07-18 | 2016-09-02 | 2018-11-22
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-608 | WASHINGTON SQUARE PARK | 9 | SUBSTANTIAL COMPLETION | 2013-07-19 | 2013-09-16 | 2018-11-23 | 2019-01-21
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-608 | WASHINGTON SQUARE PARK | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-09-17 | 2013-10-16 | 2019-01-22 | 2022-06-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-609 | TRUNK MAIN IN W60 ST, W.E. AVE TO COLUMBUS AV | 1 | DEVELOP SCOPE | 2011-01-01 | 2011-03-31 | 2011-01-01 | 2011-03-31
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-609 | TRUNK MAIN IN W60 ST, W.E. AVE TO COLUMBUS AV | 2 | PRELIMINARY DESIGN | 2011-04-01 | 2011-07-29 | 2011-04-01 | 2011-07-29
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-609 | TRUNK MAIN IN W60 ST, W.E. AVE TO COLUMBUS AV | 3 | FINAL DESIGN | 2011-07-30 | 2012-01-25 | 2011-07-30 | 2011-12-03
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-609 | TRUNK MAIN IN W60 ST, W.E. AVE TO COLUMBUS AV | 4 | BID AWARD AND REGISTER CONTRCT | 2012-01-26 | 2012-04-24 | 2011-12-04 | 2012-03-02
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-609 | TRUNK MAIN IN W60 ST, W.E. AVE TO COLUMBUS AV | 5 | CONSTRUCTION TO 25% | 2012-04-25 | 2012-08-22 | 2012-03-03 | 2014-03-02
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-609 | TRUNK MAIN IN W60 ST, W.E. AVE TO COLUMBUS AV | 6 | CONSTRUCTION TO 50% | 2012-08-23 | 2012-12-20 | 2014-03-03 | 2016-03-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-609 | TRUNK MAIN IN W60 ST, W.E. AVE TO COLUMBUS AV | 7 | CONSTRUCTION TO 75% | 2012-12-21 | 2013-04-19 | 2016-03-02 | 2019-03-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-609 | TRUNK MAIN IN W60 ST, W.E. AVE TO COLUMBUS AV | 8 | ORIGINAL EQUIP & FURNISHING | 2013-04-20 | 2013-07-18 | 2019-03-02 | 2019-03-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-609 | TRUNK MAIN IN W60 ST, W.E. AVE TO COLUMBUS AV | 9 | SUBSTANTIAL COMPLETION | 2013-07-19 | 2013-09-16 | 2019-03-02 | 2019-03-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-609 | TRUNK MAIN IN W60 ST, W.E. AVE TO COLUMBUS AV | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-09-17 | 2013-10-16 | 2019-03-02 | 2024-01-23
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-610 | TRUNK MAIN CONNECTION TO SHAFT 27B | 1 | DEVELOP SCOPE | 2011-01-01 | 2011-03-31 | 2010-12-04 | 2011-03-03
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-610 | TRUNK MAIN CONNECTION TO SHAFT 27B | 2 | PRELIMINARY DESIGN | 2011-04-01 | 2011-07-29 | 2011-03-04 | 2011-07-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-610 | TRUNK MAIN CONNECTION TO SHAFT 27B | 3 | FINAL DESIGN | 2011-07-30 | 2012-01-25 | 2011-07-02 | 2011-12-28
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-610 | TRUNK MAIN CONNECTION TO SHAFT 27B | 4 | BID AWARD AND REGISTER CONTRCT | 2012-01-26 | 2012-04-24 | 2011-12-29 | 2012-03-27
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-610 | TRUNK MAIN CONNECTION TO SHAFT 27B | 5 | CONSTRUCTION TO 25% | 2012-04-25 | 2012-08-22 | 2012-03-28 | 2012-09-23
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-610 | TRUNK MAIN CONNECTION TO SHAFT 27B | 6 | CONSTRUCTION TO 50% | 2012-08-23 | 2012-12-20 | 2012-09-24 | 2013-09-23
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-610 | TRUNK MAIN CONNECTION TO SHAFT 27B | 7 | CONSTRUCTION TO 75% | 2012-12-21 | 2013-04-19 | 2013-09-24 | 2015-09-23
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-610 | TRUNK MAIN CONNECTION TO SHAFT 27B | 8 | ORIGINAL EQUIP & FURNISHING | 2013-04-20 | 2013-07-18 | 2015-09-24 | 2015-09-25
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-610 | TRUNK MAIN CONNECTION TO SHAFT 27B | 9 | SUBSTANTIAL COMPLETION | 2013-07-19 | 2013-09-16 | 2015-09-24 | 2015-11-22
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-610 | TRUNK MAIN CONNECTION TO SHAFT 27B | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-09-17 | 2013-10-16 | 2015-11-23 | 2024-06-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-611 | TRUNK WM REPLACMT IN TRANSVERSE RD 3 | 1 | DEVELOP SCOPE | 2022-03-01 | 2022-05-29 | 2022-03-01 | 2022-05-29
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-611 | TRUNK WM REPLACMT IN TRANSVERSE RD 3 | 2 | PRELIMINARY DESIGN | 2022-05-30 | 2022-09-26 | 2022-05-30 | 2022-09-26
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-611 | TRUNK WM REPLACMT IN TRANSVERSE RD 3 | 3 | FINAL DESIGN | 2022-09-27 | 2023-03-25 | 2022-09-27 | 2023-03-25
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-611 | TRUNK WM REPLACMT IN TRANSVERSE RD 3 | 4 | BID AWARD AND REGISTER CONTRCT | 2023-03-26 | 2023-06-23 | 2023-03-26 | 2023-06-23
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-611 | TRUNK WM REPLACMT IN TRANSVERSE RD 3 | 5 | CONSTRUCTION TO 25% | 2023-06-24 | 2023-10-21 | 2023-06-24 | 2023-10-21
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-611 | TRUNK WM REPLACMT IN TRANSVERSE RD 3 | 6 | CONSTRUCTION TO 50% | 2023-10-22 | 2024-02-18 | 2023-10-22 | 2024-02-18
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-611 | TRUNK WM REPLACMT IN TRANSVERSE RD 3 | 7 | CONSTRUCTION TO 75% | 2024-02-19 | 2024-06-17 | 2024-02-19 | 2024-06-17
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-611 | TRUNK WM REPLACMT IN TRANSVERSE RD 3 | 8 | ORIGINAL EQUIP & FURNISHING | 2024-06-18 | 2024-09-15 | 2024-06-18 | 2024-09-15
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-611 | TRUNK WM REPLACMT IN TRANSVERSE RD 3 | 9 | SUBSTANTIAL COMPLETION | 2024-09-16 | 2024-11-14 | 2024-09-16 | 2024-11-14
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-611 | TRUNK WM REPLACMT IN TRANSVERSE RD 3 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-11-15 | 2024-12-14 | 2024-11-15 | 2024-12-14
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-619 | Trunk Main replacement, b'way b/t w 93 & 97 st, Manh | 1 | DEVELOP SCOPE | 2013-06-30 | 2014-03-26 | 2013-06-13 | 2013-09-10
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-619 | Trunk Main replacement, b'way b/t w 93 & 97 st, Manh | 2 | PRELIMINARY DESIGN | 2014-03-27 | 2015-03-21 | 2013-09-11 | 2014-01-08
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-619 | Trunk Main replacement, b'way b/t w 93 & 97 st, Manh | 3 | FINAL DESIGN | 2015-03-22 | 2016-09-11 | 2014-01-09 | 2014-07-07
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-619 | Trunk Main replacement, b'way b/t w 93 & 97 st, Manh | 4 | BID AWARD AND REGISTER CONTRCT | 2016-09-12 | 2017-06-08 | 2014-07-08 | 2014-10-05
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-619 | Trunk Main replacement, b'way b/t w 93 & 97 st, Manh | 5 | CONSTRUCTION TO 25% | 2017-06-09 | 2018-06-03 | 2014-10-06 | 2015-02-02
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-619 | Trunk Main replacement, b'way b/t w 93 & 97 st, Manh | 6 | CONSTRUCTION TO 50% | 2018-06-04 | 2019-05-29 | 2015-02-03 | 2015-06-02
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-619 | Trunk Main replacement, b'way b/t w 93 & 97 st, Manh | 7 | CONSTRUCTION TO 75% | 2019-05-30 | 2020-05-23 | 2015-06-03 | 2015-09-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-619 | Trunk Main replacement, b'way b/t w 93 & 97 st, Manh | 8 | ORIGINAL EQUIP & FURNISHING | 2020-05-24 | 2021-02-17 | 2015-10-01 | 2015-12-29
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-619 | Trunk Main replacement, b'way b/t w 93 & 97 st, Manh | 9 | SUBSTANTIAL COMPLETION | 2021-02-18 | 2021-08-16 | 2015-12-30 | 2016-02-27
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-619 | Trunk Main replacement, b'way b/t w 93 & 97 st, Manh | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-08-17 | 2021-11-14 | 2016-02-28 | 2024-06-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-622 | Water Main Replacement Park Ave, Man (HWPLZ004M) | 1 | DEVELOP SCOPE | 2011-07-01 | 2011-09-28 | 2009-01-27 | 2010-07-12
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-622 | Water Main Replacement Park Ave, Man (HWPLZ004M) | 2 | PRELIMINARY DESIGN | 2011-09-29 | 2012-01-26 | 2010-07-13 | 2012-03-15
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-622 | Water Main Replacement Park Ave, Man (HWPLZ004M) | 3 | FINAL DESIGN | 2012-01-27 | 2012-07-24 | 2012-03-16 | 2013-03-15
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-622 | Water Main Replacement Park Ave, Man (HWPLZ004M) | 4 | BID AWARD AND REGISTER CONTRCT | 2012-07-25 | 2012-10-22 | 2013-03-16 | 2014-04-13
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-622 | Water Main Replacement Park Ave, Man (HWPLZ004M) | 5 | CONSTRUCTION TO 25% | 2012-10-23 | 2013-02-19 | 2014-04-14 | 2014-08-11
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-622 | Water Main Replacement Park Ave, Man (HWPLZ004M) | 6 | CONSTRUCTION TO 50% | 2013-02-20 | 2013-06-19 | 2014-08-12 | 2014-12-09
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-622 | Water Main Replacement Park Ave, Man (HWPLZ004M) | 7 | CONSTRUCTION TO 75% | 2013-06-20 | 2013-10-17 | 2014-12-10 | 2015-04-08
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-622 | Water Main Replacement Park Ave, Man (HWPLZ004M) | 8 | ORIGINAL EQUIP & FURNISHING | 2013-10-18 | 2014-01-15 | 2015-04-09 | 2015-08-06
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-622 | Water Main Replacement Park Ave, Man (HWPLZ004M) | 9 | SUBSTANTIAL COMPLETION | 2014-01-16 | 2014-03-16 | 2015-08-07 | 2015-10-05
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-622 | Water Main Replacement Park Ave, Man (HWPLZ004M) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-03-17 | 2014-04-15 | 2015-10-06 | 2022-09-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-625 | WEST 14TH STREET | 1 | DEVELOP SCOPE | 2012-02-27 | 2012-05-26 | 2012-02-27 | 2012-05-26
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-625 | WEST 14TH STREET | 2 | PRELIMINARY DESIGN | 2012-05-27 | 2012-09-23 | 2012-05-27 | 2012-09-23
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-625 | WEST 14TH STREET | 3 | FINAL DESIGN | 2012-09-24 | 2013-03-22 | 2012-09-24 | 2013-03-22
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-625 | WEST 14TH STREET | 4 | BID AWARD AND REGISTER CONTRCT | 2013-03-23 | 2013-06-20 | 2013-03-23 | 2013-06-20
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-625 | WEST 14TH STREET | 5 | CONSTRUCTION TO 25% | 2013-06-21 | 2013-10-18 | 2013-06-21 | 2013-10-18
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-625 | WEST 14TH STREET | 6 | CONSTRUCTION TO 50% | 2013-10-19 | 2014-02-15 | 2013-10-19 | 2014-02-15
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-625 | WEST 14TH STREET | 7 | CONSTRUCTION TO 75% | 2014-02-16 | 2014-06-15 | 2014-02-16 | 2014-06-15
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-625 | WEST 14TH STREET | 8 | ORIGINAL EQUIP & FURNISHING | 2014-06-16 | 2014-09-13 | 2014-06-16 | 2014-09-13
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-625 | WEST 14TH STREET | 9 | SUBSTANTIAL COMPLETION | 2014-09-14 | 2014-11-12 | 2014-09-14 | 2014-11-12
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-625 | WEST 14TH STREET | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-11-13 | 2014-12-12 | 2014-11-13 | 2023-06-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-630 | WM replacement at 170 st, amsterdam ave & b'way, MANHATTAN | 2 | PRELIMINARY DESIGN | 2015-05-19 | 2015-09-15 | 2015-05-19 | 2015-09-15
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-630 | WM replacement at 170 st, amsterdam ave & b'way, MANHATTAN | 3 | FINAL DESIGN | 2015-09-16 | 2016-03-13 | 2015-09-16 | 2016-03-13
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-630 | WM replacement at 170 st, amsterdam ave & b'way, MANHATTAN | 4 | BID AWARD AND REGISTER CONTRCT | 2016-03-14 | 2016-06-11 | 2016-03-14 | 2016-06-11
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-630 | WM replacement at 170 st, amsterdam ave & b'way, MANHATTAN | 5 | CONSTRUCTION TO 25% | 2016-06-12 | 2016-10-09 | 2016-06-12 | 2016-10-09
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-630 | WM replacement at 170 st, amsterdam ave & b'way, MANHATTAN | 6 | CONSTRUCTION TO 50% | 2016-10-10 | 2017-02-06 | 2016-10-10 | 2017-02-06
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-630 | WM replacement at 170 st, amsterdam ave & b'way, MANHATTAN | 7 | CONSTRUCTION TO 75% | 2017-02-07 | 2017-06-06 | 2017-02-07 | 2017-06-06
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-630 | WM replacement at 170 st, amsterdam ave & b'way, MANHATTAN | 8 | ORIGINAL EQUIP & FURNISHING | 2017-06-07 | 2017-09-04 | 2017-06-07 | 2017-09-04
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-630 | WM replacement at 170 st, amsterdam ave & b'way, MANHATTAN | 9 | SUBSTANTIAL COMPLETION | 2017-09-05 | 2017-11-03 | 2017-09-05 | 2017-11-03
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-630 | WM replacement at 170 st, amsterdam ave & b'way, MANHATTAN | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-11-04 | 2017-12-03 | 2017-11-04 | 2017-12-03
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-667 | Replacement of Water main in Delancey Street (HWM2025) | 1 | DEVELOP SCOPE | 2017-03-19 | 2017-06-16 | 2017-03-19 | 2017-06-16
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-667 | Replacement of Water main in Delancey Street (HWM2025) | 2 | PRELIMINARY DESIGN | 2017-06-17 | 2017-10-14 | 2017-06-17 | 2017-10-14
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-667 | Replacement of Water main in Delancey Street (HWM2025) | 3 | FINAL DESIGN | 2017-10-15 | 2018-04-12 | 2017-10-15 | 2018-04-12
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-667 | Replacement of Water main in Delancey Street (HWM2025) | 4 | BID AWARD AND REGISTER CONTRCT | 2018-04-13 | 2018-07-11 | 2018-04-13 | 2018-07-11
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-667 | Replacement of Water main in Delancey Street (HWM2025) | 5 | CONSTRUCTION TO 25% | 2018-07-12 | 2018-11-08 | 2018-07-12 | 2018-11-08
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-667 | Replacement of Water main in Delancey Street (HWM2025) | 6 | CONSTRUCTION TO 50% | 2018-11-09 | 2019-03-08 | 2018-11-09 | 2019-03-08
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-667 | Replacement of Water main in Delancey Street (HWM2025) | 7 | CONSTRUCTION TO 75% | 2019-03-09 | 2019-07-06 | 2019-03-09 | 2019-07-06
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-667 | Replacement of Water main in Delancey Street (HWM2025) | 8 | ORIGINAL EQUIP & FURNISHING | 2019-07-07 | 2019-10-04 | 2019-07-07 | 2019-10-04
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-667 | Replacement of Water main in Delancey Street (HWM2025) | 9 | SUBSTANTIAL COMPLETION | 2019-10-05 | 2019-12-03 | 2019-10-05 | 2019-12-03
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-667 | Replacement of Water main in Delancey Street (HWM2025) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-04 | 2025-06-30 | 2019-12-04 | 2025-06-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-668 | Installation of Distri WM & appurtenances Vesey street | 1 | DEVELOP SCOPE | 2019-08-23 | 2019-11-20 | 2019-08-23 | 2019-11-20
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-668 | Installation of Distri WM & appurtenances Vesey street | 2 | PRELIMINARY DESIGN | 2019-11-21 | 2020-03-19 | 2019-11-21 | 2020-03-19
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-668 | Installation of Distri WM & appurtenances Vesey street | 3 | FINAL DESIGN | 2020-03-20 | 2020-09-15 | 2020-03-20 | 2020-09-15
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-668 | Installation of Distri WM & appurtenances Vesey street | 4 | BID AWARD AND REGISTER CONTRCT | 2020-09-16 | 2020-12-14 | 2020-09-16 | 2020-12-14
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-668 | Installation of Distri WM & appurtenances Vesey street | 5 | CONSTRUCTION TO 25% | 2020-12-15 | 2021-04-13 | 2020-12-15 | 2021-04-13
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-668 | Installation of Distri WM & appurtenances Vesey street | 6 | CONSTRUCTION TO 50% | 2021-04-14 | 2021-08-11 | 2021-04-14 | 2021-08-11
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-668 | Installation of Distri WM & appurtenances Vesey street | 7 | CONSTRUCTION TO 75% | 2021-08-12 | 2021-12-09 | 2021-08-12 | 2021-12-09
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-668 | Installation of Distri WM & appurtenances Vesey street | 8 | ORIGINAL EQUIP & FURNISHING | 2021-12-10 | 2022-03-09 | 2021-12-10 | 2022-03-09
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-668 | Installation of Distri WM & appurtenances Vesey street | 9 | SUBSTANTIAL COMPLETION | 2022-03-10 | 2022-05-08 | 2022-03-10 | 2022-05-08
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-668 | Installation of Distri WM & appurtenances Vesey street | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-05-09 | 2022-06-07 | 2022-05-09 | 2022-06-07
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-670 | Replacement of distriibution WM in 43rd Street, HWMME43ST | 1 | DEVELOP SCOPE | 2019-08-23 | 2019-11-20 | 2019-08-23 | 2019-11-20
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-670 | Replacement of distriibution WM in 43rd Street, HWMME43ST | 2 | PRELIMINARY DESIGN | 2019-11-21 | 2020-03-19 | 2019-11-21 | 2020-03-19
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-670 | Replacement of distriibution WM in 43rd Street, HWMME43ST | 3 | FINAL DESIGN | 2020-03-20 | 2020-09-15 | 2020-03-20 | 2020-09-15
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-670 | Replacement of distriibution WM in 43rd Street, HWMME43ST | 4 | BID AWARD AND REGISTER CONTRCT | 2020-09-16 | 2020-12-14 | 2020-09-16 | 2020-12-14
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-670 | Replacement of distriibution WM in 43rd Street, HWMME43ST | 5 | CONSTRUCTION TO 25% | 2020-12-15 | 2021-04-13 | 2020-12-15 | 2021-04-13
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-670 | Replacement of distriibution WM in 43rd Street, HWMME43ST | 6 | CONSTRUCTION TO 50% | 2021-04-14 | 2021-08-11 | 2021-04-14 | 2021-08-11
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-670 | Replacement of distriibution WM in 43rd Street, HWMME43ST | 7 | CONSTRUCTION TO 75% | 2021-08-12 | 2021-12-09 | 2021-08-12 | 2021-12-09
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-670 | Replacement of distriibution WM in 43rd Street, HWMME43ST | 8 | ORIGINAL EQUIP & FURNISHING | 2021-12-10 | 2022-03-09 | 2021-12-10 | 2022-03-09
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-670 | Replacement of distriibution WM in 43rd Street, HWMME43ST | 9 | SUBSTANTIAL COMPLETION | 2022-03-10 | 2022-05-08 | 2022-03-10 | 2022-05-08
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-670 | Replacement of distriibution WM in 43rd Street, HWMME43ST | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-05-09 | 2022-06-07 | 2022-05-09 | 2024-06-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MEDA-003 | Accelerated Distribution WM replcmnt & sewer rebhab - MAN | 1 | DEVELOP SCOPE | 2016-10-10 | 2017-01-07 | 2016-10-10 | 2017-01-07
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MEDA-003 | Accelerated Distribution WM replcmnt & sewer rebhab - MAN | 2 | PRELIMINARY DESIGN | 2017-01-08 | 2017-05-07 | 2017-01-08 | 2017-05-07
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MEDA-003 | Accelerated Distribution WM replcmnt & sewer rebhab - MAN | 3 | FINAL DESIGN | 2017-05-08 | 2017-11-03 | 2017-05-08 | 2017-11-03
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MEDA-003 | Accelerated Distribution WM replcmnt & sewer rebhab - MAN | 4 | BID AWARD AND REGISTER CONTRCT | 2017-11-04 | 2018-02-01 | 2017-11-04 | 2018-02-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MEDA-003 | Accelerated Distribution WM replcmnt & sewer rebhab - MAN | 5 | CONSTRUCTION TO 25% | 2018-02-02 | 2018-06-01 | 2018-02-02 | 2018-06-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MEDA-003 | Accelerated Distribution WM replcmnt & sewer rebhab - MAN | 6 | CONSTRUCTION TO 50% | 2018-06-02 | 2018-09-29 | 2018-06-02 | 2018-09-29
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MEDA-003 | Accelerated Distribution WM replcmnt & sewer rebhab - MAN | 7 | CONSTRUCTION TO 75% | 2018-09-30 | 2019-01-27 | 2018-09-30 | 2019-01-27
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MEDA-003 | Accelerated Distribution WM replcmnt & sewer rebhab - MAN | 8 | ORIGINAL EQUIP & FURNISHING | 2019-01-28 | 2019-04-27 | 2019-01-28 | 2019-04-27
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MEDA-003 | Accelerated Distribution WM replcmnt & sewer rebhab - MAN | 9 | SUBSTANTIAL COMPLETION | 2019-04-28 | 2019-06-26 | 2019-04-28 | 2019-06-26
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MEDA-003 | Accelerated Distribution WM replcmnt & sewer rebhab - MAN | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-06-27 | 2019-07-26 | 2019-06-27 | 2026-06-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | P-303ERPK | East River Park | 1 | PROJECT START | 2018-03-01 | 2018-03-01 | 2018-03-01 | 2018-03-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | P-303ERPK | East River Park | 2 | DESIGN START | 2018-03-02 | 2018-03-02 | 2018-03-02 | 2018-03-02
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | P-303ERPK | East River Park | 3 | DESIGN COMPLETION | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | P-303ERPK | East River Park | 4 | CONSTRUCTION START | 2018-03-04 | 2018-03-04 | 2018-03-04 | 2018-03-04
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | P-303ERPK | East River Park | 5 | CONSTRUCTION COMPLETION | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2021-03-05
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | P-30420SP | West 20th St. Park Demolition & Abatement | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-12-16 | 2016-01-03
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | P-30420SP | West 20th St. Park Demolition & Abatement | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2016-01-04 | 2016-04-02
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | P-30420SP | West 20th St. Park Demolition & Abatement | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2016-04-03 | 2017-04-26
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | P-30420SP | West 20th St. Park Demolition & Abatement | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2017-04-27 | 2018-05-31
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | P-30420SP | West 20th St. Park Demolition & Abatement | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2018-06-01 | 2025-01-21
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | P-3RANDAL | Randall's Island Infrastructure, Roadways, Drainage, & CS | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2015-12-27
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | P-3RANDAL | Randall's Island Infrastructure, Roadways, Drainage, & CS | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2015-12-28 | 2017-03-26
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | P-3RANDAL | Randall's Island Infrastructure, Roadways, Drainage, & CS | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2017-03-27 | 2017-12-21
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | P-3RANDAL | Randall's Island Infrastructure, Roadways, Drainage, & CS | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2017-12-22 | 2018-12-21
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | P-3RANDAL | Randall's Island Infrastructure, Roadways, Drainage, & CS | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2018-12-22 | 2025-06-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79BMAHJ | One Police Plaza | 1 | PROJECT START | 2013-11-12 | 2013-11-12 | 2013-11-11 | 2013-11-12
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79BMAHJ | One Police Plaza | 2 | DESIGN START | 2014-05-23 | 2014-05-23 | 2013-11-13 | 2014-05-23
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79BMAHJ | One Police Plaza | 3 | DESIGN COMPLETION | 2014-05-24 | 2015-07-02 | 2014-05-24 | 2015-10-15
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79BMAHJ | One Police Plaza | 4 | CONSTRUCTION START | 2015-07-03 | 2015-11-02 | 2015-10-16 | 2017-12-25
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79BMAHJ | One Police Plaza | 5 | CONSTRUCTION COMPLETION | 2015-11-03 | 2017-03-01 | 2017-12-26 | 2020-07-21
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79BMAHQ | ONE POLICE PLAZA PAVING AND LANDSCAPING | 1 | PROJECT START | 2013-11-12 | 2013-11-12 | 2013-11-12 | 2013-11-12
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79BMAHQ | ONE POLICE PLAZA PAVING AND LANDSCAPING | 2 | DESIGN START | 2013-11-13 | 2014-05-23 | 2013-11-13 | 2014-05-23
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79BMAHQ | ONE POLICE PLAZA PAVING AND LANDSCAPING | 3 | DESIGN COMPLETION | 2014-05-24 | 2015-07-02 | 2014-05-24 | 2015-07-02
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79BMAHQ | ONE POLICE PLAZA PAVING AND LANDSCAPING | 4 | CONSTRUCTION START | 2015-07-03 | 2015-11-02 | 2015-07-03 | 2015-11-02
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79BMAHQ | ONE POLICE PLAZA PAVING AND LANDSCAPING | 5 | CONSTRUCTION COMPLETION | 2015-11-03 | 2017-03-01 | 2015-11-03 | 2020-08-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79BMAJU | 26TH PRECINCT ROOF, WINDOWS & FACADE | 1 | DEVELOP SCOPE | 2017-12-30 | 2018-03-29 | 2017-12-30 | 2018-03-29
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79BMAJU | 26TH PRECINCT ROOF, WINDOWS & FACADE | 2 | PRELIMINARY DESIGN | 2018-03-30 | 2018-07-27 | 2018-03-30 | 2019-05-13
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79BMAJU | 26TH PRECINCT ROOF, WINDOWS & FACADE | 3 | FINAL DESIGN | 2018-07-28 | 2018-11-24 | 2019-05-14 | 2021-03-20
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79BMAJU | 26TH PRECINCT ROOF, WINDOWS & FACADE | 4 | BID AWARD AND REGISTER CONTRCT | 2018-11-25 | 2019-05-23 | 2021-03-21 | 2021-11-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79BMAJU | 26TH PRECINCT ROOF, WINDOWS & FACADE | 5 | CONSTRUCTION TO 25% | 2019-05-24 | 2019-09-20 | 2021-12-01 | 2022-03-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79BMAJU | 26TH PRECINCT ROOF, WINDOWS & FACADE | 6 | CONSTRUCTION TO 50% | 2019-09-21 | 2020-01-18 | 2022-03-31 | 2022-07-28
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79BMAJU | 26TH PRECINCT ROOF, WINDOWS & FACADE | 7 | CONSTRUCTION TO 75% | 2020-01-19 | 2020-05-17 | 2022-07-29 | 2022-11-25
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79BMAJU | 26TH PRECINCT ROOF, WINDOWS & FACADE | 8 | ORIGINAL EQUIP & FURNISHING | 2020-05-18 | 2020-08-15 | 2022-11-26 | 2022-11-27
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79BMAJU | 26TH PRECINCT ROOF, WINDOWS & FACADE | 9 | SUBSTANTIAL COMPLETION | 2020-08-16 | 2020-10-14 | 2022-11-28 | 2023-05-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79BMAJU | 26TH PRECINCT ROOF, WINDOWS & FACADE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-10-15 | 2020-11-13 | 2023-05-02 | 2024-05-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79BMAJU | 26TH PRECINCT ROOF, WINDOWS & FACADE | 11 | PROJECT START | 2020-10-15 | 2020-11-13 | 2024-05-02 | 2024-05-02
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79BMAJU | 26TH PRECINCT ROOF, WINDOWS & FACADE | 12 | DESIGN START | 2020-10-15 | 2020-11-13 | 2024-05-03 | 2024-05-03
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79BMAJU | 26TH PRECINCT ROOF, WINDOWS & FACADE | 13 | DESIGN COMPLETION | 2020-10-15 | 2020-11-13 | 2024-05-04 | 2024-05-04
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79BMAJU | 26TH PRECINCT ROOF, WINDOWS & FACADE | 14 | CONSTRUCTION START | 2020-10-15 | 2020-11-13 | 2024-05-05 | 2024-05-05
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79BMAJU | 26TH PRECINCT ROOF, WINDOWS & FACADE | 15 | CONSTRUCTION COMPLETION | 2020-10-15 | 2020-11-13 | 2024-05-06 | 2024-05-06
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV034NWCH | AMNH - Northwest Coast Hall Renovation | 1 | DEVELOP SCOPE | 2023-04-08 | 2023-07-06 | 2024-04-08 | 2024-07-06
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV034NWCH | AMNH - Northwest Coast Hall Renovation | 2 | BID AWARD AND REGISTER CONTRCT | 2023-07-07 | 2023-10-04 | 2024-07-07 | 2024-10-04
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV034NWCH | AMNH - Northwest Coast Hall Renovation | 3 | CONSTRUCTION TO 50% | 2023-10-05 | 2024-02-01 | 2024-10-05 | 2025-02-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV034NWCH | AMNH - Northwest Coast Hall Renovation | 4 | CONSTRUCTION TO 75% | 2024-02-02 | 2024-04-01 | 2025-02-02 | 2025-04-02
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV034NWCH | AMNH - Northwest Coast Hall Renovation | 5 | SUBSTANTIAL COMPLETION | 2024-04-02 | 2024-05-31 | 2025-04-03 | 2025-06-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV034NWCH | AMNH - Northwest Coast Hall Renovation | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-06-01 | 2024-06-30 | 2025-06-02 | 2025-07-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV234CSV1 | CSV - Clemente Soto Velez - Interior Code Compliance | 1 | DEVELOP SCOPE | 2010-10-18 | 2011-01-15 | 2016-10-17 | 2017-01-14
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV234CSV1 | CSV - Clemente Soto Velez - Interior Code Compliance | 2 | PRELIMINARY DESIGN | 2011-01-16 | 2011-05-15 | 2017-01-15 | 2017-05-14
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV234CSV1 | CSV - Clemente Soto Velez - Interior Code Compliance | 3 | FINAL DESIGN | 2011-05-16 | 2011-11-11 | 2017-05-15 | 2017-11-10
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV234CSV1 | CSV - Clemente Soto Velez - Interior Code Compliance | 4 | BID AWARD AND REGISTER CONTRCT | 2011-11-12 | 2012-02-09 | 2017-11-11 | 2018-02-08
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV234CSV1 | CSV - Clemente Soto Velez - Interior Code Compliance | 5 | CONSTRUCTION TO 25% | 2012-02-10 | 2012-06-08 | 2018-02-09 | 2018-06-08
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV234CSV1 | CSV - Clemente Soto Velez - Interior Code Compliance | 6 | CONSTRUCTION TO 50% | 2012-06-09 | 2012-10-06 | 2018-06-09 | 2018-10-06
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV234CSV1 | CSV - Clemente Soto Velez - Interior Code Compliance | 7 | CONSTRUCTION TO 75% | 2012-10-07 | 2013-02-03 | 2018-10-07 | 2019-02-03
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV234CSV1 | CSV - Clemente Soto Velez - Interior Code Compliance | 8 | ORIGINAL EQUIP & FURNISHING | 2013-02-04 | 2013-05-04 | 2019-02-04 | 2019-05-04
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV234CSV1 | CSV - Clemente Soto Velez - Interior Code Compliance | 9 | SUBSTANTIAL COMPLETION | 2013-05-05 | 2013-07-03 | 2019-05-05 | 2019-07-03
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV234CSV1 | CSV - Clemente Soto Velez - Interior Code Compliance | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-07-04 | 2013-08-02 | 2019-07-04 | 2022-06-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV234CSV1 | CSV - Clemente Soto Velez - Interior Code Compliance | 11 | PROJECT START | 2013-07-04 | 2013-08-02 | 2022-07-01 | 2022-07-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV234CSV1 | CSV - Clemente Soto Velez - Interior Code Compliance | 12 | DESIGN START | 2013-07-04 | 2013-08-02 | 2022-07-02 | 2022-07-02
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV234CSV1 | CSV - Clemente Soto Velez - Interior Code Compliance | 13 | DESIGN COMPLETION | 2013-07-04 | 2013-08-02 | 2022-07-03 | 2022-07-03
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV234CSV1 | CSV - Clemente Soto Velez - Interior Code Compliance | 14 | CONSTRUCTION START | 2013-07-04 | 2013-08-02 | 2022-07-04 | 2022-07-04
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV234CSV1 | CSV - Clemente Soto Velez - Interior Code Compliance | 15 | CONSTRUCTION COMPLETION | 2013-07-04 | 2013-08-02 | 2022-07-05 | 2022-07-05
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV241EXTR | MCNY - Exterior Facade Rehabilitation | 1 | DEVELOP SCOPE | 2016-06-30 | 2016-09-27 | 2016-11-17 | 2016-11-17
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV241EXTR | MCNY - Exterior Facade Rehabilitation | 2 | PRELIMINARY DESIGN | 2016-09-28 | 2017-01-25 | 2016-11-18 | 2018-08-07
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV241EXTR | MCNY - Exterior Facade Rehabilitation | 3 | FINAL DESIGN | 2017-01-26 | 2017-07-24 | 2018-08-08 | 2019-10-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV241EXTR | MCNY - Exterior Facade Rehabilitation | 4 | BID AWARD AND REGISTER CONTRCT | 2017-07-25 | 2017-10-22 | 2019-10-02 | 2020-10-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV241EXTR | MCNY - Exterior Facade Rehabilitation | 5 | CONSTRUCTION TO 25% | 2017-10-23 | 2018-02-19 | 2020-10-02 | 2021-12-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV241EXTR | MCNY - Exterior Facade Rehabilitation | 6 | CONSTRUCTION TO 50% | 2018-02-20 | 2018-06-19 | 2020-10-02 | 2021-12-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV241EXTR | MCNY - Exterior Facade Rehabilitation | 7 | CONSTRUCTION TO 75% | 2018-06-20 | 2018-10-17 | 2020-10-02 | 2021-12-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV241EXTR | MCNY - Exterior Facade Rehabilitation | 8 | ORIGINAL EQUIP & FURNISHING | 2018-10-18 | 2019-01-15 | 2020-10-02 | 2021-12-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV241EXTR | MCNY - Exterior Facade Rehabilitation | 9 | SUBSTANTIAL COMPLETION | 2019-01-16 | 2019-03-16 | 2020-10-02 | 2021-12-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV241EXTR | MCNY - Exterior Facade Rehabilitation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-03-17 | 2019-04-15 | 2020-10-02 | 2021-12-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV467-122 | 122C - 122 Community Center Bldg Reconstruction | 1 | PROJECT START | 2005-05-06 | 2005-05-06 | 2005-05-06 | 2005-05-06
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV467-122 | 122C - 122 Community Center Bldg Reconstruction | 2 | DESIGN START | 2005-05-15 | 2006-01-24 | 2006-05-15 | 2007-05-15
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV467-122 | 122C - 122 Community Center Bldg Reconstruction | 3 | DESIGN COMPLETION | 2006-01-25 | 2006-01-25 | 2010-10-26 | 2012-05-24
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV467-122 | 122C - 122 Community Center Bldg Reconstruction | 4 | CONSTRUCTION START | 2006-03-25 | 2008-03-27 | 2013-05-25 | 2014-05-25
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV467-122 | 122C - 122 Community Center Bldg Reconstruction | 5 | CONSTRUCTION COMPLETION | 2008-03-28 | 2008-03-28 | 2015-05-26 | 2021-07-05
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW195SA | 80 CENTRE ST. - SAFE ACCESS, REPLACEMENT OF CATWALKS | 1 | DEVELOP SCOPE | 2014-06-01 | 2014-08-29 | 2014-06-01 | 2014-08-29
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW195SA | 80 CENTRE ST. - SAFE ACCESS, REPLACEMENT OF CATWALKS | 2 | PRELIMINARY DESIGN | 2014-08-30 | 2014-12-27 | 2014-08-30 | 2014-12-27
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW195SA | 80 CENTRE ST. - SAFE ACCESS, REPLACEMENT OF CATWALKS | 3 | FINAL DESIGN | 2014-12-28 | 2015-06-25 | 2014-12-28 | 2015-06-25
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW195SA | 80 CENTRE ST. - SAFE ACCESS, REPLACEMENT OF CATWALKS | 4 | BID AWARD AND REGISTER CONTRCT | 2015-06-26 | 2015-09-23 | 2015-06-26 | 2015-09-23
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW195SA | 80 CENTRE ST. - SAFE ACCESS, REPLACEMENT OF CATWALKS | 5 | CONSTRUCTION TO 25% | 2015-09-24 | 2016-01-21 | 2015-09-24 | 2016-01-21
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW195SA | 80 CENTRE ST. - SAFE ACCESS, REPLACEMENT OF CATWALKS | 6 | CONSTRUCTION TO 50% | 2016-01-22 | 2016-05-20 | 2016-01-22 | 2016-05-20
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW195SA | 80 CENTRE ST. - SAFE ACCESS, REPLACEMENT OF CATWALKS | 7 | CONSTRUCTION TO 75% | 2016-05-21 | 2016-09-17 | 2016-05-21 | 2016-09-17
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW195SA | 80 CENTRE ST. - SAFE ACCESS, REPLACEMENT OF CATWALKS | 8 | ORIGINAL EQUIP & FURNISHING | 2016-09-18 | 2016-12-16 | 2016-09-18 | 2016-12-16
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW195SA | 80 CENTRE ST. - SAFE ACCESS, REPLACEMENT OF CATWALKS | 9 | SUBSTANTIAL COMPLETION | 2016-12-17 | 2017-02-14 | 2016-12-17 | 2017-02-14
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW195SA | 80 CENTRE ST. - SAFE ACCESS, REPLACEMENT OF CATWALKS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-02-15 | 2017-03-16 | 2017-02-15 | 2018-03-16
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW195SA | 80 CENTRE ST. - SAFE ACCESS, REPLACEMENT OF CATWALKS | 11 | PROJECT START | 2017-02-15 | 2017-03-16 | 2018-03-17 | 2018-03-17
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW195SA | 80 CENTRE ST. - SAFE ACCESS, REPLACEMENT OF CATWALKS | 12 | DESIGN START | 2017-02-15 | 2017-03-16 | 2018-03-18 | 2018-03-18
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW195SA | 80 CENTRE ST. - SAFE ACCESS, REPLACEMENT OF CATWALKS | 13 | DESIGN COMPLETION | 2017-02-15 | 2017-03-16 | 2018-03-19 | 2018-03-19
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW195SA | 80 CENTRE ST. - SAFE ACCESS, REPLACEMENT OF CATWALKS | 14 | CONSTRUCTION START | 2017-02-15 | 2017-03-16 | 2018-03-20 | 2018-03-20
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW195SA | 80 CENTRE ST. - SAFE ACCESS, REPLACEMENT OF CATWALKS | 15 | CONSTRUCTION COMPLETION | 2017-02-15 | 2017-03-16 | 2018-03-21 | 2023-07-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW195SW2 | 80 CENTRE ST. - SIDEWALK REHABILITATION | 1 | PROJECT START | 2014-03-27 | 2014-03-27 | 2012-03-27 | 2012-03-27
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW195SW2 | 80 CENTRE ST. - SIDEWALK REHABILITATION | 2 | DESIGN START | 2014-03-28 | 2014-12-22 | 2012-03-28 | 2012-12-22
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW195SW2 | 80 CENTRE ST. - SIDEWALK REHABILITATION | 3 | DESIGN COMPLETION | 2014-12-23 | 2015-12-22 | 2012-12-23 | 2013-12-22
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW195SW2 | 80 CENTRE ST. - SIDEWALK REHABILITATION | 4 | CONSTRUCTION START | 2015-12-23 | 2016-05-26 | 2013-12-23 | 2014-05-27
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW195SW2 | 80 CENTRE ST. - SIDEWALK REHABILITATION | 5 | CONSTRUCTION COMPLETION | 2016-05-27 | 2017-03-24 | 2015-07-01 | 2023-07-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW29380FC | 80 CENTRE ST.- FIRE ALARMS/SPRINKLERS | 1 | PROJECT START | 2019-08-15 | 2019-08-15 | 2019-08-15 | 2019-08-15
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW29380FC | 80 CENTRE ST.- FIRE ALARMS/SPRINKLERS | 2 | DESIGN START | 2019-08-16 | 2020-08-17 | 2019-08-16 | 2020-08-17
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW29380FC | 80 CENTRE ST.- FIRE ALARMS/SPRINKLERS | 3 | DESIGN COMPLETION | 2020-08-18 | 2021-08-15 | 2020-08-18 | 2021-08-15
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW29380FC | 80 CENTRE ST.- FIRE ALARMS/SPRINKLERS | 4 | CONSTRUCTION START | 2021-08-16 | 2022-05-15 | 2021-08-16 | 2022-05-15
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW29380FC | 80 CENTRE ST.- FIRE ALARMS/SPRINKLERS | 5 | CONSTRUCTION COMPLETION | 2022-05-16 | 2024-05-15 | 2022-05-16 | 2024-05-15
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW316BWY2 | 280 BROADWAY - EXTERIOR | 1 | PROJECT START | 2017-07-01 | 2017-07-01 | 2017-07-01 | 2017-07-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW316BWY2 | 280 BROADWAY - EXTERIOR | 2 | DESIGN START | 2017-07-02 | 2017-11-01 | 2017-07-02 | 2017-11-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW316BWY2 | 280 BROADWAY - EXTERIOR | 3 | DESIGN COMPLETION | 2017-11-02 | 2018-05-20 | 2017-11-02 | 2018-05-20
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW316BWY2 | 280 BROADWAY - EXTERIOR | 4 | CONSTRUCTION START | 2017-04-16 | 2018-11-30 | 2017-04-16 | 2018-11-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW316BWY2 | 280 BROADWAY - EXTERIOR | 5 | CONSTRUCTION COMPLETION | 2018-12-01 | 2024-12-01 | 2018-12-01 | 2024-12-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW3171C | 1 CENTRE STREET- FACADE REHAB | 1 | PROJECT START | 2016-06-30 | 2016-06-30 | 2020-12-28 | 2020-12-28
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW3171C | 1 CENTRE STREET- FACADE REHAB | 2 | DESIGN START | 2016-07-01 | 2016-11-15 | 2020-12-29 | 2021-02-28
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW3171C | 1 CENTRE STREET- FACADE REHAB | 3 | DESIGN COMPLETION | 2016-11-16 | 2017-02-20 | 2021-03-01 | 2022-02-28
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW3171C | 1 CENTRE STREET- FACADE REHAB | 4 | CONSTRUCTION START | 2017-02-21 | 2017-09-30 | 2022-03-01 | 2022-11-28
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW3171C | 1 CENTRE STREET- FACADE REHAB | 5 | CONSTRUCTION COMPLETION | 2017-10-01 | 2021-10-01 | 2022-11-29 | 2026-08-31
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW3172L | 2 LAFAYETTE STREET - FACADE REPAIRS | 1 | PROJECT START | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW3172L | 2 LAFAYETTE STREET - FACADE REPAIRS | 2 | DESIGN START | 2016-07-01 | 2016-12-30 | 2016-07-01 | 2016-12-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW3172L | 2 LAFAYETTE STREET - FACADE REPAIRS | 3 | DESIGN COMPLETION | 2016-12-31 | 2017-04-30 | 2016-12-31 | 2017-04-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW3172L | 2 LAFAYETTE STREET - FACADE REPAIRS | 4 | CONSTRUCTION START | 2017-05-01 | 2017-11-30 | 2017-05-01 | 2017-11-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW3172L | 2 LAFAYETTE STREET - FACADE REPAIRS | 5 | CONSTRUCTION COMPLETION | 2017-12-01 | 2025-12-01 | 2017-12-01 | 2025-12-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW317WOR | 125 WORTH STREET - FACADE REPAIRS | 1 | PROJECT START | 2017-07-01 | 2017-07-01 | 2017-07-01 | 2017-07-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW317WOR | 125 WORTH STREET - FACADE REPAIRS | 2 | DESIGN START | 2017-07-02 | 2017-12-01 | 2017-07-02 | 2017-12-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW317WOR | 125 WORTH STREET - FACADE REPAIRS | 3 | DESIGN COMPLETION | 2017-12-02 | 2018-06-01 | 2017-12-02 | 2018-06-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW317WOR | 125 WORTH STREET - FACADE REPAIRS | 4 | CONSTRUCTION START | 2018-06-02 | 2018-09-01 | 2018-06-02 | 2018-09-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW317WOR | 125 WORTH STREET - FACADE REPAIRS | 5 | CONSTRUCTION COMPLETION | 2018-09-02 | 2024-09-02 | 2018-09-02 | 2024-09-02
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW357ELEV | 253 BROADWAY- ELEVATOR MODERNIZATION | 1 | DEVELOP SCOPE | 2012-06-01 | 2012-08-29 | 2013-12-24 | 2013-12-24
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW357ELEV | 253 BROADWAY- ELEVATOR MODERNIZATION | 2 | PRELIMINARY DESIGN | 2012-08-30 | 2012-12-27 | 2014-05-15 | 2014-05-15
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW357ELEV | 253 BROADWAY- ELEVATOR MODERNIZATION | 3 | FINAL DESIGN | 2012-12-28 | 2013-06-25 | 2015-01-30 | 2015-01-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW357ELEV | 253 BROADWAY- ELEVATOR MODERNIZATION | 4 | BID AWARD AND REGISTER CONTRCT | 2013-06-26 | 2013-09-23 | 2016-07-01 | 2016-07-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW357ELEV | 253 BROADWAY- ELEVATOR MODERNIZATION | 5 | CONSTRUCTION TO 25% | 2013-09-24 | 2014-01-21 | 2017-09-01 | 2020-09-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW357ELEV | 253 BROADWAY- ELEVATOR MODERNIZATION | 6 | CONSTRUCTION TO 50% | 2014-01-22 | 2014-05-21 | 2017-09-01 | 2020-09-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW357ELEV | 253 BROADWAY- ELEVATOR MODERNIZATION | 7 | CONSTRUCTION TO 75% | 2014-05-22 | 2014-09-18 | 2017-09-01 | 2020-09-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW357ELEV | 253 BROADWAY- ELEVATOR MODERNIZATION | 8 | ORIGINAL EQUIP & FURNISHING | 2014-09-19 | 2014-12-17 | 2017-09-01 | 2020-09-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW357ELEV | 253 BROADWAY- ELEVATOR MODERNIZATION | 9 | SUBSTANTIAL COMPLETION | 2014-12-18 | 2015-02-15 | 2017-09-01 | 2020-09-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW357ELEV | 253 BROADWAY- ELEVATOR MODERNIZATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-02-16 | 2015-03-17 | 2017-09-01 | 2020-09-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW357FIRE | 253 BROADWAY- FIRE ALARM REPLACEMENT | 1 | DEVELOP SCOPE | 2011-06-01 | 2011-08-29 | 2016-11-14 | 2016-11-14
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW357FIRE | 253 BROADWAY- FIRE ALARM REPLACEMENT | 2 | PRELIMINARY DESIGN | 2011-08-30 | 2011-12-27 | 2016-11-15 | 2018-11-22
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW357FIRE | 253 BROADWAY- FIRE ALARM REPLACEMENT | 3 | FINAL DESIGN | 2011-12-28 | 2012-06-24 | 2018-11-23 | 2020-01-31
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW357FIRE | 253 BROADWAY- FIRE ALARM REPLACEMENT | 4 | BID AWARD AND REGISTER CONTRCT | 2012-06-25 | 2012-09-22 | 2020-02-01 | 2020-04-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW357FIRE | 253 BROADWAY- FIRE ALARM REPLACEMENT | 5 | CONSTRUCTION TO 25% | 2012-09-23 | 2013-01-20 | 2020-05-01 | 2020-08-28
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW357FIRE | 253 BROADWAY- FIRE ALARM REPLACEMENT | 6 | CONSTRUCTION TO 50% | 2013-01-21 | 2013-05-20 | 2020-08-29 | 2020-12-26
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW357FIRE | 253 BROADWAY- FIRE ALARM REPLACEMENT | 7 | CONSTRUCTION TO 75% | 2013-05-21 | 2013-09-17 | 2020-12-27 | 2021-04-25
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW357FIRE | 253 BROADWAY- FIRE ALARM REPLACEMENT | 8 | ORIGINAL EQUIP & FURNISHING | 2013-09-18 | 2013-12-16 | 2021-04-26 | 2021-07-24
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW357FIRE | 253 BROADWAY- FIRE ALARM REPLACEMENT | 9 | SUBSTANTIAL COMPLETION | 2013-12-17 | 2014-02-14 | 2021-07-25 | 2021-09-22
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW357FIRE | 253 BROADWAY- FIRE ALARM REPLACEMENT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-02-15 | 2014-03-16 | 2021-09-23 | 2023-07-31
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW357FIRE | 253 BROADWAY- FIRE ALARM REPLACEMENT | 11 | PROJECT START | 2014-02-15 | 2014-03-16 | 2023-08-01 | 2023-08-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW357FIRE | 253 BROADWAY- FIRE ALARM REPLACEMENT | 12 | DESIGN START | 2014-02-15 | 2014-03-16 | 2023-08-02 | 2023-08-02
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW357FIRE | 253 BROADWAY- FIRE ALARM REPLACEMENT | 13 | DESIGN COMPLETION | 2014-02-15 | 2014-03-16 | 2023-08-03 | 2023-08-03
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW357FIRE | 253 BROADWAY- FIRE ALARM REPLACEMENT | 14 | CONSTRUCTION START | 2014-02-15 | 2014-03-16 | 2023-08-04 | 2023-08-04
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW357FIRE | 253 BROADWAY- FIRE ALARM REPLACEMENT | 15 | CONSTRUCTION COMPLETION | 2014-02-15 | 2014-03-16 | 2023-08-05 | 2023-08-05
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77102S3 | CITY HALL STEPS RECONSTRUCTION | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-08-29 | 2020-06-01 | 2020-08-29
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77102S3 | CITY HALL STEPS RECONSTRUCTION | 2 | PRELIMINARY DESIGN | 2020-08-30 | 2020-12-27 | 2020-08-30 | 2020-12-27
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77102S3 | CITY HALL STEPS RECONSTRUCTION | 3 | FINAL DESIGN | 2020-12-28 | 2021-06-25 | 2020-12-28 | 2021-06-25
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77102S3 | CITY HALL STEPS RECONSTRUCTION | 4 | BID AWARD AND REGISTER CONTRCT | 2021-06-26 | 2021-09-23 | 2021-06-26 | 2021-09-23
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77102S3 | CITY HALL STEPS RECONSTRUCTION | 5 | CONSTRUCTION TO 25% | 2021-09-24 | 2022-01-21 | 2021-09-24 | 2022-01-21
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77102S3 | CITY HALL STEPS RECONSTRUCTION | 6 | CONSTRUCTION TO 50% | 2022-01-22 | 2022-05-21 | 2022-01-22 | 2022-05-21
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77102S3 | CITY HALL STEPS RECONSTRUCTION | 7 | CONSTRUCTION TO 75% | 2022-05-22 | 2022-09-18 | 2022-05-22 | 2022-09-18
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77102S3 | CITY HALL STEPS RECONSTRUCTION | 8 | ORIGINAL EQUIP & FURNISHING | 2022-09-19 | 2022-12-17 | 2022-09-19 | 2022-12-17
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77102S3 | CITY HALL STEPS RECONSTRUCTION | 9 | SUBSTANTIAL COMPLETION | 2022-12-18 | 2023-02-15 | 2022-12-18 | 2023-02-15
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77102S3 | CITY HALL STEPS RECONSTRUCTION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-02-16 | 2025-03-17 | 2023-02-16 | 2025-03-17
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW7722R | 22 READE STREET EXTERIOR | 1 | PROJECT START | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW7722R | 22 READE STREET EXTERIOR | 2 | DESIGN START | 2016-07-01 | 2016-12-01 | 2016-07-01 | 2016-12-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW7722R | 22 READE STREET EXTERIOR | 3 | DESIGN COMPLETION | 2016-12-02 | 2017-04-01 | 2016-12-02 | 2017-04-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW7722R | 22 READE STREET EXTERIOR | 4 | CONSTRUCTION START | 2017-04-02 | 2017-11-30 | 2017-04-02 | 2017-11-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW7722R | 22 READE STREET EXTERIOR | 5 | CONSTRUCTION COMPLETION | 2017-12-01 | 2024-12-01 | 2017-12-01 | 2024-12-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77CHROT | City Hall Rotunda | 1 | PROJECT START | 2012-05-21 | 2012-05-21 | 2012-05-21 | 2012-05-21
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77CHROT | City Hall Rotunda | 2 | DESIGN START | 2012-05-21 | 2012-05-21 | 2012-05-21 | 2012-05-21
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77CHROT | City Hall Rotunda | 3 | DESIGN COMPLETION | 2012-08-15 | 2012-08-15 | 2012-08-17 | 2012-08-17
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77CHROT | City Hall Rotunda | 4 | CONSTRUCTION START | 2012-10-15 | 2012-10-15 | 2012-11-05 | 2012-11-05
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77CHROT | City Hall Rotunda | 5 | CONSTRUCTION COMPLETION | 2013-10-15 | 2013-10-15 | 2015-06-29 | 2021-07-31
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77GLDA2 | 100 GOLD ST.- MIS HVAC UPGRADES | 1 | DEVELOP SCOPE | 2012-10-03 | 2012-10-03 | 2016-10-03 | 2016-10-03
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77GLDA2 | 100 GOLD ST.- MIS HVAC UPGRADES | 2 | PRELIMINARY DESIGN | 2012-10-04 | 2012-10-04 | 2016-10-03 | 2016-10-03
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77GLDA2 | 100 GOLD ST.- MIS HVAC UPGRADES | 3 | FINAL DESIGN | 2012-10-05 | 2012-10-05 | 2016-10-03 | 2016-10-03
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77GLDA2 | 100 GOLD ST.- MIS HVAC UPGRADES | 4 | BID AWARD AND REGISTER CONTRCT | 2012-10-06 | 2012-10-06 | 2016-10-03 | 2016-10-03
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77GLDA2 | 100 GOLD ST.- MIS HVAC UPGRADES | 5 | CONSTRUCTION TO 25% | 2012-10-07 | 2012-10-07 | 2016-10-03 | 2016-10-03
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77GLDA2 | 100 GOLD ST.- MIS HVAC UPGRADES | 6 | CONSTRUCTION TO 50% | 2012-10-08 | 2012-10-08 | 2016-10-03 | 2016-10-03
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77GLDA2 | 100 GOLD ST.- MIS HVAC UPGRADES | 7 | CONSTRUCTION TO 75% | 2012-10-09 | 2012-10-09 | 2016-10-03 | 2016-10-03
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77GLDA2 | 100 GOLD ST.- MIS HVAC UPGRADES | 8 | ORIGINAL EQUIP & FURNISHING | 2012-10-10 | 2012-10-10 | 2016-10-03 | 2016-10-03
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77GLDA2 | 100 GOLD ST.- MIS HVAC UPGRADES | 9 | SUBSTANTIAL COMPLETION | 2012-10-11 | 2012-10-11 | 2016-10-03 | 2016-10-03
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77GLDA2 | 100 GOLD ST.- MIS HVAC UPGRADES | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-10-12 | 2015-12-31 | 2016-10-03 | 2016-10-03
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77GLDA2 | 100 GOLD ST.- MIS HVAC UPGRADES | 11 | PROJECT START | 2012-10-12 | 2015-12-31 | 2016-10-03 | 2016-10-03
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77GLDA2 | 100 GOLD ST.- MIS HVAC UPGRADES | 12 | DESIGN START | 2012-10-12 | 2015-12-31 | 2016-10-03 | 2016-10-03
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77GLDA2 | 100 GOLD ST.- MIS HVAC UPGRADES | 13 | DESIGN COMPLETION | 2012-10-12 | 2015-12-31 | 2016-10-03 | 2016-10-03
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77GLDA2 | 100 GOLD ST.- MIS HVAC UPGRADES | 14 | CONSTRUCTION START | 2012-10-12 | 2015-12-31 | 2016-10-04 | 2016-10-04
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77GLDA2 | 100 GOLD ST.- MIS HVAC UPGRADES | 15 | CONSTRUCTION COMPLETION | 2012-10-12 | 2015-12-31 | 2016-10-05 | 2021-07-05
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77GLDWN | 100 GOLD ST.- WINDOW REPLACEMENT AND EXTERIOR REHABILITATION | 1 | DEVELOP SCOPE | 2014-06-01 | 2014-08-29 | 2017-07-01 | 2017-09-28
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77GLDWN | 100 GOLD ST.- WINDOW REPLACEMENT AND EXTERIOR REHABILITATION | 2 | PRELIMINARY DESIGN | 2014-08-30 | 2014-12-27 | 2017-09-29 | 2018-01-26
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77GLDWN | 100 GOLD ST.- WINDOW REPLACEMENT AND EXTERIOR REHABILITATION | 3 | FINAL DESIGN | 2014-12-28 | 2015-06-25 | 2018-01-27 | 2018-07-25
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77GLDWN | 100 GOLD ST.- WINDOW REPLACEMENT AND EXTERIOR REHABILITATION | 4 | BID AWARD AND REGISTER CONTRCT | 2015-06-26 | 2015-09-23 | 2018-07-26 | 2018-10-23
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77GLDWN | 100 GOLD ST.- WINDOW REPLACEMENT AND EXTERIOR REHABILITATION | 5 | CONSTRUCTION TO 25% | 2015-09-24 | 2016-01-21 | 2018-10-24 | 2019-02-20
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77GLDWN | 100 GOLD ST.- WINDOW REPLACEMENT AND EXTERIOR REHABILITATION | 6 | CONSTRUCTION TO 50% | 2016-01-22 | 2016-05-20 | 2019-02-21 | 2019-06-20
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77GLDWN | 100 GOLD ST.- WINDOW REPLACEMENT AND EXTERIOR REHABILITATION | 7 | CONSTRUCTION TO 75% | 2016-05-21 | 2016-09-17 | 2019-06-21 | 2019-10-18
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77GLDWN | 100 GOLD ST.- WINDOW REPLACEMENT AND EXTERIOR REHABILITATION | 8 | ORIGINAL EQUIP & FURNISHING | 2016-09-18 | 2016-12-16 | 2019-10-19 | 2020-01-16
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77GLDWN | 100 GOLD ST.- WINDOW REPLACEMENT AND EXTERIOR REHABILITATION | 9 | SUBSTANTIAL COMPLETION | 2016-12-17 | 2017-02-14 | 2020-01-17 | 2020-03-16
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77GLDWN | 100 GOLD ST.- WINDOW REPLACEMENT AND EXTERIOR REHABILITATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-02-15 | 2017-03-16 | 2020-03-17 | 2025-08-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77GLDWN | 100 GOLD ST.- WINDOW REPLACEMENT AND EXTERIOR REHABILITATION | 11 | PROJECT START | 2017-02-15 | 2017-03-16 | 2025-08-31 | 2025-08-31
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77GLDWN | 100 GOLD ST.- WINDOW REPLACEMENT AND EXTERIOR REHABILITATION | 12 | DESIGN START | 2017-02-15 | 2017-03-16 | 2025-09-01 | 2025-09-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77GLDWN | 100 GOLD ST.- WINDOW REPLACEMENT AND EXTERIOR REHABILITATION | 13 | DESIGN COMPLETION | 2017-02-15 | 2017-03-16 | 2025-09-02 | 2025-09-02
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77GLDWN | 100 GOLD ST.- WINDOW REPLACEMENT AND EXTERIOR REHABILITATION | 14 | CONSTRUCTION START | 2017-02-15 | 2017-03-16 | 2025-09-03 | 2025-09-03
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77GLDWN | 100 GOLD ST.- WINDOW REPLACEMENT AND EXTERIOR REHABILITATION | 15 | CONSTRUCTION COMPLETION | 2017-02-15 | 2017-03-16 | 2025-09-04 | 2029-09-04
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77LYA | 253 BROADWAY- LPC MOVE TO 2nd, 11th, 12th, 13th FLS | 1 | PROJECT START | 2012-06-15 | 2012-06-15 | 2014-06-15 | 2014-06-15
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77LYA | 253 BROADWAY- LPC MOVE TO 2nd, 11th, 12th, 13th FLS | 2 | DESIGN START | 2013-01-23 | 2013-01-23 | 2014-06-16 | 2015-06-17
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77LYA | 253 BROADWAY- LPC MOVE TO 2nd, 11th, 12th, 13th FLS | 3 | DESIGN COMPLETION | 2013-12-06 | 2013-12-06 | 2015-06-18 | 2017-06-18
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77LYA | 253 BROADWAY- LPC MOVE TO 2nd, 11th, 12th, 13th FLS | 4 | CONSTRUCTION START | 2015-04-15 | 2015-04-15 | 2017-06-19 | 2019-06-19
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77LYA | 253 BROADWAY- LPC MOVE TO 2nd, 11th, 12th, 13th FLS | 5 | CONSTRUCTION COMPLETION | 2016-06-15 | 2016-06-15 | 2020-10-02 | 2027-10-03
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW80DYCD2 | 2 LAFAYETTE STREET- DYCD RELOCATION | 1 | PROJECT START | 2011-10-26 | 2011-10-26 | 2011-10-26 | 2011-10-26
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW80DYCD2 | 2 LAFAYETTE STREET- DYCD RELOCATION | 2 | DESIGN START | 2012-01-09 | 2012-01-09 | 2012-01-09 | 2012-01-09
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW80DYCD2 | 2 LAFAYETTE STREET- DYCD RELOCATION | 3 | DESIGN COMPLETION | 2012-08-27 | 2012-08-27 | 2012-09-28 | 2012-09-28
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW80DYCD2 | 2 LAFAYETTE STREET- DYCD RELOCATION | 4 | CONSTRUCTION START | 2013-01-02 | 2013-01-02 | 2013-04-25 | 2014-04-25
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW80DYCD2 | 2 LAFAYETTE STREET- DYCD RELOCATION | 5 | CONSTRUCTION COMPLETION | 2013-12-20 | 2013-12-20 | 2014-10-31 | 2021-07-05
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PWD005FS | FORTUNE SOCIETY | 1 | PROJECT START | 2008-04-30 | 2008-04-30 | 2015-07-01 | 2016-07-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PWD005FS | FORTUNE SOCIETY | 2 | DESIGN START | 2008-05-01 | 2008-05-01 | 2016-07-02 | 2016-07-02
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PWD005FS | FORTUNE SOCIETY | 3 | DESIGN COMPLETION | 2008-05-02 | 2008-05-02 | 2016-07-03 | 2018-07-03
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PWD005FS | FORTUNE SOCIETY | 4 | CONSTRUCTION START | 2008-05-03 | 2008-05-03 | 2018-07-04 | 2020-07-04
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PWD005FS | FORTUNE SOCIETY | 5 | CONSTRUCTION COMPLETION | 2008-05-04 | 2008-05-04 | 2020-07-05 | 2022-07-05
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PWD005NEW | NONTRADITIONAL EMPLOYMENT FOR WOMEN | 1 | PROJECT START | 2005-04-26 | 2005-04-26 | 2009-02-20 | 2009-08-31
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PWD005NEW | NONTRADITIONAL EMPLOYMENT FOR WOMEN | 2 | DESIGN START | 2006-01-18 | 2006-01-18 | 2009-09-01 | 2010-09-02
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PWD005NEW | NONTRADITIONAL EMPLOYMENT FOR WOMEN | 3 | DESIGN COMPLETION | 2006-07-17 | 2006-07-17 | 2011-06-16 | 2014-01-02
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PWD005NEW | NONTRADITIONAL EMPLOYMENT FOR WOMEN | 4 | CONSTRUCTION START | 2006-12-15 | 2006-12-15 | 2016-01-03 | 2018-02-24
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PWD005NEW | NONTRADITIONAL EMPLOYMENT FOR WOMEN | 5 | CONSTRUCTION COMPLETION | 2007-08-15 | 2007-08-15 | 2018-02-25 | 2026-08-31
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | S195-227S | Spring St Salt Enclosure | 1 | PROJECT START | 2013-06-01 | 2013-06-01 | 2013-06-01 | 2013-06-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | S195-227S | Spring St Salt Enclosure | 2 | DESIGN START | 2013-06-02 | 2013-06-02 | 2013-06-02 | 2013-06-02
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | S195-227S | Spring St Salt Enclosure | 3 | DESIGN COMPLETION | 2013-06-03 | 2013-06-03 | 2013-06-03 | 2014-04-09
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | S195-227S | Spring St Salt Enclosure | 4 | CONSTRUCTION START | 2013-06-04 | 2013-06-04 | 2014-04-10 | 2014-04-10
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | S195-227S | Spring St Salt Enclosure | 5 | CONSTRUCTION COMPLETION | 2013-06-05 | 2014-06-05 | 2014-04-11 | 2020-07-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | S216-401A | EAST 91st ST MARINE TRANSFER STATION | 1 | PROJECT START | 2011-09-01 | 2011-09-01 | 2011-09-01 | 2011-09-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | S216-401A | EAST 91st ST MARINE TRANSFER STATION | 2 | DESIGN START | 2011-09-02 | 2012-09-02 | 2011-09-02 | 2012-09-02
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | S216-401A | EAST 91st ST MARINE TRANSFER STATION | 3 | DESIGN COMPLETION | 2012-09-03 | 2013-09-02 | 2012-09-03 | 2013-09-02
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | S216-401A | EAST 91st ST MARINE TRANSFER STATION | 4 | CONSTRUCTION START | 2013-09-03 | 2014-09-02 | 2013-09-03 | 2014-09-02
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | S216-401A | EAST 91st ST MARINE TRANSFER STATION | 5 | CONSTRUCTION COMPLETION | 2014-09-03 | 2015-09-03 | 2014-09-03 | 2020-07-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | S216-401R | CONSTRUCTION, E. 92 ST RAMP TO E. 91 ST MTS | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-12-27 | 2015-07-01 | 2015-12-27
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | S216-401R | CONSTRUCTION, E. 92 ST RAMP TO E. 91 ST MTS | 2 | PRELIMINARY DESIGN | 2015-12-28 | 2016-12-26 | 2015-12-28 | 2016-12-26
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | S216-401R | CONSTRUCTION, E. 92 ST RAMP TO E. 91 ST MTS | 3 | FINAL DESIGN | 2016-12-27 | 2017-12-26 | 2016-12-27 | 2017-12-26
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | S216-401R | CONSTRUCTION, E. 92 ST RAMP TO E. 91 ST MTS | 4 | BID AWARD AND REGISTER CONTRCT | 2017-12-27 | 2018-06-24 | 2017-12-27 | 2018-06-24
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | S216-401R | CONSTRUCTION, E. 92 ST RAMP TO E. 91 ST MTS | 5 | CONSTRUCTION TO 25% | 2018-06-25 | 2019-06-24 | 2018-06-25 | 2019-06-24
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | S216-401R | CONSTRUCTION, E. 92 ST RAMP TO E. 91 ST MTS | 6 | CONSTRUCTION TO 50% | 2019-06-25 | 2020-06-23 | 2019-06-25 | 2020-06-23
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | S216-401R | CONSTRUCTION, E. 92 ST RAMP TO E. 91 ST MTS | 7 | CONSTRUCTION TO 75% | 2020-06-24 | 2021-06-23 | 2020-06-24 | 2021-06-23
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | S216-401R | CONSTRUCTION, E. 92 ST RAMP TO E. 91 ST MTS | 8 | SUBSTANTIAL COMPLETION | 2021-06-24 | 2022-06-23 | 2021-06-24 | 2021-06-25
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | S216-401R | CONSTRUCTION, E. 92 ST RAMP TO E. 91 ST MTS | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-06-24 | 2023-06-23 | 2021-06-26 | 2028-07-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | S216-404A | GANSEVOORT MARINE TRANSFER STATION | 1 | PROJECT START | 2011-09-01 | 2011-09-01 | 2011-09-01 | 2011-09-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | S216-404A | GANSEVOORT MARINE TRANSFER STATION | 2 | DESIGN START | 2011-09-02 | 2012-09-02 | 2012-10-09 | 2013-08-05
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | S216-404A | GANSEVOORT MARINE TRANSFER STATION | 3 | DESIGN COMPLETION | 2012-09-03 | 2013-09-02 | 2013-08-06 | 2014-04-04
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | S216-404A | GANSEVOORT MARINE TRANSFER STATION | 4 | CONSTRUCTION START | 2013-09-03 | 2014-09-02 | 2014-04-05 | 2015-03-23
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | S216-404A | GANSEVOORT MARINE TRANSFER STATION | 5 | CONSTRUCTION COMPLETION | 2014-09-03 | 2015-09-03 | 2015-03-24 | 2028-04-15
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | S216-415A | WEST 59th STREET MTS | 1 | PROJECT START | 2011-09-01 | 2011-09-01 | 2011-09-01 | 2011-09-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | S216-415A | WEST 59th STREET MTS | 2 | DESIGN START | 2011-09-02 | 2011-09-03 | 2011-09-02 | 2011-09-03
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | S216-415A | WEST 59th STREET MTS | 3 | DESIGN COMPLETION | 2011-09-04 | 2012-09-03 | 2011-09-04 | 2012-09-03
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | S216-415A | WEST 59th STREET MTS | 4 | CONSTRUCTION START | 2012-09-04 | 2013-09-03 | 2012-09-04 | 2013-09-03
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | S216-415A | WEST 59th STREET MTS | 5 | CONSTRUCTION COMPLETION | 2013-09-04 | 2014-09-04 | 2013-09-04 | 2020-08-27
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | S219-233A | CONSTRUCTION MANHATTAN 1/2/5 GARAGE | 1 | PROJECT START | 2011-09-01 | 2011-09-01 | 2011-09-01 | 2011-09-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | S219-233A | CONSTRUCTION MANHATTAN 1/2/5 GARAGE | 2 | DESIGN START | 2011-09-02 | 2011-09-02 | 2011-09-02 | 2011-09-02
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | S219-233A | CONSTRUCTION MANHATTAN 1/2/5 GARAGE | 3 | DESIGN COMPLETION | 2011-09-03 | 2011-09-03 | 2011-09-03 | 2011-09-03
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | S219-233A | CONSTRUCTION MANHATTAN 1/2/5 GARAGE | 4 | CONSTRUCTION START | 2011-09-04 | 2011-09-04 | 2011-09-04 | 2011-09-04
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | S219-233A | CONSTRUCTION MANHATTAN 1/2/5 GARAGE | 5 | CONSTRUCTION COMPLETION | 2011-09-05 | 2011-09-05 | 2011-09-05 | 2026-06-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBHFW | Sandy: Bellevue Flood Wall | 1 | DESIGN | 2021-04-20 | 2022-09-11 | 2021-04-20 | 2022-09-11
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBHFW | Sandy: Bellevue Flood Wall | 2 | CONSTRUCTION | 2022-09-12 | 2024-09-10 | 2022-09-12 | 2024-09-10
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBHFW | Sandy: Bellevue Flood Wall | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-09-11 | 2024-12-09 | 2024-09-11 | 2024-12-09
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW06 | Reconstruction of Vestry Street- Hurricane Sandy | 1 | DEVELOP SCOPE | 2014-09-01 | 2014-11-29 | 2014-02-18 | 2015-03-16
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW06 | Reconstruction of Vestry Street- Hurricane Sandy | 2 | PRELIMINARY DESIGN | 2014-11-30 | 2016-03-29 | 2015-03-17 | 2015-10-07
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW06 | Reconstruction of Vestry Street- Hurricane Sandy | 3 | FINAL DESIGN | 2016-03-30 | 2017-01-31 | 2015-10-08 | 2016-09-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW06 | Reconstruction of Vestry Street- Hurricane Sandy | 4 | BID AWARD AND REGISTER CONTRCT | 2017-02-01 | 2017-06-01 | 2016-10-01 | 2019-07-14
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW06 | Reconstruction of Vestry Street- Hurricane Sandy | 5 | CONSTRUCTION TO 25% | 2017-06-02 | 2017-09-29 | 2019-07-15 | 2019-11-11
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW06 | Reconstruction of Vestry Street- Hurricane Sandy | 6 | CONSTRUCTION TO 50% | 2017-06-02 | 2017-09-29 | 2017-06-02 | 2017-09-29
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW06 | Reconstruction of Vestry Street- Hurricane Sandy | 7 | CONSTRUCTION TO 75% | 2017-06-02 | 2017-09-29 | 2017-06-02 | 2017-09-29
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW06 | Reconstruction of Vestry Street- Hurricane Sandy | 8 | ORIGINAL EQUIP & FURNISHING | 2017-09-30 | 2017-12-28 | 2017-09-30 | 2017-12-28
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW06 | Reconstruction of Vestry Street- Hurricane Sandy | 9 | SUBSTANTIAL COMPLETION | 2017-12-29 | 2018-02-26 | 2017-12-29 | 2018-02-26
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW06 | Reconstruction of Vestry Street- Hurricane Sandy | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-02-27 | 2018-03-28 | 2018-02-27 | 2024-06-11
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW08 | Reconstruction of Front Street-Hurricane Sandy | 1 | DEVELOP SCOPE | 2016-02-17 | 2016-05-16 | 2016-02-17 | 2016-05-16
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW08 | Reconstruction of Front Street-Hurricane Sandy | 2 | PRELIMINARY DESIGN | 2016-05-17 | 2016-09-13 | 2016-05-17 | 2016-09-13
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW08 | Reconstruction of Front Street-Hurricane Sandy | 3 | FINAL DESIGN | 2016-09-14 | 2017-03-12 | 2016-09-14 | 2017-03-12
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW08 | Reconstruction of Front Street-Hurricane Sandy | 4 | BID AWARD AND REGISTER CONTRCT | 2017-03-13 | 2017-06-10 | 2017-03-13 | 2017-06-10
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW08 | Reconstruction of Front Street-Hurricane Sandy | 5 | CONSTRUCTION TO 25% | 2017-06-11 | 2017-10-08 | 2017-06-11 | 2017-10-08
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW08 | Reconstruction of Front Street-Hurricane Sandy | 6 | CONSTRUCTION TO 50% | 2017-10-09 | 2018-02-05 | 2017-10-09 | 2018-02-05
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW08 | Reconstruction of Front Street-Hurricane Sandy | 7 | CONSTRUCTION TO 75% | 2018-02-06 | 2018-06-05 | 2018-02-06 | 2018-06-05
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW08 | Reconstruction of Front Street-Hurricane Sandy | 8 | ORIGINAL EQUIP & FURNISHING | 2018-06-06 | 2018-09-03 | 2018-06-06 | 2018-09-03
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW08 | Reconstruction of Front Street-Hurricane Sandy | 9 | SUBSTANTIAL COMPLETION | 2018-09-04 | 2018-11-02 | 2018-09-04 | 2018-11-02
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW08 | Reconstruction of Front Street-Hurricane Sandy | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-11-03 | 2018-12-02 | 2018-11-03 | 2025-01-08
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDSLIP | 100 OLD SLIP RESTORATION & SYSTEMS REPLACEMENT | 1 | DESIGN | 2019-09-01 | 2020-02-27 | 2019-09-01 | 2020-02-27
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDSLIP | 100 OLD SLIP RESTORATION & SYSTEMS REPLACEMENT | 2 | BID AWARD AND REGISTER CONTRCT | 2020-02-28 | 2020-05-27 | 2020-02-28 | 2020-05-27
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDSLIP | 100 OLD SLIP RESTORATION & SYSTEMS REPLACEMENT | 3 | CONSTRUCTION | 2020-05-28 | 2021-05-27 | 2020-05-28 | 2021-05-27
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDSLIP | 100 OLD SLIP RESTORATION & SYSTEMS REPLACEMENT | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-05-28 | 2022-04-23 | 2021-05-28 | 2022-04-23
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002152 | COMBINE SEWERS IN WORTH ST | 1 | DEVELOP SCOPE | 2009-02-13 | 2009-05-13 | 2009-02-13 | 2009-05-13
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002152 | COMBINE SEWERS IN WORTH ST | 2 | PRELIMINARY DESIGN | 2009-05-14 | 2009-09-10 | 2009-05-14 | 2009-09-10
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002152 | COMBINE SEWERS IN WORTH ST | 3 | FINAL DESIGN | 2009-09-11 | 2010-03-09 | 2009-09-11 | 2010-03-09
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002152 | COMBINE SEWERS IN WORTH ST | 4 | BID AWARD AND REGISTER CONTRCT | 2010-03-10 | 2010-06-07 | 2013-03-08 | 2013-06-05
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002152 | COMBINE SEWERS IN WORTH ST | 5 | CONSTRUCTION TO 25% | 2010-06-08 | 2010-10-05 | 2013-06-06 | 2013-06-05
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002152 | COMBINE SEWERS IN WORTH ST | 6 | CONSTRUCTION TO 50% | 2010-10-06 | 2011-02-02 | 2013-06-06 | 2013-06-05
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002152 | COMBINE SEWERS IN WORTH ST | 7 | CONSTRUCTION TO 75% | 2011-02-03 | 2011-06-02 | 2013-06-06 | 2013-06-05
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002152 | COMBINE SEWERS IN WORTH ST | 8 | ORIGINAL EQUIP & FURNISHING | 2011-06-03 | 2011-08-31 | 2013-06-06 | 2013-06-05
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002152 | COMBINE SEWERS IN WORTH ST | 9 | SUBSTANTIAL COMPLETION | 2011-09-01 | 2011-10-30 | 2013-06-06 | 2013-06-05
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002152 | COMBINE SEWERS IN WORTH ST | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2011-10-31 | 2011-11-29 | 2013-06-06 | 2021-06-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002153 | Water Main in Water St. (w/HWMWTCA7D) | 1 | DEVELOP SCOPE | 2004-01-16 | 2004-04-14 | 2004-01-16 | 2004-04-14
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002153 | Water Main in Water St. (w/HWMWTCA7D) | 2 | PRELIMINARY DESIGN | 2004-04-15 | 2004-08-12 | 2004-04-15 | 2004-08-12
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002153 | Water Main in Water St. (w/HWMWTCA7D) | 3 | FINAL DESIGN | 2004-08-13 | 2005-02-08 | 2004-08-13 | 2005-02-08
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002153 | Water Main in Water St. (w/HWMWTCA7D) | 4 | BID AWARD AND REGISTER CONTRCT | 2007-03-01 | 2007-06-01 | 2011-03-28 | 2011-06-28
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002153 | Water Main in Water St. (w/HWMWTCA7D) | 5 | CONSTRUCTION TO 25% | 2007-06-02 | 2007-06-01 | 2011-06-29 | 2011-06-28
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002153 | Water Main in Water St. (w/HWMWTCA7D) | 6 | CONSTRUCTION TO 50% | 2007-06-02 | 2007-06-01 | 2011-06-29 | 2011-06-28
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002153 | Water Main in Water St. (w/HWMWTCA7D) | 7 | CONSTRUCTION TO 75% | 2007-06-02 | 2007-06-01 | 2011-06-29 | 2011-06-28
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002153 | Water Main in Water St. (w/HWMWTCA7D) | 8 | ORIGINAL EQUIP & FURNISHING | 2007-06-02 | 2007-06-01 | 2011-06-29 | 2011-06-28
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002153 | Water Main in Water St. (w/HWMWTCA7D) | 9 | SUBSTANTIAL COMPLETION | 2007-06-02 | 2007-06-01 | 2011-06-29 | 2011-06-28
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002153 | Water Main in Water St. (w/HWMWTCA7D) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2007-06-02 | 2007-07-01 | 2011-06-29 | 2022-06-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002157 | Replacement of Combined Sewer in E. 26th Street, Manhattan | 1 | DEVELOP SCOPE | 2009-02-22 | 2009-05-22 | 2009-02-22 | 2009-05-22
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002157 | Replacement of Combined Sewer in E. 26th Street, Manhattan | 2 | PRELIMINARY DESIGN | 2009-05-23 | 2009-09-19 | 2009-05-23 | 2009-09-19
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002157 | Replacement of Combined Sewer in E. 26th Street, Manhattan | 3 | FINAL DESIGN | 2009-09-20 | 2010-03-18 | 2009-09-20 | 2010-03-18
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002157 | Replacement of Combined Sewer in E. 26th Street, Manhattan | 4 | BID AWARD AND REGISTER CONTRCT | 2010-03-19 | 2010-06-16 | 2016-05-27 | 2016-06-25
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002157 | Replacement of Combined Sewer in E. 26th Street, Manhattan | 5 | CONSTRUCTION TO 25% | 2010-06-17 | 2010-10-14 | 2016-06-26 | 2016-06-25
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002157 | Replacement of Combined Sewer in E. 26th Street, Manhattan | 6 | CONSTRUCTION TO 50% | 2010-10-15 | 2011-02-11 | 2016-06-26 | 2016-06-25
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002157 | Replacement of Combined Sewer in E. 26th Street, Manhattan | 7 | CONSTRUCTION TO 75% | 2011-02-12 | 2011-06-11 | 2016-06-26 | 2016-06-25
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002157 | Replacement of Combined Sewer in E. 26th Street, Manhattan | 8 | ORIGINAL EQUIP & FURNISHING | 2011-06-12 | 2011-09-09 | 2016-06-26 | 2016-06-25
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002157 | Replacement of Combined Sewer in E. 26th Street, Manhattan | 9 | SUBSTANTIAL COMPLETION | 2011-09-10 | 2011-11-08 | 2016-06-26 | 2016-06-25
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002157 | Replacement of Combined Sewer in E. 26th Street, Manhattan | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2011-11-09 | 2011-12-08 | 2017-12-27 | 2020-10-14
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002161 | Water main & Sewer work in Broadway b/t Leonard & Cortlandt | 1 | DEVELOP SCOPE | 2009-02-12 | 2009-05-12 | 2009-02-12 | 2009-05-12
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002161 | Water main & Sewer work in Broadway b/t Leonard & Cortlandt | 2 | PRELIMINARY DESIGN | 2009-05-13 | 2009-09-09 | 2009-05-13 | 2009-09-09
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002161 | Water main & Sewer work in Broadway b/t Leonard & Cortlandt | 3 | FINAL DESIGN | 2009-09-10 | 2010-03-08 | 2009-09-10 | 2010-03-08
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002161 | Water main & Sewer work in Broadway b/t Leonard & Cortlandt | 4 | BID AWARD AND REGISTER CONTRCT | 2010-03-09 | 2010-06-06 | 2013-03-16 | 2013-06-13
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002161 | Water main & Sewer work in Broadway b/t Leonard & Cortlandt | 5 | CONSTRUCTION TO 25% | 2010-06-07 | 2010-10-04 | 2013-06-14 | 2013-06-13
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002161 | Water main & Sewer work in Broadway b/t Leonard & Cortlandt | 6 | CONSTRUCTION TO 50% | 2010-10-05 | 2011-02-01 | 2013-06-14 | 2013-06-13
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002161 | Water main & Sewer work in Broadway b/t Leonard & Cortlandt | 7 | CONSTRUCTION TO 75% | 2011-02-02 | 2011-06-01 | 2013-06-14 | 2013-06-13
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002161 | Water main & Sewer work in Broadway b/t Leonard & Cortlandt | 8 | ORIGINAL EQUIP & FURNISHING | 2011-06-02 | 2011-08-30 | 2013-06-14 | 2013-06-13
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002161 | Water main & Sewer work in Broadway b/t Leonard & Cortlandt | 9 | SUBSTANTIAL COMPLETION | 2011-08-31 | 2011-10-29 | 2013-06-14 | 2013-06-13
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002161 | Water main & Sewer work in Broadway b/t Leonard & Cortlandt | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2011-10-30 | 2011-11-28 | 2013-06-14 | 2021-06-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002169 | RECON OF COMBINED SEWER & WM IN YORK AVE | 1 | DEVELOP SCOPE | 2011-01-01 | 2011-03-31 | 1913-07-25 | 1913-10-22
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002169 | RECON OF COMBINED SEWER & WM IN YORK AVE | 2 | PRELIMINARY DESIGN | 2011-04-01 | 2011-07-29 | 1913-10-23 | 1914-02-19
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002169 | RECON OF COMBINED SEWER & WM IN YORK AVE | 3 | FINAL DESIGN | 2011-07-30 | 2012-01-25 | 1914-02-20 | 1914-08-18
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002169 | RECON OF COMBINED SEWER & WM IN YORK AVE | 4 | BID AWARD AND REGISTER CONTRCT | 2012-01-26 | 2012-04-24 | 2022-03-28 | 2022-06-25
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002169 | RECON OF COMBINED SEWER & WM IN YORK AVE | 5 | CONSTRUCTION TO 25% | 2012-04-25 | 2012-08-22 | 2022-06-26 | 2022-06-25
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002169 | RECON OF COMBINED SEWER & WM IN YORK AVE | 6 | CONSTRUCTION TO 50% | 2012-08-23 | 2012-12-20 | 2022-06-26 | 2022-06-25
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002169 | RECON OF COMBINED SEWER & WM IN YORK AVE | 7 | CONSTRUCTION TO 75% | 2012-12-21 | 2013-04-19 | 2022-06-26 | 2022-06-25
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002169 | RECON OF COMBINED SEWER & WM IN YORK AVE | 8 | ORIGINAL EQUIP & FURNISHING | 2013-04-20 | 2013-07-18 | 2022-06-26 | 2022-06-25
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002169 | RECON OF COMBINED SEWER & WM IN YORK AVE | 9 | SUBSTANTIAL COMPLETION | 2013-07-19 | 2013-09-16 | 2022-06-26 | 2022-06-25
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002169 | RECON OF COMBINED SEWER & WM IN YORK AVE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-09-17 | 2013-10-16 | 2023-06-26 | 2024-07-25
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002178 | Replacement & guniting comb SE in W. Broadway | 1 | DEVELOP SCOPE | 2018-05-10 | 2018-08-07 | 2018-05-10 | 2018-08-07
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002178 | Replacement & guniting comb SE in W. Broadway | 2 | PRELIMINARY DESIGN | 2018-08-08 | 2018-12-05 | 2018-08-08 | 2018-12-05
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002178 | Replacement & guniting comb SE in W. Broadway | 3 | FINAL DESIGN | 2018-12-06 | 2019-06-03 | 2018-12-06 | 2019-06-03
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002178 | Replacement & guniting comb SE in W. Broadway | 4 | BID AWARD AND REGISTER CONTRCT | 2019-06-04 | 2019-09-01 | 2019-06-04 | 2019-09-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002178 | Replacement & guniting comb SE in W. Broadway | 5 | CONSTRUCTION TO 25% | 2019-09-02 | 2019-12-30 | 2019-09-02 | 2019-12-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002178 | Replacement & guniting comb SE in W. Broadway | 6 | CONSTRUCTION TO 50% | 2019-12-31 | 2020-04-28 | 2019-12-31 | 2020-04-28
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002178 | Replacement & guniting comb SE in W. Broadway | 7 | CONSTRUCTION TO 75% | 2020-04-29 | 2020-08-26 | 2020-04-29 | 2020-08-26
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002178 | Replacement & guniting comb SE in W. Broadway | 8 | ORIGINAL EQUIP & FURNISHING | 2020-08-27 | 2020-11-24 | 2020-08-27 | 2020-11-24
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002178 | Replacement & guniting comb SE in W. Broadway | 9 | SUBSTANTIAL COMPLETION | 2020-11-25 | 2021-01-23 | 2020-11-25 | 2021-01-23
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002178 | Replacement & guniting comb SE in W. Broadway | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-01-24 | 2021-02-22 | 2021-01-24 | 2021-02-22
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | TAVREH | Tavern on the Green Structure | 1 | PROJECT START | 2011-06-01 | 2011-06-01 | 2011-06-01 | 2011-06-01
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | TAVREH | Tavern on the Green Structure | 2 | DESIGN START | 2011-09-12 | 2012-04-11 | 2011-09-12 | 2011-09-12
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | TAVREH | Tavern on the Green Structure | 3 | DESIGN COMPLETION | 2012-04-12 | 2012-04-11 | 2011-09-13 | 2021-05-31
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | TAVREH | Tavern on the Green Structure | 4 | CONSTRUCTION START | 2012-04-12 | 2012-04-11 | 2021-06-01 | 2021-08-26
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | TAVREH | Tavern on the Green Structure | 5 | CONSTRUCTION COMPLETION | 2013-04-12 | 2013-04-12 | 2013-04-12 | 2024-06-30
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | TF18-2007 | DELANCEY AND ESSEX MUNICIPAL PARKING GARAGE,MANHATTAN | 1 | BID AWARD AND REGISTER CONTRCT | 2008-06-30 | 2008-06-30 | 2014-02-10 | 2014-02-10
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | TF18-2007 | DELANCEY AND ESSEX MUNICIPAL PARKING GARAGE,MANHATTAN | 2 | CONSTRUCTION START | 2008-07-01 | 2008-08-14 | 2014-02-11 | 2016-06-02
20201123 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | TF18-2007 | DELANCEY AND ESSEX MUNICIPAL PARKING GARAGE,MANHATTAN | 3 | CONSTRUCTION COMPLETION | 2008-08-15 | 2010-03-07 | 2016-06-03 | 2023-07-13
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | 70MULB1 | 70 MULBERRY - DEMOLITION | 1 | DEVELOP SCOPE | 2020-05-01 | 2020-07-29 | 2020-05-01 | 2020-07-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | 70MULB1 | 70 MULBERRY - DEMOLITION | 2 | PRELIMINARY DESIGN | 2020-07-30 | 2020-11-26 | 2020-07-30 | 2020-11-26
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | 70MULB1 | 70 MULBERRY - DEMOLITION | 3 | FINAL DESIGN | 2020-11-27 | 2021-05-25 | 2020-11-27 | 2021-05-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | 70MULB1 | 70 MULBERRY - DEMOLITION | 4 | BID AWARD AND REGISTER CONTRCT | 2021-05-26 | 2021-08-23 | 2021-05-26 | 2021-08-23
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | 70MULB1 | 70 MULBERRY - DEMOLITION | 5 | CONSTRUCTION TO 25% | 2021-08-24 | 2021-12-21 | 2021-08-24 | 2021-12-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | 70MULB1 | 70 MULBERRY - DEMOLITION | 6 | CONSTRUCTION TO 50% | 2021-12-22 | 2022-04-20 | 2021-12-22 | 2022-04-20
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | 70MULB1 | 70 MULBERRY - DEMOLITION | 7 | CONSTRUCTION TO 75% | 2022-04-21 | 2022-08-18 | 2022-04-21 | 2022-08-18
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | 70MULB1 | 70 MULBERRY - DEMOLITION | 8 | ORIGINAL EQUIP & FURNISHING | 2022-08-19 | 2022-11-16 | 2022-08-19 | 2022-11-16
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | 70MULB1 | 70 MULBERRY - DEMOLITION | 9 | SUBSTANTIAL COMPLETION | 2022-11-17 | 2023-01-15 | 2022-11-17 | 2023-01-15
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | 70MULB1 | 70 MULBERRY - DEMOLITION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-01-16 | 2023-02-14 | 2023-01-16 | 2023-02-14
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | 70MULBREC | 70 MULBERRY STREET - RECONSTRUCTION | 1 | DEVELOP SCOPE | 2021-06-01 | 2021-08-29 | 2021-06-01 | 2021-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | 70MULBREC | 70 MULBERRY STREET - RECONSTRUCTION | 2 | PRELIMINARY DESIGN | 2021-08-30 | 2021-12-27 | 2021-08-30 | 2021-12-27
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | 70MULBREC | 70 MULBERRY STREET - RECONSTRUCTION | 3 | FINAL DESIGN | 2021-12-28 | 2022-06-25 | 2021-12-28 | 2022-06-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | 70MULBREC | 70 MULBERRY STREET - RECONSTRUCTION | 4 | BID AWARD AND REGISTER CONTRCT | 2022-06-26 | 2022-09-23 | 2022-06-26 | 2022-09-23
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | 70MULBREC | 70 MULBERRY STREET - RECONSTRUCTION | 5 | CONSTRUCTION TO 25% | 2022-09-24 | 2023-01-21 | 2022-09-24 | 2023-01-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | 70MULBREC | 70 MULBERRY STREET - RECONSTRUCTION | 6 | CONSTRUCTION TO 50% | 2023-01-22 | 2023-05-21 | 2023-01-22 | 2023-05-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | 70MULBREC | 70 MULBERRY STREET - RECONSTRUCTION | 7 | CONSTRUCTION TO 75% | 2023-05-22 | 2023-09-18 | 2023-05-22 | 2023-09-18
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | 70MULBREC | 70 MULBERRY STREET - RECONSTRUCTION | 8 | ORIGINAL EQUIP & FURNISHING | 2023-09-19 | 2023-12-17 | 2023-09-19 | 2023-12-17
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | 70MULBREC | 70 MULBERRY STREET - RECONSTRUCTION | 9 | SUBSTANTIAL COMPLETION | 2023-12-18 | 2024-02-15 | 2023-12-18 | 2024-02-15
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | 70MULBREC | 70 MULBERRY STREET - RECONSTRUCTION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-02-16 | 2024-03-16 | 2024-02-16 | 2024-03-16
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOE701 | DOE - STEAM SYSTEM OPTIMIZATION | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-06-30 | 2020-06-01 | 2020-06-30
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOE701 | DOE - STEAM SYSTEM OPTIMIZATION | 2 | BID AWARD AND REGISTER CONTRCT | 2020-07-01 | 2020-08-29 | 2020-07-01 | 2020-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOE701 | DOE - STEAM SYSTEM OPTIMIZATION | 3 | CONSTRUCTION TO 50% | 2020-08-30 | 2021-02-25 | 2020-08-30 | 2021-02-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOE701 | DOE - STEAM SYSTEM OPTIMIZATION | 4 | CONSTRUCTION TO 75% | 2021-02-26 | 2021-05-26 | 2021-02-26 | 2021-05-26
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOE701 | DOE - STEAM SYSTEM OPTIMIZATION | 5 | SUBSTANTIAL COMPLETION | 2021-05-27 | 2021-07-25 | 2021-05-27 | 2021-07-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOE701 | DOE - STEAM SYSTEM OPTIMIZATION | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-07-26 | 2021-08-24 | 2021-07-26 | 2021-08-24
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | AG1RAND | DFTA -108- ST RANDOLPH SC | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-08-29 | 2020-06-01 | 2020-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | AG1RAND | DFTA -108- ST RANDOLPH SC | 2 | PRELIMINARY DESIGN | 2020-08-30 | 2020-12-27 | 2020-08-30 | 2020-12-27
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | AG1RAND | DFTA -108- ST RANDOLPH SC | 3 | FINAL DESIGN | 2020-12-28 | 2021-06-25 | 2020-12-28 | 2021-06-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | AG1RAND | DFTA -108- ST RANDOLPH SC | 4 | BID AWARD AND REGISTER CONTRCT | 2021-06-26 | 2021-09-23 | 2021-06-26 | 2021-09-23
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | AG1RAND | DFTA -108- ST RANDOLPH SC | 5 | CONSTRUCTION TO 25% | 2021-09-24 | 2022-01-21 | 2021-09-24 | 2022-01-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | AG1RAND | DFTA -108- ST RANDOLPH SC | 6 | CONSTRUCTION TO 50% | 2022-01-22 | 2022-05-21 | 2022-01-22 | 2022-05-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | AG1RAND | DFTA -108- ST RANDOLPH SC | 7 | CONSTRUCTION TO 75% | 2022-05-22 | 2022-09-18 | 2022-05-22 | 2022-09-18
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | AG1RAND | DFTA -108- ST RANDOLPH SC | 8 | ORIGINAL EQUIP & FURNISHING | 2022-09-19 | 2022-12-17 | 2022-09-19 | 2022-12-17
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | AG1RAND | DFTA -108- ST RANDOLPH SC | 9 | SUBSTANTIAL COMPLETION | 2022-12-18 | 2023-02-15 | 2022-12-18 | 2023-02-15
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | AG1RAND | DFTA -108- ST RANDOLPH SC | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-02-16 | 2023-03-17 | 2023-02-16 | 2023-03-17
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | AGHVACRM | 2 Lafayette 9th floor DFTA IT room HVAC upgrade | 1 | DEVELOP SCOPE | 2019-06-01 | 2019-08-29 | 2019-06-01 | 2019-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | AGHVACRM | 2 Lafayette 9th floor DFTA IT room HVAC upgrade | 2 | PRELIMINARY DESIGN | 2019-08-30 | 2019-12-27 | 2019-08-30 | 2019-12-27
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | AGHVACRM | 2 Lafayette 9th floor DFTA IT room HVAC upgrade | 3 | FINAL DESIGN | 2019-12-28 | 2020-06-24 | 2019-12-28 | 2020-06-24
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | AGHVACRM | 2 Lafayette 9th floor DFTA IT room HVAC upgrade | 4 | BID AWARD AND REGISTER CONTRCT | 2020-06-25 | 2020-09-22 | 2020-06-25 | 2020-09-22
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | AGHVACRM | 2 Lafayette 9th floor DFTA IT room HVAC upgrade | 5 | CONSTRUCTION TO 25% | 2020-09-23 | 2021-01-20 | 2020-09-23 | 2021-01-20
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | AGHVACRM | 2 Lafayette 9th floor DFTA IT room HVAC upgrade | 6 | CONSTRUCTION TO 50% | 2021-01-21 | 2021-05-20 | 2021-01-21 | 2021-05-20
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | AGHVACRM | 2 Lafayette 9th floor DFTA IT room HVAC upgrade | 7 | CONSTRUCTION TO 75% | 2021-05-21 | 2021-09-17 | 2021-05-21 | 2021-09-17
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | AGHVACRM | 2 Lafayette 9th floor DFTA IT room HVAC upgrade | 8 | ORIGINAL EQUIP & FURNISHING | 2021-09-18 | 2021-12-16 | 2021-09-18 | 2021-12-16
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | AGHVACRM | 2 Lafayette 9th floor DFTA IT room HVAC upgrade | 9 | SUBSTANTIAL COMPLETION | 2021-12-17 | 2022-02-14 | 2021-12-17 | 2022-02-14
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | AGHVACRM | 2 Lafayette 9th floor DFTA IT room HVAC upgrade | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-02-15 | 2022-03-16 | 2022-02-15 | 2025-06-30
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CENTCELL | 100 CENTRE ST- FLRS 1-3,5 & 12 FOR DOC | 1 | DEVELOP SCOPE | 2004-06-30 | 2004-09-27 | 2004-06-30 | 2004-09-27
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CENTCELL | 100 CENTRE ST- FLRS 1-3,5 & 12 FOR DOC | 2 | PRELIMINARY DESIGN | 2004-09-28 | 2005-01-25 | 2004-09-28 | 2005-01-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CENTCELL | 100 CENTRE ST- FLRS 1-3,5 & 12 FOR DOC | 3 | FINAL DESIGN | 2005-01-26 | 2005-07-24 | 2005-01-26 | 2005-07-24
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CENTCELL | 100 CENTRE ST- FLRS 1-3,5 & 12 FOR DOC | 4 | BID AWARD AND REGISTER CONTRCT | 2005-07-25 | 2005-10-22 | 2005-07-25 | 2005-10-22
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CENTCELL | 100 CENTRE ST- FLRS 1-3,5 & 12 FOR DOC | 5 | CONSTRUCTION TO 25% | 2005-10-23 | 2006-02-19 | 2005-10-23 | 2008-06-08
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CENTCELL | 100 CENTRE ST- FLRS 1-3,5 & 12 FOR DOC | 6 | CONSTRUCTION TO 50% | 2006-02-20 | 2006-06-19 | 2008-06-09 | 2011-01-24
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CENTCELL | 100 CENTRE ST- FLRS 1-3,5 & 12 FOR DOC | 7 | CONSTRUCTION TO 75% | 2006-06-20 | 2006-10-17 | 2011-01-25 | 2013-01-13
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CENTCELL | 100 CENTRE ST- FLRS 1-3,5 & 12 FOR DOC | 8 | ORIGINAL EQUIP & FURNISHING | 2006-10-18 | 2007-01-15 | 2013-01-14 | 2013-04-13
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CENTCELL | 100 CENTRE ST- FLRS 1-3,5 & 12 FOR DOC | 9 | SUBSTANTIAL COMPLETION | 2007-01-16 | 2007-03-16 | 2013-04-14 | 2013-06-12
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CENTCELL | 100 CENTRE ST- FLRS 1-3,5 & 12 FOR DOC | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2007-03-17 | 2007-04-15 | 2013-06-13 | 2013-06-27
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO283CTSP | 100 CENTRE ST- COOLING TOWERS TO REPLACE SPRAY PONDS | 1 | DEVELOP SCOPE | 2010-06-01 | 2010-08-29 | 2010-06-01 | 2010-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO283CTSP | 100 CENTRE ST- COOLING TOWERS TO REPLACE SPRAY PONDS | 2 | PRELIMINARY DESIGN | 2010-08-30 | 2010-12-27 | 2010-08-30 | 2010-12-27
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO283CTSP | 100 CENTRE ST- COOLING TOWERS TO REPLACE SPRAY PONDS | 3 | FINAL DESIGN | 2010-12-28 | 2011-06-25 | 2010-12-28 | 2011-06-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO283CTSP | 100 CENTRE ST- COOLING TOWERS TO REPLACE SPRAY PONDS | 4 | BID AWARD AND REGISTER CONTRCT | 2011-06-26 | 2011-09-23 | 2011-06-26 | 2011-09-23
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO283CTSP | 100 CENTRE ST- COOLING TOWERS TO REPLACE SPRAY PONDS | 5 | CONSTRUCTION TO 25% | 2011-09-24 | 2012-01-21 | 2011-09-24 | 2012-01-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO283CTSP | 100 CENTRE ST- COOLING TOWERS TO REPLACE SPRAY PONDS | 6 | CONSTRUCTION TO 50% | 2012-01-22 | 2012-05-20 | 2012-01-22 | 2012-05-20
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO283CTSP | 100 CENTRE ST- COOLING TOWERS TO REPLACE SPRAY PONDS | 7 | CONSTRUCTION TO 75% | 2012-05-21 | 2012-09-17 | 2012-05-21 | 2012-09-17
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO283CTSP | 100 CENTRE ST- COOLING TOWERS TO REPLACE SPRAY PONDS | 8 | ORIGINAL EQUIP & FURNISHING | 2012-09-18 | 2012-12-16 | 2012-09-18 | 2012-12-16
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO283CTSP | 100 CENTRE ST- COOLING TOWERS TO REPLACE SPRAY PONDS | 9 | SUBSTANTIAL COMPLETION | 2012-12-17 | 2013-02-14 | 2022-06-30 | 2022-08-28
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO283CTSP | 100 CENTRE ST- COOLING TOWERS TO REPLACE SPRAY PONDS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-02-15 | 2013-03-16 | 2022-08-29 | 2022-09-27
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO283FIRE | 100 CENTRE ST.- FIRE SAFETY | 1 | DEVELOP SCOPE | 2009-11-01 | 2010-01-30 | 2009-11-01 | 2022-01-30
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO283FIRE | 100 CENTRE ST.- FIRE SAFETY | 2 | PRELIMINARY DESIGN | 2005-05-30 | 2006-02-28 | 2005-05-30 | 2006-02-28
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO283FIRE | 100 CENTRE ST.- FIRE SAFETY | 3 | FINAL DESIGN | 2006-03-01 | 2007-05-31 | 2006-03-01 | 2007-05-31
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO283FIRE | 100 CENTRE ST.- FIRE SAFETY | 4 | BID AWARD AND REGISTER CONTRCT | 2007-06-01 | 2007-08-31 | 2007-06-01 | 2007-08-31
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO283FIRE | 100 CENTRE ST.- FIRE SAFETY | 5 | CONSTRUCTION TO 25% | 2007-09-01 | 2007-11-30 | 2007-09-01 | 2007-11-30
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO283FIRE | 100 CENTRE ST.- FIRE SAFETY | 6 | CONSTRUCTION TO 50% | 2007-12-01 | 2008-02-29 | 2007-12-01 | 2008-02-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO283FIRE | 100 CENTRE ST.- FIRE SAFETY | 7 | CONSTRUCTION TO 75% | 2008-03-01 | 2008-03-30 | 2008-03-01 | 2008-03-30
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO283FIRE | 100 CENTRE ST.- FIRE SAFETY | 8 | ORIGINAL EQUIP & FURNISHING | 2008-03-31 | 2008-03-30 | 2008-03-31 | 2008-03-30
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO283FIRE | 100 CENTRE ST.- FIRE SAFETY | 9 | SUBSTANTIAL COMPLETION | 2008-07-01 | 2008-09-30 | 2008-07-01 | 2024-06-30
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO283FIRE | 100 CENTRE ST.- FIRE SAFETY | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-10-01 | 2011-12-31 | 2024-07-01 | 2027-09-30
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO283LL11 | 100 CENTRE ST - FACADE RECONSTRUCTION | 1 | DEVELOP SCOPE | 2022-06-01 | 2022-08-29 | 2022-06-01 | 2022-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO283LL11 | 100 CENTRE ST - FACADE RECONSTRUCTION | 2 | PRELIMINARY DESIGN | 2022-08-30 | 2022-12-27 | 2022-08-30 | 2022-12-27
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO283LL11 | 100 CENTRE ST - FACADE RECONSTRUCTION | 3 | FINAL DESIGN | 2022-12-28 | 2023-06-25 | 2022-12-28 | 2023-06-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO283LL11 | 100 CENTRE ST - FACADE RECONSTRUCTION | 4 | BID AWARD AND REGISTER CONTRCT | 2023-06-26 | 2023-09-23 | 2023-06-26 | 2023-09-23
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO283LL11 | 100 CENTRE ST - FACADE RECONSTRUCTION | 5 | CONSTRUCTION TO 25% | 2023-09-24 | 2024-01-21 | 2023-09-24 | 2024-01-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO283LL11 | 100 CENTRE ST - FACADE RECONSTRUCTION | 6 | CONSTRUCTION TO 50% | 2024-01-22 | 2024-05-20 | 2024-01-22 | 2024-05-20
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO283LL11 | 100 CENTRE ST - FACADE RECONSTRUCTION | 7 | CONSTRUCTION TO 75% | 2024-05-21 | 2024-09-17 | 2024-05-21 | 2024-09-17
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO283LL11 | 100 CENTRE ST - FACADE RECONSTRUCTION | 8 | ORIGINAL EQUIP & FURNISHING | 2024-09-18 | 2024-12-16 | 2024-09-18 | 2024-12-16
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO283LL11 | 100 CENTRE ST - FACADE RECONSTRUCTION | 9 | SUBSTANTIAL COMPLETION | 2024-12-17 | 2025-02-14 | 2024-12-17 | 2025-02-14
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO283LL11 | 100 CENTRE ST - FACADE RECONSTRUCTION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-02-15 | 2025-03-16 | 2025-02-15 | 2025-03-16
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO283SG | 100 CENTRE ST. - SAFETY GRATINGS | 1 | DEVELOP SCOPE | 2012-06-01 | 2012-08-29 | 2022-06-01 | 2022-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO283SG | 100 CENTRE ST. - SAFETY GRATINGS | 2 | PRELIMINARY DESIGN | 2012-08-30 | 2012-12-27 | 2022-08-30 | 2022-12-27
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO283SG | 100 CENTRE ST. - SAFETY GRATINGS | 3 | FINAL DESIGN | 2012-12-28 | 2013-06-25 | 2022-12-28 | 2023-06-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO283SG | 100 CENTRE ST. - SAFETY GRATINGS | 4 | BID AWARD AND REGISTER CONTRCT | 2013-06-26 | 2013-09-23 | 2023-06-26 | 2023-09-23
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO283SG | 100 CENTRE ST. - SAFETY GRATINGS | 5 | CONSTRUCTION TO 25% | 2013-09-24 | 2014-01-21 | 2023-09-24 | 2024-01-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO283SG | 100 CENTRE ST. - SAFETY GRATINGS | 6 | CONSTRUCTION TO 50% | 2014-01-22 | 2014-05-21 | 2024-01-22 | 2024-05-20
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO283SG | 100 CENTRE ST. - SAFETY GRATINGS | 7 | CONSTRUCTION TO 75% | 2014-05-22 | 2014-09-18 | 2024-05-21 | 2024-09-17
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO283SG | 100 CENTRE ST. - SAFETY GRATINGS | 8 | ORIGINAL EQUIP & FURNISHING | 2014-09-19 | 2014-12-17 | 2024-09-18 | 2024-12-16
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO283SG | 100 CENTRE ST. - SAFETY GRATINGS | 9 | SUBSTANTIAL COMPLETION | 2014-12-18 | 2015-02-15 | 2024-12-17 | 2025-02-14
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO283SG | 100 CENTRE ST. - SAFETY GRATINGS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-02-16 | 2015-03-17 | 2025-02-15 | 2025-03-16
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO304HEA2 | 60 CENTRE STREET- SPRINKLERS | 1 | DEVELOP SCOPE | 2012-06-30 | 2012-09-27 | 2022-06-01 | 2022-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO304HEA2 | 60 CENTRE STREET- SPRINKLERS | 2 | PRELIMINARY DESIGN | 2012-09-28 | 2013-01-25 | 2022-08-30 | 2022-12-27
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO304HEA2 | 60 CENTRE STREET- SPRINKLERS | 3 | FINAL DESIGN | 2013-01-26 | 2013-07-24 | 2022-12-28 | 2023-06-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO304HEA2 | 60 CENTRE STREET- SPRINKLERS | 4 | BID AWARD AND REGISTER CONTRCT | 2013-07-25 | 2013-10-22 | 2023-06-26 | 2023-09-23
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO304HEA2 | 60 CENTRE STREET- SPRINKLERS | 5 | CONSTRUCTION TO 25% | 2013-10-23 | 2014-04-20 | 2023-09-24 | 2024-03-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO304HEA2 | 60 CENTRE STREET- SPRINKLERS | 6 | CONSTRUCTION TO 50% | 2014-04-21 | 2014-10-17 | 2024-03-22 | 2024-09-17
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO304HEA2 | 60 CENTRE STREET- SPRINKLERS | 7 | CONSTRUCTION TO 75% | 2014-10-18 | 2015-04-15 | 2024-09-18 | 2025-03-16
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO304HEA2 | 60 CENTRE STREET- SPRINKLERS | 8 | ORIGINAL EQUIP & FURNISHING | 2015-04-16 | 2015-05-15 | 2025-03-17 | 2025-04-15
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO304HEA2 | 60 CENTRE STREET- SPRINKLERS | 9 | SUBSTANTIAL COMPLETION | 2015-05-16 | 2015-06-14 | 2025-04-16 | 2025-05-15
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO304HEA2 | 60 CENTRE STREET- SPRINKLERS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-06-15 | 2015-06-29 | 2025-05-16 | 2025-05-30
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO304HEA5 | 60 CENTRE ST.- HEATING DISTRIBUTION SYSTEM | 1 | DEVELOP SCOPE | 2017-01-01 | 2017-03-31 | 2024-06-01 | 2024-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO304HEA5 | 60 CENTRE ST.- HEATING DISTRIBUTION SYSTEM | 2 | PRELIMINARY DESIGN | 2017-04-01 | 2017-07-29 | 2024-08-30 | 2024-12-27
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO304HEA5 | 60 CENTRE ST.- HEATING DISTRIBUTION SYSTEM | 3 | FINAL DESIGN | 2017-07-30 | 2018-01-25 | 2024-12-28 | 2025-06-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO304HEA5 | 60 CENTRE ST.- HEATING DISTRIBUTION SYSTEM | 4 | BID AWARD AND REGISTER CONTRCT | 2018-01-26 | 2018-04-25 | 2025-06-26 | 2025-09-23
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO304HEA5 | 60 CENTRE ST.- HEATING DISTRIBUTION SYSTEM | 5 | CONSTRUCTION TO 25% | 2018-04-26 | 2018-08-23 | 2025-09-24 | 2026-01-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO304HEA5 | 60 CENTRE ST.- HEATING DISTRIBUTION SYSTEM | 6 | CONSTRUCTION TO 50% | 2018-08-24 | 2018-12-21 | 2026-01-22 | 2026-05-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO304HEA5 | 60 CENTRE ST.- HEATING DISTRIBUTION SYSTEM | 7 | CONSTRUCTION TO 75% | 2018-12-22 | 2019-04-20 | 2026-05-22 | 2026-09-18
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO304HEA5 | 60 CENTRE ST.- HEATING DISTRIBUTION SYSTEM | 8 | ORIGINAL EQUIP & FURNISHING | 2019-04-21 | 2019-07-19 | 2026-09-19 | 2026-12-17
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO304HEA5 | 60 CENTRE ST.- HEATING DISTRIBUTION SYSTEM | 9 | SUBSTANTIAL COMPLETION | 2019-07-20 | 2019-09-17 | 2026-12-18 | 2027-02-15
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO304HEA5 | 60 CENTRE ST.- HEATING DISTRIBUTION SYSTEM | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-18 | 2019-10-17 | 2027-02-16 | 2027-03-17
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO305REHB | 314 W. 54TH ST.- MIDTOWN COMM COURT EXPANSION | 1 | DEVELOP SCOPE | 2002-05-15 | 2002-08-12 | 2001-01-01 | 2001-03-31
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO305REHB | 314 W. 54TH ST.- MIDTOWN COMM COURT EXPANSION | 2 | PRELIMINARY DESIGN | 2002-08-13 | 2002-12-10 | 2001-04-01 | 2001-07-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO305REHB | 314 W. 54TH ST.- MIDTOWN COMM COURT EXPANSION | 3 | FINAL DESIGN | 2002-12-11 | 2003-06-08 | 2001-07-30 | 2002-01-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO305REHB | 314 W. 54TH ST.- MIDTOWN COMM COURT EXPANSION | 4 | BID AWARD AND REGISTER CONTRCT | 2003-06-09 | 2003-09-06 | 2021-06-01 | 2021-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO305REHB | 314 W. 54TH ST.- MIDTOWN COMM COURT EXPANSION | 5 | CONSTRUCTION TO 25% | 2003-09-07 | 2004-01-04 | 2021-08-30 | 2022-04-15
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO305REHB | 314 W. 54TH ST.- MIDTOWN COMM COURT EXPANSION | 6 | CONSTRUCTION TO 50% | 2004-01-05 | 2004-05-03 | 2022-04-16 | 2022-10-16
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO305REHB | 314 W. 54TH ST.- MIDTOWN COMM COURT EXPANSION | 7 | CONSTRUCTION TO 75% | 2004-05-04 | 2004-08-31 | 2022-10-17 | 2025-06-02
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO305REHB | 314 W. 54TH ST.- MIDTOWN COMM COURT EXPANSION | 8 | ORIGINAL EQUIP & FURNISHING | 2004-09-01 | 2004-11-29 | 2025-06-03 | 2026-01-18
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO305REHB | 314 W. 54TH ST.- MIDTOWN COMM COURT EXPANSION | 9 | SUBSTANTIAL COMPLETION | 2004-11-30 | 2005-01-28 | 2026-01-19 | 2026-07-17
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO305REHB | 314 W. 54TH ST.- MIDTOWN COMM COURT EXPANSION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2005-01-29 | 2005-02-27 | 2026-07-18 | 2030-11-11
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO306CEIL | 170 E 121 ST - HARLEM CT CEILING | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-08-29 | 2020-06-01 | 2020-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO306CEIL | 170 E 121 ST - HARLEM CT CEILING | 2 | PRELIMINARY DESIGN | 2020-08-30 | 2020-12-27 | 2020-08-30 | 2020-12-27
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO306CEIL | 170 E 121 ST - HARLEM CT CEILING | 3 | FINAL DESIGN | 2020-12-28 | 2021-06-25 | 2020-12-28 | 2021-06-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO306CEIL | 170 E 121 ST - HARLEM CT CEILING | 4 | BID AWARD AND REGISTER CONTRCT | 2021-06-26 | 2021-09-23 | 2021-06-26 | 2021-09-23
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO306CEIL | 170 E 121 ST - HARLEM CT CEILING | 5 | CONSTRUCTION TO 25% | 2021-09-24 | 2022-01-21 | 2021-09-24 | 2022-01-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO306CEIL | 170 E 121 ST - HARLEM CT CEILING | 6 | CONSTRUCTION TO 50% | 2022-01-22 | 2022-05-21 | 2022-01-22 | 2022-05-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO306CEIL | 170 E 121 ST - HARLEM CT CEILING | 7 | CONSTRUCTION TO 75% | 2022-05-22 | 2022-09-18 | 2022-05-22 | 2022-09-18
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO306CEIL | 170 E 121 ST - HARLEM CT CEILING | 8 | ORIGINAL EQUIP & FURNISHING | 2022-09-19 | 2022-12-17 | 2022-09-19 | 2022-12-17
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO306CEIL | 170 E 121 ST - HARLEM CT CEILING | 9 | SUBSTANTIAL COMPLETION | 2022-12-18 | 2023-02-15 | 2022-12-18 | 2023-02-15
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO306CEIL | 170 E 121 ST - HARLEM CT CEILING | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-02-16 | 2023-03-17 | 2023-02-16 | 2023-03-17
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO306MHCB | 170 E. 121 ST. - HARLEM COURT BOILER | 1 | DEVELOP SCOPE | 2012-01-01 | 2012-03-30 | 2022-06-01 | 2022-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO306MHCB | 170 E. 121 ST. - HARLEM COURT BOILER | 2 | PRELIMINARY DESIGN | 2012-03-31 | 2012-07-28 | 2022-08-30 | 2022-12-27
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO306MHCB | 170 E. 121 ST. - HARLEM COURT BOILER | 3 | FINAL DESIGN | 2012-07-29 | 2013-01-24 | 2022-12-28 | 2023-06-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO306MHCB | 170 E. 121 ST. - HARLEM COURT BOILER | 4 | BID AWARD AND REGISTER CONTRCT | 2013-01-25 | 2013-04-24 | 2023-06-26 | 2023-09-23
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO306MHCB | 170 E. 121 ST. - HARLEM COURT BOILER | 5 | CONSTRUCTION TO 25% | 2013-04-25 | 2013-08-22 | 2023-09-24 | 2024-01-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO306MHCB | 170 E. 121 ST. - HARLEM COURT BOILER | 6 | CONSTRUCTION TO 50% | 2013-08-23 | 2013-12-20 | 2024-01-22 | 2024-05-20
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO306MHCB | 170 E. 121 ST. - HARLEM COURT BOILER | 7 | CONSTRUCTION TO 75% | 2013-12-21 | 2014-04-19 | 2024-05-21 | 2024-09-17
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO306MHCB | 170 E. 121 ST. - HARLEM COURT BOILER | 8 | ORIGINAL EQUIP & FURNISHING | 2014-04-20 | 2014-07-18 | 2024-09-18 | 2024-12-16
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO306MHCB | 170 E. 121 ST. - HARLEM COURT BOILER | 9 | SUBSTANTIAL COMPLETION | 2014-07-19 | 2014-09-16 | 2024-12-17 | 2025-02-14
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO306MHCB | 170 E. 121 ST. - HARLEM COURT BOILER | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-09-17 | 2014-10-16 | 2025-02-15 | 2025-03-16
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO81ADA1 | 31 CHAMBERS ST - ADA LIFT | 1 | DEVELOP SCOPE | 2021-06-01 | 2021-08-29 | 2021-06-01 | 2021-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO81ADA1 | 31 CHAMBERS ST - ADA LIFT | 2 | PRELIMINARY DESIGN | 2021-08-30 | 2021-12-27 | 2021-08-30 | 2021-12-27
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO81ADA1 | 31 CHAMBERS ST - ADA LIFT | 3 | FINAL DESIGN | 2021-12-28 | 2022-06-25 | 2021-12-28 | 2022-06-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO81ADA1 | 31 CHAMBERS ST - ADA LIFT | 4 | BID AWARD AND REGISTER CONTRCT | 2022-06-26 | 2022-09-23 | 2022-06-26 | 2022-09-23
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO81ADA1 | 31 CHAMBERS ST - ADA LIFT | 5 | CONSTRUCTION TO 25% | 2022-09-24 | 2023-01-21 | 2022-09-24 | 2023-01-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO81ADA1 | 31 CHAMBERS ST - ADA LIFT | 6 | CONSTRUCTION TO 50% | 2023-01-22 | 2023-05-21 | 2023-01-22 | 2023-05-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO81ADA1 | 31 CHAMBERS ST - ADA LIFT | 7 | CONSTRUCTION TO 75% | 2023-05-22 | 2023-09-18 | 2023-05-22 | 2023-09-18
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO81ADA1 | 31 CHAMBERS ST - ADA LIFT | 8 | ORIGINAL EQUIP & FURNISHING | 2023-09-19 | 2023-12-17 | 2023-09-19 | 2023-12-17
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO81ADA1 | 31 CHAMBERS ST - ADA LIFT | 9 | SUBSTANTIAL COMPLETION | 2023-12-18 | 2024-02-15 | 2023-12-18 | 2024-02-15
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO81ADA1 | 31 CHAMBERS ST - ADA LIFT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-02-16 | 2024-03-16 | 2024-02-16 | 2024-03-16
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E19-0009 | NYPD - 20th Precinct | 1 | DEVELOP SCOPE | 2019-06-01 | 2019-06-30 | 2019-06-01 | 2019-06-30
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E19-0009 | NYPD - 20th Precinct | 2 | BID AWARD AND REGISTER CONTRCT | 2019-07-01 | 2019-08-29 | 2019-07-01 | 2019-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E19-0009 | NYPD - 20th Precinct | 3 | CONSTRUCTION TO 50% | 2019-08-30 | 2020-02-25 | 2019-08-30 | 2020-02-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E19-0009 | NYPD - 20th Precinct | 4 | CONSTRUCTION TO 75% | 2020-02-26 | 2020-05-25 | 2020-02-26 | 2020-05-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E19-0009 | NYPD - 20th Precinct | 5 | SUBSTANTIAL COMPLETION | 2020-05-26 | 2020-07-24 | 2020-05-26 | 2020-07-24
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E19-0009 | NYPD - 20th Precinct | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-07-25 | 2020-08-23 | 2020-07-25 | 2020-08-23
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0019 | DCLA - Lincoln Center Campus: Plaza/Public Spaces/Garages | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-06-30 | 2020-06-01 | 2020-06-30
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0019 | DCLA - Lincoln Center Campus: Plaza/Public Spaces/Garages | 2 | BID AWARD AND REGISTER CONTRCT | 2020-07-01 | 2020-08-29 | 2020-07-01 | 2020-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0019 | DCLA - Lincoln Center Campus: Plaza/Public Spaces/Garages | 3 | CONSTRUCTION TO 50% | 2020-08-30 | 2021-02-25 | 2020-08-30 | 2021-02-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0019 | DCLA - Lincoln Center Campus: Plaza/Public Spaces/Garages | 4 | CONSTRUCTION TO 75% | 2021-02-26 | 2021-05-26 | 2021-02-26 | 2021-05-26
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0019 | DCLA - Lincoln Center Campus: Plaza/Public Spaces/Garages | 5 | SUBSTANTIAL COMPLETION | 2021-05-27 | 2021-07-25 | 2021-05-27 | 2021-07-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0019 | DCLA - Lincoln Center Campus: Plaza/Public Spaces/Garages | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-07-26 | 2021-08-24 | 2021-07-26 | 2021-08-24
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0026 | NYPL - The Library for the Performing Arts | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-06-30 | 2020-06-01 | 2020-06-30
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0026 | NYPL - The Library for the Performing Arts | 2 | BID AWARD AND REGISTER CONTRCT | 2020-07-01 | 2020-08-29 | 2020-07-01 | 2020-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0026 | NYPL - The Library for the Performing Arts | 3 | CONSTRUCTION TO 50% | 2020-08-30 | 2021-02-25 | 2020-08-30 | 2021-02-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0026 | NYPL - The Library for the Performing Arts | 4 | CONSTRUCTION TO 75% | 2021-02-26 | 2021-05-26 | 2021-02-26 | 2021-05-26
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0026 | NYPL - The Library for the Performing Arts | 5 | SUBSTANTIAL COMPLETION | 2021-05-27 | 2021-07-25 | 2021-05-27 | 2021-07-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0026 | NYPL - The Library for the Performing Arts | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-07-26 | 2021-08-24 | 2021-07-26 | 2021-08-24
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0034 | DPR-Central Park Campus: Wollman Rink | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-06-30 | 2020-06-01 | 2020-06-30
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0034 | DPR-Central Park Campus: Wollman Rink | 2 | BID AWARD AND REGISTER CONTRCT | 2020-07-01 | 2020-08-29 | 2020-07-01 | 2020-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0034 | DPR-Central Park Campus: Wollman Rink | 3 | CONSTRUCTION TO 50% | 2020-08-30 | 2021-02-25 | 2020-08-30 | 2021-02-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0034 | DPR-Central Park Campus: Wollman Rink | 4 | CONSTRUCTION TO 75% | 2021-02-26 | 2021-05-26 | 2021-02-26 | 2021-05-26
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0034 | DPR-Central Park Campus: Wollman Rink | 5 | SUBSTANTIAL COMPLETION | 2021-05-27 | 2021-07-25 | 2021-05-27 | 2021-07-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0034 | DPR-Central Park Campus: Wollman Rink | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-07-26 | 2021-08-24 | 2021-07-26 | 2021-08-24
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0041 | Manhattan Borough Repair Shop | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-06-30 | 2020-06-01 | 2020-06-30
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0041 | Manhattan Borough Repair Shop | 2 | BID AWARD AND REGISTER CONTRCT | 2020-07-01 | 2020-08-29 | 2020-07-01 | 2020-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0041 | Manhattan Borough Repair Shop | 3 | CONSTRUCTION TO 50% | 2020-08-30 | 2021-02-25 | 2020-08-30 | 2021-02-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0041 | Manhattan Borough Repair Shop | 4 | CONSTRUCTION TO 75% | 2021-02-26 | 2021-05-26 | 2021-02-26 | 2021-05-26
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0041 | Manhattan Borough Repair Shop | 5 | SUBSTANTIAL COMPLETION | 2021-05-27 | 2021-07-25 | 2021-05-27 | 2021-07-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0041 | Manhattan Borough Repair Shop | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-07-26 | 2021-08-24 | 2021-07-26 | 2021-08-24
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0046 | CUNY - BMCC Campus: Chambers St. Building (Main Campus) | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-06-30 | 2020-06-01 | 2020-06-30
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0046 | CUNY - BMCC Campus: Chambers St. Building (Main Campus) | 2 | BID AWARD AND REGISTER CONTRCT | 2020-07-01 | 2020-08-29 | 2020-07-01 | 2020-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0046 | CUNY - BMCC Campus: Chambers St. Building (Main Campus) | 3 | CONSTRUCTION TO 50% | 2020-08-30 | 2021-02-25 | 2020-08-30 | 2021-02-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0046 | CUNY - BMCC Campus: Chambers St. Building (Main Campus) | 4 | CONSTRUCTION TO 75% | 2021-02-26 | 2021-05-26 | 2021-02-26 | 2021-05-26
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0046 | CUNY - BMCC Campus: Chambers St. Building (Main Campus) | 5 | SUBSTANTIAL COMPLETION | 2021-05-27 | 2021-07-25 | 2021-05-27 | 2021-07-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0046 | CUNY - BMCC Campus: Chambers St. Building (Main Campus) | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-07-26 | 2021-08-24 | 2021-07-26 | 2021-08-24
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0054 | CIG - David H. Koch Theater | 1 | DEVELOP SCOPE | 2020-05-01 | 2020-05-30 | 2020-05-01 | 2020-05-30
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0054 | CIG - David H. Koch Theater | 2 | BID AWARD AND REGISTER CONTRCT | 2020-05-31 | 2020-07-29 | 2020-05-31 | 2020-07-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0054 | CIG - David H. Koch Theater | 3 | CONSTRUCTION TO 50% | 2020-07-30 | 2021-01-25 | 2020-07-30 | 2021-01-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0054 | CIG - David H. Koch Theater | 4 | CONSTRUCTION TO 75% | 2021-01-26 | 2021-04-25 | 2021-01-26 | 2021-04-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0054 | CIG - David H. Koch Theater | 5 | SUBSTANTIAL COMPLETION | 2021-04-26 | 2021-06-24 | 2021-04-26 | 2021-06-24
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0054 | CIG - David H. Koch Theater | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-06-25 | 2021-07-24 | 2021-06-25 | 2021-07-24
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0055 | DCAS - Midtown Community Court | 1 | DEVELOP SCOPE | 2020-02-01 | 2020-03-01 | 2022-06-01 | 2022-08-30
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0055 | DCAS - Midtown Community Court | 2 | BID AWARD AND REGISTER CONTRCT | 2020-03-02 | 2020-04-30 | 2022-08-31 | 2022-10-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0055 | DCAS - Midtown Community Court | 3 | CONSTRUCTION TO 50% | 2020-05-01 | 2020-10-27 | 2022-10-30 | 2023-04-27
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0055 | DCAS - Midtown Community Court | 4 | CONSTRUCTION TO 75% | 2020-10-28 | 2021-01-25 | 2023-04-28 | 2023-07-26
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0055 | DCAS - Midtown Community Court | 5 | SUBSTANTIAL COMPLETION | 2021-01-26 | 2021-03-26 | 2023-07-27 | 2023-09-24
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0055 | DCAS - Midtown Community Court | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-27 | 2021-04-25 | 2023-09-25 | 2023-10-24
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0056 | NYPD - 18th Precinct (Midtown North) | 1 | DEVELOP SCOPE | 2020-02-01 | 2020-03-01 | 2022-06-01 | 2022-06-30
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0056 | NYPD - 18th Precinct (Midtown North) | 2 | BID AWARD AND REGISTER CONTRCT | 2020-03-02 | 2020-04-30 | 2022-07-01 | 2022-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0056 | NYPD - 18th Precinct (Midtown North) | 3 | CONSTRUCTION TO 50% | 2020-05-01 | 2020-10-27 | 2022-08-30 | 2023-02-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0056 | NYPD - 18th Precinct (Midtown North) | 4 | CONSTRUCTION TO 75% | 2020-10-28 | 2021-01-25 | 2023-02-26 | 2023-05-26
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0056 | NYPD - 18th Precinct (Midtown North) | 5 | SUBSTANTIAL COMPLETION | 2021-01-26 | 2021-03-26 | 2023-05-27 | 2023-07-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0056 | NYPD - 18th Precinct (Midtown North) | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-27 | 2021-04-25 | 2023-07-26 | 2023-08-24
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0065 | NYPD - 10th Precinct | 1 | DEVELOP SCOPE | 2020-03-01 | 2020-03-30 | 2022-06-01 | 2022-06-30
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0065 | NYPD - 10th Precinct | 2 | BID AWARD AND REGISTER CONTRCT | 2020-03-31 | 2020-05-29 | 2022-07-01 | 2022-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0065 | NYPD - 10th Precinct | 3 | CONSTRUCTION TO 50% | 2020-05-30 | 2020-11-25 | 2022-08-30 | 2023-02-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0065 | NYPD - 10th Precinct | 4 | CONSTRUCTION TO 75% | 2020-11-26 | 2021-02-23 | 2023-02-26 | 2023-05-26
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0065 | NYPD - 10th Precinct | 5 | SUBSTANTIAL COMPLETION | 2021-02-24 | 2021-04-24 | 2023-05-27 | 2023-07-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0065 | NYPD - 10th Precinct | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-04-25 | 2021-05-24 | 2023-07-26 | 2023-08-24
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0066 | NYPD -Engine Co. 39, Ladder Co. 16 and 19th Precinct Campus | 1 | DEVELOP SCOPE | 2020-02-01 | 2020-03-01 | 2022-06-01 | 2022-06-30
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0066 | NYPD -Engine Co. 39, Ladder Co. 16 and 19th Precinct Campus | 2 | BID AWARD AND REGISTER CONTRCT | 2020-03-02 | 2020-04-30 | 2022-07-01 | 2022-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0066 | NYPD -Engine Co. 39, Ladder Co. 16 and 19th Precinct Campus | 3 | CONSTRUCTION TO 50% | 2020-05-01 | 2020-10-27 | 2022-08-30 | 2023-02-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0066 | NYPD -Engine Co. 39, Ladder Co. 16 and 19th Precinct Campus | 4 | CONSTRUCTION TO 75% | 2020-10-28 | 2021-01-25 | 2023-02-26 | 2023-05-26
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0066 | NYPD -Engine Co. 39, Ladder Co. 16 and 19th Precinct Campus | 5 | SUBSTANTIAL COMPLETION | 2021-01-26 | 2021-03-26 | 2023-05-27 | 2023-07-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0066 | NYPD -Engine Co. 39, Ladder Co. 16 and 19th Precinct Campus | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-27 | 2021-04-25 | 2023-07-26 | 2023-08-24
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0067 | NYPD - 30th Precinct | 1 | DEVELOP SCOPE | 2020-03-15 | 2020-04-13 | 2022-06-01 | 2022-06-30
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0067 | NYPD - 30th Precinct | 2 | BID AWARD AND REGISTER CONTRCT | 2020-04-14 | 2020-06-12 | 2022-07-01 | 2022-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0067 | NYPD - 30th Precinct | 3 | CONSTRUCTION TO 50% | 2020-06-13 | 2020-12-09 | 2022-08-30 | 2023-02-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0067 | NYPD - 30th Precinct | 4 | CONSTRUCTION TO 75% | 2020-12-10 | 2021-03-09 | 2023-02-26 | 2023-05-26
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0067 | NYPD - 30th Precinct | 5 | SUBSTANTIAL COMPLETION | 2021-03-10 | 2021-05-08 | 2023-05-27 | 2023-07-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0067 | NYPD - 30th Precinct | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-05-09 | 2021-06-07 | 2023-07-26 | 2023-08-24
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0068 | NYPD - 32nd Precinct | 1 | DEVELOP SCOPE | 2020-02-02 | 2020-03-02 | 2022-06-01 | 2022-06-30
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0068 | NYPD - 32nd Precinct | 2 | BID AWARD AND REGISTER CONTRCT | 2020-03-03 | 2020-05-01 | 2022-07-01 | 2022-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0068 | NYPD - 32nd Precinct | 3 | CONSTRUCTION TO 50% | 2020-05-02 | 2020-10-28 | 2022-08-30 | 2023-02-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0068 | NYPD - 32nd Precinct | 4 | CONSTRUCTION TO 75% | 2020-10-29 | 2021-01-26 | 2023-02-26 | 2023-05-26
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0068 | NYPD - 32nd Precinct | 5 | SUBSTANTIAL COMPLETION | 2021-01-27 | 2021-03-27 | 2023-05-27 | 2023-07-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0068 | NYPD - 32nd Precinct | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-28 | 2021-04-26 | 2023-07-26 | 2023-08-24
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0078 | DHS - MANHATTAN BOWERY SHELTER | 1 | DEVELOP SCOPE | 2020-02-01 | 2020-03-01 | 2022-06-01 | 2022-06-30
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0078 | DHS - MANHATTAN BOWERY SHELTER | 2 | BID AWARD AND REGISTER CONTRCT | 2020-03-02 | 2020-04-30 | 2022-07-01 | 2022-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0078 | DHS - MANHATTAN BOWERY SHELTER | 3 | CONSTRUCTION TO 50% | 2020-05-01 | 2020-10-27 | 2022-08-30 | 2023-02-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0078 | DHS - MANHATTAN BOWERY SHELTER | 4 | CONSTRUCTION TO 75% | 2020-10-28 | 2021-01-25 | 2023-02-26 | 2023-05-26
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0078 | DHS - MANHATTAN BOWERY SHELTER | 5 | SUBSTANTIAL COMPLETION | 2021-01-26 | 2021-03-26 | 2023-05-27 | 2023-07-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0078 | DHS - MANHATTAN BOWERY SHELTER | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-27 | 2021-04-25 | 2023-07-26 | 2023-08-24
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0081 | DHS - FORT WASHINGTON ARMORY - SHELTER (PROJECT RENEWAL) | 1 | DEVELOP SCOPE | 2020-02-01 | 2020-03-01 | 2020-06-01 | 2020-06-30
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0081 | DHS - FORT WASHINGTON ARMORY - SHELTER (PROJECT RENEWAL) | 2 | BID AWARD AND REGISTER CONTRCT | 2020-03-02 | 2020-04-30 | 2020-07-01 | 2020-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0081 | DHS - FORT WASHINGTON ARMORY - SHELTER (PROJECT RENEWAL) | 3 | CONSTRUCTION TO 50% | 2020-05-01 | 2020-10-27 | 2022-06-01 | 2022-11-27
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0081 | DHS - FORT WASHINGTON ARMORY - SHELTER (PROJECT RENEWAL) | 4 | CONSTRUCTION TO 75% | 2020-10-28 | 2021-01-25 | 2022-11-28 | 2023-02-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0081 | DHS - FORT WASHINGTON ARMORY - SHELTER (PROJECT RENEWAL) | 5 | SUBSTANTIAL COMPLETION | 2021-01-26 | 2021-03-26 | 2023-02-26 | 2023-04-26
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0081 | DHS - FORT WASHINGTON ARMORY - SHELTER (PROJECT RENEWAL) | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-27 | 2021-04-25 | 2023-04-27 | 2023-05-26
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0092 | CIG - METROPOLITAN MUSEUM OF ART - GALLERIES | 1 | DEVELOP SCOPE | 2021-03-15 | 2021-04-13 | 2021-03-15 | 2021-04-13
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0092 | CIG - METROPOLITAN MUSEUM OF ART - GALLERIES | 2 | BID AWARD AND REGISTER CONTRCT | 2021-04-14 | 2021-06-12 | 2021-04-14 | 2021-06-12
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0092 | CIG - METROPOLITAN MUSEUM OF ART - GALLERIES | 3 | CONSTRUCTION TO 50% | 2021-06-13 | 2021-12-09 | 2021-06-13 | 2021-12-09
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0092 | CIG - METROPOLITAN MUSEUM OF ART - GALLERIES | 4 | CONSTRUCTION TO 75% | 2021-12-10 | 2022-03-09 | 2021-12-10 | 2022-03-09
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0092 | CIG - METROPOLITAN MUSEUM OF ART - GALLERIES | 5 | SUBSTANTIAL COMPLETION | 2022-03-10 | 2022-05-08 | 2022-03-10 | 2022-05-08
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0092 | CIG - METROPOLITAN MUSEUM OF ART - GALLERIES | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-05-09 | 2022-06-07 | 2022-05-09 | 2022-06-07
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0093 | CIG - METROPOLITAN MUSEUM OF ART - OFFICE SPACES | 1 | DEVELOP SCOPE | 2021-03-15 | 2021-04-13 | 2021-03-15 | 2021-04-13
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0093 | CIG - METROPOLITAN MUSEUM OF ART - OFFICE SPACES | 2 | BID AWARD AND REGISTER CONTRCT | 2021-04-14 | 2021-06-12 | 2021-04-14 | 2021-06-12
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0093 | CIG - METROPOLITAN MUSEUM OF ART - OFFICE SPACES | 3 | CONSTRUCTION TO 50% | 2021-06-13 | 2021-12-09 | 2021-06-13 | 2021-12-09
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0093 | CIG - METROPOLITAN MUSEUM OF ART - OFFICE SPACES | 4 | CONSTRUCTION TO 75% | 2021-12-10 | 2022-03-09 | 2021-12-10 | 2022-03-09
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0093 | CIG - METROPOLITAN MUSEUM OF ART - OFFICE SPACES | 5 | SUBSTANTIAL COMPLETION | 2022-03-10 | 2022-05-08 | 2022-03-10 | 2022-05-08
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0093 | CIG - METROPOLITAN MUSEUM OF ART - OFFICE SPACES | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-05-09 | 2022-06-07 | 2022-05-09 | 2022-06-07
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0094 | NYPD - 13TH PRECINCT (OLD ACADEMY) | 1 | DEVELOP SCOPE | 2021-02-15 | 2021-03-16 | 2021-02-15 | 2021-03-16
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0094 | NYPD - 13TH PRECINCT (OLD ACADEMY) | 2 | BID AWARD AND REGISTER CONTRCT | 2021-03-17 | 2021-05-15 | 2021-03-17 | 2021-05-15
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0094 | NYPD - 13TH PRECINCT (OLD ACADEMY) | 3 | CONSTRUCTION TO 50% | 2021-05-16 | 2021-11-11 | 2021-05-16 | 2021-11-11
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0094 | NYPD - 13TH PRECINCT (OLD ACADEMY) | 4 | CONSTRUCTION TO 75% | 2021-11-12 | 2022-02-09 | 2021-11-12 | 2022-02-09
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0094 | NYPD - 13TH PRECINCT (OLD ACADEMY) | 5 | SUBSTANTIAL COMPLETION | 2022-02-10 | 2022-04-10 | 2022-02-10 | 2022-04-10
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0094 | NYPD - 13TH PRECINCT (OLD ACADEMY) | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-04-11 | 2022-05-10 | 2022-04-11 | 2022-05-10
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0095 | DOH - PUBLIC HEALTH LAB - DEEP ENERGY RETROFIT | 1 | DEVELOP SCOPE | 2021-06-01 | 2021-06-30 | 2021-06-01 | 2021-06-30
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0095 | DOH - PUBLIC HEALTH LAB - DEEP ENERGY RETROFIT | 2 | BID AWARD AND REGISTER CONTRCT | 2021-07-01 | 2021-08-29 | 2021-07-01 | 2021-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0095 | DOH - PUBLIC HEALTH LAB - DEEP ENERGY RETROFIT | 3 | CONSTRUCTION TO 50% | 2021-08-30 | 2022-02-25 | 2021-08-30 | 2022-02-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0095 | DOH - PUBLIC HEALTH LAB - DEEP ENERGY RETROFIT | 4 | CONSTRUCTION TO 75% | 2022-02-26 | 2022-05-26 | 2022-02-26 | 2022-05-26
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0095 | DOH - PUBLIC HEALTH LAB - DEEP ENERGY RETROFIT | 5 | SUBSTANTIAL COMPLETION | 2022-05-27 | 2022-07-25 | 2022-05-27 | 2022-07-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0095 | DOH - PUBLIC HEALTH LAB - DEEP ENERGY RETROFIT | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-07-26 | 2022-08-24 | 2022-07-26 | 2022-08-24
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | HR258AVEC | 400 8th Ave Construction | 1 | DESIGN | 2020-07-01 | 2020-12-27 | 2021-06-01 | 2021-11-27
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | HR258AVEC | 400 8th Ave Construction | 2 | CONSTRUCTION | 2020-12-28 | 2021-06-25 | 2021-11-28 | 2025-05-26
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79-375P | NYPD - 375 Pearl Street Renovation | 1 | DESIGN | 2018-12-30 | 2019-06-27 | 2018-12-30 | 2019-06-27
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79-375P | NYPD - 375 Pearl Street Renovation | 2 | BID AWARD AND REGISTER CONTRCT | 2019-06-28 | 2019-09-25 | 2019-06-28 | 2019-09-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79-375P | NYPD - 375 Pearl Street Renovation | 3 | CONSTRUCTION | 2019-09-26 | 2020-09-24 | 2019-09-26 | 2020-09-24
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79-375P | NYPD - 375 Pearl Street Renovation | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-25 | 2021-03-23 | 2020-09-25 | 2021-03-23
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW19325A | 1 CENTRE ST.- 25TH FL BUILDOUT PH1 - SOUTH | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-08-29 | 2020-06-01 | 2020-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW19325A | 1 CENTRE ST.- 25TH FL BUILDOUT PH1 - SOUTH | 2 | PRELIMINARY DESIGN | 2020-08-30 | 2020-12-27 | 2020-08-30 | 2020-12-27
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW19325A | 1 CENTRE ST.- 25TH FL BUILDOUT PH1 - SOUTH | 3 | FINAL DESIGN | 2020-12-28 | 2021-06-25 | 2020-12-28 | 2021-06-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW19325A | 1 CENTRE ST.- 25TH FL BUILDOUT PH1 - SOUTH | 4 | BID AWARD AND REGISTER CONTRCT | 2021-06-26 | 2021-09-23 | 2021-06-26 | 2021-09-23
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW19325A | 1 CENTRE ST.- 25TH FL BUILDOUT PH1 - SOUTH | 5 | CONSTRUCTION TO 25% | 2021-09-24 | 2022-01-21 | 2021-09-24 | 2022-01-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW19325A | 1 CENTRE ST.- 25TH FL BUILDOUT PH1 - SOUTH | 6 | CONSTRUCTION TO 50% | 2022-01-22 | 2022-05-21 | 2022-01-22 | 2022-05-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW19325A | 1 CENTRE ST.- 25TH FL BUILDOUT PH1 - SOUTH | 7 | CONSTRUCTION TO 75% | 2022-05-22 | 2022-09-18 | 2022-05-22 | 2022-09-18
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW19325A | 1 CENTRE ST.- 25TH FL BUILDOUT PH1 - SOUTH | 8 | ORIGINAL EQUIP & FURNISHING | 2022-09-19 | 2022-12-17 | 2022-09-19 | 2022-12-17
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW19325A | 1 CENTRE ST.- 25TH FL BUILDOUT PH1 - SOUTH | 9 | SUBSTANTIAL COMPLETION | 2022-12-18 | 2023-02-15 | 2022-12-18 | 2023-02-15
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW19325A | 1 CENTRE ST.- 25TH FL BUILDOUT PH1 - SOUTH | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-02-16 | 2023-03-17 | 2023-02-16 | 2023-03-17
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW19325B | 1 CENTRE ST.- 25TH FL BUILDOUT PH 2 - NORTH | 1 | DEVELOP SCOPE | 2021-06-01 | 2021-08-29 | 2021-06-01 | 2021-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW19325B | 1 CENTRE ST.- 25TH FL BUILDOUT PH 2 - NORTH | 2 | PRELIMINARY DESIGN | 2021-08-30 | 2021-12-27 | 2021-08-30 | 2021-12-27
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW19325B | 1 CENTRE ST.- 25TH FL BUILDOUT PH 2 - NORTH | 3 | FINAL DESIGN | 2021-12-28 | 2022-06-25 | 2021-12-28 | 2022-06-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW19325B | 1 CENTRE ST.- 25TH FL BUILDOUT PH 2 - NORTH | 4 | BID AWARD AND REGISTER CONTRCT | 2022-06-26 | 2022-09-23 | 2022-06-26 | 2022-09-23
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW19325B | 1 CENTRE ST.- 25TH FL BUILDOUT PH 2 - NORTH | 5 | CONSTRUCTION TO 25% | 2022-09-24 | 2023-01-21 | 2022-09-24 | 2023-01-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW19325B | 1 CENTRE ST.- 25TH FL BUILDOUT PH 2 - NORTH | 6 | CONSTRUCTION TO 50% | 2023-01-22 | 2023-05-21 | 2023-01-22 | 2023-05-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW19325B | 1 CENTRE ST.- 25TH FL BUILDOUT PH 2 - NORTH | 7 | CONSTRUCTION TO 75% | 2023-05-22 | 2023-09-18 | 2023-05-22 | 2023-09-18
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW19325B | 1 CENTRE ST.- 25TH FL BUILDOUT PH 2 - NORTH | 8 | ORIGINAL EQUIP & FURNISHING | 2023-09-19 | 2023-12-17 | 2023-09-19 | 2023-12-17
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW19325B | 1 CENTRE ST.- 25TH FL BUILDOUT PH 2 - NORTH | 9 | SUBSTANTIAL COMPLETION | 2023-12-18 | 2024-02-15 | 2023-12-18 | 2024-02-15
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW19325B | 1 CENTRE ST.- 25TH FL BUILDOUT PH 2 - NORTH | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-02-16 | 2024-03-16 | 2024-02-16 | 2024-03-16
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW193ALM | 1 CENTRE ST. - FIRE ALARM | 1 | DEVELOP SCOPE | 2006-11-01 | 2007-01-29 | 2005-06-15 | 2005-12-11
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW193ALM | 1 CENTRE ST. - FIRE ALARM | 2 | PRELIMINARY DESIGN | 2007-01-30 | 2007-01-31 | 2005-12-12 | 2006-06-09
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW193ALM | 1 CENTRE ST. - FIRE ALARM | 3 | FINAL DESIGN | 2007-02-01 | 2008-03-31 | 2006-06-10 | 2007-02-04
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW193ALM | 1 CENTRE ST. - FIRE ALARM | 4 | BID AWARD AND REGISTER CONTRCT | 2008-04-01 | 2008-06-30 | 2007-02-05 | 2007-09-12
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW193ALM | 1 CENTRE ST. - FIRE ALARM | 5 | CONSTRUCTION TO 25% | 2008-07-01 | 2008-09-30 | 2007-09-13 | 2009-05-24
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW193ALM | 1 CENTRE ST. - FIRE ALARM | 6 | CONSTRUCTION TO 50% | 2008-10-01 | 2008-12-31 | 2022-06-01 | 2024-01-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW193ALM | 1 CENTRE ST. - FIRE ALARM | 7 | CONSTRUCTION TO 75% | 2009-01-01 | 2009-03-31 | 2024-01-22 | 2025-08-23
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW193ALM | 1 CENTRE ST. - FIRE ALARM | 8 | ORIGINAL EQUIP & FURNISHING | 2009-04-01 | 2009-03-31 | 2023-08-24 | 2023-08-24
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW193ALM | 1 CENTRE ST. - FIRE ALARM | 9 | SUBSTANTIAL COMPLETION | 2009-04-01 | 2009-05-31 | 2023-08-25 | 2024-03-11
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW193ALM | 1 CENTRE ST. - FIRE ALARM | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2009-06-01 | 2009-06-30 | 2024-03-12 | 2024-03-13
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW193EV13 | 1 CENTRE ST - 13TH FL ELEVATOR REPAIR GROUP RELOCATION | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-08-29 | 2020-06-01 | 2020-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW193EV13 | 1 CENTRE ST - 13TH FL ELEVATOR REPAIR GROUP RELOCATION | 2 | PRELIMINARY DESIGN | 2020-08-30 | 2020-12-27 | 2020-08-30 | 2020-12-27
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW193EV13 | 1 CENTRE ST - 13TH FL ELEVATOR REPAIR GROUP RELOCATION | 3 | FINAL DESIGN | 2020-12-28 | 2021-06-25 | 2020-12-28 | 2021-06-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW193EV13 | 1 CENTRE ST - 13TH FL ELEVATOR REPAIR GROUP RELOCATION | 4 | BID AWARD AND REGISTER CONTRCT | 2021-06-26 | 2021-09-23 | 2021-06-26 | 2021-09-23
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW193EV13 | 1 CENTRE ST - 13TH FL ELEVATOR REPAIR GROUP RELOCATION | 5 | CONSTRUCTION TO 25% | 2021-09-24 | 2022-01-21 | 2021-09-24 | 2022-01-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW193EV13 | 1 CENTRE ST - 13TH FL ELEVATOR REPAIR GROUP RELOCATION | 6 | CONSTRUCTION TO 50% | 2022-01-22 | 2022-05-21 | 2022-01-22 | 2022-05-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW193EV13 | 1 CENTRE ST - 13TH FL ELEVATOR REPAIR GROUP RELOCATION | 7 | CONSTRUCTION TO 75% | 2022-05-22 | 2022-09-18 | 2022-05-22 | 2022-09-18
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW193EV13 | 1 CENTRE ST - 13TH FL ELEVATOR REPAIR GROUP RELOCATION | 8 | ORIGINAL EQUIP & FURNISHING | 2022-09-19 | 2022-12-17 | 2022-09-19 | 2022-12-17
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW193EV13 | 1 CENTRE ST - 13TH FL ELEVATOR REPAIR GROUP RELOCATION | 9 | SUBSTANTIAL COMPLETION | 2022-12-18 | 2023-02-15 | 2022-12-18 | 2023-02-15
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW193EV13 | 1 CENTRE ST - 13TH FL ELEVATOR REPAIR GROUP RELOCATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-02-16 | 2023-03-17 | 2023-02-16 | 2023-03-17
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW193FANS | 1 CENTRE ST. - REPLACEMENT OF LOBBY FANS | 1 | DEVELOP SCOPE | 2008-05-01 | 2008-07-29 | 1996-10-16 | 1997-01-13
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW193FANS | 1 CENTRE ST. - REPLACEMENT OF LOBBY FANS | 2 | PRELIMINARY DESIGN | 2008-07-30 | 2008-10-27 | 1997-01-14 | 1997-04-13
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW193FANS | 1 CENTRE ST. - REPLACEMENT OF LOBBY FANS | 3 | FINAL DESIGN | 2008-10-28 | 2009-01-25 | 1997-04-14 | 1997-07-12
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW193FANS | 1 CENTRE ST. - REPLACEMENT OF LOBBY FANS | 4 | BID AWARD AND REGISTER CONTRCT | 2009-01-26 | 2009-04-25 | 1997-07-13 | 1997-10-10
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW193FANS | 1 CENTRE ST. - REPLACEMENT OF LOBBY FANS | 5 | CONSTRUCTION TO 25% | 2009-04-26 | 2010-04-20 | 1997-10-11 | 1998-10-05
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW193FANS | 1 CENTRE ST. - REPLACEMENT OF LOBBY FANS | 6 | CONSTRUCTION TO 50% | 2010-04-21 | 2011-04-15 | 1998-10-06 | 1999-09-30
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW193FANS | 1 CENTRE ST. - REPLACEMENT OF LOBBY FANS | 7 | CONSTRUCTION TO 75% | 2011-04-16 | 2012-04-09 | 1999-10-01 | 2000-09-24
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW193FANS | 1 CENTRE ST. - REPLACEMENT OF LOBBY FANS | 8 | ORIGINAL EQUIP & FURNISHING | 2012-04-10 | 2013-04-04 | 2012-04-10 | 2013-04-04
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW193FANS | 1 CENTRE ST. - REPLACEMENT OF LOBBY FANS | 9 | SUBSTANTIAL COMPLETION | 2013-04-05 | 2014-03-30 | 2013-04-05 | 2014-03-30
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW193FANS | 1 CENTRE ST. - REPLACEMENT OF LOBBY FANS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-03-31 | 2014-12-15 | 2014-03-31 | 2026-06-30
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW193LB | 1 CENTRE ST. - HUMAN CAPITAL LONG BEACH | 1 | DEVELOP SCOPE | 2012-06-01 | 2012-08-29 | 2012-06-01 | 2012-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW193LB | 1 CENTRE ST. - HUMAN CAPITAL LONG BEACH | 2 | PRELIMINARY DESIGN | 2012-08-30 | 2012-12-27 | 2012-08-30 | 2012-12-27
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW193LB | 1 CENTRE ST. - HUMAN CAPITAL LONG BEACH | 3 | FINAL DESIGN | 2012-12-28 | 2013-06-25 | 2012-12-28 | 2013-06-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW193LB | 1 CENTRE ST. - HUMAN CAPITAL LONG BEACH | 4 | BID AWARD AND REGISTER CONTRCT | 2013-06-26 | 2013-09-23 | 2013-06-26 | 2013-09-23
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW193LB | 1 CENTRE ST. - HUMAN CAPITAL LONG BEACH | 5 | CONSTRUCTION TO 25% | 2013-09-24 | 2014-01-21 | 2013-09-24 | 2014-01-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW193LB | 1 CENTRE ST. - HUMAN CAPITAL LONG BEACH | 6 | CONSTRUCTION TO 50% | 2014-01-22 | 2014-05-21 | 2022-06-01 | 2022-09-28
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW193LB | 1 CENTRE ST. - HUMAN CAPITAL LONG BEACH | 7 | CONSTRUCTION TO 75% | 2014-05-22 | 2014-09-18 | 2022-09-29 | 2023-01-26
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW193LB | 1 CENTRE ST. - HUMAN CAPITAL LONG BEACH | 8 | ORIGINAL EQUIP & FURNISHING | 2014-09-19 | 2014-12-17 | 2023-01-27 | 2023-04-26
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW193LB | 1 CENTRE ST. - HUMAN CAPITAL LONG BEACH | 9 | SUBSTANTIAL COMPLETION | 2014-12-18 | 2015-02-15 | 2023-04-27 | 2023-06-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW193LB | 1 CENTRE ST. - HUMAN CAPITAL LONG BEACH | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-02-16 | 2015-03-17 | 2023-06-26 | 2023-07-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW193MOME | 1 CENTRE ST - MOME - A/C AND ANCILLARY WORK | 1 | DEVELOP SCOPE | 2016-03-01 | 2016-05-29 | 2011-12-01 | 2012-02-28
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW193MOME | 1 CENTRE ST - MOME - A/C AND ANCILLARY WORK | 2 | PRELIMINARY DESIGN | 2016-05-30 | 2016-09-26 | 2012-02-29 | 2012-06-27
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW193MOME | 1 CENTRE ST - MOME - A/C AND ANCILLARY WORK | 3 | FINAL DESIGN | 2016-09-27 | 2017-03-25 | 2012-06-28 | 2012-12-24
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW193MOME | 1 CENTRE ST - MOME - A/C AND ANCILLARY WORK | 4 | BID AWARD AND REGISTER CONTRCT | 2017-03-26 | 2017-06-23 | 2012-12-25 | 2013-03-24
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW193MOME | 1 CENTRE ST - MOME - A/C AND ANCILLARY WORK | 5 | CONSTRUCTION TO 25% | 2017-06-24 | 2017-10-21 | 2013-03-25 | 2013-07-22
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW193MOME | 1 CENTRE ST - MOME - A/C AND ANCILLARY WORK | 6 | CONSTRUCTION TO 50% | 2017-10-22 | 2018-02-18 | 2013-07-23 | 2013-11-19
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW193MOME | 1 CENTRE ST - MOME - A/C AND ANCILLARY WORK | 7 | CONSTRUCTION TO 75% | 2018-02-19 | 2018-06-18 | 2013-11-20 | 2014-03-19
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW193MOME | 1 CENTRE ST - MOME - A/C AND ANCILLARY WORK | 8 | ORIGINAL EQUIP & FURNISHING | 2018-06-19 | 2018-09-16 | 2018-06-19 | 2018-09-16
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW193MOME | 1 CENTRE ST - MOME - A/C AND ANCILLARY WORK | 9 | SUBSTANTIAL COMPLETION | 2018-09-17 | 2018-11-15 | 2018-09-17 | 2018-11-15
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW193MOME | 1 CENTRE ST - MOME - A/C AND ANCILLARY WORK | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-11-16 | 2018-12-15 | 2018-11-16 | 2027-06-30
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW195ADA | 80 CENTRE ST - ADA LIFT | 1 | DEVELOP SCOPE | 2021-06-01 | 2021-08-29 | 2021-06-01 | 2021-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW195ADA | 80 CENTRE ST - ADA LIFT | 2 | PRELIMINARY DESIGN | 2021-08-30 | 2021-12-27 | 2021-08-30 | 2021-12-27
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW195ADA | 80 CENTRE ST - ADA LIFT | 3 | FINAL DESIGN | 2021-12-28 | 2022-06-25 | 2021-12-28 | 2022-06-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW195ADA | 80 CENTRE ST - ADA LIFT | 4 | BID AWARD AND REGISTER CONTRCT | 2022-06-26 | 2022-09-23 | 2022-06-26 | 2022-09-23
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW195ADA | 80 CENTRE ST - ADA LIFT | 5 | CONSTRUCTION TO 25% | 2022-09-24 | 2023-01-21 | 2022-09-24 | 2023-01-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW195ADA | 80 CENTRE ST - ADA LIFT | 6 | CONSTRUCTION TO 50% | 2023-01-22 | 2023-05-21 | 2023-01-22 | 2023-05-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW195ADA | 80 CENTRE ST - ADA LIFT | 7 | CONSTRUCTION TO 75% | 2023-05-22 | 2023-09-18 | 2023-05-22 | 2023-09-18
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW195ADA | 80 CENTRE ST - ADA LIFT | 8 | ORIGINAL EQUIP & FURNISHING | 2023-09-19 | 2023-12-17 | 2023-09-19 | 2023-12-17
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW195ADA | 80 CENTRE ST - ADA LIFT | 9 | SUBSTANTIAL COMPLETION | 2023-12-18 | 2024-02-15 | 2023-12-18 | 2024-02-15
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW195ADA | 80 CENTRE ST - ADA LIFT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-02-16 | 2024-03-16 | 2024-02-16 | 2024-03-16
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW195RF | 80 CENTRE ST.- ROOF REPLACEMENT | 1 | DEVELOP SCOPE | 2022-06-01 | 2022-08-29 | 2022-06-01 | 2022-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW195RF | 80 CENTRE ST.- ROOF REPLACEMENT | 2 | PRELIMINARY DESIGN | 2022-08-30 | 2022-12-27 | 2022-08-30 | 2022-12-27
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW195RF | 80 CENTRE ST.- ROOF REPLACEMENT | 3 | FINAL DESIGN | 2022-12-28 | 2023-06-25 | 2022-12-28 | 2023-06-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW195RF | 80 CENTRE ST.- ROOF REPLACEMENT | 4 | BID AWARD AND REGISTER CONTRCT | 2023-06-26 | 2023-09-23 | 2023-06-26 | 2023-09-23
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW195RF | 80 CENTRE ST.- ROOF REPLACEMENT | 5 | CONSTRUCTION TO 25% | 2023-09-24 | 2024-01-21 | 2023-09-24 | 2024-01-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW195RF | 80 CENTRE ST.- ROOF REPLACEMENT | 6 | CONSTRUCTION TO 50% | 2024-01-22 | 2024-05-20 | 2024-01-22 | 2024-05-20
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW195RF | 80 CENTRE ST.- ROOF REPLACEMENT | 7 | CONSTRUCTION TO 75% | 2024-05-21 | 2024-09-17 | 2024-05-21 | 2024-09-17
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW195RF | 80 CENTRE ST.- ROOF REPLACEMENT | 8 | ORIGINAL EQUIP & FURNISHING | 2024-09-18 | 2024-12-16 | 2024-09-18 | 2024-12-16
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW195RF | 80 CENTRE ST.- ROOF REPLACEMENT | 9 | SUBSTANTIAL COMPLETION | 2024-12-17 | 2025-02-14 | 2024-12-17 | 2025-02-14
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW195RF | 80 CENTRE ST.- ROOF REPLACEMENT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-02-15 | 2026-03-16 | 2025-02-15 | 2026-03-16
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW266TOIL | 125 WORTH ST.- CODE COMPLIANT TOILET UPGRADES | 1 | DEVELOP SCOPE | 2016-01-01 | 2016-04-29 | 2021-06-01 | 2021-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW266TOIL | 125 WORTH ST.- CODE COMPLIANT TOILET UPGRADES | 2 | BID AWARD AND REGISTER CONTRCT | 2016-04-30 | 2016-10-26 | 2021-08-30 | 2021-12-27
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW266TOIL | 125 WORTH ST.- CODE COMPLIANT TOILET UPGRADES | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-10-27 | 2016-11-25 | 2021-12-28 | 2022-06-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW266TOIL | 125 WORTH ST.- CODE COMPLIANT TOILET UPGRADES | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-12-26 | 2017-01-24 | 2022-06-26 | 2022-09-23
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW266TOIL | 125 WORTH ST.- CODE COMPLIANT TOILET UPGRADES | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-11-26 | 2016-12-25 | 2022-09-24 | 2023-01-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW266TOIL | 125 WORTH ST.- CODE COMPLIANT TOILET UPGRADES | 6 | CONSTRUCTION TO 50% | 2016-11-26 | 2016-12-25 | 2023-01-22 | 2023-05-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW266TOIL | 125 WORTH ST.- CODE COMPLIANT TOILET UPGRADES | 7 | CONSTRUCTION TO 75% | 2016-11-26 | 2016-12-25 | 2023-05-22 | 2023-09-18
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW266TOIL | 125 WORTH ST.- CODE COMPLIANT TOILET UPGRADES | 8 | ORIGINAL EQUIP & FURNISHING | 2016-11-26 | 2016-12-25 | 2023-09-19 | 2023-12-17
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW266TOIL | 125 WORTH ST.- CODE COMPLIANT TOILET UPGRADES | 9 | SUBSTANTIAL COMPLETION | 2016-11-26 | 2016-12-25 | 2023-12-18 | 2024-02-15
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW266TOIL | 125 WORTH ST.- CODE COMPLIANT TOILET UPGRADES | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-11-26 | 2016-12-25 | 2024-02-16 | 2024-03-16
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW293125D | 125 WORTH STREET - FIRE ALARM -SPRINKLERS | 1 | DEVELOP SCOPE | 2021-06-01 | 2021-08-29 | 2021-06-01 | 2021-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW293125D | 125 WORTH STREET - FIRE ALARM -SPRINKLERS | 2 | PRELIMINARY DESIGN | 2021-08-30 | 2021-12-27 | 2021-08-30 | 2021-12-27
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW293125D | 125 WORTH STREET - FIRE ALARM -SPRINKLERS | 3 | FINAL DESIGN | 2021-12-28 | 2022-06-25 | 2021-12-28 | 2022-06-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW293125D | 125 WORTH STREET - FIRE ALARM -SPRINKLERS | 4 | BID AWARD AND REGISTER CONTRCT | 2022-06-26 | 2022-09-23 | 2022-06-26 | 2022-09-23
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW293125D | 125 WORTH STREET - FIRE ALARM -SPRINKLERS | 5 | CONSTRUCTION TO 25% | 2022-09-24 | 2023-01-21 | 2022-09-24 | 2023-01-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW293125D | 125 WORTH STREET - FIRE ALARM -SPRINKLERS | 6 | CONSTRUCTION TO 50% | 2023-01-22 | 2023-05-21 | 2023-01-22 | 2023-05-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW293125D | 125 WORTH STREET - FIRE ALARM -SPRINKLERS | 7 | CONSTRUCTION TO 75% | 2023-05-22 | 2023-09-18 | 2023-05-22 | 2023-09-18
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW293125D | 125 WORTH STREET - FIRE ALARM -SPRINKLERS | 8 | ORIGINAL EQUIP & FURNISHING | 2023-09-19 | 2023-12-17 | 2023-09-19 | 2023-12-17
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW293125D | 125 WORTH STREET - FIRE ALARM -SPRINKLERS | 9 | SUBSTANTIAL COMPLETION | 2023-12-18 | 2024-02-15 | 2023-12-18 | 2024-02-15
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW293125D | 125 WORTH STREET - FIRE ALARM -SPRINKLERS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-02-16 | 2024-03-16 | 2024-02-16 | 2024-03-16
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW2931C | 1 CENTRE STREET - FIRE SPRINKLERS | 1 | DEVELOP SCOPE | 2019-06-30 | 2019-09-27 | 2019-06-01 | 2019-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW2931C | 1 CENTRE STREET - FIRE SPRINKLERS | 2 | PRELIMINARY DESIGN | 2019-09-28 | 2020-01-25 | 2019-08-30 | 2019-12-27
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW2931C | 1 CENTRE STREET - FIRE SPRINKLERS | 3 | FINAL DESIGN | 2020-01-26 | 2020-07-23 | 2019-12-28 | 2020-06-24
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW2931C | 1 CENTRE STREET - FIRE SPRINKLERS | 4 | BID AWARD AND REGISTER CONTRCT | 2020-07-24 | 2020-10-21 | 2024-06-01 | 2024-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW2931C | 1 CENTRE STREET - FIRE SPRINKLERS | 5 | CONSTRUCTION TO 25% | 2020-10-22 | 2021-02-18 | 2024-08-30 | 2024-12-27
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW2931C | 1 CENTRE STREET - FIRE SPRINKLERS | 6 | CONSTRUCTION TO 50% | 2021-02-19 | 2021-06-18 | 2024-12-28 | 2025-04-26
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW2931C | 1 CENTRE STREET - FIRE SPRINKLERS | 7 | CONSTRUCTION TO 75% | 2021-06-19 | 2021-10-16 | 2025-04-27 | 2025-08-24
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW2931C | 1 CENTRE STREET - FIRE SPRINKLERS | 8 | ORIGINAL EQUIP & FURNISHING | 2021-10-17 | 2022-01-14 | 2021-09-18 | 2021-12-16
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW2931C | 1 CENTRE STREET - FIRE SPRINKLERS | 9 | SUBSTANTIAL COMPLETION | 2022-01-15 | 2022-03-15 | 2021-12-17 | 2022-02-14
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW2931C | 1 CENTRE STREET - FIRE SPRINKLERS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-16 | 2022-04-14 | 2022-02-15 | 2025-03-16
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW308PS1 | MAYOR'S OFFICE - 100 GOLD ST - PRINTSHOP UPGRADE | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-08-29 | 2020-06-01 | 2020-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW308PS1 | MAYOR'S OFFICE - 100 GOLD ST - PRINTSHOP UPGRADE | 2 | PRELIMINARY DESIGN | 2020-08-30 | 2020-12-27 | 2020-08-30 | 2020-12-27
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW308PS1 | MAYOR'S OFFICE - 100 GOLD ST - PRINTSHOP UPGRADE | 3 | FINAL DESIGN | 2020-12-28 | 2021-06-25 | 2020-12-28 | 2021-06-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW308PS1 | MAYOR'S OFFICE - 100 GOLD ST - PRINTSHOP UPGRADE | 4 | BID AWARD AND REGISTER CONTRCT | 2021-06-26 | 2021-09-23 | 2021-06-26 | 2021-09-23
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW308PS1 | MAYOR'S OFFICE - 100 GOLD ST - PRINTSHOP UPGRADE | 5 | CONSTRUCTION TO 25% | 2021-09-24 | 2022-01-21 | 2021-09-24 | 2022-01-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW308PS1 | MAYOR'S OFFICE - 100 GOLD ST - PRINTSHOP UPGRADE | 6 | CONSTRUCTION TO 50% | 2022-01-22 | 2022-05-21 | 2022-01-22 | 2022-05-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW308PS1 | MAYOR'S OFFICE - 100 GOLD ST - PRINTSHOP UPGRADE | 7 | CONSTRUCTION TO 75% | 2022-05-22 | 2022-09-18 | 2022-05-22 | 2022-09-18
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW308PS1 | MAYOR'S OFFICE - 100 GOLD ST - PRINTSHOP UPGRADE | 8 | ORIGINAL EQUIP & FURNISHING | 2022-09-19 | 2022-12-17 | 2022-09-19 | 2022-12-17
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW308PS1 | MAYOR'S OFFICE - 100 GOLD ST - PRINTSHOP UPGRADE | 9 | SUBSTANTIAL COMPLETION | 2022-12-18 | 2023-02-15 | 2022-12-18 | 2023-02-15
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW308PS1 | MAYOR'S OFFICE - 100 GOLD ST - PRINTSHOP UPGRADE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-02-16 | 2023-03-17 | 2023-02-16 | 2023-03-17
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW310COOL | 31 CHAMBERS ST.- COLD STORAGE SYSTEM FOR DORIS | 1 | DEVELOP SCOPE | 2006-06-30 | 2006-09-27 | 2016-06-01 | 2016-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW310COOL | 31 CHAMBERS ST.- COLD STORAGE SYSTEM FOR DORIS | 2 | PRELIMINARY DESIGN | 2006-09-28 | 2007-01-25 | 2016-08-30 | 2016-12-27
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW310COOL | 31 CHAMBERS ST.- COLD STORAGE SYSTEM FOR DORIS | 3 | FINAL DESIGN | 2007-01-26 | 2007-07-24 | 2016-12-28 | 2017-06-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW310COOL | 31 CHAMBERS ST.- COLD STORAGE SYSTEM FOR DORIS | 4 | BID AWARD AND REGISTER CONTRCT | 2007-07-25 | 2007-10-22 | 2017-06-26 | 2017-09-23
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW310COOL | 31 CHAMBERS ST.- COLD STORAGE SYSTEM FOR DORIS | 5 | CONSTRUCTION TO 25% | 2007-10-23 | 2008-02-19 | 2017-09-24 | 2018-01-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW310COOL | 31 CHAMBERS ST.- COLD STORAGE SYSTEM FOR DORIS | 6 | CONSTRUCTION TO 50% | 2008-02-20 | 2008-06-18 | 2018-01-22 | 2018-05-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW310COOL | 31 CHAMBERS ST.- COLD STORAGE SYSTEM FOR DORIS | 7 | CONSTRUCTION TO 75% | 2008-06-19 | 2008-10-16 | 2018-05-22 | 2018-09-18
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW310COOL | 31 CHAMBERS ST.- COLD STORAGE SYSTEM FOR DORIS | 8 | ORIGINAL EQUIP & FURNISHING | 2008-10-17 | 2009-01-14 | 2018-09-19 | 2018-12-17
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW310COOL | 31 CHAMBERS ST.- COLD STORAGE SYSTEM FOR DORIS | 9 | SUBSTANTIAL COMPLETION | 2009-01-15 | 2009-03-15 | 2018-12-18 | 2019-02-15
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW310COOL | 31 CHAMBERS ST.- COLD STORAGE SYSTEM FOR DORIS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2009-03-16 | 2009-04-14 | 2019-02-16 | 2027-06-30
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW310FAN | 31 CHAMBERS ST. - REPLACEMENT OF FAN COIL UNITS ON FIRST FL. | 1 | DEVELOP SCOPE | 2007-01-01 | 2007-02-28 | 2007-01-01 | 2007-03-31
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW310FAN | 31 CHAMBERS ST. - REPLACEMENT OF FAN COIL UNITS ON FIRST FL. | 2 | PRELIMINARY DESIGN | 2007-03-01 | 2007-05-31 | 2007-04-01 | 2007-07-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW310FAN | 31 CHAMBERS ST. - REPLACEMENT OF FAN COIL UNITS ON FIRST FL. | 3 | FINAL DESIGN | 2007-06-01 | 2008-05-31 | 2007-07-30 | 2008-01-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW310FAN | 31 CHAMBERS ST. - REPLACEMENT OF FAN COIL UNITS ON FIRST FL. | 4 | BID AWARD AND REGISTER CONTRCT | 2008-06-01 | 2008-10-31 | 2008-01-26 | 2008-04-24
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW310FAN | 31 CHAMBERS ST. - REPLACEMENT OF FAN COIL UNITS ON FIRST FL. | 5 | CONSTRUCTION TO 25% | 2008-11-01 | 2008-12-31 | 2008-04-25 | 2010-12-10
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW310FAN | 31 CHAMBERS ST. - REPLACEMENT OF FAN COIL UNITS ON FIRST FL. | 6 | CONSTRUCTION TO 50% | 2009-01-01 | 2009-02-28 | 2010-12-11 | 2013-07-27
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW310FAN | 31 CHAMBERS ST. - REPLACEMENT OF FAN COIL UNITS ON FIRST FL. | 7 | CONSTRUCTION TO 75% | 2009-03-01 | 2009-03-31 | 2013-07-28 | 2016-03-13
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW310FAN | 31 CHAMBERS ST. - REPLACEMENT OF FAN COIL UNITS ON FIRST FL. | 8 | ORIGINAL EQUIP & FURNISHING | 2009-04-01 | 2009-03-31 | 2016-03-14 | 2016-09-09
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW310FAN | 31 CHAMBERS ST. - REPLACEMENT OF FAN COIL UNITS ON FIRST FL. | 9 | SUBSTANTIAL COMPLETION | 2009-04-01 | 2009-05-31 | 2016-09-10 | 2016-12-08
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW310FAN | 31 CHAMBERS ST. - REPLACEMENT OF FAN COIL UNITS ON FIRST FL. | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2009-06-01 | 2009-06-30 | 2016-12-09 | 2025-03-16
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW324OMIS | DCAS IT LUMP SUM | 1 | DEVELOP SCOPE | 2004-06-01 | 2004-08-29 | 2004-06-01 | 2004-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW324OMIS | DCAS IT LUMP SUM | 2 | PRELIMINARY DESIGN | 2004-08-30 | 2004-12-27 | 2004-08-30 | 2004-12-27
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW324OMIS | DCAS IT LUMP SUM | 3 | FINAL DESIGN | 2004-12-28 | 2005-06-25 | 2004-12-28 | 2005-06-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW324OMIS | DCAS IT LUMP SUM | 4 | BID AWARD AND REGISTER CONTRCT | 2005-06-26 | 2005-09-23 | 2005-06-26 | 2005-09-23
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW324OMIS | DCAS IT LUMP SUM | 5 | CONSTRUCTION TO 25% | 2005-09-24 | 2008-05-10 | 2005-09-24 | 2008-05-10
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW324OMIS | DCAS IT LUMP SUM | 6 | CONSTRUCTION TO 50% | 2008-05-11 | 2010-12-26 | 2008-05-11 | 2010-12-26
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW324OMIS | DCAS IT LUMP SUM | 7 | CONSTRUCTION TO 75% | 2010-12-27 | 2013-08-12 | 2010-12-27 | 2013-08-12
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW324OMIS | DCAS IT LUMP SUM | 8 | ORIGINAL EQUIP & FURNISHING | 2013-08-13 | 2016-03-29 | 2013-08-13 | 2016-03-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW324OMIS | DCAS IT LUMP SUM | 9 | SUBSTANTIAL COMPLETION | 2016-03-30 | 2018-11-14 | 2016-03-30 | 2018-11-14
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW324OMIS | DCAS IT LUMP SUM | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-11-15 | 2021-07-01 | 2018-11-15 | 2021-07-01
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW32671T | OCA LEASE RENEWAL AT 151 WEST BROADWAY/71 THOMAS St | 1 | DEVELOP SCOPE | 2015-01-01 | 2015-03-31 | 2025-06-01 | 2025-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW32671T | OCA LEASE RENEWAL AT 151 WEST BROADWAY/71 THOMAS St | 2 | PRELIMINARY DESIGN | 2015-04-01 | 2015-07-29 | 2025-08-30 | 2025-12-27
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW32671T | OCA LEASE RENEWAL AT 151 WEST BROADWAY/71 THOMAS St | 3 | FINAL DESIGN | 2015-07-30 | 2016-01-25 | 2025-12-28 | 2026-06-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW32671T | OCA LEASE RENEWAL AT 151 WEST BROADWAY/71 THOMAS St | 4 | BID AWARD AND REGISTER CONTRCT | 2016-01-26 | 2016-04-24 | 2026-06-26 | 2026-09-23
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW32671T | OCA LEASE RENEWAL AT 151 WEST BROADWAY/71 THOMAS St | 5 | CONSTRUCTION TO 25% | 2016-04-25 | 2016-08-22 | 2026-09-24 | 2027-01-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW32671T | OCA LEASE RENEWAL AT 151 WEST BROADWAY/71 THOMAS St | 6 | CONSTRUCTION TO 50% | 2016-08-23 | 2016-12-20 | 2027-01-22 | 2027-05-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW32671T | OCA LEASE RENEWAL AT 151 WEST BROADWAY/71 THOMAS St | 7 | CONSTRUCTION TO 75% | 2016-12-21 | 2017-04-19 | 2027-05-22 | 2027-09-18
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW32671T | OCA LEASE RENEWAL AT 151 WEST BROADWAY/71 THOMAS St | 8 | ORIGINAL EQUIP & FURNISHING | 2017-04-20 | 2017-07-18 | 2027-09-19 | 2027-12-17
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW32671T | OCA LEASE RENEWAL AT 151 WEST BROADWAY/71 THOMAS St | 9 | SUBSTANTIAL COMPLETION | 2017-07-19 | 2017-09-16 | 2027-12-18 | 2028-02-15
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW32671T | OCA LEASE RENEWAL AT 151 WEST BROADWAY/71 THOMAS St | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-09-17 | 2017-10-16 | 2028-02-16 | 2028-03-16
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326NYCC | CITY COUNCIL - 250 BROADWAY, FLS 14-18, 30 RENO & EXPANSION | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-08-29 | 2026-06-01 | 2026-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326NYCC | CITY COUNCIL - 250 BROADWAY, FLS 14-18, 30 RENO & EXPANSION | 2 | PRELIMINARY DESIGN | 2020-08-30 | 2020-12-27 | 2026-08-30 | 2026-12-27
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326NYCC | CITY COUNCIL - 250 BROADWAY, FLS 14-18, 30 RENO & EXPANSION | 3 | FINAL DESIGN | 2020-12-28 | 2021-06-25 | 2026-12-28 | 2027-06-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326NYCC | CITY COUNCIL - 250 BROADWAY, FLS 14-18, 30 RENO & EXPANSION | 4 | BID AWARD AND REGISTER CONTRCT | 2021-06-26 | 2021-09-23 | 2027-06-26 | 2027-09-23
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326NYCC | CITY COUNCIL - 250 BROADWAY, FLS 14-18, 30 RENO & EXPANSION | 5 | CONSTRUCTION TO 25% | 2021-09-24 | 2022-01-21 | 2027-09-24 | 2028-01-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326NYCC | CITY COUNCIL - 250 BROADWAY, FLS 14-18, 30 RENO & EXPANSION | 6 | CONSTRUCTION TO 50% | 2022-01-22 | 2022-05-21 | 2028-01-22 | 2028-05-20
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326NYCC | CITY COUNCIL - 250 BROADWAY, FLS 14-18, 30 RENO & EXPANSION | 7 | CONSTRUCTION TO 75% | 2022-05-22 | 2022-09-18 | 2028-05-21 | 2028-09-17
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326NYCC | CITY COUNCIL - 250 BROADWAY, FLS 14-18, 30 RENO & EXPANSION | 8 | ORIGINAL EQUIP & FURNISHING | 2022-09-19 | 2022-12-17 | 2028-09-18 | 2028-12-16
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326NYCC | CITY COUNCIL - 250 BROADWAY, FLS 14-18, 30 RENO & EXPANSION | 9 | SUBSTANTIAL COMPLETION | 2022-12-18 | 2023-02-15 | 2028-12-17 | 2029-02-14
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326NYCC | CITY COUNCIL - 250 BROADWAY, FLS 14-18, 30 RENO & EXPANSION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-02-16 | 2023-03-17 | 2029-02-15 | 2029-03-16
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326OMBP | OMB Pantry at 255 Greenwich | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-09-28 | 2020-06-01 | 2020-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326OMBP | OMB Pantry at 255 Greenwich | 2 | BID AWARD AND REGISTER CONTRCT | 2020-09-29 | 2021-03-27 | 2020-08-30 | 2020-12-27
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326OMBP | OMB Pantry at 255 Greenwich | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-28 | 2021-04-26 | 2020-12-28 | 2021-06-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326OMBP | OMB Pantry at 255 Greenwich | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-05-27 | 2021-06-25 | 2021-06-26 | 2021-09-23
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326OMBP | OMB Pantry at 255 Greenwich | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-04-27 | 2021-05-26 | 2021-09-24 | 2022-01-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326OMBP | OMB Pantry at 255 Greenwich | 6 | CONSTRUCTION TO 50% | 2021-04-27 | 2021-05-26 | 2022-01-22 | 2022-05-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326OMBP | OMB Pantry at 255 Greenwich | 7 | CONSTRUCTION TO 75% | 2021-04-27 | 2021-05-26 | 2022-05-22 | 2022-09-18
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326OMBP | OMB Pantry at 255 Greenwich | 8 | ORIGINAL EQUIP & FURNISHING | 2021-04-27 | 2021-05-26 | 2022-09-19 | 2022-12-17
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326OMBP | OMB Pantry at 255 Greenwich | 9 | SUBSTANTIAL COMPLETION | 2021-04-27 | 2021-05-26 | 2022-12-18 | 2023-02-15
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326OMBP | OMB Pantry at 255 Greenwich | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-04-27 | 2021-05-26 | 2023-02-16 | 2023-03-17
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RAM | LAW DEPT - RAISE THE AGE - MANHATTAN | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-08-29 | 2020-06-01 | 2020-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RAM | LAW DEPT - RAISE THE AGE - MANHATTAN | 2 | PRELIMINARY DESIGN | 2020-08-30 | 2020-12-27 | 2020-08-30 | 2020-12-27
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RAM | LAW DEPT - RAISE THE AGE - MANHATTAN | 3 | FINAL DESIGN | 2020-12-28 | 2021-06-25 | 2020-12-28 | 2021-06-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RAM | LAW DEPT - RAISE THE AGE - MANHATTAN | 4 | BID AWARD AND REGISTER CONTRCT | 2021-06-26 | 2021-09-23 | 2021-06-26 | 2021-09-23
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RAM | LAW DEPT - RAISE THE AGE - MANHATTAN | 5 | CONSTRUCTION TO 25% | 2021-09-24 | 2022-01-21 | 2021-09-24 | 2022-01-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RAM | LAW DEPT - RAISE THE AGE - MANHATTAN | 6 | CONSTRUCTION TO 50% | 2022-01-22 | 2022-05-21 | 2022-01-22 | 2022-05-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RAM | LAW DEPT - RAISE THE AGE - MANHATTAN | 7 | CONSTRUCTION TO 75% | 2022-05-22 | 2022-09-18 | 2022-05-22 | 2022-09-18
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RAM | LAW DEPT - RAISE THE AGE - MANHATTAN | 8 | ORIGINAL EQUIP & FURNISHING | 2022-09-19 | 2022-12-17 | 2022-09-19 | 2022-12-17
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RAM | LAW DEPT - RAISE THE AGE - MANHATTAN | 9 | SUBSTANTIAL COMPLETION | 2022-12-18 | 2023-02-15 | 2022-12-18 | 2023-02-15
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RAM | LAW DEPT - RAISE THE AGE - MANHATTAN | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-02-16 | 2023-03-17 | 2023-02-16 | 2023-03-17
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RE40 | 100 GOLD ST.- TENANT RELOCATION FROM 40 RECTOR | 1 | DEVELOP SCOPE | 2010-09-15 | 2010-12-13 | 2010-09-15 | 2010-12-13
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RE40 | 100 GOLD ST.- TENANT RELOCATION FROM 40 RECTOR | 2 | PRELIMINARY DESIGN | 2010-12-14 | 2011-04-12 | 2010-12-14 | 2011-04-12
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RE40 | 100 GOLD ST.- TENANT RELOCATION FROM 40 RECTOR | 3 | FINAL DESIGN | 2011-04-13 | 2011-10-09 | 2011-04-13 | 2011-10-09
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RE40 | 100 GOLD ST.- TENANT RELOCATION FROM 40 RECTOR | 4 | BID AWARD AND REGISTER CONTRCT | 2011-10-10 | 2012-01-07 | 2011-10-10 | 2012-01-07
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RE40 | 100 GOLD ST.- TENANT RELOCATION FROM 40 RECTOR | 5 | CONSTRUCTION TO 25% | 2012-01-08 | 2012-05-06 | 2012-01-08 | 2012-05-06
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RE40 | 100 GOLD ST.- TENANT RELOCATION FROM 40 RECTOR | 6 | CONSTRUCTION TO 50% | 2012-05-07 | 2012-09-03 | 2022-06-01 | 2022-09-28
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RE40 | 100 GOLD ST.- TENANT RELOCATION FROM 40 RECTOR | 7 | CONSTRUCTION TO 75% | 2012-09-04 | 2013-01-01 | 2022-09-29 | 2023-01-26
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RE40 | 100 GOLD ST.- TENANT RELOCATION FROM 40 RECTOR | 8 | ORIGINAL EQUIP & FURNISHING | 2013-01-02 | 2013-04-01 | 2023-01-27 | 2023-04-26
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RE40 | 100 GOLD ST.- TENANT RELOCATION FROM 40 RECTOR | 9 | SUBSTANTIAL COMPLETION | 2013-04-02 | 2013-05-31 | 2023-04-27 | 2023-06-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RE40 | 100 GOLD ST.- TENANT RELOCATION FROM 40 RECTOR | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-06-01 | 2013-06-30 | 2023-06-26 | 2023-07-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326ZM03 | CBMN - RELOCATE COMM BD 3 FROM 59 E. 4TH STREET | 1 | DEVELOP SCOPE | 2014-09-01 | 2014-11-29 | 2026-06-01 | 2026-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326ZM03 | CBMN - RELOCATE COMM BD 3 FROM 59 E. 4TH STREET | 2 | PRELIMINARY DESIGN | 2014-11-30 | 2015-03-29 | 2026-08-30 | 2026-12-27
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326ZM03 | CBMN - RELOCATE COMM BD 3 FROM 59 E. 4TH STREET | 3 | FINAL DESIGN | 2015-03-30 | 2015-09-25 | 2026-12-28 | 2027-06-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326ZM03 | CBMN - RELOCATE COMM BD 3 FROM 59 E. 4TH STREET | 4 | BID AWARD AND REGISTER CONTRCT | 2015-09-26 | 2015-12-24 | 2027-06-26 | 2027-09-23
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326ZM03 | CBMN - RELOCATE COMM BD 3 FROM 59 E. 4TH STREET | 5 | CONSTRUCTION TO 25% | 2015-12-25 | 2016-04-22 | 2027-09-24 | 2028-01-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326ZM03 | CBMN - RELOCATE COMM BD 3 FROM 59 E. 4TH STREET | 6 | CONSTRUCTION TO 50% | 2016-04-23 | 2016-08-20 | 2028-01-22 | 2028-05-20
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326ZM03 | CBMN - RELOCATE COMM BD 3 FROM 59 E. 4TH STREET | 7 | CONSTRUCTION TO 75% | 2016-08-21 | 2016-12-18 | 2028-05-21 | 2028-09-17
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326ZM03 | CBMN - RELOCATE COMM BD 3 FROM 59 E. 4TH STREET | 8 | ORIGINAL EQUIP & FURNISHING | 2016-12-19 | 2017-03-18 | 2028-09-18 | 2028-12-16
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326ZM03 | CBMN - RELOCATE COMM BD 3 FROM 59 E. 4TH STREET | 9 | SUBSTANTIAL COMPLETION | 2017-03-19 | 2017-05-17 | 2028-12-17 | 2029-02-14
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326ZM03 | CBMN - RELOCATE COMM BD 3 FROM 59 E. 4TH STREET | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-05-18 | 2017-06-16 | 2029-02-15 | 2029-03-16
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326ZM09 | CBMN - MANHATTAN COMMUNITY BOARD 9 | 1 | DEVELOP SCOPE | 2014-09-01 | 2014-11-29 | 2020-06-01 | 2020-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326ZM09 | CBMN - MANHATTAN COMMUNITY BOARD 9 | 2 | PRELIMINARY DESIGN | 2014-11-30 | 2015-03-29 | 2020-08-30 | 2020-12-27
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326ZM09 | CBMN - MANHATTAN COMMUNITY BOARD 9 | 3 | FINAL DESIGN | 2015-03-30 | 2015-09-25 | 2020-12-28 | 2021-06-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326ZM09 | CBMN - MANHATTAN COMMUNITY BOARD 9 | 4 | BID AWARD AND REGISTER CONTRCT | 2015-09-26 | 2015-12-24 | 2021-06-26 | 2021-09-23
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326ZM09 | CBMN - MANHATTAN COMMUNITY BOARD 9 | 5 | CONSTRUCTION TO 25% | 2015-12-25 | 2016-04-22 | 2021-09-24 | 2022-01-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326ZM09 | CBMN - MANHATTAN COMMUNITY BOARD 9 | 6 | CONSTRUCTION TO 50% | 2016-04-23 | 2016-08-20 | 2022-01-22 | 2022-05-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326ZM09 | CBMN - MANHATTAN COMMUNITY BOARD 9 | 7 | CONSTRUCTION TO 75% | 2016-08-21 | 2016-12-18 | 2022-05-22 | 2022-09-18
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326ZM09 | CBMN - MANHATTAN COMMUNITY BOARD 9 | 8 | ORIGINAL EQUIP & FURNISHING | 2016-12-19 | 2017-03-18 | 2020-06-01 | 2020-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326ZM09 | CBMN - MANHATTAN COMMUNITY BOARD 9 | 9 | SUBSTANTIAL COMPLETION | 2017-03-19 | 2017-05-17 | 2020-08-30 | 2020-10-28
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326ZM09 | CBMN - MANHATTAN COMMUNITY BOARD 9 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-05-18 | 2017-06-16 | 2020-10-29 | 2020-11-27
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW327PLZ2 | 1 CENTRE STREET PLAZA REHABILITATION | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-08-29 | 2020-06-01 | 2020-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW327PLZ2 | 1 CENTRE STREET PLAZA REHABILITATION | 2 | PRELIMINARY DESIGN | 2020-08-30 | 2020-12-27 | 2020-08-30 | 2020-12-27
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW327PLZ2 | 1 CENTRE STREET PLAZA REHABILITATION | 3 | FINAL DESIGN | 2020-12-28 | 2021-06-25 | 2020-12-28 | 2021-06-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW327PLZ2 | 1 CENTRE STREET PLAZA REHABILITATION | 4 | BID AWARD AND REGISTER CONTRCT | 2021-06-26 | 2021-09-23 | 2021-06-26 | 2021-09-23
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW327PLZ2 | 1 CENTRE STREET PLAZA REHABILITATION | 5 | CONSTRUCTION TO 25% | 2021-09-24 | 2022-01-21 | 2024-06-01 | 2024-09-28
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW327PLZ2 | 1 CENTRE STREET PLAZA REHABILITATION | 6 | CONSTRUCTION TO 50% | 2022-01-22 | 2022-05-21 | 2024-09-29 | 2025-01-26
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW327PLZ2 | 1 CENTRE STREET PLAZA REHABILITATION | 7 | CONSTRUCTION TO 75% | 2022-05-22 | 2022-09-18 | 2025-01-27 | 2025-05-26
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW327PLZ2 | 1 CENTRE STREET PLAZA REHABILITATION | 8 | ORIGINAL EQUIP & FURNISHING | 2022-09-19 | 2022-12-17 | 2025-05-27 | 2025-08-24
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW327PLZ2 | 1 CENTRE STREET PLAZA REHABILITATION | 9 | SUBSTANTIAL COMPLETION | 2022-12-18 | 2023-02-15 | 2025-08-25 | 2025-10-23
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW327PLZ2 | 1 CENTRE STREET PLAZA REHABILITATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-02-16 | 2023-03-17 | 2025-10-24 | 2025-11-22
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW340FIP2 | BOE- FACILITIES IMPROVEMENT PROJECT | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-08-29 | 2020-06-01 | 2020-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW340FIP2 | BOE- FACILITIES IMPROVEMENT PROJECT | 2 | PRELIMINARY DESIGN | 2020-08-30 | 2020-12-27 | 2020-08-30 | 2020-12-27
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW340FIP2 | BOE- FACILITIES IMPROVEMENT PROJECT | 3 | FINAL DESIGN | 2020-12-28 | 2021-06-25 | 2020-12-28 | 2021-06-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW340FIP2 | BOE- FACILITIES IMPROVEMENT PROJECT | 4 | BID AWARD AND REGISTER CONTRCT | 2021-06-26 | 2021-09-23 | 2021-06-26 | 2021-09-23
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW340FIP2 | BOE- FACILITIES IMPROVEMENT PROJECT | 5 | CONSTRUCTION TO 25% | 2021-09-24 | 2022-01-21 | 2021-09-24 | 2022-01-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW340FIP2 | BOE- FACILITIES IMPROVEMENT PROJECT | 6 | CONSTRUCTION TO 50% | 2022-01-22 | 2022-05-21 | 2022-01-22 | 2022-05-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW340FIP2 | BOE- FACILITIES IMPROVEMENT PROJECT | 7 | CONSTRUCTION TO 75% | 2022-05-22 | 2022-09-18 | 2022-05-22 | 2022-09-18
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW340FIP2 | BOE- FACILITIES IMPROVEMENT PROJECT | 8 | ORIGINAL EQUIP & FURNISHING | 2022-09-19 | 2022-12-17 | 2022-09-19 | 2022-12-17
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW340FIP2 | BOE- FACILITIES IMPROVEMENT PROJECT | 9 | SUBSTANTIAL COMPLETION | 2022-12-18 | 2023-02-15 | 2022-12-18 | 2023-02-15
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW340FIP2 | BOE- FACILITIES IMPROVEMENT PROJECT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-02-16 | 2023-03-17 | 2023-02-16 | 2023-03-17
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW357ELC2 | 253 BROADWAY- ELECTRICAL UPGRADES PHASE 2 | 1 | DEVELOP SCOPE | 2016-05-01 | 2016-07-29 | 2020-06-01 | 2020-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW357ELC2 | 253 BROADWAY- ELECTRICAL UPGRADES PHASE 2 | 2 | PRELIMINARY DESIGN | 2016-07-30 | 2016-11-26 | 2020-06-01 | 2020-09-28
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW357ELC2 | 253 BROADWAY- ELECTRICAL UPGRADES PHASE 2 | 3 | FINAL DESIGN | 2016-11-27 | 2017-05-25 | 2020-09-29 | 2021-03-27
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW357ELC2 | 253 BROADWAY- ELECTRICAL UPGRADES PHASE 2 | 4 | BID AWARD AND REGISTER CONTRCT | 2017-05-26 | 2017-08-23 | 2021-03-28 | 2021-06-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW357ELC2 | 253 BROADWAY- ELECTRICAL UPGRADES PHASE 2 | 5 | CONSTRUCTION TO 25% | 2017-08-24 | 2017-12-21 | 2021-06-26 | 2021-10-23
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW357ELC2 | 253 BROADWAY- ELECTRICAL UPGRADES PHASE 2 | 6 | CONSTRUCTION TO 50% | 2017-12-22 | 2018-04-20 | 2021-10-24 | 2022-02-20
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW357ELC2 | 253 BROADWAY- ELECTRICAL UPGRADES PHASE 2 | 7 | CONSTRUCTION TO 75% | 2018-04-21 | 2018-08-18 | 2022-02-21 | 2023-06-20
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW357ELC2 | 253 BROADWAY- ELECTRICAL UPGRADES PHASE 2 | 8 | ORIGINAL EQUIP & FURNISHING | 2018-08-19 | 2018-11-16 | 2023-06-21 | 2023-09-18
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW357ELC2 | 253 BROADWAY- ELECTRICAL UPGRADES PHASE 2 | 9 | SUBSTANTIAL COMPLETION | 2018-11-17 | 2019-01-15 | 2023-09-19 | 2023-11-17
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW357ELC2 | 253 BROADWAY- ELECTRICAL UPGRADES PHASE 2 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-01-16 | 2019-02-14 | 2023-11-18 | 2023-12-17
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW357EXTR | 253 BROADWAY- EXTERIOR AND ROOF | 1 | DEVELOP SCOPE | 2003-06-30 | 2003-09-27 | 2003-06-01 | 2003-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW357EXTR | 253 BROADWAY- EXTERIOR AND ROOF | 2 | PRELIMINARY DESIGN | 2003-09-28 | 2004-01-25 | 2003-08-30 | 2003-12-27
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW357EXTR | 253 BROADWAY- EXTERIOR AND ROOF | 3 | FINAL DESIGN | 2004-01-26 | 2004-07-23 | 2003-12-28 | 2004-06-24
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW357EXTR | 253 BROADWAY- EXTERIOR AND ROOF | 4 | BID AWARD AND REGISTER CONTRCT | 2006-10-01 | 2007-01-31 | 2004-06-25 | 2004-09-22
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW357EXTR | 253 BROADWAY- EXTERIOR AND ROOF | 5 | CONSTRUCTION TO 25% | 2007-02-01 | 2007-05-31 | 2004-09-23 | 2007-05-10
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW357EXTR | 253 BROADWAY- EXTERIOR AND ROOF | 6 | CONSTRUCTION TO 50% | 2007-06-01 | 2007-09-30 | 2007-05-11 | 2009-12-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW357EXTR | 253 BROADWAY- EXTERIOR AND ROOF | 7 | CONSTRUCTION TO 75% | 2007-10-01 | 2008-01-31 | 2009-12-26 | 2012-08-11
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW357EXTR | 253 BROADWAY- EXTERIOR AND ROOF | 8 | ORIGINAL EQUIP & FURNISHING | 2008-02-01 | 2008-02-29 | 2012-08-12 | 2015-03-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW357EXTR | 253 BROADWAY- EXTERIOR AND ROOF | 9 | SUBSTANTIAL COMPLETION | 2008-03-01 | 2008-04-30 | 2015-03-30 | 2016-03-23
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW357EXTR | 253 BROADWAY- EXTERIOR AND ROOF | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-05-01 | 2008-05-30 | 2016-03-24 | 2025-06-30
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW357SA | 253 AND 256 BROADWAY- SAFE ACCESS CATWALK | 1 | DEVELOP SCOPE | 2014-06-01 | 2014-08-29 | 2023-06-01 | 2023-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW357SA | 253 AND 256 BROADWAY- SAFE ACCESS CATWALK | 2 | PRELIMINARY DESIGN | 2014-08-30 | 2014-12-27 | 2023-08-30 | 2023-12-27
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW357SA | 253 AND 256 BROADWAY- SAFE ACCESS CATWALK | 3 | FINAL DESIGN | 2014-12-28 | 2015-06-25 | 2023-12-28 | 2024-06-24
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW357SA | 253 AND 256 BROADWAY- SAFE ACCESS CATWALK | 4 | BID AWARD AND REGISTER CONTRCT | 2015-06-26 | 2015-09-23 | 2023-06-26 | 2023-09-23
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW357SA | 253 AND 256 BROADWAY- SAFE ACCESS CATWALK | 5 | CONSTRUCTION TO 25% | 2015-09-24 | 2016-01-21 | 2023-09-24 | 2024-01-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW357SA | 253 AND 256 BROADWAY- SAFE ACCESS CATWALK | 6 | CONSTRUCTION TO 50% | 2016-01-22 | 2016-05-20 | 2024-01-22 | 2024-05-20
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW357SA | 253 AND 256 BROADWAY- SAFE ACCESS CATWALK | 7 | CONSTRUCTION TO 75% | 2016-05-21 | 2016-09-17 | 2024-05-21 | 2024-09-17
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW357SA | 253 AND 256 BROADWAY- SAFE ACCESS CATWALK | 8 | ORIGINAL EQUIP & FURNISHING | 2016-09-18 | 2016-12-16 | 2024-09-18 | 2024-12-16
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW357SA | 253 AND 256 BROADWAY- SAFE ACCESS CATWALK | 9 | SUBSTANTIAL COMPLETION | 2016-12-17 | 2017-02-14 | 2024-12-17 | 2025-02-14
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW357SA | 253 AND 256 BROADWAY- SAFE ACCESS CATWALK | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-02-15 | 2017-03-16 | 2025-02-15 | 2025-03-16
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW357STM2 | 253 BROADWAY - RECONSTRUCT STEAM STATION | 1 | DEVELOP SCOPE | 2017-01-01 | 2017-03-31 | 2021-06-01 | 2021-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW357STM2 | 253 BROADWAY - RECONSTRUCT STEAM STATION | 2 | PRELIMINARY DESIGN | 2017-04-01 | 2017-07-29 | 2020-06-01 | 2020-09-28
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW357STM2 | 253 BROADWAY - RECONSTRUCT STEAM STATION | 3 | FINAL DESIGN | 2017-07-30 | 2018-01-25 | 2020-09-29 | 2021-03-27
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW357STM2 | 253 BROADWAY - RECONSTRUCT STEAM STATION | 4 | BID AWARD AND REGISTER CONTRCT | 2018-01-26 | 2018-04-25 | 2021-03-28 | 2021-06-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW357STM2 | 253 BROADWAY - RECONSTRUCT STEAM STATION | 5 | CONSTRUCTION TO 25% | 2018-04-26 | 2018-08-23 | 2023-06-01 | 2023-09-28
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW357STM2 | 253 BROADWAY - RECONSTRUCT STEAM STATION | 6 | CONSTRUCTION TO 50% | 2018-08-24 | 2018-12-21 | 2023-09-29 | 2024-01-26
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW357STM2 | 253 BROADWAY - RECONSTRUCT STEAM STATION | 7 | CONSTRUCTION TO 75% | 2018-12-22 | 2019-04-20 | 2024-01-27 | 2024-05-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW357STM2 | 253 BROADWAY - RECONSTRUCT STEAM STATION | 8 | ORIGINAL EQUIP & FURNISHING | 2019-04-21 | 2019-07-19 | 2024-05-26 | 2024-08-23
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW357STM2 | 253 BROADWAY - RECONSTRUCT STEAM STATION | 9 | SUBSTANTIAL COMPLETION | 2019-07-20 | 2019-09-17 | 2024-08-24 | 2024-10-22
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW357STM2 | 253 BROADWAY - RECONSTRUCT STEAM STATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-18 | 2019-10-17 | 2024-10-23 | 2027-06-05
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW357VAUL | 253 BROADWAY - VAULT RECONSTRUCTION | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-08-29 | 2020-06-01 | 2020-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW357VAUL | 253 BROADWAY - VAULT RECONSTRUCTION | 2 | PRELIMINARY DESIGN | 2020-08-30 | 2020-12-27 | 2020-08-30 | 2020-12-27
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW357VAUL | 253 BROADWAY - VAULT RECONSTRUCTION | 3 | FINAL DESIGN | 2020-12-28 | 2021-06-25 | 2020-12-28 | 2021-06-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW357VAUL | 253 BROADWAY - VAULT RECONSTRUCTION | 4 | BID AWARD AND REGISTER CONTRCT | 2021-06-26 | 2021-09-23 | 2021-06-26 | 2021-09-23
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW357VAUL | 253 BROADWAY - VAULT RECONSTRUCTION | 5 | CONSTRUCTION TO 25% | 2021-09-24 | 2022-01-21 | 2021-09-24 | 2022-01-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW357VAUL | 253 BROADWAY - VAULT RECONSTRUCTION | 6 | CONSTRUCTION TO 50% | 2022-01-22 | 2022-05-21 | 2022-01-22 | 2022-05-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW357VAUL | 253 BROADWAY - VAULT RECONSTRUCTION | 7 | CONSTRUCTION TO 75% | 2022-05-22 | 2022-09-18 | 2022-05-22 | 2022-09-18
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW357VAUL | 253 BROADWAY - VAULT RECONSTRUCTION | 8 | ORIGINAL EQUIP & FURNISHING | 2022-09-19 | 2022-12-17 | 2022-09-19 | 2022-12-17
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW357VAUL | 253 BROADWAY - VAULT RECONSTRUCTION | 9 | SUBSTANTIAL COMPLETION | 2022-12-18 | 2023-02-15 | 2022-12-18 | 2023-02-15
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW357VAUL | 253 BROADWAY - VAULT RECONSTRUCTION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-02-16 | 2024-03-17 | 2023-02-16 | 2024-03-17
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77115CH | 115 CHRYSTIE ST. - INTERIOR RENOVATIONS | 1 | DEVELOP SCOPE | 2012-06-01 | 2012-08-29 | 2022-06-01 | 2022-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77115CH | 115 CHRYSTIE ST. - INTERIOR RENOVATIONS | 2 | PRELIMINARY DESIGN | 2012-08-30 | 2012-12-27 | 2022-08-30 | 2022-12-27
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77115CH | 115 CHRYSTIE ST. - INTERIOR RENOVATIONS | 3 | FINAL DESIGN | 2012-12-28 | 2013-06-25 | 2022-12-28 | 2023-06-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77115CH | 115 CHRYSTIE ST. - INTERIOR RENOVATIONS | 4 | BID AWARD AND REGISTER CONTRCT | 2013-06-26 | 2013-09-23 | 2023-06-26 | 2023-09-23
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77115CH | 115 CHRYSTIE ST. - INTERIOR RENOVATIONS | 5 | CONSTRUCTION TO 25% | 2013-09-24 | 2014-01-21 | 2023-09-24 | 2024-01-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77115CH | 115 CHRYSTIE ST. - INTERIOR RENOVATIONS | 6 | CONSTRUCTION TO 50% | 2014-01-22 | 2014-05-21 | 2024-01-22 | 2024-05-20
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77115CH | 115 CHRYSTIE ST. - INTERIOR RENOVATIONS | 7 | CONSTRUCTION TO 75% | 2014-05-22 | 2014-09-18 | 2024-05-21 | 2024-09-17
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77115CH | 115 CHRYSTIE ST. - INTERIOR RENOVATIONS | 8 | ORIGINAL EQUIP & FURNISHING | 2014-09-19 | 2014-12-17 | 2024-09-18 | 2024-12-16
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77115CH | 115 CHRYSTIE ST. - INTERIOR RENOVATIONS | 9 | SUBSTANTIAL COMPLETION | 2014-12-18 | 2015-02-15 | 2024-12-17 | 2025-02-14
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77115CH | 115 CHRYSTIE ST. - INTERIOR RENOVATIONS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-02-16 | 2015-03-17 | 2025-02-15 | 2025-03-16
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77117SA | 137 CENTRE ST. - SAFE ACCESS | 1 | DEVELOP SCOPE | 2014-06-01 | 2014-08-29 | 2022-06-01 | 2022-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77117SA | 137 CENTRE ST. - SAFE ACCESS | 2 | PRELIMINARY DESIGN | 2014-08-30 | 2014-12-27 | 2022-08-30 | 2022-12-27
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77117SA | 137 CENTRE ST. - SAFE ACCESS | 3 | FINAL DESIGN | 2014-12-28 | 2015-06-25 | 2022-12-28 | 2023-06-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77117SA | 137 CENTRE ST. - SAFE ACCESS | 4 | BID AWARD AND REGISTER CONTRCT | 2015-06-26 | 2015-09-23 | 2023-06-26 | 2023-09-23
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77117SA | 137 CENTRE ST. - SAFE ACCESS | 5 | CONSTRUCTION TO 25% | 2015-09-24 | 2016-01-21 | 2023-09-24 | 2024-01-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77117SA | 137 CENTRE ST. - SAFE ACCESS | 6 | CONSTRUCTION TO 50% | 2016-01-22 | 2016-05-20 | 2024-01-22 | 2024-05-20
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77117SA | 137 CENTRE ST. - SAFE ACCESS | 7 | CONSTRUCTION TO 75% | 2016-05-21 | 2016-09-17 | 2024-05-21 | 2024-09-17
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77117SA | 137 CENTRE ST. - SAFE ACCESS | 8 | ORIGINAL EQUIP & FURNISHING | 2016-09-18 | 2016-12-16 | 2022-06-01 | 2022-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77117SA | 137 CENTRE ST. - SAFE ACCESS | 9 | SUBSTANTIAL COMPLETION | 2016-12-17 | 2017-02-14 | 2022-08-30 | 2022-10-28
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77117SA | 137 CENTRE ST. - SAFE ACCESS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-02-15 | 2017-03-16 | 2022-10-29 | 2024-06-30
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77136A | 60 LAFAYETTE ST, 2nd 4th FL - DOP | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-08-29 | 2020-06-01 | 2020-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77136A | 60 LAFAYETTE ST, 2nd 4th FL - DOP | 2 | PRELIMINARY DESIGN | 2020-08-30 | 2020-12-27 | 2020-08-30 | 2020-12-27
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77136A | 60 LAFAYETTE ST, 2nd 4th FL - DOP | 3 | FINAL DESIGN | 2020-12-28 | 2021-06-25 | 2020-12-28 | 2021-06-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77136A | 60 LAFAYETTE ST, 2nd 4th FL - DOP | 4 | BID AWARD AND REGISTER CONTRCT | 2021-06-26 | 2021-09-23 | 2021-06-26 | 2021-09-23
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77136A | 60 LAFAYETTE ST, 2nd 4th FL - DOP | 5 | CONSTRUCTION TO 25% | 2021-09-24 | 2022-01-21 | 2021-09-24 | 2022-01-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77136A | 60 LAFAYETTE ST, 2nd 4th FL - DOP | 6 | CONSTRUCTION TO 50% | 2022-01-22 | 2022-05-21 | 2022-01-22 | 2022-05-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77136A | 60 LAFAYETTE ST, 2nd 4th FL - DOP | 7 | CONSTRUCTION TO 75% | 2022-05-22 | 2022-09-18 | 2022-05-22 | 2022-09-18
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77136A | 60 LAFAYETTE ST, 2nd 4th FL - DOP | 8 | ORIGINAL EQUIP & FURNISHING | 2022-09-19 | 2022-12-17 | 2022-09-19 | 2022-12-17
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77136A | 60 LAFAYETTE ST, 2nd 4th FL - DOP | 9 | SUBSTANTIAL COMPLETION | 2022-12-18 | 2023-02-15 | 2022-12-18 | 2023-02-15
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77136A | 60 LAFAYETTE ST, 2nd 4th FL - DOP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-02-16 | 2023-03-17 | 2023-02-16 | 2023-03-17
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77137C | 137 CENTRE ST. Renovation | 1 | DEVELOP SCOPE | 2023-06-01 | 2023-08-29 | 2023-06-01 | 2023-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77137C | 137 CENTRE ST. Renovation | 2 | PRELIMINARY DESIGN | 2023-08-30 | 2023-12-27 | 2023-08-30 | 2023-12-27
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77137C | 137 CENTRE ST. Renovation | 3 | FINAL DESIGN | 2023-12-28 | 2024-06-24 | 2023-12-28 | 2024-06-24
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77137C | 137 CENTRE ST. Renovation | 4 | BID AWARD AND REGISTER CONTRCT | 2024-06-25 | 2024-09-22 | 2024-06-25 | 2024-09-22
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77137C | 137 CENTRE ST. Renovation | 5 | CONSTRUCTION TO 25% | 2024-09-23 | 2025-01-20 | 2024-09-23 | 2025-01-20
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77137C | 137 CENTRE ST. Renovation | 6 | CONSTRUCTION TO 50% | 2025-01-21 | 2025-05-20 | 2025-01-21 | 2025-05-20
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77137C | 137 CENTRE ST. Renovation | 7 | CONSTRUCTION TO 75% | 2025-05-21 | 2025-09-17 | 2025-05-21 | 2025-09-17
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77137C | 137 CENTRE ST. Renovation | 8 | ORIGINAL EQUIP & FURNISHING | 2025-09-18 | 2025-12-16 | 2025-09-18 | 2025-12-16
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77137C | 137 CENTRE ST. Renovation | 9 | SUBSTANTIAL COMPLETION | 2025-12-17 | 2026-02-14 | 2025-12-17 | 2026-02-14
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77137C | 137 CENTRE ST. Renovation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2026-02-15 | 2026-03-16 | 2026-02-15 | 2026-03-16
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW771C09 | 1 CENTRE ST. - 9th Floor Renovation | 1 | DEVELOP SCOPE | 2021-06-01 | 2021-08-29 | 2025-06-01 | 2025-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW771C09 | 1 CENTRE ST. - 9th Floor Renovation | 2 | PRELIMINARY DESIGN | 2021-08-30 | 2021-12-27 | 2025-08-30 | 2025-12-27
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW771C09 | 1 CENTRE ST. - 9th Floor Renovation | 3 | FINAL DESIGN | 2021-12-28 | 2022-06-25 | 2025-12-28 | 2026-06-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW771C09 | 1 CENTRE ST. - 9th Floor Renovation | 4 | BID AWARD AND REGISTER CONTRCT | 2022-06-26 | 2022-09-23 | 2026-06-26 | 2026-09-23
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW771C09 | 1 CENTRE ST. - 9th Floor Renovation | 5 | CONSTRUCTION TO 25% | 2022-09-24 | 2023-01-21 | 2026-09-24 | 2027-01-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW771C09 | 1 CENTRE ST. - 9th Floor Renovation | 6 | CONSTRUCTION TO 50% | 2023-01-22 | 2023-05-21 | 2027-01-22 | 2027-05-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW771C09 | 1 CENTRE ST. - 9th Floor Renovation | 7 | CONSTRUCTION TO 75% | 2023-05-22 | 2023-09-18 | 2027-05-22 | 2027-09-18
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW771C09 | 1 CENTRE ST. - 9th Floor Renovation | 8 | ORIGINAL EQUIP & FURNISHING | 2023-09-19 | 2023-12-17 | 2027-09-19 | 2027-12-17
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW771C09 | 1 CENTRE ST. - 9th Floor Renovation | 9 | SUBSTANTIAL COMPLETION | 2023-12-18 | 2024-02-15 | 2027-12-18 | 2028-02-15
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW771C09 | 1 CENTRE ST. - 9th Floor Renovation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-02-16 | 2024-03-16 | 2028-02-16 | 2028-03-16
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW771C21 | 1 CENTRE ST. - 21st Floor Renovation | 1 | DEVELOP SCOPE | 2021-06-01 | 2021-08-29 | 2025-06-01 | 2025-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW771C21 | 1 CENTRE ST. - 21st Floor Renovation | 2 | PRELIMINARY DESIGN | 2021-08-30 | 2021-12-27 | 2025-08-30 | 2025-12-27
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW771C21 | 1 CENTRE ST. - 21st Floor Renovation | 3 | FINAL DESIGN | 2021-12-28 | 2022-06-25 | 2025-12-28 | 2026-06-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW771C21 | 1 CENTRE ST. - 21st Floor Renovation | 4 | BID AWARD AND REGISTER CONTRCT | 2022-06-26 | 2022-09-23 | 2026-06-26 | 2026-09-23
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW771C21 | 1 CENTRE ST. - 21st Floor Renovation | 5 | CONSTRUCTION TO 25% | 2022-09-24 | 2023-01-21 | 2026-09-24 | 2027-01-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW771C21 | 1 CENTRE ST. - 21st Floor Renovation | 6 | CONSTRUCTION TO 50% | 2023-01-22 | 2023-05-21 | 2027-01-22 | 2027-05-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW771C21 | 1 CENTRE ST. - 21st Floor Renovation | 7 | CONSTRUCTION TO 75% | 2023-05-22 | 2023-09-18 | 2027-05-22 | 2027-09-18
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW771C21 | 1 CENTRE ST. - 21st Floor Renovation | 8 | ORIGINAL EQUIP & FURNISHING | 2023-09-19 | 2023-12-17 | 2027-09-19 | 2027-12-17
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW771C21 | 1 CENTRE ST. - 21st Floor Renovation | 9 | SUBSTANTIAL COMPLETION | 2023-12-18 | 2024-02-15 | 2027-12-18 | 2028-02-15
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW771C21 | 1 CENTRE ST. - 21st Floor Renovation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-02-16 | 2024-03-16 | 2028-02-16 | 2028-03-16
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW7722R5 | 22 READE ST.- 5th AND 6th FLOOR BUILDOUT | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-08-29 | 2020-06-01 | 2020-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW7722R5 | 22 READE ST.- 5th AND 6th FLOOR BUILDOUT | 2 | PRELIMINARY DESIGN | 2020-08-30 | 2020-12-27 | 2020-08-30 | 2020-12-27
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW7722R5 | 22 READE ST.- 5th AND 6th FLOOR BUILDOUT | 3 | FINAL DESIGN | 2020-12-28 | 2021-06-25 | 2020-12-28 | 2021-06-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW7722R5 | 22 READE ST.- 5th AND 6th FLOOR BUILDOUT | 4 | BID AWARD AND REGISTER CONTRCT | 2021-06-26 | 2021-09-23 | 2021-06-26 | 2021-09-23
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW7722R5 | 22 READE ST.- 5th AND 6th FLOOR BUILDOUT | 5 | CONSTRUCTION TO 25% | 2022-09-24 | 2023-05-26 | 2022-09-24 | 2023-05-26
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW7722R5 | 22 READE ST.- 5th AND 6th FLOOR BUILDOUT | 6 | CONSTRUCTION TO 50% | 2023-05-27 | 2023-09-23 | 2023-05-27 | 2023-09-23
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW7722R5 | 22 READE ST.- 5th AND 6th FLOOR BUILDOUT | 7 | CONSTRUCTION TO 75% | 2023-09-24 | 2024-01-21 | 2023-09-24 | 2024-01-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW7722R5 | 22 READE ST.- 5th AND 6th FLOOR BUILDOUT | 8 | ORIGINAL EQUIP & FURNISHING | 2024-01-22 | 2024-04-20 | 2024-01-22 | 2024-04-20
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW7722R5 | 22 READE ST.- 5th AND 6th FLOOR BUILDOUT | 9 | SUBSTANTIAL COMPLETION | 2024-04-21 | 2024-06-19 | 2024-04-21 | 2024-06-19
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW7722R5 | 22 READE ST.- 5th AND 6th FLOOR BUILDOUT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-06-20 | 2024-07-19 | 2024-06-20 | 2024-07-19
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW7722REV | 22 READE ST.- ELEVATOR MODERNIZATION | 1 | DEVELOP SCOPE | 2019-06-01 | 2019-08-29 | 2019-06-01 | 2019-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW7722REV | 22 READE ST.- ELEVATOR MODERNIZATION | 2 | PRELIMINARY DESIGN | 2019-08-30 | 2019-12-27 | 2019-08-30 | 2019-12-27
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW7722REV | 22 READE ST.- ELEVATOR MODERNIZATION | 3 | FINAL DESIGN | 2019-12-28 | 2020-06-24 | 2019-12-28 | 2020-06-24
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW7722REV | 22 READE ST.- ELEVATOR MODERNIZATION | 4 | BID AWARD AND REGISTER CONTRCT | 2020-06-25 | 2020-09-22 | 2020-06-25 | 2020-09-22
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW7722REV | 22 READE ST.- ELEVATOR MODERNIZATION | 5 | CONSTRUCTION TO 25% | 2020-09-23 | 2021-01-20 | 2020-09-23 | 2021-01-20
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW7722REV | 22 READE ST.- ELEVATOR MODERNIZATION | 6 | CONSTRUCTION TO 50% | 2021-01-21 | 2021-05-20 | 2021-01-21 | 2021-05-20
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW7722REV | 22 READE ST.- ELEVATOR MODERNIZATION | 7 | CONSTRUCTION TO 75% | 2021-05-21 | 2021-09-17 | 2021-05-21 | 2021-09-17
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW7722REV | 22 READE ST.- ELEVATOR MODERNIZATION | 8 | ORIGINAL EQUIP & FURNISHING | 2021-09-18 | 2021-12-16 | 2021-09-18 | 2021-12-16
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW7722REV | 22 READE ST.- ELEVATOR MODERNIZATION | 9 | SUBSTANTIAL COMPLETION | 2021-12-17 | 2022-02-14 | 2021-12-17 | 2022-02-14
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW7722REV | 22 READE ST.- ELEVATOR MODERNIZATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-02-15 | 2022-03-16 | 2022-02-15 | 2022-03-16
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW7725RF | 1 CENTER ST ROOF - 25th FLOOR | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-08-29 | 2020-06-01 | 2020-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW7725RF | 1 CENTER ST ROOF - 25th FLOOR | 2 | PRELIMINARY DESIGN | 2020-08-30 | 2020-12-27 | 2020-08-30 | 2020-12-27
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW7725RF | 1 CENTER ST ROOF - 25th FLOOR | 3 | FINAL DESIGN | 2020-12-28 | 2021-06-25 | 2020-12-28 | 2021-06-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW7725RF | 1 CENTER ST ROOF - 25th FLOOR | 4 | BID AWARD AND REGISTER CONTRCT | 2021-06-26 | 2021-09-23 | 2021-06-26 | 2021-09-23
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW7725RF | 1 CENTER ST ROOF - 25th FLOOR | 5 | CONSTRUCTION TO 25% | 2021-09-24 | 2022-01-21 | 2021-09-24 | 2022-01-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW7725RF | 1 CENTER ST ROOF - 25th FLOOR | 6 | CONSTRUCTION TO 50% | 2022-01-22 | 2022-05-21 | 2022-01-22 | 2022-05-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW7725RF | 1 CENTER ST ROOF - 25th FLOOR | 7 | CONSTRUCTION TO 75% | 2022-05-22 | 2022-09-18 | 2022-05-22 | 2022-09-18
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW7725RF | 1 CENTER ST ROOF - 25th FLOOR | 8 | ORIGINAL EQUIP & FURNISHING | 2022-09-19 | 2022-12-17 | 2022-09-19 | 2022-12-17
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW7725RF | 1 CENTER ST ROOF - 25th FLOOR | 9 | SUBSTANTIAL COMPLETION | 2022-12-18 | 2023-02-15 | 2022-12-18 | 2023-02-15
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW7725RF | 1 CENTER ST ROOF - 25th FLOOR | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-02-16 | 2023-03-17 | 2023-02-16 | 2023-03-17
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW7726RF | 1 CENTRE ST - 26TH FLOOR ROOF REPLACEMENT | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-08-29 | 2020-06-01 | 2020-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW7726RF | 1 CENTRE ST - 26TH FLOOR ROOF REPLACEMENT | 2 | PRELIMINARY DESIGN | 2020-08-30 | 2020-12-27 | 2020-08-30 | 2020-12-27
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW7726RF | 1 CENTRE ST - 26TH FLOOR ROOF REPLACEMENT | 3 | FINAL DESIGN | 2020-12-28 | 2021-06-25 | 2020-12-28 | 2021-06-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW7726RF | 1 CENTRE ST - 26TH FLOOR ROOF REPLACEMENT | 4 | BID AWARD AND REGISTER CONTRCT | 2021-06-26 | 2021-09-23 | 2021-06-26 | 2021-09-23
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW7726RF | 1 CENTRE ST - 26TH FLOOR ROOF REPLACEMENT | 5 | CONSTRUCTION TO 25% | 2021-09-24 | 2022-01-21 | 2021-09-24 | 2022-01-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW7726RF | 1 CENTRE ST - 26TH FLOOR ROOF REPLACEMENT | 6 | CONSTRUCTION TO 50% | 2022-01-22 | 2022-05-21 | 2022-01-22 | 2022-05-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW7726RF | 1 CENTRE ST - 26TH FLOOR ROOF REPLACEMENT | 7 | CONSTRUCTION TO 75% | 2022-05-22 | 2022-09-18 | 2022-05-22 | 2022-09-18
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW7726RF | 1 CENTRE ST - 26TH FLOOR ROOF REPLACEMENT | 8 | ORIGINAL EQUIP & FURNISHING | 2022-09-19 | 2022-12-17 | 2022-09-19 | 2022-12-17
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW7726RF | 1 CENTRE ST - 26TH FLOOR ROOF REPLACEMENT | 9 | SUBSTANTIAL COMPLETION | 2022-12-18 | 2023-02-15 | 2022-12-18 | 2023-02-15
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW7726RF | 1 CENTRE ST - 26TH FLOOR ROOF REPLACEMENT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-02-16 | 2023-03-17 | 2023-02-16 | 2023-03-17
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW7780ELC | 80 CENTRE ST.- ELECTRICAL | 1 | DEVELOP SCOPE | 2008-09-01 | 2008-11-29 | 2008-09-01 | 2008-11-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW7780ELC | 80 CENTRE ST.- ELECTRICAL | 2 | PRELIMINARY DESIGN | 2008-11-30 | 2009-03-29 | 2008-11-30 | 2009-03-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW7780ELC | 80 CENTRE ST.- ELECTRICAL | 3 | FINAL DESIGN | 2009-03-30 | 2009-09-25 | 2009-03-30 | 2009-09-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW7780ELC | 80 CENTRE ST.- ELECTRICAL | 4 | BID AWARD AND REGISTER CONTRCT | 2009-09-26 | 2009-12-24 | 2009-09-26 | 2009-12-24
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW7780ELC | 80 CENTRE ST.- ELECTRICAL | 5 | CONSTRUCTION TO 25% | 2009-12-25 | 2010-04-23 | 2009-12-25 | 2010-04-23
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW7780ELC | 80 CENTRE ST.- ELECTRICAL | 6 | CONSTRUCTION TO 50% | 2010-04-24 | 2010-08-21 | 2010-04-24 | 2010-08-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW7780ELC | 80 CENTRE ST.- ELECTRICAL | 7 | CONSTRUCTION TO 75% | 2010-08-22 | 2010-12-19 | 2010-08-22 | 2010-12-19
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW7780ELC | 80 CENTRE ST.- ELECTRICAL | 8 | ORIGINAL EQUIP & FURNISHING | 2010-12-20 | 2011-03-19 | 2010-12-20 | 2011-03-19
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW7780ELC | 80 CENTRE ST.- ELECTRICAL | 9 | SUBSTANTIAL COMPLETION | 2011-03-20 | 2011-05-18 | 2011-03-20 | 2012-03-13
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW7780ELC | 80 CENTRE ST.- ELECTRICAL | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2011-05-19 | 2011-06-17 | 2012-03-14 | 2012-09-09
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW7780FAC | 80 CENTRE ST.- EXTERIOR REHABILITATION | 1 | DEVELOP SCOPE | 2001-05-01 | 2001-07-29 | 2001-05-01 | 2001-07-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW7780FAC | 80 CENTRE ST.- EXTERIOR REHABILITATION | 2 | PRELIMINARY DESIGN | 2002-09-28 | 2003-01-25 | 2001-07-30 | 2001-11-26
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW7780FAC | 80 CENTRE ST.- EXTERIOR REHABILITATION | 3 | FINAL DESIGN | 2003-01-26 | 2003-07-24 | 2001-11-27 | 2002-05-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW7780FAC | 80 CENTRE ST.- EXTERIOR REHABILITATION | 4 | BID AWARD AND REGISTER CONTRCT | 2003-07-25 | 2006-12-31 | 2022-06-01 | 2022-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW7780FAC | 80 CENTRE ST.- EXTERIOR REHABILITATION | 5 | CONSTRUCTION TO 25% | 2007-01-01 | 2006-12-31 | 2022-06-01 | 2023-09-03
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW7780FAC | 80 CENTRE ST.- EXTERIOR REHABILITATION | 6 | CONSTRUCTION TO 50% | 2007-01-01 | 2006-12-31 | 2023-09-04 | 2024-12-06
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW7780FAC | 80 CENTRE ST.- EXTERIOR REHABILITATION | 7 | CONSTRUCTION TO 75% | 2007-01-01 | 2006-12-31 | 2024-12-07 | 2025-03-11
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW7780FAC | 80 CENTRE ST.- EXTERIOR REHABILITATION | 8 | ORIGINAL EQUIP & FURNISHING | 2007-01-01 | 2006-12-31 | 2025-03-12 | 2025-06-14
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW7780FAC | 80 CENTRE ST.- EXTERIOR REHABILITATION | 9 | SUBSTANTIAL COMPLETION | 2007-01-01 | 2006-12-31 | 2025-06-15 | 2026-09-17
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW7780FAC | 80 CENTRE ST.- EXTERIOR REHABILITATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2007-01-01 | 2007-01-30 | 2026-09-18 | 2029-05-04
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77BOC | 2 LAFAYETTE St. - 12th Fl. BOC Renovation | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-08-29 | 2020-06-01 | 2020-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77BOC | 2 LAFAYETTE St. - 12th Fl. BOC Renovation | 2 | PRELIMINARY DESIGN | 2020-08-30 | 2020-12-27 | 2020-08-30 | 2020-12-27
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77BOC | 2 LAFAYETTE St. - 12th Fl. BOC Renovation | 3 | FINAL DESIGN | 2020-12-28 | 2021-06-25 | 2020-12-28 | 2021-06-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77BOC | 2 LAFAYETTE St. - 12th Fl. BOC Renovation | 4 | BID AWARD AND REGISTER CONTRCT | 2020-06-26 | 2020-09-23 | 2020-06-26 | 2020-09-23
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77BOC | 2 LAFAYETTE St. - 12th Fl. BOC Renovation | 5 | CONSTRUCTION TO 25% | 2020-09-24 | 2021-01-21 | 2020-09-24 | 2021-01-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77BOC | 2 LAFAYETTE St. - 12th Fl. BOC Renovation | 6 | CONSTRUCTION TO 50% | 2021-01-22 | 2021-05-21 | 2021-01-22 | 2021-05-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77BOC | 2 LAFAYETTE St. - 12th Fl. BOC Renovation | 7 | CONSTRUCTION TO 75% | 2021-05-22 | 2021-09-18 | 2021-05-22 | 2021-09-18
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77BOC | 2 LAFAYETTE St. - 12th Fl. BOC Renovation | 8 | ORIGINAL EQUIP & FURNISHING | 2021-09-19 | 2021-12-17 | 2021-09-19 | 2021-12-17
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77BOC | 2 LAFAYETTE St. - 12th Fl. BOC Renovation | 9 | SUBSTANTIAL COMPLETION | 2021-12-18 | 2022-02-15 | 2021-12-18 | 2022-02-15
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77BOC | 2 LAFAYETTE St. - 12th Fl. BOC Renovation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-02-16 | 2022-03-17 | 2022-02-16 | 2022-03-17
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77DAK01 | NY COUNTY DA'S OFFICE FIRE UPGRADES | 1 | DEVELOP SCOPE | 2012-09-01 | 2012-11-29 | 2012-09-01 | 2012-11-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77DAK01 | NY COUNTY DA'S OFFICE FIRE UPGRADES | 2 | PRELIMINARY DESIGN | 2012-11-30 | 2013-03-31 | 2012-11-30 | 2013-03-31
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77DAK01 | NY COUNTY DA'S OFFICE FIRE UPGRADES | 3 | FINAL DESIGN | 2013-04-01 | 2013-09-28 | 2013-04-01 | 2013-09-28
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77DAK01 | NY COUNTY DA'S OFFICE FIRE UPGRADES | 4 | BID AWARD AND REGISTER CONTRCT | 2013-09-29 | 2013-12-28 | 2013-09-29 | 2013-12-28
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77DAK01 | NY COUNTY DA'S OFFICE FIRE UPGRADES | 5 | CONSTRUCTION TO 25% | 2013-12-29 | 2014-04-28 | 2013-12-29 | 2014-04-28
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77DAK01 | NY COUNTY DA'S OFFICE FIRE UPGRADES | 6 | CONSTRUCTION TO 50% | 2014-04-29 | 2014-08-28 | 2014-04-29 | 2014-08-28
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77DAK01 | NY COUNTY DA'S OFFICE FIRE UPGRADES | 7 | CONSTRUCTION TO 75% | 2014-08-29 | 2014-12-28 | 2014-08-29 | 2014-12-28
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77DAK01 | NY COUNTY DA'S OFFICE FIRE UPGRADES | 8 | ORIGINAL EQUIP & FURNISHING | 2014-12-29 | 2015-03-28 | 2014-12-29 | 2015-03-28
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77DAK01 | NY COUNTY DA'S OFFICE FIRE UPGRADES | 9 | SUBSTANTIAL COMPLETION | 2015-03-29 | 2015-05-28 | 2015-03-29 | 2015-05-28
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77DAK01 | NY COUNTY DA'S OFFICE FIRE UPGRADES | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-05-29 | 2015-06-30 | 2015-05-29 | 2022-06-30
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77DATU | DA MANHATTAN - ADA BATHROOM UPGRADE | 1 | DEVELOP SCOPE | 2021-06-01 | 2021-08-29 | 2021-06-01 | 2021-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77DATU | DA MANHATTAN - ADA BATHROOM UPGRADE | 2 | PRELIMINARY DESIGN | 2021-08-30 | 2021-12-27 | 2021-08-30 | 2021-12-27
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77DATU | DA MANHATTAN - ADA BATHROOM UPGRADE | 3 | FINAL DESIGN | 2021-12-28 | 2022-06-25 | 2021-12-28 | 2022-06-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77DATU | DA MANHATTAN - ADA BATHROOM UPGRADE | 4 | BID AWARD AND REGISTER CONTRCT | 2022-06-26 | 2022-09-23 | 2022-06-26 | 2022-09-23
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77DATU | DA MANHATTAN - ADA BATHROOM UPGRADE | 5 | CONSTRUCTION TO 25% | 2022-09-24 | 2023-01-21 | 2022-09-24 | 2023-01-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77DATU | DA MANHATTAN - ADA BATHROOM UPGRADE | 6 | CONSTRUCTION TO 50% | 2023-01-22 | 2023-05-21 | 2023-01-22 | 2023-05-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77DATU | DA MANHATTAN - ADA BATHROOM UPGRADE | 7 | CONSTRUCTION TO 75% | 2023-05-22 | 2023-09-18 | 2023-05-22 | 2023-09-18
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77DATU | DA MANHATTAN - ADA BATHROOM UPGRADE | 8 | ORIGINAL EQUIP & FURNISHING | 2023-09-19 | 2023-12-17 | 2023-09-19 | 2023-12-17
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77DATU | DA MANHATTAN - ADA BATHROOM UPGRADE | 9 | SUBSTANTIAL COMPLETION | 2023-12-18 | 2024-02-15 | 2023-12-18 | 2024-02-15
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77DATU | DA MANHATTAN - ADA BATHROOM UPGRADE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-02-16 | 2024-03-16 | 2024-02-16 | 2024-03-16
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLD2F | 100 GOLD STREET 2 FLOOR - MOCs | 1 | DEVELOP SCOPE | 2019-06-01 | 2019-08-29 | 2019-06-01 | 2019-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLD2F | 100 GOLD STREET 2 FLOOR - MOCs | 2 | PRELIMINARY DESIGN | 2019-08-30 | 2019-12-27 | 2019-08-30 | 2019-12-27
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLD2F | 100 GOLD STREET 2 FLOOR - MOCs | 3 | FINAL DESIGN | 2019-12-28 | 2020-06-24 | 2019-12-28 | 2020-06-24
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLD2F | 100 GOLD STREET 2 FLOOR - MOCs | 4 | BID AWARD AND REGISTER CONTRCT | 2020-06-25 | 2020-09-22 | 2020-06-25 | 2020-09-22
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLD2F | 100 GOLD STREET 2 FLOOR - MOCs | 5 | CONSTRUCTION TO 25% | 2020-09-23 | 2021-01-20 | 2020-09-23 | 2021-01-20
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLD2F | 100 GOLD STREET 2 FLOOR - MOCs | 6 | CONSTRUCTION TO 50% | 2021-01-21 | 2021-05-20 | 2021-01-21 | 2021-05-20
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLD2F | 100 GOLD STREET 2 FLOOR - MOCs | 7 | CONSTRUCTION TO 75% | 2021-05-21 | 2021-09-17 | 2021-05-21 | 2021-09-17
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLD2F | 100 GOLD STREET 2 FLOOR - MOCs | 8 | ORIGINAL EQUIP & FURNISHING | 2021-09-18 | 2021-12-16 | 2021-09-18 | 2021-12-16
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLD2F | 100 GOLD STREET 2 FLOOR - MOCs | 9 | SUBSTANTIAL COMPLETION | 2021-12-17 | 2022-02-14 | 2021-12-17 | 2022-02-14
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLD2F | 100 GOLD STREET 2 FLOOR - MOCs | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-02-15 | 2022-03-16 | 2022-02-15 | 2022-03-16
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLDBR | 100 GOLD ST - BATHROOM RENOVATION | 1 | DEVELOP SCOPE | 2022-06-01 | 2022-08-29 | 2022-06-01 | 2022-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLDBR | 100 GOLD ST - BATHROOM RENOVATION | 2 | PRELIMINARY DESIGN | 2022-08-30 | 2022-12-27 | 2022-08-30 | 2022-12-27
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLDBR | 100 GOLD ST - BATHROOM RENOVATION | 3 | FINAL DESIGN | 2022-12-28 | 2023-06-25 | 2022-12-28 | 2023-06-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLDBR | 100 GOLD ST - BATHROOM RENOVATION | 4 | BID AWARD AND REGISTER CONTRCT | 2023-06-26 | 2023-09-23 | 2023-06-26 | 2023-09-23
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLDBR | 100 GOLD ST - BATHROOM RENOVATION | 5 | CONSTRUCTION TO 25% | 2023-09-24 | 2024-01-21 | 2023-09-24 | 2024-01-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLDBR | 100 GOLD ST - BATHROOM RENOVATION | 6 | CONSTRUCTION TO 50% | 2024-01-22 | 2024-05-20 | 2024-01-22 | 2024-05-20
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLDBR | 100 GOLD ST - BATHROOM RENOVATION | 7 | CONSTRUCTION TO 75% | 2024-05-21 | 2024-09-17 | 2024-05-21 | 2024-09-17
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLDBR | 100 GOLD ST - BATHROOM RENOVATION | 8 | ORIGINAL EQUIP & FURNISHING | 2024-09-18 | 2024-12-16 | 2024-09-18 | 2024-12-16
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLDBR | 100 GOLD ST - BATHROOM RENOVATION | 9 | SUBSTANTIAL COMPLETION | 2024-12-17 | 2025-02-14 | 2024-12-17 | 2025-02-14
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLDBR | 100 GOLD ST - BATHROOM RENOVATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-02-15 | 2025-03-16 | 2025-02-15 | 2025-03-16
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLDFA | 100 GOLD ST - FIRE ALARM | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-08-29 | 2020-06-01 | 2020-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLDFA | 100 GOLD ST - FIRE ALARM | 2 | PRELIMINARY DESIGN | 2020-08-30 | 2020-12-27 | 2020-08-30 | 2020-12-27
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLDFA | 100 GOLD ST - FIRE ALARM | 3 | FINAL DESIGN | 2020-12-28 | 2021-06-25 | 2020-12-28 | 2021-06-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLDFA | 100 GOLD ST - FIRE ALARM | 4 | BID AWARD AND REGISTER CONTRCT | 2021-06-26 | 2021-09-23 | 2021-06-26 | 2021-09-23
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLDFA | 100 GOLD ST - FIRE ALARM | 5 | CONSTRUCTION TO 25% | 2021-09-24 | 2022-01-21 | 2021-09-24 | 2022-01-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLDFA | 100 GOLD ST - FIRE ALARM | 6 | CONSTRUCTION TO 50% | 2022-01-22 | 2022-05-21 | 2022-01-22 | 2022-05-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLDFA | 100 GOLD ST - FIRE ALARM | 7 | CONSTRUCTION TO 75% | 2022-05-22 | 2023-09-18 | 2022-05-22 | 2023-09-18
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLDFA | 100 GOLD ST - FIRE ALARM | 8 | ORIGINAL EQUIP & FURNISHING | 2023-09-19 | 2023-12-17 | 2023-09-19 | 2023-12-17
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLDFA | 100 GOLD ST - FIRE ALARM | 9 | SUBSTANTIAL COMPLETION | 2023-12-18 | 2024-02-15 | 2023-12-18 | 2024-02-15
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLDFA | 100 GOLD ST - FIRE ALARM | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-02-16 | 2024-03-16 | 2024-02-16 | 2024-03-16
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLDRF | 100 GOLD ST. - ROOF RECONSTRUCTION | 1 | DEVELOP SCOPE | 2006-09-01 | 2006-11-29 | 2006-06-01 | 2006-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLDRF | 100 GOLD ST. - ROOF RECONSTRUCTION | 2 | PRELIMINARY DESIGN | 2006-11-30 | 2007-03-29 | 2006-08-30 | 2006-12-27
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLDRF | 100 GOLD ST. - ROOF RECONSTRUCTION | 3 | FINAL DESIGN | 2006-09-01 | 2006-11-30 | 2006-12-28 | 2007-06-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLDRF | 100 GOLD ST. - ROOF RECONSTRUCTION | 4 | BID AWARD AND REGISTER CONTRCT | 2006-12-01 | 2007-07-31 | 2007-06-26 | 2007-09-23
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLDRF | 100 GOLD ST. - ROOF RECONSTRUCTION | 5 | CONSTRUCTION TO 25% | 2007-08-01 | 2007-09-30 | 2007-09-24 | 2010-05-10
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLDRF | 100 GOLD ST. - ROOF RECONSTRUCTION | 6 | CONSTRUCTION TO 50% | 2007-10-01 | 2007-10-30 | 2022-06-01 | 2023-05-26
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLDRF | 100 GOLD ST. - ROOF RECONSTRUCTION | 7 | CONSTRUCTION TO 75% | 2007-11-01 | 2007-11-30 | 2023-05-27 | 2024-05-20
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLDRF | 100 GOLD ST. - ROOF RECONSTRUCTION | 8 | ORIGINAL EQUIP & FURNISHING | 2007-12-01 | 2007-11-30 | 2024-05-21 | 2024-11-16
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLDRF | 100 GOLD ST. - ROOF RECONSTRUCTION | 9 | SUBSTANTIAL COMPLETION | 2007-11-01 | 2007-11-30 | 2024-11-17 | 2024-12-31
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLDRF | 100 GOLD ST. - ROOF RECONSTRUCTION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2007-12-01 | 2008-03-31 | 2025-01-01 | 2033-07-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLDSA | 100 GOLD ST. - SAFE ACCESS/CATWALK | 1 | DEVELOP SCOPE | 2012-06-17 | 2012-09-14 | 2023-06-01 | 2023-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLDSA | 100 GOLD ST. - SAFE ACCESS/CATWALK | 2 | PRELIMINARY DESIGN | 2012-09-15 | 2013-01-12 | 2023-08-30 | 2023-12-27
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLDSA | 100 GOLD ST. - SAFE ACCESS/CATWALK | 3 | FINAL DESIGN | 2013-01-13 | 2013-07-11 | 2023-12-28 | 2024-06-24
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLDSA | 100 GOLD ST. - SAFE ACCESS/CATWALK | 4 | BID AWARD AND REGISTER CONTRCT | 2013-07-12 | 2013-10-09 | 2024-06-25 | 2024-09-22
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLDSA | 100 GOLD ST. - SAFE ACCESS/CATWALK | 5 | CONSTRUCTION TO 25% | 2013-10-10 | 2014-02-06 | 2024-09-23 | 2025-01-20
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLDSA | 100 GOLD ST. - SAFE ACCESS/CATWALK | 6 | CONSTRUCTION TO 50% | 2014-02-07 | 2014-06-06 | 2025-01-21 | 2025-05-20
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLDSA | 100 GOLD ST. - SAFE ACCESS/CATWALK | 7 | CONSTRUCTION TO 75% | 2014-06-07 | 2014-10-04 | 2025-05-21 | 2025-09-17
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLDSA | 100 GOLD ST. - SAFE ACCESS/CATWALK | 8 | ORIGINAL EQUIP & FURNISHING | 2014-10-05 | 2015-01-02 | 2023-06-01 | 2023-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLDSA | 100 GOLD ST. - SAFE ACCESS/CATWALK | 9 | SUBSTANTIAL COMPLETION | 2015-01-03 | 2015-03-03 | 2023-08-30 | 2023-10-28
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLDSA | 100 GOLD ST. - SAFE ACCESS/CATWALK | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-04 | 2015-04-02 | 2023-10-29 | 2023-11-27
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77MU8EL | 1 CENTRE ST.- 8TH FL. COMPTROLLERS OFFICE RENOVATIONS | 1 | DEVELOP SCOPE | 2011-06-01 | 2011-08-29 | 2011-06-01 | 2011-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77MU8EL | 1 CENTRE ST.- 8TH FL. COMPTROLLERS OFFICE RENOVATIONS | 2 | PRELIMINARY DESIGN | 2011-08-30 | 2011-12-27 | 2011-08-30 | 2011-12-27
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77MU8EL | 1 CENTRE ST.- 8TH FL. COMPTROLLERS OFFICE RENOVATIONS | 3 | FINAL DESIGN | 2011-12-28 | 2012-06-24 | 2011-12-28 | 2012-06-24
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77MU8EL | 1 CENTRE ST.- 8TH FL. COMPTROLLERS OFFICE RENOVATIONS | 4 | BID AWARD AND REGISTER CONTRCT | 2012-06-25 | 2012-09-22 | 2012-06-25 | 2012-09-22
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77MU8EL | 1 CENTRE ST.- 8TH FL. COMPTROLLERS OFFICE RENOVATIONS | 5 | CONSTRUCTION TO 25% | 2012-09-23 | 2013-01-20 | 2012-09-23 | 2013-01-20
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77MU8EL | 1 CENTRE ST.- 8TH FL. COMPTROLLERS OFFICE RENOVATIONS | 6 | CONSTRUCTION TO 50% | 2013-01-21 | 2013-05-20 | 2013-01-21 | 2013-05-20
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77MU8EL | 1 CENTRE ST.- 8TH FL. COMPTROLLERS OFFICE RENOVATIONS | 7 | CONSTRUCTION TO 75% | 2013-05-21 | 2013-09-17 | 2013-05-21 | 2013-09-17
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77MU8EL | 1 CENTRE ST.- 8TH FL. COMPTROLLERS OFFICE RENOVATIONS | 8 | ORIGINAL EQUIP & FURNISHING | 2013-09-18 | 2013-12-16 | 2013-09-18 | 2013-12-16
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77MU8EL | 1 CENTRE ST.- 8TH FL. COMPTROLLERS OFFICE RENOVATIONS | 9 | SUBSTANTIAL COMPLETION | 2013-12-17 | 2014-02-14 | 2013-12-17 | 2014-02-14
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77MU8EL | 1 CENTRE ST.- 8TH FL. COMPTROLLERS OFFICE RENOVATIONS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-02-15 | 2014-03-16 | 2014-02-15 | 2022-06-30
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC14 | 1 CENTRE ST.- 14 FL SECURITY CAMERAS | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-08-29 | 2020-06-01 | 2020-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC14 | 1 CENTRE ST.- 14 FL SECURITY CAMERAS | 2 | PRELIMINARY DESIGN | 2020-08-30 | 2020-12-27 | 2020-08-30 | 2020-12-27
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC14 | 1 CENTRE ST.- 14 FL SECURITY CAMERAS | 3 | FINAL DESIGN | 2020-12-28 | 2021-06-25 | 2020-12-28 | 2021-06-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC14 | 1 CENTRE ST.- 14 FL SECURITY CAMERAS | 4 | BID AWARD AND REGISTER CONTRCT | 2021-06-26 | 2021-09-23 | 2021-06-26 | 2021-09-23
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC14 | 1 CENTRE ST.- 14 FL SECURITY CAMERAS | 5 | CONSTRUCTION TO 25% | 2021-09-24 | 2022-01-21 | 2021-09-24 | 2022-01-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC14 | 1 CENTRE ST.- 14 FL SECURITY CAMERAS | 6 | CONSTRUCTION TO 50% | 2022-01-22 | 2022-05-21 | 2022-01-22 | 2022-05-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC14 | 1 CENTRE ST.- 14 FL SECURITY CAMERAS | 7 | CONSTRUCTION TO 75% | 2022-05-22 | 2022-09-18 | 2022-05-22 | 2022-09-18
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC14 | 1 CENTRE ST.- 14 FL SECURITY CAMERAS | 8 | ORIGINAL EQUIP & FURNISHING | 2022-09-19 | 2022-12-17 | 2022-09-19 | 2022-12-17
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC14 | 1 CENTRE ST.- 14 FL SECURITY CAMERAS | 9 | SUBSTANTIAL COMPLETION | 2022-12-18 | 2023-02-15 | 2022-12-18 | 2023-02-15
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC14 | 1 CENTRE ST.- 14 FL SECURITY CAMERAS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-02-16 | 2023-03-17 | 2023-02-16 | 2023-03-17
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC1C | 1 CENTRE ST - DCAS POLICE CCTV SYSTEM UPGRADE | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-08-29 | 2020-06-01 | 2020-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC1C | 1 CENTRE ST - DCAS POLICE CCTV SYSTEM UPGRADE | 2 | PRELIMINARY DESIGN | 2020-08-30 | 2020-12-27 | 2020-08-30 | 2020-12-27
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC1C | 1 CENTRE ST - DCAS POLICE CCTV SYSTEM UPGRADE | 3 | FINAL DESIGN | 2020-12-28 | 2021-06-25 | 2020-12-28 | 2021-06-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC1C | 1 CENTRE ST - DCAS POLICE CCTV SYSTEM UPGRADE | 4 | BID AWARD AND REGISTER CONTRCT | 2021-06-26 | 2021-09-23 | 2021-06-26 | 2021-09-23
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC1C | 1 CENTRE ST - DCAS POLICE CCTV SYSTEM UPGRADE | 5 | CONSTRUCTION TO 25% | 2021-09-24 | 2022-01-21 | 2021-09-24 | 2022-01-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC1C | 1 CENTRE ST - DCAS POLICE CCTV SYSTEM UPGRADE | 6 | CONSTRUCTION TO 50% | 2022-01-22 | 2022-05-21 | 2022-01-22 | 2022-05-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC1C | 1 CENTRE ST - DCAS POLICE CCTV SYSTEM UPGRADE | 7 | CONSTRUCTION TO 75% | 2022-05-22 | 2022-09-18 | 2022-05-22 | 2022-09-18
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC1C | 1 CENTRE ST - DCAS POLICE CCTV SYSTEM UPGRADE | 8 | ORIGINAL EQUIP & FURNISHING | 2022-09-19 | 2022-12-17 | 2022-09-19 | 2022-12-17
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC1C | 1 CENTRE ST - DCAS POLICE CCTV SYSTEM UPGRADE | 9 | SUBSTANTIAL COMPLETION | 2022-12-18 | 2023-02-15 | 2022-12-18 | 2023-02-15
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC1C | 1 CENTRE ST - DCAS POLICE CCTV SYSTEM UPGRADE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-02-16 | 2023-03-17 | 2023-02-16 | 2023-03-17
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC22R | 22 READE ST - DCAS POLICE CCTV SYSTEM | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-08-29 | 2020-06-01 | 2020-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC22R | 22 READE ST - DCAS POLICE CCTV SYSTEM | 2 | PRELIMINARY DESIGN | 2020-08-30 | 2020-12-27 | 2020-08-30 | 2020-12-27
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC22R | 22 READE ST - DCAS POLICE CCTV SYSTEM | 3 | FINAL DESIGN | 2020-12-28 | 2021-06-25 | 2020-12-28 | 2021-06-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC22R | 22 READE ST - DCAS POLICE CCTV SYSTEM | 4 | BID AWARD AND REGISTER CONTRCT | 2021-06-26 | 2021-09-23 | 2021-06-26 | 2021-09-23
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC22R | 22 READE ST - DCAS POLICE CCTV SYSTEM | 5 | CONSTRUCTION TO 25% | 2021-09-24 | 2022-01-21 | 2021-09-24 | 2022-01-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC22R | 22 READE ST - DCAS POLICE CCTV SYSTEM | 6 | CONSTRUCTION TO 50% | 2022-01-22 | 2022-05-21 | 2022-01-22 | 2022-05-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC22R | 22 READE ST - DCAS POLICE CCTV SYSTEM | 7 | CONSTRUCTION TO 75% | 2022-05-22 | 2022-09-18 | 2022-05-22 | 2022-09-18
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC22R | 22 READE ST - DCAS POLICE CCTV SYSTEM | 8 | ORIGINAL EQUIP & FURNISHING | 2022-09-19 | 2022-12-17 | 2022-09-19 | 2022-12-17
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC22R | 22 READE ST - DCAS POLICE CCTV SYSTEM | 9 | SUBSTANTIAL COMPLETION | 2022-12-18 | 2023-02-15 | 2022-12-18 | 2023-02-15
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC22R | 22 READE ST - DCAS POLICE CCTV SYSTEM | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-02-16 | 2023-03-17 | 2023-02-16 | 2023-03-17
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC280 | 280 BROADWAY - DCAS POLICE CCTV SYSTEM | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-08-29 | 2020-06-01 | 2020-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC280 | 280 BROADWAY - DCAS POLICE CCTV SYSTEM | 2 | PRELIMINARY DESIGN | 2020-08-30 | 2020-12-27 | 2020-08-30 | 2020-12-27
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC280 | 280 BROADWAY - DCAS POLICE CCTV SYSTEM | 3 | FINAL DESIGN | 2020-12-28 | 2021-06-25 | 2020-12-28 | 2021-06-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC280 | 280 BROADWAY - DCAS POLICE CCTV SYSTEM | 4 | BID AWARD AND REGISTER CONTRCT | 2021-06-26 | 2021-09-23 | 2021-06-26 | 2021-09-23
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC280 | 280 BROADWAY - DCAS POLICE CCTV SYSTEM | 5 | CONSTRUCTION TO 25% | 2021-09-24 | 2022-01-21 | 2021-09-24 | 2022-01-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC280 | 280 BROADWAY - DCAS POLICE CCTV SYSTEM | 6 | CONSTRUCTION TO 50% | 2022-01-22 | 2022-05-21 | 2022-01-22 | 2022-05-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC280 | 280 BROADWAY - DCAS POLICE CCTV SYSTEM | 7 | CONSTRUCTION TO 75% | 2022-05-22 | 2022-09-18 | 2022-05-22 | 2022-09-18
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC280 | 280 BROADWAY - DCAS POLICE CCTV SYSTEM | 8 | ORIGINAL EQUIP & FURNISHING | 2022-09-19 | 2022-12-17 | 2022-09-19 | 2022-12-17
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC280 | 280 BROADWAY - DCAS POLICE CCTV SYSTEM | 9 | SUBSTANTIAL COMPLETION | 2022-12-18 | 2023-02-15 | 2022-12-18 | 2023-02-15
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC280 | 280 BROADWAY - DCAS POLICE CCTV SYSTEM | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-02-16 | 2023-03-17 | 2023-02-16 | 2023-03-17
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC2C | 2 LAFAYETTE ST - DCAS POLICE CCTV SYSTEM | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-08-29 | 2020-06-01 | 2020-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC2C | 2 LAFAYETTE ST - DCAS POLICE CCTV SYSTEM | 2 | PRELIMINARY DESIGN | 2020-08-30 | 2020-12-27 | 2020-08-30 | 2020-12-27
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC2C | 2 LAFAYETTE ST - DCAS POLICE CCTV SYSTEM | 3 | FINAL DESIGN | 2020-12-28 | 2021-06-25 | 2020-12-28 | 2021-06-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC2C | 2 LAFAYETTE ST - DCAS POLICE CCTV SYSTEM | 4 | BID AWARD AND REGISTER CONTRCT | 2021-06-26 | 2021-09-23 | 2021-06-26 | 2021-09-23
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC2C | 2 LAFAYETTE ST - DCAS POLICE CCTV SYSTEM | 5 | CONSTRUCTION TO 25% | 2021-09-24 | 2022-01-21 | 2021-09-24 | 2022-01-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC2C | 2 LAFAYETTE ST - DCAS POLICE CCTV SYSTEM | 6 | CONSTRUCTION TO 50% | 2022-01-22 | 2022-05-21 | 2022-01-22 | 2022-05-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC2C | 2 LAFAYETTE ST - DCAS POLICE CCTV SYSTEM | 7 | CONSTRUCTION TO 75% | 2022-05-22 | 2022-09-18 | 2022-05-22 | 2022-09-18
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC2C | 2 LAFAYETTE ST - DCAS POLICE CCTV SYSTEM | 8 | ORIGINAL EQUIP & FURNISHING | 2022-09-19 | 2022-12-17 | 2022-09-19 | 2022-12-17
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC2C | 2 LAFAYETTE ST - DCAS POLICE CCTV SYSTEM | 9 | SUBSTANTIAL COMPLETION | 2022-12-18 | 2023-02-15 | 2022-12-18 | 2023-02-15
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC2C | 2 LAFAYETTE ST - DCAS POLICE CCTV SYSTEM | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-02-16 | 2023-03-17 | 2023-02-16 | 2023-03-17
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77TAX | 1 CENTRE ST.- 11TH FL. TAX COMMISSION REHAB | 1 | DEVELOP SCOPE | 2012-06-01 | 2012-08-29 | 2024-06-01 | 2024-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77TAX | 1 CENTRE ST.- 11TH FL. TAX COMMISSION REHAB | 2 | PRELIMINARY DESIGN | 2012-08-30 | 2012-12-27 | 2024-08-30 | 2024-12-27
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77TAX | 1 CENTRE ST.- 11TH FL. TAX COMMISSION REHAB | 3 | FINAL DESIGN | 2012-12-28 | 2013-06-25 | 2024-12-28 | 2025-06-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77TAX | 1 CENTRE ST.- 11TH FL. TAX COMMISSION REHAB | 4 | BID AWARD AND REGISTER CONTRCT | 2013-06-26 | 2013-09-23 | 2025-06-26 | 2025-09-23
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77TAX | 1 CENTRE ST.- 11TH FL. TAX COMMISSION REHAB | 5 | CONSTRUCTION TO 25% | 2013-09-24 | 2014-01-21 | 2025-09-24 | 2026-01-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77TAX | 1 CENTRE ST.- 11TH FL. TAX COMMISSION REHAB | 6 | CONSTRUCTION TO 50% | 2014-01-22 | 2014-05-21 | 2026-01-22 | 2026-05-22
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77TAX | 1 CENTRE ST.- 11TH FL. TAX COMMISSION REHAB | 7 | CONSTRUCTION TO 75% | 2014-05-22 | 2014-09-18 | 2026-05-23 | 2026-09-19
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77TAX | 1 CENTRE ST.- 11TH FL. TAX COMMISSION REHAB | 8 | ORIGINAL EQUIP & FURNISHING | 2014-09-19 | 2014-12-17 | 2026-09-20 | 2026-12-18
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77TAX | 1 CENTRE ST.- 11TH FL. TAX COMMISSION REHAB | 9 | SUBSTANTIAL COMPLETION | 2014-12-18 | 2015-02-15 | 2026-12-19 | 2027-02-16
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77TAX | 1 CENTRE ST.- 11TH FL. TAX COMMISSION REHAB | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-02-16 | 2015-03-17 | 2027-02-17 | 2027-03-18
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW80CT1 | 2 LAFAYETTE ST.- COOLING TOWER | 1 | DEVELOP SCOPE | 2021-06-01 | 2021-08-29 | 2021-06-01 | 2021-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW80CT1 | 2 LAFAYETTE ST.- COOLING TOWER | 2 | PRELIMINARY DESIGN | 2021-08-30 | 2021-12-27 | 2021-08-30 | 2021-12-27
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW80CT1 | 2 LAFAYETTE ST.- COOLING TOWER | 3 | FINAL DESIGN | 2021-12-28 | 2022-06-25 | 2021-12-28 | 2022-06-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW80CT1 | 2 LAFAYETTE ST.- COOLING TOWER | 4 | BID AWARD AND REGISTER CONTRCT | 2022-06-26 | 2022-09-23 | 2022-06-26 | 2022-09-23
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW80CT1 | 2 LAFAYETTE ST.- COOLING TOWER | 5 | CONSTRUCTION TO 25% | 2022-09-24 | 2023-01-21 | 2022-09-24 | 2023-01-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW80CT1 | 2 LAFAYETTE ST.- COOLING TOWER | 6 | CONSTRUCTION TO 50% | 2023-01-22 | 2023-05-21 | 2023-01-22 | 2023-05-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW80CT1 | 2 LAFAYETTE ST.- COOLING TOWER | 7 | CONSTRUCTION TO 75% | 2023-05-22 | 2023-09-18 | 2023-05-22 | 2023-09-18
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW80CT1 | 2 LAFAYETTE ST.- COOLING TOWER | 8 | ORIGINAL EQUIP & FURNISHING | 2023-09-19 | 2023-12-17 | 2023-09-19 | 2023-12-17
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW80CT1 | 2 LAFAYETTE ST.- COOLING TOWER | 9 | SUBSTANTIAL COMPLETION | 2023-12-18 | 2024-02-15 | 2023-12-18 | 2024-02-15
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW80CT1 | 2 LAFAYETTE ST.- COOLING TOWER | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-02-16 | 2024-03-16 | 2024-02-16 | 2024-03-16
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW80ELEC | 2 LAFAYETTE STREET ELECTRICAL UPGRADE | 1 | DEVELOP SCOPE | 2017-01-01 | 2017-03-31 | 2021-06-01 | 2021-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW80ELEC | 2 LAFAYETTE STREET ELECTRICAL UPGRADE | 2 | PRELIMINARY DESIGN | 2017-04-01 | 2017-07-29 | 2021-08-30 | 2021-12-27
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW80ELEC | 2 LAFAYETTE STREET ELECTRICAL UPGRADE | 3 | FINAL DESIGN | 2017-07-30 | 2018-01-25 | 2021-12-28 | 2022-06-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW80ELEC | 2 LAFAYETTE STREET ELECTRICAL UPGRADE | 4 | BID AWARD AND REGISTER CONTRCT | 2018-01-26 | 2018-04-25 | 2023-06-01 | 2023-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW80ELEC | 2 LAFAYETTE STREET ELECTRICAL UPGRADE | 5 | CONSTRUCTION TO 25% | 2018-04-26 | 2018-08-23 | 2023-08-30 | 2023-12-27
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW80ELEC | 2 LAFAYETTE STREET ELECTRICAL UPGRADE | 6 | CONSTRUCTION TO 50% | 2018-08-24 | 2018-12-21 | 2023-12-28 | 2024-04-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW80ELEC | 2 LAFAYETTE STREET ELECTRICAL UPGRADE | 7 | CONSTRUCTION TO 75% | 2018-12-22 | 2019-04-20 | 2024-04-26 | 2024-08-23
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW80ELEC | 2 LAFAYETTE STREET ELECTRICAL UPGRADE | 8 | ORIGINAL EQUIP & FURNISHING | 2019-04-21 | 2019-07-19 | 2024-08-24 | 2024-11-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW80ELEC | 2 LAFAYETTE STREET ELECTRICAL UPGRADE | 9 | SUBSTANTIAL COMPLETION | 2019-07-20 | 2019-09-17 | 2024-11-22 | 2025-01-20
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW80ELEC | 2 LAFAYETTE STREET ELECTRICAL UPGRADE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-18 | 2019-10-17 | 2025-01-21 | 2025-11-02
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWCN001 | Sixth Street compost project | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2024-06-01 | 2024-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWCN001 | Sixth Street compost project | 2 | PRELIMINARY DESIGN | 2015-09-29 | 2016-01-26 | 2024-08-30 | 2024-12-27
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWCN001 | Sixth Street compost project | 3 | FINAL DESIGN | 2016-01-27 | 2016-07-24 | 2024-12-28 | 2025-06-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWCN001 | Sixth Street compost project | 4 | BID AWARD AND REGISTER CONTRCT | 2016-07-25 | 2016-10-22 | 2025-06-26 | 2025-09-23
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWCN001 | Sixth Street compost project | 5 | CONSTRUCTION TO 25% | 2016-10-23 | 2017-02-19 | 2025-09-24 | 2026-01-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWCN001 | Sixth Street compost project | 6 | CONSTRUCTION TO 50% | 2017-02-20 | 2017-06-19 | 2026-01-22 | 2026-05-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWCN001 | Sixth Street compost project | 7 | CONSTRUCTION TO 75% | 2017-06-20 | 2017-10-17 | 2026-05-22 | 2026-09-18
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWCN001 | Sixth Street compost project | 8 | ORIGINAL EQUIP & FURNISHING | 2017-10-18 | 2018-01-15 | 2026-09-19 | 2026-12-17
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWCN001 | Sixth Street compost project | 9 | SUBSTANTIAL COMPLETION | 2018-01-16 | 2018-03-16 | 2026-12-18 | 2027-02-15
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWCN001 | Sixth Street compost project | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-03-17 | 2018-04-15 | 2027-02-16 | 2027-03-17
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD05CYBR | 80 CENTRE ST. - NY COUNTY DA CYBERCRIME AND IDENTITY THEFT | 1 | DEVELOP SCOPE | 2012-02-12 | 2012-05-11 | 2017-03-14 | 2017-06-11
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD05CYBR | 80 CENTRE ST. - NY COUNTY DA CYBERCRIME AND IDENTITY THEFT | 2 | PRELIMINARY DESIGN | 2012-05-12 | 2012-09-08 | 2017-06-12 | 2017-10-09
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD05CYBR | 80 CENTRE ST. - NY COUNTY DA CYBERCRIME AND IDENTITY THEFT | 3 | FINAL DESIGN | 2012-09-09 | 2013-03-07 | 2017-10-10 | 2018-04-07
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD05CYBR | 80 CENTRE ST. - NY COUNTY DA CYBERCRIME AND IDENTITY THEFT | 4 | BID AWARD AND REGISTER CONTRCT | 2013-03-08 | 2013-06-05 | 2018-04-08 | 2018-07-06
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD05CYBR | 80 CENTRE ST. - NY COUNTY DA CYBERCRIME AND IDENTITY THEFT | 5 | CONSTRUCTION TO 25% | 2013-06-06 | 2013-10-03 | 2018-07-07 | 2018-11-03
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD05CYBR | 80 CENTRE ST. - NY COUNTY DA CYBERCRIME AND IDENTITY THEFT | 6 | CONSTRUCTION TO 50% | 2013-10-04 | 2014-01-31 | 2018-11-04 | 2019-03-03
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD05CYBR | 80 CENTRE ST. - NY COUNTY DA CYBERCRIME AND IDENTITY THEFT | 7 | CONSTRUCTION TO 75% | 2014-02-01 | 2014-05-31 | 2019-03-04 | 2025-07-31
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD05CYBR | 80 CENTRE ST. - NY COUNTY DA CYBERCRIME AND IDENTITY THEFT | 8 | ORIGINAL EQUIP & FURNISHING | 2014-06-01 | 2014-08-29 | 2020-07-01 | 2020-09-28
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD05CYBR | 80 CENTRE ST. - NY COUNTY DA CYBERCRIME AND IDENTITY THEFT | 9 | SUBSTANTIAL COMPLETION | 2014-08-30 | 2014-10-28 | 2020-09-29 | 2020-11-27
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD05CYBR | 80 CENTRE ST. - NY COUNTY DA CYBERCRIME AND IDENTITY THEFT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-10-29 | 2014-11-27 | 2020-11-28 | 2022-06-30
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD05DAHV | 80 CENTRE ST. - NY COUNTY DA HVAC UPGRADE SERVER ROOM | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-08-29 | 2020-06-01 | 2020-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD05DAHV | 80 CENTRE ST. - NY COUNTY DA HVAC UPGRADE SERVER ROOM | 2 | PRELIMINARY DESIGN | 2020-08-30 | 2020-12-27 | 2020-08-30 | 2020-12-27
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD05DAHV | 80 CENTRE ST. - NY COUNTY DA HVAC UPGRADE SERVER ROOM | 3 | FINAL DESIGN | 2020-12-28 | 2021-06-25 | 2020-12-28 | 2021-06-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD05DAHV | 80 CENTRE ST. - NY COUNTY DA HVAC UPGRADE SERVER ROOM | 4 | BID AWARD AND REGISTER CONTRCT | 2021-06-26 | 2021-09-23 | 2021-06-26 | 2021-09-23
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD05DAHV | 80 CENTRE ST. - NY COUNTY DA HVAC UPGRADE SERVER ROOM | 5 | CONSTRUCTION TO 25% | 2021-09-24 | 2022-01-21 | 2021-09-24 | 2022-01-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD05DAHV | 80 CENTRE ST. - NY COUNTY DA HVAC UPGRADE SERVER ROOM | 6 | CONSTRUCTION TO 50% | 2022-01-22 | 2022-05-21 | 2022-01-22 | 2022-05-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD05DAHV | 80 CENTRE ST. - NY COUNTY DA HVAC UPGRADE SERVER ROOM | 7 | CONSTRUCTION TO 75% | 2022-05-22 | 2022-09-18 | 2022-05-22 | 2022-09-18
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD05DAHV | 80 CENTRE ST. - NY COUNTY DA HVAC UPGRADE SERVER ROOM | 8 | ORIGINAL EQUIP & FURNISHING | 2022-09-19 | 2022-12-17 | 2022-09-19 | 2022-12-17
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD05DAHV | 80 CENTRE ST. - NY COUNTY DA HVAC UPGRADE SERVER ROOM | 9 | SUBSTANTIAL COMPLETION | 2022-12-18 | 2023-02-15 | 2022-12-18 | 2023-02-15
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD05DAHV | 80 CENTRE ST. - NY COUNTY DA HVAC UPGRADE SERVER ROOM | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-02-16 | 2023-03-17 | 2023-02-16 | 2023-03-17
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD5BAG | 1 CENTRE ST.- BIG APPLE GREETER | 1 | DEVELOP SCOPE | 2005-07-01 | 2005-09-28 | 2005-07-01 | 2005-09-28
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD5BAG | 1 CENTRE ST.- BIG APPLE GREETER | 2 | PRELIMINARY DESIGN | 2005-09-29 | 2006-01-26 | 2005-09-29 | 2006-01-26
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD5BAG | 1 CENTRE ST.- BIG APPLE GREETER | 3 | FINAL DESIGN | 2006-01-27 | 2006-07-25 | 2006-01-27 | 2006-07-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD5BAG | 1 CENTRE ST.- BIG APPLE GREETER | 4 | BID AWARD AND REGISTER CONTRCT | 2006-07-26 | 2006-10-23 | 2006-07-26 | 2006-10-23
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD5BAG | 1 CENTRE ST.- BIG APPLE GREETER | 5 | CONSTRUCTION TO 25% | 2006-10-24 | 2007-10-18 | 2024-06-01 | 2027-01-16
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD5BAG | 1 CENTRE ST.- BIG APPLE GREETER | 6 | CONSTRUCTION TO 50% | 2007-10-19 | 2008-10-12 | 2027-01-17 | 2029-09-02
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD5BAG | 1 CENTRE ST.- BIG APPLE GREETER | 7 | CONSTRUCTION TO 75% | 2008-10-13 | 2009-10-07 | 2029-09-03 | 2030-08-28
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD5BAG | 1 CENTRE ST.- BIG APPLE GREETER | 8 | ORIGINAL EQUIP & FURNISHING | 2009-10-08 | 2010-10-02 | 2030-08-29 | 2030-10-27
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD5BAG | 1 CENTRE ST.- BIG APPLE GREETER | 9 | SUBSTANTIAL COMPLETION | 2010-10-03 | 2011-09-27 | 2030-10-28 | 2030-11-11
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD5BAG | 1 CENTRE ST.- BIG APPLE GREETER | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2011-09-28 | 2011-12-26 | 2030-11-12 | 2030-11-26
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWDNTEW | NONTRADITIONAL EMPLOYMENT FOR WOMEN 243 W 20th St | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-08-29 | 2023-06-01 | 2023-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWDNTEW | NONTRADITIONAL EMPLOYMENT FOR WOMEN 243 W 20th St | 2 | PRELIMINARY DESIGN | 2020-08-30 | 2020-12-27 | 2023-08-30 | 2023-12-27
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWDNTEW | NONTRADITIONAL EMPLOYMENT FOR WOMEN 243 W 20th St | 3 | FINAL DESIGN | 2020-12-28 | 2021-06-25 | 2023-12-28 | 2024-06-24
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWDNTEW | NONTRADITIONAL EMPLOYMENT FOR WOMEN 243 W 20th St | 4 | BID AWARD AND REGISTER CONTRCT | 2021-06-26 | 2021-09-23 | 2024-06-25 | 2024-09-22
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWDNTEW | NONTRADITIONAL EMPLOYMENT FOR WOMEN 243 W 20th St | 5 | CONSTRUCTION TO 25% | 2021-09-24 | 2022-01-21 | 2024-09-23 | 2025-01-20
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWDNTEW | NONTRADITIONAL EMPLOYMENT FOR WOMEN 243 W 20th St | 6 | CONSTRUCTION TO 50% | 2022-01-22 | 2022-05-21 | 2025-01-21 | 2025-05-20
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWDNTEW | NONTRADITIONAL EMPLOYMENT FOR WOMEN 243 W 20th St | 7 | CONSTRUCTION TO 75% | 2022-05-22 | 2022-09-18 | 2025-05-21 | 2025-09-17
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWDNTEW | NONTRADITIONAL EMPLOYMENT FOR WOMEN 243 W 20th St | 8 | ORIGINAL EQUIP & FURNISHING | 2022-09-19 | 2022-12-17 | 2025-09-18 | 2025-12-16
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWDNTEW | NONTRADITIONAL EMPLOYMENT FOR WOMEN 243 W 20th St | 9 | SUBSTANTIAL COMPLETION | 2022-12-18 | 2023-02-15 | 2025-12-17 | 2026-02-14
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWDNTEW | NONTRADITIONAL EMPLOYMENT FOR WOMEN 243 W 20th St | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-02-16 | 2023-03-17 | 2026-02-15 | 2026-03-16
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWM77FJC | 80 CENTRE ST. - MANHATTAN FAMILY JUSTICE CENTER | 9 | SUBSTANTIAL COMPLETION | 2014-12-25 | 2015-02-22 | 2014-12-25 | 2015-02-22
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWM77FJC | 80 CENTRE ST. - MANHATTAN FAMILY JUSTICE CENTER | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-02-23 | 2015-03-24 | 2015-02-23 | 2015-03-24
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWMOCSIT1 | MOCS IT NETWORK INFRASTRUCTURE 100 GOLD STREET 2ND FL | 1 | DEVELOP SCOPE | 2021-06-01 | 2021-08-29 | 2021-06-01 | 2021-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWMOCSIT1 | MOCS IT NETWORK INFRASTRUCTURE 100 GOLD STREET 2ND FL | 2 | PRELIMINARY DESIGN | 2021-08-30 | 2021-12-27 | 2021-08-30 | 2021-12-27
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWMOCSIT1 | MOCS IT NETWORK INFRASTRUCTURE 100 GOLD STREET 2ND FL | 3 | FINAL DESIGN | 2021-12-28 | 2022-06-25 | 2021-12-28 | 2022-06-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWMOCSIT1 | MOCS IT NETWORK INFRASTRUCTURE 100 GOLD STREET 2ND FL | 4 | BID AWARD AND REGISTER CONTRCT | 2022-06-26 | 2022-09-23 | 2022-06-26 | 2022-09-23
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWMOCSIT1 | MOCS IT NETWORK INFRASTRUCTURE 100 GOLD STREET 2ND FL | 5 | CONSTRUCTION TO 25% | 2022-09-24 | 2023-01-21 | 2022-09-24 | 2023-01-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWMOCSIT1 | MOCS IT NETWORK INFRASTRUCTURE 100 GOLD STREET 2ND FL | 6 | CONSTRUCTION TO 50% | 2023-01-22 | 2023-05-21 | 2023-01-22 | 2023-05-21
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWMOCSIT1 | MOCS IT NETWORK INFRASTRUCTURE 100 GOLD STREET 2ND FL | 7 | CONSTRUCTION TO 75% | 2023-05-22 | 2023-09-18 | 2023-05-22 | 2023-09-18
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWMOCSIT1 | MOCS IT NETWORK INFRASTRUCTURE 100 GOLD STREET 2ND FL | 8 | ORIGINAL EQUIP & FURNISHING | 2023-09-19 | 2023-12-17 | 2023-09-19 | 2023-12-17
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWMOCSIT1 | MOCS IT NETWORK INFRASTRUCTURE 100 GOLD STREET 2ND FL | 9 | SUBSTANTIAL COMPLETION | 2023-12-18 | 2024-02-15 | 2023-12-18 | 2024-02-15
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWMOCSIT1 | MOCS IT NETWORK INFRASTRUCTURE 100 GOLD STREET 2ND FL | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-02-16 | 2024-03-16 | 2024-02-16 | 2024-03-16
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCACIP06 | M140 - SYSTEM REPLACEMENT | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-06-30 | 2020-06-01 | 2020-06-30
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCACIP06 | M140 - SYSTEM REPLACEMENT | 2 | BID AWARD AND REGISTER CONTRCT | 2020-07-01 | 2020-08-29 | 2020-07-01 | 2020-08-29
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCACIP06 | M140 - SYSTEM REPLACEMENT | 3 | CONSTRUCTION TO 50% | 2020-08-30 | 2021-02-25 | 2020-08-30 | 2021-02-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCACIP06 | M140 - SYSTEM REPLACEMENT | 4 | CONSTRUCTION TO 75% | 2021-02-26 | 2021-05-26 | 2021-02-26 | 2021-05-26
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCACIP06 | M140 - SYSTEM REPLACEMENT | 5 | SUBSTANTIAL COMPLETION | 2021-05-27 | 2021-07-25 | 2021-05-27 | 2021-07-25
20201123 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCACIP06 | M140 - SYSTEM REPLACEMENT | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-07-26 | 2021-08-24 | 2021-07-26 | 2021-08-24
20201123 | QUEENS | 037 | NEW YORK PUBLIC LIBRARY | LN20LSCRF | Library Services Center - Roof Deck Replacement | 1 | DEVELOP SCOPE | 2019-09-01 | 2019-11-29 | 2019-09-01 | 2019-11-29
20201123 | QUEENS | 037 | NEW YORK PUBLIC LIBRARY | LN20LSCRF | Library Services Center - Roof Deck Replacement | 2 | DESIGN | 2019-11-30 | 2020-11-28 | 2019-11-30 | 2020-11-28
20201123 | QUEENS | 037 | NEW YORK PUBLIC LIBRARY | LN20LSCRF | Library Services Center - Roof Deck Replacement | 3 | BID/ REGISTER CONTRACT | 2020-11-29 | 2021-08-25 | 2020-11-29 | 2021-08-25
20201123 | QUEENS | 037 | NEW YORK PUBLIC LIBRARY | LN20LSCRF | Library Services Center - Roof Deck Replacement | 4 | CONSTRUCTION | 2021-08-26 | 2022-08-25 | 2021-08-26 | 2022-08-25
20201123 | QUEENS | 037 | NEW YORK PUBLIC LIBRARY | LN20LSCRF | Library Services Center - Roof Deck Replacement | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-08-26 | 2023-08-25 | 2022-08-26 | 2023-08-25
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQ122-GEN | SYSTEMWIDE - General Projects/Infrastructure | 1 | DESIGN | 2012-04-01 | 2012-04-30 | 2012-04-01 | 2012-04-30
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQ122-GEN | SYSTEMWIDE - General Projects/Infrastructure | 2 | BID AWARD AND REGISTER CONTRCT | 2012-05-01 | 2012-07-29 | 2012-05-01 | 2012-07-29
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQ122-GEN | SYSTEMWIDE - General Projects/Infrastructure | 3 | CONSTRUCTION | 2012-07-30 | 2013-01-25 | 2012-07-30 | 2030-07-30
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQ122-GEN | SYSTEMWIDE - General Projects/Infrastructure | 4 | ORIGINAL EQUIP & FURNISHING | 2013-01-26 | 2013-04-25 | 2030-07-31 | 2030-10-28
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQ122-GEN | SYSTEMWIDE - General Projects/Infrastructure | 5 | SUBSTANTIAL COMPLETION | 2013-04-26 | 2013-05-25 | 2030-10-29 | 2030-11-27
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQ122-GEN | SYSTEMWIDE - General Projects/Infrastructure | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-05-26 | 2013-06-24 | 2030-11-28 | 2030-12-27
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQBCHREAD | BROAD CHANNEL: Library Seating Area | 1 | DESIGN | 2019-12-01 | 2021-11-19 | 2019-12-01 | 2021-11-19
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQBCHREAD | BROAD CHANNEL: Library Seating Area | 2 | BID AWARD AND REGISTER CONTRCT | 2021-11-20 | 2022-11-14 | 2021-11-20 | 2022-11-14
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQBCHREAD | BROAD CHANNEL: Library Seating Area | 3 | CONSTRUCTION | 2022-11-15 | 2028-11-12 | 2022-11-15 | 2028-11-12
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQBC-ROOF | BROAD CHANNEL: New roof | 1 | DESIGN | 2019-01-01 | 2020-12-20 | 2019-01-01 | 2020-12-20
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQBC-ROOF | BROAD CHANNEL: New roof | 2 | BID AWARD AND REGISTER CONTRCT | 2020-12-21 | 2021-12-15 | 2020-12-21 | 2021-12-15
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQBC-ROOF | BROAD CHANNEL: New roof | 3 | CONSTRUCTION | 2021-12-16 | 2027-12-14 | 2021-12-16 | 2027-12-14
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQBR-ROOF | BROADWAY - ROOF | 1 | DESIGN | 2019-01-01 | 2020-12-20 | 2019-01-01 | 2020-12-20
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQBR-ROOF | BROADWAY - ROOF | 2 | BID AWARD AND REGISTER CONTRCT | 2020-12-21 | 2021-12-15 | 2020-12-21 | 2021-12-15
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQBR-ROOF | BROADWAY - ROOF | 3 | CONSTRUCTION | 2021-12-16 | 2027-12-14 | 2021-12-16 | 2027-12-14
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQC122-JH | JACKSON HEIGHTS - Branch Expansion & Renovation | 1 | DEVELOP SCOPE | 2010-07-01 | 2010-09-28 | 2020-06-30 | 2022-06-30
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQC122-JH | JACKSON HEIGHTS - Branch Expansion & Renovation | 2 | PRELIMINARY DESIGN | 2010-09-29 | 2011-01-26 | 2022-07-01 | 2022-10-28
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQC122-JH | JACKSON HEIGHTS - Branch Expansion & Renovation | 3 | FINAL DESIGN | 2011-01-27 | 2011-07-25 | 2022-10-29 | 2023-04-26
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQC122-JH | JACKSON HEIGHTS - Branch Expansion & Renovation | 4 | BID AWARD AND REGISTER CONTRCT | 2011-07-26 | 2011-10-23 | 2023-04-27 | 2023-07-25
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQC122-JH | JACKSON HEIGHTS - Branch Expansion & Renovation | 5 | CONSTRUCTION TO 25% | 2011-10-24 | 2012-02-20 | 2023-07-26 | 2023-11-22
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQC122-JH | JACKSON HEIGHTS - Branch Expansion & Renovation | 6 | CONSTRUCTION TO 50% | 2012-02-21 | 2012-06-19 | 2023-11-23 | 2024-03-21
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQC122-JH | JACKSON HEIGHTS - Branch Expansion & Renovation | 7 | CONSTRUCTION TO 75% | 2012-06-20 | 2012-10-17 | 2024-03-22 | 2024-07-19
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQC122-JH | JACKSON HEIGHTS - Branch Expansion & Renovation | 8 | ORIGINAL EQUIP & FURNISHING | 2012-10-18 | 2013-01-15 | 2024-07-20 | 2024-10-17
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQC122-JH | JACKSON HEIGHTS - Branch Expansion & Renovation | 9 | SUBSTANTIAL COMPLETION | 2013-01-16 | 2013-03-16 | 2024-10-18 | 2024-12-16
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQC122-JH | JACKSON HEIGHTS - Branch Expansion & Renovation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-03-17 | 2013-04-15 | 2024-12-17 | 2025-01-15
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQCA19FRH | FOREST HILLS: Site work and drainage | 1 | DESIGN | 2019-01-01 | 2020-12-20 | 2019-01-01 | 2020-12-20
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQCA19FRH | FOREST HILLS: Site work and drainage | 2 | BID AWARD AND REGISTER CONTRCT | 2020-12-21 | 2021-12-15 | 2020-12-21 | 2021-12-15
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQCA19FRH | FOREST HILLS: Site work and drainage | 3 | CONSTRUCTION | 2021-12-16 | 2027-12-14 | 2021-12-16 | 2027-12-14
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQCA19LHS | LANGSTON HUGHES:BMS SYSTEM | 1 | DESIGN | 2019-01-01 | 2020-12-20 | 2019-01-01 | 2020-12-20
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQCA19LHS | LANGSTON HUGHES:BMS SYSTEM | 2 | BID AWARD AND REGISTER CONTRCT | 2020-12-21 | 2021-12-15 | 2020-12-21 | 2021-12-15
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQCA19LHS | LANGSTON HUGHES:BMS SYSTEM | 3 | CONSTRUCTION | 2021-12-16 | 2027-12-14 | 2021-12-16 | 2027-12-14
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQCA19QVG | QUEENS VILLAGE: Exterior Rehabilitation, ADA Access, Windows | 1 | DESIGN | 2019-01-01 | 2020-12-20 | 2019-01-01 | 2020-12-20
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQCA19QVG | QUEENS VILLAGE: Exterior Rehabilitation, ADA Access, Windows | 2 | BID AWARD AND REGISTER CONTRCT | 2020-12-21 | 2021-12-15 | 2020-12-21 | 2021-12-15
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQCA19QVG | QUEENS VILLAGE: Exterior Rehabilitation, ADA Access, Windows | 3 | CONSTRUCTION | 2021-12-16 | 2027-12-14 | 2021-12-16 | 2027-12-14
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQCA19WSD | WOODSIDE: Branch Renovation | 1 | DESIGN | 2019-01-01 | 2020-12-20 | 2019-01-01 | 2020-12-20
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQCA19WSD | WOODSIDE: Branch Renovation | 2 | BID AWARD AND REGISTER CONTRCT | 2020-12-21 | 2021-12-15 | 2020-12-21 | 2021-12-15
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQCA19WSD | WOODSIDE: Branch Renovation | 3 | CONSTRUCTION | 2021-12-16 | 2027-12-14 | 2021-12-16 | 2027-12-14
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQCA20MGR | McGoldrick: New Roof | 1 | DESIGN | 2020-07-01 | 2022-06-20 | 2020-07-01 | 2022-06-20
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQCA20MGR | McGoldrick: New Roof | 2 | BID AWARD AND REGISTER CONTRCT | 2022-06-21 | 2023-06-15 | 2022-06-21 | 2023-06-15
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQCA20MGR | McGoldrick: New Roof | 3 | CONSTRUCTION | 2018-07-03 | 2024-06-30 | 2018-07-03 | 2024-06-30
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQCELHVAC | CENTRAL: Facade Restoration, Replace HVAC, Roof Replacement | 1 | DESIGN | 2019-01-01 | 2020-12-20 | 2019-01-01 | 2020-12-20
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQCELHVAC | CENTRAL: Facade Restoration, Replace HVAC, Roof Replacement | 2 | BID AWARD AND REGISTER CONTRCT | 2020-12-21 | 2021-12-15 | 2020-12-21 | 2021-12-15
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQCELHVAC | CENTRAL: Facade Restoration, Replace HVAC, Roof Replacement | 3 | CONSTRUCTION | 2021-12-16 | 2027-12-14 | 2021-12-16 | 2027-12-14
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQCLDC-CE | Central Library: Rehabilitation of Ceilings | 1 | DESIGN | 2019-01-01 | 2020-12-20 | 2019-01-01 | 2020-12-20
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQCLDC-CE | Central Library: Rehabilitation of Ceilings | 2 | BID AWARD AND REGISTER CONTRCT | 2020-12-21 | 2021-12-15 | 2020-12-21 | 2021-12-15
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQCLDC-CE | Central Library: Rehabilitation of Ceilings | 3 | CONSTRUCTION | 2021-12-16 | 2027-12-14 | 2021-12-16 | 2027-12-14
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQCORENOV | CORONA : Branch Expansion and Renovation | 1 | DESIGN | 2019-01-01 | 2020-12-20 | 2019-01-01 | 2020-12-20
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQCORENOV | CORONA : Branch Expansion and Renovation | 2 | BID AWARD AND REGISTER CONTRCT | 2020-12-21 | 2021-12-15 | 2020-12-21 | 2021-12-15
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQCORENOV | CORONA : Branch Expansion and Renovation | 3 | CONSTRUCTION | 2021-12-16 | 2027-12-14 | 2021-12-16 | 2027-12-14
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQD122LAE | LAURELTON: Branch Renovation | 1 | DESIGN | 2019-01-01 | 2020-12-20 | 2019-01-01 | 2020-12-20
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQD122LAE | LAURELTON: Branch Renovation | 2 | BID AWARD AND REGISTER CONTRCT | 2020-12-21 | 2021-12-15 | 2020-12-21 | 2021-12-15
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQD122LAE | LAURELTON: Branch Renovation | 3 | CONSTRUCTION | 2021-12-16 | 2027-12-14 | 2021-12-16 | 2027-12-14
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQD122VEN | Mobile Library Unit | 1 | DESIGN | 2019-01-01 | 2020-12-20 | 2019-01-01 | 2020-12-20
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQD122VEN | Mobile Library Unit | 2 | BID AWARD AND REGISTER CONTRCT | 2020-12-21 | 2021-12-15 | 2020-12-21 | 2021-12-15
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQD122VEN | Mobile Library Unit | 3 | CONSTRUCTION | 2021-12-16 | 2027-12-14 | 2021-12-16 | 2027-12-14
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQFHREAD | FOREST HILLS OUTDOOR READING SPACE | 1 | DESIGN | 2018-06-30 | 2018-07-29 | 2023-12-01 | 2023-12-30
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQFHREAD | FOREST HILLS OUTDOOR READING SPACE | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-30 | 2018-10-27 | 2023-12-31 | 2024-03-29
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQFHREAD | FOREST HILLS OUTDOOR READING SPACE | 3 | CONSTRUCTION | 2018-10-28 | 2019-04-25 | 2024-03-30 | 2024-09-25
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQFHREAD | FOREST HILLS OUTDOOR READING SPACE | 4 | ORIGINAL EQUIP & FURNISHING | 2019-04-26 | 2019-07-24 | 2024-09-26 | 2024-12-24
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQFHREAD | FOREST HILLS OUTDOOR READING SPACE | 5 | SUBSTANTIAL COMPLETION | 2019-07-25 | 2019-08-23 | 2024-12-25 | 2025-01-23
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQFHREAD | FOREST HILLS OUTDOOR READING SPACE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-08-24 | 2019-09-22 | 2025-01-24 | 2025-02-22
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQFHWIND | FOREST HILLS - Windows and Doors Replacement | 1 | DESIGN | 2018-06-30 | 2018-07-29 | 2023-01-01 | 2023-01-30
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQFHWIND | FOREST HILLS - Windows and Doors Replacement | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-30 | 2018-10-27 | 2023-01-31 | 2023-04-30
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQFHWIND | FOREST HILLS - Windows and Doors Replacement | 3 | CONSTRUCTION | 2018-10-28 | 2019-04-25 | 2023-05-01 | 2024-12-30
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQFHWIND | FOREST HILLS - Windows and Doors Replacement | 4 | ORIGINAL EQUIP & FURNISHING | 2019-04-26 | 2019-07-24 | 2024-12-31 | 2025-03-30
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQFHWIND | FOREST HILLS - Windows and Doors Replacement | 5 | SUBSTANTIAL COMPLETION | 2019-07-25 | 2019-08-23 | 2025-03-31 | 2025-04-29
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQFHWIND | FOREST HILLS - Windows and Doors Replacement | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-08-24 | 2019-09-22 | 2025-04-30 | 2025-05-29
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQFM-HVAC | FRESH MEADOWS: HVAC (RTU Replacement) and Roof Replacement | 1 | DESIGN | 2019-01-01 | 2020-12-20 | 2019-01-01 | 2020-12-20
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQFM-HVAC | FRESH MEADOWS: HVAC (RTU Replacement) and Roof Replacement | 2 | BID AWARD AND REGISTER CONTRCT | 2020-12-21 | 2021-12-15 | 2020-12-21 | 2021-12-15
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQFM-HVAC | FRESH MEADOWS: HVAC (RTU Replacement) and Roof Replacement | 3 | CONSTRUCTION | 2021-12-16 | 2027-12-14 | 2021-12-16 | 2027-12-14
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQHBW/D | HOWARD BEACH WINDOWS/DOORS | 1 | DESIGN | 2019-01-01 | 2020-12-20 | 2019-01-01 | 2020-12-20
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQHBW/D | HOWARD BEACH WINDOWS/DOORS | 2 | BID AWARD AND REGISTER CONTRCT | 2020-12-21 | 2021-12-15 | 2020-12-21 | 2021-12-15
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQHBW/D | HOWARD BEACH WINDOWS/DOORS | 3 | CONSTRUCTION | 2021-12-16 | 2027-12-14 | 2021-12-16 | 2027-12-14
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQHILRENO | HILLCREST: Renovation | 1 | DESIGN | 2019-01-01 | 2020-12-20 | 2019-01-01 | 2020-12-20
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQHILRENO | HILLCREST: Renovation | 2 | BID AWARD AND REGISTER CONTRCT | 2020-12-21 | 2021-12-15 | 2020-12-21 | 2021-12-15
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQHILRENO | HILLCREST: Renovation | 3 | CONSTRUCTION | 2021-12-16 | 2027-12-14 | 2021-12-16 | 2027-12-14
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQLAHEXTR | LANGSTON HUGHES: Exterior Restoration | 1 | DESIGN | 2019-01-01 | 2020-12-20 | 2019-01-01 | 2020-12-20
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQLAHEXTR | LANGSTON HUGHES: Exterior Restoration | 2 | BID AWARD AND REGISTER CONTRCT | 2020-12-21 | 2021-12-15 | 2020-12-21 | 2021-12-15
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQLAHEXTR | LANGSTON HUGHES: Exterior Restoration | 3 | CONSTRUCTION | 2021-12-16 | 2027-12-14 | 2021-12-16 | 2027-12-14
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQLARENOV | LAURELTON - RENOVATION | 1 | DESIGN | 2018-06-30 | 2018-07-29 | 2023-03-24 | 2023-04-22
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQLARENOV | LAURELTON - RENOVATION | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-30 | 2018-10-27 | 2023-04-23 | 2023-07-21
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQLARENOV | LAURELTON - RENOVATION | 3 | CONSTRUCTION | 2018-10-28 | 2019-04-25 | 2023-07-22 | 2024-01-17
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQLARENOV | LAURELTON - RENOVATION | 4 | ORIGINAL EQUIP & FURNISHING | 2019-04-26 | 2019-07-24 | 2024-01-18 | 2024-04-16
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQLARENOV | LAURELTON - RENOVATION | 5 | SUBSTANTIAL COMPLETION | 2019-07-25 | 2019-08-23 | 2024-04-17 | 2024-05-16
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQLARENOV | LAURELTON - RENOVATION | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-08-24 | 2019-09-22 | 2024-05-17 | 2024-06-15
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQLFK-INT | Lefrak City Library - Interior renovations | 1 | DESIGN | 2019-01-01 | 2020-12-20 | 2019-01-01 | 2020-12-20
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQLFK-INT | Lefrak City Library - Interior renovations | 2 | BID AWARD AND REGISTER CONTRCT | 2020-12-21 | 2021-12-15 | 2020-12-21 | 2021-12-15
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQLFK-INT | Lefrak City Library - Interior renovations | 3 | CONSTRUCTION | 2021-12-16 | 2027-12-14 | 2021-12-16 | 2027-12-14
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQLI-ROOF | LONG ISLAND CITY: New Roof | 1 | DESIGN | 2019-01-01 | 2020-12-20 | 2019-01-01 | 2020-12-20
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQLI-ROOF | LONG ISLAND CITY: New Roof | 2 | BID AWARD AND REGISTER CONTRCT | 2020-12-21 | 2021-12-15 | 2020-12-21 | 2021-12-15
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQLI-ROOF | LONG ISLAND CITY: New Roof | 3 | CONSTRUCTION | 2021-12-16 | 2027-12-14 | 2021-12-16 | 2027-12-14
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQMA-HVAC | MASPETH - HVAC | 1 | DESIGN | 2019-01-01 | 2020-12-20 | 2019-01-01 | 2020-12-20
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQMA-HVAC | MASPETH - HVAC | 2 | BID AWARD AND REGISTER CONTRCT | 2020-12-21 | 2021-12-15 | 2020-12-21 | 2021-12-15
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQMA-HVAC | MASPETH - HVAC | 3 | CONSTRUCTION | 2021-12-16 | 2027-12-14 | 2021-12-16 | 2027-12-14
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQMAROOF | MASPETH ROOF | 1 | DESIGN | 2019-01-01 | 2020-12-20 | 2019-01-01 | 2020-12-20
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQMAROOF | MASPETH ROOF | 2 | BID AWARD AND REGISTER CONTRCT | 2020-12-21 | 2021-12-15 | 2020-12-21 | 2021-12-15
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQMAROOF | MASPETH ROOF | 3 | CONSTRUCTION | 2021-12-16 | 2027-12-14 | 2021-12-16 | 2027-12-14
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQNO-HVAC | NORTH HILLS - HVAC | 1 | DESIGN | 2019-01-01 | 2020-12-20 | 2019-01-01 | 2020-12-20
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQNO-HVAC | NORTH HILLS - HVAC | 2 | BID AWARD AND REGISTER CONTRCT | 2020-12-21 | 2021-12-15 | 2020-12-21 | 2021-12-15
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQNO-HVAC | NORTH HILLS - HVAC | 3 | CONSTRUCTION | 2021-12-16 | 2027-12-14 | 2021-12-16 | 2027-12-14
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQPOMHVAC | POMONOK - HVAC System Replacement | 1 | DESIGN | 2018-06-30 | 2018-07-29 | 2023-06-30 | 2023-07-29
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQPOMHVAC | POMONOK - HVAC System Replacement | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-30 | 2018-10-27 | 2023-07-30 | 2023-10-27
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQPOMHVAC | POMONOK - HVAC System Replacement | 3 | CONSTRUCTION | 2018-10-28 | 2019-04-25 | 2023-10-28 | 2024-04-24
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQPOMHVAC | POMONOK - HVAC System Replacement | 4 | ORIGINAL EQUIP & FURNISHING | 2019-04-26 | 2019-07-24 | 2024-04-25 | 2024-07-23
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQPOMHVAC | POMONOK - HVAC System Replacement | 5 | SUBSTANTIAL COMPLETION | 2019-07-25 | 2019-08-23 | 2024-07-24 | 2024-08-22
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQPOMHVAC | POMONOK - HVAC System Replacement | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-08-24 | 2019-09-22 | 2024-08-23 | 2024-09-21
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQQ122-MT | MITCHELL-LINDEN - Site Acquisition & Renovation | 1 | DESIGN | 2020-06-30 | 2020-07-29 | 2020-06-30 | 2020-07-29
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQQ122-MT | MITCHELL-LINDEN - Site Acquisition & Renovation | 2 | BID AWARD AND REGISTER CONTRCT | 2020-07-30 | 2020-10-27 | 2020-07-30 | 2020-10-27
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQQ122-MT | MITCHELL-LINDEN - Site Acquisition & Renovation | 3 | CONSTRUCTION | 2020-10-28 | 2021-04-25 | 2020-10-28 | 2021-04-25
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQQ122-MT | MITCHELL-LINDEN - Site Acquisition & Renovation | 4 | ORIGINAL EQUIP & FURNISHING | 2021-04-26 | 2021-07-24 | 2021-04-26 | 2021-07-24
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQQ122-MT | MITCHELL-LINDEN - Site Acquisition & Renovation | 5 | SUBSTANTIAL COMPLETION | 2021-07-25 | 2021-08-23 | 2021-07-25 | 2021-08-23
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQQ122-MT | MITCHELL-LINDEN - Site Acquisition & Renovation | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-08-24 | 2021-09-22 | 2021-08-24 | 2023-09-22
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQQA21CTQ | Court Square - New Library Fit Out | 1 | DESIGN | 2020-07-01 | 2022-06-20 | 2020-07-01 | 2022-06-20
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQQA21CTQ | Court Square - New Library Fit Out | 2 | BID AWARD AND REGISTER CONTRCT | 2022-06-21 | 2023-06-15 | 2022-06-21 | 2023-06-15
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQQA21CTQ | Court Square - New Library Fit Out | 3 | CONSTRUCTION | 2023-06-16 | 2029-06-13 | 2023-06-16 | 2029-06-13
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQQV-TECH | QUEENS VILLAGE: Improvements | 1 | DESIGN | 2019-01-01 | 2020-12-20 | 2019-01-01 | 2020-12-20
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQQV-TECH | QUEENS VILLAGE: Improvements | 2 | BID AWARD AND REGISTER CONTRCT | 2020-12-21 | 2021-12-15 | 2020-12-21 | 2021-12-15
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQQV-TECH | QUEENS VILLAGE: Improvements | 3 | CONSTRUCTION | 2021-12-16 | 2027-12-14 | 2021-12-16 | 2027-12-14
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQRS-EXTR | ROSEDALE: Branch Expansion and Renovation | 1 | DESIGN | 2019-01-01 | 2020-12-20 | 2019-01-01 | 2020-12-20
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQRS-EXTR | ROSEDALE: Branch Expansion and Renovation | 2 | BID AWARD AND REGISTER CONTRCT | 2020-12-21 | 2021-12-15 | 2020-12-21 | 2021-12-15
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQRS-EXTR | ROSEDALE: Branch Expansion and Renovation | 3 | CONSTRUCTION | 2021-12-16 | 2027-12-14 | 2021-12-16 | 2027-12-14
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQSE-ROOF | SEASIDE: New Roof | 1 | DESIGN | 2019-01-01 | 2020-12-20 | 2019-01-01 | 2020-12-20
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQSE-ROOF | SEASIDE: New Roof | 2 | BID AWARD AND REGISTER CONTRCT | 2020-12-21 | 2021-12-15 | 2020-12-21 | 2021-12-15
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQSE-ROOF | SEASIDE: New Roof | 3 | CONSTRUCTION | 2021-12-16 | 2027-12-14 | 2021-12-16 | 2027-12-14
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQSE-WIN | SEASIDE: Windows and Doors | 1 | DESIGN | 2019-01-01 | 2020-12-20 | 2019-01-01 | 2020-12-20
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQSE-WIN | SEASIDE: Windows and Doors | 2 | BID AWARD AND REGISTER CONTRCT | 2020-12-21 | 2021-12-15 | 2020-12-21 | 2021-12-15
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQSE-WIN | SEASIDE: Windows and Doors | 3 | CONSTRUCTION | 2021-12-16 | 2027-12-14 | 2021-12-16 | 2027-12-14
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQSJ-INT | SOUTH JAMAICA: Branch Renovation | 1 | DESIGN | 2019-01-01 | 2020-12-20 | 2019-01-01 | 2020-12-20
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQSJ-INT | SOUTH JAMAICA: Branch Renovation | 2 | BID AWARD AND REGISTER CONTRCT | 2020-12-21 | 2021-12-15 | 2020-12-21 | 2021-12-15
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQSJ-INT | SOUTH JAMAICA: Branch Renovation | 3 | CONSTRUCTION | 2021-12-16 | 2027-12-14 | 2021-12-16 | 2027-12-14
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQSTWSOLR | STEINWAY: Solar Panels | 1 | DESIGN | 2019-01-01 | 2020-12-20 | 2019-01-01 | 2020-12-20
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQSTWSOLR | STEINWAY: Solar Panels | 2 | BID AWARD AND REGISTER CONTRCT | 2020-12-21 | 2021-12-15 | 2020-12-21 | 2021-12-15
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQSTWSOLR | STEINWAY: Solar Panels | 3 | CONSTRUCTION | 2021-12-16 | 2027-12-14 | 2021-12-16 | 2027-12-14
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQSZ-RENO | SOUTH OZONE PARK - Branch Expansion and Renovation | 1 | DESIGN | 2019-01-01 | 2020-12-20 | 2019-01-01 | 2020-12-20
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQSZ-RENO | SOUTH OZONE PARK - Branch Expansion and Renovation | 2 | BID AWARD AND REGISTER CONTRCT | 2020-12-21 | 2021-12-15 | 2020-12-21 | 2021-12-15
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQSZ-RENO | SOUTH OZONE PARK - Branch Expansion and Renovation | 3 | CONSTRUCTION | 2021-12-16 | 2027-12-14 | 2021-12-16 | 2027-12-14
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQWP-MASO | WINDSOR PARK - MASONRY | 1 | DESIGN | 2019-01-01 | 2020-12-20 | 2019-01-01 | 2020-12-20
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQWP-MASO | WINDSOR PARK - MASONRY | 2 | BID AWARD AND REGISTER CONTRCT | 2020-12-21 | 2021-12-15 | 2020-12-21 | 2021-12-15
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQWP-MASO | WINDSOR PARK - MASONRY | 3 | CONSTRUCTION | 2021-12-16 | 2027-12-14 | 2021-12-16 | 2027-12-14
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQWP-TECH | WINDSOR PARK: Improvement | 1 | DESIGN | 2019-01-01 | 2020-12-20 | 2019-01-01 | 2020-12-20
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQWP-TECH | WINDSOR PARK: Improvement | 2 | BID AWARD AND REGISTER CONTRCT | 2020-12-21 | 2021-12-15 | 2020-12-21 | 2021-12-15
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQWP-TECH | WINDSOR PARK: Improvement | 3 | CONSTRUCTION | 2021-12-16 | 2027-12-14 | 2021-12-16 | 2027-12-14
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQWS-TEEN | WOODSIDE: Renovation | 1 | DESIGN | 2019-01-01 | 2020-12-20 | 2019-01-01 | 2020-12-20
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQWS-TEEN | WOODSIDE: Renovation | 2 | BID AWARD AND REGISTER CONTRCT | 2020-12-21 | 2021-12-15 | 2020-12-21 | 2021-12-15
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQWS-TEEN | WOODSIDE: Renovation | 3 | CONSTRUCTION | 2021-12-16 | 2027-12-14 | 2021-12-16 | 2027-12-14
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQWSTTECH | WHITESTONE: Technology Initiative | 1 | DESIGN | 2019-01-01 | 2020-12-20 | 2019-01-01 | 2020-12-20
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQWSTTECH | WHITESTONE: Technology Initiative | 2 | BID AWARD AND REGISTER CONTRCT | 2020-12-21 | 2021-12-15 | 2020-12-21 | 2021-12-15
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQWSTTECH | WHITESTONE: Technology Initiative | 3 | CONSTRUCTION | 2021-12-16 | 2027-12-14 | 2021-12-16 | 2027-12-14
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | SANDYLQLS | SANDY DAMAGES - QBPL | 1 | DESIGN | 2019-01-01 | 2020-12-20 | 2019-01-01 | 2020-12-20
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | SANDYLQLS | SANDY DAMAGES - QBPL | 2 | BID AWARD AND REGISTER CONTRCT | 2020-12-21 | 2021-12-15 | 2020-12-21 | 2021-12-15
20201123 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | SANDYLQLS | SANDY DAMAGES - QBPL | 3 | CONSTRUCTION | 2021-12-16 | 2027-12-14 | 2021-12-16 | 2027-12-14
20201123 | QUEENS | 042 | CITY UNIVERSITY | ACECUN801 | CUNY - Building Automation Controls Upgrade @ QCC | 1 | DEVELOP SCOPE | 2018-06-01 | 2018-08-29 | 2018-06-01 | 2018-08-29
20201123 | QUEENS | 042 | CITY UNIVERSITY | ACECUN801 | CUNY - Building Automation Controls Upgrade @ QCC | 2 | PRELIMINARY DESIGN | 2018-08-30 | 2018-12-27 | 2018-08-30 | 2018-12-27
20201123 | QUEENS | 042 | CITY UNIVERSITY | ACECUN801 | CUNY - Building Automation Controls Upgrade @ QCC | 3 | FINAL DESIGN | 2018-12-28 | 2019-06-25 | 2018-12-28 | 2019-06-25
20201123 | QUEENS | 042 | CITY UNIVERSITY | ACECUN801 | CUNY - Building Automation Controls Upgrade @ QCC | 4 | BID AWARD AND REGISTER CONTRCT | 2019-06-26 | 2019-09-23 | 2019-06-26 | 2019-09-23
20201123 | QUEENS | 042 | CITY UNIVERSITY | ACECUN801 | CUNY - Building Automation Controls Upgrade @ QCC | 5 | CONSTRUCTION TO 25% | 2019-09-24 | 2020-01-21 | 2019-09-24 | 2020-01-21
20201123 | QUEENS | 042 | CITY UNIVERSITY | ACECUN801 | CUNY - Building Automation Controls Upgrade @ QCC | 6 | CONSTRUCTION TO 50% | 2020-01-22 | 2020-05-20 | 2020-01-22 | 2020-05-20
20201123 | QUEENS | 042 | CITY UNIVERSITY | ACECUN801 | CUNY - Building Automation Controls Upgrade @ QCC | 7 | CONSTRUCTION TO 75% | 2020-05-21 | 2020-09-17 | 2020-05-21 | 2020-09-17
20201123 | QUEENS | 042 | CITY UNIVERSITY | ACECUN801 | CUNY - Building Automation Controls Upgrade @ QCC | 8 | ORIGINAL EQUIP & FURNISHING | 2020-09-18 | 2020-12-16 | 2020-09-18 | 2020-12-16
20201123 | QUEENS | 042 | CITY UNIVERSITY | ACECUN801 | CUNY - Building Automation Controls Upgrade @ QCC | 9 | SUBSTANTIAL COMPLETION | 2020-12-17 | 2021-02-14 | 2020-12-17 | 2021-02-14
20201123 | QUEENS | 042 | CITY UNIVERSITY | ACECUN801 | CUNY - Building Automation Controls Upgrade @ QCC | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-02-15 | 2021-03-16 | 2021-02-15 | 2021-03-16
20201123 | QUEENS | 042 | CITY UNIVERSITY | CA034QB13 | Fire Alarm Reconstruction - Phase 3 | 1 | DEVELOP SCOPE | 2017-06-01 | 2017-08-29 | 2017-06-01 | 2017-08-29
20201123 | QUEENS | 042 | CITY UNIVERSITY | CA034QB13 | Fire Alarm Reconstruction - Phase 3 | 2 | PRELIMINARY DESIGN | 2017-08-30 | 2017-12-27 | 2017-08-30 | 2017-12-27
20201123 | QUEENS | 042 | CITY UNIVERSITY | CA034QB13 | Fire Alarm Reconstruction - Phase 3 | 3 | FINAL DESIGN | 2017-12-28 | 2018-06-25 | 2017-12-28 | 2018-06-25
20201123 | QUEENS | 042 | CITY UNIVERSITY | CA034QB13 | Fire Alarm Reconstruction - Phase 3 | 4 | BID AWARD AND REGISTER CONTRCT | 2018-06-26 | 2018-09-23 | 2018-06-26 | 2018-09-23
20201123 | QUEENS | 042 | CITY UNIVERSITY | CA034QB13 | Fire Alarm Reconstruction - Phase 3 | 5 | CONSTRUCTION TO 25% | 2018-09-24 | 2019-01-21 | 2018-09-24 | 2019-01-21
20201123 | QUEENS | 042 | CITY UNIVERSITY | CA034QB13 | Fire Alarm Reconstruction - Phase 3 | 6 | CONSTRUCTION TO 50% | 2019-01-22 | 2019-05-21 | 2019-01-22 | 2019-05-21
20201123 | QUEENS | 042 | CITY UNIVERSITY | CA034QB13 | Fire Alarm Reconstruction - Phase 3 | 7 | CONSTRUCTION TO 75% | 2019-05-22 | 2019-09-18 | 2019-05-22 | 2019-09-18
20201123 | QUEENS | 042 | CITY UNIVERSITY | CA034QB13 | Fire Alarm Reconstruction - Phase 3 | 8 | ORIGINAL EQUIP & FURNISHING | 2019-09-19 | 2019-12-17 | 2019-09-19 | 2019-12-17
20201123 | QUEENS | 042 | CITY UNIVERSITY | CA034QB13 | Fire Alarm Reconstruction - Phase 3 | 9 | SUBSTANTIAL COMPLETION | 2019-12-18 | 2020-02-15 | 2019-12-18 | 2020-02-15
20201123 | QUEENS | 042 | CITY UNIVERSITY | CA034QB13 | Fire Alarm Reconstruction - Phase 3 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-02-16 | 2020-03-16 | 2020-02-16 | 2023-03-31
20201123 | QUEENS | 042 | CITY UNIVERSITY | CA052-017 | Flushing Immigration Center | 1 | DEVELOP SCOPE | 2017-06-01 | 2017-08-29 | 2020-07-01 | 2020-10-01
20201123 | QUEENS | 042 | CITY UNIVERSITY | CA052-017 | Flushing Immigration Center | 2 | PRELIMINARY DESIGN | 2017-08-30 | 2017-12-27 | 2020-10-02 | 2021-01-29
20201123 | QUEENS | 042 | CITY UNIVERSITY | CA052-017 | Flushing Immigration Center | 3 | FINAL DESIGN | 2017-12-28 | 2018-06-25 | 2021-01-30 | 2021-07-28
20201123 | QUEENS | 042 | CITY UNIVERSITY | CA052-017 | Flushing Immigration Center | 4 | BID AWARD AND REGISTER CONTRCT | 2018-06-26 | 2018-09-23 | 2021-07-29 | 2021-10-26
20201123 | QUEENS | 042 | CITY UNIVERSITY | CA052-017 | Flushing Immigration Center | 5 | CONSTRUCTION TO 25% | 2018-09-24 | 2019-01-21 | 2021-10-27 | 2022-02-23
20201123 | QUEENS | 042 | CITY UNIVERSITY | CA052-017 | Flushing Immigration Center | 6 | CONSTRUCTION TO 50% | 2019-01-22 | 2019-05-21 | 2022-02-24 | 2022-06-23
20201123 | QUEENS | 042 | CITY UNIVERSITY | CA052-017 | Flushing Immigration Center | 7 | CONSTRUCTION TO 75% | 2019-05-22 | 2019-09-18 | 2022-06-24 | 2022-10-21
20201123 | QUEENS | 042 | CITY UNIVERSITY | CA052-017 | Flushing Immigration Center | 8 | ORIGINAL EQUIP & FURNISHING | 2019-09-19 | 2019-12-17 | 2022-10-22 | 2023-01-19
20201123 | QUEENS | 042 | CITY UNIVERSITY | CA052-017 | Flushing Immigration Center | 9 | SUBSTANTIAL COMPLETION | 2019-12-18 | 2020-02-15 | 2023-01-20 | 2023-03-20
20201123 | QUEENS | 042 | CITY UNIVERSITY | CA052-017 | Flushing Immigration Center | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-02-16 | 2020-03-16 | 2023-03-21 | 2026-05-03
20201123 | QUEENS | 042 | CITY UNIVERSITY | CA055QB17 | CUNY ASAP Expansion | 1 | DEVELOP SCOPE | 2019-06-30 | 2019-09-27 | 2020-07-01 | 2020-09-28
20201123 | QUEENS | 042 | CITY UNIVERSITY | CA055QB17 | CUNY ASAP Expansion | 2 | PRELIMINARY DESIGN | 2019-09-28 | 2020-01-25 | 2020-09-29 | 2021-01-26
20201123 | QUEENS | 042 | CITY UNIVERSITY | CA055QB17 | CUNY ASAP Expansion | 3 | FINAL DESIGN | 2020-01-26 | 2020-07-23 | 2021-01-27 | 2021-07-25
20201123 | QUEENS | 042 | CITY UNIVERSITY | CA055QB17 | CUNY ASAP Expansion | 4 | BID AWARD AND REGISTER CONTRCT | 2020-07-24 | 2020-10-21 | 2021-07-26 | 2021-10-23
20201123 | QUEENS | 042 | CITY UNIVERSITY | CA055QB17 | CUNY ASAP Expansion | 5 | CONSTRUCTION TO 25% | 2020-10-22 | 2021-02-18 | 2021-10-24 | 2022-02-20
20201123 | QUEENS | 042 | CITY UNIVERSITY | CA055QB17 | CUNY ASAP Expansion | 6 | CONSTRUCTION TO 50% | 2021-02-19 | 2021-06-18 | 2022-02-21 | 2022-06-20
20201123 | QUEENS | 042 | CITY UNIVERSITY | CA055QB17 | CUNY ASAP Expansion | 7 | CONSTRUCTION TO 75% | 2021-06-19 | 2021-10-16 | 2022-06-21 | 2022-10-18
20201123 | QUEENS | 042 | CITY UNIVERSITY | CA055QB17 | CUNY ASAP Expansion | 8 | ORIGINAL EQUIP & FURNISHING | 2021-10-17 | 2022-01-14 | 2022-10-19 | 2023-01-16
20201123 | QUEENS | 042 | CITY UNIVERSITY | CA055QB17 | CUNY ASAP Expansion | 9 | SUBSTANTIAL COMPLETION | 2022-01-15 | 2022-03-15 | 2023-01-17 | 2023-03-17
20201123 | QUEENS | 042 | CITY UNIVERSITY | CA055QB17 | CUNY ASAP Expansion | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-16 | 2022-04-14 | 2023-03-18 | 2023-04-16
20201123 | QUEENS | 042 | CITY UNIVERSITY | CL018-015 | Trial Practice Room | 1 | DEVELOP SCOPE | 2015-03-01 | 2015-05-29 | 2015-03-01 | 2015-05-29
20201123 | QUEENS | 042 | CITY UNIVERSITY | CL018-015 | Trial Practice Room | 2 | PRELIMINARY DESIGN | 2015-05-30 | 2015-09-26 | 2015-05-30 | 2015-09-26
20201123 | QUEENS | 042 | CITY UNIVERSITY | CL018-015 | Trial Practice Room | 3 | FINAL DESIGN | 2015-09-27 | 2016-03-24 | 2015-09-27 | 2016-03-24
20201123 | QUEENS | 042 | CITY UNIVERSITY | CL018-015 | Trial Practice Room | 4 | BID AWARD AND REGISTER CONTRCT | 2016-03-25 | 2016-06-22 | 2016-03-25 | 2016-06-22
20201123 | QUEENS | 042 | CITY UNIVERSITY | CL018-015 | Trial Practice Room | 5 | CONSTRUCTION TO 25% | 2016-06-23 | 2016-10-20 | 2016-06-23 | 2016-10-20
20201123 | QUEENS | 042 | CITY UNIVERSITY | CL018-015 | Trial Practice Room | 6 | CONSTRUCTION TO 50% | 2016-10-21 | 2017-02-17 | 2016-10-21 | 2017-02-17
20201123 | QUEENS | 042 | CITY UNIVERSITY | CL018-015 | Trial Practice Room | 7 | CONSTRUCTION TO 75% | 2017-02-18 | 2017-06-17 | 2017-02-18 | 2017-06-17
20201123 | QUEENS | 042 | CITY UNIVERSITY | CL018-015 | Trial Practice Room | 8 | ORIGINAL EQUIP & FURNISHING | 2017-06-18 | 2017-09-15 | 2017-06-18 | 2017-09-15
20201123 | QUEENS | 042 | CITY UNIVERSITY | CL018-015 | Trial Practice Room | 9 | SUBSTANTIAL COMPLETION | 2017-09-16 | 2017-11-14 | 2017-09-16 | 2017-11-14
20201123 | QUEENS | 042 | CITY UNIVERSITY | CL018-015 | Trial Practice Room | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-11-15 | 2017-12-14 | 2017-11-15 | 2021-12-31
20201123 | QUEENS | 042 | CITY UNIVERSITY | CL021-018 | Renovation of Community Room | 1 | DEVELOP SCOPE | 2018-06-01 | 2018-08-29 | 2021-07-01 | 2021-10-01
20201123 | QUEENS | 042 | CITY UNIVERSITY | CL021-018 | Renovation of Community Room | 2 | PRELIMINARY DESIGN | 2018-08-30 | 2018-12-27 | 2021-10-02 | 2022-01-29
20201123 | QUEENS | 042 | CITY UNIVERSITY | CL021-018 | Renovation of Community Room | 3 | FINAL DESIGN | 2018-12-28 | 2019-06-25 | 2022-01-30 | 2022-07-28
20201123 | QUEENS | 042 | CITY UNIVERSITY | CL021-018 | Renovation of Community Room | 4 | BID AWARD AND REGISTER CONTRCT | 2019-06-26 | 2019-09-23 | 2022-07-29 | 2022-10-26
20201123 | QUEENS | 042 | CITY UNIVERSITY | CL021-018 | Renovation of Community Room | 5 | CONSTRUCTION TO 25% | 2019-09-24 | 2020-01-21 | 2022-10-27 | 2023-02-23
20201123 | QUEENS | 042 | CITY UNIVERSITY | CL021-018 | Renovation of Community Room | 6 | CONSTRUCTION TO 50% | 2020-01-22 | 2020-05-20 | 2023-02-24 | 2023-06-23
20201123 | QUEENS | 042 | CITY UNIVERSITY | CL021-018 | Renovation of Community Room | 7 | CONSTRUCTION TO 75% | 2020-05-21 | 2020-09-17 | 2023-06-24 | 2023-10-21
20201123 | QUEENS | 042 | CITY UNIVERSITY | CL021-018 | Renovation of Community Room | 8 | ORIGINAL EQUIP & FURNISHING | 2020-09-18 | 2020-12-16 | 2023-10-22 | 2024-01-19
20201123 | QUEENS | 042 | CITY UNIVERSITY | CL021-018 | Renovation of Community Room | 9 | SUBSTANTIAL COMPLETION | 2020-12-17 | 2021-02-14 | 2024-01-20 | 2024-03-19
20201123 | QUEENS | 042 | CITY UNIVERSITY | CL021-018 | Renovation of Community Room | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-02-15 | 2021-03-16 | 2024-03-20 | 2027-05-04
20201123 | QUEENS | 042 | CITY UNIVERSITY | CL023-019 | Worker Educational and Development Center | 1 | DEVELOP SCOPE | 2018-06-30 | 2018-09-27 | 2021-07-01 | 2021-10-01
20201123 | QUEENS | 042 | CITY UNIVERSITY | CL023-019 | Worker Educational and Development Center | 2 | PRELIMINARY DESIGN | 2018-09-28 | 2019-01-25 | 2021-10-02 | 2022-01-29
20201123 | QUEENS | 042 | CITY UNIVERSITY | CL023-019 | Worker Educational and Development Center | 3 | FINAL DESIGN | 2019-01-26 | 2019-07-24 | 2022-01-30 | 2022-07-28
20201123 | QUEENS | 042 | CITY UNIVERSITY | CL023-019 | Worker Educational and Development Center | 4 | BID AWARD AND REGISTER CONTRCT | 2019-07-25 | 2019-10-22 | 2022-07-29 | 2022-10-26
20201123 | QUEENS | 042 | CITY UNIVERSITY | CL023-019 | Worker Educational and Development Center | 5 | CONSTRUCTION TO 25% | 2019-10-23 | 2020-02-19 | 2022-10-27 | 2023-02-23
20201123 | QUEENS | 042 | CITY UNIVERSITY | CL023-019 | Worker Educational and Development Center | 6 | CONSTRUCTION TO 50% | 2020-02-20 | 2020-06-18 | 2023-02-24 | 2023-06-23
20201123 | QUEENS | 042 | CITY UNIVERSITY | CL023-019 | Worker Educational and Development Center | 7 | CONSTRUCTION TO 75% | 2020-06-19 | 2020-10-16 | 2023-06-24 | 2023-10-21
20201123 | QUEENS | 042 | CITY UNIVERSITY | CL023-019 | Worker Educational and Development Center | 8 | ORIGINAL EQUIP & FURNISHING | 2020-10-17 | 2021-01-14 | 2023-10-22 | 2024-01-19
20201123 | QUEENS | 042 | CITY UNIVERSITY | CL023-019 | Worker Educational and Development Center | 9 | SUBSTANTIAL COMPLETION | 2021-01-15 | 2021-03-15 | 2024-01-20 | 2024-03-19
20201123 | QUEENS | 042 | CITY UNIVERSITY | CL023-019 | Worker Educational and Development Center | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-16 | 2021-04-14 | 2024-03-20 | 2027-04-19
20201123 | QUEENS | 042 | CITY UNIVERSITY | CL024-019 | Data Center Fire Suppression System | 1 | DEVELOP SCOPE | 2019-06-30 | 2019-09-27 | 2019-06-30 | 2019-09-27
20201123 | QUEENS | 042 | CITY UNIVERSITY | CL024-019 | Data Center Fire Suppression System | 2 | PRELIMINARY DESIGN | 2019-09-28 | 2020-01-25 | 2019-09-28 | 2020-01-25
20201123 | QUEENS | 042 | CITY UNIVERSITY | CL024-019 | Data Center Fire Suppression System | 3 | FINAL DESIGN | 2020-01-26 | 2020-07-23 | 2020-01-26 | 2020-07-23
20201123 | QUEENS | 042 | CITY UNIVERSITY | CL024-019 | Data Center Fire Suppression System | 4 | BID AWARD AND REGISTER CONTRCT | 2020-07-24 | 2020-10-21 | 2020-07-24 | 2020-10-21
20201123 | QUEENS | 042 | CITY UNIVERSITY | CL024-019 | Data Center Fire Suppression System | 5 | CONSTRUCTION TO 25% | 2020-10-22 | 2021-02-18 | 2020-10-22 | 2021-02-18
20201123 | QUEENS | 042 | CITY UNIVERSITY | CL024-019 | Data Center Fire Suppression System | 6 | CONSTRUCTION TO 50% | 2021-02-19 | 2021-06-18 | 2021-02-19 | 2021-06-18
20201123 | QUEENS | 042 | CITY UNIVERSITY | CL024-019 | Data Center Fire Suppression System | 7 | CONSTRUCTION TO 75% | 2021-06-19 | 2021-10-16 | 2021-06-19 | 2021-10-16
20201123 | QUEENS | 042 | CITY UNIVERSITY | CL024-019 | Data Center Fire Suppression System | 8 | ORIGINAL EQUIP & FURNISHING | 2021-10-17 | 2022-01-14 | 2021-10-17 | 2022-01-14
20201123 | QUEENS | 042 | CITY UNIVERSITY | CL024-019 | Data Center Fire Suppression System | 9 | SUBSTANTIAL COMPLETION | 2022-01-15 | 2022-03-15 | 2022-01-15 | 2022-03-15
20201123 | QUEENS | 042 | CITY UNIVERSITY | CL024-019 | Data Center Fire Suppression System | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-16 | 2024-04-30 | 2022-03-16 | 2024-04-30
20201123 | QUEENS | 042 | CITY UNIVERSITY | KG037-015 | Science and Resilience Institute at Jamaica Bay | 1 | DEVELOP SCOPE | 2014-06-01 | 2014-08-29 | 2022-07-01 | 2022-09-29
20201123 | QUEENS | 042 | CITY UNIVERSITY | KG037-015 | Science and Resilience Institute at Jamaica Bay | 2 | PRELIMINARY DESIGN | 2014-08-30 | 2014-12-27 | 2022-09-30 | 2023-01-27
20201123 | QUEENS | 042 | CITY UNIVERSITY | KG037-015 | Science and Resilience Institute at Jamaica Bay | 3 | FINAL DESIGN | 2014-12-28 | 2015-06-25 | 2023-01-28 | 2023-07-26
20201123 | QUEENS | 042 | CITY UNIVERSITY | KG037-015 | Science and Resilience Institute at Jamaica Bay | 4 | BID AWARD AND REGISTER CONTRCT | 2015-06-26 | 2015-09-23 | 2023-07-27 | 2023-10-24
20201123 | QUEENS | 042 | CITY UNIVERSITY | KG037-015 | Science and Resilience Institute at Jamaica Bay | 5 | CONSTRUCTION TO 25% | 2015-09-24 | 2016-01-21 | 2023-10-25 | 2024-02-21
20201123 | QUEENS | 042 | CITY UNIVERSITY | KG037-015 | Science and Resilience Institute at Jamaica Bay | 6 | CONSTRUCTION TO 50% | 2016-01-22 | 2016-05-20 | 2024-02-22 | 2024-06-20
20201123 | QUEENS | 042 | CITY UNIVERSITY | KG037-015 | Science and Resilience Institute at Jamaica Bay | 7 | CONSTRUCTION TO 75% | 2016-05-21 | 2016-09-17 | 2024-06-21 | 2024-10-18
20201123 | QUEENS | 042 | CITY UNIVERSITY | KG037-015 | Science and Resilience Institute at Jamaica Bay | 8 | ORIGINAL EQUIP & FURNISHING | 2016-09-18 | 2016-12-16 | 2024-10-19 | 2025-01-16
20201123 | QUEENS | 042 | CITY UNIVERSITY | KG037-015 | Science and Resilience Institute at Jamaica Bay | 9 | SUBSTANTIAL COMPLETION | 2016-12-17 | 2017-02-14 | 2025-01-17 | 2025-03-17
20201123 | QUEENS | 042 | CITY UNIVERSITY | KG037-015 | Science and Resilience Institute at Jamaica Bay | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-02-15 | 2017-03-16 | 2025-03-18 | 2025-07-16
20201123 | QUEENS | 042 | CITY UNIVERSITY | LAGUARDIA | LaGuardia Community College Streetscape | 1 | DEVELOP SCOPE | 2007-03-01 | 2007-05-29 | 2007-03-01 | 2007-05-29
20201123 | QUEENS | 042 | CITY UNIVERSITY | LAGUARDIA | LaGuardia Community College Streetscape | 2 | PRELIMINARY DESIGN | 2007-05-30 | 2007-09-26 | 2007-05-30 | 2007-09-26
20201123 | QUEENS | 042 | CITY UNIVERSITY | LAGUARDIA | LaGuardia Community College Streetscape | 3 | FINAL DESIGN | 2007-09-27 | 2008-03-24 | 2007-09-27 | 2008-03-24
20201123 | QUEENS | 042 | CITY UNIVERSITY | LAGUARDIA | LaGuardia Community College Streetscape | 4 | BID AWARD AND REGISTER CONTRCT | 2008-03-25 | 2008-06-22 | 2008-03-25 | 2008-06-22
20201123 | QUEENS | 042 | CITY UNIVERSITY | LAGUARDIA | LaGuardia Community College Streetscape | 5 | CONSTRUCTION TO 25% | 2008-06-23 | 2008-10-20 | 2008-06-23 | 2008-10-20
20201123 | QUEENS | 042 | CITY UNIVERSITY | LAGUARDIA | LaGuardia Community College Streetscape | 6 | CONSTRUCTION TO 50% | 2008-10-21 | 2009-02-17 | 2008-10-21 | 2009-02-17
20201123 | QUEENS | 042 | CITY UNIVERSITY | LAGUARDIA | LaGuardia Community College Streetscape | 7 | CONSTRUCTION TO 75% | 2009-02-18 | 2009-06-17 | 2009-02-18 | 2009-06-17
20201123 | QUEENS | 042 | CITY UNIVERSITY | LAGUARDIA | LaGuardia Community College Streetscape | 8 | ORIGINAL EQUIP & FURNISHING | 2009-06-18 | 2009-09-15 | 2009-06-18 | 2009-09-15
20201123 | QUEENS | 042 | CITY UNIVERSITY | LAGUARDIA | LaGuardia Community College Streetscape | 9 | SUBSTANTIAL COMPLETION | 2009-09-16 | 2009-11-14 | 2009-09-16 | 2009-11-14
20201123 | QUEENS | 042 | CITY UNIVERSITY | LAGUARDIA | LaGuardia Community College Streetscape | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2009-11-15 | 2009-12-14 | 2009-11-15 | 2023-11-30
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG001-021 | IT Network Infrastucture Replacements | 1 | DEVELOP SCOPE | 2021-06-30 | 2021-09-27 | 2021-06-30 | 2021-09-27
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG001-021 | IT Network Infrastucture Replacements | 2 | PRELIMINARY DESIGN | 2021-09-28 | 2022-01-25 | 2021-09-28 | 2022-01-25
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG001-021 | IT Network Infrastucture Replacements | 3 | FINAL DESIGN | 2022-01-26 | 2022-07-24 | 2022-01-26 | 2022-07-24
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG001-021 | IT Network Infrastucture Replacements | 4 | BID AWARD AND REGISTER CONTRCT | 2022-07-25 | 2022-10-22 | 2022-07-25 | 2022-10-22
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG001-021 | IT Network Infrastucture Replacements | 5 | CONSTRUCTION TO 25% | 2022-10-23 | 2023-02-19 | 2022-10-23 | 2023-02-19
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG001-021 | IT Network Infrastucture Replacements | 6 | CONSTRUCTION TO 50% | 2023-02-20 | 2023-06-19 | 2023-02-20 | 2023-06-19
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG001-021 | IT Network Infrastucture Replacements | 7 | CONSTRUCTION TO 75% | 2023-06-20 | 2023-10-17 | 2023-06-20 | 2023-10-17
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG001-021 | IT Network Infrastucture Replacements | 8 | ORIGINAL EQUIP & FURNISHING | 2023-10-18 | 2024-01-15 | 2023-10-18 | 2024-01-15
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG001-021 | IT Network Infrastucture Replacements | 9 | SUBSTANTIAL COMPLETION | 2024-01-16 | 2024-03-15 | 2024-01-16 | 2024-03-15
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG001-021 | IT Network Infrastucture Replacements | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-03-16 | 2024-04-14 | 2024-03-16 | 2024-04-14
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG002-021 | Greenhouse Construction | 1 | DEVELOP SCOPE | 2021-06-30 | 2021-09-27 | 2021-06-30 | 2021-09-27
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG002-021 | Greenhouse Construction | 2 | PRELIMINARY DESIGN | 2021-09-28 | 2022-01-25 | 2021-09-28 | 2022-01-25
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG002-021 | Greenhouse Construction | 3 | FINAL DESIGN | 2022-01-26 | 2022-07-24 | 2022-01-26 | 2022-07-24
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG002-021 | Greenhouse Construction | 4 | BID AWARD AND REGISTER CONTRCT | 2022-07-25 | 2022-10-22 | 2022-07-25 | 2022-10-22
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG002-021 | Greenhouse Construction | 5 | CONSTRUCTION TO 25% | 2022-10-23 | 2023-02-19 | 2022-10-23 | 2023-02-19
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG002-021 | Greenhouse Construction | 6 | CONSTRUCTION TO 50% | 2023-02-20 | 2023-06-19 | 2023-02-20 | 2023-06-19
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG002-021 | Greenhouse Construction | 7 | CONSTRUCTION TO 75% | 2023-06-20 | 2023-10-17 | 2023-06-20 | 2023-10-17
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG002-021 | Greenhouse Construction | 8 | ORIGINAL EQUIP & FURNISHING | 2023-10-18 | 2024-01-15 | 2023-10-18 | 2024-01-15
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG002-021 | Greenhouse Construction | 9 | SUBSTANTIAL COMPLETION | 2024-01-16 | 2024-03-15 | 2024-01-16 | 2024-03-15
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG002-021 | Greenhouse Construction | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-03-16 | 2024-04-14 | 2024-03-16 | 2024-04-14
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG020-009 | NEW LIBRARY SPACE | 1 | DEVELOP SCOPE | 2009-06-01 | 2009-08-29 | 2009-06-01 | 2009-08-29
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG020-009 | NEW LIBRARY SPACE | 2 | PRELIMINARY DESIGN | 2009-08-30 | 2009-12-27 | 2009-08-30 | 2009-12-27
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG020-009 | NEW LIBRARY SPACE | 3 | FINAL DESIGN | 2009-12-28 | 2010-06-25 | 2009-12-28 | 2010-06-25
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG020-009 | NEW LIBRARY SPACE | 4 | BID AWARD AND REGISTER CONTRCT | 2010-06-26 | 2010-09-23 | 2010-06-26 | 2010-09-23
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG020-009 | NEW LIBRARY SPACE | 5 | CONSTRUCTION TO 25% | 2010-09-24 | 2011-01-21 | 2010-09-24 | 2011-01-21
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG020-009 | NEW LIBRARY SPACE | 6 | CONSTRUCTION TO 50% | 2011-01-22 | 2011-05-21 | 2011-01-22 | 2011-05-21
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG020-009 | NEW LIBRARY SPACE | 7 | CONSTRUCTION TO 75% | 2011-05-22 | 2011-09-18 | 2011-05-22 | 2011-09-18
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG020-009 | NEW LIBRARY SPACE | 8 | ORIGINAL EQUIP & FURNISHING | 2011-09-19 | 2011-12-17 | 2011-09-19 | 2011-12-17
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG020-009 | NEW LIBRARY SPACE | 9 | SUBSTANTIAL COMPLETION | 2011-12-18 | 2012-02-15 | 2011-12-18 | 2012-02-15
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG020-009 | NEW LIBRARY SPACE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-02-16 | 2012-03-16 | 2012-02-16 | 2025-12-30
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG024-009 | ADA UPGRADES | 2 | PRELIMINARY DESIGN | 2010-08-30 | 2010-12-27 | 2010-08-30 | 2010-12-27
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG024-009 | ADA UPGRADES | 3 | FINAL DESIGN | 2010-12-28 | 2011-06-25 | 2010-12-28 | 2011-06-25
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG024-009 | ADA UPGRADES | 4 | BID AWARD AND REGISTER CONTRCT | 2011-06-26 | 2011-09-23 | 2011-06-26 | 2011-09-23
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG024-009 | ADA UPGRADES | 5 | CONSTRUCTION TO 25% | 2011-09-24 | 2012-01-21 | 2011-09-24 | 2012-01-21
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG024-009 | ADA UPGRADES | 6 | CONSTRUCTION TO 50% | 2012-01-22 | 2012-05-20 | 2012-01-22 | 2012-05-20
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG024-009 | ADA UPGRADES | 7 | CONSTRUCTION TO 75% | 2012-05-21 | 2012-09-17 | 2012-05-21 | 2012-09-17
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG024-009 | ADA UPGRADES | 8 | ORIGINAL EQUIP & FURNISHING | 2012-09-18 | 2012-12-16 | 2012-09-18 | 2012-12-16
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG024-009 | ADA UPGRADES | 9 | SUBSTANTIAL COMPLETION | 2012-12-17 | 2013-02-14 | 2012-12-17 | 2013-02-14
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG024-009 | ADA UPGRADES | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-02-15 | 2013-03-16 | 2013-02-15 | 2013-03-16
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG036-014 | Library Expansion and HVAC Upgrade | 1 | DEVELOP SCOPE | 2014-06-01 | 2014-08-29 | 2020-07-01 | 2020-09-29
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG036-014 | Library Expansion and HVAC Upgrade | 2 | PRELIMINARY DESIGN | 2014-08-30 | 2014-12-27 | 2020-09-30 | 2021-01-27
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG036-014 | Library Expansion and HVAC Upgrade | 3 | FINAL DESIGN | 2014-12-28 | 2015-06-25 | 2021-01-28 | 2021-07-26
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG036-014 | Library Expansion and HVAC Upgrade | 4 | BID AWARD AND REGISTER CONTRCT | 2015-06-26 | 2015-09-23 | 2021-07-27 | 2021-10-24
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG036-014 | Library Expansion and HVAC Upgrade | 5 | CONSTRUCTION TO 25% | 2015-09-24 | 2016-01-21 | 2021-10-25 | 2022-02-21
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG036-014 | Library Expansion and HVAC Upgrade | 6 | CONSTRUCTION TO 50% | 2016-01-22 | 2016-05-20 | 2022-02-22 | 2022-06-21
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG036-014 | Library Expansion and HVAC Upgrade | 7 | CONSTRUCTION TO 75% | 2016-05-21 | 2016-09-17 | 2022-06-22 | 2022-10-19
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG036-014 | Library Expansion and HVAC Upgrade | 8 | ORIGINAL EQUIP & FURNISHING | 2016-09-18 | 2016-12-16 | 2022-10-20 | 2023-01-17
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG036-014 | Library Expansion and HVAC Upgrade | 9 | SUBSTANTIAL COMPLETION | 2016-12-17 | 2017-02-14 | 2023-01-18 | 2023-03-18
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG036-014 | Library Expansion and HVAC Upgrade | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-02-15 | 2017-03-16 | 2023-03-19 | 2023-07-17
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG040-016 | Center 3 Infrastr. Upgrade, Fitout | 1 | DEVELOP SCOPE | 2016-06-30 | 2016-09-27 | 2016-06-30 | 2016-09-27
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG040-016 | Center 3 Infrastr. Upgrade, Fitout | 2 | PRELIMINARY DESIGN | 2016-09-28 | 2017-01-25 | 2016-09-28 | 2017-01-25
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG040-016 | Center 3 Infrastr. Upgrade, Fitout | 3 | FINAL DESIGN | 2017-01-26 | 2017-07-24 | 2017-01-26 | 2017-07-24
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG040-016 | Center 3 Infrastr. Upgrade, Fitout | 4 | BID AWARD AND REGISTER CONTRCT | 2017-07-25 | 2017-10-22 | 2017-07-25 | 2017-10-22
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG040-016 | Center 3 Infrastr. Upgrade, Fitout | 5 | CONSTRUCTION TO 25% | 2017-10-23 | 2018-02-19 | 2017-10-23 | 2018-02-19
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG040-016 | Center 3 Infrastr. Upgrade, Fitout | 6 | CONSTRUCTION TO 50% | 2018-02-20 | 2018-06-19 | 2018-02-20 | 2018-06-19
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG040-016 | Center 3 Infrastr. Upgrade, Fitout | 7 | CONSTRUCTION TO 75% | 2018-06-20 | 2018-10-17 | 2018-06-20 | 2018-10-17
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG040-016 | Center 3 Infrastr. Upgrade, Fitout | 8 | ORIGINAL EQUIP & FURNISHING | 2018-10-18 | 2019-01-15 | 2018-10-18 | 2019-01-15
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG040-016 | Center 3 Infrastr. Upgrade, Fitout | 9 | SUBSTANTIAL COMPLETION | 2019-01-16 | 2019-03-16 | 2019-01-16 | 2019-03-16
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG040-016 | Center 3 Infrastr. Upgrade, Fitout | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-03-17 | 2019-04-15 | 2019-03-17 | 2027-04-30
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG041-016 | Business and Entrepreneurial Training Center | 1 | DEVELOP SCOPE | 2016-06-30 | 2016-09-27 | 2020-07-01 | 2020-09-28
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG041-016 | Business and Entrepreneurial Training Center | 2 | PRELIMINARY DESIGN | 2016-09-28 | 2017-01-25 | 2020-09-29 | 2021-01-26
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG041-016 | Business and Entrepreneurial Training Center | 3 | FINAL DESIGN | 2017-01-26 | 2017-07-24 | 2021-01-27 | 2021-07-25
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG041-016 | Business and Entrepreneurial Training Center | 4 | BID AWARD AND REGISTER CONTRCT | 2017-07-25 | 2017-10-22 | 2021-07-26 | 2021-10-23
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG041-016 | Business and Entrepreneurial Training Center | 5 | CONSTRUCTION TO 25% | 2017-10-23 | 2018-02-19 | 2021-10-24 | 2022-02-20
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG041-016 | Business and Entrepreneurial Training Center | 6 | CONSTRUCTION TO 50% | 2018-02-20 | 2018-06-19 | 2022-02-21 | 2022-06-20
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG041-016 | Business and Entrepreneurial Training Center | 7 | CONSTRUCTION TO 75% | 2018-06-20 | 2018-10-17 | 2022-06-21 | 2022-10-18
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG041-016 | Business and Entrepreneurial Training Center | 8 | ORIGINAL EQUIP & FURNISHING | 2018-10-18 | 2019-01-15 | 2022-10-19 | 2023-01-16
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG041-016 | Business and Entrepreneurial Training Center | 9 | SUBSTANTIAL COMPLETION | 2019-01-16 | 2019-03-16 | 2023-01-17 | 2023-03-17
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG041-016 | Business and Entrepreneurial Training Center | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-03-17 | 2019-04-15 | 2023-03-18 | 2023-07-15
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG043-018 | Shenker Hall Lab Renovation | 1 | DEVELOP SCOPE | 2018-06-01 | 2018-08-29 | 2019-06-30 | 2020-09-28
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG043-018 | Shenker Hall Lab Renovation | 2 | PRELIMINARY DESIGN | 2018-08-30 | 2018-12-27 | 2020-09-29 | 2021-01-26
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG043-018 | Shenker Hall Lab Renovation | 3 | FINAL DESIGN | 2018-12-28 | 2019-06-25 | 2021-01-27 | 2021-07-25
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG043-018 | Shenker Hall Lab Renovation | 4 | BID AWARD AND REGISTER CONTRCT | 2019-06-26 | 2019-09-23 | 2021-07-26 | 2021-10-23
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG043-018 | Shenker Hall Lab Renovation | 5 | CONSTRUCTION TO 25% | 2019-09-24 | 2020-01-21 | 2021-10-24 | 2022-02-20
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG043-018 | Shenker Hall Lab Renovation | 6 | CONSTRUCTION TO 50% | 2020-01-22 | 2020-05-20 | 2022-02-21 | 2022-06-20
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG043-018 | Shenker Hall Lab Renovation | 7 | CONSTRUCTION TO 75% | 2020-05-21 | 2020-09-17 | 2022-06-21 | 2022-10-18
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG043-018 | Shenker Hall Lab Renovation | 8 | ORIGINAL EQUIP & FURNISHING | 2020-09-18 | 2020-12-16 | 2022-10-19 | 2023-01-16
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG043-018 | Shenker Hall Lab Renovation | 9 | SUBSTANTIAL COMPLETION | 2020-12-17 | 2021-02-14 | 2023-01-17 | 2023-03-17
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG043-018 | Shenker Hall Lab Renovation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-02-15 | 2021-03-16 | 2023-03-18 | 2023-04-16
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG071-019 | Student Success Center: Tutoring Hub | 1 | DEVELOP SCOPE | 2018-06-30 | 2018-09-27 | 2020-07-01 | 2020-09-28
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG071-019 | Student Success Center: Tutoring Hub | 2 | PRELIMINARY DESIGN | 2018-09-28 | 2019-01-25 | 2020-09-29 | 2021-01-26
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG071-019 | Student Success Center: Tutoring Hub | 3 | FINAL DESIGN | 2019-01-26 | 2019-07-24 | 2021-01-27 | 2021-07-25
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG071-019 | Student Success Center: Tutoring Hub | 4 | BID AWARD AND REGISTER CONTRCT | 2019-07-25 | 2019-10-22 | 2021-07-26 | 2021-10-23
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG071-019 | Student Success Center: Tutoring Hub | 5 | CONSTRUCTION TO 25% | 2019-10-23 | 2020-02-19 | 2021-10-24 | 2022-02-20
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG071-019 | Student Success Center: Tutoring Hub | 6 | CONSTRUCTION TO 50% | 2020-02-20 | 2020-06-18 | 2022-02-21 | 2022-06-20
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG071-019 | Student Success Center: Tutoring Hub | 7 | CONSTRUCTION TO 75% | 2020-06-19 | 2020-10-16 | 2022-06-21 | 2022-10-18
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG071-019 | Student Success Center: Tutoring Hub | 8 | ORIGINAL EQUIP & FURNISHING | 2020-10-17 | 2021-01-14 | 2022-10-19 | 2023-01-16
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG071-019 | Student Success Center: Tutoring Hub | 9 | SUBSTANTIAL COMPLETION | 2021-01-15 | 2021-03-15 | 2023-01-17 | 2023-03-17
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG071-019 | Student Success Center: Tutoring Hub | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-16 | 2021-04-14 | 2023-03-18 | 2023-04-16
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG072-019 | Archive Construction | 1 | DEVELOP SCOPE | 2019-06-30 | 2019-09-27 | 2019-07-01 | 2019-09-28
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG072-019 | Archive Construction | 2 | PRELIMINARY DESIGN | 2019-09-28 | 2020-01-25 | 2019-09-29 | 2020-01-26
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG072-019 | Archive Construction | 3 | FINAL DESIGN | 2020-01-26 | 2020-07-23 | 2020-01-27 | 2020-07-24
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG072-019 | Archive Construction | 4 | BID AWARD AND REGISTER CONTRCT | 2020-07-24 | 2020-10-21 | 2020-07-25 | 2020-10-22
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG072-019 | Archive Construction | 5 | CONSTRUCTION TO 25% | 2020-10-22 | 2021-02-18 | 2020-10-23 | 2021-02-19
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG072-019 | Archive Construction | 6 | CONSTRUCTION TO 50% | 2021-02-19 | 2021-06-18 | 2021-02-20 | 2021-06-19
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG072-019 | Archive Construction | 7 | CONSTRUCTION TO 75% | 2021-06-19 | 2021-10-16 | 2021-06-20 | 2021-10-17
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG072-019 | Archive Construction | 8 | ORIGINAL EQUIP & FURNISHING | 2021-10-17 | 2022-01-14 | 2021-10-18 | 2022-01-15
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG072-019 | Archive Construction | 9 | SUBSTANTIAL COMPLETION | 2022-01-15 | 2022-03-15 | 2022-01-16 | 2022-03-16
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG072-019 | Archive Construction | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-16 | 2022-04-14 | 2022-03-17 | 2026-04-30
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG073-020 | LIBRARY PHASE II CONSTRUCTION | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-09-28 | 2019-07-01 | 2019-09-28
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG073-020 | LIBRARY PHASE II CONSTRUCTION | 2 | PRELIMINARY DESIGN | 2019-09-29 | 2020-01-26 | 2019-09-29 | 2020-01-26
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG073-020 | LIBRARY PHASE II CONSTRUCTION | 3 | FINAL DESIGN | 2020-01-27 | 2020-07-24 | 2020-01-27 | 2020-07-24
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG073-020 | LIBRARY PHASE II CONSTRUCTION | 4 | BID AWARD AND REGISTER CONTRCT | 2020-07-25 | 2020-10-22 | 2020-07-25 | 2020-10-22
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG073-020 | LIBRARY PHASE II CONSTRUCTION | 5 | CONSTRUCTION TO 25% | 2020-10-23 | 2021-02-19 | 2020-10-23 | 2021-02-19
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG073-020 | LIBRARY PHASE II CONSTRUCTION | 6 | CONSTRUCTION TO 50% | 2021-02-20 | 2021-06-19 | 2021-02-20 | 2021-06-19
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG073-020 | LIBRARY PHASE II CONSTRUCTION | 7 | CONSTRUCTION TO 75% | 2021-06-20 | 2021-10-17 | 2021-06-20 | 2021-10-17
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG073-020 | LIBRARY PHASE II CONSTRUCTION | 8 | ORIGINAL EQUIP & FURNISHING | 2021-10-18 | 2022-01-15 | 2021-10-18 | 2022-01-15
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG073-020 | LIBRARY PHASE II CONSTRUCTION | 9 | SUBSTANTIAL COMPLETION | 2022-01-16 | 2022-03-16 | 2022-01-16 | 2022-03-16
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG073-020 | LIBRARY PHASE II CONSTRUCTION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-17 | 2022-04-15 | 2022-03-17 | 2022-04-15
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG202-006 | Center 3 - 8th Floor and Infrastructure | 1 | DEVELOP SCOPE | 2007-01-14 | 2007-04-13 | 2007-01-14 | 2007-04-13
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG202-006 | Center 3 - 8th Floor and Infrastructure | 2 | PRELIMINARY DESIGN | 2007-04-14 | 2007-08-11 | 2007-04-14 | 2007-08-11
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG202-006 | Center 3 - 8th Floor and Infrastructure | 3 | FINAL DESIGN | 2007-08-12 | 2008-02-07 | 2007-08-12 | 2008-02-07
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG202-006 | Center 3 - 8th Floor and Infrastructure | 4 | BID AWARD AND REGISTER CONTRCT | 2008-02-08 | 2008-05-07 | 2008-02-08 | 2008-05-07
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG202-006 | Center 3 - 8th Floor and Infrastructure | 5 | CONSTRUCTION TO 25% | 2008-05-08 | 2008-09-04 | 2008-05-08 | 2008-09-04
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG202-006 | Center 3 - 8th Floor and Infrastructure | 6 | CONSTRUCTION TO 50% | 2008-09-05 | 2009-01-02 | 2008-09-05 | 2009-01-02
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG202-006 | Center 3 - 8th Floor and Infrastructure | 7 | CONSTRUCTION TO 75% | 2009-01-03 | 2009-05-02 | 2009-01-03 | 2009-05-02
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG202-006 | Center 3 - 8th Floor and Infrastructure | 8 | ORIGINAL EQUIP & FURNISHING | 2009-05-03 | 2009-07-31 | 2009-05-03 | 2009-07-31
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG202-006 | Center 3 - 8th Floor and Infrastructure | 9 | SUBSTANTIAL COMPLETION | 2009-08-01 | 2009-09-29 | 2009-08-01 | 2009-09-29
20201123 | QUEENS | 042 | CITY UNIVERSITY | LG202-006 | Center 3 - 8th Floor and Infrastructure | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2009-09-30 | 2009-10-29 | 2009-09-30 | 2024-06-30
20201123 | QUEENS | 042 | CITY UNIVERSITY | QB001-021 | ADA Restroom Upgrades | 1 | DEVELOP SCOPE | 2021-06-30 | 2021-09-27 | 2021-06-30 | 2021-09-27
20201123 | QUEENS | 042 | CITY UNIVERSITY | QB001-021 | ADA Restroom Upgrades | 2 | PRELIMINARY DESIGN | 2021-09-28 | 2022-01-25 | 2021-09-28 | 2022-01-25
20201123 | QUEENS | 042 | CITY UNIVERSITY | QB001-021 | ADA Restroom Upgrades | 3 | FINAL DESIGN | 2022-01-26 | 2022-07-24 | 2022-01-26 | 2022-07-24
20201123 | QUEENS | 042 | CITY UNIVERSITY | QB001-021 | ADA Restroom Upgrades | 4 | BID AWARD AND REGISTER CONTRCT | 2022-07-25 | 2022-10-22 | 2022-07-25 | 2022-10-22
20201123 | QUEENS | 042 | CITY UNIVERSITY | QB001-021 | ADA Restroom Upgrades | 5 | CONSTRUCTION TO 25% | 2022-10-23 | 2023-02-19 | 2022-10-23 | 2023-02-19
20201123 | QUEENS | 042 | CITY UNIVERSITY | QB001-021 | ADA Restroom Upgrades | 6 | CONSTRUCTION TO 50% | 2023-02-20 | 2023-06-19 | 2023-02-20 | 2023-06-19
20201123 | QUEENS | 042 | CITY UNIVERSITY | QB001-021 | ADA Restroom Upgrades | 7 | CONSTRUCTION TO 75% | 2023-06-20 | 2023-10-17 | 2023-06-20 | 2023-10-17
20201123 | QUEENS | 042 | CITY UNIVERSITY | QB001-021 | ADA Restroom Upgrades | 8 | ORIGINAL EQUIP & FURNISHING | 2023-10-18 | 2024-01-15 | 2023-10-18 | 2024-01-15
20201123 | QUEENS | 042 | CITY UNIVERSITY | QB001-021 | ADA Restroom Upgrades | 9 | SUBSTANTIAL COMPLETION | 2024-01-16 | 2024-03-15 | 2024-01-16 | 2024-03-15
20201123 | QUEENS | 042 | CITY UNIVERSITY | QB001-021 | ADA Restroom Upgrades | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-03-16 | 2024-04-14 | 2024-03-16 | 2024-04-14
20201123 | QUEENS | 042 | CITY UNIVERSITY | QB002-010 | Queensborough CC- Bathrooms/Campus Improvements | 1 | DEVELOP SCOPE | 2010-06-01 | 2010-08-29 | 2010-06-01 | 2010-08-29
20201123 | QUEENS | 042 | CITY UNIVERSITY | QB002-010 | Queensborough CC- Bathrooms/Campus Improvements | 2 | PRELIMINARY DESIGN | 2010-08-30 | 2010-12-27 | 2010-08-30 | 2010-12-27
20201123 | QUEENS | 042 | CITY UNIVERSITY | QB002-010 | Queensborough CC- Bathrooms/Campus Improvements | 3 | FINAL DESIGN | 2010-12-28 | 2011-06-25 | 2010-12-28 | 2011-06-25
20201123 | QUEENS | 042 | CITY UNIVERSITY | QB002-010 | Queensborough CC- Bathrooms/Campus Improvements | 4 | BID AWARD AND REGISTER CONTRCT | 2011-06-26 | 2011-09-23 | 2011-06-26 | 2011-09-23
20201123 | QUEENS | 042 | CITY UNIVERSITY | QB002-010 | Queensborough CC- Bathrooms/Campus Improvements | 5 | CONSTRUCTION TO 25% | 2011-09-24 | 2012-01-21 | 2011-09-24 | 2012-01-21
20201123 | QUEENS | 042 | CITY UNIVERSITY | QB002-010 | Queensborough CC- Bathrooms/Campus Improvements | 6 | CONSTRUCTION TO 50% | 2012-01-22 | 2012-05-20 | 2012-01-22 | 2012-05-20
20201123 | QUEENS | 042 | CITY UNIVERSITY | QB002-010 | Queensborough CC- Bathrooms/Campus Improvements | 7 | CONSTRUCTION TO 75% | 2012-05-21 | 2012-09-17 | 2012-05-21 | 2012-09-17
20201123 | QUEENS | 042 | CITY UNIVERSITY | QB002-010 | Queensborough CC- Bathrooms/Campus Improvements | 8 | ORIGINAL EQUIP & FURNISHING | 2012-09-18 | 2012-12-16 | 2012-09-18 | 2012-12-16
20201123 | QUEENS | 042 | CITY UNIVERSITY | QB002-010 | Queensborough CC- Bathrooms/Campus Improvements | 9 | SUBSTANTIAL COMPLETION | 2012-12-17 | 2013-02-14 | 2012-12-17 | 2013-02-14
20201123 | QUEENS | 042 | CITY UNIVERSITY | QB002-010 | Queensborough CC- Bathrooms/Campus Improvements | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-02-15 | 2013-03-16 | 2013-02-15 | 2021-06-30
20201123 | QUEENS | 042 | CITY UNIVERSITY | QB045-013 | Replace Three Roofs & Renovate Campus Theater | 1 | DEVELOP SCOPE | 2013-06-01 | 2013-08-29 | 2021-07-01 | 2021-09-28
20201123 | QUEENS | 042 | CITY UNIVERSITY | QB045-013 | Replace Three Roofs & Renovate Campus Theater | 2 | PRELIMINARY DESIGN | 2013-08-30 | 2013-12-27 | 2021-09-29 | 2022-01-26
20201123 | QUEENS | 042 | CITY UNIVERSITY | QB045-013 | Replace Three Roofs & Renovate Campus Theater | 3 | FINAL DESIGN | 2013-12-28 | 2014-06-25 | 2022-01-27 | 2022-07-25
20201123 | QUEENS | 042 | CITY UNIVERSITY | QB045-013 | Replace Three Roofs & Renovate Campus Theater | 4 | BID AWARD AND REGISTER CONTRCT | 2014-06-26 | 2014-09-23 | 2022-07-26 | 2022-10-23
20201123 | QUEENS | 042 | CITY UNIVERSITY | QB045-013 | Replace Three Roofs & Renovate Campus Theater | 5 | CONSTRUCTION TO 25% | 2014-09-24 | 2015-01-21 | 2022-10-24 | 2023-02-20
20201123 | QUEENS | 042 | CITY UNIVERSITY | QB045-013 | Replace Three Roofs & Renovate Campus Theater | 6 | CONSTRUCTION TO 50% | 2015-01-22 | 2015-05-21 | 2023-02-21 | 2023-06-20
20201123 | QUEENS | 042 | CITY UNIVERSITY | QB045-013 | Replace Three Roofs & Renovate Campus Theater | 7 | CONSTRUCTION TO 75% | 2015-05-22 | 2015-09-18 | 2023-06-21 | 2023-10-18
20201123 | QUEENS | 042 | CITY UNIVERSITY | QB045-013 | Replace Three Roofs & Renovate Campus Theater | 8 | ORIGINAL EQUIP & FURNISHING | 2015-09-19 | 2015-12-17 | 2023-10-19 | 2024-01-16
20201123 | QUEENS | 042 | CITY UNIVERSITY | QB045-013 | Replace Three Roofs & Renovate Campus Theater | 9 | SUBSTANTIAL COMPLETION | 2015-12-18 | 2016-02-15 | 2024-01-17 | 2024-03-16
20201123 | QUEENS | 042 | CITY UNIVERSITY | QB045-013 | Replace Three Roofs & Renovate Campus Theater | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-02-16 | 2016-03-16 | 2024-03-17 | 2024-04-16
20201123 | QUEENS | 042 | CITY UNIVERSITY | QB054-016 | Refurbishment and Upgrade of Research Labs | 1 | DEVELOP SCOPE | 2016-06-30 | 2016-09-27 | 2016-06-30 | 2016-09-27
20201123 | QUEENS | 042 | CITY UNIVERSITY | QB054-016 | Refurbishment and Upgrade of Research Labs | 2 | PRELIMINARY DESIGN | 2016-09-28 | 2017-01-25 | 2016-09-28 | 2017-01-25
20201123 | QUEENS | 042 | CITY UNIVERSITY | QB054-016 | Refurbishment and Upgrade of Research Labs | 3 | FINAL DESIGN | 2017-01-26 | 2017-07-24 | 2017-01-26 | 2017-07-24
20201123 | QUEENS | 042 | CITY UNIVERSITY | QB054-016 | Refurbishment and Upgrade of Research Labs | 4 | BID AWARD AND REGISTER CONTRCT | 2017-07-25 | 2017-10-22 | 2017-07-25 | 2017-10-22
20201123 | QUEENS | 042 | CITY UNIVERSITY | QB054-016 | Refurbishment and Upgrade of Research Labs | 5 | CONSTRUCTION TO 25% | 2017-10-23 | 2018-02-19 | 2017-10-23 | 2018-02-19
20201123 | QUEENS | 042 | CITY UNIVERSITY | QB054-016 | Refurbishment and Upgrade of Research Labs | 6 | CONSTRUCTION TO 50% | 2018-02-20 | 2018-06-19 | 2018-02-20 | 2018-06-19
20201123 | QUEENS | 042 | CITY UNIVERSITY | QB054-016 | Refurbishment and Upgrade of Research Labs | 7 | CONSTRUCTION TO 75% | 2018-06-20 | 2018-10-17 | 2018-06-20 | 2018-10-17
20201123 | QUEENS | 042 | CITY UNIVERSITY | QB054-016 | Refurbishment and Upgrade of Research Labs | 8 | ORIGINAL EQUIP & FURNISHING | 2018-10-18 | 2019-01-15 | 2018-10-18 | 2019-01-15
20201123 | QUEENS | 042 | CITY UNIVERSITY | QB054-016 | Refurbishment and Upgrade of Research Labs | 9 | SUBSTANTIAL COMPLETION | 2019-01-16 | 2019-03-16 | 2019-01-16 | 2019-03-16
20201123 | QUEENS | 042 | CITY UNIVERSITY | QB054-016 | Refurbishment and Upgrade of Research Labs | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-03-17 | 2019-04-15 | 2019-03-17 | 2022-04-30
20201123 | QUEENS | 042 | CITY UNIVERSITY | QB062-020 | RFK Gymnasium Ventilation and Air Conditioning | 1 | DEVELOP SCOPE | 2020-06-30 | 2020-09-27 | 2020-06-30 | 2020-09-27
20201123 | QUEENS | 042 | CITY UNIVERSITY | QB062-020 | RFK Gymnasium Ventilation and Air Conditioning | 2 | PRELIMINARY DESIGN | 2020-09-28 | 2021-01-25 | 2020-09-28 | 2021-01-25
20201123 | QUEENS | 042 | CITY UNIVERSITY | QB062-020 | RFK Gymnasium Ventilation and Air Conditioning | 3 | FINAL DESIGN | 2021-01-26 | 2021-07-24 | 2021-01-26 | 2021-07-24
20201123 | QUEENS | 042 | CITY UNIVERSITY | QB062-020 | RFK Gymnasium Ventilation and Air Conditioning | 4 | BID AWARD AND REGISTER CONTRCT | 2021-07-25 | 2021-10-22 | 2021-07-25 | 2021-10-22
20201123 | QUEENS | 042 | CITY UNIVERSITY | QB062-020 | RFK Gymnasium Ventilation and Air Conditioning | 5 | CONSTRUCTION TO 25% | 2021-10-23 | 2022-02-19 | 2021-10-23 | 2022-02-19
20201123 | QUEENS | 042 | CITY UNIVERSITY | QB062-020 | RFK Gymnasium Ventilation and Air Conditioning | 6 | CONSTRUCTION TO 50% | 2022-02-20 | 2022-06-19 | 2022-02-20 | 2022-06-19
20201123 | QUEENS | 042 | CITY UNIVERSITY | QB062-020 | RFK Gymnasium Ventilation and Air Conditioning | 7 | CONSTRUCTION TO 75% | 2022-06-20 | 2022-10-17 | 2022-06-20 | 2022-10-17
20201123 | QUEENS | 042 | CITY UNIVERSITY | QB062-020 | RFK Gymnasium Ventilation and Air Conditioning | 8 | ORIGINAL EQUIP & FURNISHING | 2022-10-18 | 2023-01-15 | 2022-10-18 | 2023-01-15
20201123 | QUEENS | 042 | CITY UNIVERSITY | QB062-020 | RFK Gymnasium Ventilation and Air Conditioning | 9 | SUBSTANTIAL COMPLETION | 2023-01-16 | 2023-03-16 | 2023-01-16 | 2023-03-16
20201123 | QUEENS | 042 | CITY UNIVERSITY | QB062-020 | RFK Gymnasium Ventilation and Air Conditioning | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-03-17 | 2023-04-15 | 2023-03-17 | 2027-04-30
20201123 | QUEENS | 042 | CITY UNIVERSITY | QB063-020 | Theater Upgrades (PHASE II) | 1 | DEVELOP SCOPE | 2020-06-30 | 2020-09-27 | 2020-06-30 | 2020-09-27
20201123 | QUEENS | 042 | CITY UNIVERSITY | QB063-020 | Theater Upgrades (PHASE II) | 2 | PRELIMINARY DESIGN | 2020-09-28 | 2021-01-25 | 2020-09-28 | 2021-01-25
20201123 | QUEENS | 042 | CITY UNIVERSITY | QB063-020 | Theater Upgrades (PHASE II) | 3 | FINAL DESIGN | 2021-01-26 | 2021-07-24 | 2021-01-26 | 2021-07-24
20201123 | QUEENS | 042 | CITY UNIVERSITY | QB063-020 | Theater Upgrades (PHASE II) | 4 | BID AWARD AND REGISTER CONTRCT | 2021-07-25 | 2021-10-22 | 2021-07-25 | 2021-10-22
20201123 | QUEENS | 042 | CITY UNIVERSITY | QB063-020 | Theater Upgrades (PHASE II) | 5 | CONSTRUCTION TO 25% | 2021-10-23 | 2022-02-19 | 2021-10-23 | 2022-02-19
20201123 | QUEENS | 042 | CITY UNIVERSITY | QB063-020 | Theater Upgrades (PHASE II) | 6 | CONSTRUCTION TO 50% | 2022-02-20 | 2022-06-19 | 2022-02-20 | 2022-06-19
20201123 | QUEENS | 042 | CITY UNIVERSITY | QB063-020 | Theater Upgrades (PHASE II) | 7 | CONSTRUCTION TO 75% | 2022-06-20 | 2022-10-17 | 2022-06-20 | 2022-10-17
20201123 | QUEENS | 042 | CITY UNIVERSITY | QB063-020 | Theater Upgrades (PHASE II) | 8 | ORIGINAL EQUIP & FURNISHING | 2022-10-18 | 2023-01-15 | 2022-10-18 | 2023-01-15
20201123 | QUEENS | 042 | CITY UNIVERSITY | QB063-020 | Theater Upgrades (PHASE II) | 9 | SUBSTANTIAL COMPLETION | 2023-01-16 | 2023-03-16 | 2023-01-16 | 2023-03-16
20201123 | QUEENS | 042 | CITY UNIVERSITY | QB063-020 | Theater Upgrades (PHASE II) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-03-17 | 2023-04-15 | 2023-03-17 | 2023-04-15
20201123 | QUEENS | 042 | CITY UNIVERSITY | QB200-006 | Upgrade Electric System | 1 | DEVELOP SCOPE | 2007-01-14 | 2007-04-13 | 2007-01-14 | 2007-04-13
20201123 | QUEENS | 042 | CITY UNIVERSITY | QB200-006 | Upgrade Electric System | 2 | PRELIMINARY DESIGN | 2007-04-14 | 2007-08-11 | 2007-04-14 | 2007-08-11
20201123 | QUEENS | 042 | CITY UNIVERSITY | QB200-006 | Upgrade Electric System | 3 | FINAL DESIGN | 2007-08-12 | 2008-02-07 | 2007-08-12 | 2008-02-07
20201123 | QUEENS | 042 | CITY UNIVERSITY | QB200-006 | Upgrade Electric System | 4 | BID AWARD AND REGISTER CONTRCT | 2008-02-08 | 2008-05-07 | 2008-02-08 | 2008-05-07
20201123 | QUEENS | 042 | CITY UNIVERSITY | QB200-006 | Upgrade Electric System | 5 | CONSTRUCTION TO 25% | 2008-05-08 | 2008-09-04 | 2008-05-08 | 2008-09-04
20201123 | QUEENS | 042 | CITY UNIVERSITY | QB200-006 | Upgrade Electric System | 6 | CONSTRUCTION TO 50% | 2008-09-05 | 2009-01-02 | 2008-09-05 | 2009-01-02
20201123 | QUEENS | 042 | CITY UNIVERSITY | QB200-006 | Upgrade Electric System | 7 | CONSTRUCTION TO 75% | 2009-01-03 | 2009-05-02 | 2009-01-03 | 2009-05-02
20201123 | QUEENS | 042 | CITY UNIVERSITY | QB200-006 | Upgrade Electric System | 8 | ORIGINAL EQUIP & FURNISHING | 2009-05-03 | 2009-07-31 | 2009-05-03 | 2009-07-31
20201123 | QUEENS | 042 | CITY UNIVERSITY | QB200-006 | Upgrade Electric System | 9 | SUBSTANTIAL COMPLETION | 2009-08-01 | 2009-09-29 | 2009-08-01 | 2009-09-29
20201123 | QUEENS | 042 | CITY UNIVERSITY | QB200-006 | Upgrade Electric System | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2009-09-30 | 2009-10-29 | 2009-09-30 | 2023-12-31
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC001-021 | Renovate and Upgrade Lab Spaces | 1 | DEVELOP SCOPE | 2021-06-30 | 2021-09-27 | 2021-06-30 | 2021-09-27
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC001-021 | Renovate and Upgrade Lab Spaces | 2 | PRELIMINARY DESIGN | 2021-09-28 | 2022-01-25 | 2021-09-28 | 2022-01-25
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC001-021 | Renovate and Upgrade Lab Spaces | 3 | FINAL DESIGN | 2022-01-26 | 2022-07-24 | 2022-01-26 | 2022-07-24
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC001-021 | Renovate and Upgrade Lab Spaces | 4 | BID AWARD AND REGISTER CONTRCT | 2022-07-25 | 2022-10-22 | 2022-07-25 | 2022-10-22
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC001-021 | Renovate and Upgrade Lab Spaces | 5 | CONSTRUCTION TO 25% | 2022-10-23 | 2023-02-19 | 2022-10-23 | 2023-02-19
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC001-021 | Renovate and Upgrade Lab Spaces | 6 | CONSTRUCTION TO 50% | 2023-02-20 | 2023-06-19 | 2023-02-20 | 2023-06-19
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC001-021 | Renovate and Upgrade Lab Spaces | 7 | CONSTRUCTION TO 75% | 2023-06-20 | 2023-10-17 | 2023-06-20 | 2023-10-17
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC001-021 | Renovate and Upgrade Lab Spaces | 8 | ORIGINAL EQUIP & FURNISHING | 2023-10-18 | 2024-01-15 | 2023-10-18 | 2024-01-15
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC001-021 | Renovate and Upgrade Lab Spaces | 9 | SUBSTANTIAL COMPLETION | 2024-01-16 | 2024-03-15 | 2024-01-16 | 2024-03-15
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC001-021 | Renovate and Upgrade Lab Spaces | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-03-16 | 2024-04-14 | 2024-03-16 | 2024-04-14
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC004-013 | Library and Classroom Space Upgrades | 1 | DEVELOP SCOPE | 2013-06-01 | 2013-08-29 | 2021-07-01 | 2021-09-28
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC004-013 | Library and Classroom Space Upgrades | 2 | PRELIMINARY DESIGN | 2013-08-30 | 2013-12-27 | 2021-09-29 | 2022-01-26
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC004-013 | Library and Classroom Space Upgrades | 3 | FINAL DESIGN | 2013-12-28 | 2014-06-25 | 2022-01-27 | 2022-07-25
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC004-013 | Library and Classroom Space Upgrades | 4 | BID AWARD AND REGISTER CONTRCT | 2014-06-26 | 2014-09-23 | 2022-07-26 | 2022-10-23
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC004-013 | Library and Classroom Space Upgrades | 5 | CONSTRUCTION TO 25% | 2014-09-24 | 2015-01-21 | 2022-10-24 | 2023-02-20
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC004-013 | Library and Classroom Space Upgrades | 6 | CONSTRUCTION TO 50% | 2015-01-22 | 2015-05-21 | 2023-02-21 | 2023-06-20
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC004-013 | Library and Classroom Space Upgrades | 7 | CONSTRUCTION TO 75% | 2015-05-22 | 2015-09-18 | 2023-06-21 | 2023-10-18
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC004-013 | Library and Classroom Space Upgrades | 8 | ORIGINAL EQUIP & FURNISHING | 2015-09-19 | 2015-12-17 | 2023-10-19 | 2024-01-16
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC004-013 | Library and Classroom Space Upgrades | 9 | SUBSTANTIAL COMPLETION | 2015-12-18 | 2016-02-15 | 2024-01-17 | 2024-03-16
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC004-013 | Library and Classroom Space Upgrades | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-02-16 | 2016-03-16 | 2024-03-17 | 2024-04-15
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC014-012 | DESIGN AND IMPLEMENTATION OF PHASE 3 - RENOV OF LIBR SPACE | 2 | PRELIMINARY DESIGN | 2012-08-30 | 2012-12-27 | 2012-08-30 | 2012-12-27
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC014-012 | DESIGN AND IMPLEMENTATION OF PHASE 3 - RENOV OF LIBR SPACE | 3 | FINAL DESIGN | 2012-12-28 | 2013-06-25 | 2012-12-28 | 2013-06-25
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC014-012 | DESIGN AND IMPLEMENTATION OF PHASE 3 - RENOV OF LIBR SPACE | 4 | BID AWARD AND REGISTER CONTRCT | 2013-06-26 | 2013-09-23 | 2013-06-26 | 2013-09-23
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC014-012 | DESIGN AND IMPLEMENTATION OF PHASE 3 - RENOV OF LIBR SPACE | 5 | CONSTRUCTION TO 25% | 2013-09-24 | 2014-01-21 | 2013-09-24 | 2014-01-21
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC014-012 | DESIGN AND IMPLEMENTATION OF PHASE 3 - RENOV OF LIBR SPACE | 6 | CONSTRUCTION TO 50% | 2014-01-22 | 2014-05-21 | 2014-01-22 | 2014-05-21
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC014-012 | DESIGN AND IMPLEMENTATION OF PHASE 3 - RENOV OF LIBR SPACE | 7 | CONSTRUCTION TO 75% | 2014-05-22 | 2014-09-18 | 2014-05-22 | 2014-09-18
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC014-012 | DESIGN AND IMPLEMENTATION OF PHASE 3 - RENOV OF LIBR SPACE | 8 | ORIGINAL EQUIP & FURNISHING | 2014-09-19 | 2014-12-17 | 2014-09-19 | 2014-12-17
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC014-012 | DESIGN AND IMPLEMENTATION OF PHASE 3 - RENOV OF LIBR SPACE | 9 | SUBSTANTIAL COMPLETION | 2014-12-18 | 2015-02-15 | 2014-12-18 | 2015-02-15
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC014-012 | DESIGN AND IMPLEMENTATION OF PHASE 3 - RENOV OF LIBR SPACE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-02-16 | 2015-03-17 | 2015-02-16 | 2015-03-17
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC039-011 | Louis Armstrong Visitor's Center | 1 | DEVELOP SCOPE | 2011-06-01 | 2011-08-29 | 2011-06-01 | 2011-08-29
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC039-011 | Louis Armstrong Visitor's Center | 2 | PRELIMINARY DESIGN | 2011-08-30 | 2011-12-27 | 2011-08-30 | 2011-12-27
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC039-011 | Louis Armstrong Visitor's Center | 3 | FINAL DESIGN | 2011-12-28 | 2012-06-24 | 2011-12-28 | 2012-06-24
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC039-011 | Louis Armstrong Visitor's Center | 4 | BID AWARD AND REGISTER CONTRCT | 2012-06-25 | 2012-09-22 | 2012-06-25 | 2012-09-22
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC039-011 | Louis Armstrong Visitor's Center | 5 | CONSTRUCTION TO 25% | 2012-09-23 | 2013-01-20 | 2012-09-23 | 2013-01-20
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC039-011 | Louis Armstrong Visitor's Center | 6 | CONSTRUCTION TO 50% | 2013-01-21 | 2013-05-20 | 2013-01-21 | 2013-05-20
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC039-011 | Louis Armstrong Visitor's Center | 7 | CONSTRUCTION TO 75% | 2013-05-21 | 2013-09-17 | 2013-05-21 | 2013-09-17
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC039-011 | Louis Armstrong Visitor's Center | 8 | ORIGINAL EQUIP & FURNISHING | 2013-09-18 | 2013-12-16 | 2013-09-18 | 2013-12-16
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC039-011 | Louis Armstrong Visitor's Center | 9 | SUBSTANTIAL COMPLETION | 2013-12-17 | 2014-02-14 | 2013-12-17 | 2014-02-14
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC039-011 | Louis Armstrong Visitor's Center | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-02-15 | 2014-03-16 | 2014-02-15 | 2024-12-31
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC047-013 | Kupferberg Renovation | 1 | DEVELOP SCOPE | 2013-06-01 | 2013-08-29 | 2022-07-01 | 2022-09-28
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC047-013 | Kupferberg Renovation | 2 | PRELIMINARY DESIGN | 2013-08-30 | 2013-12-27 | 2022-09-29 | 2023-01-26
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC047-013 | Kupferberg Renovation | 3 | FINAL DESIGN | 2013-12-28 | 2014-06-25 | 2023-01-27 | 2023-07-25
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC047-013 | Kupferberg Renovation | 4 | BID AWARD AND REGISTER CONTRCT | 2014-06-26 | 2014-09-23 | 2023-07-26 | 2023-10-23
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC047-013 | Kupferberg Renovation | 5 | CONSTRUCTION TO 25% | 2014-09-24 | 2015-01-21 | 2023-10-24 | 2024-02-20
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC047-013 | Kupferberg Renovation | 6 | CONSTRUCTION TO 50% | 2015-01-22 | 2015-05-21 | 2024-02-21 | 2024-06-19
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC047-013 | Kupferberg Renovation | 7 | CONSTRUCTION TO 75% | 2015-05-22 | 2015-09-18 | 2024-06-20 | 2024-10-17
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC047-013 | Kupferberg Renovation | 8 | ORIGINAL EQUIP & FURNISHING | 2015-09-19 | 2015-12-17 | 2024-10-18 | 2025-01-15
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC047-013 | Kupferberg Renovation | 9 | SUBSTANTIAL COMPLETION | 2015-12-18 | 2016-02-15 | 2025-01-16 | 2025-03-16
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC047-013 | Kupferberg Renovation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-02-16 | 2016-03-16 | 2025-03-17 | 2025-04-15
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC051-014 | Perimeter Fencing | 2 | PRELIMINARY DESIGN | 2014-08-30 | 2014-12-27 | 2014-08-30 | 2014-12-27
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC051-014 | Perimeter Fencing | 3 | FINAL DESIGN | 2014-12-28 | 2015-06-25 | 2014-12-28 | 2015-06-25
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC051-014 | Perimeter Fencing | 4 | BID AWARD AND REGISTER CONTRCT | 2015-06-26 | 2015-09-23 | 2015-06-26 | 2015-09-23
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC051-014 | Perimeter Fencing | 5 | CONSTRUCTION TO 25% | 2015-09-24 | 2016-01-21 | 2015-09-24 | 2016-01-21
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC051-014 | Perimeter Fencing | 6 | CONSTRUCTION TO 50% | 2016-01-22 | 2016-05-20 | 2016-01-22 | 2016-05-20
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC051-014 | Perimeter Fencing | 7 | CONSTRUCTION TO 75% | 2016-05-21 | 2016-09-17 | 2016-05-21 | 2016-09-17
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC051-014 | Perimeter Fencing | 8 | ORIGINAL EQUIP & FURNISHING | 2016-09-18 | 2016-12-16 | 2016-09-18 | 2016-12-16
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC051-014 | Perimeter Fencing | 9 | SUBSTANTIAL COMPLETION | 2016-12-17 | 2017-02-14 | 2016-12-17 | 2017-02-14
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC051-014 | Perimeter Fencing | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-02-15 | 2017-03-16 | 2017-02-15 | 2020-03-30
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC054-015 | Speech & Hearing Center Upgrade Ph 2 | 1 | DEVELOP SCOPE | 2015-03-01 | 2015-05-29 | 2015-03-01 | 2015-05-29
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC054-015 | Speech & Hearing Center Upgrade Ph 2 | 2 | PRELIMINARY DESIGN | 2015-05-30 | 2015-09-26 | 2015-05-30 | 2015-09-26
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC054-015 | Speech & Hearing Center Upgrade Ph 2 | 3 | FINAL DESIGN | 2015-09-27 | 2016-03-24 | 2015-09-27 | 2016-03-24
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC054-015 | Speech & Hearing Center Upgrade Ph 2 | 4 | BID AWARD AND REGISTER CONTRCT | 2016-03-25 | 2016-06-22 | 2016-03-25 | 2016-06-22
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC054-015 | Speech & Hearing Center Upgrade Ph 2 | 5 | CONSTRUCTION TO 25% | 2016-06-23 | 2016-10-20 | 2016-06-23 | 2016-10-20
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC054-015 | Speech & Hearing Center Upgrade Ph 2 | 6 | CONSTRUCTION TO 50% | 2016-10-21 | 2017-02-17 | 2016-10-21 | 2017-02-17
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC054-015 | Speech & Hearing Center Upgrade Ph 2 | 7 | CONSTRUCTION TO 75% | 2017-02-18 | 2017-06-17 | 2017-02-18 | 2017-06-17
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC054-015 | Speech & Hearing Center Upgrade Ph 2 | 8 | ORIGINAL EQUIP & FURNISHING | 2017-06-18 | 2017-09-15 | 2017-06-18 | 2017-09-15
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC054-015 | Speech & Hearing Center Upgrade Ph 2 | 9 | SUBSTANTIAL COMPLETION | 2017-09-16 | 2017-11-14 | 2017-09-16 | 2017-11-14
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC054-015 | Speech & Hearing Center Upgrade Ph 2 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-11-15 | 2017-12-14 | 2017-11-15 | 2022-12-31
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC061-016 | One Stop Service Center | 1 | DEVELOP SCOPE | 2016-06-30 | 2016-09-27 | 2021-07-01 | 2021-09-28
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC061-016 | One Stop Service Center | 2 | PRELIMINARY DESIGN | 2016-09-28 | 2017-01-25 | 2021-09-29 | 2022-01-26
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC061-016 | One Stop Service Center | 3 | FINAL DESIGN | 2017-01-26 | 2017-07-24 | 2022-01-27 | 2022-07-25
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC061-016 | One Stop Service Center | 4 | BID AWARD AND REGISTER CONTRCT | 2017-07-25 | 2017-10-22 | 2022-07-26 | 2022-10-23
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC061-016 | One Stop Service Center | 5 | CONSTRUCTION TO 25% | 2017-10-23 | 2018-02-19 | 2022-10-24 | 2023-02-20
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC061-016 | One Stop Service Center | 6 | CONSTRUCTION TO 50% | 2018-02-20 | 2018-06-19 | 2023-02-21 | 2023-06-20
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC061-016 | One Stop Service Center | 7 | CONSTRUCTION TO 75% | 2018-06-20 | 2018-10-17 | 2023-06-21 | 2023-10-18
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC061-016 | One Stop Service Center | 8 | ORIGINAL EQUIP & FURNISHING | 2018-10-18 | 2019-01-15 | 2023-10-19 | 2024-01-16
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC061-016 | One Stop Service Center | 9 | SUBSTANTIAL COMPLETION | 2019-01-16 | 2019-03-16 | 2024-01-17 | 2024-03-16
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC061-016 | One Stop Service Center | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-03-17 | 2019-04-15 | 2024-03-17 | 2024-04-16
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC061-017 | One Stop Center | 1 | DEVELOP SCOPE | 2017-06-01 | 2017-08-29 | 2021-07-01 | 2021-09-28
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC061-017 | One Stop Center | 2 | PRELIMINARY DESIGN | 2017-08-30 | 2017-12-27 | 2021-09-29 | 2022-01-26
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC061-017 | One Stop Center | 3 | FINAL DESIGN | 2017-12-28 | 2018-06-25 | 2022-01-27 | 2022-07-25
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC061-017 | One Stop Center | 4 | BID AWARD AND REGISTER CONTRCT | 2018-06-26 | 2018-09-23 | 2022-07-26 | 2022-10-23
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC061-017 | One Stop Center | 5 | CONSTRUCTION TO 25% | 2018-09-24 | 2019-01-21 | 2022-10-24 | 2023-02-20
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC061-017 | One Stop Center | 6 | CONSTRUCTION TO 50% | 2019-01-22 | 2019-05-21 | 2023-02-21 | 2023-06-20
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC061-017 | One Stop Center | 7 | CONSTRUCTION TO 75% | 2019-05-22 | 2019-09-18 | 2023-06-21 | 2023-10-18
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC061-017 | One Stop Center | 8 | ORIGINAL EQUIP & FURNISHING | 2019-09-19 | 2019-12-17 | 2023-10-19 | 2024-01-16
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC061-017 | One Stop Center | 9 | SUBSTANTIAL COMPLETION | 2019-12-18 | 2020-02-15 | 2024-01-17 | 2024-03-16
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC061-017 | One Stop Center | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-02-16 | 2020-03-16 | 2024-03-17 | 2024-04-15
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC065-017 | Recording Studio Renovation in the Music Bldg | 1 | DEVELOP SCOPE | 2017-06-01 | 2017-08-29 | 2017-06-01 | 2017-08-29
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC065-017 | Recording Studio Renovation in the Music Bldg | 2 | PRELIMINARY DESIGN | 2017-08-30 | 2017-12-27 | 2017-08-30 | 2017-12-27
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC065-017 | Recording Studio Renovation in the Music Bldg | 3 | FINAL DESIGN | 2017-12-28 | 2018-06-25 | 2017-12-28 | 2018-06-25
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC065-017 | Recording Studio Renovation in the Music Bldg | 4 | BID AWARD AND REGISTER CONTRCT | 2018-06-26 | 2018-09-23 | 2018-06-26 | 2018-09-23
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC065-017 | Recording Studio Renovation in the Music Bldg | 5 | CONSTRUCTION TO 25% | 2018-09-24 | 2019-01-21 | 2018-09-24 | 2019-01-21
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC065-017 | Recording Studio Renovation in the Music Bldg | 6 | CONSTRUCTION TO 50% | 2019-01-22 | 2019-05-21 | 2019-01-22 | 2019-05-21
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC065-017 | Recording Studio Renovation in the Music Bldg | 7 | CONSTRUCTION TO 75% | 2019-05-22 | 2019-09-18 | 2019-05-22 | 2019-09-18
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC065-017 | Recording Studio Renovation in the Music Bldg | 8 | ORIGINAL EQUIP & FURNISHING | 2019-09-19 | 2019-12-17 | 2019-09-19 | 2019-12-17
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC065-017 | Recording Studio Renovation in the Music Bldg | 9 | SUBSTANTIAL COMPLETION | 2019-12-18 | 2020-02-15 | 2019-12-18 | 2020-02-15
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC065-017 | Recording Studio Renovation in the Music Bldg | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-02-16 | 2020-03-16 | 2020-02-16 | 2026-03-31
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC066-017 | Digital Film Center Construction | 1 | DEVELOP SCOPE | 2017-06-01 | 2017-08-29 | 2017-06-01 | 2017-08-29
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC066-017 | Digital Film Center Construction | 2 | PRELIMINARY DESIGN | 2017-08-30 | 2017-12-27 | 2017-08-30 | 2017-12-27
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC066-017 | Digital Film Center Construction | 3 | FINAL DESIGN | 2017-12-28 | 2018-06-25 | 2017-12-28 | 2018-06-25
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC066-017 | Digital Film Center Construction | 4 | BID AWARD AND REGISTER CONTRCT | 2018-06-26 | 2018-09-23 | 2018-06-26 | 2018-09-23
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC066-017 | Digital Film Center Construction | 5 | CONSTRUCTION TO 25% | 2018-09-24 | 2019-01-21 | 2018-09-24 | 2019-01-21
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC066-017 | Digital Film Center Construction | 6 | CONSTRUCTION TO 50% | 2019-01-22 | 2019-05-21 | 2019-01-22 | 2019-05-21
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC066-017 | Digital Film Center Construction | 7 | CONSTRUCTION TO 75% | 2019-05-22 | 2019-09-18 | 2019-05-22 | 2019-09-18
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC066-017 | Digital Film Center Construction | 8 | ORIGINAL EQUIP & FURNISHING | 2019-09-19 | 2019-12-17 | 2019-09-19 | 2019-12-17
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC066-017 | Digital Film Center Construction | 9 | SUBSTANTIAL COMPLETION | 2019-12-18 | 2020-02-15 | 2019-12-18 | 2020-02-15
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC066-017 | Digital Film Center Construction | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-02-16 | 2020-03-16 | 2020-02-16 | 2027-03-31
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC069-018 | Library Phase III Upgrade | 1 | DEVELOP SCOPE | 2018-06-01 | 2018-08-29 | 2021-07-01 | 2021-09-28
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC069-018 | Library Phase III Upgrade | 2 | PRELIMINARY DESIGN | 2018-08-30 | 2018-12-27 | 2021-09-29 | 2022-01-26
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC069-018 | Library Phase III Upgrade | 3 | FINAL DESIGN | 2018-12-28 | 2019-06-25 | 2022-01-27 | 2022-07-25
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC069-018 | Library Phase III Upgrade | 4 | BID AWARD AND REGISTER CONTRCT | 2019-06-26 | 2019-09-23 | 2022-07-26 | 2022-10-23
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC069-018 | Library Phase III Upgrade | 5 | CONSTRUCTION TO 25% | 2019-09-24 | 2020-01-21 | 2022-10-24 | 2023-02-20
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC069-018 | Library Phase III Upgrade | 6 | CONSTRUCTION TO 50% | 2020-01-22 | 2020-05-20 | 2023-02-21 | 2023-06-20
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC069-018 | Library Phase III Upgrade | 7 | CONSTRUCTION TO 75% | 2020-05-21 | 2020-09-17 | 2023-06-21 | 2023-10-18
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC069-018 | Library Phase III Upgrade | 8 | ORIGINAL EQUIP & FURNISHING | 2020-09-18 | 2020-12-16 | 2023-10-19 | 2024-01-16
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC069-018 | Library Phase III Upgrade | 9 | SUBSTANTIAL COMPLETION | 2020-12-17 | 2021-02-14 | 2024-01-17 | 2024-03-16
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC069-018 | Library Phase III Upgrade | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-02-15 | 2021-03-16 | 2024-03-17 | 2024-04-15
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC070-018 | Psychology and Digital Photography Labs | 1 | DEVELOP SCOPE | 2018-06-01 | 2018-08-29 | 2021-07-01 | 2021-09-28
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC070-018 | Psychology and Digital Photography Labs | 2 | PRELIMINARY DESIGN | 2018-08-30 | 2018-12-27 | 2021-09-29 | 2022-01-26
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC070-018 | Psychology and Digital Photography Labs | 3 | FINAL DESIGN | 2018-12-28 | 2019-06-25 | 2022-01-27 | 2022-07-25
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC070-018 | Psychology and Digital Photography Labs | 4 | BID AWARD AND REGISTER CONTRCT | 2019-06-26 | 2019-09-23 | 2022-07-26 | 2022-10-23
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC070-018 | Psychology and Digital Photography Labs | 5 | CONSTRUCTION TO 25% | 2019-09-24 | 2020-01-21 | 2022-10-24 | 2023-02-20
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC070-018 | Psychology and Digital Photography Labs | 6 | CONSTRUCTION TO 50% | 2020-01-22 | 2020-05-20 | 2023-02-21 | 2023-06-20
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC070-018 | Psychology and Digital Photography Labs | 7 | CONSTRUCTION TO 75% | 2020-05-21 | 2020-09-17 | 2023-06-21 | 2023-10-18
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC070-018 | Psychology and Digital Photography Labs | 8 | ORIGINAL EQUIP & FURNISHING | 2020-09-18 | 2020-12-16 | 2023-10-19 | 2024-01-16
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC070-018 | Psychology and Digital Photography Labs | 9 | SUBSTANTIAL COMPLETION | 2020-12-17 | 2021-02-14 | 2024-01-17 | 2024-03-16
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC070-018 | Psychology and Digital Photography Labs | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-02-15 | 2021-03-16 | 2024-03-17 | 2027-04-30
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC072-019 | Renovation of Rathaus Hall Arts Center | 1 | DEVELOP SCOPE | 2018-06-30 | 2018-09-27 | 2021-07-01 | 2021-09-28
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC072-019 | Renovation of Rathaus Hall Arts Center | 2 | PRELIMINARY DESIGN | 2018-09-28 | 2019-01-25 | 2021-09-29 | 2022-01-26
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC072-019 | Renovation of Rathaus Hall Arts Center | 3 | FINAL DESIGN | 2019-01-26 | 2019-07-24 | 2022-01-27 | 2022-07-25
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC072-019 | Renovation of Rathaus Hall Arts Center | 4 | BID AWARD AND REGISTER CONTRCT | 2019-07-25 | 2019-10-22 | 2022-07-26 | 2022-10-23
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC072-019 | Renovation of Rathaus Hall Arts Center | 5 | CONSTRUCTION TO 25% | 2019-10-23 | 2020-02-19 | 2022-10-24 | 2023-02-20
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC072-019 | Renovation of Rathaus Hall Arts Center | 6 | CONSTRUCTION TO 50% | 2020-02-20 | 2020-06-18 | 2023-02-21 | 2023-06-20
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC072-019 | Renovation of Rathaus Hall Arts Center | 7 | CONSTRUCTION TO 75% | 2020-06-19 | 2020-10-16 | 2023-06-21 | 2023-10-18
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC072-019 | Renovation of Rathaus Hall Arts Center | 8 | ORIGINAL EQUIP & FURNISHING | 2020-10-17 | 2021-01-14 | 2023-10-19 | 2024-01-16
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC072-019 | Renovation of Rathaus Hall Arts Center | 9 | SUBSTANTIAL COMPLETION | 2021-01-15 | 2021-03-15 | 2024-01-17 | 2024-03-16
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC072-019 | Renovation of Rathaus Hall Arts Center | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-16 | 2021-04-14 | 2024-03-17 | 2027-04-30
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC074-019 | Biology Core Facility Upgrade | 1 | DEVELOP SCOPE | 2019-06-30 | 2019-09-27 | 2021-07-17 | 2021-10-14
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC074-019 | Biology Core Facility Upgrade | 2 | PRELIMINARY DESIGN | 2019-09-28 | 2020-01-25 | 2021-10-15 | 2022-02-11
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC074-019 | Biology Core Facility Upgrade | 3 | FINAL DESIGN | 2020-01-26 | 2020-07-23 | 2022-02-12 | 2022-08-10
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC074-019 | Biology Core Facility Upgrade | 4 | BID AWARD AND REGISTER CONTRCT | 2020-07-24 | 2020-10-21 | 2022-08-11 | 2022-11-08
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC074-019 | Biology Core Facility Upgrade | 5 | CONSTRUCTION TO 25% | 2020-10-22 | 2021-02-18 | 2022-11-09 | 2023-03-08
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC074-019 | Biology Core Facility Upgrade | 6 | CONSTRUCTION TO 50% | 2021-02-19 | 2021-06-18 | 2023-03-09 | 2023-07-06
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC074-019 | Biology Core Facility Upgrade | 7 | CONSTRUCTION TO 75% | 2021-06-19 | 2021-10-16 | 2023-07-07 | 2023-11-03
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC074-019 | Biology Core Facility Upgrade | 8 | ORIGINAL EQUIP & FURNISHING | 2021-10-17 | 2022-01-14 | 2023-11-04 | 2024-02-01
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC074-019 | Biology Core Facility Upgrade | 9 | SUBSTANTIAL COMPLETION | 2022-01-15 | 2022-03-15 | 2024-02-02 | 2024-04-01
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC074-019 | Biology Core Facility Upgrade | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-16 | 2023-04-30 | 2024-04-02 | 2024-05-01
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC075-020 | Colden Auditorium Renovation and Upgrades | 1 | DEVELOP SCOPE | 2021-07-01 | 2021-09-28 | 2021-07-01 | 2021-09-28
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC075-020 | Colden Auditorium Renovation and Upgrades | 2 | PRELIMINARY DESIGN | 2021-09-29 | 2022-01-26 | 2021-09-29 | 2022-01-26
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC075-020 | Colden Auditorium Renovation and Upgrades | 3 | FINAL DESIGN | 2022-01-27 | 2022-07-25 | 2022-01-27 | 2022-07-25
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC075-020 | Colden Auditorium Renovation and Upgrades | 4 | BID AWARD AND REGISTER CONTRCT | 2022-07-26 | 2022-10-23 | 2022-07-26 | 2022-10-23
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC075-020 | Colden Auditorium Renovation and Upgrades | 5 | CONSTRUCTION TO 25% | 2022-10-24 | 2023-02-20 | 2022-10-24 | 2023-02-20
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC075-020 | Colden Auditorium Renovation and Upgrades | 6 | CONSTRUCTION TO 50% | 2023-02-21 | 2023-06-20 | 2023-02-21 | 2023-06-20
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC075-020 | Colden Auditorium Renovation and Upgrades | 7 | CONSTRUCTION TO 75% | 2023-06-21 | 2023-10-18 | 2023-06-21 | 2023-10-18
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC075-020 | Colden Auditorium Renovation and Upgrades | 8 | ORIGINAL EQUIP & FURNISHING | 2023-10-19 | 2024-01-16 | 2023-10-19 | 2024-01-16
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC075-020 | Colden Auditorium Renovation and Upgrades | 9 | SUBSTANTIAL COMPLETION | 2024-01-17 | 2024-03-16 | 2024-01-17 | 2024-03-16
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC075-020 | Colden Auditorium Renovation and Upgrades | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-03-17 | 2024-04-15 | 2024-03-17 | 2027-04-30
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC076-020 | Air Pollution Laboratory-Commoner Center | 1 | DEVELOP SCOPE | 2020-06-30 | 2020-09-27 | 2020-06-30 | 2020-09-27
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC076-020 | Air Pollution Laboratory-Commoner Center | 2 | PRELIMINARY DESIGN | 2020-09-28 | 2021-01-25 | 2020-09-28 | 2021-01-25
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC076-020 | Air Pollution Laboratory-Commoner Center | 3 | FINAL DESIGN | 2021-01-26 | 2021-07-24 | 2021-01-26 | 2021-07-24
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC076-020 | Air Pollution Laboratory-Commoner Center | 4 | BID AWARD AND REGISTER CONTRCT | 2021-07-25 | 2021-10-22 | 2021-07-25 | 2021-10-22
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC076-020 | Air Pollution Laboratory-Commoner Center | 5 | CONSTRUCTION TO 25% | 2021-10-23 | 2022-02-19 | 2021-10-23 | 2022-02-19
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC076-020 | Air Pollution Laboratory-Commoner Center | 6 | CONSTRUCTION TO 50% | 2022-02-20 | 2022-06-19 | 2022-02-20 | 2022-06-19
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC076-020 | Air Pollution Laboratory-Commoner Center | 7 | CONSTRUCTION TO 75% | 2022-06-20 | 2022-10-17 | 2022-06-20 | 2022-10-17
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC076-020 | Air Pollution Laboratory-Commoner Center | 8 | ORIGINAL EQUIP & FURNISHING | 2022-10-18 | 2023-01-15 | 2022-10-18 | 2023-01-15
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC076-020 | Air Pollution Laboratory-Commoner Center | 9 | SUBSTANTIAL COMPLETION | 2023-01-16 | 2023-03-16 | 2023-01-16 | 2023-03-16
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC076-020 | Air Pollution Laboratory-Commoner Center | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-03-17 | 2023-04-15 | 2023-03-17 | 2023-04-15
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC077-020 | Remsen Hall Science Bldg Upgrades | 1 | DEVELOP SCOPE | 2020-07-01 | 2020-09-28 | 2020-07-01 | 2020-09-28
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC077-020 | Remsen Hall Science Bldg Upgrades | 2 | PRELIMINARY DESIGN | 2020-09-29 | 2021-01-26 | 2020-09-29 | 2021-01-26
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC077-020 | Remsen Hall Science Bldg Upgrades | 3 | FINAL DESIGN | 2021-01-27 | 2021-07-25 | 2021-01-27 | 2021-07-25
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC077-020 | Remsen Hall Science Bldg Upgrades | 4 | BID AWARD AND REGISTER CONTRCT | 2021-07-26 | 2021-10-23 | 2021-07-26 | 2021-10-23
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC077-020 | Remsen Hall Science Bldg Upgrades | 5 | CONSTRUCTION TO 25% | 2021-10-24 | 2022-02-20 | 2021-10-24 | 2022-02-20
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC077-020 | Remsen Hall Science Bldg Upgrades | 6 | CONSTRUCTION TO 50% | 2022-02-21 | 2022-06-20 | 2022-02-21 | 2022-06-20
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC077-020 | Remsen Hall Science Bldg Upgrades | 7 | CONSTRUCTION TO 75% | 2022-06-21 | 2022-10-18 | 2022-06-21 | 2022-10-18
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC077-020 | Remsen Hall Science Bldg Upgrades | 8 | ORIGINAL EQUIP & FURNISHING | 2022-10-19 | 2023-01-16 | 2022-10-19 | 2023-01-16
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC077-020 | Remsen Hall Science Bldg Upgrades | 9 | SUBSTANTIAL COMPLETION | 2023-01-17 | 2023-03-17 | 2023-01-17 | 2023-03-17
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC077-020 | Remsen Hall Science Bldg Upgrades | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-03-18 | 2023-04-16 | 2023-03-18 | 2027-06-30
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC078-020 | Construction of a Student Engagement and learning Ctr. | 1 | DEVELOP SCOPE | 2021-07-01 | 2021-09-29 | 2021-07-01 | 2021-09-29
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC078-020 | Construction of a Student Engagement and learning Ctr. | 2 | PRELIMINARY DESIGN | 2021-09-30 | 2022-01-27 | 2021-09-30 | 2022-01-27
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC078-020 | Construction of a Student Engagement and learning Ctr. | 3 | FINAL DESIGN | 2022-01-28 | 2022-07-26 | 2022-01-28 | 2022-07-26
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC078-020 | Construction of a Student Engagement and learning Ctr. | 4 | BID AWARD AND REGISTER CONTRCT | 2022-07-27 | 2022-10-24 | 2022-07-27 | 2022-10-24
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC078-020 | Construction of a Student Engagement and learning Ctr. | 5 | CONSTRUCTION TO 25% | 2022-10-25 | 2023-02-21 | 2022-10-25 | 2023-02-21
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC078-020 | Construction of a Student Engagement and learning Ctr. | 6 | CONSTRUCTION TO 50% | 2023-02-22 | 2023-06-21 | 2023-02-22 | 2023-06-21
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC078-020 | Construction of a Student Engagement and learning Ctr. | 7 | CONSTRUCTION TO 75% | 2023-06-22 | 2023-10-19 | 2023-06-22 | 2023-10-19
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC078-020 | Construction of a Student Engagement and learning Ctr. | 8 | ORIGINAL EQUIP & FURNISHING | 2023-10-20 | 2024-01-17 | 2023-10-20 | 2024-01-17
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC078-020 | Construction of a Student Engagement and learning Ctr. | 9 | SUBSTANTIAL COMPLETION | 2024-01-18 | 2024-03-17 | 2024-01-18 | 2024-03-17
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC078-020 | Construction of a Student Engagement and learning Ctr. | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-03-18 | 2024-04-16 | 2024-03-18 | 2024-04-16
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC079-020 | Louis Armstrong House - Theater Lighting and Sound Systems | 1 | DEVELOP SCOPE | 2020-06-30 | 2020-09-27 | 2020-06-30 | 2020-09-27
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC079-020 | Louis Armstrong House - Theater Lighting and Sound Systems | 2 | PRELIMINARY DESIGN | 2020-09-28 | 2021-01-25 | 2020-09-28 | 2021-01-25
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC079-020 | Louis Armstrong House - Theater Lighting and Sound Systems | 3 | FINAL DESIGN | 2021-01-26 | 2021-07-24 | 2021-01-26 | 2021-07-24
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC079-020 | Louis Armstrong House - Theater Lighting and Sound Systems | 4 | BID AWARD AND REGISTER CONTRCT | 2021-07-25 | 2021-10-22 | 2021-07-25 | 2021-10-22
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC079-020 | Louis Armstrong House - Theater Lighting and Sound Systems | 5 | CONSTRUCTION TO 25% | 2021-10-23 | 2022-02-19 | 2021-10-23 | 2022-02-19
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC079-020 | Louis Armstrong House - Theater Lighting and Sound Systems | 6 | CONSTRUCTION TO 50% | 2022-02-20 | 2022-06-19 | 2022-02-20 | 2022-06-19
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC079-020 | Louis Armstrong House - Theater Lighting and Sound Systems | 7 | CONSTRUCTION TO 75% | 2022-06-20 | 2022-10-17 | 2022-06-20 | 2022-10-17
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC079-020 | Louis Armstrong House - Theater Lighting and Sound Systems | 8 | ORIGINAL EQUIP & FURNISHING | 2022-10-18 | 2023-01-15 | 2022-10-18 | 2023-01-15
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC079-020 | Louis Armstrong House - Theater Lighting and Sound Systems | 9 | SUBSTANTIAL COMPLETION | 2023-01-16 | 2023-03-16 | 2023-01-16 | 2023-03-16
20201123 | QUEENS | 042 | CITY UNIVERSITY | QC079-020 | Louis Armstrong House - Theater Lighting and Sound Systems | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-03-17 | 2023-04-15 | 2023-03-17 | 2023-04-15
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC001-010 | YORK COLLEGE - DISABLED ACCESS UPGRADE | 1 | DEVELOP SCOPE | 2010-06-01 | 2010-08-29 | 2020-07-01 | 2020-09-28
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC001-010 | YORK COLLEGE - DISABLED ACCESS UPGRADE | 2 | PRELIMINARY DESIGN | 2010-08-30 | 2010-12-27 | 2020-09-29 | 2021-01-26
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC001-010 | YORK COLLEGE - DISABLED ACCESS UPGRADE | 3 | FINAL DESIGN | 2010-12-28 | 2011-06-25 | 2021-01-27 | 2021-07-25
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC001-010 | YORK COLLEGE - DISABLED ACCESS UPGRADE | 4 | BID AWARD AND REGISTER CONTRCT | 2011-06-26 | 2011-09-23 | 2021-07-26 | 2021-10-23
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC001-010 | YORK COLLEGE - DISABLED ACCESS UPGRADE | 5 | CONSTRUCTION TO 25% | 2011-09-24 | 2012-01-21 | 2021-10-24 | 2022-02-20
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC001-010 | YORK COLLEGE - DISABLED ACCESS UPGRADE | 6 | CONSTRUCTION TO 50% | 2012-01-22 | 2012-05-20 | 2022-02-21 | 2022-06-20
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC001-010 | YORK COLLEGE - DISABLED ACCESS UPGRADE | 7 | CONSTRUCTION TO 75% | 2012-05-21 | 2012-09-17 | 2022-06-21 | 2022-10-18
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC001-010 | YORK COLLEGE - DISABLED ACCESS UPGRADE | 8 | ORIGINAL EQUIP & FURNISHING | 2012-09-18 | 2012-12-16 | 2022-10-19 | 2023-01-16
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC001-010 | YORK COLLEGE - DISABLED ACCESS UPGRADE | 9 | SUBSTANTIAL COMPLETION | 2012-12-17 | 2013-02-14 | 2023-01-17 | 2023-03-17
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC001-010 | YORK COLLEGE - DISABLED ACCESS UPGRADE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-02-15 | 2013-03-16 | 2023-03-18 | 2023-04-16
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC001-021 | Track & Field Renovations | 1 | DEVELOP SCOPE | 2021-06-30 | 2021-09-27 | 2021-06-30 | 2021-09-27
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC001-021 | Track & Field Renovations | 2 | PRELIMINARY DESIGN | 2021-09-28 | 2022-01-25 | 2021-09-28 | 2022-01-25
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC001-021 | Track & Field Renovations | 3 | FINAL DESIGN | 2022-01-26 | 2022-07-24 | 2022-01-26 | 2022-07-24
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC001-021 | Track & Field Renovations | 4 | BID AWARD AND REGISTER CONTRCT | 2022-07-25 | 2022-10-22 | 2022-07-25 | 2022-10-22
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC001-021 | Track & Field Renovations | 5 | CONSTRUCTION TO 25% | 2022-10-23 | 2023-02-19 | 2022-10-23 | 2023-02-19
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC001-021 | Track & Field Renovations | 6 | CONSTRUCTION TO 50% | 2023-02-20 | 2023-06-19 | 2023-02-20 | 2023-06-19
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC001-021 | Track & Field Renovations | 7 | CONSTRUCTION TO 75% | 2023-06-20 | 2023-10-17 | 2023-06-20 | 2023-10-17
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC001-021 | Track & Field Renovations | 8 | ORIGINAL EQUIP & FURNISHING | 2023-10-18 | 2024-01-15 | 2023-10-18 | 2024-01-15
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC001-021 | Track & Field Renovations | 9 | SUBSTANTIAL COMPLETION | 2024-01-16 | 2024-03-15 | 2024-01-16 | 2024-03-15
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC001-021 | Track & Field Renovations | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-03-16 | 2024-04-14 | 2024-03-16 | 2024-04-14
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC006-010 | NEW LIGHTING FOR MAIN STAGE THEATER | 2 | PRELIMINARY DESIGN | 2010-08-30 | 2010-12-27 | 2010-08-30 | 2010-12-27
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC006-010 | NEW LIGHTING FOR MAIN STAGE THEATER | 3 | FINAL DESIGN | 2010-12-28 | 2011-06-25 | 2010-12-28 | 2011-06-25
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC006-010 | NEW LIGHTING FOR MAIN STAGE THEATER | 4 | BID AWARD AND REGISTER CONTRCT | 2011-06-26 | 2011-09-23 | 2011-06-26 | 2011-09-23
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC006-010 | NEW LIGHTING FOR MAIN STAGE THEATER | 5 | CONSTRUCTION TO 25% | 2011-09-24 | 2012-01-21 | 2011-09-24 | 2012-01-21
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC006-010 | NEW LIGHTING FOR MAIN STAGE THEATER | 6 | CONSTRUCTION TO 50% | 2012-01-22 | 2012-05-20 | 2012-01-22 | 2012-05-20
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC006-010 | NEW LIGHTING FOR MAIN STAGE THEATER | 7 | CONSTRUCTION TO 75% | 2012-05-21 | 2012-09-17 | 2012-05-21 | 2012-09-17
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC006-010 | NEW LIGHTING FOR MAIN STAGE THEATER | 8 | ORIGINAL EQUIP & FURNISHING | 2012-09-18 | 2012-12-16 | 2012-09-18 | 2012-12-16
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC006-010 | NEW LIGHTING FOR MAIN STAGE THEATER | 9 | SUBSTANTIAL COMPLETION | 2012-12-17 | 2013-02-14 | 2012-12-17 | 2013-02-14
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC006-010 | NEW LIGHTING FOR MAIN STAGE THEATER | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-02-15 | 2013-03-16 | 2013-02-15 | 2013-03-16
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC022-007 | Financial Aid Office Renovation | 1 | DEVELOP SCOPE | 2007-05-25 | 2007-08-22 | 2020-07-01 | 2020-09-28
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC022-007 | Financial Aid Office Renovation | 2 | PRELIMINARY DESIGN | 2007-08-23 | 2007-12-20 | 2020-09-29 | 2021-01-26
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC022-007 | Financial Aid Office Renovation | 3 | FINAL DESIGN | 2007-12-21 | 2008-06-17 | 2021-01-27 | 2021-07-25
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC022-007 | Financial Aid Office Renovation | 4 | BID AWARD AND REGISTER CONTRCT | 2008-06-18 | 2008-09-15 | 2021-07-26 | 2021-10-23
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC022-007 | Financial Aid Office Renovation | 5 | CONSTRUCTION TO 25% | 2008-09-16 | 2009-01-13 | 2021-10-24 | 2022-02-20
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC022-007 | Financial Aid Office Renovation | 6 | CONSTRUCTION TO 50% | 2009-01-14 | 2009-05-13 | 2022-02-21 | 2022-06-20
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC022-007 | Financial Aid Office Renovation | 7 | CONSTRUCTION TO 75% | 2009-05-14 | 2009-09-10 | 2022-06-21 | 2022-10-18
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC022-007 | Financial Aid Office Renovation | 8 | ORIGINAL EQUIP & FURNISHING | 2009-09-11 | 2009-12-09 | 2022-10-19 | 2023-01-16
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC022-007 | Financial Aid Office Renovation | 9 | SUBSTANTIAL COMPLETION | 2009-12-10 | 2010-02-07 | 2023-01-17 | 2023-03-17
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC022-007 | Financial Aid Office Renovation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2010-02-08 | 2010-03-09 | 2023-03-18 | 2023-04-16
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC025-008 | SCIENCE FACILITY UPGRADES | 1 | DEVELOP SCOPE | 2018-06-01 | 2018-08-29 | 2018-06-01 | 2018-08-29
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC025-008 | SCIENCE FACILITY UPGRADES | 2 | PRELIMINARY DESIGN | 2018-08-30 | 2018-12-27 | 2018-08-30 | 2018-12-27
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC025-008 | SCIENCE FACILITY UPGRADES | 3 | FINAL DESIGN | 2018-12-28 | 2019-06-25 | 2018-12-28 | 2019-06-25
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC025-008 | SCIENCE FACILITY UPGRADES | 4 | BID AWARD AND REGISTER CONTRCT | 2019-06-26 | 2019-09-23 | 2019-06-26 | 2019-09-23
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC025-008 | SCIENCE FACILITY UPGRADES | 5 | CONSTRUCTION TO 25% | 2019-09-24 | 2020-01-21 | 2019-09-24 | 2020-01-21
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC025-008 | SCIENCE FACILITY UPGRADES | 6 | CONSTRUCTION TO 50% | 2020-01-22 | 2020-05-20 | 2020-01-22 | 2020-05-20
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC025-008 | SCIENCE FACILITY UPGRADES | 7 | CONSTRUCTION TO 75% | 2020-05-21 | 2020-09-17 | 2020-05-21 | 2020-09-17
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC025-008 | SCIENCE FACILITY UPGRADES | 8 | ORIGINAL EQUIP & FURNISHING | 2020-09-18 | 2020-12-16 | 2020-09-18 | 2020-12-16
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC025-008 | SCIENCE FACILITY UPGRADES | 9 | SUBSTANTIAL COMPLETION | 2020-12-17 | 2021-02-14 | 2020-12-17 | 2021-02-14
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC025-008 | SCIENCE FACILITY UPGRADES | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-02-15 | 2021-03-16 | 2021-02-15 | 2024-03-31
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC027-008 | EXTERIOR BEAUTIFICATION, YORK COLLEGE | 1 | DEVELOP SCOPE | 2009-06-01 | 2009-08-29 | 2009-06-01 | 2009-08-29
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC027-008 | EXTERIOR BEAUTIFICATION, YORK COLLEGE | 2 | PRELIMINARY DESIGN | 2009-08-30 | 2009-12-27 | 2009-08-30 | 2009-12-27
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC027-008 | EXTERIOR BEAUTIFICATION, YORK COLLEGE | 3 | FINAL DESIGN | 2009-12-28 | 2010-06-25 | 2009-12-28 | 2010-06-25
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC027-008 | EXTERIOR BEAUTIFICATION, YORK COLLEGE | 4 | BID AWARD AND REGISTER CONTRCT | 2010-06-26 | 2010-09-23 | 2010-06-26 | 2010-09-23
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC027-008 | EXTERIOR BEAUTIFICATION, YORK COLLEGE | 5 | CONSTRUCTION TO 25% | 2010-09-24 | 2011-01-21 | 2010-09-24 | 2011-01-21
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC027-008 | EXTERIOR BEAUTIFICATION, YORK COLLEGE | 6 | CONSTRUCTION TO 50% | 2011-01-22 | 2011-05-21 | 2011-01-22 | 2011-05-21
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC027-008 | EXTERIOR BEAUTIFICATION, YORK COLLEGE | 7 | CONSTRUCTION TO 75% | 2011-05-22 | 2011-09-18 | 2011-05-22 | 2011-09-18
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC027-008 | EXTERIOR BEAUTIFICATION, YORK COLLEGE | 8 | ORIGINAL EQUIP & FURNISHING | 2011-09-19 | 2011-12-17 | 2011-09-19 | 2011-12-17
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC027-008 | EXTERIOR BEAUTIFICATION, YORK COLLEGE | 9 | SUBSTANTIAL COMPLETION | 2011-12-18 | 2012-02-15 | 2011-12-18 | 2012-02-15
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC027-008 | EXTERIOR BEAUTIFICATION, YORK COLLEGE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-02-16 | 2012-03-16 | 2012-02-16 | 2023-03-31
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC028-008 | IMPROVEMENTS TO THE PERFORMING ARTS CENTER | 1 | DEVELOP SCOPE | 2009-06-01 | 2009-08-29 | 2009-06-01 | 2009-08-29
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC028-008 | IMPROVEMENTS TO THE PERFORMING ARTS CENTER | 2 | PRELIMINARY DESIGN | 2009-08-30 | 2009-12-27 | 2009-08-30 | 2009-12-27
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC028-008 | IMPROVEMENTS TO THE PERFORMING ARTS CENTER | 3 | FINAL DESIGN | 2009-12-28 | 2010-06-25 | 2009-12-28 | 2010-06-25
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC028-008 | IMPROVEMENTS TO THE PERFORMING ARTS CENTER | 4 | BID AWARD AND REGISTER CONTRCT | 2010-06-26 | 2010-09-23 | 2010-06-26 | 2010-09-23
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC028-008 | IMPROVEMENTS TO THE PERFORMING ARTS CENTER | 5 | CONSTRUCTION TO 25% | 2010-09-24 | 2011-01-21 | 2010-09-24 | 2011-01-21
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC028-008 | IMPROVEMENTS TO THE PERFORMING ARTS CENTER | 6 | CONSTRUCTION TO 50% | 2011-01-22 | 2011-05-21 | 2011-01-22 | 2011-05-21
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC028-008 | IMPROVEMENTS TO THE PERFORMING ARTS CENTER | 7 | CONSTRUCTION TO 75% | 2011-05-22 | 2011-09-18 | 2011-05-22 | 2011-09-18
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC028-008 | IMPROVEMENTS TO THE PERFORMING ARTS CENTER | 8 | ORIGINAL EQUIP & FURNISHING | 2011-09-19 | 2011-12-17 | 2011-09-19 | 2011-12-17
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC028-008 | IMPROVEMENTS TO THE PERFORMING ARTS CENTER | 9 | SUBSTANTIAL COMPLETION | 2011-12-18 | 2012-02-15 | 2011-12-18 | 2012-02-15
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC028-008 | IMPROVEMENTS TO THE PERFORMING ARTS CENTER | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-02-16 | 2012-03-16 | 2012-02-16 | 2025-03-31
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC035-011 | New Media Lecture Hall | 1 | DEVELOP SCOPE | 2011-06-01 | 2011-08-29 | 2011-06-01 | 2011-08-29
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC035-011 | New Media Lecture Hall | 2 | PRELIMINARY DESIGN | 2011-08-30 | 2011-12-27 | 2011-08-30 | 2011-12-27
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC035-011 | New Media Lecture Hall | 3 | FINAL DESIGN | 2011-12-28 | 2012-06-24 | 2011-12-28 | 2012-06-24
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC035-011 | New Media Lecture Hall | 4 | BID AWARD AND REGISTER CONTRCT | 2012-06-25 | 2012-09-22 | 2012-06-25 | 2012-09-22
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC035-011 | New Media Lecture Hall | 5 | CONSTRUCTION TO 25% | 2012-09-23 | 2013-01-20 | 2012-09-23 | 2013-01-20
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC035-011 | New Media Lecture Hall | 6 | CONSTRUCTION TO 50% | 2013-01-21 | 2013-05-20 | 2013-01-21 | 2013-05-20
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC035-011 | New Media Lecture Hall | 7 | CONSTRUCTION TO 75% | 2013-05-21 | 2013-09-17 | 2013-05-21 | 2013-09-17
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC035-011 | New Media Lecture Hall | 8 | ORIGINAL EQUIP & FURNISHING | 2013-09-18 | 2013-12-16 | 2013-09-18 | 2013-12-16
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC035-011 | New Media Lecture Hall | 9 | SUBSTANTIAL COMPLETION | 2013-12-17 | 2014-02-14 | 2013-12-17 | 2014-02-14
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC035-011 | New Media Lecture Hall | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-02-15 | 2014-03-16 | 2014-02-15 | 2022-12-31
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC043-013 | Daycare Facility Improvements | 1 | DEVELOP SCOPE | 2013-06-01 | 2013-08-29 | 2013-06-01 | 2013-08-29
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC043-013 | Daycare Facility Improvements | 2 | PRELIMINARY DESIGN | 2013-08-30 | 2013-12-27 | 2013-08-30 | 2013-12-27
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC043-013 | Daycare Facility Improvements | 3 | FINAL DESIGN | 2013-12-28 | 2014-06-25 | 2013-12-28 | 2014-06-25
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC043-013 | Daycare Facility Improvements | 4 | BID AWARD AND REGISTER CONTRCT | 2014-06-26 | 2014-09-23 | 2014-06-26 | 2014-09-23
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC043-013 | Daycare Facility Improvements | 5 | CONSTRUCTION TO 25% | 2014-09-24 | 2015-01-21 | 2014-09-24 | 2015-01-21
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC043-013 | Daycare Facility Improvements | 6 | CONSTRUCTION TO 50% | 2015-01-22 | 2015-05-21 | 2015-01-22 | 2015-05-21
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC043-013 | Daycare Facility Improvements | 7 | CONSTRUCTION TO 75% | 2015-05-22 | 2015-09-18 | 2015-05-22 | 2015-09-18
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC043-013 | Daycare Facility Improvements | 8 | ORIGINAL EQUIP & FURNISHING | 2015-09-19 | 2015-12-17 | 2015-09-19 | 2015-12-17
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC043-013 | Daycare Facility Improvements | 9 | SUBSTANTIAL COMPLETION | 2015-12-18 | 2016-02-15 | 2015-12-18 | 2016-02-15
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC043-013 | Daycare Facility Improvements | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-02-16 | 2016-03-16 | 2016-02-16 | 2023-03-31
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC049-014 | Renovate/Build 3D Graphics and Printing Lab | 1 | DEVELOP SCOPE | 2014-06-01 | 2014-08-29 | 2014-06-01 | 2014-08-29
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC049-014 | Renovate/Build 3D Graphics and Printing Lab | 2 | PRELIMINARY DESIGN | 2014-08-30 | 2014-12-27 | 2014-08-30 | 2014-12-27
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC049-014 | Renovate/Build 3D Graphics and Printing Lab | 3 | FINAL DESIGN | 2014-12-28 | 2015-06-25 | 2014-12-28 | 2015-06-25
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC049-014 | Renovate/Build 3D Graphics and Printing Lab | 4 | BID AWARD AND REGISTER CONTRCT | 2015-06-26 | 2015-09-23 | 2015-06-26 | 2015-09-23
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC049-014 | Renovate/Build 3D Graphics and Printing Lab | 5 | CONSTRUCTION TO 25% | 2015-09-24 | 2016-01-21 | 2015-09-24 | 2016-01-21
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC049-014 | Renovate/Build 3D Graphics and Printing Lab | 6 | CONSTRUCTION TO 50% | 2016-01-22 | 2016-05-20 | 2016-01-22 | 2016-05-20
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC049-014 | Renovate/Build 3D Graphics and Printing Lab | 7 | CONSTRUCTION TO 75% | 2016-05-21 | 2016-09-17 | 2016-05-21 | 2016-09-17
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC049-014 | Renovate/Build 3D Graphics and Printing Lab | 8 | ORIGINAL EQUIP & FURNISHING | 2016-09-18 | 2016-12-16 | 2016-09-18 | 2016-12-16
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC049-014 | Renovate/Build 3D Graphics and Printing Lab | 9 | SUBSTANTIAL COMPLETION | 2016-12-17 | 2017-02-14 | 2016-12-17 | 2017-02-14
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC049-014 | Renovate/Build 3D Graphics and Printing Lab | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-02-15 | 2017-03-16 | 2017-02-15 | 2026-03-31
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC051-015 | Performing Arts Center Renovations | 1 | DEVELOP SCOPE | 2014-10-01 | 2014-12-29 | 2020-07-01 | 2020-09-29
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC051-015 | Performing Arts Center Renovations | 2 | PRELIMINARY DESIGN | 2014-12-30 | 2015-04-28 | 2020-09-30 | 2021-01-27
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC051-015 | Performing Arts Center Renovations | 3 | FINAL DESIGN | 2015-04-29 | 2015-10-25 | 2021-01-28 | 2021-07-26
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC051-015 | Performing Arts Center Renovations | 4 | BID AWARD AND REGISTER CONTRCT | 2015-10-26 | 2016-01-23 | 2021-07-27 | 2021-10-24
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC051-015 | Performing Arts Center Renovations | 5 | CONSTRUCTION TO 25% | 2016-01-24 | 2016-05-22 | 2021-10-25 | 2022-02-21
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC051-015 | Performing Arts Center Renovations | 6 | CONSTRUCTION TO 50% | 2016-05-23 | 2016-09-19 | 2022-02-22 | 2022-06-21
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC051-015 | Performing Arts Center Renovations | 7 | CONSTRUCTION TO 75% | 2016-09-20 | 2017-01-17 | 2022-06-22 | 2022-10-19
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC051-015 | Performing Arts Center Renovations | 8 | ORIGINAL EQUIP & FURNISHING | 2017-01-18 | 2017-04-17 | 2022-10-20 | 2023-01-17
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC051-015 | Performing Arts Center Renovations | 9 | SUBSTANTIAL COMPLETION | 2017-04-18 | 2017-06-16 | 2023-01-18 | 2023-03-18
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC051-015 | Performing Arts Center Renovations | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-06-17 | 2017-07-16 | 2023-03-19 | 2023-04-17
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC052-016 | Laboratory and Classroom Upgrades | 1 | DEVELOP SCOPE | 2016-06-30 | 2016-09-27 | 2016-06-30 | 2016-09-27
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC052-016 | Laboratory and Classroom Upgrades | 2 | PRELIMINARY DESIGN | 2016-09-28 | 2017-01-25 | 2016-09-28 | 2017-01-25
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC052-016 | Laboratory and Classroom Upgrades | 3 | FINAL DESIGN | 2017-01-26 | 2017-07-24 | 2017-01-26 | 2017-07-24
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC052-016 | Laboratory and Classroom Upgrades | 4 | BID AWARD AND REGISTER CONTRCT | 2017-07-25 | 2017-10-22 | 2017-07-25 | 2017-10-22
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC052-016 | Laboratory and Classroom Upgrades | 5 | CONSTRUCTION TO 25% | 2017-10-23 | 2018-02-19 | 2017-10-23 | 2018-02-19
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC052-016 | Laboratory and Classroom Upgrades | 6 | CONSTRUCTION TO 50% | 2018-02-20 | 2018-06-19 | 2018-02-20 | 2018-06-19