20201123 | QUEENS | 042 | CITY UNIVERSITY | YC052-016 | Laboratory and Classroom Upgrades | 7 | CONSTRUCTION TO 75% | 2018-06-20 | 2018-10-17 | 2018-06-20 | 2018-10-17
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC052-016 | Laboratory and Classroom Upgrades | 8 | ORIGINAL EQUIP & FURNISHING | 2018-10-18 | 2019-01-15 | 2018-10-18 | 2019-01-15
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC052-016 | Laboratory and Classroom Upgrades | 9 | SUBSTANTIAL COMPLETION | 2019-01-16 | 2019-03-16 | 2019-01-16 | 2019-03-16
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC052-016 | Laboratory and Classroom Upgrades | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-03-17 | 2019-04-15 | 2019-03-17 | 2025-04-30
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC054-017 | Greenhouse Renovation | 1 | DEVELOP SCOPE | 2017-06-01 | 2017-08-29 | 2020-07-01 | 2020-09-28
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC054-017 | Greenhouse Renovation | 2 | PRELIMINARY DESIGN | 2017-08-30 | 2017-12-27 | 2020-09-29 | 2021-01-26
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC054-017 | Greenhouse Renovation | 3 | FINAL DESIGN | 2017-12-28 | 2018-06-25 | 2021-01-27 | 2021-07-25
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC054-017 | Greenhouse Renovation | 4 | BID AWARD AND REGISTER CONTRCT | 2018-06-26 | 2018-09-23 | 2021-07-26 | 2021-10-23
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC054-017 | Greenhouse Renovation | 5 | CONSTRUCTION TO 25% | 2018-09-24 | 2019-01-21 | 2021-10-24 | 2022-02-20
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC054-017 | Greenhouse Renovation | 6 | CONSTRUCTION TO 50% | 2019-01-22 | 2019-05-21 | 2022-02-21 | 2022-06-20
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC054-017 | Greenhouse Renovation | 7 | CONSTRUCTION TO 75% | 2019-05-22 | 2019-09-18 | 2022-06-21 | 2022-10-18
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC054-017 | Greenhouse Renovation | 8 | ORIGINAL EQUIP & FURNISHING | 2019-09-19 | 2019-12-17 | 2022-10-19 | 2023-01-16
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC054-017 | Greenhouse Renovation | 9 | SUBSTANTIAL COMPLETION | 2019-12-18 | 2020-02-15 | 2023-01-17 | 2023-03-17
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC054-017 | Greenhouse Renovation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-02-16 | 2020-03-16 | 2023-03-18 | 2023-04-16
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC055-017 | Digital Convergence Center | 1 | DEVELOP SCOPE | 2017-06-01 | 2017-08-29 | 2021-07-01 | 2021-09-28
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC055-017 | Digital Convergence Center | 2 | PRELIMINARY DESIGN | 2017-08-30 | 2017-12-27 | 2021-09-29 | 2022-01-26
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC055-017 | Digital Convergence Center | 3 | FINAL DESIGN | 2017-12-28 | 2018-06-25 | 2022-01-27 | 2022-07-25
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC055-017 | Digital Convergence Center | 4 | BID AWARD AND REGISTER CONTRCT | 2018-06-26 | 2018-09-23 | 2022-07-26 | 2022-10-23
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC055-017 | Digital Convergence Center | 5 | CONSTRUCTION TO 25% | 2018-09-24 | 2019-01-21 | 2022-10-24 | 2023-02-20
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC055-017 | Digital Convergence Center | 6 | CONSTRUCTION TO 50% | 2019-01-22 | 2019-05-21 | 2023-02-21 | 2023-06-20
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC055-017 | Digital Convergence Center | 7 | CONSTRUCTION TO 75% | 2019-05-22 | 2019-09-18 | 2023-06-21 | 2023-10-18
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC055-017 | Digital Convergence Center | 8 | ORIGINAL EQUIP & FURNISHING | 2019-09-19 | 2019-12-17 | 2023-10-19 | 2024-01-16
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC055-017 | Digital Convergence Center | 9 | SUBSTANTIAL COMPLETION | 2019-12-18 | 2020-02-15 | 2024-01-17 | 2024-03-16
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC055-017 | Digital Convergence Center | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-02-16 | 2020-03-16 | 2024-03-17 | 2024-04-16
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC059-019 | Renonvation to Track | 1 | DEVELOP SCOPE | 2018-06-30 | 2018-09-27 | 2018-06-30 | 2018-09-27
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC059-019 | Renonvation to Track | 2 | PRELIMINARY DESIGN | 2018-09-28 | 2019-01-25 | 2018-09-28 | 2019-01-25
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC059-019 | Renonvation to Track | 3 | FINAL DESIGN | 2019-01-26 | 2019-07-24 | 2019-01-26 | 2019-07-24
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC059-019 | Renonvation to Track | 4 | BID AWARD AND REGISTER CONTRCT | 2019-07-25 | 2019-10-22 | 2019-07-25 | 2019-10-22
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC059-019 | Renonvation to Track | 5 | CONSTRUCTION TO 25% | 2019-10-23 | 2020-02-19 | 2019-10-23 | 2020-02-19
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC059-019 | Renonvation to Track | 6 | CONSTRUCTION TO 50% | 2020-02-20 | 2020-06-18 | 2020-02-20 | 2020-06-18
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC059-019 | Renonvation to Track | 7 | CONSTRUCTION TO 75% | 2020-06-19 | 2020-10-16 | 2020-06-19 | 2020-10-16
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC059-019 | Renonvation to Track | 8 | ORIGINAL EQUIP & FURNISHING | 2020-10-17 | 2021-01-14 | 2020-10-17 | 2021-01-14
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC059-019 | Renonvation to Track | 9 | SUBSTANTIAL COMPLETION | 2021-01-15 | 2021-03-15 | 2021-01-15 | 2021-03-15
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC059-019 | Renonvation to Track | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-16 | 2021-04-14 | 2021-03-16 | 2025-04-30
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC061-020 | Performing Arts Center Upgrades | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-09-28 | 2019-07-01 | 2019-09-28
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC061-020 | Performing Arts Center Upgrades | 2 | PRELIMINARY DESIGN | 2019-09-29 | 2020-01-26 | 2019-09-29 | 2020-01-26
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC061-020 | Performing Arts Center Upgrades | 3 | FINAL DESIGN | 2020-01-27 | 2020-07-24 | 2020-01-27 | 2020-07-24
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC061-020 | Performing Arts Center Upgrades | 4 | BID AWARD AND REGISTER CONTRCT | 2020-07-25 | 2020-10-22 | 2020-07-25 | 2020-10-22
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC061-020 | Performing Arts Center Upgrades | 5 | CONSTRUCTION TO 25% | 2020-10-23 | 2021-02-19 | 2020-10-23 | 2021-02-19
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC061-020 | Performing Arts Center Upgrades | 6 | CONSTRUCTION TO 50% | 2021-02-20 | 2021-06-19 | 2021-02-20 | 2021-06-19
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC061-020 | Performing Arts Center Upgrades | 7 | CONSTRUCTION TO 75% | 2021-06-20 | 2021-10-17 | 2021-06-20 | 2021-10-17
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC061-020 | Performing Arts Center Upgrades | 8 | ORIGINAL EQUIP & FURNISHING | 2021-10-18 | 2022-01-15 | 2021-10-18 | 2022-01-15
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC061-020 | Performing Arts Center Upgrades | 9 | SUBSTANTIAL COMPLETION | 2022-01-16 | 2022-03-16 | 2022-01-16 | 2022-03-16
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC061-020 | Performing Arts Center Upgrades | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-17 | 2022-04-15 | 2022-03-17 | 2022-04-15
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC063-020 | Recapture Academic Space | 1 | DEVELOP SCOPE | 2021-07-01 | 2021-09-28 | 2021-07-01 | 2021-09-28
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC063-020 | Recapture Academic Space | 2 | PRELIMINARY DESIGN | 2021-09-29 | 2022-01-26 | 2021-09-29 | 2022-01-26
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC063-020 | Recapture Academic Space | 3 | FINAL DESIGN | 2022-01-27 | 2022-07-25 | 2022-01-27 | 2022-07-25
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC063-020 | Recapture Academic Space | 4 | BID AWARD AND REGISTER CONTRCT | 2022-07-26 | 2022-10-23 | 2022-07-26 | 2022-10-23
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC063-020 | Recapture Academic Space | 5 | CONSTRUCTION TO 25% | 2022-10-24 | 2023-02-20 | 2022-10-24 | 2023-02-20
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC063-020 | Recapture Academic Space | 6 | CONSTRUCTION TO 50% | 2023-02-21 | 2023-06-20 | 2023-02-21 | 2023-06-20
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC063-020 | Recapture Academic Space | 7 | CONSTRUCTION TO 75% | 2023-06-21 | 2023-10-18 | 2023-06-21 | 2023-10-18
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC063-020 | Recapture Academic Space | 8 | ORIGINAL EQUIP & FURNISHING | 2023-10-19 | 2024-01-16 | 2023-10-19 | 2024-01-16
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC063-020 | Recapture Academic Space | 9 | SUBSTANTIAL COMPLETION | 2024-01-17 | 2024-03-16 | 2024-01-17 | 2024-03-16
20201123 | QUEENS | 042 | CITY UNIVERSITY | YC063-020 | Recapture Academic Space | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-03-17 | 2024-04-15 | 2024-03-17 | 2024-04-15
20201123 | QUEENS | 056 | POLICE DEPARTMENT | ACENYP601 | NYPD - Old Police Academy Steam Trap Replacement | 1 | DEVELOP SCOPE | 2018-06-30 | 2018-09-27 | 2018-06-30 | 2018-09-27
20201123 | QUEENS | 056 | POLICE DEPARTMENT | ACENYP601 | NYPD - Old Police Academy Steam Trap Replacement | 2 | PRELIMINARY DESIGN | 2018-09-28 | 2019-01-25 | 2018-09-28 | 2019-01-25
20201123 | QUEENS | 056 | POLICE DEPARTMENT | ACENYP601 | NYPD - Old Police Academy Steam Trap Replacement | 3 | FINAL DESIGN | 2019-01-26 | 2019-07-24 | 2019-01-26 | 2019-07-24
20201123 | QUEENS | 056 | POLICE DEPARTMENT | ACENYP601 | NYPD - Old Police Academy Steam Trap Replacement | 4 | BID AWARD AND REGISTER CONTRCT | 2019-07-25 | 2019-10-22 | 2019-07-25 | 2019-10-22
20201123 | QUEENS | 056 | POLICE DEPARTMENT | ACENYP601 | NYPD - Old Police Academy Steam Trap Replacement | 5 | CONSTRUCTION TO 25% | 2019-10-23 | 2020-02-19 | 2019-10-23 | 2020-02-19
20201123 | QUEENS | 056 | POLICE DEPARTMENT | ACENYP601 | NYPD - Old Police Academy Steam Trap Replacement | 6 | CONSTRUCTION TO 50% | 2020-02-20 | 2020-06-18 | 2020-02-20 | 2020-06-18
20201123 | QUEENS | 056 | POLICE DEPARTMENT | ACENYP601 | NYPD - Old Police Academy Steam Trap Replacement | 7 | CONSTRUCTION TO 75% | 2020-06-19 | 2020-10-16 | 2020-06-19 | 2021-10-16
20201123 | QUEENS | 056 | POLICE DEPARTMENT | ACENYP601 | NYPD - Old Police Academy Steam Trap Replacement | 8 | ORIGINAL EQUIP & FURNISHING | 2020-10-17 | 2021-01-14 | 2021-10-17 | 2022-01-14
20201123 | QUEENS | 056 | POLICE DEPARTMENT | ACENYP601 | NYPD - Old Police Academy Steam Trap Replacement | 9 | SUBSTANTIAL COMPLETION | 2021-01-15 | 2021-03-15 | 2022-01-15 | 2022-03-15
20201123 | QUEENS | 056 | POLICE DEPARTMENT | ACENYP601 | NYPD - Old Police Academy Steam Trap Replacement | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-16 | 2021-04-14 | 2022-03-16 | 2022-04-14
20201123 | QUEENS | 056 | POLICE DEPARTMENT | ACEPOL701 | NYPD - CRS STEAM TRAP REPLACEMENT | 1 | DEVELOP SCOPE | 2019-06-30 | 2019-09-27 | 2019-06-30 | 2019-09-27
20201123 | QUEENS | 056 | POLICE DEPARTMENT | ACEPOL701 | NYPD - CRS STEAM TRAP REPLACEMENT | 2 | PRELIMINARY DESIGN | 2019-09-28 | 2020-01-25 | 2019-09-28 | 2020-01-25
20201123 | QUEENS | 056 | POLICE DEPARTMENT | ACEPOL701 | NYPD - CRS STEAM TRAP REPLACEMENT | 3 | FINAL DESIGN | 2020-01-26 | 2020-07-23 | 2020-01-26 | 2020-07-23
20201123 | QUEENS | 056 | POLICE DEPARTMENT | ACEPOL701 | NYPD - CRS STEAM TRAP REPLACEMENT | 4 | BID AWARD AND REGISTER CONTRCT | 2020-07-24 | 2020-10-21 | 2020-07-24 | 2020-10-21
20201123 | QUEENS | 056 | POLICE DEPARTMENT | ACEPOL701 | NYPD - CRS STEAM TRAP REPLACEMENT | 5 | CONSTRUCTION TO 25% | 2020-10-22 | 2021-02-18 | 2020-10-22 | 2021-02-18
20201123 | QUEENS | 056 | POLICE DEPARTMENT | ACEPOL701 | NYPD - CRS STEAM TRAP REPLACEMENT | 6 | CONSTRUCTION TO 50% | 2021-02-19 | 2021-06-18 | 2021-02-19 | 2021-06-18
20201123 | QUEENS | 056 | POLICE DEPARTMENT | ACEPOL701 | NYPD - CRS STEAM TRAP REPLACEMENT | 7 | CONSTRUCTION TO 75% | 2021-06-19 | 2021-10-16 | 2021-06-19 | 2021-10-16
20201123 | QUEENS | 056 | POLICE DEPARTMENT | ACEPOL701 | NYPD - CRS STEAM TRAP REPLACEMENT | 8 | ORIGINAL EQUIP & FURNISHING | 2021-10-17 | 2022-01-14 | 2021-10-17 | 2022-01-14
20201123 | QUEENS | 056 | POLICE DEPARTMENT | ACEPOL701 | NYPD - CRS STEAM TRAP REPLACEMENT | 9 | SUBSTANTIAL COMPLETION | 2022-01-15 | 2022-03-15 | 2022-01-15 | 2022-03-15
20201123 | QUEENS | 056 | POLICE DEPARTMENT | ACEPOL701 | NYPD - CRS STEAM TRAP REPLACEMENT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-16 | 2022-04-14 | 2022-03-16 | 2022-04-14
20201123 | QUEENS | 056 | POLICE DEPARTMENT | ACEPOL901 | NYPD - Chiller Replacement at 10 NYPD Precincts | 1 | DEVELOP SCOPE | 2020-01-01 | 2020-03-30 | 2020-01-01 | 2020-03-30
20201123 | QUEENS | 056 | POLICE DEPARTMENT | ACEPOL901 | NYPD - Chiller Replacement at 10 NYPD Precincts | 2 | PRELIMINARY DESIGN | 2020-03-31 | 2020-07-28 | 2020-03-31 | 2020-07-28
20201123 | QUEENS | 056 | POLICE DEPARTMENT | ACEPOL901 | NYPD - Chiller Replacement at 10 NYPD Precincts | 3 | FINAL DESIGN | 2020-07-29 | 2021-01-24 | 2020-07-29 | 2021-01-24
20201123 | QUEENS | 056 | POLICE DEPARTMENT | ACEPOL901 | NYPD - Chiller Replacement at 10 NYPD Precincts | 4 | BID AWARD AND REGISTER CONTRCT | 2021-01-25 | 2021-04-24 | 2021-01-25 | 2021-04-24
20201123 | QUEENS | 056 | POLICE DEPARTMENT | ACEPOL901 | NYPD - Chiller Replacement at 10 NYPD Precincts | 5 | CONSTRUCTION TO 25% | 2021-04-25 | 2021-08-22 | 2021-04-25 | 2021-08-22
20201123 | QUEENS | 056 | POLICE DEPARTMENT | ACEPOL901 | NYPD - Chiller Replacement at 10 NYPD Precincts | 6 | CONSTRUCTION TO 50% | 2021-08-23 | 2021-12-20 | 2021-08-23 | 2021-12-20
20201123 | QUEENS | 056 | POLICE DEPARTMENT | ACEPOL901 | NYPD - Chiller Replacement at 10 NYPD Precincts | 7 | CONSTRUCTION TO 75% | 2021-12-21 | 2022-04-19 | 2021-12-21 | 2022-04-19
20201123 | QUEENS | 056 | POLICE DEPARTMENT | ACEPOL901 | NYPD - Chiller Replacement at 10 NYPD Precincts | 8 | ORIGINAL EQUIP & FURNISHING | 2022-04-20 | 2022-07-18 | 2022-04-20 | 2022-07-18
20201123 | QUEENS | 056 | POLICE DEPARTMENT | ACEPOL901 | NYPD - Chiller Replacement at 10 NYPD Precincts | 9 | SUBSTANTIAL COMPLETION | 2022-07-19 | 2022-09-16 | 2022-07-19 | 2022-09-16
20201123 | QUEENS | 056 | POLICE DEPARTMENT | ACEPOL901 | NYPD - Chiller Replacement at 10 NYPD Precincts | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-17 | 2022-10-16 | 2022-09-17 | 2022-10-16
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAHH | HWY # 3 SEPTIC TANK | 1 | DEVELOP SCOPE | 2014-06-30 | 2014-09-27 | 2014-06-30 | 2014-09-27
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAHH | HWY # 3 SEPTIC TANK | 2 | PRELIMINARY DESIGN | 2014-09-28 | 2015-01-25 | 2014-09-28 | 2015-01-25
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAHH | HWY # 3 SEPTIC TANK | 3 | FINAL DESIGN | 2015-01-26 | 2015-07-24 | 2015-01-26 | 2015-07-24
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAHH | HWY # 3 SEPTIC TANK | 4 | BID AWARD AND REGISTER CONTRCT | 2015-07-25 | 2015-10-22 | 2015-07-25 | 2015-10-22
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAHH | HWY # 3 SEPTIC TANK | 5 | CONSTRUCTION TO 25% | 2015-10-23 | 2016-02-19 | 2015-10-23 | 2016-02-19
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAHH | HWY # 3 SEPTIC TANK | 6 | CONSTRUCTION TO 50% | 2016-02-20 | 2016-06-18 | 2016-02-20 | 2016-06-18
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAHH | HWY # 3 SEPTIC TANK | 7 | CONSTRUCTION TO 75% | 2016-06-19 | 2016-10-16 | 2016-06-19 | 2020-10-16
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAHH | HWY # 3 SEPTIC TANK | 8 | ORIGINAL EQUIP & FURNISHING | 2016-10-17 | 2017-01-14 | 2020-10-17 | 2021-01-14
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAHH | HWY # 3 SEPTIC TANK | 9 | SUBSTANTIAL COMPLETION | 2017-01-15 | 2017-03-15 | 2021-01-15 | 2021-03-15
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAHH | HWY # 3 SEPTIC TANK | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-16 | 2017-04-14 | 2021-03-16 | 2021-04-14
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAHM | 101ST PCT HANDICAP RAMP | 1 | DEVELOP SCOPE | 2014-06-30 | 2014-09-27 | 2014-06-30 | 2014-09-27
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAHM | 101ST PCT HANDICAP RAMP | 2 | PRELIMINARY DESIGN | 2014-09-28 | 2015-01-25 | 2014-09-28 | 2015-01-25
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAHM | 101ST PCT HANDICAP RAMP | 3 | FINAL DESIGN | 2015-01-26 | 2015-07-24 | 2015-01-26 | 2015-07-24
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAHM | 101ST PCT HANDICAP RAMP | 4 | BID AWARD AND REGISTER CONTRCT | 2015-07-25 | 2015-10-22 | 2015-07-25 | 2015-10-22
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAHM | 101ST PCT HANDICAP RAMP | 5 | CONSTRUCTION TO 25% | 2015-10-23 | 2016-02-19 | 2015-10-23 | 2016-02-19
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAHM | 101ST PCT HANDICAP RAMP | 6 | CONSTRUCTION TO 50% | 2016-02-20 | 2016-06-18 | 2016-02-20 | 2016-06-18
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAHM | 101ST PCT HANDICAP RAMP | 7 | CONSTRUCTION TO 75% | 2016-06-19 | 2016-10-16 | 2016-06-19 | 2021-10-16
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAHM | 101ST PCT HANDICAP RAMP | 8 | ORIGINAL EQUIP & FURNISHING | 2016-10-17 | 2017-01-14 | 2021-10-17 | 2022-01-14
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAHM | 101ST PCT HANDICAP RAMP | 9 | SUBSTANTIAL COMPLETION | 2017-01-15 | 2017-03-15 | 2022-01-15 | 2022-03-15
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAHM | 101ST PCT HANDICAP RAMP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-16 | 2017-04-14 | 2022-03-16 | 2022-04-14
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAIF | 110TH FACADE | 1 | DEVELOP SCOPE | 2016-09-10 | 2016-12-08 | 2014-06-10 | 2014-09-07
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAIF | 110TH FACADE | 2 | PRELIMINARY DESIGN | 2016-12-09 | 2017-04-07 | 2014-09-08 | 2015-01-05
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAIF | 110TH FACADE | 3 | FINAL DESIGN | 2017-04-08 | 2017-08-05 | 2015-01-06 | 2015-05-05
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAIF | 110TH FACADE | 4 | BID AWARD AND REGISTER CONTRCT | 2017-08-06 | 2018-02-01 | 2015-05-06 | 2015-11-01
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAIF | 110TH FACADE | 5 | CONSTRUCTION TO 25% | 2018-02-02 | 2018-06-01 | 2015-11-02 | 2016-02-29
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAIF | 110TH FACADE | 6 | CONSTRUCTION TO 50% | 2018-06-02 | 2018-09-29 | 2016-03-01 | 2016-06-28
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAIF | 110TH FACADE | 7 | CONSTRUCTION TO 75% | 2018-09-30 | 2019-01-27 | 2016-06-29 | 2020-10-27
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAIF | 110TH FACADE | 8 | ORIGINAL EQUIP & FURNISHING | 2019-01-28 | 2019-04-27 | 2020-10-28 | 2021-01-25
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAIF | 110TH FACADE | 9 | SUBSTANTIAL COMPLETION | 2019-04-28 | 2019-06-26 | 2021-01-26 | 2021-03-26
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAIF | 110TH FACADE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-06-27 | 2019-07-26 | 2021-03-27 | 2021-04-25
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAII | FACADE AT NYPD'S FORENSIC LABORATORY | 1 | DEVELOP SCOPE | 2016-09-10 | 2016-12-08 | 2019-06-10 | 2019-09-07
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAII | FACADE AT NYPD'S FORENSIC LABORATORY | 2 | PRELIMINARY DESIGN | 2016-12-09 | 2017-04-07 | 2019-09-08 | 2020-01-05
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAII | FACADE AT NYPD'S FORENSIC LABORATORY | 3 | FINAL DESIGN | 2017-04-08 | 2017-08-05 | 2020-01-06 | 2020-05-04
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAII | FACADE AT NYPD'S FORENSIC LABORATORY | 4 | BID AWARD AND REGISTER CONTRCT | 2017-08-06 | 2018-02-01 | 2020-05-05 | 2020-10-31
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAII | FACADE AT NYPD'S FORENSIC LABORATORY | 5 | CONSTRUCTION TO 25% | 2018-02-02 | 2018-06-01 | 2020-11-01 | 2021-02-28
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAII | FACADE AT NYPD'S FORENSIC LABORATORY | 6 | CONSTRUCTION TO 50% | 2018-06-02 | 2018-09-29 | 2021-03-01 | 2021-06-28
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAII | FACADE AT NYPD'S FORENSIC LABORATORY | 7 | CONSTRUCTION TO 75% | 2018-09-30 | 2019-01-27 | 2021-06-29 | 2025-04-24
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAII | FACADE AT NYPD'S FORENSIC LABORATORY | 8 | ORIGINAL EQUIP & FURNISHING | 2019-01-28 | 2019-04-27 | 2025-04-25 | 2025-07-23
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAII | FACADE AT NYPD'S FORENSIC LABORATORY | 9 | SUBSTANTIAL COMPLETION | 2019-04-28 | 2019-06-26 | 2025-07-24 | 2025-09-21
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAII | FACADE AT NYPD'S FORENSIC LABORATORY | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-06-27 | 2019-07-26 | 2025-09-22 | 2025-10-21
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAIJ | 106th pct FACADE | 1 | DEVELOP SCOPE | 2016-09-10 | 2016-12-08 | 2016-06-10 | 2016-09-07
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAIJ | 106th pct FACADE | 2 | PRELIMINARY DESIGN | 2016-12-09 | 2017-04-07 | 2016-09-08 | 2017-01-05
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAIJ | 106th pct FACADE | 3 | FINAL DESIGN | 2017-04-08 | 2017-08-05 | 2017-01-06 | 2017-05-05
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAIJ | 106th pct FACADE | 4 | BID AWARD AND REGISTER CONTRCT | 2017-08-06 | 2018-02-01 | 2017-05-06 | 2017-11-01
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAIJ | 106th pct FACADE | 5 | CONSTRUCTION TO 25% | 2018-02-02 | 2018-06-01 | 2017-11-02 | 2018-03-01
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAIJ | 106th pct FACADE | 6 | CONSTRUCTION TO 50% | 2018-06-02 | 2018-09-29 | 2018-03-02 | 2018-06-29
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAIJ | 106th pct FACADE | 7 | CONSTRUCTION TO 75% | 2018-09-30 | 2019-01-27 | 2018-06-30 | 2020-10-27
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAIJ | 106th pct FACADE | 8 | ORIGINAL EQUIP & FURNISHING | 2019-01-28 | 2019-04-27 | 2020-10-28 | 2021-01-25
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAIJ | 106th pct FACADE | 9 | SUBSTANTIAL COMPLETION | 2019-04-28 | 2019-06-26 | 2021-01-26 | 2021-03-26
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAIJ | 106th pct FACADE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-06-27 | 2019-07-26 | 2021-03-27 | 2021-04-25
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAKB | REPLACEMENT OF GASOLINE PIPES AT HARBOR GEORGE | 1 | DEVELOP SCOPE | 2019-06-01 | 2019-08-29 | 2019-06-01 | 2019-08-29
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAKB | REPLACEMENT OF GASOLINE PIPES AT HARBOR GEORGE | 2 | PRELIMINARY DESIGN | 2019-08-30 | 2019-12-27 | 2019-08-30 | 2019-12-27
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAKB | REPLACEMENT OF GASOLINE PIPES AT HARBOR GEORGE | 3 | FINAL DESIGN | 2019-12-28 | 2020-04-25 | 2019-12-28 | 2020-04-25
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAKB | REPLACEMENT OF GASOLINE PIPES AT HARBOR GEORGE | 4 | BID AWARD AND REGISTER CONTRCT | 2020-04-26 | 2020-10-22 | 2020-04-26 | 2020-10-22
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAKB | REPLACEMENT OF GASOLINE PIPES AT HARBOR GEORGE | 5 | CONSTRUCTION TO 25% | 2020-10-23 | 2021-02-19 | 2020-10-23 | 2021-02-19
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAKB | REPLACEMENT OF GASOLINE PIPES AT HARBOR GEORGE | 6 | CONSTRUCTION TO 50% | 2021-02-20 | 2021-06-19 | 2021-02-20 | 2021-06-19
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAKB | REPLACEMENT OF GASOLINE PIPES AT HARBOR GEORGE | 7 | CONSTRUCTION TO 75% | 2021-06-20 | 2021-10-17 | 2021-06-20 | 2021-10-17
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAKB | REPLACEMENT OF GASOLINE PIPES AT HARBOR GEORGE | 8 | ORIGINAL EQUIP & FURNISHING | 2021-10-18 | 2022-01-15 | 2021-10-18 | 2022-01-15
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAKB | REPLACEMENT OF GASOLINE PIPES AT HARBOR GEORGE | 9 | SUBSTANTIAL COMPLETION | 2022-01-16 | 2022-03-16 | 2022-01-16 | 2022-03-16
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAKB | REPLACEMENT OF GASOLINE PIPES AT HARBOR GEORGE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-17 | 2022-04-15 | 2022-03-17 | 2022-04-15
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAKH | SRG4 BATHROOM RENOVATION | 1 | DEVELOP SCOPE | 2019-06-10 | 2019-09-07 | 2019-06-10 | 2019-09-07
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAKH | SRG4 BATHROOM RENOVATION | 2 | PRELIMINARY DESIGN | 2019-09-08 | 2020-01-05 | 2019-09-08 | 2020-01-05
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAKH | SRG4 BATHROOM RENOVATION | 3 | FINAL DESIGN | 2020-01-06 | 2020-05-04 | 2020-01-06 | 2020-05-04
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAKH | SRG4 BATHROOM RENOVATION | 4 | BID AWARD AND REGISTER CONTRCT | 2020-05-05 | 2020-10-31 | 2020-05-05 | 2020-10-31
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAKH | SRG4 BATHROOM RENOVATION | 5 | CONSTRUCTION TO 25% | 2020-11-01 | 2021-02-28 | 2020-11-01 | 2021-02-28
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAKH | SRG4 BATHROOM RENOVATION | 6 | CONSTRUCTION TO 50% | 2021-03-01 | 2021-06-28 | 2021-03-01 | 2021-06-28
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAKH | SRG4 BATHROOM RENOVATION | 7 | CONSTRUCTION TO 75% | 2021-06-29 | 2021-10-26 | 2021-06-29 | 2021-10-26
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAKH | SRG4 BATHROOM RENOVATION | 8 | ORIGINAL EQUIP & FURNISHING | 2021-10-27 | 2022-01-24 | 2021-10-27 | 2022-01-24
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAKH | SRG4 BATHROOM RENOVATION | 9 | SUBSTANTIAL COMPLETION | 2022-01-25 | 2022-03-25 | 2022-01-25 | 2022-03-25
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAKH | SRG4 BATHROOM RENOVATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-26 | 2022-04-24 | 2022-03-26 | 2022-04-24
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO79-MED | MEDICAL DIVISION RELOCATION | 1 | DESIGN | 2020-07-30 | 2021-01-25 | 2020-07-30 | 2021-01-25
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO79-MED | MEDICAL DIVISION RELOCATION | 2 | BID AWARD AND REGISTER CONTRCT | 2021-01-26 | 2021-04-25 | 2021-01-26 | 2021-04-25
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO79-MED | MEDICAL DIVISION RELOCATION | 3 | CONSTRUCTION | 2021-04-26 | 2022-04-25 | 2021-04-26 | 2022-04-25
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO79-MED | MEDICAL DIVISION RELOCATION | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-04-26 | 2022-10-22 | 2022-04-26 | 2022-10-22
20201123 | QUEENS | 056 | POLICE DEPARTMENT | POD106COM | 106TH PCT - UPGRADE COMMUNITY ROOM | 1 | DEVELOP SCOPE | 2014-12-30 | 2015-03-29 | 2019-10-01 | 2019-12-29
20201123 | QUEENS | 056 | POLICE DEPARTMENT | POD106COM | 106TH PCT - UPGRADE COMMUNITY ROOM | 2 | PRELIMINARY DESIGN | 2015-03-30 | 2015-07-27 | 2019-12-30 | 2020-04-27
20201123 | QUEENS | 056 | POLICE DEPARTMENT | POD106COM | 106TH PCT - UPGRADE COMMUNITY ROOM | 3 | FINAL DESIGN | 2015-07-28 | 2015-11-24 | 2020-04-28 | 2020-08-25
20201123 | QUEENS | 056 | POLICE DEPARTMENT | POD106COM | 106TH PCT - UPGRADE COMMUNITY ROOM | 4 | BID AWARD AND REGISTER CONTRCT | 2015-11-25 | 2016-05-22 | 2020-08-26 | 2021-02-21
20201123 | QUEENS | 056 | POLICE DEPARTMENT | POD106COM | 106TH PCT - UPGRADE COMMUNITY ROOM | 5 | CONSTRUCTION TO 25% | 2016-05-23 | 2016-09-19 | 2021-02-22 | 2024-06-20
20201123 | QUEENS | 056 | POLICE DEPARTMENT | POD106COM | 106TH PCT - UPGRADE COMMUNITY ROOM | 6 | CONSTRUCTION TO 50% | 2016-09-20 | 2017-01-17 | 2024-06-21 | 2024-10-18
20201123 | QUEENS | 056 | POLICE DEPARTMENT | POD106COM | 106TH PCT - UPGRADE COMMUNITY ROOM | 7 | CONSTRUCTION TO 75% | 2017-01-18 | 2017-05-17 | 2024-10-19 | 2025-02-15
20201123 | QUEENS | 056 | POLICE DEPARTMENT | POD106COM | 106TH PCT - UPGRADE COMMUNITY ROOM | 8 | ORIGINAL EQUIP & FURNISHING | 2017-05-18 | 2017-08-15 | 2025-02-16 | 2025-05-16
20201123 | QUEENS | 056 | POLICE DEPARTMENT | POD106COM | 106TH PCT - UPGRADE COMMUNITY ROOM | 9 | SUBSTANTIAL COMPLETION | 2017-08-16 | 2017-10-14 | 2025-05-17 | 2025-07-15
20201123 | QUEENS | 056 | POLICE DEPARTMENT | POD106COM | 106TH PCT - UPGRADE COMMUNITY ROOM | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-10-15 | 2017-11-13 | 2025-07-16 | 2025-08-14
20201123 | QUEENS | 056 | POLICE DEPARTMENT | POD115PRK | Parking Lot - 115th Precinct | 1 | DESIGN | 2019-12-30 | 2020-06-26 | 2019-12-30 | 2020-06-26
20201123 | QUEENS | 056 | POLICE DEPARTMENT | POD115PRK | Parking Lot - 115th Precinct | 2 | BID AWARD AND REGISTER CONTRCT | 2020-06-27 | 2020-09-24 | 2020-06-27 | 2020-09-24
20201123 | QUEENS | 056 | POLICE DEPARTMENT | POD115PRK | Parking Lot - 115th Precinct | 3 | CONSTRUCTION | 2020-09-25 | 2021-09-24 | 2020-09-25 | 2021-09-24
20201123 | QUEENS | 056 | POLICE DEPARTMENT | POD115PRK | Parking Lot - 115th Precinct | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-25 | 2022-03-23 | 2021-09-25 | 2022-03-23
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO-Q106 | 106th Precinct Renovation | 1 | DESIGN | 2017-12-15 | 2018-06-12 | 2017-12-15 | 2018-06-12
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO-Q106 | 106th Precinct Renovation | 2 | BID AWARD AND REGISTER CONTRCT | 2018-06-13 | 2018-09-10 | 2018-06-13 | 2018-09-10
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO-Q106 | 106th Precinct Renovation | 3 | CONSTRUCTION | 2018-09-11 | 2019-09-10 | 2018-09-11 | 2019-09-10
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO-Q106 | 106th Precinct Renovation | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-11 | 2020-03-08 | 2019-09-11 | 2022-03-08
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO-Q107 | 107th Precinct Renovation | 1 | DESIGN | 2017-10-25 | 2018-04-22 | 2017-10-25 | 2018-04-22
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO-Q107 | 107th Precinct Renovation | 2 | BID AWARD AND REGISTER CONTRCT | 2018-04-23 | 2018-07-21 | 2018-04-23 | 2018-07-21
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO-Q107 | 107th Precinct Renovation | 3 | CONSTRUCTION | 2018-07-22 | 2019-07-21 | 2018-07-22 | 2019-07-21
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO-Q107 | 107th Precinct Renovation | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-07-22 | 2020-01-17 | 2019-07-22 | 2022-01-17
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO-Q109 | 109th Precinct Locker Room Upgrade | 1 | DEVELOP SCOPE | 2017-04-19 | 2017-07-17 | 2017-04-19 | 2017-07-17
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO-Q109 | 109th Precinct Locker Room Upgrade | 2 | PRELIMINARY DESIGN | 2017-07-18 | 2017-11-14 | 2017-07-18 | 2017-11-14
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO-Q109 | 109th Precinct Locker Room Upgrade | 3 | FINAL DESIGN | 2017-11-15 | 2018-05-13 | 2017-11-15 | 2018-05-13
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO-Q109 | 109th Precinct Locker Room Upgrade | 4 | BID AWARD AND REGISTER CONTRCT | 2018-05-14 | 2018-08-11 | 2018-05-14 | 2018-08-11
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO-Q109 | 109th Precinct Locker Room Upgrade | 5 | CONSTRUCTION TO 25% | 2018-08-12 | 2018-12-09 | 2018-08-12 | 2018-12-09
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO-Q109 | 109th Precinct Locker Room Upgrade | 6 | CONSTRUCTION TO 50% | 2018-12-10 | 2019-04-08 | 2018-12-10 | 2019-04-08
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO-Q109 | 109th Precinct Locker Room Upgrade | 7 | CONSTRUCTION TO 75% | 2019-04-09 | 2019-08-06 | 2019-04-09 | 2021-08-06
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO-Q109 | 109th Precinct Locker Room Upgrade | 8 | ORIGINAL EQUIP & FURNISHING | 2019-08-07 | 2019-11-04 | 2021-08-07 | 2021-11-04
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO-Q109 | 109th Precinct Locker Room Upgrade | 9 | SUBSTANTIAL COMPLETION | 2019-11-05 | 2020-01-03 | 2021-11-05 | 2022-01-03
20201123 | QUEENS | 056 | POLICE DEPARTMENT | PO-Q109 | 109th Precinct Locker Room Upgrade | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-01-04 | 2020-02-02 | 2022-01-04 | 2022-02-02
20201123 | QUEENS | 056 | POLICE DEPARTMENT | SANDCD08 | TRANSIT DISTRICT 23 ELECTRICAL | 1 | DEVELOP SCOPE | 2016-09-10 | 2016-12-08 | 2016-06-20 | 2016-09-17
20201123 | QUEENS | 056 | POLICE DEPARTMENT | SANDCD08 | TRANSIT DISTRICT 23 ELECTRICAL | 2 | PRELIMINARY DESIGN | 2016-12-09 | 2017-04-07 | 2016-09-18 | 2017-01-15
20201123 | QUEENS | 056 | POLICE DEPARTMENT | SANDCD08 | TRANSIT DISTRICT 23 ELECTRICAL | 3 | FINAL DESIGN | 2017-04-08 | 2017-08-05 | 2017-01-16 | 2017-05-15
20201123 | QUEENS | 056 | POLICE DEPARTMENT | SANDCD08 | TRANSIT DISTRICT 23 ELECTRICAL | 4 | BID AWARD AND REGISTER CONTRCT | 2017-08-06 | 2018-02-01 | 2017-05-16 | 2017-11-11
20201123 | QUEENS | 056 | POLICE DEPARTMENT | SANDCD08 | TRANSIT DISTRICT 23 ELECTRICAL | 5 | CONSTRUCTION TO 25% | 2018-02-02 | 2018-06-01 | 2017-11-12 | 2018-03-11
20201123 | QUEENS | 056 | POLICE DEPARTMENT | SANDCD08 | TRANSIT DISTRICT 23 ELECTRICAL | 6 | CONSTRUCTION TO 50% | 2018-06-02 | 2018-09-29 | 2018-03-12 | 2018-07-09
20201123 | QUEENS | 056 | POLICE DEPARTMENT | SANDCD08 | TRANSIT DISTRICT 23 ELECTRICAL | 7 | CONSTRUCTION TO 75% | 2018-09-30 | 2019-01-27 | 2018-07-10 | 2021-11-06
20201123 | QUEENS | 056 | POLICE DEPARTMENT | SANDCD08 | TRANSIT DISTRICT 23 ELECTRICAL | 8 | ORIGINAL EQUIP & FURNISHING | 2019-01-28 | 2019-04-27 | 2021-11-07 | 2022-02-04
20201123 | QUEENS | 056 | POLICE DEPARTMENT | SANDCD08 | TRANSIT DISTRICT 23 ELECTRICAL | 9 | SUBSTANTIAL COMPLETION | 2019-04-28 | 2019-06-26 | 2022-02-05 | 2022-04-05
20201123 | QUEENS | 056 | POLICE DEPARTMENT | SANDCD08 | TRANSIT DISTRICT 23 ELECTRICAL | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-06-27 | 2019-07-26 | 2022-04-06 | 2022-05-05
20201123 | QUEENS | 056 | POLICE DEPARTMENT | SANDCD10 | HARBOR GEORGE | 1 | DEVELOP SCOPE | 2016-09-10 | 2016-12-08 | 2016-06-10 | 2016-09-07
20201123 | QUEENS | 056 | POLICE DEPARTMENT | SANDCD10 | HARBOR GEORGE | 2 | PRELIMINARY DESIGN | 2016-12-09 | 2017-04-07 | 2016-09-08 | 2017-01-05
20201123 | QUEENS | 056 | POLICE DEPARTMENT | SANDCD10 | HARBOR GEORGE | 3 | FINAL DESIGN | 2017-04-08 | 2017-08-05 | 2017-01-06 | 2017-05-05
20201123 | QUEENS | 056 | POLICE DEPARTMENT | SANDCD10 | HARBOR GEORGE | 4 | BID AWARD AND REGISTER CONTRCT | 2017-08-06 | 2018-02-01 | 2017-05-06 | 2017-11-01
20201123 | QUEENS | 056 | POLICE DEPARTMENT | SANDCD10 | HARBOR GEORGE | 5 | CONSTRUCTION TO 25% | 2018-02-02 | 2018-06-01 | 2017-11-02 | 2018-03-01
20201123 | QUEENS | 056 | POLICE DEPARTMENT | SANDCD10 | HARBOR GEORGE | 6 | CONSTRUCTION TO 50% | 2018-06-02 | 2018-09-29 | 2018-03-02 | 2018-06-29
20201123 | QUEENS | 056 | POLICE DEPARTMENT | SANDCD10 | HARBOR GEORGE | 7 | CONSTRUCTION TO 75% | 2018-09-30 | 2019-01-27 | 2018-06-30 | 2021-10-27
20201123 | QUEENS | 056 | POLICE DEPARTMENT | SANDCD10 | HARBOR GEORGE | 8 | ORIGINAL EQUIP & FURNISHING | 2019-01-28 | 2019-04-27 | 2021-10-28 | 2022-01-25
20201123 | QUEENS | 056 | POLICE DEPARTMENT | SANDCD10 | HARBOR GEORGE | 9 | SUBSTANTIAL COMPLETION | 2019-04-28 | 2019-06-26 | 2022-01-26 | 2022-03-26
20201123 | QUEENS | 056 | POLICE DEPARTMENT | SANDCD10 | HARBOR GEORGE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-06-27 | 2019-07-26 | 2022-03-27 | 2022-04-25
20201123 | QUEENS | 057 | FIRE DEPARTMENT | ACEFDN702 | FDNY - LED LIGHTING UPGRADE AT FLEET SERVICES FACILITY 35ST | 1 | DEVELOP SCOPE | 2018-03-31 | 2018-06-28 | 2018-03-31 | 2018-06-28
20201123 | QUEENS | 057 | FIRE DEPARTMENT | ACEFDN702 | FDNY - LED LIGHTING UPGRADE AT FLEET SERVICES FACILITY 35ST | 2 | PRELIMINARY DESIGN | 2018-06-29 | 2018-10-26 | 2018-06-29 | 2018-10-26
20201123 | QUEENS | 057 | FIRE DEPARTMENT | ACEFDN702 | FDNY - LED LIGHTING UPGRADE AT FLEET SERVICES FACILITY 35ST | 3 | FINAL DESIGN | 2018-10-27 | 2019-04-24 | 2018-10-27 | 2019-04-24
20201123 | QUEENS | 057 | FIRE DEPARTMENT | ACEFDN702 | FDNY - LED LIGHTING UPGRADE AT FLEET SERVICES FACILITY 35ST | 4 | BID AWARD AND REGISTER CONTRCT | 2019-04-25 | 2019-07-23 | 2019-04-25 | 2019-07-23
20201123 | QUEENS | 057 | FIRE DEPARTMENT | ACEFDN702 | FDNY - LED LIGHTING UPGRADE AT FLEET SERVICES FACILITY 35ST | 5 | CONSTRUCTION TO 25% | 2019-07-24 | 2019-11-20 | 2019-07-24 | 2019-11-20
20201123 | QUEENS | 057 | FIRE DEPARTMENT | ACEFDN702 | FDNY - LED LIGHTING UPGRADE AT FLEET SERVICES FACILITY 35ST | 6 | CONSTRUCTION TO 50% | 2019-11-21 | 2020-03-19 | 2019-11-21 | 2020-03-19
20201123 | QUEENS | 057 | FIRE DEPARTMENT | ACEFDN702 | FDNY - LED LIGHTING UPGRADE AT FLEET SERVICES FACILITY 35ST | 7 | CONSTRUCTION TO 75% | 2020-03-20 | 2020-07-17 | 2020-03-20 | 2020-07-17
20201123 | QUEENS | 057 | FIRE DEPARTMENT | ACEFDN702 | FDNY - LED LIGHTING UPGRADE AT FLEET SERVICES FACILITY 35ST | 8 | ORIGINAL EQUIP & FURNISHING | 2020-07-18 | 2020-10-15 | 2020-07-18 | 2020-10-15
20201123 | QUEENS | 057 | FIRE DEPARTMENT | ACEFDN702 | FDNY - LED LIGHTING UPGRADE AT FLEET SERVICES FACILITY 35ST | 9 | SUBSTANTIAL COMPLETION | 2020-10-16 | 2020-12-14 | 2020-10-16 | 2020-12-14
20201123 | QUEENS | 057 | FIRE DEPARTMENT | ACEFDN702 | FDNY - LED LIGHTING UPGRADE AT FLEET SERVICES FACILITY 35ST | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-12-15 | 2021-01-13 | 2020-12-15 | 2021-01-13
20201123 | QUEENS | 057 | FIRE DEPARTMENT | ACEFDN704 | FDNY - DESIGN & INSTALLATION OF 97 KW SOLAR SYSTEMS AT EMS45 | 1 | DEVELOP SCOPE | 2017-11-30 | 2018-02-27 | 2017-11-30 | 2018-02-27
20201123 | QUEENS | 057 | FIRE DEPARTMENT | ACEFDN704 | FDNY - DESIGN & INSTALLATION OF 97 KW SOLAR SYSTEMS AT EMS45 | 2 | PRELIMINARY DESIGN | 2018-02-28 | 2018-06-27 | 2018-02-28 | 2018-06-27
20201123 | QUEENS | 057 | FIRE DEPARTMENT | ACEFDN704 | FDNY - DESIGN & INSTALLATION OF 97 KW SOLAR SYSTEMS AT EMS45 | 3 | FINAL DESIGN | 2018-06-28 | 2018-12-24 | 2018-06-28 | 2018-12-24
20201123 | QUEENS | 057 | FIRE DEPARTMENT | ACEFDN704 | FDNY - DESIGN & INSTALLATION OF 97 KW SOLAR SYSTEMS AT EMS45 | 4 | BID AWARD AND REGISTER CONTRCT | 2018-12-25 | 2019-03-24 | 2018-12-25 | 2019-03-24
20201123 | QUEENS | 057 | FIRE DEPARTMENT | ACEFDN704 | FDNY - DESIGN & INSTALLATION OF 97 KW SOLAR SYSTEMS AT EMS45 | 5 | CONSTRUCTION TO 25% | 2019-03-25 | 2019-07-22 | 2019-03-25 | 2019-07-22
20201123 | QUEENS | 057 | FIRE DEPARTMENT | ACEFDN704 | FDNY - DESIGN & INSTALLATION OF 97 KW SOLAR SYSTEMS AT EMS45 | 6 | CONSTRUCTION TO 50% | 2019-07-23 | 2019-11-19 | 2019-07-23 | 2019-11-19
20201123 | QUEENS | 057 | FIRE DEPARTMENT | ACEFDN704 | FDNY - DESIGN & INSTALLATION OF 97 KW SOLAR SYSTEMS AT EMS45 | 7 | CONSTRUCTION TO 75% | 2019-11-20 | 2020-03-18 | 2019-11-20 | 2020-03-18
20201123 | QUEENS | 057 | FIRE DEPARTMENT | ACEFDN704 | FDNY - DESIGN & INSTALLATION OF 97 KW SOLAR SYSTEMS AT EMS45 | 8 | ORIGINAL EQUIP & FURNISHING | 2020-03-19 | 2020-06-16 | 2020-03-19 | 2020-06-16
20201123 | QUEENS | 057 | FIRE DEPARTMENT | ACEFDN704 | FDNY - DESIGN & INSTALLATION OF 97 KW SOLAR SYSTEMS AT EMS45 | 9 | SUBSTANTIAL COMPLETION | 2020-06-17 | 2020-08-15 | 2020-06-17 | 2020-08-15
20201123 | QUEENS | 057 | FIRE DEPARTMENT | ACEFDN704 | FDNY - DESIGN & INSTALLATION OF 97 KW SOLAR SYSTEMS AT EMS45 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-08-16 | 2020-09-14 | 2020-08-16 | 2020-09-14
20201123 | QUEENS | 057 | FIRE DEPARTMENT | ACEFDN802 | FDNY - Lighting upgrades at 15 buildings at FDNY center | 1 | DEVELOP SCOPE | 2018-10-01 | 2018-12-29 | 2018-10-01 | 2018-12-29
20201123 | QUEENS | 057 | FIRE DEPARTMENT | ACEFDN802 | FDNY - Lighting upgrades at 15 buildings at FDNY center | 2 | PRELIMINARY DESIGN | 2018-12-30 | 2019-04-28 | 2018-12-30 | 2019-04-28
20201123 | QUEENS | 057 | FIRE DEPARTMENT | ACEFDN802 | FDNY - Lighting upgrades at 15 buildings at FDNY center | 3 | FINAL DESIGN | 2019-04-29 | 2019-10-25 | 2019-04-29 | 2019-10-25
20201123 | QUEENS | 057 | FIRE DEPARTMENT | ACEFDN802 | FDNY - Lighting upgrades at 15 buildings at FDNY center | 4 | BID AWARD AND REGISTER CONTRCT | 2019-10-26 | 2020-01-23 | 2019-10-26 | 2020-01-23
20201123 | QUEENS | 057 | FIRE DEPARTMENT | ACEFDN802 | FDNY - Lighting upgrades at 15 buildings at FDNY center | 5 | CONSTRUCTION TO 25% | 2020-01-24 | 2020-05-22 | 2020-01-24 | 2020-05-22
20201123 | QUEENS | 057 | FIRE DEPARTMENT | ACEFDN802 | FDNY - Lighting upgrades at 15 buildings at FDNY center | 6 | CONSTRUCTION TO 50% | 2020-05-23 | 2020-09-19 | 2020-05-23 | 2020-09-19
20201123 | QUEENS | 057 | FIRE DEPARTMENT | ACEFDN802 | FDNY - Lighting upgrades at 15 buildings at FDNY center | 7 | CONSTRUCTION TO 75% | 2020-09-20 | 2021-01-17 | 2020-09-20 | 2021-01-17
20201123 | QUEENS | 057 | FIRE DEPARTMENT | ACEFDN802 | FDNY - Lighting upgrades at 15 buildings at FDNY center | 8 | ORIGINAL EQUIP & FURNISHING | 2021-01-18 | 2021-04-17 | 2021-01-18 | 2021-04-17
20201123 | QUEENS | 057 | FIRE DEPARTMENT | ACEFDN802 | FDNY - Lighting upgrades at 15 buildings at FDNY center | 9 | SUBSTANTIAL COMPLETION | 2021-04-18 | 2021-06-16 | 2021-04-18 | 2021-06-16
20201123 | QUEENS | 057 | FIRE DEPARTMENT | ACEFDN802 | FDNY - Lighting upgrades at 15 buildings at FDNY center | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-06-17 | 2021-07-16 | 2021-06-17 | 2021-07-16
20201123 | QUEENS | 057 | FIRE DEPARTMENT | F175FMHVC | FLEET MAINTENANCE HVAC SYSTEM UPGRADE | 1 | CONSTRUCTION | 2017-06-13 | 2018-06-12 | 2018-06-13 | 2019-06-12
20201123 | QUEENS | 057 | FIRE DEPARTMENT | F175FMHVC | FLEET MAINTENANCE HVAC SYSTEM UPGRADE | 2 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-06-13 | 2018-09-10 | 2019-06-13 | 2022-01-27
20201123 | QUEENS | 057 | FIRE DEPARTMENT | F175MC266 | Multi-Component Renovations - EC266 | 1 | DESIGN | 2019-01-15 | 2019-04-14 | 2019-01-15 | 2019-04-14
20201123 | QUEENS | 057 | FIRE DEPARTMENT | F175MC266 | Multi-Component Renovations - EC266 | 2 | BID AWARD AND REGISTER CONTRCT | 2019-04-15 | 2020-01-09 | 2019-04-15 | 2020-01-09
20201123 | QUEENS | 057 | FIRE DEPARTMENT | F175MC266 | Multi-Component Renovations - EC266 | 3 | CONSTRUCTION | 2020-01-10 | 2021-02-12 | 2020-01-10 | 2021-02-12
20201123 | QUEENS | 057 | FIRE DEPARTMENT | F175MC266 | Multi-Component Renovations - EC266 | 4 | ORIGINAL EQUIP & FURNISHING | 2021-02-13 | 2021-03-29 | 2021-02-13 | 2021-03-29
20201123 | QUEENS | 057 | FIRE DEPARTMENT | F175MC266 | Multi-Component Renovations - EC266 | 5 | SUBSTANTIAL COMPLETION | 2021-03-30 | 2021-05-08 | 2021-03-30 | 2021-05-08
20201123 | QUEENS | 057 | FIRE DEPARTMENT | F175MC266 | Multi-Component Renovations - EC266 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-05-09 | 2021-07-07 | 2021-05-09 | 2021-07-07
20201123 | QUEENS | 057 | FIRE DEPARTMENT | F175MC304 | Multi-Component Renovations - EC304 | 1 | DESIGN | 2018-10-12 | 2019-01-09 | 2018-10-12 | 2019-01-09
20201123 | QUEENS | 057 | FIRE DEPARTMENT | F175MC304 | Multi-Component Renovations - EC304 | 2 | BID AWARD AND REGISTER CONTRCT | 2019-01-10 | 2019-10-06 | 2019-01-10 | 2019-10-06
20201123 | QUEENS | 057 | FIRE DEPARTMENT | F175MC304 | Multi-Component Renovations - EC304 | 3 | CONSTRUCTION | 2019-10-07 | 2020-11-09 | 2019-10-07 | 2020-11-09
20201123 | QUEENS | 057 | FIRE DEPARTMENT | F175MC304 | Multi-Component Renovations - EC304 | 4 | ORIGINAL EQUIP & FURNISHING | 2020-11-10 | 2020-12-24 | 2020-11-10 | 2020-12-24
20201123 | QUEENS | 057 | FIRE DEPARTMENT | F175MC304 | Multi-Component Renovations - EC304 | 5 | SUBSTANTIAL COMPLETION | 2020-12-25 | 2021-02-02 | 2020-12-25 | 2021-02-02
20201123 | QUEENS | 057 | FIRE DEPARTMENT | F175MC304 | Multi-Component Renovations - EC304 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-02-03 | 2021-04-03 | 2021-02-03 | 2023-10-03
20201123 | QUEENS | 057 | FIRE DEPARTMENT | F175MC307 | Multi-Component Renovations - EC307 | 1 | DESIGN | 2018-10-19 | 2019-01-16 | 2021-09-15 | 2021-12-13
20201123 | QUEENS | 057 | FIRE DEPARTMENT | F175MC307 | Multi-Component Renovations - EC307 | 2 | BID AWARD AND REGISTER CONTRCT | 2019-01-17 | 2019-10-13 | 2021-12-14 | 2022-09-09
20201123 | QUEENS | 057 | FIRE DEPARTMENT | F175MC307 | Multi-Component Renovations - EC307 | 3 | CONSTRUCTION | 2019-10-14 | 2020-11-16 | 2022-09-10 | 2023-10-14
20201123 | QUEENS | 057 | FIRE DEPARTMENT | F175MC307 | Multi-Component Renovations - EC307 | 4 | ORIGINAL EQUIP & FURNISHING | 2020-11-17 | 2020-12-31 | 2023-10-15 | 2023-11-28
20201123 | QUEENS | 057 | FIRE DEPARTMENT | F175MC307 | Multi-Component Renovations - EC307 | 5 | SUBSTANTIAL COMPLETION | 2021-01-01 | 2021-02-09 | 2021-01-01 | 2021-02-09
20201123 | QUEENS | 057 | FIRE DEPARTMENT | F175MC307 | Multi-Component Renovations - EC307 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-02-10 | 2021-04-10 | 2021-02-10 | 2021-04-10
20201123 | QUEENS | 057 | FIRE DEPARTMENT | F175WN266 | WINDOW REPLACEMENT - EC266 | 1 | DESIGN | 2019-01-15 | 2019-07-13 | 2020-01-15 | 2020-07-12
20201123 | QUEENS | 057 | FIRE DEPARTMENT | F175WN266 | WINDOW REPLACEMENT - EC266 | 2 | CONSTRUCTION | 2019-07-14 | 2020-07-12 | 2020-07-13 | 2021-07-12
20201123 | QUEENS | 057 | FIRE DEPARTMENT | F175WN266 | WINDOW REPLACEMENT - EC266 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-07-13 | 2020-10-10 | 2021-07-13 | 2021-10-10
20201123 | QUEENS | 057 | FIRE DEPARTMENT | F175WN329 | WINDOW REPLACEMENT - EC329 | 1 | CONSTRUCTION | 2019-10-03 | 2020-10-01 | 2020-10-02 | 2021-10-01
20201123 | QUEENS | 057 | FIRE DEPARTMENT | F175WN329 | WINDOW REPLACEMENT - EC329 | 2 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-10-02 | 2020-12-30 | 2021-10-02 | 2021-12-30
20201123 | QUEENS | 057 | FIRE DEPARTMENT | F175WP301 | Waterproofing - EC301 | 1 | DESIGN | 2018-10-16 | 2019-04-13 | 2019-10-16 | 2020-04-12
20201123 | QUEENS | 057 | FIRE DEPARTMENT | F175WP301 | Waterproofing - EC301 | 2 | CONSTRUCTION | 2019-04-14 | 2020-04-12 | 2020-04-13 | 2021-04-12
20201123 | QUEENS | 057 | FIRE DEPARTMENT | F175WP301 | Waterproofing - EC301 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-04-13 | 2020-07-11 | 2021-04-13 | 2021-07-11
20201123 | QUEENS | 057 | FIRE DEPARTMENT | F175WP303 | Waterproofing - EC303 | 1 | DESIGN | 2018-10-16 | 2019-04-13 | 2019-10-16 | 2020-04-12
20201123 | QUEENS | 057 | FIRE DEPARTMENT | F175WP303 | Waterproofing - EC303 | 2 | CONSTRUCTION | 2019-04-14 | 2020-04-12 | 2020-04-13 | 2021-04-12
20201123 | QUEENS | 057 | FIRE DEPARTMENT | F175WP303 | Waterproofing - EC303 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-04-13 | 2020-07-11 | 2021-04-13 | 2021-07-11
20201123 | QUEENS | 057 | FIRE DEPARTMENT | F175WP325 | Roofing and Waterproofing - EC325 | 1 | CONSTRUCTION | 2019-09-30 | 2020-09-28 | 2020-09-29 | 2021-09-28
20201123 | QUEENS | 057 | FIRE DEPARTMENT | F175WP325 | Roofing and Waterproofing - EC325 | 2 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-29 | 2020-12-27 | 2021-09-29 | 2021-12-27
20201123 | QUEENS | 057 | FIRE DEPARTMENT | F1WOODSID | Unmanned Telemetry - Woodside | 1 | DESIGN | 2019-10-24 | 2020-04-20 | 2019-10-24 | 2020-04-20
20201123 | QUEENS | 057 | FIRE DEPARTMENT | F1WOODSID | Unmanned Telemetry - Woodside | 2 | CONSTRUCTION | 2020-04-21 | 2021-04-20 | 2020-04-21 | 2021-04-20
20201123 | QUEENS | 057 | FIRE DEPARTMENT | F1WOODSID | Unmanned Telemetry - Woodside | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-04-21 | 2021-07-19 | 2021-04-21 | 2021-07-19
20201123 | QUEENS | 057 | FIRE DEPARTMENT | FD175D262 | Door Replacement - EC262 | 1 | DESIGN | 2018-09-15 | 2019-03-13 | 2020-04-02 | 2020-09-28
20201123 | QUEENS | 057 | FIRE DEPARTMENT | FD175D262 | Door Replacement - EC262 | 2 | CONSTRUCTION | 2019-03-14 | 2020-03-12 | 2020-09-29 | 2021-09-28
20201123 | QUEENS | 057 | FIRE DEPARTMENT | FD175D262 | Door Replacement - EC262 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-03-13 | 2020-06-10 | 2021-09-29 | 2021-12-27
20201123 | QUEENS | 057 | FIRE DEPARTMENT | FD175D287 | DOOR REPLACEMENT - EC287 | 1 | DESIGN | 2018-09-15 | 2019-03-13 | 2019-04-04 | 2019-09-30
20201123 | QUEENS | 057 | FIRE DEPARTMENT | FD175D287 | DOOR REPLACEMENT - EC287 | 2 | CONSTRUCTION | 2019-03-14 | 2020-03-12 | 2019-10-01 | 2020-09-29
20201123 | QUEENS | 057 | FIRE DEPARTMENT | FD175D287 | DOOR REPLACEMENT - EC287 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-03-13 | 2020-06-10 | 2020-09-30 | 2020-12-28
20201123 | QUEENS | 057 | FIRE DEPARTMENT | FD175D291 | Door Replacement - EC291 | 2 | CONSTRUCTION | 2019-03-14 | 2020-03-12 | 2020-09-30 | 2021-09-29
20201123 | QUEENS | 057 | FIRE DEPARTMENT | FD175D291 | Door Replacement - EC291 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-03-13 | 2020-06-10 | 2021-09-30 | 2021-12-28
20201123 | QUEENS | 057 | FIRE DEPARTMENT | FD175D316 | Door Replacement - EC316 | 1 | CONSTRUCTION | 2020-06-30 | 2021-06-29 | 2020-06-30 | 2021-06-29
20201123 | QUEENS | 057 | FIRE DEPARTMENT | FD175D316 | Door Replacement - EC316 | 2 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-06-30 | 2021-09-27 | 2021-06-30 | 2021-09-27
20201123 | QUEENS | 057 | FIRE DEPARTMENT | FD175D324 | Door Replacement - EC324 | 1 | DESIGN | 2018-09-15 | 2019-03-13 | 2020-04-03 | 2020-09-29
20201123 | QUEENS | 057 | FIRE DEPARTMENT | FD175D324 | Door Replacement - EC324 | 2 | CONSTRUCTION | 2019-03-14 | 2020-03-12 | 2020-09-30 | 2021-09-29
20201123 | QUEENS | 057 | FIRE DEPARTMENT | FD175D324 | Door Replacement - EC324 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-03-13 | 2020-06-10 | 2021-09-30 | 2021-12-28
20201123 | QUEENS | 057 | FIRE DEPARTMENT | FD175G289 | Generator - EC289 | 1 | DESIGN | 2019-01-15 | 2019-07-13 | 2020-01-15 | 2020-07-12
20201123 | QUEENS | 057 | FIRE DEPARTMENT | FD175G289 | Generator - EC289 | 2 | CONSTRUCTION | 2019-07-14 | 2020-07-12 | 2020-07-13 | 2021-07-12
20201123 | QUEENS | 057 | FIRE DEPARTMENT | FD175G289 | Generator - EC289 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-07-13 | 2020-10-10 | 2021-07-13 | 2021-10-10
20201123 | QUEENS | 057 | FIRE DEPARTMENT | FD175W316 | Window Replacement - EC316 | 1 | CONSTRUCTION | 2020-06-30 | 2021-06-29 | 2020-06-30 | 2021-06-29
20201123 | QUEENS | 057 | FIRE DEPARTMENT | FD175W316 | Window Replacement - EC316 | 2 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-06-30 | 2021-09-27 | 2021-06-30 | 2021-09-27
20201123 | QUEENS | 057 | FIRE DEPARTMENT | FQ175G260 | Generator - EC260 | 1 | DESIGN | 2019-10-25 | 2020-04-21 | 2019-10-25 | 2020-04-21
20201123 | QUEENS | 057 | FIRE DEPARTMENT | FQ175G260 | Generator - EC260 | 2 | CONSTRUCTION | 2020-04-22 | 2021-04-21 | 2020-04-22 | 2021-04-21
20201123 | QUEENS | 057 | FIRE DEPARTMENT | FQ175G260 | Generator - EC260 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-04-22 | 2021-07-20 | 2021-04-22 | 2021-07-20
20201123 | QUEENS | 057 | FIRE DEPARTMENT | FQ175K307 | KITCHEN RENOVATION - EC307 | 1 | DESIGN | 2018-06-01 | 2018-11-27 | 2021-01-03 | 2021-07-01
20201123 | QUEENS | 057 | FIRE DEPARTMENT | FQ175K307 | KITCHEN RENOVATION - EC307 | 2 | CONSTRUCTION | 2018-11-28 | 2019-11-27 | 2021-07-02 | 2022-07-01
20201123 | QUEENS | 057 | FIRE DEPARTMENT | FQ175K307 | KITCHEN RENOVATION - EC307 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-11-28 | 2020-02-25 | 2022-07-02 | 2022-09-29
20201123 | QUEENS | 057 | FIRE DEPARTMENT | FQ175W275 | Window Replacement EC275 | 1 | CONSTRUCTION | 2018-04-01 | 2019-03-31 | 2018-04-22 | 2022-09-30
20201123 | QUEENS | 057 | FIRE DEPARTMENT | FQ175W275 | Window Replacement EC275 | 2 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-04-01 | 2019-06-29 | 2022-10-01 | 2022-12-29
20201123 | QUEENS | 057 | FIRE DEPARTMENT | FQ175WASH | REPLACEMENT OF WASHERS AND DRYERS | 1 | DESIGN | 2020-07-01 | 2020-12-27 | 2020-07-01 | 2020-12-27
20201123 | QUEENS | 057 | FIRE DEPARTMENT | FQ175WASH | REPLACEMENT OF WASHERS AND DRYERS | 2 | CONSTRUCTION | 2020-12-28 | 2021-12-27 | 2020-12-28 | 2021-12-27
20201123 | QUEENS | 057 | FIRE DEPARTMENT | FQ175WASH | REPLACEMENT OF WASHERS AND DRYERS | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-12-28 | 2022-03-27 | 2021-12-28 | 2022-03-27
20201123 | QUEENS | 071 | DEPT OF HOMELESS SERVICES | ACEDHS801 | DHS - Gas fired condensing hot water systems | 1 | DESIGN | 2021-05-30 | 2022-02-23 | 2021-05-30 | 2022-02-23
20201123 | QUEENS | 071 | DEPT OF HOMELESS SERVICES | ACEDHS801 | DHS - Gas fired condensing hot water systems | 2 | BID AWARD AND REGISTER CONTRCT | 2022-02-24 | 2022-08-22 | 2022-02-24 | 2022-08-22
20201123 | QUEENS | 071 | DEPT OF HOMELESS SERVICES | ACEDHS801 | DHS - Gas fired condensing hot water systems | 3 | CONSTRUCTION | 2022-08-23 | 2027-05-28 | 2022-08-23 | 2027-05-28
20201123 | QUEENS | 071 | DEPT OF HOMELESS SERVICES | HH112BARS | Shelter at 21-10 Borden Avenue, 11110 - Roof/Skylight Replac | 1 | DESIGN | 2019-01-01 | 2019-09-27 | 2019-01-01 | 2019-09-27
20201123 | QUEENS | 071 | DEPT OF HOMELESS SERVICES | HH112BARS | Shelter at 21-10 Borden Avenue, 11110 - Roof/Skylight Replac | 2 | BID AWARD AND REGISTER CONTRCT | 2019-09-28 | 2020-03-25 | 2019-09-28 | 2020-03-25
20201123 | QUEENS | 071 | DEPT OF HOMELESS SERVICES | HH112BARS | Shelter at 21-10 Borden Avenue, 11110 - Roof/Skylight Replac | 3 | CONSTRUCTION | 2020-03-26 | 2024-12-29 | 2020-03-26 | 2024-12-29
20201123 | QUEENS | 071 | DEPT OF HOMELESS SERVICES | HH112BOFW | Borden Avenue Flood Mitigation | 1 | DESIGN | 2019-01-01 | 2019-09-27 | 2019-01-01 | 2019-09-27
20201123 | QUEENS | 071 | DEPT OF HOMELESS SERVICES | HH112BOFW | Borden Avenue Flood Mitigation | 2 | BID AWARD AND REGISTER CONTRCT | 2019-09-28 | 2020-03-25 | 2019-09-28 | 2020-03-25
20201123 | QUEENS | 071 | DEPT OF HOMELESS SERVICES | HH112BOFW | Borden Avenue Flood Mitigation | 3 | CONSTRUCTION | 2020-03-26 | 2024-12-29 | 2020-03-26 | 2024-12-29
20201123 | QUEENS | 071 | DEPT OF HOMELESS SERVICES | HH115BWRF | BRIARWOOD FAMILY RESIDENCE - ROOF AND FACADE UPGRADE | 1 | DESIGN | 2019-01-01 | 2019-09-27 | 2019-01-01 | 2019-09-27
20201123 | QUEENS | 071 | DEPT OF HOMELESS SERVICES | HH115BWRF | BRIARWOOD FAMILY RESIDENCE - ROOF AND FACADE UPGRADE | 2 | BID AWARD AND REGISTER CONTRCT | 2019-09-28 | 2020-03-25 | 2019-09-28 | 2020-03-25
20201123 | QUEENS | 071 | DEPT OF HOMELESS SERVICES | HH115BWRF | BRIARWOOD FAMILY RESIDENCE - ROOF AND FACADE UPGRADE | 3 | CONSTRUCTION | 2020-03-26 | 2024-12-29 | 2020-03-26 | 2024-12-29
20201123 | QUEENS | 071 | DEPT OF HOMELESS SERVICES | HH115JAEX | JAMAICA FAMILY EXTERIOR | 1 | DESIGN | 2020-01-01 | 2020-09-26 | 2020-01-01 | 2020-09-26
20201123 | QUEENS | 071 | DEPT OF HOMELESS SERVICES | HH115JAEX | JAMAICA FAMILY EXTERIOR | 2 | BID AWARD AND REGISTER CONTRCT | 2020-09-27 | 2021-03-25 | 2020-09-27 | 2021-03-25
20201123 | QUEENS | 071 | DEPT OF HOMELESS SERVICES | HH115JAEX | JAMAICA FAMILY EXTERIOR | 3 | CONSTRUCTION | 2021-03-26 | 2025-12-29 | 2021-03-26 | 2025-12-29
20201123 | QUEENS | 071 | DEPT OF HOMELESS SERVICES | HH115SINT | SPRINGFIELD BLD FACADE RECONSTRUCTION | 1 | DESIGN | 2022-05-30 | 2023-02-23 | 2022-05-30 | 2023-02-23
20201123 | QUEENS | 071 | DEPT OF HOMELESS SERVICES | HH115SINT | SPRINGFIELD BLD FACADE RECONSTRUCTION | 2 | BID AWARD AND REGISTER CONTRCT | 2023-02-24 | 2023-08-22 | 2023-02-24 | 2023-08-22
20201123 | QUEENS | 071 | DEPT OF HOMELESS SERVICES | HH115SINT | SPRINGFIELD BLD FACADE RECONSTRUCTION | 3 | CONSTRUCTION | 2023-08-23 | 2028-05-27 | 2023-08-23 | 2028-05-27
20201123 | QUEENS | 071 | DEPT OF HOMELESS SERVICES | HH115SMEP | SPRINGFIELD BLD BOILER RECONSTRUCTION | 1 | DESIGN | 2021-05-30 | 2022-02-23 | 2021-05-30 | 2022-02-23
20201123 | QUEENS | 071 | DEPT OF HOMELESS SERVICES | HH115SMEP | SPRINGFIELD BLD BOILER RECONSTRUCTION | 2 | BID AWARD AND REGISTER CONTRCT | 2022-02-24 | 2022-08-22 | 2022-02-24 | 2022-08-22
20201123 | QUEENS | 071 | DEPT OF HOMELESS SERVICES | HH115SMEP | SPRINGFIELD BLD BOILER RECONSTRUCTION | 3 | CONSTRUCTION | 2022-08-23 | 2027-05-28 | 2022-08-23 | 2027-05-28
20201123 | QUEENS | 071 | DEPT OF HOMELESS SERVICES | SOLARDHS2 | Solar PV system at Borden Avenue facility | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-06-30 | 2020-06-01 | 2020-06-30
20201123 | QUEENS | 071 | DEPT OF HOMELESS SERVICES | SOLARDHS2 | Solar PV system at Borden Avenue facility | 2 | BID AWARD AND REGISTER CONTRCT | 2020-07-01 | 2020-08-29 | 2020-07-01 | 2020-08-29
20201123 | QUEENS | 071 | DEPT OF HOMELESS SERVICES | SOLARDHS2 | Solar PV system at Borden Avenue facility | 3 | CONSTRUCTION TO 50% | 2020-08-30 | 2021-02-25 | 2020-08-30 | 2021-02-25
20201123 | QUEENS | 071 | DEPT OF HOMELESS SERVICES | SOLARDHS2 | Solar PV system at Borden Avenue facility | 4 | CONSTRUCTION TO 75% | 2021-02-26 | 2021-05-26 | 2021-02-26 | 2021-05-26
20201123 | QUEENS | 071 | DEPT OF HOMELESS SERVICES | SOLARDHS2 | Solar PV system at Borden Avenue facility | 5 | SUBSTANTIAL COMPLETION | 2021-05-27 | 2021-07-25 | 2021-05-27 | 2021-07-25
20201123 | QUEENS | 071 | DEPT OF HOMELESS SERVICES | SOLARDHS2 | Solar PV system at Borden Avenue facility | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-07-26 | 2021-08-24 | 2021-07-26 | 2021-08-24
20201123 | QUEENS | 072 | DEPARTMENT OF CORRECTION | C101-SEC | PERIMETER SECURITY & CAMERA REPLACEMENT | 1 | DEVELOP SCOPE | 2020-06-30 | 2020-09-27 | 2020-06-30 | 2020-09-27
20201123 | QUEENS | 072 | DEPARTMENT OF CORRECTION | C101-SEC | PERIMETER SECURITY & CAMERA REPLACEMENT | 2 | PRELIMINARY DESIGN | 2020-09-28 | 2021-01-25 | 2020-09-28 | 2021-01-25
20201123 | QUEENS | 072 | DEPARTMENT OF CORRECTION | C101-SEC | PERIMETER SECURITY & CAMERA REPLACEMENT | 3 | FINAL DESIGN | 2021-01-26 | 2021-07-24 | 2021-01-26 | 2021-07-24
20201123 | QUEENS | 072 | DEPARTMENT OF CORRECTION | C101-SEC | PERIMETER SECURITY & CAMERA REPLACEMENT | 4 | BID AWARD AND REGISTER CONTRCT | 2021-07-25 | 2021-10-22 | 2021-07-25 | 2021-10-22
20201123 | QUEENS | 072 | DEPARTMENT OF CORRECTION | C101-SEC | PERIMETER SECURITY & CAMERA REPLACEMENT | 5 | CONSTRUCTION TO 25% | 2021-10-23 | 2022-02-19 | 2021-10-23 | 2022-02-19
20201123 | QUEENS | 072 | DEPARTMENT OF CORRECTION | C101-SEC | PERIMETER SECURITY & CAMERA REPLACEMENT | 6 | CONSTRUCTION TO 50% | 2022-02-20 | 2022-06-19 | 2022-02-20 | 2022-06-19
20201123 | QUEENS | 072 | DEPARTMENT OF CORRECTION | C101-SEC | PERIMETER SECURITY & CAMERA REPLACEMENT | 7 | CONSTRUCTION TO 75% | 2022-06-20 | 2022-10-17 | 2022-06-20 | 2022-10-17
20201123 | QUEENS | 072 | DEPARTMENT OF CORRECTION | C101-SEC | PERIMETER SECURITY & CAMERA REPLACEMENT | 8 | ORIGINAL EQUIP & FURNISHING | 2022-10-18 | 2023-01-15 | 2022-10-18 | 2023-01-15
20201123 | QUEENS | 072 | DEPARTMENT OF CORRECTION | C101-SEC | PERIMETER SECURITY & CAMERA REPLACEMENT | 9 | SUBSTANTIAL COMPLETION | 2023-01-16 | 2023-03-16 | 2023-01-16 | 2023-03-16
20201123 | QUEENS | 072 | DEPARTMENT OF CORRECTION | C101-SEC | PERIMETER SECURITY & CAMERA REPLACEMENT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-03-17 | 2023-04-15 | 2023-03-17 | 2023-04-15
20201123 | QUEENS | 072 | DEPARTMENT OF CORRECTION | C75SEWR | RECONSTRUCTION OF RI SEWER LINES | 1 | DEVELOP SCOPE | 2012-07-01 | 2012-09-28 | 2013-08-17 | 2013-11-14
20201123 | QUEENS | 072 | DEPARTMENT OF CORRECTION | C75SEWR | RECONSTRUCTION OF RI SEWER LINES | 2 | PRELIMINARY DESIGN | 2012-09-29 | 2013-01-26 | 2013-11-15 | 2014-03-14
20201123 | QUEENS | 072 | DEPARTMENT OF CORRECTION | C75SEWR | RECONSTRUCTION OF RI SEWER LINES | 3 | FINAL DESIGN | 2013-01-27 | 2013-07-25 | 2014-03-15 | 2014-09-10
20201123 | QUEENS | 072 | DEPARTMENT OF CORRECTION | C75SEWR | RECONSTRUCTION OF RI SEWER LINES | 4 | BID AWARD AND REGISTER CONTRCT | 2013-07-26 | 2013-10-23 | 2014-09-11 | 2014-12-09
20201123 | QUEENS | 072 | DEPARTMENT OF CORRECTION | C75SEWR | RECONSTRUCTION OF RI SEWER LINES | 5 | CONSTRUCTION TO 25% | 2013-10-24 | 2014-02-20 | 2014-12-10 | 2015-04-08
20201123 | QUEENS | 072 | DEPARTMENT OF CORRECTION | C75SEWR | RECONSTRUCTION OF RI SEWER LINES | 6 | CONSTRUCTION TO 50% | 2014-02-21 | 2014-06-20 | 2015-04-09 | 2015-08-06
20201123 | QUEENS | 072 | DEPARTMENT OF CORRECTION | C75SEWR | RECONSTRUCTION OF RI SEWER LINES | 7 | CONSTRUCTION TO 75% | 2014-06-21 | 2014-10-18 | 2015-08-07 | 2015-12-04
20201123 | QUEENS | 072 | DEPARTMENT OF CORRECTION | C75SEWR | RECONSTRUCTION OF RI SEWER LINES | 8 | ORIGINAL EQUIP & FURNISHING | 2014-10-19 | 2015-01-16 | 2015-12-05 | 2016-03-03
20201123 | QUEENS | 072 | DEPARTMENT OF CORRECTION | C75SEWR | RECONSTRUCTION OF RI SEWER LINES | 9 | SUBSTANTIAL COMPLETION | 2015-01-17 | 2015-03-17 | 2016-03-04 | 2016-05-02
20201123 | QUEENS | 072 | DEPARTMENT OF CORRECTION | C75SEWR | RECONSTRUCTION OF RI SEWER LINES | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-18 | 2015-04-16 | 2016-05-03 | 2023-06-30
20201123 | QUEENS | 096 | HUMAN RESOURCES ADMINISTRATION | HRCNSJMS2 | South Jamaica MSC renovation. | 1 | DESIGN | 2014-06-01 | 2014-11-27 | 2019-07-01 | 2019-12-27
20201123 | QUEENS | 096 | HUMAN RESOURCES ADMINISTRATION | HRCNSJMS2 | South Jamaica MSC renovation. | 2 | CONSTRUCTION | 2014-11-28 | 2015-05-26 | 2019-12-28 | 2020-06-24
20201123 | QUEENS | 096 | HUMAN RESOURCES ADMINISTRATION | HRCNSJMSC | South Jamaica MSC renovation | 1 | DESIGN | 2014-06-01 | 2014-11-27 | 2019-07-01 | 2019-12-27
20201123 | QUEENS | 096 | HUMAN RESOURCES ADMINISTRATION | HRCNSJMSC | South Jamaica MSC renovation | 2 | CONSTRUCTION | 2014-11-28 | 2015-05-26 | 2019-12-28 | 2020-06-24
20201123 | QUEENS | 125 | DEPARTMENT FOR THE AGING | AGWOODRE1 | Woodside houses new gym for the elderly | 1 | DESIGN | 2015-06-01 | 2015-11-27 | 2015-06-01 | 2015-11-27
20201123 | QUEENS | 125 | DEPARTMENT FOR THE AGING | AGWOODRE1 | Woodside houses new gym for the elderly | 2 | BID AWARD AND REGISTER CONTRCT | 2015-11-28 | 2016-02-25 | 2015-11-28 | 2016-02-25
20201123 | QUEENS | 125 | DEPARTMENT FOR THE AGING | AGWOODRE1 | Woodside houses new gym for the elderly | 3 | CONSTRUCTION | 2016-02-26 | 2017-02-24 | 2016-02-26 | 2017-02-24
20201123 | QUEENS | 125 | DEPARTMENT FOR THE AGING | AGWOODRE1 | Woodside houses new gym for the elderly | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-02-25 | 2017-08-23 | 2017-02-25 | 2017-08-23
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV040BTH1 | FTH - Flushing Town Hall - Bathroom Renovations HLD | 1 | DEVELOP SCOPE | 2021-06-30 | 2021-09-27 | 2021-06-30 | 2021-09-27
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV040BTH1 | FTH - Flushing Town Hall - Bathroom Renovations HLD | 2 | PRELIMINARY DESIGN | 2021-09-28 | 2022-01-25 | 2021-09-28 | 2022-01-25
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV040BTH1 | FTH - Flushing Town Hall - Bathroom Renovations HLD | 3 | FINAL DESIGN | 2022-01-26 | 2022-07-24 | 2022-01-26 | 2022-07-24
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV040BTH1 | FTH - Flushing Town Hall - Bathroom Renovations HLD | 4 | BID AWARD AND REGISTER CONTRCT | 2022-07-25 | 2022-10-22 | 2022-07-25 | 2022-10-22
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV040BTH1 | FTH - Flushing Town Hall - Bathroom Renovations HLD | 5 | CONSTRUCTION TO 25% | 2022-10-23 | 2023-02-19 | 2022-10-23 | 2023-02-19
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV040BTH1 | FTH - Flushing Town Hall - Bathroom Renovations HLD | 6 | CONSTRUCTION TO 50% | 2023-02-20 | 2023-06-19 | 2023-02-20 | 2023-06-19
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV040BTH1 | FTH - Flushing Town Hall - Bathroom Renovations HLD | 7 | CONSTRUCTION TO 75% | 2023-06-20 | 2023-10-17 | 2023-06-20 | 2023-10-17
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV040BTH1 | FTH - Flushing Town Hall - Bathroom Renovations HLD | 8 | ORIGINAL EQUIP & FURNISHING | 2023-10-18 | 2024-01-15 | 2023-10-18 | 2024-01-15
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV040BTH1 | FTH - Flushing Town Hall - Bathroom Renovations HLD | 9 | SUBSTANTIAL COMPLETION | 2024-01-16 | 2024-03-15 | 2024-01-16 | 2024-03-15
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV040BTH1 | FTH - Flushing Town Hall - Bathroom Renovations HLD | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-03-16 | 2024-04-14 | 2024-03-16 | 2024-04-14
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV050CYLT | MMI - Courtyard Lighting | 1 | DEVELOP SCOPE | 2018-04-01 | 2019-06-30 | 2018-04-01 | 2019-06-30
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV050CYLT | MMI - Courtyard Lighting | 2 | PRELIMINARY DESIGN | 2019-07-01 | 2019-10-28 | 2019-07-01 | 2019-10-28
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV050CYLT | MMI - Courtyard Lighting | 3 | FINAL DESIGN | 2019-10-29 | 2020-04-25 | 2019-10-29 | 2020-04-25
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV050CYLT | MMI - Courtyard Lighting | 4 | BID AWARD AND REGISTER CONTRCT | 2020-04-26 | 2020-07-24 | 2020-04-26 | 2020-07-24
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV050CYLT | MMI - Courtyard Lighting | 5 | CONSTRUCTION TO 25% | 2020-07-25 | 2020-11-21 | 2020-07-25 | 2020-11-21
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV050CYLT | MMI - Courtyard Lighting | 6 | CONSTRUCTION TO 50% | 2020-11-22 | 2021-03-21 | 2020-11-22 | 2021-03-21
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV050CYLT | MMI - Courtyard Lighting | 7 | CONSTRUCTION TO 75% | 2021-03-22 | 2021-07-19 | 2021-03-22 | 2021-07-19
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV050CYLT | MMI - Courtyard Lighting | 8 | ORIGINAL EQUIP & FURNISHING | 2021-07-20 | 2021-10-17 | 2021-07-20 | 2021-10-17
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV050CYLT | MMI - Courtyard Lighting | 9 | SUBSTANTIAL COMPLETION | 2021-10-18 | 2021-12-16 | 2021-10-18 | 2021-12-16
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV050CYLT | MMI - Courtyard Lighting | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-12-17 | 2022-01-15 | 2021-12-17 | 2022-01-15
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV050ENTR | MMI - Upgrades to Building Entrance | 1 | CONSTRUCTION | 2021-09-28 | 2022-09-22 | 2021-06-30 | 2021-09-27
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV050ENTR | MMI - Upgrades to Building Entrance | 2 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-17 | 2021-09-28 | 2022-09-22
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV050ENTR | MMI - Upgrades to Building Entrance | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-17 | 2022-09-23 | 2023-09-17
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV050MECH | MMI - Mechanical Systems Upgrade | 1 | CONSTRUCTION | 2021-09-28 | 2022-09-22 | 2021-06-30 | 2021-09-27
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV050MECH | MMI - Mechanical Systems Upgrade | 2 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-17 | 2021-09-28 | 2022-09-22
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV050MECH | MMI - Mechanical Systems Upgrade | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-17 | 2022-09-23 | 2023-09-17
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV272KIDS | QBG - Kids Culture Garden Exhibit | 1 | DEVELOP SCOPE | 2023-07-31 | 2023-10-28 | 2023-06-30 | 2023-09-27
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV272KIDS | QBG - Kids Culture Garden Exhibit | 2 | BID AWARD AND REGISTER CONTRCT | 2023-10-29 | 2024-01-26 | 2023-09-28 | 2023-12-26
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV272KIDS | QBG - Kids Culture Garden Exhibit | 3 | CONSTRUCTION TO 50% | 2024-01-27 | 2024-05-25 | 2023-12-27 | 2024-04-24
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV272KIDS | QBG - Kids Culture Garden Exhibit | 4 | CONSTRUCTION TO 75% | 2024-05-26 | 2024-07-24 | 2024-04-25 | 2024-06-23
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV272KIDS | QBG - Kids Culture Garden Exhibit | 5 | SUBSTANTIAL COMPLETION | 2024-07-25 | 2024-09-22 | 2024-06-24 | 2024-08-22
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV272KIDS | QBG - Kids Culture Garden Exhibit | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-09-23 | 2024-10-22 | 2024-08-23 | 2024-09-21
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV274-AH2 | NYHOS - New York Hall of Science - Air Handlers Replacement | 1 | DEVELOP SCOPE | 2022-06-30 | 2022-09-27 | 2022-06-30 | 2022-09-27
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV274-AH2 | NYHOS - New York Hall of Science - Air Handlers Replacement | 2 | PRELIMINARY DESIGN | 2022-09-28 | 2023-01-25 | 2022-09-28 | 2023-01-25
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV274-AH2 | NYHOS - New York Hall of Science - Air Handlers Replacement | 3 | FINAL DESIGN | 2023-01-26 | 2023-07-24 | 2023-01-26 | 2023-07-24
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV274-AH2 | NYHOS - New York Hall of Science - Air Handlers Replacement | 4 | BID AWARD AND REGISTER CONTRCT | 2023-07-25 | 2023-10-22 | 2023-07-25 | 2023-10-22
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV274-AH2 | NYHOS - New York Hall of Science - Air Handlers Replacement | 5 | CONSTRUCTION TO 25% | 2023-10-23 | 2024-02-19 | 2023-10-23 | 2024-02-19
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV274-AH2 | NYHOS - New York Hall of Science - Air Handlers Replacement | 6 | CONSTRUCTION TO 50% | 2024-02-20 | 2024-06-18 | 2024-02-20 | 2024-06-18
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV274-AH2 | NYHOS - New York Hall of Science - Air Handlers Replacement | 7 | CONSTRUCTION TO 75% | 2024-06-19 | 2024-10-16 | 2024-06-19 | 2024-10-16
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV274-AH2 | NYHOS - New York Hall of Science - Air Handlers Replacement | 8 | ORIGINAL EQUIP & FURNISHING | 2024-10-17 | 2025-01-14 | 2024-10-17 | 2025-01-14
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV274-AH2 | NYHOS - New York Hall of Science - Air Handlers Replacement | 9 | SUBSTANTIAL COMPLETION | 2025-01-15 | 2025-03-15 | 2025-01-15 | 2025-03-15
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV274-AH2 | NYHOS - New York Hall of Science - Air Handlers Replacement | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-03-16 | 2025-04-14 | 2025-03-16 | 2025-04-14
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV274ELV2 | NYHOS - New York Hall of Science - Elevator | 1 | DEVELOP SCOPE | 2020-06-30 | 2020-09-27 | 2020-06-30 | 2020-09-27
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV274ELV2 | NYHOS - New York Hall of Science - Elevator | 2 | PRELIMINARY DESIGN | 2020-09-28 | 2021-01-25 | 2020-09-28 | 2021-01-25
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV274ELV2 | NYHOS - New York Hall of Science - Elevator | 3 | FINAL DESIGN | 2021-01-26 | 2021-07-24 | 2021-01-26 | 2021-07-24
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV274ELV2 | NYHOS - New York Hall of Science - Elevator | 4 | BID AWARD AND REGISTER CONTRCT | 2021-07-25 | 2021-10-22 | 2021-07-25 | 2021-10-22
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV274ELV2 | NYHOS - New York Hall of Science - Elevator | 5 | CONSTRUCTION TO 25% | 2021-10-23 | 2022-02-19 | 2021-10-23 | 2022-02-19
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV274ELV2 | NYHOS - New York Hall of Science - Elevator | 6 | CONSTRUCTION TO 50% | 2022-02-20 | 2022-06-19 | 2022-02-20 | 2022-06-19
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV274ELV2 | NYHOS - New York Hall of Science - Elevator | 7 | CONSTRUCTION TO 75% | 2022-06-20 | 2022-10-17 | 2022-06-20 | 2022-10-17
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV274ELV2 | NYHOS - New York Hall of Science - Elevator | 8 | ORIGINAL EQUIP & FURNISHING | 2022-10-18 | 2023-01-15 | 2022-10-18 | 2023-01-15
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV274ELV2 | NYHOS - New York Hall of Science - Elevator | 9 | SUBSTANTIAL COMPLETION | 2023-01-16 | 2023-03-16 | 2023-01-16 | 2023-03-16
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV274ELV2 | NYHOS - New York Hall of Science - Elevator | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-03-17 | 2023-04-15 | 2023-03-17 | 2023-04-15
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV274PERI | NYHOS - New York Hall of Science, Perimeter Landscaping | 1 | DEVELOP SCOPE | 2022-06-30 | 2022-09-27 | 2022-06-30 | 2022-09-27
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV274PERI | NYHOS - New York Hall of Science, Perimeter Landscaping | 2 | PRELIMINARY DESIGN | 2022-09-28 | 2023-01-25 | 2022-09-28 | 2023-01-25
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV274PERI | NYHOS - New York Hall of Science, Perimeter Landscaping | 3 | FINAL DESIGN | 2023-01-26 | 2023-07-24 | 2023-01-26 | 2023-07-24
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV274PERI | NYHOS - New York Hall of Science, Perimeter Landscaping | 4 | BID AWARD AND REGISTER CONTRCT | 2023-07-25 | 2023-10-22 | 2023-07-25 | 2023-10-22
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV274PERI | NYHOS - New York Hall of Science, Perimeter Landscaping | 5 | CONSTRUCTION TO 25% | 2023-10-23 | 2024-02-19 | 2023-10-23 | 2024-02-19
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV274PERI | NYHOS - New York Hall of Science, Perimeter Landscaping | 6 | CONSTRUCTION TO 50% | 2024-02-20 | 2024-06-18 | 2024-02-20 | 2024-06-18
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV274PERI | NYHOS - New York Hall of Science, Perimeter Landscaping | 7 | CONSTRUCTION TO 75% | 2024-06-19 | 2024-10-16 | 2024-06-19 | 2024-10-16
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV274PERI | NYHOS - New York Hall of Science, Perimeter Landscaping | 8 | ORIGINAL EQUIP & FURNISHING | 2024-10-17 | 2025-01-14 | 2024-10-17 | 2025-01-14
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV274PERI | NYHOS - New York Hall of Science, Perimeter Landscaping | 9 | SUBSTANTIAL COMPLETION | 2025-01-15 | 2025-03-15 | 2025-01-15 | 2025-03-15
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV274PERI | NYHOS - New York Hall of Science, Perimeter Landscaping | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-03-16 | 2025-04-14 | 2025-03-16 | 2025-04-14
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV466BOIL | QTIP - Queens Theater in the Park Boiler | 1 | DEVELOP SCOPE | 2022-06-30 | 2022-09-27 | 2021-06-01 | 2021-08-29
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV466BOIL | QTIP - Queens Theater in the Park Boiler | 2 | PRELIMINARY DESIGN | 2022-09-28 | 2023-01-25 | 2021-08-30 | 2021-12-27
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV466BOIL | QTIP - Queens Theater in the Park Boiler | 3 | FINAL DESIGN | 2023-01-26 | 2023-07-24 | 2021-12-28 | 2022-06-25
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV466BOIL | QTIP - Queens Theater in the Park Boiler | 4 | BID AWARD AND REGISTER CONTRCT | 2023-07-25 | 2023-10-22 | 2022-06-26 | 2022-09-23
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV466BOIL | QTIP - Queens Theater in the Park Boiler | 5 | CONSTRUCTION TO 25% | 2023-10-23 | 2024-02-19 | 2022-09-24 | 2023-01-21
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV466BOIL | QTIP - Queens Theater in the Park Boiler | 6 | CONSTRUCTION TO 50% | 2024-02-20 | 2024-06-18 | 2023-01-22 | 2023-05-21
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV466BOIL | QTIP - Queens Theater in the Park Boiler | 7 | CONSTRUCTION TO 75% | 2024-06-19 | 2024-10-16 | 2023-05-22 | 2023-09-18
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV466BOIL | QTIP - Queens Theater in the Park Boiler | 8 | ORIGINAL EQUIP & FURNISHING | 2024-10-17 | 2025-01-14 | 2023-09-19 | 2023-12-17
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV466BOIL | QTIP - Queens Theater in the Park Boiler | 9 | SUBSTANTIAL COMPLETION | 2025-01-15 | 2025-03-15 | 2023-12-18 | 2024-02-15
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV466BOIL | QTIP - Queens Theater in the Park Boiler | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-03-16 | 2025-04-14 | 2024-02-16 | 2024-03-16
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV466QTP | QTIP - Queens Theater in the Park Shulman Theatre Renovation | 1 | DEVELOP SCOPE | 2020-06-30 | 2020-09-27 | 2020-06-30 | 2020-09-27
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV466QTP | QTIP - Queens Theater in the Park Shulman Theatre Renovation | 2 | PRELIMINARY DESIGN | 2020-09-28 | 2021-01-25 | 2020-09-28 | 2021-01-25
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV466QTP | QTIP - Queens Theater in the Park Shulman Theatre Renovation | 3 | FINAL DESIGN | 2021-01-26 | 2021-07-24 | 2021-01-26 | 2021-07-24
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV466QTP | QTIP - Queens Theater in the Park Shulman Theatre Renovation | 4 | BID AWARD AND REGISTER CONTRCT | 2021-07-25 | 2021-10-22 | 2021-07-25 | 2021-10-22
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV466QTP | QTIP - Queens Theater in the Park Shulman Theatre Renovation | 5 | CONSTRUCTION TO 25% | 2021-10-23 | 2022-02-19 | 2021-10-23 | 2022-02-19
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV466QTP | QTIP - Queens Theater in the Park Shulman Theatre Renovation | 6 | CONSTRUCTION TO 50% | 2022-02-20 | 2022-06-19 | 2022-02-20 | 2022-06-19
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV466QTP | QTIP - Queens Theater in the Park Shulman Theatre Renovation | 7 | CONSTRUCTION TO 75% | 2022-06-20 | 2022-10-17 | 2022-06-20 | 2022-10-17
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV466QTP | QTIP - Queens Theater in the Park Shulman Theatre Renovation | 8 | ORIGINAL EQUIP & FURNISHING | 2022-10-18 | 2023-01-15 | 2022-10-18 | 2023-01-15
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV466QTP | QTIP - Queens Theater in the Park Shulman Theatre Renovation | 9 | SUBSTANTIAL COMPLETION | 2023-01-16 | 2023-03-16 | 2023-01-16 | 2023-03-16
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV466QTP | QTIP - Queens Theater in the Park Shulman Theatre Renovation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-03-17 | 2023-04-15 | 2023-03-17 | 2023-04-15
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501ATTC | PS1 - Attic Renovation for Studios | 1 | DEVELOP SCOPE | 2016-06-15 | 2016-09-12 | 2021-06-30 | 2021-09-27
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501ATTC | PS1 - Attic Renovation for Studios | 2 | PRELIMINARY DESIGN | 2016-09-13 | 2017-01-10 | 2021-09-28 | 2022-01-25
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501ATTC | PS1 - Attic Renovation for Studios | 3 | FINAL DESIGN | 2017-01-11 | 2017-07-09 | 2022-01-26 | 2022-07-24
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501ATTC | PS1 - Attic Renovation for Studios | 4 | BID AWARD AND REGISTER CONTRCT | 2017-07-10 | 2017-10-07 | 2022-07-25 | 2022-10-22
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501ATTC | PS1 - Attic Renovation for Studios | 5 | CONSTRUCTION TO 25% | 2017-10-08 | 2018-02-04 | 2022-10-23 | 2023-02-19
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501ATTC | PS1 - Attic Renovation for Studios | 6 | CONSTRUCTION TO 50% | 2018-02-05 | 2018-06-04 | 2023-02-20 | 2023-06-19
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501ATTC | PS1 - Attic Renovation for Studios | 7 | CONSTRUCTION TO 75% | 2018-06-05 | 2018-10-02 | 2023-06-20 | 2023-10-17
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501ATTC | PS1 - Attic Renovation for Studios | 8 | ORIGINAL EQUIP & FURNISHING | 2018-10-03 | 2018-12-31 | 2023-10-18 | 2024-01-15
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501ATTC | PS1 - Attic Renovation for Studios | 9 | SUBSTANTIAL COMPLETION | 2019-01-01 | 2019-03-01 | 2019-01-01 | 2019-03-01
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501ATTC | PS1 - Attic Renovation for Studios | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-03-02 | 2019-03-31 | 2019-03-02 | 2019-03-31
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501ELEV | PS1 - Elevator Renovation | 1 | DEVELOP SCOPE | 2019-06-15 | 2019-09-12 | 2019-06-15 | 2019-09-12
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501ELEV | PS1 - Elevator Renovation | 2 | PRELIMINARY DESIGN | 2019-09-13 | 2020-01-10 | 2019-09-13 | 2020-01-10
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501ELEV | PS1 - Elevator Renovation | 3 | FINAL DESIGN | 2020-01-11 | 2020-07-08 | 2020-01-11 | 2020-07-08
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501ELEV | PS1 - Elevator Renovation | 4 | BID AWARD AND REGISTER CONTRCT | 2020-07-09 | 2020-10-06 | 2020-07-09 | 2020-10-06
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501ELEV | PS1 - Elevator Renovation | 5 | CONSTRUCTION TO 25% | 2020-10-07 | 2021-02-03 | 2020-10-07 | 2021-02-03
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501ELEV | PS1 - Elevator Renovation | 6 | CONSTRUCTION TO 50% | 2021-02-04 | 2021-06-03 | 2021-02-04 | 2021-06-03
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501ELEV | PS1 - Elevator Renovation | 7 | CONSTRUCTION TO 75% | 2021-06-04 | 2021-10-01 | 2021-06-04 | 2021-10-01
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501ELEV | PS1 - Elevator Renovation | 8 | ORIGINAL EQUIP & FURNISHING | 2021-10-02 | 2021-12-30 | 2021-10-02 | 2021-12-30
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501ELEV | PS1 - Elevator Renovation | 9 | SUBSTANTIAL COMPLETION | 2021-12-31 | 2022-02-28 | 2021-12-31 | 2022-02-28
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501ELEV | PS1 - Elevator Renovation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-01 | 2022-03-30 | 2022-03-01 | 2022-03-30
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501-PS1 | PS1 - Acquisition for studio and gallery space | 1 | DEVELOP SCOPE | 2016-06-30 | 2016-09-27 | 2022-06-30 | 2022-09-27
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501-PS1 | PS1 - Acquisition for studio and gallery space | 2 | PRELIMINARY DESIGN | 2016-09-28 | 2017-01-25 | 2022-09-28 | 2023-01-25
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501-PS1 | PS1 - Acquisition for studio and gallery space | 3 | FINAL DESIGN | 2017-01-26 | 2017-07-24 | 2023-01-26 | 2023-07-24
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501-PS1 | PS1 - Acquisition for studio and gallery space | 4 | BID AWARD AND REGISTER CONTRCT | 2017-07-25 | 2017-10-22 | 2023-07-25 | 2023-10-22
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501-PS1 | PS1 - Acquisition for studio and gallery space | 5 | CONSTRUCTION TO 25% | 2017-10-23 | 2018-02-19 | 2023-10-23 | 2024-02-19
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501-PS1 | PS1 - Acquisition for studio and gallery space | 6 | CONSTRUCTION TO 50% | 2018-02-20 | 2018-06-19 | 2024-02-20 | 2024-06-18
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501-PS1 | PS1 - Acquisition for studio and gallery space | 7 | CONSTRUCTION TO 75% | 2018-06-20 | 2018-10-17 | 2024-06-19 | 2024-10-16
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501-PS1 | PS1 - Acquisition for studio and gallery space | 8 | ORIGINAL EQUIP & FURNISHING | 2018-10-18 | 2019-01-15 | 2024-10-17 | 2025-01-14
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501-PS1 | PS1 - Acquisition for studio and gallery space | 9 | SUBSTANTIAL COMPLETION | 2019-01-16 | 2019-03-16 | 2025-01-15 | 2025-03-15
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501-PS1 | PS1 - Acquisition for studio and gallery space | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-03-17 | 2019-04-15 | 2025-03-16 | 2025-04-14
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501ROOF | PS1 - Renovation of PS1 Roof Areas PH 2 | 1 | DEVELOP SCOPE | 2023-06-30 | 2023-09-27 | 2022-06-29 | 2022-09-26
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501ROOF | PS1 - Renovation of PS1 Roof Areas PH 2 | 2 | PRELIMINARY DESIGN | 2023-09-28 | 2024-01-25 | 2022-09-27 | 2023-01-24
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501ROOF | PS1 - Renovation of PS1 Roof Areas PH 2 | 3 | FINAL DESIGN | 2024-01-26 | 2024-07-23 | 2023-01-25 | 2023-07-23
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501ROOF | PS1 - Renovation of PS1 Roof Areas PH 2 | 4 | BID AWARD AND REGISTER CONTRCT | 2024-07-24 | 2024-10-21 | 2023-07-24 | 2023-10-21
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501ROOF | PS1 - Renovation of PS1 Roof Areas PH 2 | 5 | CONSTRUCTION TO 25% | 2024-10-22 | 2025-02-18 | 2023-10-22 | 2024-02-18
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501ROOF | PS1 - Renovation of PS1 Roof Areas PH 2 | 6 | CONSTRUCTION TO 50% | 2025-02-19 | 2025-06-18 | 2024-02-19 | 2024-06-17
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501ROOF | PS1 - Renovation of PS1 Roof Areas PH 2 | 7 | CONSTRUCTION TO 75% | 2025-06-19 | 2025-10-16 | 2024-06-18 | 2024-10-15
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501ROOF | PS1 - Renovation of PS1 Roof Areas PH 2 | 8 | ORIGINAL EQUIP & FURNISHING | 2025-10-17 | 2026-01-14 | 2024-10-16 | 2025-01-13
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501ROOF | PS1 - Renovation of PS1 Roof Areas PH 2 | 9 | SUBSTANTIAL COMPLETION | 2026-01-15 | 2026-03-15 | 2025-01-14 | 2025-03-14
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501ROOF | PS1 - Renovation of PS1 Roof Areas PH 2 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2026-03-16 | 2026-04-14 | 2025-03-15 | 2025-04-13
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV502ELEV | JCAL - Elevator Reconstruction/Modernization Section | 1 | DEVELOP SCOPE | 2020-06-30 | 2020-09-27 | 2020-06-30 | 2020-09-27
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV502ELEV | JCAL - Elevator Reconstruction/Modernization Section | 2 | PRELIMINARY DESIGN | 2020-09-28 | 2021-01-25 | 2020-09-28 | 2021-01-25
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV502ELEV | JCAL - Elevator Reconstruction/Modernization Section | 3 | FINAL DESIGN | 2021-01-26 | 2021-07-24 | 2021-01-26 | 2021-07-24
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV502ELEV | JCAL - Elevator Reconstruction/Modernization Section | 4 | BID AWARD AND REGISTER CONTRCT | 2021-07-25 | 2021-10-22 | 2021-07-25 | 2021-10-22
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV502ELEV | JCAL - Elevator Reconstruction/Modernization Section | 5 | CONSTRUCTION TO 25% | 2021-10-23 | 2022-02-19 | 2021-10-23 | 2022-02-19
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV502ELEV | JCAL - Elevator Reconstruction/Modernization Section | 6 | CONSTRUCTION TO 50% | 2022-02-20 | 2022-06-19 | 2022-02-20 | 2022-06-19
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV502ELEV | JCAL - Elevator Reconstruction/Modernization Section | 7 | CONSTRUCTION TO 75% | 2022-06-20 | 2022-10-17 | 2022-06-20 | 2022-10-17
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV502ELEV | JCAL - Elevator Reconstruction/Modernization Section | 8 | ORIGINAL EQUIP & FURNISHING | 2022-10-18 | 2023-01-15 | 2022-10-18 | 2023-01-15
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV502ELEV | JCAL - Elevator Reconstruction/Modernization Section | 9 | SUBSTANTIAL COMPLETION | 2023-01-16 | 2023-03-16 | 2023-01-16 | 2023-03-16
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV502ELEV | JCAL - Elevator Reconstruction/Modernization Section | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-03-17 | 2023-04-15 | 2023-03-17 | 2023-04-15
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV502-SDW | JCAL - JPAC Outdoor Performance Space & Sidewals | 1 | DEVELOP SCOPE | 2021-06-30 | 2021-09-27 | 2021-06-30 | 2021-09-27
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV502-SDW | JCAL - JPAC Outdoor Performance Space & Sidewals | 2 | PRELIMINARY DESIGN | 2021-09-28 | 2022-01-25 | 2021-09-28 | 2022-01-25
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV502-SDW | JCAL - JPAC Outdoor Performance Space & Sidewals | 3 | FINAL DESIGN | 2022-01-26 | 2022-07-24 | 2022-01-26 | 2022-07-24
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV502-SDW | JCAL - JPAC Outdoor Performance Space & Sidewals | 4 | BID AWARD AND REGISTER CONTRCT | 2022-07-25 | 2022-10-22 | 2022-07-25 | 2022-10-22
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV502-SDW | JCAL - JPAC Outdoor Performance Space & Sidewals | 5 | CONSTRUCTION TO 25% | 2022-10-23 | 2023-02-19 | 2022-10-23 | 2023-02-19
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV502-SDW | JCAL - JPAC Outdoor Performance Space & Sidewals | 6 | CONSTRUCTION TO 50% | 2023-02-20 | 2023-06-19 | 2023-02-20 | 2023-06-19
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV502-SDW | JCAL - JPAC Outdoor Performance Space & Sidewals | 7 | CONSTRUCTION TO 75% | 2023-06-20 | 2023-10-17 | 2023-06-20 | 2023-10-17
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV502-SDW | JCAL - JPAC Outdoor Performance Space & Sidewals | 8 | ORIGINAL EQUIP & FURNISHING | 2023-10-18 | 2024-01-15 | 2023-10-18 | 2024-01-15
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV502-SDW | JCAL - JPAC Outdoor Performance Space & Sidewals | 9 | SUBSTANTIAL COMPLETION | 2024-01-16 | 2024-03-15 | 2024-01-16 | 2024-03-15
20201123 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV502-SDW | JCAL - JPAC Outdoor Performance Space & Sidewals | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-03-16 | 2024-04-14 | 2024-03-16 | 2024-04-14
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | BEACH20 | Beach 20th St. Plaza Improvements | 1 | DESIGN | 2010-01-01 | 2011-01-20 | 2013-01-01 | 2014-01-20
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | BEACH20 | Beach 20th St. Plaza Improvements | 2 | BID AWARD AND REGISTER CONTRCT | 2011-01-21 | 2011-01-20 | 2014-01-21 | 2014-01-20
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | BEACH20 | Beach 20th St. Plaza Improvements | 3 | CONSTRUCTION | 2011-01-21 | 2013-01-20 | 2014-01-21 | 2016-01-21
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | BEACH20 | Beach 20th St. Plaza Improvements | 4 | ORIGINAL EQUIP & FURNISHING | 2013-01-21 | 2013-01-20 | 2016-01-22 | 2016-01-21
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | BEACH20 | Beach 20th St. Plaza Improvements | 5 | SUBSTANTIAL COMPLETION | 2013-01-21 | 2013-01-20 | 2016-01-22 | 2016-01-21
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | BEACH20 | Beach 20th St. Plaza Improvements | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-01-21 | 2013-01-25 | 2016-01-22 | 2029-06-30
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | COLPJFK | JFK Site A (COLLEGE POINT Relocation) | 1 | DESIGN | 2009-01-01 | 2010-01-01 | 2009-01-01 | 2010-01-01
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | COLPJFK | JFK Site A (COLLEGE POINT Relocation) | 2 | BID AWARD AND REGISTER CONTRCT | 2010-01-02 | 2010-01-01 | 2010-01-02 | 2010-01-01
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | COLPJFK | JFK Site A (COLLEGE POINT Relocation) | 3 | CONSTRUCTION | 2010-01-02 | 2011-01-01 | 2010-01-02 | 2022-06-30
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | COLPJFK | JFK Site A (COLLEGE POINT Relocation) | 4 | ORIGINAL EQUIP & FURNISHING | 2011-01-02 | 2011-01-01 | 2022-07-01 | 2022-06-30
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | COLPJFK | JFK Site A (COLLEGE POINT Relocation) | 5 | SUBSTANTIAL COMPLETION | 2011-01-02 | 2011-01-01 | 2022-07-01 | 2022-06-30
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | COLPJFK | JFK Site A (COLLEGE POINT Relocation) | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2011-01-02 | 2011-01-06 | 2022-07-01 | 2029-06-28
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | COLUMBPL | Columbus Plaza | 1 | DESIGN | 2010-01-01 | 2011-01-20 | 2010-01-01 | 2011-01-20
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | COLUMBPL | Columbus Plaza | 2 | BID AWARD AND REGISTER CONTRCT | 2011-01-21 | 2011-01-20 | 2011-01-21 | 2011-01-20
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | COLUMBPL | Columbus Plaza | 3 | CONSTRUCTION | 2011-01-21 | 2013-01-20 | 2011-01-21 | 2013-01-20
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | COLUMBPL | Columbus Plaza | 4 | ORIGINAL EQUIP & FURNISHING | 2013-01-21 | 2013-01-20 | 2013-01-21 | 2013-01-20
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | COLUMBPL | Columbus Plaza | 5 | SUBSTANTIAL COMPLETION | 2013-01-21 | 2013-01-20 | 2013-01-21 | 2013-01-20
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | COLUMBPL | Columbus Plaza | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-01-21 | 2013-01-25 | 2013-01-21 | 2029-06-30
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | CPCDRAIN | College Point - Drainage Rehab | 1 | DESIGN | 2005-01-01 | 2005-01-20 | 2006-11-01 | 2007-02-01
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | CPCDRAIN | College Point - Drainage Rehab | 2 | BID AWARD AND REGISTER CONTRCT | 2005-01-21 | 2005-02-04 | 2007-02-02 | 2007-02-01
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | CPCDRAIN | College Point - Drainage Rehab | 3 | CONSTRUCTION | 2005-02-05 | 2007-06-30 | 2007-04-01 | 2020-06-30
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | CPCDRAIN | College Point - Drainage Rehab | 4 | ORIGINAL EQUIP & FURNISHING | 2007-07-01 | 2007-06-30 | 2020-07-01 | 2020-06-30
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | CPCDRAIN | College Point - Drainage Rehab | 5 | SUBSTANTIAL COMPLETION | 2007-07-01 | 2007-06-30 | 2020-07-01 | 2020-06-30
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | CPCDRAIN | College Point - Drainage Rehab | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2007-07-01 | 2007-07-05 | 2020-07-01 | 2026-07-05
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | ECODOCKHC | ECO-DOCK AT HALLETS COVE | 1 | DESIGN | 2016-01-01 | 2018-06-30 | 2016-01-01 | 2018-06-30
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | ECODOCKHC | ECO-DOCK AT HALLETS COVE | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-01 | 2018-06-30 | 2018-07-01 | 2018-06-30
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | ECODOCKHC | ECO-DOCK AT HALLETS COVE | 3 | CONSTRUCTION | 2018-07-01 | 2021-06-30 | 2018-07-01 | 2021-06-30
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | ECODOCKHC | ECO-DOCK AT HALLETS COVE | 4 | ORIGINAL EQUIP & FURNISHING | 2021-07-01 | 2021-06-30 | 2021-07-01 | 2021-06-30
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | ECODOCKHC | ECO-DOCK AT HALLETS COVE | 5 | SUBSTANTIAL COMPLETION | 2021-07-01 | 2021-06-30 | 2021-07-01 | 2021-06-30
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | ECODOCKHC | ECO-DOCK AT HALLETS COVE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-07-01 | 2021-07-05 | 2021-07-01 | 2021-07-05
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | FABARGEHP | FA Barge Replacement - Hunters Point South 5307 | 1 | DESIGN | 2016-07-01 | 2016-07-20 | 2018-07-01 | 2018-07-20
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | FABARGEHP | FA Barge Replacement - Hunters Point South 5307 | 2 | BID AWARD AND REGISTER CONTRCT | 2016-07-21 | 2016-08-04 | 2018-07-21 | 2018-08-04
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | FABARGEHP | FA Barge Replacement - Hunters Point South 5307 | 3 | CONSTRUCTION | 2016-08-05 | 2016-09-08 | 2018-08-05 | 2018-09-08
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | FABARGEHP | FA Barge Replacement - Hunters Point South 5307 | 4 | ORIGINAL EQUIP & FURNISHING | 2016-09-09 | 2016-09-18 | 2018-09-09 | 2018-09-18
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | FABARGEHP | FA Barge Replacement - Hunters Point South 5307 | 5 | SUBSTANTIAL COMPLETION | 2016-09-19 | 2016-10-03 | 2018-09-19 | 2018-10-03
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | FABARGEHP | FA Barge Replacement - Hunters Point South 5307 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-10-04 | 2016-10-08 | 2018-10-04 | 2024-10-08
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | GRANDAVEE | Grand Ave. Commercial Revitalization | 1 | DESIGN | 2005-01-01 | 2005-01-20 | 2008-01-02 | 2008-01-21
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | GRANDAVEE | Grand Ave. Commercial Revitalization | 2 | BID AWARD AND REGISTER CONTRCT | 2005-01-21 | 2005-02-04 | 2008-01-22 | 2008-02-05
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | GRANDAVEE | Grand Ave. Commercial Revitalization | 3 | CONSTRUCTION | 2005-02-05 | 2007-06-30 | 2008-02-06 | 2010-06-30
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | GRANDAVEE | Grand Ave. Commercial Revitalization | 4 | ORIGINAL EQUIP & FURNISHING | 2007-07-01 | 2007-06-30 | 2010-07-01 | 2010-06-30
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | GRANDAVEE | Grand Ave. Commercial Revitalization | 5 | SUBSTANTIAL COMPLETION | 2007-07-01 | 2007-06-30 | 2010-07-01 | 2010-06-30
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | GRANDAVEE | Grand Ave. Commercial Revitalization | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2007-07-01 | 2007-07-05 | 2010-07-01 | 2029-06-30
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQ1186 | ROCKAWAY BEACH BULKHEAD | 1 | DEVELOP SCOPE | 2011-06-30 | 2011-09-27 | 2015-06-30 | 2015-09-27
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQ1186 | ROCKAWAY BEACH BULKHEAD | 2 | PRELIMINARY DESIGN | 2011-09-28 | 2012-01-25 | 2015-09-28 | 2016-01-25
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQ1186 | ROCKAWAY BEACH BULKHEAD | 3 | FINAL DESIGN | 2012-01-26 | 2012-07-23 | 2016-01-26 | 2016-07-23
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQ1186 | ROCKAWAY BEACH BULKHEAD | 4 | BID AWARD AND REGISTER CONTRCT | 2012-07-24 | 2012-10-21 | 2016-07-24 | 2016-10-21
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQ1186 | ROCKAWAY BEACH BULKHEAD | 5 | CONSTRUCTION TO 25% | 2012-10-22 | 2013-02-18 | 2016-10-22 | 2017-02-18
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQ1186 | ROCKAWAY BEACH BULKHEAD | 6 | CONSTRUCTION TO 50% | 2013-02-19 | 2013-06-18 | 2017-02-19 | 2017-06-18
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQ1186 | ROCKAWAY BEACH BULKHEAD | 7 | CONSTRUCTION TO 75% | 2013-06-19 | 2013-10-16 | 2017-06-19 | 2017-10-16
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQ1186 | ROCKAWAY BEACH BULKHEAD | 8 | ORIGINAL EQUIP & FURNISHING | 2013-10-17 | 2014-01-14 | 2017-10-17 | 2018-01-14
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQ1186 | ROCKAWAY BEACH BULKHEAD | 9 | SUBSTANTIAL COMPLETION | 2014-01-15 | 2014-03-15 | 2018-01-15 | 2018-03-15
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQ1186 | ROCKAWAY BEACH BULKHEAD | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-03-16 | 2014-04-14 | 2018-03-16 | 2027-06-30
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQ1191 | Vernon Boulevard Bulkhead Replacement | 1 | DESIGN | 2002-01-01 | 2002-01-20 | 2002-01-01 | 2002-01-20
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQ1191 | Vernon Boulevard Bulkhead Replacement | 2 | BID AWARD AND REGISTER CONTRCT | 2002-01-21 | 2002-02-04 | 2002-01-21 | 2002-02-04
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQ1191 | Vernon Boulevard Bulkhead Replacement | 3 | CONSTRUCTION | 2016-07-01 | 2019-07-01 | 2016-07-01 | 2021-07-01
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQ1191 | Vernon Boulevard Bulkhead Replacement | 4 | ORIGINAL EQUIP & FURNISHING | 2019-07-02 | 2019-07-01 | 2021-07-02 | 2021-07-01
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQ1191 | Vernon Boulevard Bulkhead Replacement | 5 | SUBSTANTIAL COMPLETION | 2019-07-02 | 2019-07-01 | 2021-07-02 | 2021-07-01
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQ1191 | Vernon Boulevard Bulkhead Replacement | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-07-02 | 2019-07-06 | 2021-07-02 | 2026-06-30
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQ187 | 28th Avenue and Linden Place Area | 4 | ORIGINAL EQUIP & FURNISHING | 2007-06-06 | 2007-06-15 | 2020-07-01 | 2020-06-30
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQ187 | 28th Avenue and Linden Place Area | 5 | SUBSTANTIAL COMPLETION | 2007-06-16 | 2007-06-30 | 2020-07-01 | 2020-06-30
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQ187 | 28th Avenue and Linden Place Area | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2007-07-01 | 2007-07-05 | 2020-07-01 | 2020-07-05
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQ187A | 132nd St Construction - 20th Ave to Linden Place | 1 | DESIGN | 2008-01-01 | 2009-01-01 | 2010-06-25 | 2010-06-26
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQ187A | 132nd St Construction - 20th Ave to Linden Place | 2 | BID AWARD AND REGISTER CONTRCT | 2009-01-02 | 2009-01-01 | 2010-06-27 | 2010-06-26
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQ187A | 132nd St Construction - 20th Ave to Linden Place | 3 | CONSTRUCTION | 2009-01-02 | 2011-01-01 | 2001-07-02 | 2019-06-30
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQ187A | 132nd St Construction - 20th Ave to Linden Place | 4 | ORIGINAL EQUIP & FURNISHING | 2011-01-02 | 2011-01-01 | 2019-07-01 | 2019-06-30
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQ187A | 132nd St Construction - 20th Ave to Linden Place | 5 | SUBSTANTIAL COMPLETION | 2011-01-02 | 2011-01-01 | 2019-07-01 | 2019-06-30
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQ187A | 132nd St Construction - 20th Ave to Linden Place | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2011-01-02 | 2011-01-06 | 2019-07-01 | 2024-07-05
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQ662D | Springfield Gardens Residential Area, Reconstruction | 1 | DESIGN | 2006-01-01 | 2006-01-20 | 2011-03-01 | 2011-03-30
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQ662D | Springfield Gardens Residential Area, Reconstruction | 2 | BID AWARD AND REGISTER CONTRCT | 2006-01-21 | 2007-02-04 | 2011-04-01 | 2011-07-01
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQ662D | Springfield Gardens Residential Area, Reconstruction | 3 | CONSTRUCTION | 2007-02-05 | 2007-02-04 | 2011-09-01 | 2020-06-30
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQ662D | Springfield Gardens Residential Area, Reconstruction | 4 | ORIGINAL EQUIP & FURNISHING | 2007-02-05 | 2007-02-04 | 2020-07-01 | 2020-06-30
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQ662D | Springfield Gardens Residential Area, Reconstruction | 5 | SUBSTANTIAL COMPLETION | 2007-02-05 | 2007-02-04 | 2020-07-01 | 2020-06-30
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQ662D | Springfield Gardens Residential Area, Reconstruction | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2007-02-05 | 2007-02-09 | 2020-07-01 | 2029-06-28
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQ662D1 | Springfield Gardens Residential Area, Reconstruction | 1 | DESIGN | 2015-04-23 | 2015-05-12 | 2017-07-01 | 2020-04-11
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQ662D1 | Springfield Gardens Residential Area, Reconstruction | 2 | BID AWARD AND REGISTER CONTRCT | 2015-05-13 | 2015-05-27 | 2020-04-12 | 2020-04-26
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQ662D1 | Springfield Gardens Residential Area, Reconstruction | 3 | CONSTRUCTION | 2015-05-28 | 2015-07-01 | 2020-04-27 | 2020-05-31
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQ662D1 | Springfield Gardens Residential Area, Reconstruction | 4 | ORIGINAL EQUIP & FURNISHING | 2015-07-02 | 2015-07-11 | 2020-06-01 | 2020-06-10
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQ662D1 | Springfield Gardens Residential Area, Reconstruction | 5 | SUBSTANTIAL COMPLETION | 2015-07-12 | 2015-07-26 | 2020-06-11 | 2020-06-25
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQ662D1 | Springfield Gardens Residential Area, Reconstruction | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-07-27 | 2015-07-31 | 2020-06-26 | 2029-06-23
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQ996 | Harper Street Yard Bulkhead Renovation | 1 | DEVELOP SCOPE | 2012-06-30 | 2012-09-27 | 2015-07-01 | 2015-09-28
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQ996 | Harper Street Yard Bulkhead Renovation | 2 | PRELIMINARY DESIGN | 2012-09-28 | 2013-01-25 | 2015-09-29 | 2016-01-26
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQ996 | Harper Street Yard Bulkhead Renovation | 3 | FINAL DESIGN | 2013-01-26 | 2013-07-24 | 2016-01-27 | 2016-07-24
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQ996 | Harper Street Yard Bulkhead Renovation | 4 | BID AWARD AND REGISTER CONTRCT | 2013-07-25 | 2013-10-22 | 2016-07-25 | 2016-10-22
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQ996 | Harper Street Yard Bulkhead Renovation | 5 | CONSTRUCTION TO 25% | 2013-10-23 | 2014-02-19 | 2016-10-23 | 2020-06-30
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQ996 | Harper Street Yard Bulkhead Renovation | 6 | CONSTRUCTION TO 50% | 2014-02-20 | 2014-06-19 | 2020-07-01 | 2020-06-30
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQ996 | Harper Street Yard Bulkhead Renovation | 7 | CONSTRUCTION TO 75% | 2014-06-20 | 2014-10-17 | 2020-07-01 | 2020-06-30
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQ996 | Harper Street Yard Bulkhead Renovation | 8 | ORIGINAL EQUIP & FURNISHING | 2014-10-18 | 2015-01-15 | 2020-07-01 | 2020-06-30
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQ996 | Harper Street Yard Bulkhead Renovation | 9 | SUBSTANTIAL COMPLETION | 2015-01-16 | 2015-03-16 | 2020-07-01 | 2020-06-30
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQ996 | Harper Street Yard Bulkhead Renovation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-17 | 2015-04-15 | 2020-07-01 | 2026-07-30
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQWILLET | Willets Point - Van Wyck Improvements | 1 | DEVELOP SCOPE | 2015-06-01 | 2015-09-28 | 2016-06-01 | 2016-09-28
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQWILLET | Willets Point - Van Wyck Improvements | 2 | DESIGN START | 2015-09-29 | 2017-03-21 | 2016-09-29 | 2018-03-22
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQWILLET | Willets Point - Van Wyck Improvements | 3 | CONSTRUCTION START | 2017-03-22 | 2019-03-11 | 2018-03-23 | 2021-06-30
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQWILLET | Willets Point - Van Wyck Improvements | 4 | DESIGN | 2017-03-22 | 2019-03-11 | 2021-07-01 | 2021-07-20
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQWILLET | Willets Point - Van Wyck Improvements | 5 | BID AWARD AND REGISTER CONTRCT | 2017-03-22 | 2019-03-11 | 2021-07-21 | 2021-08-04
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQWILLET | Willets Point - Van Wyck Improvements | 6 | CONSTRUCTION | 2017-03-22 | 2019-03-11 | 2021-08-05 | 2021-09-08
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQWILLET | Willets Point - Van Wyck Improvements | 7 | ORIGINAL EQUIP & FURNISHING | 2017-03-22 | 2019-03-11 | 2021-09-09 | 2021-09-18
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQWILLET | Willets Point - Van Wyck Improvements | 8 | SUBSTANTIAL COMPLETION | 2017-03-22 | 2019-03-11 | 2021-09-19 | 2021-10-03
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQWILLET | Willets Point - Van Wyck Improvements | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-22 | 2019-03-11 | 2021-10-04 | 2028-06-30
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | JAMAAECT | GDJC - Atlantic Avenue Extension - Construction | 1 | DESIGN | 2013-12-27 | 2014-05-30 | 2015-06-21 | 2015-11-22
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | JAMAAECT | GDJC - Atlantic Avenue Extension - Construction | 2 | BID AWARD AND REGISTER CONTRCT | 2014-05-31 | 2014-05-30 | 2015-11-23 | 2015-11-22
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | JAMAAECT | GDJC - Atlantic Avenue Extension - Construction | 3 | CONSTRUCTION | 2014-05-31 | 2016-01-01 | 2015-11-23 | 2017-06-25
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | JAMAAECT | GDJC - Atlantic Avenue Extension - Construction | 4 | ORIGINAL EQUIP & FURNISHING | 2016-01-02 | 2016-01-01 | 2017-06-26 | 2017-06-25
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | JAMAAECT | GDJC - Atlantic Avenue Extension - Construction | 5 | SUBSTANTIAL COMPLETION | 2016-01-02 | 2016-01-01 | 2017-06-26 | 2017-06-25
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | JAMAAECT | GDJC - Atlantic Avenue Extension - Construction | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-01-02 | 2016-01-06 | 2017-06-26 | 2024-06-30
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | JAMCMFEE | GDJC AAE and Station Plaza CM | 1 | DESIGN | 2010-06-30 | 2010-07-19 | 2014-06-30 | 2014-07-19
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | JAMCMFEE | GDJC AAE and Station Plaza CM | 2 | BID AWARD AND REGISTER CONTRCT | 2010-07-20 | 2010-08-03 | 2014-07-20 | 2014-08-03
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | JAMCMFEE | GDJC AAE and Station Plaza CM | 3 | CONSTRUCTION | 2010-08-04 | 2014-06-30 | 2014-08-04 | 2020-06-30
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | JAMCMFEE | GDJC AAE and Station Plaza CM | 4 | ORIGINAL EQUIP & FURNISHING | 2014-07-01 | 2014-06-30 | 2020-07-01 | 2020-06-30
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | JAMCMFEE | GDJC AAE and Station Plaza CM | 5 | SUBSTANTIAL COMPLETION | 2014-07-01 | 2014-06-30 | 2020-07-01 | 2020-06-30
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | JAMCMFEE | GDJC AAE and Station Plaza CM | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-07-01 | 2014-07-05 | 2020-07-01 | 2020-07-05
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | JAMECODEV | FA - GDJC Transportation Center Intermodal Facilities | 1 | DESIGN | 2006-06-30 | 2006-07-19 | 2006-06-04 | 2008-07-05
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | JAMECODEV | FA - GDJC Transportation Center Intermodal Facilities | 2 | BID AWARD AND REGISTER CONTRCT | 2006-07-20 | 2006-08-03 | 2008-06-30 | 2011-06-30
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | JAMECODEV | FA - GDJC Transportation Center Intermodal Facilities | 3 | CONSTRUCTION | 2006-08-04 | 2007-09-07 | 2011-07-01 | 2011-06-30
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | JAMECODEV | FA - GDJC Transportation Center Intermodal Facilities | 4 | ORIGINAL EQUIP & FURNISHING | 2007-09-08 | 2007-09-07 | 2011-07-01 | 2011-06-30
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | JAMECODEV | FA - GDJC Transportation Center Intermodal Facilities | 5 | SUBSTANTIAL COMPLETION | 2007-09-08 | 2007-09-07 | 2011-07-01 | 2011-06-30
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | JAMECODEV | FA - GDJC Transportation Center Intermodal Facilities | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2007-09-08 | 2007-09-12 | 2011-07-01 | 2027-06-30
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | JAMSTPLZ | Station Plaza Design & Construction | 1 | DESIGN | 2016-01-01 | 2018-06-30 | 2016-01-01 | 2018-06-30
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | JAMSTPLZ | Station Plaza Design & Construction | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-01 | 2018-06-30 | 2018-07-01 | 2018-06-30
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | JAMSTPLZ | Station Plaza Design & Construction | 3 | CONSTRUCTION | 2018-07-01 | 2021-06-30 | 2018-07-01 | 2021-06-30
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | JAMSTPLZ | Station Plaza Design & Construction | 4 | ORIGINAL EQUIP & FURNISHING | 2021-07-01 | 2021-06-30 | 2021-07-01 | 2021-06-30
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | JAMSTPLZ | Station Plaza Design & Construction | 5 | SUBSTANTIAL COMPLETION | 2021-07-01 | 2021-06-30 | 2021-07-01 | 2021-06-30
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | JAMSTPLZ | Station Plaza Design & Construction | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-07-01 | 2021-07-05 | 2021-07-01 | 2021-07-05
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | JAMSUTPHI | FA - GJDC Sutphin Underpass | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2011-01-02 | 2011-01-06 | 2011-01-02 | 2011-01-06
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | PWD99AERO | FA - College of Aeronautics | 1 | DESIGN | 2006-06-30 | 2006-07-19 | 2006-06-30 | 2006-07-19
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | PWD99AERO | FA - College of Aeronautics | 2 | BID AWARD AND REGISTER CONTRCT | 2006-07-20 | 2006-08-03 | 2006-07-20 | 2006-08-03
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | PWD99AERO | FA - College of Aeronautics | 3 | CONSTRUCTION | 2006-08-04 | 2007-09-07 | 2006-08-04 | 2007-09-07
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | PWD99AERO | FA - College of Aeronautics | 4 | ORIGINAL EQUIP & FURNISHING | 2007-09-08 | 2007-09-07 | 2007-09-08 | 2007-09-07
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | PWD99AERO | FA - College of Aeronautics | 5 | SUBSTANTIAL COMPLETION | 2007-09-08 | 2007-09-07 | 2007-09-08 | 2007-09-07
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | PWD99AERO | FA - College of Aeronautics | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2007-09-08 | 2007-09-12 | 2007-09-08 | 2029-06-30
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | QNSPLGA | Queens Plaza Garage | 1 | DESIGN | 2006-06-30 | 2006-07-19 | 2012-03-10 | 2012-09-08
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | QNSPLGA | Queens Plaza Garage | 2 | BID AWARD AND REGISTER CONTRCT | 2006-07-20 | 2006-08-03 | 2012-09-09 | 2014-11-30
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | QNSPLGA | Queens Plaza Garage | 3 | CONSTRUCTION | 2006-08-04 | 2008-06-30 | 2009-02-01 | 2009-02-01
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | QNSPLGA | Queens Plaza Garage | 4 | ORIGINAL EQUIP & FURNISHING | 2008-07-01 | 2008-06-30 | 2009-02-02 | 2009-02-01
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | QNSPLGA | Queens Plaza Garage | 5 | SUBSTANTIAL COMPLETION | 2008-07-01 | 2008-06-30 | 2008-06-07 | 2009-09-03
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | QNSPLGA | Queens Plaza Garage | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-07-01 | 2008-07-05 | 2009-09-04 | 2028-06-30
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | QNSPLJACK | Long Island City-Jackson Ave | 1 | DESIGN | 2005-01-01 | 2005-01-20 | 2001-01-02 | 2002-06-02
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | QNSPLJACK | Long Island City-Jackson Ave | 2 | BID AWARD AND REGISTER CONTRCT | 2003-02-21 | 2007-02-04 | 2003-02-21 | 2003-02-20
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | QNSPLJACK | Long Island City-Jackson Ave | 3 | CONSTRUCTION | 2007-02-05 | 2007-02-04 | 2007-09-01 | 2009-09-01
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | QNSPLJACK | Long Island City-Jackson Ave | 4 | ORIGINAL EQUIP & FURNISHING | 2007-02-05 | 2007-02-04 | 2009-09-02 | 2020-09-01
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | QNSPLJACK | Long Island City-Jackson Ave | 5 | SUBSTANTIAL COMPLETION | 2007-02-05 | 2007-02-04 | 2020-09-02 | 2021-12-01
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | QNSPLJACK | Long Island City-Jackson Ave | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2007-02-05 | 2007-02-09 | 2021-12-02 | 2029-06-30
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | QUEENSC | Queens Commercial Corridors | 1 | DESIGN | 2005-01-01 | 2005-01-20 | 2017-01-02 | 2017-01-21
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | QUEENSC | Queens Commercial Corridors | 2 | BID AWARD AND REGISTER CONTRCT | 2005-01-21 | 2005-02-04 | 2017-01-22 | 2019-02-05
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | QUEENSC | Queens Commercial Corridors | 3 | CONSTRUCTION | 2005-02-05 | 2005-03-11 | 2019-02-06 | 2023-08-31
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | QUEENSC | Queens Commercial Corridors | 4 | ORIGINAL EQUIP & FURNISHING | 2005-03-12 | 2005-03-21 | 2023-09-01 | 2023-08-31
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | QUEENSC | Queens Commercial Corridors | 5 | SUBSTANTIAL COMPLETION | 2005-03-22 | 2005-04-05 | 2023-09-01 | 2023-08-31
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | QUEENSC | Queens Commercial Corridors | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2005-04-06 | 2005-04-10 | 2013-06-26 | 2029-06-30
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | QUEENSCAS | QUEENS COMMERCIAL CORRIDOR AT ASTORIA | 1 | DESIGN | 2014-07-01 | 2014-07-20 | 2018-07-01 | 2018-07-20
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | QUEENSCAS | QUEENS COMMERCIAL CORRIDOR AT ASTORIA | 2 | BID AWARD AND REGISTER CONTRCT | 2014-07-21 | 2014-08-04 | 2018-07-21 | 2018-08-04
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | QUEENSCAS | QUEENS COMMERCIAL CORRIDOR AT ASTORIA | 3 | CONSTRUCTION | 2014-08-05 | 2014-09-08 | 2018-08-05 | 2018-09-08
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | QUEENSCAS | QUEENS COMMERCIAL CORRIDOR AT ASTORIA | 4 | ORIGINAL EQUIP & FURNISHING | 2014-09-09 | 2014-09-18 | 2018-09-09 | 2018-09-18
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | QUEENSCAS | QUEENS COMMERCIAL CORRIDOR AT ASTORIA | 5 | SUBSTANTIAL COMPLETION | 2014-09-19 | 2014-10-03 | 2018-09-19 | 2018-10-03
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | QUEENSCAS | QUEENS COMMERCIAL CORRIDOR AT ASTORIA | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-10-04 | 2014-10-08 | 2018-10-04 | 2021-06-30
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | QUEENSCRK | QUEENS COMMERCIAL CORRIDOR AT ROCKAWAY | 1 | DESIGN | 2014-07-01 | 2014-07-20 | 2018-07-01 | 2018-07-20
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | QUEENSCRK | QUEENS COMMERCIAL CORRIDOR AT ROCKAWAY | 2 | BID AWARD AND REGISTER CONTRCT | 2014-07-21 | 2014-08-04 | 2018-07-21 | 2018-08-04
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | QUEENSCRK | QUEENS COMMERCIAL CORRIDOR AT ROCKAWAY | 3 | CONSTRUCTION | 2014-08-05 | 2014-09-08 | 2018-08-05 | 2021-10-30
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | QUEENSCRK | QUEENS COMMERCIAL CORRIDOR AT ROCKAWAY | 4 | ORIGINAL EQUIP & FURNISHING | 2014-09-09 | 2014-09-18 | 2021-10-31 | 2021-10-30
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | QUEENSCRK | QUEENS COMMERCIAL CORRIDOR AT ROCKAWAY | 5 | SUBSTANTIAL COMPLETION | 2014-09-19 | 2014-10-03 | 2021-10-31 | 2021-10-30
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | QUEENSCRK | QUEENS COMMERCIAL CORRIDOR AT ROCKAWAY | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-10-04 | 2014-10-08 | 2021-10-31 | 2021-11-04
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | QUEENSCSA | QUEENS COMMERCIAL CORRIDOR AT ST. ALBANS | 1 | DESIGN | 2014-07-01 | 2014-07-20 | 2018-07-01 | 2018-07-20
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | QUEENSCSA | QUEENS COMMERCIAL CORRIDOR AT ST. ALBANS | 2 | BID AWARD AND REGISTER CONTRCT | 2014-07-21 | 2014-08-04 | 2018-07-21 | 2018-08-04
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | QUEENSCSA | QUEENS COMMERCIAL CORRIDOR AT ST. ALBANS | 3 | CONSTRUCTION | 2014-08-05 | 2014-09-08 | 2018-08-05 | 2021-06-30
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | QUEENSCSA | QUEENS COMMERCIAL CORRIDOR AT ST. ALBANS | 4 | ORIGINAL EQUIP & FURNISHING | 2014-09-09 | 2014-09-18 | 2021-07-01 | 2021-06-30
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | QUEENSCSA | QUEENS COMMERCIAL CORRIDOR AT ST. ALBANS | 5 | SUBSTANTIAL COMPLETION | 2014-09-19 | 2014-10-03 | 2021-07-01 | 2021-06-30
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | QUEENSCSA | QUEENS COMMERCIAL CORRIDOR AT ST. ALBANS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-10-04 | 2014-10-08 | 2021-07-01 | 2021-07-05
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | QWESTB | Queens West/Hunter's Point South | 1 | DESIGN | 2009-01-01 | 2010-01-01 | 2012-01-02 | 2013-01-01
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | QWESTB | Queens West/Hunter's Point South | 2 | BID AWARD AND REGISTER CONTRCT | 2010-01-02 | 2010-01-01 | 2013-01-02 | 2013-01-01
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | QWESTB | Queens West/Hunter's Point South | 3 | CONSTRUCTION | 2010-01-02 | 2011-01-01 | 2013-01-02 | 2020-06-30
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | QWESTB | Queens West/Hunter's Point South | 4 | ORIGINAL EQUIP & FURNISHING | 2011-01-02 | 2011-01-01 | 2020-07-01 | 2020-06-30
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | QWESTB | Queens West/Hunter's Point South | 5 | SUBSTANTIAL COMPLETION | 2011-01-02 | 2011-01-01 | 2020-07-01 | 2020-06-30
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | QWESTB | Queens West/Hunter's Point South | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2011-01-02 | 2011-01-06 | 2020-07-01 | 2028-10-10
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | QWESTC | Hunters Point South Phase II | 1 | DESIGN | 2007-07-02 | 2007-07-21 | 2009-07-02 | 2009-07-21
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | QWESTC | Hunters Point South Phase II | 2 | BID AWARD AND REGISTER CONTRCT | 2007-07-22 | 2007-08-05 | 2009-07-22 | 2009-08-05
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | QWESTC | Hunters Point South Phase II | 3 | CONSTRUCTION | 2007-08-06 | 2007-09-09 | 2009-08-06 | 2009-09-09
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | QWESTC | Hunters Point South Phase II | 4 | ORIGINAL EQUIP & FURNISHING | 2007-09-10 | 2007-09-19 | 2009-09-10 | 2009-09-19
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | QWESTC | Hunters Point South Phase II | 5 | SUBSTANTIAL COMPLETION | 2007-09-20 | 2007-10-04 | 2009-09-20 | 2009-10-04
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | QWESTC | Hunters Point South Phase II | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2007-10-05 | 2007-10-09 | 2009-10-05 | 2025-06-30
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | ROCKBLVD | FA - Rockaway BLVD | 1 | DESIGN | 2006-08-01 | 2006-08-20 | 2006-08-01 | 2006-08-20
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | ROCKBLVD | FA - Rockaway BLVD | 2 | BID AWARD AND REGISTER CONTRCT | 2006-08-21 | 2006-09-04 | 2006-08-21 | 2006-09-04
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | ROCKBLVD | FA - Rockaway BLVD | 3 | CONSTRUCTION | 2006-09-05 | 2006-10-09 | 2011-04-30 | 2011-06-30
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | ROCKBLVD | FA - Rockaway BLVD | 4 | ORIGINAL EQUIP & FURNISHING | 2006-10-10 | 2006-10-19 | 2011-07-01 | 2011-06-30
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | ROCKBLVD | FA - Rockaway BLVD | 5 | SUBSTANTIAL COMPLETION | 2006-10-20 | 2006-11-03 | 2011-07-01 | 2011-06-30
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | ROCKBLVD | FA - Rockaway BLVD | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2006-11-04 | 2006-11-08 | 2011-07-01 | 2024-06-30
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | ROCKBULK | Rockaway Park Bulkhead Rehabilitation | 1 | DESIGN | 2009-03-12 | 2011-03-31 | 2010-03-12 | 2012-03-30
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | ROCKBULK | Rockaway Park Bulkhead Rehabilitation | 2 | BID AWARD AND REGISTER CONTRCT | 2011-04-01 | 2011-03-31 | 2012-03-31 | 2012-03-30
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | ROCKBULK | Rockaway Park Bulkhead Rehabilitation | 3 | CONSTRUCTION | 2011-04-01 | 2013-03-31 | 2012-03-31 | 2014-03-31
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | ROCKBULK | Rockaway Park Bulkhead Rehabilitation | 4 | ORIGINAL EQUIP & FURNISHING | 2013-04-01 | 2013-03-31 | 2014-04-01 | 2014-03-31
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | ROCKBULK | Rockaway Park Bulkhead Rehabilitation | 5 | SUBSTANTIAL COMPLETION | 2013-04-01 | 2013-03-31 | 2014-04-01 | 2014-03-31
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | ROCKBULK | Rockaway Park Bulkhead Rehabilitation | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-04-01 | 2013-04-05 | 2014-04-01 | 2026-06-30
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | ROCKINFRA | Rockaways Infrastructure Improvements | 1 | DESIGN | 2016-01-01 | 2016-01-20 | 2016-01-01 | 2016-01-20
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | ROCKINFRA | Rockaways Infrastructure Improvements | 2 | BID AWARD AND REGISTER CONTRCT | 2016-01-21 | 2016-06-30 | 2016-01-21 | 2016-06-30
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | ROCKINFRA | Rockaways Infrastructure Improvements | 3 | CONSTRUCTION | 2016-07-01 | 2017-06-30 | 2016-07-01 | 2017-06-30
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | ROCKINFRA | Rockaways Infrastructure Improvements | 4 | ORIGINAL EQUIP & FURNISHING | 2017-07-01 | 2018-06-30 | 2017-07-01 | 2018-06-30
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | ROCKINFRA | Rockaways Infrastructure Improvements | 5 | SUBSTANTIAL COMPLETION | 2018-07-01 | 2019-06-30 | 2018-07-01 | 2019-06-30
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | ROCKINFRA | Rockaways Infrastructure Improvements | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2005-07-12 | 2020-07-05 | 2005-07-12 | 2028-07-05
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | ROCKOUT | Rockaway Park, Outfall Improvements | 1 | DESIGN | 2014-03-01 | 2014-03-20 | 2014-03-01 | 2014-03-20
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | ROCKOUT | Rockaway Park, Outfall Improvements | 2 | BID AWARD AND REGISTER CONTRCT | 2014-03-21 | 2014-04-04 | 2014-03-21 | 2014-04-04
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | ROCKOUT | Rockaway Park, Outfall Improvements | 3 | CONSTRUCTION | 2014-04-05 | 2014-05-09 | 2014-04-05 | 2020-06-30
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | ROCKOUT | Rockaway Park, Outfall Improvements | 4 | ORIGINAL EQUIP & FURNISHING | 2014-05-10 | 2014-05-19 | 2020-07-01 | 2020-06-30
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | ROCKOUT | Rockaway Park, Outfall Improvements | 5 | SUBSTANTIAL COMPLETION | 2014-05-20 | 2014-06-03 | 2020-07-01 | 2020-06-30
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | ROCKOUT | Rockaway Park, Outfall Improvements | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-06-04 | 2014-06-08 | 2020-07-01 | 2029-06-28
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDRLHPS | FA Resiliency - Land Hardening Hunters Point South | 1 | DESIGN | 2016-07-01 | 2016-07-20 | 2018-07-02 | 2018-07-21
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDRLHPS | FA Resiliency - Land Hardening Hunters Point South | 2 | BID AWARD AND REGISTER CONTRCT | 2016-07-21 | 2016-08-04 | 2018-07-22 | 2018-08-05
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDRLHPS | FA Resiliency - Land Hardening Hunters Point South | 3 | CONSTRUCTION | 2016-08-05 | 2016-09-08 | 2018-08-06 | 2018-09-09
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDRLHPS | FA Resiliency - Land Hardening Hunters Point South | 4 | ORIGINAL EQUIP & FURNISHING | 2016-09-09 | 2016-09-18 | 2018-09-10 | 2018-09-19
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDRLHPS | FA Resiliency - Land Hardening Hunters Point South | 5 | SUBSTANTIAL COMPLETION | 2016-09-19 | 2016-10-03 | 2018-09-20 | 2018-10-04
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDRLHPS | FA Resiliency - Land Hardening Hunters Point South | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-10-04 | 2019-10-08 | 2018-10-05 | 2021-10-08
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | SSFERRY | South Shore Ferry Site Acquisition | 1 | DESIGN | 1996-02-01 | 1996-04-30 | 2001-01-31 | 2001-02-19
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | SSFERRY | South Shore Ferry Site Acquisition | 2 | BID AWARD AND REGISTER CONTRCT | 1996-05-01 | 1996-08-28 | 2001-02-20 | 2001-03-06
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | SSFERRY | South Shore Ferry Site Acquisition | 3 | CONSTRUCTION | 1996-08-29 | 2008-07-30 | 2001-03-07 | 2022-06-30
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | SSFERRY | South Shore Ferry Site Acquisition | 4 | ORIGINAL EQUIP & FURNISHING | 2008-07-31 | 2008-07-30 | 2022-07-01 | 2022-06-30
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | SSFERRY | South Shore Ferry Site Acquisition | 5 | SUBSTANTIAL COMPLETION | 2008-07-31 | 2008-07-30 | 2022-07-01 | 2022-06-30
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | SSFERRY | South Shore Ferry Site Acquisition | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-07-31 | 2008-07-30 | 2022-07-01 | 2028-07-05
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | SSFERRY | South Shore Ferry Site Acquisition | 7 | CONSTRUCTION TO 75% | 2008-07-31 | 2008-07-30 | 2022-07-01 | 2028-07-05
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | SSFERRY | South Shore Ferry Site Acquisition | 8 | ORIGINAL EQUIP & FURNISHING | 2008-07-31 | 2008-07-30 | 2022-07-01 | 2028-07-05
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | SSFERRY | South Shore Ferry Site Acquisition | 9 | SUBSTANTIAL COMPLETION | 2008-07-31 | 2008-07-30 | 2022-07-01 | 2028-07-05
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | SSFERRY | South Shore Ferry Site Acquisition | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-07-31 | 2008-08-29 | 2022-07-01 | 2028-07-05
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | SSYARDS | Sunnyside Yards | 1 | DESIGN | 2018-06-30 | 2018-07-19 | 2018-06-30 | 2018-07-19
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | SSYARDS | Sunnyside Yards | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-20 | 2018-08-03 | 2018-07-20 | 2018-08-03
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | SSYARDS | Sunnyside Yards | 3 | CONSTRUCTION | 2018-08-04 | 2018-09-07 | 2018-08-04 | 2018-09-07
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | SSYARDS | Sunnyside Yards | 4 | ORIGINAL EQUIP & FURNISHING | 2018-09-08 | 2018-09-17 | 2018-09-08 | 2018-09-17
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | SSYARDS | Sunnyside Yards | 5 | SUBSTANTIAL COMPLETION | 2018-09-18 | 2018-10-02 | 2018-09-18 | 2018-10-02
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | SSYARDS | Sunnyside Yards | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-10-03 | 2020-10-07 | 2018-10-03 | 2024-10-07
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | SUNNYARCH | Sunnyside Arch Restoration | 1 | DESIGN | 2005-01-01 | 2005-01-20 | 2008-05-26 | 2008-06-26
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | SUNNYARCH | Sunnyside Arch Restoration | 2 | BID AWARD AND REGISTER CONTRCT | 2005-01-21 | 2007-02-04 | 2008-06-27 | 2008-06-26
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | SUNNYARCH | Sunnyside Arch Restoration | 3 | CONSTRUCTION | 2007-02-05 | 2007-02-04 | 2007-03-01 | 2017-06-30
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | SUNNYARCH | Sunnyside Arch Restoration | 4 | ORIGINAL EQUIP & FURNISHING | 2007-02-05 | 2007-02-04 | 2017-07-01 | 2017-06-30
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | SUNNYARCH | Sunnyside Arch Restoration | 5 | SUBSTANTIAL COMPLETION | 2007-02-05 | 2007-02-04 | 2017-07-01 | 2017-06-30
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | SUNNYARCH | Sunnyside Arch Restoration | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2007-02-05 | 2007-02-09 | 2017-07-01 | 2027-07-04
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | WILLETDEM | Willets Point Above Grade Demolition | 1 | DESIGN | 2015-07-01 | 2015-07-20 | 2015-07-01 | 2015-07-20
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | WILLETDEM | Willets Point Above Grade Demolition | 2 | BID AWARD AND REGISTER CONTRCT | 2015-07-21 | 2015-08-04 | 2015-07-21 | 2015-08-04
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | WILLETDEM | Willets Point Above Grade Demolition | 3 | CONSTRUCTION | 2015-08-05 | 2015-09-08 | 2015-08-05 | 2015-09-08
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | WILLETDEM | Willets Point Above Grade Demolition | 4 | ORIGINAL EQUIP & FURNISHING | 2015-09-09 | 2015-09-18 | 2015-09-09 | 2015-09-18
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | WILLETDEM | Willets Point Above Grade Demolition | 5 | SUBSTANTIAL COMPLETION | 2015-09-19 | 2015-10-03 | 2015-09-19 | 2015-10-03
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | WILLETDEM | Willets Point Above Grade Demolition | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-10-04 | 2019-10-08 | 2015-10-04 | 2025-10-08
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | WILLETINF | Willets Point Redevelopment Infrastructure | 1 | DESIGN | 2010-01-01 | 2011-01-20 | 2019-08-25 | 2019-09-25
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | WILLETINF | Willets Point Redevelopment Infrastructure | 2 | BID AWARD AND REGISTER CONTRCT | 2011-01-21 | 2011-01-20 | 2019-09-26 | 2019-09-25
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | WILLETINF | Willets Point Redevelopment Infrastructure | 3 | CONSTRUCTION | 2011-01-21 | 2013-01-20 | 2019-09-26 | 2019-09-25
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | WILLETINF | Willets Point Redevelopment Infrastructure | 4 | ORIGINAL EQUIP & FURNISHING | 2013-01-21 | 2013-01-20 | 2019-09-26 | 2019-09-25
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | WILLETINF | Willets Point Redevelopment Infrastructure | 5 | SUBSTANTIAL COMPLETION | 2013-01-21 | 2013-01-20 | 2019-09-26 | 2027-06-25
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | WILLETINF | Willets Point Redevelopment Infrastructure | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-01-21 | 2013-01-25 | 2027-06-26 | 2027-06-30
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | WILLETSEN | Willets Point Environmental | 1 | DESIGN | 2010-01-01 | 2012-01-20 | 2011-07-29 | 2013-08-16
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | WILLETSEN | Willets Point Environmental | 2 | BID AWARD AND REGISTER CONTRCT | 2012-01-21 | 2012-01-20 | 2013-08-17 | 2013-08-16
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | WILLETSEN | Willets Point Environmental | 3 | CONSTRUCTION | 2012-01-21 | 2014-01-20 | 2013-08-17 | 2015-08-17
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | WILLETSEN | Willets Point Environmental | 4 | ORIGINAL EQUIP & FURNISHING | 2014-01-21 | 2014-01-20 | 2015-08-18 | 2015-08-17
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | WILLETSEN | Willets Point Environmental | 5 | SUBSTANTIAL COMPLETION | 2014-01-21 | 2014-01-20 | 2015-08-18 | 2015-08-17
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | WILLETSEN | Willets Point Environmental | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-01-21 | 2014-01-25 | 2015-08-18 | 2024-01-25
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | WILLTFAOF | FA - Willets Point Phase IA Offsite Infrastructure | 1 | DESIGN | 2019-07-01 | 2019-07-20 | 2019-07-01 | 2019-07-20
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | WILLTFAOF | FA - Willets Point Phase IA Offsite Infrastructure | 2 | BID AWARD AND REGISTER CONTRCT | 2019-07-21 | 2019-08-04 | 2019-07-21 | 2019-08-04
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | WILLTFAOF | FA - Willets Point Phase IA Offsite Infrastructure | 3 | CONSTRUCTION | 2019-08-05 | 2019-09-08 | 2019-08-05 | 2019-09-08
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | WILLTFAOF | FA - Willets Point Phase IA Offsite Infrastructure | 4 | ORIGINAL EQUIP & FURNISHING | 2019-09-09 | 2022-09-18 | 2019-09-09 | 2022-09-18
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | WILLTFAOF | FA - Willets Point Phase IA Offsite Infrastructure | 5 | SUBSTANTIAL COMPLETION | 2022-09-19 | 2022-10-03 | 2022-09-19 | 2022-10-03
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | WILLTFAOF | FA - Willets Point Phase IA Offsite Infrastructure | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-10-04 | 2022-10-08 | 2022-10-04 | 2022-10-08
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | WILLTFAON | FA - Willet's Point Onsite Infrastructure | 1 | DESIGN | 2019-07-01 | 2019-07-20 | 2019-07-01 | 2019-07-20
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | WILLTFAON | FA - Willet's Point Onsite Infrastructure | 2 | BID AWARD AND REGISTER CONTRCT | 2019-07-21 | 2019-08-04 | 2019-07-21 | 2019-08-04
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | WILLTFAON | FA - Willet's Point Onsite Infrastructure | 3 | CONSTRUCTION | 2019-08-05 | 2019-09-08 | 2019-08-05 | 2019-09-08
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | WILLTFAON | FA - Willet's Point Onsite Infrastructure | 4 | ORIGINAL EQUIP & FURNISHING | 2019-09-09 | 2022-09-18 | 2019-09-09 | 2022-09-18
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | WILLTFAON | FA - Willet's Point Onsite Infrastructure | 5 | SUBSTANTIAL COMPLETION | 2022-09-19 | 2022-10-03 | 2022-09-19 | 2022-10-03
20201123 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | WILLTFAON | FA - Willet's Point Onsite Infrastructure | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-10-04 | 2022-10-08 | 2022-10-04 | 2022-10-08
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM01ASCC | ASTORIA HOUSES - COMMUNITY CENTER UPGRADE | 1 | DESIGN | 2007-01-01 | 2007-06-29 | 2007-01-18 | 2016-09-20
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM01ASCC | ASTORIA HOUSES - COMMUNITY CENTER UPGRADE | 2 | BID AWARD AND REGISTER CONTRCT | 2007-06-30 | 2007-11-21 | 2016-09-21 | 2016-09-20
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM01ASCC | ASTORIA HOUSES - COMMUNITY CENTER UPGRADE | 3 | CONSTRUCTION | 2007-11-22 | 2008-11-20 | 2016-09-21 | 2016-09-20
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM01ASCC | ASTORIA HOUSES - COMMUNITY CENTER UPGRADE | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-11-21 | 2009-05-19 | 2016-09-21 | 2016-09-20
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM01ASCC | ASTORIA HOUSES - COMMUNITY CENTER UPGRADE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-11-21 | 2009-05-19 | 2016-09-21 | 2020-12-28
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM15QNGR | QUEENSBRIDGE NORTH PLAY AREA UPGRADE | 1 | DESIGN | 2015-01-02 | 2015-06-30 | 2016-10-12 | 2017-08-18
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM15QNGR | QUEENSBRIDGE NORTH PLAY AREA UPGRADE | 2 | BID AWARD AND REGISTER CONTRCT | 2015-07-01 | 2015-11-22 | 2017-08-19 | 2018-01-19
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM15QNGR | QUEENSBRIDGE NORTH PLAY AREA UPGRADE | 3 | CONSTRUCTION | 2015-11-23 | 2016-11-21 | 2018-01-20 | 2019-02-15
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM15QNGR | QUEENSBRIDGE NORTH PLAY AREA UPGRADE | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-11-22 | 2017-05-20 | 2018-01-20 | 2019-02-15
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM15QNGR | QUEENSBRIDGE NORTH PLAY AREA UPGRADE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-11-22 | 2017-05-20 | 2019-02-16 | 2019-08-30
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM15RFGR | REDFERN COMMUNITY CENTER PLAYGROUND | 1 | DESIGN | 2015-01-02 | 2015-06-30 | 2018-06-01 | 2018-12-31
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM15RFGR | REDFERN COMMUNITY CENTER PLAYGROUND | 2 | BID AWARD AND REGISTER CONTRCT | 2015-07-01 | 2015-11-22 | 2019-01-01 | 2019-05-25
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM15RFGR | REDFERN COMMUNITY CENTER PLAYGROUND | 3 | CONSTRUCTION | 2015-11-23 | 2016-11-21 | 2019-05-26 | 2020-05-24
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM15RFGR | REDFERN COMMUNITY CENTER PLAYGROUND | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-11-22 | 2017-05-20 | 2019-05-26 | 2020-05-24
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM15RFGR | REDFERN COMMUNITY CENTER PLAYGROUND | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-11-22 | 2017-05-20 | 2020-05-25 | 2020-11-20
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM15SJBC | SOUTH JAMAICA HOUSES BASKETBALL COURT UPGRADES | 1 | DESIGN | 2015-01-02 | 2015-06-30 | 2016-07-22 | 2017-01-17
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM15SJBC | SOUTH JAMAICA HOUSES BASKETBALL COURT UPGRADES | 2 | BID AWARD AND REGISTER CONTRCT | 2015-07-01 | 2015-11-22 | 2017-01-18 | 2017-06-11
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM15SJBC | SOUTH JAMAICA HOUSES BASKETBALL COURT UPGRADES | 3 | CONSTRUCTION | 2015-11-23 | 2016-11-21 | 2017-06-12 | 2018-06-11
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM15SJBC | SOUTH JAMAICA HOUSES BASKETBALL COURT UPGRADES | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-11-22 | 2017-05-20 | 2017-06-12 | 2018-06-11
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM15SJBC | SOUTH JAMAICA HOUSES BASKETBALL COURT UPGRADES | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-11-22 | 2017-05-20 | 2018-06-12 | 2020-06-10
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM16ASBC | ASTORIA HOUSES RENOVATE BASKETBALL COURT | 1 | DESIGN | 2016-01-04 | 2016-07-01 | 2016-01-04 | 2016-07-01
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM16ASBC | ASTORIA HOUSES RENOVATE BASKETBALL COURT | 2 | BID AWARD AND REGISTER CONTRCT | 2016-07-02 | 2016-11-23 | 2016-07-02 | 2016-11-23
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM16ASBC | ASTORIA HOUSES RENOVATE BASKETBALL COURT | 3 | CONSTRUCTION | 2016-11-24 | 2017-11-23 | 2016-11-24 | 2017-11-23
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM16ASBC | ASTORIA HOUSES RENOVATE BASKETBALL COURT | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-11-24 | 2018-05-22 | 2016-11-24 | 2017-11-23
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM16ASBC | ASTORIA HOUSES RENOVATE BASKETBALL COURT | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-11-24 | 2018-05-22 | 2017-11-24 | 2018-05-22
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM16CMPL | CARLTON MANOR PLAYGROUND RENOVATIONS BASKETBALL COURTS | 1 | DESIGN | 2016-01-04 | 2016-07-01 | 2018-01-01 | 2018-06-29
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM16CMPL | CARLTON MANOR PLAYGROUND RENOVATIONS BASKETBALL COURTS | 2 | BID AWARD AND REGISTER CONTRCT | 2016-07-02 | 2016-11-23 | 2018-06-30 | 2018-11-21
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM16CMPL | CARLTON MANOR PLAYGROUND RENOVATIONS BASKETBALL COURTS | 3 | CONSTRUCTION | 2016-11-24 | 2017-11-23 | 2018-11-22 | 2019-11-21
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM16CMPL | CARLTON MANOR PLAYGROUND RENOVATIONS BASKETBALL COURTS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-11-24 | 2018-05-22 | 2018-11-22 | 2019-11-21
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM16CMPL | CARLTON MANOR PLAYGROUND RENOVATIONS BASKETBALL COURTS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-11-24 | 2018-05-22 | 2019-11-22 | 2020-05-19
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM16LVSC | LEAVITT STREET-34TH AVENUE SECURITY CAMERAS | 1 | DESIGN | 2016-03-04 | 2016-08-30 | 2016-03-04 | 2016-08-30
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM16LVSC | LEAVITT STREET-34TH AVENUE SECURITY CAMERAS | 2 | BID AWARD AND REGISTER CONTRCT | 2016-08-31 | 2017-01-22 | 2016-08-31 | 2017-01-22
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM16LVSC | LEAVITT STREET-34TH AVENUE SECURITY CAMERAS | 3 | CONSTRUCTION | 2017-01-23 | 2018-01-22 | 2017-01-23 | 2018-01-22
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM16LVSC | LEAVITT STREET-34TH AVENUE SECURITY CAMERAS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-01-23 | 2018-07-21 | 2017-01-23 | 2018-01-22
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM16LVSC | LEAVITT STREET-34TH AVENUE SECURITY CAMERAS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-01-23 | 2018-07-21 | 2018-01-23 | 2020-01-22
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM17BPSC | BAISLEY PARK INSTALLATION OF SECURITY CAMERAS | 1 | DESIGN | 2017-02-01 | 2017-07-30 | 2017-02-01 | 2017-07-30
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM17BPSC | BAISLEY PARK INSTALLATION OF SECURITY CAMERAS | 2 | BID AWARD AND REGISTER CONTRCT | 2017-07-31 | 2017-12-22 | 2017-07-31 | 2017-12-22
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM17BPSC | BAISLEY PARK INSTALLATION OF SECURITY CAMERAS | 3 | CONSTRUCTION | 2017-12-23 | 2018-12-22 | 2017-12-23 | 2018-12-22
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM17BPSC | BAISLEY PARK INSTALLATION OF SECURITY CAMERAS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-12-23 | 2019-06-20 | 2017-12-23 | 2018-12-22
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM17BPSC | BAISLEY PARK INSTALLATION OF SECURITY CAMERAS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-12-23 | 2019-06-20 | 2018-12-23 | 2020-12-21
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM17ILTV | International Towers - Security Cameras | 1 | DESIGN | 2017-02-01 | 2017-07-30 | 2017-02-01 | 2017-07-30
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM17ILTV | International Towers - Security Cameras | 2 | BID AWARD AND REGISTER CONTRCT | 2017-07-31 | 2017-12-22 | 2017-07-31 | 2017-12-22
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM17ILTV | International Towers - Security Cameras | 3 | CONSTRUCTION | 2017-12-23 | 2018-12-22 | 2017-12-23 | 2018-12-22
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM17ILTV | International Towers - Security Cameras | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-12-23 | 2019-06-20 | 2017-12-23 | 2018-12-22
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM17ILTV | International Towers - Security Cameras | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-12-23 | 2019-06-20 | 2018-12-23 | 2020-12-21
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM17LGPL | LATIMER GARDENS PLAYGROUND UPGRADE | 1 | DESIGN | 2017-02-01 | 2017-07-30 | 2017-02-01 | 2017-07-30
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM17LGPL | LATIMER GARDENS PLAYGROUND UPGRADE | 2 | BID AWARD AND REGISTER CONTRCT | 2017-07-31 | 2017-12-22 | 2017-07-31 | 2017-12-22
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM17LGPL | LATIMER GARDENS PLAYGROUND UPGRADE | 3 | CONSTRUCTION | 2017-12-23 | 2018-12-22 | 2017-12-23 | 2018-12-22
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM17LGPL | LATIMER GARDENS PLAYGROUND UPGRADE | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-12-23 | 2019-06-20 | 2017-12-23 | 2018-12-22
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM17LGPL | LATIMER GARDENS PLAYGROUND UPGRADE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-12-23 | 2019-06-20 | 2018-12-23 | 2020-12-21
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM18ASTV | CCTV AT ASTORIA HOUSES | 1 | DESIGN | 2018-01-02 | 2018-06-30 | 2018-01-02 | 2018-06-30
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM18ASTV | CCTV AT ASTORIA HOUSES | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM18ASTV | CCTV AT ASTORIA HOUSES | 3 | CONSTRUCTION | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM18ASTV | CCTV AT ASTORIA HOUSES | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-28 | 2020-06-24 | 2018-12-28 | 2019-12-27
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM18ASTV | CCTV AT ASTORIA HOUSES | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-28 | 2020-06-24 | 2019-12-28 | 2020-06-24
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM18BLGR | BLAND HOUSES GROUNDS BEAUTIFICATION | 1 | DESIGN | 2018-01-02 | 2018-06-30 | 2018-01-02 | 2018-06-30
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM18BLGR | BLAND HOUSES GROUNDS BEAUTIFICATION | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM18BLGR | BLAND HOUSES GROUNDS BEAUTIFICATION | 3 | CONSTRUCTION | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM18BLGR | BLAND HOUSES GROUNDS BEAUTIFICATION | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-28 | 2020-06-24 | 2018-12-28 | 2019-12-27
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM18BLGR | BLAND HOUSES GROUNDS BEAUTIFICATION | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-28 | 2020-06-24 | 2019-12-28 | 2020-06-24
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM18COTV | LAYERED SECURITY ACCESS AT CONLON LIFHE | 1 | DESIGN | 2018-01-02 | 2018-06-30 | 2018-01-02 | 2018-06-30
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM18COTV | LAYERED SECURITY ACCESS AT CONLON LIFHE | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM18COTV | LAYERED SECURITY ACCESS AT CONLON LIFHE | 3 | CONSTRUCTION | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM18COTV | LAYERED SECURITY ACCESS AT CONLON LIFHE | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-28 | 2020-06-24 | 2018-12-28 | 2019-12-27
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM18COTV | LAYERED SECURITY ACCESS AT CONLON LIFHE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-28 | 2020-06-24 | 2019-12-28 | 2020-06-24
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM19AHSC | ASTORIA HOUSES SECURITY CAMERAS | 1 | DESIGN | 2019-05-19 | 2019-11-14 | 2019-05-19 | 2019-11-14
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM19AHSC | ASTORIA HOUSES SECURITY CAMERAS | 2 | BID AWARD AND REGISTER CONTRCT | 2019-11-15 | 2020-05-12 | 2019-11-15 | 2020-05-12
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM19AHSC | ASTORIA HOUSES SECURITY CAMERAS | 3 | CONSTRUCTION | 2020-05-13 | 2021-05-12 | 2020-05-13 | 2021-05-12
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM19AHSC | ASTORIA HOUSES SECURITY CAMERAS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-05-13 | 2021-11-08 | 2020-05-13 | 2021-05-12
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM19AHSC | ASTORIA HOUSES SECURITY CAMERAS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-05-13 | 2021-11-08 | 2021-05-13 | 2021-11-08
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM19CLHS | CONLON LIFHE HVAC SYSTEM | 1 | DESIGN | 2018-10-15 | 2019-04-12 | 2018-10-15 | 2019-04-12
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM19CLHS | CONLON LIFHE HVAC SYSTEM | 2 | BID AWARD AND REGISTER CONTRCT | 2019-04-13 | 2019-10-09 | 2019-04-13 | 2019-10-09
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM19CLHS | CONLON LIFHE HVAC SYSTEM | 3 | CONSTRUCTION | 2019-10-10 | 2020-10-08 | 2019-10-10 | 2020-10-08
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM19CLHS | CONLON LIFHE HVAC SYSTEM | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-10-09 | 2021-04-06 | 2019-10-10 | 2020-10-08
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM19CLHS | CONLON LIFHE HVAC SYSTEM | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-10-09 | 2021-04-06 | 2020-10-09 | 2021-04-06
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM19WHRB | WOODSIDE HOUSES RENOVATION OF BOYS AND GIRLS BATHROOMS | 1 | DESIGN | 2018-11-30 | 2019-05-28 | 2018-11-30 | 2019-05-28
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM19WHRB | WOODSIDE HOUSES RENOVATION OF BOYS AND GIRLS BATHROOMS | 2 | BID AWARD AND REGISTER CONTRCT | 2019-05-29 | 2019-11-24 | 2019-05-29 | 2019-11-24
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM19WHRB | WOODSIDE HOUSES RENOVATION OF BOYS AND GIRLS BATHROOMS | 3 | CONSTRUCTION | 2019-11-25 | 2020-11-23 | 2019-11-25 | 2020-11-23
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM19WHRB | WOODSIDE HOUSES RENOVATION OF BOYS AND GIRLS BATHROOMS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-11-24 | 2021-05-22 | 2019-11-25 | 2020-11-23
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM19WHRB | WOODSIDE HOUSES RENOVATION OF BOYS AND GIRLS BATHROOMS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-11-24 | 2021-05-22 | 2020-11-24 | 2021-05-22
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM20ASGR | ASTORIA- GARDEN AND GROUNDS BEAUTIFICATION | 1 | DESIGN | 2018-01-02 | 2018-06-30 | 2018-01-02 | 2018-06-30
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM20ASGR | ASTORIA- GARDEN AND GROUNDS BEAUTIFICATION | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM20ASGR | ASTORIA- GARDEN AND GROUNDS BEAUTIFICATION | 3 | CONSTRUCTION | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM20ASGR | ASTORIA- GARDEN AND GROUNDS BEAUTIFICATION | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-28 | 2020-06-24 | 2018-12-28 | 2019-12-27
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM20ASGR | ASTORIA- GARDEN AND GROUNDS BEAUTIFICATION | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-28 | 2020-06-24 | 2019-12-28 | 2020-06-24
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM20BHCS | BAISLEY - CCTV CAMERA SYSTEM FOR ALL 27 BUILDINGS | 1 | DESIGN | 2018-01-02 | 2018-06-30 | 2018-01-02 | 2018-06-30
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM20BHCS | BAISLEY - CCTV CAMERA SYSTEM FOR ALL 27 BUILDINGS | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM20BHCS | BAISLEY - CCTV CAMERA SYSTEM FOR ALL 27 BUILDINGS | 3 | CONSTRUCTION | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM20BHCS | BAISLEY - CCTV CAMERA SYSTEM FOR ALL 27 BUILDINGS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-28 | 2020-06-24 | 2018-12-28 | 2019-12-27
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM20BHCS | BAISLEY - CCTV CAMERA SYSTEM FOR ALL 27 BUILDINGS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-28 | 2020-06-24 | 2019-12-28 | 2020-06-24
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM20BHLL | BLAND HOUSES- LED LIGHTING | 1 | DESIGN | 2018-01-02 | 2018-06-30 | 2018-01-02 | 2018-06-30
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM20BHLL | BLAND HOUSES- LED LIGHTING | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM20BHLL | BLAND HOUSES- LED LIGHTING | 3 | CONSTRUCTION | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM20BHLL | BLAND HOUSES- LED LIGHTING | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-28 | 2020-06-24 | 2018-12-28 | 2019-12-27
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM20BHLL | BLAND HOUSES- LED LIGHTING | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-28 | 2020-06-24 | 2019-12-28 | 2020-06-24
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM20JYCL | S JAMAICA - UPGRADE TO COMPUTER LAB AT YOUTH CENTER | 1 | DEVELOP SCOPE | 2019-09-01 | 2019-11-29 | 2019-09-01 | 2019-11-29
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM20JYCL | S JAMAICA - UPGRADE TO COMPUTER LAB AT YOUTH CENTER | 2 | PRELIMINARY DESIGN | 2019-11-30 | 2020-03-28 | 2019-11-30 | 2020-03-28
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM20JYCL | S JAMAICA - UPGRADE TO COMPUTER LAB AT YOUTH CENTER | 3 | FINAL DESIGN | 2020-03-29 | 2020-09-24 | 2020-03-29 | 2020-09-24
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM20JYCL | S JAMAICA - UPGRADE TO COMPUTER LAB AT YOUTH CENTER | 4 | BID AWARD AND REGISTER CONTRCT | 2020-09-25 | 2020-12-23 | 2020-09-25 | 2020-12-23
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM20JYCL | S JAMAICA - UPGRADE TO COMPUTER LAB AT YOUTH CENTER | 5 | CONSTRUCTION TO 25% | 2020-12-24 | 2021-04-22 | 2020-12-24 | 2021-04-22
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM20JYCL | S JAMAICA - UPGRADE TO COMPUTER LAB AT YOUTH CENTER | 6 | CONSTRUCTION TO 50% | 2021-04-23 | 2021-08-20 | 2021-04-23 | 2021-08-20
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM20JYCL | S JAMAICA - UPGRADE TO COMPUTER LAB AT YOUTH CENTER | 7 | CONSTRUCTION TO 75% | 2021-08-21 | 2021-12-18 | 2021-08-21 | 2021-12-18
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM20JYCL | S JAMAICA - UPGRADE TO COMPUTER LAB AT YOUTH CENTER | 8 | ORIGINAL EQUIP & FURNISHING | 2021-12-19 | 2022-03-18 | 2021-12-19 | 2022-03-18
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM20JYCL | S JAMAICA - UPGRADE TO COMPUTER LAB AT YOUTH CENTER | 9 | SUBSTANTIAL COMPLETION | 2022-03-19 | 2022-05-17 | 2022-03-19 | 2022-05-17
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM20JYCL | S JAMAICA - UPGRADE TO COMPUTER LAB AT YOUTH CENTER | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-05-18 | 2022-06-16 | 2022-05-18 | 2022-06-16
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM20LCSC | LEWIS H. LATIMER SECURITY CAMERAS AT SENIOR CENTER | 1 | DEVELOP SCOPE | 2020-09-01 | 2020-11-29 | 2020-09-01 | 2020-11-29
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM20LCSC | LEWIS H. LATIMER SECURITY CAMERAS AT SENIOR CENTER | 2 | PRELIMINARY DESIGN | 2020-11-30 | 2021-03-29 | 2020-11-30 | 2021-03-29
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM20LCSC | LEWIS H. LATIMER SECURITY CAMERAS AT SENIOR CENTER | 3 | FINAL DESIGN | 2021-03-30 | 2021-09-25 | 2021-03-30 | 2021-09-25
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM20LCSC | LEWIS H. LATIMER SECURITY CAMERAS AT SENIOR CENTER | 4 | BID AWARD AND REGISTER CONTRCT | 2021-09-26 | 2021-12-24 | 2021-09-26 | 2021-12-24
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM20LCSC | LEWIS H. LATIMER SECURITY CAMERAS AT SENIOR CENTER | 5 | CONSTRUCTION TO 25% | 2021-12-25 | 2022-04-23 | 2021-12-25 | 2022-04-23
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM20LCSC | LEWIS H. LATIMER SECURITY CAMERAS AT SENIOR CENTER | 6 | CONSTRUCTION TO 50% | 2022-04-24 | 2022-08-21 | 2022-04-24 | 2022-08-21
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM20LCSC | LEWIS H. LATIMER SECURITY CAMERAS AT SENIOR CENTER | 7 | CONSTRUCTION TO 75% | 2022-08-22 | 2022-12-19 | 2022-08-22 | 2022-12-19
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM20LCSC | LEWIS H. LATIMER SECURITY CAMERAS AT SENIOR CENTER | 8 | ORIGINAL EQUIP & FURNISHING | 2022-12-20 | 2023-03-19 | 2022-12-20 | 2023-03-19
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM20LCSC | LEWIS H. LATIMER SECURITY CAMERAS AT SENIOR CENTER | 9 | SUBSTANTIAL COMPLETION | 2023-03-20 | 2023-05-18 | 2023-03-20 | 2023-05-18
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM20LCSC | LEWIS H. LATIMER SECURITY CAMERAS AT SENIOR CENTER | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-05-19 | 2023-06-17 | 2023-05-19 | 2023-06-17
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM20RCCB | RAVENSWOOD COMMUNITY CENTER BATHROOMS | 1 | DESIGN | 2019-09-01 | 2020-02-27 | 2019-09-01 | 2020-02-27
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM20RCCB | RAVENSWOOD COMMUNITY CENTER BATHROOMS | 2 | BID AWARD AND REGISTER CONTRCT | 2020-02-28 | 2020-08-25 | 2020-02-28 | 2020-08-25
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM20RCCB | RAVENSWOOD COMMUNITY CENTER BATHROOMS | 3 | CONSTRUCTION | 2020-08-26 | 2021-08-25 | 2020-08-26 | 2021-08-25
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM20RCCB | RAVENSWOOD COMMUNITY CENTER BATHROOMS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-08-26 | 2022-02-21 | 2020-08-26 | 2021-08-25
20201123 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM20RCCB | RAVENSWOOD COMMUNITY CENTER BATHROOMS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-08-26 | 2022-02-21 | 2021-08-26 | 2022-02-21
20201123 | QUEENS | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | ACEDOH901 | DOHMH - Boiler Controls Upgrade at 3 DOHMH Health Centers | 1 | DESIGN | 2020-01-05 | 2020-07-02 | 2020-01-05 | 2020-07-02
20201123 | QUEENS | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | ACEDOH901 | DOHMH - Boiler Controls Upgrade at 3 DOHMH Health Centers | 2 | CONSTRUCTION | 2020-07-03 | 2020-12-29 | 2020-07-03 | 2020-12-29
20201123 | QUEENS | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | CMEQANNEX | OCME - Queens Annex Phase | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-09-28 | 2017-07-01 | 2017-09-28
20201123 | QUEENS | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | CMEQANNEX | OCME - Queens Annex Phase | 2 | PRELIMINARY DESIGN | 2017-09-29 | 2018-01-26 | 2017-09-29 | 2018-01-26
20201123 | QUEENS | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | CMEQANNEX | OCME - Queens Annex Phase | 3 | FINAL DESIGN | 2018-01-27 | 2018-07-25 | 2018-01-27 | 2018-07-25
20201123 | QUEENS | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | CMEQANNEX | OCME - Queens Annex Phase | 4 | BID AWARD AND REGISTER CONTRCT | 2018-07-26 | 2018-11-22 | 2018-07-26 | 2019-05-21
20201123 | QUEENS | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | CMEQANNEX | OCME - Queens Annex Phase | 5 | CONSTRUCTION TO 25% | 2018-11-23 | 2019-05-21 | 2019-05-22 | 2019-09-18
20201123 | QUEENS | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | CMEQANNEX | OCME - Queens Annex Phase | 6 | CONSTRUCTION TO 50% | 2019-05-22 | 2019-09-18 | 2019-09-19 | 2020-01-16
20201123 | QUEENS | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | CMEQANNEX | OCME - Queens Annex Phase | 7 | CONSTRUCTION TO 75% | 2019-09-19 | 2019-12-17 | 2020-01-17 | 2020-05-15
20201123 | QUEENS | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | CMEQANNEX | OCME - Queens Annex Phase | 8 | ORIGINAL EQUIP & FURNISHING | 2019-12-18 | 2020-03-26 | 2020-05-16 | 2020-08-13
20201123 | QUEENS | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | CMEQANNEX | OCME - Queens Annex Phase | 9 | SUBSTANTIAL COMPLETION | 2020-03-27 | 2020-06-04 | 2020-08-14 | 2020-11-01
20201123 | QUEENS | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | CMEQANNEX | OCME - Queens Annex Phase | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-06-05 | 2020-07-19 | 2020-11-02 | 2020-12-31
20201123 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 02201804 | LIC OUTFIT OFFICE SPACE | 1 | DESIGN | 2018-07-06 | 2019-01-01 | 2021-07-06 | 2022-01-01
20201123 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 02201804 | LIC OUTFIT OFFICE SPACE | 2 | CONSTRUCTION | 2019-01-02 | 2019-06-30 | 2022-01-02 | 2022-06-30
20201123 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33201301 | EHC: RENOVATION OF ADULT ER | 1 | DESIGN | 2016-02-09 | 2017-07-02 | 2016-02-09 | 2017-07-02
20201123 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33201301 | EHC: RENOVATION OF ADULT ER | 2 | CONSTRUCTION | 2017-07-03 | 2019-07-02 | 2017-07-03 | 2022-07-02
20201123 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33201301 | EHC: RENOVATION OF ADULT ER | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-07-03 | 2019-09-30 | 2022-07-03 | 2022-09-30
20201123 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33201505 | ELMHURST: PURCHASE & INSTALL BIPLANE/CT SCANNER | 1 | DESIGN | 2018-07-06 | 2019-01-01 | 2018-07-06 | 2019-01-01
20201123 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33201505 | ELMHURST: PURCHASE & INSTALL BIPLANE/CT SCANNER | 2 | CONSTRUCTION | 2019-01-02 | 2019-06-30 | 2019-01-02 | 2019-06-30
20201123 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33201602 | EHC PARAPET & CORNER FACADE REHAB A,B,D,E, J AND O&G ANNEX. | 1 | DESIGN | 2019-08-11 | 2020-06-30 | 2019-08-11 | 2020-06-30
20201123 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33201602 | EHC PARAPET & CORNER FACADE REHAB A,B,D,E, J AND O&G ANNEX. | 2 | CONSTRUCTION | 2020-07-01 | 2021-06-30 | 2019-08-11 | 2020-06-30
20201123 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33201602 | EHC PARAPET & CORNER FACADE REHAB A,B,D,E, J AND O&G ANNEX. | 3 | CONSTRUCTION | 2020-07-01 | 2021-06-30 | 2020-07-01 | 2021-06-30
20201123 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33201610 | RENOVATE JUNCTION BLVD CHILD HEALTH CLINIC | 1 | DESIGN | 2017-08-10 | 2018-06-30 | 2017-08-10 | 2018-06-30
20201123 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33201610 | RENOVATE JUNCTION BLVD CHILD HEALTH CLINIC | 2 | CONSTRUCTION | 2018-07-01 | 2022-06-30 | 2017-08-10 | 2018-06-30
20201123 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33201610 | RENOVATE JUNCTION BLVD CHILD HEALTH CLINIC | 3 | CONSTRUCTION | 2018-07-01 | 2022-06-30 | 2018-07-01 | 2022-06-30
20201123 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33201804 | ELMHURST: REHABILITATE N & S STAIRWELLS IN PARKING GARAGE | 1 | DESIGN | 2019-07-07 | 2020-01-02 | 2019-07-07 | 2020-01-02
20201123 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33201804 | ELMHURST: REHABILITATE N & S STAIRWELLS IN PARKING GARAGE | 2 | CONSTRUCTION | 2020-01-03 | 2020-06-30 | 2020-01-03 | 2021-06-30
20201123 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33201901 | EHC: L&D ROOMS AND MFM UNIT SUITE RENOVATIONS | 1 | DESIGN | 2019-07-07 | 2020-01-02 | 2019-07-07 | 2020-01-02
20201123 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33201901 | EHC: L&D ROOMS AND MFM UNIT SUITE RENOVATIONS | 2 | CONSTRUCTION | 2020-01-03 | 2022-06-30 | 2020-01-03 | 2022-06-30
20201123 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33202002 | ELMHURST: CONSTRUCT AMBULATORY CENTER | 1 | DESIGN | 2019-07-07 | 2020-11-27 | 2019-07-07 | 2020-11-27
20201123 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33202002 | ELMHURST: CONSTRUCT AMBULATORY CENTER | 2 | CONSTRUCTION | 2020-11-28 | 2023-11-27 | 2020-11-28 | 2023-11-27
20201123 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33202002 | ELMHURST: CONSTRUCT AMBULATORY CENTER | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-11-28 | 2024-02-25 | 2023-11-28 | 2024-02-25
20201123 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33202003 | ELMHURST: Upgrade of Emergency Electrical System | 1 | DESIGN | 2019-07-07 | 2020-11-27 | 2019-07-07 | 2020-11-27
20201123 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33202003 | ELMHURST: Upgrade of Emergency Electrical System | 2 | CONSTRUCTION | 2020-11-28 | 2023-11-27 | 2020-11-28 | 2023-11-27
20201123 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33202003 | ELMHURST: Upgrade of Emergency Electrical System | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-11-28 | 2024-02-25 | 2023-11-28 | 2024-02-25
20201123 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33202101 | Re-lining of Sub-Basement Water Lines | 1 | DESIGN | 2020-05-01 | 2021-09-22 | 2020-05-01 | 2021-09-22
20201123 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33202101 | Re-lining of Sub-Basement Water Lines | 2 | CONSTRUCTION | 2021-09-23 | 2023-09-22 | 2021-09-23 | 2023-09-22
20201123 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33202101 | Re-lining of Sub-Basement Water Lines | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-23 | 2023-12-21 | 2023-09-23 | 2023-12-21
20201123 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33202102 | ELMHURST: CONVERSION OF VACANT PYSCH UNIT 30 BED UNIT | 1 | DESIGN | 2020-05-01 | 2021-09-22 | 2020-05-01 | 2021-09-22
20201123 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33202102 | ELMHURST: CONVERSION OF VACANT PYSCH UNIT 30 BED UNIT | 2 | CONSTRUCTION | 2021-09-23 | 2023-09-22 | 2021-09-23 | 2023-09-22
20201123 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33202102 | ELMHURST: CONVERSION OF VACANT PYSCH UNIT 30 BED UNIT | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-23 | 2023-12-21 | 2023-09-23 | 2023-12-21
20201123 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33202103 | CAT LAB ROOF REPLACEMENT | 1 | DESIGN | 2020-05-01 | 2021-09-22 | 2020-05-01 | 2021-09-22
20201123 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33202103 | CAT LAB ROOF REPLACEMENT | 2 | CONSTRUCTION | 2021-09-23 | 2023-09-22 | 2021-09-23 | 2023-09-22
20201123 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33202103 | CAT LAB ROOF REPLACEMENT | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-23 | 2023-12-21 | 2023-09-23 | 2023-12-21
20201123 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33202104 | MODERNIZE FREIGHT ELEVATORS | 1 | DESIGN | 2020-05-01 | 2021-09-22 | 2020-05-01 | 2021-09-22
20201123 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33202104 | MODERNIZE FREIGHT ELEVATORS | 2 | CONSTRUCTION | 2021-09-23 | 2023-09-22 | 2021-09-23 | 2023-09-22
20201123 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33202104 | MODERNIZE FREIGHT ELEVATORS | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-23 | 2023-12-21 | 2023-09-23 | 2023-12-21
20201123 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33202105 | MODERNIZE ELEVATOR CARS 1-5, O AND G | 1 | DESIGN | 2020-05-01 | 2021-09-22 | 2020-05-01 | 2021-09-22
20201123 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33202105 | MODERNIZE ELEVATOR CARS 1-5, O AND G | 2 | CONSTRUCTION | 2021-09-23 | 2023-09-22 | 2021-09-23 | 2023-09-22
20201123 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33202105 | MODERNIZE ELEVATOR CARS 1-5, O AND G | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-23 | 2023-12-21 | 2023-09-23 | 2023-12-21
20201123 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 34200304 | QHC: EXPANSION OF DIABETES CENTER | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-10-04 | 2023-01-01 | 2022-10-04 | 2023-01-01
20201123 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 34201201 | QHC: "T" BUILDING RELOCATIONS | 1 | DESIGN | 2016-12-10 | 2017-10-30 | 2016-12-10 | 2017-10-30
20201123 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 34201201 | QHC: "T" BUILDING RELOCATIONS | 2 | CONSTRUCTION | 2017-10-31 | 2018-10-30 | 2016-12-10 | 2017-10-30
20201123 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 34201201 | QHC: "T" BUILDING RELOCATIONS | 3 | CONSTRUCTION | 2017-10-31 | 2018-10-30 | 2017-10-31 | 2023-10-30
20201123 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 34201401 | QHC: RENOVATIONS TO RELOCATE ACUTE DIALYSIS PROG. | 1 | DESIGN | 2015-01-06 | 2015-07-04 | 2016-01-06 | 2016-07-03
20201123 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 34201401 | QHC: RENOVATIONS TO RELOCATE ACUTE DIALYSIS PROG. | 2 | CONSTRUCTION | 2015-07-05 | 2015-12-31 | 2016-07-04 | 2016-12-30
20201123 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 34201401 | QHC: RENOVATIONS TO RELOCATE ACUTE DIALYSIS PROG. | 3 | DESIGN | 2015-07-05 | 2015-12-31 | 2016-12-31 | 2018-05-24
20201123 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 34201401 | QHC: RENOVATIONS TO RELOCATE ACUTE DIALYSIS PROG. | 4 | CONSTRUCTION | 2015-07-05 | 2015-12-31 | 2018-05-25 | 2020-05-23
20201123 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 34201401 | QHC: RENOVATIONS TO RELOCATE ACUTE DIALYSIS PROG. | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-07-05 | 2015-12-31 | 2020-05-24 | 2020-08-21
20201123 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 34201401 | QHC: RENOVATIONS TO RELOCATE ACUTE DIALYSIS PROG. | 6 | DESIGN | 2015-07-05 | 2015-12-31 | 2020-08-22 | 2022-01-13
20201123 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 34201401 | QHC: RENOVATIONS TO RELOCATE ACUTE DIALYSIS PROG. | 7 | CONSTRUCTION | 2015-07-05 | 2015-12-31 | 2022-01-14 | 2025-01-12
20201123 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 34201401 | QHC: RENOVATIONS TO RELOCATE ACUTE DIALYSIS PROG. | 8 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-07-05 | 2015-12-31 | 2025-01-13 | 2025-04-12
20201123 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 34201402 | QHC: RENOVATE/EXPAND ADULT EMERGENCY DEPARTMENT | 1 | DESIGN | 2015-04-07 | 2015-10-03 | 2015-04-07 | 2015-10-03
20201123 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 34201402 | QHC: RENOVATE/EXPAND ADULT EMERGENCY DEPARTMENT | 2 | CONSTRUCTION | 2015-10-04 | 2016-03-31 | 2015-10-04 | 2022-03-31
20201123 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 34201502 | QHC: BOILER CONTROLS REPLACEMENT | 1 | DESIGN | 2019-07-07 | 2020-01-02 | 2019-07-07 | 2020-01-02
20201123 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 34201502 | QHC: BOILER CONTROLS REPLACEMENT | 2 | CONSTRUCTION | 2020-01-03 | 2020-06-30 | 2020-01-03 | 2022-06-30
20201123 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 34201503 | QHC: EXPAND AND RENOVATE PHARMACY | 1 | DESIGN | 2019-07-07 | 2020-01-02 | 2019-07-07 | 2020-01-02
20201123 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 34201503 | QHC: EXPAND AND RENOVATE PHARMACY | 2 | CONSTRUCTION | 2020-01-03 | 2020-06-30 | 2020-01-03 | 2022-06-30
20201123 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 34201901 | QHC: SIDEWALK REPLACEMENT | 1 | DESIGN | 2018-07-06 | 2019-01-01 | 2018-07-06 | 2019-01-01
20201123 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 34201901 | QHC: SIDEWALK REPLACEMENT | 2 | CONSTRUCTION | 2019-01-02 | 2019-06-30 | 2019-01-02 | 2019-06-30
20201123 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 34202101 | CONSTRUCT PARKING GARAGE | 1 | DESIGN | 2020-05-01 | 2021-09-22 | 2020-05-01 | 2021-09-22
20201123 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 34202101 | CONSTRUCT PARKING GARAGE | 2 | CONSTRUCTION | 2021-09-23 | 2023-09-22 | 2021-09-23 | 2023-09-22
20201123 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 34202101 | CONSTRUCT PARKING GARAGE | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-23 | 2023-12-21 | 2023-09-23 | 2023-12-21
20201123 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 34202102 | BUILDING S AN F ROOF REPLACEMENT | 1 | DESIGN | 2020-05-01 | 2021-09-22 | 2020-05-01 | 2021-09-22
20201123 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 34202102 | BUILDING S AN F ROOF REPLACEMENT | 2 | CONSTRUCTION | 2021-09-23 | 2023-09-22 | 2021-09-23 | 2023-09-22
20201123 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 34202102 | BUILDING S AN F ROOF REPLACEMENT | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-23 | 2023-12-21 | 2023-09-23 | 2023-12-21
20201123 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | ACEHHC803 | NYC Health + Hospitals/Queens Energy Efficiency Upgrade | 1 | DESIGN | 2020-05-13 | 2021-10-04 | 2020-05-13 | 2021-10-04
20201123 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | ACEHHC803 | NYC Health + Hospitals/Queens Energy Efficiency Upgrade | 2 | CONSTRUCTION | 2021-10-05 | 2024-10-03 | 2021-10-05 | 2024-10-03
20201123 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | ACEHHC803 | NYC Health + Hospitals/Queens Energy Efficiency Upgrade | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-10-04 | 2025-01-01 | 2024-10-04 | 2025-01-01
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | ACEDEP601 | DEP - LED LIGHTING AT CATSKILL DELAWARE UV FACILITY | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-06-30 | 2020-06-01 | 2020-06-30
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | ACEDEP601 | DEP - LED LIGHTING AT CATSKILL DELAWARE UV FACILITY | 2 | BID AWARD AND REGISTER CONTRCT | 2020-07-01 | 2020-08-29 | 2020-07-01 | 2020-08-29
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | ACEDEP601 | DEP - LED LIGHTING AT CATSKILL DELAWARE UV FACILITY | 3 | CONSTRUCTION TO 50% | 2020-08-30 | 2021-02-25 | 2020-08-30 | 2021-02-25
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | ACEDEP601 | DEP - LED LIGHTING AT CATSKILL DELAWARE UV FACILITY | 4 | CONSTRUCTION TO 75% | 2021-02-26 | 2021-05-26 | 2021-02-26 | 2021-05-26
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | ACEDEP601 | DEP - LED LIGHTING AT CATSKILL DELAWARE UV FACILITY | 5 | SUBSTANTIAL COMPLETION | 2021-05-27 | 2021-07-25 | 2021-05-27 | 2021-07-25
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | ACEDEP601 | DEP - LED LIGHTING AT CATSKILL DELAWARE UV FACILITY | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-07-26 | 2021-08-24 | 2021-07-26 | 2021-08-24
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB06-01-A | GI - ON SITE CONSTRUCTION FOR GREEN INFRASTRUCTURE IN BB-006 | 1 | FINAL DESIGN | 2018-06-01 | 2019-11-22 | 2018-06-01 | 2019-11-22
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB06-01-A | GI - ON SITE CONSTRUCTION FOR GREEN INFRASTRUCTURE IN BB-006 | 2 | CONSTRUCTION TO 25% | 2019-11-23 | 2020-07-19 | 2019-11-23 | 2020-07-19
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB06-01-A | GI - ON SITE CONSTRUCTION FOR GREEN INFRASTRUCTURE IN BB-006 | 3 | CONSTRUCTION TO 50% | 2020-07-20 | 2021-03-16 | 2020-07-20 | 2021-03-16
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB06-01-A | GI - ON SITE CONSTRUCTION FOR GREEN INFRASTRUCTURE IN BB-006 | 4 | CONSTRUCTION TO 75% | 2021-03-17 | 2021-11-11 | 2021-03-17 | 2021-11-11
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-205-L | RECONS. CBS/PBS SYSTEM AT BOWERY BAY WPCP (TOC JOB) | 1 | DEVELOP SCOPE | 2008-03-01 | 2008-05-29 | 2014-01-15 | 2014-10-11
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-205-L | RECONS. CBS/PBS SYSTEM AT BOWERY BAY WPCP (TOC JOB) | 2 | PRELIMINARY DESIGN | 2008-05-30 | 2008-09-26 | 2014-10-12 | 2015-10-06
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-205-L | RECONS. CBS/PBS SYSTEM AT BOWERY BAY WPCP (TOC JOB) | 3 | FINAL DESIGN | 2008-09-27 | 2009-03-25 | 2015-10-07 | 2017-03-29
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-205-L | RECONS. CBS/PBS SYSTEM AT BOWERY BAY WPCP (TOC JOB) | 4 | BID AWARD AND REGISTER CONTRCT | 2009-03-26 | 2009-06-23 | 2017-03-30 | 2017-12-24
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-205-L | RECONS. CBS/PBS SYSTEM AT BOWERY BAY WPCP (TOC JOB) | 5 | CONSTRUCTION TO 25% | 2009-06-24 | 2009-10-21 | 2017-12-25 | 2018-12-19
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-205-L | RECONS. CBS/PBS SYSTEM AT BOWERY BAY WPCP (TOC JOB) | 6 | CONSTRUCTION TO 50% | 2009-10-22 | 2010-02-18 | 2018-12-20 | 2019-12-14
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-205-L | RECONS. CBS/PBS SYSTEM AT BOWERY BAY WPCP (TOC JOB) | 7 | CONSTRUCTION TO 75% | 2010-02-19 | 2010-06-18 | 2019-12-15 | 2020-12-08
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-205-L | RECONS. CBS/PBS SYSTEM AT BOWERY BAY WPCP (TOC JOB) | 8 | ORIGINAL EQUIP & FURNISHING | 2010-06-19 | 2010-09-16 | 2020-12-09 | 2021-09-04
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-205-L | RECONS. CBS/PBS SYSTEM AT BOWERY BAY WPCP (TOC JOB) | 9 | SUBSTANTIAL COMPLETION | 2010-09-17 | 2010-11-15 | 2021-09-05 | 2022-03-03
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-205-L | RECONS. CBS/PBS SYSTEM AT BOWERY BAY WPCP (TOC JOB) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2010-11-16 | 2010-12-15 | 2022-03-04 | 2022-06-01
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-216-L | RECONSTRUCTION OF PRIMARY TANKS AT BOWERY BAY WPCP | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-09-28 | 2019-01-15 | 2019-10-11
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-216-L | RECONSTRUCTION OF PRIMARY TANKS AT BOWERY BAY WPCP | 2 | PRELIMINARY DESIGN | 2017-09-29 | 2018-01-26 | 2019-10-12 | 2020-10-05
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-216-L | RECONSTRUCTION OF PRIMARY TANKS AT BOWERY BAY WPCP | 3 | FINAL DESIGN | 2018-01-27 | 2018-07-25 | 2020-10-06 | 2022-03-29
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-216-L | RECONSTRUCTION OF PRIMARY TANKS AT BOWERY BAY WPCP | 4 | BID AWARD AND REGISTER CONTRCT | 2018-07-26 | 2018-10-23 | 2022-03-30 | 2022-12-24
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-216-L | RECONSTRUCTION OF PRIMARY TANKS AT BOWERY BAY WPCP | 5 | CONSTRUCTION TO 25% | 2018-10-24 | 2019-02-20 | 2022-12-25 | 2023-12-19
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-216-L | RECONSTRUCTION OF PRIMARY TANKS AT BOWERY BAY WPCP | 6 | CONSTRUCTION TO 50% | 2019-02-21 | 2019-06-20 | 2023-12-20 | 2024-12-13
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-216-L | RECONSTRUCTION OF PRIMARY TANKS AT BOWERY BAY WPCP | 7 | CONSTRUCTION TO 75% | 2019-06-21 | 2019-10-18 | 2024-12-14 | 2025-12-08
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-216-L | RECONSTRUCTION OF PRIMARY TANKS AT BOWERY BAY WPCP | 8 | ORIGINAL EQUIP & FURNISHING | 2019-10-19 | 2020-01-16 | 2025-12-09 | 2026-09-04
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-216-L | RECONSTRUCTION OF PRIMARY TANKS AT BOWERY BAY WPCP | 9 | SUBSTANTIAL COMPLETION | 2020-01-17 | 2020-03-16 | 2026-09-05 | 2027-03-03
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-216-L | RECONSTRUCTION OF PRIMARY TANKS AT BOWERY BAY WPCP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-03-17 | 2020-04-15 | 2027-03-04 | 2027-06-01
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-220-L | REPLACEMENT OF EXISTING EMERGENCY GENERATORS @ BOWERY BAY | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-09-28 | 2015-07-01 | 2015-09-28
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-220-L | REPLACEMENT OF EXISTING EMERGENCY GENERATORS @ BOWERY BAY | 2 | PRELIMINARY DESIGN | 2017-09-29 | 2018-01-26 | 2015-09-29 | 2016-01-26
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-220-L | REPLACEMENT OF EXISTING EMERGENCY GENERATORS @ BOWERY BAY | 3 | FINAL DESIGN | 2018-01-27 | 2018-07-25 | 2016-01-27 | 2016-07-24
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-220-L | REPLACEMENT OF EXISTING EMERGENCY GENERATORS @ BOWERY BAY | 4 | BID AWARD AND REGISTER CONTRCT | 2018-07-26 | 2018-10-23 | 2016-07-25 | 2016-10-22
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-220-L | REPLACEMENT OF EXISTING EMERGENCY GENERATORS @ BOWERY BAY | 5 | CONSTRUCTION TO 25% | 2018-10-24 | 2019-02-20 | 2016-10-23 | 2017-02-19
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-220-L | REPLACEMENT OF EXISTING EMERGENCY GENERATORS @ BOWERY BAY | 6 | CONSTRUCTION TO 50% | 2019-02-21 | 2019-06-20 | 2017-02-20 | 2017-06-19
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-220-L | REPLACEMENT OF EXISTING EMERGENCY GENERATORS @ BOWERY BAY | 7 | CONSTRUCTION TO 75% | 2019-06-21 | 2019-10-18 | 2017-06-20 | 2023-10-17
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-220-L | REPLACEMENT OF EXISTING EMERGENCY GENERATORS @ BOWERY BAY | 8 | ORIGINAL EQUIP & FURNISHING | 2019-10-19 | 2020-01-16 | 2023-10-18 | 2024-01-15
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-220-L | REPLACEMENT OF EXISTING EMERGENCY GENERATORS @ BOWERY BAY | 9 | SUBSTANTIAL COMPLETION | 2020-01-17 | 2020-03-16 | 2024-01-16 | 2024-03-15
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-220-L | REPLACEMENT OF EXISTING EMERGENCY GENERATORS @ BOWERY BAY | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-03-17 | 2020-04-15 | 2024-03-16 | 2024-04-14
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-239-L | INSTALL NEW WASTE ACTIVATED SLUDGE PUMPS @ BOWERY BAY WWTP | 1 | FINAL DESIGN | 2022-06-01 | 2023-11-22 | 2022-06-01 | 2023-11-22
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-239-L | INSTALL NEW WASTE ACTIVATED SLUDGE PUMPS @ BOWERY BAY WWTP | 2 | CONSTRUCTION TO 25% | 2023-11-23 | 2024-07-19 | 2023-11-23 | 2024-07-19
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-239-L | INSTALL NEW WASTE ACTIVATED SLUDGE PUMPS @ BOWERY BAY WWTP | 3 | CONSTRUCTION TO 50% | 2024-07-20 | 2025-03-16 | 2024-07-20 | 2025-03-16
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-239-L | INSTALL NEW WASTE ACTIVATED SLUDGE PUMPS @ BOWERY BAY WWTP | 4 | CONSTRUCTION TO 75% | 2025-03-17 | 2025-11-11 | 2025-03-17 | 2025-11-11
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-64 | MSP Discharge Piping/Controls at Bowery Bay WPCP | 1 | DEVELOP SCOPE | 2013-05-01 | 2014-01-25 | 2013-05-01 | 2014-01-25
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-64 | MSP Discharge Piping/Controls at Bowery Bay WPCP | 2 | PRELIMINARY DESIGN | 2014-01-26 | 2015-01-20 | 2014-01-26 | 2015-01-20
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-64 | MSP Discharge Piping/Controls at Bowery Bay WPCP | 3 | FINAL DESIGN | 2015-01-21 | 2016-07-13 | 2015-01-21 | 2016-07-13
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-64 | MSP Discharge Piping/Controls at Bowery Bay WPCP | 4 | BID AWARD AND REGISTER CONTRCT | 2016-07-14 | 2017-04-09 | 2016-07-14 | 2017-04-09
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-64 | MSP Discharge Piping/Controls at Bowery Bay WPCP | 5 | CONSTRUCTION TO 25% | 2017-04-10 | 2018-04-04 | 2017-04-10 | 2018-04-04
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-64 | MSP Discharge Piping/Controls at Bowery Bay WPCP | 6 | CONSTRUCTION TO 50% | 2018-04-05 | 2019-03-30 | 2018-04-05 | 2019-03-30
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-64 | MSP Discharge Piping/Controls at Bowery Bay WPCP | 7 | CONSTRUCTION TO 75% | 2019-03-31 | 2020-03-24 | 2019-03-31 | 2020-03-24
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-64 | MSP Discharge Piping/Controls at Bowery Bay WPCP | 8 | ORIGINAL EQUIP & FURNISHING | 2020-03-25 | 2020-12-19 | 2020-03-25 | 2020-12-19
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-64 | MSP Discharge Piping/Controls at Bowery Bay WPCP | 9 | SUBSTANTIAL COMPLETION | 2020-12-20 | 2021-06-17 | 2020-12-20 | 2021-06-17
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-64 | MSP Discharge Piping/Controls at Bowery Bay WPCP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-06-18 | 2021-09-15 | 2021-06-18 | 2021-09-15
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | C540 | Completion of CT3 Stage 2 B/Q Leg & Bklyn Downtake Intercon. | 1 | DEVELOP SCOPE | 2007-07-15 | 2008-04-09 | 2017-06-17 | 2018-03-13
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | C540 | Completion of CT3 Stage 2 B/Q Leg & Bklyn Downtake Intercon. | 2 | PRELIMINARY DESIGN | 2008-04-10 | 2009-04-04 | 2018-03-14 | 2019-03-08
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | C540 | Completion of CT3 Stage 2 B/Q Leg & Bklyn Downtake Intercon. | 3 | FINAL DESIGN | 2009-04-05 | 2010-09-26 | 2019-03-09 | 2020-08-29
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | C540 | Completion of CT3 Stage 2 B/Q Leg & Bklyn Downtake Intercon. | 4 | BID AWARD AND REGISTER CONTRCT | 2010-09-27 | 2011-06-23 | 2020-08-30 | 2021-05-26
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | C540 | Completion of CT3 Stage 2 B/Q Leg & Bklyn Downtake Intercon. | 5 | CONSTRUCTION TO 25% | 2011-06-24 | 2012-06-17 | 2021-05-27 | 2022-05-21
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | C540 | Completion of CT3 Stage 2 B/Q Leg & Bklyn Downtake Intercon. | 6 | CONSTRUCTION TO 50% | 2012-06-18 | 2013-06-12 | 2022-05-22 | 2023-05-16
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | C540 | Completion of CT3 Stage 2 B/Q Leg & Bklyn Downtake Intercon. | 7 | CONSTRUCTION TO 75% | 2013-06-13 | 2014-06-07 | 2023-05-17 | 2024-05-10
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | C540 | Completion of CT3 Stage 2 B/Q Leg & Bklyn Downtake Intercon. | 8 | ORIGINAL EQUIP & FURNISHING | 2014-06-08 | 2015-03-04 | 2024-05-11 | 2025-02-04
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | C540 | Completion of CT3 Stage 2 B/Q Leg & Bklyn Downtake Intercon. | 9 | SUBSTANTIAL COMPLETION | 2015-03-05 | 2015-08-31 | 2025-02-05 | 2025-08-03
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | C540 | Completion of CT3 Stage 2 B/Q Leg & Bklyn Downtake Intercon. | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-09-01 | 2015-11-29 | 2025-08-04 | 2025-11-01
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-AC-EBP | RESTORATION OF 1.5 ACRE WETLAND IN ALLEY CREEK | 1 | DEVELOP SCOPE | 2017-12-01 | 2018-02-28 | 2017-12-01 | 2018-02-28
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-AC-EBP | RESTORATION OF 1.5 ACRE WETLAND IN ALLEY CREEK | 2 | PRELIMINARY DESIGN | 2018-03-01 | 2018-06-28 | 2018-03-01 | 2018-06-28
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-AC-EBP | RESTORATION OF 1.5 ACRE WETLAND IN ALLEY CREEK | 3 | FINAL DESIGN | 2018-06-29 | 2018-12-25 | 2018-06-29 | 2018-12-25
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-AC-EBP | RESTORATION OF 1.5 ACRE WETLAND IN ALLEY CREEK | 4 | BID AWARD AND REGISTER CONTRCT | 2018-12-26 | 2019-03-25 | 2018-12-26 | 2019-03-25
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-AC-EBP | RESTORATION OF 1.5 ACRE WETLAND IN ALLEY CREEK | 5 | CONSTRUCTION TO 25% | 2019-03-26 | 2019-07-23 | 2019-03-26 | 2019-07-23
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-AC-EBP | RESTORATION OF 1.5 ACRE WETLAND IN ALLEY CREEK | 6 | CONSTRUCTION TO 50% | 2019-07-24 | 2019-11-20 | 2019-07-24 | 2019-11-20
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-AC-EBP | RESTORATION OF 1.5 ACRE WETLAND IN ALLEY CREEK | 7 | CONSTRUCTION TO 75% | 2019-11-21 | 2020-03-19 | 2019-11-21 | 2020-03-19
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-AC-EBP | RESTORATION OF 1.5 ACRE WETLAND IN ALLEY CREEK | 8 | ORIGINAL EQUIP & FURNISHING | 2020-03-20 | 2020-06-17 | 2020-03-20 | 2020-06-17
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-AC-EBP | RESTORATION OF 1.5 ACRE WETLAND IN ALLEY CREEK | 9 | SUBSTANTIAL COMPLETION | 2020-06-18 | 2020-08-16 | 2020-06-18 | 2020-08-16
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-AC-EBP | RESTORATION OF 1.5 ACRE WETLAND IN ALLEY CREEK | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-08-17 | 2020-09-15 | 2020-08-17 | 2020-09-15
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-FB-BWR | FLUSHING BAY BENDING WEIRS AT REGULATORS | 1 | DEVELOP SCOPE | 2011-06-01 | 2011-12-02 | 2014-05-06 | 2014-11-06
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-FB-BWR | FLUSHING BAY BENDING WEIRS AT REGULATORS | 2 | PRELIMINARY DESIGN | 2011-12-03 | 2013-05-31 | 2014-11-07 | 2016-05-05
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-FB-BWR | FLUSHING BAY BENDING WEIRS AT REGULATORS | 3 | FINAL DESIGN | 2013-06-01 | 2014-05-31 | 2016-05-06 | 2017-05-05
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-FB-BWR | FLUSHING BAY BENDING WEIRS AT REGULATORS | 4 | BID AWARD AND REGISTER CONTRCT | 2014-06-01 | 2015-03-02 | 2017-05-06 | 2018-02-04
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-FB-BWR | FLUSHING BAY BENDING WEIRS AT REGULATORS | 5 | CONSTRUCTION TO 25% | 2015-03-03 | 2015-12-02 | 2018-02-05 | 2018-11-06
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-FB-BWR | FLUSHING BAY BENDING WEIRS AT REGULATORS | 6 | CONSTRUCTION TO 50% | 2015-12-03 | 2016-08-31 | 2018-11-07 | 2019-08-06
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-FB-BWR | FLUSHING BAY BENDING WEIRS AT REGULATORS | 7 | CONSTRUCTION TO 75% | 2016-09-01 | 2017-02-27 | 2019-08-07 | 2020-02-02
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-FB-BWR | FLUSHING BAY BENDING WEIRS AT REGULATORS | 8 | ORIGINAL EQUIP & FURNISHING | 2017-02-28 | 2017-06-27 | 2020-02-03 | 2020-06-01
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-FB-BWR | FLUSHING BAY BENDING WEIRS AT REGULATORS | 9 | SUBSTANTIAL COMPLETION | 2017-06-28 | 2018-06-27 | 2020-06-02 | 2021-06-01
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-FB-BWR | FLUSHING BAY BENDING WEIRS AT REGULATORS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-06-28 | 2019-06-27 | 2021-06-02 | 2022-06-01
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-JA-BWR | JAMAICA BAY BENDING WEIRS AT REGULATORS | 1 | DEVELOP SCOPE | 2013-08-12 | 2013-11-09 | 2019-08-17 | 2019-11-14
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-JA-BWR | JAMAICA BAY BENDING WEIRS AT REGULATORS | 2 | PRELIMINARY DESIGN | 2013-11-10 | 2014-03-09 | 2019-11-15 | 2020-03-13
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-JA-BWR | JAMAICA BAY BENDING WEIRS AT REGULATORS | 3 | FINAL DESIGN | 2014-03-10 | 2014-09-05 | 2020-03-14 | 2020-09-09
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-JA-BWR | JAMAICA BAY BENDING WEIRS AT REGULATORS | 4 | BID AWARD AND REGISTER CONTRCT | 2014-09-06 | 2014-12-04 | 2020-09-10 | 2020-12-08
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-JA-BWR | JAMAICA BAY BENDING WEIRS AT REGULATORS | 5 | CONSTRUCTION TO 25% | 2014-12-05 | 2015-04-03 | 2020-12-09 | 2021-04-07
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-JA-BWR | JAMAICA BAY BENDING WEIRS AT REGULATORS | 6 | CONSTRUCTION TO 50% | 2015-04-04 | 2015-08-01 | 2021-04-08 | 2021-08-05
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-JA-BWR | JAMAICA BAY BENDING WEIRS AT REGULATORS | 7 | CONSTRUCTION TO 75% | 2015-08-02 | 2015-11-29 | 2021-08-06 | 2021-12-03
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-JA-BWR | JAMAICA BAY BENDING WEIRS AT REGULATORS | 8 | ORIGINAL EQUIP & FURNISHING | 2015-11-30 | 2016-02-27 | 2021-12-04 | 2022-03-03
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-JA-BWR | JAMAICA BAY BENDING WEIRS AT REGULATORS | 9 | SUBSTANTIAL COMPLETION | 2016-02-28 | 2016-04-27 | 2022-03-04 | 2022-05-02
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-JA-BWR | JAMAICA BAY BENDING WEIRS AT REGULATORS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-04-28 | 2016-05-27 | 2022-05-03 | 2022-06-01
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-NC-BAP | BORDEN AVENUE PUMP STATION EXPANSION | 1 | DEVELOP SCOPE | 2020-05-01 | 2021-01-25 | 2020-05-01 | 2021-01-25
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-NC-BAP | BORDEN AVENUE PUMP STATION EXPANSION | 2 | PRELIMINARY DESIGN | 2021-01-26 | 2022-01-20 | 2021-01-26 | 2022-01-20
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-NC-BAP | BORDEN AVENUE PUMP STATION EXPANSION | 3 | FINAL DESIGN | 2022-01-21 | 2023-07-14 | 2022-01-21 | 2023-07-14
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-NC-BAP | BORDEN AVENUE PUMP STATION EXPANSION | 4 | BID AWARD AND REGISTER CONTRCT | 2023-07-15 | 2024-04-09 | 2023-07-15 | 2024-04-09
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-NC-BAP | BORDEN AVENUE PUMP STATION EXPANSION | 5 | CONSTRUCTION TO 25% | 2024-04-10 | 2025-04-04 | 2024-04-10 | 2025-04-04
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-NC-BAP | BORDEN AVENUE PUMP STATION EXPANSION | 6 | CONSTRUCTION TO 50% | 2025-04-05 | 2026-03-30 | 2025-04-05 | 2026-03-30
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-NC-BAP | BORDEN AVENUE PUMP STATION EXPANSION | 7 | CONSTRUCTION TO 75% | 2026-03-31 | 2027-03-25 | 2026-03-31 | 2027-03-25
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-NC-BAP | BORDEN AVENUE PUMP STATION EXPANSION | 8 | ORIGINAL EQUIP & FURNISHING | 2027-03-26 | 2027-12-20 | 2027-03-26 | 2027-12-20
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-NC-BAP | BORDEN AVENUE PUMP STATION EXPANSION | 9 | SUBSTANTIAL COMPLETION | 2027-12-21 | 2028-06-17 | 2027-12-21 | 2028-06-17
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-NC-BAP | BORDEN AVENUE PUMP STATION EXPANSION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2028-06-18 | 2028-09-15 | 2028-06-18 | 2028-09-15
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-NC-EKE | ENGLISH KILLS AERATION, ENHANCED ZONE II | 1 | DEVELOP SCOPE | 2013-06-15 | 2014-03-11 | 1990-06-01 | 1991-02-25
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-NC-EKE | ENGLISH KILLS AERATION, ENHANCED ZONE II | 2 | PRELIMINARY DESIGN | 2014-03-12 | 2015-03-06 | 1991-02-26 | 1994-02-09
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-NC-EKE | ENGLISH KILLS AERATION, ENHANCED ZONE II | 3 | FINAL DESIGN | 2015-03-07 | 2016-08-27 | 1994-02-10 | 2000-01-09
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-NC-EKE | ENGLISH KILLS AERATION, ENHANCED ZONE II | 4 | BID AWARD AND REGISTER CONTRCT | 2016-08-28 | 2017-05-24 | 2000-01-10 | 2005-05-12
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-NC-EKE | ENGLISH KILLS AERATION, ENHANCED ZONE II | 5 | CONSTRUCTION TO 25% | 2017-05-25 | 2018-05-19 | 2005-05-13 | 2011-06-10
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-NC-EKE | ENGLISH KILLS AERATION, ENHANCED ZONE II | 6 | CONSTRUCTION TO 50% | 2018-05-20 | 2019-05-14 | 2011-06-11 | 2013-07-29
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-NC-EKE | ENGLISH KILLS AERATION, ENHANCED ZONE II | 7 | CONSTRUCTION TO 75% | 2019-05-15 | 2020-05-08 | 2013-07-30 | 2018-11-10
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-NC-EKE | ENGLISH KILLS AERATION, ENHANCED ZONE II | 8 | ORIGINAL EQUIP & FURNISHING | 2020-05-09 | 2021-02-02 | 2018-11-11 | 2019-11-05
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-NC-EKE | ENGLISH KILLS AERATION, ENHANCED ZONE II | 9 | SUBSTANTIAL COMPLETION | 2021-02-03 | 2021-08-01 | 2019-11-06 | 2021-02-27
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-NC-EKE | ENGLISH KILLS AERATION, ENHANCED ZONE II | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-08-02 | 2021-10-30 | 2021-02-28 | 2021-10-25
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-FC-DF | CSO FLUSHING CREEK & TI-011 DISINFECTION | 1 | DEVELOP SCOPE | 2017-07-01 | 2018-03-27 | 2017-07-01 | 2018-03-27
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-FC-DF | CSO FLUSHING CREEK & TI-011 DISINFECTION | 2 | PRELIMINARY DESIGN | 2018-03-28 | 2019-03-22 | 2018-03-28 | 2019-03-22
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-FC-DF | CSO FLUSHING CREEK & TI-011 DISINFECTION | 3 | FINAL DESIGN | 2019-03-23 | 2020-09-12 | 2019-03-23 | 2020-09-12
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-FC-DF | CSO FLUSHING CREEK & TI-011 DISINFECTION | 4 | BID AWARD AND REGISTER CONTRCT | 2020-09-13 | 2021-06-09 | 2020-09-13 | 2021-06-09
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-FC-DF | CSO FLUSHING CREEK & TI-011 DISINFECTION | 5 | CONSTRUCTION TO 25% | 2021-06-10 | 2022-06-04 | 2021-06-10 | 2022-06-04
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-FC-DF | CSO FLUSHING CREEK & TI-011 DISINFECTION | 6 | CONSTRUCTION TO 50% | 2022-06-05 | 2023-05-30 | 2022-06-05 | 2023-05-30
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-FC-DF | CSO FLUSHING CREEK & TI-011 DISINFECTION | 7 | CONSTRUCTION TO 75% | 2023-05-31 | 2024-05-24 | 2023-05-31 | 2024-05-24
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-FC-DF | CSO FLUSHING CREEK & TI-011 DISINFECTION | 8 | ORIGINAL EQUIP & FURNISHING | 2024-05-25 | 2025-02-18 | 2024-05-25 | 2025-02-18
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-FC-DF | CSO FLUSHING CREEK & TI-011 DISINFECTION | 9 | SUBSTANTIAL COMPLETION | 2025-02-19 | 2025-08-17 | 2025-02-19 | 2025-08-17
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-FC-DF | CSO FLUSHING CREEK & TI-011 DISINFECTION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-08-18 | 2025-11-15 | 2025-08-18 | 2025-11-15
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-JA | JAMAICA WATER QUALITY COMBINED SEWER OVERLOW | 1 | DEVELOP SCOPE | 1993-10-15 | 1994-07-11 | 2001-09-30 | 2002-06-26
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-JA | JAMAICA WATER QUALITY COMBINED SEWER OVERLOW | 2 | PRELIMINARY DESIGN | 1994-07-12 | 1995-07-06 | 2002-06-27 | 2003-06-21
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-JA | JAMAICA WATER QUALITY COMBINED SEWER OVERLOW | 3 | FINAL DESIGN | 1995-07-07 | 1996-12-27 | 2003-06-22 | 2004-12-12
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-JA | JAMAICA WATER QUALITY COMBINED SEWER OVERLOW | 4 | BID AWARD AND REGISTER CONTRCT | 1996-12-28 | 1997-09-23 | 2004-12-13 | 2005-09-08
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-JA | JAMAICA WATER QUALITY COMBINED SEWER OVERLOW | 5 | CONSTRUCTION TO 25% | 1997-09-24 | 1998-09-18 | 2005-09-09 | 2006-09-03
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-JA | JAMAICA WATER QUALITY COMBINED SEWER OVERLOW | 6 | CONSTRUCTION TO 50% | 1998-09-19 | 1999-09-13 | 2006-09-04 | 2007-08-29
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-JA | JAMAICA WATER QUALITY COMBINED SEWER OVERLOW | 7 | CONSTRUCTION TO 75% | 1999-09-14 | 2000-09-07 | 2007-08-30 | 2008-08-23
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-JA | JAMAICA WATER QUALITY COMBINED SEWER OVERLOW | 8 | ORIGINAL EQUIP & FURNISHING | 2000-09-08 | 2001-06-04 | 2008-08-24 | 2009-05-20
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-JA | JAMAICA WATER QUALITY COMBINED SEWER OVERLOW | 9 | SUBSTANTIAL COMPLETION | 2001-06-05 | 2001-12-01 | 2009-05-21 | 2021-11-13
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-JA | JAMAICA WATER QUALITY COMBINED SEWER OVERLOW | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2001-12-02 | 2002-03-01 | 2021-11-14 | 2022-06-01
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | DMCCSG | REPLACE SWITCHEARS & MCCS AT DOUGLASTON PS | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2016-03-26
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | DMCCSG | REPLACE SWITCHEARS & MCCS AT DOUGLASTON PS | 2 | PRELIMINARY DESIGN | 2015-09-29 | 2016-01-26 | 2016-03-27 | 2017-03-21
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | DMCCSG | REPLACE SWITCHEARS & MCCS AT DOUGLASTON PS | 3 | FINAL DESIGN | 2016-01-27 | 2016-07-24 | 2017-03-22 | 2018-09-12
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | DMCCSG | REPLACE SWITCHEARS & MCCS AT DOUGLASTON PS | 4 | BID AWARD AND REGISTER CONTRCT | 2016-07-25 | 2016-10-22 | 2018-09-13 | 2019-06-09
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | DMCCSG | REPLACE SWITCHEARS & MCCS AT DOUGLASTON PS | 5 | CONSTRUCTION TO 25% | 2016-10-23 | 2017-02-19 | 2019-06-10 | 2020-06-03
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | DMCCSG | REPLACE SWITCHEARS & MCCS AT DOUGLASTON PS | 6 | CONSTRUCTION TO 50% | 2017-02-20 | 2017-06-19 | 2020-06-04 | 2021-05-29
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | DMCCSG | REPLACE SWITCHEARS & MCCS AT DOUGLASTON PS | 7 | CONSTRUCTION TO 75% | 2017-06-20 | 2017-10-17 | 2021-05-30 | 2022-05-24
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | DMCCSG | REPLACE SWITCHEARS & MCCS AT DOUGLASTON PS | 8 | ORIGINAL EQUIP & FURNISHING | 2017-10-18 | 2018-01-15 | 2022-05-25 | 2023-02-18
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | DMCCSG | REPLACE SWITCHEARS & MCCS AT DOUGLASTON PS | 9 | SUBSTANTIAL COMPLETION | 2018-01-16 | 2018-03-16 | 2023-02-19 | 2023-08-17
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | DMCCSG | REPLACE SWITCHEARS & MCCS AT DOUGLASTON PS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-03-17 | 2018-04-15 | 2023-08-18 | 2023-11-15
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SEQN22 | Reconstruction of Existing Sewers, North Queens | 1 | DEVELOP SCOPE | 2020-11-09 | 2021-02-06 | 2020-11-09 | 2021-02-06
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SEQN22 | Reconstruction of Existing Sewers, North Queens | 2 | PRELIMINARY DESIGN | 2021-02-07 | 2021-06-06 | 2021-02-07 | 2021-06-06
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SEQN22 | Reconstruction of Existing Sewers, North Queens | 3 | FINAL DESIGN | 2021-06-07 | 2021-12-03 | 2021-06-07 | 2021-12-03
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SEQN22 | Reconstruction of Existing Sewers, North Queens | 4 | BID AWARD AND REGISTER CONTRCT | 2021-12-04 | 2022-03-03 | 2021-12-04 | 2022-03-03
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SEQN22 | Reconstruction of Existing Sewers, North Queens | 5 | CONSTRUCTION TO 25% | 2022-03-04 | 2022-07-01 | 2022-03-04 | 2022-07-01
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SEQN22 | Reconstruction of Existing Sewers, North Queens | 6 | CONSTRUCTION TO 50% | 2022-07-02 | 2022-10-29 | 2022-07-02 | 2022-10-29
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SEQN22 | Reconstruction of Existing Sewers, North Queens | 7 | CONSTRUCTION TO 75% | 2022-10-30 | 2023-02-26 | 2022-10-30 | 2023-02-26
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SEQN22 | Reconstruction of Existing Sewers, North Queens | 8 | ORIGINAL EQUIP & FURNISHING | 2023-02-27 | 2023-05-27 | 2023-02-27 | 2023-05-27
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SEQN22 | Reconstruction of Existing Sewers, North Queens | 9 | SUBSTANTIAL COMPLETION | 2023-05-28 | 2023-07-26 | 2023-05-28 | 2023-07-26
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SEQN22 | Reconstruction of Existing Sewers, North Queens | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-07-27 | 2023-08-25 | 2023-07-27 | 2023-08-25
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | FB-001-L | UPGRADE OF FLUSHING BAY CSO FACILITY BAR SCREEN SYSTEM | 1 | DEVELOP SCOPE | 2015-06-30 | 2015-09-27 | 2015-06-30 | 2016-03-25
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | FB-001-L | UPGRADE OF FLUSHING BAY CSO FACILITY BAR SCREEN SYSTEM | 2 | PRELIMINARY DESIGN | 2015-09-28 | 2016-01-25 | 2016-03-26 | 2017-03-20
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | FB-001-L | UPGRADE OF FLUSHING BAY CSO FACILITY BAR SCREEN SYSTEM | 3 | FINAL DESIGN | 2016-01-26 | 2016-07-23 | 2017-03-21 | 2018-09-11
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | FB-001-L | UPGRADE OF FLUSHING BAY CSO FACILITY BAR SCREEN SYSTEM | 4 | BID AWARD AND REGISTER CONTRCT | 2016-07-24 | 2016-10-21 | 2018-09-12 | 2019-06-08
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | FB-001-L | UPGRADE OF FLUSHING BAY CSO FACILITY BAR SCREEN SYSTEM | 5 | CONSTRUCTION TO 25% | 2016-10-22 | 2017-02-18 | 2019-06-09 | 2020-06-02
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | FB-001-L | UPGRADE OF FLUSHING BAY CSO FACILITY BAR SCREEN SYSTEM | 6 | CONSTRUCTION TO 50% | 2017-02-19 | 2017-06-18 | 2020-06-03 | 2021-05-28
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | FB-001-L | UPGRADE OF FLUSHING BAY CSO FACILITY BAR SCREEN SYSTEM | 7 | CONSTRUCTION TO 75% | 2017-06-19 | 2017-10-16 | 2021-05-29 | 2022-05-23
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | FB-001-L | UPGRADE OF FLUSHING BAY CSO FACILITY BAR SCREEN SYSTEM | 8 | ORIGINAL EQUIP & FURNISHING | 2017-10-17 | 2018-01-14 | 2022-05-24 | 2023-02-17
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | FB-001-L | UPGRADE OF FLUSHING BAY CSO FACILITY BAR SCREEN SYSTEM | 9 | SUBSTANTIAL COMPLETION | 2018-01-15 | 2018-03-15 | 2023-02-18 | 2023-08-16
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | FB-001-L | UPGRADE OF FLUSHING BAY CSO FACILITY BAR SCREEN SYSTEM | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-03-16 | 2018-04-14 | 2023-08-17 | 2023-11-14
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | FCWET | CONSTRUCTION OF FLUSHING CREEK WETLAND PROJECT | 1 | DEVELOP SCOPE | 2022-06-15 | 2023-03-11 | 2022-06-15 | 2023-03-11
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | FCWET | CONSTRUCTION OF FLUSHING CREEK WETLAND PROJECT | 2 | PRELIMINARY DESIGN | 2023-03-12 | 2024-03-05 | 2023-03-12 | 2024-03-05
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | FCWET | CONSTRUCTION OF FLUSHING CREEK WETLAND PROJECT | 3 | FINAL DESIGN | 2024-03-06 | 2025-08-27 | 2024-03-06 | 2025-08-27
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | FCWET | CONSTRUCTION OF FLUSHING CREEK WETLAND PROJECT | 4 | BID AWARD AND REGISTER CONTRCT | 2025-08-28 | 2026-05-24 | 2025-08-28 | 2026-05-24
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | FCWET | CONSTRUCTION OF FLUSHING CREEK WETLAND PROJECT | 5 | CONSTRUCTION TO 25% | 2026-05-25 | 2027-05-19 | 2026-05-25 | 2027-05-19
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | FCWET | CONSTRUCTION OF FLUSHING CREEK WETLAND PROJECT | 6 | CONSTRUCTION TO 50% | 2027-05-20 | 2028-05-13 | 2027-05-20 | 2028-05-13
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | FCWET | CONSTRUCTION OF FLUSHING CREEK WETLAND PROJECT | 7 | CONSTRUCTION TO 75% | 2028-05-14 | 2029-05-08 | 2028-05-14 | 2029-05-08
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | FCWET | CONSTRUCTION OF FLUSHING CREEK WETLAND PROJECT | 8 | ORIGINAL EQUIP & FURNISHING | 2029-05-09 | 2030-02-02 | 2029-05-09 | 2030-02-02
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | FCWET | CONSTRUCTION OF FLUSHING CREEK WETLAND PROJECT | 9 | SUBSTANTIAL COMPLETION | 2030-02-03 | 2030-08-01 | 2030-02-03 | 2030-08-01
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | FCWET | CONSTRUCTION OF FLUSHING CREEK WETLAND PROJECT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2030-08-02 | 2030-10-30 | 2030-08-02 | 2030-10-30
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | GCTI10-1C | CONS OF ROW GI FLUSHING CREEK CSO TRIB AREA TI-10, ST 1 PH C | 1 | DEVELOP SCOPE | 2021-06-15 | 2022-03-11 | 2021-06-15 | 2022-03-11
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | GCTI10-1C | CONS OF ROW GI FLUSHING CREEK CSO TRIB AREA TI-10, ST 1 PH C | 2 | PRELIMINARY DESIGN | 2022-03-12 | 2023-03-06 | 2022-03-12 | 2023-03-06
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | GCTI10-1C | CONS OF ROW GI FLUSHING CREEK CSO TRIB AREA TI-10, ST 1 PH C | 3 | FINAL DESIGN | 2023-03-07 | 2024-08-27 | 2023-03-07 | 2024-08-27
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | GCTI10-1C | CONS OF ROW GI FLUSHING CREEK CSO TRIB AREA TI-10, ST 1 PH C | 4 | BID AWARD AND REGISTER CONTRCT | 2024-08-28 | 2025-05-24 | 2024-08-28 | 2025-05-24
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | GCTI10-1C | CONS OF ROW GI FLUSHING CREEK CSO TRIB AREA TI-10, ST 1 PH C | 5 | CONSTRUCTION TO 25% | 2025-05-25 | 2026-05-19 | 2025-05-25 | 2026-05-19
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | GCTI10-1C | CONS OF ROW GI FLUSHING CREEK CSO TRIB AREA TI-10, ST 1 PH C | 6 | CONSTRUCTION TO 50% | 2026-05-20 | 2027-05-14 | 2026-05-20 | 2027-05-14
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | GCTI10-1C | CONS OF ROW GI FLUSHING CREEK CSO TRIB AREA TI-10, ST 1 PH C | 7 | CONSTRUCTION TO 75% | 2027-05-15 | 2028-05-08 | 2027-05-15 | 2028-05-08
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | GCTI10-1C | CONS OF ROW GI FLUSHING CREEK CSO TRIB AREA TI-10, ST 1 PH C | 8 | ORIGINAL EQUIP & FURNISHING | 2028-05-09 | 2029-02-02 | 2028-05-09 | 2029-02-02
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | GCTI10-1C | CONS OF ROW GI FLUSHING CREEK CSO TRIB AREA TI-10, ST 1 PH C | 9 | SUBSTANTIAL COMPLETION | 2029-02-03 | 2029-08-01 | 2029-02-03 | 2029-08-01
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | GCTI10-1C | CONS OF ROW GI FLUSHING CREEK CSO TRIB AREA TI-10, ST 1 PH C | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2029-08-02 | 2029-10-30 | 2029-08-02 | 2029-10-30
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | JA-179-L | INSTALLATION OF EMERGENCY GENERATORS AT JAMAICA WPCP | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2017-06-01 | 2018-02-25
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | JA-179-L | INSTALLATION OF EMERGENCY GENERATORS AT JAMAICA WPCP | 2 | PRELIMINARY DESIGN | 2015-09-29 | 2016-01-26 | 2018-02-26 | 2019-02-20
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | JA-179-L | INSTALLATION OF EMERGENCY GENERATORS AT JAMAICA WPCP | 3 | FINAL DESIGN | 2016-01-27 | 2016-07-24 | 2019-02-21 | 2020-08-13
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | JA-179-L | INSTALLATION OF EMERGENCY GENERATORS AT JAMAICA WPCP | 4 | BID AWARD AND REGISTER CONTRCT | 2016-07-25 | 2016-10-22 | 2020-08-14 | 2021-05-10
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | JA-179-L | INSTALLATION OF EMERGENCY GENERATORS AT JAMAICA WPCP | 5 | CONSTRUCTION TO 25% | 2016-10-23 | 2017-02-19 | 2021-05-11 | 2022-05-05
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | JA-179-L | INSTALLATION OF EMERGENCY GENERATORS AT JAMAICA WPCP | 6 | CONSTRUCTION TO 50% | 2017-02-20 | 2017-06-19 | 2022-05-06 | 2023-04-30
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | JA-179-L | INSTALLATION OF EMERGENCY GENERATORS AT JAMAICA WPCP | 7 | CONSTRUCTION TO 75% | 2017-06-20 | 2017-10-17 | 2023-05-01 | 2024-04-24
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | JA-179-L | INSTALLATION OF EMERGENCY GENERATORS AT JAMAICA WPCP | 8 | ORIGINAL EQUIP & FURNISHING | 2017-10-18 | 2018-01-15 | 2024-04-25 | 2025-01-19
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | JA-179-L | INSTALLATION OF EMERGENCY GENERATORS AT JAMAICA WPCP | 9 | SUBSTANTIAL COMPLETION | 2018-01-16 | 2018-03-16 | 2025-01-20 | 2025-07-18
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | JA-179-L | INSTALLATION OF EMERGENCY GENERATORS AT JAMAICA WPCP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-03-17 | 2018-04-15 | 2025-07-19 | 2025-10-16
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | JA-179-L | INSTALLATION OF EMERGENCY GENERATORS AT JAMAICA WPCP | 11 | DEVELOP SCOPE | 2018-04-16 | 2019-01-10 | 2025-07-19 | 2025-10-16
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | JA-179-L | INSTALLATION OF EMERGENCY GENERATORS AT JAMAICA WPCP | 12 | PRELIMINARY DESIGN | 2019-01-11 | 2020-01-05 | 2025-07-19 | 2025-10-16
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | JA-179-L | INSTALLATION OF EMERGENCY GENERATORS AT JAMAICA WPCP | 13 | FINAL DESIGN | 2020-01-06 | 2021-06-28 | 2025-07-19 | 2025-10-16
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | JA-179-L | INSTALLATION OF EMERGENCY GENERATORS AT JAMAICA WPCP | 14 | BID AWARD AND REGISTER CONTRCT | 2021-06-29 | 2022-03-25 | 2025-07-19 | 2025-10-16
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | JA-179-L | INSTALLATION OF EMERGENCY GENERATORS AT JAMAICA WPCP | 15 | CONSTRUCTION TO 25% | 2022-03-26 | 2023-03-20 | 2025-07-19 | 2025-10-16
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | JA-179-L | INSTALLATION OF EMERGENCY GENERATORS AT JAMAICA WPCP | 16 | CONSTRUCTION TO 50% | 2023-03-21 | 2024-03-14 | 2025-07-19 | 2025-10-16
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | JA-179-L | INSTALLATION OF EMERGENCY GENERATORS AT JAMAICA WPCP | 17 | CONSTRUCTION TO 75% | 2024-03-15 | 2025-03-09 | 2025-07-19 | 2025-10-16
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | JA-179-L | INSTALLATION OF EMERGENCY GENERATORS AT JAMAICA WPCP | 18 | ORIGINAL EQUIP & FURNISHING | 2025-03-10 | 2025-12-04 | 2025-07-19 | 2025-10-16
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | JA-179-L | INSTALLATION OF EMERGENCY GENERATORS AT JAMAICA WPCP | 19 | SUBSTANTIAL COMPLETION | 2025-12-05 | 2026-06-02 | 2025-07-19 | 2025-10-16
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | JA-179-L | INSTALLATION OF EMERGENCY GENERATORS AT JAMAICA WPCP | 20 | PUNCHLIST COMPLETE, JOB CLOSED | 2026-06-03 | 2026-08-31 | 2025-07-19 | 2025-10-16
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | JA-STAB | STABILIZATION PROGRAM AT JAMAICA WPCP | 1 | DEVELOP SCOPE | 1993-11-15 | 1994-08-11 | 2005-01-18 | 2005-10-14
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | JA-STAB | STABILIZATION PROGRAM AT JAMAICA WPCP | 2 | PRELIMINARY DESIGN | 1994-08-12 | 1995-08-06 | 2005-10-15 | 2006-10-09
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | JA-STAB | STABILIZATION PROGRAM AT JAMAICA WPCP | 3 | FINAL DESIGN | 1995-08-07 | 1997-01-27 | 2006-10-10 | 2008-04-01
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | JA-STAB | STABILIZATION PROGRAM AT JAMAICA WPCP | 4 | BID AWARD AND REGISTER CONTRCT | 1997-01-28 | 1997-10-24 | 2008-04-02 | 2008-12-27
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | JA-STAB | STABILIZATION PROGRAM AT JAMAICA WPCP | 5 | CONSTRUCTION TO 25% | 1997-10-25 | 1998-10-19 | 2008-12-28 | 2009-12-22
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | JA-STAB | STABILIZATION PROGRAM AT JAMAICA WPCP | 6 | CONSTRUCTION TO 50% | 1998-10-20 | 1999-10-14 | 2009-12-23 | 2010-12-17
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | JA-STAB | STABILIZATION PROGRAM AT JAMAICA WPCP | 7 | CONSTRUCTION TO 75% | 1999-10-15 | 2000-10-08 | 2010-12-18 | 2011-12-12
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | JA-STAB | STABILIZATION PROGRAM AT JAMAICA WPCP | 8 | ORIGINAL EQUIP & FURNISHING | 2000-10-09 | 2001-07-05 | 2011-12-13 | 2012-09-07
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | JA-STAB | STABILIZATION PROGRAM AT JAMAICA WPCP | 9 | SUBSTANTIAL COMPLETION | 2001-07-06 | 2002-01-01 | 2012-09-08 | 2025-03-03
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | JA-STAB | STABILIZATION PROGRAM AT JAMAICA WPCP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2002-01-02 | 2002-04-01 | 2025-03-04 | 2025-06-01
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | JFK-INTER | REROUTING OF INTERCEPTOR AT NEW JFK CARGO BUILDIING | 1 | FINAL DESIGN | 2021-06-01 | 2022-11-22 | 2021-06-01 | 2022-11-22
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | JFK-INTER | REROUTING OF INTERCEPTOR AT NEW JFK CARGO BUILDIING | 2 | CONSTRUCTION TO 25% | 2022-11-23 | 2023-07-20 | 2022-11-23 | 2023-07-20
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | JFK-INTER | REROUTING OF INTERCEPTOR AT NEW JFK CARGO BUILDIING | 3 | CONSTRUCTION TO 50% | 2023-07-21 | 2024-03-16 | 2023-07-21 | 2024-03-16
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | JFK-INTER | REROUTING OF INTERCEPTOR AT NEW JFK CARGO BUILDIING | 4 | CONSTRUCTION TO 75% | 2024-03-17 | 2024-11-11 | 2024-03-17 | 2024-11-11
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | MASPETH | RECONSTRUCTION OF BUILDING, MASPETH, QUEENS | 1 | DEVELOP SCOPE | 2004-09-15 | 2005-01-12 | 2020-06-15 | 2020-10-12
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | MASPETH | RECONSTRUCTION OF BUILDING, MASPETH, QUEENS | 2 | PRELIMINARY DESIGN | 2005-01-13 | 2005-07-11 | 2020-10-13 | 2021-04-10
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | MASPETH | RECONSTRUCTION OF BUILDING, MASPETH, QUEENS | 3 | FINAL DESIGN | 2005-07-12 | 2007-01-12 | 2021-04-11 | 2022-10-12
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | MASPETH | RECONSTRUCTION OF BUILDING, MASPETH, QUEENS | 4 | BID AWARD AND REGISTER CONTRCT | 2007-01-13 | 2007-07-11 | 2022-10-13 | 2023-04-10
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | MASPETH | RECONSTRUCTION OF BUILDING, MASPETH, QUEENS | 5 | CONSTRUCTION TO 25% | 2007-07-12 | 2008-04-16 | 2023-04-11 | 2024-01-15
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | MASPETH | RECONSTRUCTION OF BUILDING, MASPETH, QUEENS | 6 | CONSTRUCTION TO 50% | 2008-04-17 | 2009-01-21 | 2024-01-16 | 2024-10-21
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | MASPETH | RECONSTRUCTION OF BUILDING, MASPETH, QUEENS | 7 | CONSTRUCTION TO 75% | 2009-01-22 | 2009-10-28 | 2024-10-22 | 2025-07-28
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | MASPETH | RECONSTRUCTION OF BUILDING, MASPETH, QUEENS | 8 | ORIGINAL EQUIP & FURNISHING | 2009-10-29 | 2010-01-26 | 2025-07-29 | 2025-10-26
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | MASPETH | RECONSTRUCTION OF BUILDING, MASPETH, QUEENS | 9 | SUBSTANTIAL COMPLETION | 2010-01-27 | 2010-03-27 | 2025-10-27 | 2025-12-25
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | MASPETH | RECONSTRUCTION OF BUILDING, MASPETH, QUEENS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2010-03-28 | 2010-06-25 | 2025-12-26 | 2026-03-25
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-277 | RECONSTRUCTION AT 108 STREET PUMPING STATION | 1 | DEVELOP SCOPE | 2017-07-01 | 2018-03-27 | 2017-07-01 | 2018-03-27
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-277 | RECONSTRUCTION AT 108 STREET PUMPING STATION | 2 | PRELIMINARY DESIGN | 2018-03-28 | 2019-03-22 | 2018-03-28 | 2019-03-22
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-277 | RECONSTRUCTION AT 108 STREET PUMPING STATION | 3 | FINAL DESIGN | 2019-03-23 | 2020-09-12 | 2019-03-23 | 2020-09-12
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-277 | RECONSTRUCTION AT 108 STREET PUMPING STATION | 4 | BID AWARD AND REGISTER CONTRCT | 2020-09-13 | 2021-06-09 | 2020-09-13 | 2021-06-09
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-277 | RECONSTRUCTION AT 108 STREET PUMPING STATION | 5 | CONSTRUCTION TO 25% | 2021-06-10 | 2022-06-04 | 2021-06-10 | 2022-06-04
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-277 | RECONSTRUCTION AT 108 STREET PUMPING STATION | 6 | CONSTRUCTION TO 50% | 2022-06-05 | 2023-05-30 | 2022-06-05 | 2023-05-30
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-277 | RECONSTRUCTION AT 108 STREET PUMPING STATION | 7 | CONSTRUCTION TO 75% | 2023-05-31 | 2024-05-24 | 2023-05-31 | 2024-05-24
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-277 | RECONSTRUCTION AT 108 STREET PUMPING STATION | 8 | ORIGINAL EQUIP & FURNISHING | 2024-05-25 | 2025-02-18 | 2024-05-25 | 2025-02-18
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-277 | RECONSTRUCTION AT 108 STREET PUMPING STATION | 9 | SUBSTANTIAL COMPLETION | 2025-02-19 | 2025-08-17 | 2025-02-19 | 2025-08-17
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-277 | RECONSTRUCTION AT 108 STREET PUMPING STATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-08-18 | 2025-11-15 | 2025-08-18 | 2025-11-15
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-284 | CLEARVIEW PUMPING STATION | 1 | DEVELOP SCOPE | 2015-12-22 | 2016-09-16 | 2015-12-22 | 2016-09-16
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-284 | CLEARVIEW PUMPING STATION | 2 | PRELIMINARY DESIGN | 2016-09-17 | 2017-09-11 | 2016-09-17 | 2017-09-11
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-284 | CLEARVIEW PUMPING STATION | 3 | FINAL DESIGN | 2017-09-12 | 2019-03-05 | 2017-09-12 | 2019-03-05
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-284 | CLEARVIEW PUMPING STATION | 4 | BID AWARD AND REGISTER CONTRCT | 2019-03-06 | 2019-11-30 | 2019-03-06 | 2019-11-30
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-284 | CLEARVIEW PUMPING STATION | 5 | CONSTRUCTION TO 25% | 2019-12-01 | 2020-11-24 | 2019-12-01 | 2020-11-24
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-284 | CLEARVIEW PUMPING STATION | 6 | CONSTRUCTION TO 50% | 2020-11-25 | 2021-11-19 | 2020-11-25 | 2021-11-19
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-284 | CLEARVIEW PUMPING STATION | 7 | CONSTRUCTION TO 75% | 2021-11-20 | 2022-11-14 | 2021-11-20 | 2022-11-14
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-284 | CLEARVIEW PUMPING STATION | 8 | ORIGINAL EQUIP & FURNISHING | 2022-11-15 | 2023-08-11 | 2022-11-15 | 2023-08-11
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-284 | CLEARVIEW PUMPING STATION | 9 | SUBSTANTIAL COMPLETION | 2023-08-12 | 2024-02-07 | 2023-08-12 | 2024-02-07
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-284 | CLEARVIEW PUMPING STATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-02-08 | 2024-05-07 | 2024-02-08 | 2024-05-07
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-285 | RIKERS ISLAND NORTH AND SOUTH PUMPING STATION | 1 | DEVELOP SCOPE | 2016-07-01 | 2017-03-27 | 2016-07-01 | 2017-03-27
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-285 | RIKERS ISLAND NORTH AND SOUTH PUMPING STATION | 2 | PRELIMINARY DESIGN | 2017-03-28 | 2018-03-22 | 2017-03-28 | 2018-03-22
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-285 | RIKERS ISLAND NORTH AND SOUTH PUMPING STATION | 3 | FINAL DESIGN | 2018-03-23 | 2019-09-13 | 2018-03-23 | 2019-09-13
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-285 | RIKERS ISLAND NORTH AND SOUTH PUMPING STATION | 4 | BID AWARD AND REGISTER CONTRCT | 2019-09-14 | 2020-06-09 | 2019-09-14 | 2020-06-09
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-285 | RIKERS ISLAND NORTH AND SOUTH PUMPING STATION | 5 | CONSTRUCTION TO 25% | 2020-06-10 | 2021-06-04 | 2020-06-10 | 2021-06-04
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-285 | RIKERS ISLAND NORTH AND SOUTH PUMPING STATION | 6 | CONSTRUCTION TO 50% | 2021-06-05 | 2022-05-30 | 2021-06-05 | 2022-05-30
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-285 | RIKERS ISLAND NORTH AND SOUTH PUMPING STATION | 7 | CONSTRUCTION TO 75% | 2022-05-31 | 2023-05-25 | 2022-05-31 | 2023-05-25
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-285 | RIKERS ISLAND NORTH AND SOUTH PUMPING STATION | 8 | ORIGINAL EQUIP & FURNISHING | 2023-05-26 | 2024-02-19 | 2023-05-26 | 2024-02-19
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-285 | RIKERS ISLAND NORTH AND SOUTH PUMPING STATION | 9 | SUBSTANTIAL COMPLETION | 2024-02-20 | 2024-08-17 | 2024-02-20 | 2024-08-17
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-285 | RIKERS ISLAND NORTH AND SOUTH PUMPING STATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-08-18 | 2024-11-15 | 2024-08-18 | 2024-11-15
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-286 | ST ALBANS PUMPING STATION | 1 | DEVELOP SCOPE | 2016-07-01 | 2017-03-27 | 2016-07-01 | 2017-03-27
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-286 | ST ALBANS PUMPING STATION | 2 | PRELIMINARY DESIGN | 2017-03-28 | 2018-03-22 | 2017-03-28 | 2018-03-22
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-286 | ST ALBANS PUMPING STATION | 3 | FINAL DESIGN | 2018-03-23 | 2019-09-13 | 2018-03-23 | 2019-09-13
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-286 | ST ALBANS PUMPING STATION | 4 | BID AWARD AND REGISTER CONTRCT | 2019-09-14 | 2020-06-09 | 2019-09-14 | 2020-06-09
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-286 | ST ALBANS PUMPING STATION | 5 | CONSTRUCTION TO 25% | 2020-06-10 | 2021-06-04 | 2020-06-10 | 2021-06-04
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-286 | ST ALBANS PUMPING STATION | 6 | CONSTRUCTION TO 50% | 2021-06-05 | 2022-05-30 | 2021-06-05 | 2022-05-30
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-286 | ST ALBANS PUMPING STATION | 7 | CONSTRUCTION TO 75% | 2022-05-31 | 2023-05-25 | 2022-05-31 | 2023-05-25
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-286 | ST ALBANS PUMPING STATION | 8 | ORIGINAL EQUIP & FURNISHING | 2023-05-26 | 2024-02-19 | 2023-05-26 | 2024-02-19
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-286 | ST ALBANS PUMPING STATION | 9 | SUBSTANTIAL COMPLETION | 2024-02-20 | 2024-08-17 | 2024-02-20 | 2024-08-17
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-286 | ST ALBANS PUMPING STATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-08-18 | 2024-11-15 | 2024-08-18 | 2024-11-15
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-291 | 154TH STREET PUMPING STATION | 1 | DEVELOP SCOPE | 2020-06-01 | 2021-02-25 | 2019-06-01 | 2020-02-25
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-291 | 154TH STREET PUMPING STATION | 2 | PRELIMINARY DESIGN | 2021-02-26 | 2022-02-20 | 2020-02-26 | 2021-02-19
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-291 | 154TH STREET PUMPING STATION | 3 | FINAL DESIGN | 2022-02-21 | 2023-08-14 | 2021-02-20 | 2022-08-13
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-291 | 154TH STREET PUMPING STATION | 4 | BID AWARD AND REGISTER CONTRCT | 2023-08-15 | 2024-05-10 | 2022-08-14 | 2023-05-10
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-291 | 154TH STREET PUMPING STATION | 5 | CONSTRUCTION TO 25% | 2024-05-11 | 2025-05-05 | 2023-05-11 | 2024-05-04
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-291 | 154TH STREET PUMPING STATION | 6 | CONSTRUCTION TO 50% | 2025-05-06 | 2026-04-30 | 2024-05-05 | 2025-04-29
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-291 | 154TH STREET PUMPING STATION | 7 | CONSTRUCTION TO 75% | 2026-05-01 | 2027-04-25 | 2025-04-30 | 2026-04-24
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-291 | 154TH STREET PUMPING STATION | 8 | ORIGINAL EQUIP & FURNISHING | 2027-04-26 | 2028-01-20 | 2026-04-25 | 2027-01-19
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-291 | 154TH STREET PUMPING STATION | 9 | SUBSTANTIAL COMPLETION | 2028-01-21 | 2028-07-18 | 2027-01-20 | 2027-07-18
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-291 | 154TH STREET PUMPING STATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2028-07-19 | 2028-10-16 | 2027-07-19 | 2027-10-16
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-292 | RECONSTRUCTIONOF LINDEN PLACE PUMPING STATION | 1 | DEVELOP SCOPE | 2016-07-01 | 2017-03-27 | 2016-07-01 | 2017-03-27
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-292 | RECONSTRUCTIONOF LINDEN PLACE PUMPING STATION | 2 | PRELIMINARY DESIGN | 2017-03-28 | 2018-03-22 | 2017-03-28 | 2018-03-22
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-292 | RECONSTRUCTIONOF LINDEN PLACE PUMPING STATION | 3 | FINAL DESIGN | 2018-03-23 | 2019-09-13 | 2018-03-23 | 2019-09-13
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-292 | RECONSTRUCTIONOF LINDEN PLACE PUMPING STATION | 4 | BID AWARD AND REGISTER CONTRCT | 2019-09-14 | 2020-06-09 | 2019-09-14 | 2020-06-09
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-292 | RECONSTRUCTIONOF LINDEN PLACE PUMPING STATION | 5 | CONSTRUCTION TO 25% | 2020-06-10 | 2021-06-04 | 2020-06-10 | 2021-06-04
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-292 | RECONSTRUCTIONOF LINDEN PLACE PUMPING STATION | 6 | CONSTRUCTION TO 50% | 2021-06-05 | 2022-05-30 | 2021-06-05 | 2022-05-30
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-292 | RECONSTRUCTIONOF LINDEN PLACE PUMPING STATION | 7 | CONSTRUCTION TO 75% | 2022-05-31 | 2023-05-25 | 2022-05-31 | 2023-05-25
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-292 | RECONSTRUCTIONOF LINDEN PLACE PUMPING STATION | 8 | ORIGINAL EQUIP & FURNISHING | 2023-05-26 | 2024-02-19 | 2023-05-26 | 2024-02-19
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-292 | RECONSTRUCTIONOF LINDEN PLACE PUMPING STATION | 9 | SUBSTANTIAL COMPLETION | 2024-02-20 | 2024-08-17 | 2024-02-20 | 2024-08-17
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-292 | RECONSTRUCTIONOF LINDEN PLACE PUMPING STATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-08-18 | 2024-11-15 | 2024-08-18 | 2024-11-15
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-293 | RECONSTRUCTION AT HOWARD BEACH PUMPING STATION | 1 | DEVELOP SCOPE | 2022-06-01 | 2023-02-25 | 2018-07-01 | 2019-03-27
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-293 | RECONSTRUCTION AT HOWARD BEACH PUMPING STATION | 2 | PRELIMINARY DESIGN | 2023-02-26 | 2024-02-20 | 2019-03-28 | 2020-03-21
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-293 | RECONSTRUCTION AT HOWARD BEACH PUMPING STATION | 3 | FINAL DESIGN | 2024-02-21 | 2025-08-13 | 2020-03-22 | 2021-09-12
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-293 | RECONSTRUCTION AT HOWARD BEACH PUMPING STATION | 4 | BID AWARD AND REGISTER CONTRCT | 2025-08-14 | 2026-05-10 | 2021-09-13 | 2022-06-09
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-293 | RECONSTRUCTION AT HOWARD BEACH PUMPING STATION | 5 | CONSTRUCTION TO 25% | 2026-05-11 | 2027-05-05 | 2022-06-10 | 2023-06-04
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-293 | RECONSTRUCTION AT HOWARD BEACH PUMPING STATION | 6 | CONSTRUCTION TO 50% | 2027-05-06 | 2028-04-29 | 2023-06-05 | 2024-05-29
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-293 | RECONSTRUCTION AT HOWARD BEACH PUMPING STATION | 7 | CONSTRUCTION TO 75% | 2028-04-30 | 2029-04-24 | 2024-05-30 | 2025-05-24
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-293 | RECONSTRUCTION AT HOWARD BEACH PUMPING STATION | 8 | ORIGINAL EQUIP & FURNISHING | 2029-04-25 | 2030-01-19 | 2025-05-25 | 2026-02-18
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-293 | RECONSTRUCTION AT HOWARD BEACH PUMPING STATION | 9 | SUBSTANTIAL COMPLETION | 2030-01-20 | 2030-07-18 | 2026-02-19 | 2026-08-17
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-293 | RECONSTRUCTION AT HOWARD BEACH PUMPING STATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2030-07-19 | 2030-10-16 | 2026-08-18 | 2026-11-15
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-304 | RECONSTRUCTION AT GLENDALE PUMPING STATION | 1 | DEVELOP SCOPE | 2016-07-01 | 2017-03-27 | 2016-07-01 | 2017-03-27
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-304 | RECONSTRUCTION AT GLENDALE PUMPING STATION | 2 | PRELIMINARY DESIGN | 2017-03-28 | 2018-03-22 | 2017-03-28 | 2018-03-22
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-304 | RECONSTRUCTION AT GLENDALE PUMPING STATION | 3 | FINAL DESIGN | 2018-03-23 | 2019-09-13 | 2018-03-23 | 2019-09-13
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-304 | RECONSTRUCTION AT GLENDALE PUMPING STATION | 4 | BID AWARD AND REGISTER CONTRCT | 2019-09-14 | 2020-06-09 | 2019-09-14 | 2020-06-09
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-304 | RECONSTRUCTION AT GLENDALE PUMPING STATION | 5 | CONSTRUCTION TO 25% | 2020-06-10 | 2021-06-04 | 2020-06-10 | 2021-06-04
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-304 | RECONSTRUCTION AT GLENDALE PUMPING STATION | 6 | CONSTRUCTION TO 50% | 2021-06-05 | 2022-05-30 | 2021-06-05 | 2022-05-30
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-304 | RECONSTRUCTION AT GLENDALE PUMPING STATION | 7 | CONSTRUCTION TO 75% | 2022-05-31 | 2023-05-25 | 2022-05-31 | 2023-05-25
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-304 | RECONSTRUCTION AT GLENDALE PUMPING STATION | 8 | ORIGINAL EQUIP & FURNISHING | 2023-05-26 | 2024-02-19 | 2023-05-26 | 2024-02-19
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-304 | RECONSTRUCTION AT GLENDALE PUMPING STATION | 9 | SUBSTANTIAL COMPLETION | 2024-02-20 | 2024-08-17 | 2024-02-20 | 2024-08-17
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-304 | RECONSTRUCTION AT GLENDALE PUMPING STATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-08-18 | 2024-11-15 | 2024-08-18 | 2024-11-15
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-321 | RECONSTRUCTION OF LITTLE NECK PUMPING STATION, QUEENS, N.Y. | 1 | DEVELOP SCOPE | 2016-07-01 | 2017-03-27 | 2016-07-01 | 2017-03-27
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-321 | RECONSTRUCTION OF LITTLE NECK PUMPING STATION, QUEENS, N.Y. | 2 | PRELIMINARY DESIGN | 2017-03-28 | 2018-03-22 | 2017-03-28 | 2018-03-22
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-321 | RECONSTRUCTION OF LITTLE NECK PUMPING STATION, QUEENS, N.Y. | 3 | FINAL DESIGN | 2018-03-23 | 2019-09-13 | 2018-03-23 | 2019-09-13
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-321 | RECONSTRUCTION OF LITTLE NECK PUMPING STATION, QUEENS, N.Y. | 4 | BID AWARD AND REGISTER CONTRCT | 2019-09-14 | 2020-06-09 | 2019-09-14 | 2020-06-09
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-321 | RECONSTRUCTION OF LITTLE NECK PUMPING STATION, QUEENS, N.Y. | 5 | CONSTRUCTION TO 25% | 2020-06-10 | 2021-06-04 | 2020-06-10 | 2021-06-04
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-321 | RECONSTRUCTION OF LITTLE NECK PUMPING STATION, QUEENS, N.Y. | 6 | CONSTRUCTION TO 50% | 2021-06-05 | 2022-05-30 | 2021-06-05 | 2022-05-30
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-321 | RECONSTRUCTION OF LITTLE NECK PUMPING STATION, QUEENS, N.Y. | 7 | CONSTRUCTION TO 75% | 2022-05-31 | 2023-05-25 | 2022-05-31 | 2023-05-25
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-321 | RECONSTRUCTION OF LITTLE NECK PUMPING STATION, QUEENS, N.Y. | 8 | ORIGINAL EQUIP & FURNISHING | 2023-05-26 | 2024-02-19 | 2023-05-26 | 2024-02-19
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-321 | RECONSTRUCTION OF LITTLE NECK PUMPING STATION, QUEENS, N.Y. | 9 | SUBSTANTIAL COMPLETION | 2024-02-20 | 2024-08-17 | 2024-02-20 | 2024-08-17
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-321 | RECONSTRUCTION OF LITTLE NECK PUMPING STATION, QUEENS, N.Y. | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-08-18 | 2024-11-15 | 2024-08-18 | 2024-11-15
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-326 | INSTALLATION OF SE JAMAICA PUMPING STATION | 1 | DEVELOP SCOPE | 2017-06-01 | 2018-02-25 | 2017-06-01 | 2018-02-25
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-326 | INSTALLATION OF SE JAMAICA PUMPING STATION | 2 | PRELIMINARY DESIGN | 2018-02-26 | 2019-02-20 | 2018-02-26 | 2019-02-20
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-326 | INSTALLATION OF SE JAMAICA PUMPING STATION | 3 | FINAL DESIGN | 2019-02-21 | 2020-08-13 | 2019-02-21 | 2020-08-13
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-326 | INSTALLATION OF SE JAMAICA PUMPING STATION | 4 | BID AWARD AND REGISTER CONTRCT | 2020-08-14 | 2021-05-10 | 2020-08-14 | 2021-05-10
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-326 | INSTALLATION OF SE JAMAICA PUMPING STATION | 5 | CONSTRUCTION TO 25% | 2021-05-11 | 2022-05-05 | 2021-05-11 | 2022-05-05
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-326 | INSTALLATION OF SE JAMAICA PUMPING STATION | 6 | CONSTRUCTION TO 50% | 2022-05-06 | 2023-04-30 | 2022-05-06 | 2023-04-30
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-326 | INSTALLATION OF SE JAMAICA PUMPING STATION | 7 | CONSTRUCTION TO 75% | 2023-05-01 | 2024-04-24 | 2023-05-01 | 2024-04-24
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-326 | INSTALLATION OF SE JAMAICA PUMPING STATION | 8 | ORIGINAL EQUIP & FURNISHING | 2024-04-25 | 2025-01-19 | 2024-04-25 | 2025-01-19
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-326 | INSTALLATION OF SE JAMAICA PUMPING STATION | 9 | SUBSTANTIAL COMPLETION | 2025-01-20 | 2025-07-18 | 2025-01-20 | 2025-07-18
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-326 | INSTALLATION OF SE JAMAICA PUMPING STATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-07-19 | 2025-10-16 | 2025-07-19 | 2025-10-16
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-335 | RECONSTRUCTION OF TALLMAN ISLAND INTERCEPTOR DAMAGE | 1 | DEVELOP SCOPE | 2019-06-01 | 2019-08-29 | 2019-06-01 | 2019-08-29
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-335 | RECONSTRUCTION OF TALLMAN ISLAND INTERCEPTOR DAMAGE | 2 | PRELIMINARY DESIGN | 2019-08-30 | 2019-12-27 | 2019-08-30 | 2019-12-27
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-335 | RECONSTRUCTION OF TALLMAN ISLAND INTERCEPTOR DAMAGE | 3 | FINAL DESIGN | 2019-12-28 | 2020-06-24 | 2019-12-28 | 2020-06-24
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-335 | RECONSTRUCTION OF TALLMAN ISLAND INTERCEPTOR DAMAGE | 4 | BID AWARD AND REGISTER CONTRCT | 2020-06-25 | 2020-09-22 | 2020-06-25 | 2020-09-22
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-335 | RECONSTRUCTION OF TALLMAN ISLAND INTERCEPTOR DAMAGE | 5 | CONSTRUCTION TO 25% | 2020-09-23 | 2021-01-20 | 2020-09-23 | 2021-01-20
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-335 | RECONSTRUCTION OF TALLMAN ISLAND INTERCEPTOR DAMAGE | 6 | CONSTRUCTION TO 50% | 2021-01-21 | 2021-05-20 | 2021-01-21 | 2021-05-20
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-335 | RECONSTRUCTION OF TALLMAN ISLAND INTERCEPTOR DAMAGE | 7 | CONSTRUCTION TO 75% | 2021-05-21 | 2021-09-17 | 2021-05-21 | 2021-09-17
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-335 | RECONSTRUCTION OF TALLMAN ISLAND INTERCEPTOR DAMAGE | 8 | ORIGINAL EQUIP & FURNISHING | 2021-09-18 | 2021-12-16 | 2021-09-18 | 2021-12-16
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-335 | RECONSTRUCTION OF TALLMAN ISLAND INTERCEPTOR DAMAGE | 9 | SUBSTANTIAL COMPLETION | 2021-12-17 | 2022-02-14 | 2021-12-17 | 2022-02-14
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-335 | RECONSTRUCTION OF TALLMAN ISLAND INTERCEPTOR DAMAGE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-02-15 | 2022-03-16 | 2022-02-15 | 2022-03-16
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QED-1053 | Trunk Water Main Replacement in Rockaway Blvd | 1 | DEVELOP SCOPE | 2021-06-01 | 2021-08-29 | 2022-06-01 | 2022-08-29
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QED-1053 | Trunk Water Main Replacement in Rockaway Blvd | 2 | PRELIMINARY DESIGN | 2021-08-30 | 2021-12-27 | 2022-08-30 | 2022-12-27
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QED-1053 | Trunk Water Main Replacement in Rockaway Blvd | 3 | FINAL DESIGN | 2021-12-28 | 2022-06-25 | 2022-12-28 | 2023-06-25
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QED-1053 | Trunk Water Main Replacement in Rockaway Blvd | 4 | BID AWARD AND REGISTER CONTRCT | 2022-06-26 | 2022-09-23 | 2023-06-26 | 2023-09-23
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QED-1053 | Trunk Water Main Replacement in Rockaway Blvd | 5 | CONSTRUCTION TO 25% | 2022-09-24 | 2023-01-21 | 2023-09-24 | 2024-01-21
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QED-1053 | Trunk Water Main Replacement in Rockaway Blvd | 6 | CONSTRUCTION TO 50% | 2023-01-22 | 2023-05-21 | 2024-01-22 | 2024-05-20
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QED-1053 | Trunk Water Main Replacement in Rockaway Blvd | 7 | CONSTRUCTION TO 75% | 2023-05-22 | 2023-09-18 | 2024-05-21 | 2024-09-17
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QED-1053 | Trunk Water Main Replacement in Rockaway Blvd | 8 | ORIGINAL EQUIP & FURNISHING | 2023-09-19 | 2023-12-17 | 2024-09-18 | 2024-12-16
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QED-1053 | Trunk Water Main Replacement in Rockaway Blvd | 9 | SUBSTANTIAL COMPLETION | 2023-12-18 | 2024-02-15 | 2024-12-17 | 2025-02-14
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QED-1053 | Trunk Water Main Replacement in Rockaway Blvd | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-02-16 | 2024-03-16 | 2025-02-15 | 2025-03-16
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QED-1054 | Dist WM work in Ellwell Crescent from Alderton to Carlton St | 1 | DEVELOP SCOPE | 2020-11-09 | 2021-08-05 | 2020-11-09 | 2021-08-05
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QED-1054 | Dist WM work in Ellwell Crescent from Alderton to Carlton St | 2 | PRELIMINARY DESIGN | 2021-08-06 | 2022-07-31 | 2021-08-06 | 2022-07-31
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QED-1054 | Dist WM work in Ellwell Crescent from Alderton to Carlton St | 3 | FINAL DESIGN | 2022-08-01 | 2024-01-22 | 2022-08-01 | 2024-01-22
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QED-1054 | Dist WM work in Ellwell Crescent from Alderton to Carlton St | 4 | BID AWARD AND REGISTER CONTRCT | 2024-01-23 | 2024-10-18 | 2024-01-23 | 2024-10-18
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QED-1054 | Dist WM work in Ellwell Crescent from Alderton to Carlton St | 5 | CONSTRUCTION TO 25% | 2024-10-19 | 2025-10-13 | 2024-10-19 | 2025-10-13
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QED-1054 | Dist WM work in Ellwell Crescent from Alderton to Carlton St | 6 | CONSTRUCTION TO 50% | 2025-10-14 | 2026-10-08 | 2025-10-14 | 2026-10-08
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QED-1054 | Dist WM work in Ellwell Crescent from Alderton to Carlton St | 7 | CONSTRUCTION TO 75% | 2026-10-09 | 2027-10-03 | 2026-10-09 | 2027-10-03
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QED-1054 | Dist WM work in Ellwell Crescent from Alderton to Carlton St | 8 | ORIGINAL EQUIP & FURNISHING | 2027-10-04 | 2028-06-29 | 2027-10-04 | 2028-06-29
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QED-1054 | Dist WM work in Ellwell Crescent from Alderton to Carlton St | 9 | SUBSTANTIAL COMPLETION | 2028-06-30 | 2028-12-26 | 2028-06-30 | 2028-12-26
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QED-1054 | Dist WM work in Ellwell Crescent from Alderton to Carlton St | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2028-12-27 | 2029-03-26 | 2028-12-27 | 2029-03-26
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QED-1055 | Dist. WM work in Jay Ave btwn Borden Ave & 66th St, QNS | 1 | DEVELOP SCOPE | 2020-11-09 | 2021-08-05 | 2020-11-09 | 2021-08-05
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QED-1055 | Dist. WM work in Jay Ave btwn Borden Ave & 66th St, QNS | 2 | PRELIMINARY DESIGN | 2021-08-06 | 2022-07-31 | 2021-08-06 | 2022-07-31
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QED-1055 | Dist. WM work in Jay Ave btwn Borden Ave & 66th St, QNS | 3 | FINAL DESIGN | 2022-08-01 | 2024-01-22 | 2022-08-01 | 2024-01-22
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QED-1055 | Dist. WM work in Jay Ave btwn Borden Ave & 66th St, QNS | 4 | BID AWARD AND REGISTER CONTRCT | 2024-01-23 | 2024-10-18 | 2024-01-23 | 2024-10-18
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QED-1055 | Dist. WM work in Jay Ave btwn Borden Ave & 66th St, QNS | 5 | CONSTRUCTION TO 25% | 2024-10-19 | 2025-10-13 | 2024-10-19 | 2025-10-13
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QED-1055 | Dist. WM work in Jay Ave btwn Borden Ave & 66th St, QNS | 6 | CONSTRUCTION TO 50% | 2025-10-14 | 2026-10-08 | 2025-10-14 | 2026-10-08
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QED-1055 | Dist. WM work in Jay Ave btwn Borden Ave & 66th St, QNS | 7 | CONSTRUCTION TO 75% | 2026-10-09 | 2027-10-03 | 2026-10-09 | 2027-10-03
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QED-1055 | Dist. WM work in Jay Ave btwn Borden Ave & 66th St, QNS | 8 | ORIGINAL EQUIP & FURNISHING | 2027-10-04 | 2028-06-29 | 2027-10-04 | 2028-06-29
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QED-1055 | Dist. WM work in Jay Ave btwn Borden Ave & 66th St, QNS | 9 | SUBSTANTIAL COMPLETION | 2028-06-30 | 2028-12-26 | 2028-06-30 | 2028-12-26
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QED-1055 | Dist. WM work in Jay Ave btwn Borden Ave & 66th St, QNS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2028-12-27 | 2029-03-26 | 2028-12-27 | 2029-03-26
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QED-1056 | Dist WM work in 43rd Ave btwn National St & 104 St, QNS | 1 | DEVELOP SCOPE | 2020-11-09 | 2021-08-05 | 2020-11-09 | 2021-08-05
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QED-1056 | Dist WM work in 43rd Ave btwn National St & 104 St, QNS | 2 | PRELIMINARY DESIGN | 2021-08-06 | 2022-07-31 | 2021-08-06 | 2022-07-31
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QED-1056 | Dist WM work in 43rd Ave btwn National St & 104 St, QNS | 3 | FINAL DESIGN | 2022-08-01 | 2024-01-22 | 2022-08-01 | 2024-01-22
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QED-1056 | Dist WM work in 43rd Ave btwn National St & 104 St, QNS | 4 | BID AWARD AND REGISTER CONTRCT | 2024-01-23 | 2024-10-18 | 2024-01-23 | 2024-10-18
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QED-1056 | Dist WM work in 43rd Ave btwn National St & 104 St, QNS | 5 | CONSTRUCTION TO 25% | 2024-10-19 | 2025-10-13 | 2024-10-19 | 2025-10-13
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QED-1056 | Dist WM work in 43rd Ave btwn National St & 104 St, QNS | 6 | CONSTRUCTION TO 50% | 2025-10-14 | 2026-10-08 | 2025-10-14 | 2026-10-08
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QED-1056 | Dist WM work in 43rd Ave btwn National St & 104 St, QNS | 7 | CONSTRUCTION TO 75% | 2026-10-09 | 2027-10-03 | 2026-10-09 | 2027-10-03
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QED-1056 | Dist WM work in 43rd Ave btwn National St & 104 St, QNS | 8 | ORIGINAL EQUIP & FURNISHING | 2027-10-04 | 2028-06-29 | 2027-10-04 | 2028-06-29
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QED-1056 | Dist WM work in 43rd Ave btwn National St & 104 St, QNS | 9 | SUBSTANTIAL COMPLETION | 2028-06-30 | 2028-12-26 | 2028-06-30 | 2028-12-26
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QED-1056 | Dist WM work in 43rd Ave btwn National St & 104 St, QNS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2028-12-27 | 2029-03-26 | 2028-12-27 | 2029-03-26
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QNSREPAIR | REHABILITATION OF QUEENS REPAIR FACILITY | 1 | DEVELOP SCOPE | 2019-06-30 | 2019-10-27 | 2019-06-30 | 2019-10-27
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QNSREPAIR | REHABILITATION OF QUEENS REPAIR FACILITY | 2 | PRELIMINARY DESIGN | 2019-10-28 | 2020-04-24 | 2019-10-28 | 2020-04-24
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QNSREPAIR | REHABILITATION OF QUEENS REPAIR FACILITY | 3 | FINAL DESIGN | 2020-04-25 | 2021-10-26 | 2020-04-25 | 2021-10-26
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QNSREPAIR | REHABILITATION OF QUEENS REPAIR FACILITY | 4 | BID AWARD AND REGISTER CONTRCT | 2021-10-27 | 2022-04-24 | 2021-10-27 | 2022-04-24
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QNSREPAIR | REHABILITATION OF QUEENS REPAIR FACILITY | 5 | CONSTRUCTION TO 25% | 2022-04-25 | 2023-01-29 | 2022-04-25 | 2023-01-29
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QNSREPAIR | REHABILITATION OF QUEENS REPAIR FACILITY | 6 | CONSTRUCTION TO 50% | 2023-01-30 | 2023-11-05 | 2023-01-30 | 2023-11-05
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QNSREPAIR | REHABILITATION OF QUEENS REPAIR FACILITY | 7 | CONSTRUCTION TO 75% | 2023-11-06 | 2024-08-11 | 2023-11-06 | 2024-08-11
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QNSREPAIR | REHABILITATION OF QUEENS REPAIR FACILITY | 8 | ORIGINAL EQUIP & FURNISHING | 2024-08-12 | 2024-11-09 | 2024-08-12 | 2024-11-09
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QNSREPAIR | REHABILITATION OF QUEENS REPAIR FACILITY | 9 | SUBSTANTIAL COMPLETION | 2024-11-10 | 2025-01-08 | 2024-11-10 | 2025-01-08
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QNSREPAIR | REHABILITATION OF QUEENS REPAIR FACILITY | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-01-09 | 2025-04-08 | 2025-01-09 | 2025-04-08
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | R-009-L | RECONSTRUCT FOUR SODIUM HYPOCHLORITE CBS TANKS @ ROCKAWAY | 1 | FINAL DESIGN | 2019-06-01 | 2020-11-21 | 2019-06-01 | 2020-11-21
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | R-009-L | RECONSTRUCT FOUR SODIUM HYPOCHLORITE CBS TANKS @ ROCKAWAY | 2 | CONSTRUCTION TO 25% | 2020-11-22 | 2021-07-19 | 2020-11-22 | 2021-07-19
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | R-009-L | RECONSTRUCT FOUR SODIUM HYPOCHLORITE CBS TANKS @ ROCKAWAY | 3 | CONSTRUCTION TO 50% | 2021-07-20 | 2022-03-16 | 2021-07-20 | 2022-03-16
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | R-009-L | RECONSTRUCT FOUR SODIUM HYPOCHLORITE CBS TANKS @ ROCKAWAY | 4 | CONSTRUCTION TO 75% | 2022-03-17 | 2022-11-11 | 2022-03-17 | 2022-11-11
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | R-153-L | RECONSTRUCT FINAL SETTLING SYSTEM @ ROCKAWAY WWTP | 1 | DEVELOP SCOPE | 2020-06-01 | 2021-02-25 | 2018-06-01 | 2019-02-25
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | R-153-L | RECONSTRUCT FINAL SETTLING SYSTEM @ ROCKAWAY WWTP | 2 | PRELIMINARY DESIGN | 2021-02-26 | 2022-02-20 | 2019-02-26 | 2020-02-20
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | R-153-L | RECONSTRUCT FINAL SETTLING SYSTEM @ ROCKAWAY WWTP | 3 | FINAL DESIGN | 2022-02-21 | 2023-08-14 | 2020-02-21 | 2021-08-13
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | R-153-L | RECONSTRUCT FINAL SETTLING SYSTEM @ ROCKAWAY WWTP | 4 | BID AWARD AND REGISTER CONTRCT | 2023-08-15 | 2024-05-10 | 2021-08-14 | 2022-05-10
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | R-153-L | RECONSTRUCT FINAL SETTLING SYSTEM @ ROCKAWAY WWTP | 5 | CONSTRUCTION TO 25% | 2024-05-11 | 2025-05-05 | 2022-05-11 | 2023-05-05
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | R-153-L | RECONSTRUCT FINAL SETTLING SYSTEM @ ROCKAWAY WWTP | 6 | CONSTRUCTION TO 50% | 2025-05-06 | 2026-04-30 | 2023-05-06 | 2024-04-29
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | R-153-L | RECONSTRUCT FINAL SETTLING SYSTEM @ ROCKAWAY WWTP | 7 | CONSTRUCTION TO 75% | 2026-05-01 | 2027-04-25 | 2024-04-30 | 2025-04-24
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | R-153-L | RECONSTRUCT FINAL SETTLING SYSTEM @ ROCKAWAY WWTP | 8 | ORIGINAL EQUIP & FURNISHING | 2027-04-26 | 2028-01-20 | 2025-04-25 | 2026-01-19
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | R-153-L | RECONSTRUCT FINAL SETTLING SYSTEM @ ROCKAWAY WWTP | 9 | SUBSTANTIAL COMPLETION | 2028-01-21 | 2028-07-18 | 2026-01-20 | 2026-07-18
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | R-153-L | RECONSTRUCT FINAL SETTLING SYSTEM @ ROCKAWAY WWTP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2028-07-19 | 2028-10-16 | 2026-07-19 | 2026-10-16
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | RO-2 | REPLACE MAIN SEWAGE PUMPS AT ROCKAWAY WPCP | 1 | FINAL DESIGN | 2022-06-01 | 2023-11-22 | 2019-06-01 | 2020-02-25
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | RO-2 | REPLACE MAIN SEWAGE PUMPS AT ROCKAWAY WPCP | 2 | CONSTRUCTION TO 25% | 2023-11-23 | 2024-07-19 | 2020-02-26 | 2021-02-19
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | RO-2 | REPLACE MAIN SEWAGE PUMPS AT ROCKAWAY WPCP | 3 | CONSTRUCTION TO 50% | 2024-07-20 | 2025-03-16 | 2021-02-20 | 2022-08-13
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | RO-2 | REPLACE MAIN SEWAGE PUMPS AT ROCKAWAY WPCP | 4 | CONSTRUCTION TO 75% | 2025-03-17 | 2025-11-11 | 2022-08-14 | 2023-05-10
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | RO-2 | REPLACE MAIN SEWAGE PUMPS AT ROCKAWAY WPCP | 5 | CONSTRUCTION TO 25% | 2025-03-17 | 2025-11-11 | 2023-05-11 | 2024-05-04
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | RO-2 | REPLACE MAIN SEWAGE PUMPS AT ROCKAWAY WPCP | 6 | CONSTRUCTION TO 50% | 2025-03-17 | 2025-11-11 | 2024-05-05 | 2025-04-29
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | RO-2 | REPLACE MAIN SEWAGE PUMPS AT ROCKAWAY WPCP | 7 | CONSTRUCTION TO 75% | 2025-03-17 | 2025-11-11 | 2025-04-30 | 2026-04-24
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | RO-2 | REPLACE MAIN SEWAGE PUMPS AT ROCKAWAY WPCP | 8 | ORIGINAL EQUIP & FURNISHING | 2025-03-17 | 2025-11-11 | 2026-04-25 | 2027-01-19
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | RO-2 | REPLACE MAIN SEWAGE PUMPS AT ROCKAWAY WPCP | 9 | SUBSTANTIAL COMPLETION | 2025-03-17 | 2025-11-11 | 2027-01-20 | 2027-07-18
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | RO-2 | REPLACE MAIN SEWAGE PUMPS AT ROCKAWAY WPCP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-03-17 | 2025-11-11 | 2027-07-19 | 2027-10-16
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | RO-3 | REPLACE MAIN INFLUENT GATES & ACTUATORS AT ROCKAWAY WPCP | 1 | FINAL DESIGN | 2022-06-15 | 2023-12-06 | 2022-06-15 | 2023-12-06
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | RO-3 | REPLACE MAIN INFLUENT GATES & ACTUATORS AT ROCKAWAY WPCP | 2 | CONSTRUCTION TO 25% | 2023-12-07 | 2024-08-02 | 2023-12-07 | 2024-08-02
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | RO-3 | REPLACE MAIN INFLUENT GATES & ACTUATORS AT ROCKAWAY WPCP | 3 | CONSTRUCTION TO 50% | 2024-08-03 | 2025-03-30 | 2024-08-03 | 2025-03-30
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | RO-3 | REPLACE MAIN INFLUENT GATES & ACTUATORS AT ROCKAWAY WPCP | 4 | CONSTRUCTION TO 75% | 2025-03-31 | 2025-11-25 | 2025-03-31 | 2025-11-25
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDROCK | RECONS OF THE ROCKAWAY WPCP DUE TO HURRICANE SANDY | 1 | DEVELOP SCOPE | 2014-07-01 | 2014-09-28 | 2020-06-30 | 2021-03-26
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDROCK | RECONS OF THE ROCKAWAY WPCP DUE TO HURRICANE SANDY | 2 | PRELIMINARY DESIGN | 2014-09-29 | 2015-01-26 | 2021-03-27 | 2022-03-21
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDROCK | RECONS OF THE ROCKAWAY WPCP DUE TO HURRICANE SANDY | 3 | FINAL DESIGN | 2015-01-27 | 2015-07-25 | 2022-03-22 | 2023-09-12
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDROCK | RECONS OF THE ROCKAWAY WPCP DUE TO HURRICANE SANDY | 4 | BID AWARD AND REGISTER CONTRCT | 2015-07-26 | 2015-10-23 | 2023-09-13 | 2024-06-08
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDROCK | RECONS OF THE ROCKAWAY WPCP DUE TO HURRICANE SANDY | 5 | CONSTRUCTION TO 25% | 2015-10-24 | 2016-02-20 | 2024-06-09 | 2025-06-03
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDROCK | RECONS OF THE ROCKAWAY WPCP DUE TO HURRICANE SANDY | 6 | CONSTRUCTION TO 50% | 2016-02-21 | 2016-06-19 | 2025-06-04 | 2026-05-29
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDROCK | RECONS OF THE ROCKAWAY WPCP DUE TO HURRICANE SANDY | 7 | CONSTRUCTION TO 75% | 2016-06-20 | 2016-10-17 | 2026-05-30 | 2027-05-24
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDROCK | RECONS OF THE ROCKAWAY WPCP DUE TO HURRICANE SANDY | 8 | ORIGINAL EQUIP & FURNISHING | 2016-10-18 | 2017-01-15 | 2027-05-25 | 2028-02-18
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDROCK | RECONS OF THE ROCKAWAY WPCP DUE TO HURRICANE SANDY | 9 | SUBSTANTIAL COMPLETION | 2017-01-16 | 2017-03-16 | 2028-02-19 | 2032-08-15
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDROCK | RECONS OF THE ROCKAWAY WPCP DUE TO HURRICANE SANDY | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-17 | 2017-04-15 | 2032-08-16 | 2032-11-13
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SE-861A | HLSS; Strm, san & comb swers & WM, Borden Ave, Phase 2, Qns | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-08-29 | 2023-06-02 | 2023-08-30
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SE-861A | HLSS; Strm, san & comb swers & WM, Borden Ave, Phase 2, Qns | 2 | PRELIMINARY DESIGN | 2020-08-30 | 2020-12-27 | 2023-08-31 | 2023-12-28
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SE-861A | HLSS; Strm, san & comb swers & WM, Borden Ave, Phase 2, Qns | 3 | FINAL DESIGN | 2020-12-28 | 2021-06-25 | 2023-12-29 | 2024-06-25
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SE-861A | HLSS; Strm, san & comb swers & WM, Borden Ave, Phase 2, Qns | 4 | BID AWARD AND REGISTER CONTRCT | 2021-06-26 | 2021-09-23 | 2024-06-26 | 2024-09-23
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SE-861A | HLSS; Strm, san & comb swers & WM, Borden Ave, Phase 2, Qns | 5 | CONSTRUCTION TO 25% | 2021-09-24 | 2022-01-21 | 2024-09-24 | 2025-01-21
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SE-861A | HLSS; Strm, san & comb swers & WM, Borden Ave, Phase 2, Qns | 6 | CONSTRUCTION TO 50% | 2022-01-22 | 2022-05-21 | 2025-01-22 | 2025-05-21
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SE-861A | HLSS; Strm, san & comb swers & WM, Borden Ave, Phase 2, Qns | 7 | CONSTRUCTION TO 75% | 2022-05-22 | 2022-09-18 | 2025-05-22 | 2025-09-18
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SE-861A | HLSS; Strm, san & comb swers & WM, Borden Ave, Phase 2, Qns | 8 | ORIGINAL EQUIP & FURNISHING | 2022-09-19 | 2022-12-17 | 2025-09-19 | 2025-12-17
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SE-861A | HLSS; Strm, san & comb swers & WM, Borden Ave, Phase 2, Qns | 9 | SUBSTANTIAL COMPLETION | 2022-12-18 | 2023-02-15 | 2025-12-18 | 2026-02-15
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SE-861A | HLSS; Strm, san & comb swers & WM, Borden Ave, Phase 2, Qns | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-02-16 | 2023-03-17 | 2026-02-16 | 2026-03-17
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SE-CD32 | Drainage Improvements in City Council District 32 | 1 | DEVELOP SCOPE | 2019-08-21 | 2020-05-16 | 2019-08-21 | 2020-05-16
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SE-CD32 | Drainage Improvements in City Council District 32 | 2 | PRELIMINARY DESIGN | 2020-05-17 | 2021-05-11 | 2020-05-17 | 2021-05-11
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SE-CD32 | Drainage Improvements in City Council District 32 | 3 | FINAL DESIGN | 2021-05-12 | 2022-11-02 | 2021-05-12 | 2022-11-02
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SE-CD32 | Drainage Improvements in City Council District 32 | 4 | BID AWARD AND REGISTER CONTRCT | 2022-11-03 | 2023-07-30 | 2022-11-03 | 2023-07-30
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SE-CD32 | Drainage Improvements in City Council District 32 | 5 | CONSTRUCTION TO 25% | 2023-07-31 | 2024-07-24 | 2023-07-31 | 2024-07-24
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SE-CD32 | Drainage Improvements in City Council District 32 | 6 | CONSTRUCTION TO 50% | 2024-07-25 | 2025-07-19 | 2024-07-25 | 2025-07-19
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SE-CD32 | Drainage Improvements in City Council District 32 | 7 | CONSTRUCTION TO 75% | 2025-07-20 | 2026-07-14 | 2025-07-20 | 2026-07-14
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SE-CD32 | Drainage Improvements in City Council District 32 | 8 | ORIGINAL EQUIP & FURNISHING | 2026-07-15 | 2027-04-10 | 2026-07-15 | 2027-04-10
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SE-CD32 | Drainage Improvements in City Council District 32 | 9 | SUBSTANTIAL COMPLETION | 2027-04-11 | 2027-10-07 | 2027-04-11 | 2027-10-07
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SE-CD32 | Drainage Improvements in City Council District 32 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2027-10-08 | 2028-01-05 | 2027-10-08 | 2028-01-05
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ002715 | Replmnt & repair of combined SE outfall north 81st &19 Ave | 1 | DEVELOP SCOPE | 2019-08-23 | 2020-05-18 | 2019-08-23 | 2020-05-18
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ002715 | Replmnt & repair of combined SE outfall north 81st &19 Ave | 2 | PRELIMINARY DESIGN | 2020-05-19 | 2021-05-13 | 2020-05-19 | 2021-05-13
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ002715 | Replmnt & repair of combined SE outfall north 81st &19 Ave | 3 | FINAL DESIGN | 2021-05-14 | 2022-11-04 | 2021-05-14 | 2022-11-04
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ002715 | Replmnt & repair of combined SE outfall north 81st &19 Ave | 4 | BID AWARD AND REGISTER CONTRCT | 2022-11-05 | 2023-08-01 | 2022-11-05 | 2023-08-01
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ002715 | Replmnt & repair of combined SE outfall north 81st &19 Ave | 5 | CONSTRUCTION TO 25% | 2023-08-02 | 2024-07-26 | 2023-08-02 | 2024-07-26
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ002715 | Replmnt & repair of combined SE outfall north 81st &19 Ave | 6 | CONSTRUCTION TO 50% | 2024-07-27 | 2025-07-21 | 2024-07-27 | 2025-07-21
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ002715 | Replmnt & repair of combined SE outfall north 81st &19 Ave | 7 | CONSTRUCTION TO 75% | 2025-07-22 | 2026-07-16 | 2025-07-22 | 2026-07-16
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ002715 | Replmnt & repair of combined SE outfall north 81st &19 Ave | 8 | ORIGINAL EQUIP & FURNISHING | 2026-07-17 | 2027-04-12 | 2026-07-17 | 2027-04-12
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ002715 | Replmnt & repair of combined SE outfall north 81st &19 Ave | 9 | SUBSTANTIAL COMPLETION | 2027-04-13 | 2027-10-09 | 2027-04-13 | 2027-10-09
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ002715 | Replmnt & repair of combined SE outfall north 81st &19 Ave | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2027-10-10 | 2028-01-07 | 2027-10-10 | 2028-01-07
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ200592 | Southeast Queens - Rosedale South | 1 | DEVELOP SCOPE | 2019-06-01 | 2020-02-25 | 2019-06-01 | 2020-02-25
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ200592 | Southeast Queens - Rosedale South | 2 | PRELIMINARY DESIGN | 2020-02-26 | 2021-02-19 | 2020-02-26 | 2021-02-19
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ200592 | Southeast Queens - Rosedale South | 3 | FINAL DESIGN | 2021-02-20 | 2022-08-13 | 2021-02-20 | 2022-08-13
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ200592 | Southeast Queens - Rosedale South | 4 | BID AWARD AND REGISTER CONTRCT | 2022-08-14 | 2023-05-10 | 2022-08-14 | 2023-05-10
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ200592 | Southeast Queens - Rosedale South | 5 | CONSTRUCTION TO 25% | 2023-05-11 | 2024-05-04 | 2023-05-11 | 2024-05-04
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ200592 | Southeast Queens - Rosedale South | 6 | CONSTRUCTION TO 50% | 2024-05-05 | 2025-04-29 | 2024-05-05 | 2025-04-29
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ200592 | Southeast Queens - Rosedale South | 7 | CONSTRUCTION TO 75% | 2025-04-30 | 2026-04-24 | 2025-04-30 | 2026-04-24
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ200592 | Southeast Queens - Rosedale South | 8 | ORIGINAL EQUIP & FURNISHING | 2026-04-25 | 2027-01-19 | 2026-04-25 | 2027-01-19
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ200592 | Southeast Queens - Rosedale South | 9 | SUBSTANTIAL COMPLETION | 2027-01-20 | 2027-07-18 | 2027-01-20 | 2027-07-18
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ200592 | Southeast Queens - Rosedale South | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2027-07-19 | 2027-10-16 | 2027-07-19 | 2027-10-16
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ200604 | St. SE Ext in College Pl btwn 5th ave to US Bulkhead Line QN | 1 | DEVELOP SCOPE | 2020-11-09 | 2021-02-06 | 2020-11-09 | 2021-02-06
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ200604 | St. SE Ext in College Pl btwn 5th ave to US Bulkhead Line QN | 2 | PRELIMINARY DESIGN | 2021-02-07 | 2021-06-06 | 2021-02-07 | 2021-06-06
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ200604 | St. SE Ext in College Pl btwn 5th ave to US Bulkhead Line QN | 3 | FINAL DESIGN | 2021-06-07 | 2021-12-03 | 2021-06-07 | 2021-12-03
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ200604 | St. SE Ext in College Pl btwn 5th ave to US Bulkhead Line QN | 4 | BID AWARD AND REGISTER CONTRCT | 2021-12-04 | 2022-03-03 | 2021-12-04 | 2022-03-03
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ200604 | St. SE Ext in College Pl btwn 5th ave to US Bulkhead Line QN | 5 | CONSTRUCTION TO 25% | 2022-03-04 | 2022-07-01 | 2022-03-04 | 2022-07-01
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ200604 | St. SE Ext in College Pl btwn 5th ave to US Bulkhead Line QN | 6 | CONSTRUCTION TO 50% | 2022-07-02 | 2022-10-29 | 2022-07-02 | 2022-10-29
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ200604 | St. SE Ext in College Pl btwn 5th ave to US Bulkhead Line QN | 7 | CONSTRUCTION TO 75% | 2022-10-30 | 2023-02-26 | 2022-10-30 | 2023-02-26
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ200604 | St. SE Ext in College Pl btwn 5th ave to US Bulkhead Line QN | 8 | ORIGINAL EQUIP & FURNISHING | 2023-02-27 | 2023-05-27 | 2023-02-27 | 2023-05-27
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ200604 | St. SE Ext in College Pl btwn 5th ave to US Bulkhead Line QN | 9 | SUBSTANTIAL COMPLETION | 2023-05-28 | 2023-07-26 | 2023-05-28 | 2023-07-26
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ200604 | St. SE Ext in College Pl btwn 5th ave to US Bulkhead Line QN | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-07-27 | 2023-08-25 | 2023-07-27 | 2023-08-25
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ-B67 | BEACH 67TH STREET MEDIAN GREEN INFRASTRUCTURE | 1 | DEVELOP SCOPE | 2019-12-09 | 2020-09-03 | 2019-12-09 | 2020-09-03
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ-B67 | BEACH 67TH STREET MEDIAN GREEN INFRASTRUCTURE | 2 | PRELIMINARY DESIGN | 2020-09-04 | 2021-08-29 | 2020-09-04 | 2021-08-29
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ-B67 | BEACH 67TH STREET MEDIAN GREEN INFRASTRUCTURE | 3 | FINAL DESIGN | 2021-08-30 | 2023-02-20 | 2021-08-30 | 2023-02-20
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ-B67 | BEACH 67TH STREET MEDIAN GREEN INFRASTRUCTURE | 4 | BID AWARD AND REGISTER CONTRCT | 2023-02-21 | 2023-11-17 | 2023-02-21 | 2023-11-17
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ-B67 | BEACH 67TH STREET MEDIAN GREEN INFRASTRUCTURE | 5 | CONSTRUCTION TO 25% | 2023-11-18 | 2024-11-11 | 2023-11-18 | 2024-11-11
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ-B67 | BEACH 67TH STREET MEDIAN GREEN INFRASTRUCTURE | 6 | CONSTRUCTION TO 50% | 2024-11-12 | 2025-11-06 | 2024-11-12 | 2025-11-06
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ-B67 | BEACH 67TH STREET MEDIAN GREEN INFRASTRUCTURE | 7 | CONSTRUCTION TO 75% | 2025-11-07 | 2026-11-01 | 2025-11-07 | 2026-11-01
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ-B67 | BEACH 67TH STREET MEDIAN GREEN INFRASTRUCTURE | 8 | ORIGINAL EQUIP & FURNISHING | 2026-11-02 | 2027-07-29 | 2026-11-02 | 2027-07-29
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ-B67 | BEACH 67TH STREET MEDIAN GREEN INFRASTRUCTURE | 9 | SUBSTANTIAL COMPLETION | 2027-07-30 | 2028-01-25 | 2027-07-30 | 2028-01-25
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ-B67 | BEACH 67TH STREET MEDIAN GREEN INFRASTRUCTURE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2028-01-26 | 2028-04-24 | 2028-01-26 | 2028-04-24
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ-DKWPK | CONSTRUCTION FOR DETECTIVE KEITH WILLIAMS PARK | 1 | DEVELOP SCOPE | 2021-06-15 | 2022-03-11 | 2021-06-15 | 2022-03-11
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ-DKWPK | CONSTRUCTION FOR DETECTIVE KEITH WILLIAMS PARK | 2 | PRELIMINARY DESIGN | 2022-03-12 | 2023-03-06 | 2022-03-12 | 2023-03-06
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ-DKWPK | CONSTRUCTION FOR DETECTIVE KEITH WILLIAMS PARK | 3 | FINAL DESIGN | 2023-03-07 | 2024-08-27 | 2023-03-07 | 2024-08-27
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ-DKWPK | CONSTRUCTION FOR DETECTIVE KEITH WILLIAMS PARK | 4 | BID AWARD AND REGISTER CONTRCT | 2024-08-28 | 2025-05-24 | 2024-08-28 | 2025-05-24
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ-DKWPK | CONSTRUCTION FOR DETECTIVE KEITH WILLIAMS PARK | 5 | CONSTRUCTION TO 25% | 2025-05-25 | 2026-05-19 | 2025-05-25 | 2026-05-19
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ-DKWPK | CONSTRUCTION FOR DETECTIVE KEITH WILLIAMS PARK | 6 | CONSTRUCTION TO 50% | 2026-05-20 | 2027-05-14 | 2026-05-20 | 2027-05-14
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ-DKWPK | CONSTRUCTION FOR DETECTIVE KEITH WILLIAMS PARK | 7 | CONSTRUCTION TO 75% | 2027-05-15 | 2028-05-08 | 2027-05-15 | 2028-05-08
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ-DKWPK | CONSTRUCTION FOR DETECTIVE KEITH WILLIAMS PARK | 8 | ORIGINAL EQUIP & FURNISHING | 2028-05-09 | 2029-02-02 | 2028-05-09 | 2029-02-02
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ-DKWPK | CONSTRUCTION FOR DETECTIVE KEITH WILLIAMS PARK | 9 | SUBSTANTIAL COMPLETION | 2029-02-03 | 2029-08-01 | 2029-02-03 | 2029-08-01
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ-DKWPK | CONSTRUCTION FOR DETECTIVE KEITH WILLIAMS PARK | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2029-08-02 | 2029-10-30 | 2029-08-02 | 2029-10-30
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQGI-01 | SEQ - CONSTRUCTION OF GREEN INFRASTRUCTURE SOUTHEAST QUEENS | 1 | DEVELOP SCOPE | 2018-01-01 | 2019-06-24 | 2018-01-01 | 2018-09-27
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQGI-01 | SEQ - CONSTRUCTION OF GREEN INFRASTRUCTURE SOUTHEAST QUEENS | 2 | PRELIMINARY DESIGN | 2019-06-25 | 2020-02-19 | 2018-09-28 | 2019-09-22
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQGI-01 | SEQ - CONSTRUCTION OF GREEN INFRASTRUCTURE SOUTHEAST QUEENS | 3 | FINAL DESIGN | 2020-02-20 | 2020-10-16 | 2019-09-23 | 2021-03-15
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQGI-01 | SEQ - CONSTRUCTION OF GREEN INFRASTRUCTURE SOUTHEAST QUEENS | 4 | CONSTRUCTION TO 75% | 2020-10-17 | 2021-06-13 | 2021-03-16 | 2021-12-10
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQGI-01 | SEQ - CONSTRUCTION OF GREEN INFRASTRUCTURE SOUTHEAST QUEENS | 5 | CONSTRUCTION TO 25% | 2020-10-17 | 2021-06-13 | 2021-12-11 | 2022-12-05
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQGI-01 | SEQ - CONSTRUCTION OF GREEN INFRASTRUCTURE SOUTHEAST QUEENS | 6 | CONSTRUCTION TO 50% | 2020-10-17 | 2021-06-13 | 2022-12-06 | 2023-11-30
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQGI-01 | SEQ - CONSTRUCTION OF GREEN INFRASTRUCTURE SOUTHEAST QUEENS | 7 | CONSTRUCTION TO 75% | 2020-10-17 | 2021-06-13 | 2023-12-01 | 2024-11-24
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQGI-01 | SEQ - CONSTRUCTION OF GREEN INFRASTRUCTURE SOUTHEAST QUEENS | 8 | ORIGINAL EQUIP & FURNISHING | 2020-10-17 | 2021-06-13 | 2024-11-25 | 2025-08-21
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQGI-01 | SEQ - CONSTRUCTION OF GREEN INFRASTRUCTURE SOUTHEAST QUEENS | 9 | SUBSTANTIAL COMPLETION | 2020-10-17 | 2021-06-13 | 2025-08-22 | 2026-02-17
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQGI-01 | SEQ - CONSTRUCTION OF GREEN INFRASTRUCTURE SOUTHEAST QUEENS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-10-17 | 2021-06-13 | 2026-02-18 | 2026-05-18
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ-RAILP | CONSTRUCTION FOR RAILROAD PARK | 1 | DEVELOP SCOPE | 2021-06-15 | 2022-03-11 | 2021-06-15 | 2022-03-11
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ-RAILP | CONSTRUCTION FOR RAILROAD PARK | 2 | PRELIMINARY DESIGN | 2022-03-12 | 2023-03-06 | 2022-03-12 | 2023-03-06
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ-RAILP | CONSTRUCTION FOR RAILROAD PARK | 3 | FINAL DESIGN | 2023-03-07 | 2024-08-27 | 2023-03-07 | 2024-08-27
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ-RAILP | CONSTRUCTION FOR RAILROAD PARK | 4 | BID AWARD AND REGISTER CONTRCT | 2024-08-28 | 2025-05-24 | 2024-08-28 | 2025-05-24
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ-RAILP | CONSTRUCTION FOR RAILROAD PARK | 5 | CONSTRUCTION TO 25% | 2025-05-25 | 2026-05-19 | 2025-05-25 | 2026-05-19
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ-RAILP | CONSTRUCTION FOR RAILROAD PARK | 6 | CONSTRUCTION TO 50% | 2026-05-20 | 2027-05-14 | 2026-05-20 | 2027-05-14
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ-RAILP | CONSTRUCTION FOR RAILROAD PARK | 7 | CONSTRUCTION TO 75% | 2027-05-15 | 2028-05-08 | 2027-05-15 | 2028-05-08
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ-RAILP | CONSTRUCTION FOR RAILROAD PARK | 8 | ORIGINAL EQUIP & FURNISHING | 2028-05-09 | 2029-02-02 | 2028-05-09 | 2029-02-02
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ-RAILP | CONSTRUCTION FOR RAILROAD PARK | 9 | SUBSTANTIAL COMPLETION | 2029-02-03 | 2029-08-01 | 2029-02-03 | 2029-08-01
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ-RAILP | CONSTRUCTION FOR RAILROAD PARK | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2029-08-02 | 2029-10-30 | 2029-08-02 | 2029-10-30
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ-SJH | CONSTRUCTION FOR CLOUDBURST PROJECT AT SOUTH JAMAICA HOUSES | 1 | DEVELOP SCOPE | 2022-06-15 | 2023-03-11 | 2022-06-15 | 2023-03-11
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ-SJH | CONSTRUCTION FOR CLOUDBURST PROJECT AT SOUTH JAMAICA HOUSES | 2 | PRELIMINARY DESIGN | 2023-03-12 | 2024-03-05 | 2023-03-12 | 2024-03-05
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ-SJH | CONSTRUCTION FOR CLOUDBURST PROJECT AT SOUTH JAMAICA HOUSES | 3 | FINAL DESIGN | 2024-03-06 | 2025-08-27 | 2024-03-06 | 2025-08-27
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ-SJH | CONSTRUCTION FOR CLOUDBURST PROJECT AT SOUTH JAMAICA HOUSES | 4 | BID AWARD AND REGISTER CONTRCT | 2025-08-28 | 2026-05-24 | 2025-08-28 | 2026-05-24
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ-SJH | CONSTRUCTION FOR CLOUDBURST PROJECT AT SOUTH JAMAICA HOUSES | 5 | CONSTRUCTION TO 25% | 2026-05-25 | 2027-05-19 | 2026-05-25 | 2027-05-19
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ-SJH | CONSTRUCTION FOR CLOUDBURST PROJECT AT SOUTH JAMAICA HOUSES | 6 | CONSTRUCTION TO 50% | 2027-05-20 | 2028-05-13 | 2027-05-20 | 2028-05-13
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ-SJH | CONSTRUCTION FOR CLOUDBURST PROJECT AT SOUTH JAMAICA HOUSES | 7 | CONSTRUCTION TO 75% | 2028-05-14 | 2029-05-08 | 2028-05-14 | 2029-05-08
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ-SJH | CONSTRUCTION FOR CLOUDBURST PROJECT AT SOUTH JAMAICA HOUSES | 8 | ORIGINAL EQUIP & FURNISHING | 2029-05-09 | 2030-02-02 | 2029-05-09 | 2030-02-02
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ-SJH | CONSTRUCTION FOR CLOUDBURST PROJECT AT SOUTH JAMAICA HOUSES | 9 | SUBSTANTIAL COMPLETION | 2030-02-03 | 2030-08-01 | 2030-02-03 | 2030-08-01
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ-SJH | CONSTRUCTION FOR CLOUDBURST PROJECT AT SOUTH JAMAICA HOUSES | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2030-08-02 | 2030-10-30 | 2030-08-02 | 2030-10-30
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ-STA | CONSTRUCTION FOR CLOUDBURST PROJECT AT ST ALBANS | 1 | FINAL DESIGN | 2019-06-30 | 2020-12-20 | 2019-06-30 | 2020-12-20
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ-STA | CONSTRUCTION FOR CLOUDBURST PROJECT AT ST ALBANS | 2 | CONSTRUCTION TO 25% | 2020-12-21 | 2021-08-17 | 2020-12-21 | 2021-08-17
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ-STA | CONSTRUCTION FOR CLOUDBURST PROJECT AT ST ALBANS | 3 | CONSTRUCTION TO 50% | 2021-08-18 | 2022-04-14 | 2021-08-18 | 2022-04-14
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ-STA | CONSTRUCTION FOR CLOUDBURST PROJECT AT ST ALBANS | 4 | CONSTRUCTION TO 75% | 2022-04-15 | 2022-12-10 | 2022-04-15 | 2022-12-10
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SF-BNR-RK | STEP FEED BNR AT ROCKAWAY | 1 | DEVELOP SCOPE | 2013-07-01 | 2014-01-01 | 2013-07-01 | 2014-01-01
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SF-BNR-RK | STEP FEED BNR AT ROCKAWAY | 2 | PRELIMINARY DESIGN | 2014-01-02 | 2015-12-02 | 2014-01-02 | 2015-12-02
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SF-BNR-RK | STEP FEED BNR AT ROCKAWAY | 3 | FINAL DESIGN | 2015-12-03 | 2016-12-31 | 2015-12-03 | 2016-12-31
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SF-BNR-RK | STEP FEED BNR AT ROCKAWAY | 4 | BID AWARD AND REGISTER CONTRCT | 2017-01-01 | 2017-09-02 | 2017-01-01 | 2017-09-02
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SF-BNR-RK | STEP FEED BNR AT ROCKAWAY | 5 | CONSTRUCTION TO 25% | 2017-09-03 | 2018-06-30 | 2017-09-03 | 2018-06-30
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SF-BNR-RK | STEP FEED BNR AT ROCKAWAY | 6 | CONSTRUCTION TO 50% | 2018-07-01 | 2019-03-01 | 2018-07-01 | 2019-03-01
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SF-BNR-RK | STEP FEED BNR AT ROCKAWAY | 7 | CONSTRUCTION TO 75% | 2019-03-02 | 2019-12-01 | 2019-03-02 | 2019-12-01
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SF-BNR-RK | STEP FEED BNR AT ROCKAWAY | 8 | ORIGINAL EQUIP & FURNISHING | 2019-12-02 | 2020-05-29 | 2019-12-02 | 2020-05-29
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SF-BNR-RK | STEP FEED BNR AT ROCKAWAY | 9 | SUBSTANTIAL COMPLETION | 2020-05-30 | 2020-11-30 | 2020-05-30 | 2020-11-30
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SF-BNR-RK | STEP FEED BNR AT ROCKAWAY | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-12-01 | 2021-12-25 | 2020-12-01 | 2021-12-25
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | STA24TNKS | STATION 24 GROUNDWATER TANKS DEMOLITION | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-08-29 | 2024-06-01 | 2024-08-29
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | STA24TNKS | STATION 24 GROUNDWATER TANKS DEMOLITION | 2 | PRELIMINARY DESIGN | 2020-08-30 | 2020-12-27 | 2024-08-30 | 2024-12-27
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | STA24TNKS | STATION 24 GROUNDWATER TANKS DEMOLITION | 3 | FINAL DESIGN | 2020-12-28 | 2021-06-25 | 2024-12-28 | 2025-06-25
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | STA24TNKS | STATION 24 GROUNDWATER TANKS DEMOLITION | 4 | BID AWARD AND REGISTER CONTRCT | 2021-06-26 | 2021-09-23 | 2025-06-26 | 2025-09-23
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | STA24TNKS | STATION 24 GROUNDWATER TANKS DEMOLITION | 5 | CONSTRUCTION TO 25% | 2021-09-24 | 2022-01-21 | 2025-09-24 | 2026-01-21
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | STA24TNKS | STATION 24 GROUNDWATER TANKS DEMOLITION | 6 | CONSTRUCTION TO 50% | 2022-01-22 | 2022-05-21 | 2026-01-22 | 2026-05-21
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | STA24TNKS | STATION 24 GROUNDWATER TANKS DEMOLITION | 7 | CONSTRUCTION TO 75% | 2022-05-22 | 2022-09-18 | 2026-05-22 | 2026-09-18
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | STA24TNKS | STATION 24 GROUNDWATER TANKS DEMOLITION | 8 | ORIGINAL EQUIP & FURNISHING | 2022-09-19 | 2022-12-17 | 2026-09-19 | 2026-12-17
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | STA24TNKS | STATION 24 GROUNDWATER TANKS DEMOLITION | 9 | SUBSTANTIAL COMPLETION | 2022-12-18 | 2023-02-15 | 2026-12-18 | 2027-02-15
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | STA24TNKS | STATION 24 GROUNDWATER TANKS DEMOLITION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-02-16 | 2023-03-17 | 2027-02-16 | 2027-03-17
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-167-L | RECONSTRUCTION OF SEAWALL/DOCK @ TALLMAN ISLAND WPCP | 1 | DEVELOP SCOPE | 2016-07-01 | 2017-03-27 | 2015-07-01 | 2016-03-26
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-167-L | RECONSTRUCTION OF SEAWALL/DOCK @ TALLMAN ISLAND WPCP | 2 | PRELIMINARY DESIGN | 2017-03-28 | 2018-03-22 | 2016-03-27 | 2017-03-21
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-167-L | RECONSTRUCTION OF SEAWALL/DOCK @ TALLMAN ISLAND WPCP | 3 | FINAL DESIGN | 2018-03-23 | 2019-09-13 | 2017-03-22 | 2018-09-12
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-167-L | RECONSTRUCTION OF SEAWALL/DOCK @ TALLMAN ISLAND WPCP | 4 | BID AWARD AND REGISTER CONTRCT | 2019-09-14 | 2020-06-09 | 2018-09-13 | 2019-06-09
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-167-L | RECONSTRUCTION OF SEAWALL/DOCK @ TALLMAN ISLAND WPCP | 5 | CONSTRUCTION TO 25% | 2020-06-10 | 2021-06-04 | 2019-06-10 | 2020-06-03
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-167-L | RECONSTRUCTION OF SEAWALL/DOCK @ TALLMAN ISLAND WPCP | 6 | CONSTRUCTION TO 50% | 2021-06-05 | 2022-05-30 | 2020-06-04 | 2021-05-29
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-167-L | RECONSTRUCTION OF SEAWALL/DOCK @ TALLMAN ISLAND WPCP | 7 | CONSTRUCTION TO 75% | 2022-05-31 | 2023-05-25 | 2021-05-30 | 2022-05-24
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-167-L | RECONSTRUCTION OF SEAWALL/DOCK @ TALLMAN ISLAND WPCP | 8 | ORIGINAL EQUIP & FURNISHING | 2023-05-26 | 2024-02-19 | 2022-05-25 | 2023-02-18
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-167-L | RECONSTRUCTION OF SEAWALL/DOCK @ TALLMAN ISLAND WPCP | 9 | SUBSTANTIAL COMPLETION | 2024-02-20 | 2024-08-17 | 2023-02-19 | 2023-08-17
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-167-L | RECONSTRUCTION OF SEAWALL/DOCK @ TALLMAN ISLAND WPCP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-08-18 | 2024-11-15 | 2023-08-18 | 2023-11-15
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-168-L | HEADWORKS IMPROVEMENTS AT THE TALLMAN ISLAND WPCP | 1 | DEVELOP SCOPE | 2016-07-01 | 2017-03-27 | 2015-07-01 | 2016-03-26
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-168-L | HEADWORKS IMPROVEMENTS AT THE TALLMAN ISLAND WPCP | 2 | PRELIMINARY DESIGN | 2017-03-28 | 2018-03-22 | 2016-03-27 | 2017-03-21
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-168-L | HEADWORKS IMPROVEMENTS AT THE TALLMAN ISLAND WPCP | 3 | FINAL DESIGN | 2018-03-23 | 2019-09-13 | 2017-03-22 | 2018-09-12
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-168-L | HEADWORKS IMPROVEMENTS AT THE TALLMAN ISLAND WPCP | 4 | BID AWARD AND REGISTER CONTRCT | 2019-09-14 | 2020-06-09 | 2018-09-13 | 2019-06-09
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-168-L | HEADWORKS IMPROVEMENTS AT THE TALLMAN ISLAND WPCP | 5 | CONSTRUCTION TO 25% | 2020-06-10 | 2021-06-04 | 2019-06-10 | 2020-06-03
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-168-L | HEADWORKS IMPROVEMENTS AT THE TALLMAN ISLAND WPCP | 6 | CONSTRUCTION TO 50% | 2021-06-05 | 2022-05-30 | 2020-06-04 | 2021-05-29
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-168-L | HEADWORKS IMPROVEMENTS AT THE TALLMAN ISLAND WPCP | 7 | CONSTRUCTION TO 75% | 2022-05-31 | 2023-05-25 | 2021-05-30 | 2022-05-24
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-168-L | HEADWORKS IMPROVEMENTS AT THE TALLMAN ISLAND WPCP | 8 | ORIGINAL EQUIP & FURNISHING | 2023-05-26 | 2024-02-19 | 2022-05-25 | 2023-02-18
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-168-L | HEADWORKS IMPROVEMENTS AT THE TALLMAN ISLAND WPCP | 9 | SUBSTANTIAL COMPLETION | 2024-02-20 | 2024-08-17 | 2023-02-19 | 2023-08-17
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-168-L | HEADWORKS IMPROVEMENTS AT THE TALLMAN ISLAND WPCP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-08-18 | 2024-11-15 | 2023-08-18 | 2023-11-15
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-169-L | RECONSTRUCT OF THE POWER DISTRIBUTION AT TALLMAN ISLAND WPCP | 1 | DEVELOP SCOPE | 2017-07-01 | 2018-03-27 | 2015-07-01 | 2016-03-26
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-169-L | RECONSTRUCT OF THE POWER DISTRIBUTION AT TALLMAN ISLAND WPCP | 2 | PRELIMINARY DESIGN | 2018-03-28 | 2019-03-22 | 2016-03-27 | 2017-03-21
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-169-L | RECONSTRUCT OF THE POWER DISTRIBUTION AT TALLMAN ISLAND WPCP | 3 | FINAL DESIGN | 2019-03-23 | 2020-09-12 | 2017-03-22 | 2018-09-12
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-169-L | RECONSTRUCT OF THE POWER DISTRIBUTION AT TALLMAN ISLAND WPCP | 4 | BID AWARD AND REGISTER CONTRCT | 2020-09-13 | 2021-06-09 | 2018-09-13 | 2019-06-09
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-169-L | RECONSTRUCT OF THE POWER DISTRIBUTION AT TALLMAN ISLAND WPCP | 5 | CONSTRUCTION TO 25% | 2021-06-10 | 2022-06-04 | 2019-06-10 | 2020-06-03
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-169-L | RECONSTRUCT OF THE POWER DISTRIBUTION AT TALLMAN ISLAND WPCP | 6 | CONSTRUCTION TO 50% | 2022-06-05 | 2023-05-30 | 2020-06-04 | 2021-05-29
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-169-L | RECONSTRUCT OF THE POWER DISTRIBUTION AT TALLMAN ISLAND WPCP | 7 | CONSTRUCTION TO 75% | 2023-05-31 | 2024-05-24 | 2021-05-30 | 2022-05-24
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-169-L | RECONSTRUCT OF THE POWER DISTRIBUTION AT TALLMAN ISLAND WPCP | 8 | ORIGINAL EQUIP & FURNISHING | 2024-05-25 | 2025-02-18 | 2022-05-25 | 2023-02-18
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-169-L | RECONSTRUCT OF THE POWER DISTRIBUTION AT TALLMAN ISLAND WPCP | 9 | SUBSTANTIAL COMPLETION | 2025-02-19 | 2025-08-17 | 2023-02-19 | 2023-08-17
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-169-L | RECONSTRUCT OF THE POWER DISTRIBUTION AT TALLMAN ISLAND WPCP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-08-18 | 2025-11-15 | 2023-08-18 | 2023-11-15
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-174 | TRC- Installation of new outfall at Tallman Island WWTP | 1 | DEVELOP SCOPE | 2020-06-01 | 2021-02-25 | 2020-06-01 | 2021-02-25
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-174 | TRC- Installation of new outfall at Tallman Island WWTP | 2 | PRELIMINARY DESIGN | 2021-02-26 | 2022-02-20 | 2021-02-26 | 2022-02-20
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-174 | TRC- Installation of new outfall at Tallman Island WWTP | 3 | FINAL DESIGN | 2022-02-21 | 2023-08-14 | 2022-02-21 | 2023-08-14
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-174 | TRC- Installation of new outfall at Tallman Island WWTP | 4 | BID AWARD AND REGISTER CONTRCT | 2023-08-15 | 2024-05-10 | 2023-08-15 | 2024-05-10
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-174 | TRC- Installation of new outfall at Tallman Island WWTP | 5 | CONSTRUCTION TO 25% | 2024-05-11 | 2025-05-05 | 2024-05-11 | 2025-05-05
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-174 | TRC- Installation of new outfall at Tallman Island WWTP | 6 | CONSTRUCTION TO 50% | 2025-05-06 | 2026-04-30 | 2025-05-06 | 2026-04-30
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-174 | TRC- Installation of new outfall at Tallman Island WWTP | 7 | CONSTRUCTION TO 75% | 2026-05-01 | 2027-04-25 | 2026-05-01 | 2027-04-25
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-174 | TRC- Installation of new outfall at Tallman Island WWTP | 8 | ORIGINAL EQUIP & FURNISHING | 2027-04-26 | 2028-01-20 | 2027-04-26 | 2028-01-20
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-174 | TRC- Installation of new outfall at Tallman Island WWTP | 9 | SUBSTANTIAL COMPLETION | 2028-01-21 | 2028-07-18 | 2028-01-21 | 2028-07-18
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-174 | TRC- Installation of new outfall at Tallman Island WWTP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2028-07-19 | 2028-10-16 | 2028-07-19 | 2028-10-16
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-5 | TALLMAN ISLAND LANDSCAPING UPGRADE & MISC. SITE IMPROVEMENTS | 1 | DEVELOP SCOPE | 2015-07-01 | 2016-03-26 | 2015-07-01 | 2016-03-26
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-5 | TALLMAN ISLAND LANDSCAPING UPGRADE & MISC. SITE IMPROVEMENTS | 2 | PRELIMINARY DESIGN | 2016-03-27 | 2017-03-21 | 2016-03-27 | 2017-03-21
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-5 | TALLMAN ISLAND LANDSCAPING UPGRADE & MISC. SITE IMPROVEMENTS | 3 | FINAL DESIGN | 2017-03-22 | 2018-09-12 | 2017-03-22 | 2018-09-12
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-5 | TALLMAN ISLAND LANDSCAPING UPGRADE & MISC. SITE IMPROVEMENTS | 4 | BID AWARD AND REGISTER CONTRCT | 2018-09-13 | 2019-06-09 | 2018-09-13 | 2019-06-09
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-5 | TALLMAN ISLAND LANDSCAPING UPGRADE & MISC. SITE IMPROVEMENTS | 5 | CONSTRUCTION TO 25% | 2019-06-10 | 2020-06-03 | 2019-06-10 | 2020-06-03
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-5 | TALLMAN ISLAND LANDSCAPING UPGRADE & MISC. SITE IMPROVEMENTS | 6 | CONSTRUCTION TO 50% | 2020-06-04 | 2021-05-29 | 2020-06-04 | 2021-05-29
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-5 | TALLMAN ISLAND LANDSCAPING UPGRADE & MISC. SITE IMPROVEMENTS | 7 | CONSTRUCTION TO 75% | 2021-05-30 | 2022-05-24 | 2021-05-30 | 2022-05-24
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-5 | TALLMAN ISLAND LANDSCAPING UPGRADE & MISC. SITE IMPROVEMENTS | 8 | ORIGINAL EQUIP & FURNISHING | 2022-05-25 | 2023-02-18 | 2022-05-25 | 2023-02-18
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-5 | TALLMAN ISLAND LANDSCAPING UPGRADE & MISC. SITE IMPROVEMENTS | 9 | SUBSTANTIAL COMPLETION | 2023-02-19 | 2023-08-17 | 2023-02-19 | 2023-08-17
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-5 | TALLMAN ISLAND LANDSCAPING UPGRADE & MISC. SITE IMPROVEMENTS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-08-18 | 2023-11-15 | 2023-08-18 | 2023-11-15
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-STAB | STABILIZATION OF THE TALLMANS' ISLAND WPCP | 1 | DEVELOP SCOPE | 1994-04-01 | 1994-06-29 | 2002-02-16 | 2002-11-12
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-STAB | STABILIZATION OF THE TALLMANS' ISLAND WPCP | 2 | PRELIMINARY DESIGN | 1994-06-30 | 1994-10-27 | 2002-11-13 | 2003-11-07
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-STAB | STABILIZATION OF THE TALLMANS' ISLAND WPCP | 3 | FINAL DESIGN | 1994-10-28 | 1995-04-25 | 2003-11-08 | 2005-04-30
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-STAB | STABILIZATION OF THE TALLMANS' ISLAND WPCP | 4 | BID AWARD AND REGISTER CONTRCT | 1995-04-26 | 1995-07-24 | 2005-05-01 | 2006-01-25
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-STAB | STABILIZATION OF THE TALLMANS' ISLAND WPCP | 5 | CONSTRUCTION TO 25% | 1995-07-25 | 1995-11-21 | 2006-01-26 | 2007-01-20
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-STAB | STABILIZATION OF THE TALLMANS' ISLAND WPCP | 6 | CONSTRUCTION TO 50% | 1995-11-22 | 1996-03-20 | 2007-01-21 | 2008-01-15
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-STAB | STABILIZATION OF THE TALLMANS' ISLAND WPCP | 7 | CONSTRUCTION TO 75% | 1996-03-21 | 1996-07-18 | 2008-01-16 | 2009-01-09
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-STAB | STABILIZATION OF THE TALLMANS' ISLAND WPCP | 8 | ORIGINAL EQUIP & FURNISHING | 1996-07-19 | 1996-10-16 | 2009-01-10 | 2009-10-06
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-STAB | STABILIZATION OF THE TALLMANS' ISLAND WPCP | 9 | SUBSTANTIAL COMPLETION | 1996-10-17 | 1996-12-15 | 2009-10-07 | 2022-04-01
20201123 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-STAB | STABILIZATION OF THE TALLMANS' ISLAND WPCP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 1996-12-16 | 1997-01-14 | 2022-04-02 | 2022-06-30
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-251E | QUEENS CRS AIR COMPRESSORS REPLACEMENT | 1 | DEVELOP SCOPE | 2016-10-03 | 2016-12-31 | 2016-10-03 | 2016-12-31
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-251E | QUEENS CRS AIR COMPRESSORS REPLACEMENT | 2 | PRELIMINARY DESIGN | 2017-01-01 | 2017-06-29 | 2017-01-01 | 2017-06-29
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-251E | QUEENS CRS AIR COMPRESSORS REPLACEMENT | 3 | FINAL DESIGN | 2017-06-30 | 2017-12-26 | 2017-06-30 | 2017-12-26
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-251E | QUEENS CRS AIR COMPRESSORS REPLACEMENT | 4 | BID AWARD AND REGISTER CONTRCT | 2017-12-27 | 2018-09-22 | 2017-12-27 | 2018-09-22
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-251E | QUEENS CRS AIR COMPRESSORS REPLACEMENT | 5 | CONSTRUCTION TO 25% | 2018-09-23 | 2019-09-22 | 2018-09-23 | 2019-09-22
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-251E | QUEENS CRS AIR COMPRESSORS REPLACEMENT | 6 | CONSTRUCTION TO 50% | 2019-09-23 | 2020-09-21 | 2019-09-23 | 2020-09-21
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-251E | QUEENS CRS AIR COMPRESSORS REPLACEMENT | 7 | CONSTRUCTION TO 75% | 2020-09-22 | 2021-09-21 | 2020-09-22 | 2021-09-21
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-251E | QUEENS CRS AIR COMPRESSORS REPLACEMENT | 8 | SUBSTANTIAL COMPLETION | 2021-09-22 | 2022-09-21 | 2021-09-22 | 2022-09-21
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-251E | QUEENS CRS AIR COMPRESSORS REPLACEMENT | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-22 | 2024-08-21 | 2022-09-22 | 2024-08-21
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-251F | QUEENS CRS FIFTH FLOOR SLAB SECTIONS REPLACEMENT | 1 | DEVELOP SCOPE | 2015-06-03 | 2015-08-31 | 2015-06-03 | 2015-08-31
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-251F | QUEENS CRS FIFTH FLOOR SLAB SECTIONS REPLACEMENT | 2 | PRELIMINARY DESIGN | 2015-09-01 | 2016-02-27 | 2015-09-01 | 2016-02-27
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-251F | QUEENS CRS FIFTH FLOOR SLAB SECTIONS REPLACEMENT | 3 | FINAL DESIGN | 2016-02-28 | 2016-09-14 | 2016-02-28 | 2016-09-14
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-251F | QUEENS CRS FIFTH FLOOR SLAB SECTIONS REPLACEMENT | 4 | BID AWARD AND REGISTER CONTRCT | 2016-09-15 | 2017-04-02 | 2016-09-15 | 2017-04-02
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-251F | QUEENS CRS FIFTH FLOOR SLAB SECTIONS REPLACEMENT | 5 | CONSTRUCTION TO 25% | 2017-04-03 | 2018-04-02 | 2017-04-03 | 2018-04-02
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-251F | QUEENS CRS FIFTH FLOOR SLAB SECTIONS REPLACEMENT | 6 | CONSTRUCTION TO 50% | 2018-04-03 | 2019-04-02 | 2018-04-03 | 2020-02-11
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-251F | QUEENS CRS FIFTH FLOOR SLAB SECTIONS REPLACEMENT | 7 | CONSTRUCTION TO 75% | 2019-04-03 | 2020-04-01 | 2020-02-12 | 2021-06-25
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-251F | QUEENS CRS FIFTH FLOOR SLAB SECTIONS REPLACEMENT | 8 | SUBSTANTIAL COMPLETION | 2020-04-02 | 2021-04-01 | 2021-06-26 | 2022-06-25
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-251F | QUEENS CRS FIFTH FLOOR SLAB SECTIONS REPLACEMENT | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-04-02 | 2023-12-27 | 2022-06-26 | 2023-12-27
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-251G | QUEENS CRS Dynamometer Test Cell HVAC Replacement | 1 | DEVELOP SCOPE | 2016-10-03 | 2016-11-16 | 2016-10-03 | 2016-11-16
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-251G | QUEENS CRS Dynamometer Test Cell HVAC Replacement | 2 | PRELIMINARY DESIGN | 2016-11-17 | 2016-12-31 | 2016-11-17 | 2016-12-31
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-251G | QUEENS CRS Dynamometer Test Cell HVAC Replacement | 3 | FINAL DESIGN | 2017-01-01 | 2017-03-01 | 2017-01-01 | 2017-03-01
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-251G | QUEENS CRS Dynamometer Test Cell HVAC Replacement | 4 | BID AWARD AND REGISTER CONTRCT | 2017-03-02 | 2017-11-26 | 2017-03-02 | 2017-11-26
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-251G | QUEENS CRS Dynamometer Test Cell HVAC Replacement | 5 | CONSTRUCTION TO 25% | 2017-11-27 | 2018-08-23 | 2017-11-27 | 2018-08-23
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-251G | QUEENS CRS Dynamometer Test Cell HVAC Replacement | 6 | CONSTRUCTION TO 50% | 2018-08-24 | 2019-05-20 | 2018-08-24 | 2019-05-20
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-251G | QUEENS CRS Dynamometer Test Cell HVAC Replacement | 7 | CONSTRUCTION TO 75% | 2019-05-21 | 2020-02-14 | 2019-05-21 | 2020-02-14
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-251G | QUEENS CRS Dynamometer Test Cell HVAC Replacement | 8 | SUBSTANTIAL COMPLETION | 2020-02-15 | 2020-11-10 | 2020-02-15 | 2020-11-10
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-251G | QUEENS CRS Dynamometer Test Cell HVAC Replacement | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-11-11 | 2021-03-10 | 2020-11-11 | 2021-03-10
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-251H | CRS Water Tank Rehabilitation | 1 | DEVELOP SCOPE | 2019-04-03 | 2019-05-17 | 2019-04-03 | 2019-05-17
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-251H | CRS Water Tank Rehabilitation | 2 | PRELIMINARY DESIGN | 2019-05-18 | 2019-08-15 | 2019-05-18 | 2019-08-15
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-251H | CRS Water Tank Rehabilitation | 3 | FINAL DESIGN | 2019-08-16 | 2019-11-13 | 2019-08-16 | 2019-11-13
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-251H | CRS Water Tank Rehabilitation | 4 | BID AWARD AND REGISTER CONTRCT | 2019-11-14 | 2020-06-30 | 2019-11-14 | 2020-06-30
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-251H | CRS Water Tank Rehabilitation | 5 | CONSTRUCTION TO 25% | 2020-07-01 | 2021-01-16 | 2020-07-01 | 2021-01-16
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-251H | CRS Water Tank Rehabilitation | 6 | CONSTRUCTION TO 50% | 2021-01-17 | 2021-08-04 | 2021-01-17 | 2021-08-04
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-251H | CRS Water Tank Rehabilitation | 7 | CONSTRUCTION TO 75% | 2021-08-05 | 2022-02-20 | 2021-08-05 | 2022-02-20
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-251H | CRS Water Tank Rehabilitation | 8 | SUBSTANTIAL COMPLETION | 2022-02-21 | 2022-09-08 | 2022-02-21 | 2022-09-08
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-251H | CRS Water Tank Rehabilitation | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-09 | 2023-01-06 | 2022-09-09 | 2023-01-06
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-251K | Queens CRS Server Room Air Conditioning | 1 | DEVELOP SCOPE | 2019-04-03 | 2019-07-01 | 2019-04-03 | 2019-07-01
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-251K | Queens CRS Server Room Air Conditioning | 2 | PRELIMINARY DESIGN | 2019-07-02 | 2019-10-29 | 2019-07-02 | 2019-10-29
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-251K | Queens CRS Server Room Air Conditioning | 3 | FINAL DESIGN | 2019-10-30 | 2020-01-27 | 2019-10-30 | 2020-01-27
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-251K | Queens CRS Server Room Air Conditioning | 4 | BID AWARD AND REGISTER CONTRCT | 2020-01-28 | 2020-06-30 | 2020-01-28 | 2020-06-30
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-251K | Queens CRS Server Room Air Conditioning | 5 | CONSTRUCTION TO 25% | 2020-07-01 | 2020-12-27 | 2020-07-01 | 2020-12-27
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-251K | Queens CRS Server Room Air Conditioning | 6 | CONSTRUCTION TO 50% | 2020-12-28 | 2021-06-25 | 2020-12-28 | 2021-06-25
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-251K | Queens CRS Server Room Air Conditioning | 7 | CONSTRUCTION TO 75% | 2021-06-26 | 2021-12-22 | 2021-06-26 | 2021-12-22
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-251K | Queens CRS Server Room Air Conditioning | 8 | SUBSTANTIAL COMPLETION | 2021-12-23 | 2022-12-22 | 2021-12-23 | 2022-12-22
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-251K | Queens CRS Server Room Air Conditioning | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-12-23 | 2023-12-22 | 2022-12-23 | 2023-12-22
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-251V | QUEENS CRS Elevator Reconstruction | 1 | DEVELOP SCOPE | 2007-08-01 | 2007-11-08 | 2007-08-01 | 2007-11-08
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-251V | QUEENS CRS Elevator Reconstruction | 2 | PRELIMINARY DESIGN | 2007-11-09 | 2008-02-16 | 2007-11-09 | 2008-11-07
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-251V | QUEENS CRS Elevator Reconstruction | 3 | FINAL DESIGN | 2008-02-17 | 2008-05-26 | 2008-11-08 | 2015-09-12
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-251V | QUEENS CRS Elevator Reconstruction | 4 | BID AWARD AND REGISTER CONTRCT | 2008-05-27 | 2008-09-03 | 2015-09-13 | 2015-09-12
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-251V | QUEENS CRS Elevator Reconstruction | 5 | CONSTRUCTION TO 25% | 2008-07-06 | 2009-04-11 | 2015-09-13 | 2015-09-12
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-251V | QUEENS CRS Elevator Reconstruction | 6 | CONSTRUCTION TO 50% | 2009-04-11 | 2010-01-15 | 2015-09-13 | 2015-09-12
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-251V | QUEENS CRS Elevator Reconstruction | 7 | CONSTRUCTION TO 75% | 2010-01-15 | 2010-10-21 | 2015-09-13 | 2015-09-12
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-251V | QUEENS CRS Elevator Reconstruction | 8 | SUBSTANTIAL COMPLETION | 2010-10-22 | 2011-11-25 | 2014-12-08 | 2019-12-07
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-251V | QUEENS CRS Elevator Reconstruction | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2011-11-26 | 2012-12-29 | 2019-12-08 | 2020-09-12
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-264Q | Queens 6 Betts Ave Garage Roof Replacement | 1 | DEVELOP SCOPE | 2015-04-01 | 2015-05-15 | 2015-04-01 | 2015-05-15
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-264Q | Queens 6 Betts Ave Garage Roof Replacement | 2 | PRELIMINARY DESIGN | 2015-05-16 | 2015-07-14 | 2015-05-16 | 2015-07-14
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-264Q | Queens 6 Betts Ave Garage Roof Replacement | 3 | FINAL DESIGN | 2015-07-15 | 2015-09-12 | 2015-07-15 | 2015-09-12
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-264Q | Queens 6 Betts Ave Garage Roof Replacement | 4 | BID AWARD AND REGISTER CONTRCT | 2015-09-13 | 2015-12-11 | 2015-09-13 | 2015-12-11
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-264Q | Queens 6 Betts Ave Garage Roof Replacement | 5 | CONSTRUCTION TO 25% | 2015-12-12 | 2016-06-28 | 2015-12-12 | 2017-04-24
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-264Q | Queens 6 Betts Ave Garage Roof Replacement | 6 | CONSTRUCTION TO 50% | 2016-06-29 | 2017-01-14 | 2017-04-25 | 2019-02-03
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-264Q | Queens 6 Betts Ave Garage Roof Replacement | 7 | CONSTRUCTION TO 75% | 2017-01-15 | 2017-08-02 | 2019-02-04 | 2021-02-22
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-264Q | Queens 6 Betts Ave Garage Roof Replacement | 8 | SUBSTANTIAL COMPLETION | 2017-08-03 | 2018-02-18 | 2021-02-23 | 2021-09-10
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-264Q | Queens 6 Betts Ave Garage Roof Replacement | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-02-19 | 2020-01-19 | 2021-09-11 | 2023-08-11
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-332N | QUEENS 8/10/12 GARAGE REHAB | 1 | DEVELOP SCOPE | 2016-07-01 | 2017-07-05 | 2016-07-01 | 2017-07-05
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-332N | QUEENS 8/10/12 GARAGE REHAB | 2 | PRELIMINARY DESIGN | 2017-07-06 | 2018-07-05 | 2017-07-06 | 2018-07-05
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-332N | QUEENS 8/10/12 GARAGE REHAB | 3 | FINAL DESIGN | 2018-07-06 | 2019-07-05 | 2018-07-06 | 2019-07-05
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-332N | QUEENS 8/10/12 GARAGE REHAB | 4 | BID AWARD AND REGISTER CONTRCT | 2019-07-06 | 2020-08-08 | 2019-07-06 | 2020-08-08
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-332N | QUEENS 8/10/12 GARAGE REHAB | 5 | CONSTRUCTION TO 25% | 2020-08-09 | 2021-12-21 | 2020-08-09 | 2021-12-21
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-332N | QUEENS 8/10/12 GARAGE REHAB | 6 | CONSTRUCTION TO 50% | 2021-12-22 | 2023-05-05 | 2021-12-22 | 2023-05-05
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-332N | QUEENS 8/10/12 GARAGE REHAB | 7 | CONSTRUCTION TO 75% | 2023-05-06 | 2024-09-16 | 2023-05-06 | 2024-09-16
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-332N | QUEENS 8/10/12 GARAGE REHAB | 8 | SUBSTANTIAL COMPLETION | 2024-09-17 | 2026-01-29 | 2024-09-17 | 2026-01-29
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-332N | QUEENS 8/10/12 GARAGE REHAB | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2026-01-30 | 2027-06-13 | 2026-01-30 | 2027-06-13
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-380F | Queens 1 Garage Boilers Rehabilitation | 1 | DEVELOP SCOPE | 2020-05-01 | 2020-06-14 | 2020-05-01 | 2020-06-14
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-380F | Queens 1 Garage Boilers Rehabilitation | 2 | PRELIMINARY DESIGN | 2020-06-15 | 2020-08-13 | 2020-06-15 | 2020-08-13
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-380F | Queens 1 Garage Boilers Rehabilitation | 3 | FINAL DESIGN | 2020-08-14 | 2020-10-12 | 2020-08-14 | 2020-10-12
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-380F | Queens 1 Garage Boilers Rehabilitation | 4 | BID AWARD AND REGISTER CONTRCT | 2020-10-13 | 2021-04-10 | 2020-10-13 | 2021-04-10
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-380F | Queens 1 Garage Boilers Rehabilitation | 5 | CONSTRUCTION TO 25% | 2021-04-11 | 2021-07-09 | 2021-04-11 | 2021-07-09
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-380F | Queens 1 Garage Boilers Rehabilitation | 6 | CONSTRUCTION TO 50% | 2021-07-10 | 2021-10-07 | 2021-07-10 | 2021-10-07
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-380F | Queens 1 Garage Boilers Rehabilitation | 7 | CONSTRUCTION TO 75% | 2021-10-08 | 2022-02-04 | 2021-10-08 | 2022-02-04
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-380F | Queens 1 Garage Boilers Rehabilitation | 8 | SUBSTANTIAL COMPLETION | 2022-02-05 | 2022-07-04 | 2022-02-05 | 2022-07-04
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-380F | Queens 1 Garage Boilers Rehabilitation | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-07-05 | 2023-07-04 | 2022-07-05 | 2023-07-04
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-431 | QUEENS 1 GARAGE | 1 | DEVELOP SCOPE | 2015-09-01 | 2016-08-30 | 2015-09-01 | 2019-07-01
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-431 | QUEENS 1 GARAGE | 2 | PRELIMINARY DESIGN | 2017-05-08 | 2018-09-19 | 2019-07-02 | 2020-03-07
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-431 | QUEENS 1 GARAGE | 3 | FINAL DESIGN | 2018-09-20 | 2020-02-01 | 2020-03-08 | 2021-07-20
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-431 | QUEENS 1 GARAGE | 4 | BID AWARD AND REGISTER CONTRCT | 2020-02-02 | 2021-06-15 | 2021-07-21 | 2022-12-02
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-431 | QUEENS 1 GARAGE | 5 | CONSTRUCTION TO 25% | 2021-06-16 | 2022-10-28 | 2022-12-03 | 2024-04-15
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-431 | QUEENS 1 GARAGE | 6 | CONSTRUCTION TO 50% | 2022-10-29 | 2024-03-11 | 2024-04-16 | 2025-08-28
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-431 | QUEENS 1 GARAGE | 7 | CONSTRUCTION TO 75% | 2024-03-12 | 2025-07-24 | 2025-08-29 | 2027-01-10
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-431 | QUEENS 1 GARAGE | 8 | SUBSTANTIAL COMPLETION | 2025-07-25 | 2026-12-06 | 2027-01-11 | 2028-05-24
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-431 | QUEENS 1 GARAGE | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2026-12-07 | 2028-04-19 | 2028-05-25 | 2029-10-06
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-431A | Queens 1 Garage Rehabilitation | 1 | DEVELOP SCOPE | 2020-02-01 | 2020-03-16 | 2020-02-01 | 2020-03-16
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-431A | Queens 1 Garage Rehabilitation | 2 | PRELIMINARY DESIGN | 2020-03-17 | 2020-05-15 | 2020-03-17 | 2020-05-15
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-431A | Queens 1 Garage Rehabilitation | 3 | FINAL DESIGN | 2020-05-16 | 2020-07-14 | 2020-05-16 | 2020-07-14
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-431A | Queens 1 Garage Rehabilitation | 4 | BID AWARD AND REGISTER CONTRCT | 2020-07-15 | 2020-10-12 | 2020-07-15 | 2020-10-12
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-431A | Queens 1 Garage Rehabilitation | 5 | CONSTRUCTION TO 25% | 2020-10-13 | 2021-01-10 | 2020-10-13 | 2021-01-10
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-431A | Queens 1 Garage Rehabilitation | 6 | CONSTRUCTION TO 50% | 2021-01-11 | 2021-04-10 | 2021-01-11 | 2021-04-10
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-431A | Queens 1 Garage Rehabilitation | 7 | CONSTRUCTION TO 75% | 2021-04-11 | 2021-08-08 | 2021-04-11 | 2021-08-08
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-431A | Queens 1 Garage Rehabilitation | 8 | SUBSTANTIAL COMPLETION | 2021-08-09 | 2022-01-05 | 2021-08-09 | 2022-01-05
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-431A | Queens 1 Garage Rehabilitation | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-01-06 | 2023-03-31 | 2022-01-06 | 2023-03-31
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-442 | Queens Northborough Repair Shop Fire Alarm System Replacemen | 1 | DEVELOP SCOPE | 2016-11-01 | 2016-12-15 | 2016-11-01 | 2016-12-15
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-442 | Queens Northborough Repair Shop Fire Alarm System Replacemen | 2 | PRELIMINARY DESIGN | 2016-12-16 | 2017-05-24 | 2016-12-16 | 2017-05-24
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-442 | Queens Northborough Repair Shop Fire Alarm System Replacemen | 3 | FINAL DESIGN | 2017-05-25 | 2017-09-01 | 2017-05-25 | 2017-09-01
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-442 | Queens Northborough Repair Shop Fire Alarm System Replacemen | 4 | BID AWARD AND REGISTER CONTRCT | 2017-09-02 | 2017-11-30 | 2017-09-02 | 2017-11-30
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-442 | Queens Northborough Repair Shop Fire Alarm System Replacemen | 5 | CONSTRUCTION TO 25% | 2017-12-01 | 2018-05-29 | 2017-12-01 | 2018-05-29
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-442 | Queens Northborough Repair Shop Fire Alarm System Replacemen | 6 | CONSTRUCTION TO 50% | 2018-05-30 | 2018-11-25 | 2018-05-30 | 2018-11-25
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-442 | Queens Northborough Repair Shop Fire Alarm System Replacemen | 7 | CONSTRUCTION TO 75% | 2018-11-26 | 2019-05-24 | 2018-11-26 | 2019-05-24
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-442 | Queens Northborough Repair Shop Fire Alarm System Replacemen | 8 | SUBSTANTIAL COMPLETION | 2019-05-25 | 2022-02-17 | 2019-05-25 | 2022-02-17
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-442 | Queens Northborough Repair Shop Fire Alarm System Replacemen | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-02-18 | 2024-08-05 | 2022-02-18 | 2024-08-05
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-445 | Queens 6 Betts Ave Garage Rehab | 1 | DEVELOP SCOPE | 2020-08-01 | 2021-07-31 | 2020-08-01 | 2021-07-31
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-445 | Queens 6 Betts Ave Garage Rehab | 2 | PRELIMINARY DESIGN | 2021-08-01 | 2022-04-07 | 2021-08-01 | 2022-04-07
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-445 | Queens 6 Betts Ave Garage Rehab | 3 | FINAL DESIGN | 2022-04-08 | 2022-12-13 | 2022-04-08 | 2022-12-13
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-445 | Queens 6 Betts Ave Garage Rehab | 4 | BID AWARD AND REGISTER CONTRCT | 2022-12-14 | 2023-08-20 | 2022-12-14 | 2023-08-20
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-445 | Queens 6 Betts Ave Garage Rehab | 5 | CONSTRUCTION TO 25% | 2023-08-21 | 2024-08-19 | 2023-08-21 | 2024-08-19
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-445 | Queens 6 Betts Ave Garage Rehab | 6 | CONSTRUCTION TO 50% | 2024-08-20 | 2025-08-19 | 2024-08-20 | 2025-08-19
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-445 | Queens 6 Betts Ave Garage Rehab | 7 | CONSTRUCTION TO 75% | 2025-08-20 | 2026-08-19 | 2025-08-20 | 2026-08-19
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-445 | Queens 6 Betts Ave Garage Rehab | 8 | SUBSTANTIAL COMPLETION | 2026-08-20 | 2027-08-19 | 2026-08-20 | 2027-08-19
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-445 | Queens 6 Betts Ave Garage Rehab | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2027-08-20 | 2029-07-19 | 2027-08-20 | 2029-07-19
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-449B | Queens 5/5A Site Drainage Rehabilitation | 1 | DEVELOP SCOPE | 2019-03-01 | 2019-07-23 | 2019-03-01 | 2019-07-23
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-449B | Queens 5/5A Site Drainage Rehabilitation | 2 | PRELIMINARY DESIGN | 2019-07-24 | 2020-01-19 | 2019-07-24 | 2020-01-19
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-449B | Queens 5/5A Site Drainage Rehabilitation | 3 | FINAL DESIGN | 2020-01-20 | 2020-07-17 | 2020-01-20 | 2020-07-17
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-449B | Queens 5/5A Site Drainage Rehabilitation | 4 | BID AWARD AND REGISTER CONTRCT | 2020-07-18 | 2021-05-13 | 2020-07-18 | 2021-05-13
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-449B | Queens 5/5A Site Drainage Rehabilitation | 5 | CONSTRUCTION TO 25% | 2021-05-14 | 2021-11-09 | 2021-05-14 | 2021-11-09
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-449B | Queens 5/5A Site Drainage Rehabilitation | 6 | CONSTRUCTION TO 50% | 2021-11-10 | 2022-05-08 | 2021-11-10 | 2022-05-08
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-449B | Queens 5/5A Site Drainage Rehabilitation | 7 | CONSTRUCTION TO 75% | 2022-05-09 | 2022-11-04 | 2022-05-09 | 2022-11-04
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-449B | Queens 5/5A Site Drainage Rehabilitation | 8 | SUBSTANTIAL COMPLETION | 2022-11-05 | 2023-04-03 | 2022-11-05 | 2023-04-03
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-449B | Queens 5/5A Site Drainage Rehabilitation | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-04-04 | 2024-05-07 | 2023-04-04 | 2024-05-07
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-464H | Queens Flushing Ave Enforcement Garage Roof Replacement | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-08-14 | 2017-07-01 | 2017-08-14
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-464H | Queens Flushing Ave Enforcement Garage Roof Replacement | 2 | PRELIMINARY DESIGN | 2017-08-15 | 2018-02-20 | 2017-08-15 | 2018-02-20
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-464H | Queens Flushing Ave Enforcement Garage Roof Replacement | 3 | FINAL DESIGN | 2018-02-21 | 2019-02-20 | 2018-02-21 | 2019-02-20
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-464H | Queens Flushing Ave Enforcement Garage Roof Replacement | 4 | BID AWARD AND REGISTER CONTRCT | 2019-02-21 | 2020-02-20 | 2019-02-21 | 2020-02-20
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-464H | Queens Flushing Ave Enforcement Garage Roof Replacement | 5 | CONSTRUCTION TO 25% | 2020-02-21 | 2021-02-19 | 2020-02-21 | 2021-02-19
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-464H | Queens Flushing Ave Enforcement Garage Roof Replacement | 6 | CONSTRUCTION TO 50% | 2021-02-20 | 2022-02-19 | 2021-02-20 | 2022-02-19
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-464H | Queens Flushing Ave Enforcement Garage Roof Replacement | 7 | CONSTRUCTION TO 75% | 2022-02-20 | 2023-02-19 | 2022-02-20 | 2023-02-19
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-464H | Queens Flushing Ave Enforcement Garage Roof Replacement | 8 | SUBSTANTIAL COMPLETION | 2023-02-20 | 2024-07-03 | 2023-02-20 | 2024-07-03
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-464H | Queens Flushing Ave Enforcement Garage Roof Replacement | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-07-04 | 2026-02-23 | 2024-07-04 | 2026-02-23
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S216-402A | NORTH SHORE MARINE TRANSFER STATION REHABILITATION | 1 | DEVELOP SCOPE | 2019-01-16 | 2019-03-01 | 2019-01-16 | 2019-03-01
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S216-402A | NORTH SHORE MARINE TRANSFER STATION REHABILITATION | 2 | PRELIMINARY DESIGN | 2019-03-02 | 2019-04-30 | 2019-03-02 | 2019-04-30
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S216-402A | NORTH SHORE MARINE TRANSFER STATION REHABILITATION | 3 | FINAL DESIGN | 2019-05-01 | 2019-06-29 | 2019-05-01 | 2019-06-29
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S216-402A | NORTH SHORE MARINE TRANSFER STATION REHABILITATION | 4 | BID AWARD AND REGISTER CONTRCT | 2019-06-30 | 2019-09-27 | 2019-06-30 | 2019-09-27
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S216-402A | NORTH SHORE MARINE TRANSFER STATION REHABILITATION | 5 | CONSTRUCTION TO 25% | 2019-09-28 | 2020-01-05 | 2019-09-28 | 2020-01-05
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S216-402A | NORTH SHORE MARINE TRANSFER STATION REHABILITATION | 6 | CONSTRUCTION TO 50% | 2020-01-06 | 2020-04-04 | 2020-01-06 | 2020-04-04
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S216-402A | NORTH SHORE MARINE TRANSFER STATION REHABILITATION | 7 | CONSTRUCTION TO 75% | 2020-04-05 | 2020-08-02 | 2020-04-05 | 2020-08-02
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S216-402A | NORTH SHORE MARINE TRANSFER STATION REHABILITATION | 8 | SUBSTANTIAL COMPLETION | 2020-08-03 | 2020-12-30 | 2020-08-03 | 2020-12-30
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S216-402A | NORTH SHORE MARINE TRANSFER STATION REHABILITATION | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-12-31 | 2021-04-29 | 2020-12-31 | 2021-04-29
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S216-402F | NORTH SHORE MTS FUELING SYSTEM | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-07-30 | 2020-06-01 | 2020-07-30
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S216-402F | NORTH SHORE MTS FUELING SYSTEM | 2 | PRELIMINARY DESIGN | 2020-07-31 | 2020-11-27 | 2020-07-31 | 2020-11-27
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S216-402F | NORTH SHORE MTS FUELING SYSTEM | 3 | FINAL DESIGN | 2020-11-28 | 2021-03-27 | 2020-11-28 | 2021-03-27
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S216-402F | NORTH SHORE MTS FUELING SYSTEM | 4 | BID AWARD AND REGISTER CONTRCT | 2021-03-28 | 2022-03-27 | 2021-03-28 | 2022-03-27
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S216-402F | NORTH SHORE MTS FUELING SYSTEM | 5 | CONSTRUCTION TO 25% | 2022-03-28 | 2022-10-13 | 2022-03-28 | 2022-10-13
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S216-402F | NORTH SHORE MTS FUELING SYSTEM | 6 | CONSTRUCTION TO 50% | 2022-10-14 | 2023-05-01 | 2022-10-14 | 2023-05-01
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S216-402F | NORTH SHORE MTS FUELING SYSTEM | 7 | CONSTRUCTION TO 75% | 2023-05-02 | 2023-11-17 | 2023-05-02 | 2023-11-17
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S216-402F | NORTH SHORE MTS FUELING SYSTEM | 8 | SUBSTANTIAL COMPLETION | 2023-11-18 | 2024-06-04 | 2023-11-18 | 2024-06-04
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | S216-402F | NORTH SHORE MTS FUELING SYSTEM | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-06-05 | 2025-06-04 | 2024-06-05 | 2025-06-04
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | SANDQ14EL | Hurricane Sandy Queens 14 Electrical Replacement | 1 | DEVELOP SCOPE | 2014-08-25 | 2014-10-08 | 2014-08-25 | 2014-10-08
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | SANDQ14EL | Hurricane Sandy Queens 14 Electrical Replacement | 2 | PRELIMINARY DESIGN | 2014-10-09 | 2015-10-08 | 2014-10-09 | 2015-10-08
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | SANDQ14EL | Hurricane Sandy Queens 14 Electrical Replacement | 3 | FINAL DESIGN | 2015-10-09 | 2016-10-07 | 2015-10-09 | 2016-10-07
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | SANDQ14EL | Hurricane Sandy Queens 14 Electrical Replacement | 4 | BID AWARD AND REGISTER CONTRCT | 2016-10-08 | 2017-10-07 | 2016-10-08 | 2017-10-07
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | SANDQ14EL | Hurricane Sandy Queens 14 Electrical Replacement | 5 | CONSTRUCTION TO 25% | 2017-10-08 | 2018-10-07 | 2017-10-08 | 2018-10-07
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | SANDQ14EL | Hurricane Sandy Queens 14 Electrical Replacement | 6 | CONSTRUCTION TO 50% | 2018-10-08 | 2019-10-07 | 2018-10-08 | 2019-10-07
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | SANDQ14EL | Hurricane Sandy Queens 14 Electrical Replacement | 7 | CONSTRUCTION TO 75% | 2019-10-08 | 2020-10-06 | 2019-10-08 | 2020-10-06
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | SANDQ14EL | Hurricane Sandy Queens 14 Electrical Replacement | 8 | SUBSTANTIAL COMPLETION | 2020-10-07 | 2022-06-28 | 2020-10-07 | 2022-06-28
20201123 | QUEENS | 827 | DEPARTMENT OF SANITATION | SANDQ14EL | Hurricane Sandy Queens 14 Electrical Replacement | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-06-29 | 2025-03-24 | 2022-06-29 | 2025-03-24
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HB1070NB | Protective Coating of N blvd Bridges over Flushing River | 1 | DEVELOP SCOPE | 2019-06-30 | 2020-06-28 | 0 | 0
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HB1070NB | Protective Coating of N blvd Bridges over Flushing River | 2 | DESIGN START | 2020-06-29 | 2024-06-27 | 2019-06-30 | 2020-06-28
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HB1070NB | Protective Coating of N blvd Bridges over Flushing River | 3 | CONSTRUCTION START | 2024-06-28 | 2026-06-27 | 2020-06-29 | 2024-06-27
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HB1070NB | Protective Coating of N blvd Bridges over Flushing River | 5 | CONSTRUCTION START | 2024-06-28 | 2026-06-27 | 2024-06-28 | 2026-06-27
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HB1070QN | Protective Coating of Various Bridges in Queens | 1 | DEVELOP SCOPE | 2019-06-30 | 2020-06-28 | 0 | 0
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HB1070QN | Protective Coating of Various Bridges in Queens | 2 | DESIGN START | 2020-06-29 | 2024-06-27 | 2019-06-30 | 2020-06-28
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HB1070QN | Protective Coating of Various Bridges in Queens | 3 | CONSTRUCTION START | 2024-06-28 | 2026-06-27 | 2020-06-29 | 2024-06-27
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HB1070QN | Protective Coating of Various Bridges in Queens | 5 | CONSTRUCTION START | 2024-06-28 | 2026-06-27 | 2024-06-28 | 2026-06-27
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HB21FAC | 21ST STREET YARD - OILERS TRAILERS | 2 | DESIGN START | 2016-06-29 | 2020-06-27 | 2015-06-30 | 2016-06-28
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HB21FAC | 21ST STREET YARD - OILERS TRAILERS | 3 | CONSTRUCTION START | 2020-06-28 | 2022-06-27 | 2016-06-29 | 2020-06-27
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HB21FAC | 21ST STREET YARD - OILERS TRAILERS | 5 | CONSTRUCTION START | 2020-06-28 | 2022-06-27 | 2020-06-28 | 2022-06-27
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBGATES | Barrier Gates | 1 | DEVELOP SCOPE | 2019-06-30 | 2020-06-28 | 0 | 0
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBGATES | Barrier Gates | 2 | DESIGN START | 2020-06-29 | 2024-06-27 | 2019-06-30 | 2020-06-28
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBGATES | Barrier Gates | 3 | CONSTRUCTION START | 2024-06-28 | 2026-06-27 | 2020-06-29 | 2024-06-27
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBGATES | Barrier Gates | 5 | CONSTRUCTION START | 2024-06-28 | 2026-06-27 | 2024-06-28 | 2026-06-27
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ1114 | HEMPSTEAD AVE BR/CIP 2231780 | 1 | DEVELOP SCOPE | 2004-07-01 | 2005-06-30 | 2016-06-28 | 2019-06-27
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ1114 | HEMPSTEAD AVE BR/CIP 2231780 | 2 | DESIGN START | 2005-07-01 | 2009-06-29 | 2019-06-28 | 2019-06-27
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ1114 | HEMPSTEAD AVE BR/CIP 2231780 | 3 | CONSTRUCTION START | 2009-06-30 | 2011-06-29 | 2019-06-28 | 2025-06-25
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ1115 | UNION TURNPIKE / CROSS ISLAND PKWY 2-23185-0 | 1 | DEVELOP SCOPE | 2005-07-01 | 2006-06-30 | 2013-06-28 | 2016-06-26
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ1115 | UNION TURNPIKE / CROSS ISLAND PKWY 2-23185-0 | 2 | DESIGN START | 2006-07-01 | 2010-06-29 | 2016-06-27 | 2016-06-26
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ1115 | UNION TURNPIKE / CROSS ISLAND PKWY 2-23185-0 | 3 | CONSTRUCTION START | 2010-06-30 | 2012-06-28 | 2016-06-27 | 2022-06-25
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ1137 | RECON ELLIOT AVE BRIDGE OVER QUEENS BLVD 2-24816-0 | 1 | DEVELOP SCOPE | 2006-07-01 | 2007-06-30 | 2020-06-28 | 2023-06-27
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ1137 | RECON ELLIOT AVE BRIDGE OVER QUEENS BLVD 2-24816-0 | 2 | DESIGN START | 2007-07-01 | 2011-06-29 | 2023-06-28 | 2023-06-27
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ1137 | RECON ELLIOT AVE BRIDGE OVER QUEENS BLVD 2-24816-0 | 3 | CONSTRUCTION START | 2011-06-30 | 2013-06-28 | 2023-06-28 | 2029-06-25
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ1203 | RECON ROOSEVELT AVE BR OVER VAN WYCK EXPWY QUEENS 2-240507 | 1 | DEVELOP SCOPE | 2004-07-01 | 2005-06-30 | 0 | 0
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ1203 | RECON ROOSEVELT AVE BR OVER VAN WYCK EXPWY QUEENS 2-240507 | 2 | DESIGN START | 2005-07-01 | 2009-06-29 | 2017-07-01 | 2018-06-30
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ1203 | RECON ROOSEVELT AVE BR OVER VAN WYCK EXPWY QUEENS 2-240507 | 3 | CONSTRUCTION START | 2009-06-30 | 2011-06-29 | 2018-07-01 | 2022-06-29
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ1203 | RECON ROOSEVELT AVE BR OVER VAN WYCK EXPWY QUEENS 2-240507 | 5 | CONSTRUCTION START | 2009-06-30 | 2011-06-29 | 2015-08-10 | 2021-12-01
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ231710 | Merrick Blvd over BLP NB BIN 2231710 | 1 | DEVELOP SCOPE | 2019-06-30 | 2020-06-28 | 0 | 0
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ231710 | Merrick Blvd over BLP NB BIN 2231710 | 2 | DESIGN START | 2020-06-29 | 2024-06-27 | 2019-06-30 | 2020-06-28
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ231710 | Merrick Blvd over BLP NB BIN 2231710 | 3 | CONSTRUCTION START | 2024-06-28 | 2026-06-27 | 2020-06-29 | 2024-06-27
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ231710 | Merrick Blvd over BLP NB BIN 2231710 | 5 | CONSTRUCTION START | 2024-06-28 | 2026-06-27 | 2024-06-28 | 2026-06-27
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ231720 | Merrick Blvd over BLP SB BIN 2231720 | 1 | DEVELOP SCOPE | 2019-06-30 | 2020-06-28 | 0 | 0
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ231720 | Merrick Blvd over BLP SB BIN 2231720 | 2 | DESIGN START | 2020-06-29 | 2024-06-27 | 2019-06-30 | 2020-06-28
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ231720 | Merrick Blvd over BLP SB BIN 2231720 | 3 | CONSTRUCTION START | 2024-06-28 | 2026-06-27 | 2020-06-29 | 2024-06-27
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ231720 | Merrick Blvd over BLP SB BIN 2231720 | 5 | CONSTRUCTION START | 2024-06-28 | 2026-06-27 | 2024-06-28 | 2026-06-27
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ49AV | 49TH AVE OVER LIRR, AMT, CON NE (BIN2247290) | 1 | DEVELOP SCOPE | 2015-07-01 | 2016-06-29 | 0 | 0
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ49AV | 49TH AVE OVER LIRR, AMT, CON NE (BIN2247290) | 2 | DESIGN START | 2016-06-30 | 2020-06-28 | 2015-07-01 | 2015-12-31
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ49AV | 49TH AVE OVER LIRR, AMT, CON NE (BIN2247290) | 3 | CONSTRUCTION START | 2020-06-29 | 2022-06-28 | 2017-08-16 | 2021-10-01
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ49AV | 49TH AVE OVER LIRR, AMT, CON NE (BIN2247290) | 5 | CONSTRUCTION START | 2020-06-29 | 2022-06-28 | 2021-08-17 | 2024-04-30
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ8019 | WOODHAVEN BLVD OVER ATLANTIC AVE | 1 | DEVELOP SCOPE | 2016-06-30 | 2017-06-29 | 0 | 0
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ8019 | WOODHAVEN BLVD OVER ATLANTIC AVE | 2 | DESIGN START | 2017-06-30 | 2021-06-28 | 2018-05-02 | 2020-07-01
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ8019 | WOODHAVEN BLVD OVER ATLANTIC AVE | 3 | CONSTRUCTION START | 2021-06-29 | 2023-06-28 | 2021-06-26 | 2024-08-24
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ8019 | WOODHAVEN BLVD OVER ATLANTIC AVE | 5 | CONSTRUCTION START | 2021-06-29 | 2023-06-28 | 2025-08-22 | 2027-10-21
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA23081 | ASTORIA BLVD EB/ 278I( BQE WEST LEG) BIN# 2230810 | 1 | DEVELOP SCOPE | 2019-06-30 | 2019-09-27 | 2017-07-01 | 2017-09-06
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA23081 | ASTORIA BLVD EB/ 278I( BQE WEST LEG) BIN# 2230810 | 2 | PRELIMINARY DESIGN | 2019-09-28 | 2020-01-25 | 2019-09-28 | 2022-08-17
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA23081 | ASTORIA BLVD EB/ 278I( BQE WEST LEG) BIN# 2230810 | 3 | FINAL DESIGN | 2020-01-26 | 2020-07-23 | 2022-08-18 | 2023-02-13
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA23081 | ASTORIA BLVD EB/ 278I( BQE WEST LEG) BIN# 2230810 | 4 | BID AWARD AND REGISTER CONTRCT | 2020-07-24 | 2020-10-21 | 2023-02-14 | 2023-05-14
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA23081 | ASTORIA BLVD EB/ 278I( BQE WEST LEG) BIN# 2230810 | 5 | CONSTRUCTION TO 25% | 2020-10-22 | 2021-02-18 | 2023-05-15 | 2023-09-11
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA23081 | ASTORIA BLVD EB/ 278I( BQE WEST LEG) BIN# 2230810 | 6 | CONSTRUCTION TO 50% | 2021-02-19 | 2021-06-18 | 2023-09-12 | 2024-01-09
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA23081 | ASTORIA BLVD EB/ 278I( BQE WEST LEG) BIN# 2230810 | 7 | CONSTRUCTION TO 75% | 2021-06-19 | 2021-10-16 | 2024-01-10 | 2024-05-08
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA23081 | ASTORIA BLVD EB/ 278I( BQE WEST LEG) BIN# 2230810 | 8 | ORIGINAL EQUIP & FURNISHING | 2021-10-17 | 2022-01-14 | 2024-05-09 | 2024-08-06
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA23081 | ASTORIA BLVD EB/ 278I( BQE WEST LEG) BIN# 2230810 | 9 | SUBSTANTIAL COMPLETION | 2022-01-15 | 2022-03-15 | 2024-08-07 | 2024-10-05
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA23081 | ASTORIA BLVD EB/ 278I( BQE WEST LEG) BIN# 2230810 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-16 | 2022-04-14 | 2024-10-06 | 2024-11-04
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA23176 | BCIP OVER DUTCH BROADWAY-115 AVE BIN 2231760 | 1 | DEVELOP SCOPE | 2021-06-30 | 2022-06-29 | 0 | 0
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA23176 | BCIP OVER DUTCH BROADWAY-115 AVE BIN 2231760 | 2 | DESIGN START | 2022-06-30 | 2026-06-28 | 2016-05-25 | 2016-10-03
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA23176 | BCIP OVER DUTCH BROADWAY-115 AVE BIN 2231760 | 3 | CONSTRUCTION START | 2026-06-29 | 2028-06-27 | 2018-09-24 | 2021-06-03
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA23176 | BCIP OVER DUTCH BROADWAY-115 AVE BIN 2231760 | 5 | CONSTRUCTION START | 2026-06-29 | 2028-06-27 | 2022-05-27 | 2025-08-25
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA24750 | METROPOLITAN AVE OVER CSX TRANSPORT | 1 | DEVELOP SCOPE | 2021-06-30 | 2022-06-29 | 0 | 0
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA24750 | METROPOLITAN AVE OVER CSX TRANSPORT | 2 | DESIGN START | 2022-06-30 | 2026-06-28 | 2016-04-13 | 2016-09-28
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA24750 | METROPOLITAN AVE OVER CSX TRANSPORT | 3 | CONSTRUCTION START | 2026-06-29 | 2028-06-27 | 2018-04-16 | 2022-05-16
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA24750 | METROPOLITAN AVE OVER CSX TRANSPORT | 5 | CONSTRUCTION START | 2026-06-29 | 2028-06-27 | 2023-04-27 | 2027-07-27
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA24815 | WOODHAVEN BLVD/ QUEENS BLVD BIN# 2248159 | 1 | DEVELOP SCOPE | 2021-06-30 | 2021-09-27 | 2019-06-30 | 2019-09-27
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA24815 | WOODHAVEN BLVD/ QUEENS BLVD BIN# 2248159 | 2 | PRELIMINARY DESIGN | 2021-09-28 | 2022-01-25 | 2019-09-28 | 2020-01-25
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA24815 | WOODHAVEN BLVD/ QUEENS BLVD BIN# 2248159 | 3 | FINAL DESIGN | 2022-01-26 | 2022-07-24 | 2020-01-26 | 2020-07-23
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA24815 | WOODHAVEN BLVD/ QUEENS BLVD BIN# 2248159 | 4 | BID AWARD AND REGISTER CONTRCT | 2022-07-25 | 2022-10-22 | 2020-07-24 | 2020-10-21
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA24815 | WOODHAVEN BLVD/ QUEENS BLVD BIN# 2248159 | 5 | CONSTRUCTION TO 25% | 2022-10-23 | 2023-02-19 | 2020-10-22 | 2021-02-18
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA24815 | WOODHAVEN BLVD/ QUEENS BLVD BIN# 2248159 | 6 | CONSTRUCTION TO 50% | 2023-02-20 | 2023-06-19 | 2021-02-19 | 2021-06-18
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA24815 | WOODHAVEN BLVD/ QUEENS BLVD BIN# 2248159 | 7 | CONSTRUCTION TO 75% | 2023-06-20 | 2023-10-17 | 2021-06-19 | 2021-10-16
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA24815 | WOODHAVEN BLVD/ QUEENS BLVD BIN# 2248159 | 8 | ORIGINAL EQUIP & FURNISHING | 2023-10-18 | 2024-01-15 | 2021-10-17 | 2022-01-14
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA24815 | WOODHAVEN BLVD/ QUEENS BLVD BIN# 2248159 | 9 | SUBSTANTIAL COMPLETION | 2024-01-16 | 2024-03-15 | 2022-01-15 | 2022-03-15
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA24815 | WOODHAVEN BLVD/ QUEENS BLVD BIN# 2248159 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-03-16 | 2024-04-14 | 2022-03-16 | 2022-04-14
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA26614 | HEMPSTEAD AVE OVER BCIP RAMP NB BIN 2266149 | 1 | DEVELOP SCOPE | 2023-06-30 | 2024-06-28 | 0 | 0
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA26614 | HEMPSTEAD AVE OVER BCIP RAMP NB BIN 2266149 | 2 | DESIGN START | 2024-06-29 | 2028-06-27 | 2018-07-01 | 2019-06-30
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA26614 | HEMPSTEAD AVE OVER BCIP RAMP NB BIN 2266149 | 3 | CONSTRUCTION START | 2028-06-28 | 2030-06-27 | 2019-07-01 | 2023-06-29
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA26614 | HEMPSTEAD AVE OVER BCIP RAMP NB BIN 2266149 | 5 | CONSTRUCTION START | 2028-06-28 | 2030-06-27 | 2023-06-30 | 2024-06-27
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQC064 | 678I SB TO BCIP EB/ACCESS RD FROM 678I 2-26616-0 | 1 | DEVELOP SCOPE | 2006-07-01 | 2007-06-30 | 2015-06-28 | 2018-06-26
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQC064 | 678I SB TO BCIP EB/ACCESS RD FROM 678I 2-26616-0 | 2 | DESIGN START | 2007-07-01 | 2011-06-29 | 2018-06-27 | 2018-06-26
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQC064 | 678I SB TO BCIP EB/ACCESS RD FROM 678I 2-26616-0 | 3 | CONSTRUCTION START | 2011-06-30 | 2013-06-28 | 2018-06-27 | 2024-06-24
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQENB012 | Emergency Fender System Northern Blvd WB/EB | 1 | DEVELOP SCOPE | 2019-06-30 | 2020-06-28 | 0 | 0
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQENB012 | Emergency Fender System Northern Blvd WB/EB | 2 | DESIGN START | 2020-06-29 | 2024-06-27 | 2019-06-30 | 2020-06-28
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQENB012 | Emergency Fender System Northern Blvd WB/EB | 3 | CONSTRUCTION START | 2024-06-28 | 2026-06-27 | 2020-06-29 | 2024-06-27
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQENB012 | Emergency Fender System Northern Blvd WB/EB | 5 | CONSTRUCTION START | 2024-06-28 | 2026-06-27 | 2024-06-28 | 2026-06-27
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWCOINFAC | METER PROCESSING FACILITY REHABILITATION | 1 | DEVELOP SCOPE | 2009-06-30 | 2009-09-27 | 2019-06-30 | 2019-09-27
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWCOINFAC | METER PROCESSING FACILITY REHABILITATION | 2 | PRELIMINARY DESIGN | 2009-09-28 | 2010-01-25 | 2019-09-28 | 2027-06-30
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWCOINFAC | METER PROCESSING FACILITY REHABILITATION | 3 | FINAL DESIGN | 2010-01-26 | 2010-07-24 | 2027-07-01 | 2027-12-27
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWCOINFAC | METER PROCESSING FACILITY REHABILITATION | 4 | BID AWARD AND REGISTER CONTRCT | 2010-07-25 | 2010-10-22 | 2027-12-28 | 2028-03-26
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWCOINFAC | METER PROCESSING FACILITY REHABILITATION | 5 | CONSTRUCTION TO 25% | 2010-10-23 | 2011-02-19 | 2028-03-27 | 2028-07-24
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWCOINFAC | METER PROCESSING FACILITY REHABILITATION | 6 | CONSTRUCTION TO 50% | 2011-02-20 | 2011-06-19 | 2028-07-25 | 2028-11-21
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWCOINFAC | METER PROCESSING FACILITY REHABILITATION | 7 | CONSTRUCTION TO 75% | 2011-06-20 | 2011-10-17 | 2028-11-22 | 2029-03-21
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWCOINFAC | METER PROCESSING FACILITY REHABILITATION | 8 | ORIGINAL EQUIP & FURNISHING | 2011-10-18 | 2012-01-15 | 2029-03-22 | 2029-06-19
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWCOINFAC | METER PROCESSING FACILITY REHABILITATION | 9 | SUBSTANTIAL COMPLETION | 2012-01-16 | 2012-03-15 | 2029-06-20 | 2029-08-18
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWCOINFAC | METER PROCESSING FACILITY REHABILITATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-03-16 | 2012-04-14 | 2029-08-19 | 2033-10-06
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD103100 | RECON OF MYRTLE AVE / UNION TURNPIKE ENTRANCE TO FOREST PK | 1 | DEVELOP SCOPE | 2017-06-30 | 2017-09-27 | 2020-06-30 | 2020-09-27
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD103100 | RECON OF MYRTLE AVE / UNION TURNPIKE ENTRANCE TO FOREST PK | 2 | PRELIMINARY DESIGN | 2017-09-28 | 2018-01-25 | 2020-09-28 | 2021-01-25
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD103100 | RECON OF MYRTLE AVE / UNION TURNPIKE ENTRANCE TO FOREST PK | 3 | FINAL DESIGN | 2018-01-26 | 2018-07-24 | 2021-01-26 | 2021-07-24
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD103100 | RECON OF MYRTLE AVE / UNION TURNPIKE ENTRANCE TO FOREST PK | 4 | BID AWARD AND REGISTER CONTRCT | 2018-07-25 | 2018-10-22 | 2021-07-25 | 2021-10-22
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD103100 | RECON OF MYRTLE AVE / UNION TURNPIKE ENTRANCE TO FOREST PK | 5 | CONSTRUCTION TO 25% | 2018-10-23 | 2019-02-19 | 2021-10-23 | 2022-02-19
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD103100 | RECON OF MYRTLE AVE / UNION TURNPIKE ENTRANCE TO FOREST PK | 6 | CONSTRUCTION TO 50% | 2019-02-20 | 2019-06-19 | 2022-02-20 | 2022-06-19
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD103100 | RECON OF MYRTLE AVE / UNION TURNPIKE ENTRANCE TO FOREST PK | 7 | CONSTRUCTION TO 75% | 2019-06-20 | 2019-10-17 | 2022-06-20 | 2022-10-17
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD103100 | RECON OF MYRTLE AVE / UNION TURNPIKE ENTRANCE TO FOREST PK | 8 | ORIGINAL EQUIP & FURNISHING | 2019-10-18 | 2020-01-15 | 2022-10-18 | 2023-01-15
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD103100 | RECON OF MYRTLE AVE / UNION TURNPIKE ENTRANCE TO FOREST PK | 9 | SUBSTANTIAL COMPLETION | 2020-01-16 | 2020-03-15 | 2023-01-16 | 2023-03-16
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD103100 | RECON OF MYRTLE AVE / UNION TURNPIKE ENTRANCE TO FOREST PK | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-03-16 | 2020-04-14 | 2023-03-17 | 2025-04-15
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10312 | Safety Improvements at St. Margaret's School | 1 | DEVELOP SCOPE | 2015-06-01 | 2015-08-29 | 2020-06-01 | 2020-08-29
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10312 | Safety Improvements at St. Margaret's School | 2 | PRELIMINARY DESIGN | 2015-08-30 | 2015-12-27 | 2020-08-30 | 2020-12-27
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10312 | Safety Improvements at St. Margaret's School | 3 | FINAL DESIGN | 2015-12-28 | 2016-06-24 | 2020-12-28 | 2021-06-25
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10312 | Safety Improvements at St. Margaret's School | 4 | BID AWARD AND REGISTER CONTRCT | 2016-06-25 | 2016-09-22 | 2021-06-26 | 2021-09-23
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10312 | Safety Improvements at St. Margaret's School | 5 | CONSTRUCTION TO 25% | 2016-09-23 | 2017-01-20 | 2021-09-24 | 2022-01-21
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10312 | Safety Improvements at St. Margaret's School | 6 | CONSTRUCTION TO 50% | 2017-01-21 | 2017-05-20 | 2022-01-22 | 2022-05-21
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10312 | Safety Improvements at St. Margaret's School | 7 | CONSTRUCTION TO 75% | 2017-05-21 | 2017-09-17 | 2022-05-22 | 2022-09-18
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10312 | Safety Improvements at St. Margaret's School | 8 | ORIGINAL EQUIP & FURNISHING | 2017-09-18 | 2017-12-16 | 2022-09-19 | 2022-12-17
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10312 | Safety Improvements at St. Margaret's School | 9 | SUBSTANTIAL COMPLETION | 2017-12-17 | 2018-02-14 | 2022-12-18 | 2023-02-15
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10312 | Safety Improvements at St. Margaret's School | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-02-15 | 2018-03-16 | 2023-02-16 | 2025-06-30
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10323 | Upgrades within the Bayside BID | 1 | DEVELOP SCOPE | 2019-06-30 | 2019-09-27 | 2021-06-30 | 2021-09-27
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10323 | Upgrades within the Bayside BID | 2 | PRELIMINARY DESIGN | 2019-09-28 | 2020-01-25 | 2021-09-28 | 2022-01-25
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10323 | Upgrades within the Bayside BID | 3 | FINAL DESIGN | 2020-01-26 | 2020-07-23 | 2022-01-26 | 2022-07-24
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10323 | Upgrades within the Bayside BID | 4 | BID AWARD AND REGISTER CONTRCT | 2020-07-24 | 2020-10-21 | 2022-07-25 | 2022-10-22
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10323 | Upgrades within the Bayside BID | 5 | CONSTRUCTION TO 25% | 2020-10-22 | 2021-02-18 | 2022-10-23 | 2023-02-19
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10323 | Upgrades within the Bayside BID | 6 | CONSTRUCTION TO 50% | 2021-02-19 | 2021-06-18 | 2023-02-20 | 2023-06-19
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10323 | Upgrades within the Bayside BID | 7 | CONSTRUCTION TO 75% | 2021-06-19 | 2021-10-16 | 2023-06-20 | 2023-10-17
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10323 | Upgrades within the Bayside BID | 8 | ORIGINAL EQUIP & FURNISHING | 2021-10-17 | 2022-01-14 | 2023-10-18 | 2024-01-15
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10323 | Upgrades within the Bayside BID | 9 | SUBSTANTIAL COMPLETION | 2022-01-15 | 2022-03-15 | 2024-01-16 | 2024-03-15
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10323 | Upgrades within the Bayside BID | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-16 | 2022-04-14 | 2024-03-16 | 2024-04-14
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10324 | Parsons Blvd & 84th Ave & Hoover Ave Ped Safety Improvements | 1 | DEVELOP SCOPE | 2019-06-30 | 2019-09-27 | 2019-06-30 | 2019-09-29
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10324 | Parsons Blvd & 84th Ave & Hoover Ave Ped Safety Improvements | 2 | PRELIMINARY DESIGN | 2019-09-28 | 2020-01-25 | 2019-09-30 | 2020-01-27
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10324 | Parsons Blvd & 84th Ave & Hoover Ave Ped Safety Improvements | 3 | FINAL DESIGN | 2020-01-26 | 2020-07-23 | 2020-01-28 | 2020-07-25
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10324 | Parsons Blvd & 84th Ave & Hoover Ave Ped Safety Improvements | 4 | BID AWARD AND REGISTER CONTRCT | 2020-07-24 | 2020-10-21 | 2020-07-26 | 2020-10-23
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10324 | Parsons Blvd & 84th Ave & Hoover Ave Ped Safety Improvements | 5 | CONSTRUCTION TO 25% | 2020-10-22 | 2021-02-18 | 2020-10-24 | 2021-02-20
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10324 | Parsons Blvd & 84th Ave & Hoover Ave Ped Safety Improvements | 6 | CONSTRUCTION TO 50% | 2021-02-19 | 2021-06-18 | 2021-02-21 | 2021-06-20
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10324 | Parsons Blvd & 84th Ave & Hoover Ave Ped Safety Improvements | 7 | CONSTRUCTION TO 75% | 2021-06-19 | 2021-10-16 | 2021-06-21 | 2021-10-18
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10324 | Parsons Blvd & 84th Ave & Hoover Ave Ped Safety Improvements | 8 | ORIGINAL EQUIP & FURNISHING | 2021-10-17 | 2022-01-14 | 2021-10-19 | 2022-01-16
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10324 | Parsons Blvd & 84th Ave & Hoover Ave Ped Safety Improvements | 9 | SUBSTANTIAL COMPLETION | 2022-01-15 | 2022-03-15 | 2022-01-17 | 2022-03-17
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10324 | Parsons Blvd & 84th Ave & Hoover Ave Ped Safety Improvements | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-16 | 2022-04-14 | 2022-03-18 | 2028-04-16
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10326 | Long Island City Bikeway Improvements | 1 | DEVELOP SCOPE | 2019-06-30 | 2019-09-27 | 2020-06-30 | 2020-09-27
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10326 | Long Island City Bikeway Improvements | 2 | PRELIMINARY DESIGN | 2019-09-28 | 2020-01-25 | 2020-09-28 | 2021-01-25
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10326 | Long Island City Bikeway Improvements | 3 | FINAL DESIGN | 2020-01-26 | 2020-07-23 | 2021-01-26 | 2021-07-24
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10326 | Long Island City Bikeway Improvements | 4 | BID AWARD AND REGISTER CONTRCT | 2020-07-24 | 2020-10-21 | 2021-07-25 | 2021-10-22
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10326 | Long Island City Bikeway Improvements | 5 | CONSTRUCTION TO 25% | 2020-10-22 | 2021-02-18 | 2021-10-23 | 2022-02-19
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10326 | Long Island City Bikeway Improvements | 6 | CONSTRUCTION TO 50% | 2021-02-19 | 2021-06-18 | 2022-02-20 | 2022-06-19
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10326 | Long Island City Bikeway Improvements | 7 | CONSTRUCTION TO 75% | 2021-06-19 | 2021-10-16 | 2022-06-20 | 2022-10-17
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10326 | Long Island City Bikeway Improvements | 8 | ORIGINAL EQUIP & FURNISHING | 2021-10-17 | 2022-01-14 | 2022-10-18 | 2023-01-15
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10326 | Long Island City Bikeway Improvements | 9 | SUBSTANTIAL COMPLETION | 2022-01-15 | 2022-03-15 | 2023-01-16 | 2023-03-16
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10326 | Long Island City Bikeway Improvements | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-16 | 2022-04-14 | 2023-03-17 | 2025-04-15
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10327 | Dutch Kills Pedestrian Safety Project | 1 | DEVELOP SCOPE | 2021-06-30 | 2021-09-27 | 2021-06-30 | 2021-09-27
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10327 | Dutch Kills Pedestrian Safety Project | 2 | PRELIMINARY DESIGN | 2021-09-28 | 2022-01-25 | 2021-09-28 | 2022-01-25
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10327 | Dutch Kills Pedestrian Safety Project | 3 | FINAL DESIGN | 2022-01-26 | 2022-07-24 | 2022-01-26 | 2022-07-24
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10327 | Dutch Kills Pedestrian Safety Project | 4 | BID AWARD AND REGISTER CONTRCT | 2022-07-25 | 2022-10-22 | 2022-07-25 | 2022-10-22
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10327 | Dutch Kills Pedestrian Safety Project | 5 | CONSTRUCTION TO 25% | 2022-10-23 | 2023-02-19 | 2022-10-23 | 2023-02-19
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10327 | Dutch Kills Pedestrian Safety Project | 6 | CONSTRUCTION TO 50% | 2023-02-20 | 2023-06-19 | 2023-02-20 | 2023-06-19
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10327 | Dutch Kills Pedestrian Safety Project | 7 | CONSTRUCTION TO 75% | 2023-06-20 | 2023-10-17 | 2023-06-20 | 2023-10-17
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10327 | Dutch Kills Pedestrian Safety Project | 8 | ORIGINAL EQUIP & FURNISHING | 2023-10-18 | 2024-01-15 | 2023-10-18 | 2024-01-15
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10327 | Dutch Kills Pedestrian Safety Project | 9 | SUBSTANTIAL COMPLETION | 2024-01-16 | 2024-03-15 | 2024-01-16 | 2024-03-15
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10327 | Dutch Kills Pedestrian Safety Project | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-03-16 | 2024-04-14 | 2024-03-16 | 2025-06-30
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10328 | A Safer Intersection at 71st Avenue and Austin Street | 1 | DEVELOP SCOPE | 2019-06-30 | 2019-09-27 | 2021-06-30 | 2021-09-27
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10328 | A Safer Intersection at 71st Avenue and Austin Street | 2 | PRELIMINARY DESIGN | 2019-09-28 | 2020-01-25 | 2021-09-28 | 2022-01-25
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10328 | A Safer Intersection at 71st Avenue and Austin Street | 3 | FINAL DESIGN | 2020-01-26 | 2020-07-23 | 2022-01-26 | 2022-07-24
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10328 | A Safer Intersection at 71st Avenue and Austin Street | 4 | BID AWARD AND REGISTER CONTRCT | 2020-07-24 | 2020-10-21 | 2022-07-25 | 2022-10-22
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10328 | A Safer Intersection at 71st Avenue and Austin Street | 5 | CONSTRUCTION TO 25% | 2020-10-22 | 2021-02-18 | 2022-10-23 | 2023-02-19
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10328 | A Safer Intersection at 71st Avenue and Austin Street | 6 | CONSTRUCTION TO 50% | 2021-02-19 | 2021-06-18 | 2023-02-20 | 2023-06-19
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10328 | A Safer Intersection at 71st Avenue and Austin Street | 7 | CONSTRUCTION TO 75% | 2021-06-19 | 2021-10-16 | 2023-06-20 | 2023-10-17
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10328 | A Safer Intersection at 71st Avenue and Austin Street | 8 | ORIGINAL EQUIP & FURNISHING | 2021-10-17 | 2022-01-14 | 2023-10-18 | 2024-01-15
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10328 | A Safer Intersection at 71st Avenue and Austin Street | 9 | SUBSTANTIAL COMPLETION | 2022-01-15 | 2022-03-15 | 2024-01-16 | 2024-03-15
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10328 | A Safer Intersection at 71st Avenue and Austin Street | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-16 | 2022-04-14 | 2024-03-16 | 2025-04-14
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10330 | Median and Street Reconstruction in Broad Channel | 1 | DEVELOP SCOPE | 2019-06-30 | 2019-09-27 | 2020-06-30 | 2020-09-27
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10330 | Median and Street Reconstruction in Broad Channel | 2 | PRELIMINARY DESIGN | 2019-09-28 | 2020-01-25 | 2020-09-28 | 2021-01-25
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10330 | Median and Street Reconstruction in Broad Channel | 3 | FINAL DESIGN | 2020-01-26 | 2020-07-23 | 2021-01-26 | 2021-07-24
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10330 | Median and Street Reconstruction in Broad Channel | 4 | BID AWARD AND REGISTER CONTRCT | 2020-07-24 | 2020-10-21 | 2021-07-25 | 2021-10-22
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10330 | Median and Street Reconstruction in Broad Channel | 5 | CONSTRUCTION TO 25% | 2020-10-22 | 2021-02-18 | 2021-10-23 | 2022-02-19
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10330 | Median and Street Reconstruction in Broad Channel | 6 | CONSTRUCTION TO 50% | 2021-02-19 | 2021-06-18 | 2022-02-20 | 2022-06-19
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10330 | Median and Street Reconstruction in Broad Channel | 7 | CONSTRUCTION TO 75% | 2021-06-19 | 2021-10-16 | 2022-06-20 | 2022-10-17
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10330 | Median and Street Reconstruction in Broad Channel | 8 | ORIGINAL EQUIP & FURNISHING | 2021-10-17 | 2022-01-14 | 2022-10-18 | 2023-01-15
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10330 | Median and Street Reconstruction in Broad Channel | 9 | SUBSTANTIAL COMPLETION | 2022-01-15 | 2022-03-15 | 2023-01-16 | 2023-03-16
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10330 | Median and Street Reconstruction in Broad Channel | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-16 | 2022-04-14 | 2023-03-17 | 2025-04-15
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10332 | Reconstruct Curbs along median of Rockaway Freeway | 1 | DEVELOP SCOPE | 2022-06-30 | 2022-09-27 | 2022-06-30 | 2022-09-27
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10332 | Reconstruct Curbs along median of Rockaway Freeway | 2 | PRELIMINARY DESIGN | 2022-09-28 | 2023-01-25 | 2022-09-28 | 2023-01-25
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10332 | Reconstruct Curbs along median of Rockaway Freeway | 3 | FINAL DESIGN | 2023-01-26 | 2023-07-24 | 2023-01-26 | 2023-07-24
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10332 | Reconstruct Curbs along median of Rockaway Freeway | 4 | BID AWARD AND REGISTER CONTRCT | 2023-07-25 | 2023-10-22 | 2023-07-25 | 2023-10-22
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10332 | Reconstruct Curbs along median of Rockaway Freeway | 5 | CONSTRUCTION TO 25% | 2023-10-23 | 2024-02-19 | 2023-10-23 | 2024-02-19
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10332 | Reconstruct Curbs along median of Rockaway Freeway | 6 | CONSTRUCTION TO 50% | 2024-02-20 | 2024-06-18 | 2024-02-20 | 2024-06-18
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10332 | Reconstruct Curbs along median of Rockaway Freeway | 7 | CONSTRUCTION TO 75% | 2024-06-19 | 2024-10-16 | 2024-06-19 | 2024-10-16
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10332 | Reconstruct Curbs along median of Rockaway Freeway | 8 | ORIGINAL EQUIP & FURNISHING | 2024-10-17 | 2025-01-14 | 2024-10-17 | 2025-01-14
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10332 | Reconstruct Curbs along median of Rockaway Freeway | 9 | SUBSTANTIAL COMPLETION | 2025-01-15 | 2025-03-15 | 2025-01-15 | 2025-03-15
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10332 | Reconstruct Curbs along median of Rockaway Freeway | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-03-16 | 2025-04-14 | 2025-03-16 | 2025-04-14
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWDMM011 | Union Street Beautification | 1 | DEVELOP SCOPE | 2012-06-30 | 2012-09-27 | 2012-08-08 | 2012-11-21
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWDMM011 | Union Street Beautification | 2 | PRELIMINARY DESIGN | 2012-09-28 | 2013-01-25 | 2013-05-24 | 2014-02-24
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWDMM011 | Union Street Beautification | 3 | FINAL DESIGN | 2013-01-26 | 2013-07-24 | 2014-02-25 | 2014-08-23
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWDMM011 | Union Street Beautification | 4 | BID AWARD AND REGISTER CONTRCT | 2013-07-25 | 2013-10-22 | 2015-06-24 | 2015-07-02
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWDMM011 | Union Street Beautification | 5 | CONSTRUCTION TO 25% | 2013-10-23 | 2014-02-19 | 2015-07-03 | 2015-10-30
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWDMM011 | Union Street Beautification | 6 | CONSTRUCTION TO 50% | 2014-02-20 | 2014-06-19 | 2015-10-30 | 2015-12-30
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWDMM011 | Union Street Beautification | 7 | CONSTRUCTION TO 75% | 2014-06-20 | 2014-10-17 | 2015-12-31 | 2016-04-28
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWDMM011 | Union Street Beautification | 8 | ORIGINAL EQUIP & FURNISHING | 2014-10-18 | 2015-01-15 | 2016-04-29 | 2016-07-27
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWDMM011 | Union Street Beautification | 9 | SUBSTANTIAL COMPLETION | 2015-01-16 | 2015-03-16 | 2016-07-28 | 2016-09-25
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWDMM011 | Union Street Beautification | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-17 | 2015-04-15 | 2016-09-26 | 2025-06-30
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWHARPADM | Harper Street Administration Building Reconstruction | 1 | DEVELOP SCOPE | 2019-06-30 | 2019-09-27 | 2021-06-30 | 2021-09-27
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWHARPADM | Harper Street Administration Building Reconstruction | 2 | PRELIMINARY DESIGN | 2019-09-28 | 2020-01-25 | 2021-09-28 | 2022-01-25
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWHARPADM | Harper Street Administration Building Reconstruction | 3 | FINAL DESIGN | 2020-01-26 | 2020-07-23 | 2022-01-26 | 2022-07-24
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWHARPADM | Harper Street Administration Building Reconstruction | 4 | BID AWARD AND REGISTER CONTRCT | 2020-07-24 | 2020-10-21 | 2022-07-25 | 2022-10-22
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWHARPADM | Harper Street Administration Building Reconstruction | 5 | CONSTRUCTION TO 25% | 2020-10-22 | 2021-02-18 | 2022-10-23 | 2023-02-19
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWHARPADM | Harper Street Administration Building Reconstruction | 6 | CONSTRUCTION TO 50% | 2021-02-19 | 2021-06-18 | 2023-02-20 | 2023-06-19
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWHARPADM | Harper Street Administration Building Reconstruction | 7 | CONSTRUCTION TO 75% | 2021-06-19 | 2021-10-16 | 2023-06-20 | 2023-10-17
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWHARPADM | Harper Street Administration Building Reconstruction | 8 | ORIGINAL EQUIP & FURNISHING | 2021-10-17 | 2022-01-14 | 2023-10-18 | 2024-01-15
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWHARPADM | Harper Street Administration Building Reconstruction | 9 | SUBSTANTIAL COMPLETION | 2022-01-15 | 2022-03-15 | 2024-01-16 | 2024-03-15
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWHARPADM | Harper Street Administration Building Reconstruction | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-16 | 2022-04-14 | 2024-03-16 | 2024-04-14
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWPEDSF4B | Multi-Site Pedestrian Safety - Phase 4B -- Hoyt Avenue | 1 | DEVELOP SCOPE | 2019-06-30 | 2019-09-27 | 2019-06-30 | 2019-09-27
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWPEDSF4B | Multi-Site Pedestrian Safety - Phase 4B -- Hoyt Avenue | 2 | PRELIMINARY DESIGN | 2019-09-28 | 2020-01-25 | 2019-09-28 | 2020-01-25
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWPEDSF4B | Multi-Site Pedestrian Safety - Phase 4B -- Hoyt Avenue | 3 | FINAL DESIGN | 2020-01-26 | 2020-07-23 | 2020-01-26 | 2020-07-23
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWPEDSF4B | Multi-Site Pedestrian Safety - Phase 4B -- Hoyt Avenue | 4 | BID AWARD AND REGISTER CONTRCT | 2020-07-24 | 2020-10-21 | 2020-07-24 | 2020-10-21
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWPEDSF4B | Multi-Site Pedestrian Safety - Phase 4B -- Hoyt Avenue | 5 | CONSTRUCTION TO 25% | 2020-10-22 | 2021-02-18 | 2020-10-22 | 2021-02-18
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWPEDSF4B | Multi-Site Pedestrian Safety - Phase 4B -- Hoyt Avenue | 6 | CONSTRUCTION TO 50% | 2021-02-19 | 2021-06-18 | 2021-02-19 | 2021-06-18
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWPEDSF4B | Multi-Site Pedestrian Safety - Phase 4B -- Hoyt Avenue | 7 | CONSTRUCTION TO 75% | 2021-06-19 | 2021-10-16 | 2021-06-19 | 2021-10-16
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWPEDSF4B | Multi-Site Pedestrian Safety - Phase 4B -- Hoyt Avenue | 8 | ORIGINAL EQUIP & FURNISHING | 2021-10-17 | 2022-01-14 | 2021-10-17 | 2022-01-14
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWPEDSF4B | Multi-Site Pedestrian Safety - Phase 4B -- Hoyt Avenue | 9 | SUBSTANTIAL COMPLETION | 2022-01-15 | 2022-03-15 | 2022-01-15 | 2022-03-15
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWPEDSF4B | Multi-Site Pedestrian Safety - Phase 4B -- Hoyt Avenue | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-16 | 2022-04-14 | 2022-03-16 | 2022-04-14
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ005-01 | Median Updates at Junction/82nd & Ditmars/78-82 | 1 | DEVELOP SCOPE | 2017-06-30 | 2017-09-27 | 2020-06-30 | 2020-09-27
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ005-01 | Median Updates at Junction/82nd & Ditmars/78-82 | 2 | PRELIMINARY DESIGN | 2017-09-28 | 2018-01-25 | 2020-09-28 | 2021-01-25
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ005-01 | Median Updates at Junction/82nd & Ditmars/78-82 | 3 | FINAL DESIGN | 2018-01-26 | 2018-07-24 | 2021-01-26 | 2021-07-24
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ005-01 | Median Updates at Junction/82nd & Ditmars/78-82 | 4 | BID AWARD AND REGISTER CONTRCT | 2018-07-25 | 2018-10-22 | 2021-07-25 | 2021-10-22
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ005-01 | Median Updates at Junction/82nd & Ditmars/78-82 | 5 | CONSTRUCTION TO 25% | 2018-10-23 | 2019-02-19 | 2021-10-23 | 2022-02-19
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ005-01 | Median Updates at Junction/82nd & Ditmars/78-82 | 6 | CONSTRUCTION TO 50% | 2019-02-20 | 2019-06-19 | 2022-02-20 | 2022-06-19
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ005-01 | Median Updates at Junction/82nd & Ditmars/78-82 | 7 | CONSTRUCTION TO 75% | 2019-06-20 | 2019-10-17 | 2022-06-20 | 2022-10-17
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ005-01 | Median Updates at Junction/82nd & Ditmars/78-82 | 8 | ORIGINAL EQUIP & FURNISHING | 2019-10-18 | 2020-01-15 | 2022-10-18 | 2023-01-15
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ005-01 | Median Updates at Junction/82nd & Ditmars/78-82 | 9 | SUBSTANTIAL COMPLETION | 2020-01-16 | 2020-03-15 | 2023-01-16 | 2023-03-16
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ005-01 | Median Updates at Junction/82nd & Ditmars/78-82 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-03-16 | 2020-04-14 | 2023-03-17 | 2023-04-15
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ100SBS | Woodhaven Blvd SBS | 1 | DEVELOP SCOPE | 2013-06-30 | 2013-09-27 | 2019-06-30 | 2019-09-27
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ100SBS | Woodhaven Blvd SBS | 2 | PRELIMINARY DESIGN | 2013-09-28 | 2014-01-25 | 2019-09-28 | 2020-01-25
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ100SBS | Woodhaven Blvd SBS | 3 | FINAL DESIGN | 2014-01-26 | 2014-07-24 | 2020-01-26 | 2020-07-23
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ100SBS | Woodhaven Blvd SBS | 4 | BID AWARD AND REGISTER CONTRCT | 2014-07-25 | 2014-10-22 | 2020-07-24 | 2020-10-21
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ100SBS | Woodhaven Blvd SBS | 5 | CONSTRUCTION TO 25% | 2014-10-23 | 2015-02-19 | 2020-10-22 | 2021-02-18
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ100SBS | Woodhaven Blvd SBS | 6 | CONSTRUCTION TO 50% | 2015-02-20 | 2015-06-19 | 2021-02-19 | 2021-06-18
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ100SBS | Woodhaven Blvd SBS | 7 | CONSTRUCTION TO 75% | 2015-06-20 | 2015-10-17 | 2021-06-19 | 2021-10-16
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ100SBS | Woodhaven Blvd SBS | 8 | ORIGINAL EQUIP & FURNISHING | 2015-10-18 | 2016-01-15 | 2021-10-17 | 2022-01-14
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ100SBS | Woodhaven Blvd SBS | 9 | SUBSTANTIAL COMPLETION | 2016-01-16 | 2016-03-15 | 2022-01-15 | 2022-03-15
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ100SBS | Woodhaven Blvd SBS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-16 | 2016-04-14 | 2022-03-16 | 2027-04-14
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1190 | Reconstruction of Queens Blvd | 1 | DEVELOP SCOPE | 2019-09-30 | 2019-12-28 | 2024-09-30 | 2024-12-28
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1190 | Reconstruction of Queens Blvd | 2 | PRELIMINARY DESIGN | 2019-12-29 | 2020-04-26 | 2024-12-29 | 2025-04-27
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1190 | Reconstruction of Queens Blvd | 3 | FINAL DESIGN | 2020-04-27 | 2020-10-23 | 2025-04-28 | 2025-10-24
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1190 | Reconstruction of Queens Blvd | 4 | BID AWARD AND REGISTER CONTRCT | 2020-10-24 | 2021-01-21 | 2025-10-25 | 2026-01-22
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1190 | Reconstruction of Queens Blvd | 5 | CONSTRUCTION TO 25% | 2021-01-22 | 2021-05-21 | 2026-01-23 | 2026-05-22
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1190 | Reconstruction of Queens Blvd | 6 | CONSTRUCTION TO 50% | 2021-05-22 | 2021-09-18 | 2026-05-23 | 2026-09-19
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1190 | Reconstruction of Queens Blvd | 7 | CONSTRUCTION TO 75% | 2021-09-19 | 2022-01-16 | 2026-09-20 | 2027-01-17
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1190 | Reconstruction of Queens Blvd | 8 | ORIGINAL EQUIP & FURNISHING | 2022-01-17 | 2022-04-16 | 2027-01-18 | 2027-04-17
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1190 | Reconstruction of Queens Blvd | 9 | SUBSTANTIAL COMPLETION | 2022-04-17 | 2022-06-15 | 2027-04-18 | 2027-06-16
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1190 | Reconstruction of Queens Blvd | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-06-16 | 2022-07-15 | 2027-06-17 | 2027-07-16
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1192 | Jewel Ave | 1 | DEVELOP SCOPE | 2017-06-30 | 2017-09-27 | 2025-06-30 | 2025-09-27
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1192 | Jewel Ave | 2 | PRELIMINARY DESIGN | 2017-09-28 | 2018-01-25 | 2025-09-28 | 2026-01-25
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1192 | Jewel Ave | 3 | FINAL DESIGN | 2018-01-26 | 2018-07-24 | 2026-01-26 | 2026-07-24
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1192 | Jewel Ave | 4 | BID AWARD AND REGISTER CONTRCT | 2018-07-25 | 2018-10-22 | 2026-07-25 | 2026-10-22
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1192 | Jewel Ave | 5 | CONSTRUCTION TO 25% | 2018-10-23 | 2019-02-19 | 2026-10-23 | 2027-02-19
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1192 | Jewel Ave | 6 | CONSTRUCTION TO 50% | 2019-02-20 | 2019-06-19 | 2027-02-20 | 2027-06-19
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1192 | Jewel Ave | 7 | CONSTRUCTION TO 75% | 2019-06-20 | 2019-10-17 | 2027-06-20 | 2028-02-20
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1192 | Jewel Ave | 8 | ORIGINAL EQUIP & FURNISHING | 2019-10-18 | 2020-01-15 | 2026-10-17 | 2027-01-14
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1192 | Jewel Ave | 9 | SUBSTANTIAL COMPLETION | 2020-01-16 | 2020-03-15 | 2027-01-15 | 2027-03-15
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1192 | Jewel Ave | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-03-16 | 2020-04-14 | 2027-03-16 | 2027-04-14
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1196 | Cloudburst Project - St Albans | 1 | DEVELOP SCOPE | 2016-06-30 | 2016-09-27 | 2018-10-19 | 2020-08-06
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1196 | Cloudburst Project - St Albans | 2 | PRELIMINARY DESIGN | 2016-09-28 | 2017-01-25 | 2020-12-09 | 2022-02-20
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1196 | Cloudburst Project - St Albans | 3 | FINAL DESIGN | 2017-01-26 | 2017-07-24 | 2022-02-21 | 2022-12-09
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1196 | Cloudburst Project - St Albans | 4 | BID AWARD AND REGISTER CONTRCT | 2017-07-25 | 2017-10-22 | 2022-12-30 | 2023-05-22
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1196 | Cloudburst Project - St Albans | 5 | CONSTRUCTION TO 25% | 2017-10-23 | 2018-02-19 | 2023-05-22 | 2023-08-20
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1196 | Cloudburst Project - St Albans | 6 | CONSTRUCTION TO 50% | 2018-02-20 | 2018-06-19 | 2023-08-21 | 2023-11-18
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1196 | Cloudburst Project - St Albans | 7 | CONSTRUCTION TO 75% | 2018-06-20 | 2018-10-17 | 2023-11-19 | 2024-02-16
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1196 | Cloudburst Project - St Albans | 8 | ORIGINAL EQUIP & FURNISHING | 2018-10-18 | 2019-01-15 | 2024-02-17 | 2024-05-16
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1196 | Cloudburst Project - St Albans | 9 | SUBSTANTIAL COMPLETION | 2019-01-16 | 2019-03-16 | 2024-02-16 | 2024-05-16
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1196 | Cloudburst Project - St Albans | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-03-17 | 2019-04-15 | 2024-05-17 | 2026-06-30
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1197 | Astoria Boulevard Safety Improvements | 1 | DEVELOP SCOPE | 2020-06-30 | 2020-09-27 | 2021-06-30 | 2021-09-27
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1197 | Astoria Boulevard Safety Improvements | 2 | PRELIMINARY DESIGN | 2020-09-28 | 2021-01-25 | 2021-09-28 | 2022-01-25
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1197 | Astoria Boulevard Safety Improvements | 3 | FINAL DESIGN | 2021-01-26 | 2021-07-24 | 2022-01-26 | 2022-07-24
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1197 | Astoria Boulevard Safety Improvements | 4 | BID AWARD AND REGISTER CONTRCT | 2021-07-25 | 2021-10-22 | 2022-07-25 | 2022-10-22
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1197 | Astoria Boulevard Safety Improvements | 5 | CONSTRUCTION TO 25% | 2021-10-23 | 2022-02-19 | 2022-10-23 | 2023-02-19
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1197 | Astoria Boulevard Safety Improvements | 6 | CONSTRUCTION TO 50% | 2022-02-20 | 2022-06-19 | 2023-02-20 | 2023-06-19
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1197 | Astoria Boulevard Safety Improvements | 7 | CONSTRUCTION TO 75% | 2022-06-20 | 2022-10-17 | 2023-06-20 | 2023-10-17
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1197 | Astoria Boulevard Safety Improvements | 8 | ORIGINAL EQUIP & FURNISHING | 2022-10-18 | 2023-01-15 | 2023-10-18 | 2024-01-15
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1197 | Astoria Boulevard Safety Improvements | 9 | SUBSTANTIAL COMPLETION | 2023-01-16 | 2023-03-16 | 2024-01-16 | 2024-03-15
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1197 | Astoria Boulevard Safety Improvements | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-03-17 | 2023-04-15 | 2024-03-16 | 2024-04-14
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1198 | Reconstruction of Beach Channel Drive -- Phase B Non Sandy | 1 | DEVELOP SCOPE | 2019-06-30 | 2019-09-27 | 2022-06-30 | 2023-04-03
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1198 | Reconstruction of Beach Channel Drive -- Phase B Non Sandy | 2 | PRELIMINARY DESIGN | 2019-09-28 | 2020-01-25 | 2019-09-28 | 2020-01-25
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1198 | Reconstruction of Beach Channel Drive -- Phase B Non Sandy | 3 | FINAL DESIGN | 2020-01-26 | 2020-07-23 | 2020-01-26 | 2020-07-23
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1198 | Reconstruction of Beach Channel Drive -- Phase B Non Sandy | 4 | BID AWARD AND REGISTER CONTRCT | 2020-07-24 | 2020-10-21 | 2020-07-24 | 2020-10-21
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1198 | Reconstruction of Beach Channel Drive -- Phase B Non Sandy | 5 | CONSTRUCTION TO 25% | 2020-10-22 | 2021-02-18 | 2020-10-22 | 2021-02-18
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1198 | Reconstruction of Beach Channel Drive -- Phase B Non Sandy | 6 | CONSTRUCTION TO 50% | 2021-02-19 | 2021-06-18 | 2021-02-19 | 2021-06-18
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1198 | Reconstruction of Beach Channel Drive -- Phase B Non Sandy | 7 | CONSTRUCTION TO 75% | 2021-06-19 | 2021-10-16 | 2021-06-19 | 2024-10-16
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1198 | Reconstruction of Beach Channel Drive -- Phase B Non Sandy | 8 | ORIGINAL EQUIP & FURNISHING | 2021-10-17 | 2022-01-14 | 2022-06-30 | 2023-03-01
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1198 | Reconstruction of Beach Channel Drive -- Phase B Non Sandy | 9 | SUBSTANTIAL COMPLETION | 2022-01-15 | 2022-03-15 | 2023-03-02 | 2023-04-30
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1198 | Reconstruction of Beach Channel Drive -- Phase B Non Sandy | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-16 | 2022-04-14 | 2023-05-01 | 2024-05-29
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1199 | Beach 84th Street End | 1 | DEVELOP SCOPE | 2019-05-01 | 2019-12-11 | 2019-05-01 | 2020-01-29
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1199 | Beach 84th Street End | 2 | PRELIMINARY DESIGN | 2020-06-09 | 2021-07-04 | 2020-06-09 | 2021-07-04
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1199 | Beach 84th Street End | 3 | FINAL DESIGN | 2021-07-04 | 2022-09-11 | 2021-07-04 | 2022-09-11
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1199 | Beach 84th Street End | 4 | BID AWARD AND REGISTER CONTRCT | 2022-10-02 | 2023-02-19 | 2022-10-02 | 2023-02-19
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1199 | Beach 84th Street End | 5 | CONSTRUCTION TO 25% | 2023-08-31 | 2024-02-28 | 2023-06-01 | 2023-12-20
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1199 | Beach 84th Street End | 6 | CONSTRUCTION TO 50% | 2024-02-29 | 2024-08-28 | 2023-12-20 | 2024-07-10
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1199 | Beach 84th Street End | 7 | CONSTRUCTION TO 75% | 2024-08-29 | 2025-02-26 | 2024-07-11 | 2025-01-08
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1199 | Beach 84th Street End | 8 | ORIGINAL EQUIP & FURNISHING | 2025-02-27 | 2025-05-27 | 2025-01-09 | 2025-04-08
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1199 | Beach 84th Street End | 9 | SUBSTANTIAL COMPLETION | 2023-08-30 | 2025-08-19 | 2023-08-30 | 2025-08-19
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1199 | Beach 84th Street End | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-08-19 | 2025-11-11 | 2025-08-19 | 2025-11-11
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1200 | Vision Zero Great Streets Northern Boulevard Phase 1 | 1 | DEVELOP SCOPE | 2020-06-30 | 2020-12-11 | 2020-06-30 | 2020-12-11
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1200 | Vision Zero Great Streets Northern Boulevard Phase 1 | 2 | PRELIMINARY DESIGN | 2021-05-01 | 2022-08-06 | 2021-05-01 | 2022-08-06
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1200 | Vision Zero Great Streets Northern Boulevard Phase 1 | 3 | FINAL DESIGN | 2022-08-06 | 2023-11-18 | 2022-08-06 | 2023-11-18
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1200 | Vision Zero Great Streets Northern Boulevard Phase 1 | 4 | BID AWARD AND REGISTER CONTRCT | 2024-03-19 | 2024-05-26 | 2024-03-19 | 2024-05-26
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1200 | Vision Zero Great Streets Northern Boulevard Phase 1 | 5 | CONSTRUCTION TO 25% | 2024-06-25 | 2025-01-13 | 2024-06-25 | 2025-01-13
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1200 | Vision Zero Great Streets Northern Boulevard Phase 1 | 6 | CONSTRUCTION TO 50% | 2025-01-13 | 2025-08-04 | 2025-01-13 | 2025-08-04
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1200 | Vision Zero Great Streets Northern Boulevard Phase 1 | 7 | CONSTRUCTION TO 75% | 2025-08-05 | 2026-02-22 | 2025-08-05 | 2026-02-22
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1200 | Vision Zero Great Streets Northern Boulevard Phase 1 | 8 | ORIGINAL EQUIP & FURNISHING | 2026-02-23 | 2026-05-23 | 2026-02-23 | 2026-05-23
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1200 | Vision Zero Great Streets Northern Boulevard Phase 1 | 9 | SUBSTANTIAL COMPLETION | 2026-09-13 | 2026-09-13 | 2026-09-13 | 2026-09-13
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1200 | Vision Zero Great Streets Northern Boulevard Phase 1 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2026-09-14 | 2026-12-06 | 2026-09-14 | 2026-12-06
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1201 | 34TH AVE MALLS IMPROVEMENTS | 1 | DESIGN | 2021-05-23 | 2023-10-01 | 2021-05-23 | 2023-10-01
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1201 | 34TH AVE MALLS IMPROVEMENTS | 2 | CONSTRUCTION | 2024-05-26 | 2026-08-12 | 2024-05-26 | 2026-08-12
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1201 | 34TH AVE MALLS IMPROVEMENTS | 3 | ORIGINAL EQUIP & FURNISHING | 2026-08-13 | 2026-08-13 | 2026-08-13 | 2026-08-13
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1201 | 34TH AVE MALLS IMPROVEMENTS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2026-08-12 | 2026-11-06 | 2026-08-12 | 2026-11-06
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ788 | LIC/Hunters Point Area-wide Reconstruction | 1 | DEVELOP SCOPE | 2005-05-21 | 2005-08-18 | 2010-05-27 | 2011-12-28
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ788 | LIC/Hunters Point Area-wide Reconstruction | 2 | PRELIMINARY DESIGN | 2005-08-19 | 2005-12-16 | 2014-10-01 | 2020-08-25
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ788 | LIC/Hunters Point Area-wide Reconstruction | 3 | FINAL DESIGN | 2005-12-17 | 2006-06-14 | 2021-05-01 | 2024-11-17
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ788 | LIC/Hunters Point Area-wide Reconstruction | 4 | BID AWARD AND REGISTER CONTRCT | 2006-06-15 | 2006-09-12 | 2021-05-01 | 2024-11-17
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ788 | LIC/Hunters Point Area-wide Reconstruction | 5 | CONSTRUCTION TO 25% | 2006-09-13 | 2007-01-10 | 2021-05-01 | 2024-11-17
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ788 | LIC/Hunters Point Area-wide Reconstruction | 6 | CONSTRUCTION TO 50% | 2007-01-11 | 2007-05-10 | 2021-05-01 | 2024-11-17
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ788 | LIC/Hunters Point Area-wide Reconstruction | 7 | CONSTRUCTION TO 75% | 2007-05-11 | 2007-09-07 | 2021-05-01 | 2024-11-17
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ788 | LIC/Hunters Point Area-wide Reconstruction | 8 | ORIGINAL EQUIP & FURNISHING | 2007-09-08 | 2007-12-06 | 2021-05-01 | 2024-11-17
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ788 | LIC/Hunters Point Area-wide Reconstruction | 9 | SUBSTANTIAL COMPLETION | 2007-12-07 | 2008-02-04 | 2021-05-01 | 2024-11-17
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ788 | LIC/Hunters Point Area-wide Reconstruction | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-02-05 | 2008-03-05 | 2021-05-01 | 2024-11-17
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ789 | THOMSON AVE. SAFETY IMPROVEMENTS -- LAGUARDIA COMM. COLLEGE | 1 | DEVELOP SCOPE | 2022-06-30 | 2022-09-27 | 2019-05-11 | 2022-11-28
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ789 | THOMSON AVE. SAFETY IMPROVEMENTS -- LAGUARDIA COMM. COLLEGE | 2 | PRELIMINARY DESIGN | 2022-09-28 | 2023-01-25 | 2022-11-29 | 2023-03-28
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ789 | THOMSON AVE. SAFETY IMPROVEMENTS -- LAGUARDIA COMM. COLLEGE | 3 | FINAL DESIGN | 2023-01-26 | 2023-07-24 | 2023-03-29 | 2023-09-24
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ789 | THOMSON AVE. SAFETY IMPROVEMENTS -- LAGUARDIA COMM. COLLEGE | 4 | BID AWARD AND REGISTER CONTRCT | 2023-07-25 | 2023-10-22 | 2023-09-25 | 2023-12-23
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ789 | THOMSON AVE. SAFETY IMPROVEMENTS -- LAGUARDIA COMM. COLLEGE | 5 | CONSTRUCTION TO 25% | 2023-10-23 | 2024-02-19 | 2023-12-24 | 2024-04-21
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ789 | THOMSON AVE. SAFETY IMPROVEMENTS -- LAGUARDIA COMM. COLLEGE | 6 | CONSTRUCTION TO 50% | 2024-02-20 | 2024-06-18 | 2024-04-22 | 2024-08-19
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ789 | THOMSON AVE. SAFETY IMPROVEMENTS -- LAGUARDIA COMM. COLLEGE | 7 | CONSTRUCTION TO 75% | 2024-06-19 | 2024-10-16 | 2024-08-20 | 2024-12-17
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ789 | THOMSON AVE. SAFETY IMPROVEMENTS -- LAGUARDIA COMM. COLLEGE | 8 | ORIGINAL EQUIP & FURNISHING | 2024-10-17 | 2025-01-14 | 2024-12-18 | 2025-03-17
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ789 | THOMSON AVE. SAFETY IMPROVEMENTS -- LAGUARDIA COMM. COLLEGE | 9 | SUBSTANTIAL COMPLETION | 2025-01-15 | 2025-03-15 | 2025-03-18 | 2025-05-16
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ789 | THOMSON AVE. SAFETY IMPROVEMENTS -- LAGUARDIA COMM. COLLEGE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-03-16 | 2025-04-14 | 2025-05-17 | 2025-06-15
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ985A | Shore Road Embankment Repair | 1 | DEVELOP SCOPE | 2019-06-30 | 2019-09-27 | 2022-06-30 | 2022-09-27
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ985A | Shore Road Embankment Repair | 2 | PRELIMINARY DESIGN | 2019-09-28 | 2020-01-25 | 2022-09-28 | 2023-01-25
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ985A | Shore Road Embankment Repair | 3 | FINAL DESIGN | 2020-01-26 | 2020-07-23 | 2023-01-26 | 2023-07-24
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ985A | Shore Road Embankment Repair | 4 | BID AWARD AND REGISTER CONTRCT | 2020-07-24 | 2020-10-21 | 2023-07-25 | 2023-10-22
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ985A | Shore Road Embankment Repair | 5 | CONSTRUCTION TO 25% | 2020-10-22 | 2021-02-18 | 2023-10-23 | 2024-02-19
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ985A | Shore Road Embankment Repair | 6 | CONSTRUCTION TO 50% | 2021-02-19 | 2021-06-18 | 2024-02-20 | 2024-06-18
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ985A | Shore Road Embankment Repair | 7 | CONSTRUCTION TO 75% | 2021-06-19 | 2021-10-16 | 2024-06-19 | 2024-10-16
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ985A | Shore Road Embankment Repair | 8 | ORIGINAL EQUIP & FURNISHING | 2021-10-17 | 2022-01-14 | 2024-10-17 | 2025-01-14
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ985A | Shore Road Embankment Repair | 9 | SUBSTANTIAL COMPLETION | 2022-01-15 | 2022-03-15 | 2025-01-15 | 2025-03-15
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ985A | Shore Road Embankment Repair | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-16 | 2022-04-14 | 2025-03-16 | 2025-04-14
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF031C | Glendale Yard Pre-Engineered Shed | 1 | DEVELOP SCOPE | 2014-06-01 | 2014-08-29 | 2019-06-01 | 2019-08-29
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF031C | Glendale Yard Pre-Engineered Shed | 2 | PRELIMINARY DESIGN | 2014-08-30 | 2014-12-27 | 2019-08-30 | 2019-12-27
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF031C | Glendale Yard Pre-Engineered Shed | 3 | FINAL DESIGN | 2014-12-28 | 2015-06-25 | 2019-12-28 | 2020-06-24
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF031C | Glendale Yard Pre-Engineered Shed | 4 | BID AWARD AND REGISTER CONTRCT | 2015-06-26 | 2015-09-23 | 2020-06-25 | 2020-09-22
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF031C | Glendale Yard Pre-Engineered Shed | 5 | CONSTRUCTION TO 25% | 2015-09-24 | 2016-01-21 | 2020-09-23 | 2021-01-20
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF031C | Glendale Yard Pre-Engineered Shed | 6 | CONSTRUCTION TO 50% | 2016-01-22 | 2016-05-20 | 2021-01-21 | 2021-05-20
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF031C | Glendale Yard Pre-Engineered Shed | 7 | CONSTRUCTION TO 75% | 2016-05-21 | 2016-09-17 | 2021-05-21 | 2021-09-17
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF031C | Glendale Yard Pre-Engineered Shed | 8 | ORIGINAL EQUIP & FURNISHING | 2016-09-18 | 2016-12-16 | 2021-09-18 | 2021-12-16
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF031C | Glendale Yard Pre-Engineered Shed | 9 | SUBSTANTIAL COMPLETION | 2016-12-17 | 2017-02-14 | 2021-12-17 | 2022-02-14
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF031C | Glendale Yard Pre-Engineered Shed | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-02-15 | 2017-03-16 | 2022-02-15 | 2026-06-30
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF041 | QUEENS SAFETY CITY CONSTRUCTION 2 | 1 | DEVELOP SCOPE | 2021-06-30 | 2021-09-27 | 2021-06-30 | 2021-09-27
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF041 | QUEENS SAFETY CITY CONSTRUCTION 2 | 2 | PRELIMINARY DESIGN | 2021-09-28 | 2022-01-25 | 2021-09-28 | 2022-01-25
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF041 | QUEENS SAFETY CITY CONSTRUCTION 2 | 3 | FINAL DESIGN | 2022-01-26 | 2022-07-24 | 2022-01-26 | 2026-06-30
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF041 | QUEENS SAFETY CITY CONSTRUCTION 2 | 4 | BID AWARD AND REGISTER CONTRCT | 2022-07-25 | 2022-10-22 | 2026-07-01 | 2026-09-28
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF041 | QUEENS SAFETY CITY CONSTRUCTION 2 | 5 | CONSTRUCTION TO 25% | 2022-10-23 | 2023-02-19 | 2026-09-29 | 2027-01-26
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF041 | QUEENS SAFETY CITY CONSTRUCTION 2 | 6 | CONSTRUCTION TO 50% | 2023-02-20 | 2023-06-19 | 2027-01-27 | 2027-05-26
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF041 | QUEENS SAFETY CITY CONSTRUCTION 2 | 7 | CONSTRUCTION TO 75% | 2023-06-20 | 2023-10-17 | 2027-05-27 | 2027-09-23
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF041 | QUEENS SAFETY CITY CONSTRUCTION 2 | 8 | ORIGINAL EQUIP & FURNISHING | 2023-10-18 | 2024-01-15 | 2027-09-24 | 2027-12-22
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF041 | QUEENS SAFETY CITY CONSTRUCTION 2 | 9 | SUBSTANTIAL COMPLETION | 2024-01-16 | 2024-03-15 | 2027-12-23 | 2028-02-20
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF041 | QUEENS SAFETY CITY CONSTRUCTION 2 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-03-16 | 2024-04-14 | 2028-02-21 | 2029-10-12
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF12ST | 38-21 12th Street Rehabilitation | 1 | DEVELOP SCOPE | 2017-06-30 | 2017-09-27 | 2017-06-30 | 2017-09-27
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF12ST | 38-21 12th Street Rehabilitation | 2 | PRELIMINARY DESIGN | 2017-09-28 | 2018-01-25 | 2017-09-28 | 2018-01-25
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF12ST | 38-21 12th Street Rehabilitation | 3 | FINAL DESIGN | 2018-01-26 | 2018-07-24 | 2018-01-26 | 2018-07-24
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF12ST | 38-21 12th Street Rehabilitation | 4 | BID AWARD AND REGISTER CONTRCT | 2018-07-25 | 2018-10-22 | 2018-07-25 | 2018-10-22
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF12ST | 38-21 12th Street Rehabilitation | 5 | CONSTRUCTION TO 25% | 2018-10-23 | 2019-02-19 | 2018-10-23 | 2019-02-19
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF12ST | 38-21 12th Street Rehabilitation | 6 | CONSTRUCTION TO 50% | 2019-02-20 | 2019-06-19 | 2019-02-20 | 2019-06-19
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF12ST | 38-21 12th Street Rehabilitation | 7 | CONSTRUCTION TO 75% | 2019-06-20 | 2019-10-17 | 2019-06-20 | 2019-10-17
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF12ST | 38-21 12th Street Rehabilitation | 8 | ORIGINAL EQUIP & FURNISHING | 2019-10-18 | 2020-01-15 | 2019-10-18 | 2020-01-15
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF12ST | 38-21 12th Street Rehabilitation | 9 | SUBSTANTIAL COMPLETION | 2020-01-16 | 2020-03-15 | 2020-01-16 | 2020-03-15
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF12ST | 38-21 12th Street Rehabilitation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-03-16 | 2020-04-14 | 2020-03-16 | 2026-04-14
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF2002V | GLENDALE YARD TRAILERS | 1 | DEVELOP SCOPE | 2015-06-30 | 2015-10-27 | 2018-06-30 | 2018-10-27
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF2002V | GLENDALE YARD TRAILERS | 2 | DESIGN START | 2015-10-28 | 2017-04-19 | 2018-10-28 | 2020-04-19
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF2002V | GLENDALE YARD TRAILERS | 3 | CONSTRUCTION START | 2017-04-20 | 2019-04-09 | 2020-04-20 | 2022-04-09
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF4200V | Installation of Sewer & Water Services for 4200 Vernon Blvd. | 1 | DEVELOP SCOPE | 2020-06-30 | 2020-09-27 | 2020-06-30 | 2020-09-27
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF4200V | Installation of Sewer & Water Services for 4200 Vernon Blvd. | 2 | PRELIMINARY DESIGN | 2020-09-28 | 2021-01-25 | 2020-09-28 | 2021-01-25
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF4200V | Installation of Sewer & Water Services for 4200 Vernon Blvd. | 3 | FINAL DESIGN | 2021-01-26 | 2021-07-24 | 2021-01-26 | 2021-07-24
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF4200V | Installation of Sewer & Water Services for 4200 Vernon Blvd. | 4 | BID AWARD AND REGISTER CONTRCT | 2021-07-25 | 2021-10-22 | 2021-07-25 | 2021-10-22
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF4200V | Installation of Sewer & Water Services for 4200 Vernon Blvd. | 5 | CONSTRUCTION TO 25% | 2021-10-23 | 2022-02-19 | 2021-10-23 | 2022-02-19
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF4200V | Installation of Sewer & Water Services for 4200 Vernon Blvd. | 6 | CONSTRUCTION TO 50% | 2022-02-20 | 2022-06-19 | 2022-02-20 | 2022-06-19
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF4200V | Installation of Sewer & Water Services for 4200 Vernon Blvd. | 7 | CONSTRUCTION TO 75% | 2022-06-20 | 2022-10-17 | 2022-06-20 | 2022-10-17
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF4200V | Installation of Sewer & Water Services for 4200 Vernon Blvd. | 8 | ORIGINAL EQUIP & FURNISHING | 2022-10-18 | 2023-01-15 | 2022-10-18 | 2023-01-15
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF4200V | Installation of Sewer & Water Services for 4200 Vernon Blvd. | 9 | SUBSTANTIAL COMPLETION | 2023-01-16 | 2023-03-16 | 2023-01-16 | 2023-03-16
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF4200V | Installation of Sewer & Water Services for 4200 Vernon Blvd. | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-03-17 | 2023-04-15 | 2023-03-17 | 2023-04-15
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQFSW033 | 33-00 Northern Blvd Swing Space | 1 | DEVELOP SCOPE | 2019-06-30 | 2019-09-27 | 2019-06-30 | 2019-09-27
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQFSW033 | 33-00 Northern Blvd Swing Space | 2 | PRELIMINARY DESIGN | 2019-09-28 | 2020-01-25 | 2019-09-28 | 2020-01-25
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQFSW033 | 33-00 Northern Blvd Swing Space | 3 | FINAL DESIGN | 2020-01-26 | 2020-07-23 | 2020-01-26 | 2020-07-23
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQFSW033 | 33-00 Northern Blvd Swing Space | 4 | BID AWARD AND REGISTER CONTRCT | 2020-07-24 | 2020-10-21 | 2020-07-24 | 2020-10-21
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQFSW033 | 33-00 Northern Blvd Swing Space | 5 | CONSTRUCTION TO 25% | 2020-10-22 | 2021-02-18 | 2020-10-22 | 2021-02-18
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQFSW033 | 33-00 Northern Blvd Swing Space | 6 | CONSTRUCTION TO 50% | 2021-02-19 | 2021-06-18 | 2021-02-19 | 2021-06-18
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQFSW033 | 33-00 Northern Blvd Swing Space | 7 | CONSTRUCTION TO 75% | 2021-06-19 | 2021-10-16 | 2021-06-19 | 2021-10-16
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQFSW033 | 33-00 Northern Blvd Swing Space | 8 | ORIGINAL EQUIP & FURNISHING | 2021-10-17 | 2022-01-14 | 2021-10-17 | 2022-01-14
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQFSW033 | 33-00 Northern Blvd Swing Space | 9 | SUBSTANTIAL COMPLETION | 2022-01-15 | 2022-03-15 | 2022-01-15 | 2022-03-15
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQFSW033 | 33-00 Northern Blvd Swing Space | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-16 | 2022-04-14 | 2022-03-16 | 2022-04-14
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQMASPET | Maspeth Climate Control and Air Quality Improvements | 1 | DEVELOP SCOPE | 2017-06-30 | 2017-09-27 | 2019-06-30 | 2019-09-27
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQMASPET | Maspeth Climate Control and Air Quality Improvements | 2 | PRELIMINARY DESIGN | 2017-09-28 | 2018-01-25 | 2019-09-28 | 2020-01-25
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQMASPET | Maspeth Climate Control and Air Quality Improvements | 3 | FINAL DESIGN | 2018-01-26 | 2018-07-24 | 2020-01-26 | 2020-07-23
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQMASPET | Maspeth Climate Control and Air Quality Improvements | 4 | BID AWARD AND REGISTER CONTRCT | 2018-07-25 | 2018-10-22 | 2020-07-24 | 2020-10-21
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQMASPET | Maspeth Climate Control and Air Quality Improvements | 5 | CONSTRUCTION TO 25% | 2018-10-23 | 2019-02-19 | 2020-10-22 | 2021-02-18
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQMASPET | Maspeth Climate Control and Air Quality Improvements | 6 | CONSTRUCTION TO 50% | 2019-02-20 | 2019-06-19 | 2021-02-19 | 2021-06-18
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQMASPET | Maspeth Climate Control and Air Quality Improvements | 7 | CONSTRUCTION TO 75% | 2019-06-20 | 2019-10-17 | 2021-06-19 | 2021-10-16
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQMASPET | Maspeth Climate Control and Air Quality Improvements | 8 | ORIGINAL EQUIP & FURNISHING | 2019-10-18 | 2020-01-15 | 2021-10-17 | 2022-01-14
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQMASPET | Maspeth Climate Control and Air Quality Improvements | 9 | SUBSTANTIAL COMPLETION | 2020-01-16 | 2020-03-15 | 2022-01-15 | 2022-03-15
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQMASPET | Maspeth Climate Control and Air Quality Improvements | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-03-16 | 2020-04-14 | 2022-03-16 | 2022-04-14
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQSE877 | Woodhaven Blvd SBS SE-877 | 1 | DEVELOP SCOPE | 2020-06-30 | 2020-09-27 | 2023-06-30 | 2023-09-27
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQSE877 | Woodhaven Blvd SBS SE-877 | 2 | PRELIMINARY DESIGN | 2020-09-28 | 2021-01-25 | 2023-09-28 | 2024-01-25
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQSE877 | Woodhaven Blvd SBS SE-877 | 3 | FINAL DESIGN | 2021-01-26 | 2021-07-24 | 2024-01-26 | 2024-07-23
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQSE877 | Woodhaven Blvd SBS SE-877 | 4 | BID AWARD AND REGISTER CONTRCT | 2021-07-25 | 2021-10-22 | 2024-07-24 | 2024-10-21
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQSE877 | Woodhaven Blvd SBS SE-877 | 5 | CONSTRUCTION TO 25% | 2021-10-23 | 2022-02-19 | 2024-10-22 | 2025-02-18
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQSE877 | Woodhaven Blvd SBS SE-877 | 6 | CONSTRUCTION TO 50% | 2022-02-20 | 2022-06-19 | 2025-02-19 | 2025-06-18
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQSE877 | Woodhaven Blvd SBS SE-877 | 7 | CONSTRUCTION TO 75% | 2022-06-20 | 2022-10-17 | 2025-06-19 | 2025-10-16
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQSE877 | Woodhaven Blvd SBS SE-877 | 8 | ORIGINAL EQUIP & FURNISHING | 2022-10-18 | 2023-01-15 | 2025-10-17 | 2026-01-14
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQSE877 | Woodhaven Blvd SBS SE-877 | 9 | SUBSTANTIAL COMPLETION | 2023-01-16 | 2023-03-16 | 2026-01-15 | 2026-03-15
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQSE877 | Woodhaven Blvd SBS SE-877 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-03-17 | 2023-04-15 | 2026-03-16 | 2026-04-14
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQWILLPT | Willets Point Engineered Resurfacing | 1 | DEVELOP SCOPE | 2019-06-30 | 2019-09-03 | 2020-05-30 | 2020-11-13
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQWILLPT | Willets Point Engineered Resurfacing | 2 | PRELIMINARY DESIGN | 2020-05-10 | 2021-08-15 | 2020-05-10 | 2021-08-15
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQWILLPT | Willets Point Engineered Resurfacing | 3 | FINAL DESIGN | 2021-08-15 | 2022-11-27 | 2021-08-15 | 2022-11-27
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQWILLPT | Willets Point Engineered Resurfacing | 4 | BID AWARD AND REGISTER CONTRCT | 2022-11-27 | 2023-03-29 | 2022-11-27 | 2023-03-29
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQWILLPT | Willets Point Engineered Resurfacing | 5 | CONSTRUCTION TO 25% | 2023-10-03 | 2024-04-02 | 2023-06-05 | 2024-07-05
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQWILLPT | Willets Point Engineered Resurfacing | 6 | CONSTRUCTION TO 50% | 2024-04-03 | 2024-10-01 | 2024-07-06 | 2025-01-03
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQWILLPT | Willets Point Engineered Resurfacing | 7 | CONSTRUCTION TO 75% | 2024-10-02 | 2025-04-01 | 2025-01-04 | 2027-06-30
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQWILLPT | Willets Point Engineered Resurfacing | 8 | ORIGINAL EQUIP & FURNISHING | 2025-04-02 | 2025-06-30 | 2020-05-30 | 2020-06-30
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQWILLPT | Willets Point Engineered Resurfacing | 9 | SUBSTANTIAL COMPLETION | 2023-10-03 | 2025-09-22 | 2020-07-01 | 2025-09-22
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQWILLPT | Willets Point Engineered Resurfacing | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-09-22 | 2025-12-15 | 2025-09-25 | 2027-04-21
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWS2021Q1 | PRIOR NOTICE SIDEWALK - QUEENS | 1 | DEVELOP SCOPE | 2020-02-04 | 2020-03-24 | 2020-02-04 | 2020-03-24
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWS2021Q1 | PRIOR NOTICE SIDEWALK - QUEENS | 2 | DESIGN START | 2020-03-25 | 2020-06-30 | 2020-03-25 | 2020-06-30
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWS2021Q1 | PRIOR NOTICE SIDEWALK - QUEENS | 3 | CONSTRUCTION START | 2020-07-01 | 2021-06-20 | 2020-07-01 | 2021-06-20
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWS2021Q2 | PRIOR NOTICE SIDEWALK - QUEENS | 1 | DEVELOP SCOPE | 2020-02-04 | 2020-03-24 | 2020-02-04 | 2020-03-24
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWS2021Q2 | PRIOR NOTICE SIDEWALK - QUEENS | 2 | DESIGN START | 2020-03-25 | 2020-06-30 | 2020-03-25 | 2020-06-30
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWS2021Q2 | PRIOR NOTICE SIDEWALK - QUEENS | 3 | CONSTRUCTION START | 2020-07-01 | 2021-06-20 | 2020-07-01 | 2021-06-20
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWWATER37 | 37TH AVE DOT MOVE DUE TO DEP WATER TUN 3 | 1 | DEVELOP SCOPE | 2019-06-30 | 2019-09-27 | 2019-06-30 | 2019-09-27
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWWATER37 | 37TH AVE DOT MOVE DUE TO DEP WATER TUN 3 | 2 | PRELIMINARY DESIGN | 2019-09-28 | 2020-01-25 | 2019-09-28 | 2020-01-25
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWWATER37 | 37TH AVE DOT MOVE DUE TO DEP WATER TUN 3 | 3 | FINAL DESIGN | 2020-01-26 | 2020-07-23 | 2020-01-26 | 2020-07-23
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWWATER37 | 37TH AVE DOT MOVE DUE TO DEP WATER TUN 3 | 4 | BID AWARD AND REGISTER CONTRCT | 2020-07-24 | 2020-10-21 | 2020-07-24 | 2020-10-21
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWWATER37 | 37TH AVE DOT MOVE DUE TO DEP WATER TUN 3 | 5 | CONSTRUCTION TO 25% | 2020-10-22 | 2021-02-18 | 2020-10-22 | 2021-02-18
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWWATER37 | 37TH AVE DOT MOVE DUE TO DEP WATER TUN 3 | 6 | CONSTRUCTION TO 50% | 2021-02-19 | 2021-06-18 | 2021-02-19 | 2021-06-18
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWWATER37 | 37TH AVE DOT MOVE DUE TO DEP WATER TUN 3 | 7 | CONSTRUCTION TO 75% | 2021-06-19 | 2021-10-16 | 2021-06-19 | 2021-10-16
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWWATER37 | 37TH AVE DOT MOVE DUE TO DEP WATER TUN 3 | 8 | ORIGINAL EQUIP & FURNISHING | 2021-10-17 | 2022-01-14 | 2021-10-17 | 2022-01-14
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWWATER37 | 37TH AVE DOT MOVE DUE TO DEP WATER TUN 3 | 9 | SUBSTANTIAL COMPLETION | 2022-01-15 | 2022-03-15 | 2022-01-15 | 2022-03-15
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWWATER37 | 37TH AVE DOT MOVE DUE TO DEP WATER TUN 3 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-16 | 2022-04-14 | 2022-03-16 | 2022-04-14
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | JAMASTPLZ | Greater Jamaica Dev Corp Station Plaza Acquisition | 1 | DEVELOP SCOPE | 2014-06-30 | 2014-09-27 | 2016-06-30 | 2016-09-27
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | JAMASTPLZ | Greater Jamaica Dev Corp Station Plaza Acquisition | 2 | PRELIMINARY DESIGN | 2014-09-28 | 2015-01-25 | 2016-09-28 | 2017-01-25
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | JAMASTPLZ | Greater Jamaica Dev Corp Station Plaza Acquisition | 3 | FINAL DESIGN | 2015-01-26 | 2015-07-24 | 2017-01-26 | 2017-07-24
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | JAMASTPLZ | Greater Jamaica Dev Corp Station Plaza Acquisition | 4 | BID AWARD AND REGISTER CONTRCT | 2015-07-25 | 2015-10-22 | 2017-07-25 | 2017-10-22
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | JAMASTPLZ | Greater Jamaica Dev Corp Station Plaza Acquisition | 5 | CONSTRUCTION TO 25% | 2015-10-23 | 2016-02-19 | 2017-10-23 | 2018-02-19
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | JAMASTPLZ | Greater Jamaica Dev Corp Station Plaza Acquisition | 6 | CONSTRUCTION TO 50% | 2016-02-20 | 2016-06-18 | 2018-02-20 | 2018-06-19
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | JAMASTPLZ | Greater Jamaica Dev Corp Station Plaza Acquisition | 7 | CONSTRUCTION TO 75% | 2016-06-19 | 2016-10-16 | 2018-06-20 | 2018-10-17
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | JAMASTPLZ | Greater Jamaica Dev Corp Station Plaza Acquisition | 8 | ORIGINAL EQUIP & FURNISHING | 2016-10-17 | 2017-01-14 | 2018-10-18 | 2019-01-15
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | JAMASTPLZ | Greater Jamaica Dev Corp Station Plaza Acquisition | 9 | SUBSTANTIAL COMPLETION | 2017-01-15 | 2017-03-15 | 2019-01-16 | 2019-03-16
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | JAMASTPLZ | Greater Jamaica Dev Corp Station Plaza Acquisition | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-16 | 2017-04-14 | 2019-03-17 | 2021-04-15
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | QUEENSCWH | QUEENS COMMERCIAL CORRIDOR AT WOODHAVEN | 1 | DEVELOP SCOPE | 2014-07-01 | 2014-07-20 | 2018-07-01 | 2018-09-28
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | QUEENSCWH | QUEENS COMMERCIAL CORRIDOR AT WOODHAVEN | 2 | PRELIMINARY DESIGN | 2014-07-21 | 2014-08-04 | 2018-09-29 | 2019-01-26
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | QUEENSCWH | QUEENS COMMERCIAL CORRIDOR AT WOODHAVEN | 3 | FINAL DESIGN | 2014-08-05 | 2014-09-08 | 2019-01-27 | 2019-07-25
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | QUEENSCWH | QUEENS COMMERCIAL CORRIDOR AT WOODHAVEN | 4 | ORIGINAL EQUIP & FURNISHING | 2014-09-09 | 2014-09-18 | 2019-07-26 | 2019-10-23
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | QUEENSCWH | QUEENS COMMERCIAL CORRIDOR AT WOODHAVEN | 5 | CONSTRUCTION TO 25% | 2014-09-19 | 2014-10-03 | 2019-10-24 | 2020-02-20
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | QUEENSCWH | QUEENS COMMERCIAL CORRIDOR AT WOODHAVEN | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-10-04 | 2014-10-08 | 2020-02-21 | 2020-06-19
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | QUEENSCWH | QUEENS COMMERCIAL CORRIDOR AT WOODHAVEN | 7 | CONSTRUCTION TO 75% | 2014-10-04 | 2014-10-08 | 2020-06-20 | 2020-10-17
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | QUEENSCWH | QUEENS COMMERCIAL CORRIDOR AT WOODHAVEN | 8 | ORIGINAL EQUIP & FURNISHING | 2014-10-04 | 2014-10-08 | 2020-10-18 | 2021-01-15
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | QUEENSCWH | QUEENS COMMERCIAL CORRIDOR AT WOODHAVEN | 9 | SUBSTANTIAL COMPLETION | 2014-10-04 | 2014-10-08 | 2021-01-16 | 2021-03-16
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | QUEENSCWH | QUEENS COMMERCIAL CORRIDOR AT WOODHAVEN | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-10-04 | 2014-10-08 | 2021-03-17 | 2021-04-15
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | SANDHW11B | Reconstruction of Beach Channel Drive -- Phase B | 1 | DEVELOP SCOPE | 2018-06-30 | 2018-09-27 | 2018-08-13 | 2019-10-15
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | SANDHW11B | Reconstruction of Beach Channel Drive -- Phase B | 2 | PRELIMINARY DESIGN | 2018-09-28 | 2019-01-25 | 2019-05-17 | 2020-10-09
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | SANDHW11B | Reconstruction of Beach Channel Drive -- Phase B | 3 | FINAL DESIGN | 2019-01-26 | 2019-07-24 | 2020-10-10 | 2021-04-07
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | SANDHW11B | Reconstruction of Beach Channel Drive -- Phase B | 4 | BID AWARD AND REGISTER CONTRCT | 2019-07-25 | 2019-10-22 | 2021-04-08 | 2021-07-06
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | SANDHW11B | Reconstruction of Beach Channel Drive -- Phase B | 5 | CONSTRUCTION TO 25% | 2019-10-23 | 2020-02-19 | 2021-07-07 | 2021-11-03
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | SANDHW11B | Reconstruction of Beach Channel Drive -- Phase B | 6 | CONSTRUCTION TO 50% | 2020-02-20 | 2020-06-18 | 2021-11-04 | 2022-03-03
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | SANDHW11B | Reconstruction of Beach Channel Drive -- Phase B | 7 | CONSTRUCTION TO 75% | 2020-06-19 | 2020-10-16 | 2022-03-04 | 2022-07-01
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | SANDHW11B | Reconstruction of Beach Channel Drive -- Phase B | 8 | ORIGINAL EQUIP & FURNISHING | 2020-10-17 | 2021-01-14 | 2022-07-02 | 2022-09-29
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | SANDHW11B | Reconstruction of Beach Channel Drive -- Phase B | 9 | SUBSTANTIAL COMPLETION | 2021-01-15 | 2021-03-15 | 2022-10-17 | 2026-03-30
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | SANDHW11B | Reconstruction of Beach Channel Drive -- Phase B | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-16 | 2021-04-14 | 2026-03-31 | 2026-04-29
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | SEQPGRD4 | Southeast Queens Priority Grids 31-40 | 1 | DEVELOP SCOPE | 2018-06-30 | 2018-09-27 | 2018-06-30 | 2018-09-27
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | SEQPGRD4 | Southeast Queens Priority Grids 31-40 | 2 | PRELIMINARY DESIGN | 2018-09-28 | 2019-01-25 | 2018-09-28 | 2019-01-25
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | SEQPGRD4 | Southeast Queens Priority Grids 31-40 | 3 | FINAL DESIGN | 2019-01-26 | 2019-07-24 | 2019-01-26 | 2019-07-24
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | SEQPGRD4 | Southeast Queens Priority Grids 31-40 | 4 | BID AWARD AND REGISTER CONTRCT | 2019-07-25 | 2019-10-22 | 2019-07-25 | 2019-10-22
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | SEQPGRD4 | Southeast Queens Priority Grids 31-40 | 5 | CONSTRUCTION TO 25% | 2019-10-23 | 2020-02-19 | 2019-10-23 | 2020-02-19
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | SEQPGRD4 | Southeast Queens Priority Grids 31-40 | 6 | CONSTRUCTION TO 50% | 2020-02-20 | 2020-06-18 | 2020-02-20 | 2020-06-18
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | SEQPGRD4 | Southeast Queens Priority Grids 31-40 | 7 | CONSTRUCTION TO 75% | 2020-06-19 | 2020-10-16 | 2020-06-19 | 2020-10-16
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | SEQPGRD4 | Southeast Queens Priority Grids 31-40 | 8 | ORIGINAL EQUIP & FURNISHING | 2020-10-17 | 2021-01-14 | 2020-10-17 | 2021-01-14
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | SEQPGRD4 | Southeast Queens Priority Grids 31-40 | 9 | SUBSTANTIAL COMPLETION | 2021-01-15 | 2021-03-15 | 2021-01-15 | 2024-03-15
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | SEQPGRD4 | Southeast Queens Priority Grids 31-40 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-16 | 2021-04-14 | 2024-03-16 | 2027-06-30
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | SEQPGRD5 | Southeast Queens Priority Grids 41-50 | 1 | DEVELOP SCOPE | 2016-06-30 | 2016-09-27 | 2021-06-30 | 2021-09-27
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | SEQPGRD5 | Southeast Queens Priority Grids 41-50 | 2 | PRELIMINARY DESIGN | 2016-09-28 | 2017-01-25 | 2021-09-28 | 2022-01-25
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | SEQPGRD5 | Southeast Queens Priority Grids 41-50 | 3 | FINAL DESIGN | 2017-01-26 | 2017-07-24 | 2022-01-26 | 2022-07-24
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | SEQPGRD5 | Southeast Queens Priority Grids 41-50 | 4 | BID AWARD AND REGISTER CONTRCT | 2017-07-25 | 2017-10-22 | 2022-07-25 | 2022-10-22
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | SEQPGRD5 | Southeast Queens Priority Grids 41-50 | 5 | CONSTRUCTION TO 25% | 2017-10-23 | 2018-02-19 | 2022-10-23 | 2023-02-19
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | SEQPGRD5 | Southeast Queens Priority Grids 41-50 | 6 | CONSTRUCTION TO 50% | 2018-02-20 | 2018-06-19 | 2023-02-20 | 2023-06-19
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | SEQPGRD5 | Southeast Queens Priority Grids 41-50 | 7 | CONSTRUCTION TO 75% | 2018-06-20 | 2018-10-17 | 2023-06-20 | 2023-10-17
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | SEQPGRD5 | Southeast Queens Priority Grids 41-50 | 8 | ORIGINAL EQUIP & FURNISHING | 2018-10-18 | 2019-01-15 | 2023-10-18 | 2024-01-15
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | SEQPGRD5 | Southeast Queens Priority Grids 41-50 | 9 | SUBSTANTIAL COMPLETION | 2019-01-16 | 2019-03-16 | 2024-01-16 | 2024-03-15
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | SEQPGRD5 | Southeast Queens Priority Grids 41-50 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-03-17 | 2019-04-15 | 2024-03-16 | 2027-06-30
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF072017 | Extension of lighting project Woodhaven | 1 | BID AWARD AND REGISTER CONTRCT | 2018-06-30 | 2018-06-30 | 2018-06-30 | 2018-06-30
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF072017 | Extension of lighting project Woodhaven | 2 | CONSTRUCTION START | 2018-07-01 | 2018-08-14 | 2018-07-01 | 2018-08-14
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF072017 | Extension of lighting project Woodhaven | 3 | CONSTRUCTION COMPLETION | 2018-08-15 | 2020-03-06 | 2018-08-15 | 2024-03-06
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF18-2020 | STEINWAY #1&2 MUNICIPAL PARKING FIELDS | 1 | BID AWARD AND REGISTER CONTRCT | 2019-06-01 | 2019-06-01 | 2020-06-01 | 2020-06-01
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF18-2020 | STEINWAY #1&2 MUNICIPAL PARKING FIELDS | 2 | CONSTRUCTION START | 2019-06-02 | 2019-07-16 | 2020-06-02 | 2020-07-16
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF18-2020 | STEINWAY #1&2 MUNICIPAL PARKING FIELDS | 3 | CONSTRUCTION COMPLETION | 2019-07-17 | 2021-02-05 | 2020-07-17 | 2029-06-30
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF50308 | St lg Poles:Cross Bay Blvd ,156th to 165th Ave -S4319,MA122. | 1 | DEVELOP SCOPE | 2017-06-30 | 2017-09-27 | 2017-06-30 | 2017-09-27
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF50308 | St lg Poles:Cross Bay Blvd ,156th to 165th Ave -S4319,MA122. | 2 | PRELIMINARY DESIGN | 2017-09-28 | 2018-01-25 | 2017-09-28 | 2018-01-25
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF50308 | St lg Poles:Cross Bay Blvd ,156th to 165th Ave -S4319,MA122. | 3 | FINAL DESIGN | 2018-01-26 | 2018-07-24 | 2018-01-26 | 2018-07-24
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF50308 | St lg Poles:Cross Bay Blvd ,156th to 165th Ave -S4319,MA122. | 4 | BID AWARD AND REGISTER CONTRCT | 2018-07-25 | 2018-10-22 | 2018-07-25 | 2018-10-22
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF50308 | St lg Poles:Cross Bay Blvd ,156th to 165th Ave -S4319,MA122. | 5 | CONSTRUCTION TO 25% | 2018-10-23 | 2019-02-19 | 2018-10-23 | 2019-02-19
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF50308 | St lg Poles:Cross Bay Blvd ,156th to 165th Ave -S4319,MA122. | 6 | CONSTRUCTION TO 50% | 2019-02-20 | 2019-06-19 | 2019-02-20 | 2019-06-19
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF50308 | St lg Poles:Cross Bay Blvd ,156th to 165th Ave -S4319,MA122. | 7 | CONSTRUCTION TO 75% | 2019-06-20 | 2019-10-17 | 2019-06-20 | 2019-10-17
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF50308 | St lg Poles:Cross Bay Blvd ,156th to 165th Ave -S4319,MA122. | 8 | ORIGINAL EQUIP & FURNISHING | 2019-10-18 | 2020-01-15 | 2019-10-18 | 2020-01-15
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF50308 | St lg Poles:Cross Bay Blvd ,156th to 165th Ave -S4319,MA122. | 9 | SUBSTANTIAL COMPLETION | 2020-01-16 | 2020-03-15 | 2020-01-16 | 2020-03-15
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF50308 | St lg Poles:Cross Bay Blvd ,156th to 165th Ave -S4319,MA122. | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-03-16 | 2020-04-14 | 2020-03-16 | 2022-04-14
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF50310 | Rlp lg brackets 102nd St and 159 Ave, -XMA123.30A | 1 | DEVELOP SCOPE | 2017-06-30 | 2017-09-27 | 2017-06-30 | 2017-09-27
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF50310 | Rlp lg brackets 102nd St and 159 Ave, -XMA123.30A | 2 | PRELIMINARY DESIGN | 2017-09-28 | 2018-01-25 | 2017-09-28 | 2018-01-25
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF50310 | Rlp lg brackets 102nd St and 159 Ave, -XMA123.30A | 3 | FINAL DESIGN | 2018-01-26 | 2018-07-24 | 2018-01-26 | 2018-07-24
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF50310 | Rlp lg brackets 102nd St and 159 Ave, -XMA123.30A | 4 | BID AWARD AND REGISTER CONTRCT | 2018-07-25 | 2018-10-22 | 2018-07-25 | 2018-10-22
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF50310 | Rlp lg brackets 102nd St and 159 Ave, -XMA123.30A | 5 | CONSTRUCTION TO 25% | 2018-10-23 | 2019-02-19 | 2018-10-23 | 2019-02-19
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF50310 | Rlp lg brackets 102nd St and 159 Ave, -XMA123.30A | 6 | CONSTRUCTION TO 50% | 2019-02-20 | 2019-06-19 | 2019-02-20 | 2019-06-19
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF50310 | Rlp lg brackets 102nd St and 159 Ave, -XMA123.30A | 7 | CONSTRUCTION TO 75% | 2019-06-20 | 2019-10-17 | 2019-06-20 | 2019-10-17
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF50310 | Rlp lg brackets 102nd St and 159 Ave, -XMA123.30A | 8 | ORIGINAL EQUIP & FURNISHING | 2019-10-18 | 2020-01-15 | 2019-10-18 | 2020-01-15
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF50310 | Rlp lg brackets 102nd St and 159 Ave, -XMA123.30A | 9 | SUBSTANTIAL COMPLETION | 2020-01-16 | 2020-03-15 | 2020-01-16 | 2020-03-15
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF50310 | Rlp lg brackets 102nd St and 159 Ave, -XMA123.30A | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-03-16 | 2020-04-14 | 2020-03-16 | 2022-04-14
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF50312 | St lg repl Union Turnpike:Main St to Utopia Pkwy MA2179.30 | 1 | DEVELOP SCOPE | 2017-06-30 | 2017-09-27 | 2018-06-30 | 2018-09-27
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF50312 | St lg repl Union Turnpike:Main St to Utopia Pkwy MA2179.30 | 2 | PRELIMINARY DESIGN | 2017-09-28 | 2018-01-25 | 2018-09-28 | 2019-01-25
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF50312 | St lg repl Union Turnpike:Main St to Utopia Pkwy MA2179.30 | 3 | FINAL DESIGN | 2018-01-26 | 2018-07-24 | 2019-01-26 | 2019-07-24
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF50312 | St lg repl Union Turnpike:Main St to Utopia Pkwy MA2179.30 | 4 | BID AWARD AND REGISTER CONTRCT | 2018-07-25 | 2018-10-22 | 2019-07-25 | 2019-10-22
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF50312 | St lg repl Union Turnpike:Main St to Utopia Pkwy MA2179.30 | 5 | CONSTRUCTION TO 25% | 2018-10-23 | 2019-02-19 | 2019-10-23 | 2020-02-19
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF50312 | St lg repl Union Turnpike:Main St to Utopia Pkwy MA2179.30 | 6 | CONSTRUCTION TO 50% | 2019-02-20 | 2019-06-19 | 2020-02-20 | 2020-06-18
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF50312 | St lg repl Union Turnpike:Main St to Utopia Pkwy MA2179.30 | 7 | CONSTRUCTION TO 75% | 2019-06-20 | 2019-10-17 | 2020-06-19 | 2020-10-16
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF50312 | St lg repl Union Turnpike:Main St to Utopia Pkwy MA2179.30 | 8 | ORIGINAL EQUIP & FURNISHING | 2019-10-18 | 2020-01-15 | 2020-10-17 | 2021-01-14
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF50312 | St lg repl Union Turnpike:Main St to Utopia Pkwy MA2179.30 | 9 | SUBSTANTIAL COMPLETION | 2020-01-16 | 2020-03-15 | 2021-01-15 | 2021-03-15
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF50312 | St lg repl Union Turnpike:Main St to Utopia Pkwy MA2179.30 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-03-16 | 2020-04-14 | 2021-03-16 | 2021-04-14
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TFD503-04 | ROOSEVELT AVENUE STREET LIGHTING | 1 | BID AWARD AND REGISTER CONTRCT | 2005-05-15 | 2005-05-15 | 2018-05-15 | 2018-05-15
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TFD503-04 | ROOSEVELT AVENUE STREET LIGHTING | 2 | CONSTRUCTION START | 2005-05-16 | 2005-06-29 | 2018-05-16 | 2018-06-29
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TFD503-04 | ROOSEVELT AVENUE STREET LIGHTING | 3 | CONSTRUCTION COMPLETION | 2005-06-30 | 2007-01-20 | 2018-06-30 | 2024-06-30
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TFD503Q32 | MYRTLE AVE DECORATIVE LIGHTING QUEENS | 1 | DEVELOP SCOPE | 2017-06-30 | 2017-09-27 | 2018-06-30 | 2018-09-27
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TFD503Q32 | MYRTLE AVE DECORATIVE LIGHTING QUEENS | 2 | PRELIMINARY DESIGN | 2017-09-28 | 2018-01-25 | 2018-09-28 | 2019-01-25
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TFD503Q32 | MYRTLE AVE DECORATIVE LIGHTING QUEENS | 3 | FINAL DESIGN | 2018-01-26 | 2018-07-24 | 2019-01-26 | 2019-07-24
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TFD503Q32 | MYRTLE AVE DECORATIVE LIGHTING QUEENS | 4 | BID AWARD AND REGISTER CONTRCT | 2018-07-25 | 2018-10-22 | 2019-07-25 | 2019-10-22
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TFD503Q32 | MYRTLE AVE DECORATIVE LIGHTING QUEENS | 5 | CONSTRUCTION TO 25% | 2018-10-23 | 2019-02-19 | 2019-10-23 | 2020-02-19
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TFD503Q32 | MYRTLE AVE DECORATIVE LIGHTING QUEENS | 6 | CONSTRUCTION TO 50% | 2019-02-20 | 2019-06-19 | 2020-02-20 | 2020-06-18
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TFD503Q32 | MYRTLE AVE DECORATIVE LIGHTING QUEENS | 7 | CONSTRUCTION TO 75% | 2019-06-20 | 2019-10-17 | 2020-06-19 | 2020-10-16
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TFD503Q32 | MYRTLE AVE DECORATIVE LIGHTING QUEENS | 8 | ORIGINAL EQUIP & FURNISHING | 2019-10-18 | 2020-01-15 | 2020-10-17 | 2021-01-14
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TFD503Q32 | MYRTLE AVE DECORATIVE LIGHTING QUEENS | 9 | SUBSTANTIAL COMPLETION | 2020-01-16 | 2020-03-15 | 2021-01-15 | 2021-03-15
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TFD503Q32 | MYRTLE AVE DECORATIVE LIGHTING QUEENS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-03-16 | 2020-04-14 | 2021-03-16 | 2024-04-14
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TFD503Q33 | Lght along Merrick bt. Hook Creek Blvd &Springfield Blvd | 2 | PRELIMINARY DESIGN | 2017-09-28 | 2018-01-25 | 2017-09-28 | 2018-01-25
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TFD503Q33 | Lght along Merrick bt. Hook Creek Blvd &Springfield Blvd | 3 | FINAL DESIGN | 2018-01-26 | 2018-07-24 | 2018-01-26 | 2018-07-24
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TFD503Q33 | Lght along Merrick bt. Hook Creek Blvd &Springfield Blvd | 4 | BID AWARD AND REGISTER CONTRCT | 2018-07-25 | 2018-10-22 | 2018-07-25 | 2018-10-22
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TFD503Q33 | Lght along Merrick bt. Hook Creek Blvd &Springfield Blvd | 5 | CONSTRUCTION TO 25% | 2018-10-23 | 2019-02-19 | 2018-10-23 | 2019-02-19
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TFD503Q33 | Lght along Merrick bt. Hook Creek Blvd &Springfield Blvd | 6 | CONSTRUCTION TO 50% | 2019-02-20 | 2019-06-19 | 2019-02-20 | 2019-06-19
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TFD503Q33 | Lght along Merrick bt. Hook Creek Blvd &Springfield Blvd | 7 | CONSTRUCTION TO 75% | 2019-06-20 | 2019-10-17 | 2019-06-20 | 2019-10-17
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TFD503Q33 | Lght along Merrick bt. Hook Creek Blvd &Springfield Blvd | 8 | ORIGINAL EQUIP & FURNISHING | 2019-10-18 | 2020-01-15 | 2019-10-18 | 2020-01-15
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TFD503Q33 | Lght along Merrick bt. Hook Creek Blvd &Springfield Blvd | 9 | SUBSTANTIAL COMPLETION | 2020-01-16 | 2020-03-15 | 2020-01-16 | 2020-03-15
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TFD503Q33 | Lght along Merrick bt. Hook Creek Blvd &Springfield Blvd | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-03-16 | 2020-04-14 | 2020-03-16 | 2022-06-30
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TFWHSBSRT | SBS - Real Time Totem System | 1 | BID AWARD AND REGISTER CONTRCT | 2020-06-30 | 2020-06-30 | 2020-06-30 | 2020-06-30
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TFWHSBSRT | SBS - Real Time Totem System | 2 | CONSTRUCTION START | 2020-07-01 | 2020-08-14 | 2020-07-01 | 2020-08-14
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TFWHSBSRT | SBS - Real Time Totem System | 3 | CONSTRUCTION COMPLETION | 2020-08-15 | 2022-03-07 | 2020-08-15 | 2022-03-07
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | WHAMBEACH | HAMILTON BEACH BULKHEADS AND ROADWAYS | 1 | DEVELOP SCOPE | 2019-06-01 | 2019-08-29 | 2021-06-01 | 2021-08-29
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | WHAMBEACH | HAMILTON BEACH BULKHEADS AND ROADWAYS | 2 | PRELIMINARY DESIGN | 2019-08-30 | 2019-12-27 | 2021-08-30 | 2021-12-27
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | WHAMBEACH | HAMILTON BEACH BULKHEADS AND ROADWAYS | 3 | FINAL DESIGN | 2019-12-28 | 2020-06-24 | 2021-12-28 | 2022-06-25
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | WHAMBEACH | HAMILTON BEACH BULKHEADS AND ROADWAYS | 4 | BID AWARD AND REGISTER CONTRCT | 2020-06-25 | 2020-09-22 | 2022-06-26 | 2022-09-23
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | WHAMBEACH | HAMILTON BEACH BULKHEADS AND ROADWAYS | 5 | CONSTRUCTION TO 25% | 2020-09-23 | 2021-01-20 | 2022-09-24 | 2023-01-21
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | WHAMBEACH | HAMILTON BEACH BULKHEADS AND ROADWAYS | 6 | CONSTRUCTION TO 50% | 2021-01-21 | 2021-05-20 | 2023-01-22 | 2023-05-21
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | WHAMBEACH | HAMILTON BEACH BULKHEADS AND ROADWAYS | 7 | CONSTRUCTION TO 75% | 2021-05-21 | 2021-09-17 | 2023-05-22 | 2023-09-18
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | WHAMBEACH | HAMILTON BEACH BULKHEADS AND ROADWAYS | 8 | ORIGINAL EQUIP & FURNISHING | 2021-09-18 | 2021-12-16 | 2023-09-19 | 2023-12-17
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | WHAMBEACH | HAMILTON BEACH BULKHEADS AND ROADWAYS | 9 | SUBSTANTIAL COMPLETION | 2021-12-17 | 2022-02-14 | 2023-12-18 | 2024-02-15
20201123 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | WHAMBEACH | HAMILTON BEACH BULKHEADS AND ROADWAYS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-02-15 | 2022-03-16 | 2024-02-16 | 2027-03-16
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | GQGIKISE | GI - CONS OF PARKLAND RETROFITS IN KISSENA PK | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2021-01-04
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | GQQNGI-01 | GI - DSGN & CONS OF PARKLAND RETROFITS IN QUEENS | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | GQQNGI-01 | GI - DSGN & CONS OF PARKLAND RETROFITS IN QUEENS | 2 | DESIGN | 2018-12-28 | 2020-06-19 | 2018-12-28 | 2020-06-19
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | GQQNGI-01 | GI - DSGN & CONS OF PARKLAND RETROFITS IN QUEENS | 3 | BID/ REGISTER CONTRACT | 2020-06-20 | 2021-03-16 | 2020-06-20 | 2021-03-16
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | GQQNGI-01 | GI - DSGN & CONS OF PARKLAND RETROFITS IN QUEENS | 4 | CONSTRUCTION | 2021-03-17 | 2024-03-15 | 2021-03-17 | 2024-03-15
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | GQQNGI-01 | GI - DSGN & CONS OF PARKLAND RETROFITS IN QUEENS | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-03-16 | 2026-03-15 | 2024-03-16 | 2026-03-15
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | LIC-CTSQP | LIC- Court Square Park - Q267-120M | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | LIC-CTSQP | LIC- Court Square Park - Q267-120M | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | LIC-CTSQP | LIC- Court Square Park - Q267-120M | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | LIC-CTSQP | LIC- Court Square Park - Q267-120M | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | LIC-CTSQP | LIC- Court Square Park - Q267-120M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | LIC-QNBBP | LIC-Queensbridge Baby Park Q104 | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | LIC-QNBBP | LIC-Queensbridge Baby Park Q104 | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | LIC-QNBBP | LIC-Queensbridge Baby Park Q104 | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | LIC-QNBBP | LIC-Queensbridge Baby Park Q104 | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | LIC-QNBBP | LIC-Queensbridge Baby Park Q104 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | NDF-NMKE1 | Nameoke Avenue Park- Site Work-Q509-220M | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | NDF-NMKE1 | Nameoke Avenue Park- Site Work-Q509-220M | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | NDF-NMKE1 | Nameoke Avenue Park- Site Work-Q509-220M | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | NDF-NMKE1 | Nameoke Avenue Park- Site Work-Q509-220M | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | NDF-NMKE1 | Nameoke Avenue Park- Site Work-Q509-220M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | NDF-NMKE2 | Nameoke Avenue Park- Comfort Station | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | NDF-NMKE2 | Nameoke Avenue Park- Comfort Station | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | NDF-NMKE2 | Nameoke Avenue Park- Comfort Station | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | NDF-NMKE2 | Nameoke Avenue Park- Comfort Station | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | NDF-NMKE2 | Nameoke Avenue Park- Comfort Station | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | NDF-RDFR | NDF - Redfern Playground | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | NDF-RDFR | NDF - Redfern Playground | 2 | DESIGN | 2017-12-28 | 2019-12-27 | 2017-12-28 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | NDF-RDFR | NDF - Redfern Playground | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | NDF-RDFR | NDF - Redfern Playground | 4 | CONSTRUCTION | 2020-09-23 | 2022-09-22 | 2020-09-23 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | NDF-RDFR | NDF - Redfern Playground | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-205D17H | HIGHLAND PK BF - RENOV. BASEBALL FLD 1&2 Q020-111M | 1 | DEVELOP SCOPE | 2010-07-01 | 2010-09-28 | 2010-07-01 | 2010-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-205D17H | HIGHLAND PK BF - RENOV. BASEBALL FLD 1&2 Q020-111M | 2 | DESIGN | 2010-09-29 | 2010-12-27 | 2010-09-29 | 2010-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-205D17H | HIGHLAND PK BF - RENOV. BASEBALL FLD 1&2 Q020-111M | 3 | BID/ REGISTER CONTRACT | 2010-12-28 | 2011-03-27 | 2010-12-28 | 2011-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-205D17H | HIGHLAND PK BF - RENOV. BASEBALL FLD 1&2 Q020-111M | 4 | CONSTRUCTION | 2011-03-28 | 2012-03-26 | 2011-03-28 | 2012-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-205D17H | HIGHLAND PK BF - RENOV. BASEBALL FLD 1&2 Q020-111M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-03-27 | 2013-03-26 | 2012-03-27 | 2021-11-07
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-218MPNC | MARINE PARK- SALT MARSH CTR B057-115M | 1 | DEVELOP SCOPE | 2014-07-01 | 2014-09-28 | 2014-07-01 | 2014-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-218MPNC | MARINE PARK- SALT MARSH CTR B057-115M | 2 | DESIGN | 2014-09-29 | 2014-12-27 | 2014-09-29 | 2014-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-218MPNC | MARINE PARK- SALT MARSH CTR B057-115M | 3 | BID/ REGISTER CONTRACT | 2014-12-28 | 2015-03-27 | 2014-12-28 | 2015-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-218MPNC | MARINE PARK- SALT MARSH CTR B057-115M | 4 | CONSTRUCTION | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2016-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-218MPNC | MARINE PARK- SALT MARSH CTR B057-115M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2022-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400CHLD | FMCP - PLGD FOR ALL CHILDREN, RC Q099-499A | 4 | CONSTRUCTION | 2001-06-16 | 2003-12-02 | 2001-06-16 | 2003-12-02
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400CHLD | FMCP - PLGD FOR ALL CHILDREN, RC Q099-499A | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2003-12-03 | 2004-12-01 | 2003-12-03 | 2004-12-01
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400LNCP | Challenge Playground R/C Q346-118M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400LNCP | Challenge Playground R/C Q346-118M | 2 | DESIGN | 2017-12-28 | 2019-12-27 | 2017-12-28 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400LNCP | Challenge Playground R/C Q346-118M | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400LNCP | Challenge Playground R/C Q346-118M | 4 | CONSTRUCTION | 2020-09-23 | 2022-09-22 | 2020-09-23 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400LNCP | Challenge Playground R/C Q346-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400MEAD | FMCP - MEADOW LAKE Q099-511M | 1 | DEVELOP SCOPE | 2004-07-01 | 2004-09-28 | 2004-07-01 | 2004-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400MEAD | FMCP - MEADOW LAKE Q099-511M | 2 | DESIGN | 2004-09-29 | 2004-12-27 | 2004-09-29 | 2004-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400MEAD | FMCP - MEADOW LAKE Q099-511M | 3 | BID/ REGISTER CONTRACT | 2005-03-31 | 2005-06-30 | 2005-03-31 | 2005-06-30
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400MEAD | FMCP - MEADOW LAKE Q099-511M | 4 | CONSTRUCTION | 2005-07-01 | 2006-06-30 | 2005-07-01 | 2006-06-30
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400MEAD | FMCP - MEADOW LAKE Q099-511M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2006-07-01 | 2007-06-30 | 2006-07-01 | 2022-01-31
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400QZOO | QUEENS ZOO - AVIARY WALKWAY | 1 | DEVELOP SCOPE | 2004-07-01 | 2004-09-28 | 2004-07-01 | 2004-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400QZOO | QUEENS ZOO - AVIARY WALKWAY | 2 | DESIGN | 2004-09-29 | 2004-12-27 | 2004-09-29 | 2004-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400QZOO | QUEENS ZOO - AVIARY WALKWAY | 3 | BID/ REGISTER CONTRACT | 2004-12-28 | 2005-03-27 | 2004-12-28 | 2005-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400QZOO | QUEENS ZOO - AVIARY WALKWAY | 4 | CONSTRUCTION | 2005-03-28 | 2006-03-27 | 2005-03-28 | 2006-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400QZOO | QUEENS ZOO - AVIARY WALKWAY | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2006-03-28 | 2007-03-27 | 2006-03-28 | 2007-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400SITE | EDERLE SITE Q099-599/899 | 1 | DEVELOP SCOPE | 1998-07-01 | 1999-07-01 | 1998-07-01 | 1999-07-01
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400SITE | EDERLE SITE Q099-599/899 | 2 | DESIGN | 1999-07-02 | 2000-03-31 | 1999-07-02 | 2000-03-31
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400SITE | EDERLE SITE Q099-599/899 | 3 | BID/ REGISTER CONTRACT | 2000-05-10 | 2000-07-27 | 2000-05-10 | 2000-07-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400SITE | EDERLE SITE Q099-599/899 | 4 | CONSTRUCTION | 2000-11-13 | 2004-06-30 | 2000-11-13 | 2004-06-30
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400SITE | EDERLE SITE Q099-599/899 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2004-07-01 | 2005-06-30 | 2004-07-01 | 2011-05-01
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZO15 | Queens Zoo - public and service path paving | 1 | DEVELOP SCOPE | 2014-07-01 | 2014-09-28 | 2014-07-01 | 2014-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZO15 | Queens Zoo - public and service path paving | 2 | DESIGN | 2014-09-29 | 2014-12-27 | 2014-09-29 | 2014-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZO15 | Queens Zoo - public and service path paving | 3 | BID/ REGISTER CONTRACT | 2014-12-28 | 2015-03-27 | 2014-12-28 | 2015-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZO15 | Queens Zoo - public and service path paving | 4 | CONSTRUCTION | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2016-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZO15 | Queens Zoo - public and service path paving | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZO16 | QUEENS WILDLIFE CTR - OWL EXHIBIT | 1 | DEVELOP SCOPE | 2014-07-01 | 2014-09-28 | 2014-07-01 | 2014-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZO16 | QUEENS WILDLIFE CTR - OWL EXHIBIT | 2 | DESIGN | 2014-09-29 | 2014-12-27 | 2014-09-29 | 2014-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZO16 | QUEENS WILDLIFE CTR - OWL EXHIBIT | 3 | BID/ REGISTER CONTRACT | 2014-12-28 | 2015-03-27 | 2014-12-28 | 2015-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZO16 | QUEENS WILDLIFE CTR - OWL EXHIBIT | 4 | CONSTRUCTION | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2016-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZO16 | QUEENS WILDLIFE CTR - OWL EXHIBIT | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZO17 | Queens Zoo - Aviary Mesh Replacement | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2015-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZO17 | Queens Zoo - Aviary Mesh Replacement | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2015-09-29 | 2015-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZO17 | Queens Zoo - Aviary Mesh Replacement | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2015-12-28 | 2016-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZO17 | Queens Zoo - Aviary Mesh Replacement | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZO17 | Queens Zoo - Aviary Mesh Replacement | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2017-03-27 | 2018-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZO18 | Wildlife Conservation Society Farm Fence | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2015-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZO18 | Wildlife Conservation Society Farm Fence | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2015-09-29 | 2015-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZO18 | Wildlife Conservation Society Farm Fence | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2015-12-28 | 2016-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZO18 | Wildlife Conservation Society Farm Fence | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZO18 | Wildlife Conservation Society Farm Fence | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2017-03-27 | 2018-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZO20 | Queens Zoo - Concessions Roof Replacement | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZO20 | Queens Zoo - Concessions Roof Replacement | 2 | DESIGN | 2017-12-28 | 2019-03-27 | 2017-12-28 | 2019-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZO20 | Queens Zoo - Concessions Roof Replacement | 3 | BID/ REGISTER CONTRACT | 2019-03-28 | 2019-12-22 | 2019-03-28 | 2019-12-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZO20 | Queens Zoo - Concessions Roof Replacement | 4 | CONSTRUCTION | 2019-12-23 | 2020-12-21 | 2019-12-23 | 2020-12-21
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZO20 | Queens Zoo - Concessions Roof Replacement | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-12-22 | 2021-12-21 | 2020-12-22 | 2021-12-21
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZO21 | Queens Zoo - Animal Commis. Refrigerator | 3 | BID/ REGISTER CONTRACT | 2019-03-28 | 2019-12-22 | 2019-03-28 | 2019-12-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZO21 | Queens Zoo - Animal Commis. Refrigerator | 4 | CONSTRUCTION | 2019-12-23 | 2020-12-21 | 2019-12-23 | 2020-12-21
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZO21 | Queens Zoo - Animal Commis. Refrigerator | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-12-22 | 2021-12-21 | 2020-12-22 | 2021-12-21
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZO22 | Queens Zoo - Bear ExhibitGuest Railing/Bench replacement | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZO22 | Queens Zoo - Bear ExhibitGuest Railing/Bench replacement | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZO22 | Queens Zoo - Bear ExhibitGuest Railing/Bench replacement | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZO22 | Queens Zoo - Bear ExhibitGuest Railing/Bench replacement | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZO22 | Queens Zoo - Bear ExhibitGuest Railing/Bench replacement | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZO23 | Queens Zoo - sh/Eagle Boardwalk/Dance Floor Replacement | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZO23 | Queens Zoo - sh/Eagle Boardwalk/Dance Floor Replacement | 2 | DESIGN | 2017-12-28 | 2019-03-27 | 2017-12-28 | 2019-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZO23 | Queens Zoo - sh/Eagle Boardwalk/Dance Floor Replacement | 3 | BID/ REGISTER CONTRACT | 2019-03-28 | 2019-12-22 | 2019-03-28 | 2019-12-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZO23 | Queens Zoo - sh/Eagle Boardwalk/Dance Floor Replacement | 4 | CONSTRUCTION | 2019-12-23 | 2020-12-21 | 2019-12-23 | 2020-12-21
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZO23 | Queens Zoo - sh/Eagle Boardwalk/Dance Floor Replacement | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-12-22 | 2021-12-21 | 2020-12-22 | 2021-12-21
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZOO4 | Queens Zoo - Admnistration Building - roof replacement | 1 | DEVELOP SCOPE | 2008-07-01 | 2008-09-28 | 2008-07-01 | 2008-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZOO4 | Queens Zoo - Admnistration Building - roof replacement | 2 | DESIGN | 2008-09-29 | 2008-12-27 | 2008-09-29 | 2008-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZOO4 | Queens Zoo - Admnistration Building - roof replacement | 3 | BID/ REGISTER CONTRACT | 2008-12-28 | 2009-03-27 | 2008-12-28 | 2009-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZOO4 | Queens Zoo - Admnistration Building - roof replacement | 4 | CONSTRUCTION | 2009-03-28 | 2010-03-27 | 2009-03-28 | 2010-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZOO4 | Queens Zoo - Admnistration Building - roof replacement | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2010-03-28 | 2011-03-27 | 2010-03-28 | 2014-04-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZOO8 | Queens Zoo - Education Classroom initiative | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2013-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZOO8 | Queens Zoo - Education Classroom initiative | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2013-09-29 | 2013-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZOO8 | Queens Zoo - Education Classroom initiative | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2013-12-28 | 2014-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZOO8 | Queens Zoo - Education Classroom initiative | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2014-03-28 | 2015-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZOO8 | Queens Zoo - Education Classroom initiative | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2016-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401APFS | Astoria Pool Filtration System | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401APFS | Astoria Pool Filtration System | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401APFS | Astoria Pool Filtration System | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401APFS | Astoria Pool Filtration System | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401APFS | Astoria Pool Filtration System | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401APPS | ASTORIA PK POOL RC Q004-113MA | 1 | DEVELOP SCOPE | 2012-10-01 | 2012-12-29 | 2012-10-01 | 2012-12-29
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401APPS | ASTORIA PK POOL RC Q004-113MA | 2 | DESIGN | 2012-12-30 | 2013-03-29 | 2012-12-30 | 2013-03-29
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401APPS | ASTORIA PK POOL RC Q004-113MA | 3 | BID/ REGISTER CONTRACT | 2013-03-30 | 2013-06-27 | 2013-03-30 | 2013-06-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401APPS | ASTORIA PK POOL RC Q004-113MA | 4 | CONSTRUCTION | 2013-06-28 | 2014-06-27 | 2013-06-28 | 2014-06-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401APPS | ASTORIA PK POOL RC Q004-113MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-06-28 | 2015-06-27 | 2014-06-28 | 2018-12-31
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401ASQP | ATHENS SQUARE PK RC OF PLGDS IN PS17 Q436-107M | 1 | DEVELOP SCOPE | 2006-07-01 | 2006-09-28 | 2006-07-01 | 2006-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401ASQP | ATHENS SQUARE PK RC OF PLGDS IN PS17 Q436-107M | 2 | DESIGN | 2006-09-29 | 2006-12-27 | 2006-09-29 | 2006-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401ASQP | ATHENS SQUARE PK RC OF PLGDS IN PS17 Q436-107M | 3 | BID/ REGISTER CONTRACT | 2006-12-28 | 2007-03-27 | 2006-12-28 | 2007-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401ASQP | ATHENS SQUARE PK RC OF PLGDS IN PS17 Q436-107M | 4 | CONSTRUCTION | 2007-03-28 | 2008-03-26 | 2007-03-28 | 2008-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401ASQP | ATHENS SQUARE PK RC OF PLGDS IN PS17 Q436-107M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-27 | 2009-03-26 | 2008-03-27 | 2023-09-10
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401BSNS | ASTORIA PK- DRAINAGE AT THE TENNIS COURT Q004-102MA1 | 1 | DEVELOP SCOPE | 2001-05-14 | 2001-10-13 | 2001-05-14 | 2001-10-13
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401BSNS | ASTORIA PK- DRAINAGE AT THE TENNIS COURT Q004-102MA1 | 2 | DESIGN | 2002-04-08 | 2003-06-17 | 2002-04-08 | 2003-06-17
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401BSNS | ASTORIA PK- DRAINAGE AT THE TENNIS COURT Q004-102MA1 | 3 | BID/ REGISTER CONTRACT | 2004-05-01 | 2004-07-06 | 2004-05-01 | 2004-07-06
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401BSNS | ASTORIA PK- DRAINAGE AT THE TENNIS COURT Q004-102MA1 | 4 | CONSTRUCTION | 2004-08-01 | 2005-07-31 | 2004-08-01 | 2005-07-31
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401BSNS | ASTORIA PK- DRAINAGE AT THE TENNIS COURT Q004-102MA1 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2004-08-01 | 2005-07-31 | 2004-08-01 | 2020-07-31
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401DKLL | Dutch Kills Playground R/C Q218-116M | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401DKLL | Dutch Kills Playground R/C Q218-116M | 2 | DESIGN | 2016-12-28 | 2018-03-22 | 2016-12-28 | 2018-03-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401DKLL | Dutch Kills Playground R/C Q218-116M | 3 | BID/ REGISTER CONTRACT | 2018-03-23 | 2018-12-17 | 2018-03-23 | 2018-12-17
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401DKLL | Dutch Kills Playground R/C Q218-116M | 4 | CONSTRUCTION | 2018-12-18 | 2020-12-16 | 2018-12-18 | 2020-12-16
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401DKLL | Dutch Kills Playground R/C Q218-116M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-12-17 | 2021-12-16 | 2020-12-17 | 2021-12-16
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401HCSW | Hallets Cove Seawall Q226-118M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401HCSW | Hallets Cove Seawall Q226-118M | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401HCSW | Hallets Cove Seawall Q226-118M | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401HCSW | Hallets Cove Seawall Q226-118M | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401HCSW | Hallets Cove Seawall Q226-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401JOEM | Joe Michael's Mile Path and Lighting Q135-214M | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2013-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401JOEM | Joe Michael's Mile Path and Lighting Q135-214M | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2013-09-29 | 2013-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401JOEM | Joe Michael's Mile Path and Lighting Q135-214M | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2013-12-28 | 2014-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401JOEM | Joe Michael's Mile Path and Lighting Q135-214M | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2014-03-28 | 2015-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401JOEM | Joe Michael's Mile Path and Lighting Q135-214M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2022-01-31
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401QBHB | Queensbridge Baby Park Handball Courts Q104-119M | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401QBHB | Queensbridge Baby Park Handball Courts Q104-119M | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401QBHB | Queensbridge Baby Park Handball Courts Q104-119M | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401QBHB | Queensbridge Baby Park Handball Courts Q104-119M | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401QBHB | Queensbridge Baby Park Handball Courts Q104-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401QSE2 | QUEENSBRIDGE PARK FIELDHOUSE CONS. Q104-114M | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2013-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401QSE2 | QUEENSBRIDGE PARK FIELDHOUSE CONS. Q104-114M | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2013-09-29 | 2013-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401QSE2 | QUEENSBRIDGE PARK FIELDHOUSE CONS. Q104-114M | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2013-12-28 | 2014-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401QSE2 | QUEENSBRIDGE PARK FIELDHOUSE CONS. Q104-114M | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2014-03-28 | 2015-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401QSE2 | QUEENSBRIDGE PARK FIELDHOUSE CONS. Q104-114M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2019-01-31
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401RAV2 | Ravenswood Playground R/C Q333-118M | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401RAV2 | Ravenswood Playground R/C Q333-118M | 2 | DESIGN | 2016-12-28 | 2018-03-22 | 2016-12-28 | 2018-03-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401RAV2 | Ravenswood Playground R/C Q333-118M | 3 | BID/ REGISTER CONTRACT | 2018-03-23 | 2018-12-17 | 2018-03-23 | 2018-12-17
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401RAV2 | Ravenswood Playground R/C Q333-118M | 4 | CONSTRUCTION | 2018-12-18 | 2020-12-16 | 2018-12-18 | 2020-12-16
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401RAV2 | Ravenswood Playground R/C Q333-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-12-17 | 2021-12-16 | 2020-12-17 | 2021-12-16
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401SMST | St. Michael's Playground Synthetic Turf Field R/C Q174A-119M | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401SMST | St. Michael's Playground Synthetic Turf Field R/C Q174A-119M | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401SMST | St. Michael's Playground Synthetic Turf Field R/C Q174A-119M | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401SMST | St. Michael's Playground Synthetic Turf Field R/C Q174A-119M | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401SMST | St. Michael's Playground Synthetic Turf Field R/C Q174A-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401SOC2 | Socrates Sculpture Park Building Expansion | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2015-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401SOC2 | Socrates Sculpture Park Building Expansion | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2015-09-29 | 2015-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401SOC2 | Socrates Sculpture Park Building Expansion | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2015-12-28 | 2016-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401SOC2 | Socrates Sculpture Park Building Expansion | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401SOC2 | Socrates Sculpture Park Building Expansion | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2017-03-27 | 2018-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401SOC3 | SOCRATES SCULPTURE PARK -REPAIR TO SEAWALL | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401SOC3 | SOCRATES SCULPTURE PARK -REPAIR TO SEAWALL | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401SOC3 | SOCRATES SCULPTURE PARK -REPAIR TO SEAWALL | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401SOC3 | SOCRATES SCULPTURE PARK -REPAIR TO SEAWALL | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401SOC3 | SOCRATES SCULPTURE PARK -REPAIR TO SEAWALL | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401SXOG | Sixteen Oaks Grove Renovations | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401SXOG | Sixteen Oaks Grove Renovations | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401SXOG | Sixteen Oaks Grove Renovations | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401SXOG | Sixteen Oaks Grove Renovations | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401SXOG | Sixteen Oaks Grove Renovations | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401TBDR | Triborough Bridge Plgd C Dog Run & Bball Court Q066-116M | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2015-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401TBDR | Triborough Bridge Plgd C Dog Run & Bball Court Q066-116M | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2015-09-29 | 2015-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401TBDR | Triborough Bridge Plgd C Dog Run & Bball Court Q066-116M | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2015-12-28 | 2016-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401TBDR | Triborough Bridge Plgd C Dog Run & Bball Court Q066-116M | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401TBDR | Triborough Bridge Plgd C Dog Run & Bball Court Q066-116M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2017-03-27 | 2022-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401WFF | Whitey Ford Field | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401WFF | Whitey Ford Field | 2 | DESIGN | 2017-12-28 | 2019-12-27 | 2017-12-28 | 2018-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401WFF | Whitey Ford Field | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2018-12-28 | 2019-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401WFF | Whitey Ford Field | 4 | CONSTRUCTION | 2020-09-23 | 2022-09-22 | 2019-09-24 | 2020-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401WFF | Whitey Ford Field | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2020-09-23 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401WFF1 | WHITEY FORD FIELD: R/C OF BASEBALL FIELD Q215-118M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401WFF1 | WHITEY FORD FIELD: R/C OF BASEBALL FIELD Q215-118M | 2 | DESIGN | 2017-12-28 | 2019-03-22 | 2017-12-28 | 2019-03-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401WFF1 | WHITEY FORD FIELD: R/C OF BASEBALL FIELD Q215-118M | 3 | BID/ REGISTER CONTRACT | 2019-03-23 | 2019-12-17 | 2019-03-23 | 2019-12-17
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401WFF1 | WHITEY FORD FIELD: R/C OF BASEBALL FIELD Q215-118M | 4 | CONSTRUCTION | 2019-12-18 | 2021-12-16 | 2019-12-18 | 2021-12-16
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401WFF1 | WHITEY FORD FIELD: R/C OF BASEBALL FIELD Q215-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-12-17 | 2022-12-16 | 2021-12-17 | 2022-12-16
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-402DBOY | Doughboy Plaza Park Seating Area R/C Q031A-118M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-402DBOY | Doughboy Plaza Park Seating Area R/C Q031A-118M | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-402DBOY | Doughboy Plaza Park Seating Area R/C Q031A-118M | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-402DBOY | Doughboy Plaza Park Seating Area R/C Q031A-118M | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-402DBOY | Doughboy Plaza Park Seating Area R/C Q031A-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-402HART | Hart Playground R/C Q067-117MA | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2013-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-402HART | Hart Playground R/C Q067-117MA | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2013-09-29 | 2013-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-402HART | Hart Playground R/C Q067-117MA | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2013-12-28 | 2014-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-402HART | Hart Playground R/C Q067-117MA | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2014-03-28 | 2015-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-402HART | Hart Playground R/C Q067-117MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2022-01-04
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-402SOHN | Carl R. Sohncke Square Renovations with Flagpole | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-402SOHN | Carl R. Sohncke Square Renovations with Flagpole | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-402SOHN | Carl R. Sohncke Square Renovations with Flagpole | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-402SOHN | Carl R. Sohncke Square Renovations with Flagpole | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-402SOHN | Carl R. Sohncke Square Renovations with Flagpole | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-402WIN2 | WINDMULLER PK RC SEATING AREA AND SLOPE RETENTION Q031-109M | 1 | DEVELOP SCOPE | 2007-07-01 | 2007-09-28 | 2007-07-01 | 2007-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-402WIN2 | WINDMULLER PK RC SEATING AREA AND SLOPE RETENTION Q031-109M | 2 | DESIGN | 2007-09-29 | 2007-12-27 | 2007-09-29 | 2007-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-402WIN2 | WINDMULLER PK RC SEATING AREA AND SLOPE RETENTION Q031-109M | 3 | BID/ REGISTER CONTRACT | 2007-12-28 | 2008-03-26 | 2007-12-28 | 2008-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-402WIN2 | WINDMULLER PK RC SEATING AREA AND SLOPE RETENTION Q031-109M | 4 | CONSTRUCTION | 2008-03-27 | 2009-03-26 | 2008-03-27 | 2009-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-402WIN2 | WINDMULLER PK RC SEATING AREA AND SLOPE RETENTION Q031-109M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2009-03-27 | 2010-03-26 | 2009-03-27 | 2023-04-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4031272 | P. S. 127 EAST ELMHURST PLGD PHASE II Q373-112MA2 | 1 | DEVELOP SCOPE | 2012-07-01 | 2012-09-28 | 2011-07-01 | 2011-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4031272 | P. S. 127 EAST ELMHURST PLGD PHASE II Q373-112MA2 | 2 | DESIGN | 2012-09-29 | 2012-12-27 | 2011-09-29 | 2011-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4031272 | P. S. 127 EAST ELMHURST PLGD PHASE II Q373-112MA2 | 3 | BID/ REGISTER CONTRACT | 2012-12-28 | 2013-03-27 | 2011-12-28 | 2012-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4031272 | P. S. 127 EAST ELMHURST PLGD PHASE II Q373-112MA2 | 4 | CONSTRUCTION | 2013-03-28 | 2014-03-27 | 2012-03-27 | 2013-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4031272 | P. S. 127 EAST ELMHURST PLGD PHASE II Q373-112MA2 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-03-28 | 2015-03-27 | 2013-03-27 | 2021-06-30
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-403GOR2 | Gorman Playground Upgrades-Q085-120M | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-403GOR2 | Gorman Playground Upgrades-Q085-120M | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-403GOR2 | Gorman Playground Upgrades-Q085-120M | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-403GOR2 | Gorman Playground Upgrades-Q085-120M | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-403GOR2 | Gorman Playground Upgrades-Q085-120M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-403GORP | Gorman Park ImprovementS | 1 | DEVELOP SCOPE | 2020-07-01 | 2020-12-27 | 2020-07-01 | 2020-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-403GORP | Gorman Park ImprovementS | 2 | DESIGN | 2020-12-28 | 2021-12-27 | 2020-12-28 | 2021-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-403GORP | Gorman Park ImprovementS | 3 | BID/ REGISTER CONTRACT | 2021-12-28 | 2022-09-23 | 2021-12-28 | 2022-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-403GORP | Gorman Park ImprovementS | 4 | CONSTRUCTION | 2022-09-24 | 2023-09-23 | 2022-09-24 | 2023-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-403GORP | Gorman Park ImprovementS | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-24 | 2024-09-22 | 2023-09-24 | 2024-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-403NORT | Northern Playground Synthetic Field Upgrade Q363-118M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-403NORT | Northern Playground Synthetic Field Upgrade Q363-118M | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-403NORT | Northern Playground Synthetic Field Upgrade Q363-118M | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-403NORT | Northern Playground Synthetic Field Upgrade Q363-118M | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-403NORT | Northern Playground Synthetic Field Upgrade Q363-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-403TPP4 | Travers Park and Staunton Play Field R/C QG-714M | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2013-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-403TPP4 | Travers Park and Staunton Play Field R/C QG-714M | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2013-09-29 | 2013-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-403TPP4 | Travers Park and Staunton Play Field R/C QG-714M | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2013-12-28 | 2014-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-403TPP4 | Travers Park and Staunton Play Field R/C QG-714M | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2014-03-28 | 2015-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-403TPP4 | Travers Park and Staunton Play Field R/C QG-714M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2021-05-31
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-403TTOT | Travers Park Tot Lot R/C Q303-117M | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-403TTOT | Travers Park Tot Lot R/C Q303-117M | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2016-12-28 | 2017-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-403TTOT | Travers Park Tot Lot R/C Q303-117M | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2017-12-28 | 2018-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-403TTOT | Travers Park Tot Lot R/C Q303-117M | 4 | CONSTRUCTION | 2018-09-24 | 2019-09-23 | 2018-09-24 | 2019-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-403TTOT | Travers Park Tot Lot R/C Q303-117M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404CCPS | Moore Homestead Playground R/C Q361-115M | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2013-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404CCPS | Moore Homestead Playground R/C Q361-115M | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2013-09-29 | 2013-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404CCPS | Moore Homestead Playground R/C Q361-115M | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2013-12-28 | 2014-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404CCPS | Moore Homestead Playground R/C Q361-115M | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2014-03-28 | 2015-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404CCPS | Moore Homestead Playground R/C Q361-115M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2022-05-25
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404CROW | Crowley Playground R/C | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2015-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404CROW | Crowley Playground R/C | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2015-09-29 | 2015-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404CROW | Crowley Playground R/C | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2015-12-28 | 2016-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404CROW | Crowley Playground R/C | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404CROW | Crowley Playground R/C | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2017-03-27 | 2025-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404JCPI | Josephine Caminiti Playground Improvements | 1 | DEVELOP SCOPE | 2020-07-01 | 2020-12-27 | 2020-07-01 | 2020-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404JCPI | Josephine Caminiti Playground Improvements | 2 | DESIGN | 2020-12-28 | 2021-12-27 | 2020-12-28 | 2021-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404JCPI | Josephine Caminiti Playground Improvements | 3 | BID/ REGISTER CONTRACT | 2021-12-28 | 2022-09-23 | 2021-12-28 | 2022-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404JCPI | Josephine Caminiti Playground Improvements | 4 | CONSTRUCTION | 2022-09-24 | 2023-09-23 | 2022-09-24 | 2023-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404JCPI | Josephine Caminiti Playground Improvements | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-24 | 2024-09-22 | 2023-09-24 | 2024-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404NTPG | Newtown Playground Paths & Plantings R/C Q041-116M | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2014-07-01 | 2014-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404NTPG | Newtown Playground Paths & Plantings R/C Q041-116M | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2014-09-29 | 2014-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404NTPG | Newtown Playground Paths & Plantings R/C Q041-116M | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2014-12-28 | 2015-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404NTPG | Newtown Playground Paths & Plantings R/C Q041-116M | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2015-03-28 | 2016-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404NTPG | Newtown Playground Paths & Plantings R/C Q041-116M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2016-03-27 | 2021-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404PATF | Park of the Americas Renovation- Q026-119M | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404PATF | Park of the Americas Renovation- Q026-119M | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404PATF | Park of the Americas Renovation- Q026-119M | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404PATF | Park of the Americas Renovation- Q026-119M | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404PATF | Park of the Americas Renovation- Q026-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404PKAM | PARK OF THE AMERICAS BATHROOM IMPROVEMENTS RC Q026 | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404PKAM | PARK OF THE AMERICAS BATHROOM IMPROVEMENTS RC Q026 | 2 | DESIGN | 2016-12-28 | 2018-12-27 | 2016-12-28 | 2018-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404PKAM | PARK OF THE AMERICAS BATHROOM IMPROVEMENTS RC Q026 | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404PKAM | PARK OF THE AMERICAS BATHROOM IMPROVEMENTS RC Q026 | 4 | CONSTRUCTION | 2019-09-24 | 2021-09-22 | 2019-09-24 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404PKAM | PARK OF THE AMERICAS BATHROOM IMPROVEMENTS RC Q026 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404WFMP | William F. Moore Park Renovation Q029-119M | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404WFMP | William F. Moore Park Renovation Q029-119M | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404WFMP | William F. Moore Park Renovation Q029-119M | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404WFMP | William F. Moore Park Renovation Q029-119M | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404WFMP | William F. Moore Park Renovation Q029-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404WMPG | William F Moore Park RECONSTRUCTION | 1 | DEVELOP SCOPE | 2020-07-01 | 2020-12-27 | 2020-07-01 | 2020-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404WMPG | William F Moore Park RECONSTRUCTION | 2 | DESIGN | 2020-12-28 | 2021-12-27 | 2020-12-28 | 2021-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404WMPG | William F Moore Park RECONSTRUCTION | 3 | BID/ REGISTER CONTRACT | 2021-12-28 | 2022-09-23 | 2021-12-28 | 2022-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404WMPG | William F Moore Park RECONSTRUCTION | 4 | CONSTRUCTION | 2022-09-24 | 2023-09-23 | 2022-09-24 | 2023-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404WMPG | William F Moore Park RECONSTRUCTION | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-24 | 2024-09-22 | 2023-09-24 | 2024-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405EGPK | EVERGREEN PARK (TOT PLGD RC) Q302-112M | 1 | DEVELOP SCOPE | 2012-07-01 | 2012-09-28 | 2011-07-01 | 2011-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405EGPK | EVERGREEN PARK (TOT PLGD RC) Q302-112M | 2 | DESIGN | 2012-09-29 | 2012-12-27 | 2011-09-29 | 2011-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405EGPK | EVERGREEN PARK (TOT PLGD RC) Q302-112M | 3 | BID/ REGISTER CONTRACT | 2012-12-28 | 2013-03-27 | 2011-12-28 | 2012-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405EGPK | EVERGREEN PARK (TOT PLGD RC) Q302-112M | 4 | CONSTRUCTION | 2013-03-28 | 2014-03-27 | 2012-03-27 | 2013-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405EGPK | EVERGREEN PARK (TOT PLGD RC) Q302-112M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-03-28 | 2015-03-27 | 2013-03-27 | 2022-04-30
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405EVE2 | Evergreen Park R/C Phase II | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405EVE2 | Evergreen Park R/C Phase II | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405EVE2 | Evergreen Park R/C Phase II | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405EVE2 | Evergreen Park R/C Phase II | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405EVE2 | Evergreen Park R/C Phase II | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2024-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405FPCS | FRONTERA PK C/S Q360-104MA2/404M | 1 | DEVELOP SCOPE | 2003-07-01 | 2003-09-30 | 2003-07-01 | 2003-09-30
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405FPCS | FRONTERA PK C/S Q360-104MA2/404M | 2 | DESIGN | 2003-10-01 | 2004-03-26 | 2003-10-01 | 2004-07-14
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405FPCS | FRONTERA PK C/S Q360-104MA2/404M | 3 | BID/ REGISTER CONTRACT | 2004-09-22 | 2004-12-31 | 2005-04-08 | 2005-09-20
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405FPCS | FRONTERA PK C/S Q360-104MA2/404M | 4 | CONSTRUCTION | 2005-01-01 | 2005-12-31 | 2006-05-15 | 2007-11-16
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405FPCS | FRONTERA PK C/S Q360-104MA2/404M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2006-01-01 | 2006-12-31 | 2007-11-17 | 2022-04-05
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405HPRR | Highland Park Ridgewood Reservoir Site Restoration | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405HPRR | Highland Park Ridgewood Reservoir Site Restoration | 2 | DESIGN | 2017-12-28 | 2019-03-22 | 2017-12-28 | 2019-03-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405HPRR | Highland Park Ridgewood Reservoir Site Restoration | 3 | BID/ REGISTER CONTRACT | 2019-03-23 | 2019-12-17 | 2019-03-23 | 2021-03-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405HPRR | Highland Park Ridgewood Reservoir Site Restoration | 4 | CONSTRUCTION | 2019-12-18 | 2021-12-16 | 2021-03-24 | 2023-03-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405HPRR | Highland Park Ridgewood Reservoir Site Restoration | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-12-17 | 2022-12-16 | 2023-03-24 | 2024-03-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405JP75 | JUNIPER PARK - 75TH STREET PLGD Q102-108M | 1 | DEVELOP SCOPE | 2007-07-01 | 2007-09-28 | 2007-07-01 | 2007-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405JP75 | JUNIPER PARK - 75TH STREET PLGD Q102-108M | 2 | DESIGN | 2007-09-29 | 2007-12-27 | 2007-09-29 | 2007-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405JP75 | JUNIPER PARK - 75TH STREET PLGD Q102-108M | 3 | BID/ REGISTER CONTRACT | 2007-12-28 | 2008-03-26 | 2007-12-28 | 2008-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405JP75 | JUNIPER PARK - 75TH STREET PLGD Q102-108M | 4 | CONSTRUCTION | 2008-03-27 | 2009-03-26 | 2008-03-27 | 2009-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405JP75 | JUNIPER PARK - 75TH STREET PLGD Q102-108M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2009-03-27 | 2010-03-26 | 2009-03-27 | 2024-03-29
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405JPSS | Juniper Valley Park Spray Shower R/C Q102-117M | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405JPSS | Juniper Valley Park Spray Shower R/C Q102-117M | 2 | DESIGN | 2016-12-28 | 2018-03-22 | 2016-12-28 | 2017-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405JPSS | Juniper Valley Park Spray Shower R/C Q102-117M | 3 | BID/ REGISTER CONTRACT | 2018-03-23 | 2018-12-17 | 2017-12-28 | 2018-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405JPSS | Juniper Valley Park Spray Shower R/C Q102-117M | 4 | CONSTRUCTION | 2018-12-18 | 2020-12-16 | 2018-09-24 | 2019-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405JPSS | Juniper Valley Park Spray Shower R/C Q102-117M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-12-17 | 2021-12-16 | 2019-09-24 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405JPTK | Juniper Valley Park Track & Syn. Turf Field R/C Q102-118M | 1 | DEVELOP SCOPE | 2014-07-01 | 2014-09-28 | 2014-07-01 | 2014-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405JPTK | Juniper Valley Park Track & Syn. Turf Field R/C Q102-118M | 2 | DESIGN | 2014-09-29 | 2014-12-27 | 2014-09-29 | 2014-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405JPTK | Juniper Valley Park Track & Syn. Turf Field R/C Q102-118M | 3 | BID/ REGISTER CONTRACT | 2014-12-28 | 2015-03-27 | 2014-12-28 | 2015-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405JPTK | Juniper Valley Park Track & Syn. Turf Field R/C Q102-118M | 4 | CONSTRUCTION | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2016-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405JPTK | Juniper Valley Park Track & Syn. Turf Field R/C Q102-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2022-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405JVBB | Juniper Valley Park Baseball Fields | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405JVBB | Juniper Valley Park Baseball Fields | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405JVBB | Juniper Valley Park Baseball Fields | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405JVBB | Juniper Valley Park Baseball Fields | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405JVBB | Juniper Valley Park Baseball Fields | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405JVBC | JUNIPER BOCCI COURT Q102-111M | 1 | DEVELOP SCOPE | 2010-07-01 | 2010-09-28 | 2010-07-01 | 2010-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405JVBC | JUNIPER BOCCI COURT Q102-111M | 2 | DESIGN | 2010-09-29 | 2010-12-27 | 2010-09-29 | 2010-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405JVBC | JUNIPER BOCCI COURT Q102-111M | 3 | BID/ REGISTER CONTRACT | 2010-12-28 | 2011-03-27 | 2010-12-28 | 2011-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405JVBC | JUNIPER BOCCI COURT Q102-111M | 4 | CONSTRUCTION | 2011-03-28 | 2012-03-26 | 2011-03-28 | 2012-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405JVBC | JUNIPER BOCCI COURT Q102-111M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-03-27 | 2013-03-26 | 2012-03-27 | 2015-09-30
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405MPST | Frank Principe Park (Maurice Pk) Synthetic Fields Q131-115M | 1 | DEVELOP SCOPE | 2006-07-01 | 2006-09-28 | 2006-07-01 | 2006-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405MPST | Frank Principe Park (Maurice Pk) Synthetic Fields Q131-115M | 2 | DESIGN | 2006-09-29 | 2006-12-27 | 2006-09-29 | 2006-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405MPST | Frank Principe Park (Maurice Pk) Synthetic Fields Q131-115M | 3 | BID/ REGISTER CONTRACT | 2006-12-28 | 2007-03-27 | 2006-12-28 | 2007-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405MPST | Frank Principe Park (Maurice Pk) Synthetic Fields Q131-115M | 4 | CONSTRUCTION | 2007-03-28 | 2008-03-26 | 2007-03-28 | 2008-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405MPST | Frank Principe Park (Maurice Pk) Synthetic Fields Q131-115M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-27 | 2009-03-26 | 2008-03-27 | 2022-05-31
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405RRGH | Ridgewood Reservoir Gatehouse Rehab | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405RRGH | Ridgewood Reservoir Gatehouse Rehab | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405RRGH | Ridgewood Reservoir Gatehouse Rehab | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405RRGH | Ridgewood Reservoir Gatehouse Rehab | 4 | CONSTRUCTION | 2019-09-24 | 2021-03-21 | 2019-09-24 | 2021-03-21
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405RRGH | Ridgewood Reservoir Gatehouse Rehab | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-22 | 2022-03-21 | 2021-03-22 | 2023-03-21
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405RRIV | Ridgewood Reservoir Invasive Removals | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405RRIV | Ridgewood Reservoir Invasive Removals | 2 | DESIGN | 2017-12-28 | 2018-09-23 | 2017-12-28 | 2018-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405RRIV | Ridgewood Reservoir Invasive Removals | 3 | BID/ REGISTER CONTRACT | 2018-09-24 | 2019-06-20 | 2018-09-24 | 2019-06-20
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405RRIV | Ridgewood Reservoir Invasive Removals | 4 | CONSTRUCTION | 2019-06-21 | 2021-12-16 | 2019-06-21 | 2021-12-16
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405RRIV | Ridgewood Reservoir Invasive Removals | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-12-17 | 2023-12-16 | 2021-12-17 | 2023-12-16
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405STR2 | Starr Playground R/C Phase II Q291-120M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2013-07-01 | 2013-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405STR2 | Starr Playground R/C Phase II Q291-120M | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2013-12-28 | 2014-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405STR2 | Starr Playground R/C Phase II Q291-120M | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2014-12-28 | 2015-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405STR2 | Starr Playground R/C Phase II Q291-120M | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2015-09-24 | 2016-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405STR2 | Starr Playground R/C Phase II Q291-120M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2016-09-23 | 2025-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405STRR | Starr Playground MPPA R/C Q291-118M | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405STRR | Starr Playground MPPA R/C Q291-118M | 2 | DESIGN | 2016-12-28 | 2018-03-22 | 2016-12-28 | 2017-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405STRR | Starr Playground MPPA R/C Q291-118M | 3 | BID/ REGISTER CONTRACT | 2018-03-23 | 2018-12-17 | 2017-12-28 | 2018-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405STRR | Starr Playground MPPA R/C Q291-118M | 4 | CONSTRUCTION | 2018-12-18 | 2020-12-16 | 2018-09-24 | 2019-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405STRR | Starr Playground MPPA R/C Q291-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-12-17 | 2021-12-16 | 2019-09-24 | 2020-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405STRR | Starr Playground MPPA R/C Q291-118M | 6 | DEVELOP SCOPE | 2020-12-17 | 2021-12-16 | 2020-09-23 | 2021-03-21
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405STRR | Starr Playground MPPA R/C Q291-118M | 7 | DESIGN | 2020-12-17 | 2021-12-16 | 2021-03-22 | 2023-03-21
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405STRR | Starr Playground MPPA R/C Q291-118M | 8 | BID/ REGISTER CONTRACT | 2020-12-17 | 2021-12-16 | 2023-03-22 | 2023-12-16
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405STRR | Starr Playground MPPA R/C Q291-118M | 9 | CONSTRUCTION | 2020-12-17 | 2021-12-16 | 2023-12-17 | 2024-12-15
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405STRR | Starr Playground MPPA R/C Q291-118M | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-12-17 | 2021-12-16 | 2024-12-16 | 2025-12-15
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-406AUST | AUSTIN STREET PLAYGROUND REHAB Q304-103M | 1 | DEVELOP SCOPE | 2001-07-26 | 2001-10-27 | 2001-07-26 | 2001-10-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-406AUST | AUSTIN STREET PLAYGROUND REHAB Q304-103M | 2 | DESIGN | 2003-07-01 | 2003-10-01 | 2003-07-01 | 2003-10-01
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-406AUST | AUSTIN STREET PLAYGROUND REHAB Q304-103M | 3 | BID/ REGISTER CONTRACT | 2003-12-01 | 2004-03-01 | 2003-12-01 | 2004-03-01
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-406AUST | AUSTIN STREET PLAYGROUND REHAB Q304-103M | 4 | CONSTRUCTION | 2004-03-02 | 2005-03-01 | 2004-03-02 | 2005-03-01
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-406AUST | AUSTIN STREET PLAYGROUND REHAB Q304-103M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2005-03-02 | 2006-03-01 | 2005-03-02 | 2006-03-01
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-406GCPK | GRAND CENTRAL PARKWAY LANDSCAPING Q084-106M | 1 | DEVELOP SCOPE | 2007-06-01 | 2007-08-29 | 2007-06-01 | 2009-12-01
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-406GCPK | GRAND CENTRAL PARKWAY LANDSCAPING Q084-106M | 2 | DESIGN | 2007-08-30 | 2007-11-27 | 2009-07-29 | 2009-09-29
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-406GCPK | GRAND CENTRAL PARKWAY LANDSCAPING Q084-106M | 3 | BID/ REGISTER CONTRACT | 2007-11-28 | 2008-02-25 | 2009-09-30 | 2009-09-29
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-406GCPK | GRAND CENTRAL PARKWAY LANDSCAPING Q084-106M | 4 | CONSTRUCTION | 2008-02-26 | 2009-02-24 | 2009-09-30 | 2010-12-02
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-406GCPK | GRAND CENTRAL PARKWAY LANDSCAPING Q084-106M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2009-02-25 | 2010-02-24 | 2010-12-03 | 2013-09-10
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-406HHPR | HORACE HARDING PLGD RENOVATIONS | 1 | DEVELOP SCOPE | 2020-07-01 | 2020-12-27 | 2020-07-01 | 2020-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-406HHPR | HORACE HARDING PLGD RENOVATIONS | 2 | DESIGN | 2020-12-28 | 2021-12-27 | 2020-12-28 | 2021-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-406HHPR | HORACE HARDING PLGD RENOVATIONS | 3 | BID/ REGISTER CONTRACT | 2021-12-28 | 2022-09-23 | 2021-12-28 | 2022-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-406HHPR | HORACE HARDING PLGD RENOVATIONS | 4 | CONSTRUCTION | 2022-09-24 | 2023-09-23 | 2022-09-24 | 2023-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-406HHPR | HORACE HARDING PLGD RENOVATIONS | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-24 | 2024-09-22 | 2023-09-24 | 2024-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-406LBA2 | LOST BATTALION HALL GYM FLOOR Q401 | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2017-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-406LBA2 | LOST BATTALION HALL GYM FLOOR Q401 | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2017-09-29 | 2017-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-406LBA2 | LOST BATTALION HALL GYM FLOOR Q401 | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2017-12-28 | 2018-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-406LBA2 | LOST BATTALION HALL GYM FLOOR Q401 | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2018-03-28 | 2019-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-406LBA2 | LOST BATTALION HALL GYM FLOOR Q401 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2019-03-28 | 2020-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-406LBAT | LOST BATTALION HALL RECR CTR - PHASE I & PHASE IV | 1 | DEVELOP SCOPE | 2006-07-01 | 2006-09-28 | 2006-07-01 | 2006-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-406LBAT | LOST BATTALION HALL RECR CTR - PHASE I & PHASE IV | 2 | DESIGN | 2006-09-29 | 2006-12-27 | 2006-09-29 | 2006-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-406LBAT | LOST BATTALION HALL RECR CTR - PHASE I & PHASE IV | 3 | BID/ REGISTER CONTRACT | 2006-12-28 | 2007-03-27 | 2006-12-28 | 2007-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-406LBAT | LOST BATTALION HALL RECR CTR - PHASE I & PHASE IV | 4 | CONSTRUCTION | 2007-03-28 | 2008-03-26 | 2007-03-28 | 2008-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-406LBAT | LOST BATTALION HALL RECR CTR - PHASE I & PHASE IV | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-27 | 2009-03-26 | 2008-03-27 | 2009-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-406MCDO | GERALD MACDONALD PARK RECONSTRUCTION Q207-103M | 1 | DEVELOP SCOPE | 2002-07-01 | 2002-12-05 | 2002-07-01 | 2002-12-05
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-406MCDO | GERALD MACDONALD PARK RECONSTRUCTION Q207-103M | 2 | DESIGN | 2003-06-01 | 2003-09-01 | 2003-06-01 | 2003-09-01
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-406MCDO | GERALD MACDONALD PARK RECONSTRUCTION Q207-103M | 3 | BID/ REGISTER CONTRACT | 2003-11-01 | 2004-02-01 | 2003-11-01 | 2004-02-01
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-406MCDO | GERALD MACDONALD PARK RECONSTRUCTION Q207-103M | 4 | CONSTRUCTION | 2004-02-02 | 2005-02-01 | 2004-02-02 | 2005-02-01
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-406MCDO | GERALD MACDONALD PARK RECONSTRUCTION Q207-103M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2005-02-02 | 2006-02-01 | 2005-02-02 | 2006-02-01
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-406PG62 | Playground Sixty Two R/C | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2015-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-406PG62 | Playground Sixty Two R/C | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2015-09-29 | 2015-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-406PG62 | Playground Sixty Two R/C | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2015-12-28 | 2016-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-406PG62 | Playground Sixty Two R/C | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-406PG62 | Playground Sixty Two R/C | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2017-03-27 | 2025-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-406YPFN | Yellowstone Park Fencing Pt. 1 R/C 68th Avenue Q425-118M | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-406YPFN | Yellowstone Park Fencing Pt. 1 R/C 68th Avenue Q425-118M | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-406YPFN | Yellowstone Park Fencing Pt. 1 R/C 68th Avenue Q425-118M | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-406YPFN | Yellowstone Park Fencing Pt. 1 R/C 68th Avenue Q425-118M | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-406YPFN | Yellowstone Park Fencing Pt. 1 R/C 68th Avenue Q425-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407BAYM | Bayside Marina Electrical Update Q135-115M | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407BAYM | Bayside Marina Electrical Update Q135-115M | 2 | DESIGN | 2016-12-28 | 2018-12-27 | 2016-12-28 | 2018-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407BAYM | Bayside Marina Electrical Update Q135-115M | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407BAYM | Bayside Marina Electrical Update Q135-115M | 4 | CONSTRUCTION | 2019-09-24 | 2021-09-22 | 2019-09-24 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407BAYM | Bayside Marina Electrical Update Q135-115M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407BLND | Bland Playground Lighting (Q326-120M) | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407BLND | Bland Playground Lighting (Q326-120M) | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407BLND | Bland Playground Lighting (Q326-120M) | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407BLND | Bland Playground Lighting (Q326-120M) | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407BLND | Bland Playground Lighting (Q326-120M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2024-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407BPFF | BOWNE PK POND R/C Q006-215MA | 1 | DEVELOP SCOPE | 2014-07-01 | 2014-09-28 | 2014-07-01 | 2014-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407BPFF | BOWNE PK POND R/C Q006-215MA | 2 | DESIGN | 2014-09-29 | 2014-12-27 | 2014-09-29 | 2014-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407BPFF | BOWNE PK POND R/C Q006-215MA | 3 | BID/ REGISTER CONTRACT | 2014-12-28 | 2015-03-27 | 2014-12-28 | 2015-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407BPFF | BOWNE PK POND R/C Q006-215MA | 4 | CONSTRUCTION | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2016-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407BPFF | BOWNE PK POND R/C Q006-215MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2022-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407BTPL | Bay Terrace Playground R/C Q399-118M | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407BTPL | Bay Terrace Playground R/C Q399-118M | 2 | DESIGN | 2016-12-28 | 2018-03-22 | 2016-12-28 | 2018-03-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407BTPL | Bay Terrace Playground R/C Q399-118M | 3 | BID/ REGISTER CONTRACT | 2018-03-23 | 2018-12-17 | 2018-03-23 | 2018-12-17
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407BTPL | Bay Terrace Playground R/C Q399-118M | 4 | CONSTRUCTION | 2018-12-18 | 2020-12-16 | 2018-12-18 | 2020-12-16
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407BTPL | Bay Terrace Playground R/C Q399-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-12-17 | 2021-12-16 | 2020-12-17 | 2021-12-16
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407BWPK | Bowne Park Bocce Court Renovations | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407BWPK | Bowne Park Bocce Court Renovations | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407BWPK | Bowne Park Bocce Court Renovations | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407BWPK | Bowne Park Bocce Court Renovations | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407BWPK | Bowne Park Bocce Court Renovations | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407CPSC | College Point Fields Cons. of a Football Field Q476-117M | 1 | DEVELOP SCOPE | 2010-07-01 | 2010-09-28 | 2010-07-01 | 2010-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407CPSC | College Point Fields Cons. of a Football Field Q476-117M | 2 | DESIGN | 2010-09-29 | 2010-12-27 | 2010-09-29 | 2010-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407CPSC | College Point Fields Cons. of a Football Field Q476-117M | 3 | BID/ REGISTER CONTRACT | 2010-12-28 | 2011-03-27 | 2010-12-28 | 2011-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407CPSC | College Point Fields Cons. of a Football Field Q476-117M | 4 | CONSTRUCTION | 2011-03-28 | 2012-03-26 | 2011-03-28 | 2012-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407CPSC | College Point Fields Cons. of a Football Field Q476-117M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-03-27 | 2013-03-26 | 2012-03-27 | 2021-12-31
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407FGP2 | Frank Golden Pk - R/C of Athletic Fields Phase II Q445-118M | 1 | DEVELOP SCOPE | 2014-07-01 | 2014-09-28 | 2014-07-01 | 2014-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407FGP2 | Frank Golden Pk - R/C of Athletic Fields Phase II Q445-118M | 2 | DESIGN | 2014-09-29 | 2014-12-27 | 2014-09-29 | 2014-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407FGP2 | Frank Golden Pk - R/C of Athletic Fields Phase II Q445-118M | 3 | BID/ REGISTER CONTRACT | 2014-12-28 | 2015-03-27 | 2014-12-28 | 2015-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407FGP2 | Frank Golden Pk - R/C of Athletic Fields Phase II Q445-118M | 4 | CONSTRUCTION | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2016-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407FGP2 | Frank Golden Pk - R/C of Athletic Fields Phase II Q445-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2021-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407FLPT | Francis Lewis Park Pathway and Entrance Way Improvements | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407FLPT | Francis Lewis Park Pathway and Entrance Way Improvements | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407FLPT | Francis Lewis Park Pathway and Entrance Way Improvements | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407FLPT | Francis Lewis Park Pathway and Entrance Way Improvements | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407FLPT | Francis Lewis Park Pathway and Entrance Way Improvements | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407MAPL | Maple Playground R/C Q211-117M | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2015-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407MAPL | Maple Playground R/C Q211-117M | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2015-09-29 | 2015-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407MAPL | Maple Playground R/C Q211-117M | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2015-12-28 | 2016-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407MAPL | Maple Playground R/C Q211-117M | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407MAPL | Maple Playground R/C Q211-117M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2017-03-27 | 2023-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407MART | MARTINS FIELD PLAYGROUND RC Q017-104M | 2 | DESIGN | 2003-12-15 | 2004-04-22 | 2003-12-15 | 2004-04-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407MART | MARTINS FIELD PLAYGROUND RC Q017-104M | 3 | BID/ REGISTER CONTRACT | 2004-05-14 | 2004-07-20 | 2004-05-14 | 2004-07-20
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407MART | MARTINS FIELD PLAYGROUND RC Q017-104M | 4 | CONSTRUCTION | 2004-07-21 | 2005-07-20 | 2004-07-21 | 2005-07-20
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407MART | MARTINS FIELD PLAYGROUND RC Q017-104M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2005-07-21 | 2006-07-20 | 2005-07-21 | 2006-07-20
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407MCN4 | Herman MacNeil Park Entrance and Pathways | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407MCN4 | Herman MacNeil Park Entrance and Pathways | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407MCN4 | Herman MacNeil Park Entrance and Pathways | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407MCN4 | Herman MacNeil Park Entrance and Pathways | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407MCN4 | Herman MacNeil Park Entrance and Pathways | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407MCNS | MacNeil Park Steps Construction | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407MCNS | MacNeil Park Steps Construction | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407MCNS | MacNeil Park Steps Construction | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407MCNS | MacNeil Park Steps Construction | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407MCNS | MacNeil Park Steps Construction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407MFL2 | Olde Towne of Flushing Burial Ground Monument Cons Q017-118M | 1 | DEVELOP SCOPE | 2010-07-01 | 2010-09-28 | 2010-07-01 | 2010-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407MFL2 | Olde Towne of Flushing Burial Ground Monument Cons Q017-118M | 2 | DESIGN | 2010-09-29 | 2010-12-27 | 2010-09-29 | 2010-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407MFL2 | Olde Towne of Flushing Burial Ground Monument Cons Q017-118M | 3 | BID/ REGISTER CONTRACT | 2010-12-28 | 2011-03-27 | 2010-12-28 | 2011-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407MFL2 | Olde Towne of Flushing Burial Ground Monument Cons Q017-118M | 4 | CONSTRUCTION | 2011-03-28 | 2012-03-26 | 2011-03-28 | 2012-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407MFL2 | Olde Towne of Flushing Burial Ground Monument Cons Q017-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-03-27 | 2013-03-26 | 2012-03-27 | 2021-12-31
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407MNPW | MACNEIL PARK WATERFRONT REPAIRS | 1 | DEVELOP SCOPE | 2020-07-01 | 2020-12-27 | 2020-07-01 | 2020-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407MNPW | MACNEIL PARK WATERFRONT REPAIRS | 2 | DESIGN | 2020-12-28 | 2021-12-27 | 2020-12-28 | 2021-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407MNPW | MACNEIL PARK WATERFRONT REPAIRS | 3 | BID/ REGISTER CONTRACT | 2021-12-28 | 2022-09-23 | 2021-12-28 | 2022-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407MNPW | MACNEIL PARK WATERFRONT REPAIRS | 4 | CONSTRUCTION | 2022-09-24 | 2023-09-23 | 2022-09-24 | 2023-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407MNPW | MACNEIL PARK WATERFRONT REPAIRS | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-24 | 2024-09-22 | 2023-09-24 | 2024-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407MPSW | MACNEIL PARK SEAWALL Q009-114MA | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2013-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407MPSW | MACNEIL PARK SEAWALL Q009-114MA | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2013-09-29 | 2013-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407MPSW | MACNEIL PARK SEAWALL Q009-114MA | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2013-12-28 | 2014-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407MPSW | MACNEIL PARK SEAWALL Q009-114MA | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2014-03-28 | 2015-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407MPSW | MACNEIL PARK SEAWALL Q009-114MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2022-09-30
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407SITE | FT. TOTTEN SITE (BATTERY) PREPARATION Q458-101M | 3 | BID/ REGISTER CONTRACT | 2006-12-28 | 2007-03-27 | 2006-12-28 | 2007-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407SITE | FT. TOTTEN SITE (BATTERY) PREPARATION Q458-101M | 4 | CONSTRUCTION | 2007-03-28 | 2008-03-26 | 2007-03-28 | 2008-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407SITE | FT. TOTTEN SITE (BATTERY) PREPARATION Q458-101M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-27 | 2009-03-26 | 2008-03-27 | 2009-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407VELO | KISENNA VALLEY PK RC VELODROME | 1 | DEVELOP SCOPE | 2014-07-01 | 2014-09-28 | 2014-07-01 | 2014-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407VELO | KISENNA VALLEY PK RC VELODROME | 2 | DESIGN | 2014-09-29 | 2014-12-27 | 2014-09-29 | 2014-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407VELO | KISENNA VALLEY PK RC VELODROME | 3 | BID/ REGISTER CONTRACT | 2014-12-28 | 2015-03-27 | 2014-12-28 | 2015-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407VELO | KISENNA VALLEY PK RC VELODROME | 4 | CONSTRUCTION | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2016-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407VELO | KISENNA VALLEY PK RC VELODROME | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2025-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408BRIA | Briarwood Plgd and Phil Rizzuto Park R/C QG-116MA | 1 | DEVELOP SCOPE | 2014-07-01 | 2014-09-28 | 2014-07-01 | 2014-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408BRIA | Briarwood Plgd and Phil Rizzuto Park R/C QG-116MA | 2 | DESIGN | 2014-09-29 | 2014-12-27 | 2014-09-29 | 2014-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408BRIA | Briarwood Plgd and Phil Rizzuto Park R/C QG-116MA | 3 | BID/ REGISTER CONTRACT | 2014-12-28 | 2015-03-27 | 2014-12-28 | 2015-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408BRIA | Briarwood Plgd and Phil Rizzuto Park R/C QG-116MA | 4 | CONSTRUCTION | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2016-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408BRIA | Briarwood Plgd and Phil Rizzuto Park R/C QG-116MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2022-03-03
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408CPB2 | CUNNINGHAM PARK BALLFIELDS 2-4 UPGRADES Q021-109MA | 1 | DEVELOP SCOPE | 2008-07-01 | 2008-09-28 | 2008-07-01 | 2009-12-01
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408CPB2 | CUNNINGHAM PARK BALLFIELDS 2-4 UPGRADES Q021-109MA | 2 | DESIGN | 2008-09-29 | 2008-12-27 | 2009-10-27 | 2009-11-13
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408CPB2 | CUNNINGHAM PARK BALLFIELDS 2-4 UPGRADES Q021-109MA | 3 | BID/ REGISTER CONTRACT | 2008-12-28 | 2009-03-27 | 2010-04-20 | 2010-07-20
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408CPB2 | CUNNINGHAM PARK BALLFIELDS 2-4 UPGRADES Q021-109MA | 4 | CONSTRUCTION | 2009-03-28 | 2010-03-27 | 2010-07-21 | 2011-07-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408CPB2 | CUNNINGHAM PARK BALLFIELDS 2-4 UPGRADES Q021-109MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2010-03-28 | 2011-03-27 | 2011-07-23 | 2014-12-31
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408CPBF | CUNNINGHAM PARK BALLFIELDS (#1 & #5) Q021-108M | 1 | DEVELOP SCOPE | 2006-07-01 | 2006-09-28 | 2006-07-01 | 2009-01-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408CPBF | CUNNINGHAM PARK BALLFIELDS (#1 & #5) Q021-108M | 2 | DESIGN | 2006-09-29 | 2006-12-27 | 2009-01-24 | 2009-01-29
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408CPBF | CUNNINGHAM PARK BALLFIELDS (#1 & #5) Q021-108M | 3 | BID/ REGISTER CONTRACT | 2006-12-28 | 2007-03-27 | 2009-03-27 | 2009-07-13
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408CPBF | CUNNINGHAM PARK BALLFIELDS (#1 & #5) Q021-108M | 4 | CONSTRUCTION | 2007-03-28 | 2008-03-26 | 2010-02-22 | 2010-11-05
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408CPBF | CUNNINGHAM PARK BALLFIELDS (#1 & #5) Q021-108M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-27 | 2009-03-26 | 2010-11-06 | 2011-11-07
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408CPGA | Cunningham Park Garage Space Conversion | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408CPGA | Cunningham Park Garage Space Conversion | 2 | DESIGN | 2016-12-28 | 2018-12-27 | 2016-12-28 | 2018-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408CPGA | Cunningham Park Garage Space Conversion | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408CPGA | Cunningham Park Garage Space Conversion | 4 | CONSTRUCTION | 2019-09-24 | 2021-09-22 | 2019-09-24 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408CPGA | Cunningham Park Garage Space Conversion | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408CSTA | CUNNINGHAM PARK TENNIS HOUSE RC Q021-102M/402M | 1 | DEVELOP SCOPE | 2001-07-01 | 2001-12-31 | 2001-07-01 | 2001-12-31
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408CSTA | CUNNINGHAM PARK TENNIS HOUSE RC Q021-102M/402M | 2 | DESIGN | 2002-05-14 | 2004-03-29 | 2002-05-14 | 2004-03-29
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408CSTA | CUNNINGHAM PARK TENNIS HOUSE RC Q021-102M/402M | 3 | BID/ REGISTER CONTRACT | 2004-06-15 | 2004-09-30 | 2004-06-15 | 2004-09-30
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408CSTA | CUNNINGHAM PARK TENNIS HOUSE RC Q021-102M/402M | 4 | CONSTRUCTION | 2004-11-01 | 2005-10-31 | 2004-11-01 | 2005-10-31
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408CSTA | CUNNINGHAM PARK TENNIS HOUSE RC Q021-102M/402M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2005-11-01 | 2006-10-31 | 2005-11-01 | 2006-10-31
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408HOV2 | Hoover Playground | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2015-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408HOV2 | Hoover Playground | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2015-09-29 | 2015-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408HOV2 | Hoover Playground | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2015-12-28 | 2016-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408HOV2 | Hoover Playground | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408HOV2 | Hoover Playground | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2017-03-27 | 2025-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408MLDY | Site for Mother Language Day in Captain Tilly Park | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408MLDY | Site for Mother Language Day in Captain Tilly Park | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408MLDY | Site for Mother Language Day in Captain Tilly Park | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408MLDY | Site for Mother Language Day in Captain Tilly Park | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408MLDY | Site for Mother Language Day in Captain Tilly Park | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2025-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408TILL | CAPTAIN TILLEY PK-RENOVATIONS OF LANDSCAPE Q052-112M | 1 | DEVELOP SCOPE | 2007-07-01 | 2007-09-28 | 2007-07-01 | 2007-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408TILL | CAPTAIN TILLEY PK-RENOVATIONS OF LANDSCAPE Q052-112M | 2 | DESIGN | 2007-09-29 | 2007-12-27 | 2007-09-29 | 2007-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408TILL | CAPTAIN TILLEY PK-RENOVATIONS OF LANDSCAPE Q052-112M | 3 | BID/ REGISTER CONTRACT | 2007-12-28 | 2008-03-26 | 2007-12-28 | 2008-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408TILL | CAPTAIN TILLEY PK-RENOVATIONS OF LANDSCAPE Q052-112M | 4 | CONSTRUCTION | 2008-03-27 | 2009-03-26 | 2008-03-27 | 2009-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408TILL | CAPTAIN TILLEY PK-RENOVATIONS OF LANDSCAPE Q052-112M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2009-03-27 | 2010-03-26 | 2009-03-27 | 2016-11-30
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408VAN2 | Vanderbilt Motor Parkway Repaving Phase II QG-719M | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408VAN2 | Vanderbilt Motor Parkway Repaving Phase II QG-719M | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408VAN2 | Vanderbilt Motor Parkway Repaving Phase II QG-719M | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408VAN2 | Vanderbilt Motor Parkway Repaving Phase II QG-719M | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408VAN2 | Vanderbilt Motor Parkway Repaving Phase II QG-719M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408VAND | Vanderbilt Motor Parkway Repaving QG-718M | 1 | DEVELOP SCOPE | 2017-04-30 | 2017-10-26 | 2017-04-30 | 2017-10-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408VAND | Vanderbilt Motor Parkway Repaving QG-718M | 2 | DESIGN | 2017-10-27 | 2018-10-26 | 2017-10-27 | 2018-10-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408VAND | Vanderbilt Motor Parkway Repaving QG-718M | 3 | BID/ REGISTER CONTRACT | 2018-10-27 | 2019-07-23 | 2018-10-27 | 2019-07-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408VAND | Vanderbilt Motor Parkway Repaving QG-718M | 4 | CONSTRUCTION | 2019-07-24 | 2020-07-22 | 2019-07-24 | 2020-07-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408VAND | Vanderbilt Motor Parkway Repaving QG-718M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-07-23 | 2021-07-22 | 2020-07-23 | 2021-07-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-409DEMO | Forest Park Towers Demolition | 1 | DEVELOP SCOPE | 2020-07-01 | 2020-12-27 | 2020-07-01 | 2020-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-409DEMO | Forest Park Towers Demolition | 2 | DESIGN | 2020-12-28 | 2021-12-27 | 2020-12-28 | 2021-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-409DEMO | Forest Park Towers Demolition | 3 | BID/ REGISTER CONTRACT | 2021-12-28 | 2022-09-23 | 2021-12-28 | 2022-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-409DEMO | Forest Park Towers Demolition | 4 | CONSTRUCTION | 2022-09-24 | 2023-09-23 | 2022-09-24 | 2023-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-409DEMO | Forest Park Towers Demolition | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-24 | 2024-09-22 | 2023-09-24 | 2024-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-409EQTY | Equity Park Playground Upgrades | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2013-07-01 | 2013-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-409EQTY | Equity Park Playground Upgrades | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2013-12-28 | 2014-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-409EQTY | Equity Park Playground Upgrades | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2014-12-28 | 2015-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-409EQTY | Equity Park Playground Upgrades | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2015-09-24 | 2016-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-409EQTY | Equity Park Playground Upgrades | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2016-09-23 | 2024-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-409FPAP | Forest Park Asphalt Pathways Improvements | 1 | DEVELOP SCOPE | 2020-07-01 | 2020-12-27 | 2020-07-01 | 2020-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-409FPAP | Forest Park Asphalt Pathways Improvements | 2 | DESIGN | 2020-12-28 | 2021-12-27 | 2020-12-28 | 2021-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-409FPAP | Forest Park Asphalt Pathways Improvements | 3 | BID/ REGISTER CONTRACT | 2021-12-28 | 2022-09-23 | 2021-12-28 | 2022-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-409FPAP | Forest Park Asphalt Pathways Improvements | 4 | CONSTRUCTION | 2022-09-24 | 2023-09-23 | 2022-09-24 | 2023-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-409FPAP | Forest Park Asphalt Pathways Improvements | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-24 | 2024-09-22 | 2023-09-24 | 2024-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-409FPB3 | FOREST PARK BANDSHELL SEATING AREA Q015-111M | 3 | BID/ REGISTER CONTRACT | 2010-12-28 | 2011-03-27 | 2010-12-28 | 2011-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-409FPB3 | FOREST PARK BANDSHELL SEATING AREA Q015-111M | 4 | CONSTRUCTION | 2011-03-28 | 2012-03-26 | 2011-03-28 | 2012-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-409FPB3 | FOREST PARK BANDSHELL SEATING AREA Q015-111M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-03-27 | 2013-03-26 | 2012-03-27 | 2014-04-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-409FPG3 | FOREST PARK GREENHOUSES Q015-215M | 1 | DEVELOP SCOPE | 2012-12-01 | 2013-02-28 | 2012-12-01 | 2013-02-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-409FPG3 | FOREST PARK GREENHOUSES Q015-215M | 2 | DESIGN | 2013-03-01 | 2013-05-29 | 2013-03-01 | 2013-05-29
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-409FPG3 | FOREST PARK GREENHOUSES Q015-215M | 3 | BID/ REGISTER CONTRACT | 2013-05-30 | 2013-08-27 | 2013-05-30 | 2013-08-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-409FPG3 | FOREST PARK GREENHOUSES Q015-215M | 4 | CONSTRUCTION | 2013-08-28 | 2014-08-27 | 2013-08-28 | 2014-08-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-409FPG3 | FOREST PARK GREENHOUSES Q015-215M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-08-28 | 2015-08-27 | 2014-08-28 | 2015-08-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-409FPKO | FOREST PK. OVERLOOK - SANITARY HOUSE SEWER Q015-103M | 4 | CONSTRUCTION | 2003-09-15 | 2003-12-30 | 2003-09-15 | 2003-12-30
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-409FPKO | FOREST PK. OVERLOOK - SANITARY HOUSE SEWER Q015-103M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2003-12-31 | 2004-12-29 | 2003-12-31 | 2004-12-29
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-409FPP2 | Forest Park Pathways | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2015-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-409FPP2 | Forest Park Pathways | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2015-09-29 | 2015-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-409FPP2 | Forest Park Pathways | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2015-12-28 | 2016-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-409FPP2 | Forest Park Pathways | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-409FPP2 | Forest Park Pathways | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2017-03-27 | 2018-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-409MARD | Glendale Entrance to Forest Park Q015-217MA | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2015-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-409MARD | Glendale Entrance to Forest Park Q015-217MA | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2015-09-29 | 2015-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-409MARD | Glendale Entrance to Forest Park Q015-217MA | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2015-12-28 | 2016-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-409MARD | Glendale Entrance to Forest Park Q015-217MA | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-409MARD | Glendale Entrance to Forest Park Q015-217MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2017-03-27 | 2023-04-30
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-409SOB2 | SOBELSOHN C/S | 1 | DEVELOP SCOPE | 2014-07-01 | 2014-09-28 | 2014-07-01 | 2017-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-409SOB2 | SOBELSOHN C/S | 2 | DESIGN | 2014-09-29 | 2014-12-27 | 2017-09-29 | 2017-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-409SOB2 | SOBELSOHN C/S | 3 | BID/ REGISTER CONTRACT | 2014-12-28 | 2015-03-27 | 2017-12-28 | 2018-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-409SOB2 | SOBELSOHN C/S | 4 | CONSTRUCTION | 2015-03-28 | 2016-03-26 | 2018-03-28 | 2019-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-409SOB2 | SOBELSOHN C/S | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-27 | 2017-03-26 | 2019-03-28 | 2020-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-410ALST | Al Stabile Playground Renovation | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-410ALST | Al Stabile Playground Renovation | 2 | DESIGN | 2018-12-28 | 2020-12-26 | 2018-12-28 | 2020-12-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-410ALST | Al Stabile Playground Renovation | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-410ALST | Al Stabile Playground Renovation | 4 | CONSTRUCTION | 2021-09-23 | 2023-09-22 | 2021-09-23 | 2023-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-410ALST | Al Stabile Playground Renovation | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-23 | 2024-09-21 | 2023-09-23 | 2024-09-21
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-410BYRN | Edward Byrne Park Playground C/S X092-118M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-410BYRN | Edward Byrne Park Playground C/S X092-118M | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-410BYRN | Edward Byrne Park Playground C/S X092-118M | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-410BYRN | Edward Byrne Park Playground C/S X092-118M | 4 | CONSTRUCTION | 2019-09-24 | 2021-03-21 | 2019-09-24 | 2021-03-21
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-410BYRN | Edward Byrne Park Playground C/S X092-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-22 | 2022-03-21 | 2021-03-22 | 2022-03-21
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-410FJMC | LT. FRANK MCCONNELL MEMORIAL PK Q217-103M | 2 | DESIGN | 2003-07-30 | 2003-09-01 | 2003-07-30 | 2003-09-01
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-410FJMC | LT. FRANK MCCONNELL MEMORIAL PK Q217-103M | 3 | BID/ REGISTER CONTRACT | 2003-11-01 | 2004-02-01 | 2003-11-01 | 2004-02-01
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-410FJMC | LT. FRANK MCCONNELL MEMORIAL PK Q217-103M | 4 | CONSTRUCTION | 2004-04-01 | 2005-03-31 | 2004-04-01 | 2005-03-31
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-410FJMC | LT. FRANK MCCONNELL MEMORIAL PK Q217-103M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2005-04-01 | 2006-03-31 | 2005-04-01 | 2006-03-31
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-410LPKS | SOUTHERN FIELD - SYNTHETIC TURF SOCCER FIELD Q096-104M | 1 | DEVELOP SCOPE | 2003-07-01 | 2003-09-28 | 2003-07-01 | 2003-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-410LPKS | SOUTHERN FIELD - SYNTHETIC TURF SOCCER FIELD Q096-104M | 2 | DESIGN | 2003-09-29 | 2004-01-01 | 2003-09-29 | 2004-01-01
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-410LPKS | SOUTHERN FIELD - SYNTHETIC TURF SOCCER FIELD Q096-104M | 3 | BID/ REGISTER CONTRACT | 2004-03-01 | 2004-06-01 | 2004-03-01 | 2004-06-01
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-410LPKS | SOUTHERN FIELD - SYNTHETIC TURF SOCCER FIELD Q096-104M | 4 | CONSTRUCTION | 2004-08-01 | 2005-08-01 | 2004-08-01 | 2005-08-01
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-410LPKS | SOUTHERN FIELD - SYNTHETIC TURF SOCCER FIELD Q096-104M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2005-08-02 | 2006-08-01 | 2005-08-02 | 2006-08-01
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-410PEBP | Recon of Police Officer Edward O'Byrne Park Q092-119M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-410PEBP | Recon of Police Officer Edward O'Byrne Park Q092-119M | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-410PEBP | Recon of Police Officer Edward O'Byrne Park Q092-119M | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-410PEBP | Recon of Police Officer Edward O'Byrne Park Q092-119M | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-410PEBP | Recon of Police Officer Edward O'Byrne Park Q092-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2023-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-410PONI | P.O. NICHOLAS DEMUTIS PLGD RC Q118-114M | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2013-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-410PONI | P.O. NICHOLAS DEMUTIS PLGD RC Q118-114M | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2013-09-29 | 2013-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-410PONI | P.O. NICHOLAS DEMUTIS PLGD RC Q118-114M | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2013-12-28 | 2014-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-410PONI | P.O. NICHOLAS DEMUTIS PLGD RC Q118-114M | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2014-03-28 | 2015-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-410PONI | P.O. NICHOLAS DEMUTIS PLGD RC Q118-114M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2021-01-31
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-410SCN2 | Harold Schneiderman Playground Upgrades | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-410SCN2 | Harold Schneiderman Playground Upgrades | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-410SCN2 | Harold Schneiderman Playground Upgrades | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-410SCN2 | Harold Schneiderman Playground Upgrades | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-410SCN2 | Harold Schneiderman Playground Upgrades | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2024-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-410SFLD | SOUTHERN FIELDS AT N. CONDUIT AND 118 ST. Q096-108M | 1 | DEVELOP SCOPE | 2007-07-01 | 2007-09-28 | 2007-07-01 | 2007-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-410SFLD | SOUTHERN FIELDS AT N. CONDUIT AND 118 ST. Q096-108M | 2 | DESIGN | 2007-09-29 | 2007-12-27 | 2007-09-29 | 2007-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-410SFLD | SOUTHERN FIELDS AT N. CONDUIT AND 118 ST. Q096-108M | 3 | BID/ REGISTER CONTRACT | 2007-12-28 | 2008-03-26 | 2007-12-28 | 2008-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-410SFLD | SOUTHERN FIELDS AT N. CONDUIT AND 118 ST. Q096-108M | 4 | CONSTRUCTION | 2008-03-27 | 2009-03-26 | 2008-03-27 | 2009-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-410SFLD | SOUTHERN FIELDS AT N. CONDUIT AND 118 ST. Q096-108M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2009-03-27 | 2010-03-26 | 2009-03-27 | 2013-10-31
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-410SFLD | SOUTHERN FIELDS AT N. CONDUIT AND 118 ST. Q096-108M | 6 | DEVELOP SCOPE | 2009-03-27 | 2010-03-26 | 2013-11-01 | 2014-04-29
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-410SFLD | SOUTHERN FIELDS AT N. CONDUIT AND 118 ST. Q096-108M | 7 | DESIGN | 2009-03-27 | 2010-03-26 | 2014-04-30 | 2015-04-29
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-410SFLD | SOUTHERN FIELDS AT N. CONDUIT AND 118 ST. Q096-108M | 8 | BID/ REGISTER CONTRACT | 2009-03-27 | 2010-03-26 | 2015-04-30 | 2016-01-24
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-410SFLD | SOUTHERN FIELDS AT N. CONDUIT AND 118 ST. Q096-108M | 9 | CONSTRUCTION | 2009-03-27 | 2010-03-26 | 2016-01-25 | 2017-01-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-410SFLD | SOUTHERN FIELDS AT N. CONDUIT AND 118 ST. Q096-108M | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2009-03-27 | 2010-03-26 | 2017-01-24 | 2018-01-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-411APE2 | ALLEY POND ENVIRONMENTAL CENTER & CONS. OF ANNEX Q001-110M | 1 | DEVELOP SCOPE | 2006-07-01 | 2006-09-28 | 2006-07-01 | 2013-09-30
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-411APE2 | ALLEY POND ENVIRONMENTAL CENTER & CONS. OF ANNEX Q001-110M | 2 | DESIGN | 2006-09-29 | 2006-12-27 | 2013-10-01 | 2013-12-31
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-411APE2 | ALLEY POND ENVIRONMENTAL CENTER & CONS. OF ANNEX Q001-110M | 3 | BID/ REGISTER CONTRACT | 2006-12-28 | 2007-03-27 | 2014-01-01 | 2017-05-01
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-411APE2 | ALLEY POND ENVIRONMENTAL CENTER & CONS. OF ANNEX Q001-110M | 4 | CONSTRUCTION | 2007-03-28 | 2008-03-26 | 2017-05-02 | 2018-05-01
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-411APE2 | ALLEY POND ENVIRONMENTAL CENTER & CONS. OF ANNEX Q001-110M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-27 | 2009-03-26 | 2018-05-02 | 2019-05-01
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-411APLS | Alley Pond Park Living Shoreline Construction Q135-119M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-411APLS | Alley Pond Park Living Shoreline Construction Q135-119M | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-411APLS | Alley Pond Park Living Shoreline Construction Q135-119M | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-411APLS | Alley Pond Park Living Shoreline Construction Q135-119M | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-411APLS | Alley Pond Park Living Shoreline Construction Q135-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-411AURO | AURORA POND - RESTORATION Q452-100MA | 1 | DEVELOP SCOPE | 2000-07-01 | 2000-09-28 | 2000-07-01 | 2000-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-411AURO | AURORA POND - RESTORATION Q452-100MA | 2 | DESIGN | 2000-09-29 | 2003-04-04 | 2000-09-29 | 2003-04-04
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-411AURO | AURORA POND - RESTORATION Q452-100MA | 3 | BID/ REGISTER CONTRACT | 2002-04-05 | 2003-01-01 | 2002-04-05 | 2003-01-01
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-411AURO | AURORA POND - RESTORATION Q452-100MA | 4 | CONSTRUCTION | 2004-03-01 | 2005-02-28 | 2004-03-01 | 2005-02-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-411AURO | AURORA POND - RESTORATION Q452-100MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2005-03-01 | 2006-02-28 | 2005-03-01 | 2023-02-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-411CDTR | Captain Dermody Triangle- Reconstruction of the triangle | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-411CDTR | Captain Dermody Triangle- Reconstruction of the triangle | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-411CDTR | Captain Dermody Triangle- Reconstruction of the triangle | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-411CDTR | Captain Dermody Triangle- Reconstruction of the triangle | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-411CDTR | Captain Dermody Triangle- Reconstruction of the triangle | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-411OKPT | Oakland Lake Pathways Reconstruction | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-411OKPT | Oakland Lake Pathways Reconstruction | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-411OKPT | Oakland Lake Pathways Reconstruction | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-411OKPT | Oakland Lake Pathways Reconstruction | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-411OKPT | Oakland Lake Pathways Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-411SWP2 | Saul Weprin Playground R/C Q293-118M | 1 | Y | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-411SWP2 | Saul Weprin Playground R/C Q293-118M | 2 | DESIGN | 2016-12-28 | 2018-12-27 | 2016-12-28 | 2018-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-411SWP2 | Saul Weprin Playground R/C Q293-118M | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-411SWP2 | Saul Weprin Playground R/C Q293-118M | 4 | CONSTRUCTION | 2019-09-24 | 2021-09-22 | 2019-09-24 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-411SWP2 | Saul Weprin Playground R/C Q293-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412BAI2 | Baisley Pond Park Track & Field, Syn. Turf R/C Q005-119M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412BAI2 | Baisley Pond Park Track & Field, Syn. Turf R/C Q005-119M | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412BAI2 | Baisley Pond Park Track & Field, Syn. Turf R/C Q005-119M | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412BAI2 | Baisley Pond Park Track & Field, Syn. Turf R/C Q005-119M | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412BAI2 | Baisley Pond Park Track & Field, Syn. Turf R/C Q005-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412BPP3 | BAISLEY POND PARK PHASE III Q005-113M | 1 | DEVELOP SCOPE | 2010-07-01 | 2010-09-28 | 2010-07-01 | 2010-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412BPP3 | BAISLEY POND PARK PHASE III Q005-113M | 2 | DESIGN | 2010-09-29 | 2010-12-27 | 2010-09-29 | 2010-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412BPP3 | BAISLEY POND PARK PHASE III Q005-113M | 3 | BID/ REGISTER CONTRACT | 2010-12-28 | 2011-03-27 | 2010-12-28 | 2011-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412BPP3 | BAISLEY POND PARK PHASE III Q005-113M | 4 | CONSTRUCTION | 2011-03-28 | 2012-03-26 | 2011-03-28 | 2012-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412BPP3 | BAISLEY POND PARK PHASE III Q005-113M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-03-27 | 2013-03-26 | 2012-03-27 | 2023-06-30
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412BPP4 | Athletic Courts Multi-Site QG-216M | 1 | DEVELOP SCOPE | 2014-07-01 | 2014-09-28 | 2015-07-01 | 2015-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412BPP4 | Athletic Courts Multi-Site QG-216M | 2 | DESIGN | 2014-09-29 | 2014-12-27 | 2015-09-29 | 2015-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412BPP4 | Athletic Courts Multi-Site QG-216M | 3 | BID/ REGISTER CONTRACT | 2014-12-28 | 2015-03-27 | 2015-12-28 | 2016-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412BPP4 | Athletic Courts Multi-Site QG-216M | 4 | CONSTRUCTION | 2015-03-28 | 2016-03-26 | 2016-03-27 | 2017-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412BPP4 | Athletic Courts Multi-Site QG-216M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-27 | 2017-03-26 | 2017-03-27 | 2023-08-31
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412DKWP | Detective Keith L Williams Park (Liberty) Basketball Cts | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412DKWP | Detective Keith L Williams Park (Liberty) Basketball Cts | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412DKWP | Detective Keith L Williams Park (Liberty) Basketball Cts | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412DKWP | Detective Keith L Williams Park (Liberty) Basketball Cts | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412DKWP | Detective Keith L Williams Park (Liberty) Basketball Cts | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412DOP2 | DANIEL O'CONNELL PLAYGD. C/S Q106-113M | 1 | DEVELOP SCOPE | 2008-07-01 | 2008-09-28 | 2008-07-01 | 2008-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412DOP2 | DANIEL O'CONNELL PLAYGD. C/S Q106-113M | 2 | DESIGN | 2008-09-29 | 2008-12-27 | 2008-09-29 | 2008-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412DOP2 | DANIEL O'CONNELL PLAYGD. C/S Q106-113M | 3 | BID/ REGISTER CONTRACT | 2008-12-28 | 2009-03-27 | 2008-12-28 | 2009-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412DOP2 | DANIEL O'CONNELL PLAYGD. C/S Q106-113M | 4 | CONSTRUCTION | 2009-03-28 | 2010-03-27 | 2009-03-28 | 2010-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412DOP2 | DANIEL O'CONNELL PLAYGD. C/S Q106-113M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2010-03-28 | 2011-03-27 | 2010-03-28 | 2020-06-20
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412DOP3 | Daniel M. O'Connell Playground Renovation Q106-120M | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412DOP3 | Daniel M. O'Connell Playground Renovation Q106-120M | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412DOP3 | Daniel M. O'Connell Playground Renovation Q106-120M | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412DOP3 | Daniel M. O'Connell Playground Renovation Q106-120M | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412DOP3 | Daniel M. O'Connell Playground Renovation Q106-120M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412HOPG | J.H.S. 192 PLAYGROUND RC Q405-104M | 1 | DEVELOP SCOPE | 2003-07-01 | 2003-09-28 | 2003-07-01 | 2003-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412HOPG | J.H.S. 192 PLAYGROUND RC Q405-104M | 2 | DESIGN | 2003-09-29 | 2004-03-18 | 2003-09-29 | 2004-03-18
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412HOPG | J.H.S. 192 PLAYGROUND RC Q405-104M | 3 | BID/ REGISTER CONTRACT | 2004-05-12 | 2004-08-11 | 2004-05-12 | 2004-08-11
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412HOPG | J.H.S. 192 PLAYGROUND RC Q405-104M | 4 | CONSTRUCTION | 2004-10-01 | 2005-04-30 | 2004-10-01 | 2005-04-30
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412HOPG | J.H.S. 192 PLAYGROUND RC Q405-104M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2005-05-01 | 2006-04-30 | 2005-05-01 | 2006-04-30
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412HVDP | HOWARD VON DOHLEN PLAYGROUND-RENOVATIONS Q105-112M | 1 | DEVELOP SCOPE | 2006-07-01 | 2006-09-28 | 2006-07-01 | 2006-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412HVDP | HOWARD VON DOHLEN PLAYGROUND-RENOVATIONS Q105-112M | 2 | DESIGN | 2006-09-29 | 2006-12-27 | 2006-09-29 | 2006-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412HVDP | HOWARD VON DOHLEN PLAYGROUND-RENOVATIONS Q105-112M | 3 | BID/ REGISTER CONTRACT | 2006-12-28 | 2007-03-27 | 2006-12-28 | 2007-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412HVDP | HOWARD VON DOHLEN PLAYGROUND-RENOVATIONS Q105-112M | 4 | CONSTRUCTION | 2007-03-28 | 2008-03-26 | 2007-03-28 | 2008-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412HVDP | HOWARD VON DOHLEN PLAYGROUND-RENOVATIONS Q105-112M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-27 | 2009-03-26 | 2008-03-27 | 2017-04-30
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412JAMP | Jamaica Playground -- Renovate MPPA | 1 | DEVELOP SCOPE | 2020-07-01 | 2020-12-27 | 2020-07-01 | 2020-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412JAMP | Jamaica Playground -- Renovate MPPA | 2 | DESIGN | 2020-12-28 | 2021-12-27 | 2020-12-28 | 2021-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412JAMP | Jamaica Playground -- Renovate MPPA | 3 | BID/ REGISTER CONTRACT | 2021-12-28 | 2022-09-23 | 2021-12-28 | 2022-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412JAMP | Jamaica Playground -- Renovate MPPA | 4 | CONSTRUCTION | 2022-09-24 | 2023-09-23 | 2022-09-24 | 2023-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412JAMP | Jamaica Playground -- Renovate MPPA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-24 | 2024-09-22 | 2023-09-24 | 2024-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412JMIC | Jamaica Playground R/C Q301-119M | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412JMIC | Jamaica Playground R/C Q301-119M | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412JMIC | Jamaica Playground R/C Q301-119M | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412JMIC | Jamaica Playground R/C Q301-119M | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412JMIC | Jamaica Playground R/C Q301-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412KLWP | Detective Keith Williams Park--Renovate The Synthetic Turf | 1 | DEVELOP SCOPE | 2020-07-01 | 2020-12-27 | 2020-07-01 | 2020-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412KLWP | Detective Keith Williams Park--Renovate The Synthetic Turf | 2 | DESIGN | 2020-12-28 | 2022-06-20 | 2020-12-28 | 2022-06-20
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412KLWP | Detective Keith Williams Park--Renovate The Synthetic Turf | 3 | BID/ REGISTER CONTRACT | 2022-06-21 | 2023-03-17 | 2022-06-21 | 2023-03-17
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412KLWP | Detective Keith Williams Park--Renovate The Synthetic Turf | 4 | CONSTRUCTION | 2023-03-18 | 2024-09-07 | 2023-03-18 | 2024-09-07
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412KLWP | Detective Keith Williams Park--Renovate The Synthetic Turf | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-09-08 | 2025-09-07 | 2024-09-08 | 2025-09-07
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412MBPF | Montebellier Park Field - Playing Field Upgrades | 1 | DEVELOP SCOPE | 2020-07-01 | 2020-12-27 | 2020-07-01 | 2020-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412MBPF | Montebellier Park Field - Playing Field Upgrades | 2 | DESIGN | 2020-12-28 | 2021-12-27 | 2020-12-28 | 2021-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412MBPF | Montebellier Park Field - Playing Field Upgrades | 3 | BID/ REGISTER CONTRACT | 2021-12-28 | 2022-09-23 | 2021-12-28 | 2022-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412MBPF | Montebellier Park Field - Playing Field Upgrades | 4 | CONSTRUCTION | 2022-09-24 | 2023-09-23 | 2022-09-24 | 2023-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412MBPF | Montebellier Park Field - Playing Field Upgrades | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-24 | 2024-09-22 | 2023-09-24 | 2024-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412NAUT | Nautilus Playground R/C Q448-119M | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2015-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412NAUT | Nautilus Playground R/C Q448-119M | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2015-09-29 | 2015-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412NAUT | Nautilus Playground R/C Q448-119M | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2015-12-28 | 2016-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412NAUT | Nautilus Playground R/C Q448-119M | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412NAUT | Nautilus Playground R/C Q448-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2017-03-27 | 2023-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412NOR2 | Norelli-Hargreaves Playground MPPA R/C Q220B-118M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412NOR2 | Norelli-Hargreaves Playground MPPA R/C Q220B-118M | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412NOR2 | Norelli-Hargreaves Playground MPPA R/C Q220B-118M | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412NOR2 | Norelli-Hargreaves Playground MPPA R/C Q220B-118M | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412NOR2 | Norelli-Hargreaves Playground MPPA R/C Q220B-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412NORI | Norelli-Hargreaves Playground R/C Q220-116M | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2015-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412NORI | Norelli-Hargreaves Playground R/C Q220-116M | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2015-09-29 | 2015-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412NORI | Norelli-Hargreaves Playground R/C Q220-116M | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2015-12-28 | 2016-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412NORI | Norelli-Hargreaves Playground R/C Q220-116M | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412NORI | Norelli-Hargreaves Playground R/C Q220-116M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2017-03-27 | 2022-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RK01 | Rufus King Park Cons. of Entrance & R/C of Fence Q023-216MA | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2015-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RK01 | Rufus King Park Cons. of Entrance & R/C of Fence Q023-216MA | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2015-09-29 | 2015-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RK01 | Rufus King Park Cons. of Entrance & R/C of Fence Q023-216MA | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2015-12-28 | 2016-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RK01 | Rufus King Park Cons. of Entrance & R/C of Fence Q023-216MA | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RK01 | Rufus King Park Cons. of Entrance & R/C of Fence Q023-216MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2017-03-27 | 2020-11-10
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RKGZ | RUFUS KING PARK GAZEBO RC Q023-112M | 1 | DEVELOP SCOPE | 2010-07-01 | 2010-09-28 | 2010-07-01 | 2011-10-11
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RKGZ | RUFUS KING PARK GAZEBO RC Q023-112M | 2 | DESIGN | 2010-09-29 | 2010-12-27 | 2011-10-12 | 2013-12-02
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RKGZ | RUFUS KING PARK GAZEBO RC Q023-112M | 3 | BID/ REGISTER CONTRACT | 2010-12-28 | 2011-03-27 | 2014-06-17 | 2015-01-30
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RKGZ | RUFUS KING PARK GAZEBO RC Q023-112M | 4 | CONSTRUCTION | 2011-03-28 | 2012-03-26 | 2015-03-30 | 2016-11-17
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RKGZ | RUFUS KING PARK GAZEBO RC Q023-112M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-03-27 | 2013-03-26 | 2016-11-18 | 2017-11-17
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RKM2 | RUFUS KING MANOR MUSEUM -HVAC Q23-116M | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2013-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RKM2 | RUFUS KING MANOR MUSEUM -HVAC Q23-116M | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2013-09-29 | 2013-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RKM2 | RUFUS KING MANOR MUSEUM -HVAC Q23-116M | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2013-12-28 | 2014-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RKM2 | RUFUS KING MANOR MUSEUM -HVAC Q23-116M | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2014-03-28 | 2015-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RKM2 | RUFUS KING MANOR MUSEUM -HVAC Q23-116M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2014-03-28 | 2015-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RWFA | Roy Wilkens Rec. Center: Fire Alarm Reconstruction | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RWFA | Roy Wilkens Rec. Center: Fire Alarm Reconstruction | 2 | DESIGN | 2019-12-28 | 2021-12-26 | 2019-12-28 | 2021-12-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RWFA | Roy Wilkens Rec. Center: Fire Alarm Reconstruction | 3 | BID/ REGISTER CONTRACT | 2021-12-27 | 2022-09-22 | 2021-12-27 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RWFA | Roy Wilkens Rec. Center: Fire Alarm Reconstruction | 4 | CONSTRUCTION | 2022-09-23 | 2025-09-21 | 2022-09-23 | 2025-09-21
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RWFA | Roy Wilkens Rec. Center: Fire Alarm Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-09-22 | 2027-09-21 | 2025-09-22 | 2027-09-21
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RWIL | ROY WILKINS REC CTR ROOF & SITE Q448-112M | 1 | DEVELOP SCOPE | 2011-07-01 | 2011-09-28 | 2011-07-01 | 2011-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RWIL | ROY WILKINS REC CTR ROOF & SITE Q448-112M | 2 | DESIGN | 2011-09-29 | 2011-12-27 | 2011-09-29 | 2011-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RWIL | ROY WILKINS REC CTR ROOF & SITE Q448-112M | 3 | BID/ REGISTER CONTRACT | 2011-12-28 | 2012-03-26 | 2011-12-28 | 2012-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RWIL | ROY WILKINS REC CTR ROOF & SITE Q448-112M | 4 | CONSTRUCTION | 2012-03-27 | 2013-03-26 | 2012-03-27 | 2013-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RWIL | ROY WILKINS REC CTR ROOF & SITE Q448-112M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-03-27 | 2014-03-26 | 2013-03-27 | 2020-09-30
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RWP3 | ROY WILKINS PARK RECREATION CTR RC Q448-115M | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2016-01-13
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RWP3 | ROY WILKINS PARK RECREATION CTR RC Q448-115M | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2016-01-14 | 2017-06-12
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RWP3 | ROY WILKINS PARK RECREATION CTR RC Q448-115M | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2017-06-13 | 2017-09-10
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RWP3 | ROY WILKINS PARK RECREATION CTR RC Q448-115M | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2017-09-11 | 2018-09-10
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RWP3 | ROY WILKINS PARK RECREATION CTR RC Q448-115M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2018-09-11 | 2019-09-10
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RWTK | ROY WILKINS PARK TRACK Q448-104M | 1 | DEVELOP SCOPE | 2002-07-01 | 2002-09-28 | 1997-03-20 | 1997-06-17
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RWTK | ROY WILKINS PARK TRACK Q448-104M | 2 | DESIGN | 2002-12-01 | 2004-03-02 | 2002-12-01 | 2004-03-02
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RWTK | ROY WILKINS PARK TRACK Q448-104M | 3 | BID/ REGISTER CONTRACT | 2004-05-04 | 2004-07-24 | 2004-05-04 | 2004-07-24
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RWTK | ROY WILKINS PARK TRACK Q448-104M | 4 | CONSTRUCTION | 2004-09-24 | 2005-09-23 | 2004-09-24 | 2005-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RWTK | ROY WILKINS PARK TRACK Q448-104M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2005-09-24 | 2006-09-23 | 2005-09-24 | 2012-01-04
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RWTT | Roy Wilkins Park Turf and Track Upgrades Q448-116M | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2012-07-01 | 2012-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RWTT | Roy Wilkins Park Turf and Track Upgrades Q448-116M | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2012-09-29 | 2012-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RWTT | Roy Wilkins Park Turf and Track Upgrades Q448-116M | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2012-12-28 | 2013-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RWTT | Roy Wilkins Park Turf and Track Upgrades Q448-116M | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2013-03-28 | 2014-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RWTT | Roy Wilkins Park Turf and Track Upgrades Q448-116M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2014-03-28 | 2023-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413010F | QUEENS COUNTY FARM MUSEUM - WINDMILL, ROADWAY Q453-202M | 1 | DEVELOP SCOPE | 2003-07-01 | 2003-09-28 | 2003-07-01 | 2003-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413010F | QUEENS COUNTY FARM MUSEUM - WINDMILL, ROADWAY Q453-202M | 2 | DESIGN | 2002-12-01 | 2003-04-30 | 2002-12-01 | 2003-04-30
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413010F | QUEENS COUNTY FARM MUSEUM - WINDMILL, ROADWAY Q453-202M | 3 | BID/ REGISTER CONTRACT | 2003-09-17 | 2003-11-01 | 2003-09-17 | 2003-11-01
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413010F | QUEENS COUNTY FARM MUSEUM - WINDMILL, ROADWAY Q453-202M | 4 | CONSTRUCTION | 2004-01-01 | 2004-12-31 | 2004-01-01 | 2004-12-31
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413010F | QUEENS COUNTY FARM MUSEUM - WINDMILL, ROADWAY Q453-202M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2005-01-01 | 2005-12-31 | 2005-01-01 | 2005-12-31
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413245K | CABELLA (CAMBRIA)PK PLGD & BFLDS Q339-198 | 2 | DESIGN | 2006-09-29 | 2006-12-27 | 2006-09-29 | 2006-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413245K | CABELLA (CAMBRIA)PK PLGD & BFLDS Q339-198 | 3 | BID/ REGISTER CONTRACT | 2006-12-28 | 2007-03-27 | 2006-12-28 | 2007-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413245K | CABELLA (CAMBRIA)PK PLGD & BFLDS Q339-198 | 4 | CONSTRUCTION | 2007-03-28 | 2008-03-26 | 2007-03-28 | 2008-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413245K | CABELLA (CAMBRIA)PK PLGD & BFLDS Q339-198 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-27 | 2009-03-26 | 2008-03-27 | 2009-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413BPTC | BROOKVILLE PARK ENHANCEMENTS Q008-115M | 1 | DEVELOP SCOPE | 2012-07-01 | 2012-09-28 | 2012-07-01 | 2012-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413BPTC | BROOKVILLE PARK ENHANCEMENTS Q008-115M | 2 | DESIGN | 2012-09-29 | 2012-12-27 | 2012-09-29 | 2012-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413BPTC | BROOKVILLE PARK ENHANCEMENTS Q008-115M | 3 | BID/ REGISTER CONTRACT | 2012-12-28 | 2013-03-27 | 2012-12-28 | 2013-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413BPTC | BROOKVILLE PARK ENHANCEMENTS Q008-115M | 4 | CONSTRUCTION | 2013-03-28 | 2014-03-27 | 2013-03-28 | 2014-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413BPTC | BROOKVILLE PARK ENHANCEMENTS Q008-115M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-03-28 | 2015-03-27 | 2014-03-28 | 2023-08-31
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413BRO3 | Brookville Park Entrance R/C Q008-117M | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413BRO3 | Brookville Park Entrance R/C Q008-117M | 2 | DESIGN | 2016-12-28 | 2018-03-22 | 2016-12-28 | 2017-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413BRO3 | Brookville Park Entrance R/C Q008-117M | 3 | BID/ REGISTER CONTRACT | 2018-03-23 | 2018-12-17 | 2017-12-28 | 2018-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413BRO3 | Brookville Park Entrance R/C Q008-117M | 4 | CONSTRUCTION | 2018-12-18 | 2020-12-16 | 2018-09-24 | 2019-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413BRO3 | Brookville Park Entrance R/C Q008-117M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-12-17 | 2021-12-16 | 2019-09-24 | 2020-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413BRO4 | Brookville Park Dog Run | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413BRO4 | Brookville Park Dog Run | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413BRO4 | Brookville Park Dog Run | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413BRO4 | Brookville Park Dog Run | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413BRO4 | Brookville Park Dog Run | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413BRSY | Brookville Park Synthetic Turf Field R/C Q008-119M | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413BRSY | Brookville Park Synthetic Turf Field R/C Q008-119M | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413BRSY | Brookville Park Synthetic Turf Field R/C Q008-119M | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413BRSY | Brookville Park Synthetic Turf Field R/C Q008-119M | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413BRSY | Brookville Park Synthetic Turf Field R/C Q008-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413CAMB | CAMBRIA PLGD RECONSTRUCTION | 1 | DEVELOP SCOPE | 2020-07-01 | 2020-12-27 | 2020-07-01 | 2020-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413CAMB | CAMBRIA PLGD RECONSTRUCTION | 2 | DESIGN | 2020-12-28 | 2021-12-27 | 2020-12-28 | 2021-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413CAMB | CAMBRIA PLGD RECONSTRUCTION | 3 | BID/ REGISTER CONTRACT | 2021-12-28 | 2022-09-23 | 2021-12-28 | 2022-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413CAMB | CAMBRIA PLGD RECONSTRUCTION | 4 | CONSTRUCTION | 2022-09-24 | 2023-09-23 | 2022-09-24 | 2023-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413CAMB | CAMBRIA PLGD RECONSTRUCTION | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-24 | 2024-09-22 | 2023-09-24 | 2024-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413CAST | Castlewood Playground - Reconstruction of the MPPA Q327-119M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413CAST | Castlewood Playground - Reconstruction of the MPPA Q327-119M | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413CAST | Castlewood Playground - Reconstruction of the MPPA Q327-119M | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413CAST | Castlewood Playground - Reconstruction of the MPPA Q327-119M | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413CAST | Castlewood Playground - Reconstruction of the MPPA Q327-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2023-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413COMM | DOUGLASTON PK GOLF COURSE NET FENCING Q411-112M | 2 | DESIGN | 2012-09-29 | 2012-12-27 | 2011-09-29 | 2011-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413COMM | DOUGLASTON PK GOLF COURSE NET FENCING Q411-112M | 3 | BID/ REGISTER CONTRACT | 2012-12-28 | 2013-03-27 | 2011-12-28 | 2012-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413COMM | DOUGLASTON PK GOLF COURSE NET FENCING Q411-112M | 4 | CONSTRUCTION | 2013-03-28 | 2014-03-27 | 2012-03-27 | 2013-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413COMM | DOUGLASTON PK GOLF COURSE NET FENCING Q411-112M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-03-28 | 2015-03-27 | 2013-03-27 | 2016-03-30
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413COV2 | Sunset Cove Pk Oyster Garden/Boardwalk Cons. Q498-117M | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413COV2 | Sunset Cove Pk Oyster Garden/Boardwalk Cons. Q498-117M | 2 | DESIGN | 2016-12-28 | 2018-12-27 | 2016-12-28 | 2017-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413COV2 | Sunset Cove Pk Oyster Garden/Boardwalk Cons. Q498-117M | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2017-12-28 | 2018-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413COV2 | Sunset Cove Pk Oyster Garden/Boardwalk Cons. Q498-117M | 4 | CONSTRUCTION | 2019-09-24 | 2021-09-22 | 2018-09-24 | 2019-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413COV2 | Sunset Cove Pk Oyster Garden/Boardwalk Cons. Q498-117M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2019-09-24 | 2020-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413IDL3 | IDLEWILD PK SITE B Q392 | 1 | DEVELOP SCOPE | 2011-07-01 | 2011-09-28 | 2011-07-01 | 2011-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413IDL3 | IDLEWILD PK SITE B Q392 | 2 | DESIGN | 2011-09-29 | 2011-12-27 | 2011-09-29 | 2011-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413IDL3 | IDLEWILD PK SITE B Q392 | 3 | BID/ REGISTER CONTRACT | 2011-12-28 | 2012-03-26 | 2011-12-28 | 2012-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413IDL3 | IDLEWILD PK SITE B Q392 | 4 | CONSTRUCTION | 2012-03-27 | 2013-03-26 | 2012-03-27 | 2013-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413IDL3 | IDLEWILD PK SITE B Q392 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-03-27 | 2014-03-26 | 2013-03-27 | 2023-03-30
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413IDPK | IDLEWILD PK MARSH NATURE CENTER Q392-210M | 1 | DEVELOP SCOPE | 2006-07-01 | 2006-09-28 | 2008-07-01 | 2008-10-01
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413IDPK | IDLEWILD PK MARSH NATURE CENTER Q392-210M | 2 | DESIGN | 2006-09-29 | 2006-12-27 | 2012-06-15 | 2012-09-15
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413IDPK | IDLEWILD PK MARSH NATURE CENTER Q392-210M | 3 | BID/ REGISTER CONTRACT | 2006-12-28 | 2007-03-27 | 2012-09-16 | 2013-03-31
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413IDPK | IDLEWILD PK MARSH NATURE CENTER Q392-210M | 4 | CONSTRUCTION | 2007-03-28 | 2008-03-26 | 2013-04-01 | 2014-04-01
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413IDPK | IDLEWILD PK MARSH NATURE CENTER Q392-210M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-27 | 2009-03-26 | 2012-04-10 | 2017-12-31
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413JH72 | VIC HANSON/JHS 72 PLGD RC Q352 | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2013-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413JH72 | VIC HANSON/JHS 72 PLGD RC Q352 | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2013-09-29 | 2013-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413JH72 | VIC HANSON/JHS 72 PLGD RC Q352 | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2013-12-28 | 2014-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413JH72 | VIC HANSON/JHS 72 PLGD RC Q352 | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2014-03-28 | 2015-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413JH72 | VIC HANSON/JHS 72 PLGD RC Q352 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2024-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413LPCT | Laurelton Playground Basketball and Handball Courts | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413LPCT | Laurelton Playground Basketball and Handball Courts | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413LPCT | Laurelton Playground Basketball and Handball Courts | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413LPCT | Laurelton Playground Basketball and Handball Courts | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413LPCT | Laurelton Playground Basketball and Handball Courts | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413LPL2 | Laurelton Playground RC Q027-110M | 1 | DEVELOP SCOPE | 2008-07-01 | 2008-09-28 | 2008-07-01 | 2008-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413LPL2 | Laurelton Playground RC Q027-110M | 2 | DESIGN | 2008-09-29 | 2008-12-27 | 2008-09-29 | 2008-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413LPL2 | Laurelton Playground RC Q027-110M | 3 | BID/ REGISTER CONTRACT | 2008-12-28 | 2009-03-27 | 2008-12-28 | 2009-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413LPL2 | Laurelton Playground RC Q027-110M | 4 | CONSTRUCTION | 2009-03-28 | 2010-03-27 | 2009-03-28 | 2010-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413LPL2 | Laurelton Playground RC Q027-110M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2010-03-28 | 2011-03-27 | 2010-03-28 | 2015-05-31
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413LPL3 | Laurelton Plgd and Bayswater Park Skate Elements QG-316M | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2013-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413LPL3 | Laurelton Plgd and Bayswater Park Skate Elements QG-316M | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2013-09-29 | 2013-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413LPL3 | Laurelton Plgd and Bayswater Park Skate Elements QG-316M | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2013-12-28 | 2014-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413LPL3 | Laurelton Plgd and Bayswater Park Skate Elements QG-316M | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2014-03-28 | 2015-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413LPL3 | Laurelton Plgd and Bayswater Park Skate Elements QG-316M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2023-04-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413QCFM | QNS FMHSE-RENOV ED BLDG,GRNHSE & ADRIANCE FMHSE Q453-102MA | 1 | DEVELOP SCOPE | 2001-07-01 | 2001-07-30 | 2001-07-01 | 2001-07-30
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413QCFM | QNS FMHSE-RENOV ED BLDG,GRNHSE & ADRIANCE FMHSE Q453-102MA | 2 | DESIGN | 2001-07-31 | 2002-04-30 | 2001-07-31 | 2002-04-30
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413QCFM | QNS FMHSE-RENOV ED BLDG,GRNHSE & ADRIANCE FMHSE Q453-102MA | 3 | BID/ REGISTER CONTRACT | 2002-06-19 | 2002-11-04 | 2002-06-19 | 2002-11-04
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413QCFM | QNS FMHSE-RENOV ED BLDG,GRNHSE & ADRIANCE FMHSE Q453-102MA | 4 | CONSTRUCTION | 2003-02-18 | 2004-02-17 | 2003-02-18 | 2004-02-17
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413QCFM | QNS FMHSE-RENOV ED BLDG,GRNHSE & ADRIANCE FMHSE Q453-102MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2004-02-18 | 2005-02-16 | 2004-02-18 | 2005-02-16
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413READ | Bellerose Playground (PS 133) Creation of Reading Garden | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413READ | Bellerose Playground (PS 133) Creation of Reading Garden | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413READ | Bellerose Playground (PS 133) Creation of Reading Garden | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413READ | Bellerose Playground (PS 133) Creation of Reading Garden | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413READ | Bellerose Playground (PS 133) Creation of Reading Garden | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2024-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413SPBD | Springfield Park Basketball Courts and BBQ Area Q107-119M | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413SPBD | Springfield Park Basketball Courts and BBQ Area Q107-119M | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413SPBD | Springfield Park Basketball Courts and BBQ Area Q107-119M | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413SPBD | Springfield Park Basketball Courts and BBQ Area Q107-119M | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413SPBD | Springfield Park Basketball Courts and BBQ Area Q107-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413WGPF | WILLIAM GUNN PLAYGROUND EXPANSION | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2013-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413WGPF | WILLIAM GUNN PLAYGROUND EXPANSION | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2013-09-29 | 2013-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413WGPF | WILLIAM GUNN PLAYGROUND EXPANSION | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2013-12-28 | 2014-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413WGPF | WILLIAM GUNN PLAYGROUND EXPANSION | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2014-03-28 | 2015-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413WGPF | WILLIAM GUNN PLAYGROUND EXPANSION | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2025-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-41417PG | BROAD CHANNEL 17TH STREET PLAYGROUND Q460-118M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-41417PG | BROAD CHANNEL 17TH STREET PLAYGROUND Q460-118M | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-41417PG | BROAD CHANNEL 17TH STREET PLAYGROUND Q460-118M | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-41417PG | BROAD CHANNEL 17TH STREET PLAYGROUND Q460-118M | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-41417PG | BROAD CHANNEL 17TH STREET PLAYGROUND Q460-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414B108 | Beach 108th Esplanade Improvements Q496-119M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414B108 | Beach 108th Esplanade Improvements Q496-119M | 2 | DESIGN | 2017-12-28 | 2019-06-20 | 2017-12-28 | 2019-06-20
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414B108 | Beach 108th Esplanade Improvements Q496-119M | 3 | BID/ REGISTER CONTRACT | 2019-06-21 | 2020-03-16 | 2019-06-21 | 2020-03-16
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414B108 | Beach 108th Esplanade Improvements Q496-119M | 4 | CONSTRUCTION | 2020-03-17 | 2021-09-07 | 2020-03-17 | 2021-09-07
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414B108 | Beach 108th Esplanade Improvements Q496-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-08 | 2022-09-07 | 2021-09-08 | 2022-09-07
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414B9TH | Beach 9th Street Basketball Courts | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414B9TH | Beach 9th Street Basketball Courts | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414B9TH | Beach 9th Street Basketball Courts | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414B9TH | Beach 9th Street Basketball Courts | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414B9TH | Beach 9th Street Basketball Courts | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414BAY6 | Michaelis-Bayswater Park Reconstruction Q007-119M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414BAY6 | Michaelis-Bayswater Park Reconstruction Q007-119M | 2 | DESIGN | 2017-12-28 | 2019-06-20 | 2017-12-28 | 2019-06-20
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414BAY6 | Michaelis-Bayswater Park Reconstruction Q007-119M | 3 | BID/ REGISTER CONTRACT | 2019-06-21 | 2020-03-16 | 2019-06-21 | 2020-03-16
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414BAY6 | Michaelis-Bayswater Park Reconstruction Q007-119M | 4 | CONSTRUCTION | 2020-03-17 | 2021-09-07 | 2020-03-17 | 2021-09-07
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414BAY6 | Michaelis-Bayswater Park Reconstruction Q007-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-08 | 2022-09-07 | 2021-09-08 | 2022-09-07
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414BAYS | BAYSWATER-MICHAELIS PK-W0 B/F'S INCL IRRIG Q007-102M | 1 | DEVELOP SCOPE | 2006-07-01 | 2006-09-28 | 2006-07-01 | 2006-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414BAYS | BAYSWATER-MICHAELIS PK-W0 B/F'S INCL IRRIG Q007-102M | 2 | DESIGN | 2006-09-29 | 2006-12-27 | 2006-09-29 | 2006-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414BAYS | BAYSWATER-MICHAELIS PK-W0 B/F'S INCL IRRIG Q007-102M | 3 | BID/ REGISTER CONTRACT | 2006-12-28 | 2007-03-27 | 2006-12-28 | 2007-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414BAYS | BAYSWATER-MICHAELIS PK-W0 B/F'S INCL IRRIG Q007-102M | 4 | CONSTRUCTION | 2007-03-28 | 2008-03-26 | 2007-03-28 | 2008-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414BAYS | BAYSWATER-MICHAELIS PK-W0 B/F'S INCL IRRIG Q007-102M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-27 | 2009-03-26 | 2008-03-27 | 2009-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414BC88 | Beach 88th Street Park Construction Q499-118M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414BC88 | Beach 88th Street Park Construction Q499-118M | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414BC88 | Beach 88th Street Park Construction Q499-118M | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414BC88 | Beach 88th Street Park Construction Q499-118M | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414BC88 | Beach 88th Street Park Construction Q499-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414BCAP | Broad Channel American Park | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2015-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414BCAP | Broad Channel American Park | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2015-09-29 | 2015-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414BCAP | Broad Channel American Park | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2015-12-28 | 2016-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414BCAP | Broad Channel American Park | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414BCAP | Broad Channel American Park | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2017-03-27 | 2023-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414C03B | BROAD CHANNEL PK DAY CAMP Q467-199 | 1 | DEVELOP SCOPE | 2006-07-01 | 2006-09-28 | 2006-07-01 | 2006-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414C03B | BROAD CHANNEL PK DAY CAMP Q467-199 | 2 | DESIGN | 2006-09-29 | 2006-12-27 | 2006-09-29 | 2006-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414C03B | BROAD CHANNEL PK DAY CAMP Q467-199 | 3 | BID/ REGISTER CONTRACT | 2006-12-28 | 2007-03-27 | 2006-12-28 | 2007-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414C03B | BROAD CHANNEL PK DAY CAMP Q467-199 | 4 | CONSTRUCTION | 2007-03-28 | 2008-03-26 | 2007-03-28 | 2008-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414C03B | BROAD CHANNEL PK DAY CAMP Q467-199 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-27 | 2009-03-26 | 2008-03-27 | 2009-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414CHAN | BROAD CHANNEL PK ATHLETIC FIELDS AND LANDSCAPING Q467-102M | 3 | BID/ REGISTER CONTRACT | 2004-03-16 | 2004-06-15 | 2004-03-16 | 2004-06-15
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414CHAN | BROAD CHANNEL PK ATHLETIC FIELDS AND LANDSCAPING Q467-102M | 4 | CONSTRUCTION | 2004-06-16 | 2005-06-15 | 2004-06-16 | 2005-06-15
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414CHAN | BROAD CHANNEL PK ATHLETIC FIELDS AND LANDSCAPING Q467-102M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2005-06-16 | 2006-06-15 | 2005-06-16 | 2006-06-15
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414LABY | Shorefront Labyrinth and Seating Area Q163-518M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414LABY | Shorefront Labyrinth and Seating Area Q163-518M | 2 | DESIGN | 2017-12-28 | 2019-06-20 | 2017-12-28 | 2019-06-20
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414LABY | Shorefront Labyrinth and Seating Area Q163-518M | 3 | BID/ REGISTER CONTRACT | 2019-06-21 | 2020-03-16 | 2019-06-21 | 2020-03-16
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414LABY | Shorefront Labyrinth and Seating Area Q163-518M | 4 | CONSTRUCTION | 2020-03-17 | 2021-09-07 | 2020-03-17 | 2021-09-07
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414LABY | Shorefront Labyrinth and Seating Area Q163-518M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-08 | 2022-09-07 | 2021-09-08 | 2022-09-07
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414LAN2 | Lannett Playground Sitting Area R/C Q407-118M | 1 | DEVELOP SCOPE | 2014-07-01 | 2014-09-28 | 2014-07-01 | 2014-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414LAN2 | Lannett Playground Sitting Area R/C Q407-118M | 2 | DESIGN | 2014-09-29 | 2014-12-27 | 2014-09-29 | 2014-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414LAN2 | Lannett Playground Sitting Area R/C Q407-118M | 3 | BID/ REGISTER CONTRACT | 2014-12-28 | 2015-03-27 | 2014-12-28 | 2015-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414LAN2 | Lannett Playground Sitting Area R/C Q407-118M | 4 | CONSTRUCTION | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2016-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414LAN2 | Lannett Playground Sitting Area R/C Q407-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2021-10-31
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414ODON | O'Donohue Park Picnic Grove Construction | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2015-07-01 | 2015-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414ODON | O'Donohue Park Picnic Grove Construction | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2015-12-28 | 2016-12-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414ODON | O'Donohue Park Picnic Grove Construction | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2016-12-27 | 2017-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414ODON | O'Donohue Park Picnic Grove Construction | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2017-09-23 | 2018-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414ODON | O'Donohue Park Picnic Grove Construction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2018-09-23 | 2025-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414RB59 | Beach 59th Street Playground R/C Q162E-118M | 1 | DEVELOP SCOPE | 2014-07-01 | 2014-09-28 | 2014-07-01 | 2014-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414RB59 | Beach 59th Street Playground R/C Q162E-118M | 2 | DESIGN | 2014-09-29 | 2014-12-27 | 2014-09-29 | 2014-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414RB59 | Beach 59th Street Playground R/C Q162E-118M | 3 | BID/ REGISTER CONTRACT | 2014-12-28 | 2015-03-27 | 2014-12-28 | 2015-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414RB59 | Beach 59th Street Playground R/C Q162E-118M | 4 | CONSTRUCTION | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2016-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414RB59 | Beach 59th Street Playground R/C Q162E-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2023-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414RBHD | Rockaway Beach Shorefront Pkwy Handball Courts Q163-315M | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2013-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414RBHD | Rockaway Beach Shorefront Pkwy Handball Courts Q163-315M | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2013-09-29 | 2013-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414RBHD | Rockaway Beach Shorefront Pkwy Handball Courts Q163-315M | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2013-12-28 | 2014-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414RBHD | Rockaway Beach Shorefront Pkwy Handball Courts Q163-315M | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2014-03-28 | 2015-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414RBHD | Rockaway Beach Shorefront Pkwy Handball Courts Q163-315M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2023-11-29
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414RBRR | ROCKAWAY BEACH 108 ST ROLLER RINK Q163-114M | 1 | DEVELOP SCOPE | 2012-07-01 | 2012-09-28 | 2011-07-01 | 2011-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414RBRR | ROCKAWAY BEACH 108 ST ROLLER RINK Q163-114M | 2 | DESIGN | 2012-09-29 | 2012-12-27 | 2011-09-29 | 2011-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414RBRR | ROCKAWAY BEACH 108 ST ROLLER RINK Q163-114M | 3 | BID/ REGISTER CONTRACT | 2012-12-28 | 2013-03-27 | 2011-12-28 | 2012-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414RBRR | ROCKAWAY BEACH 108 ST ROLLER RINK Q163-114M | 4 | CONSTRUCTION | 2013-03-28 | 2014-03-27 | 2012-03-27 | 2013-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414RBRR | ROCKAWAY BEACH 108 ST ROLLER RINK Q163-114M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-03-28 | 2015-03-27 | 2013-03-27 | 2016-10-31
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414RKSP | ROCKAWAY BEACH SKATE PARK FACILITY- RC Q163-111MA | 1 | DEVELOP SCOPE | 2010-07-01 | 2010-09-28 | 2010-07-01 | 2010-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414RKSP | ROCKAWAY BEACH SKATE PARK FACILITY- RC Q163-111MA | 2 | DESIGN | 2010-09-29 | 2010-12-27 | 2010-09-29 | 2010-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414RKSP | ROCKAWAY BEACH SKATE PARK FACILITY- RC Q163-111MA | 3 | BID/ REGISTER CONTRACT | 2010-12-28 | 2011-03-27 | 2010-12-28 | 2011-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414RKSP | ROCKAWAY BEACH SKATE PARK FACILITY- RC Q163-111MA | 4 | CONSTRUCTION | 2011-03-28 | 2012-03-26 | 2011-03-28 | 2012-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414RKSP | ROCKAWAY BEACH SKATE PARK FACILITY- RC Q163-111MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-03-27 | 2013-03-26 | 2012-03-27 | 2021-04-30
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414THUR | Thursby Basin Park Construction | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414THUR | Thursby Basin Park Construction | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414THUR | Thursby Basin Park Construction | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414THUR | Thursby Basin Park Construction | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414THUR | Thursby Basin Park Construction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414TRB2 | Tribute Park Reconstruction Q028-116M | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2015-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414TRB2 | Tribute Park Reconstruction Q028-116M | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2015-09-29 | 2015-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414TRB2 | Tribute Park Reconstruction Q028-116M | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2015-12-28 | 2016-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414TRB2 | Tribute Park Reconstruction Q028-116M | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414TRB2 | Tribute Park Reconstruction Q028-116M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2017-03-27 | 2023-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415AQNT | FMCP Aquatic Center Netting | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415AQNT | FMCP Aquatic Center Netting | 2 | DESIGN | 2019-12-28 | 2021-12-26 | 2019-12-28 | 2021-12-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415AQNT | FMCP Aquatic Center Netting | 3 | BID/ REGISTER CONTRACT | 2021-12-27 | 2022-09-22 | 2021-12-27 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415AQNT | FMCP Aquatic Center Netting | 4 | CONSTRUCTION | 2022-09-23 | 2025-09-21 | 2022-09-23 | 2025-09-21
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415AQNT | FMCP Aquatic Center Netting | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-09-22 | 2027-09-21 | 2025-09-22 | 2027-09-21
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415AQUA | FMCP - Aquatic Center Roof Replacement | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415AQUA | FMCP - Aquatic Center Roof Replacement | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415AQUA | FMCP - Aquatic Center Roof Replacement | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415AQUA | FMCP - Aquatic Center Roof Replacement | 4 | CONSTRUCTION | 2019-09-24 | 2021-03-21 | 2019-09-24 | 2021-03-21
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415AQUA | FMCP - Aquatic Center Roof Replacement | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-22 | 2022-03-21 | 2021-03-22 | 2022-03-21
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415CAND | FMCP - Reconstruction of Candela Structures | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415CAND | FMCP - Reconstruction of Candela Structures | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415CAND | FMCP - Reconstruction of Candela Structures | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415CAND | FMCP - Reconstruction of Candela Structures | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415CAND | FMCP - Reconstruction of Candela Structures | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415FMC2 | FMCP - Meadow Lake Promenade R/C Q099-113M | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2013-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415FMC2 | FMCP - Meadow Lake Promenade R/C Q099-113M | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2013-09-29 | 2013-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415FMC2 | FMCP - Meadow Lake Promenade R/C Q099-113M | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2013-12-28 | 2014-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415FMC2 | FMCP - Meadow Lake Promenade R/C Q099-113M | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2014-03-28 | 2015-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415FMC2 | FMCP - Meadow Lake Promenade R/C Q099-113M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2023-09-30
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415FMWS | FMCP - Adult Fitness Equipment Installation Q099-318M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415FMWS | FMCP - Adult Fitness Equipment Installation Q099-318M | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415FMWS | FMCP - Adult Fitness Equipment Installation Q099-318M | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415FMWS | FMCP - Adult Fitness Equipment Installation Q099-318M | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415FMWS | FMCP - Adult Fitness Equipment Installation Q099-318M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415FOTF | FMCP - Fourtain of the Fairs R/C Q099-117M | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415FOTF | FMCP - Fourtain of the Fairs R/C Q099-117M | 2 | DESIGN | 2016-12-28 | 2018-03-22 | 2016-12-28 | 2018-03-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415FOTF | FMCP - Fourtain of the Fairs R/C Q099-117M | 3 | BID/ REGISTER CONTRACT | 2018-03-23 | 2018-12-17 | 2018-03-23 | 2018-12-17
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415FOTF | FMCP - Fourtain of the Fairs R/C Q099-117M | 4 | CONSTRUCTION | 2018-12-18 | 2020-12-16 | 2018-12-18 | 2020-12-16
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415FOTF | FMCP - Fourtain of the Fairs R/C Q099-117M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-12-17 | 2021-12-16 | 2020-12-17 | 2021-12-16
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415FSTF | FMCP - Synthetic Turf Fields 8 & 9 R/C Q099-319M | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415FSTF | FMCP - Synthetic Turf Fields 8 & 9 R/C Q099-319M | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415FSTF | FMCP - Synthetic Turf Fields 8 & 9 R/C Q099-319M | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415FSTF | FMCP - Synthetic Turf Fields 8 & 9 R/C Q099-319M | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415FSTF | FMCP - Synthetic Turf Fields 8 & 9 R/C Q099-319M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415LWCS | FMCP - Lawrence Playground Comfort Station R/C Q099-817MA | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415LWCS | FMCP - Lawrence Playground Comfort Station R/C Q099-817MA | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415LWCS | FMCP - Lawrence Playground Comfort Station R/C Q099-817MA | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415LWCS | FMCP - Lawrence Playground Comfort Station R/C Q099-817MA | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415LWCS | FMCP - Lawrence Playground Comfort Station R/C Q099-817MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415LWP2 | FMCP - Lawrence Playground R/C Q099-717M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415LWP2 | FMCP - Lawrence Playground R/C Q099-717M | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415LWP2 | FMCP - Lawrence Playground R/C Q099-717M | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415LWP2 | FMCP - Lawrence Playground R/C Q099-717M | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415LWP2 | FMCP - Lawrence Playground R/C Q099-717M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415MEA2 | FMCP - MEADOW LAKE- PATHS Q099-215M | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2013-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415MEA2 | FMCP - MEADOW LAKE- PATHS Q099-215M | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2013-09-29 | 2013-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415MEA2 | FMCP - MEADOW LAKE- PATHS Q099-215M | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2013-12-28 | 2014-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415MEA2 | FMCP - MEADOW LAKE- PATHS Q099-215M | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2014-03-28 | 2015-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415MEA2 | FMCP - MEADOW LAKE- PATHS Q099-215M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2023-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415PAS4 | FMCP-Passerelle Roof | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415PAS4 | FMCP-Passerelle Roof | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415PAS4 | FMCP-Passerelle Roof | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415PAS4 | FMCP-Passerelle Roof | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415PAS4 | FMCP-Passerelle Roof | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415PAVI | FMCP - NYS PAVILION RC Q099-116M | 1 | DEVELOP SCOPE | 2007-07-01 | 2007-09-28 | 2007-07-01 | 2015-09-21
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415PAVI | FMCP - NYS PAVILION RC Q099-116M | 2 | DESIGN | 2007-09-29 | 2007-12-27 | 2015-09-22 | 2015-09-21
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415PAVI | FMCP - NYS PAVILION RC Q099-116M | 3 | BID/ REGISTER CONTRACT | 2007-12-28 | 2008-03-26 | 2015-09-22 | 2015-09-21
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415PAVI | FMCP - NYS PAVILION RC Q099-116M | 4 | CONSTRUCTION | 2008-03-27 | 2009-03-26 | 2015-09-22 | 2015-09-21
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415PAVI | FMCP - NYS PAVILION RC Q099-116M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2009-03-27 | 2010-03-26 | 2015-09-22 | 2021-10-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415SCHL | Flushing Meadows Corona Park UPK | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415SCHL | Flushing Meadows Corona Park UPK | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415SCHL | Flushing Meadows Corona Park UPK | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415SCHL | Flushing Meadows Corona Park UPK | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415SCHL | Flushing Meadows Corona Park UPK | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2024-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415WLNC | FMCP-WILLOW LAKE NATURE CENTER Q348 | 1 | DEVELOP SCOPE | 2014-07-01 | 2014-09-28 | 2014-07-01 | 2017-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415WLNC | FMCP-WILLOW LAKE NATURE CENTER Q348 | 2 | DESIGN | 2014-09-29 | 2014-12-27 | 2017-09-29 | 2017-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415WLNC | FMCP-WILLOW LAKE NATURE CENTER Q348 | 3 | BID/ REGISTER CONTRACT | 2014-12-28 | 2015-03-27 | 2017-12-28 | 2018-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415WLNC | FMCP-WILLOW LAKE NATURE CENTER Q348 | 4 | CONSTRUCTION | 2015-03-28 | 2016-03-26 | 2018-03-28 | 2019-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415WLNC | FMCP-WILLOW LAKE NATURE CENTER Q348 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-27 | 2017-03-26 | 2019-03-28 | 2020-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415WRD2 | FMCP - World's Fair Marina Pier 1 & 3 R/C Q099-218M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415WRD2 | FMCP - World's Fair Marina Pier 1 & 3 R/C Q099-218M | 2 | DESIGN | 2017-12-28 | 2019-12-27 | 2017-12-28 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415WRD2 | FMCP - World's Fair Marina Pier 1 & 3 R/C Q099-218M | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415WRD2 | FMCP - World's Fair Marina Pier 1 & 3 R/C Q099-218M | 4 | CONSTRUCTION | 2020-09-23 | 2023-09-22 | 2020-09-23 | 2023-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415WRD2 | FMCP - World's Fair Marina Pier 1 & 3 R/C Q099-218M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-23 | 2025-09-21 | 2023-09-23 | 2025-09-21
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415WRLD | FMCP - World's Fair Playground Asphalt Field Q099-517M | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2015-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415WRLD | FMCP - World's Fair Playground Asphalt Field Q099-517M | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2015-09-29 | 2015-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415WRLD | FMCP - World's Fair Playground Asphalt Field Q099-517M | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2015-12-28 | 2016-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415WRLD | FMCP - World's Fair Playground Asphalt Field Q099-517M | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415WRLD | FMCP - World's Fair Playground Asphalt Field Q099-517M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2017-03-27 | 2022-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4ANCH01 | Anchor Park Site - Astoria Park (DESIGN ONLY - ALL PHASES) | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4ANCH01 | Anchor Park Site - Astoria Park (DESIGN ONLY - ALL PHASES) | 2 | DESIGN | 2016-12-28 | 2018-12-27 | 2016-12-28 | 2017-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4ANCH01 | Anchor Park Site - Astoria Park (DESIGN ONLY - ALL PHASES) | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2017-12-28 | 2018-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4ANCH01 | Anchor Park Site - Astoria Park (DESIGN ONLY - ALL PHASES) | 4 | CONSTRUCTION | 2019-09-24 | 2021-09-22 | 2018-09-24 | 2019-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4ANCH01 | Anchor Park Site - Astoria Park (DESIGN ONLY - ALL PHASES) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2019-09-24 | 2020-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4ANCH02 | Anchor Pk - Astoria Park PH1: Synthetic Turf Track Q004-218M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4ANCH02 | Anchor Pk - Astoria Park PH1: Synthetic Turf Track Q004-218M | 2 | DESIGN | 2017-12-28 | 2019-06-20 | 2017-12-28 | 2019-06-20
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4ANCH02 | Anchor Pk - Astoria Park PH1: Synthetic Turf Track Q004-218M | 3 | BID/ REGISTER CONTRACT | 2019-06-21 | 2020-03-16 | 2019-06-21 | 2020-03-16
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4ANCH02 | Anchor Pk - Astoria Park PH1: Synthetic Turf Track Q004-218M | 4 | CONSTRUCTION | 2020-03-17 | 2021-09-07 | 2020-03-17 | 2021-09-07
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4ANCH02 | Anchor Pk - Astoria Park PH1: Synthetic Turf Track Q004-218M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-08 | 2022-09-07 | 2021-09-08 | 2022-09-07
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4ANCH03 | Anchor Pk - Astoria Park PH2A: Charybdis Plgd R/C Q004-318M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4ANCH03 | Anchor Pk - Astoria Park PH2A: Charybdis Plgd R/C Q004-318M | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4ANCH03 | Anchor Pk - Astoria Park PH2A: Charybdis Plgd R/C Q004-318M | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4ANCH03 | Anchor Pk - Astoria Park PH2A: Charybdis Plgd R/C Q004-318M | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4ANCH03 | Anchor Pk - Astoria Park PH2A: Charybdis Plgd R/C Q004-318M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4ANCH04 | Anchor Pk - Astoria Pk PH2B: Charybdis Plgd CS R/C Q004-418M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4ANCH04 | Anchor Pk - Astoria Pk PH2B: Charybdis Plgd CS R/C Q004-418M | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4ANCH04 | Anchor Pk - Astoria Pk PH2B: Charybdis Plgd CS R/C Q004-418M | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4ANCH04 | Anchor Pk - Astoria Pk PH2B: Charybdis Plgd CS R/C Q004-418M | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4ANCH04 | Anchor Pk - Astoria Pk PH2B: Charybdis Plgd CS R/C Q004-418M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4ANCH05 | Anchor Park - Astoria Park Phase 3 | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4ANCH05 | Anchor Park - Astoria Park Phase 3 | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4ANCH05 | Anchor Park - Astoria Park Phase 3 | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4ANCH05 | Anchor Park - Astoria Park Phase 3 | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4ANCH05 | Anchor Park - Astoria Park Phase 3 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4ASTRRF | Recon of Roofing systems at Astoria Park FH | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4ASTRRF | Recon of Roofing systems at Astoria Park FH | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4ASTRRF | Recon of Roofing systems at Astoria Park FH | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4ASTRRF | Recon of Roofing systems at Astoria Park FH | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4ASTRRF | Recon of Roofing systems at Astoria Park FH | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BASDCS | Bayside Playground-Reconstruction of Comfort Station | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BASDCS | Bayside Playground-Reconstruction of Comfort Station | 2 | DESIGN | 2017-12-28 | 2019-12-27 | 2017-12-28 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BASDCS | Bayside Playground-Reconstruction of Comfort Station | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BASDCS | Bayside Playground-Reconstruction of Comfort Station | 4 | CONSTRUCTION | 2020-09-23 | 2022-09-22 | 2020-09-23 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BASDCS | Bayside Playground-Reconstruction of Comfort Station | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BAYMAR | Bayside Marina RC | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BAYMAR | Bayside Marina RC | 2 | DESIGN | 2018-12-28 | 2020-12-26 | 2018-12-28 | 2020-12-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BAYMAR | Bayside Marina RC | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BAYMAR | Bayside Marina RC | 4 | CONSTRUCTION | 2021-09-23 | 2023-09-22 | 2021-09-23 | 2023-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BAYMAR | Bayside Marina RC | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-23 | 2024-09-21 | 2023-09-23 | 2024-09-21
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BC94S1 | Beach 94th Street Performance Space Cons. Q163-418M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BC94S1 | Beach 94th Street Performance Space Cons. Q163-418M | 2 | DESIGN | 2017-12-28 | 2019-06-20 | 2017-12-28 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BC94S1 | Beach 94th Street Performance Space Cons. Q163-418M | 3 | BID/ REGISTER CONTRACT | 2019-06-21 | 2020-03-16 | 2019-12-28 | 2020-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BC94S1 | Beach 94th Street Performance Space Cons. Q163-418M | 4 | CONSTRUCTION | 2020-03-17 | 2021-09-07 | 2020-09-23 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BC94S1 | Beach 94th Street Performance Space Cons. Q163-418M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-08 | 2022-09-07 | 2022-09-23 | 2023-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BC94S1 | Beach 94th Street Performance Space Cons. Q163-418M | 6 | DEVELOP SCOPE | 2022-09-08 | 2023-03-06 | 2022-09-23 | 2023-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BC94S1 | Beach 94th Street Performance Space Cons. Q163-418M | 7 | DESIGN | 2023-03-07 | 2025-03-05 | 2022-09-23 | 2023-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BC94S1 | Beach 94th Street Performance Space Cons. Q163-418M | 8 | BID/ REGISTER CONTRACT | 2025-03-06 | 2025-11-30 | 2022-09-23 | 2023-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BC94S1 | Beach 94th Street Performance Space Cons. Q163-418M | 9 | CONSTRUCTION | 2025-12-01 | 2027-11-30 | 2022-09-23 | 2023-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BC94S1 | Beach 94th Street Performance Space Cons. Q163-418M | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2027-12-01 | 2028-11-29 | 2022-09-23 | 2023-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BIGBSH | Big Bush Park Playground R/C Q205A-115M | 4 | CONSTRUCTION | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2016-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BIGBSH | Big Bush Park Playground R/C Q205A-115M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2019-04-30
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BLSPTH | Black Spectrum Theatre -Interior renovations q448-219m | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BLSPTH | Black Spectrum Theatre -Interior renovations q448-219m | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BLSPTH | Black Spectrum Theatre -Interior renovations q448-219m | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BLSPTH | Black Spectrum Theatre -Interior renovations q448-219m | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BLSPTH | Black Spectrum Theatre -Interior renovations q448-219m | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BRKVBB | BROOKVILLE PARK TWO BASEBALL FIELD | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BRKVBB | BROOKVILLE PARK TWO BASEBALL FIELD | 2 | DESIGN | 2019-12-28 | 2021-12-26 | 2019-12-28 | 2021-12-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BRKVBB | BROOKVILLE PARK TWO BASEBALL FIELD | 3 | BID/ REGISTER CONTRACT | 2021-12-27 | 2022-09-22 | 2021-12-27 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BRKVBB | BROOKVILLE PARK TWO BASEBALL FIELD | 4 | CONSTRUCTION | 2022-09-23 | 2024-09-21 | 2022-09-23 | 2024-09-21
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BRKVBB | BROOKVILLE PARK TWO BASEBALL FIELD | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-09-22 | 2025-09-21 | 2024-09-22 | 2025-09-21
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BSHIST | Ft. Totten Bayside Historical Society Officers ClubQ458-116M | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2013-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BSHIST | Ft. Totten Bayside Historical Society Officers ClubQ458-116M | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2013-09-29 | 2016-07-29
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BSHIST | Ft. Totten Bayside Historical Society Officers ClubQ458-116M | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2016-07-30 | 2016-07-29
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BSHIST | Ft. Totten Bayside Historical Society Officers ClubQ458-116M | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2016-07-30 | 2016-07-29
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BSHIST | Ft. Totten Bayside Historical Society Officers ClubQ458-116M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2016-07-30 | 2017-07-29
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BW0007 | QUEENS MULTI-SITE QG-104M | 2 | DESIGN | 2006-09-29 | 2006-12-27 | 2006-09-29 | 2006-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BW0007 | QUEENS MULTI-SITE QG-104M | 3 | BID/ REGISTER CONTRACT | 2006-12-28 | 2007-03-27 | 2006-12-28 | 2007-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BW0007 | QUEENS MULTI-SITE QG-104M | 4 | CONSTRUCTION | 2007-03-28 | 2008-03-26 | 2007-03-28 | 2008-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BW0007 | QUEENS MULTI-SITE QG-104M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-27 | 2009-03-26 | 2008-03-27 | 2014-04-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWALK1 | FY12 Queens Boardwalks (FEMA Funded) Q162-212M | 1 | DEVELOP SCOPE | 2012-07-01 | 2012-09-28 | 2012-07-01 | 2012-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWALK1 | FY12 Queens Boardwalks (FEMA Funded) Q162-212M | 2 | DESIGN | 2012-09-29 | 2012-12-27 | 2012-09-29 | 2012-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWALK1 | FY12 Queens Boardwalks (FEMA Funded) Q162-212M | 3 | BID/ REGISTER CONTRACT | 2012-12-28 | 2013-03-27 | 2012-12-28 | 2013-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWALK1 | FY12 Queens Boardwalks (FEMA Funded) Q162-212M | 4 | CONSTRUCTION | 2013-03-28 | 2014-03-27 | 2013-03-28 | 2014-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWALK1 | FY12 Queens Boardwalks (FEMA Funded) Q162-212M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-03-28 | 2103-04-05 | 2014-03-28 | 2023-04-05
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWIDEF | QUEENS - MULTI SITE QG-210M | 1 | DEVELOP SCOPE | 2010-07-01 | 2010-09-28 | 2010-07-01 | 2010-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWIDEF | QUEENS - MULTI SITE QG-210M | 2 | DESIGN | 2010-09-29 | 2010-12-27 | 2010-09-29 | 2010-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWIDEF | QUEENS - MULTI SITE QG-210M | 3 | BID/ REGISTER CONTRACT | 2010-12-28 | 2011-03-27 | 2010-12-28 | 2011-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWIDEF | QUEENS - MULTI SITE QG-210M | 4 | CONSTRUCTION | 2011-03-28 | 2012-03-26 | 2011-03-28 | 2012-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWIDEF | QUEENS - MULTI SITE QG-210M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-03-27 | 2013-03-26 | 2012-03-27 | 2023-05-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWIDEJ | QUEENS - COUNCIL & BP MULTI SITE QG-811M | 3 | BID/ REGISTER CONTRACT | 2011-12-28 | 2012-03-26 | 2011-12-28 | 2012-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWIDEJ | QUEENS - COUNCIL & BP MULTI SITE QG-811M | 4 | CONSTRUCTION | 2012-03-27 | 2013-03-26 | 2012-03-27 | 2013-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWIDEJ | QUEENS - COUNCIL & BP MULTI SITE QG-811M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-03-27 | 2014-03-26 | 2013-03-27 | 2016-08-31
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWIDEK | QUEENS - COUNCIL & BP MULTI SITE (QG-1011M) | 1 | DEVELOP SCOPE | 2011-07-01 | 2011-09-28 | 2011-07-01 | 2011-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWIDEK | QUEENS - COUNCIL & BP MULTI SITE (QG-1011M) | 2 | DESIGN | 2011-09-29 | 2011-12-27 | 2011-09-29 | 2011-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWIDEK | QUEENS - COUNCIL & BP MULTI SITE (QG-1011M) | 3 | BID/ REGISTER CONTRACT | 2011-12-28 | 2012-03-26 | 2011-12-28 | 2012-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWIDEK | QUEENS - COUNCIL & BP MULTI SITE (QG-1011M) | 4 | CONSTRUCTION | 2012-03-27 | 2013-03-26 | 2012-03-27 | 2013-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWIDEK | QUEENS - COUNCIL & BP MULTI SITE (QG-1011M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-03-27 | 2014-03-26 | 2013-03-27 | 2023-07-08
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWIDEL | QUEENS - COUNCIL & MAYORAL MULTI SITE QG-1116M | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWIDEL | QUEENS - COUNCIL & MAYORAL MULTI SITE QG-1116M | 2 | DESIGN | 2016-12-28 | 2018-03-22 | 2016-12-28 | 2018-03-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWIDEL | QUEENS - COUNCIL & MAYORAL MULTI SITE QG-1116M | 3 | BID/ REGISTER CONTRACT | 2018-03-23 | 2018-12-17 | 2018-03-23 | 2018-12-17
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWIDEL | QUEENS - COUNCIL & MAYORAL MULTI SITE QG-1116M | 4 | CONSTRUCTION | 2018-12-18 | 2020-12-16 | 2018-12-18 | 2020-12-16
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWIDEL | QUEENS - COUNCIL & MAYORAL MULTI SITE QG-1116M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-12-17 | 2021-12-16 | 2020-12-17 | 2021-12-16
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWIDEM | QUEENS - MULTI SITE QG-1216M | 1 | DEVELOP SCOPE | 2016-07-11 | 2017-01-06 | 2016-07-11 | 2017-01-06
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWIDEM | QUEENS - MULTI SITE QG-1216M | 2 | DESIGN | 2017-01-07 | 2018-04-01 | 2017-01-07 | 2018-04-01
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWIDEM | QUEENS - MULTI SITE QG-1216M | 3 | BID/ REGISTER CONTRACT | 2018-04-02 | 2018-12-27 | 2018-04-02 | 2018-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWIDEM | QUEENS - MULTI SITE QG-1216M | 4 | CONSTRUCTION | 2018-12-28 | 2020-12-26 | 2018-12-28 | 2020-12-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWIDEM | QUEENS - MULTI SITE QG-1216M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-12-27 | 2021-12-26 | 2020-12-27 | 2021-12-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWIDEN | QUEENS - COUNCIL & BP MULTI SITE QG-1316M | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWIDEN | QUEENS - COUNCIL & BP MULTI SITE QG-1316M | 2 | DESIGN | 2016-12-28 | 2018-03-22 | 2016-12-28 | 2018-03-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWIDEN | QUEENS - COUNCIL & BP MULTI SITE QG-1316M | 3 | BID/ REGISTER CONTRACT | 2018-03-23 | 2018-12-17 | 2018-03-23 | 2018-12-17
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWIDEN | QUEENS - COUNCIL & BP MULTI SITE QG-1316M | 4 | CONSTRUCTION | 2018-12-18 | 2020-12-16 | 2018-12-18 | 2020-12-16
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWIDEN | QUEENS - COUNCIL & BP MULTI SITE QG-1316M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-12-17 | 2021-12-16 | 2020-12-17 | 2021-12-16
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWIDEP | QUEENS - COUNCIL MULTI SITE QG-217M | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWIDEP | QUEENS - COUNCIL MULTI SITE QG-217M | 2 | DESIGN | 2016-12-28 | 2018-12-27 | 2016-12-28 | 2017-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWIDEP | QUEENS - COUNCIL MULTI SITE QG-217M | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2017-12-28 | 2018-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWIDEP | QUEENS - COUNCIL MULTI SITE QG-217M | 4 | CONSTRUCTION | 2019-09-24 | 2021-09-22 | 2018-09-24 | 2019-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWIDEP | QUEENS - COUNCIL MULTI SITE QG-217M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2019-09-24 | 2020-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWIDEQ | Roy Wilkins Southern Qns Pk Performance Area R/C Q448-118M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWIDEQ | Roy Wilkins Southern Qns Pk Performance Area R/C Q448-118M | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWIDEQ | Roy Wilkins Southern Qns Pk Performance Area R/C Q448-118M | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWIDEQ | Roy Wilkins Southern Qns Pk Performance Area R/C Q448-118M | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWIDEQ | Roy Wilkins Southern Qns Pk Performance Area R/C Q448-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWIDER | QUEENS - COUNCIL MULTISITE QG-618M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWIDER | QUEENS - COUNCIL MULTISITE QG-618M | 2 | DESIGN | 2017-12-28 | 2019-06-25 | 2017-12-28 | 2019-06-25
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWIDER | QUEENS - COUNCIL MULTISITE QG-618M | 3 | BID/ REGISTER CONTRACT | 2019-06-26 | 2020-03-21 | 2019-06-26 | 2020-03-21
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWIDER | QUEENS - COUNCIL MULTISITE QG-618M | 4 | CONSTRUCTION | 2020-03-22 | 2021-09-17 | 2020-03-22 | 2021-09-17
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWIDER | QUEENS - COUNCIL MULTISITE QG-618M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-18 | 2022-09-17 | 2021-09-18 | 2022-09-17
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWIDES | QUEENS - COUNCIL MULTISITE QG-818M | 4 | CONSTRUCTION | 2020-03-22 | 2021-09-17 | 2020-03-22 | 2021-09-17
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWIDES | QUEENS - COUNCIL MULTISITE QG-818M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-18 | 2022-09-17 | 2021-09-18 | 2022-09-17
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWSTF1 | Grover Cleveland Plgd & Pals Oval Synthetic Turf Field R/C | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWSTF1 | Grover Cleveland Plgd & Pals Oval Synthetic Turf Field R/C | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWSTF1 | Grover Cleveland Plgd & Pals Oval Synthetic Turf Field R/C | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWSTF1 | Grover Cleveland Plgd & Pals Oval Synthetic Turf Field R/C | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWSTF1 | Grover Cleveland Plgd & Pals Oval Synthetic Turf Field R/C | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CARSON | Silent Spring Playground R/C Q300-116M | 1 | DEVELOP SCOPE | 2014-07-01 | 2014-09-28 | 2014-07-01 | 2014-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CARSON | Silent Spring Playground R/C Q300-116M | 2 | DESIGN | 2014-09-29 | 2014-12-27 | 2014-09-29 | 2014-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CARSON | Silent Spring Playground R/C Q300-116M | 3 | BID/ REGISTER CONTRACT | 2014-12-28 | 2015-03-27 | 2014-12-28 | 2015-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CARSON | Silent Spring Playground R/C Q300-116M | 4 | CONSTRUCTION | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2016-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CARSON | Silent Spring Playground R/C Q300-116M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2023-12-10
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPIAHP | CPI PH2 - Astoria Health Playground R/C Q123-116M | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2015-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPIAHP | CPI PH2 - Astoria Health Playground R/C Q123-116M | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2015-09-29 | 2015-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPIAHP | CPI PH2 - Astoria Health Playground R/C Q123-116M | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2015-12-28 | 2016-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPIAHP | CPI PH2 - Astoria Health Playground R/C Q123-116M | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPIAHP | CPI PH2 - Astoria Health Playground R/C Q123-116M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2017-03-27 | 2023-03-29
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPIALM | CPI PH2 - Almeda Playground Reconstruction Q443-117M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPIALM | CPI PH2 - Almeda Playground Reconstruction Q443-117M | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPIALM | CPI PH2 - Almeda Playground Reconstruction Q443-117M | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPIALM | CPI PH2 - Almeda Playground Reconstruction Q443-117M | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPIALM | CPI PH2 - Almeda Playground Reconstruction Q443-117M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPIBN5 | CPI PH1- RC- Astoria Heights & Bowne Plgd C/S QG-1015M | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2015-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPIBN5 | CPI PH1- RC- Astoria Heights & Bowne Plgd C/S QG-1015M | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2015-09-29 | 2015-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPIBN5 | CPI PH1- RC- Astoria Heights & Bowne Plgd C/S QG-1015M | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2015-12-28 | 2016-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPIBN5 | CPI PH1- RC- Astoria Heights & Bowne Plgd C/S QG-1015M | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPIBN5 | CPI PH1- RC- Astoria Heights & Bowne Plgd C/S QG-1015M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2017-03-27 | 2023-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPIBOW | CPI PH1- Bowne Playground R/C Q308-115M | 1 | DEVELOP SCOPE | 2014-07-01 | 2014-09-28 | 2014-07-01 | 2014-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPIBOW | CPI PH1- Bowne Playground R/C Q308-115M | 2 | DESIGN | 2014-09-29 | 2014-12-27 | 2014-12-28 | 2016-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPIBOW | CPI PH1- Bowne Playground R/C Q308-115M | 3 | BID/ REGISTER CONTRACT | 2014-12-28 | 2015-03-27 | 2016-03-27 | 2016-12-21
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPIBOW | CPI PH1- Bowne Playground R/C Q308-115M | 4 | CONSTRUCTION | 2015-03-28 | 2016-03-26 | 2016-12-22 | 2017-12-21
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPIBOW | CPI PH1- Bowne Playground R/C Q308-115M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-27 | 2017-03-26 | 2017-12-22 | 2023-02-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPICHP | CPI PH2 - Chappetto Square R/C Q066H-118M | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPICHP | CPI PH2 - Chappetto Square R/C Q066H-118M | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2016-12-28 | 2017-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPICHP | CPI PH2 - Chappetto Square R/C Q066H-118M | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2017-12-28 | 2018-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPICHP | CPI PH2 - Chappetto Square R/C Q066H-118M | 4 | CONSTRUCTION | 2018-09-24 | 2019-09-23 | 2018-09-24 | 2019-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPICHP | CPI PH2 - Chappetto Square R/C Q066H-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPICMA | CPI PH1- Louis Simeone Park R/C Q474-115M | 1 | DEVELOP SCOPE | 2014-07-01 | 2014-09-28 | 2014-07-01 | 2014-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPICMA | CPI PH1- Louis Simeone Park R/C Q474-115M | 2 | DESIGN | 2014-09-29 | 2014-12-27 | 2014-09-29 | 2014-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPICMA | CPI PH1- Louis Simeone Park R/C Q474-115M | 3 | BID/ REGISTER CONTRACT | 2014-12-28 | 2015-03-27 | 2014-12-28 | 2015-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPICMA | CPI PH1- Louis Simeone Park R/C Q474-115M | 4 | CONSTRUCTION | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2016-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPICMA | CPI PH1- Louis Simeone Park R/C Q474-115M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2021-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPIP35 | CPI PH2 - Playground Thirty Five XXXV R/C Q296-116M | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPIP35 | CPI PH2 - Playground Thirty Five XXXV R/C Q296-116M | 2 | DESIGN | 2016-12-28 | 2018-03-22 | 2016-12-28 | 2018-03-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPIP35 | CPI PH2 - Playground Thirty Five XXXV R/C Q296-116M | 3 | BID/ REGISTER CONTRACT | 2018-03-23 | 2018-12-17 | 2018-03-23 | 2018-12-17
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPIP35 | CPI PH2 - Playground Thirty Five XXXV R/C Q296-116M | 4 | CONSTRUCTION | 2018-12-18 | 2020-12-16 | 2018-12-18 | 2020-12-16
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPIP35 | CPI PH2 - Playground Thirty Five XXXV R/C Q296-116M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-12-17 | 2021-12-16 | 2020-12-17 | 2021-12-16
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPIRCP | CPI PH1 - Conch Playground R/C Q394-115M | 1 | DEVELOP SCOPE | 2014-07-01 | 2014-09-28 | 2014-07-01 | 2014-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPIRCP | CPI PH1 - Conch Playground R/C Q394-115M | 2 | DESIGN | 2014-09-29 | 2014-12-27 | 2014-09-29 | 2014-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPIRCP | CPI PH1 - Conch Playground R/C Q394-115M | 3 | BID/ REGISTER CONTRACT | 2014-12-28 | 2015-03-27 | 2014-12-28 | 2015-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPIRCP | CPI PH1 - Conch Playground R/C Q394-115M | 4 | CONSTRUCTION | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2016-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPIRCP | CPI PH1 - Conch Playground R/C Q394-115M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2021-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPPLGD | Cunningham Park Upper Playground R/C | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPPLGD | Cunningham Park Upper Playground R/C | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPPLGD | Cunningham Park Upper Playground R/C | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPPLGD | Cunningham Park Upper Playground R/C | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPPLGD | Cunningham Park Upper Playground R/C | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2023-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPSLIT | College Point Sports Park - New Lighting | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPSLIT | College Point Sports Park - New Lighting | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPSLIT | College Point Sports Park - New Lighting | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPSLIT | College Point Sports Park - New Lighting | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPSLIT | College Point Sports Park - New Lighting | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPTLCS | Captain Tilly Park Comfort Station | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPTLCS | Captain Tilly Park Comfort Station | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPTLCS | Captain Tilly Park Comfort Station | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPTLCS | Captain Tilly Park Comfort Station | 4 | CONSTRUCTION | 2020-09-23 | 2022-03-21 | 2020-09-23 | 2022-03-21
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPTLCS | Captain Tilly Park Comfort Station | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-22 | 2023-03-21 | 2022-03-22 | 2023-03-21
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CROCLL | Crocheron Park Little League Field Upgrades Q012-117M | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2015-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CROCLL | Crocheron Park Little League Field Upgrades Q012-117M | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2015-09-29 | 2015-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CROCLL | Crocheron Park Little League Field Upgrades Q012-117M | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2015-12-28 | 2016-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CROCLL | Crocheron Park Little League Field Upgrades Q012-117M | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CROCLL | Crocheron Park Little League Field Upgrades Q012-117M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2017-03-27 | 2021-06-29
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CUN210 | CUNNINGHAM PARK 210 ST PLAYGROUND UPGRADE Q021-220M | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CUN210 | CUNNINGHAM PARK 210 ST PLAYGROUND UPGRADE Q021-220M | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CUN210 | CUNNINGHAM PARK 210 ST PLAYGROUND UPGRADE Q021-220M | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CUN210 | CUNNINGHAM PARK 210 ST PLAYGROUND UPGRADE Q021-220M | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CUN210 | CUNNINGHAM PARK 210 ST PLAYGROUND UPGRADE Q021-220M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CUNNSL | Recon Upper Cunningham Park sewer line | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CUNNSL | Recon Upper Cunningham Park sewer line | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CUNNSL | Recon Upper Cunningham Park sewer line | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CUNNSL | Recon Upper Cunningham Park sewer line | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CUNNSL | Recon Upper Cunningham Park sewer line | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CUNPLG | Redwood Playground in Cunningham Park R/C Q021-117M | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2015-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CUNPLG | Redwood Playground in Cunningham Park R/C Q021-117M | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2015-09-29 | 2015-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CUNPLG | Redwood Playground in Cunningham Park R/C Q021-117M | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2015-12-28 | 2016-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CUNPLG | Redwood Playground in Cunningham Park R/C Q021-117M | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CUNPLG | Redwood Playground in Cunningham Park R/C Q021-117M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2017-03-27 | 2023-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4DUTCH1 | Dutch Kills Comfort Station Q218-216M | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4DUTCH1 | Dutch Kills Comfort Station Q218-216M | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2016-12-28 | 2017-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4DUTCH1 | Dutch Kills Comfort Station Q218-216M | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2017-12-28 | 2018-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4DUTCH1 | Dutch Kills Comfort Station Q218-216M | 4 | CONSTRUCTION | 2018-09-24 | 2020-03-21 | 2018-09-24 | 2020-03-21
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4DUTCH1 | Dutch Kills Comfort Station Q218-216M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-03-22 | 2021-03-21 | 2020-03-22 | 2021-03-21
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4EABTRC | Emerald Ash Borer (EAB) Tree Remove Queens QG-819M | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4EABTRC | Emerald Ash Borer (EAB) Tree Remove Queens QG-819M | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4EABTRC | Emerald Ash Borer (EAB) Tree Remove Queens QG-819M | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4EABTRC | Emerald Ash Borer (EAB) Tree Remove Queens QG-819M | 4 | CONSTRUCTION | 2020-09-23 | 2022-09-22 | 2020-09-23 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4EABTRC | Emerald Ash Borer (EAB) Tree Remove Queens QG-819M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4ELMPRK | EAST ELMHURST PARK | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4ELMPRK | EAST ELMHURST PARK | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4ELMPRK | EAST ELMHURST PARK | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4ELMPRK | EAST ELMHURST PARK | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4ELMPRK | EAST ELMHURST PARK | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4EMLDRF | Recon of Roofing systems at Emerald | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4EMLDRF | Recon of Roofing systems at Emerald | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4EMLDRF | Recon of Roofing systems at Emerald | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4EMLDRF | Recon of Roofing systems at Emerald | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4EMLDRF | Recon of Roofing systems at Emerald | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FITZPG | FITZGERALD PLAYGROUND | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FITZPG | FITZGERALD PLAYGROUND | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FITZPG | FITZGERALD PLAYGROUND | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FITZPG | FITZGERALD PLAYGROUND | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FITZPG | FITZGERALD PLAYGROUND | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FLBAY2 | FLUSHING BAY DREDGING & CONSTR OF BOAT RAMP Q099-300M | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FLBAY2 | FLUSHING BAY DREDGING & CONSTR OF BOAT RAMP Q099-300M | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FLBAY2 | FLUSHING BAY DREDGING & CONSTR OF BOAT RAMP Q099-300M | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FLBAY2 | FLUSHING BAY DREDGING & CONSTR OF BOAT RAMP Q099-300M | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FLBAY2 | FLUSHING BAY DREDGING & CONSTR OF BOAT RAMP Q099-300M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FMCPIC | Recon ice plant at FMCP, Queens | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FMCPIC | Recon ice plant at FMCP, Queens | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FMCPIC | Recon ice plant at FMCP, Queens | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FMCPIC | Recon ice plant at FMCP, Queens | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FMCPIC | Recon ice plant at FMCP, Queens | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FMGARG | Flushing Meadows Corona Park Garage | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2015-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FMGARG | Flushing Meadows Corona Park Garage | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2015-12-28 | 2017-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FMGARG | Flushing Meadows Corona Park Garage | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2017-03-27 | 2017-12-21
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FMGARG | Flushing Meadows Corona Park Garage | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2017-12-22 | 2018-12-21
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FMGARG | Flushing Meadows Corona Park Garage | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2018-12-22 | 2019-12-21
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FMMAUR | FMCP Mauro Playground Upgrades Q099-917M | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2015-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FMMAUR | FMCP Mauro Playground Upgrades Q099-917M | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2015-09-29 | 2015-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FMMAUR | FMCP Mauro Playground Upgrades Q099-917M | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2015-12-28 | 2016-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FMMAUR | FMCP Mauro Playground Upgrades Q099-917M | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FMMAUR | FMCP Mauro Playground Upgrades Q099-917M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2017-03-27 | 2021-05-31
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FRDJPU | FREDERICK JUDGE PLAYGROUND UPGRADES Q119-120M | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FRDJPU | FREDERICK JUDGE PLAYGROUND UPGRADES Q119-120M | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FRDJPU | FREDERICK JUDGE PLAYGROUND UPGRADES Q119-120M | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FRDJPU | FREDERICK JUDGE PLAYGROUND UPGRADES Q119-120M | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FRDJPU | FREDERICK JUDGE PLAYGROUND UPGRADES Q119-120M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FTTOTB | FT. TOTTEN PK CHAPEL & COMMANDER'S HOUSE Q458-112M | 1 | DEVELOP SCOPE | 2011-07-01 | 2011-09-28 | 2011-07-01 | 2011-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FTTOTB | FT. TOTTEN PK CHAPEL & COMMANDER'S HOUSE Q458-112M | 2 | DESIGN | 2011-09-29 | 2011-12-27 | 2011-09-29 | 2011-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FTTOTB | FT. TOTTEN PK CHAPEL & COMMANDER'S HOUSE Q458-112M | 3 | BID/ REGISTER CONTRACT | 2011-12-28 | 2012-03-26 | 2016-03-11 | 2017-02-01
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FTTOTB | FT. TOTTEN PK CHAPEL & COMMANDER'S HOUSE Q458-112M | 4 | CONSTRUCTION | 2012-03-27 | 2013-03-26 | 2017-02-02 | 2017-05-05
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FTTOTB | FT. TOTTEN PK CHAPEL & COMMANDER'S HOUSE Q458-112M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-03-27 | 2014-03-26 | 2017-05-06 | 2020-02-09
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FTTOTC | FT. TOTTEN ELEVATORS Q458 | 1 | DEVELOP SCOPE | 2016-08-01 | 2017-01-27 | 2016-08-01 | 2017-01-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FTTOTC | FT. TOTTEN ELEVATORS Q458 | 2 | DESIGN | 2017-01-28 | 2018-01-27 | 2017-01-28 | 2018-01-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FTTOTC | FT. TOTTEN ELEVATORS Q458 | 3 | BID/ REGISTER CONTRACT | 2018-01-28 | 2018-10-24 | 2018-01-28 | 2018-10-24
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FTTOTC | FT. TOTTEN ELEVATORS Q458 | 4 | CONSTRUCTION | 2018-10-25 | 2019-10-24 | 2018-10-25 | 2019-10-24
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FTTOTC | FT. TOTTEN ELEVATORS Q458 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-10-25 | 2020-10-23 | 2019-10-25 | 2020-10-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4GBLPLG | SEVEN GABLES PLAYGROUND | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4GBLPLG | SEVEN GABLES PLAYGROUND | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4GBLPLG | SEVEN GABLES PLAYGROUND | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4GBLPLG | SEVEN GABLES PLAYGROUND | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4GBLPLG | SEVEN GABLES PLAYGROUND | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4GLNOAK | Tenney Pk (Glen Oaks) Bball Ct./Play Equip. R/C Q310-118M | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2015-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4GLNOAK | Tenney Pk (Glen Oaks) Bball Ct./Play Equip. R/C Q310-118M | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2015-09-29 | 2015-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4GLNOAK | Tenney Pk (Glen Oaks) Bball Ct./Play Equip. R/C Q310-118M | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2015-12-28 | 2016-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4GLNOAK | Tenney Pk (Glen Oaks) Bball Ct./Play Equip. R/C Q310-118M | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4GLNOAK | Tenney Pk (Glen Oaks) Bball Ct./Play Equip. R/C Q310-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2017-03-27 | 2021-10-31
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4HARTRF | Recon of Roofing systems at Hart Comf Sta | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4HARTRF | Recon of Roofing systems at Hart Comf Sta | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4HARTRF | Recon of Roofing systems at Hart Comf Sta | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4HARTRF | Recon of Roofing systems at Hart Comf Sta | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4HARTRF | Recon of Roofing systems at Hart Comf Sta | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4HCHAND | HALLET'S COVE RENOVATION OF HANDBALL COURT AND FENCING | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4HCHAND | HALLET'S COVE RENOVATION OF HANDBALL COURT AND FENCING | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4HCHAND | HALLET'S COVE RENOVATION OF HANDBALL COURT AND FENCING | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4HCHAND | HALLET'S COVE RENOVATION OF HANDBALL COURT AND FENCING | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4HCHAND | HALLET'S COVE RENOVATION OF HANDBALL COURT AND FENCING | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4HCOVP2 | Hallet's Cove Playground MPPA Q226-119M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4HCOVP2 | Hallet's Cove Playground MPPA Q226-119M | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4HCOVP2 | Hallet's Cove Playground MPPA Q226-119M | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4HCOVP2 | Hallet's Cove Playground MPPA Q226-119M | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4HCOVP2 | Hallet's Cove Playground MPPA Q226-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4HCOVPG | Hallets Cove Playground R/C Q226-117M | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2010-07-01 | 2010-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4HCOVPG | Hallets Cove Playground R/C Q226-117M | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2010-12-28 | 2011-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4HCOVPG | Hallets Cove Playground R/C Q226-117M | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2011-12-28 | 2012-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4HCOVPG | Hallets Cove Playground R/C Q226-117M | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2012-09-23 | 2013-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4HCOVPG | Hallets Cove Playground R/C Q226-117M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2013-09-23 | 2023-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4HKRINK | Roller Hockey Rinks Multi-Site QG-416M | 3 | BID/ REGISTER CONTRACT | 2018-03-23 | 2018-12-17 | 2018-03-23 | 2018-12-17
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4HKRINK | Roller Hockey Rinks Multi-Site QG-416M | 4 | CONSTRUCTION | 2018-12-18 | 2020-12-16 | 2018-12-18 | 2020-12-16
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4HKRINK | Roller Hockey Rinks Multi-Site QG-416M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-12-17 | 2021-12-16 | 2020-12-17 | 2021-12-16
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4HVRMAN | Hoover Manton Park MPPA Reconstruction SOGR | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4HVRMAN | Hoover Manton Park MPPA Reconstruction SOGR | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4HVRMAN | Hoover Manton Park MPPA Reconstruction SOGR | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4HVRMAN | Hoover Manton Park MPPA Reconstruction SOGR | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4HVRMAN | Hoover Manton Park MPPA Reconstruction SOGR | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4IDLETB | IDLEWILD PARK CONSTRUCTION OF NATURE TRAIL AND BOARDWALK | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4IDLETB | IDLEWILD PARK CONSTRUCTION OF NATURE TRAIL AND BOARDWALK | 2 | DESIGN | 2016-12-28 | 2018-03-22 | 2016-12-28 | 2018-03-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4IDLETB | IDLEWILD PARK CONSTRUCTION OF NATURE TRAIL AND BOARDWALK | 3 | BID/ REGISTER CONTRACT | 2018-03-23 | 2018-12-17 | 2018-03-23 | 2018-12-17
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4IDLETB | IDLEWILD PARK CONSTRUCTION OF NATURE TRAIL AND BOARDWALK | 4 | CONSTRUCTION | 2018-12-18 | 2020-12-16 | 2018-12-18 | 2020-12-16
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4IDLETB | IDLEWILD PARK CONSTRUCTION OF NATURE TRAIL AND BOARDWALK | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-12-17 | 2021-12-16 | 2020-12-17 | 2021-12-16
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4JAUSTI | JOSEPH AUSTIN PLAYGROUND Q391-108M | 1 | DEVELOP SCOPE | 2007-07-01 | 2007-09-28 | 2005-11-30 | 2006-02-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4JAUSTI | JOSEPH AUSTIN PLAYGROUND Q391-108M | 2 | DESIGN | 2007-09-29 | 2007-12-27 | 2006-02-28 | 2006-05-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4JAUSTI | JOSEPH AUSTIN PLAYGROUND Q391-108M | 3 | BID/ REGISTER CONTRACT | 2007-12-28 | 2008-03-26 | 2006-05-29 | 2006-08-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4JAUSTI | JOSEPH AUSTIN PLAYGROUND Q391-108M | 4 | CONSTRUCTION | 2008-03-27 | 2009-03-26 | 2006-08-27 | 2007-08-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4JAUSTI | JOSEPH AUSTIN PLAYGROUND Q391-108M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2009-03-27 | 2010-03-26 | 2007-08-27 | 2014-04-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4JMMPP2 | JOE MICHAEL MILE PHASE 2 PATH RENO NORTH | 1 | DEVELOP SCOPE | 2020-07-01 | 2020-12-27 | 2020-07-01 | 2020-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4JMMPP2 | JOE MICHAEL MILE PHASE 2 PATH RENO NORTH | 2 | DESIGN | 2020-12-28 | 2021-12-27 | 2020-12-28 | 2021-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4JMMPP2 | JOE MICHAEL MILE PHASE 2 PATH RENO NORTH | 3 | BID/ REGISTER CONTRACT | 2021-12-28 | 2022-09-23 | 2021-12-28 | 2022-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4JMMPP2 | JOE MICHAEL MILE PHASE 2 PATH RENO NORTH | 4 | CONSTRUCTION | 2022-09-24 | 2023-09-23 | 2022-09-24 | 2023-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4JMMPP2 | JOE MICHAEL MILE PHASE 2 PATH RENO NORTH | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-24 | 2024-09-22 | 2023-09-24 | 2024-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4LATRUF | RUFUS KING MANOR & LEWIS H LATIMER HOUSE ROOFS QG-411M | 1 | DEVELOP SCOPE | 2010-07-01 | 2011-07-15 | 2010-07-01 | 2011-07-15
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4LATRUF | RUFUS KING MANOR & LEWIS H LATIMER HOUSE ROOFS QG-411M | 2 | DESIGN | 2011-07-16 | 2011-10-15 | 2011-07-16 | 2011-10-15
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4LATRUF | RUFUS KING MANOR & LEWIS H LATIMER HOUSE ROOFS QG-411M | 3 | BID/ REGISTER CONTRACT | 2011-10-16 | 2012-01-15 | 2011-10-16 | 2012-01-15
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4LATRUF | RUFUS KING MANOR & LEWIS H LATIMER HOUSE ROOFS QG-411M | 4 | CONSTRUCTION | 2012-01-16 | 2013-01-15 | 2012-01-16 | 2013-01-15
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4LATRUF | RUFUS KING MANOR & LEWIS H LATIMER HOUSE ROOFS QG-411M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-01-16 | 2014-01-17 | 2013-01-16 | 2018-03-31
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4LIBTPL | Recon pool deck at Liberty Pool, Queens | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4LIBTPL | Recon pool deck at Liberty Pool, Queens | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4LIBTPL | Recon pool deck at Liberty Pool, Queens | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4LIBTPL | Recon pool deck at Liberty Pool, Queens | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4LIBTPL | Recon pool deck at Liberty Pool, Queens | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4LINDE2 | Park of the Americas - Plygrd & Synthetic Turf R/C Q026-118M | 1 | DEVELOP SCOPE | 2014-07-01 | 2014-09-28 | 2014-07-01 | 2014-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4LINDE2 | Park of the Americas - Plygrd & Synthetic Turf R/C Q026-118M | 2 | DESIGN | 2014-09-29 | 2014-12-27 | 2014-09-29 | 2014-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4LINDE2 | Park of the Americas - Plygrd & Synthetic Turf R/C Q026-118M | 3 | BID/ REGISTER CONTRACT | 2014-12-28 | 2015-03-27 | 2014-12-28 | 2015-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4LINDE2 | Park of the Americas - Plygrd & Synthetic Turf R/C Q026-118M | 4 | CONSTRUCTION | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2016-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4LINDE2 | Park of the Americas - Plygrd & Synthetic Turf R/C Q026-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2021-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4LTLBSH | Nathan Weidenbaum Park Playground R/C Q205B-118M | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4LTLBSH | Nathan Weidenbaum Park Playground R/C Q205B-118M | 2 | DESIGN | 2016-12-28 | 2018-03-22 | 2016-12-28 | 2017-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4LTLBSH | Nathan Weidenbaum Park Playground R/C Q205B-118M | 3 | BID/ REGISTER CONTRACT | 2018-03-23 | 2018-12-17 | 2017-12-28 | 2018-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4LTLBSH | Nathan Weidenbaum Park Playground R/C Q205B-118M | 4 | CONSTRUCTION | 2018-12-18 | 2020-12-16 | 2018-09-24 | 2019-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4LTLBSH | Nathan Weidenbaum Park Playground R/C Q205B-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-12-17 | 2021-12-16 | 2019-09-24 | 2020-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4MARFAJ | MARIO FAJARDO PLAYGROUND | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4MARFAJ | MARIO FAJARDO PLAYGROUND | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4MARFAJ | MARIO FAJARDO PLAYGROUND | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4MARFAJ | MARIO FAJARDO PLAYGROUND | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4MARFAJ | MARIO FAJARDO PLAYGROUND | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4NFWF01 | NFWF - Alley Pond Park Living Shoreline Cons Q001-118M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4NFWF01 | NFWF - Alley Pond Park Living Shoreline Cons Q001-118M | 2 | DESIGN | 2017-12-28 | 2019-06-20 | 2017-12-28 | 2019-06-20
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4NFWF01 | NFWF - Alley Pond Park Living Shoreline Cons Q001-118M | 3 | BID/ REGISTER CONTRACT | 2019-06-21 | 2020-03-16 | 2019-06-21 | 2020-03-16
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4NFWF01 | NFWF - Alley Pond Park Living Shoreline Cons Q001-118M | 4 | CONSTRUCTION | 2020-03-17 | 2022-03-16 | 2020-03-17 | 2022-03-16
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4NFWF01 | NFWF - Alley Pond Park Living Shoreline Cons Q001-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-17 | 2024-03-15 | 2022-03-17 | 2024-03-15
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4NNANPG | NOONAN PLAYGROUND- Q044-119M | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4NNANPG | NOONAN PLAYGROUND- Q044-119M | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4NNANPG | NOONAN PLAYGROUND- Q044-119M | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4NNANPG | NOONAN PLAYGROUND- Q044-119M | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4NNANPG | NOONAN PLAYGROUND- Q044-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4OLMST3 | OLMSTED CTR FURNITURE Q099-808MA1 | 1 | DEVELOP SCOPE | 2009-07-01 | 2009-09-28 | 2009-07-01 | 2009-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4OLMST3 | OLMSTED CTR FURNITURE Q099-808MA1 | 2 | DESIGN | 2009-09-29 | 2009-12-27 | 2009-09-29 | 2009-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4OLMST3 | OLMSTED CTR FURNITURE Q099-808MA1 | 3 | BID/ REGISTER CONTRACT | 2009-12-28 | 2010-03-27 | 2009-12-28 | 2010-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4OLMST3 | OLMSTED CTR FURNITURE Q099-808MA1 | 4 | CONSTRUCTION | 2010-03-28 | 2011-03-27 | 2010-03-28 | 2011-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4OLMST3 | OLMSTED CTR FURNITURE Q099-808MA1 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2011-03-28 | 2012-03-26 | 2011-03-28 | 2015-12-31
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4OLMST4 | OLMSTED CTR RC (BUILDING) Q099-808MA | 1 | DEVELOP SCOPE | 2010-07-01 | 2010-09-28 | 2010-07-01 | 2010-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4OLMST4 | OLMSTED CTR RC (BUILDING) Q099-808MA | 2 | DESIGN | 2010-09-29 | 2010-12-27 | 2013-06-21 | 2013-09-18
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4OLMST4 | OLMSTED CTR RC (BUILDING) Q099-808MA | 3 | BID/ REGISTER CONTRACT | 2010-12-28 | 2011-03-27 | 2013-09-18 | 2014-03-17
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4OLMST4 | OLMSTED CTR RC (BUILDING) Q099-808MA | 4 | CONSTRUCTION | 2011-03-28 | 2012-03-26 | 2014-03-18 | 2019-02-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4OLMST4 | OLMSTED CTR RC (BUILDING) Q099-808MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-03-27 | 2013-03-26 | 2019-03-01 | 2020-02-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4OVERLK | Overlook Park R/C Q299-117M | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4OVERLK | Overlook Park R/C Q299-117M | 2 | DESIGN | 2016-12-28 | 2018-03-22 | 2016-12-28 | 2018-03-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4OVERLK | Overlook Park R/C Q299-117M | 3 | BID/ REGISTER CONTRACT | 2018-03-23 | 2018-12-17 | 2018-03-23 | 2018-12-17
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4OVERLK | Overlook Park R/C Q299-117M | 4 | CONSTRUCTION | 2018-12-18 | 2020-12-16 | 2018-12-18 | 2020-12-16
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4OVERLK | Overlook Park R/C Q299-117M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-12-17 | 2021-12-16 | 2020-12-17 | 2021-12-16
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PASAIR | Passerelle Building/ Port Arth. AirTrain | 1 | DEVELOP SCOPE | 2020-07-01 | 2020-12-27 | 2020-07-01 | 2020-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PASAIR | Passerelle Building/ Port Arth. AirTrain | 2 | DESIGN | 2020-12-28 | 2021-12-27 | 2020-12-28 | 2021-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PASAIR | Passerelle Building/ Port Arth. AirTrain | 3 | BID/ REGISTER CONTRACT | 2021-12-28 | 2022-09-23 | 2021-12-28 | 2022-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PASAIR | Passerelle Building/ Port Arth. AirTrain | 4 | CONSTRUCTION | 2022-09-24 | 2023-09-23 | 2022-09-24 | 2023-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PASAIR | Passerelle Building/ Port Arth. AirTrain | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-24 | 2024-09-22 | 2023-09-24 | 2024-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PDLBRC | Lost Battalion Rec Ctr RC Q401-115M | 1 | DEVELOP SCOPE | 2014-07-01 | 2014-09-28 | 2014-07-01 | 2017-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PDLBRC | Lost Battalion Rec Ctr RC Q401-115M | 2 | DESIGN | 2014-09-29 | 2014-12-27 | 2017-09-29 | 2017-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PDLBRC | Lost Battalion Rec Ctr RC Q401-115M | 3 | BID/ REGISTER CONTRACT | 2014-12-28 | 2015-03-27 | 2017-12-28 | 2018-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PDLBRC | Lost Battalion Rec Ctr RC Q401-115M | 4 | CONSTRUCTION | 2015-03-28 | 2016-03-26 | 2018-03-28 | 2019-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PDLBRC | Lost Battalion Rec Ctr RC Q401-115M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-27 | 2017-03-26 | 2019-03-28 | 2020-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PL15A1 | A.R.R.O.W. Field House Community Garden & Plgd QG-715M $ | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PL15A1 | A.R.R.O.W. Field House Community Garden & Plgd QG-715M $ | 2 | DESIGN | 2016-12-28 | 2018-12-27 | 2016-12-28 | 2018-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PL15A1 | A.R.R.O.W. Field House Community Garden & Plgd QG-715M $ | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PL15A1 | A.R.R.O.W. Field House Community Garden & Plgd QG-715M $ | 4 | CONSTRUCTION | 2019-09-24 | 2021-09-22 | 2019-09-24 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PL15A1 | A.R.R.O.W. Field House Community Garden & Plgd QG-715M $ | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PL15A2 | Ruoff Triangle R/C QG-715M $ | 2 | DESIGN | 2016-12-28 | 2018-12-27 | 2016-12-28 | 2018-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PL15A2 | Ruoff Triangle R/C QG-715M $ | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PL15A2 | Ruoff Triangle R/C QG-715M $ | 4 | CONSTRUCTION | 2019-09-24 | 2021-09-22 | 2019-09-24 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PL15A2 | Ruoff Triangle R/C QG-715M $ | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PLG12A | Reconstruction of plgr, Borough ofQueens (QG-112M) | 1 | DEVELOP SCOPE | 2011-07-01 | 2011-09-28 | 2011-07-01 | 2011-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PLG12A | Reconstruction of plgr, Borough ofQueens (QG-112M) | 2 | DESIGN | 2011-09-29 | 2011-12-27 | 2011-09-29 | 2011-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PLG12A | Reconstruction of plgr, Borough ofQueens (QG-112M) | 3 | BID/ REGISTER CONTRACT | 2011-12-28 | 2012-03-26 | 2011-12-28 | 2012-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PLG12A | Reconstruction of plgr, Borough ofQueens (QG-112M) | 4 | CONSTRUCTION | 2012-03-27 | 2013-03-26 | 2012-03-27 | 2013-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PLG12A | Reconstruction of plgr, Borough ofQueens (QG-112M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-03-27 | 2014-03-26 | 2013-03-27 | 2023-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PLG12B | FY12 Reconstruction of plgr Queens QG-212M | 1 | DEVELOP SCOPE | 2011-07-01 | 2011-09-28 | 2011-07-01 | 2011-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PLG12B | FY12 Reconstruction of plgr Queens QG-212M | 2 | DESIGN | 2011-09-29 | 2011-12-27 | 2011-09-29 | 2011-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PLG12B | FY12 Reconstruction of plgr Queens QG-212M | 3 | BID/ REGISTER CONTRACT | 2011-12-28 | 2012-03-26 | 2011-12-28 | 2012-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PLG12B | FY12 Reconstruction of plgr Queens QG-212M | 4 | CONSTRUCTION | 2012-03-27 | 2013-03-26 | 2012-03-27 | 2013-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PLG12B | FY12 Reconstruction of plgr Queens QG-212M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-03-27 | 2014-03-26 | 2013-03-27 | 2021-03-31
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PLG13F | FY13 Queens Plgrd Multisite QG-1313M | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2013-09-29 | 2013-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PLG13F | FY13 Queens Plgrd Multisite QG-1313M | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2013-12-28 | 2014-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PLG13F | FY13 Queens Plgrd Multisite QG-1313M | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2014-03-28 | 2015-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PLG13F | FY13 Queens Plgrd Multisite QG-1313M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2023-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PLG13G | FY13 Queens Plgrd Multisite QG-913M | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2013-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PLG13G | FY13 Queens Plgrd Multisite QG-913M | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2013-09-29 | 2013-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PLG13G | FY13 Queens Plgrd Multisite QG-913M | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2013-12-28 | 2014-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PLG13G | FY13 Queens Plgrd Multisite QG-913M | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2014-03-28 | 2015-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PLG13G | FY13 Queens Plgrd Multisite QG-913M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2016-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PLG13H | FY13 Queens Plgrd Multisite QG-514MA | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2013-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PLG13H | FY13 Queens Plgrd Multisite QG-514MA | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2013-09-29 | 2013-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PLG13H | FY13 Queens Plgrd Multisite QG-514MA | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2013-12-28 | 2014-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PLG13H | FY13 Queens Plgrd Multisite QG-514MA | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2014-03-28 | 2015-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PLG13H | FY13 Queens Plgrd Multisite QG-514MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2022-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PLG13M | FY13 Queens Plgrd Multisite QG-1913M | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2013-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PLG13M | FY13 Queens Plgrd Multisite QG-1913M | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2013-12-28 | 2015-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PLG13M | FY13 Queens Plgrd Multisite QG-1913M | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2015-12-28 | 2016-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PLG13M | FY13 Queens Plgrd Multisite QG-1913M | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2016-09-23 | 2018-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PLG13M | FY13 Queens Plgrd Multisite QG-1913M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2018-09-23 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PNYT29 | PlaNYC FY18 Street Tree Queens CB 7,8,11 QG- | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PNYT29 | PlaNYC FY18 Street Tree Queens CB 7,8,11 QG- | 2 | DESIGN | 2017-12-28 | 2018-06-25 | 2017-12-28 | 2018-06-25
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PNYT29 | PlaNYC FY18 Street Tree Queens CB 7,8,11 QG- | 3 | BID/ REGISTER CONTRACT | 2018-06-26 | 2019-03-22 | 2018-06-26 | 2019-03-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PNYT29 | PlaNYC FY18 Street Tree Queens CB 7,8,11 QG- | 4 | CONSTRUCTION | 2019-03-23 | 2020-09-12 | 2019-03-23 | 2020-09-12
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PNYT29 | PlaNYC FY18 Street Tree Queens CB 7,8,11 QG- | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-13 | 2022-09-12 | 2020-09-13 | 2022-09-12
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PNYT30 | PlaNYC FY18 Street Tree Queens CB 12,13,14 | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PNYT30 | PlaNYC FY18 Street Tree Queens CB 12,13,14 | 2 | DESIGN | 2017-12-28 | 2018-06-25 | 2017-12-28 | 2018-06-25
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PNYT30 | PlaNYC FY18 Street Tree Queens CB 12,13,14 | 3 | BID/ REGISTER CONTRACT | 2018-06-26 | 2019-03-22 | 2018-06-26 | 2019-03-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PNYT30 | PlaNYC FY18 Street Tree Queens CB 12,13,14 | 4 | CONSTRUCTION | 2019-03-23 | 2020-09-12 | 2019-03-23 | 2020-09-12
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PNYT30 | PlaNYC FY18 Street Tree Queens CB 12,13,14 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-13 | 2022-09-12 | 2020-09-13 | 2022-09-12
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PS183P | P.S. 183 PLAYGROUND RC Q403-111M | 1 | DEVELOP SCOPE | 2010-07-01 | 2010-09-28 | 2010-07-01 | 2010-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PS183P | P.S. 183 PLAYGROUND RC Q403-111M | 2 | DESIGN | 2010-09-29 | 2010-12-27 | 2010-09-29 | 2010-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PS183P | P.S. 183 PLAYGROUND RC Q403-111M | 3 | BID/ REGISTER CONTRACT | 2010-12-28 | 2011-03-27 | 2010-12-28 | 2011-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PS183P | P.S. 183 PLAYGROUND RC Q403-111M | 4 | CONSTRUCTION | 2011-03-28 | 2012-03-26 | 2011-03-28 | 2012-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PS183P | P.S. 183 PLAYGROUND RC Q403-111M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-03-27 | 2013-03-26 | 2012-03-27 | 2014-04-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PWOB01 | PWOB - FMCP Henry Hudson Entrance Q099-317M | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PWOB01 | PWOB - FMCP Henry Hudson Entrance Q099-317M | 2 | DESIGN | 2016-12-28 | 2018-12-27 | 2016-12-28 | 2017-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PWOB01 | PWOB - FMCP Henry Hudson Entrance Q099-317M | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2017-12-28 | 2018-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PWOB01 | PWOB - FMCP Henry Hudson Entrance Q099-317M | 4 | CONSTRUCTION | 2019-09-24 | 2021-09-22 | 2018-09-24 | 2019-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PWOB01 | PWOB - FMCP Henry Hudson Entrance Q099-317M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2019-09-24 | 2020-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4QCFMEC | QUEENS COUNTY FARM MUSEUM--CONSTRUCTION OF NEW EDUCATION CTR | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4QCFMEC | QUEENS COUNTY FARM MUSEUM--CONSTRUCTION OF NEW EDUCATION CTR | 2 | DESIGN | 2019-12-28 | 2021-12-26 | 2019-12-28 | 2021-12-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4QCFMEC | QUEENS COUNTY FARM MUSEUM--CONSTRUCTION OF NEW EDUCATION CTR | 3 | BID/ REGISTER CONTRACT | 2021-12-27 | 2022-09-22 | 2021-12-27 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4QCFMEC | QUEENS COUNTY FARM MUSEUM--CONSTRUCTION OF NEW EDUCATION CTR | 4 | CONSTRUCTION | 2022-09-23 | 2024-09-21 | 2022-09-23 | 2024-09-21
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4QCFMEC | QUEENS COUNTY FARM MUSEUM--CONSTRUCTION OF NEW EDUCATION CTR | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-09-22 | 2025-09-21 | 2024-09-22 | 2025-09-21
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4QCMGL2 | Queens County Farm-Gas Line Part II | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4QCMGL2 | Queens County Farm-Gas Line Part II | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4QCMGL2 | Queens County Farm-Gas Line Part II | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4QCMGL2 | Queens County Farm-Gas Line Part II | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4QCMGL2 | Queens County Farm-Gas Line Part II | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4QMULT2 | QUEENS MULTISITE | 1 | DEVELOP SCOPE | 2005-07-01 | 2005-09-28 | 2005-07-01 | 2005-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4QMULT2 | QUEENS MULTISITE | 2 | DESIGN | 2005-09-29 | 2005-12-27 | 2005-09-29 | 2005-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4QMULT2 | QUEENS MULTISITE | 3 | BID/ REGISTER CONTRACT | 2005-12-28 | 2006-03-27 | 2005-12-28 | 2006-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4QMULT2 | QUEENS MULTISITE | 4 | CONSTRUCTION | 2006-03-28 | 2007-03-27 | 2006-03-28 | 2007-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4QMULT2 | QUEENS MULTISITE | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2007-03-28 | 2008-03-26 | 2007-03-28 | 2025-04-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4QNHSRC | QUEENS HISTORICAL SOCIETY CONSTRUCTION AND RENOVATION | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4QNHSRC | QUEENS HISTORICAL SOCIETY CONSTRUCTION AND RENOVATION | 2 | DESIGN | 2019-12-28 | 2021-12-26 | 2019-12-28 | 2021-12-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4QNHSRC | QUEENS HISTORICAL SOCIETY CONSTRUCTION AND RENOVATION | 3 | BID/ REGISTER CONTRACT | 2021-12-27 | 2022-09-22 | 2021-12-27 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4QNHSRC | QUEENS HISTORICAL SOCIETY CONSTRUCTION AND RENOVATION | 4 | CONSTRUCTION | 2022-09-23 | 2024-09-21 | 2022-09-23 | 2024-09-21
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4QNHSRC | QUEENS HISTORICAL SOCIETY CONSTRUCTION AND RENOVATION | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-09-22 | 2025-09-21 | 2024-09-22 | 2025-09-21
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4QNPAV1 | State of Good Repair - Queens | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4QNPAV1 | State of Good Repair - Queens | 2 | DESIGN | 2019-12-28 | 2021-06-24 | 2019-12-28 | 2021-06-24
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4QNPAV1 | State of Good Repair - Queens | 3 | BID/ REGISTER CONTRACT | 2021-06-25 | 2022-03-21 | 2021-06-25 | 2022-03-21
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4QNPAV1 | State of Good Repair - Queens | 4 | CONSTRUCTION | 2022-03-22 | 2023-09-17 | 2022-03-22 | 2023-09-17
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4QNPAV1 | State of Good Repair - Queens | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-18 | 2024-09-16 | 2023-09-18 | 2024-09-16
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4QSTORE | QUEENS STOREHOUSE Q099-520M | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4QSTORE | QUEENS STOREHOUSE Q099-520M | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4QSTORE | QUEENS STOREHOUSE Q099-520M | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4QSTORE | QUEENS STOREHOUSE Q099-520M | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4QSTORE | QUEENS STOREHOUSE Q099-520M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4QWCABR | Queens Wildlife Center Marsh Bridge Repair | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2015-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4QWCABR | Queens Wildlife Center Marsh Bridge Repair | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2015-09-29 | 2015-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4QWCABR | Queens Wildlife Center Marsh Bridge Repair | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2015-12-28 | 2016-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4QWCABR | Queens Wildlife Center Marsh Bridge Repair | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4QWCABR | Queens Wildlife Center Marsh Bridge Repair | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2017-03-27 | 2018-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4QWCAMS | Queens Wildlife Center Aviary Mesh Replacement | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2015-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4QWCAMS | Queens Wildlife Center Aviary Mesh Replacement | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2015-09-29 | 2015-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4QWCAMS | Queens Wildlife Center Aviary Mesh Replacement | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2015-12-28 | 2016-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4QWCAMS | Queens Wildlife Center Aviary Mesh Replacement | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4QWCAMS | Queens Wildlife Center Aviary Mesh Replacement | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2017-03-27 | 2018-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4RAINE2 | Rainey Pk Picnic Grove, Bsktball Ct, & Dog Run R/C Q048-119M | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2015-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4RAINE2 | Rainey Pk Picnic Grove, Bsktball Ct, & Dog Run R/C Q048-119M | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2015-09-29 | 2015-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4RAINE2 | Rainey Pk Picnic Grove, Bsktball Ct, & Dog Run R/C Q048-119M | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2015-12-28 | 2016-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4RAINE2 | Rainey Pk Picnic Grove, Bsktball Ct, & Dog Run R/C Q048-119M | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4RAINE2 | Rainey Pk Picnic Grove, Bsktball Ct, & Dog Run R/C Q048-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2017-03-27 | 2022-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4RCKHQS | Rockaway Operational Headquarters-Supplement Funding | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4RCKHQS | Rockaway Operational Headquarters-Supplement Funding | 2 | DESIGN | 2019-12-28 | 2021-12-26 | 2019-12-28 | 2021-12-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4RCKHQS | Rockaway Operational Headquarters-Supplement Funding | 3 | BID/ REGISTER CONTRACT | 2021-12-27 | 2022-09-22 | 2021-12-27 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4RCKHQS | Rockaway Operational Headquarters-Supplement Funding | 4 | CONSTRUCTION | 2022-09-23 | 2024-09-21 | 2022-09-23 | 2024-09-21
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4RCKHQS | Rockaway Operational Headquarters-Supplement Funding | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-09-22 | 2025-09-21 | 2024-09-22 | 2025-09-21
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4RDGEWD | Rosemary's Plgd R/C Q398-117M | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2015-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4RDGEWD | Rosemary's Plgd R/C Q398-117M | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2015-09-29 | 2015-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4RDGEWD | Rosemary's Plgd R/C Q398-117M | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2015-12-28 | 2016-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4RDGEWD | Rosemary's Plgd R/C Q398-117M | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4RDGEWD | Rosemary's Plgd R/C Q398-117M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2017-03-27 | 2021-01-03
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4RGROI2 | Rockaway Beach Reformulation- Groin removal & crossing cons | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4RGROI2 | Rockaway Beach Reformulation- Groin removal & crossing cons | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4RGROI2 | Rockaway Beach Reformulation- Groin removal & crossing cons | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4RGROI2 | Rockaway Beach Reformulation- Groin removal & crossing cons | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4RGROI2 | Rockaway Beach Reformulation- Groin removal & crossing cons | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2024-09-22 | 2022-09-23 | 2024-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SAND01 | SANDY - Sunset Cove Salt Marsh Restoration Q498-115M | 4 | CONSTRUCTION | 2019-09-24 | 2021-09-22 | 2019-09-24 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SAND01 | SANDY - Sunset Cove Salt Marsh Restoration Q498-115M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SAND02 | SANDY - Spring Creek Pk GI Resiliency Q165-116MA | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SAND02 | SANDY - Spring Creek Pk GI Resiliency Q165-116MA | 2 | DESIGN | 2016-12-28 | 2018-03-22 | 2016-12-28 | 2018-03-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SAND02 | SANDY - Spring Creek Pk GI Resiliency Q165-116MA | 3 | BID/ REGISTER CONTRACT | 2018-03-23 | 2018-12-17 | 2018-03-23 | 2018-12-17
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SAND02 | SANDY - Spring Creek Pk GI Resiliency Q165-116MA | 4 | CONSTRUCTION | 2018-12-18 | 2020-12-16 | 2018-12-18 | 2020-12-16
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SAND02 | SANDY - Spring Creek Pk GI Resiliency Q165-116MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-12-17 | 2021-12-16 | 2020-12-17 | 2021-12-16
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SHREAC | Shorefront Parkway Adventure Course Q163-218M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SHREAC | Shorefront Parkway Adventure Course Q163-218M | 2 | DESIGN | 2017-12-28 | 2019-06-20 | 2017-12-28 | 2019-06-20
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SHREAC | Shorefront Parkway Adventure Course Q163-218M | 3 | BID/ REGISTER CONTRACT | 2019-06-21 | 2020-03-16 | 2019-06-21 | 2020-03-16
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SHREAC | Shorefront Parkway Adventure Course Q163-218M | 4 | CONSTRUCTION | 2020-03-17 | 2021-09-07 | 2020-03-17 | 2021-09-07
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SHREAC | Shorefront Parkway Adventure Course Q163-218M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-08 | 2022-09-07 | 2021-09-08 | 2022-09-07
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SHREDP | Shorefront Parkway Dog Run Cons. Q163-118M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SHREDP | Shorefront Parkway Dog Run Cons. Q163-118M | 2 | DESIGN | 2017-12-28 | 2019-06-20 | 2017-12-28 | 2019-06-20
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SHREDP | Shorefront Parkway Dog Run Cons. Q163-118M | 3 | BID/ REGISTER CONTRACT | 2019-06-21 | 2020-03-16 | 2019-06-21 | 2020-03-16
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SHREDP | Shorefront Parkway Dog Run Cons. Q163-118M | 4 | CONSTRUCTION | 2020-03-17 | 2021-09-07 | 2020-03-17 | 2021-09-07
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SHREDP | Shorefront Parkway Dog Run Cons. Q163-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-08 | 2022-09-07 | 2021-09-08 | 2022-09-07
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SHREPG | Shorefront Tot Playground and Plaza Area Q163-318M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SHREPG | Shorefront Tot Playground and Plaza Area Q163-318M | 2 | DESIGN | 2017-12-28 | 2019-06-20 | 2017-12-28 | 2019-06-20
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SHREPG | Shorefront Tot Playground and Plaza Area Q163-318M | 3 | BID/ REGISTER CONTRACT | 2019-06-21 | 2020-03-16 | 2019-06-21 | 2020-03-16
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SHREPG | Shorefront Tot Playground and Plaza Area Q163-318M | 4 | CONSTRUCTION | 2020-03-17 | 2021-09-07 | 2020-03-17 | 2021-09-07
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SHREPG | Shorefront Tot Playground and Plaza Area Q163-318M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-08 | 2022-09-07 | 2021-09-08 | 2022-09-07
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SHRESA | Shorefront Parkway Park Amenities | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SHRESA | Shorefront Parkway Park Amenities | 2 | DESIGN | 2017-12-28 | 2019-06-20 | 2017-12-28 | 2019-06-20
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SHRESA | Shorefront Parkway Park Amenities | 3 | BID/ REGISTER CONTRACT | 2019-06-21 | 2020-03-16 | 2019-06-21 | 2020-03-16
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SHRESA | Shorefront Parkway Park Amenities | 4 | CONSTRUCTION | 2020-03-17 | 2021-09-07 | 2020-03-17 | 2021-09-07
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SHRESA | Shorefront Parkway Park Amenities | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-08 | 2022-09-07 | 2021-09-08 | 2022-09-07
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SHRESF | Shorefront Parkway Multi-Purpose Sports Field Cons Q163-618M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SHRESF | Shorefront Parkway Multi-Purpose Sports Field Cons Q163-618M | 2 | DESIGN | 2017-12-28 | 2019-06-20 | 2017-12-28 | 2019-06-20
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SHRESF | Shorefront Parkway Multi-Purpose Sports Field Cons Q163-618M | 3 | BID/ REGISTER CONTRACT | 2019-06-21 | 2020-03-16 | 2019-06-21 | 2020-03-16
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SHRESF | Shorefront Parkway Multi-Purpose Sports Field Cons Q163-618M | 4 | CONSTRUCTION | 2020-03-17 | 2021-09-07 | 2020-03-17 | 2021-09-07
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SHRESF | Shorefront Parkway Multi-Purpose Sports Field Cons Q163-618M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-08 | 2022-09-07 | 2021-09-08 | 2022-09-07
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SKATE | SKATE BOARD PARK AT ROCKAWAY BEACH Q163-103M | 2 | DESIGN | 2006-09-29 | 2006-12-27 | 2006-09-29 | 2006-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SKATE | SKATE BOARD PARK AT ROCKAWAY BEACH Q163-103M | 3 | BID/ REGISTER CONTRACT | 2006-12-28 | 2007-03-27 | 2006-12-28 | 2007-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SKATE | SKATE BOARD PARK AT ROCKAWAY BEACH Q163-103M | 4 | CONSTRUCTION | 2007-03-28 | 2008-03-26 | 2007-03-28 | 2008-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SKATE | SKATE BOARD PARK AT ROCKAWAY BEACH Q163-103M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-27 | 2009-03-26 | 2008-03-27 | 2009-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SNDPIP | Sandpiper Plgd RC (Q163-215M) | 1 | DEVELOP SCOPE | 2014-07-01 | 2014-09-28 | 2014-07-01 | 2014-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SNDPIP | Sandpiper Plgd RC (Q163-215M) | 2 | DESIGN | 2014-09-29 | 2014-12-27 | 2014-09-29 | 2014-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SNDPIP | Sandpiper Plgd RC (Q163-215M) | 3 | BID/ REGISTER CONTRACT | 2014-12-28 | 2015-03-27 | 2014-12-28 | 2015-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SNDPIP | Sandpiper Plgd RC (Q163-215M) | 4 | CONSTRUCTION | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2016-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SNDPIP | Sandpiper Plgd RC (Q163-215M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2023-05-07
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4STFCAR | Syn Turf Field Recon at Rachel Carson at Kessina, QN | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4STFCAR | Syn Turf Field Recon at Rachel Carson at Kessina, QN | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4STFCAR | Syn Turf Field Recon at Rachel Carson at Kessina, QN | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4STFCAR | Syn Turf Field Recon at Rachel Carson at Kessina, QN | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4STFCAR | Syn Turf Field Recon at Rachel Carson at Kessina, QN | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SUNRSE | Sunrise Stables Acquisition | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SUNRSE | Sunrise Stables Acquisition | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SUNRSE | Sunrise Stables Acquisition | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SUNRSE | Sunrise Stables Acquisition | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SUNRSE | Sunrise Stables Acquisition | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRE14A | FY14 Street Tree Planting, Queens CB's 1 - 6 (QG-1013M) | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2013-09-29 | 2013-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRE14A | FY14 Street Tree Planting, Queens CB's 1 - 6 (QG-1013M) | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2013-12-28 | 2014-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRE14A | FY14 Street Tree Planting, Queens CB's 1 - 6 (QG-1013M) | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2014-03-28 | 2015-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRE14A | FY14 Street Tree Planting, Queens CB's 1 - 6 (QG-1013M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2016-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRE18A | FY18 Street Tree Queens CBs 1-5 QG- | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRE18A | FY18 Street Tree Queens CBs 1-5 QG- | 2 | DESIGN | 2017-12-28 | 2018-06-25 | 2017-12-28 | 2018-06-25
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRE18A | FY18 Street Tree Queens CBs 1-5 QG- | 3 | BID/ REGISTER CONTRACT | 2018-06-26 | 2019-03-22 | 2018-06-26 | 2019-03-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRE18A | FY18 Street Tree Queens CBs 1-5 QG- | 4 | CONSTRUCTION | 2019-03-23 | 2020-09-12 | 2019-03-23 | 2020-09-12
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRE18A | FY18 Street Tree Queens CBs 1-5 QG- | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-13 | 2022-09-12 | 2020-09-13 | 2022-09-12
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRE20A | FY20 Street Tree Queens CBs 1-6 QG-419M | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRE20A | FY20 Street Tree Queens CBs 1-6 QG-419M | 2 | DESIGN | 2018-12-28 | 2019-06-25 | 2018-12-28 | 2019-06-25
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRE20A | FY20 Street Tree Queens CBs 1-6 QG-419M | 3 | BID/ REGISTER CONTRACT | 2019-06-26 | 2020-03-21 | 2019-06-26 | 2020-03-21
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRE20A | FY20 Street Tree Queens CBs 1-6 QG-419M | 4 | CONSTRUCTION | 2020-03-22 | 2021-09-12 | 2020-03-22 | 2021-09-12
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRE20A | FY20 Street Tree Queens CBs 1-6 QG-419M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-13 | 2023-09-12 | 2021-09-13 | 2023-09-12
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRE20B | FY20 Street Tree Queens CBs 7,8,11 QG-219M | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRE20B | FY20 Street Tree Queens CBs 7,8,11 QG-219M | 2 | DESIGN | 2018-12-28 | 2019-06-25 | 2018-12-28 | 2019-06-25
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRE20B | FY20 Street Tree Queens CBs 7,8,11 QG-219M | 3 | BID/ REGISTER CONTRACT | 2019-06-26 | 2020-03-21 | 2019-06-26 | 2020-03-21
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRE20B | FY20 Street Tree Queens CBs 7,8,11 QG-219M | 4 | CONSTRUCTION | 2020-03-22 | 2021-09-12 | 2020-03-22 | 2021-09-12
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRE20B | FY20 Street Tree Queens CBs 7,8,11 QG-219M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-13 | 2023-09-12 | 2021-09-13 | 2023-09-12
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRE20C | FY20 Street Tree Queens CBs 9,10,14 QG-519M | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRE20C | FY20 Street Tree Queens CBs 9,10,14 QG-519M | 2 | DESIGN | 2018-12-28 | 2019-06-25 | 2018-12-28 | 2019-06-25
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRE20C | FY20 Street Tree Queens CBs 9,10,14 QG-519M | 3 | BID/ REGISTER CONTRACT | 2019-06-26 | 2020-03-21 | 2019-06-26 | 2020-03-21
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRE20C | FY20 Street Tree Queens CBs 9,10,14 QG-519M | 4 | CONSTRUCTION | 2020-03-22 | 2021-09-12 | 2020-03-22 | 2021-09-12
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRE20C | FY20 Street Tree Queens CBs 9,10,14 QG-519M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-13 | 2023-09-12 | 2021-09-13 | 2023-09-12
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRE21A | FY21 Street Tree Queens CBs 1-6 QG- | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRE21A | FY21 Street Tree Queens CBs 1-6 QG- | 2 | DESIGN | 2019-12-28 | 2020-06-24 | 2019-12-28 | 2020-06-24
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRE21A | FY21 Street Tree Queens CBs 1-6 QG- | 3 | BID/ REGISTER CONTRACT | 2020-06-25 | 2021-03-21 | 2020-06-25 | 2021-03-21
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRE21A | FY21 Street Tree Queens CBs 1-6 QG- | 4 | CONSTRUCTION | 2021-03-22 | 2022-09-12 | 2021-03-22 | 2022-09-12
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRE21A | FY21 Street Tree Queens CBs 1-6 QG- | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-13 | 2024-09-11 | 2022-09-13 | 2024-09-11
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRE21B | FY21 Street Tree Queens CBs 9,14 QG- | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRE21B | FY21 Street Tree Queens CBs 9,14 QG- | 2 | DESIGN | 2019-12-28 | 2020-06-24 | 2019-12-28 | 2020-06-24
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRE21B | FY21 Street Tree Queens CBs 9,14 QG- | 3 | BID/ REGISTER CONTRACT | 2020-06-25 | 2021-03-21 | 2020-06-25 | 2021-03-21
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRE21B | FY21 Street Tree Queens CBs 9,14 QG- | 4 | CONSTRUCTION | 2021-03-22 | 2022-09-12 | 2021-03-22 | 2022-09-12
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRE21B | FY21 Street Tree Queens CBs 9,14 QG- | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-13 | 2024-09-11 | 2022-09-13 | 2024-09-11
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TREE08 | FY13 Street Tree Planting Qns CB 1-8 (QG-911MR PlaNYC) | 2 | DESIGN | 2012-09-29 | 2012-12-27 | 2012-09-29 | 2012-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TREE08 | FY13 Street Tree Planting Qns CB 1-8 (QG-911MR PlaNYC) | 3 | BID/ REGISTER CONTRACT | 2012-12-28 | 2013-03-27 | 2012-12-28 | 2013-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TREE08 | FY13 Street Tree Planting Qns CB 1-8 (QG-911MR PlaNYC) | 4 | CONSTRUCTION | 2013-03-28 | 2014-03-27 | 2013-03-28 | 2014-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TREE08 | FY13 Street Tree Planting Qns CB 1-8 (QG-911MR PlaNYC) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-03-28 | 2015-03-27 | 2014-03-28 | 2015-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TREE09 | FY13 Street Tree Planting Qns CBs 7-9 & 11 (QG-113M) | 2 | DESIGN | 2012-09-29 | 2012-12-27 | 2012-09-29 | 2012-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TREE09 | FY13 Street Tree Planting Qns CBs 7-9 & 11 (QG-113M) | 3 | BID/ REGISTER CONTRACT | 2012-12-28 | 2013-03-27 | 2012-12-28 | 2013-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TREE09 | FY13 Street Tree Planting Qns CBs 7-9 & 11 (QG-113M) | 4 | CONSTRUCTION | 2013-03-28 | 2014-03-27 | 2013-03-28 | 2014-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TREE09 | FY13 Street Tree Planting Qns CBs 7-9 & 11 (QG-113M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-03-28 | 2015-03-27 | 2014-03-28 | 2015-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TREE10 | FY13 Street Tree Planting Queens CBs 7-10, 12-14(QG-213M) | 3 | BID/ REGISTER CONTRACT | 2012-12-28 | 2013-03-27 | 2012-12-28 | 2013-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TREE10 | FY13 Street Tree Planting Queens CBs 7-10, 12-14(QG-213M) | 4 | CONSTRUCTION | 2013-03-28 | 2014-03-27 | 2013-03-28 | 2014-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TREE10 | FY13 Street Tree Planting Queens CBs 7-10, 12-14(QG-213M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-03-28 | 2015-03-27 | 2014-03-28 | 2015-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TREL21 | FY21 Street Trees QN CB's 8,11-13(3Y) | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TREL21 | FY21 Street Trees QN CB's 8,11-13(3Y) | 2 | DESIGN | 2019-12-28 | 2021-06-19 | 2019-12-28 | 2021-06-19
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TREL21 | FY21 Street Trees QN CB's 8,11-13(3Y) | 3 | BID/ REGISTER CONTRACT | 2021-06-20 | 2022-03-16 | 2021-06-20 | 2022-03-16
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TREL21 | FY21 Street Trees QN CB's 8,11-13(3Y) | 4 | CONSTRUCTION | 2022-03-17 | 2025-03-15 | 2022-03-17 | 2025-03-15
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TREL21 | FY21 Street Trees QN CB's 8,11-13(3Y) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-03-16 | 2027-03-15 | 2025-03-16 | 2027-03-15
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRS19A | QueensTree-Damaged Sidewalk R/C CB 8,11-14 | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRS19A | QueensTree-Damaged Sidewalk R/C CB 8,11-14 | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRS19A | QueensTree-Damaged Sidewalk R/C CB 8,11-14 | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRS19A | QueensTree-Damaged Sidewalk R/C CB 8,11-14 | 4 | CONSTRUCTION | 2020-09-23 | 2022-09-22 | 2020-09-23 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRS19A | QueensTree-Damaged Sidewalk R/C CB 8,11-14 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRS21A | FY21 Street Tree 7mo Queens CBs7 QG- | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRS21A | FY21 Street Tree 7mo Queens CBs7 QG- | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRS21A | FY21 Street Tree 7mo Queens CBs7 QG- | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRS21A | FY21 Street Tree 7mo Queens CBs7 QG- | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRS21A | FY21 Street Tree 7mo Queens CBs7 QG- | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRS21B | FY21 Street Tree 7mo Queens CBs 10 QG- | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRS21B | FY21 Street Tree 7mo Queens CBs 10 QG- | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRS21B | FY21 Street Tree 7mo Queens CBs 10 QG- | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRS21B | FY21 Street Tree 7mo Queens CBs 10 QG- | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRS21B | FY21 Street Tree 7mo Queens CBs 10 QG- | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRSD19 | QueensTree-Damaged Sidewalk R/C CB 1-7,9,10 | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRSD19 | QueensTree-Damaged Sidewalk R/C CB 1-7,9,10 | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRSD19 | QueensTree-Damaged Sidewalk R/C CB 1-7,9,10 | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRSD19 | QueensTree-Damaged Sidewalk R/C CB 1-7,9,10 | 4 | CONSTRUCTION | 2020-09-23 | 2022-09-22 | 2020-09-23 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRSD19 | QueensTree-Damaged Sidewalk R/C CB 1-7,9,10 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4UDALNP | Udalls Cove Park & Nature Preserve | 1 | DEVELOP SCOPE | 2020-07-01 | 2020-12-27 | 2020-07-01 | 2020-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4UDALNP | Udalls Cove Park & Nature Preserve | 2 | DESIGN | 2020-12-28 | 2021-09-23 | 2020-12-28 | 2021-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4UDALNP | Udalls Cove Park & Nature Preserve | 3 | BID/ REGISTER CONTRACT | 2021-09-24 | 2022-06-20 | 2021-09-24 | 2022-06-20
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4UDALNP | Udalls Cove Park & Nature Preserve | 4 | CONSTRUCTION | 2022-06-21 | 2024-12-16 | 2022-06-21 | 2024-12-16
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4UDALNP | Udalls Cove Park & Nature Preserve | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-12-17 | 2026-12-16 | 2024-12-17 | 2026-12-16
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4VANDOH | VON DOHLEN PK C/S & PLAYGROUND Q105-108MA | 2 | DESIGN | 2006-09-29 | 2006-12-27 | 2006-09-29 | 2006-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4VANDOH | VON DOHLEN PK C/S & PLAYGROUND Q105-108MA | 3 | BID/ REGISTER CONTRACT | 2006-12-28 | 2007-03-27 | 2006-12-28 | 2007-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4VANDOH | VON DOHLEN PK C/S & PLAYGROUND Q105-108MA | 4 | CONSTRUCTION | 2007-03-28 | 2008-03-26 | 2007-03-28 | 2008-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4VANDOH | VON DOHLEN PK C/S & PLAYGROUND Q105-108MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-27 | 2009-03-26 | 2008-03-27 | 2015-12-31
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4VIETNA | VIETNAM VETERAN MEMORIAL - ELMHURST PARK Q492-117M | 1 | DEVELOP SCOPE | 2006-07-01 | 2006-09-28 | 2006-07-01 | 2006-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4VIETNA | VIETNAM VETERAN MEMORIAL - ELMHURST PARK Q492-117M | 2 | DESIGN | 2006-09-29 | 2006-12-27 | 2006-09-29 | 2006-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4VIETNA | VIETNAM VETERAN MEMORIAL - ELMHURST PARK Q492-117M | 3 | BID/ REGISTER CONTRACT | 2006-12-28 | 2007-03-27 | 2006-12-28 | 2007-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4VIETNA | VIETNAM VETERAN MEMORIAL - ELMHURST PARK Q492-117M | 4 | CONSTRUCTION | 2007-03-28 | 2008-03-26 | 2007-03-28 | 2008-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4VIETNA | VIETNAM VETERAN MEMORIAL - ELMHURST PARK Q492-117M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-27 | 2009-03-26 | 2008-03-27 | 2022-04-30
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4WOODPZ | WOODSIDE PLAZA | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4WOODPZ | WOODSIDE PLAZA | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4WOODPZ | WOODSIDE PLAZA | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4WOODPZ | WOODSIDE PLAZA | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4WOODPZ | WOODSIDE PLAZA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4WPJAMC | Walk to Park NYCHA Pomonok Houses Construction | 1 | DEVELOP SCOPE | 2018-03-07 | 2018-09-02 | 2018-03-07 | 2018-09-02
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4WPJAMC | Walk to Park NYCHA Pomonok Houses Construction | 2 | DESIGN | 2018-09-03 | 2019-09-02 | 2018-09-03 | 2019-09-02
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4WPJAMC | Walk to Park NYCHA Pomonok Houses Construction | 3 | BID/ REGISTER CONTRACT | 2019-09-03 | 2020-05-29 | 2019-09-03 | 2020-05-29
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4WPJAMC | Walk to Park NYCHA Pomonok Houses Construction | 4 | CONSTRUCTION | 2020-05-30 | 2021-05-29 | 2020-05-30 | 2021-05-29
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4WPJAMC | Walk to Park NYCHA Pomonok Houses Construction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-05-30 | 2022-05-29 | 2021-05-30 | 2022-05-29
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4WPWSDE | Walk to Park NYCHA Woodside Playground Construction | 1 | DEVELOP SCOPE | 2018-03-07 | 2018-09-02 | 2018-03-07 | 2018-09-02
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4WPWSDE | Walk to Park NYCHA Woodside Playground Construction | 2 | DESIGN | 2018-09-03 | 2019-09-02 | 2018-09-03 | 2019-09-02
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4WPWSDE | Walk to Park NYCHA Woodside Playground Construction | 3 | BID/ REGISTER CONTRACT | 2019-09-03 | 2020-05-29 | 2019-09-03 | 2020-05-29
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4WPWSDE | Walk to Park NYCHA Woodside Playground Construction | 4 | CONSTRUCTION | 2020-05-30 | 2021-05-29 | 2020-05-30 | 2021-05-29
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4WPWSDE | Walk to Park NYCHA Woodside Playground Construction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-05-30 | 2022-05-29 | 2021-05-30 | 2022-05-29
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-6BLD14A | FY14 BUILDINGS-RC OF C/S & FACILTIES VAR PKS LOC QG-1613MA | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2013-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-6BLD14A | FY14 BUILDINGS-RC OF C/S & FACILTIES VAR PKS LOC QG-1613MA | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2013-09-29 | 2013-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-6BLD14A | FY14 BUILDINGS-RC OF C/S & FACILTIES VAR PKS LOC QG-1613MA | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2013-12-28 | 2014-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-6BLD14A | FY14 BUILDINGS-RC OF C/S & FACILTIES VAR PKS LOC QG-1613MA | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2014-03-28 | 2015-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-6BLD14A | FY14 BUILDINGS-RC OF C/S & FACILTIES VAR PKS LOC QG-1613MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2016-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-6BLD14B | FY14 BUILDINGS-RC OF C/S & FACILTIES AT VAR PKS & RECR LOC | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2013-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-6BLD14B | FY14 BUILDINGS-RC OF C/S & FACILTIES AT VAR PKS & RECR LOC | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2013-09-29 | 2013-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-6BLD14B | FY14 BUILDINGS-RC OF C/S & FACILTIES AT VAR PKS & RECR LOC | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2013-12-28 | 2014-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-6BLD14B | FY14 BUILDINGS-RC OF C/S & FACILTIES AT VAR PKS & RECR LOC | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2014-03-28 | 2015-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-6BLD14B | FY14 BUILDINGS-RC OF C/S & FACILTIES AT VAR PKS & RECR LOC | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2016-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-6BLDG13 | RC OF C/S & FACILITIES AT VARIOUS PKS QG-1413M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2016-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-6ROOFQN | Recon roofs at Forest Pk garage & Oak Ridge QG-918M | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-6ROOFQN | Recon roofs at Forest Pk garage & Oak Ridge QG-918M | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-6ROOFQN | Recon roofs at Forest Pk garage & Oak Ridge QG-918M | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-6ROOFQN | Recon roofs at Forest Pk garage & Oak Ridge QG-918M | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-6ROOFQN | Recon roofs at Forest Pk garage & Oak Ridge QG-918M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-02 | SANDY- Emergency Storm Make Safe - Rockaway Beach Q162-213M | 1 | DEVELOP SCOPE | 2012-12-01 | 2013-02-28 | 2012-12-01 | 2013-02-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-02 | SANDY- Emergency Storm Make Safe - Rockaway Beach Q162-213M | 2 | DESIGN | 2013-03-01 | 2013-05-29 | 2013-03-01 | 2013-05-29
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-02 | SANDY- Emergency Storm Make Safe - Rockaway Beach Q162-213M | 3 | BID/ REGISTER CONTRACT | 2013-05-30 | 2013-08-27 | 2013-05-30 | 2013-08-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-02 | SANDY- Emergency Storm Make Safe - Rockaway Beach Q162-213M | 4 | CONSTRUCTION | 2013-08-28 | 2014-08-27 | 2013-08-28 | 2014-08-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-02 | SANDY- Emergency Storm Make Safe - Rockaway Beach Q162-213M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-08-28 | 2015-08-27 | 2014-08-28 | 2023-02-13
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-08 | PNP Socrates Sculpture Park | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2013-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-08 | PNP Socrates Sculpture Park | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2013-09-29 | 2013-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-08 | PNP Socrates Sculpture Park | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2013-12-28 | 2014-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-08 | PNP Socrates Sculpture Park | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2014-03-28 | 2015-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-08 | PNP Socrates Sculpture Park | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2022-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-10 | Ralph DeMarco Pk, Shoreline R/C Q004-213M | 1 | DEVELOP SCOPE | 2013-06-01 | 2013-08-29 | 2013-06-01 | 2013-08-29
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-10 | Ralph DeMarco Pk, Shoreline R/C Q004-213M | 2 | DESIGN | 2013-08-30 | 2013-11-27 | 2016-08-16 | 2017-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-10 | Ralph DeMarco Pk, Shoreline R/C Q004-213M | 3 | BID/ REGISTER CONTRACT | 2013-11-28 | 2014-02-25 | 2017-09-23 | 2017-12-21
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-10 | Ralph DeMarco Pk, Shoreline R/C Q004-213M | 4 | CONSTRUCTION | 2014-02-26 | 2015-02-25 | 2017-12-22 | 2018-12-21
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-10 | Ralph DeMarco Pk, Shoreline R/C Q004-213M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-02-26 | 2016-02-25 | 2018-12-22 | 2019-12-21
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-11 | SANDY- R/C of Rockaway Garage | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-11 | SANDY- R/C of Rockaway Garage | 2 | DESIGN | 2017-12-28 | 2019-12-27 | 2017-12-28 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-11 | SANDY- R/C of Rockaway Garage | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-11 | SANDY- R/C of Rockaway Garage | 4 | CONSTRUCTION | 2020-09-23 | 2022-09-22 | 2020-09-23 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-11 | SANDY- R/C of Rockaway Garage | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-12 | SANDY- Joe Michael's Mile Promenade Q135-214M | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2013-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-12 | SANDY- Joe Michael's Mile Promenade Q135-214M | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2013-09-29 | 2013-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-12 | SANDY- Joe Michael's Mile Promenade Q135-214M | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2013-12-28 | 2014-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-12 | SANDY- Joe Michael's Mile Promenade Q135-214M | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2014-03-28 | 2015-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-12 | SANDY- Joe Michael's Mile Promenade Q135-214M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2022-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-13 | SANDY-Rockaway Beach roller hockey rink - Type 3 Q163-114M | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2013-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-13 | SANDY-Rockaway Beach roller hockey rink - Type 3 Q163-114M | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2013-09-29 | 2013-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-13 | SANDY-Rockaway Beach roller hockey rink - Type 3 Q163-114M | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2013-12-28 | 2014-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-13 | SANDY-Rockaway Beach roller hockey rink - Type 3 Q163-114M | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2014-03-28 | 2015-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-13 | SANDY-Rockaway Beach roller hockey rink - Type 3 Q163-114M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2016-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-14 | SANDY - Tree removals - Queens CB 1-5 QG-314M | 3 | BID/ REGISTER CONTRACT | 2014-06-30 | 2014-09-27 | 2014-06-30 | 2014-09-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-14 | SANDY - Tree removals - Queens CB 1-5 QG-314M | 4 | CONSTRUCTION | 2014-09-28 | 2015-09-27 | 2014-09-28 | 2015-09-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-14 | SANDY - Tree removals - Queens CB 1-5 QG-314M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-09-28 | 2016-09-26 | 2015-09-28 | 2016-09-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-15 | SANDY - Tree removals - Queens CB 6-15 QG-414M | 1 | DEVELOP SCOPE | 2014-01-01 | 2014-03-31 | 2014-01-01 | 2014-03-31
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-15 | SANDY - Tree removals - Queens CB 6-15 QG-414M | 2 | DESIGN | 2014-04-01 | 2014-06-29 | 2014-04-01 | 2014-06-29
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-15 | SANDY - Tree removals - Queens CB 6-15 QG-414M | 3 | BID/ REGISTER CONTRACT | 2014-06-30 | 2014-09-27 | 2014-06-30 | 2014-09-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-15 | SANDY - Tree removals - Queens CB 6-15 QG-414M | 4 | CONSTRUCTION | 2014-09-28 | 2015-09-27 | 2014-09-28 | 2015-09-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-15 | SANDY - Tree removals - Queens CB 6-15 QG-414M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-09-28 | 2016-09-26 | 2015-09-28 | 2016-09-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-17 | SANDY - Rockaway Beach Skate Park Q163-111MA | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-09-28 | 2016-07-01 | 2016-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-17 | SANDY - Rockaway Beach Skate Park Q163-111MA | 2 | DESIGN | 2016-09-29 | 2016-12-27 | 2016-09-29 | 2016-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-17 | SANDY - Rockaway Beach Skate Park Q163-111MA | 3 | BID/ REGISTER CONTRACT | 2016-12-28 | 2017-03-27 | 2016-12-28 | 2017-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-17 | SANDY - Rockaway Beach Skate Park Q163-111MA | 4 | CONSTRUCTION | 2017-03-28 | 2018-03-27 | 2017-03-28 | 2018-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-17 | SANDY - Rockaway Beach Skate Park Q163-111MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-03-28 | 2019-03-27 | 2018-03-28 | 2019-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-18 | SANDY - Tribute Park Reconstruction Q028-116M | 1 | DEVELOP SCOPE | 2014-07-01 | 2014-09-28 | 2014-07-01 | 2014-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-18 | SANDY - Tribute Park Reconstruction Q028-116M | 2 | DESIGN | 2014-09-29 | 2014-12-27 | 2014-09-29 | 2014-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-18 | SANDY - Tribute Park Reconstruction Q028-116M | 3 | BID/ REGISTER CONTRACT | 2014-12-28 | 2015-03-27 | 2014-12-28 | 2015-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-18 | SANDY - Tribute Park Reconstruction Q028-116M | 4 | CONSTRUCTION | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2016-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-18 | SANDY - Tribute Park Reconstruction Q028-116M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-19 | SANDY - BAYSIDE MARINA ELECTRICAL UPGRADE Q135-115M | 3 | BID/ REGISTER CONTRACT | 2014-12-28 | 2015-03-27 | 2014-12-28 | 2015-03-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-19 | SANDY - BAYSIDE MARINA ELECTRICAL UPGRADE Q135-115M | 4 | CONSTRUCTION | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2016-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-19 | SANDY - BAYSIDE MARINA ELECTRICAL UPGRADE Q135-115M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-21 | SANDY-FOREST PARK GREENHOUSE BROKEN GLASS REPLACEMENT | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-21 | SANDY-FOREST PARK GREENHOUSE BROKEN GLASS REPLACEMENT | 2 | DESIGN | 2016-12-28 | 2018-12-27 | 2016-12-28 | 2018-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-21 | SANDY-FOREST PARK GREENHOUSE BROKEN GLASS REPLACEMENT | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-21 | SANDY-FOREST PARK GREENHOUSE BROKEN GLASS REPLACEMENT | 4 | CONSTRUCTION | 2019-09-24 | 2021-09-22 | 2019-09-24 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-21 | SANDY-FOREST PARK GREENHOUSE BROKEN GLASS REPLACEMENT | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-22 | SANDY - Rockaway Beach Shorefront Pkwy Handball Ct Q163-315M | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2015-09-28
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-22 | SANDY - Rockaway Beach Shorefront Pkwy Handball Ct Q163-315M | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2015-09-29 | 2015-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-22 | SANDY - Rockaway Beach Shorefront Pkwy Handball Ct Q163-315M | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2015-12-28 | 2016-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-22 | SANDY - Rockaway Beach Shorefront Pkwy Handball Ct Q163-315M | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-22 | SANDY - Rockaway Beach Shorefront Pkwy Handball Ct Q163-315M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2017-03-27 | 2023-03-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-23 | Rockaway Beach Sports Areas | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-23 | Rockaway Beach Sports Areas | 2 | DESIGN | 2016-12-28 | 2018-12-27 | 2016-12-28 | 2018-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-23 | Rockaway Beach Sports Areas | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-23 | Rockaway Beach Sports Areas | 4 | CONSTRUCTION | 2019-09-24 | 2021-09-22 | 2019-09-24 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-23 | Rockaway Beach Sports Areas | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2024-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-25 | Bayside Marina Reconstruction (Q135-117M) | 1 | DEVELOP SCOPE | 2016-08-01 | 2017-01-27 | 2016-08-01 | 2017-01-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-25 | Bayside Marina Reconstruction (Q135-117M) | 2 | DESIGN | 2017-01-28 | 2019-01-27 | 2017-01-28 | 2019-01-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-25 | Bayside Marina Reconstruction (Q135-117M) | 3 | BID/ REGISTER CONTRACT | 2019-01-28 | 2019-10-24 | 2019-01-28 | 2019-10-24
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-25 | Bayside Marina Reconstruction (Q135-117M) | 4 | CONSTRUCTION | 2019-10-25 | 2021-10-23 | 2019-10-25 | 2021-10-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-25 | Bayside Marina Reconstruction (Q135-117M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-10-24 | 2022-10-23 | 2021-10-24 | 2022-10-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-26 | World's Fair Marina Q099-218M | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-26 | World's Fair Marina Q099-218M | 2 | DESIGN | 2016-12-28 | 2018-12-27 | 2016-12-28 | 2018-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-26 | World's Fair Marina Q099-218M | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-26 | World's Fair Marina Q099-218M | 4 | CONSTRUCTION | 2019-09-24 | 2021-09-22 | 2019-09-24 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-26 | World's Fair Marina Q099-218M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-27 | Little Bay Revetment | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-27 | Little Bay Revetment | 2 | DESIGN | 2016-12-28 | 2018-12-27 | 2016-12-28 | 2018-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-27 | Little Bay Revetment | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-27 | Little Bay Revetment | 4 | CONSTRUCTION | 2019-09-24 | 2021-09-22 | 2019-09-24 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-27 | Little Bay Revetment | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-29 | FMCP Electrical Repairs | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-29 | FMCP Electrical Repairs | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2016-12-28 | 2017-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-29 | FMCP Electrical Repairs | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2017-12-28 | 2018-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-29 | FMCP Electrical Repairs | 4 | CONSTRUCTION | 2018-09-24 | 2019-09-23 | 2018-09-24 | 2019-09-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-29 | FMCP Electrical Repairs | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-32 | SANDY - Beach 94th Street Performance Space Cons. Q163-418M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-32 | SANDY - Beach 94th Street Performance Space Cons. Q163-418M | 2 | DESIGN | 2017-12-28 | 2019-06-20 | 2017-12-28 | 2019-06-20
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-32 | SANDY - Beach 94th Street Performance Space Cons. Q163-418M | 3 | BID/ REGISTER CONTRACT | 2019-06-21 | 2020-03-16 | 2019-06-21 | 2020-03-16
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-32 | SANDY - Beach 94th Street Performance Space Cons. Q163-418M | 4 | CONSTRUCTION | 2020-03-17 | 2021-09-07 | 2020-03-17 | 2021-09-07
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-32 | SANDY - Beach 94th Street Performance Space Cons. Q163-418M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-08 | 2022-09-07 | 2021-09-08 | 2022-09-07
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-33 | SANDY - Shorefront Park MPPA Sports Field Cons. Q163-618M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-33 | SANDY - Shorefront Park MPPA Sports Field Cons. Q163-618M | 2 | DESIGN | 2017-12-28 | 2019-06-20 | 2017-12-28 | 2019-06-20
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-33 | SANDY - Shorefront Park MPPA Sports Field Cons. Q163-618M | 3 | BID/ REGISTER CONTRACT | 2019-06-21 | 2020-03-16 | 2019-06-21 | 2020-03-16
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-33 | SANDY - Shorefront Park MPPA Sports Field Cons. Q163-618M | 4 | CONSTRUCTION | 2020-03-17 | 2021-09-07 | 2020-03-17 | 2021-09-07
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-33 | SANDY - Shorefront Park MPPA Sports Field Cons. Q163-618M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-08 | 2022-09-07 | 2021-09-08 | 2022-09-07
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-34 | SANDY - Shorefront Labyrinth and Seating Area Q163-518M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-34 | SANDY - Shorefront Labyrinth and Seating Area Q163-518M | 2 | DESIGN | 2017-12-28 | 2019-06-20 | 2017-12-28 | 2019-06-20
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-34 | SANDY - Shorefront Labyrinth and Seating Area Q163-518M | 3 | BID/ REGISTER CONTRACT | 2019-06-21 | 2020-03-16 | 2019-06-21 | 2020-03-16
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-34 | SANDY - Shorefront Labyrinth and Seating Area Q163-518M | 4 | CONSTRUCTION | 2020-03-17 | 2021-09-07 | 2020-03-17 | 2021-09-07
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-34 | SANDY - Shorefront Labyrinth and Seating Area Q163-518M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-08 | 2022-09-07 | 2021-09-08 | 2022-09-07
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-35 | SANDY - Shorefront Tot Playground and Plaza Area Q163-318M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-35 | SANDY - Shorefront Tot Playground and Plaza Area Q163-318M | 2 | DESIGN | 2017-12-28 | 2019-06-20 | 2017-12-28 | 2019-06-20
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-35 | SANDY - Shorefront Tot Playground and Plaza Area Q163-318M | 3 | BID/ REGISTER CONTRACT | 2019-06-21 | 2020-03-16 | 2019-06-21 | 2020-03-16
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-35 | SANDY - Shorefront Tot Playground and Plaza Area Q163-318M | 4 | CONSTRUCTION | 2020-03-17 | 2021-09-07 | 2020-03-17 | 2021-09-07
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-35 | SANDY - Shorefront Tot Playground and Plaza Area Q163-318M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-08 | 2022-09-07 | 2021-09-08 | 2022-09-07
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-36 | SANDY - Shorefront Parkway Adventure Course Q163-218M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-36 | SANDY - Shorefront Parkway Adventure Course Q163-218M | 2 | DESIGN | 2017-12-28 | 2019-06-20 | 2017-12-28 | 2019-06-20
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-36 | SANDY - Shorefront Parkway Adventure Course Q163-218M | 3 | BID/ REGISTER CONTRACT | 2019-06-21 | 2020-03-16 | 2019-06-21 | 2020-03-16
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-36 | SANDY - Shorefront Parkway Adventure Course Q163-218M | 4 | CONSTRUCTION | 2020-03-17 | 2021-09-07 | 2020-03-17 | 2021-09-07
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-36 | SANDY - Shorefront Parkway Adventure Course Q163-218M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-08 | 2022-09-07 | 2021-09-08 | 2022-09-07
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-37 | SANDY - Beach 88th Street Park Construction Q499-118M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-37 | SANDY - Beach 88th Street Park Construction Q499-118M | 2 | DESIGN | 2017-12-28 | 2019-06-20 | 2017-12-28 | 2019-06-20
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-37 | SANDY - Beach 88th Street Park Construction Q499-118M | 3 | BID/ REGISTER CONTRACT | 2019-06-21 | 2020-03-16 | 2019-06-21 | 2020-03-16
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-37 | SANDY - Beach 88th Street Park Construction Q499-118M | 4 | CONSTRUCTION | 2020-03-17 | 2021-09-07 | 2020-03-17 | 2021-09-07
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-37 | SANDY - Beach 88th Street Park Construction Q499-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-08 | 2022-09-07 | 2021-09-08 | 2022-09-07
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-38 | SANDY - Beach 24th to Beach 25th Street Ramp Q162-218M | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-38 | SANDY - Beach 24th to Beach 25th Street Ramp Q162-218M | 2 | DESIGN | 2018-12-28 | 2020-12-26 | 2018-12-28 | 2020-12-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-38 | SANDY - Beach 24th to Beach 25th Street Ramp Q162-218M | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-38 | SANDY - Beach 24th to Beach 25th Street Ramp Q162-218M | 4 | CONSTRUCTION | 2021-09-23 | 2023-09-22 | 2021-09-23 | 2023-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-38 | SANDY - Beach 24th to Beach 25th Street Ramp Q162-218M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-23 | 2024-09-21 | 2023-09-23 | 2024-09-21
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-39 | SANDY - Rockaway Community Park Shoreline R/C Q371-119M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-39 | SANDY - Rockaway Community Park Shoreline R/C Q371-119M | 2 | DESIGN | 2017-12-28 | 2019-06-20 | 2017-12-28 | 2019-06-20
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-39 | SANDY - Rockaway Community Park Shoreline R/C Q371-119M | 3 | BID/ REGISTER CONTRACT | 2019-06-21 | 2020-03-16 | 2019-06-21 | 2020-03-16
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-39 | SANDY - Rockaway Community Park Shoreline R/C Q371-119M | 4 | CONSTRUCTION | 2020-03-17 | 2021-09-07 | 2020-03-17 | 2021-09-07
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-39 | SANDY - Rockaway Community Park Shoreline R/C Q371-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-08 | 2022-09-07 | 2021-09-08 | 2022-09-07
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-41 | SANDY - Michaelis-Bayswater Park R/C Q007-119M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-41 | SANDY - Michaelis-Bayswater Park R/C Q007-119M | 2 | DESIGN | 2017-12-28 | 2019-06-20 | 2017-12-28 | 2019-06-20
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-41 | SANDY - Michaelis-Bayswater Park R/C Q007-119M | 3 | BID/ REGISTER CONTRACT | 2019-06-21 | 2020-03-16 | 2019-06-21 | 2020-03-16
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-41 | SANDY - Michaelis-Bayswater Park R/C Q007-119M | 4 | CONSTRUCTION | 2020-03-17 | 2021-09-07 | 2020-03-17 | 2021-09-07
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-41 | SANDY - Michaelis-Bayswater Park R/C Q007-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-08 | 2022-09-07 | 2021-09-08 | 2025-09-07
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-42 | SANDY - Shorefront Parkway Dog Run Cons. Q163-118M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-42 | SANDY - Shorefront Parkway Dog Run Cons. Q163-118M | 2 | DESIGN | 2017-12-28 | 2019-06-20 | 2017-12-28 | 2019-06-20
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-42 | SANDY - Shorefront Parkway Dog Run Cons. Q163-118M | 3 | BID/ REGISTER CONTRACT | 2019-06-21 | 2020-03-16 | 2019-06-21 | 2020-03-16
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-42 | SANDY - Shorefront Parkway Dog Run Cons. Q163-118M | 4 | CONSTRUCTION | 2020-03-17 | 2021-09-07 | 2020-03-17 | 2021-09-07
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-42 | SANDY - Shorefront Parkway Dog Run Cons. Q163-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-08 | 2022-09-07 | 2021-09-08 | 2022-09-07
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-43 | SANDY - Queens B | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-43 | SANDY - Queens B | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-43 | SANDY - Queens B | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-43 | SANDY - Queens B | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-43 | SANDY - Queens B | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2024-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-44 | SANDY - Shorefront Parkway Park Amenities | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-44 | SANDY - Shorefront Parkway Park Amenities | 2 | DESIGN | 2017-12-28 | 2019-06-20 | 2017-12-28 | 2019-06-20
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-44 | SANDY - Shorefront Parkway Park Amenities | 3 | BID/ REGISTER CONTRACT | 2019-06-21 | 2020-03-16 | 2019-06-21 | 2020-03-16
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-44 | SANDY - Shorefront Parkway Park Amenities | 4 | CONSTRUCTION | 2020-03-17 | 2021-09-07 | 2020-03-17 | 2021-09-07
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-44 | SANDY - Shorefront Parkway Park Amenities | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-08 | 2022-09-07 | 2021-09-08 | 2022-09-07
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-45 | SANDY - Thursby Basin Park Construction Q479-120M | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-45 | SANDY - Thursby Basin Park Construction Q479-120M | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-45 | SANDY - Thursby Basin Park Construction Q479-120M | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-45 | SANDY - Thursby Basin Park Construction Q479-120M | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-45 | SANDY - Thursby Basin Park Construction Q479-120M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-46 | Joe Michael's Mile (Q012-120M) | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-46 | Joe Michael's Mile (Q012-120M) | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-46 | Joe Michael's Mile (Q012-120M) | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-46 | Joe Michael's Mile (Q012-120M) | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-46 | Joe Michael's Mile (Q012-120M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-48 | Bayswater Park Reconstruction-FEMA | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-48 | Bayswater Park Reconstruction-FEMA | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-48 | Bayswater Park Reconstruction-FEMA | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-48 | Bayswater Park Reconstruction-FEMA | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-48 | Bayswater Park Reconstruction-FEMA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-49 | Bayswater Park Recons of Maint. & Operations-FEMA | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-49 | Bayswater Park Recons of Maint. & Operations-FEMA | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-49 | Bayswater Park Recons of Maint. & Operations-FEMA | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-49 | Bayswater Park Recons of Maint. & Operations-FEMA | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-49 | Bayswater Park Recons of Maint. & Operations-FEMA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-51 | Bayswater Park Comfort Station Construction-FEMA | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-51 | Bayswater Park Comfort Station Construction-FEMA | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-51 | Bayswater Park Comfort Station Construction-FEMA | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-51 | Bayswater Park Comfort Station Construction-FEMA | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-51 | Bayswater Park Comfort Station Construction-FEMA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY6-08 | Asser Levy HMP (Hazard Mitigation Plan ) Funding | 1 | DEVELOP SCOPE | 2012-12-01 | 2013-02-28 | 2012-12-01 | 2013-05-29
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY6-08 | Asser Levy HMP (Hazard Mitigation Plan ) Funding | 2 | DESIGN | 2013-03-01 | 2013-05-29 | 2013-05-30 | 2015-05-29
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY6-08 | Asser Levy HMP (Hazard Mitigation Plan ) Funding | 3 | BID/ REGISTER CONTRACT | 2013-05-30 | 2013-08-27 | 2015-05-30 | 2016-02-23
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY6-08 | Asser Levy HMP (Hazard Mitigation Plan ) Funding | 4 | CONSTRUCTION | 2013-08-28 | 2014-08-27 | 2016-02-24 | 2018-02-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY6-08 | Asser Levy HMP (Hazard Mitigation Plan ) Funding | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-08-28 | 2015-08-27 | 2018-02-23 | 2024-02-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY6-19 | Two Park Shoreline Protection | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY6-19 | Two Park Shoreline Protection | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY6-19 | Two Park Shoreline Protection | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY6-19 | Two Park Shoreline Protection | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY6-19 | Two Park Shoreline Protection | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2024-09-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SEQ-TREES | South East Queens Sewer Build-out Trees Restitution | 1 | DESIGN | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SEQ-TREES | South East Queens Sewer Build-out Trees Restitution | 2 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-06-24 | 2019-12-28 | 2020-06-24
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SEQ-TREES | South East Queens Sewer Build-out Trees Restitution | 3 | CONSTRUCTION | 2020-06-25 | 2029-06-22 | 2020-06-25 | 2029-06-22
20201123 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SEQ-TREES | South East Queens Sewer Build-out Trees Restitution | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2029-06-23 | 2029-08-21 | 2029-06-23 | 2029-08-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | BB05-01-A | GI - Cons of ROW Bioswales & Stormwwater GS in BB-005, Ph 1 | 1 | DEVELOP SCOPE | 2018-09-01 | 2018-11-29 | 2018-09-01 | 2018-11-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | BB05-01-A | GI - Cons of ROW Bioswales & Stormwwater GS in BB-005, Ph 1 | 2 | PRELIMINARY DESIGN | 2018-11-30 | 2019-03-29 | 2018-11-30 | 2019-03-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | BB05-01-A | GI - Cons of ROW Bioswales & Stormwwater GS in BB-005, Ph 1 | 3 | FINAL DESIGN | 2019-03-30 | 2019-09-25 | 2019-03-30 | 2019-09-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | BB05-01-A | GI - Cons of ROW Bioswales & Stormwwater GS in BB-005, Ph 1 | 4 | BID AWARD AND REGISTER CONTRCT | 2019-09-26 | 2019-12-24 | 2019-09-26 | 2019-12-24
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | BB05-01-A | GI - Cons of ROW Bioswales & Stormwwater GS in BB-005, Ph 1 | 5 | CONSTRUCTION TO 25% | 2019-12-25 | 2020-04-22 | 2019-12-25 | 2020-04-22
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | BB05-01-A | GI - Cons of ROW Bioswales & Stormwwater GS in BB-005, Ph 1 | 6 | CONSTRUCTION TO 50% | 2020-04-23 | 2020-08-20 | 2020-04-23 | 2020-08-20
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | BB05-01-A | GI - Cons of ROW Bioswales & Stormwwater GS in BB-005, Ph 1 | 7 | CONSTRUCTION TO 75% | 2020-08-21 | 2020-12-18 | 2020-08-21 | 2020-12-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | BB05-01-A | GI - Cons of ROW Bioswales & Stormwwater GS in BB-005, Ph 1 | 8 | ORIGINAL EQUIP & FURNISHING | 2020-12-19 | 2021-03-18 | 2020-12-19 | 2021-03-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | BB05-01-A | GI - Cons of ROW Bioswales & Stormwwater GS in BB-005, Ph 1 | 9 | SUBSTANTIAL COMPLETION | 2021-03-19 | 2021-05-17 | 2021-03-19 | 2021-05-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | BB05-01-A | GI - Cons of ROW Bioswales & Stormwwater GS in BB-005, Ph 1 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-05-18 | 2021-06-16 | 2021-05-18 | 2022-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | BB05-02-A | GI - Cons of ROW Bioswales & Stormwwater GS in BB-005, Ph 2 | 1 | FINAL DESIGN | 2019-06-15 | 2020-12-05 | 2019-06-15 | 2020-12-05
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | BB05-02-A | GI - Cons of ROW Bioswales & Stormwwater GS in BB-005, Ph 2 | 2 | CONSTRUCTION TO 25% | 2020-12-06 | 2021-08-02 | 2020-12-06 | 2021-08-02
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | BB05-02-A | GI - Cons of ROW Bioswales & Stormwwater GS in BB-005, Ph 2 | 3 | CONSTRUCTION TO 50% | 2021-08-03 | 2022-03-30 | 2021-08-03 | 2022-03-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | BB05-02-A | GI - Cons of ROW Bioswales & Stormwwater GS in BB-005, Ph 2 | 4 | CONSTRUCTION TO 75% | 2022-03-31 | 2022-11-25 | 2022-03-31 | 2022-11-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO277ELV2 | 25-10 COURT HOUSE SQ.- ELEVATORS | 1 | PROJECT START | 2014-12-15 | 2014-12-15 | 2012-07-08 | 2012-07-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO277ELV2 | 25-10 COURT HOUSE SQ.- ELEVATORS | 2 | DESIGN START | 2014-12-16 | 2014-12-16 | 2012-07-26 | 2012-07-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO277ELV2 | 25-10 COURT HOUSE SQ.- ELEVATORS | 3 | DESIGN COMPLETION | 2014-12-17 | 2014-12-17 | 2012-07-27 | 2017-09-07
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO277ELV2 | 25-10 COURT HOUSE SQ.- ELEVATORS | 4 | CONSTRUCTION START | 2014-12-18 | 2014-12-18 | 2017-09-08 | 2020-02-22
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO277ELV2 | 25-10 COURT HOUSE SQ.- ELEVATORS | 5 | CONSTRUCTION COMPLETION | 2014-12-19 | 2014-12-19 | 2020-02-23 | 2021-10-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO277FA | 25-10 COURT HOUSE SQ.- FIRE ALARM SYSTEM | 1 | DEVELOP SCOPE | 2007-09-01 | 2007-11-29 | 2015-04-01 | 2015-06-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO277FA | 25-10 COURT HOUSE SQ.- FIRE ALARM SYSTEM | 2 | PRELIMINARY DESIGN | 2007-11-30 | 2008-03-28 | 2015-06-30 | 2015-10-27
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO277FA | 25-10 COURT HOUSE SQ.- FIRE ALARM SYSTEM | 3 | FINAL DESIGN | 2008-03-29 | 2008-09-24 | 2015-10-28 | 2016-04-24
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO277FA | 25-10 COURT HOUSE SQ.- FIRE ALARM SYSTEM | 4 | BID AWARD AND REGISTER CONTRCT | 2008-09-25 | 2008-12-23 | 2016-04-25 | 2016-07-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO277FA | 25-10 COURT HOUSE SQ.- FIRE ALARM SYSTEM | 5 | CONSTRUCTION TO 25% | 2008-12-24 | 2009-04-22 | 2016-07-24 | 2016-11-20
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO277FA | 25-10 COURT HOUSE SQ.- FIRE ALARM SYSTEM | 6 | CONSTRUCTION TO 50% | 2009-04-23 | 2009-08-20 | 2016-11-21 | 2017-03-20
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO277FA | 25-10 COURT HOUSE SQ.- FIRE ALARM SYSTEM | 7 | CONSTRUCTION TO 75% | 2009-08-21 | 2009-12-18 | 2017-03-21 | 2017-07-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO277FA | 25-10 COURT HOUSE SQ.- FIRE ALARM SYSTEM | 8 | ORIGINAL EQUIP & FURNISHING | 2009-12-19 | 2010-03-18 | 2017-07-19 | 2017-10-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO277FA | 25-10 COURT HOUSE SQ.- FIRE ALARM SYSTEM | 9 | SUBSTANTIAL COMPLETION | 2010-03-19 | 2010-05-17 | 2017-10-17 | 2017-12-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO277FA | 25-10 COURT HOUSE SQ.- FIRE ALARM SYSTEM | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2010-05-18 | 2010-06-16 | 2017-12-16 | 2022-01-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO296ELEC | 125-01 QUEENS BLVD - ELECTRICAL UPGRADES | 1 | DEVELOP SCOPE | 2018-01-01 | 2018-03-31 | 2018-01-01 | 2018-03-31
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO296ELEC | 125-01 QUEENS BLVD - ELECTRICAL UPGRADES | 2 | PRELIMINARY DESIGN | 2018-04-01 | 2018-07-29 | 2018-04-01 | 2018-07-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO296ELEC | 125-01 QUEENS BLVD - ELECTRICAL UPGRADES | 3 | FINAL DESIGN | 2018-07-30 | 2019-01-25 | 2018-07-30 | 2019-01-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO296ELEC | 125-01 QUEENS BLVD - ELECTRICAL UPGRADES | 4 | BID AWARD AND REGISTER CONTRCT | 2019-01-26 | 2019-04-25 | 2019-01-26 | 2019-04-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO296ELEC | 125-01 QUEENS BLVD - ELECTRICAL UPGRADES | 5 | CONSTRUCTION TO 25% | 2019-04-26 | 2019-08-23 | 2019-04-26 | 2022-02-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO296ELEC | 125-01 QUEENS BLVD - ELECTRICAL UPGRADES | 6 | CONSTRUCTION TO 50% | 2019-08-24 | 2019-12-21 | 2022-02-22 | 2022-06-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO296ELEC | 125-01 QUEENS BLVD - ELECTRICAL UPGRADES | 7 | CONSTRUCTION TO 75% | 2019-12-22 | 2020-04-19 | 2022-06-22 | 2022-10-19
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO296ELEC | 125-01 QUEENS BLVD - ELECTRICAL UPGRADES | 8 | ORIGINAL EQUIP & FURNISHING | 2020-04-20 | 2020-07-18 | 2022-10-20 | 2023-01-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO296ELEC | 125-01 QUEENS BLVD - ELECTRICAL UPGRADES | 9 | SUBSTANTIAL COMPLETION | 2020-07-19 | 2020-09-16 | 2026-01-18 | 2026-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO296ELEC | 125-01 QUEENS BLVD - ELECTRICAL UPGRADES | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-17 | 2020-10-16 | 2026-07-01 | 2027-03-31
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO296RF | 125-01 QUEENS BLVD.- ROOF | 1 | PROJECT START | 2018-03-01 | 2018-03-01 | 2018-03-01 | 2018-03-01
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO296RF | 125-01 QUEENS BLVD.- ROOF | 2 | DESIGN START | 2018-03-02 | 2018-03-02 | 2018-03-02 | 2019-03-01
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO296RF | 125-01 QUEENS BLVD.- ROOF | 3 | DESIGN COMPLETION | 2018-03-03 | 2018-03-03 | 2019-03-02 | 2021-04-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO296RF | 125-01 QUEENS BLVD.- ROOF | 4 | CONSTRUCTION START | 2018-03-04 | 2018-03-04 | 2021-05-01 | 2021-12-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO296RF | 125-01 QUEENS BLVD.- ROOF | 5 | CONSTRUCTION COMPLETION | 2018-03-05 | 2018-03-05 | 2021-12-31 | 2024-01-31
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO299EXT2 | 89-17 SUTPHIN BLVD.- PLAZA/SIDEWALK RECONSTRUCTION | 1 | DEVELOP SCOPE | 2019-03-01 | 2019-05-29 | 2019-03-01 | 2019-05-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO299EXT2 | 89-17 SUTPHIN BLVD.- PLAZA/SIDEWALK RECONSTRUCTION | 2 | PRELIMINARY DESIGN | 2019-05-30 | 2019-09-26 | 2019-05-30 | 2019-09-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO299EXT2 | 89-17 SUTPHIN BLVD.- PLAZA/SIDEWALK RECONSTRUCTION | 3 | FINAL DESIGN | 2019-09-27 | 2020-03-24 | 2022-06-04 | 2022-06-05
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO299EXT2 | 89-17 SUTPHIN BLVD.- PLAZA/SIDEWALK RECONSTRUCTION | 4 | BID AWARD AND REGISTER CONTRCT | 2020-03-25 | 2020-06-22 | 2022-06-06 | 2022-09-03
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO299EXT2 | 89-17 SUTPHIN BLVD.- PLAZA/SIDEWALK RECONSTRUCTION | 5 | CONSTRUCTION TO 25% | 2020-06-23 | 2020-10-20 | 2022-09-04 | 2023-01-01
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO299EXT2 | 89-17 SUTPHIN BLVD.- PLAZA/SIDEWALK RECONSTRUCTION | 6 | CONSTRUCTION TO 50% | 2020-10-21 | 2021-02-17 | 2023-03-20 | 2023-03-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO299EXT2 | 89-17 SUTPHIN BLVD.- PLAZA/SIDEWALK RECONSTRUCTION | 7 | CONSTRUCTION TO 75% | 2021-02-18 | 2021-06-17 | 2023-03-22 | 2023-03-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO299EXT2 | 89-17 SUTPHIN BLVD.- PLAZA/SIDEWALK RECONSTRUCTION | 8 | ORIGINAL EQUIP & FURNISHING | 2021-06-18 | 2021-09-15 | 2023-03-24 | 2023-03-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO299EXT2 | 89-17 SUTPHIN BLVD.- PLAZA/SIDEWALK RECONSTRUCTION | 9 | SUBSTANTIAL COMPLETION | 2021-09-16 | 2021-11-14 | 2023-03-26 | 2023-03-27
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO299EXT2 | 89-17 SUTPHIN BLVD.- PLAZA/SIDEWALK RECONSTRUCTION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-11-15 | 2021-12-14 | 2023-03-28 | 2023-03-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO299FIRE | 89-17 SUTPHIN BLVD - FIRE ALARM DESIGN & REPLACEMENT | 1 | DEVELOP SCOPE | 2019-06-01 | 2019-08-29 | 2019-06-01 | 2019-08-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO299FIRE | 89-17 SUTPHIN BLVD - FIRE ALARM DESIGN & REPLACEMENT | 2 | PRELIMINARY DESIGN | 2019-08-30 | 2019-12-27 | 2019-08-30 | 2019-12-27
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO299FIRE | 89-17 SUTPHIN BLVD - FIRE ALARM DESIGN & REPLACEMENT | 3 | FINAL DESIGN | 2019-12-28 | 2020-06-24 | 2019-12-28 | 2020-06-24
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO299FIRE | 89-17 SUTPHIN BLVD - FIRE ALARM DESIGN & REPLACEMENT | 4 | BID AWARD AND REGISTER CONTRCT | 2020-06-25 | 2020-09-22 | 2020-06-25 | 2020-09-22
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO299FIRE | 89-17 SUTPHIN BLVD - FIRE ALARM DESIGN & REPLACEMENT | 5 | CONSTRUCTION TO 25% | 2020-09-23 | 2021-01-20 | 2020-09-23 | 2021-01-20
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO299FIRE | 89-17 SUTPHIN BLVD - FIRE ALARM DESIGN & REPLACEMENT | 6 | CONSTRUCTION TO 50% | 2021-01-21 | 2021-05-20 | 2021-01-21 | 2021-05-20
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO299FIRE | 89-17 SUTPHIN BLVD - FIRE ALARM DESIGN & REPLACEMENT | 7 | CONSTRUCTION TO 75% | 2021-05-21 | 2021-09-17 | 2021-05-21 | 2024-09-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO299FIRE | 89-17 SUTPHIN BLVD - FIRE ALARM DESIGN & REPLACEMENT | 8 | ORIGINAL EQUIP & FURNISHING | 2021-09-18 | 2021-12-16 | 2024-09-18 | 2024-12-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO299FIRE | 89-17 SUTPHIN BLVD - FIRE ALARM DESIGN & REPLACEMENT | 9 | SUBSTANTIAL COMPLETION | 2021-12-17 | 2022-02-14 | 2024-12-17 | 2025-02-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO299FIRE | 89-17 SUTPHIN BLVD - FIRE ALARM DESIGN & REPLACEMENT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-02-15 | 2022-03-16 | 2025-02-15 | 2026-03-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO300ELV2 | 88-11 SUTPHIN BLVD.- ELEVATOR | 1 | PROJECT START | 2014-09-25 | 2014-09-25 | 2014-09-25 | 2014-10-24
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO300ELV2 | 88-11 SUTPHIN BLVD.- ELEVATOR | 2 | DESIGN START | 2014-09-26 | 2014-09-26 | 2014-10-25 | 2015-01-22
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO300ELV2 | 88-11 SUTPHIN BLVD.- ELEVATOR | 3 | DESIGN COMPLETION | 2014-09-27 | 2014-09-27 | 2015-01-23 | 2016-01-22
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO300ELV2 | 88-11 SUTPHIN BLVD.- ELEVATOR | 4 | CONSTRUCTION START | 2014-09-28 | 2014-09-28 | 2016-01-23 | 2018-01-11
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO300ELV2 | 88-11 SUTPHIN BLVD.- ELEVATOR | 5 | CONSTRUCTION COMPLETION | 2014-09-29 | 2014-09-29 | 2018-01-12 | 2025-01-01
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CS-FB-LLD | Flushing Bay Low Lying Sewer Diversion | 1 | PROJECT START | 2014-09-19 | 2014-09-19 | 2014-09-19 | 2014-09-19
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CS-FB-LLD | Flushing Bay Low Lying Sewer Diversion | 2 | DESIGN START | 2014-09-20 | 2014-09-20 | 2014-09-20 | 2014-09-20
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CS-FB-LLD | Flushing Bay Low Lying Sewer Diversion | 3 | DESIGN COMPLETION | 2014-09-21 | 2014-09-21 | 2014-09-21 | 2014-09-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CS-FB-LLD | Flushing Bay Low Lying Sewer Diversion | 4 | CONSTRUCTION START | 2014-09-22 | 2014-09-22 | 2014-09-22 | 2014-12-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CS-FB-LLD | Flushing Bay Low Lying Sewer Diversion | 5 | CONSTRUCTION COMPLETION | 2014-09-23 | 2014-09-23 | 2014-12-31 | 2022-09-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CV19COERO | Centers of Excellence: Roosevelt | 1 | PROJECT START | 2020-05-01 | 2020-05-01 | 2020-05-01 | 2020-05-01
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CV19COERO | Centers of Excellence: Roosevelt | 2 | DESIGN START | 2020-05-02 | 2020-05-02 | 2020-05-02 | 2020-05-02
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CV19COERO | Centers of Excellence: Roosevelt | 3 | DESIGN COMPLETION | 2020-05-03 | 2020-05-03 | 2020-05-03 | 2020-05-03
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CV19COERO | Centers of Excellence: Roosevelt | 4 | CONSTRUCTION START | 2020-05-04 | 2020-06-30 | 2020-05-04 | 2020-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CV19COERO | Centers of Excellence: Roosevelt | 5 | CONSTRUCTION COMPLETION | 2020-07-01 | 2021-07-01 | 2020-07-01 | 2021-07-01
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | DOTSEQ01 | Southeast Queens - DOT Priority Grids Group 1 (SEQPGRD1) | 1 | DEVELOP SCOPE | 2019-03-01 | 2019-05-29 | 2019-03-01 | 2019-05-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | DOTSEQ01 | Southeast Queens - DOT Priority Grids Group 1 (SEQPGRD1) | 2 | PRELIMINARY DESIGN | 2019-05-30 | 2019-09-26 | 2019-05-30 | 2019-09-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | DOTSEQ01 | Southeast Queens - DOT Priority Grids Group 1 (SEQPGRD1) | 3 | FINAL DESIGN | 2019-09-27 | 2020-03-24 | 2019-09-27 | 2020-03-24
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | DOTSEQ01 | Southeast Queens - DOT Priority Grids Group 1 (SEQPGRD1) | 4 | BID AWARD AND REGISTER CONTRCT | 2020-03-25 | 2020-06-22 | 2020-03-25 | 2020-06-22
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | DOTSEQ01 | Southeast Queens - DOT Priority Grids Group 1 (SEQPGRD1) | 5 | CONSTRUCTION TO 25% | 2020-06-23 | 2020-10-20 | 2020-06-23 | 2020-10-20
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | DOTSEQ01 | Southeast Queens - DOT Priority Grids Group 1 (SEQPGRD1) | 6 | CONSTRUCTION TO 50% | 2020-10-21 | 2021-02-17 | 2020-10-21 | 2021-02-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | DOTSEQ01 | Southeast Queens - DOT Priority Grids Group 1 (SEQPGRD1) | 7 | CONSTRUCTION TO 75% | 2021-02-18 | 2021-06-17 | 2021-02-18 | 2021-06-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | DOTSEQ01 | Southeast Queens - DOT Priority Grids Group 1 (SEQPGRD1) | 8 | ORIGINAL EQUIP & FURNISHING | 2021-06-18 | 2021-09-15 | 2021-06-18 | 2021-09-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | DOTSEQ01 | Southeast Queens - DOT Priority Grids Group 1 (SEQPGRD1) | 9 | SUBSTANTIAL COMPLETION | 2021-09-16 | 2021-11-14 | 2021-09-16 | 2021-11-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | DOTSEQ01 | Southeast Queens - DOT Priority Grids Group 1 (SEQPGRD1) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-11-15 | 2021-12-14 | 2021-11-15 | 2025-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | DOTSEQ02 | Southeast Queens - DOT Priority Grids Group 2 (SEQPGRD2) | 1 | DEVELOP SCOPE | 2020-03-01 | 2020-05-29 | 2020-03-01 | 2020-05-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | DOTSEQ02 | Southeast Queens - DOT Priority Grids Group 2 (SEQPGRD2) | 2 | PRELIMINARY DESIGN | 2020-05-30 | 2020-09-26 | 2020-05-30 | 2020-09-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | DOTSEQ02 | Southeast Queens - DOT Priority Grids Group 2 (SEQPGRD2) | 3 | FINAL DESIGN | 2020-09-27 | 2021-03-25 | 2020-09-27 | 2021-03-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | DOTSEQ02 | Southeast Queens - DOT Priority Grids Group 2 (SEQPGRD2) | 4 | BID AWARD AND REGISTER CONTRCT | 2021-03-26 | 2021-06-23 | 2021-03-26 | 2021-06-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | DOTSEQ02 | Southeast Queens - DOT Priority Grids Group 2 (SEQPGRD2) | 5 | CONSTRUCTION TO 25% | 2021-06-24 | 2021-10-21 | 2021-06-24 | 2021-10-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | DOTSEQ02 | Southeast Queens - DOT Priority Grids Group 2 (SEQPGRD2) | 6 | CONSTRUCTION TO 50% | 2021-10-22 | 2022-02-18 | 2021-10-22 | 2022-02-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | DOTSEQ02 | Southeast Queens - DOT Priority Grids Group 2 (SEQPGRD2) | 7 | CONSTRUCTION TO 75% | 2022-02-19 | 2022-06-18 | 2022-02-19 | 2022-06-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | DOTSEQ02 | Southeast Queens - DOT Priority Grids Group 2 (SEQPGRD2) | 8 | ORIGINAL EQUIP & FURNISHING | 2022-06-19 | 2022-09-16 | 2022-06-19 | 2022-09-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | DOTSEQ02 | Southeast Queens - DOT Priority Grids Group 2 (SEQPGRD2) | 9 | SUBSTANTIAL COMPLETION | 2022-09-17 | 2022-11-15 | 2022-09-17 | 2022-11-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | DOTSEQ02 | Southeast Queens - DOT Priority Grids Group 2 (SEQPGRD2) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-11-16 | 2022-12-15 | 2022-11-16 | 2025-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0002 | DCAS - Queens Civil Court | 1 | PROJECT START | 2018-03-01 | 2018-03-01 | 2018-03-01 | 2018-03-01
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0002 | DCAS - Queens Civil Court | 2 | DESIGN START | 2018-03-02 | 2018-03-02 | 2018-03-02 | 2018-03-02
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0002 | DCAS - Queens Civil Court | 3 | DESIGN COMPLETION | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0002 | DCAS - Queens Civil Court | 4 | CONSTRUCTION START | 2018-03-04 | 2018-03-04 | 2018-03-04 | 2018-03-04
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0002 | DCAS - Queens Civil Court | 5 | CONSTRUCTION COMPLETION | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0002 | DCAS - Queens Civil Court | 6 | DEVELOP SCOPE | 2018-03-05 | 2018-03-05 | 2018-03-06 | 2018-06-03
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0002 | DCAS - Queens Civil Court | 7 | PRELIMINARY DESIGN | 2018-03-05 | 2018-03-05 | 2018-06-04 | 2018-10-01
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0002 | DCAS - Queens Civil Court | 8 | FINAL DESIGN | 2018-03-05 | 2018-03-05 | 2018-10-02 | 2019-03-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0002 | DCAS - Queens Civil Court | 9 | BID AWARD AND REGISTER CONTRCT | 2018-03-05 | 2018-03-05 | 2019-03-31 | 2019-06-28
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0002 | DCAS - Queens Civil Court | 10 | CONSTRUCTION TO 25% | 2018-03-05 | 2018-03-05 | 2019-06-29 | 2019-10-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0002 | DCAS - Queens Civil Court | 11 | CONSTRUCTION TO 50% | 2018-03-05 | 2018-03-05 | 2019-10-27 | 2020-02-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0002 | DCAS - Queens Civil Court | 12 | CONSTRUCTION TO 75% | 2018-03-05 | 2018-03-05 | 2020-02-24 | 2020-06-22
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0002 | DCAS - Queens Civil Court | 13 | ORIGINAL EQUIP & FURNISHING | 2018-03-05 | 2018-03-05 | 2020-06-23 | 2020-09-20
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0002 | DCAS - Queens Civil Court | 14 | SUBSTANTIAL COMPLETION | 2018-03-05 | 2018-03-05 | 2020-09-21 | 2020-11-19
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0002 | DCAS - Queens Civil Court | 15 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-03-05 | 2018-03-05 | 2020-11-20 | 2022-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0004 | DSNY - Queens 7 District Garage Annex | 1 | PROJECT START | 2018-03-01 | 2018-03-01 | 2018-03-01 | 2018-03-01
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0004 | DSNY - Queens 7 District Garage Annex | 2 | DESIGN START | 2018-03-02 | 2018-03-02 | 2018-03-02 | 2018-03-02
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0004 | DSNY - Queens 7 District Garage Annex | 3 | DESIGN COMPLETION | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0004 | DSNY - Queens 7 District Garage Annex | 4 | CONSTRUCTION START | 2018-03-04 | 2018-03-04 | 2018-03-04 | 2018-03-04
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0004 | DSNY - Queens 7 District Garage Annex | 5 | CONSTRUCTION COMPLETION | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0004 | DSNY - Queens 7 District Garage Annex | 6 | DEVELOP SCOPE | 2018-03-05 | 2018-03-05 | 2018-03-06 | 2018-06-03
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0004 | DSNY - Queens 7 District Garage Annex | 7 | PRELIMINARY DESIGN | 2018-03-05 | 2018-03-05 | 2018-06-04 | 2018-10-01
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0004 | DSNY - Queens 7 District Garage Annex | 8 | FINAL DESIGN | 2018-03-05 | 2018-03-05 | 2018-10-02 | 2019-03-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0004 | DSNY - Queens 7 District Garage Annex | 9 | BID AWARD AND REGISTER CONTRCT | 2018-03-05 | 2018-03-05 | 2019-03-31 | 2019-06-28
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0004 | DSNY - Queens 7 District Garage Annex | 10 | CONSTRUCTION TO 25% | 2018-03-05 | 2018-03-05 | 2019-06-29 | 2019-10-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0004 | DSNY - Queens 7 District Garage Annex | 11 | CONSTRUCTION TO 50% | 2018-03-05 | 2018-03-05 | 2019-10-27 | 2020-02-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0004 | DSNY - Queens 7 District Garage Annex | 12 | CONSTRUCTION TO 75% | 2018-03-05 | 2018-03-05 | 2020-02-24 | 2020-06-22
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0004 | DSNY - Queens 7 District Garage Annex | 13 | ORIGINAL EQUIP & FURNISHING | 2018-03-05 | 2018-03-05 | 2020-06-23 | 2020-09-20
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0004 | DSNY - Queens 7 District Garage Annex | 14 | SUBSTANTIAL COMPLETION | 2018-03-05 | 2018-03-05 | 2020-09-21 | 2020-11-19
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0004 | DSNY - Queens 7 District Garage Annex | 15 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-03-05 | 2018-03-05 | 2020-11-20 | 2022-10-31
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0007 | DOT - Brookville Yard (Rosedale Arterials/Fleet Services) | 1 | DEVELOP SCOPE | 2019-03-01 | 2019-05-29 | 2019-03-01 | 2019-05-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0007 | DOT - Brookville Yard (Rosedale Arterials/Fleet Services) | 2 | PRELIMINARY DESIGN | 2019-05-30 | 2019-09-26 | 2019-05-30 | 2019-09-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0007 | DOT - Brookville Yard (Rosedale Arterials/Fleet Services) | 3 | FINAL DESIGN | 2019-09-27 | 2020-03-24 | 2019-09-27 | 2020-03-24
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0007 | DOT - Brookville Yard (Rosedale Arterials/Fleet Services) | 4 | BID AWARD AND REGISTER CONTRCT | 2020-03-25 | 2020-06-22 | 2020-03-25 | 2020-06-22
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0007 | DOT - Brookville Yard (Rosedale Arterials/Fleet Services) | 5 | CONSTRUCTION TO 25% | 2020-06-23 | 2020-10-20 | 2020-06-23 | 2020-10-20
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0007 | DOT - Brookville Yard (Rosedale Arterials/Fleet Services) | 6 | CONSTRUCTION TO 50% | 2020-10-21 | 2021-02-17 | 2020-10-21 | 2021-02-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0007 | DOT - Brookville Yard (Rosedale Arterials/Fleet Services) | 7 | CONSTRUCTION TO 75% | 2021-02-18 | 2021-06-17 | 2021-02-18 | 2021-06-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0007 | DOT - Brookville Yard (Rosedale Arterials/Fleet Services) | 8 | ORIGINAL EQUIP & FURNISHING | 2021-06-18 | 2021-09-15 | 2021-06-18 | 2021-09-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0007 | DOT - Brookville Yard (Rosedale Arterials/Fleet Services) | 9 | SUBSTANTIAL COMPLETION | 2021-09-16 | 2021-11-14 | 2021-09-16 | 2021-11-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0007 | DOT - Brookville Yard (Rosedale Arterials/Fleet Services) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-11-15 | 2021-12-14 | 2021-11-15 | 2021-12-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0009 | NYPD - 620 Circle Drive - Lighting and HVAC Upgrades | 1 | DEVELOP SCOPE | 2019-03-01 | 2019-05-29 | 2019-03-01 | 2019-05-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0009 | NYPD - 620 Circle Drive - Lighting and HVAC Upgrades | 2 | PRELIMINARY DESIGN | 2019-05-30 | 2019-09-26 | 2019-05-30 | 2019-09-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0009 | NYPD - 620 Circle Drive - Lighting and HVAC Upgrades | 3 | FINAL DESIGN | 2019-09-27 | 2020-03-24 | 2019-09-27 | 2020-03-24
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0009 | NYPD - 620 Circle Drive - Lighting and HVAC Upgrades | 4 | BID AWARD AND REGISTER CONTRCT | 2020-03-25 | 2020-06-22 | 2020-03-25 | 2020-06-22
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0009 | NYPD - 620 Circle Drive - Lighting and HVAC Upgrades | 5 | CONSTRUCTION TO 25% | 2020-06-23 | 2020-10-20 | 2020-06-23 | 2020-10-20
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0009 | NYPD - 620 Circle Drive - Lighting and HVAC Upgrades | 6 | CONSTRUCTION TO 50% | 2020-10-21 | 2021-02-17 | 2020-10-21 | 2021-02-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0009 | NYPD - 620 Circle Drive - Lighting and HVAC Upgrades | 7 | CONSTRUCTION TO 75% | 2021-02-18 | 2021-06-17 | 2021-02-18 | 2021-06-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0009 | NYPD - 620 Circle Drive - Lighting and HVAC Upgrades | 8 | ORIGINAL EQUIP & FURNISHING | 2021-06-18 | 2021-09-15 | 2021-06-18 | 2021-09-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0009 | NYPD - 620 Circle Drive - Lighting and HVAC Upgrades | 9 | SUBSTANTIAL COMPLETION | 2021-09-16 | 2021-11-14 | 2021-09-16 | 2021-11-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0009 | NYPD - 620 Circle Drive - Lighting and HVAC Upgrades | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-11-15 | 2021-12-14 | 2021-11-15 | 2023-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | F175EC268 | NEW FIREHOUSE - EC268 | 1 | DESIGN | 2018-06-15 | 2018-09-12 | 2018-06-15 | 2019-10-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | F175EC268 | NEW FIREHOUSE - EC268 | 2 | BID AWARD AND REGISTER CONTRCT | 2018-09-13 | 2019-06-09 | 2019-10-18 | 2021-07-12
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | F175EC268 | NEW FIREHOUSE - EC268 | 3 | CONSTRUCTION | 2019-06-10 | 2020-07-13 | 2021-07-13 | 2023-01-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | F175EC268 | NEW FIREHOUSE - EC268 | 4 | ORIGINAL EQUIP & FURNISHING | 2020-07-14 | 2020-08-27 | 2023-01-16 | 2023-03-01
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | F175EC268 | NEW FIREHOUSE - EC268 | 5 | SUBSTANTIAL COMPLETION | 2020-08-28 | 2020-10-06 | 2023-03-02 | 2024-01-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | F175EC268 | NEW FIREHOUSE - EC268 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-10-07 | 2020-12-05 | 2024-01-16 | 2026-01-12
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | F175EC268 | NEW FIREHOUSE - EC268 | 7 | DEVELOP SCOPE | 2020-10-07 | 2020-12-05 | 2026-01-13 | 2026-04-12
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | F175EC268 | NEW FIREHOUSE - EC268 | 8 | PRELIMINARY DESIGN | 2020-10-07 | 2020-12-05 | 2026-04-13 | 2026-08-10
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | F175EC268 | NEW FIREHOUSE - EC268 | 9 | FINAL DESIGN | 2020-10-07 | 2020-12-05 | 2026-08-11 | 2027-02-06
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | F175EC268 | NEW FIREHOUSE - EC268 | 10 | BID AWARD AND REGISTER CONTRCT | 2020-10-07 | 2020-12-05 | 2027-02-07 | 2027-05-07
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | F175EC268 | NEW FIREHOUSE - EC268 | 11 | CONSTRUCTION TO 25% | 2020-10-07 | 2020-12-05 | 2027-05-08 | 2027-09-04
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | F175EC268 | NEW FIREHOUSE - EC268 | 12 | CONSTRUCTION TO 50% | 2020-10-07 | 2020-12-05 | 2027-09-05 | 2028-01-02
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | F175EC268 | NEW FIREHOUSE - EC268 | 13 | CONSTRUCTION TO 75% | 2020-10-07 | 2020-12-05 | 2028-01-03 | 2028-05-01
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | F175EC268 | NEW FIREHOUSE - EC268 | 14 | ORIGINAL EQUIP & FURNISHING | 2020-10-07 | 2020-12-05 | 2028-05-02 | 2028-07-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | F175EC268 | NEW FIREHOUSE - EC268 | 15 | SUBSTANTIAL COMPLETION | 2020-10-07 | 2020-12-05 | 2028-07-31 | 2028-09-28
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | F175EC268 | NEW FIREHOUSE - EC268 | 16 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-10-07 | 2020-12-05 | 2028-09-29 | 2028-10-28
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | F204INFRA | Fort Totten Infrastructure Upgrade | 1 | PROJECT START | 2020-01-06 | 2020-06-28 | 2020-01-06 | 2020-06-28
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | F204INFRA | Fort Totten Infrastructure Upgrade | 2 | DESIGN START | 2020-06-29 | 2021-01-04 | 2020-06-29 | 2021-01-04
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | F204INFRA | Fort Totten Infrastructure Upgrade | 3 | DESIGN COMPLETION | 2021-01-05 | 2022-01-07 | 2021-01-05 | 2022-01-07
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | F204INFRA | Fort Totten Infrastructure Upgrade | 4 | CONSTRUCTION START | 2022-01-08 | 2022-12-16 | 2022-01-08 | 2022-12-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | F204INFRA | Fort Totten Infrastructure Upgrade | 5 | CONSTRUCTION COMPLETION | 2022-12-17 | 2024-11-15 | 2022-12-17 | 2024-11-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | FD175273H | INSTALLATION OF A HVAC SYSTEM - E273 | 1 | PROJECT START | 2012-10-24 | 2012-10-24 | 2012-10-24 | 2012-10-24
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | FD175273H | INSTALLATION OF A HVAC SYSTEM - E273 | 2 | DESIGN START | 2012-10-25 | 2013-05-23 | 2012-10-25 | 2013-05-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | FD175273H | INSTALLATION OF A HVAC SYSTEM - E273 | 3 | DESIGN COMPLETION | 2013-05-24 | 2013-11-08 | 2013-05-24 | 2013-11-08
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | FD175273H | INSTALLATION OF A HVAC SYSTEM - E273 | 4 | CONSTRUCTION START | 2013-11-09 | 2014-06-30 | 2013-11-09 | 2014-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | FD175273H | INSTALLATION OF A HVAC SYSTEM - E273 | 5 | CONSTRUCTION COMPLETION | 2014-07-01 | 2015-07-24 | 2014-07-01 | 2018-07-24
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCJA03-3A | GI - Cons of ROW Bioswales & Stormwater GS in JAM-003, 3A | 1 | DEVELOP SCOPE | 2017-03-01 | 2017-05-29 | 2017-03-01 | 2017-05-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCJA03-3A | GI - Cons of ROW Bioswales & Stormwater GS in JAM-003, 3A | 2 | PRELIMINARY DESIGN | 2017-05-30 | 2017-09-26 | 2017-05-30 | 2017-09-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCJA03-3A | GI - Cons of ROW Bioswales & Stormwater GS in JAM-003, 3A | 3 | FINAL DESIGN | 2017-09-27 | 2018-03-25 | 2017-09-27 | 2018-03-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCJA03-3A | GI - Cons of ROW Bioswales & Stormwater GS in JAM-003, 3A | 4 | BID AWARD AND REGISTER CONTRCT | 2018-03-26 | 2018-06-23 | 2018-03-26 | 2018-06-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCJA03-3A | GI - Cons of ROW Bioswales & Stormwater GS in JAM-003, 3A | 5 | CONSTRUCTION TO 25% | 2018-06-24 | 2018-10-21 | 2018-06-24 | 2018-10-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCJA03-3A | GI - Cons of ROW Bioswales & Stormwater GS in JAM-003, 3A | 6 | CONSTRUCTION TO 50% | 2018-10-22 | 2019-02-18 | 2018-10-22 | 2019-02-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCJA03-3A | GI - Cons of ROW Bioswales & Stormwater GS in JAM-003, 3A | 7 | CONSTRUCTION TO 75% | 2019-02-19 | 2019-06-18 | 2019-02-19 | 2019-06-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCJA03-3A | GI - Cons of ROW Bioswales & Stormwater GS in JAM-003, 3A | 8 | ORIGINAL EQUIP & FURNISHING | 2019-06-19 | 2019-09-16 | 2019-06-19 | 2019-09-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCJA03-3A | GI - Cons of ROW Bioswales & Stormwater GS in JAM-003, 3A | 9 | SUBSTANTIAL COMPLETION | 2019-09-17 | 2019-11-15 | 2019-09-17 | 2020-07-05
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCJA03-3A | GI - Cons of ROW Bioswales & Stormwater GS in JAM-003, 3A | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-11-16 | 2019-12-15 | 2020-07-06 | 2023-04-11
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCJA03-3B | GI - CONS OF ROW GI IN JAMAICA BAY CSO AREAS JAM-03 & JAM-3A | 1 | DEVELOP SCOPE | 2017-03-01 | 2017-05-29 | 2015-09-28 | 2015-12-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCJA03-3B | GI - CONS OF ROW GI IN JAMAICA BAY CSO AREAS JAM-03 & JAM-3A | 2 | PRELIMINARY DESIGN | 2017-05-30 | 2017-09-26 | 2015-12-27 | 2016-04-24
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCJA03-3B | GI - CONS OF ROW GI IN JAMAICA BAY CSO AREAS JAM-03 & JAM-3A | 3 | FINAL DESIGN | 2017-09-27 | 2018-03-25 | 2016-04-25 | 2016-10-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCJA03-3B | GI - CONS OF ROW GI IN JAMAICA BAY CSO AREAS JAM-03 & JAM-3A | 4 | BID AWARD AND REGISTER CONTRCT | 2018-03-26 | 2018-06-23 | 2016-10-22 | 2017-01-19
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCJA03-3B | GI - CONS OF ROW GI IN JAMAICA BAY CSO AREAS JAM-03 & JAM-3A | 5 | CONSTRUCTION TO 25% | 2018-06-24 | 2018-10-21 | 2017-01-20 | 2017-05-19
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCJA03-3B | GI - CONS OF ROW GI IN JAMAICA BAY CSO AREAS JAM-03 & JAM-3A | 6 | CONSTRUCTION TO 50% | 2018-10-22 | 2019-02-18 | 2017-05-20 | 2017-09-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCJA03-3B | GI - CONS OF ROW GI IN JAMAICA BAY CSO AREAS JAM-03 & JAM-3A | 7 | CONSTRUCTION TO 75% | 2019-02-19 | 2019-06-18 | 2017-09-17 | 2018-01-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCJA03-3B | GI - CONS OF ROW GI IN JAMAICA BAY CSO AREAS JAM-03 & JAM-3A | 8 | ORIGINAL EQUIP & FURNISHING | 2019-06-19 | 2019-09-16 | 2018-01-15 | 2018-04-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCJA03-3B | GI - CONS OF ROW GI IN JAMAICA BAY CSO AREAS JAM-03 & JAM-3A | 9 | SUBSTANTIAL COMPLETION | 2019-09-17 | 2019-11-15 | 2018-04-15 | 2018-06-13
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCJA03-3B | GI - CONS OF ROW GI IN JAMAICA BAY CSO AREAS JAM-03 & JAM-3A | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-11-16 | 2019-12-15 | 2018-06-14 | 2024-03-11
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCNC77-02 | GI - GREEN INFRASTRUCTURE IN NEWTOWN CREEK AREA | 2 | PRELIMINARY DESIGN | 2014-05-30 | 2014-09-26 | 2014-05-30 | 2014-09-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCNC77-02 | GI - GREEN INFRASTRUCTURE IN NEWTOWN CREEK AREA | 3 | FINAL DESIGN | 2014-09-27 | 2015-03-25 | 2014-09-27 | 2015-03-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCNC77-02 | GI - GREEN INFRASTRUCTURE IN NEWTOWN CREEK AREA | 4 | BID AWARD AND REGISTER CONTRCT | 2015-03-26 | 2015-06-23 | 2015-03-26 | 2015-06-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCNC77-02 | GI - GREEN INFRASTRUCTURE IN NEWTOWN CREEK AREA | 5 | CONSTRUCTION TO 25% | 2015-06-24 | 2015-10-21 | 2015-06-24 | 2015-10-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCNC77-02 | GI - GREEN INFRASTRUCTURE IN NEWTOWN CREEK AREA | 6 | CONSTRUCTION TO 50% | 2015-10-22 | 2016-02-18 | 2015-10-22 | 2016-02-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCNC77-02 | GI - GREEN INFRASTRUCTURE IN NEWTOWN CREEK AREA | 7 | CONSTRUCTION TO 75% | 2016-02-19 | 2016-06-17 | 2016-02-19 | 2016-06-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCNC77-02 | GI - GREEN INFRASTRUCTURE IN NEWTOWN CREEK AREA | 8 | ORIGINAL EQUIP & FURNISHING | 2016-06-18 | 2016-09-15 | 2016-06-18 | 2016-09-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCNC77-02 | GI - GREEN INFRASTRUCTURE IN NEWTOWN CREEK AREA | 9 | SUBSTANTIAL COMPLETION | 2016-09-16 | 2016-11-14 | 2016-09-16 | 2016-11-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCNC77-02 | GI - GREEN INFRASTRUCTURE IN NEWTOWN CREEK AREA | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-11-15 | 2016-12-14 | 2016-11-15 | 2019-12-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCTI10-1A | CONS OF ROW GI FLUSHING CRK CSO TRIB AREA TI-10, ST 1, PH A | 1 | DEVELOP SCOPE | 2018-03-01 | 2018-05-29 | 2018-03-01 | 2018-05-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCTI10-1A | CONS OF ROW GI FLUSHING CRK CSO TRIB AREA TI-10, ST 1, PH A | 2 | PRELIMINARY DESIGN | 2018-05-30 | 2018-09-26 | 2018-05-30 | 2018-09-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCTI10-1A | CONS OF ROW GI FLUSHING CRK CSO TRIB AREA TI-10, ST 1, PH A | 3 | FINAL DESIGN | 2018-09-27 | 2019-03-25 | 2018-09-27 | 2019-03-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCTI10-1A | CONS OF ROW GI FLUSHING CRK CSO TRIB AREA TI-10, ST 1, PH A | 4 | BID AWARD AND REGISTER CONTRCT | 2019-03-26 | 2019-06-23 | 2019-03-26 | 2019-06-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCTI10-1A | CONS OF ROW GI FLUSHING CRK CSO TRIB AREA TI-10, ST 1, PH A | 5 | CONSTRUCTION TO 25% | 2019-06-24 | 2019-10-21 | 2019-06-24 | 2019-10-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCTI10-1A | CONS OF ROW GI FLUSHING CRK CSO TRIB AREA TI-10, ST 1, PH A | 6 | CONSTRUCTION TO 50% | 2019-10-22 | 2020-02-18 | 2019-10-22 | 2020-02-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCTI10-1A | CONS OF ROW GI FLUSHING CRK CSO TRIB AREA TI-10, ST 1, PH A | 7 | CONSTRUCTION TO 75% | 2020-02-19 | 2020-06-17 | 2020-02-19 | 2020-06-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCTI10-1A | CONS OF ROW GI FLUSHING CRK CSO TRIB AREA TI-10, ST 1, PH A | 8 | ORIGINAL EQUIP & FURNISHING | 2020-06-18 | 2020-09-15 | 2020-06-18 | 2020-09-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCTI10-1A | CONS OF ROW GI FLUSHING CRK CSO TRIB AREA TI-10, ST 1, PH A | 9 | SUBSTANTIAL COMPLETION | 2020-09-16 | 2020-11-14 | 2020-09-16 | 2020-11-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCTI10-1A | CONS OF ROW GI FLUSHING CRK CSO TRIB AREA TI-10, ST 1, PH A | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-11-15 | 2020-12-14 | 2020-11-15 | 2020-12-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCTI10-1B | CONS OF ROW GI FLUSHING CRK CSO TRIB AREA TI-10, ST 1, PH B | 1 | DEVELOP SCOPE | 2017-03-01 | 2017-05-29 | 2014-11-14 | 2017-05-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCTI10-1B | CONS OF ROW GI FLUSHING CRK CSO TRIB AREA TI-10, ST 1, PH B | 2 | PRELIMINARY DESIGN | 2017-05-30 | 2017-09-26 | 2017-05-30 | 2017-09-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCTI10-1B | CONS OF ROW GI FLUSHING CRK CSO TRIB AREA TI-10, ST 1, PH B | 3 | FINAL DESIGN | 2017-09-27 | 2018-03-25 | 2017-09-27 | 2018-03-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCTI10-1B | CONS OF ROW GI FLUSHING CRK CSO TRIB AREA TI-10, ST 1, PH B | 4 | BID AWARD AND REGISTER CONTRCT | 2018-03-26 | 2018-06-23 | 2018-03-26 | 2018-06-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCTI10-1B | CONS OF ROW GI FLUSHING CRK CSO TRIB AREA TI-10, ST 1, PH B | 5 | CONSTRUCTION TO 25% | 2018-06-24 | 2018-10-21 | 2018-06-24 | 2018-10-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCTI10-1B | CONS OF ROW GI FLUSHING CRK CSO TRIB AREA TI-10, ST 1, PH B | 6 | CONSTRUCTION TO 50% | 2018-10-22 | 2019-02-18 | 2018-10-22 | 2019-02-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCTI10-1B | CONS OF ROW GI FLUSHING CRK CSO TRIB AREA TI-10, ST 1, PH B | 7 | CONSTRUCTION TO 75% | 2019-02-19 | 2019-06-18 | 2019-02-19 | 2019-06-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCTI10-1B | CONS OF ROW GI FLUSHING CRK CSO TRIB AREA TI-10, ST 1, PH B | 8 | ORIGINAL EQUIP & FURNISHING | 2019-06-19 | 2019-09-16 | 2019-06-19 | 2019-09-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCTI10-1B | CONS OF ROW GI FLUSHING CRK CSO TRIB AREA TI-10, ST 1, PH B | 9 | SUBSTANTIAL COMPLETION | 2019-09-17 | 2019-11-15 | 2019-09-17 | 2019-11-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCTI10-1B | CONS OF ROW GI FLUSHING CRK CSO TRIB AREA TI-10, ST 1, PH B | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-11-16 | 2019-12-15 | 2019-11-16 | 2024-11-06
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCTI10-4B | CONS OF ROW GI IN PHASE 4 FLUSHING CRK CSO TRIB AREA TI-10 | 1 | DEVELOP SCOPE | 2017-03-01 | 2017-05-29 | 2017-03-01 | 2017-05-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCTI10-4B | CONS OF ROW GI IN PHASE 4 FLUSHING CRK CSO TRIB AREA TI-10 | 2 | PRELIMINARY DESIGN | 2017-05-30 | 2017-09-26 | 2017-05-30 | 2017-09-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCTI10-4B | CONS OF ROW GI IN PHASE 4 FLUSHING CRK CSO TRIB AREA TI-10 | 3 | FINAL DESIGN | 2017-09-27 | 2018-03-25 | 2017-09-27 | 2018-03-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCTI10-4B | CONS OF ROW GI IN PHASE 4 FLUSHING CRK CSO TRIB AREA TI-10 | 4 | BID AWARD AND REGISTER CONTRCT | 2018-03-26 | 2018-06-23 | 2018-03-26 | 2018-06-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCTI10-4B | CONS OF ROW GI IN PHASE 4 FLUSHING CRK CSO TRIB AREA TI-10 | 5 | CONSTRUCTION TO 25% | 2018-06-24 | 2018-10-21 | 2018-06-24 | 2018-10-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCTI10-4B | CONS OF ROW GI IN PHASE 4 FLUSHING CRK CSO TRIB AREA TI-10 | 6 | CONSTRUCTION TO 50% | 2018-10-22 | 2019-02-18 | 2018-10-22 | 2019-02-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCTI10-4B | CONS OF ROW GI IN PHASE 4 FLUSHING CRK CSO TRIB AREA TI-10 | 7 | CONSTRUCTION TO 75% | 2019-02-19 | 2019-06-18 | 2019-02-19 | 2019-06-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCTI10-4B | CONS OF ROW GI IN PHASE 4 FLUSHING CRK CSO TRIB AREA TI-10 | 8 | ORIGINAL EQUIP & FURNISHING | 2019-06-19 | 2019-09-16 | 2019-06-19 | 2019-09-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCTI10-4B | CONS OF ROW GI IN PHASE 4 FLUSHING CRK CSO TRIB AREA TI-10 | 9 | SUBSTANTIAL COMPLETION | 2019-09-17 | 2019-11-15 | 2019-09-17 | 2019-11-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCTI10-4B | CONS OF ROW GI IN PHASE 4 FLUSHING CRK CSO TRIB AREA TI-10 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-11-16 | 2019-12-15 | 2019-11-16 | 2024-06-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCTI11-02 | GI-Construct ROW Bioswales Stormwater Greenstreets in TI-011 | 1 | DEVELOP SCOPE | 2017-03-01 | 2017-05-29 | 2017-03-01 | 2017-05-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCTI11-02 | GI-Construct ROW Bioswales Stormwater Greenstreets in TI-011 | 2 | PRELIMINARY DESIGN | 2017-05-30 | 2017-09-26 | 2017-05-30 | 2017-09-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCTI11-02 | GI-Construct ROW Bioswales Stormwater Greenstreets in TI-011 | 3 | FINAL DESIGN | 2017-09-27 | 2018-03-25 | 2017-09-27 | 2018-03-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCTI11-02 | GI-Construct ROW Bioswales Stormwater Greenstreets in TI-011 | 4 | BID AWARD AND REGISTER CONTRCT | 2018-03-26 | 2018-06-23 | 2018-03-26 | 2018-06-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCTI11-02 | GI-Construct ROW Bioswales Stormwater Greenstreets in TI-011 | 5 | CONSTRUCTION TO 25% | 2018-06-24 | 2018-10-21 | 2018-06-24 | 2018-10-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCTI11-02 | GI-Construct ROW Bioswales Stormwater Greenstreets in TI-011 | 6 | CONSTRUCTION TO 50% | 2018-10-22 | 2019-02-18 | 2018-10-22 | 2019-02-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCTI11-02 | GI-Construct ROW Bioswales Stormwater Greenstreets in TI-011 | 7 | CONSTRUCTION TO 75% | 2019-02-19 | 2019-06-18 | 2019-02-19 | 2019-06-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCTI11-02 | GI-Construct ROW Bioswales Stormwater Greenstreets in TI-011 | 8 | ORIGINAL EQUIP & FURNISHING | 2019-06-19 | 2019-09-16 | 2019-06-19 | 2019-09-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCTI11-02 | GI-Construct ROW Bioswales Stormwater Greenstreets in TI-011 | 9 | SUBSTANTIAL COMPLETION | 2019-09-17 | 2019-11-15 | 2019-09-17 | 2019-11-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCTI11-02 | GI-Construct ROW Bioswales Stormwater Greenstreets in TI-011 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-11-16 | 2019-12-15 | 2019-11-16 | 2023-05-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GQTI03-23 | GI - GREEN INFRASTRUCTURE IN TI-003 & TI-023 EAST RIVER CSO | 1 | DEVELOP SCOPE | 2017-03-01 | 2017-05-29 | 2017-03-01 | 2017-05-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GQTI03-23 | GI - GREEN INFRASTRUCTURE IN TI-003 & TI-023 EAST RIVER CSO | 2 | PRELIMINARY DESIGN | 2017-05-30 | 2017-09-26 | 2017-05-30 | 2017-09-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GQTI03-23 | GI - GREEN INFRASTRUCTURE IN TI-003 & TI-023 EAST RIVER CSO | 3 | FINAL DESIGN | 2017-09-27 | 2019-06-25 | 2017-09-27 | 2019-06-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GQTI03-23 | GI - GREEN INFRASTRUCTURE IN TI-003 & TI-023 EAST RIVER CSO | 4 | BID AWARD AND REGISTER CONTRCT | 2019-06-26 | 2019-09-23 | 2019-06-26 | 2019-09-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GQTI03-23 | GI - GREEN INFRASTRUCTURE IN TI-003 & TI-023 EAST RIVER CSO | 5 | CONSTRUCTION TO 25% | 2019-09-24 | 2020-01-21 | 2019-09-24 | 2020-01-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GQTI03-23 | GI - GREEN INFRASTRUCTURE IN TI-003 & TI-023 EAST RIVER CSO | 6 | CONSTRUCTION TO 50% | 2020-01-22 | 2020-05-20 | 2020-01-22 | 2020-05-20
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GQTI03-23 | GI - GREEN INFRASTRUCTURE IN TI-003 & TI-023 EAST RIVER CSO | 7 | CONSTRUCTION TO 75% | 2020-05-21 | 2020-09-17 | 2020-05-21 | 2020-09-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GQTI03-23 | GI - GREEN INFRASTRUCTURE IN TI-003 & TI-023 EAST RIVER CSO | 8 | ORIGINAL EQUIP & FURNISHING | 2020-09-18 | 2020-12-16 | 2020-09-18 | 2020-12-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GQTI03-23 | GI - GREEN INFRASTRUCTURE IN TI-003 & TI-023 EAST RIVER CSO | 9 | SUBSTANTIAL COMPLETION | 2020-12-17 | 2021-02-14 | 2020-12-17 | 2021-02-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GQTI03-23 | GI - GREEN INFRASTRUCTURE IN TI-003 & TI-023 EAST RIVER CSO | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-02-15 | 2021-03-16 | 2021-02-15 | 2022-12-01
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HBPED216S | PED BRIDGE - 216 ST (Q) | 1 | DEVELOP SCOPE | 2014-07-01 | 2014-09-28 | 2014-07-01 | 2014-09-28
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HBPED216S | PED BRIDGE - 216 ST (Q) | 2 | PRELIMINARY DESIGN | 2014-09-29 | 2015-01-26 | 2014-09-29 | 2015-01-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HBPED216S | PED BRIDGE - 216 ST (Q) | 3 | FINAL DESIGN | 2015-01-27 | 2015-07-25 | 2015-01-27 | 2015-07-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HBPED216S | PED BRIDGE - 216 ST (Q) | 4 | BID AWARD AND REGISTER CONTRCT | 2015-07-26 | 2015-10-23 | 2015-07-26 | 2015-10-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HBPED216S | PED BRIDGE - 216 ST (Q) | 5 | CONSTRUCTION TO 25% | 2015-10-24 | 2016-02-20 | 2015-10-24 | 2016-02-20
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HBPED216S | PED BRIDGE - 216 ST (Q) | 6 | CONSTRUCTION TO 50% | 2016-02-21 | 2016-06-19 | 2016-02-21 | 2016-06-19
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HBPED216S | PED BRIDGE - 216 ST (Q) | 7 | CONSTRUCTION TO 75% | 2016-06-20 | 2016-10-17 | 2016-06-20 | 2016-10-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HBPED216S | PED BRIDGE - 216 ST (Q) | 8 | ORIGINAL EQUIP & FURNISHING | 2016-10-18 | 2017-01-15 | 2016-10-18 | 2017-01-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HBPED216S | PED BRIDGE - 216 ST (Q) | 9 | SUBSTANTIAL COMPLETION | 2017-01-16 | 2017-03-16 | 2017-01-16 | 2017-03-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HBPED216S | PED BRIDGE - 216 ST (Q) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-17 | 2017-04-15 | 2017-03-17 | 2024-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HBPED800Q | PED BRIDGE - PORPOISE BRIDGE AND TIDE GATE (SANDY4-30, 4-31) | 1 | DEVELOP SCOPE | 2017-03-01 | 2017-05-29 | 2017-03-01 | 2017-05-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HBPED800Q | PED BRIDGE - PORPOISE BRIDGE AND TIDE GATE (SANDY4-30, 4-31) | 2 | PRELIMINARY DESIGN | 2017-05-30 | 2017-09-26 | 2017-05-30 | 2017-09-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HBPED800Q | PED BRIDGE - PORPOISE BRIDGE AND TIDE GATE (SANDY4-30, 4-31) | 3 | FINAL DESIGN | 2017-09-27 | 2018-03-25 | 2017-09-27 | 2018-03-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HBPED800Q | PED BRIDGE - PORPOISE BRIDGE AND TIDE GATE (SANDY4-30, 4-31) | 4 | BID AWARD AND REGISTER CONTRCT | 2018-03-26 | 2018-06-23 | 2018-03-26 | 2018-06-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HBPED800Q | PED BRIDGE - PORPOISE BRIDGE AND TIDE GATE (SANDY4-30, 4-31) | 5 | CONSTRUCTION TO 25% | 2018-06-24 | 2018-10-21 | 2018-06-24 | 2018-10-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HBPED800Q | PED BRIDGE - PORPOISE BRIDGE AND TIDE GATE (SANDY4-30, 4-31) | 6 | CONSTRUCTION TO 50% | 2018-10-22 | 2019-02-18 | 2018-10-22 | 2019-02-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HBPED800Q | PED BRIDGE - PORPOISE BRIDGE AND TIDE GATE (SANDY4-30, 4-31) | 7 | CONSTRUCTION TO 75% | 2019-02-19 | 2019-06-18 | 2019-02-19 | 2019-06-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HBPED800Q | PED BRIDGE - PORPOISE BRIDGE AND TIDE GATE (SANDY4-30, 4-31) | 8 | ORIGINAL EQUIP & FURNISHING | 2019-06-19 | 2019-09-16 | 2019-06-19 | 2019-09-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HBPED800Q | PED BRIDGE - PORPOISE BRIDGE AND TIDE GATE (SANDY4-30, 4-31) | 9 | SUBSTANTIAL COMPLETION | 2019-09-17 | 2019-11-15 | 2019-09-17 | 2019-11-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HBPED800Q | PED BRIDGE - PORPOISE BRIDGE AND TIDE GATE (SANDY4-30, 4-31) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-11-16 | 2019-12-15 | 2019-11-16 | 2023-07-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HD-153C2 | EDGEMERE (PHASE C2) | 1 | DEVELOP SCOPE | 2008-03-01 | 2008-05-29 | 2008-03-01 | 2008-05-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HD-153C2 | EDGEMERE (PHASE C2) | 2 | PRELIMINARY DESIGN | 2008-05-30 | 2008-09-26 | 2008-05-30 | 2008-09-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HD-153C2 | EDGEMERE (PHASE C2) | 3 | FINAL DESIGN | 2008-09-27 | 2009-03-25 | 2008-09-27 | 2009-03-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HD-153C2 | EDGEMERE (PHASE C2) | 4 | BID AWARD AND REGISTER CONTRCT | 2009-03-26 | 2009-06-23 | 2009-03-26 | 2009-06-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HD-153C2 | EDGEMERE (PHASE C2) | 5 | CONSTRUCTION TO 25% | 2009-06-24 | 2009-10-21 | 2009-06-24 | 2009-10-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HD-153C2 | EDGEMERE (PHASE C2) | 6 | CONSTRUCTION TO 50% | 2009-10-22 | 2010-02-18 | 2009-10-22 | 2010-02-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HD-153C2 | EDGEMERE (PHASE C2) | 7 | CONSTRUCTION TO 75% | 2010-02-19 | 2010-06-18 | 2010-02-19 | 2010-06-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HD-153C2 | EDGEMERE (PHASE C2) | 8 | ORIGINAL EQUIP & FURNISHING | 2010-06-19 | 2010-09-16 | 2010-06-19 | 2010-09-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HD-153C2 | EDGEMERE (PHASE C2) | 9 | SUBSTANTIAL COMPLETION | 2010-09-17 | 2010-11-15 | 2010-09-17 | 2010-11-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HD-153C2 | EDGEMERE (PHASE C2) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2010-11-16 | 2010-12-15 | 2012-12-27 | 2023-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82CORHC | Corona Health Center-Exterior Facade, Basement and Lobby | 1 | DESIGN | 2016-01-01 | 2017-05-24 | 2016-01-01 | 2016-01-01
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82CORHC | Corona Health Center-Exterior Facade, Basement and Lobby | 2 | CONSTRUCTION | 2017-05-25 | 2022-05-23 | 2016-01-02 | 2017-01-02
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82CORHC | Corona Health Center-Exterior Facade, Basement and Lobby | 3 | DESIGN COMPLETION | 2022-05-24 | 2022-05-23 | 2017-01-03 | 2018-01-03
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82CORHC | Corona Health Center-Exterior Facade, Basement and Lobby | 4 | DEVELOP SCOPE | 2022-05-24 | 2022-05-23 | 2018-01-04 | 2019-01-04
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82CORHC | Corona Health Center-Exterior Facade, Basement and Lobby | 5 | PRELIMINARY DESIGN | 2022-05-24 | 2022-05-23 | 2019-01-05 | 2024-01-05
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82CORHC | Corona Health Center-Exterior Facade, Basement and Lobby | 6 | FINAL DESIGN | 2022-05-24 | 2022-05-23 | 2019-01-05 | 2024-01-05
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82CORHC | Corona Health Center-Exterior Facade, Basement and Lobby | 7 | BID AWARD AND REGISTER CONTRCT | 2022-05-24 | 2022-05-23 | 2019-01-05 | 2024-01-05
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82CORHC | Corona Health Center-Exterior Facade, Basement and Lobby | 8 | CONSTRUCTION TO 25% | 2022-05-24 | 2022-05-23 | 2019-01-05 | 2024-01-05
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82CORHC | Corona Health Center-Exterior Facade, Basement and Lobby | 9 | CONSTRUCTION TO 50% | 2022-05-24 | 2022-05-23 | 2019-01-05 | 2024-01-05
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82CORHC | Corona Health Center-Exterior Facade, Basement and Lobby | 10 | CONSTRUCTION TO 75% | 2022-05-24 | 2022-05-23 | 2019-01-05 | 2024-01-05
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82CORHC | Corona Health Center-Exterior Facade, Basement and Lobby | 11 | ORIGINAL EQUIP & FURNISHING | 2022-05-24 | 2022-05-23 | 2019-01-05 | 2024-01-05
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82CORHC | Corona Health Center-Exterior Facade, Basement and Lobby | 12 | SUBSTANTIAL COMPLETION | 2022-05-24 | 2022-05-23 | 2019-01-05 | 2024-01-05
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82CORHC | Corona Health Center-Exterior Facade, Basement and Lobby | 13 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-05-24 | 2022-06-22 | 2019-01-05 | 2024-01-05
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HRC002MPL | A/C UPGRADE OF MONTESSORI PROGRESSIVE LEARNING CTR | 1 | PROJECT START | 1996-08-31 | 1996-08-31 | 1996-08-31 | 1996-08-31
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HRC002MPL | A/C UPGRADE OF MONTESSORI PROGRESSIVE LEARNING CTR | 2 | DESIGN START | 1997-07-21 | 1997-07-21 | 1997-07-21 | 1997-07-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HRC002MPL | A/C UPGRADE OF MONTESSORI PROGRESSIVE LEARNING CTR | 3 | DESIGN COMPLETION | 1998-03-30 | 1998-03-30 | 1998-03-30 | 1998-03-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HRC002MPL | A/C UPGRADE OF MONTESSORI PROGRESSIVE LEARNING CTR | 4 | CONSTRUCTION START | 1998-06-22 | 1998-06-22 | 1998-06-22 | 2018-06-22
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HRC002MPL | A/C UPGRADE OF MONTESSORI PROGRESSIVE LEARNING CTR | 5 | CONSTRUCTION COMPLETION | 1998-11-25 | 1998-11-25 | 1998-11-25 | 2024-07-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWC988QB4 | QUEENS BOULEVARD MEDIAN EXTENSIONS INTO CROSSWALKS, QUEENS | 1 | DEVELOP SCOPE | 2009-02-21 | 2009-05-21 | 2011-07-01 | 2011-09-28
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWC988QB4 | QUEENS BOULEVARD MEDIAN EXTENSIONS INTO CROSSWALKS, QUEENS | 2 | PRELIMINARY DESIGN | 2009-05-22 | 2009-09-18 | 2011-09-29 | 2012-01-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWC988QB4 | QUEENS BOULEVARD MEDIAN EXTENSIONS INTO CROSSWALKS, QUEENS | 3 | FINAL DESIGN | 2009-09-19 | 2010-03-17 | 2012-01-27 | 2012-07-24
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWC988QB4 | QUEENS BOULEVARD MEDIAN EXTENSIONS INTO CROSSWALKS, QUEENS | 4 | BID AWARD AND REGISTER CONTRCT | 2010-03-18 | 2010-06-15 | 2012-07-25 | 2012-10-22
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWC988QB4 | QUEENS BOULEVARD MEDIAN EXTENSIONS INTO CROSSWALKS, QUEENS | 5 | CONSTRUCTION TO 25% | 2010-06-16 | 2010-10-13 | 2012-10-23 | 2013-02-19
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWC988QB4 | QUEENS BOULEVARD MEDIAN EXTENSIONS INTO CROSSWALKS, QUEENS | 6 | CONSTRUCTION TO 50% | 2010-10-14 | 2011-02-10 | 2013-02-20 | 2013-06-19
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWC988QB4 | QUEENS BOULEVARD MEDIAN EXTENSIONS INTO CROSSWALKS, QUEENS | 7 | CONSTRUCTION TO 75% | 2011-02-11 | 2011-06-10 | 2013-06-20 | 2013-10-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWC988QB4 | QUEENS BOULEVARD MEDIAN EXTENSIONS INTO CROSSWALKS, QUEENS | 8 | ORIGINAL EQUIP & FURNISHING | 2011-06-11 | 2011-09-08 | 2013-10-18 | 2014-01-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWC988QB4 | QUEENS BOULEVARD MEDIAN EXTENSIONS INTO CROSSWALKS, QUEENS | 9 | SUBSTANTIAL COMPLETION | 2011-09-09 | 2011-11-07 | 2014-01-16 | 2014-03-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWC988QB4 | QUEENS BOULEVARD MEDIAN EXTENSIONS INTO CROSSWALKS, QUEENS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2011-11-08 | 2011-12-07 | 2014-03-17 | 2021-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4C1 | Safe Routes to Schools - Phase 4C1 | 1 | DEVELOP SCOPE | 2016-03-01 | 2016-05-29 | 2016-03-01 | 2016-05-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4C1 | Safe Routes to Schools - Phase 4C1 | 2 | PRELIMINARY DESIGN | 2016-05-30 | 2016-09-26 | 2016-05-30 | 2016-09-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4C1 | Safe Routes to Schools - Phase 4C1 | 3 | FINAL DESIGN | 2016-09-27 | 2017-03-25 | 2016-09-27 | 2017-03-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4C1 | Safe Routes to Schools - Phase 4C1 | 4 | BID AWARD AND REGISTER CONTRCT | 2017-03-26 | 2017-06-23 | 2017-03-26 | 2017-06-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4C1 | Safe Routes to Schools - Phase 4C1 | 5 | CONSTRUCTION TO 25% | 2017-06-24 | 2017-10-21 | 2017-06-24 | 2017-10-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4C1 | Safe Routes to Schools - Phase 4C1 | 6 | CONSTRUCTION TO 50% | 2017-10-22 | 2018-02-18 | 2017-10-22 | 2018-02-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4C1 | Safe Routes to Schools - Phase 4C1 | 7 | CONSTRUCTION TO 75% | 2018-02-19 | 2018-06-18 | 2018-02-19 | 2018-06-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4C1 | Safe Routes to Schools - Phase 4C1 | 8 | ORIGINAL EQUIP & FURNISHING | 2018-06-19 | 2018-09-16 | 2018-06-19 | 2018-09-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4C1 | Safe Routes to Schools - Phase 4C1 | 9 | SUBSTANTIAL COMPLETION | 2018-09-17 | 2018-11-15 | 2018-09-17 | 2018-11-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4C1 | Safe Routes to Schools - Phase 4C1 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-11-16 | 2018-12-15 | 2018-11-16 | 2024-04-10
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPQN | SAFE ROUTES TO SCHOOLS- QUEENS | 1 | DEVELOP SCOPE | 2018-01-01 | 2018-03-31 | 2018-01-01 | 2018-03-31
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPQN | SAFE ROUTES TO SCHOOLS- QUEENS | 2 | PRELIMINARY DESIGN | 2018-04-01 | 2018-07-29 | 2018-04-01 | 2018-07-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPQN | SAFE ROUTES TO SCHOOLS- QUEENS | 3 | FINAL DESIGN | 2018-07-30 | 2019-01-25 | 2018-07-30 | 2019-01-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPQN | SAFE ROUTES TO SCHOOLS- QUEENS | 4 | BID AWARD AND REGISTER CONTRCT | 2019-01-26 | 2021-06-23 | 2019-01-26 | 2021-06-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPQN | SAFE ROUTES TO SCHOOLS- QUEENS | 5 | CONSTRUCTION TO 25% | 2021-06-24 | 2021-10-21 | 2021-06-24 | 2021-10-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPQN | SAFE ROUTES TO SCHOOLS- QUEENS | 6 | CONSTRUCTION TO 50% | 2021-10-22 | 2022-02-18 | 2021-10-22 | 2022-02-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPQN | SAFE ROUTES TO SCHOOLS- QUEENS | 7 | CONSTRUCTION TO 75% | 2022-02-19 | 2022-06-18 | 2022-02-19 | 2022-06-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPQN | SAFE ROUTES TO SCHOOLS- QUEENS | 8 | ORIGINAL EQUIP & FURNISHING | 2022-06-19 | 2022-09-16 | 2022-06-19 | 2022-09-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPQN | SAFE ROUTES TO SCHOOLS- QUEENS | 9 | SUBSTANTIAL COMPLETION | 2022-09-17 | 2022-11-15 | 2022-09-17 | 2022-11-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPQN | SAFE ROUTES TO SCHOOLS- QUEENS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-11-16 | 2022-12-15 | 2022-11-16 | 2022-12-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD10311 | 111th Street Malls (QED-1049) | 1 | DEVELOP SCOPE | 2015-06-01 | 2015-08-29 | 2016-06-01 | 2016-08-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD10311 | 111th Street Malls (QED-1049) | 2 | PRELIMINARY DESIGN | 2015-08-30 | 2015-12-27 | 2016-08-30 | 2016-12-27
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD10311 | 111th Street Malls (QED-1049) | 3 | FINAL DESIGN | 2015-12-28 | 2016-06-24 | 2016-12-28 | 2019-02-27
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD10311 | 111th Street Malls (QED-1049) | 4 | BID AWARD AND REGISTER CONTRCT | 2016-06-25 | 2016-09-22 | 2019-02-28 | 2019-03-01
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD10311 | 111th Street Malls (QED-1049) | 5 | CONSTRUCTION TO 25% | 2016-09-23 | 2017-01-20 | 2019-03-02 | 2019-06-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD10311 | 111th Street Malls (QED-1049) | 6 | CONSTRUCTION TO 50% | 2017-01-21 | 2017-05-20 | 2019-06-30 | 2019-10-27
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD10311 | 111th Street Malls (QED-1049) | 7 | CONSTRUCTION TO 75% | 2017-05-21 | 2017-09-17 | 2019-10-28 | 2020-02-24
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD10311 | 111th Street Malls (QED-1049) | 8 | ORIGINAL EQUIP & FURNISHING | 2017-09-18 | 2017-12-16 | 2020-02-25 | 2020-05-24
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD10311 | 111th Street Malls (QED-1049) | 9 | SUBSTANTIAL COMPLETION | 2017-12-17 | 2018-02-14 | 2020-05-25 | 2020-07-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD10311 | 111th Street Malls (QED-1049) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-02-15 | 2018-03-16 | 2020-07-24 | 2022-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWHARPER | Reconstruction of Harper Street Asphalt Plant - Construction | 1 | PROJECT START | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWHARPER | Reconstruction of Harper Street Asphalt Plant - Construction | 2 | DESIGN START | 2017-06-02 | 2017-06-02 | 2017-06-02 | 2019-04-02
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWHARPER | Reconstruction of Harper Street Asphalt Plant - Construction | 3 | DESIGN COMPLETION | 2017-06-03 | 2017-06-03 | 2019-04-03 | 2021-08-06
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWHARPER | Reconstruction of Harper Street Asphalt Plant - Construction | 4 | CONSTRUCTION START | 2017-06-04 | 2017-06-04 | 2021-08-07 | 2022-04-22
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWHARPER | Reconstruction of Harper Street Asphalt Plant - Construction | 5 | CONSTRUCTION COMPLETION | 2017-06-05 | 2020-07-30 | 2022-04-23 | 2025-08-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP14QTA | CITYWIDE COMPLEX PED RAMPS (TRANSIT AUTHORITY) - QUEENS | 1 | DEVELOP SCOPE | 2014-05-17 | 2014-08-14 | 2014-05-17 | 2014-08-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP14QTA | CITYWIDE COMPLEX PED RAMPS (TRANSIT AUTHORITY) - QUEENS | 2 | PRELIMINARY DESIGN | 2014-08-15 | 2014-12-12 | 2014-08-15 | 2014-12-12
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP14QTA | CITYWIDE COMPLEX PED RAMPS (TRANSIT AUTHORITY) - QUEENS | 3 | FINAL DESIGN | 2014-12-13 | 2015-06-10 | 2014-12-13 | 2015-06-10
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP14QTA | CITYWIDE COMPLEX PED RAMPS (TRANSIT AUTHORITY) - QUEENS | 4 | BID AWARD AND REGISTER CONTRCT | 2015-06-11 | 2015-09-08 | 2015-06-11 | 2015-09-08
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP14QTA | CITYWIDE COMPLEX PED RAMPS (TRANSIT AUTHORITY) - QUEENS | 5 | CONSTRUCTION TO 25% | 2015-09-09 | 2016-01-06 | 2015-09-09 | 2016-01-06
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP14QTA | CITYWIDE COMPLEX PED RAMPS (TRANSIT AUTHORITY) - QUEENS | 6 | CONSTRUCTION TO 50% | 2016-01-07 | 2016-05-05 | 2016-01-07 | 2016-05-05
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP14QTA | CITYWIDE COMPLEX PED RAMPS (TRANSIT AUTHORITY) - QUEENS | 7 | CONSTRUCTION TO 75% | 2016-05-06 | 2016-09-02 | 2016-05-06 | 2016-09-02
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP14QTA | CITYWIDE COMPLEX PED RAMPS (TRANSIT AUTHORITY) - QUEENS | 8 | ORIGINAL EQUIP & FURNISHING | 2016-09-03 | 2016-12-01 | 2016-09-03 | 2016-12-01
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP14QTA | CITYWIDE COMPLEX PED RAMPS (TRANSIT AUTHORITY) - QUEENS | 9 | SUBSTANTIAL COMPLETION | 2016-12-02 | 2017-01-30 | 2016-12-02 | 2019-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP14QTA | CITYWIDE COMPLEX PED RAMPS (TRANSIT AUTHORITY) - QUEENS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-01-31 | 2017-03-01 | 2019-07-01 | 2022-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2006Q | CITYWIDE PED RAMPS - QUEENS(SIM) | 1 | DEVELOP SCOPE | 2005-03-17 | 2005-06-14 | 2005-03-17 | 2005-06-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2006Q | CITYWIDE PED RAMPS - QUEENS(SIM) | 2 | PRELIMINARY DESIGN | 2005-06-15 | 2005-10-12 | 2005-06-15 | 2005-10-12
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2006Q | CITYWIDE PED RAMPS - QUEENS(SIM) | 3 | FINAL DESIGN | 2005-10-13 | 2006-04-10 | 2005-10-13 | 2006-04-10
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2006Q | CITYWIDE PED RAMPS - QUEENS(SIM) | 4 | BID AWARD AND REGISTER CONTRCT | 2006-04-11 | 2006-07-09 | 2006-04-11 | 2006-07-09
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2006Q | CITYWIDE PED RAMPS - QUEENS(SIM) | 5 | CONSTRUCTION TO 25% | 2006-07-10 | 2006-11-06 | 2006-07-10 | 2006-11-06
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2006Q | CITYWIDE PED RAMPS - QUEENS(SIM) | 6 | CONSTRUCTION TO 50% | 2006-11-07 | 2007-03-06 | 2006-11-07 | 2007-03-06
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2006Q | CITYWIDE PED RAMPS - QUEENS(SIM) | 7 | CONSTRUCTION TO 75% | 2007-03-07 | 2007-07-04 | 2007-03-07 | 2007-07-04
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2006Q | CITYWIDE PED RAMPS - QUEENS(SIM) | 8 | ORIGINAL EQUIP & FURNISHING | 2007-07-05 | 2007-10-02 | 2007-07-05 | 2007-10-02
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2006Q | CITYWIDE PED RAMPS - QUEENS(SIM) | 9 | SUBSTANTIAL COMPLETION | 2007-10-03 | 2007-12-01 | 2007-10-03 | 2007-12-01
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2006Q | CITYWIDE PED RAMPS - QUEENS(SIM) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2007-12-02 | 2007-12-31 | 2007-12-02 | 2021-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ010Q | Corona Plaza | 1 | DEVELOP SCOPE | 2013-06-30 | 2013-09-27 | 2013-06-30 | 2013-09-27
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ010Q | Corona Plaza | 2 | PRELIMINARY DESIGN | 2013-09-28 | 2014-01-25 | 2013-09-28 | 2014-01-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ010Q | Corona Plaza | 3 | FINAL DESIGN | 2014-01-26 | 2014-07-24 | 2014-01-26 | 2014-07-24
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ010Q | Corona Plaza | 4 | BID AWARD AND REGISTER CONTRCT | 2014-07-25 | 2014-10-22 | 2014-07-25 | 2014-10-22
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ010Q | Corona Plaza | 5 | CONSTRUCTION TO 25% | 2014-10-23 | 2015-02-19 | 2014-10-23 | 2015-02-19
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ010Q | Corona Plaza | 6 | CONSTRUCTION TO 50% | 2015-02-20 | 2015-06-19 | 2015-02-20 | 2015-06-19
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ010Q | Corona Plaza | 7 | CONSTRUCTION TO 75% | 2015-06-20 | 2015-10-17 | 2015-06-20 | 2015-10-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ010Q | Corona Plaza | 8 | ORIGINAL EQUIP & FURNISHING | 2015-10-18 | 2016-01-15 | 2015-10-18 | 2016-01-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ010Q | Corona Plaza | 9 | SUBSTANTIAL COMPLETION | 2016-01-16 | 2016-03-15 | 2016-01-16 | 2016-03-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ010Q | Corona Plaza | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-16 | 2016-04-14 | 2016-03-16 | 2022-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19Q1 | Pedestrian Ramp Rehabilitation - Queens | 1 | DEVELOP SCOPE | 2017-06-30 | 2017-09-27 | 2017-06-30 | 2017-09-27
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19Q1 | Pedestrian Ramp Rehabilitation - Queens | 2 | PRELIMINARY DESIGN | 2017-09-28 | 2018-01-25 | 2017-09-28 | 2018-01-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19Q1 | Pedestrian Ramp Rehabilitation - Queens | 3 | FINAL DESIGN | 2018-01-26 | 2018-07-24 | 2018-01-26 | 2018-07-24
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19Q1 | Pedestrian Ramp Rehabilitation - Queens | 4 | BID AWARD AND REGISTER CONTRCT | 2018-07-25 | 2018-10-22 | 2018-07-25 | 2018-10-22
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19Q1 | Pedestrian Ramp Rehabilitation - Queens | 5 | CONSTRUCTION TO 25% | 2018-10-23 | 2019-02-19 | 2018-10-23 | 2019-02-19
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19Q1 | Pedestrian Ramp Rehabilitation - Queens | 6 | CONSTRUCTION TO 50% | 2019-02-20 | 2019-06-19 | 2019-02-20 | 2019-06-19
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19Q1 | Pedestrian Ramp Rehabilitation - Queens | 7 | CONSTRUCTION TO 75% | 2019-06-20 | 2019-10-17 | 2019-06-20 | 2019-10-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19Q1 | Pedestrian Ramp Rehabilitation - Queens | 8 | ORIGINAL EQUIP & FURNISHING | 2019-10-18 | 2020-01-15 | 2019-10-18 | 2020-01-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19Q1 | Pedestrian Ramp Rehabilitation - Queens | 9 | SUBSTANTIAL COMPLETION | 2020-01-16 | 2020-03-15 | 2020-01-16 | 2020-03-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19Q1 | Pedestrian Ramp Rehabilitation - Queens | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-03-16 | 2020-04-14 | 2020-03-16 | 2023-09-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19Q2 | Pedestrian Ramp Rehabilitation - Queens | 1 | DEVELOP SCOPE | 2017-06-30 | 2017-09-27 | 2017-06-30 | 2017-09-27
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19Q2 | Pedestrian Ramp Rehabilitation - Queens | 2 | PRELIMINARY DESIGN | 2017-09-28 | 2018-01-25 | 2017-09-28 | 2018-01-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19Q2 | Pedestrian Ramp Rehabilitation - Queens | 3 | FINAL DESIGN | 2018-01-26 | 2018-07-24 | 2018-01-26 | 2018-07-24
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19Q2 | Pedestrian Ramp Rehabilitation - Queens | 4 | BID AWARD AND REGISTER CONTRCT | 2018-07-25 | 2018-10-22 | 2018-07-25 | 2018-10-22
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19Q2 | Pedestrian Ramp Rehabilitation - Queens | 5 | CONSTRUCTION TO 25% | 2018-10-23 | 2019-02-19 | 2018-10-23 | 2019-02-19
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19Q2 | Pedestrian Ramp Rehabilitation - Queens | 6 | CONSTRUCTION TO 50% | 2019-02-20 | 2019-06-19 | 2019-02-20 | 2019-06-19
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19Q2 | Pedestrian Ramp Rehabilitation - Queens | 7 | CONSTRUCTION TO 75% | 2019-06-20 | 2019-10-17 | 2019-06-20 | 2019-10-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19Q2 | Pedestrian Ramp Rehabilitation - Queens | 8 | ORIGINAL EQUIP & FURNISHING | 2019-10-18 | 2020-01-15 | 2019-10-18 | 2020-01-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19Q2 | Pedestrian Ramp Rehabilitation - Queens | 9 | SUBSTANTIAL COMPLETION | 2020-01-16 | 2020-03-15 | 2020-01-16 | 2020-03-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19Q2 | Pedestrian Ramp Rehabilitation - Queens | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-03-16 | 2020-04-14 | 2020-03-16 | 2023-09-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20Q1 | Pedestrian Ramp Rehabilitation - Queens | 1 | DEVELOP SCOPE | 2019-05-23 | 2019-08-20 | 2019-05-23 | 2019-08-20
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20Q1 | Pedestrian Ramp Rehabilitation - Queens | 2 | PRELIMINARY DESIGN | 2019-08-21 | 2019-12-18 | 2019-08-21 | 2019-12-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20Q1 | Pedestrian Ramp Rehabilitation - Queens | 3 | FINAL DESIGN | 2019-12-19 | 2020-06-15 | 2019-12-19 | 2020-06-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20Q1 | Pedestrian Ramp Rehabilitation - Queens | 4 | BID AWARD AND REGISTER CONTRCT | 2020-06-16 | 2020-09-13 | 2020-06-16 | 2020-09-13
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20Q1 | Pedestrian Ramp Rehabilitation - Queens | 5 | CONSTRUCTION TO 25% | 2020-09-14 | 2021-01-11 | 2020-09-14 | 2021-01-11
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20Q1 | Pedestrian Ramp Rehabilitation - Queens | 6 | CONSTRUCTION TO 50% | 2021-01-12 | 2021-05-11 | 2021-01-12 | 2021-05-11
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20Q1 | Pedestrian Ramp Rehabilitation - Queens | 7 | CONSTRUCTION TO 75% | 2021-05-12 | 2021-09-08 | 2021-05-12 | 2021-09-08
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20Q1 | Pedestrian Ramp Rehabilitation - Queens | 8 | ORIGINAL EQUIP & FURNISHING | 2021-09-09 | 2021-12-07 | 2021-09-09 | 2021-12-07
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20Q1 | Pedestrian Ramp Rehabilitation - Queens | 9 | SUBSTANTIAL COMPLETION | 2021-12-08 | 2022-02-05 | 2021-12-08 | 2022-02-05
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20Q1 | Pedestrian Ramp Rehabilitation - Queens | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-02-06 | 2025-09-26 | 2022-02-06 | 2025-09-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20Q2 | Pedestrian Ramp Rehabilitation - Queens | 1 | DEVELOP SCOPE | 2019-05-23 | 2019-08-20 | 2019-05-23 | 2019-08-20
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20Q2 | Pedestrian Ramp Rehabilitation - Queens | 2 | PRELIMINARY DESIGN | 2019-08-21 | 2019-12-18 | 2019-08-21 | 2019-12-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20Q2 | Pedestrian Ramp Rehabilitation - Queens | 3 | FINAL DESIGN | 2019-12-19 | 2020-06-15 | 2019-12-19 | 2020-06-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20Q2 | Pedestrian Ramp Rehabilitation - Queens | 4 | BID AWARD AND REGISTER CONTRCT | 2020-06-16 | 2020-09-13 | 2020-06-16 | 2020-09-13
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20Q2 | Pedestrian Ramp Rehabilitation - Queens | 5 | CONSTRUCTION TO 25% | 2020-09-14 | 2021-01-11 | 2020-09-14 | 2021-01-11
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20Q2 | Pedestrian Ramp Rehabilitation - Queens | 6 | CONSTRUCTION TO 50% | 2021-01-12 | 2021-05-11 | 2021-01-12 | 2021-05-11
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20Q2 | Pedestrian Ramp Rehabilitation - Queens | 7 | CONSTRUCTION TO 75% | 2021-05-12 | 2021-09-08 | 2021-05-12 | 2021-09-08
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20Q2 | Pedestrian Ramp Rehabilitation - Queens | 8 | ORIGINAL EQUIP & FURNISHING | 2021-09-09 | 2021-12-07 | 2021-09-09 | 2021-12-07
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20Q2 | Pedestrian Ramp Rehabilitation - Queens | 9 | SUBSTANTIAL COMPLETION | 2021-12-08 | 2022-02-05 | 2021-12-08 | 2022-02-05
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20Q2 | Pedestrian Ramp Rehabilitation - Queens | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-02-06 | 2025-09-26 | 2022-02-06 | 2025-09-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20Q3 | Pedestrian Ramp Rehabilitation - Queens | 1 | DEVELOP SCOPE | 2019-05-23 | 2019-08-20 | 2019-05-23 | 2019-08-20
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20Q3 | Pedestrian Ramp Rehabilitation - Queens | 2 | PRELIMINARY DESIGN | 2019-08-21 | 2019-12-18 | 2019-08-21 | 2019-12-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20Q3 | Pedestrian Ramp Rehabilitation - Queens | 3 | FINAL DESIGN | 2019-12-19 | 2020-06-15 | 2019-12-19 | 2020-06-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20Q3 | Pedestrian Ramp Rehabilitation - Queens | 4 | BID AWARD AND REGISTER CONTRCT | 2020-06-16 | 2020-09-13 | 2020-06-16 | 2020-09-13
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20Q3 | Pedestrian Ramp Rehabilitation - Queens | 5 | CONSTRUCTION TO 25% | 2020-09-14 | 2021-01-11 | 2020-09-14 | 2021-01-11
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20Q3 | Pedestrian Ramp Rehabilitation - Queens | 6 | CONSTRUCTION TO 50% | 2021-01-12 | 2021-05-11 | 2021-01-12 | 2021-05-11
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20Q3 | Pedestrian Ramp Rehabilitation - Queens | 7 | CONSTRUCTION TO 75% | 2021-05-12 | 2021-09-08 | 2021-05-12 | 2021-09-08
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20Q3 | Pedestrian Ramp Rehabilitation - Queens | 8 | ORIGINAL EQUIP & FURNISHING | 2021-09-09 | 2021-12-07 | 2021-09-09 | 2021-12-07
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20Q3 | Pedestrian Ramp Rehabilitation - Queens | 9 | SUBSTANTIAL COMPLETION | 2021-12-08 | 2022-02-05 | 2021-12-08 | 2022-02-05
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20Q3 | Pedestrian Ramp Rehabilitation - Queens | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-02-06 | 2025-09-12 | 2022-02-06 | 2025-09-12
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20QC | Non-Standard Upgrades Ped Ramp - Queens | 1 | DEVELOP SCOPE | 2019-06-30 | 2019-09-27 | 2019-06-30 | 2019-09-27
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20QC | Non-Standard Upgrades Ped Ramp - Queens | 2 | PRELIMINARY DESIGN | 2019-09-28 | 2020-01-25 | 2019-09-28 | 2020-01-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20QC | Non-Standard Upgrades Ped Ramp - Queens | 3 | FINAL DESIGN | 2020-01-26 | 2020-07-23 | 2020-01-26 | 2020-07-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20QC | Non-Standard Upgrades Ped Ramp - Queens | 4 | BID AWARD AND REGISTER CONTRCT | 2020-07-24 | 2020-10-21 | 2020-07-24 | 2020-10-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20QC | Non-Standard Upgrades Ped Ramp - Queens | 5 | CONSTRUCTION TO 25% | 2020-10-22 | 2021-02-18 | 2020-10-22 | 2021-02-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20QC | Non-Standard Upgrades Ped Ramp - Queens | 6 | CONSTRUCTION TO 50% | 2021-02-19 | 2021-06-18 | 2021-02-19 | 2021-06-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20QC | Non-Standard Upgrades Ped Ramp - Queens | 7 | CONSTRUCTION TO 75% | 2021-06-19 | 2021-10-16 | 2021-06-19 | 2021-10-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20QC | Non-Standard Upgrades Ped Ramp - Queens | 8 | ORIGINAL EQUIP & FURNISHING | 2021-10-17 | 2022-01-14 | 2021-10-17 | 2022-01-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20QC | Non-Standard Upgrades Ped Ramp - Queens | 9 | SUBSTANTIAL COMPLETION | 2022-01-15 | 2022-03-15 | 2022-01-15 | 2022-03-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20QC | Non-Standard Upgrades Ped Ramp - Queens | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-16 | 2022-04-14 | 2022-03-16 | 2023-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21Q1 | Rehabilitation of Standard Ped Ramps - Queens | 1 | DEVELOP SCOPE | 2021-06-30 | 2021-09-27 | 2021-06-30 | 2021-09-27
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21Q1 | Rehabilitation of Standard Ped Ramps - Queens | 2 | PRELIMINARY DESIGN | 2021-09-28 | 2022-01-25 | 2021-09-28 | 2022-01-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21Q1 | Rehabilitation of Standard Ped Ramps - Queens | 3 | FINAL DESIGN | 2022-01-26 | 2022-07-24 | 2022-01-26 | 2022-07-24
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21Q1 | Rehabilitation of Standard Ped Ramps - Queens | 4 | BID AWARD AND REGISTER CONTRCT | 2022-07-25 | 2022-10-22 | 2022-07-25 | 2022-10-22
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21Q1 | Rehabilitation of Standard Ped Ramps - Queens | 5 | CONSTRUCTION TO 25% | 2022-10-23 | 2023-02-19 | 2022-10-23 | 2023-02-19
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21Q1 | Rehabilitation of Standard Ped Ramps - Queens | 6 | CONSTRUCTION TO 50% | 2023-02-20 | 2023-06-19 | 2023-02-20 | 2023-06-19
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21Q1 | Rehabilitation of Standard Ped Ramps - Queens | 7 | CONSTRUCTION TO 75% | 2023-06-20 | 2023-10-17 | 2023-06-20 | 2023-10-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21Q1 | Rehabilitation of Standard Ped Ramps - Queens | 8 | ORIGINAL EQUIP & FURNISHING | 2023-10-18 | 2024-01-15 | 2023-10-18 | 2024-01-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21Q1 | Rehabilitation of Standard Ped Ramps - Queens | 9 | SUBSTANTIAL COMPLETION | 2024-01-16 | 2024-03-15 | 2024-01-16 | 2024-03-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21Q1 | Rehabilitation of Standard Ped Ramps - Queens | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-03-16 | 2024-04-14 | 2024-03-16 | 2024-04-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ100SBA | Woodhaven Blvd Segment A (QED-1040) | 1 | DEVELOP SCOPE | 2017-03-01 | 2017-05-29 | 2017-03-01 | 2017-05-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ100SBA | Woodhaven Blvd Segment A (QED-1040) | 2 | PRELIMINARY DESIGN | 2017-05-30 | 2017-09-26 | 2017-05-30 | 2017-09-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ100SBA | Woodhaven Blvd Segment A (QED-1040) | 3 | FINAL DESIGN | 2017-09-27 | 2018-03-25 | 2017-09-27 | 2018-03-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ100SBA | Woodhaven Blvd Segment A (QED-1040) | 4 | BID AWARD AND REGISTER CONTRCT | 2018-03-26 | 2018-06-23 | 2018-03-26 | 2018-06-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ100SBA | Woodhaven Blvd Segment A (QED-1040) | 5 | CONSTRUCTION TO 25% | 2018-06-24 | 2018-10-21 | 2018-06-24 | 2018-10-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ100SBA | Woodhaven Blvd Segment A (QED-1040) | 6 | CONSTRUCTION TO 50% | 2018-10-22 | 2019-02-18 | 2018-10-22 | 2019-02-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ100SBA | Woodhaven Blvd Segment A (QED-1040) | 7 | CONSTRUCTION TO 75% | 2019-02-19 | 2019-06-18 | 2019-02-19 | 2019-06-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ100SBA | Woodhaven Blvd Segment A (QED-1040) | 8 | ORIGINAL EQUIP & FURNISHING | 2019-06-19 | 2019-09-16 | 2019-06-19 | 2019-09-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ100SBA | Woodhaven Blvd Segment A (QED-1040) | 9 | SUBSTANTIAL COMPLETION | 2019-09-17 | 2019-11-15 | 2019-09-17 | 2019-11-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ100SBA | Woodhaven Blvd Segment A (QED-1040) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-11-16 | 2019-12-15 | 2019-11-16 | 2027-09-13
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ100SBB | Woodhaven Blvd SBS Phase B | 1 | DEVELOP SCOPE | 2019-06-30 | 2019-09-27 | 2019-06-30 | 2019-09-27
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ100SBB | Woodhaven Blvd SBS Phase B | 2 | PRELIMINARY DESIGN | 2019-09-28 | 2020-01-25 | 2019-09-28 | 2020-01-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ100SBB | Woodhaven Blvd SBS Phase B | 3 | FINAL DESIGN | 2020-01-26 | 2020-07-23 | 2020-01-26 | 2020-07-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ100SBB | Woodhaven Blvd SBS Phase B | 4 | BID AWARD AND REGISTER CONTRCT | 2020-07-24 | 2020-10-21 | 2020-07-24 | 2020-10-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ100SBB | Woodhaven Blvd SBS Phase B | 5 | CONSTRUCTION TO 25% | 2020-10-22 | 2021-02-18 | 2020-10-22 | 2021-02-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ100SBB | Woodhaven Blvd SBS Phase B | 6 | CONSTRUCTION TO 50% | 2021-02-19 | 2021-06-18 | 2021-02-19 | 2021-06-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ100SBB | Woodhaven Blvd SBS Phase B | 7 | CONSTRUCTION TO 75% | 2021-06-19 | 2021-10-16 | 2021-06-19 | 2021-10-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ100SBB | Woodhaven Blvd SBS Phase B | 8 | ORIGINAL EQUIP & FURNISHING | 2021-10-17 | 2022-01-14 | 2021-10-17 | 2022-01-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ100SBB | Woodhaven Blvd SBS Phase B | 9 | SUBSTANTIAL COMPLETION | 2022-01-15 | 2022-03-15 | 2022-01-15 | 2022-03-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ100SBB | Woodhaven Blvd SBS Phase B | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-16 | 2022-04-14 | 2022-03-16 | 2029-09-12
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1161 | REHAB OF 99TH AND 100TH AVENUES | 1 | DEVELOP SCOPE | 2003-05-22 | 2003-08-19 | 2003-05-22 | 2003-08-19
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1161 | REHAB OF 99TH AND 100TH AVENUES | 2 | PRELIMINARY DESIGN | 2003-08-20 | 2003-12-17 | 2003-08-20 | 2003-12-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1161 | REHAB OF 99TH AND 100TH AVENUES | 3 | FINAL DESIGN | 2003-12-18 | 2004-06-14 | 2003-12-18 | 2004-06-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1161 | REHAB OF 99TH AND 100TH AVENUES | 4 | BID AWARD AND REGISTER CONTRCT | 2004-06-15 | 2004-09-12 | 2004-06-15 | 2008-04-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1161 | REHAB OF 99TH AND 100TH AVENUES | 5 | CONSTRUCTION TO 25% | 2004-09-13 | 2005-01-10 | 2008-04-15 | 2008-04-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1161 | REHAB OF 99TH AND 100TH AVENUES | 6 | CONSTRUCTION TO 50% | 2005-01-11 | 2005-05-10 | 2008-04-15 | 2008-04-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1161 | REHAB OF 99TH AND 100TH AVENUES | 7 | CONSTRUCTION TO 75% | 2005-05-11 | 2005-09-07 | 2008-04-15 | 2008-04-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1161 | REHAB OF 99TH AND 100TH AVENUES | 8 | ORIGINAL EQUIP & FURNISHING | 2005-09-08 | 2005-12-06 | 2008-04-15 | 2008-04-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1161 | REHAB OF 99TH AND 100TH AVENUES | 9 | SUBSTANTIAL COMPLETION | 2005-12-07 | 2006-02-04 | 2008-04-15 | 2008-04-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1161 | REHAB OF 99TH AND 100TH AVENUES | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2006-02-05 | 2006-03-06 | 2008-04-15 | 2022-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1182A | Broad Channel Bulkheads - Phase I (SEQ200582) | 1 | DEVELOP SCOPE | 2012-06-30 | 2012-09-27 | 2012-06-30 | 2012-09-27
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1182A | Broad Channel Bulkheads - Phase I (SEQ200582) | 2 | PRELIMINARY DESIGN | 2012-09-28 | 2013-01-25 | 2012-09-28 | 2013-01-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1182A | Broad Channel Bulkheads - Phase I (SEQ200582) | 3 | FINAL DESIGN | 2013-01-26 | 2013-07-24 | 2013-01-26 | 2013-07-24
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1182A | Broad Channel Bulkheads - Phase I (SEQ200582) | 4 | BID AWARD AND REGISTER CONTRCT | 2013-07-25 | 2013-10-22 | 2013-07-25 | 2013-10-22
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1182A | Broad Channel Bulkheads - Phase I (SEQ200582) | 5 | CONSTRUCTION TO 25% | 2013-10-23 | 2014-02-19 | 2013-10-23 | 2014-02-19
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1182A | Broad Channel Bulkheads - Phase I (SEQ200582) | 6 | CONSTRUCTION TO 50% | 2014-02-20 | 2014-06-19 | 2014-02-20 | 2014-06-19
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1182A | Broad Channel Bulkheads - Phase I (SEQ200582) | 7 | CONSTRUCTION TO 75% | 2014-06-20 | 2014-10-17 | 2014-06-20 | 2014-10-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1182A | Broad Channel Bulkheads - Phase I (SEQ200582) | 8 | ORIGINAL EQUIP & FURNISHING | 2014-10-18 | 2015-01-15 | 2014-10-18 | 2015-01-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1182A | Broad Channel Bulkheads - Phase I (SEQ200582) | 9 | SUBSTANTIAL COMPLETION | 2015-01-16 | 2015-03-16 | 2015-01-16 | 2015-03-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1182A | Broad Channel Bulkheads - Phase I (SEQ200582) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-17 | 2015-04-15 | 2015-03-17 | 2026-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1182B | Broad Channel Bulkheads - Phase II (SEQ200586) | 1 | DEVELOP SCOPE | 2015-06-30 | 2015-10-27 | 2015-06-30 | 2015-10-27
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1182B | Broad Channel Bulkheads - Phase II (SEQ200586) | 2 | DESIGN START | 2015-10-28 | 2017-04-19 | 2015-10-28 | 2017-04-19
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1182B | Broad Channel Bulkheads - Phase II (SEQ200586) | 3 | CONSTRUCTION START | 2017-04-20 | 2019-04-09 | 2017-04-20 | 2027-07-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1184A | James Court Roadway & Bulkhead, Queens (Joint Bid) | 1 | DEVELOP SCOPE | 2011-02-28 | 2013-05-28 | 2011-02-28 | 2013-05-28
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1184A | James Court Roadway & Bulkhead, Queens (Joint Bid) | 2 | PRELIMINARY DESIGN | 2013-05-29 | 2013-05-28 | 2013-05-29 | 2013-05-28
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1184A | James Court Roadway & Bulkhead, Queens (Joint Bid) | 3 | FINAL DESIGN | 2013-05-29 | 2013-05-28 | 2013-05-29 | 2013-05-28
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1184A | James Court Roadway & Bulkhead, Queens (Joint Bid) | 4 | BID AWARD AND REGISTER CONTRCT | 2013-03-28 | 2013-06-25 | 2013-03-28 | 2013-06-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1184A | James Court Roadway & Bulkhead, Queens (Joint Bid) | 5 | CONSTRUCTION TO 25% | 2013-06-26 | 2013-06-25 | 2013-06-26 | 2013-06-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1184A | James Court Roadway & Bulkhead, Queens (Joint Bid) | 6 | CONSTRUCTION TO 50% | 2013-06-26 | 2013-06-25 | 2013-06-26 | 2013-06-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1184A | James Court Roadway & Bulkhead, Queens (Joint Bid) | 7 | CONSTRUCTION TO 75% | 2013-06-26 | 2013-06-25 | 2013-06-26 | 2013-06-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1184A | James Court Roadway & Bulkhead, Queens (Joint Bid) | 8 | ORIGINAL EQUIP & FURNISHING | 2013-06-26 | 2013-06-25 | 2013-06-26 | 2013-06-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1184A | James Court Roadway & Bulkhead, Queens (Joint Bid) | 9 | SUBSTANTIAL COMPLETION | 2013-06-26 | 2013-06-25 | 2013-06-26 | 2013-06-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1184A | James Court Roadway & Bulkhead, Queens (Joint Bid) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-06-26 | 2015-07-25 | 2013-06-26 | 2024-04-20
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1187 | Westbourne-Dunbar Roadways & Bulkheads (SAND1187, SEQ200595) | 1 | DEVELOP SCOPE | 2017-06-30 | 2017-09-27 | 2016-06-30 | 2016-09-27
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1187 | Westbourne-Dunbar Roadways & Bulkheads (SAND1187, SEQ200595) | 2 | PRELIMINARY DESIGN | 2017-09-28 | 2018-01-25 | 2016-09-28 | 2017-01-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1187 | Westbourne-Dunbar Roadways & Bulkheads (SAND1187, SEQ200595) | 3 | FINAL DESIGN | 2018-01-26 | 2018-07-24 | 2017-01-26 | 2017-07-24
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1187 | Westbourne-Dunbar Roadways & Bulkheads (SAND1187, SEQ200595) | 4 | BID AWARD AND REGISTER CONTRCT | 2018-07-25 | 2018-10-22 | 2017-07-25 | 2017-10-22
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1187 | Westbourne-Dunbar Roadways & Bulkheads (SAND1187, SEQ200595) | 5 | CONSTRUCTION TO 25% | 2018-10-23 | 2019-02-19 | 2017-10-23 | 2018-02-19
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1187 | Westbourne-Dunbar Roadways & Bulkheads (SAND1187, SEQ200595) | 6 | CONSTRUCTION TO 50% | 2019-02-20 | 2019-06-19 | 2018-02-20 | 2018-06-19
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1187 | Westbourne-Dunbar Roadways & Bulkheads (SAND1187, SEQ200595) | 7 | CONSTRUCTION TO 75% | 2019-06-20 | 2019-10-17 | 2018-06-20 | 2018-10-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1187 | Westbourne-Dunbar Roadways & Bulkheads (SAND1187, SEQ200595) | 8 | ORIGINAL EQUIP & FURNISHING | 2019-10-18 | 2020-01-15 | 2018-10-18 | 2019-01-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1187 | Westbourne-Dunbar Roadways & Bulkheads (SAND1187, SEQ200595) | 9 | SUBSTANTIAL COMPLETION | 2020-01-16 | 2020-03-15 | 2019-01-16 | 2019-03-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1187 | Westbourne-Dunbar Roadways & Bulkheads (SAND1187, SEQ200595) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-03-16 | 2020-04-14 | 2019-03-17 | 2029-09-11
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1190A | Reconstruction of Queens Blvd Phase 1 (QED-1042A) | 1 | DEVELOP SCOPE | 2017-03-01 | 2017-05-29 | 2017-03-01 | 2017-05-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1190A | Reconstruction of Queens Blvd Phase 1 (QED-1042A) | 2 | PRELIMINARY DESIGN | 2017-05-30 | 2017-09-26 | 2017-05-30 | 2017-09-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1190A | Reconstruction of Queens Blvd Phase 1 (QED-1042A) | 3 | FINAL DESIGN | 2017-09-27 | 2018-03-25 | 2017-09-27 | 2018-03-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1190A | Reconstruction of Queens Blvd Phase 1 (QED-1042A) | 4 | BID AWARD AND REGISTER CONTRCT | 2018-03-26 | 2018-06-23 | 2018-03-26 | 2018-06-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1190A | Reconstruction of Queens Blvd Phase 1 (QED-1042A) | 5 | CONSTRUCTION TO 25% | 2018-06-24 | 2018-10-21 | 2018-06-24 | 2018-10-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1190A | Reconstruction of Queens Blvd Phase 1 (QED-1042A) | 6 | CONSTRUCTION TO 50% | 2018-10-22 | 2019-02-18 | 2018-10-22 | 2019-02-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1190A | Reconstruction of Queens Blvd Phase 1 (QED-1042A) | 7 | CONSTRUCTION TO 75% | 2019-02-19 | 2019-06-18 | 2019-02-19 | 2019-06-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1190A | Reconstruction of Queens Blvd Phase 1 (QED-1042A) | 8 | ORIGINAL EQUIP & FURNISHING | 2019-06-19 | 2019-09-16 | 2019-06-19 | 2019-09-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1190A | Reconstruction of Queens Blvd Phase 1 (QED-1042A) | 9 | SUBSTANTIAL COMPLETION | 2019-09-17 | 2019-11-15 | 2019-09-17 | 2019-11-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1190A | Reconstruction of Queens Blvd Phase 1 (QED-1042A) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-11-16 | 2019-12-15 | 2019-11-16 | 2029-03-12
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1190B | Reconstruction of Queens Blvd Phase 2 | 1 | DEVELOP SCOPE | 2016-03-01 | 2016-05-29 | 2016-03-01 | 2016-05-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1190B | Reconstruction of Queens Blvd Phase 2 | 2 | PRELIMINARY DESIGN | 2016-05-30 | 2016-09-26 | 2016-05-30 | 2016-09-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1190B | Reconstruction of Queens Blvd Phase 2 | 3 | FINAL DESIGN | 2016-09-27 | 2017-03-25 | 2016-09-27 | 2017-03-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1190B | Reconstruction of Queens Blvd Phase 2 | 4 | BID AWARD AND REGISTER CONTRCT | 2017-03-26 | 2017-06-23 | 2017-03-26 | 2017-06-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1190B | Reconstruction of Queens Blvd Phase 2 | 5 | CONSTRUCTION TO 25% | 2017-06-24 | 2017-10-21 | 2017-06-24 | 2017-10-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1190B | Reconstruction of Queens Blvd Phase 2 | 6 | CONSTRUCTION TO 50% | 2017-10-22 | 2018-02-18 | 2017-10-22 | 2018-02-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1190B | Reconstruction of Queens Blvd Phase 2 | 7 | CONSTRUCTION TO 75% | 2018-02-19 | 2018-06-18 | 2018-02-19 | 2018-06-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1190B | Reconstruction of Queens Blvd Phase 2 | 8 | ORIGINAL EQUIP & FURNISHING | 2018-06-19 | 2018-09-16 | 2018-06-19 | 2018-09-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1190B | Reconstruction of Queens Blvd Phase 2 | 9 | SUBSTANTIAL COMPLETION | 2018-09-17 | 2018-11-15 | 2018-09-17 | 2018-11-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1190B | Reconstruction of Queens Blvd Phase 2 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-11-16 | 2018-12-15 | 2018-11-16 | 2026-04-11
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1190-C | Reconstruction of Queens Blvd Phase 3 | 1 | DEVELOP SCOPE | 2017-03-01 | 2017-05-29 | 2017-03-01 | 2017-05-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1190-C | Reconstruction of Queens Blvd Phase 3 | 2 | PRELIMINARY DESIGN | 2017-05-30 | 2017-09-26 | 2017-05-30 | 2017-09-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1190-C | Reconstruction of Queens Blvd Phase 3 | 3 | FINAL DESIGN | 2017-09-27 | 2018-03-25 | 2017-09-27 | 2020-11-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1190-C | Reconstruction of Queens Blvd Phase 3 | 4 | BID AWARD AND REGISTER CONTRCT | 2018-03-26 | 2018-06-23 | 2020-12-01 | 2021-02-28
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1190-C | Reconstruction of Queens Blvd Phase 3 | 5 | CONSTRUCTION TO 25% | 2018-06-24 | 2018-10-21 | 2021-03-01 | 2021-06-28
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1190-C | Reconstruction of Queens Blvd Phase 3 | 6 | CONSTRUCTION TO 50% | 2018-10-22 | 2019-02-18 | 2021-06-29 | 2021-10-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1190-C | Reconstruction of Queens Blvd Phase 3 | 7 | CONSTRUCTION TO 75% | 2019-02-19 | 2019-06-18 | 2021-10-27 | 2022-02-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1190-C | Reconstruction of Queens Blvd Phase 3 | 8 | ORIGINAL EQUIP & FURNISHING | 2019-06-19 | 2019-09-16 | 2022-02-24 | 2022-05-24
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1190-C | Reconstruction of Queens Blvd Phase 3 | 9 | SUBSTANTIAL COMPLETION | 2019-09-17 | 2019-11-15 | 2022-05-25 | 2022-07-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1190-C | Reconstruction of Queens Blvd Phase 3 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-11-16 | 2019-12-15 | 2022-07-24 | 2026-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1193 | Union Turnpike Curb Repair | 1 | DEVELOP SCOPE | 2016-06-30 | 2016-09-27 | 2016-06-30 | 2016-09-27
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1193 | Union Turnpike Curb Repair | 2 | PRELIMINARY DESIGN | 2016-09-28 | 2017-01-25 | 2016-09-28 | 2017-01-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1193 | Union Turnpike Curb Repair | 3 | FINAL DESIGN | 2017-01-26 | 2017-07-24 | 2017-01-26 | 2017-07-24
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1193 | Union Turnpike Curb Repair | 4 | BID AWARD AND REGISTER CONTRCT | 2017-07-25 | 2017-10-22 | 2017-07-25 | 2017-10-22
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1193 | Union Turnpike Curb Repair | 5 | CONSTRUCTION TO 25% | 2017-10-23 | 2018-02-19 | 2017-10-23 | 2018-02-19
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1193 | Union Turnpike Curb Repair | 6 | CONSTRUCTION TO 50% | 2018-02-20 | 2018-06-19 | 2018-02-20 | 2018-06-19
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1193 | Union Turnpike Curb Repair | 7 | CONSTRUCTION TO 75% | 2018-06-20 | 2018-10-17 | 2018-06-20 | 2018-10-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1193 | Union Turnpike Curb Repair | 8 | ORIGINAL EQUIP & FURNISHING | 2018-10-18 | 2019-01-15 | 2018-10-18 | 2019-01-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1193 | Union Turnpike Curb Repair | 9 | SUBSTANTIAL COMPLETION | 2019-01-16 | 2019-03-16 | 2019-01-16 | 2019-03-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1193 | Union Turnpike Curb Repair | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-03-17 | 2019-04-15 | 2019-03-17 | 2026-09-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1195 | Colfax and Murdock Street Raising (SEQNS003) | 1 | DEVELOP SCOPE | 2016-06-30 | 2016-09-27 | 2018-06-30 | 2018-09-27
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1195 | Colfax and Murdock Street Raising (SEQNS003) | 2 | PRELIMINARY DESIGN | 2016-09-28 | 2017-01-25 | 2018-09-28 | 2019-01-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1195 | Colfax and Murdock Street Raising (SEQNS003) | 3 | FINAL DESIGN | 2017-01-26 | 2017-07-24 | 2019-01-26 | 2019-07-24
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1195 | Colfax and Murdock Street Raising (SEQNS003) | 4 | BID AWARD AND REGISTER CONTRCT | 2017-07-25 | 2017-10-22 | 2019-07-25 | 2020-06-01
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1195 | Colfax and Murdock Street Raising (SEQNS003) | 5 | CONSTRUCTION TO 25% | 2017-10-23 | 2018-02-19 | 2020-06-02 | 2020-09-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1195 | Colfax and Murdock Street Raising (SEQNS003) | 6 | CONSTRUCTION TO 50% | 2018-02-20 | 2018-06-19 | 2020-09-30 | 2021-01-27
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1195 | Colfax and Murdock Street Raising (SEQNS003) | 7 | CONSTRUCTION TO 75% | 2018-06-20 | 2018-10-17 | 2021-01-28 | 2021-05-27
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1195 | Colfax and Murdock Street Raising (SEQNS003) | 8 | ORIGINAL EQUIP & FURNISHING | 2018-10-18 | 2019-01-15 | 2021-05-28 | 2021-08-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1195 | Colfax and Murdock Street Raising (SEQNS003) | 9 | SUBSTANTIAL COMPLETION | 2019-01-16 | 2019-03-16 | 2021-08-26 | 2021-10-24
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1195 | Colfax and Murdock Street Raising (SEQNS003) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-03-17 | 2019-04-15 | 2021-10-25 | 2026-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ121B3 | RECONSTRUCTION OF SOUTH JAMAICA AREA (SEQ200562) | 1 | DEVELOP SCOPE | 2005-05-21 | 2005-08-18 | 2005-05-21 | 2005-08-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ121B3 | RECONSTRUCTION OF SOUTH JAMAICA AREA (SEQ200562) | 2 | PRELIMINARY DESIGN | 2005-08-19 | 2005-12-16 | 2005-08-19 | 2005-12-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ121B3 | RECONSTRUCTION OF SOUTH JAMAICA AREA (SEQ200562) | 3 | FINAL DESIGN | 2005-12-17 | 2006-06-14 | 2005-12-17 | 2006-06-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ121B3 | RECONSTRUCTION OF SOUTH JAMAICA AREA (SEQ200562) | 4 | BID AWARD AND REGISTER CONTRCT | 2006-06-15 | 2006-09-12 | 2006-06-15 | 2022-06-02
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ121B3 | RECONSTRUCTION OF SOUTH JAMAICA AREA (SEQ200562) | 5 | CONSTRUCTION TO 25% | 2006-09-13 | 2007-01-10 | 2022-06-03 | 2022-06-02
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ121B3 | RECONSTRUCTION OF SOUTH JAMAICA AREA (SEQ200562) | 6 | CONSTRUCTION TO 50% | 2007-01-11 | 2007-05-10 | 2022-06-03 | 2022-06-02
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ121B3 | RECONSTRUCTION OF SOUTH JAMAICA AREA (SEQ200562) | 7 | CONSTRUCTION TO 75% | 2007-05-11 | 2007-09-07 | 2022-06-03 | 2022-06-02
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ121B3 | RECONSTRUCTION OF SOUTH JAMAICA AREA (SEQ200562) | 8 | ORIGINAL EQUIP & FURNISHING | 2007-09-08 | 2007-12-06 | 2022-06-03 | 2022-06-02
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ121B3 | RECONSTRUCTION OF SOUTH JAMAICA AREA (SEQ200562) | 9 | SUBSTANTIAL COMPLETION | 2007-12-07 | 2008-02-04 | 2022-06-03 | 2022-06-02
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ121B3 | RECONSTRUCTION OF SOUTH JAMAICA AREA (SEQ200562) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-02-05 | 2008-03-05 | 2022-06-03 | 2023-12-05
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ200578 | SEQ - Foch Boulevard Safety Improvements (SEQ200578) | 1 | DEVELOP SCOPE | 2017-03-01 | 2017-05-29 | 2017-03-01 | 2017-05-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ200578 | SEQ - Foch Boulevard Safety Improvements (SEQ200578) | 2 | PRELIMINARY DESIGN | 2017-05-30 | 2017-09-26 | 2017-05-30 | 2017-09-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ200578 | SEQ - Foch Boulevard Safety Improvements (SEQ200578) | 3 | FINAL DESIGN | 2017-09-27 | 2018-10-30 | 2017-09-27 | 2018-10-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ200578 | SEQ - Foch Boulevard Safety Improvements (SEQ200578) | 4 | BID AWARD AND REGISTER CONTRCT | 2018-10-31 | 2019-01-28 | 2018-10-31 | 2019-01-28
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ200578 | SEQ - Foch Boulevard Safety Improvements (SEQ200578) | 5 | CONSTRUCTION TO 25% | 2019-01-29 | 2019-05-28 | 2019-01-29 | 2019-05-28
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ200578 | SEQ - Foch Boulevard Safety Improvements (SEQ200578) | 6 | CONSTRUCTION TO 50% | 2019-05-29 | 2019-09-25 | 2019-05-29 | 2019-09-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ200578 | SEQ - Foch Boulevard Safety Improvements (SEQ200578) | 7 | CONSTRUCTION TO 75% | 2019-09-26 | 2020-01-23 | 2019-09-26 | 2020-01-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ200578 | SEQ - Foch Boulevard Safety Improvements (SEQ200578) | 8 | ORIGINAL EQUIP & FURNISHING | 2020-01-24 | 2020-04-22 | 2020-01-24 | 2020-04-22
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ200578 | SEQ - Foch Boulevard Safety Improvements (SEQ200578) | 9 | SUBSTANTIAL COMPLETION | 2020-04-23 | 2020-06-21 | 2020-04-23 | 2020-06-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ200578 | SEQ - Foch Boulevard Safety Improvements (SEQ200578) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-06-22 | 2020-07-21 | 2020-06-22 | 2026-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ213C | Main Street Sidewalk Widening | 1 | DEVELOP SCOPE | 2013-03-01 | 2013-05-29 | 2013-03-01 | 2013-05-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ213C | Main Street Sidewalk Widening | 2 | PRELIMINARY DESIGN | 2013-05-30 | 2013-09-26 | 2013-05-30 | 2013-09-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ213C | Main Street Sidewalk Widening | 3 | FINAL DESIGN | 2013-09-27 | 2014-03-25 | 2013-09-27 | 2015-03-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ213C | Main Street Sidewalk Widening | 4 | BID AWARD AND REGISTER CONTRCT | 2014-03-26 | 2014-06-23 | 2015-03-26 | 2015-06-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ213C | Main Street Sidewalk Widening | 5 | CONSTRUCTION TO 25% | 2014-06-24 | 2014-10-21 | 2015-06-24 | 2015-10-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ213C | Main Street Sidewalk Widening | 6 | CONSTRUCTION TO 50% | 2014-10-22 | 2015-02-18 | 2015-10-22 | 2016-02-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ213C | Main Street Sidewalk Widening | 7 | CONSTRUCTION TO 75% | 2015-02-19 | 2015-06-18 | 2016-02-19 | 2016-06-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ213C | Main Street Sidewalk Widening | 8 | ORIGINAL EQUIP & FURNISHING | 2015-06-19 | 2015-09-16 | 2016-06-18 | 2016-06-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ213C | Main Street Sidewalk Widening | 9 | SUBSTANTIAL COMPLETION | 2015-09-17 | 2015-11-15 | 2016-06-18 | 2016-09-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ213C | Main Street Sidewalk Widening | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-11-16 | 2015-12-15 | 2016-09-16 | 2024-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ274F1 | RECONSTRUCTION OF STREETS IN ROSEDALE AREA (SEQ200446) | 1 | DEVELOP SCOPE | 2004-07-01 | 2004-09-28 | 2004-07-01 | 2004-09-28
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ274F1 | RECONSTRUCTION OF STREETS IN ROSEDALE AREA (SEQ200446) | 2 | PRELIMINARY DESIGN | 2004-09-29 | 2005-01-26 | 2004-09-29 | 2005-01-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ274F1 | RECONSTRUCTION OF STREETS IN ROSEDALE AREA (SEQ200446) | 3 | FINAL DESIGN | 2005-01-27 | 2005-07-25 | 2005-01-27 | 2005-07-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ274F1 | RECONSTRUCTION OF STREETS IN ROSEDALE AREA (SEQ200446) | 4 | BID AWARD AND REGISTER CONTRCT | 2005-07-26 | 2005-10-23 | 2005-07-26 | 2022-06-05
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ274F1 | RECONSTRUCTION OF STREETS IN ROSEDALE AREA (SEQ200446) | 5 | CONSTRUCTION TO 25% | 2005-10-24 | 2006-02-20 | 2022-06-06 | 2022-06-05
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ274F1 | RECONSTRUCTION OF STREETS IN ROSEDALE AREA (SEQ200446) | 6 | CONSTRUCTION TO 50% | 2006-02-21 | 2006-06-20 | 2022-06-06 | 2022-06-05
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ274F1 | RECONSTRUCTION OF STREETS IN ROSEDALE AREA (SEQ200446) | 7 | CONSTRUCTION TO 75% | 2006-06-21 | 2006-10-18 | 2022-06-06 | 2022-06-05
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ274F1 | RECONSTRUCTION OF STREETS IN ROSEDALE AREA (SEQ200446) | 8 | ORIGINAL EQUIP & FURNISHING | 2006-10-19 | 2007-01-16 | 2022-06-06 | 2022-06-05
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ274F1 | RECONSTRUCTION OF STREETS IN ROSEDALE AREA (SEQ200446) | 9 | SUBSTANTIAL COMPLETION | 2007-01-17 | 2007-03-17 | 2022-06-06 | 2022-06-05
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ274F1 | RECONSTRUCTION OF STREETS IN ROSEDALE AREA (SEQ200446) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2007-03-18 | 2007-04-16 | 2022-06-06 | 2023-12-13
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ274F2 | RECON OF STREETS IN ROSEDALE AREA - PHASE 2 | 1 | DEVELOP SCOPE | 2020-06-30 | 2020-09-27 | 2020-06-30 | 2020-09-27
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ274F2 | RECON OF STREETS IN ROSEDALE AREA - PHASE 2 | 2 | PRELIMINARY DESIGN | 2020-09-28 | 2021-01-25 | 2020-09-28 | 2021-01-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ274F2 | RECON OF STREETS IN ROSEDALE AREA - PHASE 2 | 3 | FINAL DESIGN | 2021-01-26 | 2021-07-24 | 2021-01-26 | 2021-07-24
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ274F2 | RECON OF STREETS IN ROSEDALE AREA - PHASE 2 | 4 | BID AWARD AND REGISTER CONTRCT | 2021-07-25 | 2021-10-22 | 2021-07-25 | 2021-10-22
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ274F2 | RECON OF STREETS IN ROSEDALE AREA - PHASE 2 | 5 | CONSTRUCTION TO 25% | 2021-10-23 | 2022-02-19 | 2021-10-23 | 2022-02-19
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ274F2 | RECON OF STREETS IN ROSEDALE AREA - PHASE 2 | 6 | CONSTRUCTION TO 50% | 2022-02-20 | 2022-06-19 | 2022-02-20 | 2022-06-19
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ274F2 | RECON OF STREETS IN ROSEDALE AREA - PHASE 2 | 7 | CONSTRUCTION TO 75% | 2022-06-20 | 2022-10-17 | 2022-06-20 | 2022-10-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ274F2 | RECON OF STREETS IN ROSEDALE AREA - PHASE 2 | 8 | ORIGINAL EQUIP & FURNISHING | 2022-10-18 | 2023-01-15 | 2022-10-18 | 2023-01-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ274F2 | RECON OF STREETS IN ROSEDALE AREA - PHASE 2 | 9 | SUBSTANTIAL COMPLETION | 2023-01-16 | 2023-03-16 | 2023-01-16 | 2023-03-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ274F2 | RECON OF STREETS IN ROSEDALE AREA - PHASE 2 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-03-17 | 2023-04-15 | 2023-03-17 | 2023-04-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ411B | Reconstruction of Albert Road Area, 94th St, Qns (SEQ002568) | 1 | DEVELOP SCOPE | 2008-03-05 | 2008-06-02 | 2008-03-05 | 2008-06-02
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ411B | Reconstruction of Albert Road Area, 94th St, Qns (SEQ002568) | 2 | PRELIMINARY DESIGN | 2008-06-03 | 2008-09-30 | 2008-06-03 | 2008-09-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ411B | Reconstruction of Albert Road Area, 94th St, Qns (SEQ002568) | 3 | FINAL DESIGN | 2008-10-01 | 2009-03-29 | 2008-10-01 | 2014-03-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ411B | Reconstruction of Albert Road Area, 94th St, Qns (SEQ002568) | 4 | BID AWARD AND REGISTER CONTRCT | 2009-03-30 | 2009-06-27 | 2014-03-18 | 2014-06-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ411B | Reconstruction of Albert Road Area, 94th St, Qns (SEQ002568) | 5 | CONSTRUCTION TO 25% | 2009-06-28 | 2009-10-25 | 2014-06-16 | 2015-04-11
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ411B | Reconstruction of Albert Road Area, 94th St, Qns (SEQ002568) | 6 | CONSTRUCTION TO 50% | 2009-10-26 | 2010-02-22 | 2015-04-12 | 2016-04-10
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ411B | Reconstruction of Albert Road Area, 94th St, Qns (SEQ002568) | 7 | CONSTRUCTION TO 75% | 2010-02-23 | 2010-06-22 | 2016-04-11 | 2016-12-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ411B | Reconstruction of Albert Road Area, 94th St, Qns (SEQ002568) | 8 | ORIGINAL EQUIP & FURNISHING | 2010-06-23 | 2010-09-20 | 2016-12-26 | 2017-03-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ411B | Reconstruction of Albert Road Area, 94th St, Qns (SEQ002568) | 9 | SUBSTANTIAL COMPLETION | 2010-09-21 | 2010-11-19 | 2017-03-26 | 2017-05-24
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ411B | Reconstruction of Albert Road Area, 94th St, Qns (SEQ002568) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2010-11-20 | 2010-12-19 | 2017-05-25 | 2023-06-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ631B-3 | ALMEDA AV - PHASE III | 1 | DEVELOP SCOPE | 2011-03-06 | 2011-06-03 | 2011-03-06 | 2011-06-03
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ631B-3 | ALMEDA AV - PHASE III | 2 | PRELIMINARY DESIGN | 2011-06-04 | 2011-10-01 | 2011-06-04 | 2011-10-01
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ631B-3 | ALMEDA AV - PHASE III | 3 | FINAL DESIGN | 2011-10-02 | 2012-03-29 | 2011-10-02 | 2012-03-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ631B-3 | ALMEDA AV - PHASE III | 4 | BID AWARD AND REGISTER CONTRCT | 2012-03-30 | 2012-06-27 | 2022-03-17 | 2022-06-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ631B-3 | ALMEDA AV - PHASE III | 5 | CONSTRUCTION TO 25% | 2012-06-28 | 2012-10-25 | 2022-06-15 | 2022-06-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ631B-3 | ALMEDA AV - PHASE III | 6 | CONSTRUCTION TO 50% | 2012-10-26 | 2013-02-22 | 2022-06-15 | 2022-06-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ631B-3 | ALMEDA AV - PHASE III | 7 | CONSTRUCTION TO 75% | 2013-02-23 | 2013-06-22 | 2022-06-15 | 2022-06-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ631B-3 | ALMEDA AV - PHASE III | 8 | ORIGINAL EQUIP & FURNISHING | 2013-06-23 | 2013-09-20 | 2022-06-15 | 2022-06-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ631B-3 | ALMEDA AV - PHASE III | 9 | SUBSTANTIAL COMPLETION | 2013-09-21 | 2013-11-19 | 2022-06-15 | 2022-06-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ631B-3 | ALMEDA AV - PHASE III | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-11-20 | 2013-12-19 | 2024-01-04 | 2025-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ662G | Springfield Gardens Phase V (SE-862) | 1 | DEVELOP SCOPE | 2014-06-01 | 2014-08-29 | 2020-03-01 | 2020-05-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ662G | Springfield Gardens Phase V (SE-862) | 2 | PRELIMINARY DESIGN | 2014-08-30 | 2014-12-27 | 2020-05-30 | 2020-09-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ662G | Springfield Gardens Phase V (SE-862) | 3 | FINAL DESIGN | 2014-12-28 | 2015-06-25 | 2020-09-27 | 2021-03-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ662G | Springfield Gardens Phase V (SE-862) | 4 | BID AWARD AND REGISTER CONTRCT | 2015-06-26 | 2015-09-23 | 2021-03-26 | 2021-06-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ662G | Springfield Gardens Phase V (SE-862) | 5 | CONSTRUCTION TO 25% | 2015-09-24 | 2016-01-21 | 2021-06-24 | 2021-10-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ662G | Springfield Gardens Phase V (SE-862) | 6 | CONSTRUCTION TO 50% | 2016-01-22 | 2016-05-20 | 2021-10-22 | 2022-02-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ662G | Springfield Gardens Phase V (SE-862) | 7 | CONSTRUCTION TO 75% | 2016-05-21 | 2016-09-17 | 2022-02-19 | 2022-06-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ662G | Springfield Gardens Phase V (SE-862) | 8 | ORIGINAL EQUIP & FURNISHING | 2016-09-18 | 2016-12-16 | 2022-06-19 | 2022-09-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ662G | Springfield Gardens Phase V (SE-862) | 9 | SUBSTANTIAL COMPLETION | 2016-12-17 | 2017-02-14 | 2022-09-17 | 2022-11-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ662G | Springfield Gardens Phase V (SE-862) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-02-15 | 2017-03-16 | 2022-11-16 | 2026-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ677 | 91ST AVE, ETC, QUEENS | 1 | DEVELOP SCOPE | 2000-05-21 | 2000-08-18 | 2000-05-21 | 2000-08-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ677 | 91ST AVE, ETC, QUEENS | 2 | PRELIMINARY DESIGN | 2000-08-19 | 2000-12-16 | 2000-08-19 | 2000-12-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ677 | 91ST AVE, ETC, QUEENS | 3 | FINAL DESIGN | 2000-12-17 | 2001-06-14 | 2000-12-17 | 2001-06-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ677 | 91ST AVE, ETC, QUEENS | 4 | BID AWARD AND REGISTER CONTRCT | 2001-06-15 | 2001-09-12 | 2001-06-15 | 2001-09-12
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ677 | 91ST AVE, ETC, QUEENS | 5 | CONSTRUCTION TO 25% | 2001-09-13 | 2002-01-10 | 2001-09-13 | 2002-01-10
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ677 | 91ST AVE, ETC, QUEENS | 6 | CONSTRUCTION TO 50% | 2002-01-11 | 2002-05-10 | 2002-01-11 | 2002-05-10
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ677 | 91ST AVE, ETC, QUEENS | 7 | CONSTRUCTION TO 75% | 2002-05-11 | 2002-09-07 | 2002-05-11 | 2002-09-07
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ677 | 91ST AVE, ETC, QUEENS | 8 | ORIGINAL EQUIP & FURNISHING | 2002-09-08 | 2002-12-06 | 2002-09-08 | 2002-12-06
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ677 | 91ST AVE, ETC, QUEENS | 9 | SUBSTANTIAL COMPLETION | 2002-12-07 | 2003-02-04 | 2002-12-07 | 2003-02-04
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ677 | 91ST AVE, ETC, QUEENS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2003-02-05 | 2003-03-06 | 2003-02-05 | 2021-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ708 | RECONSTRUCTION OF 73RD PLACE | 1 | DEVELOP SCOPE | 2004-05-21 | 2004-08-18 | 2004-05-21 | 2004-08-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ708 | RECONSTRUCTION OF 73RD PLACE | 2 | PRELIMINARY DESIGN | 2004-08-19 | 2004-12-16 | 2004-08-19 | 2004-12-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ708 | RECONSTRUCTION OF 73RD PLACE | 3 | FINAL DESIGN | 2004-12-17 | 2005-06-14 | 2004-12-17 | 2005-06-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ708 | RECONSTRUCTION OF 73RD PLACE | 4 | BID AWARD AND REGISTER CONTRCT | 2005-06-15 | 2005-09-12 | 2005-06-15 | 2022-06-01
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ708 | RECONSTRUCTION OF 73RD PLACE | 5 | CONSTRUCTION TO 25% | 2005-09-13 | 2006-01-10 | 2022-06-02 | 2022-06-01
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ708 | RECONSTRUCTION OF 73RD PLACE | 6 | CONSTRUCTION TO 50% | 2006-01-11 | 2006-05-10 | 2022-06-02 | 2022-06-01
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ708 | RECONSTRUCTION OF 73RD PLACE | 7 | CONSTRUCTION TO 75% | 2006-05-11 | 2006-09-07 | 2022-06-02 | 2022-06-01
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ708 | RECONSTRUCTION OF 73RD PLACE | 8 | ORIGINAL EQUIP & FURNISHING | 2006-09-08 | 2006-12-06 | 2022-06-02 | 2022-06-01
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ708 | RECONSTRUCTION OF 73RD PLACE | 9 | SUBSTANTIAL COMPLETION | 2006-12-07 | 2007-02-04 | 2022-06-02 | 2022-06-01
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ708 | RECONSTRUCTION OF 73RD PLACE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2007-02-05 | 2007-03-06 | 2023-11-04 | 2023-12-03
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ724B | Recon of Streets in Brookville-Edgewood Triangle (SEQ200519) | 1 | DEVELOP SCOPE | 2003-08-13 | 2003-11-10 | 2003-08-13 | 2003-11-10
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ724B | Recon of Streets in Brookville-Edgewood Triangle (SEQ200519) | 2 | PRELIMINARY DESIGN | 2003-11-11 | 2004-03-09 | 2003-11-11 | 2004-03-09
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ724B | Recon of Streets in Brookville-Edgewood Triangle (SEQ200519) | 3 | FINAL DESIGN | 2004-03-10 | 2004-09-05 | 2004-03-10 | 2017-03-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ724B | Recon of Streets in Brookville-Edgewood Triangle (SEQ200519) | 4 | BID AWARD AND REGISTER CONTRCT | 2004-09-06 | 2004-12-04 | 2017-03-15 | 2017-06-12
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ724B | Recon of Streets in Brookville-Edgewood Triangle (SEQ200519) | 5 | CONSTRUCTION TO 25% | 2004-12-05 | 2005-04-03 | 2017-06-13 | 2018-01-08
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ724B | Recon of Streets in Brookville-Edgewood Triangle (SEQ200519) | 6 | CONSTRUCTION TO 50% | 2005-04-04 | 2005-08-01 | 2018-01-09 | 2018-08-06
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ724B | Recon of Streets in Brookville-Edgewood Triangle (SEQ200519) | 7 | CONSTRUCTION TO 75% | 2005-08-02 | 2005-11-29 | 2018-03-05 | 2019-03-04
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ724B | Recon of Streets in Brookville-Edgewood Triangle (SEQ200519) | 8 | ORIGINAL EQUIP & FURNISHING | 2005-11-30 | 2006-02-27 | 2019-03-05 | 2019-06-02
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ724B | Recon of Streets in Brookville-Edgewood Triangle (SEQ200519) | 9 | SUBSTANTIAL COMPLETION | 2006-02-28 | 2006-04-28 | 2019-06-03 | 2019-08-01
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ724B | Recon of Streets in Brookville-Edgewood Triangle (SEQ200519) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2006-04-29 | 2006-05-28 | 2019-08-02 | 2027-03-22
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ787B3 | Sutter Ave, Etc - Phase V (B3) | 1 | DEVELOP SCOPE | 2012-02-25 | 2012-05-24 | 2012-02-25 | 2012-05-24
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ787B3 | Sutter Ave, Etc - Phase V (B3) | 2 | PRELIMINARY DESIGN | 2012-05-25 | 2012-09-21 | 2012-05-25 | 2012-09-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ787B3 | Sutter Ave, Etc - Phase V (B3) | 3 | FINAL DESIGN | 2012-09-22 | 2013-03-20 | 2012-09-22 | 2018-03-20
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ787B3 | Sutter Ave, Etc - Phase V (B3) | 4 | BID AWARD AND REGISTER CONTRCT | 2013-03-21 | 2013-06-18 | 2018-03-21 | 2018-03-20
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ787B3 | Sutter Ave, Etc - Phase V (B3) | 5 | CONSTRUCTION TO 25% | 2013-06-19 | 2013-10-16 | 2018-03-21 | 2018-03-20
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ787B3 | Sutter Ave, Etc - Phase V (B3) | 6 | CONSTRUCTION TO 50% | 2013-10-17 | 2014-02-13 | 2018-03-21 | 2018-03-20
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ787B3 | Sutter Ave, Etc - Phase V (B3) | 7 | CONSTRUCTION TO 75% | 2014-02-14 | 2014-06-13 | 2018-03-21 | 2018-03-20
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ787B3 | Sutter Ave, Etc - Phase V (B3) | 8 | ORIGINAL EQUIP & FURNISHING | 2014-06-14 | 2014-09-11 | 2018-03-21 | 2018-03-20
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ787B3 | Sutter Ave, Etc - Phase V (B3) | 9 | SUBSTANTIAL COMPLETION | 2014-09-12 | 2014-11-10 | 2018-03-21 | 2018-03-20
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ787B3 | Sutter Ave, Etc - Phase V (B3) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-11-11 | 2014-12-10 | 2018-03-21 | 2029-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ976 | SEQ - FRANCIS LEWIS BLVD & 93RD AVE (QED-976) | 1 | DEVELOP SCOPE | 2017-03-01 | 2017-05-29 | 2017-03-01 | 2017-05-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ976 | SEQ - FRANCIS LEWIS BLVD & 93RD AVE (QED-976) | 2 | PRELIMINARY DESIGN | 2017-05-30 | 2017-09-26 | 2017-05-30 | 2017-09-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ976 | SEQ - FRANCIS LEWIS BLVD & 93RD AVE (QED-976) | 3 | FINAL DESIGN | 2017-09-27 | 2018-03-25 | 2017-09-27 | 2018-03-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ976 | SEQ - FRANCIS LEWIS BLVD & 93RD AVE (QED-976) | 4 | BID AWARD AND REGISTER CONTRCT | 2018-03-26 | 2018-06-23 | 2018-03-26 | 2018-06-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ976 | SEQ - FRANCIS LEWIS BLVD & 93RD AVE (QED-976) | 5 | CONSTRUCTION TO 25% | 2018-06-24 | 2018-10-21 | 2018-06-24 | 2018-10-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ976 | SEQ - FRANCIS LEWIS BLVD & 93RD AVE (QED-976) | 6 | CONSTRUCTION TO 50% | 2018-10-22 | 2019-02-18 | 2018-10-22 | 2019-02-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ976 | SEQ - FRANCIS LEWIS BLVD & 93RD AVE (QED-976) | 7 | CONSTRUCTION TO 75% | 2019-02-19 | 2019-06-18 | 2019-02-19 | 2019-06-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ976 | SEQ - FRANCIS LEWIS BLVD & 93RD AVE (QED-976) | 8 | ORIGINAL EQUIP & FURNISHING | 2019-06-19 | 2019-09-16 | 2019-06-19 | 2019-09-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ976 | SEQ - FRANCIS LEWIS BLVD & 93RD AVE (QED-976) | 9 | SUBSTANTIAL COMPLETION | 2019-09-17 | 2019-11-15 | 2019-09-17 | 2019-11-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ976 | SEQ - FRANCIS LEWIS BLVD & 93RD AVE (QED-976) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-11-16 | 2019-12-15 | 2019-11-16 | 2028-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ985 | SHORE ROAD RECONSTRUCTION (SEQ200585) | 1 | DEVELOP SCOPE | 2009-06-30 | 2009-09-27 | 2011-07-01 | 2011-09-28
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ985 | SHORE ROAD RECONSTRUCTION (SEQ200585) | 2 | PRELIMINARY DESIGN | 2009-09-28 | 2010-01-25 | 2011-09-29 | 2012-01-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ985 | SHORE ROAD RECONSTRUCTION (SEQ200585) | 3 | FINAL DESIGN | 2010-01-26 | 2010-07-24 | 2012-01-27 | 2014-08-04
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ985 | SHORE ROAD RECONSTRUCTION (SEQ200585) | 4 | BID AWARD AND REGISTER CONTRCT | 2010-07-25 | 2010-10-22 | 2014-08-05 | 2014-11-02
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ985 | SHORE ROAD RECONSTRUCTION (SEQ200585) | 5 | CONSTRUCTION TO 25% | 2010-10-23 | 2011-02-19 | 2014-11-03 | 2015-04-01
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ985 | SHORE ROAD RECONSTRUCTION (SEQ200585) | 6 | CONSTRUCTION TO 50% | 2011-02-20 | 2011-06-19 | 2015-04-02 | 2015-08-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ985 | SHORE ROAD RECONSTRUCTION (SEQ200585) | 7 | CONSTRUCTION TO 75% | 2011-06-20 | 2011-10-17 | 2015-08-30 | 2016-01-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ985 | SHORE ROAD RECONSTRUCTION (SEQ200585) | 8 | ORIGINAL EQUIP & FURNISHING | 2011-10-18 | 2012-01-15 | 2016-01-27 | 2016-04-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ985 | SHORE ROAD RECONSTRUCTION (SEQ200585) | 9 | SUBSTANTIAL COMPLETION | 2012-01-16 | 2012-03-15 | 2016-04-26 | 2016-06-24
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ985 | SHORE ROAD RECONSTRUCTION (SEQ200585) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-03-16 | 2012-04-14 | 2016-06-25 | 2022-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQF030 | HARPER ST WASTE WATER AND STORM WATER CONVEYANCES | 1 | DEVELOP SCOPE | 2012-06-30 | 2012-09-27 | 2012-06-30 | 2012-09-27
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQF030 | HARPER ST WASTE WATER AND STORM WATER CONVEYANCES | 2 | PRELIMINARY DESIGN | 2012-09-28 | 2013-01-25 | 2012-09-28 | 2013-01-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQF030 | HARPER ST WASTE WATER AND STORM WATER CONVEYANCES | 3 | FINAL DESIGN | 2013-01-26 | 2013-07-24 | 2013-01-26 | 2021-12-31
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQF030 | HARPER ST WASTE WATER AND STORM WATER CONVEYANCES | 4 | BID AWARD AND REGISTER CONTRCT | 2013-07-25 | 2013-10-22 | 2022-01-01 | 2022-03-31
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQF030 | HARPER ST WASTE WATER AND STORM WATER CONVEYANCES | 5 | CONSTRUCTION TO 25% | 2013-10-23 | 2014-02-19 | 2022-04-01 | 2022-07-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQF030 | HARPER ST WASTE WATER AND STORM WATER CONVEYANCES | 6 | CONSTRUCTION TO 50% | 2014-02-20 | 2014-06-19 | 2022-07-30 | 2022-11-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQF030 | HARPER ST WASTE WATER AND STORM WATER CONVEYANCES | 7 | CONSTRUCTION TO 75% | 2014-06-20 | 2014-10-17 | 2022-11-27 | 2023-03-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQF030 | HARPER ST WASTE WATER AND STORM WATER CONVEYANCES | 8 | ORIGINAL EQUIP & FURNISHING | 2014-10-18 | 2015-01-15 | 2023-03-27 | 2023-06-24
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQF030 | HARPER ST WASTE WATER AND STORM WATER CONVEYANCES | 9 | SUBSTANTIAL COMPLETION | 2015-01-16 | 2015-03-16 | 2023-06-25 | 2023-12-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQF030 | HARPER ST WASTE WATER AND STORM WATER CONVEYANCES | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-17 | 2015-04-15 | 2023-12-30 | 2024-12-27
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQF033 | 28-11 QPN 7TH FL REHABILITATION | 1 | DEVELOP SCOPE | 2015-06-01 | 2015-08-29 | 2018-06-01 | 2018-08-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQF033 | 28-11 QPN 7TH FL REHABILITATION | 2 | PRELIMINARY DESIGN | 2015-08-30 | 2015-12-27 | 2018-08-30 | 2018-12-27
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQF033 | 28-11 QPN 7TH FL REHABILITATION | 3 | FINAL DESIGN | 2015-12-28 | 2016-06-24 | 2018-12-28 | 2019-06-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQF033 | 28-11 QPN 7TH FL REHABILITATION | 4 | BID AWARD AND REGISTER CONTRCT | 2016-06-25 | 2016-09-22 | 2019-06-26 | 2019-09-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQF033 | 28-11 QPN 7TH FL REHABILITATION | 5 | CONSTRUCTION TO 25% | 2016-09-23 | 2017-01-20 | 2019-09-24 | 2020-01-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQF033 | 28-11 QPN 7TH FL REHABILITATION | 6 | CONSTRUCTION TO 50% | 2017-01-21 | 2017-05-20 | 2020-01-22 | 2020-05-20
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQF033 | 28-11 QPN 7TH FL REHABILITATION | 7 | CONSTRUCTION TO 75% | 2017-05-21 | 2017-09-17 | 2020-05-21 | 2020-09-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQF033 | 28-11 QPN 7TH FL REHABILITATION | 8 | ORIGINAL EQUIP & FURNISHING | 2017-09-18 | 2017-12-16 | 2020-09-18 | 2020-12-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQF033 | 28-11 QPN 7TH FL REHABILITATION | 9 | SUBSTANTIAL COMPLETION | 2017-12-17 | 2018-02-14 | 2020-12-17 | 2021-02-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQF033 | 28-11 QPN 7TH FL REHABILITATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-02-15 | 2018-03-16 | 2021-02-15 | 2024-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2006Q2 | PRIOR NOTICE SIDEWALKS - QUEENS (2) | 1 | DEVELOP SCOPE | 2005-01-03 | 2005-04-02 | 2005-01-03 | 2005-04-02
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2006Q2 | PRIOR NOTICE SIDEWALKS - QUEENS (2) | 2 | PRELIMINARY DESIGN | 2005-04-03 | 2005-07-31 | 2005-04-03 | 2005-07-31
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2006Q2 | PRIOR NOTICE SIDEWALKS - QUEENS (2) | 3 | FINAL DESIGN | 2005-08-01 | 2006-01-27 | 2005-08-01 | 2006-01-27
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2006Q2 | PRIOR NOTICE SIDEWALKS - QUEENS (2) | 4 | BID AWARD AND REGISTER CONTRCT | 2006-02-24 | 2006-06-08 | 2006-02-24 | 2006-06-08
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2006Q2 | PRIOR NOTICE SIDEWALKS - QUEENS (2) | 5 | CONSTRUCTION TO 25% | 2006-06-09 | 2006-06-08 | 2006-06-09 | 2006-06-08
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2006Q2 | PRIOR NOTICE SIDEWALKS - QUEENS (2) | 6 | CONSTRUCTION TO 50% | 2006-06-09 | 2006-06-08 | 2006-06-09 | 2006-06-08
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2006Q2 | PRIOR NOTICE SIDEWALKS - QUEENS (2) | 7 | CONSTRUCTION TO 75% | 2006-06-09 | 2006-06-08 | 2006-06-09 | 2006-06-08
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2006Q2 | PRIOR NOTICE SIDEWALKS - QUEENS (2) | 8 | ORIGINAL EQUIP & FURNISHING | 2006-06-09 | 2006-06-08 | 2006-06-09 | 2006-06-08
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2006Q2 | PRIOR NOTICE SIDEWALKS - QUEENS (2) | 9 | SUBSTANTIAL COMPLETION | 2006-06-09 | 2006-06-08 | 2006-06-09 | 2006-06-08
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2006Q2 | PRIOR NOTICE SIDEWALKS - QUEENS (2) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2006-06-09 | 2006-07-08 | 2006-06-09 | 2029-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2018Q2 | Prior Notice Sidwalks - Queens | 1 | DEVELOP SCOPE | 2017-03-01 | 2017-05-29 | 2017-03-01 | 2017-05-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2018Q2 | Prior Notice Sidwalks - Queens | 2 | PRELIMINARY DESIGN | 2017-05-30 | 2017-09-26 | 2017-05-30 | 2017-09-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2018Q2 | Prior Notice Sidwalks - Queens | 3 | FINAL DESIGN | 2017-09-27 | 2018-03-25 | 2017-09-27 | 2018-03-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2018Q2 | Prior Notice Sidwalks - Queens | 4 | BID AWARD AND REGISTER CONTRCT | 2018-03-26 | 2018-06-23 | 2018-03-26 | 2018-06-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2018Q2 | Prior Notice Sidwalks - Queens | 5 | CONSTRUCTION TO 25% | 2018-06-24 | 2018-10-21 | 2018-06-24 | 2018-10-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2018Q2 | Prior Notice Sidwalks - Queens | 6 | CONSTRUCTION TO 50% | 2018-10-22 | 2019-02-18 | 2018-10-22 | 2019-02-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2018Q2 | Prior Notice Sidwalks - Queens | 7 | CONSTRUCTION TO 75% | 2019-02-19 | 2019-06-18 | 2019-02-19 | 2019-06-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2018Q2 | Prior Notice Sidwalks - Queens | 8 | ORIGINAL EQUIP & FURNISHING | 2019-06-19 | 2019-09-16 | 2019-06-19 | 2019-09-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2018Q2 | Prior Notice Sidwalks - Queens | 9 | SUBSTANTIAL COMPLETION | 2019-09-17 | 2019-11-15 | 2019-09-17 | 2019-11-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2018Q2 | Prior Notice Sidwalks - Queens | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-11-16 | 2019-12-15 | 2019-11-16 | 2023-04-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020Q1 | Prior Notice Sidewalks- Queens | 1 | DEVELOP SCOPE | 2019-06-30 | 2019-09-27 | 2019-06-30 | 2019-09-27
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020Q1 | Prior Notice Sidewalks- Queens | 2 | PRELIMINARY DESIGN | 2019-09-28 | 2020-01-25 | 2019-09-28 | 2020-01-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020Q1 | Prior Notice Sidewalks- Queens | 3 | FINAL DESIGN | 2020-01-26 | 2020-07-23 | 2020-01-26 | 2020-07-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020Q1 | Prior Notice Sidewalks- Queens | 4 | BID AWARD AND REGISTER CONTRCT | 2020-07-24 | 2020-10-21 | 2020-07-24 | 2020-10-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020Q1 | Prior Notice Sidewalks- Queens | 5 | CONSTRUCTION TO 25% | 2020-10-22 | 2021-02-18 | 2020-10-22 | 2021-02-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020Q1 | Prior Notice Sidewalks- Queens | 6 | CONSTRUCTION TO 50% | 2021-02-19 | 2021-06-18 | 2021-02-19 | 2021-06-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020Q1 | Prior Notice Sidewalks- Queens | 7 | CONSTRUCTION TO 75% | 2021-06-19 | 2021-10-16 | 2021-06-19 | 2021-10-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020Q1 | Prior Notice Sidewalks- Queens | 8 | ORIGINAL EQUIP & FURNISHING | 2021-10-17 | 2022-01-14 | 2021-10-17 | 2022-01-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020Q1 | Prior Notice Sidewalks- Queens | 9 | SUBSTANTIAL COMPLETION | 2022-01-15 | 2022-03-15 | 2022-01-15 | 2022-03-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020Q1 | Prior Notice Sidewalks- Queens | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-16 | 2022-04-14 | 2022-03-16 | 2022-04-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020Q2 | Prior Notice Sidewalks- Queens | 1 | DEVELOP SCOPE | 2019-01-30 | 2019-04-29 | 2019-01-30 | 2019-04-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020Q2 | Prior Notice Sidewalks- Queens | 2 | PRELIMINARY DESIGN | 2019-04-30 | 2019-08-27 | 2019-04-30 | 2019-08-27
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020Q2 | Prior Notice Sidewalks- Queens | 3 | FINAL DESIGN | 2019-08-28 | 2020-02-23 | 2019-08-28 | 2020-02-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020Q2 | Prior Notice Sidewalks- Queens | 4 | BID AWARD AND REGISTER CONTRCT | 2020-02-24 | 2020-05-23 | 2020-02-24 | 2020-05-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020Q2 | Prior Notice Sidewalks- Queens | 5 | CONSTRUCTION TO 25% | 2020-05-24 | 2020-09-20 | 2020-05-24 | 2020-09-20
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020Q2 | Prior Notice Sidewalks- Queens | 6 | CONSTRUCTION TO 50% | 2020-09-21 | 2021-01-18 | 2020-09-21 | 2021-01-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020Q2 | Prior Notice Sidewalks- Queens | 7 | CONSTRUCTION TO 75% | 2021-01-19 | 2021-05-18 | 2021-01-19 | 2021-05-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020Q2 | Prior Notice Sidewalks- Queens | 8 | ORIGINAL EQUIP & FURNISHING | 2021-05-19 | 2021-08-16 | 2021-05-19 | 2021-08-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020Q2 | Prior Notice Sidewalks- Queens | 9 | SUBSTANTIAL COMPLETION | 2021-08-17 | 2021-10-15 | 2021-08-17 | 2021-10-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020Q2 | Prior Notice Sidewalks- Queens | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-10-16 | 2021-11-14 | 2021-10-16 | 2021-11-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQ122-FHR | FOREST HILLS ROOF | 2 | DESIGN START | 2015-03-16 | 2017-02-06 | 2015-03-16 | 2017-02-06
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQ122-FHR | FOREST HILLS ROOF | 3 | DESIGN COMPLETION | 2016-11-29 | 2017-01-02 | 2016-11-29 | 2017-01-02
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQ122-FHR | FOREST HILLS ROOF | 4 | CONSTRUCTION START | 2017-01-03 | 2017-09-30 | 2017-01-03 | 2017-09-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQ122-FHR | FOREST HILLS ROOF | 5 | CONSTRUCTION COMPLETION | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQ122-FHR | FOREST HILLS ROOF | 6 | DEVELOP SCOPE | 2017-10-01 | 2017-10-01 | 2017-10-02 | 2017-12-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQ122-FHR | FOREST HILLS ROOF | 7 | PRELIMINARY DESIGN | 2017-10-01 | 2017-10-01 | 2017-12-31 | 2018-04-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQ122-FHR | FOREST HILLS ROOF | 8 | FINAL DESIGN | 2017-10-01 | 2017-10-01 | 2018-04-30 | 2018-10-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQ122-FHR | FOREST HILLS ROOF | 9 | BID AWARD AND REGISTER CONTRCT | 2017-10-01 | 2017-10-01 | 2018-10-27 | 2019-01-24
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQ122-FHR | FOREST HILLS ROOF | 10 | CONSTRUCTION TO 25% | 2017-10-01 | 2017-10-01 | 2019-01-25 | 2019-05-24
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQ122-FHR | FOREST HILLS ROOF | 11 | CONSTRUCTION TO 50% | 2017-10-01 | 2017-10-01 | 2019-05-25 | 2019-09-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQ122-FHR | FOREST HILLS ROOF | 12 | CONSTRUCTION TO 75% | 2017-10-01 | 2017-10-01 | 2019-09-22 | 2020-01-19
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQ122-FHR | FOREST HILLS ROOF | 13 | ORIGINAL EQUIP & FURNISHING | 2017-10-01 | 2017-10-01 | 2020-01-20 | 2020-04-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQ122-FHR | FOREST HILLS ROOF | 14 | SUBSTANTIAL COMPLETION | 2017-10-01 | 2017-10-01 | 2020-04-19 | 2020-06-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQ122-FHR | FOREST HILLS ROOF | 15 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-10-01 | 2017-10-01 | 2020-06-18 | 2020-07-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQ122-W | Whitestone - Selected Masonry | 2 | DESIGN START | 2012-05-01 | 2012-05-06 | 2013-03-20 | 2013-06-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQ122-W | Whitestone - Selected Masonry | 3 | DESIGN COMPLETION | 2012-05-07 | 2012-06-27 | 2013-06-19 | 2014-12-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQ122-W | Whitestone - Selected Masonry | 4 | CONSTRUCTION START | 2012-06-28 | 2013-01-08 | 2014-12-15 | 2015-09-11
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQ122-W | Whitestone - Selected Masonry | 5 | CONSTRUCTION COMPLETION | 2013-01-09 | 2013-10-16 | 2015-09-12 | 2019-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQARVEXPN | Arverne Library - Replacement facility | 1 | PROJECT START | 2016-04-25 | 2016-04-25 | 2015-09-30 | 2015-09-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQARVEXPN | Arverne Library - Replacement facility | 2 | DESIGN START | 2016-04-26 | 2016-04-26 | 2015-10-01 | 2018-04-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQARVEXPN | Arverne Library - Replacement facility | 3 | DESIGN COMPLETION | 2016-04-27 | 2016-04-27 | 2018-04-27 | 2021-01-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQARVEXPN | Arverne Library - Replacement facility | 4 | CONSTRUCTION START | 2016-04-28 | 2016-04-28 | 2021-01-16 | 2021-10-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQARVEXPN | Arverne Library - Replacement facility | 5 | CONSTRUCTION COMPLETION | 2016-04-29 | 2021-12-08 | 2021-10-16 | 2024-10-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQASADA | ASTORIA - Brach renovation with ADA | 1 | PROJECT START | 2016-02-23 | 2016-02-23 | 2015-10-21 | 2015-10-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQASADA | ASTORIA - Brach renovation with ADA | 2 | DESIGN START | 2016-02-24 | 2016-02-24 | 2015-10-22 | 2016-06-28
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQASADA | ASTORIA - Brach renovation with ADA | 3 | DESIGN COMPLETION | 2016-02-25 | 2016-02-25 | 2016-06-29 | 2019-11-08
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQASADA | ASTORIA - Brach renovation with ADA | 4 | CONSTRUCTION START | 2016-02-26 | 2016-02-26 | 2019-11-09 | 2019-11-09
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQASADA | ASTORIA - Brach renovation with ADA | 5 | CONSTRUCTION COMPLETION | 2016-02-27 | 2018-12-28 | 2019-11-10 | 2022-09-10
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQBPEXPN | BAISLEY PARK - Branch Renovation | 1 | DESIGN | 2018-06-30 | 2018-07-29 | 2020-06-30 | 2021-07-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQBPEXPN | BAISLEY PARK - Branch Renovation | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-30 | 2018-10-27 | 2021-07-30 | 2021-10-27
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQBPEXPN | BAISLEY PARK - Branch Renovation | 3 | CONSTRUCTION | 2018-10-28 | 2019-04-25 | 2021-10-28 | 2023-04-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQBPEXPN | BAISLEY PARK - Branch Renovation | 4 | ORIGINAL EQUIP & FURNISHING | 2019-04-26 | 2019-07-24 | 2023-04-26 | 2023-07-24
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQBPEXPN | BAISLEY PARK - Branch Renovation | 5 | SUBSTANTIAL COMPLETION | 2019-07-25 | 2019-08-23 | 2023-07-25 | 2023-08-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQBPEXPN | BAISLEY PARK - Branch Renovation | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-08-24 | 2019-09-22 | 2023-08-24 | 2023-09-22
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQBPEXPN | BAISLEY PARK - Branch Renovation | 7 | PROJECT START | 2019-08-24 | 2019-09-22 | 2023-09-23 | 2023-09-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQBPEXPN | BAISLEY PARK - Branch Renovation | 8 | DESIGN START | 2019-08-24 | 2019-09-22 | 2023-09-24 | 2023-09-24
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQBPEXPN | BAISLEY PARK - Branch Renovation | 9 | DESIGN COMPLETION | 2019-08-24 | 2019-09-22 | 2023-09-25 | 2023-09-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQBPEXPN | BAISLEY PARK - Branch Renovation | 10 | CONSTRUCTION START | 2019-08-24 | 2019-09-22 | 2023-09-26 | 2023-09-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQBPEXPN | BAISLEY PARK - Branch Renovation | 11 | CONSTRUCTION COMPLETION | 2019-08-24 | 2019-09-22 | 2023-09-27 | 2023-09-27
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQBTRENOV | BAY TERRACE: Branch Renovation and Expansion | 1 | DESIGN | 2018-06-30 | 2018-07-29 | 2018-06-30 | 2018-07-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQBTRENOV | BAY TERRACE: Branch Renovation and Expansion | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-30 | 2018-10-27 | 2018-07-30 | 2018-10-27
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQBTRENOV | BAY TERRACE: Branch Renovation and Expansion | 3 | CONSTRUCTION | 2018-10-28 | 2019-04-25 | 2018-10-28 | 2022-04-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQBTRENOV | BAY TERRACE: Branch Renovation and Expansion | 4 | ORIGINAL EQUIP & FURNISHING | 2019-04-26 | 2019-07-24 | 2022-04-26 | 2022-07-24
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQBTRENOV | BAY TERRACE: Branch Renovation and Expansion | 5 | SUBSTANTIAL COMPLETION | 2019-07-25 | 2019-08-23 | 2022-07-25 | 2022-08-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQBTRENOV | BAY TERRACE: Branch Renovation and Expansion | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-08-24 | 2019-09-22 | 2022-08-24 | 2022-09-22
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQBW-EXP | Briarwood: Branch Renovation | 1 | DESIGN | 2019-01-01 | 2020-12-20 | 2019-01-01 | 2020-12-20
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQBW-EXP | Briarwood: Branch Renovation | 2 | BID AWARD AND REGISTER CONTRCT | 2020-12-21 | 2021-12-15 | 2020-12-21 | 2021-12-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQBW-EXP | Briarwood: Branch Renovation | 3 | CONSTRUCTION | 2021-12-16 | 2027-12-14 | 2021-12-16 | 2027-12-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122-AU | Auburndale - Roof Replacement | 1 | PROJECT START | 2012-05-04 | 2012-05-04 | 2012-05-04 | 2012-05-04
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122-AU | Auburndale - Roof Replacement | 2 | DESIGN START | 2012-06-11 | 2012-06-11 | 2012-06-11 | 2012-09-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122-AU | Auburndale - Roof Replacement | 3 | DESIGN COMPLETION | 2012-09-17 | 2012-09-17 | 2012-09-17 | 2014-04-08
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122-AU | Auburndale - Roof Replacement | 4 | CONSTRUCTION START | 2013-04-09 | 2013-04-09 | 2014-04-09 | 2016-08-07
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122-AU | Auburndale - Roof Replacement | 5 | CONSTRUCTION COMPLETION | 2013-12-06 | 2013-12-06 | 2016-08-08 | 2024-08-08
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122BCE | BROAD CHANNEL EXTERIOR RENOVATION | 1 | PROJECT START | 2014-11-24 | 2014-11-24 | 2013-07-18 | 2013-07-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122BCE | BROAD CHANNEL EXTERIOR RENOVATION | 2 | DESIGN START | 2014-11-25 | 2014-11-25 | 2013-07-19 | 2013-09-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122BCE | BROAD CHANNEL EXTERIOR RENOVATION | 3 | DESIGN COMPLETION | 2014-11-26 | 2014-11-26 | 2013-09-17 | 2016-09-28
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122BCE | BROAD CHANNEL EXTERIOR RENOVATION | 4 | CONSTRUCTION START | 2014-11-27 | 2014-11-27 | 2016-09-29 | 2019-07-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122BCE | BROAD CHANNEL EXTERIOR RENOVATION | 5 | CONSTRUCTION COMPLETION | 2014-11-28 | 2018-12-28 | 2019-07-18 | 2024-07-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122BR2 | BROADWAY LIBRARY - RENOVATION (PHASE THREE AND FOUR) | 1 | PROJECT START | 2014-02-13 | 2014-02-13 | 2014-02-13 | 2014-02-13
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122BR2 | BROADWAY LIBRARY - RENOVATION (PHASE THREE AND FOUR) | 2 | DESIGN START | 2015-03-02 | 2016-03-01 | 2015-03-02 | 2016-09-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122BR2 | BROADWAY LIBRARY - RENOVATION (PHASE THREE AND FOUR) | 3 | DESIGN COMPLETION | 2016-03-02 | 2016-07-30 | 2016-09-30 | 2018-11-12
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122BR2 | BROADWAY LIBRARY - RENOVATION (PHASE THREE AND FOUR) | 4 | CONSTRUCTION START | 2016-07-31 | 2017-12-20 | 2018-11-13 | 2019-08-12
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122BR2 | BROADWAY LIBRARY - RENOVATION (PHASE THREE AND FOUR) | 5 | CONSTRUCTION COMPLETION | 2017-12-21 | 2017-12-21 | 2019-08-13 | 2022-04-12
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122-CM | CAMBRIA HEIGHTS - Lower Level Renovation | 1 | DEVELOP SCOPE | 2011-01-02 | 2011-04-01 | 2012-12-17 | 2012-12-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122-CM | CAMBRIA HEIGHTS - Lower Level Renovation | 2 | PRELIMINARY DESIGN | 2011-04-02 | 2011-07-30 | 2012-12-18 | 2014-12-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122-CM | CAMBRIA HEIGHTS - Lower Level Renovation | 3 | FINAL DESIGN | 2011-07-31 | 2012-01-26 | 2014-04-09 | 2016-04-09
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122-CM | CAMBRIA HEIGHTS - Lower Level Renovation | 4 | BID AWARD AND REGISTER CONTRCT | 2012-01-27 | 2012-04-25 | 2016-04-10 | 2016-04-09
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122-CM | CAMBRIA HEIGHTS - Lower Level Renovation | 5 | CONSTRUCTION TO 25% | 2012-04-26 | 2012-08-23 | 2016-04-10 | 2025-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122-CM | CAMBRIA HEIGHTS - Lower Level Renovation | 6 | CONSTRUCTION TO 50% | 2012-08-24 | 2012-12-21 | 2016-04-10 | 2025-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122-CM | CAMBRIA HEIGHTS - Lower Level Renovation | 7 | CONSTRUCTION TO 75% | 2012-12-22 | 2013-04-20 | 2016-04-10 | 2025-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122-CM | CAMBRIA HEIGHTS - Lower Level Renovation | 8 | ORIGINAL EQUIP & FURNISHING | 2013-04-21 | 2013-07-19 | 2016-04-10 | 2025-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122-CM | CAMBRIA HEIGHTS - Lower Level Renovation | 9 | SUBSTANTIAL COMPLETION | 2013-07-20 | 2013-09-17 | 2016-04-10 | 2025-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122-CM | CAMBRIA HEIGHTS - Lower Level Renovation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-09-18 | 2013-10-17 | 2016-04-10 | 2025-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122GL2 | GLENDALE LIBRARY RENOVATION | 1 | PROJECT START | 2010-03-24 | 2010-03-24 | 2010-03-24 | 2010-03-24
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122GL2 | GLENDALE LIBRARY RENOVATION | 2 | DESIGN START | 2011-12-06 | 2011-12-06 | 2011-12-06 | 2011-12-06
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122GL2 | GLENDALE LIBRARY RENOVATION | 3 | DESIGN COMPLETION | 2013-06-28 | 2013-06-28 | 2011-12-07 | 2014-03-10
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122GL2 | GLENDALE LIBRARY RENOVATION | 4 | CONSTRUCTION START | 2014-02-11 | 2014-02-11 | 2014-03-11 | 2018-03-10
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122GL2 | GLENDALE LIBRARY RENOVATION | 5 | CONSTRUCTION COMPLETION | 2015-02-16 | 2015-02-16 | 2018-03-08 | 2020-12-28
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122HO1 | Hollis Library - Building Infrastructure | 1 | PROJECT START | 2014-02-12 | 2014-02-12 | 2014-02-12 | 2014-02-12
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122HO1 | Hollis Library - Building Infrastructure | 2 | DESIGN START | 2015-01-31 | 2016-01-23 | 2015-01-31 | 2015-04-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122HO1 | Hollis Library - Building Infrastructure | 3 | DESIGN COMPLETION | 2016-01-24 | 2016-08-05 | 2015-04-15 | 2017-04-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122HO1 | Hollis Library - Building Infrastructure | 4 | CONSTRUCTION START | 2016-08-06 | 2018-02-11 | 2019-05-01 | 2020-07-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122HO1 | Hollis Library - Building Infrastructure | 5 | CONSTRUCTION COMPLETION | 2018-02-12 | 2018-02-12 | 2020-07-17 | 2022-12-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122NF4 | NORTH FOREST PARK - Renovation | 1 | PROJECT START | 2011-12-02 | 2011-12-02 | 2011-12-02 | 2011-12-02
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122NF4 | NORTH FOREST PARK - Renovation | 2 | DESIGN START | 2013-01-30 | 2013-01-30 | 2013-01-30 | 2013-01-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122NF4 | NORTH FOREST PARK - Renovation | 3 | DESIGN COMPLETION | 2014-07-10 | 2014-07-10 | 2014-07-10 | 2020-03-27
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122NF4 | NORTH FOREST PARK - Renovation | 4 | CONSTRUCTION START | 2014-09-26 | 2014-09-26 | 2014-09-26 | 2020-10-27
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122NF4 | NORTH FOREST PARK - Renovation | 5 | CONSTRUCTION COMPLETION | 2016-04-20 | 2016-04-20 | 2016-04-20 | 2024-01-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122-QW | QUEENS WEST BRANCH | 1 | DEVELOP SCOPE | 2010-07-01 | 2010-09-28 | 2010-02-01 | 2010-02-01
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122-QW | QUEENS WEST BRANCH | 2 | PRELIMINARY DESIGN | 2010-09-29 | 2011-01-26 | 2010-07-06 | 2010-07-06
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122-QW | QUEENS WEST BRANCH | 3 | FINAL DESIGN | 2011-01-27 | 2011-07-25 | 2013-03-30 | 2014-01-05
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122-QW | QUEENS WEST BRANCH | 4 | BID AWARD AND REGISTER CONTRCT | 2011-07-26 | 2011-10-23 | 2014-01-06 | 2015-02-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122-QW | QUEENS WEST BRANCH | 5 | CONSTRUCTION TO 25% | 2011-10-24 | 2012-02-20 | 2017-02-14 | 2021-08-31
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122-QW | QUEENS WEST BRANCH | 6 | CONSTRUCTION TO 50% | 2012-02-21 | 2012-06-19 | 2017-02-14 | 2021-08-31
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122-QW | QUEENS WEST BRANCH | 7 | CONSTRUCTION TO 75% | 2012-06-20 | 2012-10-17 | 2017-02-14 | 2021-08-31
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122-QW | QUEENS WEST BRANCH | 8 | ORIGINAL EQUIP & FURNISHING | 2012-10-18 | 2013-01-15 | 2017-02-14 | 2021-08-31
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122-QW | QUEENS WEST BRANCH | 9 | SUBSTANTIAL COMPLETION | 2013-01-16 | 2013-03-16 | 2017-02-14 | 2021-08-31
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122-QW | QUEENS WEST BRANCH | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-03-17 | 2013-04-15 | 2017-02-14 | 2021-08-31
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122RO2 | ROCHDALE VILLAGE - HVAC & Controls | 1 | DESIGN | 2010-10-01 | 2010-10-30 | 2011-01-31 | 2011-01-31
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122RO2 | ROCHDALE VILLAGE - HVAC & Controls | 2 | BID AWARD AND REGISTER CONTRCT | 2010-10-31 | 2011-01-28 | 2014-05-19 | 2014-05-20
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122RO2 | ROCHDALE VILLAGE - HVAC & Controls | 3 | CONSTRUCTION | 2011-01-29 | 2011-07-27 | 2014-10-23 | 2019-11-11
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122RO2 | ROCHDALE VILLAGE - HVAC & Controls | 4 | ORIGINAL EQUIP & FURNISHING | 2011-07-28 | 2011-10-25 | 2015-04-22 | 2020-03-20
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122RO2 | ROCHDALE VILLAGE - HVAC & Controls | 5 | SUBSTANTIAL COMPLETION | 2011-10-26 | 2011-11-24 | 2015-11-10 | 2020-11-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122RO2 | ROCHDALE VILLAGE - HVAC & Controls | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2011-11-25 | 2011-12-24 | 2015-11-10 | 2020-11-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122-S2 | STEINWAY - Phase II Renovation | 1 | PROJECT START | 2012-03-14 | 2012-03-14 | 2010-03-21 | 2010-03-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122-S2 | STEINWAY - Phase II Renovation | 2 | DESIGN START | 2013-04-19 | 2013-04-19 | 2013-04-19 | 2013-04-19
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122-S2 | STEINWAY - Phase II Renovation | 3 | DESIGN COMPLETION | 2014-08-12 | 2014-08-12 | 2014-08-12 | 2017-08-09
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122-S2 | STEINWAY - Phase II Renovation | 4 | CONSTRUCTION START | 2014-12-12 | 2014-12-12 | 2014-12-12 | 2018-06-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122-S2 | STEINWAY - Phase II Renovation | 5 | CONSTRUCTION COMPLETION | 2016-01-04 | 2016-01-04 | 2016-01-04 | 2020-12-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122-WN | WOODHAVEN - Renovation | 1 | DESIGN | 2010-10-01 | 2010-10-30 | 2014-02-14 | 2014-02-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122-WN | WOODHAVEN - Renovation | 2 | BID AWARD AND REGISTER CONTRCT | 2010-10-31 | 2011-01-28 | 2014-02-15 | 2015-06-22
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122-WN | WOODHAVEN - Renovation | 3 | CONSTRUCTION | 2011-01-29 | 2011-07-27 | 2015-06-23 | 2017-06-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122-WN | WOODHAVEN - Renovation | 4 | ORIGINAL EQUIP & FURNISHING | 2011-07-28 | 2011-10-25 | 2017-06-24 | 2019-12-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122-WN | WOODHAVEN - Renovation | 5 | SUBSTANTIAL COMPLETION | 2011-10-26 | 2011-11-24 | 2019-12-31 | 2022-12-31
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122-WN | WOODHAVEN - Renovation | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2011-11-25 | 2011-12-24 | 2019-12-31 | 2022-12-31
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122-WP | WINDSOR PARK - Renovation | 1 | PROJECT START | 2008-07-30 | 2008-07-30 | 2009-05-31 | 2009-05-31
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122-WP | WINDSOR PARK - Renovation | 2 | DESIGN START | 2008-07-31 | 2008-07-31 | 2009-05-31 | 2009-05-31
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122-WP | WINDSOR PARK - Renovation | 3 | DESIGN COMPLETION | 2008-08-01 | 2008-08-01 | 2009-06-01 | 2011-05-31
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122-WP | WINDSOR PARK - Renovation | 4 | CONSTRUCTION START | 2009-05-01 | 2009-05-01 | 2011-06-15 | 2014-06-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122-WP | WINDSOR PARK - Renovation | 5 | CONSTRUCTION COMPLETION | 2009-05-03 | 2021-06-20 | 2014-06-16 | 2027-06-20
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122WS3 | WOODSIDE - INTERIOR LIGHTING UPGRADE | 1 | PROJECT START | 2009-12-02 | 2009-12-02 | 2014-03-17 | 2014-03-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122WS3 | WOODSIDE - INTERIOR LIGHTING UPGRADE | 2 | DESIGN START | 2010-01-04 | 2010-01-31 | 2014-07-02 | 2014-07-03
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122WS3 | WOODSIDE - INTERIOR LIGHTING UPGRADE | 3 | DESIGN COMPLETION | 2010-02-01 | 2010-04-30 | 2014-07-04 | 2015-06-19
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122WS3 | WOODSIDE - INTERIOR LIGHTING UPGRADE | 4 | CONSTRUCTION START | 2010-05-01 | 2015-07-30 | 2017-06-20 | 2019-06-22
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122WS3 | WOODSIDE - INTERIOR LIGHTING UPGRADE | 5 | CONSTRUCTION COMPLETION | 2015-07-31 | 2015-07-31 | 2019-06-23 | 2021-01-13
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQDL-NEW | DOUGLASTON: Replacement Facility | 1 | DESIGN | 2019-01-01 | 2020-12-20 | 2019-01-01 | 2020-12-20
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQDL-NEW | DOUGLASTON: Replacement Facility | 2 | BID AWARD AND REGISTER CONTRCT | 2020-12-21 | 2021-12-15 | 2020-12-21 | 2021-12-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQDL-NEW | DOUGLASTON: Replacement Facility | 3 | CONSTRUCTION | 2021-12-16 | 2027-12-14 | 2021-12-16 | 2027-12-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQEM19BKP | BAISLEY PARK: AC Replacement | 1 | PROJECT START | 2018-07-10 | 2018-07-10 | 2018-07-10 | 2018-07-10
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQEM19BKP | BAISLEY PARK: AC Replacement | 2 | DESIGN START | 2018-07-11 | 2018-08-01 | 2018-07-11 | 2018-08-01
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQEM19BKP | BAISLEY PARK: AC Replacement | 3 | DESIGN COMPLETION | 2018-08-02 | 2018-09-10 | 2018-08-02 | 2018-09-10
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQEM19BKP | BAISLEY PARK: AC Replacement | 4 | CONSTRUCTION START | 2018-09-11 | 2018-10-02 | 2018-09-11 | 2018-10-02
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQEM19BKP | BAISLEY PARK: AC Replacement | 5 | CONSTRUCTION COMPLETION | 2018-10-03 | 2019-09-06 | 2018-10-03 | 2021-09-06
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQEM19BPK | BAISLEY PARK: New Boiler | 1 | DESIGN | 2019-01-01 | 2020-12-20 | 2019-01-01 | 2020-12-20
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQEM19BPK | BAISLEY PARK: New Boiler | 2 | BID AWARD AND REGISTER CONTRCT | 2020-12-21 | 2021-12-15 | 2020-12-21 | 2021-12-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQEM19BPK | BAISLEY PARK: New Boiler | 3 | CONSTRUCTION | 2021-12-16 | 2027-12-14 | 2021-12-16 | 2027-12-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQEM19FFA | FLUSHING: FIRE ALARM | 1 | DESIGN | 2020-01-01 | 2021-12-20 | 2020-01-01 | 2021-12-20
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQEM19FFA | FLUSHING: FIRE ALARM | 2 | BID AWARD AND REGISTER CONTRCT | 2021-12-21 | 2022-12-15 | 2021-12-21 | 2022-12-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQEM19FFA | FLUSHING: FIRE ALARM | 3 | CONSTRUCTION | 2022-12-16 | 2023-12-13 | 2022-12-16 | 2023-12-13
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQEM19FFA | FLUSHING: FIRE ALARM | 4 | PROJECT START | 2022-12-16 | 2023-12-13 | 2023-12-14 | 2023-12-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQEM19FFA | FLUSHING: FIRE ALARM | 5 | DESIGN START | 2022-12-16 | 2023-12-13 | 2023-12-15 | 2023-12-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQEM19FFA | FLUSHING: FIRE ALARM | 6 | DESIGN COMPLETION | 2022-12-16 | 2023-12-13 | 2023-12-16 | 2023-12-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQEM19FFA | FLUSHING: FIRE ALARM | 7 | CONSTRUCTION START | 2022-12-16 | 2023-12-13 | 2023-12-17 | 2023-12-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQEM19FFA | FLUSHING: FIRE ALARM | 8 | CONSTRUCTION COMPLETION | 2022-12-16 | 2023-12-13 | 2023-12-18 | 2025-12-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQEM19FLU | FLUSHING:Emergency Functionality | 1 | DESIGN | 2020-01-01 | 2021-12-20 | 2020-01-01 | 2021-12-20
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQEM19FLU | FLUSHING:Emergency Functionality | 2 | BID AWARD AND REGISTER CONTRCT | 2021-12-21 | 2022-12-15 | 2021-12-21 | 2022-12-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQEM19FLU | FLUSHING:Emergency Functionality | 3 | CONSTRUCTION | 2022-12-16 | 2023-12-13 | 2022-12-16 | 2023-12-13
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQEM19FLU | FLUSHING:Emergency Functionality | 4 | PROJECT START | 2022-12-16 | 2023-12-13 | 2023-12-14 | 2023-12-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQEM19FLU | FLUSHING:Emergency Functionality | 5 | DESIGN START | 2022-12-16 | 2023-12-13 | 2023-12-15 | 2023-12-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQEM19FLU | FLUSHING:Emergency Functionality | 6 | DESIGN COMPLETION | 2022-12-16 | 2023-12-13 | 2023-12-16 | 2023-12-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQEM19FLU | FLUSHING:Emergency Functionality | 7 | CONSTRUCTION START | 2022-12-16 | 2023-12-13 | 2023-12-17 | 2023-12-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQEM19FLU | FLUSHING:Emergency Functionality | 8 | CONSTRUCTION COMPLETION | 2022-12-16 | 2023-12-13 | 2023-12-18 | 2025-12-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQFLELV | FLUSHING LIBRARY - CONSTRUCTION OF SECOND ELEVATOR | 1 | PROJECT START | 2016-05-10 | 2016-05-10 | 2015-10-21 | 2015-10-22
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQFLELV | FLUSHING LIBRARY - CONSTRUCTION OF SECOND ELEVATOR | 2 | DESIGN START | 2016-05-11 | 2016-05-11 | 2015-10-23 | 2016-06-28
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQFLELV | FLUSHING LIBRARY - CONSTRUCTION OF SECOND ELEVATOR | 3 | DESIGN COMPLETION | 2016-05-12 | 2016-05-12 | 2016-06-29 | 2018-11-28
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQFLELV | FLUSHING LIBRARY - CONSTRUCTION OF SECOND ELEVATOR | 4 | CONSTRUCTION START | 2016-05-13 | 2016-05-13 | 2018-11-29 | 2020-02-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQFLELV | FLUSHING LIBRARY - CONSTRUCTION OF SECOND ELEVATOR | 5 | CONSTRUCTION COMPLETION | 2016-05-14 | 2019-12-28 | 2020-02-15 | 2023-09-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQHIHVAC | HILLCREST - HVAC | 1 | PROJECT START | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQHIHVAC | HILLCREST - HVAC | 2 | DESIGN START | 2016-04-15 | 2016-04-15 | 2016-04-15 | 2016-04-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQHIHVAC | HILLCREST - HVAC | 3 | DESIGN COMPLETION | 2016-04-16 | 2016-04-16 | 2016-04-16 | 2016-04-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQHIHVAC | HILLCREST - HVAC | 4 | CONSTRUCTION START | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQHIHVAC | HILLCREST - HVAC | 5 | CONSTRUCTION COMPLETION | 2016-04-18 | 2020-12-28 | 2016-04-18 | 2020-12-28
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQHIROOF | HILLCREST ROOF | 1 | PROJECT START | 2016-05-17 | 2016-05-17 | 2015-10-20 | 2015-10-20
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQHIROOF | HILLCREST ROOF | 2 | DESIGN START | 2016-05-18 | 2016-05-18 | 2015-10-21 | 2017-03-27
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQHIROOF | HILLCREST ROOF | 3 | DESIGN COMPLETION | 2016-05-19 | 2016-05-19 | 2017-03-28 | 2019-05-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQHIROOF | HILLCREST ROOF | 4 | CONSTRUCTION START | 2016-05-20 | 2016-05-20 | 2019-05-16 | 2020-02-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQHIROOF | HILLCREST ROOF | 5 | CONSTRUCTION COMPLETION | 2016-05-21 | 2019-12-28 | 2020-02-15 | 2023-09-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQLAROOF | LAURELTON ROOF | 1 | PROJECT START | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQLAROOF | LAURELTON ROOF | 2 | DESIGN START | 2016-04-15 | 2016-04-15 | 2016-04-15 | 2016-04-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQLAROOF | LAURELTON ROOF | 3 | DESIGN COMPLETION | 2016-04-16 | 2016-04-16 | 2016-04-16 | 2016-04-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQLAROOF | LAURELTON ROOF | 4 | CONSTRUCTION START | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQLAROOF | LAURELTON ROOF | 5 | CONSTRUCTION COMPLETION | 2016-04-18 | 2020-12-28 | 2016-04-18 | 2020-12-28
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQMA-BLR | MASPETH: New Boiler | 5 | CONSTRUCTION COMPLETION | 2017-07-28 | 2019-11-18 | 2017-07-28 | 2019-11-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQMVHVAC | MIDDLE VILLAGE - HVAC | 1 | PROJECT START | 2016-12-14 | 2016-12-14 | 2016-12-14 | 2016-12-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQMVHVAC | MIDDLE VILLAGE - HVAC | 2 | DESIGN START | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQMVHVAC | MIDDLE VILLAGE - HVAC | 3 | DESIGN COMPLETION | 2016-12-16 | 2016-12-16 | 2016-12-16 | 2016-12-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQMVHVAC | MIDDLE VILLAGE - HVAC | 4 | CONSTRUCTION START | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQMVHVAC | MIDDLE VILLAGE - HVAC | 5 | CONSTRUCTION COMPLETION | 2016-12-18 | 2021-12-28 | 2016-12-18 | 2021-12-28
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQOZROOF | OZONE PARK ROOF REPLACEMENT | 1 | PROJECT START | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQOZROOF | OZONE PARK ROOF REPLACEMENT | 2 | DESIGN START | 2016-07-23 | 2017-02-15 | 2016-07-23 | 2017-02-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQOZROOF | OZONE PARK ROOF REPLACEMENT | 3 | DESIGN COMPLETION | 2017-02-16 | 2018-07-16 | 2017-02-16 | 2018-07-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQOZROOF | OZONE PARK ROOF REPLACEMENT | 4 | CONSTRUCTION START | 2018-07-17 | 2019-01-14 | 2018-07-17 | 2019-01-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQOZROOF | OZONE PARK ROOF REPLACEMENT | 5 | CONSTRUCTION COMPLETION | 2019-01-15 | 2020-01-13 | 2019-01-15 | 2022-01-13
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQ122-BL | Masonry Repairs - Bellerose | 1 | PROJECT START | 2012-10-22 | 2012-10-22 | 2012-10-22 | 2012-10-22
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQ122-BL | Masonry Repairs - Bellerose | 2 | DESIGN START | 2013-11-26 | 2013-11-26 | 2013-11-26 | 2015-04-28
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQ122-BL | Masonry Repairs - Bellerose | 3 | DESIGN COMPLETION | 2014-11-14 | 2014-11-14 | 2014-11-14 | 2016-06-22
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQ122-BL | Masonry Repairs - Bellerose | 4 | CONSTRUCTION START | 2015-05-14 | 2015-05-14 | 2015-05-14 | 2017-10-24
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQ122-BL | Masonry Repairs - Bellerose | 5 | CONSTRUCTION COMPLETION | 2015-11-26 | 2015-11-26 | 2015-11-26 | 2022-11-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQ122-DL | MULTIBRANCH (C, DL, NO, RO, S &SZ) - Roof Replacements | 1 | DESIGN | 2010-09-01 | 2010-09-30 | 2012-06-05 | 2012-06-05
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQ122-DL | MULTIBRANCH (C, DL, NO, RO, S &SZ) - Roof Replacements | 2 | BID AWARD AND REGISTER CONTRCT | 2010-10-01 | 2010-12-29 | 2014-01-31 | 2014-01-31
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQ122-DL | MULTIBRANCH (C, DL, NO, RO, S &SZ) - Roof Replacements | 3 | CONSTRUCTION | 2010-12-30 | 2011-06-27 | 2014-09-11 | 2016-12-12
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQ122-DL | MULTIBRANCH (C, DL, NO, RO, S &SZ) - Roof Replacements | 4 | ORIGINAL EQUIP & FURNISHING | 2011-06-28 | 2011-09-25 | 2015-03-26 | 2017-07-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQ122-DL | MULTIBRANCH (C, DL, NO, RO, S &SZ) - Roof Replacements | 5 | SUBSTANTIAL COMPLETION | 2011-09-26 | 2011-10-25 | 2015-10-23 | 2021-12-28
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQ122-DL | MULTIBRANCH (C, DL, NO, RO, S &SZ) - Roof Replacements | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2011-10-26 | 2011-11-24 | 2015-10-23 | 2021-12-28
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQ122EE2 | EAST ELMHURST - Expansion | 1 | PROJECT START | 2010-01-07 | 2010-01-07 | 2010-01-07 | 2010-01-07
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQ122EE2 | EAST ELMHURST - Expansion | 2 | DESIGN START | 2010-10-20 | 2011-10-11 | 2010-01-20 | 2011-10-20
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQ122EE2 | EAST ELMHURST - Expansion | 3 | DESIGN COMPLETION | 2011-10-12 | 2012-02-24 | 2011-10-21 | 2014-07-08
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQ122EE2 | EAST ELMHURST - Expansion | 4 | CONSTRUCTION START | 2012-02-25 | 2013-07-17 | 2014-07-09 | 2015-08-03
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQ122EE2 | EAST ELMHURST - Expansion | 5 | CONSTRUCTION COMPLETION | 2013-07-18 | 2013-07-18 | 2015-08-04 | 2020-08-03
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQ122-FA | FAR ROCKAWAY - Replacement Facility | 1 | DEVELOP SCOPE | 2010-07-01 | 2010-09-28 | 2011-09-30 | 2011-09-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQ122-FA | FAR ROCKAWAY - Replacement Facility | 2 | PRELIMINARY DESIGN | 2010-09-29 | 2011-01-26 | 2012-01-10 | 2012-01-10
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQ122-FA | FAR ROCKAWAY - Replacement Facility | 3 | FINAL DESIGN | 2011-01-27 | 2011-07-25 | 2015-10-26 | 2017-10-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQ122-FA | FAR ROCKAWAY - Replacement Facility | 4 | BID AWARD AND REGISTER CONTRCT | 2011-07-26 | 2011-10-23 | 2017-10-24 | 2018-07-31
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQ122-FA | FAR ROCKAWAY - Replacement Facility | 5 | CONSTRUCTION TO 25% | 2011-10-24 | 2012-02-20 | 2018-08-01 | 2023-08-09
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQ122-FA | FAR ROCKAWAY - Replacement Facility | 6 | CONSTRUCTION TO 50% | 2012-02-21 | 2012-06-19 | 2018-08-01 | 2023-08-09
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQ122-FA | FAR ROCKAWAY - Replacement Facility | 7 | CONSTRUCTION TO 75% | 2012-06-20 | 2012-10-17 | 2018-08-01 | 2023-08-09
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQ122-FA | FAR ROCKAWAY - Replacement Facility | 8 | ORIGINAL EQUIP & FURNISHING | 2012-10-18 | 2013-01-15 | 2018-08-01 | 2023-08-09
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQ122-FA | FAR ROCKAWAY - Replacement Facility | 9 | SUBSTANTIAL COMPLETION | 2013-01-16 | 2013-03-16 | 2018-08-01 | 2023-08-09
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQ122-FA | FAR ROCKAWAY - Replacement Facility | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-03-17 | 2013-04-15 | 2018-08-01 | 2023-08-09
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQ122-R1 | RICHMOND HILL - Branch Renovation | 1 | DESIGN | 2010-10-01 | 2010-10-30 | 2012-03-08 | 2012-03-08
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQ122-R1 | RICHMOND HILL - Branch Renovation | 2 | BID AWARD AND REGISTER CONTRCT | 2010-10-31 | 2011-01-28 | 2012-03-09 | 2012-03-09
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQ122-R1 | RICHMOND HILL - Branch Renovation | 3 | CONSTRUCTION | 2011-01-29 | 2011-07-27 | 2012-03-10 | 2012-03-10
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQ122-R1 | RICHMOND HILL - Branch Renovation | 4 | ORIGINAL EQUIP & FURNISHING | 2011-07-28 | 2011-10-25 | 2012-03-11 | 2012-03-11
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQ122-R1 | RICHMOND HILL - Branch Renovation | 5 | SUBSTANTIAL COMPLETION | 2011-10-26 | 2011-11-24 | 2012-03-12 | 2023-12-28
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQ122-R1 | RICHMOND HILL - Branch Renovation | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2011-11-25 | 2011-12-24 | 2012-03-12 | 2023-12-28
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQ122-RG | REGO PARK LIBRARY - REPLACEMENT FACILITY | 1 | DEVELOP SCOPE | 2010-07-01 | 2010-09-28 | 2018-06-07 | 2019-04-09
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQ122-RG | REGO PARK LIBRARY - REPLACEMENT FACILITY | 2 | PRELIMINARY DESIGN | 2010-09-29 | 2011-01-26 | 2019-04-10 | 2019-07-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQ122-RG | REGO PARK LIBRARY - REPLACEMENT FACILITY | 3 | FINAL DESIGN | 2011-01-27 | 2011-07-25 | 2019-07-16 | 2021-02-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQ122-RG | REGO PARK LIBRARY - REPLACEMENT FACILITY | 4 | BID AWARD AND REGISTER CONTRCT | 2011-07-26 | 2011-10-23 | 2021-11-15 | 2024-11-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQ122-RG | REGO PARK LIBRARY - REPLACEMENT FACILITY | 5 | CONSTRUCTION TO 25% | 2011-10-24 | 2012-02-20 | 2024-11-16 | 2026-11-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQ122-RG | REGO PARK LIBRARY - REPLACEMENT FACILITY | 6 | CONSTRUCTION TO 50% | 2012-02-21 | 2012-06-19 | 2024-11-16 | 2026-11-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQ122-RG | REGO PARK LIBRARY - REPLACEMENT FACILITY | 7 | CONSTRUCTION TO 75% | 2012-06-20 | 2012-10-17 | 2024-11-16 | 2026-11-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQ122-RG | REGO PARK LIBRARY - REPLACEMENT FACILITY | 8 | ORIGINAL EQUIP & FURNISHING | 2012-10-18 | 2013-01-15 | 2024-11-16 | 2026-11-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQ122-RG | REGO PARK LIBRARY - REPLACEMENT FACILITY | 9 | SUBSTANTIAL COMPLETION | 2013-01-16 | 2013-03-16 | 2024-11-16 | 2026-11-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQ122-RG | REGO PARK LIBRARY - REPLACEMENT FACILITY | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-03-17 | 2013-04-15 | 2024-11-16 | 2026-11-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQBHHVAC | QUEENSBORO HILL - HVAC | 1 | PROJECT START | 2003-10-10 | 2003-10-10 | 2003-10-10 | 2003-10-10
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQBHHVAC | QUEENSBORO HILL - HVAC | 2 | DESIGN START | 2003-10-11 | 2003-10-11 | 2003-10-11 | 2003-10-11
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQBHHVAC | QUEENSBORO HILL - HVAC | 3 | DESIGN COMPLETION | 2003-10-12 | 2003-10-12 | 2003-10-12 | 2003-10-12
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQBHHVAC | QUEENSBORO HILL - HVAC | 4 | CONSTRUCTION START | 2003-10-13 | 2003-10-13 | 2003-10-13 | 2003-10-13
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQBHHVAC | QUEENSBORO HILL - HVAC | 5 | CONSTRUCTION COMPLETION | 2003-10-14 | 2020-12-27 | 2003-10-14 | 2020-12-27
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQVHVAC | QUEENS VILLAGE - HVAC | 1 | PROJECT START | 2016-12-14 | 2016-12-14 | 2016-12-14 | 2016-12-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQVHVAC | QUEENS VILLAGE - HVAC | 2 | DESIGN START | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQVHVAC | QUEENS VILLAGE - HVAC | 3 | DESIGN COMPLETION | 2016-12-16 | 2016-12-16 | 2016-12-16 | 2016-12-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQVHVAC | QUEENS VILLAGE - HVAC | 4 | CONSTRUCTION START | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQVHVAC | QUEENS VILLAGE - HVAC | 5 | CONSTRUCTION COMPLETION | 2016-12-18 | 2021-12-28 | 2016-12-18 | 2021-12-28
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQVROOF | QUEENS VILLAGE - ROOF | 1 | PROJECT START | 2016-12-14 | 2016-12-14 | 2016-12-14 | 2016-12-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQVROOF | QUEENS VILLAGE - ROOF | 2 | DESIGN START | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQVROOF | QUEENS VILLAGE - ROOF | 3 | DESIGN COMPLETION | 2016-12-16 | 2016-12-16 | 2016-12-16 | 2016-12-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQVROOF | QUEENS VILLAGE - ROOF | 4 | CONSTRUCTION START | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQVROOF | QUEENS VILLAGE - ROOF | 5 | CONSTRUCTION COMPLETION | 2021-12-28 | 2027-01-05 | 2021-12-28 | 2027-01-05
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQRDMASON | RIDGEWOOD - MASONRY | 1 | PROJECT START | 2016-12-14 | 2016-12-14 | 2016-12-14 | 2016-12-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQRDMASON | RIDGEWOOD - MASONRY | 2 | DESIGN START | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQRDMASON | RIDGEWOOD - MASONRY | 3 | DESIGN COMPLETION | 2016-12-16 | 2016-12-16 | 2016-12-16 | 2016-12-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQRDMASON | RIDGEWOOD - MASONRY | 4 | CONSTRUCTION START | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQRDMASON | RIDGEWOOD - MASONRY | 5 | CONSTRUCTION COMPLETION | 2016-12-18 | 2021-12-28 | 2016-12-18 | 2021-12-28
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQSARENOV | ST. ALBANS RENOVATION | 1 | PROJECT START | 2016-12-14 | 2016-12-14 | 2016-12-14 | 2016-12-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQSARENOV | ST. ALBANS RENOVATION | 2 | DESIGN START | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQSARENOV | ST. ALBANS RENOVATION | 3 | DESIGN COMPLETION | 2016-12-16 | 2016-12-16 | 2016-12-16 | 2016-12-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQSARENOV | ST. ALBANS RENOVATION | 4 | CONSTRUCTION START | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQSARENOV | ST. ALBANS RENOVATION | 5 | CONSTRUCTION COMPLETION | 2016-12-18 | 2021-12-28 | 2016-12-18 | 2023-12-28
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQSAROOF | ST. ALBANS ROOF REPLACEMENT | 1 | PROJECT START | 2015-01-21 | 2015-01-21 | 2015-01-21 | 2015-01-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQSAROOF | ST. ALBANS ROOF REPLACEMENT | 2 | DESIGN START | 2015-10-16 | 2016-07-04 | 2015-10-16 | 2015-12-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQSAROOF | ST. ALBANS ROOF REPLACEMENT | 3 | DESIGN COMPLETION | 2016-07-05 | 2016-11-26 | 2015-12-22 | 2017-06-02
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQSAROOF | ST. ALBANS ROOF REPLACEMENT | 4 | CONSTRUCTION START | 2016-11-27 | 2017-08-11 | 2017-06-03 | 2018-03-20
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQSAROOF | ST. ALBANS ROOF REPLACEMENT | 5 | CONSTRUCTION COMPLETION | 2017-08-12 | 2017-08-12 | 2018-03-21 | 2026-08-05
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQSEHVAC | SEASIDE -HVAC | 1 | PROJECT START | 2015-01-21 | 2015-01-21 | 2015-01-21 | 2015-01-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQSEHVAC | SEASIDE -HVAC | 2 | DESIGN START | 2015-01-22 | 2015-01-22 | 2015-01-22 | 2015-01-22
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQSEHVAC | SEASIDE -HVAC | 3 | DESIGN COMPLETION | 2015-01-23 | 2015-01-23 | 2015-01-23 | 2015-01-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQSEHVAC | SEASIDE -HVAC | 4 | CONSTRUCTION START | 2015-01-24 | 2015-01-24 | 2015-01-24 | 2015-01-24
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQSEHVAC | SEASIDE -HVAC | 5 | CONSTRUCTION COMPLETION | 2015-01-25 | 2021-12-28 | 2015-01-25 | 2021-12-28
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQSUADA | SUNNYSIDE ADA | 2 | DESIGN START | 2016-05-24 | 2016-05-24 | 2016-05-24 | 2016-05-24
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQSUADA | SUNNYSIDE ADA | 3 | DESIGN COMPLETION | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQSUADA | SUNNYSIDE ADA | 4 | CONSTRUCTION START | 2016-05-26 | 2016-05-26 | 2016-05-26 | 2016-05-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQSUADA | SUNNYSIDE ADA | 5 | CONSTRUCTION COMPLETION | 2016-05-27 | 2021-12-28 | 2016-05-27 | 2021-12-28
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQWSADA | WOODSIDE ADA | 1 | PROJECT START | 2016-05-23 | 2016-05-23 | 2016-05-23 | 2016-05-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQWSADA | WOODSIDE ADA | 2 | DESIGN START | 2016-05-24 | 2016-05-24 | 2016-05-24 | 2016-05-24
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQWSADA | WOODSIDE ADA | 3 | DESIGN COMPLETION | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQWSADA | WOODSIDE ADA | 4 | CONSTRUCTION START | 2016-05-26 | 2016-05-26 | 2016-05-26 | 2016-05-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQWSADA | WOODSIDE ADA | 5 | CONSTRUCTION COMPLETION | 2016-05-27 | 2021-12-28 | 2016-05-27 | 2026-12-28
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | P-407BHI3 | BOWNE HOUSE INTERIOR RESTORATIONS | 1 | PROJECT START | 2015-09-30 | 2015-09-30 | 2015-09-30 | 2015-09-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | P-407BHI3 | BOWNE HOUSE INTERIOR RESTORATIONS | 2 | DESIGN START | 2015-10-01 | 2015-10-01 | 2016-10-01 | 2016-10-02
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | P-407BHI3 | BOWNE HOUSE INTERIOR RESTORATIONS | 3 | DESIGN COMPLETION | 2015-10-02 | 2015-10-02 | 2016-10-03 | 2021-01-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | P-407BHI3 | BOWNE HOUSE INTERIOR RESTORATIONS | 4 | CONSTRUCTION START | 2015-10-03 | 2015-10-03 | 2018-06-01 | 2018-06-02
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | P-407BHI3 | BOWNE HOUSE INTERIOR RESTORATIONS | 5 | CONSTRUCTION COMPLETION | 2015-10-04 | 2017-10-04 | 2018-06-03 | 2022-01-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | P-407BHV4 | BOWNE HOUSE VISITORS CENTER Q022 | 1 | PROJECT START | 2016-01-30 | 2016-01-30 | 2019-11-01 | 2019-11-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | P-407BHV4 | BOWNE HOUSE VISITORS CENTER Q022 | 2 | DESIGN START | 2016-01-31 | 2016-02-01 | 2019-12-01 | 2019-12-02
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | P-407BHV4 | BOWNE HOUSE VISITORS CENTER Q022 | 3 | DESIGN COMPLETION | 2016-02-02 | 2016-06-30 | 2019-12-03 | 2022-04-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | P-407BHV4 | BOWNE HOUSE VISITORS CENTER Q022 | 4 | CONSTRUCTION START | 2016-07-01 | 2016-07-02 | 2022-05-01 | 2022-05-02
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | P-407BHV4 | BOWNE HOUSE VISITORS CENTER Q022 | 5 | CONSTRUCTION COMPLETION | 2016-07-03 | 2018-07-03 | 2022-05-03 | 2024-05-02
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | P-407KIN2 | Kingsland Homestead Roof/Floor Renovations | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2016-12-20 | 2017-03-19
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | P-407KIN2 | Kingsland Homestead Roof/Floor Renovations | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2017-03-20 | 2018-03-19
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | P-407KIN2 | Kingsland Homestead Roof/Floor Renovations | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2018-03-20 | 2022-12-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | P-4RCKGHQ | Rockaway Operational Headquarters, SANDY4-50 and Sandy4-11 | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | P-4RCKGHQ | Rockaway Operational Headquarters, SANDY4-50 and Sandy4-11 | 2 | DESIGN | 2019-12-28 | 2021-12-26 | 2019-12-28 | 2021-12-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | P-4RCKGHQ | Rockaway Operational Headquarters, SANDY4-50 and Sandy4-11 | 3 | BID/ REGISTER CONTRACT | 2021-12-27 | 2022-09-22 | 2021-12-27 | 2022-09-22
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | P-4RCKGHQ | Rockaway Operational Headquarters, SANDY4-50 and Sandy4-11 | 4 | CONSTRUCTION | 2022-09-23 | 2024-09-21 | 2022-09-23 | 2024-09-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | P-4RCKGHQ | Rockaway Operational Headquarters, SANDY4-50 and Sandy4-11 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-09-22 | 2025-09-21 | 2024-09-22 | 2025-09-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79BMAHW | 114TH PCT PLUMBING SYSTEM REPLACEMENT | 1 | DEVELOP SCOPE | 2014-06-30 | 2014-09-27 | 2014-06-30 | 2014-09-27
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79BMAHW | 114TH PCT PLUMBING SYSTEM REPLACEMENT | 2 | PRELIMINARY DESIGN | 2014-09-28 | 2015-01-25 | 2014-09-28 | 2015-01-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79BMAHW | 114TH PCT PLUMBING SYSTEM REPLACEMENT | 3 | FINAL DESIGN | 2015-01-26 | 2015-07-24 | 2015-01-26 | 2015-07-24
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79BMAHW | 114TH PCT PLUMBING SYSTEM REPLACEMENT | 4 | BID AWARD AND REGISTER CONTRCT | 2015-07-25 | 2015-10-22 | 2015-07-25 | 2015-10-22
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79BMAHW | 114TH PCT PLUMBING SYSTEM REPLACEMENT | 5 | CONSTRUCTION TO 25% | 2015-10-23 | 2016-02-19 | 2015-10-23 | 2016-02-19
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79BMAHW | 114TH PCT PLUMBING SYSTEM REPLACEMENT | 6 | CONSTRUCTION TO 50% | 2016-02-20 | 2016-06-18 | 2016-02-20 | 2016-06-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79BMAHW | 114TH PCT PLUMBING SYSTEM REPLACEMENT | 7 | CONSTRUCTION TO 75% | 2016-06-19 | 2016-10-16 | 2016-06-19 | 2016-10-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79BMAHW | 114TH PCT PLUMBING SYSTEM REPLACEMENT | 8 | ORIGINAL EQUIP & FURNISHING | 2016-10-17 | 2017-01-14 | 2016-10-17 | 2017-01-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79BMAHW | 114TH PCT PLUMBING SYSTEM REPLACEMENT | 9 | SUBSTANTIAL COMPLETION | 2017-01-15 | 2017-03-15 | 2017-01-15 | 2017-03-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79BMAHW | 114TH PCT PLUMBING SYSTEM REPLACEMENT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-16 | 2017-04-14 | 2017-03-16 | 2022-10-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV001SELM | LAH - Louis Armstrong House - Administration Facility | 1 | PROJECT START | 2015-06-15 | 2015-06-15 | 2015-09-11 | 2015-09-11
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV001SELM | LAH - Louis Armstrong House - Administration Facility | 2 | DESIGN START | 2015-06-16 | 2015-06-16 | 2015-09-12 | 2017-09-20
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV001SELM | LAH - Louis Armstrong House - Administration Facility | 3 | DESIGN COMPLETION | 2015-06-17 | 2015-06-17 | 2017-09-21 | 2018-12-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV001SELM | LAH - Louis Armstrong House - Administration Facility | 4 | CONSTRUCTION START | 2015-06-18 | 2015-06-18 | 2018-12-18 | 2020-01-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV001SELM | LAH - Louis Armstrong House - Administration Facility | 5 | CONSTRUCTION COMPLETION | 2015-06-19 | 2018-06-19 | 2020-01-17 | 2023-06-19
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV040ELEV | FTH - Flushing Town Hall Elevator Replacement | 1 | DEVELOP SCOPE | 2018-09-30 | 2019-06-30 | 2018-09-30 | 2019-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV040ELEV | FTH - Flushing Town Hall Elevator Replacement | 2 | PRELIMINARY DESIGN | 2019-07-01 | 2019-10-28 | 2019-07-01 | 2019-10-28
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV040ELEV | FTH - Flushing Town Hall Elevator Replacement | 3 | FINAL DESIGN | 2019-10-29 | 2020-04-25 | 2019-10-29 | 2020-04-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV040ELEV | FTH - Flushing Town Hall Elevator Replacement | 4 | BID AWARD AND REGISTER CONTRCT | 2020-04-26 | 2020-07-24 | 2020-04-26 | 2020-07-24
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV040ELEV | FTH - Flushing Town Hall Elevator Replacement | 5 | CONSTRUCTION TO 25% | 2020-07-25 | 2020-11-21 | 2020-07-25 | 2020-11-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV040ELEV | FTH - Flushing Town Hall Elevator Replacement | 6 | CONSTRUCTION TO 50% | 2020-11-22 | 2021-03-21 | 2020-11-22 | 2021-03-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV040ELEV | FTH - Flushing Town Hall Elevator Replacement | 7 | CONSTRUCTION TO 75% | 2021-03-22 | 2021-07-19 | 2021-03-22 | 2021-07-19
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV040ELEV | FTH - Flushing Town Hall Elevator Replacement | 8 | ORIGINAL EQUIP & FURNISHING | 2021-07-20 | 2021-10-17 | 2021-07-20 | 2021-10-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV040ELEV | FTH - Flushing Town Hall Elevator Replacement | 9 | SUBSTANTIAL COMPLETION | 2021-10-18 | 2021-12-16 | 2021-10-18 | 2021-12-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV040ELEV | FTH - Flushing Town Hall Elevator Replacement | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-12-17 | 2022-01-15 | 2021-12-17 | 2022-01-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV040HVAC | FTH - Flushing Town Hall HVAC System Replacement | 1 | DEVELOP SCOPE | 2018-09-30 | 2019-06-30 | 2018-09-30 | 2019-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV040HVAC | FTH - Flushing Town Hall HVAC System Replacement | 2 | PRELIMINARY DESIGN | 2019-07-01 | 2019-10-28 | 2019-07-01 | 2019-10-28
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV040HVAC | FTH - Flushing Town Hall HVAC System Replacement | 3 | FINAL DESIGN | 2019-10-29 | 2020-04-25 | 2019-10-29 | 2020-04-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV040HVAC | FTH - Flushing Town Hall HVAC System Replacement | 4 | BID AWARD AND REGISTER CONTRCT | 2020-04-26 | 2020-07-24 | 2020-04-26 | 2020-07-24
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV040HVAC | FTH - Flushing Town Hall HVAC System Replacement | 5 | CONSTRUCTION TO 25% | 2020-07-25 | 2020-11-21 | 2020-07-25 | 2020-11-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV040HVAC | FTH - Flushing Town Hall HVAC System Replacement | 6 | CONSTRUCTION TO 50% | 2020-11-22 | 2021-03-21 | 2020-11-22 | 2021-03-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV040HVAC | FTH - Flushing Town Hall HVAC System Replacement | 7 | CONSTRUCTION TO 75% | 2021-03-22 | 2021-07-19 | 2021-03-22 | 2021-07-19
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV040HVAC | FTH - Flushing Town Hall HVAC System Replacement | 8 | ORIGINAL EQUIP & FURNISHING | 2021-07-20 | 2021-10-17 | 2021-07-20 | 2021-10-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV040HVAC | FTH - Flushing Town Hall HVAC System Replacement | 9 | SUBSTANTIAL COMPLETION | 2021-10-18 | 2021-12-16 | 2021-10-18 | 2021-12-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV040HVAC | FTH - Flushing Town Hall HVAC System Replacement | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-12-17 | 2022-01-15 | 2021-12-17 | 2023-09-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV040HVAC | FTH - Flushing Town Hall HVAC System Replacement | 11 | PROJECT START | 2021-12-17 | 2022-01-15 | 2023-10-01 | 2023-10-01
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV040HVAC | FTH - Flushing Town Hall HVAC System Replacement | 12 | DESIGN START | 2021-12-17 | 2022-01-15 | 2023-10-02 | 2023-10-02
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV040HVAC | FTH - Flushing Town Hall HVAC System Replacement | 13 | DESIGN COMPLETION | 2021-12-17 | 2022-01-15 | 2023-10-03 | 2023-10-03
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV040HVAC | FTH - Flushing Town Hall HVAC System Replacement | 14 | CONSTRUCTION START | 2021-12-17 | 2022-01-15 | 2023-10-04 | 2023-10-04
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV040HVAC | FTH - Flushing Town Hall HVAC System Replacement | 15 | CONSTRUCTION COMPLETION | 2021-12-17 | 2022-01-15 | 2023-10-05 | 2023-10-05
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV272EDUC | QBG - Queens Botanical Garden Educ Bldg Renovation | 1 | DEVELOP SCOPE | 2014-06-30 | 2014-09-27 | 2014-06-30 | 2014-09-27
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV272EDUC | QBG - Queens Botanical Garden Educ Bldg Renovation | 2 | PRELIMINARY DESIGN | 2014-09-28 | 2015-01-25 | 2014-09-28 | 2015-01-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV272EDUC | QBG - Queens Botanical Garden Educ Bldg Renovation | 3 | FINAL DESIGN | 2015-01-26 | 2015-07-24 | 2015-01-26 | 2015-07-24
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV272EDUC | QBG - Queens Botanical Garden Educ Bldg Renovation | 4 | BID AWARD AND REGISTER CONTRCT | 2015-07-25 | 2015-10-22 | 2015-07-25 | 2015-10-22
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV272EDUC | QBG - Queens Botanical Garden Educ Bldg Renovation | 5 | CONSTRUCTION TO 25% | 2015-10-23 | 2016-02-19 | 2015-10-23 | 2016-02-19
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV272EDUC | QBG - Queens Botanical Garden Educ Bldg Renovation | 6 | CONSTRUCTION TO 50% | 2016-02-20 | 2016-06-18 | 2016-02-20 | 2016-06-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV272EDUC | QBG - Queens Botanical Garden Educ Bldg Renovation | 7 | CONSTRUCTION TO 75% | 2016-06-19 | 2016-10-16 | 2021-02-21 | 2021-06-20
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV272EDUC | QBG - Queens Botanical Garden Educ Bldg Renovation | 8 | ORIGINAL EQUIP & FURNISHING | 2015-04-21 | 2015-07-19 | 2015-04-21 | 2015-07-19
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV272EDUC | QBG - Queens Botanical Garden Educ Bldg Renovation | 9 | SUBSTANTIAL COMPLETION | 2015-07-20 | 2015-09-17 | 2015-07-20 | 2015-09-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV272EDUC | QBG - Queens Botanical Garden Educ Bldg Renovation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-05-03 | 2021-06-01 | 2021-05-03 | 2022-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV272SITE | QBG - Site-wide Exterior Improvements | 1 | DEVELOP SCOPE | 2016-04-30 | 2016-07-28 | 2016-04-30 | 2016-07-28
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV272SITE | QBG - Site-wide Exterior Improvements | 2 | PRELIMINARY DESIGN | 2016-07-29 | 2016-11-25 | 2016-07-29 | 2016-11-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV272SITE | QBG - Site-wide Exterior Improvements | 3 | FINAL DESIGN | 2016-11-26 | 2017-05-24 | 2016-11-26 | 2017-05-24
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV272SITE | QBG - Site-wide Exterior Improvements | 4 | BID AWARD AND REGISTER CONTRCT | 2017-05-25 | 2017-08-22 | 2017-05-25 | 2017-08-22
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV272SITE | QBG - Site-wide Exterior Improvements | 5 | CONSTRUCTION TO 25% | 2017-08-23 | 2017-12-20 | 2017-08-23 | 2017-12-20
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV272SITE | QBG - Site-wide Exterior Improvements | 6 | CONSTRUCTION TO 50% | 2017-12-21 | 2018-04-19 | 2017-12-21 | 2018-04-19
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV272SITE | QBG - Site-wide Exterior Improvements | 7 | CONSTRUCTION TO 75% | 2018-04-20 | 2018-08-17 | 2018-04-20 | 2018-08-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV272SITE | QBG - Site-wide Exterior Improvements | 8 | ORIGINAL EQUIP & FURNISHING | 2018-08-18 | 2018-11-15 | 2018-08-18 | 2018-11-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV272SITE | QBG - Site-wide Exterior Improvements | 9 | SUBSTANTIAL COMPLETION | 2018-11-16 | 2019-01-14 | 2018-11-16 | 2019-01-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV272SITE | QBG - Site-wide Exterior Improvements | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-01-15 | 2019-02-13 | 2019-01-15 | 2019-02-13
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV272SITE | QBG - Site-wide Exterior Improvements | 11 | PROJECT START | 2019-01-15 | 2019-02-13 | 2019-02-14 | 2019-02-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV272SITE | QBG - Site-wide Exterior Improvements | 12 | DESIGN START | 2019-01-15 | 2019-02-13 | 2019-02-15 | 2019-02-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV272SITE | QBG - Site-wide Exterior Improvements | 13 | DESIGN COMPLETION | 2019-01-15 | 2019-02-13 | 2019-02-16 | 2019-02-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV272SITE | QBG - Site-wide Exterior Improvements | 14 | CONSTRUCTION START | 2019-01-15 | 2019-02-13 | 2019-02-17 | 2019-02-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV272SITE | QBG - Site-wide Exterior Improvements | 15 | CONSTRUCTION COMPLETION | 2019-01-15 | 2019-02-13 | 2019-02-18 | 2022-07-01
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV274CHLL | NYHOS - New York Hall of Science - Chiller Replacement | 1 | PROJECT START | 2016-06-30 | 2016-09-27 | 2018-01-18 | 2018-04-20
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV274CHLL | NYHOS - New York Hall of Science - Chiller Replacement | 2 | DESIGN START | 2016-09-28 | 2017-01-25 | 2018-04-21 | 2019-02-13
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV274CHLL | NYHOS - New York Hall of Science - Chiller Replacement | 3 | DESIGN COMPLETION | 2017-01-26 | 2017-07-24 | 2019-02-14 | 2020-09-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV274CHLL | NYHOS - New York Hall of Science - Chiller Replacement | 4 | CONSTRUCTION START | 2017-07-25 | 2017-10-22 | 2020-09-16 | 2021-10-02
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV274CHLL | NYHOS - New York Hall of Science - Chiller Replacement | 5 | CONSTRUCTION COMPLETION | 2017-10-23 | 2018-02-19 | 2021-10-03 | 2023-09-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV274CHLL | NYHOS - New York Hall of Science - Chiller Replacement | 6 | CONSTRUCTION TO 50% | 2018-02-20 | 2018-06-19 | 2021-10-03 | 2023-09-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV274CHLL | NYHOS - New York Hall of Science - Chiller Replacement | 7 | CONSTRUCTION TO 75% | 2018-06-20 | 2018-10-17 | 2021-10-03 | 2023-09-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV274CHLL | NYHOS - New York Hall of Science - Chiller Replacement | 8 | ORIGINAL EQUIP & FURNISHING | 2018-10-18 | 2019-01-15 | 2021-10-03 | 2023-09-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV274CHLL | NYHOS - New York Hall of Science - Chiller Replacement | 9 | SUBSTANTIAL COMPLETION | 2019-01-16 | 2019-03-16 | 2021-10-03 | 2023-09-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV274CHLL | NYHOS - New York Hall of Science - Chiller Replacement | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-03-17 | 2019-04-15 | 2021-10-03 | 2023-09-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV274EXLT | NYHOS - NY Hall of Science Lighting for Outdoor Exhibits | 1 | PROJECT START | 2010-03-20 | 2010-03-20 | 2007-07-01 | 2009-03-20
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV274EXLT | NYHOS - NY Hall of Science Lighting for Outdoor Exhibits | 2 | DESIGN START | 2010-03-21 | 2010-03-21 | 2009-03-21 | 2009-06-20
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV274EXLT | NYHOS - NY Hall of Science Lighting for Outdoor Exhibits | 3 | DESIGN COMPLETION | 2010-03-22 | 2010-03-22 | 2011-06-21 | 2013-07-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV274EXLT | NYHOS - NY Hall of Science Lighting for Outdoor Exhibits | 4 | CONSTRUCTION START | 2010-03-23 | 2010-03-23 | 2013-07-16 | 2014-01-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV274EXLT | NYHOS - NY Hall of Science Lighting for Outdoor Exhibits | 5 | CONSTRUCTION COMPLETION | 2010-03-24 | 2010-03-24 | 2014-01-16 | 2023-07-05
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV274GHIN | NYHOS - NY HALL OF SCIENCE - Great Hall Int. Systems Recon. | 1 | DEVELOP SCOPE | 2009-06-30 | 2009-09-27 | 2007-10-16 | 2007-10-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV274GHIN | NYHOS - NY HALL OF SCIENCE - Great Hall Int. Systems Recon. | 2 | PRELIMINARY DESIGN | 2009-09-28 | 2010-01-25 | 2007-10-17 | 2008-08-27
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV274GHIN | NYHOS - NY HALL OF SCIENCE - Great Hall Int. Systems Recon. | 3 | FINAL DESIGN | 2010-01-26 | 2010-07-24 | 2008-08-28 | 2010-07-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV274GHIN | NYHOS - NY HALL OF SCIENCE - Great Hall Int. Systems Recon. | 4 | BID AWARD AND REGISTER CONTRCT | 2010-07-25 | 2010-10-22 | 2010-07-31 | 2012-08-09
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV274GHIN | NYHOS - NY HALL OF SCIENCE - Great Hall Int. Systems Recon. | 5 | CONSTRUCTION TO 25% | 2010-10-23 | 2011-02-19 | 2012-08-10 | 2022-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV274GHIN | NYHOS - NY HALL OF SCIENCE - Great Hall Int. Systems Recon. | 6 | CONSTRUCTION TO 50% | 2011-02-20 | 2011-06-19 | 2012-08-10 | 2022-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV274GHIN | NYHOS - NY HALL OF SCIENCE - Great Hall Int. Systems Recon. | 7 | CONSTRUCTION TO 75% | 2011-06-20 | 2011-10-17 | 2012-08-10 | 2022-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV274GHIN | NYHOS - NY HALL OF SCIENCE - Great Hall Int. Systems Recon. | 8 | ORIGINAL EQUIP & FURNISHING | 2011-10-18 | 2012-01-15 | 2012-08-10 | 2022-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV274GHIN | NYHOS - NY HALL OF SCIENCE - Great Hall Int. Systems Recon. | 9 | SUBSTANTIAL COMPLETION | 2012-01-16 | 2012-03-15 | 2012-08-10 | 2022-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV274GHIN | NYHOS - NY HALL OF SCIENCE - Great Hall Int. Systems Recon. | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-03-16 | 2012-04-14 | 2012-08-10 | 2022-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV274KITR | NYHOS - NY Hall of Science,Great Hall, Kitchen & Restroom | 1 | DEVELOP SCOPE | 2016-06-30 | 2016-09-27 | 2016-07-07 | 2016-07-07
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV274KITR | NYHOS - NY Hall of Science,Great Hall, Kitchen & Restroom | 2 | PRELIMINARY DESIGN | 2016-09-28 | 2017-01-25 | 2016-07-07 | 2016-07-07
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV274KITR | NYHOS - NY Hall of Science,Great Hall, Kitchen & Restroom | 3 | FINAL DESIGN | 2017-01-26 | 2017-07-24 | 2016-07-08 | 2019-02-01
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV274KITR | NYHOS - NY Hall of Science,Great Hall, Kitchen & Restroom | 4 | BID AWARD AND REGISTER CONTRCT | 2017-07-25 | 2017-10-22 | 2019-02-02 | 2019-08-28
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV274KITR | NYHOS - NY Hall of Science,Great Hall, Kitchen & Restroom | 5 | CONSTRUCTION TO 25% | 2017-10-23 | 2018-02-19 | 2019-08-29 | 2020-10-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV274KITR | NYHOS - NY Hall of Science,Great Hall, Kitchen & Restroom | 6 | CONSTRUCTION TO 50% | 2018-02-20 | 2018-06-19 | 2019-08-29 | 2020-10-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV274KITR | NYHOS - NY Hall of Science,Great Hall, Kitchen & Restroom | 7 | CONSTRUCTION TO 75% | 2018-06-20 | 2018-10-17 | 2019-08-29 | 2020-10-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV274KITR | NYHOS - NY Hall of Science,Great Hall, Kitchen & Restroom | 8 | ORIGINAL EQUIP & FURNISHING | 2018-10-18 | 2019-01-15 | 2019-08-29 | 2020-10-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV274KITR | NYHOS - NY Hall of Science,Great Hall, Kitchen & Restroom | 9 | SUBSTANTIAL COMPLETION | 2019-01-16 | 2019-03-16 | 2019-08-29 | 2020-10-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV274KITR | NYHOS - NY Hall of Science,Great Hall, Kitchen & Restroom | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-03-17 | 2019-04-15 | 2019-08-29 | 2020-10-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV291-QM2 | QMA - Queen's Museum of Art Expansion Phase II | 1 | CONSTRUCTION | 2013-09-29 | 2014-09-23 | 2018-03-22 | 2018-03-22
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV291-QM2 | QMA - Queen's Museum of Art Expansion Phase II | 2 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-09-24 | 2015-09-18 | 2018-03-23 | 2019-09-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV291-QM2 | QMA - Queen's Museum of Art Expansion Phase II | 3 | DESIGN COMPLETION | 2014-09-24 | 2015-09-18 | 2019-09-24 | 2021-01-22
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV291-QM2 | QMA - Queen's Museum of Art Expansion Phase II | 4 | CONSTRUCTION START | 2014-09-24 | 2015-09-18 | 2021-01-23 | 2022-02-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV291-QM2 | QMA - Queen's Museum of Art Expansion Phase II | 5 | CONSTRUCTION COMPLETION | 2014-09-24 | 2015-09-18 | 2022-02-26 | 2023-04-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV291-QMX | QMA - Queens Museum of Art Expansion | 1 | PROJECT START | 2002-01-01 | 2003-07-16 | 2005-02-17 | 2005-02-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV291-QMX | QMA - Queens Museum of Art Expansion | 2 | DESIGN START | 2003-07-17 | 2005-07-20 | 2005-02-18 | 2005-07-20
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV291-QMX | QMA - Queens Museum of Art Expansion | 3 | DESIGN COMPLETION | 2005-07-21 | 2007-09-04 | 2005-07-21 | 2007-11-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV291-QMX | QMA - Queens Museum of Art Expansion | 4 | CONSTRUCTION START | 2007-09-05 | 2008-04-11 | 2007-12-01 | 2009-07-27
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV291-QMX | QMA - Queens Museum of Art Expansion | 5 | CONSTRUCTION COMPLETION | 2008-04-12 | 2009-12-17 | 2009-07-28 | 2022-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV466CRLB | QTIP - Queens Theater in the Park, Circular Lobby Renovation | 2 | DESIGN START | 2009-07-23 | 2010-02-18 | 2009-07-23 | 2010-09-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV466CRLB | QTIP - Queens Theater in the Park, Circular Lobby Renovation | 3 | DESIGN COMPLETION | 2010-02-19 | 2010-08-23 | 2010-09-24 | 2012-06-24
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV466CRLB | QTIP - Queens Theater in the Park, Circular Lobby Renovation | 4 | CONSTRUCTION START | 2010-08-24 | 2010-12-23 | 2012-06-25 | 2015-03-20
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV466CRLB | QTIP - Queens Theater in the Park, Circular Lobby Renovation | 5 | CONSTRUCTION COMPLETION | 2010-12-24 | 2011-08-25 | 2015-03-21 | 2016-09-20
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV501BOIL | PS1 - PS1 Boiler Replacement | 1 | DEVELOP SCOPE | 2015-12-15 | 2016-03-13 | 2016-01-10 | 2016-01-10
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV501BOIL | PS1 - PS1 Boiler Replacement | 2 | PRELIMINARY DESIGN | 2016-03-14 | 2016-07-11 | 2016-01-10 | 2016-01-10
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV501BOIL | PS1 - PS1 Boiler Replacement | 3 | FINAL DESIGN | 2016-07-12 | 2017-01-07 | 2016-01-10 | 2016-01-10
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV501BOIL | PS1 - PS1 Boiler Replacement | 4 | BID AWARD AND REGISTER CONTRCT | 2017-01-08 | 2017-04-07 | 2016-01-10 | 2016-01-10
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV501BOIL | PS1 - PS1 Boiler Replacement | 5 | CONSTRUCTION TO 25% | 2017-04-08 | 2017-08-05 | 2016-01-10 | 2016-01-10
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV501BOIL | PS1 - PS1 Boiler Replacement | 6 | CONSTRUCTION TO 50% | 2017-08-06 | 2017-12-03 | 2016-01-10 | 2016-01-10
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV501BOIL | PS1 - PS1 Boiler Replacement | 7 | CONSTRUCTION TO 75% | 2017-12-04 | 2018-04-02 | 2016-01-10 | 2016-01-10
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV501BOIL | PS1 - PS1 Boiler Replacement | 8 | ORIGINAL EQUIP & FURNISHING | 2018-04-03 | 2018-07-01 | 2016-01-10 | 2016-01-10
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV501BOIL | PS1 - PS1 Boiler Replacement | 9 | SUBSTANTIAL COMPLETION | 2018-07-02 | 2018-08-30 | 2016-01-10 | 2016-01-10
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV501BOIL | PS1 - PS1 Boiler Replacement | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-08-31 | 2018-09-29 | 2016-01-10 | 2016-01-10
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV501BOIL | PS1 - PS1 Boiler Replacement | 11 | PROJECT START | 2018-08-31 | 2018-09-29 | 2016-01-10 | 2016-01-10
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV501BOIL | PS1 - PS1 Boiler Replacement | 12 | DESIGN START | 2018-08-31 | 2018-09-29 | 2016-01-11 | 2017-09-13
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV501BOIL | PS1 - PS1 Boiler Replacement | 13 | DESIGN COMPLETION | 2018-08-31 | 2018-09-29 | 2017-09-14 | 2019-05-24
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV501BOIL | PS1 - PS1 Boiler Replacement | 14 | CONSTRUCTION START | 2018-08-31 | 2018-09-29 | 2019-05-25 | 2020-05-27
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV501BOIL | PS1 - PS1 Boiler Replacement | 15 | CONSTRUCTION COMPLETION | 2018-08-31 | 2018-09-29 | 2020-05-28 | 2022-05-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV655QCFM | QCFM - Queen's County Farm Museum Greenhouse Restoration | 2 | DESIGN START | 2011-09-28 | 2012-06-18 | 2011-09-28 | 2012-06-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV655QCFM | QCFM - Queen's County Farm Museum Greenhouse Restoration | 3 | DESIGN COMPLETION | 2012-06-19 | 2014-06-25 | 2012-06-19 | 2014-06-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV655QCFM | QCFM - Queen's County Farm Museum Greenhouse Restoration | 4 | CONSTRUCTION START | 2014-06-26 | 2015-10-28 | 2014-06-26 | 2015-10-28
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV655QCFM | QCFM - Queen's County Farm Museum Greenhouse Restoration | 5 | CONSTRUCTION COMPLETION | 2015-10-29 | 2019-06-30 | 2015-10-29 | 2019-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PW293QBLV | 120-55 QUEENS BLVD - FIRE ALARM | 1 | PROJECT START | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PW293QBLV | 120-55 QUEENS BLVD - FIRE ALARM | 2 | DESIGN START | 2016-07-01 | 2016-12-30 | 2016-07-01 | 2016-12-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PW293QBLV | 120-55 QUEENS BLVD - FIRE ALARM | 3 | DESIGN COMPLETION | 2016-12-31 | 2017-09-30 | 2016-12-31 | 2017-09-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PW293QBLV | 120-55 QUEENS BLVD - FIRE ALARM | 4 | CONSTRUCTION START | 2017-10-01 | 2018-03-30 | 2017-10-01 | 2018-03-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PW293QBLV | 120-55 QUEENS BLVD - FIRE ALARM | 5 | CONSTRUCTION COMPLETION | 2018-03-31 | 2023-03-31 | 2018-03-31 | 2023-03-31
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77417DA | 120-55 QUEENS BLVD.- QUEENS DA TRAINING ROOM | 1 | PROJECT START | 2013-04-12 | 2013-04-12 | 2013-04-12 | 2013-04-12
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77417DA | 120-55 QUEENS BLVD.- QUEENS DA TRAINING ROOM | 2 | DESIGN START | 2014-03-24 | 2014-03-24 | 2013-04-11 | 2014-04-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77417DA | 120-55 QUEENS BLVD.- QUEENS DA TRAINING ROOM | 3 | DESIGN COMPLETION | 2015-02-15 | 2015-02-15 | 2015-04-22 | 2018-01-05
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77417DA | 120-55 QUEENS BLVD.- QUEENS DA TRAINING ROOM | 4 | CONSTRUCTION START | 2015-06-16 | 2015-08-13 | 2018-01-06 | 2019-05-31
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77417DA | 120-55 QUEENS BLVD.- QUEENS DA TRAINING ROOM | 5 | CONSTRUCTION COMPLETION | 2015-12-14 | 2016-04-11 | 2019-06-01 | 2023-05-03
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77417P2 | 120-55 QUEENS BLVD - PLAZA, STEPS AND ENTRANCE | 1 | PROJECT START | 2016-05-13 | 2016-05-13 | 2016-05-13 | 2016-05-13
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77417P2 | 120-55 QUEENS BLVD - PLAZA, STEPS AND ENTRANCE | 2 | DESIGN START | 2016-10-17 | 2016-10-18 | 2016-10-17 | 2016-10-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77417P2 | 120-55 QUEENS BLVD - PLAZA, STEPS AND ENTRANCE | 3 | DESIGN COMPLETION | 2016-10-19 | 2017-10-19 | 2016-10-19 | 2017-10-19
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77417P2 | 120-55 QUEENS BLVD - PLAZA, STEPS AND ENTRANCE | 4 | CONSTRUCTION START | 2017-10-20 | 2017-10-20 | 2017-10-20 | 2017-10-20
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77417P2 | 120-55 QUEENS BLVD - PLAZA, STEPS AND ENTRANCE | 5 | CONSTRUCTION COMPLETION | 2017-10-21 | 2019-10-20 | 2017-10-21 | 2021-07-01
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77ELEV | 120-55 QUEENS BLVD. ELEVATOR MODERNIZATION | 1 | DEVELOP SCOPE | 2017-01-01 | 2017-03-31 | 2020-01-05 | 2020-01-05
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77ELEV | 120-55 QUEENS BLVD. ELEVATOR MODERNIZATION | 2 | PRELIMINARY DESIGN | 2017-04-01 | 2017-07-29 | 2020-01-05 | 2020-01-05
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77ELEV | 120-55 QUEENS BLVD. ELEVATOR MODERNIZATION | 3 | FINAL DESIGN | 2017-07-30 | 2018-01-25 | 2020-01-05 | 2020-01-05
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77ELEV | 120-55 QUEENS BLVD. ELEVATOR MODERNIZATION | 4 | BID AWARD AND REGISTER CONTRCT | 2018-01-26 | 2018-04-25 | 2020-01-05 | 2020-01-05
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77ELEV | 120-55 QUEENS BLVD. ELEVATOR MODERNIZATION | 5 | CONSTRUCTION TO 25% | 2018-04-26 | 2018-08-23 | 2020-01-05 | 2020-01-05
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77ELEV | 120-55 QUEENS BLVD. ELEVATOR MODERNIZATION | 6 | CONSTRUCTION TO 50% | 2018-08-24 | 2018-12-21 | 2020-01-05 | 2020-01-05
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77ELEV | 120-55 QUEENS BLVD. ELEVATOR MODERNIZATION | 7 | CONSTRUCTION TO 75% | 2018-12-22 | 2019-04-20 | 2020-01-05 | 2020-01-05
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77ELEV | 120-55 QUEENS BLVD. ELEVATOR MODERNIZATION | 8 | ORIGINAL EQUIP & FURNISHING | 2019-04-21 | 2019-07-19 | 2020-01-05 | 2020-01-05
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77ELEV | 120-55 QUEENS BLVD. ELEVATOR MODERNIZATION | 9 | SUBSTANTIAL COMPLETION | 2019-07-20 | 2019-09-17 | 2020-01-05 | 2020-01-05
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77ELEV | 120-55 QUEENS BLVD. ELEVATOR MODERNIZATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-18 | 2019-10-17 | 2020-01-05 | 2020-01-05
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77ELEV | 120-55 QUEENS BLVD. ELEVATOR MODERNIZATION | 11 | PROJECT START | 2019-09-18 | 2019-10-17 | 2020-01-05 | 2020-01-05
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77ELEV | 120-55 QUEENS BLVD. ELEVATOR MODERNIZATION | 12 | DESIGN START | 2019-09-18 | 2019-10-17 | 2020-01-06 | 2020-09-05
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77ELEV | 120-55 QUEENS BLVD. ELEVATOR MODERNIZATION | 13 | DESIGN COMPLETION | 2019-09-18 | 2019-10-17 | 2020-09-06 | 2021-09-06
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77ELEV | 120-55 QUEENS BLVD. ELEVATOR MODERNIZATION | 14 | CONSTRUCTION START | 2019-09-18 | 2019-10-17 | 2021-09-07 | 2022-09-07
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77ELEV | 120-55 QUEENS BLVD. ELEVATOR MODERNIZATION | 15 | CONSTRUCTION COMPLETION | 2019-09-18 | 2019-10-17 | 2022-09-08 | 2023-09-08
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PWD99WNY1 | CENTER FOR THE WOMEN OF NEW YORK | 1 | DEVELOP SCOPE | 2008-07-01 | 2008-09-28 | 2017-05-15 | 2017-05-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PWD99WNY1 | CENTER FOR THE WOMEN OF NEW YORK | 2 | PRELIMINARY DESIGN | 2008-09-29 | 2009-01-26 | 2017-05-16 | 2017-11-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PWD99WNY1 | CENTER FOR THE WOMEN OF NEW YORK | 3 | FINAL DESIGN | 2009-01-27 | 2009-07-25 | 2018-05-15 | 2018-12-31
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PWD99WNY1 | CENTER FOR THE WOMEN OF NEW YORK | 4 | BID AWARD AND REGISTER CONTRCT | 2009-07-26 | 2009-10-23 | 2019-07-03 | 2020-07-03
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PWD99WNY1 | CENTER FOR THE WOMEN OF NEW YORK | 5 | CONSTRUCTION TO 25% | 2009-10-24 | 2010-02-20 | 2021-09-15 | 2022-08-31
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PWD99WNY1 | CENTER FOR THE WOMEN OF NEW YORK | 6 | CONSTRUCTION TO 50% | 2010-02-21 | 2010-06-20 | 2021-09-15 | 2022-08-31
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PWD99WNY1 | CENTER FOR THE WOMEN OF NEW YORK | 7 | CONSTRUCTION TO 75% | 2010-06-21 | 2010-10-18 | 2021-09-15 | 2022-08-31
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PWD99WNY1 | CENTER FOR THE WOMEN OF NEW YORK | 8 | ORIGINAL EQUIP & FURNISHING | 2010-10-19 | 2011-01-16 | 2021-09-15 | 2022-08-31
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PWD99WNY1 | CENTER FOR THE WOMEN OF NEW YORK | 9 | SUBSTANTIAL COMPLETION | 2011-01-17 | 2011-03-17 | 2021-09-15 | 2022-08-31
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PWD99WNY1 | CENTER FOR THE WOMEN OF NEW YORK | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2011-03-18 | 2011-04-16 | 2021-09-15 | 2022-08-31
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PWQ077AT2 | 120-55 QUEENS BLVD- QUEENS BOROUGH HALL ATRIUM | 1 | PROJECT START | 2012-06-01 | 2012-06-01 | 2012-02-01 | 2012-02-01
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PWQ077AT2 | 120-55 QUEENS BLVD- QUEENS BOROUGH HALL ATRIUM | 2 | DESIGN START | 2012-06-02 | 2012-06-02 | 2013-02-02 | 2015-02-02
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PWQ077AT2 | 120-55 QUEENS BLVD- QUEENS BOROUGH HALL ATRIUM | 3 | DESIGN COMPLETION | 2012-06-03 | 2012-06-03 | 2015-02-03 | 2017-04-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PWQ077AT2 | 120-55 QUEENS BLVD- QUEENS BOROUGH HALL ATRIUM | 4 | CONSTRUCTION START | 2012-06-04 | 2012-06-04 | 2017-04-26 | 2018-06-02
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PWQ077AT2 | 120-55 QUEENS BLVD- QUEENS BOROUGH HALL ATRIUM | 5 | CONSTRUCTION COMPLETION | 2015-08-30 | 2015-08-30 | 2018-06-03 | 2022-08-01
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1000 | WATER MAIN WORK IN VARIOUS LOCATIONS PROJECT Q2006-04 | 1 | DEVELOP SCOPE | 2011-06-01 | 2011-08-29 | 2011-06-01 | 2011-08-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1000 | WATER MAIN WORK IN VARIOUS LOCATIONS PROJECT Q2006-04 | 2 | PRELIMINARY DESIGN | 2011-08-30 | 2011-12-27 | 2011-08-30 | 2011-12-27
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1000 | WATER MAIN WORK IN VARIOUS LOCATIONS PROJECT Q2006-04 | 3 | FINAL DESIGN | 2011-12-28 | 2012-06-24 | 2011-12-28 | 2012-06-24
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1000 | WATER MAIN WORK IN VARIOUS LOCATIONS PROJECT Q2006-04 | 4 | BID AWARD AND REGISTER CONTRCT | 2012-06-25 | 2012-09-22 | 2012-06-25 | 2012-09-22
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1000 | WATER MAIN WORK IN VARIOUS LOCATIONS PROJECT Q2006-04 | 5 | CONSTRUCTION TO 25% | 2012-09-23 | 2013-01-20 | 2012-09-23 | 2013-01-20
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1000 | WATER MAIN WORK IN VARIOUS LOCATIONS PROJECT Q2006-04 | 6 | CONSTRUCTION TO 50% | 2013-01-21 | 2013-05-20 | 2013-01-21 | 2013-05-20
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1000 | WATER MAIN WORK IN VARIOUS LOCATIONS PROJECT Q2006-04 | 7 | CONSTRUCTION TO 75% | 2013-05-21 | 2013-09-17 | 2013-05-21 | 2013-09-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1000 | WATER MAIN WORK IN VARIOUS LOCATIONS PROJECT Q2006-04 | 8 | ORIGINAL EQUIP & FURNISHING | 2013-09-18 | 2013-12-16 | 2013-09-18 | 2013-12-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1000 | WATER MAIN WORK IN VARIOUS LOCATIONS PROJECT Q2006-04 | 9 | SUBSTANTIAL COMPLETION | 2013-12-17 | 2014-02-14 | 2013-12-17 | 2014-02-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1000 | WATER MAIN WORK IN VARIOUS LOCATIONS PROJECT Q2006-04 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-02-15 | 2014-03-16 | 2014-02-15 | 2021-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED1002 | WATER MAIN WORK IN VARIOUS LOCATIONS PROJ Q2007-05 | 1 | DEVELOP SCOPE | 2011-02-18 | 2011-05-18 | 2011-02-18 | 2011-05-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED1002 | WATER MAIN WORK IN VARIOUS LOCATIONS PROJ Q2007-05 | 2 | PRELIMINARY DESIGN | 2011-05-19 | 2011-09-15 | 2011-05-19 | 2011-09-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED1002 | WATER MAIN WORK IN VARIOUS LOCATIONS PROJ Q2007-05 | 3 | FINAL DESIGN | 2011-09-16 | 2012-03-13 | 2011-09-16 | 2014-01-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED1002 | WATER MAIN WORK IN VARIOUS LOCATIONS PROJ Q2007-05 | 4 | BID AWARD AND REGISTER CONTRCT | 2012-03-14 | 2012-06-11 | 2014-01-19 | 2014-04-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED1002 | WATER MAIN WORK IN VARIOUS LOCATIONS PROJ Q2007-05 | 5 | CONSTRUCTION TO 25% | 2012-06-12 | 2012-10-09 | 2014-04-19 | 2014-10-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED1002 | WATER MAIN WORK IN VARIOUS LOCATIONS PROJ Q2007-05 | 6 | CONSTRUCTION TO 50% | 2012-10-10 | 2013-02-06 | 2014-10-16 | 2015-06-12
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED1002 | WATER MAIN WORK IN VARIOUS LOCATIONS PROJ Q2007-05 | 7 | CONSTRUCTION TO 75% | 2013-02-07 | 2013-06-06 | 2015-06-13 | 2016-02-07
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED1002 | WATER MAIN WORK IN VARIOUS LOCATIONS PROJ Q2007-05 | 8 | ORIGINAL EQUIP & FURNISHING | 2013-06-07 | 2013-09-04 | 2016-02-08 | 2016-03-08
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED1002 | WATER MAIN WORK IN VARIOUS LOCATIONS PROJ Q2007-05 | 9 | SUBSTANTIAL COMPLETION | 2013-09-05 | 2013-11-03 | 2016-03-09 | 2016-05-07
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED1002 | WATER MAIN WORK IN VARIOUS LOCATIONS PROJ Q2007-05 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-11-04 | 2013-12-03 | 2016-05-08 | 2021-06-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED1005 | DIST WATER MAIN REPLACEMENT LONG ISLAND CITY | 1 | DEVELOP SCOPE | 2011-01-01 | 2011-03-31 | 2015-10-01 | 2015-12-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED1005 | DIST WATER MAIN REPLACEMENT LONG ISLAND CITY | 2 | PRELIMINARY DESIGN | 2011-04-01 | 2011-07-29 | 2015-12-30 | 2016-04-27
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED1005 | DIST WATER MAIN REPLACEMENT LONG ISLAND CITY | 3 | FINAL DESIGN | 2011-07-30 | 2012-01-25 | 2016-04-28 | 2016-08-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED1005 | DIST WATER MAIN REPLACEMENT LONG ISLAND CITY | 4 | BID AWARD AND REGISTER CONTRCT | 2012-01-26 | 2012-04-24 | 2016-08-26 | 2016-11-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED1005 | DIST WATER MAIN REPLACEMENT LONG ISLAND CITY | 5 | CONSTRUCTION TO 25% | 2012-04-25 | 2012-08-22 | 2016-11-24 | 2017-03-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED1005 | DIST WATER MAIN REPLACEMENT LONG ISLAND CITY | 6 | CONSTRUCTION TO 50% | 2012-08-23 | 2012-12-20 | 2017-03-24 | 2017-07-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED1005 | DIST WATER MAIN REPLACEMENT LONG ISLAND CITY | 7 | CONSTRUCTION TO 75% | 2012-12-21 | 2013-04-19 | 2017-07-22 | 2017-11-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED1005 | DIST WATER MAIN REPLACEMENT LONG ISLAND CITY | 8 | ORIGINAL EQUIP & FURNISHING | 2013-04-20 | 2013-07-18 | 2017-11-19 | 2017-11-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED1005 | DIST WATER MAIN REPLACEMENT LONG ISLAND CITY | 9 | SUBSTANTIAL COMPLETION | 2013-07-19 | 2013-09-16 | 2017-11-19 | 2018-02-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED1005 | DIST WATER MAIN REPLACEMENT LONG ISLAND CITY | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-09-17 | 2013-10-16 | 2018-02-17 | 2023-03-28
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1007 | New Trunk Water Main in Rockaway Beach Blvd (SANDHW12) | 1 | DEVELOP SCOPE | 2014-03-05 | 2014-06-02 | 2014-03-05 | 2014-06-02
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1007 | New Trunk Water Main in Rockaway Beach Blvd (SANDHW12) | 2 | PRELIMINARY DESIGN | 2014-06-03 | 2014-09-30 | 2014-06-03 | 2014-09-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1007 | New Trunk Water Main in Rockaway Beach Blvd (SANDHW12) | 3 | FINAL DESIGN | 2014-10-01 | 2015-03-29 | 2014-10-01 | 2015-03-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1007 | New Trunk Water Main in Rockaway Beach Blvd (SANDHW12) | 4 | BID AWARD AND REGISTER CONTRCT | 2015-03-30 | 2015-06-27 | 2015-03-30 | 2015-06-27
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1007 | New Trunk Water Main in Rockaway Beach Blvd (SANDHW12) | 5 | CONSTRUCTION TO 25% | 2015-06-28 | 2015-10-25 | 2015-06-28 | 2015-10-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1007 | New Trunk Water Main in Rockaway Beach Blvd (SANDHW12) | 6 | CONSTRUCTION TO 50% | 2015-10-26 | 2016-02-22 | 2015-10-26 | 2016-02-22
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1007 | New Trunk Water Main in Rockaway Beach Blvd (SANDHW12) | 7 | CONSTRUCTION TO 75% | 2016-02-23 | 2016-06-21 | 2016-02-23 | 2016-06-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1007 | New Trunk Water Main in Rockaway Beach Blvd (SANDHW12) | 8 | ORIGINAL EQUIP & FURNISHING | 2016-06-22 | 2016-09-19 | 2016-06-22 | 2016-09-19
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1007 | New Trunk Water Main in Rockaway Beach Blvd (SANDHW12) | 9 | SUBSTANTIAL COMPLETION | 2016-09-20 | 2016-11-18 | 2016-09-20 | 2016-11-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1007 | New Trunk Water Main in Rockaway Beach Blvd (SANDHW12) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-11-19 | 2016-12-18 | 2016-11-19 | 2022-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1008 | 3WT-TRUNK MAIN CONNECTION IN 54 ST | 1 | DEVELOP SCOPE | 2010-01-03 | 2010-04-02 | 2010-01-03 | 2010-04-02
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1008 | 3WT-TRUNK MAIN CONNECTION IN 54 ST | 2 | PRELIMINARY DESIGN | 2010-04-03 | 2010-07-31 | 2010-04-03 | 2010-07-31
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1008 | 3WT-TRUNK MAIN CONNECTION IN 54 ST | 3 | FINAL DESIGN | 2010-08-01 | 2011-01-27 | 2010-08-01 | 2011-01-27
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1008 | 3WT-TRUNK MAIN CONNECTION IN 54 ST | 4 | BID AWARD AND REGISTER CONTRCT | 2012-03-19 | 2012-06-16 | 2012-03-19 | 2012-06-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1008 | 3WT-TRUNK MAIN CONNECTION IN 54 ST | 5 | CONSTRUCTION TO 25% | 2012-06-17 | 2012-06-16 | 2012-06-17 | 2012-10-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1008 | 3WT-TRUNK MAIN CONNECTION IN 54 ST | 6 | CONSTRUCTION TO 50% | 2012-06-17 | 2012-06-16 | 2012-10-15 | 2012-10-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1008 | 3WT-TRUNK MAIN CONNECTION IN 54 ST | 7 | CONSTRUCTION TO 75% | 2012-06-17 | 2012-06-16 | 2012-10-15 | 2012-10-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1008 | 3WT-TRUNK MAIN CONNECTION IN 54 ST | 8 | ORIGINAL EQUIP & FURNISHING | 2012-06-17 | 2012-06-16 | 2012-10-15 | 2012-10-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1008 | 3WT-TRUNK MAIN CONNECTION IN 54 ST | 9 | SUBSTANTIAL COMPLETION | 2012-06-17 | 2012-06-16 | 2012-10-15 | 2012-10-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1008 | 3WT-TRUNK MAIN CONNECTION IN 54 ST | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-06-17 | 2013-12-16 | 2014-10-04 | 2021-08-09
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED1014 | Rehabilitation of Astoria Water Trunk Main by Lining | 1 | DEVELOP SCOPE | 2015-02-16 | 2015-05-16 | 2012-05-22 | 2013-04-07
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED1014 | Rehabilitation of Astoria Water Trunk Main by Lining | 2 | PRELIMINARY DESIGN | 2015-05-17 | 2015-09-13 | 2013-04-08 | 2015-09-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED1014 | Rehabilitation of Astoria Water Trunk Main by Lining | 3 | FINAL DESIGN | 2015-09-14 | 2016-03-11 | 2015-09-15 | 2015-12-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED1014 | Rehabilitation of Astoria Water Trunk Main by Lining | 4 | BID AWARD AND REGISTER CONTRCT | 2016-03-12 | 2016-06-09 | 2015-12-31 | 2017-03-27
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED1014 | Rehabilitation of Astoria Water Trunk Main by Lining | 5 | CONSTRUCTION TO 25% | 2016-06-10 | 2016-10-07 | 2017-03-28 | 2017-07-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED1014 | Rehabilitation of Astoria Water Trunk Main by Lining | 6 | CONSTRUCTION TO 50% | 2016-10-08 | 2017-02-04 | 2017-07-26 | 2017-11-22
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED1014 | Rehabilitation of Astoria Water Trunk Main by Lining | 7 | CONSTRUCTION TO 75% | 2017-02-05 | 2017-06-04 | 2017-11-23 | 2018-03-22
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED1014 | Rehabilitation of Astoria Water Trunk Main by Lining | 8 | ORIGINAL EQUIP & FURNISHING | 2017-06-05 | 2017-09-02 | 2018-03-23 | 2018-06-20
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED1014 | Rehabilitation of Astoria Water Trunk Main by Lining | 9 | SUBSTANTIAL COMPLETION | 2017-09-03 | 2017-11-01 | 2018-06-21 | 2018-08-19
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED1014 | Rehabilitation of Astoria Water Trunk Main by Lining | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-11-02 | 2017-12-01 | 2018-08-20 | 2022-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1018 | Replcing 12" & 8" WM in 217th-235th STs ( WFF) | 1 | DEVELOP SCOPE | 2013-02-16 | 2013-05-16 | 2013-02-16 | 2013-05-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1018 | Replcing 12" & 8" WM in 217th-235th STs ( WFF) | 2 | PRELIMINARY DESIGN | 2013-05-17 | 2013-09-13 | 2013-05-17 | 2013-09-13
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1018 | Replcing 12" & 8" WM in 217th-235th STs ( WFF) | 3 | FINAL DESIGN | 2013-09-14 | 2014-03-12 | 2013-09-14 | 2014-03-12
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1018 | Replcing 12" & 8" WM in 217th-235th STs ( WFF) | 4 | BID AWARD AND REGISTER CONTRCT | 2014-03-13 | 2014-06-10 | 2014-03-13 | 2014-06-10
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1018 | Replcing 12" & 8" WM in 217th-235th STs ( WFF) | 5 | CONSTRUCTION TO 25% | 2014-06-11 | 2014-10-08 | 2014-06-11 | 2014-10-08
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1018 | Replcing 12" & 8" WM in 217th-235th STs ( WFF) | 6 | CONSTRUCTION TO 50% | 2014-10-09 | 2015-02-05 | 2014-10-09 | 2015-02-05
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1018 | Replcing 12" & 8" WM in 217th-235th STs ( WFF) | 7 | CONSTRUCTION TO 75% | 2015-02-06 | 2015-06-05 | 2015-02-06 | 2015-06-05
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1018 | Replcing 12" & 8" WM in 217th-235th STs ( WFF) | 8 | ORIGINAL EQUIP & FURNISHING | 2015-06-06 | 2015-09-03 | 2015-06-06 | 2015-09-03
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1018 | Replcing 12" & 8" WM in 217th-235th STs ( WFF) | 9 | SUBSTANTIAL COMPLETION | 2015-09-04 | 2015-11-02 | 2015-09-04 | 2015-11-02
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1018 | Replcing 12" & 8" WM in 217th-235th STs ( WFF) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-11-03 | 2015-12-02 | 2015-11-03 | 2017-12-02
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1022 | Replcmnt of Water Mains in Former Jamaica Water Supply Area | 1 | DEVELOP SCOPE | 2013-06-30 | 2014-03-26 | 2013-06-30 | 2014-03-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1022 | Replcmnt of Water Mains in Former Jamaica Water Supply Area | 2 | PRELIMINARY DESIGN | 2014-03-27 | 2015-03-21 | 2014-03-27 | 2015-03-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1022 | Replcmnt of Water Mains in Former Jamaica Water Supply Area | 3 | FINAL DESIGN | 2015-03-22 | 2016-09-11 | 2015-03-22 | 2016-09-11
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1022 | Replcmnt of Water Mains in Former Jamaica Water Supply Area | 4 | BID AWARD AND REGISTER CONTRCT | 2016-09-12 | 2017-06-08 | 2016-09-12 | 2017-06-08
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1022 | Replcmnt of Water Mains in Former Jamaica Water Supply Area | 5 | CONSTRUCTION TO 25% | 2017-06-09 | 2018-06-03 | 2017-06-09 | 2018-06-03
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1022 | Replcmnt of Water Mains in Former Jamaica Water Supply Area | 6 | CONSTRUCTION TO 50% | 2018-06-04 | 2019-05-29 | 2018-06-04 | 2019-05-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1022 | Replcmnt of Water Mains in Former Jamaica Water Supply Area | 7 | CONSTRUCTION TO 75% | 2019-05-30 | 2020-05-23 | 2019-05-30 | 2020-05-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1022 | Replcmnt of Water Mains in Former Jamaica Water Supply Area | 8 | ORIGINAL EQUIP & FURNISHING | 2020-05-24 | 2021-02-17 | 2020-05-24 | 2021-02-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1022 | Replcmnt of Water Mains in Former Jamaica Water Supply Area | 9 | SUBSTANTIAL COMPLETION | 2021-02-18 | 2021-08-16 | 2021-02-18 | 2021-08-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1022 | Replcmnt of Water Mains in Former Jamaica Water Supply Area | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-08-17 | 2021-11-14 | 2021-08-17 | 2021-11-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1023A | Distribution WM replacement, Onderdonk Ave, Qns | 1 | DEVELOP SCOPE | 2013-12-19 | 2014-09-14 | 2013-12-19 | 2014-09-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1023A | Distribution WM replacement, Onderdonk Ave, Qns | 2 | PRELIMINARY DESIGN | 2014-09-15 | 2015-09-09 | 2014-09-15 | 2015-09-09
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1023A | Distribution WM replacement, Onderdonk Ave, Qns | 3 | FINAL DESIGN | 2015-09-10 | 2017-03-02 | 2015-09-10 | 2017-03-02
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1023A | Distribution WM replacement, Onderdonk Ave, Qns | 4 | BID AWARD AND REGISTER CONTRCT | 2017-03-03 | 2017-11-27 | 2017-03-03 | 2017-11-27
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1023A | Distribution WM replacement, Onderdonk Ave, Qns | 5 | CONSTRUCTION TO 25% | 2017-11-28 | 2018-11-22 | 2017-11-28 | 2018-11-22
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1023A | Distribution WM replacement, Onderdonk Ave, Qns | 6 | CONSTRUCTION TO 50% | 2018-11-23 | 2019-11-17 | 2018-11-23 | 2019-11-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1023A | Distribution WM replacement, Onderdonk Ave, Qns | 7 | CONSTRUCTION TO 75% | 2019-11-18 | 2020-11-11 | 2019-11-18 | 2020-11-11
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1023A | Distribution WM replacement, Onderdonk Ave, Qns | 8 | ORIGINAL EQUIP & FURNISHING | 2020-11-12 | 2021-08-08 | 2020-11-12 | 2021-08-08
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1023A | Distribution WM replacement, Onderdonk Ave, Qns | 9 | SUBSTANTIAL COMPLETION | 2021-08-09 | 2022-02-04 | 2021-08-09 | 2022-02-04
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1023A | Distribution WM replacement, Onderdonk Ave, Qns | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-02-05 | 2022-05-05 | 2022-02-05 | 2022-05-05
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1023B | Distr & Trunk WM Replacement Cypress Ave, Queens (Joint Bid) | 1 | DEVELOP SCOPE | 2013-12-23 | 2014-09-18 | 2013-12-23 | 2014-09-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1023B | Distr & Trunk WM Replacement Cypress Ave, Queens (Joint Bid) | 2 | PRELIMINARY DESIGN | 2014-09-19 | 2015-09-13 | 2014-09-19 | 2015-09-13
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1023B | Distr & Trunk WM Replacement Cypress Ave, Queens (Joint Bid) | 3 | FINAL DESIGN | 2015-09-14 | 2017-03-06 | 2015-09-14 | 2017-03-06
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1023B | Distr & Trunk WM Replacement Cypress Ave, Queens (Joint Bid) | 4 | BID AWARD AND REGISTER CONTRCT | 2017-03-07 | 2017-12-01 | 2017-03-07 | 2017-12-01
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1023B | Distr & Trunk WM Replacement Cypress Ave, Queens (Joint Bid) | 5 | CONSTRUCTION TO 25% | 2017-12-02 | 2018-11-26 | 2017-12-02 | 2018-11-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1023B | Distr & Trunk WM Replacement Cypress Ave, Queens (Joint Bid) | 6 | CONSTRUCTION TO 50% | 2018-11-27 | 2019-11-21 | 2018-11-27 | 2019-11-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1023B | Distr & Trunk WM Replacement Cypress Ave, Queens (Joint Bid) | 7 | CONSTRUCTION TO 75% | 2019-11-22 | 2020-11-15 | 2019-11-22 | 2020-11-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1023B | Distr & Trunk WM Replacement Cypress Ave, Queens (Joint Bid) | 8 | ORIGINAL EQUIP & FURNISHING | 2020-11-16 | 2021-08-12 | 2020-11-16 | 2021-08-12
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1023B | Distr & Trunk WM Replacement Cypress Ave, Queens (Joint Bid) | 9 | SUBSTANTIAL COMPLETION | 2021-08-13 | 2022-02-08 | 2021-08-13 | 2022-02-08
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1023B | Distr & Trunk WM Replacement Cypress Ave, Queens (Joint Bid) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-02-09 | 2022-05-09 | 2022-02-09 | 2022-05-09
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1027 | Replacement of Dist WM in 222nd St | 1 | DEVELOP SCOPE | 2019-03-01 | 2019-05-29 | 2019-03-01 | 2019-05-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1027 | Replacement of Dist WM in 222nd St | 2 | PRELIMINARY DESIGN | 2019-05-30 | 2019-09-26 | 2019-05-30 | 2019-09-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1027 | Replacement of Dist WM in 222nd St | 3 | FINAL DESIGN | 2019-09-27 | 2020-03-24 | 2019-09-27 | 2020-03-24
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1027 | Replacement of Dist WM in 222nd St | 4 | BID AWARD AND REGISTER CONTRCT | 2020-03-25 | 2020-06-22 | 2020-03-25 | 2020-06-22
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1027 | Replacement of Dist WM in 222nd St | 5 | CONSTRUCTION TO 25% | 2020-06-23 | 2020-10-20 | 2020-06-23 | 2020-10-20
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1027 | Replacement of Dist WM in 222nd St | 6 | CONSTRUCTION TO 50% | 2020-10-21 | 2021-02-17 | 2020-10-21 | 2021-02-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1027 | Replacement of Dist WM in 222nd St | 7 | CONSTRUCTION TO 75% | 2021-02-18 | 2021-06-17 | 2021-02-18 | 2021-06-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1027 | Replacement of Dist WM in 222nd St | 8 | ORIGINAL EQUIP & FURNISHING | 2021-06-18 | 2021-09-15 | 2021-06-18 | 2021-09-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1027 | Replacement of Dist WM in 222nd St | 9 | SUBSTANTIAL COMPLETION | 2021-09-16 | 2021-11-14 | 2021-09-16 | 2021-11-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1027 | Replacement of Dist WM in 222nd St | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-11-15 | 2021-12-14 | 2021-11-15 | 2024-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1030 | Water Main & Sewer Work, Beach Channel Drive Area (SANDHW11) | 1 | DEVELOP SCOPE | 2017-03-01 | 2017-05-29 | 2017-03-01 | 2017-05-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1030 | Water Main & Sewer Work, Beach Channel Drive Area (SANDHW11) | 2 | PRELIMINARY DESIGN | 2017-05-30 | 2017-09-26 | 2017-05-30 | 2017-09-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1030 | Water Main & Sewer Work, Beach Channel Drive Area (SANDHW11) | 3 | FINAL DESIGN | 2017-09-27 | 2018-03-25 | 2017-09-27 | 2018-03-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1030 | Water Main & Sewer Work, Beach Channel Drive Area (SANDHW11) | 4 | BID AWARD AND REGISTER CONTRCT | 2018-03-26 | 2018-06-23 | 2018-03-26 | 2018-06-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1030 | Water Main & Sewer Work, Beach Channel Drive Area (SANDHW11) | 5 | CONSTRUCTION TO 25% | 2018-06-24 | 2018-10-21 | 2018-06-24 | 2018-10-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1030 | Water Main & Sewer Work, Beach Channel Drive Area (SANDHW11) | 6 | CONSTRUCTION TO 50% | 2018-10-22 | 2019-02-18 | 2018-10-22 | 2019-02-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1030 | Water Main & Sewer Work, Beach Channel Drive Area (SANDHW11) | 7 | CONSTRUCTION TO 75% | 2019-02-19 | 2019-06-18 | 2019-02-19 | 2019-06-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1030 | Water Main & Sewer Work, Beach Channel Drive Area (SANDHW11) | 8 | ORIGINAL EQUIP & FURNISHING | 2019-06-19 | 2019-09-16 | 2019-06-19 | 2019-09-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1030 | Water Main & Sewer Work, Beach Channel Drive Area (SANDHW11) | 9 | SUBSTANTIAL COMPLETION | 2019-09-17 | 2019-11-15 | 2019-09-17 | 2019-11-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1030 | Water Main & Sewer Work, Beach Channel Drive Area (SANDHW11) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-11-16 | 2019-12-15 | 2019-11-16 | 2023-06-07
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1036 | Water Main Replacement in Queens Blvd | 1 | DEVELOP SCOPE | 2017-06-01 | 2018-02-25 | 2017-06-01 | 2018-02-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1036 | Water Main Replacement in Queens Blvd | 2 | PRELIMINARY DESIGN | 2018-02-26 | 2019-02-20 | 2018-02-26 | 2019-02-20
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1036 | Water Main Replacement in Queens Blvd | 3 | FINAL DESIGN | 2019-02-21 | 2020-08-13 | 2019-02-21 | 2020-08-13
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1036 | Water Main Replacement in Queens Blvd | 4 | BID AWARD AND REGISTER CONTRCT | 2020-08-14 | 2021-05-10 | 2020-08-14 | 2021-05-10
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1036 | Water Main Replacement in Queens Blvd | 5 | CONSTRUCTION TO 25% | 2021-05-11 | 2022-05-05 | 2021-05-11 | 2022-05-05
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1036 | Water Main Replacement in Queens Blvd | 6 | CONSTRUCTION TO 50% | 2022-05-06 | 2023-04-30 | 2022-05-06 | 2023-04-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1036 | Water Main Replacement in Queens Blvd | 7 | CONSTRUCTION TO 75% | 2023-05-01 | 2024-04-24 | 2023-05-01 | 2024-04-24
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1036 | Water Main Replacement in Queens Blvd | 8 | ORIGINAL EQUIP & FURNISHING | 2024-04-25 | 2025-01-19 | 2024-04-25 | 2025-01-19
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1036 | Water Main Replacement in Queens Blvd | 9 | SUBSTANTIAL COMPLETION | 2025-01-20 | 2025-07-18 | 2025-01-20 | 2025-07-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1036 | Water Main Replacement in Queens Blvd | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-07-19 | 2025-10-16 | 2025-07-19 | 2025-10-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1037 | WM Replacement in South Conduit Ave, Queens | 1 | DEVELOP SCOPE | 2017-03-01 | 2017-05-29 | 2017-03-01 | 2017-05-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1037 | WM Replacement in South Conduit Ave, Queens | 2 | PRELIMINARY DESIGN | 2017-05-30 | 2017-09-26 | 2017-05-30 | 2017-09-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1037 | WM Replacement in South Conduit Ave, Queens | 3 | FINAL DESIGN | 2017-09-27 | 2018-03-25 | 2017-09-27 | 2018-03-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1037 | WM Replacement in South Conduit Ave, Queens | 4 | BID AWARD AND REGISTER CONTRCT | 2018-03-26 | 2018-06-23 | 2018-03-26 | 2018-06-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1037 | WM Replacement in South Conduit Ave, Queens | 5 | CONSTRUCTION TO 25% | 2018-06-24 | 2018-10-21 | 2018-06-24 | 2018-10-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1037 | WM Replacement in South Conduit Ave, Queens | 6 | CONSTRUCTION TO 50% | 2018-10-22 | 2019-02-18 | 2018-10-22 | 2019-02-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1037 | WM Replacement in South Conduit Ave, Queens | 7 | CONSTRUCTION TO 75% | 2019-02-19 | 2019-06-18 | 2019-02-19 | 2019-06-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1037 | WM Replacement in South Conduit Ave, Queens | 8 | ORIGINAL EQUIP & FURNISHING | 2019-06-19 | 2019-09-16 | 2019-06-19 | 2019-09-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1037 | WM Replacement in South Conduit Ave, Queens | 9 | SUBSTANTIAL COMPLETION | 2019-09-17 | 2019-11-15 | 2019-09-17 | 2019-11-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1037 | WM Replacement in South Conduit Ave, Queens | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-11-16 | 2019-12-15 | 2019-11-16 | 2023-06-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1042A | Watermain replacement & sewer repair on Queens Blvd-HWQ1190A | 1 | DEVELOP SCOPE | 2020-03-01 | 2020-05-29 | 2020-03-01 | 2020-05-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1042A | Watermain replacement & sewer repair on Queens Blvd-HWQ1190A | 2 | PRELIMINARY DESIGN | 2020-05-30 | 2020-09-26 | 2020-05-30 | 2020-09-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1042A | Watermain replacement & sewer repair on Queens Blvd-HWQ1190A | 3 | FINAL DESIGN | 2020-09-27 | 2021-03-25 | 2020-09-27 | 2021-03-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1042A | Watermain replacement & sewer repair on Queens Blvd-HWQ1190A | 4 | BID AWARD AND REGISTER CONTRCT | 2021-03-26 | 2021-06-23 | 2021-03-26 | 2021-06-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1042A | Watermain replacement & sewer repair on Queens Blvd-HWQ1190A | 5 | CONSTRUCTION TO 25% | 2021-06-24 | 2021-10-21 | 2021-06-24 | 2021-10-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1042A | Watermain replacement & sewer repair on Queens Blvd-HWQ1190A | 6 | CONSTRUCTION TO 50% | 2021-10-22 | 2022-02-18 | 2021-10-22 | 2022-02-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1042A | Watermain replacement & sewer repair on Queens Blvd-HWQ1190A | 7 | CONSTRUCTION TO 75% | 2022-02-19 | 2022-06-18 | 2022-02-19 | 2022-06-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1042A | Watermain replacement & sewer repair on Queens Blvd-HWQ1190A | 8 | ORIGINAL EQUIP & FURNISHING | 2022-06-19 | 2022-09-16 | 2022-06-19 | 2022-09-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1042A | Watermain replacement & sewer repair on Queens Blvd-HWQ1190A | 9 | SUBSTANTIAL COMPLETION | 2022-09-17 | 2022-11-15 | 2022-09-17 | 2022-11-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1042A | Watermain replacement & sewer repair on Queens Blvd-HWQ1190A | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-11-16 | 2022-12-15 | 2022-11-16 | 2022-12-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1044 | Replacement of Water Mains in Beach 108th Street (SANDR04) | 1 | DEVELOP SCOPE | 2017-03-01 | 2017-05-29 | 2017-03-01 | 2017-05-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1044 | Replacement of Water Mains in Beach 108th Street (SANDR04) | 2 | PRELIMINARY DESIGN | 2017-05-30 | 2017-09-26 | 2017-05-30 | 2017-09-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1044 | Replacement of Water Mains in Beach 108th Street (SANDR04) | 3 | FINAL DESIGN | 2017-09-27 | 2018-03-25 | 2017-09-27 | 2019-10-31
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1044 | Replacement of Water Mains in Beach 108th Street (SANDR04) | 4 | BID AWARD AND REGISTER CONTRCT | 2018-03-26 | 2018-06-23 | 2019-11-01 | 2020-01-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1044 | Replacement of Water Mains in Beach 108th Street (SANDR04) | 5 | CONSTRUCTION TO 25% | 2018-06-24 | 2018-10-21 | 2020-01-30 | 2020-05-28
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1044 | Replacement of Water Mains in Beach 108th Street (SANDR04) | 6 | CONSTRUCTION TO 50% | 2018-10-22 | 2019-02-18 | 2020-05-29 | 2020-09-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1044 | Replacement of Water Mains in Beach 108th Street (SANDR04) | 7 | CONSTRUCTION TO 75% | 2019-02-19 | 2019-06-18 | 2020-09-26 | 2021-01-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1044 | Replacement of Water Mains in Beach 108th Street (SANDR04) | 8 | ORIGINAL EQUIP & FURNISHING | 2019-06-19 | 2019-09-16 | 2021-01-24 | 2021-04-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1044 | Replacement of Water Mains in Beach 108th Street (SANDR04) | 9 | SUBSTANTIAL COMPLETION | 2019-09-17 | 2019-11-15 | 2021-04-24 | 2021-06-22
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1044 | Replacement of Water Mains in Beach 108th Street (SANDR04) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-11-16 | 2019-12-15 | 2021-06-23 | 2021-07-22
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1045 | Schl Safety Prog 4 - Replmt of WM 16th Ave bwtn Bell & 212st | 1 | DEVELOP SCOPE | 2016-03-01 | 2016-05-29 | 2016-03-01 | 2016-05-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1045 | Schl Safety Prog 4 - Replmt of WM 16th Ave bwtn Bell & 212st | 2 | PRELIMINARY DESIGN | 2016-05-30 | 2016-09-26 | 2016-05-30 | 2016-09-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1045 | Schl Safety Prog 4 - Replmt of WM 16th Ave bwtn Bell & 212st | 3 | FINAL DESIGN | 2016-09-27 | 2017-03-25 | 2016-09-27 | 2017-03-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1045 | Schl Safety Prog 4 - Replmt of WM 16th Ave bwtn Bell & 212st | 4 | BID AWARD AND REGISTER CONTRCT | 2017-03-26 | 2018-02-23 | 2017-03-26 | 2018-02-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1045 | Schl Safety Prog 4 - Replmt of WM 16th Ave bwtn Bell & 212st | 5 | CONSTRUCTION TO 25% | 2018-02-24 | 2018-06-23 | 2018-02-24 | 2018-06-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1045 | Schl Safety Prog 4 - Replmt of WM 16th Ave bwtn Bell & 212st | 6 | CONSTRUCTION TO 50% | 2018-06-24 | 2018-10-21 | 2018-06-24 | 2018-10-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1045 | Schl Safety Prog 4 - Replmt of WM 16th Ave bwtn Bell & 212st | 7 | CONSTRUCTION TO 75% | 2018-10-22 | 2019-02-18 | 2018-10-22 | 2019-02-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1045 | Schl Safety Prog 4 - Replmt of WM 16th Ave bwtn Bell & 212st | 8 | ORIGINAL EQUIP & FURNISHING | 2019-02-19 | 2019-05-19 | 2019-02-19 | 2019-05-19
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1045 | Schl Safety Prog 4 - Replmt of WM 16th Ave bwtn Bell & 212st | 9 | SUBSTANTIAL COMPLETION | 2019-05-20 | 2019-07-18 | 2019-05-20 | 2019-07-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1045 | Schl Safety Prog 4 - Replmt of WM 16th Ave bwtn Bell & 212st | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-07-19 | 2019-08-17 | 2019-07-19 | 2024-06-20
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1049 | Rplmnt WM at 111 St btw 45th & Corona Ave (HWD10311) | 1 | DEVELOP SCOPE | 2021-06-01 | 2021-08-29 | 2021-06-01 | 2021-08-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1049 | Rplmnt WM at 111 St btw 45th & Corona Ave (HWD10311) | 2 | PRELIMINARY DESIGN | 2021-08-30 | 2021-12-27 | 2021-08-30 | 2021-12-27
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1049 | Rplmnt WM at 111 St btw 45th & Corona Ave (HWD10311) | 3 | FINAL DESIGN | 2021-12-28 | 2022-06-25 | 2021-12-28 | 2022-06-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1049 | Rplmnt WM at 111 St btw 45th & Corona Ave (HWD10311) | 4 | BID AWARD AND REGISTER CONTRCT | 2022-06-26 | 2022-09-23 | 2022-06-26 | 2022-09-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1049 | Rplmnt WM at 111 St btw 45th & Corona Ave (HWD10311) | 5 | CONSTRUCTION TO 25% | 2022-09-24 | 2023-01-21 | 2022-09-24 | 2023-01-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1049 | Rplmnt WM at 111 St btw 45th & Corona Ave (HWD10311) | 6 | CONSTRUCTION TO 50% | 2023-01-22 | 2023-05-21 | 2023-01-22 | 2023-05-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1049 | Rplmnt WM at 111 St btw 45th & Corona Ave (HWD10311) | 7 | CONSTRUCTION TO 75% | 2023-05-22 | 2023-09-18 | 2023-05-22 | 2023-09-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1049 | Rplmnt WM at 111 St btw 45th & Corona Ave (HWD10311) | 8 | ORIGINAL EQUIP & FURNISHING | 2023-09-19 | 2023-12-17 | 2023-09-19 | 2023-12-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1049 | Rplmnt WM at 111 St btw 45th & Corona Ave (HWD10311) | 9 | SUBSTANTIAL COMPLETION | 2023-12-18 | 2024-02-15 | 2023-12-18 | 2024-02-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1049 | Rplmnt WM at 111 St btw 45th & Corona Ave (HWD10311) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-02-16 | 2024-03-16 | 2024-02-16 | 2024-03-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1051 | Water Main Replacement in Maspeth Avenue | 1 | DEVELOP SCOPE | 2023-06-01 | 2023-08-29 | 2023-06-01 | 2023-08-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1051 | Water Main Replacement in Maspeth Avenue | 2 | PRELIMINARY DESIGN | 2023-08-30 | 2023-12-27 | 2023-08-30 | 2023-12-27
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1051 | Water Main Replacement in Maspeth Avenue | 3 | FINAL DESIGN | 2023-12-28 | 2024-06-24 | 2023-12-28 | 2024-06-24
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1051 | Water Main Replacement in Maspeth Avenue | 4 | BID AWARD AND REGISTER CONTRCT | 2024-06-25 | 2024-09-22 | 2024-06-25 | 2024-09-22
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1051 | Water Main Replacement in Maspeth Avenue | 5 | CONSTRUCTION TO 25% | 2024-09-23 | 2025-01-20 | 2024-09-23 | 2025-01-20
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1051 | Water Main Replacement in Maspeth Avenue | 6 | CONSTRUCTION TO 50% | 2025-01-21 | 2025-05-20 | 2025-01-21 | 2025-05-20
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1051 | Water Main Replacement in Maspeth Avenue | 7 | CONSTRUCTION TO 75% | 2025-05-21 | 2025-09-17 | 2025-05-21 | 2025-09-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1051 | Water Main Replacement in Maspeth Avenue | 8 | ORIGINAL EQUIP & FURNISHING | 2025-09-18 | 2025-12-16 | 2025-09-18 | 2025-12-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1051 | Water Main Replacement in Maspeth Avenue | 9 | SUBSTANTIAL COMPLETION | 2025-12-17 | 2026-02-14 | 2025-12-17 | 2026-02-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1051 | Water Main Replacement in Maspeth Avenue | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2026-02-15 | 2026-03-16 | 2026-02-15 | 2026-03-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-976 | SEQ - Trunk Water Main in Francis Lewis Blvd (HWQ976) | 1 | DEVELOP SCOPE | 2007-05-01 | 2007-07-29 | 2007-05-01 | 2007-07-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-976 | SEQ - Trunk Water Main in Francis Lewis Blvd (HWQ976) | 2 | PRELIMINARY DESIGN | 2007-07-30 | 2007-11-26 | 2007-07-30 | 2007-11-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-976 | SEQ - Trunk Water Main in Francis Lewis Blvd (HWQ976) | 3 | FINAL DESIGN | 2007-11-27 | 2008-05-24 | 2007-11-27 | 2008-05-24
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-976 | SEQ - Trunk Water Main in Francis Lewis Blvd (HWQ976) | 4 | BID AWARD AND REGISTER CONTRCT | 2008-05-25 | 2008-08-22 | 2019-03-24 | 2019-06-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-976 | SEQ - Trunk Water Main in Francis Lewis Blvd (HWQ976) | 5 | CONSTRUCTION TO 25% | 2008-08-23 | 2008-12-20 | 2019-06-22 | 2019-06-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-976 | SEQ - Trunk Water Main in Francis Lewis Blvd (HWQ976) | 6 | CONSTRUCTION TO 50% | 2008-12-21 | 2009-04-19 | 2019-06-22 | 2019-06-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-976 | SEQ - Trunk Water Main in Francis Lewis Blvd (HWQ976) | 7 | CONSTRUCTION TO 75% | 2009-04-20 | 2009-08-17 | 2019-06-22 | 2019-06-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-976 | SEQ - Trunk Water Main in Francis Lewis Blvd (HWQ976) | 8 | ORIGINAL EQUIP & FURNISHING | 2009-08-18 | 2009-11-15 | 2019-06-22 | 2019-06-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-976 | SEQ - Trunk Water Main in Francis Lewis Blvd (HWQ976) | 9 | SUBSTANTIAL COMPLETION | 2009-11-16 | 2010-01-14 | 2019-06-22 | 2019-06-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-976 | SEQ - Trunk Water Main in Francis Lewis Blvd (HWQ976) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2010-01-15 | 2010-02-13 | 2020-12-15 | 2021-01-13
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-990 | NEW TRUNK & DISTR WMS IN VERMONT PL B/T CYPRESS & JR | 1 | DEVELOP SCOPE | 2009-06-30 | 2009-09-27 | 2009-05-24 | 2009-08-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-990 | NEW TRUNK & DISTR WMS IN VERMONT PL B/T CYPRESS & JR | 2 | PRELIMINARY DESIGN | 2009-09-28 | 2010-01-25 | 2009-08-22 | 2009-12-19
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-990 | NEW TRUNK & DISTR WMS IN VERMONT PL B/T CYPRESS & JR | 3 | FINAL DESIGN | 2010-01-26 | 2010-07-24 | 2009-12-20 | 2010-06-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-990 | NEW TRUNK & DISTR WMS IN VERMONT PL B/T CYPRESS & JR | 4 | BID AWARD AND REGISTER CONTRCT | 2010-07-25 | 2010-10-22 | 2010-06-18 | 2010-09-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-990 | NEW TRUNK & DISTR WMS IN VERMONT PL B/T CYPRESS & JR | 5 | CONSTRUCTION TO 25% | 2010-10-23 | 2011-02-19 | 2010-09-16 | 2011-03-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-990 | NEW TRUNK & DISTR WMS IN VERMONT PL B/T CYPRESS & JR | 6 | CONSTRUCTION TO 50% | 2011-02-20 | 2011-06-19 | 2011-03-15 | 2012-03-13
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-990 | NEW TRUNK & DISTR WMS IN VERMONT PL B/T CYPRESS & JR | 7 | CONSTRUCTION TO 75% | 2011-06-20 | 2011-10-17 | 2012-03-14 | 2017-06-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-990 | NEW TRUNK & DISTR WMS IN VERMONT PL B/T CYPRESS & JR | 8 | ORIGINAL EQUIP & FURNISHING | 2011-10-18 | 2012-01-15 | 2017-06-24 | 2017-09-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-990 | NEW TRUNK & DISTR WMS IN VERMONT PL B/T CYPRESS & JR | 9 | SUBSTANTIAL COMPLETION | 2012-01-16 | 2012-03-15 | 2017-09-22 | 2018-03-20
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-990 | NEW TRUNK & DISTR WMS IN VERMONT PL B/T CYPRESS & JR | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-03-16 | 2012-04-14 | 2018-03-21 | 2022-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-991 | New WM, Trunk Main Ext, 33 Ave & Francis Lewis Blvd, Queens | 1 | DEVELOP SCOPE | 2014-10-16 | 2015-05-16 | 2014-10-16 | 2015-05-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-991 | New WM, Trunk Main Ext, 33 Ave & Francis Lewis Blvd, Queens | 2 | PRELIMINARY DESIGN | 2014-05-17 | 2015-05-16 | 2014-05-17 | 2015-05-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-991 | New WM, Trunk Main Ext, 33 Ave & Francis Lewis Blvd, Queens | 3 | FINAL DESIGN | 2015-05-17 | 2016-03-16 | 2015-05-17 | 2016-03-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-991 | New WM, Trunk Main Ext, 33 Ave & Francis Lewis Blvd, Queens | 4 | BID AWARD AND REGISTER CONTRCT | 2016-03-17 | 2016-06-01 | 2016-03-17 | 2016-06-01
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-991 | New WM, Trunk Main Ext, 33 Ave & Francis Lewis Blvd, Queens | 5 | CONSTRUCTION TO 25% | 2016-06-02 | 2016-12-18 | 2016-06-02 | 2016-12-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-991 | New WM, Trunk Main Ext, 33 Ave & Francis Lewis Blvd, Queens | 6 | CONSTRUCTION TO 50% | 2016-12-19 | 2017-07-06 | 2016-12-19 | 2017-07-06
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-991 | New WM, Trunk Main Ext, 33 Ave & Francis Lewis Blvd, Queens | 7 | CONSTRUCTION TO 75% | 2017-07-07 | 2018-05-02 | 2017-07-07 | 2018-05-02
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-991 | New WM, Trunk Main Ext, 33 Ave & Francis Lewis Blvd, Queens | 8 | ORIGINAL EQUIP & FURNISHING | 2018-05-03 | 2018-07-31 | 2018-05-03 | 2018-07-31
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-991 | New WM, Trunk Main Ext, 33 Ave & Francis Lewis Blvd, Queens | 9 | SUBSTANTIAL COMPLETION | 2018-08-01 | 2018-09-29 | 2018-08-01 | 2018-09-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-991 | New WM, Trunk Main Ext, 33 Ave & Francis Lewis Blvd, Queens | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-09-30 | 2018-10-29 | 2018-09-30 | 2029-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-996 | WATER MAIN IN VARIOUS LOCATIONS. PROJECT Q2005-16 | 1 | DEVELOP SCOPE | 2008-06-30 | 2008-09-27 | 2008-07-01 | 2008-09-28
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-996 | WATER MAIN IN VARIOUS LOCATIONS. PROJECT Q2005-16 | 2 | PRELIMINARY DESIGN | 2008-09-28 | 2009-01-25 | 2008-09-29 | 2009-01-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-996 | WATER MAIN IN VARIOUS LOCATIONS. PROJECT Q2005-16 | 3 | FINAL DESIGN | 2009-01-26 | 2009-07-24 | 2009-01-27 | 2009-07-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-996 | WATER MAIN IN VARIOUS LOCATIONS. PROJECT Q2005-16 | 4 | BID AWARD AND REGISTER CONTRCT | 2009-07-25 | 2009-10-22 | 2009-07-26 | 2009-10-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-996 | WATER MAIN IN VARIOUS LOCATIONS. PROJECT Q2005-16 | 5 | CONSTRUCTION TO 25% | 2009-10-23 | 2010-02-19 | 2009-10-24 | 2010-06-20
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-996 | WATER MAIN IN VARIOUS LOCATIONS. PROJECT Q2005-16 | 6 | CONSTRUCTION TO 50% | 2010-02-20 | 2010-06-19 | 2010-06-21 | 2012-02-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-996 | WATER MAIN IN VARIOUS LOCATIONS. PROJECT Q2005-16 | 7 | CONSTRUCTION TO 75% | 2010-06-20 | 2010-10-17 | 2012-02-16 | 2014-10-01
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-996 | WATER MAIN IN VARIOUS LOCATIONS. PROJECT Q2005-16 | 8 | ORIGINAL EQUIP & FURNISHING | 2010-10-18 | 2011-01-15 | 2014-10-02 | 2014-12-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-996 | WATER MAIN IN VARIOUS LOCATIONS. PROJECT Q2005-16 | 9 | SUBSTANTIAL COMPLETION | 2011-01-16 | 2011-03-16 | 2014-12-31 | 2015-02-28
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-996 | WATER MAIN IN VARIOUS LOCATIONS. PROJECT Q2005-16 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2011-03-17 | 2011-04-15 | 2015-03-01 | 2021-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QEDA-003 | Accelerated Distribution WM Replacement & Sewer Rehab - QNS | 1 | DEVELOP SCOPE | 2016-03-01 | 2016-05-29 | 2016-03-01 | 2016-05-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QEDA-003 | Accelerated Distribution WM Replacement & Sewer Rehab - QNS | 2 | PRELIMINARY DESIGN | 2016-05-30 | 2016-09-26 | 2016-05-30 | 2016-09-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QEDA-003 | Accelerated Distribution WM Replacement & Sewer Rehab - QNS | 3 | FINAL DESIGN | 2016-09-27 | 2017-03-25 | 2016-09-27 | 2017-03-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QEDA-003 | Accelerated Distribution WM Replacement & Sewer Rehab - QNS | 4 | BID AWARD AND REGISTER CONTRCT | 2017-03-26 | 2017-06-23 | 2017-03-26 | 2017-06-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QEDA-003 | Accelerated Distribution WM Replacement & Sewer Rehab - QNS | 5 | CONSTRUCTION TO 25% | 2017-06-24 | 2017-10-21 | 2017-06-24 | 2017-10-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QEDA-003 | Accelerated Distribution WM Replacement & Sewer Rehab - QNS | 6 | CONSTRUCTION TO 50% | 2017-10-22 | 2018-02-18 | 2017-10-22 | 2018-02-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QEDA-003 | Accelerated Distribution WM Replacement & Sewer Rehab - QNS | 7 | CONSTRUCTION TO 75% | 2018-02-19 | 2018-06-18 | 2018-02-19 | 2018-06-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QEDA-003 | Accelerated Distribution WM Replacement & Sewer Rehab - QNS | 8 | ORIGINAL EQUIP & FURNISHING | 2018-06-19 | 2018-09-16 | 2018-06-19 | 2018-09-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QEDA-003 | Accelerated Distribution WM Replacement & Sewer Rehab - QNS | 9 | SUBSTANTIAL COMPLETION | 2018-09-17 | 2018-11-15 | 2018-09-17 | 2018-11-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QEDA-003 | Accelerated Distribution WM Replacement & Sewer Rehab - QNS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-11-16 | 2018-12-15 | 2018-11-16 | 2022-05-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-383K | QUEENS 5/5A HVAC | 1 | PROJECT START | 2015-07-01 | 2015-07-01 | 2015-07-01 | 2015-07-01
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-383K | QUEENS 5/5A HVAC | 2 | DESIGN START | 2015-07-02 | 2015-07-02 | 2015-07-02 | 2015-07-02
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-383K | QUEENS 5/5A HVAC | 3 | DESIGN COMPLETION | 2015-07-03 | 2015-07-03 | 2015-07-03 | 2015-07-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-383K | QUEENS 5/5A HVAC | 4 | CONSTRUCTION START | 2015-07-04 | 2015-07-04 | 2015-07-17 | 2015-08-06
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-383K | QUEENS 5/5A HVAC | 5 | CONSTRUCTION COMPLETION | 2015-07-05 | 2016-07-05 | 2017-03-27 | 2021-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-419L | OAU Offices Expansion at CRS | 1 | DEVELOP SCOPE | 2014-06-01 | 2014-07-15 | 2014-06-01 | 2014-07-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-419L | OAU Offices Expansion at CRS | 2 | PRELIMINARY DESIGN | 2014-07-16 | 2015-01-31 | 2014-07-16 | 2016-12-27
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-419L | OAU Offices Expansion at CRS | 3 | FINAL DESIGN | 2015-02-01 | 2015-08-19 | 2016-12-28 | 2019-01-24
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-419L | OAU Offices Expansion at CRS | 4 | BID AWARD AND REGISTER CONTRCT | 2015-08-20 | 2016-03-06 | 2019-01-25 | 2019-12-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-419L | OAU Offices Expansion at CRS | 5 | CONSTRUCTION TO 25% | 2016-03-07 | 2016-09-22 | 2019-12-17 | 2019-12-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-419L | OAU Offices Expansion at CRS | 6 | CONSTRUCTION TO 50% | 2016-09-23 | 2017-04-10 | 2019-12-19 | 2019-12-20
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-419L | OAU Offices Expansion at CRS | 7 | CONSTRUCTION TO 75% | 2017-04-11 | 2017-10-27 | 2019-12-21 | 2019-12-22
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-419L | OAU Offices Expansion at CRS | 8 | SUBSTANTIAL COMPLETION | 2017-10-28 | 2018-05-15 | 2019-12-23 | 2021-04-09
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-419L | OAU Offices Expansion at CRS | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-05-16 | 2021-02-08 | 2021-04-10 | 2022-04-09
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-423 | Queens 11/13 FLOOR SLAB REPLACEMENT | 1 | DEVELOP SCOPE | 2014-07-01 | 2014-08-14 | 2015-12-15 | 2017-03-05
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-423 | Queens 11/13 FLOOR SLAB REPLACEMENT | 2 | PRELIMINARY DESIGN | 2014-08-15 | 2015-04-21 | 2017-03-06 | 2019-03-05
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-423 | Queens 11/13 FLOOR SLAB REPLACEMENT | 3 | FINAL DESIGN | 2015-04-22 | 2016-04-20 | 2019-03-06 | 2020-03-31
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-423 | Queens 11/13 FLOOR SLAB REPLACEMENT | 4 | BID AWARD AND REGISTER CONTRCT | 2016-04-21 | 2017-09-02 | 2020-04-01 | 2020-12-31
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-423 | Queens 11/13 FLOOR SLAB REPLACEMENT | 5 | CONSTRUCTION TO 25% | 2017-09-03 | 2025-11-19 | 2021-01-01 | 2021-12-31
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-423 | Queens 11/13 FLOOR SLAB REPLACEMENT | 6 | CONSTRUCTION TO 50% | 2025-11-20 | 2025-11-19 | 2022-01-01 | 2022-04-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-423 | Queens 11/13 FLOOR SLAB REPLACEMENT | 7 | CONSTRUCTION TO 75% | 2025-11-20 | 2025-11-19 | 2022-05-01 | 2022-08-28
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-423 | Queens 11/13 FLOOR SLAB REPLACEMENT | 8 | SUBSTANTIAL COMPLETION | 2025-11-20 | 2025-11-19 | 2022-08-29 | 2022-11-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-423 | Queens 11/13 FLOOR SLAB REPLACEMENT | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-11-20 | 2031-05-12 | 2022-11-27 | 2023-07-31
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-423 | Queens 11/13 FLOOR SLAB REPLACEMENT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-11-20 | 2031-05-12 | 2023-08-01 | 2024-12-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-438 | QUEENS 7 GARAGE REHABILITATION | 1 | PROJECT START | 2015-09-09 | 2015-09-09 | 2015-09-09 | 2015-09-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-438 | QUEENS 7 GARAGE REHABILITATION | 2 | DESIGN START | 2015-09-10 | 2016-11-06 | 2015-09-22 | 2017-04-11
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-438 | QUEENS 7 GARAGE REHABILITATION | 3 | DESIGN COMPLETION | 2016-11-07 | 2018-06-29 | 2017-04-12 | 2019-06-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-438 | QUEENS 7 GARAGE REHABILITATION | 4 | CONSTRUCTION START | 2018-06-30 | 2019-04-03 | 2019-06-18 | 2020-02-12
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-438 | QUEENS 7 GARAGE REHABILITATION | 5 | CONSTRUCTION COMPLETION | 2019-04-04 | 2021-11-21 | 2020-02-13 | 2022-10-31
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANBROAD2 | BROAD CHANNEL LIBRARY GUTTERS AND LEADERS | 1 | DEVELOP SCOPE | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANBROAD2 | BROAD CHANNEL LIBRARY GUTTERS AND LEADERS | 2 | PRELIMINARY DESIGN | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANBROAD2 | BROAD CHANNEL LIBRARY GUTTERS AND LEADERS | 3 | FINAL DESIGN | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANBROAD2 | BROAD CHANNEL LIBRARY GUTTERS AND LEADERS | 4 | BID AWARD AND REGISTER CONTRCT | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANBROAD2 | BROAD CHANNEL LIBRARY GUTTERS AND LEADERS | 5 | CONSTRUCTION TO 25% | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANBROAD2 | BROAD CHANNEL LIBRARY GUTTERS AND LEADERS | 6 | CONSTRUCTION TO 50% | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANBROAD2 | BROAD CHANNEL LIBRARY GUTTERS AND LEADERS | 7 | CONSTRUCTION TO 75% | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANBROAD2 | BROAD CHANNEL LIBRARY GUTTERS AND LEADERS | 8 | ORIGINAL EQUIP & FURNISHING | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANBROAD2 | BROAD CHANNEL LIBRARY GUTTERS AND LEADERS | 9 | SUBSTANTIAL COMPLETION | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANBROAD2 | BROAD CHANNEL LIBRARY GUTTERS AND LEADERS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANBROAD2 | BROAD CHANNEL LIBRARY GUTTERS AND LEADERS | 11 | PROJECT START | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANBROAD2 | BROAD CHANNEL LIBRARY GUTTERS AND LEADERS | 12 | DESIGN START | 2017-03-02 | 2017-09-01 | 2017-03-02 | 2017-09-01
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANBROAD2 | BROAD CHANNEL LIBRARY GUTTERS AND LEADERS | 13 | DESIGN COMPLETION | 2017-09-02 | 2018-09-01 | 2017-09-02 | 2018-09-01
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANBROAD2 | BROAD CHANNEL LIBRARY GUTTERS AND LEADERS | 14 | CONSTRUCTION START | 2018-09-02 | 2019-03-01 | 2018-09-02 | 2019-03-01
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANBROAD2 | BROAD CHANNEL LIBRARY GUTTERS AND LEADERS | 15 | CONSTRUCTION COMPLETION | 2019-03-02 | 2023-03-01 | 2019-03-02 | 2023-03-01
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SAND1187 | Recon of Norton Drive - Hurricane Sandy (HWQ1187, SEQ200595) | 1 | DEVELOP SCOPE | 2017-06-30 | 2017-09-27 | 2017-06-30 | 2017-09-27
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SAND1187 | Recon of Norton Drive - Hurricane Sandy (HWQ1187, SEQ200595) | 2 | PRELIMINARY DESIGN | 2017-09-28 | 2018-01-25 | 2017-09-28 | 2018-01-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SAND1187 | Recon of Norton Drive - Hurricane Sandy (HWQ1187, SEQ200595) | 3 | FINAL DESIGN | 2018-01-26 | 2018-07-24 | 2018-01-26 | 2018-07-24
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SAND1187 | Recon of Norton Drive - Hurricane Sandy (HWQ1187, SEQ200595) | 4 | BID AWARD AND REGISTER CONTRCT | 2018-07-25 | 2018-10-22 | 2018-07-25 | 2018-10-22
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SAND1187 | Recon of Norton Drive - Hurricane Sandy (HWQ1187, SEQ200595) | 5 | CONSTRUCTION TO 25% | 2018-10-23 | 2019-02-19 | 2018-10-23 | 2019-02-19
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SAND1187 | Recon of Norton Drive - Hurricane Sandy (HWQ1187, SEQ200595) | 6 | CONSTRUCTION TO 50% | 2019-02-20 | 2019-06-19 | 2019-02-20 | 2019-06-19
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SAND1187 | Recon of Norton Drive - Hurricane Sandy (HWQ1187, SEQ200595) | 7 | CONSTRUCTION TO 75% | 2019-06-20 | 2019-10-17 | 2019-06-20 | 2019-10-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SAND1187 | Recon of Norton Drive - Hurricane Sandy (HWQ1187, SEQ200595) | 8 | ORIGINAL EQUIP & FURNISHING | 2019-10-18 | 2020-01-15 | 2019-10-18 | 2020-01-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SAND1187 | Recon of Norton Drive - Hurricane Sandy (HWQ1187, SEQ200595) | 9 | SUBSTANTIAL COMPLETION | 2020-01-16 | 2020-03-15 | 2020-01-16 | 2020-03-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SAND1187 | Recon of Norton Drive - Hurricane Sandy (HWQ1187, SEQ200595) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-03-16 | 2020-04-14 | 2020-03-16 | 2027-09-10
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBROAD | SANDY DAMAGES BROAD CHANNEL BRANCH LIBRARY | 1 | PROJECT START | 2012-11-13 | 2012-11-13 | 2012-11-13 | 2012-11-13
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBROAD | SANDY DAMAGES BROAD CHANNEL BRANCH LIBRARY | 2 | DESIGN START | 2012-11-14 | 2012-11-14 | 2012-11-14 | 2012-11-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBROAD | SANDY DAMAGES BROAD CHANNEL BRANCH LIBRARY | 3 | DESIGN COMPLETION | 2012-11-15 | 2012-11-15 | 2012-11-15 | 2012-11-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBROAD | SANDY DAMAGES BROAD CHANNEL BRANCH LIBRARY | 4 | CONSTRUCTION START | 2012-11-19 | 2016-01-13 | 2012-11-17 | 2013-04-06
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBROAD | SANDY DAMAGES BROAD CHANNEL BRANCH LIBRARY | 5 | CONSTRUCTION COMPLETION | 2016-01-14 | 2016-01-14 | 2013-04-07 | 2021-04-07
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDELEC5 | 100 the precint electrical system replacement, Sandy | 1 | PROJECT START | 2013-01-11 | 2013-01-11 | 2013-01-11 | 2013-01-11
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDELEC5 | 100 the precint electrical system replacement, Sandy | 2 | DESIGN START | 2013-01-12 | 2013-01-14 | 2013-01-12 | 2013-01-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDELEC5 | 100 the precint electrical system replacement, Sandy | 3 | DESIGN COMPLETION | 2013-01-15 | 2013-03-18 | 2013-01-15 | 2013-03-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDELEC5 | 100 the precint electrical system replacement, Sandy | 4 | CONSTRUCTION START | 2013-03-19 | 2014-04-09 | 2013-03-19 | 2014-04-09
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDELEC5 | 100 the precint electrical system replacement, Sandy | 5 | CONSTRUCTION COMPLETION | 2014-04-10 | 2014-12-21 | 2014-04-10 | 2021-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW10 | Reconstruction of Willets Point - Hurricane Sandy | 1 | DEVELOP SCOPE | 2016-02-16 | 2016-05-15 | 2016-02-16 | 2016-05-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW10 | Reconstruction of Willets Point - Hurricane Sandy | 2 | PRELIMINARY DESIGN | 2016-05-16 | 2016-09-12 | 2016-05-16 | 2016-09-12
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW10 | Reconstruction of Willets Point - Hurricane Sandy | 3 | FINAL DESIGN | 2016-09-13 | 2017-03-11 | 2016-09-13 | 2017-03-11
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW10 | Reconstruction of Willets Point - Hurricane Sandy | 4 | BID AWARD AND REGISTER CONTRCT | 2017-03-12 | 2017-06-09 | 2017-03-12 | 2017-06-09
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW10 | Reconstruction of Willets Point - Hurricane Sandy | 5 | CONSTRUCTION TO 25% | 2017-06-10 | 2017-10-07 | 2017-06-10 | 2017-10-07
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW10 | Reconstruction of Willets Point - Hurricane Sandy | 6 | CONSTRUCTION TO 50% | 2017-10-08 | 2018-02-04 | 2017-10-08 | 2018-02-04
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW10 | Reconstruction of Willets Point - Hurricane Sandy | 7 | CONSTRUCTION TO 75% | 2018-02-05 | 2018-06-04 | 2018-02-05 | 2018-06-04
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW10 | Reconstruction of Willets Point - Hurricane Sandy | 8 | ORIGINAL EQUIP & FURNISHING | 2018-06-05 | 2018-09-02 | 2018-06-05 | 2018-09-02
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW10 | Reconstruction of Willets Point - Hurricane Sandy | 9 | SUBSTANTIAL COMPLETION | 2018-09-03 | 2018-11-01 | 2018-09-03 | 2018-11-01
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW10 | Reconstruction of Willets Point - Hurricane Sandy | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-11-02 | 2018-12-01 | 2018-11-02 | 2026-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW11 | Recon of Beach Channel Drive - Hurricane Sandy (QED-1030) | 1 | DEVELOP SCOPE | 2016-02-16 | 2016-05-15 | 2014-02-19 | 2014-09-13
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW11 | Recon of Beach Channel Drive - Hurricane Sandy (QED-1030) | 2 | PRELIMINARY DESIGN | 2016-05-16 | 2016-09-12 | 2014-09-14 | 2016-06-07
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW11 | Recon of Beach Channel Drive - Hurricane Sandy (QED-1030) | 3 | FINAL DESIGN | 2016-09-13 | 2017-03-11 | 2016-06-08 | 2016-12-07
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW11 | Recon of Beach Channel Drive - Hurricane Sandy (QED-1030) | 4 | BID AWARD AND REGISTER CONTRCT | 2017-03-12 | 2017-06-09 | 2016-12-08 | 2018-03-12
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW11 | Recon of Beach Channel Drive - Hurricane Sandy (QED-1030) | 5 | CONSTRUCTION TO 25% | 2017-06-10 | 2017-10-07 | 2018-03-13 | 2018-07-10
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW11 | Recon of Beach Channel Drive - Hurricane Sandy (QED-1030) | 6 | CONSTRUCTION TO 50% | 2017-10-08 | 2018-02-04 | 2018-07-11 | 2018-11-07
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW11 | Recon of Beach Channel Drive - Hurricane Sandy (QED-1030) | 7 | CONSTRUCTION TO 75% | 2018-02-05 | 2018-06-04 | 2018-11-08 | 2019-03-07
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW11 | Recon of Beach Channel Drive - Hurricane Sandy (QED-1030) | 8 | ORIGINAL EQUIP & FURNISHING | 2018-06-05 | 2018-09-02 | 2019-03-08 | 2019-06-05
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW11 | Recon of Beach Channel Drive - Hurricane Sandy (QED-1030) | 9 | SUBSTANTIAL COMPLETION | 2018-09-03 | 2018-11-01 | 2019-06-06 | 2019-08-04
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW11 | Recon of Beach Channel Drive - Hurricane Sandy (QED-1030) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-11-02 | 2018-12-01 | 2019-08-05 | 2023-06-07
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW12 | Reconstruction of Edgemere - Hurricane Sandy (QED-1007) | 1 | DEVELOP SCOPE | 2016-02-16 | 2016-05-15 | 2016-02-16 | 2016-05-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW12 | Reconstruction of Edgemere - Hurricane Sandy (QED-1007) | 2 | PRELIMINARY DESIGN | 2016-05-16 | 2016-09-12 | 2016-05-16 | 2016-09-12
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW12 | Reconstruction of Edgemere - Hurricane Sandy (QED-1007) | 3 | FINAL DESIGN | 2016-09-13 | 2017-03-11 | 2016-09-13 | 2017-03-11
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW12 | Reconstruction of Edgemere - Hurricane Sandy (QED-1007) | 4 | BID AWARD AND REGISTER CONTRCT | 2017-03-12 | 2017-06-09 | 2017-03-12 | 2018-08-05
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW12 | Reconstruction of Edgemere - Hurricane Sandy (QED-1007) | 5 | CONSTRUCTION TO 25% | 2017-06-10 | 2017-10-07 | 2018-08-06 | 2018-12-03
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW12 | Reconstruction of Edgemere - Hurricane Sandy (QED-1007) | 6 | CONSTRUCTION TO 50% | 2017-10-08 | 2018-02-04 | 2018-12-04 | 2019-04-02
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW12 | Reconstruction of Edgemere - Hurricane Sandy (QED-1007) | 7 | CONSTRUCTION TO 75% | 2018-02-05 | 2018-06-04 | 2019-04-03 | 2019-07-31
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW12 | Reconstruction of Edgemere - Hurricane Sandy (QED-1007) | 8 | ORIGINAL EQUIP & FURNISHING | 2018-06-05 | 2018-09-02 | 2019-08-01 | 2019-10-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW12 | Reconstruction of Edgemere - Hurricane Sandy (QED-1007) | 9 | SUBSTANTIAL COMPLETION | 2018-09-03 | 2018-11-01 | 2019-10-30 | 2019-12-28
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW12 | Reconstruction of Edgemere - Hurricane Sandy (QED-1007) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-11-02 | 2018-12-01 | 2019-12-29 | 2024-08-02
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW13 | Reconstruction of Rockaway Beach - Hurricane Sandy (QED-982) | 1 | DEVELOP SCOPE | 2016-02-16 | 2016-05-15 | 2016-02-16 | 2016-05-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW13 | Reconstruction of Rockaway Beach - Hurricane Sandy (QED-982) | 2 | PRELIMINARY DESIGN | 2016-05-16 | 2016-09-12 | 2016-05-16 | 2016-09-12
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW13 | Reconstruction of Rockaway Beach - Hurricane Sandy (QED-982) | 3 | FINAL DESIGN | 2016-09-13 | 2017-03-11 | 2016-09-13 | 2017-03-11
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW13 | Reconstruction of Rockaway Beach - Hurricane Sandy (QED-982) | 4 | BID AWARD AND REGISTER CONTRCT | 2017-03-12 | 2017-06-09 | 2017-03-12 | 2017-06-09
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW13 | Reconstruction of Rockaway Beach - Hurricane Sandy (QED-982) | 5 | CONSTRUCTION TO 25% | 2017-06-10 | 2017-10-07 | 2017-06-10 | 2017-10-07
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW13 | Reconstruction of Rockaway Beach - Hurricane Sandy (QED-982) | 6 | CONSTRUCTION TO 50% | 2017-10-08 | 2018-02-04 | 2017-10-08 | 2018-02-04
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW13 | Reconstruction of Rockaway Beach - Hurricane Sandy (QED-982) | 7 | CONSTRUCTION TO 75% | 2018-02-05 | 2018-06-04 | 2018-02-05 | 2018-06-04
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW13 | Reconstruction of Rockaway Beach - Hurricane Sandy (QED-982) | 8 | ORIGINAL EQUIP & FURNISHING | 2018-06-05 | 2018-09-02 | 2018-06-05 | 2018-09-02
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW13 | Reconstruction of Rockaway Beach - Hurricane Sandy (QED-982) | 9 | SUBSTANTIAL COMPLETION | 2018-09-03 | 2018-11-01 | 2018-09-03 | 2018-11-01
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW13 | Reconstruction of Rockaway Beach - Hurricane Sandy (QED-982) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-11-02 | 2018-12-01 | 2018-11-02 | 2029-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW24 | WHEN AND WHERE HURRICANE SANDY - QUEENS | 1 | DEVELOP SCOPE | 2013-08-18 | 2013-11-15 | 2013-08-18 | 2013-11-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW24 | WHEN AND WHERE HURRICANE SANDY - QUEENS | 2 | PRELIMINARY DESIGN | 2013-11-16 | 2014-03-15 | 2013-11-16 | 2014-03-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW24 | WHEN AND WHERE HURRICANE SANDY - QUEENS | 3 | FINAL DESIGN | 2014-03-16 | 2014-09-11 | 2014-03-16 | 2014-09-11
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW24 | WHEN AND WHERE HURRICANE SANDY - QUEENS | 4 | BID AWARD AND REGISTER CONTRCT | 2014-09-12 | 2014-12-10 | 2014-09-12 | 2014-12-10
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW24 | WHEN AND WHERE HURRICANE SANDY - QUEENS | 5 | CONSTRUCTION TO 25% | 2014-12-11 | 2015-10-06 | 2014-12-11 | 2015-10-06
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW24 | WHEN AND WHERE HURRICANE SANDY - QUEENS | 6 | CONSTRUCTION TO 50% | 2015-10-07 | 2016-08-01 | 2015-10-07 | 2016-08-01
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW24 | WHEN AND WHERE HURRICANE SANDY - QUEENS | 7 | CONSTRUCTION TO 75% | 2016-08-02 | 2017-05-28 | 2016-08-02 | 2017-05-28
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW24 | WHEN AND WHERE HURRICANE SANDY - QUEENS | 8 | ORIGINAL EQUIP & FURNISHING | 2017-05-29 | 2017-08-26 | 2017-05-29 | 2017-08-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW24 | WHEN AND WHERE HURRICANE SANDY - QUEENS | 9 | SUBSTANTIAL COMPLETION | 2017-08-27 | 2017-10-25 | 2017-08-27 | 2017-10-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW24 | WHEN AND WHERE HURRICANE SANDY - QUEENS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-10-26 | 2017-12-24 | 2017-10-26 | 2027-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW26 | Reconstruction of East 10th Road - Hurricane Sandy | 1 | DEVELOP SCOPE | 2014-02-17 | 2014-05-16 | 2014-02-17 | 2014-05-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW26 | Reconstruction of East 10th Road - Hurricane Sandy | 2 | PRELIMINARY DESIGN | 2014-05-17 | 2015-05-16 | 2014-05-17 | 2015-05-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW26 | Reconstruction of East 10th Road - Hurricane Sandy | 3 | FINAL DESIGN | 2015-09-14 | 2017-03-12 | 2015-09-14 | 2017-03-12
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW26 | Reconstruction of East 10th Road - Hurricane Sandy | 4 | BID AWARD AND REGISTER CONTRCT | 2017-03-13 | 2017-06-01 | 2017-03-13 | 2017-06-01
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW26 | Reconstruction of East 10th Road - Hurricane Sandy | 5 | CONSTRUCTION TO 25% | 2017-06-02 | 2017-09-29 | 2017-06-02 | 2017-09-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW26 | Reconstruction of East 10th Road - Hurricane Sandy | 6 | CONSTRUCTION TO 50% | 2017-09-30 | 2018-01-27 | 2017-09-30 | 2018-01-27
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW26 | Reconstruction of East 10th Road - Hurricane Sandy | 7 | CONSTRUCTION TO 75% | 2018-01-28 | 2018-05-27 | 2018-01-28 | 2018-05-27
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW26 | Reconstruction of East 10th Road - Hurricane Sandy | 8 | ORIGINAL EQUIP & FURNISHING | 2018-05-28 | 2018-08-25 | 2018-05-28 | 2018-08-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW26 | Reconstruction of East 10th Road - Hurricane Sandy | 9 | SUBSTANTIAL COMPLETION | 2018-08-26 | 2018-10-24 | 2018-08-26 | 2018-10-24
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW26 | Reconstruction of East 10th Road - Hurricane Sandy | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-10-25 | 2018-11-23 | 2018-10-25 | 2028-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR02 | FAR ROCKAWAY BUSINESS DISTRICT IMPROVEMENTS (SE-830) | 1 | DEVELOP SCOPE | 2011-06-01 | 2011-09-28 | 2017-03-01 | 2017-05-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR02 | FAR ROCKAWAY BUSINESS DISTRICT IMPROVEMENTS (SE-830) | 2 | DESIGN START | 2011-09-29 | 2013-03-21 | 2017-05-30 | 2017-09-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR02 | FAR ROCKAWAY BUSINESS DISTRICT IMPROVEMENTS (SE-830) | 3 | CONSTRUCTION START | 2013-03-22 | 2015-03-11 | 2017-09-27 | 2018-03-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR02 | FAR ROCKAWAY BUSINESS DISTRICT IMPROVEMENTS (SE-830) | 4 | BID AWARD AND REGISTER CONTRCT | 2013-03-22 | 2015-03-11 | 2018-03-26 | 2018-06-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR02 | FAR ROCKAWAY BUSINESS DISTRICT IMPROVEMENTS (SE-830) | 5 | CONSTRUCTION TO 25% | 2013-03-22 | 2015-03-11 | 2018-06-24 | 2018-10-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR02 | FAR ROCKAWAY BUSINESS DISTRICT IMPROVEMENTS (SE-830) | 6 | CONSTRUCTION TO 50% | 2013-03-22 | 2015-03-11 | 2018-10-22 | 2019-02-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR02 | FAR ROCKAWAY BUSINESS DISTRICT IMPROVEMENTS (SE-830) | 7 | CONSTRUCTION TO 75% | 2013-03-22 | 2015-03-11 | 2019-02-19 | 2019-06-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR02 | FAR ROCKAWAY BUSINESS DISTRICT IMPROVEMENTS (SE-830) | 8 | ORIGINAL EQUIP & FURNISHING | 2013-03-22 | 2015-03-11 | 2019-06-19 | 2019-09-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR02 | FAR ROCKAWAY BUSINESS DISTRICT IMPROVEMENTS (SE-830) | 9 | SUBSTANTIAL COMPLETION | 2013-03-22 | 2015-03-11 | 2019-09-17 | 2020-01-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR02 | FAR ROCKAWAY BUSINESS DISTRICT IMPROVEMENTS (SE-830) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-03-22 | 2015-03-11 | 2020-01-15 | 2025-08-12
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR04 | Beach 108th Streetscape Improvements (QED-1044) | 1 | DEVELOP SCOPE | 2012-09-30 | 2012-12-28 | 2017-09-30 | 2017-12-28
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR04 | Beach 108th Streetscape Improvements (QED-1044) | 2 | PRELIMINARY DESIGN | 2012-12-29 | 2013-04-27 | 2017-12-29 | 2018-04-27
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR04 | Beach 108th Streetscape Improvements (QED-1044) | 3 | FINAL DESIGN | 2013-04-28 | 2013-10-24 | 2018-04-28 | 2018-10-24
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR04 | Beach 108th Streetscape Improvements (QED-1044) | 4 | BID AWARD AND REGISTER CONTRCT | 2013-10-25 | 2014-01-22 | 2018-10-25 | 2019-01-22
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR04 | Beach 108th Streetscape Improvements (QED-1044) | 5 | CONSTRUCTION TO 25% | 2014-01-23 | 2014-05-22 | 2019-01-23 | 2019-05-22
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR04 | Beach 108th Streetscape Improvements (QED-1044) | 6 | CONSTRUCTION TO 50% | 2014-05-23 | 2014-09-19 | 2019-05-23 | 2019-09-19
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR04 | Beach 108th Streetscape Improvements (QED-1044) | 7 | CONSTRUCTION TO 75% | 2014-09-20 | 2015-01-17 | 2019-09-20 | 2020-01-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR04 | Beach 108th Streetscape Improvements (QED-1044) | 8 | ORIGINAL EQUIP & FURNISHING | 2015-01-18 | 2015-04-17 | 2020-01-18 | 2020-04-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR04 | Beach 108th Streetscape Improvements (QED-1044) | 9 | SUBSTANTIAL COMPLETION | 2015-04-18 | 2015-06-16 | 2020-04-17 | 2020-06-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR04 | Beach 108th Streetscape Improvements (QED-1044) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-06-17 | 2015-07-16 | 2020-06-16 | 2025-06-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDY4-30 | Tide Gate - FEMA 406 In-Kind, HMP & 428 Conduit HBPED800Q | 1 | DEVELOP SCOPE | 2017-03-01 | 2017-05-29 | 2017-03-01 | 2017-05-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDY4-30 | Tide Gate - FEMA 406 In-Kind, HMP & 428 Conduit HBPED800Q | 2 | PRELIMINARY DESIGN | 2017-05-30 | 2017-09-26 | 2017-05-30 | 2017-09-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDY4-30 | Tide Gate - FEMA 406 In-Kind, HMP & 428 Conduit HBPED800Q | 3 | FINAL DESIGN | 2017-09-27 | 2018-03-25 | 2017-09-27 | 2018-03-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDY4-30 | Tide Gate - FEMA 406 In-Kind, HMP & 428 Conduit HBPED800Q | 4 | BID AWARD AND REGISTER CONTRCT | 2018-03-26 | 2018-06-23 | 2018-03-26 | 2018-06-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDY4-30 | Tide Gate - FEMA 406 In-Kind, HMP & 428 Conduit HBPED800Q | 5 | CONSTRUCTION TO 25% | 2018-06-24 | 2018-10-21 | 2018-06-24 | 2018-10-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDY4-30 | Tide Gate - FEMA 406 In-Kind, HMP & 428 Conduit HBPED800Q | 6 | CONSTRUCTION TO 50% | 2018-10-22 | 2019-02-18 | 2018-10-22 | 2019-02-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDY4-30 | Tide Gate - FEMA 406 In-Kind, HMP & 428 Conduit HBPED800Q | 7 | CONSTRUCTION TO 75% | 2019-02-19 | 2019-06-18 | 2019-02-19 | 2019-06-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDY4-30 | Tide Gate - FEMA 406 In-Kind, HMP & 428 Conduit HBPED800Q | 8 | ORIGINAL EQUIP & FURNISHING | 2019-06-19 | 2019-09-16 | 2019-06-19 | 2019-09-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDY4-30 | Tide Gate - FEMA 406 In-Kind, HMP & 428 Conduit HBPED800Q | 9 | SUBSTANTIAL COMPLETION | 2019-09-17 | 2019-11-15 | 2019-09-17 | 2019-11-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDY4-30 | Tide Gate - FEMA 406 In-Kind, HMP & 428 Conduit HBPED800Q | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-11-16 | 2019-12-15 | 2019-11-16 | 2023-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDY4-31 | Tide Gate - 404 HMGP HBPED800Q | 1 | DEVELOP SCOPE | 2018-03-01 | 2018-05-29 | 2018-03-01 | 2018-05-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDY4-31 | Tide Gate - 404 HMGP HBPED800Q | 2 | PRELIMINARY DESIGN | 2018-05-30 | 2018-09-26 | 2018-05-30 | 2018-09-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDY4-31 | Tide Gate - 404 HMGP HBPED800Q | 3 | FINAL DESIGN | 2018-09-27 | 2019-03-25 | 2018-09-27 | 2019-03-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDY4-31 | Tide Gate - 404 HMGP HBPED800Q | 4 | BID AWARD AND REGISTER CONTRCT | 2019-03-26 | 2019-06-23 | 2019-03-26 | 2019-06-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDY4-31 | Tide Gate - 404 HMGP HBPED800Q | 5 | CONSTRUCTION TO 25% | 2019-06-24 | 2019-10-21 | 2019-06-24 | 2019-10-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDY4-31 | Tide Gate - 404 HMGP HBPED800Q | 6 | CONSTRUCTION TO 50% | 2019-10-22 | 2020-02-18 | 2019-10-22 | 2020-02-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDY4-31 | Tide Gate - 404 HMGP HBPED800Q | 7 | CONSTRUCTION TO 75% | 2020-02-19 | 2020-06-17 | 2020-02-19 | 2020-06-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDY4-31 | Tide Gate - 404 HMGP HBPED800Q | 8 | ORIGINAL EQUIP & FURNISHING | 2020-06-18 | 2020-09-15 | 2020-06-18 | 2020-09-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDY4-31 | Tide Gate - 404 HMGP HBPED800Q | 9 | SUBSTANTIAL COMPLETION | 2020-09-16 | 2020-11-14 | 2020-09-16 | 2020-11-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDY4-31 | Tide Gate - 404 HMGP HBPED800Q | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-11-15 | 2020-12-14 | 2020-11-15 | 2025-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDY4-50 | SANDY-Rockaway Operational Headquarters Reconstruction | 1 | PROJECT START | 2023-07-01 | 2023-07-01 | 2022-06-01 | 2022-12-31
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDY4-50 | SANDY-Rockaway Operational Headquarters Reconstruction | 2 | DESIGN START | 2023-07-02 | 2023-07-02 | 2023-01-01 | 2023-08-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDY4-50 | SANDY-Rockaway Operational Headquarters Reconstruction | 3 | DESIGN COMPLETION | 2023-07-03 | 2023-07-03 | 2023-08-31 | 2023-08-31
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDY4-50 | SANDY-Rockaway Operational Headquarters Reconstruction | 4 | CONSTRUCTION START | 2023-07-04 | 2023-07-04 | 2023-09-01 | 2023-09-01
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDY4-50 | SANDY-Rockaway Operational Headquarters Reconstruction | 5 | CONSTRUCTION COMPLETION | 2023-07-05 | 2023-07-05 | 2023-09-02 | 2024-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-785 | STORM SEWER IN 110 AV - SUTPHIN BLVD AND 173 ST | 1 | DEVELOP SCOPE | 2003-07-01 | 2003-09-28 | 1997-05-04 | 1997-08-01
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-785 | STORM SEWER IN 110 AV - SUTPHIN BLVD AND 173 ST | 2 | PRELIMINARY DESIGN | 2003-09-29 | 2004-01-26 | 1997-08-02 | 1997-11-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-785 | STORM SEWER IN 110 AV - SUTPHIN BLVD AND 173 ST | 3 | FINAL DESIGN | 2004-01-27 | 2004-07-24 | 1997-11-30 | 1998-05-28
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-785 | STORM SEWER IN 110 AV - SUTPHIN BLVD AND 173 ST | 4 | BID AWARD AND REGISTER CONTRCT | 2004-07-25 | 2004-10-22 | 2006-02-12 | 2006-05-12
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-785 | STORM SEWER IN 110 AV - SUTPHIN BLVD AND 173 ST | 5 | CONSTRUCTION TO 25% | 2004-10-23 | 2005-02-19 | 2006-05-13 | 2006-05-12
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-785 | STORM SEWER IN 110 AV - SUTPHIN BLVD AND 173 ST | 6 | CONSTRUCTION TO 50% | 2005-02-20 | 2005-06-19 | 2006-05-13 | 2006-05-12
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-785 | STORM SEWER IN 110 AV - SUTPHIN BLVD AND 173 ST | 7 | CONSTRUCTION TO 75% | 2005-06-20 | 2005-10-17 | 2006-05-13 | 2006-05-12
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-785 | STORM SEWER IN 110 AV - SUTPHIN BLVD AND 173 ST | 8 | ORIGINAL EQUIP & FURNISHING | 2005-10-18 | 2006-01-15 | 2006-05-13 | 2006-05-12
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-785 | STORM SEWER IN 110 AV - SUTPHIN BLVD AND 173 ST | 9 | SUBSTANTIAL COMPLETION | 2006-01-16 | 2006-03-16 | 2006-05-13 | 2006-05-12
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-785 | STORM SEWER IN 110 AV - SUTPHIN BLVD AND 173 ST | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2006-03-17 | 2006-04-15 | 2012-05-13 | 2021-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-789B-3 | B 63 ST - BAYFIELD AV & ROCKAWAY FWAY (SOMMERVILLE III) | 1 | DEVELOP SCOPE | 2010-06-28 | 2010-09-25 | 2010-06-28 | 2010-09-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-789B-3 | B 63 ST - BAYFIELD AV & ROCKAWAY FWAY (SOMMERVILLE III) | 2 | PRELIMINARY DESIGN | 2010-09-26 | 2011-01-23 | 2010-09-26 | 2011-01-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-789B-3 | B 63 ST - BAYFIELD AV & ROCKAWAY FWAY (SOMMERVILLE III) | 3 | FINAL DESIGN | 2011-01-24 | 2011-07-22 | 2011-01-24 | 2011-07-22
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-789B-3 | B 63 ST - BAYFIELD AV & ROCKAWAY FWAY (SOMMERVILLE III) | 4 | BID AWARD AND REGISTER CONTRCT | 2011-07-23 | 2011-10-20 | 2011-07-23 | 2011-10-20
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-789B-3 | B 63 ST - BAYFIELD AV & ROCKAWAY FWAY (SOMMERVILLE III) | 5 | CONSTRUCTION TO 25% | 2011-10-21 | 2012-02-17 | 2022-02-16 | 2022-06-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-789B-3 | B 63 ST - BAYFIELD AV & ROCKAWAY FWAY (SOMMERVILLE III) | 6 | CONSTRUCTION TO 50% | 2012-02-18 | 2012-06-16 | 2022-06-16 | 2022-06-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-789B-3 | B 63 ST - BAYFIELD AV & ROCKAWAY FWAY (SOMMERVILLE III) | 7 | CONSTRUCTION TO 75% | 2012-06-17 | 2012-10-14 | 2022-06-16 | 2022-06-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-789B-3 | B 63 ST - BAYFIELD AV & ROCKAWAY FWAY (SOMMERVILLE III) | 8 | ORIGINAL EQUIP & FURNISHING | 2012-10-15 | 2013-01-12 | 2022-06-16 | 2022-06-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-789B-3 | B 63 ST - BAYFIELD AV & ROCKAWAY FWAY (SOMMERVILLE III) | 9 | SUBSTANTIAL COMPLETION | 2013-01-13 | 2013-03-13 | 2022-06-16 | 2022-06-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-789B-3 | B 63 ST - BAYFIELD AV & ROCKAWAY FWAY (SOMMERVILLE III) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-03-14 | 2013-04-12 | 2023-11-29 | 2023-12-28
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-795 | Storm & Sani Sewer in Chandler St - Nameoke Av & Battery Rd | 1 | DEVELOP SCOPE | 2008-02-20 | 2008-05-19 | 2008-02-20 | 2008-05-19
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-795 | Storm & Sani Sewer in Chandler St - Nameoke Av & Battery Rd | 2 | PRELIMINARY DESIGN | 2008-05-20 | 2008-09-16 | 2008-05-20 | 2008-09-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-795 | Storm & Sani Sewer in Chandler St - Nameoke Av & Battery Rd | 3 | FINAL DESIGN | 2008-09-17 | 2009-03-15 | 2008-09-17 | 2009-03-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-795 | Storm & Sani Sewer in Chandler St - Nameoke Av & Battery Rd | 4 | BID AWARD AND REGISTER CONTRCT | 2009-03-16 | 2009-06-13 | 2011-03-04 | 2011-06-01
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-795 | Storm & Sani Sewer in Chandler St - Nameoke Av & Battery Rd | 5 | CONSTRUCTION TO 25% | 2009-06-14 | 2009-10-11 | 2011-06-02 | 2011-06-01
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-795 | Storm & Sani Sewer in Chandler St - Nameoke Av & Battery Rd | 6 | CONSTRUCTION TO 50% | 2009-10-12 | 2010-02-08 | 2011-06-02 | 2011-06-01
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-795 | Storm & Sani Sewer in Chandler St - Nameoke Av & Battery Rd | 7 | CONSTRUCTION TO 75% | 2010-02-09 | 2010-06-08 | 2011-06-02 | 2011-06-01
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-795 | Storm & Sani Sewer in Chandler St - Nameoke Av & Battery Rd | 8 | ORIGINAL EQUIP & FURNISHING | 2010-06-09 | 2010-09-06 | 2011-06-02 | 2011-06-01
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-795 | Storm & Sani Sewer in Chandler St - Nameoke Av & Battery Rd | 9 | SUBSTANTIAL COMPLETION | 2010-09-07 | 2010-11-05 | 2011-06-02 | 2011-06-01
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-795 | Storm & Sani Sewer in Chandler St - Nameoke Av & Battery Rd | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2010-11-06 | 2010-12-05 | 2013-06-02 | 2022-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-807 | Storm & San Sewers in 20th Ave b/t 126 St & US Bulkhead Line | 1 | DEVELOP SCOPE | 2012-06-30 | 2013-03-26 | 2012-06-30 | 2013-03-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-807 | Storm & San Sewers in 20th Ave b/t 126 St & US Bulkhead Line | 2 | PRELIMINARY DESIGN | 2013-03-27 | 2014-03-21 | 2013-03-27 | 2014-03-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-807 | Storm & San Sewers in 20th Ave b/t 126 St & US Bulkhead Line | 3 | FINAL DESIGN | 2014-03-22 | 2015-09-12 | 2014-03-22 | 2015-09-12
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-807 | Storm & San Sewers in 20th Ave b/t 126 St & US Bulkhead Line | 4 | BID AWARD AND REGISTER CONTRCT | 2015-09-13 | 2016-06-08 | 2015-09-13 | 2016-06-08
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-807 | Storm & San Sewers in 20th Ave b/t 126 St & US Bulkhead Line | 5 | CONSTRUCTION TO 25% | 2016-06-09 | 2017-06-03 | 2016-06-09 | 2017-06-03
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-807 | Storm & San Sewers in 20th Ave b/t 126 St & US Bulkhead Line | 6 | CONSTRUCTION TO 50% | 2017-06-04 | 2018-05-29 | 2017-06-04 | 2018-05-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-807 | Storm & San Sewers in 20th Ave b/t 126 St & US Bulkhead Line | 7 | CONSTRUCTION TO 75% | 2018-05-30 | 2019-05-24 | 2018-05-30 | 2019-05-24
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-807 | Storm & San Sewers in 20th Ave b/t 126 St & US Bulkhead Line | 8 | ORIGINAL EQUIP & FURNISHING | 2019-05-25 | 2020-02-18 | 2019-05-25 | 2020-02-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-807 | Storm & San Sewers in 20th Ave b/t 126 St & US Bulkhead Line | 9 | SUBSTANTIAL COMPLETION | 2020-02-19 | 2020-08-16 | 2020-02-19 | 2020-08-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-807 | Storm & San Sewers in 20th Ave b/t 126 St & US Bulkhead Line | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-08-17 | 2020-11-14 | 2020-08-17 | 2020-11-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-809 | STORM & SAN SEWERS IN N.B WHITESTONE EXPWY SERV RD PHASE 1 | 1 | DEVELOP SCOPE | 2008-06-30 | 2009-03-26 | 2008-06-30 | 2009-03-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-809 | STORM & SAN SEWERS IN N.B WHITESTONE EXPWY SERV RD PHASE 1 | 2 | PRELIMINARY DESIGN | 2009-03-27 | 2010-03-21 | 2009-03-27 | 2010-03-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-809 | STORM & SAN SEWERS IN N.B WHITESTONE EXPWY SERV RD PHASE 1 | 3 | FINAL DESIGN | 2010-03-22 | 2011-09-12 | 2010-03-22 | 2011-09-12
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-809 | STORM & SAN SEWERS IN N.B WHITESTONE EXPWY SERV RD PHASE 1 | 4 | BID AWARD AND REGISTER CONTRCT | 2011-09-13 | 2012-06-08 | 2011-09-13 | 2012-06-08
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-809 | STORM & SAN SEWERS IN N.B WHITESTONE EXPWY SERV RD PHASE 1 | 5 | CONSTRUCTION TO 25% | 2012-06-09 | 2013-06-03 | 2012-06-09 | 2013-06-03
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-809 | STORM & SAN SEWERS IN N.B WHITESTONE EXPWY SERV RD PHASE 1 | 6 | CONSTRUCTION TO 50% | 2013-06-04 | 2014-05-29 | 2013-06-04 | 2014-05-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-809 | STORM & SAN SEWERS IN N.B WHITESTONE EXPWY SERV RD PHASE 1 | 7 | CONSTRUCTION TO 75% | 2014-05-30 | 2015-05-24 | 2014-05-30 | 2017-12-01
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-809 | STORM & SAN SEWERS IN N.B WHITESTONE EXPWY SERV RD PHASE 1 | 8 | ORIGINAL EQUIP & FURNISHING | 2015-05-25 | 2016-02-18 | 2017-12-02 | 2018-08-28
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-809 | STORM & SAN SEWERS IN N.B WHITESTONE EXPWY SERV RD PHASE 1 | 9 | SUBSTANTIAL COMPLETION | 2016-02-19 | 2016-08-16 | 2018-08-29 | 2019-02-24
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-809 | STORM & SAN SEWERS IN N.B WHITESTONE EXPWY SERV RD PHASE 1 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-08-17 | 2016-11-14 | 2019-02-25 | 2022-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-810 | STORM & SAN SWR, WILLET PT BLVD WHITESTONE AREA PHASE 2 | 1 | DEVELOP SCOPE | 2010-06-30 | 2011-03-26 | 2010-06-30 | 2011-03-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-810 | STORM & SAN SWR, WILLET PT BLVD WHITESTONE AREA PHASE 2 | 2 | PRELIMINARY DESIGN | 2011-03-27 | 2012-03-20 | 2011-03-27 | 2012-03-20
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-810 | STORM & SAN SWR, WILLET PT BLVD WHITESTONE AREA PHASE 2 | 3 | FINAL DESIGN | 2012-03-21 | 2013-09-11 | 2012-03-21 | 2013-09-11
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-810 | STORM & SAN SWR, WILLET PT BLVD WHITESTONE AREA PHASE 2 | 4 | BID AWARD AND REGISTER CONTRCT | 2013-09-12 | 2014-06-08 | 2013-09-12 | 2014-06-08
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-810 | STORM & SAN SWR, WILLET PT BLVD WHITESTONE AREA PHASE 2 | 5 | CONSTRUCTION TO 25% | 2014-06-09 | 2015-06-03 | 2014-06-09 | 2015-06-03
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-810 | STORM & SAN SWR, WILLET PT BLVD WHITESTONE AREA PHASE 2 | 6 | CONSTRUCTION TO 50% | 2015-06-04 | 2016-05-28 | 2015-06-04 | 2016-05-28
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-810 | STORM & SAN SWR, WILLET PT BLVD WHITESTONE AREA PHASE 2 | 7 | CONSTRUCTION TO 75% | 2016-05-29 | 2017-05-23 | 2016-05-29 | 2017-05-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-810 | STORM & SAN SWR, WILLET PT BLVD WHITESTONE AREA PHASE 2 | 8 | ORIGINAL EQUIP & FURNISHING | 2017-05-24 | 2018-02-17 | 2017-05-24 | 2018-02-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-810 | STORM & SAN SWR, WILLET PT BLVD WHITESTONE AREA PHASE 2 | 9 | SUBSTANTIAL COMPLETION | 2018-02-18 | 2018-08-16 | 2018-02-18 | 2018-08-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-810 | STORM & SAN SWR, WILLET PT BLVD WHITESTONE AREA PHASE 2 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-08-17 | 2018-11-14 | 2018-08-17 | 2025-09-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-811 | STORM & SAN SWR, N.B. WHITESTONE EXPWY SERV RD PHASE 3 | 1 | DEVELOP SCOPE | 2010-06-30 | 2011-03-26 | 2010-06-30 | 2016-07-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-811 | STORM & SAN SWR, N.B. WHITESTONE EXPWY SERV RD PHASE 3 | 2 | PRELIMINARY DESIGN | 2011-03-27 | 2012-03-20 | 2016-07-15 | 2017-07-09
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-811 | STORM & SAN SWR, N.B. WHITESTONE EXPWY SERV RD PHASE 3 | 3 | FINAL DESIGN | 2012-03-21 | 2013-09-11 | 2017-07-10 | 2018-12-31
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-811 | STORM & SAN SWR, N.B. WHITESTONE EXPWY SERV RD PHASE 3 | 4 | BID AWARD AND REGISTER CONTRCT | 2013-09-12 | 2014-06-08 | 2019-01-01 | 2019-09-27
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-811 | STORM & SAN SWR, N.B. WHITESTONE EXPWY SERV RD PHASE 3 | 5 | CONSTRUCTION TO 25% | 2014-06-09 | 2015-06-03 | 2019-09-28 | 2020-09-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-811 | STORM & SAN SWR, N.B. WHITESTONE EXPWY SERV RD PHASE 3 | 6 | CONSTRUCTION TO 50% | 2015-06-04 | 2016-05-28 | 2020-09-22 | 2021-09-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-811 | STORM & SAN SWR, N.B. WHITESTONE EXPWY SERV RD PHASE 3 | 7 | CONSTRUCTION TO 75% | 2016-05-29 | 2017-05-23 | 2021-09-17 | 2022-09-11
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-811 | STORM & SAN SWR, N.B. WHITESTONE EXPWY SERV RD PHASE 3 | 8 | ORIGINAL EQUIP & FURNISHING | 2017-05-24 | 2018-02-17 | 2022-09-12 | 2023-06-08
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-811 | STORM & SAN SWR, N.B. WHITESTONE EXPWY SERV RD PHASE 3 | 9 | SUBSTANTIAL COMPLETION | 2018-02-18 | 2018-08-16 | 2023-06-09 | 2023-12-05
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-811 | STORM & SAN SWR, N.B. WHITESTONE EXPWY SERV RD PHASE 3 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-08-17 | 2018-11-14 | 2023-12-06 | 2024-03-04
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-823 | SEQ - 229th Street Laurelton Area - Part 1, Phase A (HWQ823) | 1 | DEVELOP SCOPE | 2014-03-05 | 2014-06-02 | 2014-03-05 | 2014-06-02
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-823 | SEQ - 229th Street Laurelton Area - Part 1, Phase A (HWQ823) | 2 | PRELIMINARY DESIGN | 2014-06-03 | 2014-09-30 | 2014-06-03 | 2015-04-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-823 | SEQ - 229th Street Laurelton Area - Part 1, Phase A (HWQ823) | 3 | FINAL DESIGN | 2014-10-01 | 2015-03-29 | 2015-05-01 | 2017-12-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-823 | SEQ - 229th Street Laurelton Area - Part 1, Phase A (HWQ823) | 4 | BID AWARD AND REGISTER CONTRCT | 2015-03-30 | 2015-06-27 | 2017-12-16 | 2018-07-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-823 | SEQ - 229th Street Laurelton Area - Part 1, Phase A (HWQ823) | 5 | CONSTRUCTION TO 25% | 2015-06-28 | 2015-10-25 | 2018-07-30 | 2018-11-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-823 | SEQ - 229th Street Laurelton Area - Part 1, Phase A (HWQ823) | 6 | CONSTRUCTION TO 50% | 2015-10-26 | 2016-02-22 | 2018-11-27 | 2019-03-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-823 | SEQ - 229th Street Laurelton Area - Part 1, Phase A (HWQ823) | 7 | CONSTRUCTION TO 75% | 2016-02-23 | 2016-06-21 | 2019-03-27 | 2019-07-24
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-823 | SEQ - 229th Street Laurelton Area - Part 1, Phase A (HWQ823) | 8 | ORIGINAL EQUIP & FURNISHING | 2016-06-22 | 2016-09-19 | 2019-07-25 | 2019-10-22
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-823 | SEQ - 229th Street Laurelton Area - Part 1, Phase A (HWQ823) | 9 | SUBSTANTIAL COMPLETION | 2016-09-20 | 2016-11-18 | 2019-10-23 | 2019-12-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-823 | SEQ - 229th Street Laurelton Area - Part 1, Phase A (HWQ823) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-11-19 | 2016-12-18 | 2019-12-22 | 2022-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-824 | SEQ - 230th Place Laurelton Area - Part 1, Phase B | 1 | DEVELOP SCOPE | 2017-03-01 | 2017-05-29 | 2017-03-01 | 2017-05-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-824 | SEQ - 230th Place Laurelton Area - Part 1, Phase B | 2 | PRELIMINARY DESIGN | 2017-05-30 | 2017-09-26 | 2017-05-30 | 2017-09-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-824 | SEQ - 230th Place Laurelton Area - Part 1, Phase B | 3 | FINAL DESIGN | 2017-09-27 | 2018-03-25 | 2017-09-27 | 2018-03-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-824 | SEQ - 230th Place Laurelton Area - Part 1, Phase B | 4 | BID AWARD AND REGISTER CONTRCT | 2018-03-26 | 2018-06-23 | 2018-03-26 | 2018-06-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-824 | SEQ - 230th Place Laurelton Area - Part 1, Phase B | 5 | CONSTRUCTION TO 25% | 2018-06-24 | 2018-10-21 | 2018-06-24 | 2018-10-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-824 | SEQ - 230th Place Laurelton Area - Part 1, Phase B | 6 | CONSTRUCTION TO 50% | 2018-10-22 | 2019-02-18 | 2018-10-22 | 2019-02-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-824 | SEQ - 230th Place Laurelton Area - Part 1, Phase B | 7 | CONSTRUCTION TO 75% | 2019-02-19 | 2019-06-18 | 2019-02-19 | 2019-06-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-824 | SEQ - 230th Place Laurelton Area - Part 1, Phase B | 8 | ORIGINAL EQUIP & FURNISHING | 2019-06-19 | 2019-09-16 | 2019-06-19 | 2019-09-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-824 | SEQ - 230th Place Laurelton Area - Part 1, Phase B | 9 | SUBSTANTIAL COMPLETION | 2019-09-17 | 2019-11-15 | 2019-09-17 | 2019-11-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-824 | SEQ - 230th Place Laurelton Area - Part 1, Phase B | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-11-16 | 2019-12-15 | 2019-11-16 | 2028-10-28
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-825 | SEQ - Laurelton Area - Part 1, Phase C | 1 | DEVELOP SCOPE | 2017-03-01 | 2017-05-29 | 2017-03-01 | 2017-05-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-825 | SEQ - Laurelton Area - Part 1, Phase C | 2 | PRELIMINARY DESIGN | 2017-05-30 | 2017-09-26 | 2017-05-30 | 2017-09-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-825 | SEQ - Laurelton Area - Part 1, Phase C | 3 | FINAL DESIGN | 2017-09-27 | 2018-03-25 | 2017-09-27 | 2018-03-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-825 | SEQ - Laurelton Area - Part 1, Phase C | 4 | BID AWARD AND REGISTER CONTRCT | 2018-03-26 | 2018-06-23 | 2018-03-26 | 2018-06-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-825 | SEQ - Laurelton Area - Part 1, Phase C | 5 | CONSTRUCTION TO 25% | 2018-06-24 | 2018-10-21 | 2018-06-24 | 2018-10-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-825 | SEQ - Laurelton Area - Part 1, Phase C | 6 | CONSTRUCTION TO 50% | 2018-10-22 | 2019-02-18 | 2018-10-22 | 2019-02-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-825 | SEQ - Laurelton Area - Part 1, Phase C | 7 | CONSTRUCTION TO 75% | 2019-02-19 | 2019-06-18 | 2019-02-19 | 2019-06-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-825 | SEQ - Laurelton Area - Part 1, Phase C | 8 | ORIGINAL EQUIP & FURNISHING | 2019-06-19 | 2019-09-16 | 2019-06-19 | 2019-09-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-825 | SEQ - Laurelton Area - Part 1, Phase C | 9 | SUBSTANTIAL COMPLETION | 2019-09-17 | 2019-11-15 | 2019-09-17 | 2019-11-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-825 | SEQ - Laurelton Area - Part 1, Phase C | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-11-16 | 2019-12-15 | 2019-11-16 | 2029-06-22
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-829 | NDF -- Storm and Sanitary Sewers in Brundwick Ave, Queens | 1 | DEVELOP SCOPE | 2012-05-25 | 2013-02-18 | 2012-05-25 | 2013-02-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-829 | NDF -- Storm and Sanitary Sewers in Brundwick Ave, Queens | 2 | PRELIMINARY DESIGN | 2013-02-19 | 2014-02-13 | 2020-01-15 | 2021-02-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-829 | NDF -- Storm and Sanitary Sewers in Brundwick Ave, Queens | 3 | FINAL DESIGN | 2014-02-14 | 2015-08-07 | 2021-02-16 | 2022-01-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-829 | NDF -- Storm and Sanitary Sewers in Brundwick Ave, Queens | 4 | BID AWARD AND REGISTER CONTRCT | 2015-08-08 | 2016-05-03 | 2022-01-16 | 2022-09-24
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-829 | NDF -- Storm and Sanitary Sewers in Brundwick Ave, Queens | 5 | CONSTRUCTION TO 25% | 2016-05-04 | 2017-04-28 | 2022-09-25 | 2023-09-19
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-829 | NDF -- Storm and Sanitary Sewers in Brundwick Ave, Queens | 6 | CONSTRUCTION TO 50% | 2017-04-29 | 2018-04-23 | 2023-09-20 | 2024-09-13
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-829 | NDF -- Storm and Sanitary Sewers in Brundwick Ave, Queens | 7 | CONSTRUCTION TO 75% | 2018-04-24 | 2019-04-18 | 2024-09-14 | 2025-09-08
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-829 | NDF -- Storm and Sanitary Sewers in Brundwick Ave, Queens | 8 | ORIGINAL EQUIP & FURNISHING | 2019-04-19 | 2020-01-13 | 2025-09-09 | 2026-06-05
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-829 | NDF -- Storm and Sanitary Sewers in Brundwick Ave, Queens | 9 | SUBSTANTIAL COMPLETION | 2020-01-14 | 2020-07-11 | 2026-06-06 | 2026-12-02
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-829 | NDF -- Storm and Sanitary Sewers in Brundwick Ave, Queens | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-07-12 | 2020-10-09 | 2026-12-03 | 2027-03-02
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-842A | SEQ - Storm, Sanitary Sewers & WM in 225th Street | 1 | DEVELOP SCOPE | 2018-03-01 | 2018-05-29 | 2018-03-01 | 2018-05-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-842A | SEQ - Storm, Sanitary Sewers & WM in 225th Street | 2 | PRELIMINARY DESIGN | 2018-05-30 | 2018-09-26 | 2018-05-30 | 2018-09-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-842A | SEQ - Storm, Sanitary Sewers & WM in 225th Street | 3 | FINAL DESIGN | 2018-09-27 | 2019-03-25 | 2018-09-27 | 2019-03-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-842A | SEQ - Storm, Sanitary Sewers & WM in 225th Street | 4 | BID AWARD AND REGISTER CONTRCT | 2019-03-26 | 2019-06-23 | 2019-03-26 | 2019-06-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-842A | SEQ - Storm, Sanitary Sewers & WM in 225th Street | 5 | CONSTRUCTION TO 25% | 2019-06-24 | 2019-10-21 | 2019-06-24 | 2019-10-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-842A | SEQ - Storm, Sanitary Sewers & WM in 225th Street | 6 | CONSTRUCTION TO 50% | 2019-10-22 | 2020-02-18 | 2019-10-22 | 2020-02-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-842A | SEQ - Storm, Sanitary Sewers & WM in 225th Street | 7 | CONSTRUCTION TO 75% | 2020-02-19 | 2020-06-17 | 2020-02-19 | 2020-06-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-842A | SEQ - Storm, Sanitary Sewers & WM in 225th Street | 8 | ORIGINAL EQUIP & FURNISHING | 2020-06-18 | 2020-09-15 | 2020-06-18 | 2020-09-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-842A | SEQ - Storm, Sanitary Sewers & WM in 225th Street | 9 | SUBSTANTIAL COMPLETION | 2020-09-16 | 2020-11-14 | 2020-09-16 | 2020-11-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-842A | SEQ - Storm, Sanitary Sewers & WM in 225th Street | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-11-15 | 2020-12-14 | 2020-11-15 | 2028-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-842A1 | SEQ - Storm Sewer Outlet in 224th Street | 1 | DEVELOP SCOPE | 2017-03-01 | 2017-05-29 | 2017-03-01 | 2017-05-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-842A1 | SEQ - Storm Sewer Outlet in 224th Street | 2 | PRELIMINARY DESIGN | 2017-05-30 | 2017-09-26 | 2017-05-30 | 2017-09-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-842A1 | SEQ - Storm Sewer Outlet in 224th Street | 3 | FINAL DESIGN | 2017-09-27 | 2018-03-25 | 2017-09-27 | 2018-03-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-842A1 | SEQ - Storm Sewer Outlet in 224th Street | 4 | BID AWARD AND REGISTER CONTRCT | 2018-03-26 | 2018-06-23 | 2018-03-26 | 2018-06-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-842A1 | SEQ - Storm Sewer Outlet in 224th Street | 5 | CONSTRUCTION TO 25% | 2018-06-24 | 2018-10-21 | 2018-06-24 | 2018-10-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-842A1 | SEQ - Storm Sewer Outlet in 224th Street | 6 | CONSTRUCTION TO 50% | 2018-10-22 | 2019-02-18 | 2018-10-22 | 2019-02-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-842A1 | SEQ - Storm Sewer Outlet in 224th Street | 7 | CONSTRUCTION TO 75% | 2019-02-19 | 2019-06-18 | 2019-02-19 | 2019-06-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-842A1 | SEQ - Storm Sewer Outlet in 224th Street | 8 | ORIGINAL EQUIP & FURNISHING | 2019-06-19 | 2019-09-16 | 2019-06-19 | 2019-09-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-842A1 | SEQ - Storm Sewer Outlet in 224th Street | 9 | SUBSTANTIAL COMPLETION | 2019-09-17 | 2019-11-15 | 2019-09-17 | 2019-11-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-842A1 | SEQ - Storm Sewer Outlet in 224th Street | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-11-16 | 2019-12-15 | 2019-11-16 | 2022-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-842B | SEQ - Storm & Sanitary Sewers & WM Work in 224th Street | 1 | DEVELOP SCOPE | 2020-03-01 | 2020-05-29 | 2020-03-01 | 2020-05-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-842B | SEQ - Storm & Sanitary Sewers & WM Work in 224th Street | 2 | PRELIMINARY DESIGN | 2020-05-30 | 2020-09-26 | 2020-05-30 | 2020-09-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-842B | SEQ - Storm & Sanitary Sewers & WM Work in 224th Street | 3 | FINAL DESIGN | 2020-09-27 | 2021-03-25 | 2020-09-27 | 2021-03-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-842B | SEQ - Storm & Sanitary Sewers & WM Work in 224th Street | 4 | BID AWARD AND REGISTER CONTRCT | 2021-03-26 | 2021-06-23 | 2021-03-26 | 2021-06-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-842B | SEQ - Storm & Sanitary Sewers & WM Work in 224th Street | 5 | CONSTRUCTION TO 25% | 2021-06-24 | 2021-10-21 | 2021-06-24 | 2021-10-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-842B | SEQ - Storm & Sanitary Sewers & WM Work in 224th Street | 6 | CONSTRUCTION TO 50% | 2021-10-22 | 2022-02-18 | 2021-10-22 | 2022-02-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-842B | SEQ - Storm & Sanitary Sewers & WM Work in 224th Street | 7 | CONSTRUCTION TO 75% | 2022-02-19 | 2022-06-18 | 2022-02-19 | 2022-06-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-842B | SEQ - Storm & Sanitary Sewers & WM Work in 224th Street | 8 | ORIGINAL EQUIP & FURNISHING | 2022-06-19 | 2022-09-16 | 2022-06-19 | 2022-09-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-842B | SEQ - Storm & Sanitary Sewers & WM Work in 224th Street | 9 | SUBSTANTIAL COMPLETION | 2022-09-17 | 2022-11-15 | 2022-09-17 | 2022-11-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-842B | SEQ - Storm & Sanitary Sewers & WM Work in 224th Street | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-11-16 | 2022-12-15 | 2022-11-16 | 2028-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-850 | SEQ - Storm & Sani Sewers, Force Main & WM in Liverpool St. | 1 | DEVELOP SCOPE | 2019-03-01 | 2019-05-29 | 2019-03-01 | 2019-05-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-850 | SEQ - Storm & Sani Sewers, Force Main & WM in Liverpool St. | 2 | PRELIMINARY DESIGN | 2019-05-30 | 2019-09-26 | 2019-05-30 | 2019-09-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-850 | SEQ - Storm & Sani Sewers, Force Main & WM in Liverpool St. | 3 | FINAL DESIGN | 2019-09-27 | 2020-03-24 | 2019-09-27 | 2020-03-24
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-850 | SEQ - Storm & Sani Sewers, Force Main & WM in Liverpool St. | 4 | BID AWARD AND REGISTER CONTRCT | 2020-03-25 | 2020-06-22 | 2020-03-25 | 2020-06-22
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-850 | SEQ - Storm & Sani Sewers, Force Main & WM in Liverpool St. | 5 | CONSTRUCTION TO 25% | 2020-06-23 | 2020-10-20 | 2020-06-23 | 2020-10-20
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-850 | SEQ - Storm & Sani Sewers, Force Main & WM in Liverpool St. | 6 | CONSTRUCTION TO 50% | 2020-10-21 | 2021-02-17 | 2020-10-21 | 2021-02-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-850 | SEQ - Storm & Sani Sewers, Force Main & WM in Liverpool St. | 7 | CONSTRUCTION TO 75% | 2021-02-18 | 2021-06-17 | 2021-02-18 | 2021-06-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-850 | SEQ - Storm & Sani Sewers, Force Main & WM in Liverpool St. | 8 | ORIGINAL EQUIP & FURNISHING | 2021-06-18 | 2021-09-15 | 2021-06-18 | 2021-09-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-850 | SEQ - Storm & Sani Sewers, Force Main & WM in Liverpool St. | 9 | SUBSTANTIAL COMPLETION | 2021-09-16 | 2021-11-14 | 2021-09-16 | 2021-11-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-850 | SEQ - Storm & Sani Sewers, Force Main & WM in Liverpool St. | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-11-15 | 2021-12-14 | 2021-11-15 | 2026-08-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-859 | Combined Sewer Replmnt & WM work 70 st & calamus ave, Qns | 1 | DEVELOP SCOPE | 2018-06-30 | 2019-03-26 | 2018-06-30 | 2019-03-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-859 | Combined Sewer Replmnt & WM work 70 st & calamus ave, Qns | 2 | PRELIMINARY DESIGN | 2019-03-27 | 2020-03-20 | 2019-03-27 | 2020-03-20
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-859 | Combined Sewer Replmnt & WM work 70 st & calamus ave, Qns | 3 | FINAL DESIGN | 2020-03-21 | 2021-09-11 | 2020-03-21 | 2021-09-11
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-859 | Combined Sewer Replmnt & WM work 70 st & calamus ave, Qns | 4 | BID AWARD AND REGISTER CONTRCT | 2021-09-12 | 2022-06-08 | 2021-09-12 | 2022-06-08
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-859 | Combined Sewer Replmnt & WM work 70 st & calamus ave, Qns | 5 | CONSTRUCTION TO 25% | 2022-06-09 | 2023-06-03 | 2022-06-09 | 2023-06-03
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-859 | Combined Sewer Replmnt & WM work 70 st & calamus ave, Qns | 6 | CONSTRUCTION TO 50% | 2023-06-04 | 2024-05-28 | 2023-06-04 | 2024-05-28
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-859 | Combined Sewer Replmnt & WM work 70 st & calamus ave, Qns | 7 | CONSTRUCTION TO 75% | 2024-05-29 | 2025-05-23 | 2024-05-29 | 2025-05-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-859 | Combined Sewer Replmnt & WM work 70 st & calamus ave, Qns | 8 | ORIGINAL EQUIP & FURNISHING | 2025-05-24 | 2026-02-17 | 2025-05-24 | 2026-02-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-859 | Combined Sewer Replmnt & WM work 70 st & calamus ave, Qns | 9 | SUBSTANTIAL COMPLETION | 2026-02-18 | 2026-08-16 | 2026-02-18 | 2026-08-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-859 | Combined Sewer Replmnt & WM work 70 st & calamus ave, Qns | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2026-08-17 | 2026-11-14 | 2026-08-17 | 2026-11-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-860 | Combined Swr Replac & WM work 71st, QNS | 1 | DEVELOP SCOPE | 2019-03-01 | 2019-05-29 | 2019-03-01 | 2019-05-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-860 | Combined Swr Replac & WM work 71st, QNS | 2 | PRELIMINARY DESIGN | 2019-05-30 | 2019-09-26 | 2019-05-30 | 2019-09-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-860 | Combined Swr Replac & WM work 71st, QNS | 3 | FINAL DESIGN | 2019-09-27 | 2020-03-24 | 2019-09-27 | 2020-03-24
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-860 | Combined Swr Replac & WM work 71st, QNS | 4 | BID AWARD AND REGISTER CONTRCT | 2020-03-25 | 2020-06-22 | 2020-03-25 | 2020-06-22
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-860 | Combined Swr Replac & WM work 71st, QNS | 5 | CONSTRUCTION TO 25% | 2020-06-23 | 2020-10-20 | 2020-06-23 | 2020-10-20
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-860 | Combined Swr Replac & WM work 71st, QNS | 6 | CONSTRUCTION TO 50% | 2020-10-21 | 2021-02-17 | 2020-10-21 | 2021-02-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-860 | Combined Swr Replac & WM work 71st, QNS | 7 | CONSTRUCTION TO 75% | 2021-02-18 | 2021-06-17 | 2021-02-18 | 2021-06-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-860 | Combined Swr Replac & WM work 71st, QNS | 8 | ORIGINAL EQUIP & FURNISHING | 2021-06-18 | 2021-09-15 | 2021-06-18 | 2021-09-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-860 | Combined Swr Replac & WM work 71st, QNS | 9 | SUBSTANTIAL COMPLETION | 2021-09-16 | 2021-11-14 | 2021-09-16 | 2021-11-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-860 | Combined Swr Replac & WM work 71st, QNS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-11-15 | 2021-12-14 | 2021-11-15 | 2021-12-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-862 | SEQ - Storm & Sanitary Sewer Replcmnt/Ext. 146 Ave (HWQ662G) | 1 | DEVELOP SCOPE | 2018-03-01 | 2018-05-29 | 2018-03-01 | 2018-05-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-862 | SEQ - Storm & Sanitary Sewer Replcmnt/Ext. 146 Ave (HWQ662G) | 2 | PRELIMINARY DESIGN | 2018-05-30 | 2018-09-26 | 2018-05-30 | 2018-09-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-862 | SEQ - Storm & Sanitary Sewer Replcmnt/Ext. 146 Ave (HWQ662G) | 3 | FINAL DESIGN | 2018-09-27 | 2019-03-25 | 2018-09-27 | 2019-03-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-862 | SEQ - Storm & Sanitary Sewer Replcmnt/Ext. 146 Ave (HWQ662G) | 4 | BID AWARD AND REGISTER CONTRCT | 2019-03-26 | 2019-06-23 | 2019-03-26 | 2019-06-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-862 | SEQ - Storm & Sanitary Sewer Replcmnt/Ext. 146 Ave (HWQ662G) | 5 | CONSTRUCTION TO 25% | 2019-06-24 | 2019-10-21 | 2019-06-24 | 2019-10-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-862 | SEQ - Storm & Sanitary Sewer Replcmnt/Ext. 146 Ave (HWQ662G) | 6 | CONSTRUCTION TO 50% | 2019-10-22 | 2020-02-18 | 2019-10-22 | 2020-02-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-862 | SEQ - Storm & Sanitary Sewer Replcmnt/Ext. 146 Ave (HWQ662G) | 7 | CONSTRUCTION TO 75% | 2020-02-19 | 2020-06-17 | 2020-02-19 | 2020-06-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-862 | SEQ - Storm & Sanitary Sewer Replcmnt/Ext. 146 Ave (HWQ662G) | 8 | ORIGINAL EQUIP & FURNISHING | 2020-06-18 | 2020-09-15 | 2020-06-18 | 2020-09-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-862 | SEQ - Storm & Sanitary Sewer Replcmnt/Ext. 146 Ave (HWQ662G) | 9 | SUBSTANTIAL COMPLETION | 2020-09-16 | 2020-11-14 | 2020-09-16 | 2020-11-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-862 | SEQ - Storm & Sanitary Sewer Replcmnt/Ext. 146 Ave (HWQ662G) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-11-15 | 2020-12-14 | 2020-11-15 | 2026-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-885 | SEQ - 150th St Spine: Phase I, Outlet at Bergen Basin | 1 | DEVELOP SCOPE | 2019-03-01 | 2019-05-29 | 2019-03-01 | 2019-05-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-885 | SEQ - 150th St Spine: Phase I, Outlet at Bergen Basin | 2 | PRELIMINARY DESIGN | 2019-05-30 | 2019-09-26 | 2019-05-30 | 2019-09-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-885 | SEQ - 150th St Spine: Phase I, Outlet at Bergen Basin | 3 | FINAL DESIGN | 2019-09-27 | 2020-03-24 | 2019-09-27 | 2020-03-24
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-885 | SEQ - 150th St Spine: Phase I, Outlet at Bergen Basin | 4 | BID AWARD AND REGISTER CONTRCT | 2020-03-25 | 2020-06-22 | 2020-03-25 | 2020-06-22
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-885 | SEQ - 150th St Spine: Phase I, Outlet at Bergen Basin | 5 | CONSTRUCTION TO 25% | 2020-06-23 | 2020-10-20 | 2020-06-23 | 2020-10-20
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-885 | SEQ - 150th St Spine: Phase I, Outlet at Bergen Basin | 6 | CONSTRUCTION TO 50% | 2020-10-21 | 2021-02-17 | 2020-10-21 | 2021-02-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-885 | SEQ - 150th St Spine: Phase I, Outlet at Bergen Basin | 7 | CONSTRUCTION TO 75% | 2021-02-18 | 2021-06-17 | 2021-02-18 | 2021-06-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-885 | SEQ - 150th St Spine: Phase I, Outlet at Bergen Basin | 8 | ORIGINAL EQUIP & FURNISHING | 2021-06-18 | 2021-09-15 | 2021-06-18 | 2021-09-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-885 | SEQ - 150th St Spine: Phase I, Outlet at Bergen Basin | 9 | SUBSTANTIAL COMPLETION | 2021-09-16 | 2021-11-14 | 2021-09-16 | 2021-11-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-885 | SEQ - 150th St Spine: Phase I, Outlet at Bergen Basin | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-11-15 | 2021-12-14 | 2021-11-15 | 2024-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-885A | SEQ - 150th St Spine: Phase II, Trunk Storm Sewer in JFK | 1 | DEVELOP SCOPE | 2020-08-30 | 2020-11-27 | 2020-08-30 | 2020-11-27
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-885A | SEQ - 150th St Spine: Phase II, Trunk Storm Sewer in JFK | 2 | PRELIMINARY DESIGN | 2020-11-28 | 2021-03-27 | 2020-11-28 | 2021-03-27
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-885A | SEQ - 150th St Spine: Phase II, Trunk Storm Sewer in JFK | 3 | FINAL DESIGN | 2021-03-28 | 2021-09-23 | 2021-03-28 | 2021-09-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-885A | SEQ - 150th St Spine: Phase II, Trunk Storm Sewer in JFK | 4 | BID AWARD AND REGISTER CONTRCT | 2021-09-24 | 2021-12-22 | 2021-09-24 | 2021-12-22
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-885A | SEQ - 150th St Spine: Phase II, Trunk Storm Sewer in JFK | 5 | CONSTRUCTION TO 25% | 2021-12-23 | 2022-04-21 | 2021-12-23 | 2022-04-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-885A | SEQ - 150th St Spine: Phase II, Trunk Storm Sewer in JFK | 6 | CONSTRUCTION TO 50% | 2022-04-22 | 2022-08-19 | 2022-04-22 | 2022-08-19
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-885A | SEQ - 150th St Spine: Phase II, Trunk Storm Sewer in JFK | 7 | CONSTRUCTION TO 75% | 2022-08-20 | 2022-12-17 | 2022-08-20 | 2022-12-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-885A | SEQ - 150th St Spine: Phase II, Trunk Storm Sewer in JFK | 8 | ORIGINAL EQUIP & FURNISHING | 2022-12-18 | 2023-03-17 | 2022-12-18 | 2023-03-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-885A | SEQ - 150th St Spine: Phase II, Trunk Storm Sewer in JFK | 9 | SUBSTANTIAL COMPLETION | 2023-03-18 | 2023-05-16 | 2023-03-18 | 2023-05-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-885A | SEQ - 150th St Spine: Phase II, Trunk Storm Sewer in JFK | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-05-17 | 2023-06-15 | 2023-05-17 | 2028-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-886 | NDF -- Storm & Sanitary Sewers in Beach Channel Drive, Qns | 1 | DEVELOP SCOPE | 2019-03-01 | 2019-05-29 | 2019-03-01 | 2019-05-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-886 | NDF -- Storm & Sanitary Sewers in Beach Channel Drive, Qns | 2 | PRELIMINARY DESIGN | 2019-05-30 | 2019-09-26 | 2019-05-30 | 2019-09-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-886 | NDF -- Storm & Sanitary Sewers in Beach Channel Drive, Qns | 3 | FINAL DESIGN | 2019-09-27 | 2020-03-24 | 2019-09-27 | 2020-03-24
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-886 | NDF -- Storm & Sanitary Sewers in Beach Channel Drive, Qns | 4 | BID AWARD AND REGISTER CONTRCT | 2020-03-25 | 2020-06-22 | 2020-03-25 | 2020-06-22
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-886 | NDF -- Storm & Sanitary Sewers in Beach Channel Drive, Qns | 5 | CONSTRUCTION TO 25% | 2020-06-23 | 2020-10-20 | 2020-06-23 | 2020-10-20
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-886 | NDF -- Storm & Sanitary Sewers in Beach Channel Drive, Qns | 6 | CONSTRUCTION TO 50% | 2020-10-21 | 2021-02-17 | 2020-10-21 | 2021-02-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-886 | NDF -- Storm & Sanitary Sewers in Beach Channel Drive, Qns | 7 | CONSTRUCTION TO 75% | 2021-02-18 | 2021-06-17 | 2021-02-18 | 2021-06-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-886 | NDF -- Storm & Sanitary Sewers in Beach Channel Drive, Qns | 8 | ORIGINAL EQUIP & FURNISHING | 2021-06-18 | 2021-09-15 | 2021-06-18 | 2021-09-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-886 | NDF -- Storm & Sanitary Sewers in Beach Channel Drive, Qns | 9 | SUBSTANTIAL COMPLETION | 2021-09-16 | 2021-11-14 | 2021-09-16 | 2021-11-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-886 | NDF -- Storm & Sanitary Sewers in Beach Channel Drive, Qns | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-11-15 | 2021-12-14 | 2021-11-15 | 2024-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-887 | NDF -- Storm & Sanitary Sewers, WM work in Cornaga Ave, Qns | 1 | DEVELOP SCOPE | 2019-03-01 | 2019-05-29 | 2019-03-01 | 2019-05-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-887 | NDF -- Storm & Sanitary Sewers, WM work in Cornaga Ave, Qns | 2 | PRELIMINARY DESIGN | 2019-05-30 | 2019-09-26 | 2019-05-30 | 2019-09-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-887 | NDF -- Storm & Sanitary Sewers, WM work in Cornaga Ave, Qns | 3 | FINAL DESIGN | 2019-09-27 | 2020-03-24 | 2019-09-27 | 2020-03-24
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-887 | NDF -- Storm & Sanitary Sewers, WM work in Cornaga Ave, Qns | 4 | BID AWARD AND REGISTER CONTRCT | 2020-03-25 | 2020-06-22 | 2020-03-25 | 2020-06-22
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-887 | NDF -- Storm & Sanitary Sewers, WM work in Cornaga Ave, Qns | 5 | CONSTRUCTION TO 25% | 2020-06-23 | 2020-10-20 | 2020-06-23 | 2020-10-20
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-887 | NDF -- Storm & Sanitary Sewers, WM work in Cornaga Ave, Qns | 6 | CONSTRUCTION TO 50% | 2020-10-21 | 2021-02-17 | 2020-10-21 | 2021-02-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-887 | NDF -- Storm & Sanitary Sewers, WM work in Cornaga Ave, Qns | 7 | CONSTRUCTION TO 75% | 2021-02-18 | 2021-06-17 | 2021-02-18 | 2021-06-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-887 | NDF -- Storm & Sanitary Sewers, WM work in Cornaga Ave, Qns | 8 | ORIGINAL EQUIP & FURNISHING | 2021-06-18 | 2021-09-15 | 2021-06-18 | 2021-09-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-887 | NDF -- Storm & Sanitary Sewers, WM work in Cornaga Ave, Qns | 9 | SUBSTANTIAL COMPLETION | 2021-09-16 | 2021-11-14 | 2021-09-16 | 2021-11-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-887 | NDF -- Storm & Sanitary Sewers, WM work in Cornaga Ave, Qns | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-11-15 | 2021-12-14 | 2021-11-15 | 2027-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-889 | SEQ - New Storm Sewer N. Conduit Ave | 1 | DEVELOP SCOPE | 2017-03-01 | 2017-05-29 | 2017-03-01 | 2017-05-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-889 | SEQ - New Storm Sewer N. Conduit Ave | 2 | PRELIMINARY DESIGN | 2017-05-30 | 2017-09-26 | 2017-05-30 | 2017-09-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-889 | SEQ - New Storm Sewer N. Conduit Ave | 3 | FINAL DESIGN | 2017-09-27 | 2018-03-25 | 2017-09-27 | 2018-03-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-889 | SEQ - New Storm Sewer N. Conduit Ave | 4 | BID AWARD AND REGISTER CONTRCT | 2018-03-26 | 2018-06-23 | 2018-03-26 | 2018-06-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-889 | SEQ - New Storm Sewer N. Conduit Ave | 5 | CONSTRUCTION TO 25% | 2018-06-24 | 2018-10-21 | 2018-06-24 | 2018-10-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-889 | SEQ - New Storm Sewer N. Conduit Ave | 6 | CONSTRUCTION TO 50% | 2018-10-22 | 2019-02-18 | 2018-10-22 | 2019-02-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-889 | SEQ - New Storm Sewer N. Conduit Ave | 7 | CONSTRUCTION TO 75% | 2019-02-19 | 2019-06-18 | 2019-02-19 | 2019-06-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-889 | SEQ - New Storm Sewer N. Conduit Ave | 8 | ORIGINAL EQUIP & FURNISHING | 2019-06-19 | 2019-09-16 | 2019-06-19 | 2019-09-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-889 | SEQ - New Storm Sewer N. Conduit Ave | 9 | SUBSTANTIAL COMPLETION | 2019-09-17 | 2019-11-15 | 2019-09-17 | 2019-11-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-889 | SEQ - New Storm Sewer N. Conduit Ave | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-11-16 | 2019-12-15 | 2019-11-16 | 2024-09-13
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002539 | SEQ - Storm & Sanitary Sewers in 111th Ave (HWQ002539) | 1 | DEVELOP SCOPE | 2017-03-01 | 2017-05-29 | 2016-03-01 | 2016-05-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002539 | SEQ - Storm & Sanitary Sewers in 111th Ave (HWQ002539) | 2 | PRELIMINARY DESIGN | 2017-05-30 | 2017-09-26 | 2016-05-30 | 2016-09-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002539 | SEQ - Storm & Sanitary Sewers in 111th Ave (HWQ002539) | 3 | FINAL DESIGN | 2017-09-27 | 2018-03-25 | 2016-09-27 | 2017-11-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002539 | SEQ - Storm & Sanitary Sewers in 111th Ave (HWQ002539) | 4 | BID AWARD AND REGISTER CONTRCT | 2018-03-26 | 2018-06-23 | 2017-11-22 | 2018-09-24
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002539 | SEQ - Storm & Sanitary Sewers in 111th Ave (HWQ002539) | 5 | CONSTRUCTION TO 25% | 2018-06-24 | 2018-10-21 | 2018-09-25 | 2019-01-22
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002539 | SEQ - Storm & Sanitary Sewers in 111th Ave (HWQ002539) | 6 | CONSTRUCTION TO 50% | 2018-10-22 | 2019-02-18 | 2019-01-23 | 2019-05-22
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002539 | SEQ - Storm & Sanitary Sewers in 111th Ave (HWQ002539) | 7 | CONSTRUCTION TO 75% | 2019-02-19 | 2019-06-18 | 2019-05-23 | 2019-09-19
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002539 | SEQ - Storm & Sanitary Sewers in 111th Ave (HWQ002539) | 8 | ORIGINAL EQUIP & FURNISHING | 2019-06-19 | 2019-09-16 | 2019-09-20 | 2019-12-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002539 | SEQ - Storm & Sanitary Sewers in 111th Ave (HWQ002539) | 9 | SUBSTANTIAL COMPLETION | 2019-09-17 | 2019-11-15 | 2019-12-19 | 2020-02-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002539 | SEQ - Storm & Sanitary Sewers in 111th Ave (HWQ002539) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-11-16 | 2019-12-15 | 2020-02-17 | 2022-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002583 | SANITARY SEWERS IN B 54 ST - ALMEDA AV & B CHANNEL DR | 1 | DEVELOP SCOPE | 2009-03-01 | 2009-05-29 | 2009-03-01 | 2009-05-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002583 | SANITARY SEWERS IN B 54 ST - ALMEDA AV & B CHANNEL DR | 2 | PRELIMINARY DESIGN | 2009-05-30 | 2009-09-26 | 2009-05-30 | 2009-09-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002583 | SANITARY SEWERS IN B 54 ST - ALMEDA AV & B CHANNEL DR | 3 | FINAL DESIGN | 2009-09-27 | 2010-03-25 | 2009-09-27 | 2010-03-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002583 | SANITARY SEWERS IN B 54 ST - ALMEDA AV & B CHANNEL DR | 4 | BID AWARD AND REGISTER CONTRCT | 2010-03-26 | 2010-06-23 | 2022-03-28 | 2022-06-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002583 | SANITARY SEWERS IN B 54 ST - ALMEDA AV & B CHANNEL DR | 5 | CONSTRUCTION TO 25% | 2010-06-24 | 2010-10-21 | 2022-06-26 | 2022-06-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002583 | SANITARY SEWERS IN B 54 ST - ALMEDA AV & B CHANNEL DR | 6 | CONSTRUCTION TO 50% | 2010-10-22 | 2011-02-18 | 2022-06-26 | 2022-06-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002583 | SANITARY SEWERS IN B 54 ST - ALMEDA AV & B CHANNEL DR | 7 | CONSTRUCTION TO 75% | 2011-02-19 | 2011-06-18 | 2022-06-26 | 2022-06-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002583 | SANITARY SEWERS IN B 54 ST - ALMEDA AV & B CHANNEL DR | 8 | ORIGINAL EQUIP & FURNISHING | 2011-06-19 | 2011-09-16 | 2022-06-26 | 2022-06-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002583 | SANITARY SEWERS IN B 54 ST - ALMEDA AV & B CHANNEL DR | 9 | SUBSTANTIAL COMPLETION | 2011-09-17 | 2011-11-15 | 2022-06-26 | 2022-06-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002583 | SANITARY SEWERS IN B 54 ST - ALMEDA AV & B CHANNEL DR | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2011-11-16 | 2011-12-15 | 2023-03-16 | 2026-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002649 | COMBINED SEWERS IN 110 STREET BTWN. NORTHERN & ASTORIA BLVD. | 2 | PRELIMINARY DESIGN | 2008-05-25 | 2008-09-21 | 2008-09-29 | 2009-01-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002649 | COMBINED SEWERS IN 110 STREET BTWN. NORTHERN & ASTORIA BLVD. | 3 | FINAL DESIGN | 2008-09-22 | 2009-03-20 | 2009-01-27 | 2009-07-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002649 | COMBINED SEWERS IN 110 STREET BTWN. NORTHERN & ASTORIA BLVD. | 4 | BID AWARD AND REGISTER CONTRCT | 2009-03-21 | 2009-06-18 | 2009-07-26 | 2009-10-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002649 | COMBINED SEWERS IN 110 STREET BTWN. NORTHERN & ASTORIA BLVD. | 5 | CONSTRUCTION TO 25% | 2009-06-19 | 2009-10-16 | 2009-10-24 | 2010-02-20
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002649 | COMBINED SEWERS IN 110 STREET BTWN. NORTHERN & ASTORIA BLVD. | 6 | CONSTRUCTION TO 50% | 2009-10-17 | 2010-02-13 | 2010-02-21 | 2010-06-20
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002649 | COMBINED SEWERS IN 110 STREET BTWN. NORTHERN & ASTORIA BLVD. | 7 | CONSTRUCTION TO 75% | 2010-02-14 | 2010-06-13 | 2010-06-21 | 2011-06-20
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002649 | COMBINED SEWERS IN 110 STREET BTWN. NORTHERN & ASTORIA BLVD. | 8 | ORIGINAL EQUIP & FURNISHING | 2010-06-14 | 2010-09-11 | 2011-06-21 | 2011-09-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002649 | COMBINED SEWERS IN 110 STREET BTWN. NORTHERN & ASTORIA BLVD. | 9 | SUBSTANTIAL COMPLETION | 2010-09-12 | 2010-11-10 | 2011-09-19 | 2011-11-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002649 | COMBINED SEWERS IN 110 STREET BTWN. NORTHERN & ASTORIA BLVD. | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2010-11-11 | 2010-12-10 | 2011-11-18 | 2019-12-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002693 | Combined Sewer and Water Main Replacements at Penelope Ave. | 1 | DEVELOP SCOPE | 2014-02-27 | 2014-05-27 | 2009-10-23 | 2012-11-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002693 | Combined Sewer and Water Main Replacements at Penelope Ave. | 2 | PRELIMINARY DESIGN | 2014-05-28 | 2014-09-24 | 2012-11-26 | 2013-03-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002693 | Combined Sewer and Water Main Replacements at Penelope Ave. | 3 | FINAL DESIGN | 2014-09-25 | 2015-03-23 | 2013-03-26 | 2013-09-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002693 | Combined Sewer and Water Main Replacements at Penelope Ave. | 4 | BID AWARD AND REGISTER CONTRCT | 2015-03-24 | 2015-06-21 | 2013-09-22 | 2013-12-20
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002693 | Combined Sewer and Water Main Replacements at Penelope Ave. | 5 | CONSTRUCTION TO 25% | 2015-06-22 | 2015-10-19 | 2013-12-21 | 2014-04-19
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002693 | Combined Sewer and Water Main Replacements at Penelope Ave. | 6 | CONSTRUCTION TO 50% | 2015-10-20 | 2016-02-16 | 2014-04-20 | 2014-08-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002693 | Combined Sewer and Water Main Replacements at Penelope Ave. | 7 | CONSTRUCTION TO 75% | 2016-02-17 | 2016-06-15 | 2014-08-18 | 2014-12-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002693 | Combined Sewer and Water Main Replacements at Penelope Ave. | 8 | ORIGINAL EQUIP & FURNISHING | 2016-06-16 | 2016-09-13 | 2014-12-16 | 2015-03-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002693 | Combined Sewer and Water Main Replacements at Penelope Ave. | 9 | SUBSTANTIAL COMPLETION | 2016-09-14 | 2016-11-12 | 2015-03-16 | 2015-05-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002693 | Combined Sewer and Water Main Replacements at Penelope Ave. | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-11-13 | 2016-12-12 | 2015-05-15 | 2022-05-20
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002700 | REHABILITATION OF COMBINED SEWER AND WATER MAIN | 1 | DEVELOP SCOPE | 2011-01-01 | 2011-03-31 | 2013-08-18 | 2013-11-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002700 | REHABILITATION OF COMBINED SEWER AND WATER MAIN | 2 | PRELIMINARY DESIGN | 2011-04-01 | 2011-07-29 | 2013-11-16 | 2014-05-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002700 | REHABILITATION OF COMBINED SEWER AND WATER MAIN | 3 | FINAL DESIGN | 2011-07-30 | 2012-01-25 | 2014-05-15 | 2015-03-08
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002700 | REHABILITATION OF COMBINED SEWER AND WATER MAIN | 4 | BID AWARD AND REGISTER CONTRCT | 2012-01-26 | 2012-04-24 | 2015-03-09 | 2015-06-06
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002700 | REHABILITATION OF COMBINED SEWER AND WATER MAIN | 5 | CONSTRUCTION TO 25% | 2012-04-25 | 2012-08-22 | 2015-06-07 | 2018-06-05
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002700 | REHABILITATION OF COMBINED SEWER AND WATER MAIN | 6 | CONSTRUCTION TO 50% | 2012-08-23 | 2012-12-20 | 2018-06-06 | 2021-06-04
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002700 | REHABILITATION OF COMBINED SEWER AND WATER MAIN | 7 | CONSTRUCTION TO 75% | 2012-12-21 | 2013-04-19 | 2021-06-05 | 2022-07-04
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002700 | REHABILITATION OF COMBINED SEWER AND WATER MAIN | 8 | ORIGINAL EQUIP & FURNISHING | 2013-04-20 | 2013-07-18 | 2022-07-05 | 2022-10-02
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002700 | REHABILITATION OF COMBINED SEWER AND WATER MAIN | 9 | SUBSTANTIAL COMPLETION | 2013-07-19 | 2013-09-16 | 2022-10-03 | 2022-12-01
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002700 | REHABILITATION OF COMBINED SEWER AND WATER MAIN | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-09-17 | 2013-10-16 | 2022-12-02 | 2030-08-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002709 | Combined Sewer Installation in 45th Avenue | 1 | DEVELOP SCOPE | 2017-05-01 | 2018-01-25 | 2017-05-01 | 2018-01-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002709 | Combined Sewer Installation in 45th Avenue | 2 | PRELIMINARY DESIGN | 2018-01-26 | 2019-01-20 | 2018-01-26 | 2019-01-20
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002709 | Combined Sewer Installation in 45th Avenue | 3 | FINAL DESIGN | 2019-01-21 | 2020-07-13 | 2019-01-21 | 2020-07-13
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002709 | Combined Sewer Installation in 45th Avenue | 4 | BID AWARD AND REGISTER CONTRCT | 2020-07-14 | 2021-04-09 | 2020-07-14 | 2021-04-09
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002709 | Combined Sewer Installation in 45th Avenue | 5 | CONSTRUCTION TO 25% | 2021-04-10 | 2022-04-04 | 2021-04-10 | 2022-04-04
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002709 | Combined Sewer Installation in 45th Avenue | 6 | CONSTRUCTION TO 50% | 2022-04-05 | 2023-03-30 | 2022-04-05 | 2023-03-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002709 | Combined Sewer Installation in 45th Avenue | 7 | CONSTRUCTION TO 75% | 2023-03-31 | 2024-03-24 | 2023-03-31 | 2024-03-24
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002709 | Combined Sewer Installation in 45th Avenue | 8 | ORIGINAL EQUIP & FURNISHING | 2024-03-25 | 2024-12-19 | 2024-03-25 | 2024-12-19
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002709 | Combined Sewer Installation in 45th Avenue | 9 | SUBSTANTIAL COMPLETION | 2024-12-20 | 2025-06-17 | 2024-12-20 | 2025-06-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002709 | Combined Sewer Installation in 45th Avenue | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-06-18 | 2025-09-15 | 2025-06-18 | 2025-09-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002710 | Combined sewer replcmnt & water main work in Selfridge St. | 1 | DEVELOP SCOPE | 2017-03-01 | 2017-05-29 | 2017-03-01 | 2017-05-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002710 | Combined sewer replcmnt & water main work in Selfridge St. | 2 | PRELIMINARY DESIGN | 2017-05-30 | 2017-09-26 | 2017-05-30 | 2017-09-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002710 | Combined sewer replcmnt & water main work in Selfridge St. | 3 | FINAL DESIGN | 2017-09-27 | 2018-03-25 | 2017-09-27 | 2018-03-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002710 | Combined sewer replcmnt & water main work in Selfridge St. | 4 | BID AWARD AND REGISTER CONTRCT | 2018-03-26 | 2018-06-23 | 2018-03-26 | 2018-06-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002710 | Combined sewer replcmnt & water main work in Selfridge St. | 5 | CONSTRUCTION TO 25% | 2018-06-24 | 2018-10-21 | 2018-06-24 | 2018-10-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002710 | Combined sewer replcmnt & water main work in Selfridge St. | 6 | CONSTRUCTION TO 50% | 2018-10-22 | 2019-02-18 | 2018-10-22 | 2019-02-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002710 | Combined sewer replcmnt & water main work in Selfridge St. | 7 | CONSTRUCTION TO 75% | 2019-02-19 | 2019-06-18 | 2019-02-19 | 2019-06-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002710 | Combined sewer replcmnt & water main work in Selfridge St. | 8 | ORIGINAL EQUIP & FURNISHING | 2019-06-19 | 2019-09-16 | 2019-06-19 | 2019-09-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002710 | Combined sewer replcmnt & water main work in Selfridge St. | 9 | SUBSTANTIAL COMPLETION | 2019-09-17 | 2019-11-15 | 2019-09-17 | 2019-11-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002710 | Combined sewer replcmnt & water main work in Selfridge St. | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-11-16 | 2019-12-15 | 2019-11-16 | 2022-12-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002711 | Combilned Sewer in Main Street betwwen 40th Road and 41 St. | 1 | DEVELOP SCOPE | 2013-06-30 | 2014-03-26 | 2013-06-30 | 2014-03-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002711 | Combilned Sewer in Main Street betwwen 40th Road and 41 St. | 2 | PRELIMINARY DESIGN | 2014-03-27 | 2015-03-21 | 2014-03-27 | 2015-03-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002711 | Combilned Sewer in Main Street betwwen 40th Road and 41 St. | 3 | FINAL DESIGN | 2015-03-22 | 2016-09-11 | 2015-03-22 | 2016-09-11
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002711 | Combilned Sewer in Main Street betwwen 40th Road and 41 St. | 4 | BID AWARD AND REGISTER CONTRCT | 2016-09-12 | 2017-06-08 | 2016-09-12 | 2017-06-08
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002711 | Combilned Sewer in Main Street betwwen 40th Road and 41 St. | 5 | CONSTRUCTION TO 25% | 2017-06-09 | 2018-06-03 | 2017-06-09 | 2018-06-03
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002711 | Combilned Sewer in Main Street betwwen 40th Road and 41 St. | 6 | CONSTRUCTION TO 50% | 2018-06-04 | 2019-05-29 | 2018-06-04 | 2019-05-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002711 | Combilned Sewer in Main Street betwwen 40th Road and 41 St. | 7 | CONSTRUCTION TO 75% | 2019-05-30 | 2020-05-23 | 2019-05-30 | 2020-05-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002711 | Combilned Sewer in Main Street betwwen 40th Road and 41 St. | 8 | ORIGINAL EQUIP & FURNISHING | 2020-05-24 | 2021-02-17 | 2020-05-24 | 2021-02-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002711 | Combilned Sewer in Main Street betwwen 40th Road and 41 St. | 9 | SUBSTANTIAL COMPLETION | 2021-02-18 | 2021-08-16 | 2021-02-18 | 2021-08-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002711 | Combilned Sewer in Main Street betwwen 40th Road and 41 St. | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-08-17 | 2021-11-14 | 2021-08-17 | 2021-11-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200328 | STM SEWERS IN 110 AV, QNS | 3 | FINAL DESIGN | 2003-12-28 | 2004-06-24 | 2002-09-12 | 2003-03-10
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200328 | STM SEWERS IN 110 AV, QNS | 4 | BID AWARD AND REGISTER CONTRCT | 2007-03-01 | 2007-06-01 | 2008-08-26 | 2008-11-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200328 | STM SEWERS IN 110 AV, QNS | 5 | CONSTRUCTION TO 25% | 2007-06-02 | 2007-06-01 | 2008-11-27 | 2009-11-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200328 | STM SEWERS IN 110 AV, QNS | 6 | CONSTRUCTION TO 50% | 2007-06-02 | 2007-06-01 | 2009-11-27 | 2011-11-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200328 | STM SEWERS IN 110 AV, QNS | 7 | CONSTRUCTION TO 75% | 2007-06-02 | 2007-06-01 | 2011-11-27 | 2012-11-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200328 | STM SEWERS IN 110 AV, QNS | 8 | ORIGINAL EQUIP & FURNISHING | 2007-06-02 | 2007-06-01 | 2012-11-26 | 2013-02-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200328 | STM SEWERS IN 110 AV, QNS | 9 | SUBSTANTIAL COMPLETION | 2007-06-02 | 2007-06-01 | 2013-02-24 | 2014-02-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200328 | STM SEWERS IN 110 AV, QNS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2007-06-02 | 2007-07-01 | 2014-02-24 | 2019-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200426 | STORM SEWERS IN B 54 ST - ALMEDA AV & B CHANNEL DR | 1 | DEVELOP SCOPE | 2009-02-14 | 2009-05-14 | 2009-02-14 | 2009-05-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200426 | STORM SEWERS IN B 54 ST - ALMEDA AV & B CHANNEL DR | 2 | PRELIMINARY DESIGN | 2009-05-15 | 2009-09-11 | 2009-05-15 | 2009-09-11
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200426 | STORM SEWERS IN B 54 ST - ALMEDA AV & B CHANNEL DR | 3 | FINAL DESIGN | 2009-09-12 | 2010-03-10 | 2009-09-12 | 2010-03-10
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200426 | STORM SEWERS IN B 54 ST - ALMEDA AV & B CHANNEL DR | 4 | BID AWARD AND REGISTER CONTRCT | 2010-03-11 | 2010-06-08 | 2022-03-28 | 2022-06-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200426 | STORM SEWERS IN B 54 ST - ALMEDA AV & B CHANNEL DR | 5 | CONSTRUCTION TO 25% | 2010-06-09 | 2010-10-06 | 2022-06-26 | 2022-06-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200426 | STORM SEWERS IN B 54 ST - ALMEDA AV & B CHANNEL DR | 6 | CONSTRUCTION TO 50% | 2010-10-07 | 2011-02-03 | 2022-06-26 | 2022-06-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200426 | STORM SEWERS IN B 54 ST - ALMEDA AV & B CHANNEL DR | 7 | CONSTRUCTION TO 75% | 2011-02-04 | 2011-06-03 | 2022-06-26 | 2022-06-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200426 | STORM SEWERS IN B 54 ST - ALMEDA AV & B CHANNEL DR | 8 | ORIGINAL EQUIP & FURNISHING | 2011-06-04 | 2011-09-01 | 2022-06-26 | 2022-06-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200426 | STORM SEWERS IN B 54 ST - ALMEDA AV & B CHANNEL DR | 9 | SUBSTANTIAL COMPLETION | 2011-09-02 | 2011-10-31 | 2022-06-26 | 2022-06-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200426 | STORM SEWERS IN B 54 ST - ALMEDA AV & B CHANNEL DR | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2011-11-01 | 2011-11-30 | 2022-06-26 | 2023-12-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200463 | Storm & San Sewers in College point b/t 9 av & US Bulkhead | 1 | DEVELOP SCOPE | 2005-08-16 | 2006-05-12 | 2014-03-05 | 2014-06-02
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200463 | Storm & San Sewers in College point b/t 9 av & US Bulkhead | 2 | PRELIMINARY DESIGN | 2006-05-13 | 2007-05-07 | 2014-06-03 | 2014-09-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200463 | Storm & San Sewers in College point b/t 9 av & US Bulkhead | 3 | FINAL DESIGN | 2007-05-08 | 2008-10-28 | 2014-10-01 | 2015-03-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200463 | Storm & San Sewers in College point b/t 9 av & US Bulkhead | 4 | BID AWARD AND REGISTER CONTRCT | 2008-10-29 | 2009-07-25 | 2015-03-30 | 2015-06-27
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200463 | Storm & San Sewers in College point b/t 9 av & US Bulkhead | 5 | CONSTRUCTION TO 25% | 2009-07-26 | 2010-07-20 | 2015-06-28 | 2015-10-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200463 | Storm & San Sewers in College point b/t 9 av & US Bulkhead | 6 | CONSTRUCTION TO 50% | 2010-07-21 | 2011-07-15 | 2015-10-26 | 2016-02-22
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200463 | Storm & San Sewers in College point b/t 9 av & US Bulkhead | 7 | CONSTRUCTION TO 75% | 2011-07-16 | 2012-07-09 | 2016-02-23 | 2016-06-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200463 | Storm & San Sewers in College point b/t 9 av & US Bulkhead | 8 | ORIGINAL EQUIP & FURNISHING | 2012-07-10 | 2013-04-05 | 2016-06-22 | 2016-09-19
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200463 | Storm & San Sewers in College point b/t 9 av & US Bulkhead | 9 | SUBSTANTIAL COMPLETION | 2013-04-06 | 2013-10-02 | 2016-09-20 | 2016-11-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200463 | Storm & San Sewers in College point b/t 9 av & US Bulkhead | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-10-03 | 2013-12-31 | 2016-11-19 | 2021-06-24
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200467 | STRM & SAN SWRS IN 14 AV B/T 115 ST & US BULKHEAD LINE | 1 | DEVELOP SCOPE | 2006-08-16 | 2007-05-12 | 2020-07-01 | 2020-09-28
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200467 | STRM & SAN SWRS IN 14 AV B/T 115 ST & US BULKHEAD LINE | 2 | PRELIMINARY DESIGN | 2007-05-13 | 2008-05-06 | 2020-09-29 | 2021-01-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200467 | STRM & SAN SWRS IN 14 AV B/T 115 ST & US BULKHEAD LINE | 3 | FINAL DESIGN | 2008-05-07 | 2009-10-28 | 2021-01-27 | 2021-07-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200467 | STRM & SAN SWRS IN 14 AV B/T 115 ST & US BULKHEAD LINE | 4 | BID AWARD AND REGISTER CONTRCT | 2009-10-29 | 2010-07-25 | 2021-07-26 | 2021-10-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200467 | STRM & SAN SWRS IN 14 AV B/T 115 ST & US BULKHEAD LINE | 5 | CONSTRUCTION TO 25% | 2010-07-26 | 2011-07-20 | 2021-10-24 | 2022-02-20
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200467 | STRM & SAN SWRS IN 14 AV B/T 115 ST & US BULKHEAD LINE | 6 | CONSTRUCTION TO 50% | 2011-07-21 | 2012-07-14 | 2022-02-21 | 2022-06-20
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200467 | STRM & SAN SWRS IN 14 AV B/T 115 ST & US BULKHEAD LINE | 7 | CONSTRUCTION TO 75% | 2012-07-15 | 2013-07-09 | 2022-06-21 | 2022-10-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200467 | STRM & SAN SWRS IN 14 AV B/T 115 ST & US BULKHEAD LINE | 8 | ORIGINAL EQUIP & FURNISHING | 2013-07-10 | 2014-04-05 | 2022-10-19 | 2023-01-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200467 | STRM & SAN SWRS IN 14 AV B/T 115 ST & US BULKHEAD LINE | 9 | SUBSTANTIAL COMPLETION | 2014-04-06 | 2014-10-02 | 2023-01-17 | 2023-03-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200467 | STRM & SAN SWRS IN 14 AV B/T 115 ST & US BULKHEAD LINE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-10-03 | 2014-12-31 | 2023-03-18 | 2028-04-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200489 | STRM SWR & W/M IN 202 ST B/T 118 AV & LINDEN BLVD, ETC... | 1 | DEVELOP SCOPE | 2009-07-01 | 2009-09-28 | 2011-07-01 | 2011-09-28
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200489 | STRM SWR & W/M IN 202 ST B/T 118 AV & LINDEN BLVD, ETC... | 2 | PRELIMINARY DESIGN | 2009-09-29 | 2010-01-26 | 2011-09-29 | 2012-01-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200489 | STRM SWR & W/M IN 202 ST B/T 118 AV & LINDEN BLVD, ETC... | 3 | FINAL DESIGN | 2010-01-27 | 2010-07-25 | 2012-01-27 | 2012-07-24
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200489 | STRM SWR & W/M IN 202 ST B/T 118 AV & LINDEN BLVD, ETC... | 4 | BID AWARD AND REGISTER CONTRCT | 2010-07-26 | 2010-10-23 | 2012-07-25 | 2012-10-22
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200489 | STRM SWR & W/M IN 202 ST B/T 118 AV & LINDEN BLVD, ETC... | 5 | CONSTRUCTION TO 25% | 2010-10-24 | 2011-02-20 | 2012-10-23 | 2013-02-19
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200489 | STRM SWR & W/M IN 202 ST B/T 118 AV & LINDEN BLVD, ETC... | 6 | CONSTRUCTION TO 50% | 2011-02-21 | 2011-06-20 | 2013-02-20 | 2013-06-19
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200489 | STRM SWR & W/M IN 202 ST B/T 118 AV & LINDEN BLVD, ETC... | 7 | CONSTRUCTION TO 75% | 2011-06-21 | 2011-10-18 | 2013-06-20 | 2013-10-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200489 | STRM SWR & W/M IN 202 ST B/T 118 AV & LINDEN BLVD, ETC... | 8 | ORIGINAL EQUIP & FURNISHING | 2011-10-19 | 2012-01-16 | 2013-10-18 | 2014-01-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200489 | STRM SWR & W/M IN 202 ST B/T 118 AV & LINDEN BLVD, ETC... | 9 | SUBSTANTIAL COMPLETION | 2012-01-17 | 2012-03-16 | 2014-01-16 | 2014-03-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200489 | STRM SWR & W/M IN 202 ST B/T 118 AV & LINDEN BLVD, ETC... | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-03-17 | 2012-04-15 | 2014-03-17 | 2021-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200490 | Storm Sewer in 95th Street, Queens | 1 | DEVELOP SCOPE | 2011-02-23 | 2011-05-23 | 2011-02-23 | 2011-05-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200490 | Storm Sewer in 95th Street, Queens | 2 | PRELIMINARY DESIGN | 2011-05-24 | 2011-09-20 | 2011-05-24 | 2011-09-20
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200490 | Storm Sewer in 95th Street, Queens | 3 | FINAL DESIGN | 2011-09-21 | 2012-03-18 | 2011-09-21 | 2016-03-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200490 | Storm Sewer in 95th Street, Queens | 4 | BID AWARD AND REGISTER CONTRCT | 2012-03-19 | 2012-06-16 | 2016-03-19 | 2016-03-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200490 | Storm Sewer in 95th Street, Queens | 5 | CONSTRUCTION TO 25% | 2012-06-17 | 2012-10-14 | 2016-03-19 | 2016-03-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200490 | Storm Sewer in 95th Street, Queens | 6 | CONSTRUCTION TO 50% | 2012-10-15 | 2013-02-11 | 2016-03-19 | 2016-03-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200490 | Storm Sewer in 95th Street, Queens | 7 | CONSTRUCTION TO 75% | 2013-02-12 | 2013-06-11 | 2016-03-19 | 2016-03-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200490 | Storm Sewer in 95th Street, Queens | 8 | ORIGINAL EQUIP & FURNISHING | 2013-06-12 | 2013-09-09 | 2016-03-19 | 2016-03-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200490 | Storm Sewer in 95th Street, Queens | 9 | SUBSTANTIAL COMPLETION | 2013-09-10 | 2013-11-08 | 2016-03-19 | 2016-03-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200490 | Storm Sewer in 95th Street, Queens | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-11-09 | 2013-12-08 | 2016-03-19 | 2024-07-22
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200491 | STRM EXT IN FERN PLACE B/T POLHEMUS AV & 108 RD, ETC.... | 1 | DEVELOP SCOPE | 2008-02-25 | 2008-05-24 | 2008-02-25 | 2008-05-24
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200491 | STRM EXT IN FERN PLACE B/T POLHEMUS AV & 108 RD, ETC.... | 2 | PRELIMINARY DESIGN | 2008-05-25 | 2008-09-21 | 2008-05-25 | 2008-09-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200491 | STRM EXT IN FERN PLACE B/T POLHEMUS AV & 108 RD, ETC.... | 3 | FINAL DESIGN | 2008-09-22 | 2009-03-20 | 2008-09-22 | 2009-03-20
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200491 | STRM EXT IN FERN PLACE B/T POLHEMUS AV & 108 RD, ETC.... | 4 | BID AWARD AND REGISTER CONTRCT | 2009-03-21 | 2009-06-18 | 2012-03-21 | 2012-08-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200491 | STRM EXT IN FERN PLACE B/T POLHEMUS AV & 108 RD, ETC.... | 5 | CONSTRUCTION TO 25% | 2009-06-19 | 2009-10-16 | 2012-08-19 | 2013-08-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200491 | STRM EXT IN FERN PLACE B/T POLHEMUS AV & 108 RD, ETC.... | 6 | CONSTRUCTION TO 50% | 2009-10-17 | 2010-02-13 | 2013-08-19 | 2014-08-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200491 | STRM EXT IN FERN PLACE B/T POLHEMUS AV & 108 RD, ETC.... | 7 | CONSTRUCTION TO 75% | 2010-02-14 | 2010-06-13 | 2014-08-19 | 2015-08-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200491 | STRM EXT IN FERN PLACE B/T POLHEMUS AV & 108 RD, ETC.... | 8 | ORIGINAL EQUIP & FURNISHING | 2010-06-14 | 2010-09-11 | 2015-08-19 | 2015-11-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200491 | STRM EXT IN FERN PLACE B/T POLHEMUS AV & 108 RD, ETC.... | 9 | SUBSTANTIAL COMPLETION | 2010-09-12 | 2010-11-10 | 2015-11-17 | 2016-01-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200491 | STRM EXT IN FERN PLACE B/T POLHEMUS AV & 108 RD, ETC.... | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2010-11-11 | 2010-12-10 | 2016-01-16 | 2021-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200492 | Storm sewer extension and san. replacement @ 41st avenue, | 1 | DEVELOP SCOPE | 2012-08-16 | 2013-05-12 | 2012-08-16 | 2013-05-12
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200492 | Storm sewer extension and san. replacement @ 41st avenue, | 2 | PRELIMINARY DESIGN | 2013-05-13 | 2014-05-07 | 2013-05-13 | 2014-05-07
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200492 | Storm sewer extension and san. replacement @ 41st avenue, | 3 | FINAL DESIGN | 2014-05-08 | 2015-10-29 | 2014-05-08 | 2015-10-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200492 | Storm sewer extension and san. replacement @ 41st avenue, | 4 | BID AWARD AND REGISTER CONTRCT | 2015-10-30 | 2016-07-25 | 2015-10-30 | 2016-07-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200492 | Storm sewer extension and san. replacement @ 41st avenue, | 5 | CONSTRUCTION TO 25% | 2016-07-26 | 2017-07-20 | 2016-07-26 | 2017-07-20
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200492 | Storm sewer extension and san. replacement @ 41st avenue, | 6 | CONSTRUCTION TO 50% | 2017-07-21 | 2018-07-15 | 2017-07-21 | 2018-07-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200492 | Storm sewer extension and san. replacement @ 41st avenue, | 7 | CONSTRUCTION TO 75% | 2018-07-16 | 2019-07-10 | 2018-07-16 | 2019-07-10
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200492 | Storm sewer extension and san. replacement @ 41st avenue, | 8 | ORIGINAL EQUIP & FURNISHING | 2019-07-11 | 2020-04-05 | 2019-07-11 | 2020-04-05
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200492 | Storm sewer extension and san. replacement @ 41st avenue, | 9 | SUBSTANTIAL COMPLETION | 2020-04-06 | 2020-10-02 | 2020-04-06 | 2020-10-02
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200492 | Storm sewer extension and san. replacement @ 41st avenue, | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-10-03 | 2020-12-31 | 2020-10-03 | 2020-12-31
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200506 | STORM, SANITARY SEWERS AND WATER MAIN IN 93 AVENUE | 1 | DEVELOP SCOPE | 2009-02-15 | 2009-05-15 | 2009-02-15 | 2009-05-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200506 | STORM, SANITARY SEWERS AND WATER MAIN IN 93 AVENUE | 2 | PRELIMINARY DESIGN | 2009-05-16 | 2009-09-12 | 2009-05-16 | 2009-09-12
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200506 | STORM, SANITARY SEWERS AND WATER MAIN IN 93 AVENUE | 3 | FINAL DESIGN | 2009-09-13 | 2010-03-11 | 2009-09-13 | 2010-03-11
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200506 | STORM, SANITARY SEWERS AND WATER MAIN IN 93 AVENUE | 4 | BID AWARD AND REGISTER CONTRCT | 2010-03-12 | 2010-06-09 | 2010-03-12 | 2010-06-09
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200506 | STORM, SANITARY SEWERS AND WATER MAIN IN 93 AVENUE | 5 | CONSTRUCTION TO 25% | 2010-06-10 | 2010-10-07 | 2010-06-10 | 2010-10-07
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200506 | STORM, SANITARY SEWERS AND WATER MAIN IN 93 AVENUE | 6 | CONSTRUCTION TO 50% | 2010-10-08 | 2011-02-04 | 2010-10-08 | 2011-02-04
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200506 | STORM, SANITARY SEWERS AND WATER MAIN IN 93 AVENUE | 7 | CONSTRUCTION TO 75% | 2011-02-05 | 2011-06-04 | 2011-02-05 | 2011-06-04
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200506 | STORM, SANITARY SEWERS AND WATER MAIN IN 93 AVENUE | 8 | ORIGINAL EQUIP & FURNISHING | 2011-06-05 | 2011-09-02 | 2011-06-05 | 2011-09-02
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200506 | STORM, SANITARY SEWERS AND WATER MAIN IN 93 AVENUE | 9 | SUBSTANTIAL COMPLETION | 2011-09-03 | 2011-11-01 | 2011-09-03 | 2011-11-01
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200506 | STORM, SANITARY SEWERS AND WATER MAIN IN 93 AVENUE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2011-11-02 | 2011-12-01 | 2011-11-02 | 2021-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200519 | SEQ - Brookville-Edgewood Triangle West - Phase II (HWQ724B) | 1 | DEVELOP SCOPE | 2010-06-30 | 2010-09-27 | 2010-06-30 | 2010-09-27
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200519 | SEQ - Brookville-Edgewood Triangle West - Phase II (HWQ724B) | 2 | PRELIMINARY DESIGN | 2010-09-28 | 2011-01-25 | 2010-09-28 | 2011-01-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200519 | SEQ - Brookville-Edgewood Triangle West - Phase II (HWQ724B) | 3 | FINAL DESIGN | 2011-01-26 | 2011-07-24 | 2011-01-26 | 2011-07-24
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200519 | SEQ - Brookville-Edgewood Triangle West - Phase II (HWQ724B) | 4 | BID AWARD AND REGISTER CONTRCT | 2011-07-25 | 2011-10-22 | 2014-03-31 | 2014-06-28
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200519 | SEQ - Brookville-Edgewood Triangle West - Phase II (HWQ724B) | 5 | CONSTRUCTION TO 25% | 2011-10-23 | 2012-02-19 | 2014-06-29 | 2014-06-28
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200519 | SEQ - Brookville-Edgewood Triangle West - Phase II (HWQ724B) | 6 | CONSTRUCTION TO 50% | 2012-02-20 | 2012-06-18 | 2014-06-29 | 2014-06-28
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200519 | SEQ - Brookville-Edgewood Triangle West - Phase II (HWQ724B) | 7 | CONSTRUCTION TO 75% | 2012-06-19 | 2012-10-16 | 2014-06-29 | 2014-06-28
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200519 | SEQ - Brookville-Edgewood Triangle West - Phase II (HWQ724B) | 8 | ORIGINAL EQUIP & FURNISHING | 2012-10-17 | 2013-01-14 | 2014-06-29 | 2014-06-28
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200519 | SEQ - Brookville-Edgewood Triangle West - Phase II (HWQ724B) | 9 | SUBSTANTIAL COMPLETION | 2013-01-15 | 2013-03-15 | 2014-06-29 | 2014-06-28
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200519 | SEQ - Brookville-Edgewood Triangle West - Phase II (HWQ724B) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-03-16 | 2013-04-14 | 2014-06-29 | 2027-03-22
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200524 | Storm & Sanitary Sewers in B. 21st Street, Queens | 1 | DEVELOP SCOPE | 2011-01-01 | 2011-03-31 | 2011-01-01 | 2011-03-31
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200524 | Storm & Sanitary Sewers in B. 21st Street, Queens | 2 | PRELIMINARY DESIGN | 2011-04-01 | 2011-07-29 | 2011-04-01 | 2011-07-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200524 | Storm & Sanitary Sewers in B. 21st Street, Queens | 3 | FINAL DESIGN | 2011-07-30 | 2012-01-25 | 2011-07-30 | 2014-03-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200524 | Storm & Sanitary Sewers in B. 21st Street, Queens | 4 | BID AWARD AND REGISTER CONTRCT | 2012-01-26 | 2012-04-24 | 2014-03-27 | 2014-06-24
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200524 | Storm & Sanitary Sewers in B. 21st Street, Queens | 5 | CONSTRUCTION TO 25% | 2012-04-25 | 2012-08-22 | 2014-06-25 | 2014-10-22
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200524 | Storm & Sanitary Sewers in B. 21st Street, Queens | 6 | CONSTRUCTION TO 50% | 2012-08-23 | 2012-12-20 | 2014-10-23 | 2015-02-19
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200524 | Storm & Sanitary Sewers in B. 21st Street, Queens | 7 | CONSTRUCTION TO 75% | 2012-12-21 | 2013-04-19 | 2015-02-20 | 2015-06-19
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200524 | Storm & Sanitary Sewers in B. 21st Street, Queens | 8 | ORIGINAL EQUIP & FURNISHING | 2013-04-20 | 2013-07-18 | 2016-09-01 | 2016-11-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200524 | Storm & Sanitary Sewers in B. 21st Street, Queens | 9 | SUBSTANTIAL COMPLETION | 2013-07-19 | 2013-09-16 | 2016-11-30 | 2017-01-28
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200524 | Storm & Sanitary Sewers in B. 21st Street, Queens | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-09-17 | 2013-10-16 | 2017-01-29 | 2023-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200529 | SEQ - Storm & Combined Sewers in 130th Road (Joint Bid) | 1 | DEVELOP SCOPE | 2012-02-22 | 2012-05-21 | 2016-03-01 | 2016-05-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200529 | SEQ - Storm & Combined Sewers in 130th Road (Joint Bid) | 2 | PRELIMINARY DESIGN | 2012-05-22 | 2012-09-18 | 2016-05-30 | 2017-08-02
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200529 | SEQ - Storm & Combined Sewers in 130th Road (Joint Bid) | 3 | FINAL DESIGN | 2012-09-19 | 2013-03-17 | 2017-08-03 | 2018-01-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200529 | SEQ - Storm & Combined Sewers in 130th Road (Joint Bid) | 4 | BID AWARD AND REGISTER CONTRCT | 2013-03-18 | 2013-06-15 | 2018-01-24 | 2018-08-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200529 | SEQ - Storm & Combined Sewers in 130th Road (Joint Bid) | 5 | CONSTRUCTION TO 25% | 2013-06-16 | 2013-10-13 | 2018-08-27 | 2018-12-24
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200529 | SEQ - Storm & Combined Sewers in 130th Road (Joint Bid) | 6 | CONSTRUCTION TO 50% | 2013-10-14 | 2014-02-10 | 2018-12-25 | 2019-04-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200529 | SEQ - Storm & Combined Sewers in 130th Road (Joint Bid) | 7 | CONSTRUCTION TO 75% | 2014-02-11 | 2014-06-10 | 2019-04-24 | 2021-10-28
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200529 | SEQ - Storm & Combined Sewers in 130th Road (Joint Bid) | 8 | ORIGINAL EQUIP & FURNISHING | 2014-06-11 | 2014-09-08 | 2021-10-29 | 2022-01-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200529 | SEQ - Storm & Combined Sewers in 130th Road (Joint Bid) | 9 | SUBSTANTIAL COMPLETION | 2014-09-09 | 2014-11-07 | 2022-01-27 | 2022-03-27
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200529 | SEQ - Storm & Combined Sewers in 130th Road (Joint Bid) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-11-08 | 2014-12-07 | 2022-03-28 | 2022-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200531 | SEQ - Storm Sewer Ext in 239th Street, Queens (Joint Bid) | 1 | DEVELOP SCOPE | 2014-02-27 | 2014-05-27 | 2010-03-19 | 2016-04-03
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200531 | SEQ - Storm Sewer Ext in 239th Street, Queens (Joint Bid) | 2 | PRELIMINARY DESIGN | 2014-05-28 | 2014-09-24 | 2016-04-04 | 2016-08-01
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200531 | SEQ - Storm Sewer Ext in 239th Street, Queens (Joint Bid) | 3 | FINAL DESIGN | 2014-09-25 | 2015-03-23 | 2016-08-02 | 2017-01-28
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200531 | SEQ - Storm Sewer Ext in 239th Street, Queens (Joint Bid) | 4 | BID AWARD AND REGISTER CONTRCT | 2015-03-24 | 2015-06-21 | 2017-01-29 | 2017-04-28
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200531 | SEQ - Storm Sewer Ext in 239th Street, Queens (Joint Bid) | 5 | CONSTRUCTION TO 25% | 2015-06-22 | 2015-10-19 | 2017-04-29 | 2017-08-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200531 | SEQ - Storm Sewer Ext in 239th Street, Queens (Joint Bid) | 6 | CONSTRUCTION TO 50% | 2015-10-20 | 2016-02-16 | 2017-08-27 | 2017-12-24
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200531 | SEQ - Storm Sewer Ext in 239th Street, Queens (Joint Bid) | 7 | CONSTRUCTION TO 75% | 2016-02-17 | 2016-06-15 | 2017-12-25 | 2018-04-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200531 | SEQ - Storm Sewer Ext in 239th Street, Queens (Joint Bid) | 8 | ORIGINAL EQUIP & FURNISHING | 2016-06-16 | 2016-09-13 | 2018-04-24 | 2018-07-22
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200531 | SEQ - Storm Sewer Ext in 239th Street, Queens (Joint Bid) | 9 | SUBSTANTIAL COMPLETION | 2016-09-14 | 2016-11-12 | 2018-07-23 | 2018-09-20
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200531 | SEQ - Storm Sewer Ext in 239th Street, Queens (Joint Bid) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-11-13 | 2016-12-12 | 2018-09-21 | 2022-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200536 | SEQ - Storm Sewer & Water Main in 182nd Street | 1 | DEVELOP SCOPE | 2010-02-27 | 2010-05-27 | 2010-02-27 | 2010-05-27
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200536 | SEQ - Storm Sewer & Water Main in 182nd Street | 2 | PRELIMINARY DESIGN | 2010-05-28 | 2010-09-24 | 2010-05-28 | 2010-09-24
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200536 | SEQ - Storm Sewer & Water Main in 182nd Street | 3 | FINAL DESIGN | 2010-09-25 | 2011-03-23 | 2010-09-25 | 2011-03-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200536 | SEQ - Storm Sewer & Water Main in 182nd Street | 4 | BID AWARD AND REGISTER CONTRCT | 2011-03-24 | 2011-06-21 | 2011-03-24 | 2011-06-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200536 | SEQ - Storm Sewer & Water Main in 182nd Street | 5 | CONSTRUCTION TO 25% | 2011-06-22 | 2011-10-19 | 2011-06-22 | 2011-12-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200536 | SEQ - Storm Sewer & Water Main in 182nd Street | 6 | CONSTRUCTION TO 50% | 2011-10-20 | 2012-02-16 | 2011-12-19 | 2012-12-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200536 | SEQ - Storm Sewer & Water Main in 182nd Street | 7 | CONSTRUCTION TO 75% | 2012-02-17 | 2012-06-15 | 2012-12-18 | 2013-12-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200536 | SEQ - Storm Sewer & Water Main in 182nd Street | 8 | ORIGINAL EQUIP & FURNISHING | 2012-06-16 | 2012-09-13 | 2013-12-18 | 2014-03-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200536 | SEQ - Storm Sewer & Water Main in 182nd Street | 9 | SUBSTANTIAL COMPLETION | 2012-09-14 | 2012-11-12 | 2014-03-18 | 2015-03-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200536 | SEQ - Storm Sewer & Water Main in 182nd Street | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-11-13 | 2012-12-12 | 2015-03-18 | 2021-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200538 | SEQ - Storm Sewer in 69th Ave, Glen Oaks Area, Queens | 3 | FINAL DESIGN | 2014-09-14 | 2015-03-12 | 2014-09-14 | 2015-03-12
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200538 | SEQ - Storm Sewer in 69th Ave, Glen Oaks Area, Queens | 4 | BID AWARD AND REGISTER CONTRCT | 2015-03-13 | 2015-06-10 | 2015-03-13 | 2015-06-10
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200538 | SEQ - Storm Sewer in 69th Ave, Glen Oaks Area, Queens | 5 | CONSTRUCTION TO 25% | 2015-06-11 | 2015-10-08 | 2015-06-11 | 2015-10-08
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200538 | SEQ - Storm Sewer in 69th Ave, Glen Oaks Area, Queens | 6 | CONSTRUCTION TO 50% | 2015-10-09 | 2016-02-05 | 2015-10-09 | 2016-02-05
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200538 | SEQ - Storm Sewer in 69th Ave, Glen Oaks Area, Queens | 7 | CONSTRUCTION TO 75% | 2016-02-06 | 2016-06-04 | 2016-02-06 | 2016-06-04
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200538 | SEQ - Storm Sewer in 69th Ave, Glen Oaks Area, Queens | 8 | ORIGINAL EQUIP & FURNISHING | 2016-06-05 | 2016-09-02 | 2016-06-05 | 2016-09-02
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200538 | SEQ - Storm Sewer in 69th Ave, Glen Oaks Area, Queens | 9 | SUBSTANTIAL COMPLETION | 2016-09-03 | 2016-11-01 | 2016-09-03 | 2016-11-01
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200538 | SEQ - Storm Sewer in 69th Ave, Glen Oaks Area, Queens | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-11-02 | 2016-12-01 | 2016-11-02 | 2018-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200547 | SEQ - Storm Sewer in Commonwealth Blvd | 1 | DEVELOP SCOPE | 2019-03-01 | 2019-05-29 | 2019-03-01 | 2019-05-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200547 | SEQ - Storm Sewer in Commonwealth Blvd | 2 | PRELIMINARY DESIGN | 2019-05-30 | 2019-09-26 | 2019-05-30 | 2019-09-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200547 | SEQ - Storm Sewer in Commonwealth Blvd | 3 | FINAL DESIGN | 2019-09-27 | 2020-03-24 | 2019-09-27 | 2020-03-24
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200547 | SEQ - Storm Sewer in Commonwealth Blvd | 4 | BID AWARD AND REGISTER CONTRCT | 2020-03-25 | 2020-06-22 | 2020-03-25 | 2020-06-22
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200547 | SEQ - Storm Sewer in Commonwealth Blvd | 5 | CONSTRUCTION TO 25% | 2020-06-23 | 2020-10-20 | 2020-06-23 | 2020-10-20
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200547 | SEQ - Storm Sewer in Commonwealth Blvd | 6 | CONSTRUCTION TO 50% | 2020-10-21 | 2021-02-17 | 2020-10-21 | 2021-02-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200547 | SEQ - Storm Sewer in Commonwealth Blvd | 7 | CONSTRUCTION TO 75% | 2021-02-18 | 2021-06-17 | 2021-02-18 | 2021-06-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200547 | SEQ - Storm Sewer in Commonwealth Blvd | 8 | ORIGINAL EQUIP & FURNISHING | 2021-06-18 | 2021-09-15 | 2021-06-18 | 2021-09-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200547 | SEQ - Storm Sewer in Commonwealth Blvd | 9 | SUBSTANTIAL COMPLETION | 2021-09-16 | 2021-11-14 | 2021-09-16 | 2021-11-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200547 | SEQ - Storm Sewer in Commonwealth Blvd | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-11-15 | 2021-12-14 | 2021-11-15 | 2026-08-10
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200550 | Storm & San Sewer Ext in 99 St, Rockwy Beach Blvd & Dead End | 1 | DEVELOP SCOPE | 2012-05-18 | 2013-02-11 | 2012-05-18 | 2013-02-11
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200550 | Storm & San Sewer Ext in 99 St, Rockwy Beach Blvd & Dead End | 2 | PRELIMINARY DESIGN | 2013-02-12 | 2014-02-06 | 2013-02-12 | 2014-02-06
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200550 | Storm & San Sewer Ext in 99 St, Rockwy Beach Blvd & Dead End | 3 | FINAL DESIGN | 2014-02-07 | 2015-07-31 | 2014-02-07 | 2015-07-31
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200550 | Storm & San Sewer Ext in 99 St, Rockwy Beach Blvd & Dead End | 4 | BID AWARD AND REGISTER CONTRCT | 2015-08-01 | 2016-04-26 | 2015-08-01 | 2016-04-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200550 | Storm & San Sewer Ext in 99 St, Rockwy Beach Blvd & Dead End | 5 | CONSTRUCTION TO 25% | 2016-04-27 | 2017-04-21 | 2016-04-27 | 2017-04-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200550 | Storm & San Sewer Ext in 99 St, Rockwy Beach Blvd & Dead End | 6 | CONSTRUCTION TO 50% | 2017-04-22 | 2018-04-16 | 2017-04-22 | 2018-04-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200550 | Storm & San Sewer Ext in 99 St, Rockwy Beach Blvd & Dead End | 7 | CONSTRUCTION TO 75% | 2018-04-17 | 2019-04-11 | 2018-04-17 | 2019-04-11
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200550 | Storm & San Sewer Ext in 99 St, Rockwy Beach Blvd & Dead End | 8 | ORIGINAL EQUIP & FURNISHING | 2019-04-12 | 2020-01-06 | 2019-04-12 | 2020-01-06
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200550 | Storm & San Sewer Ext in 99 St, Rockwy Beach Blvd & Dead End | 9 | SUBSTANTIAL COMPLETION | 2020-01-07 | 2020-07-04 | 2020-01-07 | 2020-07-04
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200550 | Storm & San Sewer Ext in 99 St, Rockwy Beach Blvd & Dead End | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-07-05 | 2020-10-02 | 2020-07-05 | 2020-10-02
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200553 | Combined & HLSS & WM Work in Lefferts Blvd | 1 | DEVELOP SCOPE | 2014-06-30 | 2015-03-26 | 2014-06-30 | 2015-03-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200553 | Combined & HLSS & WM Work in Lefferts Blvd | 2 | PRELIMINARY DESIGN | 2015-03-27 | 2016-03-20 | 2015-03-27 | 2016-03-20
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200553 | Combined & HLSS & WM Work in Lefferts Blvd | 3 | FINAL DESIGN | 2016-03-21 | 2017-09-11 | 2016-03-21 | 2017-09-11
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200553 | Combined & HLSS & WM Work in Lefferts Blvd | 4 | BID AWARD AND REGISTER CONTRCT | 2017-09-12 | 2018-06-08 | 2017-09-12 | 2018-06-08
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200553 | Combined & HLSS & WM Work in Lefferts Blvd | 5 | CONSTRUCTION TO 25% | 2018-06-09 | 2019-06-03 | 2018-06-09 | 2019-06-03
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200553 | Combined & HLSS & WM Work in Lefferts Blvd | 6 | CONSTRUCTION TO 50% | 2019-06-04 | 2020-05-28 | 2019-06-04 | 2020-05-28
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200553 | Combined & HLSS & WM Work in Lefferts Blvd | 7 | CONSTRUCTION TO 75% | 2020-05-29 | 2021-05-23 | 2020-05-29 | 2021-05-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200553 | Combined & HLSS & WM Work in Lefferts Blvd | 8 | ORIGINAL EQUIP & FURNISHING | 2021-05-24 | 2022-02-17 | 2021-05-24 | 2022-02-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200553 | Combined & HLSS & WM Work in Lefferts Blvd | 9 | SUBSTANTIAL COMPLETION | 2022-02-18 | 2022-08-16 | 2022-02-18 | 2022-08-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200553 | Combined & HLSS & WM Work in Lefferts Blvd | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-08-17 | 2022-11-14 | 2022-08-17 | 2022-11-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200558 | Install of storm SE & replacement of sanitary SE & dist.WM | 1 | DEVELOP SCOPE | 2019-08-23 | 2020-05-18 | 2019-08-23 | 2020-05-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200558 | Install of storm SE & replacement of sanitary SE & dist.WM | 2 | PRELIMINARY DESIGN | 2020-05-19 | 2021-05-13 | 2020-05-19 | 2021-05-13
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200558 | Install of storm SE & replacement of sanitary SE & dist.WM | 3 | FINAL DESIGN | 2021-05-14 | 2022-11-04 | 2021-05-14 | 2022-11-04
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200558 | Install of storm SE & replacement of sanitary SE & dist.WM | 4 | BID AWARD AND REGISTER CONTRCT | 2022-11-05 | 2023-08-01 | 2022-11-05 | 2023-08-01
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200558 | Install of storm SE & replacement of sanitary SE & dist.WM | 5 | CONSTRUCTION TO 25% | 2023-08-02 | 2024-07-26 | 2023-08-02 | 2024-07-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200558 | Install of storm SE & replacement of sanitary SE & dist.WM | 6 | CONSTRUCTION TO 50% | 2024-07-27 | 2025-07-21 | 2024-07-27 | 2025-07-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200558 | Install of storm SE & replacement of sanitary SE & dist.WM | 7 | CONSTRUCTION TO 75% | 2025-07-22 | 2026-07-16 | 2025-07-22 | 2026-07-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200558 | Install of storm SE & replacement of sanitary SE & dist.WM | 8 | ORIGINAL EQUIP & FURNISHING | 2026-07-17 | 2027-04-12 | 2026-07-17 | 2027-04-12
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200558 | Install of storm SE & replacement of sanitary SE & dist.WM | 9 | SUBSTANTIAL COMPLETION | 2027-04-13 | 2027-10-09 | 2027-04-13 | 2027-10-09
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200558 | Install of storm SE & replacement of sanitary SE & dist.WM | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2027-10-10 | 2028-01-07 | 2027-10-10 | 2028-01-07
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200562 | SEQ - Storm Sewer & WM Work in 158th Street (HWQ121B3) | 1 | DEVELOP SCOPE | 2014-02-16 | 2014-05-16 | 2014-02-16 | 2014-05-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200562 | SEQ - Storm Sewer & WM Work in 158th Street (HWQ121B3) | 2 | PRELIMINARY DESIGN | 2014-05-17 | 2014-09-13 | 2014-05-17 | 2014-09-13
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200562 | SEQ - Storm Sewer & WM Work in 158th Street (HWQ121B3) | 3 | FINAL DESIGN | 2014-09-14 | 2015-03-12 | 2014-09-14 | 2015-03-12
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200562 | SEQ - Storm Sewer & WM Work in 158th Street (HWQ121B3) | 4 | BID AWARD AND REGISTER CONTRCT | 2015-03-13 | 2015-06-10 | 2015-03-13 | 2015-06-10
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200562 | SEQ - Storm Sewer & WM Work in 158th Street (HWQ121B3) | 5 | CONSTRUCTION TO 25% | 2015-06-11 | 2015-10-08 | 2015-06-11 | 2015-10-08
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200562 | SEQ - Storm Sewer & WM Work in 158th Street (HWQ121B3) | 6 | CONSTRUCTION TO 50% | 2015-10-09 | 2016-02-05 | 2015-10-09 | 2016-02-05
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200562 | SEQ - Storm Sewer & WM Work in 158th Street (HWQ121B3) | 7 | CONSTRUCTION TO 75% | 2016-02-06 | 2016-06-04 | 2016-02-06 | 2016-06-04
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200562 | SEQ - Storm Sewer & WM Work in 158th Street (HWQ121B3) | 8 | ORIGINAL EQUIP & FURNISHING | 2016-06-05 | 2016-09-02 | 2016-06-05 | 2016-09-02
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200562 | SEQ - Storm Sewer & WM Work in 158th Street (HWQ121B3) | 9 | SUBSTANTIAL COMPLETION | 2016-09-03 | 2016-11-01 | 2016-09-03 | 2016-11-01
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200562 | SEQ - Storm Sewer & WM Work in 158th Street (HWQ121B3) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-11-02 | 2016-12-01 | 2016-11-02 | 2022-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200569 | Construction of Storm Sewers in 204th Street, Queens. | 1 | DEVELOP SCOPE | 2014-06-30 | 2015-03-26 | 2014-06-30 | 2015-03-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200569 | Construction of Storm Sewers in 204th Street, Queens. | 2 | PRELIMINARY DESIGN | 2015-03-27 | 2016-03-20 | 2015-03-27 | 2016-03-20
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200569 | Construction of Storm Sewers in 204th Street, Queens. | 3 | FINAL DESIGN | 2016-03-21 | 2017-09-11 | 2016-03-21 | 2017-09-11
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200569 | Construction of Storm Sewers in 204th Street, Queens. | 4 | BID AWARD AND REGISTER CONTRCT | 2017-09-12 | 2018-06-08 | 2017-09-12 | 2018-06-08
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200569 | Construction of Storm Sewers in 204th Street, Queens. | 5 | CONSTRUCTION TO 25% | 2018-06-09 | 2019-06-03 | 2018-06-09 | 2019-06-03
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200569 | Construction of Storm Sewers in 204th Street, Queens. | 6 | CONSTRUCTION TO 50% | 2019-06-04 | 2020-05-28 | 2019-06-04 | 2020-05-28
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200569 | Construction of Storm Sewers in 204th Street, Queens. | 7 | CONSTRUCTION TO 75% | 2020-05-29 | 2021-05-23 | 2020-05-29 | 2021-05-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200569 | Construction of Storm Sewers in 204th Street, Queens. | 8 | ORIGINAL EQUIP & FURNISHING | 2021-05-24 | 2022-02-17 | 2021-05-24 | 2022-02-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200569 | Construction of Storm Sewers in 204th Street, Queens. | 9 | SUBSTANTIAL COMPLETION | 2022-02-18 | 2022-08-16 | 2022-02-18 | 2022-08-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200569 | Construction of Storm Sewers in 204th Street, Queens. | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-08-17 | 2022-11-14 | 2022-08-17 | 2022-11-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200578 | SEQ - Storm & San Sewers, WM Work in Foch Blvd (HWQ200578) | 1 | DEVELOP SCOPE | 2017-03-01 | 2017-05-29 | 2017-03-01 | 2017-05-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200578 | SEQ - Storm & San Sewers, WM Work in Foch Blvd (HWQ200578) | 2 | PRELIMINARY DESIGN | 2017-05-30 | 2017-09-26 | 2017-05-30 | 2017-09-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200578 | SEQ - Storm & San Sewers, WM Work in Foch Blvd (HWQ200578) | 3 | FINAL DESIGN | 2017-09-27 | 2018-03-25 | 2017-09-27 | 2018-03-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200578 | SEQ - Storm & San Sewers, WM Work in Foch Blvd (HWQ200578) | 4 | BID AWARD AND REGISTER CONTRCT | 2018-03-26 | 2018-06-23 | 2018-03-26 | 2018-06-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200578 | SEQ - Storm & San Sewers, WM Work in Foch Blvd (HWQ200578) | 5 | CONSTRUCTION TO 25% | 2018-06-24 | 2018-10-21 | 2018-06-24 | 2018-10-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200578 | SEQ - Storm & San Sewers, WM Work in Foch Blvd (HWQ200578) | 6 | CONSTRUCTION TO 50% | 2018-10-22 | 2019-02-18 | 2018-10-22 | 2019-02-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200578 | SEQ - Storm & San Sewers, WM Work in Foch Blvd (HWQ200578) | 7 | CONSTRUCTION TO 75% | 2019-02-19 | 2019-06-18 | 2019-02-19 | 2019-06-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200578 | SEQ - Storm & San Sewers, WM Work in Foch Blvd (HWQ200578) | 8 | ORIGINAL EQUIP & FURNISHING | 2019-06-19 | 2019-09-16 | 2019-06-19 | 2019-09-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200578 | SEQ - Storm & San Sewers, WM Work in Foch Blvd (HWQ200578) | 9 | SUBSTANTIAL COMPLETION | 2019-09-17 | 2019-11-15 | 2019-09-17 | 2019-11-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200578 | SEQ - Storm & San Sewers, WM Work in Foch Blvd (HWQ200578) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-11-16 | 2019-12-15 | 2019-11-16 | 2022-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200584 | SEQ-Storm and Sanitary Sewers in 119th Road | 1 | DEVELOP SCOPE | 2015-02-16 | 2015-05-16 | 2015-02-16 | 2015-05-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200584 | SEQ-Storm and Sanitary Sewers in 119th Road | 2 | PRELIMINARY DESIGN | 2015-05-17 | 2015-09-13 | 2015-05-17 | 2015-09-13
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200584 | SEQ-Storm and Sanitary Sewers in 119th Road | 3 | FINAL DESIGN | 2015-09-14 | 2016-03-11 | 2015-09-14 | 2016-03-11
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200584 | SEQ-Storm and Sanitary Sewers in 119th Road | 4 | BID AWARD AND REGISTER CONTRCT | 2016-03-12 | 2016-06-09 | 2016-03-12 | 2016-06-09
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200584 | SEQ-Storm and Sanitary Sewers in 119th Road | 5 | CONSTRUCTION TO 25% | 2016-06-10 | 2016-10-07 | 2016-06-10 | 2016-10-07
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200584 | SEQ-Storm and Sanitary Sewers in 119th Road | 6 | CONSTRUCTION TO 50% | 2016-10-08 | 2017-02-04 | 2016-10-08 | 2017-02-04
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200584 | SEQ-Storm and Sanitary Sewers in 119th Road | 7 | CONSTRUCTION TO 75% | 2017-02-05 | 2017-06-04 | 2017-02-05 | 2017-06-04
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200584 | SEQ-Storm and Sanitary Sewers in 119th Road | 8 | ORIGINAL EQUIP & FURNISHING | 2017-06-05 | 2017-09-02 | 2017-06-05 | 2017-09-02
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200584 | SEQ-Storm and Sanitary Sewers in 119th Road | 9 | SUBSTANTIAL COMPLETION | 2017-09-03 | 2017-11-01 | 2017-09-03 | 2017-11-01
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200584 | SEQ-Storm and Sanitary Sewers in 119th Road | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-11-02 | 2017-12-01 | 2017-11-02 | 2021-09-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200586 | Broad Channel: Storm & San Sewers in W 11th Rd. (HWQ1182B) | 1 | DEVELOP SCOPE | 2017-03-01 | 2017-05-29 | 2017-03-01 | 2017-05-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200586 | Broad Channel: Storm & San Sewers in W 11th Rd. (HWQ1182B) | 2 | PRELIMINARY DESIGN | 2017-05-30 | 2017-09-26 | 2017-05-30 | 2017-09-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200586 | Broad Channel: Storm & San Sewers in W 11th Rd. (HWQ1182B) | 3 | FINAL DESIGN | 2017-09-27 | 2018-03-25 | 2017-09-27 | 2018-03-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200586 | Broad Channel: Storm & San Sewers in W 11th Rd. (HWQ1182B) | 4 | BID AWARD AND REGISTER CONTRCT | 2018-03-26 | 2018-06-23 | 2018-03-26 | 2018-06-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200586 | Broad Channel: Storm & San Sewers in W 11th Rd. (HWQ1182B) | 5 | CONSTRUCTION TO 25% | 2018-06-24 | 2018-10-21 | 2018-06-24 | 2018-10-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200586 | Broad Channel: Storm & San Sewers in W 11th Rd. (HWQ1182B) | 6 | CONSTRUCTION TO 50% | 2018-10-22 | 2019-02-18 | 2018-10-22 | 2019-02-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200586 | Broad Channel: Storm & San Sewers in W 11th Rd. (HWQ1182B) | 7 | CONSTRUCTION TO 75% | 2019-02-19 | 2019-06-18 | 2019-02-19 | 2019-06-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200586 | Broad Channel: Storm & San Sewers in W 11th Rd. (HWQ1182B) | 8 | ORIGINAL EQUIP & FURNISHING | 2019-06-19 | 2019-09-16 | 2019-06-19 | 2019-09-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200586 | Broad Channel: Storm & San Sewers in W 11th Rd. (HWQ1182B) | 9 | SUBSTANTIAL COMPLETION | 2019-09-17 | 2019-11-15 | 2019-09-17 | 2019-11-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200586 | Broad Channel: Storm & San Sewers in W 11th Rd. (HWQ1182B) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-11-16 | 2019-12-15 | 2019-11-16 | 2027-07-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200595 | Westbourne Ave-Norton Drive Recon (HWQ1187, SAND1187) | 1 | DEVELOP SCOPE | 2018-03-01 | 2018-05-29 | 2018-03-01 | 2018-05-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200595 | Westbourne Ave-Norton Drive Recon (HWQ1187, SAND1187) | 2 | PRELIMINARY DESIGN | 2018-05-30 | 2018-09-26 | 2018-05-30 | 2018-09-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200595 | Westbourne Ave-Norton Drive Recon (HWQ1187, SAND1187) | 3 | FINAL DESIGN | 2018-09-27 | 2019-03-25 | 2018-09-27 | 2019-03-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200595 | Westbourne Ave-Norton Drive Recon (HWQ1187, SAND1187) | 4 | BID AWARD AND REGISTER CONTRCT | 2019-03-26 | 2019-06-23 | 2019-03-26 | 2019-06-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200595 | Westbourne Ave-Norton Drive Recon (HWQ1187, SAND1187) | 5 | CONSTRUCTION TO 25% | 2019-06-24 | 2019-10-21 | 2019-06-24 | 2019-10-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200595 | Westbourne Ave-Norton Drive Recon (HWQ1187, SAND1187) | 6 | CONSTRUCTION TO 50% | 2019-10-22 | 2020-02-18 | 2019-10-22 | 2020-02-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200595 | Westbourne Ave-Norton Drive Recon (HWQ1187, SAND1187) | 7 | CONSTRUCTION TO 75% | 2020-02-19 | 2020-06-17 | 2020-02-19 | 2020-06-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200595 | Westbourne Ave-Norton Drive Recon (HWQ1187, SAND1187) | 8 | ORIGINAL EQUIP & FURNISHING | 2020-06-18 | 2020-09-15 | 2020-06-18 | 2020-09-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200595 | Westbourne Ave-Norton Drive Recon (HWQ1187, SAND1187) | 9 | SUBSTANTIAL COMPLETION | 2020-09-16 | 2020-11-14 | 2020-09-16 | 2020-11-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200595 | Westbourne Ave-Norton Drive Recon (HWQ1187, SAND1187) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-11-15 | 2020-12-14 | 2020-11-15 | 2029-09-11
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200596 | SEQ - Storm Sewer Installation & WM in 183rd Street | 1 | DEVELOP SCOPE | 2017-03-01 | 2017-05-29 | 2017-03-01 | 2017-08-07
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200596 | SEQ - Storm Sewer Installation & WM in 183rd Street | 2 | PRELIMINARY DESIGN | 2017-05-30 | 2017-09-26 | 2017-08-08 | 2017-10-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200596 | SEQ - Storm Sewer Installation & WM in 183rd Street | 3 | FINAL DESIGN | 2017-09-27 | 2018-03-25 | 2017-10-16 | 2017-12-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200596 | SEQ - Storm Sewer Installation & WM in 183rd Street | 4 | BID AWARD AND REGISTER CONTRCT | 2018-03-26 | 2018-06-23 | 2017-12-19 | 2018-10-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200596 | SEQ - Storm Sewer Installation & WM in 183rd Street | 5 | CONSTRUCTION TO 25% | 2018-06-24 | 2018-10-21 | 2018-10-31 | 2019-02-27
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200596 | SEQ - Storm Sewer Installation & WM in 183rd Street | 6 | CONSTRUCTION TO 50% | 2018-10-22 | 2019-02-18 | 2019-02-28 | 2019-06-27
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200596 | SEQ - Storm Sewer Installation & WM in 183rd Street | 7 | CONSTRUCTION TO 75% | 2019-02-19 | 2019-06-18 | 2019-06-28 | 2019-10-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200596 | SEQ - Storm Sewer Installation & WM in 183rd Street | 8 | ORIGINAL EQUIP & FURNISHING | 2019-06-19 | 2019-09-16 | 2019-10-26 | 2020-01-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200596 | SEQ - Storm Sewer Installation & WM in 183rd Street | 9 | SUBSTANTIAL COMPLETION | 2019-09-17 | 2019-11-15 | 2020-01-24 | 2020-03-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200596 | SEQ - Storm Sewer Installation & WM in 183rd Street | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-11-16 | 2019-12-15 | 2020-03-24 | 2022-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ201BN9 | Reconstruction of Existing Sewers, North Queens | 1 | DEVELOP SCOPE | 2017-03-01 | 2017-05-29 | 2017-03-01 | 2017-05-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ201BN9 | Reconstruction of Existing Sewers, North Queens | 2 | PRELIMINARY DESIGN | 2017-05-30 | 2017-09-26 | 2017-05-30 | 2017-09-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ201BN9 | Reconstruction of Existing Sewers, North Queens | 3 | FINAL DESIGN | 2017-09-27 | 2018-03-25 | 2017-09-27 | 2018-03-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ201BN9 | Reconstruction of Existing Sewers, North Queens | 4 | BID AWARD AND REGISTER CONTRCT | 2018-03-26 | 2018-06-23 | 2018-03-26 | 2018-06-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ201BN9 | Reconstruction of Existing Sewers, North Queens | 5 | CONSTRUCTION TO 25% | 2018-06-24 | 2018-10-21 | 2018-06-24 | 2018-10-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ201BN9 | Reconstruction of Existing Sewers, North Queens | 6 | CONSTRUCTION TO 50% | 2018-10-22 | 2019-02-18 | 2018-10-22 | 2019-02-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ201BN9 | Reconstruction of Existing Sewers, North Queens | 7 | CONSTRUCTION TO 75% | 2019-02-19 | 2019-06-18 | 2019-02-19 | 2019-06-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ201BN9 | Reconstruction of Existing Sewers, North Queens | 8 | ORIGINAL EQUIP & FURNISHING | 2019-06-19 | 2019-09-16 | 2019-06-19 | 2019-09-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ201BN9 | Reconstruction of Existing Sewers, North Queens | 9 | SUBSTANTIAL COMPLETION | 2019-09-17 | 2019-11-15 | 2019-09-17 | 2019-11-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ201BN9 | Reconstruction of Existing Sewers, North Queens | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-11-16 | 2019-12-15 | 2019-11-16 | 2022-11-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQBS11 | Reconstruction of Existing Sewers, South Queens | 1 | DEVELOP SCOPE | 2022-06-01 | 2022-08-29 | 2020-06-01 | 2020-08-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQBS11 | Reconstruction of Existing Sewers, South Queens | 2 | PRELIMINARY DESIGN | 2022-08-30 | 2022-12-27 | 2020-08-30 | 2020-12-27
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQBS11 | Reconstruction of Existing Sewers, South Queens | 3 | FINAL DESIGN | 2022-12-28 | 2023-06-25 | 2020-12-28 | 2021-06-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQBS11 | Reconstruction of Existing Sewers, South Queens | 4 | BID AWARD AND REGISTER CONTRCT | 2023-06-26 | 2023-09-23 | 2021-06-26 | 2021-09-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQBS11 | Reconstruction of Existing Sewers, South Queens | 5 | CONSTRUCTION TO 25% | 2023-09-24 | 2024-01-21 | 2021-09-24 | 2022-01-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQBS11 | Reconstruction of Existing Sewers, South Queens | 6 | CONSTRUCTION TO 50% | 2024-01-22 | 2024-05-20 | 2022-01-22 | 2022-05-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQBS11 | Reconstruction of Existing Sewers, South Queens | 7 | CONSTRUCTION TO 75% | 2024-05-21 | 2024-09-17 | 2022-05-22 | 2022-09-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQBS11 | Reconstruction of Existing Sewers, South Queens | 8 | ORIGINAL EQUIP & FURNISHING | 2024-09-18 | 2024-12-16 | 2022-09-19 | 2022-12-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQBS11 | Reconstruction of Existing Sewers, South Queens | 9 | SUBSTANTIAL COMPLETION | 2024-12-17 | 2025-02-14 | 2022-12-18 | 2023-02-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQBS11 | Reconstruction of Existing Sewers, South Queens | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-02-15 | 2025-03-16 | 2023-02-16 | 2023-03-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS001 | SEQ - Sewer When & Where Contract in SE Queens | 1 | DEVELOP SCOPE | 2014-10-01 | 2014-12-29 | 2014-10-01 | 2015-02-08
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS001 | SEQ - Sewer When & Where Contract in SE Queens | 2 | PRELIMINARY DESIGN | 2014-12-30 | 2015-04-28 | 2015-02-09 | 2015-08-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS001 | SEQ - Sewer When & Where Contract in SE Queens | 3 | FINAL DESIGN | 2015-04-29 | 2015-10-25 | 2015-08-16 | 2016-07-13
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS001 | SEQ - Sewer When & Where Contract in SE Queens | 4 | BID AWARD AND REGISTER CONTRCT | 2015-10-26 | 2016-01-23 | 2016-07-14 | 2017-07-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS001 | SEQ - Sewer When & Where Contract in SE Queens | 5 | CONSTRUCTION TO 25% | 2016-01-24 | 2016-05-22 | 2017-07-17 | 2017-11-13
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS001 | SEQ - Sewer When & Where Contract in SE Queens | 6 | CONSTRUCTION TO 50% | 2016-05-23 | 2016-09-19 | 2017-11-14 | 2018-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS001 | SEQ - Sewer When & Where Contract in SE Queens | 7 | CONSTRUCTION TO 75% | 2016-09-20 | 2017-01-17 | 2018-07-01 | 2018-10-28
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS001 | SEQ - Sewer When & Where Contract in SE Queens | 8 | ORIGINAL EQUIP & FURNISHING | 2017-01-18 | 2017-04-17 | 2018-10-29 | 2019-01-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS001 | SEQ - Sewer When & Where Contract in SE Queens | 9 | SUBSTANTIAL COMPLETION | 2017-04-18 | 2017-06-16 | 2019-01-27 | 2019-03-27
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS001 | SEQ - Sewer When & Where Contract in SE Queens | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-06-17 | 2017-07-16 | 2019-03-28 | 2022-06-11
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS002 | SEQ - Sewer When & Where Contract in SE Queens | 1 | DEVELOP SCOPE | 2017-03-01 | 2017-05-29 | 2017-03-01 | 2017-05-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS002 | SEQ - Sewer When & Where Contract in SE Queens | 2 | PRELIMINARY DESIGN | 2017-05-30 | 2017-09-26 | 2017-05-30 | 2017-09-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS002 | SEQ - Sewer When & Where Contract in SE Queens | 3 | FINAL DESIGN | 2017-09-27 | 2018-03-25 | 2017-09-27 | 2018-03-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS002 | SEQ - Sewer When & Where Contract in SE Queens | 4 | BID AWARD AND REGISTER CONTRCT | 2018-03-26 | 2018-06-23 | 2018-03-26 | 2018-06-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS002 | SEQ - Sewer When & Where Contract in SE Queens | 5 | CONSTRUCTION TO 25% | 2018-06-24 | 2018-10-21 | 2018-06-24 | 2018-10-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS002 | SEQ - Sewer When & Where Contract in SE Queens | 6 | CONSTRUCTION TO 50% | 2018-10-22 | 2019-02-18 | 2018-10-22 | 2019-02-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS002 | SEQ - Sewer When & Where Contract in SE Queens | 7 | CONSTRUCTION TO 75% | 2019-02-19 | 2019-06-18 | 2019-02-19 | 2019-06-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS002 | SEQ - Sewer When & Where Contract in SE Queens | 8 | ORIGINAL EQUIP & FURNISHING | 2019-06-19 | 2019-09-16 | 2019-06-19 | 2019-09-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS002 | SEQ - Sewer When & Where Contract in SE Queens | 9 | SUBSTANTIAL COMPLETION | 2019-09-17 | 2019-11-15 | 2019-09-17 | 2019-11-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS002 | SEQ - Sewer When & Where Contract in SE Queens | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-11-16 | 2019-12-15 | 2019-11-16 | 2022-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS003 | SEQ - Sewer When & Where Contract in SE Queens (HWQ1195) | 1 | DEVELOP SCOPE | 2017-03-01 | 2017-05-29 | 2017-03-01 | 2017-05-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS003 | SEQ - Sewer When & Where Contract in SE Queens (HWQ1195) | 2 | PRELIMINARY DESIGN | 2017-05-30 | 2017-09-26 | 2017-05-30 | 2017-09-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS003 | SEQ - Sewer When & Where Contract in SE Queens (HWQ1195) | 3 | FINAL DESIGN | 2017-09-27 | 2018-03-25 | 2017-09-27 | 2018-03-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS003 | SEQ - Sewer When & Where Contract in SE Queens (HWQ1195) | 4 | BID AWARD AND REGISTER CONTRCT | 2018-03-26 | 2018-06-23 | 2018-03-26 | 2018-06-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS003 | SEQ - Sewer When & Where Contract in SE Queens (HWQ1195) | 5 | CONSTRUCTION TO 25% | 2018-06-24 | 2018-10-21 | 2018-06-24 | 2018-10-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS003 | SEQ - Sewer When & Where Contract in SE Queens (HWQ1195) | 6 | CONSTRUCTION TO 50% | 2018-10-22 | 2019-02-18 | 2018-10-22 | 2019-02-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS003 | SEQ - Sewer When & Where Contract in SE Queens (HWQ1195) | 7 | CONSTRUCTION TO 75% | 2019-02-19 | 2019-06-18 | 2019-02-19 | 2019-06-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS003 | SEQ - Sewer When & Where Contract in SE Queens (HWQ1195) | 8 | ORIGINAL EQUIP & FURNISHING | 2019-06-19 | 2019-09-16 | 2019-06-19 | 2019-09-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS003 | SEQ - Sewer When & Where Contract in SE Queens (HWQ1195) | 9 | SUBSTANTIAL COMPLETION | 2019-09-17 | 2019-11-15 | 2019-09-17 | 2019-11-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS003 | SEQ - Sewer When & Where Contract in SE Queens (HWQ1195) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-11-16 | 2019-12-15 | 2019-11-16 | 2026-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS004 | SEQ -SEWER WHEN & WHERE CONTRACT IN S.E. QNS | 1 | DEVELOP SCOPE | 2019-06-01 | 2019-08-29 | 2019-06-01 | 2019-08-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS004 | SEQ -SEWER WHEN & WHERE CONTRACT IN S.E. QNS | 2 | PRELIMINARY DESIGN | 2019-08-30 | 2019-12-27 | 2019-08-30 | 2019-12-27
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS004 | SEQ -SEWER WHEN & WHERE CONTRACT IN S.E. QNS | 3 | FINAL DESIGN | 2019-12-28 | 2020-06-24 | 2019-12-28 | 2020-06-24
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS004 | SEQ -SEWER WHEN & WHERE CONTRACT IN S.E. QNS | 4 | BID AWARD AND REGISTER CONTRCT | 2020-06-25 | 2020-09-22 | 2020-06-25 | 2020-09-22
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS004 | SEQ -SEWER WHEN & WHERE CONTRACT IN S.E. QNS | 5 | CONSTRUCTION TO 25% | 2020-09-23 | 2021-01-20 | 2020-09-23 | 2021-01-20
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS004 | SEQ -SEWER WHEN & WHERE CONTRACT IN S.E. QNS | 6 | CONSTRUCTION TO 50% | 2021-01-21 | 2021-05-20 | 2021-01-21 | 2021-05-20
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS004 | SEQ -SEWER WHEN & WHERE CONTRACT IN S.E. QNS | 7 | CONSTRUCTION TO 75% | 2021-05-21 | 2021-09-17 | 2021-05-21 | 2021-09-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS004 | SEQ -SEWER WHEN & WHERE CONTRACT IN S.E. QNS | 8 | ORIGINAL EQUIP & FURNISHING | 2021-09-18 | 2021-12-16 | 2021-09-18 | 2021-12-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS004 | SEQ -SEWER WHEN & WHERE CONTRACT IN S.E. QNS | 9 | SUBSTANTIAL COMPLETION | 2021-12-17 | 2022-02-14 | 2021-12-17 | 2022-02-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS004 | SEQ -SEWER WHEN & WHERE CONTRACT IN S.E. QNS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-02-15 | 2022-03-16 | 2022-02-15 | 2024-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS005 | SEQ - Sewer When & Where Contract in SE Queens | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-08-29 | 2020-06-01 | 2020-08-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS005 | SEQ - Sewer When & Where Contract in SE Queens | 2 | PRELIMINARY DESIGN | 2020-08-30 | 2020-12-27 | 2020-08-30 | 2020-12-27
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS005 | SEQ - Sewer When & Where Contract in SE Queens | 3 | FINAL DESIGN | 2020-12-28 | 2021-06-25 | 2020-12-28 | 2021-06-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS005 | SEQ - Sewer When & Where Contract in SE Queens | 4 | BID AWARD AND REGISTER CONTRCT | 2021-06-26 | 2021-09-23 | 2021-06-26 | 2021-09-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS005 | SEQ - Sewer When & Where Contract in SE Queens | 5 | CONSTRUCTION TO 25% | 2021-09-24 | 2022-01-21 | 2021-09-24 | 2022-01-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS005 | SEQ - Sewer When & Where Contract in SE Queens | 6 | CONSTRUCTION TO 50% | 2022-01-22 | 2022-05-21 | 2022-01-22 | 2022-05-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS005 | SEQ - Sewer When & Where Contract in SE Queens | 7 | CONSTRUCTION TO 75% | 2022-05-22 | 2022-09-18 | 2022-05-22 | 2022-09-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS005 | SEQ - Sewer When & Where Contract in SE Queens | 8 | ORIGINAL EQUIP & FURNISHING | 2022-09-19 | 2022-12-17 | 2022-09-19 | 2022-12-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS005 | SEQ - Sewer When & Where Contract in SE Queens | 9 | SUBSTANTIAL COMPLETION | 2022-12-18 | 2023-02-15 | 2022-12-18 | 2023-02-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS005 | SEQ - Sewer When & Where Contract in SE Queens | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-02-16 | 2023-03-17 | 2023-02-16 | 2027-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS006 | SEQ - Neighborhood Storm Sewer Extensions | 1 | DEVELOP SCOPE | 2020-03-01 | 2020-05-29 | 2020-03-01 | 2020-05-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS006 | SEQ - Neighborhood Storm Sewer Extensions | 2 | PRELIMINARY DESIGN | 2020-05-30 | 2020-09-26 | 2020-05-30 | 2020-09-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS006 | SEQ - Neighborhood Storm Sewer Extensions | 3 | FINAL DESIGN | 2020-09-27 | 2021-03-25 | 2020-09-27 | 2021-03-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS006 | SEQ - Neighborhood Storm Sewer Extensions | 4 | BID AWARD AND REGISTER CONTRCT | 2021-03-26 | 2021-06-23 | 2021-03-26 | 2021-06-23
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS006 | SEQ - Neighborhood Storm Sewer Extensions | 5 | CONSTRUCTION TO 25% | 2021-06-24 | 2021-10-21 | 2021-06-24 | 2021-10-21
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS006 | SEQ - Neighborhood Storm Sewer Extensions | 6 | CONSTRUCTION TO 50% | 2021-10-22 | 2022-02-18 | 2021-10-22 | 2022-02-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS006 | SEQ - Neighborhood Storm Sewer Extensions | 7 | CONSTRUCTION TO 75% | 2022-02-19 | 2022-06-18 | 2022-02-19 | 2022-06-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS006 | SEQ - Neighborhood Storm Sewer Extensions | 8 | ORIGINAL EQUIP & FURNISHING | 2022-06-19 | 2022-09-16 | 2022-06-19 | 2022-09-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS006 | SEQ - Neighborhood Storm Sewer Extensions | 9 | SUBSTANTIAL COMPLETION | 2022-09-17 | 2022-11-15 | 2022-09-17 | 2022-11-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS006 | SEQ - Neighborhood Storm Sewer Extensions | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-11-16 | 2022-12-15 | 2022-11-16 | 2026-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQPGRD1 | Southeast Queens Priority Grids -- Group 1 (DOTSEQ01) | 1 | DEVELOP SCOPE | 2016-06-30 | 2016-09-27 | 2016-06-30 | 2016-09-27
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQPGRD1 | Southeast Queens Priority Grids -- Group 1 (DOTSEQ01) | 2 | PRELIMINARY DESIGN | 2016-09-28 | 2017-01-25 | 2016-09-28 | 2017-01-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQPGRD1 | Southeast Queens Priority Grids -- Group 1 (DOTSEQ01) | 3 | FINAL DESIGN | 2017-01-26 | 2017-07-24 | 2017-01-26 | 2017-07-24
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQPGRD1 | Southeast Queens Priority Grids -- Group 1 (DOTSEQ01) | 4 | BID AWARD AND REGISTER CONTRCT | 2017-07-25 | 2017-10-22 | 2017-07-25 | 2017-10-22
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQPGRD1 | Southeast Queens Priority Grids -- Group 1 (DOTSEQ01) | 5 | CONSTRUCTION TO 25% | 2017-10-23 | 2018-02-19 | 2017-10-23 | 2018-02-19
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQPGRD1 | Southeast Queens Priority Grids -- Group 1 (DOTSEQ01) | 6 | CONSTRUCTION TO 50% | 2018-02-20 | 2018-06-19 | 2018-02-20 | 2018-06-19
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQPGRD1 | Southeast Queens Priority Grids -- Group 1 (DOTSEQ01) | 7 | CONSTRUCTION TO 75% | 2018-06-20 | 2018-10-17 | 2018-06-20 | 2018-10-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQPGRD1 | Southeast Queens Priority Grids -- Group 1 (DOTSEQ01) | 8 | ORIGINAL EQUIP & FURNISHING | 2018-10-18 | 2019-01-15 | 2018-10-18 | 2019-01-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQPGRD1 | Southeast Queens Priority Grids -- Group 1 (DOTSEQ01) | 9 | SUBSTANTIAL COMPLETION | 2019-01-16 | 2019-03-16 | 2019-01-16 | 2019-03-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQPGRD1 | Southeast Queens Priority Grids -- Group 1 (DOTSEQ01) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-03-17 | 2019-04-15 | 2019-03-17 | 2026-08-12
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQPGRD2 | Southeast Queens Priority Grids -- Group 2 (DOTSEQ02) | 1 | DEVELOP SCOPE | 2017-06-30 | 2017-09-27 | 2017-06-30 | 2017-09-27
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQPGRD2 | Southeast Queens Priority Grids -- Group 2 (DOTSEQ02) | 2 | PRELIMINARY DESIGN | 2017-09-28 | 2018-01-25 | 2017-09-28 | 2018-01-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQPGRD2 | Southeast Queens Priority Grids -- Group 2 (DOTSEQ02) | 3 | FINAL DESIGN | 2018-01-26 | 2018-07-24 | 2018-01-26 | 2018-07-24
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQPGRD2 | Southeast Queens Priority Grids -- Group 2 (DOTSEQ02) | 4 | BID AWARD AND REGISTER CONTRCT | 2018-07-25 | 2018-10-22 | 2018-07-25 | 2018-10-22
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQPGRD2 | Southeast Queens Priority Grids -- Group 2 (DOTSEQ02) | 5 | CONSTRUCTION TO 25% | 2018-10-23 | 2019-02-19 | 2018-10-23 | 2019-02-19
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQPGRD2 | Southeast Queens Priority Grids -- Group 2 (DOTSEQ02) | 6 | CONSTRUCTION TO 50% | 2019-02-20 | 2019-06-19 | 2019-02-20 | 2019-06-19
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQPGRD2 | Southeast Queens Priority Grids -- Group 2 (DOTSEQ02) | 7 | CONSTRUCTION TO 75% | 2019-06-20 | 2019-10-17 | 2019-06-20 | 2019-10-17
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQPGRD2 | Southeast Queens Priority Grids -- Group 2 (DOTSEQ02) | 8 | ORIGINAL EQUIP & FURNISHING | 2019-10-18 | 2020-01-15 | 2019-10-18 | 2020-01-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQPGRD2 | Southeast Queens Priority Grids -- Group 2 (DOTSEQ02) | 9 | SUBSTANTIAL COMPLETION | 2020-01-16 | 2020-03-15 | 2020-01-16 | 2020-03-15
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQPGRD2 | Southeast Queens Priority Grids -- Group 2 (DOTSEQ02) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-03-16 | 2020-04-14 | 2020-03-16 | 2027-09-13
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | TF18-2012 | QUEENSBORO HALL MUNICIPAL PARKING GARAGE, QUEENS | 1 | BID AWARD AND REGISTER CONTRCT | 2008-06-30 | 2008-06-30 | 2013-11-25 | 2013-11-25
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | TF18-2012 | QUEENSBORO HALL MUNICIPAL PARKING GARAGE, QUEENS | 2 | CONSTRUCTION START | 2008-07-01 | 2008-08-14 | 2009-10-15 | 2012-02-08
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | TF18-2012 | QUEENSBORO HALL MUNICIPAL PARKING GARAGE, QUEENS | 3 | CONSTRUCTION COMPLETION | 2008-08-15 | 2010-03-07 | 2012-02-09 | 2021-06-30
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | TLCWOOD | TLC - NEW OFFICE FACILITY - 24-55 BQE WEST | 1 | DEVELOP SCOPE | 2015-05-01 | 2015-07-29 | 2015-05-01 | 2015-07-29
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | TLCWOOD | TLC - NEW OFFICE FACILITY - 24-55 BQE WEST | 2 | PRELIMINARY DESIGN | 2015-07-30 | 2015-11-26 | 2015-07-30 | 2015-11-26
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | TLCWOOD | TLC - NEW OFFICE FACILITY - 24-55 BQE WEST | 3 | FINAL DESIGN | 2015-11-27 | 2016-05-24 | 2015-11-27 | 2019-05-24
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | TLCWOOD | TLC - NEW OFFICE FACILITY - 24-55 BQE WEST | 4 | BID AWARD AND REGISTER CONTRCT | 2016-05-25 | 2016-08-22 | 2019-05-25 | 2019-08-22
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | TLCWOOD | TLC - NEW OFFICE FACILITY - 24-55 BQE WEST | 5 | CONSTRUCTION TO 25% | 2016-08-23 | 2016-12-20 | 2019-08-23 | 2019-12-20
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | TLCWOOD | TLC - NEW OFFICE FACILITY - 24-55 BQE WEST | 6 | CONSTRUCTION TO 50% | 2016-12-21 | 2017-04-19 | 2019-12-21 | 2020-04-18
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | TLCWOOD | TLC - NEW OFFICE FACILITY - 24-55 BQE WEST | 7 | CONSTRUCTION TO 75% | 2017-04-20 | 2017-08-17 | 2020-04-19 | 2020-08-16
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | TLCWOOD | TLC - NEW OFFICE FACILITY - 24-55 BQE WEST | 8 | ORIGINAL EQUIP & FURNISHING | 2017-08-18 | 2017-11-15 | 2020-08-17 | 2020-11-14
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | TLCWOOD | TLC - NEW OFFICE FACILITY - 24-55 BQE WEST | 9 | SUBSTANTIAL COMPLETION | 2017-11-16 | 2018-01-14 | 2020-11-15 | 2021-01-13
20201123 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | TLCWOOD | TLC - NEW OFFICE FACILITY - 24-55 BQE WEST | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-01-15 | 2018-02-13 | 2021-01-14 | 2023-06-30
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEHHC902 | HHC - -Energy Upgrades at Queens Hospital N Building | 1 | DEVELOP SCOPE | 2021-03-01 | 2021-03-30 | 2021-03-01 | 2021-03-30
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEHHC902 | HHC - -Energy Upgrades at Queens Hospital N Building | 2 | BID AWARD AND REGISTER CONTRCT | 2021-03-31 | 2021-05-29 | 2021-03-31 | 2021-05-29
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEHHC902 | HHC - -Energy Upgrades at Queens Hospital N Building | 3 | CONSTRUCTION TO 50% | 2021-05-30 | 2021-11-25 | 2021-05-30 | 2021-11-25
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEHHC902 | HHC - -Energy Upgrades at Queens Hospital N Building | 4 | CONSTRUCTION TO 75% | 2021-11-26 | 2022-02-23 | 2021-11-26 | 2022-02-23
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEHHC902 | HHC - -Energy Upgrades at Queens Hospital N Building | 5 | SUBSTANTIAL COMPLETION | 2022-02-24 | 2022-04-24 | 2022-02-24 | 2022-04-24
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEHHC902 | HHC - -Energy Upgrades at Queens Hospital N Building | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-04-25 | 2022-05-24 | 2022-04-25 | 2022-05-24
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO296EV | 125-01 QUEENS BLVD.- ELEVATORS | 1 | DEVELOP SCOPE | 2022-06-01 | 2022-08-29 | 2022-06-01 | 2022-08-29
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO296EV | 125-01 QUEENS BLVD.- ELEVATORS | 2 | PRELIMINARY DESIGN | 2022-08-30 | 2022-12-27 | 2022-08-30 | 2022-12-27
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO296EV | 125-01 QUEENS BLVD.- ELEVATORS | 3 | FINAL DESIGN | 2022-12-28 | 2023-06-25 | 2022-12-28 | 2023-06-25
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO296EV | 125-01 QUEENS BLVD.- ELEVATORS | 4 | BID AWARD AND REGISTER CONTRCT | 2023-06-26 | 2023-09-23 | 2023-06-26 | 2023-09-23
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO296EV | 125-01 QUEENS BLVD.- ELEVATORS | 5 | CONSTRUCTION TO 25% | 2023-09-24 | 2024-01-21 | 2023-09-24 | 2024-01-21
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO296EV | 125-01 QUEENS BLVD.- ELEVATORS | 6 | CONSTRUCTION TO 50% | 2024-01-22 | 2024-05-20 | 2024-01-22 | 2024-05-20
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO296EV | 125-01 QUEENS BLVD.- ELEVATORS | 7 | CONSTRUCTION TO 75% | 2024-05-21 | 2024-09-17 | 2024-05-21 | 2024-09-17
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO296EV | 125-01 QUEENS BLVD.- ELEVATORS | 8 | ORIGINAL EQUIP & FURNISHING | 2024-09-18 | 2024-12-16 | 2024-09-18 | 2024-12-16
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO296EV | 125-01 QUEENS BLVD.- ELEVATORS | 9 | SUBSTANTIAL COMPLETION | 2024-12-17 | 2025-02-14 | 2024-12-17 | 2025-02-14
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO296EV | 125-01 QUEENS BLVD.- ELEVATORS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-02-15 | 2026-06-30 | 2025-02-15 | 2026-06-30
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO296FA | 125-01 QUEENS BLVD.- FIRE ALARMS | 1 | DEVELOP SCOPE | 2007-09-01 | 2007-11-29 | 2022-06-01 | 2022-08-29
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO296FA | 125-01 QUEENS BLVD.- FIRE ALARMS | 2 | PRELIMINARY DESIGN | 2007-11-30 | 2008-03-28 | 2022-08-30 | 2022-12-27
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO296FA | 125-01 QUEENS BLVD.- FIRE ALARMS | 3 | FINAL DESIGN | 2008-03-29 | 2008-09-24 | 2022-12-28 | 2023-06-25
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO296FA | 125-01 QUEENS BLVD.- FIRE ALARMS | 4 | BID AWARD AND REGISTER CONTRCT | 2008-09-25 | 2008-12-23 | 2023-06-26 | 2023-09-23
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO296FA | 125-01 QUEENS BLVD.- FIRE ALARMS | 5 | CONSTRUCTION TO 25% | 2008-12-24 | 2009-04-22 | 2023-09-24 | 2024-01-21
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO296FA | 125-01 QUEENS BLVD.- FIRE ALARMS | 6 | CONSTRUCTION TO 50% | 2009-04-23 | 2009-08-20 | 2024-01-22 | 2024-05-20
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO296FA | 125-01 QUEENS BLVD.- FIRE ALARMS | 7 | CONSTRUCTION TO 75% | 2009-08-21 | 2009-12-18 | 2024-05-21 | 2024-09-17
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO296FA | 125-01 QUEENS BLVD.- FIRE ALARMS | 8 | ORIGINAL EQUIP & FURNISHING | 2009-12-19 | 2010-03-18 | 2024-09-18 | 2024-12-16
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO296FA | 125-01 QUEENS BLVD.- FIRE ALARMS | 9 | SUBSTANTIAL COMPLETION | 2010-03-19 | 2010-05-17 | 2024-12-17 | 2025-02-14
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO296FA | 125-01 QUEENS BLVD.- FIRE ALARMS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2010-05-18 | 2010-06-16 | 2025-02-15 | 2025-03-16
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO298CHIL | 151-20 JAMAICA AVE.- CHILLER REPLACEMENT | 1 | DEVELOP SCOPE | 2022-06-01 | 2022-08-29 | 2022-06-01 | 2022-08-29
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO298CHIL | 151-20 JAMAICA AVE.- CHILLER REPLACEMENT | 2 | PRELIMINARY DESIGN | 2022-08-30 | 2022-12-27 | 2022-08-30 | 2022-12-27
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO298CHIL | 151-20 JAMAICA AVE.- CHILLER REPLACEMENT | 3 | FINAL DESIGN | 2022-12-28 | 2023-06-25 | 2022-12-28 | 2023-06-25
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO298CHIL | 151-20 JAMAICA AVE.- CHILLER REPLACEMENT | 4 | BID AWARD AND REGISTER CONTRCT | 2023-06-26 | 2023-09-23 | 2023-06-26 | 2023-09-23
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO298CHIL | 151-20 JAMAICA AVE.- CHILLER REPLACEMENT | 5 | CONSTRUCTION TO 25% | 2023-09-24 | 2024-01-21 | 2023-09-24 | 2024-01-21
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO298CHIL | 151-20 JAMAICA AVE.- CHILLER REPLACEMENT | 6 | CONSTRUCTION TO 50% | 2024-01-22 | 2024-05-20 | 2024-01-22 | 2024-05-20
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO298CHIL | 151-20 JAMAICA AVE.- CHILLER REPLACEMENT | 7 | CONSTRUCTION TO 75% | 2024-05-21 | 2024-09-17 | 2024-05-21 | 2024-09-17
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO298CHIL | 151-20 JAMAICA AVE.- CHILLER REPLACEMENT | 8 | ORIGINAL EQUIP & FURNISHING | 2024-09-18 | 2024-12-16 | 2024-09-18 | 2024-12-16
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO298CHIL | 151-20 JAMAICA AVE.- CHILLER REPLACEMENT | 9 | SUBSTANTIAL COMPLETION | 2024-12-17 | 2025-02-14 | 2024-12-17 | 2025-02-14
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO298CHIL | 151-20 JAMAICA AVE.- CHILLER REPLACEMENT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-02-15 | 2025-03-16 | 2025-02-15 | 2025-03-16
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO299CHIL | 89-17 SUTPHIN BLVD.- CHILLER REPLACEMENT | 1 | DEVELOP SCOPE | 2023-06-01 | 2023-08-29 | 2023-06-01 | 2023-08-29
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO299CHIL | 89-17 SUTPHIN BLVD.- CHILLER REPLACEMENT | 2 | PRELIMINARY DESIGN | 2023-08-30 | 2023-12-27 | 2023-08-30 | 2023-12-27
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO299CHIL | 89-17 SUTPHIN BLVD.- CHILLER REPLACEMENT | 3 | FINAL DESIGN | 2023-12-28 | 2024-06-24 | 2023-12-28 | 2024-06-24
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO299CHIL | 89-17 SUTPHIN BLVD.- CHILLER REPLACEMENT | 4 | BID AWARD AND REGISTER CONTRCT | 2024-06-25 | 2024-09-22 | 2024-06-25 | 2024-09-22
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO299CHIL | 89-17 SUTPHIN BLVD.- CHILLER REPLACEMENT | 5 | CONSTRUCTION TO 25% | 2024-09-23 | 2025-01-20 | 2024-09-23 | 2025-01-20
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO299CHIL | 89-17 SUTPHIN BLVD.- CHILLER REPLACEMENT | 6 | CONSTRUCTION TO 50% | 2025-01-21 | 2025-05-20 | 2025-01-21 | 2025-05-20
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO299CHIL | 89-17 SUTPHIN BLVD.- CHILLER REPLACEMENT | 7 | CONSTRUCTION TO 75% | 2025-05-21 | 2025-09-17 | 2025-05-21 | 2025-09-17
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO299CHIL | 89-17 SUTPHIN BLVD.- CHILLER REPLACEMENT | 8 | ORIGINAL EQUIP & FURNISHING | 2025-09-18 | 2025-12-16 | 2025-09-18 | 2025-12-16
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO299CHIL | 89-17 SUTPHIN BLVD.- CHILLER REPLACEMENT | 9 | SUBSTANTIAL COMPLETION | 2025-12-17 | 2026-02-14 | 2025-12-17 | 2026-02-14
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO299CHIL | 89-17 SUTPHIN BLVD.- CHILLER REPLACEMENT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2026-02-15 | 2026-03-16 | 2026-02-15 | 2026-03-16
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO300415A | DASNY - 88-11 SUTPHIN BLVD.- RENOVATION | 1 | DEVELOP SCOPE | 2002-01-01 | 2002-03-31 | 2002-01-01 | 2002-03-31
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO300415A | DASNY - 88-11 SUTPHIN BLVD.- RENOVATION | 2 | PRELIMINARY DESIGN | 2002-04-01 | 2002-07-29 | 2002-04-01 | 2002-07-29
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO300415A | DASNY - 88-11 SUTPHIN BLVD.- RENOVATION | 3 | FINAL DESIGN | 2002-07-30 | 2003-01-25 | 2002-07-30 | 2003-01-25
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO300415A | DASNY - 88-11 SUTPHIN BLVD.- RENOVATION | 4 | BID AWARD AND REGISTER CONTRCT | 2003-01-26 | 2003-04-25 | 2003-01-26 | 2003-04-25
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO300415A | DASNY - 88-11 SUTPHIN BLVD.- RENOVATION | 5 | CONSTRUCTION TO 25% | 2003-04-26 | 2005-12-10 | 2003-04-26 | 2005-12-10
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO300415A | DASNY - 88-11 SUTPHIN BLVD.- RENOVATION | 6 | CONSTRUCTION TO 50% | 2005-12-11 | 2008-07-27 | 2005-12-11 | 2008-07-27
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO300415A | DASNY - 88-11 SUTPHIN BLVD.- RENOVATION | 7 | CONSTRUCTION TO 75% | 2008-07-28 | 2011-03-14 | 2008-07-28 | 2011-03-14
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO300415A | DASNY - 88-11 SUTPHIN BLVD.- RENOVATION | 8 | ORIGINAL EQUIP & FURNISHING | 2011-03-15 | 2011-09-10 | 2011-03-15 | 2011-09-10
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO300415A | DASNY - 88-11 SUTPHIN BLVD.- RENOVATION | 9 | SUBSTANTIAL COMPLETION | 2011-09-11 | 2011-12-09 | 2011-09-11 | 2011-12-09
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO300415A | DASNY - 88-11 SUTPHIN BLVD.- RENOVATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2011-12-10 | 2011-12-24 | 2011-12-10 | 2022-06-30
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO300FIRE | 88-11 SUTPHIN BLVD. FIRE ALARM SYSTEM UPGRADE | 1 | DEVELOP SCOPE | 2016-02-01 | 2016-04-30 | 2022-06-01 | 2028-06-30
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO300FIRE | 88-11 SUTPHIN BLVD. FIRE ALARM SYSTEM UPGRADE | 2 | PRELIMINARY DESIGN | 2016-05-01 | 2016-08-28 | 2028-07-01 | 2028-10-28
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO300FIRE | 88-11 SUTPHIN BLVD. FIRE ALARM SYSTEM UPGRADE | 3 | FINAL DESIGN | 2016-08-29 | 2017-02-24 | 2028-10-29 | 2029-04-26
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO300FIRE | 88-11 SUTPHIN BLVD. FIRE ALARM SYSTEM UPGRADE | 4 | BID AWARD AND REGISTER CONTRCT | 2017-02-25 | 2017-05-25 | 2029-04-27 | 2029-07-25
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO300FIRE | 88-11 SUTPHIN BLVD. FIRE ALARM SYSTEM UPGRADE | 5 | CONSTRUCTION TO 25% | 2017-05-26 | 2017-09-22 | 2029-07-26 | 2029-11-22
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO300FIRE | 88-11 SUTPHIN BLVD. FIRE ALARM SYSTEM UPGRADE | 6 | CONSTRUCTION TO 50% | 2017-09-23 | 2018-01-20 | 2029-11-23 | 2030-03-22
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO300FIRE | 88-11 SUTPHIN BLVD. FIRE ALARM SYSTEM UPGRADE | 7 | CONSTRUCTION TO 75% | 2018-01-21 | 2018-05-20 | 2030-03-23 | 2030-07-20
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO300FIRE | 88-11 SUTPHIN BLVD. FIRE ALARM SYSTEM UPGRADE | 8 | ORIGINAL EQUIP & FURNISHING | 2018-05-21 | 2018-08-18 | 2030-07-21 | 2030-10-18
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO300FIRE | 88-11 SUTPHIN BLVD. FIRE ALARM SYSTEM UPGRADE | 9 | SUBSTANTIAL COMPLETION | 2018-08-19 | 2018-10-17 | 2030-10-19 | 2030-12-17
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO300FIRE | 88-11 SUTPHIN BLVD. FIRE ALARM SYSTEM UPGRADE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-10-18 | 2018-11-16 | 2030-12-18 | 2031-01-16
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO300RF | 88-11 SUTPHIN BOULEVARD - ROOF | 1 | DEVELOP SCOPE | 2022-01-15 | 2022-04-14 | 2022-01-15 | 2022-04-14
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO300RF | 88-11 SUTPHIN BOULEVARD - ROOF | 2 | PRELIMINARY DESIGN | 2022-04-15 | 2022-08-12 | 2022-04-15 | 2022-08-12
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO300RF | 88-11 SUTPHIN BOULEVARD - ROOF | 3 | FINAL DESIGN | 2022-08-13 | 2023-02-08 | 2022-08-13 | 2023-02-08
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO300RF | 88-11 SUTPHIN BOULEVARD - ROOF | 4 | BID AWARD AND REGISTER CONTRCT | 2023-02-09 | 2023-05-09 | 2023-02-09 | 2023-05-09
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO300RF | 88-11 SUTPHIN BOULEVARD - ROOF | 5 | CONSTRUCTION TO 25% | 2023-05-10 | 2023-09-06 | 2023-05-10 | 2023-09-06
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO300RF | 88-11 SUTPHIN BOULEVARD - ROOF | 6 | CONSTRUCTION TO 50% | 2023-09-07 | 2024-01-04 | 2023-09-07 | 2024-01-04
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO300RF | 88-11 SUTPHIN BOULEVARD - ROOF | 7 | CONSTRUCTION TO 75% | 2024-01-05 | 2024-05-03 | 2024-01-05 | 2024-05-03
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO300RF | 88-11 SUTPHIN BOULEVARD - ROOF | 8 | ORIGINAL EQUIP & FURNISHING | 2024-05-04 | 2024-08-01 | 2024-05-04 | 2024-08-01
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO300RF | 88-11 SUTPHIN BOULEVARD - ROOF | 9 | SUBSTANTIAL COMPLETION | 2024-08-02 | 2024-09-30 | 2024-08-02 | 2024-09-30
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO300RF | 88-11 SUTPHIN BOULEVARD - ROOF | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-10-01 | 2024-10-30 | 2024-10-01 | 2024-10-30
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | E19-0005 | DOHMH - Jamaica Health Center | 1 | DEVELOP SCOPE | 2019-06-01 | 2019-06-30 | 2019-06-01 | 2019-06-30
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | E19-0005 | DOHMH - Jamaica Health Center | 2 | BID AWARD AND REGISTER CONTRCT | 2019-07-01 | 2019-08-29 | 2019-07-01 | 2019-08-29
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | E19-0005 | DOHMH - Jamaica Health Center | 3 | CONSTRUCTION TO 50% | 2019-08-30 | 2020-02-25 | 2019-08-30 | 2020-02-25
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | E19-0005 | DOHMH - Jamaica Health Center | 4 | CONSTRUCTION TO 75% | 2020-02-26 | 2020-05-25 | 2020-02-26 | 2020-05-25
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | E19-0005 | DOHMH - Jamaica Health Center | 5 | SUBSTANTIAL COMPLETION | 2020-05-26 | 2020-07-24 | 2020-05-26 | 2020-07-24
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | E19-0005 | DOHMH - Jamaica Health Center | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-07-25 | 2020-08-23 | 2020-07-25 | 2020-08-23
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | E19-0006 | NYPD - 102th Precinct | 2 | BID AWARD AND REGISTER CONTRCT | 2019-07-01 | 2019-08-29 | 2019-07-01 | 2019-08-29
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | E19-0006 | NYPD - 102th Precinct | 3 | CONSTRUCTION TO 50% | 2019-08-30 | 2020-02-25 | 2019-08-30 | 2020-02-25
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | E19-0006 | NYPD - 102th Precinct | 4 | CONSTRUCTION TO 75% | 2020-02-26 | 2020-05-25 | 2020-02-26 | 2020-05-25
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | E19-0006 | NYPD - 102th Precinct | 5 | SUBSTANTIAL COMPLETION | 2020-05-26 | 2020-07-24 | 2020-05-26 | 2020-07-24
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | E19-0006 | NYPD - 102th Precinct | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-07-25 | 2020-08-23 | 2020-07-25 | 2020-08-23
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0069 | NYPD - 101st Precinct | 1 | DEVELOP SCOPE | 2020-02-02 | 2020-03-02 | 2022-06-01 | 2022-06-30
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0069 | NYPD - 101st Precinct | 2 | BID AWARD AND REGISTER CONTRCT | 2020-03-03 | 2020-05-01 | 2022-07-01 | 2022-08-29
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0069 | NYPD - 101st Precinct | 3 | CONSTRUCTION TO 50% | 2020-05-02 | 2020-10-28 | 2022-08-30 | 2023-02-25
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0069 | NYPD - 101st Precinct | 4 | CONSTRUCTION TO 75% | 2020-10-29 | 2021-01-26 | 2023-02-26 | 2023-05-26
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0069 | NYPD - 101st Precinct | 5 | SUBSTANTIAL COMPLETION | 2021-01-27 | 2021-03-27 | 2023-05-27 | 2023-07-25
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0069 | NYPD - 101st Precinct | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-28 | 2021-04-26 | 2023-07-26 | 2023-08-24
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0070 | NYPD - 106th Precinct | 1 | DEVELOP SCOPE | 2020-02-01 | 2020-03-01 | 2022-06-01 | 2022-06-30
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0070 | NYPD - 106th Precinct | 2 | BID AWARD AND REGISTER CONTRCT | 2020-03-02 | 2020-04-30 | 2022-07-01 | 2022-08-29
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0070 | NYPD - 106th Precinct | 3 | CONSTRUCTION TO 50% | 2020-05-01 | 2020-10-27 | 2022-08-30 | 2023-02-25
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0070 | NYPD - 106th Precinct | 4 | CONSTRUCTION TO 75% | 2020-10-28 | 2021-01-25 | 2023-02-26 | 2023-05-26
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0070 | NYPD - 106th Precinct | 5 | SUBSTANTIAL COMPLETION | 2021-01-26 | 2021-03-26 | 2023-05-27 | 2023-07-25
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0070 | NYPD - 106th Precinct | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-27 | 2021-04-25 | 2023-07-26 | 2023-08-24
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0071 | NYPD - 108TH PRECINCT | 1 | DEVELOP SCOPE | 2020-02-15 | 2020-03-15 | 2022-06-01 | 2022-06-30
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0071 | NYPD - 108TH PRECINCT | 2 | BID AWARD AND REGISTER CONTRCT | 2020-03-16 | 2020-05-14 | 2022-07-01 | 2022-08-29
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0071 | NYPD - 108TH PRECINCT | 3 | CONSTRUCTION TO 50% | 2020-05-15 | 2020-11-10 | 2022-08-30 | 2023-02-25
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0071 | NYPD - 108TH PRECINCT | 4 | CONSTRUCTION TO 75% | 2020-11-11 | 2021-02-08 | 2023-02-26 | 2023-05-26
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0071 | NYPD - 108TH PRECINCT | 5 | SUBSTANTIAL COMPLETION | 2021-02-09 | 2021-04-09 | 2023-05-27 | 2023-07-25
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0071 | NYPD - 108TH PRECINCT | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-04-10 | 2021-05-09 | 2023-07-26 | 2023-08-24
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0087 | DPR - LOST BATTALION HALL RECREATION CENTER | 1 | DEVELOP SCOPE | 2020-01-15 | 2020-02-13 | 2022-06-01 | 2022-06-30
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0087 | DPR - LOST BATTALION HALL RECREATION CENTER | 2 | BID AWARD AND REGISTER CONTRCT | 2020-02-14 | 2020-04-13 | 2022-07-01 | 2022-08-29
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0087 | DPR - LOST BATTALION HALL RECREATION CENTER | 3 | CONSTRUCTION TO 50% | 2020-04-14 | 2020-10-10 | 2022-08-30 | 2023-02-25
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0087 | DPR - LOST BATTALION HALL RECREATION CENTER | 4 | CONSTRUCTION TO 75% | 2020-10-11 | 2021-01-08 | 2023-02-26 | 2023-05-26
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0087 | DPR - LOST BATTALION HALL RECREATION CENTER | 5 | SUBSTANTIAL COMPLETION | 2021-01-09 | 2021-03-09 | 2023-05-27 | 2023-07-25
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0087 | DPR - LOST BATTALION HALL RECREATION CENTER | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-10 | 2021-04-08 | 2023-07-26 | 2023-08-24
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0090 | QPL - McGOLDRICK COMMUNITY LIBRARY | 1 | DEVELOP SCOPE | 2020-02-15 | 2020-03-15 | 2022-06-01 | 2022-06-30
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0090 | QPL - McGOLDRICK COMMUNITY LIBRARY | 2 | BID AWARD AND REGISTER CONTRCT | 2020-03-16 | 2020-05-14 | 2022-07-01 | 2022-08-29
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0090 | QPL - McGOLDRICK COMMUNITY LIBRARY | 3 | CONSTRUCTION TO 50% | 2020-05-15 | 2020-11-10 | 2022-08-30 | 2023-02-25
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0090 | QPL - McGOLDRICK COMMUNITY LIBRARY | 4 | CONSTRUCTION TO 75% | 2020-11-11 | 2021-02-08 | 2023-02-26 | 2023-05-26
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0090 | QPL - McGOLDRICK COMMUNITY LIBRARY | 5 | SUBSTANTIAL COMPLETION | 2021-02-09 | 2021-04-09 | 2023-05-27 | 2023-07-25
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0090 | QPL - McGOLDRICK COMMUNITY LIBRARY | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-04-10 | 2021-05-09 | 2023-07-26 | 2023-08-24
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0091 | QPL - OZONE PARK COMMUNITY LIBRARY | 1 | DEVELOP SCOPE | 2020-02-15 | 2020-03-15 | 2022-06-01 | 2022-06-30
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0091 | QPL - OZONE PARK COMMUNITY LIBRARY | 2 | BID AWARD AND REGISTER CONTRCT | 2020-03-16 | 2020-05-14 | 2022-07-01 | 2022-08-29
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0091 | QPL - OZONE PARK COMMUNITY LIBRARY | 3 | CONSTRUCTION TO 50% | 2020-05-15 | 2020-11-10 | 2022-08-30 | 2023-02-25
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0091 | QPL - OZONE PARK COMMUNITY LIBRARY | 4 | CONSTRUCTION TO 75% | 2020-11-11 | 2021-02-08 | 2023-02-26 | 2023-05-26
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0091 | QPL - OZONE PARK COMMUNITY LIBRARY | 5 | SUBSTANTIAL COMPLETION | 2021-02-09 | 2021-04-09 | 2023-05-27 | 2023-07-25
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0091 | QPL - OZONE PARK COMMUNITY LIBRARY | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-04-10 | 2021-05-09 | 2023-07-26 | 2023-08-24
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | HL82WAREH | DOHMH - Relocation Warehouse from 540 Kingsland Ave Brooklyn | 1 | DESIGN | 2018-05-01 | 2018-10-27 | 2018-05-01 | 2018-10-27
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | HL82WAREH | DOHMH - Relocation Warehouse from 540 Kingsland Ave Brooklyn | 2 | CONSTRUCTION | 2018-10-28 | 2019-04-25 | 2019-06-01 | 2022-06-30
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | HR25QCRT | 151-20 Jamaica Ave 4th floor | 1 | DESIGN | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | HR25QCRT | 151-20 Jamaica Ave 4th floor | 2 | CONSTRUCTION | 2019-12-28 | 2020-06-24 | 2021-06-01 | 2022-11-27
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79QTP | NYPD - COLLEGE POINT TOW POUND | 1 | DEVELOP SCOPE | 2017-03-01 | 2017-05-29 | 2017-03-01 | 2017-05-29
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79QTP | NYPD - COLLEGE POINT TOW POUND | 2 | PRELIMINARY DESIGN | 2017-05-30 | 2017-09-26 | 2017-05-30 | 2017-09-26
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79QTP | NYPD - COLLEGE POINT TOW POUND | 3 | FINAL DESIGN | 2017-09-27 | 2018-03-25 | 2017-09-27 | 2018-03-25
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79QTP | NYPD - COLLEGE POINT TOW POUND | 4 | BID AWARD AND REGISTER CONTRCT | 2018-03-26 | 2018-06-23 | 2018-03-26 | 2018-06-23
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79QTP | NYPD - COLLEGE POINT TOW POUND | 5 | CONSTRUCTION TO 25% | 2018-06-24 | 2018-10-21 | 2021-06-01 | 2021-09-28
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79QTP | NYPD - COLLEGE POINT TOW POUND | 6 | CONSTRUCTION TO 50% | 2018-10-22 | 2019-02-18 | 2021-09-29 | 2022-01-26
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79QTP | NYPD - COLLEGE POINT TOW POUND | 7 | CONSTRUCTION TO 75% | 2019-02-19 | 2019-06-18 | 2022-01-27 | 2022-05-26
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79QTP | NYPD - COLLEGE POINT TOW POUND | 8 | ORIGINAL EQUIP & FURNISHING | 2019-06-19 | 2019-09-16 | 2022-05-27 | 2022-08-24
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79QTP | NYPD - COLLEGE POINT TOW POUND | 9 | SUBSTANTIAL COMPLETION | 2019-09-17 | 2019-11-15 | 2022-08-25 | 2022-10-23
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79QTP | NYPD - COLLEGE POINT TOW POUND | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-11-16 | 2019-12-15 | 2022-10-24 | 2022-11-22
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DAQ3 | DA QUEENS - CYBER CRIME UNIT | 1 | DEVELOP SCOPE | 2019-06-01 | 2019-08-29 | 2019-06-01 | 2019-08-29
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DAQ3 | DA QUEENS - CYBER CRIME UNIT | 2 | PRELIMINARY DESIGN | 2019-08-30 | 2019-12-27 | 2019-08-30 | 2019-12-27
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DAQ3 | DA QUEENS - CYBER CRIME UNIT | 3 | FINAL DESIGN | 2019-12-28 | 2020-06-24 | 2019-12-28 | 2020-06-24
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DAQ3 | DA QUEENS - CYBER CRIME UNIT | 4 | BID AWARD AND REGISTER CONTRCT | 2020-06-25 | 2020-09-22 | 2020-06-25 | 2020-09-22
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DAQ3 | DA QUEENS - CYBER CRIME UNIT | 5 | CONSTRUCTION TO 25% | 2020-09-23 | 2021-01-20 | 2020-09-23 | 2021-01-20
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DAQ3 | DA QUEENS - CYBER CRIME UNIT | 6 | CONSTRUCTION TO 50% | 2021-01-21 | 2021-05-20 | 2021-01-21 | 2021-05-20
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DAQ3 | DA QUEENS - CYBER CRIME UNIT | 7 | CONSTRUCTION TO 75% | 2021-05-21 | 2021-09-17 | 2021-05-21 | 2021-09-17
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DAQ3 | DA QUEENS - CYBER CRIME UNIT | 8 | ORIGINAL EQUIP & FURNISHING | 2021-09-18 | 2021-12-16 | 2021-09-18 | 2021-12-16
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DAQ3 | DA QUEENS - CYBER CRIME UNIT | 9 | SUBSTANTIAL COMPLETION | 2021-12-17 | 2022-02-14 | 2021-12-17 | 2022-02-14
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DAQ3 | DA QUEENS - CYBER CRIME UNIT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-02-15 | 2022-03-16 | 2022-02-15 | 2022-03-16
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DAQ4 | DA QUEENS - SUPREME COURT TRIAL BUREAU | 1 | DEVELOP SCOPE | 2019-06-01 | 2019-08-29 | 2019-06-01 | 2019-08-29
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DAQ4 | DA QUEENS - SUPREME COURT TRIAL BUREAU | 2 | PRELIMINARY DESIGN | 2019-08-30 | 2019-12-27 | 2019-08-30 | 2019-12-27
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DAQ4 | DA QUEENS - SUPREME COURT TRIAL BUREAU | 3 | FINAL DESIGN | 2019-12-28 | 2020-06-24 | 2019-12-28 | 2020-06-24
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DAQ4 | DA QUEENS - SUPREME COURT TRIAL BUREAU | 4 | BID AWARD AND REGISTER CONTRCT | 2020-06-25 | 2020-09-22 | 2026-06-01 | 2026-08-29
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DAQ4 | DA QUEENS - SUPREME COURT TRIAL BUREAU | 5 | CONSTRUCTION TO 25% | 2020-09-23 | 2021-01-20 | 2026-08-30 | 2026-12-27
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DAQ4 | DA QUEENS - SUPREME COURT TRIAL BUREAU | 6 | CONSTRUCTION TO 50% | 2021-01-21 | 2021-05-20 | 2026-12-28 | 2027-04-26
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DAQ4 | DA QUEENS - SUPREME COURT TRIAL BUREAU | 7 | CONSTRUCTION TO 75% | 2021-05-21 | 2021-09-17 | 2027-04-27 | 2027-08-24
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DAQ4 | DA QUEENS - SUPREME COURT TRIAL BUREAU | 8 | ORIGINAL EQUIP & FURNISHING | 2021-09-18 | 2021-12-16 | 2027-08-25 | 2027-11-22
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DAQ4 | DA QUEENS - SUPREME COURT TRIAL BUREAU | 9 | SUBSTANTIAL COMPLETION | 2021-12-17 | 2022-02-14 | 2027-11-23 | 2028-01-21
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DAQ4 | DA QUEENS - SUPREME COURT TRIAL BUREAU | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-02-15 | 2022-03-16 | 2028-01-22 | 2028-02-20
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DAQ5 | DA QUEENS - ECONOMIC CRIMES UNIT | 1 | DEVELOP SCOPE | 2019-06-01 | 2019-08-29 | 2019-06-01 | 2019-08-29
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DAQ5 | DA QUEENS - ECONOMIC CRIMES UNIT | 2 | PRELIMINARY DESIGN | 2019-08-30 | 2019-12-27 | 2019-08-30 | 2019-12-27
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DAQ5 | DA QUEENS - ECONOMIC CRIMES UNIT | 3 | FINAL DESIGN | 2019-12-28 | 2020-06-24 | 2019-12-28 | 2020-06-24
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DAQ5 | DA QUEENS - ECONOMIC CRIMES UNIT | 4 | BID AWARD AND REGISTER CONTRCT | 2020-06-25 | 2020-09-22 | 2020-06-25 | 2020-09-22
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DAQ5 | DA QUEENS - ECONOMIC CRIMES UNIT | 5 | CONSTRUCTION TO 25% | 2020-09-23 | 2021-01-20 | 2020-09-23 | 2021-01-20
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DAQ5 | DA QUEENS - ECONOMIC CRIMES UNIT | 6 | CONSTRUCTION TO 50% | 2021-01-21 | 2021-05-20 | 2021-01-21 | 2021-05-20
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DAQ5 | DA QUEENS - ECONOMIC CRIMES UNIT | 7 | CONSTRUCTION TO 75% | 2021-05-21 | 2021-09-17 | 2021-05-21 | 2021-09-17
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DAQ5 | DA QUEENS - ECONOMIC CRIMES UNIT | 8 | ORIGINAL EQUIP & FURNISHING | 2021-09-18 | 2021-12-16 | 2021-09-18 | 2021-12-16
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DAQ5 | DA QUEENS - ECONOMIC CRIMES UNIT | 9 | SUBSTANTIAL COMPLETION | 2021-12-17 | 2022-02-14 | 2021-12-17 | 2022-02-14
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DAQ5 | DA QUEENS - ECONOMIC CRIMES UNIT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-02-15 | 2022-03-16 | 2022-02-15 | 2022-03-16
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DDC8 | DDC - RENEWAL AT 30-30 THOMSON AVE, LIC | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-08-29 | 2020-06-01 | 2020-08-29
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DDC8 | DDC - RENEWAL AT 30-30 THOMSON AVE, LIC | 2 | PRELIMINARY DESIGN | 2020-08-30 | 2020-12-27 | 2020-08-30 | 2020-12-27
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DDC8 | DDC - RENEWAL AT 30-30 THOMSON AVE, LIC | 3 | FINAL DESIGN | 2020-12-28 | 2021-06-25 | 2020-12-28 | 2021-06-25
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DDC8 | DDC - RENEWAL AT 30-30 THOMSON AVE, LIC | 4 | BID AWARD AND REGISTER CONTRCT | 2021-06-26 | 2021-09-23 | 2021-06-26 | 2021-09-23
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DDC8 | DDC - RENEWAL AT 30-30 THOMSON AVE, LIC | 5 | CONSTRUCTION TO 25% | 2021-09-24 | 2022-01-21 | 2021-09-24 | 2022-01-21
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DDC8 | DDC - RENEWAL AT 30-30 THOMSON AVE, LIC | 6 | CONSTRUCTION TO 50% | 2022-01-22 | 2022-05-21 | 2022-01-22 | 2022-05-21
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DDC8 | DDC - RENEWAL AT 30-30 THOMSON AVE, LIC | 7 | CONSTRUCTION TO 75% | 2022-05-22 | 2022-09-18 | 2022-05-22 | 2022-09-18
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DDC8 | DDC - RENEWAL AT 30-30 THOMSON AVE, LIC | 8 | ORIGINAL EQUIP & FURNISHING | 2022-09-19 | 2022-12-17 | 2022-09-19 | 2022-12-17
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DDC8 | DDC - RENEWAL AT 30-30 THOMSON AVE, LIC | 9 | SUBSTANTIAL COMPLETION | 2022-12-18 | 2023-02-15 | 2022-12-18 | 2023-02-15
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DDC8 | DDC - RENEWAL AT 30-30 THOMSON AVE, LIC | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-02-16 | 2023-03-17 | 2023-02-16 | 2023-03-17
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DOF4 | DOF - 144-06 94TH AVENUE, QUEENS - LEASE RENEWAL | 1 | DEVELOP SCOPE | 2013-06-02 | 2013-08-30 | 2019-06-02 | 2019-08-30
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DOF4 | DOF - 144-06 94TH AVENUE, QUEENS - LEASE RENEWAL | 2 | PRELIMINARY DESIGN | 2013-08-31 | 2013-12-28 | 2019-08-31 | 2019-12-28
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DOF4 | DOF - 144-06 94TH AVENUE, QUEENS - LEASE RENEWAL | 3 | FINAL DESIGN | 2013-12-29 | 2014-06-26 | 2019-12-29 | 2020-06-25
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DOF4 | DOF - 144-06 94TH AVENUE, QUEENS - LEASE RENEWAL | 4 | BID AWARD AND REGISTER CONTRCT | 2014-06-27 | 2014-09-24 | 2020-06-26 | 2020-09-23
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DOF4 | DOF - 144-06 94TH AVENUE, QUEENS - LEASE RENEWAL | 5 | CONSTRUCTION TO 25% | 2014-09-25 | 2015-01-22 | 2020-09-24 | 2021-01-21
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DOF4 | DOF - 144-06 94TH AVENUE, QUEENS - LEASE RENEWAL | 6 | CONSTRUCTION TO 50% | 2015-01-23 | 2015-05-22 | 2021-01-22 | 2021-05-21
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DOF4 | DOF - 144-06 94TH AVENUE, QUEENS - LEASE RENEWAL | 7 | CONSTRUCTION TO 75% | 2015-05-23 | 2015-09-19 | 2021-05-22 | 2021-09-18
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DOF4 | DOF - 144-06 94TH AVENUE, QUEENS - LEASE RENEWAL | 8 | ORIGINAL EQUIP & FURNISHING | 2015-09-20 | 2015-12-18 | 2021-09-19 | 2021-12-17
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DOF4 | DOF - 144-06 94TH AVENUE, QUEENS - LEASE RENEWAL | 9 | SUBSTANTIAL COMPLETION | 2015-12-19 | 2016-02-16 | 2021-12-18 | 2022-02-15
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DOF4 | DOF - 144-06 94TH AVENUE, QUEENS - LEASE RENEWAL | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-02-17 | 2016-03-17 | 2022-02-16 | 2022-03-17
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326EV | DOHMH - 2 GOTHAM CHARGING STATION INFRASTRUCTURE | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-08-29 | 2020-06-01 | 2020-08-29
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326EV | DOHMH - 2 GOTHAM CHARGING STATION INFRASTRUCTURE | 2 | PRELIMINARY DESIGN | 2020-08-30 | 2020-12-27 | 2020-08-30 | 2020-12-27
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326EV | DOHMH - 2 GOTHAM CHARGING STATION INFRASTRUCTURE | 3 | FINAL DESIGN | 2020-12-28 | 2021-06-25 | 2020-12-28 | 2021-06-25
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326EV | DOHMH - 2 GOTHAM CHARGING STATION INFRASTRUCTURE | 4 | BID AWARD AND REGISTER CONTRCT | 2021-06-26 | 2021-09-23 | 2021-06-26 | 2021-09-23
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326EV | DOHMH - 2 GOTHAM CHARGING STATION INFRASTRUCTURE | 5 | CONSTRUCTION TO 25% | 2021-09-24 | 2022-01-21 | 2021-09-24 | 2022-01-21
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326EV | DOHMH - 2 GOTHAM CHARGING STATION INFRASTRUCTURE | 6 | CONSTRUCTION TO 50% | 2022-01-22 | 2022-05-21 | 2022-01-22 | 2022-05-21
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326EV | DOHMH - 2 GOTHAM CHARGING STATION INFRASTRUCTURE | 7 | CONSTRUCTION TO 75% | 2022-05-22 | 2022-09-18 | 2022-05-22 | 2022-09-18
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326EV | DOHMH - 2 GOTHAM CHARGING STATION INFRASTRUCTURE | 8 | ORIGINAL EQUIP & FURNISHING | 2022-09-19 | 2022-12-17 | 2022-09-19 | 2022-12-17
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326EV | DOHMH - 2 GOTHAM CHARGING STATION INFRASTRUCTURE | 9 | SUBSTANTIAL COMPLETION | 2022-12-18 | 2023-02-15 | 2022-12-18 | 2023-02-15
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326EV | DOHMH - 2 GOTHAM CHARGING STATION INFRASTRUCTURE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-02-16 | 2023-03-17 | 2023-02-16 | 2023-03-17
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RAQ | LAW DEPT - RAISE THE AGE - QUEENS | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-08-29 | 2020-06-01 | 2020-08-29
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RAQ | LAW DEPT - RAISE THE AGE - QUEENS | 2 | PRELIMINARY DESIGN | 2020-08-30 | 2020-12-27 | 2020-08-30 | 2020-12-27
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RAQ | LAW DEPT - RAISE THE AGE - QUEENS | 3 | FINAL DESIGN | 2020-12-28 | 2021-06-25 | 2020-12-28 | 2021-06-25
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RAQ | LAW DEPT - RAISE THE AGE - QUEENS | 4 | BID AWARD AND REGISTER CONTRCT | 2021-06-26 | 2021-09-23 | 2021-06-26 | 2021-09-23
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RAQ | LAW DEPT - RAISE THE AGE - QUEENS | 5 | CONSTRUCTION TO 25% | 2021-09-24 | 2022-01-21 | 2021-09-24 | 2022-01-21
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RAQ | LAW DEPT - RAISE THE AGE - QUEENS | 6 | CONSTRUCTION TO 50% | 2022-01-22 | 2022-05-21 | 2022-01-22 | 2022-05-21
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RAQ | LAW DEPT - RAISE THE AGE - QUEENS | 7 | CONSTRUCTION TO 75% | 2022-05-22 | 2022-09-18 | 2022-05-22 | 2022-09-18
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RAQ | LAW DEPT - RAISE THE AGE - QUEENS | 8 | ORIGINAL EQUIP & FURNISHING | 2022-09-19 | 2022-12-17 | 2022-09-19 | 2022-12-17
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RAQ | LAW DEPT - RAISE THE AGE - QUEENS | 9 | SUBSTANTIAL COMPLETION | 2022-12-18 | 2023-02-15 | 2022-12-18 | 2023-02-15
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RAQ | LAW DEPT - RAISE THE AGE - QUEENS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-02-16 | 2023-03-17 | 2023-02-16 | 2023-03-17
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326TLQ3 | TLC -31-00 47 AVE QUEENS | 1 | DEVELOP SCOPE | 2024-06-01 | 2024-09-28 | 2024-06-01 | 2024-08-29
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326TLQ3 | TLC -31-00 47 AVE QUEENS | 2 | BID AWARD AND REGISTER CONTRCT | 2024-09-29 | 2025-03-27 | 2024-08-30 | 2024-12-27
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326TLQ3 | TLC -31-00 47 AVE QUEENS | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-03-28 | 2025-04-26 | 2024-12-28 | 2025-06-25
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326TLQ3 | TLC -31-00 47 AVE QUEENS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-05-27 | 2025-06-25 | 2025-06-26 | 2025-09-23
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326TLQ3 | TLC -31-00 47 AVE QUEENS | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-04-27 | 2025-05-26 | 2025-09-24 | 2026-01-21
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326TLQ3 | TLC -31-00 47 AVE QUEENS | 6 | CONSTRUCTION TO 50% | 2025-04-27 | 2025-05-26 | 2026-01-22 | 2026-05-21
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326TLQ3 | TLC -31-00 47 AVE QUEENS | 7 | CONSTRUCTION TO 75% | 2025-04-27 | 2025-05-26 | 2026-05-22 | 2026-09-18
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326TLQ3 | TLC -31-00 47 AVE QUEENS | 8 | ORIGINAL EQUIP & FURNISHING | 2025-04-27 | 2025-05-26 | 2026-09-19 | 2026-12-17
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326TLQ3 | TLC -31-00 47 AVE QUEENS | 9 | SUBSTANTIAL COMPLETION | 2025-04-27 | 2025-05-26 | 2026-12-18 | 2027-02-15
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326TLQ3 | TLC -31-00 47 AVE QUEENS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-04-27 | 2025-05-26 | 2027-02-16 | 2027-03-17
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77417SW | 120-55 QUEENS BLVD.- SITE WORK | 1 | DEVELOP SCOPE | 2006-06-01 | 2006-08-29 | 2009-01-17 | 2009-04-16
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77417SW | 120-55 QUEENS BLVD.- SITE WORK | 2 | PRELIMINARY DESIGN | 2006-08-30 | 2006-11-27 | 2009-04-17 | 2009-08-14
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77417SW | 120-55 QUEENS BLVD.- SITE WORK | 3 | FINAL DESIGN | 2006-11-28 | 2007-02-25 | 2009-08-15 | 2010-02-10
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77417SW | 120-55 QUEENS BLVD.- SITE WORK | 4 | BID AWARD AND REGISTER CONTRCT | 2007-02-26 | 2007-05-26 | 2022-06-01 | 2022-08-29
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77417SW | 120-55 QUEENS BLVD.- SITE WORK | 5 | CONSTRUCTION TO 25% | 2007-05-27 | 2008-06-29 | 2022-08-30 | 2024-08-18
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77417SW | 120-55 QUEENS BLVD.- SITE WORK | 6 | CONSTRUCTION TO 50% | 2008-06-30 | 2009-08-03 | 2024-08-19 | 2026-08-08
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77417SW | 120-55 QUEENS BLVD.- SITE WORK | 7 | CONSTRUCTION TO 75% | 2009-08-04 | 2010-09-07 | 2026-08-09 | 2027-08-03
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77417SW | 120-55 QUEENS BLVD.- SITE WORK | 8 | ORIGINAL EQUIP & FURNISHING | 2010-09-08 | 2011-08-23 | 2027-08-04 | 2027-09-02
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77417SW | 120-55 QUEENS BLVD.- SITE WORK | 9 | SUBSTANTIAL COMPLETION | 2011-08-24 | 2012-06-18 | 2027-09-03 | 2027-09-17
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77417SW | 120-55 QUEENS BLVD.- SITE WORK | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-06-19 | 2013-03-25 | 2027-09-18 | 2027-10-17
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77417TU | 120-55 QUEENS BOULEVARD- CODE COMPLIANT TOILET UPGRADES | 1 | DEVELOP SCOPE | 2016-06-01 | 2016-08-29 | 2022-06-01 | 2022-08-29
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77417TU | 120-55 QUEENS BOULEVARD- CODE COMPLIANT TOILET UPGRADES | 2 | PRELIMINARY DESIGN | 2016-08-30 | 2016-12-27 | 2022-06-01 | 2022-09-28
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77417TU | 120-55 QUEENS BOULEVARD- CODE COMPLIANT TOILET UPGRADES | 3 | FINAL DESIGN | 2016-12-28 | 2017-06-25 | 2022-09-29 | 2023-03-27
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77417TU | 120-55 QUEENS BOULEVARD- CODE COMPLIANT TOILET UPGRADES | 4 | BID AWARD AND REGISTER CONTRCT | 2017-06-26 | 2017-09-23 | 2023-03-28 | 2023-06-25
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77417TU | 120-55 QUEENS BOULEVARD- CODE COMPLIANT TOILET UPGRADES | 5 | CONSTRUCTION TO 25% | 2017-09-24 | 2018-01-21 | 2024-06-01 | 2024-09-28
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77417TU | 120-55 QUEENS BOULEVARD- CODE COMPLIANT TOILET UPGRADES | 6 | CONSTRUCTION TO 50% | 2018-01-22 | 2018-05-21 | 2024-09-29 | 2025-01-26
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77417TU | 120-55 QUEENS BOULEVARD- CODE COMPLIANT TOILET UPGRADES | 7 | CONSTRUCTION TO 75% | 2018-05-22 | 2018-09-18 | 2025-01-27 | 2026-05-26
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77417TU | 120-55 QUEENS BOULEVARD- CODE COMPLIANT TOILET UPGRADES | 8 | ORIGINAL EQUIP & FURNISHING | 2018-09-19 | 2018-12-17 | 2022-06-01 | 2025-09-17
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77417TU | 120-55 QUEENS BOULEVARD- CODE COMPLIANT TOILET UPGRADES | 9 | SUBSTANTIAL COMPLETION | 2018-12-18 | 2019-02-15 | 2025-09-18 | 2025-11-16
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77417TU | 120-55 QUEENS BOULEVARD- CODE COMPLIANT TOILET UPGRADES | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-02-16 | 2019-03-17 | 2025-11-17 | 2025-12-16
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD78415A | 88-11 SUTPHIN BLVD.- FACADE RESTORATION | 1 | DEVELOP SCOPE | 2011-06-01 | 2011-08-29 | 2026-06-01 | 2026-08-29
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD78415A | 88-11 SUTPHIN BLVD.- FACADE RESTORATION | 2 | PRELIMINARY DESIGN | 2011-08-30 | 2011-12-27 | 2026-08-30 | 2026-12-27
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD78415A | 88-11 SUTPHIN BLVD.- FACADE RESTORATION | 3 | FINAL DESIGN | 2011-12-28 | 2012-06-24 | 2026-12-28 | 2027-06-25
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD78415A | 88-11 SUTPHIN BLVD.- FACADE RESTORATION | 4 | BID AWARD AND REGISTER CONTRCT | 2012-06-25 | 2012-09-22 | 2027-06-26 | 2027-09-23
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD78415A | 88-11 SUTPHIN BLVD.- FACADE RESTORATION | 5 | CONSTRUCTION TO 25% | 2012-09-23 | 2013-01-20 | 2027-09-24 | 2028-01-21
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD78415A | 88-11 SUTPHIN BLVD.- FACADE RESTORATION | 6 | CONSTRUCTION TO 50% | 2013-01-21 | 2013-05-20 | 2028-01-22 | 2028-05-20
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD78415A | 88-11 SUTPHIN BLVD.- FACADE RESTORATION | 7 | CONSTRUCTION TO 75% | 2013-05-21 | 2013-09-17 | 2028-05-21 | 2028-09-17
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD78415A | 88-11 SUTPHIN BLVD.- FACADE RESTORATION | 8 | ORIGINAL EQUIP & FURNISHING | 2013-09-18 | 2013-12-16 | 2028-09-18 | 2028-12-16
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD78415A | 88-11 SUTPHIN BLVD.- FACADE RESTORATION | 9 | SUBSTANTIAL COMPLETION | 2013-12-17 | 2014-02-14 | 2028-12-17 | 2029-02-14
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD78415A | 88-11 SUTPHIN BLVD.- FACADE RESTORATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-02-15 | 2014-03-16 | 2029-02-15 | 2029-03-16
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWQ77QBH2 | 120-55 QUEENS BLVD.- RENOVATIONS | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-08-29 | 2025-06-01 | 2025-08-29
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWQ77QBH2 | 120-55 QUEENS BLVD.- RENOVATIONS | 2 | PRELIMINARY DESIGN | 2020-08-30 | 2020-12-27 | 2025-08-30 | 2025-12-27
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWQ77QBH2 | 120-55 QUEENS BLVD.- RENOVATIONS | 3 | FINAL DESIGN | 2020-12-28 | 2021-06-25 | 2025-12-28 | 2026-06-25
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWQ77QBH2 | 120-55 QUEENS BLVD.- RENOVATIONS | 4 | BID AWARD AND REGISTER CONTRCT | 2021-06-26 | 2021-09-23 | 2026-06-26 | 2026-09-23
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWQ77QBH2 | 120-55 QUEENS BLVD.- RENOVATIONS | 5 | CONSTRUCTION TO 25% | 2021-09-24 | 2022-01-21 | 2026-09-24 | 2027-01-21
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWQ77QBH2 | 120-55 QUEENS BLVD.- RENOVATIONS | 6 | CONSTRUCTION TO 50% | 2022-01-22 | 2022-05-21 | 2027-01-22 | 2027-05-21
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWQ77QBH2 | 120-55 QUEENS BLVD.- RENOVATIONS | 7 | CONSTRUCTION TO 75% | 2022-05-22 | 2022-09-18 | 2027-05-22 | 2027-09-18
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWQ77QBH2 | 120-55 QUEENS BLVD.- RENOVATIONS | 8 | ORIGINAL EQUIP & FURNISHING | 2022-09-19 | 2022-12-17 | 2027-09-19 | 2027-12-17
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWQ77QBH2 | 120-55 QUEENS BLVD.- RENOVATIONS | 9 | SUBSTANTIAL COMPLETION | 2022-12-18 | 2023-02-15 | 2027-12-18 | 2028-02-15
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWQ77QBH2 | 120-55 QUEENS BLVD.- RENOVATIONS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-02-16 | 2023-03-17 | 2028-02-16 | 2028-03-16
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWQ77R213 | 120-55 QUEENS BLVD- QUEENS BORO HALL RENOVATIONS | 1 | DEVELOP SCOPE | 2014-09-01 | 2014-11-29 | 2024-06-01 | 2024-08-29
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWQ77R213 | 120-55 QUEENS BLVD- QUEENS BORO HALL RENOVATIONS | 2 | PRELIMINARY DESIGN | 2014-11-30 | 2015-03-29 | 2024-08-30 | 2024-12-27
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWQ77R213 | 120-55 QUEENS BLVD- QUEENS BORO HALL RENOVATIONS | 3 | FINAL DESIGN | 2015-03-30 | 2015-09-25 | 2024-12-28 | 2025-06-25
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWQ77R213 | 120-55 QUEENS BLVD- QUEENS BORO HALL RENOVATIONS | 4 | BID AWARD AND REGISTER CONTRCT | 2015-09-26 | 2015-12-24 | 2025-06-26 | 2025-09-23
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWQ77R213 | 120-55 QUEENS BLVD- QUEENS BORO HALL RENOVATIONS | 5 | CONSTRUCTION TO 25% | 2015-12-25 | 2016-04-22 | 2025-09-24 | 2026-01-21
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWQ77R213 | 120-55 QUEENS BLVD- QUEENS BORO HALL RENOVATIONS | 6 | CONSTRUCTION TO 50% | 2016-04-23 | 2016-08-20 | 2026-01-22 | 2026-05-21
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWQ77R213 | 120-55 QUEENS BLVD- QUEENS BORO HALL RENOVATIONS | 7 | CONSTRUCTION TO 75% | 2016-08-21 | 2016-12-18 | 2026-05-22 | 2026-09-18
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWQ77R213 | 120-55 QUEENS BLVD- QUEENS BORO HALL RENOVATIONS | 8 | ORIGINAL EQUIP & FURNISHING | 2016-12-19 | 2017-03-18 | 2026-09-19 | 2026-12-19
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWQ77R213 | 120-55 QUEENS BLVD- QUEENS BORO HALL RENOVATIONS | 9 | SUBSTANTIAL COMPLETION | 2017-03-19 | 2017-05-17 | 2026-12-20 | 2027-02-17
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWQ77R213 | 120-55 QUEENS BLVD- QUEENS BORO HALL RENOVATIONS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-05-18 | 2017-06-16 | 2027-02-18 | 2027-04-18
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | RE25VERN | PLATFORM / BULKHEAD REPLACEMENT | 1 | DEVELOP SCOPE | 2023-06-01 | 2023-08-29 | 2023-06-01 | 2023-08-29
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | RE25VERN | PLATFORM / BULKHEAD REPLACEMENT | 2 | PRELIMINARY DESIGN | 2023-08-30 | 2023-12-27 | 2023-08-30 | 2023-12-27
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | RE25VERN | PLATFORM / BULKHEAD REPLACEMENT | 3 | FINAL DESIGN | 2023-12-28 | 2024-06-24 | 2023-12-28 | 2024-06-24
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | RE25VERN | PLATFORM / BULKHEAD REPLACEMENT | 4 | BID AWARD AND REGISTER CONTRCT | 2024-06-25 | 2024-09-22 | 2024-06-25 | 2024-09-22
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | RE25VERN | PLATFORM / BULKHEAD REPLACEMENT | 5 | CONSTRUCTION TO 25% | 2024-09-23 | 2025-01-20 | 2024-09-23 | 2025-01-20
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | RE25VERN | PLATFORM / BULKHEAD REPLACEMENT | 6 | CONSTRUCTION TO 50% | 2025-01-21 | 2025-05-20 | 2025-01-21 | 2025-05-20
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | RE25VERN | PLATFORM / BULKHEAD REPLACEMENT | 7 | CONSTRUCTION TO 75% | 2025-05-21 | 2025-09-17 | 2025-05-21 | 2025-09-17
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | RE25VERN | PLATFORM / BULKHEAD REPLACEMENT | 8 | ORIGINAL EQUIP & FURNISHING | 2025-09-18 | 2025-12-16 | 2025-09-18 | 2025-12-16
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | RE25VERN | PLATFORM / BULKHEAD REPLACEMENT | 9 | SUBSTANTIAL COMPLETION | 2025-12-17 | 2026-02-14 | 2025-12-17 | 2026-02-14
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | RE25VERN | PLATFORM / BULKHEAD REPLACEMENT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2026-02-15 | 2026-03-16 | 2026-02-15 | 2026-03-16
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCACIP04 | CAPACITY NEW SCHOOL - DSF0000866092 @ Q472 | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-06-30 | 2020-06-01 | 2020-06-30
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCACIP04 | CAPACITY NEW SCHOOL - DSF0000866092 @ Q472 | 2 | BID AWARD AND REGISTER CONTRCT | 2020-07-01 | 2020-08-29 | 2020-07-01 | 2020-08-29
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCACIP04 | CAPACITY NEW SCHOOL - DSF0000866092 @ Q472 | 3 | CONSTRUCTION TO 50% | 2020-08-30 | 2021-02-25 | 2020-08-30 | 2021-02-25
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCACIP04 | CAPACITY NEW SCHOOL - DSF0000866092 @ Q472 | 4 | CONSTRUCTION TO 75% | 2021-02-26 | 2021-05-26 | 2021-02-26 | 2021-05-26
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCACIP04 | CAPACITY NEW SCHOOL - DSF0000866092 @ Q472 | 5 | SUBSTANTIAL COMPLETION | 2021-05-27 | 2021-07-25 | 2021-05-27 | 2021-07-25
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCACIP04 | CAPACITY NEW SCHOOL - DSF0000866092 @ Q472 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-07-26 | 2021-08-24 | 2021-07-26 | 2021-08-24
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCACIP07 | Q075 - SYSTEM REPLACEMENT | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-06-30 | 2020-06-01 | 2020-06-30
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCACIP07 | Q075 - SYSTEM REPLACEMENT | 2 | BID AWARD AND REGISTER CONTRCT | 2020-07-01 | 2020-08-29 | 2020-07-01 | 2020-08-29
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCACIP07 | Q075 - SYSTEM REPLACEMENT | 3 | CONSTRUCTION TO 50% | 2020-08-30 | 2021-02-25 | 2020-08-30 | 2021-02-25
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCACIP07 | Q075 - SYSTEM REPLACEMENT | 4 | CONSTRUCTION TO 75% | 2021-02-26 | 2021-05-26 | 2021-02-26 | 2021-05-26
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCACIP07 | Q075 - SYSTEM REPLACEMENT | 5 | SUBSTANTIAL COMPLETION | 2021-05-27 | 2021-07-25 | 2021-05-27 | 2021-07-25
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCACIP07 | Q075 - SYSTEM REPLACEMENT | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-07-26 | 2021-08-24 | 2021-07-26 | 2021-08-24
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | SOLARPQL1 | DCAS PQL Round 1 (EME) DCAS PQL Round 1 (EME) | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-06-30 | 2020-06-01 | 2020-06-30
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | SOLARPQL1 | DCAS PQL Round 1 (EME) DCAS PQL Round 1 (EME) | 2 | BID AWARD AND REGISTER CONTRCT | 2020-07-01 | 2020-08-29 | 2020-07-01 | 2020-08-29
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | SOLARPQL1 | DCAS PQL Round 1 (EME) DCAS PQL Round 1 (EME) | 3 | CONSTRUCTION TO 50% | 2020-08-30 | 2021-02-25 | 2020-08-30 | 2021-02-25
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | SOLARPQL1 | DCAS PQL Round 1 (EME) DCAS PQL Round 1 (EME) | 4 | CONSTRUCTION TO 75% | 2021-02-26 | 2021-05-26 | 2021-02-26 | 2021-05-26
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | SOLARPQL1 | DCAS PQL Round 1 (EME) DCAS PQL Round 1 (EME) | 5 | SUBSTANTIAL COMPLETION | 2021-05-27 | 2021-07-25 | 2021-05-27 | 2021-07-25
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | SOLARPQL1 | DCAS PQL Round 1 (EME) DCAS PQL Round 1 (EME) | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-07-26 | 2021-08-24 | 2021-07-26 | 2021-08-24
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | UNIONHALL | ACS - WORKFORCE INSTITUTE UNION HALL | 1 | DESIGN | 2018-05-18 | 2018-08-10 | 2018-05-18 | 2018-08-10
20201123 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | UNIONHALL | ACS - WORKFORCE INSTITUTE UNION HALL | 2 | CONSTRUCTION | 2018-08-11 | 2021-08-16 | 2018-08-11 | 2021-08-16
20201123 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNCA17THL | TODT HILL - New Lighting | 1 | DEVELOP SCOPE | 2021-07-01 | 2021-09-28 | 2021-07-01 | 2021-09-28
20201123 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNCA17THL | TODT HILL - New Lighting | 2 | DESIGN | 2021-09-29 | 2022-09-28 | 2021-09-29 | 2022-09-28
20201123 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNCA17THL | TODT HILL - New Lighting | 3 | BID/ REGISTER CONTRACT | 2022-09-29 | 2023-06-25 | 2022-09-29 | 2023-06-25
20201123 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNCA17THL | TODT HILL - New Lighting | 4 | CONSTRUCTION | 2023-06-26 | 2024-06-24 | 2023-06-26 | 2024-06-24
20201123 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNCA17THL | TODT HILL - New Lighting | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-06-25 | 2025-06-24 | 2024-06-25 | 2025-06-24
20201123 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNCM15STB | South Beach - New Roof | 1 | DEVELOP SCOPE | 2021-07-01 | 2021-09-28 | 2021-07-01 | 2021-09-28
20201123 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNCM15STB | South Beach - New Roof | 2 | DESIGN | 2021-09-29 | 2022-09-28 | 2021-09-29 | 2022-09-28
20201123 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNCM15STB | South Beach - New Roof | 3 | BID/ REGISTER CONTRACT | 2022-09-29 | 2023-06-25 | 2022-09-29 | 2023-06-25
20201123 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNCM15STB | South Beach - New Roof | 4 | CONSTRUCTION | 2023-06-26 | 2024-06-24 | 2023-06-26 | 2024-06-24
20201123 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNCM15STB | South Beach - New Roof | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-06-25 | 2025-06-24 | 2024-06-25 | 2025-06-24
20201123 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNEM17RTW | RICHMONDTOWN - HVAC System Replacement | 1 | DEVELOP SCOPE | 2021-01-01 | 2021-03-31 | 2023-01-01 | 2023-03-31
20201123 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNEM17RTW | RICHMONDTOWN - HVAC System Replacement | 2 | DESIGN | 2021-04-01 | 2022-03-31 | 2023-04-01 | 2024-03-30
20201123 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNEM17RTW | RICHMONDTOWN - HVAC System Replacement | 3 | BID/ REGISTER CONTRACT | 2022-04-01 | 2022-12-26 | 2024-03-31 | 2024-12-25
20201123 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNEM17RTW | RICHMONDTOWN - HVAC System Replacement | 4 | CONSTRUCTION | 2022-12-27 | 2023-12-26 | 2024-12-26 | 2025-12-25
20201123 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNEM17RTW | RICHMONDTOWN - HVAC System Replacement | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-12-27 | 2024-12-25 | 2025-12-26 | 2026-12-25
20201123 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNRA17NDP | NEW DORP - HVAC System Replacement | 1 | DEVELOP SCOPE | 2016-12-30 | 2017-03-29 | 2019-09-01 | 2019-11-29
20201123 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNRA17NDP | NEW DORP - HVAC System Replacement | 2 | PRELIMINARY DESIGN | 2017-03-30 | 2017-07-27 | 2019-11-30 | 2020-03-28
20201123 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNRA17NDP | NEW DORP - HVAC System Replacement | 3 | FINAL DESIGN | 2017-07-28 | 2018-01-23 | 2020-03-29 | 2020-09-24
20201123 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNRA17NDP | NEW DORP - HVAC System Replacement | 4 | BID AWARD AND REGISTER CONTRCT | 2018-01-24 | 2018-04-23 | 2020-09-25 | 2020-12-23
20201123 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNRA17NDP | NEW DORP - HVAC System Replacement | 5 | CONSTRUCTION TO 25% | 2018-04-24 | 2018-08-21 | 2020-12-24 | 2021-04-22
20201123 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNRA17NDP | NEW DORP - HVAC System Replacement | 6 | CONSTRUCTION TO 50% | 2018-08-22 | 2018-12-19 | 2021-04-23 | 2021-08-20
20201123 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNRA17NDP | NEW DORP - HVAC System Replacement | 7 | CONSTRUCTION TO 75% | 2018-12-20 | 2019-04-18 | 2021-08-21 | 2021-12-18
20201123 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNRA17NDP | NEW DORP - HVAC System Replacement | 8 | ORIGINAL EQUIP & FURNISHING | 2019-04-19 | 2019-07-17 | 2021-12-19 | 2022-03-18
20201123 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNRA17NDP | NEW DORP - HVAC System Replacement | 9 | SUBSTANTIAL COMPLETION | 2019-07-18 | 2019-09-15 | 2022-03-19 | 2022-05-17
20201123 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNRA17NDP | NEW DORP - HVAC System Replacement | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-16 | 2019-10-15 | 2022-05-18 | 2022-06-16
20201123 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNRA17WNB | WEST NEW BRIGHTON - ADA-compliant Elevators | 1 | DEVELOP SCOPE | 2017-12-01 | 2018-02-28 | 2021-06-29 | 2021-09-26
20201123 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNRA17WNB | WEST NEW BRIGHTON - ADA-compliant Elevators | 2 | PRELIMINARY DESIGN | 2018-03-01 | 2018-06-28 | 2021-09-27 | 2022-01-24
20201123 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNRA17WNB | WEST NEW BRIGHTON - ADA-compliant Elevators | 3 | FINAL DESIGN | 2018-06-29 | 2018-12-25 | 2022-01-25 | 2022-07-23
20201123 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNRA17WNB | WEST NEW BRIGHTON - ADA-compliant Elevators | 4 | BID AWARD AND REGISTER CONTRCT | 2018-12-26 | 2019-03-25 | 2022-07-24 | 2022-10-21
20201123 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNRA17WNB | WEST NEW BRIGHTON - ADA-compliant Elevators | 5 | CONSTRUCTION TO 25% | 2019-03-26 | 2019-07-23 | 2022-10-22 | 2023-02-18
20201123 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNRA17WNB | WEST NEW BRIGHTON - ADA-compliant Elevators | 6 | CONSTRUCTION TO 50% | 2019-07-24 | 2019-11-20 | 2023-02-19 | 2023-06-18
20201123 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNRA17WNB | WEST NEW BRIGHTON - ADA-compliant Elevators | 7 | CONSTRUCTION TO 75% | 2019-11-21 | 2020-03-19 | 2023-06-19 | 2023-10-16
20201123 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNRA17WNB | WEST NEW BRIGHTON - ADA-compliant Elevators | 8 | ORIGINAL EQUIP & FURNISHING | 2020-03-20 | 2020-06-17 | 2023-10-17 | 2024-01-14
20201123 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNRA17WNB | WEST NEW BRIGHTON - ADA-compliant Elevators | 9 | SUBSTANTIAL COMPLETION | 2020-06-18 | 2020-08-16 | 2024-01-15 | 2024-03-14
20201123 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNRA17WNB | WEST NEW BRIGHTON - ADA-compliant Elevators | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-08-17 | 2020-09-15 | 2024-03-15 | 2024-04-13
20201123 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNRA18GCK | Great Kills - ADA-compliant Restrooms | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-09-28 | 2019-07-01 | 2019-09-28
20201123 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNRA18GCK | Great Kills - ADA-compliant Restrooms | 2 | DESIGN | 2019-09-29 | 2020-09-27 | 2019-09-29 | 2020-09-27
20201123 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNRA18GCK | Great Kills - ADA-compliant Restrooms | 3 | BID/ REGISTER CONTRACT | 2020-09-28 | 2021-06-24 | 2020-09-28 | 2021-06-24
20201123 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNRA18GCK | Great Kills - ADA-compliant Restrooms | 4 | CONSTRUCTION | 2021-06-25 | 2022-06-24 | 2021-06-25 | 2022-06-24
20201123 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNRA18GCK | Great Kills - ADA-compliant Restrooms | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-06-25 | 2023-06-24 | 2022-06-25 | 2023-06-24
20201123 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNRA18RCH | Richmondtown - New Boiler | 1 | DEVELOP SCOPE | 2019-12-01 | 2020-02-28 | 2019-12-01 | 2020-02-28
20201123 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNRA18RCH | Richmondtown - New Boiler | 2 | DESIGN | 2020-02-29 | 2021-02-27 | 2020-02-29 | 2021-02-27
20201123 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNRA18RCH | Richmondtown - New Boiler | 3 | BID/ REGISTER CONTRACT | 2021-02-28 | 2021-11-24 | 2021-02-28 | 2021-11-24
20201123 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNRA18RCH | Richmondtown - New Boiler | 4 | CONSTRUCTION | 2021-11-25 | 2022-11-24 | 2021-11-25 | 2022-11-24
20201123 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNRA18RCH | Richmondtown - New Boiler | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-11-25 | 2023-11-24 | 2022-11-25 | 2023-11-24
20201123 | RICHMOND | 042 | CITY UNIVERSITY | ST001-021 | Science Lecture Room | 1 | DEVELOP SCOPE | 2021-06-30 | 2021-09-27 | 2021-06-30 | 2021-09-27
20201123 | RICHMOND | 042 | CITY UNIVERSITY | ST001-021 | Science Lecture Room | 2 | PRELIMINARY DESIGN | 2021-09-28 | 2022-01-25 | 2021-09-28 | 2022-01-25
20201123 | RICHMOND | 042 | CITY UNIVERSITY | ST001-021 | Science Lecture Room | 3 | FINAL DESIGN | 2022-01-26 | 2022-07-24 | 2022-01-26 | 2022-07-24
20201123 | RICHMOND | 042 | CITY UNIVERSITY | ST001-021 | Science Lecture Room | 4 | BID AWARD AND REGISTER CONTRCT | 2022-07-25 | 2022-10-22 | 2022-07-25 | 2022-10-22
20201123 | RICHMOND | 042 | CITY UNIVERSITY | ST001-021 | Science Lecture Room | 5 | CONSTRUCTION TO 25% | 2022-10-23 | 2023-02-19 | 2022-10-23 | 2023-02-19
20201123 | RICHMOND | 042 | CITY UNIVERSITY | ST001-021 | Science Lecture Room | 6 | CONSTRUCTION TO 50% | 2023-02-20 | 2023-06-19 | 2023-02-20 | 2023-06-19
20201123 | RICHMOND | 042 | CITY UNIVERSITY | ST001-021 | Science Lecture Room | 7 | CONSTRUCTION TO 75% | 2023-06-20 | 2023-10-17 | 2023-06-20 | 2023-10-17
20201123 | RICHMOND | 042 | CITY UNIVERSITY | ST001-021 | Science Lecture Room | 8 | ORIGINAL EQUIP & FURNISHING | 2023-10-18 | 2024-01-15 | 2023-10-18 | 2024-01-15
20201123 | RICHMOND | 042 | CITY UNIVERSITY | ST001-021 | Science Lecture Room | 9 | SUBSTANTIAL COMPLETION | 2024-01-16 | 2024-03-15 | 2024-01-16 | 2024-03-15
20201123 | RICHMOND | 042 | CITY UNIVERSITY | ST001-021 | Science Lecture Room | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-03-16 | 2024-04-14 | 2024-03-16 | 2024-04-14
20201123 | RICHMOND | 042 | CITY UNIVERSITY | ST030-015 | Support Center for High Performance Computer | 1 | DEVELOP SCOPE | 2015-03-01 | 2015-05-29 | 2015-03-01 | 2015-05-29
20201123 | RICHMOND | 042 | CITY UNIVERSITY | ST030-015 | Support Center for High Performance Computer | 2 | PRELIMINARY DESIGN | 2015-05-30 | 2015-09-26 | 2015-05-30 | 2015-09-26
20201123 | RICHMOND | 042 | CITY UNIVERSITY | ST030-015 | Support Center for High Performance Computer | 3 | FINAL DESIGN | 2015-09-27 | 2016-03-24 | 2015-09-27 | 2016-03-24
20201123 | RICHMOND | 042 | CITY UNIVERSITY | ST030-015 | Support Center for High Performance Computer | 4 | BID AWARD AND REGISTER CONTRCT | 2016-03-25 | 2016-06-22 | 2016-03-25 | 2016-06-22
20201123 | RICHMOND | 042 | CITY UNIVERSITY | ST030-015 | Support Center for High Performance Computer | 5 | CONSTRUCTION TO 25% | 2016-06-23 | 2016-10-20 | 2016-06-23 | 2016-10-20
20201123 | RICHMOND | 042 | CITY UNIVERSITY | ST030-015 | Support Center for High Performance Computer | 6 | CONSTRUCTION TO 50% | 2016-10-21 | 2017-02-17 | 2016-10-21 | 2017-02-17
20201123 | RICHMOND | 042 | CITY UNIVERSITY | ST030-015 | Support Center for High Performance Computer | 7 | CONSTRUCTION TO 75% | 2017-02-18 | 2017-06-17 | 2017-02-18 | 2017-06-17
20201123 | RICHMOND | 042 | CITY UNIVERSITY | ST030-015 | Support Center for High Performance Computer | 8 | ORIGINAL EQUIP & FURNISHING | 2017-06-18 | 2017-09-15 | 2017-06-18 | 2017-09-15
20201123 | RICHMOND | 042 | CITY UNIVERSITY | ST030-015 | Support Center for High Performance Computer | 9 | SUBSTANTIAL COMPLETION | 2017-09-16 | 2017-11-14 | 2017-09-16 | 2017-11-14
20201123 | RICHMOND | 042 | CITY UNIVERSITY | ST030-015 | Support Center for High Performance Computer | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-11-15 | 2017-12-14 | 2017-11-15 | 2025-12-30
20201123 | RICHMOND | 042 | CITY UNIVERSITY | ST031-015 | Soccer Field Lighting and Bleachers | 2 | PRELIMINARY DESIGN | 2014-12-30 | 2015-04-28 | 2014-12-30 | 2015-04-28
20201123 | RICHMOND | 042 | CITY UNIVERSITY | ST031-015 | Soccer Field Lighting and Bleachers | 3 | FINAL DESIGN | 2015-04-29 | 2015-10-25 | 2015-04-29 | 2015-10-25
20201123 | RICHMOND | 042 | CITY UNIVERSITY | ST031-015 | Soccer Field Lighting and Bleachers | 4 | BID AWARD AND REGISTER CONTRCT | 2015-10-26 | 2016-01-23 | 2015-10-26 | 2016-01-23
20201123 | RICHMOND | 042 | CITY UNIVERSITY | ST031-015 | Soccer Field Lighting and Bleachers | 5 | CONSTRUCTION TO 25% | 2016-01-24 | 2016-05-22 | 2016-01-24 | 2016-05-22
20201123 | RICHMOND | 042 | CITY UNIVERSITY | ST031-015 | Soccer Field Lighting and Bleachers | 6 | CONSTRUCTION TO 50% | 2016-05-23 | 2016-09-19 | 2016-05-23 | 2016-09-19
20201123 | RICHMOND | 042 | CITY UNIVERSITY | ST031-015 | Soccer Field Lighting and Bleachers | 7 | CONSTRUCTION TO 75% | 2016-09-20 | 2017-01-17 | 2016-09-20 | 2017-01-17
20201123 | RICHMOND | 042 | CITY UNIVERSITY | ST031-015 | Soccer Field Lighting and Bleachers | 8 | ORIGINAL EQUIP & FURNISHING | 2017-01-18 | 2017-04-17 | 2017-01-18 | 2017-04-17
20201123 | RICHMOND | 042 | CITY UNIVERSITY | ST031-015 | Soccer Field Lighting and Bleachers | 9 | SUBSTANTIAL COMPLETION | 2017-04-18 | 2017-06-16 | 2017-04-18 | 2017-06-16
20201123 | RICHMOND | 042 | CITY UNIVERSITY | ST031-015 | Soccer Field Lighting and Bleachers | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-06-17 | 2017-07-16 | 2017-06-17 | 2021-07-31
20201123 | RICHMOND | 042 | CITY UNIVERSITY | ST032-015 | Media Culture Screening Room | 1 | DEVELOP SCOPE | 2014-10-01 | 2014-12-29 | 2014-10-01 | 2014-12-29
20201123 | RICHMOND | 042 | CITY UNIVERSITY | ST032-015 | Media Culture Screening Room | 2 | PRELIMINARY DESIGN | 2014-12-30 | 2015-04-28 | 2014-12-30 | 2015-04-28
20201123 | RICHMOND | 042 | CITY UNIVERSITY | ST032-015 | Media Culture Screening Room | 3 | FINAL DESIGN | 2015-04-29 | 2015-10-25 | 2015-04-29 | 2015-10-25
20201123 | RICHMOND | 042 | CITY UNIVERSITY | ST032-015 | Media Culture Screening Room | 4 | BID AWARD AND REGISTER CONTRCT | 2015-10-26 | 2016-01-23 | 2015-10-26 | 2016-01-23
20201123 | RICHMOND | 042 | CITY UNIVERSITY | ST032-015 | Media Culture Screening Room | 5 | CONSTRUCTION TO 25% | 2016-01-24 | 2016-05-22 | 2016-01-24 | 2016-05-22
20201123 | RICHMOND | 042 | CITY UNIVERSITY | ST032-015 | Media Culture Screening Room | 6 | CONSTRUCTION TO 50% | 2016-05-23 | 2016-09-19 | 2016-05-23 | 2016-09-19
20201123 | RICHMOND | 042 | CITY UNIVERSITY | ST032-015 | Media Culture Screening Room | 7 | CONSTRUCTION TO 75% | 2016-09-20 | 2017-01-17 | 2016-09-20 | 2017-01-17
20201123 | RICHMOND | 042 | CITY UNIVERSITY | ST032-015 | Media Culture Screening Room | 8 | ORIGINAL EQUIP & FURNISHING | 2017-01-18 | 2017-04-17 | 2017-01-18 | 2017-04-17
20201123 | RICHMOND | 042 | CITY UNIVERSITY | ST032-015 | Media Culture Screening Room | 9 | SUBSTANTIAL COMPLETION | 2017-04-18 | 2017-06-16 | 2017-04-18 | 2017-06-16
20201123 | RICHMOND | 042 | CITY UNIVERSITY | ST032-015 | Media Culture Screening Room | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-06-17 | 2017-07-16 | 2017-06-17 | 2022-07-31
20201123 | RICHMOND | 042 | CITY UNIVERSITY | ST034-016 | High Performance Computer Center | 1 | DEVELOP SCOPE | 2016-06-30 | 2016-09-27 | 2016-06-30 | 2016-09-27
20201123 | RICHMOND | 042 | CITY UNIVERSITY | ST034-016 | High Performance Computer Center | 2 | PRELIMINARY DESIGN | 2016-09-28 | 2017-01-25 | 2016-09-28 | 2017-01-25
20201123 | RICHMOND | 042 | CITY UNIVERSITY | ST034-016 | High Performance Computer Center | 3 | FINAL DESIGN | 2017-01-26 | 2017-07-24 | 2017-01-26 | 2017-07-24
20201123 | RICHMOND | 042 | CITY UNIVERSITY | ST034-016 | High Performance Computer Center | 4 | BID AWARD AND REGISTER CONTRCT | 2017-07-25 | 2017-10-22 | 2017-07-25 | 2017-10-22
20201123 | RICHMOND | 042 | CITY UNIVERSITY | ST034-016 | High Performance Computer Center | 5 | CONSTRUCTION TO 25% | 2017-10-23 | 2018-02-19 | 2017-10-23 | 2018-02-19
20201123 | RICHMOND | 042 | CITY UNIVERSITY | ST034-016 | High Performance Computer Center | 6 | CONSTRUCTION TO 50% | 2018-02-20 | 2018-06-19 | 2018-02-20 | 2018-06-19
20201123 | RICHMOND | 042 | CITY UNIVERSITY | ST034-016 | High Performance Computer Center | 7 | CONSTRUCTION TO 75% | 2018-06-20 | 2018-10-17 | 2018-06-20 | 2018-10-17
20201123 | RICHMOND | 042 | CITY UNIVERSITY | ST034-016 | High Performance Computer Center | 8 | ORIGINAL EQUIP & FURNISHING | 2018-10-18 | 2019-01-15 | 2018-10-18 | 2019-01-15
20201123 | RICHMOND | 042 | CITY UNIVERSITY | ST034-016 | High Performance Computer Center | 9 | SUBSTANTIAL COMPLETION | 2019-01-16 | 2019-03-16 | 2019-01-16 | 2019-03-16
20201123 | RICHMOND | 042 | CITY UNIVERSITY | ST034-016 | High Performance Computer Center | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-03-17 | 2019-04-15 | 2019-03-17 | 2024-04-15
20201123 | RICHMOND | 042 | CITY UNIVERSITY | ST035-016 | Storage Facility Improvements | 3 | FINAL DESIGN | 2017-01-26 | 2017-07-24 | 2017-01-26 | 2017-07-24
20201123 | RICHMOND | 042 | CITY UNIVERSITY | ST035-016 | Storage Facility Improvements | 4 | BID AWARD AND REGISTER CONTRCT | 2017-07-25 | 2017-10-22 | 2017-07-25 | 2017-10-22
20201123 | RICHMOND | 042 | CITY UNIVERSITY | ST035-016 | Storage Facility Improvements | 5 | CONSTRUCTION TO 25% | 2017-10-23 | 2018-02-19 | 2017-10-23 | 2018-02-19
20201123 | RICHMOND | 042 | CITY UNIVERSITY | ST035-016 | Storage Facility Improvements | 6 | CONSTRUCTION TO 50% | 2018-02-20 | 2018-06-19 | 2018-02-20 | 2018-06-19
20201123 | RICHMOND | 042 | CITY UNIVERSITY | ST035-016 | Storage Facility Improvements | 7 | CONSTRUCTION TO 75% | 2018-06-20 | 2018-10-17 | 2018-06-20 | 2018-10-17
20201123 | RICHMOND | 042 | CITY UNIVERSITY | ST035-016 | Storage Facility Improvements | 8 | ORIGINAL EQUIP & FURNISHING | 2018-10-18 | 2019-01-15 | 2018-10-18 | 2019-01-15
20201123 | RICHMOND | 042 | CITY UNIVERSITY | ST035-016 | Storage Facility Improvements | 9 | SUBSTANTIAL COMPLETION | 2019-01-16 | 2019-03-16 | 2019-01-16 | 2019-03-16
20201123 | RICHMOND | 042 | CITY UNIVERSITY | ST035-016 | Storage Facility Improvements | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-03-17 | 2019-04-15 | 2019-03-17 | 2019-04-15
20201123 | RICHMOND | 042 | CITY UNIVERSITY | ST038-018 | Reconstruction of Baseball Field | 1 | DEVELOP SCOPE | 2018-06-01 | 2018-08-29 | 2018-06-01 | 2018-08-29
20201123 | RICHMOND | 042 | CITY UNIVERSITY | ST038-018 | Reconstruction of Baseball Field | 2 | PRELIMINARY DESIGN | 2018-08-30 | 2018-12-27 | 2018-08-30 | 2018-12-27
20201123 | RICHMOND | 042 | CITY UNIVERSITY | ST038-018 | Reconstruction of Baseball Field | 3 | FINAL DESIGN | 2018-12-28 | 2019-06-25 | 2018-12-28 | 2019-06-25
20201123 | RICHMOND | 042 | CITY UNIVERSITY | ST038-018 | Reconstruction of Baseball Field | 4 | BID AWARD AND REGISTER CONTRCT | 2019-06-26 | 2019-09-23 | 2019-06-26 | 2019-09-23
20201123 | RICHMOND | 042 | CITY UNIVERSITY | ST038-018 | Reconstruction of Baseball Field | 5 | CONSTRUCTION TO 25% | 2019-09-24 | 2020-01-21 | 2019-09-24 | 2020-01-21
20201123 | RICHMOND | 042 | CITY UNIVERSITY | ST038-018 | Reconstruction of Baseball Field | 6 | CONSTRUCTION TO 50% | 2020-01-22 | 2020-05-20 | 2020-01-22 | 2020-05-20
20201123 | RICHMOND | 042 | CITY UNIVERSITY | ST038-018 | Reconstruction of Baseball Field | 7 | CONSTRUCTION TO 75% | 2020-05-21 | 2020-09-17 | 2020-05-21 | 2020-09-17
20201123 | RICHMOND | 042 | CITY UNIVERSITY | ST038-018 | Reconstruction of Baseball Field | 8 | ORIGINAL EQUIP & FURNISHING | 2020-09-18 | 2020-12-16 | 2020-09-18 | 2020-12-16
20201123 | RICHMOND | 042 | CITY UNIVERSITY | ST038-018 | Reconstruction of Baseball Field | 9 | SUBSTANTIAL COMPLETION | 2020-12-17 | 2021-02-14 | 2020-12-17 | 2021-02-14
20201123 | RICHMOND | 042 | CITY UNIVERSITY | ST038-018 | Reconstruction of Baseball Field | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-02-15 | 2021-03-16 | 2021-02-15 | 2021-03-16
20201123 | RICHMOND | 042 | CITY UNIVERSITY | ST039-019 | Maker Space Lab | 1 | DEVELOP SCOPE | 2018-06-30 | 2018-09-27 | 2021-07-01 | 2021-09-28
20201123 | RICHMOND | 042 | CITY UNIVERSITY | ST039-019 | Maker Space Lab | 2 | PRELIMINARY DESIGN | 2018-09-28 | 2019-01-25 | 2021-09-29 | 2022-01-26
20201123 | RICHMOND | 042 | CITY UNIVERSITY | ST039-019 | Maker Space Lab | 3 | FINAL DESIGN | 2019-01-26 | 2019-07-24 | 2022-01-27 | 2022-07-25
20201123 | RICHMOND | 042 | CITY UNIVERSITY | ST039-019 | Maker Space Lab | 4 | BID AWARD AND REGISTER CONTRCT | 2019-07-25 | 2019-10-22 | 2022-07-26 | 2022-10-23
20201123 | RICHMOND | 042 | CITY UNIVERSITY | ST039-019 | Maker Space Lab | 5 | CONSTRUCTION TO 25% | 2019-10-23 | 2020-02-19 | 2022-10-24 | 2023-02-20
20201123 | RICHMOND | 042 | CITY UNIVERSITY | ST039-019 | Maker Space Lab | 6 | CONSTRUCTION TO 50% | 2020-02-20 | 2020-06-18 | 2023-02-21 | 2023-06-20
20201123 | RICHMOND | 042 | CITY UNIVERSITY | ST039-019 | Maker Space Lab | 7 | CONSTRUCTION TO 75% | 2020-06-19 | 2020-10-16 | 2023-06-21 | 2023-10-18
20201123 | RICHMOND | 042 | CITY UNIVERSITY | ST039-019 | Maker Space Lab | 8 | ORIGINAL EQUIP & FURNISHING | 2020-10-17 | 2021-01-14 | 2023-10-19 | 2024-01-16
20201123 | RICHMOND | 042 | CITY UNIVERSITY | ST039-019 | Maker Space Lab | 9 | SUBSTANTIAL COMPLETION | 2021-01-15 | 2021-03-15 | 2024-01-17 | 2024-03-16
20201123 | RICHMOND | 042 | CITY UNIVERSITY | ST039-019 | Maker Space Lab | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-16 | 2021-04-14 | 2024-03-17 | 2024-04-15
20201123 | RICHMOND | 042 | CITY UNIVERSITY | ST041-020 | Room Conversion for the Genomic Research Center | 1 | DEVELOP SCOPE | 2020-06-30 | 2020-09-27 | 2020-06-30 | 2020-09-27
20201123 | RICHMOND | 042 | CITY UNIVERSITY | ST041-020 | Room Conversion for the Genomic Research Center | 2 | PRELIMINARY DESIGN | 2020-09-28 | 2021-01-25 | 2020-09-28 | 2021-01-25
20201123 | RICHMOND | 042 | CITY UNIVERSITY | ST041-020 | Room Conversion for the Genomic Research Center | 3 | FINAL DESIGN | 2021-01-26 | 2021-07-24 | 2021-01-26 | 2021-07-24
20201123 | RICHMOND | 042 | CITY UNIVERSITY | ST041-020 | Room Conversion for the Genomic Research Center | 4 | BID AWARD AND REGISTER CONTRCT | 2021-07-25 | 2021-10-22 | 2021-07-25 | 2021-10-22
20201123 | RICHMOND | 042 | CITY UNIVERSITY | ST041-020 | Room Conversion for the Genomic Research Center | 5 | CONSTRUCTION TO 25% | 2021-10-23 | 2022-02-19 | 2021-10-23 | 2022-02-19
20201123 | RICHMOND | 042 | CITY UNIVERSITY | ST041-020 | Room Conversion for the Genomic Research Center | 6 | CONSTRUCTION TO 50% | 2022-02-20 | 2022-06-19 | 2022-02-20 | 2022-06-19
20201123 | RICHMOND | 042 | CITY UNIVERSITY | ST041-020 | Room Conversion for the Genomic Research Center | 7 | CONSTRUCTION TO 75% | 2022-06-20 | 2022-10-17 | 2022-06-20 | 2022-10-17
20201123 | RICHMOND | 042 | CITY UNIVERSITY | ST041-020 | Room Conversion for the Genomic Research Center | 8 | ORIGINAL EQUIP & FURNISHING | 2022-10-18 | 2023-01-15 | 2022-10-18 | 2023-01-15
20201123 | RICHMOND | 042 | CITY UNIVERSITY | ST041-020 | Room Conversion for the Genomic Research Center | 9 | SUBSTANTIAL COMPLETION | 2023-01-16 | 2023-03-16 | 2023-01-16 | 2023-03-16
20201123 | RICHMOND | 042 | CITY UNIVERSITY | ST041-020 | Room Conversion for the Genomic Research Center | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-03-17 | 2023-04-15 | 2023-03-17 | 2023-04-15
20201123 | RICHMOND | 056 | POLICE DEPARTMENT | PO79120AC | 120TH PCT - NEW HVAC SYSTEM | 1 | DEVELOP SCOPE | 2012-09-30 | 2012-12-28 | 2016-06-20 | 2016-09-17
20201123 | RICHMOND | 056 | POLICE DEPARTMENT | PO79120AC | 120TH PCT - NEW HVAC SYSTEM | 2 | PRELIMINARY DESIGN | 2012-12-29 | 2013-04-27 | 2016-09-18 | 2017-01-15
20201123 | RICHMOND | 056 | POLICE DEPARTMENT | PO79120AC | 120TH PCT - NEW HVAC SYSTEM | 3 | FINAL DESIGN | 2013-04-28 | 2013-08-25 | 2017-01-16 | 2017-05-15
20201123 | RICHMOND | 056 | POLICE DEPARTMENT | PO79120AC | 120TH PCT - NEW HVAC SYSTEM | 4 | BID AWARD AND REGISTER CONTRCT | 2013-08-26 | 2014-02-21 | 2017-05-16 | 2017-11-11
20201123 | RICHMOND | 056 | POLICE DEPARTMENT | PO79120AC | 120TH PCT - NEW HVAC SYSTEM | 5 | CONSTRUCTION TO 25% | 2014-02-22 | 2014-06-21 | 2017-11-12 | 2018-03-11
20201123 | RICHMOND | 056 | POLICE DEPARTMENT | PO79120AC | 120TH PCT - NEW HVAC SYSTEM | 6 | CONSTRUCTION TO 50% | 2014-06-22 | 2014-10-19 | 2018-03-12 | 2018-07-09
20201123 | RICHMOND | 056 | POLICE DEPARTMENT | PO79120AC | 120TH PCT - NEW HVAC SYSTEM | 7 | CONSTRUCTION TO 75% | 2014-10-20 | 2015-02-16 | 2018-07-10 | 2020-11-06
20201123 | RICHMOND | 056 | POLICE DEPARTMENT | PO79120AC | 120TH PCT - NEW HVAC SYSTEM | 8 | ORIGINAL EQUIP & FURNISHING | 2015-02-17 | 2015-05-17 | 2020-11-07 | 2021-02-04
20201123 | RICHMOND | 056 | POLICE DEPARTMENT | PO79120AC | 120TH PCT - NEW HVAC SYSTEM | 9 | SUBSTANTIAL COMPLETION | 2015-05-18 | 2015-07-16 | 2021-02-05 | 2021-04-05
20201123 | RICHMOND | 056 | POLICE DEPARTMENT | PO79120AC | 120TH PCT - NEW HVAC SYSTEM | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-07-17 | 2015-08-15 | 2021-04-06 | 2021-05-05
20201123 | RICHMOND | 057 | FIRE DEPARTMENT | F175MC152 | Multi-Component Renovations - EC152 | 1 | DESIGN | 2019-03-06 | 2019-09-01 | 2020-03-04 | 2020-08-30
20201123 | RICHMOND | 057 | FIRE DEPARTMENT | F175MC152 | Multi-Component Renovations - EC152 | 2 | CONSTRUCTION | 2019-09-02 | 2020-08-31 | 2020-08-31 | 2021-08-30
20201123 | RICHMOND | 057 | FIRE DEPARTMENT | F175MC152 | Multi-Component Renovations - EC152 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-01 | 2020-11-29 | 2021-08-31 | 2022-01-28
20201123 | RICHMOND | 057 | FIRE DEPARTMENT | F175MC159 | Multi-Component Renovations - EC159 | 1 | DESIGN | 2019-01-15 | 2019-04-14 | 2019-01-15 | 2019-04-14
20201123 | RICHMOND | 057 | FIRE DEPARTMENT | F175MC159 | Multi-Component Renovations - EC159 | 2 | BID AWARD AND REGISTER CONTRCT | 2019-04-15 | 2020-01-09 | 2019-04-15 | 2020-01-09
20201123 | RICHMOND | 057 | FIRE DEPARTMENT | F175MC159 | Multi-Component Renovations - EC159 | 3 | CONSTRUCTION | 2020-01-10 | 2021-02-12 | 2020-01-10 | 2021-02-12
20201123 | RICHMOND | 057 | FIRE DEPARTMENT | F175MC159 | Multi-Component Renovations - EC159 | 4 | ORIGINAL EQUIP & FURNISHING | 2021-02-13 | 2021-03-29 | 2021-02-13 | 2021-03-29
20201123 | RICHMOND | 057 | FIRE DEPARTMENT | F175MC159 | Multi-Component Renovations - EC159 | 5 | SUBSTANTIAL COMPLETION | 2021-03-30 | 2021-05-08 | 2021-03-30 | 2021-05-08
20201123 | RICHMOND | 057 | FIRE DEPARTMENT | F175MC159 | Multi-Component Renovations - EC159 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-05-09 | 2021-07-07 | 2021-05-09 | 2021-07-07
20201123 | RICHMOND | 057 | FIRE DEPARTMENT | F175SEWER | New Sewer Main and Pumping Station - Outside Plant Garage | 1 | DESIGN | 2018-11-16 | 2019-05-14 | 2018-11-16 | 2019-05-14
20201123 | RICHMOND | 057 | FIRE DEPARTMENT | F175SEWER | New Sewer Main and Pumping Station - Outside Plant Garage | 2 | CONSTRUCTION | 2019-05-15 | 2020-05-13 | 2019-05-15 | 2020-05-13
20201123 | RICHMOND | 057 | FIRE DEPARTMENT | F175SEWER | New Sewer Main and Pumping Station - Outside Plant Garage | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-05-14 | 2020-08-11 | 2020-05-14 | 2020-08-11
20201123 | RICHMOND | 057 | FIRE DEPARTMENT | FD175G161 | Generator - EC161 | 1 | DESIGN | 2019-01-15 | 2019-07-13 | 2020-01-15 | 2020-07-12
20201123 | RICHMOND | 057 | FIRE DEPARTMENT | FD175G161 | Generator - EC161 | 2 | CONSTRUCTION | 2019-07-14 | 2020-07-12 | 2020-07-13 | 2021-07-12
20201123 | RICHMOND | 057 | FIRE DEPARTMENT | FD175G161 | Generator - EC161 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-07-13 | 2020-10-10 | 2021-07-13 | 2021-10-10
20201123 | RICHMOND | 057 | FIRE DEPARTMENT | FD175G165 | Generator - EC165 | 1 | DESIGN | 2019-01-15 | 2019-07-13 | 2020-01-15 | 2020-07-12
20201123 | RICHMOND | 057 | FIRE DEPARTMENT | FD175G165 | Generator - EC165 | 2 | CONSTRUCTION | 2019-07-14 | 2020-07-12 | 2020-07-13 | 2021-07-12
20201123 | RICHMOND | 057 | FIRE DEPARTMENT | FD175G165 | Generator - EC165 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-07-13 | 2020-10-10 | 2021-07-13 | 2021-10-10
20201123 | RICHMOND | 057 | FIRE DEPARTMENT | FD175W154 | WINDOW REPLACEMENT - EC154 | 1 | CONSTRUCTION | 2018-04-01 | 2019-03-31 | 2019-10-02 | 2020-09-30
20201123 | RICHMOND | 057 | FIRE DEPARTMENT | FD175W154 | WINDOW REPLACEMENT - EC154 | 2 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-04-01 | 2019-06-29 | 2020-10-01 | 2020-12-29
20201123 | RICHMOND | 057 | FIRE DEPARTMENT | FD175W166 | WINDOW REPLACEMENT - EC166 | 1 | CONSTRUCTION | 2018-04-01 | 2019-03-31 | 2019-10-02 | 2020-09-30
20201123 | RICHMOND | 057 | FIRE DEPARTMENT | FD175W166 | WINDOW REPLACEMENT - EC166 | 2 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-04-01 | 2019-06-29 | 2020-10-01 | 2020-12-29
20201123 | RICHMOND | 057 | FIRE DEPARTMENT | FR175G166 | Generator - EC166 | 1 | DESIGN | 2019-06-15 | 2019-12-11 | 2020-06-14 | 2020-12-10
20201123 | RICHMOND | 057 | FIRE DEPARTMENT | FR175G166 | Generator - EC166 | 2 | CONSTRUCTION | 2019-12-12 | 2020-12-10 | 2020-12-11 | 2021-12-10
20201123 | RICHMOND | 057 | FIRE DEPARTMENT | FR175G166 | Generator - EC166 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-12-11 | 2021-03-10 | 2021-12-11 | 2022-03-10
20201123 | RICHMOND | 071 | DEPT OF HOMELESS SERVICES | HH115HOBU | HOSPITALITY HOUSE BUILDING UPGRADE | 1 | DESIGN | 2022-01-01 | 2022-09-27 | 2022-01-01 | 2022-09-27
20201123 | RICHMOND | 071 | DEPT OF HOMELESS SERVICES | HH115HOBU | HOSPITALITY HOUSE BUILDING UPGRADE | 2 | BID AWARD AND REGISTER CONTRCT | 2022-09-28 | 2023-03-26 | 2022-09-28 | 2023-03-26
20201123 | RICHMOND | 071 | DEPT OF HOMELESS SERVICES | HH115HOBU | HOSPITALITY HOUSE BUILDING UPGRADE | 3 | CONSTRUCTION | 2023-03-27 | 2027-12-30 | 2023-03-27 | 2027-12-30
20201123 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV175CLOV | SIZ - Staten Island Zoo Clove Road Restoration | 1 | DEVELOP SCOPE | 2018-06-30 | 2019-06-30 | 2020-06-30 | 2021-06-30
20201123 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV175CLOV | SIZ - Staten Island Zoo Clove Road Restoration | 2 | PRELIMINARY DESIGN | 2019-07-01 | 2019-10-28 | 2021-07-01 | 2021-10-28
20201123 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV175CLOV | SIZ - Staten Island Zoo Clove Road Restoration | 3 | FINAL DESIGN | 2019-10-29 | 2020-04-25 | 2021-10-29 | 2022-04-26
20201123 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV175CLOV | SIZ - Staten Island Zoo Clove Road Restoration | 4 | BID AWARD AND REGISTER CONTRCT | 2020-04-26 | 2020-07-24 | 2022-04-27 | 2022-07-25
20201123 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV175CLOV | SIZ - Staten Island Zoo Clove Road Restoration | 5 | CONSTRUCTION TO 25% | 2020-07-25 | 2020-11-21 | 2022-07-26 | 2022-11-22
20201123 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV175CLOV | SIZ - Staten Island Zoo Clove Road Restoration | 6 | CONSTRUCTION TO 50% | 2020-11-22 | 2021-03-21 | 2022-11-23 | 2023-03-22
20201123 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV175CLOV | SIZ - Staten Island Zoo Clove Road Restoration | 7 | CONSTRUCTION TO 75% | 2021-03-22 | 2021-07-19 | 2023-03-23 | 2023-07-20
20201123 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV175CLOV | SIZ - Staten Island Zoo Clove Road Restoration | 8 | ORIGINAL EQUIP & FURNISHING | 2021-07-20 | 2021-10-17 | 2023-07-21 | 2023-10-18
20201123 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV175CLOV | SIZ - Staten Island Zoo Clove Road Restoration | 9 | SUBSTANTIAL COMPLETION | 2021-10-18 | 2021-12-16 | 2023-10-19 | 2023-12-17
20201123 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV175CLOV | SIZ - Staten Island Zoo Clove Road Restoration | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-12-17 | 2022-01-15 | 2023-12-18 | 2024-01-16
20201123 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV341CAR2 | SIHS - Carriage Barn Phase 2 | 1 | DEVELOP SCOPE | 2020-06-30 | 2020-09-27 | 2020-06-30 | 2020-09-27
20201123 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV341CAR2 | SIHS - Carriage Barn Phase 2 | 2 | PRELIMINARY DESIGN | 2020-09-28 | 2021-01-25 | 2020-09-28 | 2021-01-25
20201123 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV341CAR2 | SIHS - Carriage Barn Phase 2 | 3 | FINAL DESIGN | 2021-01-26 | 2021-07-24 | 2021-01-26 | 2021-07-24
20201123 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV341CAR2 | SIHS - Carriage Barn Phase 2 | 4 | BID AWARD AND REGISTER CONTRCT | 2021-07-25 | 2021-10-22 | 2021-07-25 | 2021-10-22
20201123 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV341CAR2 | SIHS - Carriage Barn Phase 2 | 5 | CONSTRUCTION TO 25% | 2021-10-23 | 2022-02-19 | 2021-10-23 | 2022-02-19
20201123 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV341CAR2 | SIHS - Carriage Barn Phase 2 | 6 | CONSTRUCTION TO 50% | 2022-02-20 | 2022-06-19 | 2022-02-20 | 2022-06-19
20201123 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV341CAR2 | SIHS - Carriage Barn Phase 2 | 7 | CONSTRUCTION TO 75% | 2022-06-20 | 2022-10-17 | 2022-06-20 | 2022-10-17
20201123 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV341CAR2 | SIHS - Carriage Barn Phase 2 | 8 | ORIGINAL EQUIP & FURNISHING | 2022-10-18 | 2023-01-15 | 2022-10-18 | 2023-01-15
20201123 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV341CAR2 | SIHS - Carriage Barn Phase 2 | 9 | SUBSTANTIAL COMPLETION | 2023-01-16 | 2023-03-16 | 2023-01-16 | 2023-03-16
20201123 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV341CAR2 | SIHS - Carriage Barn Phase 2 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-03-17 | 2023-04-15 | 2023-03-17 | 2023-04-15
20201123 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV341GALL | SIHS - Gallery Renovation | 1 | DEVELOP SCOPE | 2023-06-30 | 2023-09-27 | 2023-06-30 | 2023-09-27
20201123 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV341GALL | SIHS - Gallery Renovation | 2 | PRELIMINARY DESIGN | 2023-09-28 | 2024-01-25 | 2023-09-28 | 2024-01-25
20201123 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV341GALL | SIHS - Gallery Renovation | 3 | FINAL DESIGN | 2024-01-26 | 2024-07-23 | 2024-01-26 | 2024-07-23
20201123 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV341GALL | SIHS - Gallery Renovation | 4 | BID AWARD AND REGISTER CONTRCT | 2024-07-24 | 2024-10-21 | 2024-07-24 | 2024-10-21
20201123 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV341GALL | SIHS - Gallery Renovation | 5 | CONSTRUCTION TO 25% | 2024-10-22 | 2025-02-18 | 2024-10-22 | 2025-02-18
20201123 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV341GALL | SIHS - Gallery Renovation | 6 | CONSTRUCTION TO 50% | 2025-02-19 | 2025-06-18 | 2025-02-19 | 2025-06-18
20201123 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV341GALL | SIHS - Gallery Renovation | 7 | CONSTRUCTION TO 75% | 2025-06-19 | 2025-10-16 | 2025-06-19 | 2025-10-16
20201123 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV341GALL | SIHS - Gallery Renovation | 8 | ORIGINAL EQUIP & FURNISHING | 2025-10-17 | 2026-01-14 | 2025-10-17 | 2026-01-14
20201123 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV341GALL | SIHS - Gallery Renovation | 9 | SUBSTANTIAL COMPLETION | 2026-01-15 | 2026-03-15 | 2026-01-15 | 2026-03-15
20201123 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV341GALL | SIHS - Gallery Renovation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2026-03-16 | 2026-04-14 | 2026-03-16 | 2026-04-14
20201123 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV341SIPA | SIHS - Security System and Security Gates | 1 | DEVELOP SCOPE | 2023-06-30 | 2023-09-27 | 2023-06-30 | 2023-09-27
20201123 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV341SIPA | SIHS - Security System and Security Gates | 2 | PRELIMINARY DESIGN | 2023-09-28 | 2024-01-25 | 2023-09-28 | 2024-01-25
20201123 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV341SIPA | SIHS - Security System and Security Gates | 3 | FINAL DESIGN | 2024-01-26 | 2024-07-23 | 2024-01-26 | 2024-07-23
20201123 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV341SIPA | SIHS - Security System and Security Gates | 4 | BID AWARD AND REGISTER CONTRCT | 2024-07-24 | 2024-10-21 | 2024-07-24 | 2024-10-21
20201123 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV341SIPA | SIHS - Security System and Security Gates | 5 | CONSTRUCTION TO 25% | 2024-10-22 | 2025-02-18 | 2024-10-22 | 2025-02-18
20201123 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV341SIPA | SIHS - Security System and Security Gates | 6 | CONSTRUCTION TO 50% | 2025-02-19 | 2025-06-18 | 2025-02-19 | 2025-06-18
20201123 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV341SIPA | SIHS - Security System and Security Gates | 7 | CONSTRUCTION TO 75% | 2025-06-19 | 2025-10-16 | 2025-06-19 | 2025-10-16
20201123 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV341SIPA | SIHS - Security System and Security Gates | 8 | ORIGINAL EQUIP & FURNISHING | 2025-10-17 | 2026-01-14 | 2025-10-17 | 2026-01-14
20201123 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV341SIPA | SIHS - Security System and Security Gates | 9 | SUBSTANTIAL COMPLETION | 2026-01-15 | 2026-03-15 | 2026-01-15 | 2026-03-15
20201123 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV341SIPA | SIHS - Security System and Security Gates | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2026-03-16 | 2026-04-14 | 2026-03-16 | 2026-04-14
20201123 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV490-GOV | SHCC - SNUG HARBOR - Governor's House Exterior Renovation | 1 | DEVELOP SCOPE | 2023-06-30 | 2023-09-27 | 2022-01-12 | 2022-08-17
20201123 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV490-GOV | SHCC - SNUG HARBOR - Governor's House Exterior Renovation | 2 | PRELIMINARY DESIGN | 2023-09-28 | 2024-01-25 | 2023-02-01 | 2023-06-23
20201123 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV490-GOV | SHCC - SNUG HARBOR - Governor's House Exterior Renovation | 3 | FINAL DESIGN | 2024-01-26 | 2024-07-23 | 2023-06-24 | 2023-12-30
20201123 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV490-GOV | SHCC - SNUG HARBOR - Governor's House Exterior Renovation | 4 | BID AWARD AND REGISTER CONTRCT | 2024-07-24 | 2024-10-21 | 2023-12-31 | 2024-05-30
20201123 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV490-GOV | SHCC - SNUG HARBOR - Governor's House Exterior Renovation | 5 | CONSTRUCTION TO 25% | 2024-10-22 | 2025-02-18 | 2024-05-31 | 2024-12-16
20201123 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV490-GOV | SHCC - SNUG HARBOR - Governor's House Exterior Renovation | 6 | CONSTRUCTION TO 50% | 2025-02-19 | 2025-06-18 | 2024-12-17 | 2025-07-04
20201123 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV490-GOV | SHCC - SNUG HARBOR - Governor's House Exterior Renovation | 7 | CONSTRUCTION TO 75% | 2025-06-19 | 2025-10-16 | 2025-07-05 | 2026-01-20
20201123 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV490-GOV | SHCC - SNUG HARBOR - Governor's House Exterior Renovation | 8 | ORIGINAL EQUIP & FURNISHING | 2025-10-17 | 2026-01-14 | 2024-10-16 | 2025-01-13
20201123 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV490-GOV | SHCC - SNUG HARBOR - Governor's House Exterior Renovation | 9 | SUBSTANTIAL COMPLETION | 2026-01-15 | 2026-03-15 | 2025-01-14 | 2025-03-14
20201123 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV490-GOV | SHCC - SNUG HARBOR - Governor's House Exterior Renovation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2026-03-16 | 2026-04-14 | 2025-03-15 | 2025-04-13
20201123 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV490-K | SHCC - SNUG HARBOR - BLDG K Matrons House | 1 | DEVELOP SCOPE | 2020-09-14 | 2020-12-12 | 2020-09-14 | 2020-12-12
20201123 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV490-K | SHCC - SNUG HARBOR - BLDG K Matrons House | 2 | PRELIMINARY DESIGN | 2020-12-13 | 2021-04-11 | 2020-12-13 | 2021-04-11
20201123 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV490-K | SHCC - SNUG HARBOR - BLDG K Matrons House | 3 | FINAL DESIGN | 2021-04-12 | 2021-10-08 | 2021-04-12 | 2021-10-08
20201123 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV490-K | SHCC - SNUG HARBOR - BLDG K Matrons House | 4 | BID AWARD AND REGISTER CONTRCT | 2021-10-09 | 2022-01-06 | 2021-10-09 | 2022-01-06
20201123 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV490-K | SHCC - SNUG HARBOR - BLDG K Matrons House | 5 | CONSTRUCTION TO 25% | 2022-01-07 | 2022-05-06 | 2022-01-07 | 2022-05-06
20201123 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV490-K | SHCC - SNUG HARBOR - BLDG K Matrons House | 6 | CONSTRUCTION TO 50% | 2022-05-07 | 2022-09-03 | 2022-05-07 | 2022-09-03
20201123 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV490-K | SHCC - SNUG HARBOR - BLDG K Matrons House | 7 | CONSTRUCTION TO 75% | 2022-09-04 | 2023-01-01 | 2022-09-04 | 2023-01-01
20201123 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV490-K | SHCC - SNUG HARBOR - BLDG K Matrons House | 8 | ORIGINAL EQUIP & FURNISHING | 2023-01-02 | 2023-04-01 | 2023-01-02 | 2023-04-01
20201123 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV490-K | SHCC - SNUG HARBOR - BLDG K Matrons House | 9 | SUBSTANTIAL COMPLETION | 2023-04-02 | 2023-05-31 | 2023-04-02 | 2023-05-31
20201123 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV490-K | SHCC - SNUG HARBOR - BLDG K Matrons House | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-06-01 | 2023-06-30 | 2023-06-01 | 2023-06-30
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | ANNADALE | Annadale Road Streetscape Project - Infrastructure Reno | 1 | DESIGN | 2015-06-30 | 2015-07-19 | 2018-06-30 | 2018-07-19
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | ANNADALE | Annadale Road Streetscape Project - Infrastructure Reno | 2 | BID AWARD AND REGISTER CONTRCT | 2015-07-20 | 2015-08-03 | 2018-07-20 | 2018-08-03
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | ANNADALE | Annadale Road Streetscape Project - Infrastructure Reno | 3 | CONSTRUCTION | 2015-08-04 | 2015-09-07 | 2018-08-04 | 2018-09-07
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | ANNADALE | Annadale Road Streetscape Project - Infrastructure Reno | 4 | ORIGINAL EQUIP & FURNISHING | 2015-09-08 | 2015-09-17 | 2018-09-08 | 2018-09-17
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | ANNADALE | Annadale Road Streetscape Project - Infrastructure Reno | 5 | SUBSTANTIAL COMPLETION | 2015-09-18 | 2015-10-02 | 2018-09-18 | 2018-10-02
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | ANNADALE | Annadale Road Streetscape Project - Infrastructure Reno | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-10-03 | 2015-10-07 | 2018-10-03 | 2029-10-07
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | C5215AB2 | St. George Ferry Terminal | 1 | DEVELOP SCOPE | 2003-04-01 | 2003-06-29 | 1999-07-01 | 1999-07-20
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | C5215AB2 | St. George Ferry Terminal | 2 | PRELIMINARY DESIGN | 2003-06-30 | 2003-10-27 | 1999-07-21 | 1999-08-04
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | C5215AB2 | St. George Ferry Terminal | 3 | FINAL DESIGN | 2003-10-28 | 2007-07-01 | 1999-08-05 | 2022-06-30
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | C5215AB2 | St. George Ferry Terminal | 4 | BID AWARD AND REGISTER CONTRCT | 2007-07-02 | 2007-07-01 | 2022-07-01 | 2022-07-10
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | C5215AB2 | St. George Ferry Terminal | 5 | CONSTRUCTION TO 25% | 2007-07-02 | 2007-07-01 | 2022-07-11 | 2022-07-25
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | C5215AB2 | St. George Ferry Terminal | 6 | CONSTRUCTION TO 50% | 2007-07-02 | 2007-07-01 | 2022-07-26 | 2022-07-30
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | C5215AB2 | St. George Ferry Terminal | 7 | CONSTRUCTION TO 75% | 2007-07-02 | 2007-07-01 | 2022-07-26 | 2022-07-30
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | C5215AB2 | St. George Ferry Terminal | 8 | ORIGINAL EQUIP & FURNISHING | 2007-07-02 | 2007-07-01 | 2022-07-26 | 2022-07-30
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | C5215AB2 | St. George Ferry Terminal | 9 | SUBSTANTIAL COMPLETION | 2007-07-02 | 2007-07-01 | 2022-07-26 | 2022-07-30
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | C5215AB2 | St. George Ferry Terminal | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2007-07-02 | 2007-07-31 | 2022-07-26 | 2022-07-30
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | CMETENT | OCME Relocation of Disaster Cache Equipment to Fresh Kills | 1 | DESIGN | 2018-07-01 | 2018-07-20 | 2018-07-01 | 2018-07-20
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | CMETENT | OCME Relocation of Disaster Cache Equipment to Fresh Kills | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-21 | 2018-08-04 | 2018-07-21 | 2018-08-04
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | CMETENT | OCME Relocation of Disaster Cache Equipment to Fresh Kills | 3 | CONSTRUCTION | 2018-08-05 | 2018-09-08 | 2018-08-05 | 2018-09-08
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | CMETENT | OCME Relocation of Disaster Cache Equipment to Fresh Kills | 4 | ORIGINAL EQUIP & FURNISHING | 2018-09-09 | 2018-09-18 | 2018-09-09 | 2018-09-18
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | CMETENT | OCME Relocation of Disaster Cache Equipment to Fresh Kills | 5 | SUBSTANTIAL COMPLETION | 2018-09-19 | 2018-10-03 | 2018-09-19 | 2018-10-03
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | CMETENT | OCME Relocation of Disaster Cache Equipment to Fresh Kills | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-10-04 | 2018-10-08 | 2018-10-04 | 2021-06-30
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | FORESTAVE | FOREST AVENUE | 1 | DESIGN | 2019-07-01 | 2019-07-20 | 2019-07-01 | 2019-07-20
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | FORESTAVE | FOREST AVENUE | 2 | BID AWARD AND REGISTER CONTRCT | 2019-07-21 | 2019-08-04 | 2019-07-21 | 2019-08-04
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | FORESTAVE | FOREST AVENUE | 3 | CONSTRUCTION | 2019-08-05 | 2019-09-08 | 2019-08-05 | 2019-09-08
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | FORESTAVE | FOREST AVENUE | 4 | ORIGINAL EQUIP & FURNISHING | 2019-09-09 | 2019-09-18 | 2019-09-09 | 2019-09-18
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | FORESTAVE | FOREST AVENUE | 5 | SUBSTANTIAL COMPLETION | 2019-09-19 | 2021-10-03 | 2019-09-19 | 2021-10-03
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | FORESTAVE | FOREST AVENUE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-10-04 | 2021-10-08 | 2021-10-04 | 2025-06-30
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | GE-343 | Replacement of Siphons b/t Brooklyn & SI | 1 | DESIGN | 2005-01-01 | 2007-03-01 | 2005-01-01 | 2007-03-01
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | GE-343 | Replacement of Siphons b/t Brooklyn & SI | 2 | BID AWARD AND REGISTER CONTRCT | 2007-03-02 | 2007-03-01 | 2007-03-02 | 2007-03-01
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | GE-343 | Replacement of Siphons b/t Brooklyn & SI | 3 | CONSTRUCTION | 2007-07-01 | 2009-08-01 | 2007-07-01 | 2009-08-01
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | GE-343 | Replacement of Siphons b/t Brooklyn & SI | 4 | ORIGINAL EQUIP & FURNISHING | 2009-08-02 | 2009-08-01 | 2009-08-02 | 2009-08-01
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | GE-343 | Replacement of Siphons b/t Brooklyn & SI | 5 | SUBSTANTIAL COMPLETION | 2009-08-02 | 2009-08-01 | 2009-08-02 | 2017-06-30
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | GE-343 | Replacement of Siphons b/t Brooklyn & SI | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2009-08-02 | 2009-08-06 | 2017-07-01 | 2021-06-29
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | HIFNSW | HIF - New Stapleton Waterfront | 1 | DESIGN | 2019-07-01 | 2022-07-20 | 2019-07-01 | 2022-07-20
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | HIFNSW | HIF - New Stapleton Waterfront | 2 | BID AWARD AND REGISTER CONTRCT | 2022-07-21 | 2022-08-04 | 2022-07-21 | 2022-08-04
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | HIFNSW | HIF - New Stapleton Waterfront | 3 | CONSTRUCTION | 2022-08-05 | 2022-09-08 | 2022-08-05 | 2022-09-08
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | HIFNSW | HIF - New Stapleton Waterfront | 4 | ORIGINAL EQUIP & FURNISHING | 2022-09-09 | 2022-09-18 | 2022-09-09 | 2022-09-18
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | HIFNSW | HIF - New Stapleton Waterfront | 5 | SUBSTANTIAL COMPLETION | 2022-09-19 | 2022-10-03 | 2022-09-19 | 2022-10-03
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | HIFNSW | HIF - New Stapleton Waterfront | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-10-04 | 2022-10-08 | 2022-10-04 | 2029-06-30
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | HOMEPORT2 | Stapleton Waterfront Phase II & III | 1 | DESIGN | 2015-06-30 | 2015-07-19 | 2015-06-30 | 2018-07-19
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | HOMEPORT2 | Stapleton Waterfront Phase II & III | 2 | BID AWARD AND REGISTER CONTRCT | 2015-07-20 | 2015-08-03 | 2018-07-20 | 2018-08-03
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | HOMEPORT2 | Stapleton Waterfront Phase II & III | 3 | CONSTRUCTION | 2015-08-04 | 2015-09-07 | 2018-08-04 | 2018-09-07
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | HOMEPORT2 | Stapleton Waterfront Phase II & III | 4 | ORIGINAL EQUIP & FURNISHING | 2015-09-08 | 2015-09-17 | 2018-09-08 | 2018-09-17
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | HOMEPORT2 | Stapleton Waterfront Phase II & III | 5 | SUBSTANTIAL COMPLETION | 2015-09-18 | 2015-10-02 | 2018-09-18 | 2018-10-02
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | HOMEPORT2 | Stapleton Waterfront Phase II & III | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-10-03 | 2015-10-07 | 2018-10-03 | 2028-06-30
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | HWRLASEWF | Lipsett Avenue Street End (Waterfront) | 1 | DEVELOP SCOPE | 2018-06-30 | 2018-09-27 | 2018-06-30 | 2018-09-27
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | HWRLASEWF | Lipsett Avenue Street End (Waterfront) | 2 | PRELIMINARY DESIGN | 2018-09-28 | 2019-01-25 | 2018-09-28 | 2019-01-25
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | HWRLASEWF | Lipsett Avenue Street End (Waterfront) | 3 | FINAL DESIGN | 2019-01-26 | 2019-07-24 | 2019-01-26 | 2019-07-24
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | HWRLASEWF | Lipsett Avenue Street End (Waterfront) | 4 | BID AWARD AND REGISTER CONTRCT | 2019-07-25 | 2019-10-22 | 2019-07-25 | 2019-10-22
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | HWRLASEWF | Lipsett Avenue Street End (Waterfront) | 5 | CONSTRUCTION TO 25% | 2019-10-23 | 2020-02-19 | 2019-10-23 | 2020-02-19
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | HWRLASEWF | Lipsett Avenue Street End (Waterfront) | 6 | CONSTRUCTION TO 50% | 2020-02-20 | 2020-06-18 | 2020-02-20 | 2020-06-18
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | HWRLASEWF | Lipsett Avenue Street End (Waterfront) | 7 | CONSTRUCTION TO 75% | 2020-06-19 | 2020-10-16 | 2020-06-19 | 2025-01-01
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | HWRLASEWF | Lipsett Avenue Street End (Waterfront) | 8 | ORIGINAL EQUIP & FURNISHING | 2020-10-17 | 2021-01-14 | 2025-01-02 | 2025-04-01
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | HWRLASEWF | Lipsett Avenue Street End (Waterfront) | 9 | SUBSTANTIAL COMPLETION | 2021-01-15 | 2021-03-15 | 2025-04-02 | 2025-05-31
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | HWRLASEWF | Lipsett Avenue Street End (Waterfront) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-16 | 2021-04-14 | 2025-06-01 | 2025-06-30
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | LIGHTHOUS | National Lighthouse Museum | 1 | DESIGN | 2000-07-01 | 2000-07-20 | 1998-06-01 | 1998-06-20
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | LIGHTHOUS | National Lighthouse Museum | 2 | BID AWARD AND REGISTER CONTRCT | 2000-07-21 | 2000-08-04 | 1998-06-21 | 1998-07-05
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | LIGHTHOUS | National Lighthouse Museum | 3 | CONSTRUCTION | 2000-08-05 | 2007-06-30 | 1998-07-06 | 2021-08-09
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | LIGHTHOUS | National Lighthouse Museum | 4 | ORIGINAL EQUIP & FURNISHING | 2007-07-01 | 2007-06-30 | 2021-08-10 | 2021-08-19
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | LIGHTHOUS | National Lighthouse Museum | 5 | SUBSTANTIAL COMPLETION | 2007-07-01 | 2007-06-30 | 2021-08-20 | 2021-09-03
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | LIGHTHOUS | National Lighthouse Museum | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2007-07-01 | 2007-06-30 | 2021-09-04 | 2024-09-08
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | LIGHTHOUS | National Lighthouse Museum | 7 | DEVELOP SCOPE | 2007-07-01 | 2007-06-30 | 2021-09-04 | 2024-09-08
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | LIGHTHOUS | National Lighthouse Museum | 8 | PRELIMINARY DESIGN | 2007-07-01 | 2007-06-30 | 2021-09-04 | 2024-09-08
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | LIGHTHOUS | National Lighthouse Museum | 9 | FINAL DESIGN | 2007-07-01 | 2007-06-30 | 2021-09-04 | 2024-09-08
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | LIGHTHOUS | National Lighthouse Museum | 10 | BID AWARD AND REGISTER CONTRCT | 2007-07-01 | 2007-06-30 | 2021-09-04 | 2024-09-08
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | LIGHTHOUS | National Lighthouse Museum | 11 | CONSTRUCTION TO 25% | 2007-07-01 | 2007-06-30 | 2021-09-04 | 2024-09-08
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | LIGHTHOUS | National Lighthouse Museum | 12 | CONSTRUCTION TO 50% | 2007-07-01 | 2007-06-30 | 2021-09-04 | 2024-09-08
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | LIGHTHOUS | National Lighthouse Museum | 13 | CONSTRUCTION TO 75% | 2007-07-01 | 2007-06-30 | 2021-09-04 | 2024-09-08
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | LIGHTHOUS | National Lighthouse Museum | 14 | ORIGINAL EQUIP & FURNISHING | 2007-07-01 | 2007-06-30 | 2021-09-04 | 2024-09-08
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | LIGHTHOUS | National Lighthouse Museum | 15 | SUBSTANTIAL COMPLETION | 2007-07-01 | 2007-06-30 | 2021-09-04 | 2024-09-08
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | LIGHTHOUS | National Lighthouse Museum | 16 | PUNCHLIST COMPLETE, JOB CLOSED | 2007-07-01 | 2007-07-30 | 2021-09-04 | 2024-09-08
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | LNC018CHA | CHARLESTON - Site Acquisition and New Branch Construction | 1 | DESIGN | 2017-07-01 | 2017-07-20 | 2017-07-01 | 2017-07-20
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | LNC018CHA | CHARLESTON - Site Acquisition and New Branch Construction | 2 | BID AWARD AND REGISTER CONTRCT | 2017-07-21 | 2017-08-04 | 2017-07-21 | 2017-08-04
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | LNC018CHA | CHARLESTON - Site Acquisition and New Branch Construction | 3 | CONSTRUCTION | 2017-08-05 | 2017-09-08 | 2017-08-05 | 2017-09-08
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | LNC018CHA | CHARLESTON - Site Acquisition and New Branch Construction | 4 | ORIGINAL EQUIP & FURNISHING | 2017-09-09 | 2017-09-18 | 2017-09-09 | 2017-09-18
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | LNC018CHA | CHARLESTON - Site Acquisition and New Branch Construction | 5 | SUBSTANTIAL COMPLETION | 2017-09-19 | 2017-10-03 | 2017-09-19 | 2017-10-03
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | LNC018CHA | CHARLESTON - Site Acquisition and New Branch Construction | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-10-04 | 2017-10-08 | 2017-10-04 | 2022-10-08
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | LNEA16PRT | PORT RICHMOND: MAJOR RENOVATION | 1 | DESIGN | 2016-08-01 | 2017-01-27 | 2016-08-01 | 2017-01-27
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | LNEA16PRT | PORT RICHMOND: MAJOR RENOVATION | 2 | BID AWARD AND REGISTER CONTRCT | 2017-01-28 | 2017-04-27 | 2017-01-28 | 2017-04-27
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | LNEA16PRT | PORT RICHMOND: MAJOR RENOVATION | 3 | CONSTRUCTION | 2017-04-28 | 2018-04-27 | 2017-04-28 | 2020-04-27
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | LNEA16PRT | PORT RICHMOND: MAJOR RENOVATION | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-04-28 | 2019-02-21 | 2020-04-28 | 2022-02-21
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | PWDSIBPCT | Van for the Staten Island Borough President's Clean Team -- | 1 | DESIGN | 2015-06-30 | 2015-07-19 | 2015-06-30 | 2015-07-19
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | PWDSIBPCT | Van for the Staten Island Borough President's Clean Team -- | 2 | BID AWARD AND REGISTER CONTRCT | 2015-07-20 | 2015-08-03 | 2015-07-20 | 2015-08-03
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | PWDSIBPCT | Van for the Staten Island Borough President's Clean Team -- | 3 | CONSTRUCTION | 2015-08-04 | 2015-09-07 | 2015-08-04 | 2015-09-07
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | PWDSIBPCT | Van for the Staten Island Borough President's Clean Team -- | 4 | ORIGINAL EQUIP & FURNISHING | 2015-09-08 | 2015-09-17 | 2015-09-08 | 2015-09-17
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | PWDSIBPCT | Van for the Staten Island Borough President's Clean Team -- | 5 | SUBSTANTIAL COMPLETION | 2015-09-18 | 2015-10-02 | 2015-09-18 | 2015-10-02
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | PWDSIBPCT | Van for the Staten Island Borough President's Clean Team -- | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-10-03 | 2015-10-07 | 2015-10-03 | 2023-10-07
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | RCBBALLPK | RICHMOND COUNTY BANK BALLPARK AT ST. GEORGE | 1 | DESIGN | 2019-07-01 | 2019-07-20 | 2019-07-01 | 2019-07-20
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | RCBBALLPK | RICHMOND COUNTY BANK BALLPARK AT ST. GEORGE | 2 | BID AWARD AND REGISTER CONTRCT | 2019-07-21 | 2019-08-04 | 2019-07-21 | 2019-08-04
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | RCBBALLPK | RICHMOND COUNTY BANK BALLPARK AT ST. GEORGE | 3 | CONSTRUCTION | 2019-08-05 | 2019-09-08 | 2019-08-05 | 2019-09-08
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | RCBBALLPK | RICHMOND COUNTY BANK BALLPARK AT ST. GEORGE | 4 | ORIGINAL EQUIP & FURNISHING | 2019-09-09 | 2019-09-18 | 2019-09-09 | 2019-09-18
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | RCBBALLPK | RICHMOND COUNTY BANK BALLPARK AT ST. GEORGE | 5 | SUBSTANTIAL COMPLETION | 2019-09-19 | 2021-10-03 | 2019-09-19 | 2021-10-03
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | RCBBALLPK | RICHMOND COUNTY BANK BALLPARK AT ST. GEORGE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-10-04 | 2021-10-08 | 2021-10-04 | 2024-10-08
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDEDCG5 | Tompkinsville Esplanade - FEMA 428 Group 5 | 1 | DESIGN | 2016-07-01 | 2016-07-20 | 2019-07-01 | 2019-07-20
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDEDCG5 | Tompkinsville Esplanade - FEMA 428 Group 5 | 2 | BID AWARD AND REGISTER CONTRCT | 2016-07-21 | 2016-08-04 | 2019-07-21 | 2019-08-04
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDEDCG5 | Tompkinsville Esplanade - FEMA 428 Group 5 | 3 | CONSTRUCTION | 2016-08-05 | 2016-09-08 | 2019-08-05 | 2019-09-08
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDEDCG5 | Tompkinsville Esplanade - FEMA 428 Group 5 | 4 | ORIGINAL EQUIP & FURNISHING | 2016-09-09 | 2016-09-18 | 2019-09-09 | 2019-09-18
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDEDCG5 | Tompkinsville Esplanade - FEMA 428 Group 5 | 5 | SUBSTANTIAL COMPLETION | 2016-09-19 | 2016-10-03 | 2019-09-19 | 2019-10-03
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDEDCG5 | Tompkinsville Esplanade - FEMA 428 Group 5 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-10-04 | 2016-10-08 | 2019-10-04 | 2023-10-08
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDG1HP | FEMA 428 G1 - Homeport Pier | 1 | DESIGN | 2016-07-01 | 2016-07-20 | 2016-07-01 | 2016-07-20
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDG1HP | FEMA 428 G1 - Homeport Pier | 2 | BID AWARD AND REGISTER CONTRCT | 2016-07-21 | 2016-08-04 | 2016-07-21 | 2016-08-04
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDG1HP | FEMA 428 G1 - Homeport Pier | 3 | CONSTRUCTION | 2016-08-05 | 2016-09-08 | 2016-08-05 | 2016-09-08
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDG1HP | FEMA 428 G1 - Homeport Pier | 4 | ORIGINAL EQUIP & FURNISHING | 2016-09-09 | 2016-09-18 | 2016-09-09 | 2016-09-18
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDG1HP | FEMA 428 G1 - Homeport Pier | 5 | SUBSTANTIAL COMPLETION | 2016-09-19 | 2016-10-03 | 2016-09-19 | 2016-10-03
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDG1HP | FEMA 428 G1 - Homeport Pier | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-10-04 | 2016-10-08 | 2016-10-04 | 2024-10-08
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDG1HS | FEMA 428 G1 - Homeport Substation | 1 | DESIGN | 2016-07-01 | 2016-07-20 | 2019-07-01 | 2019-07-20
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDG1HS | FEMA 428 G1 - Homeport Substation | 2 | BID AWARD AND REGISTER CONTRCT | 2016-07-21 | 2016-08-04 | 2019-07-21 | 2019-08-04
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDG1HS | FEMA 428 G1 - Homeport Substation | 3 | CONSTRUCTION | 2016-08-05 | 2016-09-08 | 2019-08-05 | 2019-09-08
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDG1HS | FEMA 428 G1 - Homeport Substation | 4 | ORIGINAL EQUIP & FURNISHING | 2016-09-09 | 2016-09-18 | 2019-09-09 | 2019-09-18
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDG1HS | FEMA 428 G1 - Homeport Substation | 5 | SUBSTANTIAL COMPLETION | 2016-09-19 | 2016-10-03 | 2019-09-19 | 2019-10-03
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDG1HS | FEMA 428 G1 - Homeport Substation | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-10-04 | 2016-10-08 | 2019-10-04 | 2022-10-08
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDG4DOC | FEMA 428 G4- DOCKBUILDERS | 1 | DESIGN | 2016-07-01 | 2016-07-20 | 2019-03-24 | 2019-04-12
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDG4DOC | FEMA 428 G4- DOCKBUILDERS | 2 | BID AWARD AND REGISTER CONTRCT | 2016-07-21 | 2016-08-04 | 2019-04-13 | 2019-04-27
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDG4DOC | FEMA 428 G4- DOCKBUILDERS | 3 | CONSTRUCTION | 2016-08-05 | 2016-09-08 | 2019-04-28 | 2019-06-01
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDG4DOC | FEMA 428 G4- DOCKBUILDERS | 4 | ORIGINAL EQUIP & FURNISHING | 2016-09-09 | 2016-09-18 | 2019-06-02 | 2019-06-11
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDG4DOC | FEMA 428 G4- DOCKBUILDERS | 5 | SUBSTANTIAL COMPLETION | 2016-09-19 | 2016-10-03 | 2019-06-12 | 2019-06-26
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDG4DOC | FEMA 428 G4- DOCKBUILDERS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-10-04 | 2016-10-08 | 2019-06-27 | 2022-06-30
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDHOME | Repairs to Homeport as a result of Hurricane Sandy | 1 | DESIGN | 2015-06-30 | 2015-07-19 | 2018-06-30 | 2018-07-19
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDHOME | Repairs to Homeport as a result of Hurricane Sandy | 2 | BID AWARD AND REGISTER CONTRCT | 2015-07-20 | 2015-08-03 | 2018-07-20 | 2018-08-03
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDHOME | Repairs to Homeport as a result of Hurricane Sandy | 3 | CONSTRUCTION | 2015-08-04 | 2015-09-07 | 2018-08-04 | 2018-09-07
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDHOME | Repairs to Homeport as a result of Hurricane Sandy | 4 | ORIGINAL EQUIP & FURNISHING | 2015-09-08 | 2015-09-17 | 2018-09-08 | 2018-09-17
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDHOME | Repairs to Homeport as a result of Hurricane Sandy | 5 | SUBSTANTIAL COMPLETION | 2015-09-18 | 2015-10-02 | 2018-09-18 | 2018-10-02
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDHOME | Repairs to Homeport as a result of Hurricane Sandy | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-10-03 | 2015-10-07 | 2018-10-03 | 2024-10-07
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDSIHP2 | Stapleton Waterfront Phase II & III - Sandy Repairs | 1 | DESIGN | 2018-07-01 | 2018-07-20 | 2018-07-01 | 2018-07-20
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDSIHP2 | Stapleton Waterfront Phase II & III - Sandy Repairs | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-21 | 2018-08-04 | 2018-07-21 | 2018-08-04
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDSIHP2 | Stapleton Waterfront Phase II & III - Sandy Repairs | 3 | CONSTRUCTION | 2018-08-05 | 2018-09-08 | 2018-08-05 | 2018-09-08
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDSIHP2 | Stapleton Waterfront Phase II & III - Sandy Repairs | 4 | ORIGINAL EQUIP & FURNISHING | 2018-09-09 | 2018-09-18 | 2018-09-09 | 2018-09-18
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDSIHP2 | Stapleton Waterfront Phase II & III - Sandy Repairs | 5 | SUBSTANTIAL COMPLETION | 2018-09-19 | 2018-10-03 | 2018-09-19 | 2018-10-03
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDSIHP2 | Stapleton Waterfront Phase II & III - Sandy Repairs | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-10-04 | 2018-10-08 | 2018-10-04 | 2021-10-08
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDSMC | Hurricane Sandy - Saw Mill Creek Marsh Restoration | 1 | DESIGN | 2016-01-01 | 2016-01-20 | 2016-01-01 | 2016-01-20
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDSMC | Hurricane Sandy - Saw Mill Creek Marsh Restoration | 2 | BID AWARD AND REGISTER CONTRCT | 2016-01-21 | 2016-06-30 | 2016-01-21 | 2016-06-30
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDSMC | Hurricane Sandy - Saw Mill Creek Marsh Restoration | 3 | CONSTRUCTION | 2016-07-01 | 2017-06-30 | 2016-07-01 | 2017-06-30
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDSMC | Hurricane Sandy - Saw Mill Creek Marsh Restoration | 4 | ORIGINAL EQUIP & FURNISHING | 2017-07-01 | 2020-06-30 | 2017-07-01 | 2020-06-30
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDSMC | Hurricane Sandy - Saw Mill Creek Marsh Restoration | 5 | SUBSTANTIAL COMPLETION | 2020-07-01 | 2020-06-30 | 2020-07-01 | 2020-06-30
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDSMC | Hurricane Sandy - Saw Mill Creek Marsh Restoration | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-07-01 | 2020-07-05 | 2020-07-01 | 2020-07-05
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SEAVIEW | FA - Seaview Senior Housing - Met Council | 1 | DESIGN | 2008-09-30 | 2010-10-19 | 2008-09-30 | 2010-10-19
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SEAVIEW | FA - Seaview Senior Housing - Met Council | 2 | BID AWARD AND REGISTER CONTRCT | 2010-10-20 | 2010-10-19 | 2010-10-20 | 2010-10-19
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SEAVIEW | FA - Seaview Senior Housing - Met Council | 3 | CONSTRUCTION | 2010-10-20 | 2012-10-19 | 2010-10-20 | 2019-06-30
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SEAVIEW | FA - Seaview Senior Housing - Met Council | 4 | ORIGINAL EQUIP & FURNISHING | 2012-10-20 | 2012-10-19 | 2019-07-01 | 2019-06-30
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SEAVIEW | FA - Seaview Senior Housing - Met Council | 5 | SUBSTANTIAL COMPLETION | 2012-10-20 | 2012-10-19 | 2019-07-01 | 2019-06-30
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SEAVIEW | FA - Seaview Senior Housing - Met Council | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-10-20 | 2012-10-24 | 2019-07-01 | 2021-07-05
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SIBULK | Sandy Staten Island Esplanade Emergency Bulkhead Work | 1 | DESIGN | 2011-06-30 | 2011-07-19 | 2014-06-30 | 2014-07-19
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SIBULK | Sandy Staten Island Esplanade Emergency Bulkhead Work | 2 | BID AWARD AND REGISTER CONTRCT | 2011-07-20 | 2011-08-03 | 2014-07-20 | 2014-08-03
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SIBULK | Sandy Staten Island Esplanade Emergency Bulkhead Work | 3 | CONSTRUCTION | 2011-08-04 | 2011-09-07 | 2014-08-04 | 2020-06-30
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SIBULK | Sandy Staten Island Esplanade Emergency Bulkhead Work | 4 | ORIGINAL EQUIP & FURNISHING | 2011-09-08 | 2011-09-17 | 2020-07-01 | 2020-06-30
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SIBULK | Sandy Staten Island Esplanade Emergency Bulkhead Work | 5 | SUBSTANTIAL COMPLETION | 2011-09-18 | 2012-09-30 | 2020-07-01 | 2020-06-30
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SIBULK | Sandy Staten Island Esplanade Emergency Bulkhead Work | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-10-01 | 2012-10-05 | 2020-07-01 | 2025-07-05
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SIESPLAND | Staten Island North Shore Esplanade | 1 | DESIGN | 2000-07-01 | 2000-07-20 | 1920-03-17 | 1920-07-08
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SIESPLAND | Staten Island North Shore Esplanade | 2 | BID AWARD AND REGISTER CONTRCT | 2000-07-21 | 2000-08-04 | 2011-04-01 | 2011-07-01
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SIESPLAND | Staten Island North Shore Esplanade | 3 | CONSTRUCTION | 2000-08-05 | 2007-06-30 | 2011-07-02 | 2014-12-31
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SIESPLAND | Staten Island North Shore Esplanade | 4 | ORIGINAL EQUIP & FURNISHING | 2007-07-01 | 2007-06-30 | 2015-01-01 | 2014-12-31
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SIESPLAND | Staten Island North Shore Esplanade | 5 | SUBSTANTIAL COMPLETION | 2007-07-01 | 2007-06-30 | 2015-01-01 | 2014-12-31
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SIESPLAND | Staten Island North Shore Esplanade | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2007-07-01 | 2007-07-05 | 2014-12-07 | 2024-06-30
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SIHOMEPT | Staten Island Homeport Emergency Bulkhead Work | 1 | DESIGN | 2011-12-01 | 2011-12-20 | 2014-12-01 | 2014-12-20
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SIHOMEPT | Staten Island Homeport Emergency Bulkhead Work | 2 | BID AWARD AND REGISTER CONTRCT | 2011-12-21 | 2012-01-04 | 2014-12-21 | 2015-01-04
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SIHOMEPT | Staten Island Homeport Emergency Bulkhead Work | 3 | CONSTRUCTION | 2012-01-05 | 2012-02-08 | 2015-01-05 | 2020-06-30
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SIHOMEPT | Staten Island Homeport Emergency Bulkhead Work | 4 | ORIGINAL EQUIP & FURNISHING | 2012-02-09 | 2012-02-18 | 2020-07-01 | 2020-06-30
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SIHOMEPT | Staten Island Homeport Emergency Bulkhead Work | 5 | SUBSTANTIAL COMPLETION | 2012-02-19 | 2012-09-30 | 2020-07-01 | 2020-06-30
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SIHOMEPT | Staten Island Homeport Emergency Bulkhead Work | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-10-01 | 2012-10-05 | 2020-07-01 | 2025-07-05
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SIOUTLET | Staten Island Empire Outlets | 1 | DESIGN | 2014-07-01 | 2014-07-20 | 2016-06-30 | 2016-07-19
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SIOUTLET | Staten Island Empire Outlets | 2 | BID AWARD AND REGISTER CONTRCT | 2014-07-21 | 2014-08-04 | 2016-07-20 | 2016-08-03
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SIOUTLET | Staten Island Empire Outlets | 3 | CONSTRUCTION | 2014-08-05 | 2014-09-08 | 2016-08-04 | 2016-09-07
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SIOUTLET | Staten Island Empire Outlets | 4 | ORIGINAL EQUIP & FURNISHING | 2014-09-09 | 2014-09-18 | 2016-09-08 | 2016-09-17
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SIOUTLET | Staten Island Empire Outlets | 5 | SUBSTANTIAL COMPLETION | 2014-09-19 | 2014-10-03 | 2016-09-18 | 2016-10-02
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SIOUTLET | Staten Island Empire Outlets | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-10-04 | 2014-10-08 | 2016-10-03 | 2023-06-30
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SIPIER1A | Staten Island Pier 1 Rehabilitation | 1 | DESIGN | 2008-09-30 | 2010-10-19 | 2017-09-30 | 2019-10-19
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SIPIER1A | Staten Island Pier 1 Rehabilitation | 2 | BID AWARD AND REGISTER CONTRCT | 2010-10-20 | 2010-10-19 | 2019-10-20 | 2019-10-19
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SIPIER1A | Staten Island Pier 1 Rehabilitation | 3 | CONSTRUCTION | 2010-10-20 | 2012-10-19 | 2019-10-20 | 2021-10-19
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SIPIER1A | Staten Island Pier 1 Rehabilitation | 4 | ORIGINAL EQUIP & FURNISHING | 2012-10-20 | 2012-10-19 | 2021-10-20 | 2021-10-19
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SIPIER1A | Staten Island Pier 1 Rehabilitation | 5 | SUBSTANTIAL COMPLETION | 2012-10-20 | 2012-10-19 | 2021-10-20 | 2021-10-19
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SIPIER1A | Staten Island Pier 1 Rehabilitation | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-10-20 | 2012-10-24 | 2021-10-20 | 2023-10-24
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SIWHEEL | St. George Improvements | 1 | DESIGN | 2014-07-01 | 2014-07-20 | 2015-07-01 | 2015-07-20
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SIWHEEL | St. George Improvements | 2 | BID AWARD AND REGISTER CONTRCT | 2014-07-21 | 2014-08-04 | 2015-07-21 | 2015-08-04
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SIWHEEL | St. George Improvements | 3 | CONSTRUCTION | 2014-08-05 | 2014-09-08 | 2015-08-05 | 2015-09-08
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SIWHEEL | St. George Improvements | 4 | ORIGINAL EQUIP & FURNISHING | 2014-09-09 | 2014-09-18 | 2015-09-09 | 2015-09-18
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SIWHEEL | St. George Improvements | 5 | SUBSTANTIAL COMPLETION | 2014-09-19 | 2014-10-03 | 2015-09-19 | 2015-10-03
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SIWHEEL | St. George Improvements | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-10-04 | 2014-10-08 | 2015-10-04 | 2027-06-30
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | STGRGEFIT | St. George Ferry Terminal - Fit Out | 1 | DESIGN | 2013-09-30 | 2013-10-19 | 2015-09-30 | 2015-10-19
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | STGRGEFIT | St. George Ferry Terminal - Fit Out | 2 | BID AWARD AND REGISTER CONTRCT | 2013-10-20 | 2013-11-03 | 2015-10-20 | 2015-11-03
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | STGRGEFIT | St. George Ferry Terminal - Fit Out | 3 | CONSTRUCTION | 2014-01-30 | 2014-03-05 | 2014-01-30 | 2014-03-05
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | STGRGEFIT | St. George Ferry Terminal - Fit Out | 4 | ORIGINAL EQUIP & FURNISHING | 2014-03-06 | 2014-03-05 | 2014-03-06 | 2014-03-05
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | STGRGEFIT | St. George Ferry Terminal - Fit Out | 5 | SUBSTANTIAL COMPLETION | 2014-03-06 | 2014-03-05 | 2014-03-06 | 2019-03-05
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | STGRGEFIT | St. George Ferry Terminal - Fit Out | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-03-06 | 2014-03-10 | 2019-03-06 | 2022-06-30
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | STGSECURE | St. George Ferry Terminal - Security | 1 | DESIGN | 2004-11-01 | 2006-08-15 | 2016-10-29 | 2018-08-12
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | STGSECURE | St. George Ferry Terminal - Security | 2 | BID AWARD AND REGISTER CONTRCT | 2006-08-16 | 2006-08-15 | 2018-08-13 | 2018-08-12
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | STGSECURE | St. George Ferry Terminal - Security | 3 | CONSTRUCTION | 2006-11-01 | 2007-11-01 | 2006-11-01 | 2007-11-01
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | STGSECURE | St. George Ferry Terminal - Security | 4 | ORIGINAL EQUIP & FURNISHING | 2007-11-02 | 2007-11-01 | 2007-11-02 | 2007-11-01
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | STGSECURE | St. George Ferry Terminal - Security | 5 | SUBSTANTIAL COMPLETION | 2007-11-02 | 2007-11-01 | 2007-11-02 | 2019-11-01
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | STGSECURE | St. George Ferry Terminal - Security | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2007-11-02 | 2007-11-06 | 2019-11-02 | 2029-06-30
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SVIEWDIAB | Sea View Diabetes Center | 1 | DESIGN | 2021-06-30 | 2021-07-20 | 2021-06-30 | 2021-07-20
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SVIEWDIAB | Sea View Diabetes Center | 2 | BID AWARD AND REGISTER CONTRCT | 2021-07-21 | 2021-08-04 | 2021-07-21 | 2021-08-04
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SVIEWDIAB | Sea View Diabetes Center | 3 | CONSTRUCTION | 2021-08-05 | 2021-09-08 | 2021-08-05 | 2021-09-08
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SVIEWDIAB | Sea View Diabetes Center | 4 | ORIGINAL EQUIP & FURNISHING | 2021-09-09 | 2021-09-18 | 2021-09-09 | 2021-09-18
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SVIEWDIAB | Sea View Diabetes Center | 5 | SUBSTANTIAL COMPLETION | 2021-09-19 | 2021-10-03 | 2021-09-19 | 2021-10-03
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SVIEWDIAB | Sea View Diabetes Center | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-10-04 | 2023-06-30 | 2021-10-04 | 2027-06-30
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | TOTTENCBD | Tottenville Central Business District | 1 | DESIGN | 2000-07-01 | 2000-07-20 | 2002-06-30 | 2002-08-30
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | TOTTENCBD | Tottenville Central Business District | 2 | BID AWARD AND REGISTER CONTRCT | 2000-07-21 | 2000-08-04 | 2002-08-31 | 2002-08-30
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | TOTTENCBD | Tottenville Central Business District | 3 | CONSTRUCTION | 2000-08-05 | 2007-06-30 | 2005-06-30 | 2005-07-30
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | TOTTENCBD | Tottenville Central Business District | 4 | ORIGINAL EQUIP & FURNISHING | 2007-07-01 | 2007-06-30 | 2005-07-31 | 2005-07-30
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | TOTTENCBD | Tottenville Central Business District | 5 | SUBSTANTIAL COMPLETION | 2007-07-01 | 2007-06-30 | 2005-07-31 | 2007-07-30
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | TOTTENCBD | Tottenville Central Business District | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2007-07-01 | 2007-07-05 | 2007-07-31 | 2028-06-30
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | TRAVLIFT | Travis Avenue Lift Project -- Elevating section of Travis Av | 1 | DESIGN | 2022-01-01 | 2022-01-20 | 2022-01-01 | 2022-01-20
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | TRAVLIFT | Travis Avenue Lift Project -- Elevating section of Travis Av | 2 | BID AWARD AND REGISTER CONTRCT | 2022-01-21 | 2022-02-04 | 2022-01-21 | 2022-02-04
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | TRAVLIFT | Travis Avenue Lift Project -- Elevating section of Travis Av | 3 | CONSTRUCTION | 2022-02-05 | 2022-03-11 | 2022-02-05 | 2022-03-11
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | TRAVLIFT | Travis Avenue Lift Project -- Elevating section of Travis Av | 4 | ORIGINAL EQUIP & FURNISHING | 2022-03-12 | 2022-03-21 | 2022-03-12 | 2022-03-21
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | TRAVLIFT | Travis Avenue Lift Project -- Elevating section of Travis Av | 5 | SUBSTANTIAL COMPLETION | 2022-03-22 | 2022-04-05 | 2022-03-22 | 2022-04-05
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | TRAVLIFT | Travis Avenue Lift Project -- Elevating section of Travis Av | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-04-06 | 2022-04-10 | 2022-04-06 | 2026-04-10
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | TRAVSIDEW | TRAVIS AVENUE ELEVATION - FOR SIDEWALK/WALKWAY TO NATURE PRE | 1 | DESIGN | 2022-01-01 | 2022-01-20 | 2022-01-01 | 2022-01-20
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | TRAVSIDEW | TRAVIS AVENUE ELEVATION - FOR SIDEWALK/WALKWAY TO NATURE PRE | 2 | BID AWARD AND REGISTER CONTRCT | 2022-01-21 | 2022-02-04 | 2022-01-21 | 2022-02-04
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | TRAVSIDEW | TRAVIS AVENUE ELEVATION - FOR SIDEWALK/WALKWAY TO NATURE PRE | 3 | CONSTRUCTION | 2022-02-05 | 2022-03-11 | 2022-02-05 | 2022-03-11
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | TRAVSIDEW | TRAVIS AVENUE ELEVATION - FOR SIDEWALK/WALKWAY TO NATURE PRE | 4 | ORIGINAL EQUIP & FURNISHING | 2022-03-12 | 2022-03-21 | 2022-03-12 | 2022-03-21
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | TRAVSIDEW | TRAVIS AVENUE ELEVATION - FOR SIDEWALK/WALKWAY TO NATURE PRE | 5 | SUBSTANTIAL COMPLETION | 2022-03-22 | 2022-04-05 | 2022-03-22 | 2022-04-05
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | TRAVSIDEW | TRAVIS AVENUE ELEVATION - FOR SIDEWALK/WALKWAY TO NATURE PRE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-04-06 | 2022-04-10 | 2022-04-06 | 2026-04-10
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | YMCASOSH | YMCA South Shore - Staten Island | 1 | DESIGN | 2010-01-01 | 2011-01-20 | 2010-01-01 | 2011-01-20
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | YMCASOSH | YMCA South Shore - Staten Island | 2 | BID AWARD AND REGISTER CONTRCT | 2011-01-21 | 2011-01-20 | 2011-01-21 | 2011-01-20
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | YMCASOSH | YMCA South Shore - Staten Island | 3 | CONSTRUCTION | 2011-01-21 | 2012-01-20 | 2011-01-21 | 2012-01-20
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | YMCASOSH | YMCA South Shore - Staten Island | 4 | ORIGINAL EQUIP & FURNISHING | 2012-01-21 | 2012-01-20 | 2012-01-21 | 2012-01-20
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | YMCASOSH | YMCA South Shore - Staten Island | 5 | SUBSTANTIAL COMPLETION | 2012-01-21 | 2012-01-20 | 2012-01-21 | 2012-01-20
20201123 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | YMCASOSH | YMCA South Shore - Staten Island | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-01-21 | 2012-01-25 | 2012-01-21 | 2026-06-30
20201123 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM16NLSC | NEW LANE HOUSES - SECURITY CAMERAS AND DOORS | 1 | DESIGN | 2016-03-02 | 2016-08-28 | 2016-03-02 | 2016-08-28
20201123 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM16NLSC | NEW LANE HOUSES - SECURITY CAMERAS AND DOORS | 2 | BID AWARD AND REGISTER CONTRCT | 2016-08-29 | 2017-01-20 | 2016-08-29 | 2017-01-20
20201123 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM16NLSC | NEW LANE HOUSES - SECURITY CAMERAS AND DOORS | 3 | CONSTRUCTION | 2017-01-21 | 2018-01-20 | 2017-01-21 | 2018-01-20
20201123 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM16NLSC | NEW LANE HOUSES - SECURITY CAMERAS AND DOORS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-01-21 | 2018-07-19 | 2017-01-21 | 2018-01-20
20201123 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM16NLSC | NEW LANE HOUSES - SECURITY CAMERAS AND DOORS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-01-21 | 2018-07-19 | 2018-01-21 | 2020-01-20
20201123 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM16THSC | TODT HILL HOUSES SECURITY CAMERAS AND DOORS | 1 | DESIGN | 2016-01-02 | 2016-06-29 | 2016-01-02 | 2016-06-29
20201123 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM16THSC | TODT HILL HOUSES SECURITY CAMERAS AND DOORS | 2 | BID AWARD AND REGISTER CONTRCT | 2016-06-30 | 2016-11-21 | 2016-06-30 | 2016-11-21
20201123 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM16THSC | TODT HILL HOUSES SECURITY CAMERAS AND DOORS | 3 | CONSTRUCTION | 2016-11-22 | 2017-11-21 | 2016-11-22 | 2017-11-21
20201123 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM16THSC | TODT HILL HOUSES SECURITY CAMERAS AND DOORS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-11-22 | 2018-05-20 | 2016-11-22 | 2017-11-21
20201123 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM16THSC | TODT HILL HOUSES SECURITY CAMERAS AND DOORS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-11-22 | 2018-05-20 | 2017-11-22 | 2020-11-20
20201123 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM16WBDR | WEST BRIGHTON HOUSES UPGRADING OF DOORS AND SECURITY CAMERAS | 1 | DESIGN | 2016-03-02 | 2016-08-28 | 2016-03-02 | 2016-08-28
20201123 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM16WBDR | WEST BRIGHTON HOUSES UPGRADING OF DOORS AND SECURITY CAMERAS | 2 | BID AWARD AND REGISTER CONTRCT | 2016-08-29 | 2017-01-20 | 2016-08-29 | 2017-01-20
20201123 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM16WBDR | WEST BRIGHTON HOUSES UPGRADING OF DOORS AND SECURITY CAMERAS | 3 | CONSTRUCTION | 2017-01-21 | 2018-01-20 | 2017-01-21 | 2018-01-20
20201123 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM16WBDR | WEST BRIGHTON HOUSES UPGRADING OF DOORS AND SECURITY CAMERAS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-01-21 | 2018-07-19 | 2017-01-21 | 2018-01-20
20201123 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM16WBDR | WEST BRIGHTON HOUSES UPGRADING OF DOORS AND SECURITY CAMERAS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-01-21 | 2018-07-19 | 2018-01-21 | 2020-01-20
20201123 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CSLF | CASSIDY LAFAYETTE SECURITY CAMERAS | 1 | DESIGN | 2018-01-02 | 2018-06-30 | 2018-01-02 | 2018-06-30
20201123 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CSLF | CASSIDY LAFAYETTE SECURITY CAMERAS | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CSLF | CASSIDY LAFAYETTE SECURITY CAMERAS | 3 | CONSTRUCTION | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CSLF | CASSIDY LAFAYETTE SECURITY CAMERAS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-28 | 2020-06-24 | 2018-12-28 | 2019-12-27
20201123 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CSLF | CASSIDY LAFAYETTE SECURITY CAMERAS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-28 | 2020-06-24 | 2019-12-28 | 2020-06-24
20201123 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM18NLAC | NEW LANE SHORES LUNCH ROOM AC | 1 | DESIGN | 2018-05-01 | 2018-10-27 | 2018-05-01 | 2018-10-27
20201123 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM18NLAC | NEW LANE SHORES LUNCH ROOM AC | 2 | BID AWARD AND REGISTER CONTRCT | 2018-10-28 | 2019-04-25 | 2018-10-28 | 2019-04-25
20201123 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM18NLAC | NEW LANE SHORES LUNCH ROOM AC | 3 | CONSTRUCTION | 2019-04-26 | 2020-04-24 | 2019-04-26 | 2020-04-24
20201123 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM18NLAC | NEW LANE SHORES LUNCH ROOM AC | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-04-25 | 2020-10-21 | 2019-04-26 | 2020-04-24
20201123 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM18NLAC | NEW LANE SHORES LUNCH ROOM AC | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-04-25 | 2020-10-21 | 2020-04-25 | 2020-10-21
20201123 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM18THGR | TODT HILL GROUNDS UPDATES | 1 | DESIGN | 2018-01-15 | 2018-07-13 | 2018-01-15 | 2018-07-13
20201123 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM18THGR | TODT HILL GROUNDS UPDATES | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-14 | 2019-01-09 | 2018-07-14 | 2019-01-09
20201123 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM18THGR | TODT HILL GROUNDS UPDATES | 3 | CONSTRUCTION | 2019-01-10 | 2020-01-09 | 2019-01-10 | 2020-01-09
20201123 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM18THGR | TODT HILL GROUNDS UPDATES | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-01-10 | 2020-07-07 | 2019-01-10 | 2020-01-09
20201123 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM18THGR | TODT HILL GROUNDS UPDATES | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-01-10 | 2020-07-07 | 2020-01-10 | 2020-07-07
20201123 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM19BHLU | BERRY HOUSES INTERIOR LIGHTING | 1 | DESIGN | 2019-01-15 | 2019-07-13 | 2019-01-15 | 2019-07-13
20201123 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM19BHLU | BERRY HOUSES INTERIOR LIGHTING | 2 | BID AWARD AND REGISTER CONTRCT | 2019-07-14 | 2020-01-09 | 2019-07-14 | 2020-01-09
20201123 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM19BHLU | BERRY HOUSES INTERIOR LIGHTING | 3 | CONSTRUCTION | 2020-01-10 | 2021-01-08 | 2020-01-10 | 2021-01-08
20201123 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM19BHLU | BERRY HOUSES INTERIOR LIGHTING | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-01-09 | 2021-07-07 | 2020-01-10 | 2021-01-08
20201123 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM19BHLU | BERRY HOUSES INTERIOR LIGHTING | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-01-09 | 2021-07-07 | 2021-01-09 | 2021-07-07
20201123 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM19MHBC | MARINER HARBOR BASKETBALL COURTS | 1 | DESIGN | 2019-01-15 | 2019-07-13 | 2019-01-15 | 2019-07-13
20201123 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM19MHBC | MARINER HARBOR BASKETBALL COURTS | 2 | BID AWARD AND REGISTER CONTRCT | 2019-07-14 | 2020-01-09 | 2019-07-14 | 2020-01-09
20201123 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM19MHBC | MARINER HARBOR BASKETBALL COURTS | 3 | CONSTRUCTION | 2020-01-10 | 2021-01-08 | 2020-01-10 | 2021-01-08
20201123 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM19MHBC | MARINER HARBOR BASKETBALL COURTS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-01-09 | 2021-07-07 | 2020-01-10 | 2021-01-08
20201123 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM19MHBC | MARINER HARBOR BASKETBALL COURTS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-01-09 | 2021-07-07 | 2021-01-09 | 2021-07-07
20201123 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM19SBCU | SOUTH BEACH HOUSES CAMERA UPGRADES | 1 | DESIGN | 2018-10-25 | 2019-04-22 | 2018-10-25 | 2019-04-22
20201123 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM19SBCU | SOUTH BEACH HOUSES CAMERA UPGRADES | 2 | BID AWARD AND REGISTER CONTRCT | 2019-04-23 | 2019-10-19 | 2019-04-23 | 2019-10-19
20201123 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM19SBCU | SOUTH BEACH HOUSES CAMERA UPGRADES | 3 | CONSTRUCTION | 2019-10-20 | 2020-10-18 | 2019-10-20 | 2020-10-18
20201123 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM19SBCU | SOUTH BEACH HOUSES CAMERA UPGRADES | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-10-19 | 2021-04-16 | 2019-10-20 | 2020-10-18
20201123 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM19SBCU | SOUTH BEACH HOUSES CAMERA UPGRADES | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-10-19 | 2021-04-16 | 2020-10-19 | 2021-04-16
20201123 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM19THSS | TODT HILL HOUSES SPRINKLER SYSTEM | 1 | DESIGN | 2019-01-15 | 2019-07-13 | 2019-01-15 | 2019-07-13
20201123 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM19THSS | TODT HILL HOUSES SPRINKLER SYSTEM | 2 | BID AWARD AND REGISTER CONTRCT | 2019-07-14 | 2020-01-09 | 2019-07-14 | 2020-01-09
20201123 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM19THSS | TODT HILL HOUSES SPRINKLER SYSTEM | 3 | CONSTRUCTION | 2020-01-10 | 2021-01-08 | 2020-01-10 | 2021-01-08
20201123 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM19THSS | TODT HILL HOUSES SPRINKLER SYSTEM | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-01-09 | 2021-07-07 | 2020-01-10 | 2021-01-08
20201123 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM19THSS | TODT HILL HOUSES SPRINKLER SYSTEM | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-01-09 | 2021-07-07 | 2021-01-09 | 2021-07-07
20201123 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM20BHCC | BERRY HOUSES CAMERA UPGRADES | 1 | DESIGN | 2018-01-02 | 2018-06-30 | 2018-01-02 | 2018-06-30
20201123 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM20BHCC | BERRY HOUSES CAMERA UPGRADES | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM20BHCC | BERRY HOUSES CAMERA UPGRADES | 3 | CONSTRUCTION | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM20BHCC | BERRY HOUSES CAMERA UPGRADES | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-28 | 2020-06-24 | 2018-12-28 | 2019-12-27
20201123 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM20BHCC | BERRY HOUSES CAMERA UPGRADES | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-28 | 2020-06-24 | 2019-12-28 | 2020-06-24
20201123 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM20SBLU | SOUTH BEACH HOUSES- LIGHTING UPGRADES | 1 | DESIGN | 2019-09-01 | 2020-02-27 | 2019-09-01 | 2020-02-27
20201123 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM20SBLU | SOUTH BEACH HOUSES- LIGHTING UPGRADES | 2 | BID AWARD AND REGISTER CONTRCT | 2020-02-28 | 2020-08-25 | 2020-02-28 | 2020-08-25
20201123 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM20SBLU | SOUTH BEACH HOUSES- LIGHTING UPGRADES | 3 | CONSTRUCTION | 2020-08-26 | 2021-08-25 | 2020-08-26 | 2021-08-25
20201123 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM20SBLU | SOUTH BEACH HOUSES- LIGHTING UPGRADES | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-08-26 | 2022-02-21 | 2020-08-26 | 2021-08-25
20201123 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM20SBLU | SOUTH BEACH HOUSES- LIGHTING UPGRADES | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-08-26 | 2022-02-21 | 2021-08-26 | 2022-02-21
20201123 | RICHMOND | 819 | HEALTH AND HOSPITALS CORP | 75200403 | SEA VIEW: RENOVATE MARINER'S HARBOR HOUSES CHC | 1 | DESIGN | 2018-05-13 | 2019-10-04 | 2018-05-13 | 2019-10-04
20201123 | RICHMOND | 819 | HEALTH AND HOSPITALS CORP | 75200403 | SEA VIEW: RENOVATE MARINER'S HARBOR HOUSES CHC | 2 | CONSTRUCTION | 2019-10-05 | 2022-10-03 | 2019-10-05 | 2022-10-03
20201123 | RICHMOND | 819 | HEALTH AND HOSPITALS CORP | 75200403 | SEA VIEW: RENOVATE MARINER'S HARBOR HOUSES CHC | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-10-04 | 2023-01-01 | 2022-10-04 | 2023-01-01
20201123 | RICHMOND | 819 | HEALTH AND HOSPITALS CORP | 75200902 | SEAVIEW: RENOVATION OF ISOLATION BUILDING | 1 | DESIGN | 2012-07-11 | 2013-05-31 | 2012-07-11 | 2013-05-31
20201123 | RICHMOND | 819 | HEALTH AND HOSPITALS CORP | 75200902 | SEAVIEW: RENOVATION OF ISOLATION BUILDING | 2 | CONSTRUCTION | 2013-06-01 | 2014-05-31 | 2012-07-11 | 2013-05-31
20201123 | RICHMOND | 819 | HEALTH AND HOSPITALS CORP | 75200902 | SEAVIEW: RENOVATION OF ISOLATION BUILDING | 3 | CONSTRUCTION | 2013-06-01 | 2014-05-31 | 2013-06-01 | 2022-05-31
20201123 | RICHMOND | 819 | HEALTH AND HOSPITALS CORP | 75201502 | SEA VIEW: EMERGENCY GENERATOR REPLACEMENT | 1 | DESIGN | 2015-05-11 | 2016-03-30 | 2015-05-11 | 2016-03-30
20201123 | RICHMOND | 819 | HEALTH AND HOSPITALS CORP | 75201502 | SEA VIEW: EMERGENCY GENERATOR REPLACEMENT | 2 | CONSTRUCTION | 2016-03-31 | 2017-03-30 | 2015-05-11 | 2016-03-30
20201123 | RICHMOND | 819 | HEALTH AND HOSPITALS CORP | 75201502 | SEA VIEW: EMERGENCY GENERATOR REPLACEMENT | 3 | CONSTRUCTION | 2016-03-31 | 2017-03-30 | 2016-03-31 | 2021-03-30
20201123 | RICHMOND | 819 | HEALTH AND HOSPITALS CORP | 75202101 | SEAVIEW: REH CENTER & HOME GRACE FOUNDATION PHASE 3 | 1 | DESIGN | 2020-05-01 | 2021-09-22 | 2020-05-01 | 2021-09-22
20201123 | RICHMOND | 819 | HEALTH AND HOSPITALS CORP | 75202101 | SEAVIEW: REH CENTER & HOME GRACE FOUNDATION PHASE 3 | 2 | CONSTRUCTION | 2021-09-23 | 2023-09-22 | 2021-09-23 | 2023-09-22
20201123 | RICHMOND | 819 | HEALTH AND HOSPITALS CORP | 75202101 | SEAVIEW: REH CENTER & HOME GRACE FOUNDATION PHASE 3 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-23 | 2023-12-21 | 2023-09-23 | 2023-12-21
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | NCMCCSG | NEW CLOVE PS: EQUIPMENT REPLACEMENT | 1 | PRE-CONSTRUCTION MOBILIZATION | 2019-06-01 | 2020-05-25 | 2019-06-01 | 2020-05-25
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | NCMCCSG | NEW CLOVE PS: EQUIPMENT REPLACEMENT | 2 | ON-SITE CONSTRUCTION MANAGEMEN | 2020-05-26 | 2026-04-24 | 2020-05-26 | 2026-04-24
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | NCMCCSG | NEW CLOVE PS: EQUIPMENT REPLACEMENT | 3 | POST-CONSTRUCTION CLOSE-OUT | 2026-04-25 | 2027-04-19 | 2026-04-25 | 2027-04-19
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-125-L | RECONSTRUCTION OF SUBSTATION AT THE OAKWOOD BEACH WPCP | 1 | DEVELOP SCOPE | 2008-03-01 | 2008-05-29 | 2008-03-01 | 2008-11-25
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-125-L | RECONSTRUCTION OF SUBSTATION AT THE OAKWOOD BEACH WPCP | 2 | PRELIMINARY DESIGN | 2008-05-30 | 2008-09-26 | 2008-11-26 | 2009-11-20
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-125-L | RECONSTRUCTION OF SUBSTATION AT THE OAKWOOD BEACH WPCP | 3 | FINAL DESIGN | 2008-09-27 | 2009-03-25 | 2009-11-21 | 2011-05-14
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-125-L | RECONSTRUCTION OF SUBSTATION AT THE OAKWOOD BEACH WPCP | 4 | BID AWARD AND REGISTER CONTRCT | 2009-03-26 | 2009-06-23 | 2011-05-15 | 2012-02-08
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-125-L | RECONSTRUCTION OF SUBSTATION AT THE OAKWOOD BEACH WPCP | 5 | CONSTRUCTION TO 25% | 2009-06-24 | 2009-10-21 | 2012-02-09 | 2013-02-02
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-125-L | RECONSTRUCTION OF SUBSTATION AT THE OAKWOOD BEACH WPCP | 6 | CONSTRUCTION TO 50% | 2009-10-22 | 2010-02-18 | 2013-02-03 | 2014-01-28
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-125-L | RECONSTRUCTION OF SUBSTATION AT THE OAKWOOD BEACH WPCP | 7 | CONSTRUCTION TO 75% | 2010-02-19 | 2010-06-18 | 2014-01-29 | 2015-01-23
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-125-L | RECONSTRUCTION OF SUBSTATION AT THE OAKWOOD BEACH WPCP | 8 | ORIGINAL EQUIP & FURNISHING | 2010-06-19 | 2010-09-16 | 2015-01-24 | 2015-10-20
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-125-L | RECONSTRUCTION OF SUBSTATION AT THE OAKWOOD BEACH WPCP | 9 | SUBSTANTIAL COMPLETION | 2010-09-17 | 2010-11-15 | 2015-10-21 | 2024-04-15
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-125-L | RECONSTRUCTION OF SUBSTATION AT THE OAKWOOD BEACH WPCP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2010-11-16 | 2010-12-15 | 2024-04-16 | 2024-07-14
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-133-L | SLUDGE THICKENING IMPROVEMENT @ OAKWOOD BEACH WPCP | 1 | DEVELOP SCOPE | 2015-06-01 | 2016-02-25 | 2015-06-01 | 2016-02-25
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-133-L | SLUDGE THICKENING IMPROVEMENT @ OAKWOOD BEACH WPCP | 2 | PRELIMINARY DESIGN | 2016-02-26 | 2017-02-19 | 2016-02-26 | 2017-02-19
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-133-L | SLUDGE THICKENING IMPROVEMENT @ OAKWOOD BEACH WPCP | 3 | FINAL DESIGN | 2017-02-20 | 2018-08-13 | 2017-02-20 | 2018-08-13
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-133-L | SLUDGE THICKENING IMPROVEMENT @ OAKWOOD BEACH WPCP | 4 | BID AWARD AND REGISTER CONTRCT | 2018-08-14 | 2019-05-10 | 2018-08-14 | 2019-05-10
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-133-L | SLUDGE THICKENING IMPROVEMENT @ OAKWOOD BEACH WPCP | 5 | CONSTRUCTION TO 25% | 2019-05-11 | 2020-05-04 | 2019-05-11 | 2020-05-04
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-133-L | SLUDGE THICKENING IMPROVEMENT @ OAKWOOD BEACH WPCP | 6 | CONSTRUCTION TO 50% | 2020-05-05 | 2021-04-29 | 2020-05-05 | 2021-04-29
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-133-L | SLUDGE THICKENING IMPROVEMENT @ OAKWOOD BEACH WPCP | 7 | CONSTRUCTION TO 75% | 2021-04-30 | 2022-04-24 | 2021-04-30 | 2022-04-24
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-133-L | SLUDGE THICKENING IMPROVEMENT @ OAKWOOD BEACH WPCP | 8 | ORIGINAL EQUIP & FURNISHING | 2022-04-25 | 2023-01-19 | 2022-04-25 | 2023-01-19
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-133-L | SLUDGE THICKENING IMPROVEMENT @ OAKWOOD BEACH WPCP | 9 | SUBSTANTIAL COMPLETION | 2023-01-20 | 2023-07-18 | 2023-01-20 | 2023-07-18
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-133-L | SLUDGE THICKENING IMPROVEMENT @ OAKWOOD BEACH WPCP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-07-19 | 2023-10-16 | 2023-07-19 | 2023-10-16
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-134-L | POWER DISTRIBUTION AT OAKWOOD BEACH WPCP | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-09-28 | 2017-07-01 | 2018-03-27
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-134-L | POWER DISTRIBUTION AT OAKWOOD BEACH WPCP | 2 | PRELIMINARY DESIGN | 2017-09-29 | 2018-01-26 | 2018-03-28 | 2019-03-22
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-134-L | POWER DISTRIBUTION AT OAKWOOD BEACH WPCP | 3 | FINAL DESIGN | 2018-01-27 | 2018-07-25 | 2019-03-23 | 2020-09-12
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-134-L | POWER DISTRIBUTION AT OAKWOOD BEACH WPCP | 4 | BID AWARD AND REGISTER CONTRCT | 2018-07-26 | 2018-10-23 | 2020-09-13 | 2021-06-09
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-134-L | POWER DISTRIBUTION AT OAKWOOD BEACH WPCP | 5 | CONSTRUCTION TO 25% | 2018-10-24 | 2019-02-20 | 2021-06-10 | 2022-06-04
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-134-L | POWER DISTRIBUTION AT OAKWOOD BEACH WPCP | 6 | CONSTRUCTION TO 50% | 2019-02-21 | 2019-06-20 | 2022-06-05 | 2023-05-30
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-134-L | POWER DISTRIBUTION AT OAKWOOD BEACH WPCP | 7 | CONSTRUCTION TO 75% | 2019-06-21 | 2019-10-18 | 2023-05-31 | 2024-05-24
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-134-L | POWER DISTRIBUTION AT OAKWOOD BEACH WPCP | 8 | ORIGINAL EQUIP & FURNISHING | 2019-10-19 | 2020-01-16 | 2024-05-25 | 2025-02-18
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-134-L | POWER DISTRIBUTION AT OAKWOOD BEACH WPCP | 9 | SUBSTANTIAL COMPLETION | 2020-01-17 | 2020-03-16 | 2025-02-19 | 2029-08-16
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-134-L | POWER DISTRIBUTION AT OAKWOOD BEACH WPCP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-03-17 | 2020-04-15 | 2029-08-17 | 2029-11-14
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-135-L | HEADWORKS AT OAKWOOD BEACH WPCP | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-09-28 | 2017-07-01 | 2018-03-27
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-135-L | HEADWORKS AT OAKWOOD BEACH WPCP | 2 | PRELIMINARY DESIGN | 2017-09-29 | 2018-01-26 | 2018-03-28 | 2019-03-22
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-135-L | HEADWORKS AT OAKWOOD BEACH WPCP | 3 | FINAL DESIGN | 2018-01-27 | 2018-07-25 | 2019-03-23 | 2020-09-12
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-135-L | HEADWORKS AT OAKWOOD BEACH WPCP | 4 | BID AWARD AND REGISTER CONTRCT | 2018-07-26 | 2018-10-23 | 2020-09-13 | 2021-06-09
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-135-L | HEADWORKS AT OAKWOOD BEACH WPCP | 5 | CONSTRUCTION TO 25% | 2018-10-24 | 2019-02-20 | 2021-06-10 | 2022-06-04
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-135-L | HEADWORKS AT OAKWOOD BEACH WPCP | 6 | CONSTRUCTION TO 50% | 2019-02-21 | 2019-06-20 | 2022-06-05 | 2023-05-30
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-135-L | HEADWORKS AT OAKWOOD BEACH WPCP | 7 | CONSTRUCTION TO 75% | 2019-06-21 | 2019-10-18 | 2023-05-31 | 2024-05-24
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-135-L | HEADWORKS AT OAKWOOD BEACH WPCP | 8 | ORIGINAL EQUIP & FURNISHING | 2019-10-19 | 2020-01-16 | 2024-05-25 | 2025-02-18
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-135-L | HEADWORKS AT OAKWOOD BEACH WPCP | 9 | SUBSTANTIAL COMPLETION | 2020-01-17 | 2020-03-16 | 2025-02-19 | 2025-08-17
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-135-L | HEADWORKS AT OAKWOOD BEACH WPCP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-03-17 | 2020-04-15 | 2025-08-18 | 2025-11-15
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-136-L | INSTALLATION OF (2) MAIN TRANSFORMERS @ OAKWOOD BEACH WPCP | 1 | DEVELOP SCOPE | 2013-06-10 | 2014-03-06 | 2013-06-10 | 2014-03-06
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-136-L | INSTALLATION OF (2) MAIN TRANSFORMERS @ OAKWOOD BEACH WPCP | 2 | PRELIMINARY DESIGN | 2014-03-07 | 2015-03-01 | 2014-03-07 | 2015-03-01
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-136-L | INSTALLATION OF (2) MAIN TRANSFORMERS @ OAKWOOD BEACH WPCP | 3 | FINAL DESIGN | 2015-03-02 | 2016-08-22 | 2015-03-02 | 2016-08-22
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-136-L | INSTALLATION OF (2) MAIN TRANSFORMERS @ OAKWOOD BEACH WPCP | 4 | BID AWARD AND REGISTER CONTRCT | 2016-08-23 | 2017-05-19 | 2016-08-23 | 2017-05-19
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-136-L | INSTALLATION OF (2) MAIN TRANSFORMERS @ OAKWOOD BEACH WPCP | 5 | CONSTRUCTION TO 25% | 2017-05-20 | 2018-05-14 | 2017-05-20 | 2018-05-14
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-136-L | INSTALLATION OF (2) MAIN TRANSFORMERS @ OAKWOOD BEACH WPCP | 6 | CONSTRUCTION TO 50% | 2018-05-15 | 2019-05-09 | 2018-05-15 | 2019-05-09
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-136-L | INSTALLATION OF (2) MAIN TRANSFORMERS @ OAKWOOD BEACH WPCP | 7 | CONSTRUCTION TO 75% | 2019-05-10 | 2020-05-03 | 2019-05-10 | 2020-05-03
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-136-L | INSTALLATION OF (2) MAIN TRANSFORMERS @ OAKWOOD BEACH WPCP | 8 | ORIGINAL EQUIP & FURNISHING | 2020-05-04 | 2021-01-28 | 2020-05-04 | 2021-01-28
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-136-L | INSTALLATION OF (2) MAIN TRANSFORMERS @ OAKWOOD BEACH WPCP | 9 | SUBSTANTIAL COMPLETION | 2021-01-29 | 2021-07-27 | 2021-01-29 | 2021-07-27
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-136-L | INSTALLATION OF (2) MAIN TRANSFORMERS @ OAKWOOD BEACH WPCP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-07-28 | 2021-10-25 | 2021-07-28 | 2021-10-25
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-149-L | UPGRADE FIRE ALARM SYSTEM @ OAKWOOD BEACH DEWATERING BLDG | 1 | FINAL DESIGN | 2022-06-01 | 2023-11-22 | 2022-06-01 | 2023-11-22
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-149-L | UPGRADE FIRE ALARM SYSTEM @ OAKWOOD BEACH DEWATERING BLDG | 2 | CONSTRUCTION TO 25% | 2023-11-23 | 2024-07-19 | 2023-11-23 | 2024-07-19
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-149-L | UPGRADE FIRE ALARM SYSTEM @ OAKWOOD BEACH DEWATERING BLDG | 3 | CONSTRUCTION TO 50% | 2024-07-20 | 2025-03-16 | 2024-07-20 | 2025-03-16
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-149-L | UPGRADE FIRE ALARM SYSTEM @ OAKWOOD BEACH DEWATERING BLDG | 4 | CONSTRUCTION TO 75% | 2025-03-17 | 2025-11-11 | 2025-03-17 | 2025-11-11
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-132-L | RECONSTRUCTION OF SEA WALL/SLUDGE DOCK IMPROVEMENTS | 1 | DEVELOP SCOPE | 2022-07-01 | 2022-09-28 | 2018-07-01 | 2019-03-27
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-132-L | RECONSTRUCTION OF SEA WALL/SLUDGE DOCK IMPROVEMENTS | 2 | PRELIMINARY DESIGN | 2022-09-29 | 2023-01-26 | 2019-03-28 | 2020-03-21
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-132-L | RECONSTRUCTION OF SEA WALL/SLUDGE DOCK IMPROVEMENTS | 3 | FINAL DESIGN | 2023-01-27 | 2023-07-25 | 2020-03-22 | 2021-09-12
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-132-L | RECONSTRUCTION OF SEA WALL/SLUDGE DOCK IMPROVEMENTS | 4 | BID AWARD AND REGISTER CONTRCT | 2023-07-26 | 2023-10-23 | 2021-09-13 | 2022-06-09
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-132-L | RECONSTRUCTION OF SEA WALL/SLUDGE DOCK IMPROVEMENTS | 5 | CONSTRUCTION TO 25% | 2023-10-24 | 2024-02-20 | 2022-06-10 | 2023-06-04
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-132-L | RECONSTRUCTION OF SEA WALL/SLUDGE DOCK IMPROVEMENTS | 6 | CONSTRUCTION TO 50% | 2024-02-21 | 2024-06-19 | 2023-06-05 | 2024-05-29
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-132-L | RECONSTRUCTION OF SEA WALL/SLUDGE DOCK IMPROVEMENTS | 7 | CONSTRUCTION TO 75% | 2024-06-20 | 2024-10-17 | 2024-05-30 | 2025-05-24
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-132-L | RECONSTRUCTION OF SEA WALL/SLUDGE DOCK IMPROVEMENTS | 8 | ORIGINAL EQUIP & FURNISHING | 2024-10-18 | 2025-01-15 | 2025-05-25 | 2026-02-18
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-132-L | RECONSTRUCTION OF SEA WALL/SLUDGE DOCK IMPROVEMENTS | 9 | SUBSTANTIAL COMPLETION | 2025-01-16 | 2025-03-16 | 2026-02-19 | 2030-08-16
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-132-L | RECONSTRUCTION OF SEA WALL/SLUDGE DOCK IMPROVEMENTS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-03-17 | 2025-04-15 | 2030-08-17 | 2030-11-14
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-134-L | RECONSTRUCT FINAL SETTLING SYSTEM EQUIPMENT @ PORT RICHMOND | 1 | DEVELOP SCOPE | 2017-07-01 | 2018-03-27 | 2021-06-01 | 2022-02-25
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-134-L | RECONSTRUCT FINAL SETTLING SYSTEM EQUIPMENT @ PORT RICHMOND | 2 | PRELIMINARY DESIGN | 2018-03-28 | 2019-03-22 | 2022-02-26 | 2023-02-20
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-134-L | RECONSTRUCT FINAL SETTLING SYSTEM EQUIPMENT @ PORT RICHMOND | 3 | FINAL DESIGN | 2019-03-23 | 2020-09-12 | 2023-02-21 | 2024-08-13
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-134-L | RECONSTRUCT FINAL SETTLING SYSTEM EQUIPMENT @ PORT RICHMOND | 4 | BID AWARD AND REGISTER CONTRCT | 2020-09-13 | 2021-06-09 | 2024-08-14 | 2025-05-10
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-134-L | RECONSTRUCT FINAL SETTLING SYSTEM EQUIPMENT @ PORT RICHMOND | 5 | CONSTRUCTION TO 25% | 2021-06-10 | 2022-06-04 | 2025-05-11 | 2026-05-05
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-134-L | RECONSTRUCT FINAL SETTLING SYSTEM EQUIPMENT @ PORT RICHMOND | 6 | CONSTRUCTION TO 50% | 2022-06-05 | 2023-05-30 | 2026-05-06 | 2027-04-30
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-134-L | RECONSTRUCT FINAL SETTLING SYSTEM EQUIPMENT @ PORT RICHMOND | 7 | CONSTRUCTION TO 75% | 2023-05-31 | 2024-05-24 | 2027-05-01 | 2028-04-24
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-134-L | RECONSTRUCT FINAL SETTLING SYSTEM EQUIPMENT @ PORT RICHMOND | 8 | ORIGINAL EQUIP & FURNISHING | 2024-05-25 | 2025-02-18 | 2028-04-25 | 2029-01-19
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-134-L | RECONSTRUCT FINAL SETTLING SYSTEM EQUIPMENT @ PORT RICHMOND | 9 | SUBSTANTIAL COMPLETION | 2025-02-19 | 2025-08-17 | 2029-01-20 | 2033-07-17
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-134-L | RECONSTRUCT FINAL SETTLING SYSTEM EQUIPMENT @ PORT RICHMOND | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-08-18 | 2025-11-15 | 2033-07-18 | 2033-10-15
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-135-L | RECONSTRUCT POWER DISTRIBUTION EQUIPMENT @ PORT RICHMOND | 1 | DEVELOP SCOPE | 2022-06-01 | 2022-08-29 | 2022-06-01 | 2023-02-25
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-135-L | RECONSTRUCT POWER DISTRIBUTION EQUIPMENT @ PORT RICHMOND | 2 | PRELIMINARY DESIGN | 2022-08-30 | 2022-12-27 | 2023-02-26 | 2024-02-20
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-135-L | RECONSTRUCT POWER DISTRIBUTION EQUIPMENT @ PORT RICHMOND | 3 | FINAL DESIGN | 2022-12-28 | 2023-06-25 | 2024-02-21 | 2025-08-13
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-135-L | RECONSTRUCT POWER DISTRIBUTION EQUIPMENT @ PORT RICHMOND | 4 | BID AWARD AND REGISTER CONTRCT | 2023-06-26 | 2023-09-23 | 2025-08-14 | 2026-05-10
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-135-L | RECONSTRUCT POWER DISTRIBUTION EQUIPMENT @ PORT RICHMOND | 5 | CONSTRUCTION TO 25% | 2023-09-24 | 2024-01-21 | 2026-05-11 | 2027-05-05
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-135-L | RECONSTRUCT POWER DISTRIBUTION EQUIPMENT @ PORT RICHMOND | 6 | CONSTRUCTION TO 50% | 2024-01-22 | 2024-05-20 | 2027-05-06 | 2028-04-29
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-135-L | RECONSTRUCT POWER DISTRIBUTION EQUIPMENT @ PORT RICHMOND | 7 | CONSTRUCTION TO 75% | 2024-05-21 | 2024-09-17 | 2028-04-30 | 2029-04-24
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-135-L | RECONSTRUCT POWER DISTRIBUTION EQUIPMENT @ PORT RICHMOND | 8 | ORIGINAL EQUIP & FURNISHING | 2024-09-18 | 2024-12-16 | 2029-04-25 | 2030-01-19
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-135-L | RECONSTRUCT POWER DISTRIBUTION EQUIPMENT @ PORT RICHMOND | 9 | SUBSTANTIAL COMPLETION | 2024-12-17 | 2025-02-14 | 2030-01-20 | 2030-07-18
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-135-L | RECONSTRUCT POWER DISTRIBUTION EQUIPMENT @ PORT RICHMOND | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-02-15 | 2025-03-16 | 2030-07-19 | 2030-10-16
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-138-L | RECONSTRUCT MAIN SEWAGE PUMP CONTROLS @ PORT RICHMOND WWTP | 1 | DEVELOP SCOPE | 2017-11-01 | 2018-07-28 | 2017-11-01 | 2018-07-28
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-138-L | RECONSTRUCT MAIN SEWAGE PUMP CONTROLS @ PORT RICHMOND WWTP | 2 | PRELIMINARY DESIGN | 2018-07-29 | 2019-07-23 | 2018-07-29 | 2019-07-23
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-138-L | RECONSTRUCT MAIN SEWAGE PUMP CONTROLS @ PORT RICHMOND WWTP | 3 | FINAL DESIGN | 2019-07-24 | 2021-01-13 | 2019-07-24 | 2021-01-13
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-138-L | RECONSTRUCT MAIN SEWAGE PUMP CONTROLS @ PORT RICHMOND WWTP | 4 | BID AWARD AND REGISTER CONTRCT | 2021-01-14 | 2021-10-10 | 2021-01-14 | 2021-10-10
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-138-L | RECONSTRUCT MAIN SEWAGE PUMP CONTROLS @ PORT RICHMOND WWTP | 5 | CONSTRUCTION TO 25% | 2021-10-11 | 2022-10-05 | 2021-10-11 | 2022-10-05
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-138-L | RECONSTRUCT MAIN SEWAGE PUMP CONTROLS @ PORT RICHMOND WWTP | 6 | CONSTRUCTION TO 50% | 2022-10-06 | 2023-09-30 | 2022-10-06 | 2023-09-30
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-138-L | RECONSTRUCT MAIN SEWAGE PUMP CONTROLS @ PORT RICHMOND WWTP | 7 | CONSTRUCTION TO 75% | 2023-10-01 | 2024-09-24 | 2023-10-01 | 2024-09-24
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-138-L | RECONSTRUCT MAIN SEWAGE PUMP CONTROLS @ PORT RICHMOND WWTP | 8 | ORIGINAL EQUIP & FURNISHING | 2024-09-25 | 2025-06-21 | 2024-09-25 | 2025-06-21
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-138-L | RECONSTRUCT MAIN SEWAGE PUMP CONTROLS @ PORT RICHMOND WWTP | 9 | SUBSTANTIAL COMPLETION | 2025-06-22 | 2025-12-18 | 2025-06-22 | 2025-12-18
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-138-L | RECONSTRUCT MAIN SEWAGE PUMP CONTROLS @ PORT RICHMOND WWTP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-12-19 | 2026-03-18 | 2025-12-19 | 2026-03-18
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-140 | TRC - Dechlorination Facilities at Port Richmond WWTP | 1 | DEVELOP SCOPE | 2019-07-01 | 2020-03-26 | 2019-07-01 | 2020-03-26
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-140 | TRC - Dechlorination Facilities at Port Richmond WWTP | 2 | PRELIMINARY DESIGN | 2020-03-27 | 2021-03-21 | 2020-03-27 | 2021-03-21
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-140 | TRC - Dechlorination Facilities at Port Richmond WWTP | 3 | FINAL DESIGN | 2021-03-22 | 2022-09-12 | 2021-03-22 | 2022-09-12
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-140 | TRC - Dechlorination Facilities at Port Richmond WWTP | 4 | BID AWARD AND REGISTER CONTRCT | 2022-09-13 | 2023-06-09 | 2022-09-13 | 2023-06-09
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-140 | TRC - Dechlorination Facilities at Port Richmond WWTP | 5 | CONSTRUCTION TO 25% | 2023-06-10 | 2024-06-03 | 2023-06-10 | 2024-06-03
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-140 | TRC - Dechlorination Facilities at Port Richmond WWTP | 6 | CONSTRUCTION TO 50% | 2024-06-04 | 2025-05-29 | 2024-06-04 | 2025-05-29
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-140 | TRC - Dechlorination Facilities at Port Richmond WWTP | 7 | CONSTRUCTION TO 75% | 2025-05-30 | 2026-05-24 | 2025-05-30 | 2026-05-24
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-140 | TRC - Dechlorination Facilities at Port Richmond WWTP | 8 | ORIGINAL EQUIP & FURNISHING | 2026-05-25 | 2027-02-18 | 2026-05-25 | 2027-02-18
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-140 | TRC - Dechlorination Facilities at Port Richmond WWTP | 9 | SUBSTANTIAL COMPLETION | 2027-02-19 | 2027-08-17 | 2027-02-19 | 2027-08-17
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-140 | TRC - Dechlorination Facilities at Port Richmond WWTP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2027-08-18 | 2027-11-15 | 2027-08-18 | 2027-11-15
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-144-L | RECONSTRUCT BLOWERS AND CONTROLS @ PORT RICHMOND WPCP | 1 | FINAL DESIGN | 2023-06-01 | 2024-11-21 | 2023-06-01 | 2024-11-21
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-144-L | RECONSTRUCT BLOWERS AND CONTROLS @ PORT RICHMOND WPCP | 2 | CONSTRUCTION TO 25% | 2024-11-22 | 2025-07-19 | 2024-11-22 | 2025-07-19
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-144-L | RECONSTRUCT BLOWERS AND CONTROLS @ PORT RICHMOND WPCP | 3 | CONSTRUCTION TO 50% | 2025-07-20 | 2026-03-16 | 2025-07-20 | 2026-03-16
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-144-L | RECONSTRUCT BLOWERS AND CONTROLS @ PORT RICHMOND WPCP | 4 | CONSTRUCTION TO 75% | 2026-03-17 | 2026-11-11 | 2026-03-17 | 2026-11-11
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-276 | RECONSTRUCTION AT HANNAH STREET PUMPING STATION (BEDC) | 1 | DEVELOP SCOPE | 2015-07-01 | 2016-03-26 | 2015-07-01 | 2016-03-26
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-276 | RECONSTRUCTION AT HANNAH STREET PUMPING STATION (BEDC) | 2 | PRELIMINARY DESIGN | 2016-03-27 | 2017-03-21 | 2016-03-27 | 2017-03-21
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-276 | RECONSTRUCTION AT HANNAH STREET PUMPING STATION (BEDC) | 3 | FINAL DESIGN | 2017-03-22 | 2018-09-12 | 2017-03-22 | 2018-09-12
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-276 | RECONSTRUCTION AT HANNAH STREET PUMPING STATION (BEDC) | 4 | BID AWARD AND REGISTER CONTRCT | 2018-09-13 | 2019-06-09 | 2018-09-13 | 2019-06-09
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-276 | RECONSTRUCTION AT HANNAH STREET PUMPING STATION (BEDC) | 5 | CONSTRUCTION TO 25% | 2019-06-10 | 2020-06-03 | 2019-06-10 | 2020-06-03
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-276 | RECONSTRUCTION AT HANNAH STREET PUMPING STATION (BEDC) | 6 | CONSTRUCTION TO 50% | 2020-06-04 | 2021-05-29 | 2020-06-04 | 2021-05-29
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-276 | RECONSTRUCTION AT HANNAH STREET PUMPING STATION (BEDC) | 7 | CONSTRUCTION TO 75% | 2021-05-30 | 2022-05-24 | 2021-05-30 | 2022-05-24
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-276 | RECONSTRUCTION AT HANNAH STREET PUMPING STATION (BEDC) | 8 | ORIGINAL EQUIP & FURNISHING | 2022-05-25 | 2023-02-18 | 2022-05-25 | 2023-02-18
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-276 | RECONSTRUCTION AT HANNAH STREET PUMPING STATION (BEDC) | 9 | SUBSTANTIAL COMPLETION | 2023-02-19 | 2023-08-17 | 2023-02-19 | 2023-08-17
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-276 | RECONSTRUCTION AT HANNAH STREET PUMPING STATION (BEDC) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-08-18 | 2023-11-15 | 2023-08-18 | 2023-11-15
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-295 | RECONSTRUCTION AT MERSEREAU PUMPING STATION | 1 | DEVELOP SCOPE | 2020-06-01 | 2021-02-25 | 2018-07-01 | 2019-03-27
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-295 | RECONSTRUCTION AT MERSEREAU PUMPING STATION | 2 | PRELIMINARY DESIGN | 2021-02-26 | 2022-02-20 | 2019-03-28 | 2020-03-21
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-295 | RECONSTRUCTION AT MERSEREAU PUMPING STATION | 3 | FINAL DESIGN | 2022-02-21 | 2023-08-14 | 2020-03-22 | 2021-09-12
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-295 | RECONSTRUCTION AT MERSEREAU PUMPING STATION | 4 | BID AWARD AND REGISTER CONTRCT | 2023-08-15 | 2024-05-10 | 2021-09-13 | 2022-06-09
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-295 | RECONSTRUCTION AT MERSEREAU PUMPING STATION | 5 | CONSTRUCTION TO 25% | 2024-05-11 | 2025-05-05 | 2022-06-10 | 2023-06-04
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-295 | RECONSTRUCTION AT MERSEREAU PUMPING STATION | 6 | CONSTRUCTION TO 50% | 2025-05-06 | 2026-04-30 | 2023-06-05 | 2024-05-29
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-295 | RECONSTRUCTION AT MERSEREAU PUMPING STATION | 7 | CONSTRUCTION TO 75% | 2026-05-01 | 2027-04-25 | 2024-05-30 | 2025-05-24
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-295 | RECONSTRUCTION AT MERSEREAU PUMPING STATION | 8 | ORIGINAL EQUIP & FURNISHING | 2027-04-26 | 2028-01-20 | 2025-05-25 | 2026-02-18
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-295 | RECONSTRUCTION AT MERSEREAU PUMPING STATION | 9 | SUBSTANTIAL COMPLETION | 2028-01-21 | 2028-07-18 | 2026-02-19 | 2026-08-17
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-295 | RECONSTRUCTION AT MERSEREAU PUMPING STATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2028-07-19 | 2028-10-16 | 2026-08-18 | 2026-11-15
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-296 | RECONSTRUCTION AT MELVIN PUMPING STATION | 1 | DEVELOP SCOPE | 2017-07-01 | 2018-03-27 | 2016-07-01 | 2017-03-27
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-296 | RECONSTRUCTION AT MELVIN PUMPING STATION | 2 | PRELIMINARY DESIGN | 2018-03-28 | 2019-03-22 | 2017-03-28 | 2018-03-22
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-296 | RECONSTRUCTION AT MELVIN PUMPING STATION | 3 | FINAL DESIGN | 2019-03-23 | 2020-09-12 | 2018-03-23 | 2019-09-13
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-296 | RECONSTRUCTION AT MELVIN PUMPING STATION | 4 | BID AWARD AND REGISTER CONTRCT | 2020-09-13 | 2021-06-09 | 2019-09-14 | 2020-06-09
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-296 | RECONSTRUCTION AT MELVIN PUMPING STATION | 5 | CONSTRUCTION TO 25% | 2021-06-10 | 2022-06-04 | 2020-06-10 | 2021-06-04
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-296 | RECONSTRUCTION AT MELVIN PUMPING STATION | 6 | CONSTRUCTION TO 50% | 2022-06-05 | 2023-05-30 | 2021-06-05 | 2022-05-30
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-296 | RECONSTRUCTION AT MELVIN PUMPING STATION | 7 | CONSTRUCTION TO 75% | 2023-05-31 | 2024-05-24 | 2022-05-31 | 2023-05-25
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-296 | RECONSTRUCTION AT MELVIN PUMPING STATION | 8 | ORIGINAL EQUIP & FURNISHING | 2024-05-25 | 2025-02-18 | 2023-05-26 | 2024-02-19
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-296 | RECONSTRUCTION AT MELVIN PUMPING STATION | 9 | SUBSTANTIAL COMPLETION | 2025-02-19 | 2025-08-17 | 2024-02-20 | 2024-08-17
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-296 | RECONSTRUCTION AT MELVIN PUMPING STATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-08-18 | 2025-11-15 | 2024-08-18 | 2024-11-15
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-317 | RECONSTRUCT VICTORY BOULEVARD PUMPING STATION STATEN ISLAND | 1 | DEVELOP SCOPE | 2016-07-01 | 2017-03-27 | 2016-07-01 | 2017-03-27
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-317 | RECONSTRUCT VICTORY BOULEVARD PUMPING STATION STATEN ISLAND | 2 | PRELIMINARY DESIGN | 2017-03-28 | 2018-03-22 | 2017-03-28 | 2018-03-22
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-317 | RECONSTRUCT VICTORY BOULEVARD PUMPING STATION STATEN ISLAND | 3 | FINAL DESIGN | 2018-03-23 | 2019-09-13 | 2018-03-23 | 2019-09-13
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-317 | RECONSTRUCT VICTORY BOULEVARD PUMPING STATION STATEN ISLAND | 4 | BID AWARD AND REGISTER CONTRCT | 2019-09-14 | 2020-06-09 | 2019-09-14 | 2020-06-09
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-317 | RECONSTRUCT VICTORY BOULEVARD PUMPING STATION STATEN ISLAND | 5 | CONSTRUCTION TO 25% | 2020-06-10 | 2021-06-04 | 2020-06-10 | 2021-06-04
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-317 | RECONSTRUCT VICTORY BOULEVARD PUMPING STATION STATEN ISLAND | 6 | CONSTRUCTION TO 50% | 2021-06-05 | 2022-05-30 | 2021-06-05 | 2022-05-30
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-317 | RECONSTRUCT VICTORY BOULEVARD PUMPING STATION STATEN ISLAND | 7 | CONSTRUCTION TO 75% | 2022-05-31 | 2023-05-25 | 2022-05-31 | 2023-05-25
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-317 | RECONSTRUCT VICTORY BOULEVARD PUMPING STATION STATEN ISLAND | 8 | ORIGINAL EQUIP & FURNISHING | 2023-05-26 | 2024-02-19 | 2023-05-26 | 2024-02-19
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-317 | RECONSTRUCT VICTORY BOULEVARD PUMPING STATION STATEN ISLAND | 9 | SUBSTANTIAL COMPLETION | 2024-02-20 | 2024-08-17 | 2024-02-20 | 2024-08-17
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-317 | RECONSTRUCT VICTORY BOULEVARD PUMPING STATION STATEN ISLAND | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-08-18 | 2024-11-15 | 2024-08-18 | 2024-11-15
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-322 | RECONSTRUCT MAYFLOWER AVENUE PUMPING STATION, STATEN ISLAND | 1 | DEVELOP SCOPE | 2022-06-01 | 2023-02-25 | 2018-07-01 | 2019-03-27
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-322 | RECONSTRUCT MAYFLOWER AVENUE PUMPING STATION, STATEN ISLAND | 2 | PRELIMINARY DESIGN | 2023-02-26 | 2024-02-20 | 2019-03-28 | 2020-03-21
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-322 | RECONSTRUCT MAYFLOWER AVENUE PUMPING STATION, STATEN ISLAND | 3 | FINAL DESIGN | 2024-02-21 | 2025-08-13 | 2020-03-22 | 2021-09-12
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-322 | RECONSTRUCT MAYFLOWER AVENUE PUMPING STATION, STATEN ISLAND | 4 | BID AWARD AND REGISTER CONTRCT | 2025-08-14 | 2026-05-10 | 2021-09-13 | 2022-06-09
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-322 | RECONSTRUCT MAYFLOWER AVENUE PUMPING STATION, STATEN ISLAND | 5 | CONSTRUCTION TO 25% | 2026-05-11 | 2027-05-05 | 2022-06-10 | 2023-06-04
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-322 | RECONSTRUCT MAYFLOWER AVENUE PUMPING STATION, STATEN ISLAND | 6 | CONSTRUCTION TO 50% | 2027-05-06 | 2028-04-29 | 2023-06-05 | 2024-05-29
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-322 | RECONSTRUCT MAYFLOWER AVENUE PUMPING STATION, STATEN ISLAND | 7 | CONSTRUCTION TO 75% | 2028-04-30 | 2029-04-24 | 2024-05-30 | 2025-05-24
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-322 | RECONSTRUCT MAYFLOWER AVENUE PUMPING STATION, STATEN ISLAND | 8 | ORIGINAL EQUIP & FURNISHING | 2029-04-25 | 2030-01-19 | 2025-05-25 | 2026-02-18
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-322 | RECONSTRUCT MAYFLOWER AVENUE PUMPING STATION, STATEN ISLAND | 9 | SUBSTANTIAL COMPLETION | 2030-01-20 | 2030-07-18 | 2026-02-19 | 2026-08-17
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-322 | RECONSTRUCT MAYFLOWER AVENUE PUMPING STATION, STATEN ISLAND | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2030-07-19 | 2030-10-16 | 2026-08-18 | 2026-11-15
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-323 | RECONSTRUCT RICHMOND AVENUE PUMPING STATION, STATEN ISLAND | 1 | DEVELOP SCOPE | 2022-06-01 | 2023-02-25 | 2019-06-01 | 2020-02-25
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-323 | RECONSTRUCT RICHMOND AVENUE PUMPING STATION, STATEN ISLAND | 2 | PRELIMINARY DESIGN | 2023-02-26 | 2024-02-20 | 2020-02-26 | 2021-02-19
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-323 | RECONSTRUCT RICHMOND AVENUE PUMPING STATION, STATEN ISLAND | 3 | FINAL DESIGN | 2024-02-21 | 2025-08-13 | 2021-02-20 | 2022-08-13
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-323 | RECONSTRUCT RICHMOND AVENUE PUMPING STATION, STATEN ISLAND | 4 | BID AWARD AND REGISTER CONTRCT | 2025-08-14 | 2026-05-10 | 2022-08-14 | 2023-05-10
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-323 | RECONSTRUCT RICHMOND AVENUE PUMPING STATION, STATEN ISLAND | 5 | CONSTRUCTION TO 25% | 2026-05-11 | 2027-05-05 | 2023-05-11 | 2024-05-04
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-323 | RECONSTRUCT RICHMOND AVENUE PUMPING STATION, STATEN ISLAND | 6 | CONSTRUCTION TO 50% | 2027-05-06 | 2028-04-29 | 2024-05-05 | 2025-04-29
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-323 | RECONSTRUCT RICHMOND AVENUE PUMPING STATION, STATEN ISLAND | 7 | CONSTRUCTION TO 75% | 2028-04-30 | 2029-04-24 | 2025-04-30 | 2026-04-24
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-323 | RECONSTRUCT RICHMOND AVENUE PUMPING STATION, STATEN ISLAND | 8 | ORIGINAL EQUIP & FURNISHING | 2029-04-25 | 2030-01-19 | 2026-04-25 | 2027-01-19
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-323 | RECONSTRUCT RICHMOND AVENUE PUMPING STATION, STATEN ISLAND | 9 | SUBSTANTIAL COMPLETION | 2030-01-20 | 2030-07-18 | 2027-01-20 | 2027-07-18
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-323 | RECONSTRUCT RICHMOND AVENUE PUMPING STATION, STATEN ISLAND | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2030-07-19 | 2030-10-16 | 2027-07-19 | 2027-10-16
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | RED-384 | TRUNK AND DISTRIBUTION WATER MAIN IN FRONT ST, SI | 1 | DEVELOP SCOPE | 2018-06-01 | 2018-08-29 | 2021-06-01 | 2021-08-29
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | RED-384 | TRUNK AND DISTRIBUTION WATER MAIN IN FRONT ST, SI | 2 | PRELIMINARY DESIGN | 2018-08-30 | 2018-12-27 | 2021-08-30 | 2021-12-27
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | RED-384 | TRUNK AND DISTRIBUTION WATER MAIN IN FRONT ST, SI | 3 | FINAL DESIGN | 2018-12-28 | 2019-06-25 | 2021-12-28 | 2022-06-25
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | RED-384 | TRUNK AND DISTRIBUTION WATER MAIN IN FRONT ST, SI | 4 | BID AWARD AND REGISTER CONTRCT | 2019-06-26 | 2019-09-23 | 2022-06-26 | 2022-09-23
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | RED-384 | TRUNK AND DISTRIBUTION WATER MAIN IN FRONT ST, SI | 5 | CONSTRUCTION TO 25% | 2019-09-24 | 2020-01-21 | 2022-09-24 | 2023-01-21
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | RED-384 | TRUNK AND DISTRIBUTION WATER MAIN IN FRONT ST, SI | 6 | CONSTRUCTION TO 50% | 2020-01-22 | 2020-05-20 | 2023-01-22 | 2023-05-21
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | RED-384 | TRUNK AND DISTRIBUTION WATER MAIN IN FRONT ST, SI | 7 | CONSTRUCTION TO 75% | 2020-05-21 | 2020-09-17 | 2023-05-22 | 2023-09-18
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | RED-384 | TRUNK AND DISTRIBUTION WATER MAIN IN FRONT ST, SI | 8 | ORIGINAL EQUIP & FURNISHING | 2020-09-18 | 2020-12-16 | 2023-09-19 | 2023-12-17
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | RED-384 | TRUNK AND DISTRIBUTION WATER MAIN IN FRONT ST, SI | 9 | SUBSTANTIAL COMPLETION | 2020-12-17 | 2021-02-14 | 2023-12-18 | 2024-02-15
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | RED-384 | TRUNK AND DISTRIBUTION WATER MAIN IN FRONT ST, SI | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-02-15 | 2021-03-16 | 2024-02-16 | 2024-03-16
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | RED-392 | WM rplcmt in Bay St between Slosson Ter & Minthorne St SI | 1 | DEVELOP SCOPE | 2020-11-09 | 2021-08-05 | 2020-11-09 | 2021-08-05
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | RED-392 | WM rplcmt in Bay St between Slosson Ter & Minthorne St SI | 2 | PRELIMINARY DESIGN | 2021-08-06 | 2022-07-31 | 2021-08-06 | 2022-07-31
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | RED-392 | WM rplcmt in Bay St between Slosson Ter & Minthorne St SI | 3 | FINAL DESIGN | 2022-08-01 | 2024-01-22 | 2022-08-01 | 2024-01-22
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | RED-392 | WM rplcmt in Bay St between Slosson Ter & Minthorne St SI | 4 | BID AWARD AND REGISTER CONTRCT | 2024-01-23 | 2024-10-18 | 2024-01-23 | 2024-10-18
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | RED-392 | WM rplcmt in Bay St between Slosson Ter & Minthorne St SI | 5 | CONSTRUCTION TO 25% | 2024-10-19 | 2025-10-13 | 2024-10-19 | 2025-10-13
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | RED-392 | WM rplcmt in Bay St between Slosson Ter & Minthorne St SI | 6 | CONSTRUCTION TO 50% | 2025-10-14 | 2026-10-08 | 2025-10-14 | 2026-10-08
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | RED-392 | WM rplcmt in Bay St between Slosson Ter & Minthorne St SI | 7 | CONSTRUCTION TO 75% | 2026-10-09 | 2027-10-03 | 2026-10-09 | 2027-10-03
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | RED-392 | WM rplcmt in Bay St between Slosson Ter & Minthorne St SI | 8 | ORIGINAL EQUIP & FURNISHING | 2027-10-04 | 2028-06-29 | 2027-10-04 | 2028-06-29
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | RED-392 | WM rplcmt in Bay St between Slosson Ter & Minthorne St SI | 9 | SUBSTANTIAL COMPLETION | 2028-06-30 | 2028-12-26 | 2028-06-30 | 2028-12-26
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | RED-392 | WM rplcmt in Bay St between Slosson Ter & Minthorne St SI | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2028-12-27 | 2029-03-26 | 2028-12-27 | 2029-03-26
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDOB | RECONS OF THE OAKWOOD BEACH WPCP DUE TO HURRICANE SANDY | 1 | DEVELOP SCOPE | 2014-07-01 | 2014-09-28 | 2017-06-01 | 2018-02-25
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDOB | RECONS OF THE OAKWOOD BEACH WPCP DUE TO HURRICANE SANDY | 2 | PRELIMINARY DESIGN | 2014-09-29 | 2015-01-26 | 2018-02-26 | 2019-02-20
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDOB | RECONS OF THE OAKWOOD BEACH WPCP DUE TO HURRICANE SANDY | 3 | FINAL DESIGN | 2015-01-27 | 2015-07-25 | 2019-02-21 | 2020-08-13
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDOB | RECONS OF THE OAKWOOD BEACH WPCP DUE TO HURRICANE SANDY | 4 | BID AWARD AND REGISTER CONTRCT | 2015-07-26 | 2015-10-23 | 2020-08-14 | 2021-05-10
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDOB | RECONS OF THE OAKWOOD BEACH WPCP DUE TO HURRICANE SANDY | 5 | CONSTRUCTION TO 25% | 2015-10-24 | 2016-02-20 | 2021-05-11 | 2022-05-05
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDOB | RECONS OF THE OAKWOOD BEACH WPCP DUE TO HURRICANE SANDY | 6 | CONSTRUCTION TO 50% | 2016-02-21 | 2016-06-19 | 2022-05-06 | 2023-04-30
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDOB | RECONS OF THE OAKWOOD BEACH WPCP DUE TO HURRICANE SANDY | 7 | CONSTRUCTION TO 75% | 2016-06-20 | 2016-10-17 | 2023-05-01 | 2024-04-24
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDOB | RECONS OF THE OAKWOOD BEACH WPCP DUE TO HURRICANE SANDY | 8 | ORIGINAL EQUIP & FURNISHING | 2016-10-18 | 2017-01-15 | 2024-04-25 | 2025-01-19
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDOB | RECONS OF THE OAKWOOD BEACH WPCP DUE TO HURRICANE SANDY | 9 | SUBSTANTIAL COMPLETION | 2017-01-16 | 2017-03-16 | 2025-01-20 | 2029-07-17
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDOB | RECONS OF THE OAKWOOD BEACH WPCP DUE TO HURRICANE SANDY | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-17 | 2017-04-15 | 2029-07-18 | 2029-10-15
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SER002334 | NDF - Rplcmt 6" sanitary sewers & distribution wtr mains SI | 1 | DEVELOP SCOPE | 2020-11-09 | 2021-08-05 | 2020-11-09 | 2021-08-05
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SER002334 | NDF - Rplcmt 6" sanitary sewers & distribution wtr mains SI | 2 | PRELIMINARY DESIGN | 2021-08-06 | 2022-07-31 | 2021-08-06 | 2022-07-31
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SER002334 | NDF - Rplcmt 6" sanitary sewers & distribution wtr mains SI | 3 | FINAL DESIGN | 2022-08-01 | 2024-01-22 | 2022-08-01 | 2024-01-22
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SER002334 | NDF - Rplcmt 6" sanitary sewers & distribution wtr mains SI | 4 | BID AWARD AND REGISTER CONTRCT | 2024-01-23 | 2024-10-18 | 2024-01-23 | 2024-10-18
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SER002334 | NDF - Rplcmt 6" sanitary sewers & distribution wtr mains SI | 5 | CONSTRUCTION TO 25% | 2024-10-19 | 2025-10-13 | 2024-10-19 | 2025-10-13
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SER002334 | NDF - Rplcmt 6" sanitary sewers & distribution wtr mains SI | 6 | CONSTRUCTION TO 50% | 2025-10-14 | 2026-10-08 | 2025-10-14 | 2026-10-08
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SER002334 | NDF - Rplcmt 6" sanitary sewers & distribution wtr mains SI | 7 | CONSTRUCTION TO 75% | 2026-10-09 | 2027-10-03 | 2026-10-09 | 2027-10-03
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SER002334 | NDF - Rplcmt 6" sanitary sewers & distribution wtr mains SI | 8 | ORIGINAL EQUIP & FURNISHING | 2027-10-04 | 2028-06-29 | 2027-10-04 | 2028-06-29
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SER002334 | NDF - Rplcmt 6" sanitary sewers & distribution wtr mains SI | 9 | SUBSTANTIAL COMPLETION | 2028-06-30 | 2028-12-26 | 2028-06-30 | 2028-12-26
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SER002334 | NDF - Rplcmt 6" sanitary sewers & distribution wtr mains SI | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2028-12-27 | 2029-03-26 | 2028-12-27 | 2029-03-26
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SER200256 | Extension & Replacmt of San Sewers in Victory Blvd SI | 1 | DEVELOP SCOPE | 2019-12-09 | 2020-09-03 | 2019-12-09 | 2020-09-03
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SER200256 | Extension & Replacmt of San Sewers in Victory Blvd SI | 2 | PRELIMINARY DESIGN | 2020-09-04 | 2021-08-29 | 2020-09-04 | 2021-08-29
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SER200256 | Extension & Replacmt of San Sewers in Victory Blvd SI | 3 | FINAL DESIGN | 2021-08-30 | 2023-02-20 | 2021-08-30 | 2023-02-20
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SER200256 | Extension & Replacmt of San Sewers in Victory Blvd SI | 4 | BID AWARD AND REGISTER CONTRCT | 2023-02-21 | 2023-11-17 | 2023-02-21 | 2023-11-17
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SER200256 | Extension & Replacmt of San Sewers in Victory Blvd SI | 5 | CONSTRUCTION TO 25% | 2023-11-18 | 2024-11-11 | 2023-11-18 | 2024-11-11
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SER200256 | Extension & Replacmt of San Sewers in Victory Blvd SI | 6 | CONSTRUCTION TO 50% | 2024-11-12 | 2025-11-06 | 2024-11-12 | 2025-11-06
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SER200256 | Extension & Replacmt of San Sewers in Victory Blvd SI | 7 | CONSTRUCTION TO 75% | 2025-11-07 | 2026-11-01 | 2025-11-07 | 2026-11-01
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SER200256 | Extension & Replacmt of San Sewers in Victory Blvd SI | 8 | ORIGINAL EQUIP & FURNISHING | 2026-11-02 | 2027-07-29 | 2026-11-02 | 2027-07-29
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SER200256 | Extension & Replacmt of San Sewers in Victory Blvd SI | 9 | SUBSTANTIAL COMPLETION | 2027-07-30 | 2028-01-25 | 2027-07-30 | 2028-01-25
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SER200256 | Extension & Replacmt of San Sewers in Victory Blvd SI | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2028-01-26 | 2028-04-24 | 2028-01-26 | 2028-04-24
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SIBB2-OAK | STATEN ISLAND BLUEBELT - OAKWOOD BEACH | 1 | DEVELOP SCOPE | 2013-06-01 | 2013-08-29 | 2013-06-01 | 2013-08-29
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SIBB2-OAK | STATEN ISLAND BLUEBELT - OAKWOOD BEACH | 2 | PRELIMINARY DESIGN | 2013-08-30 | 2013-12-27 | 2013-08-30 | 2013-12-27
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SIBB2-OAK | STATEN ISLAND BLUEBELT - OAKWOOD BEACH | 3 | FINAL DESIGN | 2013-12-28 | 2014-06-25 | 2013-12-28 | 2014-06-25
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SIBB2-OAK | STATEN ISLAND BLUEBELT - OAKWOOD BEACH | 4 | BID AWARD AND REGISTER CONTRCT | 2014-06-26 | 2014-09-23 | 2014-06-26 | 2014-09-23
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SIBB2-OAK | STATEN ISLAND BLUEBELT - OAKWOOD BEACH | 5 | CONSTRUCTION TO 25% | 2014-09-24 | 2015-01-21 | 2014-09-24 | 2015-01-21
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SIBB2-OAK | STATEN ISLAND BLUEBELT - OAKWOOD BEACH | 6 | CONSTRUCTION TO 50% | 2015-01-22 | 2015-05-21 | 2015-01-22 | 2015-05-21
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SIBB2-OAK | STATEN ISLAND BLUEBELT - OAKWOOD BEACH | 7 | CONSTRUCTION TO 75% | 2015-05-22 | 2015-09-18 | 2015-05-22 | 2015-09-18
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SIBB2-OAK | STATEN ISLAND BLUEBELT - OAKWOOD BEACH | 8 | ORIGINAL EQUIP & FURNISHING | 2015-09-19 | 2015-12-17 | 2015-09-19 | 2015-12-17
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SIBB2-OAK | STATEN ISLAND BLUEBELT - OAKWOOD BEACH | 9 | SUBSTANTIAL COMPLETION | 2015-12-18 | 2016-02-15 | 2015-12-18 | 2028-02-15
20201123 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SIBB2-OAK | STATEN ISLAND BLUEBELT - OAKWOOD BEACH | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-02-16 | 2016-03-16 | 2028-02-16 | 2028-03-16
20201123 | RICHMOND | 827 | DEPARTMENT OF SANITATION | S136-366G | S I Compost Bagging Building | 1 | DEVELOP SCOPE | 2020-02-01 | 2020-03-16 | 2020-02-01 | 2020-03-16
20201123 | RICHMOND | 827 | DEPARTMENT OF SANITATION | S136-366G | S I Compost Bagging Building | 2 | PRELIMINARY DESIGN | 2020-03-17 | 2020-05-15 | 2020-03-17 | 2020-05-15
20201123 | RICHMOND | 827 | DEPARTMENT OF SANITATION | S136-366G | S I Compost Bagging Building | 3 | FINAL DESIGN | 2020-05-16 | 2020-07-14 | 2020-05-16 | 2020-07-14
20201123 | RICHMOND | 827 | DEPARTMENT OF SANITATION | S136-366G | S I Compost Bagging Building | 4 | BID AWARD AND REGISTER CONTRCT | 2020-07-15 | 2020-10-31 | 2020-07-15 | 2020-10-31
20201123 | RICHMOND | 827 | DEPARTMENT OF SANITATION | S136-366G | S I Compost Bagging Building | 5 | CONSTRUCTION TO 25% | 2020-11-01 | 2021-02-28 | 2020-11-01 | 2021-02-28
20201123 | RICHMOND | 827 | DEPARTMENT OF SANITATION | S136-366G | S I Compost Bagging Building | 6 | CONSTRUCTION TO 50% | 2021-03-01 | 2021-06-28 | 2021-03-01 | 2021-06-28
20201123 | RICHMOND | 827 | DEPARTMENT OF SANITATION | S136-366G | S I Compost Bagging Building | 7 | CONSTRUCTION TO 75% | 2021-06-29 | 2021-10-26 | 2021-06-29 | 2021-10-26
20201123 | RICHMOND | 827 | DEPARTMENT OF SANITATION | S136-366G | S I Compost Bagging Building | 8 | SUBSTANTIAL COMPLETION | 2021-10-27 | 2022-03-25 | 2021-10-27 | 2022-03-25
20201123 | RICHMOND | 827 | DEPARTMENT OF SANITATION | S136-366G | S I Compost Bagging Building | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-26 | 2022-10-11 | 2022-03-26 | 2022-10-11
20201123 | RICHMOND | 827 | DEPARTMENT OF SANITATION | S136-367C | Parking Lot Paving | 1 | DEVELOP SCOPE | 2020-02-01 | 2020-03-16 | 2020-02-01 | 2020-03-16
20201123 | RICHMOND | 827 | DEPARTMENT OF SANITATION | S136-367C | Parking Lot Paving | 2 | PRELIMINARY DESIGN | 2020-03-17 | 2020-05-15 | 2020-03-17 | 2020-05-15
20201123 | RICHMOND | 827 | DEPARTMENT OF SANITATION | S136-367C | Parking Lot Paving | 3 | FINAL DESIGN | 2020-05-16 | 2020-07-14 | 2020-05-16 | 2020-07-14
20201123 | RICHMOND | 827 | DEPARTMENT OF SANITATION | S136-367C | Parking Lot Paving | 4 | BID AWARD AND REGISTER CONTRCT | 2020-07-15 | 2020-10-12 | 2020-07-15 | 2020-10-12
20201123 | RICHMOND | 827 | DEPARTMENT OF SANITATION | S136-367C | Parking Lot Paving | 5 | CONSTRUCTION TO 25% | 2020-10-13 | 2021-01-10 | 2020-10-13 | 2021-01-10
20201123 | RICHMOND | 827 | DEPARTMENT OF SANITATION | S136-367C | Parking Lot Paving | 6 | CONSTRUCTION TO 50% | 2021-01-11 | 2021-04-10 | 2021-01-11 | 2021-04-10
20201123 | RICHMOND | 827 | DEPARTMENT OF SANITATION | S136-367C | Parking Lot Paving | 7 | CONSTRUCTION TO 75% | 2021-04-11 | 2021-08-08 | 2021-04-11 | 2021-08-08
20201123 | RICHMOND | 827 | DEPARTMENT OF SANITATION | S136-367C | Parking Lot Paving | 8 | SUBSTANTIAL COMPLETION | 2021-08-09 | 2022-01-05 | 2021-08-09 | 2022-01-05
20201123 | RICHMOND | 827 | DEPARTMENT OF SANITATION | S136-367C | Parking Lot Paving | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-01-06 | 2023-01-05 | 2022-01-06 | 2023-01-05
20201123 | RICHMOND | 827 | DEPARTMENT OF SANITATION | S136-374P | STATEN ISLAND 2 BOILER REPLACEMENT | 1 | DEVELOP SCOPE | 2019-05-01 | 2019-07-19 | 2019-05-01 | 2019-07-19
20201123 | RICHMOND | 827 | DEPARTMENT OF SANITATION | S136-374P | STATEN ISLAND 2 BOILER REPLACEMENT | 2 | PRELIMINARY DESIGN | 2019-07-20 | 2019-10-17 | 2019-07-20 | 2019-10-17
20201123 | RICHMOND | 827 | DEPARTMENT OF SANITATION | S136-374P | STATEN ISLAND 2 BOILER REPLACEMENT | 3 | FINAL DESIGN | 2019-10-18 | 2020-02-14 | 2019-10-18 | 2020-02-14
20201123 | RICHMOND | 827 | DEPARTMENT OF SANITATION | S136-374P | STATEN ISLAND 2 BOILER REPLACEMENT | 4 | BID AWARD AND REGISTER CONTRCT | 2020-02-15 | 2020-06-30 | 2020-02-15 | 2020-06-30
20201123 | RICHMOND | 827 | DEPARTMENT OF SANITATION | S136-374P | STATEN ISLAND 2 BOILER REPLACEMENT | 5 | CONSTRUCTION TO 25% | 2020-07-01 | 2020-12-27 | 2020-07-01 | 2020-12-27
20201123 | RICHMOND | 827 | DEPARTMENT OF SANITATION | S136-374P | STATEN ISLAND 2 BOILER REPLACEMENT | 6 | CONSTRUCTION TO 50% | 2020-12-28 | 2021-06-25 | 2020-12-28 | 2021-06-25
20201123 | RICHMOND | 827 | DEPARTMENT OF SANITATION | S136-374P | STATEN ISLAND 2 BOILER REPLACEMENT | 7 | CONSTRUCTION TO 75% | 2021-06-26 | 2021-12-22 | 2021-06-26 | 2021-12-22
20201123 | RICHMOND | 827 | DEPARTMENT OF SANITATION | S136-374P | STATEN ISLAND 2 BOILER REPLACEMENT | 8 | SUBSTANTIAL COMPLETION | 2021-12-23 | 2022-12-22 | 2021-12-23 | 2022-12-22
20201123 | RICHMOND | 827 | DEPARTMENT OF SANITATION | S136-374P | STATEN ISLAND 2 BOILER REPLACEMENT | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-12-23 | 2023-12-22 | 2022-12-23 | 2023-12-22
20201123 | RICHMOND | 827 | DEPARTMENT OF SANITATION | S136-380B | Staten Island Garage 3 Boiler Replacement | 1 | DEVELOP SCOPE | 2018-06-01 | 2018-07-15 | 2018-06-01 | 2018-07-15
20201123 | RICHMOND | 827 | DEPARTMENT OF SANITATION | S136-380B | Staten Island Garage 3 Boiler Replacement | 2 | PRELIMINARY DESIGN | 2018-07-16 | 2018-09-13 | 2018-07-16 | 2018-09-13
20201123 | RICHMOND | 827 | DEPARTMENT OF SANITATION | S136-380B | Staten Island Garage 3 Boiler Replacement | 3 | FINAL DESIGN | 2018-09-14 | 2018-11-12 | 2018-09-14 | 2018-11-12
20201123 | RICHMOND | 827 | DEPARTMENT OF SANITATION | S136-380B | Staten Island Garage 3 Boiler Replacement | 4 | BID AWARD AND REGISTER CONTRCT | 2018-11-13 | 2019-02-10 | 2018-11-13 | 2019-02-10
20201123 | RICHMOND | 827 | DEPARTMENT OF SANITATION | S136-380B | Staten Island Garage 3 Boiler Replacement | 5 | CONSTRUCTION TO 25% | 2019-02-11 | 2019-12-07 | 2019-02-11 | 2019-12-07
20201123 | RICHMOND | 827 | DEPARTMENT OF SANITATION | S136-380B | Staten Island Garage 3 Boiler Replacement | 6 | CONSTRUCTION TO 50% | 2019-12-08 | 2020-10-02 | 2019-12-08 | 2020-10-02
20201123 | RICHMOND | 827 | DEPARTMENT OF SANITATION | S136-380B | Staten Island Garage 3 Boiler Replacement | 7 | CONSTRUCTION TO 75% | 2020-10-03 | 2021-07-29 | 2020-10-03 | 2021-07-29
20201123 | RICHMOND | 827 | DEPARTMENT OF SANITATION | S136-380B | Staten Island Garage 3 Boiler Replacement | 8 | SUBSTANTIAL COMPLETION | 2021-07-30 | 2021-12-26 | 2021-07-30 | 2021-12-26
20201123 | RICHMOND | 827 | DEPARTMENT OF SANITATION | S136-380B | Staten Island Garage 3 Boiler Replacement | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-12-27 | 2022-04-25 | 2021-12-27 | 2022-04-25
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | C5219FM5 | STATEN ISLAND FMF FACILITY UTILITIES UPGRADES X823.48 | 1 | DEVELOP SCOPE | 2009-06-30 | 2010-06-29 | 2017-06-30 | 2018-06-29
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | C5219FM5 | STATEN ISLAND FMF FACILITY UTILITIES UPGRADES X823.48 | 2 | DESIGN START | 2010-06-30 | 2012-06-28 | 2018-06-30 | 2020-06-28
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | C5219FM5 | STATEN ISLAND FMF FACILITY UTILITIES UPGRADES X823.48 | 3 | CONSTRUCTION START | 2012-06-29 | 2014-06-28 | 2020-06-29 | 2022-06-28
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | C5517B | DOCKBUILDING HARDWOOD TIMBER | 1 | DEVELOP SCOPE | 2009-07-01 | 2010-06-30 | 2017-07-01 | 2018-06-30
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | C5517B | DOCKBUILDING HARDWOOD TIMBER | 2 | DESIGN START | 2010-07-01 | 2012-06-29 | 2018-07-01 | 2020-06-29
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | C5517B | DOCKBUILDING HARDWOOD TIMBER | 3 | CONSTRUCTION START | 2012-06-30 | 2014-06-29 | 2020-06-30 | 2022-06-29
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | C5588 | REPLACEMENT OF OIL BARGE #5 | 1 | DEVELOP SCOPE | 2009-06-01 | 2010-05-31 | 2019-06-02 | 2026-06-30
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | C5588 | REPLACEMENT OF OIL BARGE #5 | 2 | DESIGN START | 2010-06-01 | 2012-05-30 | 2027-06-30 | 2027-07-30
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | C5588 | REPLACEMENT OF OIL BARGE #5 | 3 | CONSTRUCTION START | 2012-05-31 | 2014-05-30 | 2027-07-31 | 2030-07-29
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | C5590 | DRYDOCK MOLINARI FERRY BOATS | 1 | DEVELOP SCOPE | 2004-06-01 | 2005-05-31 | 2017-06-01 | 2018-05-31
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | C5590 | DRYDOCK MOLINARI FERRY BOATS | 2 | DESIGN START | 2005-06-01 | 2007-05-31 | 2018-06-01 | 2020-05-30
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | C5590 | DRYDOCK MOLINARI FERRY BOATS | 3 | CONSTRUCTION START | 2007-06-01 | 2009-05-30 | 2020-05-31 | 2022-05-30
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FABLDG45R | Building 45 Rehabilitation | 1 | DEVELOP SCOPE | 2016-06-30 | 2017-06-29 | 2017-09-10 | 2019-06-29
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FABLDG45R | Building 45 Rehabilitation | 2 | DESIGN START | 2017-06-30 | 2019-06-29 | 2019-06-30 | 2021-06-28
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FABLDG45R | Building 45 Rehabilitation | 3 | CONSTRUCTION START | 2019-06-30 | 2021-06-28 | 2021-06-29 | 2023-06-28
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FAFUELFC | Fuel Facility Centrifuge | 1 | DEVELOP SCOPE | 2018-06-30 | 2019-06-29 | 2018-06-30 | 2019-06-29
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FAFUELFC | Fuel Facility Centrifuge | 2 | DESIGN START | 2019-06-30 | 2021-06-28 | 2019-06-30 | 2021-06-28
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FAFUELFC | Fuel Facility Centrifuge | 3 | CONSTRUCTION START | 2021-06-29 | 2023-06-28 | 2021-06-29 | 2023-06-28
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FASGTRCN | St.George Ferry Terminal Waterfront Remediation | 1 | DEVELOP SCOPE | 2018-06-30 | 2019-06-29 | 2018-06-30 | 2019-06-29
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FASGTRCN | St.George Ferry Terminal Waterfront Remediation | 2 | DESIGN START | 2019-06-30 | 2021-06-28 | 2019-06-30 | 2021-06-28
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FASGTRCN | St.George Ferry Terminal Waterfront Remediation | 3 | CONSTRUCTION START | 2021-06-29 | 2023-06-28 | 2021-06-29 | 2023-06-28
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FASGTRHB | SGT Terminal Brick Facade Rehabilitation | 1 | DEVELOP SCOPE | 2018-06-30 | 2019-06-29 | 2018-06-30 | 2019-06-29
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FASGTRHB | SGT Terminal Brick Facade Rehabilitation | 2 | DESIGN START | 2019-06-30 | 2021-06-28 | 2019-06-30 | 2025-06-30
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FASGTRHB | SGT Terminal Brick Facade Rehabilitation | 3 | CONSTRUCTION START | 2021-06-29 | 2023-06-28 | 2025-07-01 | 2026-06-30
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FASTGCCTV | STG Terminal CCTV Upgrade | 1 | DEVELOP SCOPE | 2017-06-30 | 2018-06-29 | 2017-06-30 | 2018-06-29
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FASTGCCTV | STG Terminal CCTV Upgrade | 2 | DESIGN START | 2018-06-30 | 2020-06-28 | 2018-06-30 | 2020-06-28
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FASTGCCTV | STG Terminal CCTV Upgrade | 3 | CONSTRUCTION START | 2020-06-29 | 2022-06-28 | 2020-06-29 | 2022-06-28
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FAUREABRG | SIF Diesel Exhaust Fluid (DEF) Storage & Distribution | 1 | DEVELOP SCOPE | 2018-06-30 | 2019-06-29 | 2018-06-30 | 2019-06-29
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FAUREABRG | SIF Diesel Exhaust Fluid (DEF) Storage & Distribution | 2 | DESIGN START | 2019-06-30 | 2021-06-28 | 2019-06-30 | 2021-06-28
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FAUREABRG | SIF Diesel Exhaust Fluid (DEF) Storage & Distribution | 3 | CONSTRUCTION START | 2021-06-29 | 2023-06-28 | 2021-06-29 | 2023-06-28
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FBENVCOM | Ferryboat Environmental Compliance Upgrades | 1 | DEVELOP SCOPE | 2016-07-01 | 2017-06-30 | 2023-07-01 | 2024-06-29
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FBENVCOM | Ferryboat Environmental Compliance Upgrades | 2 | DESIGN START | 2017-07-01 | 2019-06-30 | 2024-06-30 | 2026-06-29
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FBENVCOM | Ferryboat Environmental Compliance Upgrades | 3 | CONSTRUCTION START | 2019-07-01 | 2021-06-29 | 2026-07-02 | 2027-12-09
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FERRYR1SG | Construction of Ferryrack at Slip1, St. George Terminal | 1 | DEVELOP SCOPE | 2020-06-30 | 2021-06-29 | 2020-06-30 | 2021-06-29
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FERRYR1SG | Construction of Ferryrack at Slip1, St. George Terminal | 2 | DESIGN START | 2021-06-30 | 2023-06-29 | 2021-06-30 | 2023-06-29
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FERRYR1SG | Construction of Ferryrack at Slip1, St. George Terminal | 3 | CONSTRUCTION START | 2023-06-30 | 2025-06-28 | 2023-06-30 | 2025-06-28
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FERRYR3SG | Construction of Ferryrack at Slip3, St. George Terminal | 1 | DEVELOP SCOPE | 2020-06-30 | 2021-06-29 | 2020-06-30 | 2021-06-29
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FERRYR3SG | Construction of Ferryrack at Slip3, St. George Terminal | 2 | DESIGN START | 2021-06-30 | 2023-06-29 | 2021-06-30 | 2023-06-29
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FERRYR3SG | Construction of Ferryrack at Slip3, St. George Terminal | 3 | CONSTRUCTION START | 2023-06-30 | 2025-06-28 | 2023-06-30 | 2025-06-28
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FERRYRACK | CONSTRUCTION OF FERRY RACK | 1 | DEVELOP SCOPE | 2007-10-01 | 2008-09-29 | 2017-10-01 | 2018-09-30
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FERRYRACK | CONSTRUCTION OF FERRY RACK | 2 | DESIGN START | 2008-09-30 | 2010-09-29 | 2018-10-01 | 2020-09-29
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FERRYRACK | CONSTRUCTION OF FERRY RACK | 3 | CONSTRUCTION START | 2010-09-30 | 2012-09-28 | 2020-09-30 | 2022-09-29
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FMFVARNR | FMF Vehicle Access Ramps and Nose Upgrade | 1 | DEVELOP SCOPE | 2016-06-30 | 2017-06-29 | 2017-06-30 | 2018-06-29
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FMFVARNR | FMF Vehicle Access Ramps and Nose Upgrade | 2 | DESIGN START | 2017-06-30 | 2019-06-29 | 2018-06-30 | 2020-06-28
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FMFVARNR | FMF Vehicle Access Ramps and Nose Upgrade | 3 | CONSTRUCTION START | 2019-06-30 | 2021-06-28 | 2020-06-29 | 2022-06-28
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FVESSGANR | Facility/Vessel Gangways Replacement/Upgrade | 1 | DEVELOP SCOPE | 2017-06-30 | 2018-06-29 | 2017-06-30 | 2018-06-29
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FVESSGANR | Facility/Vessel Gangways Replacement/Upgrade | 2 | DESIGN START | 2018-06-30 | 2020-06-28 | 2018-06-30 | 2020-06-28
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FVESSGANR | Facility/Vessel Gangways Replacement/Upgrade | 3 | CONSTRUCTION START | 2020-06-29 | 2022-06-28 | 2021-06-02 | 2022-06-04
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HBR249730 | BR OVER DAM OVER NORTH END CLOVE LAKE BIN 2249730 | 1 | DEVELOP SCOPE | 2017-06-30 | 2018-06-29 | 0 | 0
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HBR249730 | BR OVER DAM OVER NORTH END CLOVE LAKE BIN 2249730 | 2 | DESIGN START | 2018-06-30 | 2022-06-28 | 2017-06-30 | 2018-06-29
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HBR249730 | BR OVER DAM OVER NORTH END CLOVE LAKE BIN 2249730 | 3 | CONSTRUCTION START | 2022-06-29 | 2024-06-27 | 2018-06-30 | 2022-06-28
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HBR249730 | BR OVER DAM OVER NORTH END CLOVE LAKE BIN 2249730 | 5 | CONSTRUCTION START | 2022-06-29 | 2024-06-27 | 2022-06-29 | 2024-06-27
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HBRA24925 | BETHEL AVE PED BRIDGE BIN:2249250 | 1 | DEVELOP SCOPE | 2018-06-30 | 2019-06-29 | 0 | 0
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HBRA24925 | BETHEL AVE PED BRIDGE BIN:2249250 | 2 | DESIGN START | 2019-06-30 | 2023-06-28 | 2015-06-30 | 2016-06-28
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HBRA24925 | BETHEL AVE PED BRIDGE BIN:2249250 | 3 | CONSTRUCTION START | 2023-06-29 | 2025-06-27 | 2016-06-29 | 2020-06-27
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HBRA24925 | BETHEL AVE PED BRIDGE BIN:2249250 | 5 | CONSTRUCTION START | 2023-06-29 | 2025-06-27 | 2020-06-28 | 2022-06-27
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HBRA24939 | CEDARVIEW AVE PED BRIDGE BIN: 2249390 | 1 | DEVELOP SCOPE | 2018-06-30 | 2019-06-29 | 0 | 0
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HBRA24939 | CEDARVIEW AVE PED BRIDGE BIN: 2249390 | 2 | DESIGN START | 2019-06-30 | 2023-06-28 | 2015-10-19 | 2016-02-23
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HBRA24939 | CEDARVIEW AVE PED BRIDGE BIN: 2249390 | 3 | CONSTRUCTION START | 2023-06-29 | 2025-06-27 | 2017-11-15 | 2022-02-03
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HBRA24939 | CEDARVIEW AVE PED BRIDGE BIN: 2249390 | 5 | CONSTRUCTION START | 2023-06-29 | 2025-06-27 | 2013-01-12 | 2025-04-14
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HBRA24982 | ARTHUR KILL RD/ ARTHUR KILL STREAM BIN#2249820 | 1 | DEVELOP SCOPE | 2021-06-30 | 2021-09-27 | 2019-06-30 | 2019-09-27
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HBRA24982 | ARTHUR KILL RD/ ARTHUR KILL STREAM BIN#2249820 | 2 | PRELIMINARY DESIGN | 2021-09-28 | 2022-01-25 | 2019-09-28 | 2020-01-25
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HBRA24982 | ARTHUR KILL RD/ ARTHUR KILL STREAM BIN#2249820 | 3 | FINAL DESIGN | 2022-01-26 | 2022-07-24 | 2020-01-26 | 2020-07-23
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HBRA24982 | ARTHUR KILL RD/ ARTHUR KILL STREAM BIN#2249820 | 4 | BID AWARD AND REGISTER CONTRCT | 2022-07-25 | 2022-10-22 | 2020-07-24 | 2020-10-21
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HBRA24982 | ARTHUR KILL RD/ ARTHUR KILL STREAM BIN#2249820 | 5 | CONSTRUCTION TO 25% | 2022-10-23 | 2023-02-19 | 2020-10-22 | 2021-02-18
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HBRA24982 | ARTHUR KILL RD/ ARTHUR KILL STREAM BIN#2249820 | 6 | CONSTRUCTION TO 50% | 2023-02-20 | 2023-06-19 | 2021-02-19 | 2021-06-18
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HBRA24982 | ARTHUR KILL RD/ ARTHUR KILL STREAM BIN#2249820 | 7 | CONSTRUCTION TO 75% | 2023-06-20 | 2023-10-17 | 2021-06-19 | 2021-10-16
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HBRA24982 | ARTHUR KILL RD/ ARTHUR KILL STREAM BIN#2249820 | 8 | ORIGINAL EQUIP & FURNISHING | 2023-10-18 | 2024-01-15 | 2021-10-17 | 2022-01-14
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HBRA24982 | ARTHUR KILL RD/ ARTHUR KILL STREAM BIN#2249820 | 9 | SUBSTANTIAL COMPLETION | 2024-01-16 | 2024-03-15 | 2022-01-15 | 2022-03-15
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HBRA24982 | ARTHUR KILL RD/ ARTHUR KILL STREAM BIN#2249820 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-03-16 | 2024-04-14 | 2022-03-16 | 2022-04-14
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HBRSGFT17 | ARMAJANI STRUCTURE | 1 | DEVELOP SCOPE | 2017-06-30 | 2018-06-29 | 0 | 0
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HBRSGFT17 | ARMAJANI STRUCTURE | 2 | DEVELOP SCOPE | 2018-06-30 | 2022-06-28 | 2017-06-30 | 2018-06-29
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HBRSGFT17 | ARMAJANI STRUCTURE | 3 | DESIGN START | 2022-06-29 | 2024-06-27 | 2018-06-30 | 2019-06-29
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HBRSGFT17 | ARMAJANI STRUCTURE | 5 | CONSTRUCTION START | 2022-06-29 | 2024-06-27 | 2019-06-30 | 2020-06-28
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-07 | North Bridge Street/South Bridge Street - Construction | 1 | DEVELOP SCOPE | 2019-06-30 | 2019-09-27 | 2020-06-30 | 2020-09-27
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-07 | North Bridge Street/South Bridge Street - Construction | 2 | PRELIMINARY DESIGN | 2019-09-28 | 2020-01-25 | 2020-09-28 | 2021-01-25
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-07 | North Bridge Street/South Bridge Street - Construction | 3 | FINAL DESIGN | 2020-01-26 | 2020-07-23 | 2021-01-26 | 2021-07-24
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-07 | North Bridge Street/South Bridge Street - Construction | 4 | BID AWARD AND REGISTER CONTRCT | 2020-07-24 | 2020-10-21 | 2021-07-25 | 2021-10-22
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-07 | North Bridge Street/South Bridge Street - Construction | 5 | CONSTRUCTION TO 25% | 2020-10-22 | 2021-02-18 | 2021-10-23 | 2022-02-19
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-07 | North Bridge Street/South Bridge Street - Construction | 6 | CONSTRUCTION TO 50% | 2021-02-19 | 2021-06-18 | 2022-02-20 | 2022-06-19
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-07 | North Bridge Street/South Bridge Street - Construction | 7 | CONSTRUCTION TO 75% | 2021-06-19 | 2021-10-16 | 2022-06-20 | 2022-10-17
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-07 | North Bridge Street/South Bridge Street - Construction | 8 | ORIGINAL EQUIP & FURNISHING | 2021-10-17 | 2022-01-14 | 2022-10-18 | 2023-01-15
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-07 | North Bridge Street/South Bridge Street - Construction | 9 | SUBSTANTIAL COMPLETION | 2022-01-15 | 2022-03-15 | 2023-01-16 | 2023-03-16
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-07 | North Bridge Street/South Bridge Street - Construction | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-16 | 2022-04-14 | 2023-03-17 | 2025-04-15
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-08 | Victory CPI | 1 | DEVELOP SCOPE | 2019-06-30 | 2019-09-27 | 2020-06-30 | 2020-09-27
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-08 | Victory CPI | 2 | PRELIMINARY DESIGN | 2019-09-28 | 2020-01-25 | 2020-09-28 | 2021-01-25
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-08 | Victory CPI | 3 | FINAL DESIGN | 2020-01-26 | 2020-07-23 | 2021-01-26 | 2021-07-24
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-08 | Victory CPI | 4 | BID AWARD AND REGISTER CONTRCT | 2020-07-24 | 2020-10-21 | 2021-07-25 | 2021-10-22
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-08 | Victory CPI | 5 | CONSTRUCTION TO 25% | 2020-10-22 | 2021-02-18 | 2021-10-23 | 2022-02-19
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-08 | Victory CPI | 6 | CONSTRUCTION TO 50% | 2021-02-19 | 2021-06-18 | 2022-02-20 | 2022-06-19
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-08 | Victory CPI | 7 | CONSTRUCTION TO 75% | 2021-06-19 | 2021-10-16 | 2022-06-20 | 2022-10-17
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-08 | Victory CPI | 8 | ORIGINAL EQUIP & FURNISHING | 2021-10-17 | 2022-01-14 | 2022-10-18 | 2023-01-15
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-08 | Victory CPI | 9 | SUBSTANTIAL COMPLETION | 2022-01-15 | 2022-03-15 | 2023-01-16 | 2023-03-16
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-08 | Victory CPI | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-16 | 2022-04-14 | 2023-03-17 | 2025-04-15
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-09 | Pleasant Plains Park and Ride | 1 | DEVELOP SCOPE | 2019-06-30 | 2019-09-27 | 2023-06-30 | 2023-09-27
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-09 | Pleasant Plains Park and Ride | 2 | PRELIMINARY DESIGN | 2019-09-28 | 2020-01-25 | 2023-09-28 | 2024-01-25
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-09 | Pleasant Plains Park and Ride | 3 | FINAL DESIGN | 2020-01-26 | 2020-07-23 | 2024-01-26 | 2024-07-23
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-09 | Pleasant Plains Park and Ride | 4 | BID AWARD AND REGISTER CONTRCT | 2020-07-24 | 2020-10-21 | 2024-07-24 | 2024-10-21
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-09 | Pleasant Plains Park and Ride | 5 | CONSTRUCTION TO 25% | 2020-10-22 | 2021-02-18 | 2024-10-22 | 2025-02-18
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-09 | Pleasant Plains Park and Ride | 6 | CONSTRUCTION TO 50% | 2021-02-19 | 2021-06-18 | 2025-02-19 | 2025-06-18
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-09 | Pleasant Plains Park and Ride | 7 | CONSTRUCTION TO 75% | 2021-06-19 | 2021-10-16 | 2025-06-19 | 2025-10-16
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-09 | Pleasant Plains Park and Ride | 8 | ORIGINAL EQUIP & FURNISHING | 2021-10-17 | 2022-01-14 | 2025-10-17 | 2026-01-14
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-09 | Pleasant Plains Park and Ride | 9 | SUBSTANTIAL COMPLETION | 2022-01-15 | 2022-03-15 | 2026-01-15 | 2026-03-15
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-09 | Pleasant Plains Park and Ride | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-16 | 2022-04-14 | 2026-03-16 | 2026-04-14
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-10 | Sidewalks along Forest Hill Rd btw Ashworth and Ballfield | 1 | DEVELOP SCOPE | 2022-06-30 | 2022-09-27 | 2022-06-30 | 2022-09-27
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-10 | Sidewalks along Forest Hill Rd btw Ashworth and Ballfield | 2 | PRELIMINARY DESIGN | 2022-09-28 | 2023-01-25 | 2022-09-28 | 2023-01-25
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-10 | Sidewalks along Forest Hill Rd btw Ashworth and Ballfield | 3 | FINAL DESIGN | 2023-01-26 | 2023-07-24 | 2023-01-26 | 2023-07-24
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-10 | Sidewalks along Forest Hill Rd btw Ashworth and Ballfield | 4 | BID AWARD AND REGISTER CONTRCT | 2023-07-25 | 2023-10-22 | 2023-07-25 | 2023-10-22
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-10 | Sidewalks along Forest Hill Rd btw Ashworth and Ballfield | 5 | CONSTRUCTION TO 25% | 2023-10-23 | 2024-02-19 | 2023-10-23 | 2024-02-19
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-10 | Sidewalks along Forest Hill Rd btw Ashworth and Ballfield | 6 | CONSTRUCTION TO 50% | 2024-02-20 | 2024-06-18 | 2024-02-20 | 2024-06-18
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-10 | Sidewalks along Forest Hill Rd btw Ashworth and Ballfield | 7 | CONSTRUCTION TO 75% | 2024-06-19 | 2024-10-16 | 2024-06-19 | 2024-10-16
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-10 | Sidewalks along Forest Hill Rd btw Ashworth and Ballfield | 8 | ORIGINAL EQUIP & FURNISHING | 2024-10-17 | 2025-01-14 | 2024-10-17 | 2025-01-14
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-10 | Sidewalks along Forest Hill Rd btw Ashworth and Ballfield | 9 | SUBSTANTIAL COMPLETION | 2025-01-15 | 2025-03-15 | 2025-01-15 | 2025-03-15
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-10 | Sidewalks along Forest Hill Rd btw Ashworth and Ballfield | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-03-16 | 2025-04-14 | 2025-03-16 | 2025-04-14
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-11 | Christopher Lane Extension | 1 | DEVELOP SCOPE | 2020-06-30 | 2020-09-27 | 2023-06-30 | 2023-09-27
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-11 | Christopher Lane Extension | 2 | PRELIMINARY DESIGN | 2020-09-28 | 2021-01-25 | 2023-09-28 | 2024-01-25
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-11 | Christopher Lane Extension | 3 | FINAL DESIGN | 2021-01-26 | 2021-07-24 | 2024-01-26 | 2024-07-23
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-11 | Christopher Lane Extension | 4 | BID AWARD AND REGISTER CONTRCT | 2021-07-25 | 2021-10-22 | 2024-07-24 | 2024-10-21
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-11 | Christopher Lane Extension | 5 | CONSTRUCTION TO 25% | 2021-10-23 | 2022-02-19 | 2024-10-22 | 2025-02-18
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-11 | Christopher Lane Extension | 6 | CONSTRUCTION TO 50% | 2022-02-20 | 2022-06-19 | 2025-02-19 | 2025-06-18
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-11 | Christopher Lane Extension | 7 | CONSTRUCTION TO 75% | 2022-06-20 | 2022-10-17 | 2025-06-19 | 2025-10-16
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-11 | Christopher Lane Extension | 8 | ORIGINAL EQUIP & FURNISHING | 2022-10-18 | 2023-01-15 | 2025-10-17 | 2026-01-14
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-11 | Christopher Lane Extension | 9 | SUBSTANTIAL COMPLETION | 2023-01-16 | 2023-03-16 | 2026-01-15 | 2026-03-15
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-11 | Christopher Lane Extension | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-03-17 | 2023-04-15 | 2026-03-16 | 2026-04-14
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR00513 | Street Widening in the 50th Council District | 1 | DEVELOP SCOPE | 2020-06-30 | 2020-09-27 | 2025-06-30 | 2025-09-27
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR00513 | Street Widening in the 50th Council District | 2 | PRELIMINARY DESIGN | 2020-09-28 | 2021-01-25 | 2025-09-28 | 2026-01-25
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR00513 | Street Widening in the 50th Council District | 3 | FINAL DESIGN | 2021-01-26 | 2021-07-24 | 2026-01-26 | 2026-07-24
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR00513 | Street Widening in the 50th Council District | 4 | BID AWARD AND REGISTER CONTRCT | 2021-07-25 | 2021-10-22 | 2026-07-25 | 2026-10-22
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR00513 | Street Widening in the 50th Council District | 5 | CONSTRUCTION TO 25% | 2021-10-23 | 2022-02-19 | 2026-10-23 | 2027-02-19
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR00513 | Street Widening in the 50th Council District | 6 | CONSTRUCTION TO 50% | 2022-02-20 | 2022-06-19 | 2027-02-20 | 2027-06-19
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR00513 | Street Widening in the 50th Council District | 7 | CONSTRUCTION TO 75% | 2022-06-20 | 2022-10-17 | 2027-06-20 | 2027-10-17
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR00513 | Street Widening in the 50th Council District | 8 | ORIGINAL EQUIP & FURNISHING | 2022-10-18 | 2023-01-15 | 2027-10-18 | 2028-01-15
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR00513 | Street Widening in the 50th Council District | 9 | SUBSTANTIAL COMPLETION | 2023-01-16 | 2023-03-16 | 2028-01-16 | 2028-03-15
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR00513 | Street Widening in the 50th Council District | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-03-17 | 2023-04-15 | 2028-03-16 | 2028-04-14
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR700 | St George-Richmond Terrace Intersection Improvements | 1 | DEVELOP SCOPE | 2022-06-30 | 2022-09-27 | 2018-11-26 | 2019-11-21
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR700 | St George-Richmond Terrace Intersection Improvements | 2 | PRELIMINARY DESIGN | 2022-09-28 | 2023-01-25 | 2020-09-19 | 2022-01-06
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR700 | St George-Richmond Terrace Intersection Improvements | 3 | FINAL DESIGN | 2023-01-26 | 2023-07-24 | 2021-08-25 | 2022-12-10
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR700 | St George-Richmond Terrace Intersection Improvements | 4 | BID AWARD AND REGISTER CONTRCT | 2023-07-25 | 2023-10-22 | 2022-12-31 | 2023-06-08
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR700 | St George-Richmond Terrace Intersection Improvements | 5 | CONSTRUCTION TO 25% | 2023-10-23 | 2024-02-19 | 2023-06-08 | 2023-06-09
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR700 | St George-Richmond Terrace Intersection Improvements | 6 | CONSTRUCTION TO 50% | 2024-02-20 | 2024-06-18 | 2023-06-05 | 2023-06-06
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR700 | St George-Richmond Terrace Intersection Improvements | 7 | CONSTRUCTION TO 75% | 2024-06-19 | 2024-10-16 | 2023-06-02 | 2023-06-03
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR700 | St George-Richmond Terrace Intersection Improvements | 8 | ORIGINAL EQUIP & FURNISHING | 2024-10-17 | 2025-01-14 | 2023-05-31 | 2023-08-28
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR700 | St George-Richmond Terrace Intersection Improvements | 9 | SUBSTANTIAL COMPLETION | 2025-01-15 | 2025-03-15 | 2023-08-29 | 2023-10-27
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR700 | St George-Richmond Terrace Intersection Improvements | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-03-16 | 2025-04-14 | 2025-02-13 | 2025-05-14
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR703 | Bay Street Area Safety Improvements | 1 | DEVELOP SCOPE | 2022-06-30 | 2022-09-27 | 2017-09-15 | 2019-10-06
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR703 | Bay Street Area Safety Improvements | 2 | PRELIMINARY DESIGN | 2022-09-28 | 2023-01-25 | 2020-06-20 | 2021-05-04
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR703 | Bay Street Area Safety Improvements | 3 | FINAL DESIGN | 2023-01-26 | 2023-07-24 | 2021-04-20 | 2022-01-31
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR703 | Bay Street Area Safety Improvements | 4 | BID AWARD AND REGISTER CONTRCT | 2023-07-25 | 2023-10-22 | 2022-02-21 | 2022-06-28
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR703 | Bay Street Area Safety Improvements | 5 | CONSTRUCTION TO 25% | 2023-10-23 | 2024-02-19 | 2022-09-04 | 2023-03-03
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR703 | Bay Street Area Safety Improvements | 6 | CONSTRUCTION TO 50% | 2024-02-20 | 2024-06-18 | 2023-03-03 | 2023-08-30
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR703 | Bay Street Area Safety Improvements | 7 | CONSTRUCTION TO 75% | 2024-06-19 | 2024-10-16 | 2023-08-30 | 2024-02-26
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR703 | Bay Street Area Safety Improvements | 8 | ORIGINAL EQUIP & FURNISHING | 2024-10-17 | 2025-01-14 | 2024-02-27 | 2024-05-26
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR703 | Bay Street Area Safety Improvements | 9 | SUBSTANTIAL COMPLETION | 2025-01-15 | 2025-03-15 | 2024-02-26 | 2024-08-24
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR703 | Bay Street Area Safety Improvements | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-03-16 | 2025-04-14 | 2024-08-24 | 2024-11-22
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR72017 | Richmond Ave Ped Safety | 1 | DEVELOP SCOPE | 2018-06-30 | 2018-09-27 | 2018-06-01 | 2018-09-29
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR72017 | Richmond Ave Ped Safety | 2 | PRELIMINARY DESIGN | 2018-09-28 | 2019-01-25 | 2018-09-30 | 2019-01-27
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR72017 | Richmond Ave Ped Safety | 3 | FINAL DESIGN | 2019-01-26 | 2019-07-24 | 2019-01-28 | 2019-07-26
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR72017 | Richmond Ave Ped Safety | 4 | BID AWARD AND REGISTER CONTRCT | 2019-07-25 | 2019-10-22 | 2019-07-27 | 2019-10-24
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR72017 | Richmond Ave Ped Safety | 5 | CONSTRUCTION TO 25% | 2019-10-23 | 2020-02-19 | 2019-10-25 | 2020-02-21
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR72017 | Richmond Ave Ped Safety | 6 | CONSTRUCTION TO 50% | 2020-02-20 | 2020-06-18 | 2020-02-22 | 2020-06-20
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR72017 | Richmond Ave Ped Safety | 7 | CONSTRUCTION TO 75% | 2020-06-19 | 2020-10-16 | 2020-06-21 | 2020-10-18
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR72017 | Richmond Ave Ped Safety | 8 | ORIGINAL EQUIP & FURNISHING | 2020-10-17 | 2021-01-14 | 2020-10-19 | 2021-01-16
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR72017 | Richmond Ave Ped Safety | 9 | SUBSTANTIAL COMPLETION | 2021-01-15 | 2021-03-15 | 2021-01-17 | 2021-03-17
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR72017 | Richmond Ave Ped Safety | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-16 | 2021-04-14 | 2021-03-18 | 2027-07-02
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR920 | Huguenot Park N Ride | 1 | DEVELOP SCOPE | 2018-06-30 | 2018-09-27 | 2019-06-30 | 2019-09-27
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR920 | Huguenot Park N Ride | 2 | PRELIMINARY DESIGN | 2018-09-28 | 2019-01-25 | 2019-09-28 | 2020-01-25
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR920 | Huguenot Park N Ride | 3 | FINAL DESIGN | 2019-01-26 | 2019-07-24 | 2020-01-26 | 2020-07-23
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR920 | Huguenot Park N Ride | 4 | BID AWARD AND REGISTER CONTRCT | 2019-07-25 | 2019-10-22 | 2020-07-24 | 2020-10-21
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR920 | Huguenot Park N Ride | 5 | CONSTRUCTION TO 25% | 2019-10-23 | 2020-02-19 | 2020-10-22 | 2021-02-18
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR920 | Huguenot Park N Ride | 6 | CONSTRUCTION TO 50% | 2020-02-20 | 2020-06-18 | 2021-02-19 | 2021-06-18
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR920 | Huguenot Park N Ride | 7 | CONSTRUCTION TO 75% | 2020-06-19 | 2020-10-16 | 2021-06-19 | 2021-10-16
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR920 | Huguenot Park N Ride | 8 | ORIGINAL EQUIP & FURNISHING | 2020-10-17 | 2021-01-14 | 2021-10-17 | 2022-01-14
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR920 | Huguenot Park N Ride | 9 | SUBSTANTIAL COMPLETION | 2021-01-15 | 2021-03-15 | 2022-01-15 | 2022-03-15
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR920 | Huguenot Park N Ride | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-16 | 2021-04-14 | 2022-03-16 | 2027-06-30
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR921 | Mid Island Blue Belt Street Reconstruction | 1 | DEVELOP SCOPE | 2019-06-30 | 2019-09-27 | 2022-06-30 | 2022-09-27
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR921 | Mid Island Blue Belt Street Reconstruction | 2 | PRELIMINARY DESIGN | 2019-09-28 | 2020-01-25 | 2022-09-28 | 2023-01-25
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR921 | Mid Island Blue Belt Street Reconstruction | 3 | FINAL DESIGN | 2020-01-26 | 2020-07-23 | 2023-01-26 | 2023-07-24
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR921 | Mid Island Blue Belt Street Reconstruction | 4 | BID AWARD AND REGISTER CONTRCT | 2020-07-24 | 2020-10-21 | 2023-07-25 | 2023-10-22
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR921 | Mid Island Blue Belt Street Reconstruction | 5 | CONSTRUCTION TO 25% | 2020-10-22 | 2021-02-18 | 2023-10-23 | 2024-02-19
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR921 | Mid Island Blue Belt Street Reconstruction | 6 | CONSTRUCTION TO 50% | 2021-02-19 | 2021-06-18 | 2024-02-20 | 2024-06-18
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR921 | Mid Island Blue Belt Street Reconstruction | 7 | CONSTRUCTION TO 75% | 2021-06-19 | 2021-10-16 | 2024-06-19 | 2024-10-16
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR921 | Mid Island Blue Belt Street Reconstruction | 8 | ORIGINAL EQUIP & FURNISHING | 2021-10-17 | 2022-01-14 | 2024-10-17 | 2025-01-14
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR921 | Mid Island Blue Belt Street Reconstruction | 9 | SUBSTANTIAL COMPLETION | 2022-01-15 | 2022-03-15 | 2025-01-15 | 2025-03-15
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR921 | Mid Island Blue Belt Street Reconstruction | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-16 | 2022-04-14 | 2025-03-16 | 2025-04-14
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWS2021R | PRIOR NOTICE SIDEWALK - STATEN ISLAND | 1 | DEVELOP SCOPE | 2020-02-24 | 2020-03-24 | 2020-02-24 | 2020-03-24
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWS2021R | PRIOR NOTICE SIDEWALK - STATEN ISLAND | 2 | DESIGN START | 2020-03-25 | 2020-09-15 | 2020-03-25 | 2020-09-15
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWS2021R | PRIOR NOTICE SIDEWALK - STATEN ISLAND | 3 | CONSTRUCTION START | 2020-09-16 | 2021-06-30 | 2020-09-16 | 2021-06-30
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWSCD50 | Sidewalk Construction in Council District 50 | 1 | DEVELOP SCOPE | 2020-06-30 | 2020-09-27 | 2021-06-30 | 2021-09-27
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWSCD50 | Sidewalk Construction in Council District 50 | 2 | PRELIMINARY DESIGN | 2020-09-28 | 2021-01-25 | 2021-09-28 | 2022-01-25
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWSCD50 | Sidewalk Construction in Council District 50 | 3 | FINAL DESIGN | 2021-01-26 | 2021-07-24 | 2022-01-26 | 2022-07-24
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWSCD50 | Sidewalk Construction in Council District 50 | 4 | BID AWARD AND REGISTER CONTRCT | 2021-07-25 | 2021-10-22 | 2022-07-25 | 2022-10-22
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWSCD50 | Sidewalk Construction in Council District 50 | 5 | CONSTRUCTION TO 25% | 2021-10-23 | 2022-02-19 | 2022-10-23 | 2023-02-19
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWSCD50 | Sidewalk Construction in Council District 50 | 6 | CONSTRUCTION TO 50% | 2022-02-20 | 2022-06-19 | 2023-02-20 | 2023-06-19
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWSCD50 | Sidewalk Construction in Council District 50 | 7 | CONSTRUCTION TO 75% | 2022-06-20 | 2022-10-17 | 2023-06-20 | 2023-10-17
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWSCD50 | Sidewalk Construction in Council District 50 | 8 | ORIGINAL EQUIP & FURNISHING | 2022-10-18 | 2023-01-15 | 2023-10-18 | 2024-01-15
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWSCD50 | Sidewalk Construction in Council District 50 | 9 | SUBSTANTIAL COMPLETION | 2023-01-16 | 2023-03-16 | 2024-01-16 | 2024-03-15
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWSCD50 | Sidewalk Construction in Council District 50 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-03-17 | 2023-04-15 | 2024-03-16 | 2024-04-14
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | ITSKOREAN | Intelligent Transportation Systems on Korean Vet Pky X501.65 | 1 | BID AWARD AND REGISTER CONTRCT | 2018-06-30 | 2018-06-30 | 2019-06-30 | 2019-06-30
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | ITSKOREAN | Intelligent Transportation Systems on Korean Vet Pky X501.65 | 2 | CONSTRUCTION START | 2018-07-01 | 2018-08-14 | 2019-07-01 | 2019-08-14
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | ITSKOREAN | Intelligent Transportation Systems on Korean Vet Pky X501.65 | 3 | CONSTRUCTION COMPLETION | 2018-08-15 | 2020-03-06 | 2019-08-15 | 2021-03-06
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | SANDRF09 | FMF Emergency Generator Installation | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-09-28 | 2018-07-01 | 2018-09-28
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | SANDRF09 | FMF Emergency Generator Installation | 2 | PRELIMINARY DESIGN | 2016-09-29 | 2017-01-26 | 2018-09-29 | 2019-01-26
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | SANDRF09 | FMF Emergency Generator Installation | 3 | FINAL DESIGN | 2017-01-27 | 2017-07-25 | 2019-01-27 | 2019-07-25
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | SANDRF09 | FMF Emergency Generator Installation | 4 | BID AWARD AND REGISTER CONTRCT | 2017-07-26 | 2017-10-23 | 2019-01-03 | 2019-04-16
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | SANDRF09 | FMF Emergency Generator Installation | 5 | CONSTRUCTION TO 25% | 2017-10-24 | 2018-02-20 | 2019-04-17 | 2019-08-14
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | SANDRF09 | FMF Emergency Generator Installation | 6 | CONSTRUCTION TO 50% | 2018-02-21 | 2018-06-20 | 2019-08-15 | 2019-12-12
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | SANDRF09 | FMF Emergency Generator Installation | 7 | CONSTRUCTION TO 75% | 2018-06-21 | 2018-10-18 | 2019-12-13 | 2020-04-10
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | SANDRF09 | FMF Emergency Generator Installation | 8 | ORIGINAL EQUIP & FURNISHING | 2018-10-19 | 2019-01-16 | 2019-05-25 | 2019-08-22
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | SANDRF09 | FMF Emergency Generator Installation | 9 | SUBSTANTIAL COMPLETION | 2019-01-17 | 2019-03-17 | 2020-07-10 | 2020-09-07
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | SANDRF09 | FMF Emergency Generator Installation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-03-18 | 2019-04-16 | 2020-09-08 | 2021-10-07
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | SANDSIFMF | SIF FACILITIES RESTORATION & REPLACEMENT - HURRICANE SANDY | 1 | DEVELOP SCOPE | 2013-06-30 | 2014-06-29 | 2019-06-30 | 2020-06-28
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | SANDSIFMF | SIF FACILITIES RESTORATION & REPLACEMENT - HURRICANE SANDY | 2 | DESIGN START | 2014-06-30 | 2016-06-28 | 2020-06-29 | 2022-06-28
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | SANDSIFMF | SIF FACILITIES RESTORATION & REPLACEMENT - HURRICANE SANDY | 3 | CONSTRUCTION START | 2016-06-29 | 2018-06-28 | 2022-06-29 | 2024-06-27
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | STGTELPAN | St. George Terminal Electrical Panel Upgrade | 1 | DEVELOP SCOPE | 2016-06-01 | 2017-05-31 | 2017-06-01 | 2018-05-31
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | STGTELPAN | St. George Terminal Electrical Panel Upgrade | 2 | DESIGN START | 2017-06-01 | 2019-05-31 | 2018-06-01 | 2020-05-30
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | STGTELPAN | St. George Terminal Electrical Panel Upgrade | 3 | CONSTRUCTION START | 2019-06-01 | 2021-05-30 | 2020-05-31 | 2024-05-30
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | STGTROOF | Reconstruction of St.George Terminal Roof | 1 | DEVELOP SCOPE | 2016-06-01 | 2017-05-31 | 2016-06-01 | 2017-05-31
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | STGTROOF | Reconstruction of St.George Terminal Roof | 2 | DESIGN START | 2017-06-01 | 2019-05-31 | 2017-06-01 | 2019-05-31
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | STGTROOF | Reconstruction of St.George Terminal Roof | 3 | CONSTRUCTION START | 2019-06-01 | 2021-05-30 | 2019-06-01 | 2021-05-30
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | STGWIRERP | ST. GEORGE FERRY SLIPS WIRE ROPES, X823.66 | 1 | DEVELOP SCOPE | 2014-06-30 | 2015-06-29 | 2017-06-30 | 2018-06-29
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | STGWIRERP | ST. GEORGE FERRY SLIPS WIRE ROPES, X823.66 | 2 | DESIGN START | 2015-06-30 | 2017-06-28 | 2018-06-30 | 2019-06-28
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | STGWIRERP | ST. GEORGE FERRY SLIPS WIRE ROPES, X823.66 | 3 | CONSTRUCTION START | 2017-06-29 | 2019-06-28 | 2019-06-29 | 2026-06-30
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | TFD503-07 | GREAT KILLS MUNICIPAL PARKING LOT LIGHTING | 1 | BID AWARD AND REGISTER CONTRCT | 2005-05-15 | 2005-05-15 | 2019-05-15 | 2019-05-15
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | TFD503-07 | GREAT KILLS MUNICIPAL PARKING LOT LIGHTING | 2 | CONSTRUCTION START | 2005-05-16 | 2005-06-29 | 2019-05-16 | 2019-06-29
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | TFD503-07 | GREAT KILLS MUNICIPAL PARKING LOT LIGHTING | 3 | CONSTRUCTION COMPLETION | 2005-06-30 | 2007-01-20 | 2019-06-30 | 2024-06-20
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | TFR0103 | Smart Lights-various locations Staten Island | 1 | BID AWARD AND REGISTER CONTRCT | 2013-06-30 | 2013-06-30 | 2020-06-30 | 2020-06-30
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | TFR0103 | Smart Lights-various locations Staten Island | 2 | CONSTRUCTION START | 2013-07-01 | 2013-08-14 | 2020-07-01 | 2020-08-14
20201123 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | TFR0103 | Smart Lights-various locations Staten Island | 3 | CONSTRUCTION COMPLETION | 2013-08-15 | 2015-03-07 | 2020-08-15 | 2022-03-07
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | HWPLZ001R | Van Name/Van Pelt Plaza | 1 | DEVELOP SCOPE | 2014-06-30 | 2014-09-27 | 2014-06-30 | 2014-09-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | HWPLZ001R | Van Name/Van Pelt Plaza | 2 | PRELIMINARY DESIGN | 2014-09-28 | 2015-01-25 | 2014-09-28 | 2015-01-25
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | HWPLZ001R | Van Name/Van Pelt Plaza | 3 | FINAL DESIGN | 2015-01-26 | 2015-07-24 | 2015-01-26 | 2015-07-24
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | HWPLZ001R | Van Name/Van Pelt Plaza | 4 | BID AWARD AND REGISTER CONTRCT | 2015-07-25 | 2015-10-22 | 2015-07-25 | 2015-10-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | HWPLZ001R | Van Name/Van Pelt Plaza | 5 | CONSTRUCTION TO 25% | 2015-10-23 | 2016-02-19 | 2015-10-23 | 2016-02-19
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | HWPLZ001R | Van Name/Van Pelt Plaza | 6 | CONSTRUCTION TO 50% | 2016-02-20 | 2016-06-18 | 2016-02-20 | 2016-06-18
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | HWPLZ001R | Van Name/Van Pelt Plaza | 7 | CONSTRUCTION TO 75% | 2016-06-19 | 2016-10-16 | 2016-06-19 | 2016-10-16
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | HWPLZ001R | Van Name/Van Pelt Plaza | 8 | ORIGINAL EQUIP & FURNISHING | 2016-10-17 | 2017-01-14 | 2016-10-17 | 2017-01-14
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | HWPLZ001R | Van Name/Van Pelt Plaza | 9 | SUBSTANTIAL COMPLETION | 2017-01-15 | 2017-03-15 | 2017-01-15 | 2017-03-15
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | HWPLZ001R | Van Name/Van Pelt Plaza | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-16 | 2017-04-14 | 2017-03-16 | 2017-04-14
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | NDF-CRLYN | NDF-Cromwell Rec Center RC | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | NDF-CRLYN | NDF-Cromwell Rec Center RC | 2 | DESIGN | 2019-12-28 | 2021-12-26 | 2019-12-28 | 2021-12-26
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | NDF-CRLYN | NDF-Cromwell Rec Center RC | 3 | BID/ REGISTER CONTRACT | 2021-12-27 | 2022-09-22 | 2021-12-27 | 2022-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | NDF-CRLYN | NDF-Cromwell Rec Center RC | 4 | CONSTRUCTION | 2022-09-23 | 2024-09-21 | 2022-09-23 | 2024-09-21
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | NDF-CRLYN | NDF-Cromwell Rec Center RC | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-09-22 | 2025-09-21 | 2024-09-22 | 2025-09-21
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | NDF-VHALL | NDF-Village Hall Roof | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | NDF-VHALL | NDF-Village Hall Roof | 2 | DESIGN | 2019-12-28 | 2021-12-26 | 2019-12-28 | 2021-12-26
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | NDF-VHALL | NDF-Village Hall Roof | 3 | BID/ REGISTER CONTRACT | 2021-12-27 | 2022-09-22 | 2021-12-27 | 2022-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | NDF-VHALL | NDF-Village Hall Roof | 4 | CONSTRUCTION | 2022-09-23 | 2024-09-21 | 2022-09-23 | 2024-09-21
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | NDF-VHALL | NDF-Village Hall Roof | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-09-22 | 2025-09-21 | 2024-09-22 | 2025-09-21
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-500BEAC | STATEN ISLAND BIKEWAY & CULTURAL TRAIL & BIKEWAY/ RG-500M | 3 | BID/ REGISTER CONTRACT | 2004-02-15 | 2004-05-15 | 2004-11-08 | 2005-07-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-500BEAC | STATEN ISLAND BIKEWAY & CULTURAL TRAIL & BIKEWAY/ RG-500M | 4 | CONSTRUCTION | 2004-05-16 | 2005-05-15 | 2005-12-05 | 2006-06-01
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-500BEAC | STATEN ISLAND BIKEWAY & CULTURAL TRAIL & BIKEWAY/ RG-500M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2005-05-16 | 2006-05-15 | 2006-06-02 | 2007-06-28
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-500RINK | Recon condenser at WW2 Memorial Rink, SI R005-119M | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-500RINK | Recon condenser at WW2 Memorial Rink, SI R005-119M | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-500RINK | Recon condenser at WW2 Memorial Rink, SI R005-119M | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-500RINK | Recon condenser at WW2 Memorial Rink, SI R005-119M | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-500RINK | Recon condenser at WW2 Memorial Rink, SI R005-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501ALAS | Alice Austen House-Landscape & Site Impr. R117- | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2015-09-28
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501ALAS | Alice Austen House-Landscape & Site Impr. R117- | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2015-09-29 | 2015-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501ALAS | Alice Austen House-Landscape & Site Impr. R117- | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2015-12-28 | 2016-03-26
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501ALAS | Alice Austen House-Landscape & Site Impr. R117- | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501ALAS | Alice Austen House-Landscape & Site Impr. R117- | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2017-03-27 | 2022-12-31
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501ALIC | Alice Austen House-Exterior Lighting & Security System | 1 | DEVELOP SCOPE | 2007-07-01 | 2007-09-28 | 2007-07-01 | 2007-09-28
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501ALIC | Alice Austen House-Exterior Lighting & Security System | 2 | DESIGN | 2007-09-29 | 2007-12-27 | 2009-03-06 | 2009-06-05
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501ALIC | Alice Austen House-Exterior Lighting & Security System | 3 | BID/ REGISTER CONTRACT | 2007-12-28 | 2008-03-26 | 2007-12-28 | 2008-03-26
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501ALIC | Alice Austen House-Exterior Lighting & Security System | 4 | CONSTRUCTION | 2008-03-27 | 2009-03-26 | 2008-03-27 | 2009-03-26
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501ALIC | Alice Austen House-Exterior Lighting & Security System | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2009-03-27 | 2010-03-26 | 2009-03-27 | 2021-12-31
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501BRE1 | MCFARLANE-BREDT HOUSE R117-110MA | 1 | DEVELOP SCOPE | 2007-07-01 | 2007-09-28 | 2007-07-01 | 2007-09-28
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501BRE1 | MCFARLANE-BREDT HOUSE R117-110MA | 2 | DESIGN | 2007-09-29 | 2007-12-27 | 2007-09-29 | 2007-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501BRE1 | MCFARLANE-BREDT HOUSE R117-110MA | 3 | BID/ REGISTER CONTRACT | 2007-12-28 | 2008-03-26 | 2007-12-28 | 2008-03-26
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501BRE1 | MCFARLANE-BREDT HOUSE R117-110MA | 4 | CONSTRUCTION | 2008-03-27 | 2009-03-26 | 2008-03-27 | 2009-03-26
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501BRE1 | MCFARLANE-BREDT HOUSE R117-110MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2009-03-27 | 2010-03-26 | 2009-03-27 | 2011-10-31
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501CLEX | Clove Lakes Pk-Adult Exercise Equipment R005-118M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501CLEX | Clove Lakes Pk-Adult Exercise Equipment R005-118M | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501CLEX | Clove Lakes Pk-Adult Exercise Equipment R005-118M | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501CLEX | Clove Lakes Pk-Adult Exercise Equipment R005-118M | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501CLEX | Clove Lakes Pk-Adult Exercise Equipment R005-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501CLP2 | Cloves Lakes Walking Path Rehab R005 | 1 | DEVELOP SCOPE | 2020-07-01 | 2020-12-27 | 2020-07-01 | 2020-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501CLP2 | Cloves Lakes Walking Path Rehab R005 | 2 | DESIGN | 2020-12-28 | 2021-09-23 | 2020-12-28 | 2021-09-23
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501CLP2 | Cloves Lakes Walking Path Rehab R005 | 3 | BID/ REGISTER CONTRACT | 2021-09-24 | 2022-06-20 | 2021-09-24 | 2022-06-20
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501CLP2 | Cloves Lakes Walking Path Rehab R005 | 4 | CONSTRUCTION | 2022-06-21 | 2024-12-16 | 2022-06-21 | 2024-12-16
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501CLP2 | Cloves Lakes Walking Path Rehab R005 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-12-17 | 2026-12-16 | 2024-12-17 | 2026-12-16
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501FABB | Faber & Lyons Pools -Boiler & Heater Replacement RG-714M | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2014-04-04
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501FABB | Faber & Lyons Pools -Boiler & Heater Replacement RG-714M | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2014-04-05 | 2015-06-24
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501FABB | Faber & Lyons Pools -Boiler & Heater Replacement RG-714M | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2015-06-25 | 2015-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501FABB | Faber & Lyons Pools -Boiler & Heater Replacement RG-714M | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2015-09-23 | 2017-09-21
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501FABB | Faber & Lyons Pools -Boiler & Heater Replacement RG-714M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2017-09-22 | 2022-09-21
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501FABL | Faber Park-Install of active recreation, lighting-R008-117M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501FABL | Faber Park-Install of active recreation, lighting-R008-117M | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501FABL | Faber Park-Install of active recreation, lighting-R008-117M | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501FABL | Faber Park-Install of active recreation, lighting-R008-117M | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501FABL | Faber Park-Install of active recreation, lighting-R008-117M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501FPFA | Faber Park Rec. Center: Fire Alarm Reconstruction | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501FPFA | Faber Park Rec. Center: Fire Alarm Reconstruction | 2 | DESIGN | 2019-12-28 | 2021-12-26 | 2019-12-28 | 2021-12-26
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501FPFA | Faber Park Rec. Center: Fire Alarm Reconstruction | 3 | BID/ REGISTER CONTRACT | 2021-12-27 | 2022-09-22 | 2021-12-27 | 2022-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501FPFA | Faber Park Rec. Center: Fire Alarm Reconstruction | 4 | CONSTRUCTION | 2022-09-23 | 2025-09-21 | 2022-09-23 | 2025-09-21
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501FPFA | Faber Park Rec. Center: Fire Alarm Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-09-22 | 2027-09-21 | 2025-09-22 | 2027-09-21
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501LLCS | Luis Lopez Park Modular Comfort Station Construction | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501LLCS | Luis Lopez Park Modular Comfort Station Construction | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501LLCS | Luis Lopez Park Modular Comfort Station Construction | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501LLCS | Luis Lopez Park Modular Comfort Station Construction | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501LLCS | Luis Lopez Park Modular Comfort Station Construction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501LPFA | Lyons Pool Rec. Center: Fire Alarm Reconstruction | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501LPFA | Lyons Pool Rec. Center: Fire Alarm Reconstruction | 2 | DESIGN | 2019-12-28 | 2021-12-26 | 2019-12-28 | 2021-12-26
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501LPFA | Lyons Pool Rec. Center: Fire Alarm Reconstruction | 3 | BID/ REGISTER CONTRACT | 2021-12-27 | 2022-09-22 | 2021-12-27 | 2022-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501LPFA | Lyons Pool Rec. Center: Fire Alarm Reconstruction | 4 | CONSTRUCTION | 2022-09-23 | 2025-09-21 | 2022-09-23 | 2025-09-21
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501LPFA | Lyons Pool Rec. Center: Fire Alarm Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-09-22 | 2027-09-21 | 2025-09-22 | 2027-09-21
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501MAR2 | MARINERS MARSH | 1 | DEVELOP SCOPE | 2010-07-01 | 2010-09-28 | 2010-07-01 | 2010-09-28
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501MAR2 | MARINERS MARSH | 2 | DESIGN | 2010-09-29 | 2010-12-27 | 2010-09-29 | 2010-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501MAR2 | MARINERS MARSH | 3 | BID/ REGISTER CONTRACT | 2010-12-28 | 2011-03-27 | 2010-12-28 | 2011-03-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501MAR2 | MARINERS MARSH | 4 | CONSTRUCTION | 2011-03-28 | 2012-03-26 | 2011-03-28 | 2012-03-26
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501MAR2 | MARINERS MARSH | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-03-27 | 2013-03-26 | 2012-03-27 | 2024-12-01
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501NAPL | Naple Plgr-Reconstruction R073-119M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501NAPL | Naple Plgr-Reconstruction R073-119M | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501NAPL | Naple Plgr-Reconstruction R073-119M | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501NAPL | Naple Plgr-Reconstruction R073-119M | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501NAPL | Naple Plgr-Reconstruction R073-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501SIB2 | S.I.B.G-Tuscan Garden & Lemon House R116-105M/405M | 1 | DEVELOP SCOPE | 2003-07-01 | 2003-09-28 | 2003-07-01 | 2003-09-28
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501SIB2 | S.I.B.G-Tuscan Garden & Lemon House R116-105M/405M | 2 | DESIGN | 2003-09-29 | 2004-03-15 | 2003-09-29 | 2004-03-15
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501SIB2 | S.I.B.G-Tuscan Garden & Lemon House R116-105M/405M | 3 | BID/ REGISTER CONTRACT | 2004-04-01 | 2004-06-30 | 2004-04-01 | 2004-06-30
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501SIB2 | S.I.B.G-Tuscan Garden & Lemon House R116-105M/405M | 4 | CONSTRUCTION | 2004-09-01 | 2005-08-31 | 2004-09-01 | 2005-08-31
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501SIB2 | S.I.B.G-Tuscan Garden & Lemon House R116-105M/405M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2005-09-01 | 2006-08-31 | 2016-12-31 | 2021-12-31
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501WEPE | WesterleighPk-Play Equipment | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501WEPE | WesterleighPk-Play Equipment | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501WEPE | WesterleighPk-Play Equipment | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501WEPE | WesterleighPk-Play Equipment | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501WEPE | WesterleighPk-Play Equipment | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2024-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501WOOD | PARK ON DRUMGOOLE RD EAST CONSTRUCTION - RG-12400-102M | 1 | DEVELOP SCOPE | 2001-07-01 | 2001-12-14 | 2001-07-01 | 2001-12-14
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501WOOD | PARK ON DRUMGOOLE RD EAST CONSTRUCTION - RG-12400-102M | 2 | DESIGN | 2001-12-15 | 2004-01-14 | 2001-12-15 | 2004-01-14
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501WOOD | PARK ON DRUMGOOLE RD EAST CONSTRUCTION - RG-12400-102M | 3 | BID/ REGISTER CONTRACT | 2004-03-15 | 2004-06-15 | 2004-03-15 | 2004-06-15
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501WOOD | PARK ON DRUMGOOLE RD EAST CONSTRUCTION - RG-12400-102M | 4 | CONSTRUCTION | 2004-06-16 | 2005-06-16 | 2004-06-16 | 2005-06-16
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501WOOD | PARK ON DRUMGOOLE RD EAST CONSTRUCTION - RG-12400-102M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2005-06-17 | 2006-06-16 | 2005-06-17 | 2006-06-16
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-502CTPK | MIDLAND BEACH PROMENADE ENTRY PLAZA & PARKING LT R046-107MA2 | 1 | DEVELOP SCOPE | 2006-07-01 | 2006-09-28 | 2006-07-01 | 2008-03-28
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-502CTPK | MIDLAND BEACH PROMENADE ENTRY PLAZA & PARKING LT R046-107MA2 | 2 | DESIGN | 2006-09-29 | 2006-12-27 | 2008-03-29 | 2011-01-03
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-502CTPK | MIDLAND BEACH PROMENADE ENTRY PLAZA & PARKING LT R046-107MA2 | 3 | BID/ REGISTER CONTRACT | 2006-12-28 | 2007-03-27 | 2011-01-04 | 2011-01-03
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-502CTPK | MIDLAND BEACH PROMENADE ENTRY PLAZA & PARKING LT R046-107MA2 | 4 | CONSTRUCTION | 2007-03-28 | 2008-03-26 | 2011-01-04 | 2011-01-03
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-502CTPK | MIDLAND BEACH PROMENADE ENTRY PLAZA & PARKING LT R046-107MA2 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-27 | 2009-03-26 | 2011-01-04 | 2018-03-29
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-502GBFA | Greenbelt Rec. Center: Fire Alarm Reconstruction | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-502GBFA | Greenbelt Rec. Center: Fire Alarm Reconstruction | 2 | DESIGN | 2019-12-28 | 2021-12-26 | 2019-12-28 | 2021-12-26
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-502GBFA | Greenbelt Rec. Center: Fire Alarm Reconstruction | 3 | BID/ REGISTER CONTRACT | 2021-12-27 | 2022-09-22 | 2021-12-27 | 2022-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-502GBFA | Greenbelt Rec. Center: Fire Alarm Reconstruction | 4 | CONSTRUCTION | 2022-09-23 | 2025-09-21 | 2022-09-23 | 2025-09-21
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-502GBFA | Greenbelt Rec. Center: Fire Alarm Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-09-22 | 2027-09-21 | 2025-09-22 | 2027-09-21
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-502NDPK | New Dorp Center Kitchen Recon. (R016-214MA) | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-502NDPK | New Dorp Center Kitchen Recon. (R016-214MA) | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-502NDPK | New Dorp Center Kitchen Recon. (R016-214MA) | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-502NDPK | New Dorp Center Kitchen Recon. (R016-214MA) | 4 | CONSTRUCTION | 2019-09-24 | 2021-03-21 | 2019-09-24 | 2021-03-21
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-502NDPK | New Dorp Center Kitchen Recon. (R016-214MA) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-22 | 2022-03-21 | 2021-03-22 | 2022-03-21
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-502PIER | MIDLAND BEACH RECREATIONAL PIER & C/S / R046-100M/400M | 1 | DEVELOP SCOPE | 1998-07-01 | 2000-07-25 | 1998-07-01 | 2000-07-25
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-502PIER | MIDLAND BEACH RECREATIONAL PIER & C/S / R046-100M/400M | 2 | DESIGN | 2000-08-01 | 2001-04-13 | 2000-08-01 | 2001-04-13
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-502PIER | MIDLAND BEACH RECREATIONAL PIER & C/S / R046-100M/400M | 3 | BID/ REGISTER CONTRACT | 2001-04-30 | 2001-12-06 | 2001-04-30 | 2001-12-06
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-502PIER | MIDLAND BEACH RECREATIONAL PIER & C/S / R046-100M/400M | 4 | CONSTRUCTION | 2002-01-22 | 2003-04-16 | 2002-01-22 | 2003-04-16
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-502PIER | MIDLAND BEACH RECREATIONAL PIER & C/S / R046-100M/400M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2003-04-17 | 2004-04-15 | 2003-04-17 | 2021-04-15
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503BFDS | Ballfields in Dugan & Schmul parks | 1 | DEVELOP SCOPE | 2014-07-01 | 2014-09-28 | 2014-07-01 | 2014-09-28
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503BFDS | Ballfields in Dugan & Schmul parks | 2 | DESIGN | 2014-09-29 | 2014-12-27 | 2014-09-29 | 2014-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503BFDS | Ballfields in Dugan & Schmul parks | 3 | BID/ REGISTER CONTRACT | 2014-12-28 | 2015-03-27 | 2015-04-27 | 2016-01-14
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503BFDS | Ballfields in Dugan & Schmul parks | 4 | CONSTRUCTION | 2015-03-28 | 2016-03-26 | 2016-03-28 | 2017-06-14
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503BFDS | Ballfields in Dugan & Schmul parks | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-27 | 2017-03-26 | 2017-06-15 | 2021-12-31
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503CHP1 | Conference House Park Pavilion R006-213M | 1 | DEVELOP SCOPE | 2012-07-01 | 2012-09-28 | 2012-07-01 | 2012-09-28
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503CHP1 | Conference House Park Pavilion R006-213M | 2 | DESIGN | 2012-09-29 | 2012-12-27 | 2012-09-29 | 2012-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503CHP1 | Conference House Park Pavilion R006-213M | 3 | BID/ REGISTER CONTRACT | 2012-12-28 | 2013-03-27 | 2012-12-28 | 2013-03-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503CHP1 | Conference House Park Pavilion R006-213M | 4 | CONSTRUCTION | 2013-03-28 | 2014-03-27 | 2013-03-28 | 2014-03-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503CHP1 | Conference House Park Pavilion R006-213M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-03-28 | 2015-03-27 | 2014-03-28 | 2021-12-31
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503CHPV | Conference House Park Pavilion | 1 | DEVELOP SCOPE | 2012-07-01 | 2012-09-28 | 2012-07-01 | 2012-07-17
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503CHPV | Conference House Park Pavilion | 2 | DESIGN | 2012-09-29 | 2012-12-27 | 2012-07-18 | 2012-08-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503CHPV | Conference House Park Pavilion | 3 | BID/ REGISTER CONTRACT | 2012-12-28 | 2013-03-27 | 2012-08-02 | 2012-11-08
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503CHPV | Conference House Park Pavilion | 4 | CONSTRUCTION | 2013-03-28 | 2014-03-27 | 2012-08-13 | 2012-09-21
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503CHPV | Conference House Park Pavilion | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-03-28 | 2015-03-27 | 2012-09-22 | 2023-12-31
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503CRBP | CRESCENT BEACH PARK CONS 135-113MA | 1 | DEVELOP SCOPE | 2008-07-01 | 2008-09-28 | 2008-07-01 | 2011-06-15
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503CRBP | CRESCENT BEACH PARK CONS 135-113MA | 2 | DESIGN | 2008-09-29 | 2008-12-27 | 2011-06-16 | 2011-09-13
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503CRBP | CRESCENT BEACH PARK CONS 135-113MA | 3 | BID/ REGISTER CONTRACT | 2008-12-28 | 2009-03-27 | 2011-09-14 | 2011-12-12
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503CRBP | CRESCENT BEACH PARK CONS 135-113MA | 4 | CONSTRUCTION | 2009-03-28 | 2010-03-27 | 2011-12-13 | 2012-12-11
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503CRBP | CRESCENT BEACH PARK CONS 135-113MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2010-03-28 | 2011-03-27 | 2012-12-12 | 2018-11-15
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503DUPL | DUGAN PLAYGROUND R/C R026- | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503DUPL | DUGAN PLAYGROUND R/C R026- | 2 | DESIGN | 2018-12-28 | 2020-12-26 | 2018-12-28 | 2020-12-26
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503DUPL | DUGAN PLAYGROUND R/C R026- | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503DUPL | DUGAN PLAYGROUND R/C R026- | 4 | CONSTRUCTION | 2021-09-23 | 2023-09-22 | 2021-09-23 | 2023-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503DUPL | DUGAN PLAYGROUND R/C R026- | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-23 | 2024-09-21 | 2023-09-23 | 2024-09-21
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503GCPG | Greencroft Playgroud R089 | 1 | DEVELOP SCOPE | 2020-07-01 | 2020-12-27 | 2020-07-01 | 2020-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503GCPG | Greencroft Playgroud R089 | 2 | DESIGN | 2020-12-28 | 2021-12-27 | 2020-12-28 | 2021-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503GCPG | Greencroft Playgroud R089 | 3 | BID/ REGISTER CONTRACT | 2021-12-28 | 2022-09-23 | 2021-12-28 | 2022-09-23
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503GCPG | Greencroft Playgroud R089 | 4 | CONSTRUCTION | 2022-09-24 | 2023-09-23 | 2022-09-24 | 2023-09-23
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503GCPG | Greencroft Playgroud R089 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-24 | 2024-09-22 | 2023-09-24 | 2024-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503GCPL | Greencroft Plgr- R/C of Comfort Station R089-115M | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2015-05-18
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503GCPL | Greencroft Plgr- R/C of Comfort Station R089-115M | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2015-05-19 | 2017-08-16
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503GCPL | Greencroft Plgr- R/C of Comfort Station R089-115M | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2017-08-17 | 2017-11-14
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503GCPL | Greencroft Plgr- R/C of Comfort Station R089-115M | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2017-11-15 | 2018-11-14
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503GCPL | Greencroft Plgr- R/C of Comfort Station R089-115M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2018-11-15 | 2021-11-14
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503HUG | HUGEUNOT PONDS PARK EXPANSION | 1 | DEVELOP SCOPE | 2009-07-01 | 2009-09-28 | 2009-07-01 | 2009-09-28
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503HUG | HUGEUNOT PONDS PARK EXPANSION | 2 | DESIGN | 2009-09-29 | 2009-12-27 | 2009-09-29 | 2009-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503HUG | HUGEUNOT PONDS PARK EXPANSION | 3 | BID/ REGISTER CONTRACT | 2009-12-28 | 2010-03-27 | 2009-12-28 | 2010-03-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503HUG | HUGEUNOT PONDS PARK EXPANSION | 4 | CONSTRUCTION | 2010-03-28 | 2011-03-27 | 2010-03-28 | 2011-03-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503HUG | HUGEUNOT PONDS PARK EXPANSION | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2011-03-28 | 2012-03-26 | 2011-03-28 | 2024-12-31
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503SNCS | Seaside Nature Pk CS construction R145-119M | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2017-09-28
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503SNCS | Seaside Nature Pk CS construction R145-119M | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2017-09-29 | 2017-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503SNCS | Seaside Nature Pk CS construction R145-119M | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2017-12-28 | 2018-03-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503SNCS | Seaside Nature Pk CS construction R145-119M | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2018-03-28 | 2019-03-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503SNCS | Seaside Nature Pk CS construction R145-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2019-03-28 | 2020-03-26
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503TLCH | Conference House Tot Lot (Lenape plgr) RG-212M WO5 | 1 | DEVELOP SCOPE | 2014-07-01 | 2014-09-28 | 2014-07-01 | 2014-09-28
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503TLCH | Conference House Tot Lot (Lenape plgr) RG-212M WO5 | 2 | DESIGN | 2014-09-29 | 2014-12-27 | 2014-09-29 | 2014-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503TLCH | Conference House Tot Lot (Lenape plgr) RG-212M WO5 | 3 | BID/ REGISTER CONTRACT | 2014-12-28 | 2015-03-27 | 2014-12-28 | 2015-03-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503TLCH | Conference House Tot Lot (Lenape plgr) RG-212M WO5 | 4 | CONSTRUCTION | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2016-03-26
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503TLCH | Conference House Tot Lot (Lenape plgr) RG-212M WO5 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503TOTT | Tottenville Shoreline Protection - Staten Island | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503TOTT | Tottenville Shoreline Protection - Staten Island | 2 | DESIGN | 2018-12-28 | 2020-03-21 | 2018-12-28 | 2020-03-21
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503TOTT | Tottenville Shoreline Protection - Staten Island | 3 | BID/ REGISTER CONTRACT | 2020-03-22 | 2020-12-16 | 2020-03-22 | 2020-12-16
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503TOTT | Tottenville Shoreline Protection - Staten Island | 4 | CONSTRUCTION | 2020-12-17 | 2022-12-16 | 2020-12-17 | 2022-12-16
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503TOTT | Tottenville Shoreline Protection - Staten Island | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-12-17 | 2023-12-16 | 2022-12-17 | 2023-12-16
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5ALTARF | Recon of Roofing systems at Altamont | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5ALTARF | Recon of Roofing systems at Altamont | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5ALTARF | Recon of Roofing systems at Altamont | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5ALTARF | Recon of Roofing systems at Altamont | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5ALTARF | Recon of Roofing systems at Altamont | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5ANCH01 | Anchor Park Site - South Pk Fresh kills DESIGN | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5ANCH01 | Anchor Park Site - South Pk Fresh kills DESIGN | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2016-12-28 | 2019-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5ANCH01 | Anchor Park Site - South Pk Fresh kills DESIGN | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2019-12-28 | 2020-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5ANCH01 | Anchor Park Site - South Pk Fresh kills DESIGN | 4 | CONSTRUCTION | 2018-09-24 | 2019-09-23 | 2020-09-23 | 2021-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5ANCH01 | Anchor Park Site - South Pk Fresh kills DESIGN | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-24 | 2020-09-22 | 2021-09-23 | 2022-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5ANCH02 | Anchor Park Site - South Pk Construction /Fresh kills | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5ANCH02 | Anchor Park Site - South Pk Construction /Fresh kills | 2 | DESIGN | 2019-12-28 | 2021-12-26 | 2019-12-28 | 2021-12-26
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5ANCH02 | Anchor Park Site - South Pk Construction /Fresh kills | 3 | BID/ REGISTER CONTRACT | 2021-12-27 | 2022-09-22 | 2021-12-27 | 2022-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5ANCH02 | Anchor Park Site - South Pk Construction /Fresh kills | 4 | CONSTRUCTION | 2022-09-23 | 2024-09-21 | 2022-09-23 | 2024-09-21
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5ANCH02 | Anchor Park Site - South Pk Construction /Fresh kills | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-09-22 | 2025-09-21 | 2024-09-22 | 2025-09-21
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5ANCH03 | Anchor Park Site - South Pk CS /Fresh kills | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5ANCH03 | Anchor Park Site - South Pk CS /Fresh kills | 2 | DESIGN | 2019-12-28 | 2021-12-26 | 2019-12-28 | 2021-12-26
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5ANCH03 | Anchor Park Site - South Pk CS /Fresh kills | 3 | BID/ REGISTER CONTRACT | 2021-12-27 | 2022-09-22 | 2021-12-27 | 2022-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5ANCH03 | Anchor Park Site - South Pk CS /Fresh kills | 4 | CONSTRUCTION | 2022-09-23 | 2024-09-21 | 2022-09-23 | 2024-09-21
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5ANCH03 | Anchor Park Site - South Pk CS /Fresh kills | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-09-22 | 2025-09-21 | 2024-09-22 | 2025-09-21
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5ARDTR | Arden Heights Wood -Trails & Parking R120-117M | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5ARDTR | Arden Heights Wood -Trails & Parking R120-117M | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2016-12-28 | 2017-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5ARDTR | Arden Heights Wood -Trails & Parking R120-117M | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2017-12-28 | 2018-09-23
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5ARDTR | Arden Heights Wood -Trails & Parking R120-117M | 4 | CONSTRUCTION | 2018-09-24 | 2019-09-23 | 2018-09-24 | 2019-09-23
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5ARDTR | Arden Heights Wood -Trails & Parking R120-117M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2022-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5BBPAV | Multisite SI-Basketball Cours paving R | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5BBPAV | Multisite SI-Basketball Cours paving R | 2 | DESIGN | 2017-12-28 | 2019-06-25 | 2017-12-28 | 2019-06-25
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5BBPAV | Multisite SI-Basketball Cours paving R | 3 | BID/ REGISTER CONTRACT | 2019-06-26 | 2020-03-21 | 2019-06-26 | 2020-03-21
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5BBPAV | Multisite SI-Basketball Cours paving R | 4 | CONSTRUCTION | 2020-03-22 | 2021-09-17 | 2020-03-22 | 2021-09-17
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5BBPAV | Multisite SI-Basketball Cours paving R | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-18 | 2022-09-17 | 2021-09-18 | 2022-09-17
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5BEDFGR | Bedford Green-Passive landscape | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5BEDFGR | Bedford Green-Passive landscape | 2 | DESIGN | 2016-12-28 | 2018-06-25 | 2016-12-28 | 2018-06-25
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5BEDFGR | Bedford Green-Passive landscape | 3 | BID/ REGISTER CONTRACT | 2018-06-26 | 2019-03-22 | 2018-06-26 | 2019-03-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5BEDFGR | Bedford Green-Passive landscape | 4 | CONSTRUCTION | 2019-03-23 | 2020-09-17 | 2019-03-23 | 2020-09-17
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5BEDFGR | Bedford Green-Passive landscape | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-18 | 2021-09-17 | 2020-09-18 | 2024-09-17
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5BLOOJF | Bloomingdale Park Junior Fields Installation | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2015-09-28
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5BLOOJF | Bloomingdale Park Junior Fields Installation | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2015-09-29 | 2015-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5BLOOJF | Bloomingdale Park Junior Fields Installation | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2015-12-28 | 2016-03-26
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5BLOOJF | Bloomingdale Park Junior Fields Installation | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5BLOOJF | Bloomingdale Park Junior Fields Installation | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2017-03-27 | 2020-12-30
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5BLUHNC | Blue Heron Nature Center HVAC System Retrofit R119-119M | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5BLUHNC | Blue Heron Nature Center HVAC System Retrofit R119-119M | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5BLUHNC | Blue Heron Nature Center HVAC System Retrofit R119-119M | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5BLUHNC | Blue Heron Nature Center HVAC System Retrofit R119-119M | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5BLUHNC | Blue Heron Nature Center HVAC System Retrofit R119-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5BUNBCH | Buono Beach-Reconstruction of Fountain | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5BUNBCH | Buono Beach-Reconstruction of Fountain | 2 | DESIGN | 2018-12-28 | 2020-12-26 | 2018-12-28 | 2020-12-26
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5BUNBCH | Buono Beach-Reconstruction of Fountain | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5BUNBCH | Buono Beach-Reconstruction of Fountain | 4 | CONSTRUCTION | 2021-09-23 | 2023-09-22 | 2021-09-23 | 2023-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5BUNBCH | Buono Beach-Reconstruction of Fountain | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-23 | 2024-09-21 | 2023-09-23 | 2024-09-21
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CARLPK | Carlton Park & Ida Court--Basketball Courts and Field | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2016-01-29
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CARLPK | Carlton Park & Ida Court--Basketball Courts and Field | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2016-01-30 | 2017-05-05
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CARLPK | Carlton Park & Ida Court--Basketball Courts and Field | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2017-08-16 | 2017-12-12
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CARLPK | Carlton Park & Ida Court--Basketball Courts and Field | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2018-03-26 | 2018-12-12
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CARLPK | Carlton Park & Ida Court--Basketball Courts and Field | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2018-12-13 | 2021-12-31
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CHARCS | Fairview Park - Cons. Comfort Station | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CHARCS | Fairview Park - Cons. Comfort Station | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CHARCS | Fairview Park - Cons. Comfort Station | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CHARCS | Fairview Park - Cons. Comfort Station | 4 | CONSTRUCTION | 2019-09-24 | 2021-03-21 | 2019-09-24 | 2021-03-21
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CHARCS | Fairview Park - Cons. Comfort Station | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-22 | 2022-03-21 | 2021-03-22 | 2022-03-21
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CHARLS | Fairview Park Landscape Construction | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CHARLS | Fairview Park Landscape Construction | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CHARLS | Fairview Park Landscape Construction | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CHARLS | Fairview Park Landscape Construction | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CHARLS | Fairview Park Landscape Construction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CLAWS | RENOVATION OF CLAWSON PLAYGROUND | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CLAWS | RENOVATION OF CLAWSON PLAYGROUND | 2 | DESIGN | 2016-12-28 | 2018-06-20 | 2016-12-28 | 2017-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CLAWS | RENOVATION OF CLAWSON PLAYGROUND | 3 | BID/ REGISTER CONTRACT | 2018-06-21 | 2019-03-17 | 2017-12-28 | 2018-09-23
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CLAWS | RENOVATION OF CLAWSON PLAYGROUND | 4 | CONSTRUCTION | 2019-03-18 | 2020-09-07 | 2018-09-24 | 2019-09-23
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CLAWS | RENOVATION OF CLAWSON PLAYGROUND | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-08 | 2021-09-07 | 2019-09-24 | 2020-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CLVCHL | Recon chiller slab & header at Cloves Lake Park | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CLVCHL | Recon chiller slab & header at Cloves Lake Park | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CLVCHL | Recon chiller slab & header at Cloves Lake Park | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CLVCHL | Recon chiller slab & header at Cloves Lake Park | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CLVCHL | Recon chiller slab & header at Cloves Lake Park | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CLVLKP | Clove Lakes Park | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CLVLKP | Clove Lakes Park | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CLVLKP | Clove Lakes Park | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CLVLKP | Clove Lakes Park | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CLVLKP | Clove Lakes Park | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CONNFR | Conference House Pk-pathways, parking lot R006-114M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CONNFR | Conference House Pk-pathways, parking lot R006-114M | 2 | DESIGN | 2017-12-28 | 2019-03-22 | 2017-12-28 | 2019-03-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CONNFR | Conference House Pk-pathways, parking lot R006-114M | 3 | BID/ REGISTER CONTRACT | 2019-03-23 | 2019-12-17 | 2019-03-23 | 2019-12-17
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CONNFR | Conference House Pk-pathways, parking lot R006-114M | 4 | CONSTRUCTION | 2019-12-18 | 2021-12-16 | 2019-12-18 | 2021-12-16
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CONNFR | Conference House Pk-pathways, parking lot R006-114M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-12-17 | 2022-12-16 | 2021-12-17 | 2022-12-16
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CPIB12 | CPI PH1- SI COMFORT STATIONS -BUNDLE 3 RG-216MA | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CPIB12 | CPI PH1- SI COMFORT STATIONS -BUNDLE 3 RG-216MA | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CPIB12 | CPI PH1- SI COMFORT STATIONS -BUNDLE 3 RG-216MA | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CPIB12 | CPI PH1- SI COMFORT STATIONS -BUNDLE 3 RG-216MA | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CPIB12 | CPI PH1- SI COMFORT STATIONS -BUNDLE 3 RG-216MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CPIBN6 | CPI - SI Comfort Stations-Bundle 2 RG-515M | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2015-09-28
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CPIBN6 | CPI - SI Comfort Stations-Bundle 2 RG-515M | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2015-09-29 | 2015-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CPIBN6 | CPI - SI Comfort Stations-Bundle 2 RG-515M | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2015-12-28 | 2016-03-26
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CPIBN6 | CPI - SI Comfort Stations-Bundle 2 RG-515M | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CPIBN6 | CPI - SI Comfort Stations-Bundle 2 RG-515M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2017-03-27 | 2022-03-26
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CPIDMT | CPI PH1 - DeMatti Plgd | 1 | DEVELOP SCOPE | 2014-07-01 | 2014-09-28 | 2014-07-01 | 2014-12-11
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CPIDMT | CPI PH1 - DeMatti Plgd | 2 | DESIGN | 2014-09-29 | 2014-12-27 | 2014-12-12 | 2015-12-31
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CPIDMT | CPI PH1 - DeMatti Plgd | 3 | BID/ REGISTER CONTRACT | 2014-12-28 | 2015-03-27 | 2016-03-15 | 2016-07-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CPIDMT | CPI PH1 - DeMatti Plgd | 4 | CONSTRUCTION | 2015-03-28 | 2016-03-26 | 2016-09-06 | 2018-02-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CPIDMT | CPI PH1 - DeMatti Plgd | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-27 | 2017-03-26 | 2018-02-28 | 2022-02-26
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CPIMDP | CPI PH1- McDonald Playground reconstruction | 1 | DEVELOP SCOPE | 2014-07-01 | 2014-09-28 | 2014-07-01 | 2015-01-15
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CPIMDP | CPI PH1- McDonald Playground reconstruction | 2 | DESIGN | 2014-09-29 | 2014-12-27 | 2015-01-16 | 2016-01-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CPIMDP | CPI PH1- McDonald Playground reconstruction | 3 | BID/ REGISTER CONTRACT | 2014-12-28 | 2015-03-27 | 2016-03-10 | 2016-09-20
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CPIMDP | CPI PH1- McDonald Playground reconstruction | 4 | CONSTRUCTION | 2015-03-28 | 2016-03-26 | 2016-10-03 | 2018-04-20
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CPIMDP | CPI PH1- McDonald Playground reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-27 | 2017-03-26 | 2018-04-21 | 2021-12-31
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CPIMH | CPI PH2 - Mariner's Harbor Playground-RC R036-118M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CPIMH | CPI PH2 - Mariner's Harbor Playground-RC R036-118M | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CPIMH | CPI PH2 - Mariner's Harbor Playground-RC R036-118M | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CPIMH | CPI PH2 - Mariner's Harbor Playground-RC R036-118M | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CPIMH | CPI PH2 - Mariner's Harbor Playground-RC R036-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CPISTP | CPI PH2 - RC-Stapleton Playground- R061-116M | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CPISTP | CPI PH2 - RC-Stapleton Playground- R061-116M | 2 | DESIGN | 2016-12-28 | 2018-06-20 | 2016-12-28 | 2018-06-20
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CPISTP | CPI PH2 - RC-Stapleton Playground- R061-116M | 3 | BID/ REGISTER CONTRACT | 2018-06-21 | 2019-03-17 | 2018-06-21 | 2019-03-17
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CPISTP | CPI PH2 - RC-Stapleton Playground- R061-116M | 4 | CONSTRUCTION | 2019-03-18 | 2020-09-07 | 2019-03-18 | 2020-09-07
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CPISTP | CPI PH2 - RC-Stapleton Playground- R061-116M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-08 | 2021-09-07 | 2020-09-08 | 2021-09-07
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5DONGAN | Dongan Plgr-reconstruction | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5DONGAN | Dongan Plgr-reconstruction | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5DONGAN | Dongan Plgr-reconstruction | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5DONGAN | Dongan Plgr-reconstruction | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5DONGAN | Dongan Plgr-reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5FABBAS | Faber Park -Remove Equipment & Install Basketball Court | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5FABBAS | Faber Park -Remove Equipment & Install Basketball Court | 2 | DESIGN | 2018-12-28 | 2020-12-26 | 2018-12-28 | 2020-12-26
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5FABBAS | Faber Park -Remove Equipment & Install Basketball Court | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5FABBAS | Faber Park -Remove Equipment & Install Basketball Court | 4 | CONSTRUCTION | 2021-09-23 | 2023-09-22 | 2021-09-23 | 2023-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5FABBAS | Faber Park -Remove Equipment & Install Basketball Court | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-23 | 2024-09-21 | 2023-09-23 | 2024-09-21
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5FABRWF | Faber Park Waterfront | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5FABRWF | Faber Park Waterfront | 2 | DESIGN | 2017-12-28 | 2019-12-27 | 2017-12-28 | 2019-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5FABRWF | Faber Park Waterfront | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5FABRWF | Faber Park Waterfront | 4 | CONSTRUCTION | 2020-09-23 | 2022-09-22 | 2020-09-23 | 2022-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5FABRWF | Faber Park Waterfront | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5FRES10 | FRESH KILLS OWL HOLLOW FIELDS C/S | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5FRES10 | FRESH KILLS OWL HOLLOW FIELDS C/S | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5FRES10 | FRESH KILLS OWL HOLLOW FIELDS C/S | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5FRES10 | FRESH KILLS OWL HOLLOW FIELDS C/S | 4 | CONSTRUCTION | 2019-09-24 | 2021-03-21 | 2019-09-24 | 2021-03-21
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5FRES10 | FRESH KILLS OWL HOLLOW FIELDS C/S | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-22 | 2022-03-21 | 2021-03-22 | 2022-03-21
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5FRESH | Fresh Kills - East Park | 1 | DEVELOP SCOPE | 2006-07-01 | 2006-09-28 | 2006-07-01 | 2006-09-28
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5FRESH | Fresh Kills - East Park | 2 | DESIGN | 2006-09-29 | 2006-12-27 | 2006-09-29 | 2006-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5FRESH | Fresh Kills - East Park | 3 | BID/ REGISTER CONTRACT | 2006-12-28 | 2007-03-27 | 2006-12-28 | 2007-03-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5FRESH | Fresh Kills - East Park | 4 | CONSTRUCTION | 2007-03-28 | 2008-03-26 | 2007-03-28 | 2008-03-26
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5FRESH | Fresh Kills - East Park | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-27 | 2009-03-26 | 2008-03-27 | 2021-12-31
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5FRESH9 | Fresh Kills - construction of North Park R017-115M | 1 | DEVELOP SCOPE | 2006-07-01 | 2006-09-28 | 2006-07-01 | 2012-10-23
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5FRESH9 | Fresh Kills - construction of North Park R017-115M | 2 | DESIGN | 2006-09-29 | 2006-12-27 | 2012-10-24 | 2013-01-21
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5FRESH9 | Fresh Kills - construction of North Park R017-115M | 3 | BID/ REGISTER CONTRACT | 2006-12-28 | 2007-03-27 | 2013-01-22 | 2013-04-21
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5FRESH9 | Fresh Kills - construction of North Park R017-115M | 4 | CONSTRUCTION | 2007-03-28 | 2008-03-26 | 2013-04-22 | 2014-04-21
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5FRESH9 | Fresh Kills - construction of North Park R017-115M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-27 | 2009-03-26 | 2014-04-22 | 2025-01-25
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5FRESHS | Fresh Kills - Springville Greenway bicycle path RG-410M | 1 | DEVELOP SCOPE | 2010-07-01 | 2010-09-28 | 2010-07-01 | 2010-09-28
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5FRESHS | Fresh Kills - Springville Greenway bicycle path RG-410M | 2 | DESIGN | 2010-09-29 | 2010-12-27 | 2010-09-29 | 2012-10-09
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5FRESHS | Fresh Kills - Springville Greenway bicycle path RG-410M | 3 | BID/ REGISTER CONTRACT | 2010-12-28 | 2011-03-27 | 2013-05-14 | 2013-12-09
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5FRESHS | Fresh Kills - Springville Greenway bicycle path RG-410M | 4 | CONSTRUCTION | 2011-03-28 | 2012-03-26 | 2014-01-13 | 2015-07-06
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5FRESHS | Fresh Kills - Springville Greenway bicycle path RG-410M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-03-27 | 2013-03-26 | 2015-07-07 | 2022-12-31
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5GBPATH | Greenbelt Perimeter Path R013-112M | 1 | DEVELOP SCOPE | 2011-07-01 | 2011-09-28 | 2011-07-01 | 2011-09-28
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5GBPATH | Greenbelt Perimeter Path R013-112M | 2 | DESIGN | 2011-09-29 | 2011-12-27 | 2011-09-29 | 2011-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5GBPATH | Greenbelt Perimeter Path R013-112M | 3 | BID/ REGISTER CONTRACT | 2011-12-28 | 2012-03-26 | 2011-12-28 | 2012-03-26
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5GBPATH | Greenbelt Perimeter Path R013-112M | 4 | CONSTRUCTION | 2012-03-27 | 2013-03-26 | 2012-03-27 | 2013-03-26
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5GBPATH | Greenbelt Perimeter Path R013-112M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-03-27 | 2014-03-26 | 2013-03-27 | 2021-12-31
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5GBRCTF | Greenbelt Rec.Cntr-Constr. of turf field | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5GBRCTF | Greenbelt Rec.Cntr-Constr. of turf field | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5GBRCTF | Greenbelt Rec.Cntr-Constr. of turf field | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5GBRCTF | Greenbelt Rec.Cntr-Constr. of turf field | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5GBRCTF | Greenbelt Rec.Cntr-Constr. of turf field | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5GKBIKE | GREAT KILLS BICYCLE PATH R016-204MA | 1 | DEVELOP SCOPE | 2006-07-01 | 2006-09-28 | 2006-07-01 | 2006-09-28
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5GKBIKE | GREAT KILLS BICYCLE PATH R016-204MA | 2 | DESIGN | 2006-09-29 | 2006-12-27 | 2006-09-29 | 2006-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5GKBIKE | GREAT KILLS BICYCLE PATH R016-204MA | 3 | BID/ REGISTER CONTRACT | 2006-12-28 | 2007-03-27 | 2006-12-28 | 2007-03-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5GKBIKE | GREAT KILLS BICYCLE PATH R016-204MA | 4 | CONSTRUCTION | 2007-03-28 | 2008-03-26 | 2007-03-28 | 2008-03-26
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5GKBIKE | GREAT KILLS BICYCLE PATH R016-204MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-27 | 2009-03-26 | 2008-03-27 | 2019-12-30
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5GRNBRC | Greenbelt Rec Ctr Partial RC R129-119M | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5GRNBRC | Greenbelt Rec Ctr Partial RC R129-119M | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5GRNBRC | Greenbelt Rec Ctr Partial RC R129-119M | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5GRNBRC | Greenbelt Rec Ctr Partial RC R129-119M | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5GRNBRC | Greenbelt Rec Ctr Partial RC R129-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5IRENE | IRENE - Wolfe's Pond Park Berm | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5IRENE | IRENE - Wolfe's Pond Park Berm | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5IRENE | IRENE - Wolfe's Pond Park Berm | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5IRENE | IRENE - Wolfe's Pond Park Berm | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5IRENE | IRENE - Wolfe's Pond Park Berm | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5IRRIG | GOLF COURSE IRRIGATION - S.I. RG-200M | 2 | DESIGN | 1999-11-03 | 1999-12-20 | 1999-11-03 | 1999-12-20
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5IRRIG | GOLF COURSE IRRIGATION - S.I. RG-200M | 3 | BID/ REGISTER CONTRACT | 2000-01-18 | 2000-03-17 | 2000-01-18 | 2000-03-17
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5IRRIG | GOLF COURSE IRRIGATION - S.I. RG-200M | 4 | CONSTRUCTION | 2000-03-02 | 2001-04-18 | 2000-03-02 | 2001-04-18
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5IRRIG | GOLF COURSE IRRIGATION - S.I. RG-200M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2001-04-19 | 2002-04-18 | 2001-04-19 | 2002-04-18
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5JENNRF | Recon of Roofing systems at Jennifer CS | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5JENNRF | Recon of Roofing systems at Jennifer CS | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5JENNRF | Recon of Roofing systems at Jennifer CS | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5JENNRF | Recon of Roofing systems at Jennifer CS | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5JENNRF | Recon of Roofing systems at Jennifer CS | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5LILOPL | Luis LopezPlgr- Play Equipment (R125-118M) | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5LILOPL | Luis LopezPlgr- Play Equipment (R125-118M) | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5LILOPL | Luis LopezPlgr- Play Equipment (R125-118M) | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5LILOPL | Luis LopezPlgr- Play Equipment (R125-118M) | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5LILOPL | Luis LopezPlgr- Play Equipment (R125-118M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5MAPLWD | Maple Woods-Passive landscape | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5MAPLWD | Maple Woods-Passive landscape | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2016-12-28 | 2017-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5MAPLWD | Maple Woods-Passive landscape | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2017-12-28 | 2018-09-23
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5MAPLWD | Maple Woods-Passive landscape | 4 | CONSTRUCTION | 2018-09-24 | 2019-09-23 | 2018-09-24 | 2019-09-23
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5MAPLWD | Maple Woods-Passive landscape | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2024-12-31
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5MCARPK | Gen. MacArthur Park Baseball Field Renovation R067-117M | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2015-09-28
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5MCARPK | Gen. MacArthur Park Baseball Field Renovation R067-117M | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2015-09-29 | 2015-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5MCARPK | Gen. MacArthur Park Baseball Field Renovation R067-117M | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2015-12-28 | 2016-03-26
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5MCARPK | Gen. MacArthur Park Baseball Field Renovation R067-117M | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5MCARPK | Gen. MacArthur Park Baseball Field Renovation R067-117M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2017-03-27 | 2020-12-30
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5OAKBRM | Oakwood Beach Berm R016-312M | 1 | DEVELOP SCOPE | 2011-07-01 | 2011-09-28 | 2011-07-01 | 2011-10-12
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5OAKBRM | Oakwood Beach Berm R016-312M | 2 | DESIGN | 2011-09-29 | 2011-12-27 | 2011-10-13 | 2012-09-06
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5OAKBRM | Oakwood Beach Berm R016-312M | 3 | BID/ REGISTER CONTRACT | 2011-12-28 | 2012-03-26 | 2013-01-28 | 2013-05-28
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5OAKBRM | Oakwood Beach Berm R016-312M | 4 | CONSTRUCTION | 2012-03-27 | 2013-03-26 | 2014-06-02 | 2015-05-29
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5OAKBRM | Oakwood Beach Berm R016-312M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-03-27 | 2014-03-26 | 2015-05-30 | 2021-12-31
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5PKTR21 | FY21-Park Trees - Staten Island | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5PKTR21 | FY21-Park Trees - Staten Island | 2 | DESIGN | 2019-12-28 | 2020-06-24 | 2019-12-28 | 2020-06-24
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5PKTR21 | FY21-Park Trees - Staten Island | 3 | BID/ REGISTER CONTRACT | 2020-06-25 | 2021-03-21 | 2020-06-25 | 2021-03-21
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5PKTR21 | FY21-Park Trees - Staten Island | 4 | CONSTRUCTION | 2021-03-22 | 2022-09-12 | 2021-03-22 | 2022-09-12
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5PKTR21 | FY21-Park Trees - Staten Island | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-13 | 2024-09-11 | 2022-09-13 | 2024-09-11
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5PKTR21 | FY21-Park Trees - Staten Island | 6 | DEVELOP SCOPE | 2024-09-12 | 2025-03-10 | 2024-09-12 | 2025-03-10
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5PKTR21 | FY21-Park Trees - Staten Island | 7 | DESIGN | 2025-03-11 | 2026-03-10 | 2025-03-11 | 2026-03-10
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5PKTR21 | FY21-Park Trees - Staten Island | 8 | BID/ REGISTER CONTRACT | 2026-03-11 | 2026-12-05 | 2026-03-11 | 2026-12-05
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5PKTR21 | FY21-Park Trees - Staten Island | 9 | CONSTRUCTION | 2026-12-06 | 2027-12-05 | 2026-12-06 | 2027-12-05
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5PKTR21 | FY21-Park Trees - Staten Island | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2027-12-06 | 2028-12-04 | 2027-12-06 | 2028-12-04
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5PL15A2 | $1Contract-R/C of rain garden at Mahoney Plgr WO2 RG-215M | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5PL15A2 | $1Contract-R/C of rain garden at Mahoney Plgr WO2 RG-215M | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2016-12-28 | 2017-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5PL15A2 | $1Contract-R/C of rain garden at Mahoney Plgr WO2 RG-215M | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2017-12-28 | 2018-09-23
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5PL15A2 | $1Contract-R/C of rain garden at Mahoney Plgr WO2 RG-215M | 4 | CONSTRUCTION | 2018-09-24 | 2019-09-23 | 2018-09-24 | 2019-09-23
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5PL15A2 | $1Contract-R/C of rain garden at Mahoney Plgr WO2 RG-215M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5PL15A5 | $1Contract-Silver Lake Pk Path R/C WO# RG-215M | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5PL15A5 | $1Contract-Silver Lake Pk Path R/C WO# RG-215M | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5PL15A5 | $1Contract-Silver Lake Pk Path R/C WO# RG-215M | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5PL15A5 | $1Contract-Silver Lake Pk Path R/C WO# RG-215M | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5PL15A5 | $1Contract-Silver Lake Pk Path R/C WO# RG-215M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5PL15A6 | $1Contract-Clove Lake Pk Parking WO#6 RG-215M | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5PL15A6 | $1Contract-Clove Lake Pk Parking WO#6 RG-215M | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5PL15A6 | $1Contract-Clove Lake Pk Parking WO#6 RG-215M | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5PL15A6 | $1Contract-Clove Lake Pk Parking WO#6 RG-215M | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5PL15A6 | $1Contract-Clove Lake Pk Parking WO#6 RG-215M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5PLG13C | Reconstruction of plgrnds in SI /RG-214M | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2014-02-12 | 2014-11-07
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5PLG13C | Reconstruction of plgrnds in SI /RG-214M | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2015-04-17 | 2016-07-24
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5PLG13C | Reconstruction of plgrnds in SI /RG-214M | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2016-09-06 | 2017-09-12
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5PLG13C | Reconstruction of plgrnds in SI /RG-214M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2017-09-13 | 2019-09-12
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5PLG15B | R/C of parks & plgr in Staten Island RG-315MA1 | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5PLG15B | R/C of parks & plgr in Staten Island RG-315MA1 | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2016-12-28 | 2017-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5PLG15B | R/C of parks & plgr in Staten Island RG-315MA1 | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2017-12-28 | 2018-09-23
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5PLG15B | R/C of parks & plgr in Staten Island RG-315MA1 | 4 | CONSTRUCTION | 2018-09-24 | 2019-09-23 | 2018-09-24 | 2019-09-23
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5PLG15B | R/C of parks & plgr in Staten Island RG-315MA1 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2021-12-31
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5PNYC07 | PlaNYC-Ocean Breeze Beach Mainten.Area Fencing | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-23 | 2024-09-21 | 2023-09-23 | 2024-09-21
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5PNYC08 | PlaNYC-Ocean Breeze Beach Parking Lot | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5PNYC08 | PlaNYC-Ocean Breeze Beach Parking Lot | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5PNYC08 | PlaNYC-Ocean Breeze Beach Parking Lot | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5PNYC08 | PlaNYC-Ocean Breeze Beach Parking Lot | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5PNYC08 | PlaNYC-Ocean Breeze Beach Parking Lot | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5PRALCS | Prall Playground-Reconstruction of Comfort Station | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5PRALCS | Prall Playground-Reconstruction of Comfort Station | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5PRALCS | Prall Playground-Reconstruction of Comfort Station | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5PRALCS | Prall Playground-Reconstruction of Comfort Station | 4 | CONSTRUCTION | 2020-09-23 | 2022-03-21 | 2020-09-23 | 2022-03-21
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5PRALCS | Prall Playground-Reconstruction of Comfort Station | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-22 | 2023-03-21 | 2022-03-22 | 2023-03-21
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5PRESPL | Prescott Playground RC R085-118M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5PRESPL | Prescott Playground RC R085-118M | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5PRESPL | Prescott Playground RC R085-118M | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5PRESPL | Prescott Playground RC R085-118M | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5PRESPL | Prescott Playground RC R085-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5RECSI | Greenbelt Rec Ctr RC in Staten Island | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2015-09-28
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5RECSI | Greenbelt Rec Ctr RC in Staten Island | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2015-09-29 | 2015-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5RECSI | Greenbelt Rec Ctr RC in Staten Island | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2015-12-28 | 2016-03-26
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5RECSI | Greenbelt Rec Ctr RC in Staten Island | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5RECSI | Greenbelt Rec Ctr RC in Staten Island | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2017-03-27 | 2023-12-30
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5REFO20 | Reforestation FY20 Staten Is | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5REFO20 | Reforestation FY20 Staten Is | 2 | DESIGN | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5REFO20 | Reforestation FY20 Staten Is | 3 | BID/ REGISTER CONTRACT | 2019-09-24 | 2020-06-19 | 2019-09-24 | 2020-06-19
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5REFO20 | Reforestation FY20 Staten Is | 4 | CONSTRUCTION | 2020-06-20 | 2022-12-16 | 2020-06-20 | 2022-12-16
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5REFO20 | Reforestation FY20 Staten Is | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-12-17 | 2024-12-15 | 2022-12-17 | 2024-12-15
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5SIPOOL | Staten Island Indoor Pool | 1 | DEVELOP SCOPE | 2016-08-01 | 2017-01-27 | 2016-08-01 | 2017-01-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5SIPOOL | Staten Island Indoor Pool | 2 | DESIGN | 2017-01-28 | 2019-01-27 | 2017-01-28 | 2019-01-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5SIPOOL | Staten Island Indoor Pool | 3 | BID/ REGISTER CONTRACT | 2019-01-28 | 2019-10-24 | 2019-01-28 | 2019-10-24
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5SIPOOL | Staten Island Indoor Pool | 4 | CONSTRUCTION | 2019-10-25 | 2022-10-23 | 2019-10-25 | 2022-10-23
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5SIPOOL | Staten Island Indoor Pool | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-10-24 | 2024-10-22 | 2022-10-24 | 2024-10-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5SIWETL | STATEN ISLAND BOTANICAL GARDEN WETLAND RC/ R116-104M | 1 | DEVELOP SCOPE | 2003-07-01 | 2003-09-28 | 2003-07-01 | 2003-09-28
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5SIWETL | STATEN ISLAND BOTANICAL GARDEN WETLAND RC/ R116-104M | 2 | DESIGN | 2003-09-29 | 2004-03-15 | 2003-09-29 | 2004-03-15
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5SIWETL | STATEN ISLAND BOTANICAL GARDEN WETLAND RC/ R116-104M | 3 | BID/ REGISTER CONTRACT | 2004-03-16 | 2004-06-30 | 2004-03-16 | 2004-06-30
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5SIWETL | STATEN ISLAND BOTANICAL GARDEN WETLAND RC/ R116-104M | 4 | CONSTRUCTION | 2004-07-01 | 2005-06-30 | 2004-07-01 | 2005-06-30
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5SIWETL | STATEN ISLAND BOTANICAL GARDEN WETLAND RC/ R116-104M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2005-07-01 | 2006-06-30 | 2005-07-01 | 2006-06-30
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5SLVLK1 | Silver Lake Park | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5SLVLK1 | Silver Lake Park | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5SLVLK1 | Silver Lake Park | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5SLVLK1 | Silver Lake Park | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5SLVLK1 | Silver Lake Park | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5TPSBF | Tappen Park & South Beach Fountain Reconstruction | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5TPSBF | Tappen Park & South Beach Fountain Reconstruction | 2 | DESIGN | 2018-12-28 | 2020-06-24 | 2018-12-28 | 2020-06-24
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5TPSBF | Tappen Park & South Beach Fountain Reconstruction | 3 | BID/ REGISTER CONTRACT | 2020-06-25 | 2021-03-21 | 2020-06-25 | 2021-03-21
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5TPSBF | Tappen Park & South Beach Fountain Reconstruction | 4 | CONSTRUCTION | 2021-03-22 | 2022-09-17 | 2021-03-22 | 2022-09-17
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5TPSBF | Tappen Park & South Beach Fountain Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-18 | 2023-09-17 | 2022-09-18 | 2023-09-17
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5TRE14A | FY14 Street Tree Planting, Staten Island CBs 1-3 (RG-1113M) | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2013-09-28
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5TRE14A | FY14 Street Tree Planting, Staten Island CBs 1-3 (RG-1113M) | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2013-09-29 | 2013-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5TRE14A | FY14 Street Tree Planting, Staten Island CBs 1-3 (RG-1113M) | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2013-12-28 | 2014-03-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5TRE14A | FY14 Street Tree Planting, Staten Island CBs 1-3 (RG-1113M) | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2014-03-28 | 2015-03-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5TRE14A | FY14 Street Tree Planting, Staten Island CBs 1-3 (RG-1113M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2021-03-26
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5TRE21A | FY21 Street Trees Staten Island, CB 1-3 RG- | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5TRE21A | FY21 Street Trees Staten Island, CB 1-3 RG- | 2 | DESIGN | 2019-12-28 | 2020-06-24 | 2019-12-28 | 2020-06-24
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5TRE21A | FY21 Street Trees Staten Island, CB 1-3 RG- | 3 | BID/ REGISTER CONTRACT | 2020-06-25 | 2021-03-21 | 2020-06-25 | 2021-03-21
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5TRE21A | FY21 Street Trees Staten Island, CB 1-3 RG- | 4 | CONSTRUCTION | 2021-03-22 | 2022-09-12 | 2021-03-22 | 2022-09-12
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5TRE21A | FY21 Street Trees Staten Island, CB 1-3 RG- | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-13 | 2024-09-11 | 2022-09-13 | 2024-09-11
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5TREEFA | Fairview Pk -Reforestation R153-117MA | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5TREEFA | Fairview Pk -Reforestation R153-117MA | 2 | DESIGN | 2016-12-28 | 2017-09-23 | 2016-12-28 | 2017-09-23
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5TREEFA | Fairview Pk -Reforestation R153-117MA | 3 | BID/ REGISTER CONTRACT | 2017-09-24 | 2018-06-20 | 2017-09-24 | 2018-06-20
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5TREEFA | Fairview Pk -Reforestation R153-117MA | 4 | CONSTRUCTION | 2018-06-21 | 2020-12-16 | 2018-06-21 | 2020-12-16
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5TREEFA | Fairview Pk -Reforestation R153-117MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-12-17 | 2022-12-16 | 2020-12-17 | 2022-12-16
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5TRSD19 | Staten Island-Tree-Damaged Sidewalk R/C | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5TRSD19 | Staten Island-Tree-Damaged Sidewalk R/C | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5TRSD19 | Staten Island-Tree-Damaged Sidewalk R/C | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5TRSD19 | Staten Island-Tree-Damaged Sidewalk R/C | 4 | CONSTRUCTION | 2020-09-23 | 2022-09-22 | 2020-09-23 | 2022-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5TRSD19 | Staten Island-Tree-Damaged Sidewalk R/C | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5WBRKRF | Recon of Roofing systems at Willowbrook | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5WBRKRF | Recon of Roofing systems at Willowbrook | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5WBRKRF | Recon of Roofing systems at Willowbrook | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5WBRKRF | Recon of Roofing systems at Willowbrook | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5WBRKRF | Recon of Roofing systems at Willowbrook | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5WHITEP | White Plgr-Hillside Slide Construction R012- | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5WHITEP | White Plgr-Hillside Slide Construction R012- | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5WHITEP | White Plgr-Hillside Slide Construction R012- | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5WHITEP | White Plgr-Hillside Slide Construction R012- | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5WHITEP | White Plgr-Hillside Slide Construction R012- | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5WPBERM | Wolfe's Pond Park Berm | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2013-09-28
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5WPBERM | Wolfe's Pond Park Berm | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2013-09-29 | 2015-10-14
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5WPBERM | Wolfe's Pond Park Berm | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2016-04-28 | 2017-06-01
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5WPBERM | Wolfe's Pond Park Berm | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2017-10-01 | 2019-09-30
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5WPBERM | Wolfe's Pond Park Berm | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2019-10-01 | 2021-12-31
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5WPPLGR | Wolf Pond Pk Plgr R031-115M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5WPPLGR | Wolf Pond Pk Plgr R031-115M | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5WPPLGR | Wolf Pond Pk Plgr R031-115M | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5WPPLGR | Wolf Pond Pk Plgr R031-115M | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5WPPLGR | Wolf Pond Pk Plgr R031-115M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-6PAVESI | Staten Island Pavement Reconstruction (SoGR) RG-120M | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-6PAVESI | Staten Island Pavement Reconstruction (SoGR) RG-120M | 2 | DESIGN | 2019-12-28 | 2021-06-24 | 2019-12-28 | 2021-06-24
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-6PAVESI | Staten Island Pavement Reconstruction (SoGR) RG-120M | 3 | BID/ REGISTER CONTRACT | 2021-06-25 | 2022-03-21 | 2021-06-25 | 2022-03-21
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-6PAVESI | Staten Island Pavement Reconstruction (SoGR) RG-120M | 4 | CONSTRUCTION | 2022-03-22 | 2023-09-17 | 2022-03-22 | 2023-09-17
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-6PAVESI | Staten Island Pavement Reconstruction (SoGR) RG-120M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-18 | 2024-09-16 | 2023-09-18 | 2024-09-16
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | PV510-HLG | SIBG -SI BOTANICAL GARDEN Healing Garden R116-506M | 1 | DEVELOP SCOPE | 2008-07-01 | 2008-09-28 | 2008-07-01 | 2008-09-28
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | PV510-HLG | SIBG -SI BOTANICAL GARDEN Healing Garden R116-506M | 2 | PRELIMINARY DESIGN | 2008-09-29 | 2009-01-26 | 2008-09-29 | 2009-01-26
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | PV510-HLG | SIBG -SI BOTANICAL GARDEN Healing Garden R116-506M | 3 | FINAL DESIGN | 2009-01-27 | 2009-07-25 | 2009-01-27 | 2009-07-25
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | PV510-HLG | SIBG -SI BOTANICAL GARDEN Healing Garden R116-506M | 4 | BID AWARD AND REGISTER CONTRCT | 2009-07-26 | 2009-10-23 | 2009-07-26 | 2009-10-23
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | PV510-HLG | SIBG -SI BOTANICAL GARDEN Healing Garden R116-506M | 5 | CONSTRUCTION TO 25% | 2009-10-24 | 2010-02-20 | 2009-10-24 | 2010-02-20
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | PV510-HLG | SIBG -SI BOTANICAL GARDEN Healing Garden R116-506M | 6 | CONSTRUCTION TO 50% | 2010-02-21 | 2010-06-20 | 2010-02-21 | 2010-06-20
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | PV510-HLG | SIBG -SI BOTANICAL GARDEN Healing Garden R116-506M | 7 | CONSTRUCTION TO 75% | 2010-06-21 | 2010-10-18 | 2010-06-21 | 2010-10-18
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | PV510-HLG | SIBG -SI BOTANICAL GARDEN Healing Garden R116-506M | 8 | ORIGINAL EQUIP & FURNISHING | 2010-10-19 | 2011-01-16 | 2010-10-19 | 2011-01-16
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | PV510-HLG | SIBG -SI BOTANICAL GARDEN Healing Garden R116-506M | 9 | SUBSTANTIAL COMPLETION | 2011-01-17 | 2011-03-17 | 2011-01-17 | 2011-03-17
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | PV510-HLG | SIBG -SI BOTANICAL GARDEN Healing Garden R116-506M | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2011-03-18 | 2011-04-16 | 2011-03-18 | 2011-04-16
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | PV510-IRR | SIBG -SI BOTANICAL GARDEN Site Irrigation | 1 | DEVELOP SCOPE | 2008-07-01 | 2008-09-28 | 2008-07-01 | 2008-09-28
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | PV510-IRR | SIBG -SI BOTANICAL GARDEN Site Irrigation | 2 | PRELIMINARY DESIGN | 2008-09-29 | 2009-01-26 | 2008-09-29 | 2009-01-26
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | PV510-IRR | SIBG -SI BOTANICAL GARDEN Site Irrigation | 3 | FINAL DESIGN | 2009-01-27 | 2009-07-25 | 2009-01-27 | 2009-07-25
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | PV510-IRR | SIBG -SI BOTANICAL GARDEN Site Irrigation | 4 | BID AWARD AND REGISTER CONTRCT | 2009-07-26 | 2009-10-23 | 2009-07-26 | 2009-10-23
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | PV510-IRR | SIBG -SI BOTANICAL GARDEN Site Irrigation | 5 | CONSTRUCTION TO 25% | 2009-10-24 | 2010-02-20 | 2009-10-24 | 2010-02-20
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | PV510-IRR | SIBG -SI BOTANICAL GARDEN Site Irrigation | 6 | CONSTRUCTION TO 50% | 2010-02-21 | 2010-06-20 | 2010-02-21 | 2010-06-20
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | PV510-IRR | SIBG -SI BOTANICAL GARDEN Site Irrigation | 7 | CONSTRUCTION TO 75% | 2010-06-21 | 2010-10-18 | 2010-06-21 | 2010-10-18
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | PV510-IRR | SIBG -SI BOTANICAL GARDEN Site Irrigation | 8 | ORIGINAL EQUIP & FURNISHING | 2010-10-19 | 2011-01-16 | 2010-10-19 | 2011-01-16
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | PV510-IRR | SIBG -SI BOTANICAL GARDEN Site Irrigation | 9 | SUBSTANTIAL COMPLETION | 2011-01-17 | 2011-03-17 | 2011-01-17 | 2011-03-17
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | PV510-IRR | SIBG -SI BOTANICAL GARDEN Site Irrigation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2011-03-18 | 2011-04-16 | 2011-03-18 | 2011-04-16
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-05 | SANDY - Blissenbach Marina Demo (Type 3) R160-113M | 1 | DEVELOP SCOPE | 2012-12-01 | 2013-02-28 | 2012-12-01 | 2013-06-06
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-05 | SANDY - Blissenbach Marina Demo (Type 3) R160-113M | 2 | DESIGN | 2013-03-01 | 2013-05-29 | 2013-06-07 | 2014-01-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-05 | SANDY - Blissenbach Marina Demo (Type 3) R160-113M | 3 | BID/ REGISTER CONTRACT | 2013-05-30 | 2013-08-27 | 2014-12-15 | 2016-04-02
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-05 | SANDY - Blissenbach Marina Demo (Type 3) R160-113M | 4 | CONSTRUCTION | 2013-08-28 | 2014-08-27 | 2016-09-06 | 2017-10-03
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-05 | SANDY - Blissenbach Marina Demo (Type 3) R160-113M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-08-28 | 2015-08-27 | 2017-10-04 | 2021-12-30
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-13 | SANDY - SI Type 2 Plgrd R/C (RG-713M) | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2013-09-28
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-13 | SANDY - SI Type 2 Plgrd R/C (RG-713M) | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2013-09-29 | 2013-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-13 | SANDY - SI Type 2 Plgrd R/C (RG-713M) | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2013-12-28 | 2014-03-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-13 | SANDY - SI Type 2 Plgrd R/C (RG-713M) | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2014-03-28 | 2015-03-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-13 | SANDY - SI Type 2 Plgrd R/C (RG-713M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2021-12-30
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-16 | Conference House Pk landscape (Type 3 ) R006-114M | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2015-05-01
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-16 | Conference House Pk landscape (Type 3 ) R006-114M | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2015-05-02 | 2016-12-30
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-16 | Conference House Pk landscape (Type 3 ) R006-114M | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2017-06-23 | 2018-05-01
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-16 | Conference House Pk landscape (Type 3 ) R006-114M | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2018-06-18 | 2019-01-10
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-16 | Conference House Pk landscape (Type 3 ) R006-114M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2019-01-11 | 2021-01-09
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-17 | Tappen Park & Dolphin Fountains (Type3) | 1 | DEVELOP SCOPE | 2013-06-01 | 2013-08-29 | 2013-06-01 | 2015-07-01
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-17 | Tappen Park & Dolphin Fountains (Type3) | 2 | DESIGN | 2013-08-30 | 2013-11-27 | 2015-07-02 | 2017-03-31
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-17 | Tappen Park & Dolphin Fountains (Type3) | 3 | BID/ REGISTER CONTRACT | 2013-11-28 | 2014-02-25 | 2017-04-01 | 2017-06-29
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-17 | Tappen Park & Dolphin Fountains (Type3) | 4 | CONSTRUCTION | 2014-02-26 | 2015-02-25 | 2017-06-30 | 2018-06-29
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-17 | Tappen Park & Dolphin Fountains (Type3) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-02-26 | 2016-02-25 | 2018-06-30 | 2021-06-29
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-18 | SANDY-Midland Beach Protective Berm Emergency | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2013-09-28
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-18 | SANDY-Midland Beach Protective Berm Emergency | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2013-09-29 | 2013-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-18 | SANDY-Midland Beach Protective Berm Emergency | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2013-12-28 | 2014-03-04
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-18 | SANDY-Midland Beach Protective Berm Emergency | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2013-11-18 | 2014-04-11
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-18 | SANDY-Midland Beach Protective Berm Emergency | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2014-04-12 | 2022-12-30
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-20 | SANDY - Tree removals - Staten Island RG-614M | 1 | DEVELOP SCOPE | 2014-01-01 | 2014-03-31 | 2014-01-01 | 2014-03-31
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-20 | SANDY - Tree removals - Staten Island RG-614M | 2 | DESIGN | 2014-04-01 | 2014-06-29 | 2014-04-01 | 2014-06-29
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-20 | SANDY - Tree removals - Staten Island RG-614M | 3 | BID/ REGISTER CONTRACT | 2014-06-30 | 2014-09-27 | 2014-06-30 | 2014-09-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-20 | SANDY - Tree removals - Staten Island RG-614M | 4 | CONSTRUCTION | 2014-09-28 | 2015-09-27 | 2014-09-28 | 2015-09-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-20 | SANDY - Tree removals - Staten Island RG-614M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-09-28 | 2016-09-26 | 2015-09-28 | 2021-09-26
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-24 | Sandy-Seaside Wildlife Nature Pk-reconstruction | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-24 | Sandy-Seaside Wildlife Nature Pk-reconstruction | 2 | DESIGN | 2016-12-28 | 2018-06-20 | 2016-12-28 | 2018-06-20
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-24 | Sandy-Seaside Wildlife Nature Pk-reconstruction | 3 | BID/ REGISTER CONTRACT | 2018-06-21 | 2019-03-17 | 2018-06-21 | 2019-03-17
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-24 | Sandy-Seaside Wildlife Nature Pk-reconstruction | 4 | CONSTRUCTION | 2019-03-18 | 2020-09-07 | 2019-03-18 | 2020-09-07
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-24 | Sandy-Seaside Wildlife Nature Pk-reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-08 | 2021-09-07 | 2020-09-08 | 2021-09-07
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-26 | Sandy-R/C of playground at Wolfe's Pond Park | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2015-09-28
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-26 | Sandy-R/C of playground at Wolfe's Pond Park | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2015-09-29 | 2015-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-26 | Sandy-R/C of playground at Wolfe's Pond Park | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2015-12-28 | 2016-03-26
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-26 | Sandy-R/C of playground at Wolfe's Pond Park | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-26 | Sandy-R/C of playground at Wolfe's Pond Park | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2017-03-27 | 2021-03-26
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-27 | Sandy-Wolfe's Pond Park-R/C of the berm | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-27 | Sandy-Wolfe's Pond Park-R/C of the berm | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-27 | Sandy-Wolfe's Pond Park-R/C of the berm | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-27 | Sandy-Wolfe's Pond Park-R/C of the berm | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-27 | Sandy-Wolfe's Pond Park-R/C of the berm | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-28 | Sandy-FDR bdwk & Midland Plgr-R/C of tthe pavements,etc | 1 | DEVELOP SCOPE | 2014-07-01 | 2014-09-28 | 2014-07-01 | 2014-09-28
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-28 | Sandy-FDR bdwk & Midland Plgr-R/C of tthe pavements,etc | 2 | DESIGN | 2014-09-29 | 2014-12-27 | 2014-09-29 | 2014-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-28 | Sandy-FDR bdwk & Midland Plgr-R/C of tthe pavements,etc | 3 | BID/ REGISTER CONTRACT | 2014-12-28 | 2015-03-27 | 2014-12-28 | 2015-03-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-28 | Sandy-FDR bdwk & Midland Plgr-R/C of tthe pavements,etc | 4 | CONSTRUCTION | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2016-03-26
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-28 | Sandy-FDR bdwk & Midland Plgr-R/C of tthe pavements,etc | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2021-03-26
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-30 | Sandy-New Dorp Bch Site Restor.R016-115M | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2015-09-28
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-30 | Sandy-New Dorp Bch Site Restor.R016-115M | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2015-09-29 | 2015-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-30 | Sandy-New Dorp Bch Site Restor.R016-115M | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2015-12-28 | 2016-03-26
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-30 | Sandy-New Dorp Bch Site Restor.R016-115M | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-30 | Sandy-New Dorp Bch Site Restor.R016-115M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2017-03-27 | 2021-12-30
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-32 | Sandy-R/C of S. Bch-Playland Plgr, RG-212M WO 1 | 1 | DEVELOP SCOPE | 2014-07-01 | 2014-09-28 | 2014-07-01 | 2014-09-28
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-32 | Sandy-R/C of S. Bch-Playland Plgr, RG-212M WO 1 | 2 | DESIGN | 2014-09-29 | 2014-12-27 | 2014-09-29 | 2014-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-32 | Sandy-R/C of S. Bch-Playland Plgr, RG-212M WO 1 | 3 | BID/ REGISTER CONTRACT | 2014-12-28 | 2015-03-27 | 2014-12-28 | 2015-03-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-32 | Sandy-R/C of S. Bch-Playland Plgr, RG-212M WO 1 | 4 | CONSTRUCTION | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2016-03-26
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-32 | Sandy-R/C of S. Bch-Playland Plgr, RG-212M WO 1 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2022-12-30
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-33 | Sandy-R/C of S.Bch-SaturnPlgr, RG-212M WO 2 | 3 | BID/ REGISTER CONTRACT | 2014-12-28 | 2015-03-27 | 2014-12-28 | 2015-03-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-33 | Sandy-R/C of S.Bch-SaturnPlgr, RG-212M WO 2 | 4 | CONSTRUCTION | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2016-03-26
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-33 | Sandy-R/C of S.Bch-SaturnPlgr, RG-212M WO 2 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-34 | Sandy-R/C of Faber Plgr, SI RG-212M WO 3 | 2 | DESIGN | 2014-09-29 | 2014-12-27 | 2014-09-29 | 2014-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-34 | Sandy-R/C of Faber Plgr, SI RG-212M WO 3 | 3 | BID/ REGISTER CONTRACT | 2014-12-28 | 2015-03-27 | 2014-12-28 | 2015-03-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-34 | Sandy-R/C of Faber Plgr, SI RG-212M WO 3 | 4 | CONSTRUCTION | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2016-03-26
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-34 | Sandy-R/C of Faber Plgr, SI RG-212M WO 3 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-36 | SANDY - FDR BOARDWALK | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-36 | SANDY - FDR BOARDWALK | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-36 | SANDY - FDR BOARDWALK | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-36 | SANDY - FDR BOARDWALK | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-36 | SANDY - FDR BOARDWALK | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2024-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-37 | SANDY - BUONO BEACH FOUNTAIN REPAIR - R117-117MA | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-37 | SANDY - BUONO BEACH FOUNTAIN REPAIR - R117-117MA | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-37 | SANDY - BUONO BEACH FOUNTAIN REPAIR - R117-117MA | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-37 | SANDY - BUONO BEACH FOUNTAIN REPAIR - R117-117MA | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-37 | SANDY - BUONO BEACH FOUNTAIN REPAIR - R117-117MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-41 | Sandy-Lemon Creek Pk -timbler rail RG-212M WO 5 | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2015-09-29 | 2015-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-41 | Sandy-Lemon Creek Pk -timbler rail RG-212M WO 5 | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2015-12-28 | 2016-03-26
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-41 | Sandy-Lemon Creek Pk -timbler rail RG-212M WO 5 | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-41 | Sandy-Lemon Creek Pk -timbler rail RG-212M WO 5 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2017-03-27 | 2018-03-26
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-42 | Sandy-Conference House Barrier Rail RG-212M WO6 | 1 | DEVELOP SCOPE | 2020-07-01 | 2020-12-27 | 2020-07-01 | 2020-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-42 | Sandy-Conference House Barrier Rail RG-212M WO6 | 2 | DESIGN | 2020-12-28 | 2021-12-27 | 2020-12-28 | 2021-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-42 | Sandy-Conference House Barrier Rail RG-212M WO6 | 3 | BID/ REGISTER CONTRACT | 2021-12-28 | 2022-09-23 | 2021-12-28 | 2022-09-23
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-42 | Sandy-Conference House Barrier Rail RG-212M WO6 | 4 | CONSTRUCTION | 2022-09-24 | 2023-09-23 | 2022-09-24 | 2023-09-23
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-42 | Sandy-Conference House Barrier Rail RG-212M WO6 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-24 | 2024-09-22 | 2023-09-24 | 2024-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-43 | Lemon Creek Marina R079-120M | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-43 | Lemon Creek Marina R079-120M | 2 | DESIGN | 2016-12-28 | 2018-12-27 | 2016-12-28 | 2018-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-43 | Lemon Creek Marina R079-120M | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-43 | Lemon Creek Marina R079-120M | 4 | CONSTRUCTION | 2019-09-24 | 2022-09-22 | 2019-09-24 | 2022-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-43 | Lemon Creek Marina R079-120M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2024-09-21 | 2022-09-23 | 2024-09-21
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-44 | New Dorp Pk./Corp. Kivlehan Pk. | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-44 | New Dorp Pk./Corp. Kivlehan Pk. | 2 | DESIGN | 2016-12-28 | 2018-06-20 | 2016-12-28 | 2018-06-20
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-44 | New Dorp Pk./Corp. Kivlehan Pk. | 3 | BID/ REGISTER CONTRACT | 2018-06-21 | 2019-03-17 | 2018-06-21 | 2019-03-17
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-44 | New Dorp Pk./Corp. Kivlehan Pk. | 4 | CONSTRUCTION | 2019-03-18 | 2020-09-07 | 2019-03-18 | 2020-09-07
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-44 | New Dorp Pk./Corp. Kivlehan Pk. | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-08 | 2021-09-07 | 2020-09-08 | 2021-09-07
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-45 | SANDY-MacArthur Park Reconstruction | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-45 | SANDY-MacArthur Park Reconstruction | 2 | DESIGN | 2016-12-28 | 2018-06-20 | 2016-12-28 | 2018-06-20
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-45 | SANDY-MacArthur Park Reconstruction | 3 | BID/ REGISTER CONTRACT | 2018-06-21 | 2019-03-17 | 2018-06-21 | 2019-03-17
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-45 | SANDY-MacArthur Park Reconstruction | 4 | CONSTRUCTION | 2019-03-18 | 2020-09-07 | 2019-03-18 | 2020-09-07
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-45 | SANDY-MacArthur Park Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-08 | 2021-09-07 | 2020-09-08 | 2021-09-07
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-46 | Alice Austen Park (R117-115M) | 1 | DEVELOP SCOPE | 2016-08-01 | 2017-01-27 | 2016-08-01 | 2017-01-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-46 | Alice Austen Park (R117-115M) | 2 | DESIGN | 2017-01-28 | 2018-01-27 | 2017-01-28 | 2018-01-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-46 | Alice Austen Park (R117-115M) | 3 | BID/ REGISTER CONTRACT | 2018-01-28 | 2018-10-24 | 2018-01-28 | 2018-10-24
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-46 | Alice Austen Park (R117-115M) | 4 | CONSTRUCTION | 2018-10-25 | 2019-10-24 | 2018-10-25 | 2019-10-24
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-46 | Alice Austen Park (R117-115M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-10-25 | 2020-10-23 | 2019-10-25 | 2020-10-23
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-47 | Midland Beach Bath House | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-47 | Midland Beach Bath House | 2 | DESIGN | 2017-12-28 | 2019-12-27 | 2017-12-28 | 2019-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-47 | Midland Beach Bath House | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-47 | Midland Beach Bath House | 4 | CONSTRUCTION | 2020-09-23 | 2023-09-22 | 2020-09-23 | 2023-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-47 | Midland Beach Bath House | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-23 | 2025-09-21 | 2023-09-23 | 2025-09-21
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-48 | Five Parks in SI | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-48 | Five Parks in SI | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-48 | Five Parks in SI | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-48 | Five Parks in SI | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-48 | Five Parks in SI | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2024-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-49 | Fairview Park Comfort Station Construction | 1 | DEVELOP SCOPE | 2017-08-01 | 2018-01-27 | 2017-08-01 | 2018-01-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-49 | Fairview Park Comfort Station Construction | 2 | DESIGN | 2018-01-28 | 2019-07-21 | 2018-01-28 | 2019-07-21
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-49 | Fairview Park Comfort Station Construction | 3 | BID/ REGISTER CONTRACT | 2019-07-22 | 2020-04-16 | 2019-07-22 | 2020-04-16
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-49 | Fairview Park Comfort Station Construction | 4 | CONSTRUCTION | 2020-04-17 | 2021-10-08 | 2020-04-17 | 2021-10-08
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-49 | Fairview Park Comfort Station Construction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-10-09 | 2022-10-08 | 2021-10-09 | 2022-10-08
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-50 | Fairview Park Landscape Construction R153-118M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-50 | Fairview Park Landscape Construction R153-118M | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-50 | Fairview Park Landscape Construction R153-118M | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-50 | Fairview Park Landscape Construction R153-118M | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-50 | Fairview Park Landscape Construction R153-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | 288CLOVE | REHABILITATION OF 288 CLOVE RD FACILITY | 1 | DEVELOP SCOPE | 2018-06-01 | 2018-09-28 | 2018-06-01 | 2018-09-28
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | 288CLOVE | REHABILITATION OF 288 CLOVE RD FACILITY | 2 | PRELIMINARY DESIGN | 2018-09-29 | 2019-03-27 | 2018-09-29 | 2019-03-27
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | 288CLOVE | REHABILITATION OF 288 CLOVE RD FACILITY | 3 | FINAL DESIGN | 2019-03-28 | 2020-09-27 | 2019-03-28 | 2020-09-27
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | 288CLOVE | REHABILITATION OF 288 CLOVE RD FACILITY | 4 | BID AWARD AND REGISTER CONTRCT | 2020-09-28 | 2021-03-26 | 2020-09-28 | 2021-03-26
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | 288CLOVE | REHABILITATION OF 288 CLOVE RD FACILITY | 5 | CONSTRUCTION TO 25% | 2021-03-27 | 2021-12-31 | 2021-03-27 | 2021-12-31
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | 288CLOVE | REHABILITATION OF 288 CLOVE RD FACILITY | 6 | CONSTRUCTION TO 50% | 2022-01-01 | 2022-10-07 | 2022-01-01 | 2022-10-07
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | 288CLOVE | REHABILITATION OF 288 CLOVE RD FACILITY | 7 | CONSTRUCTION TO 75% | 2022-10-08 | 2023-07-14 | 2022-10-08 | 2023-07-14
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | 288CLOVE | REHABILITATION OF 288 CLOVE RD FACILITY | 8 | ORIGINAL EQUIP & FURNISHING | 2023-07-15 | 2023-10-12 | 2023-07-15 | 2023-10-12
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | 288CLOVE | REHABILITATION OF 288 CLOVE RD FACILITY | 9 | SUBSTANTIAL COMPLETION | 2023-10-13 | 2023-12-11 | 2023-10-13 | 2023-12-11
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | 288CLOVE | REHABILITATION OF 288 CLOVE RD FACILITY | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-12-12 | 2024-03-10 | 2023-12-12 | 2024-03-10
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | CO301LL | 130 STUYVESANT PL - FACADE REPAIRS LOCAL LAW 11 | 1 | DEVELOP SCOPE | 2018-03-01 | 2018-05-29 | 2018-03-01 | 2018-05-29
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | CO301LL | 130 STUYVESANT PL - FACADE REPAIRS LOCAL LAW 11 | 2 | PRELIMINARY DESIGN | 2018-05-30 | 2018-09-26 | 2018-05-30 | 2018-09-26
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | CO301LL | 130 STUYVESANT PL - FACADE REPAIRS LOCAL LAW 11 | 3 | FINAL DESIGN | 2018-09-27 | 2019-03-25 | 2018-09-27 | 2019-03-25
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | CO301LL | 130 STUYVESANT PL - FACADE REPAIRS LOCAL LAW 11 | 4 | BID AWARD AND REGISTER CONTRCT | 2019-03-26 | 2019-06-23 | 2019-03-26 | 2019-06-23
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | CO301LL | 130 STUYVESANT PL - FACADE REPAIRS LOCAL LAW 11 | 5 | CONSTRUCTION TO 25% | 2019-06-24 | 2019-10-21 | 2019-06-24 | 2019-10-21
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | CO301LL | 130 STUYVESANT PL - FACADE REPAIRS LOCAL LAW 11 | 6 | CONSTRUCTION TO 50% | 2019-10-22 | 2020-02-18 | 2019-10-22 | 2020-02-18
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | CO301LL | 130 STUYVESANT PL - FACADE REPAIRS LOCAL LAW 11 | 7 | CONSTRUCTION TO 75% | 2020-02-19 | 2020-06-17 | 2020-02-19 | 2020-06-17
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | CO301LL | 130 STUYVESANT PL - FACADE REPAIRS LOCAL LAW 11 | 8 | ORIGINAL EQUIP & FURNISHING | 2020-06-18 | 2020-09-15 | 2020-06-18 | 2020-09-15
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | CO301LL | 130 STUYVESANT PL - FACADE REPAIRS LOCAL LAW 11 | 9 | SUBSTANTIAL COMPLETION | 2020-09-16 | 2020-11-14 | 2020-09-16 | 2020-11-14
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | CO301LL | 130 STUYVESANT PL - FACADE REPAIRS LOCAL LAW 11 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-11-15 | 2020-12-14 | 2020-11-15 | 2023-07-28
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | CO301PD | 130 STUYVESANT PL.- PARKING GARAGE DECK | 1 | DEVELOP SCOPE | 2014-09-24 | 2014-12-22 | 2014-09-24 | 2014-12-22
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | CO301PD | 130 STUYVESANT PL.- PARKING GARAGE DECK | 2 | PRELIMINARY DESIGN | 2014-12-23 | 2015-04-21 | 2014-12-23 | 2015-04-21
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | CO301PD | 130 STUYVESANT PL.- PARKING GARAGE DECK | 3 | FINAL DESIGN | 2015-04-22 | 2015-10-18 | 2015-04-22 | 2018-08-17
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | CO301PD | 130 STUYVESANT PL.- PARKING GARAGE DECK | 4 | BID AWARD AND REGISTER CONTRCT | 2015-10-19 | 2016-01-16 | 2018-08-18 | 2018-11-15
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | CO301PD | 130 STUYVESANT PL.- PARKING GARAGE DECK | 5 | CONSTRUCTION TO 25% | 2016-01-17 | 2016-05-15 | 2018-11-16 | 2019-03-15
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | CO301PD | 130 STUYVESANT PL.- PARKING GARAGE DECK | 6 | CONSTRUCTION TO 50% | 2016-05-16 | 2016-09-12 | 2019-03-16 | 2019-07-13
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | CO301PD | 130 STUYVESANT PL.- PARKING GARAGE DECK | 7 | CONSTRUCTION TO 75% | 2016-09-13 | 2017-01-10 | 2019-07-14 | 2019-11-10
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | CO301PD | 130 STUYVESANT PL.- PARKING GARAGE DECK | 8 | ORIGINAL EQUIP & FURNISHING | 2017-01-11 | 2017-04-10 | 2019-11-11 | 2020-02-08
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | CO301PD | 130 STUYVESANT PL.- PARKING GARAGE DECK | 9 | SUBSTANTIAL COMPLETION | 2017-04-11 | 2017-06-09 | 2020-02-09 | 2020-04-08
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | CO301PD | 130 STUYVESANT PL.- PARKING GARAGE DECK | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-06-10 | 2017-07-09 | 2020-04-09 | 2023-04-30
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | CO301PD | 130 STUYVESANT PL.- PARKING GARAGE DECK | 11 | PROJECT START | 2017-06-10 | 2017-07-09 | 2023-05-01 | 2023-05-01
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | CO301PD | 130 STUYVESANT PL.- PARKING GARAGE DECK | 12 | DESIGN START | 2017-06-10 | 2017-07-09 | 2023-05-02 | 2023-05-02
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | CO301PD | 130 STUYVESANT PL.- PARKING GARAGE DECK | 13 | DESIGN COMPLETION | 2017-06-10 | 2017-07-09 | 2023-05-03 | 2023-05-03
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | CO301PD | 130 STUYVESANT PL.- PARKING GARAGE DECK | 14 | CONSTRUCTION START | 2017-06-10 | 2017-07-09 | 2023-05-04 | 2023-05-04
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | CO301PD | 130 STUYVESANT PL.- PARKING GARAGE DECK | 15 | CONSTRUCTION COMPLETION | 2017-06-10 | 2017-07-09 | 2023-05-05 | 2023-05-05
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | CO302ST | 18 RICHMOND TERRACE - EXTERIOR STEPS RECONSTRUCTION | 1 | DEVELOP SCOPE | 2019-03-01 | 2019-05-29 | 2019-03-01 | 2019-05-29
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | CO302ST | 18 RICHMOND TERRACE - EXTERIOR STEPS RECONSTRUCTION | 2 | PRELIMINARY DESIGN | 2019-05-30 | 2019-09-26 | 2019-05-30 | 2019-09-26
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | CO302ST | 18 RICHMOND TERRACE - EXTERIOR STEPS RECONSTRUCTION | 3 | FINAL DESIGN | 2019-09-27 | 2020-03-24 | 2019-09-27 | 2020-03-24
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | CO302ST | 18 RICHMOND TERRACE - EXTERIOR STEPS RECONSTRUCTION | 4 | BID AWARD AND REGISTER CONTRCT | 2020-03-25 | 2020-06-22 | 2020-03-25 | 2020-06-22
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | CO302ST | 18 RICHMOND TERRACE - EXTERIOR STEPS RECONSTRUCTION | 5 | CONSTRUCTION TO 25% | 2020-06-23 | 2020-10-20 | 2020-06-23 | 2020-10-20
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | CO302ST | 18 RICHMOND TERRACE - EXTERIOR STEPS RECONSTRUCTION | 6 | CONSTRUCTION TO 50% | 2020-10-21 | 2021-02-17 | 2020-10-21 | 2021-02-17
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | CO302ST | 18 RICHMOND TERRACE - EXTERIOR STEPS RECONSTRUCTION | 7 | CONSTRUCTION TO 75% | 2021-02-18 | 2021-06-17 | 2021-02-18 | 2021-06-17
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | CO302ST | 18 RICHMOND TERRACE - EXTERIOR STEPS RECONSTRUCTION | 8 | ORIGINAL EQUIP & FURNISHING | 2021-06-18 | 2021-09-15 | 2021-06-18 | 2021-09-15
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | CO302ST | 18 RICHMOND TERRACE - EXTERIOR STEPS RECONSTRUCTION | 9 | SUBSTANTIAL COMPLETION | 2021-09-16 | 2021-11-14 | 2021-09-16 | 2021-11-14
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | CO302ST | 18 RICHMOND TERRACE - EXTERIOR STEPS RECONSTRUCTION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-11-15 | 2021-12-14 | 2021-11-15 | 2021-12-14
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM18MHCC | Mariner's Harbor Community Center | 1 | PROJECT START | 2019-02-28 | 2019-02-28 | 2019-02-28 | 2019-02-28
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM18MHCC | Mariner's Harbor Community Center | 2 | DESIGN START | 2019-03-01 | 2019-07-05 | 2019-03-01 | 2019-07-05
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM18MHCC | Mariner's Harbor Community Center | 3 | DESIGN COMPLETION | 2019-07-06 | 2020-07-06 | 2019-07-06 | 2020-07-06
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM18MHCC | Mariner's Harbor Community Center | 4 | CONSTRUCTION START | 2020-07-07 | 2021-04-05 | 2020-07-07 | 2021-04-05
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM18MHCC | Mariner's Harbor Community Center | 5 | CONSTRUCTION COMPLETION | 2021-04-06 | 2022-04-05 | 2021-04-06 | 2022-04-05
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115HHFA | Hospitality at 100 Central Ave., 10301 - Fire Alarm Upgrade | 1 | PROJECT START | 2016-03-30 | 2016-03-31 | 2016-03-30 | 2016-03-31
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115HHFA | Hospitality at 100 Central Ave., 10301 - Fire Alarm Upgrade | 2 | DESIGN START | 2016-04-01 | 2016-07-01 | 2016-04-01 | 2016-07-01
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115HHFA | Hospitality at 100 Central Ave., 10301 - Fire Alarm Upgrade | 3 | DESIGN COMPLETION | 2016-07-02 | 2017-06-30 | 2016-07-02 | 2017-06-30
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115HHFA | Hospitality at 100 Central Ave., 10301 - Fire Alarm Upgrade | 4 | CONSTRUCTION START | 2017-07-01 | 2017-10-31 | 2017-07-01 | 2017-10-31
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115HHFA | Hospitality at 100 Central Ave., 10301 - Fire Alarm Upgrade | 5 | CONSTRUCTION COMPLETION | 2017-11-01 | 2023-06-30 | 2017-11-01 | 2023-06-30
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82SIABE | REHAB OF THE STATEN ISLAND ANIMAL SHELTER | 1 | PROJECT START | 2008-12-01 | 2008-12-01 | 2008-12-01 | 2008-12-01
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82SIABE | REHAB OF THE STATEN ISLAND ANIMAL SHELTER | 2 | DESIGN START | 2008-12-02 | 2009-05-01 | 2008-12-02 | 2009-05-01
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82SIABE | REHAB OF THE STATEN ISLAND ANIMAL SHELTER | 3 | DESIGN COMPLETION | 2009-05-02 | 2010-05-31 | 2009-05-02 | 2010-05-31
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82SIABE | REHAB OF THE STATEN ISLAND ANIMAL SHELTER | 4 | CONSTRUCTION START | 2010-06-01 | 2010-12-01 | 2010-06-01 | 2010-12-01
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82SIABE | REHAB OF THE STATEN ISLAND ANIMAL SHELTER | 5 | CONSTRUCTION COMPLETION | 2010-12-02 | 2011-06-30 | 2010-12-02 | 2021-06-30
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD104-05 | RECON AND IMPROVEMENT OF AMBOY ROAD WITH HUGUENOT AVE SI | 1 | DEVELOP SCOPE | 2010-07-01 | 2010-09-28 | 2010-07-01 | 2010-09-28
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD104-05 | RECON AND IMPROVEMENT OF AMBOY ROAD WITH HUGUENOT AVE SI | 2 | PRELIMINARY DESIGN | 2010-09-29 | 2011-01-26 | 2010-09-29 | 2011-01-26
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD104-05 | RECON AND IMPROVEMENT OF AMBOY ROAD WITH HUGUENOT AVE SI | 3 | FINAL DESIGN | 2011-01-27 | 2011-07-25 | 2011-01-27 | 2015-05-03
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD104-05 | RECON AND IMPROVEMENT OF AMBOY ROAD WITH HUGUENOT AVE SI | 4 | BID AWARD AND REGISTER CONTRCT | 2011-07-26 | 2011-10-23 | 2015-05-04 | 2015-08-03
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD104-05 | RECON AND IMPROVEMENT OF AMBOY ROAD WITH HUGUENOT AVE SI | 5 | CONSTRUCTION TO 25% | 2011-10-24 | 2012-02-20 | 2015-08-04 | 2015-12-01
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD104-05 | RECON AND IMPROVEMENT OF AMBOY ROAD WITH HUGUENOT AVE SI | 6 | CONSTRUCTION TO 50% | 2012-02-21 | 2012-06-19 | 2015-12-02 | 2016-04-04
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD104-05 | RECON AND IMPROVEMENT OF AMBOY ROAD WITH HUGUENOT AVE SI | 7 | CONSTRUCTION TO 75% | 2012-06-20 | 2012-10-17 | 2016-04-05 | 2016-12-10
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD104-05 | RECON AND IMPROVEMENT OF AMBOY ROAD WITH HUGUENOT AVE SI | 8 | ORIGINAL EQUIP & FURNISHING | 2012-10-18 | 2013-01-15 | 2016-12-11 | 2017-03-10
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD104-05 | RECON AND IMPROVEMENT OF AMBOY ROAD WITH HUGUENOT AVE SI | 9 | SUBSTANTIAL COMPLETION | 2013-01-16 | 2013-03-16 | 2017-03-11 | 2017-05-09
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD104-05 | RECON AND IMPROVEMENT OF AMBOY ROAD WITH HUGUENOT AVE SI | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-03-17 | 2013-04-15 | 2017-05-10 | 2024-06-30
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP14RTA | CITYWIDE COMPLEX PED RAMPS (TRANSIT AUTHORITY) - SI | 1 | DEVELOP SCOPE | 2014-05-17 | 2014-08-14 | 2014-05-17 | 2014-08-14
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP14RTA | CITYWIDE COMPLEX PED RAMPS (TRANSIT AUTHORITY) - SI | 2 | PRELIMINARY DESIGN | 2014-08-15 | 2014-12-12 | 2014-08-15 | 2014-12-12
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP14RTA | CITYWIDE COMPLEX PED RAMPS (TRANSIT AUTHORITY) - SI | 3 | FINAL DESIGN | 2014-12-13 | 2015-06-10 | 2014-12-13 | 2015-06-10
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP14RTA | CITYWIDE COMPLEX PED RAMPS (TRANSIT AUTHORITY) - SI | 4 | BID AWARD AND REGISTER CONTRCT | 2015-06-11 | 2015-09-08 | 2015-06-11 | 2015-09-08
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP14RTA | CITYWIDE COMPLEX PED RAMPS (TRANSIT AUTHORITY) - SI | 5 | CONSTRUCTION TO 25% | 2015-09-09 | 2016-01-06 | 2015-09-09 | 2016-01-06
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP14RTA | CITYWIDE COMPLEX PED RAMPS (TRANSIT AUTHORITY) - SI | 6 | CONSTRUCTION TO 50% | 2016-01-07 | 2016-05-05 | 2016-01-07 | 2016-05-05
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP14RTA | CITYWIDE COMPLEX PED RAMPS (TRANSIT AUTHORITY) - SI | 7 | CONSTRUCTION TO 75% | 2016-05-06 | 2016-09-02 | 2016-05-06 | 2016-09-02
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP14RTA | CITYWIDE COMPLEX PED RAMPS (TRANSIT AUTHORITY) - SI | 8 | ORIGINAL EQUIP & FURNISHING | 2016-09-03 | 2016-12-01 | 2016-09-03 | 2016-12-01
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP14RTA | CITYWIDE COMPLEX PED RAMPS (TRANSIT AUTHORITY) - SI | 9 | SUBSTANTIAL COMPLETION | 2016-12-02 | 2017-01-30 | 2016-12-02 | 2017-01-30
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP14RTA | CITYWIDE COMPLEX PED RAMPS (TRANSIT AUTHORITY) - SI | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-01-31 | 2017-03-01 | 2017-01-31 | 2022-06-03
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP15RSC | Simple & Complex Ped Ramps - Staten Island | 4 | BID AWARD AND REGISTER CONTRCT | 2016-03-12 | 2016-06-09 | 2016-03-12 | 2016-06-09
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP15RSC | Simple & Complex Ped Ramps - Staten Island | 5 | CONSTRUCTION TO 25% | 2016-06-10 | 2016-10-07 | 2016-06-10 | 2016-10-07
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP15RSC | Simple & Complex Ped Ramps - Staten Island | 6 | CONSTRUCTION TO 50% | 2016-10-08 | 2017-02-04 | 2016-10-08 | 2017-02-04
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP15RSC | Simple & Complex Ped Ramps - Staten Island | 7 | CONSTRUCTION TO 75% | 2017-02-05 | 2017-06-04 | 2017-02-05 | 2017-06-04
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP15RSC | Simple & Complex Ped Ramps - Staten Island | 8 | ORIGINAL EQUIP & FURNISHING | 2017-06-05 | 2017-09-02 | 2017-06-05 | 2017-09-02
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP15RSC | Simple & Complex Ped Ramps - Staten Island | 9 | SUBSTANTIAL COMPLETION | 2017-09-03 | 2017-11-01 | 2017-09-03 | 2017-11-01
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP15RSC | Simple & Complex Ped Ramps - Staten Island | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-11-02 | 2017-12-01 | 2017-11-02 | 2020-03-15
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2008R | CITYWIDE PED RAMPS - STATEN ISLAND(SIM) | 1 | DEVELOP SCOPE | 2006-12-21 | 2007-03-20 | 2006-12-21 | 2007-03-20
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2008R | CITYWIDE PED RAMPS - STATEN ISLAND(SIM) | 2 | PRELIMINARY DESIGN | 2007-03-21 | 2007-07-18 | 2007-03-21 | 2007-07-18
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2008R | CITYWIDE PED RAMPS - STATEN ISLAND(SIM) | 3 | FINAL DESIGN | 2007-07-19 | 2008-01-14 | 2007-07-19 | 2008-01-14
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2008R | CITYWIDE PED RAMPS - STATEN ISLAND(SIM) | 4 | BID AWARD AND REGISTER CONTRCT | 2008-01-15 | 2008-04-13 | 2008-01-15 | 2008-04-13
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2008R | CITYWIDE PED RAMPS - STATEN ISLAND(SIM) | 5 | CONSTRUCTION TO 25% | 2008-04-14 | 2008-08-11 | 2008-04-14 | 2008-08-11
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2008R | CITYWIDE PED RAMPS - STATEN ISLAND(SIM) | 6 | CONSTRUCTION TO 50% | 2008-08-12 | 2008-12-09 | 2008-08-12 | 2008-12-09
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2008R | CITYWIDE PED RAMPS - STATEN ISLAND(SIM) | 7 | CONSTRUCTION TO 75% | 2008-12-10 | 2009-04-08 | 2008-12-10 | 2009-04-08
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2008R | CITYWIDE PED RAMPS - STATEN ISLAND(SIM) | 8 | ORIGINAL EQUIP & FURNISHING | 2009-04-09 | 2009-07-07 | 2009-04-09 | 2009-07-07
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2008R | CITYWIDE PED RAMPS - STATEN ISLAND(SIM) | 9 | SUBSTANTIAL COMPLETION | 2009-07-08 | 2009-09-05 | 2009-07-08 | 2009-09-05
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2008R | CITYWIDE PED RAMPS - STATEN ISLAND(SIM) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2009-09-06 | 2009-10-05 | 2009-09-06 | 2029-06-30
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2010R | CITYWIDE PED RAMPS - STATEN ISLAND | 3 | FINAL DESIGN | 2010-01-02 | 2010-06-30 | 2010-01-02 | 2010-06-30
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2010R | CITYWIDE PED RAMPS - STATEN ISLAND | 4 | BID AWARD AND REGISTER CONTRCT | 2010-07-01 | 2010-09-28 | 2010-07-01 | 2010-09-28
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2010R | CITYWIDE PED RAMPS - STATEN ISLAND | 5 | CONSTRUCTION TO 25% | 2010-09-29 | 2011-01-26 | 2010-09-29 | 2011-01-26
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2010R | CITYWIDE PED RAMPS - STATEN ISLAND | 6 | CONSTRUCTION TO 50% | 2011-01-27 | 2011-05-26 | 2011-01-27 | 2011-05-26
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2010R | CITYWIDE PED RAMPS - STATEN ISLAND | 7 | CONSTRUCTION TO 75% | 2011-05-27 | 2011-09-23 | 2011-05-27 | 2011-09-23
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2010R | CITYWIDE PED RAMPS - STATEN ISLAND | 8 | ORIGINAL EQUIP & FURNISHING | 2011-09-24 | 2011-12-22 | 2011-09-24 | 2011-12-22
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2010R | CITYWIDE PED RAMPS - STATEN ISLAND | 9 | SUBSTANTIAL COMPLETION | 2011-12-23 | 2012-02-20 | 2011-12-23 | 2012-02-20
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2010R | CITYWIDE PED RAMPS - STATEN ISLAND | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-02-21 | 2012-03-21 | 2012-02-21 | 2012-03-21
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19R | Pedestrian Ramp Rehabilitation - Staten Island | 1 | DEVELOP SCOPE | 2017-06-30 | 2017-09-27 | 2017-06-30 | 2017-09-27
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19R | Pedestrian Ramp Rehabilitation - Staten Island | 2 | PRELIMINARY DESIGN | 2017-09-28 | 2018-01-25 | 2017-09-28 | 2018-01-25
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19R | Pedestrian Ramp Rehabilitation - Staten Island | 3 | FINAL DESIGN | 2018-01-26 | 2018-07-24 | 2018-01-26 | 2018-07-24
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19R | Pedestrian Ramp Rehabilitation - Staten Island | 4 | BID AWARD AND REGISTER CONTRCT | 2018-07-25 | 2018-10-22 | 2018-07-25 | 2018-10-22
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19R | Pedestrian Ramp Rehabilitation - Staten Island | 5 | CONSTRUCTION TO 25% | 2018-10-23 | 2019-02-19 | 2018-10-23 | 2019-02-19
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19R | Pedestrian Ramp Rehabilitation - Staten Island | 6 | CONSTRUCTION TO 50% | 2019-02-20 | 2019-06-19 | 2019-02-20 | 2019-06-19
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19R | Pedestrian Ramp Rehabilitation - Staten Island | 7 | CONSTRUCTION TO 75% | 2019-06-20 | 2019-10-17 | 2019-06-20 | 2019-10-17
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19R | Pedestrian Ramp Rehabilitation - Staten Island | 8 | ORIGINAL EQUIP & FURNISHING | 2019-10-18 | 2020-01-15 | 2019-10-18 | 2020-01-15
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19R | Pedestrian Ramp Rehabilitation - Staten Island | 9 | SUBSTANTIAL COMPLETION | 2020-01-16 | 2020-03-15 | 2020-01-16 | 2020-03-15
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19R | Pedestrian Ramp Rehabilitation - Staten Island | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-03-16 | 2020-04-14 | 2020-03-16 | 2024-03-26
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00505 | VICTORY BLVD AND MANOR ROAD INTERSECTION IMPROVEMENT | 1 | DEVELOP SCOPE | 2011-03-01 | 2011-05-29 | 2011-03-01 | 2011-05-29
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00505 | VICTORY BLVD AND MANOR ROAD INTERSECTION IMPROVEMENT | 2 | PRELIMINARY DESIGN | 2011-05-30 | 2011-09-26 | 2011-05-30 | 2011-09-26
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00505 | VICTORY BLVD AND MANOR ROAD INTERSECTION IMPROVEMENT | 3 | FINAL DESIGN | 2011-09-27 | 2012-03-24 | 2011-09-27 | 2016-03-25
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00505 | VICTORY BLVD AND MANOR ROAD INTERSECTION IMPROVEMENT | 4 | BID AWARD AND REGISTER CONTRCT | 2012-03-25 | 2012-06-22 | 2016-03-26 | 2016-06-23
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00505 | VICTORY BLVD AND MANOR ROAD INTERSECTION IMPROVEMENT | 5 | CONSTRUCTION TO 25% | 2012-06-23 | 2012-10-20 | 2016-06-24 | 2016-12-20
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00505 | VICTORY BLVD AND MANOR ROAD INTERSECTION IMPROVEMENT | 6 | CONSTRUCTION TO 50% | 2012-10-21 | 2013-02-17 | 2016-12-21 | 2017-06-18
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00505 | VICTORY BLVD AND MANOR ROAD INTERSECTION IMPROVEMENT | 7 | CONSTRUCTION TO 75% | 2013-02-18 | 2013-06-17 | 2017-06-19 | 2017-12-15
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00505 | VICTORY BLVD AND MANOR ROAD INTERSECTION IMPROVEMENT | 8 | ORIGINAL EQUIP & FURNISHING | 2013-06-18 | 2013-09-15 | 2017-12-16 | 2018-03-25
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00505 | VICTORY BLVD AND MANOR ROAD INTERSECTION IMPROVEMENT | 9 | SUBSTANTIAL COMPLETION | 2013-09-16 | 2013-11-14 | 2018-03-26 | 2018-06-23
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00505 | VICTORY BLVD AND MANOR ROAD INTERSECTION IMPROVEMENT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-11-15 | 2013-12-14 | 2018-06-24 | 2023-12-11
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00508 | AMBOY ROAD IMPROVEMENTS AT ELTINGVILLE CORRIDOR | 1 | DEVELOP SCOPE | 2011-06-30 | 2011-09-27 | 2011-06-30 | 2011-09-27
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00508 | AMBOY ROAD IMPROVEMENTS AT ELTINGVILLE CORRIDOR | 2 | PRELIMINARY DESIGN | 2011-09-28 | 2012-01-25 | 2011-09-28 | 2012-01-25
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00508 | AMBOY ROAD IMPROVEMENTS AT ELTINGVILLE CORRIDOR | 3 | FINAL DESIGN | 2012-01-26 | 2012-07-23 | 2012-01-26 | 2016-03-25
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00508 | AMBOY ROAD IMPROVEMENTS AT ELTINGVILLE CORRIDOR | 4 | BID AWARD AND REGISTER CONTRCT | 2012-07-24 | 2012-10-21 | 2016-03-26 | 2016-06-23
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00508 | AMBOY ROAD IMPROVEMENTS AT ELTINGVILLE CORRIDOR | 5 | CONSTRUCTION TO 25% | 2012-10-22 | 2013-02-18 | 2016-06-24 | 2016-12-20
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00508 | AMBOY ROAD IMPROVEMENTS AT ELTINGVILLE CORRIDOR | 6 | CONSTRUCTION TO 50% | 2013-02-19 | 2013-06-18 | 2016-12-21 | 2017-06-18
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00508 | AMBOY ROAD IMPROVEMENTS AT ELTINGVILLE CORRIDOR | 7 | CONSTRUCTION TO 75% | 2013-06-19 | 2013-10-16 | 2017-06-19 | 2017-12-15
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00508 | AMBOY ROAD IMPROVEMENTS AT ELTINGVILLE CORRIDOR | 8 | ORIGINAL EQUIP & FURNISHING | 2013-10-17 | 2014-01-14 | 2017-12-16 | 2018-03-15
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00508 | AMBOY ROAD IMPROVEMENTS AT ELTINGVILLE CORRIDOR | 9 | SUBSTANTIAL COMPLETION | 2014-01-15 | 2014-03-15 | 2018-03-16 | 2018-05-14
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00508 | AMBOY ROAD IMPROVEMENTS AT ELTINGVILLE CORRIDOR | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-03-16 | 2014-04-14 | 2018-05-15 | 2022-12-16
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00510 | Woodrow Rd Improvements btw Gladwin Ave & Veterans Rd East | 1 | DEVELOP SCOPE | 2013-06-30 | 2013-09-27 | 2013-06-30 | 2013-09-27
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00510 | Woodrow Rd Improvements btw Gladwin Ave & Veterans Rd East | 2 | PRELIMINARY DESIGN | 2013-09-28 | 2014-01-25 | 2013-09-28 | 2014-09-27
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00510 | Woodrow Rd Improvements btw Gladwin Ave & Veterans Rd East | 3 | FINAL DESIGN | 2014-01-26 | 2014-07-24 | 2014-09-28 | 2017-09-21
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00510 | Woodrow Rd Improvements btw Gladwin Ave & Veterans Rd East | 4 | BID AWARD AND REGISTER CONTRCT | 2014-07-25 | 2014-10-22 | 2017-09-22 | 2017-09-21
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00510 | Woodrow Rd Improvements btw Gladwin Ave & Veterans Rd East | 5 | CONSTRUCTION TO 25% | 2014-10-23 | 2015-02-19 | 2017-09-22 | 2017-09-21
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00510 | Woodrow Rd Improvements btw Gladwin Ave & Veterans Rd East | 6 | CONSTRUCTION TO 50% | 2015-02-20 | 2015-06-19 | 2017-09-22 | 2017-09-21
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00510 | Woodrow Rd Improvements btw Gladwin Ave & Veterans Rd East | 7 | CONSTRUCTION TO 75% | 2015-06-20 | 2015-10-17 | 2017-09-22 | 2017-09-21
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00510 | Woodrow Rd Improvements btw Gladwin Ave & Veterans Rd East | 8 | ORIGINAL EQUIP & FURNISHING | 2015-10-18 | 2016-01-15 | 2017-09-22 | 2017-09-21
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00510 | Woodrow Rd Improvements btw Gladwin Ave & Veterans Rd East | 9 | SUBSTANTIAL COMPLETION | 2016-01-16 | 2016-03-15 | 2017-09-22 | 2017-09-21
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00510 | Woodrow Rd Improvements btw Gladwin Ave & Veterans Rd East | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-16 | 2016-04-14 | 2017-09-22 | 2027-06-30
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00511 | Travis Avenue Widening | 1 | DEVELOP SCOPE | 2013-06-30 | 2013-09-27 | 2013-06-30 | 2013-09-27
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00511 | Travis Avenue Widening | 2 | PRELIMINARY DESIGN | 2013-09-28 | 2014-01-25 | 2013-09-28 | 2014-01-25
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00511 | Travis Avenue Widening | 3 | FINAL DESIGN | 2014-01-26 | 2014-07-24 | 2014-01-26 | 2017-03-13
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00511 | Travis Avenue Widening | 4 | BID AWARD AND REGISTER CONTRCT | 2014-07-25 | 2014-10-22 | 2017-03-14 | 2017-06-11
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00511 | Travis Avenue Widening | 5 | CONSTRUCTION TO 25% | 2014-10-23 | 2015-02-19 | 2017-06-12 | 2017-12-08
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00511 | Travis Avenue Widening | 6 | CONSTRUCTION TO 50% | 2015-02-20 | 2015-06-19 | 2017-12-09 | 2018-06-06
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00511 | Travis Avenue Widening | 7 | CONSTRUCTION TO 75% | 2015-06-20 | 2015-10-17 | 2018-06-07 | 2018-12-03
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00511 | Travis Avenue Widening | 8 | ORIGINAL EQUIP & FURNISHING | 2015-10-18 | 2016-01-15 | 2018-12-04 | 2019-03-03
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00511 | Travis Avenue Widening | 9 | SUBSTANTIAL COMPLETION | 2016-01-16 | 2016-03-15 | 2019-03-04 | 2019-05-02
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00511 | Travis Avenue Widening | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-16 | 2016-04-14 | 2019-05-03 | 2024-03-10
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00512 | Richmond Valley Road | 1 | DEVELOP SCOPE | 2016-03-01 | 2016-05-29 | 2016-03-01 | 2016-05-29
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00512 | Richmond Valley Road | 2 | PRELIMINARY DESIGN | 2016-05-30 | 2016-09-26 | 2016-05-30 | 2016-09-26
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00512 | Richmond Valley Road | 3 | FINAL DESIGN | 2016-09-27 | 2017-03-25 | 2016-09-27 | 2017-03-25
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00512 | Richmond Valley Road | 4 | BID AWARD AND REGISTER CONTRCT | 2017-03-26 | 2017-06-23 | 2017-03-26 | 2017-06-23
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00512 | Richmond Valley Road | 5 | CONSTRUCTION TO 25% | 2017-06-24 | 2017-10-21 | 2017-06-24 | 2017-10-21
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00512 | Richmond Valley Road | 6 | CONSTRUCTION TO 50% | 2017-10-22 | 2018-02-18 | 2017-10-22 | 2018-02-18
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00512 | Richmond Valley Road | 7 | CONSTRUCTION TO 75% | 2018-02-19 | 2018-06-18 | 2018-02-19 | 2018-06-18
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00512 | Richmond Valley Road | 8 | ORIGINAL EQUIP & FURNISHING | 2018-06-19 | 2018-09-16 | 2018-06-19 | 2018-09-16
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00512 | Richmond Valley Road | 9 | SUBSTANTIAL COMPLETION | 2018-09-17 | 2018-11-15 | 2018-09-17 | 2018-11-15
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00512 | Richmond Valley Road | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-11-16 | 2018-12-15 | 2018-11-16 | 2024-09-30
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR005B | TODT HILL ROAD CURVE REHAB, | 1 | DEVELOP SCOPE | 2007-02-21 | 2007-06-20 | 2007-02-21 | 2007-05-21
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR005B | TODT HILL ROAD CURVE REHAB, | 2 | DESIGN START | 2007-06-21 | 2008-12-11 | 2007-05-22 | 2007-09-18
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR005B | TODT HILL ROAD CURVE REHAB, | 3 | CONSTRUCTION START | 2008-12-12 | 2010-12-01 | 2007-09-19 | 2017-03-05
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR005B | TODT HILL ROAD CURVE REHAB, | 4 | BID AWARD AND REGISTER CONTRCT | 2008-12-12 | 2010-12-01 | 2017-03-06 | 2017-06-03
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR005B | TODT HILL ROAD CURVE REHAB, | 5 | CONSTRUCTION TO 25% | 2008-12-12 | 2010-12-01 | 2017-06-04 | 2017-11-30
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR005B | TODT HILL ROAD CURVE REHAB, | 6 | CONSTRUCTION TO 50% | 2008-12-12 | 2010-12-01 | 2017-12-01 | 2018-05-29
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR005B | TODT HILL ROAD CURVE REHAB, | 7 | CONSTRUCTION TO 75% | 2008-12-12 | 2010-12-01 | 2018-05-30 | 2018-11-25
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR005B | TODT HILL ROAD CURVE REHAB, | 8 | ORIGINAL EQUIP & FURNISHING | 2008-12-12 | 2010-12-01 | 2018-11-26 | 2019-02-23
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR005B | TODT HILL ROAD CURVE REHAB, | 9 | SUBSTANTIAL COMPLETION | 2008-12-12 | 2010-12-01 | 2019-02-24 | 2019-04-24
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR005B | TODT HILL ROAD CURVE REHAB, | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-12-12 | 2010-12-01 | 2019-04-25 | 2025-09-09
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR005B1 | TODT HILL ROAD - CIRCLE RD | 1 | DEVELOP SCOPE | 2008-02-23 | 2008-05-22 | 2008-02-23 | 2008-05-22
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR005B1 | TODT HILL ROAD - CIRCLE RD | 2 | PRELIMINARY DESIGN | 2008-05-23 | 2008-09-19 | 2008-05-23 | 2008-09-19
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR005B1 | TODT HILL ROAD - CIRCLE RD | 3 | FINAL DESIGN | 2008-09-20 | 2009-03-18 | 2008-09-20 | 2009-03-18
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR005B1 | TODT HILL ROAD - CIRCLE RD | 4 | BID AWARD AND REGISTER CONTRCT | 2009-03-19 | 2009-06-16 | 2011-11-15 | 2012-02-12
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR005B1 | TODT HILL ROAD - CIRCLE RD | 5 | CONSTRUCTION TO 25% | 2009-06-17 | 2009-10-14 | 2012-02-13 | 2012-02-12
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR005B1 | TODT HILL ROAD - CIRCLE RD | 6 | CONSTRUCTION TO 50% | 2009-10-15 | 2010-02-11 | 2012-02-13 | 2012-02-12
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR005B1 | TODT HILL ROAD - CIRCLE RD | 7 | CONSTRUCTION TO 75% | 2010-02-12 | 2010-06-11 | 2012-02-13 | 2012-02-12
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR005B1 | TODT HILL ROAD - CIRCLE RD | 8 | ORIGINAL EQUIP & FURNISHING | 2010-06-12 | 2010-09-09 | 2012-02-13 | 2012-02-12
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR005B1 | TODT HILL ROAD - CIRCLE RD | 9 | SUBSTANTIAL COMPLETION | 2010-09-10 | 2010-11-08 | 2012-02-13 | 2012-02-12
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR005B1 | TODT HILL ROAD - CIRCLE RD | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2010-11-09 | 2010-12-08 | 2014-02-12 | 2023-09-14
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR1140A | ARTHUR KILL ROAD (PHASE I) - CLARKE AVE, RICHMOD AV, RED-366 | 1 | DEVELOP SCOPE | 2004-05-21 | 2004-08-18 | 2004-05-21 | 2004-08-18
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR1140A | ARTHUR KILL ROAD (PHASE I) - CLARKE AVE, RICHMOD AV, RED-366 | 2 | PRELIMINARY DESIGN | 2004-08-19 | 2004-12-16 | 2004-08-19 | 2004-12-16
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR1140A | ARTHUR KILL ROAD (PHASE I) - CLARKE AVE, RICHMOD AV, RED-366 | 3 | FINAL DESIGN | 2004-12-17 | 2005-06-14 | 2004-12-17 | 2005-06-14
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR1140A | ARTHUR KILL ROAD (PHASE I) - CLARKE AVE, RICHMOD AV, RED-366 | 4 | BID AWARD AND REGISTER CONTRCT | 2005-06-15 | 2005-09-12 | 2005-06-16 | 2022-06-13
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR1140A | ARTHUR KILL ROAD (PHASE I) - CLARKE AVE, RICHMOD AV, RED-366 | 5 | CONSTRUCTION TO 25% | 2005-09-13 | 2006-01-10 | 2022-06-14 | 2022-06-13
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR1140A | ARTHUR KILL ROAD (PHASE I) - CLARKE AVE, RICHMOD AV, RED-366 | 6 | CONSTRUCTION TO 50% | 2006-01-11 | 2006-05-10 | 2022-06-14 | 2022-06-13
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR1140A | ARTHUR KILL ROAD (PHASE I) - CLARKE AVE, RICHMOD AV, RED-366 | 7 | CONSTRUCTION TO 75% | 2006-05-11 | 2006-09-07 | 2022-06-14 | 2022-06-13
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR1140A | ARTHUR KILL ROAD (PHASE I) - CLARKE AVE, RICHMOD AV, RED-366 | 8 | ORIGINAL EQUIP & FURNISHING | 2006-09-08 | 2006-12-06 | 2022-06-14 | 2022-06-13
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR1140A | ARTHUR KILL ROAD (PHASE I) - CLARKE AVE, RICHMOD AV, RED-366 | 9 | SUBSTANTIAL COMPLETION | 2006-12-07 | 2007-02-04 | 2022-06-14 | 2022-06-13
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR1140A | ARTHUR KILL ROAD (PHASE I) - CLARKE AVE, RICHMOD AV, RED-366 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2007-02-05 | 2007-03-06 | 2023-11-14 | 2023-12-13
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR1140B | ARTHUR KILL ROAD (PHASE II) - RICHMOND AVE AND HUGUENOT AVE | 1 | DEVELOP SCOPE | 2009-03-04 | 2009-06-01 | 2009-03-04 | 2009-06-01
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR1140B | ARTHUR KILL ROAD (PHASE II) - RICHMOND AVE AND HUGUENOT AVE | 2 | PRELIMINARY DESIGN | 2009-06-02 | 2009-09-29 | 2009-06-02 | 2009-09-29
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR1140B | ARTHUR KILL ROAD (PHASE II) - RICHMOND AVE AND HUGUENOT AVE | 3 | FINAL DESIGN | 2009-09-30 | 2010-03-28 | 2009-09-30 | 2010-03-28
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR1140B | ARTHUR KILL ROAD (PHASE II) - RICHMOND AVE AND HUGUENOT AVE | 4 | BID AWARD AND REGISTER CONTRCT | 2010-03-29 | 2010-06-26 | 2022-03-30 | 2022-06-27
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR1140B | ARTHUR KILL ROAD (PHASE II) - RICHMOND AVE AND HUGUENOT AVE | 5 | CONSTRUCTION TO 25% | 2010-06-27 | 2010-10-24 | 2022-06-28 | 2022-06-27
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR1140B | ARTHUR KILL ROAD (PHASE II) - RICHMOND AVE AND HUGUENOT AVE | 6 | CONSTRUCTION TO 50% | 2010-10-25 | 2011-02-21 | 2022-06-28 | 2022-06-27
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR1140B | ARTHUR KILL ROAD (PHASE II) - RICHMOND AVE AND HUGUENOT AVE | 7 | CONSTRUCTION TO 75% | 2011-02-22 | 2011-06-21 | 2022-06-28 | 2022-06-27
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR1140B | ARTHUR KILL ROAD (PHASE II) - RICHMOND AVE AND HUGUENOT AVE | 8 | ORIGINAL EQUIP & FURNISHING | 2011-06-22 | 2011-09-19 | 2022-06-28 | 2022-06-27
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR1140B | ARTHUR KILL ROAD (PHASE II) - RICHMOND AVE AND HUGUENOT AVE | 9 | SUBSTANTIAL COMPLETION | 2011-09-20 | 2011-11-18 | 2022-06-28 | 2022-06-27
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR1140B | ARTHUR KILL ROAD (PHASE II) - RICHMOND AVE AND HUGUENOT AVE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2011-11-19 | 2011-12-18 | 2024-01-27 | 2025-06-30
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR1160 | RE- ALIGN ROCKLAND AVE AT MANOR RD/MEISNER AVE | 1 | DEVELOP SCOPE | 2003-07-01 | 2003-09-28 | 2003-07-01 | 2003-09-28
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR1160 | RE- ALIGN ROCKLAND AVE AT MANOR RD/MEISNER AVE | 2 | PRELIMINARY DESIGN | 2003-09-29 | 2004-01-26 | 2003-09-29 | 2004-01-26
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR1160 | RE- ALIGN ROCKLAND AVE AT MANOR RD/MEISNER AVE | 3 | FINAL DESIGN | 2004-01-27 | 2004-07-24 | 2004-01-27 | 2004-07-24
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR1160 | RE- ALIGN ROCKLAND AVE AT MANOR RD/MEISNER AVE | 4 | BID AWARD AND REGISTER CONTRCT | 2004-07-25 | 2004-10-22 | 2022-03-18 | 2022-06-15
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR1160 | RE- ALIGN ROCKLAND AVE AT MANOR RD/MEISNER AVE | 5 | CONSTRUCTION TO 25% | 2004-10-23 | 2005-02-19 | 2022-06-16 | 2022-06-15
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR1160 | RE- ALIGN ROCKLAND AVE AT MANOR RD/MEISNER AVE | 6 | CONSTRUCTION TO 50% | 2005-02-20 | 2005-06-19 | 2022-06-16 | 2022-06-15
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR1160 | RE- ALIGN ROCKLAND AVE AT MANOR RD/MEISNER AVE | 7 | CONSTRUCTION TO 75% | 2005-06-20 | 2005-10-17 | 2022-06-16 | 2022-06-15
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR1160 | RE- ALIGN ROCKLAND AVE AT MANOR RD/MEISNER AVE | 8 | ORIGINAL EQUIP & FURNISHING | 2005-10-18 | 2006-01-15 | 2022-06-16 | 2022-06-15
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR1160 | RE- ALIGN ROCKLAND AVE AT MANOR RD/MEISNER AVE | 9 | SUBSTANTIAL COMPLETION | 2006-01-16 | 2006-03-16 | 2022-06-16 | 2022-06-15
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR1160 | RE- ALIGN ROCKLAND AVE AT MANOR RD/MEISNER AVE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2006-03-17 | 2006-04-15 | 2022-06-17 | 2025-12-23
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR300-03 | ROAD WIDENING AT SOUTH AVENUE AND FOREST AVENUE | 1 | DEVELOP SCOPE | 2010-06-01 | 2010-08-29 | 2010-06-01 | 2010-08-29
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR300-03 | ROAD WIDENING AT SOUTH AVENUE AND FOREST AVENUE | 2 | PRELIMINARY DESIGN | 2010-08-30 | 2010-12-27 | 2010-08-30 | 2010-12-27
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR300-03 | ROAD WIDENING AT SOUTH AVENUE AND FOREST AVENUE | 3 | FINAL DESIGN | 2010-12-28 | 2011-06-25 | 2010-12-28 | 2015-05-25
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR300-03 | ROAD WIDENING AT SOUTH AVENUE AND FOREST AVENUE | 4 | BID AWARD AND REGISTER CONTRCT | 2011-06-26 | 2011-09-23 | 2015-05-26 | 2015-08-23
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR300-03 | ROAD WIDENING AT SOUTH AVENUE AND FOREST AVENUE | 5 | CONSTRUCTION TO 25% | 2011-09-24 | 2012-01-21 | 2015-08-24 | 2016-02-19
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR300-03 | ROAD WIDENING AT SOUTH AVENUE AND FOREST AVENUE | 6 | CONSTRUCTION TO 50% | 2012-01-22 | 2012-05-20 | 2016-02-20 | 2016-08-17
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR300-03 | ROAD WIDENING AT SOUTH AVENUE AND FOREST AVENUE | 7 | CONSTRUCTION TO 75% | 2012-05-21 | 2012-09-17 | 2016-02-15 | 2017-02-13
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR300-03 | ROAD WIDENING AT SOUTH AVENUE AND FOREST AVENUE | 8 | ORIGINAL EQUIP & FURNISHING | 2012-09-18 | 2012-12-16 | 2017-02-14 | 2017-05-14
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR300-03 | ROAD WIDENING AT SOUTH AVENUE AND FOREST AVENUE | 9 | SUBSTANTIAL COMPLETION | 2012-12-17 | 2013-02-14 | 2017-05-15 | 2017-07-13
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR300-03 | ROAD WIDENING AT SOUTH AVENUE AND FOREST AVENUE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-02-15 | 2013-03-16 | 2017-07-14 | 2019-06-28
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR669C | RECONSTRUCTION OF ROMA, HETT, ETC | 1 | DEVELOP SCOPE | 2004-05-21 | 2004-08-18 | 2004-05-21 | 2004-08-18
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR669C | RECONSTRUCTION OF ROMA, HETT, ETC | 2 | PRELIMINARY DESIGN | 2004-08-19 | 2004-12-16 | 2004-08-19 | 2004-12-16
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR669C | RECONSTRUCTION OF ROMA, HETT, ETC | 3 | FINAL DESIGN | 2004-12-17 | 2005-06-14 | 2004-12-17 | 2005-06-14
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR669C | RECONSTRUCTION OF ROMA, HETT, ETC | 4 | BID AWARD AND REGISTER CONTRCT | 2005-06-15 | 2005-09-12 | 2022-03-14 | 2022-06-11
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR669C | RECONSTRUCTION OF ROMA, HETT, ETC | 5 | CONSTRUCTION TO 25% | 2005-09-13 | 2006-01-10 | 2022-06-12 | 2022-06-11
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR669C | RECONSTRUCTION OF ROMA, HETT, ETC | 6 | CONSTRUCTION TO 50% | 2006-01-11 | 2006-05-10 | 2022-06-12 | 2022-06-11
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR669C | RECONSTRUCTION OF ROMA, HETT, ETC | 7 | CONSTRUCTION TO 75% | 2006-05-11 | 2006-09-07 | 2022-06-12 | 2022-06-11
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR669C | RECONSTRUCTION OF ROMA, HETT, ETC | 8 | ORIGINAL EQUIP & FURNISHING | 2006-09-08 | 2006-12-06 | 2022-06-12 | 2022-06-11
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR669C | RECONSTRUCTION OF ROMA, HETT, ETC | 9 | SUBSTANTIAL COMPLETION | 2006-12-07 | 2007-02-04 | 2022-06-12 | 2022-06-11
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR669C | RECONSTRUCTION OF ROMA, HETT, ETC | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2007-02-05 | 2007-03-06 | 2023-11-22 | 2023-12-21
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR890 | WOODROW RD | 1 | DEVELOP SCOPE | 2005-05-21 | 2005-08-18 | 2005-05-21 | 2005-08-18
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR890 | WOODROW RD | 2 | PRELIMINARY DESIGN | 2005-08-19 | 2005-12-16 | 2005-08-19 | 2005-12-16
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR890 | WOODROW RD | 3 | FINAL DESIGN | 2005-12-17 | 2006-06-14 | 2005-12-17 | 2006-06-14
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR890 | WOODROW RD | 4 | BID AWARD AND REGISTER CONTRCT | 2006-06-15 | 2006-09-12 | 2016-03-28 | 2016-06-25
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR890 | WOODROW RD | 5 | CONSTRUCTION TO 25% | 2006-09-13 | 2007-01-10 | 2016-06-26 | 2016-06-25
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR890 | WOODROW RD | 6 | CONSTRUCTION TO 50% | 2007-01-11 | 2007-05-10 | 2016-06-26 | 2016-06-25
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR890 | WOODROW RD | 7 | CONSTRUCTION TO 75% | 2007-05-11 | 2007-09-07 | 2016-06-26 | 2016-06-25
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR890 | WOODROW RD | 8 | ORIGINAL EQUIP & FURNISHING | 2007-09-08 | 2007-12-06 | 2016-06-26 | 2016-06-25
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR890 | WOODROW RD | 9 | SUBSTANTIAL COMPLETION | 2007-12-07 | 2008-02-04 | 2016-06-26 | 2016-06-25
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR890 | WOODROW RD | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-02-05 | 2008-03-05 | 2016-12-27 | 2019-10-06
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR919 | BLOOMINGDALE ROAD: AMBOY ROAD TO ARTHUR KILL ROAD | 1 | DEVELOP SCOPE | 2004-05-21 | 2004-08-18 | 2004-05-21 | 2004-08-18
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR919 | BLOOMINGDALE ROAD: AMBOY ROAD TO ARTHUR KILL ROAD | 2 | PRELIMINARY DESIGN | 2004-08-19 | 2004-12-16 | 2004-08-19 | 2004-12-16
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR919 | BLOOMINGDALE ROAD: AMBOY ROAD TO ARTHUR KILL ROAD | 3 | FINAL DESIGN | 2004-12-17 | 2005-06-14 | 2004-12-17 | 2005-06-14
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR919 | BLOOMINGDALE ROAD: AMBOY ROAD TO ARTHUR KILL ROAD | 4 | BID AWARD AND REGISTER CONTRCT | 2010-03-01 | 2010-06-01 | 2020-03-25 | 2020-06-25
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR919 | BLOOMINGDALE ROAD: AMBOY ROAD TO ARTHUR KILL ROAD | 5 | CONSTRUCTION TO 25% | 2010-06-02 | 2010-06-01 | 2020-06-26 | 2020-06-25
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR919 | BLOOMINGDALE ROAD: AMBOY ROAD TO ARTHUR KILL ROAD | 6 | CONSTRUCTION TO 50% | 2010-06-02 | 2010-06-01 | 2020-06-26 | 2020-06-25
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR919 | BLOOMINGDALE ROAD: AMBOY ROAD TO ARTHUR KILL ROAD | 7 | CONSTRUCTION TO 75% | 2010-06-02 | 2010-06-01 | 2020-06-26 | 2020-06-25
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR919 | BLOOMINGDALE ROAD: AMBOY ROAD TO ARTHUR KILL ROAD | 8 | ORIGINAL EQUIP & FURNISHING | 2010-06-02 | 2010-06-01 | 2020-06-26 | 2020-06-25
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR919 | BLOOMINGDALE ROAD: AMBOY ROAD TO ARTHUR KILL ROAD | 9 | SUBSTANTIAL COMPLETION | 2010-06-02 | 2010-06-01 | 2020-06-26 | 2020-06-25
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR919 | BLOOMINGDALE ROAD: AMBOY ROAD TO ARTHUR KILL ROAD | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2010-06-02 | 2010-07-01 | 2022-01-27 | 2030-08-16
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWRF05R | Dubois Yard Roof | 1 | DEVELOP SCOPE | 2015-06-30 | 2015-10-27 | 2015-06-30 | 2015-10-27
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWRF05R | Dubois Yard Roof | 2 | DESIGN START | 2015-10-28 | 2017-04-19 | 2015-10-28 | 2017-04-19
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWRF05R | Dubois Yard Roof | 3 | CONSTRUCTION START | 2017-04-20 | 2019-04-09 | 2017-04-20 | 2023-05-16
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2013R | PRIOR NOTICE SIDEWALKS - STATEN ISLAND | 1 | DEVELOP SCOPE | 2013-09-23 | 2013-12-21 | 2013-09-23 | 2013-12-21
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2013R | PRIOR NOTICE SIDEWALKS - STATEN ISLAND | 2 | PRELIMINARY DESIGN | 2013-12-22 | 2014-04-20 | 2013-12-22 | 2014-04-20
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2013R | PRIOR NOTICE SIDEWALKS - STATEN ISLAND | 3 | FINAL DESIGN | 2014-04-21 | 2014-10-17 | 2014-04-21 | 2014-10-17
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2013R | PRIOR NOTICE SIDEWALKS - STATEN ISLAND | 4 | BID AWARD AND REGISTER CONTRCT | 2014-10-18 | 2015-01-15 | 2014-10-18 | 2015-01-15
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2013R | PRIOR NOTICE SIDEWALKS - STATEN ISLAND | 5 | CONSTRUCTION TO 25% | 2015-01-16 | 2015-05-15 | 2015-01-16 | 2015-05-15
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2013R | PRIOR NOTICE SIDEWALKS - STATEN ISLAND | 6 | CONSTRUCTION TO 50% | 2015-05-16 | 2015-09-12 | 2015-05-16 | 2015-09-12
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2013R | PRIOR NOTICE SIDEWALKS - STATEN ISLAND | 7 | CONSTRUCTION TO 75% | 2015-09-13 | 2016-01-10 | 2015-09-13 | 2016-01-10
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2013R | PRIOR NOTICE SIDEWALKS - STATEN ISLAND | 8 | ORIGINAL EQUIP & FURNISHING | 2016-01-11 | 2016-04-09 | 2016-01-11 | 2016-04-09
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2013R | PRIOR NOTICE SIDEWALKS - STATEN ISLAND | 9 | SUBSTANTIAL COMPLETION | 2016-04-10 | 2016-06-08 | 2016-04-10 | 2016-06-08
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2013R | PRIOR NOTICE SIDEWALKS - STATEN ISLAND | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-06-09 | 2029-06-30 | 2016-06-09 | 2029-06-30
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020R | Prior Notice Sidewalks- Staten Island | 1 | DEVELOP SCOPE | 2019-06-30 | 2019-09-27 | 2019-06-30 | 2019-09-27
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020R | Prior Notice Sidewalks- Staten Island | 2 | PRELIMINARY DESIGN | 2019-09-28 | 2020-01-25 | 2019-09-28 | 2020-01-25
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020R | Prior Notice Sidewalks- Staten Island | 3 | FINAL DESIGN | 2020-01-26 | 2020-07-23 | 2020-01-26 | 2020-07-23
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020R | Prior Notice Sidewalks- Staten Island | 4 | BID AWARD AND REGISTER CONTRCT | 2020-07-24 | 2020-10-21 | 2020-07-24 | 2020-10-21
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020R | Prior Notice Sidewalks- Staten Island | 5 | CONSTRUCTION TO 25% | 2020-10-22 | 2021-02-18 | 2020-10-22 | 2021-02-18
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020R | Prior Notice Sidewalks- Staten Island | 6 | CONSTRUCTION TO 50% | 2021-02-19 | 2021-06-18 | 2021-02-19 | 2021-06-18
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020R | Prior Notice Sidewalks- Staten Island | 7 | CONSTRUCTION TO 75% | 2021-06-19 | 2021-10-16 | 2021-06-19 | 2021-10-16
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020R | Prior Notice Sidewalks- Staten Island | 8 | ORIGINAL EQUIP & FURNISHING | 2021-10-17 | 2022-01-14 | 2021-10-17 | 2022-01-14
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020R | Prior Notice Sidewalks- Staten Island | 9 | SUBSTANTIAL COMPLETION | 2022-01-15 | 2022-03-15 | 2022-01-15 | 2022-03-15
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020R | Prior Notice Sidewalks- Staten Island | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-16 | 2022-04-14 | 2022-03-16 | 2022-04-14
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020X | Prior Notice Sidewalks- Bronx | 1 | DEVELOP SCOPE | 2019-06-30 | 2019-09-27 | 2019-06-30 | 2019-09-27
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020X | Prior Notice Sidewalks- Bronx | 2 | PRELIMINARY DESIGN | 2019-09-28 | 2020-01-25 | 2019-09-28 | 2020-01-25
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020X | Prior Notice Sidewalks- Bronx | 3 | FINAL DESIGN | 2020-01-26 | 2020-07-23 | 2020-01-26 | 2020-07-23
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020X | Prior Notice Sidewalks- Bronx | 4 | BID AWARD AND REGISTER CONTRCT | 2020-07-24 | 2020-10-21 | 2020-07-24 | 2020-10-21
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020X | Prior Notice Sidewalks- Bronx | 5 | CONSTRUCTION TO 25% | 2020-10-22 | 2021-02-18 | 2020-10-22 | 2021-02-18
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020X | Prior Notice Sidewalks- Bronx | 6 | CONSTRUCTION TO 50% | 2021-02-19 | 2021-06-18 | 2021-02-19 | 2021-06-18
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020X | Prior Notice Sidewalks- Bronx | 7 | CONSTRUCTION TO 75% | 2021-06-19 | 2021-10-16 | 2021-06-19 | 2021-10-16
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020X | Prior Notice Sidewalks- Bronx | 8 | ORIGINAL EQUIP & FURNISHING | 2021-10-17 | 2022-01-14 | 2021-10-17 | 2022-01-14
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020X | Prior Notice Sidewalks- Bronx | 9 | SUBSTANTIAL COMPLETION | 2022-01-15 | 2022-03-15 | 2022-01-15 | 2022-03-15
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020X | Prior Notice Sidewalks- Bronx | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-16 | 2022-04-14 | 2022-03-16 | 2022-04-14
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRR1 | Trench Restoration - Staten Island (SER002333) | 1 | DEVELOP SCOPE | 2020-03-01 | 2020-05-29 | 2020-03-01 | 2020-05-29
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRR1 | Trench Restoration - Staten Island (SER002333) | 2 | PRELIMINARY DESIGN | 2020-05-30 | 2020-09-26 | 2020-05-30 | 2020-09-26
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRR1 | Trench Restoration - Staten Island (SER002333) | 3 | FINAL DESIGN | 2020-09-27 | 2021-03-25 | 2020-09-27 | 2021-03-25
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRR1 | Trench Restoration - Staten Island (SER002333) | 4 | BID AWARD AND REGISTER CONTRCT | 2021-03-26 | 2021-06-23 | 2021-03-26 | 2021-06-23
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRR1 | Trench Restoration - Staten Island (SER002333) | 5 | CONSTRUCTION TO 25% | 2021-06-24 | 2021-10-21 | 2021-06-24 | 2021-10-21
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRR1 | Trench Restoration - Staten Island (SER002333) | 6 | CONSTRUCTION TO 50% | 2021-10-22 | 2022-02-18 | 2021-10-22 | 2022-02-18
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRR1 | Trench Restoration - Staten Island (SER002333) | 7 | CONSTRUCTION TO 75% | 2022-02-19 | 2022-06-18 | 2022-02-19 | 2022-06-18
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRR1 | Trench Restoration - Staten Island (SER002333) | 8 | ORIGINAL EQUIP & FURNISHING | 2022-06-19 | 2022-09-16 | 2022-06-19 | 2022-09-16
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRR1 | Trench Restoration - Staten Island (SER002333) | 9 | SUBSTANTIAL COMPLETION | 2022-09-17 | 2022-11-15 | 2022-09-17 | 2022-11-15
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRR1 | Trench Restoration - Staten Island (SER002333) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-11-16 | 2022-12-15 | 2022-11-16 | 2022-12-15
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCAL15TV | Tottenville: New Roof | 1 | PROJECT START | 2014-12-04 | 2014-12-04 | 2014-12-04 | 2014-12-04
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCAL15TV | Tottenville: New Roof | 2 | DESIGN START | 2014-12-05 | 2014-12-05 | 2014-12-05 | 2014-12-05
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCAL15TV | Tottenville: New Roof | 3 | DESIGN COMPLETION | 2014-12-06 | 2014-12-06 | 2014-12-06 | 2014-12-06
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCAL15TV | Tottenville: New Roof | 4 | CONSTRUCTION START | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCAL15TV | Tottenville: New Roof | 5 | CONSTRUCTION COMPLETION | 2018-06-30 | 2018-06-30 | 2018-06-30 | 2022-06-30
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEA13STG | ST GEORGE: Exterior and Interior renovation | 1 | PROJECT START | 2013-02-04 | 2013-02-04 | 2013-02-04 | 2013-02-04
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEA13STG | ST GEORGE: Exterior and Interior renovation | 2 | DESIGN START | 2015-02-06 | 2015-02-06 | 2015-02-06 | 2015-02-06
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEA13STG | ST GEORGE: Exterior and Interior renovation | 3 | DESIGN COMPLETION | 2015-12-30 | 2015-12-30 | 2015-12-30 | 2015-12-30
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEA13STG | ST GEORGE: Exterior and Interior renovation | 4 | CONSTRUCTION START | 2016-05-14 | 2016-05-14 | 2016-05-14 | 2016-05-14
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEA13STG | ST GEORGE: Exterior and Interior renovation | 5 | CONSTRUCTION COMPLETION | 2017-10-23 | 2017-10-23 | 2020-10-23 | 2020-10-23
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEAL15RT | Richmond town: New Roof | 1 | PROJECT START | 2014-12-09 | 2014-12-09 | 2014-12-09 | 2014-12-09
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEAL15RT | Richmond town: New Roof | 2 | DESIGN START | 2015-06-24 | 2015-06-24 | 2015-06-24 | 2015-06-24
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEAL15RT | Richmond town: New Roof | 3 | DESIGN COMPLETION | 2018-10-17 | 2018-10-17 | 2015-06-24 | 2018-10-17
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEAL15RT | Richmond town: New Roof | 4 | CONSTRUCTION START | 2019-03-18 | 2019-03-18 | 2019-03-18 | 2022-12-25
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEAL15RT | Richmond town: New Roof | 5 | CONSTRUCTION COMPLETION | 2019-12-25 | 2019-12-25 | 2022-12-25 | 2022-12-25
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEM14NDP | New Roof | 2 | DESIGN START | 2015-06-25 | 2015-08-12 | 2015-06-25 | 2015-08-12
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEM14NDP | New Roof | 3 | DESIGN COMPLETION | 2015-08-13 | 2015-08-12 | 2015-08-13 | 2015-08-12
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEM14NDP | New Roof | 4 | CONSTRUCTION START | 2015-08-13 | 2015-08-12 | 2015-08-13 | 2015-08-12
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEM14NDP | New Roof | 5 | CONSTRUCTION COMPLETION | 2016-12-04 | 2017-09-06 | 2021-09-30 | 2021-09-30
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC001 | New Creek West Branch Bluebelt, BMPs NC-7 and NC-8. Low Flow | 1 | DEVELOP SCOPE | 2013-08-19 | 2013-11-16 | 2013-08-19 | 2013-11-16
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC001 | New Creek West Branch Bluebelt, BMPs NC-7 and NC-8. Low Flow | 2 | PRELIMINARY DESIGN | 2013-11-17 | 2014-03-16 | 2013-11-17 | 2014-03-16
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC001 | New Creek West Branch Bluebelt, BMPs NC-7 and NC-8. Low Flow | 3 | FINAL DESIGN | 2014-03-17 | 2014-09-12 | 2014-03-17 | 2014-09-12
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC001 | New Creek West Branch Bluebelt, BMPs NC-7 and NC-8. Low Flow | 4 | BID AWARD AND REGISTER CONTRCT | 2014-09-13 | 2014-12-11 | 2014-09-13 | 2014-12-11
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC001 | New Creek West Branch Bluebelt, BMPs NC-7 and NC-8. Low Flow | 5 | CONSTRUCTION TO 25% | 2014-12-12 | 2015-04-10 | 2014-12-12 | 2015-04-10
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC001 | New Creek West Branch Bluebelt, BMPs NC-7 and NC-8. Low Flow | 6 | CONSTRUCTION TO 50% | 2015-04-11 | 2015-08-08 | 2015-04-11 | 2015-08-08
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC001 | New Creek West Branch Bluebelt, BMPs NC-7 and NC-8. Low Flow | 7 | CONSTRUCTION TO 75% | 2015-08-09 | 2015-12-06 | 2015-08-09 | 2015-12-06
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC001 | New Creek West Branch Bluebelt, BMPs NC-7 and NC-8. Low Flow | 8 | ORIGINAL EQUIP & FURNISHING | 2015-12-07 | 2016-03-05 | 2015-12-07 | 2016-03-05
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC001 | New Creek West Branch Bluebelt, BMPs NC-7 and NC-8. Low Flow | 9 | SUBSTANTIAL COMPLETION | 2016-03-06 | 2016-05-04 | 2016-03-06 | 2016-05-04
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC001 | New Creek West Branch Bluebelt, BMPs NC-7 and NC-8. Low Flow | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-05-05 | 2016-06-03 | 2016-05-05 | 2020-02-01
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC002 | Last Chance Pond BMP NC 11/12, storm & sanitary sewer constr | 1 | DEVELOP SCOPE | 2017-05-07 | 2017-08-04 | 2017-05-07 | 2017-08-04
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC002 | Last Chance Pond BMP NC 11/12, storm & sanitary sewer constr | 2 | PRELIMINARY DESIGN | 2017-08-05 | 2017-12-02 | 2017-08-05 | 2017-12-02
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC002 | Last Chance Pond BMP NC 11/12, storm & sanitary sewer constr | 3 | FINAL DESIGN | 2017-12-03 | 2018-05-31 | 2017-12-03 | 2018-05-31
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC002 | Last Chance Pond BMP NC 11/12, storm & sanitary sewer constr | 4 | BID AWARD AND REGISTER CONTRCT | 2018-06-01 | 2018-08-29 | 2018-06-01 | 2018-08-29
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC002 | Last Chance Pond BMP NC 11/12, storm & sanitary sewer constr | 5 | CONSTRUCTION TO 25% | 2018-08-30 | 2018-12-27 | 2018-08-30 | 2018-12-27
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC002 | Last Chance Pond BMP NC 11/12, storm & sanitary sewer constr | 6 | CONSTRUCTION TO 50% | 2018-12-28 | 2019-04-26 | 2018-12-28 | 2019-04-26
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC002 | Last Chance Pond BMP NC 11/12, storm & sanitary sewer constr | 7 | CONSTRUCTION TO 75% | 2019-04-27 | 2019-08-24 | 2019-04-27 | 2019-08-24
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC002 | Last Chance Pond BMP NC 11/12, storm & sanitary sewer constr | 8 | ORIGINAL EQUIP & FURNISHING | 2019-08-25 | 2019-11-22 | 2019-08-25 | 2019-11-22
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC002 | Last Chance Pond BMP NC 11/12, storm & sanitary sewer constr | 9 | SUBSTANTIAL COMPLETION | 2019-11-23 | 2020-01-21 | 2019-11-23 | 2020-01-21
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC002 | Last Chance Pond BMP NC 11/12, storm & sanitary sewer constr | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-01-22 | 2020-02-20 | 2020-01-22 | 2022-05-27
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC003 | Strm & Sani Swr const & WM replac in Mason Ave, SI | 1 | DEVELOP SCOPE | 2018-06-01 | 2019-02-25 | 2018-06-01 | 2019-02-25
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC003 | Strm & Sani Swr const & WM replac in Mason Ave, SI | 2 | PRELIMINARY DESIGN | 2019-02-26 | 2020-02-20 | 2019-02-26 | 2020-02-20
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC003 | Strm & Sani Swr const & WM replac in Mason Ave, SI | 3 | FINAL DESIGN | 2020-02-21 | 2021-08-13 | 2020-02-21 | 2021-08-13
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC003 | Strm & Sani Swr const & WM replac in Mason Ave, SI | 4 | BID AWARD AND REGISTER CONTRCT | 2021-08-14 | 2022-05-10 | 2021-08-14 | 2022-05-10
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC003 | Strm & Sani Swr const & WM replac in Mason Ave, SI | 5 | CONSTRUCTION TO 25% | 2022-05-11 | 2023-05-05 | 2022-05-11 | 2023-05-05
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC003 | Strm & Sani Swr const & WM replac in Mason Ave, SI | 6 | CONSTRUCTION TO 50% | 2023-05-06 | 2024-04-29 | 2023-05-06 | 2024-04-29
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC003 | Strm & Sani Swr const & WM replac in Mason Ave, SI | 7 | CONSTRUCTION TO 75% | 2024-04-30 | 2025-04-24 | 2024-04-30 | 2025-04-24
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC003 | Strm & Sani Swr const & WM replac in Mason Ave, SI | 8 | ORIGINAL EQUIP & FURNISHING | 2025-04-25 | 2026-01-19 | 2025-04-25 | 2026-01-19
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC003 | Strm & Sani Swr const & WM replac in Mason Ave, SI | 9 | SUBSTANTIAL COMPLETION | 2026-01-20 | 2026-07-18 | 2026-01-20 | 2026-07-18
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC003 | Strm & Sani Swr const & WM replac in Mason Ave, SI | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2026-07-19 | 2026-10-16 | 2026-07-19 | 2026-10-16
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC005 | Storm Sewer Tributary for BMPs NC-13 and NC-14 | 1 | DEVELOP SCOPE | 2019-03-01 | 2019-05-29 | 2019-03-01 | 2019-05-29
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC005 | Storm Sewer Tributary for BMPs NC-13 and NC-14 | 2 | PRELIMINARY DESIGN | 2019-05-30 | 2019-09-26 | 2019-05-30 | 2019-09-26
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC005 | Storm Sewer Tributary for BMPs NC-13 and NC-14 | 3 | FINAL DESIGN | 2019-09-27 | 2020-03-24 | 2019-09-27 | 2020-03-24
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC005 | Storm Sewer Tributary for BMPs NC-13 and NC-14 | 4 | BID AWARD AND REGISTER CONTRCT | 2020-03-25 | 2020-06-22 | 2020-03-25 | 2020-06-22
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC005 | Storm Sewer Tributary for BMPs NC-13 and NC-14 | 5 | CONSTRUCTION TO 25% | 2020-06-23 | 2020-10-20 | 2020-06-23 | 2020-10-20
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC005 | Storm Sewer Tributary for BMPs NC-13 and NC-14 | 6 | CONSTRUCTION TO 50% | 2020-10-21 | 2021-02-17 | 2020-10-21 | 2021-02-17
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC005 | Storm Sewer Tributary for BMPs NC-13 and NC-14 | 7 | CONSTRUCTION TO 75% | 2021-02-18 | 2021-06-17 | 2021-02-18 | 2021-06-17
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC005 | Storm Sewer Tributary for BMPs NC-13 and NC-14 | 8 | ORIGINAL EQUIP & FURNISHING | 2021-06-18 | 2021-09-15 | 2021-06-18 | 2021-09-15
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC005 | Storm Sewer Tributary for BMPs NC-13 and NC-14 | 9 | SUBSTANTIAL COMPLETION | 2021-09-16 | 2021-11-14 | 2021-09-16 | 2021-11-14
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC005 | Storm Sewer Tributary for BMPs NC-13 and NC-14 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-11-15 | 2021-12-14 | 2021-11-15 | 2024-06-30
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC04A | BMP NC 6 and 15 storm & sanitary sewer installation | 1 | DEVELOP SCOPE | 2018-03-01 | 2018-05-29 | 2018-03-01 | 2018-05-29
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC04A | BMP NC 6 and 15 storm & sanitary sewer installation | 2 | PRELIMINARY DESIGN | 2018-05-30 | 2018-09-26 | 2018-05-30 | 2018-09-26
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC04A | BMP NC 6 and 15 storm & sanitary sewer installation | 3 | FINAL DESIGN | 2018-09-27 | 2019-03-25 | 2018-09-27 | 2019-03-25
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC04A | BMP NC 6 and 15 storm & sanitary sewer installation | 4 | BID AWARD AND REGISTER CONTRCT | 2019-03-26 | 2019-06-23 | 2019-03-26 | 2019-06-23
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC04A | BMP NC 6 and 15 storm & sanitary sewer installation | 5 | CONSTRUCTION TO 25% | 2019-06-24 | 2019-10-21 | 2019-06-24 | 2019-10-21
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC04A | BMP NC 6 and 15 storm & sanitary sewer installation | 6 | CONSTRUCTION TO 50% | 2019-10-22 | 2020-02-18 | 2019-10-22 | 2020-02-18
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC04A | BMP NC 6 and 15 storm & sanitary sewer installation | 7 | CONSTRUCTION TO 75% | 2020-02-19 | 2020-06-17 | 2020-02-19 | 2020-06-17
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC04A | BMP NC 6 and 15 storm & sanitary sewer installation | 8 | ORIGINAL EQUIP & FURNISHING | 2020-06-18 | 2020-09-15 | 2020-06-18 | 2020-09-15
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC04A | BMP NC 6 and 15 storm & sanitary sewer installation | 9 | SUBSTANTIAL COMPLETION | 2020-09-16 | 2020-11-14 | 2020-09-16 | 2020-11-14
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC04A | BMP NC 6 and 15 storm & sanitary sewer installation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-11-15 | 2020-12-14 | 2020-11-15 | 2023-11-24
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC04B | Storm and sanitary sewer installation | 1 | DEVELOP SCOPE | 2021-03-01 | 2021-05-29 | 2021-03-01 | 2021-05-29
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC04B | Storm and sanitary sewer installation | 2 | PRELIMINARY DESIGN | 2021-05-30 | 2021-09-26 | 2021-05-30 | 2021-09-26
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC04B | Storm and sanitary sewer installation | 3 | FINAL DESIGN | 2021-09-27 | 2022-03-25 | 2021-09-27 | 2022-03-25
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC04B | Storm and sanitary sewer installation | 4 | BID AWARD AND REGISTER CONTRCT | 2022-03-26 | 2022-06-23 | 2022-03-26 | 2022-06-23
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC04B | Storm and sanitary sewer installation | 5 | CONSTRUCTION TO 25% | 2022-06-24 | 2022-10-21 | 2022-06-24 | 2022-10-21
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC04B | Storm and sanitary sewer installation | 6 | CONSTRUCTION TO 50% | 2022-10-22 | 2023-02-18 | 2022-10-22 | 2023-02-18
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC04B | Storm and sanitary sewer installation | 7 | CONSTRUCTION TO 75% | 2023-02-19 | 2023-06-18 | 2023-02-19 | 2023-06-18
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC04B | Storm and sanitary sewer installation | 8 | ORIGINAL EQUIP & FURNISHING | 2023-06-19 | 2023-09-16 | 2023-06-19 | 2023-09-16
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC04B | Storm and sanitary sewer installation | 9 | SUBSTANTIAL COMPLETION | 2023-09-17 | 2023-11-15 | 2023-09-17 | 2023-11-15
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC04B | Storm and sanitary sewer installation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-11-16 | 2023-12-15 | 2023-11-16 | 2025-06-30
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC05 | Construction of BMPs NC-13 and NC-14 (SANDR01) | 1 | DEVELOP SCOPE | 2017-03-01 | 2017-05-29 | 2017-03-01 | 2017-05-29
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC05 | Construction of BMPs NC-13 and NC-14 (SANDR01) | 2 | PRELIMINARY DESIGN | 2017-05-30 | 2017-09-26 | 2017-05-30 | 2017-09-26
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC05 | Construction of BMPs NC-13 and NC-14 (SANDR01) | 3 | FINAL DESIGN | 2017-09-27 | 2018-03-25 | 2017-09-27 | 2018-03-25
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC05 | Construction of BMPs NC-13 and NC-14 (SANDR01) | 4 | BID AWARD AND REGISTER CONTRCT | 2018-03-26 | 2018-06-23 | 2018-03-26 | 2018-06-23
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC05 | Construction of BMPs NC-13 and NC-14 (SANDR01) | 5 | CONSTRUCTION TO 25% | 2018-06-24 | 2018-10-21 | 2018-06-24 | 2018-10-21
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC05 | Construction of BMPs NC-13 and NC-14 (SANDR01) | 6 | CONSTRUCTION TO 50% | 2018-10-22 | 2019-02-18 | 2018-10-22 | 2019-02-18
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC05 | Construction of BMPs NC-13 and NC-14 (SANDR01) | 7 | CONSTRUCTION TO 75% | 2019-02-19 | 2019-06-18 | 2019-02-19 | 2019-06-18
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC05 | Construction of BMPs NC-13 and NC-14 (SANDR01) | 8 | ORIGINAL EQUIP & FURNISHING | 2019-06-19 | 2019-09-16 | 2019-06-19 | 2019-09-16
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC05 | Construction of BMPs NC-13 and NC-14 (SANDR01) | 9 | SUBSTANTIAL COMPLETION | 2019-09-17 | 2019-11-15 | 2019-09-17 | 2019-11-15
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC05 | Construction of BMPs NC-13 and NC-14 (SANDR01) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-11-16 | 2019-12-15 | 2019-11-16 | 2027-11-27
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | P-5PNYC06 | PlaNYC-Ocean Breeze Athletic Fac-Building Fit-Out R149-108M | 1 | PROJECT START | 2010-10-05 | 2010-10-05 | 2010-07-17 | 2010-07-17
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | P-5PNYC06 | PlaNYC-Ocean Breeze Athletic Fac-Building Fit-Out R149-108M | 2 | DESIGN START | 2010-10-06 | 2010-10-06 | 2010-07-18 | 2010-07-18
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | P-5PNYC06 | PlaNYC-Ocean Breeze Athletic Fac-Building Fit-Out R149-108M | 3 | DESIGN COMPLETION | 2010-10-07 | 2010-10-07 | 2010-07-19 | 2010-10-15
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | P-5PNYC06 | PlaNYC-Ocean Breeze Athletic Fac-Building Fit-Out R149-108M | 4 | CONSTRUCTION START | 2010-10-08 | 2011-01-04 | 2010-10-16 | 2011-01-12
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | P-5PNYC06 | PlaNYC-Ocean Breeze Athletic Fac-Building Fit-Out R149-108M | 5 | CONSTRUCTION COMPLETION | 2011-01-05 | 2015-01-05 | 2011-01-13 | 2024-06-30
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV175AQUA | SIZ - Staten Island Zoo - Aquarium Reconstruction | 1 | DEVELOP SCOPE | 2010-09-13 | 2010-12-11 | 2010-09-13 | 2010-12-11
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV175AQUA | SIZ - Staten Island Zoo - Aquarium Reconstruction | 2 | PRELIMINARY DESIGN | 2010-12-12 | 2011-04-10 | 2010-12-12 | 2011-04-10
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV175AQUA | SIZ - Staten Island Zoo - Aquarium Reconstruction | 3 | FINAL DESIGN | 2011-04-11 | 2011-10-07 | 2011-04-11 | 2011-10-07
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV175AQUA | SIZ - Staten Island Zoo - Aquarium Reconstruction | 4 | BID AWARD AND REGISTER CONTRCT | 2011-10-08 | 2012-01-05 | 2011-10-08 | 2012-01-05
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV175AQUA | SIZ - Staten Island Zoo - Aquarium Reconstruction | 5 | CONSTRUCTION TO 25% | 2012-01-06 | 2012-05-04 | 2012-01-06 | 2012-05-04
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV175AQUA | SIZ - Staten Island Zoo - Aquarium Reconstruction | 6 | CONSTRUCTION TO 50% | 2012-05-05 | 2012-09-01 | 2012-05-05 | 2012-09-01
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV175AQUA | SIZ - Staten Island Zoo - Aquarium Reconstruction | 7 | CONSTRUCTION TO 75% | 2012-09-02 | 2012-12-30 | 2012-09-02 | 2012-12-30
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV175AQUA | SIZ - Staten Island Zoo - Aquarium Reconstruction | 8 | ORIGINAL EQUIP & FURNISHING | 2012-12-31 | 2013-03-30 | 2012-12-31 | 2013-03-30
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV175AQUA | SIZ - Staten Island Zoo - Aquarium Reconstruction | 9 | SUBSTANTIAL COMPLETION | 2013-03-31 | 2013-05-29 | 2014-09-15 | 2016-03-15
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV175AQUA | SIZ - Staten Island Zoo - Aquarium Reconstruction | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-05-30 | 2013-06-28 | 2016-03-16 | 2016-09-09
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV175AQUA | SIZ - Staten Island Zoo - Aquarium Reconstruction | 11 | PROJECT START | 2013-05-30 | 2013-06-28 | 2016-09-10 | 2016-09-10
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV175AQUA | SIZ - Staten Island Zoo - Aquarium Reconstruction | 12 | DESIGN START | 2013-05-30 | 2013-06-28 | 2016-09-11 | 2016-09-11
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV175AQUA | SIZ - Staten Island Zoo - Aquarium Reconstruction | 13 | DESIGN COMPLETION | 2013-05-30 | 2013-06-28 | 2016-09-12 | 2016-09-12
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV175AQUA | SIZ - Staten Island Zoo - Aquarium Reconstruction | 14 | CONSTRUCTION START | 2013-05-30 | 2013-06-28 | 2016-09-13 | 2016-09-13
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV175AQUA | SIZ - Staten Island Zoo - Aquarium Reconstruction | 15 | CONSTRUCTION COMPLETION | 2013-05-30 | 2013-06-28 | 2016-09-14 | 2022-06-28
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV175ROOF | SIZ - Roof Replacement | 1 | DEVELOP SCOPE | 2015-06-01 | 2015-08-29 | 2017-01-02 | 2017-04-01
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV175ROOF | SIZ - Roof Replacement | 2 | PRELIMINARY DESIGN | 2015-08-30 | 2015-12-27 | 2017-04-02 | 2017-07-30
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV175ROOF | SIZ - Roof Replacement | 3 | FINAL DESIGN | 2015-12-28 | 2016-06-24 | 2017-07-31 | 2018-01-26
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV175ROOF | SIZ - Roof Replacement | 4 | BID AWARD AND REGISTER CONTRCT | 2016-06-25 | 2016-09-22 | 2018-01-27 | 2018-04-26
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV175ROOF | SIZ - Roof Replacement | 5 | CONSTRUCTION TO 25% | 2016-09-23 | 2017-01-20 | 2018-04-27 | 2018-08-24
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV175ROOF | SIZ - Roof Replacement | 6 | CONSTRUCTION TO 50% | 2017-01-21 | 2017-05-20 | 2018-08-25 | 2018-12-22
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV175ROOF | SIZ - Roof Replacement | 7 | CONSTRUCTION TO 75% | 2017-05-21 | 2017-09-17 | 2018-12-23 | 2019-04-21
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV175ROOF | SIZ - Roof Replacement | 8 | ORIGINAL EQUIP & FURNISHING | 2017-09-18 | 2017-12-16 | 2019-04-22 | 2019-07-20
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV175ROOF | SIZ - Roof Replacement | 9 | SUBSTANTIAL COMPLETION | 2017-12-17 | 2018-02-14 | 2019-07-21 | 2019-09-18
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV175ROOF | SIZ - Roof Replacement | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-02-15 | 2018-03-16 | 2019-09-19 | 2021-10-18
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV175ROOF | SIZ - Roof Replacement | 11 | PROJECT START | 2018-02-15 | 2018-03-16 | 2021-10-19 | 2021-10-19
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV175ROOF | SIZ - Roof Replacement | 12 | DESIGN START | 2018-02-15 | 2018-03-16 | 2021-10-20 | 2021-10-20
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV175ROOF | SIZ - Roof Replacement | 13 | DESIGN COMPLETION | 2018-02-15 | 2018-03-16 | 2021-10-21 | 2021-10-21
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV175ROOF | SIZ - Roof Replacement | 14 | CONSTRUCTION START | 2018-02-15 | 2018-03-16 | 2021-10-22 | 2021-10-22
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV175ROOF | SIZ - Roof Replacement | 15 | CONSTRUCTION COMPLETION | 2018-02-15 | 2018-03-16 | 2021-10-23 | 2022-10-23
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV302BPH1 | SIIAS - Building B at SHCC Phase1 Geo-Thermal & Ground Floor | 1 | DEVELOP SCOPE | 2015-06-01 | 2015-08-29 | 2015-06-01 | 2015-08-29
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV302BPH1 | SIIAS - Building B at SHCC Phase1 Geo-Thermal & Ground Floor | 2 | PRELIMINARY DESIGN | 2015-08-30 | 2015-12-27 | 2015-08-30 | 2015-12-27
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV302BPH1 | SIIAS - Building B at SHCC Phase1 Geo-Thermal & Ground Floor | 3 | FINAL DESIGN | 2015-12-28 | 2016-06-24 | 2015-12-28 | 2016-06-24
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV302BPH1 | SIIAS - Building B at SHCC Phase1 Geo-Thermal & Ground Floor | 4 | BID AWARD AND REGISTER CONTRCT | 2016-06-25 | 2016-09-22 | 2016-06-25 | 2016-09-22
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV302BPH1 | SIIAS - Building B at SHCC Phase1 Geo-Thermal & Ground Floor | 5 | CONSTRUCTION TO 25% | 2016-09-23 | 2017-01-20 | 2016-09-23 | 2017-01-20
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV302BPH1 | SIIAS - Building B at SHCC Phase1 Geo-Thermal & Ground Floor | 6 | CONSTRUCTION TO 50% | 2017-01-21 | 2017-05-20 | 2017-01-21 | 2017-05-20
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV302BPH1 | SIIAS - Building B at SHCC Phase1 Geo-Thermal & Ground Floor | 7 | CONSTRUCTION TO 75% | 2017-05-21 | 2017-09-17 | 2017-05-21 | 2017-09-17
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV302BPH1 | SIIAS - Building B at SHCC Phase1 Geo-Thermal & Ground Floor | 8 | ORIGINAL EQUIP & FURNISHING | 2017-09-18 | 2017-12-16 | 2017-09-18 | 2017-12-16
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV302BPH1 | SIIAS - Building B at SHCC Phase1 Geo-Thermal & Ground Floor | 9 | SUBSTANTIAL COMPLETION | 2017-12-17 | 2018-02-14 | 2017-12-17 | 2018-02-14
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV302BPH1 | SIIAS - Building B at SHCC Phase1 Geo-Thermal & Ground Floor | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-02-15 | 2018-03-16 | 2018-02-15 | 2021-03-16
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV302BPH1 | SIIAS - Building B at SHCC Phase1 Geo-Thermal & Ground Floor | 11 | PROJECT START | 2018-02-15 | 2018-03-16 | 2021-03-17 | 2021-03-17
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV302BPH1 | SIIAS - Building B at SHCC Phase1 Geo-Thermal & Ground Floor | 12 | DESIGN START | 2018-02-15 | 2018-03-16 | 2021-03-18 | 2021-03-18
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV302BPH1 | SIIAS - Building B at SHCC Phase1 Geo-Thermal & Ground Floor | 13 | DESIGN COMPLETION | 2018-02-15 | 2018-03-16 | 2021-03-19 | 2021-03-19
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV302BPH1 | SIIAS - Building B at SHCC Phase1 Geo-Thermal & Ground Floor | 14 | CONSTRUCTION START | 2018-02-15 | 2018-03-16 | 2021-03-20 | 2021-03-20
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV302BPH1 | SIIAS - Building B at SHCC Phase1 Geo-Thermal & Ground Floor | 15 | CONSTRUCTION COMPLETION | 2018-02-15 | 2018-03-16 | 2023-03-21 | 2023-03-21
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV341BRIT | SIHS - Britton Cottage Restoration | 1 | DEVELOP SCOPE | 2010-08-15 | 2010-11-12 | 2010-08-16 | 2012-02-01
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV341BRIT | SIHS - Britton Cottage Restoration | 2 | PRELIMINARY DESIGN | 2010-11-13 | 2011-03-12 | 2012-02-02 | 2014-04-25
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV341BRIT | SIHS - Britton Cottage Restoration | 3 | FINAL DESIGN | 2011-03-13 | 2011-09-08 | 2014-04-26 | 2014-04-27
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV341BRIT | SIHS - Britton Cottage Restoration | 4 | BID AWARD AND REGISTER CONTRCT | 2011-09-09 | 2011-12-07 | 2014-04-28 | 2016-02-25
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV341BRIT | SIHS - Britton Cottage Restoration | 5 | CONSTRUCTION TO 25% | 2011-12-08 | 2012-04-05 | 2025-02-26 | 2025-02-26
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV341BRIT | SIHS - Britton Cottage Restoration | 6 | CONSTRUCTION TO 50% | 2012-04-06 | 2012-08-03 | 2025-02-26 | 2025-02-26
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV341BRIT | SIHS - Britton Cottage Restoration | 7 | CONSTRUCTION TO 75% | 2012-08-04 | 2012-12-01 | 2025-02-26 | 2025-02-26
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV341BRIT | SIHS - Britton Cottage Restoration | 8 | ORIGINAL EQUIP & FURNISHING | 2012-12-02 | 2013-03-01 | 2025-02-26 | 2025-02-26
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV341BRIT | SIHS - Britton Cottage Restoration | 9 | SUBSTANTIAL COMPLETION | 2013-03-02 | 2013-04-30 | 2025-02-26 | 2025-02-26
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV341BRIT | SIHS - Britton Cottage Restoration | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-05-01 | 2013-05-30 | 2025-02-26 | 2025-02-26
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV477TEMP | SICM -Staten Island Children's Museum Temp Control System | 1 | PROJECT START | 2018-08-24 | 2018-08-25 | 2018-08-24 | 2018-08-25
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV477TEMP | SICM -Staten Island Children's Museum Temp Control System | 2 | DESIGN START | 2018-08-26 | 2019-06-03 | 2018-08-26 | 2019-06-03
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV477TEMP | SICM -Staten Island Children's Museum Temp Control System | 3 | DESIGN COMPLETION | 2020-09-01 | 2020-09-01 | 2020-09-01 | 2020-09-01
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV477TEMP | SICM -Staten Island Children's Museum Temp Control System | 4 | CONSTRUCTION START | 2022-06-01 | 2024-05-29 | 2022-06-01 | 2024-05-29
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV477TEMP | SICM -Staten Island Children's Museum Temp Control System | 5 | CONSTRUCTION COMPLETION | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490-C | SHCC - SHCC Main Hall Bldg C Roof Reconstruction | 1 | DEVELOP SCOPE | 2015-06-15 | 2015-09-12 | 2015-06-15 | 2015-09-12
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490-C | SHCC - SHCC Main Hall Bldg C Roof Reconstruction | 2 | PRELIMINARY DESIGN | 2015-09-13 | 2016-01-10 | 2015-09-13 | 2016-01-10
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490-C | SHCC - SHCC Main Hall Bldg C Roof Reconstruction | 3 | FINAL DESIGN | 2016-01-11 | 2016-07-08 | 2016-01-11 | 2016-07-08
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490-C | SHCC - SHCC Main Hall Bldg C Roof Reconstruction | 4 | BID AWARD AND REGISTER CONTRCT | 2016-07-09 | 2016-10-06 | 2016-07-09 | 2016-10-06
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490-C | SHCC - SHCC Main Hall Bldg C Roof Reconstruction | 5 | CONSTRUCTION TO 25% | 2016-10-07 | 2017-02-03 | 2016-10-07 | 2017-02-03
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490-C | SHCC - SHCC Main Hall Bldg C Roof Reconstruction | 6 | CONSTRUCTION TO 50% | 2017-02-04 | 2017-06-03 | 2017-02-04 | 2017-06-03
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490-C | SHCC - SHCC Main Hall Bldg C Roof Reconstruction | 7 | CONSTRUCTION TO 75% | 2017-06-04 | 2017-10-01 | 2017-06-04 | 2017-10-01
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490-C | SHCC - SHCC Main Hall Bldg C Roof Reconstruction | 8 | ORIGINAL EQUIP & FURNISHING | 2017-10-02 | 2017-12-30 | 2017-10-02 | 2017-12-30
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490-C | SHCC - SHCC Main Hall Bldg C Roof Reconstruction | 9 | SUBSTANTIAL COMPLETION | 2017-12-31 | 2018-02-28 | 2017-12-31 | 2018-02-28
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490-C | SHCC - SHCC Main Hall Bldg C Roof Reconstruction | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-03-01 | 2018-03-30 | 2018-03-01 | 2021-03-30
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490-C | SHCC - SHCC Main Hall Bldg C Roof Reconstruction | 11 | PROJECT START | 2018-03-01 | 2018-03-30 | 2021-03-31 | 2021-03-31
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490-C | SHCC - SHCC Main Hall Bldg C Roof Reconstruction | 12 | DESIGN START | 2018-03-01 | 2018-03-30 | 2021-04-01 | 2021-04-01
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490-C | SHCC - SHCC Main Hall Bldg C Roof Reconstruction | 13 | DESIGN COMPLETION | 2018-03-01 | 2018-03-30 | 2021-04-02 | 2021-04-02
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490-C | SHCC - SHCC Main Hall Bldg C Roof Reconstruction | 14 | CONSTRUCTION START | 2018-03-01 | 2018-03-30 | 2021-04-03 | 2021-04-03
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490-C | SHCC - SHCC Main Hall Bldg C Roof Reconstruction | 15 | CONSTRUCTION COMPLETION | 2018-03-01 | 2018-03-30 | 2021-04-04 | 2024-04-08
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490ELEC | SHCC - Snug Harbor Cult. Ctr. Site - Wide Electrical Upgrade | 1 | DEVELOP SCOPE | 2015-06-15 | 2015-09-12 | 2015-06-15 | 2015-09-12
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490ELEC | SHCC - Snug Harbor Cult. Ctr. Site - Wide Electrical Upgrade | 2 | PRELIMINARY DESIGN | 2015-09-13 | 2016-01-10 | 2015-09-13 | 2016-01-10
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490ELEC | SHCC - Snug Harbor Cult. Ctr. Site - Wide Electrical Upgrade | 3 | FINAL DESIGN | 2016-01-11 | 2016-07-08 | 2016-01-11 | 2016-07-08
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490ELEC | SHCC - Snug Harbor Cult. Ctr. Site - Wide Electrical Upgrade | 4 | BID AWARD AND REGISTER CONTRCT | 2016-07-09 | 2016-10-06 | 2016-07-09 | 2016-10-06
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490ELEC | SHCC - Snug Harbor Cult. Ctr. Site - Wide Electrical Upgrade | 5 | CONSTRUCTION TO 25% | 2016-10-07 | 2017-02-03 | 2016-10-07 | 2017-02-03
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490ELEC | SHCC - Snug Harbor Cult. Ctr. Site - Wide Electrical Upgrade | 6 | CONSTRUCTION TO 50% | 2017-02-04 | 2017-06-03 | 2017-02-04 | 2017-06-03
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490ELEC | SHCC - Snug Harbor Cult. Ctr. Site - Wide Electrical Upgrade | 7 | CONSTRUCTION TO 75% | 2017-06-04 | 2017-10-01 | 2017-06-04 | 2017-10-01
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490ELEC | SHCC - Snug Harbor Cult. Ctr. Site - Wide Electrical Upgrade | 8 | ORIGINAL EQUIP & FURNISHING | 2017-10-02 | 2017-12-30 | 2017-10-02 | 2017-12-30
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490ELEC | SHCC - Snug Harbor Cult. Ctr. Site - Wide Electrical Upgrade | 9 | SUBSTANTIAL COMPLETION | 2017-12-31 | 2018-02-28 | 2017-12-31 | 2018-02-28
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490ELEC | SHCC - Snug Harbor Cult. Ctr. Site - Wide Electrical Upgrade | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-03-01 | 2018-03-30 | 2018-03-01 | 2021-03-30
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490ELEC | SHCC - Snug Harbor Cult. Ctr. Site - Wide Electrical Upgrade | 11 | PROJECT START | 2018-03-01 | 2018-03-30 | 2021-03-31 | 2021-03-31
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490ELEC | SHCC - Snug Harbor Cult. Ctr. Site - Wide Electrical Upgrade | 12 | DESIGN START | 2018-03-01 | 2018-03-30 | 2021-04-01 | 2021-04-01
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490ELEC | SHCC - Snug Harbor Cult. Ctr. Site - Wide Electrical Upgrade | 13 | DESIGN COMPLETION | 2018-03-01 | 2018-03-30 | 2021-04-02 | 2021-04-02
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490ELEC | SHCC - Snug Harbor Cult. Ctr. Site - Wide Electrical Upgrade | 14 | CONSTRUCTION START | 2018-03-01 | 2018-03-30 | 2021-04-03 | 2021-04-03
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490ELEC | SHCC - Snug Harbor Cult. Ctr. Site - Wide Electrical Upgrade | 15 | CONSTRUCTION COMPLETION | 2018-03-01 | 2018-03-30 | 2021-04-04 | 2023-08-10
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490-INF | SHCC - Site-wide Infrastructure Upgrade | 1 | DEVELOP SCOPE | 2016-06-30 | 2016-09-27 | 2016-06-30 | 2016-09-27
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490-INF | SHCC - Site-wide Infrastructure Upgrade | 2 | PRELIMINARY DESIGN | 2016-09-28 | 2017-01-25 | 2016-09-28 | 2017-01-25
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490-INF | SHCC - Site-wide Infrastructure Upgrade | 3 | FINAL DESIGN | 2017-01-26 | 2017-07-24 | 2017-01-26 | 2017-07-24
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490-INF | SHCC - Site-wide Infrastructure Upgrade | 4 | BID AWARD AND REGISTER CONTRCT | 2017-07-25 | 2017-10-22 | 2017-07-25 | 2017-10-22
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490-INF | SHCC - Site-wide Infrastructure Upgrade | 5 | CONSTRUCTION TO 25% | 2017-10-23 | 2018-02-19 | 2017-10-23 | 2018-02-19
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490-INF | SHCC - Site-wide Infrastructure Upgrade | 6 | CONSTRUCTION TO 50% | 2018-02-20 | 2018-06-19 | 2018-02-20 | 2018-06-19
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490-INF | SHCC - Site-wide Infrastructure Upgrade | 7 | CONSTRUCTION TO 75% | 2018-06-20 | 2018-10-17 | 2018-06-20 | 2018-10-17
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490-INF | SHCC - Site-wide Infrastructure Upgrade | 8 | ORIGINAL EQUIP & FURNISHING | 2018-10-18 | 2019-01-15 | 2018-10-18 | 2019-01-15
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490-INF | SHCC - Site-wide Infrastructure Upgrade | 9 | SUBSTANTIAL COMPLETION | 2019-01-16 | 2019-03-16 | 2019-01-16 | 2019-03-16
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490-INF | SHCC - Site-wide Infrastructure Upgrade | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-03-17 | 2019-04-15 | 2019-03-17 | 2019-04-15
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490-INF | SHCC - Site-wide Infrastructure Upgrade | 11 | PROJECT START | 2019-03-17 | 2019-04-15 | 2019-04-16 | 2019-04-16
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490-INF | SHCC - Site-wide Infrastructure Upgrade | 12 | DESIGN START | 2019-03-17 | 2019-04-15 | 2019-04-17 | 2019-04-17
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490-INF | SHCC - Site-wide Infrastructure Upgrade | 13 | DESIGN COMPLETION | 2019-03-17 | 2019-04-15 | 2019-04-18 | 2019-04-18
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490-INF | SHCC - Site-wide Infrastructure Upgrade | 14 | CONSTRUCTION START | 2019-03-17 | 2019-04-15 | 2019-04-19 | 2019-04-19
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490-INF | SHCC - Site-wide Infrastructure Upgrade | 15 | CONSTRUCTION COMPLETION | 2019-03-17 | 2019-04-15 | 2022-04-20 | 2022-07-15
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490-Q3 | SHCC - Snug Harbor Cult. Ctr. Music Hall, Dressing Rooms | 1 | CONSTRUCTION | 2013-04-30 | 2014-04-24 | 2013-01-30 | 2013-04-29
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490-Q3 | SHCC - Snug Harbor Cult. Ctr. Music Hall, Dressing Rooms | 2 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-04-25 | 2015-04-19 | 2013-04-30 | 2014-04-24
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490-Q3 | SHCC - Snug Harbor Cult. Ctr. Music Hall, Dressing Rooms | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-04-25 | 2015-04-19 | 2014-04-25 | 2015-04-19
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490-Q3 | SHCC - Snug Harbor Cult. Ctr. Music Hall, Dressing Rooms | 4 | PROJECT START | 2014-04-25 | 2015-04-19 | 2015-04-20 | 2015-04-20
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490-Q3 | SHCC - Snug Harbor Cult. Ctr. Music Hall, Dressing Rooms | 5 | DESIGN START | 2014-04-25 | 2015-04-19 | 2015-04-21 | 2015-04-21
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490-Q3 | SHCC - Snug Harbor Cult. Ctr. Music Hall, Dressing Rooms | 6 | DESIGN COMPLETION | 2014-04-25 | 2015-04-19 | 2015-04-22 | 2015-04-22
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490-Q3 | SHCC - Snug Harbor Cult. Ctr. Music Hall, Dressing Rooms | 7 | CONSTRUCTION START | 2014-04-25 | 2015-04-19 | 2015-04-23 | 2015-04-23
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490-Q3 | SHCC - Snug Harbor Cult. Ctr. Music Hall, Dressing Rooms | 8 | CONSTRUCTION COMPLETION | 2014-04-25 | 2015-04-19 | 2016-06-30 | 2025-06-30
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PVC341-M | SIHS - SIHS TYSEN COURT RECONSTRUCTION | 1 | PROJECT START | 1995-07-15 | 1995-07-15 | 2008-08-26 | 2008-08-26
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PVC341-M | SIHS - SIHS TYSEN COURT RECONSTRUCTION | 2 | DESIGN START | 1995-07-16 | 1995-07-16 | 2009-10-06 | 2011-01-19
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PVC341-M | SIHS - SIHS TYSEN COURT RECONSTRUCTION | 3 | DESIGN COMPLETION | 2006-12-13 | 2008-07-20 | 2011-01-19 | 2011-01-19
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PVC341-M | SIHS - SIHS TYSEN COURT RECONSTRUCTION | 4 | CONSTRUCTION START | 2008-07-21 | 2009-07-16 | 2011-09-02 | 2013-08-22
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PVC341-M | SIHS - SIHS TYSEN COURT RECONSTRUCTION | 5 | CONSTRUCTION COMPLETION | 2009-07-17 | 2010-06-30 | 2013-08-22 | 2020-08-22
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-74 | FUEL TANK REPLACEMENT | 1 | PROJECT START | 2017-07-01 | 2017-07-01 | 2017-07-01 | 2017-07-01
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-74 | FUEL TANK REPLACEMENT | 2 | DESIGN START | 2017-07-02 | 2017-07-02 | 2017-07-02 | 2017-07-02
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-74 | FUEL TANK REPLACEMENT | 3 | DESIGN COMPLETION | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-74 | FUEL TANK REPLACEMENT | 4 | CONSTRUCTION START | 2017-07-04 | 2017-07-04 | 2017-07-04 | 2017-07-04
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-74 | FUEL TANK REPLACEMENT | 5 | CONSTRUCTION COMPLETION | 2017-07-05 | 2019-07-05 | 2017-07-05 | 2022-06-30
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PWD5SOUTH | SOUTH SHORE LITTLE LEAGUE | 1 | PROJECT START | 2010-07-01 | 2010-07-01 | 2012-06-15 | 2012-06-15
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PWD5SOUTH | SOUTH SHORE LITTLE LEAGUE | 2 | DESIGN START | 2010-07-02 | 2010-07-02 | 2013-06-25 | 2014-06-25
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PWD5SOUTH | SOUTH SHORE LITTLE LEAGUE | 3 | DESIGN COMPLETION | 2010-07-03 | 2010-07-03 | 2014-12-15 | 2016-05-10
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PWD5SOUTH | SOUTH SHORE LITTLE LEAGUE | 4 | CONSTRUCTION START | 2010-07-04 | 2010-07-04 | 2019-05-11 | 2020-05-08
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PWD5SOUTH | SOUTH SHORE LITTLE LEAGUE | 5 | CONSTRUCTION COMPLETION | 2010-07-05 | 2010-07-05 | 2020-07-31 | 2023-08-31
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-366 | WM WORK IN ARTHUR KILL RD BTW RICHMOND & ABINGTON AVES | 1 | DEVELOP SCOPE | 2014-03-05 | 2014-06-02 | 2011-07-02 | 2012-09-29
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-366 | WM WORK IN ARTHUR KILL RD BTW RICHMOND & ABINGTON AVES | 2 | PRELIMINARY DESIGN | 2014-06-03 | 2014-09-30 | 2011-09-30 | 2012-01-27
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-366 | WM WORK IN ARTHUR KILL RD BTW RICHMOND & ABINGTON AVES | 3 | FINAL DESIGN | 2014-10-01 | 2015-03-29 | 2012-01-28 | 2022-03-06
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-366 | WM WORK IN ARTHUR KILL RD BTW RICHMOND & ABINGTON AVES | 4 | BID AWARD AND REGISTER CONTRCT | 2015-03-30 | 2015-06-27 | 2022-03-07 | 2022-06-05
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-366 | WM WORK IN ARTHUR KILL RD BTW RICHMOND & ABINGTON AVES | 5 | CONSTRUCTION TO 25% | 2015-06-28 | 2015-10-25 | 2022-06-06 | 2022-10-18
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-366 | WM WORK IN ARTHUR KILL RD BTW RICHMOND & ABINGTON AVES | 6 | CONSTRUCTION TO 50% | 2015-10-26 | 2016-02-22 | 2022-10-19 | 2023-02-15
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-366 | WM WORK IN ARTHUR KILL RD BTW RICHMOND & ABINGTON AVES | 7 | CONSTRUCTION TO 75% | 2016-02-23 | 2016-06-21 | 2023-02-16 | 2023-03-07
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-366 | WM WORK IN ARTHUR KILL RD BTW RICHMOND & ABINGTON AVES | 8 | ORIGINAL EQUIP & FURNISHING | 2016-06-22 | 2016-09-19 | 2023-03-08 | 2023-07-05
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-366 | WM WORK IN ARTHUR KILL RD BTW RICHMOND & ABINGTON AVES | 9 | SUBSTANTIAL COMPLETION | 2016-09-20 | 2016-11-18 | 2023-07-06 | 2023-11-02
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-366 | WM WORK IN ARTHUR KILL RD BTW RICHMOND & ABINGTON AVES | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-11-19 | 2016-12-18 | 2023-11-02 | 2023-12-01
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-369 | CORE WM AREA CONTRACT, S.I. & BKLYN | 1 | DEVELOP SCOPE | 2011-03-02 | 2011-05-30 | 2011-03-02 | 2011-05-30
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-369 | CORE WM AREA CONTRACT, S.I. & BKLYN | 2 | PRELIMINARY DESIGN | 2011-05-31 | 2011-09-27 | 2011-05-31 | 2011-09-27
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-369 | CORE WM AREA CONTRACT, S.I. & BKLYN | 3 | FINAL DESIGN | 2011-09-28 | 2012-03-25 | 2011-09-28 | 2012-03-25
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-369 | CORE WM AREA CONTRACT, S.I. & BKLYN | 4 | BID AWARD AND REGISTER CONTRCT | 2012-03-26 | 2012-06-23 | 2012-03-26 | 2012-06-23
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-369 | CORE WM AREA CONTRACT, S.I. & BKLYN | 5 | CONSTRUCTION TO 25% | 2012-06-24 | 2012-10-21 | 2012-06-24 | 2012-10-21
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-369 | CORE WM AREA CONTRACT, S.I. & BKLYN | 6 | CONSTRUCTION TO 50% | 2012-10-22 | 2013-02-18 | 2012-10-22 | 2013-02-18
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-369 | CORE WM AREA CONTRACT, S.I. & BKLYN | 7 | CONSTRUCTION TO 75% | 2013-02-19 | 2013-06-18 | 2013-02-19 | 2013-06-18
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-369 | CORE WM AREA CONTRACT, S.I. & BKLYN | 8 | ORIGINAL EQUIP & FURNISHING | 2013-06-19 | 2013-09-16 | 2013-06-19 | 2013-09-16
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-369 | CORE WM AREA CONTRACT, S.I. & BKLYN | 9 | SUBSTANTIAL COMPLETION | 2013-09-17 | 2013-11-15 | 2013-09-17 | 2013-11-15
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-369 | CORE WM AREA CONTRACT, S.I. & BKLYN | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-11-16 | 2013-12-15 | 2013-11-16 | 2022-06-30
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-372 | WM, PART OF RECON TRAVIS AVE FORM PARK DR N TO DRAPER PL | 1 | DEVELOP SCOPE | 2017-03-01 | 2017-05-29 | 2017-03-01 | 2017-05-29
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-372 | WM, PART OF RECON TRAVIS AVE FORM PARK DR N TO DRAPER PL | 2 | PRELIMINARY DESIGN | 2017-05-30 | 2017-09-26 | 2017-05-30 | 2017-09-26
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-372 | WM, PART OF RECON TRAVIS AVE FORM PARK DR N TO DRAPER PL | 3 | FINAL DESIGN | 2017-09-27 | 2018-03-25 | 2017-09-27 | 2018-03-25
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-372 | WM, PART OF RECON TRAVIS AVE FORM PARK DR N TO DRAPER PL | 4 | BID AWARD AND REGISTER CONTRCT | 2018-03-26 | 2018-06-23 | 2018-03-26 | 2018-06-23
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-372 | WM, PART OF RECON TRAVIS AVE FORM PARK DR N TO DRAPER PL | 5 | CONSTRUCTION TO 25% | 2018-06-24 | 2018-10-21 | 2018-06-24 | 2018-10-21
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-372 | WM, PART OF RECON TRAVIS AVE FORM PARK DR N TO DRAPER PL | 6 | CONSTRUCTION TO 50% | 2018-10-22 | 2019-02-18 | 2018-10-22 | 2019-02-18
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-372 | WM, PART OF RECON TRAVIS AVE FORM PARK DR N TO DRAPER PL | 7 | CONSTRUCTION TO 75% | 2019-02-19 | 2019-06-18 | 2019-02-19 | 2019-06-18
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-372 | WM, PART OF RECON TRAVIS AVE FORM PARK DR N TO DRAPER PL | 8 | ORIGINAL EQUIP & FURNISHING | 2019-06-19 | 2019-09-16 | 2019-06-19 | 2019-09-16
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-372 | WM, PART OF RECON TRAVIS AVE FORM PARK DR N TO DRAPER PL | 9 | SUBSTANTIAL COMPLETION | 2019-09-17 | 2019-11-15 | 2019-09-17 | 2019-11-15
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-372 | WM, PART OF RECON TRAVIS AVE FORM PARK DR N TO DRAPER PL | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-11-16 | 2019-12-15 | 2019-11-16 | 2025-01-10
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-376 | Water Main Replacment and/or Lining in Clove Road | 1 | DEVELOP SCOPE | 2016-06-01 | 2017-02-25 | 2016-06-01 | 2017-02-25
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-376 | Water Main Replacment and/or Lining in Clove Road | 2 | PRELIMINARY DESIGN | 2017-02-26 | 2018-02-20 | 2017-02-26 | 2018-02-20
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-376 | Water Main Replacment and/or Lining in Clove Road | 3 | FINAL DESIGN | 2018-02-21 | 2019-08-14 | 2018-02-21 | 2019-08-14
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-376 | Water Main Replacment and/or Lining in Clove Road | 4 | BID AWARD AND REGISTER CONTRCT | 2019-08-15 | 2020-05-10 | 2019-08-15 | 2020-05-10
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-376 | Water Main Replacment and/or Lining in Clove Road | 5 | CONSTRUCTION TO 25% | 2020-05-11 | 2021-05-05 | 2020-05-11 | 2021-05-05
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-376 | Water Main Replacment and/or Lining in Clove Road | 6 | CONSTRUCTION TO 50% | 2021-05-06 | 2022-04-30 | 2021-05-06 | 2022-04-30
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-376 | Water Main Replacment and/or Lining in Clove Road | 7 | CONSTRUCTION TO 75% | 2022-05-01 | 2023-04-25 | 2022-05-01 | 2023-04-25
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-376 | Water Main Replacment and/or Lining in Clove Road | 8 | ORIGINAL EQUIP & FURNISHING | 2023-04-26 | 2024-01-20 | 2023-04-26 | 2024-01-20
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-376 | Water Main Replacment and/or Lining in Clove Road | 9 | SUBSTANTIAL COMPLETION | 2024-01-21 | 2024-07-18 | 2024-01-21 | 2024-07-18
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-376 | Water Main Replacment and/or Lining in Clove Road | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-07-19 | 2024-10-16 | 2024-07-19 | 2024-10-16
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-381 | (SANDHWSI) Storm swr replacement ext. in Harold Avenue | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-08-29 | 2020-06-01 | 2020-08-29
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-381 | (SANDHWSI) Storm swr replacement ext. in Harold Avenue | 2 | PRELIMINARY DESIGN | 2020-08-30 | 2020-12-27 | 2020-08-30 | 2020-12-27
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-381 | (SANDHWSI) Storm swr replacement ext. in Harold Avenue | 3 | FINAL DESIGN | 2020-12-28 | 2021-06-25 | 2020-12-28 | 2021-06-25
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-381 | (SANDHWSI) Storm swr replacement ext. in Harold Avenue | 4 | BID AWARD AND REGISTER CONTRCT | 2021-06-26 | 2021-09-23 | 2021-06-26 | 2021-09-23
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-381 | (SANDHWSI) Storm swr replacement ext. in Harold Avenue | 5 | CONSTRUCTION TO 25% | 2021-09-24 | 2022-01-21 | 2021-09-24 | 2022-01-21
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-381 | (SANDHWSI) Storm swr replacement ext. in Harold Avenue | 6 | CONSTRUCTION TO 50% | 2022-01-22 | 2022-05-21 | 2022-01-22 | 2022-05-21
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-381 | (SANDHWSI) Storm swr replacement ext. in Harold Avenue | 7 | CONSTRUCTION TO 75% | 2022-05-22 | 2022-09-18 | 2022-05-22 | 2022-09-18
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-381 | (SANDHWSI) Storm swr replacement ext. in Harold Avenue | 8 | ORIGINAL EQUIP & FURNISHING | 2022-09-19 | 2022-12-17 | 2022-09-19 | 2022-12-17
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-381 | (SANDHWSI) Storm swr replacement ext. in Harold Avenue | 9 | SUBSTANTIAL COMPLETION | 2022-12-18 | 2023-02-15 | 2022-12-18 | 2023-02-15
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-381 | (SANDHWSI) Storm swr replacement ext. in Harold Avenue | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-02-16 | 2023-03-17 | 2023-02-16 | 2023-03-17
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-386 | Water Main replacement, South & Arlington Aves, SI | 1 | DEVELOP SCOPE | 2020-06-30 | 2020-09-27 | 2020-06-30 | 2020-09-27
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-386 | Water Main replacement, South & Arlington Aves, SI | 2 | PRELIMINARY DESIGN | 2020-09-28 | 2021-01-25 | 2020-09-28 | 2021-01-25
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-386 | Water Main replacement, South & Arlington Aves, SI | 3 | FINAL DESIGN | 2021-01-26 | 2021-07-24 | 2021-01-26 | 2021-07-24
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-386 | Water Main replacement, South & Arlington Aves, SI | 4 | BID AWARD AND REGISTER CONTRCT | 2021-07-25 | 2021-10-22 | 2021-07-25 | 2021-10-22
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-386 | Water Main replacement, South & Arlington Aves, SI | 5 | CONSTRUCTION TO 25% | 2021-10-23 | 2022-02-19 | 2021-10-23 | 2022-02-19
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-386 | Water Main replacement, South & Arlington Aves, SI | 6 | CONSTRUCTION TO 50% | 2022-02-20 | 2022-06-19 | 2022-02-20 | 2022-06-19
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-386 | Water Main replacement, South & Arlington Aves, SI | 7 | CONSTRUCTION TO 75% | 2022-06-20 | 2022-10-17 | 2022-06-20 | 2022-10-17
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-386 | Water Main replacement, South & Arlington Aves, SI | 8 | ORIGINAL EQUIP & FURNISHING | 2022-10-18 | 2023-01-15 | 2022-10-18 | 2023-01-15
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-386 | Water Main replacement, South & Arlington Aves, SI | 9 | SUBSTANTIAL COMPLETION | 2023-01-16 | 2023-03-16 | 2023-01-16 | 2023-03-16
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-386 | Water Main replacement, South & Arlington Aves, SI | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-03-17 | 2023-04-15 | 2023-03-17 | 2023-04-15
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | REDA-002 | Accelerated Distribution WM replcmnt & sewer rehab: S.I. | 1 | DEVELOP SCOPE | 2018-03-01 | 2018-05-29 | 2018-03-01 | 2018-05-29
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | REDA-002 | Accelerated Distribution WM replcmnt & sewer rehab: S.I. | 2 | PRELIMINARY DESIGN | 2018-05-30 | 2018-09-26 | 2018-05-30 | 2018-09-26
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | REDA-002 | Accelerated Distribution WM replcmnt & sewer rehab: S.I. | 3 | FINAL DESIGN | 2018-09-27 | 2019-03-25 | 2018-09-27 | 2019-03-25
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | REDA-002 | Accelerated Distribution WM replcmnt & sewer rehab: S.I. | 4 | BID AWARD AND REGISTER CONTRCT | 2019-03-26 | 2019-06-23 | 2019-03-26 | 2019-06-23
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | REDA-002 | Accelerated Distribution WM replcmnt & sewer rehab: S.I. | 5 | CONSTRUCTION TO 25% | 2019-06-24 | 2019-10-21 | 2019-06-24 | 2019-10-21
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | REDA-002 | Accelerated Distribution WM replcmnt & sewer rehab: S.I. | 6 | CONSTRUCTION TO 50% | 2019-10-22 | 2020-02-18 | 2019-10-22 | 2020-02-18
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | REDA-002 | Accelerated Distribution WM replcmnt & sewer rehab: S.I. | 7 | CONSTRUCTION TO 75% | 2020-02-19 | 2020-06-17 | 2020-02-19 | 2020-06-17
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | REDA-002 | Accelerated Distribution WM replcmnt & sewer rehab: S.I. | 8 | ORIGINAL EQUIP & FURNISHING | 2020-06-18 | 2020-09-15 | 2020-06-18 | 2020-09-15
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | REDA-002 | Accelerated Distribution WM replcmnt & sewer rehab: S.I. | 9 | SUBSTANTIAL COMPLETION | 2020-09-16 | 2020-11-14 | 2020-09-16 | 2020-11-14
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | REDA-002 | Accelerated Distribution WM replcmnt & sewer rehab: S.I. | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-11-15 | 2020-12-14 | 2020-11-15 | 2020-12-14
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | REDA-003 | Accelerated Distribution WM replcmnt & sewer rehab: S.I. | 1 | DEVELOP SCOPE | 2016-03-01 | 2016-05-29 | 2016-03-01 | 2016-05-29
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | REDA-003 | Accelerated Distribution WM replcmnt & sewer rehab: S.I. | 2 | PRELIMINARY DESIGN | 2016-05-30 | 2016-09-26 | 2016-05-30 | 2016-09-26
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | REDA-003 | Accelerated Distribution WM replcmnt & sewer rehab: S.I. | 3 | FINAL DESIGN | 2016-09-27 | 2017-03-25 | 2016-09-27 | 2017-03-25
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | REDA-003 | Accelerated Distribution WM replcmnt & sewer rehab: S.I. | 4 | BID AWARD AND REGISTER CONTRCT | 2017-03-26 | 2017-06-23 | 2017-03-26 | 2017-06-23
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | REDA-003 | Accelerated Distribution WM replcmnt & sewer rehab: S.I. | 5 | CONSTRUCTION TO 25% | 2017-06-24 | 2017-10-21 | 2017-06-24 | 2017-10-21
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | REDA-003 | Accelerated Distribution WM replcmnt & sewer rehab: S.I. | 6 | CONSTRUCTION TO 50% | 2017-10-22 | 2018-02-18 | 2017-10-22 | 2018-02-18
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | REDA-003 | Accelerated Distribution WM replcmnt & sewer rehab: S.I. | 7 | CONSTRUCTION TO 75% | 2018-02-19 | 2018-06-18 | 2018-02-19 | 2018-06-18
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | REDA-003 | Accelerated Distribution WM replcmnt & sewer rehab: S.I. | 8 | ORIGINAL EQUIP & FURNISHING | 2018-06-19 | 2018-09-16 | 2018-06-19 | 2018-09-16
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | REDA-003 | Accelerated Distribution WM replcmnt & sewer rehab: S.I. | 9 | SUBSTANTIAL COMPLETION | 2018-09-17 | 2018-11-15 | 2018-09-17 | 2018-11-15
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | REDA-003 | Accelerated Distribution WM replcmnt & sewer rehab: S.I. | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-11-16 | 2018-12-15 | 2018-11-16 | 2022-06-30
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-367 | Staten Island 1 and 3 Garage Construction + SOLARGR10 | 1 | PROJECT START | 2019-03-01 | 2019-03-01 | 2019-03-01 | 2019-03-01
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-367 | Staten Island 1 and 3 Garage Construction + SOLARGR10 | 2 | DESIGN START | 2019-03-02 | 2019-03-02 | 2019-03-02 | 2019-03-02
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-367 | Staten Island 1 and 3 Garage Construction + SOLARGR10 | 3 | DESIGN COMPLETION | 2019-03-03 | 2019-03-03 | 2019-03-03 | 2019-06-28
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-367 | Staten Island 1 and 3 Garage Construction + SOLARGR10 | 4 | CONSTRUCTION START | 2019-03-04 | 2019-03-04 | 2019-06-29 | 2020-02-28
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-367 | Staten Island 1 and 3 Garage Construction + SOLARGR10 | 5 | CONSTRUCTION COMPLETION | 2019-03-05 | 2019-03-05 | 2020-02-29 | 2022-08-31
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-383S | STATEN ISLAND 3 GARAGE HVAC | 1 | DEVELOP SCOPE | 2007-08-01 | 2008-02-16 | 2007-08-01 | 2008-02-16
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-383S | STATEN ISLAND 3 GARAGE HVAC | 2 | PRELIMINARY DESIGN | 2008-02-17 | 2008-09-03 | 2008-02-17 | 2017-07-14
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-383S | STATEN ISLAND 3 GARAGE HVAC | 3 | FINAL DESIGN | 2008-09-04 | 2009-03-22 | 2017-07-15 | 2019-06-28
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-383S | STATEN ISLAND 3 GARAGE HVAC | 4 | BID AWARD AND REGISTER CONTRCT | 2009-03-23 | 2009-10-08 | 2019-06-29 | 2020-02-03
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-383S | STATEN ISLAND 3 GARAGE HVAC | 5 | CONSTRUCTION TO 25% | 2009-10-09 | 2010-10-08 | 2020-02-04 | 2020-02-03
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-383S | STATEN ISLAND 3 GARAGE HVAC | 6 | CONSTRUCTION TO 50% | 2010-10-09 | 2011-10-08 | 2020-02-04 | 2020-02-03
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-383S | STATEN ISLAND 3 GARAGE HVAC | 7 | CONSTRUCTION TO 75% | 2011-10-09 | 2012-10-07 | 2020-02-04 | 2020-02-03
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-383S | STATEN ISLAND 3 GARAGE HVAC | 8 | SUBSTANTIAL COMPLETION | 2012-10-08 | 2013-10-07 | 2020-02-04 | 2021-02-03
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-383S | STATEN ISLAND 3 GARAGE HVAC | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-10-08 | 2015-09-07 | 2021-02-04 | 2021-08-09
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SAND669C | Reconstruction of Roma,Hett,Etc - Hurricane Sandy | 1 | DEVELOP SCOPE | 2016-02-17 | 2016-05-16 | 2016-02-17 | 2016-05-16
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SAND669C | Reconstruction of Roma,Hett,Etc - Hurricane Sandy | 2 | PRELIMINARY DESIGN | 2016-05-17 | 2016-09-13 | 2016-05-17 | 2016-09-13
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SAND669C | Reconstruction of Roma,Hett,Etc - Hurricane Sandy | 3 | FINAL DESIGN | 2016-09-14 | 2017-03-12 | 2016-09-14 | 2017-03-12
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SAND669C | Reconstruction of Roma,Hett,Etc - Hurricane Sandy | 4 | BID AWARD AND REGISTER CONTRCT | 2017-03-13 | 2017-06-10 | 2017-03-13 | 2017-06-10
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SAND669C | Reconstruction of Roma,Hett,Etc - Hurricane Sandy | 5 | CONSTRUCTION TO 25% | 2017-06-11 | 2017-10-08 | 2017-06-11 | 2017-10-08
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SAND669C | Reconstruction of Roma,Hett,Etc - Hurricane Sandy | 6 | CONSTRUCTION TO 50% | 2017-10-09 | 2018-02-05 | 2017-10-09 | 2018-02-05
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SAND669C | Reconstruction of Roma,Hett,Etc - Hurricane Sandy | 7 | CONSTRUCTION TO 75% | 2018-02-06 | 2018-06-05 | 2018-02-06 | 2018-06-05
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SAND669C | Reconstruction of Roma,Hett,Etc - Hurricane Sandy | 8 | ORIGINAL EQUIP & FURNISHING | 2018-06-06 | 2018-09-03 | 2018-06-06 | 2018-09-03
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SAND669C | Reconstruction of Roma,Hett,Etc - Hurricane Sandy | 9 | SUBSTANTIAL COMPLETION | 2018-09-04 | 2018-11-02 | 2018-09-04 | 2018-11-02
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SAND669C | Reconstruction of Roma,Hett,Etc - Hurricane Sandy | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-11-03 | 2018-12-02 | 2018-11-03 | 2024-06-30
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW14 | Reconstruction of South Beach - Hurricane Sandy - RED-375 | 1 | DEVELOP SCOPE | 2016-02-16 | 2016-05-15 | 2016-02-16 | 2016-05-15
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW14 | Reconstruction of South Beach - Hurricane Sandy - RED-375 | 2 | PRELIMINARY DESIGN | 2016-05-16 | 2016-09-12 | 2016-05-16 | 2016-09-12
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW14 | Reconstruction of South Beach - Hurricane Sandy - RED-375 | 3 | FINAL DESIGN | 2016-09-13 | 2017-03-11 | 2016-09-13 | 2017-03-11
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW14 | Reconstruction of South Beach - Hurricane Sandy - RED-375 | 4 | BID AWARD AND REGISTER CONTRCT | 2017-03-12 | 2017-06-09 | 2017-03-12 | 2017-06-09
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW14 | Reconstruction of South Beach - Hurricane Sandy - RED-375 | 5 | CONSTRUCTION TO 25% | 2017-06-10 | 2017-10-07 | 2017-06-10 | 2017-10-07
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW14 | Reconstruction of South Beach - Hurricane Sandy - RED-375 | 6 | CONSTRUCTION TO 50% | 2017-10-08 | 2018-02-04 | 2017-10-08 | 2018-02-04
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW14 | Reconstruction of South Beach - Hurricane Sandy - RED-375 | 7 | CONSTRUCTION TO 75% | 2018-02-05 | 2018-06-04 | 2018-02-05 | 2018-06-04
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW14 | Reconstruction of South Beach - Hurricane Sandy - RED-375 | 8 | ORIGINAL EQUIP & FURNISHING | 2018-06-05 | 2018-09-02 | 2018-06-05 | 2018-09-02
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW14 | Reconstruction of South Beach - Hurricane Sandy - RED-375 | 9 | SUBSTANTIAL COMPLETION | 2018-09-03 | 2018-11-01 | 2018-09-03 | 2018-11-01
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW14 | Reconstruction of South Beach - Hurricane Sandy - RED-375 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-11-02 | 2018-12-01 | 2018-11-02 | 2023-06-30
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW15 | Reconstruction of Midland Beach - Hurricane Sandy | 1 | DEVELOP SCOPE | 2016-02-16 | 2016-05-15 | 2016-02-16 | 2016-05-15
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW15 | Reconstruction of Midland Beach - Hurricane Sandy | 2 | PRELIMINARY DESIGN | 2016-05-16 | 2016-09-12 | 2016-05-16 | 2016-09-12
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW15 | Reconstruction of Midland Beach - Hurricane Sandy | 3 | FINAL DESIGN | 2016-09-13 | 2017-03-11 | 2016-09-13 | 2017-03-11
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW15 | Reconstruction of Midland Beach - Hurricane Sandy | 4 | BID AWARD AND REGISTER CONTRCT | 2017-03-12 | 2017-06-09 | 2017-03-12 | 2017-06-09
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW15 | Reconstruction of Midland Beach - Hurricane Sandy | 5 | CONSTRUCTION TO 25% | 2017-06-10 | 2017-10-07 | 2017-06-10 | 2017-10-07
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW15 | Reconstruction of Midland Beach - Hurricane Sandy | 6 | CONSTRUCTION TO 50% | 2017-10-08 | 2018-02-04 | 2017-10-08 | 2018-02-04
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW15 | Reconstruction of Midland Beach - Hurricane Sandy | 7 | CONSTRUCTION TO 75% | 2018-02-05 | 2018-06-04 | 2018-02-05 | 2018-06-04
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW15 | Reconstruction of Midland Beach - Hurricane Sandy | 8 | ORIGINAL EQUIP & FURNISHING | 2018-06-05 | 2018-09-02 | 2018-06-05 | 2018-09-02
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW15 | Reconstruction of Midland Beach - Hurricane Sandy | 9 | SUBSTANTIAL COMPLETION | 2018-09-03 | 2018-11-01 | 2018-09-03 | 2018-11-01
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW15 | Reconstruction of Midland Beach - Hurricane Sandy | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-11-02 | 2018-12-01 | 2018-11-02 | 2022-08-23
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHWSI | Non When & Where - Staten Island - Hurricane Sandy | 1 | DEVELOP SCOPE | 2015-10-10 | 2016-01-07 | 2015-10-10 | 2016-01-07
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHWSI | Non When & Where - Staten Island - Hurricane Sandy | 2 | PRELIMINARY DESIGN | 2016-01-08 | 2016-05-06 | 2016-01-08 | 2016-05-06
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHWSI | Non When & Where - Staten Island - Hurricane Sandy | 3 | FINAL DESIGN | 2016-05-07 | 2016-11-02 | 2016-05-07 | 2016-11-02
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHWSI | Non When & Where - Staten Island - Hurricane Sandy | 4 | BID AWARD AND REGISTER CONTRCT | 2016-11-03 | 2017-01-31 | 2016-11-03 | 2017-01-31
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHWSI | Non When & Where - Staten Island - Hurricane Sandy | 5 | CONSTRUCTION TO 25% | 2017-02-01 | 2017-05-31 | 2017-02-01 | 2017-05-31
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHWSI | Non When & Where - Staten Island - Hurricane Sandy | 6 | CONSTRUCTION TO 50% | 2017-06-01 | 2017-09-28 | 2017-06-01 | 2017-09-28
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHWSI | Non When & Where - Staten Island - Hurricane Sandy | 7 | CONSTRUCTION TO 75% | 2017-09-29 | 2018-01-26 | 2017-09-29 | 2018-01-26
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHWSI | Non When & Where - Staten Island - Hurricane Sandy | 8 | ORIGINAL EQUIP & FURNISHING | 2018-01-27 | 2018-04-26 | 2018-01-27 | 2018-04-26
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHWSI | Non When & Where - Staten Island - Hurricane Sandy | 9 | SUBSTANTIAL COMPLETION | 2018-04-27 | 2018-06-25 | 2018-04-27 | 2018-06-25
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHWSI | Non When & Where - Staten Island - Hurricane Sandy | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-06-26 | 2018-07-25 | 2018-06-26 | 2021-02-08
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR01 | Hylan Blvd Streetscape Improvements (MIBBNC05) | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-09-28 | 2016-07-01 | 2016-09-28
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR01 | Hylan Blvd Streetscape Improvements (MIBBNC05) | 2 | PRELIMINARY DESIGN | 2016-09-29 | 2017-01-26 | 2016-09-29 | 2017-01-26
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR01 | Hylan Blvd Streetscape Improvements (MIBBNC05) | 3 | FINAL DESIGN | 2017-01-27 | 2017-07-25 | 2017-01-27 | 2017-07-25
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR01 | Hylan Blvd Streetscape Improvements (MIBBNC05) | 4 | BID AWARD AND REGISTER CONTRCT | 2017-07-26 | 2017-10-23 | 2017-07-26 | 2017-10-23
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR01 | Hylan Blvd Streetscape Improvements (MIBBNC05) | 5 | CONSTRUCTION TO 25% | 2017-10-24 | 2018-02-20 | 2017-10-24 | 2018-02-20
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR01 | Hylan Blvd Streetscape Improvements (MIBBNC05) | 6 | CONSTRUCTION TO 50% | 2018-02-21 | 2018-06-20 | 2018-02-21 | 2018-06-20
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR01 | Hylan Blvd Streetscape Improvements (MIBBNC05) | 7 | CONSTRUCTION TO 75% | 2018-06-21 | 2018-10-18 | 2018-06-21 | 2018-10-18
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR01 | Hylan Blvd Streetscape Improvements (MIBBNC05) | 8 | ORIGINAL EQUIP & FURNISHING | 2018-10-19 | 2019-01-16 | 2018-10-19 | 2019-01-16
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR01 | Hylan Blvd Streetscape Improvements (MIBBNC05) | 9 | SUBSTANTIAL COMPLETION | 2019-01-17 | 2019-03-17 | 2019-01-17 | 2019-03-17
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR01 | Hylan Blvd Streetscape Improvements (MIBBNC05) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-03-18 | 2019-04-16 | 2019-03-18 | 2023-06-16
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-734 | SE-734 SAN SEWER IN RICHARD AVE, SI | 1 | DEVELOP SCOPE | 2006-04-14 | 2006-07-12 | 2006-04-14 | 2006-07-12
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-734 | SE-734 SAN SEWER IN RICHARD AVE, SI | 2 | PRELIMINARY DESIGN | 2006-07-13 | 2006-11-09 | 2006-07-13 | 2006-11-09
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-734 | SE-734 SAN SEWER IN RICHARD AVE, SI | 3 | FINAL DESIGN | 2006-11-10 | 2007-05-08 | 2006-11-10 | 2007-05-08
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-734 | SE-734 SAN SEWER IN RICHARD AVE, SI | 4 | BID AWARD AND REGISTER CONTRCT | 2009-04-09 | 2009-06-30 | 2012-03-28 | 2012-06-18
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-734 | SE-734 SAN SEWER IN RICHARD AVE, SI | 5 | CONSTRUCTION TO 25% | 2009-07-01 | 2009-06-30 | 2012-06-19 | 2012-06-18
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-734 | SE-734 SAN SEWER IN RICHARD AVE, SI | 6 | CONSTRUCTION TO 50% | 2009-07-01 | 2009-06-30 | 2012-06-19 | 2012-06-18
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-734 | SE-734 SAN SEWER IN RICHARD AVE, SI | 7 | CONSTRUCTION TO 75% | 2009-07-01 | 2009-06-30 | 2012-06-19 | 2012-06-18
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-734 | SE-734 SAN SEWER IN RICHARD AVE, SI | 8 | ORIGINAL EQUIP & FURNISHING | 2009-07-01 | 2009-06-30 | 2012-06-19 | 2012-06-18
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-734 | SE-734 SAN SEWER IN RICHARD AVE, SI | 9 | SUBSTANTIAL COMPLETION | 2009-07-01 | 2009-06-30 | 2012-06-19 | 2012-06-18
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-734 | SE-734 SAN SEWER IN RICHARD AVE, SI | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2009-07-01 | 2009-07-30 | 2013-11-19 | 2021-12-19
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-740B | SANITARY SEWERS IN ROCKLAND AVENUE | 1 | DEVELOP SCOPE | 2009-03-21 | 2009-06-18 | 2004-06-13 | 2004-09-10
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-740B | SANITARY SEWERS IN ROCKLAND AVENUE | 2 | PRELIMINARY DESIGN | 2009-06-19 | 2009-10-16 | 2004-09-11 | 2005-03-09
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-740B | SANITARY SEWERS IN ROCKLAND AVENUE | 3 | FINAL DESIGN | 2009-10-17 | 2010-04-14 | 2005-03-10 | 2017-03-08
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-740B | SANITARY SEWERS IN ROCKLAND AVENUE | 4 | BID AWARD AND REGISTER CONTRCT | 2010-04-15 | 2010-07-13 | 2017-03-09 | 2017-06-06
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-740B | SANITARY SEWERS IN ROCKLAND AVENUE | 5 | CONSTRUCTION TO 25% | 2010-07-14 | 2010-11-10 | 2017-06-07 | 2017-10-04
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-740B | SANITARY SEWERS IN ROCKLAND AVENUE | 6 | CONSTRUCTION TO 50% | 2010-11-11 | 2011-03-10 | 2017-10-05 | 2018-10-04
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-740B | SANITARY SEWERS IN ROCKLAND AVENUE | 7 | CONSTRUCTION TO 75% | 2011-03-11 | 2011-07-08 | 2018-10-05 | 2019-02-01
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-740B | SANITARY SEWERS IN ROCKLAND AVENUE | 8 | ORIGINAL EQUIP & FURNISHING | 2011-07-09 | 2011-10-06 | 2019-02-02 | 2019-03-03
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-740B | SANITARY SEWERS IN ROCKLAND AVENUE | 9 | SUBSTANTIAL COMPLETION | 2011-10-07 | 2011-12-05 | 2019-03-04 | 2019-08-30
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-740B | SANITARY SEWERS IN ROCKLAND AVENUE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2011-12-06 | 2012-01-04 | 2019-08-31 | 2028-09-14
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-751 | CHESTER AV - IRVINGTON ST AND ARBUTUS AVE | 1 | DEVELOP SCOPE | 2004-02-21 | 2004-05-20 | 2004-02-21 | 2004-05-20
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-751 | CHESTER AV - IRVINGTON ST AND ARBUTUS AVE | 2 | PRELIMINARY DESIGN | 2004-05-21 | 2004-09-17 | 2004-05-21 | 2016-08-27
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-751 | CHESTER AV - IRVINGTON ST AND ARBUTUS AVE | 3 | FINAL DESIGN | 2004-09-18 | 2005-03-16 | 2015-08-28 | 2016-02-23
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-751 | CHESTER AV - IRVINGTON ST AND ARBUTUS AVE | 4 | BID AWARD AND REGISTER CONTRCT | 2005-03-17 | 2005-06-14 | 2016-02-24 | 2016-06-01
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-751 | CHESTER AV - IRVINGTON ST AND ARBUTUS AVE | 5 | CONSTRUCTION TO 25% | 2005-06-15 | 2005-10-12 | 2016-06-02 | 2016-09-29
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-751 | CHESTER AV - IRVINGTON ST AND ARBUTUS AVE | 6 | CONSTRUCTION TO 50% | 2005-10-13 | 2006-02-09 | 2016-09-30 | 2017-01-27
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-751 | CHESTER AV - IRVINGTON ST AND ARBUTUS AVE | 7 | CONSTRUCTION TO 75% | 2006-02-10 | 2006-06-09 | 2017-01-28 | 2017-05-27
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-751 | CHESTER AV - IRVINGTON ST AND ARBUTUS AVE | 8 | ORIGINAL EQUIP & FURNISHING | 2006-06-10 | 2006-09-07 | 2017-01-28 | 2017-04-27
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-751 | CHESTER AV - IRVINGTON ST AND ARBUTUS AVE | 9 | SUBSTANTIAL COMPLETION | 2006-09-08 | 2006-11-06 | 2017-04-28 | 2017-06-26
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-751 | CHESTER AV - IRVINGTON ST AND ARBUTUS AVE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2006-11-07 | 2006-12-06 | 2017-06-27 | 2023-06-28
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-796 | SANITARY SEWER IN RICHMOND VALLEY ROAD | 1 | DEVELOP SCOPE | 2009-03-01 | 2009-05-29 | 2010-07-01 | 2010-09-28
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-796 | SANITARY SEWER IN RICHMOND VALLEY ROAD | 2 | PRELIMINARY DESIGN | 2009-05-30 | 2009-09-26 | 2010-09-29 | 2011-01-26
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-796 | SANITARY SEWER IN RICHMOND VALLEY ROAD | 3 | FINAL DESIGN | 2009-09-27 | 2010-03-25 | 2011-01-27 | 2011-12-02
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-796 | SANITARY SEWER IN RICHMOND VALLEY ROAD | 4 | BID AWARD AND REGISTER CONTRCT | 2010-03-26 | 2010-06-23 | 2011-12-03 | 2012-03-01
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-796 | SANITARY SEWER IN RICHMOND VALLEY ROAD | 5 | CONSTRUCTION TO 25% | 2010-06-24 | 2010-10-21 | 2012-03-02 | 2013-03-01
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-796 | SANITARY SEWER IN RICHMOND VALLEY ROAD | 6 | CONSTRUCTION TO 50% | 2010-10-22 | 2011-02-18 | 2013-03-02 | 2014-03-01
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-796 | SANITARY SEWER IN RICHMOND VALLEY ROAD | 7 | CONSTRUCTION TO 75% | 2011-02-19 | 2011-06-18 | 2014-03-02 | 2015-06-01
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-796 | SANITARY SEWER IN RICHMOND VALLEY ROAD | 8 | ORIGINAL EQUIP & FURNISHING | 2011-06-19 | 2011-09-16 | 2015-06-02 | 2015-08-30
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-796 | SANITARY SEWER IN RICHMOND VALLEY ROAD | 9 | SUBSTANTIAL COMPLETION | 2011-09-17 | 2011-11-15 | 2015-08-31 | 2015-10-29
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-796 | SANITARY SEWER IN RICHMOND VALLEY ROAD | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2011-11-16 | 2011-12-15 | 2015-10-30 | 2022-06-30
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-803 | SAN & STRM SEWER IN RAMBLE ROAD B/T ADRIENNE PL & DENT ROAD | 1 | DEVELOP SCOPE | 2011-06-30 | 2012-03-25 | 2011-06-30 | 2012-03-25
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-803 | SAN & STRM SEWER IN RAMBLE ROAD B/T ADRIENNE PL & DENT ROAD | 2 | PRELIMINARY DESIGN | 2012-03-26 | 2013-03-20 | 2012-03-26 | 2013-03-20
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-803 | SAN & STRM SEWER IN RAMBLE ROAD B/T ADRIENNE PL & DENT ROAD | 3 | FINAL DESIGN | 2013-03-21 | 2014-09-11 | 2013-03-21 | 2014-09-11
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-803 | SAN & STRM SEWER IN RAMBLE ROAD B/T ADRIENNE PL & DENT ROAD | 4 | BID AWARD AND REGISTER CONTRCT | 2014-09-12 | 2015-06-08 | 2014-09-12 | 2015-06-08
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-803 | SAN & STRM SEWER IN RAMBLE ROAD B/T ADRIENNE PL & DENT ROAD | 5 | CONSTRUCTION TO 25% | 2015-06-09 | 2016-06-02 | 2015-06-09 | 2016-06-02
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-803 | SAN & STRM SEWER IN RAMBLE ROAD B/T ADRIENNE PL & DENT ROAD | 6 | CONSTRUCTION TO 50% | 2016-06-03 | 2017-05-28 | 2016-06-03 | 2017-05-28
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-803 | SAN & STRM SEWER IN RAMBLE ROAD B/T ADRIENNE PL & DENT ROAD | 7 | CONSTRUCTION TO 75% | 2017-05-29 | 2018-05-23 | 2017-05-29 | 2018-05-23
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-803 | SAN & STRM SEWER IN RAMBLE ROAD B/T ADRIENNE PL & DENT ROAD | 8 | ORIGINAL EQUIP & FURNISHING | 2018-05-24 | 2019-02-17 | 2018-05-24 | 2019-02-17
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-803 | SAN & STRM SEWER IN RAMBLE ROAD B/T ADRIENNE PL & DENT ROAD | 9 | SUBSTANTIAL COMPLETION | 2019-02-18 | 2019-08-16 | 2019-02-18 | 2019-08-16
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-803 | SAN & STRM SEWER IN RAMBLE ROAD B/T ADRIENNE PL & DENT ROAD | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-08-17 | 2019-11-14 | 2019-08-17 | 2021-06-30
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-812 | Sanitary & Storm swr in Page Av b/t Amboy Rd & Estella Pl | 1 | DEVELOP SCOPE | 2009-06-30 | 2010-03-26 | 2016-03-01 | 2016-05-29
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-812 | Sanitary & Storm swr in Page Av b/t Amboy Rd & Estella Pl | 2 | PRELIMINARY DESIGN | 2010-03-27 | 2011-03-21 | 2016-05-30 | 2016-09-26
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-812 | Sanitary & Storm swr in Page Av b/t Amboy Rd & Estella Pl | 3 | FINAL DESIGN | 2011-03-22 | 2012-09-11 | 2016-09-27 | 2017-03-25
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-812 | Sanitary & Storm swr in Page Av b/t Amboy Rd & Estella Pl | 4 | BID AWARD AND REGISTER CONTRCT | 2012-09-12 | 2013-06-08 | 2017-03-26 | 2017-06-23
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-812 | Sanitary & Storm swr in Page Av b/t Amboy Rd & Estella Pl | 5 | CONSTRUCTION TO 25% | 2013-06-09 | 2014-06-03 | 2017-06-24 | 2018-02-18
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-812 | Sanitary & Storm swr in Page Av b/t Amboy Rd & Estella Pl | 6 | CONSTRUCTION TO 50% | 2014-06-04 | 2015-05-29 | 2018-02-19 | 2018-10-16
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-812 | Sanitary & Storm swr in Page Av b/t Amboy Rd & Estella Pl | 7 | CONSTRUCTION TO 75% | 2015-05-30 | 2016-05-23 | 2018-10-17 | 2019-06-13
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-812 | Sanitary & Storm swr in Page Av b/t Amboy Rd & Estella Pl | 8 | ORIGINAL EQUIP & FURNISHING | 2016-05-24 | 2017-02-17 | 2019-06-14 | 2019-09-11
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-812 | Sanitary & Storm swr in Page Av b/t Amboy Rd & Estella Pl | 9 | SUBSTANTIAL COMPLETION | 2017-02-18 | 2017-08-16 | 2019-09-12 | 2019-11-10
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-812 | Sanitary & Storm swr in Page Av b/t Amboy Rd & Estella Pl | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-08-17 | 2017-11-14 | 2019-11-11 | 2023-12-15
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-846 | New Storm & Sanitary Sewers Snug Harbor area, SI | 1 | DEVELOP SCOPE | 2018-03-01 | 2018-05-29 | 2018-03-01 | 2018-05-29
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-846 | New Storm & Sanitary Sewers Snug Harbor area, SI | 2 | PRELIMINARY DESIGN | 2018-05-30 | 2018-09-26 | 2018-05-30 | 2018-09-26
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-846 | New Storm & Sanitary Sewers Snug Harbor area, SI | 3 | FINAL DESIGN | 2018-09-27 | 2019-03-25 | 2018-09-27 | 2019-03-25
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-846 | New Storm & Sanitary Sewers Snug Harbor area, SI | 4 | BID AWARD AND REGISTER CONTRCT | 2019-03-26 | 2019-06-23 | 2019-03-26 | 2019-06-23
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-846 | New Storm & Sanitary Sewers Snug Harbor area, SI | 5 | CONSTRUCTION TO 25% | 2019-06-24 | 2019-10-21 | 2019-06-24 | 2019-10-21
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-846 | New Storm & Sanitary Sewers Snug Harbor area, SI | 6 | CONSTRUCTION TO 50% | 2019-10-22 | 2020-02-18 | 2019-10-22 | 2020-02-18
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-846 | New Storm & Sanitary Sewers Snug Harbor area, SI | 7 | CONSTRUCTION TO 75% | 2020-02-19 | 2020-06-17 | 2020-02-19 | 2020-06-17
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-846 | New Storm & Sanitary Sewers Snug Harbor area, SI | 8 | ORIGINAL EQUIP & FURNISHING | 2020-06-18 | 2020-09-15 | 2020-06-18 | 2020-09-15
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-846 | New Storm & Sanitary Sewers Snug Harbor area, SI | 9 | SUBSTANTIAL COMPLETION | 2020-09-16 | 2020-11-14 | 2020-09-16 | 2020-11-14
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-846 | New Storm & Sanitary Sewers Snug Harbor area, SI | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-11-15 | 2020-12-14 | 2020-11-15 | 2026-08-20
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002237 | Sanitary and Storm Sewer in Manee Avenue | 1 | DEVELOP SCOPE | 2013-02-14 | 2013-11-10 | 2013-02-14 | 2013-11-10
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002237 | Sanitary and Storm Sewer in Manee Avenue | 2 | PRELIMINARY DESIGN | 2013-11-11 | 2014-11-05 | 2013-11-11 | 2014-11-05
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002237 | Sanitary and Storm Sewer in Manee Avenue | 3 | FINAL DESIGN | 2014-11-06 | 2016-04-28 | 2014-11-06 | 2016-04-28
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002237 | Sanitary and Storm Sewer in Manee Avenue | 4 | BID AWARD AND REGISTER CONTRCT | 2016-04-29 | 2017-01-23 | 2016-04-29 | 2017-01-23
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002237 | Sanitary and Storm Sewer in Manee Avenue | 5 | CONSTRUCTION TO 25% | 2017-01-24 | 2018-01-18 | 2017-01-24 | 2018-01-18
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002237 | Sanitary and Storm Sewer in Manee Avenue | 6 | CONSTRUCTION TO 50% | 2018-01-19 | 2019-01-13 | 2018-01-19 | 2019-01-13
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002237 | Sanitary and Storm Sewer in Manee Avenue | 7 | CONSTRUCTION TO 75% | 2019-01-14 | 2020-01-08 | 2019-01-14 | 2020-01-08
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002237 | Sanitary and Storm Sewer in Manee Avenue | 8 | ORIGINAL EQUIP & FURNISHING | 2020-01-09 | 2020-10-04 | 2020-01-09 | 2020-10-04
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002237 | Sanitary and Storm Sewer in Manee Avenue | 9 | SUBSTANTIAL COMPLETION | 2020-10-05 | 2021-04-02 | 2020-10-05 | 2021-04-02
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002237 | Sanitary and Storm Sewer in Manee Avenue | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-04-03 | 2021-07-01 | 2021-04-03 | 2026-06-30
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002274 | SAN SWR IN TWOMBLEY, HOPKINS, CEBRA, AVENUE | 1 | DEVELOP SCOPE | 2014-02-16 | 2014-05-16 | 2014-02-16 | 2014-05-16
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002274 | SAN SWR IN TWOMBLEY, HOPKINS, CEBRA, AVENUE | 2 | PRELIMINARY DESIGN | 2014-05-17 | 2014-09-13 | 2014-05-17 | 2014-09-13
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002274 | SAN SWR IN TWOMBLEY, HOPKINS, CEBRA, AVENUE | 3 | FINAL DESIGN | 2014-09-14 | 2015-03-12 | 2014-09-14 | 2015-03-12
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002274 | SAN SWR IN TWOMBLEY, HOPKINS, CEBRA, AVENUE | 4 | BID AWARD AND REGISTER CONTRCT | 2015-03-13 | 2015-06-10 | 2015-03-13 | 2015-06-10
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002274 | SAN SWR IN TWOMBLEY, HOPKINS, CEBRA, AVENUE | 5 | CONSTRUCTION TO 25% | 2015-06-11 | 2015-10-08 | 2015-06-11 | 2015-10-08
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002274 | SAN SWR IN TWOMBLEY, HOPKINS, CEBRA, AVENUE | 6 | CONSTRUCTION TO 50% | 2015-10-09 | 2016-02-05 | 2015-10-09 | 2016-02-05
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002274 | SAN SWR IN TWOMBLEY, HOPKINS, CEBRA, AVENUE | 7 | CONSTRUCTION TO 75% | 2016-02-06 | 2016-06-04 | 2016-02-06 | 2016-06-04
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002274 | SAN SWR IN TWOMBLEY, HOPKINS, CEBRA, AVENUE | 8 | ORIGINAL EQUIP & FURNISHING | 2016-06-05 | 2016-09-02 | 2016-06-05 | 2016-09-02
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002274 | SAN SWR IN TWOMBLEY, HOPKINS, CEBRA, AVENUE | 9 | SUBSTANTIAL COMPLETION | 2016-09-03 | 2016-11-01 | 2016-09-03 | 2016-11-01
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002274 | SAN SWR IN TWOMBLEY, HOPKINS, CEBRA, AVENUE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-11-02 | 2016-12-01 | 2016-11-02 | 2020-12-01
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002311 | SAN & STRM SWR IN BERTRAM AV B/T ZEPHYR AV & HYLAN BLVD. ETC | 1 | DEVELOP SCOPE | 2012-06-30 | 2012-09-27 | 2011-06-18 | 2011-09-15
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002311 | SAN & STRM SWR IN BERTRAM AV B/T ZEPHYR AV & HYLAN BLVD. ETC | 2 | PRELIMINARY DESIGN | 2012-09-28 | 2013-01-25 | 2011-09-16 | 2012-01-13
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002311 | SAN & STRM SWR IN BERTRAM AV B/T ZEPHYR AV & HYLAN BLVD. ETC | 3 | FINAL DESIGN | 2013-01-26 | 2013-07-24 | 2012-01-14 | 2013-08-18
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002311 | SAN & STRM SWR IN BERTRAM AV B/T ZEPHYR AV & HYLAN BLVD. ETC | 4 | BID AWARD AND REGISTER CONTRCT | 2013-07-25 | 2013-10-22 | 2013-08-19 | 2013-11-16
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002311 | SAN & STRM SWR IN BERTRAM AV B/T ZEPHYR AV & HYLAN BLVD. ETC | 5 | CONSTRUCTION TO 25% | 2013-10-23 | 2014-02-19 | 2013-11-17 | 2014-05-15
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002311 | SAN & STRM SWR IN BERTRAM AV B/T ZEPHYR AV & HYLAN BLVD. ETC | 6 | CONSTRUCTION TO 50% | 2014-02-20 | 2014-06-19 | 2014-05-16 | 2014-11-11
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002311 | SAN & STRM SWR IN BERTRAM AV B/T ZEPHYR AV & HYLAN BLVD. ETC | 7 | CONSTRUCTION TO 75% | 2014-06-20 | 2014-10-17 | 2014-11-12 | 2015-05-10
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002311 | SAN & STRM SWR IN BERTRAM AV B/T ZEPHYR AV & HYLAN BLVD. ETC | 8 | ORIGINAL EQUIP & FURNISHING | 2014-10-18 | 2015-01-15 | 2015-05-11 | 2015-08-08
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002311 | SAN & STRM SWR IN BERTRAM AV B/T ZEPHYR AV & HYLAN BLVD. ETC | 9 | SUBSTANTIAL COMPLETION | 2015-01-16 | 2015-03-16 | 2015-08-09 | 2016-08-07
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002311 | SAN & STRM SWR IN BERTRAM AV B/T ZEPHYR AV & HYLAN BLVD. ETC | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-17 | 2015-04-15 | 2016-08-08 | 2020-10-06
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002317 | SAN & STRM SEWER IN HALPIN AVE | 1 | DEVELOP SCOPE | 2012-06-30 | 2012-09-27 | 2010-06-30 | 2010-09-27
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002317 | SAN & STRM SEWER IN HALPIN AVE | 2 | PRELIMINARY DESIGN | 2012-09-28 | 2013-01-25 | 2010-09-28 | 2011-01-25
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002317 | SAN & STRM SEWER IN HALPIN AVE | 3 | FINAL DESIGN | 2013-01-26 | 2013-07-24 | 2011-01-26 | 2011-07-24
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002317 | SAN & STRM SEWER IN HALPIN AVE | 4 | BID AWARD AND REGISTER CONTRCT | 2013-07-25 | 2013-10-22 | 2014-03-18 | 2014-06-15
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002317 | SAN & STRM SEWER IN HALPIN AVE | 5 | CONSTRUCTION TO 25% | 2013-10-23 | 2014-02-19 | 2014-06-16 | 2014-06-15
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002317 | SAN & STRM SEWER IN HALPIN AVE | 6 | CONSTRUCTION TO 50% | 2014-02-20 | 2014-06-19 | 2014-06-16 | 2014-06-15
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002317 | SAN & STRM SEWER IN HALPIN AVE | 7 | CONSTRUCTION TO 75% | 2014-06-20 | 2014-10-17 | 2014-06-16 | 2014-06-15
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002317 | SAN & STRM SEWER IN HALPIN AVE | 8 | ORIGINAL EQUIP & FURNISHING | 2014-10-18 | 2015-01-15 | 2014-06-16 | 2014-06-15
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002317 | SAN & STRM SEWER IN HALPIN AVE | 9 | SUBSTANTIAL COMPLETION | 2015-01-16 | 2015-03-16 | 2014-06-16 | 2014-06-15
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002317 | SAN & STRM SEWER IN HALPIN AVE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-17 | 2015-04-15 | 2014-06-16 | 2022-07-30
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002320 | SAN & STRM SWR IN DAHLIA ST B/T ROSEDALE AV & DEAD END ETC | 1 | DEVELOP SCOPE | 2010-03-02 | 2010-05-30 | 2010-03-02 | 2010-05-30
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002320 | SAN & STRM SWR IN DAHLIA ST B/T ROSEDALE AV & DEAD END ETC | 2 | PRELIMINARY DESIGN | 2010-05-31 | 2010-09-27 | 2010-05-31 | 2010-09-27
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002320 | SAN & STRM SWR IN DAHLIA ST B/T ROSEDALE AV & DEAD END ETC | 3 | FINAL DESIGN | 2010-09-28 | 2011-03-26 | 2010-09-28 | 2011-03-26
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002320 | SAN & STRM SWR IN DAHLIA ST B/T ROSEDALE AV & DEAD END ETC | 4 | BID AWARD AND REGISTER CONTRCT | 2011-03-27 | 2011-06-24 | 2011-03-27 | 2011-06-24
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002320 | SAN & STRM SWR IN DAHLIA ST B/T ROSEDALE AV & DEAD END ETC | 5 | CONSTRUCTION TO 25% | 2011-06-25 | 2011-10-22 | 2011-06-25 | 2011-10-22
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002320 | SAN & STRM SWR IN DAHLIA ST B/T ROSEDALE AV & DEAD END ETC | 6 | CONSTRUCTION TO 50% | 2011-10-23 | 2012-02-19 | 2011-10-23 | 2012-02-19
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002320 | SAN & STRM SWR IN DAHLIA ST B/T ROSEDALE AV & DEAD END ETC | 7 | CONSTRUCTION TO 75% | 2012-02-20 | 2012-06-18 | 2012-02-20 | 2012-06-18
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002320 | SAN & STRM SWR IN DAHLIA ST B/T ROSEDALE AV & DEAD END ETC | 8 | ORIGINAL EQUIP & FURNISHING | 2012-06-19 | 2012-09-16 | 2012-06-19 | 2012-09-16
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002320 | SAN & STRM SWR IN DAHLIA ST B/T ROSEDALE AV & DEAD END ETC | 9 | SUBSTANTIAL COMPLETION | 2012-09-17 | 2012-11-15 | 2012-09-17 | 2012-11-15
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002320 | SAN & STRM SWR IN DAHLIA ST B/T ROSEDALE AV & DEAD END ETC | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-11-16 | 2012-12-15 | 2012-11-16 | 2024-06-30
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002323 | SAN & STRM SWRS: WALKER ST, ETC. | 1 | DEVELOP SCOPE | 2014-06-30 | 2015-03-26 | 2014-06-30 | 2015-03-26
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002323 | SAN & STRM SWRS: WALKER ST, ETC. | 2 | PRELIMINARY DESIGN | 2015-03-27 | 2016-03-20 | 2015-03-27 | 2016-03-20
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002323 | SAN & STRM SWRS: WALKER ST, ETC. | 3 | FINAL DESIGN | 2016-03-21 | 2017-09-11 | 2016-03-21 | 2017-09-11
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002323 | SAN & STRM SWRS: WALKER ST, ETC. | 4 | BID AWARD AND REGISTER CONTRCT | 2017-09-12 | 2018-06-08 | 2017-09-12 | 2018-06-08
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002323 | SAN & STRM SWRS: WALKER ST, ETC. | 5 | CONSTRUCTION TO 25% | 2018-06-09 | 2019-06-03 | 2018-06-09 | 2019-06-03
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002323 | SAN & STRM SWRS: WALKER ST, ETC. | 6 | CONSTRUCTION TO 50% | 2019-06-04 | 2020-05-28 | 2019-06-04 | 2020-05-28
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002323 | SAN & STRM SWRS: WALKER ST, ETC. | 7 | CONSTRUCTION TO 75% | 2020-05-29 | 2021-05-23 | 2020-05-29 | 2021-05-23
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002323 | SAN & STRM SWRS: WALKER ST, ETC. | 8 | ORIGINAL EQUIP & FURNISHING | 2021-05-24 | 2022-02-17 | 2021-05-24 | 2022-02-17
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002323 | SAN & STRM SWRS: WALKER ST, ETC. | 9 | SUBSTANTIAL COMPLETION | 2022-02-18 | 2022-08-16 | 2022-02-18 | 2022-08-16
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002323 | SAN & STRM SWRS: WALKER ST, ETC. | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-08-17 | 2022-11-14 | 2022-08-17 | 2022-11-14
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002324 | New sanitary sewers in Camden ave. Staten Island | 1 | DEVELOP SCOPE | 2010-08-03 | 2011-04-29 | 2010-08-03 | 2011-04-29
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002324 | New sanitary sewers in Camden ave. Staten Island | 2 | PRELIMINARY DESIGN | 2011-04-30 | 2012-04-23 | 2011-04-30 | 2012-04-23
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002324 | New sanitary sewers in Camden ave. Staten Island | 3 | FINAL DESIGN | 2012-04-24 | 2013-10-15 | 2012-04-24 | 2013-10-15
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002324 | New sanitary sewers in Camden ave. Staten Island | 4 | BID AWARD AND REGISTER CONTRCT | 2013-10-16 | 2014-07-12 | 2013-10-16 | 2014-07-12
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002324 | New sanitary sewers in Camden ave. Staten Island | 5 | CONSTRUCTION TO 25% | 2014-07-13 | 2015-07-07 | 2014-07-13 | 2015-07-07
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002324 | New sanitary sewers in Camden ave. Staten Island | 6 | CONSTRUCTION TO 50% | 2015-07-08 | 2016-07-01 | 2015-07-08 | 2016-07-01
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002324 | New sanitary sewers in Camden ave. Staten Island | 7 | CONSTRUCTION TO 75% | 2016-07-02 | 2017-06-26 | 2016-07-02 | 2017-06-26
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002324 | New sanitary sewers in Camden ave. Staten Island | 8 | ORIGINAL EQUIP & FURNISHING | 2017-06-27 | 2018-03-23 | 2017-06-27 | 2018-03-23
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002324 | New sanitary sewers in Camden ave. Staten Island | 9 | SUBSTANTIAL COMPLETION | 2018-03-24 | 2018-09-19 | 2018-03-24 | 2018-09-19
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002324 | New sanitary sewers in Camden ave. Staten Island | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-09-20 | 2018-12-18 | 2018-09-20 | 2024-06-30
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002326 | Storm and Sanitary Sewers in Wardwell Ave. S.I. | 1 | DEVELOP SCOPE | 2015-02-16 | 2015-05-16 | 2015-02-16 | 2015-05-16
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002326 | Storm and Sanitary Sewers in Wardwell Ave. S.I. | 2 | PRELIMINARY DESIGN | 2015-05-17 | 2015-09-13 | 2015-05-17 | 2015-09-13
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002326 | Storm and Sanitary Sewers in Wardwell Ave. S.I. | 3 | FINAL DESIGN | 2015-09-14 | 2016-03-11 | 2015-09-14 | 2016-03-11
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002326 | Storm and Sanitary Sewers in Wardwell Ave. S.I. | 4 | BID AWARD AND REGISTER CONTRCT | 2016-03-12 | 2016-06-09 | 2016-03-12 | 2016-06-09
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002326 | Storm and Sanitary Sewers in Wardwell Ave. S.I. | 5 | CONSTRUCTION TO 25% | 2016-06-10 | 2016-10-07 | 2016-06-10 | 2016-10-07
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002326 | Storm and Sanitary Sewers in Wardwell Ave. S.I. | 6 | CONSTRUCTION TO 50% | 2016-10-08 | 2017-02-04 | 2016-10-08 | 2017-02-04
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002326 | Storm and Sanitary Sewers in Wardwell Ave. S.I. | 7 | CONSTRUCTION TO 75% | 2017-02-05 | 2017-06-04 | 2017-02-05 | 2017-06-04
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002326 | Storm and Sanitary Sewers in Wardwell Ave. S.I. | 8 | ORIGINAL EQUIP & FURNISHING | 2017-06-05 | 2017-09-02 | 2017-06-05 | 2017-09-02
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002326 | Storm and Sanitary Sewers in Wardwell Ave. S.I. | 9 | SUBSTANTIAL COMPLETION | 2017-09-03 | 2017-11-01 | 2017-09-03 | 2017-11-01
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002326 | Storm and Sanitary Sewers in Wardwell Ave. S.I. | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-11-02 | 2017-12-01 | 2017-11-02 | 2020-12-01
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002329 | SAN, STM & WM IN LANDMARK COLONY | 1 | DEVELOP SCOPE | 2017-03-01 | 2017-05-29 | 2017-03-01 | 2017-05-29
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002329 | SAN, STM & WM IN LANDMARK COLONY | 2 | PRELIMINARY DESIGN | 2017-05-30 | 2017-09-26 | 2017-05-30 | 2017-09-26
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002329 | SAN, STM & WM IN LANDMARK COLONY | 3 | FINAL DESIGN | 2017-09-27 | 2018-03-25 | 2017-09-27 | 2018-03-25
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002329 | SAN, STM & WM IN LANDMARK COLONY | 4 | BID AWARD AND REGISTER CONTRCT | 2018-03-26 | 2018-06-23 | 2018-03-26 | 2018-06-23
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002329 | SAN, STM & WM IN LANDMARK COLONY | 5 | CONSTRUCTION TO 25% | 2018-06-24 | 2018-10-21 | 2018-06-24 | 2018-10-21
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002329 | SAN, STM & WM IN LANDMARK COLONY | 6 | CONSTRUCTION TO 50% | 2018-10-22 | 2019-02-18 | 2018-10-22 | 2019-02-18
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002329 | SAN, STM & WM IN LANDMARK COLONY | 7 | CONSTRUCTION TO 75% | 2019-02-19 | 2019-06-18 | 2019-02-19 | 2019-06-18
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002329 | SAN, STM & WM IN LANDMARK COLONY | 8 | ORIGINAL EQUIP & FURNISHING | 2019-06-19 | 2019-09-16 | 2019-06-19 | 2019-09-16
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002329 | SAN, STM & WM IN LANDMARK COLONY | 9 | SUBSTANTIAL COMPLETION | 2019-09-17 | 2019-11-15 | 2019-09-17 | 2019-11-15
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002329 | SAN, STM & WM IN LANDMARK COLONY | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-11-16 | 2021-12-15 | 2019-11-16 | 2021-12-15
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200100 | STORM SEWER EXT IN AMSTERDAM AVE | 3 | FINAL DESIGN | 2012-09-24 | 2013-03-22 | 2012-09-24 | 2013-03-22
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200100 | STORM SEWER EXT IN AMSTERDAM AVE | 4 | BID AWARD AND REGISTER CONTRCT | 2013-03-23 | 2013-06-20 | 2013-03-23 | 2013-06-20
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200100 | STORM SEWER EXT IN AMSTERDAM AVE | 5 | CONSTRUCTION TO 25% | 2013-06-21 | 2013-10-18 | 2013-06-21 | 2013-10-18
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200100 | STORM SEWER EXT IN AMSTERDAM AVE | 6 | CONSTRUCTION TO 50% | 2013-10-19 | 2014-02-15 | 2013-10-19 | 2014-02-15
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200100 | STORM SEWER EXT IN AMSTERDAM AVE | 7 | CONSTRUCTION TO 75% | 2014-02-16 | 2014-06-15 | 2014-02-16 | 2014-06-15
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200100 | STORM SEWER EXT IN AMSTERDAM AVE | 8 | ORIGINAL EQUIP & FURNISHING | 2014-06-16 | 2014-09-13 | 2014-06-16 | 2014-09-13
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200100 | STORM SEWER EXT IN AMSTERDAM AVE | 9 | SUBSTANTIAL COMPLETION | 2014-09-14 | 2014-11-12 | 2014-09-14 | 2014-11-12
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200100 | STORM SEWER EXT IN AMSTERDAM AVE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-11-13 | 2014-12-12 | 2014-11-13 | 2019-06-30
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200127 | STORM SEWER IN ROCKLAND AV - RICHMOND RD AND MEISNER AV | 1 | DEVELOP SCOPE | 2005-02-21 | 2005-05-21 | 2005-02-21 | 2005-05-21
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200127 | STORM SEWER IN ROCKLAND AV - RICHMOND RD AND MEISNER AV | 2 | PRELIMINARY DESIGN | 2005-05-22 | 2005-09-18 | 2005-05-22 | 2005-09-18
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200127 | STORM SEWER IN ROCKLAND AV - RICHMOND RD AND MEISNER AV | 3 | FINAL DESIGN | 2005-09-19 | 2006-03-17 | 2005-09-19 | 2006-03-17
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200127 | STORM SEWER IN ROCKLAND AV - RICHMOND RD AND MEISNER AV | 4 | BID AWARD AND REGISTER CONTRCT | 2006-03-18 | 2006-06-15 | 2022-03-10 | 2022-06-07
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200127 | STORM SEWER IN ROCKLAND AV - RICHMOND RD AND MEISNER AV | 5 | CONSTRUCTION TO 25% | 2006-06-16 | 2006-10-13 | 2022-06-08 | 2022-06-07
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200127 | STORM SEWER IN ROCKLAND AV - RICHMOND RD AND MEISNER AV | 6 | CONSTRUCTION TO 50% | 2006-10-14 | 2007-02-10 | 2022-06-08 | 2022-06-07
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200127 | STORM SEWER IN ROCKLAND AV - RICHMOND RD AND MEISNER AV | 7 | CONSTRUCTION TO 75% | 2007-02-11 | 2007-06-10 | 2022-06-08 | 2022-06-07
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200127 | STORM SEWER IN ROCKLAND AV - RICHMOND RD AND MEISNER AV | 8 | ORIGINAL EQUIP & FURNISHING | 2007-06-11 | 2007-09-08 | 2022-06-08 | 2022-06-07
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200127 | STORM SEWER IN ROCKLAND AV - RICHMOND RD AND MEISNER AV | 9 | SUBSTANTIAL COMPLETION | 2007-09-09 | 2007-11-07 | 2022-06-08 | 2022-06-07
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200127 | STORM SEWER IN ROCKLAND AV - RICHMOND RD AND MEISNER AV | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2007-11-08 | 2007-12-07 | 2023-11-29 | 2025-06-30
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200128 | STORM SEWER (BMP) IN ROCKLAND AV - RICHMOND RD & MEISNER AV | 1 | DEVELOP SCOPE | 2009-03-01 | 2009-05-29 | 2009-03-01 | 2009-05-29
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200128 | STORM SEWER (BMP) IN ROCKLAND AV - RICHMOND RD & MEISNER AV | 2 | PRELIMINARY DESIGN | 2009-05-30 | 2009-09-26 | 2009-05-30 | 2009-09-26
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200128 | STORM SEWER (BMP) IN ROCKLAND AV - RICHMOND RD & MEISNER AV | 3 | FINAL DESIGN | 2009-09-27 | 2010-03-25 | 2009-09-27 | 2010-03-25
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200128 | STORM SEWER (BMP) IN ROCKLAND AV - RICHMOND RD & MEISNER AV | 4 | BID AWARD AND REGISTER CONTRCT | 2010-03-26 | 2010-06-23 | 2022-03-18 | 2022-06-15
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200128 | STORM SEWER (BMP) IN ROCKLAND AV - RICHMOND RD & MEISNER AV | 5 | CONSTRUCTION TO 25% | 2010-06-24 | 2010-10-21 | 2022-06-16 | 2022-06-15
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200128 | STORM SEWER (BMP) IN ROCKLAND AV - RICHMOND RD & MEISNER AV | 6 | CONSTRUCTION TO 50% | 2010-10-22 | 2011-02-18 | 2022-06-16 | 2022-06-15
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200128 | STORM SEWER (BMP) IN ROCKLAND AV - RICHMOND RD & MEISNER AV | 7 | CONSTRUCTION TO 75% | 2011-02-19 | 2011-06-18 | 2022-06-16 | 2022-06-15
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200128 | STORM SEWER (BMP) IN ROCKLAND AV - RICHMOND RD & MEISNER AV | 8 | ORIGINAL EQUIP & FURNISHING | 2011-06-19 | 2011-09-16 | 2022-06-16 | 2022-06-15
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200128 | STORM SEWER (BMP) IN ROCKLAND AV - RICHMOND RD & MEISNER AV | 9 | SUBSTANTIAL COMPLETION | 2011-09-17 | 2011-11-15 | 2022-06-16 | 2022-06-15
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200128 | STORM SEWER (BMP) IN ROCKLAND AV - RICHMOND RD & MEISNER AV | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2011-11-16 | 2011-12-15 | 2023-12-17 | 2024-01-15
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200151 | Stm & Sani swr ext. & WM replacement Amboy Rd, SI | 1 | DEVELOP SCOPE | 2018-06-15 | 2019-03-11 | 2018-06-15 | 2019-03-11
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200151 | Stm & Sani swr ext. & WM replacement Amboy Rd, SI | 2 | PRELIMINARY DESIGN | 2019-03-12 | 2020-03-05 | 2019-03-12 | 2020-03-05
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200151 | Stm & Sani swr ext. & WM replacement Amboy Rd, SI | 3 | FINAL DESIGN | 2020-03-06 | 2021-08-27 | 2020-03-06 | 2021-08-27
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200151 | Stm & Sani swr ext. & WM replacement Amboy Rd, SI | 4 | BID AWARD AND REGISTER CONTRCT | 2021-08-28 | 2022-05-24 | 2021-08-28 | 2022-05-24
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200151 | Stm & Sani swr ext. & WM replacement Amboy Rd, SI | 5 | CONSTRUCTION TO 25% | 2022-05-25 | 2023-05-19 | 2022-05-25 | 2023-05-19
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200151 | Stm & Sani swr ext. & WM replacement Amboy Rd, SI | 6 | CONSTRUCTION TO 50% | 2023-05-20 | 2024-05-13 | 2023-05-20 | 2024-05-13
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200151 | Stm & Sani swr ext. & WM replacement Amboy Rd, SI | 7 | CONSTRUCTION TO 75% | 2024-05-14 | 2025-05-08 | 2024-05-14 | 2025-05-08
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200151 | Stm & Sani swr ext. & WM replacement Amboy Rd, SI | 8 | ORIGINAL EQUIP & FURNISHING | 2025-05-09 | 2026-02-02 | 2025-05-09 | 2026-02-02
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200151 | Stm & Sani swr ext. & WM replacement Amboy Rd, SI | 9 | SUBSTANTIAL COMPLETION | 2026-02-03 | 2026-08-01 | 2026-02-03 | 2026-08-01
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200151 | Stm & Sani swr ext. & WM replacement Amboy Rd, SI | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2026-08-02 | 2026-10-30 | 2026-08-02 | 2026-10-30
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200153 | STORM SEWER IN FOREST HILL RD - TRAVIS AV & ROCKLAND AV | 1 | DEVELOP SCOPE | 2007-03-02 | 2007-05-30 | 2007-03-02 | 2007-05-30
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200153 | STORM SEWER IN FOREST HILL RD - TRAVIS AV & ROCKLAND AV | 2 | PRELIMINARY DESIGN | 2007-05-31 | 2007-09-27 | 2007-05-31 | 2007-09-27
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200153 | STORM SEWER IN FOREST HILL RD - TRAVIS AV & ROCKLAND AV | 3 | FINAL DESIGN | 2007-09-28 | 2008-03-25 | 2007-09-28 | 2008-03-25
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200153 | STORM SEWER IN FOREST HILL RD - TRAVIS AV & ROCKLAND AV | 4 | BID AWARD AND REGISTER CONTRCT | 2008-03-26 | 2008-06-23 | 2022-03-28 | 2022-06-25
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200153 | STORM SEWER IN FOREST HILL RD - TRAVIS AV & ROCKLAND AV | 5 | CONSTRUCTION TO 25% | 2008-06-24 | 2008-10-21 | 2022-06-26 | 2022-06-25
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200153 | STORM SEWER IN FOREST HILL RD - TRAVIS AV & ROCKLAND AV | 6 | CONSTRUCTION TO 50% | 2008-10-22 | 2009-02-18 | 2022-06-26 | 2022-06-25
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200153 | STORM SEWER IN FOREST HILL RD - TRAVIS AV & ROCKLAND AV | 7 | CONSTRUCTION TO 75% | 2009-02-19 | 2009-06-18 | 2022-06-26 | 2022-06-25
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200153 | STORM SEWER IN FOREST HILL RD - TRAVIS AV & ROCKLAND AV | 8 | ORIGINAL EQUIP & FURNISHING | 2009-06-19 | 2009-09-16 | 2022-06-26 | 2022-06-25
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200153 | STORM SEWER IN FOREST HILL RD - TRAVIS AV & ROCKLAND AV | 9 | SUBSTANTIAL COMPLETION | 2009-09-17 | 2009-11-15 | 2022-06-26 | 2022-06-25
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200153 | STORM SEWER IN FOREST HILL RD - TRAVIS AV & ROCKLAND AV | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2009-11-16 | 2009-12-15 | 2024-05-27 | 2026-06-30
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200200 | NEW STORM SEWER EXTENSION, VARIOUS LOC IN STATEN ISLAND | 1 | DEVELOP SCOPE | 2009-06-30 | 2009-09-27 | 2011-07-01 | 2011-09-28
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200200 | NEW STORM SEWER EXTENSION, VARIOUS LOC IN STATEN ISLAND | 2 | PRELIMINARY DESIGN | 2009-09-28 | 2010-01-25 | 2011-09-29 | 2012-01-26
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200200 | NEW STORM SEWER EXTENSION, VARIOUS LOC IN STATEN ISLAND | 3 | FINAL DESIGN | 2010-01-26 | 2010-07-24 | 2012-01-27 | 2012-07-24
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200200 | NEW STORM SEWER EXTENSION, VARIOUS LOC IN STATEN ISLAND | 4 | BID AWARD AND REGISTER CONTRCT | 2010-07-25 | 2010-10-22 | 2012-07-25 | 2012-10-22
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200200 | NEW STORM SEWER EXTENSION, VARIOUS LOC IN STATEN ISLAND | 5 | CONSTRUCTION TO 25% | 2010-10-23 | 2011-02-19 | 2012-10-23 | 2013-02-19
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200200 | NEW STORM SEWER EXTENSION, VARIOUS LOC IN STATEN ISLAND | 6 | CONSTRUCTION TO 50% | 2011-02-20 | 2011-06-19 | 2013-02-20 | 2013-06-19
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200200 | NEW STORM SEWER EXTENSION, VARIOUS LOC IN STATEN ISLAND | 7 | CONSTRUCTION TO 75% | 2011-06-20 | 2011-10-17 | 2013-06-20 | 2013-10-17
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200200 | NEW STORM SEWER EXTENSION, VARIOUS LOC IN STATEN ISLAND | 8 | ORIGINAL EQUIP & FURNISHING | 2011-10-18 | 2012-01-15 | 2013-10-18 | 2014-01-15
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200200 | NEW STORM SEWER EXTENSION, VARIOUS LOC IN STATEN ISLAND | 9 | SUBSTANTIAL COMPLETION | 2012-01-16 | 2012-03-15 | 2014-01-16 | 2014-03-16
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200200 | NEW STORM SEWER EXTENSION, VARIOUS LOC IN STATEN ISLAND | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-03-16 | 2012-04-14 | 2014-03-17 | 2022-06-30
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200202 | New Stm. Swr. Ext. in Eagan Ave. S.I. | 1 | DEVELOP SCOPE | 2009-11-19 | 2010-08-15 | 2009-11-19 | 2010-08-15
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200202 | New Stm. Swr. Ext. in Eagan Ave. S.I. | 2 | PRELIMINARY DESIGN | 2010-08-16 | 2011-08-10 | 2010-08-16 | 2011-08-10
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200202 | New Stm. Swr. Ext. in Eagan Ave. S.I. | 3 | FINAL DESIGN | 2011-08-11 | 2013-01-31 | 2011-08-11 | 2013-01-31
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200202 | New Stm. Swr. Ext. in Eagan Ave. S.I. | 4 | BID AWARD AND REGISTER CONTRCT | 2013-02-01 | 2013-10-28 | 2013-02-01 | 2013-10-28
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200202 | New Stm. Swr. Ext. in Eagan Ave. S.I. | 5 | CONSTRUCTION TO 25% | 2013-10-29 | 2014-10-23 | 2013-10-29 | 2014-10-23
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200202 | New Stm. Swr. Ext. in Eagan Ave. S.I. | 6 | CONSTRUCTION TO 50% | 2014-10-24 | 2015-10-18 | 2014-10-24 | 2015-10-18
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200202 | New Stm. Swr. Ext. in Eagan Ave. S.I. | 7 | CONSTRUCTION TO 75% | 2015-10-19 | 2016-10-12 | 2015-10-19 | 2016-10-12
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200202 | New Stm. Swr. Ext. in Eagan Ave. S.I. | 8 | ORIGINAL EQUIP & FURNISHING | 2016-10-13 | 2017-07-09 | 2016-10-13 | 2017-07-09
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200202 | New Stm. Swr. Ext. in Eagan Ave. S.I. | 9 | SUBSTANTIAL COMPLETION | 2017-07-10 | 2018-01-05 | 2017-07-10 | 2018-01-05
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200202 | New Stm. Swr. Ext. in Eagan Ave. S.I. | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-01-06 | 2018-04-05 | 2018-01-06 | 2025-05-30
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200219 | storm swr ext in Cleveland Pl & Fingerboard Rd | 1 | DEVELOP SCOPE | 2009-06-30 | 2009-09-27 | 2011-07-01 | 2011-09-28
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200219 | storm swr ext in Cleveland Pl & Fingerboard Rd | 2 | PRELIMINARY DESIGN | 2009-09-28 | 2010-01-25 | 2011-09-29 | 2012-01-26
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200219 | storm swr ext in Cleveland Pl & Fingerboard Rd | 3 | FINAL DESIGN | 2010-01-26 | 2010-07-24 | 2012-01-27 | 2012-07-24
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200219 | storm swr ext in Cleveland Pl & Fingerboard Rd | 4 | BID AWARD AND REGISTER CONTRCT | 2010-07-25 | 2010-10-22 | 2012-07-25 | 2012-10-22
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200219 | storm swr ext in Cleveland Pl & Fingerboard Rd | 5 | CONSTRUCTION TO 25% | 2010-10-23 | 2011-02-19 | 2012-10-23 | 2013-02-19
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200219 | storm swr ext in Cleveland Pl & Fingerboard Rd | 6 | CONSTRUCTION TO 50% | 2011-02-20 | 2011-06-19 | 2013-02-20 | 2013-06-19
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200219 | storm swr ext in Cleveland Pl & Fingerboard Rd | 7 | CONSTRUCTION TO 75% | 2011-06-20 | 2011-10-17 | 2013-06-20 | 2013-10-17
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200219 | storm swr ext in Cleveland Pl & Fingerboard Rd | 8 | ORIGINAL EQUIP & FURNISHING | 2011-10-18 | 2012-01-15 | 2013-10-18 | 2014-01-15
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200219 | storm swr ext in Cleveland Pl & Fingerboard Rd | 9 | SUBSTANTIAL COMPLETION | 2012-01-16 | 2012-03-15 | 2014-01-16 | 2014-03-16
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200219 | storm swr ext in Cleveland Pl & Fingerboard Rd | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-03-16 | 2012-04-14 | 2014-03-17 | 2022-06-30
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200226 | STORM AND SANITARY SEWERS & WM WORK IN TRAVIS AREA | 1 | DEVELOP SCOPE | 2012-02-27 | 2012-05-26 | 2012-06-12 | 2012-09-09
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200226 | STORM AND SANITARY SEWERS & WM WORK IN TRAVIS AREA | 2 | PRELIMINARY DESIGN | 2012-05-27 | 2012-09-23 | 2012-09-10 | 2013-03-08
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200226 | STORM AND SANITARY SEWERS & WM WORK IN TRAVIS AREA | 3 | FINAL DESIGN | 2012-09-24 | 2013-03-22 | 2013-03-09 | 2016-03-08
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200226 | STORM AND SANITARY SEWERS & WM WORK IN TRAVIS AREA | 4 | BID AWARD AND REGISTER CONTRCT | 2013-03-23 | 2013-06-20 | 2016-03-09 | 2016-06-06
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200226 | STORM AND SANITARY SEWERS & WM WORK IN TRAVIS AREA | 5 | CONSTRUCTION TO 25% | 2013-06-21 | 2013-10-18 | 2016-06-07 | 2016-12-03
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200226 | STORM AND SANITARY SEWERS & WM WORK IN TRAVIS AREA | 6 | CONSTRUCTION TO 50% | 2013-10-19 | 2014-02-15 | 2016-12-04 | 2017-07-31
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200226 | STORM AND SANITARY SEWERS & WM WORK IN TRAVIS AREA | 7 | CONSTRUCTION TO 75% | 2014-02-16 | 2014-06-15 | 2017-08-01 | 2018-03-28
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200226 | STORM AND SANITARY SEWERS & WM WORK IN TRAVIS AREA | 8 | ORIGINAL EQUIP & FURNISHING | 2014-06-16 | 2014-09-13 | 2018-03-29 | 2018-06-26
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200226 | STORM AND SANITARY SEWERS & WM WORK IN TRAVIS AREA | 9 | SUBSTANTIAL COMPLETION | 2014-09-14 | 2014-11-12 | 2018-06-27 | 2018-08-25
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200226 | STORM AND SANITARY SEWERS & WM WORK IN TRAVIS AREA | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-11-13 | 2014-12-12 | 2018-08-26 | 2024-06-30
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200232 | STORM,SANIT SEWERS & WATER MAIN IN XENIA ST | 1 | DEVELOP SCOPE | 2014-02-27 | 2014-05-27 | 2014-02-27 | 2014-05-27
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200232 | STORM,SANIT SEWERS & WATER MAIN IN XENIA ST | 2 | PRELIMINARY DESIGN | 2014-05-28 | 2014-09-24 | 2014-05-28 | 2014-09-24
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200232 | STORM,SANIT SEWERS & WATER MAIN IN XENIA ST | 3 | FINAL DESIGN | 2014-09-25 | 2015-03-23 | 2014-09-25 | 2015-03-23
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200232 | STORM,SANIT SEWERS & WATER MAIN IN XENIA ST | 4 | BID AWARD AND REGISTER CONTRCT | 2015-03-24 | 2015-06-21 | 2015-03-24 | 2015-06-21
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200232 | STORM,SANIT SEWERS & WATER MAIN IN XENIA ST | 5 | CONSTRUCTION TO 25% | 2015-06-22 | 2015-10-19 | 2015-06-22 | 2015-10-19
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200232 | STORM,SANIT SEWERS & WATER MAIN IN XENIA ST | 6 | CONSTRUCTION TO 50% | 2015-10-20 | 2016-02-16 | 2015-10-20 | 2016-02-16
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200232 | STORM,SANIT SEWERS & WATER MAIN IN XENIA ST | 7 | CONSTRUCTION TO 75% | 2016-02-17 | 2016-06-15 | 2016-02-17 | 2016-06-15
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200232 | STORM,SANIT SEWERS & WATER MAIN IN XENIA ST | 8 | ORIGINAL EQUIP & FURNISHING | 2016-06-16 | 2016-09-13 | 2016-06-16 | 2016-09-13
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200232 | STORM,SANIT SEWERS & WATER MAIN IN XENIA ST | 9 | SUBSTANTIAL COMPLETION | 2016-09-14 | 2016-11-12 | 2016-09-14 | 2016-11-12
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200232 | STORM,SANIT SEWERS & WATER MAIN IN XENIA ST | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-11-13 | 2016-12-12 | 2016-11-13 | 2024-09-15
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200235 | Storm Sewer Extension in Richmond Ave & Amboy Rd, SI | 1 | DEVELOP SCOPE | 2012-06-12 | 2013-03-08 | 2012-06-12 | 2013-03-08
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200235 | Storm Sewer Extension in Richmond Ave & Amboy Rd, SI | 2 | PRELIMINARY DESIGN | 2013-03-09 | 2014-03-03 | 2013-03-09 | 2014-03-03
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200235 | Storm Sewer Extension in Richmond Ave & Amboy Rd, SI | 3 | FINAL DESIGN | 2014-03-04 | 2015-08-25 | 2014-03-04 | 2015-08-25
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200235 | Storm Sewer Extension in Richmond Ave & Amboy Rd, SI | 4 | BID AWARD AND REGISTER CONTRCT | 2015-08-26 | 2016-05-21 | 2015-08-26 | 2016-05-21
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200235 | Storm Sewer Extension in Richmond Ave & Amboy Rd, SI | 5 | CONSTRUCTION TO 25% | 2016-05-22 | 2017-05-16 | 2016-05-22 | 2017-05-16
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200235 | Storm Sewer Extension in Richmond Ave & Amboy Rd, SI | 6 | CONSTRUCTION TO 50% | 2017-05-17 | 2018-05-11 | 2017-05-17 | 2018-05-11
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200235 | Storm Sewer Extension in Richmond Ave & Amboy Rd, SI | 7 | CONSTRUCTION TO 75% | 2018-05-12 | 2019-05-06 | 2018-05-12 | 2019-05-06
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200235 | Storm Sewer Extension in Richmond Ave & Amboy Rd, SI | 8 | ORIGINAL EQUIP & FURNISHING | 2019-05-07 | 2020-01-31 | 2019-05-07 | 2020-01-31
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200235 | Storm Sewer Extension in Richmond Ave & Amboy Rd, SI | 9 | SUBSTANTIAL COMPLETION | 2020-02-01 | 2020-07-29 | 2020-02-01 | 2020-07-29
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200235 | Storm Sewer Extension in Richmond Ave & Amboy Rd, SI | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-07-30 | 2020-10-27 | 2020-07-30 | 2026-06-30
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200236 | STRM SWR EXT & WM WORK IN NORTH AV, ETC. | 1 | DEVELOP SCOPE | 2019-03-01 | 2019-05-29 | 2019-03-01 | 2019-05-29
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200236 | STRM SWR EXT & WM WORK IN NORTH AV, ETC. | 2 | PRELIMINARY DESIGN | 2019-05-30 | 2019-09-26 | 2019-05-30 | 2019-09-26
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200236 | STRM SWR EXT & WM WORK IN NORTH AV, ETC. | 3 | FINAL DESIGN | 2019-09-27 | 2020-03-24 | 2019-09-27 | 2020-03-24
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200236 | STRM SWR EXT & WM WORK IN NORTH AV, ETC. | 4 | BID AWARD AND REGISTER CONTRCT | 2020-03-25 | 2020-06-22 | 2020-03-25 | 2020-06-22
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200236 | STRM SWR EXT & WM WORK IN NORTH AV, ETC. | 5 | CONSTRUCTION TO 25% | 2020-06-23 | 2020-10-20 | 2020-06-23 | 2020-10-20
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200236 | STRM SWR EXT & WM WORK IN NORTH AV, ETC. | 6 | CONSTRUCTION TO 50% | 2020-10-21 | 2021-02-17 | 2020-10-21 | 2021-02-17
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200236 | STRM SWR EXT & WM WORK IN NORTH AV, ETC. | 7 | CONSTRUCTION TO 75% | 2021-02-18 | 2021-06-17 | 2021-02-18 | 2021-06-17
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200236 | STRM SWR EXT & WM WORK IN NORTH AV, ETC. | 8 | ORIGINAL EQUIP & FURNISHING | 2021-06-18 | 2021-09-15 | 2021-06-18 | 2021-09-15
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200236 | STRM SWR EXT & WM WORK IN NORTH AV, ETC. | 9 | SUBSTANTIAL COMPLETION | 2021-09-16 | 2021-11-14 | 2021-09-16 | 2021-11-14
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200236 | STRM SWR EXT & WM WORK IN NORTH AV, ETC. | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-11-15 | 2021-12-14 | 2021-11-15 | 2021-12-14
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200241 | STRM & SWR IN BLOOMINGTON RD B/T AUTHUR KILL RD & PITNEY AVE | 1 | DEVELOP SCOPE | 2012-06-30 | 2012-09-27 | 2012-06-01 | 2012-08-29
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200241 | STRM & SWR IN BLOOMINGTON RD B/T AUTHUR KILL RD & PITNEY AVE | 2 | PRELIMINARY DESIGN | 2012-09-28 | 2013-01-25 | 2012-08-30 | 2013-02-25
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200241 | STRM & SWR IN BLOOMINGTON RD B/T AUTHUR KILL RD & PITNEY AVE | 3 | FINAL DESIGN | 2013-01-26 | 2013-07-24 | 2012-02-07 | 2015-03-16
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200241 | STRM & SWR IN BLOOMINGTON RD B/T AUTHUR KILL RD & PITNEY AVE | 4 | BID AWARD AND REGISTER CONTRCT | 2013-07-25 | 2013-10-22 | 2015-03-17 | 2015-06-14
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200241 | STRM & SWR IN BLOOMINGTON RD B/T AUTHUR KILL RD & PITNEY AVE | 5 | CONSTRUCTION TO 25% | 2013-10-23 | 2014-02-19 | 2015-06-15 | 2015-12-11
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200241 | STRM & SWR IN BLOOMINGTON RD B/T AUTHUR KILL RD & PITNEY AVE | 6 | CONSTRUCTION TO 50% | 2014-02-20 | 2014-06-19 | 2015-12-12 | 2016-12-10
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200241 | STRM & SWR IN BLOOMINGTON RD B/T AUTHUR KILL RD & PITNEY AVE | 7 | CONSTRUCTION TO 75% | 2014-06-20 | 2014-10-17 | 2016-12-11 | 2017-06-08
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200241 | STRM & SWR IN BLOOMINGTON RD B/T AUTHUR KILL RD & PITNEY AVE | 8 | ORIGINAL EQUIP & FURNISHING | 2014-10-18 | 2015-01-15 | 2017-06-09 | 2017-09-06
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200241 | STRM & SWR IN BLOOMINGTON RD B/T AUTHUR KILL RD & PITNEY AVE | 9 | SUBSTANTIAL COMPLETION | 2015-01-16 | 2015-03-16 | 2017-09-07 | 2017-11-05
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200241 | STRM & SWR IN BLOOMINGTON RD B/T AUTHUR KILL RD & PITNEY AVE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-17 | 2015-04-15 | 2017-11-06 | 2022-07-14
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200245 | NEW STRM SWR & WM REPLACEMT IN ACACIA AV, ETC. | 1 | DEVELOP SCOPE | 2015-02-16 | 2015-05-16 | 2017-03-01 | 2017-05-29
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200245 | NEW STRM SWR & WM REPLACEMT IN ACACIA AV, ETC. | 2 | PRELIMINARY DESIGN | 2015-05-17 | 2015-09-13 | 2017-05-30 | 2017-09-26
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200245 | NEW STRM SWR & WM REPLACEMT IN ACACIA AV, ETC. | 3 | FINAL DESIGN | 2015-09-14 | 2016-03-11 | 2017-09-27 | 2018-03-25
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200245 | NEW STRM SWR & WM REPLACEMT IN ACACIA AV, ETC. | 4 | BID AWARD AND REGISTER CONTRCT | 2016-03-12 | 2016-06-09 | 2018-03-26 | 2018-06-23
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200245 | NEW STRM SWR & WM REPLACEMT IN ACACIA AV, ETC. | 5 | CONSTRUCTION TO 25% | 2016-06-10 | 2016-10-07 | 2018-06-24 | 2018-10-21
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200245 | NEW STRM SWR & WM REPLACEMT IN ACACIA AV, ETC. | 6 | CONSTRUCTION TO 50% | 2016-10-08 | 2017-02-04 | 2018-10-22 | 2019-02-18
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200245 | NEW STRM SWR & WM REPLACEMT IN ACACIA AV, ETC. | 7 | CONSTRUCTION TO 75% | 2017-02-05 | 2017-06-04 | 2019-02-19 | 2019-06-18
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200245 | NEW STRM SWR & WM REPLACEMT IN ACACIA AV, ETC. | 8 | ORIGINAL EQUIP & FURNISHING | 2017-06-05 | 2017-09-02 | 2019-06-19 | 2019-09-16
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200245 | NEW STRM SWR & WM REPLACEMT IN ACACIA AV, ETC. | 9 | SUBSTANTIAL COMPLETION | 2017-09-03 | 2017-11-01 | 2019-09-17 | 2019-11-15
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200245 | NEW STRM SWR & WM REPLACEMT IN ACACIA AV, ETC. | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-11-02 | 2017-12-01 | 2019-11-16 | 2023-11-27
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200247 | New Storm Sewers in King St | 1 | DEVELOP SCOPE | 2013-04-18 | 2014-01-12 | 2013-04-18 | 2014-01-12
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200247 | New Storm Sewers in King St | 2 | PRELIMINARY DESIGN | 2014-01-13 | 2015-01-07 | 2014-01-13 | 2015-01-07
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200247 | New Storm Sewers in King St | 3 | FINAL DESIGN | 2015-01-08 | 2016-06-30 | 2015-01-08 | 2016-06-30
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200247 | New Storm Sewers in King St | 4 | BID AWARD AND REGISTER CONTRCT | 2016-07-01 | 2017-03-27 | 2016-07-01 | 2017-03-27
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200247 | New Storm Sewers in King St | 5 | CONSTRUCTION TO 25% | 2017-03-28 | 2018-03-22 | 2017-03-28 | 2018-03-22
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200247 | New Storm Sewers in King St | 6 | CONSTRUCTION TO 50% | 2018-03-23 | 2019-03-17 | 2018-03-23 | 2019-03-17
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200247 | New Storm Sewers in King St | 7 | CONSTRUCTION TO 75% | 2019-03-18 | 2020-03-11 | 2019-03-18 | 2020-03-11
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200247 | New Storm Sewers in King St | 8 | ORIGINAL EQUIP & FURNISHING | 2020-03-12 | 2020-12-06 | 2020-03-12 | 2020-12-06
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200247 | New Storm Sewers in King St | 9 | SUBSTANTIAL COMPLETION | 2020-12-07 | 2021-06-04 | 2020-12-07 | 2021-06-04
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200247 | New Storm Sewers in King St | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-06-05 | 2021-09-02 | 2021-06-05 | 2021-09-02
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200251 | EXT OF STRM SWR AND WM WORK IN 3RD ST | 1 | DEVELOP SCOPE | 2021-03-01 | 2021-05-29 | 2021-03-01 | 2021-05-29
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200251 | EXT OF STRM SWR AND WM WORK IN 3RD ST | 2 | PRELIMINARY DESIGN | 2021-05-30 | 2021-09-26 | 2021-05-30 | 2021-09-26
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200251 | EXT OF STRM SWR AND WM WORK IN 3RD ST | 3 | FINAL DESIGN | 2021-09-27 | 2022-03-25 | 2021-09-27 | 2022-03-25
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200251 | EXT OF STRM SWR AND WM WORK IN 3RD ST | 4 | BID AWARD AND REGISTER CONTRCT | 2022-03-26 | 2022-06-23 | 2022-03-26 | 2022-06-23
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200251 | EXT OF STRM SWR AND WM WORK IN 3RD ST | 5 | CONSTRUCTION TO 25% | 2022-06-24 | 2022-10-21 | 2022-06-24 | 2022-10-21
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200251 | EXT OF STRM SWR AND WM WORK IN 3RD ST | 6 | CONSTRUCTION TO 50% | 2022-10-22 | 2023-02-18 | 2022-10-22 | 2023-02-18
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200251 | EXT OF STRM SWR AND WM WORK IN 3RD ST | 7 | CONSTRUCTION TO 75% | 2023-02-19 | 2023-06-18 | 2023-02-19 | 2023-06-18
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200251 | EXT OF STRM SWR AND WM WORK IN 3RD ST | 8 | ORIGINAL EQUIP & FURNISHING | 2023-06-19 | 2023-09-16 | 2023-06-19 | 2023-09-16
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200251 | EXT OF STRM SWR AND WM WORK IN 3RD ST | 9 | SUBSTANTIAL COMPLETION | 2023-09-17 | 2023-11-15 | 2023-09-17 | 2023-11-15
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200251 | EXT OF STRM SWR AND WM WORK IN 3RD ST | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-11-16 | 2023-12-15 | 2023-11-16 | 2023-12-15
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200255 | Stm. Swr. Ext. W. Cedarview Ave b/t Wolverine&Gilbert st, SI | 1 | DEVELOP SCOPE | 2018-03-01 | 2018-05-29 | 2018-03-01 | 2018-05-29
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200255 | Stm. Swr. Ext. W. Cedarview Ave b/t Wolverine&Gilbert st, SI | 2 | PRELIMINARY DESIGN | 2018-05-30 | 2018-09-26 | 2018-05-30 | 2018-09-26
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200255 | Stm. Swr. Ext. W. Cedarview Ave b/t Wolverine&Gilbert st, SI | 3 | FINAL DESIGN | 2018-09-27 | 2019-03-25 | 2018-09-27 | 2019-03-25
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200255 | Stm. Swr. Ext. W. Cedarview Ave b/t Wolverine&Gilbert st, SI | 4 | BID AWARD AND REGISTER CONTRCT | 2019-03-26 | 2019-06-23 | 2019-03-26 | 2019-06-23
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200255 | Stm. Swr. Ext. W. Cedarview Ave b/t Wolverine&Gilbert st, SI | 5 | CONSTRUCTION TO 25% | 2019-06-24 | 2019-10-21 | 2019-06-24 | 2019-10-21
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200255 | Stm. Swr. Ext. W. Cedarview Ave b/t Wolverine&Gilbert st, SI | 6 | CONSTRUCTION TO 50% | 2019-10-22 | 2020-02-18 | 2019-10-22 | 2020-02-18
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200255 | Stm. Swr. Ext. W. Cedarview Ave b/t Wolverine&Gilbert st, SI | 7 | CONSTRUCTION TO 75% | 2020-02-19 | 2020-06-17 | 2020-02-19 | 2020-06-17
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200255 | Stm. Swr. Ext. W. Cedarview Ave b/t Wolverine&Gilbert st, SI | 8 | ORIGINAL EQUIP & FURNISHING | 2020-06-18 | 2020-09-15 | 2020-06-18 | 2020-09-15
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200255 | Stm. Swr. Ext. W. Cedarview Ave b/t Wolverine&Gilbert st, SI | 9 | SUBSTANTIAL COMPLETION | 2020-09-16 | 2020-11-14 | 2020-09-16 | 2020-11-14
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200255 | Stm. Swr. Ext. W. Cedarview Ave b/t Wolverine&Gilbert st, SI | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-11-15 | 2020-12-14 | 2020-11-15 | 2020-12-14
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200258 | Sanitary and Storm Sewer in West Castor Place between Alvers | 1 | DEVELOP SCOPE | 2015-02-27 | 2015-05-27 | 2015-02-27 | 2015-05-27
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200258 | Sanitary and Storm Sewer in West Castor Place between Alvers | 2 | PRELIMINARY DESIGN | 2015-05-28 | 2015-09-24 | 2015-05-28 | 2015-09-24
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200258 | Sanitary and Storm Sewer in West Castor Place between Alvers | 3 | FINAL DESIGN | 2015-09-25 | 2016-03-22 | 2015-09-25 | 2016-03-22
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200258 | Sanitary and Storm Sewer in West Castor Place between Alvers | 4 | BID AWARD AND REGISTER CONTRCT | 2016-03-23 | 2016-06-20 | 2016-03-23 | 2016-06-20
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200258 | Sanitary and Storm Sewer in West Castor Place between Alvers | 5 | CONSTRUCTION TO 25% | 2016-06-21 | 2016-10-18 | 2016-06-21 | 2016-10-18
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200258 | Sanitary and Storm Sewer in West Castor Place between Alvers | 6 | CONSTRUCTION TO 50% | 2016-10-19 | 2017-02-15 | 2016-10-19 | 2017-02-15
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200258 | Sanitary and Storm Sewer in West Castor Place between Alvers | 7 | CONSTRUCTION TO 75% | 2017-02-16 | 2017-06-15 | 2017-02-16 | 2017-06-15
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200258 | Sanitary and Storm Sewer in West Castor Place between Alvers | 8 | ORIGINAL EQUIP & FURNISHING | 2017-06-16 | 2017-09-13 | 2017-06-16 | 2017-09-13
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200258 | Sanitary and Storm Sewer in West Castor Place between Alvers | 9 | SUBSTANTIAL COMPLETION | 2017-09-14 | 2017-11-12 | 2017-09-14 | 2017-11-12
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200258 | Sanitary and Storm Sewer in West Castor Place between Alvers | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-11-13 | 2017-12-12 | 2017-11-13 | 2024-06-30
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200261 | Storm sewer in Roma Ave bet Tysens Lane & Ebbits Street | 1 | DEVELOP SCOPE | 2018-03-01 | 2018-05-29 | 2018-03-01 | 2018-05-29
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200261 | Storm sewer in Roma Ave bet Tysens Lane & Ebbits Street | 2 | PRELIMINARY DESIGN | 2018-05-30 | 2018-09-26 | 2018-05-30 | 2018-09-26
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200261 | Storm sewer in Roma Ave bet Tysens Lane & Ebbits Street | 3 | FINAL DESIGN | 2018-09-27 | 2019-03-25 | 2018-09-27 | 2019-03-25
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200261 | Storm sewer in Roma Ave bet Tysens Lane & Ebbits Street | 4 | BID AWARD AND REGISTER CONTRCT | 2019-03-26 | 2019-06-23 | 2019-03-26 | 2019-06-23
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200261 | Storm sewer in Roma Ave bet Tysens Lane & Ebbits Street | 5 | CONSTRUCTION TO 25% | 2019-06-24 | 2019-10-21 | 2019-06-24 | 2019-10-21
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200261 | Storm sewer in Roma Ave bet Tysens Lane & Ebbits Street | 6 | CONSTRUCTION TO 50% | 2019-10-22 | 2020-02-18 | 2019-10-22 | 2020-02-18
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200261 | Storm sewer in Roma Ave bet Tysens Lane & Ebbits Street | 7 | CONSTRUCTION TO 75% | 2020-02-19 | 2020-06-17 | 2020-02-19 | 2020-06-17
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200261 | Storm sewer in Roma Ave bet Tysens Lane & Ebbits Street | 8 | ORIGINAL EQUIP & FURNISHING | 2020-06-18 | 2020-09-15 | 2020-06-18 | 2020-09-15
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200261 | Storm sewer in Roma Ave bet Tysens Lane & Ebbits Street | 9 | SUBSTANTIAL COMPLETION | 2020-09-16 | 2020-11-14 | 2020-09-16 | 2020-11-14
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200261 | Storm sewer in Roma Ave bet Tysens Lane & Ebbits Street | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-11-15 | 2020-12-14 | 2020-11-15 | 2023-12-15
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200285 | NEW STM. SWR EXT. & WM REPL IN TODT HILL RD., SI | 1 | DEVELOP SCOPE | 2017-03-01 | 2017-05-29 | 2017-03-01 | 2017-05-29
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200285 | NEW STM. SWR EXT. & WM REPL IN TODT HILL RD., SI | 2 | PRELIMINARY DESIGN | 2017-05-30 | 2017-09-26 | 2017-05-30 | 2017-09-26
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200285 | NEW STM. SWR EXT. & WM REPL IN TODT HILL RD., SI | 3 | FINAL DESIGN | 2017-09-27 | 2018-03-25 | 2017-09-27 | 2018-03-25
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200285 | NEW STM. SWR EXT. & WM REPL IN TODT HILL RD., SI | 4 | BID AWARD AND REGISTER CONTRCT | 2018-03-26 | 2018-06-23 | 2018-03-26 | 2018-06-23
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200285 | NEW STM. SWR EXT. & WM REPL IN TODT HILL RD., SI | 5 | CONSTRUCTION TO 25% | 2018-06-24 | 2018-10-21 | 2018-06-24 | 2018-10-21
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200285 | NEW STM. SWR EXT. & WM REPL IN TODT HILL RD., SI | 6 | CONSTRUCTION TO 50% | 2018-10-22 | 2019-02-18 | 2018-10-22 | 2019-02-18
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200285 | NEW STM. SWR EXT. & WM REPL IN TODT HILL RD., SI | 7 | CONSTRUCTION TO 75% | 2019-02-19 | 2019-06-18 | 2019-02-19 | 2019-06-18
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200285 | NEW STM. SWR EXT. & WM REPL IN TODT HILL RD., SI | 8 | ORIGINAL EQUIP & FURNISHING | 2019-06-19 | 2019-09-16 | 2019-06-19 | 2019-09-16
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200285 | NEW STM. SWR EXT. & WM REPL IN TODT HILL RD., SI | 9 | SUBSTANTIAL COMPLETION | 2019-09-17 | 2019-11-15 | 2019-09-17 | 2019-11-15
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200285 | NEW STM. SWR EXT. & WM REPL IN TODT HILL RD., SI | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-11-16 | 2019-12-15 | 2019-11-16 | 2024-09-09
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200290 | New Storm Sewer Ext & Water Main Replacement in Forest Ave | 1 | DEVELOP SCOPE | 2018-06-01 | 2018-08-29 | 2018-06-01 | 2018-08-29
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200290 | New Storm Sewer Ext & Water Main Replacement in Forest Ave | 2 | PRELIMINARY DESIGN | 2018-08-30 | 2018-12-27 | 2018-08-30 | 2018-12-27
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200290 | New Storm Sewer Ext & Water Main Replacement in Forest Ave | 3 | FINAL DESIGN | 2018-12-28 | 2019-06-25 | 2018-12-28 | 2019-06-25
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200290 | New Storm Sewer Ext & Water Main Replacement in Forest Ave | 4 | BID AWARD AND REGISTER CONTRCT | 2019-06-26 | 2019-09-23 | 2019-06-26 | 2019-09-23
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200290 | New Storm Sewer Ext & Water Main Replacement in Forest Ave | 5 | CONSTRUCTION TO 25% | 2019-09-24 | 2020-01-21 | 2019-09-24 | 2020-01-21
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200290 | New Storm Sewer Ext & Water Main Replacement in Forest Ave | 6 | CONSTRUCTION TO 50% | 2020-01-22 | 2020-05-20 | 2020-01-22 | 2020-05-20
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200290 | New Storm Sewer Ext & Water Main Replacement in Forest Ave | 7 | CONSTRUCTION TO 75% | 2020-05-21 | 2020-09-17 | 2020-05-21 | 2020-09-17
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200290 | New Storm Sewer Ext & Water Main Replacement in Forest Ave | 8 | ORIGINAL EQUIP & FURNISHING | 2020-09-18 | 2020-12-16 | 2020-09-18 | 2020-12-16
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200290 | New Storm Sewer Ext & Water Main Replacement in Forest Ave | 9 | SUBSTANTIAL COMPLETION | 2020-12-17 | 2021-02-14 | 2020-12-17 | 2021-02-14
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200290 | New Storm Sewer Ext & Water Main Replacement in Forest Ave | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-02-15 | 2021-03-16 | 2021-02-15 | 2026-01-30
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200292 | SAN & STRM SWR REPLACMT & WM WORK IN FLOYD ST | 1 | DEVELOP SCOPE | 2020-10-01 | 2020-12-29 | 2020-10-01 | 2020-12-29
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200292 | SAN & STRM SWR REPLACMT & WM WORK IN FLOYD ST | 2 | PRELIMINARY DESIGN | 2020-12-30 | 2021-04-28 | 2020-12-30 | 2021-04-28
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200292 | SAN & STRM SWR REPLACMT & WM WORK IN FLOYD ST | 3 | FINAL DESIGN | 2021-04-29 | 2021-10-25 | 2021-04-29 | 2021-10-25
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200292 | SAN & STRM SWR REPLACMT & WM WORK IN FLOYD ST | 4 | BID AWARD AND REGISTER CONTRCT | 2021-10-26 | 2022-01-23 | 2021-10-26 | 2022-01-23
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200292 | SAN & STRM SWR REPLACMT & WM WORK IN FLOYD ST | 5 | CONSTRUCTION TO 25% | 2022-01-24 | 2022-05-23 | 2022-01-24 | 2022-05-23
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200292 | SAN & STRM SWR REPLACMT & WM WORK IN FLOYD ST | 6 | CONSTRUCTION TO 50% | 2022-05-24 | 2022-09-20 | 2022-05-24 | 2022-09-20
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200292 | SAN & STRM SWR REPLACMT & WM WORK IN FLOYD ST | 7 | CONSTRUCTION TO 75% | 2022-09-21 | 2023-01-18 | 2022-09-21 | 2023-01-18
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200292 | SAN & STRM SWR REPLACMT & WM WORK IN FLOYD ST | 8 | ORIGINAL EQUIP & FURNISHING | 2023-01-19 | 2023-04-18 | 2023-01-19 | 2023-04-18
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200292 | SAN & STRM SWR REPLACMT & WM WORK IN FLOYD ST | 9 | SUBSTANTIAL COMPLETION | 2023-04-19 | 2023-06-17 | 2023-04-19 | 2023-06-17
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200292 | SAN & STRM SWR REPLACMT & WM WORK IN FLOYD ST | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-06-18 | 2023-07-17 | 2023-06-18 | 2025-10-02
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200309 | Strm swr R+Ext & WM Work, Maguire Avenue | 1 | DEVELOP SCOPE | 2018-01-15 | 2018-04-14 | 2018-01-15 | 2018-04-14
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200309 | Strm swr R+Ext & WM Work, Maguire Avenue | 2 | PRELIMINARY DESIGN | 2018-04-15 | 2018-08-12 | 2018-04-15 | 2018-08-12
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200309 | Strm swr R+Ext & WM Work, Maguire Avenue | 3 | FINAL DESIGN | 2018-08-13 | 2019-02-08 | 2018-08-13 | 2019-02-08
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200309 | Strm swr R+Ext & WM Work, Maguire Avenue | 4 | BID AWARD AND REGISTER CONTRCT | 2019-02-09 | 2019-05-09 | 2019-02-09 | 2019-05-09
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200309 | Strm swr R+Ext & WM Work, Maguire Avenue | 5 | CONSTRUCTION TO 25% | 2019-05-10 | 2019-09-06 | 2019-05-10 | 2019-09-06
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200309 | Strm swr R+Ext & WM Work, Maguire Avenue | 6 | CONSTRUCTION TO 50% | 2019-09-07 | 2020-01-04 | 2019-09-07 | 2020-01-04
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200309 | Strm swr R+Ext & WM Work, Maguire Avenue | 7 | CONSTRUCTION TO 75% | 2020-01-05 | 2020-05-03 | 2020-01-05 | 2020-05-03
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200309 | Strm swr R+Ext & WM Work, Maguire Avenue | 8 | ORIGINAL EQUIP & FURNISHING | 2020-05-04 | 2020-08-01 | 2020-05-04 | 2020-08-01
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200309 | Strm swr R+Ext & WM Work, Maguire Avenue | 9 | SUBSTANTIAL COMPLETION | 2020-08-02 | 2020-09-30 | 2020-08-02 | 2020-09-30
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200309 | Strm swr R+Ext & WM Work, Maguire Avenue | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-10-01 | 2020-10-30 | 2020-10-01 | 2026-06-30
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200552 | STRM & SAN SWR AND WM WORK IN GRANITE AV | 1 | DEVELOP SCOPE | 2019-10-01 | 2019-12-29 | 2019-10-01 | 2019-12-29
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200552 | STRM & SAN SWR AND WM WORK IN GRANITE AV | 2 | PRELIMINARY DESIGN | 2019-12-30 | 2020-04-27 | 2019-12-30 | 2020-04-27
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200552 | STRM & SAN SWR AND WM WORK IN GRANITE AV | 3 | FINAL DESIGN | 2020-04-28 | 2020-10-24 | 2020-04-28 | 2020-10-24
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200552 | STRM & SAN SWR AND WM WORK IN GRANITE AV | 4 | BID AWARD AND REGISTER CONTRCT | 2020-10-25 | 2021-01-22 | 2020-10-25 | 2021-01-22
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200552 | STRM & SAN SWR AND WM WORK IN GRANITE AV | 5 | CONSTRUCTION TO 25% | 2021-01-23 | 2021-05-22 | 2021-01-23 | 2021-05-22
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200552 | STRM & SAN SWR AND WM WORK IN GRANITE AV | 6 | CONSTRUCTION TO 50% | 2021-05-23 | 2021-09-19 | 2021-05-23 | 2021-09-19
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200552 | STRM & SAN SWR AND WM WORK IN GRANITE AV | 7 | CONSTRUCTION TO 75% | 2021-09-20 | 2022-01-17 | 2021-09-20 | 2022-01-17
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200552 | STRM & SAN SWR AND WM WORK IN GRANITE AV | 8 | ORIGINAL EQUIP & FURNISHING | 2022-01-18 | 2022-04-17 | 2022-01-18 | 2022-04-17
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200552 | STRM & SAN SWR AND WM WORK IN GRANITE AV | 9 | SUBSTANTIAL COMPLETION | 2022-04-18 | 2022-06-16 | 2022-04-18 | 2022-06-16
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200552 | STRM & SAN SWR AND WM WORK IN GRANITE AV | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-06-17 | 2022-07-16 | 2022-06-17 | 2025-06-30
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER20079 | RECON OF STORM SEWER, WILLOW AV(TOMPKINS-EDGEWATER AVS) | 1 | DEVELOP SCOPE | 2008-02-24 | 2008-05-23 | 2011-06-18 | 2011-09-15
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER20079 | RECON OF STORM SEWER, WILLOW AV(TOMPKINS-EDGEWATER AVS) | 2 | PRELIMINARY DESIGN | 2008-05-24 | 2008-09-20 | 2011-09-16 | 2012-03-13
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER20079 | RECON OF STORM SEWER, WILLOW AV(TOMPKINS-EDGEWATER AVS) | 3 | FINAL DESIGN | 2008-09-21 | 2009-03-19 | 2012-03-14 | 2016-03-08
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER20079 | RECON OF STORM SEWER, WILLOW AV(TOMPKINS-EDGEWATER AVS) | 4 | BID AWARD AND REGISTER CONTRCT | 2009-03-20 | 2009-06-17 | 2016-03-09 | 2016-03-08
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER20079 | RECON OF STORM SEWER, WILLOW AV(TOMPKINS-EDGEWATER AVS) | 5 | CONSTRUCTION TO 25% | 2009-06-18 | 2009-10-15 | 2016-03-09 | 2016-03-08
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER20079 | RECON OF STORM SEWER, WILLOW AV(TOMPKINS-EDGEWATER AVS) | 6 | CONSTRUCTION TO 50% | 2009-10-16 | 2010-02-12 | 2016-03-09 | 2016-03-08
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER20079 | RECON OF STORM SEWER, WILLOW AV(TOMPKINS-EDGEWATER AVS) | 7 | CONSTRUCTION TO 75% | 2010-02-13 | 2010-06-12 | 2016-03-09 | 2016-03-08
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER20079 | RECON OF STORM SEWER, WILLOW AV(TOMPKINS-EDGEWATER AVS) | 8 | ORIGINAL EQUIP & FURNISHING | 2010-06-13 | 2010-09-10 | 2016-03-09 | 2016-03-08
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER20079 | RECON OF STORM SEWER, WILLOW AV(TOMPKINS-EDGEWATER AVS) | 9 | SUBSTANTIAL COMPLETION | 2010-09-11 | 2010-11-09 | 2016-03-09 | 2016-03-08
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER20079 | RECON OF STORM SEWER, WILLOW AV(TOMPKINS-EDGEWATER AVS) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2010-11-10 | 2010-12-09 | 2016-03-09 | 2021-09-28
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SOLARDOS2 | Staten Island 3 Garage HVAC | 1 | PROJECT START | 2019-03-01 | 2019-03-01 | 2015-12-09 | 2015-12-10
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SOLARDOS2 | Staten Island 3 Garage HVAC | 2 | DESIGN START | 2019-03-02 | 2019-03-02 | 2015-12-11 | 2017-07-14
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SOLARDOS2 | Staten Island 3 Garage HVAC | 3 | DESIGN COMPLETION | 2019-03-03 | 2019-03-03 | 2017-07-15 | 2019-06-28
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SOLARDOS2 | Staten Island 3 Garage HVAC | 4 | CONSTRUCTION START | 2019-03-04 | 2019-03-04 | 2019-06-29 | 2020-03-30
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SOLARDOS2 | Staten Island 3 Garage HVAC | 5 | CONSTRUCTION COMPLETION | 2019-03-05 | 2019-03-05 | 2020-03-31 | 2022-03-30
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SOLARGR10 | DSNY - PV INSTALLATION ON NEW GARAGE- STATEN ISLAND 1/3 | 1 | PROJECT START | 2019-03-01 | 2019-03-01 | 2019-03-01 | 2019-03-01
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SOLARGR10 | DSNY - PV INSTALLATION ON NEW GARAGE- STATEN ISLAND 1/3 | 2 | DESIGN START | 2019-03-02 | 2019-03-02 | 2019-03-02 | 2019-03-02
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SOLARGR10 | DSNY - PV INSTALLATION ON NEW GARAGE- STATEN ISLAND 1/3 | 3 | DESIGN COMPLETION | 2019-03-03 | 2019-03-03 | 2019-03-03 | 2019-03-03
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SOLARGR10 | DSNY - PV INSTALLATION ON NEW GARAGE- STATEN ISLAND 1/3 | 4 | CONSTRUCTION START | 2019-03-04 | 2019-03-04 | 2019-03-04 | 2019-03-04
20201123 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SOLARGR10 | DSNY - PV INSTALLATION ON NEW GARAGE- STATEN ISLAND 1/3 | 5 | CONSTRUCTION COMPLETION | 2019-03-05 | 2022-12-31 | 2019-03-05 | 2022-12-31
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO276EXT2 | 100 Richmond Terrace - Family Court/ Exterior | 1 | DEVELOP SCOPE | 2022-01-01 | 2022-03-31 | 2025-06-01 | 2025-08-29
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO276EXT2 | 100 Richmond Terrace - Family Court/ Exterior | 2 | PRELIMINARY DESIGN | 2022-04-01 | 2022-07-29 | 2025-08-30 | 2025-12-27
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO276EXT2 | 100 Richmond Terrace - Family Court/ Exterior | 3 | FINAL DESIGN | 2022-07-30 | 2023-01-25 | 2025-12-28 | 2026-06-25
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO276EXT2 | 100 Richmond Terrace - Family Court/ Exterior | 4 | BID AWARD AND REGISTER CONTRCT | 2023-01-26 | 2023-04-25 | 2026-06-26 | 2026-09-23
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO276EXT2 | 100 Richmond Terrace - Family Court/ Exterior | 5 | CONSTRUCTION TO 25% | 2023-04-26 | 2023-08-23 | 2026-09-24 | 2027-01-21
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO276EXT2 | 100 Richmond Terrace - Family Court/ Exterior | 6 | CONSTRUCTION TO 50% | 2023-08-24 | 2023-12-21 | 2027-01-22 | 2027-05-21
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO276EXT2 | 100 Richmond Terrace - Family Court/ Exterior | 7 | CONSTRUCTION TO 75% | 2023-12-22 | 2024-04-19 | 2027-05-22 | 2027-09-18
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO276EXT2 | 100 Richmond Terrace - Family Court/ Exterior | 8 | ORIGINAL EQUIP & FURNISHING | 2024-04-20 | 2024-07-18 | 2027-09-19 | 2027-12-17
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO276EXT2 | 100 Richmond Terrace - Family Court/ Exterior | 9 | SUBSTANTIAL COMPLETION | 2024-07-19 | 2024-09-16 | 2027-12-18 | 2028-02-15
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO276EXT2 | 100 Richmond Terrace - Family Court/ Exterior | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-09-17 | 2024-10-16 | 2028-02-16 | 2028-03-16
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO287R-1 | DASNY - NEW STATEN ISLAND SUPREME COURT | 1 | DEVELOP SCOPE | 2006-06-01 | 2006-08-29 | 2006-06-01 | 2006-08-29
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO287R-1 | DASNY - NEW STATEN ISLAND SUPREME COURT | 2 | PRELIMINARY DESIGN | 2006-08-30 | 2006-12-27 | 2006-08-30 | 2006-12-27
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO287R-1 | DASNY - NEW STATEN ISLAND SUPREME COURT | 3 | FINAL DESIGN | 2006-12-28 | 2007-06-25 | 2006-12-28 | 2007-06-25
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO287R-1 | DASNY - NEW STATEN ISLAND SUPREME COURT | 4 | BID AWARD AND REGISTER CONTRCT | 2007-06-26 | 2007-09-23 | 2007-06-26 | 2007-09-23
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO287R-1 | DASNY - NEW STATEN ISLAND SUPREME COURT | 5 | CONSTRUCTION TO 25% | 2007-09-24 | 2009-01-15 | 2007-09-24 | 2009-01-15
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO287R-1 | DASNY - NEW STATEN ISLAND SUPREME COURT | 6 | CONSTRUCTION TO 50% | 2009-01-16 | 2010-05-10 | 2009-01-16 | 2010-05-10
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO287R-1 | DASNY - NEW STATEN ISLAND SUPREME COURT | 7 | CONSTRUCTION TO 75% | 2010-05-11 | 2011-05-05 | 2010-05-11 | 2011-05-05
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO287R-1 | DASNY - NEW STATEN ISLAND SUPREME COURT | 8 | ORIGINAL EQUIP & FURNISHING | 2011-05-06 | 2011-08-03 | 2011-05-06 | 2022-06-30
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO287R-1 | DASNY - NEW STATEN ISLAND SUPREME COURT | 9 | SUBSTANTIAL COMPLETION | 2011-08-04 | 2011-11-01 | 2022-07-01 | 2022-09-28
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO287R-1 | DASNY - NEW STATEN ISLAND SUPREME COURT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2011-11-02 | 2011-12-01 | 2022-09-29 | 2022-10-28
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO301FA | 130 STUYVESANT PL.- FIRE ALARM/SPRINKLER | 1 | DEVELOP SCOPE | 2016-03-01 | 2016-05-29 | 2022-06-01 | 2022-08-29
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO301FA | 130 STUYVESANT PL.- FIRE ALARM/SPRINKLER | 2 | PRELIMINARY DESIGN | 2016-05-30 | 2016-09-26 | 2022-08-30 | 2022-12-27
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO301FA | 130 STUYVESANT PL.- FIRE ALARM/SPRINKLER | 3 | FINAL DESIGN | 2016-09-27 | 2017-03-25 | 2022-12-28 | 2023-06-25
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO301FA | 130 STUYVESANT PL.- FIRE ALARM/SPRINKLER | 4 | BID AWARD AND REGISTER CONTRCT | 2017-03-26 | 2017-06-23 | 2023-06-26 | 2023-09-23
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO301FA | 130 STUYVESANT PL.- FIRE ALARM/SPRINKLER | 5 | CONSTRUCTION TO 25% | 2017-06-24 | 2017-10-21 | 2023-09-24 | 2024-01-21
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO301FA | 130 STUYVESANT PL.- FIRE ALARM/SPRINKLER | 6 | CONSTRUCTION TO 50% | 2017-10-22 | 2018-02-18 | 2024-01-22 | 2024-05-20
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO301FA | 130 STUYVESANT PL.- FIRE ALARM/SPRINKLER | 7 | CONSTRUCTION TO 75% | 2018-02-19 | 2018-06-18 | 2024-05-21 | 2024-09-17
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO301FA | 130 STUYVESANT PL.- FIRE ALARM/SPRINKLER | 8 | ORIGINAL EQUIP & FURNISHING | 2018-06-19 | 2018-09-16 | 2024-09-18 | 2024-12-16
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO301FA | 130 STUYVESANT PL.- FIRE ALARM/SPRINKLER | 9 | SUBSTANTIAL COMPLETION | 2018-09-17 | 2018-11-15 | 2024-12-17 | 2025-02-14
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO301FA | 130 STUYVESANT PL.- FIRE ALARM/SPRINKLER | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-11-16 | 2018-12-15 | 2025-02-15 | 2025-03-16
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO301HV1 | 130 STUYVESANT PL.- CHILLER AND BOILER | 1 | DEVELOP SCOPE | 2022-06-01 | 2022-08-29 | 2022-06-01 | 2022-08-29
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO301HV1 | 130 STUYVESANT PL.- CHILLER AND BOILER | 2 | PRELIMINARY DESIGN | 2022-08-30 | 2022-12-27 | 2022-08-30 | 2022-12-27
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO301HV1 | 130 STUYVESANT PL.- CHILLER AND BOILER | 3 | FINAL DESIGN | 2022-12-28 | 2023-06-25 | 2022-12-28 | 2023-06-25
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO301HV1 | 130 STUYVESANT PL.- CHILLER AND BOILER | 4 | BID AWARD AND REGISTER CONTRCT | 2023-06-26 | 2023-09-23 | 2023-06-26 | 2023-09-23
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO301HV1 | 130 STUYVESANT PL.- CHILLER AND BOILER | 5 | CONSTRUCTION TO 25% | 2023-09-24 | 2024-01-21 | 2023-09-24 | 2024-01-21
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO301HV1 | 130 STUYVESANT PL.- CHILLER AND BOILER | 6 | CONSTRUCTION TO 50% | 2024-01-22 | 2024-05-20 | 2024-01-22 | 2024-05-20
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO301HV1 | 130 STUYVESANT PL.- CHILLER AND BOILER | 7 | CONSTRUCTION TO 75% | 2024-05-21 | 2024-09-17 | 2024-05-21 | 2024-09-17
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO301HV1 | 130 STUYVESANT PL.- CHILLER AND BOILER | 8 | ORIGINAL EQUIP & FURNISHING | 2024-09-18 | 2024-12-16 | 2024-09-18 | 2024-12-16
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO301HV1 | 130 STUYVESANT PL.- CHILLER AND BOILER | 9 | SUBSTANTIAL COMPLETION | 2024-12-17 | 2025-02-14 | 2024-12-17 | 2025-02-14
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO301HV1 | 130 STUYVESANT PL.- CHILLER AND BOILER | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-02-15 | 2026-03-16 | 2025-02-15 | 2026-03-16
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0035 | DPR-Greenbelt Recreation Center | 2 | BID AWARD AND REGISTER CONTRCT | 2019-07-01 | 2019-08-29 | 2019-07-01 | 2019-08-29
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0035 | DPR-Greenbelt Recreation Center | 3 | CONSTRUCTION TO 50% | 2019-08-30 | 2020-02-25 | 2019-08-30 | 2020-02-25
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0035 | DPR-Greenbelt Recreation Center | 4 | CONSTRUCTION TO 75% | 2020-02-26 | 2020-05-25 | 2020-02-26 | 2020-05-25
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0035 | DPR-Greenbelt Recreation Center | 5 | SUBSTANTIAL COMPLETION | 2020-05-26 | 2020-07-24 | 2020-05-26 | 2020-07-24
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0035 | DPR-Greenbelt Recreation Center | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-07-25 | 2020-08-23 | 2020-07-25 | 2020-08-23
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0072 | NYPD - 123RD PRECINCT | 1 | DEVELOP SCOPE | 2020-02-01 | 2020-03-01 | 2022-06-01 | 2022-06-30
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0072 | NYPD - 123RD PRECINCT | 2 | BID AWARD AND REGISTER CONTRCT | 2020-03-02 | 2020-04-30 | 2022-07-01 | 2022-08-29
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0072 | NYPD - 123RD PRECINCT | 3 | CONSTRUCTION TO 50% | 2020-05-01 | 2020-10-27 | 2022-08-30 | 2023-02-25
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0072 | NYPD - 123RD PRECINCT | 4 | CONSTRUCTION TO 75% | 2020-10-28 | 2021-01-25 | 2023-02-26 | 2023-05-26
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0072 | NYPD - 123RD PRECINCT | 5 | SUBSTANTIAL COMPLETION | 2021-01-26 | 2021-03-26 | 2023-05-27 | 2023-07-25
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0072 | NYPD - 123RD PRECINCT | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-27 | 2021-04-25 | 2023-07-26 | 2023-08-24
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0076 | NYPD - 122ND PRECINCT | 1 | DEVELOP SCOPE | 2020-02-15 | 2020-03-15 | 2022-06-01 | 2022-06-30
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0076 | NYPD - 122ND PRECINCT | 2 | BID AWARD AND REGISTER CONTRCT | 2020-03-16 | 2020-05-14 | 2022-07-01 | 2022-08-29
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0076 | NYPD - 122ND PRECINCT | 3 | CONSTRUCTION TO 50% | 2020-05-15 | 2020-11-10 | 2022-08-30 | 2023-02-25
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0076 | NYPD - 122ND PRECINCT | 4 | CONSTRUCTION TO 75% | 2020-11-11 | 2021-02-08 | 2023-02-26 | 2023-05-26
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0076 | NYPD - 122ND PRECINCT | 5 | SUBSTANTIAL COMPLETION | 2021-02-09 | 2021-04-09 | 2023-05-27 | 2023-07-25
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0076 | NYPD - 122ND PRECINCT | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-04-10 | 2021-05-09 | 2023-07-26 | 2023-08-24
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW29310R | 10 RICHMOND TERRACE - FIRE ALARM | 1 | DEVELOP SCOPE | 2019-06-27 | 2019-09-24 | 2019-06-27 | 2019-09-24
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW29310R | 10 RICHMOND TERRACE - FIRE ALARM | 2 | PRELIMINARY DESIGN | 2019-09-25 | 2020-01-22 | 2019-09-25 | 2020-01-22
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW29310R | 10 RICHMOND TERRACE - FIRE ALARM | 3 | FINAL DESIGN | 2020-01-23 | 2020-07-20 | 2020-01-23 | 2020-07-20
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW29310R | 10 RICHMOND TERRACE - FIRE ALARM | 4 | BID AWARD AND REGISTER CONTRCT | 2022-06-01 | 2022-08-29 | 2022-06-01 | 2022-08-29
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW29310R | 10 RICHMOND TERRACE - FIRE ALARM | 5 | CONSTRUCTION TO 25% | 2022-08-30 | 2022-12-27 | 2022-08-30 | 2022-12-27
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW29310R | 10 RICHMOND TERRACE - FIRE ALARM | 6 | CONSTRUCTION TO 50% | 2022-12-28 | 2023-04-26 | 2022-12-28 | 2023-04-26
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW29310R | 10 RICHMOND TERRACE - FIRE ALARM | 7 | CONSTRUCTION TO 75% | 2023-04-27 | 2023-08-24 | 2023-04-27 | 2023-08-24
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW29310R | 10 RICHMOND TERRACE - FIRE ALARM | 8 | ORIGINAL EQUIP & FURNISHING | 2023-08-25 | 2023-11-22 | 2023-08-25 | 2023-11-22
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW29310R | 10 RICHMOND TERRACE - FIRE ALARM | 9 | SUBSTANTIAL COMPLETION | 2023-11-23 | 2024-01-21 | 2023-11-23 | 2024-01-21
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW29310R | 10 RICHMOND TERRACE - FIRE ALARM | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-01-22 | 2024-02-20 | 2024-01-22 | 2024-02-20
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DOFR | DOF - 350 ST. MARK'S PLACE - LEASED SPACE | 1 | DEVELOP SCOPE | 2014-06-01 | 2014-08-29 | 2021-06-01 | 2021-08-29
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DOFR | DOF - 350 ST. MARK'S PLACE - LEASED SPACE | 2 | PRELIMINARY DESIGN | 2014-08-30 | 2014-12-27 | 2021-08-30 | 2021-12-27
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DOFR | DOF - 350 ST. MARK'S PLACE - LEASED SPACE | 3 | FINAL DESIGN | 2014-12-28 | 2015-06-25 | 2021-12-28 | 2022-06-25
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DOFR | DOF - 350 ST. MARK'S PLACE - LEASED SPACE | 4 | BID AWARD AND REGISTER CONTRCT | 2015-06-26 | 2015-09-23 | 2022-06-26 | 2022-09-23
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DOFR | DOF - 350 ST. MARK'S PLACE - LEASED SPACE | 5 | CONSTRUCTION TO 25% | 2015-09-24 | 2016-01-21 | 2022-09-24 | 2023-01-21
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DOFR | DOF - 350 ST. MARK'S PLACE - LEASED SPACE | 6 | CONSTRUCTION TO 50% | 2016-01-22 | 2016-05-20 | 2023-01-22 | 2023-05-21
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DOFR | DOF - 350 ST. MARK'S PLACE - LEASED SPACE | 7 | CONSTRUCTION TO 75% | 2016-05-21 | 2016-09-17 | 2023-05-22 | 2023-09-18
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DOFR | DOF - 350 ST. MARK'S PLACE - LEASED SPACE | 8 | ORIGINAL EQUIP & FURNISHING | 2016-09-18 | 2016-12-16 | 2023-09-19 | 2023-12-17
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DOFR | DOF - 350 ST. MARK'S PLACE - LEASED SPACE | 9 | SUBSTANTIAL COMPLETION | 2016-12-17 | 2017-02-14 | 2023-12-18 | 2024-02-15
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DOFR | DOF - 350 ST. MARK'S PLACE - LEASED SPACE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-02-15 | 2017-03-16 | 2024-02-16 | 2024-03-16
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RAR | LAW DEPT - RAISE THE AGE -SI | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-08-29 | 2020-06-01 | 2020-08-29
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RAR | LAW DEPT - RAISE THE AGE -SI | 2 | PRELIMINARY DESIGN | 2020-08-30 | 2020-12-27 | 2020-08-30 | 2020-12-27
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RAR | LAW DEPT - RAISE THE AGE -SI | 3 | FINAL DESIGN | 2020-12-28 | 2021-06-25 | 2020-12-28 | 2021-06-25
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RAR | LAW DEPT - RAISE THE AGE -SI | 4 | BID AWARD AND REGISTER CONTRCT | 2021-06-26 | 2021-09-23 | 2021-06-26 | 2021-09-23
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RAR | LAW DEPT - RAISE THE AGE -SI | 5 | CONSTRUCTION TO 25% | 2021-09-24 | 2022-01-21 | 2021-09-24 | 2022-01-21
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RAR | LAW DEPT - RAISE THE AGE -SI | 6 | CONSTRUCTION TO 50% | 2022-01-22 | 2022-05-21 | 2022-01-22 | 2022-05-21
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RAR | LAW DEPT - RAISE THE AGE -SI | 7 | CONSTRUCTION TO 75% | 2022-05-22 | 2022-09-18 | 2022-05-22 | 2022-09-18
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RAR | LAW DEPT - RAISE THE AGE -SI | 8 | ORIGINAL EQUIP & FURNISHING | 2022-09-19 | 2022-12-17 | 2022-09-19 | 2022-12-17
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RAR | LAW DEPT - RAISE THE AGE -SI | 9 | SUBSTANTIAL COMPLETION | 2022-12-18 | 2023-02-15 | 2022-12-18 | 2023-02-15
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RAR | LAW DEPT - RAISE THE AGE -SI | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-02-16 | 2023-03-17 | 2023-02-16 | 2023-03-17
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RHP | OCA RELOCATION FROM HOMEPORT - STATEN ISLAND | 1 | DEVELOP SCOPE | 2002-06-30 | 2002-09-27 | 2008-06-01 | 2008-08-29
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RHP | OCA RELOCATION FROM HOMEPORT - STATEN ISLAND | 2 | PRELIMINARY DESIGN | 2006-09-28 | 2006-10-31 | 2006-09-28 | 2006-10-31
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RHP | OCA RELOCATION FROM HOMEPORT - STATEN ISLAND | 3 | FINAL DESIGN | 2006-11-01 | 2007-01-31 | 2006-11-01 | 2007-01-31
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RHP | OCA RELOCATION FROM HOMEPORT - STATEN ISLAND | 4 | BID AWARD AND REGISTER CONTRCT | 2007-02-01 | 2007-03-31 | 2007-02-01 | 2007-03-31
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RHP | OCA RELOCATION FROM HOMEPORT - STATEN ISLAND | 5 | CONSTRUCTION TO 25% | 2007-02-01 | 2007-04-30 | 2007-02-01 | 2007-04-30
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RHP | OCA RELOCATION FROM HOMEPORT - STATEN ISLAND | 6 | CONSTRUCTION TO 50% | 2007-05-01 | 2007-06-30 | 2007-05-01 | 2007-06-30
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RHP | OCA RELOCATION FROM HOMEPORT - STATEN ISLAND | 7 | CONSTRUCTION TO 75% | 2007-07-01 | 2007-07-31 | 2007-07-01 | 2007-07-31
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RHP | OCA RELOCATION FROM HOMEPORT - STATEN ISLAND | 8 | ORIGINAL EQUIP & FURNISHING | 2007-08-01 | 2007-07-31 | 2007-08-01 | 2010-03-17
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RHP | OCA RELOCATION FROM HOMEPORT - STATEN ISLAND | 9 | SUBSTANTIAL COMPLETION | 2007-08-01 | 2007-09-30 | 2010-03-18 | 2011-07-10
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RHP | OCA RELOCATION FROM HOMEPORT - STATEN ISLAND | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2007-10-01 | 2007-12-31 | 2011-07-11 | 2023-06-30
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77501BL | 10 RICHMOND TERR.- BOILER REPLACEMENT | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-08-29 | 2020-06-01 | 2020-08-29
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77501BL | 10 RICHMOND TERR.- BOILER REPLACEMENT | 2 | PRELIMINARY DESIGN | 2020-08-30 | 2020-12-27 | 2020-08-30 | 2020-12-27
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77501BL | 10 RICHMOND TERR.- BOILER REPLACEMENT | 3 | FINAL DESIGN | 2020-12-28 | 2021-06-25 | 2020-12-28 | 2021-06-25
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77501BL | 10 RICHMOND TERR.- BOILER REPLACEMENT | 4 | BID AWARD AND REGISTER CONTRCT | 2021-06-26 | 2021-09-23 | 2021-06-26 | 2021-09-23
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77501BL | 10 RICHMOND TERR.- BOILER REPLACEMENT | 5 | CONSTRUCTION TO 25% | 2021-09-24 | 2022-01-21 | 2021-09-24 | 2022-01-21
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77501BL | 10 RICHMOND TERR.- BOILER REPLACEMENT | 6 | CONSTRUCTION TO 50% | 2022-01-22 | 2022-05-21 | 2022-01-22 | 2022-05-21
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77501BL | 10 RICHMOND TERR.- BOILER REPLACEMENT | 7 | CONSTRUCTION TO 75% | 2022-05-22 | 2022-09-18 | 2022-05-22 | 2022-09-18
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77501BL | 10 RICHMOND TERR.- BOILER REPLACEMENT | 8 | ORIGINAL EQUIP & FURNISHING | 2022-09-19 | 2022-12-17 | 2022-09-19 | 2022-12-17
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77501BL | 10 RICHMOND TERR.- BOILER REPLACEMENT | 9 | SUBSTANTIAL COMPLETION | 2022-12-18 | 2023-02-15 | 2022-12-18 | 2023-02-15
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77501BL | 10 RICHMOND TERR.- BOILER REPLACEMENT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-02-16 | 2023-03-17 | 2023-02-16 | 2023-03-17
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77501DB | 10 RICHMOND TERRACE - 2nd & 3rd FLs DOB RENOVATION | 1 | DEVELOP SCOPE | 2021-06-01 | 2021-08-29 | 2021-06-01 | 2021-08-29
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77501DB | 10 RICHMOND TERRACE - 2nd & 3rd FLs DOB RENOVATION | 2 | PRELIMINARY DESIGN | 2021-08-30 | 2021-12-27 | 2021-08-30 | 2021-12-27
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77501DB | 10 RICHMOND TERRACE - 2nd & 3rd FLs DOB RENOVATION | 3 | FINAL DESIGN | 2021-12-28 | 2022-06-25 | 2021-12-28 | 2022-06-25
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77501DB | 10 RICHMOND TERRACE - 2nd & 3rd FLs DOB RENOVATION | 4 | BID AWARD AND REGISTER CONTRCT | 2022-06-26 | 2022-09-23 | 2022-06-26 | 2022-09-23
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77501DB | 10 RICHMOND TERRACE - 2nd & 3rd FLs DOB RENOVATION | 5 | CONSTRUCTION TO 25% | 2022-09-24 | 2023-01-21 | 2022-09-24 | 2023-01-21
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77501DB | 10 RICHMOND TERRACE - 2nd & 3rd FLs DOB RENOVATION | 6 | CONSTRUCTION TO 50% | 2023-01-22 | 2023-05-21 | 2023-01-22 | 2023-05-21
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77501DB | 10 RICHMOND TERRACE - 2nd & 3rd FLs DOB RENOVATION | 7 | CONSTRUCTION TO 75% | 2023-05-22 | 2023-09-18 | 2023-05-22 | 2023-09-18
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77501DB | 10 RICHMOND TERRACE - 2nd & 3rd FLs DOB RENOVATION | 8 | ORIGINAL EQUIP & FURNISHING | 2023-09-19 | 2023-12-17 | 2023-09-19 | 2023-12-17
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77501DB | 10 RICHMOND TERRACE - 2nd & 3rd FLs DOB RENOVATION | 9 | SUBSTANTIAL COMPLETION | 2023-12-18 | 2024-02-15 | 2023-12-18 | 2024-02-15
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77501DB | 10 RICHMOND TERRACE - 2nd & 3rd FLs DOB RENOVATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-02-16 | 2024-03-16 | 2024-02-16 | 2024-03-16
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77501EL | 10 RICHMOND TERRACE- ELECTRICAL UPGRADE | 1 | DEVELOP SCOPE | 2010-05-16 | 2010-08-13 | 2010-05-16 | 2010-08-13
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77501EL | 10 RICHMOND TERRACE- ELECTRICAL UPGRADE | 2 | PRELIMINARY DESIGN | 2010-08-14 | 2010-12-11 | 2010-08-14 | 2010-12-11
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77501EL | 10 RICHMOND TERRACE- ELECTRICAL UPGRADE | 3 | FINAL DESIGN | 2010-12-12 | 2011-06-09 | 2010-12-12 | 2011-06-09
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77501EL | 10 RICHMOND TERRACE- ELECTRICAL UPGRADE | 4 | BID AWARD AND REGISTER CONTRCT | 2011-06-10 | 2011-09-07 | 2011-06-10 | 2011-09-07
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77501EL | 10 RICHMOND TERRACE- ELECTRICAL UPGRADE | 5 | CONSTRUCTION TO 25% | 2011-09-08 | 2012-01-05 | 2011-09-08 | 2012-01-05
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77501EL | 10 RICHMOND TERRACE- ELECTRICAL UPGRADE | 6 | CONSTRUCTION TO 50% | 2012-01-06 | 2012-05-04 | 2012-01-06 | 2012-05-04
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77501EL | 10 RICHMOND TERRACE- ELECTRICAL UPGRADE | 7 | CONSTRUCTION TO 75% | 2012-05-05 | 2012-09-01 | 2012-05-05 | 2012-09-01
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77501EL | 10 RICHMOND TERRACE- ELECTRICAL UPGRADE | 8 | ORIGINAL EQUIP & FURNISHING | 2012-09-02 | 2012-11-30 | 2012-09-02 | 2012-11-30
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77501EL | 10 RICHMOND TERRACE- ELECTRICAL UPGRADE | 9 | SUBSTANTIAL COMPLETION | 2012-12-01 | 2013-01-29 | 2012-12-01 | 2013-01-29
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77501EL | 10 RICHMOND TERRACE- ELECTRICAL UPGRADE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-01-30 | 2013-02-28 | 2013-01-30 | 2023-06-30
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SEC3 | 130 STUYVESANT PLACE- SECURITY BARRIER SI DA | 1 | DEVELOP SCOPE | 2011-06-01 | 2011-08-29 | 2022-06-01 | 2022-08-29
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SEC3 | 130 STUYVESANT PLACE- SECURITY BARRIER SI DA | 2 | PRELIMINARY DESIGN | 2011-08-30 | 2011-12-27 | 2022-08-30 | 2022-12-27
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SEC3 | 130 STUYVESANT PLACE- SECURITY BARRIER SI DA | 3 | FINAL DESIGN | 2011-12-28 | 2012-06-24 | 2022-12-28 | 2023-06-25
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SEC3 | 130 STUYVESANT PLACE- SECURITY BARRIER SI DA | 4 | BID AWARD AND REGISTER CONTRCT | 2012-06-25 | 2012-09-22 | 2023-06-26 | 2023-09-23
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SEC3 | 130 STUYVESANT PLACE- SECURITY BARRIER SI DA | 5 | CONSTRUCTION TO 25% | 2012-09-23 | 2013-01-20 | 2022-06-01 | 2022-09-28
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SEC3 | 130 STUYVESANT PLACE- SECURITY BARRIER SI DA | 6 | CONSTRUCTION TO 50% | 2013-01-21 | 2013-05-20 | 2022-09-29 | 2023-01-26
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SEC3 | 130 STUYVESANT PLACE- SECURITY BARRIER SI DA | 7 | CONSTRUCTION TO 75% | 2013-05-21 | 2013-09-17 | 2023-01-27 | 2023-05-26
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SEC3 | 130 STUYVESANT PLACE- SECURITY BARRIER SI DA | 8 | ORIGINAL EQUIP & FURNISHING | 2013-09-18 | 2013-12-16 | 2023-05-27 | 2023-08-24
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SEC3 | 130 STUYVESANT PLACE- SECURITY BARRIER SI DA | 9 | SUBSTANTIAL COMPLETION | 2013-12-17 | 2014-02-14 | 2023-08-25 | 2023-10-23
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SEC3 | 130 STUYVESANT PLACE- SECURITY BARRIER SI DA | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-02-15 | 2014-03-16 | 2023-10-24 | 2023-11-22
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWR077MUR | 18 RICHMOND TERRACE- STATEN ISLAND COURTHOUSE MURALS | 1 | DEVELOP SCOPE | 2012-09-05 | 2012-10-04 | 2024-06-01 | 2024-06-30
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWR077MUR | 18 RICHMOND TERRACE- STATEN ISLAND COURTHOUSE MURALS | 2 | PRELIMINARY DESIGN | 2012-10-05 | 2012-11-03 | 2024-07-01 | 2024-07-30
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWR077MUR | 18 RICHMOND TERRACE- STATEN ISLAND COURTHOUSE MURALS | 3 | FINAL DESIGN | 2012-11-04 | 2012-12-03 | 2024-07-31 | 2024-08-29
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWR077MUR | 18 RICHMOND TERRACE- STATEN ISLAND COURTHOUSE MURALS | 4 | BID AWARD AND REGISTER CONTRCT | 2012-12-04 | 2013-01-02 | 2024-08-30 | 2024-09-28
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWR077MUR | 18 RICHMOND TERRACE- STATEN ISLAND COURTHOUSE MURALS | 5 | CONSTRUCTION TO 25% | 2013-01-03 | 2013-02-01 | 2024-09-29 | 2024-10-28
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWR077MUR | 18 RICHMOND TERRACE- STATEN ISLAND COURTHOUSE MURALS | 6 | CONSTRUCTION TO 50% | 2013-02-02 | 2013-04-02 | 2024-10-29 | 2024-12-27
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWR077MUR | 18 RICHMOND TERRACE- STATEN ISLAND COURTHOUSE MURALS | 7 | CONSTRUCTION TO 75% | 2013-04-03 | 2013-05-02 | 2024-12-28 | 2025-01-26
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWR077MUR | 18 RICHMOND TERRACE- STATEN ISLAND COURTHOUSE MURALS | 8 | ORIGINAL EQUIP & FURNISHING | 2013-05-03 | 2013-05-12 | 2026-06-01 | 2026-06-10
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWR077MUR | 18 RICHMOND TERRACE- STATEN ISLAND COURTHOUSE MURALS | 9 | SUBSTANTIAL COMPLETION | 2013-05-13 | 2013-05-22 | 2026-06-11 | 2026-06-20
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWR077MUR | 18 RICHMOND TERRACE- STATEN ISLAND COURTHOUSE MURALS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-05-23 | 2013-06-21 | 2026-06-21 | 2026-07-20
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWR77GRGE | ST. GEORGE COURTHOUSE & HYATT STREET PLAZA | 1 | DEVELOP SCOPE | 2015-04-01 | 2015-06-29 | 2024-06-01 | 2024-08-29
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWR77GRGE | ST. GEORGE COURTHOUSE & HYATT STREET PLAZA | 2 | PRELIMINARY DESIGN | 2015-06-30 | 2015-10-27 | 2024-08-30 | 2024-12-27
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWR77GRGE | ST. GEORGE COURTHOUSE & HYATT STREET PLAZA | 3 | FINAL DESIGN | 2015-10-28 | 2016-04-24 | 2024-12-28 | 2025-06-25
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWR77GRGE | ST. GEORGE COURTHOUSE & HYATT STREET PLAZA | 4 | BID AWARD AND REGISTER CONTRCT | 2016-04-25 | 2016-07-23 | 2025-06-26 | 2025-09-23
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWR77GRGE | ST. GEORGE COURTHOUSE & HYATT STREET PLAZA | 5 | CONSTRUCTION TO 25% | 2016-07-24 | 2016-11-20 | 2025-09-24 | 2026-01-21
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWR77GRGE | ST. GEORGE COURTHOUSE & HYATT STREET PLAZA | 6 | CONSTRUCTION TO 50% | 2016-11-21 | 2017-03-20 | 2026-01-22 | 2026-05-21
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWR77GRGE | ST. GEORGE COURTHOUSE & HYATT STREET PLAZA | 7 | CONSTRUCTION TO 75% | 2017-03-21 | 2017-07-18 | 2026-05-22 | 2026-09-18
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWR77GRGE | ST. GEORGE COURTHOUSE & HYATT STREET PLAZA | 8 | ORIGINAL EQUIP & FURNISHING | 2017-07-19 | 2017-10-16 | 2026-09-19 | 2026-12-17
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWR77GRGE | ST. GEORGE COURTHOUSE & HYATT STREET PLAZA | 9 | SUBSTANTIAL COMPLETION | 2017-10-17 | 2017-12-15 | 2026-12-18 | 2027-02-15
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWR77GRGE | ST. GEORGE COURTHOUSE & HYATT STREET PLAZA | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-12-16 | 2018-01-14 | 2027-02-16 | 2027-03-17
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | STGESPLND | ST. GEORGE ESPLANADE | 1 | DEVELOP SCOPE | 2004-06-30 | 2004-09-27 | 2004-06-01 | 2004-08-29
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | STGESPLND | ST. GEORGE ESPLANADE | 2 | PRELIMINARY DESIGN | 2004-09-28 | 2005-01-25 | 2004-08-30 | 2004-12-27
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | STGESPLND | ST. GEORGE ESPLANADE | 3 | FINAL DESIGN | 2005-01-26 | 2005-07-24 | 2004-12-28 | 2005-06-25
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | STGESPLND | ST. GEORGE ESPLANADE | 4 | BID AWARD AND REGISTER CONTRCT | 2005-07-25 | 2005-10-22 | 2005-06-26 | 2005-09-23
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | STGESPLND | ST. GEORGE ESPLANADE | 5 | CONSTRUCTION TO 25% | 2005-10-23 | 2006-02-19 | 2005-09-24 | 2008-05-10
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | STGESPLND | ST. GEORGE ESPLANADE | 6 | CONSTRUCTION TO 50% | 2006-02-20 | 2006-06-19 | 2008-05-11 | 2010-12-26
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | STGESPLND | ST. GEORGE ESPLANADE | 7 | CONSTRUCTION TO 75% | 2006-06-20 | 2006-10-17 | 2022-06-01 | 2024-06-29
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | STGESPLND | ST. GEORGE ESPLANADE | 8 | ORIGINAL EQUIP & FURNISHING | 2006-10-18 | 2007-01-15 | 2024-06-30 | 2024-07-29
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | STGESPLND | ST. GEORGE ESPLANADE | 9 | SUBSTANTIAL COMPLETION | 2007-01-16 | 2007-03-16 | 2024-07-30 | 2024-08-13
20201123 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | STGESPLND | ST. GEORGE ESPLANADE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2007-03-17 | 2007-04-15 | 2024-08-14 | 2024-08-28
20201123 | RICHMOND | 858 | DEPT OF INFO TECH & TELECOMM | DATACENTR | FISA Alternative Data Center | 1 | DEVELOP SCOPE | 2011-07-01 | 2011-09-28 | 2011-07-01 | 2012-06-24
20201123 | RICHMOND | 858 | DEPT OF INFO TECH & TELECOMM | DATACENTR | FISA Alternative Data Center | 2 | PRELIMINARY DESIGN | 2011-09-29 | 2012-01-26 | 2012-06-25 | 2014-01-15
20201123 | RICHMOND | 858 | DEPT OF INFO TECH & TELECOMM | DATACENTR | FISA Alternative Data Center | 3 | FINAL DESIGN | 2012-01-27 | 2012-07-24 | 2014-01-16 | 2015-01-10
20201123 | RICHMOND | 858 | DEPT OF INFO TECH & TELECOMM | DATACENTR | FISA Alternative Data Center | 4 | BID AWARD AND REGISTER CONTRCT | 2012-07-25 | 2012-10-22 | 2015-01-11 | 2016-01-25
20201123 | RICHMOND | 858 | DEPT OF INFO TECH & TELECOMM | DATACENTR | FISA Alternative Data Center | 5 | CONSTRUCTION TO 25% | 2012-10-23 | 2013-02-19 | 2016-01-26 | 2017-04-09
20201123 | RICHMOND | 858 | DEPT OF INFO TECH & TELECOMM | DATACENTR | FISA Alternative Data Center | 6 | CONSTRUCTION TO 50% | 2013-02-20 | 2013-06-19 | 2017-04-10 | 2018-06-23
20201123 | RICHMOND | 858 | DEPT OF INFO TECH & TELECOMM | DATACENTR | FISA Alternative Data Center | 7 | CONSTRUCTION TO 75% | 2013-06-20 | 2013-10-17 | 2018-06-24 | 2019-09-06
20201123 | RICHMOND | 858 | DEPT OF INFO TECH & TELECOMM | DATACENTR | FISA Alternative Data Center | 8 | ORIGINAL EQUIP & FURNISHING | 2013-10-18 | 2014-01-15 | 2019-09-07 | 2021-03-19
20201123 | RICHMOND | 858 | DEPT OF INFO TECH & TELECOMM | DATACENTR | FISA Alternative Data Center | 9 | SUBSTANTIAL COMPLETION | 2014-01-16 | 2014-03-16 | 2021-03-20 | 2022-05-13
20201123 | RICHMOND | 858 | DEPT OF INFO TECH & TELECOMM | DATACENTR | FISA Alternative Data Center | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-03-17 | 2014-04-15 | 2022-05-14 | 2023-06-17
20201123 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LN18ALRFW | Allerton - New Roof and Windows | 1 | DEVELOP SCOPE | 2021-07-01 | 2021-09-28 | 2024-07-01 | 2024-09-28
20201123 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LN18ALRFW | Allerton - New Roof and Windows | 2 | DESIGN | 2021-09-29 | 2022-09-28 | 2024-09-29 | 2025-09-28
20201123 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LN18ALRFW | Allerton - New Roof and Windows | 3 | BID/ REGISTER CONTRACT | 2022-09-29 | 2023-06-25 | 2025-09-29 | 2026-06-25
20201123 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LN18ALRFW | Allerton - New Roof and Windows | 4 | CONSTRUCTION | 2023-06-26 | 2024-06-24 | 2026-06-26 | 2027-06-25
20201123 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LN18ALRFW | Allerton - New Roof and Windows | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-06-25 | 2025-06-24 | 2027-06-26 | 2028-06-24
20201123 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LN18BEADA | BELMONT- ADA-compliant Restrooms | 1 | DEVELOP SCOPE | 2021-07-01 | 2021-09-28 | 2022-07-01 | 2022-09-28
20201123 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LN18BEADA | BELMONT- ADA-compliant Restrooms | 2 | DESIGN | 2021-09-29 | 2022-09-28 | 2022-09-29 | 2023-09-28
20201123 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LN18BEADA | BELMONT- ADA-compliant Restrooms | 3 | BID/ REGISTER CONTRACT | 2022-09-29 | 2023-06-25 | 2023-09-29 | 2024-06-24
20201123 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LN18BEADA | BELMONT- ADA-compliant Restrooms | 4 | CONSTRUCTION | 2023-06-26 | 2024-06-24 | 2024-06-25 | 2025-06-24
20201123 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LN18BEADA | BELMONT- ADA-compliant Restrooms | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-06-25 | 2025-06-24 | 2025-06-25 | 2026-06-24
20201123 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LN18CPBOI | CLASON'S POINT - New Boiler | 1 | DEVELOP SCOPE | 2024-07-01 | 2024-09-28 | 2024-07-01 | 2024-09-28
20201123 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LN18CPBOI | CLASON'S POINT - New Boiler | 2 | DESIGN | 2024-09-29 | 2025-09-28 | 2024-09-29 | 2025-09-28
20201123 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LN18CPBOI | CLASON'S POINT - New Boiler | 3 | BID/ REGISTER CONTRACT | 2025-09-29 | 2026-06-25 | 2025-09-29 | 2026-06-25
20201123 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LN18CPBOI | CLASON'S POINT - New Boiler | 4 | CONSTRUCTION | 2026-06-26 | 2027-06-25 | 2026-06-26 | 2027-06-25
20201123 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LN18CPBOI | CLASON'S POINT - New Boiler | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2027-06-26 | 2028-06-24 | 2027-06-26 | 2028-06-24
20201123 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LN18DYBHV | SPUYTEN DUYVIL - Boiler and HVAC Replacement | 1 | DEVELOP SCOPE | 2022-07-01 | 2022-09-28 | 2022-07-01 | 2022-09-28
20201123 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LN18DYBHV | SPUYTEN DUYVIL - Boiler and HVAC Replacement | 2 | DESIGN | 2022-09-29 | 2023-09-28 | 2022-09-29 | 2023-09-28
20201123 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LN18DYBHV | SPUYTEN DUYVIL - Boiler and HVAC Replacement | 3 | BID/ REGISTER CONTRACT | 2023-09-29 | 2024-06-24 | 2023-09-29 | 2024-06-24
20201123 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LN18DYBHV | SPUYTEN DUYVIL - Boiler and HVAC Replacement | 4 | CONSTRUCTION | 2024-06-25 | 2025-06-24 | 2024-06-25 | 2025-06-24
20201123 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LN18DYBHV | SPUYTEN DUYVIL - Boiler and HVAC Replacement | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-06-25 | 2026-06-24 | 2025-06-25 | 2026-06-24
20201123 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LN18MRBOI | Morrisania - Boiler Replacement | 1 | DEVELOP SCOPE | 2021-07-01 | 2021-09-28 | 2021-06-01 | 2021-08-29
20201123 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LN18MRBOI | Morrisania - Boiler Replacement | 2 | DESIGN | 2021-09-29 | 2022-09-28 | 2021-08-30 | 2022-08-29
20201123 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LN18MRBOI | Morrisania - Boiler Replacement | 3 | BID/ REGISTER CONTRACT | 2022-09-29 | 2023-06-25 | 2022-08-30 | 2023-05-26
20201123 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LN18MRBOI | Morrisania - Boiler Replacement | 4 | CONSTRUCTION | 2023-06-26 | 2024-06-24 | 2023-05-27 | 2024-05-25
20201123 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LN18MRBOI | Morrisania - Boiler Replacement | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-06-25 | 2025-06-24 | 2024-05-26 | 2025-05-25
20201123 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LN18RDADA | Riverdale - ADA-compliant Bathroom Renovation | 1 | DEVELOP SCOPE | 2021-07-01 | 2021-09-28 | 2021-07-01 | 2021-09-28
20201123 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LN18RDADA | Riverdale - ADA-compliant Bathroom Renovation | 2 | DESIGN | 2021-09-29 | 2022-09-28 | 2021-09-29 | 2022-09-28
20201123 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LN18RDADA | Riverdale - ADA-compliant Bathroom Renovation | 3 | BID/ REGISTER CONTRACT | 2022-09-29 | 2023-06-25 | 2022-09-29 | 2023-06-25
20201123 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LN18RDADA | Riverdale - ADA-compliant Bathroom Renovation | 4 | CONSTRUCTION | 2023-06-26 | 2024-06-24 | 2023-06-26 | 2024-06-24
20201123 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LN18RDADA | Riverdale - ADA-compliant Bathroom Renovation | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-06-25 | 2025-06-24 | 2024-06-25 | 2025-06-24
20201123 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LNBEREXRE | Belmont - Exterior Renovation | 1 | DEVELOP SCOPE | 2021-07-01 | 2021-10-28 | 2021-07-01 | 2021-10-28
20201123 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LNBEREXRE | Belmont - Exterior Renovation | 2 | DESIGN | 2021-10-29 | 2022-10-28 | 2021-10-29 | 2022-10-28
20201123 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LNBEREXRE | Belmont - Exterior Renovation | 3 | BID/ REGISTER CONTRACT | 2022-10-29 | 2023-07-25 | 2022-10-29 | 2023-07-25
20201123 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LNBEREXRE | Belmont - Exterior Renovation | 4 | CONSTRUCTION | 2023-07-26 | 2025-01-20 | 2023-07-26 | 2025-01-20
20201123 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LNBEREXRE | Belmont - Exterior Renovation | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-01-21 | 2026-01-20 | 2025-01-21 | 2026-01-20
20201123 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LNBERHVAC | Belmont - HVAC /Mechnical Systems Upgrade | 1 | DEVELOP SCOPE | 2021-07-01 | 2021-09-28 | 2022-07-01 | 2022-09-28
20201123 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LNBERHVAC | Belmont - HVAC /Mechnical Systems Upgrade | 2 | DESIGN | 2021-09-29 | 2022-09-28 | 2022-09-29 | 2023-09-28
20201123 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LNBERHVAC | Belmont - HVAC /Mechnical Systems Upgrade | 3 | BID/ REGISTER CONTRACT | 2022-09-29 | 2023-06-25 | 2023-09-29 | 2024-06-24
20201123 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LNBERHVAC | Belmont - HVAC /Mechnical Systems Upgrade | 4 | CONSTRUCTION | 2023-06-26 | 2024-06-24 | 2024-06-25 | 2025-06-24
20201123 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LNBERHVAC | Belmont - HVAC /Mechnical Systems Upgrade | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-06-25 | 2025-06-24 | 2025-06-25 | 2026-06-24
20201123 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LNCA16SDW | Sedgwick - New Roof | 1 | DEVELOP SCOPE | 2021-07-01 | 2021-09-28 | 2021-07-01 | 2021-09-28
20201123 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LNCA16SDW | Sedgwick - New Roof | 2 | DESIGN | 2021-09-29 | 2022-09-28 | 2021-09-29 | 2022-09-28
20201123 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LNCA16SDW | Sedgwick - New Roof | 3 | BID/ REGISTER CONTRACT | 2022-09-29 | 2023-06-25 | 2022-09-29 | 2023-06-25
20201123 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LNCA16SDW | Sedgwick - New Roof | 4 | CONSTRUCTION | 2023-06-26 | 2024-06-24 | 2023-06-26 | 2024-06-24
20201123 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LNCA16SDW | Sedgwick - New Roof | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-06-25 | 2025-06-24 | 2024-06-25 | 2025-06-24
20201123 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LNCA17PBY | PELHAM BAY - ADA Restrooms, New Roof | 1 | DEVELOP SCOPE | 2021-07-01 | 2021-10-28 | 2021-07-01 | 2021-10-28
20201123 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LNCA17PBY | PELHAM BAY - ADA Restrooms, New Roof | 2 | DESIGN | 2021-10-29 | 2022-10-28 | 2021-10-29 | 2022-10-28
20201123 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LNCA17PBY | PELHAM BAY - ADA Restrooms, New Roof | 3 | BID/ REGISTER CONTRACT | 2022-10-29 | 2023-07-25 | 2022-10-29 | 2023-07-25
20201123 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LNCA17PBY | PELHAM BAY - ADA Restrooms, New Roof | 4 | CONSTRUCTION | 2023-07-26 | 2025-07-24 | 2023-07-26 | 2025-07-24
20201123 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LNCA17PBY | PELHAM BAY - ADA Restrooms, New Roof | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-07-25 | 2026-07-24 | 2025-07-25 | 2026-07-24
20201123 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LNGDEXTRO | Grand Concourse - New Roof, Building Envelope | 1 | DEVELOP SCOPE | 2019-02-01 | 2019-05-31 | 2019-02-01 | 2019-05-31
20201123 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LNGDEXTRO | Grand Concourse - New Roof, Building Envelope | 2 | DESIGN | 2019-06-01 | 2020-05-30 | 2019-06-01 | 2020-05-30
20201123 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LNGDEXTRO | Grand Concourse - New Roof, Building Envelope | 3 | BID/ REGISTER CONTRACT | 2020-05-31 | 2021-02-24 | 2020-05-31 | 2021-02-24
20201123 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LNGDEXTRO | Grand Concourse - New Roof, Building Envelope | 4 | CONSTRUCTION | 2021-02-25 | 2023-02-24 | 2021-02-25 | 2023-02-24
20201123 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LNGDEXTRO | Grand Concourse - New Roof, Building Envelope | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-02-25 | 2024-02-24 | 2023-02-25 | 2024-02-24
20201123 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LNMPADA01 | Morris Park - ADA-compliant Entrance | 1 | DEVELOP SCOPE | 2020-12-01 | 2021-02-28 | 2020-12-01 | 2021-02-28
20201123 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LNMPADA01 | Morris Park - ADA-compliant Entrance | 2 | DESIGN | 2021-03-01 | 2022-02-28 | 2021-03-01 | 2022-02-28
20201123 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LNMPADA01 | Morris Park - ADA-compliant Entrance | 3 | BID/ REGISTER CONTRACT | 2022-03-01 | 2022-11-25 | 2022-03-01 | 2022-11-25
20201123 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LNMPADA01 | Morris Park - ADA-compliant Entrance | 4 | CONSTRUCTION | 2022-11-26 | 2023-11-25 | 2022-11-26 | 2023-11-25
20201123 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LNMPADA01 | Morris Park - ADA-compliant Entrance | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-11-26 | 2024-11-24 | 2023-11-26 | 2024-11-24
20201123 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LNVNADABA | Pelham Pkwy/Van Nest - ADA-compliant Bathroom | 1 | DEVELOP SCOPE | 2021-01-01 | 2021-03-31 | 2021-01-01 | 2021-03-31
20201123 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LNVNADABA | Pelham Pkwy/Van Nest - ADA-compliant Bathroom | 2 | DESIGN | 2021-04-01 | 2022-03-31 | 2021-04-01 | 2022-03-31
20201123 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LNVNADABA | Pelham Pkwy/Van Nest - ADA-compliant Bathroom | 3 | BID/ REGISTER CONTRACT | 2022-04-01 | 2022-12-26 | 2022-04-01 | 2022-12-26
20201123 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LNVNADABA | Pelham Pkwy/Van Nest - ADA-compliant Bathroom | 4 | CONSTRUCTION | 2022-12-27 | 2023-12-26 | 2022-12-27 | 2023-12-26
20201123 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LNVNADABA | Pelham Pkwy/Van Nest - ADA-compliant Bathroom | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-12-27 | 2024-12-25 | 2023-12-27 | 2024-12-25
20201123 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LNXA20WKF | Wakefield - Infrastructure and ADA Upgrades | 1 | DEVELOP SCOPE | 2019-09-01 | 2019-12-29 | 2019-09-01 | 2019-12-29
20201123 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LNXA20WKF | Wakefield - Infrastructure and ADA Upgrades | 2 | DESIGN | 2019-12-30 | 2020-12-28 | 2019-12-30 | 2020-12-28
20201123 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LNXA20WKF | Wakefield - Infrastructure and ADA Upgrades | 3 | BID/ REGISTER CONTRACT | 2020-12-29 | 2021-09-24 | 2020-12-29 | 2021-09-24
20201123 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LNXA20WKF | Wakefield - Infrastructure and ADA Upgrades | 4 | CONSTRUCTION | 2021-09-25 | 2023-03-23 | 2021-09-25 | 2023-03-23
20201123 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LNXA20WKF | Wakefield - Infrastructure and ADA Upgrades | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-03-24 | 2024-03-22 | 2023-03-24 | 2024-03-22
20201123 | BRONX | 042 | CITY UNIVERSITY | ACECUN901 | CUNY - BMS Upgrade at 4 Hostos College Buildings | 1 | DEVELOP SCOPE | 2020-03-15 | 2020-04-13 | 2020-03-15 | 2020-04-13
20201123 | BRONX | 042 | CITY UNIVERSITY | ACECUN901 | CUNY - BMS Upgrade at 4 Hostos College Buildings | 2 | BID AWARD AND REGISTER CONTRCT | 2020-04-14 | 2020-06-12 | 2020-04-14 | 2020-06-12
20201123 | BRONX | 042 | CITY UNIVERSITY | ACECUN901 | CUNY - BMS Upgrade at 4 Hostos College Buildings | 3 | CONSTRUCTION TO 50% | 2020-06-13 | 2020-12-09 | 2020-06-13 | 2020-12-09
20201123 | BRONX | 042 | CITY UNIVERSITY | ACECUN901 | CUNY - BMS Upgrade at 4 Hostos College Buildings | 4 | CONSTRUCTION TO 75% | 2020-12-10 | 2021-03-09 | 2020-12-10 | 2021-03-09
20201123 | BRONX | 042 | CITY UNIVERSITY | ACECUN901 | CUNY - BMS Upgrade at 4 Hostos College Buildings | 5 | SUBSTANTIAL COMPLETION | 2021-03-10 | 2021-05-08 | 2021-03-10 | 2021-05-08
20201123 | BRONX | 042 | CITY UNIVERSITY | ACECUN901 | CUNY - BMS Upgrade at 4 Hostos College Buildings | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-05-09 | 2021-06-07 | 2021-05-09 | 2021-06-07
20201123 | BRONX | 042 | CITY UNIVERSITY | BX001-021 | Roscoe Brown Memorial | 1 | DEVELOP SCOPE | 2021-06-30 | 2021-09-27 | 2021-06-30 | 2021-09-27
20201123 | BRONX | 042 | CITY UNIVERSITY | BX001-021 | Roscoe Brown Memorial | 2 | PRELIMINARY DESIGN | 2021-09-28 | 2022-01-25 | 2021-09-28 | 2022-01-25
20201123 | BRONX | 042 | CITY UNIVERSITY | BX001-021 | Roscoe Brown Memorial | 3 | FINAL DESIGN | 2022-01-26 | 2022-07-24 | 2022-01-26 | 2022-07-24
20201123 | BRONX | 042 | CITY UNIVERSITY | BX001-021 | Roscoe Brown Memorial | 4 | BID AWARD AND REGISTER CONTRCT | 2022-07-25 | 2022-10-22 | 2022-07-25 | 2022-10-22
20201123 | BRONX | 042 | CITY UNIVERSITY | BX001-021 | Roscoe Brown Memorial | 5 | CONSTRUCTION TO 25% | 2022-10-23 | 2023-02-19 | 2022-10-23 | 2023-02-19
20201123 | BRONX | 042 | CITY UNIVERSITY | BX001-021 | Roscoe Brown Memorial | 6 | CONSTRUCTION TO 50% | 2023-02-20 | 2023-06-19 | 2023-02-20 | 2023-06-19
20201123 | BRONX | 042 | CITY UNIVERSITY | BX001-021 | Roscoe Brown Memorial | 7 | CONSTRUCTION TO 75% | 2023-06-20 | 2023-10-17 | 2023-06-20 | 2023-10-17
20201123 | BRONX | 042 | CITY UNIVERSITY | BX001-021 | Roscoe Brown Memorial | 8 | ORIGINAL EQUIP & FURNISHING | 2023-10-18 | 2024-01-15 | 2023-10-18 | 2024-01-15
20201123 | BRONX | 042 | CITY UNIVERSITY | BX001-021 | Roscoe Brown Memorial | 9 | SUBSTANTIAL COMPLETION | 2024-01-16 | 2024-03-15 | 2024-01-16 | 2024-03-15
20201123 | BRONX | 042 | CITY UNIVERSITY | BX001-021 | Roscoe Brown Memorial | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-03-16 | 2024-04-14 | 2024-03-16 | 2024-04-14
20201123 | BRONX | 042 | CITY UNIVERSITY | BX022-009 | Gould Memorial Lib Rotunda Staircase Installation | 1 | DEVELOP SCOPE | 2009-06-01 | 2009-08-29 | 2009-06-01 | 2009-08-29
20201123 | BRONX | 042 | CITY UNIVERSITY | BX022-009 | Gould Memorial Lib Rotunda Staircase Installation | 2 | PRELIMINARY DESIGN | 2009-08-30 | 2009-12-27 | 2009-08-30 | 2009-12-27
20201123 | BRONX | 042 | CITY UNIVERSITY | BX022-009 | Gould Memorial Lib Rotunda Staircase Installation | 3 | FINAL DESIGN | 2009-12-28 | 2010-06-25 | 2009-12-28 | 2010-06-25
20201123 | BRONX | 042 | CITY UNIVERSITY | BX022-009 | Gould Memorial Lib Rotunda Staircase Installation | 4 | BID AWARD AND REGISTER CONTRCT | 2010-06-26 | 2010-09-23 | 2010-06-26 | 2010-09-23
20201123 | BRONX | 042 | CITY UNIVERSITY | BX022-009 | Gould Memorial Lib Rotunda Staircase Installation | 5 | CONSTRUCTION TO 25% | 2010-09-24 | 2011-01-21 | 2010-09-24 | 2011-01-21
20201123 | BRONX | 042 | CITY UNIVERSITY | BX022-009 | Gould Memorial Lib Rotunda Staircase Installation | 6 | CONSTRUCTION TO 50% | 2011-01-22 | 2011-05-21 | 2011-01-22 | 2011-05-21
20201123 | BRONX | 042 | CITY UNIVERSITY | BX022-009 | Gould Memorial Lib Rotunda Staircase Installation | 7 | CONSTRUCTION TO 75% | 2011-05-22 | 2011-09-18 | 2011-05-22 | 2011-09-18
20201123 | BRONX | 042 | CITY UNIVERSITY | BX022-009 | Gould Memorial Lib Rotunda Staircase Installation | 8 | ORIGINAL EQUIP & FURNISHING | 2011-09-19 | 2011-12-17 | 2011-09-19 | 2011-12-17
20201123 | BRONX | 042 | CITY UNIVERSITY | BX022-009 | Gould Memorial Lib Rotunda Staircase Installation | 9 | SUBSTANTIAL COMPLETION | 2011-12-18 | 2012-02-15 | 2011-12-18 | 2012-02-15
20201123 | BRONX | 042 | CITY UNIVERSITY | BX022-009 | Gould Memorial Lib Rotunda Staircase Installation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-02-16 | 2012-03-16 | 2012-02-16 | 2026-02-15
20201123 | BRONX | 042 | CITY UNIVERSITY | BX024-011 | Roof Replacement | 6 | CONSTRUCTION TO 50% | 2013-01-21 | 2013-05-20 | 2013-01-21 | 2013-05-20
20201123 | BRONX | 042 | CITY UNIVERSITY | BX024-011 | Roof Replacement | 7 | CONSTRUCTION TO 75% | 2013-05-21 | 2013-09-17 | 2013-05-21 | 2013-09-17
20201123 | BRONX | 042 | CITY UNIVERSITY | BX024-011 | Roof Replacement | 8 | ORIGINAL EQUIP & FURNISHING | 2013-09-18 | 2013-12-16 | 2013-09-18 | 2013-12-16
20201123 | BRONX | 042 | CITY UNIVERSITY | BX024-011 | Roof Replacement | 9 | SUBSTANTIAL COMPLETION | 2013-12-17 | 2014-02-14 | 2013-12-17 | 2014-02-14
20201123 | BRONX | 042 | CITY UNIVERSITY | BX024-011 | Roof Replacement | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-02-15 | 2014-03-16 | 2014-02-15 | 2022-04-01
20201123 | BRONX | 042 | CITY UNIVERSITY | BX024-019 | Gould Memorial Library Reconstruction | 1 | DEVELOP SCOPE | 2018-06-30 | 2018-09-27 | 2020-07-01 | 2020-10-01
20201123 | BRONX | 042 | CITY UNIVERSITY | BX024-019 | Gould Memorial Library Reconstruction | 2 | PRELIMINARY DESIGN | 2018-09-28 | 2019-01-25 | 2020-10-02 | 2021-01-29
20201123 | BRONX | 042 | CITY UNIVERSITY | BX024-019 | Gould Memorial Library Reconstruction | 3 | FINAL DESIGN | 2019-01-26 | 2019-07-24 | 2021-01-30 | 2021-07-28
20201123 | BRONX | 042 | CITY UNIVERSITY | BX024-019 | Gould Memorial Library Reconstruction | 4 | BID AWARD AND REGISTER CONTRCT | 2019-07-25 | 2019-10-22 | 2021-07-29 | 2021-10-26
20201123 | BRONX | 042 | CITY UNIVERSITY | BX024-019 | Gould Memorial Library Reconstruction | 5 | CONSTRUCTION TO 25% | 2019-10-23 | 2020-02-19 | 2021-10-27 | 2022-02-23
20201123 | BRONX | 042 | CITY UNIVERSITY | BX024-019 | Gould Memorial Library Reconstruction | 6 | CONSTRUCTION TO 50% | 2020-02-20 | 2020-06-18 | 2022-02-24 | 2022-06-23
20201123 | BRONX | 042 | CITY UNIVERSITY | BX024-019 | Gould Memorial Library Reconstruction | 7 | CONSTRUCTION TO 75% | 2020-06-19 | 2020-10-16 | 2022-06-24 | 2022-10-21
20201123 | BRONX | 042 | CITY UNIVERSITY | BX024-019 | Gould Memorial Library Reconstruction | 8 | ORIGINAL EQUIP & FURNISHING | 2020-10-17 | 2021-01-14 | 2022-10-22 | 2023-01-19
20201123 | BRONX | 042 | CITY UNIVERSITY | BX024-019 | Gould Memorial Library Reconstruction | 9 | SUBSTANTIAL COMPLETION | 2021-01-15 | 2021-03-15 | 2023-01-20 | 2023-03-20
20201123 | BRONX | 042 | CITY UNIVERSITY | BX024-019 | Gould Memorial Library Reconstruction | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-16 | 2021-04-14 | 2023-03-21 | 2025-04-19
20201123 | BRONX | 042 | CITY UNIVERSITY | BX026-013 | ADA Entrance Ramps | 1 | DEVELOP SCOPE | 2013-06-01 | 2013-08-29 | 2013-06-01 | 2013-08-29
20201123 | BRONX | 042 | CITY UNIVERSITY | BX026-013 | ADA Entrance Ramps | 2 | PRELIMINARY DESIGN | 2013-08-30 | 2013-12-27 | 2013-08-30 | 2013-12-27
20201123 | BRONX | 042 | CITY UNIVERSITY | BX026-013 | ADA Entrance Ramps | 3 | FINAL DESIGN | 2013-12-28 | 2014-06-25 | 2013-12-28 | 2014-06-25
20201123 | BRONX | 042 | CITY UNIVERSITY | BX026-013 | ADA Entrance Ramps | 4 | BID AWARD AND REGISTER CONTRCT | 2014-06-26 | 2014-09-23 | 2014-06-26 | 2014-09-23
20201123 | BRONX | 042 | CITY UNIVERSITY | BX026-013 | ADA Entrance Ramps | 5 | CONSTRUCTION TO 25% | 2014-09-24 | 2015-01-21 | 2014-09-24 | 2015-01-21
20201123 | BRONX | 042 | CITY UNIVERSITY | BX026-013 | ADA Entrance Ramps | 6 | CONSTRUCTION TO 50% | 2015-01-22 | 2015-05-21 | 2015-01-22 | 2015-05-21
20201123 | BRONX | 042 | CITY UNIVERSITY | BX026-013 | ADA Entrance Ramps | 7 | CONSTRUCTION TO 75% | 2015-05-22 | 2015-09-18 | 2015-05-22 | 2015-09-18
20201123 | BRONX | 042 | CITY UNIVERSITY | BX026-013 | ADA Entrance Ramps | 8 | ORIGINAL EQUIP & FURNISHING | 2015-09-19 | 2015-12-17 | 2015-09-19 | 2015-12-17
20201123 | BRONX | 042 | CITY UNIVERSITY | BX026-013 | ADA Entrance Ramps | 9 | SUBSTANTIAL COMPLETION | 2015-12-18 | 2016-02-15 | 2015-12-18 | 2016-02-15
20201123 | BRONX | 042 | CITY UNIVERSITY | BX026-013 | ADA Entrance Ramps | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-02-16 | 2016-03-16 | 2016-02-16 | 2027-03-31
20201123 | BRONX | 042 | CITY UNIVERSITY | BX027-015 | Ohio Track & Field Restoration | 1 | DEVELOP SCOPE | 2015-03-01 | 2015-05-29 | 2015-03-01 | 2015-05-29
20201123 | BRONX | 042 | CITY UNIVERSITY | BX027-015 | Ohio Track & Field Restoration | 2 | PRELIMINARY DESIGN | 2015-05-30 | 2015-09-26 | 2015-05-30 | 2015-09-26
20201123 | BRONX | 042 | CITY UNIVERSITY | BX027-015 | Ohio Track & Field Restoration | 3 | FINAL DESIGN | 2015-09-27 | 2016-03-24 | 2015-09-27 | 2016-03-24
20201123 | BRONX | 042 | CITY UNIVERSITY | BX027-015 | Ohio Track & Field Restoration | 4 | BID AWARD AND REGISTER CONTRCT | 2016-03-25 | 2016-06-22 | 2016-03-25 | 2016-06-22
20201123 | BRONX | 042 | CITY UNIVERSITY | BX027-015 | Ohio Track & Field Restoration | 5 | CONSTRUCTION TO 25% | 2016-06-23 | 2016-10-20 | 2016-06-23 | 2016-10-20
20201123 | BRONX | 042 | CITY UNIVERSITY | BX027-015 | Ohio Track & Field Restoration | 6 | CONSTRUCTION TO 50% | 2016-10-21 | 2017-02-17 | 2016-10-21 | 2017-02-17
20201123 | BRONX | 042 | CITY UNIVERSITY | BX027-015 | Ohio Track & Field Restoration | 7 | CONSTRUCTION TO 75% | 2017-02-18 | 2017-06-17 | 2017-02-18 | 2017-06-17
20201123 | BRONX | 042 | CITY UNIVERSITY | BX027-015 | Ohio Track & Field Restoration | 8 | ORIGINAL EQUIP & FURNISHING | 2017-06-18 | 2017-09-15 | 2017-06-18 | 2017-09-15
20201123 | BRONX | 042 | CITY UNIVERSITY | BX027-015 | Ohio Track & Field Restoration | 9 | SUBSTANTIAL COMPLETION | 2017-09-16 | 2017-11-14 | 2017-09-16 | 2017-11-14
20201123 | BRONX | 042 | CITY UNIVERSITY | BX027-015 | Ohio Track & Field Restoration | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-11-15 | 2017-12-14 | 2017-11-15 | 2023-12-31
20201123 | BRONX | 042 | CITY UNIVERSITY | BX032-015 | Monument Hills Restoration | 1 | DEVELOP SCOPE | 2014-10-01 | 2014-12-29 | 2014-10-01 | 2014-12-29
20201123 | BRONX | 042 | CITY UNIVERSITY | BX032-015 | Monument Hills Restoration | 2 | PRELIMINARY DESIGN | 2014-12-30 | 2015-04-28 | 2014-12-30 | 2015-04-28
20201123 | BRONX | 042 | CITY UNIVERSITY | BX032-015 | Monument Hills Restoration | 3 | FINAL DESIGN | 2015-04-29 | 2015-10-25 | 2015-04-29 | 2015-10-25
20201123 | BRONX | 042 | CITY UNIVERSITY | BX032-015 | Monument Hills Restoration | 4 | BID AWARD AND REGISTER CONTRCT | 2015-10-26 | 2016-01-23 | 2015-10-26 | 2016-01-23
20201123 | BRONX | 042 | CITY UNIVERSITY | BX032-015 | Monument Hills Restoration | 5 | CONSTRUCTION TO 25% | 2016-01-24 | 2016-05-22 | 2016-01-24 | 2016-05-22
20201123 | BRONX | 042 | CITY UNIVERSITY | BX032-015 | Monument Hills Restoration | 6 | CONSTRUCTION TO 50% | 2016-05-23 | 2016-09-19 | 2016-05-23 | 2016-09-19
20201123 | BRONX | 042 | CITY UNIVERSITY | BX032-015 | Monument Hills Restoration | 7 | CONSTRUCTION TO 75% | 2016-09-20 | 2017-01-17 | 2016-09-20 | 2017-01-17
20201123 | BRONX | 042 | CITY UNIVERSITY | BX032-015 | Monument Hills Restoration | 8 | ORIGINAL EQUIP & FURNISHING | 2017-01-18 | 2017-04-17 | 2017-01-18 | 2017-04-17
20201123 | BRONX | 042 | CITY UNIVERSITY | BX032-015 | Monument Hills Restoration | 9 | SUBSTANTIAL COMPLETION | 2017-04-18 | 2017-06-16 | 2017-04-18 | 2017-06-16
20201123 | BRONX | 042 | CITY UNIVERSITY | BX032-015 | Monument Hills Restoration | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-06-17 | 2017-07-16 | 2017-06-17 | 2025-07-31
20201123 | BRONX | 042 | CITY UNIVERSITY | BX034-015 | Bliss Hall ADA Accessibility Improvements | 1 | DEVELOP SCOPE | 2014-10-01 | 2014-12-29 | 2019-07-01 | 2019-10-01
20201123 | BRONX | 042 | CITY UNIVERSITY | BX034-015 | Bliss Hall ADA Accessibility Improvements | 2 | PRELIMINARY DESIGN | 2014-12-30 | 2015-04-28 | 2019-10-02 | 2020-01-29
20201123 | BRONX | 042 | CITY UNIVERSITY | BX034-015 | Bliss Hall ADA Accessibility Improvements | 3 | FINAL DESIGN | 2015-04-29 | 2015-10-25 | 2020-01-30 | 2020-07-27
20201123 | BRONX | 042 | CITY UNIVERSITY | BX034-015 | Bliss Hall ADA Accessibility Improvements | 4 | BID AWARD AND REGISTER CONTRCT | 2015-10-26 | 2016-01-23 | 2020-07-28 | 2020-10-25
20201123 | BRONX | 042 | CITY UNIVERSITY | BX034-015 | Bliss Hall ADA Accessibility Improvements | 5 | CONSTRUCTION TO 25% | 2016-01-24 | 2016-05-22 | 2020-10-26 | 2021-02-22
20201123 | BRONX | 042 | CITY UNIVERSITY | BX034-015 | Bliss Hall ADA Accessibility Improvements | 6 | CONSTRUCTION TO 50% | 2016-05-23 | 2016-09-19 | 2021-02-23 | 2021-06-22
20201123 | BRONX | 042 | CITY UNIVERSITY | BX034-015 | Bliss Hall ADA Accessibility Improvements | 7 | CONSTRUCTION TO 75% | 2016-09-20 | 2017-01-17 | 2021-06-23 | 2021-10-20
20201123 | BRONX | 042 | CITY UNIVERSITY | BX034-015 | Bliss Hall ADA Accessibility Improvements | 8 | ORIGINAL EQUIP & FURNISHING | 2017-01-18 | 2017-04-17 | 2021-10-21 | 2022-01-18
20201123 | BRONX | 042 | CITY UNIVERSITY | BX034-015 | Bliss Hall ADA Accessibility Improvements | 9 | SUBSTANTIAL COMPLETION | 2017-04-18 | 2017-06-16 | 2022-01-19 | 2022-03-19
20201123 | BRONX | 042 | CITY UNIVERSITY | BX034-015 | Bliss Hall ADA Accessibility Improvements | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-06-17 | 2017-07-16 | 2022-03-20 | 2022-07-30
20201123 | BRONX | 042 | CITY UNIVERSITY | BX038-016 | Lowe Hall ADA Accessibility Improvements | 1 | DEVELOP SCOPE | 2015-06-01 | 2015-08-29 | 2019-07-01 | 2019-10-01
20201123 | BRONX | 042 | CITY UNIVERSITY | BX038-016 | Lowe Hall ADA Accessibility Improvements | 2 | PRELIMINARY DESIGN | 2015-08-30 | 2015-12-27 | 2019-10-02 | 2020-01-29
20201123 | BRONX | 042 | CITY UNIVERSITY | BX038-016 | Lowe Hall ADA Accessibility Improvements | 3 | FINAL DESIGN | 2015-12-28 | 2016-06-24 | 2020-01-30 | 2020-07-27
20201123 | BRONX | 042 | CITY UNIVERSITY | BX038-016 | Lowe Hall ADA Accessibility Improvements | 4 | BID AWARD AND REGISTER CONTRCT | 2016-06-25 | 2016-09-22 | 2020-07-28 | 2020-10-25
20201123 | BRONX | 042 | CITY UNIVERSITY | BX038-016 | Lowe Hall ADA Accessibility Improvements | 5 | CONSTRUCTION TO 25% | 2016-09-23 | 2017-01-20 | 2020-10-26 | 2021-02-22
20201123 | BRONX | 042 | CITY UNIVERSITY | BX038-016 | Lowe Hall ADA Accessibility Improvements | 6 | CONSTRUCTION TO 50% | 2017-01-21 | 2017-05-20 | 2021-02-23 | 2021-06-22
20201123 | BRONX | 042 | CITY UNIVERSITY | BX038-016 | Lowe Hall ADA Accessibility Improvements | 7 | CONSTRUCTION TO 75% | 2017-05-21 | 2017-09-17 | 2021-06-23 | 2021-10-20
20201123 | BRONX | 042 | CITY UNIVERSITY | BX038-016 | Lowe Hall ADA Accessibility Improvements | 8 | ORIGINAL EQUIP & FURNISHING | 2017-09-18 | 2017-12-16 | 2021-10-21 | 2022-01-18
20201123 | BRONX | 042 | CITY UNIVERSITY | BX038-016 | Lowe Hall ADA Accessibility Improvements | 9 | SUBSTANTIAL COMPLETION | 2017-12-17 | 2018-02-14 | 2022-01-19 | 2022-03-19
20201123 | BRONX | 042 | CITY UNIVERSITY | BX038-016 | Lowe Hall ADA Accessibility Improvements | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-02-15 | 2018-03-16 | 2022-03-20 | 2026-05-03
20201123 | BRONX | 042 | CITY UNIVERSITY | BX039-016 | Alumni Gym Locker Room Accessibility Improvements | 1 | DEVELOP SCOPE | 2015-06-01 | 2015-08-29 | 2019-07-01 | 2019-09-29
20201123 | BRONX | 042 | CITY UNIVERSITY | BX039-016 | Alumni Gym Locker Room Accessibility Improvements | 2 | PRELIMINARY DESIGN | 2015-08-30 | 2015-12-27 | 2019-09-30 | 2020-01-27
20201123 | BRONX | 042 | CITY UNIVERSITY | BX039-016 | Alumni Gym Locker Room Accessibility Improvements | 3 | FINAL DESIGN | 2015-12-28 | 2016-06-24 | 2020-01-28 | 2020-07-25
20201123 | BRONX | 042 | CITY UNIVERSITY | BX039-016 | Alumni Gym Locker Room Accessibility Improvements | 4 | BID AWARD AND REGISTER CONTRCT | 2016-06-25 | 2016-09-22 | 2020-07-26 | 2020-10-23
20201123 | BRONX | 042 | CITY UNIVERSITY | BX039-016 | Alumni Gym Locker Room Accessibility Improvements | 5 | CONSTRUCTION TO 25% | 2016-09-23 | 2017-01-20 | 2020-10-24 | 2021-02-20
20201123 | BRONX | 042 | CITY UNIVERSITY | BX039-016 | Alumni Gym Locker Room Accessibility Improvements | 6 | CONSTRUCTION TO 50% | 2017-01-21 | 2017-05-20 | 2021-02-21 | 2021-06-20
20201123 | BRONX | 042 | CITY UNIVERSITY | BX039-016 | Alumni Gym Locker Room Accessibility Improvements | 7 | CONSTRUCTION TO 75% | 2017-05-21 | 2017-09-17 | 2021-06-21 | 2021-10-18
20201123 | BRONX | 042 | CITY UNIVERSITY | BX039-016 | Alumni Gym Locker Room Accessibility Improvements | 8 | ORIGINAL EQUIP & FURNISHING | 2017-09-18 | 2017-12-16 | 2021-10-19 | 2022-01-16
20201123 | BRONX | 042 | CITY UNIVERSITY | BX039-016 | Alumni Gym Locker Room Accessibility Improvements | 9 | SUBSTANTIAL COMPLETION | 2017-12-17 | 2018-02-14 | 2022-01-17 | 2022-03-17
20201123 | BRONX | 042 | CITY UNIVERSITY | BX039-016 | Alumni Gym Locker Room Accessibility Improvements | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-02-15 | 2018-03-16 | 2022-03-18 | 2022-04-15
20201123 | BRONX | 042 | CITY UNIVERSITY | BX040-017 | Bronx Express | 1 | DEVELOP SCOPE | 2017-06-30 | 2017-09-27 | 2019-07-01 | 2019-10-01
20201123 | BRONX | 042 | CITY UNIVERSITY | BX040-017 | Bronx Express | 2 | PRELIMINARY DESIGN | 2017-09-28 | 2018-01-25 | 2019-10-02 | 2020-01-29
20201123 | BRONX | 042 | CITY UNIVERSITY | BX040-017 | Bronx Express | 3 | FINAL DESIGN | 2018-01-26 | 2018-07-24 | 2020-01-30 | 2020-07-27
20201123 | BRONX | 042 | CITY UNIVERSITY | BX040-017 | Bronx Express | 4 | BID AWARD AND REGISTER CONTRCT | 2018-07-25 | 2018-10-22 | 2020-07-28 | 2020-10-25
20201123 | BRONX | 042 | CITY UNIVERSITY | BX040-017 | Bronx Express | 5 | CONSTRUCTION TO 25% | 2018-10-23 | 2019-02-19 | 2020-10-26 | 2021-02-22
20201123 | BRONX | 042 | CITY UNIVERSITY | BX040-017 | Bronx Express | 6 | CONSTRUCTION TO 50% | 2019-02-20 | 2019-06-19 | 2021-02-23 | 2021-06-22
20201123 | BRONX | 042 | CITY UNIVERSITY | BX040-017 | Bronx Express | 7 | CONSTRUCTION TO 75% | 2019-06-20 | 2019-10-17 | 2021-06-23 | 2021-10-20
20201123 | BRONX | 042 | CITY UNIVERSITY | BX040-017 | Bronx Express | 8 | ORIGINAL EQUIP & FURNISHING | 2019-10-18 | 2020-01-15 | 2021-10-21 | 2022-01-18
20201123 | BRONX | 042 | CITY UNIVERSITY | BX040-017 | Bronx Express | 9 | SUBSTANTIAL COMPLETION | 2020-01-16 | 2020-03-15 | 2022-01-19 | 2022-03-19
20201123 | BRONX | 042 | CITY UNIVERSITY | BX040-017 | Bronx Express | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-03-16 | 2020-04-14 | 2022-03-20 | 2023-04-18
20201123 | BRONX | 042 | CITY UNIVERSITY | BX041-017 | STEM Resourse Center | 1 | DEVELOP SCOPE | 2017-06-01 | 2017-08-29 | 2017-06-01 | 2017-08-29
20201123 | BRONX | 042 | CITY UNIVERSITY | BX041-017 | STEM Resourse Center | 2 | PRELIMINARY DESIGN | 2017-08-30 | 2017-12-27 | 2017-08-30 | 2017-12-27
20201123 | BRONX | 042 | CITY UNIVERSITY | BX041-017 | STEM Resourse Center | 3 | FINAL DESIGN | 2017-12-28 | 2018-06-25 | 2017-12-28 | 2018-06-25
20201123 | BRONX | 042 | CITY UNIVERSITY | BX041-017 | STEM Resourse Center | 4 | BID AWARD AND REGISTER CONTRCT | 2018-06-26 | 2018-09-23 | 2018-06-26 | 2018-09-23
20201123 | BRONX | 042 | CITY UNIVERSITY | BX041-017 | STEM Resourse Center | 5 | CONSTRUCTION TO 25% | 2018-09-24 | 2019-01-21 | 2018-09-24 | 2019-01-21
20201123 | BRONX | 042 | CITY UNIVERSITY | BX041-017 | STEM Resourse Center | 6 | CONSTRUCTION TO 50% | 2019-01-22 | 2019-05-21 | 2019-01-22 | 2019-05-21
20201123 | BRONX | 042 | CITY UNIVERSITY | BX041-017 | STEM Resourse Center | 7 | CONSTRUCTION TO 75% | 2019-05-22 | 2019-09-18 | 2019-05-22 | 2019-09-18
20201123 | BRONX | 042 | CITY UNIVERSITY | BX041-017 | STEM Resourse Center | 8 | ORIGINAL EQUIP & FURNISHING | 2019-09-19 | 2019-12-17 | 2019-09-19 | 2019-12-17
20201123 | BRONX | 042 | CITY UNIVERSITY | BX041-017 | STEM Resourse Center | 9 | SUBSTANTIAL COMPLETION | 2019-12-18 | 2020-02-15 | 2019-12-18 | 2020-02-15
20201123 | BRONX | 042 | CITY UNIVERSITY | BX041-017 | STEM Resourse Center | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-02-16 | 2020-03-16 | 2020-02-16 | 2026-03-31
20201123 | BRONX | 042 | CITY UNIVERSITY | BX042-018 | Renovate Roscoe Brown Student Center | 1 | DEVELOP SCOPE | 2018-06-01 | 2018-08-29 | 2021-07-01 | 2021-10-01
20201123 | BRONX | 042 | CITY UNIVERSITY | BX042-018 | Renovate Roscoe Brown Student Center | 2 | PRELIMINARY DESIGN | 2018-08-30 | 2018-12-27 | 2021-10-02 | 2022-01-29
20201123 | BRONX | 042 | CITY UNIVERSITY | BX042-018 | Renovate Roscoe Brown Student Center | 3 | FINAL DESIGN | 2018-12-28 | 2019-06-25 | 2022-01-30 | 2022-07-28
20201123 | BRONX | 042 | CITY UNIVERSITY | BX042-018 | Renovate Roscoe Brown Student Center | 4 | BID AWARD AND REGISTER CONTRCT | 2019-06-26 | 2019-09-23 | 2022-07-29 | 2022-10-26
20201123 | BRONX | 042 | CITY UNIVERSITY | BX042-018 | Renovate Roscoe Brown Student Center | 5 | CONSTRUCTION TO 25% | 2019-09-24 | 2020-01-21 | 2022-10-27 | 2023-02-23
20201123 | BRONX | 042 | CITY UNIVERSITY | BX042-018 | Renovate Roscoe Brown Student Center | 6 | CONSTRUCTION TO 50% | 2020-01-22 | 2020-05-20 | 2023-02-24 | 2023-06-23
20201123 | BRONX | 042 | CITY UNIVERSITY | BX042-018 | Renovate Roscoe Brown Student Center | 7 | CONSTRUCTION TO 75% | 2020-05-21 | 2020-09-17 | 2023-06-24 | 2023-10-21
20201123 | BRONX | 042 | CITY UNIVERSITY | BX042-018 | Renovate Roscoe Brown Student Center | 8 | ORIGINAL EQUIP & FURNISHING | 2020-09-18 | 2020-12-16 | 2023-10-22 | 2024-01-19
20201123 | BRONX | 042 | CITY UNIVERSITY | BX042-018 | Renovate Roscoe Brown Student Center | 9 | SUBSTANTIAL COMPLETION | 2020-12-17 | 2021-02-14 | 2024-01-20 | 2024-03-19
20201123 | BRONX | 042 | CITY UNIVERSITY | BX042-018 | Renovate Roscoe Brown Student Center | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-02-15 | 2021-03-16 | 2024-03-20 | 2026-05-03
20201123 | BRONX | 042 | CITY UNIVERSITY | BX044-018 | Community Hall First Floor Renovation | 1 | DEVELOP SCOPE | 2018-06-01 | 2018-08-29 | 2021-07-01 | 2021-10-01
20201123 | BRONX | 042 | CITY UNIVERSITY | BX044-018 | Community Hall First Floor Renovation | 2 | PRELIMINARY DESIGN | 2018-08-30 | 2018-12-27 | 2021-10-02 | 2022-01-29
20201123 | BRONX | 042 | CITY UNIVERSITY | BX044-018 | Community Hall First Floor Renovation | 3 | FINAL DESIGN | 2018-12-28 | 2019-06-25 | 2022-01-30 | 2022-07-28
20201123 | BRONX | 042 | CITY UNIVERSITY | BX044-018 | Community Hall First Floor Renovation | 4 | BID AWARD AND REGISTER CONTRCT | 2019-06-26 | 2019-09-23 | 2022-07-29 | 2022-10-26
20201123 | BRONX | 042 | CITY UNIVERSITY | BX044-018 | Community Hall First Floor Renovation | 5 | CONSTRUCTION TO 25% | 2019-09-24 | 2020-01-21 | 2022-10-27 | 2023-02-23
20201123 | BRONX | 042 | CITY UNIVERSITY | BX044-018 | Community Hall First Floor Renovation | 6 | CONSTRUCTION TO 50% | 2020-01-22 | 2020-05-20 | 2023-02-24 | 2023-06-23
20201123 | BRONX | 042 | CITY UNIVERSITY | BX044-018 | Community Hall First Floor Renovation | 7 | CONSTRUCTION TO 75% | 2020-05-21 | 2020-09-17 | 2023-06-24 | 2023-10-21
20201123 | BRONX | 042 | CITY UNIVERSITY | BX044-018 | Community Hall First Floor Renovation | 8 | ORIGINAL EQUIP & FURNISHING | 2020-09-18 | 2020-12-16 | 2023-10-22 | 2024-01-19
20201123 | BRONX | 042 | CITY UNIVERSITY | BX044-018 | Community Hall First Floor Renovation | 9 | SUBSTANTIAL COMPLETION | 2020-12-17 | 2021-02-14 | 2024-01-20 | 2024-03-19
20201123 | BRONX | 042 | CITY UNIVERSITY | BX044-018 | Community Hall First Floor Renovation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-02-15 | 2021-03-16 | 2024-03-20 | 2026-05-03
20201123 | BRONX | 042 | CITY UNIVERSITY | BX045-018 | ADA Accessibility for Roscoe C Brown Student Center | 1 | DEVELOP SCOPE | 2018-06-01 | 2018-08-29 | 2021-07-01 | 2021-10-01
20201123 | BRONX | 042 | CITY UNIVERSITY | BX045-018 | ADA Accessibility for Roscoe C Brown Student Center | 2 | PRELIMINARY DESIGN | 2018-08-30 | 2018-12-27 | 2021-10-02 | 2022-01-29
20201123 | BRONX | 042 | CITY UNIVERSITY | BX045-018 | ADA Accessibility for Roscoe C Brown Student Center | 3 | FINAL DESIGN | 2018-12-28 | 2019-06-25 | 2022-01-30 | 2022-07-28
20201123 | BRONX | 042 | CITY UNIVERSITY | BX045-018 | ADA Accessibility for Roscoe C Brown Student Center | 4 | BID AWARD AND REGISTER CONTRCT | 2019-06-26 | 2019-09-23 | 2022-07-29 | 2022-10-26
20201123 | BRONX | 042 | CITY UNIVERSITY | BX045-018 | ADA Accessibility for Roscoe C Brown Student Center | 5 | CONSTRUCTION TO 25% | 2019-09-24 | 2020-01-21 | 2022-10-27 | 2023-02-23
20201123 | BRONX | 042 | CITY UNIVERSITY | BX045-018 | ADA Accessibility for Roscoe C Brown Student Center | 6 | CONSTRUCTION TO 50% | 2020-01-22 | 2020-05-20 | 2023-02-24 | 2023-06-23
20201123 | BRONX | 042 | CITY UNIVERSITY | BX045-018 | ADA Accessibility for Roscoe C Brown Student Center | 7 | CONSTRUCTION TO 75% | 2020-05-21 | 2020-09-17 | 2023-06-24 | 2023-10-21
20201123 | BRONX | 042 | CITY UNIVERSITY | BX045-018 | ADA Accessibility for Roscoe C Brown Student Center | 8 | ORIGINAL EQUIP & FURNISHING | 2020-09-18 | 2020-12-16 | 2023-10-22 | 2024-01-19
20201123 | BRONX | 042 | CITY UNIVERSITY | BX045-018 | ADA Accessibility for Roscoe C Brown Student Center | 9 | SUBSTANTIAL COMPLETION | 2020-12-17 | 2021-02-14 | 2024-01-20 | 2024-03-19
20201123 | BRONX | 042 | CITY UNIVERSITY | BX045-018 | ADA Accessibility for Roscoe C Brown Student Center | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-02-15 | 2021-03-16 | 2024-03-20 | 2026-05-03
20201123 | BRONX | 042 | CITY UNIVERSITY | BX046-019 | Alumni Gym HVAC & ADA Improvements | 1 | DEVELOP SCOPE | 2018-06-30 | 2018-09-27 | 2020-07-01 | 2020-10-01
20201123 | BRONX | 042 | CITY UNIVERSITY | BX046-019 | Alumni Gym HVAC & ADA Improvements | 2 | PRELIMINARY DESIGN | 2018-09-28 | 2019-01-25 | 2020-10-02 | 2021-01-29
20201123 | BRONX | 042 | CITY UNIVERSITY | BX046-019 | Alumni Gym HVAC & ADA Improvements | 3 | FINAL DESIGN | 2019-01-26 | 2019-07-24 | 2021-01-30 | 2021-07-28
20201123 | BRONX | 042 | CITY UNIVERSITY | BX046-019 | Alumni Gym HVAC & ADA Improvements | 4 | BID AWARD AND REGISTER CONTRCT | 2019-07-25 | 2019-10-22 | 2021-07-29 | 2021-10-26
20201123 | BRONX | 042 | CITY UNIVERSITY | BX046-019 | Alumni Gym HVAC & ADA Improvements | 5 | CONSTRUCTION TO 25% | 2019-10-23 | 2020-02-19 | 2021-10-27 | 2022-02-23
20201123 | BRONX | 042 | CITY UNIVERSITY | BX046-019 | Alumni Gym HVAC & ADA Improvements | 6 | CONSTRUCTION TO 50% | 2020-02-20 | 2020-06-18 | 2022-02-24 | 2022-06-23
20201123 | BRONX | 042 | CITY UNIVERSITY | BX046-019 | Alumni Gym HVAC & ADA Improvements | 7 | CONSTRUCTION TO 75% | 2020-06-19 | 2020-10-16 | 2022-06-24 | 2022-10-21
20201123 | BRONX | 042 | CITY UNIVERSITY | BX046-019 | Alumni Gym HVAC & ADA Improvements | 8 | ORIGINAL EQUIP & FURNISHING | 2020-10-17 | 2021-01-14 | 2022-10-22 | 2023-01-19
20201123 | BRONX | 042 | CITY UNIVERSITY | BX046-019 | Alumni Gym HVAC & ADA Improvements | 9 | SUBSTANTIAL COMPLETION | 2021-01-15 | 2021-03-15 | 2023-01-20 | 2023-03-20
20201123 | BRONX | 042 | CITY UNIVERSITY | BX046-019 | Alumni Gym HVAC & ADA Improvements | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-16 | 2021-04-14 | 2023-03-21 | 2026-04-19
20201123 | BRONX | 042 | CITY UNIVERSITY | BX047-020 | Ohio Track & Field Upgrade | 1 | DEVELOP SCOPE | 2020-06-30 | 2020-09-27 | 2020-06-30 | 2020-09-27
20201123 | BRONX | 042 | CITY UNIVERSITY | BX047-020 | Ohio Track & Field Upgrade | 2 | PRELIMINARY DESIGN | 2020-09-28 | 2021-01-25 | 2020-09-28 | 2021-01-25
20201123 | BRONX | 042 | CITY UNIVERSITY | BX047-020 | Ohio Track & Field Upgrade | 3 | FINAL DESIGN | 2021-01-26 | 2021-07-24 | 2021-01-26 | 2021-07-24
20201123 | BRONX | 042 | CITY UNIVERSITY | BX047-020 | Ohio Track & Field Upgrade | 4 | BID AWARD AND REGISTER CONTRCT | 2021-07-25 | 2021-10-22 | 2021-07-25 | 2021-10-22
20201123 | BRONX | 042 | CITY UNIVERSITY | BX047-020 | Ohio Track & Field Upgrade | 5 | CONSTRUCTION TO 25% | 2021-10-23 | 2022-02-19 | 2021-10-23 | 2022-02-19
20201123 | BRONX | 042 | CITY UNIVERSITY | BX047-020 | Ohio Track & Field Upgrade | 6 | CONSTRUCTION TO 50% | 2022-02-20 | 2022-06-19 | 2022-02-20 | 2022-06-19
20201123 | BRONX | 042 | CITY UNIVERSITY | BX047-020 | Ohio Track & Field Upgrade | 7 | CONSTRUCTION TO 75% | 2022-06-20 | 2022-10-17 | 2022-06-20 | 2022-10-17
20201123 | BRONX | 042 | CITY UNIVERSITY | BX047-020 | Ohio Track & Field Upgrade | 8 | ORIGINAL EQUIP & FURNISHING | 2022-10-18 | 2023-01-15 | 2022-10-18 | 2023-01-15
20201123 | BRONX | 042 | CITY UNIVERSITY | BX047-020 | Ohio Track & Field Upgrade | 9 | SUBSTANTIAL COMPLETION | 2023-01-16 | 2023-03-16 | 2023-01-16 | 2023-03-16
20201123 | BRONX | 042 | CITY UNIVERSITY | BX047-020 | Ohio Track & Field Upgrade | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-03-17 | 2023-04-15 | 2023-03-17 | 2023-04-15
20201123 | BRONX | 042 | CITY UNIVERSITY | BX048-020 | ELEVATOR UPGRADES | 1 | DEVELOP SCOPE | 2020-06-30 | 2020-09-27 | 2020-06-30 | 2020-09-27
20201123 | BRONX | 042 | CITY UNIVERSITY | BX048-020 | ELEVATOR UPGRADES | 2 | PRELIMINARY DESIGN | 2020-09-28 | 2021-01-25 | 2020-09-28 | 2021-01-25
20201123 | BRONX | 042 | CITY UNIVERSITY | BX048-020 | ELEVATOR UPGRADES | 3 | FINAL DESIGN | 2021-01-26 | 2021-07-24 | 2021-01-26 | 2021-07-24
20201123 | BRONX | 042 | CITY UNIVERSITY | BX048-020 | ELEVATOR UPGRADES | 4 | BID AWARD AND REGISTER CONTRCT | 2021-07-25 | 2021-10-22 | 2021-07-25 | 2021-10-22
20201123 | BRONX | 042 | CITY UNIVERSITY | BX048-020 | ELEVATOR UPGRADES | 5 | CONSTRUCTION TO 25% | 2021-10-23 | 2022-02-19 | 2021-10-23 | 2022-02-19
20201123 | BRONX | 042 | CITY UNIVERSITY | BX048-020 | ELEVATOR UPGRADES | 6 | CONSTRUCTION TO 50% | 2022-02-20 | 2022-06-19 | 2022-02-20 | 2022-06-19
20201123 | BRONX | 042 | CITY UNIVERSITY | BX048-020 | ELEVATOR UPGRADES | 7 | CONSTRUCTION TO 75% | 2022-06-20 | 2022-10-17 | 2022-06-20 | 2022-10-17
20201123 | BRONX | 042 | CITY UNIVERSITY | BX048-020 | ELEVATOR UPGRADES | 8 | ORIGINAL EQUIP & FURNISHING | 2022-10-18 | 2023-01-15 | 2022-10-18 | 2023-01-15
20201123 | BRONX | 042 | CITY UNIVERSITY | BX048-020 | ELEVATOR UPGRADES | 9 | SUBSTANTIAL COMPLETION | 2023-01-16 | 2023-03-16 | 2023-01-16 | 2023-03-16
20201123 | BRONX | 042 | CITY UNIVERSITY | BX048-020 | ELEVATOR UPGRADES | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-03-17 | 2023-04-15 | 2023-03-17 | 2026-04-15
20201123 | BRONX | 042 | CITY UNIVERSITY | BX049-020 | Carl Polowczyk Hall Upgrades | 1 | DEVELOP SCOPE | 2020-06-30 | 2020-09-27 | 2020-06-30 | 2020-09-27
20201123 | BRONX | 042 | CITY UNIVERSITY | BX049-020 | Carl Polowczyk Hall Upgrades | 2 | PRELIMINARY DESIGN | 2020-09-28 | 2021-01-25 | 2020-09-28 | 2021-01-25
20201123 | BRONX | 042 | CITY UNIVERSITY | BX049-020 | Carl Polowczyk Hall Upgrades | 3 | FINAL DESIGN | 2021-01-26 | 2021-07-24 | 2021-01-26 | 2021-07-24
20201123 | BRONX | 042 | CITY UNIVERSITY | BX049-020 | Carl Polowczyk Hall Upgrades | 4 | BID AWARD AND REGISTER CONTRCT | 2021-07-25 | 2021-10-22 | 2021-07-25 | 2021-10-22
20201123 | BRONX | 042 | CITY UNIVERSITY | BX049-020 | Carl Polowczyk Hall Upgrades | 5 | CONSTRUCTION TO 25% | 2021-10-23 | 2022-02-19 | 2021-10-23 | 2022-02-19
20201123 | BRONX | 042 | CITY UNIVERSITY | BX049-020 | Carl Polowczyk Hall Upgrades | 6 | CONSTRUCTION TO 50% | 2022-02-20 | 2022-06-19 | 2022-02-20 | 2022-06-19
20201123 | BRONX | 042 | CITY UNIVERSITY | BX049-020 | Carl Polowczyk Hall Upgrades | 7 | CONSTRUCTION TO 75% | 2022-06-20 | 2022-10-17 | 2022-06-20 | 2022-10-17
20201123 | BRONX | 042 | CITY UNIVERSITY | BX049-020 | Carl Polowczyk Hall Upgrades | 8 | ORIGINAL EQUIP & FURNISHING | 2022-10-18 | 2023-01-15 | 2022-10-18 | 2023-01-15
20201123 | BRONX | 042 | CITY UNIVERSITY | BX049-020 | Carl Polowczyk Hall Upgrades | 9 | SUBSTANTIAL COMPLETION | 2023-01-16 | 2023-03-16 | 2023-01-16 | 2023-03-16
20201123 | BRONX | 042 | CITY UNIVERSITY | BX049-020 | Carl Polowczyk Hall Upgrades | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-03-17 | 2023-04-15 | 2023-03-17 | 2026-04-15
20201123 | BRONX | 042 | CITY UNIVERSITY | BX050-021 | Elevator Installation Gould Memorial Library | 1 | DEVELOP SCOPE | 2021-06-30 | 2021-09-27 | 2021-06-30 | 2021-09-27
20201123 | BRONX | 042 | CITY UNIVERSITY | BX050-021 | Elevator Installation Gould Memorial Library | 2 | PRELIMINARY DESIGN | 2021-09-28 | 2022-01-25 | 2021-09-28 | 2022-01-25
20201123 | BRONX | 042 | CITY UNIVERSITY | BX050-021 | Elevator Installation Gould Memorial Library | 3 | FINAL DESIGN | 2022-01-26 | 2022-07-24 | 2022-01-26 | 2022-07-24
20201123 | BRONX | 042 | CITY UNIVERSITY | BX050-021 | Elevator Installation Gould Memorial Library | 4 | BID AWARD AND REGISTER CONTRCT | 2022-07-25 | 2022-10-22 | 2022-07-25 | 2022-10-22
20201123 | BRONX | 042 | CITY UNIVERSITY | BX050-021 | Elevator Installation Gould Memorial Library | 5 | CONSTRUCTION TO 25% | 2022-10-23 | 2023-02-19 | 2022-10-23 | 2023-02-19
20201123 | BRONX | 042 | CITY UNIVERSITY | BX050-021 | Elevator Installation Gould Memorial Library | 6 | CONSTRUCTION TO 50% | 2023-02-20 | 2023-06-19 | 2023-02-20 | 2023-06-19
20201123 | BRONX | 042 | CITY UNIVERSITY | BX050-021 | Elevator Installation Gould Memorial Library | 7 | CONSTRUCTION TO 75% | 2023-06-20 | 2023-10-17 | 2023-06-20 | 2023-10-17
20201123 | BRONX | 042 | CITY UNIVERSITY | BX050-021 | Elevator Installation Gould Memorial Library | 8 | ORIGINAL EQUIP & FURNISHING | 2023-10-18 | 2024-01-15 | 2023-10-18 | 2024-01-15
20201123 | BRONX | 042 | CITY UNIVERSITY | BX050-021 | Elevator Installation Gould Memorial Library | 9 | SUBSTANTIAL COMPLETION | 2024-01-16 | 2024-03-15 | 2024-01-16 | 2024-03-15
20201123 | BRONX | 042 | CITY UNIVERSITY | BX050-021 | Elevator Installation Gould Memorial Library | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-03-16 | 2024-04-14 | 2024-03-16 | 2024-04-14
20201123 | BRONX | 042 | CITY UNIVERSITY | CA034HS13 | 500 Grand Concourse 3rd Floor Renovation | 1 | DEVELOP SCOPE | 2017-06-01 | 2017-08-29 | 2017-06-01 | 2017-08-29
20201123 | BRONX | 042 | CITY UNIVERSITY | CA034HS13 | 500 Grand Concourse 3rd Floor Renovation | 2 | PRELIMINARY DESIGN | 2017-08-30 | 2017-12-27 | 2017-08-30 | 2017-12-27
20201123 | BRONX | 042 | CITY UNIVERSITY | CA034HS13 | 500 Grand Concourse 3rd Floor Renovation | 3 | FINAL DESIGN | 2017-12-28 | 2018-06-25 | 2017-12-28 | 2018-06-25
20201123 | BRONX | 042 | CITY UNIVERSITY | CA034HS13 | 500 Grand Concourse 3rd Floor Renovation | 4 | BID AWARD AND REGISTER CONTRCT | 2018-06-26 | 2018-09-23 | 2018-06-26 | 2018-09-23
20201123 | BRONX | 042 | CITY UNIVERSITY | CA034HS13 | 500 Grand Concourse 3rd Floor Renovation | 5 | CONSTRUCTION TO 25% | 2018-09-24 | 2019-01-21 | 2018-09-24 | 2019-01-21
20201123 | BRONX | 042 | CITY UNIVERSITY | CA034HS13 | 500 Grand Concourse 3rd Floor Renovation | 6 | CONSTRUCTION TO 50% | 2019-01-22 | 2019-05-21 | 2019-01-22 | 2019-05-21
20201123 | BRONX | 042 | CITY UNIVERSITY | CA034HS13 | 500 Grand Concourse 3rd Floor Renovation | 7 | CONSTRUCTION TO 75% | 2019-05-22 | 2019-09-18 | 2019-05-22 | 2019-09-18
20201123 | BRONX | 042 | CITY UNIVERSITY | CA034HS13 | 500 Grand Concourse 3rd Floor Renovation | 8 | ORIGINAL EQUIP & FURNISHING | 2019-09-19 | 2019-12-17 | 2019-09-19 | 2019-12-17
20201123 | BRONX | 042 | CITY UNIVERSITY | CA034HS13 | 500 Grand Concourse 3rd Floor Renovation | 9 | SUBSTANTIAL COMPLETION | 2019-12-18 | 2020-02-15 | 2019-12-18 | 2020-02-15
20201123 | BRONX | 042 | CITY UNIVERSITY | CA034HS13 | 500 Grand Concourse 3rd Floor Renovation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-02-16 | 2020-03-16 | 2020-02-16 | 2021-03-30
20201123 | BRONX | 042 | CITY UNIVERSITY | CA036-014 | Hostos CC: Allied Health and Sciences Building | 1 | DEVELOP SCOPE | 2014-06-01 | 2014-08-29 | 2021-07-01 | 2021-09-28
20201123 | BRONX | 042 | CITY UNIVERSITY | CA036-014 | Hostos CC: Allied Health and Sciences Building | 2 | PRELIMINARY DESIGN | 2014-08-30 | 2014-12-27 | 2021-09-29 | 2022-01-26
20201123 | BRONX | 042 | CITY UNIVERSITY | CA036-014 | Hostos CC: Allied Health and Sciences Building | 3 | FINAL DESIGN | 2014-12-28 | 2015-06-25 | 2022-01-27 | 2022-07-25
20201123 | BRONX | 042 | CITY UNIVERSITY | CA036-014 | Hostos CC: Allied Health and Sciences Building | 4 | BID AWARD AND REGISTER CONTRCT | 2015-06-26 | 2015-09-23 | 2022-07-26 | 2022-10-23
20201123 | BRONX | 042 | CITY UNIVERSITY | CA036-014 | Hostos CC: Allied Health and Sciences Building | 5 | CONSTRUCTION TO 25% | 2015-09-24 | 2016-01-21 | 2022-10-24 | 2023-02-20
20201123 | BRONX | 042 | CITY UNIVERSITY | CA036-014 | Hostos CC: Allied Health and Sciences Building | 6 | CONSTRUCTION TO 50% | 2016-01-22 | 2016-05-20 | 2023-02-21 | 2023-06-20
20201123 | BRONX | 042 | CITY UNIVERSITY | CA036-014 | Hostos CC: Allied Health and Sciences Building | 7 | CONSTRUCTION TO 75% | 2016-05-21 | 2016-09-17 | 2023-06-21 | 2023-10-18
20201123 | BRONX | 042 | CITY UNIVERSITY | CA036-014 | Hostos CC: Allied Health and Sciences Building | 8 | ORIGINAL EQUIP & FURNISHING | 2016-09-18 | 2016-12-16 | 2023-10-19 | 2024-01-16
20201123 | BRONX | 042 | CITY UNIVERSITY | CA036-014 | Hostos CC: Allied Health and Sciences Building | 9 | SUBSTANTIAL COMPLETION | 2016-12-17 | 2017-02-14 | 2024-01-17 | 2024-03-16
20201123 | BRONX | 042 | CITY UNIVERSITY | CA036-014 | Hostos CC: Allied Health and Sciences Building | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-02-15 | 2017-03-16 | 2024-03-17 | 2026-04-15
20201123 | BRONX | 042 | CITY UNIVERSITY | CA091HS96 | Hostos Retaining Wall Project | 1 | DEVELOP SCOPE | 2018-06-30 | 2018-09-27 | 2018-06-30 | 2018-09-27
20201123 | BRONX | 042 | CITY UNIVERSITY | CA091HS96 | Hostos Retaining Wall Project | 2 | PRELIMINARY DESIGN | 2018-09-28 | 2019-01-25 | 2018-09-28 | 2019-01-25
20201123 | BRONX | 042 | CITY UNIVERSITY | CA091HS96 | Hostos Retaining Wall Project | 3 | FINAL DESIGN | 2019-01-26 | 2019-07-24 | 2019-01-26 | 2019-07-24
20201123 | BRONX | 042 | CITY UNIVERSITY | CA091HS96 | Hostos Retaining Wall Project | 4 | BID AWARD AND REGISTER CONTRCT | 2019-07-25 | 2019-10-22 | 2019-07-25 | 2019-10-22
20201123 | BRONX | 042 | CITY UNIVERSITY | CA091HS96 | Hostos Retaining Wall Project | 5 | CONSTRUCTION TO 25% | 2019-10-23 | 2020-02-19 | 2019-10-23 | 2020-02-19
20201123 | BRONX | 042 | CITY UNIVERSITY | CA091HS96 | Hostos Retaining Wall Project | 6 | CONSTRUCTION TO 50% | 2020-02-20 | 2020-06-18 | 2020-02-20 | 2020-06-18
20201123 | BRONX | 042 | CITY UNIVERSITY | CA091HS96 | Hostos Retaining Wall Project | 7 | CONSTRUCTION TO 75% | 2020-06-19 | 2020-10-16 | 2020-06-19 | 2020-10-16
20201123 | BRONX | 042 | CITY UNIVERSITY | CA091HS96 | Hostos Retaining Wall Project | 8 | ORIGINAL EQUIP & FURNISHING | 2020-10-17 | 2021-01-14 | 2020-10-17 | 2021-01-14
20201123 | BRONX | 042 | CITY UNIVERSITY | CA091HS96 | Hostos Retaining Wall Project | 9 | SUBSTANTIAL COMPLETION | 2021-01-15 | 2021-03-15 | 2021-01-15 | 2021-03-15
20201123 | BRONX | 042 | CITY UNIVERSITY | CA091HS96 | Hostos Retaining Wall Project | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-16 | 2021-04-14 | 2021-03-16 | 2023-04-30
20201123 | BRONX | 042 | CITY UNIVERSITY | CA200BX06 | ALUMNI GYM BRIDGE REPLACEMENT | 9 | SUBSTANTIAL COMPLETION | 2020-12-17 | 2021-02-14 | 2020-12-17 | 2021-02-14
20201123 | BRONX | 042 | CITY UNIVERSITY | CA200BX06 | ALUMNI GYM BRIDGE REPLACEMENT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-02-15 | 2021-03-16 | 2021-02-15 | 2023-03-16
20201123 | BRONX | 042 | CITY UNIVERSITY | CA202HS04 | ADA Improvements | 1 | DEVELOP SCOPE | 2007-05-30 | 2007-08-27 | 2007-05-30 | 2007-08-27
20201123 | BRONX | 042 | CITY UNIVERSITY | CA202HS04 | ADA Improvements | 2 | PRELIMINARY DESIGN | 2007-08-28 | 2007-12-25 | 2007-08-28 | 2007-12-25
20201123 | BRONX | 042 | CITY UNIVERSITY | CA202HS04 | ADA Improvements | 3 | FINAL DESIGN | 2007-12-26 | 2008-06-22 | 2007-12-26 | 2008-06-22
20201123 | BRONX | 042 | CITY UNIVERSITY | CA202HS04 | ADA Improvements | 4 | BID AWARD AND REGISTER CONTRCT | 2008-06-23 | 2008-09-20 | 2008-06-23 | 2008-09-20
20201123 | BRONX | 042 | CITY UNIVERSITY | CA202HS04 | ADA Improvements | 5 | CONSTRUCTION TO 25% | 2008-09-21 | 2009-01-18 | 2008-09-21 | 2009-01-18
20201123 | BRONX | 042 | CITY UNIVERSITY | CA202HS04 | ADA Improvements | 6 | CONSTRUCTION TO 50% | 2009-01-19 | 2009-05-18 | 2009-01-19 | 2009-05-18
20201123 | BRONX | 042 | CITY UNIVERSITY | CA202HS04 | ADA Improvements | 7 | CONSTRUCTION TO 75% | 2009-05-19 | 2009-09-15 | 2009-05-19 | 2009-09-15
20201123 | BRONX | 042 | CITY UNIVERSITY | CA202HS04 | ADA Improvements | 8 | ORIGINAL EQUIP & FURNISHING | 2009-09-16 | 2009-12-14 | 2009-09-16 | 2009-12-14
20201123 | BRONX | 042 | CITY UNIVERSITY | CA202HS04 | ADA Improvements | 9 | SUBSTANTIAL COMPLETION | 2009-12-15 | 2010-02-12 | 2009-12-15 | 2010-02-12
20201123 | BRONX | 042 | CITY UNIVERSITY | CA202HS04 | ADA Improvements | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2010-02-13 | 2010-03-14 | 2010-02-13 | 2025-06-30
20201123 | BRONX | 042 | CITY UNIVERSITY | CA92BX019 | Colston Emergency Heating Restoration | 1 | DEVELOP SCOPE | 2019-06-30 | 2019-09-27 | 2019-06-30 | 2019-09-27
20201123 | BRONX | 042 | CITY UNIVERSITY | CA92BX019 | Colston Emergency Heating Restoration | 2 | PRELIMINARY DESIGN | 2019-09-28 | 2020-01-25 | 2019-09-28 | 2020-01-25
20201123 | BRONX | 042 | CITY UNIVERSITY | CA92BX019 | Colston Emergency Heating Restoration | 3 | FINAL DESIGN | 2020-01-26 | 2020-07-23 | 2020-01-26 | 2020-07-23
20201123 | BRONX | 042 | CITY UNIVERSITY | CA92BX019 | Colston Emergency Heating Restoration | 4 | BID AWARD AND REGISTER CONTRCT | 2020-07-24 | 2020-10-21 | 2020-07-24 | 2020-10-21
20201123 | BRONX | 042 | CITY UNIVERSITY | CA92BX019 | Colston Emergency Heating Restoration | 5 | CONSTRUCTION TO 25% | 2020-10-22 | 2021-02-18 | 2020-10-22 | 2021-02-18
20201123 | BRONX | 042 | CITY UNIVERSITY | CA92BX019 | Colston Emergency Heating Restoration | 6 | CONSTRUCTION TO 50% | 2021-02-19 | 2021-06-18 | 2021-02-19 | 2021-06-18
20201123 | BRONX | 042 | CITY UNIVERSITY | CA92BX019 | Colston Emergency Heating Restoration | 7 | CONSTRUCTION TO 75% | 2021-06-19 | 2021-10-16 | 2021-06-19 | 2021-10-16
20201123 | BRONX | 042 | CITY UNIVERSITY | CA92BX019 | Colston Emergency Heating Restoration | 8 | ORIGINAL EQUIP & FURNISHING | 2021-10-17 | 2022-01-14 | 2021-10-17 | 2022-01-14
20201123 | BRONX | 042 | CITY UNIVERSITY | CA92BX019 | Colston Emergency Heating Restoration | 9 | SUBSTANTIAL COMPLETION | 2022-01-15 | 2022-03-15 | 2022-01-15 | 2022-03-15
20201123 | BRONX | 042 | CITY UNIVERSITY | CA92BX019 | Colston Emergency Heating Restoration | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-16 | 2022-04-14 | 2022-03-16 | 2026-04-15
20201123 | BRONX | 042 | CITY UNIVERSITY | HS007-010 | PEDESTRIAN BRIDGE ROOF REPLACEMENT | 1 | DEVELOP SCOPE | 2010-06-01 | 2010-08-29 | 2010-06-01 | 2010-08-29
20201123 | BRONX | 042 | CITY UNIVERSITY | HS007-010 | PEDESTRIAN BRIDGE ROOF REPLACEMENT | 2 | PRELIMINARY DESIGN | 2010-08-30 | 2010-12-27 | 2010-08-30 | 2010-12-27
20201123 | BRONX | 042 | CITY UNIVERSITY | HS007-010 | PEDESTRIAN BRIDGE ROOF REPLACEMENT | 3 | FINAL DESIGN | 2010-12-28 | 2011-06-25 | 2010-12-28 | 2011-06-25
20201123 | BRONX | 042 | CITY UNIVERSITY | HS007-010 | PEDESTRIAN BRIDGE ROOF REPLACEMENT | 4 | BID AWARD AND REGISTER CONTRCT | 2011-06-26 | 2011-09-23 | 2011-06-26 | 2011-09-23
20201123 | BRONX | 042 | CITY UNIVERSITY | HS007-010 | PEDESTRIAN BRIDGE ROOF REPLACEMENT | 5 | CONSTRUCTION TO 25% | 2011-09-24 | 2012-01-21 | 2011-09-24 | 2012-01-21
20201123 | BRONX | 042 | CITY UNIVERSITY | HS007-010 | PEDESTRIAN BRIDGE ROOF REPLACEMENT | 6 | CONSTRUCTION TO 50% | 2012-01-22 | 2012-05-20 | 2012-01-22 | 2012-05-20
20201123 | BRONX | 042 | CITY UNIVERSITY | HS007-010 | PEDESTRIAN BRIDGE ROOF REPLACEMENT | 7 | CONSTRUCTION TO 75% | 2012-05-21 | 2012-09-17 | 2012-05-21 | 2012-09-17
20201123 | BRONX | 042 | CITY UNIVERSITY | HS007-010 | PEDESTRIAN BRIDGE ROOF REPLACEMENT | 8 | ORIGINAL EQUIP & FURNISHING | 2012-09-18 | 2012-12-16 | 2012-09-18 | 2012-12-16
20201123 | BRONX | 042 | CITY UNIVERSITY | HS007-010 | PEDESTRIAN BRIDGE ROOF REPLACEMENT | 9 | SUBSTANTIAL COMPLETION | 2012-12-17 | 2013-02-14 | 2012-12-17 | 2013-02-14
20201123 | BRONX | 042 | CITY UNIVERSITY | HS007-010 | PEDESTRIAN BRIDGE ROOF REPLACEMENT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-02-15 | 2013-03-16 | 2013-02-15 | 2026-12-31
20201123 | BRONX | 042 | CITY UNIVERSITY | HS033-007 | Natural Science Lab Renovation | 1 | DEVELOP SCOPE | 2007-05-25 | 2007-08-22 | 2021-07-01 | 2021-10-01
20201123 | BRONX | 042 | CITY UNIVERSITY | HS033-007 | Natural Science Lab Renovation | 2 | PRELIMINARY DESIGN | 2007-08-23 | 2007-12-20 | 2021-10-02 | 2022-01-29
20201123 | BRONX | 042 | CITY UNIVERSITY | HS033-007 | Natural Science Lab Renovation | 3 | FINAL DESIGN | 2007-12-21 | 2008-06-17 | 2022-01-30 | 2022-07-28
20201123 | BRONX | 042 | CITY UNIVERSITY | HS033-007 | Natural Science Lab Renovation | 4 | BID AWARD AND REGISTER CONTRCT | 2008-06-18 | 2008-09-15 | 2022-07-29 | 2022-10-26
20201123 | BRONX | 042 | CITY UNIVERSITY | HS033-007 | Natural Science Lab Renovation | 5 | CONSTRUCTION TO 25% | 2008-09-16 | 2009-01-13 | 2022-10-27 | 2023-02-23
20201123 | BRONX | 042 | CITY UNIVERSITY | HS033-007 | Natural Science Lab Renovation | 6 | CONSTRUCTION TO 50% | 2009-01-14 | 2009-05-13 | 2023-02-24 | 2023-06-23
20201123 | BRONX | 042 | CITY UNIVERSITY | HS033-007 | Natural Science Lab Renovation | 7 | CONSTRUCTION TO 75% | 2009-05-14 | 2009-09-10 | 2023-06-24 | 2023-10-21
20201123 | BRONX | 042 | CITY UNIVERSITY | HS033-007 | Natural Science Lab Renovation | 8 | ORIGINAL EQUIP & FURNISHING | 2009-09-11 | 2009-12-09 | 2023-10-22 | 2024-01-19
20201123 | BRONX | 042 | CITY UNIVERSITY | HS033-007 | Natural Science Lab Renovation | 9 | SUBSTANTIAL COMPLETION | 2009-12-10 | 2010-02-07 | 2024-01-20 | 2024-03-19
20201123 | BRONX | 042 | CITY UNIVERSITY | HS033-007 | Natural Science Lab Renovation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2010-02-08 | 2010-03-09 | 2024-03-20 | 2026-04-30
20201123 | BRONX | 042 | CITY UNIVERSITY | HS034-007 | 450 Grand Concourse Theater Improvements | 1 | DEVELOP SCOPE | 2014-06-01 | 2014-08-29 | 2014-06-01 | 2014-08-29
20201123 | BRONX | 042 | CITY UNIVERSITY | HS034-007 | 450 Grand Concourse Theater Improvements | 2 | PRELIMINARY DESIGN | 2014-08-30 | 2014-12-27 | 2014-08-30 | 2014-12-27
20201123 | BRONX | 042 | CITY UNIVERSITY | HS034-007 | 450 Grand Concourse Theater Improvements | 3 | FINAL DESIGN | 2014-12-28 | 2015-06-25 | 2014-12-28 | 2015-06-25
20201123 | BRONX | 042 | CITY UNIVERSITY | HS034-007 | 450 Grand Concourse Theater Improvements | 4 | BID AWARD AND REGISTER CONTRCT | 2015-06-26 | 2015-09-23 | 2015-06-26 | 2015-09-23
20201123 | BRONX | 042 | CITY UNIVERSITY | HS034-007 | 450 Grand Concourse Theater Improvements | 5 | CONSTRUCTION TO 25% | 2015-09-24 | 2016-01-21 | 2015-09-24 | 2016-01-21
20201123 | BRONX | 042 | CITY UNIVERSITY | HS034-007 | 450 Grand Concourse Theater Improvements | 6 | CONSTRUCTION TO 50% | 2016-01-22 | 2016-05-20 | 2016-01-22 | 2016-05-20
20201123 | BRONX | 042 | CITY UNIVERSITY | HS034-007 | 450 Grand Concourse Theater Improvements | 7 | CONSTRUCTION TO 75% | 2016-05-21 | 2016-09-17 | 2016-05-21 | 2016-09-17
20201123 | BRONX | 042 | CITY UNIVERSITY | HS034-007 | 450 Grand Concourse Theater Improvements | 8 | ORIGINAL EQUIP & FURNISHING | 2016-09-18 | 2016-12-16 | 2016-09-18 | 2016-12-16
20201123 | BRONX | 042 | CITY UNIVERSITY | HS034-007 | 450 Grand Concourse Theater Improvements | 9 | SUBSTANTIAL COMPLETION | 2016-12-17 | 2017-02-14 | 2016-12-17 | 2017-02-14
20201123 | BRONX | 042 | CITY UNIVERSITY | HS034-007 | 450 Grand Concourse Theater Improvements | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-02-15 | 2017-03-16 | 2017-02-15 | 2027-03-31
20201123 | BRONX | 042 | CITY UNIVERSITY | HS041-011 | 500 Grand Concourse 4th Floor and Emerg. Generator | 1 | DEVELOP SCOPE | 2011-06-01 | 2011-08-29 | 2011-06-01 | 2011-08-29
20201123 | BRONX | 042 | CITY UNIVERSITY | HS041-011 | 500 Grand Concourse 4th Floor and Emerg. Generator | 2 | PRELIMINARY DESIGN | 2011-08-30 | 2011-12-27 | 2011-08-30 | 2011-12-27
20201123 | BRONX | 042 | CITY UNIVERSITY | HS041-011 | 500 Grand Concourse 4th Floor and Emerg. Generator | 3 | FINAL DESIGN | 2011-12-28 | 2012-06-24 | 2011-12-28 | 2012-06-24
20201123 | BRONX | 042 | CITY UNIVERSITY | HS041-011 | 500 Grand Concourse 4th Floor and Emerg. Generator | 4 | BID AWARD AND REGISTER CONTRCT | 2012-06-25 | 2012-09-22 | 2012-06-25 | 2012-09-22
20201123 | BRONX | 042 | CITY UNIVERSITY | HS041-011 | 500 Grand Concourse 4th Floor and Emerg. Generator | 5 | CONSTRUCTION TO 25% | 2012-09-23 | 2013-01-20 | 2012-09-23 | 2013-01-20
20201123 | BRONX | 042 | CITY UNIVERSITY | HS041-011 | 500 Grand Concourse 4th Floor and Emerg. Generator | 6 | CONSTRUCTION TO 50% | 2013-01-21 | 2013-05-20 | 2013-01-21 | 2013-05-20
20201123 | BRONX | 042 | CITY UNIVERSITY | HS041-011 | 500 Grand Concourse 4th Floor and Emerg. Generator | 7 | CONSTRUCTION TO 75% | 2013-05-21 | 2013-09-17 | 2013-05-21 | 2013-09-17
20201123 | BRONX | 042 | CITY UNIVERSITY | HS041-011 | 500 Grand Concourse 4th Floor and Emerg. Generator | 8 | ORIGINAL EQUIP & FURNISHING | 2013-09-18 | 2013-12-16 | 2013-09-18 | 2013-12-16
20201123 | BRONX | 042 | CITY UNIVERSITY | HS041-011 | 500 Grand Concourse 4th Floor and Emerg. Generator | 9 | SUBSTANTIAL COMPLETION | 2013-12-17 | 2014-02-14 | 2013-12-17 | 2014-02-14
20201123 | BRONX | 042 | CITY UNIVERSITY | HS041-011 | 500 Grand Concourse 4th Floor and Emerg. Generator | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-02-15 | 2014-03-16 | 2014-02-15 | 2024-12-31
20201123 | BRONX | 042 | CITY UNIVERSITY | HS043-011 | Hostos CC - 500 Grand Concourse Renovations | 1 | DEVELOP SCOPE | 2011-06-01 | 2011-08-29 | 2019-07-01 | 2019-10-01
20201123 | BRONX | 042 | CITY UNIVERSITY | HS043-011 | Hostos CC - 500 Grand Concourse Renovations | 2 | PRELIMINARY DESIGN | 2011-08-30 | 2011-12-27 | 2019-10-02 | 2020-01-29
20201123 | BRONX | 042 | CITY UNIVERSITY | HS043-011 | Hostos CC - 500 Grand Concourse Renovations | 3 | FINAL DESIGN | 2011-12-28 | 2012-06-24 | 2020-01-30 | 2020-07-27
20201123 | BRONX | 042 | CITY UNIVERSITY | HS043-011 | Hostos CC - 500 Grand Concourse Renovations | 4 | BID AWARD AND REGISTER CONTRCT | 2012-06-25 | 2012-09-22 | 2020-07-28 | 2020-10-25
20201123 | BRONX | 042 | CITY UNIVERSITY | HS043-011 | Hostos CC - 500 Grand Concourse Renovations | 5 | CONSTRUCTION TO 25% | 2012-09-23 | 2013-01-20 | 2020-10-26 | 2021-02-22
20201123 | BRONX | 042 | CITY UNIVERSITY | HS043-011 | Hostos CC - 500 Grand Concourse Renovations | 6 | CONSTRUCTION TO 50% | 2013-01-21 | 2013-05-20 | 2021-02-23 | 2021-06-22
20201123 | BRONX | 042 | CITY UNIVERSITY | HS043-011 | Hostos CC - 500 Grand Concourse Renovations | 7 | CONSTRUCTION TO 75% | 2013-05-21 | 2013-09-17 | 2021-06-23 | 2021-10-20
20201123 | BRONX | 042 | CITY UNIVERSITY | HS043-011 | Hostos CC - 500 Grand Concourse Renovations | 8 | ORIGINAL EQUIP & FURNISHING | 2013-09-18 | 2013-12-16 | 2021-10-21 | 2022-01-18
20201123 | BRONX | 042 | CITY UNIVERSITY | HS043-011 | Hostos CC - 500 Grand Concourse Renovations | 9 | SUBSTANTIAL COMPLETION | 2013-12-17 | 2014-02-14 | 2022-01-19 | 2022-03-19
20201123 | BRONX | 042 | CITY UNIVERSITY | HS043-011 | Hostos CC - 500 Grand Concourse Renovations | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-02-15 | 2014-03-16 | 2022-03-20 | 2027-04-30
20201123 | BRONX | 042 | CITY UNIVERSITY | HS045-012 | 500 Grand Concourse Renovations | 1 | DEVELOP SCOPE | 2012-06-01 | 2012-08-29 | 2012-06-01 | 2012-08-29
20201123 | BRONX | 042 | CITY UNIVERSITY | HS045-012 | 500 Grand Concourse Renovations | 2 | PRELIMINARY DESIGN | 2012-08-30 | 2012-12-27 | 2012-08-30 | 2012-12-27
20201123 | BRONX | 042 | CITY UNIVERSITY | HS045-012 | 500 Grand Concourse Renovations | 3 | FINAL DESIGN | 2012-12-28 | 2013-06-25 | 2012-12-28 | 2013-06-25
20201123 | BRONX | 042 | CITY UNIVERSITY | HS045-012 | 500 Grand Concourse Renovations | 4 | BID AWARD AND REGISTER CONTRCT | 2013-06-26 | 2013-09-23 | 2013-06-26 | 2013-09-23
20201123 | BRONX | 042 | CITY UNIVERSITY | HS045-012 | 500 Grand Concourse Renovations | 5 | CONSTRUCTION TO 25% | 2013-09-24 | 2014-01-21 | 2013-09-24 | 2014-01-21
20201123 | BRONX | 042 | CITY UNIVERSITY | HS045-012 | 500 Grand Concourse Renovations | 6 | CONSTRUCTION TO 50% | 2014-01-22 | 2014-05-21 | 2014-01-22 | 2014-05-21
20201123 | BRONX | 042 | CITY UNIVERSITY | HS045-012 | 500 Grand Concourse Renovations | 7 | CONSTRUCTION TO 75% | 2014-05-22 | 2014-09-18 | 2014-05-22 | 2014-09-18
20201123 | BRONX | 042 | CITY UNIVERSITY | HS045-012 | 500 Grand Concourse Renovations | 8 | ORIGINAL EQUIP & FURNISHING | 2014-09-19 | 2014-12-17 | 2014-09-19 | 2014-12-17
20201123 | BRONX | 042 | CITY UNIVERSITY | HS045-012 | 500 Grand Concourse Renovations | 9 | SUBSTANTIAL COMPLETION | 2014-12-18 | 2015-02-15 | 2014-12-18 | 2015-02-15
20201123 | BRONX | 042 | CITY UNIVERSITY | HS045-012 | 500 Grand Concourse Renovations | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-02-16 | 2015-03-17 | 2015-02-16 | 2027-12-31
20201123 | BRONX | 042 | CITY UNIVERSITY | HS047-013 | Savoy Building Roof Replacement | 1 | DEVELOP SCOPE | 2013-06-01 | 2013-08-29 | 2013-06-01 | 2013-08-29
20201123 | BRONX | 042 | CITY UNIVERSITY | HS047-013 | Savoy Building Roof Replacement | 2 | PRELIMINARY DESIGN | 2013-08-30 | 2013-12-27 | 2013-08-30 | 2013-12-27
20201123 | BRONX | 042 | CITY UNIVERSITY | HS047-013 | Savoy Building Roof Replacement | 3 | FINAL DESIGN | 2013-12-28 | 2014-06-25 | 2013-12-28 | 2014-06-25
20201123 | BRONX | 042 | CITY UNIVERSITY | HS047-013 | Savoy Building Roof Replacement | 4 | BID AWARD AND REGISTER CONTRCT | 2014-06-26 | 2014-09-23 | 2014-06-26 | 2014-09-23
20201123 | BRONX | 042 | CITY UNIVERSITY | HS047-013 | Savoy Building Roof Replacement | 5 | CONSTRUCTION TO 25% | 2014-09-24 | 2015-01-21 | 2014-09-24 | 2015-01-21
20201123 | BRONX | 042 | CITY UNIVERSITY | HS047-013 | Savoy Building Roof Replacement | 6 | CONSTRUCTION TO 50% | 2015-01-22 | 2015-05-21 | 2015-01-22 | 2015-05-21
20201123 | BRONX | 042 | CITY UNIVERSITY | HS047-013 | Savoy Building Roof Replacement | 7 | CONSTRUCTION TO 75% | 2015-05-22 | 2015-09-18 | 2015-05-22 | 2015-09-18
20201123 | BRONX | 042 | CITY UNIVERSITY | HS047-013 | Savoy Building Roof Replacement | 8 | ORIGINAL EQUIP & FURNISHING | 2015-09-19 | 2015-12-17 | 2015-09-19 | 2015-12-17
20201123 | BRONX | 042 | CITY UNIVERSITY | HS047-013 | Savoy Building Roof Replacement | 9 | SUBSTANTIAL COMPLETION | 2015-12-18 | 2016-02-15 | 2015-12-18 | 2016-02-15
20201123 | BRONX | 042 | CITY UNIVERSITY | HS047-013 | Savoy Building Roof Replacement | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-02-16 | 2016-03-16 | 2016-02-16 | 2026-03-30
20201123 | BRONX | 042 | CITY UNIVERSITY | HS048-013 | Renovation and HVAC Upgrade | 1 | DEVELOP SCOPE | 2013-06-01 | 2013-08-29 | 2013-06-01 | 2013-08-29
20201123 | BRONX | 042 | CITY UNIVERSITY | HS048-013 | Renovation and HVAC Upgrade | 2 | PRELIMINARY DESIGN | 2013-08-30 | 2013-12-27 | 2013-08-30 | 2013-12-27
20201123 | BRONX | 042 | CITY UNIVERSITY | HS048-013 | Renovation and HVAC Upgrade | 3 | FINAL DESIGN | 2013-12-28 | 2014-06-25 | 2013-12-28 | 2014-06-25
20201123 | BRONX | 042 | CITY UNIVERSITY | HS048-013 | Renovation and HVAC Upgrade | 4 | BID AWARD AND REGISTER CONTRCT | 2014-06-26 | 2014-09-23 | 2014-06-26 | 2014-09-23
20201123 | BRONX | 042 | CITY UNIVERSITY | HS048-013 | Renovation and HVAC Upgrade | 5 | CONSTRUCTION TO 25% | 2014-09-24 | 2015-01-21 | 2014-09-24 | 2015-01-21
20201123 | BRONX | 042 | CITY UNIVERSITY | HS048-013 | Renovation and HVAC Upgrade | 6 | CONSTRUCTION TO 50% | 2015-01-22 | 2015-05-21 | 2015-01-22 | 2015-05-21
20201123 | BRONX | 042 | CITY UNIVERSITY | HS048-013 | Renovation and HVAC Upgrade | 7 | CONSTRUCTION TO 75% | 2015-05-22 | 2015-09-18 | 2015-05-22 | 2015-09-18
20201123 | BRONX | 042 | CITY UNIVERSITY | HS048-013 | Renovation and HVAC Upgrade | 8 | ORIGINAL EQUIP & FURNISHING | 2015-09-19 | 2015-12-17 | 2015-09-19 | 2015-12-17
20201123 | BRONX | 042 | CITY UNIVERSITY | HS048-013 | Renovation and HVAC Upgrade | 9 | SUBSTANTIAL COMPLETION | 2015-12-18 | 2016-02-15 | 2015-12-18 | 2016-02-15
20201123 | BRONX | 042 | CITY UNIVERSITY | HS048-013 | Renovation and HVAC Upgrade | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-02-16 | 2016-03-16 | 2016-02-16 | 2022-03-30
20201123 | BRONX | 042 | CITY UNIVERSITY | HS050-014 | Allied Health and Sciences Building | 1 | DEVELOP SCOPE | 2014-06-01 | 2014-08-29 | 2021-07-01 | 2021-09-29
20201123 | BRONX | 042 | CITY UNIVERSITY | HS050-014 | Allied Health and Sciences Building | 2 | PRELIMINARY DESIGN | 2014-08-30 | 2014-12-27 | 2021-09-30 | 2022-01-27
20201123 | BRONX | 042 | CITY UNIVERSITY | HS050-014 | Allied Health and Sciences Building | 3 | FINAL DESIGN | 2014-12-28 | 2015-06-25 | 2022-01-28 | 2022-07-26
20201123 | BRONX | 042 | CITY UNIVERSITY | HS050-014 | Allied Health and Sciences Building | 4 | BID AWARD AND REGISTER CONTRCT | 2015-06-26 | 2015-09-23 | 2022-07-27 | 2022-10-24
20201123 | BRONX | 042 | CITY UNIVERSITY | HS050-014 | Allied Health and Sciences Building | 5 | CONSTRUCTION TO 25% | 2015-09-24 | 2016-01-21 | 2022-10-25 | 2023-02-21
20201123 | BRONX | 042 | CITY UNIVERSITY | HS050-014 | Allied Health and Sciences Building | 6 | CONSTRUCTION TO 50% | 2016-01-22 | 2016-05-20 | 2023-02-22 | 2023-06-21
20201123 | BRONX | 042 | CITY UNIVERSITY | HS050-014 | Allied Health and Sciences Building | 7 | CONSTRUCTION TO 75% | 2016-05-21 | 2016-09-17 | 2023-06-22 | 2023-10-19
20201123 | BRONX | 042 | CITY UNIVERSITY | HS050-014 | Allied Health and Sciences Building | 8 | ORIGINAL EQUIP & FURNISHING | 2016-09-18 | 2016-12-16 | 2023-10-20 | 2024-01-17
20201123 | BRONX | 042 | CITY UNIVERSITY | HS050-014 | Allied Health and Sciences Building | 9 | SUBSTANTIAL COMPLETION | 2016-12-17 | 2017-02-14 | 2024-01-18 | 2024-03-17
20201123 | BRONX | 042 | CITY UNIVERSITY | HS050-014 | Allied Health and Sciences Building | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-02-15 | 2017-03-16 | 2024-03-18 | 2026-04-30
20201123 | BRONX | 042 | CITY UNIVERSITY | HS054-017 | Create one Stop Center | 1 | DEVELOP SCOPE | 2017-06-01 | 2017-08-29 | 2019-07-01 | 2019-10-01
20201123 | BRONX | 042 | CITY UNIVERSITY | HS054-017 | Create one Stop Center | 2 | PRELIMINARY DESIGN | 2017-08-30 | 2017-12-27 | 2019-10-02 | 2020-01-29
20201123 | BRONX | 042 | CITY UNIVERSITY | HS054-017 | Create one Stop Center | 3 | FINAL DESIGN | 2017-12-28 | 2018-06-25 | 2020-01-30 | 2020-07-27
20201123 | BRONX | 042 | CITY UNIVERSITY | HS054-017 | Create one Stop Center | 4 | BID AWARD AND REGISTER CONTRCT | 2018-06-26 | 2018-09-23 | 2020-07-28 | 2020-10-25
20201123 | BRONX | 042 | CITY UNIVERSITY | HS054-017 | Create one Stop Center | 5 | CONSTRUCTION TO 25% | 2018-09-24 | 2019-01-21 | 2020-10-26 | 2021-02-22
20201123 | BRONX | 042 | CITY UNIVERSITY | HS054-017 | Create one Stop Center | 6 | CONSTRUCTION TO 50% | 2019-01-22 | 2019-05-21 | 2021-02-23 | 2021-06-22
20201123 | BRONX | 042 | CITY UNIVERSITY | HS054-017 | Create one Stop Center | 7 | CONSTRUCTION TO 75% | 2019-05-22 | 2019-09-18 | 2021-06-23 | 2021-10-20
20201123 | BRONX | 042 | CITY UNIVERSITY | HS054-017 | Create one Stop Center | 8 | ORIGINAL EQUIP & FURNISHING | 2019-09-19 | 2019-12-17 | 2021-10-21 | 2022-01-18
20201123 | BRONX | 042 | CITY UNIVERSITY | HS054-017 | Create one Stop Center | 9 | SUBSTANTIAL COMPLETION | 2019-12-18 | 2020-02-15 | 2022-01-19 | 2022-03-19
20201123 | BRONX | 042 | CITY UNIVERSITY | HS054-017 | Create one Stop Center | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-02-16 | 2020-03-16 | 2022-03-20 | 2027-05-03
20201123 | BRONX | 042 | CITY UNIVERSITY | HS055-018 | Lighting Electrical Upgrade | 1 | DEVELOP SCOPE | 2018-06-01 | 2018-08-29 | 2019-07-01 | 2019-10-01
20201123 | BRONX | 042 | CITY UNIVERSITY | HS055-018 | Lighting Electrical Upgrade | 2 | PRELIMINARY DESIGN | 2018-08-30 | 2018-12-27 | 2019-10-02 | 2020-01-29
20201123 | BRONX | 042 | CITY UNIVERSITY | HS055-018 | Lighting Electrical Upgrade | 3 | FINAL DESIGN | 2018-12-28 | 2019-06-25 | 2020-01-30 | 2020-07-27
20201123 | BRONX | 042 | CITY UNIVERSITY | HS055-018 | Lighting Electrical Upgrade | 4 | BID AWARD AND REGISTER CONTRCT | 2019-06-26 | 2019-09-23 | 2020-07-28 | 2020-10-25
20201123 | BRONX | 042 | CITY UNIVERSITY | HS055-018 | Lighting Electrical Upgrade | 5 | CONSTRUCTION TO 25% | 2019-09-24 | 2020-01-21 | 2020-10-26 | 2021-02-22
20201123 | BRONX | 042 | CITY UNIVERSITY | HS055-018 | Lighting Electrical Upgrade | 6 | CONSTRUCTION TO 50% | 2020-01-22 | 2020-05-20 | 2021-02-23 | 2021-06-22
20201123 | BRONX | 042 | CITY UNIVERSITY | HS055-018 | Lighting Electrical Upgrade | 7 | CONSTRUCTION TO 75% | 2020-05-21 | 2020-09-17 | 2021-06-23 | 2021-10-20
20201123 | BRONX | 042 | CITY UNIVERSITY | HS055-018 | Lighting Electrical Upgrade | 8 | ORIGINAL EQUIP & FURNISHING | 2020-09-18 | 2020-12-16 | 2021-10-21 | 2022-01-18
20201123 | BRONX | 042 | CITY UNIVERSITY | HS055-018 | Lighting Electrical Upgrade | 9 | SUBSTANTIAL COMPLETION | 2020-12-17 | 2021-02-14 | 2022-01-19 | 2022-03-19
20201123 | BRONX | 042 | CITY UNIVERSITY | HS055-018 | Lighting Electrical Upgrade | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-02-15 | 2021-03-16 | 2022-03-20 | 2022-04-18
20201123 | BRONX | 042 | CITY UNIVERSITY | HS055-098 | Window Rehab - 471 Walton | 2 | PRELIMINARY DESIGN | 2007-05-30 | 2007-09-26 | 2007-05-30 | 2007-09-26
20201123 | BRONX | 042 | CITY UNIVERSITY | HS055-098 | Window Rehab - 471 Walton | 3 | FINAL DESIGN | 2007-09-27 | 2008-03-24 | 2007-09-27 | 2008-03-24
20201123 | BRONX | 042 | CITY UNIVERSITY | HS055-098 | Window Rehab - 471 Walton | 4 | BID AWARD AND REGISTER CONTRCT | 2008-03-25 | 2008-06-22 | 2008-03-25 | 2008-06-22
20201123 | BRONX | 042 | CITY UNIVERSITY | HS055-098 | Window Rehab - 471 Walton | 5 | CONSTRUCTION TO 25% | 2008-06-23 | 2008-10-20 | 2008-06-23 | 2008-10-20
20201123 | BRONX | 042 | CITY UNIVERSITY | HS055-098 | Window Rehab - 471 Walton | 6 | CONSTRUCTION TO 50% | 2008-10-21 | 2009-06-17 | 2008-10-21 | 2009-06-17
20201123 | BRONX | 042 | CITY UNIVERSITY | HS055-098 | Window Rehab - 471 Walton | 7 | CONSTRUCTION TO 75% | 2009-06-18 | 2010-06-17 | 2009-06-18 | 2010-06-17
20201123 | BRONX | 042 | CITY UNIVERSITY | HS055-098 | Window Rehab - 471 Walton | 8 | ORIGINAL EQUIP & FURNISHING | 2010-06-18 | 2010-06-17 | 2010-06-18 | 2010-06-17
20201123 | BRONX | 042 | CITY UNIVERSITY | HS055-098 | Window Rehab - 471 Walton | 9 | SUBSTANTIAL COMPLETION | 2010-06-18 | 2010-06-17 | 2010-06-18 | 2010-06-17
20201123 | BRONX | 042 | CITY UNIVERSITY | HS055-098 | Window Rehab - 471 Walton | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2010-06-18 | 2010-07-17 | 2010-06-18 | 2018-07-31
20201123 | BRONX | 042 | CITY UNIVERSITY | HS057-019 | Smart Classroom Conversion | 1 | DEVELOP SCOPE | 2018-06-30 | 2018-09-27 | 2020-07-01 | 2020-10-01
20201123 | BRONX | 042 | CITY UNIVERSITY | HS057-019 | Smart Classroom Conversion | 2 | PRELIMINARY DESIGN | 2018-09-28 | 2019-01-25 | 2020-10-02 | 2021-01-29
20201123 | BRONX | 042 | CITY UNIVERSITY | HS057-019 | Smart Classroom Conversion | 3 | FINAL DESIGN | 2019-01-26 | 2019-07-24 | 2021-01-30 | 2021-07-28
20201123 | BRONX | 042 | CITY UNIVERSITY | HS057-019 | Smart Classroom Conversion | 4 | BID AWARD AND REGISTER CONTRCT | 2019-07-25 | 2019-10-22 | 2021-07-29 | 2021-10-26
20201123 | BRONX | 042 | CITY UNIVERSITY | HS057-019 | Smart Classroom Conversion | 5 | CONSTRUCTION TO 25% | 2019-10-23 | 2020-02-19 | 2021-10-27 | 2022-02-23
20201123 | BRONX | 042 | CITY UNIVERSITY | HS057-019 | Smart Classroom Conversion | 6 | CONSTRUCTION TO 50% | 2020-02-20 | 2020-06-18 | 2022-02-24 | 2022-06-23
20201123 | BRONX | 042 | CITY UNIVERSITY | HS057-019 | Smart Classroom Conversion | 7 | CONSTRUCTION TO 75% | 2020-06-19 | 2020-10-16 | 2022-06-24 | 2022-10-21
20201123 | BRONX | 042 | CITY UNIVERSITY | HS057-019 | Smart Classroom Conversion | 8 | ORIGINAL EQUIP & FURNISHING | 2020-10-17 | 2021-01-14 | 2022-10-22 | 2023-01-19
20201123 | BRONX | 042 | CITY UNIVERSITY | HS057-019 | Smart Classroom Conversion | 9 | SUBSTANTIAL COMPLETION | 2021-01-15 | 2021-03-15 | 2023-01-20 | 2023-03-20
20201123 | BRONX | 042 | CITY UNIVERSITY | HS057-019 | Smart Classroom Conversion | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-16 | 2021-04-14 | 2023-03-21 | 2026-04-30
20201123 | BRONX | 042 | CITY UNIVERSITY | HS058-019 | Basement Renovations at 500 Grand Concourse | 1 | DEVELOP SCOPE | 2019-06-30 | 2019-09-27 | 2021-07-01 | 2021-10-01
20201123 | BRONX | 042 | CITY UNIVERSITY | HS058-019 | Basement Renovations at 500 Grand Concourse | 2 | PRELIMINARY DESIGN | 2019-09-28 | 2020-01-25 | 2021-10-02 | 2022-01-29
20201123 | BRONX | 042 | CITY UNIVERSITY | HS058-019 | Basement Renovations at 500 Grand Concourse | 3 | FINAL DESIGN | 2020-01-26 | 2020-07-23 | 2022-01-30 | 2022-07-28
20201123 | BRONX | 042 | CITY UNIVERSITY | HS058-019 | Basement Renovations at 500 Grand Concourse | 4 | BID AWARD AND REGISTER CONTRCT | 2020-07-24 | 2020-10-21 | 2022-07-29 | 2022-10-26
20201123 | BRONX | 042 | CITY UNIVERSITY | HS058-019 | Basement Renovations at 500 Grand Concourse | 5 | CONSTRUCTION TO 25% | 2020-10-22 | 2021-02-18 | 2022-10-27 | 2023-02-23
20201123 | BRONX | 042 | CITY UNIVERSITY | HS058-019 | Basement Renovations at 500 Grand Concourse | 6 | CONSTRUCTION TO 50% | 2021-02-19 | 2021-06-18 | 2023-02-24 | 2023-06-23
20201123 | BRONX | 042 | CITY UNIVERSITY | HS058-019 | Basement Renovations at 500 Grand Concourse | 7 | CONSTRUCTION TO 75% | 2021-06-19 | 2021-10-16 | 2023-06-24 | 2023-10-21
20201123 | BRONX | 042 | CITY UNIVERSITY | HS058-019 | Basement Renovations at 500 Grand Concourse | 8 | ORIGINAL EQUIP & FURNISHING | 2021-10-17 | 2022-01-14 | 2023-10-22 | 2024-01-19
20201123 | BRONX | 042 | CITY UNIVERSITY | HS058-019 | Basement Renovations at 500 Grand Concourse | 9 | SUBSTANTIAL COMPLETION | 2022-01-15 | 2022-03-15 | 2024-01-20 | 2024-03-19
20201123 | BRONX | 042 | CITY UNIVERSITY | HS058-019 | Basement Renovations at 500 Grand Concourse | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-16 | 2022-04-14 | 2024-03-20 | 2026-04-30
20201123 | BRONX | 042 | CITY UNIVERSITY | HS058-020 | 2nd Floor & Basement Renovation/Final Phase (500 GC) | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-10-01 | 2019-07-01 | 2019-10-01
20201123 | BRONX | 042 | CITY UNIVERSITY | HS058-020 | 2nd Floor & Basement Renovation/Final Phase (500 GC) | 2 | PRELIMINARY DESIGN | 2019-10-02 | 2020-01-29 | 2019-10-02 | 2020-01-29
20201123 | BRONX | 042 | CITY UNIVERSITY | HS058-020 | 2nd Floor & Basement Renovation/Final Phase (500 GC) | 3 | FINAL DESIGN | 2020-01-30 | 2020-07-27 | 2020-01-30 | 2020-07-27
20201123 | BRONX | 042 | CITY UNIVERSITY | HS058-020 | 2nd Floor & Basement Renovation/Final Phase (500 GC) | 4 | BID AWARD AND REGISTER CONTRCT | 2020-07-28 | 2020-10-25 | 2020-07-28 | 2020-10-25
20201123 | BRONX | 042 | CITY UNIVERSITY | HS058-020 | 2nd Floor & Basement Renovation/Final Phase (500 GC) | 5 | CONSTRUCTION TO 25% | 2020-10-26 | 2021-02-22 | 2020-10-26 | 2021-02-22
20201123 | BRONX | 042 | CITY UNIVERSITY | HS058-020 | 2nd Floor & Basement Renovation/Final Phase (500 GC) | 6 | CONSTRUCTION TO 50% | 2021-02-23 | 2021-06-22 | 2021-02-23 | 2021-06-22
20201123 | BRONX | 042 | CITY UNIVERSITY | HS058-020 | 2nd Floor & Basement Renovation/Final Phase (500 GC) | 7 | CONSTRUCTION TO 75% | 2021-06-23 | 2021-10-20 | 2021-06-23 | 2021-10-20
20201123 | BRONX | 042 | CITY UNIVERSITY | HS058-020 | 2nd Floor & Basement Renovation/Final Phase (500 GC) | 8 | ORIGINAL EQUIP & FURNISHING | 2021-10-21 | 2022-01-18 | 2021-10-21 | 2022-01-18
20201123 | BRONX | 042 | CITY UNIVERSITY | HS058-020 | 2nd Floor & Basement Renovation/Final Phase (500 GC) | 9 | SUBSTANTIAL COMPLETION | 2022-01-19 | 2022-03-19 | 2022-01-19 | 2022-03-19
20201123 | BRONX | 042 | CITY UNIVERSITY | HS058-020 | 2nd Floor & Basement Renovation/Final Phase (500 GC) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-20 | 2022-04-18 | 2022-03-20 | 2025-04-30
20201123 | BRONX | 042 | CITY UNIVERSITY | HS059-021 | Video Pojection | 1 | DEVELOP SCOPE | 2021-06-30 | 2021-09-27 | 2021-06-30 | 2021-09-27
20201123 | BRONX | 042 | CITY UNIVERSITY | HS059-021 | Video Pojection | 2 | PRELIMINARY DESIGN | 2021-09-28 | 2022-01-25 | 2021-09-28 | 2022-01-25
20201123 | BRONX | 042 | CITY UNIVERSITY | HS059-021 | Video Pojection | 3 | FINAL DESIGN | 2022-01-26 | 2022-07-24 | 2022-01-26 | 2022-07-24
20201123 | BRONX | 042 | CITY UNIVERSITY | HS059-021 | Video Pojection | 4 | BID AWARD AND REGISTER CONTRCT | 2022-07-25 | 2022-10-22 | 2022-07-25 | 2022-10-22
20201123 | BRONX | 042 | CITY UNIVERSITY | HS059-021 | Video Pojection | 5 | CONSTRUCTION TO 25% | 2022-10-23 | 2023-02-19 | 2022-10-23 | 2023-02-19
20201123 | BRONX | 042 | CITY UNIVERSITY | HS059-021 | Video Pojection | 6 | CONSTRUCTION TO 50% | 2023-02-20 | 2023-06-19 | 2023-02-20 | 2023-06-19
20201123 | BRONX | 042 | CITY UNIVERSITY | HS059-021 | Video Pojection | 7 | CONSTRUCTION TO 75% | 2023-06-20 | 2023-10-17 | 2023-06-20 | 2023-10-17
20201123 | BRONX | 042 | CITY UNIVERSITY | HS059-021 | Video Pojection | 8 | ORIGINAL EQUIP & FURNISHING | 2023-10-18 | 2024-01-15 | 2023-10-18 | 2024-01-15
20201123 | BRONX | 042 | CITY UNIVERSITY | HS059-021 | Video Pojection | 9 | SUBSTANTIAL COMPLETION | 2024-01-16 | 2024-03-15 | 2024-01-16 | 2024-03-15
20201123 | BRONX | 042 | CITY UNIVERSITY | HS059-021 | Video Pojection | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-03-16 | 2024-04-14 | 2024-03-16 | 2024-04-14
20201123 | BRONX | 042 | CITY UNIVERSITY | LM002-021 | Teaching and Learning Innovation Space - Art | 1 | DEVELOP SCOPE | 2021-06-30 | 2021-09-27 | 2021-06-30 | 2021-09-27
20201123 | BRONX | 042 | CITY UNIVERSITY | LM002-021 | Teaching and Learning Innovation Space - Art | 2 | PRELIMINARY DESIGN | 2021-09-28 | 2022-01-25 | 2021-09-28 | 2022-01-25
20201123 | BRONX | 042 | CITY UNIVERSITY | LM002-021 | Teaching and Learning Innovation Space - Art | 3 | FINAL DESIGN | 2022-01-26 | 2022-07-24 | 2022-01-26 | 2022-07-24
20201123 | BRONX | 042 | CITY UNIVERSITY | LM002-021 | Teaching and Learning Innovation Space - Art | 4 | BID AWARD AND REGISTER CONTRCT | 2022-07-25 | 2022-10-22 | 2022-07-25 | 2022-10-22
20201123 | BRONX | 042 | CITY UNIVERSITY | LM002-021 | Teaching and Learning Innovation Space - Art | 5 | CONSTRUCTION TO 25% | 2022-10-23 | 2023-02-19 | 2022-10-23 | 2023-02-19
20201123 | BRONX | 042 | CITY UNIVERSITY | LM002-021 | Teaching and Learning Innovation Space - Art | 6 | CONSTRUCTION TO 50% | 2023-02-20 | 2023-06-19 | 2023-02-20 | 2023-06-19
20201123 | BRONX | 042 | CITY UNIVERSITY | LM002-021 | Teaching and Learning Innovation Space - Art | 7 | CONSTRUCTION TO 75% | 2023-06-20 | 2023-10-17 | 2023-06-20 | 2023-10-17
20201123 | BRONX | 042 | CITY UNIVERSITY | LM002-021 | Teaching and Learning Innovation Space - Art | 8 | ORIGINAL EQUIP & FURNISHING | 2023-10-18 | 2024-01-15 | 2023-10-18 | 2024-01-15
20201123 | BRONX | 042 | CITY UNIVERSITY | LM002-021 | Teaching and Learning Innovation Space - Art | 9 | SUBSTANTIAL COMPLETION | 2024-01-16 | 2024-03-15 | 2024-01-16 | 2024-03-15
20201123 | BRONX | 042 | CITY UNIVERSITY | LM002-021 | Teaching and Learning Innovation Space - Art | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-03-16 | 2024-04-14 | 2024-03-16 | 2024-04-14
20201123 | BRONX | 042 | CITY UNIVERSITY | LM019-011 | Concert Hall Lighting Upgrade / Acoustics Upgrade | 1 | DEVELOP SCOPE | 2011-06-01 | 2011-08-29 | 2011-06-01 | 2011-08-29
20201123 | BRONX | 042 | CITY UNIVERSITY | LM019-011 | Concert Hall Lighting Upgrade / Acoustics Upgrade | 2 | PRELIMINARY DESIGN | 2011-08-30 | 2011-12-27 | 2011-08-30 | 2011-12-27
20201123 | BRONX | 042 | CITY UNIVERSITY | LM019-011 | Concert Hall Lighting Upgrade / Acoustics Upgrade | 3 | FINAL DESIGN | 2011-12-28 | 2012-06-24 | 2011-12-28 | 2012-06-24
20201123 | BRONX | 042 | CITY UNIVERSITY | LM019-011 | Concert Hall Lighting Upgrade / Acoustics Upgrade | 4 | BID AWARD AND REGISTER CONTRCT | 2012-06-25 | 2012-09-22 | 2012-06-25 | 2012-09-22
20201123 | BRONX | 042 | CITY UNIVERSITY | LM019-011 | Concert Hall Lighting Upgrade / Acoustics Upgrade | 5 | CONSTRUCTION TO 25% | 2012-09-23 | 2013-01-20 | 2012-09-23 | 2013-01-20
20201123 | BRONX | 042 | CITY UNIVERSITY | LM019-011 | Concert Hall Lighting Upgrade / Acoustics Upgrade | 6 | CONSTRUCTION TO 50% | 2013-01-21 | 2013-05-20 | 2013-01-21 | 2013-05-20
20201123 | BRONX | 042 | CITY UNIVERSITY | LM019-011 | Concert Hall Lighting Upgrade / Acoustics Upgrade | 7 | CONSTRUCTION TO 75% | 2013-05-21 | 2013-09-17 | 2013-05-21 | 2013-09-17
20201123 | BRONX | 042 | CITY UNIVERSITY | LM019-011 | Concert Hall Lighting Upgrade / Acoustics Upgrade | 8 | ORIGINAL EQUIP & FURNISHING | 2013-09-18 | 2013-12-16 | 2013-09-18 | 2013-12-16
20201123 | BRONX | 042 | CITY UNIVERSITY | LM019-011 | Concert Hall Lighting Upgrade / Acoustics Upgrade | 9 | SUBSTANTIAL COMPLETION | 2013-12-17 | 2014-02-14 | 2013-12-17 | 2014-02-14
20201123 | BRONX | 042 | CITY UNIVERSITY | LM019-011 | Concert Hall Lighting Upgrade / Acoustics Upgrade | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-02-15 | 2014-03-16 | 2014-02-15 | 2026-06-30
20201123 | BRONX | 042 | CITY UNIVERSITY | LM021-012 | Teaching and Learning Commons | 1 | DEVELOP SCOPE | 2012-06-01 | 2012-08-29 | 2012-06-01 | 2012-08-29
20201123 | BRONX | 042 | CITY UNIVERSITY | LM021-012 | Teaching and Learning Commons | 2 | PRELIMINARY DESIGN | 2012-08-30 | 2012-12-27 | 2012-08-30 | 2012-12-27
20201123 | BRONX | 042 | CITY UNIVERSITY | LM021-012 | Teaching and Learning Commons | 3 | FINAL DESIGN | 2012-12-28 | 2013-06-25 | 2012-12-28 | 2013-06-25
20201123 | BRONX | 042 | CITY UNIVERSITY | LM021-012 | Teaching and Learning Commons | 4 | BID AWARD AND REGISTER CONTRCT | 2013-06-26 | 2013-09-23 | 2013-06-26 | 2013-09-23
20201123 | BRONX | 042 | CITY UNIVERSITY | LM021-012 | Teaching and Learning Commons | 5 | CONSTRUCTION TO 25% | 2013-09-24 | 2014-01-21 | 2013-09-24 | 2014-01-21
20201123 | BRONX | 042 | CITY UNIVERSITY | LM021-012 | Teaching and Learning Commons | 6 | CONSTRUCTION TO 50% | 2014-01-22 | 2014-05-21 | 2014-01-22 | 2014-05-21
20201123 | BRONX | 042 | CITY UNIVERSITY | LM021-012 | Teaching and Learning Commons | 7 | CONSTRUCTION TO 75% | 2014-05-22 | 2014-09-18 | 2014-05-22 | 2014-09-18
20201123 | BRONX | 042 | CITY UNIVERSITY | LM021-012 | Teaching and Learning Commons | 8 | ORIGINAL EQUIP & FURNISHING | 2014-09-19 | 2014-12-17 | 2014-09-19 | 2014-12-17
20201123 | BRONX | 042 | CITY UNIVERSITY | LM021-012 | Teaching and Learning Commons | 9 | SUBSTANTIAL COMPLETION | 2014-12-18 | 2015-02-15 | 2014-12-18 | 2015-02-15
20201123 | BRONX | 042 | CITY UNIVERSITY | LM021-012 | Teaching and Learning Commons | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-02-16 | 2015-03-17 | 2015-02-16 | 2023-03-30
20201123 | BRONX | 042 | CITY UNIVERSITY | LM022-013 | One-Stop Student Services & Transfer Center | 1 | DEVELOP SCOPE | 2013-06-01 | 2013-08-29 | 2013-06-01 | 2013-08-29
20201123 | BRONX | 042 | CITY UNIVERSITY | LM022-013 | One-Stop Student Services & Transfer Center | 2 | PRELIMINARY DESIGN | 2013-08-30 | 2013-12-27 | 2013-08-30 | 2013-12-27
20201123 | BRONX | 042 | CITY UNIVERSITY | LM022-013 | One-Stop Student Services & Transfer Center | 3 | FINAL DESIGN | 2013-12-28 | 2014-06-25 | 2013-12-28 | 2014-06-25
20201123 | BRONX | 042 | CITY UNIVERSITY | LM022-013 | One-Stop Student Services & Transfer Center | 4 | BID AWARD AND REGISTER CONTRCT | 2014-06-26 | 2014-09-23 | 2014-06-26 | 2014-09-23
20201123 | BRONX | 042 | CITY UNIVERSITY | LM022-013 | One-Stop Student Services & Transfer Center | 5 | CONSTRUCTION TO 25% | 2014-09-24 | 2015-01-21 | 2014-09-24 | 2015-01-21
20201123 | BRONX | 042 | CITY UNIVERSITY | LM022-013 | One-Stop Student Services & Transfer Center | 6 | CONSTRUCTION TO 50% | 2015-01-22 | 2015-05-21 | 2015-01-22 | 2015-05-21
20201123 | BRONX | 042 | CITY UNIVERSITY | LM022-013 | One-Stop Student Services & Transfer Center | 7 | CONSTRUCTION TO 75% | 2015-05-22 | 2015-09-18 | 2015-05-22 | 2015-09-18
20201123 | BRONX | 042 | CITY UNIVERSITY | LM022-013 | One-Stop Student Services & Transfer Center | 8 | ORIGINAL EQUIP & FURNISHING | 2015-09-19 | 2015-12-17 | 2015-09-19 | 2015-12-17
20201123 | BRONX | 042 | CITY UNIVERSITY | LM022-013 | One-Stop Student Services & Transfer Center | 9 | SUBSTANTIAL COMPLETION | 2015-12-18 | 2016-02-15 | 2015-12-18 | 2016-02-15
20201123 | BRONX | 042 | CITY UNIVERSITY | LM022-013 | One-Stop Student Services & Transfer Center | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-02-16 | 2016-03-16 | 2016-02-16 | 2016-03-16
20201123 | BRONX | 042 | CITY UNIVERSITY | LM025-014 | Cloudlink Student Lab Virtual Desktop (iCloud Upgrade) | 3 | FINAL DESIGN | 2014-12-28 | 2015-06-25 | 2014-12-28 | 2015-06-25
20201123 | BRONX | 042 | CITY UNIVERSITY | LM025-014 | Cloudlink Student Lab Virtual Desktop (iCloud Upgrade) | 4 | BID AWARD AND REGISTER CONTRCT | 2015-06-26 | 2015-09-23 | 2015-06-26 | 2015-09-23
20201123 | BRONX | 042 | CITY UNIVERSITY | LM025-014 | Cloudlink Student Lab Virtual Desktop (iCloud Upgrade) | 5 | CONSTRUCTION TO 25% | 2015-09-24 | 2016-01-21 | 2015-09-24 | 2016-01-21
20201123 | BRONX | 042 | CITY UNIVERSITY | LM025-014 | Cloudlink Student Lab Virtual Desktop (iCloud Upgrade) | 6 | CONSTRUCTION TO 50% | 2016-01-22 | 2016-05-20 | 2016-01-22 | 2016-05-20
20201123 | BRONX | 042 | CITY UNIVERSITY | LM025-014 | Cloudlink Student Lab Virtual Desktop (iCloud Upgrade) | 7 | CONSTRUCTION TO 75% | 2016-05-21 | 2016-09-17 | 2016-05-21 | 2016-09-17
20201123 | BRONX | 042 | CITY UNIVERSITY | LM025-014 | Cloudlink Student Lab Virtual Desktop (iCloud Upgrade) | 8 | ORIGINAL EQUIP & FURNISHING | 2016-09-18 | 2016-12-16 | 2016-09-18 | 2016-12-16
20201123 | BRONX | 042 | CITY UNIVERSITY | LM025-014 | Cloudlink Student Lab Virtual Desktop (iCloud Upgrade) | 9 | SUBSTANTIAL COMPLETION | 2016-12-17 | 2017-02-14 | 2016-12-17 | 2017-02-14
20201123 | BRONX | 042 | CITY UNIVERSITY | LM025-014 | Cloudlink Student Lab Virtual Desktop (iCloud Upgrade) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-02-15 | 2017-03-16 | 2017-02-15 | 2020-03-30
20201123 | BRONX | 042 | CITY UNIVERSITY | LM027-015 | Lecture Hall Renovations | 5 | CONSTRUCTION TO 25% | 2016-01-24 | 2016-05-22 | 2016-01-24 | 2016-05-22
20201123 | BRONX | 042 | CITY UNIVERSITY | LM027-015 | Lecture Hall Renovations | 6 | CONSTRUCTION TO 50% | 2016-05-23 | 2016-09-19 | 2016-05-23 | 2016-09-19
20201123 | BRONX | 042 | CITY UNIVERSITY | LM027-015 | Lecture Hall Renovations | 7 | CONSTRUCTION TO 75% | 2016-09-20 | 2017-01-17 | 2016-09-20 | 2017-01-17
20201123 | BRONX | 042 | CITY UNIVERSITY | LM027-015 | Lecture Hall Renovations | 8 | ORIGINAL EQUIP & FURNISHING | 2017-01-18 | 2017-04-17 | 2017-01-18 | 2017-04-17
20201123 | BRONX | 042 | CITY UNIVERSITY | LM027-015 | Lecture Hall Renovations | 9 | SUBSTANTIAL COMPLETION | 2017-04-18 | 2017-06-16 | 2017-04-18 | 2017-06-16
20201123 | BRONX | 042 | CITY UNIVERSITY | LM027-015 | Lecture Hall Renovations | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-06-17 | 2017-07-16 | 2017-06-17 | 2020-07-31
20201123 | BRONX | 042 | CITY UNIVERSITY | LM029016 | Upgrade and Convert Carman Hall | 1 | DEVELOP SCOPE | 2016-06-30 | 2016-09-27 | 2021-07-01 | 2021-09-28
20201123 | BRONX | 042 | CITY UNIVERSITY | LM029016 | Upgrade and Convert Carman Hall | 2 | PRELIMINARY DESIGN | 2016-09-28 | 2017-01-25 | 2021-09-29 | 2022-01-26
20201123 | BRONX | 042 | CITY UNIVERSITY | LM029016 | Upgrade and Convert Carman Hall | 3 | FINAL DESIGN | 2017-01-26 | 2017-07-24 | 2022-01-27 | 2022-07-25
20201123 | BRONX | 042 | CITY UNIVERSITY | LM029016 | Upgrade and Convert Carman Hall | 4 | BID AWARD AND REGISTER CONTRCT | 2017-07-25 | 2017-10-22 | 2022-07-26 | 2022-10-23
20201123 | BRONX | 042 | CITY UNIVERSITY | LM029016 | Upgrade and Convert Carman Hall | 5 | CONSTRUCTION TO 25% | 2017-10-23 | 2018-02-19 | 2022-10-24 | 2023-02-20
20201123 | BRONX | 042 | CITY UNIVERSITY | LM029016 | Upgrade and Convert Carman Hall | 6 | CONSTRUCTION TO 50% | 2018-02-20 | 2018-06-19 | 2023-02-21 | 2023-06-20
20201123 | BRONX | 042 | CITY UNIVERSITY | LM029016 | Upgrade and Convert Carman Hall | 7 | CONSTRUCTION TO 75% | 2018-06-20 | 2018-10-17 | 2023-06-21 | 2023-10-18
20201123 | BRONX | 042 | CITY UNIVERSITY | LM029016 | Upgrade and Convert Carman Hall | 8 | ORIGINAL EQUIP & FURNISHING | 2018-10-18 | 2019-01-15 | 2023-10-19 | 2024-01-16
20201123 | BRONX | 042 | CITY UNIVERSITY | LM029016 | Upgrade and Convert Carman Hall | 9 | SUBSTANTIAL COMPLETION | 2019-01-16 | 2019-03-16 | 2024-01-17 | 2024-03-16
20201123 | BRONX | 042 | CITY UNIVERSITY | LM029016 | Upgrade and Convert Carman Hall | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-03-17 | 2019-04-15 | 2024-03-17 | 2024-07-15
20201123 | BRONX | 042 | CITY UNIVERSITY | LM032-017 | Gillet Auditorium Renovation | 1 | DEVELOP SCOPE | 2017-06-01 | 2017-08-29 | 2021-07-01 | 2021-09-29
20201123 | BRONX | 042 | CITY UNIVERSITY | LM032-017 | Gillet Auditorium Renovation | 2 | PRELIMINARY DESIGN | 2017-08-30 | 2017-12-27 | 2021-09-30 | 2022-01-27
20201123 | BRONX | 042 | CITY UNIVERSITY | LM032-017 | Gillet Auditorium Renovation | 3 | FINAL DESIGN | 2017-12-28 | 2018-06-25 | 2022-01-28 | 2022-07-26
20201123 | BRONX | 042 | CITY UNIVERSITY | LM032-017 | Gillet Auditorium Renovation | 4 | BID AWARD AND REGISTER CONTRCT | 2018-06-26 | 2018-09-23 | 2022-07-27 | 2022-10-24
20201123 | BRONX | 042 | CITY UNIVERSITY | LM032-017 | Gillet Auditorium Renovation | 5 | CONSTRUCTION TO 25% | 2018-09-24 | 2019-01-21 | 2022-10-25 | 2023-02-21
20201123 | BRONX | 042 | CITY UNIVERSITY | LM032-017 | Gillet Auditorium Renovation | 6 | CONSTRUCTION TO 50% | 2019-01-22 | 2019-05-21 | 2023-02-22 | 2023-06-21
20201123 | BRONX | 042 | CITY UNIVERSITY | LM032-017 | Gillet Auditorium Renovation | 7 | CONSTRUCTION TO 75% | 2019-05-22 | 2019-09-18 | 2023-06-22 | 2023-10-19
20201123 | BRONX | 042 | CITY UNIVERSITY | LM032-017 | Gillet Auditorium Renovation | 8 | ORIGINAL EQUIP & FURNISHING | 2019-09-19 | 2019-12-17 | 2023-10-20 | 2024-01-17
20201123 | BRONX | 042 | CITY UNIVERSITY | LM032-017 | Gillet Auditorium Renovation | 9 | SUBSTANTIAL COMPLETION | 2019-12-18 | 2020-02-15 | 2024-01-18 | 2024-03-17
20201123 | BRONX | 042 | CITY UNIVERSITY | LM032-017 | Gillet Auditorium Renovation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-02-16 | 2020-03-16 | 2024-03-18 | 2024-04-16
20201123 | BRONX | 042 | CITY UNIVERSITY | LM034-018 | Convert classrooms into NetworkSmart Rooms | 1 | DEVELOP SCOPE | 2018-06-01 | 2018-08-29 | 2021-07-01 | 2021-09-28
20201123 | BRONX | 042 | CITY UNIVERSITY | LM034-018 | Convert classrooms into NetworkSmart Rooms | 2 | PRELIMINARY DESIGN | 2018-08-30 | 2018-12-27 | 2021-09-29 | 2022-01-26
20201123 | BRONX | 042 | CITY UNIVERSITY | LM034-018 | Convert classrooms into NetworkSmart Rooms | 3 | FINAL DESIGN | 2018-12-28 | 2019-06-25 | 2022-01-27 | 2022-07-25
20201123 | BRONX | 042 | CITY UNIVERSITY | LM034-018 | Convert classrooms into NetworkSmart Rooms | 4 | BID AWARD AND REGISTER CONTRCT | 2019-06-26 | 2019-09-23 | 2022-07-26 | 2022-10-23
20201123 | BRONX | 042 | CITY UNIVERSITY | LM034-018 | Convert classrooms into NetworkSmart Rooms | 5 | CONSTRUCTION TO 25% | 2019-09-24 | 2020-01-21 | 2022-10-24 | 2023-02-20
20201123 | BRONX | 042 | CITY UNIVERSITY | LM034-018 | Convert classrooms into NetworkSmart Rooms | 6 | CONSTRUCTION TO 50% | 2020-01-22 | 2020-05-20 | 2023-02-21 | 2023-06-20
20201123 | BRONX | 042 | CITY UNIVERSITY | LM034-018 | Convert classrooms into NetworkSmart Rooms | 7 | CONSTRUCTION TO 75% | 2020-05-21 | 2020-09-17 | 2023-06-21 | 2023-10-18
20201123 | BRONX | 042 | CITY UNIVERSITY | LM034-018 | Convert classrooms into NetworkSmart Rooms | 8 | ORIGINAL EQUIP & FURNISHING | 2020-09-18 | 2020-12-16 | 2023-10-19 | 2024-01-16
20201123 | BRONX | 042 | CITY UNIVERSITY | LM034-018 | Convert classrooms into NetworkSmart Rooms | 9 | SUBSTANTIAL COMPLETION | 2020-12-17 | 2021-02-14 | 2024-01-17 | 2024-03-16
20201123 | BRONX | 042 | CITY UNIVERSITY | LM034-018 | Convert classrooms into NetworkSmart Rooms | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-02-15 | 2021-03-16 | 2024-03-17 | 2024-07-15
20201123 | BRONX | 042 | CITY UNIVERSITY | LM035-018 | Gillet Auditorium Renovation | 1 | DEVELOP SCOPE | 2018-06-01 | 2018-08-29 | 2021-07-01 | 2021-09-29
20201123 | BRONX | 042 | CITY UNIVERSITY | LM035-018 | Gillet Auditorium Renovation | 2 | PRELIMINARY DESIGN | 2018-08-30 | 2018-12-27 | 2021-09-30 | 2022-01-27
20201123 | BRONX | 042 | CITY UNIVERSITY | LM035-018 | Gillet Auditorium Renovation | 3 | FINAL DESIGN | 2018-12-28 | 2019-06-25 | 2022-01-28 | 2022-07-26
20201123 | BRONX | 042 | CITY UNIVERSITY | LM035-018 | Gillet Auditorium Renovation | 4 | BID AWARD AND REGISTER CONTRCT | 2019-06-26 | 2019-09-23 | 2022-07-27 | 2022-10-24
20201123 | BRONX | 042 | CITY UNIVERSITY | LM035-018 | Gillet Auditorium Renovation | 5 | CONSTRUCTION TO 25% | 2019-09-24 | 2020-01-21 | 2022-10-25 | 2023-02-21
20201123 | BRONX | 042 | CITY UNIVERSITY | LM035-018 | Gillet Auditorium Renovation | 6 | CONSTRUCTION TO 50% | 2020-01-22 | 2020-05-20 | 2023-02-22 | 2023-06-21
20201123 | BRONX | 042 | CITY UNIVERSITY | LM035-018 | Gillet Auditorium Renovation | 7 | CONSTRUCTION TO 75% | 2020-05-21 | 2020-09-17 | 2023-06-22 | 2023-10-19
20201123 | BRONX | 042 | CITY UNIVERSITY | LM035-018 | Gillet Auditorium Renovation | 8 | ORIGINAL EQUIP & FURNISHING | 2020-09-18 | 2020-12-16 | 2023-10-20 | 2024-01-17
20201123 | BRONX | 042 | CITY UNIVERSITY | LM035-018 | Gillet Auditorium Renovation | 9 | SUBSTANTIAL COMPLETION | 2020-12-17 | 2021-02-14 | 2024-01-18 | 2024-03-17
20201123 | BRONX | 042 | CITY UNIVERSITY | LM035-018 | Gillet Auditorium Renovation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-02-15 | 2021-03-16 | 2024-03-18 | 2024-04-16
20201123 | BRONX | 042 | CITY UNIVERSITY | LM036-019 | Concert Hall Fixed Seating | 1 | DEVELOP SCOPE | 2018-06-30 | 2018-09-27 | 2018-06-30 | 2018-09-27
20201123 | BRONX | 042 | CITY UNIVERSITY | LM036-019 | Concert Hall Fixed Seating | 2 | PRELIMINARY DESIGN | 2018-09-28 | 2019-01-25 | 2018-09-28 | 2019-01-25
20201123 | BRONX | 042 | CITY UNIVERSITY | LM036-019 | Concert Hall Fixed Seating | 3 | FINAL DESIGN | 2019-01-26 | 2019-07-24 | 2019-01-26 | 2019-07-24
20201123 | BRONX | 042 | CITY UNIVERSITY | LM036-019 | Concert Hall Fixed Seating | 4 | BID AWARD AND REGISTER CONTRCT | 2019-07-25 | 2019-10-22 | 2019-07-25 | 2019-10-22
20201123 | BRONX | 042 | CITY UNIVERSITY | LM036-019 | Concert Hall Fixed Seating | 5 | CONSTRUCTION TO 25% | 2019-10-23 | 2020-02-19 | 2019-10-23 | 2020-02-19
20201123 | BRONX | 042 | CITY UNIVERSITY | LM036-019 | Concert Hall Fixed Seating | 6 | CONSTRUCTION TO 50% | 2020-02-20 | 2020-06-18 | 2020-02-20 | 2020-06-18
20201123 | BRONX | 042 | CITY UNIVERSITY | LM036-019 | Concert Hall Fixed Seating | 7 | CONSTRUCTION TO 75% | 2020-06-19 | 2020-10-16 | 2020-06-19 | 2020-10-16
20201123 | BRONX | 042 | CITY UNIVERSITY | LM036-019 | Concert Hall Fixed Seating | 8 | ORIGINAL EQUIP & FURNISHING | 2020-10-17 | 2021-01-14 | 2020-10-17 | 2021-01-14
20201123 | BRONX | 042 | CITY UNIVERSITY | LM036-019 | Concert Hall Fixed Seating | 9 | SUBSTANTIAL COMPLETION | 2021-01-15 | 2021-03-15 | 2021-01-15 | 2021-03-15
20201123 | BRONX | 042 | CITY UNIVERSITY | LM036-019 | Concert Hall Fixed Seating | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-16 | 2021-04-14 | 2021-03-16 | 2023-04-30
20201123 | BRONX | 042 | CITY UNIVERSITY | LM041-020 | Studio Theatre Lighting & Dimming System | 1 | DEVELOP SCOPE | 2021-07-01 | 2021-09-28 | 2021-07-01 | 2021-09-28
20201123 | BRONX | 042 | CITY UNIVERSITY | LM041-020 | Studio Theatre Lighting & Dimming System | 2 | PRELIMINARY DESIGN | 2021-09-29 | 2022-01-26 | 2021-09-29 | 2022-01-26
20201123 | BRONX | 042 | CITY UNIVERSITY | LM041-020 | Studio Theatre Lighting & Dimming System | 3 | FINAL DESIGN | 2022-01-27 | 2022-07-25 | 2022-01-27 | 2022-07-25
20201123 | BRONX | 042 | CITY UNIVERSITY | LM041-020 | Studio Theatre Lighting & Dimming System | 4 | BID AWARD AND REGISTER CONTRCT | 2022-07-26 | 2022-10-23 | 2022-07-26 | 2022-10-23
20201123 | BRONX | 042 | CITY UNIVERSITY | LM041-020 | Studio Theatre Lighting & Dimming System | 5 | CONSTRUCTION TO 25% | 2022-10-24 | 2023-02-20 | 2022-10-24 | 2023-02-20
20201123 | BRONX | 042 | CITY UNIVERSITY | LM041-020 | Studio Theatre Lighting & Dimming System | 6 | CONSTRUCTION TO 50% | 2023-02-21 | 2023-06-20 | 2023-02-21 | 2023-06-20
20201123 | BRONX | 042 | CITY UNIVERSITY | LM041-020 | Studio Theatre Lighting & Dimming System | 7 | CONSTRUCTION TO 75% | 2023-06-21 | 2023-10-18 | 2023-06-21 | 2023-10-18
20201123 | BRONX | 042 | CITY UNIVERSITY | LM041-020 | Studio Theatre Lighting & Dimming System | 8 | ORIGINAL EQUIP & FURNISHING | 2023-10-19 | 2024-01-16 | 2023-10-19 | 2024-01-16
20201123 | BRONX | 042 | CITY UNIVERSITY | LM041-020 | Studio Theatre Lighting & Dimming System | 9 | SUBSTANTIAL COMPLETION | 2024-01-17 | 2024-03-16 | 2024-01-17 | 2024-03-16
20201123 | BRONX | 042 | CITY UNIVERSITY | LM041-020 | Studio Theatre Lighting & Dimming System | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-03-17 | 2024-04-15 | 2024-03-17 | 2024-04-15
20201123 | BRONX | 042 | CITY UNIVERSITY | LM042-020 | Nursing Facility Construction, Furniture and Equipment | 1 | DEVELOP SCOPE | 2021-07-01 | 2021-09-29 | 2021-07-01 | 2021-09-29
20201123 | BRONX | 042 | CITY UNIVERSITY | LM042-020 | Nursing Facility Construction, Furniture and Equipment | 2 | PRELIMINARY DESIGN | 2021-09-30 | 2022-01-27 | 2021-09-30 | 2022-01-27
20201123 | BRONX | 042 | CITY UNIVERSITY | LM042-020 | Nursing Facility Construction, Furniture and Equipment | 3 | FINAL DESIGN | 2022-01-28 | 2022-07-26 | 2022-01-28 | 2022-07-26
20201123 | BRONX | 042 | CITY UNIVERSITY | LM042-020 | Nursing Facility Construction, Furniture and Equipment | 4 | BID AWARD AND REGISTER CONTRCT | 2022-07-27 | 2022-10-24 | 2022-07-27 | 2022-10-24
20201123 | BRONX | 042 | CITY UNIVERSITY | LM042-020 | Nursing Facility Construction, Furniture and Equipment | 5 | CONSTRUCTION TO 25% | 2022-10-25 | 2023-02-21 | 2022-10-25 | 2023-02-21
20201123 | BRONX | 042 | CITY UNIVERSITY | LM042-020 | Nursing Facility Construction, Furniture and Equipment | 6 | CONSTRUCTION TO 50% | 2023-02-22 | 2023-06-21 | 2023-02-22 | 2023-06-21
20201123 | BRONX | 042 | CITY UNIVERSITY | LM042-020 | Nursing Facility Construction, Furniture and Equipment | 7 | CONSTRUCTION TO 75% | 2023-06-22 | 2023-10-19 | 2023-06-22 | 2023-10-19
20201123 | BRONX | 042 | CITY UNIVERSITY | LM042-020 | Nursing Facility Construction, Furniture and Equipment | 8 | ORIGINAL EQUIP & FURNISHING | 2023-10-20 | 2024-01-17 | 2023-10-20 | 2024-01-17
20201123 | BRONX | 042 | CITY UNIVERSITY | LM042-020 | Nursing Facility Construction, Furniture and Equipment | 9 | SUBSTANTIAL COMPLETION | 2024-01-18 | 2024-03-17 | 2024-01-18 | 2024-03-17
20201123 | BRONX | 042 | CITY UNIVERSITY | LM042-020 | Nursing Facility Construction, Furniture and Equipment | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-03-18 | 2024-04-16 | 2024-03-18 | 2024-04-16
20201123 | BRONX | 042 | CITY UNIVERSITY | LM043-021 | Social Work Deppartment Expansion | 1 | DEVELOP SCOPE | 2021-06-30 | 2021-09-27 | 2021-06-30 | 2021-09-27
20201123 | BRONX | 042 | CITY UNIVERSITY | LM043-021 | Social Work Deppartment Expansion | 2 | PRELIMINARY DESIGN | 2021-09-28 | 2022-01-25 | 2021-09-28 | 2022-01-25
20201123 | BRONX | 042 | CITY UNIVERSITY | LM043-021 | Social Work Deppartment Expansion | 3 | FINAL DESIGN | 2022-01-26 | 2022-07-24 | 2022-01-26 | 2022-07-24
20201123 | BRONX | 042 | CITY UNIVERSITY | LM043-021 | Social Work Deppartment Expansion | 4 | BID AWARD AND REGISTER CONTRCT | 2022-07-25 | 2022-10-22 | 2022-07-25 | 2022-10-22
20201123 | BRONX | 042 | CITY UNIVERSITY | LM043-021 | Social Work Deppartment Expansion | 5 | CONSTRUCTION TO 25% | 2022-10-23 | 2023-02-19 | 2022-10-23 | 2023-02-19
20201123 | BRONX | 042 | CITY UNIVERSITY | LM043-021 | Social Work Deppartment Expansion | 6 | CONSTRUCTION TO 50% | 2023-02-20 | 2023-06-19 | 2023-02-20 | 2023-06-19
20201123 | BRONX | 042 | CITY UNIVERSITY | LM043-021 | Social Work Deppartment Expansion | 7 | CONSTRUCTION TO 75% | 2023-06-20 | 2023-10-17 | 2023-06-20 | 2023-10-17
20201123 | BRONX | 042 | CITY UNIVERSITY | LM043-021 | Social Work Deppartment Expansion | 8 | ORIGINAL EQUIP & FURNISHING | 2023-10-18 | 2024-01-15 | 2023-10-18 | 2024-01-15
20201123 | BRONX | 042 | CITY UNIVERSITY | LM043-021 | Social Work Deppartment Expansion | 9 | SUBSTANTIAL COMPLETION | 2024-01-16 | 2024-03-15 | 2024-01-16 | 2024-03-15
20201123 | BRONX | 042 | CITY UNIVERSITY | LM043-021 | Social Work Deppartment Expansion | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-03-16 | 2024-04-14 | 2024-03-16 | 2024-04-14
20201123 | BRONX | 042 | CITY UNIVERSITY | LM058-995 | KIOSK AND DIRECTIONAL SIGNAGE ON CAMPUS | 2 | PRELIMINARY DESIGN | 2007-05-30 | 2007-09-26 | 2007-05-30 | 2007-09-26
20201123 | BRONX | 042 | CITY UNIVERSITY | LM058-995 | KIOSK AND DIRECTIONAL SIGNAGE ON CAMPUS | 3 | FINAL DESIGN | 2007-09-27 | 2008-03-24 | 2007-09-27 | 2008-03-24
20201123 | BRONX | 042 | CITY UNIVERSITY | LM058-995 | KIOSK AND DIRECTIONAL SIGNAGE ON CAMPUS | 4 | BID AWARD AND REGISTER CONTRCT | 2008-03-25 | 2008-06-22 | 2008-03-25 | 2008-06-22
20201123 | BRONX | 042 | CITY UNIVERSITY | LM058-995 | KIOSK AND DIRECTIONAL SIGNAGE ON CAMPUS | 5 | CONSTRUCTION TO 25% | 2008-06-23 | 2008-10-20 | 2008-06-23 | 2008-10-20
20201123 | BRONX | 042 | CITY UNIVERSITY | LM058-995 | KIOSK AND DIRECTIONAL SIGNAGE ON CAMPUS | 6 | CONSTRUCTION TO 50% | 2008-10-21 | 2009-02-17 | 2008-10-21 | 2009-02-17
20201123 | BRONX | 042 | CITY UNIVERSITY | LM058-995 | KIOSK AND DIRECTIONAL SIGNAGE ON CAMPUS | 7 | CONSTRUCTION TO 75% | 2009-02-18 | 2009-06-17 | 2009-02-18 | 2009-06-17
20201123 | BRONX | 042 | CITY UNIVERSITY | LM058-995 | KIOSK AND DIRECTIONAL SIGNAGE ON CAMPUS | 8 | ORIGINAL EQUIP & FURNISHING | 2009-06-18 | 2009-09-15 | 2009-06-18 | 2009-09-15
20201123 | BRONX | 042 | CITY UNIVERSITY | LM058-995 | KIOSK AND DIRECTIONAL SIGNAGE ON CAMPUS | 9 | SUBSTANTIAL COMPLETION | 2009-09-16 | 2009-11-14 | 2009-09-16 | 2009-11-14
20201123 | BRONX | 042 | CITY UNIVERSITY | LM058-995 | KIOSK AND DIRECTIONAL SIGNAGE ON CAMPUS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2009-11-15 | 2009-12-14 | 2009-11-15 | 2011-05-14
20201123 | BRONX | 056 | POLICE DEPARTMENT | P-103CCAM | Crotona Park - Security Cameras | 3 | BID/ REGISTER CONTRACT | 2014-12-28 | 2015-03-27 | 2014-12-28 | 2015-03-27
20201123 | BRONX | 056 | POLICE DEPARTMENT | P-103CCAM | Crotona Park - Security Cameras | 4 | CONSTRUCTION | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2016-03-26
20201123 | BRONX | 056 | POLICE DEPARTMENT | P-103CCAM | Crotona Park - Security Cameras | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | BRONX | 056 | POLICE DEPARTMENT | PO79-52P | 52ND PRECINCT RENOVATION | 1 | DESIGN | 2020-07-30 | 2021-01-25 | 2020-07-30 | 2021-01-25
20201123 | BRONX | 056 | POLICE DEPARTMENT | PO79-52P | 52ND PRECINCT RENOVATION | 2 | BID AWARD AND REGISTER CONTRCT | 2021-01-26 | 2021-04-25 | 2021-01-26 | 2021-04-25
20201123 | BRONX | 056 | POLICE DEPARTMENT | PO79-52P | 52ND PRECINCT RENOVATION | 3 | CONSTRUCTION | 2021-04-26 | 2022-04-25 | 2022-04-26 | 2022-04-25
20201123 | BRONX | 056 | POLICE DEPARTMENT | PO79-52P | 52ND PRECINCT RENOVATION | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-04-26 | 2022-10-22 | 2022-04-26 | 2023-10-22
20201123 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAJX | 46th PRECINCT ADA RAMP | 1 | DESIGN | 2018-09-20 | 2019-03-18 | 2018-09-20 | 2019-03-18
20201123 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAJX | 46th PRECINCT ADA RAMP | 2 | BID AWARD AND REGISTER CONTRCT | 2019-03-19 | 2019-06-16 | 2019-03-19 | 2019-06-16
20201123 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAJX | 46th PRECINCT ADA RAMP | 3 | CONSTRUCTION | 2019-06-17 | 2020-06-15 | 2019-06-17 | 2020-06-15
20201123 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAJX | 46th PRECINCT ADA RAMP | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-06-16 | 2020-12-12 | 2020-06-16 | 2020-12-12
20201123 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAKD | RODMAN'S NECK BATHROOM TRAILERS | 1 | DEVELOP SCOPE | 2019-10-01 | 2019-12-29 | 2019-10-01 | 2019-12-29
20201123 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAKD | RODMAN'S NECK BATHROOM TRAILERS | 2 | PRELIMINARY DESIGN | 2019-12-30 | 2020-04-27 | 2019-12-30 | 2020-04-27
20201123 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAKD | RODMAN'S NECK BATHROOM TRAILERS | 3 | FINAL DESIGN | 2020-04-28 | 2020-08-25 | 2020-04-28 | 2020-08-25
20201123 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAKD | RODMAN'S NECK BATHROOM TRAILERS | 4 | BID AWARD AND REGISTER CONTRCT | 2020-08-26 | 2021-02-21 | 2020-08-26 | 2021-02-21
20201123 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAKD | RODMAN'S NECK BATHROOM TRAILERS | 5 | CONSTRUCTION TO 25% | 2021-02-22 | 2021-06-21 | 2021-02-22 | 2021-06-21
20201123 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAKD | RODMAN'S NECK BATHROOM TRAILERS | 6 | CONSTRUCTION TO 50% | 2021-06-22 | 2021-10-19 | 2021-06-22 | 2021-10-19
20201123 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAKD | RODMAN'S NECK BATHROOM TRAILERS | 7 | CONSTRUCTION TO 75% | 2021-10-20 | 2022-02-16 | 2021-10-20 | 2022-02-16
20201123 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAKD | RODMAN'S NECK BATHROOM TRAILERS | 8 | ORIGINAL EQUIP & FURNISHING | 2022-02-17 | 2022-05-17 | 2022-02-17 | 2022-05-17
20201123 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAKD | RODMAN'S NECK BATHROOM TRAILERS | 9 | SUBSTANTIAL COMPLETION | 2022-05-18 | 2022-07-16 | 2022-05-18 | 2022-07-16
20201123 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAKD | RODMAN'S NECK BATHROOM TRAILERS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-07-17 | 2022-08-15 | 2022-07-17 | 2022-08-15
20201123 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAKK | REHABILITATION OF 48TH PCT ELEVATOR | 1 | DEVELOP SCOPE | 2020-12-10 | 2021-03-09 | 2020-12-10 | 2021-03-09
20201123 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAKK | REHABILITATION OF 48TH PCT ELEVATOR | 2 | PRELIMINARY DESIGN | 2021-03-10 | 2021-07-07 | 2021-03-10 | 2021-07-07
20201123 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAKK | REHABILITATION OF 48TH PCT ELEVATOR | 3 | FINAL DESIGN | 2021-07-08 | 2021-11-04 | 2021-07-08 | 2021-11-04
20201123 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAKK | REHABILITATION OF 48TH PCT ELEVATOR | 4 | BID AWARD AND REGISTER CONTRCT | 2021-11-05 | 2022-05-03 | 2021-11-05 | 2022-05-03
20201123 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAKK | REHABILITATION OF 48TH PCT ELEVATOR | 5 | CONSTRUCTION TO 25% | 2022-05-04 | 2022-08-31 | 2022-05-04 | 2022-08-31
20201123 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAKK | REHABILITATION OF 48TH PCT ELEVATOR | 6 | CONSTRUCTION TO 50% | 2022-09-01 | 2022-12-29 | 2022-09-01 | 2022-12-29
20201123 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAKK | REHABILITATION OF 48TH PCT ELEVATOR | 7 | CONSTRUCTION TO 75% | 2022-12-30 | 2023-04-28 | 2022-12-30 | 2023-04-28
20201123 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAKK | REHABILITATION OF 48TH PCT ELEVATOR | 8 | ORIGINAL EQUIP & FURNISHING | 2023-04-29 | 2023-07-27 | 2023-04-29 | 2023-07-27
20201123 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAKK | REHABILITATION OF 48TH PCT ELEVATOR | 9 | SUBSTANTIAL COMPLETION | 2023-07-28 | 2023-09-25 | 2023-07-28 | 2023-09-25
20201123 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAKK | REHABILITATION OF 48TH PCT ELEVATOR | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-26 | 2023-10-25 | 2023-09-26 | 2023-10-25
20201123 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAKO | ROOF REPLACEMENT AT 49TH PCT | 1 | DEVELOP SCOPE | 2020-12-10 | 2021-03-09 | 2020-12-10 | 2021-03-09
20201123 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAKO | ROOF REPLACEMENT AT 49TH PCT | 2 | PRELIMINARY DESIGN | 2021-03-10 | 2021-07-07 | 2021-03-10 | 2021-07-07
20201123 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAKO | ROOF REPLACEMENT AT 49TH PCT | 3 | FINAL DESIGN | 2021-07-08 | 2021-11-04 | 2021-07-08 | 2021-11-04
20201123 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAKO | ROOF REPLACEMENT AT 49TH PCT | 4 | BID AWARD AND REGISTER CONTRCT | 2021-11-05 | 2022-05-03 | 2021-11-05 | 2022-05-03
20201123 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAKO | ROOF REPLACEMENT AT 49TH PCT | 5 | CONSTRUCTION TO 25% | 2022-05-04 | 2022-08-31 | 2022-05-04 | 2022-08-31
20201123 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAKO | ROOF REPLACEMENT AT 49TH PCT | 6 | CONSTRUCTION TO 50% | 2022-09-01 | 2022-12-29 | 2022-09-01 | 2022-12-29
20201123 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAKO | ROOF REPLACEMENT AT 49TH PCT | 7 | CONSTRUCTION TO 75% | 2022-12-30 | 2023-04-28 | 2022-12-30 | 2023-04-28
20201123 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAKO | ROOF REPLACEMENT AT 49TH PCT | 8 | ORIGINAL EQUIP & FURNISHING | 2023-04-29 | 2023-07-27 | 2023-04-29 | 2023-07-27
20201123 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAKO | ROOF REPLACEMENT AT 49TH PCT | 9 | SUBSTANTIAL COMPLETION | 2023-07-28 | 2023-09-25 | 2023-07-28 | 2023-09-25
20201123 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAKO | ROOF REPLACEMENT AT 49TH PCT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-26 | 2023-10-25 | 2023-09-26 | 2023-10-25
20201123 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAKU | 49TH PCT ROOF REPLACEMENT | 1 | DEVELOP SCOPE | 2020-12-10 | 2021-03-09 | 2020-12-10 | 2021-03-09
20201123 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAKU | 49TH PCT ROOF REPLACEMENT | 2 | PRELIMINARY DESIGN | 2021-03-10 | 2021-07-07 | 2021-03-10 | 2021-07-07
20201123 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAKU | 49TH PCT ROOF REPLACEMENT | 3 | FINAL DESIGN | 2021-07-08 | 2021-11-04 | 2021-07-08 | 2021-11-04
20201123 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAKU | 49TH PCT ROOF REPLACEMENT | 4 | BID AWARD AND REGISTER CONTRCT | 2021-11-05 | 2022-05-03 | 2021-11-05 | 2022-05-03
20201123 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAKU | 49TH PCT ROOF REPLACEMENT | 5 | CONSTRUCTION TO 25% | 2022-05-04 | 2022-08-31 | 2022-05-04 | 2022-08-31
20201123 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAKU | 49TH PCT ROOF REPLACEMENT | 6 | CONSTRUCTION TO 50% | 2022-09-01 | 2022-12-29 | 2022-09-01 | 2022-12-29
20201123 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAKU | 49TH PCT ROOF REPLACEMENT | 7 | CONSTRUCTION TO 75% | 2022-12-30 | 2023-04-28 | 2022-12-30 | 2023-04-28
20201123 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAKU | 49TH PCT ROOF REPLACEMENT | 8 | ORIGINAL EQUIP & FURNISHING | 2023-04-29 | 2023-07-27 | 2023-04-29 | 2023-07-27
20201123 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAKU | 49TH PCT ROOF REPLACEMENT | 9 | SUBSTANTIAL COMPLETION | 2023-07-28 | 2023-09-25 | 2023-07-28 | 2023-09-25
20201123 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAKU | 49TH PCT ROOF REPLACEMENT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-26 | 2023-10-25 | 2023-09-26 | 2023-10-25
20201123 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAKV | 41ST PCT ROOF REPLACEMENT | 1 | DEVELOP SCOPE | 2020-12-10 | 2021-03-09 | 2020-12-10 | 2021-03-09
20201123 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAKV | 41ST PCT ROOF REPLACEMENT | 2 | PRELIMINARY DESIGN | 2021-03-10 | 2021-07-07 | 2021-03-10 | 2021-07-07
20201123 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAKV | 41ST PCT ROOF REPLACEMENT | 3 | FINAL DESIGN | 2021-07-08 | 2021-11-04 | 2021-07-08 | 2021-11-04
20201123 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAKV | 41ST PCT ROOF REPLACEMENT | 4 | BID AWARD AND REGISTER CONTRCT | 2021-11-05 | 2022-05-03 | 2021-11-05 | 2022-05-03
20201123 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAKV | 41ST PCT ROOF REPLACEMENT | 5 | CONSTRUCTION TO 25% | 2022-05-04 | 2022-08-31 | 2022-05-04 | 2022-08-31
20201123 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAKV | 41ST PCT ROOF REPLACEMENT | 6 | CONSTRUCTION TO 50% | 2022-09-01 | 2022-12-29 | 2022-09-01 | 2022-12-29
20201123 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAKV | 41ST PCT ROOF REPLACEMENT | 7 | CONSTRUCTION TO 75% | 2022-12-30 | 2023-04-28 | 2022-12-30 | 2023-04-28
20201123 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAKV | 41ST PCT ROOF REPLACEMENT | 8 | ORIGINAL EQUIP & FURNISHING | 2023-04-29 | 2023-07-27 | 2023-04-29 | 2023-07-27
20201123 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAKV | 41ST PCT ROOF REPLACEMENT | 9 | SUBSTANTIAL COMPLETION | 2023-07-28 | 2023-09-25 | 2023-07-28 | 2023-09-25
20201123 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAKV | 41ST PCT ROOF REPLACEMENT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-26 | 2023-10-25 | 2023-09-26 | 2023-10-25
20201123 | BRONX | 056 | POLICE DEPARTMENT | POD47RENO | Renovate/Upgrade 47th Precinct. | 1 | DESIGN | 2017-11-01 | 2018-04-29 | 2017-11-01 | 2018-04-29
20201123 | BRONX | 056 | POLICE DEPARTMENT | POD47RENO | Renovate/Upgrade 47th Precinct. | 2 | BID AWARD AND REGISTER CONTRCT | 2018-04-30 | 2018-07-28 | 2018-04-30 | 2018-07-28
20201123 | BRONX | 056 | POLICE DEPARTMENT | POD47RENO | Renovate/Upgrade 47th Precinct. | 3 | CONSTRUCTION | 2018-07-29 | 2019-07-28 | 2018-07-29 | 2019-07-28
20201123 | BRONX | 056 | POLICE DEPARTMENT | POD47RENO | Renovate/Upgrade 47th Precinct. | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-07-29 | 2020-01-24 | 2019-07-29 | 2022-01-24
20201123 | BRONX | 056 | POLICE DEPARTMENT | POD49RENO | 49TH PCT - RENOVATION | 1 | DEVELOP SCOPE | 2011-06-01 | 2011-08-29 | 2011-06-01 | 2011-08-29
20201123 | BRONX | 056 | POLICE DEPARTMENT | POD49RENO | 49TH PCT - RENOVATION | 2 | PRELIMINARY DESIGN | 2011-08-30 | 2011-12-27 | 2011-08-30 | 2011-12-27
20201123 | BRONX | 056 | POLICE DEPARTMENT | POD49RENO | 49TH PCT - RENOVATION | 3 | FINAL DESIGN | 2011-12-28 | 2012-04-25 | 2011-12-28 | 2012-04-25
20201123 | BRONX | 056 | POLICE DEPARTMENT | POD49RENO | 49TH PCT - RENOVATION | 4 | BID AWARD AND REGISTER CONTRCT | 2012-04-26 | 2012-10-22 | 2012-04-26 | 2012-10-22
20201123 | BRONX | 056 | POLICE DEPARTMENT | POD49RENO | 49TH PCT - RENOVATION | 5 | CONSTRUCTION TO 25% | 2012-10-23 | 2013-02-19 | 2012-10-23 | 2013-02-19
20201123 | BRONX | 056 | POLICE DEPARTMENT | POD49RENO | 49TH PCT - RENOVATION | 6 | CONSTRUCTION TO 50% | 2013-02-20 | 2013-06-19 | 2013-02-20 | 2013-06-19
20201123 | BRONX | 056 | POLICE DEPARTMENT | POD49RENO | 49TH PCT - RENOVATION | 7 | CONSTRUCTION TO 75% | 2013-06-20 | 2013-10-17 | 2013-06-20 | 2020-10-17
20201123 | BRONX | 056 | POLICE DEPARTMENT | POD49RENO | 49TH PCT - RENOVATION | 8 | ORIGINAL EQUIP & FURNISHING | 2013-10-18 | 2014-01-15 | 2020-10-18 | 2021-01-15
20201123 | BRONX | 056 | POLICE DEPARTMENT | POD49RENO | 49TH PCT - RENOVATION | 9 | SUBSTANTIAL COMPLETION | 2014-01-16 | 2014-03-16 | 2021-01-16 | 2021-03-16
20201123 | BRONX | 056 | POLICE DEPARTMENT | POD49RENO | 49TH PCT - RENOVATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-03-17 | 2014-04-15 | 2021-03-17 | 2022-03-16
20201123 | BRONX | 056 | POLICE DEPARTMENT | POD50ELGE | 50TH PCT REPLACE ELEVATORS AND GENERATORS | 1 | DEVELOP SCOPE | 2005-06-30 | 2005-09-27 | 2019-04-04 | 2019-07-02
20201123 | BRONX | 056 | POLICE DEPARTMENT | POD50ELGE | 50TH PCT REPLACE ELEVATORS AND GENERATORS | 2 | PRELIMINARY DESIGN | 2005-09-28 | 2006-01-25 | 2019-07-03 | 2019-10-30
20201123 | BRONX | 056 | POLICE DEPARTMENT | POD50ELGE | 50TH PCT REPLACE ELEVATORS AND GENERATORS | 3 | FINAL DESIGN | 2006-01-26 | 2006-05-25 | 2019-10-31 | 2020-02-27
20201123 | BRONX | 056 | POLICE DEPARTMENT | POD50ELGE | 50TH PCT REPLACE ELEVATORS AND GENERATORS | 4 | BID AWARD AND REGISTER CONTRCT | 2006-05-26 | 2006-11-21 | 2020-02-28 | 2020-08-25
20201123 | BRONX | 056 | POLICE DEPARTMENT | POD50ELGE | 50TH PCT REPLACE ELEVATORS AND GENERATORS | 5 | CONSTRUCTION TO 25% | 2006-11-22 | 2007-03-21 | 2020-08-26 | 2020-12-23
20201123 | BRONX | 056 | POLICE DEPARTMENT | POD50ELGE | 50TH PCT REPLACE ELEVATORS AND GENERATORS | 6 | CONSTRUCTION TO 50% | 2007-03-22 | 2007-07-19 | 2020-12-24 | 2021-04-22
20201123 | BRONX | 056 | POLICE DEPARTMENT | POD50ELGE | 50TH PCT REPLACE ELEVATORS AND GENERATORS | 7 | CONSTRUCTION TO 75% | 2007-07-20 | 2007-11-16 | 2021-04-23 | 2023-08-21
20201123 | BRONX | 056 | POLICE DEPARTMENT | POD50ELGE | 50TH PCT REPLACE ELEVATORS AND GENERATORS | 8 | ORIGINAL EQUIP & FURNISHING | 2007-11-17 | 2008-02-14 | 2023-08-22 | 2023-11-19
20201123 | BRONX | 056 | POLICE DEPARTMENT | POD50ELGE | 50TH PCT REPLACE ELEVATORS AND GENERATORS | 9 | SUBSTANTIAL COMPLETION | 2008-02-15 | 2008-04-14 | 2023-11-20 | 2024-01-18
20201123 | BRONX | 056 | POLICE DEPARTMENT | POD50ELGE | 50TH PCT REPLACE ELEVATORS AND GENERATORS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-04-15 | 2008-05-14 | 2024-01-19 | 2024-02-17
20201123 | BRONX | 056 | POLICE DEPARTMENT | POD52PARK | 52nd Precinct Parking Lot Renovation Upgrade | 1 | DESIGN | 2019-12-30 | 2020-06-26 | 2019-12-30 | 2020-06-26
20201123 | BRONX | 056 | POLICE DEPARTMENT | POD52PARK | 52nd Precinct Parking Lot Renovation Upgrade | 2 | BID AWARD AND REGISTER CONTRCT | 2020-06-27 | 2020-09-24 | 2020-06-27 | 2020-09-24
20201123 | BRONX | 056 | POLICE DEPARTMENT | POD52PARK | 52nd Precinct Parking Lot Renovation Upgrade | 3 | CONSTRUCTION | 2020-09-25 | 2021-09-24 | 2020-09-25 | 2021-09-24
20201123 | BRONX | 056 | POLICE DEPARTMENT | POD52PARK | 52nd Precinct Parking Lot Renovation Upgrade | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-25 | 2022-03-23 | 2021-09-25 | 2022-03-23
20201123 | BRONX | 057 | FIRE DEPARTMENT | F175KIT42 | KITCHEN REPLACEMENT - EC42 | 1 | DESIGN | 2013-08-09 | 2014-02-04 | 2016-12-04 | 2017-06-01
20201123 | BRONX | 057 | FIRE DEPARTMENT | F175KIT42 | KITCHEN REPLACEMENT - EC42 | 2 | CONSTRUCTION | 2014-02-05 | 2015-02-04 | 2017-06-02 | 2018-06-01
20201123 | BRONX | 057 | FIRE DEPARTMENT | F175KIT42 | KITCHEN REPLACEMENT - EC42 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-02-05 | 2015-05-05 | 2018-06-02 | 2022-07-06
20201123 | BRONX | 057 | FIRE DEPARTMENT | F175RFW20 | Roof and Windows - EMS 20 | 1 | CONSTRUCTION | 2020-01-02 | 2020-12-31 | 2020-01-02 | 2020-12-31
20201123 | BRONX | 057 | FIRE DEPARTMENT | F175RFW20 | Roof and Windows - EMS 20 | 2 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-01-01 | 2021-03-31 | 2021-01-01 | 2021-03-31
20201123 | BRONX | 057 | FIRE DEPARTMENT | F175XIN82 | Exterior and Interior Renovations - EC 82 | 1 | DESIGN | 2017-12-17 | 2018-06-14 | 2017-12-17 | 2018-06-14
20201123 | BRONX | 057 | FIRE DEPARTMENT | F175XIN82 | Exterior and Interior Renovations - EC 82 | 2 | CONSTRUCTION | 2018-06-15 | 2019-06-14 | 2018-06-15 | 2019-06-14
20201123 | BRONX | 057 | FIRE DEPARTMENT | F175XIN82 | Exterior and Interior Renovations - EC 82 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-06-15 | 2019-09-12 | 2019-06-15 | 2023-07-03
20201123 | BRONX | 057 | FIRE DEPARTMENT | F1TELMPS2 | PSACII Telemetry | 1 | DESIGN | 2019-02-15 | 2019-05-15 | 2019-02-15 | 2019-05-15
20201123 | BRONX | 057 | FIRE DEPARTMENT | F1TELMPS2 | PSACII Telemetry | 2 | BID AWARD AND REGISTER CONTRCT | 2019-05-16 | 2020-02-09 | 2019-05-16 | 2020-02-09
20201123 | BRONX | 057 | FIRE DEPARTMENT | F1TELMPS2 | PSACII Telemetry | 3 | CONSTRUCTION | 2020-02-10 | 2021-03-15 | 2020-02-10 | 2021-03-15
20201123 | BRONX | 057 | FIRE DEPARTMENT | F1TELMPS2 | PSACII Telemetry | 4 | ORIGINAL EQUIP & FURNISHING | 2021-03-16 | 2021-04-29 | 2021-03-16 | 2021-04-29
20201123 | BRONX | 057 | FIRE DEPARTMENT | F1TELMPS2 | PSACII Telemetry | 5 | SUBSTANTIAL COMPLETION | 2021-04-30 | 2021-06-08 | 2021-04-30 | 2021-06-08
20201123 | BRONX | 057 | FIRE DEPARTMENT | F1TELMPS2 | PSACII Telemetry | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-06-09 | 2021-08-07 | 2021-06-09 | 2021-08-07
20201123 | BRONX | 057 | FIRE DEPARTMENT | FD175DS61 | DOOR REPLACEMENT - SQ61 | 2 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-05-01 | 2019-07-29 | 2019-05-01 | 2019-07-29
20201123 | BRONX | 057 | FIRE DEPARTMENT | FX175GE42 | Generator - EC42 | 1 | DESIGN | 2019-10-30 | 2020-04-26 | 2019-10-30 | 2020-04-26
20201123 | BRONX | 057 | FIRE DEPARTMENT | FX175GE42 | Generator - EC42 | 2 | CONSTRUCTION | 2020-04-27 | 2021-04-26 | 2020-04-27 | 2021-04-26
20201123 | BRONX | 057 | FIRE DEPARTMENT | FX175GE42 | Generator - EC42 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-04-27 | 2021-07-25 | 2021-04-27 | 2021-07-25
20201123 | BRONX | 057 | FIRE DEPARTMENT | FX175WN46 | Window Replacement - EC46 | 1 | DESIGN | 2018-11-01 | 2019-04-29 | 2018-11-01 | 2019-04-29
20201123 | BRONX | 057 | FIRE DEPARTMENT | FX175WN46 | Window Replacement - EC46 | 2 | CONSTRUCTION | 2019-04-30 | 2020-04-28 | 2019-04-30 | 2020-04-28
20201123 | BRONX | 057 | FIRE DEPARTMENT | FX175WN46 | Window Replacement - EC46 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-04-29 | 2020-07-27 | 2020-04-29 | 2020-07-27
20201123 | BRONX | 057 | FIRE DEPARTMENT | FX175WN48 | Window Replacement EC48 | 1 | CONSTRUCTION | 2018-04-01 | 2019-03-31 | 2018-04-22 | 2021-09-30
20201123 | BRONX | 057 | FIRE DEPARTMENT | FX175WN48 | Window Replacement EC48 | 2 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-04-01 | 2019-06-29 | 2021-10-01 | 2021-12-29
20201123 | BRONX | 068 | ADMIN FOR CHILDREN'S SERVICES | BEACH REP | Replacement Site for Beach Non-Secure Detention Site | 1 | DESIGN | 2014-01-01 | 2014-06-29 | 2019-06-30 | 2019-12-26
20201123 | BRONX | 068 | ADMIN FOR CHILDREN'S SERVICES | BEACH REP | Replacement Site for Beach Non-Secure Detention Site | 2 | CONSTRUCTION | 2014-06-30 | 2015-06-29 | 2019-12-27 | 2021-06-30
20201123 | BRONX | 068 | ADMIN FOR CHILDREN'S SERVICES | BXELEVFAR | 1250 E229th Street Elevator and Fire Alarm Replacement | 1 | DEVELOP SCOPE | 2019-04-09 | 2019-07-07 | 2019-04-09 | 2019-07-07
20201123 | BRONX | 068 | ADMIN FOR CHILDREN'S SERVICES | BXELEVFAR | 1250 E229th Street Elevator and Fire Alarm Replacement | 2 | BID AWARD AND REGISTER CONTRCT | 2019-07-08 | 2019-10-05 | 2019-07-08 | 2019-10-05
20201123 | BRONX | 068 | ADMIN FOR CHILDREN'S SERVICES | BXELEVFAR | 1250 E229th Street Elevator and Fire Alarm Replacement | 3 | CONSTRUCTION TO 50% | 2019-10-06 | 2020-02-02 | 2019-10-06 | 2020-02-02
20201123 | BRONX | 068 | ADMIN FOR CHILDREN'S SERVICES | BXELEVFAR | 1250 E229th Street Elevator and Fire Alarm Replacement | 4 | CONSTRUCTION TO 75% | 2020-02-03 | 2020-04-02 | 2020-02-03 | 2020-04-02
20201123 | BRONX | 068 | ADMIN FOR CHILDREN'S SERVICES | BXELEVFAR | 1250 E229th Street Elevator and Fire Alarm Replacement | 5 | SUBSTANTIAL COMPLETION | 2020-04-03 | 2020-06-01 | 2020-04-03 | 2020-06-01
20201123 | BRONX | 068 | ADMIN FOR CHILDREN'S SERVICES | BXELEVFAR | 1250 E229th Street Elevator and Fire Alarm Replacement | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-06-02 | 2020-07-01 | 2020-06-02 | 2020-07-01
20201123 | BRONX | 068 | ADMIN FOR CHILDREN'S SERVICES | JJCONS | Adolescent Facility | 1 | DESIGN | 2020-07-31 | 2021-01-26 | 2020-07-31 | 2021-01-26
20201123 | BRONX | 068 | ADMIN FOR CHILDREN'S SERVICES | JJCONS | Adolescent Facility | 2 | CONSTRUCTION | 2021-01-27 | 2022-01-26 | 2021-01-27 | 2022-01-26
20201123 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HH112FAFC | FRANKLIN'S WOMEN'S SHELTER - FACADE REHABILITATION | 1 | DESIGN | 2022-01-01 | 2022-09-27 | 2022-01-01 | 2022-09-27
20201123 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HH112FAFC | FRANKLIN'S WOMEN'S SHELTER - FACADE REHABILITATION | 2 | BID AWARD AND REGISTER CONTRCT | 2022-09-28 | 2023-03-26 | 2022-09-28 | 2023-03-26
20201123 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HH112FAFC | FRANKLIN'S WOMEN'S SHELTER - FACADE REHABILITATION | 3 | CONSTRUCTION | 2023-03-27 | 2027-12-30 | 2023-03-27 | 2027-12-30
20201123 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HH115JEXT | UNIVERSITY AVENUE FAMILY FACAD | 1 | DESIGN | 2022-01-01 | 2022-09-27 | 2022-01-01 | 2022-09-27
20201123 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HH115JEXT | UNIVERSITY AVENUE FAMILY FACAD | 2 | BID AWARD AND REGISTER CONTRCT | 2022-09-28 | 2023-03-26 | 2022-09-28 | 2023-03-26
20201123 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HH115JEXT | UNIVERSITY AVENUE FAMILY FACAD | 3 | CONSTRUCTION | 2023-03-27 | 2027-12-30 | 2023-03-27 | 2027-12-30
20201123 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HH115NLBR | JAMAICA'S WOMENN'S SHELTER - BATHROOM RECONSTRUCTION | 1 | DESIGN | 2022-01-01 | 2022-09-27 | 2022-01-01 | 2022-09-27
20201123 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HH115NLBR | JAMAICA'S WOMENN'S SHELTER - BATHROOM RECONSTRUCTION | 2 | BID AWARD AND REGISTER CONTRCT | 2022-09-28 | 2023-03-26 | 2022-09-28 | 2023-03-26
20201123 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HH115NLBR | JAMAICA'S WOMENN'S SHELTER - BATHROOM RECONSTRUCTION | 3 | CONSTRUCTION | 2023-03-27 | 2027-12-30 | 2023-03-27 | 2027-12-30
20201123 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HH115SNRF | SENECA HOUSES - ROOF REPLACEMENT AND FACADE REHABILITATION | 1 | DESIGN | 2019-07-03 | 2020-03-28 | 2019-07-03 | 2020-03-28
20201123 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HH115SNRF | SENECA HOUSES - ROOF REPLACEMENT AND FACADE REHABILITATION | 2 | BID AWARD AND REGISTER CONTRCT | 2020-03-29 | 2020-09-24 | 2020-03-29 | 2020-09-24
20201123 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HH115SNRF | SENECA HOUSES - ROOF REPLACEMENT AND FACADE REHABILITATION | 3 | CONSTRUCTION | 2020-09-25 | 2025-06-30 | 2020-09-25 | 2025-06-30
20201123 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HH115UNBT | UNIVERSITY FAMILY KITCHEN BATHROOMS AND VENTILATION | 1 | DESIGN | 2019-07-03 | 2020-03-28 | 2019-07-03 | 2020-03-28
20201123 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HH115UNBT | UNIVERSITY FAMILY KITCHEN BATHROOMS AND VENTILATION | 2 | BID AWARD AND REGISTER CONTRCT | 2020-03-29 | 2020-09-24 | 2020-03-29 | 2020-09-24
20201123 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HH115UNBT | UNIVERSITY FAMILY KITCHEN BATHROOMS AND VENTILATION | 3 | CONSTRUCTION | 2020-09-25 | 2025-06-30 | 2020-09-25 | 2025-06-30
20201123 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HH115UNEU | UNIVERSITY FAMILY RESIDENCE ROOF REPLACEMENT | 1 | DEVELOP SCOPE | 2012-11-15 | 2013-02-12 | 2017-01-14 | 2027-04-13
20201123 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HH115UNEU | UNIVERSITY FAMILY RESIDENCE ROOF REPLACEMENT | 2 | PRELIMINARY DESIGN | 2013-02-13 | 2013-06-12 | 2027-04-14 | 2027-08-11
20201123 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HH115UNEU | UNIVERSITY FAMILY RESIDENCE ROOF REPLACEMENT | 3 | FINAL DESIGN | 2013-06-13 | 2013-10-10 | 2027-08-12 | 2027-12-09
20201123 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HH115UNEU | UNIVERSITY FAMILY RESIDENCE ROOF REPLACEMENT | 4 | BID AWARD AND REGISTER CONTRCT | 2013-10-11 | 2014-04-08 | 2027-12-10 | 2028-06-06
20201123 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HH115UNEU | UNIVERSITY FAMILY RESIDENCE ROOF REPLACEMENT | 5 | CONSTRUCTION TO 25% | 2014-04-09 | 2014-08-06 | 2028-06-07 | 2028-10-04
20201123 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HH115UNEU | UNIVERSITY FAMILY RESIDENCE ROOF REPLACEMENT | 6 | CONSTRUCTION TO 50% | 2014-08-07 | 2014-12-04 | 2028-10-05 | 2029-02-01
20201123 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HH115UNEU | UNIVERSITY FAMILY RESIDENCE ROOF REPLACEMENT | 7 | CONSTRUCTION TO 75% | 2014-12-05 | 2015-04-03 | 2029-02-02 | 2029-06-01
20201123 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HH115UNEU | UNIVERSITY FAMILY RESIDENCE ROOF REPLACEMENT | 8 | ORIGINAL EQUIP & FURNISHING | 2015-04-04 | 2015-07-02 | 2029-06-02 | 2029-08-30
20201123 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HH115UNEU | UNIVERSITY FAMILY RESIDENCE ROOF REPLACEMENT | 9 | SUBSTANTIAL COMPLETION | 2015-07-03 | 2015-08-31 | 2029-08-31 | 2029-10-29
20201123 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HH115UNEU | UNIVERSITY FAMILY RESIDENCE ROOF REPLACEMENT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-09-01 | 2015-09-30 | 2029-10-30 | 2029-11-28
20201123 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HH115UNFL | UNIVERSITY AVENUE FOUNDATION RECONSTRUCTION | 1 | DESIGN | 2019-07-03 | 2020-03-28 | 2019-07-03 | 2020-03-28
20201123 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HH115UNFL | UNIVERSITY AVENUE FOUNDATION RECONSTRUCTION | 2 | BID AWARD AND REGISTER CONTRCT | 2020-03-29 | 2020-09-24 | 2020-03-29 | 2020-09-24
20201123 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HH115UNFL | UNIVERSITY AVENUE FOUNDATION RECONSTRUCTION | 3 | CONSTRUCTION | 2020-09-25 | 2025-06-30 | 2020-09-25 | 2025-06-30
20201123 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HHNC001 | NEW ERA VETERANS SRO- KITCHEN RENOVATION | 1 | DEVELOP SCOPE | 2014-11-01 | 2015-01-29 | 2014-11-01 | 2015-01-29
20201123 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HHNC001 | NEW ERA VETERANS SRO- KITCHEN RENOVATION | 2 | PRELIMINARY DESIGN | 2015-01-30 | 2015-05-29 | 2015-01-30 | 2015-05-29
20201123 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HHNC001 | NEW ERA VETERANS SRO- KITCHEN RENOVATION | 3 | FINAL DESIGN | 2015-05-30 | 2015-09-26 | 2015-05-30 | 2015-09-26
20201123 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HHNC001 | NEW ERA VETERANS SRO- KITCHEN RENOVATION | 4 | BID AWARD AND REGISTER CONTRCT | 2015-09-27 | 2016-03-24 | 2015-09-27 | 2016-03-24
20201123 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HHNC001 | NEW ERA VETERANS SRO- KITCHEN RENOVATION | 5 | CONSTRUCTION TO 25% | 2016-03-25 | 2016-07-22 | 2016-03-25 | 2016-07-22
20201123 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HHNC001 | NEW ERA VETERANS SRO- KITCHEN RENOVATION | 6 | CONSTRUCTION TO 50% | 2016-07-23 | 2016-11-19 | 2016-07-23 | 2016-11-19
20201123 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HHNC001 | NEW ERA VETERANS SRO- KITCHEN RENOVATION | 7 | CONSTRUCTION TO 75% | 2016-11-20 | 2017-03-19 | 2016-11-20 | 2017-03-19
20201123 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HHNC001 | NEW ERA VETERANS SRO- KITCHEN RENOVATION | 8 | ORIGINAL EQUIP & FURNISHING | 2017-03-20 | 2017-06-17 | 2017-03-20 | 2017-06-17
20201123 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HHNC001 | NEW ERA VETERANS SRO- KITCHEN RENOVATION | 9 | SUBSTANTIAL COMPLETION | 2017-06-18 | 2017-08-16 | 2017-06-18 | 2017-08-16
20201123 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HHNC001 | NEW ERA VETERANS SRO- KITCHEN RENOVATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-08-17 | 2017-09-15 | 2017-08-17 | 2024-09-15
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C-101WEST | RI WEST PERIMETER EXTERIOR FENCING REPLACEMENT | 1 | DEVELOP SCOPE | 2006-01-01 | 2006-03-31 | 2012-07-03 | 2012-09-30
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C-101WEST | RI WEST PERIMETER EXTERIOR FENCING REPLACEMENT | 2 | PRELIMINARY DESIGN | 2006-04-01 | 2006-07-29 | 2012-10-01 | 2013-01-28
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C-101WEST | RI WEST PERIMETER EXTERIOR FENCING REPLACEMENT | 3 | FINAL DESIGN | 2006-07-30 | 2007-01-25 | 2013-01-29 | 2013-07-27
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C-101WEST | RI WEST PERIMETER EXTERIOR FENCING REPLACEMENT | 4 | BID AWARD AND REGISTER CONTRCT | 2007-01-26 | 2007-04-25 | 2013-07-28 | 2013-10-25
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C-101WEST | RI WEST PERIMETER EXTERIOR FENCING REPLACEMENT | 5 | CONSTRUCTION TO 25% | 2007-04-26 | 2007-08-23 | 2013-10-26 | 2014-02-22
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C-101WEST | RI WEST PERIMETER EXTERIOR FENCING REPLACEMENT | 6 | CONSTRUCTION TO 50% | 2007-08-24 | 2007-12-21 | 2014-02-23 | 2014-06-22
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C-101WEST | RI WEST PERIMETER EXTERIOR FENCING REPLACEMENT | 7 | CONSTRUCTION TO 75% | 2007-12-22 | 2008-04-19 | 2014-06-23 | 2014-10-20
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C-101WEST | RI WEST PERIMETER EXTERIOR FENCING REPLACEMENT | 8 | ORIGINAL EQUIP & FURNISHING | 2008-04-20 | 2008-07-18 | 2014-10-21 | 2015-01-18
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C-101WEST | RI WEST PERIMETER EXTERIOR FENCING REPLACEMENT | 9 | SUBSTANTIAL COMPLETION | 2008-07-19 | 2008-09-16 | 2015-01-19 | 2015-03-19
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C-101WEST | RI WEST PERIMETER EXTERIOR FENCING REPLACEMENT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-09-17 | 2008-10-16 | 2015-03-20 | 2020-04-17
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C130PANEL | REPLACEMENT OF ELECTRICAL DISTRIBUTION PANELS- RI POWERHOUSE | 1 | DESIGN | 2016-05-30 | 2016-06-28 | 2016-05-30 | 2016-06-28
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C130PANEL | REPLACEMENT OF ELECTRICAL DISTRIBUTION PANELS- RI POWERHOUSE | 2 | BID AWARD AND REGISTER CONTRCT | 2016-06-29 | 2016-09-26 | 2016-06-29 | 2016-09-26
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C130PANEL | REPLACEMENT OF ELECTRICAL DISTRIBUTION PANELS- RI POWERHOUSE | 3 | CONSTRUCTION | 2016-09-27 | 2017-03-25 | 2016-09-27 | 2017-03-25
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C130PANEL | REPLACEMENT OF ELECTRICAL DISTRIBUTION PANELS- RI POWERHOUSE | 4 | ORIGINAL EQUIP & FURNISHING | 2017-03-26 | 2017-06-23 | 2017-03-26 | 2017-06-23
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C130PANEL | REPLACEMENT OF ELECTRICAL DISTRIBUTION PANELS- RI POWERHOUSE | 5 | SUBSTANTIAL COMPLETION | 2017-06-24 | 2017-07-23 | 2017-06-24 | 2017-07-23
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C130PANEL | REPLACEMENT OF ELECTRICAL DISTRIBUTION PANELS- RI POWERHOUSE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-07-24 | 2017-08-22 | 2017-07-24 | 2021-08-22
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138FEDER | NIC Power Feder Replacement | 1 | DESIGN | 2014-06-30 | 2014-07-29 | 2014-06-30 | 2020-07-29
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138FEDER | NIC Power Feder Replacement | 2 | BID AWARD AND REGISTER CONTRCT | 2014-07-30 | 2014-10-27 | 2020-07-30 | 2020-10-27
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138FEDER | NIC Power Feder Replacement | 3 | CONSTRUCTION | 2014-10-28 | 2015-04-25 | 2020-10-28 | 2021-04-25
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138FEDER | NIC Power Feder Replacement | 4 | ORIGINAL EQUIP & FURNISHING | 2015-04-26 | 2015-07-24 | 2021-04-26 | 2021-07-24
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138FEDER | NIC Power Feder Replacement | 5 | SUBSTANTIAL COMPLETION | 2015-07-25 | 2015-08-23 | 2021-07-25 | 2021-08-23
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138FEDER | NIC Power Feder Replacement | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-08-24 | 2015-09-22 | 2021-08-24 | 2021-09-22
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138FSPH2 | Fire Life Safety Phase II | 1 | DESIGN | 2015-07-01 | 2016-05-01 | 2015-07-01 | 2016-05-01
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138FSPH2 | Fire Life Safety Phase II | 2 | BID AWARD AND REGISTER CONTRCT | 2016-05-02 | 2017-05-01 | 2016-05-02 | 2017-05-01
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138FSPH2 | Fire Life Safety Phase II | 3 | CONSTRUCTION TO 75% | 2017-05-02 | 2018-03-16 | 2017-05-02 | 2018-03-16
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138FSPH2 | Fire Life Safety Phase II | 4 | SUBSTANTIAL COMPLETION | 2018-03-17 | 2018-05-19 | 2018-03-17 | 2018-05-19
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138FSPH2 | Fire Life Safety Phase II | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-05-20 | 2018-07-01 | 2018-05-20 | 2024-07-01
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138FSYS | FIRE SAFETY SYSTEM CONSTRUCTION | 1 | DEVELOP SCOPE | 2008-06-30 | 2009-03-26 | 2011-06-30 | 2012-03-25
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138FSYS | FIRE SAFETY SYSTEM CONSTRUCTION | 2 | PRELIMINARY DESIGN | 2009-03-27 | 2009-11-21 | 2012-03-26 | 2012-11-20
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138FSYS | FIRE SAFETY SYSTEM CONSTRUCTION | 3 | FINAL DESIGN | 2009-11-22 | 2010-11-16 | 2012-11-21 | 2013-11-15
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138FSYS | FIRE SAFETY SYSTEM CONSTRUCTION | 4 | BID AWARD AND REGISTER CONTRCT | 2010-11-17 | 2011-05-15 | 2013-11-16 | 2014-05-14
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138FSYS | FIRE SAFETY SYSTEM CONSTRUCTION | 5 | CONSTRUCTION TO 25% | 2011-05-16 | 2012-01-10 | 2014-05-15 | 2015-01-09
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138FSYS | FIRE SAFETY SYSTEM CONSTRUCTION | 6 | CONSTRUCTION TO 50% | 2012-01-11 | 2012-09-06 | 2015-01-10 | 2015-09-06
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138FSYS | FIRE SAFETY SYSTEM CONSTRUCTION | 7 | CONSTRUCTION TO 75% | 2012-09-07 | 2013-05-04 | 2015-09-07 | 2016-05-03
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138FSYS | FIRE SAFETY SYSTEM CONSTRUCTION | 8 | ORIGINAL EQUIP & FURNISHING | 2013-05-05 | 2014-01-29 | 2013-05-05 | 2014-01-29
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138FSYS | FIRE SAFETY SYSTEM CONSTRUCTION | 9 | SUBSTANTIAL COMPLETION | 2014-01-30 | 2014-07-28 | 2014-01-30 | 2014-01-29
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138FSYS | FIRE SAFETY SYSTEM CONSTRUCTION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-07-29 | 2014-10-26 | 2014-01-30 | 2027-04-29
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138GRFS2 | GRVC - Fire Life Safety Phase II | 1 | DESIGN | 2017-09-01 | 2018-07-03 | 2017-09-01 | 2018-07-03
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138GRFS2 | GRVC - Fire Life Safety Phase II | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-04 | 2019-07-03 | 2018-07-04 | 2019-07-03
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138GRFS2 | GRVC - Fire Life Safety Phase II | 3 | CONSTRUCTION TO 75% | 2019-07-04 | 2020-05-17 | 2019-07-04 | 2020-05-17
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138GRFS2 | GRVC - Fire Life Safety Phase II | 4 | SUBSTANTIAL COMPLETION | 2020-05-18 | 2020-07-20 | 2020-05-18 | 2020-07-20
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138GRFS2 | GRVC - Fire Life Safety Phase II | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-07-21 | 2020-09-01 | 2020-07-21 | 2020-09-01
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138NCFS2 | Fire Life Safety Phase II for NIC Annex | 1 | DESIGN | 2017-09-01 | 2018-07-03 | 2017-09-01 | 2018-07-03
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138NCFS2 | Fire Life Safety Phase II for NIC Annex | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-04 | 2019-07-03 | 2018-07-04 | 2019-07-03
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138NCFS2 | Fire Life Safety Phase II for NIC Annex | 3 | CONSTRUCTION TO 75% | 2019-07-04 | 2020-05-17 | 2019-07-04 | 2020-05-17
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138NCFS2 | Fire Life Safety Phase II for NIC Annex | 4 | SUBSTANTIAL COMPLETION | 2020-05-18 | 2020-07-20 | 2020-05-18 | 2020-07-20
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138NCFS2 | Fire Life Safety Phase II for NIC Annex | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-07-21 | 2020-09-01 | 2020-07-21 | 2020-09-01
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138PURGR | POST FIRE PURGE SYSTEM AT GRVC | 1 | DESIGN | 2015-05-30 | 2015-06-28 | 2015-05-30 | 2015-06-28
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138PURGR | POST FIRE PURGE SYSTEM AT GRVC | 2 | BID AWARD AND REGISTER CONTRCT | 2015-06-29 | 2015-09-26 | 2015-06-29 | 2015-09-26
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138PURGR | POST FIRE PURGE SYSTEM AT GRVC | 3 | CONSTRUCTION | 2015-09-27 | 2016-03-24 | 2015-09-27 | 2016-03-24
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138PURGR | POST FIRE PURGE SYSTEM AT GRVC | 4 | ORIGINAL EQUIP & FURNISHING | 2016-03-25 | 2016-06-22 | 2016-03-25 | 2016-06-22
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138PURGR | POST FIRE PURGE SYSTEM AT GRVC | 5 | SUBSTANTIAL COMPLETION | 2016-06-23 | 2016-07-22 | 2016-06-23 | 2016-07-22
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138PURGR | POST FIRE PURGE SYSTEM AT GRVC | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-07-23 | 2017-12-01 | 2016-07-23 | 2021-12-01
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138PWRHS | DESIGN AND INSTALL FIRE ALARM SYSTEM AT EXISTING POWERHOUSE | 1 | DEVELOP SCOPE | 2016-01-01 | 2016-03-30 | 2016-01-01 | 2016-03-30
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138PWRHS | DESIGN AND INSTALL FIRE ALARM SYSTEM AT EXISTING POWERHOUSE | 2 | PRELIMINARY DESIGN | 2016-03-31 | 2016-07-28 | 2016-03-31 | 2016-07-28
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138PWRHS | DESIGN AND INSTALL FIRE ALARM SYSTEM AT EXISTING POWERHOUSE | 3 | FINAL DESIGN | 2016-07-29 | 2017-01-24 | 2016-07-29 | 2017-01-24
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138PWRHS | DESIGN AND INSTALL FIRE ALARM SYSTEM AT EXISTING POWERHOUSE | 4 | BID AWARD AND REGISTER CONTRCT | 2017-01-25 | 2017-04-24 | 2017-01-25 | 2017-04-24
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138PWRHS | DESIGN AND INSTALL FIRE ALARM SYSTEM AT EXISTING POWERHOUSE | 5 | CONSTRUCTION TO 25% | 2017-04-25 | 2017-08-22 | 2017-04-25 | 2019-12-22
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138PWRHS | DESIGN AND INSTALL FIRE ALARM SYSTEM AT EXISTING POWERHOUSE | 6 | CONSTRUCTION TO 50% | 2017-08-23 | 2017-12-20 | 2019-12-23 | 2020-04-20
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138PWRHS | DESIGN AND INSTALL FIRE ALARM SYSTEM AT EXISTING POWERHOUSE | 7 | CONSTRUCTION TO 75% | 2017-12-21 | 2018-04-19 | 2020-04-21 | 2020-08-18
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138PWRHS | DESIGN AND INSTALL FIRE ALARM SYSTEM AT EXISTING POWERHOUSE | 8 | ORIGINAL EQUIP & FURNISHING | 2018-04-20 | 2018-07-18 | 2020-08-19 | 2020-11-16
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138PWRHS | DESIGN AND INSTALL FIRE ALARM SYSTEM AT EXISTING POWERHOUSE | 9 | SUBSTANTIAL COMPLETION | 2018-07-19 | 2018-09-16 | 2020-11-17 | 2021-01-15
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138PWRHS | DESIGN AND INSTALL FIRE ALARM SYSTEM AT EXISTING POWERHOUSE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-09-17 | 2018-10-16 | 2021-01-16 | 2021-05-30
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138RMFS2 | RMSC - Fire Life Safety Phase II | 1 | DESIGN | 2016-06-01 | 2017-04-01 | 2016-06-01 | 2017-04-01
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138RMFS2 | RMSC - Fire Life Safety Phase II | 2 | BID AWARD AND REGISTER CONTRCT | 2017-04-02 | 2018-04-01 | 2017-04-02 | 2018-04-01
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138RMFS2 | RMSC - Fire Life Safety Phase II | 3 | CONSTRUCTION TO 75% | 2018-04-02 | 2019-11-15 | 2018-04-02 | 2019-11-15
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138RMFS2 | RMSC - Fire Life Safety Phase II | 4 | SUBSTANTIAL COMPLETION | 2019-11-16 | 2020-03-13 | 2019-11-16 | 2020-03-13
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138RMFS2 | RMSC - Fire Life Safety Phase II | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-03-14 | 2020-05-31 | 2020-03-14 | 2021-09-30
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138TRANS | DESIGN AND INSTALL FIRE ALARM SYSTEM AT TRANSPORTATION DIV | 1 | DESIGN | 2015-07-01 | 2016-05-01 | 2017-01-05 | 2019-04-28
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138TRANS | DESIGN AND INSTALL FIRE ALARM SYSTEM AT TRANSPORTATION DIV | 2 | BID AWARD AND REGISTER CONTRCT | 2016-05-02 | 2017-05-01 | 2019-04-29 | 2019-09-20
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138TRANS | DESIGN AND INSTALL FIRE ALARM SYSTEM AT TRANSPORTATION DIV | 3 | CONSTRUCTION TO 75% | 2017-05-02 | 2018-03-16 | 2019-09-21 | 2020-05-04
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138TRANS | DESIGN AND INSTALL FIRE ALARM SYSTEM AT TRANSPORTATION DIV | 4 | SUBSTANTIAL COMPLETION | 2018-03-17 | 2018-05-19 | 2020-05-05 | 2020-07-30
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138TRANS | DESIGN AND INSTALL FIRE ALARM SYSTEM AT TRANSPORTATION DIV | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-05-20 | 2018-07-01 | 2020-08-01 | 2020-10-31
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ADACOM | ADA COMPLIANCE FOR NIC, CENTRAL VISITS, FACILITY VISIT AREAS | 1 | DEVELOP SCOPE | 2017-06-30 | 2017-09-27 | 2017-06-30 | 2017-09-27
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ADACOM | ADA COMPLIANCE FOR NIC, CENTRAL VISITS, FACILITY VISIT AREAS | 2 | PRELIMINARY DESIGN | 2017-09-28 | 2018-01-25 | 2017-09-28 | 2018-01-25
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ADACOM | ADA COMPLIANCE FOR NIC, CENTRAL VISITS, FACILITY VISIT AREAS | 3 | FINAL DESIGN | 2018-01-26 | 2018-07-24 | 2018-01-26 | 2018-07-24
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ADACOM | ADA COMPLIANCE FOR NIC, CENTRAL VISITS, FACILITY VISIT AREAS | 4 | BID AWARD AND REGISTER CONTRCT | 2018-07-25 | 2018-10-22 | 2018-07-25 | 2018-10-22
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ADACOM | ADA COMPLIANCE FOR NIC, CENTRAL VISITS, FACILITY VISIT AREAS | 5 | CONSTRUCTION TO 25% | 2018-10-23 | 2019-02-19 | 2018-10-23 | 2019-02-19
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ADACOM | ADA COMPLIANCE FOR NIC, CENTRAL VISITS, FACILITY VISIT AREAS | 6 | CONSTRUCTION TO 50% | 2019-02-20 | 2019-06-19 | 2019-02-20 | 2019-06-19
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ADACOM | ADA COMPLIANCE FOR NIC, CENTRAL VISITS, FACILITY VISIT AREAS | 7 | CONSTRUCTION TO 75% | 2019-06-20 | 2019-10-17 | 2019-06-20 | 2019-10-17
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ADACOM | ADA COMPLIANCE FOR NIC, CENTRAL VISITS, FACILITY VISIT AREAS | 8 | ORIGINAL EQUIP & FURNISHING | 2019-10-18 | 2020-01-15 | 2019-10-18 | 2020-01-15
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ADACOM | ADA COMPLIANCE FOR NIC, CENTRAL VISITS, FACILITY VISIT AREAS | 9 | SUBSTANTIAL COMPLETION | 2020-01-16 | 2020-03-15 | 2020-01-16 | 2020-03-15
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ADACOM | ADA COMPLIANCE FOR NIC, CENTRAL VISITS, FACILITY VISIT AREAS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-03-16 | 2020-04-14 | 2020-03-16 | 2021-07-30
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ADACVT | ADA Compliance for Central Visits | 1 | DESIGN | 2017-09-01 | 2018-07-03 | 2017-09-01 | 2018-07-03
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ADACVT | ADA Compliance for Central Visits | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-04 | 2019-07-03 | 2018-07-04 | 2019-07-03
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ADACVT | ADA Compliance for Central Visits | 3 | CONSTRUCTION TO 75% | 2019-07-04 | 2020-05-17 | 2019-07-04 | 2020-05-17
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ADACVT | ADA Compliance for Central Visits | 4 | SUBSTANTIAL COMPLETION | 2020-05-18 | 2020-07-20 | 2020-05-18 | 2020-07-20
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ADACVT | ADA Compliance for Central Visits | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-07-21 | 2020-09-01 | 2020-07-21 | 2020-09-01
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ADAGRV | ADA Compliance for GRVC | 1 | DESIGN | 2017-09-01 | 2018-07-03 | 2017-09-01 | 2018-07-03
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ADAGRV | ADA Compliance for GRVC | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-04 | 2019-07-03 | 2018-07-04 | 2019-07-03
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ADAGRV | ADA Compliance for GRVC | 3 | CONSTRUCTION TO 75% | 2019-07-04 | 2020-05-17 | 2019-07-04 | 2020-05-17
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ADAGRV | ADA Compliance for GRVC | 4 | SUBSTANTIAL COMPLETION | 2020-05-18 | 2020-07-20 | 2020-05-18 | 2020-07-20
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ADAGRV | ADA Compliance for GRVC | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-07-21 | 2020-09-01 | 2020-07-21 | 2020-09-01
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ADANIC | NIC SHOWER RECONSTRUCTION DORMS 3/4 TO COMPLY WITH ADA | 1 | DEVELOP SCOPE | 2008-06-30 | 2008-09-27 | 2016-06-30 | 2016-09-27
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ADANIC | NIC SHOWER RECONSTRUCTION DORMS 3/4 TO COMPLY WITH ADA | 2 | PRELIMINARY DESIGN | 2008-09-28 | 2009-01-25 | 2016-09-28 | 2017-01-25
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ADANIC | NIC SHOWER RECONSTRUCTION DORMS 3/4 TO COMPLY WITH ADA | 3 | FINAL DESIGN | 2009-01-26 | 2009-07-24 | 2017-01-26 | 2017-07-24
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ADANIC | NIC SHOWER RECONSTRUCTION DORMS 3/4 TO COMPLY WITH ADA | 4 | BID AWARD AND REGISTER CONTRCT | 2009-07-25 | 2009-10-22 | 2017-07-25 | 2017-10-22
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ADANIC | NIC SHOWER RECONSTRUCTION DORMS 3/4 TO COMPLY WITH ADA | 5 | CONSTRUCTION TO 25% | 2009-10-23 | 2010-02-19 | 2017-10-23 | 2018-02-19
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ADANIC | NIC SHOWER RECONSTRUCTION DORMS 3/4 TO COMPLY WITH ADA | 6 | CONSTRUCTION TO 50% | 2010-02-20 | 2010-06-19 | 2018-02-20 | 2018-06-19
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ADANIC | NIC SHOWER RECONSTRUCTION DORMS 3/4 TO COMPLY WITH ADA | 7 | CONSTRUCTION TO 75% | 2010-06-20 | 2010-10-17 | 2018-06-20 | 2018-10-17
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ADANIC | NIC SHOWER RECONSTRUCTION DORMS 3/4 TO COMPLY WITH ADA | 8 | ORIGINAL EQUIP & FURNISHING | 2010-10-18 | 2011-01-15 | 2018-10-18 | 2019-01-15
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ADANIC | NIC SHOWER RECONSTRUCTION DORMS 3/4 TO COMPLY WITH ADA | 9 | SUBSTANTIAL COMPLETION | 2011-01-16 | 2011-03-16 | 2019-01-16 | 2019-03-16
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ADANIC | NIC SHOWER RECONSTRUCTION DORMS 3/4 TO COMPLY WITH ADA | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2011-03-17 | 2011-04-15 | 2019-03-17 | 2021-04-15
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ADARMS | ADA Compliance for RMSC | 1 | DESIGN | 2017-09-01 | 2018-07-03 | 2017-09-01 | 2018-07-03
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ADARMS | ADA Compliance for RMSC | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-04 | 2019-07-03 | 2018-07-04 | 2019-07-03
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ADARMS | ADA Compliance for RMSC | 3 | CONSTRUCTION TO 75% | 2019-07-04 | 2020-05-17 | 2019-07-04 | 2020-05-17
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ADARMS | ADA Compliance for RMSC | 4 | SUBSTANTIAL COMPLETION | 2020-05-18 | 2020-07-20 | 2020-05-18 | 2020-07-20
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ADARMS | ADA Compliance for RMSC | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-07-21 | 2020-09-01 | 2020-07-21 | 2020-09-01
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ASBEST | Asbestos Abatement and Air Monitoring - Various Facilities | 1 | DESIGN | 2015-10-30 | 2016-08-29 | 2015-10-30 | 2016-08-29
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ASBEST | Asbestos Abatement and Air Monitoring - Various Facilities | 2 | BID AWARD AND REGISTER CONTRCT | 2016-08-30 | 2017-08-29 | 2016-08-30 | 2017-08-29
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ASBEST | Asbestos Abatement and Air Monitoring - Various Facilities | 3 | CONSTRUCTION TO 75% | 2017-08-30 | 2019-04-14 | 2017-08-30 | 2019-04-14
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ASBEST | Asbestos Abatement and Air Monitoring - Various Facilities | 4 | SUBSTANTIAL COMPLETION | 2019-04-15 | 2019-08-11 | 2019-04-15 | 2019-08-11
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ASBEST | Asbestos Abatement and Air Monitoring - Various Facilities | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-08-12 | 2019-10-29 | 2019-08-12 | 2023-10-29
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75CELLD | Electronic Cell Door Panels at All Facilities | 1 | DESIGN | 2016-07-01 | 2017-05-02 | 2016-07-01 | 2017-05-02
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75CELLD | Electronic Cell Door Panels at All Facilities | 2 | BID AWARD AND REGISTER CONTRCT | 2017-05-03 | 2018-05-02 | 2017-05-03 | 2018-05-02
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75CELLD | Electronic Cell Door Panels at All Facilities | 3 | CONSTRUCTION TO 75% | 2018-05-03 | 2019-03-17 | 2018-05-03 | 2019-03-17
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75CELLD | Electronic Cell Door Panels at All Facilities | 4 | SUBSTANTIAL COMPLETION | 2019-03-18 | 2019-05-20 | 2019-03-18 | 2019-05-20
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75CELLD | Electronic Cell Door Panels at All Facilities | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-05-21 | 2019-07-02 | 2019-05-21 | 2027-07-02
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75-ELEV | ELEVATOR REHAB VARIOUS FACILITIES | 1 | DEVELOP SCOPE | 2012-06-30 | 2013-03-26 | 2011-06-30 | 2012-03-25
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75-ELEV | ELEVATOR REHAB VARIOUS FACILITIES | 2 | PRELIMINARY DESIGN | 2013-03-27 | 2013-11-21 | 2012-03-26 | 2012-11-20
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75-ELEV | ELEVATOR REHAB VARIOUS FACILITIES | 3 | FINAL DESIGN | 2013-11-22 | 2014-11-16 | 2012-11-21 | 2013-11-15
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75-ELEV | ELEVATOR REHAB VARIOUS FACILITIES | 4 | BID AWARD AND REGISTER CONTRCT | 2014-11-17 | 2015-05-15 | 2013-11-16 | 2014-05-14
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75-ELEV | ELEVATOR REHAB VARIOUS FACILITIES | 5 | CONSTRUCTION TO 25% | 2015-05-16 | 2016-01-10 | 2014-05-15 | 2015-01-09
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75-ELEV | ELEVATOR REHAB VARIOUS FACILITIES | 6 | CONSTRUCTION TO 50% | 2016-01-11 | 2016-09-06 | 2015-01-10 | 2015-09-06
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75-ELEV | ELEVATOR REHAB VARIOUS FACILITIES | 7 | CONSTRUCTION TO 75% | 2016-09-07 | 2017-05-04 | 2015-09-07 | 2016-05-03
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75-ELEV | ELEVATOR REHAB VARIOUS FACILITIES | 8 | ORIGINAL EQUIP & FURNISHING | 2017-05-05 | 2018-01-29 | 2016-05-04 | 2017-01-28
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75-ELEV | ELEVATOR REHAB VARIOUS FACILITIES | 9 | SUBSTANTIAL COMPLETION | 2018-01-30 | 2018-07-28 | 2017-01-29 | 2017-07-27
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75-ELEV | ELEVATOR REHAB VARIOUS FACILITIES | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-07-29 | 2018-10-26 | 2017-07-28 | 2021-10-25
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ENTGRV | Modification of Facility Entrance-GRVC | 1 | DESIGN | 2017-09-01 | 2018-07-03 | 2017-09-01 | 2018-07-03
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ENTGRV | Modification of Facility Entrance-GRVC | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-04 | 2019-07-03 | 2018-07-04 | 2019-07-03
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ENTGRV | Modification of Facility Entrance-GRVC | 3 | CONSTRUCTION TO 75% | 2019-07-04 | 2020-05-17 | 2019-07-04 | 2020-05-17
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ENTGRV | Modification of Facility Entrance-GRVC | 4 | SUBSTANTIAL COMPLETION | 2020-05-18 | 2020-07-20 | 2020-05-18 | 2020-07-20
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ENTGRV | Modification of Facility Entrance-GRVC | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-07-21 | 2020-09-01 | 2020-07-21 | 2020-09-01
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ENTNC | Modification for Facility Entries - NIC | 1 | DESIGN | 2017-09-01 | 2018-07-03 | 2017-09-01 | 2018-07-03
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ENTNC | Modification for Facility Entries - NIC | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-04 | 2019-07-03 | 2018-07-04 | 2019-07-03
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ENTNC | Modification for Facility Entries - NIC | 3 | CONSTRUCTION TO 75% | 2019-07-04 | 2020-05-17 | 2019-07-04 | 2020-05-17
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ENTNC | Modification for Facility Entries - NIC | 4 | SUBSTANTIAL COMPLETION | 2020-05-18 | 2020-07-20 | 2020-05-18 | 2020-07-20
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ENTNC | Modification for Facility Entries - NIC | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-07-21 | 2020-09-01 | 2020-07-21 | 2020-09-01
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ENTRMS | Modification of Facility Entry at RMSC | 1 | DESIGN | 2018-01-31 | 2018-08-02 | 2018-01-31 | 2018-08-02
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ENTRMS | Modification of Facility Entry at RMSC | 2 | BID AWARD AND REGISTER CONTRCT | 2018-08-03 | 2019-08-02 | 2018-08-03 | 2019-08-02
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ENTRMS | Modification of Facility Entry at RMSC | 3 | CONSTRUCTION TO 75% | 2019-08-03 | 2022-08-03 | 2019-08-03 | 2022-08-03
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ENTRMS | Modification of Facility Entry at RMSC | 4 | SUBSTANTIAL COMPLETION | 2022-08-04 | 2023-03-10 | 2022-08-04 | 2023-03-10
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ENTRMS | Modification of Facility Entry at RMSC | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-03-11 | 2023-08-03 | 2023-03-11 | 2023-08-03
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ESUCP | New ESU Compound at Rikers Island | 1 | DESIGN | 2019-05-01 | 2019-07-31 | 2019-05-01 | 2019-07-31
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ESUCP | New ESU Compound at Rikers Island | 2 | BID AWARD AND REGISTER CONTRCT | 2019-08-01 | 2020-03-30 | 2019-08-01 | 2020-03-30
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ESUCP | New ESU Compound at Rikers Island | 3 | CONSTRUCTION TO 75% | 2020-03-31 | 2020-09-30 | 2020-03-31 | 2020-09-30
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ESUCP | New ESU Compound at Rikers Island | 4 | SUBSTANTIAL COMPLETION | 2020-10-01 | 2020-10-31 | 2020-10-01 | 2020-10-31
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ESUCP | New ESU Compound at Rikers Island | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-11-01 | 2020-12-31 | 2020-11-01 | 2025-12-31
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75FENCE1 | FENCING RECONSTRUCTION | 1 | DEVELOP SCOPE | 2005-08-24 | 2005-11-21 | 2010-08-24 | 2010-11-21
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75FENCE1 | FENCING RECONSTRUCTION | 2 | PRELIMINARY DESIGN | 2005-11-22 | 2006-03-21 | 2010-11-22 | 2011-03-21
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75FENCE1 | FENCING RECONSTRUCTION | 3 | FINAL DESIGN | 2006-03-22 | 2006-09-17 | 2011-03-22 | 2011-09-17
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75FENCE1 | FENCING RECONSTRUCTION | 4 | BID AWARD AND REGISTER CONTRCT | 2006-09-18 | 2006-12-16 | 2011-09-18 | 2011-12-16
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75FENCE1 | FENCING RECONSTRUCTION | 5 | CONSTRUCTION TO 25% | 2006-12-17 | 2007-04-15 | 2011-12-17 | 2012-04-14
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75FENCE1 | FENCING RECONSTRUCTION | 6 | CONSTRUCTION TO 50% | 2007-04-16 | 2007-08-13 | 2012-04-15 | 2012-08-12
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75FENCE1 | FENCING RECONSTRUCTION | 7 | CONSTRUCTION TO 75% | 2007-08-14 | 2007-12-11 | 2012-08-13 | 2012-12-10
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75FENCE1 | FENCING RECONSTRUCTION | 8 | ORIGINAL EQUIP & FURNISHING | 2007-12-12 | 2008-03-10 | 2012-12-11 | 2013-03-10
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75FENCE1 | FENCING RECONSTRUCTION | 9 | SUBSTANTIAL COMPLETION | 2008-03-11 | 2008-05-09 | 2013-03-11 | 2013-05-09
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75FENCE1 | FENCING RECONSTRUCTION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-05-10 | 2008-06-08 | 2013-05-10 | 2023-06-08
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75-GCELL | GANG CELL DOOR RELEASE | 1 | DEVELOP SCOPE | 2011-06-30 | 2011-09-27 | 2018-07-01 | 2024-01-08
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75-GCELL | GANG CELL DOOR RELEASE | 2 | PRELIMINARY DESIGN | 2011-09-28 | 2012-01-25 | 2024-01-09 | 2024-01-08
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75-GCELL | GANG CELL DOOR RELEASE | 3 | FINAL DESIGN | 2012-01-26 | 2012-07-23 | 2024-01-09 | 2024-01-08
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75-GCELL | GANG CELL DOOR RELEASE | 4 | BID AWARD AND REGISTER CONTRCT | 2012-07-24 | 2012-10-21 | 2024-01-09 | 2024-01-08
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75-GCELL | GANG CELL DOOR RELEASE | 5 | CONSTRUCTION TO 25% | 2012-10-22 | 2013-02-18 | 2024-01-09 | 2024-01-08
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75-GCELL | GANG CELL DOOR RELEASE | 6 | CONSTRUCTION TO 50% | 2013-02-19 | 2013-06-18 | 2024-01-09 | 2024-01-08
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75-GCELL | GANG CELL DOOR RELEASE | 7 | CONSTRUCTION TO 75% | 2013-06-19 | 2013-10-16 | 2024-01-09 | 2024-01-08
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75-GCELL | GANG CELL DOOR RELEASE | 8 | DESIGN | 2014-04-15 | 2014-05-14 | 2024-01-09 | 2024-01-08
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75-GCELL | GANG CELL DOOR RELEASE | 9 | BID AWARD AND REGISTER CONTRCT | 2014-05-15 | 2014-08-12 | 2024-01-09 | 2024-01-08
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75-GCELL | GANG CELL DOOR RELEASE | 10 | CONSTRUCTION | 2014-08-13 | 2015-02-08 | 2024-01-09 | 2024-02-07
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75-GCELL | GANG CELL DOOR RELEASE | 11 | ORIGINAL EQUIP & FURNISHING | 2015-02-09 | 2015-05-09 | 2024-01-09 | 2024-02-07
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75-GCELL | GANG CELL DOOR RELEASE | 12 | SUBSTANTIAL COMPLETION | 2015-05-10 | 2015-06-08 | 2024-01-09 | 2024-02-07
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75-GCELL | GANG CELL DOOR RELEASE | 13 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-06-09 | 2015-07-08 | 2024-01-09 | 2024-02-07
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75GPARK | Construction of Parking Lot for GMDC Academy | 1 | DEVELOP SCOPE | 2020-04-01 | 2020-06-29 | 2020-04-01 | 2020-06-29
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75GPARK | Construction of Parking Lot for GMDC Academy | 2 | PRELIMINARY DESIGN | 2020-06-30 | 2020-10-27 | 2020-06-30 | 2020-10-27
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75GPARK | Construction of Parking Lot for GMDC Academy | 3 | FINAL DESIGN | 2020-10-28 | 2021-04-25 | 2020-10-28 | 2021-04-25
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75GPARK | Construction of Parking Lot for GMDC Academy | 4 | BID AWARD AND REGISTER CONTRCT | 2021-04-26 | 2021-07-24 | 2021-04-26 | 2021-07-24
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75GPARK | Construction of Parking Lot for GMDC Academy | 5 | CONSTRUCTION TO 25% | 2021-07-25 | 2021-11-21 | 2021-07-25 | 2021-11-21
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75GPARK | Construction of Parking Lot for GMDC Academy | 6 | CONSTRUCTION TO 50% | 2021-11-22 | 2022-03-21 | 2021-11-22 | 2022-03-21
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75GPARK | Construction of Parking Lot for GMDC Academy | 7 | CONSTRUCTION TO 75% | 2022-03-22 | 2022-07-19 | 2022-03-22 | 2022-07-19
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75GPARK | Construction of Parking Lot for GMDC Academy | 8 | ORIGINAL EQUIP & FURNISHING | 2022-07-20 | 2022-10-17 | 2022-07-20 | 2022-10-17
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75GPARK | Construction of Parking Lot for GMDC Academy | 9 | SUBSTANTIAL COMPLETION | 2022-10-18 | 2022-12-16 | 2022-10-18 | 2022-12-16
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75GPARK | Construction of Parking Lot for GMDC Academy | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-12-17 | 2023-01-15 | 2022-12-17 | 2025-06-30
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75GRVCHV | GRVC HVAC Upgrades and Related Housing Area Renovations | 1 | DESIGN | 2015-09-01 | 2016-07-02 | 2015-09-01 | 2016-07-02
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75GRVCHV | GRVC HVAC Upgrades and Related Housing Area Renovations | 2 | BID AWARD AND REGISTER CONTRCT | 2016-07-03 | 2017-07-02 | 2016-07-03 | 2017-07-02
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75GRVCHV | GRVC HVAC Upgrades and Related Housing Area Renovations | 3 | CONSTRUCTION TO 75% | 2017-07-03 | 2018-05-17 | 2017-07-03 | 2018-05-17
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75GRVCHV | GRVC HVAC Upgrades and Related Housing Area Renovations | 4 | SUBSTANTIAL COMPLETION | 2018-05-18 | 2018-07-20 | 2018-05-18 | 2018-07-20
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75GRVCHV | GRVC HVAC Upgrades and Related Housing Area Renovations | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-07-21 | 2018-09-01 | 2018-07-21 | 2020-09-01
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75GRVRFW | GRVC Roof Replacement, Exterior Facades, Windows, Court Yard | 1 | DESIGN | 2016-06-30 | 2016-12-30 | 2016-06-30 | 2016-12-30
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75GRVRFW | GRVC Roof Replacement, Exterior Facades, Windows, Court Yard | 2 | BID AWARD AND REGISTER CONTRCT | 2016-12-31 | 2017-12-30 | 2016-12-31 | 2017-12-30
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75GRVRFW | GRVC Roof Replacement, Exterior Facades, Windows, Court Yard | 3 | CONSTRUCTION TO 75% | 2017-12-31 | 2020-12-31 | 2017-12-31 | 2020-12-31
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75GRVRFW | GRVC Roof Replacement, Exterior Facades, Windows, Court Yard | 4 | SUBSTANTIAL COMPLETION | 2021-01-01 | 2020-12-31 | 2021-01-01 | 2020-12-31
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75GRVRFW | GRVC Roof Replacement, Exterior Facades, Windows, Court Yard | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-01-01 | 2021-05-26 | 2021-01-01 | 2021-05-26
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75K9UNIT | New K 9 Facility at Rikers Island | 1 | DEVELOP SCOPE | 2012-07-01 | 2012-09-28 | 2015-11-01 | 2016-01-29
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75K9UNIT | New K 9 Facility at Rikers Island | 2 | PRELIMINARY DESIGN | 2012-09-29 | 2013-01-26 | 2016-01-30 | 2016-05-28
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75K9UNIT | New K 9 Facility at Rikers Island | 3 | FINAL DESIGN | 2013-01-27 | 2013-07-25 | 2016-05-29 | 2016-11-24
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75K9UNIT | New K 9 Facility at Rikers Island | 4 | BID AWARD AND REGISTER CONTRCT | 2013-07-26 | 2013-10-23 | 2016-11-25 | 2016-12-24
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75K9UNIT | New K 9 Facility at Rikers Island | 5 | CONSTRUCTION TO 25% | 2013-10-24 | 2014-02-20 | 2019-08-30 | 2019-10-28
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75K9UNIT | New K 9 Facility at Rikers Island | 6 | CONSTRUCTION TO 50% | 2014-02-21 | 2014-06-20 | 2019-10-29 | 2020-01-01
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75K9UNIT | New K 9 Facility at Rikers Island | 7 | CONSTRUCTION TO 75% | 2014-06-21 | 2014-10-18 | 2020-01-02 | 2020-03-30
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75K9UNIT | New K 9 Facility at Rikers Island | 8 | ORIGINAL EQUIP & FURNISHING | 2014-10-19 | 2015-01-16 | 2020-03-31 | 2020-05-29
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75K9UNIT | New K 9 Facility at Rikers Island | 9 | SUBSTANTIAL COMPLETION | 2015-01-17 | 2015-03-17 | 2020-05-30 | 2020-06-28
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75K9UNIT | New K 9 Facility at Rikers Island | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-18 | 2015-04-16 | 2020-06-29 | 2020-08-27
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75MARINA | Rehabilitation of Existing Marina on RI | 1 | DEVELOP SCOPE | 2020-04-01 | 2020-06-29 | 2020-04-01 | 2020-06-29
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75MARINA | Rehabilitation of Existing Marina on RI | 2 | PRELIMINARY DESIGN | 2020-06-30 | 2020-10-27 | 2020-06-30 | 2020-10-27
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75MARINA | Rehabilitation of Existing Marina on RI | 3 | FINAL DESIGN | 2020-10-28 | 2021-04-25 | 2020-10-28 | 2021-04-25
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75MARINA | Rehabilitation of Existing Marina on RI | 4 | BID AWARD AND REGISTER CONTRCT | 2021-04-26 | 2021-07-24 | 2021-04-26 | 2021-07-24
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75MARINA | Rehabilitation of Existing Marina on RI | 5 | CONSTRUCTION TO 25% | 2021-07-25 | 2021-11-21 | 2021-07-25 | 2021-11-21
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75MARINA | Rehabilitation of Existing Marina on RI | 6 | CONSTRUCTION TO 50% | 2021-11-22 | 2022-03-21 | 2021-11-22 | 2022-03-21
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75MARINA | Rehabilitation of Existing Marina on RI | 7 | CONSTRUCTION TO 75% | 2022-03-22 | 2022-07-19 | 2022-03-22 | 2022-07-19
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75MARINA | Rehabilitation of Existing Marina on RI | 8 | ORIGINAL EQUIP & FURNISHING | 2022-07-20 | 2022-10-17 | 2022-07-20 | 2022-10-17
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75MARINA | Rehabilitation of Existing Marina on RI | 9 | SUBSTANTIAL COMPLETION | 2022-10-18 | 2022-12-16 | 2022-10-18 | 2022-12-16
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75MARINA | Rehabilitation of Existing Marina on RI | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-12-17 | 2023-01-15 | 2022-12-17 | 2023-01-15
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75-METH | Methane Detection System Replacement and Central Monitoring | 1 | DESIGN | 2015-12-01 | 2016-09-30 | 2015-12-01 | 2019-09-30
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75-METH | Methane Detection System Replacement and Central Monitoring | 2 | BID AWARD AND REGISTER CONTRCT | 2016-10-01 | 2017-09-30 | 2019-10-01 | 2020-09-29
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75-METH | Methane Detection System Replacement and Central Monitoring | 3 | CONSTRUCTION TO 75% | 2017-10-01 | 2019-05-16 | 2020-09-30 | 2022-05-15
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75-METH | Methane Detection System Replacement and Central Monitoring | 4 | SUBSTANTIAL COMPLETION | 2019-05-17 | 2019-09-12 | 2022-05-16 | 2022-09-11
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75-METH | Methane Detection System Replacement and Central Monitoring | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-13 | 2019-11-30 | 2022-09-12 | 2022-11-29
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75NICA/C | NIC Air Conditioning -Benjamin Ventilation Order | 1 | DEVELOP SCOPE | 2008-06-30 | 2008-09-27 | 2008-06-30 | 2008-09-27
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75NICA/C | NIC Air Conditioning -Benjamin Ventilation Order | 2 | PRELIMINARY DESIGN | 2008-09-28 | 2009-01-25 | 2008-09-28 | 2009-01-25
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75NICA/C | NIC Air Conditioning -Benjamin Ventilation Order | 3 | FINAL DESIGN | 2009-01-26 | 2009-07-24 | 2009-01-26 | 2009-07-24
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75NICA/C | NIC Air Conditioning -Benjamin Ventilation Order | 4 | BID AWARD AND REGISTER CONTRCT | 2009-07-25 | 2009-10-22 | 2009-07-25 | 2009-10-22
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75NICA/C | NIC Air Conditioning -Benjamin Ventilation Order | 5 | CONSTRUCTION TO 25% | 2009-10-23 | 2010-02-19 | 2009-10-23 | 2010-02-19
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75NICA/C | NIC Air Conditioning -Benjamin Ventilation Order | 6 | CONSTRUCTION TO 50% | 2010-02-20 | 2010-06-19 | 2010-02-20 | 2010-06-19
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75NICA/C | NIC Air Conditioning -Benjamin Ventilation Order | 7 | CONSTRUCTION TO 75% | 2010-06-20 | 2010-10-17 | 2010-06-20 | 2010-10-17
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75NICA/C | NIC Air Conditioning -Benjamin Ventilation Order | 8 | ORIGINAL EQUIP & FURNISHING | 2010-10-18 | 2011-01-15 | 2010-10-18 | 2011-01-15
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75NICA/C | NIC Air Conditioning -Benjamin Ventilation Order | 9 | SUBSTANTIAL COMPLETION | 2011-01-16 | 2011-03-16 | 2011-01-16 | 2011-03-16
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75NICA/C | NIC Air Conditioning -Benjamin Ventilation Order | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2011-03-17 | 2011-04-15 | 2011-03-17 | 2021-06-30
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75NICADA | NIC Annex Shower-2010 ADA Compliance-Dorm 1& 2B | 1 | DEVELOP SCOPE | 2013-07-31 | 2013-10-28 | 2013-07-31 | 2013-10-28
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75NICADA | NIC Annex Shower-2010 ADA Compliance-Dorm 1& 2B | 2 | PRELIMINARY DESIGN | 2013-10-29 | 2014-02-25 | 2013-10-29 | 2014-02-25
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75NICADA | NIC Annex Shower-2010 ADA Compliance-Dorm 1& 2B | 3 | FINAL DESIGN | 2014-02-26 | 2014-08-24 | 2014-02-26 | 2014-08-24
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75NICADA | NIC Annex Shower-2010 ADA Compliance-Dorm 1& 2B | 4 | BID AWARD AND REGISTER CONTRCT | 2014-08-25 | 2014-11-22 | 2014-08-25 | 2014-11-22
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75NICADA | NIC Annex Shower-2010 ADA Compliance-Dorm 1& 2B | 5 | CONSTRUCTION TO 25% | 2014-11-23 | 2015-03-22 | 2014-11-23 | 2015-03-22
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75NICADA | NIC Annex Shower-2010 ADA Compliance-Dorm 1& 2B | 6 | CONSTRUCTION TO 50% | 2015-03-23 | 2015-07-20 | 2015-03-23 | 2015-07-20
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75NICADA | NIC Annex Shower-2010 ADA Compliance-Dorm 1& 2B | 7 | CONSTRUCTION TO 75% | 2015-07-21 | 2015-11-17 | 2015-07-21 | 2015-11-17
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75NICADA | NIC Annex Shower-2010 ADA Compliance-Dorm 1& 2B | 8 | ORIGINAL EQUIP & FURNISHING | 2015-11-18 | 2016-02-15 | 2015-11-18 | 2016-02-15
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75NICADA | NIC Annex Shower-2010 ADA Compliance-Dorm 1& 2B | 9 | SUBSTANTIAL COMPLETION | 2016-02-16 | 2016-04-15 | 2016-02-16 | 2016-04-15
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75NICADA | NIC Annex Shower-2010 ADA Compliance-Dorm 1& 2B | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-04-16 | 2016-05-15 | 2016-04-16 | 2021-05-15
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75NICFAC | ROOF & FACADE RECONSTRUCTION FOR MAIN AND ANNEX | 1 | DESIGN | 2015-06-30 | 2016-04-30 | 2016-07-31 | 2017-05-31
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75NICFAC | ROOF & FACADE RECONSTRUCTION FOR MAIN AND ANNEX | 2 | BID AWARD AND REGISTER CONTRCT | 2016-05-01 | 2017-04-30 | 2017-06-01 | 2019-12-01
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75NICFAC | ROOF & FACADE RECONSTRUCTION FOR MAIN AND ANNEX | 3 | CONSTRUCTION TO 75% | 2017-05-01 | 2018-03-15 | 2019-12-02 | 2021-07-16
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75NICFAC | ROOF & FACADE RECONSTRUCTION FOR MAIN AND ANNEX | 4 | SUBSTANTIAL COMPLETION | 2018-03-16 | 2018-05-18 | 2021-07-17 | 2021-11-12
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75NICFAC | ROOF & FACADE RECONSTRUCTION FOR MAIN AND ANNEX | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-05-19 | 2018-06-30 | 2021-11-13 | 2022-01-30
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75OBDISH | OBCC Installation of Dishwasher | 1 | DESIGN | 2018-10-15 | 2019-08-16 | 2018-10-15 | 2019-08-16
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75OBDISH | OBCC Installation of Dishwasher | 2 | BID AWARD AND REGISTER CONTRCT | 2019-08-17 | 2020-08-15 | 2019-08-17 | 2020-08-15
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75OBDISH | OBCC Installation of Dishwasher | 3 | CONSTRUCTION TO 75% | 2020-08-16 | 2021-06-30 | 2020-08-16 | 2021-06-30
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75OBDISH | OBCC Installation of Dishwasher | 4 | SUBSTANTIAL COMPLETION | 2021-07-01 | 2021-09-02 | 2021-07-01 | 2021-09-02
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75OBDISH | OBCC Installation of Dishwasher | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-03 | 2021-10-15 | 2021-09-03 | 2021-10-15
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75PTREAT | Water Treatment for Powerhouse | 1 | DESIGN | 2018-09-01 | 2019-07-03 | 2018-09-01 | 2019-07-03
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75PTREAT | Water Treatment for Powerhouse | 2 | BID AWARD AND REGISTER CONTRCT | 2019-07-04 | 2020-07-02 | 2019-07-04 | 2020-07-02
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75PTREAT | Water Treatment for Powerhouse | 3 | CONSTRUCTION TO 75% | 2020-07-03 | 2021-05-17 | 2020-07-03 | 2021-05-17
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75PTREAT | Water Treatment for Powerhouse | 4 | SUBSTANTIAL COMPLETION | 2021-05-18 | 2021-07-20 | 2021-05-18 | 2021-07-20
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75PTREAT | Water Treatment for Powerhouse | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-07-21 | 2021-09-01 | 2021-07-21 | 2021-09-01
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75RDSRNG | New Modular Trailers and Classroom Renovation- Rodman's Neck | 1 | DESIGN | 2018-10-01 | 2019-08-01 | 2018-10-01 | 2019-08-01
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75RDSRNG | New Modular Trailers and Classroom Renovation- Rodman's Neck | 2 | BID AWARD AND REGISTER CONTRCT | 2019-08-02 | 2020-07-31 | 2019-08-02 | 2020-07-31
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75RDSRNG | New Modular Trailers and Classroom Renovation- Rodman's Neck | 3 | CONSTRUCTION TO 75% | 2020-08-01 | 2022-03-16 | 2020-08-01 | 2022-03-16
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75RDSRNG | New Modular Trailers and Classroom Renovation- Rodman's Neck | 4 | SUBSTANTIAL COMPLETION | 2022-03-17 | 2022-07-13 | 2022-03-17 | 2022-07-13
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75RDSRNG | New Modular Trailers and Classroom Renovation- Rodman's Neck | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-07-14 | 2022-09-30 | 2022-07-14 | 2022-09-30
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75RMPWR | RMSC Power Upgrades for buildings 1,2,3,4,5,6 & 7 | 1 | DESIGN | 2016-06-30 | 2017-04-30 | 2016-06-30 | 2017-04-30
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75RMPWR | RMSC Power Upgrades for buildings 1,2,3,4,5,6 & 7 | 2 | BID AWARD AND REGISTER CONTRCT | 2017-05-01 | 2018-04-30 | 2017-05-01 | 2018-04-30
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75RMPWR | RMSC Power Upgrades for buildings 1,2,3,4,5,6 & 7 | 3 | CONSTRUCTION TO 75% | 2018-05-01 | 2019-12-14 | 2018-05-01 | 2019-12-14
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75RMPWR | RMSC Power Upgrades for buildings 1,2,3,4,5,6 & 7 | 4 | SUBSTANTIAL COMPLETION | 2019-12-15 | 2020-04-11 | 2019-12-15 | 2020-04-11
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75RMPWR | RMSC Power Upgrades for buildings 1,2,3,4,5,6 & 7 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-04-12 | 2020-06-29 | 2020-04-12 | 2021-06-30
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75RMS-AC | RMSC A/C Power Upgrades for Bldgs 1,2,3,4,5,6 and 7 | 1 | DESIGN | 2017-06-30 | 2018-04-30 | 2017-06-30 | 2018-04-30
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75RMS-AC | RMSC A/C Power Upgrades for Bldgs 1,2,3,4,5,6 and 7 | 2 | BID AWARD AND REGISTER CONTRCT | 2018-05-01 | 2019-04-30 | 2018-05-01 | 2019-04-30
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75RMS-AC | RMSC A/C Power Upgrades for Bldgs 1,2,3,4,5,6 and 7 | 3 | CONSTRUCTION TO 75% | 2019-05-01 | 2020-12-13 | 2019-05-01 | 2020-12-13
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75RMS-AC | RMSC A/C Power Upgrades for Bldgs 1,2,3,4,5,6 and 7 | 4 | SUBSTANTIAL COMPLETION | 2020-12-14 | 2021-04-11 | 2020-12-14 | 2021-04-11
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75RMS-AC | RMSC A/C Power Upgrades for Bldgs 1,2,3,4,5,6 and 7 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-04-12 | 2021-06-29 | 2021-04-12 | 2021-06-29
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75RMSCAC | RMSC Air Conditioning-Benjamin Vent.Order | 1 | DEVELOP SCOPE | 2008-06-30 | 2008-09-27 | 2008-06-30 | 2008-09-27
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75RMSCAC | RMSC Air Conditioning-Benjamin Vent.Order | 2 | PRELIMINARY DESIGN | 2008-09-28 | 2009-01-25 | 2008-09-28 | 2009-01-25
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75RMSCAC | RMSC Air Conditioning-Benjamin Vent.Order | 3 | FINAL DESIGN | 2009-01-26 | 2009-07-24 | 2009-01-26 | 2009-07-24
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75RMSCAC | RMSC Air Conditioning-Benjamin Vent.Order | 4 | BID AWARD AND REGISTER CONTRCT | 2009-07-25 | 2009-10-22 | 2009-07-25 | 2009-10-22
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75RMSCAC | RMSC Air Conditioning-Benjamin Vent.Order | 5 | CONSTRUCTION TO 25% | 2009-10-23 | 2010-02-19 | 2009-10-23 | 2010-02-19
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75RMSCAC | RMSC Air Conditioning-Benjamin Vent.Order | 6 | CONSTRUCTION TO 50% | 2010-02-20 | 2010-06-19 | 2010-02-20 | 2010-06-19
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75RMSCAC | RMSC Air Conditioning-Benjamin Vent.Order | 7 | CONSTRUCTION TO 75% | 2010-06-20 | 2010-10-17 | 2010-06-20 | 2010-10-17
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75RMSCAC | RMSC Air Conditioning-Benjamin Vent.Order | 8 | ORIGINAL EQUIP & FURNISHING | 2010-10-18 | 2011-01-15 | 2010-10-18 | 2011-01-15
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75RMSCAC | RMSC Air Conditioning-Benjamin Vent.Order | 9 | SUBSTANTIAL COMPLETION | 2011-01-16 | 2011-03-16 | 2011-01-16 | 2011-03-16
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75RMSCAC | RMSC Air Conditioning-Benjamin Vent.Order | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2011-03-17 | 2011-04-15 | 2011-03-17 | 2011-12-31
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75RMSCHV | RMSC AHU,Duct Work,Heating,Ventilation & Cooling Equipment | 1 | DESIGN | 2016-06-30 | 2017-04-30 | 2016-06-30 | 2017-04-30
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75RMSCHV | RMSC AHU,Duct Work,Heating,Ventilation & Cooling Equipment | 2 | BID AWARD AND REGISTER CONTRCT | 2017-05-01 | 2018-04-30 | 2017-05-01 | 2018-04-30
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75RMSCHV | RMSC AHU,Duct Work,Heating,Ventilation & Cooling Equipment | 3 | CONSTRUCTION TO 75% | 2018-05-01 | 2019-12-14 | 2018-05-01 | 2019-12-14
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75RMSCHV | RMSC AHU,Duct Work,Heating,Ventilation & Cooling Equipment | 4 | SUBSTANTIAL COMPLETION | 2019-12-15 | 2020-04-11 | 2019-12-15 | 2020-04-11
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75RMSCHV | RMSC AHU,Duct Work,Heating,Ventilation & Cooling Equipment | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-04-12 | 2020-06-29 | 2020-04-12 | 2021-06-30
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75RMSRFW | RMSC Roof Replacement, Exterior Facades, Windows, Court Yard | 1 | DESIGN | 2016-06-30 | 2016-12-30 | 2016-06-30 | 2016-12-30
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75RMSRFW | RMSC Roof Replacement, Exterior Facades, Windows, Court Yard | 2 | BID AWARD AND REGISTER CONTRCT | 2016-12-31 | 2017-12-30 | 2016-12-31 | 2017-12-30
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75RMSRFW | RMSC Roof Replacement, Exterior Facades, Windows, Court Yard | 3 | CONSTRUCTION TO 75% | 2017-12-31 | 2020-12-31 | 2017-12-31 | 2020-12-31
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75RMSRFW | RMSC Roof Replacement, Exterior Facades, Windows, Court Yard | 4 | SUBSTANTIAL COMPLETION | 2021-01-01 | 2020-12-31 | 2021-01-01 | 2020-12-31
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75RMSRFW | RMSC Roof Replacement, Exterior Facades, Windows, Court Yard | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-01-01 | 2021-05-26 | 2021-01-01 | 2021-05-26
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75SEAWLL | Construction of Sea Wall and Raising of Madanici Road | 1 | DESIGN | 2014-06-30 | 2014-07-29 | 2016-04-01 | 2017-12-31
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75SEAWLL | Construction of Sea Wall and Raising of Madanici Road | 2 | BID AWARD AND REGISTER CONTRCT | 2014-07-30 | 2014-10-27 | 2018-01-01 | 2020-05-30
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75SEAWLL | Construction of Sea Wall and Raising of Madanici Road | 3 | CONSTRUCTION | 2014-10-28 | 2015-04-25 | 2020-05-31 | 2022-01-13
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75SEAWLL | Construction of Sea Wall and Raising of Madanici Road | 4 | ORIGINAL EQUIP & FURNISHING | 2015-04-26 | 2015-07-24 | 2022-01-14 | 2022-05-12
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75SEAWLL | Construction of Sea Wall and Raising of Madanici Road | 5 | SUBSTANTIAL COMPLETION | 2015-07-25 | 2015-08-23 | 2022-05-13 | 2025-07-30
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75SEAWLL | Construction of Sea Wall and Raising of Madanici Road | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-08-24 | 2015-09-22 | 2022-05-13 | 2025-07-30
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75STDRN | Replace Storm Water Mains and Outfalls | 1 | DESIGN | 2015-12-01 | 2016-09-30 | 2015-12-01 | 2016-09-30
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75STDRN | Replace Storm Water Mains and Outfalls | 2 | BID AWARD AND REGISTER CONTRCT | 2016-10-01 | 2017-09-30 | 2016-10-01 | 2017-09-30
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75STDRN | Replace Storm Water Mains and Outfalls | 3 | CONSTRUCTION TO 75% | 2017-10-01 | 2019-05-16 | 2017-10-01 | 2019-05-16
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75STDRN | Replace Storm Water Mains and Outfalls | 4 | SUBSTANTIAL COMPLETION | 2019-05-17 | 2019-09-12 | 2019-05-17 | 2019-09-12
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75STDRN | Replace Storm Water Mains and Outfalls | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-13 | 2019-11-30 | 2019-09-13 | 2023-06-30
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75STEAM | Upgrade Steam Lines | 1 | DESIGN | 2015-12-01 | 2016-09-30 | 2015-12-01 | 2016-09-30
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75STEAM | Upgrade Steam Lines | 2 | BID AWARD AND REGISTER CONTRCT | 2016-10-01 | 2017-09-30 | 2016-10-01 | 2017-09-30
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75STEAM | Upgrade Steam Lines | 3 | CONSTRUCTION TO 75% | 2017-10-01 | 2019-05-16 | 2017-10-01 | 2019-05-16
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75STEAM | Upgrade Steam Lines | 4 | SUBSTANTIAL COMPLETION | 2019-05-17 | 2019-09-12 | 2019-05-17 | 2019-09-12
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75STEAM | Upgrade Steam Lines | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-13 | 2019-11-30 | 2019-09-13 | 2022-11-30
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75SUPFC | Exterior Reconstruction for Support Facilities | 1 | DEVELOP SCOPE | 2015-08-01 | 2015-10-29 | 2015-08-01 | 2015-10-29
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75SUPFC | Exterior Reconstruction for Support Facilities | 2 | PRELIMINARY DESIGN | 2015-10-30 | 2016-02-26 | 2015-10-30 | 2016-02-26
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75SUPFC | Exterior Reconstruction for Support Facilities | 3 | FINAL DESIGN | 2016-02-27 | 2016-08-24 | 2016-02-27 | 2016-08-24
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75SUPFC | Exterior Reconstruction for Support Facilities | 4 | BID AWARD AND REGISTER CONTRCT | 2016-08-25 | 2016-11-22 | 2016-08-25 | 2016-11-22
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75SUPFC | Exterior Reconstruction for Support Facilities | 5 | CONSTRUCTION TO 25% | 2016-11-23 | 2017-03-22 | 2016-11-23 | 2017-03-22
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75SUPFC | Exterior Reconstruction for Support Facilities | 6 | CONSTRUCTION TO 50% | 2017-03-23 | 2017-07-20 | 2017-03-23 | 2017-07-20
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75SUPFC | Exterior Reconstruction for Support Facilities | 7 | CONSTRUCTION TO 75% | 2017-07-21 | 2017-11-17 | 2017-07-21 | 2017-11-17
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75SUPFC | Exterior Reconstruction for Support Facilities | 8 | ORIGINAL EQUIP & FURNISHING | 2017-11-18 | 2018-02-15 | 2017-11-18 | 2018-02-15
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75SUPFC | Exterior Reconstruction for Support Facilities | 9 | SUBSTANTIAL COMPLETION | 2018-02-16 | 2018-04-16 | 2018-02-16 | 2018-04-16
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75SUPFC | Exterior Reconstruction for Support Facilities | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-04-17 | 2018-05-16 | 2018-04-17 | 2027-05-16
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75SWITCH | REPLACEMENT OF ELECTRICAL AUTOMATIC TRANSFER SWITCHES | 1 | DESIGN | 2016-05-30 | 2016-06-28 | 2015-07-01 | 2016-05-01
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75SWITCH | REPLACEMENT OF ELECTRICAL AUTOMATIC TRANSFER SWITCHES | 2 | BID AWARD AND REGISTER CONTRCT | 2016-06-29 | 2016-09-26 | 2016-05-02 | 2017-05-01
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75SWITCH | REPLACEMENT OF ELECTRICAL AUTOMATIC TRANSFER SWITCHES | 3 | CONSTRUCTION | 2016-09-27 | 2017-03-25 | 2017-05-02 | 2018-03-16
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75SWITCH | REPLACEMENT OF ELECTRICAL AUTOMATIC TRANSFER SWITCHES | 4 | ORIGINAL EQUIP & FURNISHING | 2017-03-26 | 2017-06-23 | 2018-03-17 | 2018-05-19
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75SWITCH | REPLACEMENT OF ELECTRICAL AUTOMATIC TRANSFER SWITCHES | 5 | SUBSTANTIAL COMPLETION | 2017-06-24 | 2017-07-23 | 2018-05-20 | 2022-07-01
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75SWITCH | REPLACEMENT OF ELECTRICAL AUTOMATIC TRANSFER SWITCHES | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-07-24 | 2017-08-22 | 2018-05-20 | 2022-07-01
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75SWITCH | REPLACEMENT OF ELECTRICAL AUTOMATIC TRANSFER SWITCHES | 7 | DESIGN | 2017-08-23 | 2018-06-23 | 2018-05-20 | 2022-07-01
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75SWITCH | REPLACEMENT OF ELECTRICAL AUTOMATIC TRANSFER SWITCHES | 8 | BID AWARD AND REGISTER CONTRCT | 2018-06-24 | 2019-06-23 | 2018-05-20 | 2022-07-01
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75SWITCH | REPLACEMENT OF ELECTRICAL AUTOMATIC TRANSFER SWITCHES | 9 | CONSTRUCTION TO 75% | 2019-06-24 | 2021-02-05 | 2018-05-20 | 2022-07-01
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75SWITCH | REPLACEMENT OF ELECTRICAL AUTOMATIC TRANSFER SWITCHES | 10 | SUBSTANTIAL COMPLETION | 2021-02-06 | 2021-06-04 | 2018-05-20 | 2022-07-01
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75SWITCH | REPLACEMENT OF ELECTRICAL AUTOMATIC TRANSFER SWITCHES | 11 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-06-05 | 2021-08-22 | 2018-05-20 | 2022-07-01
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75TMTRLR | Design and Installation of new Teams Modular Building | 1 | DEVELOP SCOPE | 2019-04-01 | 2019-06-29 | 2019-04-01 | 2019-06-29
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75TMTRLR | Design and Installation of new Teams Modular Building | 2 | PRELIMINARY DESIGN | 2019-06-30 | 2019-10-27 | 2019-06-30 | 2019-10-27
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75TMTRLR | Design and Installation of new Teams Modular Building | 3 | FINAL DESIGN | 2019-10-28 | 2019-12-31 | 2019-10-28 | 2019-12-31
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75TMTRLR | Design and Installation of new Teams Modular Building | 4 | BID AWARD AND REGISTER CONTRCT | 2020-01-01 | 2020-03-30 | 2020-01-01 | 2020-03-30
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75TMTRLR | Design and Installation of new Teams Modular Building | 5 | CONSTRUCTION TO 25% | 2020-03-31 | 2020-07-28 | 2020-03-31 | 2020-07-28
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75TMTRLR | Design and Installation of new Teams Modular Building | 6 | CONSTRUCTION TO 50% | 2020-07-29 | 2020-11-25 | 2020-07-29 | 2020-11-25
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75TMTRLR | Design and Installation of new Teams Modular Building | 7 | CONSTRUCTION TO 75% | 2020-11-26 | 2021-03-25 | 2020-11-26 | 2021-03-25
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75TMTRLR | Design and Installation of new Teams Modular Building | 8 | ORIGINAL EQUIP & FURNISHING | 2021-03-26 | 2021-06-23 | 2021-03-26 | 2021-06-23
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75TMTRLR | Design and Installation of new Teams Modular Building | 9 | SUBSTANTIAL COMPLETION | 2021-06-24 | 2021-08-22 | 2021-06-24 | 2021-08-22
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75TMTRLR | Design and Installation of new Teams Modular Building | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-08-23 | 2021-09-21 | 2021-08-23 | 2025-09-21
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75VLAUND | VCBC Laundry System Installation | 1 | DESIGN | 2014-06-30 | 2014-07-29 | 2014-06-30 | 2014-07-29
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75VLAUND | VCBC Laundry System Installation | 2 | BID AWARD AND REGISTER CONTRCT | 2014-07-30 | 2014-10-27 | 2014-07-30 | 2014-10-27
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75VLAUND | VCBC Laundry System Installation | 3 | CONSTRUCTION | 2014-10-28 | 2015-04-25 | 2014-10-28 | 2015-04-25
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75VLAUND | VCBC Laundry System Installation | 4 | ORIGINAL EQUIP & FURNISHING | 2015-04-26 | 2015-07-24 | 2015-04-26 | 2015-07-24
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75VLAUND | VCBC Laundry System Installation | 5 | SUBSTANTIAL COMPLETION | 2015-07-25 | 2015-08-23 | 2015-07-25 | 2015-08-23
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75VLAUND | VCBC Laundry System Installation | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-08-24 | 2015-09-22 | 2015-08-24 | 2021-09-22
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDAMKC | Hurricane Sandy - AMKC Roof Reconstruction | 1 | DEVELOP SCOPE | 2012-12-01 | 2013-02-28 | 2012-12-01 | 2013-02-28
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDAMKC | Hurricane Sandy - AMKC Roof Reconstruction | 2 | PRELIMINARY DESIGN | 2013-03-01 | 2013-06-28 | 2013-03-01 | 2013-06-28
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDAMKC | Hurricane Sandy - AMKC Roof Reconstruction | 3 | FINAL DESIGN | 2013-06-29 | 2013-12-25 | 2013-06-29 | 2013-12-25
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDAMKC | Hurricane Sandy - AMKC Roof Reconstruction | 4 | BID AWARD AND REGISTER CONTRCT | 2013-12-26 | 2014-03-25 | 2013-12-26 | 2014-03-25
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDAMKC | Hurricane Sandy - AMKC Roof Reconstruction | 5 | CONSTRUCTION TO 25% | 2014-03-26 | 2014-07-23 | 2014-03-26 | 2014-07-23
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDAMKC | Hurricane Sandy - AMKC Roof Reconstruction | 6 | CONSTRUCTION TO 50% | 2014-07-24 | 2014-11-20 | 2014-07-24 | 2014-11-20
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDAMKC | Hurricane Sandy - AMKC Roof Reconstruction | 7 | CONSTRUCTION TO 75% | 2014-11-21 | 2015-03-20 | 2014-11-21 | 2015-03-20
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDAMKC | Hurricane Sandy - AMKC Roof Reconstruction | 8 | ORIGINAL EQUIP & FURNISHING | 2015-03-21 | 2015-06-18 | 2015-03-21 | 2015-06-18
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDAMKC | Hurricane Sandy - AMKC Roof Reconstruction | 9 | SUBSTANTIAL COMPLETION | 2015-06-19 | 2015-08-17 | 2015-06-19 | 2015-08-17
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDAMKC | Hurricane Sandy - AMKC Roof Reconstruction | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-08-18 | 2015-09-16 | 2015-08-18 | 2021-10-30
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDCONDT | Hurricane Sandy Underground Conduits at VCBC | 1 | DESIGN | 2015-06-30 | 2016-04-30 | 2015-06-30 | 2016-04-30
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDCONDT | Hurricane Sandy Underground Conduits at VCBC | 2 | BID AWARD AND REGISTER CONTRCT | 2016-05-01 | 2017-04-30 | 2016-05-01 | 2017-04-30
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDCONDT | Hurricane Sandy Underground Conduits at VCBC | 3 | CONSTRUCTION TO 75% | 2017-05-01 | 2018-03-15 | 2017-05-01 | 2018-03-15
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDCONDT | Hurricane Sandy Underground Conduits at VCBC | 4 | SUBSTANTIAL COMPLETION | 2018-03-16 | 2018-05-18 | 2018-03-16 | 2018-05-18
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDCONDT | Hurricane Sandy Underground Conduits at VCBC | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-05-19 | 2018-06-30 | 2018-05-19 | 2021-06-30
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDHART | Hurricane Sandy-harts island Reconstruct from storm damage | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2013-09-28
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDHART | Hurricane Sandy-harts island Reconstruct from storm damage | 2 | PRELIMINARY DESIGN | 2013-09-29 | 2014-01-26 | 2013-09-29 | 2014-01-26
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDHART | Hurricane Sandy-harts island Reconstruct from storm damage | 3 | FINAL DESIGN | 2014-01-27 | 2014-07-25 | 2014-01-27 | 2014-07-25
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDHART | Hurricane Sandy-harts island Reconstruct from storm damage | 4 | BID AWARD AND REGISTER CONTRCT | 2014-07-26 | 2014-10-23 | 2014-07-26 | 2014-10-23
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDHART | Hurricane Sandy-harts island Reconstruct from storm damage | 5 | CONSTRUCTION TO 25% | 2014-10-24 | 2015-02-20 | 2014-10-24 | 2015-02-20
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDHART | Hurricane Sandy-harts island Reconstruct from storm damage | 6 | CONSTRUCTION TO 50% | 2015-02-21 | 2015-06-20 | 2015-02-21 | 2015-06-20
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDHART | Hurricane Sandy-harts island Reconstruct from storm damage | 7 | CONSTRUCTION TO 75% | 2015-06-21 | 2015-10-18 | 2015-06-21 | 2015-10-18
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDHART | Hurricane Sandy-harts island Reconstruct from storm damage | 8 | ORIGINAL EQUIP & FURNISHING | 2015-10-19 | 2016-01-16 | 2015-10-19 | 2016-01-16
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDHART | Hurricane Sandy-harts island Reconstruct from storm damage | 9 | SUBSTANTIAL COMPLETION | 2016-01-17 | 2016-03-16 | 2016-01-17 | 2016-03-16
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDHART | Hurricane Sandy-harts island Reconstruct from storm damage | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-17 | 2016-04-15 | 2016-03-17 | 2021-06-30
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDRNDC | Hurricane Sandy - RNDC Roof Reconstruction | 1 | DEVELOP SCOPE | 2013-07-31 | 2013-10-28 | 2013-07-31 | 2013-10-28
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDRNDC | Hurricane Sandy - RNDC Roof Reconstruction | 2 | PRELIMINARY DESIGN | 2013-10-29 | 2014-02-25 | 2013-10-29 | 2014-02-25
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDRNDC | Hurricane Sandy - RNDC Roof Reconstruction | 3 | FINAL DESIGN | 2014-02-26 | 2014-08-24 | 2014-02-26 | 2014-08-24
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDRNDC | Hurricane Sandy - RNDC Roof Reconstruction | 4 | BID AWARD AND REGISTER CONTRCT | 2014-08-25 | 2014-11-22 | 2014-08-25 | 2014-11-22
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDRNDC | Hurricane Sandy - RNDC Roof Reconstruction | 5 | CONSTRUCTION TO 25% | 2014-11-23 | 2015-03-22 | 2014-11-23 | 2018-03-22
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDRNDC | Hurricane Sandy - RNDC Roof Reconstruction | 6 | CONSTRUCTION TO 50% | 2015-03-23 | 2015-07-20 | 2018-03-23 | 2019-07-20
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDRNDC | Hurricane Sandy - RNDC Roof Reconstruction | 7 | CONSTRUCTION TO 75% | 2015-07-21 | 2015-11-17 | 2019-07-21 | 2019-11-17
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDRNDC | Hurricane Sandy - RNDC Roof Reconstruction | 8 | ORIGINAL EQUIP & FURNISHING | 2015-11-18 | 2016-02-15 | 2019-11-18 | 2020-02-15
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDRNDC | Hurricane Sandy - RNDC Roof Reconstruction | 9 | SUBSTANTIAL COMPLETION | 2016-02-16 | 2016-04-15 | 2020-02-16 | 2020-04-15
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDRNDC | Hurricane Sandy - RNDC Roof Reconstruction | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-04-16 | 2016-05-15 | 2020-04-16 | 2021-06-30
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDSHORE | Hurricane Sandy- RI NShoreline Reconstruct from Storm Damage | 1 | DEVELOP SCOPE | 2012-11-01 | 2013-01-29 | 2012-11-01 | 2013-01-29
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDSHORE | Hurricane Sandy- RI NShoreline Reconstruct from Storm Damage | 2 | PRELIMINARY DESIGN | 2013-01-30 | 2013-05-29 | 2013-01-30 | 2013-05-29
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDSHORE | Hurricane Sandy- RI NShoreline Reconstruct from Storm Damage | 3 | FINAL DESIGN | 2013-05-30 | 2013-11-25 | 2013-05-30 | 2013-11-25
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDSHORE | Hurricane Sandy- RI NShoreline Reconstruct from Storm Damage | 4 | BID AWARD AND REGISTER CONTRCT | 2013-11-26 | 2014-02-23 | 2013-11-26 | 2014-02-23
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDSHORE | Hurricane Sandy- RI NShoreline Reconstruct from Storm Damage | 5 | CONSTRUCTION TO 25% | 2014-02-24 | 2014-06-23 | 2014-02-24 | 2014-06-23
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDSHORE | Hurricane Sandy- RI NShoreline Reconstruct from Storm Damage | 6 | CONSTRUCTION TO 50% | 2014-06-24 | 2014-10-21 | 2014-06-24 | 2014-10-21
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDSHORE | Hurricane Sandy- RI NShoreline Reconstruct from Storm Damage | 7 | CONSTRUCTION TO 75% | 2014-10-22 | 2015-02-18 | 2014-10-22 | 2015-02-18
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDSHORE | Hurricane Sandy- RI NShoreline Reconstruct from Storm Damage | 8 | ORIGINAL EQUIP & FURNISHING | 2015-02-19 | 2015-05-19 | 2015-02-19 | 2015-05-19
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDSHORE | Hurricane Sandy- RI NShoreline Reconstruct from Storm Damage | 9 | SUBSTANTIAL COMPLETION | 2015-05-20 | 2015-07-18 | 2015-05-20 | 2015-07-18
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDSHORE | Hurricane Sandy- RI NShoreline Reconstruct from Storm Damage | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-07-19 | 2015-08-17 | 2015-07-19 | 2021-08-17
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDTRLR | Hurricane Sandy-Relocation of RI Trailers - Storm Damage | 1 | DEVELOP SCOPE | 2013-06-01 | 2013-08-29 | 2013-06-01 | 2013-08-29
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDTRLR | Hurricane Sandy-Relocation of RI Trailers - Storm Damage | 2 | PRELIMINARY DESIGN | 2013-08-30 | 2013-12-27 | 2013-08-30 | 2013-12-27
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDTRLR | Hurricane Sandy-Relocation of RI Trailers - Storm Damage | 3 | FINAL DESIGN | 2013-12-28 | 2014-06-25 | 2013-12-28 | 2014-06-25
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDTRLR | Hurricane Sandy-Relocation of RI Trailers - Storm Damage | 4 | BID AWARD AND REGISTER CONTRCT | 2014-06-26 | 2014-09-23 | 2014-06-26 | 2019-09-23
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDTRLR | Hurricane Sandy-Relocation of RI Trailers - Storm Damage | 5 | CONSTRUCTION TO 25% | 2014-09-24 | 2015-01-21 | 2019-09-24 | 2020-01-21
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDTRLR | Hurricane Sandy-Relocation of RI Trailers - Storm Damage | 6 | CONSTRUCTION TO 50% | 2015-01-22 | 2015-05-21 | 2020-01-22 | 2020-05-21
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDTRLR | Hurricane Sandy-Relocation of RI Trailers - Storm Damage | 7 | CONSTRUCTION TO 75% | 2015-05-22 | 2015-09-18 | 2020-05-22 | 2020-09-18
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDTRLR | Hurricane Sandy-Relocation of RI Trailers - Storm Damage | 8 | ORIGINAL EQUIP & FURNISHING | 2015-09-19 | 2015-12-17 | 2020-09-19 | 2020-12-17
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDTRLR | Hurricane Sandy-Relocation of RI Trailers - Storm Damage | 9 | SUBSTANTIAL COMPLETION | 2015-12-18 | 2016-02-15 | 2020-12-18 | 2021-02-15
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDTRLR | Hurricane Sandy-Relocation of RI Trailers - Storm Damage | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-02-16 | 2016-03-16 | 2021-02-16 | 2021-03-16
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDVCBC | Hurricane Sandy - VCBC Reconstruction Due To Storm Damage | 1 | DEVELOP SCOPE | 2012-11-01 | 2013-01-29 | 2012-11-01 | 2013-01-29
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDVCBC | Hurricane Sandy - VCBC Reconstruction Due To Storm Damage | 2 | PRELIMINARY DESIGN | 2013-01-30 | 2013-05-29 | 2013-01-30 | 2013-05-29
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDVCBC | Hurricane Sandy - VCBC Reconstruction Due To Storm Damage | 3 | FINAL DESIGN | 2013-05-30 | 2013-11-25 | 2013-05-30 | 2013-11-25
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDVCBC | Hurricane Sandy - VCBC Reconstruction Due To Storm Damage | 4 | BID AWARD AND REGISTER CONTRCT | 2013-11-26 | 2014-02-23 | 2013-11-26 | 2014-02-23
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDVCBC | Hurricane Sandy - VCBC Reconstruction Due To Storm Damage | 5 | CONSTRUCTION TO 25% | 2014-02-24 | 2014-06-23 | 2014-02-24 | 2014-06-23
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDVCBC | Hurricane Sandy - VCBC Reconstruction Due To Storm Damage | 6 | CONSTRUCTION TO 50% | 2014-06-24 | 2014-10-21 | 2014-06-24 | 2014-10-21
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDVCBC | Hurricane Sandy - VCBC Reconstruction Due To Storm Damage | 7 | CONSTRUCTION TO 75% | 2014-10-22 | 2015-02-18 | 2014-10-22 | 2015-02-18
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDVCBC | Hurricane Sandy - VCBC Reconstruction Due To Storm Damage | 8 | ORIGINAL EQUIP & FURNISHING | 2015-02-19 | 2015-05-19 | 2015-02-19 | 2015-05-19
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDVCBC | Hurricane Sandy - VCBC Reconstruction Due To Storm Damage | 9 | SUBSTANTIAL COMPLETION | 2015-05-20 | 2015-07-18 | 2015-05-20 | 2015-07-18
20201123 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDVCBC | Hurricane Sandy - VCBC Reconstruction Due To Storm Damage | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-07-19 | 2015-08-17 | 2015-07-19 | 2021-08-17
20201123 | BRONX | 096 | HUMAN RESOURCES ADMINISTRATION | HR25305RC | 305 Rider Avenue construction | 1 | DESIGN | 2020-07-01 | 2020-12-27 | 2020-07-01 | 2020-12-27
20201123 | BRONX | 096 | HUMAN RESOURCES ADMINISTRATION | HR25305RC | 305 Rider Avenue construction | 2 | CONSTRUCTION | 2020-12-28 | 2021-06-25 | 2020-12-28 | 2021-06-25
20201123 | BRONX | 096 | HUMAN RESOURCES ADMINISTRATION | HR25TREMC | 555 E Tremont Construction | 1 | DESIGN | 2021-10-01 | 2022-03-29 | 2021-10-01 | 2022-03-29
20201123 | BRONX | 096 | HUMAN RESOURCES ADMINISTRATION | HR25TREMC | 555 E Tremont Construction | 2 | CONSTRUCTION | 2022-03-30 | 2022-09-25 | 2022-03-30 | 2022-09-25
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | ACEDCA433 | DCLA: Wildlife Conservation Society: Bronx Zoo Roofs | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-09-28 | 2020-06-30 | 2020-09-27
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | ACEDCA433 | DCLA: Wildlife Conservation Society: Bronx Zoo Roofs | 2 | PRELIMINARY DESIGN | 2016-09-29 | 2017-01-26 | 2020-09-28 | 2021-01-25
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | ACEDCA433 | DCLA: Wildlife Conservation Society: Bronx Zoo Roofs | 3 | FINAL DESIGN | 2017-01-27 | 2017-07-25 | 2021-01-26 | 2021-07-24
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | ACEDCA433 | DCLA: Wildlife Conservation Society: Bronx Zoo Roofs | 4 | BID AWARD AND REGISTER CONTRCT | 2017-07-26 | 2017-10-23 | 2021-07-25 | 2021-10-22
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | ACEDCA433 | DCLA: Wildlife Conservation Society: Bronx Zoo Roofs | 5 | CONSTRUCTION TO 25% | 2017-10-24 | 2018-02-20 | 2021-10-23 | 2022-02-19
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | ACEDCA433 | DCLA: Wildlife Conservation Society: Bronx Zoo Roofs | 6 | CONSTRUCTION TO 50% | 2018-02-21 | 2018-06-20 | 2022-02-20 | 2022-06-19
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | ACEDCA433 | DCLA: Wildlife Conservation Society: Bronx Zoo Roofs | 7 | CONSTRUCTION TO 75% | 2018-06-21 | 2018-10-18 | 2022-06-20 | 2022-10-17
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | ACEDCA433 | DCLA: Wildlife Conservation Society: Bronx Zoo Roofs | 8 | ORIGINAL EQUIP & FURNISHING | 2018-10-19 | 2019-01-16 | 2022-10-18 | 2023-01-15
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | ACEDCA433 | DCLA: Wildlife Conservation Society: Bronx Zoo Roofs | 9 | SUBSTANTIAL COMPLETION | 2019-01-17 | 2019-03-17 | 2023-01-16 | 2023-03-16
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | ACEDCA433 | DCLA: Wildlife Conservation Society: Bronx Zoo Roofs | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-03-18 | 2019-04-16 | 2023-03-17 | 2023-04-15
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176-BLR | WCS Bronx Zoo - Boiler Replacement Various Bldgs. | 1 | DEVELOP SCOPE | 2013-03-01 | 2013-05-29 | 2022-06-30 | 2022-09-27
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176-BLR | WCS Bronx Zoo - Boiler Replacement Various Bldgs. | 2 | PRELIMINARY DESIGN | 2013-05-30 | 2013-09-26 | 2022-09-28 | 2023-01-25
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176-BLR | WCS Bronx Zoo - Boiler Replacement Various Bldgs. | 3 | FINAL DESIGN | 2013-09-27 | 2014-03-25 | 2023-01-26 | 2023-07-24
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176-BLR | WCS Bronx Zoo - Boiler Replacement Various Bldgs. | 4 | BID AWARD AND REGISTER CONTRCT | 2014-03-26 | 2014-06-23 | 2023-07-25 | 2023-10-22
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176-BLR | WCS Bronx Zoo - Boiler Replacement Various Bldgs. | 5 | CONSTRUCTION TO 25% | 2014-06-24 | 2014-10-21 | 2023-10-23 | 2024-02-19
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176-BLR | WCS Bronx Zoo - Boiler Replacement Various Bldgs. | 6 | CONSTRUCTION TO 50% | 2014-10-22 | 2015-02-18 | 2024-02-20 | 2024-06-18
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176-BLR | WCS Bronx Zoo - Boiler Replacement Various Bldgs. | 7 | CONSTRUCTION TO 75% | 2015-02-19 | 2015-06-18 | 2024-06-19 | 2024-10-16
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176-BLR | WCS Bronx Zoo - Boiler Replacement Various Bldgs. | 8 | ORIGINAL EQUIP & FURNISHING | 2015-06-19 | 2015-09-16 | 2024-10-17 | 2025-01-14
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176-BLR | WCS Bronx Zoo - Boiler Replacement Various Bldgs. | 9 | SUBSTANTIAL COMPLETION | 2015-09-17 | 2015-11-15 | 2025-01-15 | 2025-03-15
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176-BLR | WCS Bronx Zoo - Boiler Replacement Various Bldgs. | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-11-16 | 2015-12-15 | 2025-03-16 | 2025-04-14
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176CES2 | WCS - Bronx Zoo - Switch Gear Phase 2 | 1 | DEVELOP SCOPE | 2023-06-30 | 2023-09-27 | 2023-06-30 | 2023-09-27
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176CES2 | WCS - Bronx Zoo - Switch Gear Phase 2 | 2 | PRELIMINARY DESIGN | 2023-09-28 | 2024-01-25 | 2023-09-28 | 2024-01-25
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176CES2 | WCS - Bronx Zoo - Switch Gear Phase 2 | 3 | FINAL DESIGN | 2024-01-26 | 2024-07-23 | 2024-01-26 | 2024-07-23
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176CES2 | WCS - Bronx Zoo - Switch Gear Phase 2 | 4 | BID AWARD AND REGISTER CONTRCT | 2024-07-24 | 2024-10-21 | 2024-07-24 | 2024-10-21
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176CES2 | WCS - Bronx Zoo - Switch Gear Phase 2 | 5 | CONSTRUCTION TO 25% | 2024-10-22 | 2025-02-18 | 2024-10-22 | 2025-02-18
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176CES2 | WCS - Bronx Zoo - Switch Gear Phase 2 | 6 | CONSTRUCTION TO 50% | 2025-02-19 | 2025-06-18 | 2025-02-19 | 2025-06-18
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176CES2 | WCS - Bronx Zoo - Switch Gear Phase 2 | 7 | CONSTRUCTION TO 75% | 2025-06-19 | 2025-10-16 | 2025-06-19 | 2025-10-16
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176CES2 | WCS - Bronx Zoo - Switch Gear Phase 2 | 8 | ORIGINAL EQUIP & FURNISHING | 2025-10-17 | 2026-01-14 | 2025-10-17 | 2026-01-14
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176CES2 | WCS - Bronx Zoo - Switch Gear Phase 2 | 9 | SUBSTANTIAL COMPLETION | 2026-01-15 | 2026-03-15 | 2026-01-15 | 2026-03-15
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176CES2 | WCS - Bronx Zoo - Switch Gear Phase 2 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2026-03-16 | 2026-04-14 | 2026-03-16 | 2026-04-14
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176GELA | WCS - Bronx Zoo - Gelada Exhibit | 1 | DEVELOP SCOPE | 2019-03-01 | 2019-09-01 | 2023-06-30 | 2023-12-31
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176GELA | WCS - Bronx Zoo - Gelada Exhibit | 2 | PRELIMINARY DESIGN | 2019-09-02 | 2019-12-30 | 2024-01-01 | 2024-04-29
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176GELA | WCS - Bronx Zoo - Gelada Exhibit | 3 | FINAL DESIGN | 2019-12-31 | 2020-06-27 | 2024-04-30 | 2024-10-26
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176GELA | WCS - Bronx Zoo - Gelada Exhibit | 4 | BID AWARD AND REGISTER CONTRCT | 2020-06-28 | 2020-09-25 | 2024-10-27 | 2025-01-24
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176GELA | WCS - Bronx Zoo - Gelada Exhibit | 5 | CONSTRUCTION TO 25% | 2020-09-26 | 2021-01-23 | 2025-01-25 | 2025-05-24
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176GELA | WCS - Bronx Zoo - Gelada Exhibit | 6 | CONSTRUCTION TO 50% | 2021-01-24 | 2021-05-23 | 2025-05-25 | 2025-09-21
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176GELA | WCS - Bronx Zoo - Gelada Exhibit | 7 | CONSTRUCTION TO 75% | 2021-05-24 | 2021-09-20 | 2025-09-22 | 2026-01-19
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176GELA | WCS - Bronx Zoo - Gelada Exhibit | 8 | ORIGINAL EQUIP & FURNISHING | 2021-09-21 | 2021-12-19 | 2026-01-20 | 2026-04-19
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176GELA | WCS - Bronx Zoo - Gelada Exhibit | 9 | SUBSTANTIAL COMPLETION | 2021-12-20 | 2022-02-17 | 2026-04-20 | 2026-06-18
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176GELA | WCS - Bronx Zoo - Gelada Exhibit | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-02-18 | 2022-03-19 | 2026-06-19 | 2026-07-18
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176-REP | WCS - Bronx Zoo - Reptile House Facade Restoration | 1 | CONSTRUCTION | 2013-09-29 | 2014-09-23 | 2022-06-30 | 2024-06-30
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176-REP | WCS - Bronx Zoo - Reptile House Facade Restoration | 2 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-09-24 | 2015-09-18 | 2013-09-29 | 2014-09-23
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176-REP | WCS - Bronx Zoo - Reptile House Facade Restoration | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-09-24 | 2015-09-18 | 2014-09-24 | 2015-09-18
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176WILD | WCS - Bronx Zoo - Wildlife Exhibit Center | 1 | DEVELOP SCOPE | 2022-06-30 | 2022-09-27 | 2022-06-30 | 2022-09-27
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176WILD | WCS - Bronx Zoo - Wildlife Exhibit Center | 2 | PRELIMINARY DESIGN | 2022-09-28 | 2023-01-25 | 2022-09-28 | 2023-01-25
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176WILD | WCS - Bronx Zoo - Wildlife Exhibit Center | 3 | FINAL DESIGN | 2023-01-26 | 2023-07-24 | 2023-01-26 | 2023-07-24
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176WILD | WCS - Bronx Zoo - Wildlife Exhibit Center | 4 | BID AWARD AND REGISTER CONTRCT | 2023-07-25 | 2023-10-22 | 2023-07-25 | 2023-10-22
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176WILD | WCS - Bronx Zoo - Wildlife Exhibit Center | 5 | CONSTRUCTION TO 25% | 2023-10-23 | 2024-02-19 | 2023-10-23 | 2024-02-19
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176WILD | WCS - Bronx Zoo - Wildlife Exhibit Center | 6 | CONSTRUCTION TO 50% | 2024-02-20 | 2024-06-18 | 2024-02-20 | 2024-06-18
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176WILD | WCS - Bronx Zoo - Wildlife Exhibit Center | 7 | CONSTRUCTION TO 75% | 2024-06-19 | 2024-10-16 | 2024-06-19 | 2024-10-16
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176WILD | WCS - Bronx Zoo - Wildlife Exhibit Center | 8 | ORIGINAL EQUIP & FURNISHING | 2024-10-17 | 2025-01-14 | 2024-10-17 | 2025-01-14
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176WILD | WCS - Bronx Zoo - Wildlife Exhibit Center | 9 | SUBSTANTIAL COMPLETION | 2025-01-15 | 2025-03-15 | 2025-01-15 | 2025-03-15
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176WILD | WCS - Bronx Zoo - Wildlife Exhibit Center | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-03-16 | 2025-04-14 | 2025-03-16 | 2025-04-14
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV205WOC | NYBG - Worker's Operation Center Renovation | 1 | DEVELOP SCOPE | 2019-04-01 | 2020-04-30 | 2024-06-01 | 2025-07-01
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV205WOC | NYBG - Worker's Operation Center Renovation | 2 | PRELIMINARY DESIGN | 2020-05-01 | 2020-08-28 | 2025-07-02 | 2025-10-29
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV205WOC | NYBG - Worker's Operation Center Renovation | 3 | FINAL DESIGN | 2020-08-29 | 2021-02-24 | 2025-10-30 | 2026-04-27
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV205WOC | NYBG - Worker's Operation Center Renovation | 4 | BID AWARD AND REGISTER CONTRCT | 2021-02-25 | 2021-05-25 | 2026-04-28 | 2026-07-26
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV205WOC | NYBG - Worker's Operation Center Renovation | 5 | CONSTRUCTION TO 25% | 2021-05-26 | 2021-09-22 | 2026-07-27 | 2026-11-23
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV205WOC | NYBG - Worker's Operation Center Renovation | 6 | CONSTRUCTION TO 50% | 2021-09-23 | 2022-01-20 | 2026-11-24 | 2027-03-23
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV205WOC | NYBG - Worker's Operation Center Renovation | 7 | CONSTRUCTION TO 75% | 2022-01-21 | 2022-05-20 | 2027-03-24 | 2027-07-21
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV205WOC | NYBG - Worker's Operation Center Renovation | 8 | ORIGINAL EQUIP & FURNISHING | 2022-05-21 | 2022-08-18 | 2027-07-22 | 2027-10-19
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV205WOC | NYBG - Worker's Operation Center Renovation | 9 | SUBSTANTIAL COMPLETION | 2022-08-19 | 2022-10-17 | 2027-10-20 | 2027-12-18
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV205WOC | NYBG - Worker's Operation Center Renovation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-10-18 | 2022-11-16 | 2027-12-19 | 2028-01-17
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV293-EXT | BCHS - Exterior/Interior Rehab and Tech Upgrade | 1 | CONSTRUCTION | 2023-09-28 | 2024-09-21 | 2023-06-30 | 2023-09-27
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV293-EXT | BCHS - Exterior/Interior Rehab and Tech Upgrade | 2 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-09-22 | 2025-09-16 | 2023-09-28 | 2024-09-21
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV293-EXT | BCHS - Exterior/Interior Rehab and Tech Upgrade | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-09-22 | 2025-09-16 | 2024-09-22 | 2025-09-16
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV464GLYN | WH - Wave Hill - Glyndor Hse. Boiler/Armor Hall AHU | 1 | DEVELOP SCOPE | 2016-05-31 | 2016-08-28 | 2021-06-30 | 2021-09-27
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV464GLYN | WH - Wave Hill - Glyndor Hse. Boiler/Armor Hall AHU | 2 | PRELIMINARY DESIGN | 2016-08-29 | 2016-12-26 | 2021-09-28 | 2022-01-25
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV464GLYN | WH - Wave Hill - Glyndor Hse. Boiler/Armor Hall AHU | 3 | FINAL DESIGN | 2016-12-27 | 2017-06-24 | 2022-01-26 | 2022-07-24
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV464GLYN | WH - Wave Hill - Glyndor Hse. Boiler/Armor Hall AHU | 4 | BID AWARD AND REGISTER CONTRCT | 2017-06-25 | 2017-09-22 | 2022-07-25 | 2022-10-22
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV464GLYN | WH - Wave Hill - Glyndor Hse. Boiler/Armor Hall AHU | 5 | CONSTRUCTION TO 25% | 2017-09-23 | 2018-01-20 | 2022-10-23 | 2023-02-19
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV464GLYN | WH - Wave Hill - Glyndor Hse. Boiler/Armor Hall AHU | 6 | CONSTRUCTION TO 50% | 2018-01-21 | 2018-05-20 | 2023-02-20 | 2023-06-19
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV464GLYN | WH - Wave Hill - Glyndor Hse. Boiler/Armor Hall AHU | 7 | CONSTRUCTION TO 75% | 2018-05-21 | 2018-09-17 | 2023-06-20 | 2023-10-17
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV464GLYN | WH - Wave Hill - Glyndor Hse. Boiler/Armor Hall AHU | 8 | ORIGINAL EQUIP & FURNISHING | 2018-09-18 | 2018-12-16 | 2023-10-18 | 2024-01-15
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV464GLYN | WH - Wave Hill - Glyndor Hse. Boiler/Armor Hall AHU | 9 | SUBSTANTIAL COMPLETION | 2018-12-17 | 2019-02-14 | 2024-01-16 | 2024-03-15
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV464GLYN | WH - Wave Hill - Glyndor Hse. Boiler/Armor Hall AHU | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-02-15 | 2019-03-16 | 2024-03-16 | 2024-04-14
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV464-PAV | WH - Wave Hill - Woodland Pavilion | 1 | DEVELOP SCOPE | 2022-06-30 | 2022-09-27 | 2022-06-30 | 2022-09-27
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV464-PAV | WH - Wave Hill - Woodland Pavilion | 2 | PRELIMINARY DESIGN | 2022-09-28 | 2023-01-25 | 2022-09-28 | 2023-01-25
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV464-PAV | WH - Wave Hill - Woodland Pavilion | 3 | FINAL DESIGN | 2023-01-26 | 2023-07-24 | 2023-01-26 | 2023-07-24
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV464-PAV | WH - Wave Hill - Woodland Pavilion | 4 | BID AWARD AND REGISTER CONTRCT | 2023-07-25 | 2023-10-22 | 2023-07-25 | 2023-10-22
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV464-PAV | WH - Wave Hill - Woodland Pavilion | 5 | CONSTRUCTION TO 25% | 2023-10-23 | 2024-02-19 | 2023-10-23 | 2024-02-19
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV464-PAV | WH - Wave Hill - Woodland Pavilion | 6 | CONSTRUCTION TO 50% | 2024-02-20 | 2024-06-18 | 2024-02-20 | 2024-06-18
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV464-PAV | WH - Wave Hill - Woodland Pavilion | 7 | CONSTRUCTION TO 75% | 2024-06-19 | 2024-10-16 | 2024-06-19 | 2024-10-16
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV464-PAV | WH - Wave Hill - Woodland Pavilion | 8 | ORIGINAL EQUIP & FURNISHING | 2024-10-17 | 2025-01-14 | 2024-10-17 | 2025-01-14
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV464-PAV | WH - Wave Hill - Woodland Pavilion | 9 | SUBSTANTIAL COMPLETION | 2025-01-15 | 2025-03-15 | 2025-01-15 | 2025-03-15
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV464-PAV | WH - Wave Hill - Woodland Pavilion | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-03-16 | 2025-04-14 | 2025-03-16 | 2025-04-14
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV464SITE | WH - Wave Hill - Sitewide Pathway Replacement | 1 | DEVELOP SCOPE | 2016-06-30 | 2016-09-27 | 2024-06-30 | 2024-09-27
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV464SITE | WH - Wave Hill - Sitewide Pathway Replacement | 2 | PRELIMINARY DESIGN | 2016-09-28 | 2017-01-25 | 2024-09-28 | 2025-01-25
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV464SITE | WH - Wave Hill - Sitewide Pathway Replacement | 3 | FINAL DESIGN | 2017-01-26 | 2017-07-24 | 2025-01-26 | 2025-07-24
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV464SITE | WH - Wave Hill - Sitewide Pathway Replacement | 4 | BID AWARD AND REGISTER CONTRCT | 2017-07-25 | 2017-10-22 | 2025-07-25 | 2025-10-22
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV464SITE | WH - Wave Hill - Sitewide Pathway Replacement | 5 | CONSTRUCTION TO 25% | 2017-10-23 | 2018-02-19 | 2025-10-23 | 2026-02-19
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV464SITE | WH - Wave Hill - Sitewide Pathway Replacement | 6 | CONSTRUCTION TO 50% | 2018-02-20 | 2018-06-19 | 2026-02-20 | 2026-06-19
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV464SITE | WH - Wave Hill - Sitewide Pathway Replacement | 7 | CONSTRUCTION TO 75% | 2018-06-20 | 2018-10-17 | 2026-06-20 | 2026-10-17
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV464SITE | WH - Wave Hill - Sitewide Pathway Replacement | 8 | ORIGINAL EQUIP & FURNISHING | 2018-10-18 | 2019-01-15 | 2026-10-18 | 2027-01-15
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV464SITE | WH - Wave Hill - Sitewide Pathway Replacement | 9 | SUBSTANTIAL COMPLETION | 2019-01-16 | 2019-03-16 | 2027-01-16 | 2027-03-16
20201123 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV464SITE | WH - Wave Hill - Sitewide Pathway Replacement | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-03-17 | 2019-04-15 | 2027-03-17 | 2027-04-15
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | AGDRAIN | FA - Rain Senior Center Renovation | 1 | DEVELOP SCOPE | 2000-07-01 | 2000-09-28 | 2019-07-01 | 2019-07-20
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | AGDRAIN | FA - Rain Senior Center Renovation | 2 | PRELIMINARY DESIGN | 2000-09-29 | 2001-01-26 | 2019-07-21 | 2019-08-04
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | AGDRAIN | FA - Rain Senior Center Renovation | 3 | FINAL DESIGN | 2001-01-27 | 2008-06-30 | 2019-08-05 | 2023-09-08
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | AGDRAIN | FA - Rain Senior Center Renovation | 4 | BID AWARD AND REGISTER CONTRCT | 2008-07-01 | 2008-06-30 | 2023-09-09 | 2023-09-18
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | AGDRAIN | FA - Rain Senior Center Renovation | 5 | CONSTRUCTION TO 25% | 2008-07-01 | 2008-06-30 | 2023-09-19 | 2023-10-03
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | AGDRAIN | FA - Rain Senior Center Renovation | 6 | CONSTRUCTION TO 50% | 2008-07-01 | 2008-06-30 | 2023-10-04 | 2023-10-08
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | AGDRAIN | FA - Rain Senior Center Renovation | 7 | CONSTRUCTION TO 75% | 2008-07-01 | 2008-06-30 | 2023-10-04 | 2023-10-08
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | AGDRAIN | FA - Rain Senior Center Renovation | 8 | ORIGINAL EQUIP & FURNISHING | 2008-07-01 | 2008-06-30 | 2023-10-04 | 2023-10-08
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | AGDRAIN | FA - Rain Senior Center Renovation | 9 | SUBSTANTIAL COMPLETION | 2008-07-01 | 2008-06-30 | 2023-10-04 | 2023-10-08
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | AGDRAIN | FA - Rain Senior Center Renovation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-07-01 | 2008-07-30 | 2023-10-04 | 2023-10-08
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | ALTFUELS | Hunts Point Alternative Fueling Station | 1 | DESIGN | 2015-06-30 | 2015-07-19 | 2012-10-06 | 2012-10-25
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | ALTFUELS | Hunts Point Alternative Fueling Station | 2 | BID AWARD AND REGISTER CONTRCT | 2015-07-20 | 2015-08-03 | 2012-10-26 | 2012-11-09
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | ALTFUELS | Hunts Point Alternative Fueling Station | 3 | CONSTRUCTION | 2015-08-04 | 2015-09-07 | 2012-11-10 | 2012-12-14
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | ALTFUELS | Hunts Point Alternative Fueling Station | 4 | ORIGINAL EQUIP & FURNISHING | 2015-09-08 | 2015-09-17 | 2012-12-15 | 2012-12-24
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | ALTFUELS | Hunts Point Alternative Fueling Station | 5 | SUBSTANTIAL COMPLETION | 2015-09-18 | 2015-10-02 | 2012-12-25 | 2013-01-08
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | ALTFUELS | Hunts Point Alternative Fueling Station | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-10-03 | 2015-10-07 | 2013-01-09 | 2024-06-30
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | ARTHURAVE | ARTHUR AVENUE MARKET | 1 | DESIGN | 2019-07-01 | 2019-07-20 | 2019-07-01 | 2019-07-20
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | ARTHURAVE | ARTHUR AVENUE MARKET | 2 | BID AWARD AND REGISTER CONTRCT | 2019-07-21 | 2019-08-04 | 2019-07-21 | 2019-08-04
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | ARTHURAVE | ARTHUR AVENUE MARKET | 3 | CONSTRUCTION | 2019-08-05 | 2019-09-08 | 2019-08-05 | 2019-09-08
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | ARTHURAVE | ARTHUR AVENUE MARKET | 4 | ORIGINAL EQUIP & FURNISHING | 2019-09-09 | 2019-09-18 | 2019-09-09 | 2019-09-18
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | ARTHURAVE | ARTHUR AVENUE MARKET | 5 | SUBSTANTIAL COMPLETION | 2019-09-19 | 2022-10-03 | 2019-09-19 | 2022-10-03
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | ARTHURAVE | ARTHUR AVENUE MARKET | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-10-04 | 2022-10-08 | 2022-10-04 | 2027-07-09
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | EDXHPGEN | Hunts Point Cooperative Market | 1 | DESIGN | 2016-07-01 | 2016-07-20 | 2019-07-01 | 2019-07-20
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | EDXHPGEN | Hunts Point Cooperative Market | 2 | BID AWARD AND REGISTER CONTRCT | 2016-07-21 | 2016-08-04 | 2019-07-21 | 2019-08-04
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | EDXHPGEN | Hunts Point Cooperative Market | 3 | CONSTRUCTION | 2016-08-05 | 2016-09-08 | 2019-08-05 | 2019-09-08
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | EDXHPGEN | Hunts Point Cooperative Market | 4 | ORIGINAL EQUIP & FURNISHING | 2016-09-09 | 2016-09-18 | 2019-09-09 | 2019-09-18
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | EDXHPGEN | Hunts Point Cooperative Market | 5 | SUBSTANTIAL COMPLETION | 2016-09-19 | 2016-10-03 | 2019-09-19 | 2019-10-03
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | EDXHPGEN | Hunts Point Cooperative Market | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-10-04 | 2016-10-08 | 2019-10-04 | 2029-10-08
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | FFMDRAIN | New Fulton Fish Market -- Facility Upgrades: New Drainage Sy | 1 | DESIGN | 2019-07-01 | 2019-07-20 | 2019-07-01 | 2019-07-20
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | FFMDRAIN | New Fulton Fish Market -- Facility Upgrades: New Drainage Sy | 2 | BID AWARD AND REGISTER CONTRCT | 2019-07-21 | 2019-08-04 | 2019-07-21 | 2019-08-04
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | FFMDRAIN | New Fulton Fish Market -- Facility Upgrades: New Drainage Sy | 3 | CONSTRUCTION | 2019-08-05 | 2019-09-08 | 2019-08-05 | 2019-09-08
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | FFMDRAIN | New Fulton Fish Market -- Facility Upgrades: New Drainage Sy | 4 | ORIGINAL EQUIP & FURNISHING | 2019-09-09 | 2019-09-18 | 2019-09-09 | 2019-09-18
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | FFMDRAIN | New Fulton Fish Market -- Facility Upgrades: New Drainage Sy | 5 | SUBSTANTIAL COMPLETION | 2019-09-19 | 2019-10-03 | 2019-09-19 | 2019-10-03
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | FFMDRAIN | New Fulton Fish Market -- Facility Upgrades: New Drainage Sy | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-10-04 | 2020-10-08 | 2019-10-04 | 2020-10-08
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | FREIGHTHP | Freight NYC - Hunts Point Marine Highway | 1 | DESIGN | 2018-07-01 | 2018-07-20 | 2020-03-23 | 2020-04-11
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | FREIGHTHP | Freight NYC - Hunts Point Marine Highway | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-21 | 2018-08-04 | 2020-04-12 | 2020-04-26
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | FREIGHTHP | Freight NYC - Hunts Point Marine Highway | 3 | CONSTRUCTION | 2018-08-05 | 2018-09-08 | 2020-04-27 | 2020-05-31
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | FREIGHTHP | Freight NYC - Hunts Point Marine Highway | 4 | ORIGINAL EQUIP & FURNISHING | 2018-09-09 | 2018-09-18 | 2020-06-01 | 2020-06-10
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | FREIGHTHP | Freight NYC - Hunts Point Marine Highway | 5 | SUBSTANTIAL COMPLETION | 2018-09-19 | 2018-10-03 | 2020-06-11 | 2020-06-25
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | FREIGHTHP | Freight NYC - Hunts Point Marine Highway | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-10-04 | 2018-10-08 | 2024-06-26 | 2027-06-30
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | GXHP07-02 | GI - DSGN & CONS OF ROW BIOSWALES & GREENSTREETS IN HP-007 | 1 | DESIGN | 2015-02-01 | 2017-06-15 | 2015-02-01 | 2017-06-15
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | GXHP07-02 | GI - DSGN & CONS OF ROW BIOSWALES & GREENSTREETS IN HP-007 | 2 | BID AWARD AND REGISTER CONTRCT | 2017-06-16 | 2017-06-15 | 2017-06-16 | 2017-06-15
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | GXHP07-02 | GI - DSGN & CONS OF ROW BIOSWALES & GREENSTREETS IN HP-007 | 3 | CONSTRUCTION | 2017-06-16 | 2017-12-15 | 2017-06-16 | 2017-12-15
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | GXHP07-02 | GI - DSGN & CONS OF ROW BIOSWALES & GREENSTREETS IN HP-007 | 4 | ORIGINAL EQUIP & FURNISHING | 2017-12-16 | 2017-12-15 | 2017-12-16 | 2017-12-15
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | GXHP07-02 | GI - DSGN & CONS OF ROW BIOSWALES & GREENSTREETS IN HP-007 | 5 | SUBSTANTIAL COMPLETION | 2017-12-16 | 2017-12-15 | 2017-12-16 | 2017-12-15
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | GXHP07-02 | GI - DSGN & CONS OF ROW BIOSWALES & GREENSTREETS IN HP-007 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-12-16 | 2019-06-30 | 2017-12-16 | 2024-06-30
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | GXHP14-01 | GI - Green infrastructure in Westchester Creek HP-14 | 1 | DESIGN | 2014-06-02 | 2014-06-21 | 2014-06-02 | 2014-06-21
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | GXHP14-01 | GI - Green infrastructure in Westchester Creek HP-14 | 2 | BID AWARD AND REGISTER CONTRCT | 2014-06-22 | 2014-07-06 | 2014-06-22 | 2014-07-06
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | GXHP14-01 | GI - Green infrastructure in Westchester Creek HP-14 | 3 | CONSTRUCTION | 2014-07-07 | 2014-08-10 | 2014-07-07 | 2019-06-30
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | GXHP14-01 | GI - Green infrastructure in Westchester Creek HP-14 | 4 | ORIGINAL EQUIP & FURNISHING | 2014-08-11 | 2014-08-20 | 2019-07-01 | 2019-06-30
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | GXHP14-01 | GI - Green infrastructure in Westchester Creek HP-14 | 5 | SUBSTANTIAL COMPLETION | 2014-08-21 | 2014-09-04 | 2019-07-01 | 2019-06-30
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | GXHP14-01 | GI - Green infrastructure in Westchester Creek HP-14 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-09-05 | 2014-09-09 | 2019-07-01 | 2022-04-25
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | GXHP16-01 | GI - Green infrastructure in Westchester Creek HP-12/HP-16 | 1 | DESIGN | 2017-07-24 | 2017-08-12 | 2016-08-07 | 2017-08-26
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | GXHP16-01 | GI - Green infrastructure in Westchester Creek HP-12/HP-16 | 2 | BID AWARD AND REGISTER CONTRCT | 2017-08-13 | 2017-08-27 | 2017-08-27 | 2017-08-26
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | GXHP16-01 | GI - Green infrastructure in Westchester Creek HP-12/HP-16 | 3 | CONSTRUCTION | 2017-08-28 | 2017-10-01 | 2015-09-15 | 2017-09-15
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | GXHP16-01 | GI - Green infrastructure in Westchester Creek HP-12/HP-16 | 4 | ORIGINAL EQUIP & FURNISHING | 2017-10-02 | 2017-10-11 | 2017-09-16 | 2017-09-15
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | GXHP16-01 | GI - Green infrastructure in Westchester Creek HP-12/HP-16 | 5 | SUBSTANTIAL COMPLETION | 2017-10-12 | 2017-10-26 | 2017-09-16 | 2017-09-15
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | GXHP16-01 | GI - Green infrastructure in Westchester Creek HP-12/HP-16 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-10-27 | 2017-10-31 | 2017-09-16 | 2020-09-20
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HPBOILER | HUNTS POINT MEAT MARKET (EDC)--BOILER UPDATES | 1 | DESIGN | 2017-07-01 | 2017-07-20 | 2019-03-23 | 2019-04-11
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HPBOILER | HUNTS POINT MEAT MARKET (EDC)--BOILER UPDATES | 2 | BID AWARD AND REGISTER CONTRCT | 2017-07-21 | 2017-08-04 | 2019-04-12 | 2019-04-26
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HPBOILER | HUNTS POINT MEAT MARKET (EDC)--BOILER UPDATES | 3 | CONSTRUCTION | 2017-08-05 | 2017-09-08 | 2019-04-27 | 2019-05-31
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HPBOILER | HUNTS POINT MEAT MARKET (EDC)--BOILER UPDATES | 4 | ORIGINAL EQUIP & FURNISHING | 2017-09-09 | 2017-09-18 | 2019-06-01 | 2019-06-10
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HPBOILER | HUNTS POINT MEAT MARKET (EDC)--BOILER UPDATES | 5 | SUBSTANTIAL COMPLETION | 2017-09-19 | 2017-10-03 | 2019-06-11 | 2019-06-25
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HPBOILER | HUNTS POINT MEAT MARKET (EDC)--BOILER UPDATES | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-10-04 | 2017-10-08 | 2019-06-26 | 2026-06-30
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HPCMFRIDG | Hunts Point Cooperative Market (Efficient Refrigeration Comp | 1 | DESIGN | 2019-07-01 | 2019-07-20 | 2019-07-01 | 2019-07-20
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HPCMFRIDG | Hunts Point Cooperative Market (Efficient Refrigeration Comp | 2 | BID AWARD AND REGISTER CONTRCT | 2019-07-21 | 2019-08-04 | 2019-07-21 | 2019-08-04
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HPCMFRIDG | Hunts Point Cooperative Market (Efficient Refrigeration Comp | 3 | CONSTRUCTION | 2019-08-05 | 2019-09-08 | 2019-08-05 | 2019-09-08
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HPCMFRIDG | Hunts Point Cooperative Market (Efficient Refrigeration Comp | 4 | ORIGINAL EQUIP & FURNISHING | 2019-09-09 | 2019-09-18 | 2019-09-09 | 2019-09-18
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HPCMFRIDG | Hunts Point Cooperative Market (Efficient Refrigeration Comp | 5 | SUBSTANTIAL COMPLETION | 2019-09-19 | 2020-10-03 | 2019-09-19 | 2020-10-03
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HPCMFRIDG | Hunts Point Cooperative Market (Efficient Refrigeration Comp | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-10-04 | 2020-10-08 | 2020-10-04 | 2029-10-08
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HPMRKRAIL | Hunts Point Produce Market Raill Imp. | 1 | DESIGN | 2016-01-01 | 2018-06-30 | 2016-01-01 | 2018-06-30
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HPMRKRAIL | Hunts Point Produce Market Raill Imp. | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-01 | 2018-06-30 | 2018-07-01 | 2018-06-30
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HPMRKRAIL | Hunts Point Produce Market Raill Imp. | 3 | CONSTRUCTION | 2018-07-01 | 2021-06-30 | 2018-07-01 | 2021-06-30
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HPMRKRAIL | Hunts Point Produce Market Raill Imp. | 4 | ORIGINAL EQUIP & FURNISHING | 2021-07-01 | 2021-06-30 | 2021-07-01 | 2021-06-30
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HPMRKRAIL | Hunts Point Produce Market Raill Imp. | 5 | SUBSTANTIAL COMPLETION | 2021-07-01 | 2021-06-30 | 2021-07-01 | 2021-06-30
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HPMRKRAIL | Hunts Point Produce Market Raill Imp. | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-07-01 | 2021-07-05 | 2021-07-01 | 2021-07-05
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HPRAILSBG | HUNTS POINT RAIL SPUR | 1 | DESIGN | 2008-09-30 | 2010-10-19 | 2015-06-30 | 2017-07-18
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HPRAILSBG | HUNTS POINT RAIL SPUR | 2 | BID AWARD AND REGISTER CONTRCT | 2010-10-20 | 2010-10-19 | 2017-07-19 | 2017-07-18
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HPRAILSBG | HUNTS POINT RAIL SPUR | 3 | CONSTRUCTION | 2010-10-20 | 2012-10-19 | 2017-07-19 | 2019-07-19
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HPRAILSBG | HUNTS POINT RAIL SPUR | 4 | ORIGINAL EQUIP & FURNISHING | 2012-10-20 | 2012-10-19 | 2019-07-20 | 2019-07-19
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HPRAILSBG | HUNTS POINT RAIL SPUR | 5 | SUBSTANTIAL COMPLETION | 2012-10-20 | 2012-10-19 | 2019-07-20 | 2019-07-19
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HPRAILSBG | HUNTS POINT RAIL SPUR | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-10-20 | 2012-10-24 | 2019-07-20 | 2023-07-24
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HTPRODUC2 | Hunts Point Market | 1 | DESIGN | 2011-01-01 | 2011-06-01 | 2015-01-01 | 2015-06-01
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HTPRODUC2 | Hunts Point Market | 2 | BID AWARD AND REGISTER CONTRCT | 2011-06-02 | 2011-06-01 | 2015-06-02 | 2015-06-01
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HTPRODUC2 | Hunts Point Market | 3 | CONSTRUCTION | 2011-06-02 | 2012-06-01 | 2015-06-02 | 2017-06-01
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HTPRODUC2 | Hunts Point Market | 4 | ORIGINAL EQUIP & FURNISHING | 2012-06-02 | 2012-06-01 | 2017-06-02 | 2017-06-01
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HTPRODUC2 | Hunts Point Market | 5 | SUBSTANTIAL COMPLETION | 2012-06-02 | 2012-06-01 | 2017-06-02 | 2017-06-01
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HTPRODUC2 | Hunts Point Market | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-06-02 | 2012-06-06 | 2017-06-02 | 2025-06-30
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HUNTMEAT2 | Hunts Point Meat Market 2 | 1 | DESIGN | 2016-01-01 | 2018-06-30 | 2016-01-01 | 2018-06-30
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HUNTMEAT2 | Hunts Point Meat Market 2 | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-01 | 2018-06-30 | 2018-07-01 | 2018-06-30
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HUNTMEAT2 | Hunts Point Meat Market 2 | 3 | CONSTRUCTION | 2018-07-01 | 2021-06-30 | 2018-07-01 | 2021-06-30
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HUNTMEAT2 | Hunts Point Meat Market 2 | 4 | ORIGINAL EQUIP & FURNISHING | 2021-07-01 | 2021-06-30 | 2021-07-01 | 2021-06-30
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HUNTMEAT2 | Hunts Point Meat Market 2 | 5 | SUBSTANTIAL COMPLETION | 2021-07-01 | 2021-06-30 | 2021-07-01 | 2021-06-30
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HUNTMEAT2 | Hunts Point Meat Market 2 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-07-01 | 2021-07-05 | 2021-07-01 | 2021-07-05
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HUNTSAOU2 | Hunts Point AOU-2 and Building G Development | 1 | DESIGN | 2017-07-01 | 2017-07-20 | 2019-03-23 | 2019-04-11
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HUNTSAOU2 | Hunts Point AOU-2 and Building G Development | 2 | BID AWARD AND REGISTER CONTRCT | 2017-07-21 | 2017-08-04 | 2019-04-12 | 2019-04-26
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HUNTSAOU2 | Hunts Point AOU-2 and Building G Development | 3 | CONSTRUCTION | 2017-08-05 | 2017-09-08 | 2019-04-27 | 2019-05-31
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HUNTSAOU2 | Hunts Point AOU-2 and Building G Development | 4 | ORIGINAL EQUIP & FURNISHING | 2017-09-09 | 2017-09-18 | 2019-06-01 | 2019-06-10
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HUNTSAOU2 | Hunts Point AOU-2 and Building G Development | 5 | SUBSTANTIAL COMPLETION | 2017-09-19 | 2017-10-03 | 2019-06-11 | 2019-06-25
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HUNTSAOU2 | Hunts Point AOU-2 and Building G Development | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-10-04 | 2017-10-08 | 2019-06-26 | 2024-06-30
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HUNTSFISH | Hunts Point Fish Market | 1 | DESIGN | 2016-01-01 | 2018-06-30 | 2016-01-01 | 2018-06-30
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HUNTSFISH | Hunts Point Fish Market | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-01 | 2018-06-30 | 2018-07-01 | 2018-06-30
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HUNTSFISH | Hunts Point Fish Market | 3 | CONSTRUCTION | 2018-07-01 | 2021-06-30 | 2018-07-01 | 2021-06-30
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HUNTSFISH | Hunts Point Fish Market | 4 | ORIGINAL EQUIP & FURNISHING | 2021-07-01 | 2021-06-30 | 2021-07-01 | 2021-06-30
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HUNTSFISH | Hunts Point Fish Market | 5 | SUBSTANTIAL COMPLETION | 2021-07-01 | 2021-06-30 | 2021-07-01 | 2021-06-30
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HUNTSFISH | Hunts Point Fish Market | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-07-01 | 2021-07-05 | 2021-07-01 | 2021-07-05
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HUNTSPROD | Hunts Point Produce Market | 1 | DESIGN | 2016-01-01 | 2018-06-30 | 2016-01-01 | 2018-06-30
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HUNTSPROD | Hunts Point Produce Market | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-01 | 2018-06-30 | 2018-07-01 | 2018-06-30
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HUNTSPROD | Hunts Point Produce Market | 3 | CONSTRUCTION | 2018-07-01 | 2021-06-30 | 2018-07-01 | 2024-06-30
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HUNTSPROD | Hunts Point Produce Market | 4 | ORIGINAL EQUIP & FURNISHING | 2021-07-01 | 2021-06-30 | 2024-07-01 | 2024-06-30
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HUNTSPROD | Hunts Point Produce Market | 5 | SUBSTANTIAL COMPLETION | 2021-07-01 | 2021-06-30 | 2024-07-01 | 2024-06-30
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HUNTSPROD | Hunts Point Produce Market | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-07-01 | 2021-07-05 | 2024-07-01 | 2024-07-05
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HUNTSPTR2 | Hunts Point Area Wide Improvements | 1 | DESIGN | 2017-07-01 | 2017-07-20 | 2017-07-01 | 2017-07-20
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HUNTSPTR2 | Hunts Point Area Wide Improvements | 2 | BID AWARD AND REGISTER CONTRCT | 2017-07-21 | 2017-08-04 | 2017-07-21 | 2017-08-04
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HUNTSPTR2 | Hunts Point Area Wide Improvements | 3 | CONSTRUCTION | 2017-08-05 | 2017-09-08 | 2017-08-05 | 2017-09-08
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HUNTSPTR2 | Hunts Point Area Wide Improvements | 4 | ORIGINAL EQUIP & FURNISHING | 2017-09-09 | 2017-09-18 | 2017-09-09 | 2017-09-18
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HUNTSPTR2 | Hunts Point Area Wide Improvements | 5 | SUBSTANTIAL COMPLETION | 2017-09-19 | 2020-06-30 | 2017-09-19 | 2020-06-30
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HUNTSPTR2 | Hunts Point Area Wide Improvements | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-07-01 | 2020-07-05 | 2020-07-01 | 2028-06-30
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HUNTSPTRR | Hunts Point Infrastructure Improvements | 1 | DESIGN | 2016-01-01 | 2018-06-30 | 2016-01-01 | 2018-06-30
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HUNTSPTRR | Hunts Point Infrastructure Improvements | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-01 | 2018-06-30 | 2018-07-01 | 2018-06-30
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HUNTSPTRR | Hunts Point Infrastructure Improvements | 3 | CONSTRUCTION | 2018-07-01 | 2021-06-30 | 2018-07-01 | 2021-06-30
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HUNTSPTRR | Hunts Point Infrastructure Improvements | 4 | ORIGINAL EQUIP & FURNISHING | 2021-07-01 | 2021-06-30 | 2021-07-01 | 2021-06-30
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HUNTSPTRR | Hunts Point Infrastructure Improvements | 5 | SUBSTANTIAL COMPLETION | 2021-07-01 | 2021-06-30 | 2021-07-01 | 2021-06-30
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HUNTSPTRR | Hunts Point Infrastructure Improvements | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-07-01 | 2021-07-05 | 2021-07-01 | 2021-07-05
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HWXP2010 | Hunts Point Signage and Streetscape Project | 1 | DEVELOP SCOPE | 2004-05-21 | 2004-08-18 | 2013-05-22 | 2020-08-19
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HWXP2010 | Hunts Point Signage and Streetscape Project | 2 | PRELIMINARY DESIGN | 2004-08-19 | 2004-12-16 | 2020-08-20 | 2020-12-17
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HWXP2010 | Hunts Point Signage and Streetscape Project | 3 | FINAL DESIGN | 2004-12-17 | 2007-06-30 | 2003-09-01 | 2003-09-01
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HWXP2010 | Hunts Point Signage and Streetscape Project | 4 | BID AWARD AND REGISTER CONTRCT | 2007-07-01 | 2007-06-30 | 2003-09-02 | 2017-06-30
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HWXP2010 | Hunts Point Signage and Streetscape Project | 5 | CONSTRUCTION TO 25% | 2007-07-01 | 2007-06-30 | 2017-07-01 | 2017-06-30
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HWXP2010 | Hunts Point Signage and Streetscape Project | 6 | CONSTRUCTION TO 50% | 2007-07-01 | 2007-06-30 | 2017-07-01 | 2017-06-30
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HWXP2010 | Hunts Point Signage and Streetscape Project | 7 | CONSTRUCTION TO 75% | 2007-07-01 | 2007-06-30 | 2017-07-01 | 2017-06-30
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HWXP2010 | Hunts Point Signage and Streetscape Project | 8 | ORIGINAL EQUIP & FURNISHING | 2007-07-01 | 2007-06-30 | 2017-07-01 | 2017-06-30
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HWXP2010 | Hunts Point Signage and Streetscape Project | 9 | SUBSTANTIAL COMPLETION | 2007-07-01 | 2007-06-30 | 2007-03-01 | 2011-06-20
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HWXP2010 | Hunts Point Signage and Streetscape Project | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2007-07-01 | 2007-07-30 | 2011-06-21 | 2022-06-25
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | LAFFAVELT | Laffayette Avenue Street Lighting | 1 | DESIGN | 2019-07-01 | 2019-07-20 | 2019-07-01 | 2019-07-20
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | LAFFAVELT | Laffayette Avenue Street Lighting | 2 | BID AWARD AND REGISTER CONTRCT | 2019-07-21 | 2019-08-04 | 2019-07-21 | 2019-08-04
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | LAFFAVELT | Laffayette Avenue Street Lighting | 3 | CONSTRUCTION | 2019-08-05 | 2019-09-08 | 2019-08-05 | 2019-09-08
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | LAFFAVELT | Laffayette Avenue Street Lighting | 4 | ORIGINAL EQUIP & FURNISHING | 2019-09-09 | 2019-09-18 | 2019-09-09 | 2019-09-18
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | LAFFAVELT | Laffayette Avenue Street Lighting | 5 | SUBSTANTIAL COMPLETION | 2019-09-19 | 2019-10-03 | 2019-09-19 | 2019-10-03
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | LAFFAVELT | Laffayette Avenue Street Lighting | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-10-04 | 2020-10-08 | 2019-10-04 | 2024-10-08
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | LNEA16HPT | HUNTS POINT: MAJOR RENOVATION | 1 | DESIGN | 2016-08-01 | 2017-01-27 | 2016-08-01 | 2017-01-27
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | LNEA16HPT | HUNTS POINT: MAJOR RENOVATION | 2 | BID AWARD AND REGISTER CONTRCT | 2017-01-28 | 2017-04-27 | 2017-01-28 | 2017-04-27
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | LNEA16HPT | HUNTS POINT: MAJOR RENOVATION | 3 | CONSTRUCTION | 2017-04-28 | 2018-04-27 | 2017-04-28 | 2020-04-27
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | LNEA16HPT | HUNTS POINT: MAJOR RENOVATION | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-04-28 | 2019-02-21 | 2020-04-28 | 2022-02-21
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | LNEA16MLR | Melrose: Major Renovation | 1 | DESIGN | 2016-08-01 | 2017-01-27 | 2016-08-01 | 2017-01-27
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | LNEA16MLR | Melrose: Major Renovation | 2 | BID AWARD AND REGISTER CONTRCT | 2017-01-28 | 2017-04-27 | 2017-01-28 | 2017-04-27
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | LNEA16MLR | Melrose: Major Renovation | 3 | CONSTRUCTION | 2017-04-28 | 2018-04-27 | 2017-04-28 | 2020-04-27
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | LNEA16MLR | Melrose: Major Renovation | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-04-28 | 2019-02-21 | 2020-04-28 | 2022-02-21
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-JEROM | Jerome Avenue Safety Improvements NDF Funding | 1 | DESIGN | 2019-07-01 | 2019-07-20 | 2019-07-01 | 2019-07-20
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-JEROM | Jerome Avenue Safety Improvements NDF Funding | 2 | BID AWARD AND REGISTER CONTRCT | 2019-07-21 | 2019-08-04 | 2019-07-21 | 2019-08-04
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-JEROM | Jerome Avenue Safety Improvements NDF Funding | 3 | CONSTRUCTION | 2019-08-05 | 2019-09-08 | 2019-08-05 | 2019-09-08
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-JEROM | Jerome Avenue Safety Improvements NDF Funding | 4 | ORIGINAL EQUIP & FURNISHING | 2019-09-09 | 2019-09-18 | 2019-09-09 | 2019-09-18
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-JEROM | Jerome Avenue Safety Improvements NDF Funding | 5 | SUBSTANTIAL COMPLETION | 2019-09-19 | 2019-10-03 | 2019-09-19 | 2019-10-03
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-JEROM | Jerome Avenue Safety Improvements NDF Funding | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-10-04 | 2023-10-08 | 2019-10-04 | 2028-10-08
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-SCH4D | School Safety 4D NDF Funding | 1 | DESIGN | 2019-07-01 | 2019-07-20 | 2019-07-01 | 2019-07-20
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-SCH4D | School Safety 4D NDF Funding | 2 | BID AWARD AND REGISTER CONTRCT | 2019-07-21 | 2019-08-04 | 2019-07-21 | 2019-08-04
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-SCH4D | School Safety 4D NDF Funding | 3 | CONSTRUCTION | 2019-08-05 | 2019-09-08 | 2019-08-05 | 2019-09-08
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-SCH4D | School Safety 4D NDF Funding | 4 | ORIGINAL EQUIP & FURNISHING | 2019-09-09 | 2019-09-18 | 2019-09-09 | 2019-09-18
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-SCH4D | School Safety 4D NDF Funding | 5 | SUBSTANTIAL COMPLETION | 2019-09-19 | 2019-10-03 | 2019-09-19 | 2019-10-03
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-SCH4D | School Safety 4D NDF Funding | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-10-04 | 2021-10-08 | 2019-10-04 | 2025-10-08
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | NFFMSTORG | NEW FULTON FISH MARKET RENOVATION-- REFRIGERATED STORAGE ARE | 1 | DESIGN | 2019-07-01 | 2019-07-20 | 2019-07-01 | 2019-07-20
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | NFFMSTORG | NEW FULTON FISH MARKET RENOVATION-- REFRIGERATED STORAGE ARE | 2 | BID AWARD AND REGISTER CONTRCT | 2019-07-21 | 2019-08-04 | 2019-07-21 | 2019-08-04
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | NFFMSTORG | NEW FULTON FISH MARKET RENOVATION-- REFRIGERATED STORAGE ARE | 3 | CONSTRUCTION | 2019-08-05 | 2019-09-08 | 2019-08-05 | 2019-09-08
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | NFFMSTORG | NEW FULTON FISH MARKET RENOVATION-- REFRIGERATED STORAGE ARE | 4 | ORIGINAL EQUIP & FURNISHING | 2019-09-09 | 2019-09-18 | 2019-09-09 | 2019-09-18
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | NFFMSTORG | NEW FULTON FISH MARKET RENOVATION-- REFRIGERATED STORAGE ARE | 5 | SUBSTANTIAL COMPLETION | 2019-09-19 | 2020-10-03 | 2019-09-19 | 2020-10-03
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | NFFMSTORG | NEW FULTON FISH MARKET RENOVATION-- REFRIGERATED STORAGE ARE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-10-04 | 2020-10-08 | 2020-10-04 | 2024-10-08
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | P-1ORCHPA | Orchard Beach Pavillion & Ancillary Reconstruction | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | P-1ORCHPA | Orchard Beach Pavillion & Ancillary Reconstruction | 2 | DESIGN | 2016-12-28 | 2018-12-27 | 2016-12-28 | 2018-12-27
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | P-1ORCHPA | Orchard Beach Pavillion & Ancillary Reconstruction | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | P-1ORCHPA | Orchard Beach Pavillion & Ancillary Reconstruction | 4 | CONSTRUCTION | 2019-09-24 | 2021-09-22 | 2019-09-24 | 2021-09-22
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | P-1ORCHPA | Orchard Beach Pavillion & Ancillary Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | P-6NEWYN2 | New Yankee Stadium - Associated Soft Costs | 1 | DESIGN | 2004-04-01 | 2004-04-20 | 2005-04-01 | 2005-04-20
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | P-6NEWYN2 | New Yankee Stadium - Associated Soft Costs | 2 | BID AWARD AND REGISTER CONTRCT | 2004-04-21 | 2004-05-05 | 2006-07-01 | 2006-06-30
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | P-6NEWYN2 | New Yankee Stadium - Associated Soft Costs | 3 | CONSTRUCTION | 2004-05-06 | 2008-06-30 | 2006-07-01 | 2008-06-30
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | P-6NEWYN2 | New Yankee Stadium - Associated Soft Costs | 4 | ORIGINAL EQUIP & FURNISHING | 2008-07-01 | 2008-06-30 | 2008-07-01 | 2008-06-30
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | P-6NEWYN2 | New Yankee Stadium - Associated Soft Costs | 5 | SUBSTANTIAL COMPLETION | 2008-07-01 | 2008-06-30 | 2008-07-01 | 2008-06-30
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | P-6NEWYN2 | New Yankee Stadium - Associated Soft Costs | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-07-01 | 2008-07-05 | 2008-07-01 | 2020-06-30
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | PV471SWA2 | BxMA - South Wing Atrium Renovation | 1 | DESIGN | 2021-06-01 | 2021-06-20 | 2021-06-01 | 2021-06-20
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | PV471SWA2 | BxMA - South Wing Atrium Renovation | 2 | BID AWARD AND REGISTER CONTRCT | 2021-06-21 | 2021-07-05 | 2021-06-21 | 2021-07-05
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | PV471SWA2 | BxMA - South Wing Atrium Renovation | 3 | CONSTRUCTION | 2021-07-06 | 2021-08-09 | 2021-07-06 | 2021-08-09
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | PV471SWA2 | BxMA - South Wing Atrium Renovation | 4 | ORIGINAL EQUIP & FURNISHING | 2021-08-10 | 2021-08-19 | 2021-08-10 | 2021-08-19
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | PV471SWA2 | BxMA - South Wing Atrium Renovation | 5 | SUBSTANTIAL COMPLETION | 2021-08-20 | 2021-09-03 | 2021-08-20 | 2021-09-03
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | PV471SWA2 | BxMA - South Wing Atrium Renovation | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-04 | 2023-09-08 | 2021-09-04 | 2023-09-08
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | RICONNECT | Randall's Island Connector | 1 | DESIGN | 2008-01-01 | 2009-01-01 | 2017-01-01 | 2017-01-20
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | RICONNECT | Randall's Island Connector | 2 | BID AWARD AND REGISTER CONTRCT | 2009-01-02 | 2009-01-01 | 2017-01-21 | 2017-02-04
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | RICONNECT | Randall's Island Connector | 3 | CONSTRUCTION | 2009-01-02 | 2011-01-01 | 2017-02-05 | 2020-06-30
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | RICONNECT | Randall's Island Connector | 4 | ORIGINAL EQUIP & FURNISHING | 2011-01-02 | 2011-01-01 | 2020-07-01 | 2020-06-30
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | RICONNECT | Randall's Island Connector | 5 | SUBSTANTIAL COMPLETION | 2011-01-02 | 2011-01-01 | 2020-07-01 | 2020-06-30
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | RICONNECT | Randall's Island Connector | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2011-01-02 | 2011-01-06 | 2020-07-01 | 2029-06-30
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDHPRXD | Hunts Point Energy Resiliency Pilot - DR | 1 | DESIGN | 2016-07-01 | 2016-07-20 | 2016-07-01 | 2016-07-20
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDHPRXD | Hunts Point Energy Resiliency Pilot - DR | 2 | BID AWARD AND REGISTER CONTRCT | 2016-07-21 | 2016-08-04 | 2016-07-21 | 2016-08-04
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDHPRXD | Hunts Point Energy Resiliency Pilot - DR | 3 | CONSTRUCTION | 2016-08-05 | 2016-09-08 | 2016-08-05 | 2016-09-08
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDHPRXD | Hunts Point Energy Resiliency Pilot - DR | 4 | ORIGINAL EQUIP & FURNISHING | 2016-09-09 | 2016-09-18 | 2016-09-09 | 2016-09-18
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDHPRXD | Hunts Point Energy Resiliency Pilot - DR | 5 | SUBSTANTIAL COMPLETION | 2016-09-19 | 2016-10-03 | 2016-09-19 | 2016-10-03
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDHPRXD | Hunts Point Energy Resiliency Pilot - DR | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-10-04 | 2016-10-08 | 2016-10-04 | 2024-10-08
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | STHBRXGRN | South Bronx Greenway | 1 | DESIGN | 2006-08-01 | 2006-08-20 | 2011-06-01 | 2021-06-30
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | STHBRXGRN | South Bronx Greenway | 2 | BID AWARD AND REGISTER CONTRCT | 2006-08-21 | 2006-09-04 | 2011-04-01 | 2011-07-01
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | STHBRXGRN | South Bronx Greenway | 3 | CONSTRUCTION | 2006-09-05 | 2006-10-09 | 2009-05-21 | 2020-06-30
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | STHBRXGRN | South Bronx Greenway | 4 | ORIGINAL EQUIP & FURNISHING | 2006-10-10 | 2006-10-19 | 2020-07-01 | 2020-06-30
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | STHBRXGRN | South Bronx Greenway | 5 | SUBSTANTIAL COMPLETION | 2006-10-20 | 2006-11-03 | 2020-07-01 | 2020-06-30
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | STHBRXGRN | South Bronx Greenway | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2006-11-04 | 2006-11-08 | 2020-07-01 | 2020-07-05
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | SWBXINFRA | Southwest Bronx Infrastructure Improvements | 1 | DESIGN | 2016-01-01 | 2016-01-20 | 2016-01-01 | 2016-01-20
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | SWBXINFRA | Southwest Bronx Infrastructure Improvements | 2 | BID AWARD AND REGISTER CONTRCT | 2016-01-21 | 2016-06-30 | 2016-01-21 | 2016-06-30
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | SWBXINFRA | Southwest Bronx Infrastructure Improvements | 3 | CONSTRUCTION | 2016-07-01 | 2017-06-30 | 2016-07-01 | 2017-06-30
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | SWBXINFRA | Southwest Bronx Infrastructure Improvements | 4 | ORIGINAL EQUIP & FURNISHING | 2017-07-01 | 2020-06-30 | 2017-07-01 | 2020-06-30
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | SWBXINFRA | Southwest Bronx Infrastructure Improvements | 5 | SUBSTANTIAL COMPLETION | 2020-07-01 | 2020-06-30 | 2020-07-01 | 2020-06-30
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | SWBXINFRA | Southwest Bronx Infrastructure Improvements | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-07-01 | 2020-07-05 | 2020-07-01 | 2023-07-05
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | SWBXLCN | Lower Concourse North | 1 | DESIGN | 2021-01-01 | 2021-01-20 | 2019-12-01 | 2021-01-20
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | SWBXLCN | Lower Concourse North | 2 | BID AWARD AND REGISTER CONTRCT | 2021-01-21 | 2021-02-04 | 2021-01-21 | 2021-02-04
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | SWBXLCN | Lower Concourse North | 3 | CONSTRUCTION | 2021-02-05 | 2021-03-11 | 2021-02-05 | 2021-03-11
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | SWBXLCN | Lower Concourse North | 4 | ORIGINAL EQUIP & FURNISHING | 2021-03-12 | 2021-03-21 | 2021-03-12 | 2021-03-21
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | SWBXLCN | Lower Concourse North | 5 | SUBSTANTIAL COMPLETION | 2021-03-22 | 2021-04-05 | 2021-03-22 | 2021-04-05
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | SWBXLCN | Lower Concourse North | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-04-06 | 2021-04-10 | 2021-04-06 | 2024-04-10
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | VINCEAVE | Vincent Avenue Seawall Rehabilitation | 1 | DESIGN | 2017-07-01 | 2017-07-20 | 2019-03-23 | 2019-04-11
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | VINCEAVE | Vincent Avenue Seawall Rehabilitation | 2 | BID AWARD AND REGISTER CONTRCT | 2017-07-21 | 2017-08-04 | 2019-04-12 | 2019-04-26
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | VINCEAVE | Vincent Avenue Seawall Rehabilitation | 3 | CONSTRUCTION | 2017-08-05 | 2017-09-08 | 2019-04-27 | 2019-05-31
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | VINCEAVE | Vincent Avenue Seawall Rehabilitation | 4 | ORIGINAL EQUIP & FURNISHING | 2017-09-09 | 2017-09-18 | 2019-06-01 | 2019-06-10
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | VINCEAVE | Vincent Avenue Seawall Rehabilitation | 5 | SUBSTANTIAL COMPLETION | 2017-09-19 | 2017-10-03 | 2019-06-11 | 2019-06-25
20201123 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | VINCEAVE | Vincent Avenue Seawall Rehabilitation | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-10-04 | 2017-10-08 | 2019-06-26 | 2025-06-30
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM06MPLE | MIDDLETON PLAZA SENIOR HOUSING LIGHTING AND ELECTRICAL | 1 | DESIGN | 2006-10-01 | 2007-03-29 | 2006-10-01 | 2007-03-29
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM06MPLE | MIDDLETON PLAZA SENIOR HOUSING LIGHTING AND ELECTRICAL | 2 | BID AWARD AND REGISTER CONTRCT | 2007-03-30 | 2007-08-21 | 2007-03-30 | 2007-08-21
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM06MPLE | MIDDLETON PLAZA SENIOR HOUSING LIGHTING AND ELECTRICAL | 3 | CONSTRUCTION | 2007-08-22 | 2008-08-20 | 2007-08-22 | 2011-12-31
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM06MPLE | MIDDLETON PLAZA SENIOR HOUSING LIGHTING AND ELECTRICAL | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-08-21 | 2009-02-16 | 2007-08-22 | 2011-12-31
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM06MPLE | MIDDLETON PLAZA SENIOR HOUSING LIGHTING AND ELECTRICAL | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-08-21 | 2009-02-16 | 2012-01-01 | 2012-06-28
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM06TNIN | THROGGS NECK HOUSES LIGHTING | 3 | CONSTRUCTION | 2006-11-22 | 2007-11-21 | 2019-02-16 | 2020-02-16
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM06TNIN | THROGGS NECK HOUSES LIGHTING | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2007-11-22 | 2008-05-19 | 2019-02-16 | 2020-02-16
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM06TNIN | THROGGS NECK HOUSES LIGHTING | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2007-11-22 | 2008-05-19 | 2020-02-17 | 2021-03-28
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM07PPCR | PELHAM PARKWAY HOUSES - COMMUNITY ROOM UPGRADE | 1 | DESIGN | 2007-01-01 | 2007-06-29 | 2011-02-01 | 2011-07-30
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM07PPCR | PELHAM PARKWAY HOUSES - COMMUNITY ROOM UPGRADE | 2 | BID AWARD AND REGISTER CONTRCT | 2007-06-30 | 2007-11-21 | 2011-07-31 | 2011-12-22
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM07PPCR | PELHAM PARKWAY HOUSES - COMMUNITY ROOM UPGRADE | 3 | CONSTRUCTION | 2007-11-22 | 2008-11-20 | 2011-12-23 | 2012-12-21
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM07PPCR | PELHAM PARKWAY HOUSES - COMMUNITY ROOM UPGRADE | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-11-21 | 2009-05-19 | 2011-12-23 | 2012-12-21
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM07PPCR | PELHAM PARKWAY HOUSES - COMMUNITY ROOM UPGRADE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-11-21 | 2009-05-19 | 2012-12-22 | 2020-12-19
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM07VYSE | VYSE AVENUE FRONT ENTRANCE DOORS | 1 | DESIGN | 2011-01-01 | 2011-06-29 | 2015-04-01 | 2017-05-11
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM07VYSE | VYSE AVENUE FRONT ENTRANCE DOORS | 2 | BID AWARD AND REGISTER CONTRCT | 2011-06-30 | 2011-11-21 | 2017-05-12 | 2019-02-22
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM07VYSE | VYSE AVENUE FRONT ENTRANCE DOORS | 3 | CONSTRUCTION | 2011-11-22 | 2012-11-20 | 2019-02-23 | 2020-08-14
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM07VYSE | VYSE AVENUE FRONT ENTRANCE DOORS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-11-21 | 2013-05-19 | 2019-02-23 | 2020-08-14
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM07VYSE | VYSE AVENUE FRONT ENTRANCE DOORS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-11-21 | 2013-05-19 | 2020-08-15 | 2021-02-10
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM10EDTV | EDENWALD HOUSES SECURITY CAMERAS | 3 | CONSTRUCTION | 2010-11-22 | 2011-11-21 | 2012-11-21 | 2013-11-20
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM10EDTV | EDENWALD HOUSES SECURITY CAMERAS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2011-11-22 | 2012-05-19 | 2012-11-21 | 2013-11-20
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM10EDTV | EDENWALD HOUSES SECURITY CAMERAS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2011-11-22 | 2012-05-19 | 2013-11-21 | 2014-05-19
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM10SHEC | STEBBINS AVE- HEWITT PLACE (UNION AVE CONS) EXTERIOR COMP | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2011-11-22 | 2012-05-19 | 2017-04-01 | 2018-03-25
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM10SHEC | STEBBINS AVE- HEWITT PLACE (UNION AVE CONS) EXTERIOR COMP | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2011-11-22 | 2012-05-19 | 2018-03-26 | 2018-09-26
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM11CHPY | CASTLE HILL PLAYGROUND AND OUTDOOR AREA | 1 | DESIGN | 2011-01-01 | 2011-06-29 | 2014-05-22 | 2016-11-05
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM11CHPY | CASTLE HILL PLAYGROUND AND OUTDOOR AREA | 2 | BID AWARD AND REGISTER CONTRCT | 2011-06-30 | 2011-11-21 | 2016-11-06 | 2017-03-23
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM11CHPY | CASTLE HILL PLAYGROUND AND OUTDOOR AREA | 3 | CONSTRUCTION | 2011-11-22 | 2012-11-20 | 2017-03-24 | 2018-02-15
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM11CHPY | CASTLE HILL PLAYGROUND AND OUTDOOR AREA | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-11-21 | 2013-05-19 | 2017-03-24 | 2018-02-15
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM11CHPY | CASTLE HILL PLAYGROUND AND OUTDOOR AREA | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-11-21 | 2013-05-19 | 2018-02-16 | 2020-02-15
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM11CPGP | CLASON POINT PLAYGROUND AND OUTDOOR AREA IMPROVEMENTS | 1 | DESIGN | 2011-01-01 | 2011-06-29 | 2014-05-22 | 2016-10-13
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM11CPGP | CLASON POINT PLAYGROUND AND OUTDOOR AREA IMPROVEMENTS | 2 | BID AWARD AND REGISTER CONTRCT | 2011-06-30 | 2011-11-21 | 2016-10-14 | 2017-11-08
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM11CPGP | CLASON POINT PLAYGROUND AND OUTDOOR AREA IMPROVEMENTS | 3 | CONSTRUCTION | 2011-11-22 | 2012-11-20 | 2017-11-09 | 2019-04-02
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM11CPGP | CLASON POINT PLAYGROUND AND OUTDOOR AREA IMPROVEMENTS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-11-21 | 2013-05-19 | 2017-11-09 | 2019-04-02
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM11CPGP | CLASON POINT PLAYGROUND AND OUTDOOR AREA IMPROVEMENTS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-11-21 | 2013-05-19 | 2019-04-03 | 2021-04-01
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM11DAVC | DAVIDSON/ SITE 166 RES. ASSN SPORTS DOME AND CULINARY PROG. | 1 | DESIGN | 2014-10-14 | 2015-04-11 | 2012-06-29 | 2018-06-15
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM11DAVC | DAVIDSON/ SITE 166 RES. ASSN SPORTS DOME AND CULINARY PROG. | 2 | BID AWARD AND REGISTER CONTRCT | 2015-04-12 | 2015-09-03 | 2018-06-16 | 2018-12-12
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM11DAVC | DAVIDSON/ SITE 166 RES. ASSN SPORTS DOME AND CULINARY PROG. | 3 | CONSTRUCTION | 2015-09-04 | 2016-09-02 | 2018-12-13 | 2020-03-04
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM11DAVC | DAVIDSON/ SITE 166 RES. ASSN SPORTS DOME AND CULINARY PROG. | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-09-03 | 2017-03-01 | 2018-12-13 | 2020-03-04
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM11DAVC | DAVIDSON/ SITE 166 RES. ASSN SPORTS DOME AND CULINARY PROG. | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-09-03 | 2017-03-01 | 2020-03-05 | 2020-08-31
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM12BHTV | BETANCES HOUSES SECURITY CAMERAS | 1 | DESIGN | 2013-01-01 | 2013-06-29 | 2013-01-01 | 2013-06-29
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM12BHTV | BETANCES HOUSES SECURITY CAMERAS | 2 | BID AWARD AND REGISTER CONTRCT | 2013-06-30 | 2013-11-21 | 2013-06-30 | 2013-11-21
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM12BHTV | BETANCES HOUSES SECURITY CAMERAS | 3 | CONSTRUCTION | 2013-11-22 | 2014-11-21 | 2013-11-22 | 2014-11-21
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM12BHTV | BETANCES HOUSES SECURITY CAMERAS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-11-22 | 2015-05-20 | 2013-11-22 | 2014-11-21
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM12BHTV | BETANCES HOUSES SECURITY CAMERAS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-11-22 | 2015-05-20 | 2014-11-22 | 2015-05-20
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM12SHTV | SOUNDVIEW HOUSES SECURITY CAMERAS | 3 | CONSTRUCTION | 2013-11-22 | 2014-11-21 | 2013-11-22 | 2014-11-21
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM12SHTV | SOUNDVIEW HOUSES SECURITY CAMERAS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-11-22 | 2015-05-20 | 2013-11-22 | 2014-11-21
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM12SHTV | SOUNDVIEW HOUSES SECURITY CAMERAS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-11-22 | 2015-05-20 | 2014-11-22 | 2015-05-20
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM13BRPG | BRONX RIVER HOUSES PLAYGROUND RENOVATION | 1 | DESIGN | 2013-01-01 | 2013-06-29 | 2014-05-22 | 2016-10-13
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM13BRPG | BRONX RIVER HOUSES PLAYGROUND RENOVATION | 2 | BID AWARD AND REGISTER CONTRCT | 2013-06-30 | 2013-11-21 | 2016-10-14 | 2017-03-09
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM13BRPG | BRONX RIVER HOUSES PLAYGROUND RENOVATION | 3 | CONSTRUCTION | 2013-11-22 | 2014-11-21 | 2017-03-10 | 2018-06-02
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM13BRPG | BRONX RIVER HOUSES PLAYGROUND RENOVATION | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-11-22 | 2015-05-20 | 2017-03-10 | 2018-06-02
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM13BRPG | BRONX RIVER HOUSES PLAYGROUND RENOVATION | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-11-22 | 2015-05-20 | 2018-06-03 | 2021-06-01
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM13SAPK | SACK WERN HOUSES PARKING LOT | 1 | DESIGN | 2013-01-01 | 2013-06-29 | 2013-01-01 | 2013-12-30
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM13SAPK | SACK WERN HOUSES PARKING LOT | 2 | BID AWARD AND REGISTER CONTRCT | 2013-06-30 | 2013-11-21 | 2013-12-31 | 2015-06-09
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM13SAPK | SACK WERN HOUSES PARKING LOT | 3 | CONSTRUCTION | 2013-11-22 | 2014-11-21 | 2015-06-10 | 2016-10-06
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM13SAPK | SACK WERN HOUSES PARKING LOT | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-11-22 | 2015-05-20 | 2015-06-10 | 2016-10-06
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM13SAPK | SACK WERN HOUSES PARKING LOT | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-11-22 | 2015-05-20 | 2016-10-07 | 2017-04-04
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM14BASE | BAILEY HOUSES SECURITY ENHANCEMENTS | 2 | BID AWARD AND REGISTER CONTRCT | 2014-04-29 | 2014-09-20 | 2014-04-29 | 2014-09-20
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM14BASE | BAILEY HOUSES SECURITY ENHANCEMENTS | 3 | CONSTRUCTION | 2014-09-21 | 2015-09-20 | 2014-09-21 | 2015-09-20
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM14BASE | BAILEY HOUSES SECURITY ENHANCEMENTS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-09-21 | 2016-03-18 | 2014-09-21 | 2015-09-20
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM14BASE | BAILEY HOUSES SECURITY ENHANCEMENTS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-09-21 | 2016-03-18 | 2015-09-21 | 2016-03-18
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM14EGSE | EASTCHESTER GARDENS SECURITY ENHANCEMENTS | 1 | DESIGN | 2013-10-31 | 2014-04-28 | 2013-10-31 | 2014-04-28
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM14EGSE | EASTCHESTER GARDENS SECURITY ENHANCEMENTS | 2 | BID AWARD AND REGISTER CONTRCT | 2014-04-29 | 2014-09-20 | 2014-04-29 | 2014-09-20
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM14EGSE | EASTCHESTER GARDENS SECURITY ENHANCEMENTS | 3 | CONSTRUCTION | 2014-09-21 | 2015-09-20 | 2014-09-21 | 2015-09-20
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM14EGSE | EASTCHESTER GARDENS SECURITY ENHANCEMENTS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-09-21 | 2016-03-18 | 2014-09-21 | 2015-09-20
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM14EGSE | EASTCHESTER GARDENS SECURITY ENHANCEMENTS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-09-21 | 2016-03-18 | 2015-09-21 | 2016-03-18
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM14FISE | FORT INDEPENDNECE SECURITY ENHANCEMENTS | 3 | CONSTRUCTION | 2014-09-21 | 2015-09-20 | 2014-09-21 | 2015-09-20
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM14FISE | FORT INDEPENDNECE SECURITY ENHANCEMENTS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-09-21 | 2016-03-18 | 2014-09-21 | 2015-09-20
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM14FISE | FORT INDEPENDNECE SECURITY ENHANCEMENTS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-09-21 | 2016-03-18 | 2015-09-21 | 2016-03-18
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM14MCSE | MCKINLEY SECURITY ENHANCEMENTS | 3 | CONSTRUCTION | 2014-09-21 | 2015-09-20 | 2014-09-21 | 2015-09-20
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM14MCSE | MCKINLEY SECURITY ENHANCEMENTS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-09-21 | 2016-03-18 | 2014-09-21 | 2015-09-20
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM14MCSE | MCKINLEY SECURITY ENHANCEMENTS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-09-21 | 2016-03-18 | 2015-09-21 | 2016-03-18
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM14MISC | MIDDLETOWN SECURITY ENHANCEMENTS | 1 | DESIGN | 2013-10-31 | 2014-04-28 | 2013-10-31 | 2014-04-28
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM14MISC | MIDDLETOWN SECURITY ENHANCEMENTS | 2 | BID AWARD AND REGISTER CONTRCT | 2014-04-29 | 2014-09-20 | 2014-04-29 | 2014-09-20
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM14MISC | MIDDLETOWN SECURITY ENHANCEMENTS | 3 | CONSTRUCTION | 2014-09-21 | 2015-09-20 | 2014-09-21 | 2015-09-20
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM14MISC | MIDDLETOWN SECURITY ENHANCEMENTS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-09-21 | 2016-03-18 | 2014-09-21 | 2015-09-20
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM14MISC | MIDDLETOWN SECURITY ENHANCEMENTS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-09-21 | 2016-03-18 | 2015-09-21 | 2016-03-18
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM14MKGH | MILLBROOK HOUSES SOLAR POWERED GREENHOUSE | 1 | DESIGN | 2014-01-01 | 2014-06-29 | 2014-09-01 | 2017-11-22
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM14MKGH | MILLBROOK HOUSES SOLAR POWERED GREENHOUSE | 2 | BID AWARD AND REGISTER CONTRCT | 2014-06-30 | 2014-11-21 | 2017-11-23 | 2018-05-21
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM14MKGH | MILLBROOK HOUSES SOLAR POWERED GREENHOUSE | 3 | CONSTRUCTION | 2014-11-22 | 2015-11-21 | 2018-05-22 | 2020-02-08
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM14MKGH | MILLBROOK HOUSES SOLAR POWERED GREENHOUSE | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-11-22 | 2016-05-19 | 2018-05-22 | 2020-02-08
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM14MKGH | MILLBROOK HOUSES SOLAR POWERED GREENHOUSE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-11-22 | 2016-05-19 | 2020-02-09 | 2020-06-19
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM14MLBQ | MILLBROOK HOUSES - TWO BARBEQUE AREAS | 1 | DESIGN | 2014-01-01 | 2014-06-29 | 2014-05-22 | 2017-02-17
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM14MLBQ | MILLBROOK HOUSES - TWO BARBEQUE AREAS | 2 | BID AWARD AND REGISTER CONTRCT | 2014-06-30 | 2014-11-21 | 2017-02-18 | 2017-08-16
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM14MLBQ | MILLBROOK HOUSES - TWO BARBEQUE AREAS | 3 | CONSTRUCTION | 2014-11-22 | 2015-11-21 | 2017-08-17 | 2018-06-30
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM14MLBQ | MILLBROOK HOUSES - TWO BARBEQUE AREAS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-11-22 | 2016-05-19 | 2017-08-17 | 2018-06-30
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM14MLBQ | MILLBROOK HOUSES - TWO BARBEQUE AREAS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-11-22 | 2016-05-19 | 2018-07-01 | 2020-06-29
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM14MRSR | MONROE HOUSES SENIOR CENTER RENOVATION | 1 | DESIGN | 2014-01-01 | 2014-06-29 | 2015-05-15 | 2017-03-13
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM14MRSR | MONROE HOUSES SENIOR CENTER RENOVATION | 2 | BID AWARD AND REGISTER CONTRCT | 2014-06-30 | 2014-11-21 | 2017-03-14 | 2017-08-09
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM14MRSR | MONROE HOUSES SENIOR CENTER RENOVATION | 3 | CONSTRUCTION | 2014-11-22 | 2015-11-21 | 2017-08-10 | 2018-05-07
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM14MRSR | MONROE HOUSES SENIOR CENTER RENOVATION | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-11-22 | 2016-05-19 | 2017-08-10 | 2018-05-07
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM14MRSR | MONROE HOUSES SENIOR CENTER RENOVATION | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-11-22 | 2016-05-19 | 2018-05-08 | 2021-05-06
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM14SHPL | STEBBINS AVENUE - HEWITT PLACE PLAYGROUND RENOVATION | 1 | DESIGN | 2014-01-01 | 2014-06-29 | 2014-06-13 | 2017-01-31
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM14SHPL | STEBBINS AVENUE - HEWITT PLACE PLAYGROUND RENOVATION | 2 | BID AWARD AND REGISTER CONTRCT | 2014-06-30 | 2014-11-21 | 2017-02-01 | 2017-07-29
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM14SHPL | STEBBINS AVENUE - HEWITT PLACE PLAYGROUND RENOVATION | 3 | CONSTRUCTION | 2014-11-22 | 2015-11-21 | 2017-07-30 | 2018-06-14
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM14SHPL | STEBBINS AVENUE - HEWITT PLACE PLAYGROUND RENOVATION | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-11-22 | 2016-05-19 | 2017-07-30 | 2018-06-14
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM14SHPL | STEBBINS AVENUE - HEWITT PLACE PLAYGROUND RENOVATION | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-11-22 | 2016-05-19 | 2018-06-15 | 2020-06-13
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM14SMGD | ST. MARY'S PARK PLAYGROUND RENOVATION | 1 | DESIGN | 2014-01-01 | 2014-06-29 | 2014-01-15 | 2015-10-29
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM14SMGD | ST. MARY'S PARK PLAYGROUND RENOVATION | 2 | BID AWARD AND REGISTER CONTRCT | 2014-06-30 | 2014-11-21 | 2015-10-30 | 2016-04-01
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM14SMGD | ST. MARY'S PARK PLAYGROUND RENOVATION | 3 | CONSTRUCTION | 2014-11-22 | 2015-11-21 | 2016-04-02 | 2017-03-25
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM14SMGD | ST. MARY'S PARK PLAYGROUND RENOVATION | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-11-22 | 2016-05-19 | 2016-04-02 | 2017-03-25
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM14SMGD | ST. MARY'S PARK PLAYGROUND RENOVATION | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-11-22 | 2016-05-19 | 2017-03-26 | 2021-03-24
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM15FOCC | FOREST HOUSES COMMUNITY CENTER GYM AND LOCKER ROOMS | 1 | DESIGN | 2015-01-02 | 2015-06-30 | 2015-02-19 | 2017-08-17
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM15FOCC | FOREST HOUSES COMMUNITY CENTER GYM AND LOCKER ROOMS | 2 | BID AWARD AND REGISTER CONTRCT | 2015-07-01 | 2015-11-22 | 2017-08-18 | 2018-07-30
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM15FOCC | FOREST HOUSES COMMUNITY CENTER GYM AND LOCKER ROOMS | 3 | CONSTRUCTION | 2015-11-23 | 2016-11-21 | 2018-07-31 | 2019-07-23
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM15FOCC | FOREST HOUSES COMMUNITY CENTER GYM AND LOCKER ROOMS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-11-22 | 2017-05-20 | 2018-07-31 | 2019-07-23
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM15FOCC | FOREST HOUSES COMMUNITY CENTER GYM AND LOCKER ROOMS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-11-22 | 2017-05-20 | 2019-07-24 | 2020-01-19
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM15FTGD | FORT INDEPENDENCE - HEATH AVENUE REHAB PARK | 2 | BID AWARD AND REGISTER CONTRCT | 2015-07-01 | 2015-11-22 | 2017-03-31 | 2017-09-11
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM15FTGD | FORT INDEPENDENCE - HEATH AVENUE REHAB PARK | 3 | CONSTRUCTION | 2015-11-23 | 2016-11-21 | 2017-09-12 | 2018-03-09
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM15FTGD | FORT INDEPENDENCE - HEATH AVENUE REHAB PARK | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-11-22 | 2017-05-20 | 2017-09-12 | 2018-03-09
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM15FTGD | FORT INDEPENDENCE - HEATH AVENUE REHAB PARK | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-11-22 | 2017-05-20 | 2018-03-10 | 2018-09-04
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM15SHGC | STEBBINS AVENUE-HEWITT PLACE INFRASTRUCTURE IMPROVEMENTS | 1 | DESIGN | 2015-01-02 | 2015-06-30 | 2015-12-31 | 2016-12-29
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM15SHGC | STEBBINS AVENUE-HEWITT PLACE INFRASTRUCTURE IMPROVEMENTS | 2 | BID AWARD AND REGISTER CONTRCT | 2015-07-01 | 2015-11-22 | 2016-12-30 | 2017-03-26
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM15SHGC | STEBBINS AVENUE-HEWITT PLACE INFRASTRUCTURE IMPROVEMENTS | 3 | CONSTRUCTION | 2015-11-23 | 2016-11-21 | 2017-03-27 | 2017-11-30
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM15SHGC | STEBBINS AVENUE-HEWITT PLACE INFRASTRUCTURE IMPROVEMENTS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-11-22 | 2017-05-20 | 2017-03-27 | 2017-11-30
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM15SHGC | STEBBINS AVENUE-HEWITT PLACE INFRASTRUCTURE IMPROVEMENTS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-11-22 | 2017-05-20 | 2017-12-01 | 2019-11-30
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM15TWPK | SECURITY SYSTEMS AT TWIN PARKS CONS AND PARKSIDE | 1 | DESIGN | 2015-01-02 | 2015-06-30 | 2015-01-02 | 2015-06-30
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM15TWPK | SECURITY SYSTEMS AT TWIN PARKS CONS AND PARKSIDE | 2 | BID AWARD AND REGISTER CONTRCT | 2015-07-01 | 2015-11-22 | 2015-07-01 | 2015-11-22
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM15TWPK | SECURITY SYSTEMS AT TWIN PARKS CONS AND PARKSIDE | 3 | CONSTRUCTION | 2015-11-23 | 2016-11-21 | 2015-11-23 | 2016-11-21
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM15TWPK | SECURITY SYSTEMS AT TWIN PARKS CONS AND PARKSIDE | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-11-22 | 2017-05-20 | 2015-11-23 | 2016-11-21
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM15TWPK | SECURITY SYSTEMS AT TWIN PARKS CONS AND PARKSIDE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-11-22 | 2017-05-20 | 2016-11-22 | 2020-11-20
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM16BSGD | BOSTON SECOR PLAYGROUND RENOVATION | 1 | DESIGN | 2016-06-30 | 2016-12-26 | 2016-06-30 | 2016-12-26
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM16BSGD | BOSTON SECOR PLAYGROUND RENOVATION | 2 | BID AWARD AND REGISTER CONTRCT | 2016-12-27 | 2017-05-20 | 2016-12-27 | 2017-05-20
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM16BSGD | BOSTON SECOR PLAYGROUND RENOVATION | 3 | CONSTRUCTION | 2017-05-21 | 2018-05-20 | 2017-05-21 | 2018-05-20
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM16BSGD | BOSTON SECOR PLAYGROUND RENOVATION | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-05-21 | 2018-11-16 | 2017-05-21 | 2018-05-20
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM16BSGD | BOSTON SECOR PLAYGROUND RENOVATION | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-05-21 | 2018-11-16 | 2018-05-21 | 2020-05-19
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM16CLGY | CLAREMONT HOUSES GYM RENOVATION FOR CLAREMONT NEIGHBORHOOD | 1 | DESIGN | 2016-01-04 | 2016-07-01 | 2016-05-27 | 2018-12-30
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM16CLGY | CLAREMONT HOUSES GYM RENOVATION FOR CLAREMONT NEIGHBORHOOD | 2 | BID AWARD AND REGISTER CONTRCT | 2016-07-02 | 2016-11-23 | 2018-12-31 | 2019-06-28
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM16CLGY | CLAREMONT HOUSES GYM RENOVATION FOR CLAREMONT NEIGHBORHOOD | 3 | CONSTRUCTION | 2016-11-24 | 2017-11-23 | 2018-06-29 | 2020-11-11
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM16CLGY | CLAREMONT HOUSES GYM RENOVATION FOR CLAREMONT NEIGHBORHOOD | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-11-24 | 2018-05-22 | 2018-06-29 | 2020-11-11
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM16CLGY | CLAREMONT HOUSES GYM RENOVATION FOR CLAREMONT NEIGHBORHOOD | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-11-24 | 2018-05-22 | 2020-11-12 | 2021-05-10
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM16FOSC | INSTALLATION OF SECURITY CAMERAS AT FOREST HOUSES | 1 | DESIGN | 2016-03-02 | 2016-08-28 | 2016-03-02 | 2016-08-28
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM16FOSC | INSTALLATION OF SECURITY CAMERAS AT FOREST HOUSES | 2 | BID AWARD AND REGISTER CONTRCT | 2016-08-29 | 2017-01-20 | 2016-08-29 | 2017-01-20
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM16FOSC | INSTALLATION OF SECURITY CAMERAS AT FOREST HOUSES | 3 | CONSTRUCTION | 2017-01-21 | 2018-01-20 | 2017-01-21 | 2018-01-20
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM16FOSC | INSTALLATION OF SECURITY CAMERAS AT FOREST HOUSES | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-01-21 | 2018-07-19 | 2017-01-21 | 2018-01-20
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM16FOSC | INSTALLATION OF SECURITY CAMERAS AT FOREST HOUSES | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-01-21 | 2018-07-19 | 2018-01-21 | 2020-01-20
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM16GUPL | GUN HILL HOUSES PLAYGROUND | 2 | BID AWARD AND REGISTER CONTRCT | 2016-12-27 | 2017-05-20 | 2016-12-27 | 2017-05-20
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM16GUPL | GUN HILL HOUSES PLAYGROUND | 3 | CONSTRUCTION | 2017-05-21 | 2018-05-20 | 2017-05-21 | 2018-05-20
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM16GUPL | GUN HILL HOUSES PLAYGROUND | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-05-21 | 2018-11-16 | 2017-05-21 | 2018-05-20
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM16GUPL | GUN HILL HOUSES PLAYGROUND | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-05-21 | 2018-11-16 | 2018-05-21 | 2018-11-16
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM16MODC | JAMES MONROE HOUSES RENOVATE COMMUNITY CENTER | 1 | DESIGN | 2016-01-04 | 2016-07-01 | 2016-01-04 | 2016-07-01
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM16MODC | JAMES MONROE HOUSES RENOVATE COMMUNITY CENTER | 2 | BID AWARD AND REGISTER CONTRCT | 2016-07-02 | 2016-11-23 | 2016-07-02 | 2016-11-23
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM16MODC | JAMES MONROE HOUSES RENOVATE COMMUNITY CENTER | 3 | CONSTRUCTION | 2016-11-24 | 2017-11-23 | 2016-11-24 | 2017-11-23
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM16MODC | JAMES MONROE HOUSES RENOVATE COMMUNITY CENTER | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-11-24 | 2018-05-22 | 2016-11-24 | 2017-11-23
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM16MODC | JAMES MONROE HOUSES RENOVATE COMMUNITY CENTER | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-11-24 | 2018-05-22 | 2017-11-24 | 2020-11-22
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM16VRCA | RECONSTRUCTION OF COMMON AREAS | 1 | DESIGN | 2016-01-04 | 2016-07-01 | 2016-01-04 | 2016-07-01
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM16VRCA | RECONSTRUCTION OF COMMON AREAS | 2 | BID AWARD AND REGISTER CONTRCT | 2016-07-02 | 2016-11-23 | 2016-07-02 | 2016-11-23
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM16VRCA | RECONSTRUCTION OF COMMON AREAS | 3 | CONSTRUCTION | 2016-11-24 | 2017-11-23 | 2016-11-24 | 2017-11-23
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM16VRCA | RECONSTRUCTION OF COMMON AREAS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-11-24 | 2018-05-22 | 2016-11-24 | 2017-11-23
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM16VRCA | RECONSTRUCTION OF COMMON AREAS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-11-24 | 2018-05-22 | 2017-11-24 | 2020-11-22
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM17BASK | BASKETBALL COURTS RENOVATION AT ADAMS HOUSES | 3 | CONSTRUCTION | 2018-10-05 | 2019-10-04 | 2018-10-05 | 2019-10-04
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM17BASK | BASKETBALL COURTS RENOVATION AT ADAMS HOUSES | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-10-05 | 2020-04-01 | 2018-10-05 | 2019-10-04
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM17BASK | BASKETBALL COURTS RENOVATION AT ADAMS HOUSES | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-10-05 | 2020-04-01 | 2019-10-05 | 2020-04-01
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM17CLTV | COLLEGE AVENUE -EAST 165TH STREET SECURITY CAMERAS | 1 | DESIGN | 2017-02-01 | 2017-07-30 | 2017-02-01 | 2017-07-30
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM17CLTV | COLLEGE AVENUE -EAST 165TH STREET SECURITY CAMERAS | 2 | BID AWARD AND REGISTER CONTRCT | 2017-07-31 | 2017-12-22 | 2017-07-31 | 2017-12-22
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM17CLTV | COLLEGE AVENUE -EAST 165TH STREET SECURITY CAMERAS | 3 | CONSTRUCTION | 2017-12-23 | 2018-12-22 | 2017-12-23 | 2018-12-22
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM17CLTV | COLLEGE AVENUE -EAST 165TH STREET SECURITY CAMERAS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-12-23 | 2019-06-20 | 2017-12-23 | 2018-12-22
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM17CLTV | COLLEGE AVENUE -EAST 165TH STREET SECURITY CAMERAS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-12-23 | 2019-06-20 | 2018-12-23 | 2020-12-21
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM17FORF | ROOF REPLACEMENT AT FOREST HOUSES | 1 | DESIGN | 2017-01-02 | 2017-06-30 | 2017-01-02 | 2017-06-30
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM17FORF | ROOF REPLACEMENT AT FOREST HOUSES | 2 | BID AWARD AND REGISTER CONTRCT | 2017-07-01 | 2017-11-22 | 2017-07-01 | 2017-11-22
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM17FORF | ROOF REPLACEMENT AT FOREST HOUSES | 3 | CONSTRUCTION | 2017-11-23 | 2018-11-22 | 2017-11-23 | 2018-11-22
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM17FORF | ROOF REPLACEMENT AT FOREST HOUSES | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-11-23 | 2019-05-21 | 2017-11-23 | 2018-11-22
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM17FORF | ROOF REPLACEMENT AT FOREST HOUSES | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-11-23 | 2019-05-21 | 2018-11-23 | 2020-11-21
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM17MASC | MORRISANIA SECURITY ENHANCEMENTS | 1 | DESIGN | 2016-08-01 | 2017-01-27 | 2016-08-01 | 2017-01-27
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM17MASC | MORRISANIA SECURITY ENHANCEMENTS | 2 | BID AWARD AND REGISTER CONTRCT | 2017-01-28 | 2017-06-21 | 2017-01-28 | 2017-06-21
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM17MASC | MORRISANIA SECURITY ENHANCEMENTS | 3 | CONSTRUCTION | 2017-06-22 | 2018-06-21 | 2017-06-22 | 2018-06-21
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM17MASC | MORRISANIA SECURITY ENHANCEMENTS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-06-22 | 2018-12-18 | 2017-06-22 | 2018-06-21
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM17MASC | MORRISANIA SECURITY ENHANCEMENTS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-06-22 | 2018-12-18 | 2018-06-22 | 2018-12-18
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM17MNTV | MONROE HOUSES SECURITY CAMERAS | 1 | DESIGN | 2017-02-02 | 2017-07-31 | 2017-02-02 | 2017-07-31
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM17MNTV | MONROE HOUSES SECURITY CAMERAS | 2 | BID AWARD AND REGISTER CONTRCT | 2017-08-01 | 2017-12-23 | 2017-08-01 | 2017-12-23
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM17MNTV | MONROE HOUSES SECURITY CAMERAS | 3 | CONSTRUCTION | 2017-12-24 | 2018-12-23 | 2017-12-24 | 2018-12-23
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM17MNTV | MONROE HOUSES SECURITY CAMERAS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-12-24 | 2019-06-21 | 2017-12-24 | 2018-12-23
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM17MNTV | MONROE HOUSES SECURITY CAMERAS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-12-24 | 2019-06-21 | 2018-12-24 | 2020-12-22
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM17MUGR | MURPHY HOUSES GROUNDS RENOVATION | 1 | DESIGN | 2017-02-02 | 2017-07-31 | 2017-02-02 | 2017-07-31
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM17MUGR | MURPHY HOUSES GROUNDS RENOVATION | 2 | BID AWARD AND REGISTER CONTRCT | 2017-08-01 | 2017-12-23 | 2017-08-01 | 2017-12-23
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM17MUGR | MURPHY HOUSES GROUNDS RENOVATION | 3 | CONSTRUCTION | 2017-12-24 | 2018-12-23 | 2017-12-24 | 2018-12-23
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM17MUGR | MURPHY HOUSES GROUNDS RENOVATION | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-12-24 | 2019-06-21 | 2017-12-24 | 2018-12-23
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM17MUGR | MURPHY HOUSES GROUNDS RENOVATION | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-12-24 | 2019-06-21 | 2018-12-24 | 2020-12-22
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM17PHCC | PATTERSON HOUSES COMMUNITY CENTER REHAB | 1 | DESIGN | 2017-02-01 | 2017-07-30 | 2017-02-01 | 2017-07-30
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM17PHCC | PATTERSON HOUSES COMMUNITY CENTER REHAB | 2 | BID AWARD AND REGISTER CONTRCT | 2017-07-31 | 2017-12-22 | 2017-07-31 | 2017-12-22
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM17PHCC | PATTERSON HOUSES COMMUNITY CENTER REHAB | 3 | CONSTRUCTION | 2017-12-23 | 2018-12-22 | 2017-12-23 | 2018-12-22
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM17PHCC | PATTERSON HOUSES COMMUNITY CENTER REHAB | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-12-23 | 2019-06-20 | 2017-12-23 | 2018-12-22
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM17PHCC | PATTERSON HOUSES COMMUNITY CENTER REHAB | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-12-23 | 2019-06-20 | 2018-12-23 | 2020-12-21
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18BRCB | BOSTON ROAD SENIOR CENTER ROOF REPLACEMENT | 1 | DESIGN | 2018-01-02 | 2018-06-30 | 2018-01-02 | 2018-06-30
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18BRCB | BOSTON ROAD SENIOR CENTER ROOF REPLACEMENT | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18BRCB | BOSTON ROAD SENIOR CENTER ROOF REPLACEMENT | 3 | CONSTRUCTION | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18BRCB | BOSTON ROAD SENIOR CENTER ROOF REPLACEMENT | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-28 | 2020-06-24 | 2018-12-28 | 2019-12-27
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18BRCB | BOSTON ROAD SENIOR CENTER ROOF REPLACEMENT | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-28 | 2020-06-24 | 2019-12-28 | 2020-06-24
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18BRCC | Bronx River CC: Children's Arts and Science Workshops | 1 | DESIGN | 2018-01-02 | 2018-06-30 | 2018-01-02 | 2018-06-30
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18BRCC | Bronx River CC: Children's Arts and Science Workshops | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18BRCC | Bronx River CC: Children's Arts and Science Workshops | 3 | CONSTRUCTION | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18BRCC | Bronx River CC: Children's Arts and Science Workshops | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-28 | 2020-06-24 | 2018-12-28 | 2019-12-27
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18BRCC | Bronx River CC: Children's Arts and Science Workshops | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-28 | 2020-06-24 | 2019-12-28 | 2020-06-24
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CCMH | MELROSE HOUSES CCTV AND LAC | 1 | DESIGN | 2018-02-05 | 2018-08-03 | 2018-02-05 | 2018-08-03
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CCMH | MELROSE HOUSES CCTV AND LAC | 2 | BID AWARD AND REGISTER CONTRCT | 2018-08-04 | 2019-01-30 | 2018-08-04 | 2019-01-30
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CCMH | MELROSE HOUSES CCTV AND LAC | 3 | CONSTRUCTION | 2019-01-31 | 2020-01-30 | 2019-01-31 | 2020-01-30
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CCMH | MELROSE HOUSES CCTV AND LAC | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-01-31 | 2020-07-28 | 2019-01-31 | 2020-01-30
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CCMH | MELROSE HOUSES CCTV AND LAC | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-01-31 | 2020-07-28 | 2020-01-31 | 2020-07-28
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18COSC | SECURITY CAMERA INSTALLATION AT 372 EAST 152ND ST COURTLANDT | 1 | DESIGN | 2018-01-02 | 2018-06-30 | 2018-01-02 | 2018-06-30
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18COSC | SECURITY CAMERA INSTALLATION AT 372 EAST 152ND ST COURTLANDT | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18COSC | SECURITY CAMERA INSTALLATION AT 372 EAST 152ND ST COURTLANDT | 3 | CONSTRUCTION | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18COSC | SECURITY CAMERA INSTALLATION AT 372 EAST 152ND ST COURTLANDT | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-28 | 2020-06-24 | 2018-12-28 | 2019-12-27
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18COSC | SECURITY CAMERA INSTALLATION AT 372 EAST 152ND ST COURTLANDT | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-28 | 2020-06-24 | 2019-12-28 | 2020-06-24
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18EATR | Renovation of East Tremont Childcare Center Playground | 1 | DESIGN | 2018-06-01 | 2018-11-27 | 2018-06-01 | 2018-11-27
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18EATR | Renovation of East Tremont Childcare Center Playground | 2 | BID AWARD AND REGISTER CONTRCT | 2018-11-28 | 2019-05-26 | 2018-11-28 | 2019-05-26
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18EATR | Renovation of East Tremont Childcare Center Playground | 3 | CONSTRUCTION | 2019-05-27 | 2020-05-25 | 2019-05-27 | 2020-05-25
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18EATR | Renovation of East Tremont Childcare Center Playground | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-05-26 | 2020-11-21 | 2019-05-27 | 2020-05-25
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18EATR | Renovation of East Tremont Childcare Center Playground | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-05-26 | 2020-11-21 | 2020-05-26 | 2020-11-21
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18FSBO | Boiler Replacements at Pelham Parkway | 1 | DESIGN | 2017-09-16 | 2018-03-14 | 2017-09-16 | 2018-03-14
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18FSBO | Boiler Replacements at Pelham Parkway | 2 | BID AWARD AND REGISTER CONTRCT | 2018-03-15 | 2018-09-10 | 2018-03-15 | 2018-09-10
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18FSBO | Boiler Replacements at Pelham Parkway | 3 | CONSTRUCTION | 2018-09-11 | 2019-09-10 | 2018-09-11 | 2019-09-10
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18FSBO | Boiler Replacements at Pelham Parkway | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-11 | 2020-03-08 | 2018-09-11 | 2019-09-10
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18FSBO | Boiler Replacements at Pelham Parkway | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-11 | 2020-03-08 | 2019-09-11 | 2020-03-08
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18HBLG | EXTERIOR LED LIGHTING AT HIGHBRIDGE GARDENS | 1 | DESIGN | 2018-05-01 | 2018-10-27 | 2018-05-01 | 2018-10-27
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18HBLG | EXTERIOR LED LIGHTING AT HIGHBRIDGE GARDENS | 2 | BID AWARD AND REGISTER CONTRCT | 2018-10-28 | 2019-04-25 | 2018-10-28 | 2019-04-25
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18HBLG | EXTERIOR LED LIGHTING AT HIGHBRIDGE GARDENS | 3 | CONSTRUCTION | 2019-04-26 | 2020-04-24 | 2019-04-26 | 2020-04-24
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18HBLG | EXTERIOR LED LIGHTING AT HIGHBRIDGE GARDENS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-04-25 | 2020-10-21 | 2019-04-26 | 2020-04-24
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18HBLG | EXTERIOR LED LIGHTING AT HIGHBRIDGE GARDENS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-04-25 | 2020-10-21 | 2020-04-25 | 2020-10-21
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18MBLT | MILL BROOK EXTERIOR LIGHTING | 1 | DESIGN | 2018-05-01 | 2018-10-27 | 2018-05-01 | 2018-10-27
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18MBLT | MILL BROOK EXTERIOR LIGHTING | 2 | BID AWARD AND REGISTER CONTRCT | 2018-10-28 | 2019-04-25 | 2018-10-28 | 2019-04-25
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18MBLT | MILL BROOK EXTERIOR LIGHTING | 3 | CONSTRUCTION | 2019-04-26 | 2020-04-24 | 2019-04-26 | 2020-04-24
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18MBLT | MILL BROOK EXTERIOR LIGHTING | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-04-25 | 2020-10-21 | 2019-04-26 | 2020-04-24
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18MBLT | MILL BROOK EXTERIOR LIGHTING | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-04-25 | 2020-10-21 | 2020-04-25 | 2020-10-21
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18MBSS | MILL BROOK HOUSES SPRAY SHOWERS | 1 | DESIGN | 2018-02-15 | 2018-08-13 | 2018-02-15 | 2018-08-13
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18MBSS | MILL BROOK HOUSES SPRAY SHOWERS | 2 | BID AWARD AND REGISTER CONTRCT | 2018-08-14 | 2019-02-09 | 2018-08-14 | 2019-02-09
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18MBSS | MILL BROOK HOUSES SPRAY SHOWERS | 3 | CONSTRUCTION | 2019-02-10 | 2020-02-09 | 2019-02-10 | 2020-02-09
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18MBSS | MILL BROOK HOUSES SPRAY SHOWERS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-02-10 | 2020-08-07 | 2019-02-10 | 2020-02-09
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18MBSS | MILL BROOK HOUSES SPRAY SHOWERS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-02-10 | 2020-08-07 | 2020-02-10 | 2020-08-07
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18MRP1 | MORRIS I PLAYGROUND RENOVATION IN FRONT OF 3606 THIRD AVE | 1 | DESIGN | 2018-06-01 | 2018-11-27 | 2018-06-01 | 2018-11-27
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18MRP1 | MORRIS I PLAYGROUND RENOVATION IN FRONT OF 3606 THIRD AVE | 2 | BID AWARD AND REGISTER CONTRCT | 2018-11-28 | 2019-05-26 | 2018-11-28 | 2019-05-26
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18MRP1 | MORRIS I PLAYGROUND RENOVATION IN FRONT OF 3606 THIRD AVE | 3 | CONSTRUCTION | 2019-05-27 | 2020-05-25 | 2019-05-27 | 2020-05-25
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18MRP1 | MORRIS I PLAYGROUND RENOVATION IN FRONT OF 3606 THIRD AVE | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-05-26 | 2020-11-21 | 2019-05-27 | 2020-05-25
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18MRP1 | MORRIS I PLAYGROUND RENOVATION IN FRONT OF 3606 THIRD AVE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-05-26 | 2020-11-21 | 2020-05-26 | 2020-11-21
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18MRPG | MORRIS II PLAYGROUND RENOVATION IN FRONT OF 1481 WASHINGTON | 1 | DESIGN | 2018-06-01 | 2018-11-27 | 2018-06-01 | 2018-11-27
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18MRPG | MORRIS II PLAYGROUND RENOVATION IN FRONT OF 1481 WASHINGTON | 2 | BID AWARD AND REGISTER CONTRCT | 2018-11-28 | 2019-05-26 | 2018-11-28 | 2019-05-26
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18MRPG | MORRIS II PLAYGROUND RENOVATION IN FRONT OF 1481 WASHINGTON | 3 | CONSTRUCTION | 2019-05-27 | 2020-05-25 | 2019-05-27 | 2020-05-25
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18MRPG | MORRIS II PLAYGROUND RENOVATION IN FRONT OF 1481 WASHINGTON | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-05-26 | 2020-11-21 | 2019-05-27 | 2020-05-25
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18MRPG | MORRIS II PLAYGROUND RENOVATION IN FRONT OF 1481 WASHINGTON | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-05-26 | 2020-11-21 | 2020-05-26 | 2020-11-21
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18MTGD | MITCHEL HOUSES EXTERIOR LIGHTING | 1 | DESIGN | 2018-05-01 | 2018-10-27 | 2018-05-01 | 2018-10-27
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18MTGD | MITCHEL HOUSES EXTERIOR LIGHTING | 2 | BID AWARD AND REGISTER CONTRCT | 2018-10-28 | 2019-04-25 | 2018-10-28 | 2019-04-25
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18MTGD | MITCHEL HOUSES EXTERIOR LIGHTING | 3 | CONSTRUCTION | 2019-04-26 | 2020-04-24 | 2019-04-26 | 2020-04-24
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18MTGD | MITCHEL HOUSES EXTERIOR LIGHTING | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-04-25 | 2020-10-21 | 2019-04-26 | 2020-04-24
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18MTGD | MITCHEL HOUSES EXTERIOR LIGHTING | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-04-25 | 2020-10-21 | 2020-04-25 | 2020-10-21
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18PCCK | KITCHEN RENOVATION AT PATTERSON HOUSES COMMUNITY CENTER | 1 | DESIGN | 2018-01-02 | 2018-06-30 | 2018-01-02 | 2018-06-30
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18PCCK | KITCHEN RENOVATION AT PATTERSON HOUSES COMMUNITY CENTER | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18PCCK | KITCHEN RENOVATION AT PATTERSON HOUSES COMMUNITY CENTER | 3 | CONSTRUCTION | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18PCCK | KITCHEN RENOVATION AT PATTERSON HOUSES COMMUNITY CENTER | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-28 | 2020-06-24 | 2018-12-28 | 2019-12-27
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18PCCK | KITCHEN RENOVATION AT PATTERSON HOUSES COMMUNITY CENTER | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-28 | 2020-06-24 | 2019-12-28 | 2020-06-24
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18PPHL | Pelham Parkway Houses Exterior Lighting Installation | 1 | DESIGN | 2018-05-01 | 2018-10-27 | 2018-05-01 | 2018-10-27
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18PPHL | Pelham Parkway Houses Exterior Lighting Installation | 2 | BID AWARD AND REGISTER CONTRCT | 2018-10-28 | 2019-04-25 | 2018-10-28 | 2019-04-25
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18PPHL | Pelham Parkway Houses Exterior Lighting Installation | 3 | CONSTRUCTION | 2019-04-26 | 2020-04-24 | 2019-04-26 | 2020-04-24
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18PPHL | Pelham Parkway Houses Exterior Lighting Installation | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-04-25 | 2020-10-21 | 2019-04-26 | 2020-04-24
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18PPHL | Pelham Parkway Houses Exterior Lighting Installation | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-04-25 | 2020-10-21 | 2020-04-25 | 2020-10-21
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18RBSC | SECURITY CAMERAS AT THROGGS NECK (RANDALL- BALCOLM) | 1 | DESIGN | 2018-01-02 | 2018-06-30 | 2018-01-02 | 2018-06-30
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18RBSC | SECURITY CAMERAS AT THROGGS NECK (RANDALL- BALCOLM) | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18RBSC | SECURITY CAMERAS AT THROGGS NECK (RANDALL- BALCOLM) | 3 | CONSTRUCTION | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18RBSC | SECURITY CAMERAS AT THROGGS NECK (RANDALL- BALCOLM) | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-28 | 2020-06-24 | 2018-12-28 | 2019-12-27
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18RBSC | SECURITY CAMERAS AT THROGGS NECK (RANDALL- BALCOLM) | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-28 | 2020-06-24 | 2019-12-28 | 2020-06-24
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18SMTV | SOTOMAYOR SECURITY ENHANCEMENTS AT 1055 ROSEDALE AVENURE | 1 | DESIGN | 2018-01-02 | 2018-06-30 | 2018-01-02 | 2018-06-30
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18SMTV | SOTOMAYOR SECURITY ENHANCEMENTS AT 1055 ROSEDALE AVENURE | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18SMTV | SOTOMAYOR SECURITY ENHANCEMENTS AT 1055 ROSEDALE AVENURE | 3 | CONSTRUCTION | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18SMTV | SOTOMAYOR SECURITY ENHANCEMENTS AT 1055 ROSEDALE AVENURE | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-28 | 2020-06-24 | 2018-12-28 | 2019-12-27
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18SMTV | SOTOMAYOR SECURITY ENHANCEMENTS AT 1055 ROSEDALE AVENURE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-28 | 2020-06-24 | 2019-12-28 | 2020-06-24
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18SOCC | Sotomayor CC Cornerstone Program - Computer Technology | 1 | DESIGN | 2018-01-02 | 2018-06-30 | 2018-01-02 | 2018-06-30
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18SOCC | Sotomayor CC Cornerstone Program - Computer Technology | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18SOCC | Sotomayor CC Cornerstone Program - Computer Technology | 3 | CONSTRUCTION | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18SOCC | Sotomayor CC Cornerstone Program - Computer Technology | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-28 | 2020-06-24 | 2018-12-28 | 2019-12-27
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18SOCC | Sotomayor CC Cornerstone Program - Computer Technology | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-28 | 2020-06-24 | 2019-12-28 | 2020-06-24
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18SOMO | SOTOMAYOR HOUSES/MONTEFIORE BEHAVIOR HC - PSYCH CENTER | 1 | DESIGN | 2018-01-02 | 2018-06-30 | 2018-01-02 | 2018-06-30
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18SOMO | SOTOMAYOR HOUSES/MONTEFIORE BEHAVIOR HC - PSYCH CENTER | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18SOMO | SOTOMAYOR HOUSES/MONTEFIORE BEHAVIOR HC - PSYCH CENTER | 3 | CONSTRUCTION | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18SOMO | SOTOMAYOR HOUSES/MONTEFIORE BEHAVIOR HC - PSYCH CENTER | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-28 | 2020-06-24 | 2018-12-28 | 2019-12-27
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18SOMO | SOTOMAYOR HOUSES/MONTEFIORE BEHAVIOR HC - PSYCH CENTER | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-28 | 2020-06-24 | 2019-12-28 | 2020-06-24
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18SVCC | Soundview CC Cornerstone Program - Computer Technology | 1 | DESIGN | 2018-01-02 | 2018-06-30 | 2018-01-02 | 2018-06-30
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18SVCC | Soundview CC Cornerstone Program - Computer Technology | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18SVCC | Soundview CC Cornerstone Program - Computer Technology | 3 | CONSTRUCTION | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18SVCC | Soundview CC Cornerstone Program - Computer Technology | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-28 | 2020-06-24 | 2018-12-28 | 2019-12-27
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18SVCC | Soundview CC Cornerstone Program - Computer Technology | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-28 | 2020-06-24 | 2019-12-28 | 2020-06-24
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18TCCK | THROGGS NECK COMMUNITY C ENTER KITCHEN UPDATE | 1 | DESIGN | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18TCCK | THROGGS NECK COMMUNITY C ENTER KITCHEN UPDATE | 2 | BID AWARD AND REGISTER CONTRCT | 2018-12-28 | 2019-06-25 | 2018-12-28 | 2019-06-25
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18TCCK | THROGGS NECK COMMUNITY C ENTER KITCHEN UPDATE | 3 | CONSTRUCTION | 2019-06-26 | 2020-06-24 | 2019-06-26 | 2020-06-24
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18TCCK | THROGGS NECK COMMUNITY C ENTER KITCHEN UPDATE | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-06-25 | 2020-12-21 | 2019-06-26 | 2020-06-24
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18TCCK | THROGGS NECK COMMUNITY C ENTER KITCHEN UPDATE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-06-25 | 2020-12-21 | 2020-06-25 | 2020-12-21
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18TCCL | THROGGS NECK COMMUNITY CENTER LIGHTING | 1 | DESIGN | 2018-07-01 | 2018-12-27 | 2018-02-09 | 2018-08-07
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18TCCL | THROGGS NECK COMMUNITY CENTER LIGHTING | 2 | BID AWARD AND REGISTER CONTRCT | 2018-12-28 | 2019-06-25 | 2018-08-08 | 2018-12-11
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18TCCL | THROGGS NECK COMMUNITY CENTER LIGHTING | 3 | CONSTRUCTION | 2019-06-26 | 2020-06-24 | 2018-12-12 | 2020-06-03
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18TCCL | THROGGS NECK COMMUNITY CENTER LIGHTING | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-06-25 | 2020-12-21 | 2018-12-12 | 2020-06-03
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18TCCL | THROGGS NECK COMMUNITY CENTER LIGHTING | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-06-25 | 2020-12-21 | 2020-06-04 | 2020-11-30
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18TCCR | Claremont Consolidated Security Enhancements | 1 | DESIGN | 2018-01-02 | 2018-06-30 | 2018-01-02 | 2018-06-30
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18TCCR | Claremont Consolidated Security Enhancements | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18TCCR | Claremont Consolidated Security Enhancements | 3 | CONSTRUCTION | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18TCCR | Claremont Consolidated Security Enhancements | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-28 | 2020-06-24 | 2018-12-28 | 2019-12-27
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18TCCR | Claremont Consolidated Security Enhancements | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-28 | 2020-06-24 | 2019-12-28 | 2020-06-24
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18TNCR | THROGGS NECK COMMUNITY - ROOF RENOVATIONS | 1 | DESIGN | 2017-10-15 | 2018-04-12 | 2017-10-15 | 2018-04-12
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18TNCR | THROGGS NECK COMMUNITY - ROOF RENOVATIONS | 2 | BID AWARD AND REGISTER CONTRCT | 2018-04-13 | 2018-10-09 | 2018-04-13 | 2018-10-09
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18TNCR | THROGGS NECK COMMUNITY - ROOF RENOVATIONS | 3 | CONSTRUCTION | 2018-10-10 | 2019-10-09 | 2018-10-10 | 2019-10-09
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18TNCR | THROGGS NECK COMMUNITY - ROOF RENOVATIONS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-10-10 | 2020-04-06 | 2018-10-10 | 2019-10-09
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18TNCR | THROGGS NECK COMMUNITY - ROOF RENOVATIONS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-10-10 | 2020-04-06 | 2019-10-10 | 2020-04-06
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19ADEL | ADAMS HOUSES ELEVATOR REPLACEMENT | 1 | DESIGN | 2019-06-01 | 2019-11-27 | 2019-02-15 | 2019-08-13
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19ADEL | ADAMS HOUSES ELEVATOR REPLACEMENT | 2 | BID AWARD AND REGISTER CONTRCT | 2019-11-28 | 2020-04-20 | 2019-08-14 | 2020-01-05
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19ADEL | ADAMS HOUSES ELEVATOR REPLACEMENT | 3 | CONSTRUCTION | 2020-04-21 | 2021-04-20 | 2020-01-06 | 2021-01-04
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19ADEL | ADAMS HOUSES ELEVATOR REPLACEMENT | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-04-21 | 2021-10-17 | 2020-01-06 | 2021-01-04
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19ADEL | ADAMS HOUSES ELEVATOR REPLACEMENT | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-04-21 | 2021-10-17 | 2021-01-05 | 2021-07-03
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19BESC | BETANCES SENIOR CENTER COURTYARD RENOVATIONS | 1 | DEVELOP SCOPE | 2019-01-15 | 2019-04-14 | 2019-01-15 | 2019-04-14
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19BESC | BETANCES SENIOR CENTER COURTYARD RENOVATIONS | 2 | PRELIMINARY DESIGN | 2019-04-15 | 2019-08-12 | 2019-04-15 | 2019-08-12
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19BESC | BETANCES SENIOR CENTER COURTYARD RENOVATIONS | 3 | FINAL DESIGN | 2019-08-13 | 2020-02-08 | 2019-08-13 | 2020-02-08
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19BESC | BETANCES SENIOR CENTER COURTYARD RENOVATIONS | 4 | BID AWARD AND REGISTER CONTRCT | 2020-02-09 | 2020-05-08 | 2020-02-09 | 2020-05-08
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19BESC | BETANCES SENIOR CENTER COURTYARD RENOVATIONS | 5 | CONSTRUCTION TO 25% | 2020-05-09 | 2020-09-05 | 2020-05-09 | 2020-09-05
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19BESC | BETANCES SENIOR CENTER COURTYARD RENOVATIONS | 6 | CONSTRUCTION TO 50% | 2020-09-06 | 2021-01-03 | 2020-09-06 | 2021-01-03
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19BESC | BETANCES SENIOR CENTER COURTYARD RENOVATIONS | 7 | CONSTRUCTION TO 75% | 2021-01-04 | 2021-05-03 | 2021-01-04 | 2021-05-03
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19BESC | BETANCES SENIOR CENTER COURTYARD RENOVATIONS | 8 | ORIGINAL EQUIP & FURNISHING | 2021-05-04 | 2021-08-01 | 2021-05-04 | 2021-08-01
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19BESC | BETANCES SENIOR CENTER COURTYARD RENOVATIONS | 9 | SUBSTANTIAL COMPLETION | 2021-08-02 | 2021-09-30 | 2021-08-02 | 2021-09-30
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19BESC | BETANCES SENIOR CENTER COURTYARD RENOVATIONS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-10-01 | 2021-10-30 | 2021-10-01 | 2021-10-30
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19BHSC | BAILEY HOUSES SECURITY CAMERAS | 1 | DESIGN | 2019-03-18 | 2019-09-13 | 2019-03-18 | 2019-09-13
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19BHSC | BAILEY HOUSES SECURITY CAMERAS | 2 | BID AWARD AND REGISTER CONTRCT | 2019-09-14 | 2020-03-11 | 2019-09-14 | 2020-03-11
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19BHSC | BAILEY HOUSES SECURITY CAMERAS | 3 | CONSTRUCTION | 2020-03-12 | 2021-03-11 | 2020-03-12 | 2021-03-11
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19BHSC | BAILEY HOUSES SECURITY CAMERAS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-12 | 2021-09-07 | 2020-03-12 | 2021-03-11
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19BHSC | BAILEY HOUSES SECURITY CAMERAS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-12 | 2021-09-07 | 2021-03-12 | 2021-09-07
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19BPWS | BUTLER HOUSES PLAYGROUND WATER SPRAYS | 1 | DESIGN | 2019-01-15 | 2019-07-13 | 2019-01-15 | 2019-07-13
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19BPWS | BUTLER HOUSES PLAYGROUND WATER SPRAYS | 2 | BID AWARD AND REGISTER CONTRCT | 2019-07-14 | 2020-01-09 | 2019-07-14 | 2020-01-09
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19BPWS | BUTLER HOUSES PLAYGROUND WATER SPRAYS | 3 | CONSTRUCTION | 2020-01-10 | 2021-01-08 | 2020-01-10 | 2021-01-08
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19BPWS | BUTLER HOUSES PLAYGROUND WATER SPRAYS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-01-09 | 2021-07-07 | 2020-01-10 | 2021-01-08
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19BPWS | BUTLER HOUSES PLAYGROUND WATER SPRAYS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-01-09 | 2021-07-07 | 2021-01-09 | 2021-07-07
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19BRSC | BRONX RIVER SENIOR CENTER KITCHEN RENOVATIONS | 1 | DESIGN | 2018-10-30 | 2019-04-27 | 2018-10-30 | 2019-04-27
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19BRSC | BRONX RIVER SENIOR CENTER KITCHEN RENOVATIONS | 2 | BID AWARD AND REGISTER CONTRCT | 2019-04-28 | 2019-10-24 | 2019-04-28 | 2019-10-24
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19BRSC | BRONX RIVER SENIOR CENTER KITCHEN RENOVATIONS | 3 | CONSTRUCTION | 2019-10-25 | 2020-10-23 | 2019-10-25 | 2020-10-23
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19BRSC | BRONX RIVER SENIOR CENTER KITCHEN RENOVATIONS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-10-24 | 2021-04-21 | 2019-10-25 | 2020-10-23
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19BRSC | BRONX RIVER SENIOR CENTER KITCHEN RENOVATIONS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-10-24 | 2021-04-21 | 2020-10-24 | 2021-04-21
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19CAGR | CASTLE HILL HOUSES GAS RISER REPLACEMENTS | 1 | DESIGN | 2019-07-01 | 2020-06-30 | 2019-03-15 | 2020-03-14
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19CAGR | CASTLE HILL HOUSES GAS RISER REPLACEMENTS | 2 | BID AWARD AND REGISTER CONTRCT | 2020-07-01 | 2020-12-23 | 2020-03-15 | 2020-09-06
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19CAGR | CASTLE HILL HOUSES GAS RISER REPLACEMENTS | 3 | CONSTRUCTION | 2020-12-24 | 2022-06-15 | 2020-09-07 | 2022-02-27
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19CAGR | CASTLE HILL HOUSES GAS RISER REPLACEMENTS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-06-16 | 2022-09-15 | 2020-09-07 | 2022-02-27
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19CAGR | CASTLE HILL HOUSES GAS RISER REPLACEMENTS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-06-16 | 2022-09-15 | 2022-02-28 | 2022-05-30
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19CASC | EAST 152ND-COURTLANDT AVENUE SECURITY CAMERAS | 1 | DESIGN | 2018-01-02 | 2018-06-30 | 2018-01-02 | 2018-06-30
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19CASC | EAST 152ND-COURTLANDT AVENUE SECURITY CAMERAS | 2 | BID AWARD AND REGISTER CONTRCT | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19CASC | EAST 152ND-COURTLANDT AVENUE SECURITY CAMERAS | 3 | CONSTRUCTION | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19CASC | EAST 152ND-COURTLANDT AVENUE SECURITY CAMERAS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-28 | 2020-06-24 | 2018-12-28 | 2019-12-27
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19CASC | EAST 152ND-COURTLANDT AVENUE SECURITY CAMERAS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-12-28 | 2020-06-24 | 2019-12-28 | 2020-06-24
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19CMHP | MOORE HOUSES PLAYGROUND | 1 | DESIGN | 2019-01-15 | 2019-07-13 | 2019-01-15 | 2019-07-13
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19CMHP | MOORE HOUSES PLAYGROUND | 2 | BID AWARD AND REGISTER CONTRCT | 2019-07-14 | 2020-01-09 | 2019-07-14 | 2020-01-09
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19CMHP | MOORE HOUSES PLAYGROUND | 3 | CONSTRUCTION | 2020-01-10 | 2021-01-08 | 2020-01-10 | 2021-01-08
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19CMHP | MOORE HOUSES PLAYGROUND | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-01-09 | 2021-07-07 | 2020-01-10 | 2021-01-08
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19CMHP | MOORE HOUSES PLAYGROUND | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-01-09 | 2021-07-07 | 2021-01-09 | 2021-07-07
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19MARE | MORRISANIA AIR RIGHTS ELEVATOR REPLACEMENT AT 3135 PARK AVE | 1 | DESIGN | 2019-02-15 | 2019-08-13 | 2019-02-15 | 2019-08-13
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19MARE | MORRISANIA AIR RIGHTS ELEVATOR REPLACEMENT AT 3135 PARK AVE | 2 | BID AWARD AND REGISTER CONTRCT | 2019-08-14 | 2020-02-09 | 2019-08-14 | 2020-02-09
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19MARE | MORRISANIA AIR RIGHTS ELEVATOR REPLACEMENT AT 3135 PARK AVE | 3 | CONSTRUCTION | 2020-02-10 | 2021-02-08 | 2020-02-10 | 2021-02-08
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19MARE | MORRISANIA AIR RIGHTS ELEVATOR REPLACEMENT AT 3135 PARK AVE | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-02-09 | 2021-08-07 | 2020-02-10 | 2021-02-08
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19MARE | MORRISANIA AIR RIGHTS ELEVATOR REPLACEMENT AT 3135 PARK AVE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-02-09 | 2021-08-07 | 2021-02-09 | 2021-08-07
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19MHSE | MARBLE HILL SECURITY ENHANCEMENTS | 1 | DESIGN | 2019-03-18 | 2019-09-13 | 2019-03-18 | 2019-09-13
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19MHSE | MARBLE HILL SECURITY ENHANCEMENTS | 2 | BID AWARD AND REGISTER CONTRCT | 2019-09-14 | 2020-03-11 | 2019-09-14 | 2020-03-11
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19MHSE | MARBLE HILL SECURITY ENHANCEMENTS | 3 | CONSTRUCTION | 2020-03-12 | 2021-03-11 | 2020-03-12 | 2021-03-11
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19MHSE | MARBLE HILL SECURITY ENHANCEMENTS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-12 | 2021-09-07 | 2020-03-12 | 2021-03-11
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19MHSE | MARBLE HILL SECURITY ENHANCEMENTS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-12 | 2021-09-07 | 2021-03-12 | 2021-09-07
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19MHSP | MARBLE HILL PARKING LOT SECURITY POLES | 1 | DESIGN | 2019-03-18 | 2019-09-13 | 2019-03-18 | 2019-09-13
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19MHSP | MARBLE HILL PARKING LOT SECURITY POLES | 2 | BID AWARD AND REGISTER CONTRCT | 2019-09-14 | 2020-03-11 | 2019-09-14 | 2020-03-11
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19MHSP | MARBLE HILL PARKING LOT SECURITY POLES | 3 | CONSTRUCTION | 2020-03-12 | 2021-03-11 | 2020-03-12 | 2021-03-11
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19MHSP | MARBLE HILL PARKING LOT SECURITY POLES | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-12 | 2021-09-07 | 2020-03-12 | 2021-03-11
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19MHSP | MARBLE HILL PARKING LOT SECURITY POLES | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-12 | 2021-09-07 | 2021-03-12 | 2021-09-07
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19PHBC | PATTERSON HOUSES BASKETBALL COURT UPGRADE | 1 | DESIGN | 2019-01-15 | 2019-07-13 | 2019-01-15 | 2019-07-13
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19PHBC | PATTERSON HOUSES BASKETBALL COURT UPGRADE | 2 | BID AWARD AND REGISTER CONTRCT | 2019-07-14 | 2020-01-09 | 2019-07-14 | 2020-01-09
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19PHBC | PATTERSON HOUSES BASKETBALL COURT UPGRADE | 3 | CONSTRUCTION | 2020-01-10 | 2021-01-08 | 2020-01-10 | 2021-01-08
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19PHBC | PATTERSON HOUSES BASKETBALL COURT UPGRADE | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-01-09 | 2021-07-07 | 2020-01-10 | 2021-01-08
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19PHBC | PATTERSON HOUSES BASKETBALL COURT UPGRADE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-01-09 | 2021-07-07 | 2021-01-09 | 2021-07-07
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19UNSC | 1865 UNIVERSITY AVE- SECURITY CAMERAS | 1 | DESIGN | 2019-04-15 | 2019-10-11 | 2019-04-15 | 2019-10-11
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19UNSC | 1865 UNIVERSITY AVE- SECURITY CAMERAS | 2 | BID AWARD AND REGISTER CONTRCT | 2019-10-12 | 2020-04-08 | 2019-10-12 | 2020-04-08
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19UNSC | 1865 UNIVERSITY AVE- SECURITY CAMERAS | 3 | CONSTRUCTION | 2020-04-09 | 2021-04-08 | 2020-04-09 | 2021-04-08
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19UNSC | 1865 UNIVERSITY AVE- SECURITY CAMERAS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-04-09 | 2021-10-05 | 2020-04-09 | 2021-04-08
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19UNSC | 1865 UNIVERSITY AVE- SECURITY CAMERAS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-04-09 | 2021-10-05 | 2021-04-09 | 2021-10-05
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20EGCC | EASTCHESTER GARDENS COMMUNITY CENTER UPGRADE | 1 | DESIGN | 2020-09-01 | 2021-02-27 | 2020-09-01 | 2021-02-27
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20EGCC | EASTCHESTER GARDENS COMMUNITY CENTER UPGRADE | 2 | BID AWARD AND REGISTER CONTRCT | 2021-02-28 | 2021-08-26 | 2021-02-28 | 2021-08-26
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20EGCC | EASTCHESTER GARDENS COMMUNITY CENTER UPGRADE | 3 | CONSTRUCTION | 2021-08-27 | 2022-08-26 | 2021-08-27 | 2022-08-26
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20EGCC | EASTCHESTER GARDENS COMMUNITY CENTER UPGRADE | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-08-27 | 2023-02-22 | 2021-08-27 | 2022-08-26
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20EGCC | EASTCHESTER GARDENS COMMUNITY CENTER UPGRADE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-08-27 | 2023-02-22 | 2022-08-27 | 2023-02-22
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20GMEL | GOUVERNEUR MORRIS- EXTERIOR LED LIGHTING | 1 | DESIGN | 2019-09-01 | 2020-02-27 | 2019-09-01 | 2020-02-27
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20GMEL | GOUVERNEUR MORRIS- EXTERIOR LED LIGHTING | 2 | BID AWARD AND REGISTER CONTRCT | 2020-02-28 | 2020-08-25 | 2020-02-28 | 2020-08-25
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20GMEL | GOUVERNEUR MORRIS- EXTERIOR LED LIGHTING | 3 | CONSTRUCTION | 2020-08-26 | 2021-08-25 | 2020-08-26 | 2021-08-25
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20GMEL | GOUVERNEUR MORRIS- EXTERIOR LED LIGHTING | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-08-26 | 2022-02-21 | 2020-08-26 | 2021-08-25
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20GMEL | GOUVERNEUR MORRIS- EXTERIOR LED LIGHTING | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-08-26 | 2022-02-21 | 2021-08-26 | 2022-02-21
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20MCIE | JAMES MONROE HOUSES- CAMERAS, INSTALLATION, EQUIPMENT | 1 | DEVELOP SCOPE | 2020-09-01 | 2020-11-29 | 2020-09-01 | 2020-11-29
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20MCIE | JAMES MONROE HOUSES- CAMERAS, INSTALLATION, EQUIPMENT | 2 | PRELIMINARY DESIGN | 2020-11-30 | 2021-03-29 | 2020-11-30 | 2021-03-29
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20MCIE | JAMES MONROE HOUSES- CAMERAS, INSTALLATION, EQUIPMENT | 3 | FINAL DESIGN | 2021-03-30 | 2021-09-25 | 2021-03-30 | 2021-09-25
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20MCIE | JAMES MONROE HOUSES- CAMERAS, INSTALLATION, EQUIPMENT | 4 | BID AWARD AND REGISTER CONTRCT | 2021-09-26 | 2021-12-24 | 2021-09-26 | 2021-12-24
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20MCIE | JAMES MONROE HOUSES- CAMERAS, INSTALLATION, EQUIPMENT | 5 | CONSTRUCTION TO 25% | 2021-12-25 | 2022-04-23 | 2021-12-25 | 2022-04-23
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20MCIE | JAMES MONROE HOUSES- CAMERAS, INSTALLATION, EQUIPMENT | 6 | CONSTRUCTION TO 50% | 2022-04-24 | 2022-08-21 | 2022-04-24 | 2022-08-21
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20MCIE | JAMES MONROE HOUSES- CAMERAS, INSTALLATION, EQUIPMENT | 7 | CONSTRUCTION TO 75% | 2022-08-22 | 2022-12-19 | 2022-08-22 | 2022-12-19
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20MCIE | JAMES MONROE HOUSES- CAMERAS, INSTALLATION, EQUIPMENT | 8 | ORIGINAL EQUIP & FURNISHING | 2022-12-20 | 2023-03-19 | 2022-12-20 | 2023-03-19
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20MCIE | JAMES MONROE HOUSES- CAMERAS, INSTALLATION, EQUIPMENT | 9 | SUBSTANTIAL COMPLETION | 2023-03-20 | 2023-05-18 | 2023-03-20 | 2023-05-18
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20MCIE | JAMES MONROE HOUSES- CAMERAS, INSTALLATION, EQUIPMENT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-05-19 | 2023-06-17 | 2023-05-19 | 2023-06-17
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20MHGR | MONTEREY HOUSES-RENOVATIONS TO PLAYGROUND | 1 | DEVELOP SCOPE | 2020-09-01 | 2020-11-29 | 2020-09-01 | 2020-11-29
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20MHGR | MONTEREY HOUSES-RENOVATIONS TO PLAYGROUND | 2 | PRELIMINARY DESIGN | 2020-11-30 | 2021-03-29 | 2020-11-30 | 2021-03-29
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20MHGR | MONTEREY HOUSES-RENOVATIONS TO PLAYGROUND | 3 | FINAL DESIGN | 2021-03-30 | 2021-09-25 | 2021-03-30 | 2021-09-25
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20MHGR | MONTEREY HOUSES-RENOVATIONS TO PLAYGROUND | 4 | BID AWARD AND REGISTER CONTRCT | 2021-09-26 | 2021-12-24 | 2021-09-26 | 2021-12-24
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20MHGR | MONTEREY HOUSES-RENOVATIONS TO PLAYGROUND | 5 | CONSTRUCTION TO 25% | 2021-12-25 | 2022-04-23 | 2021-12-25 | 2022-04-23
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20MHGR | MONTEREY HOUSES-RENOVATIONS TO PLAYGROUND | 6 | CONSTRUCTION TO 50% | 2022-04-24 | 2022-08-21 | 2022-04-24 | 2022-08-21
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20MHGR | MONTEREY HOUSES-RENOVATIONS TO PLAYGROUND | 7 | CONSTRUCTION TO 75% | 2022-08-22 | 2022-12-19 | 2022-08-22 | 2022-12-19
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20MHGR | MONTEREY HOUSES-RENOVATIONS TO PLAYGROUND | 8 | ORIGINAL EQUIP & FURNISHING | 2022-12-20 | 2023-03-19 | 2022-12-20 | 2023-03-19
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20MHGR | MONTEREY HOUSES-RENOVATIONS TO PLAYGROUND | 9 | SUBSTANTIAL COMPLETION | 2023-03-20 | 2023-05-18 | 2023-03-20 | 2023-05-18
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20MHGR | MONTEREY HOUSES-RENOVATIONS TO PLAYGROUND | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-05-19 | 2023-06-17 | 2023-05-19 | 2023-06-17
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20MLPC | MILLBROOK- LIGHTS, PLAYGROUNDS UPGRADES AND CAMERAS | 1 | DESIGN | 2019-09-01 | 2020-02-27 | 2019-09-01 | 2020-02-27
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20MLPC | MILLBROOK- LIGHTS, PLAYGROUNDS UPGRADES AND CAMERAS | 2 | BID AWARD AND REGISTER CONTRCT | 2020-02-28 | 2020-08-25 | 2020-02-28 | 2020-08-25
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20MLPC | MILLBROOK- LIGHTS, PLAYGROUNDS UPGRADES AND CAMERAS | 3 | CONSTRUCTION | 2020-08-26 | 2021-08-25 | 2020-08-26 | 2021-08-25
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20MLPC | MILLBROOK- LIGHTS, PLAYGROUNDS UPGRADES AND CAMERAS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-08-26 | 2022-02-21 | 2020-08-26 | 2021-08-25
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20MLPC | MILLBROOK- LIGHTS, PLAYGROUNDS UPGRADES AND CAMERAS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-08-26 | 2022-02-21 | 2021-08-26 | 2022-02-21
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20PSCC | PARKSIDE COMMUNITY CENTER UPGRADE | 1 | DEVELOP SCOPE | 2020-09-01 | 2020-11-29 | 2020-09-01 | 2020-11-29
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20PSCC | PARKSIDE COMMUNITY CENTER UPGRADE | 2 | PRELIMINARY DESIGN | 2020-11-30 | 2021-03-29 | 2020-11-30 | 2021-03-29
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20PSCC | PARKSIDE COMMUNITY CENTER UPGRADE | 3 | FINAL DESIGN | 2021-03-30 | 2021-09-25 | 2021-03-30 | 2021-09-25
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20PSCC | PARKSIDE COMMUNITY CENTER UPGRADE | 4 | BID AWARD AND REGISTER CONTRCT | 2021-09-26 | 2021-12-24 | 2021-09-26 | 2021-12-24
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20PSCC | PARKSIDE COMMUNITY CENTER UPGRADE | 5 | CONSTRUCTION TO 25% | 2021-12-25 | 2022-04-23 | 2021-12-25 | 2022-04-23
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20PSCC | PARKSIDE COMMUNITY CENTER UPGRADE | 6 | CONSTRUCTION TO 50% | 2022-04-24 | 2022-08-21 | 2022-04-24 | 2022-08-21
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20PSCC | PARKSIDE COMMUNITY CENTER UPGRADE | 7 | CONSTRUCTION TO 75% | 2022-08-22 | 2022-12-19 | 2022-08-22 | 2022-12-19
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20PSCC | PARKSIDE COMMUNITY CENTER UPGRADE | 8 | ORIGINAL EQUIP & FURNISHING | 2022-12-20 | 2023-03-19 | 2022-12-20 | 2023-03-19
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20PSCC | PARKSIDE COMMUNITY CENTER UPGRADE | 9 | SUBSTANTIAL COMPLETION | 2023-03-20 | 2023-05-18 | 2023-03-20 | 2023-05-18
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20PSCC | PARKSIDE COMMUNITY CENTER UPGRADE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-05-19 | 2023-06-17 | 2023-05-19 | 2023-06-17
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20SEED | SEDGWICK HOUSES ENHANCEMENT ENTRANCE DOORS | 1 | DESIGN | 2019-09-01 | 2020-02-27 | 2019-09-01 | 2020-02-27
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20SEED | SEDGWICK HOUSES ENHANCEMENT ENTRANCE DOORS | 2 | BID AWARD AND REGISTER CONTRCT | 2020-02-28 | 2020-08-25 | 2020-02-28 | 2020-08-25
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20SEED | SEDGWICK HOUSES ENHANCEMENT ENTRANCE DOORS | 3 | CONSTRUCTION | 2020-08-26 | 2021-08-25 | 2020-08-26 | 2021-08-25
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20SEED | SEDGWICK HOUSES ENHANCEMENT ENTRANCE DOORS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-08-26 | 2022-02-21 | 2020-08-26 | 2021-08-25
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20SEED | SEDGWICK HOUSES ENHANCEMENT ENTRANCE DOORS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-08-26 | 2022-02-21 | 2021-08-26 | 2022-02-21
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21EWGR | EDENWALD GAS RISERS #6 | 1 | DESIGN | 2020-07-01 | 2021-06-30 | 2020-07-01 | 2021-06-30
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21EWGR | EDENWALD GAS RISERS #6 | 2 | BID AWARD AND REGISTER CONTRCT | 2021-07-01 | 2021-11-22 | 2021-07-01 | 2021-11-22
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21EWGR | EDENWALD GAS RISERS #6 | 3 | CONSTRUCTION | 2021-11-23 | 2023-06-16 | 2021-11-23 | 2023-06-16
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21EWGR | EDENWALD GAS RISERS #6 | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-06-17 | 2023-09-15 | 2021-11-23 | 2023-06-16
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21EWGR | EDENWALD GAS RISERS #6 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-06-17 | 2023-09-15 | 2023-06-17 | 2023-09-15
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21MHCC | UPGRADE COMMUNITY CENTER MOTT HAVEN | 1 | DESIGN | 2019-09-01 | 2020-02-27 | 2019-09-01 | 2020-02-27
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21MHCC | UPGRADE COMMUNITY CENTER MOTT HAVEN | 2 | BID AWARD AND REGISTER CONTRCT | 2020-02-28 | 2020-08-25 | 2020-02-28 | 2020-08-25
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21MHCC | UPGRADE COMMUNITY CENTER MOTT HAVEN | 3 | CONSTRUCTION | 2020-08-26 | 2021-08-25 | 2020-08-26 | 2021-08-25
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21MHCC | UPGRADE COMMUNITY CENTER MOTT HAVEN | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-08-26 | 2022-02-21 | 2020-08-26 | 2021-08-25
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21MHCC | UPGRADE COMMUNITY CENTER MOTT HAVEN | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-08-26 | 2022-02-21 | 2021-08-26 | 2022-02-21
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21MICC | UPGRADE COMMUNITY CENTER MITCHEL | 1 | DESIGN | 2021-01-02 | 2021-06-30 | 2021-01-02 | 2021-06-30
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21MICC | UPGRADE COMMUNITY CENTER MITCHEL | 2 | BID AWARD AND REGISTER CONTRCT | 2021-07-01 | 2021-12-27 | 2021-07-01 | 2021-12-27
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21MICC | UPGRADE COMMUNITY CENTER MITCHEL | 3 | CONSTRUCTION | 2021-12-28 | 2022-12-27 | 2021-12-28 | 2022-12-27
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21MICC | UPGRADE COMMUNITY CENTER MITCHEL | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-12-28 | 2023-06-25 | 2021-12-28 | 2022-12-27
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21MICC | UPGRADE COMMUNITY CENTER MITCHEL | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-12-28 | 2023-06-25 | 2022-12-28 | 2023-06-25
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21MLCC | UPGRADE COMMUNITY CENTER MILLBROOK | 1 | DESIGN | 2021-09-30 | 2022-03-28 | 2021-09-30 | 2022-03-28
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21MLCC | UPGRADE COMMUNITY CENTER MILLBROOK | 2 | BID AWARD AND REGISTER CONTRCT | 2022-03-29 | 2022-09-24 | 2022-03-29 | 2022-09-24
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21MLCC | UPGRADE COMMUNITY CENTER MILLBROOK | 3 | CONSTRUCTION | 2022-09-25 | 2023-09-24 | 2022-09-25 | 2023-09-24
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21MLCC | UPGRADE COMMUNITY CENTER MILLBROOK | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-25 | 2024-03-22 | 2022-09-25 | 2023-09-24
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21MLCC | UPGRADE COMMUNITY CENTER MILLBROOK | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-25 | 2024-03-22 | 2023-09-25 | 2024-03-22
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21PHCC | UPGRADE COMMUNITY CENTER PATTERSON | 1 | DESIGN | 2021-09-30 | 2022-03-28 | 2021-09-30 | 2022-03-28
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21PHCC | UPGRADE COMMUNITY CENTER PATTERSON | 2 | BID AWARD AND REGISTER CONTRCT | 2022-03-29 | 2022-09-24 | 2022-03-29 | 2022-09-24
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21PHCC | UPGRADE COMMUNITY CENTER PATTERSON | 3 | CONSTRUCTION | 2022-09-25 | 2023-09-24 | 2022-09-25 | 2023-09-24
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21PHCC | UPGRADE COMMUNITY CENTER PATTERSON | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-25 | 2024-03-22 | 2022-09-25 | 2023-09-24
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21PHCC | UPGRADE COMMUNITY CENTER PATTERSON | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-25 | 2024-03-22 | 2023-09-25 | 2024-03-22
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM24CHBR | CASTLE HILL BATHROOMS | 1 | DESIGN | 2024-06-30 | 2025-12-30 | 2024-06-30 | 2025-12-30
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM24CHBR | CASTLE HILL BATHROOMS | 2 | BID AWARD AND REGISTER CONTRCT | 2025-12-31 | 2026-05-25 | 2025-12-31 | 2026-05-25
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM24CHBR | CASTLE HILL BATHROOMS | 3 | CONSTRUCTION | 2026-05-26 | 2027-12-16 | 2026-05-26 | 2027-12-16
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM24CHBR | CASTLE HILL BATHROOMS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2027-12-17 | 2028-03-16 | 2026-05-26 | 2027-12-16
20201123 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM24CHBR | CASTLE HILL BATHROOMS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2027-12-17 | 2028-03-16 | 2027-12-17 | 2028-03-16
20201123 | BRONX | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82BERGN | BERGEN BUILDING RENOVATION - 1932 ARTHUR AVE., BRONX, NY | 1 | DESIGN | 2019-01-20 | 2019-07-18 | 2019-01-20 | 2019-07-18
20201123 | BRONX | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82BERGN | BERGEN BUILDING RENOVATION - 1932 ARTHUR AVE., BRONX, NY | 2 | CONSTRUCTION | 2019-07-19 | 2020-01-14 | 2019-07-19 | 2020-01-14
20201123 | BRONX | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82GLEEB | BUILDING RENOVATION - 2527 GLEBE AVE, BRONX, NY | 1 | DESIGN | 2019-01-10 | 2019-07-08 | 2019-01-10 | 2019-07-08
20201123 | BRONX | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82GLEEB | BUILDING RENOVATION - 2527 GLEBE AVE, BRONX, NY | 2 | CONSTRUCTION | 2019-07-09 | 2020-07-12 | 2019-07-09 | 2020-07-12
20201123 | BRONX | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82GLEEB | BUILDING RENOVATION - 2527 GLEBE AVE, BRONX, NY | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-07-13 | 2021-01-08 | 2020-07-13 | 2025-12-20
20201123 | BRONX | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82MORHC | Morrisania Health Center interior renovation | 1 | DESIGN | 2020-01-01 | 2021-05-24 | 2019-11-02 | 2021-03-25
20201123 | BRONX | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82MORHC | Morrisania Health Center interior renovation | 2 | CONSTRUCTION | 2021-05-25 | 2026-05-23 | 2021-03-26 | 2026-03-24
20201123 | BRONX | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82MORHC | Morrisania Health Center interior renovation | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2026-05-24 | 2026-05-23 | 2026-03-25 | 2026-06-22
20201123 | BRONX | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82MORHC | Morrisania Health Center interior renovation | 4 | DEVELOP SCOPE | 2026-05-24 | 2026-05-23 | 2026-03-25 | 2026-06-22
20201123 | BRONX | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82MORHC | Morrisania Health Center interior renovation | 5 | PRELIMINARY DESIGN | 2026-05-24 | 2026-05-23 | 2026-03-25 | 2026-06-22
20201123 | BRONX | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82MORHC | Morrisania Health Center interior renovation | 6 | FINAL DESIGN | 2026-05-24 | 2026-05-23 | 2026-03-25 | 2026-06-22
20201123 | BRONX | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82MORHC | Morrisania Health Center interior renovation | 7 | BID AWARD AND REGISTER CONTRCT | 2026-05-24 | 2026-05-23 | 2026-03-25 | 2026-06-22
20201123 | BRONX | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82MORHC | Morrisania Health Center interior renovation | 8 | CONSTRUCTION TO 25% | 2026-05-24 | 2026-05-23 | 2026-03-25 | 2026-06-22
20201123 | BRONX | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82MORHC | Morrisania Health Center interior renovation | 9 | CONSTRUCTION TO 50% | 2026-05-24 | 2026-05-23 | 2026-03-25 | 2026-06-22
20201123 | BRONX | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82MORHC | Morrisania Health Center interior renovation | 10 | CONSTRUCTION TO 75% | 2026-05-24 | 2026-05-23 | 2026-03-25 | 2026-06-22
20201123 | BRONX | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82MORHC | Morrisania Health Center interior renovation | 11 | ORIGINAL EQUIP & FURNISHING | 2026-05-24 | 2026-05-23 | 2026-03-25 | 2026-06-22
20201123 | BRONX | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82MORHC | Morrisania Health Center interior renovation | 12 | SUBSTANTIAL COMPLETION | 2026-05-24 | 2026-05-23 | 2026-03-25 | 2026-06-22
20201123 | BRONX | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82MORHC | Morrisania Health Center interior renovation | 13 | PUNCHLIST COMPLETE, JOB CLOSED | 2026-05-24 | 2026-06-22 | 2026-03-25 | 2026-06-22
20201123 | BRONX | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82ZERGA | LEASE SPACE RENOVATION - 1235 ZEREGA AVENUE, BRONX, NY | 1 | DESIGN | 2019-03-10 | 2019-09-05 | 2019-03-10 | 2019-09-05
20201123 | BRONX | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82ZERGA | LEASE SPACE RENOVATION - 1235 ZEREGA AVENUE, BRONX, NY | 2 | CONSTRUCTION | 2019-09-06 | 2020-09-09 | 2019-09-06 | 2020-09-09
20201123 | BRONX | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82ZERGA | LEASE SPACE RENOVATION - 1235 ZEREGA AVENUE, BRONX, NY | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-10 | 2021-03-08 | 2020-09-10 | 2021-03-08
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 02201801 | JMC: BUILDING #4 RENOVATIONS | 1 | DESIGN | 2018-08-11 | 2019-07-01 | 2023-08-11 | 2024-06-30
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 02201801 | JMC: BUILDING #4 RENOVATIONS | 2 | CONSTRUCTION | 2019-07-02 | 2020-06-30 | 2023-08-11 | 2024-06-30
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 02201801 | JMC: BUILDING #4 RENOVATIONS | 3 | CONSTRUCTION | 2019-07-02 | 2020-06-30 | 2024-07-01 | 2025-06-30
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 02201802 | JACOBI: CONSTRUCT PLAYGROUND FOR THE PEDIATRIC DEPT | 1 | DESIGN | 2018-02-10 | 2018-12-31 | 2018-02-10 | 2018-12-31
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 02201802 | JACOBI: CONSTRUCT PLAYGROUND FOR THE PEDIATRIC DEPT | 2 | CONSTRUCTION | 2019-01-01 | 2019-12-31 | 2018-02-10 | 2018-12-31
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 02201802 | JACOBI: CONSTRUCT PLAYGROUND FOR THE PEDIATRIC DEPT | 3 | CONSTRUCTION | 2019-01-01 | 2019-12-31 | 2019-01-01 | 2019-12-31
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 02201802 | JACOBI: CONSTRUCT PLAYGROUND FOR THE PEDIATRIC DEPT | 4 | DESIGN | 2019-01-01 | 2019-12-31 | 2020-01-01 | 2021-05-24
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 02201802 | JACOBI: CONSTRUCT PLAYGROUND FOR THE PEDIATRIC DEPT | 5 | CONSTRUCTION | 2019-01-01 | 2019-12-31 | 2021-05-25 | 2023-05-24
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 02201802 | JACOBI: CONSTRUCT PLAYGROUND FOR THE PEDIATRIC DEPT | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-01-01 | 2019-12-31 | 2023-05-25 | 2023-08-22
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 20201501 | BELVIS: PEDIATRIC SUITE MODERNIZATION | 1 | DESIGN | 2019-07-07 | 2020-01-02 | 2021-07-30 | 2022-01-25
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 20201501 | BELVIS: PEDIATRIC SUITE MODERNIZATION | 2 | CONSTRUCTION | 2020-01-03 | 2020-06-30 | 2022-01-26 | 2022-07-24
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 20201801 | BELVIS: REPLACEMENT OF MAIN ENTRANCE DOORS | 2 | CONSTRUCTION | 2020-01-03 | 2020-06-30 | 2020-01-03 | 2020-06-30
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 21200603 | JACOBI: CENTRALIZE REPRODUCTIVE HEALTH SERVICES | 1 | DESIGN | 2007-07-12 | 2008-05-31 | 2007-07-12 | 2008-05-31
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 21200603 | JACOBI: CENTRALIZE REPRODUCTIVE HEALTH SERVICES | 2 | CONSTRUCTION | 2008-06-01 | 2009-05-31 | 2007-07-12 | 2008-05-31
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 21200603 | JACOBI: CENTRALIZE REPRODUCTIVE HEALTH SERVICES | 3 | CONSTRUCTION | 2008-06-01 | 2009-05-31 | 2008-06-01 | 2022-05-31
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 21201601 | JACOBI: LOCAL LAW 11 COMPLIANCE | 1 | DESIGN | 2019-08-11 | 2020-06-30 | 2019-08-11 | 2020-06-30
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 21201601 | JACOBI: LOCAL LAW 11 COMPLIANCE | 2 | CONSTRUCTION | 2020-07-01 | 2021-06-30 | 2019-08-11 | 2020-06-30
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 21201601 | JACOBI: LOCAL LAW 11 COMPLIANCE | 3 | CONSTRUCTION | 2020-07-01 | 2021-06-30 | 2020-07-01 | 2021-06-30
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 21201601 | JACOBI: LOCAL LAW 11 COMPLIANCE | 4 | DESIGN | 2020-07-01 | 2021-06-30 | 2021-07-01 | 2022-11-22
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 21201601 | JACOBI: LOCAL LAW 11 COMPLIANCE | 5 | CONSTRUCTION | 2020-07-01 | 2021-06-30 | 2022-11-23 | 2024-11-21
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 21201601 | JACOBI: LOCAL LAW 11 COMPLIANCE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-07-01 | 2021-06-30 | 2024-11-22 | 2025-02-19
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 21201703 | JMC: INSTALL A SECONDARY WATER DISINFECTION SYSTEM-BLGS 1&6 | 2 | CONSTRUCTION | 2019-01-02 | 2019-06-30 | 2019-01-02 | 2019-06-30
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 21201704 | JMC: REHABILITATE MAIN LOBBY CEILING IN BUILDING 6 | 1 | DESIGN | 2019-06-27 | 2019-12-23 | 2019-06-27 | 2019-12-23
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 21201704 | JMC: REHABILITATE MAIN LOBBY CEILING IN BUILDING 6 | 2 | CONSTRUCTION | 2019-12-24 | 2020-06-20 | 2019-12-24 | 2022-06-20
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 21201804 | Replace MCC Feeders & Associated Wiring and Conduit | 2 | CONSTRUCTION | 2020-02-22 | 2023-02-20 | 2020-02-22 | 2023-02-20
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 21201804 | Replace MCC Feeders & Associated Wiring and Conduit | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-02-21 | 2023-05-21 | 2023-02-21 | 2023-05-21
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 21201901 | JMC: ELECTRICAL UPGRADE FOR MAIN KITCHEN | 1 | DESIGN | 2018-07-06 | 2019-01-01 | 2018-07-06 | 2019-01-01
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 21201901 | JMC: ELECTRICAL UPGRADE FOR MAIN KITCHEN | 2 | CONSTRUCTION | 2019-01-02 | 2019-06-30 | 2019-01-02 | 2021-06-30
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 21202004 | JAC: Wellness Gym | 1 | DESIGN | 2020-01-03 | 2021-05-26 | 2020-01-03 | 2021-05-26
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 21202004 | JAC: Wellness Gym | 2 | CONSTRUCTION | 2021-05-27 | 2023-05-26 | 2021-05-27 | 2023-05-26
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 21202004 | JAC: Wellness Gym | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-05-27 | 2023-08-24 | 2023-05-27 | 2023-08-24
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 21202101 | HVAC SYSTEM LAB UPGRADE | 1 | DESIGN | 2021-02-01 | 2022-06-25 | 2021-02-01 | 2022-06-25
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 21202101 | HVAC SYSTEM LAB UPGRADE | 2 | CONSTRUCTION | 2022-06-26 | 2025-06-24 | 2022-06-26 | 2025-06-24
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 21202101 | HVAC SYSTEM LAB UPGRADE | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-06-25 | 2025-09-22 | 2025-06-25 | 2025-09-22
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 24201502 | NCB: OB/GYN NURSING UNIT UPGRADE | 1 | DESIGN | 2013-12-21 | 2014-06-18 | 2013-12-21 | 2014-06-18
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 24201502 | NCB: OB/GYN NURSING UNIT UPGRADE | 2 | CONSTRUCTION | 2014-06-19 | 2014-12-15 | 2014-06-19 | 2021-12-15
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 24201610 | RENOVATE TREMONT HEALTH CLINIC | 1 | DESIGN | 2015-12-07 | 2016-06-03 | 2015-12-07 | 2016-06-03
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 24201610 | RENOVATE TREMONT HEALTH CLINIC | 2 | CONSTRUCTION | 2016-06-04 | 2016-11-30 | 2022-06-04 | 2027-12-05
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 24201901 | NCB: FACADE REHABILITATION & WINDOW REPLACEMENT | 1 | DESIGN | 2020-08-10 | 2021-06-30 | 2020-08-10 | 2021-06-30
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 24201901 | NCB: FACADE REHABILITATION & WINDOW REPLACEMENT | 2 | CONSTRUCTION | 2021-07-01 | 2022-06-30 | 2020-08-10 | 2021-06-30
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 24201901 | NCB: FACADE REHABILITATION & WINDOW REPLACEMENT | 3 | CONSTRUCTION | 2021-07-01 | 2022-06-30 | 2021-07-01 | 2022-06-30
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 24201920 | NCB: REPLACE DISHWASHER | 1 | DESIGN | 2021-02-01 | 2022-06-25 | 2021-02-01 | 2022-06-25
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 24201920 | NCB: REPLACE DISHWASHER | 2 | CONSTRUCTION | 2022-06-26 | 2025-06-24 | 2022-06-26 | 2025-06-24
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 24201920 | NCB: REPLACE DISHWASHER | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-06-25 | 2025-09-22 | 2025-06-25 | 2025-09-22
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 24202001 | NORTH CENTRAL BRONX HOSPITAL - ELEVATOR UPGRADE | 1 | DESIGN | 2020-04-20 | 2021-09-11 | 2020-04-20 | 2021-09-11
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 24202001 | NORTH CENTRAL BRONX HOSPITAL - ELEVATOR UPGRADE | 2 | CONSTRUCTION | 2021-09-12 | 2023-09-11 | 2021-09-12 | 2023-09-11
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 24202001 | NORTH CENTRAL BRONX HOSPITAL - ELEVATOR UPGRADE | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-12 | 2023-12-10 | 2023-09-12 | 2023-12-10
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25201262 | LINCOLN: REPLACE LINEAR ACCELERATOR | 1 | DESIGN | 2018-08-11 | 2019-07-01 | 2018-08-11 | 2019-07-01
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25201262 | LINCOLN: REPLACE LINEAR ACCELERATOR | 2 | CONSTRUCTION | 2019-07-02 | 2020-06-30 | 2018-08-11 | 2019-07-01
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25201262 | LINCOLN: REPLACE LINEAR ACCELERATOR | 3 | CONSTRUCTION | 2019-07-02 | 2020-06-30 | 2019-07-02 | 2022-06-30
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25201401 | LINCOLN: RENOVATE ADOLESCENT CLINIC | 1 | DESIGN | 2019-07-07 | 2020-01-02 | 2020-07-07 | 2020-10-07
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25201401 | LINCOLN: RENOVATE ADOLESCENT CLINIC | 2 | CONSTRUCTION | 2020-01-03 | 2020-06-30 | 2020-10-08 | 2021-07-30
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25201601 | LINCOLN: COOLING TOWER REPLACEMENT | 1 | DESIGN | 2018-08-11 | 2019-07-01 | 2018-08-11 | 2019-07-01
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25201601 | LINCOLN: COOLING TOWER REPLACEMENT | 2 | CONSTRUCTION | 2019-07-02 | 2020-06-30 | 2018-08-11 | 2019-07-01
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25201601 | LINCOLN: COOLING TOWER REPLACEMENT | 3 | CONSTRUCTION | 2019-07-02 | 2020-06-30 | 2019-07-02 | 2022-06-30
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25201602 | LINCOLN: REPLACE UNDERGROUND FUEL TANKS | 1 | DESIGN | 2019-08-11 | 2020-06-30 | 2019-08-11 | 2020-06-30
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25201602 | LINCOLN: REPLACE UNDERGROUND FUEL TANKS | 2 | CONSTRUCTION | 2020-07-01 | 2021-06-30 | 2019-08-11 | 2020-06-30
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25201602 | LINCOLN: REPLACE UNDERGROUND FUEL TANKS | 3 | CONSTRUCTION | 2020-07-01 | 2021-06-30 | 2020-07-01 | 2021-10-30
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25201604 | LINCOLN: EXTERIOR FACADE RESTORATION - LL11 COMPLIANCE | 1 | DESIGN | 2019-06-27 | 2019-12-23 | 2019-06-27 | 2019-12-23
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25201604 | LINCOLN: EXTERIOR FACADE RESTORATION - LL11 COMPLIANCE | 2 | CONSTRUCTION | 2019-12-24 | 2020-06-20 | 2019-12-24 | 2020-06-20
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25201701 | LINCOLN: EMERGENCY PANEL UPGRADE | 1 | DESIGN | 2019-08-11 | 2020-06-30 | 2019-08-11 | 2020-06-30
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25201701 | LINCOLN: EMERGENCY PANEL UPGRADE | 2 | CONSTRUCTION | 2020-07-01 | 2021-06-30 | 2019-08-11 | 2020-06-30
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25201701 | LINCOLN: EMERGENCY PANEL UPGRADE | 3 | CONSTRUCTION | 2020-07-01 | 2021-06-30 | 2020-07-01 | 2021-06-30
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25201805 | LINCOLN: REHABILITATE ELECTRICAL DISTRIBUTION SYSTEM | 2 | CONSTRUCTION | 2019-01-02 | 2019-06-30 | 2019-01-02 | 2019-06-30
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25201806 | LINCOLN: REPLACEMENT OF GENERATORS B1 AND B2 & 6 RADIATORS | 1 | DESIGN | 2020-07-06 | 2021-01-01 | 2020-07-06 | 2021-01-01
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25201806 | LINCOLN: REPLACEMENT OF GENERATORS B1 AND B2 & 6 RADIATORS | 2 | CONSTRUCTION | 2021-01-02 | 2021-06-30 | 2021-01-02 | 2021-06-30
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25201807 | LINCOLN: UPGRADE ELEVATORS 18 & 19 | 1 | DESIGN | 2019-07-07 | 2020-01-02 | 2019-07-07 | 2020-01-02
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25201807 | LINCOLN: UPGRADE ELEVATORS 18 & 19 | 2 | CONSTRUCTION | 2020-01-03 | 2020-06-30 | 2020-01-03 | 2020-06-30
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25201901 | LINCOLN: RETAIL PHARMACY RENOVATION | 1 | DESIGN | 2019-07-07 | 2020-01-02 | 2019-07-07 | 2020-01-02
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25201901 | LINCOLN: RETAIL PHARMACY RENOVATION | 2 | CONSTRUCTION | 2020-01-03 | 2020-06-30 | 2020-01-03 | 2022-06-30
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25201942 | LINCOLN: PURCHASE MRI & CONSTRUCT SUITE | 1 | DESIGN | 2021-02-01 | 2022-06-25 | 2021-02-01 | 2022-06-25
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25201942 | LINCOLN: PURCHASE MRI & CONSTRUCT SUITE | 2 | CONSTRUCTION | 2022-06-26 | 2025-06-24 | 2022-06-26 | 2025-06-24
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25201942 | LINCOLN: PURCHASE MRI & CONSTRUCT SUITE | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-06-25 | 2025-09-22 | 2025-06-25 | 2025-09-22
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25202001 | LIN: CONSTRUCT INPATIENT PHARMACY VAULT | 1 | DESIGN | 2020-09-30 | 2022-02-21 | 2020-03-30 | 2021-08-21
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25202001 | LIN: CONSTRUCT INPATIENT PHARMACY VAULT | 2 | CONSTRUCTION | 2022-02-22 | 2025-02-20 | 2021-08-22 | 2024-08-20
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25202001 | LIN: CONSTRUCT INPATIENT PHARMACY VAULT | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-02-21 | 2025-05-21 | 2024-08-21 | 2024-11-18
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25202002 | LINCOLN MEDICAL CENTER - DEVELOP A BRIDGE CLINIC | 1 | DESIGN | 2021-04-20 | 2022-09-11 | 2021-04-20 | 2022-09-11
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25202002 | LINCOLN MEDICAL CENTER - DEVELOP A BRIDGE CLINIC | 2 | CONSTRUCTION | 2022-09-12 | 2024-09-10 | 2022-09-12 | 2024-09-10
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25202002 | LINCOLN MEDICAL CENTER - DEVELOP A BRIDGE CLINIC | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-09-11 | 2024-12-09 | 2024-09-11 | 2024-12-09
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25202003 | LINCOLN: INSTALLATION OF ENTRANCE TURNSTILES | 1 | DESIGN | 2021-02-01 | 2022-06-25 | 2021-02-01 | 2022-06-25
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25202003 | LINCOLN: INSTALLATION OF ENTRANCE TURNSTILES | 2 | CONSTRUCTION | 2022-06-26 | 2025-06-24 | 2022-06-26 | 2025-06-24
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25202003 | LINCOLN: INSTALLATION OF ENTRANCE TURNSTILES | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-06-25 | 2025-09-22 | 2025-06-25 | 2025-09-22
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 42201301 | MORRISANIA: RENOVATE DENTAL SUITE | 1 | DESIGN | 2019-07-07 | 2020-01-02 | 2019-07-07 | 2020-01-02
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 42201301 | MORRISANIA: RENOVATE DENTAL SUITE | 2 | CONSTRUCTION | 2020-01-03 | 2020-06-30 | 2020-01-03 | 2020-06-30
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 42201515 | MORRISANIA: RENOVATE WOMEN'S HEALTH SERVICES - RADIOLOGY | 1 | DESIGN | 2015-01-06 | 2015-07-04 | 2015-01-06 | 2015-07-04
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 42201515 | MORRISANIA: RENOVATE WOMEN'S HEALTH SERVICES - RADIOLOGY | 2 | CONSTRUCTION | 2015-07-05 | 2015-12-31 | 2015-07-05 | 2020-12-31
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 42201901 | MORRISANIA: EXTERIOR STRUCTURAL RESTORATIONS | 1 | DESIGN | 2018-08-11 | 2019-07-01 | 2018-08-11 | 2019-07-01
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 42201901 | MORRISANIA: EXTERIOR STRUCTURAL RESTORATIONS | 2 | CONSTRUCTION | 2019-07-02 | 2020-06-30 | 2018-08-11 | 2019-07-01
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 42201901 | MORRISANIA: EXTERIOR STRUCTURAL RESTORATIONS | 3 | CONSTRUCTION | 2019-07-02 | 2020-06-30 | 2019-07-02 | 2020-06-30
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | ACEHHC409 | HHC LINCOLN MEDICAL CENTER ENERGY UPGRADE | 1 | DESIGN | 2019-08-11 | 2020-06-30 | 2019-08-11 | 2020-06-30
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | ACEHHC409 | HHC LINCOLN MEDICAL CENTER ENERGY UPGRADE | 2 | CONSTRUCTION | 2020-07-01 | 2021-06-30 | 2020-07-01 | 2021-06-30
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | ACEHHC606 | JMC ENERGY CONSERVATION MEASURES | 1 | DESIGN | 2019-08-11 | 2020-06-30 | 2019-08-11 | 2020-06-30
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | ACEHHC606 | JMC ENERGY CONSERVATION MEASURES | 2 | CONSTRUCTION | 2020-07-01 | 2021-06-30 | 2019-08-11 | 2020-06-30
20201123 | BRONX | 819 | HEALTH AND HOSPITALS CORP | ACEHHC606 | JMC ENERGY CONSERVATION MEASURES | 3 | CONSTRUCTION | 2020-07-01 | 2021-06-30 | 2020-07-01 | 2023-06-30
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-590 | Jerome Park Gate House #7 Sluice Gate and Operator Replacmnt | 1 | DEVELOP SCOPE | 2022-06-01 | 2022-08-29 | 2022-06-01 | 2022-08-29
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-590 | Jerome Park Gate House #7 Sluice Gate and Operator Replacmnt | 2 | PRELIMINARY DESIGN | 2022-08-30 | 2022-12-27 | 2022-08-30 | 2022-12-27
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-590 | Jerome Park Gate House #7 Sluice Gate and Operator Replacmnt | 3 | FINAL DESIGN | 2022-12-28 | 2023-06-25 | 2022-12-28 | 2023-06-25
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-590 | Jerome Park Gate House #7 Sluice Gate and Operator Replacmnt | 4 | BID AWARD AND REGISTER CONTRCT | 2023-06-26 | 2023-09-23 | 2023-06-26 | 2023-09-23
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-590 | Jerome Park Gate House #7 Sluice Gate and Operator Replacmnt | 5 | CONSTRUCTION TO 25% | 2023-09-24 | 2024-01-21 | 2023-09-24 | 2024-01-21
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-590 | Jerome Park Gate House #7 Sluice Gate and Operator Replacmnt | 6 | CONSTRUCTION TO 50% | 2024-01-22 | 2024-05-20 | 2024-01-22 | 2024-05-20
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-590 | Jerome Park Gate House #7 Sluice Gate and Operator Replacmnt | 7 | CONSTRUCTION TO 75% | 2024-05-21 | 2024-09-17 | 2024-05-21 | 2024-09-17
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-590 | Jerome Park Gate House #7 Sluice Gate and Operator Replacmnt | 8 | ORIGINAL EQUIP & FURNISHING | 2024-09-18 | 2024-12-16 | 2024-09-18 | 2024-12-16
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-590 | Jerome Park Gate House #7 Sluice Gate and Operator Replacmnt | 9 | SUBSTANTIAL COMPLETION | 2024-12-17 | 2025-02-14 | 2024-12-17 | 2025-02-14
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-590 | Jerome Park Gate House #7 Sluice Gate and Operator Replacmnt | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-02-15 | 2025-03-16 | 2025-02-15 | 2025-03-16
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-593 | INSTALL. MONO CRANE AND HOIST OF SHUTTERS AT JEROME GATE | 1 | DEVELOP SCOPE | 2019-06-01 | 2019-08-29 | 2020-08-16 | 2020-11-13
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-593 | INSTALL. MONO CRANE AND HOIST OF SHUTTERS AT JEROME GATE | 2 | PRELIMINARY DESIGN | 2019-08-30 | 2019-12-27 | 2020-11-14 | 2021-03-13
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-593 | INSTALL. MONO CRANE AND HOIST OF SHUTTERS AT JEROME GATE | 3 | FINAL DESIGN | 2019-12-28 | 2020-06-24 | 2021-03-14 | 2021-09-09
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-593 | INSTALL. MONO CRANE AND HOIST OF SHUTTERS AT JEROME GATE | 4 | BID AWARD AND REGISTER CONTRCT | 2020-06-25 | 2020-09-22 | 2021-09-10 | 2021-12-08
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-593 | INSTALL. MONO CRANE AND HOIST OF SHUTTERS AT JEROME GATE | 5 | CONSTRUCTION TO 25% | 2020-09-23 | 2021-01-20 | 2021-12-09 | 2022-04-07
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-593 | INSTALL. MONO CRANE AND HOIST OF SHUTTERS AT JEROME GATE | 6 | CONSTRUCTION TO 50% | 2021-01-21 | 2021-05-20 | 2022-04-08 | 2022-08-05
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-593 | INSTALL. MONO CRANE AND HOIST OF SHUTTERS AT JEROME GATE | 7 | CONSTRUCTION TO 75% | 2021-05-21 | 2021-09-17 | 2022-08-06 | 2022-12-03
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-593 | INSTALL. MONO CRANE AND HOIST OF SHUTTERS AT JEROME GATE | 8 | ORIGINAL EQUIP & FURNISHING | 2021-09-18 | 2021-12-16 | 2022-12-04 | 2023-03-03
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-593 | INSTALL. MONO CRANE AND HOIST OF SHUTTERS AT JEROME GATE | 9 | SUBSTANTIAL COMPLETION | 2021-12-17 | 2022-02-14 | 2023-03-04 | 2023-05-02
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-593 | INSTALL. MONO CRANE AND HOIST OF SHUTTERS AT JEROME GATE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-02-15 | 2022-03-16 | 2023-05-03 | 2023-06-01
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-604 | Croton Filtration Optimization | 1 | DEVELOP SCOPE | 2024-06-01 | 2024-08-29 | 2024-06-01 | 2024-08-29
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-604 | Croton Filtration Optimization | 2 | PRELIMINARY DESIGN | 2024-08-30 | 2024-12-27 | 2024-08-30 | 2024-12-27
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-604 | Croton Filtration Optimization | 3 | FINAL DESIGN | 2024-12-28 | 2025-06-25 | 2024-12-28 | 2025-06-25
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-604 | Croton Filtration Optimization | 4 | BID AWARD AND REGISTER CONTRCT | 2025-06-26 | 2025-09-23 | 2025-06-26 | 2025-09-23
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-604 | Croton Filtration Optimization | 5 | CONSTRUCTION TO 25% | 2025-09-24 | 2026-01-21 | 2025-09-24 | 2026-01-21
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-604 | Croton Filtration Optimization | 6 | CONSTRUCTION TO 50% | 2026-01-22 | 2026-05-21 | 2026-01-22 | 2026-05-21
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-604 | Croton Filtration Optimization | 7 | CONSTRUCTION TO 75% | 2026-05-22 | 2026-09-18 | 2026-05-22 | 2026-09-18
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-604 | Croton Filtration Optimization | 8 | ORIGINAL EQUIP & FURNISHING | 2026-09-19 | 2026-12-17 | 2026-09-19 | 2026-12-17
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-604 | Croton Filtration Optimization | 9 | SUBSTANTIAL COMPLETION | 2026-12-18 | 2027-02-15 | 2026-12-18 | 2027-02-15
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-604 | Croton Filtration Optimization | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2027-02-16 | 2027-03-17 | 2027-02-16 | 2027-03-17
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-M&A | MITIGATION AND AMENITIES FOR WTP | 1 | DEVELOP SCOPE | 2003-07-01 | 2103-06-05 | 2003-07-01 | 2103-06-05
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-NCA | NEW CROTON AQUEDUCT | 1 | DEVELOP SCOPE | 2006-10-02 | 2006-12-30 | 2017-01-15 | 2017-10-11
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-NCA | NEW CROTON AQUEDUCT | 2 | PRELIMINARY DESIGN | 2006-12-31 | 2007-04-29 | 2017-10-12 | 2018-10-06
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-NCA | NEW CROTON AQUEDUCT | 3 | FINAL DESIGN | 2007-04-30 | 2007-10-26 | 2018-10-07 | 2020-03-29
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-NCA | NEW CROTON AQUEDUCT | 4 | BID AWARD AND REGISTER CONTRCT | 2007-10-27 | 2008-01-24 | 2020-03-30 | 2020-12-24
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-NCA | NEW CROTON AQUEDUCT | 5 | CONSTRUCTION TO 25% | 2008-01-25 | 2008-05-23 | 2020-12-25 | 2021-12-19
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-NCA | NEW CROTON AQUEDUCT | 6 | CONSTRUCTION TO 50% | 2008-05-24 | 2008-09-20 | 2021-12-20 | 2022-12-14
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-NCA | NEW CROTON AQUEDUCT | 7 | CONSTRUCTION TO 75% | 2008-09-21 | 2009-01-18 | 2022-12-15 | 2023-12-09
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-NCA | NEW CROTON AQUEDUCT | 8 | ORIGINAL EQUIP & FURNISHING | 2009-01-19 | 2009-04-18 | 2023-12-10 | 2024-09-04
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-NCA | NEW CROTON AQUEDUCT | 9 | SUBSTANTIAL COMPLETION | 2009-04-19 | 2009-06-17 | 2024-09-05 | 2025-03-03
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-NCA | NEW CROTON AQUEDUCT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2009-06-18 | 2009-07-17 | 2025-03-04 | 2025-06-01
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-BX-LTP | BRONX RIVER LONG TERM CONTROL PLAN FOR CSO ABATEMENT | 1 | DEVELOP SCOPE | 2018-06-01 | 2019-02-25 | 2018-06-01 | 2019-02-25
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-BX-LTP | BRONX RIVER LONG TERM CONTROL PLAN FOR CSO ABATEMENT | 2 | PRELIMINARY DESIGN | 2019-02-26 | 2020-02-20 | 2019-02-26 | 2020-02-20
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-BX-LTP | BRONX RIVER LONG TERM CONTROL PLAN FOR CSO ABATEMENT | 3 | FINAL DESIGN | 2020-02-21 | 2021-08-13 | 2020-02-21 | 2021-08-13
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-BX-LTP | BRONX RIVER LONG TERM CONTROL PLAN FOR CSO ABATEMENT | 4 | BID AWARD AND REGISTER CONTRCT | 2021-08-14 | 2022-05-10 | 2021-08-14 | 2022-05-10
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-BX-LTP | BRONX RIVER LONG TERM CONTROL PLAN FOR CSO ABATEMENT | 5 | CONSTRUCTION TO 25% | 2022-05-11 | 2023-05-05 | 2022-05-11 | 2023-05-05
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-BX-LTP | BRONX RIVER LONG TERM CONTROL PLAN FOR CSO ABATEMENT | 6 | CONSTRUCTION TO 50% | 2023-05-06 | 2024-04-29 | 2023-05-06 | 2024-04-29
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-BX-LTP | BRONX RIVER LONG TERM CONTROL PLAN FOR CSO ABATEMENT | 7 | CONSTRUCTION TO 75% | 2024-04-30 | 2025-04-24 | 2024-04-30 | 2025-04-24
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-BX-LTP | BRONX RIVER LONG TERM CONTROL PLAN FOR CSO ABATEMENT | 8 | ORIGINAL EQUIP & FURNISHING | 2025-04-25 | 2026-01-19 | 2025-04-25 | 2026-01-19
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-BX-LTP | BRONX RIVER LONG TERM CONTROL PLAN FOR CSO ABATEMENT | 9 | SUBSTANTIAL COMPLETION | 2026-01-20 | 2026-07-18 | 2026-01-20 | 2026-07-18
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-BX-LTP | BRONX RIVER LONG TERM CONTROL PLAN FOR CSO ABATEMENT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2026-07-19 | 2026-10-16 | 2026-07-19 | 2026-10-16
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-ER-WCM | WESTCHESTER CSO MODIFICATIONS | 1 | DEVELOP SCOPE | 2011-06-01 | 2012-02-25 | 2011-06-01 | 2012-02-25
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-ER-WCM | WESTCHESTER CSO MODIFICATIONS | 2 | PRELIMINARY DESIGN | 2012-02-26 | 2013-02-19 | 2012-02-26 | 2013-02-19
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-ER-WCM | WESTCHESTER CSO MODIFICATIONS | 3 | FINAL DESIGN | 2013-02-20 | 2014-08-13 | 2013-02-20 | 2014-08-13
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-ER-WCM | WESTCHESTER CSO MODIFICATIONS | 4 | BID AWARD AND REGISTER CONTRCT | 2014-08-14 | 2015-05-10 | 2014-08-14 | 2015-05-10
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-ER-WCM | WESTCHESTER CSO MODIFICATIONS | 5 | CONSTRUCTION TO 25% | 2015-05-11 | 2016-05-04 | 2015-05-11 | 2016-05-04
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-ER-WCM | WESTCHESTER CSO MODIFICATIONS | 6 | CONSTRUCTION TO 50% | 2016-05-05 | 2017-04-29 | 2016-05-05 | 2017-04-29
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-ER-WCM | WESTCHESTER CSO MODIFICATIONS | 7 | CONSTRUCTION TO 75% | 2017-04-30 | 2018-04-24 | 2017-04-30 | 2018-04-24
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-ER-WCM | WESTCHESTER CSO MODIFICATIONS | 8 | ORIGINAL EQUIP & FURNISHING | 2018-04-25 | 2019-01-19 | 2018-04-25 | 2019-01-19
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-ER-WCM | WESTCHESTER CSO MODIFICATIONS | 9 | SUBSTANTIAL COMPLETION | 2019-01-20 | 2019-07-18 | 2019-01-20 | 2023-07-17
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-ER-WCM | WESTCHESTER CSO MODIFICATIONS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-07-19 | 2019-10-16 | 2023-07-18 | 2023-10-15
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-HR-DF | CSO HUTCHINSON RIVER DISINFECTION FACILITY | 1 | DEVELOP SCOPE | 2015-07-01 | 2016-03-26 | 2015-07-01 | 2016-03-26
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-HR-DF | CSO HUTCHINSON RIVER DISINFECTION FACILITY | 2 | PRELIMINARY DESIGN | 2016-03-27 | 2017-03-21 | 2016-03-27 | 2017-03-21
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-HR-DF | CSO HUTCHINSON RIVER DISINFECTION FACILITY | 3 | FINAL DESIGN | 2017-03-22 | 2018-09-12 | 2017-03-22 | 2018-09-12
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-HR-DF | CSO HUTCHINSON RIVER DISINFECTION FACILITY | 4 | BID AWARD AND REGISTER CONTRCT | 2018-09-13 | 2019-06-09 | 2018-09-13 | 2019-06-09
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-HR-DF | CSO HUTCHINSON RIVER DISINFECTION FACILITY | 5 | CONSTRUCTION TO 25% | 2019-06-10 | 2020-06-03 | 2019-06-10 | 2020-06-03
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-HR-DF | CSO HUTCHINSON RIVER DISINFECTION FACILITY | 6 | CONSTRUCTION TO 50% | 2020-06-04 | 2021-05-29 | 2020-06-04 | 2021-05-29
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-HR-DF | CSO HUTCHINSON RIVER DISINFECTION FACILITY | 7 | CONSTRUCTION TO 75% | 2021-05-30 | 2022-05-24 | 2021-05-30 | 2022-05-24
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-HR-DF | CSO HUTCHINSON RIVER DISINFECTION FACILITY | 8 | ORIGINAL EQUIP & FURNISHING | 2022-05-25 | 2023-02-18 | 2022-05-25 | 2023-02-18
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-HR-DF | CSO HUTCHINSON RIVER DISINFECTION FACILITY | 9 | SUBSTANTIAL COMPLETION | 2023-02-19 | 2027-08-16 | 2023-02-19 | 2027-08-16
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-HR-DF | CSO HUTCHINSON RIVER DISINFECTION FACILITY | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2027-08-17 | 2027-11-14 | 2027-08-17 | 2027-11-14
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-NYCHA | GI - NYCHA GREEN INFRASTRUCTURE AT EDENWALD HOUSES - NO & SO | 2 | PRELIMINARY DESIGN | 2011-12-30 | 2012-04-27 | 2012-06-27 | 2013-06-21
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-NYCHA | GI - NYCHA GREEN INFRASTRUCTURE AT EDENWALD HOUSES - NO & SO | 3 | FINAL DESIGN | 2012-04-28 | 2012-10-24 | 2013-06-22 | 2014-12-13
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-NYCHA | GI - NYCHA GREEN INFRASTRUCTURE AT EDENWALD HOUSES - NO & SO | 4 | BID AWARD AND REGISTER CONTRCT | 2012-10-25 | 2013-01-22 | 2014-12-14 | 2015-09-09
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-NYCHA | GI - NYCHA GREEN INFRASTRUCTURE AT EDENWALD HOUSES - NO & SO | 5 | CONSTRUCTION TO 25% | 2013-01-23 | 2013-05-22 | 2015-09-10 | 2016-09-03
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-NYCHA | GI - NYCHA GREEN INFRASTRUCTURE AT EDENWALD HOUSES - NO & SO | 6 | CONSTRUCTION TO 50% | 2013-05-23 | 2013-09-19 | 2016-09-04 | 2017-08-29
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-NYCHA | GI - NYCHA GREEN INFRASTRUCTURE AT EDENWALD HOUSES - NO & SO | 7 | CONSTRUCTION TO 75% | 2013-09-20 | 2014-01-17 | 2017-08-30 | 2018-08-24
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-NYCHA | GI - NYCHA GREEN INFRASTRUCTURE AT EDENWALD HOUSES - NO & SO | 8 | ORIGINAL EQUIP & FURNISHING | 2014-01-18 | 2014-04-17 | 2018-08-25 | 2019-05-21
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-NYCHA | GI - NYCHA GREEN INFRASTRUCTURE AT EDENWALD HOUSES - NO & SO | 9 | SUBSTANTIAL COMPLETION | 2014-04-18 | 2014-06-16 | 2019-05-22 | 2019-11-17
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-NYCHA | GI - NYCHA GREEN INFRASTRUCTURE AT EDENWALD HOUSES - NO & SO | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-06-17 | 2014-07-16 | 2019-11-18 | 2020-02-15
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HBBA24181 | Replacement of WM Infra on E 188 Street, Bronx | 1 | DEVELOP SCOPE | 2020-11-09 | 2021-08-05 | 2020-11-09 | 2021-08-05
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HBBA24181 | Replacement of WM Infra on E 188 Street, Bronx | 2 | PRELIMINARY DESIGN | 2021-08-06 | 2022-07-31 | 2021-08-06 | 2022-07-31
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HBBA24181 | Replacement of WM Infra on E 188 Street, Bronx | 3 | FINAL DESIGN | 2022-08-01 | 2024-01-22 | 2022-08-01 | 2024-01-22
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HBBA24181 | Replacement of WM Infra on E 188 Street, Bronx | 4 | BID AWARD AND REGISTER CONTRCT | 2024-01-23 | 2024-10-18 | 2024-01-23 | 2024-10-18
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HBBA24181 | Replacement of WM Infra on E 188 Street, Bronx | 5 | CONSTRUCTION TO 25% | 2024-10-19 | 2025-10-13 | 2024-10-19 | 2025-10-13
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HBBA24181 | Replacement of WM Infra on E 188 Street, Bronx | 6 | CONSTRUCTION TO 50% | 2025-10-14 | 2026-10-08 | 2025-10-14 | 2026-10-08
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HBBA24181 | Replacement of WM Infra on E 188 Street, Bronx | 7 | CONSTRUCTION TO 75% | 2026-10-09 | 2027-10-03 | 2026-10-09 | 2027-10-03
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HBBA24181 | Replacement of WM Infra on E 188 Street, Bronx | 8 | ORIGINAL EQUIP & FURNISHING | 2027-10-04 | 2028-06-29 | 2027-10-04 | 2028-06-29
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HBBA24181 | Replacement of WM Infra on E 188 Street, Bronx | 9 | SUBSTANTIAL COMPLETION | 2028-06-30 | 2028-12-26 | 2028-06-30 | 2028-12-26
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HBBA24181 | Replacement of WM Infra on E 188 Street, Bronx | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2028-12-27 | 2029-03-26 | 2028-12-27 | 2029-03-26
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HED-545 | CROTON FILTRATION PLANT | 1 | DEVELOP SCOPE | 2004-09-10 | 2004-12-08 | 2007-07-09 | 2008-04-03
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HED-545 | CROTON FILTRATION PLANT | 2 | PRELIMINARY DESIGN | 2004-12-09 | 2005-04-07 | 2008-04-04 | 2009-03-29
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HED-545 | CROTON FILTRATION PLANT | 3 | FINAL DESIGN | 2005-04-08 | 2005-10-04 | 2009-03-30 | 2010-09-20
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HED-545 | CROTON FILTRATION PLANT | 4 | BID AWARD AND REGISTER CONTRCT | 2005-10-05 | 2006-01-02 | 2010-09-21 | 2011-06-17
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HED-545 | CROTON FILTRATION PLANT | 5 | CONSTRUCTION TO 25% | 2006-01-03 | 2006-05-02 | 2011-06-18 | 2012-06-11
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HED-545 | CROTON FILTRATION PLANT | 6 | CONSTRUCTION TO 50% | 2006-05-03 | 2006-08-30 | 2012-06-12 | 2013-06-06
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HED-545 | CROTON FILTRATION PLANT | 7 | CONSTRUCTION TO 75% | 2006-08-31 | 2006-12-28 | 2013-06-07 | 2014-06-01
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HED-545 | CROTON FILTRATION PLANT | 8 | ORIGINAL EQUIP & FURNISHING | 2006-12-29 | 2007-03-28 | 2014-06-02 | 2015-02-26
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HED-545 | CROTON FILTRATION PLANT | 9 | SUBSTANTIAL COMPLETION | 2007-03-29 | 2007-05-27 | 2015-02-27 | 2023-08-23
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HED-545 | CROTON FILTRATION PLANT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2007-05-28 | 2007-06-26 | 2023-08-24 | 2023-11-21
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HED-581 | Dist WM rplmt in Mace Ave btwn Olinville & Cruger Ave, BX | 1 | DEVELOP SCOPE | 2020-11-09 | 2021-08-05 | 2020-11-09 | 2021-08-05
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HED-581 | Dist WM rplmt in Mace Ave btwn Olinville & Cruger Ave, BX | 2 | PRELIMINARY DESIGN | 2021-08-06 | 2022-07-31 | 2021-08-06 | 2022-07-31
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HED-581 | Dist WM rplmt in Mace Ave btwn Olinville & Cruger Ave, BX | 3 | FINAL DESIGN | 2022-08-01 | 2024-01-22 | 2022-08-01 | 2024-01-22
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HED-581 | Dist WM rplmt in Mace Ave btwn Olinville & Cruger Ave, BX | 4 | BID AWARD AND REGISTER CONTRCT | 2024-01-23 | 2024-10-18 | 2024-01-23 | 2024-10-18
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HED-581 | Dist WM rplmt in Mace Ave btwn Olinville & Cruger Ave, BX | 5 | CONSTRUCTION TO 25% | 2024-10-19 | 2025-10-13 | 2024-10-19 | 2025-10-13
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HED-581 | Dist WM rplmt in Mace Ave btwn Olinville & Cruger Ave, BX | 6 | CONSTRUCTION TO 50% | 2025-10-14 | 2026-10-08 | 2025-10-14 | 2026-10-08
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HED-581 | Dist WM rplmt in Mace Ave btwn Olinville & Cruger Ave, BX | 7 | CONSTRUCTION TO 75% | 2026-10-09 | 2027-10-03 | 2026-10-09 | 2027-10-03
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HED-581 | Dist WM rplmt in Mace Ave btwn Olinville & Cruger Ave, BX | 8 | ORIGINAL EQUIP & FURNISHING | 2027-10-04 | 2028-06-29 | 2027-10-04 | 2028-06-29
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HED-581 | Dist WM rplmt in Mace Ave btwn Olinville & Cruger Ave, BX | 9 | SUBSTANTIAL COMPLETION | 2028-06-30 | 2028-12-26 | 2028-06-30 | 2028-12-26
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HED-581 | Dist WM rplmt in Mace Ave btwn Olinville & Cruger Ave, BX | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2028-12-27 | 2029-03-26 | 2028-12-27 | 2029-03-26
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HED-CROOS | CROTON FILTRATION PLANT - OFF-SITE FACILITIES | 1 | DEVELOP SCOPE | 2004-02-08 | 2004-11-03 | 2008-11-25 | 2009-08-21
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HED-CROOS | CROTON FILTRATION PLANT - OFF-SITE FACILITIES | 2 | PRELIMINARY DESIGN | 2004-11-04 | 2005-10-29 | 2009-08-22 | 2010-08-16
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HED-CROOS | CROTON FILTRATION PLANT - OFF-SITE FACILITIES | 3 | FINAL DESIGN | 2005-10-30 | 2007-04-22 | 2010-08-17 | 2012-02-07
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HED-CROOS | CROTON FILTRATION PLANT - OFF-SITE FACILITIES | 4 | BID AWARD AND REGISTER CONTRCT | 2007-04-23 | 2008-01-17 | 2012-02-08 | 2012-11-03
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HED-CROOS | CROTON FILTRATION PLANT - OFF-SITE FACILITIES | 5 | CONSTRUCTION TO 25% | 2008-01-18 | 2009-01-11 | 2012-11-04 | 2013-10-29
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HED-CROOS | CROTON FILTRATION PLANT - OFF-SITE FACILITIES | 6 | CONSTRUCTION TO 50% | 2009-01-12 | 2010-01-06 | 2013-10-30 | 2014-10-24
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HED-CROOS | CROTON FILTRATION PLANT - OFF-SITE FACILITIES | 7 | CONSTRUCTION TO 75% | 2010-01-07 | 2011-01-01 | 2014-10-25 | 2015-10-19
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HED-CROOS | CROTON FILTRATION PLANT - OFF-SITE FACILITIES | 8 | ORIGINAL EQUIP & FURNISHING | 2011-01-02 | 2011-09-28 | 2015-10-20 | 2016-07-15
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HED-CROOS | CROTON FILTRATION PLANT - OFF-SITE FACILITIES | 9 | SUBSTANTIAL COMPLETION | 2011-09-29 | 2012-03-26 | 2016-07-16 | 2021-01-10
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HED-CROOS | CROTON FILTRATION PLANT - OFF-SITE FACILITIES | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-03-27 | 2012-06-24 | 2021-01-11 | 2023-10-07
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-238-L | REPLACEMENT OF THE DIGESTER @ THE HUNTS POINT WWTP | 1 | DEVELOP SCOPE | 2015-06-30 | 2016-03-25 | 2015-06-30 | 2016-03-25
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-238-L | REPLACEMENT OF THE DIGESTER @ THE HUNTS POINT WWTP | 2 | PRELIMINARY DESIGN | 2016-03-26 | 2017-03-20 | 2016-03-26 | 2017-03-20
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-238-L | REPLACEMENT OF THE DIGESTER @ THE HUNTS POINT WWTP | 3 | FINAL DESIGN | 2017-03-21 | 2018-09-11 | 2017-03-21 | 2018-09-11
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-238-L | REPLACEMENT OF THE DIGESTER @ THE HUNTS POINT WWTP | 4 | BID AWARD AND REGISTER CONTRCT | 2018-09-12 | 2019-06-08 | 2018-09-12 | 2019-06-08
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-238-L | REPLACEMENT OF THE DIGESTER @ THE HUNTS POINT WWTP | 5 | CONSTRUCTION TO 25% | 2019-06-09 | 2020-06-02 | 2019-06-09 | 2020-06-02
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-238-L | REPLACEMENT OF THE DIGESTER @ THE HUNTS POINT WWTP | 6 | CONSTRUCTION TO 50% | 2020-06-03 | 2021-05-28 | 2020-06-03 | 2021-05-28
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-238-L | REPLACEMENT OF THE DIGESTER @ THE HUNTS POINT WWTP | 7 | CONSTRUCTION TO 75% | 2021-05-29 | 2022-05-23 | 2021-05-29 | 2022-05-23
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-238-L | REPLACEMENT OF THE DIGESTER @ THE HUNTS POINT WWTP | 8 | ORIGINAL EQUIP & FURNISHING | 2022-05-24 | 2023-02-17 | 2022-05-24 | 2023-02-17
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-238-L | REPLACEMENT OF THE DIGESTER @ THE HUNTS POINT WWTP | 9 | SUBSTANTIAL COMPLETION | 2023-02-18 | 2023-08-16 | 2023-02-18 | 2023-08-16
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-238-L | REPLACEMENT OF THE DIGESTER @ THE HUNTS POINT WWTP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-08-17 | 2023-11-14 | 2023-08-17 | 2023-11-14
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-252-L | INSTALL (2) MOTOR CONTROL CENTERS (MCCS) @ HUNTS POINT WWTP | 1 | DEVELOP SCOPE | 2019-06-01 | 2019-08-29 | 2019-06-01 | 2019-08-29
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-252-L | INSTALL (2) MOTOR CONTROL CENTERS (MCCS) @ HUNTS POINT WWTP | 2 | PRELIMINARY DESIGN | 2019-08-30 | 2019-12-27 | 2019-08-30 | 2019-12-27
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-252-L | INSTALL (2) MOTOR CONTROL CENTERS (MCCS) @ HUNTS POINT WWTP | 3 | FINAL DESIGN | 2019-12-28 | 2020-06-24 | 2019-12-28 | 2020-06-24
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-252-L | INSTALL (2) MOTOR CONTROL CENTERS (MCCS) @ HUNTS POINT WWTP | 4 | BID AWARD AND REGISTER CONTRCT | 2020-06-25 | 2020-09-22 | 2020-06-25 | 2020-09-22
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-252-L | INSTALL (2) MOTOR CONTROL CENTERS (MCCS) @ HUNTS POINT WWTP | 5 | CONSTRUCTION TO 25% | 2020-09-23 | 2021-01-20 | 2020-09-23 | 2021-01-20
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-252-L | INSTALL (2) MOTOR CONTROL CENTERS (MCCS) @ HUNTS POINT WWTP | 6 | CONSTRUCTION TO 50% | 2021-01-21 | 2021-05-20 | 2021-01-21 | 2021-05-20
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-252-L | INSTALL (2) MOTOR CONTROL CENTERS (MCCS) @ HUNTS POINT WWTP | 7 | CONSTRUCTION TO 75% | 2021-05-21 | 2021-09-17 | 2021-05-21 | 2021-09-17
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-252-L | INSTALL (2) MOTOR CONTROL CENTERS (MCCS) @ HUNTS POINT WWTP | 8 | ORIGINAL EQUIP & FURNISHING | 2021-09-18 | 2021-12-16 | 2021-09-18 | 2021-12-16
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-252-L | INSTALL (2) MOTOR CONTROL CENTERS (MCCS) @ HUNTS POINT WWTP | 9 | SUBSTANTIAL COMPLETION | 2021-12-17 | 2022-02-14 | 2021-12-17 | 2022-02-14
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-252-L | INSTALL (2) MOTOR CONTROL CENTERS (MCCS) @ HUNTS POINT WWTP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-02-15 | 2022-03-16 | 2022-02-15 | 2022-03-16
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-254-L | TRC - CONS OF DECHLORINATION FACILITY @ HUNTS POINT WWTP | 1 | PRE-CONSTRUCTION MOBILIZATION | 2020-02-01 | 2021-01-25 | 2020-02-01 | 2021-01-25
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-254-L | TRC - CONS OF DECHLORINATION FACILITY @ HUNTS POINT WWTP | 2 | ON-SITE CONSTRUCTION MANAGEMEN | 2021-01-26 | 2026-12-25 | 2021-01-26 | 2026-12-25
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-254-L | TRC - CONS OF DECHLORINATION FACILITY @ HUNTS POINT WWTP | 3 | POST-CONSTRUCTION CLOSE-OUT | 2026-12-26 | 2027-12-20 | 2026-12-26 | 2027-12-20
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-3R | RECONSTRUCTION OF EXISTING DIGESTERS AT HUNTS POINT WPCP | 1 | DEVELOP SCOPE | 2008-06-15 | 2009-03-11 | 2010-07-15 | 2011-04-10
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-3R | RECONSTRUCTION OF EXISTING DIGESTERS AT HUNTS POINT WPCP | 2 | PRELIMINARY DESIGN | 2009-03-12 | 2010-03-06 | 2011-04-11 | 2012-04-04
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-3R | RECONSTRUCTION OF EXISTING DIGESTERS AT HUNTS POINT WPCP | 3 | FINAL DESIGN | 2010-03-07 | 2011-08-28 | 2012-04-05 | 2013-09-26
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-3R | RECONSTRUCTION OF EXISTING DIGESTERS AT HUNTS POINT WPCP | 4 | BID AWARD AND REGISTER CONTRCT | 2011-08-29 | 2012-05-24 | 2013-09-27 | 2014-06-23
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-3R | RECONSTRUCTION OF EXISTING DIGESTERS AT HUNTS POINT WPCP | 5 | CONSTRUCTION TO 25% | 2012-05-25 | 2013-05-19 | 2014-06-24 | 2015-06-18
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-3R | RECONSTRUCTION OF EXISTING DIGESTERS AT HUNTS POINT WPCP | 6 | CONSTRUCTION TO 50% | 2013-05-20 | 2014-05-14 | 2015-06-19 | 2016-06-12
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-3R | RECONSTRUCTION OF EXISTING DIGESTERS AT HUNTS POINT WPCP | 7 | CONSTRUCTION TO 75% | 2014-05-15 | 2015-05-09 | 2016-06-13 | 2017-06-07
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-3R | RECONSTRUCTION OF EXISTING DIGESTERS AT HUNTS POINT WPCP | 8 | ORIGINAL EQUIP & FURNISHING | 2015-05-10 | 2016-02-03 | 2017-06-08 | 2018-03-04
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-3R | RECONSTRUCTION OF EXISTING DIGESTERS AT HUNTS POINT WPCP | 9 | SUBSTANTIAL COMPLETION | 2016-02-04 | 2016-08-01 | 2018-03-05 | 2022-08-30
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-3R | RECONSTRUCTION OF EXISTING DIGESTERS AT HUNTS POINT WPCP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-08-02 | 2016-10-30 | 2022-08-31 | 2022-11-28
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | JRAQ-REH | JEROME RESERVOIR & AQUEDUCT REHABILITATION | 1 | DEVELOP SCOPE | 2019-06-01 | 2020-02-25 | 2017-06-01 | 2018-02-25
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | JRAQ-REH | JEROME RESERVOIR & AQUEDUCT REHABILITATION | 2 | PRELIMINARY DESIGN | 2020-02-26 | 2021-02-19 | 2018-02-26 | 2019-02-20
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | JRAQ-REH | JEROME RESERVOIR & AQUEDUCT REHABILITATION | 3 | FINAL DESIGN | 2021-02-20 | 2022-08-13 | 2019-02-21 | 2020-08-13
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | JRAQ-REH | JEROME RESERVOIR & AQUEDUCT REHABILITATION | 4 | BID AWARD AND REGISTER CONTRCT | 2022-08-14 | 2023-05-10 | 2020-08-14 | 2021-05-10
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | JRAQ-REH | JEROME RESERVOIR & AQUEDUCT REHABILITATION | 5 | CONSTRUCTION TO 25% | 2023-05-11 | 2024-05-04 | 2021-05-11 | 2022-05-05
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | JRAQ-REH | JEROME RESERVOIR & AQUEDUCT REHABILITATION | 6 | CONSTRUCTION TO 50% | 2024-05-05 | 2025-04-29 | 2022-05-06 | 2023-04-30
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | JRAQ-REH | JEROME RESERVOIR & AQUEDUCT REHABILITATION | 7 | CONSTRUCTION TO 75% | 2025-04-30 | 2026-04-24 | 2023-05-01 | 2024-04-24
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | JRAQ-REH | JEROME RESERVOIR & AQUEDUCT REHABILITATION | 8 | ORIGINAL EQUIP & FURNISHING | 2026-04-25 | 2027-01-19 | 2024-04-25 | 2025-01-19
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | JRAQ-REH | JEROME RESERVOIR & AQUEDUCT REHABILITATION | 9 | SUBSTANTIAL COMPLETION | 2027-01-20 | 2027-07-18 | 2025-01-20 | 2025-07-18
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | JRAQ-REH | JEROME RESERVOIR & AQUEDUCT REHABILITATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2027-07-19 | 2027-10-16 | 2025-07-19 | 2025-10-16
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-125 | PUMPING STATION AT CO-OP CITY NORTH AND SOUTH | 1 | DEVELOP SCOPE | 2002-12-15 | 2003-09-10 | 2014-01-01 | 2014-03-31
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-125 | PUMPING STATION AT CO-OP CITY NORTH AND SOUTH | 2 | PRELIMINARY DESIGN | 2003-09-11 | 2004-09-04 | 2014-04-01 | 2014-07-29
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-125 | PUMPING STATION AT CO-OP CITY NORTH AND SOUTH | 3 | FINAL DESIGN | 2004-09-05 | 2006-02-26 | 2014-07-30 | 2015-01-25
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-125 | PUMPING STATION AT CO-OP CITY NORTH AND SOUTH | 4 | BID AWARD AND REGISTER CONTRCT | 2006-02-27 | 2006-11-23 | 2015-01-26 | 2015-04-25
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-125 | PUMPING STATION AT CO-OP CITY NORTH AND SOUTH | 5 | CONSTRUCTION TO 25% | 2006-11-24 | 2007-11-18 | 2015-04-26 | 2015-08-23
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-125 | PUMPING STATION AT CO-OP CITY NORTH AND SOUTH | 6 | CONSTRUCTION TO 50% | 2007-11-19 | 2008-11-12 | 2015-08-24 | 2015-12-21
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-125 | PUMPING STATION AT CO-OP CITY NORTH AND SOUTH | 7 | CONSTRUCTION TO 75% | 2008-11-13 | 2009-11-07 | 2015-12-22 | 2016-04-19
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-125 | PUMPING STATION AT CO-OP CITY NORTH AND SOUTH | 8 | ORIGINAL EQUIP & FURNISHING | 2009-11-08 | 2010-08-04 | 2016-04-20 | 2016-07-18
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-125 | PUMPING STATION AT CO-OP CITY NORTH AND SOUTH | 9 | SUBSTANTIAL COMPLETION | 2010-08-05 | 2011-01-31 | 2016-07-19 | 2016-09-16
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-125 | PUMPING STATION AT CO-OP CITY NORTH AND SOUTH | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2011-02-01 | 2011-05-01 | 2016-09-17 | 2016-10-16
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-236A | Throgs Neck Pumping Station Rehabilitation and Improvements | 1 | DEVELOP SCOPE | 2019-07-01 | 2020-03-26 | 2019-07-01 | 2020-03-26
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-236A | Throgs Neck Pumping Station Rehabilitation and Improvements | 2 | PRELIMINARY DESIGN | 2020-03-27 | 2021-03-21 | 2020-03-27 | 2021-03-21
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-236A | Throgs Neck Pumping Station Rehabilitation and Improvements | 3 | FINAL DESIGN | 2021-03-22 | 2022-09-12 | 2021-03-22 | 2022-09-12
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-236A | Throgs Neck Pumping Station Rehabilitation and Improvements | 4 | BID AWARD AND REGISTER CONTRCT | 2022-09-13 | 2023-06-09 | 2022-09-13 | 2023-06-09
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-236A | Throgs Neck Pumping Station Rehabilitation and Improvements | 5 | CONSTRUCTION TO 25% | 2023-06-10 | 2024-06-03 | 2023-06-10 | 2024-06-03
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-236A | Throgs Neck Pumping Station Rehabilitation and Improvements | 6 | CONSTRUCTION TO 50% | 2024-06-04 | 2025-05-29 | 2024-06-04 | 2025-05-29
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-236A | Throgs Neck Pumping Station Rehabilitation and Improvements | 7 | CONSTRUCTION TO 75% | 2025-05-30 | 2026-05-24 | 2025-05-30 | 2026-05-24
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-236A | Throgs Neck Pumping Station Rehabilitation and Improvements | 8 | ORIGINAL EQUIP & FURNISHING | 2026-05-25 | 2027-02-18 | 2026-05-25 | 2027-02-18
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-236A | Throgs Neck Pumping Station Rehabilitation and Improvements | 9 | SUBSTANTIAL COMPLETION | 2027-02-19 | 2027-08-17 | 2027-02-19 | 2027-08-17
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-236A | Throgs Neck Pumping Station Rehabilitation and Improvements | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2027-08-18 | 2027-11-15 | 2027-08-18 | 2027-11-15
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-288 | 233RD STREET PUMPING STATION | 1 | DEVELOP SCOPE | 2020-06-01 | 2021-11-22 | 2021-06-01 | 2022-02-25
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-288 | 233RD STREET PUMPING STATION | 2 | PRELIMINARY DESIGN | 2021-11-23 | 2022-07-20 | 2022-02-26 | 2023-02-20
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-288 | 233RD STREET PUMPING STATION | 3 | FINAL DESIGN | 2022-07-21 | 2023-03-17 | 2023-02-21 | 2024-08-13
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-288 | 233RD STREET PUMPING STATION | 4 | BID AWARD AND REGISTER CONTRCT | 2023-03-18 | 2023-11-12 | 2024-08-14 | 2025-05-10
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-288 | 233RD STREET PUMPING STATION | 5 | CONSTRUCTION TO 25% | 2023-03-18 | 2023-11-12 | 2025-05-11 | 2026-05-05
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-288 | 233RD STREET PUMPING STATION | 6 | CONSTRUCTION TO 50% | 2023-03-18 | 2023-11-12 | 2026-05-06 | 2027-04-30
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-288 | 233RD STREET PUMPING STATION | 7 | CONSTRUCTION TO 75% | 2023-03-18 | 2023-11-12 | 2027-05-01 | 2028-04-24
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-288 | 233RD STREET PUMPING STATION | 8 | ORIGINAL EQUIP & FURNISHING | 2023-03-18 | 2023-11-12 | 2028-04-25 | 2029-01-19
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-288 | 233RD STREET PUMPING STATION | 9 | SUBSTANTIAL COMPLETION | 2023-03-18 | 2023-11-12 | 2029-01-20 | 2033-07-17
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-288 | 233RD STREET PUMPING STATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-03-18 | 2023-11-12 | 2033-07-18 | 2033-10-15
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-290 | CONNER STREET PUMPING STATION | 1 | DEVELOP SCOPE | 2016-07-01 | 2017-03-27 | 2016-07-01 | 2017-03-27
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-290 | CONNER STREET PUMPING STATION | 2 | PRELIMINARY DESIGN | 2017-03-28 | 2018-03-22 | 2017-03-28 | 2018-03-22
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-290 | CONNER STREET PUMPING STATION | 3 | FINAL DESIGN | 2018-03-23 | 2019-09-13 | 2018-03-23 | 2019-09-13
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-290 | CONNER STREET PUMPING STATION | 4 | BID AWARD AND REGISTER CONTRCT | 2019-09-14 | 2020-06-09 | 2019-09-14 | 2020-06-09
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-290 | CONNER STREET PUMPING STATION | 5 | CONSTRUCTION TO 25% | 2020-06-10 | 2021-06-04 | 2020-06-10 | 2021-06-04
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-290 | CONNER STREET PUMPING STATION | 6 | CONSTRUCTION TO 50% | 2021-06-05 | 2022-05-30 | 2021-06-05 | 2022-05-30
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-290 | CONNER STREET PUMPING STATION | 7 | CONSTRUCTION TO 75% | 2022-05-31 | 2023-05-25 | 2022-05-31 | 2023-05-25
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-290 | CONNER STREET PUMPING STATION | 8 | ORIGINAL EQUIP & FURNISHING | 2023-05-26 | 2024-02-19 | 2023-05-26 | 2024-02-19
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-290 | CONNER STREET PUMPING STATION | 9 | SUBSTANTIAL COMPLETION | 2024-02-20 | 2024-08-17 | 2024-02-20 | 2024-08-17
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-290 | CONNER STREET PUMPING STATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-08-18 | 2024-11-15 | 2024-08-18 | 2024-11-15
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | SEX002272 | Combined SE Replacement in Davidson Avenue. Bronx | 1 | DEVELOP SCOPE | 2021-06-01 | 2022-02-25 | 2021-06-01 | 2022-02-25
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | SEX002272 | Combined SE Replacement in Davidson Avenue. Bronx | 2 | PRELIMINARY DESIGN | 2022-02-26 | 2023-02-20 | 2022-02-26 | 2023-02-20
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | SEX002272 | Combined SE Replacement in Davidson Avenue. Bronx | 3 | FINAL DESIGN | 2023-02-21 | 2024-08-13 | 2023-02-21 | 2024-08-13
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | SEX002272 | Combined SE Replacement in Davidson Avenue. Bronx | 4 | BID AWARD AND REGISTER CONTRCT | 2024-08-14 | 2025-05-10 | 2024-08-14 | 2025-05-10
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | SEX002272 | Combined SE Replacement in Davidson Avenue. Bronx | 5 | CONSTRUCTION TO 25% | 2025-05-11 | 2026-05-05 | 2025-05-11 | 2026-05-05
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | SEX002272 | Combined SE Replacement in Davidson Avenue. Bronx | 6 | CONSTRUCTION TO 50% | 2026-05-06 | 2027-04-30 | 2026-05-06 | 2027-04-30
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | SEX002272 | Combined SE Replacement in Davidson Avenue. Bronx | 7 | CONSTRUCTION TO 75% | 2027-05-01 | 2028-04-24 | 2027-05-01 | 2028-04-24
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | SEX002272 | Combined SE Replacement in Davidson Avenue. Bronx | 8 | ORIGINAL EQUIP & FURNISHING | 2028-04-25 | 2029-01-19 | 2028-04-25 | 2029-01-19
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | SEX002272 | Combined SE Replacement in Davidson Avenue. Bronx | 9 | SUBSTANTIAL COMPLETION | 2029-01-20 | 2029-07-18 | 2029-01-20 | 2029-07-18
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | SEX002272 | Combined SE Replacement in Davidson Avenue. Bronx | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2029-07-19 | 2029-10-16 | 2029-07-19 | 2029-10-16
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | SEX002273 | Replacement of combined sewers in Bruckner Blvd BRONX | 1 | DEVELOP SCOPE | 2019-12-09 | 2020-09-03 | 2019-12-09 | 2020-09-03
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | SEX002273 | Replacement of combined sewers in Bruckner Blvd BRONX | 2 | PRELIMINARY DESIGN | 2020-09-04 | 2021-08-29 | 2020-09-04 | 2021-08-29
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | SEX002273 | Replacement of combined sewers in Bruckner Blvd BRONX | 3 | FINAL DESIGN | 2021-08-30 | 2023-02-20 | 2021-08-30 | 2023-02-20
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | SEX002273 | Replacement of combined sewers in Bruckner Blvd BRONX | 4 | BID AWARD AND REGISTER CONTRCT | 2023-02-21 | 2023-11-17 | 2023-02-21 | 2023-11-17
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | SEX002273 | Replacement of combined sewers in Bruckner Blvd BRONX | 5 | CONSTRUCTION TO 25% | 2023-11-18 | 2024-11-11 | 2023-11-18 | 2024-11-11
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | SEX002273 | Replacement of combined sewers in Bruckner Blvd BRONX | 6 | CONSTRUCTION TO 50% | 2024-11-12 | 2025-11-06 | 2024-11-12 | 2025-11-06
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | SEX002273 | Replacement of combined sewers in Bruckner Blvd BRONX | 7 | CONSTRUCTION TO 75% | 2025-11-07 | 2026-11-01 | 2025-11-07 | 2026-11-01
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | SEX002273 | Replacement of combined sewers in Bruckner Blvd BRONX | 8 | ORIGINAL EQUIP & FURNISHING | 2026-11-02 | 2027-07-29 | 2026-11-02 | 2027-07-29
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | SEX002273 | Replacement of combined sewers in Bruckner Blvd BRONX | 9 | SUBSTANTIAL COMPLETION | 2027-07-30 | 2028-01-25 | 2027-07-30 | 2028-01-25
20201123 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | SEX002273 | Replacement of combined sewers in Bruckner Blvd BRONX | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2028-01-26 | 2028-04-24 | 2028-01-26 | 2028-04-24
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-264L | Bronx 5 Garage Roof Replacement | 1 | DEVELOP SCOPE | 2015-08-25 | 2016-02-20 | 2015-08-25 | 2016-02-20
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-264L | Bronx 5 Garage Roof Replacement | 2 | PRELIMINARY DESIGN | 2016-02-21 | 2017-02-19 | 2016-02-21 | 2017-02-19
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-264L | Bronx 5 Garage Roof Replacement | 3 | FINAL DESIGN | 2017-02-20 | 2018-02-19 | 2017-02-20 | 2018-02-19
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-264L | Bronx 5 Garage Roof Replacement | 4 | BID AWARD AND REGISTER CONTRCT | 2018-02-20 | 2019-02-19 | 2018-02-20 | 2019-02-19
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-264L | Bronx 5 Garage Roof Replacement | 5 | CONSTRUCTION TO 25% | 2019-02-20 | 2020-02-19 | 2019-02-20 | 2020-02-19
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-264L | Bronx 5 Garage Roof Replacement | 6 | CONSTRUCTION TO 50% | 2020-02-20 | 2021-02-18 | 2020-02-20 | 2021-02-18
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-264L | Bronx 5 Garage Roof Replacement | 7 | CONSTRUCTION TO 75% | 2021-02-19 | 2022-02-18 | 2021-02-19 | 2022-02-18
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-264L | Bronx 5 Garage Roof Replacement | 8 | SUBSTANTIAL COMPLETION | 2022-02-19 | 2024-11-14 | 2022-02-19 | 2024-11-14
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-264L | Bronx 5 Garage Roof Replacement | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-06-19 | 2025-03-14 | 2022-06-19 | 2025-03-14
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-332M | BRONX 6/6A GARAGE REHAB | 1 | DEVELOP SCOPE | 2016-07-01 | 2017-06-30 | 2016-07-01 | 2017-06-30
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-332M | BRONX 6/6A GARAGE REHAB | 2 | PRELIMINARY DESIGN | 2017-07-01 | 2018-03-27 | 2017-07-01 | 2018-03-27
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-332M | BRONX 6/6A GARAGE REHAB | 3 | FINAL DESIGN | 2018-03-28 | 2018-12-22 | 2018-03-28 | 2018-12-22
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-332M | BRONX 6/6A GARAGE REHAB | 4 | BID AWARD AND REGISTER CONTRCT | 2018-12-23 | 2019-09-18 | 2018-12-23 | 2019-09-18
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-332M | BRONX 6/6A GARAGE REHAB | 5 | CONSTRUCTION TO 25% | 2019-09-19 | 2020-09-17 | 2019-09-19 | 2020-09-17
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-332M | BRONX 6/6A GARAGE REHAB | 6 | CONSTRUCTION TO 50% | 2020-09-18 | 2022-08-18 | 2020-09-18 | 2022-08-18
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-332M | BRONX 6/6A GARAGE REHAB | 7 | CONSTRUCTION TO 75% | 2022-08-19 | 2024-07-18 | 2022-08-19 | 2024-07-18
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-332M | BRONX 6/6A GARAGE REHAB | 8 | SUBSTANTIAL COMPLETION | 2024-07-19 | 2026-06-18 | 2024-07-19 | 2026-06-18
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-332M | BRONX 6/6A GARAGE REHAB | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2026-06-19 | 2028-05-18 | 2026-06-19 | 2028-05-18
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-424 | Bronx 12 Rehabilitation (Slabs, Roof, Fueling Enclosure) | 1 | DEVELOP SCOPE | 2014-07-01 | 2014-08-14 | 2014-07-01 | 2014-08-14
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-424 | Bronx 12 Rehabilitation (Slabs, Roof, Fueling Enclosure) | 2 | PRELIMINARY DESIGN | 2014-08-15 | 2015-09-18 | 2014-08-15 | 2015-09-18
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-424 | Bronx 12 Rehabilitation (Slabs, Roof, Fueling Enclosure) | 3 | FINAL DESIGN | 2015-09-19 | 2017-05-10 | 2015-09-19 | 2017-05-10
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-424 | Bronx 12 Rehabilitation (Slabs, Roof, Fueling Enclosure) | 4 | BID AWARD AND REGISTER CONTRCT | 2017-05-11 | 2021-06-18 | 2017-05-11 | 2021-06-18
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-424 | Bronx 12 Rehabilitation (Slabs, Roof, Fueling Enclosure) | 5 | CONSTRUCTION TO 25% | 2021-06-19 | 2021-06-18 | 2021-06-19 | 2021-06-18
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-424 | Bronx 12 Rehabilitation (Slabs, Roof, Fueling Enclosure) | 6 | CONSTRUCTION TO 50% | 2021-06-19 | 2021-06-18 | 2021-06-19 | 2021-06-18
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-424 | Bronx 12 Rehabilitation (Slabs, Roof, Fueling Enclosure) | 7 | CONSTRUCTION TO 75% | 2021-06-19 | 2021-06-18 | 2021-06-19 | 2021-06-18
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-424 | Bronx 12 Rehabilitation (Slabs, Roof, Fueling Enclosure) | 8 | SUBSTANTIAL COMPLETION | 2021-06-19 | 2023-08-27 | 2021-06-19 | 2023-08-27
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-424 | Bronx 12 Rehabilitation (Slabs, Roof, Fueling Enclosure) | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-08-28 | 2026-05-23 | 2023-08-28 | 2026-05-23
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-429 | Bronx 3A 1661 West Farms Road Garage Reconstruction | 1 | DEVELOP SCOPE | 2018-08-01 | 2018-11-28 | 2018-08-01 | 2018-11-28
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-429 | Bronx 3A 1661 West Farms Road Garage Reconstruction | 2 | PRELIMINARY DESIGN | 2018-11-29 | 2019-08-05 | 2018-11-29 | 2019-08-05
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-429 | Bronx 3A 1661 West Farms Road Garage Reconstruction | 3 | FINAL DESIGN | 2019-08-06 | 2020-04-11 | 2019-08-06 | 2020-04-11
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-429 | Bronx 3A 1661 West Farms Road Garage Reconstruction | 4 | BID AWARD AND REGISTER CONTRCT | 2020-04-12 | 2021-04-11 | 2020-04-12 | 2021-04-11
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-429 | Bronx 3A 1661 West Farms Road Garage Reconstruction | 5 | CONSTRUCTION TO 25% | 2021-04-12 | 2022-04-11 | 2021-04-12 | 2022-04-11
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-429 | Bronx 3A 1661 West Farms Road Garage Reconstruction | 6 | CONSTRUCTION TO 50% | 2022-04-12 | 2023-04-11 | 2022-04-12 | 2023-04-11
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-429 | Bronx 3A 1661 West Farms Road Garage Reconstruction | 7 | CONSTRUCTION TO 75% | 2023-04-12 | 2024-04-10 | 2023-04-12 | 2024-04-10
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-429 | Bronx 3A 1661 West Farms Road Garage Reconstruction | 8 | SUBSTANTIAL COMPLETION | 2024-04-11 | 2025-04-10 | 2024-04-11 | 2025-04-10
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-429 | Bronx 3A 1661 West Farms Road Garage Reconstruction | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-04-11 | 2026-04-10 | 2025-04-11 | 2026-04-10
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-429D | Bronx 3A 1661 West Farms Road Garage Demolition | 1 | DEVELOP SCOPE | 2019-05-01 | 2019-09-14 | 2019-05-01 | 2019-09-14
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-429D | Bronx 3A 1661 West Farms Road Garage Demolition | 2 | PRELIMINARY DESIGN | 2019-09-15 | 2019-11-13 | 2019-09-15 | 2019-11-13
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-429D | Bronx 3A 1661 West Farms Road Garage Demolition | 3 | FINAL DESIGN | 2019-11-14 | 2020-01-12 | 2019-11-14 | 2020-01-12
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-429D | Bronx 3A 1661 West Farms Road Garage Demolition | 4 | BID AWARD AND REGISTER CONTRCT | 2020-01-13 | 2020-06-30 | 2020-01-13 | 2020-06-30
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-429D | Bronx 3A 1661 West Farms Road Garage Demolition | 5 | CONSTRUCTION TO 25% | 2020-07-01 | 2021-01-16 | 2020-07-01 | 2021-01-16
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-429D | Bronx 3A 1661 West Farms Road Garage Demolition | 6 | CONSTRUCTION TO 50% | 2021-01-17 | 2021-08-04 | 2021-01-17 | 2021-08-04
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-429D | Bronx 3A 1661 West Farms Road Garage Demolition | 7 | CONSTRUCTION TO 75% | 2021-08-05 | 2022-02-20 | 2021-08-05 | 2022-02-20
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-429D | Bronx 3A 1661 West Farms Road Garage Demolition | 8 | SUBSTANTIAL COMPLETION | 2022-02-21 | 2022-09-08 | 2022-02-21 | 2022-09-08
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-429D | Bronx 3A 1661 West Farms Road Garage Demolition | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-09 | 2023-01-06 | 2022-09-09 | 2023-01-06
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-440C | Bronx 9/10/11 South Lot Sidewalk and Driveway Rconstruction | 1 | DEVELOP SCOPE | 2019-12-01 | 2020-01-14 | 2019-12-01 | 2020-01-14
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-440C | Bronx 9/10/11 South Lot Sidewalk and Driveway Rconstruction | 2 | PRELIMINARY DESIGN | 2020-01-15 | 2020-03-14 | 2020-01-15 | 2020-03-14
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-440C | Bronx 9/10/11 South Lot Sidewalk and Driveway Rconstruction | 3 | FINAL DESIGN | 2020-03-15 | 2020-10-13 | 2020-03-15 | 2020-10-13
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-440C | Bronx 9/10/11 South Lot Sidewalk and Driveway Rconstruction | 4 | BID AWARD AND REGISTER CONTRCT | 2020-10-14 | 2021-04-11 | 2020-10-14 | 2021-04-11
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-440C | Bronx 9/10/11 South Lot Sidewalk and Driveway Rconstruction | 5 | CONSTRUCTION TO 25% | 2021-04-12 | 2021-08-09 | 2021-04-12 | 2021-08-09
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-440C | Bronx 9/10/11 South Lot Sidewalk and Driveway Rconstruction | 6 | CONSTRUCTION TO 50% | 2021-08-10 | 2021-12-07 | 2021-08-10 | 2021-12-07
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-440C | Bronx 9/10/11 South Lot Sidewalk and Driveway Rconstruction | 7 | CONSTRUCTION TO 75% | 2021-12-08 | 2022-04-06 | 2021-12-08 | 2022-04-06
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-440C | Bronx 9/10/11 South Lot Sidewalk and Driveway Rconstruction | 8 | SUBSTANTIAL COMPLETION | 2022-04-07 | 2022-09-03 | 2022-04-07 | 2022-09-03
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-440C | Bronx 9/10/11 South Lot Sidewalk and Driveway Rconstruction | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-04 | 2023-06-30 | 2022-09-04 | 2023-06-30
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-464G | Bronx 3 Sec 31 Roof Replacement Washington Ave | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-08-28 | 2017-07-01 | 2017-08-28
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-464G | Bronx 3 Sec 31 Roof Replacement Washington Ave | 2 | PRELIMINARY DESIGN | 2017-08-29 | 2018-01-25 | 2017-08-29 | 2021-10-06
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-464G | Bronx 3 Sec 31 Roof Replacement Washington Ave | 3 | FINAL DESIGN | 2018-01-26 | 2018-06-24 | 2021-10-07 | 2022-03-05
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-464G | Bronx 3 Sec 31 Roof Replacement Washington Ave | 4 | BID AWARD AND REGISTER CONTRCT | 2018-06-25 | 2018-11-21 | 2022-03-06 | 2022-08-02
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-464G | Bronx 3 Sec 31 Roof Replacement Washington Ave | 5 | CONSTRUCTION TO 25% | 2018-11-22 | 2019-04-20 | 2022-08-03 | 2022-12-30
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-464G | Bronx 3 Sec 31 Roof Replacement Washington Ave | 6 | CONSTRUCTION TO 50% | 2019-04-21 | 2019-09-17 | 2022-12-31 | 2023-05-29
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-464G | Bronx 3 Sec 31 Roof Replacement Washington Ave | 7 | CONSTRUCTION TO 75% | 2019-09-18 | 2020-02-14 | 2023-05-30 | 2023-10-26
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-464G | Bronx 3 Sec 31 Roof Replacement Washington Ave | 8 | SUBSTANTIAL COMPLETION | 2020-02-15 | 2020-07-13 | 2023-10-27 | 2025-03-09
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-464G | Bronx 3 Sec 31 Roof Replacement Washington Ave | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-07-14 | 2022-03-05 | 2025-03-10 | 2026-10-30
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | S195-228M | Bronx 2 Salt Shed Rehabilitation | 1 | DEVELOP SCOPE | 2019-11-01 | 2020-01-19 | 2019-11-01 | 2020-01-19
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | S195-228M | Bronx 2 Salt Shed Rehabilitation | 2 | PRELIMINARY DESIGN | 2020-01-20 | 2020-03-09 | 2020-01-20 | 2020-03-09
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | S195-228M | Bronx 2 Salt Shed Rehabilitation | 3 | FINAL DESIGN | 2020-03-10 | 2020-09-01 | 2020-03-10 | 2020-09-01
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | S195-228M | Bronx 2 Salt Shed Rehabilitation | 4 | BID AWARD AND REGISTER CONTRCT | 2020-07-01 | 2020-09-01 | 2020-07-01 | 2020-09-01
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | S195-228M | Bronx 2 Salt Shed Rehabilitation | 5 | CONSTRUCTION TO 25% | 2020-09-02 | 2020-11-30 | 2020-09-02 | 2020-11-30
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | S195-228M | Bronx 2 Salt Shed Rehabilitation | 6 | CONSTRUCTION TO 50% | 2020-12-01 | 2021-02-28 | 2020-12-01 | 2021-02-28
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | S195-228M | Bronx 2 Salt Shed Rehabilitation | 7 | CONSTRUCTION TO 75% | 2021-03-01 | 2021-06-28 | 2021-03-01 | 2021-06-28
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | S195-228M | Bronx 2 Salt Shed Rehabilitation | 8 | SUBSTANTIAL COMPLETION | 2021-06-29 | 2021-11-25 | 2021-06-29 | 2021-11-25
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | S195-228M | Bronx 2 Salt Shed Rehabilitation | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-11-26 | 2022-03-25 | 2021-11-26 | 2022-03-25
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | S248-423 | Bronx 9/10/11 Garage Replacement | 1 | DEVELOP SCOPE | 2015-12-01 | 2017-01-03 | 2015-12-01 | 2017-01-03
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | S248-423 | Bronx 9/10/11 Garage Replacement | 2 | PRELIMINARY DESIGN | 2017-01-04 | 2018-05-18 | 2017-01-04 | 2018-05-18
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | S248-423 | Bronx 9/10/11 Garage Replacement | 3 | FINAL DESIGN | 2018-05-19 | 2019-09-30 | 2018-05-19 | 2020-06-06
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | S248-423 | Bronx 9/10/11 Garage Replacement | 4 | BID AWARD AND REGISTER CONTRCT | 2019-10-01 | 2020-07-01 | 2020-06-07 | 2021-03-08
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | S248-423 | Bronx 9/10/11 Garage Replacement | 5 | CONSTRUCTION TO 25% | 2020-07-02 | 2021-11-13 | 2021-03-09 | 2022-07-21
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | S248-423 | Bronx 9/10/11 Garage Replacement | 6 | CONSTRUCTION TO 50% | 2021-11-14 | 2023-03-28 | 2022-07-22 | 2023-12-03
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | S248-423 | Bronx 9/10/11 Garage Replacement | 7 | CONSTRUCTION TO 75% | 2023-03-29 | 2024-08-09 | 2023-12-04 | 2025-04-16
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | S248-423 | Bronx 9/10/11 Garage Replacement | 8 | SUBSTANTIAL COMPLETION | 2024-08-10 | 2025-12-22 | 2025-04-17 | 2026-08-29
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | S248-423 | Bronx 9/10/11 Garage Replacement | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-12-23 | 2028-09-17 | 2026-08-30 | 2028-09-17
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | SANDBX12C | Hurricane Sandy Bronx 12 Garage Conduit Work | 3 | FINAL DESIGN | 2018-11-28 | 2019-09-03 | 2018-11-28 | 2019-09-03
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | SANDBX12C | Hurricane Sandy Bronx 12 Garage Conduit Work | 4 | BID AWARD AND REGISTER CONTRCT | 2019-09-04 | 2020-06-09 | 2019-09-04 | 2020-06-09
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | SANDBX12C | Hurricane Sandy Bronx 12 Garage Conduit Work | 5 | CONSTRUCTION TO 25% | 2020-06-10 | 2021-03-16 | 2020-06-10 | 2021-03-16
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | SANDBX12C | Hurricane Sandy Bronx 12 Garage Conduit Work | 6 | CONSTRUCTION TO 50% | 2021-03-17 | 2022-01-10 | 2021-03-17 | 2022-01-10
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | SANDBX12C | Hurricane Sandy Bronx 12 Garage Conduit Work | 7 | CONSTRUCTION TO 75% | 2022-01-11 | 2023-04-05 | 2022-01-11 | 2023-04-05
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | SANDBX12C | Hurricane Sandy Bronx 12 Garage Conduit Work | 8 | SUBSTANTIAL COMPLETION | 2023-04-06 | 2024-11-25 | 2023-04-06 | 2024-11-25
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | SANDBX12C | Hurricane Sandy Bronx 12 Garage Conduit Work | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-11-26 | 2027-05-14 | 2024-11-26 | 2027-05-14
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | SANDBX12G | Hurricane Sandy Bronx 12 Garage R/R & Haz Mitigation | 1 | DEVELOP SCOPE | 2015-08-25 | 2015-12-22 | 2015-08-25 | 2015-12-22
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | SANDBX12G | Hurricane Sandy Bronx 12 Garage R/R & Haz Mitigation | 2 | PRELIMINARY DESIGN | 2015-12-23 | 2016-06-19 | 2015-12-23 | 2016-06-19
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | SANDBX12G | Hurricane Sandy Bronx 12 Garage R/R & Haz Mitigation | 3 | FINAL DESIGN | 2016-06-20 | 2017-06-19 | 2016-06-20 | 2017-06-19
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | SANDBX12G | Hurricane Sandy Bronx 12 Garage R/R & Haz Mitigation | 4 | BID AWARD AND REGISTER CONTRCT | 2017-06-20 | 2018-06-19 | 2017-06-20 | 2018-06-19
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | SANDBX12G | Hurricane Sandy Bronx 12 Garage R/R & Haz Mitigation | 5 | CONSTRUCTION TO 25% | 2018-06-20 | 2019-06-19 | 2018-06-20 | 2019-06-19
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | SANDBX12G | Hurricane Sandy Bronx 12 Garage R/R & Haz Mitigation | 6 | CONSTRUCTION TO 50% | 2019-06-20 | 2020-06-18 | 2019-06-20 | 2020-06-18
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | SANDBX12G | Hurricane Sandy Bronx 12 Garage R/R & Haz Mitigation | 7 | CONSTRUCTION TO 75% | 2020-06-19 | 2021-06-18 | 2020-06-19 | 2021-06-18
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | SANDBX12G | Hurricane Sandy Bronx 12 Garage R/R & Haz Mitigation | 8 | SUBSTANTIAL COMPLETION | 2021-06-19 | 2024-03-14 | 2021-06-19 | 2024-03-14
20201123 | BRONX | 827 | DEPARTMENT OF SANITATION | SANDBX12G | Hurricane Sandy Bronx 12 Garage R/R & Haz Mitigation | 9 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-10-17 | 2024-07-12 | 2021-10-17 | 2024-07-12
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | BRX2110 | BOSTON ROAD OVER BRONX RIVER BIN: 2242110 | 1 | DEVELOP SCOPE | 2016-06-30 | 2017-06-29 | 2017-08-30 | 2017-09-19
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | BRX2110 | BOSTON ROAD OVER BRONX RIVER BIN: 2242110 | 2 | DESIGN START | 2017-06-30 | 2021-06-28 | 2019-11-20 | 2021-09-05
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | BRX2110 | BOSTON ROAD OVER BRONX RIVER BIN: 2242110 | 3 | CONSTRUCTION START | 2021-06-29 | 2023-06-28 | 2023-09-03 | 2025-08-03
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | BRX9579 | BOSTON ROAD OVER HUTCHINSON RIVER BIN: 2229579 | 1 | DEVELOP SCOPE | 2016-06-30 | 2017-06-29 | 2014-10-02 | 2014-10-02
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | BRX9579 | BOSTON ROAD OVER HUTCHINSON RIVER BIN: 2229579 | 2 | DESIGN START | 2017-06-30 | 2021-06-28 | 2016-11-28 | 2021-06-16
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | BRX9579 | BOSTON ROAD OVER HUTCHINSON RIVER BIN: 2229579 | 3 | CONSTRUCTION START | 2021-06-29 | 2023-06-28 | 2021-06-17 | 2025-06-02
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | BXECONDEV | FA - BX Council for Economic Devel. - Streetscape Furniture | 1 | DESIGN | 2006-01-01 | 2006-01-20 | 2018-01-01 | 2018-03-31
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | BXECONDEV | FA - BX Council for Economic Devel. - Streetscape Furniture | 2 | BID AWARD AND REGISTER CONTRCT | 2004-07-21 | 2004-08-04 | 2018-04-01 | 2018-07-29
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | BXECONDEV | FA - BX Council for Economic Devel. - Streetscape Furniture | 3 | CONSTRUCTION | 2004-08-05 | 2007-06-30 | 2018-07-30 | 2019-01-25
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | BXECONDEV | FA - BX Council for Economic Devel. - Streetscape Furniture | 4 | ORIGINAL EQUIP & FURNISHING | 2007-07-01 | 2007-06-30 | 2019-01-26 | 2019-04-25
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | BXECONDEV | FA - BX Council for Economic Devel. - Streetscape Furniture | 5 | SUBSTANTIAL COMPLETION | 2007-07-01 | 2007-06-30 | 2019-04-26 | 2019-08-23
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | BXECONDEV | FA - BX Council for Economic Devel. - Streetscape Furniture | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2007-07-01 | 2007-07-05 | 2019-08-24 | 2019-12-21
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | BXECONDEV | FA - BX Council for Economic Devel. - Streetscape Furniture | 7 | CONSTRUCTION TO 75% | 2007-07-01 | 2007-07-05 | 2019-12-22 | 2020-04-19
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | BXECONDEV | FA - BX Council for Economic Devel. - Streetscape Furniture | 8 | ORIGINAL EQUIP & FURNISHING | 2007-07-01 | 2007-07-05 | 2020-04-20 | 2020-07-18
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | BXECONDEV | FA - BX Council for Economic Devel. - Streetscape Furniture | 9 | SUBSTANTIAL COMPLETION | 2007-07-01 | 2007-07-05 | 2020-07-19 | 2020-09-16
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | BXECONDEV | FA - BX Council for Economic Devel. - Streetscape Furniture | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2007-07-01 | 2007-07-05 | 2020-09-17 | 2020-10-16
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | CTYISLBRD | Reconstruction of City Island Access Bridge | 1 | DEVELOP SCOPE | 2019-06-30 | 2020-06-28 | 2017-06-30 | 2018-06-29
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | CTYISLBRD | Reconstruction of City Island Access Bridge | 2 | DESIGN START | 2020-06-29 | 2022-06-28 | 2018-06-30 | 2020-06-28
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | CTYISLBRD | Reconstruction of City Island Access Bridge | 3 | CONSTRUCTION START | 2022-06-29 | 2024-06-27 | 2020-06-29 | 2026-06-30
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA06672 | EAST 174TH ST/SHERIDAN EXPWY AMTRAK BIN# 2066720 | 1 | DEVELOP SCOPE | 2016-07-01 | 2017-06-30 | 0 | 0
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA06672 | EAST 174TH ST/SHERIDAN EXPWY AMTRAK BIN# 2066720 | 2 | DESIGN START | 2017-07-01 | 2021-06-29 | 2017-01-02 | 2017-08-11
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA06672 | EAST 174TH ST/SHERIDAN EXPWY AMTRAK BIN# 2066720 | 3 | CONSTRUCTION START | 2021-06-30 | 2023-06-29 | 2019-06-07 | 2021-03-24
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA06672 | EAST 174TH ST/SHERIDAN EXPWY AMTRAK BIN# 2066720 | 5 | CONSTRUCTION START | 2021-06-30 | 2023-06-29 | 2023-07-19 | 2027-07-18
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA24138 | Pelham Bay Park Equestrian over Amtrak- CSX BIN 2241380 | 1 | DEVELOP SCOPE | 2017-06-30 | 2018-06-29 | 0 | 0
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA24138 | Pelham Bay Park Equestrian over Amtrak- CSX BIN 2241380 | 2 | DESIGN START | 2018-06-30 | 2022-06-28 | 2017-06-30 | 2018-06-29
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA24138 | Pelham Bay Park Equestrian over Amtrak- CSX BIN 2241380 | 3 | CONSTRUCTION START | 2022-06-29 | 2024-06-27 | 2018-06-30 | 2022-06-28
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA24138 | Pelham Bay Park Equestrian over Amtrak- CSX BIN 2241380 | 5 | CONSTRUCTION START | 2022-06-29 | 2024-06-27 | 2022-06-29 | 2024-06-27
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA24180 | East 183rd St over MNRR Har BIN 2241800 | 1 | DEVELOP SCOPE | 2017-06-30 | 2018-06-29 | 0 | 0
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA24180 | East 183rd St over MNRR Har BIN 2241800 | 2 | DESIGN START | 2018-06-30 | 2022-06-28 | 2017-07-01 | 2017-09-06
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA24180 | East 183rd St over MNRR Har BIN 2241800 | 3 | CONSTRUCTION START | 2022-06-29 | 2024-06-27 | 2019-04-25 | 2022-10-29
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA24180 | East 183rd St over MNRR Har BIN 2241800 | 5 | CONSTRUCTION START | 2022-06-29 | 2024-06-27 | 2023-10-01 | 2026-12-30
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA24181 | East 188th St over MNRR Har BIN 2241810 | 1 | DEVELOP SCOPE | 2016-06-30 | 2017-06-29 | 0 | 0
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA24181 | East 188th St over MNRR Har BIN 2241810 | 2 | DESIGN START | 2017-06-30 | 2021-06-28 | 2015-03-20 | 2015-04-03
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA24181 | East 188th St over MNRR Har BIN 2241810 | 3 | CONSTRUCTION START | 2021-06-29 | 2023-06-28 | 2018-10-18 | 2021-01-08
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA24181 | East 188th St over MNRR Har BIN 2241810 | 5 | CONSTRUCTION START | 2021-06-29 | 2023-06-28 | 2021-12-09 | 2025-03-21
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA24245 | EAST 233RD ST/ BRONX RIVER BIN # 2242459 | 1 | DEVELOP SCOPE | 2019-06-30 | 2019-09-27 | 2019-06-30 | 2019-09-27
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA24245 | EAST 233RD ST/ BRONX RIVER BIN # 2242459 | 2 | PRELIMINARY DESIGN | 2019-09-28 | 2020-01-25 | 2019-09-28 | 2020-01-25
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA24245 | EAST 233RD ST/ BRONX RIVER BIN # 2242459 | 3 | FINAL DESIGN | 2020-01-26 | 2020-07-23 | 2020-01-26 | 2020-07-23
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA24245 | EAST 233RD ST/ BRONX RIVER BIN # 2242459 | 4 | BID AWARD AND REGISTER CONTRCT | 2020-07-24 | 2020-10-21 | 2020-07-24 | 2020-10-21
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA24245 | EAST 233RD ST/ BRONX RIVER BIN # 2242459 | 5 | CONSTRUCTION TO 25% | 2020-10-22 | 2021-02-18 | 2020-10-22 | 2021-02-18
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA24245 | EAST 233RD ST/ BRONX RIVER BIN # 2242459 | 6 | CONSTRUCTION TO 50% | 2021-02-19 | 2021-06-18 | 2021-02-19 | 2021-06-18
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA24245 | EAST 233RD ST/ BRONX RIVER BIN # 2242459 | 7 | CONSTRUCTION TO 75% | 2021-06-19 | 2021-10-16 | 2021-06-19 | 2021-10-16
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA24245 | EAST 233RD ST/ BRONX RIVER BIN # 2242459 | 8 | ORIGINAL EQUIP & FURNISHING | 2021-10-17 | 2022-01-14 | 2021-10-17 | 2022-01-14
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA24245 | EAST 233RD ST/ BRONX RIVER BIN # 2242459 | 9 | SUBSTANTIAL COMPLETION | 2022-01-15 | 2022-03-15 | 2022-01-15 | 2022-03-15
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA24245 | EAST 233RD ST/ BRONX RIVER BIN # 2242459 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-16 | 2022-04-14 | 2022-03-16 | 2022-04-14
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX1086 | WESTCHESTER AVE BR OVER HUTCH RIVER PKWY 2-075837 | 1 | DEVELOP SCOPE | 2003-07-01 | 2004-06-29 | 0 | 0
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX1086 | WESTCHESTER AVE BR OVER HUTCH RIVER PKWY 2-075837 | 2 | DESIGN START | 2004-06-30 | 2008-06-28 | 2017-07-01 | 2018-06-30
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX1086 | WESTCHESTER AVE BR OVER HUTCH RIVER PKWY 2-075837 | 3 | CONSTRUCTION START | 2008-06-29 | 2010-06-28 | 2018-07-01 | 2022-06-29
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX1086 | WESTCHESTER AVE BR OVER HUTCH RIVER PKWY 2-075837 | 5 | CONSTRUCTION START | 2008-06-29 | 2010-06-28 | 2022-06-30 | 2022-07-29
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX1103 | CONCOURSE VLGE AVE/ M-N 2-24159-0 | 1 | DEVELOP SCOPE | 2004-07-01 | 2005-06-30 | 2016-03-02 | 2016-09-22
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX1103 | CONCOURSE VLGE AVE/ M-N 2-24159-0 | 2 | DESIGN START | 2005-07-01 | 2009-06-29 | 2019-01-25 | 2022-05-19
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX1103 | CONCOURSE VLGE AVE/ M-N 2-24159-0 | 3 | CONSTRUCTION START | 2009-06-30 | 2011-06-29 | 2023-04-30 | 2027-07-30
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX1127 | RECON PELHAM PKWY BRIDGE OVER HUTCHINSON PKWY 2-07584-9 | 1 | DEVELOP SCOPE | 2005-07-01 | 2006-06-30 | 0 | 0
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX1127 | RECON PELHAM PKWY BRIDGE OVER HUTCHINSON PKWY 2-07584-9 | 2 | DESIGN START | 2006-07-01 | 2010-06-29 | 2015-11-06 | 2016-03-09
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX1127 | RECON PELHAM PKWY BRIDGE OVER HUTCHINSON PKWY 2-07584-9 | 3 | CONSTRUCTION START | 2010-06-30 | 2012-06-28 | 2017-11-08 | 2022-08-26
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX1127 | RECON PELHAM PKWY BRIDGE OVER HUTCHINSON PKWY 2-07584-9 | 5 | CONSTRUCTION START | 2010-06-30 | 2012-06-28 | 2022-06-26 | 2026-09-29
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX1131 | BRUCKNER EXP / WESTCHESTER CREEK 1-066510 | 1 | DEVELOP SCOPE | 2001-07-01 | 2003-06-30 | 0 | 0
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX1131 | BRUCKNER EXP / WESTCHESTER CREEK 1-066510 | 2 | DESIGN START | 1999-07-02 | 2003-06-30 | 0 | 0
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX1131 | BRUCKNER EXP / WESTCHESTER CREEK 1-066510 | 3 | CONSTRUCTION START | 2008-06-30 | 2010-06-29 | 0 | 0
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX1131 | BRUCKNER EXP / WESTCHESTER CREEK 1-066510 | 6 | DEVELOP SCOPE | 2008-06-30 | 2010-06-29 | 2011-06-07 | 2011-07-27
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX1131 | BRUCKNER EXP / WESTCHESTER CREEK 1-066510 | 7 | DESIGN START | 2008-06-30 | 2010-06-29 | 2014-06-28 | 2016-08-25
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX1131 | BRUCKNER EXP / WESTCHESTER CREEK 1-066510 | 8 | CONSTRUCTION START | 2008-06-30 | 2010-06-29 | 2017-07-17 | 2021-09-30
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX1148B | SHORE ROAD BRIDGE / HUTCHINSON RIVER 2-240200 | 1 | DEVELOP SCOPE | 2007-07-01 | 2008-06-29 | 2013-07-15 | 2015-09-01
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX1148B | SHORE ROAD BRIDGE / HUTCHINSON RIVER 2-240200 | 2 | DESIGN START | 2008-06-30 | 2012-06-28 | 2017-05-31 | 2023-03-26
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX1148B | SHORE ROAD BRIDGE / HUTCHINSON RIVER 2-240200 | 3 | CONSTRUCTION START | 2012-06-29 | 2014-06-28 | 2024-01-23 | 2026-03-24
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX1190 | GRAND CONCOURSE / METRO NORTH RR HUD2-24140-9 | 1 | DEVELOP SCOPE | 2004-06-30 | 2005-06-29 | 0 | 0
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX1190 | GRAND CONCOURSE / METRO NORTH RR HUD2-24140-9 | 2 | DESIGN START | 2005-06-30 | 2009-06-28 | 1998-01-06 | 1998-07-28
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX1190 | GRAND CONCOURSE / METRO NORTH RR HUD2-24140-9 | 3 | CONSTRUCTION START | 2009-06-29 | 2011-06-28 | 2000-01-14 | 2019-10-22
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX1190 | GRAND CONCOURSE / METRO NORTH RR HUD2-24140-9 | 5 | CONSTRUCTION START | 2009-06-29 | 2011-06-28 | 2019-11-27 | 2022-08-13
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX1215 | E. 175TH ST/METRO NORTH RR HAR 2-24174-0 TD PKG 1 | 1 | DEVELOP SCOPE | 2005-07-01 | 2006-06-30 | 2011-06-30 | 2014-06-28
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX1215 | E. 175TH ST/METRO NORTH RR HAR 2-24174-0 TD PKG 1 | 2 | DESIGN START | 2006-07-01 | 2010-06-29 | 2008-03-11 | 2018-08-06
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX1215 | E. 175TH ST/METRO NORTH RR HAR 2-24174-0 TD PKG 1 | 3 | CONSTRUCTION START | 2010-06-30 | 2012-06-28 | 2020-07-29 | 2022-11-17
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX1460 | WEST TREMONT AVENUE OVER METRO NORTH RR BIN:2241460 | 1 | DEVELOP SCOPE | 2015-06-30 | 2016-06-28 | 0 | 0
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX1460 | WEST TREMONT AVENUE OVER METRO NORTH RR BIN:2241460 | 2 | DESIGN START | 2016-06-29 | 2020-06-27 | 2015-06-30 | 2016-06-28
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX1460 | WEST TREMONT AVENUE OVER METRO NORTH RR BIN:2241460 | 3 | CONSTRUCTION START | 2020-06-28 | 2022-06-27 | 2018-01-16 | 2021-02-13
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX1460 | WEST TREMONT AVENUE OVER METRO NORTH RR BIN:2241460 | 5 | CONSTRUCTION START | 2020-06-28 | 2022-06-27 | 2021-02-14 | 2026-05-02
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX156 | E 156TH ST BRIDGE OVER ACCESS TO HOUSING (BIN 2270030) | 1 | DEVELOP SCOPE | 2015-07-01 | 2016-06-29 | 0 | 0
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX156 | E 156TH ST BRIDGE OVER ACCESS TO HOUSING (BIN 2270030) | 2 | DESIGN START | 2016-06-30 | 2020-06-28 | 2016-03-02 | 2016-09-30
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX156 | E 156TH ST BRIDGE OVER ACCESS TO HOUSING (BIN 2270030) | 3 | CONSTRUCTION START | 2020-06-29 | 2022-06-28 | 2019-01-25 | 2022-05-21
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX156 | E 156TH ST BRIDGE OVER ACCESS TO HOUSING (BIN 2270030) | 5 | CONSTRUCTION START | 2020-06-29 | 2022-06-28 | 2023-05-02 | 2027-08-01
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX163 | 5 Bridges - Melrose, Bronx | 1 | DEVELOP SCOPE | 2014-06-30 | 2015-06-29 | 0 | 0
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX163 | 5 Bridges - Melrose, Bronx | 2 | DESIGN START | 2015-06-30 | 2019-06-28 | 2014-06-30 | 2015-06-29
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX163 | 5 Bridges - Melrose, Bronx | 3 | CONSTRUCTION START | 2019-06-29 | 2021-06-27 | 2014-10-17 | 2015-11-13
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX163 | 5 Bridges - Melrose, Bronx | 5 | CONSTRUCTION START | 2019-06-29 | 2021-06-27 | 2020-07-29 | 2021-06-27
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX180 | E. 180TH ST OVER METRO NORTH RR HAR (BIN 2-24179-0) | 1 | DEVELOP SCOPE | 2011-06-30 | 2014-06-28 | 2014-06-02 | 2014-06-02
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX180 | E. 180TH ST OVER METRO NORTH RR HAR (BIN 2-24179-0) | 2 | DESIGN START | 2014-06-29 | 2014-06-28 | 2015-05-27 | 2018-07-12
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX180 | E. 180TH ST OVER METRO NORTH RR HAR (BIN 2-24179-0) | 3 | CONSTRUCTION START | 2014-06-29 | 2020-06-26 | 2020-07-29 | 2023-04-15
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX199 | E153RD ST BR AT PARK AVE OVER RR | 1 | DEVELOP SCOPE | 2003-07-02 | 2004-06-30 | 0 | 0
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX199 | E153RD ST BR AT PARK AVE OVER RR | 2 | DESIGN START | 2004-07-01 | 2008-06-29 | 2018-05-02 | 2020-02-05
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX199 | E153RD ST BR AT PARK AVE OVER RR | 3 | CONSTRUCTION START | 2008-06-30 | 2010-06-29 | 2021-04-03 | 2024-04-01
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX199 | E153RD ST BR AT PARK AVE OVER RR | 5 | CONSTRUCTION START | 2008-06-30 | 2010-06-29 | 2025-03-30 | 2027-05-29
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX2370 | REHAB GRAND CONCOURSE BIN 2242370 | 1 | DEVELOP SCOPE | 2016-06-30 | 2017-06-29 | 0 | 0
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX2370 | REHAB GRAND CONCOURSE BIN 2242370 | 2 | DESIGN START | 2017-06-30 | 2021-06-28 | 2018-07-11 | 2019-12-28
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX2370 | REHAB GRAND CONCOURSE BIN 2242370 | 3 | CONSTRUCTION START | 2021-06-29 | 2023-06-28 | 2019-12-29 | 2023-12-27
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX2370 | REHAB GRAND CONCOURSE BIN 2242370 | 5 | CONSTRUCTION START | 2021-06-29 | 2023-06-28 | 2023-12-28 | 2025-12-26
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX644S | MADISON AVE BR - REHAB OF ELECTRICAL AND MECHANICAL SYSTEM | 1 | DEVELOP SCOPE | 2005-07-01 | 2006-06-30 | 0 | 0
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX644S | MADISON AVE BR - REHAB OF ELECTRICAL AND MECHANICAL SYSTEM | 2 | DESIGN START | 2006-07-01 | 2010-06-29 | 2016-01-22 | 2016-03-08
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX644S | MADISON AVE BR - REHAB OF ELECTRICAL AND MECHANICAL SYSTEM | 3 | CONSTRUCTION START | 2010-06-30 | 2012-06-28 | 2011-02-10 | 2016-02-08
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX644S | MADISON AVE BR - REHAB OF ELECTRICAL AND MECHANICAL SYSTEM | 5 | CONSTRUCTION START | 2010-06-30 | 2012-06-28 | 2024-12-24 | 2027-09-04
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR19A | Citywide Milling - Bronx | 1 | DEVELOP SCOPE | 2017-06-30 | 2017-09-27 | 2018-06-30 | 2018-09-27
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR19A | Citywide Milling - Bronx | 2 | PRELIMINARY DESIGN | 2017-09-28 | 2018-01-25 | 2018-09-28 | 2019-01-25
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR19A | Citywide Milling - Bronx | 3 | FINAL DESIGN | 2018-01-26 | 2018-07-24 | 2019-01-26 | 2019-07-24
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR19A | Citywide Milling - Bronx | 4 | BID AWARD AND REGISTER CONTRCT | 2018-07-25 | 2018-10-22 | 2019-07-25 | 2019-10-22
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR19A | Citywide Milling - Bronx | 5 | CONSTRUCTION TO 25% | 2018-10-23 | 2019-02-19 | 2019-10-23 | 2020-02-19
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR19A | Citywide Milling - Bronx | 6 | CONSTRUCTION TO 50% | 2019-02-20 | 2019-06-19 | 2020-02-20 | 2020-06-18
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR19A | Citywide Milling - Bronx | 7 | CONSTRUCTION TO 75% | 2019-06-20 | 2019-10-17 | 2020-06-19 | 2020-10-16
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR19A | Citywide Milling - Bronx | 8 | ORIGINAL EQUIP & FURNISHING | 2019-10-18 | 2020-01-15 | 2020-10-17 | 2021-01-14
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR19A | Citywide Milling - Bronx | 9 | SUBSTANTIAL COMPLETION | 2020-01-16 | 2020-03-15 | 2021-01-15 | 2021-03-15
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR19A | Citywide Milling - Bronx | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-03-16 | 2020-04-14 | 2021-03-16 | 2021-04-14
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWCWSTPR | NY RESTORATION PROJECT - DEVELOP & DESIGN STREET PIER | 1 | DEVELOP SCOPE | 2017-06-30 | 2017-09-27 | 2020-06-30 | 2020-09-27
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWCWSTPR | NY RESTORATION PROJECT - DEVELOP & DESIGN STREET PIER | 2 | PRELIMINARY DESIGN | 2017-09-28 | 2018-01-25 | 2020-09-28 | 2021-01-25
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWCWSTPR | NY RESTORATION PROJECT - DEVELOP & DESIGN STREET PIER | 3 | FINAL DESIGN | 2018-01-26 | 2018-07-24 | 2021-01-26 | 2021-07-24
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWCWSTPR | NY RESTORATION PROJECT - DEVELOP & DESIGN STREET PIER | 4 | BID AWARD AND REGISTER CONTRCT | 2018-07-25 | 2018-10-22 | 2021-07-25 | 2021-10-22
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWCWSTPR | NY RESTORATION PROJECT - DEVELOP & DESIGN STREET PIER | 5 | CONSTRUCTION TO 25% | 2018-10-23 | 2019-02-19 | 2021-10-23 | 2022-02-19
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWCWSTPR | NY RESTORATION PROJECT - DEVELOP & DESIGN STREET PIER | 6 | CONSTRUCTION TO 50% | 2019-02-20 | 2019-06-19 | 2022-02-20 | 2022-06-19
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWCWSTPR | NY RESTORATION PROJECT - DEVELOP & DESIGN STREET PIER | 7 | CONSTRUCTION TO 75% | 2019-06-20 | 2019-10-17 | 2022-06-20 | 2022-10-17
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWCWSTPR | NY RESTORATION PROJECT - DEVELOP & DESIGN STREET PIER | 8 | ORIGINAL EQUIP & FURNISHING | 2019-10-18 | 2020-01-15 | 2022-10-18 | 2023-01-15
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWCWSTPR | NY RESTORATION PROJECT - DEVELOP & DESIGN STREET PIER | 9 | SUBSTANTIAL COMPLETION | 2020-01-16 | 2020-03-15 | 2023-01-16 | 2023-03-16
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWCWSTPR | NY RESTORATION PROJECT - DEVELOP & DESIGN STREET PIER | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-03-16 | 2020-04-14 | 2023-03-17 | 2028-06-30
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWS2021X | PRIOR NOTICE SIDEWALK - BRONX | 1 | DEVELOP SCOPE | 2020-02-24 | 2020-03-24 | 2020-02-24 | 2020-03-24
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWS2021X | PRIOR NOTICE SIDEWALK - BRONX | 2 | DESIGN START | 2020-03-25 | 2020-09-15 | 2020-03-25 | 2020-09-15
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWS2021X | PRIOR NOTICE SIDEWALK - BRONX | 3 | CONSTRUCTION START | 2020-09-16 | 2021-06-30 | 2020-09-16 | 2021-06-30
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX1048A | South Bronx Greenway: East 138th to Southern Boulevard | 1 | DEVELOP SCOPE | 2021-06-30 | 2021-09-27 | 2024-05-29 | 2025-02-12
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX1048A | South Bronx Greenway: East 138th to Southern Boulevard | 2 | PRELIMINARY DESIGN | 2021-09-28 | 2022-01-25 | 2025-02-13 | 2025-06-12
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX1048A | South Bronx Greenway: East 138th to Southern Boulevard | 3 | FINAL DESIGN | 2022-01-26 | 2022-07-24 | 2025-06-13 | 2025-12-09
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX1048A | South Bronx Greenway: East 138th to Southern Boulevard | 4 | BID AWARD AND REGISTER CONTRCT | 2022-07-25 | 2022-10-22 | 2025-12-10 | 2026-03-09
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX1048A | South Bronx Greenway: East 138th to Southern Boulevard | 5 | CONSTRUCTION TO 25% | 2022-10-23 | 2023-02-19 | 2026-03-10 | 2026-07-07
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX1048A | South Bronx Greenway: East 138th to Southern Boulevard | 6 | CONSTRUCTION TO 50% | 2023-02-20 | 2023-06-19 | 2026-07-08 | 2026-11-04
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX1048A | South Bronx Greenway: East 138th to Southern Boulevard | 7 | CONSTRUCTION TO 75% | 2023-06-20 | 2023-10-17 | 2026-11-05 | 2027-03-04
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX1048A | South Bronx Greenway: East 138th to Southern Boulevard | 8 | ORIGINAL EQUIP & FURNISHING | 2023-10-18 | 2024-01-15 | 2027-03-05 | 2027-06-02
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX1048A | South Bronx Greenway: East 138th to Southern Boulevard | 9 | SUBSTANTIAL COMPLETION | 2024-01-16 | 2024-03-15 | 2027-06-03 | 2027-08-01
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX1048A | South Bronx Greenway: East 138th to Southern Boulevard | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-03-16 | 2024-04-14 | 2027-08-02 | 2027-08-31
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX405 | Southern Blvd Pedestrian and Bike Improvements | 1 | DEVELOP SCOPE | 2020-06-30 | 2020-09-27 | 2024-06-30 | 2024-09-27
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX405 | Southern Blvd Pedestrian and Bike Improvements | 2 | PRELIMINARY DESIGN | 2020-09-28 | 2021-01-25 | 2024-09-28 | 2025-01-25
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX405 | Southern Blvd Pedestrian and Bike Improvements | 3 | FINAL DESIGN | 2021-01-26 | 2021-07-24 | 2025-01-26 | 2025-07-24
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX405 | Southern Blvd Pedestrian and Bike Improvements | 4 | BID AWARD AND REGISTER CONTRCT | 2021-07-25 | 2021-10-22 | 2025-07-25 | 2025-10-22
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX405 | Southern Blvd Pedestrian and Bike Improvements | 5 | CONSTRUCTION TO 25% | 2021-10-23 | 2022-02-19 | 2025-10-23 | 2026-02-19
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX405 | Southern Blvd Pedestrian and Bike Improvements | 6 | CONSTRUCTION TO 50% | 2022-02-20 | 2022-06-19 | 2026-02-20 | 2026-06-19
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX405 | Southern Blvd Pedestrian and Bike Improvements | 7 | CONSTRUCTION TO 75% | 2022-06-20 | 2022-10-17 | 2026-06-20 | 2026-10-17
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX405 | Southern Blvd Pedestrian and Bike Improvements | 8 | ORIGINAL EQUIP & FURNISHING | 2022-10-18 | 2023-01-15 | 2026-10-18 | 2027-01-15
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX405 | Southern Blvd Pedestrian and Bike Improvements | 9 | SUBSTANTIAL COMPLETION | 2023-01-16 | 2023-03-16 | 2027-01-16 | 2027-03-16
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX405 | Southern Blvd Pedestrian and Bike Improvements | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-03-17 | 2023-04-15 | 2027-03-17 | 2027-04-15
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX711 | Bronx River Greenway @ 233rd St | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-09-28 | 2020-07-01 | 2020-09-28
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX711 | Bronx River Greenway @ 233rd St | 2 | PRELIMINARY DESIGN | 2016-09-29 | 2017-01-26 | 2020-09-29 | 2021-01-26
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX711 | Bronx River Greenway @ 233rd St | 3 | FINAL DESIGN | 2017-01-27 | 2017-07-25 | 2021-01-27 | 2021-07-25
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX711 | Bronx River Greenway @ 233rd St | 4 | BID AWARD AND REGISTER CONTRCT | 2017-07-26 | 2017-10-23 | 2021-07-26 | 2021-10-23
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX711 | Bronx River Greenway @ 233rd St | 5 | CONSTRUCTION TO 25% | 2017-10-24 | 2018-02-20 | 2021-10-24 | 2022-02-20
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX711 | Bronx River Greenway @ 233rd St | 6 | CONSTRUCTION TO 50% | 2018-02-21 | 2018-06-20 | 2022-02-21 | 2022-06-20
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX711 | Bronx River Greenway @ 233rd St | 7 | CONSTRUCTION TO 75% | 2018-06-21 | 2018-10-18 | 2022-06-21 | 2022-10-18
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX711 | Bronx River Greenway @ 233rd St | 8 | ORIGINAL EQUIP & FURNISHING | 2018-10-19 | 2019-01-16 | 2022-10-19 | 2023-01-16
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX711 | Bronx River Greenway @ 233rd St | 9 | SUBSTANTIAL COMPLETION | 2019-01-17 | 2019-03-17 | 2023-01-17 | 2023-03-17
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX711 | Bronx River Greenway @ 233rd St | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-03-18 | 2019-04-16 | 2023-03-18 | 2023-04-16
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWXJEROME | Jerome Avenue Safety Improvements | 1 | DEVELOP SCOPE | 2019-06-30 | 2019-09-27 | 2016-02-02 | 2018-01-17
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWXJEROME | Jerome Avenue Safety Improvements | 2 | PRELIMINARY DESIGN | 2019-09-28 | 2020-01-25 | 2021-02-10 | 2022-09-21
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWXJEROME | Jerome Avenue Safety Improvements | 3 | FINAL DESIGN | 2020-01-26 | 2020-07-23 | 2022-05-18 | 2023-11-01
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWXJEROME | Jerome Avenue Safety Improvements | 4 | BID AWARD AND REGISTER CONTRCT | 2020-07-24 | 2020-10-21 | 2023-11-23 | 2024-01-03
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWXJEROME | Jerome Avenue Safety Improvements | 5 | CONSTRUCTION TO 25% | 2020-10-22 | 2021-02-18 | 2024-09-25 | 2024-12-24
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWXJEROME | Jerome Avenue Safety Improvements | 6 | CONSTRUCTION TO 50% | 2021-02-19 | 2021-06-18 | 2024-12-25 | 2025-04-23
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWXJEROME | Jerome Avenue Safety Improvements | 7 | CONSTRUCTION TO 75% | 2021-06-19 | 2021-10-16 | 2025-04-24 | 2027-12-09
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWXJEROME | Jerome Avenue Safety Improvements | 8 | ORIGINAL EQUIP & FURNISHING | 2021-10-17 | 2022-01-14 | 2027-12-10 | 2028-03-08
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWXJEROME | Jerome Avenue Safety Improvements | 9 | SUBSTANTIAL COMPLETION | 2022-01-15 | 2022-03-15 | 2028-03-09 | 2028-05-07
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWXJEROME | Jerome Avenue Safety Improvements | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-16 | 2022-04-14 | 2028-05-08 | 2028-06-06
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | TFD005X01 | DOT Camera install at Clay Avenue Step Street and 169th BX | 1 | BID AWARD AND REGISTER CONTRCT | 2021-06-01 | 2021-06-02 | 2021-06-01 | 2021-06-02
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | TFD005X01 | DOT Camera install at Clay Avenue Step Street and 169th BX | 2 | CONSTRUCTION START | 2021-06-03 | 2021-06-20 | 2021-06-03 | 2021-06-20
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | TFD005X01 | DOT Camera install at Clay Avenue Step Street and 169th BX | 3 | CONSTRUCTION COMPLETION | 2021-06-21 | 2021-06-30 | 2021-06-21 | 2021-06-30
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | TFD503X21 | CLAY AV.HISTORIC DISTRICT OLD-STYLE ST LAMP BET. E165& 167TH | 1 | BID AWARD AND REGISTER CONTRCT | 2011-06-30 | 2011-06-30 | 2022-06-30 | 2022-06-30
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | TFD503X21 | CLAY AV.HISTORIC DISTRICT OLD-STYLE ST LAMP BET. E165& 167TH | 2 | CONSTRUCTION START | 2011-07-01 | 2011-08-14 | 2022-07-01 | 2022-08-14
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | TFD503X21 | CLAY AV.HISTORIC DISTRICT OLD-STYLE ST LAMP BET. E165& 167TH | 3 | CONSTRUCTION COMPLETION | 2011-08-15 | 2013-03-06 | 2022-08-15 | 2024-03-06
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | TFX50301 | GRAND CONCOURSE DECORATIVE STREET LIGHTING | 1 | BID AWARD AND REGISTER CONTRCT | 2006-06-15 | 2006-06-15 | 2022-06-15 | 2022-06-15
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | TFX50301 | GRAND CONCOURSE DECORATIVE STREET LIGHTING | 2 | CONSTRUCTION START | 2006-06-16 | 2006-07-30 | 2022-06-16 | 2022-07-30
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | TFX50301 | GRAND CONCOURSE DECORATIVE STREET LIGHTING | 3 | CONSTRUCTION COMPLETION | 2006-07-31 | 2008-02-20 | 2022-07-31 | 2024-02-20
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | TRANSBCTY | Reconstruction Transfer Bridge Structure at City Island | 1 | DEVELOP SCOPE | 2019-06-30 | 2020-06-28 | 2019-06-30 | 2020-06-28
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | TRANSBCTY | Reconstruction Transfer Bridge Structure at City Island | 2 | DESIGN START | 2020-06-29 | 2022-06-28 | 2020-06-29 | 2022-06-28
20201123 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | TRANSBCTY | Reconstruction Transfer Bridge Structure at City Island | 3 | CONSTRUCTION START | 2022-06-29 | 2024-06-27 | 2022-06-29 | 2024-06-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | GXBXGI-01 | Bronx Parkland Green Infrastructure Retrofits | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | GXBXGI-01 | Bronx Parkland Green Infrastructure Retrofits | 2 | DESIGN | 2016-12-28 | 2018-06-20 | 2016-12-28 | 2018-06-20
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | GXBXGI-01 | Bronx Parkland Green Infrastructure Retrofits | 3 | BID/ REGISTER CONTRACT | 2018-06-21 | 2019-03-17 | 2018-06-21 | 2019-03-17
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | GXBXGI-01 | Bronx Parkland Green Infrastructure Retrofits | 4 | CONSTRUCTION | 2019-03-18 | 2021-03-16 | 2019-03-18 | 2021-03-16
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | GXBXGI-01 | Bronx Parkland Green Infrastructure Retrofits | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-17 | 2023-03-16 | 2021-03-17 | 2023-03-16
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | HIF-1FSPB | Franz Sigel Park Ballfields-Install BallField Lighting | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | HIF-1FSPB | Franz Sigel Park Ballfields-Install BallField Lighting | 2 | DESIGN | 2018-12-28 | 2020-03-26 | 2018-12-28 | 2020-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | HIF-1FSPB | Franz Sigel Park Ballfields-Install BallField Lighting | 3 | BID/ REGISTER CONTRACT | 2020-03-27 | 2020-12-21 | 2020-03-27 | 2020-12-21
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | HIF-1FSPB | Franz Sigel Park Ballfields-Install BallField Lighting | 4 | CONSTRUCTION | 2020-12-22 | 2021-12-21 | 2020-12-22 | 2021-12-21
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | HIF-1FSPB | Franz Sigel Park Ballfields-Install BallField Lighting | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-12-22 | 2022-12-21 | 2021-12-22 | 2022-12-21
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | NDF-BRPLG | NDF-Bridge Playground- X148A3-318M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | NDF-BRPLG | NDF-Bridge Playground- X148A3-318M | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | NDF-BRPLG | NDF-Bridge Playground- X148A3-318M | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | NDF-BRPLG | NDF-Bridge Playground- X148A3-318M | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | NDF-BRPLG | NDF-Bridge Playground- X148A3-318M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | NDF-CPFSP | NDF-CORPORAL FISCHER PLAYGROUND X269-119M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | NDF-CPFSP | NDF-CORPORAL FISCHER PLAYGROUND X269-119M | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | NDF-CPFSP | NDF-CORPORAL FISCHER PLAYGROUND X269-119M | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | NDF-CPFSP | NDF-CORPORAL FISCHER PLAYGROUND X269-119M | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | NDF-CPFSP | NDF-CORPORAL FISCHER PLAYGROUND X269-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | NDF-DVDSO | Neighborhood Dev. Fund-1801 Davidson | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | NDF-DVDSO | Neighborhood Dev. Fund-1801 Davidson | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | NDF-DVDSO | Neighborhood Dev. Fund-1801 Davidson | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | NDF-DVDSO | Neighborhood Dev. Fund-1801 Davidson | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | NDF-DVDSO | Neighborhood Dev. Fund-1801 Davidson | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | NDF-GRANT | NDF-Grant Park X271-119M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | NDF-GRANT | NDF-Grant Park X271-119M | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | NDF-GRANT | NDF-Grant Park X271-119M | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | NDF-GRANT | NDF-Grant Park X271-119M | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | NDF-GRANT | NDF-Grant Park X271-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | NDF-MORTN | NDF-MORTON PLAYGROUND RECONSTRUCTION (X001A) | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | NDF-MORTN | NDF-MORTON PLAYGROUND RECONSTRUCTION (X001A) | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | NDF-MORTN | NDF-MORTON PLAYGROUND RECONSTRUCTION (X001A) | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | NDF-MORTN | NDF-MORTON PLAYGROUND RECONSTRUCTION (X001A) | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | NDF-MORTN | NDF-MORTON PLAYGROUND RECONSTRUCTION (X001A) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | NDF-SOAQK | NDF-Aqueduct Walk | 1 | DEVELOP SCOPE | 2020-07-01 | 2020-12-27 | 2020-07-01 | 2020-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | NDF-SOAQK | NDF-Aqueduct Walk | 2 | DESIGN | 2020-12-28 | 2021-12-27 | 2020-12-28 | 2021-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | NDF-SOAQK | NDF-Aqueduct Walk | 3 | BID/ REGISTER CONTRACT | 2021-12-28 | 2022-09-23 | 2021-12-28 | 2022-09-23
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | NDF-SOAQK | NDF-Aqueduct Walk | 4 | CONSTRUCTION | 2022-09-24 | 2023-09-23 | 2022-09-24 | 2023-09-23
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | NDF-SOAQK | NDF-Aqueduct Walk | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-24 | 2024-09-22 | 2023-09-24 | 2024-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-100CDAR | Cedar Playground - RC C/S X111-114M | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2014-11-10
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-100CDAR | Cedar Playground - RC C/S X111-114M | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2014-11-11 | 2016-08-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-100CDAR | Cedar Playground - RC C/S X111-114M | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2016-08-23 | 2016-11-20
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-100CDAR | Cedar Playground - RC C/S X111-114M | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2016-11-21 | 2017-11-20
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-100CDAR | Cedar Playground - RC C/S X111-114M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2017-11-21 | 2024-02-01
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-100PBSG | Pelham Bay Park Sensory Garden X039-118M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-100PBSG | Pelham Bay Park Sensory Garden X039-118M | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-100PBSG | Pelham Bay Park Sensory Garden X039-118M | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-100PBSG | Pelham Bay Park Sensory Garden X039-118M | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-100PBSG | Pelham Bay Park Sensory Garden X039-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-101BPAR | Brook Park - sitting area & comfort station | 1 | DEVELOP SCOPE | 2006-07-01 | 2006-09-28 | 2006-07-01 | 2006-09-28
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-101BPAR | Brook Park - sitting area & comfort station | 2 | DESIGN | 2006-09-29 | 2006-12-27 | 2006-09-29 | 2006-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-101BPAR | Brook Park - sitting area & comfort station | 3 | BID/ REGISTER CONTRACT | 2006-12-28 | 2007-03-27 | 2006-12-28 | 2007-03-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-101BPAR | Brook Park - sitting area & comfort station | 4 | CONSTRUCTION | 2007-03-28 | 2008-03-26 | 2007-03-28 | 2008-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-101BPAR | Brook Park - sitting area & comfort station | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-27 | 2009-03-26 | 2008-03-27 | 2024-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-101LZDA | Lozada Park Renovation- New play equip.,spray shower, swings | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-101LZDA | Lozada Park Renovation- New play equip.,spray shower, swings | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-101LZDA | Lozada Park Renovation- New play equip.,spray shower, swings | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-101LZDA | Lozada Park Renovation- New play equip.,spray shower, swings | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-101LZDA | Lozada Park Renovation- New play equip.,spray shower, swings | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2024-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-101MAR2 | St. Mary's Plgd West - ADA CS (X045-118M) | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-101MAR2 | St. Mary's Plgd West - ADA CS (X045-118M) | 2 | DESIGN | 2016-12-28 | 2018-12-27 | 2016-12-28 | 2018-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-101MAR2 | St. Mary's Plgd West - ADA CS (X045-118M) | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-101MAR2 | St. Mary's Plgd West - ADA CS (X045-118M) | 4 | CONSTRUCTION | 2019-09-24 | 2022-09-22 | 2019-09-24 | 2022-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-101MAR2 | St. Mary's Plgd West - ADA CS (X045-118M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2024-09-21 | 2022-09-23 | 2024-09-21
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-101MBRO | Millbrook Plgd- basketball & handball courts- X182-115M | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2016-09-02 | 2017-04-28
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-101MBRO | Millbrook Plgd- basketball & handball courts- X182-115M | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2017-06-05 | 2018-06-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-101MBRO | Millbrook Plgd- basketball & handball courts- X182-115M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2018-06-23 | 2022-09-17
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-101PULP | Pulaski Park Reconstruction- X041-118M | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-101PULP | Pulaski Park Reconstruction- X041-118M | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2016-12-28 | 2017-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-101PULP | Pulaski Park Reconstruction- X041-118M | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2017-12-28 | 2018-09-23
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-101PULP | Pulaski Park Reconstruction- X041-118M | 4 | CONSTRUCTION | 2018-09-24 | 2019-09-23 | 2018-09-24 | 2019-09-23
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-101PULP | Pulaski Park Reconstruction- X041-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-101STMH | ST. MARY'S PK REC CTR HVAC X045-116M | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2015-09-28
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-101STMH | ST. MARY'S PK REC CTR HVAC X045-116M | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2015-09-29 | 2015-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-101STMH | ST. MARY'S PK REC CTR HVAC X045-116M | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2015-12-28 | 2016-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-101STMH | ST. MARY'S PK REC CTR HVAC X045-116M | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-101STMH | ST. MARY'S PK REC CTR HVAC X045-116M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2017-03-27 | 2022-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-101STMR | St Mary's plgd (w) ph1 recon w/equip, landscape-X045-215MA | 1 | DEVELOP SCOPE | 2014-07-01 | 2014-09-28 | 2014-07-01 | 2015-03-04
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-101STMR | St Mary's plgd (w) ph1 recon w/equip, landscape-X045-215MA | 2 | DESIGN | 2014-09-29 | 2014-12-27 | 2015-03-05 | 2017-09-07
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-101STMR | St Mary's plgd (w) ph1 recon w/equip, landscape-X045-215MA | 3 | BID/ REGISTER CONTRACT | 2014-12-28 | 2015-03-27 | 2017-08-17 | 2018-05-18
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-101STMR | St Mary's plgd (w) ph1 recon w/equip, landscape-X045-215MA | 4 | CONSTRUCTION | 2015-03-28 | 2016-03-26 | 2018-07-23 | 2019-07-20
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-101STMR | St Mary's plgd (w) ph1 recon w/equip, landscape-X045-215MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-27 | 2017-03-26 | 2019-07-21 | 2022-07-20
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-101WLSP | Willis Plgd Recon - X217-118M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-101WLSP | Willis Plgd Recon - X217-118M | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-101WLSP | Willis Plgd Recon - X217-118M | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-101WLSP | Willis Plgd Recon - X217-118M | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-101WLSP | Willis Plgd Recon - X217-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-102BRPP | Bill Rainey Park--Lights For Baseball Field & Score Board | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-102BRPP | Bill Rainey Park--Lights For Baseball Field & Score Board | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-102BRPP | Bill Rainey Park--Lights For Baseball Field & Score Board | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-102BRPP | Bill Rainey Park--Lights For Baseball Field & Score Board | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-102BRPP | Bill Rainey Park--Lights For Baseball Field & Score Board | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-102CEME | Bronx River - Concrete Plant Park - XG-31700-201M, 205M | 1 | DEVELOP SCOPE | 2002-07-01 | 2003-11-01 | 2002-07-01 | 2004-11-01
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-102CEME | Bronx River - Concrete Plant Park - XG-31700-201M, 205M | 2 | DESIGN | 2003-11-02 | 2004-03-01 | 2004-09-13 | 2004-10-07
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-102CEME | Bronx River - Concrete Plant Park - XG-31700-201M, 205M | 3 | BID/ REGISTER CONTRACT | 2004-03-02 | 2004-06-01 | 2005-02-14 | 2006-05-03
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-102CEME | Bronx River - Concrete Plant Park - XG-31700-201M, 205M | 4 | CONSTRUCTION | 2003-07-31 | 2005-03-30 | 2007-01-22 | 2009-08-31
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-102CEME | Bronx River - Concrete Plant Park - XG-31700-201M, 205M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2005-03-31 | 2006-03-30 | 2009-09-01 | 2019-09-01
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-102HNT2 | Hunts Point - Riverside Park - Dock Repair X336-119M | 1 | DEVELOP SCOPE | 2010-07-01 | 2010-09-28 | 2010-07-01 | 2010-09-28
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-102HNT2 | Hunts Point - Riverside Park - Dock Repair X336-119M | 2 | DESIGN | 2010-09-29 | 2010-12-27 | 2010-09-29 | 2010-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-102HNT2 | Hunts Point - Riverside Park - Dock Repair X336-119M | 3 | BID/ REGISTER CONTRACT | 2010-12-28 | 2011-03-27 | 2010-12-28 | 2011-03-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-102HNT2 | Hunts Point - Riverside Park - Dock Repair X336-119M | 4 | CONSTRUCTION | 2011-03-28 | 2012-03-26 | 2011-03-28 | 2012-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-102HNT2 | Hunts Point - Riverside Park - Dock Repair X336-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-03-27 | 2013-03-26 | 2012-03-27 | 2023-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-102MNDA | Manida Park-Lighting & Scoreboard Renovation | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-102MNDA | Manida Park-Lighting & Scoreboard Renovation | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-102MNDA | Manida Park-Lighting & Scoreboard Renovation | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-102MNDA | Manida Park-Lighting & Scoreboard Renovation | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-102MNDA | Manida Park-Lighting & Scoreboard Renovation | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2023-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-102PL52 | CPI PH1 - Playground 52 - Reconstruct Kelly Plgd X179-112M | 2 | DESIGN | 2010-09-29 | 2010-12-27 | 2011-06-04 | 2015-12-13
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-102PL52 | CPI PH1 - Playground 52 - Reconstruct Kelly Plgd X179-112M | 3 | BID/ REGISTER CONTRACT | 2010-12-28 | 2011-03-27 | 2015-02-02 | 2016-04-02
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-102PL52 | CPI PH1 - Playground 52 - Reconstruct Kelly Plgd X179-112M | 4 | CONSTRUCTION | 2011-03-28 | 2012-03-26 | 2016-05-06 | 2018-07-20
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-102PL52 | CPI PH1 - Playground 52 - Reconstruct Kelly Plgd X179-112M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-03-27 | 2013-03-26 | 2018-07-21 | 2025-11-12
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-102RJPP | Rev. J Polite Plgd-Recon of synthetic turf | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-102RJPP | Rev. J Polite Plgd-Recon of synthetic turf | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-102RJPP | Rev. J Polite Plgd-Recon of synthetic turf | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-102RJPP | Rev. J Polite Plgd-Recon of synthetic turf | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-102RJPP | Rev. J Polite Plgd-Recon of synthetic turf | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103CGJF | CS-134-Fence and Water Supply- (X340-116MA) | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2017-03-01
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103CGJF | CS-134-Fence and Water Supply- (X340-116MA) | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2017-03-02 | 2021-11-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103CGJF | CS-134-Fence and Water Supply- (X340-116MA) | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2018-11-26 | 2019-03-20
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103CGJF | CS-134-Fence and Water Supply- (X340-116MA) | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2019-04-30 | 2020-04-29
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103CGJF | CS-134-Fence and Water Supply- (X340-116MA) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2020-04-30 | 2021-04-29
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103CPB5 | Crotona Park - ballfield #5 * X010-115M | 1 | DEVELOP SCOPE | 2012-07-01 | 2012-09-28 | 2012-07-01 | 2016-04-18
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103CPB5 | Crotona Park - ballfield #5 * X010-115M | 2 | DESIGN | 2012-09-29 | 2012-12-27 | 2016-04-19 | 2021-01-16
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103CPB5 | Crotona Park - ballfield #5 * X010-115M | 3 | BID/ REGISTER CONTRACT | 2012-12-28 | 2013-03-27 | 2018-02-20 | 2018-06-04
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103CPB5 | Crotona Park - ballfield #5 * X010-115M | 4 | CONSTRUCTION | 2013-03-28 | 2014-03-27 | 2018-08-06 | 2019-08-04
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103CPB5 | Crotona Park - ballfield #5 * X010-115M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-03-28 | 2015-03-27 | 2019-03-08 | 2020-08-03
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103CPEW | CROTONA PARK GREENWAY - X010-105M | 1 | DEVELOP SCOPE | 2004-07-01 | 2004-09-28 | 2004-07-01 | 2004-08-01
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103CPEW | CROTONA PARK GREENWAY - X010-105M | 2 | DESIGN | 2004-09-29 | 2004-12-27 | 2004-08-02 | 2004-09-21
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103CPEW | CROTONA PARK GREENWAY - X010-105M | 3 | BID/ REGISTER CONTRACT | 2004-12-28 | 2005-03-27 | 2004-09-22 | 2004-12-07
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103CPEW | CROTONA PARK GREENWAY - X010-105M | 4 | CONSTRUCTION | 2005-03-28 | 2006-03-27 | 2004-12-20 | 2006-05-03
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103CPEW | CROTONA PARK GREENWAY - X010-105M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2006-03-28 | 2007-03-27 | 2007-01-26 | 2023-05-03
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103CPFH | CROTONA PK TENNIS HOUSE - X010-104M/404M | 2 | DESIGN | 2004-09-29 | 2004-12-27 | 2003-09-03 | 2003-12-04
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103CPFH | CROTONA PK TENNIS HOUSE - X010-104M/404M | 3 | BID/ REGISTER CONTRACT | 2004-12-28 | 2005-03-27 | 2003-12-05 | 2004-03-03
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103CPFH | CROTONA PK TENNIS HOUSE - X010-104M/404M | 4 | CONSTRUCTION | 2005-03-28 | 2006-03-27 | 2005-03-05 | 2006-03-06
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103CPFH | CROTONA PK TENNIS HOUSE - X010-104M/404M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2006-03-28 | 2008-02-28 | 2007-03-07 | 2007-05-03
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103CRCS | CROTONA PK COMFORT STATION X010-214M | 1 | DEVELOP SCOPE | 2010-07-01 | 2010-09-28 | 2010-07-01 | 2010-09-28
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103CRCS | CROTONA PK COMFORT STATION X010-214M | 2 | DESIGN | 2010-09-29 | 2010-12-27 | 2010-09-29 | 2016-08-25
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103CRCS | CROTONA PK COMFORT STATION X010-214M | 3 | BID/ REGISTER CONTRACT | 2010-12-28 | 2011-03-27 | 2016-08-26 | 2016-11-23
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103CRCS | CROTONA PK COMFORT STATION X010-214M | 4 | CONSTRUCTION | 2011-03-28 | 2012-03-26 | 2016-11-24 | 2017-11-23
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103CRCS | CROTONA PK COMFORT STATION X010-214M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-03-27 | 2013-03-26 | 2017-11-24 | 2018-11-23
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103CRO1 | CROTONA PK LIGHTING FOR B/F X010-116M | 1 | DEVELOP SCOPE | 2012-07-01 | 2012-09-28 | 2012-07-01 | 2015-08-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103CRO1 | CROTONA PK LIGHTING FOR B/F X010-116M | 2 | DESIGN | 2012-09-29 | 2012-12-27 | 2015-08-27 | 2015-11-24
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103CRO1 | CROTONA PK LIGHTING FOR B/F X010-116M | 3 | BID/ REGISTER CONTRACT | 2012-12-28 | 2013-03-27 | 2015-11-25 | 2016-02-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103CRO1 | CROTONA PK LIGHTING FOR B/F X010-116M | 4 | CONSTRUCTION | 2013-03-28 | 2014-03-27 | 2016-02-23 | 2017-02-21
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103CRO1 | CROTONA PK LIGHTING FOR B/F X010-116M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-03-28 | 2015-03-27 | 2017-02-22 | 2018-02-21
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103DPLS | Drew Playground Security Lighting X021-119M | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103DPLS | Drew Playground Security Lighting X021-119M | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103DPLS | Drew Playground Security Lighting X021-119M | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103DPLS | Drew Playground Security Lighting X021-119M | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103DPLS | Drew Playground Security Lighting X021-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103GARD | HIAWATHA FALLS/COMMUNITY ROCK GARDEN X273-199A2 | 2 | DESIGN | 1998-12-28 | 2000-04-17 | 1998-12-28 | 2000-04-17
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103GARD | HIAWATHA FALLS/COMMUNITY ROCK GARDEN X273-199A2 | 3 | BID/ REGISTER CONTRACT | 2000-07-25 | 2001-06-29 | 2000-07-25 | 2001-06-29
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103GARD | HIAWATHA FALLS/COMMUNITY ROCK GARDEN X273-199A2 | 4 | CONSTRUCTION | 2001-07-05 | 2002-06-29 | 2001-07-05 | 2002-06-29
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103GARD | HIAWATHA FALLS/COMMUNITY ROCK GARDEN X273-199A2 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2003-06-30 | 2004-06-29 | 2003-06-30 | 2004-06-29
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103WPBC | Waring Plgd Basketball Courts Recon (X002-118M) | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2017-10-03
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103WPBC | Waring Plgd Basketball Courts Recon (X002-118M) | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2017-10-04 | 2020-12-10
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103WPBC | Waring Plgd Basketball Courts Recon (X002-118M) | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2019-04-30 | 2019-10-01
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103WPBC | Waring Plgd Basketball Courts Recon (X002-118M) | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2019-12-01 | 2020-11-10
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103WPBC | Waring Plgd Basketball Courts Recon (X002-118M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2020-11-11 | 2025-06-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104AMEN | Amendola Plaza XG-32100-111M | 1 | DEVELOP SCOPE | 2010-07-01 | 2010-09-28 | 2010-07-01 | 2010-09-28
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104AMEN | Amendola Plaza XG-32100-111M | 2 | DESIGN | 2010-09-29 | 2010-12-27 | 2010-09-29 | 2010-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104AMEN | Amendola Plaza XG-32100-111M | 3 | BID/ REGISTER CONTRACT | 2010-12-28 | 2011-03-27 | 2010-12-28 | 2011-03-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104AMEN | Amendola Plaza XG-32100-111M | 4 | CONSTRUCTION | 2011-03-28 | 2012-03-26 | 2011-03-28 | 2012-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104AMEN | Amendola Plaza XG-32100-111M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-03-27 | 2013-03-26 | 2012-03-27 | 2019-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104CAGS | Mullaly Park Recr Center- bronze doors X034-108MA OMBP | 1 | DEVELOP SCOPE | 2003-07-01 | 2003-12-28 | 2009-07-01 | 2012-12-21
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104CAGS | Mullaly Park Recr Center- bronze doors X034-108MA OMBP | 2 | DESIGN | 2003-12-29 | 2004-03-12 | 2012-12-22 | 2013-03-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104CAGS | Mullaly Park Recr Center- bronze doors X034-108MA OMBP | 3 | BID/ REGISTER CONTRACT | 2004-03-13 | 2004-07-28 | 2013-03-23 | 2013-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104CAGS | Mullaly Park Recr Center- bronze doors X034-108MA OMBP | 4 | CONSTRUCTION | 2004-07-29 | 2005-04-22 | 2013-09-23 | 2014-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104CAGS | Mullaly Park Recr Center- bronze doors X034-108MA OMBP | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2005-04-23 | 2006-04-22 | 2014-09-23 | 2019-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104CLMT | Claremont Park Improvements | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104CLMT | Claremont Park Improvements | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104CLMT | Claremont Park Improvements | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104CLMT | Claremont Park Improvements | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104CLMT | Claremont Park Improvements | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2024-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104FIS2 | Cons of Fish Passage Twin Dams | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104FIS2 | Cons of Fish Passage Twin Dams | 2 | DESIGN | 2018-12-28 | 2020-06-19 | 2018-12-28 | 2020-06-19
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104FIS2 | Cons of Fish Passage Twin Dams | 3 | BID/ REGISTER CONTRACT | 2020-06-20 | 2021-03-16 | 2020-06-20 | 2021-03-16
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104FIS2 | Cons of Fish Passage Twin Dams | 4 | CONSTRUCTION | 2021-03-17 | 2023-03-16 | 2021-03-17 | 2023-03-16
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104FIS2 | Cons of Fish Passage Twin Dams | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-03-17 | 2025-03-15 | 2023-03-17 | 2025-03-15
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104FISH | Cons of 182nd St. Fish Passage Dam X002-111M | 1 | DEVELOP SCOPE | 2010-07-01 | 2010-09-28 | 2010-07-01 | 2010-09-28
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104FISH | Cons of 182nd St. Fish Passage Dam X002-111M | 2 | DESIGN | 2010-09-29 | 2010-12-27 | 2010-09-29 | 2010-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104FISH | Cons of 182nd St. Fish Passage Dam X002-111M | 3 | BID/ REGISTER CONTRACT | 2010-12-28 | 2011-03-27 | 2010-12-28 | 2011-03-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104FISH | Cons of 182nd St. Fish Passage Dam X002-111M | 4 | CONSTRUCTION | 2011-03-28 | 2012-03-26 | 2011-03-28 | 2012-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104FISH | Cons of 182nd St. Fish Passage Dam X002-111M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-03-27 | 2013-03-26 | 2012-03-27 | 2021-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104GBLE | Goble Playground- new BBall equip., swings, handball court | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104GBLE | Goble Playground- new BBall equip., swings, handball court | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104GBLE | Goble Playground- new BBall equip., swings, handball court | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104GBLE | Goble Playground- new BBall equip., swings, handball court | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104GBLE | Goble Playground- new BBall equip., swings, handball court | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104GPPV | Grant Avenue Park - Reconst of playground ( X271-115M) | 1 | DEVELOP SCOPE | 2006-07-01 | 2006-09-28 | 2006-07-01 | 2015-03-20
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104GPPV | Grant Avenue Park - Reconst of playground ( X271-115M) | 2 | DESIGN | 2006-09-29 | 2006-12-27 | 2015-03-21 | 2026-02-04
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104GPPV | Grant Avenue Park - Reconst of playground ( X271-115M) | 3 | BID/ REGISTER CONTRACT | 2006-12-28 | 2007-03-27 | 2026-02-05 | 2037-08-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104GPPV | Grant Avenue Park - Reconst of playground ( X271-115M) | 4 | CONSTRUCTION | 2007-03-28 | 2008-03-26 | 2018-08-20 | 2020-02-17
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104GPPV | Grant Avenue Park - Reconst of playground ( X271-115M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-27 | 2009-03-26 | 2020-02-18 | 2022-01-08
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104HGBG | Highbridge Park - step streets/park ldscape X120-110M | 1 | DEVELOP SCOPE | 2007-07-01 | 2007-09-28 | 2007-07-01 | 2011-08-08
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104HGBG | Highbridge Park - step streets/park ldscape X120-110M | 2 | DESIGN | 2007-09-29 | 2007-12-27 | 2011-08-09 | 2022-08-07
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104HGBG | Highbridge Park - step streets/park ldscape X120-110M | 3 | BID/ REGISTER CONTRACT | 2007-12-28 | 2008-03-26 | 2019-02-13 | 2019-05-30
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104HGBG | Highbridge Park - step streets/park ldscape X120-110M | 4 | CONSTRUCTION | 2008-03-27 | 2009-03-26 | 2019-11-30 | 2020-10-15
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104HGBG | Highbridge Park - step streets/park ldscape X120-110M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2009-03-27 | 2010-03-26 | 2020-10-16 | 2033-05-05
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104HPRM | Bridge Park-Highbridge Greenway promenade | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2013-09-28
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104HPRM | Bridge Park-Highbridge Greenway promenade | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2013-09-29 | 2020-12-01
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104HPRM | Bridge Park-Highbridge Greenway promenade | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2020-12-02 | 2021-03-01
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104HPRM | Bridge Park-Highbridge Greenway promenade | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2021-03-02 | 2022-03-01
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104HPRM | Bridge Park-Highbridge Greenway promenade | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2022-03-02 | 2028-02-29
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104JKIL | Joyce Kilmer Park - Fencing (X028-114M) | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2013-11-01
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104JKIL | Joyce Kilmer Park - Fencing (X028-114M) | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2013-11-02 | 2015-08-13
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104JKIL | Joyce Kilmer Park - Fencing (X028-114M) | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2016-05-03 | 2017-02-03
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104JKIL | Joyce Kilmer Park - Fencing (X028-114M) | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2017-03-17 | 2018-03-12
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104JKIL | Joyce Kilmer Park - Fencing (X028-114M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2018-03-13 | 2022-03-31
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104JOYP | JOYCE KILMER PLAYGROUND - X028-103M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2004-11-21 | 2005-11-20 | 2004-11-21 | 2005-11-20
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104JRME | Jerome Playground S- Handball courts renovation | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104JRME | Jerome Playground S- Handball courts renovation | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104JRME | Jerome Playground S- Handball courts renovation | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104JRME | Jerome Playground S- Handball courts renovation | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104JRME | Jerome Playground S- Handball courts renovation | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2024-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104MPSK | Mullaly Park Skate Park Reconstruction | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104MPSK | Mullaly Park Skate Park Reconstruction | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104MPSK | Mullaly Park Skate Park Reconstruction | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104MPSK | Mullaly Park Skate Park Reconstruction | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104MPSK | Mullaly Park Skate Park Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104NELP | Nelson Bleacher Reconstruction-X168-117M | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104NELP | Nelson Bleacher Reconstruction-X168-117M | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2016-12-28 | 2017-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104NELP | Nelson Bleacher Reconstruction-X168-117M | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2017-12-28 | 2018-09-23
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104NELP | Nelson Bleacher Reconstruction-X168-117M | 4 | CONSTRUCTION | 2018-09-24 | 2019-09-23 | 2018-09-24 | 2019-09-23
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104NELP | Nelson Bleacher Reconstruction-X168-117M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2022-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-105GALO | Galileo Playground - bring surface area to grade | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-105GALO | Galileo Playground - bring surface area to grade | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-105GALO | Galileo Playground - bring surface area to grade | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-105GALO | Galileo Playground - bring surface area to grade | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-105GALO | Galileo Playground - bring surface area to grade | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-106CMLT | CROTONA MALLS - MOHEGAN LOT - X334-104M | 1 | DEVELOP SCOPE | 2003-07-01 | 2003-09-28 | 2003-07-01 | 2004-06-25
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-106CMLT | CROTONA MALLS - MOHEGAN LOT - X334-104M | 2 | DESIGN | 2003-09-29 | 2003-12-27 | 2004-06-26 | 2004-11-24
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-106CMLT | CROTONA MALLS - MOHEGAN LOT - X334-104M | 3 | BID/ REGISTER CONTRACT | 2003-12-28 | 2004-03-26 | 2005-01-20 | 2005-04-18
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-106CMLT | CROTONA MALLS - MOHEGAN LOT - X334-104M | 4 | CONSTRUCTION | 2004-03-27 | 2005-03-26 | 2006-07-10 | 2007-04-05
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-106CMLT | CROTONA MALLS - MOHEGAN LOT - X334-104M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2005-03-27 | 2006-03-26 | 2007-04-06 | 2008-04-15
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-106MAPE | CPI Phase 2-Mapes Ballfield-X289-118M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-106MAPE | CPI Phase 2-Mapes Ballfield-X289-118M | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-106MAPE | CPI Phase 2-Mapes Ballfield-X289-118M | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-106MAPE | CPI Phase 2-Mapes Ballfield-X289-118M | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-106MAPE | CPI Phase 2-Mapes Ballfield-X289-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2023-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-106QUAR | Quarry Ballfield-Cons of synthetic turf soccer fd-X263-119M | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-106QUAR | Quarry Ballfield-Cons of synthetic turf soccer fd-X263-119M | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-106QUAR | Quarry Ballfield-Cons of synthetic turf soccer fd-X263-119M | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-106QUAR | Quarry Ballfield-Cons of synthetic turf soccer fd-X263-119M | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-106QUAR | Quarry Ballfield-Cons of synthetic turf soccer fd-X263-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107CPFE | Classic Plgd in Van Cortlandt Park-Install Fitness Equipment | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107CPFE | Classic Plgd in Van Cortlandt Park-Install Fitness Equipment | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107CPFE | Classic Plgd in Van Cortlandt Park-Install Fitness Equipment | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107CPFE | Classic Plgd in Van Cortlandt Park-Install Fitness Equipment | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107CPFE | Classic Plgd in Van Cortlandt Park-Install Fitness Equipment | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107DPDR | Devoe Park- Cons of a Dog Run X013-218M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107DPDR | Devoe Park- Cons of a Dog Run X013-218M | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107DPDR | Devoe Park- Cons of a Dog Run X013-218M | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107DPDR | Devoe Park- Cons of a Dog Run X013-218M | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107DPDR | Devoe Park- Cons of a Dog Run X013-218M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107KOSS | Kossuth Playground Recon X033-118M | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2015-09-28
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107KOSS | Kossuth Playground Recon X033-118M | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2015-09-29 | 2015-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107KOSS | Kossuth Playground Recon X033-118M | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2015-12-28 | 2016-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107KOSS | Kossuth Playground Recon X033-118M | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107KOSS | Kossuth Playground Recon X033-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2017-03-27 | 2021-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107LIGT | World War I monument lighting - Mosholu & Hull X033-111M | 2 | DESIGN | 2010-09-29 | 2010-12-27 | 2010-09-29 | 2010-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107LIGT | World War I monument lighting - Mosholu & Hull X033-111M | 3 | BID/ REGISTER CONTRACT | 2010-12-28 | 2011-03-27 | 2010-12-28 | 2011-03-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107LIGT | World War I monument lighting - Mosholu & Hull X033-111M | 4 | CONSTRUCTION | 2011-03-28 | 2012-03-26 | 2011-03-28 | 2012-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107LIGT | World War I monument lighting - Mosholu & Hull X033-111M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-03-27 | 2013-03-26 | 2012-03-27 | 2013-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107PCOT | POE PARK COTTAGE - RESTORATION X040-108M/408M | 1 | DEVELOP SCOPE | 2006-07-01 | 2006-09-28 | 2006-07-01 | 2007-08-08
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107PCOT | POE PARK COTTAGE - RESTORATION X040-108M/408M | 2 | DESIGN | 2006-09-29 | 2006-12-27 | 2007-08-09 | 2009-08-20
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107PCOT | POE PARK COTTAGE - RESTORATION X040-108M/408M | 3 | BID/ REGISTER CONTRACT | 2006-12-28 | 2007-03-27 | 2009-12-02 | 2010-07-09
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107PCOT | POE PARK COTTAGE - RESTORATION X040-108M/408M | 4 | CONSTRUCTION | 2007-03-28 | 2008-03-26 | 2010-08-02 | 2011-01-28
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107PCOT | POE PARK COTTAGE - RESTORATION X040-108M/408M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-27 | 2009-03-26 | 2011-01-29 | 2014-01-28
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107POEM | Poe Park - Portions of the Bandstand - X040-104M,604M | 3 | BID/ REGISTER CONTRACT | 2004-03-13 | 2004-06-12 | 2004-03-13 | 2004-06-12
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107POEM | Poe Park - Portions of the Bandstand - X040-104M,604M | 4 | CONSTRUCTION | 2004-06-13 | 2005-06-12 | 2004-06-13 | 2005-06-12
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107POEM | Poe Park - Portions of the Bandstand - X040-104M,604M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2005-06-13 | 2006-06-12 | 2005-06-13 | 2006-06-12
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107PPV1 | Poe Park - Poe Cottage - ADA ramp X040-116M | 1 | DEVELOP SCOPE | 2014-07-01 | 2014-09-28 | 2014-07-01 | 2014-09-28
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107PPV1 | Poe Park - Poe Cottage - ADA ramp X040-116M | 2 | DESIGN | 2014-09-29 | 2014-12-27 | 2014-09-29 | 2014-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107PPV1 | Poe Park - Poe Cottage - ADA ramp X040-116M | 3 | BID/ REGISTER CONTRACT | 2014-12-28 | 2015-03-27 | 2014-12-28 | 2015-03-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107PPV1 | Poe Park - Poe Cottage - ADA ramp X040-116M | 4 | CONSTRUCTION | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2016-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107PPV1 | Poe Park - Poe Cottage - ADA ramp X040-116M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2021-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107SJDR | St. James Park--Dog Run- X044-118M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107SJDR | St. James Park--Dog Run- X044-118M | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107SJDR | St. James Park--Dog Run- X044-118M | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107SJDR | St. James Park--Dog Run- X044-118M | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107SJDR | St. James Park--Dog Run- X044-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107SJHV | ST. JAMES PARK HVAC X044-113M | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2013-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107SJHV | ST. JAMES PARK HVAC X044-113M | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2013-12-28 | 2015-03-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107SJHV | ST. JAMES PARK HVAC X044-113M | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2015-03-28 | 2015-12-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107SJHV | ST. JAMES PARK HVAC X044-113M | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2015-12-23 | 2016-12-21
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107SJHV | ST. JAMES PARK HVAC X044-113M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2016-12-22 | 2021-12-21
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107SJRC | MISC PARKS, PLGDS, CONS, RC, BX-ST JAMES PARK REC CTR RENOV. | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107SJRC | MISC PARKS, PLGDS, CONS, RC, BX-ST JAMES PARK REC CTR RENOV. | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107SJRC | MISC PARKS, PLGDS, CONS, RC, BX-ST JAMES PARK REC CTR RENOV. | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107SJRC | MISC PARKS, PLGDS, CONS, RC, BX-ST JAMES PARK REC CTR RENOV. | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107SJRC | MISC PARKS, PLGDS, CONS, RC, BX-ST JAMES PARK REC CTR RENOV. | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107STFA | ST. James Rec. Center: Fire Alarm Reconstruction | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107STFA | ST. James Rec. Center: Fire Alarm Reconstruction | 2 | DESIGN | 2019-12-28 | 2021-12-26 | 2019-12-28 | 2021-12-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107STFA | ST. James Rec. Center: Fire Alarm Reconstruction | 3 | BID/ REGISTER CONTRACT | 2021-12-27 | 2022-09-22 | 2021-12-27 | 2022-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107STFA | ST. James Rec. Center: Fire Alarm Reconstruction | 4 | CONSTRUCTION | 2022-09-23 | 2025-09-21 | 2022-09-23 | 2025-09-21
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107STFA | ST. James Rec. Center: Fire Alarm Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-09-22 | 2027-09-21 | 2025-09-22 | 2027-09-21
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107WBSK | Williamsbridge Oval const Skate Park- X104-115M | 1 | DEVELOP SCOPE | 2014-07-01 | 2014-09-28 | 2014-07-01 | 2015-05-18
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107WBSK | Williamsbridge Oval const Skate Park- X104-115M | 2 | DESIGN | 2014-09-29 | 2014-12-27 | 2015-05-19 | 2017-02-11
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107WBSK | Williamsbridge Oval const Skate Park- X104-115M | 3 | BID/ REGISTER CONTRACT | 2014-12-28 | 2015-03-27 | 2016-11-01 | 2018-01-04
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107WBSK | Williamsbridge Oval const Skate Park- X104-115M | 4 | CONSTRUCTION | 2015-03-28 | 2016-03-26 | 2018-02-26 | 2019-03-01
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107WBSK | Williamsbridge Oval const Skate Park- X104-115M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-27 | 2017-03-26 | 2019-03-02 | 2024-03-01
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108EWNP | Ewen Park Installation of adult fitness equipment(X019-119M) | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108EWNP | Ewen Park Installation of adult fitness equipment(X019-119M) | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108EWNP | Ewen Park Installation of adult fitness equipment(X019-119M) | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108EWNP | Ewen Park Installation of adult fitness equipment(X019-119M) | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108EWNP | Ewen Park Installation of adult fitness equipment(X019-119M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108FTFR | Washington's Walk Fort Four Plgd comfort station- X038-118M | 1 | DEVELOP SCOPE | 2014-07-01 | 2014-09-28 | 2014-07-01 | 2017-09-28
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108FTFR | Washington's Walk Fort Four Plgd comfort station- X038-118M | 2 | DESIGN | 2014-09-29 | 2014-12-27 | 2017-09-29 | 2017-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108FTFR | Washington's Walk Fort Four Plgd comfort station- X038-118M | 3 | BID/ REGISTER CONTRACT | 2014-12-28 | 2015-03-27 | 2017-12-28 | 2018-03-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108FTFR | Washington's Walk Fort Four Plgd comfort station- X038-118M | 4 | CONSTRUCTION | 2015-03-28 | 2016-03-26 | 2018-03-28 | 2019-03-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108FTFR | Washington's Walk Fort Four Plgd comfort station- X038-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-27 | 2017-03-26 | 2019-03-28 | 2020-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108HHPK | Henry Hudson Park basketball court renovation (X080-115M) | 1 | DEVELOP SCOPE | 2014-07-01 | 2014-09-28 | 2014-07-01 | 2014-09-28
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108HHPK | Henry Hudson Park basketball court renovation (X080-115M) | 2 | DESIGN | 2014-09-29 | 2014-12-27 | 2014-09-29 | 2014-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108HHPK | Henry Hudson Park basketball court renovation (X080-115M) | 3 | BID/ REGISTER CONTRACT | 2014-12-28 | 2015-03-27 | 2014-12-28 | 2015-03-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108HHPK | Henry Hudson Park basketball court renovation (X080-115M) | 4 | CONSTRUCTION | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2016-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108HHPK | Henry Hudson Park basketball court renovation (X080-115M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2024-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108MUSM | Van Cortlandt Park - House Museum Renovation | 1 | DEVELOP SCOPE | 2020-07-01 | 2020-12-27 | 2020-07-01 | 2020-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108MUSM | Van Cortlandt Park - House Museum Renovation | 2 | DESIGN | 2020-12-28 | 2021-12-27 | 2020-12-28 | 2021-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108MUSM | Van Cortlandt Park - House Museum Renovation | 3 | BID/ REGISTER CONTRACT | 2021-12-28 | 2022-09-23 | 2021-12-28 | 2022-09-23
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108MUSM | Van Cortlandt Park - House Museum Renovation | 4 | CONSTRUCTION | 2022-09-24 | 2023-09-23 | 2022-09-24 | 2023-09-23
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108MUSM | Van Cortlandt Park - House Museum Renovation | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-09-24 | 2024-09-22 | 2023-09-24 | 2024-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108RIVE | RIVERDALE PARK-WETLANDS & SLOPES / X142-101M | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108RIVE | RIVERDALE PARK-WETLANDS & SLOPES / X142-101M | 2 | DESIGN | 2016-12-28 | 2017-09-23 | 2016-12-28 | 2017-09-23
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108RIVE | RIVERDALE PARK-WETLANDS & SLOPES / X142-101M | 3 | BID/ REGISTER CONTRACT | 2017-09-24 | 2018-06-20 | 2017-09-24 | 2018-06-20
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108RIVE | RIVERDALE PARK-WETLANDS & SLOPES / X142-101M | 4 | CONSTRUCTION | 2018-06-21 | 2020-12-16 | 2018-06-21 | 2020-12-16
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108RIVE | RIVERDALE PARK-WETLANDS & SLOPES / X142-101M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-12-17 | 2022-12-16 | 2020-12-17 | 2022-12-16
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108SETN | Seton Park soccer & ball field X201-113M | 1 | DEVELOP SCOPE | 2011-07-01 | 2011-09-28 | 2011-07-01 | 2011-09-28
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108SETN | Seton Park soccer & ball field X201-113M | 2 | DESIGN | 2011-09-29 | 2011-12-27 | 2011-09-29 | 2011-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108SETN | Seton Park soccer & ball field X201-113M | 3 | BID/ REGISTER CONTRACT | 2011-12-28 | 2012-03-26 | 2011-12-28 | 2012-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108SETN | Seton Park soccer & ball field X201-113M | 4 | CONSTRUCTION | 2012-03-27 | 2013-03-26 | 2012-03-27 | 2013-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108SETN | Seton Park soccer & ball field X201-113M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-03-27 | 2014-03-26 | 2013-03-27 | 2024-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108SKTE | Van Cortlandt Park - Skate park & Basketballl cou(X092-114M) | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2015-01-18
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108SKTE | Van Cortlandt Park - Skate park & Basketballl cou(X092-114M) | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2015-01-19 | 2015-08-07
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108SKTE | Van Cortlandt Park - Skate park & Basketballl cou(X092-114M) | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2015-12-10 | 2016-11-04
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108SKTE | Van Cortlandt Park - Skate park & Basketballl cou(X092-114M) | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2017-02-13 | 2018-02-15
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108SKTE | Van Cortlandt Park - Skate park & Basketballl cou(X092-114M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2018-02-16 | 2024-02-20
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108SPBC | Seton Park Basketball Court Recon (X201-220M) | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2015-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108SPBC | Seton Park Basketball Court Recon (X201-220M) | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2015-12-28 | 2016-12-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108SPBC | Seton Park Basketball Court Recon (X201-220M) | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2016-12-27 | 2017-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108SPBC | Seton Park Basketball Court Recon (X201-220M) | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2017-09-23 | 2018-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108SPBC | Seton Park Basketball Court Recon (X201-220M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2018-09-23 | 2021-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108SPDU | Spuyten Duyvil Park - pond restoration- X171-116M | 1 | DEVELOP SCOPE | 2006-07-01 | 2006-09-28 | 2006-07-01 | 2016-02-17
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108SPDU | Spuyten Duyvil Park - pond restoration- X171-116M | 2 | DESIGN | 2006-09-29 | 2006-12-27 | 2016-02-18 | 2026-07-23
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108SPDU | Spuyten Duyvil Park - pond restoration- X171-116M | 3 | BID/ REGISTER CONTRACT | 2006-12-28 | 2007-03-27 | 2018-02-22 | 2018-07-24
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108SPDU | Spuyten Duyvil Park - pond restoration- X171-116M | 4 | CONSTRUCTION | 2007-03-28 | 2008-03-26 | 2018-09-25 | 2019-09-24
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108SPDU | Spuyten Duyvil Park - pond restoration- X171-116M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-27 | 2009-03-26 | 2019-09-25 | 2020-09-25
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108VCBD | Van Cortlandt Pk. Tot Lot Recon (X092-115M) | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2015-09-28
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108VCBD | Van Cortlandt Pk. Tot Lot Recon (X092-115M) | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2015-09-29 | 2017-06-29
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108VCBD | Van Cortlandt Pk. Tot Lot Recon (X092-115M) | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2018-03-30 | 2018-10-15
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108VCBD | Van Cortlandt Pk. Tot Lot Recon (X092-115M) | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2018-10-16 | 2020-03-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108VCBD | Van Cortlandt Pk. Tot Lot Recon (X092-115M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2020-03-28 | 2024-03-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108VCIW | Van Cortlandt Park renovate Indian Fields (X092-215M) | 1 | DEVELOP SCOPE | 2014-07-01 | 2014-09-28 | 2014-07-01 | 2014-09-28
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108VCIW | Van Cortlandt Park renovate Indian Fields (X092-215M) | 2 | DESIGN | 2014-09-29 | 2014-12-27 | 2014-09-29 | 2014-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108VCIW | Van Cortlandt Park renovate Indian Fields (X092-215M) | 3 | BID/ REGISTER CONTRACT | 2014-12-28 | 2015-03-27 | 2014-12-28 | 2015-03-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108VCIW | Van Cortlandt Park renovate Indian Fields (X092-215M) | 4 | CONSTRUCTION | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2016-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108VCIW | Van Cortlandt Park renovate Indian Fields (X092-215M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2024-04-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108VCPT | Van Cortlandt Park Trails Recon (X092- | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2015-09-28
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108VCPT | Van Cortlandt Park Trails Recon (X092- | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2015-09-29 | 2015-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108VCPT | Van Cortlandt Park Trails Recon (X092- | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2015-12-28 | 2016-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108VCPT | Van Cortlandt Park Trails Recon (X092- | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108VCPT | Van Cortlandt Park Trails Recon (X092- | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2017-03-27 | 2024-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108WDLN | WOODLAWN PARK RENOVATIONS | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108WDLN | WOODLAWN PARK RENOVATIONS | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108WDLN | WOODLAWN PARK RENOVATIONS | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108WDLN | WOODLAWN PARK RENOVATIONS | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108WDLN | WOODLAWN PARK RENOVATIONS | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108WWST | Strong Street Plg Reconstruction | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108WWST | Strong Street Plg Reconstruction | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108WWST | Strong Street Plg Reconstruction | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108WWST | Strong Street Plg Reconstruction | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108WWST | Strong Street Plg Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-109NBLE | Noble Playground - RC Comfort Station X123-118M | 1 | DEVELOP SCOPE | 2014-04-21 | 2014-07-19 | 2014-04-21 | 2017-07-19
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-109NBLE | Noble Playground - RC Comfort Station X123-118M | 2 | DESIGN | 2014-07-20 | 2014-10-17 | 2017-07-20 | 2017-10-17
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-109NBLE | Noble Playground - RC Comfort Station X123-118M | 3 | BID/ REGISTER CONTRACT | 2014-10-18 | 2015-01-15 | 2017-10-18 | 2018-01-15
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-109NBLE | Noble Playground - RC Comfort Station X123-118M | 4 | CONSTRUCTION | 2015-01-16 | 2016-01-15 | 2018-01-16 | 2019-01-15
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-109NBLE | Noble Playground - RC Comfort Station X123-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-01-16 | 2017-01-14 | 2019-01-16 | 2020-01-15
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-109NOBE | Noble Playground Reconstruction (X123-119M) | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-109NOBE | Noble Playground Reconstruction (X123-119M) | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-109NOBE | Noble Playground Reconstruction (X123-119M) | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-109NOBE | Noble Playground Reconstruction (X123-119M) | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-109NOBE | Noble Playground Reconstruction (X123-119M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-109PAR2 | Parque de los Ninos Ph II - track & BField X004A-114M | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2014-03-09
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-109PAR2 | Parque de los Ninos Ph II - track & BField X004A-114M | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2014-03-10 | 2016-09-16
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-109PAR2 | Parque de los Ninos Ph II - track & BField X004A-114M | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2016-09-13 | 2018-05-31
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-109PAR2 | Parque de los Ninos Ph II - track & BField X004A-114M | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2018-08-06 | 2019-08-06
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-109PAR2 | Parque de los Ninos Ph II - track & BField X004A-114M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2019-08-07 | 2020-08-07
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110CCCS | Co-Op City Park - Comfort Station | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110CCCS | Co-Op City Park - Comfort Station | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110CCCS | Co-Op City Park - Comfort Station | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110CCCS | Co-Op City Park - Comfort Station | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110CCCS | Co-Op City Park - Comfort Station | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2023-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110CCTY | Co-Op City Park | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110CCTY | Co-Op City Park | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110CCTY | Co-Op City Park | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110CCTY | Co-Op City Park | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110CCTY | Co-Op City Park | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2024-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110CIDR | City Island Dog Run | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110CIDR | City Island Dog Run | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110CIDR | City Island Dog Run | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110CIDR | City Island Dog Run | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110CIDR | City Island Dog Run | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110EXPA | ORCHARD BEACH BATHHOUSE -- X039-102M/402M | 1 | DEVELOP SCOPE | 2003-01-05 | 2003-03-04 | 2003-01-05 | 2003-03-04
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110EXPA | ORCHARD BEACH BATHHOUSE -- X039-102M/402M | 2 | DESIGN | 2003-03-05 | 2003-03-31 | 2003-03-05 | 2003-03-31
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110EXPA | ORCHARD BEACH BATHHOUSE -- X039-102M/402M | 3 | BID/ REGISTER CONTRACT | 2003-04-01 | 2004-03-31 | 2003-04-01 | 2004-03-31
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110EXPA | ORCHARD BEACH BATHHOUSE -- X039-102M/402M | 4 | CONSTRUCTION | 2004-04-01 | 2005-04-01 | 2004-04-01 | 2005-04-01
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110EXPA | ORCHARD BEACH BATHHOUSE -- X039-102M/402M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2005-04-02 | 2006-03-30 | 2005-04-02 | 2006-03-30
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110MAN2 | Bartow Mansion Structural Stabilization&Carriage House Roof | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110MAN2 | Bartow Mansion Structural Stabilization&Carriage House Roof | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110MAN2 | Bartow Mansion Structural Stabilization&Carriage House Roof | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110MAN2 | Bartow Mansion Structural Stabilization&Carriage House Roof | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110MAN2 | Bartow Mansion Structural Stabilization&Carriage House Roof | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110MANS | PDF - BARTOW PELL MANSION - PORTIONS OF BUILDING X039-506M | 1 | DEVELOP SCOPE | 2006-07-01 | 2006-09-28 | 2006-07-01 | 2006-09-28
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110MANS | PDF - BARTOW PELL MANSION - PORTIONS OF BUILDING X039-506M | 2 | DESIGN | 2006-09-29 | 2006-12-27 | 2006-09-29 | 2006-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110MANS | PDF - BARTOW PELL MANSION - PORTIONS OF BUILDING X039-506M | 3 | BID/ REGISTER CONTRACT | 2006-12-28 | 2007-03-27 | 2006-12-28 | 2007-03-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110MANS | PDF - BARTOW PELL MANSION - PORTIONS OF BUILDING X039-506M | 4 | CONSTRUCTION | 2007-03-28 | 2008-03-26 | 2007-03-28 | 2008-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110MANS | PDF - BARTOW PELL MANSION - PORTIONS OF BUILDING X039-506M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-27 | 2009-03-26 | 2008-03-27 | 2021-12-30
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110ODFA | Owen Dolen Rec. Center: Fire Alarm Reconstruction | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110ODFA | Owen Dolen Rec. Center: Fire Alarm Reconstruction | 2 | DESIGN | 2019-12-28 | 2021-12-26 | 2019-12-28 | 2021-12-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110ODFA | Owen Dolen Rec. Center: Fire Alarm Reconstruction | 3 | BID/ REGISTER CONTRACT | 2021-12-27 | 2022-09-22 | 2021-12-27 | 2022-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110ODFA | Owen Dolen Rec. Center: Fire Alarm Reconstruction | 4 | CONSTRUCTION | 2022-09-23 | 2025-09-21 | 2022-09-23 | 2025-09-21
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110ODFA | Owen Dolen Rec. Center: Fire Alarm Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-09-22 | 2027-09-21 | 2025-09-22 | 2027-09-21
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110PBBL | Pelham Bay Park Svc Bldg. Heating Recon. X039-115M | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2015-09-29 | 2015-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110PBBL | Pelham Bay Park Svc Bldg. Heating Recon. X039-115M | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2015-12-28 | 2016-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110PBBL | Pelham Bay Park Svc Bldg. Heating Recon. X039-115M | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110PBBL | Pelham Bay Park Svc Bldg. Heating Recon. X039-115M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2017-03-27 | 2021-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110PFIT | Pelham bay Park - construction of fitness area X039-213M | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2013-09-28
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110PFIT | Pelham bay Park - construction of fitness area X039-213M | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2013-09-29 | 2013-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110PFIT | Pelham bay Park - construction of fitness area X039-213M | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2013-12-28 | 2014-03-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110PFIT | Pelham bay Park - construction of fitness area X039-213M | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2014-03-28 | 2015-03-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110PFIT | Pelham bay Park - construction of fitness area X039-213M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2024-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110PSKT | PELHAM BAY PK- Renovation of Skate Park (X039-220M) | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110PSKT | PELHAM BAY PK- Renovation of Skate Park (X039-220M) | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110PSKT | PELHAM BAY PK- Renovation of Skate Park (X039-220M) | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110PSKT | PELHAM BAY PK- Renovation of Skate Park (X039-220M) | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110PSKT | PELHAM BAY PK- Renovation of Skate Park (X039-220M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-111BPWF | Bronx PK- Installation of a water fountain | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-111BPWF | Bronx PK- Installation of a water fountain | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-111BPWF | Bronx PK- Installation of a water fountain | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-111BPWF | Bronx PK- Installation of a water fountain | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-111BPWF | Bronx PK- Installation of a water fountain | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-111FFBB | FRISCH FIELD IN BRONX PK- RENO OF BBALL FIELD | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-111FFBB | FRISCH FIELD IN BRONX PK- RENO OF BBALL FIELD | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-111FFBB | FRISCH FIELD IN BRONX PK- RENO OF BBALL FIELD | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-111FFBB | FRISCH FIELD IN BRONX PK- RENO OF BBALL FIELD | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-111FFBB | FRISCH FIELD IN BRONX PK- RENO OF BBALL FIELD | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-111LPFE | Cons. of Adult Fitness Equip in Colucci Pk. (X122-117M) | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-111LPFE | Cons. of Adult Fitness Equip in Colucci Pk. (X122-117M) | 2 | DESIGN | 2016-12-28 | 2018-06-25 | 2016-12-28 | 2018-06-25
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-111LPFE | Cons. of Adult Fitness Equip in Colucci Pk. (X122-117M) | 3 | BID/ REGISTER CONTRACT | 2018-06-26 | 2019-03-22 | 2018-06-26 | 2019-03-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-111LPFE | Cons. of Adult Fitness Equip in Colucci Pk. (X122-117M) | 4 | CONSTRUCTION | 2019-03-23 | 2020-09-17 | 2019-03-23 | 2020-09-17
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-111LPFE | Cons. of Adult Fitness Equip in Colucci Pk. (X122-117M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-18 | 2021-09-17 | 2020-09-18 | 2021-09-17
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-111LRTO | Loreto Park - Recon Soccer field Asphalt to Turf (X163-118M | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2015-09-28
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-111LRTO | Loreto Park - Recon Soccer field Asphalt to Turf (X163-118M | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2015-09-29 | 2015-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-111LRTO | Loreto Park - Recon Soccer field Asphalt to Turf (X163-118M | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2015-12-28 | 2016-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-111LRTO | Loreto Park - Recon Soccer field Asphalt to Turf (X163-118M | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-111LRTO | Loreto Park - Recon Soccer field Asphalt to Turf (X163-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2017-03-27 | 2021-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-111MULI | MATTHEWS/MULLINER PLGD- X178-104M | 1 | DEVELOP SCOPE | 2003-07-01 | 2003-12-28 | 2003-07-01 | 2003-12-28
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-111MULI | MATTHEWS/MULLINER PLGD- X178-104M | 2 | DESIGN | 2003-12-29 | 2004-03-01 | 2003-12-29 | 2004-03-01
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-111MULI | MATTHEWS/MULLINER PLGD- X178-104M | 3 | BID/ REGISTER CONTRACT | 2004-03-02 | 2004-06-01 | 2004-03-02 | 2004-06-01
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-111MULI | MATTHEWS/MULLINER PLGD- X178-104M | 4 | CONSTRUCTION | 2004-06-02 | 2005-06-01 | 2004-06-02 | 2005-06-01
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-111MULI | MATTHEWS/MULLINER PLGD- X178-104M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2005-06-02 | 2006-06-01 | 2005-06-02 | 2006-06-01
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-111VCPE | PWOB - Van Cortlandt Park Broadway Entrance Recon- X092-217M | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-11-10
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-111VCPE | PWOB - Van Cortlandt Park Broadway Entrance Recon- X092-217M | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2016-11-11 | 2017-11-12
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-111VCPE | PWOB - Van Cortlandt Park Broadway Entrance Recon- X092-217M | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2017-11-13 | 2018-11-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-111VCPE | PWOB - Van Cortlandt Park Broadway Entrance Recon- X092-217M | 4 | CONSTRUCTION | 2018-09-24 | 2019-09-23 | 2018-11-27 | 2020-05-28
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-111VCPE | PWOB - Van Cortlandt Park Broadway Entrance Recon- X092-217M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-24 | 2020-09-22 | 2020-05-29 | 2022-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-111ZIMP | Zimmerman Playground Basketball Court Recon.-X087-118M | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-111ZIMP | Zimmerman Playground Basketball Court Recon.-X087-118M | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2016-12-28 | 2017-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-111ZIMP | Zimmerman Playground Basketball Court Recon.-X087-118M | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2017-12-28 | 2018-09-23
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-111ZIMP | Zimmerman Playground Basketball Court Recon.-X087-118M | 4 | CONSTRUCTION | 2018-09-24 | 2019-09-23 | 2018-09-24 | 2019-09-23
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-111ZIMP | Zimmerman Playground Basketball Court Recon.-X087-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2024-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-112AGNS | Agnes Haywood Park - basketball court & park house X169-114M | 1 | DEVELOP SCOPE | 2010-07-01 | 2010-09-28 | 2010-07-01 | 2015-03-03
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-112AGNS | Agnes Haywood Park - basketball court & park house X169-114M | 2 | DESIGN | 2010-09-29 | 2010-12-27 | 2015-03-04 | 2020-09-10
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-112AGNS | Agnes Haywood Park - basketball court & park house X169-114M | 3 | BID/ REGISTER CONTRACT | 2010-12-28 | 2011-03-27 | 2016-07-07 | 2017-06-20
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-112AGNS | Agnes Haywood Park - basketball court & park house X169-114M | 4 | CONSTRUCTION | 2011-03-28 | 2012-03-26 | 2017-07-10 | 2019-03-18
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-112AGNS | Agnes Haywood Park - basketball court & park house X169-114M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-03-27 | 2013-03-26 | 2019-03-19 | 2022-03-18
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-112LACE | BX River Shoelace Pk- Recon of Paths & Entrance (X004-117M) | 1 | DEVELOP SCOPE | 2015-10-01 | 2016-03-28 | 2015-10-01 | 2016-03-28
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-112LACE | BX River Shoelace Pk- Recon of Paths & Entrance (X004-117M) | 2 | DESIGN | 2016-03-29 | 2017-06-26 | 2016-03-29 | 2017-06-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-112LACE | BX River Shoelace Pk- Recon of Paths & Entrance (X004-117M) | 3 | BID/ REGISTER CONTRACT | 2017-06-27 | 2018-03-23 | 2017-06-27 | 2018-03-23
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-112LACE | BX River Shoelace Pk- Recon of Paths & Entrance (X004-117M) | 4 | CONSTRUCTION | 2018-03-24 | 2019-03-23 | 2018-03-24 | 2019-03-23
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-112LACE | BX River Shoelace Pk- Recon of Paths & Entrance (X004-117M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-03-24 | 2020-03-22 | 2019-03-24 | 2021-03-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-112SETW | Seton Falls Park Walkways Renovations X092-113M | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-112SETW | Seton Falls Park Walkways Renovations X092-113M | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-112SETW | Seton Falls Park Walkways Renovations X092-113M | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-112SETW | Seton Falls Park Walkways Renovations X092-113M | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-112SETW | Seton Falls Park Walkways Renovations X092-113M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-112WKFD | Wakefield Park Reconstruction (X188-116M) | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2016-12-07
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-112WKFD | Wakefield Park Reconstruction (X188-116M) | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2016-12-08 | 2020-03-13
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-112WKFD | Wakefield Park Reconstruction (X188-116M) | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2020-03-14 | 2020-06-11
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-112WKFD | Wakefield Park Reconstruction (X188-116M) | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2020-06-12 | 2021-06-11
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-112WKFD | Wakefield Park Reconstruction (X188-116M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2021-06-12 | 2023-06-11
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-113LLSF | Resurfacing of little league fields and sports field in CD13 | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-113LLSF | Resurfacing of little league fields and sports field in CD13 | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-113LLSF | Resurfacing of little league fields and sports field in CD13 | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-113LLSF | Resurfacing of little league fields and sports field in CD13 | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-113LLSF | Resurfacing of little league fields and sports field in CD13 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-117CPBM | Crotona Park- Install Bluelight Monitors in CD17 | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-117CPBM | Crotona Park- Install Bluelight Monitors in CD17 | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-117CPBM | Crotona Park- Install Bluelight Monitors in CD17 | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-117CPBM | Crotona Park- Install Bluelight Monitors in CD17 | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-117CPBM | Crotona Park- Install Bluelight Monitors in CD17 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-118FOXP | FOX PLAYGROUND C/S X247-118M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-118FOXP | FOX PLAYGROUND C/S X247-118M | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-118FOXP | FOX PLAYGROUND C/S X247-118M | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-118FOXP | FOX PLAYGROUND C/S X247-118M | 4 | CONSTRUCTION | 2019-09-24 | 2021-03-21 | 2019-09-24 | 2021-03-21
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-118FOXP | FOX PLAYGROUND C/S X247-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-22 | 2022-03-21 | 2021-03-22 | 2022-03-21
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1ANCH01 | Anchor Pk St.Mary's Park Ballfields &Dog Run Recon X045-318M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1ANCH01 | Anchor Pk St.Mary's Park Ballfields &Dog Run Recon X045-318M | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1ANCH01 | Anchor Pk St.Mary's Park Ballfields &Dog Run Recon X045-318M | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1ANCH01 | Anchor Pk St.Mary's Park Ballfields &Dog Run Recon X045-318M | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1ANCH01 | Anchor Pk St.Mary's Park Ballfields &Dog Run Recon X045-318M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1ANCH02 | St. Mary's Anchor Pk Ph. 2-Amphi, Plaza &Pathways X045-218M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1ANCH02 | St. Mary's Anchor Pk Ph. 2-Amphi, Plaza &Pathways X045-218M | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1ANCH02 | St. Mary's Anchor Pk Ph. 2-Amphi, Plaza &Pathways X045-218M | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1ANCH02 | St. Mary's Anchor Pk Ph. 2-Amphi, Plaza &Pathways X045-218M | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1ANCH02 | St. Mary's Anchor Pk Ph. 2-Amphi, Plaza &Pathways X045-218M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1AQWALK | MLK Triangle/Aqueduct Walk X001-114M | 1 | DEVELOP SCOPE | 2010-07-01 | 2010-09-28 | 2010-07-01 | 2010-09-28
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1AQWALK | MLK Triangle/Aqueduct Walk X001-114M | 2 | DESIGN | 2010-09-29 | 2010-12-27 | 2010-09-29 | 2010-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1AQWALK | MLK Triangle/Aqueduct Walk X001-114M | 3 | BID/ REGISTER CONTRACT | 2010-12-28 | 2011-03-27 | 2010-12-28 | 2011-03-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1AQWALK | MLK Triangle/Aqueduct Walk X001-114M | 4 | CONSTRUCTION | 2011-03-28 | 2012-03-26 | 2011-03-28 | 2012-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1AQWALK | MLK Triangle/Aqueduct Walk X001-114M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-03-27 | 2013-03-26 | 2012-03-27 | 2021-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1ARAMEZ | Mezzanine dsgn & cons Aramark Bldg Shops & store X360-119M | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1ARAMEZ | Mezzanine dsgn & cons Aramark Bldg Shops & store X360-119M | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1ARAMEZ | Mezzanine dsgn & cons Aramark Bldg Shops & store X360-119M | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1ARAMEZ | Mezzanine dsgn & cons Aramark Bldg Shops & store X360-119M | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1ARAMEZ | Mezzanine dsgn & cons Aramark Bldg Shops & store X360-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BARTOW | BARTOW PELL MANSION SEPTIC TANK REPLACEMENT - X039-105M | 2 | DESIGN | 2006-09-29 | 2006-12-27 | 2006-09-29 | 2006-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BARTOW | BARTOW PELL MANSION SEPTIC TANK REPLACEMENT - X039-105M | 3 | BID/ REGISTER CONTRACT | 2006-12-28 | 2007-03-27 | 2006-12-28 | 2007-03-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BARTOW | BARTOW PELL MANSION SEPTIC TANK REPLACEMENT - X039-105M | 4 | CONSTRUCTION | 2007-03-28 | 2008-03-26 | 2007-03-28 | 2008-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BARTOW | BARTOW PELL MANSION SEPTIC TANK REPLACEMENT - X039-105M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-27 | 2009-03-26 | 2008-03-27 | 2009-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BATHGA | Bathgate Avenue Park - X252-102MA | 1 | DEVELOP SCOPE | 2003-01-05 | 2003-02-20 | 2003-01-05 | 2003-02-20
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BATHGA | Bathgate Avenue Park - X252-102MA | 2 | DESIGN | 2003-02-21 | 2003-03-26 | 2003-02-21 | 2003-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BATHGA | Bathgate Avenue Park - X252-102MA | 3 | BID/ REGISTER CONTRACT | 2003-03-27 | 2004-03-26 | 2003-03-27 | 2004-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BATHGA | Bathgate Avenue Park - X252-102MA | 4 | CONSTRUCTION | 2004-03-27 | 2005-03-26 | 2004-03-27 | 2005-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BATHGA | Bathgate Avenue Park - X252-102MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2005-03-27 | 2006-03-26 | 2005-03-27 | 2006-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BCREQ5 | REQUIREMENTS - BRONX XG-305M | 1 | DEVELOP SCOPE | 2006-07-01 | 2006-09-28 | 2006-07-01 | 2006-09-28
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BCREQ5 | REQUIREMENTS - BRONX XG-305M | 2 | DESIGN | 2006-09-29 | 2006-12-27 | 2006-09-29 | 2006-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BCREQ5 | REQUIREMENTS - BRONX XG-305M | 3 | BID/ REGISTER CONTRACT | 2006-12-28 | 2007-03-27 | 2006-12-28 | 2007-03-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BCREQ5 | REQUIREMENTS - BRONX XG-305M | 4 | CONSTRUCTION | 2007-03-28 | 2008-03-26 | 2007-03-28 | 2008-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BCREQ5 | REQUIREMENTS - BRONX XG-305M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-27 | 2009-03-26 | 2008-03-27 | 2009-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BCSHV1 | BRONX - ELEC OFFICIALS BLDG REQ - HVAC XG-408M | 2 | DESIGN | 2008-09-29 | 2008-12-27 | 2008-09-29 | 2008-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BCSHV1 | BRONX - ELEC OFFICIALS BLDG REQ - HVAC XG-408M | 3 | BID/ REGISTER CONTRACT | 2008-12-28 | 2009-03-27 | 2008-12-28 | 2009-03-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BCSHV1 | BRONX - ELEC OFFICIALS BLDG REQ - HVAC XG-408M | 4 | CONSTRUCTION | 2009-03-28 | 2010-03-27 | 2009-03-28 | 2010-03-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BCSHV1 | BRONX - ELEC OFFICIALS BLDG REQ - HVAC XG-408M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2010-03-28 | 2011-03-27 | 2010-03-28 | 2011-03-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BCSPL1 | BRONX - ELEC OFFICIALS BLDG REQ - PLMB XG-308M | 1 | DEVELOP SCOPE | 2008-07-01 | 2008-09-28 | 2008-07-01 | 2008-09-28
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BCSPL1 | BRONX - ELEC OFFICIALS BLDG REQ - PLMB XG-308M | 2 | DESIGN | 2008-09-29 | 2008-12-27 | 2008-09-29 | 2008-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BCSPL1 | BRONX - ELEC OFFICIALS BLDG REQ - PLMB XG-308M | 3 | BID/ REGISTER CONTRACT | 2008-12-28 | 2009-03-27 | 2008-12-28 | 2009-03-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BCSPL1 | BRONX - ELEC OFFICIALS BLDG REQ - PLMB XG-308M | 4 | CONSTRUCTION | 2009-03-28 | 2010-03-27 | 2009-03-28 | 2010-03-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BCSPL1 | BRONX - ELEC OFFICIALS BLDG REQ - PLMB XG-308M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2010-03-28 | 2011-03-27 | 2010-03-28 | 2021-03-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BRTPEL | BARTOW PELL MANSION RESTORE THE ORANGERIE | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BRTPEL | BARTOW PELL MANSION RESTORE THE ORANGERIE | 2 | DESIGN | 2019-12-28 | 2021-12-26 | 2019-12-28 | 2021-12-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BRTPEL | BARTOW PELL MANSION RESTORE THE ORANGERIE | 3 | BID/ REGISTER CONTRACT | 2021-12-27 | 2022-09-22 | 2021-12-27 | 2022-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BRTPEL | BARTOW PELL MANSION RESTORE THE ORANGERIE | 4 | CONSTRUCTION | 2022-09-23 | 2024-09-21 | 2022-09-23 | 2024-09-21
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BRTPEL | BARTOW PELL MANSION RESTORE THE ORANGERIE | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-09-22 | 2025-09-21 | 2024-09-22 | 2025-09-21
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BRUCKN | Bruckner Soundview Greenway Connection - XG-31700-104M | 1 | DEVELOP SCOPE | 2007-07-01 | 2007-09-28 | 2007-07-01 | 2007-09-28
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BRUCKN | Bruckner Soundview Greenway Connection - XG-31700-104M | 2 | DESIGN | 2007-09-29 | 2007-12-27 | 2007-09-29 | 2007-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BRUCKN | Bruckner Soundview Greenway Connection - XG-31700-104M | 3 | BID/ REGISTER CONTRACT | 2007-12-28 | 2008-03-26 | 2007-12-28 | 2008-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BRUCKN | Bruckner Soundview Greenway Connection - XG-31700-104M | 4 | CONSTRUCTION | 2008-03-27 | 2009-03-26 | 2008-03-27 | 2009-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BRUCKN | Bruckner Soundview Greenway Connection - XG-31700-104M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2009-03-27 | 2010-03-26 | 2009-03-27 | 2024-03-30
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BRXPK1 | Bronx Park, bet. Zones 3 & 5A, Priority 1 | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BRXPK1 | Bronx Park, bet. Zones 3 & 5A, Priority 1 | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BRXPK1 | Bronx Park, bet. Zones 3 & 5A, Priority 1 | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BRXPK1 | Bronx Park, bet. Zones 3 & 5A, Priority 1 | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BRXPK1 | Bronx Park, bet. Zones 3 & 5A, Priority 1 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BRXPK2 | Bronx Park, bet. Zones 3 & 5A, Priority 2 | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BRXPK2 | Bronx Park, bet. Zones 3 & 5A, Priority 2 | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BRXPK2 | Bronx Park, bet. Zones 3 & 5A, Priority 2 | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BRXPK2 | Bronx Park, bet. Zones 3 & 5A, Priority 2 | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BRXPK2 | Bronx Park, bet. Zones 3 & 5A, Priority 2 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BRXPK3 | Bronx Park, Zone 1 | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BRXPK3 | Bronx Park, Zone 1 | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BRXPK3 | Bronx Park, Zone 1 | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BRXPK3 | Bronx Park, Zone 1 | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BRXPK3 | Bronx Park, Zone 1 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BWBXP1 | Reconstruction of plgrs, Borough of Bronx (XG-508M) | 1 | DEVELOP SCOPE | 2011-07-01 | 2011-09-28 | 2011-07-01 | 2011-09-28
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BWBXP1 | Reconstruction of plgrs, Borough of Bronx (XG-508M) | 2 | DESIGN | 2011-09-29 | 2011-12-27 | 2011-09-29 | 2011-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BWBXP1 | Reconstruction of plgrs, Borough of Bronx (XG-508M) | 3 | BID/ REGISTER CONTRACT | 2011-12-28 | 2012-03-26 | 2011-12-28 | 2012-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BWBXP1 | Reconstruction of plgrs, Borough of Bronx (XG-508M) | 4 | CONSTRUCTION | 2012-03-27 | 2013-03-26 | 2012-03-27 | 2013-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BWBXP1 | Reconstruction of plgrs, Borough of Bronx (XG-508M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-03-27 | 2014-03-26 | 2013-03-27 | 2024-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BWRCTR | WEST BX RECR CTR HVAC RC- X261-116M | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BWRCTR | WEST BX RECR CTR HVAC RC- X261-116M | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2016-12-28 | 2017-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BWRCTR | WEST BX RECR CTR HVAC RC- X261-116M | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2017-12-28 | 2018-09-23
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BWRCTR | WEST BX RECR CTR HVAC RC- X261-116M | 4 | CONSTRUCTION | 2018-09-24 | 2019-09-23 | 2018-09-24 | 2019-09-23
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BWRCTR | WEST BX RECR CTR HVAC RC- X261-116M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BXPFIT | Bronx Park - Adult Fitness Equipment Construction- X002-117M | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2017-03-30 | 2017-11-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BXPFIT | Bronx Park - Adult Fitness Equipment Construction- X002-117M | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2018-04-03 | 2019-01-10
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BXPFIT | Bronx Park - Adult Fitness Equipment Construction- X002-117M | 4 | CONSTRUCTION | 2018-09-24 | 2019-09-23 | 2019-03-25 | 2020-03-23
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BXPFIT | Bronx Park - Adult Fitness Equipment Construction- X002-117M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-24 | 2020-09-22 | 2020-03-24 | 2021-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CASHIL | Castle Hill Park - reconstruction of pier X007-113M | 1 | DEVELOP SCOPE | 2006-07-01 | 2006-09-28 | 2006-07-01 | 2006-09-28
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CASHIL | Castle Hill Park - reconstruction of pier X007-113M | 2 | DESIGN | 2006-09-29 | 2006-12-27 | 2006-09-29 | 2006-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CASHIL | Castle Hill Park - reconstruction of pier X007-113M | 3 | BID/ REGISTER CONTRACT | 2006-12-28 | 2007-03-27 | 2006-12-28 | 2007-03-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CASHIL | Castle Hill Park - reconstruction of pier X007-113M | 4 | CONSTRUCTION | 2007-03-28 | 2008-03-26 | 2007-03-28 | 2008-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CASHIL | Castle Hill Park - reconstruction of pier X007-113M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-27 | 2009-03-26 | 2008-03-27 | 2021-12-30
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CHARLG | Charlton Garden - Phase II X086-108M | 1 | DEVELOP SCOPE | 2006-07-01 | 2006-09-28 | 2006-07-01 | 2006-09-28
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CHARLG | Charlton Garden - Phase II X086-108M | 2 | DESIGN | 2006-09-29 | 2006-12-27 | 2006-09-29 | 2006-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CHARLG | Charlton Garden - Phase II X086-108M | 3 | BID/ REGISTER CONTRACT | 2006-12-28 | 2007-03-27 | 2006-12-28 | 2007-03-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CHARLG | Charlton Garden - Phase II X086-108M | 4 | CONSTRUCTION | 2007-03-28 | 2008-03-26 | 2007-03-28 | 2008-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CHARLG | Charlton Garden - Phase II X086-108M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-27 | 2009-03-26 | 2008-03-27 | 2023-12-30
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CLEMAB | Roberto Clemente State Park - Activities Building | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CLEMAB | Roberto Clemente State Park - Activities Building | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CLEMAB | Roberto Clemente State Park - Activities Building | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CLEMAB | Roberto Clemente State Park - Activities Building | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CLEMAB | Roberto Clemente State Park - Activities Building | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPI134 | CPI PH2 - Playground 134 Reconstruction (X138-117M) | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPI134 | CPI PH2 - Playground 134 Reconstruction (X138-117M) | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2016-12-28 | 2017-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPI134 | CPI PH2 - Playground 134 Reconstruction (X138-117M) | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2017-12-28 | 2018-09-23
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPI134 | CPI PH2 - Playground 134 Reconstruction (X138-117M) | 4 | CONSTRUCTION | 2018-09-24 | 2019-09-23 | 2018-09-24 | 2019-09-23
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPI134 | CPI PH2 - Playground 134 Reconstruction (X138-117M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIBPG | CPI PH2 - Blackrock Plgd. Recon. (X205-116M) | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-12-27 | 2015-07-01 | 2016-03-29
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIBPG | CPI PH2 - Blackrock Plgd. Recon. (X205-116M) | 2 | DESIGN | 2015-12-28 | 2017-03-26 | 2016-03-30 | 2016-07-02
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIBPG | CPI PH2 - Blackrock Plgd. Recon. (X205-116M) | 3 | BID/ REGISTER CONTRACT | 2017-03-27 | 2017-12-21 | 2016-07-03 | 2017-05-16
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIBPG | CPI PH2 - Blackrock Plgd. Recon. (X205-116M) | 4 | CONSTRUCTION | 2017-12-22 | 2018-12-21 | 2018-03-30 | 2019-04-18
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIBPG | CPI PH2 - Blackrock Plgd. Recon. (X205-116M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-12-22 | 2019-12-21 | 2019-04-19 | 2022-04-17
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIBR2 | CPI PH2-174TH St.Plgd/BX River House-Plgd/Mini Pool X159-118 | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIBR2 | CPI PH2-174TH St.Plgd/BX River House-Plgd/Mini Pool X159-118 | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIBR2 | CPI PH2-174TH St.Plgd/BX River House-Plgd/Mini Pool X159-118 | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIBR2 | CPI PH2-174TH St.Plgd/BX River House-Plgd/Mini Pool X159-118 | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIBR2 | CPI PH2-174TH St.Plgd/BX River House-Plgd/Mini Pool X159-118 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIBR3 | CPI PH2-174TH St.Plgd/BX River House- Comfort Stat X159-218M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIBR3 | CPI PH2-174TH St.Plgd/BX River House- Comfort Stat X159-218M | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIBR3 | CPI PH2-174TH St.Plgd/BX River House- Comfort Stat X159-218M | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIBR3 | CPI PH2-174TH St.Plgd/BX River House- Comfort Stat X159-218M | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIBR3 | CPI PH2-174TH St.Plgd/BX River House- Comfort Stat X159-218M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIGAR | CPI PH2 - Garrison Playground (X106-117M) | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIGAR | CPI PH2 - Garrison Playground (X106-117M) | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2016-12-28 | 2017-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIGAR | CPI PH2 - Garrison Playground (X106-117M) | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2018-04-04 | 2018-07-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIGAR | CPI PH2 - Garrison Playground (X106-117M) | 4 | CONSTRUCTION | 2018-09-24 | 2019-09-23 | 2018-10-29 | 2019-10-29
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIGAR | CPI PH2 - Garrison Playground (X106-117M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-24 | 2020-09-22 | 2019-10-30 | 2022-12-05
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIHNT | CPI PH 1- Hunts Point Playground (X113-115M) | 1 | DEVELOP SCOPE | 2014-07-01 | 2014-09-28 | 2014-07-01 | 2014-12-12
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIHNT | CPI PH 1- Hunts Point Playground (X113-115M) | 2 | DESIGN | 2014-09-29 | 2014-12-27 | 2014-12-13 | 2015-03-12
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIHNT | CPI PH 1- Hunts Point Playground (X113-115M) | 3 | BID/ REGISTER CONTRACT | 2014-12-28 | 2015-03-27 | 2017-02-22 | 2017-08-17
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIHNT | CPI PH 1- Hunts Point Playground (X113-115M) | 4 | CONSTRUCTION | 2015-03-28 | 2016-03-26 | 2017-08-28 | 2019-03-29
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIHNT | CPI PH 1- Hunts Point Playground (X113-115M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-27 | 2017-03-26 | 2019-03-30 | 2020-03-30
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPILCM | CPI Phase 1- Little Claremont Pk X299-116M | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPILCM | CPI Phase 1- Little Claremont Pk X299-116M | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2016-12-28 | 2017-12-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPILCM | CPI Phase 1- Little Claremont Pk X299-116M | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2016-04-14 | 2017-04-14
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPILCM | CPI Phase 1- Little Claremont Pk X299-116M | 4 | CONSTRUCTION | 2018-09-24 | 2019-09-23 | 2018-04-28 | 2018-12-21
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPILCM | CPI Phase 1- Little Claremont Pk X299-116M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-24 | 2020-09-22 | 2018-12-22 | 2022-12-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIP52 | CPI - Plgd 52 (LII) Reconstruction-X179-115M | 1 | DEVELOP SCOPE | 2014-07-01 | 2014-09-28 | 2014-07-01 | 2014-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIP52 | CPI - Plgd 52 (LII) Reconstruction-X179-115M | 2 | DESIGN | 2014-09-29 | 2014-12-27 | 2014-12-28 | 2016-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIP52 | CPI - Plgd 52 (LII) Reconstruction-X179-115M | 3 | BID/ REGISTER CONTRACT | 2014-12-28 | 2015-03-27 | 2016-03-27 | 2016-12-21
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIP52 | CPI - Plgd 52 (LII) Reconstruction-X179-115M | 4 | CONSTRUCTION | 2015-03-28 | 2016-03-26 | 2016-12-22 | 2017-12-21
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIP52 | CPI - Plgd 52 (LII) Reconstruction-X179-115M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-27 | 2017-03-26 | 2017-12-22 | 2019-12-21
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIPMT | CPI PH 2 - Plimpton Playground (X148A2-117M) | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIPMT | CPI PH 2 - Plimpton Playground (X148A2-117M) | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2016-12-28 | 2017-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIPMT | CPI PH 2 - Plimpton Playground (X148A2-117M) | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2017-12-28 | 2018-09-23
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIPMT | CPI PH 2 - Plimpton Playground (X148A2-117M) | 4 | CONSTRUCTION | 2018-09-24 | 2019-09-23 | 2018-09-24 | 2019-09-23
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIPMT | CPI PH 2 - Plimpton Playground (X148A2-117M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2022-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIPRO | CPI Phase 2- Prospect Playground-X148H1-118M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIPRO | CPI Phase 2- Prospect Playground-X148H1-118M | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIPRO | CPI Phase 2- Prospect Playground-X148H1-118M | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIPRO | CPI Phase 2- Prospect Playground-X148H1-118M | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIPRO | CPI Phase 2- Prospect Playground-X148H1-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIWPK | CPI PH2 - Walton Park Rcons. (X291-116M) | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-12-27 | 2015-07-01 | 2015-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIWPK | CPI PH2 - Walton Park Rcons. (X291-116M) | 2 | DESIGN | 2015-12-28 | 2017-03-26 | 2015-12-28 | 2017-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIWPK | CPI PH2 - Walton Park Rcons. (X291-116M) | 3 | BID/ REGISTER CONTRACT | 2017-03-27 | 2017-12-21 | 2017-03-27 | 2017-12-21
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIWPK | CPI PH2 - Walton Park Rcons. (X291-116M) | 4 | CONSTRUCTION | 2017-12-22 | 2018-12-21 | 2017-12-22 | 2018-12-21
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIWPK | CPI PH2 - Walton Park Rcons. (X291-116M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-12-22 | 2019-12-21 | 2018-12-22 | 2021-12-21
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPMSGS | Con -Crotona Pkwy Malls Stormwater Greenstreet XG32350-114M | 2 | DESIGN | 2014-09-29 | 2014-12-27 | 2014-09-29 | 2014-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPMSGS | Con -Crotona Pkwy Malls Stormwater Greenstreet XG32350-114M | 3 | BID/ REGISTER CONTRACT | 2014-12-28 | 2015-03-27 | 2014-12-28 | 2015-03-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPMSGS | Con -Crotona Pkwy Malls Stormwater Greenstreet XG32350-114M | 4 | CONSTRUCTION | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2016-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPMSGS | Con -Crotona Pkwy Malls Stormwater Greenstreet XG32350-114M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CRNAPK | Crotona Park RC of the Nature Center X010-114M | 1 | DEVELOP SCOPE | 2009-07-01 | 2009-09-28 | 2009-07-01 | 2013-09-02
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CRNAPK | Crotona Park RC of the Nature Center X010-114M | 2 | DESIGN | 2009-09-29 | 2009-12-27 | 2013-09-03 | 2021-01-29
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CRNAPK | Crotona Park RC of the Nature Center X010-114M | 3 | BID/ REGISTER CONTRACT | 2009-12-28 | 2010-03-27 | 2017-08-15 | 2017-11-28
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CRNAPK | Crotona Park RC of the Nature Center X010-114M | 4 | CONSTRUCTION | 2010-03-28 | 2011-03-27 | 2018-03-18 | 2019-09-10
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CRNAPK | Crotona Park RC of the Nature Center X010-114M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2011-03-28 | 2012-03-26 | 2019-09-11 | 2022-09-11
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CRO17A | Williamsbridge Oval Park - Recr Bldg X104-207M/507M | 1 | DEVELOP SCOPE | 2006-07-01 | 2006-09-28 | 2006-07-01 | 2006-09-28
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CRO17A | Williamsbridge Oval Park - Recr Bldg X104-207M/507M | 2 | DESIGN | 2006-09-29 | 2006-12-27 | 2006-09-29 | 2006-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CRO17A | Williamsbridge Oval Park - Recr Bldg X104-207M/507M | 3 | BID/ REGISTER CONTRACT | 2006-12-28 | 2007-03-27 | 2006-12-28 | 2007-03-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CRO17A | Williamsbridge Oval Park - Recr Bldg X104-207M/507M | 4 | CONSTRUCTION | 2007-03-28 | 2008-03-26 | 2007-03-28 | 2008-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CRO17A | Williamsbridge Oval Park - Recr Bldg X104-207M/507M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-27 | 2009-03-26 | 2008-03-27 | 2024-12-30
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CRO17B | WILLIAMSBRIDGE OVAL PLGD 1 & 3 AND SPRAY PLAZA X104-107MA | 1 | DEVELOP SCOPE | 2008-07-01 | 2008-09-28 | 2008-07-01 | 2008-09-28
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CRO17B | WILLIAMSBRIDGE OVAL PLGD 1 & 3 AND SPRAY PLAZA X104-107MA | 2 | DESIGN | 2008-09-29 | 2008-12-27 | 2008-09-29 | 2008-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CRO17B | WILLIAMSBRIDGE OVAL PLGD 1 & 3 AND SPRAY PLAZA X104-107MA | 3 | BID/ REGISTER CONTRACT | 2008-12-28 | 2009-03-27 | 2008-12-28 | 2009-03-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CRO17B | WILLIAMSBRIDGE OVAL PLGD 1 & 3 AND SPRAY PLAZA X104-107MA | 4 | CONSTRUCTION | 2009-03-28 | 2010-03-27 | 2009-03-28 | 2010-03-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CRO17B | WILLIAMSBRIDGE OVAL PLGD 1 & 3 AND SPRAY PLAZA X104-107MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2010-03-28 | 2011-03-27 | 2010-03-28 | 2024-03-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CRO19 | Harris Park - Recon perimeter,construct new fence X136-115M | 1 | DEVELOP SCOPE | 2014-04-01 | 2014-06-29 | 2014-04-01 | 2014-06-29
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CRO19 | Harris Park - Recon perimeter,construct new fence X136-115M | 2 | DESIGN | 2014-06-30 | 2014-09-27 | 2014-06-30 | 2014-09-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CRO19 | Harris Park - Recon perimeter,construct new fence X136-115M | 3 | BID/ REGISTER CONTRACT | 2014-09-28 | 2014-12-26 | 2014-09-28 | 2014-12-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CRO19 | Harris Park - Recon perimeter,construct new fence X136-115M | 4 | CONSTRUCTION | 2014-12-27 | 2015-12-26 | 2014-12-27 | 2015-12-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CRO19 | Harris Park - Recon perimeter,construct new fence X136-115M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-12-27 | 2016-12-25 | 2015-12-27 | 2021-12-25
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CRO66C | Ferry Point Park Comfort Station - Plumbing X126-306MA | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2013-09-29 | 2013-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CRO66C | Ferry Point Park Comfort Station - Plumbing X126-306MA | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2013-12-28 | 2014-03-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CRO66C | Ferry Point Park Comfort Station - Plumbing X126-306MA | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2016-07-04 | 2017-12-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CRO66C | Ferry Point Park Comfort Station - Plumbing X126-306MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2017-12-27 | 2018-12-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROALG | CROTONA PARK INDIAN LAKE ALGAE REDUCTION | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROALG | CROTONA PARK INDIAN LAKE ALGAE REDUCTION | 2 | DESIGN | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROALG | CROTONA PARK INDIAN LAKE ALGAE REDUCTION | 3 | BID/ REGISTER CONTRACT | 2020-09-23 | 2021-06-19 | 2020-09-23 | 2021-06-19
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROALG | CROTONA PARK INDIAN LAKE ALGAE REDUCTION | 4 | CONSTRUCTION | 2021-06-20 | 2023-12-16 | 2021-06-20 | 2023-12-16
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROALG | CROTONA PARK INDIAN LAKE ALGAE REDUCTION | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-12-17 | 2025-12-15 | 2023-12-17 | 2025-12-15
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT02 | BRONX RIVER GNWAY: BIRCHALL/180TH ST CONNECTION X002-107M | 1 | DEVELOP SCOPE | 2006-07-01 | 2006-09-28 | 2006-07-01 | 2006-09-28
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT02 | BRONX RIVER GNWAY: BIRCHALL/180TH ST CONNECTION X002-107M | 2 | DESIGN | 2006-09-29 | 2006-12-27 | 2006-09-29 | 2006-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT02 | BRONX RIVER GNWAY: BIRCHALL/180TH ST CONNECTION X002-107M | 3 | BID/ REGISTER CONTRACT | 2006-12-28 | 2007-03-27 | 2006-12-28 | 2007-03-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT02 | BRONX RIVER GNWAY: BIRCHALL/180TH ST CONNECTION X002-107M | 4 | CONSTRUCTION | 2007-03-28 | 2008-03-26 | 2007-03-28 | 2008-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT02 | BRONX RIVER GNWAY: BIRCHALL/180TH ST CONNECTION X002-107M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-27 | 2009-03-26 | 2008-03-27 | 2019-12-30
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT05 | Putnam Trail - Acquisition of Right-of-Way- XPUTNAM | 1 | DEVELOP SCOPE | 2007-07-01 | 2007-09-28 | 2007-07-01 | 2007-09-28
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT05 | Putnam Trail - Acquisition of Right-of-Way- XPUTNAM | 2 | DESIGN | 2007-09-29 | 2007-12-27 | 2007-09-29 | 2007-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT05 | Putnam Trail - Acquisition of Right-of-Way- XPUTNAM | 3 | BID/ REGISTER CONTRACT | 2007-12-28 | 2008-03-26 | 2007-12-28 | 2008-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT05 | Putnam Trail - Acquisition of Right-of-Way- XPUTNAM | 4 | CONSTRUCTION | 2008-03-27 | 2009-03-26 | 2008-03-27 | 2009-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT05 | Putnam Trail - Acquisition of Right-of-Way- XPUTNAM | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2009-03-27 | 2010-03-26 | 2009-03-27 | 2021-12-30
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT06 | BRONX RIVER GREENWAY: MULTI USE PATH 233 ST X004-213M | 1 | DEVELOP SCOPE | 2006-07-01 | 2006-09-28 | 2006-07-01 | 2006-09-28
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT06 | BRONX RIVER GREENWAY: MULTI USE PATH 233 ST X004-213M | 2 | DESIGN | 2006-09-29 | 2006-12-27 | 2006-09-29 | 2006-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT06 | BRONX RIVER GREENWAY: MULTI USE PATH 233 ST X004-213M | 3 | BID/ REGISTER CONTRACT | 2006-12-28 | 2007-03-27 | 2006-12-28 | 2007-03-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT06 | BRONX RIVER GREENWAY: MULTI USE PATH 233 ST X004-213M | 4 | CONSTRUCTION | 2007-03-28 | 2008-03-26 | 2007-03-28 | 2008-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT06 | BRONX RIVER GREENWAY: MULTI USE PATH 233 ST X004-213M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-27 | 2009-03-26 | 2008-03-27 | 2019-12-30
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT09 | Pelham Bay Park: Waterfront Development X039-507MA | 1 | DEVELOP SCOPE | 2006-07-01 | 2006-09-28 | 2006-07-01 | 2006-09-28
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT09 | Pelham Bay Park: Waterfront Development X039-507MA | 2 | DESIGN | 2006-09-29 | 2006-12-27 | 2006-09-29 | 2006-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT09 | Pelham Bay Park: Waterfront Development X039-507MA | 3 | BID/ REGISTER CONTRACT | 2006-12-28 | 2007-03-27 | 2006-12-28 | 2007-03-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT09 | Pelham Bay Park: Waterfront Development X039-507MA | 4 | CONSTRUCTION | 2007-03-28 | 2008-03-26 | 2007-03-28 | 2008-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT09 | Pelham Bay Park: Waterfront Development X039-507MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-27 | 2009-03-26 | 2008-03-27 | 2021-12-30
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT12 | PUGSLEY CREEK SALT MARSH & BUFFER RESTOR X088-506M&106M OMBP | 1 | DEVELOP SCOPE | 2006-07-01 | 2006-09-28 | 2006-07-01 | 2006-09-28
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT12 | PUGSLEY CREEK SALT MARSH & BUFFER RESTOR X088-506M&106M OMBP | 2 | DESIGN | 2006-09-29 | 2006-12-27 | 2006-09-29 | 2006-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT12 | PUGSLEY CREEK SALT MARSH & BUFFER RESTOR X088-506M&106M OMBP | 3 | BID/ REGISTER CONTRACT | 2006-12-28 | 2007-03-27 | 2006-12-28 | 2007-03-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT12 | PUGSLEY CREEK SALT MARSH & BUFFER RESTOR X088-506M&106M OMBP | 4 | CONSTRUCTION | 2007-03-28 | 2008-03-26 | 2007-03-28 | 2008-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT12 | PUGSLEY CREEK SALT MARSH & BUFFER RESTOR X088-506M&106M OMBP | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-27 | 2009-03-26 | 2008-03-27 | 2021-03-30
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT13 | VC PK- Recon Headhouse & Demolish Greenhouse X092-207M | 1 | DEVELOP SCOPE | 2006-07-01 | 2006-09-28 | 2006-07-01 | 2006-09-28
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT13 | VC PK- Recon Headhouse & Demolish Greenhouse X092-207M | 2 | DESIGN | 2006-09-29 | 2006-12-27 | 2012-03-01 | 2012-05-31
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT13 | VC PK- Recon Headhouse & Demolish Greenhouse X092-207M | 3 | BID/ REGISTER CONTRACT | 2006-12-28 | 2007-03-27 | 2012-08-30 | 2012-10-31
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT13 | VC PK- Recon Headhouse & Demolish Greenhouse X092-207M | 4 | CONSTRUCTION | 2007-03-28 | 2008-03-26 | 2012-11-01 | 2014-02-28
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT13 | VC PK- Recon Headhouse & Demolish Greenhouse X092-207M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-27 | 2009-03-26 | 2014-03-01 | 2023-05-31
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT14 | AQUEDUCT WALK - COMF. STATION X001-207M/507M | 1 | DEVELOP SCOPE | 2006-07-01 | 2006-09-28 | 2006-07-01 | 2010-08-17
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT14 | AQUEDUCT WALK - COMF. STATION X001-207M/507M | 2 | DESIGN | 2006-09-29 | 2006-12-27 | 2010-11-17 | 2011-02-17
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT14 | AQUEDUCT WALK - COMF. STATION X001-207M/507M | 3 | BID/ REGISTER CONTRACT | 2006-12-28 | 2007-03-27 | 2011-02-18 | 2012-05-31
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT14 | AQUEDUCT WALK - COMF. STATION X001-207M/507M | 4 | CONSTRUCTION | 2007-03-28 | 2008-03-26 | 2016-09-19 | 2018-03-12
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT14 | AQUEDUCT WALK - COMF. STATION X001-207M/507M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-27 | 2009-03-26 | 2018-03-13 | 2021-12-15
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT19 | HARRIS PARK ATHLETIC FIELDS X136-106M | 1 | DEVELOP SCOPE | 2006-07-01 | 2006-09-28 | 2006-07-01 | 2006-09-28
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT19 | HARRIS PARK ATHLETIC FIELDS X136-106M | 2 | DESIGN | 2006-09-29 | 2006-12-27 | 2006-09-29 | 2006-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT19 | HARRIS PARK ATHLETIC FIELDS X136-106M | 3 | BID/ REGISTER CONTRACT | 2006-12-28 | 2007-03-27 | 2006-12-28 | 2007-03-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT19 | HARRIS PARK ATHLETIC FIELDS X136-106M | 4 | CONSTRUCTION | 2007-03-28 | 2008-03-26 | 2007-03-28 | 2008-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT19 | HARRIS PARK ATHLETIC FIELDS X136-106M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-27 | 2009-03-26 | 2008-03-27 | 2021-12-30
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT23 | VAN CORTLANDT PK: DISTRICT HQS & COMF STAT X092-106M | 2 | DESIGN | 2006-09-29 | 2006-12-27 | 2007-01-05 | 2008-01-30
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT23 | VAN CORTLANDT PK: DISTRICT HQS & COMF STAT X092-106M | 3 | BID/ REGISTER CONTRACT | 2006-12-28 | 2007-03-27 | 2008-02-01 | 2009-05-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT23 | VAN CORTLANDT PK: DISTRICT HQS & COMF STAT X092-106M | 4 | CONSTRUCTION | 2007-03-28 | 2008-03-26 | 2009-12-28 | 2010-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT23 | VAN CORTLANDT PK: DISTRICT HQS & COMF STAT X092-106M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-27 | 2009-03-26 | 2010-12-28 | 2019-12-28
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT28 | JEROME PARK RESERVOIR-RECREATIONAL PATHWAY XG-20000-107M | 1 | DEVELOP SCOPE | 2006-07-01 | 2006-09-28 | 2006-07-01 | 2006-09-28
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT28 | JEROME PARK RESERVOIR-RECREATIONAL PATHWAY XG-20000-107M | 2 | DESIGN | 2006-09-29 | 2006-12-27 | 2006-09-29 | 2006-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT28 | JEROME PARK RESERVOIR-RECREATIONAL PATHWAY XG-20000-107M | 3 | BID/ REGISTER CONTRACT | 2006-12-28 | 2007-03-27 | 2006-12-28 | 2007-03-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT28 | JEROME PARK RESERVOIR-RECREATIONAL PATHWAY XG-20000-107M | 4 | CONSTRUCTION | 2007-03-28 | 2008-03-26 | 2007-03-28 | 2008-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT28 | JEROME PARK RESERVOIR-RECREATIONAL PATHWAY XG-20000-107M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-27 | 2009-03-26 | 2008-03-27 | 2021-12-30
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT31 | AQUEDUCT LANDS: BASKETBALL CTS & PLGD X001-105M | 1 | DEVELOP SCOPE | 2006-07-01 | 2006-09-28 | 2006-07-01 | 2006-09-28
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT31 | AQUEDUCT LANDS: BASKETBALL CTS & PLGD X001-105M | 2 | DESIGN | 2006-09-29 | 2006-12-27 | 2006-09-29 | 2006-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT31 | AQUEDUCT LANDS: BASKETBALL CTS & PLGD X001-105M | 3 | BID/ REGISTER CONTRACT | 2006-12-28 | 2007-03-27 | 2006-12-28 | 2007-03-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT31 | AQUEDUCT LANDS: BASKETBALL CTS & PLGD X001-105M | 4 | CONSTRUCTION | 2007-03-28 | 2008-03-26 | 2007-03-28 | 2008-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT31 | AQUEDUCT LANDS: BASKETBALL CTS & PLGD X001-105M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-27 | 2009-03-26 | 2008-03-27 | 2011-12-30
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT32 | RECON PATH & MISC WORK @ AQUEDUCT WALK X001-107M | 1 | DEVELOP SCOPE | 2006-07-01 | 2006-09-28 | 2006-07-01 | 2006-09-28
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT32 | RECON PATH & MISC WORK @ AQUEDUCT WALK X001-107M | 2 | DESIGN | 2006-09-29 | 2006-12-27 | 2006-09-29 | 2006-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT32 | RECON PATH & MISC WORK @ AQUEDUCT WALK X001-107M | 3 | BID/ REGISTER CONTRACT | 2006-12-28 | 2007-03-27 | 2006-12-28 | 2007-03-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT32 | RECON PATH & MISC WORK @ AQUEDUCT WALK X001-107M | 4 | CONSTRUCTION | 2007-03-28 | 2008-03-26 | 2007-03-28 | 2008-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT32 | RECON PATH & MISC WORK @ AQUEDUCT WALK X001-107M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-27 | 2009-03-26 | 2008-03-27 | 2021-12-30
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT36 | PELHAM PARKWAY MALLS X003-107M | 1 | DEVELOP SCOPE | 2006-07-01 | 2006-09-28 | 2006-07-01 | 2006-09-28
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT36 | PELHAM PARKWAY MALLS X003-107M | 2 | DESIGN | 2006-09-29 | 2006-12-27 | 2006-09-29 | 2006-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT36 | PELHAM PARKWAY MALLS X003-107M | 3 | BID/ REGISTER CONTRACT | 2006-12-28 | 2007-03-27 | 2006-12-28 | 2007-03-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT36 | PELHAM PARKWAY MALLS X003-107M | 4 | CONSTRUCTION | 2007-03-28 | 2008-03-26 | 2007-03-28 | 2008-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT36 | PELHAM PARKWAY MALLS X003-107M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-27 | 2009-03-26 | 2008-03-27 | 2021-12-30
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT42 | STORY PLAYGROUND RC OF P. S. 100 X204-106M | 1 | DEVELOP SCOPE | 2006-07-01 | 2006-09-28 | 2006-07-01 | 2006-09-28
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT42 | STORY PLAYGROUND RC OF P. S. 100 X204-106M | 2 | DESIGN | 2006-09-29 | 2006-12-27 | 2006-09-29 | 2006-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT42 | STORY PLAYGROUND RC OF P. S. 100 X204-106M | 3 | BID/ REGISTER CONTRACT | 2006-12-28 | 2007-03-27 | 2006-12-28 | 2007-03-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT42 | STORY PLAYGROUND RC OF P. S. 100 X204-106M | 4 | CONSTRUCTION | 2007-03-28 | 2008-03-26 | 2007-03-28 | 2015-04-05
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT42 | STORY PLAYGROUND RC OF P. S. 100 X204-106M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-27 | 2009-03-26 | 2011-10-01 | 2021-04-05
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT44 | PUGSLEY CREEK - FIELD OF DREAMS BFLDS & SITEWORK X088-207M | 1 | DEVELOP SCOPE | 2006-07-01 | 2006-09-28 | 2006-07-01 | 2006-09-28
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT44 | PUGSLEY CREEK - FIELD OF DREAMS BFLDS & SITEWORK X088-207M | 2 | DESIGN | 2006-09-29 | 2006-12-27 | 2006-09-29 | 2006-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT44 | PUGSLEY CREEK - FIELD OF DREAMS BFLDS & SITEWORK X088-207M | 3 | BID/ REGISTER CONTRACT | 2006-12-28 | 2007-03-27 | 2006-12-28 | 2007-03-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT44 | PUGSLEY CREEK - FIELD OF DREAMS BFLDS & SITEWORK X088-207M | 4 | CONSTRUCTION | 2007-03-28 | 2008-03-26 | 2007-03-28 | 2008-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT44 | PUGSLEY CREEK - FIELD OF DREAMS BFLDS & SITEWORK X088-207M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-27 | 2009-03-26 | 2008-03-27 | 2019-11-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT45 | PUGSLEY CREEK PK - Construct basketball court X088-111M | 1 | DEVELOP SCOPE | 2006-07-01 | 2006-09-28 | 2006-07-01 | 2006-09-28
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT45 | PUGSLEY CREEK PK - Construct basketball court X088-111M | 2 | DESIGN | 2006-09-29 | 2006-12-27 | 2006-09-29 | 2006-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT45 | PUGSLEY CREEK PK - Construct basketball court X088-111M | 3 | BID/ REGISTER CONTRACT | 2006-12-28 | 2007-03-27 | 2006-12-28 | 2007-03-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT45 | PUGSLEY CREEK PK - Construct basketball court X088-111M | 4 | CONSTRUCTION | 2007-03-28 | 2008-03-26 | 2007-03-28 | 2008-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT45 | PUGSLEY CREEK PK - Construct basketball court X088-111M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-27 | 2009-03-26 | 2008-03-27 | 2021-12-30
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT46 | HINES PARK - RECONST OF RETAINING WALL X026-107M | 1 | DEVELOP SCOPE | 2006-07-01 | 2006-09-28 | 2006-07-01 | 2006-09-28
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT46 | HINES PARK - RECONST OF RETAINING WALL X026-107M | 2 | DESIGN | 2006-09-29 | 2006-12-27 | 2006-09-29 | 2006-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT46 | HINES PARK - RECONST OF RETAINING WALL X026-107M | 3 | BID/ REGISTER CONTRACT | 2006-12-28 | 2007-03-27 | 2006-12-28 | 2007-03-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT46 | HINES PARK - RECONST OF RETAINING WALL X026-107M | 4 | CONSTRUCTION | 2007-03-28 | 2008-03-26 | 2007-03-28 | 2008-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT46 | HINES PARK - RECONST OF RETAINING WALL X026-107M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-27 | 2009-03-26 | 2008-03-27 | 2021-12-30
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT48 | CLARK PLAYGROUND RC X200-105M | 1 | DEVELOP SCOPE | 2006-07-01 | 2006-09-28 | 2006-07-01 | 2006-09-28
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT48 | CLARK PLAYGROUND RC X200-105M | 2 | DESIGN | 2006-09-29 | 2006-12-27 | 2006-09-29 | 2006-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT48 | CLARK PLAYGROUND RC X200-105M | 3 | BID/ REGISTER CONTRACT | 2006-12-28 | 2007-03-27 | 2006-12-28 | 2007-03-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT48 | CLARK PLAYGROUND RC X200-105M | 4 | CONSTRUCTION | 2007-03-28 | 2008-03-26 | 2007-03-28 | 2008-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT48 | CLARK PLAYGROUND RC X200-105M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-27 | 2009-03-26 | 2008-03-27 | 2021-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT51 | SEDGWICK PLAYGROUND X158-106M | 1 | DEVELOP SCOPE | 2006-07-01 | 2006-09-28 | 2006-07-01 | 2006-09-28
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT51 | SEDGWICK PLAYGROUND X158-106M | 2 | DESIGN | 2006-09-29 | 2006-12-27 | 2006-09-29 | 2006-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT51 | SEDGWICK PLAYGROUND X158-106M | 3 | BID/ REGISTER CONTRACT | 2006-12-28 | 2007-03-27 | 2006-12-28 | 2007-03-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT51 | SEDGWICK PLAYGROUND X158-106M | 4 | CONSTRUCTION | 2007-03-28 | 2008-03-26 | 2007-03-28 | 2008-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT51 | SEDGWICK PLAYGROUND X158-106M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-27 | 2009-03-26 | 2008-03-27 | 2019-12-30
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT68 | MULLALY PARK - SKATE BUILDING X034-207M | 1 | DEVELOP SCOPE | 2007-07-01 | 2007-09-28 | 2007-07-01 | 2008-05-01
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT68 | MULLALY PARK - SKATE BUILDING X034-207M | 2 | DESIGN | 2007-09-29 | 2007-12-27 | 2008-05-01 | 2008-08-01
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT68 | MULLALY PARK - SKATE BUILDING X034-207M | 3 | BID/ REGISTER CONTRACT | 2007-12-28 | 2008-03-26 | 2008-10-10 | 2009-05-18
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT68 | MULLALY PARK - SKATE BUILDING X034-207M | 4 | CONSTRUCTION | 2008-03-27 | 2009-03-26 | 2009-08-17 | 2010-08-17
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT68 | MULLALY PARK - SKATE BUILDING X034-207M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2009-03-27 | 2010-03-26 | 2012-06-22 | 2021-06-21
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT72 | Synthetic Turf Field at Crotona Park X010-109M | 1 | DEVELOP SCOPE | 2009-07-01 | 2009-09-28 | 2009-07-01 | 2009-09-28
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT72 | Synthetic Turf Field at Crotona Park X010-109M | 2 | DESIGN | 2009-09-29 | 2009-12-27 | 2009-09-29 | 2009-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT72 | Synthetic Turf Field at Crotona Park X010-109M | 3 | BID/ REGISTER CONTRACT | 2009-12-28 | 2010-03-27 | 2009-12-28 | 2010-03-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT72 | Synthetic Turf Field at Crotona Park X010-109M | 4 | CONSTRUCTION | 2010-03-28 | 2011-03-27 | 2010-03-28 | 2011-03-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT72 | Synthetic Turf Field at Crotona Park X010-109M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2011-03-28 | 2012-03-26 | 2011-03-28 | 2012-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROUL1 | VAN CORT PLGD & COMF. STAT(SACHKERAH WOODS) X092-400MA/700MA | 1 | DEVELOP SCOPE | 2006-07-01 | 2006-09-28 | 2006-07-01 | 2006-09-28
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROUL1 | VAN CORT PLGD & COMF. STAT(SACHKERAH WOODS) X092-400MA/700MA | 2 | DESIGN | 2006-09-29 | 2006-12-27 | 2006-09-29 | 2006-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROUL1 | VAN CORT PLGD & COMF. STAT(SACHKERAH WOODS) X092-400MA/700MA | 3 | BID/ REGISTER CONTRACT | 2006-12-28 | 2007-03-27 | 2006-12-28 | 2007-03-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROUL1 | VAN CORT PLGD & COMF. STAT(SACHKERAH WOODS) X092-400MA/700MA | 4 | CONSTRUCTION | 2007-03-28 | 2008-03-26 | 2007-03-28 | 2008-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROUL1 | VAN CORT PLGD & COMF. STAT(SACHKERAH WOODS) X092-400MA/700MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-27 | 2009-03-26 | 2008-03-27 | 2019-12-30
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROUL6 | Van Cortl. Park-Old Croton Aqueduct Trail Phase 2 X092-1107M | 1 | DEVELOP SCOPE | 2008-07-01 | 2008-09-28 | 2011-04-27 | 2011-07-25
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROUL6 | Van Cortl. Park-Old Croton Aqueduct Trail Phase 2 X092-1107M | 2 | DESIGN | 2008-09-29 | 2008-12-27 | 2011-07-26 | 2011-10-23
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROUL6 | Van Cortl. Park-Old Croton Aqueduct Trail Phase 2 X092-1107M | 3 | BID/ REGISTER CONTRACT | 2008-12-28 | 2009-03-27 | 2011-10-24 | 2011-10-23
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROUL6 | Van Cortl. Park-Old Croton Aqueduct Trail Phase 2 X092-1107M | 4 | CONSTRUCTION | 2009-03-28 | 2010-03-27 | 2011-10-24 | 2011-10-23
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROUL6 | Van Cortl. Park-Old Croton Aqueduct Trail Phase 2 X092-1107M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2010-03-28 | 2011-03-27 | 2013-01-21 | 2014-11-21
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CRPOFW | Crotona Park -Recon pool perimeter fence & wall X010-314M | 1 | DEVELOP SCOPE | 2014-07-01 | 2014-09-28 | 2014-07-01 | 2014-09-28
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CRPOFW | Crotona Park -Recon pool perimeter fence & wall X010-314M | 2 | DESIGN | 2014-09-29 | 2014-12-27 | 2014-09-29 | 2014-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CRPOFW | Crotona Park -Recon pool perimeter fence & wall X010-314M | 3 | BID/ REGISTER CONTRACT | 2014-12-28 | 2015-03-27 | 2014-12-28 | 2015-03-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CRPOFW | Crotona Park -Recon pool perimeter fence & wall X010-314M | 4 | CONSTRUCTION | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2016-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CRPOFW | Crotona Park -Recon pool perimeter fence & wall X010-314M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2024-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CRPOHS | Crotona Park - pool towers X010-210MA3 | 1 | DEVELOP SCOPE | 2009-07-01 | 2009-09-28 | 2009-07-01 | 2010-11-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CRPOHS | Crotona Park - pool towers X010-210MA3 | 2 | DESIGN | 2009-09-29 | 2009-12-27 | 2010-11-23 | 2012-11-30
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CRPOHS | Crotona Park - pool towers X010-210MA3 | 3 | BID/ REGISTER CONTRACT | 2009-12-28 | 2010-03-27 | 2012-12-01 | 2013-06-01
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CRPOHS | Crotona Park - pool towers X010-210MA3 | 4 | CONSTRUCTION | 2010-03-28 | 2011-03-27 | 2013-06-02 | 2014-06-02
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CRPOHS | Crotona Park - pool towers X010-210MA3 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2011-03-28 | 2012-03-26 | 2014-06-03 | 2021-06-02
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1DEPOT | Depot Place - portion of Harlem River greenway XG-31800-106M | 1 | DEVELOP SCOPE | 2006-07-01 | 2006-09-28 | 2006-07-01 | 2006-09-28
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1DEPOT | Depot Place - portion of Harlem River greenway XG-31800-106M | 2 | DESIGN | 2006-09-29 | 2006-12-27 | 2006-09-29 | 2006-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1DEPOT | Depot Place - portion of Harlem River greenway XG-31800-106M | 3 | BID/ REGISTER CONTRACT | 2006-12-28 | 2007-03-27 | 2006-12-28 | 2007-03-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1DEPOT | Depot Place - portion of Harlem River greenway XG-31800-106M | 4 | CONSTRUCTION | 2007-03-28 | 2008-03-26 | 2007-03-28 | 2008-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1DEPOT | Depot Place - portion of Harlem River greenway XG-31800-106M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-27 | 2009-03-26 | 2008-03-27 | 2024-03-30
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1DEVORF | Recon of Roofing systems at Devoe Park | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1DEVORF | Recon of Roofing systems at Devoe Park | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1DEVORF | Recon of Roofing systems at Devoe Park | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1DEVORF | Recon of Roofing systems at Devoe Park | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1DEVORF | Recon of Roofing systems at Devoe Park | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1ECHOPK | Echo Park Playground and Sports Fields- X017-117M | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1ECHOPK | Echo Park Playground and Sports Fields- X017-117M | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2016-12-28 | 2017-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1ECHOPK | Echo Park Playground and Sports Fields- X017-117M | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2017-12-28 | 2018-09-23
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1ECHOPK | Echo Park Playground and Sports Fields- X017-117M | 4 | CONSTRUCTION | 2018-09-24 | 2019-09-23 | 2018-09-24 | 2019-09-23
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1ECHOPK | Echo Park Playground and Sports Fields- X017-117M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1ECHORF | Recon of Roofing systems at Echo | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1ECHORF | Recon of Roofing systems at Echo | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1ECHORF | Recon of Roofing systems at Echo | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1ECHORF | Recon of Roofing systems at Echo | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1ECHORF | Recon of Roofing systems at Echo | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1EDENPG | Edenwald PLGD - basketball & handball crts (X165-116MA) | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2015-10-07
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1EDENPG | Edenwald PLGD - basketball & handball crts (X165-116MA) | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2015-10-08 | 2020-06-28
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1EDENPG | Edenwald PLGD - basketball & handball crts (X165-116MA) | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2018-05-10 | 2022-06-21
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1EDENPG | Edenwald PLGD - basketball & handball crts (X165-116MA) | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2022-06-22 | 2023-06-21
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1EDENPG | Edenwald PLGD - basketball & handball crts (X165-116MA) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2023-06-22 | 2027-06-20
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1EWENPK | Ewen Park - construct playground X019-112M | 1 | DEVELOP SCOPE | 2009-07-01 | 2009-09-28 | 2009-07-01 | 2009-09-28
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1EWENPK | Ewen Park - construct playground X019-112M | 2 | DESIGN | 2009-09-29 | 2009-12-27 | 2009-09-29 | 2009-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1EWENPK | Ewen Park - construct playground X019-112M | 3 | BID/ REGISTER CONTRACT | 2009-12-28 | 2010-03-27 | 2009-12-28 | 2010-03-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1EWENPK | Ewen Park - construct playground X019-112M | 4 | CONSTRUCTION | 2010-03-28 | 2011-03-27 | 2010-03-28 | 2011-03-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1EWENPK | Ewen Park - construct playground X019-112M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2011-03-28 | 2012-03-26 | 2011-03-28 | 2024-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1FERPNT | Ferry Point Community Park - Adult Fitness Area | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1FERPNT | Ferry Point Community Park - Adult Fitness Area | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1FERPNT | Ferry Point Community Park - Adult Fitness Area | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1FERPNT | Ferry Point Community Park - Adult Fitness Area | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1FERPNT | Ferry Point Community Park - Adult Fitness Area | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1FERRY8 | Ferry Point Park - Waterfront Park X126-116M | 1 | DEVELOP SCOPE | 2009-07-01 | 2009-09-28 | 2009-07-01 | 2015-11-02
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1FERRY8 | Ferry Point Park - Waterfront Park X126-116M | 2 | DESIGN | 2009-09-29 | 2009-12-27 | 2015-11-03 | 2018-07-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1FERRY8 | Ferry Point Park - Waterfront Park X126-116M | 3 | BID/ REGISTER CONTRACT | 2009-12-28 | 2010-03-27 | 2018-11-13 | 2025-04-04
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1FERRY8 | Ferry Point Park - Waterfront Park X126-116M | 4 | CONSTRUCTION | 2010-03-28 | 2011-03-27 | 2025-04-05 | 2025-04-04
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1FERRY8 | Ferry Point Park - Waterfront Park X126-116M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2011-03-28 | 2012-03-26 | 2025-04-05 | 2032-04-03
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1GHPCSR | Grove Hill Playground-Comfort Station Reconstruction | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1GHPCSR | Grove Hill Playground-Comfort Station Reconstruction | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1GHPCSR | Grove Hill Playground-Comfort Station Reconstruction | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1GHPCSR | Grove Hill Playground-Comfort Station Reconstruction | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1GHPCSR | Grove Hill Playground-Comfort Station Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1GIGP01 | St. Mary's Park & Rec Ctr Green Infrastructure XG-413M | 1 | DEVELOP SCOPE | 2012-07-01 | 2012-09-28 | 2012-07-01 | 2012-09-28
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1GIGP01 | St. Mary's Park & Rec Ctr Green Infrastructure XG-413M | 2 | DESIGN | 2012-09-29 | 2012-12-27 | 2012-09-29 | 2017-09-25
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1GIGP01 | St. Mary's Park & Rec Ctr Green Infrastructure XG-413M | 3 | BID/ REGISTER CONTRACT | 2012-12-28 | 2013-03-27 | 2017-09-26 | 2017-12-24
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1GIGP01 | St. Mary's Park & Rec Ctr Green Infrastructure XG-413M | 4 | CONSTRUCTION | 2013-03-28 | 2014-03-27 | 2017-12-25 | 2018-12-24
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1GIGP01 | St. Mary's Park & Rec Ctr Green Infrastructure XG-413M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-03-28 | 2015-03-27 | 2018-12-25 | 2023-12-24
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1GRAUER | Conrad Grauer field - demo & const of 20 ft fence X150-113M | 1 | DEVELOP SCOPE | 2009-07-01 | 2009-09-28 | 2009-07-01 | 2009-09-28
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1GRAUER | Conrad Grauer field - demo & const of 20 ft fence X150-113M | 2 | DESIGN | 2009-09-29 | 2009-12-27 | 2009-09-29 | 2009-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1GRAUER | Conrad Grauer field - demo & const of 20 ft fence X150-113M | 3 | BID/ REGISTER CONTRACT | 2009-12-28 | 2010-03-27 | 2009-12-28 | 2010-03-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1GRAUER | Conrad Grauer field - demo & const of 20 ft fence X150-113M | 4 | CONSTRUCTION | 2010-03-28 | 2011-03-27 | 2010-03-28 | 2011-03-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1GRAUER | Conrad Grauer field - demo & const of 20 ft fence X150-113M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2011-03-28 | 2012-03-26 | 2011-03-28 | 2024-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1HAFFPT | HAFFEN PARK - CONSTRUCT ADULT FITNESS AREA | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1HAFFPT | HAFFEN PARK - CONSTRUCT ADULT FITNESS AREA | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1HAFFPT | HAFFEN PARK - CONSTRUCT ADULT FITNESS AREA | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1HAFFPT | HAFFEN PARK - CONSTRUCT ADULT FITNESS AREA | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1HAFFPT | HAFFEN PARK - CONSTRUCT ADULT FITNESS AREA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1HCMARI | Hammond Cove Marina | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1HCMARI | Hammond Cove Marina | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1HCMARI | Hammond Cove Marina | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1HCMARI | Hammond Cove Marina | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1HCMARI | Hammond Cove Marina | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1HGCVPR | PWOB-Hugh Grant Circle & Virginia Pk. Recon. XG-117MA | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1HGCVPR | PWOB-Hugh Grant Circle & Virginia Pk. Recon. XG-117MA | 2 | DESIGN | 2016-12-28 | 2018-03-22 | 2016-12-28 | 2017-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1HGCVPR | PWOB-Hugh Grant Circle & Virginia Pk. Recon. XG-117MA | 3 | BID/ REGISTER CONTRACT | 2018-03-23 | 2018-12-17 | 2017-12-28 | 2018-09-23
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1HGCVPR | PWOB-Hugh Grant Circle & Virginia Pk. Recon. XG-117MA | 4 | CONSTRUCTION | 2018-12-18 | 2020-12-16 | 2018-09-24 | 2019-09-23
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1HGCVPR | PWOB-Hugh Grant Circle & Virginia Pk. Recon. XG-117MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-12-17 | 2021-12-16 | 2019-09-24 | 2023-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1HUNTPT | HUNTS POINT RECREATION CENTER - REPLACE GYMNASIUM FLOOR | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1HUNTPT | HUNTS POINT RECREATION CENTER - REPLACE GYMNASIUM FLOOR | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1HUNTPT | HUNTS POINT RECREATION CENTER - REPLACE GYMNASIUM FLOOR | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1HUNTPT | HUNTS POINT RECREATION CENTER - REPLACE GYMNASIUM FLOOR | 4 | CONSTRUCTION | 2021-09-23 | 2023-03-21 | 2021-09-23 | 2023-03-21
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1HUNTPT | HUNTS POINT RECREATION CENTER - REPLACE GYMNASIUM FLOOR | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-03-22 | 2024-03-20 | 2023-03-22 | 2024-03-20
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1HVMRCS | Havemeyer Playground C.S. | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1HVMRCS | Havemeyer Playground C.S. | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1HVMRCS | Havemeyer Playground C.S. | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1HVMRCS | Havemeyer Playground C.S. | 4 | CONSTRUCTION | 2020-09-23 | 2022-03-21 | 2020-09-23 | 2022-03-21
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1HVMRCS | Havemeyer Playground C.S. | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-22 | 2023-03-21 | 2022-03-22 | 2023-03-21
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1IRRIG | Golf Course Irrigation - XG-200M | 1 | DEVELOP SCOPE | 1999-11-01 | 1999-11-29 | 1999-11-01 | 1999-11-29
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1IRRIG | Golf Course Irrigation - XG-200M | 2 | DESIGN | 1999-11-03 | 1999-12-20 | 1999-11-03 | 1999-12-20
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1IRRIG | Golf Course Irrigation - XG-200M | 3 | BID/ REGISTER CONTRACT | 2000-05-08 | 2000-07-13 | 2000-05-08 | 2000-07-13
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1IRRIG | Golf Course Irrigation - XG-200M | 4 | CONSTRUCTION | 2000-09-05 | 2001-03-03 | 2000-09-05 | 2001-03-03
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1IRRIG | Golf Course Irrigation - XG-200M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2001-03-04 | 2002-03-03 | 2001-03-04 | 2021-03-03
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1JASPBB | JASPER BASEBALL STADIUM | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1JASPBB | JASPER BASEBALL STADIUM | 2 | DESIGN | 2019-12-28 | 2021-12-26 | 2019-12-28 | 2021-12-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1JASPBB | JASPER BASEBALL STADIUM | 3 | BID/ REGISTER CONTRACT | 2021-12-27 | 2022-09-22 | 2021-12-27 | 2022-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1JASPBB | JASPER BASEBALL STADIUM | 4 | CONSTRUCTION | 2022-09-23 | 2024-09-21 | 2022-09-23 | 2024-09-21
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1JASPBB | JASPER BASEBALL STADIUM | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-09-22 | 2025-09-21 | 2024-09-22 | 2025-09-21
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1MELCOM | CPI PH 1- Melrose Commons Site 32 - XG3200-111M | 1 | DEVELOP SCOPE | 2007-07-01 | 2007-09-28 | 2007-07-01 | 2007-09-28
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1MELCOM | CPI PH 1- Melrose Commons Site 32 - XG3200-111M | 2 | DESIGN | 2007-09-29 | 2007-12-27 | 2007-09-29 | 2007-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1MELCOM | CPI PH 1- Melrose Commons Site 32 - XG3200-111M | 3 | BID/ REGISTER CONTRACT | 2007-12-28 | 2008-03-26 | 2007-12-28 | 2008-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1MELCOM | CPI PH 1- Melrose Commons Site 32 - XG3200-111M | 4 | CONSTRUCTION | 2008-03-27 | 2009-03-26 | 2008-03-27 | 2009-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1MELCOM | CPI PH 1- Melrose Commons Site 32 - XG3200-111M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2009-03-27 | 2010-03-26 | 2009-03-27 | 2022-09-06
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1MELRO | Melrose Commons URA Site 62 Park Development (X350-119M) | 1 | DEVELOP SCOPE | 2015-10-16 | 2016-04-12 | 2015-10-16 | 2016-04-12
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1MELRO | Melrose Commons URA Site 62 Park Development (X350-119M) | 2 | DESIGN | 2016-04-13 | 2017-07-11 | 2016-04-13 | 2017-07-11
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1MELRO | Melrose Commons URA Site 62 Park Development (X350-119M) | 3 | BID/ REGISTER CONTRACT | 2017-07-12 | 2018-04-07 | 2017-07-12 | 2018-04-07
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1MELRO | Melrose Commons URA Site 62 Park Development (X350-119M) | 4 | CONSTRUCTION | 2018-04-08 | 2019-04-07 | 2018-04-08 | 2019-04-07
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1MELRO | Melrose Commons URA Site 62 Park Development (X350-119M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-04-08 | 2020-04-06 | 2019-04-08 | 2023-04-06
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1OWEND2 | OWEN F. DOLEN PK GOLDEN AGE CTR X016-114M | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2013-09-28
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1OWEND2 | OWEN F. DOLEN PK GOLDEN AGE CTR X016-114M | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2013-09-29 | 2013-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1OWEND2 | OWEN F. DOLEN PK GOLDEN AGE CTR X016-114M | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2013-12-28 | 2014-03-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1OWEND2 | OWEN F. DOLEN PK GOLDEN AGE CTR X016-114M | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2014-03-28 | 2015-03-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1OWEND2 | OWEN F. DOLEN PK GOLDEN AGE CTR X016-114M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2022-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1OWEND3 | OWEN DOLEN RECREATION CENTER - X016-118M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1OWEND3 | OWEN DOLEN RECREATION CENTER - X016-118M | 2 | DESIGN | 2017-12-28 | 2019-12-27 | 2017-12-28 | 2019-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1OWEND3 | OWEN DOLEN RECREATION CENTER - X016-118M | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1OWEND3 | OWEN DOLEN RECREATION CENTER - X016-118M | 4 | CONSTRUCTION | 2020-09-23 | 2022-09-22 | 2020-09-23 | 2022-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1OWEND3 | OWEN DOLEN RECREATION CENTER - X016-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PAVMOS | Mosholu Parkway Greenway Pavement Reconstruction (SoGR) | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PAVMOS | Mosholu Parkway Greenway Pavement Reconstruction (SoGR) | 2 | DESIGN | 2019-12-28 | 2021-12-26 | 2019-12-28 | 2021-12-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PAVMOS | Mosholu Parkway Greenway Pavement Reconstruction (SoGR) | 3 | BID/ REGISTER CONTRACT | 2021-12-27 | 2022-09-22 | 2021-12-27 | 2022-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PAVMOS | Mosholu Parkway Greenway Pavement Reconstruction (SoGR) | 4 | CONSTRUCTION | 2022-09-23 | 2024-09-21 | 2022-09-23 | 2024-09-21
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PAVMOS | Mosholu Parkway Greenway Pavement Reconstruction (SoGR) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-09-22 | 2025-09-21 | 2024-09-22 | 2025-09-21
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PDSMRC | PDF -St. Mary's Rec Ctr RC X045-115M | 1 | DEVELOP SCOPE | 2014-05-20 | 2014-08-17 | 2014-05-20 | 2014-08-17
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PDSMRC | PDF -St. Mary's Rec Ctr RC X045-115M | 2 | DESIGN | 2014-08-18 | 2014-11-15 | 2014-08-18 | 2017-09-29
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PDSMRC | PDF -St. Mary's Rec Ctr RC X045-115M | 3 | BID/ REGISTER CONTRACT | 2014-11-16 | 2015-02-13 | 2017-09-30 | 2017-12-28
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PDSMRC | PDF -St. Mary's Rec Ctr RC X045-115M | 4 | CONSTRUCTION | 2015-02-14 | 2016-02-13 | 2017-12-29 | 2018-12-28
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PDSMRC | PDF -St. Mary's Rec Ctr RC X045-115M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-02-14 | 2017-02-12 | 2018-12-29 | 2019-12-28
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PELBRV | Pelham parkway -connection to Bronx river greenwayX002-211M | 1 | DEVELOP SCOPE | 2008-07-01 | 2008-09-28 | 2008-07-01 | 2011-09-28
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PELBRV | Pelham parkway -connection to Bronx river greenwayX002-211M | 2 | DESIGN | 2008-09-29 | 2008-12-27 | 2011-09-29 | 2012-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PELBRV | Pelham parkway -connection to Bronx river greenwayX002-211M | 3 | BID/ REGISTER CONTRACT | 2008-12-28 | 2009-03-27 | 2012-12-29 | 2013-12-30
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PELBRV | Pelham parkway -connection to Bronx river greenwayX002-211M | 4 | CONSTRUCTION | 2009-03-28 | 2010-03-27 | 2013-12-31 | 2014-12-01
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PELBRV | Pelham parkway -connection to Bronx river greenwayX002-211M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2010-03-28 | 2011-03-27 | 2014-12-02 | 2021-12-02
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PELDOG | Pelham Parkway Dog Run (X002-116M) | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2016-02-02
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PELDOG | Pelham Parkway Dog Run (X002-116M) | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2016-02-03 | 2017-07-05
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PELDOG | Pelham Parkway Dog Run (X002-116M) | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2017-07-13 | 2018-05-30
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PELDOG | Pelham Parkway Dog Run (X002-116M) | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2018-06-11 | 2019-07-11
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PELDOG | Pelham Parkway Dog Run (X002-116M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2019-07-12 | 2020-07-11
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PELSHO | Pelham Bay Park- Shoreline Recons. (X039-116M) | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PELSHO | Pelham Bay Park- Shoreline Recons. (X039-116M) | 2 | DESIGN | 2016-12-28 | 2018-12-27 | 2016-12-28 | 2018-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PELSHO | Pelham Bay Park- Shoreline Recons. (X039-116M) | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PELSHO | Pelham Bay Park- Shoreline Recons. (X039-116M) | 4 | CONSTRUCTION | 2019-09-24 | 2021-09-22 | 2019-09-24 | 2021-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PELSHO | Pelham Bay Park- Shoreline Recons. (X039-116M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PL12A3 | St James Park - Recon two basketball courts XG-112M | 1 | DEVELOP SCOPE | 2011-07-01 | 2011-09-28 | 2011-07-01 | 2011-09-28
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PL12A3 | St James Park - Recon two basketball courts XG-112M | 2 | DESIGN | 2011-09-29 | 2011-12-27 | 2011-09-29 | 2011-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PL12A3 | St James Park - Recon two basketball courts XG-112M | 3 | BID/ REGISTER CONTRACT | 2011-12-28 | 2012-03-26 | 2011-12-28 | 2012-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PL12A3 | St James Park - Recon two basketball courts XG-112M | 4 | CONSTRUCTION | 2012-03-27 | 2013-03-26 | 2012-03-27 | 2013-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PL12A3 | St James Park - Recon two basketball courts XG-112M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-03-27 | 2014-03-26 | 2013-03-27 | 2014-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PLG10B | FY10 Playground Requirements (XG-410M) | 1 | DEVELOP SCOPE | 2010-07-01 | 2010-09-28 | 2010-07-01 | 2010-09-28
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PLG10B | FY10 Playground Requirements (XG-410M) | 2 | DESIGN | 2010-09-29 | 2010-12-27 | 2010-09-29 | 2010-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PLG10B | FY10 Playground Requirements (XG-410M) | 3 | BID/ REGISTER CONTRACT | 2010-12-28 | 2011-03-27 | 2010-12-28 | 2011-03-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PLG10B | FY10 Playground Requirements (XG-410M) | 4 | CONSTRUCTION | 2011-03-28 | 2012-03-26 | 2011-03-28 | 2012-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PLG10B | FY10 Playground Requirements (XG-410M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-03-27 | 2013-03-26 | 2012-03-27 | 2023-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PLG11B | FY11 Playground Requirements (XG-415M) | 1 | DEVELOP SCOPE | 2010-07-01 | 2010-09-28 | 2010-07-01 | 2010-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PLG11B | FY11 Playground Requirements (XG-415M) | 2 | DESIGN | 2010-09-29 | 2010-12-27 | 2010-12-28 | 2012-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PLG11B | FY11 Playground Requirements (XG-415M) | 3 | BID/ REGISTER CONTRACT | 2010-12-28 | 2011-03-27 | 2012-03-27 | 2012-12-21
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PLG11B | FY11 Playground Requirements (XG-415M) | 4 | CONSTRUCTION | 2011-03-28 | 2012-03-26 | 2012-12-22 | 2013-12-21
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PLG11B | FY11 Playground Requirements (XG-415M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-03-27 | 2013-03-26 | 2013-12-22 | 2021-12-21
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PNYFL5 | PlaNYC- Coop City ballfield - Irrigation Install X251-116M | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2013-09-28
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PNYFL5 | PlaNYC- Coop City ballfield - Irrigation Install X251-116M | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2013-09-29 | 2013-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PNYFL5 | PlaNYC- Coop City ballfield - Irrigation Install X251-116M | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2013-12-28 | 2014-03-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PNYFL5 | PlaNYC- Coop City ballfield - Irrigation Install X251-116M | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2014-03-28 | 2015-03-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PNYFL5 | PlaNYC- Coop City ballfield - Irrigation Install X251-116M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2021-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PNYR07 | PLANYC- BX PK CHANNEL RESTORATION X002-214M | 1 | DEVELOP SCOPE | 2014-07-01 | 2014-09-28 | 2014-07-01 | 2014-09-28
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PNYR07 | PLANYC- BX PK CHANNEL RESTORATION X002-214M | 2 | DESIGN | 2014-09-29 | 2014-12-27 | 2014-09-29 | 2014-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PNYR07 | PLANYC- BX PK CHANNEL RESTORATION X002-214M | 3 | BID/ REGISTER CONTRACT | 2014-12-28 | 2015-03-27 | 2014-12-28 | 2015-03-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PNYR07 | PLANYC- BX PK CHANNEL RESTORATION X002-214M | 4 | CONSTRUCTION | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2016-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PNYR07 | PLANYC- BX PK CHANNEL RESTORATION X002-214M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2023-12-05
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1POECOT | POE COTTAGE - INSTALLATION OF ROOF & EXTERIOR RENOVATIONS | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1POECOT | POE COTTAGE - INSTALLATION OF ROOF & EXTERIOR RENOVATIONS | 2 | DESIGN | 2019-12-28 | 2021-12-26 | 2019-12-28 | 2021-12-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1POECOT | POE COTTAGE - INSTALLATION OF ROOF & EXTERIOR RENOVATIONS | 3 | BID/ REGISTER CONTRACT | 2021-12-27 | 2022-09-22 | 2021-12-27 | 2022-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1POECOT | POE COTTAGE - INSTALLATION OF ROOF & EXTERIOR RENOVATIONS | 4 | CONSTRUCTION | 2022-09-23 | 2024-09-21 | 2022-09-23 | 2024-09-21
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1POECOT | POE COTTAGE - INSTALLATION OF ROOF & EXTERIOR RENOVATIONS | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-09-22 | 2025-09-21 | 2024-09-22 | 2025-09-21
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PTSNPK | Patterson Park (X155-116M | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2015-09-28
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PTSNPK | Patterson Park (X155-116M | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2015-09-29 | 2015-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PTSNPK | Patterson Park (X155-116M | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2015-12-28 | 2016-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PTSNPK | Patterson Park (X155-116M | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PTSNPK | Patterson Park (X155-116M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2017-03-27 | 2024-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PUGSLY | PUGSLEY CREEK & SOUNDVIEW PARKS INSTALLATION OF BLUE LIGHT | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PUGSLY | PUGSLEY CREEK & SOUNDVIEW PARKS INSTALLATION OF BLUE LIGHT | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PUGSLY | PUGSLEY CREEK & SOUNDVIEW PARKS INSTALLATION OF BLUE LIGHT | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PUGSLY | PUGSLEY CREEK & SOUNDVIEW PARKS INSTALLATION OF BLUE LIGHT | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PUGSLY | PUGSLEY CREEK & SOUNDVIEW PARKS INSTALLATION OF BLUE LIGHT | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PUTNAM | Putnam Greenway- X092-508M | 1 | DEVELOP SCOPE | 2006-07-01 | 2006-09-28 | 2006-07-01 | 2006-09-28
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PUTNAM | Putnam Greenway- X092-508M | 2 | DESIGN | 2006-09-29 | 2006-12-27 | 2006-09-29 | 2018-01-29
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PUTNAM | Putnam Greenway- X092-508M | 3 | BID/ REGISTER CONTRACT | 2006-12-28 | 2007-03-27 | 2018-01-30 | 2018-04-29
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PUTNAM | Putnam Greenway- X092-508M | 4 | CONSTRUCTION | 2007-03-28 | 2008-03-26 | 2018-04-30 | 2019-04-29
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PUTNAM | Putnam Greenway- X092-508M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-27 | 2009-03-26 | 2011-03-27 | 2021-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1RNQARF | Ranaqua Roof Reconstruction | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1RNQARF | Ranaqua Roof Reconstruction | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1RNQARF | Ranaqua Roof Reconstruction | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1RNQARF | Ranaqua Roof Reconstruction | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1RNQARF | Ranaqua Roof Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1RNQRMP | Reconstruction of Ranaqua M&O Storehouse Ramp | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1RNQRMP | Reconstruction of Ranaqua M&O Storehouse Ramp | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1RNQRMP | Reconstruction of Ranaqua M&O Storehouse Ramp | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1RNQRMP | Reconstruction of Ranaqua M&O Storehouse Ramp | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1RNQRMP | Reconstruction of Ranaqua M&O Storehouse Ramp | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1SPACET | SpaceTime Playgroun Reconstruction | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1SPACET | SpaceTime Playgroun Reconstruction | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1SPACET | SpaceTime Playgroun Reconstruction | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1SPACET | SpaceTime Playgroun Reconstruction | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1SPACET | SpaceTime Playgroun Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1STFPEL | Synthetic Turf Field Reconstruction at Pelham Bay | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1STFPEL | Synthetic Turf Field Reconstruction at Pelham Bay | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1STFPEL | Synthetic Turf Field Reconstruction at Pelham Bay | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1STFPEL | Synthetic Turf Field Reconstruction at Pelham Bay | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1STFPEL | Synthetic Turf Field Reconstruction at Pelham Bay | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1STJMPK | St. James Park | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1STJMPK | St. James Park | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1STJMPK | St. James Park | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1STJMPK | St. James Park | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1STJMPK | St. James Park | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1TRAILX | West Farms Park - Construction Continuation X288-114M | 1 | DEVELOP SCOPE | 2014-01-07 | 2014-04-06 | 2014-01-07 | 2014-12-02
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1TRAILX | West Farms Park - Construction Continuation X288-114M | 2 | DESIGN | 2014-04-07 | 2014-07-05 | 2014-12-03 | 2017-01-29
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1TRAILX | West Farms Park - Construction Continuation X288-114M | 3 | BID/ REGISTER CONTRACT | 2014-07-06 | 2014-10-03 | 2016-11-02 | 2019-01-08
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1TRAILX | West Farms Park - Construction Continuation X288-114M | 4 | CONSTRUCTION | 2014-10-04 | 2015-10-03 | 2019-04-01 | 2020-05-05
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1TRAILX | West Farms Park - Construction Continuation X288-114M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-10-04 | 2016-10-02 | 2020-05-06 | 2022-05-06
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1TRE15A | FY15 Street Tree Planting, Bronx CB's 1-8 , XG-115M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-27 | 2017-03-26 | 2016-03-27 | 2017-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1TRE18B | FY 18 Street Trees Bronx CB's 9-12, XG- | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1TRE18B | FY 18 Street Trees Bronx CB's 9-12, XG- | 2 | DESIGN | 2017-12-28 | 2018-06-25 | 2017-12-28 | 2018-06-25
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1TRE18B | FY 18 Street Trees Bronx CB's 9-12, XG- | 3 | BID/ REGISTER CONTRACT | 2018-06-26 | 2019-03-22 | 2018-06-26 | 2019-03-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1TRE18B | FY 18 Street Trees Bronx CB's 9-12, XG- | 4 | CONSTRUCTION | 2019-03-23 | 2020-09-12 | 2019-03-23 | 2020-09-12
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1TRE18B | FY 18 Street Trees Bronx CB's 9-12, XG- | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-13 | 2022-09-12 | 2020-09-13 | 2022-09-12
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1TRE20A | FY20 Street Trees Bronx CB's 1-4, XG-119M | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1TRE20A | FY20 Street Trees Bronx CB's 1-4, XG-119M | 2 | DESIGN | 2018-12-28 | 2019-06-25 | 2018-12-28 | 2019-06-25
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1TRE20A | FY20 Street Trees Bronx CB's 1-4, XG-119M | 3 | BID/ REGISTER CONTRACT | 2019-06-26 | 2020-03-21 | 2019-06-26 | 2020-03-21
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1TRE20A | FY20 Street Trees Bronx CB's 1-4, XG-119M | 4 | CONSTRUCTION | 2020-03-22 | 2021-09-12 | 2020-03-22 | 2021-09-12
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1TRE20A | FY20 Street Trees Bronx CB's 1-4, XG-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-13 | 2023-09-12 | 2021-09-13 | 2023-09-12
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1TRE20B | FY20 Street Trees Bronx CB's 5-8 XG-219M | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1TRE20B | FY20 Street Trees Bronx CB's 5-8 XG-219M | 2 | DESIGN | 2018-12-28 | 2019-06-25 | 2018-12-28 | 2019-06-25
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1TRE20B | FY20 Street Trees Bronx CB's 5-8 XG-219M | 3 | BID/ REGISTER CONTRACT | 2019-06-26 | 2020-03-21 | 2019-06-26 | 2020-03-21
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1TRE20B | FY20 Street Trees Bronx CB's 5-8 XG-219M | 4 | CONSTRUCTION | 2020-03-22 | 2021-09-12 | 2020-03-22 | 2021-09-12
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1TRE20B | FY20 Street Trees Bronx CB's 5-8 XG-219M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-13 | 2023-09-12 | 2021-09-13 | 2023-09-12
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1TRE21A | FY21 Street Trees Bronx CB's 1-4,9,10 XG- | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1TRE21A | FY21 Street Trees Bronx CB's 1-4,9,10 XG- | 2 | DESIGN | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1TRE21A | FY21 Street Trees Bronx CB's 1-4,9,10 XG- | 3 | BID/ REGISTER CONTRACT | 2020-09-23 | 2021-06-19 | 2020-09-23 | 2021-06-19
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1TRE21A | FY21 Street Trees Bronx CB's 1-4,9,10 XG- | 4 | CONSTRUCTION | 2021-06-20 | 2023-12-16 | 2021-06-20 | 2023-12-16
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1TRE21A | FY21 Street Trees Bronx CB's 1-4,9,10 XG- | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-12-17 | 2025-12-15 | 2023-12-17 | 2025-12-15
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1TREL21 | FY21 Street Trees BX CB's5-8,11,12 (3Y) | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1TREL21 | FY21 Street Trees BX CB's5-8,11,12 (3Y) | 2 | DESIGN | 2019-12-28 | 2021-06-19 | 2019-12-28 | 2021-06-19
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1TREL21 | FY21 Street Trees BX CB's5-8,11,12 (3Y) | 3 | BID/ REGISTER CONTRACT | 2021-06-20 | 2022-03-16 | 2021-06-20 | 2022-03-16
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1TREL21 | FY21 Street Trees BX CB's5-8,11,12 (3Y) | 4 | CONSTRUCTION | 2022-03-17 | 2025-03-15 | 2022-03-17 | 2025-03-15
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1TREL21 | FY21 Street Trees BX CB's5-8,11,12 (3Y) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-03-16 | 2027-03-15 | 2025-03-16 | 2027-03-15
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1VCSHND | Van Cortlandt Park, Shandler Rec. Area, all 3 Priorities | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1VCSHND | Van Cortlandt Park, Shandler Rec. Area, all 3 Priorities | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1VCSHND | Van Cortlandt Park, Shandler Rec. Area, all 3 Priorities | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1VCSHND | Van Cortlandt Park, Shandler Rec. Area, all 3 Priorities | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1VCSHND | Van Cortlandt Park, Shandler Rec. Area, all 3 Priorities | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1VCSTDM | Pavement | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1VCSTDM | Pavement | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1VCSTDM | Pavement | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1VCSTDM | Pavement | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1VCSTDM | Pavement | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1VCTRAL | Van Cortlandt's Tail | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1VCTRAL | Van Cortlandt's Tail | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1VCTRAL | Van Cortlandt's Tail | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1VCTRAL | Van Cortlandt's Tail | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1VCTRAL | Van Cortlandt's Tail | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1VNFPOL | Van Nest Flag Pole X093-116M | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2016-02-08
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1VNFPOL | Van Nest Flag Pole X093-116M | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2016-02-09 | 2017-05-08
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1VNFPOL | Van Nest Flag Pole X093-116M | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2017-06-16 | 2017-11-13
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1VNFPOL | Van Nest Flag Pole X093-116M | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2018-02-13 | 2019-02-05
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1VNFPOL | Van Nest Flag Pole X093-116M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2019-02-06 | 2021-12-18
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1WDLNCS | Woodlawn Playground C.S X092-119M | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1WDLNCS | Woodlawn Playground C.S X092-119M | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1WDLNCS | Woodlawn Playground C.S X092-119M | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1WDLNCS | Woodlawn Playground C.S X092-119M | 4 | CONSTRUCTION | 2020-09-23 | 2022-03-21 | 2020-09-23 | 2022-03-21
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1WDLNCS | Woodlawn Playground C.S X092-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-22 | 2023-03-21 | 2022-03-22 | 2023-03-21
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1WDLNSS | Woodlawn Plgd- Recon of Spray Shower X092-118M | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1WDLNSS | Woodlawn Plgd- Recon of Spray Shower X092-118M | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2018-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1WDLNSS | Woodlawn Plgd- Recon of Spray Shower X092-118M | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2018-12-28 | 2019-09-23
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1WDLNSS | Woodlawn Plgd- Recon of Spray Shower X092-118M | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2020-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1WDLNSS | Woodlawn Plgd- Recon of Spray Shower X092-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1WPSOTO | Sotomayor Houses - Construction of Open Space | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1WPSOTO | Sotomayor Houses - Construction of Open Space | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1WPSOTO | Sotomayor Houses - Construction of Open Space | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1WPSOTO | Sotomayor Houses - Construction of Open Space | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1WPSOTO | Sotomayor Houses - Construction of Open Space | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1WPWATS | Watson Houses - Construction of Open Space | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-12-27 | 2019-07-01 | 2019-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1WPWATS | Watson Houses - Construction of Open Space | 2 | DESIGN | 2019-12-28 | 2020-12-26 | 2019-12-28 | 2020-12-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1WPWATS | Watson Houses - Construction of Open Space | 3 | BID/ REGISTER CONTRACT | 2020-12-27 | 2021-09-22 | 2020-12-27 | 2021-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1WPWATS | Watson Houses - Construction of Open Space | 4 | CONSTRUCTION | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2022-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1WPWATS | Watson Houses - Construction of Open Space | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-09-23 | 2023-09-22 | 2022-09-23 | 2023-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-6CYANK4 | YANKEE STADIUM - REQUIREMENTS - X237-104M | 1 | DEVELOP SCOPE | 2006-07-01 | 2006-09-28 | 2006-07-01 | 2006-09-28
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-6CYANK4 | YANKEE STADIUM - REQUIREMENTS - X237-104M | 2 | DESIGN | 2006-09-29 | 2006-12-27 | 2006-09-29 | 2006-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-6CYANK4 | YANKEE STADIUM - REQUIREMENTS - X237-104M | 3 | BID/ REGISTER CONTRACT | 2006-12-28 | 2007-03-27 | 2006-12-28 | 2007-03-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-6CYANK4 | YANKEE STADIUM - REQUIREMENTS - X237-104M | 4 | CONSTRUCTION | 2007-03-28 | 2008-03-26 | 2007-03-28 | 2008-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-6CYANK4 | YANKEE STADIUM - REQUIREMENTS - X237-104M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-03-27 | 2009-03-26 | 2008-03-27 | 2009-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | SANDY1-03 | SANDY - Bronx Type 2 Playgrounds R/C | 1 | DEVELOP SCOPE | 2018-07-01 | 2018-12-27 | 2018-07-01 | 2018-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | SANDY1-03 | SANDY - Bronx Type 2 Playgrounds R/C | 2 | DESIGN | 2018-12-28 | 2019-12-27 | 2018-12-28 | 2019-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | SANDY1-03 | SANDY - Bronx Type 2 Playgrounds R/C | 3 | BID/ REGISTER CONTRACT | 2019-12-28 | 2020-09-22 | 2019-12-28 | 2020-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | SANDY1-03 | SANDY - Bronx Type 2 Playgrounds R/C | 4 | CONSTRUCTION | 2020-09-23 | 2021-09-22 | 2020-09-23 | 2021-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | SANDY1-03 | SANDY - Bronx Type 2 Playgrounds R/C | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-09-23 | 2022-09-22 | 2021-09-23 | 2024-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | SANDY1-06 | SANDY - Ferry Point Park Type 3 X126-115M | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2013-09-28
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | SANDY1-06 | SANDY - Ferry Point Park Type 3 X126-115M | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2013-09-29 | 2013-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | SANDY1-06 | SANDY - Ferry Point Park Type 3 X126-115M | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2013-12-28 | 2014-03-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | SANDY1-06 | SANDY - Ferry Point Park Type 3 X126-115M | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2014-03-28 | 2015-03-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | SANDY1-06 | SANDY - Ferry Point Park Type 3 X126-115M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2022-03-26
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | SANDY1-09 | SANDY Type 3 Pelham Bay Park - Recon seawall X039-215M | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | SANDY1-09 | SANDY Type 3 Pelham Bay Park - Recon seawall X039-215M | 2 | DESIGN | 2016-12-28 | 2017-12-27 | 2016-12-28 | 2017-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | SANDY1-09 | SANDY Type 3 Pelham Bay Park - Recon seawall X039-215M | 3 | BID/ REGISTER CONTRACT | 2017-12-28 | 2018-09-23 | 2017-12-28 | 2018-09-23
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | SANDY1-09 | SANDY Type 3 Pelham Bay Park - Recon seawall X039-215M | 4 | CONSTRUCTION | 2018-09-24 | 2019-09-23 | 2018-09-24 | 2019-09-23
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | SANDY1-09 | SANDY Type 3 Pelham Bay Park - Recon seawall X039-215M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-09-24 | 2020-09-22 | 2019-09-24 | 2024-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | SANDY1-10 | Hammond Cove Marina X310-117M | 1 | DEVELOP SCOPE | 2016-07-01 | 2016-12-27 | 2016-07-01 | 2016-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | SANDY1-10 | Hammond Cove Marina X310-117M | 2 | DESIGN | 2016-12-28 | 2018-03-22 | 2016-12-28 | 2017-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | SANDY1-10 | Hammond Cove Marina X310-117M | 3 | BID/ REGISTER CONTRACT | 2018-03-23 | 2018-12-17 | 2017-12-28 | 2018-09-23
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | SANDY1-10 | Hammond Cove Marina X310-117M | 4 | CONSTRUCTION | 2018-12-18 | 2020-12-16 | 2018-09-24 | 2019-09-23
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | SANDY1-10 | Hammond Cove Marina X310-117M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-12-17 | 2021-12-16 | 2019-09-24 | 2022-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | SANDY1-11 | Pelham Bay Landfill | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-12-27 | 2017-07-01 | 2017-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | SANDY1-11 | Pelham Bay Landfill | 2 | DESIGN | 2017-12-28 | 2018-12-27 | 2017-12-28 | 2019-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | SANDY1-11 | Pelham Bay Landfill | 3 | BID/ REGISTER CONTRACT | 2018-12-28 | 2019-09-23 | 2019-12-28 | 2020-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | SANDY1-11 | Pelham Bay Landfill | 4 | CONSTRUCTION | 2019-09-24 | 2020-09-22 | 2020-09-23 | 2022-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | SANDY1-11 | Pelham Bay Landfill | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-09-23 | 2021-09-22 | 2022-09-23 | 2024-09-22
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | SANDY6-11 | SANDY - Park reconstruction (Type 3 ) (Non - Emergency) | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2013-07-01 | 2013-09-28
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | SANDY6-11 | SANDY - Park reconstruction (Type 3 ) (Non - Emergency) | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2013-09-29 | 2013-12-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | SANDY6-11 | SANDY - Park reconstruction (Type 3 ) (Non - Emergency) | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2013-12-28 | 2014-03-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | SANDY6-11 | SANDY - Park reconstruction (Type 3 ) (Non - Emergency) | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2014-03-28 | 2015-03-27
20201123 | BRONX | 846 | DEPT OF PARKS AND RECREATION | SANDY6-11 | SANDY - Park reconstruction (Type 3 ) (Non - Emergency) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2015-03-28 | 2024-03-26
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | C75-FCAD | FACADE RECONSTRUCTION AT EMTC, NIC,QDC, MDC, and GRVC | 1 | DEVELOP SCOPE | 2006-07-01 | 2006-09-28 | 2007-05-13 | 2007-08-10
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | C75-FCAD | FACADE RECONSTRUCTION AT EMTC, NIC,QDC, MDC, and GRVC | 2 | PRELIMINARY DESIGN | 2006-09-29 | 2007-01-26 | 2007-08-11 | 2007-12-08
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | C75-FCAD | FACADE RECONSTRUCTION AT EMTC, NIC,QDC, MDC, and GRVC | 3 | FINAL DESIGN | 2007-01-27 | 2007-07-25 | 2007-12-09 | 2008-06-05
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | C75-FCAD | FACADE RECONSTRUCTION AT EMTC, NIC,QDC, MDC, and GRVC | 4 | BID AWARD AND REGISTER CONTRCT | 2007-07-26 | 2007-10-23 | 2008-06-06 | 2008-09-03
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | C75-FCAD | FACADE RECONSTRUCTION AT EMTC, NIC,QDC, MDC, and GRVC | 5 | CONSTRUCTION TO 25% | 2007-10-24 | 2008-02-20 | 2008-09-04 | 2009-01-01
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | C75-FCAD | FACADE RECONSTRUCTION AT EMTC, NIC,QDC, MDC, and GRVC | 6 | CONSTRUCTION TO 50% | 2008-02-21 | 2008-06-19 | 2009-01-02 | 2010-05-01
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | C75-FCAD | FACADE RECONSTRUCTION AT EMTC, NIC,QDC, MDC, and GRVC | 7 | CONSTRUCTION TO 75% | 2008-06-20 | 2008-10-17 | 2010-05-02 | 2014-01-09
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | C75-FCAD | FACADE RECONSTRUCTION AT EMTC, NIC,QDC, MDC, and GRVC | 8 | ORIGINAL EQUIP & FURNISHING | 2008-10-18 | 2009-01-15 | 2014-01-10 | 2014-08-20
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | C75-FCAD | FACADE RECONSTRUCTION AT EMTC, NIC,QDC, MDC, and GRVC | 9 | SUBSTANTIAL COMPLETION | 2009-01-16 | 2009-03-16 | 2014-08-21 | 2019-06-28
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | C75-FCAD | FACADE RECONSTRUCTION AT EMTC, NIC,QDC, MDC, and GRVC | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2009-03-17 | 2009-04-15 | 2019-06-29 | 2022-11-19
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | C75NICSHW | NIC SHOWER RECONSTRUCTION | 1 | DEVELOP SCOPE | 2006-01-30 | 2006-04-29 | 2007-12-25 | 2008-03-23
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | C75NICSHW | NIC SHOWER RECONSTRUCTION | 2 | PRELIMINARY DESIGN | 2006-04-30 | 2006-08-27 | 2008-03-24 | 2008-07-21
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | C75NICSHW | NIC SHOWER RECONSTRUCTION | 3 | FINAL DESIGN | 2006-08-28 | 2007-02-23 | 2008-07-22 | 2009-01-17
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | C75NICSHW | NIC SHOWER RECONSTRUCTION | 4 | BID AWARD AND REGISTER CONTRCT | 2007-02-24 | 2007-05-24 | 2009-01-18 | 2009-04-17
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | C75NICSHW | NIC SHOWER RECONSTRUCTION | 5 | CONSTRUCTION TO 25% | 2007-05-25 | 2007-09-21 | 2009-04-18 | 2009-08-15
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | C75NICSHW | NIC SHOWER RECONSTRUCTION | 6 | CONSTRUCTION TO 50% | 2007-09-22 | 2008-01-19 | 2009-08-16 | 2009-12-13
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | C75NICSHW | NIC SHOWER RECONSTRUCTION | 7 | CONSTRUCTION TO 75% | 2008-01-20 | 2008-05-18 | 2009-12-14 | 2010-04-12
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | C75NICSHW | NIC SHOWER RECONSTRUCTION | 8 | ORIGINAL EQUIP & FURNISHING | 2008-05-19 | 2008-08-16 | 2011-09-22 | 2011-09-21
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | C75NICSHW | NIC SHOWER RECONSTRUCTION | 9 | SUBSTANTIAL COMPLETION | 2008-08-17 | 2008-10-15 | 2011-09-22 | 2011-09-21
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | C75NICSHW | NIC SHOWER RECONSTRUCTION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-10-16 | 2008-11-14 | 2011-09-22 | 2017-06-30
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO290BCHJ | BCHJ-Post Construction Work | 1 | PROJECT START | 2013-11-13 | 2013-11-13 | 2013-11-13 | 2013-11-13
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO290BCHJ | BCHJ-Post Construction Work | 2 | DESIGN START | 2014-02-14 | 2014-02-14 | 2014-02-14 | 2014-02-14
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO290BCHJ | BCHJ-Post Construction Work | 3 | DESIGN COMPLETION | 2014-12-24 | 2014-12-24 | 2014-12-24 | 2014-12-24
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO290BCHJ | BCHJ-Post Construction Work | 4 | CONSTRUCTION START | 2015-04-30 | 2015-05-01 | 2015-04-30 | 2015-05-01
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO290BCHJ | BCHJ-Post Construction Work | 5 | CONSTRUCTION COMPLETION | 2020-05-04 | 2020-05-04 | 2020-05-04 | 2024-05-04
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO290XSB1 | DASNY - BRONX CRIMINAL CT COMPLEX | 1 | PROJECT START | 1994-05-02 | 1994-05-02 | 1994-05-02 | 1994-05-02
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO290XSB1 | DASNY - BRONX CRIMINAL CT COMPLEX | 2 | DESIGN START | 1994-05-03 | 1995-04-10 | 1994-05-03 | 1995-04-10
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO290XSB1 | DASNY - BRONX CRIMINAL CT COMPLEX | 3 | DESIGN COMPLETION | 1995-04-11 | 2001-01-10 | 1995-04-11 | 2001-01-10
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO290XSB1 | DASNY - BRONX CRIMINAL CT COMPLEX | 4 | CONSTRUCTION START | 2001-01-11 | 2001-01-24 | 2001-01-11 | 2003-10-31
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO290XSB1 | DASNY - BRONX CRIMINAL CT COMPLEX | 5 | CONSTRUCTION COMPLETION | 2001-01-25 | 2006-09-01 | 2020-06-29 | 2024-06-30
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO293LL11 | 851 GRAND CONCOURSE - FACADE RECONSTRUCTION | 1 | DEVELOP SCOPE | 2021-03-01 | 2021-05-29 | 2021-03-01 | 2021-05-29
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO293LL11 | 851 GRAND CONCOURSE - FACADE RECONSTRUCTION | 2 | PRELIMINARY DESIGN | 2021-05-30 | 2021-09-26 | 2021-05-30 | 2021-09-26
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO293LL11 | 851 GRAND CONCOURSE - FACADE RECONSTRUCTION | 3 | FINAL DESIGN | 2021-09-27 | 2022-03-25 | 2021-09-27 | 2022-03-25
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO293LL11 | 851 GRAND CONCOURSE - FACADE RECONSTRUCTION | 4 | BID AWARD AND REGISTER CONTRCT | 2022-03-26 | 2022-06-23 | 2022-03-26 | 2022-06-23
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO293LL11 | 851 GRAND CONCOURSE - FACADE RECONSTRUCTION | 5 | CONSTRUCTION TO 25% | 2022-06-24 | 2022-10-21 | 2022-06-24 | 2022-10-21
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO293LL11 | 851 GRAND CONCOURSE - FACADE RECONSTRUCTION | 6 | CONSTRUCTION TO 50% | 2022-10-22 | 2023-02-18 | 2022-10-22 | 2023-02-18
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO293LL11 | 851 GRAND CONCOURSE - FACADE RECONSTRUCTION | 7 | CONSTRUCTION TO 75% | 2023-02-19 | 2023-06-18 | 2023-02-19 | 2023-06-18
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO293LL11 | 851 GRAND CONCOURSE - FACADE RECONSTRUCTION | 8 | ORIGINAL EQUIP & FURNISHING | 2023-06-19 | 2023-09-16 | 2023-06-19 | 2023-09-16
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO293LL11 | 851 GRAND CONCOURSE - FACADE RECONSTRUCTION | 9 | SUBSTANTIAL COMPLETION | 2023-09-17 | 2023-11-15 | 2023-09-17 | 2023-11-15
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO293LL11 | 851 GRAND CONCOURSE - FACADE RECONSTRUCTION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-11-16 | 2023-12-15 | 2023-11-16 | 2025-06-30
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO293SP | 851 GRAND CONCOURSE - FIRE PROTECTION/SPRINKLERS | 1 | DEVELOP SCOPE | 2017-02-01 | 2017-05-01 | 2017-02-01 | 2017-05-01
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO293SP | 851 GRAND CONCOURSE - FIRE PROTECTION/SPRINKLERS | 2 | PRELIMINARY DESIGN | 2017-05-02 | 2017-08-29 | 2017-05-02 | 2017-08-29
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO293SP | 851 GRAND CONCOURSE - FIRE PROTECTION/SPRINKLERS | 3 | FINAL DESIGN | 2017-08-30 | 2018-02-25 | 2017-08-30 | 2019-12-20
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO293SP | 851 GRAND CONCOURSE - FIRE PROTECTION/SPRINKLERS | 4 | BID AWARD AND REGISTER CONTRCT | 2018-02-26 | 2018-05-26 | 2019-12-21 | 2020-03-19
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO293SP | 851 GRAND CONCOURSE - FIRE PROTECTION/SPRINKLERS | 5 | CONSTRUCTION TO 25% | 2018-05-27 | 2018-09-23 | 2020-03-20 | 2021-10-04
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO293SP | 851 GRAND CONCOURSE - FIRE PROTECTION/SPRINKLERS | 6 | CONSTRUCTION TO 50% | 2018-09-24 | 2019-01-21 | 2021-10-05 | 2022-02-01
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO293SP | 851 GRAND CONCOURSE - FIRE PROTECTION/SPRINKLERS | 7 | CONSTRUCTION TO 75% | 2019-01-22 | 2019-05-21 | 2022-02-02 | 2022-06-01
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO293SP | 851 GRAND CONCOURSE - FIRE PROTECTION/SPRINKLERS | 8 | ORIGINAL EQUIP & FURNISHING | 2019-05-22 | 2019-08-19 | 2022-06-02 | 2022-08-30
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO293SP | 851 GRAND CONCOURSE - FIRE PROTECTION/SPRINKLERS | 9 | SUBSTANTIAL COMPLETION | 2019-08-20 | 2019-10-18 | 2022-08-31 | 2027-09-14
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO293SP | 851 GRAND CONCOURSE - FIRE PROTECTION/SPRINKLERS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-10-19 | 2019-11-17 | 2027-09-15 | 2027-10-14
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO294RF | 215 E161 ST.- ROOF | 1 | DEVELOP SCOPE | 2022-02-02 | 2022-05-02 | 2022-02-02 | 2022-05-02
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO294RF | 215 E161 ST.- ROOF | 2 | PRELIMINARY DESIGN | 2022-05-03 | 2022-08-30 | 2022-05-03 | 2022-08-30
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO294RF | 215 E161 ST.- ROOF | 3 | FINAL DESIGN | 2022-08-31 | 2023-02-26 | 2022-08-31 | 2023-02-26
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO294RF | 215 E161 ST.- ROOF | 4 | BID AWARD AND REGISTER CONTRCT | 2023-02-27 | 2023-05-27 | 2023-02-27 | 2023-05-27
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO294RF | 215 E161 ST.- ROOF | 5 | CONSTRUCTION TO 25% | 2023-05-28 | 2023-09-24 | 2023-05-28 | 2023-09-24
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO294RF | 215 E161 ST.- ROOF | 6 | CONSTRUCTION TO 50% | 2023-09-25 | 2024-01-22 | 2023-09-25 | 2024-01-22
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO294RF | 215 E161 ST.- ROOF | 7 | CONSTRUCTION TO 75% | 2024-01-23 | 2024-05-21 | 2024-01-23 | 2024-05-21
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO294RF | 215 E161 ST.- ROOF | 8 | ORIGINAL EQUIP & FURNISHING | 2024-05-22 | 2024-08-19 | 2024-05-22 | 2024-08-19
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO294RF | 215 E161 ST.- ROOF | 9 | SUBSTANTIAL COMPLETION | 2024-08-20 | 2024-10-18 | 2024-08-20 | 2024-10-18
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO294RF | 215 E161 ST.- ROOF | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-10-19 | 2024-11-17 | 2024-10-19 | 2024-11-17
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO295EV | 1118 GRAND CONCOURSE - ELEVATORS | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-08-29 | 2020-06-01 | 2020-08-29
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO295EV | 1118 GRAND CONCOURSE - ELEVATORS | 2 | PRELIMINARY DESIGN | 2020-08-30 | 2020-12-27 | 2020-08-30 | 2020-12-27
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO295EV | 1118 GRAND CONCOURSE - ELEVATORS | 3 | FINAL DESIGN | 2020-12-28 | 2021-06-25 | 2020-12-28 | 2021-06-25
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO295EV | 1118 GRAND CONCOURSE - ELEVATORS | 4 | BID AWARD AND REGISTER CONTRCT | 2021-06-26 | 2021-09-23 | 2021-06-26 | 2021-09-23
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO295EV | 1118 GRAND CONCOURSE - ELEVATORS | 5 | CONSTRUCTION TO 25% | 2021-09-24 | 2022-01-21 | 2021-09-24 | 2022-01-21
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO295EV | 1118 GRAND CONCOURSE - ELEVATORS | 6 | CONSTRUCTION TO 50% | 2022-01-22 | 2022-05-21 | 2022-01-22 | 2022-05-21
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO295EV | 1118 GRAND CONCOURSE - ELEVATORS | 7 | CONSTRUCTION TO 75% | 2022-05-22 | 2022-09-18 | 2022-05-22 | 2022-09-18
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO295EV | 1118 GRAND CONCOURSE - ELEVATORS | 8 | ORIGINAL EQUIP & FURNISHING | 2022-09-19 | 2022-12-17 | 2022-09-19 | 2022-12-17
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO295EV | 1118 GRAND CONCOURSE - ELEVATORS | 9 | SUBSTANTIAL COMPLETION | 2022-12-18 | 2023-02-15 | 2022-12-18 | 2023-02-15
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO295EV | 1118 GRAND CONCOURSE - ELEVATORS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-02-16 | 2023-03-17 | 2023-02-16 | 2023-03-17
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO295EV | 1118 GRAND CONCOURSE - ELEVATORS | 11 | PROJECT START | 2023-02-16 | 2023-03-17 | 2023-03-18 | 2023-03-18
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO295EV | 1118 GRAND CONCOURSE - ELEVATORS | 12 | DESIGN START | 2023-02-16 | 2023-03-17 | 2023-03-19 | 2023-03-19
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO295EV | 1118 GRAND CONCOURSE - ELEVATORS | 13 | DESIGN COMPLETION | 2023-02-16 | 2023-03-17 | 2023-03-20 | 2023-03-20
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO295EV | 1118 GRAND CONCOURSE - ELEVATORS | 14 | CONSTRUCTION START | 2023-02-16 | 2023-03-17 | 2023-03-21 | 2023-03-21
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO295EV | 1118 GRAND CONCOURSE - ELEVATORS | 15 | CONSTRUCTION COMPLETION | 2023-02-16 | 2023-03-17 | 2023-03-22 | 2024-09-30
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CRO-AGS | CROTON ABOVE-GROUND STRUCTURE AND LANDSCAPING | 1 | DEVELOP SCOPE | 2017-03-01 | 2017-05-29 | 2017-03-01 | 2017-05-29
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CRO-AGS | CROTON ABOVE-GROUND STRUCTURE AND LANDSCAPING | 2 | PRELIMINARY DESIGN | 2017-05-30 | 2017-09-26 | 2017-05-30 | 2017-09-26
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CRO-AGS | CROTON ABOVE-GROUND STRUCTURE AND LANDSCAPING | 3 | FINAL DESIGN | 2017-09-27 | 2018-03-25 | 2017-09-27 | 2018-03-25
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CRO-AGS | CROTON ABOVE-GROUND STRUCTURE AND LANDSCAPING | 4 | BID AWARD AND REGISTER CONTRCT | 2018-03-26 | 2018-06-23 | 2018-03-26 | 2018-06-23
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CRO-AGS | CROTON ABOVE-GROUND STRUCTURE AND LANDSCAPING | 5 | CONSTRUCTION TO 25% | 2018-06-24 | 2018-10-21 | 2018-06-24 | 2018-10-21
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CRO-AGS | CROTON ABOVE-GROUND STRUCTURE AND LANDSCAPING | 6 | CONSTRUCTION TO 50% | 2018-10-22 | 2019-02-18 | 2018-10-22 | 2019-02-18
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CRO-AGS | CROTON ABOVE-GROUND STRUCTURE AND LANDSCAPING | 7 | CONSTRUCTION TO 75% | 2019-02-19 | 2019-06-18 | 2019-02-19 | 2019-06-18
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CRO-AGS | CROTON ABOVE-GROUND STRUCTURE AND LANDSCAPING | 8 | ORIGINAL EQUIP & FURNISHING | 2019-06-19 | 2019-09-16 | 2019-06-19 | 2019-09-16
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CRO-AGS | CROTON ABOVE-GROUND STRUCTURE AND LANDSCAPING | 9 | SUBSTANTIAL COMPLETION | 2019-09-17 | 2019-11-15 | 2019-09-17 | 2022-06-02
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CRO-AGS | CROTON ABOVE-GROUND STRUCTURE AND LANDSCAPING | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-11-16 | 2019-12-15 | 2022-06-03 | 2023-06-02
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CV19COETR | Centers of Excellence: Tremont | 1 | PROJECT START | 2020-05-01 | 2020-05-01 | 2020-05-01 | 2020-05-01
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CV19COETR | Centers of Excellence: Tremont | 2 | DESIGN START | 2020-05-02 | 2020-05-02 | 2020-05-02 | 2020-05-02
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CV19COETR | Centers of Excellence: Tremont | 3 | DESIGN COMPLETION | 2020-05-03 | 2020-05-03 | 2020-05-03 | 2020-05-03
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CV19COETR | Centers of Excellence: Tremont | 4 | CONSTRUCTION START | 2020-05-04 | 2020-05-04 | 2020-05-04 | 2020-05-04
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CV19COETR | Centers of Excellence: Tremont | 5 | CONSTRUCTION COMPLETION | 2020-05-05 | 2021-06-30 | 2020-05-05 | 2021-06-30
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-553 | WATER MAIN IN SOUTHERN BLVD - WESTCHESTER AV & BOSTON RD | 1 | DEVELOP SCOPE | 2009-04-01 | 2009-06-29 | 2009-04-01 | 2009-06-29
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-553 | WATER MAIN IN SOUTHERN BLVD - WESTCHESTER AV & BOSTON RD | 2 | PRELIMINARY DESIGN | 2009-06-30 | 2009-10-27 | 2009-06-30 | 2009-10-27
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-553 | WATER MAIN IN SOUTHERN BLVD - WESTCHESTER AV & BOSTON RD | 3 | FINAL DESIGN | 2009-10-28 | 2010-04-25 | 2009-10-28 | 2010-04-25
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-553 | WATER MAIN IN SOUTHERN BLVD - WESTCHESTER AV & BOSTON RD | 4 | BID AWARD AND REGISTER CONTRCT | 2010-04-26 | 2010-07-24 | 2015-03-11 | 2015-06-08
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-553 | WATER MAIN IN SOUTHERN BLVD - WESTCHESTER AV & BOSTON RD | 5 | CONSTRUCTION TO 25% | 2010-07-25 | 2010-11-21 | 2015-06-09 | 2015-06-08
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-553 | WATER MAIN IN SOUTHERN BLVD - WESTCHESTER AV & BOSTON RD | 6 | CONSTRUCTION TO 50% | 2010-11-22 | 2011-03-21 | 2015-06-09 | 2015-06-08
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-553 | WATER MAIN IN SOUTHERN BLVD - WESTCHESTER AV & BOSTON RD | 7 | CONSTRUCTION TO 75% | 2011-03-22 | 2011-07-19 | 2015-06-09 | 2015-06-08
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-553 | WATER MAIN IN SOUTHERN BLVD - WESTCHESTER AV & BOSTON RD | 8 | ORIGINAL EQUIP & FURNISHING | 2011-07-20 | 2011-10-17 | 2015-06-09 | 2015-06-08
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-553 | WATER MAIN IN SOUTHERN BLVD - WESTCHESTER AV & BOSTON RD | 9 | SUBSTANTIAL COMPLETION | 2011-10-18 | 2011-12-16 | 2015-06-09 | 2015-06-08
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-553 | WATER MAIN IN SOUTHERN BLVD - WESTCHESTER AV & BOSTON RD | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2011-12-17 | 2012-01-15 | 2016-12-27 | 2029-06-30
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-556A | UPGRADE WATER MAINS AT NY BOTANICAL GARDENS (BX) | 1 | DEVELOP SCOPE | 2008-03-01 | 2008-05-29 | 2017-07-01 | 2017-09-28
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-556A | UPGRADE WATER MAINS AT NY BOTANICAL GARDENS (BX) | 2 | PRELIMINARY DESIGN | 2008-05-30 | 2008-09-26 | 2017-09-29 | 2018-01-26
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-556A | UPGRADE WATER MAINS AT NY BOTANICAL GARDENS (BX) | 3 | FINAL DESIGN | 2008-09-27 | 2009-03-25 | 2018-01-27 | 2018-07-25
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-556A | UPGRADE WATER MAINS AT NY BOTANICAL GARDENS (BX) | 4 | BID AWARD AND REGISTER CONTRCT | 2009-03-26 | 2009-06-23 | 2018-07-25 | 2018-10-22
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-556A | UPGRADE WATER MAINS AT NY BOTANICAL GARDENS (BX) | 5 | CONSTRUCTION TO 25% | 2009-06-24 | 2009-10-21 | 2018-10-23 | 2019-02-19
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-556A | UPGRADE WATER MAINS AT NY BOTANICAL GARDENS (BX) | 6 | CONSTRUCTION TO 50% | 2009-10-22 | 2010-02-18 | 2019-02-20 | 2019-06-19
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-556A | UPGRADE WATER MAINS AT NY BOTANICAL GARDENS (BX) | 7 | CONSTRUCTION TO 75% | 2010-02-19 | 2010-06-18 | 2019-06-20 | 2019-10-17
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-556A | UPGRADE WATER MAINS AT NY BOTANICAL GARDENS (BX) | 8 | ORIGINAL EQUIP & FURNISHING | 2010-06-19 | 2010-09-16 | 2019-10-18 | 2019-10-17
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-556A | UPGRADE WATER MAINS AT NY BOTANICAL GARDENS (BX) | 9 | SUBSTANTIAL COMPLETION | 2010-09-17 | 2010-11-15 | 2019-10-18 | 2019-12-16
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-556A | UPGRADE WATER MAINS AT NY BOTANICAL GARDENS (BX) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2010-11-16 | 2010-12-15 | 2019-12-17 | 2030-09-10
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-560 | RECON WM IN WEST FARMS SQUARE (HWXP2007) | 1 | DEVELOP SCOPE | 2017-03-01 | 2017-05-29 | 2017-03-01 | 2017-05-29
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-560 | RECON WM IN WEST FARMS SQUARE (HWXP2007) | 2 | PRELIMINARY DESIGN | 2017-05-30 | 2017-09-26 | 2017-05-30 | 2017-09-26
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-560 | RECON WM IN WEST FARMS SQUARE (HWXP2007) | 3 | FINAL DESIGN | 2017-09-27 | 2018-03-25 | 2017-09-27 | 2018-03-25
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-560 | RECON WM IN WEST FARMS SQUARE (HWXP2007) | 4 | BID AWARD AND REGISTER CONTRCT | 2018-03-26 | 2018-06-23 | 2018-03-26 | 2018-06-23
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-560 | RECON WM IN WEST FARMS SQUARE (HWXP2007) | 5 | CONSTRUCTION TO 25% | 2018-06-24 | 2018-10-21 | 2018-06-24 | 2018-10-21
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-560 | RECON WM IN WEST FARMS SQUARE (HWXP2007) | 6 | CONSTRUCTION TO 50% | 2018-10-22 | 2019-02-18 | 2018-10-22 | 2019-02-18
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-560 | RECON WM IN WEST FARMS SQUARE (HWXP2007) | 7 | CONSTRUCTION TO 75% | 2019-02-19 | 2019-06-18 | 2019-02-19 | 2019-06-18
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-560 | RECON WM IN WEST FARMS SQUARE (HWXP2007) | 8 | ORIGINAL EQUIP & FURNISHING | 2019-06-19 | 2019-09-16 | 2019-06-19 | 2019-09-16
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-560 | RECON WM IN WEST FARMS SQUARE (HWXP2007) | 9 | SUBSTANTIAL COMPLETION | 2019-09-17 | 2019-11-15 | 2019-09-17 | 2019-11-15
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-560 | RECON WM IN WEST FARMS SQUARE (HWXP2007) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-11-16 | 2019-12-15 | 2019-11-16 | 2022-06-30
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-562 | New 46" Trunk Water Main in E.233rd St. Bronx | 1 | DEVELOP SCOPE | 2012-05-17 | 2012-08-14 | 2015-05-17 | 2015-08-14
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-562 | New 46" Trunk Water Main in E.233rd St. Bronx | 2 | PRELIMINARY DESIGN | 2012-08-15 | 2012-12-12 | 2015-08-15 | 2015-12-12
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-562 | New 46" Trunk Water Main in E.233rd St. Bronx | 3 | FINAL DESIGN | 2012-12-13 | 2013-06-10 | 2015-12-13 | 2016-06-09
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-562 | New 46" Trunk Water Main in E.233rd St. Bronx | 4 | BID AWARD AND REGISTER CONTRCT | 2013-06-11 | 2013-09-08 | 2016-06-10 | 2016-09-07
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-562 | New 46" Trunk Water Main in E.233rd St. Bronx | 5 | CONSTRUCTION TO 25% | 2013-09-09 | 2014-01-06 | 2016-09-08 | 2017-01-05
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-562 | New 46" Trunk Water Main in E.233rd St. Bronx | 6 | CONSTRUCTION TO 50% | 2014-01-07 | 2014-05-06 | 2017-01-06 | 2017-05-05
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-562 | New 46" Trunk Water Main in E.233rd St. Bronx | 7 | CONSTRUCTION TO 75% | 2014-05-07 | 2014-09-03 | 2017-05-06 | 2017-09-02
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-562 | New 46" Trunk Water Main in E.233rd St. Bronx | 8 | ORIGINAL EQUIP & FURNISHING | 2014-09-04 | 2014-12-02 | 2017-09-03 | 2017-12-01
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-562 | New 46" Trunk Water Main in E.233rd St. Bronx | 9 | SUBSTANTIAL COMPLETION | 2014-12-03 | 2015-01-31 | 2017-12-02 | 2018-01-30
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-562 | New 46" Trunk Water Main in E.233rd St. Bronx | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-02-01 | 2015-03-02 | 2018-01-31 | 2025-03-11
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-564 | NEW 20" SUB-AQUEOUS WATER MAIN TO CITY ISLAND | 1 | DEVELOP SCOPE | 2011-02-27 | 2011-05-27 | 2011-02-27 | 2011-05-27
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-564 | NEW 20" SUB-AQUEOUS WATER MAIN TO CITY ISLAND | 2 | PRELIMINARY DESIGN | 2011-05-28 | 2011-09-24 | 2011-05-28 | 2011-09-24
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-564 | NEW 20" SUB-AQUEOUS WATER MAIN TO CITY ISLAND | 3 | FINAL DESIGN | 2011-09-25 | 2012-03-22 | 2011-09-25 | 2016-03-03
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-564 | NEW 20" SUB-AQUEOUS WATER MAIN TO CITY ISLAND | 4 | BID AWARD AND REGISTER CONTRCT | 2012-03-23 | 2012-06-20 | 2016-03-04 | 2016-06-01
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-564 | NEW 20" SUB-AQUEOUS WATER MAIN TO CITY ISLAND | 5 | CONSTRUCTION TO 25% | 2012-06-21 | 2012-10-18 | 2016-06-02 | 2017-02-06
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-564 | NEW 20" SUB-AQUEOUS WATER MAIN TO CITY ISLAND | 6 | CONSTRUCTION TO 50% | 2012-10-19 | 2013-02-15 | 2017-02-07 | 2017-10-14
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-564 | NEW 20" SUB-AQUEOUS WATER MAIN TO CITY ISLAND | 7 | CONSTRUCTION TO 75% | 2013-02-16 | 2013-06-15 | 2017-10-15 | 2018-06-21
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-564 | NEW 20" SUB-AQUEOUS WATER MAIN TO CITY ISLAND | 8 | ORIGINAL EQUIP & FURNISHING | 2013-06-16 | 2013-09-13 | 2018-06-22 | 2018-09-19
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-564 | NEW 20" SUB-AQUEOUS WATER MAIN TO CITY ISLAND | 9 | SUBSTANTIAL COMPLETION | 2013-09-14 | 2013-11-12 | 2018-09-20 | 2018-11-18
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-564 | NEW 20" SUB-AQUEOUS WATER MAIN TO CITY ISLAND | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-11-13 | 2013-12-12 | 2018-11-19 | 2022-06-30
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-568 | New 20" sub-aqueous water main extension to Randall's Island | 1 | DEVELOP SCOPE | 2011-07-01 | 2011-09-28 | 2011-07-01 | 2011-09-28
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-568 | New 20" sub-aqueous water main extension to Randall's Island | 2 | PRELIMINARY DESIGN | 2011-09-29 | 2012-01-26 | 2011-09-29 | 2012-01-26
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-568 | New 20" sub-aqueous water main extension to Randall's Island | 3 | FINAL DESIGN | 2012-01-27 | 2012-07-24 | 2012-01-27 | 2014-10-03
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-568 | New 20" sub-aqueous water main extension to Randall's Island | 4 | BID AWARD AND REGISTER CONTRCT | 2012-07-25 | 2012-10-22 | 2014-10-04 | 2015-01-01
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-568 | New 20" sub-aqueous water main extension to Randall's Island | 5 | CONSTRUCTION TO 25% | 2012-10-23 | 2013-02-19 | 2015-01-01 | 2015-09-07
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-568 | New 20" sub-aqueous water main extension to Randall's Island | 6 | CONSTRUCTION TO 50% | 2013-02-20 | 2013-06-19 | 2015-09-08 | 2016-05-14
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-568 | New 20" sub-aqueous water main extension to Randall's Island | 7 | CONSTRUCTION TO 75% | 2013-06-20 | 2013-10-17 | 2016-05-15 | 2017-01-19
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-568 | New 20" sub-aqueous water main extension to Randall's Island | 8 | ORIGINAL EQUIP & FURNISHING | 2013-10-18 | 2014-01-15 | 2017-01-20 | 2017-04-19
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-568 | New 20" sub-aqueous water main extension to Randall's Island | 9 | SUBSTANTIAL COMPLETION | 2014-01-16 | 2014-03-16 | 2017-04-20 | 2017-06-18
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-568 | New 20" sub-aqueous water main extension to Randall's Island | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-03-17 | 2014-04-15 | 2017-06-19 | 2022-06-23
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-569 | Replacement of Trunk WM in Bainbridge Ave | 1 | DEVELOP SCOPE | 2014-03-01 | 2014-05-29 | 2014-03-01 | 2014-05-29
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-569 | Replacement of Trunk WM in Bainbridge Ave | 2 | PRELIMINARY DESIGN | 2014-05-30 | 2014-09-26 | 2014-05-30 | 2014-09-26
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-569 | Replacement of Trunk WM in Bainbridge Ave | 3 | FINAL DESIGN | 2014-09-27 | 2015-03-25 | 2014-09-27 | 2015-03-25
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-569 | Replacement of Trunk WM in Bainbridge Ave | 4 | BID AWARD AND REGISTER CONTRCT | 2015-03-26 | 2015-06-23 | 2015-03-26 | 2015-06-23
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-569 | Replacement of Trunk WM in Bainbridge Ave | 5 | CONSTRUCTION TO 25% | 2015-06-24 | 2015-10-21 | 2015-06-24 | 2015-10-21
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-569 | Replacement of Trunk WM in Bainbridge Ave | 6 | CONSTRUCTION TO 50% | 2015-10-22 | 2016-02-18 | 2015-10-22 | 2016-02-18
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-569 | Replacement of Trunk WM in Bainbridge Ave | 7 | CONSTRUCTION TO 75% | 2016-02-19 | 2016-06-17 | 2016-02-19 | 2016-06-17
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-569 | Replacement of Trunk WM in Bainbridge Ave | 8 | ORIGINAL EQUIP & FURNISHING | 2016-06-18 | 2016-09-15 | 2016-06-18 | 2016-09-15
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-569 | Replacement of Trunk WM in Bainbridge Ave | 9 | SUBSTANTIAL COMPLETION | 2016-09-16 | 2016-11-14 | 2016-09-16 | 2016-11-14
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-569 | Replacement of Trunk WM in Bainbridge Ave | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-11-15 | 2016-12-14 | 2016-11-15 | 2023-06-04
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-570 | Trunk & Dist WM & Comb. Sewer Replacement, bx | 1 | DEVELOP SCOPE | 2020-03-01 | 2020-05-29 | 2020-03-01 | 2020-05-29
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-570 | Trunk & Dist WM & Comb. Sewer Replacement, bx | 2 | PRELIMINARY DESIGN | 2020-05-30 | 2020-09-26 | 2020-05-30 | 2020-09-26
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-570 | Trunk & Dist WM & Comb. Sewer Replacement, bx | 3 | FINAL DESIGN | 2020-09-27 | 2021-03-25 | 2020-09-27 | 2021-03-25
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-570 | Trunk & Dist WM & Comb. Sewer Replacement, bx | 4 | BID AWARD AND REGISTER CONTRCT | 2021-03-26 | 2021-06-23 | 2021-03-26 | 2021-06-23
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-570 | Trunk & Dist WM & Comb. Sewer Replacement, bx | 5 | CONSTRUCTION TO 25% | 2021-06-24 | 2021-10-21 | 2021-06-24 | 2021-10-21
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-570 | Trunk & Dist WM & Comb. Sewer Replacement, bx | 6 | CONSTRUCTION TO 50% | 2021-10-22 | 2022-02-18 | 2021-10-22 | 2022-02-18
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-570 | Trunk & Dist WM & Comb. Sewer Replacement, bx | 7 | CONSTRUCTION TO 75% | 2022-02-19 | 2022-06-18 | 2022-02-19 | 2022-06-18
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-570 | Trunk & Dist WM & Comb. Sewer Replacement, bx | 8 | ORIGINAL EQUIP & FURNISHING | 2022-06-19 | 2022-09-16 | 2022-06-19 | 2022-09-16
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-570 | Trunk & Dist WM & Comb. Sewer Replacement, bx | 9 | SUBSTANTIAL COMPLETION | 2022-09-17 | 2022-11-15 | 2022-09-17 | 2022-11-15
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-570 | Trunk & Dist WM & Comb. Sewer Replacement, bx | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-11-16 | 2022-12-15 | 2022-11-16 | 2022-12-15
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-578 | Replcmt of Dist WM In Mundy Lane btwn Cranford & Nereid Ave | 1 | DEVELOP SCOPE | 2019-08-23 | 2019-11-20 | 2019-08-23 | 2019-11-20
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-578 | Replcmt of Dist WM In Mundy Lane btwn Cranford & Nereid Ave | 2 | PRELIMINARY DESIGN | 2019-11-21 | 2020-03-19 | 2019-11-21 | 2020-03-19
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-578 | Replcmt of Dist WM In Mundy Lane btwn Cranford & Nereid Ave | 3 | FINAL DESIGN | 2020-03-20 | 2020-09-15 | 2020-03-20 | 2020-09-15
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-578 | Replcmt of Dist WM In Mundy Lane btwn Cranford & Nereid Ave | 4 | BID AWARD AND REGISTER CONTRCT | 2020-09-16 | 2020-12-14 | 2020-09-16 | 2020-12-14
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-578 | Replcmt of Dist WM In Mundy Lane btwn Cranford & Nereid Ave | 5 | CONSTRUCTION TO 25% | 2020-12-15 | 2021-04-13 | 2020-12-15 | 2021-04-13
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-578 | Replcmt of Dist WM In Mundy Lane btwn Cranford & Nereid Ave | 6 | CONSTRUCTION TO 50% | 2021-04-14 | 2021-08-11 | 2021-04-14 | 2021-08-11
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-578 | Replcmt of Dist WM In Mundy Lane btwn Cranford & Nereid Ave | 7 | CONSTRUCTION TO 75% | 2021-08-12 | 2021-12-09 | 2021-08-12 | 2021-12-09
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-578 | Replcmt of Dist WM In Mundy Lane btwn Cranford & Nereid Ave | 8 | ORIGINAL EQUIP & FURNISHING | 2021-12-10 | 2022-03-09 | 2021-12-10 | 2022-03-09
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-578 | Replcmt of Dist WM In Mundy Lane btwn Cranford & Nereid Ave | 9 | SUBSTANTIAL COMPLETION | 2022-03-10 | 2022-05-08 | 2022-03-10 | 2022-05-08
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-578 | Replcmt of Dist WM In Mundy Lane btwn Cranford & Nereid Ave | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-05-09 | 2022-06-07 | 2022-05-09 | 2022-06-07
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HEDA-002 | Accelerated Distribution WM replcmnt & sewer rehab: BX | 1 | DEVELOP SCOPE | 2016-03-01 | 2016-05-29 | 2016-03-01 | 2016-05-29
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HEDA-002 | Accelerated Distribution WM replcmnt & sewer rehab: BX | 2 | PRELIMINARY DESIGN | 2016-05-30 | 2016-09-26 | 2016-05-30 | 2016-09-26
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HEDA-002 | Accelerated Distribution WM replcmnt & sewer rehab: BX | 3 | FINAL DESIGN | 2016-09-27 | 2017-03-25 | 2016-09-27 | 2017-03-25
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HEDA-002 | Accelerated Distribution WM replcmnt & sewer rehab: BX | 4 | BID AWARD AND REGISTER CONTRCT | 2017-03-26 | 2017-06-23 | 2017-03-26 | 2017-06-23
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HEDA-002 | Accelerated Distribution WM replcmnt & sewer rehab: BX | 5 | CONSTRUCTION TO 25% | 2017-06-24 | 2017-10-21 | 2017-06-24 | 2017-10-21
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HEDA-002 | Accelerated Distribution WM replcmnt & sewer rehab: BX | 6 | CONSTRUCTION TO 50% | 2017-10-22 | 2018-02-18 | 2017-10-22 | 2018-02-18
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HEDA-002 | Accelerated Distribution WM replcmnt & sewer rehab: BX | 7 | CONSTRUCTION TO 75% | 2018-02-19 | 2018-06-18 | 2018-02-19 | 2018-06-18
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HEDA-002 | Accelerated Distribution WM replcmnt & sewer rehab: BX | 8 | ORIGINAL EQUIP & FURNISHING | 2018-06-19 | 2018-09-16 | 2018-06-19 | 2018-09-16
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HEDA-002 | Accelerated Distribution WM replcmnt & sewer rehab: BX | 9 | SUBSTANTIAL COMPLETION | 2018-09-17 | 2018-11-15 | 2018-09-17 | 2018-11-15
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HEDA-002 | Accelerated Distribution WM replcmnt & sewer rehab: BX | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-11-16 | 2018-12-15 | 2018-11-16 | 2021-06-28
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HEDA-003 | Accelerated Distribution WM replcmnt & sewer rehab: BX | 1 | DEVELOP SCOPE | 2016-03-01 | 2016-05-29 | 2016-03-01 | 2016-05-29
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HEDA-003 | Accelerated Distribution WM replcmnt & sewer rehab: BX | 2 | PRELIMINARY DESIGN | 2016-05-30 | 2016-09-26 | 2016-05-30 | 2016-09-26
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HEDA-003 | Accelerated Distribution WM replcmnt & sewer rehab: BX | 3 | FINAL DESIGN | 2016-09-27 | 2017-03-25 | 2016-09-27 | 2017-03-25
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HEDA-003 | Accelerated Distribution WM replcmnt & sewer rehab: BX | 4 | BID AWARD AND REGISTER CONTRCT | 2017-03-26 | 2017-06-23 | 2017-03-26 | 2017-06-23
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HEDA-003 | Accelerated Distribution WM replcmnt & sewer rehab: BX | 5 | CONSTRUCTION TO 25% | 2017-06-24 | 2017-10-21 | 2017-06-24 | 2017-10-21
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HEDA-003 | Accelerated Distribution WM replcmnt & sewer rehab: BX | 6 | CONSTRUCTION TO 50% | 2017-10-22 | 2018-02-18 | 2017-10-22 | 2018-02-18
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HEDA-003 | Accelerated Distribution WM replcmnt & sewer rehab: BX | 7 | CONSTRUCTION TO 75% | 2018-02-19 | 2018-06-18 | 2018-02-19 | 2018-06-18
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HEDA-003 | Accelerated Distribution WM replcmnt & sewer rehab: BX | 8 | ORIGINAL EQUIP & FURNISHING | 2018-06-19 | 2018-09-16 | 2018-06-19 | 2018-09-16
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HEDA-003 | Accelerated Distribution WM replcmnt & sewer rehab: BX | 9 | SUBSTANTIAL COMPLETION | 2018-09-17 | 2018-11-15 | 2018-09-17 | 2018-11-15
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HEDA-003 | Accelerated Distribution WM replcmnt & sewer rehab: BX | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-11-16 | 2018-12-15 | 2018-11-16 | 2023-03-01
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112CWFR | COMMONWEALTH AVENUE FIRE SAFETY SYSTEM | 1 | PROJECT START | 2016-03-30 | 2016-03-31 | 2016-03-30 | 2016-03-31
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112CWFR | COMMONWEALTH AVENUE FIRE SAFETY SYSTEM | 2 | DESIGN START | 2016-04-01 | 2016-07-01 | 2016-04-01 | 2016-07-01
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112CWFR | COMMONWEALTH AVENUE FIRE SAFETY SYSTEM | 3 | DESIGN COMPLETION | 2016-07-02 | 2017-06-30 | 2016-07-02 | 2017-06-30
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112CWFR | COMMONWEALTH AVENUE FIRE SAFETY SYSTEM | 4 | CONSTRUCTION START | 2017-07-01 | 2017-10-31 | 2017-07-01 | 2017-10-31
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112CWFR | COMMONWEALTH AVENUE FIRE SAFETY SYSTEM | 5 | CONSTRUCTION COMPLETION | 2017-11-01 | 2023-06-30 | 2017-11-01 | 2023-06-30
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112WLFA | WILLOW AVE FIRE SAFETY | 1 | PROJECT START | 2016-07-26 | 2016-07-26 | 2016-07-26 | 2016-07-26
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112WLFA | WILLOW AVE FIRE SAFETY | 2 | DESIGN START | 2016-07-27 | 2016-10-19 | 2016-10-19 | 2016-10-19
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112WLFA | WILLOW AVE FIRE SAFETY | 3 | DESIGN COMPLETION | 2016-10-20 | 2017-06-13 | 2017-06-13 | 2017-06-13
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112WLFA | WILLOW AVE FIRE SAFETY | 4 | CONSTRUCTION START | 2017-06-14 | 2019-02-26 | 2018-06-13 | 2018-06-13
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112WLFA | WILLOW AVE FIRE SAFETY | 5 | CONSTRUCTION COMPLETION | 2019-02-27 | 2019-05-26 | 2018-06-14 | 2021-08-30
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115FRFA | FREEMAN FAMILY RESIDENCE - FIRE ALARM SYSTEM UPGRADE | 1 | PROJECT START | 2016-03-30 | 2016-03-31 | 2016-03-30 | 2016-03-31
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115FRFA | FREEMAN FAMILY RESIDENCE - FIRE ALARM SYSTEM UPGRADE | 2 | DESIGN START | 2016-04-01 | 2016-07-01 | 2016-04-01 | 2016-07-01
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115FRFA | FREEMAN FAMILY RESIDENCE - FIRE ALARM SYSTEM UPGRADE | 3 | DESIGN COMPLETION | 2016-07-02 | 2017-06-30 | 2016-07-02 | 2017-06-30
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115FRFA | FREEMAN FAMILY RESIDENCE - FIRE ALARM SYSTEM UPGRADE | 4 | CONSTRUCTION START | 2017-07-01 | 2017-10-31 | 2017-07-01 | 2017-10-31
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115FRFA | FREEMAN FAMILY RESIDENCE - FIRE ALARM SYSTEM UPGRADE | 5 | CONSTRUCTION COMPLETION | 2017-11-01 | 2023-06-30 | 2017-11-01 | 2023-06-30
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115JCFS | JACKSON FAMILY FIRE SAFETY | 1 | PROJECT START | 2016-07-26 | 2016-07-26 | 2016-07-26 | 2016-07-26
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115JCFS | JACKSON FAMILY FIRE SAFETY | 2 | DESIGN START | 2016-07-27 | 2016-10-19 | 2016-07-27 | 2016-10-19
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115JCFS | JACKSON FAMILY FIRE SAFETY | 3 | DESIGN COMPLETION | 2016-10-20 | 2017-06-14 | 2016-10-20 | 2017-06-14
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115JCFS | JACKSON FAMILY FIRE SAFETY | 4 | CONSTRUCTION START | 2017-06-15 | 2018-08-10 | 2017-06-15 | 2018-08-10
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115JCFS | JACKSON FAMILY FIRE SAFETY | 5 | CONSTRUCTION COMPLETION | 2018-08-11 | 2019-05-24 | 2018-08-11 | 2022-08-24
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115SNEC | SENECA HOUSES - ELECTRICAL AND KITCHEN UPGRADE | 1 | PROJECT START | 2018-06-15 | 2018-06-15 | 2018-06-15 | 2019-06-15
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115SNEC | SENECA HOUSES - ELECTRICAL AND KITCHEN UPGRADE | 2 | DESIGN START | 2018-06-16 | 2018-06-16 | 2019-06-16 | 2020-06-16
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115SNEC | SENECA HOUSES - ELECTRICAL AND KITCHEN UPGRADE | 3 | DESIGN COMPLETION | 2018-06-17 | 2018-06-17 | 2020-06-17 | 2021-06-17
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115SNEC | SENECA HOUSES - ELECTRICAL AND KITCHEN UPGRADE | 4 | CONSTRUCTION START | 2018-06-18 | 2018-06-18 | 2021-06-18 | 2022-06-18
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115SNEC | SENECA HOUSES - ELECTRICAL AND KITCHEN UPGRADE | 5 | CONSTRUCTION COMPLETION | 2018-06-19 | 2020-06-19 | 2022-06-19 | 2024-06-19
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115UNFA | UNIVERSITY FAMILY RESIDENCE - FIRE ALARM SYSTEM UPGRADE | 1 | PROJECT START | 2016-03-30 | 2016-03-31 | 2016-03-30 | 2016-03-31
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115UNFA | UNIVERSITY FAMILY RESIDENCE - FIRE ALARM SYSTEM UPGRADE | 2 | DESIGN START | 2016-04-01 | 2016-07-01 | 2016-04-01 | 2016-07-01
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115UNFA | UNIVERSITY FAMILY RESIDENCE - FIRE ALARM SYSTEM UPGRADE | 3 | DESIGN COMPLETION | 2016-07-02 | 2017-06-30 | 2016-07-02 | 2018-06-06
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115UNFA | UNIVERSITY FAMILY RESIDENCE - FIRE ALARM SYSTEM UPGRADE | 4 | CONSTRUCTION START | 2017-07-01 | 2017-10-31 | 2018-06-07 | 2020-04-02
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115UNFA | UNIVERSITY FAMILY RESIDENCE - FIRE ALARM SYSTEM UPGRADE | 5 | CONSTRUCTION COMPLETION | 2017-11-01 | 2023-06-30 | 2020-04-03 | 2025-11-30
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82BRONX | Bronx Animal Care Center and Veterinary Clinic | 1 | DESIGN | 2016-07-01 | 2016-12-27 | 2019-07-01 | 2019-07-30
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82BRONX | Bronx Animal Care Center and Veterinary Clinic | 2 | DESIGN START | 2016-12-28 | 2017-03-27 | 2019-07-31 | 2019-10-28
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82BRONX | Bronx Animal Care Center and Veterinary Clinic | 3 | DESIGN COMPLETION | 2017-03-28 | 2018-03-27 | 2019-10-29 | 2020-10-27
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82BRONX | Bronx Animal Care Center and Veterinary Clinic | 4 | CONSTRUCTION START | 2018-03-28 | 2018-09-23 | 2020-10-28 | 2021-01-25
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82BRONX | Bronx Animal Care Center and Veterinary Clinic | 5 | CONSTRUCTION COMPLETION | 2018-03-28 | 2018-09-23 | 2021-01-26 | 2024-06-25
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPBX | SAFE ROUTES TO SCHOOLS- BRONX | 1 | DEVELOP SCOPE | 2019-03-01 | 2019-05-29 | 2019-03-01 | 2019-05-29
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPBX | SAFE ROUTES TO SCHOOLS- BRONX | 2 | PRELIMINARY DESIGN | 2019-05-30 | 2019-09-26 | 2019-05-30 | 2019-09-26
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPBX | SAFE ROUTES TO SCHOOLS- BRONX | 3 | FINAL DESIGN | 2019-09-27 | 2020-03-24 | 2019-09-27 | 2020-03-24
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPBX | SAFE ROUTES TO SCHOOLS- BRONX | 4 | BID AWARD AND REGISTER CONTRCT | 2020-03-25 | 2020-06-22 | 2020-03-25 | 2020-06-22
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPBX | SAFE ROUTES TO SCHOOLS- BRONX | 5 | CONSTRUCTION TO 25% | 2020-06-23 | 2020-10-20 | 2020-06-23 | 2020-10-20
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPBX | SAFE ROUTES TO SCHOOLS- BRONX | 6 | CONSTRUCTION TO 50% | 2020-10-21 | 2021-02-17 | 2020-10-21 | 2021-02-17
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPBX | SAFE ROUTES TO SCHOOLS- BRONX | 7 | CONSTRUCTION TO 75% | 2021-02-18 | 2021-06-17 | 2021-02-18 | 2021-06-17
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPBX | SAFE ROUTES TO SCHOOLS- BRONX | 8 | ORIGINAL EQUIP & FURNISHING | 2021-06-18 | 2021-09-15 | 2021-06-18 | 2021-09-15
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPBX | SAFE ROUTES TO SCHOOLS- BRONX | 9 | SUBSTANTIAL COMPLETION | 2021-09-16 | 2021-11-14 | 2021-09-16 | 2021-11-14
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPBX | SAFE ROUTES TO SCHOOLS- BRONX | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-11-15 | 2021-12-14 | 2021-11-15 | 2023-06-30
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD105-01 | METROPOLITAN AVE & UNIONPORT ROAD IN PARKCHESTER -CENTER IS. | 1 | DEVELOP SCOPE | 2008-05-22 | 2008-08-19 | 2009-05-10 | 2009-08-07
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD105-01 | METROPOLITAN AVE & UNIONPORT ROAD IN PARKCHESTER -CENTER IS. | 2 | PRELIMINARY DESIGN | 2008-08-20 | 2008-12-17 | 2009-08-15 | 2009-12-12
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD105-01 | METROPOLITAN AVE & UNIONPORT ROAD IN PARKCHESTER -CENTER IS. | 3 | FINAL DESIGN | 2008-12-18 | 2009-06-15 | 2009-12-13 | 2010-06-10
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD105-01 | METROPOLITAN AVE & UNIONPORT ROAD IN PARKCHESTER -CENTER IS. | 4 | BID AWARD AND REGISTER CONTRCT | 2009-06-16 | 2009-09-13 | 2010-06-11 | 2010-09-08
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD105-01 | METROPOLITAN AVE & UNIONPORT ROAD IN PARKCHESTER -CENTER IS. | 5 | CONSTRUCTION TO 25% | 2009-09-14 | 2010-01-11 | 2010-09-09 | 2011-07-05
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD105-01 | METROPOLITAN AVE & UNIONPORT ROAD IN PARKCHESTER -CENTER IS. | 6 | CONSTRUCTION TO 50% | 2010-01-12 | 2010-05-11 | 2011-07-06 | 2012-06-19
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD105-01 | METROPOLITAN AVE & UNIONPORT ROAD IN PARKCHESTER -CENTER IS. | 7 | CONSTRUCTION TO 75% | 2010-05-12 | 2010-09-08 | 2012-06-20 | 2015-12-02
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD105-01 | METROPOLITAN AVE & UNIONPORT ROAD IN PARKCHESTER -CENTER IS. | 8 | ORIGINAL EQUIP & FURNISHING | 2010-09-09 | 2010-12-07 | 2015-12-01 | 2016-02-28
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD105-01 | METROPOLITAN AVE & UNIONPORT ROAD IN PARKCHESTER -CENTER IS. | 9 | SUBSTANTIAL COMPLETION | 2010-12-08 | 2011-02-05 | 2016-02-29 | 2016-04-28
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD105-01 | METROPOLITAN AVE & UNIONPORT ROAD IN PARKCHESTER -CENTER IS. | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2011-02-06 | 2011-03-07 | 2016-04-29 | 2026-06-30
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD105-03 | LIBRARY LANE PROJECT | 1 | DEVELOP SCOPE | 2005-08-30 | 2005-12-27 | 2005-06-30 | 2005-09-27
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD105-03 | LIBRARY LANE PROJECT | 2 | DESIGN START | 2005-12-28 | 2007-06-20 | 2005-09-28 | 2006-01-25
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD105-03 | LIBRARY LANE PROJECT | 3 | CONSTRUCTION START | 2007-06-21 | 2009-06-09 | 2006-01-26 | 2016-03-14
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD105-03 | LIBRARY LANE PROJECT | 4 | BID AWARD AND REGISTER CONTRCT | 2007-06-21 | 2009-06-09 | 2016-03-15 | 2016-06-12
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD105-03 | LIBRARY LANE PROJECT | 5 | CONSTRUCTION TO 25% | 2007-06-21 | 2009-06-09 | 2016-06-13 | 2016-10-10
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD105-03 | LIBRARY LANE PROJECT | 6 | CONSTRUCTION TO 50% | 2007-06-21 | 2009-06-09 | 2016-10-11 | 2017-02-07
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD105-03 | LIBRARY LANE PROJECT | 7 | CONSTRUCTION TO 75% | 2007-06-21 | 2009-06-09 | 2017-02-08 | 2017-06-07
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD105-03 | LIBRARY LANE PROJECT | 8 | ORIGINAL EQUIP & FURNISHING | 2007-06-21 | 2009-06-09 | 2017-06-08 | 2017-09-05
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD105-03 | LIBRARY LANE PROJECT | 9 | SUBSTANTIAL COMPLETION | 2007-06-21 | 2009-06-09 | 2017-09-06 | 2017-11-04
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD105-03 | LIBRARY LANE PROJECT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2007-06-21 | 2009-06-09 | 2017-11-05 | 2023-10-27
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP16XTA | Citywide Complex Pedestrian Ramps (TA Locations) - Bronx | 2 | PRELIMINARY DESIGN | 2016-05-30 | 2016-09-26 | 2016-05-30 | 2016-09-26
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP16XTA | Citywide Complex Pedestrian Ramps (TA Locations) - Bronx | 3 | FINAL DESIGN | 2016-09-27 | 2017-03-25 | 2016-09-27 | 2017-03-25
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP16XTA | Citywide Complex Pedestrian Ramps (TA Locations) - Bronx | 4 | BID AWARD AND REGISTER CONTRCT | 2017-03-26 | 2017-06-23 | 2017-03-26 | 2017-06-23
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP16XTA | Citywide Complex Pedestrian Ramps (TA Locations) - Bronx | 5 | CONSTRUCTION TO 25% | 2017-06-24 | 2017-10-21 | 2017-06-24 | 2017-10-21
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP16XTA | Citywide Complex Pedestrian Ramps (TA Locations) - Bronx | 6 | CONSTRUCTION TO 50% | 2017-10-22 | 2018-02-18 | 2017-10-22 | 2018-02-18
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP16XTA | Citywide Complex Pedestrian Ramps (TA Locations) - Bronx | 7 | CONSTRUCTION TO 75% | 2018-02-19 | 2018-06-18 | 2018-02-19 | 2018-06-18
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP16XTA | Citywide Complex Pedestrian Ramps (TA Locations) - Bronx | 8 | ORIGINAL EQUIP & FURNISHING | 2018-06-19 | 2018-09-16 | 2018-06-19 | 2018-09-16
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP16XTA | Citywide Complex Pedestrian Ramps (TA Locations) - Bronx | 9 | SUBSTANTIAL COMPLETION | 2018-09-17 | 2018-11-15 | 2018-09-17 | 2018-11-15
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP16XTA | Citywide Complex Pedestrian Ramps (TA Locations) - Bronx | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-11-16 | 2018-12-15 | 2018-11-16 | 2018-12-15
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ004X | Morrison Avenue Plaza (HED-572) | 1 | DEVELOP SCOPE | 2016-06-01 | 2016-08-29 | 2016-06-01 | 2016-08-29
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ004X | Morrison Avenue Plaza (HED-572) | 2 | PRELIMINARY DESIGN | 2016-08-30 | 2016-12-27 | 2016-08-30 | 2016-12-27
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ004X | Morrison Avenue Plaza (HED-572) | 3 | FINAL DESIGN | 2016-12-28 | 2017-06-25 | 2016-12-28 | 2017-06-25
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ004X | Morrison Avenue Plaza (HED-572) | 4 | BID AWARD AND REGISTER CONTRCT | 2017-06-26 | 2017-09-23 | 2017-06-26 | 2017-09-23
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ004X | Morrison Avenue Plaza (HED-572) | 5 | CONSTRUCTION TO 25% | 2017-09-24 | 2018-01-21 | 2017-09-24 | 2018-01-21
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ004X | Morrison Avenue Plaza (HED-572) | 6 | CONSTRUCTION TO 50% | 2018-01-22 | 2018-05-21 | 2018-01-22 | 2018-05-21
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ004X | Morrison Avenue Plaza (HED-572) | 7 | CONSTRUCTION TO 75% | 2018-05-22 | 2018-09-18 | 2018-05-22 | 2018-09-18
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ004X | Morrison Avenue Plaza (HED-572) | 8 | ORIGINAL EQUIP & FURNISHING | 2018-09-19 | 2018-12-17 | 2018-09-19 | 2018-12-17
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ004X | Morrison Avenue Plaza (HED-572) | 9 | SUBSTANTIAL COMPLETION | 2018-12-18 | 2019-02-15 | 2018-12-18 | 2019-02-15
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ004X | Morrison Avenue Plaza (HED-572) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-02-16 | 2019-03-17 | 2019-02-16 | 2023-12-27
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19X | Pedestrian Ramp Rehabilitation - The Bronx | 1 | DEVELOP SCOPE | 2017-06-30 | 2017-09-27 | 2017-06-30 | 2017-09-27
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19X | Pedestrian Ramp Rehabilitation - The Bronx | 2 | PRELIMINARY DESIGN | 2017-09-28 | 2018-01-25 | 2017-09-28 | 2018-01-25
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19X | Pedestrian Ramp Rehabilitation - The Bronx | 3 | FINAL DESIGN | 2018-01-26 | 2018-07-24 | 2018-01-26 | 2018-07-24
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19X | Pedestrian Ramp Rehabilitation - The Bronx | 4 | BID AWARD AND REGISTER CONTRCT | 2018-07-25 | 2018-10-22 | 2018-07-25 | 2018-10-22
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19X | Pedestrian Ramp Rehabilitation - The Bronx | 5 | CONSTRUCTION TO 25% | 2018-10-23 | 2019-02-19 | 2018-10-23 | 2019-02-19
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19X | Pedestrian Ramp Rehabilitation - The Bronx | 6 | CONSTRUCTION TO 50% | 2019-02-20 | 2019-06-19 | 2019-02-20 | 2019-06-19
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19X | Pedestrian Ramp Rehabilitation - The Bronx | 7 | CONSTRUCTION TO 75% | 2019-06-20 | 2019-10-17 | 2019-06-20 | 2019-10-17
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19X | Pedestrian Ramp Rehabilitation - The Bronx | 8 | ORIGINAL EQUIP & FURNISHING | 2019-10-18 | 2020-01-15 | 2019-10-18 | 2020-01-15
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19X | Pedestrian Ramp Rehabilitation - The Bronx | 9 | SUBSTANTIAL COMPLETION | 2020-01-16 | 2020-03-15 | 2020-01-16 | 2020-03-15
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19X | Pedestrian Ramp Rehabilitation - The Bronx | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-03-16 | 2020-04-14 | 2020-03-16 | 2024-03-22
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS20000X | PRIOR NOTICE SIDEWALKS - BRONX | 1 | DEVELOP SCOPE | 2017-03-01 | 2017-05-29 | 2017-03-01 | 2017-05-29
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS20000X | PRIOR NOTICE SIDEWALKS - BRONX | 2 | PRELIMINARY DESIGN | 2017-05-30 | 2017-09-26 | 2017-05-30 | 2017-09-26
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS20000X | PRIOR NOTICE SIDEWALKS - BRONX | 3 | FINAL DESIGN | 2017-09-27 | 2018-03-25 | 2017-09-27 | 2018-03-25
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS20000X | PRIOR NOTICE SIDEWALKS - BRONX | 4 | BID AWARD AND REGISTER CONTRCT | 2018-03-26 | 2018-06-23 | 2018-03-26 | 2018-06-23
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS20000X | PRIOR NOTICE SIDEWALKS - BRONX | 5 | CONSTRUCTION TO 25% | 2018-06-24 | 2018-10-21 | 2018-06-24 | 2018-10-21
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS20000X | PRIOR NOTICE SIDEWALKS - BRONX | 6 | CONSTRUCTION TO 50% | 2018-10-22 | 2019-02-18 | 2018-10-22 | 2019-02-18
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS20000X | PRIOR NOTICE SIDEWALKS - BRONX | 7 | CONSTRUCTION TO 75% | 2019-02-19 | 2019-06-18 | 2019-02-19 | 2019-06-18
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS20000X | PRIOR NOTICE SIDEWALKS - BRONX | 8 | ORIGINAL EQUIP & FURNISHING | 2019-06-19 | 2019-09-16 | 2019-06-19 | 2019-09-16
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS20000X | PRIOR NOTICE SIDEWALKS - BRONX | 9 | SUBSTANTIAL COMPLETION | 2019-09-17 | 2019-11-15 | 2019-09-17 | 2019-11-15
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS20000X | PRIOR NOTICE SIDEWALKS - BRONX | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-11-16 | 2020-06-30 | 2019-11-16 | 2021-06-30
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2014X | PRIOR NOTICE SIDEWALKS - BRONX | 1 | DEVELOP SCOPE | 2013-02-15 | 2013-05-15 | 2013-02-15 | 2013-05-15
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2014X | PRIOR NOTICE SIDEWALKS - BRONX | 2 | PRELIMINARY DESIGN | 2013-05-16 | 2013-09-12 | 2013-05-16 | 2013-09-12
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2014X | PRIOR NOTICE SIDEWALKS - BRONX | 3 | FINAL DESIGN | 2013-09-13 | 2014-03-11 | 2013-09-13 | 2014-03-11
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2014X | PRIOR NOTICE SIDEWALKS - BRONX | 4 | BID AWARD AND REGISTER CONTRCT | 2014-03-12 | 2014-06-09 | 2014-03-12 | 2014-06-09
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2014X | PRIOR NOTICE SIDEWALKS - BRONX | 5 | CONSTRUCTION TO 25% | 2014-06-10 | 2014-10-07 | 2014-06-10 | 2014-10-07
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2014X | PRIOR NOTICE SIDEWALKS - BRONX | 6 | CONSTRUCTION TO 50% | 2014-10-08 | 2015-02-04 | 2014-10-08 | 2015-02-04
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2014X | PRIOR NOTICE SIDEWALKS - BRONX | 7 | CONSTRUCTION TO 75% | 2015-02-05 | 2015-06-04 | 2015-02-05 | 2015-06-04
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2014X | PRIOR NOTICE SIDEWALKS - BRONX | 8 | ORIGINAL EQUIP & FURNISHING | 2015-06-05 | 2015-09-02 | 2015-06-05 | 2015-09-02
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2014X | PRIOR NOTICE SIDEWALKS - BRONX | 9 | SUBSTANTIAL COMPLETION | 2015-09-03 | 2015-11-01 | 2015-09-03 | 2015-11-01
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2014X | PRIOR NOTICE SIDEWALKS - BRONX | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-11-02 | 2015-12-01 | 2015-11-02 | 2022-06-30
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX006-01 | Henwood Place Step Street | 1 | DEVELOP SCOPE | 2018-06-30 | 2018-09-27 | 2019-06-30 | 2019-09-27
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX006-01 | Henwood Place Step Street | 2 | PRELIMINARY DESIGN | 2018-09-28 | 2019-01-25 | 2019-09-28 | 2020-01-25
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX006-01 | Henwood Place Step Street | 3 | FINAL DESIGN | 2019-01-26 | 2019-07-24 | 2020-01-26 | 2020-07-23
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX006-01 | Henwood Place Step Street | 4 | BID AWARD AND REGISTER CONTRCT | 2019-07-25 | 2019-10-22 | 2020-07-24 | 2020-10-21
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX006-01 | Henwood Place Step Street | 5 | CONSTRUCTION TO 25% | 2019-10-23 | 2020-02-19 | 2020-10-22 | 2021-02-18
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX006-01 | Henwood Place Step Street | 6 | CONSTRUCTION TO 50% | 2020-02-20 | 2020-06-18 | 2021-02-19 | 2021-06-18
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX006-01 | Henwood Place Step Street | 7 | CONSTRUCTION TO 75% | 2020-06-19 | 2020-10-16 | 2021-06-19 | 2021-10-16
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX006-01 | Henwood Place Step Street | 8 | ORIGINAL EQUIP & FURNISHING | 2020-10-17 | 2021-01-14 | 2021-10-17 | 2022-01-14
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX006-01 | Henwood Place Step Street | 9 | SUBSTANTIAL COMPLETION | 2021-01-15 | 2021-03-15 | 2022-01-15 | 2022-03-15
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX006-01 | Henwood Place Step Street | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-16 | 2021-04-14 | 2022-03-16 | 2026-12-30
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX100SBC | South Bronx East-West Crosstown SBS | 1 | DEVELOP SCOPE | 2017-06-30 | 2017-09-27 | 2019-06-30 | 2019-09-27
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX100SBC | South Bronx East-West Crosstown SBS | 2 | PRELIMINARY DESIGN | 2017-09-28 | 2018-01-25 | 2019-09-28 | 2020-01-25
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX100SBC | South Bronx East-West Crosstown SBS | 3 | FINAL DESIGN | 2018-01-26 | 2018-07-24 | 2020-01-26 | 2020-07-23
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX100SBC | South Bronx East-West Crosstown SBS | 4 | BID AWARD AND REGISTER CONTRCT | 2018-07-25 | 2018-10-22 | 2020-07-24 | 2020-10-21
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX100SBC | South Bronx East-West Crosstown SBS | 5 | CONSTRUCTION TO 25% | 2018-10-23 | 2019-02-19 | 2020-10-22 | 2021-02-18
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX100SBC | South Bronx East-West Crosstown SBS | 6 | CONSTRUCTION TO 50% | 2019-02-20 | 2019-06-19 | 2021-02-19 | 2021-06-18
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX100SBC | South Bronx East-West Crosstown SBS | 7 | CONSTRUCTION TO 75% | 2019-06-20 | 2019-10-17 | 2021-06-19 | 2021-10-16
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX100SBC | South Bronx East-West Crosstown SBS | 8 | ORIGINAL EQUIP & FURNISHING | 2019-10-18 | 2020-01-15 | 2021-10-17 | 2022-01-14
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX100SBC | South Bronx East-West Crosstown SBS | 9 | SUBSTANTIAL COMPLETION | 2020-01-16 | 2020-03-15 | 2022-01-15 | 2022-03-15
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX100SBC | South Bronx East-West Crosstown SBS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-03-16 | 2020-04-14 | 2022-03-16 | 2023-06-30
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX100SBS | Webster Ave SBS | 1 | DEVELOP SCOPE | 2015-01-17 | 2015-04-16 | 2015-01-17 | 2015-04-16
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX100SBS | Webster Ave SBS | 2 | PRELIMINARY DESIGN | 2015-04-17 | 2015-08-14 | 2015-04-17 | 2015-08-14
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX100SBS | Webster Ave SBS | 3 | FINAL DESIGN | 2015-08-15 | 2016-02-10 | 2015-08-15 | 2016-02-10
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX100SBS | Webster Ave SBS | 4 | BID AWARD AND REGISTER CONTRCT | 2016-02-11 | 2016-05-10 | 2016-02-11 | 2016-05-10
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX100SBS | Webster Ave SBS | 5 | CONSTRUCTION TO 25% | 2016-05-11 | 2016-09-07 | 2016-05-11 | 2016-09-07
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX100SBS | Webster Ave SBS | 6 | CONSTRUCTION TO 50% | 2016-09-08 | 2017-01-05 | 2016-09-08 | 2017-01-05
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX100SBS | Webster Ave SBS | 7 | CONSTRUCTION TO 75% | 2017-01-06 | 2017-05-05 | 2017-01-06 | 2017-05-05
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX100SBS | Webster Ave SBS | 8 | ORIGINAL EQUIP & FURNISHING | 2017-05-06 | 2017-08-03 | 2017-05-06 | 2017-08-03
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX100SBS | Webster Ave SBS | 9 | SUBSTANTIAL COMPLETION | 2017-08-04 | 2017-10-02 | 2017-08-04 | 2017-10-02
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX100SBS | Webster Ave SBS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-10-03 | 2017-11-01 | 2017-10-03 | 2024-06-30
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX402 | Bruner and Ely | 1 | DEVELOP SCOPE | 2018-06-30 | 2018-09-27 | 2020-06-30 | 2020-09-27
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX402 | Bruner and Ely | 2 | PRELIMINARY DESIGN | 2018-09-28 | 2019-01-25 | 2020-09-28 | 2021-01-25
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX402 | Bruner and Ely | 3 | FINAL DESIGN | 2019-01-26 | 2019-07-24 | 2021-01-26 | 2021-07-24
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX402 | Bruner and Ely | 4 | BID AWARD AND REGISTER CONTRCT | 2019-07-25 | 2019-10-22 | 2021-07-25 | 2021-10-22
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX402 | Bruner and Ely | 5 | CONSTRUCTION TO 25% | 2019-10-23 | 2020-02-19 | 2021-10-23 | 2022-02-19
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX402 | Bruner and Ely | 6 | CONSTRUCTION TO 50% | 2020-02-20 | 2020-06-18 | 2022-02-20 | 2022-06-19
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX402 | Bruner and Ely | 7 | CONSTRUCTION TO 75% | 2020-06-19 | 2020-10-16 | 2022-06-20 | 2022-10-17
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX402 | Bruner and Ely | 8 | ORIGINAL EQUIP & FURNISHING | 2020-10-17 | 2021-01-14 | 2022-10-18 | 2023-01-15
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX402 | Bruner and Ely | 9 | SUBSTANTIAL COMPLETION | 2021-01-15 | 2021-03-15 | 2023-01-16 | 2023-03-16
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX402 | Bruner and Ely | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-16 | 2021-04-14 | 2023-03-17 | 2023-04-15
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX404 | Southern Bronx Multi-Site Safety Improvements | 1 | DEVELOP SCOPE | 2020-06-30 | 2020-09-27 | 2019-03-15 | 2020-01-02
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX404 | Southern Bronx Multi-Site Safety Improvements | 2 | PRELIMINARY DESIGN | 2020-09-28 | 2021-01-25 | 2020-01-03 | 2020-05-01
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX404 | Southern Bronx Multi-Site Safety Improvements | 3 | FINAL DESIGN | 2021-01-26 | 2021-07-24 | 2020-05-02 | 2020-10-28
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX404 | Southern Bronx Multi-Site Safety Improvements | 4 | BID AWARD AND REGISTER CONTRCT | 2021-07-25 | 2021-10-22 | 2020-10-29 | 2021-01-26
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX404 | Southern Bronx Multi-Site Safety Improvements | 5 | CONSTRUCTION TO 25% | 2021-10-23 | 2022-02-19 | 2021-01-27 | 2021-05-26
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX404 | Southern Bronx Multi-Site Safety Improvements | 6 | CONSTRUCTION TO 50% | 2022-02-20 | 2022-06-19 | 2021-05-27 | 2021-09-23
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX404 | Southern Bronx Multi-Site Safety Improvements | 7 | CONSTRUCTION TO 75% | 2022-06-20 | 2022-10-17 | 2021-09-24 | 2022-01-21
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX404 | Southern Bronx Multi-Site Safety Improvements | 8 | ORIGINAL EQUIP & FURNISHING | 2022-10-18 | 2023-01-15 | 2022-01-22 | 2022-04-21
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX404 | Southern Bronx Multi-Site Safety Improvements | 9 | SUBSTANTIAL COMPLETION | 2023-01-16 | 2023-03-16 | 2022-04-22 | 2022-06-20
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX404 | Southern Bronx Multi-Site Safety Improvements | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-03-17 | 2023-04-15 | 2022-06-21 | 2024-06-30
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX406 | Northwest Bronx School Safety Improvements | 1 | DEVELOP SCOPE | 2019-06-30 | 2019-09-27 | 2019-03-18 | 2019-12-12
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX406 | Northwest Bronx School Safety Improvements | 2 | PRELIMINARY DESIGN | 2019-09-28 | 2020-01-25 | 2019-12-13 | 2020-04-10
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX406 | Northwest Bronx School Safety Improvements | 3 | FINAL DESIGN | 2020-01-26 | 2020-07-23 | 2020-04-11 | 2020-10-07
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX406 | Northwest Bronx School Safety Improvements | 4 | BID AWARD AND REGISTER CONTRCT | 2020-07-24 | 2020-10-21 | 2020-10-08 | 2021-01-05
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX406 | Northwest Bronx School Safety Improvements | 5 | CONSTRUCTION TO 25% | 2020-10-22 | 2021-02-18 | 2021-01-06 | 2021-05-05
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX406 | Northwest Bronx School Safety Improvements | 6 | CONSTRUCTION TO 50% | 2021-02-19 | 2021-06-18 | 2021-05-06 | 2021-09-02
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX406 | Northwest Bronx School Safety Improvements | 7 | CONSTRUCTION TO 75% | 2021-06-19 | 2021-10-16 | 2021-09-03 | 2021-12-31
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX406 | Northwest Bronx School Safety Improvements | 8 | ORIGINAL EQUIP & FURNISHING | 2021-10-17 | 2022-01-14 | 2022-01-01 | 2022-03-31
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX406 | Northwest Bronx School Safety Improvements | 9 | SUBSTANTIAL COMPLETION | 2022-01-15 | 2022-03-15 | 2022-04-01 | 2022-05-30
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX406 | Northwest Bronx School Safety Improvements | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-03-16 | 2022-04-14 | 2022-05-31 | 2025-06-30
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX710A | Pelham Pkwy - West & East and North & South Bounds (Phase A) | 1 | DEVELOP SCOPE | 2010-03-05 | 2010-06-02 | 2006-07-01 | 2007-06-30
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX710A | Pelham Pkwy - West & East and North & South Bounds (Phase A) | 2 | PRELIMINARY DESIGN | 2010-06-03 | 2010-09-30 | 2007-07-01 | 2009-06-29
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX710A | Pelham Pkwy - West & East and North & South Bounds (Phase A) | 3 | FINAL DESIGN | 2010-10-01 | 2011-03-29 | 2009-06-30 | 2016-03-20
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX710A | Pelham Pkwy - West & East and North & South Bounds (Phase A) | 4 | BID AWARD AND REGISTER CONTRCT | 2011-03-30 | 2011-06-27 | 2016-03-04 | 2016-06-01
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX710A | Pelham Pkwy - West & East and North & South Bounds (Phase A) | 5 | CONSTRUCTION TO 25% | 2011-06-28 | 2011-10-25 | 2016-06-02 | 2016-09-29
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX710A | Pelham Pkwy - West & East and North & South Bounds (Phase A) | 6 | CONSTRUCTION TO 50% | 2011-10-26 | 2012-02-22 | 2016-09-30 | 2017-01-27
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX710A | Pelham Pkwy - West & East and North & South Bounds (Phase A) | 7 | CONSTRUCTION TO 75% | 2012-02-23 | 2012-06-21 | 2017-01-28 | 2017-05-27
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX710A | Pelham Pkwy - West & East and North & South Bounds (Phase A) | 8 | ORIGINAL EQUIP & FURNISHING | 2012-06-22 | 2012-09-19 | 2017-05-28 | 2017-08-25
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX710A | Pelham Pkwy - West & East and North & South Bounds (Phase A) | 9 | SUBSTANTIAL COMPLETION | 2012-09-20 | 2012-11-18 | 2017-08-26 | 2021-07-31
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX710A | Pelham Pkwy - West & East and North & South Bounds (Phase A) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-11-19 | 2012-12-18 | 2021-08-01 | 2024-04-06
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXF2000B | 1400 WILLIAMSBRIDGE RD - HVAC AND FIRE ALARM SYS | 1 | DEVELOP SCOPE | 2016-06-30 | 2016-09-27 | 2016-06-30 | 2016-09-27
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXF2000B | 1400 WILLIAMSBRIDGE RD - HVAC AND FIRE ALARM SYS | 2 | PRELIMINARY DESIGN | 2016-09-28 | 2017-01-25 | 2016-09-28 | 2017-01-25
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXF2000B | 1400 WILLIAMSBRIDGE RD - HVAC AND FIRE ALARM SYS | 3 | FINAL DESIGN | 2017-01-26 | 2017-07-24 | 2017-01-26 | 2017-07-24
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXF2000B | 1400 WILLIAMSBRIDGE RD - HVAC AND FIRE ALARM SYS | 4 | BID AWARD AND REGISTER CONTRCT | 2017-07-25 | 2017-10-22 | 2017-07-25 | 2017-10-22
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXF2000B | 1400 WILLIAMSBRIDGE RD - HVAC AND FIRE ALARM SYS | 5 | CONSTRUCTION TO 25% | 2017-10-23 | 2018-02-19 | 2017-10-23 | 2018-02-19
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXF2000B | 1400 WILLIAMSBRIDGE RD - HVAC AND FIRE ALARM SYS | 6 | CONSTRUCTION TO 50% | 2018-02-20 | 2018-06-19 | 2018-02-20 | 2018-06-19
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXF2000B | 1400 WILLIAMSBRIDGE RD - HVAC AND FIRE ALARM SYS | 7 | CONSTRUCTION TO 75% | 2018-06-20 | 2018-10-17 | 2018-06-20 | 2018-10-17
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXF2000B | 1400 WILLIAMSBRIDGE RD - HVAC AND FIRE ALARM SYS | 8 | ORIGINAL EQUIP & FURNISHING | 2018-10-18 | 2019-01-15 | 2018-10-18 | 2019-01-15
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXF2000B | 1400 WILLIAMSBRIDGE RD - HVAC AND FIRE ALARM SYS | 9 | SUBSTANTIAL COMPLETION | 2019-01-16 | 2019-03-16 | 2019-01-16 | 2019-03-16
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXF2000B | 1400 WILLIAMSBRIDGE RD - HVAC AND FIRE ALARM SYS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-03-17 | 2019-04-15 | 2019-03-17 | 2022-06-30
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXF2144W | Replacement of HVAC Unit | 1 | PROJECT START | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-02
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXF2144W | Replacement of HVAC Unit | 2 | DESIGN START | 2016-07-02 | 2016-07-02 | 2016-07-03 | 2016-08-17
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXF2144W | Replacement of HVAC Unit | 3 | DESIGN COMPLETION | 2016-07-03 | 2016-07-03 | 2016-08-18 | 2017-01-09
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXF2144W | Replacement of HVAC Unit | 4 | CONSTRUCTION START | 2016-07-04 | 2016-07-04 | 2017-01-10 | 2017-10-19
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXF2144W | Replacement of HVAC Unit | 5 | CONSTRUCTION COMPLETION | 2016-07-05 | 2017-07-05 | 2017-10-20 | 2021-01-13
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP132 | RECON JOHNSON/IRWIN AVES-RET WALL | 1 | DEVELOP SCOPE | 2001-07-01 | 2001-09-28 | 2001-07-01 | 2001-09-28
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP132 | RECON JOHNSON/IRWIN AVES-RET WALL | 2 | PRELIMINARY DESIGN | 2001-09-29 | 2002-01-26 | 2001-09-29 | 2002-01-26
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP132 | RECON JOHNSON/IRWIN AVES-RET WALL | 3 | FINAL DESIGN | 2002-01-27 | 2002-07-25 | 2002-01-27 | 2002-07-25
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP132 | RECON JOHNSON/IRWIN AVES-RET WALL | 4 | BID AWARD AND REGISTER CONTRCT | 2002-07-26 | 2002-10-23 | 2002-07-26 | 2002-10-23
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP132 | RECON JOHNSON/IRWIN AVES-RET WALL | 5 | CONSTRUCTION TO 25% | 2002-10-24 | 2003-02-20 | 2002-10-24 | 2003-02-20
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP132 | RECON JOHNSON/IRWIN AVES-RET WALL | 6 | CONSTRUCTION TO 50% | 2003-02-21 | 2003-06-20 | 2003-02-21 | 2003-06-20
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP132 | RECON JOHNSON/IRWIN AVES-RET WALL | 7 | CONSTRUCTION TO 75% | 2003-06-21 | 2003-10-18 | 2003-06-21 | 2003-10-18
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP132 | RECON JOHNSON/IRWIN AVES-RET WALL | 8 | ORIGINAL EQUIP & FURNISHING | 2003-10-19 | 2004-01-16 | 2003-10-19 | 2004-01-16
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP132 | RECON JOHNSON/IRWIN AVES-RET WALL | 9 | SUBSTANTIAL COMPLETION | 2004-01-17 | 2004-03-16 | 2004-01-17 | 2004-03-16
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP132 | RECON JOHNSON/IRWIN AVES-RET WALL | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2004-03-17 | 2004-04-15 | 2004-03-17 | 2021-06-30
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP134 | BRONX QUAD (EAST FORDHAM RD) | 1 | DEVELOP SCOPE | 2008-06-30 | 2008-10-27 | 2007-06-30 | 2007-09-27
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP134 | BRONX QUAD (EAST FORDHAM RD) | 2 | DESIGN START | 2008-10-28 | 2010-04-20 | 2007-09-28 | 2008-01-25
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP134 | BRONX QUAD (EAST FORDHAM RD) | 3 | CONSTRUCTION START | 2010-04-21 | 2012-04-09 | 2008-01-26 | 2008-07-23
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP134 | BRONX QUAD (EAST FORDHAM RD) | 4 | BID AWARD AND REGISTER CONTRCT | 2010-04-21 | 2012-04-09 | 2010-06-24 | 2010-09-21
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP134 | BRONX QUAD (EAST FORDHAM RD) | 5 | CONSTRUCTION TO 25% | 2010-04-21 | 2012-04-09 | 2010-09-22 | 2010-09-21
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP134 | BRONX QUAD (EAST FORDHAM RD) | 6 | CONSTRUCTION TO 50% | 2010-04-21 | 2012-04-09 | 2010-09-22 | 2010-09-21
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP134 | BRONX QUAD (EAST FORDHAM RD) | 7 | CONSTRUCTION TO 75% | 2010-04-21 | 2012-04-09 | 2010-09-22 | 2010-09-21
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP134 | BRONX QUAD (EAST FORDHAM RD) | 8 | ORIGINAL EQUIP & FURNISHING | 2010-04-21 | 2012-04-09 | 2010-09-22 | 2010-09-21
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP134 | BRONX QUAD (EAST FORDHAM RD) | 9 | SUBSTANTIAL COMPLETION | 2010-04-21 | 2012-04-09 | 2010-09-22 | 2010-09-21
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP134 | BRONX QUAD (EAST FORDHAM RD) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2010-04-21 | 2012-04-09 | 2021-03-27 | 2021-04-25
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP136A | GRAND CONCOURSE RECON SERVICE ROAD E.166 TO E171ST | 1 | DEVELOP SCOPE | 2007-02-21 | 2007-06-20 | 2011-12-09 | 2012-03-07
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP136A | GRAND CONCOURSE RECON SERVICE ROAD E.166 TO E171ST | 2 | DESIGN START | 2007-06-21 | 2008-12-11 | 2012-03-08 | 2013-03-07
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP136A | GRAND CONCOURSE RECON SERVICE ROAD E.166 TO E171ST | 3 | CONSTRUCTION START | 2008-12-12 | 2010-12-01 | 2013-03-08 | 2014-01-01
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP136A | GRAND CONCOURSE RECON SERVICE ROAD E.166 TO E171ST | 4 | BID AWARD AND REGISTER CONTRCT | 2008-12-12 | 2010-12-01 | 2014-01-02 | 2014-04-01
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP136A | GRAND CONCOURSE RECON SERVICE ROAD E.166 TO E171ST | 5 | CONSTRUCTION TO 25% | 2008-12-12 | 2010-12-01 | 2014-04-01 | 2014-07-29
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP136A | GRAND CONCOURSE RECON SERVICE ROAD E.166 TO E171ST | 6 | CONSTRUCTION TO 50% | 2008-12-12 | 2010-12-01 | 2014-07-30 | 2014-11-26
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP136A | GRAND CONCOURSE RECON SERVICE ROAD E.166 TO E171ST | 7 | CONSTRUCTION TO 75% | 2008-12-12 | 2010-12-01 | 2014-11-27 | 2015-03-26
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP136A | GRAND CONCOURSE RECON SERVICE ROAD E.166 TO E171ST | 8 | ORIGINAL EQUIP & FURNISHING | 2008-12-12 | 2010-12-01 | 2015-03-27 | 2015-06-24
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP136A | GRAND CONCOURSE RECON SERVICE ROAD E.166 TO E171ST | 9 | SUBSTANTIAL COMPLETION | 2008-12-12 | 2010-12-01 | 2015-04-26 | 2015-06-24
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP136A | GRAND CONCOURSE RECON SERVICE ROAD E.166 TO E171ST | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2008-12-12 | 2010-12-01 | 2015-06-25 | 2024-06-30
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP136B | Grand Concourse Phase 3 | 1 | DEVELOP SCOPE | 2018-06-30 | 2018-09-27 | 2015-07-01 | 2015-09-28
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP136B | Grand Concourse Phase 3 | 2 | PRELIMINARY DESIGN | 2018-09-28 | 2019-01-25 | 2015-09-29 | 2016-01-26
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP136B | Grand Concourse Phase 3 | 3 | FINAL DESIGN | 2019-01-26 | 2019-07-24 | 2016-01-27 | 2016-07-24
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP136B | Grand Concourse Phase 3 | 4 | BID AWARD AND REGISTER CONTRCT | 2019-07-25 | 2019-10-22 | 2016-07-25 | 2016-10-22
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP136B | Grand Concourse Phase 3 | 5 | CONSTRUCTION TO 25% | 2019-10-23 | 2020-02-19 | 2016-10-23 | 2017-02-19
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP136B | Grand Concourse Phase 3 | 6 | CONSTRUCTION TO 50% | 2020-02-20 | 2020-06-18 | 2017-02-20 | 2017-06-19
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP136B | Grand Concourse Phase 3 | 7 | CONSTRUCTION TO 75% | 2020-06-19 | 2020-10-16 | 2017-06-20 | 2017-10-17
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP136B | Grand Concourse Phase 3 | 8 | ORIGINAL EQUIP & FURNISHING | 2020-10-17 | 2021-01-14 | 2017-10-18 | 2018-01-15
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP136B | Grand Concourse Phase 3 | 9 | SUBSTANTIAL COMPLETION | 2021-01-15 | 2021-03-15 | 2018-01-16 | 2019-11-30
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP136B | Grand Concourse Phase 3 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-16 | 2021-04-14 | 2019-12-01 | 2022-11-29
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP136C | Grand Concourse Phase 4 (SEX002268) | 1 | DEVELOP SCOPE | 2017-06-30 | 2017-09-27 | 2017-06-30 | 2017-09-27
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP136C | Grand Concourse Phase 4 (SEX002268) | 2 | PRELIMINARY DESIGN | 2017-09-28 | 2018-01-25 | 2017-09-28 | 2018-01-25
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP136C | Grand Concourse Phase 4 (SEX002268) | 3 | FINAL DESIGN | 2018-01-26 | 2018-07-24 | 2018-01-26 | 2018-07-24
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP136C | Grand Concourse Phase 4 (SEX002268) | 4 | BID AWARD AND REGISTER CONTRCT | 2018-07-25 | 2018-10-22 | 2018-07-25 | 2018-10-22
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP136C | Grand Concourse Phase 4 (SEX002268) | 5 | CONSTRUCTION TO 25% | 2018-10-23 | 2019-02-19 | 2018-10-23 | 2019-02-19
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP136C | Grand Concourse Phase 4 (SEX002268) | 6 | CONSTRUCTION TO 50% | 2019-02-20 | 2019-06-19 | 2019-02-20 | 2019-06-19
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP136C | Grand Concourse Phase 4 (SEX002268) | 7 | CONSTRUCTION TO 75% | 2019-06-20 | 2019-10-17 | 2019-06-20 | 2019-10-17
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP136C | Grand Concourse Phase 4 (SEX002268) | 8 | ORIGINAL EQUIP & FURNISHING | 2019-10-18 | 2020-01-15 | 2019-10-18 | 2020-01-15
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP136C | Grand Concourse Phase 4 (SEX002268) | 9 | SUBSTANTIAL COMPLETION | 2020-01-16 | 2020-03-15 | 2020-01-16 | 2020-03-15
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP136C | Grand Concourse Phase 4 (SEX002268) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-03-16 | 2020-04-14 | 2020-03-16 | 2022-06-30
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP136D | Grand Concourse Phase 5 | 1 | DEVELOP SCOPE | 2022-06-30 | 2022-09-27 | 2019-06-30 | 2019-09-27
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP136D | Grand Concourse Phase 5 | 2 | PRELIMINARY DESIGN | 2022-09-28 | 2023-01-25 | 2019-09-28 | 2020-01-25
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP136D | Grand Concourse Phase 5 | 3 | FINAL DESIGN | 2023-01-26 | 2023-07-24 | 2020-01-26 | 2020-07-23
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP136D | Grand Concourse Phase 5 | 4 | BID AWARD AND REGISTER CONTRCT | 2023-07-25 | 2023-10-22 | 2020-07-24 | 2020-10-21
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP136D | Grand Concourse Phase 5 | 5 | CONSTRUCTION TO 25% | 2023-10-23 | 2024-02-19 | 2020-10-22 | 2021-02-18
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP136D | Grand Concourse Phase 5 | 6 | CONSTRUCTION TO 50% | 2024-02-20 | 2024-06-18 | 2021-02-19 | 2021-06-18
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP136D | Grand Concourse Phase 5 | 7 | CONSTRUCTION TO 75% | 2024-06-19 | 2024-10-16 | 2021-06-19 | 2021-10-16
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP136D | Grand Concourse Phase 5 | 8 | ORIGINAL EQUIP & FURNISHING | 2024-10-17 | 2025-01-14 | 2021-10-17 | 2022-01-14
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP136D | Grand Concourse Phase 5 | 9 | SUBSTANTIAL COMPLETION | 2025-01-15 | 2025-03-15 | 2022-01-15 | 2022-03-15
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP136D | Grand Concourse Phase 5 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-03-16 | 2025-04-14 | 2022-03-16 | 2023-06-30
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP2007 | E177TH ST/DEVOE AVE BT SHERIDAN (I-895) /E.TREMONT HED-560 | 1 | DEVELOP SCOPE | 2002-05-21 | 2002-08-18 | 2002-05-21 | 2002-08-18
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP2007 | E177TH ST/DEVOE AVE BT SHERIDAN (I-895) /E.TREMONT HED-560 | 2 | PRELIMINARY DESIGN | 2002-08-19 | 2002-12-16 | 2002-08-19 | 2002-12-16
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP2007 | E177TH ST/DEVOE AVE BT SHERIDAN (I-895) /E.TREMONT HED-560 | 3 | FINAL DESIGN | 2002-12-17 | 2003-06-14 | 2002-12-17 | 2003-06-14
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP2007 | E177TH ST/DEVOE AVE BT SHERIDAN (I-895) /E.TREMONT HED-560 | 4 | BID AWARD AND REGISTER CONTRCT | 2003-06-15 | 2003-09-12 | 2022-03-04 | 2022-06-01
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP2007 | E177TH ST/DEVOE AVE BT SHERIDAN (I-895) /E.TREMONT HED-560 | 5 | CONSTRUCTION TO 25% | 2003-09-13 | 2004-01-10 | 2022-06-02 | 2022-06-01
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP2007 | E177TH ST/DEVOE AVE BT SHERIDAN (I-895) /E.TREMONT HED-560 | 6 | CONSTRUCTION TO 50% | 2004-01-11 | 2004-05-09 | 2022-06-02 | 2022-06-01
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP2007 | E177TH ST/DEVOE AVE BT SHERIDAN (I-895) /E.TREMONT HED-560 | 7 | CONSTRUCTION TO 75% | 2004-05-10 | 2004-09-06 | 2022-06-02 | 2022-06-01
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP2007 | E177TH ST/DEVOE AVE BT SHERIDAN (I-895) /E.TREMONT HED-560 | 8 | ORIGINAL EQUIP & FURNISHING | 2004-09-07 | 2004-12-05 | 2022-06-02 | 2022-06-01
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP2007 | E177TH ST/DEVOE AVE BT SHERIDAN (I-895) /E.TREMONT HED-560 | 9 | SUBSTANTIAL COMPLETION | 2004-12-06 | 2005-02-03 | 2022-06-02 | 2022-06-01
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP2007 | E177TH ST/DEVOE AVE BT SHERIDAN (I-895) /E.TREMONT HED-560 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2005-02-04 | 2005-03-05 | 2023-11-04 | 2023-12-03
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXPRATT | Pratt Ave Reconstruction and Retaining Wall | 1 | DEVELOP SCOPE | 2017-06-30 | 2017-09-27 | 2017-06-30 | 2017-09-27
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXPRATT | Pratt Ave Reconstruction and Retaining Wall | 2 | PRELIMINARY DESIGN | 2017-09-28 | 2018-01-25 | 2017-09-28 | 2018-01-25
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXPRATT | Pratt Ave Reconstruction and Retaining Wall | 3 | FINAL DESIGN | 2018-01-26 | 2018-07-24 | 2018-01-26 | 2018-07-24
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXPRATT | Pratt Ave Reconstruction and Retaining Wall | 4 | BID AWARD AND REGISTER CONTRCT | 2018-07-25 | 2018-10-22 | 2018-07-25 | 2018-10-22
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXPRATT | Pratt Ave Reconstruction and Retaining Wall | 5 | CONSTRUCTION TO 25% | 2018-10-23 | 2019-02-19 | 2018-10-23 | 2019-02-19
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXPRATT | Pratt Ave Reconstruction and Retaining Wall | 6 | CONSTRUCTION TO 50% | 2019-02-20 | 2019-06-19 | 2019-02-20 | 2019-06-19
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXPRATT | Pratt Ave Reconstruction and Retaining Wall | 7 | CONSTRUCTION TO 75% | 2019-06-20 | 2019-10-17 | 2019-06-20 | 2019-10-17
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXPRATT | Pratt Ave Reconstruction and Retaining Wall | 8 | ORIGINAL EQUIP & FURNISHING | 2019-10-18 | 2020-01-15 | 2019-10-18 | 2020-01-15
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXPRATT | Pratt Ave Reconstruction and Retaining Wall | 9 | SUBSTANTIAL COMPLETION | 2020-01-16 | 2020-03-15 | 2020-01-16 | 2022-01-22
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXPRATT | Pratt Ave Reconstruction and Retaining Wall | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-03-16 | 2020-04-14 | 2022-01-23 | 2025-01-20
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXRCPLZ | ROBERTO CLEMENTE PLAZA & HUB REDESIGN AND RECONSTRUCTION | 1 | DEVELOP SCOPE | 2008-06-30 | 2008-10-27 | 2008-10-17 | 2009-01-14
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXRCPLZ | ROBERTO CLEMENTE PLAZA & HUB REDESIGN AND RECONSTRUCTION | 2 | DESIGN START | 2008-10-28 | 2010-04-20 | 2009-01-15 | 2009-05-14
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXRCPLZ | ROBERTO CLEMENTE PLAZA & HUB REDESIGN AND RECONSTRUCTION | 3 | CONSTRUCTION START | 2010-04-21 | 2012-04-09 | 2009-05-15 | 2009-11-10
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXRCPLZ | ROBERTO CLEMENTE PLAZA & HUB REDESIGN AND RECONSTRUCTION | 4 | BID AWARD AND REGISTER CONTRCT | 2010-04-21 | 2012-04-09 | 2009-11-11 | 2010-02-08
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXRCPLZ | ROBERTO CLEMENTE PLAZA & HUB REDESIGN AND RECONSTRUCTION | 5 | CONSTRUCTION TO 25% | 2010-04-21 | 2012-04-09 | 2013-04-11 | 2013-10-07
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXRCPLZ | ROBERTO CLEMENTE PLAZA & HUB REDESIGN AND RECONSTRUCTION | 6 | CONSTRUCTION TO 50% | 2010-04-21 | 2012-04-09 | 2013-10-08 | 2014-10-07
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXRCPLZ | ROBERTO CLEMENTE PLAZA & HUB REDESIGN AND RECONSTRUCTION | 7 | CONSTRUCTION TO 75% | 2010-04-21 | 2012-04-09 | 2014-10-08 | 2015-04-05
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXRCPLZ | ROBERTO CLEMENTE PLAZA & HUB REDESIGN AND RECONSTRUCTION | 8 | ORIGINAL EQUIP & FURNISHING | 2010-04-21 | 2012-04-09 | 2015-04-06 | 2015-07-04
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXRCPLZ | ROBERTO CLEMENTE PLAZA & HUB REDESIGN AND RECONSTRUCTION | 9 | SUBSTANTIAL COMPLETION | 2010-04-21 | 2012-04-09 | 2015-05-06 | 2015-11-01
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXRCPLZ | ROBERTO CLEMENTE PLAZA & HUB REDESIGN AND RECONSTRUCTION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2010-04-21 | 2012-04-09 | 2015-11-02 | 2021-10-11
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXS311V1 | CLIFFORD PLACE STEP STREET | 1 | DEVELOP SCOPE | 2011-03-01 | 2011-05-29 | 2011-03-01 | 2011-05-29
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXS311V1 | CLIFFORD PLACE STEP STREET | 2 | PRELIMINARY DESIGN | 2011-05-30 | 2011-09-26 | 2011-05-30 | 2011-09-26
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXS311V1 | CLIFFORD PLACE STEP STREET | 3 | FINAL DESIGN | 2011-09-27 | 2012-03-24 | 2011-09-27 | 2012-03-24
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXS311V1 | CLIFFORD PLACE STEP STREET | 4 | BID AWARD AND REGISTER CONTRCT | 2012-03-25 | 2012-06-22 | 2022-03-25 | 2022-06-22
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXS311V1 | CLIFFORD PLACE STEP STREET | 5 | CONSTRUCTION TO 25% | 2012-06-23 | 2012-10-20 | 2022-06-23 | 2022-06-22
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXS311V1 | CLIFFORD PLACE STEP STREET | 6 | CONSTRUCTION TO 50% | 2012-10-21 | 2013-02-17 | 2022-06-23 | 2022-06-22
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXS311V1 | CLIFFORD PLACE STEP STREET | 7 | CONSTRUCTION TO 75% | 2013-02-18 | 2013-06-17 | 2022-06-23 | 2022-06-22
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXS311V1 | CLIFFORD PLACE STEP STREET | 8 | ORIGINAL EQUIP & FURNISHING | 2013-06-18 | 2013-09-15 | 2022-06-23 | 2022-06-22
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXS311V1 | CLIFFORD PLACE STEP STREET | 9 | SUBSTANTIAL COMPLETION | 2013-09-16 | 2013-11-14 | 2022-06-23 | 2022-06-22
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXS311V1 | CLIFFORD PLACE STEP STREET | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-11-15 | 2013-12-14 | 2022-06-23 | 2024-01-25
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXS411 | West 229th St Step Street | 1 | DEVELOP SCOPE | 2015-02-16 | 2015-05-16 | 2015-02-16 | 2015-05-16
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXS411 | West 229th St Step Street | 2 | PRELIMINARY DESIGN | 2015-05-17 | 2015-09-13 | 2015-05-17 | 2015-09-13
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXS411 | West 229th St Step Street | 3 | FINAL DESIGN | 2015-09-14 | 2016-03-11 | 2015-09-14 | 2016-03-11
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXS411 | West 229th St Step Street | 4 | BID AWARD AND REGISTER CONTRCT | 2016-03-12 | 2016-06-09 | 2016-03-12 | 2016-06-09
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXS411 | West 229th St Step Street | 5 | CONSTRUCTION TO 25% | 2016-06-10 | 2016-10-07 | 2016-06-10 | 2016-10-07
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXS411 | West 229th St Step Street | 6 | CONSTRUCTION TO 50% | 2016-10-08 | 2017-02-04 | 2016-10-08 | 2017-02-04
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXS411 | West 229th St Step Street | 7 | CONSTRUCTION TO 75% | 2017-02-05 | 2017-06-04 | 2017-02-05 | 2017-06-04
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXS411 | West 229th St Step Street | 8 | ORIGINAL EQUIP & FURNISHING | 2017-06-05 | 2017-09-02 | 2017-06-05 | 2017-09-02
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXS411 | West 229th St Step Street | 9 | SUBSTANTIAL COMPLETION | 2017-09-03 | 2017-11-01 | 2017-09-03 | 2017-11-01
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXS411 | West 229th St Step Street | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-11-02 | 2017-12-01 | 2017-11-02 | 2023-06-30
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXS511 | West Tremont Ave Step Street | 1 | DEVELOP SCOPE | 2015-06-01 | 2015-08-29 | 2015-06-01 | 2015-08-29
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXS511 | West Tremont Ave Step Street | 2 | PRELIMINARY DESIGN | 2015-08-30 | 2015-12-27 | 2015-08-30 | 2015-12-27
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXS511 | West Tremont Ave Step Street | 3 | FINAL DESIGN | 2015-12-28 | 2016-06-24 | 2015-12-28 | 2016-06-24
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXS511 | West Tremont Ave Step Street | 4 | BID AWARD AND REGISTER CONTRCT | 2016-06-25 | 2016-09-22 | 2016-06-25 | 2016-09-22
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXS511 | West Tremont Ave Step Street | 5 | CONSTRUCTION TO 25% | 2016-09-23 | 2017-01-20 | 2016-09-23 | 2017-01-20
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXS511 | West Tremont Ave Step Street | 6 | CONSTRUCTION TO 50% | 2017-01-21 | 2017-05-20 | 2017-01-21 | 2017-05-20
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXS511 | West Tremont Ave Step Street | 7 | CONSTRUCTION TO 75% | 2017-05-21 | 2017-09-17 | 2017-05-21 | 2017-09-17
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXS511 | West Tremont Ave Step Street | 8 | ORIGINAL EQUIP & FURNISHING | 2017-09-18 | 2017-12-16 | 2017-09-18 | 2017-12-16
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXS511 | West Tremont Ave Step Street | 9 | SUBSTANTIAL COMPLETION | 2017-12-17 | 2018-02-14 | 2017-12-17 | 2019-10-05
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXS511 | West Tremont Ave Step Street | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-02-15 | 2018-03-16 | 2019-10-06 | 2022-10-04
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXS711 | RECONSTRUCTION OF STEP STREET AT DAVIDSON AVE | 1 | DEVELOP SCOPE | 2017-03-01 | 2017-05-29 | 2017-03-01 | 2017-05-29
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXS711 | RECONSTRUCTION OF STEP STREET AT DAVIDSON AVE | 2 | PRELIMINARY DESIGN | 2017-05-30 | 2017-09-26 | 2017-05-30 | 2017-09-26
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXS711 | RECONSTRUCTION OF STEP STREET AT DAVIDSON AVE | 3 | FINAL DESIGN | 2017-09-27 | 2018-03-25 | 2017-09-27 | 2018-03-25
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXS711 | RECONSTRUCTION OF STEP STREET AT DAVIDSON AVE | 4 | BID AWARD AND REGISTER CONTRCT | 2018-03-26 | 2018-06-23 | 2018-03-26 | 2018-06-23
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXS711 | RECONSTRUCTION OF STEP STREET AT DAVIDSON AVE | 5 | CONSTRUCTION TO 25% | 2018-06-24 | 2018-10-21 | 2018-06-24 | 2018-10-21
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXS711 | RECONSTRUCTION OF STEP STREET AT DAVIDSON AVE | 6 | CONSTRUCTION TO 50% | 2018-10-22 | 2019-02-18 | 2018-10-22 | 2019-02-18
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXS711 | RECONSTRUCTION OF STEP STREET AT DAVIDSON AVE | 7 | CONSTRUCTION TO 75% | 2019-02-19 | 2019-06-18 | 2019-02-19 | 2019-06-18
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXS711 | RECONSTRUCTION OF STEP STREET AT DAVIDSON AVE | 8 | ORIGINAL EQUIP & FURNISHING | 2019-06-19 | 2019-09-16 | 2019-06-19 | 2019-09-16
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXS711 | RECONSTRUCTION OF STEP STREET AT DAVIDSON AVE | 9 | SUBSTANTIAL COMPLETION | 2019-09-17 | 2019-11-15 | 2019-09-17 | 2019-11-15
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXS711 | RECONSTRUCTION OF STEP STREET AT DAVIDSON AVE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-11-16 | 2019-12-15 | 2019-11-16 | 2026-01-19
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LN18ALELE | ALLERTON - Elevator Replacement - 3 stop | 1 | DEVELOP SCOPE | 2019-07-01 | 2019-09-28 | 2019-07-01 | 2019-09-28
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LN18ALELE | ALLERTON - Elevator Replacement - 3 stop | 2 | DESIGN | 2019-09-29 | 2020-09-27 | 2019-09-29 | 2020-09-27
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LN18ALELE | ALLERTON - Elevator Replacement - 3 stop | 3 | BID/ REGISTER CONTRACT | 2020-09-28 | 2021-06-24 | 2020-09-28 | 2021-06-24
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LN18ALELE | ALLERTON - Elevator Replacement - 3 stop | 4 | CONSTRUCTION | 2021-06-25 | 2022-06-24 | 2021-06-25 | 2022-06-24
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LN18ALELE | ALLERTON - Elevator Replacement - 3 stop | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-06-25 | 2023-06-24 | 2022-06-25 | 2023-06-24
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LN18SVBOI | SOUNDVIEW - New Boiler | 1 | DEVELOP SCOPE | 2020-07-01 | 2020-09-28 | 2020-07-01 | 2020-09-28
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LN18SVBOI | SOUNDVIEW - New Boiler | 2 | DESIGN | 2020-09-29 | 2021-09-28 | 2020-09-29 | 2021-09-28
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LN18SVBOI | SOUNDVIEW - New Boiler | 3 | BID/ REGISTER CONTRACT | 2021-09-29 | 2022-06-25 | 2021-09-29 | 2022-06-25
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LN18SVBOI | SOUNDVIEW - New Boiler | 4 | CONSTRUCTION | 2022-06-26 | 2023-06-25 | 2022-06-26 | 2023-06-25
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LN18SVBOI | SOUNDVIEW - New Boiler | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-06-26 | 2024-06-24 | 2023-06-26 | 2024-06-24
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNBXA08LS | BRONX - Life Safety Projects @ 8 Branch Libraries | 1 | PROJECT START | 2010-01-31 | 2010-01-31 | 2008-01-24 | 2008-01-24
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNBXA08LS | BRONX - Life Safety Projects @ 8 Branch Libraries | 2 | DESIGN START | 2010-02-01 | 2010-02-01 | 2014-10-13 | 2014-10-13
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNBXA08LS | BRONX - Life Safety Projects @ 8 Branch Libraries | 3 | DESIGN COMPLETION | 2010-02-02 | 2010-02-02 | 2014-10-29 | 2014-10-29
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNBXA08LS | BRONX - Life Safety Projects @ 8 Branch Libraries | 4 | CONSTRUCTION START | 2010-02-03 | 2010-02-03 | 2014-11-20 | 2014-11-20
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNBXA08LS | BRONX - Life Safety Projects @ 8 Branch Libraries | 5 | CONSTRUCTION COMPLETION | 2010-02-04 | 2010-02-04 | 2020-12-30 | 2020-12-30
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNC4WLEX | WOODLAWN - Branch Expansion | 1 | PROJECT START | 2006-08-30 | 2006-08-30 | 2012-05-23 | 2012-05-23
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNC4WLEX | WOODLAWN - Branch Expansion | 2 | DESIGN START | 2006-08-30 | 2006-08-30 | 2013-06-12 | 2013-06-12
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNC4WLEX | WOODLAWN - Branch Expansion | 3 | DESIGN COMPLETION | 2006-08-31 | 2006-08-30 | 2016-07-05 | 2016-07-05
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNC4WLEX | WOODLAWN - Branch Expansion | 4 | CONSTRUCTION START | 2006-08-31 | 2006-08-30 | 2017-12-25 | 2017-12-25
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNC4WLEX | WOODLAWN - Branch Expansion | 5 | CONSTRUCTION COMPLETION | 2006-08-31 | 2007-08-31 | 2023-01-28 | 2023-01-28
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA11BEL | BELMONT - Upper and Lower Roof | 1 | DESIGN | 2010-10-01 | 2011-03-29 | 2011-10-21 | 2011-10-21
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA11BEL | BELMONT - Upper and Lower Roof | 2 | BID AWARD AND REGISTER CONTRCT | 2011-03-30 | 2011-06-27 | 2013-04-15 | 2013-04-15
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA11BEL | BELMONT - Upper and Lower Roof | 3 | CONSTRUCTION | 2011-06-28 | 2012-06-26 | 2014-09-30 | 2014-09-30
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA11BEL | BELMONT - Upper and Lower Roof | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-06-27 | 2012-12-23 | 2015-05-20 | 2015-05-20
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA11BEL | BELMONT - Upper and Lower Roof | 5 | CONSTRUCTION COMPLETION | 2012-06-27 | 2012-12-23 | 2016-06-30 | 2020-12-30
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA11SNV | SOUNDVIEW - Interior/Exterior Renovation | 1 | DESIGN | 2010-10-01 | 2011-03-29 | 2010-10-01 | 2011-03-29
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA11SNV | SOUNDVIEW - Interior/Exterior Renovation | 2 | BID AWARD AND REGISTER CONTRCT | 2011-03-30 | 2011-06-27 | 2011-03-30 | 2011-06-27
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA11SNV | SOUNDVIEW - Interior/Exterior Renovation | 3 | CONSTRUCTION | 2011-06-28 | 2012-06-26 | 2011-06-28 | 2012-06-26
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA11SNV | SOUNDVIEW - Interior/Exterior Renovation | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-06-27 | 2012-12-23 | 2012-06-27 | 2021-06-30
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13ECH | EASTCHESTER: HVAC Replacement | 1 | PROJECT START | 2013-06-30 | 2013-06-30 | 2013-06-30 | 2013-06-30
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13ECH | EASTCHESTER: HVAC Replacement | 2 | DESIGN START | 2014-12-08 | 2014-12-08 | 2014-12-08 | 2018-06-27
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13ECH | EASTCHESTER: HVAC Replacement | 3 | DESIGN COMPLETION | 2018-06-27 | 2018-06-27 | 2018-06-27 | 2018-06-27
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13ECH | EASTCHESTER: HVAC Replacement | 4 | CONSTRUCTION START | 2019-07-15 | 2019-07-15 | 2019-07-15 | 2022-12-08
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13ECH | EASTCHESTER: HVAC Replacement | 5 | CONSTRUCTION COMPLETION | 2019-12-08 | 2019-12-08 | 2022-12-08 | 2022-12-08
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13MOR | MORRISANIA: HVAC and Roof | 1 | PROJECT START | 2013-02-27 | 2013-02-27 | 2013-02-27 | 2013-02-27
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13MOR | MORRISANIA: HVAC and Roof | 2 | DESIGN START | 2014-06-26 | 2014-06-26 | 2014-06-26 | 2014-06-26
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13MOR | MORRISANIA: HVAC and Roof | 3 | DESIGN COMPLETION | 2015-03-26 | 2015-03-26 | 2015-03-26 | 2015-03-26
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13MOR | MORRISANIA: HVAC and Roof | 4 | CONSTRUCTION START | 2015-10-23 | 2015-10-23 | 2015-10-23 | 2015-10-23
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13MOR | MORRISANIA: HVAC and Roof | 5 | CONSTRUCTION COMPLETION | 2016-07-09 | 2016-07-09 | 2016-07-09 | 2022-07-09
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13MOT | MOTT HAVEN: HVAC | 1 | PROJECT START | 2013-02-27 | 2013-02-27 | 2017-02-27 | 2017-02-27
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13MOT | MOTT HAVEN: HVAC | 2 | DESIGN START | 2014-08-06 | 2014-08-06 | 2017-02-28 | 2018-01-23
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13MOT | MOTT HAVEN: HVAC | 3 | DESIGN COMPLETION | 2015-05-01 | 2015-05-01 | 2018-01-24 | 2018-10-02
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13MOT | MOTT HAVEN: HVAC | 4 | CONSTRUCTION START | 2015-11-25 | 2015-11-25 | 2018-10-03 | 2022-10-03
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13MOT | MOTT HAVEN: HVAC | 5 | CONSTRUCTION COMPLETION | 2016-09-21 | 2016-09-21 | 2022-10-04 | 2022-10-04
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA15EDW | HVAC Replacement @ Edenwald | 1 | PROJECT START | 2014-11-24 | 2014-11-24 | 2014-11-24 | 2014-11-24
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA15EDW | HVAC Replacement @ Edenwald | 2 | DESIGN START | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA15EDW | HVAC Replacement @ Edenwald | 3 | DESIGN COMPLETION | 2016-10-07 | 2016-10-07 | 2016-10-07 | 2016-10-07
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA15EDW | HVAC Replacement @ Edenwald | 4 | CONSTRUCTION START | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA15EDW | HVAC Replacement @ Edenwald | 5 | CONSTRUCTION COMPLETION | 2018-01-07 | 2018-01-07 | 2018-01-07 | 2022-01-07
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA15MOT | Window Replacement | 1 | PROJECT START | 2014-11-24 | 2014-11-24 | 2014-11-24 | 2014-11-24
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA15MOT | Window Replacement | 2 | DESIGN START | 2014-11-25 | 2014-11-25 | 2014-11-25 | 2014-11-25
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA15MOT | Window Replacement | 3 | DESIGN COMPLETION | 2014-11-26 | 2014-11-26 | 2014-11-26 | 2014-11-26
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA15MOT | Window Replacement | 4 | CONSTRUCTION START | 2016-11-27 | 2016-11-27 | 2016-11-27 | 2016-11-27
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA15MOT | Window Replacement | 5 | CONSTRUCTION COMPLETION | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2020-12-30
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA15RSD | RIVERDALE BRANCH Exterior / Facades/ Retaining Wall / HVAC | 1 | PROJECT START | 2014-12-15 | 2014-12-15 | 2014-12-15 | 2014-12-15
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA15RSD | RIVERDALE BRANCH Exterior / Facades/ Retaining Wall / HVAC | 2 | DESIGN START | 2015-11-21 | 2015-11-21 | 2015-11-21 | 2015-11-21
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA15RSD | RIVERDALE BRANCH Exterior / Facades/ Retaining Wall / HVAC | 3 | DESIGN COMPLETION | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA15RSD | RIVERDALE BRANCH Exterior / Facades/ Retaining Wall / HVAC | 4 | CONSTRUCTION START | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA15RSD | RIVERDALE BRANCH Exterior / Facades/ Retaining Wall / HVAC | 5 | CONSTRUCTION COMPLETION | 2017-09-05 | 2017-09-05 | 2017-09-05 | 2020-09-05
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCL15CAS | CASTLE HILL: Partial Interior Renovation | 1 | PROJECT START | 2014-12-04 | 2014-12-04 | 2014-12-04 | 2014-12-04
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCL15CAS | CASTLE HILL: Partial Interior Renovation | 2 | DESIGN START | 2014-12-05 | 2014-12-05 | 2014-12-05 | 2014-12-05
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCL15CAS | CASTLE HILL: Partial Interior Renovation | 3 | DESIGN COMPLETION | 2014-12-06 | 2014-12-06 | 2014-12-06 | 2014-12-06
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCL15CAS | CASTLE HILL: Partial Interior Renovation | 4 | CONSTRUCTION START | 2014-12-07 | 2014-12-07 | 2014-12-07 | 2014-12-07
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCL15CAS | CASTLE HILL: Partial Interior Renovation | 5 | CONSTRUCTION COMPLETION | 2018-08-26 | 2018-08-26 | 2018-08-26 | 2022-08-26
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCM10WCH | WESTCHESTER SQUARE - Replacement Branch Construction | 1 | DEVELOP SCOPE | 2010-10-01 | 2010-12-29 | 2007-12-02 | 2007-12-02
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCM10WCH | WESTCHESTER SQUARE - Replacement Branch Construction | 2 | PRELIMINARY DESIGN | 2010-12-30 | 2011-04-28 | 2011-12-02 | 2011-12-02
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCM10WCH | WESTCHESTER SQUARE - Replacement Branch Construction | 3 | FINAL DESIGN | 2011-04-29 | 2011-10-25 | 2011-12-02 | 2011-12-02
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCM10WCH | WESTCHESTER SQUARE - Replacement Branch Construction | 4 | BID AWARD AND REGISTER CONTRCT | 2011-10-26 | 2012-01-23 | 2011-12-02 | 2011-12-02
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCM10WCH | WESTCHESTER SQUARE - Replacement Branch Construction | 5 | CONSTRUCTION TO 25% | 2012-01-24 | 2012-05-22 | 2011-12-02 | 2011-12-02
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCM10WCH | WESTCHESTER SQUARE - Replacement Branch Construction | 6 | CONSTRUCTION TO 50% | 2012-05-23 | 2012-09-19 | 2011-12-02 | 2011-12-02
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCM10WCH | WESTCHESTER SQUARE - Replacement Branch Construction | 7 | CONSTRUCTION TO 75% | 2012-09-20 | 2013-01-17 | 2011-12-02 | 2011-12-02
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCM10WCH | WESTCHESTER SQUARE - Replacement Branch Construction | 8 | ORIGINAL EQUIP & FURNISHING | 2013-01-18 | 2013-04-17 | 2011-12-02 | 2011-12-02
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCM10WCH | WESTCHESTER SQUARE - Replacement Branch Construction | 9 | SUBSTANTIAL COMPLETION | 2013-04-18 | 2013-06-16 | 2011-12-02 | 2011-12-02
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCM10WCH | WESTCHESTER SQUARE - Replacement Branch Construction | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-06-17 | 2013-07-16 | 2011-12-02 | 2011-12-02
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCM10WCH | WESTCHESTER SQUARE - Replacement Branch Construction | 11 | PROJECT START | 2013-06-17 | 2013-07-16 | 2011-12-02 | 2011-12-02
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCM10WCH | WESTCHESTER SQUARE - Replacement Branch Construction | 12 | DESIGN START | 2013-06-17 | 2013-07-16 | 2011-12-03 | 2013-05-12
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCM10WCH | WESTCHESTER SQUARE - Replacement Branch Construction | 13 | DESIGN COMPLETION | 2013-06-17 | 2013-07-16 | 2013-05-13 | 2018-05-29
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCM10WCH | WESTCHESTER SQUARE - Replacement Branch Construction | 14 | CONSTRUCTION START | 2013-06-17 | 2013-07-16 | 2018-05-30 | 2018-05-30
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCM10WCH | WESTCHESTER SQUARE - Replacement Branch Construction | 15 | CONSTRUCTION COMPLETION | 2013-06-17 | 2013-07-16 | 2018-05-31 | 2024-05-31
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCM12CPT | CLASON'S POINT - NEW ROOF AND DRAINS | 1 | PROJECT START | 2014-07-07 | 2014-07-07 | 2014-07-07 | 2014-07-07
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCM12CPT | CLASON'S POINT - NEW ROOF AND DRAINS | 2 | DESIGN START | 2015-04-22 | 2015-04-22 | 2015-04-22 | 2015-04-22
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCM12CPT | CLASON'S POINT - NEW ROOF AND DRAINS | 3 | DESIGN COMPLETION | 2015-08-27 | 2015-08-27 | 2015-08-27 | 2015-08-27
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCM12CPT | CLASON'S POINT - NEW ROOF AND DRAINS | 4 | CONSTRUCTION START | 2016-03-10 | 2016-03-10 | 2016-03-10 | 2016-03-10
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCM12CPT | CLASON'S POINT - NEW ROOF AND DRAINS | 5 | CONSTRUCTION COMPLETION | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2021-12-17
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNDSVRENO | SOUNDVIEW - Branch Renovation | 1 | PROJECT START | 2005-11-03 | 2005-11-03 | 2005-11-03 | 2005-11-03
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNDSVRENO | SOUNDVIEW - Branch Renovation | 2 | DESIGN START | 2005-11-04 | 2006-08-03 | 2007-09-06 | 2007-09-06
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNDSVRENO | SOUNDVIEW - Branch Renovation | 3 | DESIGN COMPLETION | 2006-08-04 | 2007-06-03 | 2008-06-27 | 2008-06-27
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNDSVRENO | SOUNDVIEW - Branch Renovation | 4 | CONSTRUCTION START | 2007-06-04 | 2007-11-03 | 2012-07-10 | 2012-07-10
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNDSVRENO | SOUNDVIEW - Branch Renovation | 5 | CONSTRUCTION COMPLETION | 2007-11-04 | 2008-08-03 | 2021-07-10 | 2021-07-10
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEA13MHU | Mosholu: New Roof and Exterior Work | 1 | PROJECT START | 2013-02-11 | 2013-02-11 | 2013-02-11 | 2013-02-11
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEA13MHU | Mosholu: New Roof and Exterior Work | 2 | DESIGN START | 2015-02-16 | 2015-02-16 | 2015-02-16 | 2015-02-16
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEA13MHU | Mosholu: New Roof and Exterior Work | 3 | DESIGN COMPLETION | 2015-07-15 | 2015-07-15 | 2015-07-15 | 2015-07-15
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEA13MHU | Mosholu: New Roof and Exterior Work | 4 | CONSTRUCTION START | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEA13MHU | Mosholu: New Roof and Exterior Work | 5 | CONSTRUCTION COMPLETION | 2016-07-01 | 2016-07-01 | 2021-12-30 | 2021-12-30
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEA13TNK | THROGS NECK: New Roof, HVAC | 1 | PROJECT START | 2013-02-04 | 2013-02-04 | 2013-02-04 | 2013-02-04
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEA13TNK | THROGS NECK: New Roof, HVAC | 2 | DESIGN START | 2015-07-15 | 2015-07-15 | 2015-07-15 | 2015-07-15
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEA13TNK | THROGS NECK: New Roof, HVAC | 3 | DESIGN COMPLETION | 2016-06-17 | 2016-06-17 | 2016-06-17 | 2016-06-17
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEA13TNK | THROGS NECK: New Roof, HVAC | 4 | CONSTRUCTION START | 2017-01-14 | 2017-01-14 | 2017-01-14 | 2017-01-14
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEA13TNK | THROGS NECK: New Roof, HVAC | 5 | CONSTRUCTION COMPLETION | 2017-11-08 | 2017-11-08 | 2020-11-08 | 2020-11-08
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEA14VNT | HVAC Replacement | 1 | PROJECT START | 2014-09-22 | 2014-09-22 | 2014-09-22 | 2014-09-22
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEA14VNT | HVAC Replacement | 2 | DESIGN START | 2015-06-10 | 2015-06-10 | 2015-06-10 | 2015-06-10
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEA14VNT | HVAC Replacement | 3 | DESIGN COMPLETION | 2015-10-15 | 2015-10-15 | 2015-10-15 | 2015-10-15
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEA14VNT | HVAC Replacement | 4 | CONSTRUCTION START | 2016-04-28 | 2016-04-28 | 2016-04-28 | 2016-04-28
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEA14VNT | HVAC Replacement | 5 | CONSTRUCTION COMPLETION | 2017-02-04 | 2017-02-04 | 2021-02-04 | 2021-02-04
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEM13EDW | EDENWALD: Fire Safety | 2 | DESIGN START | 2014-12-15 | 2014-12-15 | 2014-12-15 | 2014-12-15
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEM13EDW | EDENWALD: Fire Safety | 3 | DESIGN COMPLETION | 2015-12-11 | 2015-12-11 | 2015-12-11 | 2015-12-11
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEM13EDW | EDENWALD: Fire Safety | 4 | CONSTRUCTION START | 2016-08-28 | 2016-08-28 | 2016-08-28 | 2016-08-28
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEM13EDW | EDENWALD: Fire Safety | 5 | CONSTRUCTION COMPLETION | 2017-10-06 | 2017-10-06 | 2017-10-06 | 2017-10-06
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEM13MSH | Mosholu: Fire Safety | 5 | CONSTRUCTION COMPLETION | 2017-10-06 | 2017-10-06 | 2017-10-30 | 2017-10-30
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEM13VNE | VAN NEST: Fire Safety | 2 | DESIGN START | 2014-12-22 | 2014-12-22 | 2014-12-22 | 2014-12-22
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEM13VNE | VAN NEST: Fire Safety | 3 | DESIGN COMPLETION | 2015-12-18 | 2015-12-18 | 2015-12-18 | 2015-12-18
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEM13VNE | VAN NEST: Fire Safety | 4 | CONSTRUCTION START | 2016-09-04 | 2016-09-04 | 2016-09-04 | 2016-09-04
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEM13VNE | VAN NEST: Fire Safety | 5 | CONSTRUCTION COMPLETION | 2017-10-13 | 2017-10-13 | 2017-10-13 | 2017-10-13
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNXA11WFM | WEST FARMS - New Front Entry | 1 | DESIGN | 2010-10-01 | 2011-03-29 | 2011-01-13 | 2011-01-13
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNXA11WFM | WEST FARMS - New Front Entry | 2 | BID AWARD AND REGISTER CONTRCT | 2011-03-30 | 2011-06-27 | 2012-07-23 | 2012-07-23
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNXA11WFM | WEST FARMS - New Front Entry | 3 | CONSTRUCTION | 2011-06-28 | 2012-06-26 | 2019-05-13 | 2019-05-13
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNXA11WFM | WEST FARMS - New Front Entry | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-06-27 | 2012-12-23 | 2021-03-08 | 2021-03-08
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNXA11WFM | WEST FARMS - New Front Entry | 5 | CONSTRUCTION COMPLETION | 2012-06-27 | 2012-12-23 | 2022-01-05 | 2022-01-05
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNXA12GRC | GRAND CONCOURSE - ADA Compliance and Related Work | 1 | DEVELOP SCOPE | 2012-09-30 | 2012-12-28 | 2012-01-05 | 2012-01-05
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNXA12GRC | GRAND CONCOURSE - ADA Compliance and Related Work | 2 | PRELIMINARY DESIGN | 2012-12-29 | 2013-04-27 | 2013-04-23 | 2013-04-23
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNXA12GRC | GRAND CONCOURSE - ADA Compliance and Related Work | 3 | FINAL DESIGN | 2013-04-28 | 2013-10-24 | 2015-08-26 | 2015-08-26
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNXA12GRC | GRAND CONCOURSE - ADA Compliance and Related Work | 4 | BID AWARD AND REGISTER CONTRCT | 2013-10-25 | 2014-01-22 | 2016-04-10 | 2016-04-10
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNXA12GRC | GRAND CONCOURSE - ADA Compliance and Related Work | 5 | CONSTRUCTION TO 25% | 2014-01-23 | 2014-05-22 | 2021-05-03 | 2021-05-03
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNXA12GRC | GRAND CONCOURSE - ADA Compliance and Related Work | 6 | CONSTRUCTION TO 50% | 2014-05-23 | 2014-09-19 | 2021-05-03 | 2021-05-03
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNXA12GRC | GRAND CONCOURSE - ADA Compliance and Related Work | 7 | CONSTRUCTION TO 75% | 2014-09-20 | 2015-01-17 | 2021-05-03 | 2021-05-03
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNXA12GRC | GRAND CONCOURSE - ADA Compliance and Related Work | 8 | ORIGINAL EQUIP & FURNISHING | 2015-01-18 | 2015-04-17 | 2021-05-03 | 2021-05-03
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNXA12GRC | GRAND CONCOURSE - ADA Compliance and Related Work | 9 | SUBSTANTIAL COMPLETION | 2015-04-18 | 2015-06-16 | 2021-05-03 | 2021-05-03
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNXA12GRC | GRAND CONCOURSE - ADA Compliance and Related Work | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-06-17 | 2015-07-16 | 2021-05-03 | 2021-05-03
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNXEA08BA | BAYCHESTER: HVAC | 1 | PROJECT START | 2008-01-07 | 2008-01-07 | 2015-11-04 | 2015-11-04
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNXEA08BA | BAYCHESTER: HVAC | 2 | DESIGN START | 2009-10-20 | 2009-10-20 | 2015-11-05 | 2015-11-05
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNXEA08BA | BAYCHESTER: HVAC | 3 | DESIGN COMPLETION | 2011-10-18 | 2011-10-18 | 2015-11-06 | 2017-07-10
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNXEA08BA | BAYCHESTER: HVAC | 4 | CONSTRUCTION START | 2014-12-15 | 2014-12-15 | 2017-07-11 | 2020-07-15
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNXEA08BA | BAYCHESTER: HVAC | 5 | CONSTRUCTION COMPLETION | 2016-02-12 | 2016-02-12 | 2020-07-16 | 2026-01-03
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNXEA08CP | CLASONS POINT: HVAC | 1 | PROJECT START | 2008-01-07 | 2008-01-07 | 2008-01-07 | 2008-01-07
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNXEA08CP | CLASONS POINT: HVAC | 2 | DESIGN START | 2008-10-20 | 2008-10-20 | 2009-10-20 | 2009-10-20
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNXEA08CP | CLASONS POINT: HVAC | 3 | DESIGN COMPLETION | 2011-10-18 | 2011-10-18 | 2011-10-18 | 2011-10-18
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNXEA08CP | CLASONS POINT: HVAC | 4 | CONSTRUCTION START | 2014-12-16 | 2014-12-16 | 2019-03-22 | 2019-03-22
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNXEA08CP | CLASONS POINT: HVAC | 5 | CONSTRUCTION COMPLETION | 2016-04-04 | 2016-04-04 | 2020-07-10 | 2020-07-10
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNXEA08FN | FRANCIS MARTIN: HVAC | 1 | PROJECT START | 2008-01-07 | 2008-01-07 | 2008-01-07 | 2008-01-07
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNXEA08FN | FRANCIS MARTIN: HVAC | 2 | DESIGN START | 2009-10-20 | 2009-10-20 | 2009-10-20 | 2009-10-20
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNXEA08FN | FRANCIS MARTIN: HVAC | 3 | DESIGN COMPLETION | 2011-10-18 | 2011-10-18 | 2011-10-18 | 2011-10-18
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNXEA08FN | FRANCIS MARTIN: HVAC | 4 | CONSTRUCTION START | 2014-12-15 | 2014-12-15 | 2018-04-24 | 2018-04-24
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNXEA08FN | FRANCIS MARTIN: HVAC | 5 | CONSTRUCTION COMPLETION | 2016-04-04 | 2016-04-04 | 2021-03-15 | 2021-03-15
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-102DELV | Del Valle Square X009-111M | 1 | DEVELOP SCOPE | 2018-03-01 | 2018-05-29 | 2018-03-01 | 2018-05-29
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-102DELV | Del Valle Square X009-111M | 2 | PRELIMINARY DESIGN | 2018-05-30 | 2018-09-26 | 2018-05-30 | 2018-09-26
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-102DELV | Del Valle Square X009-111M | 3 | FINAL DESIGN | 2018-09-27 | 2019-03-25 | 2018-09-27 | 2019-03-25
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-102DELV | Del Valle Square X009-111M | 4 | BID AWARD AND REGISTER CONTRCT | 2019-03-26 | 2019-06-23 | 2019-03-26 | 2019-06-23
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-102DELV | Del Valle Square X009-111M | 5 | CONSTRUCTION TO 25% | 2019-06-24 | 2019-10-21 | 2019-06-24 | 2019-10-21
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-102DELV | Del Valle Square X009-111M | 6 | CONSTRUCTION TO 50% | 2019-10-22 | 2020-02-18 | 2019-10-22 | 2020-02-18
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-102DELV | Del Valle Square X009-111M | 7 | CONSTRUCTION TO 75% | 2020-02-19 | 2020-06-17 | 2020-02-19 | 2020-06-17
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-102DELV | Del Valle Square X009-111M | 8 | ORIGINAL EQUIP & FURNISHING | 2020-06-18 | 2020-09-15 | 2020-06-18 | 2020-09-15
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-102DELV | Del Valle Square X009-111M | 9 | SUBSTANTIAL COMPLETION | 2020-09-16 | 2020-11-14 | 2020-09-16 | 2020-11-14
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-102DELV | Del Valle Square X009-111M | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-11-15 | 2020-12-14 | 2020-11-15 | 2026-10-16
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P109STARA | STARLIGHT PARK COMFORT STATION X147-111M | 1 | PROJECT START | 2012-02-09 | 2012-02-09 | 2012-02-09 | 2013-03-26
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P109STARA | STARLIGHT PARK COMFORT STATION X147-111M | 2 | DESIGN START | 2012-02-10 | 2013-03-27 | 2013-03-27 | 2014-05-12
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P109STARA | STARLIGHT PARK COMFORT STATION X147-111M | 3 | DESIGN COMPLETION | 2013-03-28 | 2014-03-27 | 2014-05-13 | 2017-06-20
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P109STARA | STARLIGHT PARK COMFORT STATION X147-111M | 4 | CONSTRUCTION START | 2014-03-28 | 2015-10-27 | 2017-06-21 | 2019-01-20
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P109STARA | STARLIGHT PARK COMFORT STATION X147-111M | 5 | CONSTRUCTION COMPLETION | 2015-10-28 | 2015-11-30 | 2019-01-21 | 2020-09-23
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P1CROT16A | BRONX RIVER GRWAY RIVER HOUSE IN STARLIGHT PK X147-107M/407M | 1 | PROJECT START | 2011-01-19 | 2011-01-19 | 2011-01-19 | 2011-01-19
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P1CROT16A | BRONX RIVER GRWAY RIVER HOUSE IN STARLIGHT PK X147-107M/407M | 2 | DESIGN START | 2011-01-20 | 2011-11-16 | 2011-01-20 | 2011-11-16
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P1CROT16A | BRONX RIVER GRWAY RIVER HOUSE IN STARLIGHT PK X147-107M/407M | 3 | DESIGN COMPLETION | 2011-11-17 | 2013-01-04 | 2011-11-17 | 2013-01-04
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P1CROT16A | BRONX RIVER GRWAY RIVER HOUSE IN STARLIGHT PK X147-107M/407M | 4 | CONSTRUCTION START | 2013-01-05 | 2014-03-20 | 2013-01-05 | 2014-03-20
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P1CROT16A | BRONX RIVER GRWAY RIVER HOUSE IN STARLIGHT PK X147-107M/407M | 5 | CONSTRUCTION COMPLETION | 2014-03-21 | 2015-05-30 | 2014-03-21 | 2023-01-29
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-1ORCHMO | Orchard Beach M&O Facility Reconstruction | 1 | DEVELOP SCOPE | 2016-10-16 | 2017-04-13 | 2016-10-16 | 2017-04-13
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-1ORCHMO | Orchard Beach M&O Facility Reconstruction | 2 | DESIGN | 2017-04-14 | 2019-04-13 | 2017-04-14 | 2019-04-13
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-1ORCHMO | Orchard Beach M&O Facility Reconstruction | 3 | BID/ REGISTER CONTRACT | 2019-04-14 | 2020-01-08 | 2019-04-14 | 2020-01-08
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-1ORCHMO | Orchard Beach M&O Facility Reconstruction | 4 | CONSTRUCTION | 2020-01-09 | 2023-01-07 | 2020-01-09 | 2023-01-07
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-1ORCHMO | Orchard Beach M&O Facility Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-01-08 | 2024-01-07 | 2023-01-08 | 2024-01-07
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-1PBSTAR | Starlight Park Pedestrian Bridge (P-1SAND01) | 1 | DEVELOP SCOPE | 2013-07-01 | 2013-09-28 | 2016-03-01 | 2016-05-29
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-1PBSTAR | Starlight Park Pedestrian Bridge (P-1SAND01) | 2 | DESIGN | 2013-09-29 | 2013-12-27 | 2016-05-30 | 2016-09-26
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-1PBSTAR | Starlight Park Pedestrian Bridge (P-1SAND01) | 3 | BID/ REGISTER CONTRACT | 2013-12-28 | 2014-03-27 | 2016-09-27 | 2017-03-25
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-1PBSTAR | Starlight Park Pedestrian Bridge (P-1SAND01) | 4 | CONSTRUCTION | 2014-03-28 | 2015-03-27 | 2017-03-26 | 2017-06-23
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-1PBSTAR | Starlight Park Pedestrian Bridge (P-1SAND01) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2017-06-24 | 2018-02-18
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-1PBSTAR | Starlight Park Pedestrian Bridge (P-1SAND01) | 6 | CONSTRUCTION TO 50% | 2015-03-28 | 2016-03-26 | 2018-02-19 | 2018-10-16
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-1PBSTAR | Starlight Park Pedestrian Bridge (P-1SAND01) | 7 | CONSTRUCTION TO 75% | 2015-03-28 | 2016-03-26 | 2018-10-17 | 2019-06-13
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-1PBSTAR | Starlight Park Pedestrian Bridge (P-1SAND01) | 8 | ORIGINAL EQUIP & FURNISHING | 2015-03-28 | 2016-03-26 | 2019-06-14 | 2019-09-11
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-1PBSTAR | Starlight Park Pedestrian Bridge (P-1SAND01) | 9 | SUBSTANTIAL COMPLETION | 2015-03-28 | 2016-03-26 | 2019-09-12 | 2019-11-10
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-1PBSTAR | Starlight Park Pedestrian Bridge (P-1SAND01) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-28 | 2016-03-26 | 2019-11-11 | 2022-06-30
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-1STARLP | BRONX RIVER GREENWAY: STARLIGHT PARK PHASE II, STAGE 2, BX | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2014-08-26 | 2015-02-21
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-1STARLP | BRONX RIVER GREENWAY: STARLIGHT PARK PHASE II, STAGE 2, BX | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2015-02-22 | 2016-05-21
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-1STARLP | BRONX RIVER GREENWAY: STARLIGHT PARK PHASE II, STAGE 2, BX | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2016-05-22 | 2017-02-15
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-1STARLP | BRONX RIVER GREENWAY: STARLIGHT PARK PHASE II, STAGE 2, BX | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2017-02-16 | 2018-02-15
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-1STARLP | BRONX RIVER GREENWAY: STARLIGHT PARK PHASE II, STAGE 2, BX | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2018-02-16 | 2024-05-30
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-1VCPDBR | Vancortlandt Park pedestrian bridge | 1 | DEVELOP SCOPE | 2015-07-01 | 2015-09-28 | 2015-07-01 | 2015-12-27
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-1VCPDBR | Vancortlandt Park pedestrian bridge | 2 | DESIGN | 2015-09-29 | 2015-12-27 | 2015-12-28 | 2019-06-30
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-1VCPDBR | Vancortlandt Park pedestrian bridge | 3 | BID/ REGISTER CONTRACT | 2015-12-28 | 2016-03-26 | 2019-07-01 | 2023-10-04
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-1VCPDBR | Vancortlandt Park pedestrian bridge | 4 | CONSTRUCTION | 2016-03-27 | 2017-03-26 | 2023-10-05 | 2024-10-03
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-1VCPDBR | Vancortlandt Park pedestrian bridge | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-27 | 2018-03-26 | 2024-10-04 | 2025-10-03
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P1YANK15A | Bronx Children's Museum Fitout | 1 | PROJECT START | 2012-07-16 | 2012-07-16 | 2012-07-16 | 2013-04-14
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P1YANK15A | Bronx Children's Museum Fitout | 2 | DESIGN START | 2012-07-17 | 2013-04-15 | 2013-04-15 | 2015-06-17
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P1YANK15A | Bronx Children's Museum Fitout | 3 | DESIGN COMPLETION | 2013-04-16 | 2015-07-25 | 2015-06-18 | 2016-07-22
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P1YANK15A | Bronx Children's Museum Fitout | 4 | CONSTRUCTION START | 2015-07-26 | 2016-03-28 | 2016-07-23 | 2017-06-14
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P1YANK15A | Bronx Children's Museum Fitout | 5 | CONSTRUCTION COMPLETION | 2016-03-29 | 2018-11-29 | 2017-06-15 | 2018-02-09
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P1YANK15A | Bronx Children's Museum Fitout | 6 | CONSTRUCTION TO 50% | 2016-03-29 | 2018-11-29 | 2018-02-10 | 2018-10-07
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P1YANK15A | Bronx Children's Museum Fitout | 7 | CONSTRUCTION TO 75% | 2016-03-29 | 2018-11-29 | 2018-10-08 | 2019-10-07
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P1YANK15A | Bronx Children's Museum Fitout | 8 | ORIGINAL EQUIP & FURNISHING | 2016-03-29 | 2018-11-29 | 2019-10-08 | 2020-01-05
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P1YANK15A | Bronx Children's Museum Fitout | 9 | SUBSTANTIAL COMPLETION | 2016-03-29 | 2018-11-29 | 2020-01-06 | 2020-05-15
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P1YANK15A | Bronx Children's Museum Fitout | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-29 | 2018-11-29 | 2020-05-16 | 2023-12-31
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79FDBNX | BRONX FRONT DESK REPLACEMENT 42ND, 44TH, 46TH, 108TH | 1 | PROJECT START | 2018-03-01 | 2018-03-01 | 2018-03-01 | 2018-03-01
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79FDBNX | BRONX FRONT DESK REPLACEMENT 42ND, 44TH, 46TH, 108TH | 2 | DESIGN START | 2018-03-02 | 2018-03-02 | 2018-03-02 | 2018-03-02
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79FDBNX | BRONX FRONT DESK REPLACEMENT 42ND, 44TH, 46TH, 108TH | 3 | DESIGN COMPLETION | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79FDBNX | BRONX FRONT DESK REPLACEMENT 42ND, 44TH, 46TH, 108TH | 4 | CONSTRUCTION START | 2018-03-04 | 2018-03-04 | 2018-03-04 | 2018-03-04
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79FDBNX | BRONX FRONT DESK REPLACEMENT 42ND, 44TH, 46TH, 108TH | 5 | CONSTRUCTION COMPLETION | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2022-01-14
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79ROD | NEW FIREARMS TRAINING FACILITY | 1 | DESIGN | 2017-06-20 | 2017-12-16 | 2017-06-20 | 2017-07-24
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79ROD | NEW FIREARMS TRAINING FACILITY | 2 | BID AWARD AND REGISTER CONTRCT | 2017-12-17 | 2018-03-16 | 2017-07-25 | 2018-09-18
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79ROD | NEW FIREARMS TRAINING FACILITY | 3 | CONSTRUCTION | 2018-03-17 | 2019-03-16 | 2018-09-19 | 2021-04-14
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79ROD | NEW FIREARMS TRAINING FACILITY | 4 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-03-17 | 2019-09-12 | 2021-04-15 | 2022-01-09
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79ROD | NEW FIREARMS TRAINING FACILITY | 5 | CONSTRUCTION COMPLETION | 2019-03-17 | 2019-09-12 | 2022-01-10 | 2025-07-07
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PV176CESU | WCS - Bronx Zoo - Con Ed Switchgear Upgrade | 1 | PROJECT START | 2014-02-14 | 2014-02-14 | 2013-10-09 | 2013-10-09
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PV176CESU | WCS - Bronx Zoo - Con Ed Switchgear Upgrade | 2 | DESIGN START | 2014-02-15 | 2014-12-15 | 2013-10-10 | 2015-02-18
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PV176CESU | WCS - Bronx Zoo - Con Ed Switchgear Upgrade | 3 | DESIGN COMPLETION | 2014-12-16 | 2015-12-10 | 2015-02-19 | 2018-11-30
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PV176CESU | WCS - Bronx Zoo - Con Ed Switchgear Upgrade | 4 | CONSTRUCTION START | 2015-12-11 | 2016-07-01 | 2018-12-01 | 2019-06-22
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PV176CESU | WCS - Bronx Zoo - Con Ed Switchgear Upgrade | 5 | CONSTRUCTION COMPLETION | 2016-07-02 | 2017-07-12 | 2019-06-23 | 2023-07-03
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PV176ITF1 | WCS - Bronx Zoo Parking Lot Improvements | 1 | CONSTRUCTION | 2013-09-29 | 2014-09-23 | 2011-07-01 | 2011-09-28
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PV176ITF1 | WCS - Bronx Zoo Parking Lot Improvements | 2 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-09-24 | 2015-09-18 | 2011-09-29 | 2012-09-22
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PV176ITF1 | WCS - Bronx Zoo Parking Lot Improvements | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-09-24 | 2015-09-18 | 2012-09-23 | 2015-09-18
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PV176ITF1 | WCS - Bronx Zoo Parking Lot Improvements | 4 | PROJECT START | 2014-09-24 | 2015-09-18 | 2015-09-19 | 2015-09-19
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PV176ITF1 | WCS - Bronx Zoo Parking Lot Improvements | 5 | DESIGN START | 2014-09-24 | 2015-09-18 | 2015-09-20 | 2015-09-20
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PV176ITF1 | WCS - Bronx Zoo Parking Lot Improvements | 6 | DESIGN COMPLETION | 2014-09-24 | 2015-09-18 | 2015-09-21 | 2015-09-21
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PV176ITF1 | WCS - Bronx Zoo Parking Lot Improvements | 7 | CONSTRUCTION START | 2014-09-24 | 2015-09-18 | 2015-09-22 | 2015-09-22
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PV176ITF1 | WCS - Bronx Zoo Parking Lot Improvements | 8 | CONSTRUCTION COMPLETION | 2014-09-24 | 2015-09-18 | 2015-09-23 | 2024-09-23
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PV205CONS | NYBG - NY Botanical Garden - Conservatory Dome/Boiler Rep. | 1 | CONSTRUCTION | 2016-09-28 | 2017-09-22 | 2019-04-20 | 2019-10-02
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PV205CONS | NYBG - NY Botanical Garden - Conservatory Dome/Boiler Rep. | 2 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-09-23 | 2018-09-17 | 2019-10-03 | 2020-12-04
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PV205CONS | NYBG - NY Botanical Garden - Conservatory Dome/Boiler Rep. | 3 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-09-23 | 2018-09-17 | 2020-12-05 | 2021-11-29
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PV205CONS | NYBG - NY Botanical Garden - Conservatory Dome/Boiler Rep. | 4 | PROJECT START | 2017-09-23 | 2018-09-17 | 2021-11-30 | 2021-11-30
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PV205CONS | NYBG - NY Botanical Garden - Conservatory Dome/Boiler Rep. | 5 | DESIGN START | 2017-09-23 | 2018-09-17 | 2021-12-01 | 2021-12-01
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PV205CONS | NYBG - NY Botanical Garden - Conservatory Dome/Boiler Rep. | 6 | DESIGN COMPLETION | 2017-09-23 | 2018-09-17 | 2021-12-02 | 2021-12-02
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PV205CONS | NYBG - NY Botanical Garden - Conservatory Dome/Boiler Rep. | 7 | CONSTRUCTION START | 2017-09-23 | 2018-09-17 | 2021-12-03 | 2021-12-03
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PV205CONS | NYBG - NY Botanical Garden - Conservatory Dome/Boiler Rep. | 8 | CONSTRUCTION COMPLETION | 2017-09-23 | 2018-09-17 | 2021-12-04 | 2021-12-04
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PV464PRKG | WH - Wave Hill - Parking Lot Improvements | 1 | DEVELOP SCOPE | 2014-07-15 | 2014-10-12 | 2013-07-15 | 2013-10-12
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PV464PRKG | WH - Wave Hill - Parking Lot Improvements | 2 | PRELIMINARY DESIGN | 2014-10-13 | 2015-02-09 | 2013-10-13 | 2014-02-09
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PV464PRKG | WH - Wave Hill - Parking Lot Improvements | 3 | FINAL DESIGN | 2015-02-10 | 2015-08-08 | 2014-02-10 | 2014-08-08
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PV464PRKG | WH - Wave Hill - Parking Lot Improvements | 4 | BID AWARD AND REGISTER CONTRCT | 2015-08-09 | 2015-11-06 | 2014-08-09 | 2014-11-06
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PV464PRKG | WH - Wave Hill - Parking Lot Improvements | 5 | CONSTRUCTION TO 25% | 2015-11-07 | 2016-03-05 | 2014-11-07 | 2015-03-06
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PV464PRKG | WH - Wave Hill - Parking Lot Improvements | 6 | CONSTRUCTION TO 50% | 2016-03-06 | 2016-07-03 | 2015-03-07 | 2015-07-04
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PV464PRKG | WH - Wave Hill - Parking Lot Improvements | 7 | CONSTRUCTION TO 75% | 2016-07-04 | 2016-10-31 | 2015-07-05 | 2015-11-01
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PV464PRKG | WH - Wave Hill - Parking Lot Improvements | 8 | ORIGINAL EQUIP & FURNISHING | 2016-11-01 | 2017-01-29 | 2015-11-02 | 2016-01-30
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PV464PRKG | WH - Wave Hill - Parking Lot Improvements | 9 | SUBSTANTIAL COMPLETION | 2017-01-30 | 2017-03-30 | 2016-01-31 | 2016-03-30
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PV464PRKG | WH - Wave Hill - Parking Lot Improvements | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2017-03-31 | 2017-04-29 | 2016-03-31 | 2016-04-29
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PV464PRKG | WH - Wave Hill - Parking Lot Improvements | 11 | PROJECT START | 2017-03-31 | 2017-04-29 | 2016-04-30 | 2016-04-30
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PV464PRKG | WH - Wave Hill - Parking Lot Improvements | 12 | DESIGN START | 2017-03-31 | 2017-04-29 | 2016-05-01 | 2016-05-01
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PV464PRKG | WH - Wave Hill - Parking Lot Improvements | 13 | DESIGN COMPLETION | 2017-03-31 | 2017-04-29 | 2016-05-02 | 2016-05-02
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PV464PRKG | WH - Wave Hill - Parking Lot Improvements | 14 | CONSTRUCTION START | 2017-03-31 | 2017-04-29 | 2016-05-03 | 2016-05-03
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PV464PRKG | WH - Wave Hill - Parking Lot Improvements | 15 | CONSTRUCTION COMPLETION | 2017-03-31 | 2017-04-29 | 2016-05-04 | 2022-05-04
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77207C6 | 1932 ARTHUR AVE. RELOCATION OF CB # 6 WITHIN BLDG | 2 | PRELIMINARY DESIGN | 2012-08-30 | 2012-12-27 | 2012-08-30 | 2012-12-27
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77207C6 | 1932 ARTHUR AVE. RELOCATION OF CB # 6 WITHIN BLDG | 3 | FINAL DESIGN | 2012-12-28 | 2013-06-25 | 2012-12-28 | 2013-06-25
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77207C6 | 1932 ARTHUR AVE. RELOCATION OF CB # 6 WITHIN BLDG | 4 | BID AWARD AND REGISTER CONTRCT | 2013-06-26 | 2013-09-23 | 2013-06-26 | 2013-09-23
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77207C6 | 1932 ARTHUR AVE. RELOCATION OF CB # 6 WITHIN BLDG | 5 | CONSTRUCTION TO 25% | 2013-09-24 | 2014-01-21 | 2013-09-24 | 2014-01-21
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77207C6 | 1932 ARTHUR AVE. RELOCATION OF CB # 6 WITHIN BLDG | 6 | CONSTRUCTION TO 50% | 2014-01-22 | 2014-05-21 | 2014-01-22 | 2014-05-21
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77207C6 | 1932 ARTHUR AVE. RELOCATION OF CB # 6 WITHIN BLDG | 7 | CONSTRUCTION TO 75% | 2014-05-22 | 2014-09-18 | 2014-05-22 | 2014-09-18
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77207C6 | 1932 ARTHUR AVE. RELOCATION OF CB # 6 WITHIN BLDG | 8 | ORIGINAL EQUIP & FURNISHING | 2014-09-19 | 2014-12-17 | 2014-09-19 | 2014-12-17
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77207C6 | 1932 ARTHUR AVE. RELOCATION OF CB # 6 WITHIN BLDG | 9 | SUBSTANTIAL COMPLETION | 2014-12-18 | 2015-02-15 | 2014-12-18 | 2015-02-15
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77207C6 | 1932 ARTHUR AVE. RELOCATION OF CB # 6 WITHIN BLDG | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-02-16 | 2015-03-17 | 2015-02-16 | 2015-03-17
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PWD05TH1 | THROGS NECK LITTLE LEAGUE BALLFIELD RENOVATION LIGHTING | 1 | PROJECT START | 2018-03-15 | 2018-03-15 | 2018-03-15 | 2018-03-15
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PWD05TH1 | THROGS NECK LITTLE LEAGUE BALLFIELD RENOVATION LIGHTING | 2 | DESIGN START | 2018-03-16 | 2018-09-06 | 2018-03-16 | 2018-09-06
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PWD05TH1 | THROGS NECK LITTLE LEAGUE BALLFIELD RENOVATION LIGHTING | 3 | DESIGN COMPLETION | 2018-09-07 | 2019-03-07 | 2018-09-07 | 2019-03-07
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PWD05TH1 | THROGS NECK LITTLE LEAGUE BALLFIELD RENOVATION LIGHTING | 4 | CONSTRUCTION START | 2019-03-08 | 2019-09-08 | 2019-03-08 | 2019-09-08
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PWD05TH1 | THROGS NECK LITTLE LEAGUE BALLFIELD RENOVATION LIGHTING | 5 | CONSTRUCTION COMPLETION | 2019-09-09 | 2019-09-09 | 2019-09-09 | 2019-09-09
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PWX78BXP | BRONX BOROUGH PRESIDENT'S OFFICE INITIAL OUT-FITTING | 1 | PROJECT START | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PWX78BXP | BRONX BOROUGH PRESIDENT'S OFFICE INITIAL OUT-FITTING | 2 | DESIGN START | 2016-07-01 | 2016-09-30 | 2016-07-01 | 2016-09-30
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PWX78BXP | BRONX BOROUGH PRESIDENT'S OFFICE INITIAL OUT-FITTING | 3 | DESIGN COMPLETION | 2016-10-01 | 2017-04-30 | 2016-10-01 | 2017-04-30
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PWX78BXP | BRONX BOROUGH PRESIDENT'S OFFICE INITIAL OUT-FITTING | 4 | CONSTRUCTION START | 2017-05-01 | 2017-10-30 | 2017-05-01 | 2017-10-30
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PWX78BXP | BRONX BOROUGH PRESIDENT'S OFFICE INITIAL OUT-FITTING | 5 | CONSTRUCTION COMPLETION | 2017-10-31 | 2023-10-31 | 2017-10-31 | 2023-10-31
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PWXTNLLRE | Throgs Neck Little League- Infrastructure Rehabilitation | 1 | PROJECT START | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2017-06-30
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PWXTNLLRE | Throgs Neck Little League- Infrastructure Rehabilitation | 2 | DESIGN START | 2016-07-01 | 2016-10-15 | 2017-07-01 | 2018-07-02
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PWXTNLLRE | Throgs Neck Little League- Infrastructure Rehabilitation | 3 | DESIGN COMPLETION | 2016-10-16 | 2017-02-28 | 2018-07-03 | 2019-08-15
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PWXTNLLRE | Throgs Neck Little League- Infrastructure Rehabilitation | 4 | CONSTRUCTION START | 2017-03-01 | 2017-08-15 | 2019-08-16 | 2020-01-30
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PWXTNLLRE | Throgs Neck Little League- Infrastructure Rehabilitation | 5 | CONSTRUCTION COMPLETION | 2017-08-16 | 2024-08-16 | 2020-01-31 | 2027-01-31
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | REG-HP06 | RECONSTRUCTION OF REGULATOR HP-06 | 1 | DEVELOP SCOPE | 2023-06-01 | 2024-02-25 | 2023-06-01 | 2024-02-25
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBOMB | Reconstruct Hurricane Sandy Damaged Bomb Sq bldg | 1 | DEVELOP SCOPE | 2013-06-30 | 2013-09-27 | 2016-08-31 | 2016-11-28
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBOMB | Reconstruct Hurricane Sandy Damaged Bomb Sq bldg | 2 | PRELIMINARY DESIGN | 2013-09-28 | 2014-01-25 | 2016-11-29 | 2017-03-28
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBOMB | Reconstruct Hurricane Sandy Damaged Bomb Sq bldg | 3 | FINAL DESIGN | 2014-01-26 | 2014-07-24 | 2017-03-29 | 2017-09-24
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBOMB | Reconstruct Hurricane Sandy Damaged Bomb Sq bldg | 4 | BID AWARD AND REGISTER CONTRCT | 2014-07-25 | 2014-10-22 | 2017-09-25 | 2017-12-23
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBOMB | Reconstruct Hurricane Sandy Damaged Bomb Sq bldg | 5 | CONSTRUCTION TO 25% | 2014-10-23 | 2015-02-19 | 2017-12-24 | 2018-04-22
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBOMB | Reconstruct Hurricane Sandy Damaged Bomb Sq bldg | 6 | CONSTRUCTION TO 50% | 2015-02-20 | 2015-06-19 | 2018-04-23 | 2018-08-20
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBOMB | Reconstruct Hurricane Sandy Damaged Bomb Sq bldg | 7 | CONSTRUCTION TO 75% | 2015-06-20 | 2015-10-17 | 2018-08-21 | 2018-12-18
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBOMB | Reconstruct Hurricane Sandy Damaged Bomb Sq bldg | 8 | ORIGINAL EQUIP & FURNISHING | 2015-10-18 | 2016-01-15 | 2018-12-19 | 2019-03-18
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBOMB | Reconstruct Hurricane Sandy Damaged Bomb Sq bldg | 9 | SUBSTANTIAL COMPLETION | 2016-01-16 | 2016-03-15 | 2019-03-19 | 2019-05-17
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBOMB | Reconstruct Hurricane Sandy Damaged Bomb Sq bldg | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2016-03-16 | 2016-04-14 | 2019-05-18 | 2019-09-01
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBOMB | Reconstruct Hurricane Sandy Damaged Bomb Sq bldg | 11 | PROJECT START | 2016-03-16 | 2016-04-14 | 2013-04-30 | 2013-05-01
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBOMB | Reconstruct Hurricane Sandy Damaged Bomb Sq bldg | 12 | DESIGN START | 2016-03-16 | 2016-04-14 | 2013-05-02 | 2014-04-15
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBOMB | Reconstruct Hurricane Sandy Damaged Bomb Sq bldg | 13 | DESIGN COMPLETION | 2016-03-16 | 2016-04-14 | 2014-04-16 | 2017-06-30
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBOMB | Reconstruct Hurricane Sandy Damaged Bomb Sq bldg | 14 | CONSTRUCTION START | 2016-03-16 | 2016-04-14 | 2017-07-01 | 2017-12-11
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBOMB | Reconstruct Hurricane Sandy Damaged Bomb Sq bldg | 15 | CONSTRUCTION COMPLETION | 2016-03-16 | 2016-04-14 | 2017-12-12 | 2022-03-28
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBULK2 | Reconstruction of Vincent Ave Bulkhead - Hurricane Sandy | 1 | DEVELOP SCOPE | 2016-06-30 | 2016-09-27 | 2021-06-30 | 2021-09-27
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBULK2 | Reconstruction of Vincent Ave Bulkhead - Hurricane Sandy | 2 | PRELIMINARY DESIGN | 2016-09-28 | 2017-01-25 | 2021-09-28 | 2022-01-25
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBULK2 | Reconstruction of Vincent Ave Bulkhead - Hurricane Sandy | 3 | FINAL DESIGN | 2017-01-26 | 2017-07-24 | 2022-01-26 | 2022-07-24
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBULK2 | Reconstruction of Vincent Ave Bulkhead - Hurricane Sandy | 4 | BID AWARD AND REGISTER CONTRCT | 2017-07-25 | 2017-10-22 | 2022-07-25 | 2022-10-22
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBULK2 | Reconstruction of Vincent Ave Bulkhead - Hurricane Sandy | 5 | CONSTRUCTION TO 25% | 2017-10-23 | 2018-02-19 | 2022-10-23 | 2023-02-19
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBULK2 | Reconstruction of Vincent Ave Bulkhead - Hurricane Sandy | 6 | CONSTRUCTION TO 50% | 2018-02-20 | 2018-06-19 | 2023-02-20 | 2023-06-19
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBULK2 | Reconstruction of Vincent Ave Bulkhead - Hurricane Sandy | 7 | CONSTRUCTION TO 75% | 2018-06-20 | 2018-10-17 | 2023-06-20 | 2023-10-17
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBULK2 | Reconstruction of Vincent Ave Bulkhead - Hurricane Sandy | 8 | ORIGINAL EQUIP & FURNISHING | 2018-10-18 | 2019-01-15 | 2023-10-18 | 2024-01-15
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBULK2 | Reconstruction of Vincent Ave Bulkhead - Hurricane Sandy | 9 | SUBSTANTIAL COMPLETION | 2019-01-16 | 2019-03-16 | 2024-01-16 | 2024-03-15
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBULK2 | Reconstruction of Vincent Ave Bulkhead - Hurricane Sandy | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-03-17 | 2019-04-15 | 2024-03-16 | 2024-04-14
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX002266 | Repl & Rehab of Combined swrs 171 to 175 sts, bx | 1 | DEVELOP SCOPE | 2016-03-01 | 2016-05-29 | 2016-03-01 | 2016-05-29
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX002266 | Repl & Rehab of Combined swrs 171 to 175 sts, bx | 2 | PRELIMINARY DESIGN | 2016-05-30 | 2016-09-26 | 2016-05-30 | 2016-09-26
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX002266 | Repl & Rehab of Combined swrs 171 to 175 sts, bx | 3 | FINAL DESIGN | 2016-09-27 | 2017-03-25 | 2016-09-27 | 2017-03-25
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX002266 | Repl & Rehab of Combined swrs 171 to 175 sts, bx | 4 | BID AWARD AND REGISTER CONTRCT | 2017-03-26 | 2017-06-23 | 2017-03-26 | 2017-06-23
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX002266 | Repl & Rehab of Combined swrs 171 to 175 sts, bx | 5 | CONSTRUCTION TO 25% | 2017-06-24 | 2017-10-21 | 2017-06-24 | 2017-10-21
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX002266 | Repl & Rehab of Combined swrs 171 to 175 sts, bx | 6 | CONSTRUCTION TO 50% | 2017-10-22 | 2018-02-18 | 2017-10-22 | 2018-02-18
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX002266 | Repl & Rehab of Combined swrs 171 to 175 sts, bx | 7 | CONSTRUCTION TO 75% | 2018-02-19 | 2018-06-18 | 2018-02-19 | 2018-06-18
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX002266 | Repl & Rehab of Combined swrs 171 to 175 sts, bx | 8 | ORIGINAL EQUIP & FURNISHING | 2018-06-19 | 2018-09-16 | 2018-06-19 | 2018-09-16
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX002266 | Repl & Rehab of Combined swrs 171 to 175 sts, bx | 9 | SUBSTANTIAL COMPLETION | 2018-09-17 | 2018-11-15 | 2018-09-17 | 2018-11-15
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX002266 | Repl & Rehab of Combined swrs 171 to 175 sts, bx | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2018-11-16 | 2018-12-15 | 2018-11-16 | 2021-06-30
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX002268 | Reconstruction of Grand Concourse - Phase 4 (HWXP136C) | 1 | DEVELOP SCOPE | 2017-03-01 | 2017-05-29 | 2017-03-01 | 2017-05-29
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX002268 | Reconstruction of Grand Concourse - Phase 4 (HWXP136C) | 2 | PRELIMINARY DESIGN | 2017-05-30 | 2017-09-26 | 2017-05-30 | 2017-09-26
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX002268 | Reconstruction of Grand Concourse - Phase 4 (HWXP136C) | 3 | FINAL DESIGN | 2017-09-27 | 2018-03-25 | 2017-09-27 | 2018-03-25
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX002268 | Reconstruction of Grand Concourse - Phase 4 (HWXP136C) | 4 | BID AWARD AND REGISTER CONTRCT | 2018-03-26 | 2018-06-23 | 2018-03-26 | 2018-06-23
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX002268 | Reconstruction of Grand Concourse - Phase 4 (HWXP136C) | 5 | CONSTRUCTION TO 25% | 2018-06-24 | 2018-10-21 | 2018-06-24 | 2018-10-21
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX002268 | Reconstruction of Grand Concourse - Phase 4 (HWXP136C) | 6 | CONSTRUCTION TO 50% | 2018-10-22 | 2019-02-18 | 2018-10-22 | 2019-02-18
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX002268 | Reconstruction of Grand Concourse - Phase 4 (HWXP136C) | 7 | CONSTRUCTION TO 75% | 2019-02-19 | 2019-06-18 | 2019-02-19 | 2019-06-18
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX002268 | Reconstruction of Grand Concourse - Phase 4 (HWXP136C) | 8 | ORIGINAL EQUIP & FURNISHING | 2019-06-19 | 2019-09-16 | 2019-06-19 | 2019-09-16
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX002268 | Reconstruction of Grand Concourse - Phase 4 (HWXP136C) | 9 | SUBSTANTIAL COMPLETION | 2019-09-17 | 2019-11-15 | 2019-09-17 | 2019-11-15
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX002268 | Reconstruction of Grand Concourse - Phase 4 (HWXP136C) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-11-16 | 2019-12-15 | 2019-11-16 | 2022-06-22
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX002271 | Upgrade combined sewer Franklin ave- other Locs HWTRQX1 | 1 | DEVELOP SCOPE | 2018-05-01 | 2018-07-29 | 2018-05-01 | 2018-07-29
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX002271 | Upgrade combined sewer Franklin ave- other Locs HWTRQX1 | 2 | PRELIMINARY DESIGN | 2018-07-30 | 2018-11-26 | 2018-07-30 | 2018-11-26
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX002271 | Upgrade combined sewer Franklin ave- other Locs HWTRQX1 | 3 | FINAL DESIGN | 2018-11-27 | 2019-05-25 | 2018-11-27 | 2019-05-25
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX002271 | Upgrade combined sewer Franklin ave- other Locs HWTRQX1 | 4 | BID AWARD AND REGISTER CONTRCT | 2019-05-26 | 2019-08-23 | 2019-05-26 | 2019-08-23
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX002271 | Upgrade combined sewer Franklin ave- other Locs HWTRQX1 | 5 | CONSTRUCTION TO 25% | 2019-08-24 | 2019-12-21 | 2019-08-24 | 2019-12-21
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX002271 | Upgrade combined sewer Franklin ave- other Locs HWTRQX1 | 6 | CONSTRUCTION TO 50% | 2019-12-22 | 2020-04-19 | 2019-12-22 | 2020-04-19
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX002271 | Upgrade combined sewer Franklin ave- other Locs HWTRQX1 | 7 | CONSTRUCTION TO 75% | 2020-04-20 | 2020-08-17 | 2020-04-20 | 2020-08-17
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX002271 | Upgrade combined sewer Franklin ave- other Locs HWTRQX1 | 8 | ORIGINAL EQUIP & FURNISHING | 2020-08-18 | 2020-11-15 | 2020-08-18 | 2020-11-15
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX002271 | Upgrade combined sewer Franklin ave- other Locs HWTRQX1 | 9 | SUBSTANTIAL COMPLETION | 2020-11-16 | 2021-01-14 | 2020-11-16 | 2021-01-14
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX002271 | Upgrade combined sewer Franklin ave- other Locs HWTRQX1 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-01-15 | 2021-02-13 | 2021-01-15 | 2022-06-30
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX200400 | STORM & SAN SEWERS REPL & EXT IN MININIEFORD AVE AREA | 1 | DEVELOP SCOPE | 2012-06-30 | 2012-09-27 | 2009-05-29 | 2009-08-26
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX200400 | STORM & SAN SEWERS REPL & EXT IN MININIEFORD AVE AREA | 2 | PRELIMINARY DESIGN | 2012-09-28 | 2013-01-25 | 2008-12-25 | 2009-12-24
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX200400 | STORM & SAN SEWERS REPL & EXT IN MININIEFORD AVE AREA | 3 | FINAL DESIGN | 2013-01-26 | 2013-07-24 | 2009-12-25 | 2017-03-08
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX200400 | STORM & SAN SEWERS REPL & EXT IN MININIEFORD AVE AREA | 4 | BID AWARD AND REGISTER CONTRCT | 2013-07-25 | 2013-10-22 | 2017-03-09 | 2017-06-06
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX200400 | STORM & SAN SEWERS REPL & EXT IN MININIEFORD AVE AREA | 5 | CONSTRUCTION TO 25% | 2013-10-23 | 2014-02-19 | 2017-06-07 | 2017-12-03
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX200400 | STORM & SAN SEWERS REPL & EXT IN MININIEFORD AVE AREA | 6 | CONSTRUCTION TO 50% | 2014-02-20 | 2014-06-19 | 2017-12-04 | 2018-12-03
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX200400 | STORM & SAN SEWERS REPL & EXT IN MININIEFORD AVE AREA | 7 | CONSTRUCTION TO 75% | 2014-06-20 | 2014-10-17 | 2018-12-04 | 2019-06-01
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX200400 | STORM & SAN SEWERS REPL & EXT IN MININIEFORD AVE AREA | 8 | ORIGINAL EQUIP & FURNISHING | 2014-10-18 | 2015-01-15 | 2019-06-02 | 2019-08-30
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX200400 | STORM & SAN SEWERS REPL & EXT IN MININIEFORD AVE AREA | 9 | SUBSTANTIAL COMPLETION | 2015-01-16 | 2015-03-16 | 2019-08-31 | 2019-10-29
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX200400 | STORM & SAN SEWERS REPL & EXT IN MININIEFORD AVE AREA | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-17 | 2015-04-15 | 2019-10-30 | 2025-03-10
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX20042 | STRM SWR IN WILLIAM AVE B/T DITMARS ST AND TIER ST | 1 | DEVELOP SCOPE | 2010-03-05 | 2010-06-02 | 2010-03-05 | 2010-06-02
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX20042 | STRM SWR IN WILLIAM AVE B/T DITMARS ST AND TIER ST | 2 | PRELIMINARY DESIGN | 2010-06-03 | 2010-09-30 | 2009-10-01 | 2010-09-30
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX20042 | STRM SWR IN WILLIAM AVE B/T DITMARS ST AND TIER ST | 3 | FINAL DESIGN | 2010-10-01 | 2011-03-29 | 2010-10-01 | 2016-03-08
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX20042 | STRM SWR IN WILLIAM AVE B/T DITMARS ST AND TIER ST | 4 | BID AWARD AND REGISTER CONTRCT | 2011-03-30 | 2011-06-27 | 2016-03-09 | 2016-06-06
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX20042 | STRM SWR IN WILLIAM AVE B/T DITMARS ST AND TIER ST | 5 | CONSTRUCTION TO 25% | 2011-06-28 | 2011-10-25 | 2016-06-07 | 2016-12-03
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX20042 | STRM SWR IN WILLIAM AVE B/T DITMARS ST AND TIER ST | 6 | CONSTRUCTION TO 50% | 2011-10-26 | 2012-02-22 | 2016-12-04 | 2017-06-01
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX20042 | STRM SWR IN WILLIAM AVE B/T DITMARS ST AND TIER ST | 7 | CONSTRUCTION TO 75% | 2012-02-23 | 2012-06-21 | 2017-06-02 | 2017-11-28
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX20042 | STRM SWR IN WILLIAM AVE B/T DITMARS ST AND TIER ST | 8 | ORIGINAL EQUIP & FURNISHING | 2012-06-22 | 2012-09-19 | 2017-11-29 | 2018-02-26
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX20042 | STRM SWR IN WILLIAM AVE B/T DITMARS ST AND TIER ST | 9 | SUBSTANTIAL COMPLETION | 2012-09-20 | 2012-11-18 | 2018-02-27 | 2018-04-27
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX20042 | STRM SWR IN WILLIAM AVE B/T DITMARS ST AND TIER ST | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2012-11-19 | 2012-12-18 | 2018-04-28 | 2020-06-30
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX20047 | Replacement of combined sewer in Burr Ave | 1 | DEVELOP SCOPE | 2018-03-01 | 2018-11-30 | 2018-03-01 | 2018-11-30
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX20047 | Replacement of combined sewer in Burr Ave | 2 | PRELIMINARY DESIGN | 2018-12-01 | 2019-03-30 | 2018-12-01 | 2019-03-30
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX20047 | Replacement of combined sewer in Burr Ave | 3 | FINAL DESIGN | 2019-03-31 | 2019-09-26 | 2019-03-31 | 2019-09-26
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX20047 | Replacement of combined sewer in Burr Ave | 4 | BID AWARD AND REGISTER CONTRCT | 2019-09-27 | 2019-12-25 | 2019-09-27 | 2019-12-25
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX20047 | Replacement of combined sewer in Burr Ave | 5 | CONSTRUCTION TO 25% | 2019-12-26 | 2020-04-23 | 2019-12-26 | 2020-04-23
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX20047 | Replacement of combined sewer in Burr Ave | 6 | CONSTRUCTION TO 50% | 2020-04-24 | 2020-08-21 | 2020-04-24 | 2020-08-21
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX20047 | Replacement of combined sewer in Burr Ave | 7 | CONSTRUCTION TO 75% | 2020-08-22 | 2020-12-19 | 2020-08-22 | 2020-12-19
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX20047 | Replacement of combined sewer in Burr Ave | 8 | ORIGINAL EQUIP & FURNISHING | 2020-12-20 | 2021-03-19 | 2020-12-20 | 2021-03-19
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX20047 | Replacement of combined sewer in Burr Ave | 9 | SUBSTANTIAL COMPLETION | 2021-03-20 | 2021-05-18 | 2021-03-20 | 2021-05-18
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX20047 | Replacement of combined sewer in Burr Ave | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-05-19 | 2021-06-17 | 2021-05-19 | 2021-06-17
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX20049 | Replacing deteriorating retain wall along Pratt Ave in BX | 1 | DEVELOP SCOPE | 2019-12-09 | 2020-03-07 | 2019-12-09 | 2020-03-07
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX20049 | Replacing deteriorating retain wall along Pratt Ave in BX | 2 | PRELIMINARY DESIGN | 2020-03-08 | 2020-07-05 | 2020-03-08 | 2020-07-05
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX20049 | Replacing deteriorating retain wall along Pratt Ave in BX | 3 | FINAL DESIGN | 2020-07-06 | 2021-01-01 | 2020-07-06 | 2021-01-01
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX20049 | Replacing deteriorating retain wall along Pratt Ave in BX | 4 | BID AWARD AND REGISTER CONTRCT | 2021-01-02 | 2021-04-01 | 2021-01-02 | 2021-04-01
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX20049 | Replacing deteriorating retain wall along Pratt Ave in BX | 5 | CONSTRUCTION TO 25% | 2021-04-02 | 2021-07-30 | 2021-04-02 | 2021-07-30
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX20049 | Replacing deteriorating retain wall along Pratt Ave in BX | 6 | CONSTRUCTION TO 50% | 2021-07-31 | 2021-11-27 | 2021-07-31 | 2021-11-27
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX20049 | Replacing deteriorating retain wall along Pratt Ave in BX | 7 | CONSTRUCTION TO 75% | 2021-11-28 | 2022-03-27 | 2021-11-28 | 2022-03-27
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX20049 | Replacing deteriorating retain wall along Pratt Ave in BX | 8 | ORIGINAL EQUIP & FURNISHING | 2022-03-28 | 2022-06-25 | 2022-03-28 | 2022-06-25
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX20049 | Replacing deteriorating retain wall along Pratt Ave in BX | 9 | SUBSTANTIAL COMPLETION | 2022-06-26 | 2022-08-24 | 2022-06-26 | 2022-08-24
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX20049 | Replacing deteriorating retain wall along Pratt Ave in BX | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-08-25 | 2022-09-23 | 2022-08-25 | 2022-09-23
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX-SURV4 | SURVEYS FOR SEWERS IN BRONX | 1 | DEVELOP SCOPE | 2012-03-01 | 2012-05-29 | 2012-03-01 | 2012-05-29
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX-SURV4 | SURVEYS FOR SEWERS IN BRONX | 2 | PRELIMINARY DESIGN | 2012-05-30 | 2012-09-26 | 2012-05-30 | 2012-09-26
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX-SURV4 | SURVEYS FOR SEWERS IN BRONX | 3 | FINAL DESIGN | 2012-09-27 | 2013-03-25 | 2012-09-27 | 2013-03-25
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX-SURV4 | SURVEYS FOR SEWERS IN BRONX | 4 | BID AWARD AND REGISTER CONTRCT | 2013-03-26 | 2013-06-23 | 2013-03-26 | 2013-06-23
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX-SURV4 | SURVEYS FOR SEWERS IN BRONX | 5 | CONSTRUCTION TO 25% | 2013-06-24 | 2013-10-21 | 2013-06-24 | 2013-10-21
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX-SURV4 | SURVEYS FOR SEWERS IN BRONX | 6 | CONSTRUCTION TO 50% | 2013-10-22 | 2014-02-18 | 2013-10-22 | 2014-02-18
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX-SURV4 | SURVEYS FOR SEWERS IN BRONX | 7 | CONSTRUCTION TO 75% | 2014-02-19 | 2014-06-18 | 2014-02-19 | 2014-06-18
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX-SURV4 | SURVEYS FOR SEWERS IN BRONX | 8 | ORIGINAL EQUIP & FURNISHING | 2014-06-19 | 2014-09-16 | 2014-06-19 | 2014-09-16
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX-SURV4 | SURVEYS FOR SEWERS IN BRONX | 9 | SUBSTANTIAL COMPLETION | 2014-09-17 | 2014-11-15 | 2014-09-17 | 2014-11-15
20201123 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX-SURV4 | SURVEYS FOR SEWERS IN BRONX | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2014-11-16 | 2020-06-30 | 2014-11-16 | 2021-06-30
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOE703 | DOE - STEAM TRAPS | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-06-30 | 2020-06-01 | 2020-06-30
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOE703 | DOE - STEAM TRAPS | 2 | BID AWARD AND REGISTER CONTRCT | 2020-07-01 | 2020-08-29 | 2020-07-01 | 2020-08-29
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOE703 | DOE - STEAM TRAPS | 3 | CONSTRUCTION TO 50% | 2020-08-30 | 2021-02-25 | 2020-08-30 | 2021-02-25
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOE703 | DOE - STEAM TRAPS | 4 | CONSTRUCTION TO 75% | 2021-02-26 | 2021-05-26 | 2021-02-26 | 2021-05-26
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOE703 | DOE - STEAM TRAPS | 5 | SUBSTANTIAL COMPLETION | 2021-05-27 | 2021-07-25 | 2021-05-27 | 2021-07-25
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOE703 | DOE - STEAM TRAPS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-07-26 | 2021-08-24 | 2021-07-26 | 2021-08-24
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEHHC901 | HHC - Energy Upgrades at Lincoln Hospital Phase 2 | 1 | DEVELOP SCOPE | 2021-03-01 | 2021-03-30 | 2021-03-01 | 2021-03-30
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEHHC901 | HHC - Energy Upgrades at Lincoln Hospital Phase 2 | 2 | BID AWARD AND REGISTER CONTRCT | 2021-03-31 | 2021-05-29 | 2021-03-31 | 2021-05-29
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEHHC901 | HHC - Energy Upgrades at Lincoln Hospital Phase 2 | 3 | CONSTRUCTION TO 50% | 2021-05-30 | 2021-11-25 | 2021-05-30 | 2021-11-25
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEHHC901 | HHC - Energy Upgrades at Lincoln Hospital Phase 2 | 4 | CONSTRUCTION TO 75% | 2021-11-26 | 2022-02-23 | 2021-11-26 | 2022-02-23
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEHHC901 | HHC - Energy Upgrades at Lincoln Hospital Phase 2 | 5 | SUBSTANTIAL COMPLETION | 2022-02-24 | 2022-04-24 | 2022-02-24 | 2022-04-24
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEHHC901 | HHC - Energy Upgrades at Lincoln Hospital Phase 2 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-04-25 | 2022-05-24 | 2022-04-25 | 2022-05-24
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | C75TURB | REPLACEMENT OF CO-GENERATION PLANT TURBINES | 1 | DESIGN | 2019-06-30 | 2019-12-30 | 2019-06-30 | 2019-12-30
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | C75TURB | REPLACEMENT OF CO-GENERATION PLANT TURBINES | 2 | BID AWARD AND REGISTER CONTRCT | 2019-12-31 | 2020-12-29 | 2019-12-31 | 2020-12-29
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | C75TURB | REPLACEMENT OF CO-GENERATION PLANT TURBINES | 3 | CONSTRUCTION TO 75% | 2020-12-30 | 2023-12-31 | 2020-12-30 | 2023-12-31
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | C75TURB | REPLACEMENT OF CO-GENERATION PLANT TURBINES | 4 | SUBSTANTIAL COMPLETION | 2024-01-01 | 2023-12-31 | 2024-01-01 | 2023-12-31
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | C75TURB | REPLACEMENT OF CO-GENERATION PLANT TURBINES | 5 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-01-01 | 2024-05-25 | 2024-01-01 | 2024-05-25
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293201A | DASNY - 851 GRAND CONCOURSE- RENOVATIONS | 1 | DEVELOP SCOPE | 2006-08-01 | 2006-10-29 | 2006-08-01 | 2006-10-29
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293201A | DASNY - 851 GRAND CONCOURSE- RENOVATIONS | 2 | PRELIMINARY DESIGN | 2006-10-30 | 2007-02-26 | 2006-10-30 | 2007-02-26
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293201A | DASNY - 851 GRAND CONCOURSE- RENOVATIONS | 3 | FINAL DESIGN | 2007-02-27 | 2007-08-25 | 2007-02-27 | 2007-08-25
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293201A | DASNY - 851 GRAND CONCOURSE- RENOVATIONS | 4 | BID AWARD AND REGISTER CONTRCT | 2007-08-26 | 2007-11-23 | 2007-08-26 | 2007-11-23
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293201A | DASNY - 851 GRAND CONCOURSE- RENOVATIONS | 5 | CONSTRUCTION TO 25% | 2007-11-24 | 2008-11-17 | 2007-11-24 | 2008-11-17
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293201A | DASNY - 851 GRAND CONCOURSE- RENOVATIONS | 6 | CONSTRUCTION TO 50% | 2008-11-18 | 2009-11-12 | 2008-11-18 | 2009-11-12
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293201A | DASNY - 851 GRAND CONCOURSE- RENOVATIONS | 7 | CONSTRUCTION TO 75% | 2009-11-13 | 2010-11-07 | 2009-11-13 | 2010-11-07
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293201A | DASNY - 851 GRAND CONCOURSE- RENOVATIONS | 8 | ORIGINAL EQUIP & FURNISHING | 2010-11-08 | 2011-11-02 | 2010-11-08 | 2011-11-02
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293201A | DASNY - 851 GRAND CONCOURSE- RENOVATIONS | 9 | SUBSTANTIAL COMPLETION | 2011-11-03 | 2011-12-02 | 2011-11-03 | 2022-06-30
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293201A | DASNY - 851 GRAND CONCOURSE- RENOVATIONS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2011-12-07 | 2011-12-26 | 2022-07-30 | 2022-08-18
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293CTR | 851 GRAND CONCOURSE -COOLING TOWER REPLACEMENT | 1 | DEVELOP SCOPE | 2022-03-01 | 2022-05-29 | 2022-03-01 | 2022-05-29
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293CTR | 851 GRAND CONCOURSE -COOLING TOWER REPLACEMENT | 2 | PRELIMINARY DESIGN | 2022-05-30 | 2022-09-26 | 2022-05-30 | 2022-09-26
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293CTR | 851 GRAND CONCOURSE -COOLING TOWER REPLACEMENT | 3 | FINAL DESIGN | 2022-09-27 | 2023-03-25 | 2022-09-27 | 2023-03-25
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293CTR | 851 GRAND CONCOURSE -COOLING TOWER REPLACEMENT | 4 | BID AWARD AND REGISTER CONTRCT | 2023-03-26 | 2023-06-23 | 2023-03-26 | 2023-06-23
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293CTR | 851 GRAND CONCOURSE -COOLING TOWER REPLACEMENT | 5 | CONSTRUCTION TO 25% | 2023-06-24 | 2023-10-21 | 2023-06-24 | 2023-10-21
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293CTR | 851 GRAND CONCOURSE -COOLING TOWER REPLACEMENT | 6 | CONSTRUCTION TO 50% | 2023-10-22 | 2024-02-18 | 2023-10-22 | 2024-02-18
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293CTR | 851 GRAND CONCOURSE -COOLING TOWER REPLACEMENT | 7 | CONSTRUCTION TO 75% | 2024-02-19 | 2024-06-17 | 2024-02-19 | 2024-06-17
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293CTR | 851 GRAND CONCOURSE -COOLING TOWER REPLACEMENT | 8 | ORIGINAL EQUIP & FURNISHING | 2024-06-18 | 2024-09-15 | 2024-06-18 | 2024-09-15
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293CTR | 851 GRAND CONCOURSE -COOLING TOWER REPLACEMENT | 9 | SUBSTANTIAL COMPLETION | 2024-09-16 | 2024-11-14 | 2024-09-16 | 2024-11-14
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293CTR | 851 GRAND CONCOURSE -COOLING TOWER REPLACEMENT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-11-15 | 2024-12-14 | 2024-11-15 | 2024-12-14
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293EV | 851 GRAND CONCOURSE - ELEVATORS | 1 | DEVELOP SCOPE | 2022-06-01 | 2022-08-29 | 2022-06-01 | 2022-08-29
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293EV | 851 GRAND CONCOURSE - ELEVATORS | 2 | PRELIMINARY DESIGN | 2022-08-30 | 2022-12-27 | 2022-08-30 | 2022-12-27
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293EV | 851 GRAND CONCOURSE - ELEVATORS | 3 | FINAL DESIGN | 2022-12-28 | 2023-06-25 | 2022-12-28 | 2023-06-25
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293EV | 851 GRAND CONCOURSE - ELEVATORS | 4 | BID AWARD AND REGISTER CONTRCT | 2024-06-26 | 2024-09-23 | 2024-06-26 | 2024-09-23
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293EV | 851 GRAND CONCOURSE - ELEVATORS | 5 | CONSTRUCTION TO 25% | 2024-09-24 | 2025-01-21 | 2024-09-24 | 2025-01-21
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293EV | 851 GRAND CONCOURSE - ELEVATORS | 6 | CONSTRUCTION TO 50% | 2025-01-22 | 2025-05-21 | 2025-01-22 | 2025-05-21
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293EV | 851 GRAND CONCOURSE - ELEVATORS | 7 | CONSTRUCTION TO 75% | 2025-05-22 | 2025-09-18 | 2025-05-22 | 2025-09-18
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293EV | 851 GRAND CONCOURSE - ELEVATORS | 8 | ORIGINAL EQUIP & FURNISHING | 2025-09-19 | 2025-12-17 | 2025-09-19 | 2025-12-17
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293EV | 851 GRAND CONCOURSE - ELEVATORS | 9 | SUBSTANTIAL COMPLETION | 2025-12-18 | 2026-02-15 | 2025-12-18 | 2026-02-15
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293EV | 851 GRAND CONCOURSE - ELEVATORS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2026-02-16 | 2026-03-17 | 2026-02-16 | 2026-03-17
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293HO | 851 GRAND CONCOURSE - HOUSING COURT RELOCATION | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-08-29 | 2020-06-01 | 2020-08-29
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293HO | 851 GRAND CONCOURSE - HOUSING COURT RELOCATION | 2 | PRELIMINARY DESIGN | 2020-08-30 | 2020-12-27 | 2020-08-30 | 2020-12-27
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293HO | 851 GRAND CONCOURSE - HOUSING COURT RELOCATION | 3 | FINAL DESIGN | 2020-12-28 | 2021-06-25 | 2020-12-28 | 2021-06-25
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293HO | 851 GRAND CONCOURSE - HOUSING COURT RELOCATION | 4 | BID AWARD AND REGISTER CONTRCT | 2021-06-26 | 2021-09-23 | 2021-06-26 | 2021-09-23
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293HO | 851 GRAND CONCOURSE - HOUSING COURT RELOCATION | 5 | CONSTRUCTION TO 25% | 2021-09-24 | 2022-01-21 | 2021-09-24 | 2022-01-21
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293HO | 851 GRAND CONCOURSE - HOUSING COURT RELOCATION | 6 | CONSTRUCTION TO 50% | 2022-01-22 | 2022-05-21 | 2022-01-22 | 2022-05-21
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293HO | 851 GRAND CONCOURSE - HOUSING COURT RELOCATION | 7 | CONSTRUCTION TO 75% | 2022-05-22 | 2022-09-18 | 2022-05-22 | 2022-09-18
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293HO | 851 GRAND CONCOURSE - HOUSING COURT RELOCATION | 8 | ORIGINAL EQUIP & FURNISHING | 2022-09-19 | 2022-12-17 | 2022-09-19 | 2022-12-17
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293HO | 851 GRAND CONCOURSE - HOUSING COURT RELOCATION | 9 | SUBSTANTIAL COMPLETION | 2022-12-18 | 2023-02-15 | 2022-12-18 | 2023-02-15
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293HO | 851 GRAND CONCOURSE - HOUSING COURT RELOCATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-02-16 | 2023-03-17 | 2023-02-16 | 2023-03-17
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293SA | 851 GRAND CONCOURSE - SAFE ACCESS TO MECHANICAL SYSTEM | 1 | DEVELOP SCOPE | 2010-06-01 | 2010-08-29 | 2021-06-01 | 2021-08-29
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293SA | 851 GRAND CONCOURSE - SAFE ACCESS TO MECHANICAL SYSTEM | 2 | PRELIMINARY DESIGN | 2010-08-30 | 2010-12-27 | 2021-08-30 | 2021-12-27
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293SA | 851 GRAND CONCOURSE - SAFE ACCESS TO MECHANICAL SYSTEM | 3 | FINAL DESIGN | 2010-12-28 | 2011-06-25 | 2021-12-28 | 2022-06-25
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293SA | 851 GRAND CONCOURSE - SAFE ACCESS TO MECHANICAL SYSTEM | 4 | BID AWARD AND REGISTER CONTRCT | 2011-06-26 | 2011-09-23 | 2022-06-26 | 2022-09-23
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293SA | 851 GRAND CONCOURSE - SAFE ACCESS TO MECHANICAL SYSTEM | 5 | CONSTRUCTION TO 25% | 2011-09-24 | 2012-01-21 | 2022-09-24 | 2023-01-21
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293SA | 851 GRAND CONCOURSE - SAFE ACCESS TO MECHANICAL SYSTEM | 6 | CONSTRUCTION TO 50% | 2012-01-22 | 2012-05-20 | 2023-01-22 | 2023-05-21
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293SA | 851 GRAND CONCOURSE - SAFE ACCESS TO MECHANICAL SYSTEM | 7 | CONSTRUCTION TO 75% | 2012-05-21 | 2012-09-17 | 2023-05-22 | 2023-09-18
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293SA | 851 GRAND CONCOURSE - SAFE ACCESS TO MECHANICAL SYSTEM | 8 | ORIGINAL EQUIP & FURNISHING | 2012-09-18 | 2012-12-16 | 2023-09-19 | 2023-12-17
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293SA | 851 GRAND CONCOURSE - SAFE ACCESS TO MECHANICAL SYSTEM | 9 | SUBSTANTIAL COMPLETION | 2012-12-17 | 2013-02-14 | 2023-12-18 | 2024-02-15
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293SA | 851 GRAND CONCOURSE - SAFE ACCESS TO MECHANICAL SYSTEM | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2013-02-15 | 2013-03-16 | 2024-02-16 | 2027-06-30
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO294BACK | DASNY - 215 E. 161ST ST.- BACKFILL | 1 | DEVELOP SCOPE | 2006-12-01 | 2007-02-28 | 2006-12-01 | 2007-02-28
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO294BACK | DASNY - 215 E. 161ST ST.- BACKFILL | 2 | PRELIMINARY DESIGN | 2007-03-01 | 2007-06-28 | 2007-03-01 | 2007-06-28
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO294BACK | DASNY - 215 E. 161ST ST.- BACKFILL | 3 | FINAL DESIGN | 2007-06-29 | 2007-12-25 | 2007-06-29 | 2007-12-25
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO294BACK | DASNY - 215 E. 161ST ST.- BACKFILL | 4 | BID AWARD AND REGISTER CONTRCT | 2007-12-26 | 2008-03-24 | 2007-12-26 | 2008-03-24
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO294BACK | DASNY - 215 E. 161ST ST.- BACKFILL | 5 | CONSTRUCTION TO 25% | 2008-03-25 | 2009-03-19 | 2008-03-25 | 2009-03-19
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO294BACK | DASNY - 215 E. 161ST ST.- BACKFILL | 6 | CONSTRUCTION TO 50% | 2009-03-20 | 2010-03-14 | 2009-03-20 | 2010-03-14
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO294BACK | DASNY - 215 E. 161ST ST.- BACKFILL | 7 | CONSTRUCTION TO 75% | 2010-03-15 | 2011-03-09 | 2010-03-15 | 2011-03-09
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO294BACK | DASNY - 215 E. 161ST ST.- BACKFILL | 8 | ORIGINAL EQUIP & FURNISHING | 2011-03-10 | 2011-09-05 | 2011-03-10 | 2011-09-05
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO294BACK | DASNY - 215 E. 161ST ST.- BACKFILL | 9 | SUBSTANTIAL COMPLETION | 2011-09-06 | 2011-11-04 | 2011-09-06 | 2011-11-04
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO294BACK | DASNY - 215 E. 161ST ST.- BACKFILL | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2011-11-05 | 2011-12-04 | 2011-11-05 | 2022-06-30
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO294BOIL | 215 EAST161ST STREET- REPLACEMENT OF BOILER | 1 | DEVELOP SCOPE | 2017-06-01 | 2017-08-29 | 2017-06-01 | 2017-08-29
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO294BOIL | 215 EAST161ST STREET- REPLACEMENT OF BOILER | 2 | PRELIMINARY DESIGN | 2017-08-30 | 2017-12-27 | 2017-08-30 | 2017-12-27
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO294BOIL | 215 EAST161ST STREET- REPLACEMENT OF BOILER | 3 | FINAL DESIGN | 2017-12-28 | 2018-06-25 | 2017-12-28 | 2018-06-25
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO294BOIL | 215 EAST161ST STREET- REPLACEMENT OF BOILER | 4 | BID AWARD AND REGISTER CONTRCT | 2018-06-26 | 2018-09-23 | 2018-06-26 | 2018-09-23
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO294BOIL | 215 EAST161ST STREET- REPLACEMENT OF BOILER | 5 | CONSTRUCTION TO 25% | 2023-06-01 | 2023-09-28 | 2023-06-01 | 2023-09-28
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO294BOIL | 215 EAST161ST STREET- REPLACEMENT OF BOILER | 6 | CONSTRUCTION TO 50% | 2023-09-29 | 2024-01-26 | 2023-09-29 | 2024-01-26
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO294BOIL | 215 EAST161ST STREET- REPLACEMENT OF BOILER | 7 | CONSTRUCTION TO 75% | 2024-01-27 | 2024-05-25 | 2024-01-27 | 2024-05-25
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO294BOIL | 215 EAST161ST STREET- REPLACEMENT OF BOILER | 8 | ORIGINAL EQUIP & FURNISHING | 2024-05-26 | 2024-08-23 | 2024-05-26 | 2024-08-23
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO294BOIL | 215 EAST161ST STREET- REPLACEMENT OF BOILER | 9 | SUBSTANTIAL COMPLETION | 2024-08-24 | 2024-10-22 | 2024-08-24 | 2024-10-22
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO294BOIL | 215 EAST161ST STREET- REPLACEMENT OF BOILER | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-10-23 | 2024-11-21 | 2024-10-23 | 2024-11-21
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO295FIRE | 1118 GRAND CONCOURSE - FIRE ALARM UPGRADE | 1 | DEVELOP SCOPE | 2022-06-01 | 2022-08-29 | 2022-06-01 | 2022-08-29
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO295FIRE | 1118 GRAND CONCOURSE - FIRE ALARM UPGRADE | 2 | PRELIMINARY DESIGN | 2022-08-30 | 2022-12-27 | 2022-08-30 | 2022-12-27
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO295FIRE | 1118 GRAND CONCOURSE - FIRE ALARM UPGRADE | 3 | FINAL DESIGN | 2022-12-28 | 2023-06-25 | 2022-12-28 | 2023-06-25
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO295FIRE | 1118 GRAND CONCOURSE - FIRE ALARM UPGRADE | 4 | BID AWARD AND REGISTER CONTRCT | 2023-06-26 | 2023-09-23 | 2023-06-26 | 2023-09-23
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO295FIRE | 1118 GRAND CONCOURSE - FIRE ALARM UPGRADE | 5 | CONSTRUCTION TO 25% | 2023-09-24 | 2024-01-21 | 2023-09-24 | 2024-01-21
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO295FIRE | 1118 GRAND CONCOURSE - FIRE ALARM UPGRADE | 6 | CONSTRUCTION TO 50% | 2024-01-22 | 2024-05-20 | 2024-01-22 | 2024-05-20
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO295FIRE | 1118 GRAND CONCOURSE - FIRE ALARM UPGRADE | 7 | CONSTRUCTION TO 75% | 2024-05-21 | 2024-09-17 | 2024-05-21 | 2024-09-17
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO295FIRE | 1118 GRAND CONCOURSE - FIRE ALARM UPGRADE | 8 | ORIGINAL EQUIP & FURNISHING | 2024-09-18 | 2024-12-16 | 2024-09-18 | 2024-12-16
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO295FIRE | 1118 GRAND CONCOURSE - FIRE ALARM UPGRADE | 9 | SUBSTANTIAL COMPLETION | 2024-12-17 | 2025-02-14 | 2024-12-17 | 2025-02-14
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO295FIRE | 1118 GRAND CONCOURSE - FIRE ALARM UPGRADE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-02-15 | 2026-06-30 | 2025-02-15 | 2026-06-30
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO295ROOF | 1118 GRAND CONCOURSE - ROOF | 1 | DEVELOP SCOPE | 2022-03-01 | 2022-05-29 | 2022-03-01 | 2022-05-29
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO295ROOF | 1118 GRAND CONCOURSE - ROOF | 2 | PRELIMINARY DESIGN | 2022-05-30 | 2022-09-26 | 2022-05-30 | 2022-09-26
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO295ROOF | 1118 GRAND CONCOURSE - ROOF | 3 | FINAL DESIGN | 2022-09-27 | 2023-03-25 | 2022-09-27 | 2023-03-25
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO295ROOF | 1118 GRAND CONCOURSE - ROOF | 4 | BID AWARD AND REGISTER CONTRCT | 2023-03-26 | 2023-06-23 | 2023-03-26 | 2023-06-23
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO295ROOF | 1118 GRAND CONCOURSE - ROOF | 5 | CONSTRUCTION TO 25% | 2023-06-24 | 2023-10-21 | 2023-06-24 | 2023-10-21
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO295ROOF | 1118 GRAND CONCOURSE - ROOF | 6 | CONSTRUCTION TO 50% | 2023-10-22 | 2024-02-18 | 2023-10-22 | 2024-02-18
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO295ROOF | 1118 GRAND CONCOURSE - ROOF | 7 | CONSTRUCTION TO 75% | 2024-02-19 | 2024-06-17 | 2024-02-19 | 2024-06-17
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO295ROOF | 1118 GRAND CONCOURSE - ROOF | 8 | ORIGINAL EQUIP & FURNISHING | 2024-06-18 | 2024-09-15 | 2024-06-18 | 2024-09-15
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO295ROOF | 1118 GRAND CONCOURSE - ROOF | 9 | SUBSTANTIAL COMPLETION | 2024-09-16 | 2024-11-14 | 2024-09-16 | 2024-11-14
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO295ROOF | 1118 GRAND CONCOURSE - ROOF | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-11-15 | 2024-12-14 | 2024-11-15 | 2024-12-14
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | COD294CBG | BRONX CENTRAL BOOKING /BRONX COURT SECTION - FITNESS CENTER | 1 | DEVELOP SCOPE | 2021-06-01 | 2021-08-29 | 2021-06-01 | 2021-08-29
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | COD294CBG | BRONX CENTRAL BOOKING /BRONX COURT SECTION - FITNESS CENTER | 2 | PRELIMINARY DESIGN | 2021-08-30 | 2021-12-27 | 2021-08-30 | 2021-12-27
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | COD294CBG | BRONX CENTRAL BOOKING /BRONX COURT SECTION - FITNESS CENTER | 3 | FINAL DESIGN | 2021-12-28 | 2022-06-25 | 2021-12-28 | 2022-06-25
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | COD294CBG | BRONX CENTRAL BOOKING /BRONX COURT SECTION - FITNESS CENTER | 4 | BID AWARD AND REGISTER CONTRCT | 2022-06-26 | 2022-09-23 | 2022-06-26 | 2022-09-23
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | COD294CBG | BRONX CENTRAL BOOKING /BRONX COURT SECTION - FITNESS CENTER | 5 | CONSTRUCTION TO 25% | 2022-09-24 | 2023-01-21 | 2022-09-24 | 2023-01-21
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | COD294CBG | BRONX CENTRAL BOOKING /BRONX COURT SECTION - FITNESS CENTER | 6 | CONSTRUCTION TO 50% | 2023-01-22 | 2023-05-21 | 2023-01-22 | 2023-05-21
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | COD294CBG | BRONX CENTRAL BOOKING /BRONX COURT SECTION - FITNESS CENTER | 7 | CONSTRUCTION TO 75% | 2023-05-22 | 2023-09-18 | 2023-05-22 | 2023-09-18
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | COD294CBG | BRONX CENTRAL BOOKING /BRONX COURT SECTION - FITNESS CENTER | 8 | ORIGINAL EQUIP & FURNISHING | 2021-06-01 | 2021-08-29 | 2021-06-01 | 2021-08-29
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | COD294CBG | BRONX CENTRAL BOOKING /BRONX COURT SECTION - FITNESS CENTER | 9 | SUBSTANTIAL COMPLETION | 2021-08-30 | 2021-10-28 | 2021-08-30 | 2021-10-28
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | COD294CBG | BRONX CENTRAL BOOKING /BRONX COURT SECTION - FITNESS CENTER | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-10-29 | 2021-11-27 | 2021-10-29 | 2021-11-27
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | DAVIDCC | DAVIDSON COMMUNITY CENTER GYM | 1 | DEVELOP SCOPE | 2019-06-01 | 2019-08-29 | 2019-06-01 | 2019-08-29
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | DAVIDCC | DAVIDSON COMMUNITY CENTER GYM | 2 | PRELIMINARY DESIGN | 2019-08-30 | 2019-12-27 | 2019-08-30 | 2019-12-27
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | DAVIDCC | DAVIDSON COMMUNITY CENTER GYM | 3 | FINAL DESIGN | 2019-12-28 | 2020-06-24 | 2019-12-28 | 2020-06-24
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | DAVIDCC | DAVIDSON COMMUNITY CENTER GYM | 4 | BID AWARD AND REGISTER CONTRCT | 2020-06-25 | 2020-09-22 | 2020-06-25 | 2020-09-22
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | DAVIDCC | DAVIDSON COMMUNITY CENTER GYM | 5 | CONSTRUCTION TO 25% | 2020-09-23 | 2021-01-20 | 2020-09-23 | 2021-01-20
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | DAVIDCC | DAVIDSON COMMUNITY CENTER GYM | 6 | CONSTRUCTION TO 50% | 2021-01-21 | 2021-05-20 | 2021-01-21 | 2021-05-20
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | DAVIDCC | DAVIDSON COMMUNITY CENTER GYM | 7 | CONSTRUCTION TO 75% | 2021-05-21 | 2021-09-17 | 2021-05-21 | 2021-09-17
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | DAVIDCC | DAVIDSON COMMUNITY CENTER GYM | 8 | ORIGINAL EQUIP & FURNISHING | 2021-09-18 | 2021-12-16 | 2021-09-18 | 2021-12-16
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | DAVIDCC | DAVIDSON COMMUNITY CENTER GYM | 9 | SUBSTANTIAL COMPLETION | 2021-12-17 | 2022-02-14 | 2021-12-17 | 2022-02-14
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | DAVIDCC | DAVIDSON COMMUNITY CENTER GYM | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2022-02-15 | 2022-03-16 | 2022-02-15 | 2022-03-16
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | E08-0006A | NYPD - 08-147: OLD 41st PRECINCT, 1086 SIMPSON STREET | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-06-30 | 2020-06-01 | 2020-06-30
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | E08-0006A | NYPD - 08-147: OLD 41st PRECINCT, 1086 SIMPSON STREET | 2 | BID AWARD AND REGISTER CONTRCT | 2020-07-01 | 2020-08-29 | 2020-07-01 | 2020-08-29
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | E08-0006A | NYPD - 08-147: OLD 41st PRECINCT, 1086 SIMPSON STREET | 3 | CONSTRUCTION TO 50% | 2020-08-30 | 2021-02-25 | 2020-08-30 | 2021-02-25
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | E08-0006A | NYPD - 08-147: OLD 41st PRECINCT, 1086 SIMPSON STREET | 4 | CONSTRUCTION TO 75% | 2021-02-26 | 2021-05-26 | 2021-02-26 | 2021-05-26
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | E08-0006A | NYPD - 08-147: OLD 41st PRECINCT, 1086 SIMPSON STREET | 5 | SUBSTANTIAL COMPLETION | 2021-05-27 | 2021-07-25 | 2021-05-27 | 2021-07-25
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | E08-0006A | NYPD - 08-147: OLD 41st PRECINCT, 1086 SIMPSON STREET | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-07-26 | 2021-08-24 | 2021-07-26 | 2021-08-24
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | E14-0002 | DCAS - BRONX COUNTY COURT COMP ENERGY UPGRADE | 1 | DEVELOP SCOPE | 2013-12-01 | 2015-03-31 | 2020-06-01 | 2021-09-29
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | E14-0002 | DCAS - BRONX COUNTY COURT COMP ENERGY UPGRADE | 2 | BID AWARD AND REGISTER CONTRCT | 2015-04-01 | 2015-05-30 | 2021-09-30 | 2021-11-28
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | E14-0002 | DCAS - BRONX COUNTY COURT COMP ENERGY UPGRADE | 3 | CONSTRUCTION TO 50% | 2015-05-31 | 2015-08-28 | 2022-06-01 | 2022-08-29
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | E14-0002 | DCAS - BRONX COUNTY COURT COMP ENERGY UPGRADE | 4 | CONSTRUCTION TO 75% | 2015-08-29 | 2015-10-27 | 2022-08-30 | 2022-10-28
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | E14-0002 | DCAS - BRONX COUNTY COURT COMP ENERGY UPGRADE | 5 | SUBSTANTIAL COMPLETION | 2015-10-28 | 2015-11-26 | 2022-10-29 | 2022-11-27
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | E14-0002 | DCAS - BRONX COUNTY COURT COMP ENERGY UPGRADE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-11-27 | 2015-12-26 | 2022-11-28 | 2023-06-30
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0040 | CUNY - Bronx Community College Campus: Meister Hall | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-06-30 | 2020-06-01 | 2020-06-30
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0040 | CUNY - Bronx Community College Campus: Meister Hall | 2 | BID AWARD AND REGISTER CONTRCT | 2020-07-01 | 2020-08-29 | 2020-07-01 | 2020-08-29
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0040 | CUNY - Bronx Community College Campus: Meister Hall | 3 | CONSTRUCTION TO 50% | 2020-08-30 | 2021-02-25 | 2020-08-30 | 2021-02-25
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0040 | CUNY - Bronx Community College Campus: Meister Hall | 4 | CONSTRUCTION TO 75% | 2021-02-26 | 2021-05-26 | 2021-02-26 | 2021-05-26
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0040 | CUNY - Bronx Community College Campus: Meister Hall | 5 | SUBSTANTIAL COMPLETION | 2021-05-27 | 2021-07-25 | 2021-05-27 | 2021-07-25
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0040 | CUNY - Bronx Community College Campus: Meister Hall | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-07-26 | 2021-08-24 | 2021-07-26 | 2021-08-24
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0042 | CUNY - Bronx Community College Campus: Polowczyk Hall | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-06-30 | 2020-06-01 | 2020-06-30
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0042 | CUNY - Bronx Community College Campus: Polowczyk Hall | 2 | BID AWARD AND REGISTER CONTRCT | 2020-07-01 | 2020-08-29 | 2020-07-01 | 2020-08-29
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0042 | CUNY - Bronx Community College Campus: Polowczyk Hall | 3 | CONSTRUCTION TO 50% | 2020-08-30 | 2021-02-25 | 2020-08-30 | 2021-02-25
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0042 | CUNY - Bronx Community College Campus: Polowczyk Hall | 4 | CONSTRUCTION TO 75% | 2021-02-26 | 2021-05-26 | 2021-02-26 | 2021-05-26
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0042 | CUNY - Bronx Community College Campus: Polowczyk Hall | 5 | SUBSTANTIAL COMPLETION | 2021-05-27 | 2021-07-25 | 2021-05-27 | 2021-07-25
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0042 | CUNY - Bronx Community College Campus: Polowczyk Hall | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-07-26 | 2021-08-24 | 2021-07-26 | 2021-08-24
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0043 | CUNY - Bronx Community College Campus: Colston Hall | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-06-30 | 2020-06-01 | 2020-06-30
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0043 | CUNY - Bronx Community College Campus: Colston Hall | 2 | BID AWARD AND REGISTER CONTRCT | 2020-07-01 | 2020-08-29 | 2020-07-01 | 2020-08-29
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0043 | CUNY - Bronx Community College Campus: Colston Hall | 3 | CONSTRUCTION TO 50% | 2020-08-30 | 2021-02-25 | 2020-08-30 | 2021-02-25
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0043 | CUNY - Bronx Community College Campus: Colston Hall | 4 | CONSTRUCTION TO 75% | 2021-02-26 | 2021-05-26 | 2021-02-26 | 2021-05-26
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0043 | CUNY - Bronx Community College Campus: Colston Hall | 5 | SUBSTANTIAL COMPLETION | 2021-05-27 | 2021-07-25 | 2021-05-27 | 2021-07-25
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0043 | CUNY - Bronx Community College Campus: Colston Hall | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-07-26 | 2021-08-24 | 2021-07-26 | 2021-08-24
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0044 | CUNY - Bronx Community College Campus: Loew Hall | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-06-30 | 2020-06-01 | 2020-06-30
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0044 | CUNY - Bronx Community College Campus: Loew Hall | 2 | BID AWARD AND REGISTER CONTRCT | 2020-07-01 | 2020-08-29 | 2020-07-01 | 2020-08-29
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0044 | CUNY - Bronx Community College Campus: Loew Hall | 3 | CONSTRUCTION TO 50% | 2020-08-30 | 2021-02-25 | 2020-08-30 | 2021-02-25
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0044 | CUNY - Bronx Community College Campus: Loew Hall | 4 | CONSTRUCTION TO 75% | 2021-02-26 | 2021-05-26 | 2021-02-26 | 2021-05-26
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0044 | CUNY - Bronx Community College Campus: Loew Hall | 5 | SUBSTANTIAL COMPLETION | 2021-05-27 | 2021-07-25 | 2021-05-27 | 2021-07-25
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0044 | CUNY - Bronx Community College Campus: Loew Hall | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-07-26 | 2021-08-24 | 2021-07-26 | 2021-08-24
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0045 | CUNY - Bronx Community College Campus: Nichols Hall | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-06-30 | 2020-06-01 | 2020-06-30
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0045 | CUNY - Bronx Community College Campus: Nichols Hall | 2 | BID AWARD AND REGISTER CONTRCT | 2020-07-01 | 2020-08-29 | 2020-07-01 | 2020-08-29
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0045 | CUNY - Bronx Community College Campus: Nichols Hall | 3 | CONSTRUCTION TO 50% | 2020-08-30 | 2021-02-25 | 2020-08-30 | 2021-02-25
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0045 | CUNY - Bronx Community College Campus: Nichols Hall | 4 | CONSTRUCTION TO 75% | 2021-02-26 | 2021-05-26 | 2021-02-26 | 2021-05-26
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0045 | CUNY - Bronx Community College Campus: Nichols Hall | 5 | SUBSTANTIAL COMPLETION | 2021-05-27 | 2021-07-25 | 2021-05-27 | 2021-07-25
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0045 | CUNY - Bronx Community College Campus: Nichols Hall | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-07-26 | 2021-08-24 | 2021-07-26 | 2021-08-24
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0063 | NYPD - 40th Precinct | 1 | DEVELOP SCOPE | 2020-02-01 | 2020-03-01 | 2022-06-01 | 2022-06-30
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0063 | NYPD - 40th Precinct | 2 | BID AWARD AND REGISTER CONTRCT | 2020-03-02 | 2020-04-30 | 2022-07-01 | 2022-08-29
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0063 | NYPD - 40th Precinct | 3 | CONSTRUCTION TO 50% | 2020-05-01 | 2020-10-27 | 2022-08-30 | 2023-02-25
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0063 | NYPD - 40th Precinct | 4 | CONSTRUCTION TO 75% | 2020-10-28 | 2021-01-25 | 2023-02-26 | 2023-05-26
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0063 | NYPD - 40th Precinct | 5 | SUBSTANTIAL COMPLETION | 2021-01-26 | 2021-03-26 | 2023-05-27 | 2023-07-25
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0063 | NYPD - 40th Precinct | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-27 | 2021-04-25 | 2023-07-26 | 2023-08-24
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0064 | NYPD - 52nd Precinct | 1 | DEVELOP SCOPE | 2020-03-01 | 2020-03-30 | 2022-06-01 | 2022-06-30
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0064 | NYPD - 52nd Precinct | 2 | BID AWARD AND REGISTER CONTRCT | 2020-03-31 | 2020-05-29 | 2022-07-01 | 2022-08-29
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0064 | NYPD - 52nd Precinct | 3 | CONSTRUCTION TO 50% | 2020-05-30 | 2020-11-25 | 2022-08-30 | 2023-02-25
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0064 | NYPD - 52nd Precinct | 4 | CONSTRUCTION TO 75% | 2020-11-26 | 2021-02-23 | 2023-02-26 | 2023-05-26
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0064 | NYPD - 52nd Precinct | 5 | SUBSTANTIAL COMPLETION | 2021-02-24 | 2021-04-24 | 2023-05-27 | 2023-07-25
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0064 | NYPD - 52nd Precinct | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-04-25 | 2021-05-24 | 2023-07-26 | 2023-08-24
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0075 | NYPD - 44TH PRECINCT | 1 | DEVELOP SCOPE | 2020-01-15 | 2020-02-13 | 2020-01-15 | 2020-02-13
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0075 | NYPD - 44TH PRECINCT | 2 | BID AWARD AND REGISTER CONTRCT | 2020-02-14 | 2020-04-13 | 2020-02-14 | 2020-04-13
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0075 | NYPD - 44TH PRECINCT | 3 | CONSTRUCTION TO 50% | 2020-04-14 | 2020-10-10 | 2022-06-01 | 2022-11-27
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0075 | NYPD - 44TH PRECINCT | 4 | CONSTRUCTION TO 75% | 2020-10-11 | 2021-01-08 | 2022-11-28 | 2023-02-25
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0075 | NYPD - 44TH PRECINCT | 5 | SUBSTANTIAL COMPLETION | 2021-01-09 | 2021-03-09 | 2023-02-26 | 2023-04-26
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0075 | NYPD - 44TH PRECINCT | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-10 | 2021-04-08 | 2023-04-27 | 2023-05-26
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0080 | DHS - FRANKLIN WOMEN'S SHELTER | 1 | DEVELOP SCOPE | 2020-02-15 | 2020-03-15 | 2022-06-01 | 2022-06-30
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0080 | DHS - FRANKLIN WOMEN'S SHELTER | 2 | BID AWARD AND REGISTER CONTRCT | 2020-03-16 | 2020-05-14 | 2022-07-01 | 2022-08-29
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0080 | DHS - FRANKLIN WOMEN'S SHELTER | 3 | CONSTRUCTION TO 50% | 2020-05-15 | 2020-11-10 | 2022-08-30 | 2023-02-25
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0080 | DHS - FRANKLIN WOMEN'S SHELTER | 4 | CONSTRUCTION TO 75% | 2020-11-11 | 2021-02-08 | 2023-02-26 | 2023-05-26
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0080 | DHS - FRANKLIN WOMEN'S SHELTER | 5 | SUBSTANTIAL COMPLETION | 2021-02-09 | 2021-04-09 | 2023-05-27 | 2023-07-25
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0080 | DHS - FRANKLIN WOMEN'S SHELTER | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-04-10 | 2021-05-09 | 2023-07-26 | 2023-08-24
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0089 | DPR - BRONX PARKS HEADQUARTERS AND SHOPS | 1 | DEVELOP SCOPE | 2020-02-01 | 2020-03-01 | 2022-06-01 | 2022-06-30
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0089 | DPR - BRONX PARKS HEADQUARTERS AND SHOPS | 2 | BID AWARD AND REGISTER CONTRCT | 2020-03-02 | 2020-04-30 | 2022-07-01 | 2022-08-29
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0089 | DPR - BRONX PARKS HEADQUARTERS AND SHOPS | 3 | CONSTRUCTION TO 50% | 2020-05-01 | 2020-10-27 | 2022-08-30 | 2023-02-25
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0089 | DPR - BRONX PARKS HEADQUARTERS AND SHOPS | 4 | CONSTRUCTION TO 75% | 2020-10-28 | 2021-01-25 | 2023-02-26 | 2023-05-26
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0089 | DPR - BRONX PARKS HEADQUARTERS AND SHOPS | 5 | SUBSTANTIAL COMPLETION | 2021-01-26 | 2021-03-26 | 2023-05-27 | 2023-07-25
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0089 | DPR - BRONX PARKS HEADQUARTERS AND SHOPS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-03-27 | 2021-04-25 | 2023-07-26 | 2023-08-24
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | NDF-DAVID | NDF - DAVIDSON AVE COMMUNITY CENTER | 1 | DEVELOP SCOPE | 2021-06-01 | 2021-08-29 | 2021-06-01 | 2021-08-29
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | NDF-DAVID | NDF - DAVIDSON AVE COMMUNITY CENTER | 2 | PRELIMINARY DESIGN | 2021-08-30 | 2021-12-27 | 2021-08-30 | 2021-12-27
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | NDF-DAVID | NDF - DAVIDSON AVE COMMUNITY CENTER | 3 | FINAL DESIGN | 2021-12-28 | 2022-06-25 | 2021-12-28 | 2022-06-25
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | NDF-DAVID | NDF - DAVIDSON AVE COMMUNITY CENTER | 4 | BID AWARD AND REGISTER CONTRCT | 2022-06-26 | 2022-09-23 | 2022-06-26 | 2022-09-23
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | NDF-DAVID | NDF - DAVIDSON AVE COMMUNITY CENTER | 5 | CONSTRUCTION TO 25% | 2022-09-24 | 2023-01-21 | 2022-09-24 | 2023-01-21
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | NDF-DAVID | NDF - DAVIDSON AVE COMMUNITY CENTER | 6 | CONSTRUCTION TO 50% | 2023-01-22 | 2023-05-21 | 2023-01-22 | 2023-05-21
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | NDF-DAVID | NDF - DAVIDSON AVE COMMUNITY CENTER | 7 | CONSTRUCTION TO 75% | 2023-05-22 | 2023-09-18 | 2023-05-22 | 2023-09-18
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | NDF-DAVID | NDF - DAVIDSON AVE COMMUNITY CENTER | 8 | ORIGINAL EQUIP & FURNISHING | 2023-09-19 | 2023-12-17 | 2023-09-19 | 2023-12-17
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | NDF-DAVID | NDF - DAVIDSON AVE COMMUNITY CENTER | 9 | SUBSTANTIAL COMPLETION | 2023-12-18 | 2024-02-15 | 2023-12-18 | 2024-02-15
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | NDF-DAVID | NDF - DAVIDSON AVE COMMUNITY CENTER | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-02-16 | 2024-03-16 | 2024-02-16 | 2024-03-16
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW293198X | 198 E 161ST STREET - FIRE ALARM UPGRADE | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-08-29 | 2020-06-01 | 2020-08-29
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW293198X | 198 E 161ST STREET - FIRE ALARM UPGRADE | 2 | PRELIMINARY DESIGN | 2020-08-30 | 2020-12-27 | 2020-08-30 | 2020-12-27
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW293198X | 198 E 161ST STREET - FIRE ALARM UPGRADE | 3 | FINAL DESIGN | 2020-12-28 | 2021-06-25 | 2020-12-28 | 2021-06-25
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW293198X | 198 E 161ST STREET - FIRE ALARM UPGRADE | 4 | BID AWARD AND REGISTER CONTRCT | 2021-06-26 | 2021-09-23 | 2021-06-26 | 2021-09-23
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW293198X | 198 E 161ST STREET - FIRE ALARM UPGRADE | 5 | CONSTRUCTION TO 25% | 2022-09-24 | 2023-01-21 | 2022-09-24 | 2023-01-21
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW293198X | 198 E 161ST STREET - FIRE ALARM UPGRADE | 6 | CONSTRUCTION TO 50% | 2023-01-22 | 2023-05-21 | 2023-01-22 | 2023-05-21
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW293198X | 198 E 161ST STREET - FIRE ALARM UPGRADE | 7 | CONSTRUCTION TO 75% | 2023-05-22 | 2023-09-18 | 2023-05-22 | 2023-09-18
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW293198X | 198 E 161ST STREET - FIRE ALARM UPGRADE | 8 | ORIGINAL EQUIP & FURNISHING | 2023-09-19 | 2023-12-17 | 2023-09-19 | 2023-12-17
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW293198X | 198 E 161ST STREET - FIRE ALARM UPGRADE | 9 | SUBSTANTIAL COMPLETION | 2023-12-18 | 2024-02-15 | 2023-12-18 | 2024-02-15
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW293198X | 198 E 161ST STREET - FIRE ALARM UPGRADE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-02-16 | 2024-03-16 | 2024-02-16 | 2024-03-16
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77198CT | 198 E 161 ST.- COOLING TOWER REPLACEMENT | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-08-29 | 2020-06-01 | 2020-08-29
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77198CT | 198 E 161 ST.- COOLING TOWER REPLACEMENT | 2 | PRELIMINARY DESIGN | 2020-08-30 | 2020-12-27 | 2020-08-30 | 2020-12-27
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77198CT | 198 E 161 ST.- COOLING TOWER REPLACEMENT | 3 | FINAL DESIGN | 2020-12-28 | 2021-06-25 | 2020-12-28 | 2021-06-25
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77198CT | 198 E 161 ST.- COOLING TOWER REPLACEMENT | 4 | BID AWARD AND REGISTER CONTRCT | 2021-06-26 | 2021-09-23 | 2021-06-26 | 2021-09-23
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77198CT | 198 E 161 ST.- COOLING TOWER REPLACEMENT | 5 | CONSTRUCTION TO 25% | 2022-09-24 | 2023-05-26 | 2022-09-24 | 2023-05-26
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77198CT | 198 E 161 ST.- COOLING TOWER REPLACEMENT | 6 | CONSTRUCTION TO 50% | 2023-05-27 | 2023-09-23 | 2023-05-27 | 2023-09-23
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77198CT | 198 E 161 ST.- COOLING TOWER REPLACEMENT | 7 | CONSTRUCTION TO 75% | 2023-09-24 | 2024-01-21 | 2023-09-24 | 2024-01-21
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77198CT | 198 E 161 ST.- COOLING TOWER REPLACEMENT | 8 | ORIGINAL EQUIP & FURNISHING | 2024-01-22 | 2024-04-20 | 2024-01-22 | 2024-04-20
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77198CT | 198 E 161 ST.- COOLING TOWER REPLACEMENT | 9 | SUBSTANTIAL COMPLETION | 2024-04-21 | 2024-06-19 | 2024-04-21 | 2024-06-19
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77198CT | 198 E 161 ST.- COOLING TOWER REPLACEMENT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-06-20 | 2024-07-19 | 2024-06-20 | 2024-07-19
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77198EV | 198 E 161 ST - ELEVATOR ,MODERNIZATION | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-08-29 | 2020-06-01 | 2020-08-29
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77198EV | 198 E 161 ST - ELEVATOR ,MODERNIZATION | 2 | PRELIMINARY DESIGN | 2020-08-30 | 2020-12-27 | 2020-08-30 | 2020-12-27
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77198EV | 198 E 161 ST - ELEVATOR ,MODERNIZATION | 3 | FINAL DESIGN | 2020-12-28 | 2021-06-25 | 2020-12-28 | 2021-06-25
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77198EV | 198 E 161 ST - ELEVATOR ,MODERNIZATION | 4 | BID AWARD AND REGISTER CONTRCT | 2021-06-26 | 2021-09-23 | 2021-06-26 | 2021-09-23
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77198EV | 198 E 161 ST - ELEVATOR ,MODERNIZATION | 5 | CONSTRUCTION TO 25% | 2022-06-01 | 2022-09-28 | 2022-06-01 | 2022-09-28
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77198EV | 198 E 161 ST - ELEVATOR ,MODERNIZATION | 6 | CONSTRUCTION TO 50% | 2022-09-29 | 2023-01-26 | 2022-09-29 | 2023-01-26
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77198EV | 198 E 161 ST - ELEVATOR ,MODERNIZATION | 7 | CONSTRUCTION TO 75% | 2023-01-27 | 2023-05-26 | 2023-01-27 | 2023-05-26
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77198EV | 198 E 161 ST - ELEVATOR ,MODERNIZATION | 8 | ORIGINAL EQUIP & FURNISHING | 2023-05-27 | 2023-08-24 | 2023-05-27 | 2023-08-24
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77198EV | 198 E 161 ST - ELEVATOR ,MODERNIZATION | 9 | SUBSTANTIAL COMPLETION | 2023-08-25 | 2023-10-23 | 2023-08-25 | 2023-10-23
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77198EV | 198 E 161 ST - ELEVATOR ,MODERNIZATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-10-24 | 2023-11-22 | 2023-10-24 | 2023-11-22
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW772076 | 1932 ARTHUR AVE.- 7th FLOOR BUILDOUT | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-08-29 | 2020-06-01 | 2020-08-29
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW772076 | 1932 ARTHUR AVE.- 7th FLOOR BUILDOUT | 2 | PRELIMINARY DESIGN | 2020-08-30 | 2020-12-27 | 2020-08-30 | 2020-12-27
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW772076 | 1932 ARTHUR AVE.- 7th FLOOR BUILDOUT | 3 | FINAL DESIGN | 2020-12-28 | 2021-06-25 | 2020-12-28 | 2021-06-25
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW772076 | 1932 ARTHUR AVE.- 7th FLOOR BUILDOUT | 4 | BID AWARD AND REGISTER CONTRCT | 2021-06-26 | 2021-09-23 | 2021-06-26 | 2021-09-23
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW772076 | 1932 ARTHUR AVE.- 7th FLOOR BUILDOUT | 5 | CONSTRUCTION TO 25% | 2022-09-24 | 2023-05-26 | 2022-09-24 | 2023-05-26
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW772076 | 1932 ARTHUR AVE.- 7th FLOOR BUILDOUT | 6 | CONSTRUCTION TO 50% | 2023-05-27 | 2023-09-23 | 2023-05-27 | 2023-09-23
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW772076 | 1932 ARTHUR AVE.- 7th FLOOR BUILDOUT | 7 | CONSTRUCTION TO 75% | 2023-09-24 | 2024-01-21 | 2023-09-24 | 2024-01-21
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW772076 | 1932 ARTHUR AVE.- 7th FLOOR BUILDOUT | 8 | ORIGINAL EQUIP & FURNISHING | 2024-01-22 | 2024-04-20 | 2024-01-22 | 2024-04-20
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW772076 | 1932 ARTHUR AVE.- 7th FLOOR BUILDOUT | 9 | SUBSTANTIAL COMPLETION | 2024-04-21 | 2024-06-19 | 2024-04-21 | 2024-06-19
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW772076 | 1932 ARTHUR AVE.- 7th FLOOR BUILDOUT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-06-20 | 2024-07-19 | 2024-06-20 | 2024-07-19
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207DC | 1932 ARTHUR AVENUE RENOVATION - 5TH FLOOR - DOB | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-08-29 | 2020-06-01 | 2020-08-29
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207DC | 1932 ARTHUR AVENUE RENOVATION - 5TH FLOOR - DOB | 2 | PRELIMINARY DESIGN | 2020-08-30 | 2020-12-27 | 2020-08-30 | 2020-12-27
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207DC | 1932 ARTHUR AVENUE RENOVATION - 5TH FLOOR - DOB | 3 | FINAL DESIGN | 2020-12-28 | 2021-06-25 | 2020-12-28 | 2021-06-25
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207DC | 1932 ARTHUR AVENUE RENOVATION - 5TH FLOOR - DOB | 4 | BID AWARD AND REGISTER CONTRCT | 2021-06-26 | 2021-09-23 | 2021-06-26 | 2021-09-23
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207DC | 1932 ARTHUR AVENUE RENOVATION - 5TH FLOOR - DOB | 5 | CONSTRUCTION TO 25% | 2021-09-24 | 2022-01-21 | 2021-09-24 | 2022-01-21
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207DC | 1932 ARTHUR AVENUE RENOVATION - 5TH FLOOR - DOB | 6 | CONSTRUCTION TO 50% | 2022-01-22 | 2022-05-21 | 2022-01-22 | 2022-05-21
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207DC | 1932 ARTHUR AVENUE RENOVATION - 5TH FLOOR - DOB | 7 | CONSTRUCTION TO 75% | 2022-05-22 | 2022-09-18 | 2022-05-22 | 2022-09-18
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207DC | 1932 ARTHUR AVENUE RENOVATION - 5TH FLOOR - DOB | 8 | ORIGINAL EQUIP & FURNISHING | 2022-09-19 | 2022-12-17 | 2022-09-19 | 2022-12-17
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207DC | 1932 ARTHUR AVENUE RENOVATION - 5TH FLOOR - DOB | 9 | SUBSTANTIAL COMPLETION | 2022-12-18 | 2023-02-15 | 2022-12-18 | 2023-02-15
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207DC | 1932 ARTHUR AVENUE RENOVATION - 5TH FLOOR - DOB | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-02-16 | 2023-03-17 | 2023-02-16 | 2023-03-17
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207EL | 1932 ARTHUR AVE.- ELECTRICAL UPGRADES | 1 | DEVELOP SCOPE | 2017-07-15 | 2017-10-12 | 2021-06-01 | 2021-08-29
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207EL | 1932 ARTHUR AVE.- ELECTRICAL UPGRADES | 2 | PRELIMINARY DESIGN | 2017-10-13 | 2018-02-09 | 2021-08-30 | 2021-12-27
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207EL | 1932 ARTHUR AVE.- ELECTRICAL UPGRADES | 3 | FINAL DESIGN | 2018-02-10 | 2018-08-08 | 2021-12-28 | 2022-06-25
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207EL | 1932 ARTHUR AVE.- ELECTRICAL UPGRADES | 4 | BID AWARD AND REGISTER CONTRCT | 2018-08-09 | 2018-11-06 | 2022-06-26 | 2022-09-23
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207EL | 1932 ARTHUR AVE.- ELECTRICAL UPGRADES | 5 | CONSTRUCTION TO 25% | 2018-11-07 | 2019-03-06 | 2022-09-24 | 2023-01-21
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207EL | 1932 ARTHUR AVE.- ELECTRICAL UPGRADES | 6 | CONSTRUCTION TO 50% | 2019-03-07 | 2019-07-04 | 2023-01-22 | 2023-05-21
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207EL | 1932 ARTHUR AVE.- ELECTRICAL UPGRADES | 7 | CONSTRUCTION TO 75% | 2019-07-05 | 2019-11-01 | 2023-05-22 | 2023-09-18
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207EL | 1932 ARTHUR AVE.- ELECTRICAL UPGRADES | 8 | ORIGINAL EQUIP & FURNISHING | 2019-11-02 | 2020-01-30 | 2021-06-01 | 2021-08-29
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207EL | 1932 ARTHUR AVE.- ELECTRICAL UPGRADES | 9 | SUBSTANTIAL COMPLETION | 2020-01-31 | 2020-03-30 | 2021-08-30 | 2021-10-28
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207EL | 1932 ARTHUR AVE.- ELECTRICAL UPGRADES | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-03-31 | 2020-04-29 | 2021-10-29 | 2024-06-30
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207RF | 1932 ARTHUR AVE.- ROOF | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-08-29 | 2020-06-01 | 2020-08-29
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207RF | 1932 ARTHUR AVE.- ROOF | 2 | PRELIMINARY DESIGN | 2020-08-30 | 2020-12-27 | 2020-08-30 | 2020-12-27
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207RF | 1932 ARTHUR AVE.- ROOF | 3 | FINAL DESIGN | 2020-12-28 | 2021-06-25 | 2020-12-28 | 2021-06-25
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207RF | 1932 ARTHUR AVE.- ROOF | 4 | BID AWARD AND REGISTER CONTRCT | 2021-06-26 | 2021-09-23 | 2021-06-26 | 2021-09-23
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207RF | 1932 ARTHUR AVE.- ROOF | 5 | CONSTRUCTION TO 25% | 2021-09-24 | 2022-01-21 | 2021-09-24 | 2022-01-21
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207RF | 1932 ARTHUR AVE.- ROOF | 6 | CONSTRUCTION TO 50% | 2022-01-22 | 2022-05-21 | 2022-01-22 | 2022-05-21
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207RF | 1932 ARTHUR AVE.- ROOF | 7 | CONSTRUCTION TO 75% | 2022-05-22 | 2022-09-18 | 2022-05-22 | 2022-09-18
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207RF | 1932 ARTHUR AVE.- ROOF | 8 | ORIGINAL EQUIP & FURNISHING | 2022-09-19 | 2022-12-17 | 2022-09-19 | 2022-12-17
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207RF | 1932 ARTHUR AVE.- ROOF | 9 | SUBSTANTIAL COMPLETION | 2022-12-18 | 2023-02-15 | 2022-12-18 | 2023-02-15
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207RF | 1932 ARTHUR AVE.- ROOF | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-02-16 | 2025-03-17 | 2023-02-16 | 2025-03-17
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207TU | 1932 ARTHUR AVENUE- CODE COMPLIANT TOILET UPGRADES | 1 | DEVELOP SCOPE | 2017-07-01 | 2017-09-28 | 2022-06-01 | 2022-08-29
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207TU | 1932 ARTHUR AVENUE- CODE COMPLIANT TOILET UPGRADES | 2 | PRELIMINARY DESIGN | 2017-09-29 | 2018-01-26 | 2022-08-30 | 2022-12-27
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207TU | 1932 ARTHUR AVENUE- CODE COMPLIANT TOILET UPGRADES | 3 | FINAL DESIGN | 2018-01-27 | 2018-07-25 | 2022-12-28 | 2023-06-25
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207TU | 1932 ARTHUR AVENUE- CODE COMPLIANT TOILET UPGRADES | 4 | BID AWARD AND REGISTER CONTRCT | 2018-07-26 | 2018-10-23 | 2023-06-26 | 2023-09-23
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207TU | 1932 ARTHUR AVENUE- CODE COMPLIANT TOILET UPGRADES | 5 | CONSTRUCTION TO 25% | 2018-10-24 | 2019-02-20 | 2024-06-01 | 2024-09-28
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207TU | 1932 ARTHUR AVENUE- CODE COMPLIANT TOILET UPGRADES | 6 | CONSTRUCTION TO 50% | 2019-02-21 | 2019-06-20 | 2024-09-29 | 2025-01-26
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207TU | 1932 ARTHUR AVENUE- CODE COMPLIANT TOILET UPGRADES | 7 | CONSTRUCTION TO 75% | 2019-06-21 | 2019-10-18 | 2025-01-27 | 2025-05-26
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207TU | 1932 ARTHUR AVENUE- CODE COMPLIANT TOILET UPGRADES | 8 | ORIGINAL EQUIP & FURNISHING | 2019-10-19 | 2020-01-16 | 2022-06-01 | 2022-08-29
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207TU | 1932 ARTHUR AVENUE- CODE COMPLIANT TOILET UPGRADES | 9 | SUBSTANTIAL COMPLETION | 2020-01-17 | 2020-03-16 | 2022-08-30 | 2022-10-28
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207TU | 1932 ARTHUR AVENUE- CODE COMPLIANT TOILET UPGRADES | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-03-17 | 2020-04-15 | 2022-10-29 | 2025-06-30
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207W | 1932 ARTHUR AVE.- WINDOWS AND FACADE | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-08-29 | 2020-06-01 | 2020-08-29
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207W | 1932 ARTHUR AVE.- WINDOWS AND FACADE | 2 | PRELIMINARY DESIGN | 2020-08-30 | 2020-12-27 | 2020-08-30 | 2020-12-27
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207W | 1932 ARTHUR AVE.- WINDOWS AND FACADE | 3 | FINAL DESIGN | 2020-12-28 | 2021-06-25 | 2020-12-28 | 2021-06-25
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207W | 1932 ARTHUR AVE.- WINDOWS AND FACADE | 4 | BID AWARD AND REGISTER CONTRCT | 2021-06-26 | 2021-09-23 | 2021-06-26 | 2021-09-23
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207W | 1932 ARTHUR AVE.- WINDOWS AND FACADE | 5 | CONSTRUCTION TO 25% | 2021-09-24 | 2022-01-21 | 2021-09-24 | 2022-01-21
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207W | 1932 ARTHUR AVE.- WINDOWS AND FACADE | 6 | CONSTRUCTION TO 50% | 2022-01-22 | 2022-05-21 | 2022-01-22 | 2022-05-21
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207W | 1932 ARTHUR AVE.- WINDOWS AND FACADE | 7 | CONSTRUCTION TO 75% | 2022-05-22 | 2022-09-18 | 2022-05-22 | 2022-09-18
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207W | 1932 ARTHUR AVE.- WINDOWS AND FACADE | 8 | ORIGINAL EQUIP & FURNISHING | 2022-09-19 | 2022-12-17 | 2022-09-19 | 2022-12-17
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207W | 1932 ARTHUR AVE.- WINDOWS AND FACADE | 9 | SUBSTANTIAL COMPLETION | 2022-12-18 | 2023-02-15 | 2022-12-18 | 2023-02-15
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207W | 1932 ARTHUR AVE.- WINDOWS AND FACADE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-02-16 | 2025-03-17 | 2023-02-16 | 2025-03-17
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77CTCX4 | 2556 BAINBRIDGE AVE- CIVIL SERVICE EXAM TESTING CENTER | 1 | PROJECT START | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77CTCX4 | 2556 BAINBRIDGE AVE- CIVIL SERVICE EXAM TESTING CENTER | 2 | DESIGN START | 2016-07-01 | 2016-12-01 | 2016-07-01 | 2016-12-01
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77CTCX4 | 2556 BAINBRIDGE AVE- CIVIL SERVICE EXAM TESTING CENTER | 3 | DESIGN COMPLETION | 2016-12-02 | 2017-04-01 | 2016-12-02 | 2017-04-01
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77CTCX4 | 2556 BAINBRIDGE AVE- CIVIL SERVICE EXAM TESTING CENTER | 4 | CONSTRUCTION START | 2017-04-02 | 2017-11-30 | 2017-04-02 | 2017-11-30
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77CTCX4 | 2556 BAINBRIDGE AVE- CIVIL SERVICE EXAM TESTING CENTER | 5 | CONSTRUCTION COMPLETION | 2017-12-01 | 2024-12-01 | 2017-12-01 | 2024-12-01
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77X215 | 215 E161 ST.- OFFICE RENOVATIONS | 1 | DEVELOP SCOPE | 2012-06-25 | 2012-09-22 | 2022-06-01 | 2022-08-29
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77X215 | 215 E161 ST.- OFFICE RENOVATIONS | 2 | PRELIMINARY DESIGN | 2012-09-23 | 2013-01-20 | 2022-08-30 | 2022-12-27
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77X215 | 215 E161 ST.- OFFICE RENOVATIONS | 3 | FINAL DESIGN | 2013-01-21 | 2013-07-19 | 2022-12-28 | 2023-06-25
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77X215 | 215 E161 ST.- OFFICE RENOVATIONS | 4 | BID AWARD AND REGISTER CONTRCT | 2013-07-20 | 2013-10-17 | 2023-06-26 | 2023-09-23
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77X215 | 215 E161 ST.- OFFICE RENOVATIONS | 5 | CONSTRUCTION TO 25% | 2013-10-18 | 2014-02-14 | 2023-09-24 | 2024-01-21
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77X215 | 215 E161 ST.- OFFICE RENOVATIONS | 6 | CONSTRUCTION TO 50% | 2014-02-15 | 2014-06-14 | 2024-01-22 | 2024-05-20
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77X215 | 215 E161 ST.- OFFICE RENOVATIONS | 7 | CONSTRUCTION TO 75% | 2014-06-15 | 2014-10-12 | 2024-05-21 | 2024-09-17
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77X215 | 215 E161 ST.- OFFICE RENOVATIONS | 8 | ORIGINAL EQUIP & FURNISHING | 2014-10-13 | 2015-01-10 | 2024-09-18 | 2024-12-16
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77X215 | 215 E161 ST.- OFFICE RENOVATIONS | 9 | SUBSTANTIAL COMPLETION | 2015-01-11 | 2015-03-11 | 2024-12-17 | 2025-02-14
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77X215 | 215 E161 ST.- OFFICE RENOVATIONS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2015-03-12 | 2015-04-10 | 2025-02-15 | 2025-03-16
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD5BA1 | 2556 Bainbridge Ave. Community Ctr. | 1 | DEVELOP SCOPE | 2022-06-01 | 2022-08-29 | 2022-06-01 | 2022-08-29
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD5BA1 | 2556 Bainbridge Ave. Community Ctr. | 2 | PRELIMINARY DESIGN | 2022-08-30 | 2022-12-27 | 2022-08-30 | 2022-12-27
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD5BA1 | 2556 Bainbridge Ave. Community Ctr. | 3 | FINAL DESIGN | 2022-12-28 | 2023-06-25 | 2022-12-28 | 2023-06-25
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD5BA1 | 2556 Bainbridge Ave. Community Ctr. | 4 | BID AWARD AND REGISTER CONTRCT | 2023-06-26 | 2023-09-23 | 2023-06-26 | 2023-09-23
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD5BA1 | 2556 Bainbridge Ave. Community Ctr. | 5 | CONSTRUCTION TO 25% | 2023-09-24 | 2024-01-21 | 2023-09-24 | 2024-01-21
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD5BA1 | 2556 Bainbridge Ave. Community Ctr. | 6 | CONSTRUCTION TO 50% | 2024-01-22 | 2024-05-20 | 2024-01-22 | 2024-05-20
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD5BA1 | 2556 Bainbridge Ave. Community Ctr. | 7 | CONSTRUCTION TO 75% | 2024-05-21 | 2024-09-17 | 2024-05-21 | 2024-09-17
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD5BA1 | 2556 Bainbridge Ave. Community Ctr. | 8 | ORIGINAL EQUIP & FURNISHING | 2024-09-18 | 2024-12-16 | 2024-09-18 | 2024-12-16
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD5BA1 | 2556 Bainbridge Ave. Community Ctr. | 9 | SUBSTANTIAL COMPLETION | 2024-12-17 | 2025-02-14 | 2024-12-17 | 2025-02-14
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD5BA1 | 2556 Bainbridge Ave. Community Ctr. | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2025-02-15 | 2025-03-16 | 2025-02-15 | 2025-03-16
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD5BA2 | 2556 Bainbridge Ave - Fordham Library renovation | 1 | DEVELOP SCOPE | 2017-06-30 | 2017-09-27 | 2022-06-01 | 2022-08-29
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD5BA2 | 2556 Bainbridge Ave - Fordham Library renovation | 2 | PRELIMINARY DESIGN | 2017-09-28 | 2018-01-25 | 2022-08-30 | 2022-12-27
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD5BA2 | 2556 Bainbridge Ave - Fordham Library renovation | 3 | FINAL DESIGN | 2018-01-26 | 2018-07-24 | 2022-12-28 | 2023-06-25
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD5BA2 | 2556 Bainbridge Ave - Fordham Library renovation | 4 | BID AWARD AND REGISTER CONTRCT | 2018-07-25 | 2018-10-22 | 2023-06-26 | 2023-10-23
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD5BA2 | 2556 Bainbridge Ave - Fordham Library renovation | 5 | CONSTRUCTION TO 25% | 2018-10-23 | 2019-02-19 | 2023-10-24 | 2024-02-20
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD5BA2 | 2556 Bainbridge Ave - Fordham Library renovation | 6 | CONSTRUCTION TO 50% | 2019-02-20 | 2019-06-19 | 2024-02-21 | 2024-06-19
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD5BA2 | 2556 Bainbridge Ave - Fordham Library renovation | 7 | CONSTRUCTION TO 75% | 2019-06-20 | 2019-10-17 | 2024-06-20 | 2024-10-17
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD5BA2 | 2556 Bainbridge Ave - Fordham Library renovation | 8 | ORIGINAL EQUIP & FURNISHING | 2019-10-18 | 2020-01-15 | 2024-10-18 | 2025-01-15
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD5BA2 | 2556 Bainbridge Ave - Fordham Library renovation | 9 | SUBSTANTIAL COMPLETION | 2020-01-16 | 2020-03-15 | 2025-01-16 | 2025-03-16
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD5BA2 | 2556 Bainbridge Ave - Fordham Library renovation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2020-03-16 | 2020-04-14 | 2025-03-17 | 2025-04-15
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWXDAVDCC | DCAS/DAVIDSON COMMUNITY CENTER - CONSTRUCT 2 ADDITIONAL FLOO | 1 | DEVELOP SCOPE | 2021-06-01 | 2021-08-29 | 2021-06-01 | 2021-08-29
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWXDAVDCC | DCAS/DAVIDSON COMMUNITY CENTER - CONSTRUCT 2 ADDITIONAL FLOO | 2 | PRELIMINARY DESIGN | 2021-08-30 | 2021-12-27 | 2021-08-30 | 2021-12-27
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWXDAVDCC | DCAS/DAVIDSON COMMUNITY CENTER - CONSTRUCT 2 ADDITIONAL FLOO | 3 | FINAL DESIGN | 2021-12-28 | 2022-06-25 | 2021-12-28 | 2022-06-25
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWXDAVDCC | DCAS/DAVIDSON COMMUNITY CENTER - CONSTRUCT 2 ADDITIONAL FLOO | 4 | BID AWARD AND REGISTER CONTRCT | 2022-06-26 | 2022-09-23 | 2022-06-26 | 2022-09-23
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWXDAVDCC | DCAS/DAVIDSON COMMUNITY CENTER - CONSTRUCT 2 ADDITIONAL FLOO | 5 | CONSTRUCTION TO 25% | 2022-09-24 | 2023-01-21 | 2022-09-24 | 2023-01-21
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWXDAVDCC | DCAS/DAVIDSON COMMUNITY CENTER - CONSTRUCT 2 ADDITIONAL FLOO | 6 | CONSTRUCTION TO 50% | 2023-01-22 | 2023-05-21 | 2023-01-22 | 2023-05-21
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWXDAVDCC | DCAS/DAVIDSON COMMUNITY CENTER - CONSTRUCT 2 ADDITIONAL FLOO | 7 | CONSTRUCTION TO 75% | 2023-05-22 | 2023-09-18 | 2023-05-22 | 2023-09-18
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWXDAVDCC | DCAS/DAVIDSON COMMUNITY CENTER - CONSTRUCT 2 ADDITIONAL FLOO | 8 | ORIGINAL EQUIP & FURNISHING | 2023-09-19 | 2023-12-17 | 2023-09-19 | 2023-12-17
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWXDAVDCC | DCAS/DAVIDSON COMMUNITY CENTER - CONSTRUCT 2 ADDITIONAL FLOO | 9 | SUBSTANTIAL COMPLETION | 2023-12-18 | 2024-02-15 | 2023-12-18 | 2024-02-15
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWXDAVDCC | DCAS/DAVIDSON COMMUNITY CENTER - CONSTRUCT 2 ADDITIONAL FLOO | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2024-02-16 | 2024-03-16 | 2024-02-16 | 2024-03-16
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | S136-434 | DSNY - 720-780 E132 St - Bronx 1 3 4 Garage Rehab | 1 | DEVELOP SCOPE | 2017-03-01 | 2017-05-29 | 2021-06-01 | 2021-08-29
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | S136-434 | DSNY - 720-780 E132 St - Bronx 1 3 4 Garage Rehab | 2 | PRELIMINARY DESIGN | 2017-05-30 | 2017-09-26 | 2021-08-30 | 2021-12-27
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | S136-434 | DSNY - 720-780 E132 St - Bronx 1 3 4 Garage Rehab | 3 | FINAL DESIGN | 2017-09-27 | 2018-03-25 | 2021-12-28 | 2022-06-25
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | S136-434 | DSNY - 720-780 E132 St - Bronx 1 3 4 Garage Rehab | 4 | BID AWARD AND REGISTER CONTRCT | 2018-03-26 | 2018-06-23 | 2022-06-26 | 2022-09-23
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | S136-434 | DSNY - 720-780 E132 St - Bronx 1 3 4 Garage Rehab | 5 | CONSTRUCTION TO 25% | 2018-06-24 | 2018-10-21 | 2022-09-24 | 2023-01-21
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | S136-434 | DSNY - 720-780 E132 St - Bronx 1 3 4 Garage Rehab | 6 | CONSTRUCTION TO 50% | 2018-10-22 | 2019-02-18 | 2023-01-22 | 2023-05-21
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | S136-434 | DSNY - 720-780 E132 St - Bronx 1 3 4 Garage Rehab | 7 | CONSTRUCTION TO 75% | 2019-02-19 | 2019-06-18 | 2023-05-22 | 2023-09-18
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | S136-434 | DSNY - 720-780 E132 St - Bronx 1 3 4 Garage Rehab | 8 | ORIGINAL EQUIP & FURNISHING | 2019-06-19 | 2019-09-16 | 2023-09-19 | 2023-12-17
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | S136-434 | DSNY - 720-780 E132 St - Bronx 1 3 4 Garage Rehab | 9 | SUBSTANTIAL COMPLETION | 2019-09-17 | 2019-11-15 | 2023-12-18 | 2024-02-15
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | S136-434 | DSNY - 720-780 E132 St - Bronx 1 3 4 Garage Rehab | 10 | PUNCHLIST COMPLETE, JOB CLOSED | 2019-11-16 | 2019-12-15 | 2024-02-16 | 2024-03-16
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | SOLARDOS5 | DSNY - PV Installation on Garage - Bronx 9/10/11 | 1 | DEVELOP SCOPE | 2022-06-01 | 2022-06-30 | 2022-06-01 | 2022-06-30
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | SOLARDOS5 | DSNY - PV Installation on Garage - Bronx 9/10/11 | 2 | BID AWARD AND REGISTER CONTRCT | 2022-07-01 | 2022-08-29 | 2022-07-01 | 2022-08-29
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | SOLARDOS5 | DSNY - PV Installation on Garage - Bronx 9/10/11 | 3 | CONSTRUCTION TO 50% | 2022-08-30 | 2023-02-25 | 2022-08-30 | 2023-02-25
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | SOLARDOS5 | DSNY - PV Installation on Garage - Bronx 9/10/11 | 4 | CONSTRUCTION TO 75% | 2023-02-26 | 2023-05-26 | 2023-02-26 | 2023-05-26
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | SOLARDOS5 | DSNY - PV Installation on Garage - Bronx 9/10/11 | 5 | SUBSTANTIAL COMPLETION | 2023-05-27 | 2023-07-25 | 2023-05-27 | 2023-07-25
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | SOLARDOS5 | DSNY - PV Installation on Garage - Bronx 9/10/11 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2023-07-26 | 2023-08-24 | 2023-07-26 | 2023-08-24
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | SOLARPQL2 | DCAS PQL Round 2 (EdEn) | 1 | DEVELOP SCOPE | 2020-06-01 | 2020-06-30 | 2020-06-01 | 2020-06-30
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | SOLARPQL2 | DCAS PQL Round 2 (EdEn) | 2 | BID AWARD AND REGISTER CONTRCT | 2020-07-01 | 2020-08-29 | 2020-07-01 | 2020-08-29
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | SOLARPQL2 | DCAS PQL Round 2 (EdEn) | 3 | CONSTRUCTION TO 50% | 2020-08-30 | 2021-02-25 | 2020-08-30 | 2021-02-25
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | SOLARPQL2 | DCAS PQL Round 2 (EdEn) | 4 | CONSTRUCTION TO 75% | 2021-02-26 | 2021-05-26 | 2021-02-26 | 2021-05-26
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | SOLARPQL2 | DCAS PQL Round 2 (EdEn) | 5 | SUBSTANTIAL COMPLETION | 2021-05-27 | 2021-07-25 | 2021-05-27 | 2021-07-25
20201123 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | SOLARPQL2 | DCAS PQL Round 2 (EdEn) | 6 | PUNCHLIST COMPLETE, JOB CLOSED | 2021-07-26 | 2021-08-24 | 2021-07-26 | 2021-08-24