## Data Definition
Captical Project Detail Data--Dollars
This dataset contains capital commitment plan data by project type, budget line and source of funds. The dollar values are in thousands. The dataset is updated three times a year during the Preliminary, Executive and Adopted Capital Commitment Plans.
FIELD NAME | DISPLAY NAME | DATA TYPE | DESCRIPTION | COMMENTS
PUB_DATE | PUBLICATION DATE |  | DATE OF CAPITAL PROJECT DETAIL DATA PUBLICATION
BORO | BOROUGH |  | BOROUGH (BRONX, BROOKLYN, MANHATTAN, QUEENS, STATEN ISLAND)
MANAGING_AGCY_CD | MANAGING AGENCY CODE |  | THREE DIGIT CODE IDENTIFYING THE CAPITAL PROJECT MANAGING AGENCY
MANAGING_AGCY | MANAGING AGENCY NAME |  | AGENCY NAME THAT WILL MANAGE THE CAPITAL PROJECT
PROJECT_ID | PROJECT ID |  | CAPITAL PROJECT IDENTIFICATION NUMBER
PROJECT_DESCR | PROJECT DESCRIPTION |  | DESCRIPTION OF THE CAPITAL PROJECT
TYP_CATEGORY_NAME | TEN-YEAR PLAN CATEGORY |  | TEN YEAR CAPITAL PLAN CATEGORY
COMMUNITY_BOARD | COMMUNITY BOARDS SERVED |  | COMMUNITY BOARD(S) WHERE A CAPITAL PROJECT IS LOCATED
BUDGET_LINE | BUDGET LINES |  | CAPITAL BUDGET UNIT OF APPROPRIATION
DELAY_DESC | EXPLANATION FOR DELAY |  | REASON FOR A CAPITAL PROJECT DELAY
SITE_DESCR | PROJECT LOCATION |  | CAPITAL PROJECT LOCATION
SCOPE_TEXT | SCOPE SUMMARY |  | SUMMARY DESCRIPTION OF THE WORK TO BE PERFORMED
FY_YR1_PLAN | PLAN YEAR 1 |  | CURRENT FISCAL YEAR
ORIG_BUD_AMT | ORIGINAL BUDGET |  | THE ORIGINAL ESTIMATED COST OF A CAPITAL PROJECT
CITY_PRIOR_ACTUAL | CITY PRIOR ACTUAL |  | YEAR-TO-DATE ACTUAL CITY FUNDED CONTRACT REGISTRATIONS FOR A CAPITAL PROJECT
CITY_YR1_PLAN | CITY PLAN YEAR 1 |  | CITY FUNDS FOR THE FIRST FISCAL YEAR
CITY_YR2_PLAN | CITY PLAN YEAR 2 |  | CITY FUNDS FOR THE SECOND FISCAL YEAR
CITY_YR3_PLAN | CITY PLAN YEAR 3 |  | CITY FUNDS FOR THE THIRD FISCAL YEAR
CITY_YR4_PLAN | CITY PLAN YEAR 4 |  | CITY FUNDS FOR THE FOURTH FISCAL YEAR
CITY_YR5_PLAN | CITY PLAN YEAR 5 |  | CITY FUNDS FOR THE FIFTH FISCAL YEAR
CITY_RTC | CITY RTC |  | TOTAL AMOUNT OF CITY FUNDS REQUIRED TO COMPLETE A CAPITAL PROJECT AFTER THE FIFTH FISCAL YEAR
CITY_PLAN_TOTAL | CITY PLAN TOTAL |  | TOTAL CITY FUNDED PLANNED CONTRACT REGISTRATION(S) FOR A CAPITAL PROJECT
NONCITY_PRIOR_ACTUAL | NON-CITY PRIOR ACTUAL |  | YEAR-TO-DATE ACTUAL NON-CITY FUNDED CONTRACT REGISTRATIONS FOR A CAPITAL PROJECT
NONCITY_YR1_PLAN | NON-CITY PLAN YEAR 1 |  | NON-CITY FUNDS FOR THE FIRST FISCAL YEAR
NONCITY_YR2_PLAN | NON-CITY PLAN YEAR 2 |  | NON-CITY FUNDS FOR THE SECOND FISCAL YEAR
NONCITY_YR3_PLAN | NON-CITY PLAN YEAR 3 |  | NON-CITY FUNDS FOR THE THIRD FISCAL YEAR
NONCITY_YR4_PLAN | NON-CITY PLAN YEAR 4 |  | NON-CITY FUNDS FOR THE FOURTH FISCAL YEAR
NONCITY_YR5_PLAN | NON-CITY PLAN YEAR 5 |  | NON-CITY FUNDS FOR THE FIFTH FISCAL YEAR
NONCITY_RTC | NON-CITY RTC |  | TOTAL AMOUNT OF NON-CITY FUNDS REQUIRED TO COMPLETE A CAPITAL PROJECT AFTER THE FIFTH FISCAL YEAR
NONCITY_PLAN_TOTAL | NON-CITY PLAN TOTAL |  | TOTAL NON- CITY FUNDED PLANNED CONTRACT REGISTRATION(S) FOR A CAPITAL PROJECT

## Data
PUB_DATE | BORO | MANAGING_AGCY_CD | MANAGING_AGCY | PROJECT_ID | PROJECT_DESCR | TYP_CATEGORY_NAME | COMMUNITY_BOARD | BUDGET_LINE | DELAY_DESC | SITE_DESCR | SCOPE_TEXT | FY_YR1_PLAN | ORIG_BUD_AMT | CITY_PRIOR_ACTUAL | CITY_YR1_PLAN | CITY_YR2_PLAN | CITY_YR3_PLAN | CITY_YR4_PLAN | CITY_YR5_PLAN | CITY_RTC | CITY_PLAN_TOTAL | NONCITY_PRIOR_ACTUAL | NONCITY_YR1_PLAN | NONCITY_YR2_PLAN | NONCITY_YR3_PLAN | NONCITY_YR4_PLAN | NONCITY_YR5_PLAN | NONCITY_RTC | NONCITY_PLAN_TOTAL
20190425 | CITYWIDE | 035 | NEW YORK RESEARCH LIBRARY | L103RENO | RESEARCH LIBRARIES - Renovations | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | L-0101 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | NA | RESEARCH LIBRARIES RENOVATION | 2019 | 9045 | 0 | 0 | 0 | 45 | 221 | 334 | 1908 | 2508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 037 | NEW YORK PUBLIC LIBRARY | LN18SYSWI | SYSTEMWIDE LUMP-SUM ALLOCATION | ESSENTIAL RECONSTRUCTION OF FACILITIES | 000 | LN-0008 LN-0101M |  |  | FY18 MAYORAL LUMP SUM ALLOCATION | 2019 | 0 | 0 | 0 | 6710 | 0 | 758 | 3114 | 14657 | 25239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 037 | NEW YORK PUBLIC LIBRARY | LN19CAREN | Carnegie Renovation Overruns | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | LN-0008 |  |  | FUNDING FOR POSSIBLE COST OVERRUNS ASSOCIATED WITH THE COMPREHENSIVE RENOVATIONS OF THE FOLLOWING CARNEGIE BRANCHES: 125TH ST, FORT WASHINGTON, HUNTS POINT, MELROSE, AND PORT RICHMOND | 2019 | 0 | 0 | 0 | 0 | 0 | 3745 | 0 | 0 | 3745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 037 | NEW YORK PUBLIC LIBRARY | LNCOUNCIL | NYC Council funding by District | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | LN-D008 LN-D002 LN-D003 |  |  | NYC COUNCIL FUNDING BY DISTRICT | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 6488 | 0 | 6488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 037 | NEW YORK PUBLIC LIBRARY | LNSYSBFFE | Systemwide FF&E Needs | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | LN-0008 |  |  | FUNDING FOR FF&E NEEDS SYSTEMWIDE | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 158 | 572 | 730 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 037 | NEW YORK PUBLIC LIBRARY | LNSYSBOIL | Systemwide Emergency Boiler Replacement | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | LN-0008 |  |  | FUNDING FOR NECESSARY BOILER REPLACEMENT SYSTEMWIDE. | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 109 | 1450 | 1559 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 037 | NEW YORK PUBLIC LIBRARY | LNSYSFLS | Systemwide Fire/Life Safety | RECONSTRUCTION NECESSARY TO MAINTAIN FACILITIES |  | LN-0008 |  |  | FUNDING FOR FIRE ALARMS AND LIFE SAFETY PROJECTS SYSTEMWIDE | 2019 | 0 | 0 | 0 | 0 | 0 | 383 | 100 | 1550 | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 037 | NEW YORK PUBLIC LIBRARY | LNSYSRFHV | Systemwide Roof/HVAC Replacement and Repair | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | LN-0008 |  |  | FUNDING FOR ROOF AND HVAC REPLACEMENT/REPAIR SYSTEMWIDE (LN-SYSWID) | 2019 | 0 | 0 | 0 | 0 | 0 | 18 | 300 | 3200 | 3518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 037 | NEW YORK PUBLIC LIBRARY | LNSYS-SEC | Systemwide Emergency Security System Needs | RECONSTRUCTION NECESSARY TO MAINTAIN FACILITIES |  | LN-0008 |  |  | FUNDING FOR UNPLANNED SECURITY SYSTEM NEEDS SYSTEMWIDE | 2019 | 0 | 0 | 0 | 0 | 66 | 100 | 100 | 200 | 466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 037 | NEW YORK PUBLIC LIBRARY | LN-SYSWID | SYSTEMWIDE Reconstruction, Roofs, HVAC, Boilers, Life Safety | ESSENTIAL RECONSTRUCTION OF FACILITIES | 000 | LN-0008 |  |  | SYSTEM WIDE RECONSTRUCTION, ROOFS, HVAC, BOILERS, LIFE SAFET | 2019 | 22 | 0 | 0 | 0 | 0 | 1903 | 931 | 7062 | 9896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 040 | DEPARTMENT OF EDUCATION | SANDYCOST | SANDY RELATED WORK | EMERGENCY, INSPECTION AND MISCELLANEOUS | 099 | E-2500 |  | SANDY COST | SANDY RELATED WORK - SCA LUMP SUM | 2019 | 0 | 69843.1 | 757 | 11904 | 0 | 0 | 0 | 0 | 82504.1 | 647581.67 | 9214 | 72282 | 0 | 0 | 0 | 0 | 729077.67
20190425 | CITYWIDE | 040 | DEPARTMENT OF EDUCATION | SCA17 | SCA17 | REHABILITATION OF SCHOOL COMPONENTS | 099 | E-D001 |  | SCA17 | SCA17 | 2019 | 0 | 2753061.26 | 1768 | 0 | 0 | 0 | 0 | 0 | 2754829.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 040 | DEPARTMENT OF EDUCATION | SCA18 | SCA18 | REHABILITATION OF SCHOOL COMPONENTS | 099 | E-D001 |  | SCA18 | SCA18 | 2019 | 0 | 2953770.42 | 1112 | 0 | 0 | 0 | 0 | 0 | 2954882.42 | 476830 | 0 | 0 | 0 | 0 | 0 | 0 | 476830
20190425 | CITYWIDE | 040 | DEPARTMENT OF EDUCATION | SCA19 | SCA19 | REHABILITATION OF SCHOOL COMPONENTS | 000 | E-2364 E-K001 E-M001 E-Q001 E-R001 E-X001 E-4005 E-4006 E-4002 E-M4001 E-D4001 E-D001 E-2361 E-2362 E-2363 E-4001 |  | SCA19 | SCA19 | 2019 | 0 | 0 | 3669242 | 0 | 0 | 0 | 0 | 0 | 3669242 | 0 | 360562 | 0 | 0 | 0 | 0 | 0 | 360562
20190425 | CITYWIDE | 040 | DEPARTMENT OF EDUCATION | SCA20 | SCA20 | REHABILITATION OF SCHOOL COMPONENTS | 000 | E-2365 E-2364 E-K001 E-M001 E-Q001 E-R001 E-X001 E-D001 E-4005 E-4006 E-M4001 |  |  | SCA LUMP SUM | 2019 | 0 | 0 | 0 | 3794083 | 0 | 0 | 0 | 0 | 3794083 | 0 | 0 | 260000 | 0 | 0 | 0 | 0 | 260000
20190425 | CITYWIDE | 040 | DEPARTMENT OF EDUCATION | SCA21 | SCA21 | REHABILITATION OF SCHOOL COMPONENTS | 000 | E-2365 E-2364 |  |  | SCA LUMP SUM | 2019 | 0 | 0 | 0 | 0 | 2829820 | 0 | 0 | 0 | 2829820 | 0 | 0 | 0 | 744080 | 0 | 0 | 0 | 744080
20190425 | CITYWIDE | 040 | DEPARTMENT OF EDUCATION | SCA22 | SCA22 | REHABILITATION OF SCHOOL COMPONENTS | 000 | E-2365 E-2364 |  |  | SCA LUMP SUM | 2019 | 0 | 0 | 0 | 0 | 0 | 3631320 | 0 | 0 | 3631320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 040 | DEPARTMENT OF EDUCATION | SCA23 | SCA23 | REHABILITATION OF SCHOOL COMPONENTS | 000 | E-2365 E-2364 |  |  | SCA LUMP SUM | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 3514380 | 0 | 3514380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 040 | DEPARTMENT OF EDUCATION | SCA24 | SCA24 | REHABILITATION OF SCHOOL COMPONENTS | 000 | E-2365 |  |  | SCA LUMP SUM | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2677330 | 2677330 | 0 | 0 | 0 | 0 | 0 | 0 | 562450 | 562450
20190425 | CITYWIDE | 040 | DEPARTMENT OF EDUCATION | SCA25 | SCA25 | REHABILITATION OF SCHOOL COMPONENTS | 000 | E-2365 |  |  | SCA LUMP SUM | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1174000 | 1174000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 040 | DEPARTMENT OF EDUCATION | SCA26 | SCA26 | REHABILITATION OF SCHOOL COMPONENTS | 000 | E-2365 |  | SCA LUMP SUM | SCA LUMP SUM | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1174000 | 1174000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 040 | DEPARTMENT OF EDUCATION | SCA27 | SCA27 | REHABILITATION OF SCHOOL COMPONENTS | 000 | E-2365 |  | SCA LUMP SUM | SCA LUMP SUM | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1174000 | 1174000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 040 | DEPARTMENT OF EDUCATION | SCA28 | SCA28 | REHABILITATION OF SCHOOL COMPONENTS | 000 | E-2365 |  |  | SCA LUMP SUM | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1220960 | 1220960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 040 | DEPARTMENT OF EDUCATION | SCA29 | SCA29 | REHABILITATION OF SCHOOL COMPONENTS | 000 | E-2365 |  |  | SCA LUMP SUM | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1269798 | 1269798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 040 | DEPARTMENT OF EDUCATION | SOLARGR3 | DOE- Design of 17 Solar Photovoltaic Systems | DISTRIBUTED GENERATION | 000 | PU-0025 |  |  | DOE- DESIGN OF 17 SOLAR PHOTOVOLTAIC SYSTEMS | 2019 | 0 | 1108.16 | 0 | 6501 | 0 | 0 | 0 | 0 | 7609.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 042 | CITY UNIVERSITY | CA207-006 | CUNY Incubator Network | MISCELLANEOUS RECONSTRUCTION | 000 | HN-0206 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | PROVIDE SPACE IN EACH COMMUNITY COLLEGE TO OFFER RESOURCES FOR SMALL BUSINESS OWNERS. | 2019 | 7500 | 0 | 0 | 0 | 3310 | 3850 | 0 | 0 | 7160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BATH | CITYWIDE BATHROOM RENOVATION | POLICE FACILITIES | 000 | PO-0079 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BATHROOM RENOVATION | 2019 | 346 | 36574.96 | 543 | 0 | 0 | 0 | 0 | 0 | 37117.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAHD | BATHROOM RENO AT 67TH, 77TH AND TRAFFIC CONTROL DIVISION | POLICE FACILITIES | 000 | PO-0079 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BATHROOM RENOVATION | 2019 | 1407 | 1344 | 63 | 0 | 0 | 0 | 0 | 0 | 1407 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAHG | ELEVATOR REHABILITATION FOR 20TH, 25TH | POLICE FACILITIES | 000 | PO-0079 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | VARIOUS CITYWIDE | ELEVATOR REHABILITATION | 2019 | 602 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAHI | BOILER REPLACEMENT AT 68TH, 76TH AND 102ND PCTS | POLICE FACILITIES | 000 | PO-0079 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BOILER REPLACEMENTS | 2019 | 1430 | 104.5 | 1325 | 0 | 0 | 0 | 0 | 0 | 1429.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAHY | BOILERS AT 26TH, 42ND & 46TH PRECINCTS | POLICE FACILITIES | 000 | PO-0079 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BOILER REPLACEMENT | 2019 | 1258 | 136.5 | 0 | 1121 | 0 | 0 | 0 | 0 | 1257.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAJC | FACADE REPLACEMENT AND REPAIR 114TH PCT | POLICE FACILITIES | 000 | PO-0079 |  | RANDALL'S CRC AND 114TH PCT | FACADE REPLACEMENT AND REPAIR RANDALL'S CRC AND 114TH PCT | 2019 | 95 | 0 | 0 | 49 | 0 | 0 | 0 | 0 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAJD | FENCE RENO CITYWIDE (32ND, FBF SOD, BOMB SQD, BRNX TOW,TRPD) | POLICE FACILITIES | 000 | PO-0079 |  |  | FENCE RECONSTRUCTION CITYWIDE (32ND, FBF SOD, QNS TOW PND) | 2019 | 560 | 744.51 | 56 | 0 | 0 | 0 | 0 | 0 | 800.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAJZ | 49TH & 115TH & MTN PCT HVAC REPLACEMENT | POLICE FACILITIES | 000 | PO-0079 |  |  | ESTIMATES | 2019 | 2755 | 0 | 0 | 2755 | 0 | 0 | 0 | 0 | 2755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAKA | 75TH, 76TH, 84TH AND 105TH PCT PARKING LOTS | POLICE FACILITIES | 000 | PO-0079 |  |  | 75TH, 76TH, 84TH AND 105TH PCT PARKING LOT | 2019 | 700 | 0 | 700 | 0 | 0 | 0 | 0 | 0 | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAKF | SRG4 AND CAC BATHROOM RENOVATION | POLICE FACILITIES | 000 | PO-0079 |  |  | ESTIMATE | 2019 | 487 | 0 | 487 | 0 | 0 | 0 | 0 | 0 | 487 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79CWAC | CITYWIDE HVAC PROGRAM | POLICE FACILITIES | 000 | PO-0079 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | CITYWIDE | HVAC | 2019 | 20800 | 354 | 0 | 15446 | 5000 | 0 | 0 | 0 | 20800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79FATS | FIREARMS TACTICAL TRAINING CENTERS | POLICE FACILITIES | 000 | PO-0079 |  | CITYWIDE | TRAINING CENTERS | 2019 | 9614 | 320.44 | 9294 | 0 | 0 | 0 | 0 | 0 | 9614.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79LOCK | CITYWIDE LOCKER ROOM RENOVATION | POLICE FACILITIES | 000 | PO-0079 |  | CITYWIDE | LOCKER ROOMS | 2019 | 59699 | 20825.32 | 19261 | 19613 | 0 | 0 | 0 | 0 | 59699.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79TIME | TIMES SQUARE STATION RENOVATION | POLICE FACILITIES | 000 | PO-0079 |  | TIMES SQUARE | RENOVATION | 2019 | 1500 | 4879.45 | 503 | 0 | 0 | 0 | 0 | 0 | 5382.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 056 | POLICE DEPARTMENT | SANDCONDT | ELECTRICAL CONDUIT REPLACEMENT (SANDY) | POLICE FACILITIES |  | PO-0079 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ELECTRICAL | 2019 | 30329 | 0 | 404 | 0 | 0 | 0 | 0 | 0 | 404 | 0 | 3781 | 0 | 0 | 0 | 0 | 0 | 3781
20190425 | CITYWIDE | 057 | FIRE DEPARTMENT | F175EMS20 | EMS 20 EXPANSION AND RENOVATON | NEW FACILITIES AND RENOVATIONS | 000 | F-0175 |  |  | EMS 20 EXPANSION AND RENOVATON | 2019 | 3000 | 336.89 | 7670 | 0 | 0 | 0 | 0 | 0 | 8006.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 057 | FIRE DEPARTMENT | F175EMS4M | MULTI COMPONENT RENOVATIONS - EMS 4 | NEW FACILITIES AND RENOVATIONS | 000 | F-0175 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES |  | MULTI COMPONENT RENOVATIONS - EMS 4 | 2019 | 3576 | 446.9 | 47 | 0 | 3244 | 0 | 0 | 0 | 3737.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 057 | FIRE DEPARTMENT | F175MC153 | MULTI COMPONENT RENOVATIONS - EC153 | NEW FACILITIES AND RENOVATIONS | 000 | F-0175 |  |  | MULTI COMPONENT RENOVATIONS - EC153 | 2019 | 3070 | 343.58 | 0 | 2725 | 0 | 0 | 0 | 0 | 3068.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 057 | FIRE DEPARTMENT | F175MC227 | Multi - Component Renovaitons - EC 227 | NEW FACILITIES AND RENOVATIONS | 000 | F-0175 |  |  | MULTI - COMPONENT RENOVAITONS - EC 227 | 2019 | 7148 | 9424.59 | 699 | 0 | 0 | 0 | 0 | 0 | 10123.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 057 | FIRE DEPARTMENT | F175MC253 | MULTI COMPONENT RENOVATIONS - EC253 | NEW FACILITIES AND RENOVATIONS | 000 | F-0175 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | MULTI COMPONENT RENOVATIONS - EC253 | 2019 | 4471 | 564.78 | 8005 | 728 | 0 | 0 | 0 | 0 | 9297.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 057 | FIRE DEPARTMENT | F175TOI24 | Female Firefighter Toilet Upgrade - EC24 | NEW FACILITIES AND RENOVATIONS | 000 | F-0175 |  |  | FEMALE FIREFIGHTER TOILET UPGRADE - EC24 | 2019 | 1348 | 1315 | 2615 | 0 | 0 | 0 | 0 | 0 | 3930 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 057 | FIRE DEPARTMENT | F175WP202 | Roof and Waterproofing Project - EC202 | NEW FACILITIES AND RENOVATIONS | 000 | F-0175 |  |  | ROOF AND WATERPROOFING PROJECT - EC202 | 2019 | 1311 | 1431.73 | 0 | 117 | 0 | 0 | 0 | 0 | 1548.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 057 | FIRE DEPARTMENT | F175WP276 | WATERPROOFING - EC276 | NEW FACILITIES AND RENOVATIONS | 000 | F-0175 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | WATERPROOFING - EC276 | 2019 | 2329 | 2155.71 | 421 | 1068 | 0 | 0 | 0 | 0 | 3644.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 057 | FIRE DEPARTMENT | F175WPE46 | Roof and Waterproofing Project - EC46 | NEW FACILITIES AND RENOVATIONS | 000 | F-0175 |  |  | ROOF AND WATERPROOFING PROJECT - EC46 | 2019 | 1698 | 232.53 | 0 | 1504 | 0 | 0 | 0 | 0 | 1736.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 057 | FIRE DEPARTMENT | F1GAZ1901 | Gazebo - Manholes Project at 4th Ave. | COMMUNICATIONS | 000 | F-0001 |  |  | GAZEBO - MANHOLES PROJECT AT 4TH AVE. | 2019 | 456 | 0 | 456 | 0 | 0 | 0 | 0 | 0 | 456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 057 | FIRE DEPARTMENT | F204WATER | Randall's Island Water Tank Replacement | NEW FACILITIES AND RENOVATIONS | 000 | F-0204 |  |  | RANDALL'S ISLAND WATER TANK REPLACEMENT | 2019 | 1140 | 193.32 | 0 | 1000 | 0 | 0 | 0 | 0 | 1193.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 057 | FIRE DEPARTMENT | FDNYMAR1 | Waterfront Program - Marine 1 | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 000 | PU-0200 |  |  | WATERFRONT PROGRAM - MARINE 1 | 2019 | 0 | 0 | 0 | 0 | 846 | 0 | 0 | 0 | 846 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 057 | FIRE DEPARTMENT | FDNYMAR4 | Waterfront program - Marine 4 | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 000 | PU-0200 |  |  | WATERFRONT PROGRAM - MARINE 4 | 2019 | 0 | 0 | 0 | 0 | 347 | 0 | 0 | 0 | 347 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 057 | FIRE DEPARTMENT | FDNYMAR9 | Waterfront Program - Marine 9 | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 000 | PU-0200 |  |  | WATERFRONT PROGRAM - MARINE 9 | 2019 | 0 | 0 | 0 | 0 | 848 | 0 | 0 | 0 | 848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 057 | FIRE DEPARTMENT | SANDHM265 | HURRICANE SANDY HAZMAT MITIGATION-EC265 | NEW FACILITIES AND RENOVATIONS | 000 | F-0175 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES |  | HURRICANE SANDY HAZMAT MITIGATION-EC265 | 2019 | 1216 | 20.75 | 0 | 172 | 0 | 0 | 0 | 0 | 192.75 | 186.81 | 0 | 1548 | 0 | 0 | 0 | 0 | 1734.81
20190425 | CITYWIDE | 057 | FIRE DEPARTMENT | SANDHM266 | HURRICANE SANDY HAZMAT MITIGATION - EC266 | NEW FACILITIES AND RENOVATIONS | 000 | F-0175 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES |  | HURRICANE SANDY HAZMAT MITIGATION - EC266 | 2019 | 946 | 10.07 | 0 | 85 | 0 | 0 | 0 | 0 | 95.07 | 90.64 | 0 | 765 | 0 | 0 | 0 | 0 | 855.64
20190425 | CITYWIDE | 068 | ADMIN FOR CHILDREN'S SERVICES | ACSPDF | Renovation projects for field offices | SOCIAL SERVICE BUILDINGS | 000 | CS-0003 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RENOVATION PROJECTS FOR FIELD OFFICES: PAINTING, NEW FLOORING, NEW CEILING SYSTEMS, AS WELL AS, PURCHASE AND INSTALLATION OF NEW MODULAR SYSTEMS FURNITURE AND ASSOCIATED EQUIPMENT | 2019 | 14821 | 0 | 0 | 0 | 0 | 2177 | 2526 | 7091 | 11794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 068 | ADMIN FOR CHILDREN'S SERVICES | CCREN | Renovation for city leased child care sites. | CHILD WELFARE FACILITIES | 000 | CS-0002 |  |  |  | 2019 | 37324 | 0 | 1000 | 5589 | 1077 | 2245 | 16600 | 0 | 26511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 068 | ADMIN FOR CHILDREN'S SERVICES | DCSTRUC | DAY CARE RENOVATION | DAY CARE FACILITIES | 000 | CS-0002 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | DAY CARE STRUCTUAL RENOVATION | VARIOUS SITE RENOVATIONS | 2019 | 28195 | 0 | 0 | 0 | 3802 | 1267 | 2534 | 9400 | 17003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 071 | DEPT OF HOMELESS SERVICES | HH-MRBU | MAJOR REPAIRS AND BLD UPGRADES | SHELTERS FOR HOMELESS INDIVIDUALS | 000 | HH-0112 HH-0115 |  |  |  | 2019 | 0 | 0 | 1534 | 14145 | 500 | 1281 | 29474 | 154197 | 201131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 071 | DEPT OF HOMELESS SERVICES | HRCN100VA | Volunteers of America | SHELTERS FOR HOMELESS FAMILIES | 000 | HH-D025 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | IMPROVEMENTS TO VARIOUS DOMESTIC VIOLENCE SHELTERS. (CONSTRUCTION COSTS) | 2019 | 908 | 0 | 182 | 726 | 0 | 0 | 0 | 0 | 908 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 072 | DEPARTMENT OF CORRECTION | C11421STC | NEW JAIL FACILITIES | New Jail Facilities | 000 | C-0114 |  |  | 21ST CENTURY DEPARTMENT OF CORRECTION PLAN | 2019 | 1065627 | 0 | 0 | 201835 | 392351 | 823263 | 2226316 | 5102397 | 8746162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 072 | DEPARTMENT OF CORRECTION | C114ACADY | Construction of a New Training Academy | SUPPORT SPACE | 000 | C-0114 |  |  | CONSTRUCTION OF NEW ACADEMY BUILDING | 2019 | 100600 | 0 | 0 | 10000 | 90000 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 072 | DEPARTMENT OF CORRECTION | C75ADAOBC | ADA Compliance for OBCC | BUILDING SYSTEMS AND INFRASTRUCTURE | 000 | C-0075 |  |  | MODIFICATION OF FACILITY 'S ENTRANCE TO ENSURE COMPLIANCE WITH THE AMERICANS WITH DISABILITIES ACT (ADA). | 2019 | 5602 | 39.59 | 0 | 4971 | 0 | 0 | 0 | 0 | 5010.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 072 | DEPARTMENT OF CORRECTION | C75GENREP | Installation of Replacement Generators RNDC, EMTC,GMDC,RMSC | EQUIPMENT |  | C-0075 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  |  | 2019 | 12540 | 727.21 | 0 | 10753 | 0 | 0 | 0 | 0 | 11480.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 072 | DEPARTMENT OF CORRECTION | C-75MISC | MISC INFRASTRUCTURE RECON | BUILDING SYSTEMS AND INFRASTRUCTURE | 000 | C-0075 |  | CITYWIDE | MISCELLANIOUS ITEMSMISCELLANIOUS PROJECETS FOR C-75 BUDGET LINE | 2019 | 425881 | 480.24 | 0 | 20425 | 25544 | 108055 | 44189 | 120299 | 318992.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 072 | DEPARTMENT OF CORRECTION | C75POWRF | Replace 5 and 27 KV Feeders | BUILDING SYSTEMS AND INFRASTRUCTURE |  | C-0075 |  |  | REPLACE 5 AND 27 KV ELECTRICAL POWER FEEDERS AT RI. | 2019 | 5950 | 376.72 | 0 | 4350 | 563 | 0 | 0 | 0 | 5289.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 096 | HUMAN RESOURCES ADMINISTRATION | HR25EFOY | HRA FACILITIES & EQUIPMENT OUTYEARS FOR UPGRADES | SOCIAL SERVICES BUILDINGS | 000 | HR-0025 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | CITYWIDE | CITYWIDE FACILITIES AND EQUIPMENT UPGRADES IN OUT YEARS | 2019 | 35921 | 0 | 0 | 0 | 0 | 0 | 0 | 16789 | 16789 | 0 | 0 | 0 | 0 | 0 | 0 | 4813 | 4813
20190425 | CITYWIDE | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467-EMR | DCA - EMERGENCY CAPITAL FUND FOR DCA | ESSENTIAL RECONSTRUCTION OF FACILITIES | 099 | PV-0467 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | DEPARTMENT OF CULTURAL AFFAIRS/ALL CULTURAL INSTITUTIONS 2 COLUMBUS CIRCLE NEW YORK, NY 10019 | EMERGENCY CAPITAL FUNDS TO BE USED FOR EMERGENCY REPAIRS AT INSTITUTIOREMOVE IMMEDIATE BUILDING CODE VIOLATIONS, CORRECT UNSAFE HAZARDS TO TC, AND ASBESTOS REMOVAL | 2019 | 30478 | 0 | 0 | 250 | 2250 | 5000 | 3500 | 32512 | 43512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PVDCLAEMR | DCLA Emergency FY18 | FINANCING COSTS | 000 | PV-0467 |  |  | RES | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4116 | 4116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PVSHEBLT1 | SBLT - She Built NY Project 1 | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | PV-0467 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RENOVATION | 2019 | 1000 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | ACQFUND | Acquistion Fund | NEIGHBORHOOD REVITALIZATION | 000 | ED-0075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ACQUISITION FUND | 2019 | 68500 | 0 | 0 | 1000 | 4000 | 51500 | 0 | 0 | 56500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | C5234 | Pier 11 Intermodal Ferry | RECONSTRUCTION OF FERRY TERMINAL FACILITIES | 000 | FA-0027 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  |  | 2019 | 19350 | 1234.89 | 0 | 43 | 0 | 0 | 0 | 0 | 1277.89 | 3215.63 | 0 | 0 | 0 | 851 | 0 | 0 | 4066.63
20190425 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | C5234A | Pier 11 Intermodal Ferry | RECONSTRUCTION OF FERRY TERMINAL FACILITIES | 000 | FA-0027 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | PIER 11, MANHATTAN | ADA RELATED WORK,PLUMBING | 2019 | 600 | 508.19 | 0 | 0 | 0 | 92 | 0 | 0 | 600.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | CLEANYC | CleaNYC - Graffiti Free Trucks | MISCELLANEOUS | 000 | ED-0075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CLEANYC - GRAFFITI FREE TRUCKS | 2019 | 2500 | 1953 | 0 | 807 | 0 | 0 | 0 | 0 | 2760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | CWFSBARGE | New York City Ferry Barges | WATERFRONT DEVELOPMENT | 000 | ED-0409 |  |  | CITYIWDE FERRY SERVICE BARGES | 2019 | 55000 | 65791.2 | 47755 | 25000 | 3000 | 0 | 0 | 0 | 141546.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | CWFSFERRY | New York City Ferry - Ferry Purchase and Upgrade | WATERFRONT DEVELOPMENT | 000 | ED-0409 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CITYWIDE FERRY SERVICE FERRY PURCHASE (4) | 2019 | 11600 | 6000 | 0 | 500 | 0 | 5100 | 0 | 0 | 11600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | FSHELTER | East River Ferry Service Passenger Shelters | MISCELLANEOUS | 000 | FA-D001 FA-0027 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | WILLIAMSBURG FERRY SHELTERS | 2019 | 100 | 81.31 | 18 | 0 | 0 | 400 | 0 | 0 | 499.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | INDUSFUND | Industrial Fund | INDUSTRIAL DEVELOPMENT | 000 | ED-0404 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | INDUSTRIAL FUND | 2019 | 41000 | 0 | 11000 | 1000 | 1000 | 10000 | 5000 | 3000 | 31000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | INFRAHOUS | Housing Fund | NEIGHBORHOOD REVITALIZATION | 000 | ED-0075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | HOUSING FUND | 2019 | 512172 | 0 | 0 | 8881 | 37237 | 120598 | 94689 | 100000 | 361405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | INFRANEIG | Neighborhood Fund | NEIGHBORHOOD REVITALIZATION | 000 | ED-0384 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NEIGHBORHOOD FUND | 2019 | 630821 | 0 | 0 | 0 | 0 | 89136 | 91104 | 120648 | 300888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | LOWMANHUD | East River Waterfront | COMMERCIAL DEVELOPMENT | 000 | ED-0075 SE-0002M WM-0001 HW-0001M HW-0001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | REDEVELOPMENT | 2019 | 137980 | 6849.33 | 1883 | 0 | 0 | 0 | 0 | 0 | 8732.33 | 143704.97 | 6130 | 4732 | 0 | 0 | 0 | 0 | 154566.97
20190425 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | PASSSHIP2 | Passenger Ship Terminal - Cruise Industry Develp. | PORT DEVELOPMENT | 000 | ED-0409 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | MANHATTAN | DEVELOPMENT | 2019 | 148871 | 194807.14 | 0 | 0 | 0 | 0 | 0 | 0 | 194807.14 | 7297.5 | 197 | 0 | 0 | 0 | 0 | 0 | 7494.5
20190425 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | PFLANDING | Rehabilitation of Ferry Landings | RECONSTRUCTION OF FERRY TERMINAL FACILITIES | 000 | FA-0027 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ADA REHAB | 2019 | 3600 | 2923.48 | 0 | 75 | 0 | 0 | 0 | 0 | 2998.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | PSG6-7 | Port Security Grant Funds | MISCELLANEOUS | 000 | ED-0075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | PORT SECURITY GRANT FUNDS ROUND 6 & 7 | 2019 | 5469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5414.75 | 0 | 53 | 0 | 0 | 0 | 0 | 5467.75
20190425 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | RBWTRMAIN | Rockaway Boardwalk - Water Main Improvement | MISCELLANEOUS |  | WM-0006 |  |  | ROCKAWAY BOARDWALK - WATER MAIN IMPROVEMENT | 2019 | 1390 | 1389.7 | 1390 | 0 | 0 | 0 | 0 | 0 | 2779.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND000 | Project Management for NYC Health + Hospitals Sandy Projects | MISCELLANEOUS |  | HO-0214 |  |  | H+H SANDY MITIGATION | 2019 | 57008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39513.13 | 0 | 17503 | 0 | 0 | 0 | 0 | 57016.13
20190425 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDEDCAM | EDC - Hurricane Sandy - Asset Management | MISCELLANEOUS | 000 | ED-0075 |  |  | REPAIRS TO EDC-MANAGED CITY-OWNED PROPERTY CAUSED BY HURRICANE SANDY | 2019 | 94081 | 0 | 0 | 0 | 0 | 0 | 11570 | 0 | 11570 | 0 | 0 | 4010 | 2761 | 2761 | 20762 | 0 | 30294
20190425 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDY4-03 | Sandy - Rockaway Beach: Long-Term RC | MISCELLANEOUS | 000 | P-1018 |  |  | SANDY - ROCKAWAY BEACH: LONG-TERM RC | 2019 | 341379 | 1.84 | 0 | 0 | 0 | 0 | 0 | 0 | 1.84 | 319546.74 | 0 | 0 | 0 | 0 | 0 | 20584 | 340130.74
20190425 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | TENANTIMP | Tenant Improvement Fund | INDUSTRIAL DEVELOPMENT |  | ED-0380 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | TENANT IMPROVEMENT FUND - 100K JOBS PLAN | 2019 | 7500 | 0 | 0 | 0 | 0 | 5700 | 1800 | 0 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM11IHWH | INSTANTANEOUS HOT WATER HEATERS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE |  | HA-0001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | INSTALL INSTANTANEOUS HOT WATER HEATERS AT VARIOUS DEVELOPMENTS | 2019 | 25000 | 3952.67 | 25518 | 0 | 0 | 0 | 0 | 0 | 29470.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM13GCON | GENERAL CONSTRUCTION CITYWIDE | LOW TO MODERATE INCOME PUBLIC HOUSING REHAB/RECONSTRUCTION | 000 | HA-0001 |  |  | GENERAL CONSTRUCTION CITYWIDE | 2019 | 4551 | 0 | 96298 | 10000 | 10000 | 10000 | 10000 | 40000 | 176298 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM13VAEL | CITYWIDE REPAIRS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 000 | HA-0001 HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CITYWIDE REPAIRS | 2019 | 10000 | 9870.93 | 1213 | 0 | 0 | 0 | 0 | 0 | 11083.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM14VAUP | Major Renovations-Brickwork and Roofs at Sotomayer Houses | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 000 | HA-D001 HA-0001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | OPERATIONS AND MAINTENANCE | 2019 | 10000 | 7516.12 | 30455 | 0 | 0 | 0 | 0 | 0 | 37971.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM15HMLS | HOMELESS INITIATIVE | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 000 | HA-0001 |  |  | REHABILITATE 200 NYCHA UNITS | 2019 | 16940 | 14720.23 | 5862 | 0 | 0 | 0 | 0 | 0 | 20582.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM15SCVA | SECURITY ENHANCEMENTS AT VARIOUS LOCATIONS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE |  | HA-D001 |  |  | SECURITY ENHANCEMENTS AT VARIOUS LOCATIONS | 2019 | 10000 | 8433.43 | 1566 | 0 | 0 | 0 | 0 | 0 | 9999.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM15SLVA | SECURITY INITIATIVES - LIGHTING AT VARIOUS DEVELOPMENTS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 000 | HA-0001 |  |  | EXTERIOR SITE LIGHTING UPGRADES AT VARIOUS DEVELOPMENTS | 2019 | 25000 | 46588.38 | 8911 | 0 | 0 | 0 | 0 | 0 | 55499.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM16MRVR | ROOF WORK TO PREVENT MOLD AT VARIOUS DEVELOPMENTS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE |  | HA-0001 |  |  | MOLD REMOVAL AT VARIOUS DEVELOPMENTS | 2019 | 300000 | 211090.46 | 249911 | 111000 | 61000 | 111000 | 111000 | 445000 | 1300001.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18BOIL | MOBLE BOILERS AT VARIOUS NYCHA DEVELOPMENTS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE |  | HA-0001 |  | CITIWIDE | MOBLE BOILERS AT VARIOUS NYCHA DEVELOPMENTS CITIWIDE | 2019 | 0 | 1499.85 | 7800 | 0 | 0 | 0 | 0 | 0 | 9299.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CDCP | BUILDING IMPROVEMENTS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE |  | HA-0001 |  |  | FUNDING FOR REHABILITATION AND CAPITAL REPAIRS TO NYCHA DEVELOPMENTS | 2019 | 0 | 0 | 250000 | 250000 | 250000 | 250000 | 200000 | 1000000 | 2200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CSVA | CONCRETE SLABS AT VARIOUS DEVELOPMENTS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 000 | HA-0001 |  |  | CONCRETE SLABS | 2019 | 17941 | 0 | 16310 | 0 | 0 | 0 | 0 | 0 | 16310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18HEAT | HEATING SYSTEM IMPROVEMENTS AT NYCHA DEVELOPMENTS CITYWIDE | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 000 | HA-0001 |  |  | HEATING SYSTEM IMPROVEMENTS AT NYCHA DEVELOPMENTS CITYWIDE | 2019 | 0 | 0 | 156878 | 43122 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18IHWH | INSTANTANEOUS HOT WATER HEATERS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 000 | HA-0001 |  |  | INSTALL INSTANTANEOUS HOT WATER HEATERS | 2019 | 7642 | 0 | 7642 | 0 | 0 | 0 | 0 | 0 | 7642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18PNAP | Gas Risers | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE |  | HA-0001 |  |  | GAS RISERS | 2019 | 0 | 0 | 8689 | 0 | 0 | 0 | 0 | 0 | 8689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18RAEX | EXTERNAL COMPACTORS-BULK CRUSHERS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE |  | HA-0001 |  |  | INSTALL EXTERNAL COMPACTORS AND BULK CRUSHERS | 2019 | 0 | 0 | 3050 | 0 | 0 | 0 | 0 | 0 | 3050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18RSPL | Plumbing repairs at six developments citywide | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 000 | HA-0001 |  |  | GAS RISER REPLACEMENT AT GRANT, PATTERSON, WASHINGTON HOUSES, AND DOUGLASS I, AND UNDERGROUND FIRE AND WATER LINES AT MITCHEL AND VAN DYKE | 2019 | 0 | 0 | 38533 | 0 | 0 | 0 | 0 | 0 | 38533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM19DGV2 | DIGITAL VAN | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 000 | HA-M001 |  |  | FUNDING FOR DIGITAL VAN | 2019 | 0 | 0 | 160 | 0 | 0 | 0 | 0 | 0 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | CMERADIOS | OCME - Upgrade of Radio Communications System | OCME | 000 | HL-0083 |  |  |  | 2019 | 5834 | 0 | 5835 | 0 | 0 | 0 | 0 | 0 | 5835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82VCLIN | EMERGENCY FUNDING FOR VARIOUS CLINICS | CLINIC RENOVATION AND REHABILITATION | 000 | HL-0082 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RENOVATE VARIOUS HEALTH CENTERS | 2019 | 41723 | 4559.92 | 0 | 0 | 0 | 0 | 0 | 72420 | 76979.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 819 | HEALTH AND HOSPITALS CORP | 02201601 | HHC PRIMARY HEALTH CLINICS | ROUTINE RECONSTRUCTION |  | HO-0214 |  |  | EXPAND CAPACITY IN EXISTING CLINICS AND BUILD NEW CLINICS IN UNDERSERVED AREAS. | 2019 | 0 | 0 | 2000 | 50188 | 52473 | 0 | 0 | 0 | 104661 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 819 | HEALTH AND HOSPITALS CORP | 02201602 | UPGRADE IDF AND MDF ROOMS (LAN ENVIRONMENTALS) | ROUTINE RECONSTRUCTION |  | HO-0214 |  | CORPORATE-WIDE | THIS IS A CENTRAL OFFICE INITIATIVE MANAGED BY THE OFFICE OF FACILITIES DEVELOPMENT, WORKING WITH ENTERPRISE IT SERVICES MANAGEMENT, TO UPGRADE THE IMMEDIATE DISTRIBUTION FRAME (IDF) AND MEDIUM DISTRIBUTION FRAME (MDF) ROOMS AT VARIOUS FACILITIES THROUGHOUT THE PUBLIC HEALTH CARE SYSTEM. | 2019 | 8768 | 0 | 6768 | 2000 | 0 | 0 | 0 | 0 | 8768 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 819 | HEALTH AND HOSPITALS CORP | 72201602 | CORRECTIONAL HEALTH: MINI CLINICS | ROUTINE RECONSTRUCTION |  | HO-0214 |  | TBD | CORRECTIONAL HEALTH: MINI CLINICS | 2019 | 0 | 0 | 400 | 400 | 400 | 0 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 819 | HEALTH AND HOSPITALS CORP | HL82DISHC | DISTRICT HEALTH CENTER | CLINIC RENOVATION AND REHABILITATION |  | HL-0082 |  |  | DISTRICT HEALTH CENTER RENOVATION | 2019 | 0 | 0 | 1600 | 0 | 0 | 0 | 0 | 0 | 1600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 819 | HEALTH AND HOSPITALS CORP | HOPROJCTS | MISCELLANEOUS CONSTRUCTION PROJECTS | ROUTINE RECONSTRUCTION | 000 | HO-0214 |  | 55 WATER STREET, 25TH FL, NEW YORK, NY 10041 | FUNDING FOR THIS PROJECT WILL FINANCE CONSTRUCTION RENOVATION PROJECTS AND MEDICAL EQUIPMENT ACQUISITIONS THROUGHOUT THE HHC FACILITIES | 2019 | 0 | 0 | 0 | 0 | 12051 | 102553 | 67500 | 223913 | 406017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 819 | HEALTH AND HOSPITALS CORP | SANDDR | HHC Sandy CDBG-DR Match | ROUTINE RECONSTRUCTION | 000 | HO-0214 |  | N/A | HHC SANDY CDBG-DR MATCH | 2019 | 0 | 0 | 0 | 0 | 23802 | 45000 | 0 | 0 | 68802 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 819 | HEALTH AND HOSPITALS CORP | SANDNEW | MISC CORPORATE-WIDE RECONSTRUCTION AS A RESULT OF SANDY | ROUTINE RECONSTRUCTION |  | HO-0214 |  | N/A | ADDITIONAL $410M FOR HHC FOR CORPORATE-WIDE RECONSTRUCTION PROJECTS NECESSITATED BY HURRICANE SANDY - PLACEHOLDER. | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 1183 | 0 | 1183 | 0 | 27393 | 90346 | 192141 | 150856 | 45810 | 0 | 506546
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | ACEDEP504 | HVAC Upgrades at Grahamsville WWTP | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT |  | PU-0025 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | UPSTATE | 2019 | 470 | 0 | 0 | 451 | 0 | 0 | 0 | 0 | 451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | ACEDEP505 | HVAC Upgrades at Margaretville WWTP | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT |  | PU-0025 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | SQ FT | 2019 | 730 | 0 | 0 | 701 | 0 | 0 | 0 | 0 | 701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | ACEDEP507 | Replacement of Existing Plant HVAC at Tannersville | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT |  | PU-0025 |  |  | REPLACE ROOFTOP HEATING AIR HANDLING AND EXHAUST UNITS NEAR END OF USEFUL LIFE WITH MORE EFFICIENT UNITS. REPLACE SINGLE SPEED UNITS WITH DUAL SPEED UNITS TO ELIMINATE UNNECESSARY AIR EXCHANGES AND RELATED HEAT LOSSES. REPLACE SOME UNITS NOW USING 100% OUTSIDE AIR WITH UNITS CAPABLE OF RE-CIRCULATION UP TO 66% INSIDE AIR TO REDUCE RELATED HEAT LOSSES. MAKE RELATED, SUPPORTING ALTERATIONS IN CONTROLS AND DUCTWORK. | 2019 | 7056 | 0 | 7056 | 0 | 0 | 0 | 0 | 0 | 7056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | ACEDEP701 | DEP- DEMAND CONTROLLED VENTILATION UPGRADE | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 000 | PU-0025 |  |  | DEP- DEMAND CONTROLLED VENTILATION UPGRADE | 2019 | 248 | 0 | 0 | 248 | 0 | 0 | 0 | 0 | 248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | AGRI-13 | FAD 13-17 WAP and Forestry | WATER QUALITY PRESERVATION | 000 | WM-0030 |  |  | FAD 13-17 WAP AND FORESTRY | 2019 | 42000 | 28599.37 | 84 | 0 | 0 | 0 | 0 | 0 | 28683.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | AGRI-18 | FAD 18-22 WAP AND FORESTRY | FILTRATION AVOIDANCE DETERMINATION | 000 | WM-0030 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | FAD 18-22 WAP AND FORESTRY | 2019 | 56000 | 0 | 40765 | 5000 | 10000 | 5985 | 0 | 0 | 61750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | AIR-MON | Air Monitoring Analysis | FACILITY PURCHASES AND RECONSTRUCTION |  | EP-0006 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | AIR MONITORING ANALYSIS | 2019 | 6000 | 1019.17 | 481 | 0 | 0 | 0 | 0 | 0 | 1500.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | AIR-MON1 | Air Monitoring Analysis | FACILITY PURCHASES AND RECONSTRUCTION |  | EP-0006 |  |  | AIR MONITORING ANALYSIS | 2019 | 1500 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | AIR-MON2 | Air Monitoring Analysis | FACILITY PURCHASES AND RECONSTRUCTION |  | EP-0006 |  |  | AIR MONITORING ANALYSIS | 2019 | 1500 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | ASB-REM | Asbestos Removal | FACILITY PURCHASES AND RECONSTRUCTION |  | EP-0006 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ASBESTOS REMOVAL | 2019 | 7900 | 1929.49 | -318 | 2500 | 0 | 3000 | 0 | 0 | 7111.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | AWT2-CARB | CONSTRUCTION OF CARBON ADDITION FACILITY AT VARIOUS WWTPs | BIOLOGICAL NUTRIENT REMOVAL |  | WP-0285 |  |  | THIS PROJECT IS DESIGNED TO PROVIDE SUPPLEMENTAL CARBON ADDITION SYSTEMS TO ENHANCE NITROGEN REMOVAL AT BOWERY BAY, TALLMAN ISLAND, WARDS ISLAND, AND 26TH WARD WWTP. GLYCEROL HAS BEEN SELECTED AS THE PRIMARY CARBON SOURCE. THE SYSTEM WILL INCLUDE SUPPLEMENTAL CARBON RECEIVING STATION, BULK STORAGE, FEED AND DELIVERY, AND ANY ANCILLARY INSTRUMENTATION AND CONTROL SYSTEMS NEEDED TO OPERATE THESE FACILITIES. | 2019 | 123537 | 105271.8 | 626 | 0 | 0 | 0 | 0 | 0 | 105897.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | BLUBLTNEW | CITYWIDE BLUEBELT INITIATIVES | BLUEBELT PROGRAM | 000 | SE-0001 |  |  | CITYWIDE BLUEBELT INITIATIVES | 2019 | 32000 | 0 | 0 | 0 | 5338 | 16000 | 0 | 14000 | 35338 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | BWS-LEAD | LEAD PAINT REMOVAL AT BWS FACILITIES | FACILITY PURCHASES AND RECONSTRUCTION | 000 | EP-0006 |  |  | THIS PROJECT IS TO PROVIDE THE NEW YORK CITY DEPARTMENT OF ENVIRONMENTAL PROTECTION ("DEP"), BUREAU OF WATER SUPPLY WITH SERVICES TO REMOVEAND DISPOSE OF CONTAMINATED LEAD AND/OR NON-LEAD BASED PAINT AND CONTAMINANTS. THIS PROJECT REQUIRES PAINT ABATEMENT AND ASSOCIATED WORK TO STRUCTURES DIRECTLY ABOVE OR ADJOINING ACCESS TO DEP WATER SUPPLY. IN SOME FACILITIES THE PAINT MAY ALSO CONTAIN ASBESTOS, ARSENIC, CADMIUM, MERCURY, AND POLYCHLORINATED BIPHENYLS ("PCB"). | 2019 | 4443 | 0 | 0 | 4443 | 0 | 0 | 0 | 0 | 4443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | C519 | MODIFICATION OF CHAMBERS AT HILLVIEW | CITY TUNNEL NO. 3, STAGE 1 | 000 | W-0010 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | VALVE CHAMBERS AT HILL VIEW RESERVOIR (UPSTATE) | MODIFICATION OF CHAMBERS AT HILL VIEW RES IN CONNECTION WITH THE CONSTOF CITY TUNNEL NO 3, STAGE 1, GENERAL, ELECTRICAL, PLUMBING | 2019 | 198184 | 81705.49 | 0 | 18500 | 0 | 128000 | 30000 | 163000 | 421205.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | C-591 | Hillview Reservoir Dry Scrubbers - Downtake Chambers 1 & 2 | CITY TUNNEL NO. 3, STAGE 1 | 000 | W-0010 |  |  | HILLVIEW DRY SCRUBBER | 2019 | 2875 | 0 | 375 | 2500 | 0 | 0 | 0 | 0 | 2875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAN-HYDRO | Development of Hydroelectric Cannonsville Dam. incl P'wrhse | WATER QUALITY PRESERVATION | 000 | WM-0030 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | DEVELOPMENT OF HYDROELECTRIC CANNONSVILLE DAM. INCL P'WRHSE | 2019 | 138000 | 0 | 0 | 0 | 0 | 0 | 8000 | 0 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-178 | REPLACEMENT OF DIVIDING WEIR BRIDGE | DAM SAFETY PROGRAM | 000 | WM-0030 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | CATSKILLS, UPSTATE | REPLACEMENT OF DIVIDING WEIR BRIDGE | 2019 | 55400 | 1000 | 0 | 0 | 0 | 0 | 0 | 265000 | 266000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-186 | RESURFACING SCHOHARIE ROADS WEST AND BEARKILL BRIDGE | DAM SAFETY PROGRAM | 000 | WM-0030 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | UPSTATE | RESURFACING SCHOHARIE ROADS WEST AND BEARKILL BRIDGE | 2019 | 7875 | 8079.88 | 273 | 0 | 0 | 0 | 0 | 0 | 8352.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-210 | CAT/DEL UV LIGHT TREATMENT FACILITIES | WATER QUALITY PRESERVATION | 000 | WM-0030 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | CATSKILL & DELAWARE RESERVIORS | CATSKILL & DELAWARE ULTRAVIOLET LIGHT TREATMENT FACILITIES | 2019 | 904233 | 1578747.37 | -4651 | 0 | 15000 | 0 | 0 | 0 | 1589096.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-212 | SCHOHARIE RESERVOIR/GILBOA DAM AND INTAKE/OUTLET CHAMBER | DAM SAFETY PROGRAM | 000 | WM-0030 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | SCHOLARIE RESERVIOR/GILBOA DAM | SCHOLARIE RESERVIOR/GILBOA DAM AND INTAKE/OUTLET CHAMBER | 2019 | 390807 | 443878.93 | -9661 | 0 | 0 | 432 | 31000 | 0 | 465649.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-213 | ASHOKAN RESERVOIR/OLIVE BRIDGE DAM & UPPER/LOWER OUTLET& SCR | DAM SAFETY PROGRAM | 000 | WM-0030 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | UPSTATE | ASHOKAN RESERVIOR/OLIVE BRIDGE DAM & UPPER/LOWER OUTLET& SCREEN CHAMBERS RECONSTRUCTION | 2019 | 110000 | 90495.7 | 38712 | 0 | 15000 | 0 | 162000 | 330000 | 636207.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-252 | REPLACEMENT OF ESOPUS AND ROUTE 28A RAILROAD BRIDGES | DAM SAFETY PROGRAM | 000 | WM-0030 | PROJECT DELAYED PENDING RELEASE OF NEW TECHNOLOGY | REPLACEMENT OF ESOPUS AND ROUTE 28A RAILROAD BRIDGES | REPLACEMENT OF ESOPUS AND ROUTE 28A RAILROAD BRIDGES | 2019 | 60000 | 15580.66 | 12 | 0 | 0 | 0 | 72000 | 0 | 87592.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-259 | BEN NESIN FACILITY/ASHOKAN RECONSTRUCTION | WATER QUALITY PRESERVATION | 000 | WM-0030 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | BEN NESIN FACILITY/ASHOKAN RECONSTRUCTION | 2019 | 2100 | 10713.2 | 504 | 0 | 0 | 0 | 0 | 0 | 11217.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-390 | Schoharie Reservoir road improvement- NYS Rt. 990V | WATER QUALITY PRESERVATION | 000 | WM-0030 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | SCHOHARIE RESERVOIR ROAD IMPROVEMENT- NYS RT. 990V | 2019 | 585 | 584.1 | 0 | 800 | 0 | 0 | 300 | 4325 | 6009.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-392 | Energy Conservation Measures Improvement at Four WWTPs | WATER QUALITY PRESERVATION | 000 | WM-0030 |  |  | ENERGY CONSERVATION MEASURES IMPROVEMENT AT GRAND GORGE AND TANNERSVILLE WWTPS | 2019 | 10000 | 500 | 13119 | 0 | 0 | 0 | 0 | 0 | 13619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-399 | CA Hudson River Drainage Chamber | WATER QUALITY PRESERVATION | 000 | WM-0030 |  |  | CA HUDSON RIVE DRAINAGE CHAMBER | 2019 | 2000 | 4382.01 | 0 | 2000 | 15000 | 0 | 0 | 0 | 21382.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-431 | CATSKILL AQUEDUCT RECONST.-KENSICO TO HILVIEW | WATER QUALITY PRESERVATION | 000 | WM-0030 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CATSKILL AQUEDUCT RECONST.-KENSICO TO HILVIEW | 2019 | 59032 | 28300.84 | 209 | 0 | 0 | 10000 | 0 | 115000 | 153509.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-452 | WOH Catskill Acqueduct Chambers Rehab & Restoration | WATER QUALITY PRESERVATION | 000 | WM-0030 |  |  | WOH CATSKILL ACQUEDUCT CHAMBERS REHABILITATION & RESTORATION | 2019 | 9600 | 0 | 0 | 3184 | 0 | 0 | 1990 | 19900 | 25074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-454 | RECONSTRUCTION GRAND GORGE WWTP | MISCELLANEOUS IMPROVEMENTS UPSTATE |  | WM-0030 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RECONSTRUCTION GRAND GORDE WWTP | 2019 | 1700 | 0 | 0 | 0 | 3100 | 0 | 0 | 0 | 3100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-475 | GILBOA HLO | WATER QUALITY PRESERVATION | 000 | WM-0030 |  |  | GILBOA HLO | 2019 | 14500 | 0 | 0 | 2000 | 2000 | 11000 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-477 | Catskill Acqueduct Pressure Tunnels | WATER QUALITY PRESERVATION | 000 | WM-0030 |  |  | TUNNEL WORK | 2019 | 217389 | 0 | 7389 | 0 | 0 | 0 | 42000 | 168000 | 217389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-508 | DR-30 Culvert Repair & Embankment Stabilization | WATER QUALITY PRESERVATION | 000 | WM-0030 |  |  | DR-30 CULVERT REPAIR & EMBANKMENT STABILIZATION | 2019 | 5020 | 0 | 0 | 620 | 400 | 4000 | 0 | 0 | 5020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-OPTIM | To Increase the Capacity of Upper Catskill Aqueduct | WATER FOR THE FUTURE | 000 | W-0005 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | THE PROJECT INVOLVES IMPROVEMENTS TO INCREASE THE CAPACITY OF UPPER CATSKILL AQUEDUCT,UP TO 60 MGD, WHICH EXTENDS APPROXIMATELY 74 MILES FROM ASHOKAN RESERVOIR TO KENSICO RESERVOIR. | THE PROJECT INVOLVES IMPROVEMENTS TO INCREASE THE CAPACITY OF UPPER CATSKILL AQUEDUCT,UP TO 60 MGD, WHICH EXTENDS APPROXIMATELY 74 MILES FROM ASHOKAN RESERVOIR TO KENSICO RESERVOIR. | 2019 | 139000 | 202462.92 | 11796 | 0 | 0 | 482 | 0 | 0 | 214740.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-208B | NEW CROTON DAM RECONSTRUCTION | WATER QUALITY PRESERVATION | 000 | WM-0030 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | NEW CROTON DAM RECONSTRUCTION | 2019 | 17000 | 0 | 12901 | 0 | 0 | 15000 | 120000 | 0 | 147901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-286 | CROSS RIVER AND CROTON FALLS PUMPING STATIONS | WATER FOR THE FUTURE | 000 | W-0005 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | CROSS RIVER & CROTON FALLS | DESIGN FOR CROSS RIVER AND CROTON FALLS PUMPING STATIONS | 2019 | 67500 | 93751.49 | 692 | 0 | 0 | 0 | 0 | 0 | 94443.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-366 | REPLACE DOORS, EAST-OF-HUDSON DISTRICT | WATER QUALITY PRESERVATION | 000 | WM-0030 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | VARIOUS LOCATIONS THROUGHOUT THE EAST-OF-HUDSON WATER SUPPLY DISTRICT | REMOVAL AND REPLACEMENT OF HEAVY STEEL DOORS AT VARIOUS WATER SUPPLY STRUCTURES IN THE EAST-OF-HUDSON WATER SUPPLY DISTRICT | 2019 | 1275 | 4606.16 | 129 | 0 | 0 | 0 | 0 | 0 | 4735.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-410 | NEW CROTON LAKE GATE HOUSE HVAC REHABILITATION | WATER QUALITY PRESERVATION | 000 | WM-0030 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CROTON LAKE GATE HOUSE HVAC | 2019 | 850 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-452 | WWTP - CYCLICAL EQUIPMENT REPLACEMENT | WATER QUALITY PRESERVATION | 000 | WM-0030 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | MAHOPAC WWTP - EQUIPMENT REPLACEMENT & FACILITY REHAB. | 2019 | 4500 | 1040.12 | 1811 | 1085 | 0 | 750 | 750 | 1500 | 6936.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-497 | Aqueduct Erosion Restoration at EOH | WATER QUALITY PRESERVATION | 000 | WM-0030 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | AQUEDUCT EROSION RESTORATION AT EOH | 2019 | 2400 | 0 | 977 | 0 | 0 | 0 | 0 | 0 | 977 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-502 | Road Improvement due to Kensico Dam Road Closure | WATER QUALITY PRESERVATION | 000 | WM-0030 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | ROAD IMPROVEMENT DUE TO KENSICO DAM ROAD CLOSURE | 2019 | 2400 | 200 | 4884 | 0 | 0 | 0 | 0 | 0 | 5084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-509 | Arcady Road Reconstruction | WATER QUALITY PRESERVATION | 000 | WM-0030 |  |  | ARCADY ROAD IS LOCATED IN WESTCHESTER COUNTY, NY ADJACENT TO THE CROTON RESERVOIR. THIS CONSTRUCTION CONTRACT IS FOR THE RECONSTRUCTION OF APPROXIMATELY 1 MILE OF ROADWAY AND REPLACEMENT/RECONSTRUCTION OF ALL DRAINAGE CULVERTS AND GUIDE RAILING. A PORTION OF THE EXISTING ROADWAY IS COLLAPSED (DUE TO TROPICAL STORM FLOYD IN 1999) AND THE ROAD IS CURRENTLY CLOSED TO TRAFFIC. THIS SECTION OF ROADWAY WILL NEED TO BE RECONSTRUCTED AND STABILIZED. | 2019 | 2000 | 0 | 0 | 2000 | 0 | 0 | 6000 | 0 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-518 | Wetland Mitigation at KAP Site | WATER QUALITY PRESERVATION | 000 | WM-0030 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | WETLAND MITIGATION AT KAP SITE | 2019 | 5600 | 0 | 5539 | 0 | 0 | 0 | 0 | 0 | 5539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-530 | REPLACEMENT OF THE BAPTIST CHURCH ROAD BRIDGE | WATER QUALITY PRESERVATION | 000 | WM-0030 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | REPLACEMENT OF THE BAPTIST CHURCH ROAD BRIDGE | 2019 | 19000 | 2646.96 | 0 | 0 | 0 | 0 | 0 | 20000 | 22646.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-534 | WEST BRANCH AUXILIARY DAM-CREEP REMEDIATION | WATER QUALITY PRESERVATION | 000 | WM-0030 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | WEST BRANCH AUXILIARY DAM-CREEP REMEDIATION | 2019 | 4000 | 0 | 0 | 8600 | 0 | 0 | 0 | 0 | 8600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-536 | EOH Dam Facing | WATER QUALITY PRESERVATION | 000 | WM-0030 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CATSKILL AQUEDUCT PRESSURE CAPS-MODNA SIPHON | 2019 | 21000 | 3695.8 | 0 | 0 | 1850 | 0 | 0 | 20664 | 26209.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-546 | Amawalk Dam Ogee Spillway Replacement | WATER QUALITY PRESERVATION | 000 | WM-0030 |  |  | PERMANENT REPLACEMENT OF BOTH SPILLWAY APPROACH WALLS AT AMAWALK DAM | 2019 | 3000 | 0 | 2130 | 0 | 0 | 0 | 0 | 0 | 2130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-551 | Conversion of Kensico Lab to EOH Operations HQ | WATER QUALITY PRESERVATION | 000 | WM-0030 |  |  | CONVERSION OF KENSICO LAB TO EOH OPERATIONS HQ | 2019 | 5000 | 0 | 0 | 6300 | 0 | 0 | 0 | 0 | 6300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-552 | Shaft 18 Traveling Screens & Other Work | WATER QUALITY PRESERVATION | 000 | WM-0030 |  |  | PURCHASE AND INSTALLATION OF TRAVELING SCREENS AT SHAFT 18 | 2019 | 5000 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-553 | KENSICO SPILLWAY CRACK RECONSTRUCTION | WATER QUALITY PRESERVATION | 000 | WM-0030 |  |  | KENSICO SPILLWAY CRACK RECONSTRUCTION | 2019 | 4000 | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-557 | Kensico Waterfowl Facility Construction & Paving | WATER QUALITY PRESERVATION | 000 | WM-0030 |  |  | KENSICO WATERFOWL FACILITY CONSTRUCTION & PAVING | 2019 | 8100 | 0 | 0 | 8100 | 0 | 0 | 0 | 0 | 8100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-558 | Aqueduct Restoration at Lake Street - EOH | WATER QUALITY PRESERVATION | 000 | WM-0030 |  |  | AQUEDUCT RESTORATION AT LAKE STREET - EOH | 2019 | 3500 | 0 | 0 | 0 | 2500 | 0 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-570 | HILLVIEW MAINTENANCE SHOP | WATER QUALITY PRESERVATION | 000 | WM-0030 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | HILLVIEW MAINTENANCE SHOP | 2019 | 5000 | 0 | 0 | 0 | 5250 | 0 | 0 | 0 | 5250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-572 | HILLVIEW WATERFOWL MGMT FACILITY | WATER QUALITY PRESERVATION | 000 | WM-0030 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | HILLVIEW POLICE PRECINCT | 2019 | 1000 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-589 | EASTVIEW MAINTENANCE SHOP | WATER QUALITY PRESERVATION | 000 | WM-0030 |  |  | EASTVIEW MAINTENANCE SHOP | 2019 | 5000 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-594 | UV FOUNDATION DRAIN MH PHASE 2 | WATER QUALITY PRESERVATION | 000 | WM-0030 |  |  | UV FOUNDATION DRAIN MH PHASE 2 | 2019 | 1300 | 0 | 0 | 1300 | 0 | 0 | 0 | 0 | 1300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-607 | Shaft 17 Elevator Replacement | WATER QUALITY PRESERVATION | 000 | WM-0030 |  |  | SHAFT 17 ELEVATOR REPLACEMENT | 2019 | 300 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-609 | Cyclic Equipment Replacement for WTO | WATER QUALITY PRESERVATION | 000 | WM-0030 |  |  | CYCLIC EQUIPMENT REPLACEMENT FOR WTO | 2019 | 3000 | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-610 | Paving of Roadway at Hillview Complex | WATER QUALITY PRESERVATION | 000 | WM-0030 |  |  | PAVING OF ROADWAY AT HILLVIEW COMPLEX | 2019 | 600 | 0 | 0 | 0 | 0 | 600 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-611 | BWS Emergency Services Contract | WATER QUALITY PRESERVATION | 000 | WM-0030 |  |  | BWS EMERGENCY SERVICES CONTRACT | 2019 | 9000 | 0 | 0 | 3000 | 0 | 3000 | 0 | 3000 | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-NC-BAP | BORDEN AVENUE PUMP STATION EXPANSION | WATER QUALITY MANDATES |  | WP-0169 |  |  | THE PROJECT WILL CONTROL CSO DISCHARGES TO DUTCH KILLS BY DIVERTING WET WEATHER FLOW FROM OUTFALL BB-026 VIA A NEW DIVERSION CHAMBER WITH TIDE GATE. NEW GRAVITY PIPING WILL BE CONSTRUCTED TO CONVEY FLOW FROM THE NEW DIVERSION CHAMBER TO THE BORDEN AVENUE PUMP STATION. THE CAPACITY OF THE BORDEN AVENUE PUMP STATION WILL BE EXPANDED TO INCLUDE 26 MGD OF WET WEATHER FLOW AND NEW FORCE MAIN WILL BE CONSTRUCTED FROM THE BORDEN AVENUE PUMP STATION TO UPSTREAM OF THE KENT AVENUE GATE WHICH SERVICES THE NEWTOWN CREEK WWTP. | 2019 | 74000 | 0 | 0 | 0 | 8000 | 0 | 0 | 66000 | 74000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-UPGRD | UPGRADES AT CSO FACILITIES | WATER QUALITY MANDATES | 000 | WP-0169 |  |  | UPGRADES AT CSO FACILITIES | 2019 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CT12VENT | CITY TUNNELS1 & 2, REPLACE VENTURI LINES @ SHAFTS | CITY TUNNEL NO. 1, RECONSTRUCTION | 000 | W-0015 |  |  | CITY TUNNELS1 & 2, REPLACE VENTURI LINES @ SHAFTS | 2019 | 22000 | 0 | 0 | 0 | 0 | 965 | 0 | 0 | 965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CT3-13B | CITY TUNNEL #3 13B EGRESS | MISCELLANEOUS PROGRAMS | 000 | W-0013 |  |  | CITY TUNNEL #3 13B EGRESS | 2019 | 8000 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CT315B | CITY TUNNEL 3, REPAIR LEAK@ SHAFT 15B | WATER QUALITY PRESERVATION |  | W-0013 |  |  | CITY TUNNEL 3, REPAIR LEAK@ SHAFT 15B | 2019 | 4000 | 0 | 2160 | 0 | 0 | 0 | 0 | 0 | 2160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CT3CORR | Repairs & Remediate Corrosion Issues - CT 3 | CORROSION PROTECTION SYSTEM |  | W-0013 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CITY TUNNEL 3, CORRECT STAGE 1 CORROSION ISSUES | 2019 | 67000 | 10018.77 | 0 | 2000 | 0 | 0 | 19000 | 0 | 31018.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DECL-SE | Citywide emergency sewer reconstruction | REPLACEMENT OF CHRONICALLY FAILING COMPONENTS | 000 | SE-0002X |  |  | CITYWIDE EMERGENCY SEWER RECONSTRUCTION | 2019 | 9778 | 9094 | 95 | 0 | 0 | 0 | 0 | 0 | 9189 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-134 | Del Repair: HYDRAULIC INV - RONDOUT-WEST BRANCH TUNNEL | WATER FOR THE FUTURE | 000 | WM-0030 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | HYDRAULIC INVESTIGATION-RONDOUT-WEST BRANCH TUNNEL | HYDRAULIC INVESTIGATION-RONDOUT-WEST BRANCH TUNNEL | 2019 | 47385 | 59901.36 | 0 | 2000 | 2000 | 0 | 0 | 0 | 63901.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-194 | Merriman Dam Spillway | DAM SAFETY PROGRAM | 000 | WM-0030 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | UPSTATE | MERRIMAN DAM & RONDOUT RESERVOIR INTAKE & EFFLUENT CHAMBER | 2019 | 25250 | 1927.66 | 572 | 3000 | 0 | 20000 | 0 | 0 | 25499.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-231 | CANNONSVILLE EMERGENCY GATE TOWER | WATER QUALITY PRESERVATION | 000 | WM-0030 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | CANNONSVILLE RESERVOIR, DELAWARE COUNTY, NY | RPLACEMENT OF EMERGENCY GATE TOWER HOIST | 2019 | 1150 | 0 | 500 | 1100 | 0 | 0 | 0 | 0 | 1600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-233 | WOH WWTPs Sewer Line Stream Crossings | WATER QUALITY PRESERVATION | 000 | WM-0030 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | VILLAGE OF GRAHAMSVILLE, SULLIVAN COUNTY, NY | INSPECTION, AND RECONSTRUCTION IF NECESSARY, ALL PARTS OF THE GRAHAMSVILLE SEWER SYSTEM THAT CROSS STREAMS FEEDING NEW YORK CITY WATER SUPPLY | 2019 | 550 | 254.78 | 5763 | 0 | 0 | 0 | 0 | 0 | 6017.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-359V | Shaft 4 Gate Valve Replacements | WATER QUALITY PRESERVATION |  | WM-0030 |  |  | SHAFT 4 GATE VALVE REPLACEMENTS | 2019 | 6000 | 0 | 0 | 1000 | 5000 | 0 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-360 | SCADA SYSTEM UPGRADE | WATER QUALITY PRESERVATION |  | WM-0030 |  |  | SCADA SYSTEM UPGRADE | 2019 | 4600 | 0 | 2670 | 0 | 0 | 0 | 0 | 0 | 2670 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-373 | West of Hudson Boat Launches | WATER QUALITY PRESERVATION | 000 | WM-0030 |  |  | BOAT LAUNCHES IN WOH UPSTATE WATERSHED DISTRICT | 2019 | 1700 | 0 | 0 | 1700 | 0 | 0 | 0 | 0 | 1700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-377 | Delaware County Roads | WATER QUALITY PRESERVATION | 000 | WM-0030 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | DELAWARE COUNTY ROADS | 2019 | 8750 | 25983.91 | 0 | 0 | 2000 | 2000 | 0 | 0 | 29983.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-397 | Riser Valve Control Mechanism at DA Chambers | WATER QUALITY PRESERVATION | 000 | WM-0030 |  |  | DA/CA FASTENERS REPLACMENT & RISER VALVE OPERATORS | 2019 | 10000 | 0 | 0 | 2000 | 8000 | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-413 | Security Gate Construction at Six Locations in Delaware Dist | WATER QUALITY PRESERVATION | 000 | WM-0030 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | SECURITY GATE CONSTRUCTION AT SIX LOCATIONS IN DELAWARE DISTRICT | 2019 | 1500 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-415 | EAST DELAWARE RELEASE CHAMBER VALVE REPLACEMENTS | MISCELLANEOUS IMPROVEMENTS UPSTATE |  | WM-0030 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | REPLACEMENT OF RELEASE CHAMER VALVE AT EAST DELAWARE. | 2019 | 5990 | 0 | 0 | 5990 | 0 | 0 | 0 | 0 | 5990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-424 | Replacement/Rehabilitation of Honk Falls Dam | DAM SAFETY PROGRAM | 000 | WM-0030 |  |  | REPLACEMENT/REHABILITATION OF HONK FALLS DAM | 2019 | 8221 | 0 | 4713 | 3800 | 9500 | 0 | 0 | 0 | 18013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-428 | EDTO VALVE | WATER QUALITY PRESERVATION | 000 | WM-0030 |  |  | EDTO VALVE | 2019 | 800 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-429 | CENTRAL HUDSON AGREEMENT | WATER QUALITY PRESERVATION | 000 | WM-0030 |  |  | CENTRAL HUDSON AGREEMENT | 2019 | 796 | 0 | 796 | 0 | 0 | 0 | 0 | 0 | 796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-431 | EDTO & NTO TURBINE REPLACEMENT | WATER QUALITY PRESERVATION | 000 | WM-0030 |  |  | EDTO & NTO TURBINE REPLACEMENT | 2019 | 1 | 0 | 0 | 200 | 0 | 1000 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-434 | DAM STABILITY IMPROVEMENTS | WATER QUALITY PRESERVATION | 000 | WM-0030 |  |  | DAM STABILITY IMPROVEMENTS | 2019 | 19500 | 0 | 0 | 2000 | 0 | 0 | 0 | 15000 | 17000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-439 | Sludge Drying Greenhouse Recon. at Margaretville WWTP | WATER QUALITY PRESERVATION | 000 | WM-0030 |  |  | THIS PROJECT IS TO REPLACE GREENHOUSE SUPERSTRUCTURE OVER 6 SLUDGE DRYING BEDS AT THE MARGARETVILLE WASTEWATER TREATMENT PLANT (MVWWTP). | 2019 | 1990 | 0 | 0 | 1990 | 0 | 0 | 0 | 0 | 1990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-SHFT4 | Dependability- Connection from Del Aqueduct to Cat Aqueduct | WATER FOR THE FUTURE | 000 | W-0005 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | TO CONSTRUCT A CONNCECTION FROM SHAFT 4 OF THE DELAWARE AQUEDUCT TO THE CATSKILL AQUEDUCT | TO CONSTRUCT A CONNCECTION FROM SHAFT 4 OF THE DELAWARE AQUEDUCT TO THE CATSKILL AQUEDUCT. | 2019 | 57000 | 31014.07 | 246 | 1000 | 1000 | 6000 | 0 | 0 | 39260.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEP-DRA | DELAWARE-RONDOUT AQUEDUCT (PARALLEL TUNNEL TO RWBT) | WATER FOR THE FUTURE | 000 | W-0005 |  | UPSTATE | DELAWARE-RONDOUT AQUEDUCT (PARALLEL TUNNEL TO RWBT). | 2019 | 25000 | 1053179.69 | 2132 | 0 | 21473 | 0 | 0 | 0 | 1076784.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DOERETRO | WATER EFFICIENCY UPGRADES AT DOE SCHOOLS | WATER FOR THE FUTURE | 000 | EP-0009 |  |  | REPLACEMENT OF DOE SCHOOLS TOILETS AND URINALS WITH HIGH EFFICIENCY MODELS, CITYWIDE PROGRAM | 2019 | 11593 | 0 | 0 | 0 | 11593 | 0 | 0 | 0 | 11593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DOT-SE-SP | SEWER REPLACEMENTS IN CONJUNCTION WITH DOT PRIORITY PROJECTS | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 000 | SE-0001 |  |  | SEWER REPLACEMENTS IN CONJUNCTION WITH DOT PRIORITY PROJECTS, CITYWIDE | 2019 | 72284 | 0 | 0 | 0 | 0 | 12000 | 12000 | 14000 | 38000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DOT-WM-SP | MAIN REPLACEMENTS IN CONNECTION WITH DOT PRIORITY PROJECTS | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 000 | WM-0001 WM-0006 |  |  | WATER MAIN REPLACEMENTS IN CONJUNCTION WITH DOT PRIORITY PROJECTS, CITYWIDE | 2019 | 200466 | 0 | 0 | 0 | 0 | 7344 | 7344 | 10344 | 25032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EE-RRC | TRC - RESIDUAL CHLORINE REDUCTION PROGRAM | CONSENT DECREE UPGRADING AND CONSTRUCTION | 000 | WP-0282 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | RESIDUAL CHLORINE REDUCTION PROGRAM | RESIDUAL CHLORINE REDUCTION PROGRAM | 2019 | 76848 | 82045.32 | 1779 | 6818 | 0 | 0 | 0 | 109434 | 200076.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | FMC-LEAD | LEAD PAINT ABATEMENT & REMOVAL | FACILITY PURCHASES AND RECONSTRUCTION | 000 | EP-0006 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | LEAD PAINT ABATEMENT & REMOVAL | 2019 | 1986 | 1896.25 | 1500 | 1250 | 0 | 0 | 0 | 3500 | 8146.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-DDC | GI - DDC PROJECTS-GREEN INFRASTRUCTURE AND PUBLIC BUILDINGS | GREEN INFRASTRUCTURE PROGRAM | 000 | WP-0169 |  |  | DDC PROJECTS - GREEN INFRASTRUCTURE | 2019 | 44202 | 0 | 235 | 0 | 0 | 0 | 0 | 0 | 235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-DDCBP | GI - FUNDING FOR DDC PUBLIC BUILDINGS PROJECTS | GREEN INFRASTRUCTURE PROGRAM | 000 | WP-0169 |  |  | GREEN INFRASTRUCTURE FUNDING FOR DDC PUBLIC BUILDINGS CAPITAL PROJECTS | 2019 | 3400 | 0 | 0 | 500 | 500 | 500 | 500 | 500 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-DOESCA | GI - DOE/SCA GREEN INFRASTRUCTURE | GREEN INFRASTRUCTURE PROGRAM | 000 | WP-0169 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | DOE/SCA GREEN INFRASTRUCTURE | 2019 | 15520 | 0 | 3000 | 0 | 1500 | 1500 | 1500 | 4500 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-DOTDDC | GI - FUNDING FOR DOT GREEN INFRASTRUCTURE CAPITAL PROJECTS | GREEN INFRASTRUCTURE PROGRAM | 000 | WP-0169 |  |  | GI - FUNDING FOR DOT GREEN INFRASTRUCTURE CAPITAL PROJECTS | 2019 | 1500 | 0 | 0 | 1000 | 500 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-DPRCAP | GI - FUNDING FOR DPR GREEN INFRASTRUCTURE CAPITAL PROJECTS | GREEN INFRASTRUCTURE PROGRAM | 000 | WP-0169 |  |  | GI - FUNDING FOR DPR GREEN INFRASTRUCTURE CAPITAL PROJECTS | 2019 | 17400 | 0 | 0 | 0 | 11890 | 500 | 500 | 500 | 13390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-EDC | GI -EDC PROJECTS & FINANCING PROGRAMS - GREEN INFRASTRUCTURE | GREEN INFRASTRUCTURE PROGRAM | 000 | WP-0169 |  |  | EDC CAPITAL PROGRAMS & FINANCING PROGRAMS | 2019 | 750 | 0 | 0 | 0 | 0 | 6585 | 0 | 0 | 6585 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-GGEO-1 | GI - GEOTECHNICAL SERVICES FOR GREEN INFRASTRUCTURE | GREEN INFRASTRUCTURE PROGRAM | 000 | WP-0169 |  |  | GEOTECHNICAL SERVICES FOR GREEN INFRASTRUCTURE | 2019 | 5404 | 0 | 0 | 2637 | 0 | 0 | 0 | 0 | 2637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-GRANT | GI - GREEN INFRASTRUCTURE GRANT PROGRAM | GREEN INFRASTRUCTURE PROGRAM | 000 | WP-0169 |  |  | GREEN INFRASTRUCTURE GRANT PROGRAM | 2019 | 30000 | 10621.82 | 0 | 3949 | 0 | 3078 | 0 | 0 | 17648.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-HPD | GI - FUNDING FOR HPD GREEN INFRASTRUCTURE PROJECTS | GREEN INFRASTRUCTURE PROGRAM | 000 | WP-0169 |  |  | GI - FUNDING FOR HPD GREEN INFRASTRUCTURE PROJECTS | 2019 | 750 | 0 | 0 | 0 | 0 | 0 | 1000 | 500 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-ONSITE | TASK ORDER CONTRACT FOR CONS MGMT SVCS FOR GREEN INFRASTRUCT | GREEN INFRASTRUCTURE PROGRAM | 000 | WP-0169 |  |  | TASK ORDER CONTRACT FOR CONSTRUCTION MANAGEMENT SERVCES FOR GREEN IINFRASTRUCTURE | 2019 | 25000 | 0 | 4 | 8000 | 6000 | 4000 | 6996 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-OTHER | GI - OTHER AGENCY PROJECTS - GREEN INFRASTRUCTURE | GREEN INFRASTRUCTURE PROGRAM | 000 | WP-0169 |  |  | OTHER AGENCY PROJECTS - GREEN INFRASTRUCTURE | 2019 | 1000 | 0 | 0 | 0 | 0 | 0 | 11028 | 0 | 11028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-S-DSGN | TASK ORDER CONTRACT FOR DESIGN SERVCES FOR GI - DOE | GREEN INFRASTRUCTURE PROGRAM | 000 | WP-0169 |  |  | TASK ORDER CONTRACT FOR DESIGN SERVCES FOR GREEN IINFRASTRUCTURE - DOE | 2019 | 15000 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | IN-CITYAC | Agency Proposed Accelerated Projects | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 000 | SE-0001 WM-0001 |  |  | RECONSTRUCTION OF TRUNKAND DISTRIBUTION MAINS, CITYWIDE | 2019 | 319000 | 0 | 0 | 0 | 0 | 0 | 16671 | 50000 | 66671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | IN-CITYSE | Agency Proposed Projects | EXTENSIONS TO ACCOMMODATE NEW DEVELOPMENT | 099 | SE-0001 |  | CITYWIDE | AGENCY PROPOSED PROJECTS | 2019 | 325285 | 0 | 0 | 0 | 0 | 15618 | 89211 | 640237 | 745066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | IN-CITYWM | Agency-Proposed Projects | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 000 | WM-0001 WM-0006 |  | CITYWIDE | IN-CITY WATER MAINS | 2019 | 476725 | 0 | 0 | 300 | 6732 | 9579 | 111989 | 752543 | 881143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JFK-12 | WATER METER INSTALLATION AT JFK AIRPORT | CONSERVATION FOR WATER METER REPLACEMENTS | 000 | EP-0010 |  |  |  | 2019 | 9811 | 8586 | 1225 | 0 | 0 | 0 | 0 | 0 | 9811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-12-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH, & EAST | PLANT UPGRADING AND RECONSTRUCTION | 000 | WP-0112 |  | VARIOUS LOCATIONS - CITY-WIDE | JOB ORDER CONTRACTING FOR PLUMBING WORK IN REGION SOUTH (NEWTOWN CREEK, NORTH RIVER, OAKWOOD BEACH, PORT RICHMOND, AND RED HOOK, | 2019 | 119798 | 65046.96 | 782 | 0 | 0 | 0 | 0 | 0 | 65828.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-15BWS | Facilities Improvement Program | WATER QUALITY PRESERVATION | 000 | WM-0030 WM-0011 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | PROCUREMENT CONTRACT FOR JOB ORDER CONTRACTING-UPSTATE | 2019 | 44160 | 26282.73 | 520 | 38420 | 0 | 0 | 0 | 0 | 65222.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-17-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | PLANT UPGRADING AND RECONSTRUCTION | 000 | WP-0112 |  | VARIOUS WPCPS IN VARIOUS REGIONS AND LOCATIONS CITY-WIDE | JOB ORDER CONTRACTING FOR SMALL TO MEDIUM SIZED PROJECTS IN GENERAL CONSTRUCTION/ PLUMBING/ HVAC AND ELECTRICAL WORK IN REGIONS NORTH, SOUTH AND EAST AT VARIOUS WASTEWATER TREATMANT PLANTS AND FACILITIES CITY-WIDE. | 2019 | 121700 | 80655.7 | 28800 | 0 | 0 | 0 | 0 | 0 | 109455.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-18-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | PLANT UPGRADING AND RECONSTRUCTION | 000 | WP-0112 |  | VARIOUS LOCATIONS CITY-WIDE | JOB ORDER CONTRACTING FOR GENERAL CONSTRUCTION/PLUMBING/HVAC / ELECTRICAL/SCADA AND FIRE ALARM SYSTEMS WORK IN VARIOUS REGIONS IN NORTH, SOUTH, AND EAST AT THE VARIOUS WASTEWATER TREATMENT PLANTS, CITY-WIDE | 2019 | 54800 | 5837 | 48960 | 0 | 0 | 0 | 0 | 0 | 54797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-19-L | JOC JOB ORDER CONTRACTING WORK IN REGIONS NORTH,SOUTH & EAST | PLANT UPGRADING AND RECONSTRUCTION | 000 | WP-0112 |  |  | JOB ORDER CONTRACTING FOR SMALL TO MEDIUM SIZED PROJECTS IN GENERAL CONSTRUCTION/ PLUMBING/ HVAC AND ELECTRICAL WORK IN REGIONS NORTH, SOUTH AND EAST AT VARIOUS WASTEWATER TREATMANT PLANTS AND FACILITIES CITY-WIDE. | 2019 | 37400 | 0 | 0 | 17280 | 0 | 0 | 0 | 0 | 17280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-20-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | PLANT UPGRADING AND RECONSTRUCTION | 000 | WP-0112 |  |  | JOB ORDER CONTRACTING FOR SMALL TO MEDIUM SIZED PROJECTS IN GENERAL CONSTRUCTION/ PLUMBING/ HVAC AND ELECTRICAL WORK IN REGIONS NORTH, SOUTH AND EAST AT VARIOUS WASTEWATER TREATMANT PLANTS AND FACILITIES CITY-WIDE. | 2019 | 34594 | 0 | 0 | 0 | 0 | 36040 | 0 | 35000 | 71040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-21-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | PLANT UPGRADING AND RECONSTRUCTION | 000 | WP-0112 |  |  | JOB ORDER CONTRACTING FOR SMALL TO MEDIUM SIZED PROJECTS IN GENERAL CONSTRUCTION/ PLUMBING/ HVAC AND ELECTRICAL WORK IN REGIONS NORTH, SOUTH AND EAST AT VARIOUS WASTEWATER TREATMANT PLANTS AND FACILITIES CITY-WIDE. | 2019 | 43200 | 0 | 0 | 0 | 0 | 0 | 58560 | 0 | 58560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-22-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | PLANT UPGRADING AND RECONSTRUCTION | 000 | WP-0112 |  |  | JOB ORDER CONTRACTING FOR SMALL TO MEDIUM SIZED PROJECTS IN GENERAL CONSTRUCTION/ PLUMBING/ HVAC AND ELECTRICAL WORK IN REGIONS NORTH, SOUTH AND EAST AT VARIOUS WASTEWATER TREATMANT PLANTS AND FACILITIES CITY-WIDE. | 2019 | 45280 | 0 | 0 | 0 | 0 | 24000 | 0 | 0 | 24000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-23-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | PLANT UPGRADING AND RECONSTRUCTION | 000 | WP-0112 |  |  | JOB ORDER CONTRACTING FOR SMALL TO MEDIUM SIZED PROJECTS IN GENERAL CONSTRUCTION/ PLUMBING/ HVAC AND ELECTRICAL WORK IN REGIONS NORTH, SOUTH AND EAST AT VARIOUS WASTEWATER TREATMANT PLANTS AND FACILITIES CITY-WIDE. | 2019 | 30200 | 0 | 0 | 0 | 0 | 0 | 0 | 68160 | 68160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-24-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | PLANT UPGRADING AND RECONSTRUCTION | 000 | WP-0112 |  |  | JOB ORDER CONTRACTING FOR SMALL TO MEDIUM SIZED PROJECTS IN GENERAL CONSTRUCTION/ PLUMBING/ HVAC AND ELECTRICAL WORK IN REGIONS NORTH, SOUTH AND EAST AT VARIOUS WASTEWATER TREATMANT PLANTS AND FACILITIES CITY-WIDE. | 2019 | 30080 | 0 | 0 | 0 | 0 | 0 | 0 | 61440 | 61440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-25-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | PLANT UPGRADING AND RECONSTRUCTION | 000 | WP-0112 |  |  | JOB ORDER CONTRACTING FOR SMALL TO MEDIUM SIZED PROJECTS IN GENERAL CONSTRUCTION/ PLUMBING/ HVAC AND ELECTRICAL WORK IN REGIONS NORTH, SOUTH AND EAST AT VARIOUS WASTEWATER TREATMANT PLANTS AND FACILITIES CITY-WIDE. | 2019 | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 21120 | 21120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-26-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | PLANT UPGRADING AND RECONSTRUCTION | 000 | WP-0112 |  |  | JOB ORDER CONTRACTING FOR SMALL TO MEDIUM SIZED PROJECTS IN GENERAL CONSTRUCTION/ PLUMBING/ HVAC AND ELECTRICAL WORK IN REGIONS NORTH, SOUTH AND EAST AT VARIOUS WASTEWATER TREATMANT PLANTS AND FACILITIES CITY-WIDE. | 2019 | 115000 | 0 | 0 | 0 | 0 | 0 | 0 | 71040 | 71040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-27-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | PLANT UPGRADING AND RECONSTRUCTION | 000 | WP-0112 |  |  | JOB ORDER CONTRACTING FOR SMALL TO MEDIUM SIZED PROJECTS IN GENERAL CONSTRUCTION/ PLUMBING/ HVAC AND ELECTRICAL WORK IN REGIONS NORTH, SOUTH AND EAST AT VARIOUS WASTEWATER TREATMANT PLANTS AND FACILITIES CITY-WIDE. | 2019 | 65000 | 0 | 0 | 0 | 0 | 0 | 0 | 58560 | 58560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-28-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | PLANT UPGRADING AND RECONSTRUCTION | 000 | WP-0112 |  |  | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 2019 | 20160 | 0 | 0 | 0 | 0 | 0 | 0 | 20160 | 20160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-29-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | PLANT UPGRADING AND RECONSTRUCTION | 000 | WP-0112 |  |  | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 2019 | 68160 | 0 | 0 | 0 | 0 | 0 | 0 | 68160 | 68160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-BWS | BWS JOC Contracts (E-O-H & W-O-H) | WATER QUALITY PRESERVATION | 000 | WM-0030 |  |  | BWS JOC CONTRACTS (E-O-H & W-O-H) | 2019 | 64000 | 0 | 0 | 0 | 0 | 0 | 6220 | 48500 | 54720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-BWSO | BWSO Facilities Improvement Program | PLANT UPGRADING AND RECONSTRUCTION | 000 | WM-0105 |  |  | PROCUREMENT CONTRACT FOR JOB ORDER CONTRACTING - CITYWIDE FOR THE BUREAU OF WATER & SEWER OPERATIONS | 2019 | 37680 | 15170 | 5760 | 5240 | 3000 | 4000 | 2980 | 12900 | 49050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-CS4 | CONSULTANT SERVICES FOR JOB ORDER CONTRACTING PROGRAM | PLANT UPGRADING AND RECONSTRUCTION | 000 | WP-0112 |  |  | CONSULTANT CONTRACT TO DEVELOP, IMPLEMENT AND MAINTAIN COMPLETE COMPREHENSIVE JOB ORDER CONTRACTING SYSTEM FOR CONSTRUCTION AND CONSTRUCTION RELATED TASKS IN VARIOUS D.E.P. BUREAUS BUT NOT LIMITED TO BWT, BWSO, AND THE BUREAU OF MANAGEMENT AND BUDGET | 2019 | 8000 | 0 | 0 | 0 | 0 | 8000 | 0 | 0 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC3 | FMC Facilities Improvement Program | FACILITY PURCHASES AND RECONSTRUCTION |  | EP-0006 |  |  | FMC FACILITIES IMPROVEMENT PROGRAM | 2019 | 5720 | 2400 | 0 | 3320 | 0 | 0 | 0 | 0 | 5720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC4 | Job Order Contract 2 - CIitywide | FACILITY PURCHASES AND RECONSTRUCTION |  | EP-0006 |  |  | JOB ORDER CONTRACT 2 - CITYWIDE | 2019 | 4760 | 2400 | 0 | 2360 | 0 | 0 | 0 | 0 | 4760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC6 | FMC Facilities Improvement Program | FACILITY PURCHASES AND RECONSTRUCTION |  | EP-0006 |  |  | FMC FACILITIES IMPROVEMENT PROGRAM | 2019 | 3600 | 0 | 0 | 0 | 2400 | 0 | 1200 | 0 | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC7 | Job Order Contract 2 - Citywide | FACILITY PURCHASES AND RECONSTRUCTION |  | EP-0006 |  |  | JOB ORDER CONTRACT 2 - CITYWIDE | 2019 | 3600 | 0 | 0 | 0 | 2400 | 0 | 1200 | 0 | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC8 | FMC Facilities Improvement Program | FACILITY PURCHASES AND RECONSTRUCTION |  | EP-0006 |  |  | FMC FACILITIES IMPROVEMENT PROGRAM | 2019 | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 3600 | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC9 | Job Order Contract 2 - Citywide | FACILITY PURCHASES AND RECONSTRUCTION |  | EP-0006 |  |  | JOB ORDER CONTRACT 2 - CITYWIDE | 2019 | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 3600 | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JPSCOMPEH | JEROME PS ELECTRIC & HYDRAULIC SVC REPLAMNT | WATER QUALITY PRESERVATION |  | WM-0105 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | JEROME PS ELECTRIC & HYDRAULIC SVC REPLAMNT | 2019 | 5000 | 0 | 0 | 0 | 0 | 0 | 1000 | 5000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | KENS-EAST | KENSICO-EASTVIEW CONNECTION TUNNEL | KENSICO-CITY TUNNEL | 000 | W-0014 |  |  | KENSICO-EASTVIEW CONNECTION TUNNEL | 2019 | 563000 | 52131.03 | 36140 | 10525 | 75000 | 37000 | 24069 | 1133608 | 1368473.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | LANDMG-08 | FAD 08-12 - Land Management | FILTRATION AVOIDANCE DETERMINATION | 000 | WM-0030 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | FAD 08-12 - LAND MANAGEMENT | 2019 | 600 | 707.92 | 338 | 0 | 0 | 0 | 0 | 0 | 1045.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | LANDMG-13 | FAD 13-17 Land Management | FILTRATION AVOIDANCE DETERMINATION | 000 | WM-0030 |  |  | FAD 13-17 LAND MANAGEMENT | 2019 | 1140 | 0 | 1881 | 0 | 0 | 0 | 0 | 0 | 1881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | LFK-RELO | Lefrak Relocation | FACILITY PURCHASES AND RECONSTRUCTION |  | EP-0006 |  |  | LEFRAK RELOCATION INCLUDING OIT COST, LABS, PARKING AND ETC. | 2019 | 10500 | 0 | 0 | 0 | 0 | 10500 | 0 | 0 | 10500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | LTCP2015 | CITY-WIDE LONG TERM CONTROL PLAN FOR CSO ABATEMENT | WATER QUALITY MANDATES | 000 | WP-0169 |  |  | CITY-WIDE LONG TERM CONTROL PLAN FOR COMBINED SEWER OVERFLOW (CSO) ABATEMENT | 2019 | 590100 | 0 | 0 | 0 | 0 | 0 | 34416 | 623434 | 657850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | MONIT-13 | FAD 13-17 Monitoring | FILTRATION AVOIDANCE DETERMINATION | 000 | WM-0030 |  |  | FAD 13-17 MONITORING | 2019 | 215 | 78 | 150 | 0 | 0 | 147 | 103 | 736 | 1214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | MS4-STORM | MS4 CITYWIDE STORMWATER MANAGEMENT PROGRAM | WATER QUALITY MANDATES | 000 | WP-0169 |  |  | MS4 CITYWIDE STORMWATER MANAGEMENT PROGRAM | 2019 | 29378 | 9377.85 | 0 | 0 | 10000 | 0 | 0 | 0 | 19377.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | NYSDOTBRG | NYS DOT Bridges El Grant, Jesup, Nelson, Depot, Boston Road | WATER QUALITY PRESERVATION | 000 | WM-0006 |  |  | NYS DOT EL GRANT, JESUP AND NELSON AVENUE (PIN X806.56), DEPOT PLACE (PIN X720.39), AND BOSTON ROAD BRIDGE REHABILITATION. ADDITIONAL WATERMAINS ON THE BRIDGES OR UPGRADE OF EXISTING WATER MAINS ON THESE BRIDGES THAT WAS REQUESTED BY DEP BWSO DISTRIBUTION. | 2019 | 5000 | 0 | 1003 | 3997 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PJ-PLNT | RECONSTRUCTION OF PORT JERVIS WPCP, DEL | WATER QUALITY PRESERVATION | 000 | WM-0030 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | UPSTATE | RECONSTRUCTION OF THE PORT JERVIS WATER POLLUTION CONTROL PLANT | 2019 | 44140 | 13441.86 | 40 | 3767 | 0 | 32960 | 0 | 0 | 50208.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PS179 | REHAB 179 ST PS/CONST MULTIPLE PS IN TOWER AREA | WATER QUALITY PRESERVATION |  | WM-0105 |  |  | REHAB 179 ST PS/CONST MULTIPLE PS IN TOWER AREA | 2019 | 12000 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-FORCEM | RECONSTRUCT PUMPING STATION FORCEMAINS OLDER THAN 50 YEARS | PLANT UPGRADING AND RECONSTRUCTION | 000 | WP-0269 |  |  | RECONSTRUCT PUMPING STATION FORCEMAINS OLDER THAN 50 YEARS | 2019 | 125000 | 0 | 0 | 0 | 0 | 0 | 0 | 125000 | 125000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PSNCPS | STRUCTURAL REHABILITATION OF NEW CLOVE PS | WATER QUALITY PRESERVATION |  | WM-0105 |  |  | NEWTOWN CREEK PS FULL EQUIP & STRUCTURAL REHAB | 2019 | 16600 | 0 | 0 | 0 | 0 | 0 | 8000 | 8600 | 16600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PW-116-L | INSTALL SOLAR CCTV SURVEILLANCE AT CSO OUTFALLS | PLANT UPGRADING AND RECONSTRUCTION | 000 | WP-0112 |  | VARIOUS WWT'S CITY-WIDE | INSTALL SOLAR CCTV SURVEILLANCE AT CSO OUTFALLS | 2019 | 2150 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PW-117-L | INSTALLATION OF DISTRIBUTED CONTROL SYSTEMS @ VARIOUS WWTPS | PLANT UPGRADING AND RECONSTRUCTION | 000 | WP-0112 |  | VARIOUS LOCATIONS CITY-WIDE HUNTS WWTP, BOWERY BAY WWTP, AND PAERDEGAT BWQY | INSTALLATION OF VARIOUS HARDWARE AND SOFTWARE EQUIPMENT TO UPGRADE THE EXISTING DISTRIBUTED CONTROL SYSTEMS. THE SCOPE OF THE PROJECT IS TOUPGRADE THE VARIOUS CONTROL SYSTEMS HARDWARE AND SOFTWARE AT THE HUNTS POINT WWTP, BOWERY BAY WWTP, AND PAERDEGAT BWQF. | 2019 | 2650 | 0 | 0 | 2400 | 0 | 0 | 0 | 0 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PW-118-L | EMERGENCY PIPING RECONSTR @ VAR BWWT FACILITIES CITY-WIDE | PLANT UPGRADING AND RECONSTRUCTION | 000 | WP-0112 |  | VARIOUS LOCATIONS CITY-WIDE | EMERGENCY RECONSTRUCTION OF PIPING SYSTEMS AT VARIOUS BWWT FACILITIES CITY-WIDE | 2019 | 9700 | 0 | 0 | 0 | 9000 | 0 | 0 | 0 | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PW-78-L | RECONSTRUCTION OF PIPES PLANT WIDE | PLANT UPGRADING AND RECONSTRUCTION | 000 | WP-0112 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | VARIOUS LOCATIONS | RECONSTRUCTION OF PIPES PLANT WIDE | 2019 | 24428 | 10786.13 | 48 | 0 | 0 | 0 | 0 | 0 | 10834.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PW-82-L | RECONSTRUCTION OF DEWATERING BELTS AT VARIOUS W.P.C.P.S | PLANT UPGRADING AND RECONSTRUCTION | 000 | WP-0112 |  | VARIOUS LOCATIONS - HUNTS POINT, WARDS ISLAND, 26TH WARD, BOWERY BAY WPCPS | RECONSTRUCTION OF DEWATERING BELTS AT VARIOUS WPCPS | 2019 | 25062 | 24138.17 | 115 | 0 | 0 | 0 | 0 | 0 | 24253.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PW-CBS | REPLACEMENT OF CHEMICAL BULK STORAGE TANKS PLANT- WIDE | PLANT UPGRADING AND RECONSTRUCTION | 000 | WP-0112 |  |  | REPLACEMENT OF CHEMICAL BULK STORAGE TANKS PLANT- WIDE | 2019 | 7650 | 0 | 0 | 0 | 8170 | 0 | 0 | 0 | 8170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PW-TOC3 | CONSULTANT DESIGN SVCS FOR ALL BWWT JOC & CAPITAL PROJECTS | PLANT UPGRADING AND RECONSTRUCTION | 000 | WP-0112 |  | VARIOUS BWWT LOCATIONS CITY-WIDE | CONSULTANT DESIGN SERVICES FOR ALL BWWT JOC AND CAPITAL PROJECTS CITY-WIDE | 2019 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | REG-27 | INSTALLATION OF SCADA PUMPING STATION & REGULATORS CITYWIDE | PLANT UPGRADING AND RECONSTRUCTION | 000 | WP-0269 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES | VARIOUS PUMPING STATIONS AND REGULATORS CITY-WIDE | INSTALLATION OF SCADA PUMPING STATIONS AND REGULATORS, CITY-WIDE | 2019 | 42615 | 25078.41 | 3280 | 0 | 0 | 0 | 0 | 0 | 28358.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | RESAMSAF | DESIGN & CM FOR DAM SAFETY CONSTRUCTION | WATER QUALITY PRESERVATION | 000 | WM-0105 |  |  | DESIGN & CM FOR DAM SAFETY CONSTRUCTION | 2019 | 29000 | 9690.94 | 0 | 4000 | 0 | 0 | 40000 | 0 | 53690.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | RESHVDAM | HILLVIEW DAM SEEPAGE CONTROL & SLOPE STABILITY | WATER QUALITY PRESERVATION | 000 | WM-0105 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | HILLVIEW DAM SEEPAGE CONTROL & SLOPE STABILITY | 2019 | 2000 | 700 | 3639 | 0 | 0 | 0 | 0 | 0 | 4339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | REZONING | EXPANSION FOR RE-ZONING, CITYWIDE | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 000 | SE-0001 |  |  | EXPANSION FOR RE-ZONING, CITYWIDE | 2019 | 31105 | 0 | 0 | 0 | 0 | 0 | 53285 | 230599 | 283884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | RIDGEPIPE | RIDGEWOOD RESERVOIR PIPE ABANDONMENT | WATER QUALITY PRESERVATION |  | WM-0105 |  |  | RIDGEWOOD RESERVOIR PIPE ABANDONMENT - FILLING IN OF ABANDONED UNDERGROUND RESERVOIR PIPES IN ORDER TO AVOID COLLAPSE AND DANGEROUS CONDITIONS | 2019 | 2000 | 0 | 0 | 250 | 1750 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | RLCY-WWT | FLOODWATER RESILIENCY AT BWT FACILITES | PLANT UPGRADING AND RECONSTRUCTION | 000 | WP-0112 |  |  | DESIGN AND CONSTRUCTION REQUIREMENTS CONTRACTS WHICH WILL FOCUS ON IMPLEMENTING THE WASTEWATER RESILIENCY PLAN AT VARIOUS WASTEWATER TREATMENT PLANT FACILITIES THROUGHOUT THE CITY. THE VARIOUS MEASURES WHICH HAVE BEEN IDENTIFIED AND ARE INTENDED TO BE THE FOCUS OF THE DESIGN WORK UNDER THIS CONTRACT ARE: PERMANENT BARRIERS, TEMPORARY, SEAL BUILDING, SANDBAGGING, FLOOD-PROOF EQUIPMENT, ELEVATE EQUIPMENT AND BACKUP POWER. | 2019 | 181000 | 63920 | 94860 | 0 | 128431 | 0 | 0 | 0 | 287211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | ROWGI-A | GI - CITYWIDE CONSTRUCTION OF ROW GREEN INFRASTRUCTURE | GREEN INFRASTRUCTURE PROGRAM | 000 | WP-0169 |  |  | GI - CITYWIDE CM SERVICES FOR RIGHT OF WAY GREEN INFRASTRUCTURE PROJECTS | 2019 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDHILLV | HILLVIEW RESERVOIR SECURITY FENCE IMPROVEMENTS | MANAGEMENT INFORMATION SYSTEMS | 000 | EP-0006 |  | HILLVIEW RESERVIOR AT YONKERS, NEW YORK | IMPROVEMENTS TO THE HILLVIEW RESERVOIR SECURITY FENCE AND INTRUSION ALERT SYSTEM AS A RESULT OF HURRICANE SANDY | 2019 | 574 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 568 | 0 | 0 | 0 | 0 | 568
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDJOC12 | JOC RECONS OF VARIOUS PUMP STATIONS DUE TO HURRICANE SANDY | PLANT UPGRADING AND RECONSTRUCTION | 000 | WP-0112 |  |  | JOB ORDER CONTRACTING FOR THE RECONSTRUCTION OF VARIOUS PUMPING STATIONS CITYWIDE DUE TO HURRICANE SANDY | 2019 | 10396 | 377 | 0 | 1474 | 0 | 0 | 0 | 0 | 1851 | 12390.38 | 0 | 13269 | 0 | 0 | 0 | 0 | 25659.38
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDPUMP | RECONS OF VARIOUS PUMPING STATIONS DUE TO HURRICANE SANDY | PLANT UPGRADING AND RECONSTRUCTION | 000 | WP-0269 | PROJECT DELAYED PENDING NON-CITY GRANT APPROVAL |  | RECONSTRUCTION OF VARIOUS PUMPING STATIONS CITYWIDE DUE TO HURRICANE SANDY | 2019 | 12969 | 100 | 0 | 927 | 0 | 0 | 0 | 0 | 1027 | 896 | 0 | 8338 | 0 | 0 | 0 | 0 | 9234
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDSEWER | RECONSTRUCTION OF SEWERS CITYWIDE DUE TO HURRICANE SANDY | EXTENSIONS TO ACCOMMODATE NEW DEVELOPMENT | 000 | SE-0001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RECONSTRUCTION OF SEWERS CITYWIDE DUE TO HURRICANE SANDY | 2019 | 2000 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 1800
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDWM | RECONS OF WATER MAINS CITYWIDE DUE TO HURRICANE SANDY | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 000 | WM-0001 |  |  | RECONS OF WATER MAINS CITYWIDE DUE TO HURRICANE SANDY | 2019 | 3300 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 3000
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDWPCPS | RECONS OF WPCPS AND PUMPING STATIONS DUE TO HURRICANE SANDY | PLANT UPGRADING AND RECONSTRUCTION | 000 | WP-0112 |  |  | RECONSTRUCTION OF CITYWIDE WATER POLLUTION CONTROL PLANTS AND PUMPINGSTATIONS DUE TO HURRICANE SANDY | 2019 | 111579 | 500 | 4543 | 15821 | 0 | 0 | 0 | 0 | 20864 | 0 | 40868 | 142381 | 0 | 0 | 0 | 0 | 183249
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SEBLKR01 | Reconstruction of existing sewers from backlog BK & SI | REPLACEMENT OF CHRONICALLY FAILING COMPONENTS | 000 | SE-0002K SE-0002R |  |  | RECONSTRUCTION OF EXISTING SEWERS FROM BACKLOG FOR BROOKLYN AND STATEN ISLAND | 2019 | 9500 | 0 | 0 | 0 | 0 | 9500 | 0 | 0 | 9500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SEBLQX01 | Reconstruction of existing sewers from back log QN & BX | REPLACEMENT OF CHRONICALLY FAILING COMPONENTS | 000 | SE-0002Q SE-0002X |  |  | RECONSTRUCTION OF EXISTING SEWERS FROM BACK LOG IN QUEENS AND THE BRONX | 2019 | 9500 | 0 | 0 | 0 | 0 | 9500 | 0 | 0 | 9500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SE-EMRNGY | EMERGENCY CONTRACTS FOR SEWERS, CITYWIDE | REPLACEMENT OF CHRONICALLY FAILING COMPONENTS | 099 | SE-0001 |  |  | EMERGENCY CONTRACTS FOR SEWERS, CITYWIDE | 2019 | 586103 | 0 | 0 | 0 | 0 | 74725 | 33186 | 404198 | 512109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SE-GUN-20 | Emergency Guniting of Sewers, Citywide | REPLACEMENT OF CHRONICALLY FAILING COMPONENTS |  | SE-0758 |  |  | EMERGENCY GUNITING OF SEWERS, CITYWIDE | 2019 | 9000 | 0 | 0 | 0 | 9000 | 0 | 0 | 0 | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SEKBN9 | Reconstruction of Existing Sewers, North Brooklyn | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 000 | SE-0002K |  |  | RECONSTRUCTION OF EXISTING SEWERS, NORTH BROOKLYN | 2019 | 7125 | 0 | 0 | 0 | 0 | 7125 | 0 | 0 | 7125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SEKBS8 | Reconstruction of Existing Sewers, South Brooklyn | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 000 | SE-0002K |  |  | RECONSTRUCTION OF EXISTING SEWERS, SOUTH BROOKLYN | 2019 | 7125 | 0 | 0 | 0 | 0 | 7125 | 0 | 0 | 7125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SE-LC-22 | Emergency Sewer Lining | REPLACEMENT OF CHRONICALLY FAILING COMPONENTS |  | SE-0001 |  |  | EMERGENCY SEWER LINING, CITYWIDE | 2019 | 4050 | 0 | 0 | 4050 | 0 | 0 | 0 | 0 | 4050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SELCDDC | LINING CONTRACT - CITYWIDE | REPLACEMENT OF CHRONICALLY FAILING COMPONENTS | 000 | SE-0002 |  |  | LINING CONTRACT - CITYWIDE | 2019 | 28945 | 0 | 0 | 0 | 0 | 6700 | 3700 | 11694 | 22094 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQBN11 | Reconstruction of Existing Sewers, North Queens | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS |  | SE-0002Q |  |  | RECONSTRUCTION OF EXISTING SEWERS, NORTH QUEENS | 2019 | 7600 | 0 | 0 | 0 | 0 | 7600 | 0 | 0 | 7600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQBS11 | Reconstruction of Existing Sewers, South Queens | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS |  | SE-0002Q |  |  | RECONSTRUCTION OF EXISTING SEWERS, SOUTH QUEENS | 2019 | 8550 | 0 | 0 | 0 | 0 | 8550 | 0 | 0 | 8550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SETVDDC | TV INSPECTION & RECON OF SEWERS BY DDC | REPLACEMENT OF CHRONICALLY FAILING COMPONENTS | 000 | SE-0002 |  |  | CLEANING AND TELEVISING OF SEWERS BY DDC | 2019 | 16191 | 0 | 0 | 0 | 5401 | 2216 | 0 | 0 | 7617 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SFM-1 | RECONS OF SLUDGE FORCEMAIN FROM JAMAICA TO 26TH WARD WPCP | PLANT UPGRADING AND RECONSTRUCTION | 000 | WP-0112 |  |  | RECONS OF SLUDGE FORCEMAIN FROM JAMAICA TO 26TH WARD WPCP | 2019 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | STMEOH-08 | FAD 08-12 - Stormwater Management-EOH | FILTRATION AVOIDANCE DETERMINATION | 000 | WM-0030 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | FAD 08-12 - STORMWATER MANAGEMENT-EOH | 2019 | 17265 | 3562.1 | 0 | 147 | 0 | 0 | 0 | 0 | 3709.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | STMEOH-18 | FAD 18-22 STORMWATER MGMT. (EOH) | FILTRATION AVOIDANCE DETERMINATION | 000 | WM-0030 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | FAD 18-22 STORMWATER MGMT. (EOH) | 2019 | 22500 | 0 | 22000 | 500 | 0 | 0 | 0 | 0 | 22500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | STM-RETRO | FAD - STORMWATER MANAGEMENT, UPSTATE | FILTRATION AVOIDANCE DETERMINATION | 000 | WM-0030 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  |  | 2019 | 47685 | 25762.79 | 6051 | 0 | 0 | 0 | 0 | 0 | 31813.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | STMWOH-13 | FAD 13-17 Stormwater Mgmt. (WOH) | FILTRATION AVOIDANCE DETERMINATION | 000 | WM-0030 |  |  | FAD 13-17 STORMWATER MGMT. (WOH) | 2019 | 6875 | 6000 | 0 | 875 | 0 | 0 | 0 | 0 | 6875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | STMWOH-18 | FAD 18-22 STORMWATER MGMT. (WOH) | FILTRATION AVOIDANCE DETERMINATION | 000 | WM-0030 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | FAD 18-22 STORMWATER MGMT. (WOH) | 2019 | 14721 | 0 | 4721 | 0 | 10000 | 0 | 0 | 0 | 14721 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | STPUPG-18 | FAD 18-22 WWTP UPGRADE PROGRAM | FILTRATION AVOIDANCE DETERMINATION | 000 | WM-0030 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | FAD 18-22 WWTP UPGRADE PROGRAM | 2019 | 26200 | 0 | 26200 | 0 | 0 | 0 | 0 | 0 | 26200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | STREAM-18 | FAD 18-22 STREAM MANAGEMENT | FILTRATION AVOIDANCE DETERMINATION | 000 | WM-0030 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | FAD 18-22 STREAM MANAGEMENT | 2019 | 52167 | 0 | 0 | 48467 | 0 | 3700 | 0 | 0 | 52167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | TOSC1 | TASK ORDER SERVICES | AUGMENTATION OF WATER SUPPLY SYSTEMS | 000 | SE-0432 |  |  | TASK ORDER SERVICES CONTRACT FOR VARIOUS WATER AND SEWER PROJECTS | 2019 | 500 | 4004.04 | 0 | 0 | 3200 | 3000 | 2000 | 7680 | 19884.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | USGS | USGS Agreements | CONVEYANCE | 000 | W-0005 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | USGS AGREEMENTS (WATER LEVEL/FLOW IN ALL 5 BOROS) | 2019 | 5335 | 4885.99 | 0 | 0 | 5000 | 0 | 0 | 0 | 9885.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | UTIL-GEN | UTILITY CONTRACTS - GENERAL | UTILITY RELOCATION FOR SE AND WM PROJECTS | 000 | EP-0007 |  |  | GENERAL UTILITY CONTRACTS FOR SEWER AND WATER MAIN CONSTRUCTION | 2019 | 123203 | 0 | 0 | 0 | 0 | 2000 | 2649 | 11000 | 15649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | UTIUTIL | UTILITY RELOCATION FOR SE AND WM PROJECTS | UTILITY RELOCATION FOR SE AND WM PROJECTS | 000 | EP-0007 |  |  |  | 2019 | 334014 | 267449.68 | 59841 | 10000 | 10000 | 10000 | 40000 | 80000 | 477290.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WEC-LGE16 | LARGE WATER METER PURCHASES, REPLACEMENTS AND INSTALLATIONS | CONSERVATION FOR WATER METER REPLACEMENTS | 000 | EP-0010 |  |  | PURCHASES AND INSTALLATION OF METERS AND RELATED AUTOMATIC METER READING (AMR) SYSTEM THROUGHOUT THE FIVE BOROUGHS. REPLACEMENT AND REPAIR OF LARGE WATER METERS EITHER BECAUSE THE METERS ARE NO LONGER FUNCTIONING OR BECAUSE THEIR AGE IS RESULTING IN UNDER REGISTRATION. | 2019 | 44983 | 17937.35 | 3036 | 9592 | 4909 | 8227 | 1065 | 0 | 44766.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WFF-HHC | HHC Fixture Replacement in City-owned Hospitals | WATER FOR THE FUTURE |  | EP-0009 |  |  | WATER DEMAND MANAGEMENT PROGRAM - MUNICIPAL WATER EFFICIENCY PROGRAM (MWEP): HHC FIXTURE REPLACEMENT IN CITY-OWNED HOSPITALS | 2019 | 6000 | 0 | 0 | 3000 | 3000 | 0 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WFF-IGAS | WFF-INTER-GOV'T AGREEMENT | WATER FOR THE FUTURE | 000 | WM-0030 |  |  | TWO INTER-GOV'T AGREEMENTS TIED TO THE BYPASS TUNNEL PROJECT-WFF. THEAGREEMENTS ARE INTENDED TO PROVIDE AN ALTERNATE SOURCE OF WATER FOR COMMUNITIES WHO WILL BE IMPACTED BY THE CONSTRUCTION OF THE BYPASS TUNNEL. | 2019 | 23000 | 12062.72 | 723 | 11000 | 0 | 7077 | 0 | 0 | 30862.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WFF-WWTP | WATER EFICIENCY UPGRADES AT DEP WASTEWATER TREATMENT PLANTS | WATER FOR THE FUTURE | 000 | EP-0009 |  |  | CAPITAL WATER EFICIENCY UPGRADES AT DEP'S WASTEWATER TREATMENT PLANTS | 2019 | 6000 | 0 | 0 | 3000 | 3000 | 0 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WFINSP-SP | CITYWIDE WATERFRONT INSPECTIONS AT VARIOUS WPCPS | PLANT UPGRADING AND RECONSTRUCTION | 000 | WP-0112 |  |  | CITYWIDE WATERFRONT INSPECTIONS AT VARIOUS WPCPS | 2019 | 22200 | 0 | 0 | 0 | 0 | 0 | 22200 | 0 | 22200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WM-EMRNGY | EMERGENCY CONTRACTS FOR WATER MAINS, CITYWIDE | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 000 | WM-0001 WM-0006 |  | CITYWIDE | EMERGENCY CONTRACTS FOR IN-CITY WATER MAINS, CITYWIDE | 2019 | 217238 | 0 | 0 | 0 | 0 | 11089 | 8115 | 109801 | 129005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WPSOGR | Holding Code- Small SOGR for BWT Projects | PLANT UPGRADING AND RECONSTRUCTION |  | WP-0112 |  |  | HOLDING CODE TO FUND BOTH SMALL SOGR PROJECTS AND CHANGES TO EXISTINGBWT PROJECTS, CITYWIDE | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74255 | 74255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WQMON-EN2 | ABOVE GROUND MONITORING STATIONS 2 | WATER QUALITY PRESERVATION | 000 | WM-0105 |  |  | CONSTRUCT ABOVE GROUND ONE ROOM STRUCTURE | 2019 | 2769 | 0 | 2769 | 0 | 0 | 0 | 0 | 0 | 2769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WWMGT-13 | FAD 13-17 Community Wastewater Mgmt. | FILTRATION AVOIDANCE DETERMINATION | 000 | WM-0030 |  |  | FAD 13-17 COMMUNITY WASTEWATER MGMT. | 2019 | 29500 | 29500 | 8600 | 0 | 0 | 0 | 0 | 0 | 38100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WWMGT-18 | FAD 18-22 COMMUNITY WASTEWATER MGMT. | FILTRATION AVOIDANCE DETERMINATION | 000 | WM-0030 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | FAD 18-22 COMMUNITY WASTEWATER MGMT. | 2019 | 30000 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-281D | Female Locker Rooms in the Bronx, Brooklyn, Queens, citywide | GARAGES AND FACILITIES | 000 | S-0136 |  |  | CONSTRUCTION OF FEMALE LOCKER ROOMS INCLUDING TOILETS, SINKS, SHOWERS, CHANGING ROOMS, AND LOCKERS/BENCHES WITHIN EXISTING BUT UNIMPROVED SPACE. | 2019 | 2081 | 5219.89 | 293 | 0 | 0 | 0 | 0 | 0 | 5512.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-366D | Construct/Reconstruct composting sites Citywide | SOLID WASTE MANAGEMENT | 000 | S-0136 S-D136 S-K136 |  |  | CONSTRUCT/RECONSTRUCT COMPOSTING SITES CITYWIDE | 2019 | 15195 | 813 | 13246 | 0 | 0 | 0 | 0 | 0 | 14059 | 2918.9 | -2885 | 0 | 0 | 0 | 0 | 0 | 33.9
20190425 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-374 | BOILER & BURNER REPLACEMENT CITYWIDE | GARAGES AND FACILITIES | 000 | S-0136 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | CITYWIDE | UPGRADING AND/OR REPLACING BOILERS AND BURNERS AT VARIOUS SANITATION FACILITIES CITYWIDE WHEN NEEDED TO MAINTAIN EFFICACY AND STANDARDS. THIS PROJECT IS 100% CITY FUNDED, NON-EXEMPT. | 2019 | 27070 | 141.08 | 0 | 8013 | 6289 | 0 | 0 | 0 | 14443.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-383T | REPLACEMENT OF HVAC ROOF TOP UNITS CITYWIDE | GARAGES AND FACILITIES |  | S-0136 |  |  | REPLACE OVERAGE ROOF TOP UNITS | 2019 | 2102 | 2355.54 | 96 | 0 | 0 | 0 | 0 | 0 | 2451.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-439 | DSNY FACILITY REHAB, CITYWIDE | GARAGES AND FACILITIES | 000 | S-0136 |  |  | REHABILITATION PROJECTS CITYWIDE | 2019 | 32800 | 0 | 28 | 5561 | 5000 | 7000 | 15009 | 150000 | 182598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-440 | Sidewalks at DSNY Facilities, Citywide | GARAGES AND FACILITIES |  | S-0136 |  |  | SIDEWALK REPLACEMENT AT SANITATION FACILITIES | 2019 | 374 | 0 | 472 | 0 | 0 | 0 | 0 | 0 | 472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S216-235 | PIER WORK -- CITYWIDE | WASTE DISPOSAL | 000 | S-0216 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | CITY WIDE | THESE FUNDS ARE REQUIRED FOR UPGRADING AND REPLACEMENT OF HEATING PLANT SYSTEMS, LIGHTING AND RAMPS ETC. MISCELLANEOUS PROJECTS ARE REQUIRED TOTHE TRANSFER STATION THROUGH CAPITAL RECONSTRUCTION IN ORDER TO MEET SAFETY STANDARDS AND PREVENT MAJOR RECONSTRUCTION DUE TO DETERIORATION | 2019 | 103093 | 13818.61 | 0 | 0 | 0 | 0 | 3750 | 24969 | 42537.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | SANDMTSAP | MTS HAZARD MITIGATION ALTERNATE PROJECT- SANDY RELATED WORK | SOLID WASTE MANAGEMENT | 000 | S-0216 |  |  | HAZARD MITIGATION REHABILITATION WORK AT MARINE TRANSFER STATIONS | 2019 | 1124 | 0 | 0 | 68 | 0 | 0 | 0 | 0 | 68 | 0 | 0 | 615 | 0 | 0 | 0 | 0 | 615
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT503 | DOT Replacement of Streetlight Fixtures to LED,Manh,BX,SI | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 000 | TF-0503 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | REPLACEMENT OF EXISTING HPS STREET LIGHT FIXTURES WITH ENERGY EFFICIENT, LONG LIFE LED FIXTURES. | 2019 | 22475 | 17572.93 | 0 | 0 | 0 | 0 | 427 | 0 | 17999.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BIKE2030 | BIKE NETWORK DEVELOPMENT 2030 | TRAFFIC WORK IN CONJUNCTION WITH HIGHWAY RECONSTRUCTION | 000 | TF-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | BIKE NETWORK DEVELOPMENT 2030 | 2019 | 12340 | 0 | 0 | 0 | 0 | 0 | 160 | 1080 | 1240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BR10YR15 | Waterway Bridges Ten Year Plan | USEFUL LIFE EXTENSION | 000 | BR-0270 |  | WATERWAY BRIDGES TEN YEAR PLAN | WATERWAY BRIDGES TEN YEAR PLAN | 2019 | 175000 | 0 | 0 | 0 | 0 | 15000 | 50000 | 305247 | 370247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BRBM24012 | EMERG FENDER SYS REPLAC AT UNIV. HGHTS BRDG BIN:2240120 | USEFUL LIFE EXTENSION | 000 | HB-0215 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | EMERG FENDER SYS REPLAC AT UNIV. HGHTS BRDG BIN:2240120 | EMERG FENDER SYS REPLAC AT UNIV. HGHTS BRDG BIN:2240120 | 2019 | 16250 | 26430.29 | 0 | 0 | 240 | 0 | 0 | 0 | 26670.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BRC156F | MANHATTAN BRIDGE #15 | EAST RIVER BRIDGES | 000 | BR-0156 |  |  | REHAB OF MANHATTAN BRIDGE | 2019 | 98600 | 37521.1 | -549 | 27647 | 714 | 0 | 0 | 0 | 65333.1 | 61983.88 | 0 | 0 | 0 | 0 | 0 | 0 | 61983.88
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BRC156R | MANHATTAN BRIDGE #14 (CABLE RE-WRAPPING & SUSPENDER) | EAST RIVER BRIDGES | 000 | BR-0156 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | NA |  | 2019 | 115671 | 45984.87 | 1177 | 0 | 0 | 0 | 0 | 0 | 47161.87 | 135751.77 | 0 | 0 | 0 | 0 | 0 | 0 | 135751.77
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BRC231F | QUEENSBORO BRIDGE #10 OVER EAST RIVER | EAST RIVER BRIDGES | 000 | BR-0231 |  |  | REHAB OF QUEENSBORO BRIDGE | 2019 | 153800 | 321919.93 | 6000 | 6426 | 51702 | 0 | 0 | 0 | 386047.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BRC253D | WILLIAMSBURG BRIDGE MISC REPAIRS AND PAINTING FY20 | EAST RIVER BRIDGES | 000 | BR-0253 |  | WILLIAMSBURG BRIDGE MISC REPAIRS AND PAINTING FY20 | WILLIAMSBURG BRIDGE MISC REPAIRS AND PAINTING FY20 | 2019 | 414300 | 7315.52 | 186 | 0 | 12322 | 30863 | 257000 | 0 | 307686.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BRC270C | BROOKLYN BR (#6) BK APPR'S, MAIN SPAN & PAINT X751 54 (07) | EAST RIVER BRIDGES | 000 | BR-0270 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | BROOKLYN BR (#6) BROOKLYN APPROCHES AND MAIN SPAN, EAST RIVER | REHABILITATION AND PAINTING OF THE BROOKLYN BRIDGE APPROACH ANDBROOKLYN RAMPS THE FUNDING FOR THIS PROJECT IS ALL CITY | 2019 | 311920 | 416052.21 | 0 | 230 | 0 | 0 | 0 | 0 | 416282.21 | 335952.72 | 0 | 0 | 0 | 0 | 0 | 0 | 335952.72
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BRC270D | BROOKLYN BRIDGE REHABILITATION OF APPOACH ARCHES FY19 | EAST RIVER BRIDGES | 000 | BR-0270 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | BROOKLYN BRIDGE REHABILITATION OF APPOACH ARCHES FY19 | BROOKLYN BRIDGE REHABILITATION OF APPOACH ARCHES FY19 | 2019 | 300000 | 25872.64 | 204488 | 23634 | 0 | 0 | 0 | 0 | 253994.64 | 0 | 86398 | 0 | 0 | 0 | 0 | 0 | 86398
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BRC270FR | BROOKLYN BRIDGE #6A REPLACE CLADDING | EAST RIVER BRIDGES | 000 | BR-0270 |  | BROOKLYN BRIDGE #6A FOUNDATION RETROFITTING | BROOKLYN BRIDGE #6A REPLACE CLADDING | 2019 | 14920 | 21592.41 | 1762 | 1186 | 0 | 0 | 0 | 0 | 24540.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BRCHAZMIG | HAZARD MITIGATION (EAST RIVER BRIDGES - CITYWIDE) | EAST RIVER BRIDGES | 000 | BR-0156 BR-0253 BR-0231 BR-0270 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | HAZARD MITIGATION (EAST RIVER BRIDGES - CITYWIDE) | HAZARD MITIGATION (EAST RIVER BRIDGES - CITYWIDE) | 2019 | 107081 | 583171.43 | 0 | 140877 | 0 | 0 | 0 | 0 | 724048.43 | 76431 | 0 | 0 | 0 | 0 | 0 | 0 | 76431
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BRKA24039 | GRAND STREET/ NEWTON CREEK BIN: 2240390 | USEFUL LIFE EXTENSION | 000 | HB-1012 HB-0215 |  | GRAND STREET/ NEWTON CREEK BIN: 2240390 | GRAND STREET/ NEWTON CREEK BIN: 2240390 | 2019 | 138500 | 0 | 5863 | 0 | 11893 | 0 | 121000 | 0 | 138756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BRX287BS | Macombs Dam Bridge- Bus Stop | USEFUL LIFE EXTENSION | 000 | BR-0287 |  | MACOMBS DAM BRIDGE- BUS STOP | MACOMBS DAM BRIDGE- BUS STOP | 2019 | 3216 | 349.48 | 0 | 1567 | 0 | 0 | 0 | 0 | 1916.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BRX287S | MACOMBS DAM BRIDGE - REHAB OF FENDER SYSTEM & 155TH VIA | USEFUL LIFE EXTENSION | 000 | BR-0287 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | MACOMBS DAM BRIDGE - SEISMIC RETROFIT | MACOMBS DAM BRIDGE - SEISMIC RETROFIT | 2019 | 45920 | 26391.28 | 5025 | 2518 | 0 | 0 | 0 | 0 | 33934.28 | 35131 | 738 | 1406 | 0 | 0 | 0 | 0 | 37275
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BUS2030 | BUS INITIATIVES | TRAFFIC WORK IN CONJUNCTION WITH HIGHWAY RECONSTRUCTION | 000 | HW-1684 TF-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | BUS INITIATIVES | 2019 | 55290 | 0 | 0 | 0 | 0 | 53256 | 1040 | 7012 | 61308 | 0 | 0 | 0 | 0 | 2897 | 0 | 0 | 2897
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | C5447 | MISCELLANEOUS UPGRADES TO FERRYBOATS | RECONSTRUCTION OF FERRY BOATS | 000 | FA-0313 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | NA |  | 2019 | 7252 | 452.04 | 0 | 0 | 0 | 1508 | 955 | 8112 | 11027.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | C5574 | Design, CSS&Owner's Rep for Construction of New Ferryboats | RECONSTRUCTION OF FERRY BOATS | 000 | FA-0313 |  | CITYWIDE | SMALL FERRY BOATS | 2019 | 10000 | 18929.98 | 0 | 200 | 1624 | 0 | 0 | 0 | 20753.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | C5586 | REPLACEMENT OF COSGROVE FERRY BOAT | RECONSTRUCTION OF FERRY BOATS | 000 | FA-0313 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | DESIGN AND CONS OF COSGROVE F/BOAT | 2019 | 5275 | 0 | 371 | 0 | 3129 | 0 | 0 | 0 | 3500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | C5589AUS | DRYDOCK AUSTEN CLASS FERRY BOATS | RECONSTRUCTION OF FERRY BOATS | 000 | FA-0313 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | DRYDOCK AUSTEN FBOATS | 2019 | 3500 | 2366.86 | 1264 | 0 | 2755 | 0 | 145 | 0 | 6530.86 | 6540.29 | 0 | 0 | 0 | 0 | 0 | 0 | 6540.29
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | C5BARBERI | RECON & DRYDOCKING OF BARBERI CLASS FERRY BOATS | RECONSTRUCTION OF FERRY BOATS | 000 | FA-0313 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | DRYDOCK AND RECON OF FERRY VESSELS | 2019 | 11000 | 9577.29 | 0 | 0 | 2730 | 2748 | 290 | 0 | 15345.29 | 12203.87 | 0 | 0 | 0 | 0 | 0 | 0 | 12203.87
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | CONG2030 | CONGESTED CORRIDORS/ GROWTH AREAS | TRAFFIC WORK IN CONJUNCTION WITH HIGHWAY RECONSTRUCTION | 000 | TF-0777 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CONGESTED CORRIDORS/ GROWTH AREAS | 2019 | 124790 | 942.58 | 0 | 0 | 0 | 0 | 2328 | 13554 | 16824.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | DECKSCRPL | Deck Scows Replacement | FERRY MAINTENANCE FACILITY CONSTRUCTION | 000 | FA-0313 |  |  | SCOWS REPLACEMENT | 2019 | 3300 | 0 | 0 | 330 | 0 | 0 | 0 | 0 | 330 | 0 | 0 | 2970 | 0 | 0 | 0 | 0 | 2970
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | FACLUMP | LUMP SUM FOR FACILITIES | BRIDGE FACILITIES | 000 | HB-1014 HW-0003 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | CITYWIDE |  | 2019 | 66253 | 0 | 46 | 0 | 1321 | 12619 | 5514 | 35729 | 55229 | 0 | 419 | 0 | 0 | 290 | 0 | 0 | 709
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | FARRSLIP | Arrestors for all slips | RECONSTRUCTION OF FERRY TERMINAL FACILITIES | 000 | FA-0021 |  |  | INSTALLATION OF ARRESTORS AT SLIPS | 2019 | 45137 | 857.16 | 0 | 0 | 10000 | 19613 | 20207 | 0 | 50677.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | FATERMTBC | STGand WHT Ferry Terminals Transfer Bridge Control Update | RECONSTRUCTION OF FERRY TERMINAL FACILITIES | 000 | FA-0021 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | ELECTRICAL UPGRADE AT TERMINALS TRANSFER BRIDGE | 2019 | 1600 | 0 | 0 | 200 | 0 | 1400 | 0 | 0 | 1600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | FAVEHBARP | Vehicle Barrier Replacement Upgrade | RECONSTRUCTION OF FERRY TERMINAL FACILITIES | 000 | FA-0021 |  |  | BARRIER REPLACEMENT | 2019 | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | FAVESSPC | Ferry Terminals Vessel Passenger Counters | RECONSTRUCTION OF FERRY TERMINAL FACILITIES | 000 | FA-0021 |  |  | VESSEL PASSENGER COUNTERS | 2019 | 1000 | 0 | 973 | 0 | 0 | 27 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | GEAN-2013 | STREET LIGHTING ANNUAL CONSTRUCTION-FY14 | INSTALLATION OF LAMPPOSTS AND LUMINAIRES | 000 | TF-0503 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | ST LIGHT ANNUAL CONSTRUCTION CONTRACT | 2019 | 4000 | 4021 | 0 | 0 | 0 | 0 | 0 | 0 | 4021 | 7469.3 | 0 | 0 | 0 | 358 | 0 | 0 | 7827.3
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | GEAN2017 | STREET LIGHTING ANNUAL CONSTRUCTION -FY17 | INSTALLATION OF LAMPPOSTS AND LUMINAIRES | 000 | TF-0503 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | INSTALLATION OF STREET LIGHT POLES | 2019 | 7515 | 2140 | 0 | 0 | 0 | 0 | 0 | 0 | 2140 | 6387.07 | 513 | 0 | 0 | 0 | 0 | 0 | 6900.07
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | GEAN2019 | STREET LIGHTING ANNUAL CONSTRUCTION 2019 | INSTALLATION OF LAMPPOSTS AND LUMINAIRES | 000 | TF-0503 |  |  | THIS CONTRACT IS FOR INSTALLING AND REMOVING EQUIPMENT FURNISHED BY THE CITY, OR BY THE CONTRACTOR, AND FOR PERFORMING OTHER ELECTRICAL WORK IN CONNECTION WITH STREET LIGHTING IN THE CITY OF NEW YORK. | 2019 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 4500 | 3000 | 0 | 0 | 0 | 0 | 7500
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | GEHD-2013 | HIGHWAY & PARK DISTRIBUTION FY14 | REPLACEMENT OF ELECTRICAL DISTRIBUTION SYSTEMS | 000 | TF-0503 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | REPLACEMENT AND NEW DISTRIBUTION SYSTEM ON HIGHWAY AND IN PARKS | 2019 | 3000 | 1950 | 0 | 0 | 0 | 0 | 0 | 0 | 1950 | 4480 | 0 | 0 | 0 | 50 | 0 | 0 | 4530
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | GEHD2017 | HIGHWAYS & PARKS DISTRIBUTION -FY17 | REPLACEMENT OF ELECTRICAL DISTRIBUTION SYSTEMS | 000 | TF-0503 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | HIGHWAYS/PARKS DISTRIBUTION CITYWIDE | 2019 | 5000 | 985 | 0 | 0 | 0 | 0 | 0 | 0 | 985 | 3777.27 | 1694 | 0 | 0 | 0 | 0 | 0 | 5471.27
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | GEHD2019 | HIGHWAYS AND PARKS DISTRIBUTION 2019 | INSTALLATION OF LAMPPOSTS AND LUMINAIRES | 000 | TF-0503 |  |  | THIS CONTRACT IS FOR INSTALLING, REMOVING OR RELOCATING EQUIPMENT FURNISHED BY THE CITY, | 2019 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 5000
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | GEMN-13 | CAPITAL COMPONENT-STREET LIGHT MAINTENANCE-FY14 | SIGNAL INSTALLATION AND COMPUTERIZATION | 000 | TF-0503 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | STREET LIGHT MAINENANCE | 2019 | 21054 | 7351.62 | 0 | 0 | 0 | 12 | 0 | 0 | 7363.62 | 19327.28 | 0 | 0 | 0 | 70 | 0 | 0 | 19397.28
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | GEMN16 | CAPITAL COMPONENT- STREET LG MAINTENANCE-FY16 | INSTALLATION OF LAMPPOSTS AND LUMINAIRES | 000 | TF-0503 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | ST LG MAINTENANCE | 2019 | 22371 | 5090 | 0 | 0 | 0 | 72 | 0 | 0 | 5162 | 19870.9 | 0 | 0 | 0 | 2428 | 0 | 0 | 22298.9
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | GRTSTRTS | Vision Zero - Great Streets | PRIMARY STREET RECONSTRUCTION | 000 | HW-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | VISION ZERO - GREAT STREETS | VISION ZERO - GREAT STREETS | 2019 | 313707 | 0 | 0 | 0 | 7875 | 0 | 12075 | 70875 | 90825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HB1070ST | PROTECTIVE COATING OF VARIOUS BRIDGES IN STATEN ISLAND | BRIDGE PAINTING | 000 | HB-1070 |  |  | PROTECTIVE COATING OF VARIOUS BRIDGES IN QUEENS & STATEN ISLAND | 2019 | 13650 | 0 | 12043 | 2207 | 0 | 0 | 0 | 0 | 14250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HB-BIDSAD | ADVERTISEMENT FOR CAPITAL BRIDGE PROJECTS | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 000 | HB-0215 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | CITYWIDE | ADVERTISEMENT FOR CAPITAL PROJECTS | 2019 | 1425 | 679.19 | 0 | 0 | 102 | 0 | 0 | 0 | 781.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBC1070 | BRIDGE PROTECTIVE COATING | BRIDGE PAINTING | 000 | HB-1070 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | PAINTING FOR VARIOUS BRIDGES CITYWIDE | PAINTING AND PROTECTIVE TREATMENT FOR VARIOUS BRIDGES, FUNDING IS ALL | 2019 | 206749 | 0 | 0 | 9248 | 20591 | 25000 | 32000 | 192919 | 279758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBC10YR20 | BRIDGE 10 YEAR PLAN FY 2020 | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 000 | HB-0215 HB-1189 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | BRIDGE 10 YEAR PLAN FY 2020 | BRIDGE 10 YEAR PLAN FY 2020 | 2019 | 136773 | 0 | 0 | 8538 | 3971 | 16885 | 29778 | 1015886 | 1075058 | 0 | 0 | 0 | 0 | 41956 | 0 | 0 | 41956
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBC19YR29 | BRIDGE 10 YEAR PLAN FY 2029 | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 000 | HB-0215 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | BRIDGE 10 YEAR PLAN FY 2029 | 2019 | 314841 | 0 | 0 | 18116 | 0 | 10423 | 90383 | 12643 | 131565 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD0011 | INSPECTION SERVICES AT CONCRETE & ASPHALT PLANTS | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 000 | HB-1012 |  | INSPECTION SERVICES CONCRETE & ASPHALT PLANTS | INSPECTION SERVICES CONCRETE & ASPHALT PLANTS | 2019 | 6760 | 0 | 0 | 4874 | 0 | 0 | 0 | 0 | 4874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD0011A | IN-PROCESS FAB INSPECTION STRUCTURAL STEEL IN NE USA | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 000 | HB-1012 |  | IN-PROCESS FAB INSPECTION STRUCTURAL STEEL IN NE USA | IN-PROCESS FAB INSPECTION STRUCTURAL STEEL IN NE USA | 2019 | 12383 | 0 | 0 | 12383 | 0 | 0 | 0 | 0 | 12383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD0011B | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN US/CAN | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 000 | HB-1012 |  | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN US/CAN | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN US/CAN | 2019 | 6756 | 0 | 0 | 6756 | 0 | 0 | 0 | 0 | 6756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD0011C | IN-PROCESS FAB INSPECTION OF PP CONCRETE IN NE USA | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 000 | HB-1012 |  | IN-PROCESS FAB INSPECTION OF PP CONCRETE IN NE USA | IN-PROCESS FAB INSPECTION OF PP CONCRETE IN NE USA | 2019 | 3165 | 0 | 0 | 3796 | 0 | 0 | 0 | 0 | 3796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD0012 | TESTING AND SAMPLING OF MATERIAL (CITYWIDE) | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 000 | HB-1012 |  | TESTING AND SAMPLING OF MATERIAL (CITYWIDE) | TESTING AND SAMPLING OF MATERIAL (CITYWIDE) | 2019 | 10876 | 0 | 0 | 0 | 9800 | 0 | 0 | 0 | 9800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD006P | Citywide Inspection/Monitoring of Bridge Paint Removal&Appli | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 000 | HB-1012 |  | QUALITY ASSURANCE CONTRACT (PAINT, CHEMICAL TEST, FAILURE) | QUALITY ASSURANCE CONTRACT (PAINT, CHEMICAL TEST, FAILURE) | 2019 | 3465 | 0 | 0 | 2465 | 0 | 0 | 0 | 0 | 2465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD007P | Citywide Inspection/Monitoring of Bridge Paint Removal & App | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 000 | HB-1070 |  | CITYWIDE INSPECTION/MONITORING OF BRIDGE PAINT REMOVAL & APP | CITYWIDE INSPECTION/MONITORING OF BRIDGE PAINT REMOVAL & APP | 2019 | 2711 | 0 | 0 | 0 | 0 | 0 | 2711 | 0 | 2711 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD008P | Citywide Inspection/Monitoring of Bridge Paint Removal & App | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 000 | HB-1070 |  | CITYWIDE INSPECTION/MONITORING OF BRIDGE PAINT REMOVAL AND APPLICATION | CITYWIDE INSPECTION/MONITORING OF BRIDGE PAINT REMOVAL & APP | 2019 | 3050 | 0 | 0 | 0 | 0 | 0 | 0 | 3050 | 3050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD009A | IN-Process FAB Inspection of Structural Steel in the NE US | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 000 | HB-1012 |  | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN NE USA | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN NE USA | 2019 | 6617 | 7993.81 | 1500 | 0 | 0 | 0 | 0 | 0 | 9493.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD010 | TESTING AND SAMPLING OF MATERIALS (CITYWIDE) | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 000 | HB-1012 |  | TESTING AND SAMPLING OF MATERIALS (CITYWIDE) | TESTING AND SAMPLING OF MATERIALS (CITYWIDE) | 2019 | 10290 | 4540.98 | 0 | 0 | 182 | 0 | 0 | 0 | 4722.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD013 | Inspection Services at Concrete & Asphalt Plants | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 000 | HB-1012 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | INSPECTION SERVICES AT CONCRETE & ASPHALT PLANTS | INSPECTION SERVICES AT CONCRETE & ASPHALT PLANTS | 2019 | 5200 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD013A | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN NE US | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 000 | HB-1012 |  | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN NE US | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN NE US | 2019 | 12386 | 0 | 0 | 0 | 0 | 0 | 12386 | 0 | 12386 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD013B | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN US | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 000 | HB-1012 |  | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN US | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN US | 2019 | 6756 | 0 | 0 | 0 | 0 | 0 | 6756 | 0 | 6756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD013C | IN-PROCESS FAB INSPECTION OF PP CONCRETE IN USA/CAN | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 000 | HB-1012 |  | IN-PROCESS FAB INSPECTION OF PP CONCRETE IN USA/CAN | IN-PROCESS FAB INSPECTION OF PP CONCRETE IN USA/CAN | 2019 | 3165 | 0 | 0 | 0 | 0 | 0 | 3165 | 0 | 3165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD014 | Testing and Sampling of Material (Citywide) | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 000 | HB-1012 |  | TESTING AND SAMPLING OF MATERIAL (CITYWIDE) | TESTING AND SAMPLING OF MATERIAL (CITYWIDE) | 2019 | 11301 | 0 | 0 | 0 | 0 | 0 | 0 | 11301 | 11301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD015 | INSPECTION SERVICES AT CONCRETE & ASPHALT PLANTS | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 000 | HB-1012 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | TESTING AND SAMPLING OF MATERIAL (CITYWIDE) | TESTING AND SAMPLING OF MATERIAL (CITYWIDE) | 2019 | 5400 | 0 | 0 | 0 | 0 | 0 | 0 | 5400 | 5400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD015A | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN NE USA | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 000 | HB-1012 |  | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN NE USA | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN NE USA | 2019 | 12383 | 0 | 0 | 0 | 0 | 0 | 0 | 12767 | 12767 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD015B | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN US/CAN | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 000 | HB-1012 |  | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN US/CAN | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN US/CAN | 2019 | 6756 | 0 | 0 | 0 | 0 | 0 | 0 | 6965 | 6965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD015C | IN-PROCESS FAB INSPECTION OF PP CONCRETE IN USA/CAN | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 000 | HB-1012 |  | IN-PROCESS FAB INSPECTION OF PP CONCRETE IN USA/CAN | IN-PROCESS FAB INSPECTION OF PP CONCRETE IN USA/CAN | 2019 | 3165 | 0 | 0 | 0 | 0 | 0 | 0 | 3263 | 3263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD016 | TESTING AND SAMPLING OF MATERIAL (CITYWIDE) | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 000 | HB-1012 |  | TESTING AND SAMPLING OF MATERIAL (CITYWIDE) | TESTING AND SAMPLING OF MATERIAL (CITYWIDE) | 2019 | 12802 | 0 | 0 | 0 | 0 | 0 | 0 | 12802 | 12802 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR01B | COMP REHAB 01 CONST (B CONTRACT) | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 000 | HB-0215 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  |  | 2019 | 13993 | 17660.73 | 746 | 36 | 0 | 1840 | 0 | 0 | 20282.73 | 12098.74 | 0 | 0 | 0 | 0 | 0 | 0 | 12098.74
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR02A | COMPONENT REHABILITATION 02A CONSTRUCTION | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 000 | HB-0215 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | COMP REHAB CONST | COMP REHAB CONST | 2019 | 10595 | 18674.39 | 467 | 286 | 0 | 0 | 0 | 0 | 19427.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR02B | COMPONENT REHABILITATION 02B CONSTRUCTION | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 000 | HB-0215 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | COMP REHAB 02B CONS | COMP REHAB 02B CONS | 2019 | 10595 | 31994.22 | 30 | 3216 | 245 | 0 | 0 | 0 | 35485.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR03A | COMPONENT REHABILITATION 03A CONSTRUCTION | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 000 | HB-0215 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | COMP REHAB CONS | COMP REHAB CONS | 2019 | 11070 | 34454.34 | 80 | 2000 | 2077 | 0 | 0 | 0 | 38611.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR03B | COMPONENT REHABILITATION 03B CONSTRUCTION | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 000 | HB-0215 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | COMP REHAB 03B CONST | COMP REHAB 03B CONST | 2019 | 12120 | 2713.23 | 0 | 4933 | 26175 | 0 | 0 | 0 | 33821.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR16 | COMPONENT REHAB OF BRIDGES CITYWIDE (8 BRIDGES) | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 000 | HB-0215 |  | COMPONENT REHAB OF BRIDGES CITYWIDE (8 BRIDGES) | COMPONENT REHAB OF BRIDGES CITYWIDE (8 BRIDGES) | 2019 | 10724 | 2121.94 | 0 | 22373 | 0 | 0 | 0 | 0 | 24494.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR21A | COMPONENT REHAB OF BRIDGES 21A | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 000 | HB-0215 |  | CONVERSION DATA- DESCRIPTION REQUIRED | COMPONENT REHAB OF BRIDGES 21A | 2019 | 21550 | 718.98 | 2221 | 0 | 0 | 19238 | 0 | 0 | 22177.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR21B | COMPONENT REHAB OF BRIDGES 21B | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 000 | HB-0215 |  | COMPONENT REHAB OF BRIDGES 21B | COMPONENT REHAB OF BRIDGES 21B | 2019 | 19234 | 75 | 1685 | 0 | 182 | 17179 | 0 | 0 | 19121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR22A | COMPONENT REHAB OF BRIDGES 22A | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 000 | HB-0215 |  | COMPONENT REHAB | COMPONENT REHAB OF BRIDGES | 2019 | 21695 | 0 | 0 | 1951 | 0 | 0 | 21091 | 0 | 23042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR22B | COMPONENT REHAB OF BRIDGES 22B | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 000 | HB-0215 |  | COMPONENT REHAB OF BRIDGES 22B | COMPONENT REHAB OF BRIDGES 22B | 2019 | 19530 | 0 | 0 | 1935 | 0 | 0 | 19048 | 0 | 20983 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR23A | COMPONENT REHAB OF BRIDGES 23A | FINANCING COSTS | 000 | HB-0215 |  |  | COMPONENT REHAB OF BRIDGES 23A | 2019 | 0 | 0 | 0 | 1910 | 0 | 0 | 0 | 20435 | 22345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR23B | COMPONENT REHAB OF BRIDGES 23B | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 000 | HB-0215 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | COMPONENT REHAB OF BRIDGES 23B | 2019 | 22345 | 0 | 0 | 1910 | 0 | 0 | 0 | 20435 | 22345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR24A | COMPONENT REHAB OF BRIDGES 24A | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 000 | HB-0215 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | COMPONENT REHAB OF BRIDGES 24A | COMPONENT REHAB OF BRIDGES 24A | 2019 | 23020 | 0 | 0 | 0 | 0 | 1970 | 0 | 21050 | 23020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR24B | COMPONENT REHAB OF BRIDGES 24B | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 000 | HB-0215 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | COMPONENT REHAB OF BRIDGES 24B | COMPONENT REHAB OF BRIDGES 24B | 2019 | 20725 | 0 | 0 | 0 | 0 | 1970 | 0 | 18755 | 20725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBKBQE | Rehabilitation of BQE (I-278) from Sands St. to Atlantic Ave | FAIR BRIDGES | 000 | HB-1012 HB-0278 P-0508 |  | 21 BINS: 2268497; 2268498;2268507;2268508;2268517;2268518;2268350;2230410;2230420; 2230430; 2230440;2230450;2230460;2230470;2230480;2230490;2230857;2230858;2230870;2230887;2230888 | 21 BINS: 2268497; 2268498;2268507;2268508;2268517;2268518;2268350;2230410;2230420; 2230430; 2230440;2230450;2230460;2230470;2230480;2230490;2230857;2230858;2230870;2230887;2230888 | 2019 | 1901292 | 196639.26 | 704 | 9157 | 44810 | 661666 | 504563 | 479193 | 1896732.26 | 0 | 0 | 6507 | 0 | 0 | 0 | 0 | 6507
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBR10COMP | TEN YR COMP | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 000 | HB-0215 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  |  | 2019 | 43020 | 0 | 0 | 0 | 367 | 2009 | 47432 | 300000 | 349808 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBX1670 | EAST 169TH STREET OVER METRO NORTH RR BIN: 2241670 | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 000 | HB-0167 HB-1070 TF-0002 TF-0502 |  |  | EAST 169TH STREET OVER METRO NORTH RR ÝBIN: 2241670 | 2019 | 7265 | 2394.26 | 4583 | 5122 | 0 | 0 | 0 | 0 | 12099.26 | 0 | 56 | 0 | 0 | 0 | 0 | 0 | 56
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW200IFA1 | In-House Pedestrian Ramp Rehabilitation - Crews | PEDESTRIAN RAMP CONSTRUCTION | 000 | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | IN-HOUSE PEDESTRIAN RAMP REHABILITATION - CREWS | IN-HOUSE PEDESTRIAN RAMP REHABILITATION - CREWS | 2019 | 19402 | 13284.92 | 10832 | 33082 | 32434 | 32025 | 39969 | 239339 | 400965.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW200IFA2 | In-House Pedestrian Ramp Rehabilitation - OTPS | PEDESTRIAN RAMP CONSTRUCTION | 000 | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | IN-HOUSE PEDESTRIAN RAMP REHABILITATION - OTPS | IN-HOUSE PEDESTRIAN RAMP REHABILITATION - OTPS | 2019 | 24888 | 3654.52 | 9627 | 17681 | 14457 | 14471 | 6535 | 39989 | 106414.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR06 | CITYWIDE MILLING | PRIMARY STREET RESURFACING | 099 | HW-0002M | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | N/A |  | 2019 | 125195 | 0 | 0 | 0 | 10515 | 10670 | 8126 | 54777 | 84088 | 0 | 0 | 135 | 613 | 0 | 0 | 0 | 748
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR17A1 | Citywide Milling - Brooklyn and Staten Island | PRIMARY STREET RESURFACING | 000 | HW-0002K HW-0002R |  |  | CITYWIDE MILLING- BROOKLYN AND STATEN ISLAND | 2019 | 11420 | 0 | 11420 | 0 | 0 | 0 | 0 | 0 | 11420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR18B | Citywide Milling - Bronx and Manhattan | PRIMARY STREET RESURFACING | 000 | HW-0002M HW-0002X |  | CITYWIDE MILLING - BRONX AND MANHATTAN | CITYWIDE MILLING - BRONX AND MANHATTAN | 2019 | 11760 | 10168 | 7342 | 0 | 0 | 0 | 0 | 0 | 17510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR18D | Citywide Milling - Bronx, Manhattan and Queens | PRIMARY STREET RESURFACING | 000 | HW-0002X HW-0002M HW-0002Q |  | CITYWIDE MILLING - BRONX, MANHATTAN AND QUEENS | CITYWIDE MILLING - BRONX, MANHATTAN AND QUEENS | 2019 | 10139 | 8285 | 5329 | 0 | 0 | 0 | 0 | 0 | 13614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR18E | Citywide Milling - Brooklyn, Queens and Staten Island | PRIMARY STREET RESURFACING | 000 | HW-0002K HW-0002Q HW-0002R |  | CITYWIDE MILLING - BROOKLYN, QUEENS AND STATEN ISLAND | CITYWIDE MILLING - BROOKLYN, QUEENS AND STATEN ISLAND | 2019 | 10544 | 9503 | 5250 | 0 | 0 | 0 | 0 | 0 | 14753 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR19F | Citywide Milling - Brooklyn and Queens | PRIMARY STREET RESURFACING | 000 | HW-0002K HW-0002Q |  |  | CITYWIDE MILLING- BROOKLYN AND QUEENS | 2019 | 2529 | 0 | 2529 | 8660 | 0 | 0 | 0 | 0 | 11189 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW34907 | IN-HOUSE RESURFACING - CREWS&OTHER NON-ASPHALT OTPS | PRIMARY STREET RESURFACING | 099 | HW-0349 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  |  | 2019 | 891282 | 1050355.19 | 129237 | 138101 | 80738 | 82314 | 83921 | 564947 | 2129613.19 | 83493.27 | 0 | 0 | 0 | 0 | 0 | 0 | 83493.27
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWC349M03 | MANHOLE RINGS | PRIMARY STREET RESURFACING | 000 | HW-0349 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  |  | 2019 | 8370 | 646.99 | 924 | 1200 | 0 | 0 | 500 | 3373 | 6643.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCFTRLR | Citywide Trailer Rehabilitation | FACILITY RECONSTRUCTION | 000 | HB-1014 HW-0003 |  |  | CITYWIDE TRAILER REHABILITATION | 2019 | 3169 | 1656.49 | 1513 | 0 | 0 | 0 | 0 | 0 | 3169.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWC-HDBP | High-Density Bike Parking | PRIMARY STREET RECONSTRUCTION | 000 | HW-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | HIGH-DENSITY BIKE PARKING | HIGH-DENSITY BIKE PARKING | 2019 | 2800 | 0 | 0 | 0 | 0 | 2800 | 0 | 0 | 2800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCPDLOC2 | Perimeter Security Measures 2 | PRIMARY STREET RECONSTRUCTION | 000 | HW-0001 |  | PERIMETER SECURITY MEASURES 2 | PERIMETER SECURITY MEASURES 2 | 2019 | 70000 | 0 | 0 | 0 | 0 | 31452 | 0 | 35000 | 66452 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCSCH4D | Safe Routes to Schools - Phase 4D | PRIMARY STREET RECONSTRUCTION | 000 | HW-0988 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | SAFE ROUTES TO SCHOOLS - PHASE 4D | SAFE ROUTES TO SCHOOLS - PHASE 4D | 2019 | 4200 | 0 | 0 | 0 | 11358 | 0 | 0 | 0 | 11358 | 0 | 0 | 0 | 12195 | 0 | 0 | 0 | 12195
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCWREC | CITYWIDE RECONSTRUCTION OF STREETS | PRIMARY STREET RECONSTRUCTION | 099 | HW-0001Q HW-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | NA |  | 2019 | 546260 | 0 | 0 | 0 | 8500 | 5289 | 13896 | 85882 | 113567 | 0 | 0 | 0 | 0 | 0 | 5434 | 0 | 5434
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCW-SOGR | Citywide Streets - 30-Year State of Good Repair | PRIMARY STREET RECONSTRUCTION |  | HW-0001 HW-1684 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | CITYWIDE | FY13 JAN PLAN SUPPLEMENTAL REQUEST - CITYWIDE RECONSTRUCTION OF PRIMARY STREETS TO A STATE OF GOOD REPAIR ON A 30-YEAR CYCLE | 2019 | 49250 | 0 | 650 | 34804 | 4000 | 0 | 38343 | 30344 | 108141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCW-VZSR | Vision Zero Street Reconstuction | PRIMARY STREET RECONSTRUCTION | 000 | HW-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | VISION ZERO STREET RECONSTUCTION | 2019 | 272324 | 0 | 0 | 5871 | 0 | 4423 | 31182 | 0 | 41476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWMMPEDSW | MULTI-MODAL #2 - 2000 PED RAMPS AND SIDEWALK | SIDEWALK RECONSTRUCTION | 000 | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | MULTI-MODAL #2 - 2000 PED RAMPS AND SIDEWALK | MULTI-MODAL #2 - 2000 PED RAMPS AND SIDEWALK | 2019 | 260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 260 | 0 | 0 | 260
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPL20006 | PRIOR NOTICE SIDEWALK(SIM) | SIDEWALK RECONSTRUCTION | 000 | HW-0200 P-1018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  |  | 2019 | 180000 | 0 | 0 | 38698 | 31578 | 34938 | 32188 | 199343 | 336745 | 0 | 22837 | 11062 | 11062 | 11062 | 11062 | 66100 | 133185
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ015Q | Ozone Park Plaza | PRIMARY STREET RECONSTRUCTION | 000 | HW-1684 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | OZONE PARK PLAZA | OZONE PARK PLAZA | 2019 | 3000 | 0 | 0 | 0 | 0 | 2500 | 500 | 5717 | 8717 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPR19MXC | Complex Upgrades Ped Ramps - Manhattan and the Bronx | PEDESTRIAN RAMP CONSTRUCTION | 000 | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | COMPLEX UPGRADES PED RAMPS - MANHATTAN AND THE BRONX | COMPLEX UPGRADES PED RAMPS - MANHATTAN AND THE BRONX | 2019 | 7510 | 0 | 520 | 0 | 6955 | 0 | 0 | 0 | 7475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPR19QRC | Complex Upgrades Ped Ramps - Queens and Staten Island | PEDESTRIAN RAMP CONSTRUCTION | 000 | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | COMPLEX UPGRADES PED RAMPS - QUEENS AND STATEN ISLAND | COMPLEX UPGRADES PED RAMPS - QUEENS AND STATEN ISLAND | 2019 | 7421 | 0 | 524 | 0 | 6942 | 0 | 0 | 0 | 7466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPRINSTL | Pedestrian Ramps Installation - Lump Sum | PEDESTRIAN RAMP CONSTRUCTION | 000 | HW-0200 |  | PEDESTRIAN RAMPS INSTALLATION - LUMP SUM | PEDESTRIAN RAMPS INSTALLATION - LUMP SUM | 2019 | 40000 | 0 | 0 | 16983 | 0 | 36786 | 20000 | 122432 | 196201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPRREHAB | Pedestrian Ramps Rehabilitation - Lump Sum | PEDESTRIAN RAMP CONSTRUCTION | 000 | HW-0200 |  | PEDESTRIAN RAMPS REHABILITATION | PEDESTRIAN RAMPS REHABILITATION - LUMP SUM | 2019 | 75074 | 0 | 0 | 121951 | 0 | 41297 | 39112 | 252804 | 455164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWRAP07 | RAP HAULING | PRIMARY STREET RESURFACING | 000 | HW-0349 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | RAP HAULING | RAP HAULING | 2019 | 74651 | 61296.42 | 8776 | 6424 | 6424 | 6552 | 6684 | 45038 | 141194.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWSAFTR | Safe Routes to Transit | PRIMARY STREET RECONSTRUCTION | 000 | HW-1684 HW-0988 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | SAFE ROUTES TO TRANSIT | 2019 | 16058 | 0 | 0 | 0 | 0 | 11906 | 1904 | 12831 | 26641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWSTEP04 | STEP STREET REHABILITATION | RECONSTRUCTION OF STEP STREETS | 000 | HW-0211 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | CITYWIDE | STEP STREET REHABILITATION CITYWIDE | 2019 | 10100 | 0 | 0 | 0 | 0 | 1122 | 0 | 0 | 1122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWTSQI | Public Plaza Improvements | PRIMARY STREET RECONSTRUCTION | 000 | HW-1684 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | TOWN SQUARE INITIATIVE | 2019 | 133970 | 0 | 0 | 0 | 0 | 27632 | 6045 | 40735 | 74412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | ITSBELTPK | Intelligent Transportation Systems on Belt Parkway X501.62 | SIGNAL INSTALLATION AND COMPUTERIZATION | 000 | TF-0001 |  |  | NYCDOT'S TRAFFIC MANAGEMENT CENTER HAS LIMITATIONS TO PROVIDING DAILYTRAFFIC INCIDENT REPORTS ALONG THE BELT PARKWAY. THIS ITS PROJECT AIMS AT DEPLOYING ITS SYSTEM TO PROVIDE REAL-TIME INFORMATION AND DISSEMINATE TRAFFIC ADVISORY INFORMATION TO THE MOTORIST OF RECURRING, NON-RECURRING EVENTS AND TRAVEL TIME. | 2019 | 4925 | 0 | 0 | 985 | 0 | 0 | 0 | 0 | 985 | 0 | 0 | 3940 | 0 | 0 | 0 | 0 | 3940
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | MOLRETROF | MOLINARI CLASS UPGRADES-RETRO FIT | RECONSTRUCTION OF FERRY BOATS | 000 | FA-0313 |  | MOLINARI CLASS UPGRADES-RETRO FIT | MOLINARI CLASS UPGRADES-RETRO FIT | 2019 | 11030 | 770.7 | 0 | 4144 | 5934 | 0 | 226 | 0 | 11074.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | NYCWINRPL | NYCWIN Replacement | SIGNAL INSTALLATION AND COMPUTERIZATION | 000 | TF-0001 |  |  | NYCWIN REPLACEMENT | 2019 | 75000 | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | PARKMLPR | Parking Meters Retrofitted for License Plate Recognition | Parking Meters, Lots, and Garages | 000 | TF-0003 |  |  | METER UPGRADE | 2019 | 0 | 0 | 13000 | 26713 | 0 | 0 | 0 | 0 | 39713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | PLANTRANS | TRANSIT SIGNAL PRIORITY-2030 | SIGNAL INSTALLATION AND COMPUTERIZATION | 000 | TF-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | TRANSIT SIGNAL PRIORITY-2030 | TRANSIT SIGNAL RIORITY-2030 | 2019 | 9246 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 300 | 1222.03 | 0 | 0 | 0 | 0 | 0 | 0 | 1222.03
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | RTPIFY19 | REAL TIME PASSENGER INFO SIGNS - FY19 | SIGNAL INSTALLATION AND COMPUTERIZATION | 000 | TF-X001 TF-D005 TF-K001 |  |  | FUNDING FOR FURNISH AND INSTALLATION OF REAL TIME PASSENGER INFORMATION SIGNS CITYWIDE FY19 | 2019 | 7441 | 0 | 7441 | 0 | 0 | 0 | 0 | 0 | 7441 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SAND-349R | Citywide In-House Resurfacing - Hurricane Sandy Recovery | PRIMARY STREET RESURFACING | 000 | HW-0349 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | CITYWIDE IN-HOUSE RESURFACING - HURRICANE SANDY RECOVERY | IN-HOUSE RESURFACING - HURRICANE SANDY RECOVERY | 2019 | 43320 | 453.38 | 0 | 22 | 0 | 0 | 0 | 0 | 475.38 | 4080.44 | 0 | 201 | 0 | 0 | 0 | 0 | 4281.44
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SANDCONDU | SANDY CONDUIT ADDITIONAL CITY-WIDE WORK | REPLACEMENT OF ELECTRICAL DISTRIBUTION SYSTEMS | 000 | HW-0003 TF-0503 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | SANDY CONDUIT ADDITIONAL CITY-WIDE WORK | 2019 | 29731 | 30 | 0 | 294 | 0 | 589 | 0 | 0 | 913 | 0 | 0 | 2641 | 0 | 5295 | 0 | 0 | 7936
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SANDHB002 | Rehab of Movable Bridges Citywide - Sandy | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 000 | HB-0215 |  |  | TO REPAIR VARIOUS MOVABLE BRIDGES DAMAGED DUE TO HURRICANE SANDY, CITYWIDE. | 2019 | 35654 | 26058.16 | 441 | 1338 | 0 | 0 | 0 | 0 | 27837.16 | 82283.35 | 1764 | 8811 | 0 | 0 | 0 | 0 | 92858.35
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SANDRF05 | Construction of New Ferryboats | RECONSTRUCTION OF FERRY BOATS | 000 | FA-0313 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CONSTRUCTION OF 3 NEW FERRYBOATS | 2019 | 340000 | 81806.75 | -14882 | 0 | 0 | 13696 | 14093 | 0 | 94713.75 | 169099.63 | 14882 | 0 | 0 | 49024 | 0 | 0 | 233005.63
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SANDRF07 | SEVERE WEATHER MOORING UPGRADE | RECONSTRUCTION OF FERRY TERMINAL FACILITIES | 000 | FA-0021 |  | SEVERE WEATHER MOORING UPGRADE | SEVERE WEATHER MOORING UPGRADE | 2019 | 2844 | 94.53 | -42 | 0 | 215 | 311 | 0 | 0 | 578.53 | 338.12 | 43 | 0 | 1894 | 0 | 0 | 0 | 2275.12
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SANDRF08 | SIF COMPUTER & ELECTRICAL EQUIPMENT RELOCATION | RECONSTRUCTION OF FERRY TERMINAL FACILITIES | 000 | FA-0021 |  | SIF COMPUTER & ELECTRICAL EQUIPMENT RELOCATION | SIF COMPUTER & ELECTRICAL EQUIPMENT RELOCATION | 2019 | 569 | 0 | 0 | 0 | 0 | 0 | 0 | 114 | 114 | 0 | 0 | 0 | 0 | 0 | 0 | 455 | 455
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SANDRF10 | ROCK-SOCKETED STEEL MOORING PILES | RECONSTRUCTION OF FERRY TERMINAL FACILITIES | 000 | FA-0021 |  | ROCK-SOCKETED STEEL MOORING PILES | ROCK-SOCKETED STEEL MOORING PILES | 2019 | 14751 | 0 | 0 | 0 | 0 | 0 | 2950 | 0 | 2950 | 0 | 0 | 0 | 0 | 0 | 11801 | 0 | 11801
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SANDRF11 | Ferry Terminal Floodproofing | RECONSTRUCTION OF FERRY TERMINAL FACILITIES | 000 | FA-0021 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | MEASURES TO MITIGATE STORM SURGE IMPACT AT SIF FACILITIES | 2019 | 25355 | 20 | 1147 | 4299 | 0 | 0 | 0 | 0 | 5466 | 0 | 0 | 19570 | 0 | 0 | 0 | 0 | 19570
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SANDTFITS | Various ITS Replacements - Sandy | SIGNAL INSTALLATION AND COMPUTERIZATION | 000 | TF-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | VARIOUS ITS REPLACEMENTS - SANDY | VARIOUS ITS REPLACEMENTS - SANDY | 2019 | 4256 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 305 | 0 | 0 | 305
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SEQUEENS | South East Queens Initiative | PRIMARY STREET RECONSTRUCTION | 000 | HW-0001Q |  | SOUTH EAST QUEENS INITIATIVE | SOUTH EAST QUEENS INITIATIVE | 2019 | 100505 | 0 | 0 | 0 | 0 | 0 | 0 | 54769 | 54769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SIGNALSF2 | TRAFFIC SIGNAL SAFETY, CITYWIDE | SIGNAL INSTALLATION AND COMPUTERIZATION | 000 | TF-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | TRAFFIC SIGNAL SAFETY, CITYWIDE | TRAFFIC SIGNAL SAFETY, CITYWIDE | 2019 | 70000 | 2719 | 7500 | 9478 | 9099 | 0 | 0 | 0 | 28796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SIGNALSFY | TRAFFIC SIGNALS SAFETY, CITYWIDE | SIGNAL INSTALLATION AND COMPUTERIZATION | 000 | TF-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | SIGNALS INSTALLATION | 2019 | 15500 | 8956.18 | 0 | 0 | 0 | 47 | 0 | 0 | 9003.18 | 13944.44 | 0 | 0 | 0 | 930 | 0 | 0 | 14874.44
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SLMNTLUMP | CAPITAL COMPONENT STREETLIGHT MAINTENANCE (TEN YR PLAN) | INSTALLATION OF LAMPPOSTS AND LUMINAIRES | 000 | TF-0503 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | CAPITAL COMPONENT STREET LIGHT MAINTENANCE | CAPITAL COMPONENT STREET LIGHT MAINTENANCE | 2019 | 30500 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 44000 | 44000
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | STEFFSCMV | NYC Street Efficiency Strategic Commercial Vehicle Monitorin | SIGNAL INSTALLATION AND COMPUTERIZATION | 000 | TF-0001 |  |  | CVM | 2019 | 2441 | 0 | 0 | 1174 | 1175 | 0 | 92 | 0 | 2441 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TF012013 | NEW SIGNAL INSTALLATION REQUIREMENT CONTRACT FY13 | SIGNAL INSTALLATION AND COMPUTERIZATION | 000 | TF-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | INSTALLATION OF NEW SIGNALS | 2019 | 15500 | 4965 | 0 | 0 | 0 | 0 | 0 | 0 | 4965 | 12805.29 | 0 | 0 | 0 | 1499 | 0 | 0 | 14304.29
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TF012014 | NEW SIGNALS INSTALLATION REQUIREMENT | SIGNAL INSTALLATION AND COMPUTERIZATION | 000 | TF-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | NEW SIGNAL INSTALLATION REQUIREMENT | NEW SIGNAL INSTALLATION REQUIREMENT | 2019 | 16600 | 8274.69 | 0 | 0 | 0 | 0 | 0 | 0 | 8274.69 | 15182.75 | 0 | 0 | 0 | 289 | 0 | 0 | 15471.75
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TF012017 | NEW SIGNALS INSTALLATION REQUIREMENT FY17 | SIGNAL INSTALLATION AND COMPUTERIZATION | 000 | TF-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | FURNISHED AND INSTALL NEW SIGNALS | 2019 | 28932 | 3957.35 | 4659 | 0 | 0 | 0 | 0 | 0 | 8616.35 | 17969.82 | 0 | 2371 | 0 | 0 | 0 | 0 | 20340.82
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TF012019 | NEW SIGNALS INSTALLATION REQUIREMENT 2019 | SIGNAL INSTALLATION AND COMPUTERIZATION | 000 | TF-0001 |  |  | THIS CONTRACT IS FOR THE FURNISHING, INSTALLATION AND REMOVAL OF ELECTRICAL TRAFFIC SIGNAL EQUIPMENT TO CONTROL TRAFFIC IN THE FIVE BOROUGHS OF THE CITY OF NEW YORK. THE WORK WILL BE ISSUED TO THE CONTRACTOR. | 2019 | 32426 | 0 | 2400 | 4763 | 4763 | 0 | 0 | 0 | 11926 | 0 | 6200 | 7150 | 7150 | 0 | 0 | 0 | 20500
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TF01-9910 | LOCAL STREET NETWORK MGMT AND INCIDENT MGMT X500.94 | SIGNAL INSTALLATION AND COMPUTERIZATION | 000 | TF-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | LOCAL STREET NETWORK MGMT AND INCIDENT MGMT | LOCAL STREET NETWORK MGMT AND INCIDENT MGMT | 2019 | 4346 | 3581.97 | 0 | 0 | 0 | 1738 | 0 | 0 | 5319.97 | 3231.39 | 0 | 0 | 0 | 0 | 0 | 0 | 3231.39
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TF01-9911 | Advance Travel Information System Upgrade | SIGNAL INSTALLATION AND COMPUTERIZATION | 000 | TF-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | UPGRADE OF EZPASS REVENUE SYSTEM | 2019 | 500 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TF01APS | Accessible Pedestrian System(AT 75 LOCATIONS PER YEAR) | SIGNAL INSTALLATION AND COMPUTERIZATION | 000 | TF-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | APS (AT 75 LOCATIONS PER YEAR ) | APS (AT 75 LOCATIONS PER YEAR ) | 2019 | 15200 | 0 | 0 | 5048 | 5050 | 10098 | 0 | 41596 | 61792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TF01VARMS | Variable Message Signs Replacement, Citywide | SIGNAL INSTALLATION AND COMPUTERIZATION | 000 | TF-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | VARIABLE MESSAGE SIGNS REPLACEMENT , CITYWIDE | 2019 | 4586 | 0 | 0 | 4586 | 0 | 0 | 0 | 0 | 4586 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TF18-LUMP | LUMP SUM FOR PARKING RECONSTRUCTION | Parking Meters, Lots, and Garages | 000 | TF-0018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | CITY-WIDE | LUMP SUM FOR PARKING RECONSTRUCTION | 2019 | 1405 | 0 | 0 | 0 | 0 | 2008 | 2938 | 0 | 4946 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFCWSBST | SBS-Citywide Real Time Totem System | SIGNAL INSTALLATION AND COMPUTERIZATION | 000 | TF-0001 |  |  | PURCHASE AND INSTALLATION OF TOTEM SIGNS CITYWIDE ON SBS ROUTES | 2019 | 0 | 0 | 1675 | 0 | 0 | 1882 | 0 | 0 | 3557 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFITSAMS | INTELLIGENT TRANSPORTATION SYSTEM(ITS) ON HIGHWAYS | SIGNAL INSTALLATION AND COMPUTERIZATION | 000 | TF-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | ITS AND AMS INSTALLATION | ITS AND AMS INSTALLATION | 2019 | 27758 | 492.36 | 0 | 0 | 1219 | 2205 | 0 | 0 | 3916.36 | 1969.46 | 0 | 0 | 2678 | 6618 | 0 | 0 | 11265.46
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFLGUDECK | Lighting at underdeck Structure, citywide | INSTALLATION OF LAMPPOSTS AND LUMINAIRES | 000 | TF-0503 |  |  | FURNISH AND INSTALL LIGHT AT UNDERDECK | 2019 | 4000 | 0 | 1799 | 2201 | 0 | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFLGUSBWY | Furnish and Install Lighting under elevated structures | INSTALLATION OF LAMPPOSTS AND LUMINAIRES | 000 | TF-0503 |  |  | FURNISH AND INSTALL LIGHT UNDER ELEVEATED SUBWAY | 2019 | 7735 | 0 | 3735 | 0 | 1241 | 2000 | 0 | 0 | 6976 | 0 | 0 | 0 | 759 | 0 | 0 | 0 | 759
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFMARKLMP | THERMOPLASTIC MARKINGS-TEN YEARS | INSTALLATION OF PAVEMENT MARKINGS | 000 | TF-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | INSTALLATION OF THERM MARKINGS ON RESURFACED STREETS | 2019 | 30456 | 0 | 0 | 10300 | 0 | 10804 | 0 | 69279 | 90383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFPEDCDW3 | Furnish and install Pedestrian Countdown Clocks | SIGNAL INSTALLATION AND COMPUTERIZATION | 000 | TF-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | URNISH AND INSTALL PEDESTRIAN COUNTDOWN CLOCKS | 2019 | 3222 | 0 | 0 | 322 | 0 | 0 | 0 | 0 | 322 | 0 | 0 | 2900 | 0 | 0 | 0 | 0 | 2900
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFPWSIGNL | PROACTIVE WARRANT NEW SIGNALS INSTALLATION | SIGNAL INSTALLATION AND COMPUTERIZATION | 000 | TF-0001 |  |  | NEW SIGNALS INSTALLATION | 2019 | 10500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10500 | 0 | 0 | 0 | 0 | 0 | 10500
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFSPDCAM | Purchase and Install Speed Cameras in School Zones Areas | SIGNAL INSTALLATION AND COMPUTERIZATION | 000 | TF-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | SPEED CAMERA | SPEED CAMERA | 2019 | 2495 | 26170.18 | 33620 | 0 | 0 | 2194 | 0 | 0 | 61984.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFVISIONZ | Traffic Vision Zero projects-St Light Enhancement | INSTALLATION OF LAMPPOSTS AND LUMINAIRES | 000 | TF-0503 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | ST LIGHT AND SPEED CAMERAS FURNISHED AND INSTALLATION | 2019 | 3949 | 2261.09 | 82 | 1606 | 0 | 0 | 0 | 0 | 3949.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TRNCHREST | Trench Restoration | PRIMARY STREET RECONSTRUCTION | 000 | HW-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | TRENCH RESTORATION | TRENCH RESTORATION | 2019 | 60000 | 0 | 0 | 0 | 0 | 6957 | 0 | 0 | 6957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TTEXTOSP | Upgrade of SBS Totems System, Citywide | SIGNAL INSTALLATION AND COMPUTERIZATION | 000 | TF-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | RETROFFING OF SBS TOTEMS CITYWIDE | 2019 | 908 | 0 | 909 | 0 | 0 | 0 | 0 | 0 | 909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TYPLILL | STREET LIGHTING <TEN YEAR PLAN) | INSTALLATION OF LAMPPOSTS AND LUMINAIRES | 000 | TF-0503 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  |  | 2019 | 70000 | 0 | 0 | 0 | 15 | 0 | 15 | 112 | 142 | 0 | 0 | 0 | 7500 | 0 | 7500 | 22500 | 37500
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TYPLREP | TRAFFIC PARK & HIGHWAY DISTRIBUTION(TEN YEAR PLAN) | REPLACEMENT OF ELECTRICAL DISTRIBUTION SYSTEMS | 000 | TF-0503 P-0705 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  |  | 2019 | 55300 | 0 | 0 | 0 | 0 | 0 | 600 | 0 | 600 | 0 | 0 | 0 | 5000 | 0 | 5000 | 15000 | 25000
20190425 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TYPLSGM | TRAFFIC SIGNALS (TEN YEAR PLAN) | SIGNAL INSTALLATION AND COMPUTERIZATION | 000 | TF-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  |  | 2019 | 172000 | 0 | 0 | 0 | 0 | 7094 | 7094 | 29236 | 43424 | 0 | 0 | 0 | 0 | 10000 | 20500 | 61500 | 92000
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | ACEDPR402 | LIGHTING | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT |  | PU-0025 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | PARKS LIGHTING CITYWIDE - ACE PROGRAM | 2019 | 2204 | 2117.43 | 85 | 34 | 0 | 0 | 0 | 0 | 2236.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | ACEDPR403 | DPR efficient lighting @various facilities 5bor CNYG-2415MA1 | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT |  | PU-0025 |  | FY15 $1 CONTRACT FOR DCAS ACE PROGRAM | FY15 $1 CONTRACT FOR DCAS ACE PROGRAM | 2019 | 2500 | 2500.72 | 0 | 228 | 0 | 0 | 0 | 0 | 2728.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | ACEDPR404 | DPR efficient lighting @ ballfields SI & Q CNYG-2815M | MISCELLANEOUS ENERGY EFFICIENCY AND SUSTAINABILITY |  | P-1018 P-0882 |  | DACS - ENERGY EFFICIENCY BALLFIELD LIGHTING RETROFIT AT VARIOUS PARKS& RECREATION FACILITIES, FOR THE BOROUGHS OF THE BX & QN | DCAS - ENERGY EFFICIENCY BALLFIELD LIGHTING RETROFIT AT VARIOUS PARKS& RECREATION FACILITIES, FOR THE BOROUGHS OF THE BX & QN | 2019 | 1460 | 1606 | 2 | 15 | 0 | 157 | 0 | 0 | 1780 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | ACEDPR405 | DPR efficient lighting @ ballfields MN, BK & BX CNYG-2915 | MISCELLANEOUS ENERGY EFFICIENCY AND SUSTAINABILITY |  | P-1018 PU-0025 |  | DCAS - ENERGY EFFICIENCY BALLFIELD LIGHTING RETROFIT AT VARIOUS PARKS& RECREATION FACILITIES, FOR THE BOROUGHS OF THE MN, BK & SI | DCAS - ENERGY EFFICIENCY BALLFIELD LIGHTING RETROFIT AT VARIOUS PARKS& RECREATION FACILITIES, FOR THE BOROUGHS OF THE MN, BK & SI | 2019 | 2386 | 2856 | 1342 | 1193 | 0 | 0 | 0 | 0 | 5391 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | GXBXBKQ1 | GI Citywide-Bioswales in Parks Bronx, Queens & Brooklyn | LAND ACQUISITION AND TREE PLANTING | 000 | WP-0169 |  | GI CITYWIDE-BIOSWALES IN PARKS BRONX, QUEENS & BROOKLYN | GI CITYWIDE-BIOSWALES IN PARKS BRONX, QUEENS & BROOKLYN | 2019 | 2272 | 321.3 | 502 | 1021 | 1230 | 0 | 0 | 0 | 3074.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-3ALRMMN | Manhattan - Fire Alarm | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 000 | P-1008 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | MANHATTAN | MANHATTAN - FIRE ALARM | 2019 | 1150 | 1928 | 0 | 0 | 0 | 193 | 0 | 0 | 2121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-600ZOO3 | Citywide Zoos - roof replacements at various buildings | ZOOS | 000 | P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | REPLACEMENT OF ROOFS AT QUEENS ZOO OPERATIONS BUILDING, PROSPECT PARKZOO BUILDING A, PROSPECT PARK ZOO BUILDING E, AND PROSPECT PARK ZOO BUILDING F | REPLACEMENT OF ROOFS AT QUEENS ZOO OPERATIONS BUILDING, PROSPECT PARKZOO BUILDING A, PROSPECT PARK ZOO BUILDING E, AND PROSPECT PARK ZOO BUILDING F | 2019 | 2007 | 1773 | 177 | 0 | 0 | 0 | 0 | 0 | 1950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-600ZOO4 | Citywide Zoos - HVAC replacements | ZOOS | 000 | P-0887 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | CENTRAL PARK ZOO AND PROSPECT PARK ZOO | HVAC REPLACEMENT AT CPZ DANCING CRANE CAFE, CPZ ZOOTIQUE GIFT SHOP, CPZ OUTDOOR BIRD HOLDING, AND PPZ CLINIC | 2019 | 790 | 718 | 72 | 0 | 0 | 0 | 0 | 0 | 790 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-600ZOO5 | Citywide Zoos - HVAC at CPZ snow leopard & QZ concession | ZOOS | 000 | P-0887 |  | CITYWIDE ZOOS - HVAC AT CPZ SNOW LEOPARD & QZ CONCESSION | CITYWIDE ZOOS - HVAC AT CPZ SNOW LEOPARD & QZ CONCESSION | 2019 | 700 | 0 | 100 | 600 | 0 | 0 | 0 | 0 | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6517CBF | Capital Fund Reconstitution | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 000 | P-1018 P-0944 |  | 11/20/17 $168K (P-0060 FY18) FR P-1PNYC06...$25K P1250 FY19 FR P-217HVAC...$201K TR FR P-2PNYSP2 (P-0127 CHANGED BL TO P 1018)...$803(FY19 ) AND $197K(FY18) TRF FR P-212CDMP (CHANGED B/L P 1018)...$2388K (P-1018,FY18) TR TO P-1FERRY8...$17K FY20 P1026 & $10K FY20 P1018 TR FR P-501SIB2..$1K FY20 FR P-5BWPA00..$65K P-0245 TR FR P-500WAR..$57K P-1322FY18 FR P-6517CBF..$106K FR P-1PNYC04..$72K(FY18,PC021) FR P-102LAFA.. $1K(,P1329) FR P-1VCMEMO $242K OFFSET FORESTFY18 TO FY19..$20K FR P-501SIB2..$2K (P1250 FR P-4061250..$480K FR P-5GBPATH.. | TRF TO P-208LTPG (P 0374 FY19) $676K...8/17/17 $134K P1018 FY19 TRSFRTO P-4CARSON...FY18 $112K TR TO P-501CLRT...$187K P0374 FY18 TRSF TOP-313CPAB...8/24/17 $205K (P-1018, FY19) XFER FROM P-1BCREQ6...$66K (P1018, FY 18) TRF FR P-2BFREQ2 TO FY'19..8/29/17 $1.5M (P-0374, FY18)TR TO P-1PTSNPK, BUT WILL CHNAGE B/L TO P-1018 IN P-1PTSNPK,...FY 18 $31K ( P C017) TRF IN FR P-202C17I... $6K ( P C017) TRF IN FR P-203C17G...$19K ( P C017) TRF IN FR P-209C17B...$335K ( P0972) & $77K ( P C017) TRF IN FR P-210P972..$154K ( P0245K) TRF IN FR P-212245K...$6K ( P C017) TRF IN FR P-211C017...$8K ( P C017) TRF IN FR P-211C17A...$5K ( P C017) TRF IN FR P-213C17E...$77K ( P C017) TRF IN FR P-213C54B...$2K( P 0245K TRF IN FR P-200JFKM...$15K TRF FR P-3BWPE98...$412K FR P-413IDPK.. $10K FR P-3PLG11A.$101K FR 850 P3CROMNEW..$2K FR 850 P-1PBSSTAR | 2019 | 7121 | 0 | 8141 | 0 | 0 | 0 | 0 | 0 | 8141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-65BORO | 5 Boro Relocation - 850 East 138th street, Bronx | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 000 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | CW | 5 BORO RELOCATION | 2019 | 30000 | 5.08 | 0 | 0 | 0 | 0 | 0 | 0 | 5.08 | 10200 | 2629 | 0 | 0 | 0 | 0 | 0 | 12829
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6BLGC15 | FY15 Citywide buildings (gen construction) CNYG-1615MA | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION |  | P-D019 |  | CITYWIDE | FY15 CITYWIDE BUILDINGS (GEN CONSTRUCTION) | 2019 | 1025 | 633.2 | 0 | 36 | 0 | 0 | 0 | 0 | 669.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6BLRC14 | RC OF C/S & FACILITIES @ VARIOUS PKS MAYOR FUNDED CNYG-814MA | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 000 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | CITYWIDE BUILDINGS | RC OF C/S & FACILITIES AT VARIOUS PKS MAYOR FUNDED | 2019 | 3050 | 1932.63 | 804 | 400 | 0 | 0 | 0 | 0 | 3136.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6BOIL15 | MOSHOLU PK CS, PROSPECT PK PAINT SHOP, BENSONHURST SR CTR | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 000 | P-1250 |  |  | MOSHOLU PK CS, PROSPECT PK PAINT SHOP, BENSONHURST SR CTR | 2019 | 348 | 54 | 9 | 0 | 0 | 1063 | 0 | 0 | 1126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6BORDRS | Parks Without Borders | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 000 | P-1018 |  | FY18 EXEC PLAN $26K FR P-4CPIVAL...$290K TO P-303TSPL...5/10/17 $1048K ($503K FY18, $545K FY19) TRSFR TO P-4PWOB01...1/12/18 $381K ($53K FRP-4CPIVAL, $82K FR P-3CPIJAK, $62K FR P-2CPISBF, $42K FR P-2CPITBP, $34K FR P-3CPISOL, $2K FR P-1CPISEA, $1K FR P-500ARPG, $13K FR P-309CARM, $49K FR P-3CPILMLK, $15K FR P-1CPILSQ, $9K FR P-4CPIGRS, $19K FR P-1CPIRNQ)...3/8/18 $20K TO P-2CPISBF... | $476K TO P-1CPILSQ...$1.11M XFER FROM P-6CPIBN8...$102K FR P-3CPIBN9...TRF $4K FRON P-3CPIJWJ...$278K TRSF TO P-6CPIBN3...$134K FR P-6CWNPFY17 EXE...FY'16- $8K TO P-1CPIHNT, $254K TO P-1CPILFG, $42K TO P-1CPIP52, $35K TO P-1CPIRNQ, $23K TO P-2CPIJOP, $47K TO P-2CPISBF, $25K TOP-2CPISTK, $56K TO P-2CPITEN, $12K TO P-309CARM, $2K TO P-3CPIJAK, $15K TO P-3CPIJWJ, $30K TO 3CPIMLK, $127K TO P-3CPIBN9, $28K TO P-4CPIVAL, $19K TO P-4CPIGRS, $11K TO P-5CPIDMT...$TRF 200K TO P-303TSPL...$15K TO P-5CPIGVP...$47K TO P-2CPIBN7..TRF $4.400M (FY18) TO P-3PWBJRP...TRF $6.400M(FY18) TO P-3PWBSEP...$7K (FY17)TO P-2CPISTK...$4.2M (P1018, FY18) TO P-111VCPE PER JCG... $7.1M TO P-1HGCVPR ($550K FY17, $6,550 FY19)...$3M P1018 ($1403K FY17 TO FY18, $1597K FY18) TO P-4PWOB01...$450K(FY18) & $4005K (FY19)TO P-501FABL | 2019 | 45574 | 0 | 15 | 0 | 51 | 0 | 0 | 0 | 66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6BRIDGE | Citywide Flag Repairs | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 000 | P-0508 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | CW | FLAG REPAIRS | 2019 | 4000 | 0 | 0 | 0 | 2181 | 0 | 0 | 0 | 2181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6COMF18 | Recon citywide Comfort Stations $1 contract | NEIGHBORHOOD PARKS AND PLAYGROUNDS |  | P-0505 |  | CITYWIDE | RECON CITYWIDE COMFORT STATIONS $1 CONTRACT | 2019 | 2657 | 0 | 2657 | 0 | 0 | 0 | 0 | 0 | 2657 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CPIBN3 | CPI PH1- Construction of CW C/S CNYG-3215M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 000 | P-1018 WP-0169 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | CITYWIDE | THE CONSTRUCTION OF TEN, EYCK PLGD CS, LYONS SQUARE PLGD CS, MELROSE COMMONS CS, SAW MILL PLGD CS, HENRY M. JACKSON PLGD CS, LUTHER GULICK PLGD CS | 2019 | 1392 | 18552.65 | 283 | 0 | 0 | 1970 | 0 | 0 | 20805.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CPIBN4 | CPI PH1- Bx & Mn C/S-Bundle 4 CNYG-3315M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION |  | P-1018 |  | CPI- BX & MN COMFORT STATIONS-BUNDLE 4 | CPI- BX & MN COMFORT STATIONS-BUNDLE 4 | 2019 | 555 | 9254.95 | 12 | 0 | 0 | 579 | 0 | 0 | 9845.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CPIPH2 | Community Parks Initiative (CPI) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 000 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | $181K OFFSET W/P1CPIOPG FY18 TO FY19..$52K TRSF TO P-1CPIOPG..7/28/17$2434K FY19 TRSF TO P-3CPI3AP..$361K FY18 TRSF TO ($325K P-1CPIBPG, $36K P-1CPIWPK)..$4688K OFFSET W P-5CPISTP FY19 TO FY18..8/21/17 $36,727K TRSF TO (FY18 - $933K P-3CPI3AL, $888K P-2CPIBRT, $140K P-2CPILWS, $627K P-1CPIPRO, $869K P-106MAPE, $2167K P-3CPIHLM; FY19 - $1148K P-3CPIBBJ, $221K P-2CPIBRT; FY20 - $5555K P-2CPIBRT, $905K P-2CPIPEN, $905K P-2CPILWS, $4072K P-1CPIPRO, $5643K P-106MAPE, $2022K P-3CPIPGI, $2937K P-3CPISUR, $3258K P-4CPICHP, $1806K P-5CPIMH, $2631K P-3CPIHLM)... | XFERS FY17: $459K TO P-3CPIJAK, $644K TO P-3CPIJWJ, $666K TO P-2CPISBF, $2.657M TO P-3CPIBN9, $809K TO P-4CPIGRS, $283K TO P-2CPIJOP, $195KTO P-5CPIDMT..XFER $242K TO P-500ARPG..XFER $212K TO P-6CPIQBR..XFER $171K TO P-6CPIMNX..XFER $222K TO P-6CPIBN4..XFER $5176K TO P-6CWRC2..XFER $1035K TO P-5CPIGVP..XFER $239K TO P-1CPILFG..XFER $535K FR P-6CPIBN3...XFER $1.1M FY17 TO P-303LGPK..XFER FY17 $190K TO P-2CPIWKS, $535K TO P-2CPILGD...XFER FY19 $1.710M TO P-2CPIWKS, $4.815M TO P-2CPILGD..XFER $730K FY17 TO P-3CPIAB...XFER $6570K FY18 TO P-3CPI3AB...XFER $53K FY17 TO P-6CPIBN4...XFER $171K FY17 FR P-6CPIMNX..XFER $212K FY17 FR P-6CPIQBR..XFER $538K FY17 TO P-4CPIBN5...XFERS $12.916M FY19: $2.23M TO P-1CPI134, $4.435M TO P-1CPIPMT, $1.5M TO P-1CPIGAR, $4.751M TO P-100BRH1..XFER $1055K FY17 $470K TO P-1CPI134, $585K TO P-100BRH1... | 2019 | 107106 | 0 | 213 | 2399 | 5666 | 7548 | 0 | 0 | 15826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CSBLDG | Reconst of Comfort Stations & Buildings Citywide CNYG-219M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 000 | P-0505 P-1018 |  |  | RECONSTRUCTION OF COMFORT STATIONS AND BUILDINGS CITYWIDE | 2019 | 2800 | 0 | 0 | 1000 | 1800 | 0 | 0 | 0 | 2800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CW1250 | BOILERS RECONSTRUCTION,CITYWIDE | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 000 | P-1250 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | TRF FR P-202BWHB ($30K P 1250 FY18 AND $1470 FY19)...3/5/2018 $1052K (P-1250 FY19) XFER FR P-3ALBOIL...7/19/18 $1900K P-1250 FY21 TRSF TO P-306ASLV...7/26/18 $4,885K P-1250 FY21 XFER TO P-3HANSBO...10/23/18 $37K P1250 TRSF TO P-414SRHV...FY20 JAN NN REQUEST TOTAL 60,735M .. ($5,135 FY20; $5,315 FY21; $5,520 FY22; $5,740 FY23; $5,965 FY24; $6,190 FY25; $6,410 FY26, $6,620 FY27 $6,820 FY28 $7,020 FY29)...FY20J NN NOT APPROVED. 2/25/19 $3.4M ($3.1M P-1250 FY21, $300K P-1250 FY22) XFER TO P-4OLMST4; $150K P-1250 FY19 XFER TO P-215BBPG | RC OF BOILERS - CW...FY'15 TRF $1.0M TO P-217PDGT...$1500K FY17 P1250TRSF TO P-101STMH...$735K P1250 FY17 TRSF P-414SRHV...$900K P1250 TRSF TO P-1BWRCTR..FY'16 $182 TRF TO P-208HVAC...$415K (FY'17) TRF TO P-208HVAC...FY17 JAN PL NEW NEEDS $3655K FY18, $3660 FY19, $3942K FY20...FY17 JAN PL NEW NEEDS REJECTED $3655K FY18, $3660 FY19, $3942K FY20...TRF $100K TO P-110PBBL...$443K TO P-501FABB.....$1.426M ADDED FY26 & $1.470M IN FY27... FY18 JAN PLAN NEW NEEDS - $5,335 FY19, $7,461 FY20,$7,659 FY21, $7,853 FY22, $8,038 FY23, $8,200 FY24, $8,351 FY25, $10,344 FY26 & $10,592 FY27...$1300 FY18 P1250 TRSF TO P-311HCTR...$1500 FY18 (P 1250) TO P-202BWHB....$1500K FY18 P1250 TRSF TO P-311HCTR...XFER $646K (P-1250, FY18) TO P-101STMH...$1K TO P-5BOIL10..FY18: TRF $11KFROM P-3BOIL07...TRF FR P-218BILD $1K .$5K TOP-5BOIL10. | 2019 | 13931 | 443.24 | 0 | 58 | 0 | 893 | 5500 | 44355 | 51249.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWASBR | Citwide - HazMat Abatement & Borings | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 000 | P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | VARIOUS FACILITIES | XFER $195K (P-1018) TO P-6ROOF15...$800K (P 1018) TO P-218BILD...$200K XFER FR P-6HZMT11...$57K TRF TO P-215KELY.... $64K P-1018 TO P-6ROOF15...FY18 TRANSFER ÝP-1018 $192K TO P-3HELIP2...$37K XFER FR P-6ASBE06 11.28.17...FY19 JAN PLAN NEW NEEDS REQ TOT: $6000 ÝFY19- $1,500 ;FY20- $1,500; FY21-$1,500, FY22-1,500)...FY19 JAN PLAN NN NOT APPROVED...2/9/18 $78K (P-1018 FY18) XFER TO P-4FMGARG...FY19 EXE PLAN NEW NEEDS REQ TOT: $6000 ÝFY19- $1,500 ;FY20- $1,500; FY21-$1,500, FY22-1,500)...FY19 ALL NN APPROVED...FY'18 $201K ( P 1018) TRF FR P-2PLG14C...FY'19 TRF $103K FR P-2GPWB23...FY'19 TRF IN $65K FR P-215KELY..TRF $108K FROM P-215KELY...2/25/19 $134K P-1018 FY19 XFER TO P-4OLMST4; $99K P-1018 FY19 XFER TO P-203D17E... | 2019 | 8036 | 798.04 | 273 | 1000 | 1000 | 1000 | 1000 | 3373 | 8444.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWBLDG | Citywide - Building Requirement Contracts | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 000 | P-1018 P-0505 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | $1.4M TO P-6WPEBCS..$250K TO P-6CADMAR..$224K P-0505 FY19 TO P-5GRNBRC..$2.35M P-0505 FY20 TO P-6ORCAST..$100K P-0505 TO P-6MSHVAC..$20K P-0505 TO P-6MSHVAC..$6K & $1.057M TO P-1ARAMEZ..$97K FY20 P-0505 FR P-1ARAMEZ.$275K FY20 P-0505 TO P-6MSHVAC .$40K TO P-6PBUT15..$38K P-1018FR P-6CWBLD3..$660K TO P-6WPEBCS..$20K TO P-6CADMAR ..$182K FY19 & $216K FY20 FR P-6PBUT15..$40K P-0505 FY19 FR P-6PBUT15.. $1.327M FR P-6BLPB14..$27K & $996K FR P-6BLEL14..$1K FY19, $103K FY20 & $421K FR P-6CWBLDG .$57K FY20 & $269K FY21 FR P-6BLDG9C.$500K FY20 FR P-6WPEBCS.. | $1M XF TO P-6ALRMXQ & $1M TO P-6ALRMBR PER IRFAN'S E-MAIL CONFIRMATION...$1K TRSNF TO P-600HHT...$4M P-1018 TRSF TO P-313CPAB... $50K (P-1018) XFER FR P-6BLDG9E PER JONNA 2.22.16...$1.147M (FY'17) TRF TO P-215BBPG..$39K (FY16) TO P-215BBPG & $11K (FY16) TO P-203SUMN...$1.5M TO P-6PRKLOT...$1.493M ADDED FY26 & $1.539M ADDED FY27...$4K TO P-6REC11B...$385K TO P-6BLDG13...$400K P-1018 TO P-6GASBXQ...$1,050 P-1018 TO P-6BLD14B...$322K P-1018 TO P-6BLGC15..$70K P-1018 TO P-6ELBR15..$188K P-1018 TO P-6PBBP15..$1K P-1018 TO P-6COMF18..FY19 JAN PLAN $168K P1018 TRSFR TO P-6PRKLOT...$34K P-1018 XFER TO P-6BLGC15...$7K P-1018 XFERTO P-6ELBR15...$33K P-1018 XFER TO P-6PBBP15...$100K P-1018 XFER TO P-6ENVTST...$17K XFER TO P-6PRKLOT...$1M FR P-6PDBLEL, $110K FR P-6BLDG9A & $359K FR P-6REC11A - TOTAL XFER IN $1.469M.. | 2019 | 19123 | 938.1 | 0 | 735 | 1117 | 1330 | 1357 | 9148 | 14625.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWCMFT | Citwide- Comfort Stations | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 000 | P-0505 |  | CITYWIDE | CITYWIDE COMFORT STATIONS | 2019 | 14529 | 0 | 0 | 0 | 0 | 0 | 2108 | 1334 | 3442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWCMVE | Citywide - Comfort Stations Standards Study | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 000 | P-1018 |  |  | CITYWIDE COMFORT STATIONS STANDARDS STUDY | 2019 | 225 | 184.21 | 0 | 0 | 0 | 41 | 0 | 0 | 225.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWFALM | NATURE CTRS AND REC CTRS-FIRE ALARMS AND LIFE SAFETY | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 000 | P-0506 |  | NATURE CTRS AND REC CTRS | NATURE CTRS AND REC CTRS. 10/26/18 $475K P-0506 FY21 TRANSFER TO P-3PDHBRC...3/8/19 $6,256K P-1018 FY22 XFER TO P-411APE2 | 2019 | 59017 | 0 | 0 | 4124 | 0 | 29620 | 4302 | 0 | 38046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWGRNT | Hazardous Sidewalk Removal and Replacement | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 000 | P-1018 |  | GREENTHUMB GARDEN:HAZARDOUS SIDEWALK REMOVAL AND REPLACEMENT | GREENTHUMB GARDEN:HAZARDOUS SIDEWALK REMOVAL AND REPLACEMENT | 2019 | 2019 | 0 | 0 | 0 | 0 | 889 | 161 | 0 | 1050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWMARI | CITYWIDE - MARINAS | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 000 | P-1018 P-1245 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | CW | RECONSTRUCTION OF MARINAS - CITYWIDE | 2019 | 5000 | 0 | 1 | 0 | 0 | 2698 | 0 | 0 | 2699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWMINI | MINI-POOLS - CITYWIDE CNYG-1601MA | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 000 | P-1008 |  | CITYWIDE | RECONSTRUCTION OF MINI-POOLS - CITYWIDE | 2019 | 789 | 369.44 | 0 | 0 | 0 | 0 | 0 | 0 | 369.44 | 277.98 | 0 | 0 | 0 | 0 | 71 | 0 | 348.98
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWNP | CPI - NEIGHBORHOOD PARKS | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 000 | WP-0169 P-1018 |  | $1187K TO P-4CPIBOW, $1279K TO P-4CPIAST)..10/16/15 $343K P1018 TR IN($133K P-1CPIP52, $40K P-2CPITBP, $54K P-4CPI5B1, $41K P-6CPIBN8, $37K P-4CPIGRS,$38K P-4CPIAST)..$315K P1018 TO ($259K P-3CPISOL, $33K P-5CPIGVP, $23K TO P-5CPIMDP)..$80K/0169) TR TO P-4CPIVAL..0169 TO ($304KP-500ARPG, $369KP-1CPIP52 $30K P-5CPIGVP, $30K P-5CPIDMT, $1305K P-5CPIDMT, $61K P-1CPISEA, $92K P-1CPIRNQ, $31K P-3CPISOL). .$179K DEP TO P-5CPILEV..$800K TO P-5CPIGVP..$223K TO P-5CPISTP..$28K TO P-1CPILCM..$582KTO P-5CPIDMT$41K (WP-0169) P-5C.$19K P-3CPIJAK..$176 P4CPIBOW | FY15 SEPT PLAN $36.3M WP0169..1/6/15 $1500K P1018 TR TO P-4CPICMA...$273K P-1018 TRSF TO P-6CPIQBR...$273K P-1018 TRSF TO P-6CPIMNX...(4/15) $336K XFER TO P-6CPIBN3, $499K XFER TO P-5CPIBN6, $536K XFER TO P-6CPIBN4,& $1.679M XFER TO P-2CPIBN7..FY16 : TRF $244K (WP0169) TO P-1CPIP52; TRF $2.065M ($620K+$540K+$318K+$587K) (WP0169) TO P-6CPIBN8; TRF $17K (WP0169) TO P-1CPIHNT; TRF $92K TO P-1CPISEA; TRF $738K TO P-1CPIRNQ...FY'16 $664K DEP TO P-2CPITBP..$622K DEP TR TO P-6CPIBN8, $780K DEP TR TO P-5CPIMDP..$324K DEP TO P-5CPILEV..$822K DEP TO P-3CPISOL..$710K DEP TO P-3CPISNN..$647 DEP TO P-3CPI103..$1127K DEP TO P-3CPIJWJ..$277K DEP TO P-309CARM..$18K DEP TO P-5CPIGVP..$624K (WP0169) TR TO P-500ARPG..10/13/15 $3591K WP0169 TRSFR ($450K P-4CPIVAL, $25K P-4CPIRCP, $634K P-4CPIGRS, $16K P-4CPICMA..PJLO | 2019 | 75750 | 0 | 545 | 95 | 391 | 0 | 0 | 0 | 1031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWPOOL | CITYWIDE - POOLS | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 000 | P-1008 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | $18K FR P-6POL11B...$49K FR P-6POOL11...FY'19 TRF $376K TO P-215HCPL...FY'19S TRF IN $283K ( P 1008)-$85K FR P-6CEPOOL & $159K FR P-6CFPOOL...$491K & $709K XFER TO P-6POOL18...$550K XFER TO P-500RINK...$3.2M XFER TO P-6PLFLTR...FY20 JAN NN REQUEST TOTAL $67,294M ( $5,690 FY20;$5,889 FY21; $6,116 FY22 $6,360; FY23; $6,609 FY24 $6,859 FY25;..FY20J NEW NEEDS NOT APPROVED..$923K TO P-6PLHNGR...$1.56M TO P-6CADMAR..$300K TO P-1HPLFLT..$327K, $818K & $1.2M TO P-6OLYMPL.. | $1.346M XFER TO ACEDPR405... FY17 JAN PLAN PROPOSAL - THE PARKS DEPARTMENT IS REQUESTING ADDITIONAL BASELINE FUNDING TO SUPPLEMENT EXISTINGFUNDING TO RECONSTRUCT ELECTRICAL, PLUMBING, AND STRUCTURAL FEATURES OF 33 OUTDOOR POOLS ($3.087M FY17, $3.093M FY18, $3.096M FY19 & $3.099M FY20)... FY17 JAN PLAN NEW NEEDS REJECTED ($3.087M FY17, $3.093M FY18, $3.096M FY19 & $3.099M FY20)...$1.38M TO P-216BRWN.. $2.139M ADDED FY26 & $2.206 IN FY27... FY18 JAN PLAN NEW NEEDS - $4,803 FY18, $3,201FY19, $3,303 FY20, $3,402 FY21, $5,835 FY22, $5,995 FY23, $6,155 FY24, $6,310 FY25, $6,465 FY26, & $6,620 FY27... FY18 JAN PLAN NEW NEEDS NOT APPROVED: FY18 $5,165 FY19 $2,935, FY20 $3,671, FY21 $3.801M, FY22$3.929M, FY23 $4.050M, FY24 $4.146M, FY25 $4.235M, FY26 $6.465M & FY27 $6.62M...XFER $661K TO ACEDPR404 1/31/17...XFER $350K TO P-1EDENPG.. | 2019 | 18199 | 651.89 | 0 | 0 | 0 | 706 | 1945 | 13109 | 16411.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWR22C | CityWide - HVAC R22 coolant retrofit | VEHICLES AND EQUIPMENT | 000 | P-1250 |  |  | FY20 JAN | 2019 | 9777 | 0 | 0 | 2911 | 7033 | 3641 | 1621 | 0 | 15206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWR23C | CityWide - HVAC R22 coolant retrofit (other facilities) | VEHICLES AND EQUIPMENT | 000 | P-1250 |  | CITYWIDE | HVAC | 2019 | 15467 | 0 | 0 | 73 | 753 | 7816 | 1135 | 0 | 9777 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWRDIO | CITYWIDE - RUPS/ Radio System & Field equipment Revamp | VEHICLES AND EQUIPMENT | 000 | P-0931 |  |  | FY20 JAN NN | 2019 | 4871 | 0 | 0 | 4871 | 0 | 0 | 0 | 0 | 4871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWROOF | CITYWIDE - ROOFING SYSTEMS RC | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 000 | P-1018 P-1249 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | ROOFING SYSTEMS CITYWIDE..$323K & $2.177K TO P-1RNQARF.. | RECONSTRUCTION OF ROOFING SYSTEMS, CITY-WIDE...$1.665M ADDED FY26 & $1.717M IN FY27...$216K TO P-6PDRFSB...$82K TO P-6RFMN14...$425K FR P-6GDRL15...$16K TO P-3ROOF9A... FY18 JAN PLAN NEW NEEDS - $5,502 FY18, $3,201 FY19, $3,303 FY20, $3,402 FY21, $2,334 FY22, $2,398 FY23, $6,155FY24, $6,310 FY25, $6,465 FY26, $6,620 FY27...$2K XFER TO P-6GASBSI... XFER $140K TO P-6RFMN14 & $435K TO P-6ROOF15...$200K XFER TO P-216BRWN... $250K TO P-303JACK...XFER $36K TO P-6RFMN14...XFER $805K TO P-6ROOF15...$330K TO P-6ROOF14...$140K TO P-6RFMN14..$1K P-1249 TO P-6ROOF18..$400K FY18 & $435K FY19 (P-1249) TO P-6RFSB14...$100K P-1249 XFER TO P-6ENVTST...$5K P-1018 & $1K P-1249 XFER FR P-6CROOF9A...$20K XFER FR P-3ROOF9A...$3.075M TO P-6ROOFQN .. $125K TO P-412DOP2..8/18/17 -$214K P-1249 FR P-6PDRFSB IN FY20...$166K XFER FR P-216BRWN IN FY20... | 2019 | 18524 | 92.88 | 5 | 19 | 574 | 1483 | 1513 | 10203 | 13889.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWRWAL | RETAINING WALLS - CITYWIDE | VEHICLES AND EQUIPMENT | 000 | P-1329 P-0245M |  | CITYWIDE | RETAINING WALLS - CITYWIDE - FY'20J PLAN NN APPROVED $4045 (FY22),$4196(FY23), $4309(FY24), $4417(FY25),$4526(FY26), $4634(FY27)... | 2019 | 5000 | 0 | 0 | 0 | 6977 | 4085 | 4196 | 27717 | 42975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWSSPE | REQUIREMENTS CONTRACTS- CITYWIDE | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 000 | P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | ...$6.996M (FY16-18) XFER TO P-1BWPLGR...$9.207M (FY16-18) XFER TO P-2BWPLGR......$7.129M ADDED FY26 & $7.35M IN FY27...$4K FR P-6PLGR9A...XFER $4K (FY18), $1.808M (FY20), $6.23M (FY21) & $6.356M (FY22) TO P-6REQU PER SPRUOT B/L P-1018 3/6/18...FY'20J PLAN TRF $6.480M (FY23), $6.694M (FY'24), $6.915M (FY'25), $7.129M (FY'26), $7.350M (FY27) TO P-6REQU... | 2019 | 158690 | 2284.22 | 0 | 0 | 0 | 0 | 0 | 15594 | 17878.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWWALK | BOARDWALKS - CITYWIDE | VEHICLES AND EQUIPMENT | 099 | P-1245 | PROJECT DELAYED PENDING APPROVAL OF NECESSARY PERMITS | CITYWIDE | ...$552K XFER TO P-107WHLN...$1.753M XFER TO P-311MGFI...$604K TRSFR TO P-3PLG15C...8/29/16 $89K P1018 TRSFR TO P-4BIGBSH...FY17 $552K (P-1018) XFER BACK FROM P-107WHLN...$952K ADDED FY26 & $981K IN FY27...$420K (P-1018, FY17) TO P-407MPSW..$797K (P-1018 - $738 FY17, $59K FY18) TO P-408CPPA...$216K (P-1018, FY18) TO P-408AUS2...$1M (P-1018, FY19) TO P-408AUS2...$13K (P-1018, FY20) TO P-408AUS2...$672K (P-1018, FY20)TO P-109PAR2...$114K (P-1018, FY20) TO P-112DRUN... | 2019 | 109368 | 215.37 | 0 | 0 | 847 | 848 | 865 | 5831 | 8606.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6DTREE7 | Trees - FY07 Spring Trees (CNYG-407M) | LAND ACQUISITION AND TREE PLANTING | 000 | P-D171 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | FY07 SPRING TREES - CITYWIDE | FY07 SPRING TREES (CNYG-407M) | 2019 | 633 | 623.04 | 0 | 0 | 0 | 69 | 0 | 0 | 692.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6EABTRA | Emerald Ash Borer (EAB) Tree Remove BX &MHT | LAND ACQUISITION AND TREE PLANTING | 000 | P-0822 |  | CITYWIDE | EMERALD ASH BORER (EAB) TREE REMOVE BX &MHT | 2019 | 345 | 0 | 0 | 345 | 0 | 0 | 0 | 0 | 345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6EABTRB | Emerald Ash Borer (EAB) Tree Remove BK &SI | LAND ACQUISITION AND TREE PLANTING | 000 | P-0822 |  | EMERALD ASH BORER (EAB) TREE REMOVE BK &SI | EMERALD ASH BORER (EAB) TREE REMOVE BK &SI | 2019 | 894 | 0 | 0 | 894 | 0 | 0 | 0 | 0 | 894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6EABTRE | Emerald Ash Borer (EAB) Remove and Replace | LAND ACQUISITION AND TREE PLANTING | 000 | P-0822 |  |  | EMERALD ASH BORER (EAB) REMOVE AND REPLACE | 2019 | 7934 | 0 | 945 | 235 | 2976 | 0 | 0 | 0 | 4156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6EABTRS | Emerald Ash Borer (EAB) Removal Supervision FY20 | LAND ACQUISITION AND TREE PLANTING | 000 | P-0822 |  | CITYWIDE | EMERALD ASH BORER (EAB) REMOVAL SUPERVISION FY20 | 2019 | 307 | 0 | 0 | 307 | 0 | 0 | 0 | 0 | 307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6ELUT15 | FY15 site utility (dig job) electric CNYG-1715M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION |  | P-0245M P-1106 |  | CITYWIDE | FY15 SITE UTILITY (DIG JOB) ELECTRIC - $1 CONTRACT | 2019 | 1336 | 0 | 167 | 0 | 1169 | 0 | 0 | 0 | 1336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6ENVTST | Citywide environment testing at DPR facilities CNYG-119M | NEIGHBORHOOD PARKS AND PLAYGROUNDS |  | P-1018 P-1249 P-1008 |  | CITYWIDE | CITYWIDE ENVIRONMENT TESTING AT DPR FACILITIES | 2019 | 0 | 0 | 320 | 0 | 0 | 0 | 0 | 0 | 320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6FLMMUL | Fire Alarm - Rec Ctr & Nature Ctr Citywide CNYG-1217M | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION |  | P-0506 |  | CITYWIDE | FIRE ALARM - REC CTR & NATURE CTR CITYWIDE | 2019 | 8451 | 584.86 | 0 | 7903 | 0 | 0 | 0 | 0 | 8487.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6FOREST | Forest Restoration-Citywide | LAND ACQUISITION AND TREE PLANTING | 099 | P-0822 |  | FOREST RESTORATION-CITYWIDE | FOREST RESTORATION-CITYWIDE | 2019 | 7787 | 65 | 0 | 1000 | 2862 | 0 | 0 | 0 | 3927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6GASBSI | CONVERSION OF OIL TO GAS BKLYN & SI CNYG-1914M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION |  | P-1250 |  | CONVERSION OF OIL TO GAS BKLYN & SI | CONVERSION OF OIL TO GAS BROOKLYN & STATEN ISLAND | 2019 | 1250 | 142.17 | 0 | 136 | 915 | 79 | 0 | 0 | 1272.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6GASBXQ | CONVERSION OF OIL TO GAS BX & QNS CNYG-1814M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION |  | P-1250 |  | CONVERSION OF OIL TO GAS BX & QNS | CONVERSION OF OIL TO GAS IN BRONX & QUEENS | 2019 | 2100 | 195.61 | 0 | 183 | 1229 | 106 | 0 | 0 | 1713.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6GASMAN | CONVERSION OF OIL TO GAS MANHATTAN MG-814M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION |  | P-1250 |  | CONVERSION OF OIL TO GAS MANHATTAN | CONVERSION OF OIL TO GAS MANHATTAN | 2019 | 1750 | 161.96 | 0 | 164 | 1101 | 95 | 0 | 0 | 1521.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6GDRL15 | FY15 Citywide guiderail & fencing CNYG-2015M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION |  | P-1018 |  | CITYWIDE | FY15 CITYWIDE GUIDERAIL & FENCING | 2019 | 901 | 204 | 0 | 0 | 0 | 0 | 0 | 0 | 204 | 82.8 | 0 | 57 | 0 | 0 | 0 | 0 | 139.8
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6GRST16 | FY16 Greenstreets - CITYWIDE | LAND ACQUISITION AND TREE PLANTING | 000 | ED-Q384 P-D822 P-0822 P-Q245 P-Q822 P-D171 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | FY 16 ADOPT SECT 254. ADD (PD822) $150K(UNION & 9TH ST) AND $35K(66THST)... | FY 16 ADOPT SECT 254. ADD (PD822) $150K(UNION & 9TH ST) AND $35K(66THST)... | 2019 | 595 | 366 | 800 | 0 | 1239 | 202 | 0 | 0 | 2607 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6LIGHT1 | Construction Of Multisite Path Lighting | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 000 | P-0087 P-D021 |  |  | CONSTRUCTION OF MULTISITE PATH LIGHTING-KISSENA CORRIDOR PARK AND CO-OP CITY BIKE PATH | 2019 | 1016 | 0 | 0 | 0 | 0 | 798 | 0 | 0 | 798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6MSHVAC | Recon HVAC at Greenbelt R/C & Queens Museum CNYG-1318M | NEIGHBORHOOD PARKS AND PLAYGROUNDS |  | P-0505 PU-0025 P-1250 |  | GREENBELT R/C & QUEENS MUSEUM | RECON HVAC AT GREENBELT R/C & QUEENS MUSEUM | 2019 | 650 | 0 | 197 | 578 | 848 | 0 | 0 | 0 | 1623 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6NCRC15 | FY15 Citywide Nature & Rec Ctr CNYG-1215MA | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION |  | P-D018 P-M245 |  | CITYWIDE | FY15 CITYWIDE NAURE & REC CTR | 2019 | 620 | 0 | 0 | 0 | 0 | 620 | 0 | 0 | 620 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6OLYMPL | Citywide Olympic Pool Mechanical Systems Recon | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION |  | P-1008 |  | CITYWIDE | CITYWIDE OLYMPIC POOL MECHANICAL SYSTEMS RECON | 2019 | 2985 | 0 | 0 | 327 | 818 | 1200 | 0 | 0 | 2345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6ORCAST | Recon Orchard Beach N/C | NEIGHBORHOOD PARKS AND PLAYGROUNDS |  | P-0505 |  | BRONX & QUEENS | RECON ORCHARD BEACH N/C & ASTORIA PARK F/H | 2019 | 2990 | 0 | 0 | 0 | 0 | 2350 | 0 | 0 | 2350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PBBP15 | FY15 Recon plumbing system in bldg & pool CW CNYG-1415M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION |  | P-M245 P-1018 |  | CITYWIDE | FY15 RECON PLUMBING SYSTEM IN BLDG & POOL CW | 2019 | 483 | 425.1 | 193 | 0 | 0 | 61 | 0 | 0 | 679.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PBUT15 | FY15 site utility (dig job) plumbing CNYG-1815M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION |  | PU-0025 |  | CITYWIDE | FY15 SITE UTILITY (DIG JOB) PLUMBING - $1 CONTRACT | 2019 | 1016 | 619.53 | 0 | 152 | 0 | 0 | 0 | 0 | 771.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PDPLEL | Recon electrical systems in pools - Citywide CNYG - 815M | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 000 | P-1018 P-1008 |  | RECON ELECTRICAL SYSTEMS IN POOL FACILITIES - CITYWIDE | RECON ELECTRICAL SYSTEMS IN POOL FACILITIES - CITYWIDE | 2019 | 1500 | 2100 | 0 | 0 | 393 | 0 | 0 | 0 | 2493 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PDPLPB | Recon of plumbing systems in pools - Citywide CNYG - 915M | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 000 | P-1018 P-1008 |  | RECON OF PLUMBING SYSTEMS IN POOL FACILITIES - CITYWIDE | RECON OF PLUMBING SYSTEMS IN POOL FACILITIES - CITYWIDE | 2019 | 1637 | 1795.9 | 0 | 286 | 0 | 14 | 0 | 0 | 2095.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PDRFMN | Recon roofs at Parks facilities in Manhattan MG-215M | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 000 | P-1018 |  | RECON ROOFS AT PARKS FACILITIES IN MANHATTAN | RECON ROOFS AT PARKS FACILITIES IN MANHATTAN | 2019 | 1750 | 2282.13 | 0 | 0 | 0 | 242 | 0 | 0 | 2524.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PDRFQX | Recon roofs at Parks facilities in BX & QNS CNYG - 315M | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 000 | P-1249 |  | RECON ROOFS AT PARKS FACILITIES IN BRONX & QUEENS | RECON ROOFS AT PARKS FACILITIES IN BRONX & QUEENS | 2019 | 1500 | 1989.81 | 15 | 0 | 0 | 31 | 0 | 0 | 2035.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PKTR18 | Park Trees-Trees Replanting Supervision FY18 | LAND ACQUISITION AND TREE PLANTING | 000 | P-0822 |  | PARK TREES-TREES REPLANTING SUPERVISION FY18 | PARK TREES-TREES REPLANTING SUPERVISION FY18 | 2019 | 606 | 81 | 570 | 0 | 0 | 0 | 0 | 0 | 651 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PKTREE | Park Trees - Maintain Stem Count | LAND ACQUISITION AND TREE PLANTING | 099 | P-0822 P-1018 |  | PARK TREES - MAINTAIN STEM COUNT | PARK TREES - MAINTAIN STEM COUNT | 2019 | 13524 | 520 | 0 | 1188 | 5461 | 3656 | 0 | 0 | 10825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PLFLTR | Recon of intermediate pool filter plants citywide | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 000 | P-1008 |  | CITYWIDE | RECON OF INTERMEDIATE POOL FILTER PLANTS CITYWIDE | 2019 | 3200 | 0 | 0 | 0 | 3200 | 0 | 0 | 0 | 3200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PLHNGR | Recon of citywide pool piping hangers & supports CNYG-419M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 000 | P-1008 |  | CITYWIDE | RECON OF CITYWIDE POOL PIPING HANGERS & SUPPORTS | 2019 | 0 | 0 | 0 | 923 | 0 | 0 | 0 | 0 | 923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PNYCST | PlaNYC 2030 Street Trees | LAND ACQUISITION AND TREE PLANTING |  | P-0822 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | $848K TO P-4PNYT31.. | (P0822) TO P-4PNYT26...FY 16 TRF $1.285M (P 0822) TO P-6PNYT22... TRF$1.321M (P0822) TO P-4PNYTP1...TRF $2,123M TO P-6PNYTP09, $427K TO P-6PNYTP2...$40K FR P-6PNYD02..$375K TO P-6PNYR35..$1,650K TO P-1PNYT21..$1,500K TO P-2PNYT29..$1,950K TO P-4PNYT27..$1,350K TO P-4PNYT28..$1,500K TO P-2PNYT28..$490K TR TO P-2PNYT27..$772K TR FR DIFF.IDS PER APRIL FY18..$672K TO P-2PNYTP2, $1,775K TO P-2PNYT30, $1,525K TO P-2PNYT31,, $1,735K TO P-4PNYT30..$644K TO P-1PNYT21 & $248K TO P-4PNYT27..$108K TO P-4PNYT27..$500K TO P-2PNYT29... FY19 EXEC PLAN $2808K P0822 TRSFR FR ($1K P-1PNYT14, $40K P-1PNYT15, $16K P-1PNYT16, $281K P-2PNYT27,$7K P-4PNYR02, $64K P-4PNYR05, $1K P-4PNYT08, , $58K P-4PNYT21, $4K P-4PNYT22, $6K P-5PNYT10, $160K P-6PNYD03, $3K P-6PNYR24, $1314K P-6PNYT09, $843K P-6PNYT16, $10K P-6PNYT18)..$2.2M TR TO P-3PNYT12.. | 2019 | 244790 | 0 | 0 | 203 | 1548 | 465 | 0 | 0 | 2216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PNYDOT | PlaNYC - Street Trees | LAND ACQUISITION AND TREE PLANTING | 000 | P-0822 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | CW | PLANYC - STREET TREES (DOT CONSTRUCTION PJCTS) | 2019 | 20131 | 0 | 0 | 79 | 7807 | 0 | 0 | 0 | 7886 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PNYG05 | PlaNYC - FY09 Spring Greenstreets (CNYG-2109M) | LAND ACQUISITION AND TREE PLANTING | 000 | P-D171 |  | CW | FY09 SPRING GREENSTREETS | 2019 | 769 | 696.08 | 0 | 0 | 0 | 73 | 0 | 0 | 769.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PNYR31 | PlaNYC - FY16 NRG Reforestation the Bronx & Queens, | LAND ACQUISITION AND TREE PLANTING | 000 | P-0822 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | CITYWIDE REFORESTATION (NRG) | PLANYC - FY16 NRG REFORESTATION THE BRONX & QUEENS, | 2019 | 1100 | 1242.57 | 237 | 0 | 0 | 0 | 0 | 0 | 1479.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PNYR34 | PlaNYC - Reforestatiob Bk,Que,& SI FY17-25 (CNYG-3816M) | LAND ACQUISITION AND TREE PLANTING | 000 | P-0822 |  | PLANYC - REFORESTATION BK,QUE,& SI FY17-25 | PLANYC - REFORESTATIOB BK,QUE,& SI FY17-25 | 2019 | 500 | 499.39 | 0 | 0 | 0 | 0 | 92 | 0 | 591.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PNYR36 | PlaNYC - FY18 Reforestation Br,Q &SI | LAND ACQUISITION AND TREE PLANTING | 000 | P-0822 SE-0200R |  | CITYWIDE | PLANYC - FY18 REFORESTATION BR,Q &SI | 2019 | 2005 | 267 | 1426 | 0 | 0 | 2 | 0 | 0 | 1695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PNYR37 | PlaNYC - FY18 Reforestation Bx & Mnt | LAND ACQUISITION AND TREE PLANTING | 000 | P-0822 |  | CITYWIDE | PLANYC - FY18 REFORESTATION BX & MNT | 2019 | 1411 | 188 | 1015 | 0 | 0 | 20 | 0 | 0 | 1223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PNYT24 | PlaNYC - FY19 Street Tree SUPERVISION CNYG-RENEWAL | LAND ACQUISITION AND TREE PLANTING | 000 | P-0822 |  | PLANYC - FY19 STREET TREE SUPERVISION CNYG-RENEWAL | PLANYC - FY19 STREET TREE SUPERVISION CNYG-RENEWAL | 2019 | 377 | 0 | 286 | 0 | 0 | 0 | 0 | 0 | 286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6POGC15 | FY15 Citywide pool structure CNYG-1515M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION |  | P-1008 |  | CITYWIDE | FY15 CITYWIDE POOL STRUCTURE | 2019 | 901 | 988.74 | 111 | 0 | 0 | 249 | 0 | 0 | 1348.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6POL11A | FY11 Recnstr of electrical system for pools CNYG-1611M | NEIGHBORHOOD PARKS AND PLAYGROUNDS |  | P-1018 |  | CITYWIDE | RECONSTRUCTION OF DETERIORATED ELECTRICAL SYSTEMS FOR VARIOUS PARKS AND RECREATION POOL FACILITIES CITYWIDE, CNYG-1611M | 2019 | 500 | 1110.81 | 0 | 0 | 0 | 184 | 0 | 0 | 1294.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6POOL18 | Recon Citywide pools $1 Contract | NEIGHBORHOOD PARKS AND PLAYGROUNDS |  | P-1008 |  | CITYWIDE | RECON CITYWIDE POOLS $1 CONTRACT | 2019 | 1529 | 0 | 0 | 492 | 709 | 0 | 0 | 0 | 1201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PRKLOT | Recon 5Boro & Garage complex prkg lot M104-117M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 000 | P-1018 |  | RECON 5BORO & GARAGE COMPLEX PRKG LOT | RECON 5BORO & GARAGE COMPLEX PRKG LOT | 2019 | 1500 | 155 | 0 | 1667 | 0 | 0 | 0 | 0 | 1822 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PVMNT1 | Reconstruct pavement various Parks CNYG-117MA | NEIGHBORHOOD PARKS AND PLAYGROUNDS |  | P-1018 |  | VARIOUS PARKS AND RECREATION LOCATIONS | DOLLAR CONTRACT WILL RECONSTRUCT PAVEMENT SURFACES AT VARIOUS PARKS AND RECREATION LOCATIONS CITYWIDE. | 2019 | 1 | 0 | 0 | 3713 | 0 | 0 | 0 | 0 | 3713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PVMNT2 | Citywide Pavement Reconstruction 2 | NEIGHBORHOOD PARKS AND PLAYGROUNDS |  | P-1018 |  | CITYWIDE | THIS DOLLAR CONTRACT WILL RECONSTRUCT PAVEMENT SURFACES AT VARIOUS PARKS AND RECREATION LOCATIONS, CITYWIDE - DOLLAR CONTRACT | 2019 | 1 | 0 | 1 | 2299 | 0 | 0 | 0 | 0 | 2300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6REC07B | FY07 Recreation & Nature Centers (Elec) - CNYG-1807M | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION |  | P-1018 |  | CW | FY07 RECREATION & NATURE CENTERS (ELEC) - CNYG-1807M | 2019 | 916 | 584.42 | 0 | 0 | 0 | 0 | 274 | 0 | 858.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6REC07D | FY07 Recreation & Nature Centers (HVAC) - CNYG-2007MA2 | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION |  | P-Q245 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | CW | FY07 RECREATION & NATURE CENTERS (HVAC) - CNYG-2007M | 2019 | 1145 | 9.11 | 0 | 0 | 0 | 0 | 200 | 0 | 209.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6REC11B | Queens, Brooklyn & SI HVAC systems CNYG-1910MA1 | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 000 | P-1018 PU-0025 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | RECREATION AND NATURE CENTERS IN QUEENS, BROOKLYN AND SI | RECONSTRUCTION OF HVAC SYSTEMS IN REC AND NATURE SENTERS IN THE QUEENS, BROOKLYN AND SI | 2019 | 250 | 906.41 | 57 | 0 | 0 | 0 | 0 | 0 | 963.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6REF20A | Reforestation FY20 Br & Que CB8-14 | LAND ACQUISITION AND TREE PLANTING | 000 | P-0822 |  | REFORESTATION FY20 BR & QUE CB8-14 | REFORESTATION FY20 BR & QUE CB8-14 | 2019 | 1065 | 0 | 0 | 0 | 1065 | 0 | 0 | 0 | 1065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6REF20B | Reforestation FY20 BX & Que CB 1-7 | LAND ACQUISITION AND TREE PLANTING | 000 | P-0822 |  | REFORESTATION FY20 BX & QUE CB 1-7 | REFORESTATION FY20 BX & QUE CB 1-7 | 2019 | 1135 | 0 | 0 | 0 | 1135 | 0 | 0 | 0 | 1135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6REF20S | Reforestation FY20 -CNSP | LAND ACQUISITION AND TREE PLANTING | 000 | P-0822 |  | REFORESTATION FY20 -CNSP | REFORESTATION FY20 -CNSP | 2019 | 540 | 0 | 0 | 540 | 0 | 0 | 0 | 0 | 540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6REMT35 | Non Sandy Tree Removal Bx, Mht, Qn | LAND ACQUISITION AND TREE PLANTING | 000 | P-0822 |  | CITYWIDE | NON SANDY TREE REMOVAL BX, MHT, QN | 2019 | 210 | 164.2 | 45 | 0 | 0 | 1 | 0 | 0 | 210.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6REMT36 | Non Sandy Tree Removal Br & SI | LAND ACQUISITION AND TREE PLANTING | 000 | P-0822 |  | CITYWIDE | NON SANDY TREE REMOVAL BR & SI | 2019 | 452 | 356.21 | 95 | 0 | 0 | 1 | 0 | 0 | 452.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6REMT37 | Tree Removal Bx, Mht, Qn FY19 | LAND ACQUISITION AND TREE PLANTING | 000 | P-0822 |  | NON SANDY TREE REMOVAL BX, MHT, QN FY19 | NON SANDY TREE REMOVAL BX, MHT, QN FY19 | 2019 | 1013 | 0 | 1013 | 0 | 0 | 0 | 0 | 0 | 1013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6REQU | State of Good Repair - CW | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 000 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | FY'18 TRF $137K TO P-214LTFN...4/5/18 $673K TO P-4HCOVPG...FY'19 TRF $557K TO P-303SDRB... XFER $2.3M TO P-6PVMNT1...FY20 JAN NN REQUEST TOTAL $218,646: ( $18,486 FY20; $19,134 FY21; $19,872 FY22; $20,664FY23; $21,474 FY24; $22,284 FY25; $23,076 FY26; $23,832 FY27;$24,552 FY28; $25,272 FY29;)...$2.3M FY20 FUND XFER FR P-6PVMNT1...FY20 JAN NN REQUEST TOTAL $218,646 NOT APPROVED...$1.412M XFER TO P-6PVMNT1...$2.299M XFER TO P-6PVMNT2...$650K FY20, $5659K FY20, $4440K FY21, $4611K FY22 P1018 TRSF TO 841 HWPL20006...$4,113K TO P-2PNYC05 | REQUIREMENTS - CITYWIDE.. FY26 $23.274 & FY27 $23,832...FY18 ARP PLAN: FY20 $14.406M; FY21- $8.883M; FY22- $9.279M...PER TB 8/21/17 $584K P1018 FY18 TRSFR TO P-407MPSW...$2089K P1018 FY18 TRSF TO P-401QSE2...$289K P1018 FY18 TRSF TO P-401QSE2... 9/1/17 TRF $164K (P 1018) TO HWPLZ001R..$453K TRF TO P-210SHRE (P 1018 FY18)...$492K P1018 FY18 TRSFR TO P-415LWP2...$325K P1018 FY18 TRSFR TO P-4CUNPLG...$319K TRF TO P-304LRSQ..$270K TO P-307STGR...3/5/2018 $130K (P-1018 FY18) XFER TO P-304CRLB...3/5/2018 $130K (P-1018 FY19) XFER FR P-6CWRC2...XFER $4K (FY18), $1.808M (FY20), $6.23M (FY21) & $6.356M (FY22) FR P-6CWSSPE PER SPRUOT B/L P-1018 3/6/18...$805K FR P-5BWPLGR..FY18 TRF $2.262 TRF FROM P-3BWPLGR PER COMMISIONER TB AND JOAN NOBLE MEETING 03/05/2018...PER LP $528K P1018 TRSF TO P-103CPB5..... | 2019 | 15000 | 0 | 298 | 1529 | 12080 | 12163 | 12248 | 72074 | 110392 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6RETW11 | FY11-Reconstr & stabilization of retaining walls CNYG-1511M | NEIGHBORHOOD PARKS AND PLAYGROUNDS |  | P-D018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | CITYWIDE | FY11 RECONSTRUCTION AND STABILIZATION OF RETAINING WALLS | 2019 | 1502 | 3673.08 | 0 | 0 | 0 | 571 | 0 | 0 | 4244.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6RETW14 | Retaining Wall R/C (CNYG-514M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 099 | P-1329 P-D018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | CITYWIDE | THE RECONSTRUCTION AND STABILIZATION OF RETAINING WALLS - CITYWIDE | 2019 | 24853 | 10715.28 | 13708 | 0 | 0 | 4020 | 0 | 0 | 28443.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6RETW18 | Citywide Retaining Wall FY18 CNYG-1818M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 099 | P-1329 |  | CITYWIDE | CITYWIDE RETAINING WALL FY18 | 2019 | 8081 | 129 | 552 | 0 | 0 | 6308 | 0 | 0 | 6989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6RETWA2 | FY10 RC of Retaining Walls (CNYG-1209M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 000 | P-D018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | CW | RECONSTRUCTION OF RETAINING WALLLS | 2019 | 2399 | 2664.15 | 0 | 0 | 0 | 0 | 227 | 0 | 2891.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6RFMN14 | FY14 RECON ROOFINGS IN MANHATTAN MG-614M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION |  | P-1249 |  | FY14 RECON ROOFINGS IN MANHATTAN | FY14 RECON ROOFINGS IN MANHATTAN | 2019 | 1980 | 1585.62 | 0 | 0 | 0 | 296 | 0 | 0 | 1881.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6RFSB14 | FY14 RECON ROOFINGS IN STATEN IS & BKLYN CNYG-1214MA | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION |  | P-1249 P-1018 |  | FY14 RECON ROOFINGS IN STATEN IS & BRKLN | FY14 RECON ROOFINGS IN STATEN IS & BRKLN | 2019 | 2590 | 1775.36 | 834 | 0 | 0 | 0 | 0 | 0 | 2609.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6ROOF14 | FY14 Roof Requirements for Bronx & Queens CNYG-1114M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION |  | P-1249 |  | CITYWIDE | FY14 ROOF REQUIREMENTS | 2019 | 2590 | 2156.41 | 0 | 0 | 0 | 39 | 0 | 0 | 2195.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6ROOF18 | Citywide recon of Roofing systems $1 contact CNYG-1018MA | NEIGHBORHOOD PARKS AND PLAYGROUNDS |  | P-1249 |  | CITYWIDE | CITYWIDE RECON OF ROOFING SYSTEMS $1 CONTACT | 2019 | 2151 | 0 | 0 | 0 | 2151 | 0 | 0 | 0 | 2151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6ROOF9A | FY09 Roof Requirements QNS & BX (CNYG-3009M) | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 000 | P-Q245 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | QNS & BX | FY09 ROOF REQUIREMENTS QNS & BX | 2019 | 2403 | 5508.65 | 0 | 0 | 0 | 330 | 0 | 0 | 5838.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6SAFTY1 | Life Safety - Rec Ctr & Nat Ctr - BK & SI | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION |  | P-0506 |  | BK & SI | LIFE SAFETY - REC CTR & NAT CTR - BK & SI | 2019 | 1150 | 0 | 0 | 1800 | 0 | 867 | 0 | 0 | 2667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6SAFTY2 | Life Safety - Rec Ctr & Nat Ctr - BX & Q | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION |  | P-0506 |  | BX & Q | LIFE SAFETY - REC CTR & NAT CTR - BX & Q | 2019 | 1150 | 0 | 0 | 1800 | 0 | 866 | 0 | 0 | 2666 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6SANDT1 | FY18 Sandy Related Tree Replacement - Q, X, M | LAND ACQUISITION AND TREE PLANTING | 000 | P-0822 |  |  | FY18 SANDY RELATED TREE REPLACEMENT - Q, X, M | 2019 | 0 | 0 | 0 | 500 | 0 | 2204 | 0 | 0 | 2704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6SECBOL | Parks Security Measures Citywide | NEIGHBORHOOD PARKS AND PLAYGROUNDS |  | P-1095 |  | CITYWIDE | PARKS SECURITY BOLLARDS CITYWIDE | 2019 | 33740 | 0 | 0 | 2630 | 0 | 30085 | 0 | 0 | 32715 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6SPCR15 | NRG - Spring Creek Salt Marsh Restoration CNYG-2715M | LAND ACQUISITION AND TREE PLANTING | 000 | P-1327 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | BORDERS THE BOROUGHS OF BROOKLYN AND QUEENS. | SPRING CREEK SALT MARSH AND COASTAL UPLAND RESTORATION | 2019 | 2000 | 434.95 | 0 | 8673 | 0 | 0 | 0 | 0 | 9107.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6SRAPRS | Recon Sara D BRC Senior Center & Prospect PEP Off | NEIGHBORHOOD PARKS AND PLAYGROUNDS |  | P-1018 |  | SARA D BRC SENIOR CENTER & PROSPECT PEP OFF | RECON SARA D BRC SENIOR CENTER & PROSPECT PEP OFF | 2019 | 1782 | 0 | 0 | 0 | 1400 | 0 | 0 | 0 | 1400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6STIMUB | SIDEWALKS DAMAGED BY TREES-CITYWIDE CNYG-2509M | LAND ACQUISITION AND TREE PLANTING | 000 | P-1331 P-1018 |  | CITYWIDE | RECONSTRUCTION OF SIDEWALKS DAMAGED BY TREES - CITYWIDE | 2019 | 1037 | 1102.65 | 0 | 5000 | 0 | 9 | 0 | 0 | 6111.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6STRUC1 | Citywide structural stabilization - Multisite CNYG-1617M | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION |  | P-0505 P-D018 |  | CITYWIDE | CITYWIDE STRUCTURAL STABILIZATION - MULTISITE - FOR METROPOLITAN POOL& E54TH ST REC CTR... | 2019 | 1267 | 122 | 0 | 0 | 0 | 1165 | 0 | 0 | 1287 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6STURF1 | Reconstruction of Synthetic Turf Fields Citywide MG-718M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 000 | P-0510 |  | CITYWIDE | RECONSTRUCTION OF SYNTHETIC TURF FIELDS CITYWIDE | 2019 | 4771 | 0 | 2196 | 1841 | 0 | 0 | 0 | 0 | 4037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6STURF2 | Citywide Synthetic Turf Field Reconstruction | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 000 | P-0510 |  | CITYWIDE | CITYWIDE SYNTHETIC TURF FIELD RECONSTRUCTION | 2019 | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 0 | 1260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRAI20 | BX,QUE,SI Trail R/C, & Planting Trees | LAND ACQUISITION AND TREE PLANTING | 000 | P-R245 P-0822 P-D019 P-D021 |  | BX,QUE,SI TRAIL R/C, & PLANTING TREES | BX,QUE,SI TRAIL R/C, & PLANTING TREES | 2019 | 522 | 0 | 300 | 28 | 222 | 0 | 0 | 0 | 550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRBRSI | Park Trees-Trees Replanting Brooklyn & SI | LAND ACQUISITION AND TREE PLANTING | 000 | P-0822 |  | PARK TREES-TREES REPLANTING BROOKLYN & SI | PARK TREES-TREES REPLANTING BROOKLYN & SI | 2019 | 2964 | 364 | 0 | 0 | 0 | 2210 | 0 | 0 | 2574 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRBXMQ | Park Trees-Trees Replanting Bronx, Mnhtn, Queens | LAND ACQUISITION AND TREE PLANTING | 000 | P-0822 |  | PARK TREES-TREES REPLANTING BRONX, MNHTN, QUEENS | PARK TREES-TREES REPLANTING BRONX, MNHTN, QUEENS | 2019 | 2964 | 364 | 0 | 2990 | 0 | 0 | 0 | 0 | 3354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRE17A | FY17 Street Tree Supervision | LAND ACQUISITION AND TREE PLANTING | 099 | P-0822 |  | CITYWIDE | FY17 STREET TREE SUPERVISION | 2019 | 1041 | 756.62 | 761 | 0 | 0 | 0 | 0 | 0 | 1517.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRE18A | Street Trees Supervision FY18 | LAND ACQUISITION AND TREE PLANTING | 000 | P-0822 |  | STREET TREES SUPERVISION FY18 | STREET TREES SUPERVISION FY18 | 2019 | 3813 | 508 | 0 | 2400 | 0 | 0 | 0 | 0 | 2908 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRE19A | Street Trees Supervision FY19 | LAND ACQUISITION AND TREE PLANTING | 000 | P-0822 |  | STREET TREES SUPERVISION FY19 | STREET TREES SUPERVISION FY19 | 2019 | 1142 | 0 | 0 | 958 | 0 | 0 | 0 | 0 | 958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRE20A | FY20 Street Trees Supervision | LAND ACQUISITION AND TREE PLANTING | 000 | P-K822 P-0822 |  | FY20 STREET TREES SUPERVISION | FY20 STREET TREES SUPERVISION | 2019 | 5033 | 0 | 0 | 5033 | 0 | 0 | 0 | 0 | 5033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TREEP1 | Procurement of Street Trees Region 1-CNYG-3916M | LAND ACQUISITION AND TREE PLANTING |  | P-0822 |  | CITYWIDE | PROCUREMENT OF STREET TREES REGION 1-CNYG-3916M | 2019 | 13800 | 5150 | 5000 | 5148 | 0 | 0 | 0 | 0 | 15298 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TREEP2 | Procurement of Street Trees Region 2-CNYG-4016M | LAND ACQUISITION AND TREE PLANTING |  | P-0822 |  | CITYWIDE | PROCUREMENT OF STREET TREES REGION 2-CNYG-4016M | 2019 | 13800 | 5150 | 5000 | 2676 | 0 | 0 | 0 | 0 | 12826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TREES2 | RISK MANAGEMENT TREES | LAND ACQUISITION AND TREE PLANTING | 000 | P-0822 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | CITYWIDE | RISK MANAGEMENT TREES | 2019 | 2000 | 0 | 0 | 0 | 214 | 0 | 0 | 0 | 214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TREESA | TREES - CITYWIDE | LAND ACQUISITION AND TREE PLANTING | 099 | P-0822 |  | TREES - CITYWIDE | $1,008K TO P-3TRE20B;$848K TO P-3TRE20A;$551K TOP-2TRE20F; $2,546K TOP-2TRE20D; $2,651K TO P-2TRE20B; $2,373K TO P-2TRE20A;.$1,513K TOP-1TRE20A..$2,682K TO P-1TRE20B..$2,360K TO P-1TRE20C..FY20 JAN PLAN NEW NEEDS -FY22 $15,499K, FY23 $16,117K, FY24 $16,749K, FY25 $17,380K, FY26$17,998K, FY27 $18,588K, FY28 $19,149K AND FY29 $19,711K...FY20 JAN PLAN NEW NEEDS NOT APPROVED -FY22 $15,499K, FY23 $16,117K, FY24 $16,749K, FY25 $17,380K, FY26 $17,998K, FY27 $18,588K, FY28 $19,149K AND FY29$19,711K. | 2019 | 54505 | 0 | 400 | 1000 | 9194 | 9291 | 8000 | 0 | 27885 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TREESB | TREES - CITYWIDE | LAND ACQUISITION AND TREE PLANTING | 099 | P-0822 SE-0200Q WM-0006 F-0175 S-0216 P-D822 P-1018 WP-0169 HB-0215 HB-1193 |  | $1,595K TO P-4TRE20B..$1,800K TO P-3TRE20B..$1,188K TO P-2TRE20E..$769K TO P-2TRE20C $296K TO P-5TRE20A..$10K/S0136 & $87K/S0213 TO P-3TRE20A..$231K/SE0004 TO P-2TRE20C.. $33KTO P-4TRE20C; $2,131K TO P-3TRE20A..D822 $547K TO P-4TRE20A, $804K TO P-3TRE20B, $500K TO P-2TRE20A, $804K TO P-2TRE20D...$100K/K822 TO P-2TRE20D..$596K TO P-6TRE20A.. $336KFR P-2TRE20D..$10K FR P-3TRE20B..$296K FR P-5TRE20A...$47K TO P-6PNYT19..PV $31K FR P-2TRE14A; $18K FR P-4TRE14A; $1K FR P-4TREE08; $13K FRP-1TRE14A..$2K/F175 F P-2TRE14A..2-19-19 $24K P-1018 FY21 FR P-1CPIGAR | $45K FY19 TR FR GXBXGI-01..$MTA CHECK RESTITUTION CANARSIE TUBE MNHT $556K..$4K ED0409)TR FR 801CWFSBARGE..$180K P0822 XFER FROM SCA BUDGET, NET ZERO CITYWIDE...$26K FR P-501FABL..$210K & $4K FR 850 SEQNS001..FY19 ADOPT TOTAL $1,882K (P-D822: $210K, $500K,$75K,$45K,$344K,$415K,$75K,$148K,$70K)..$62K FR 801 STHBRXGAN...FY'19 TRF IN $938K ( $128K FROM P-4PNYT20 & $810 FROM P-6TREE02...$700K TO P-5TRE18A. ..FY'19S-DOT ROLLS $296K (HW0001R FR FY'18 TO FY20...$32K FR DDC BED-777..$102K FR P-5CPIMH..$1.3M FR P-2TRE19A..$1.2M CHECK FR MUSEUM NH...PER BN 10/5/18 $40K P0822 TRSFR TO P-2CONYGS...$1,187K FR 850 QED-976..$42K FR DDC..$44K FR DDC..$586K TO P-5TRE20A..$135K SE002R TO P-5TRE20A..$93K WP0169 TO P-4TRE20B..D822 $106K TO P-1TRE20A;$75K TO P-3TRE20A; $70K TO P-2TRE20C...$743K/ED075 &4K/ED049 TO P-1TRE20A..$55K/WP0169 TO P-1TRE20C. | 2019 | 74316 | 0 | 2192 | 3449 | 5071 | 6920 | 6000 | 58179 | 81811 | 0 | 500 | 894 | 0 | 0 | 0 | 0 | 1394
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TREM18 | FY18-Citywide NRG Reforestation | LAND ACQUISITION AND TREE PLANTING |  | P-0822 |  | CITYWIDE | FY18-CITYWIDE NRG REFORESTATION | 2019 | 0 | 0 | 941 | 0 | 0 | 102 | 0 | 0 | 1043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRREMD | TREE REMEDIATION- Sandy Damaged Trees | LAND ACQUISITION AND TREE PLANTING |  | P-0822 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | CITYWIDE | TREE REMEDIATION | 2019 | 9580 | 0 | 985 | 642 | 0 | 1821 | 0 | 0 | 3448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRS19A | Citywide- R/C Sidewalks Damaged by Trees Supervision | LAND ACQUISITION AND TREE PLANTING | 000 | P-1331 |  | CITYWIDE- R/C SIDEWALKS DAMAGED BY TREES SUPERVISION | CITYWIDE- R/C SIDEWALKS DAMAGED BY TREES SUPERVISION | 2019 | 1691 | 0 | 1409 | 0 | 0 | 0 | 0 | 0 | 1409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRSD19 | Bronx & Mnht- R/C Sidewalks Damaged by Trees | LAND ACQUISITION AND TREE PLANTING | 000 | P-1331 |  | BRONX & MNHT- | BRONX & MNHT- R/C SIDEWALKS DAMAGED BY TREES | 2019 | 1259 | 0 | 1065 | 0 | 0 | 0 | 0 | 0 | 1065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6ZOOIN1 | Zoo Improvements - Citywide | ZOOS | 000 | P-0887 |  | CITYWIDE | RECONSTRUCTION OF ZOOS - CITYWIDE..$3K FR P-300ZOO4..$1,136K TOP-200ZO17,, $470K TO P-200ZO18,.$2,763K TO P-200ZO19.. $60K TR FR P-300ZO20.. | 2019 | 3913 | 0 | 60 | 1032 | 1650 | 4500 | 6000 | 6950 | 20192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6ZOOINF | Citywide Zoos- Infrastructure /Requirements Work | ZOOS | 000 | P-0887 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | INFRASTRUCTURE / REQUIREMENTS WORK FOR CITY ZOOS | 2019 | 5537 | 50 | 240 | 1320 | 800 | 500 | 390 | 2541 | 5841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | SANDY4330 | NYC4330 Surplus | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 000 | P-1018 |  |  | SANDY - NYC4330 SURPLUS | 2019 | 10416 | 0 | 0 | 0 | 0 | 0 | 1042 | 0 | 1042 | 0 | 0 | 0 | 0 | 0 | 9374 | 0 | 9374
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | SANDY4371 | NYC4371 Surplus | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 000 | P-1018 |  |  | SANDY - PW4371 SURPLUS | 2019 | 5088 | 0 | 0 | 0 | 0 | 0 | 0 | 509 | 509 | 0 | 0 | 0 | 0 | 0 | 0 | 4579 | 4579
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | SANDY6-06 | SANDY - S.I. Beaches Protective Measures North RG-813M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 000 | P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | SANDY -EMERGENCY BOILER WORK | 2019 | 6003 | 448.86 | 0 | 0 | 0 | 0 | 50 | 0 | 498.86 | 4061.18 | 0 | 0 | 0 | 0 | 438 | 0 | 4499.18
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | SANDY6-16 | For Flushing Meadow Conduit | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 000 | P-1018 |  |  | SANDY CITYWIDE CONDUIT REPLACEMENT | 2019 | 50894 | 0 | 0 | 0 | 0 | 0 | 0 | 5089 | 5089 | 0 | 0 | 0 | 0 | 0 | 0 | 45805 | 45805
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | SANDY6-17 | Sandy-Trees Removal in Bk & SI CNYG-3616M | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 000 | P-1018 |  | BROOKLYN & STATEN ISLAND | SANDY-TREES REMOVAL IN BK & SI | 2019 | 1100 | 103.9 | 0 | 0 | 0 | 6 | 0 | 0 | 109.9 | 935.1 | 55 | 0 | 0 | 0 | 0 | 0 | 990.1
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | SANDY6-18 | Sandy-Trees Removal in BX ,Mnht & Que CNYG-3516M | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 000 | P-1018 |  | BRONX, MANHATTAN , QUEENS | SANDY-TREES REMOVAL IN BX ,MNHT & QUE | 2019 | 550 | 51 | 0 | 0 | 0 | 4 | 0 | 0 | 55 | 459 | 36 | 0 | 0 | 0 | 0 | 0 | 495
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | SANDY6-21 | Sandy Tree Planting and Replanting - BX, Q, & M | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 000 | P-1018 |  |  | SANDY TREE PLANTING AND REPLANTING - BX, Q, & M | 2019 | 2200 | 400 | 4 | 0 | 0 | 0 | 0 | 0 | 404 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 32
20190425 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | SANDYCDUT | SANDY-NYC4371 Conduit Funding | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 000 | P-1018 |  | CITYWIDE | SANDY PWNYC4371 CONDUIT FUNDING | 2019 | 17391 | 0 | 0 | 0 | 0 | 0 | 0 | 1739 | 1739 | 0 | 0 | 0 | 0 | 0 | 0 | 15652 | 15652
20190425 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-827 | Regulator Chamber Roof Replacements | TRUNK AND DISTRIBUTION MAIN REPLACEMENT |  | WM-0001 |  |  | REGULATOR CHAMBER ROOF REPLACEMENTS: BROOKLYN (5), BRONX (1). REMOVAL AND REPLACEMENT OF EXISTING DEHABILITATED CONCRETE SLAB ROOFS WITH SUPPORTING STRUCTURAL STEEL SUPPORTS. | 2019 | 563 | 0 | 0 | 450 | 0 | 68 | 0 | 0 | 518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | CT2-INTER | CITY TUNNEL #2, REPLACE GUARD VALVES @ 16A | WATER QUALITY PRESERVATION | 000 | WM-0105 TF-0002 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | CITY TUNNEL #2, REPLACE GUARD VALVES @ 16A 17A, ETC | 2019 | 10012 | 533.78 | 10114 | 0 | 0 | 0 | 0 | 0 | 10647.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | F175EMS17 | EMS Station 17 - New Facility | NEW FACILITIES AND RENOVATIONS | 000 | F-0175 |  |  | EMS STATION 17 - NEW FACILITY | 2019 | 17001 | 0 | 1686 | 1215 | 0 | 14100 | 0 | 0 | 17001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | GE-348 | EMERGENCY RECONSTRUCTION OF WATER MAINS | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 000 | WM-0001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | EMERGENCY RECONSTRUCTION OF WATER MAINS | 2019 | 11950 | 12453.5 | 202 | 0 | 0 | 0 | 0 | 0 | 12655.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | GE-353 | DIST. WM EXT/REPL; NEW BLDGS, ETC ADJ. TO T.A. FACILITIES | TRUNK AND DISTRIBUTION MAIN REPLACEMENT |  | WM-0001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | DISTRIBUTION WATER MAIN EXTENSIONS/REPLACEMENTS; NEW BLDGS, HYDRANT &VALVE REPLACMENT, ADJACENT TO T.A. FACILITIES | 2019 | 4400 | 7943.47 | 292 | 0 | 0 | 0 | 0 | 0 | 8235.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | GE-359 | Area-wide Contract for Water Mains | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 000 | WM-0001 WM-0006 EP-0007 HW-0200 |  |  | AREA-WIDE CONTRACT FOR WATER MAINS | 2019 | 12600 | 50 | 17562 | 0 | 0 | 0 | 0 | 0 | 17612 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | GE-361 | Emergency reconstruction of Water Mains | TRUNK AND DISTRIBUTION MAIN REPLACEMENT |  | WM-0001 WM-0006 |  |  | EMERGENCY RECONSTRUCTION OF WATER MAINS, CITYWIDE | 2019 | 13800 | 0 | 0 | 0 | 12000 | 0 | 0 | 0 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HBPED100Q | PED BRIDGE - 51 AVE (Q) | FAIR BRIDGES | 000 | HB-1012 HB-0215 P-0245M | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | PED BRIDGE - 51 ST (Q) | PED BRIDGE - 51 ST (Q) | 2019 | 11330 | 5845.82 | 898 | 19101 | 0 | 161 | 0 | 0 | 26005.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HR25FACA | FACADE RESTORATION MULTIPLE SITES | SOCIAL SERVICES BUILDINGS | 000 | HR-0025 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | OBA ADVISED THAT ONLY ONE ADDRESS COULD BE LISTED AS THIS PROJECT ISCONSIDERED TO BE CONFIDENTIAL. | FACADE RESTORATION: ROOFS, PARAPETS, EXTERIOR MASONRY, WINDOWS, DOORS, AND RELATED APPURTANCES (EXTERIOR LIGHTING, WINDOW GUARDS, ETC.,) | 2019 | 3260 | 19638.87 | 700 | 1303 | 0 | 0 | 0 | 0 | 21641.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HR25FACA4 | FACADE RESTORATION MULTIPLE SITES | SOCIAL SERVICES BUILDINGS | 000 | HR-0025 |  | (1.) 1275 WESTCHESTER AVE., BX. OBA ADVISED THAT ONLY ONE ADDRESS COULD BE LISTED AS THIS PROJECT IS CONSIDERED TO BE CONFIDENTIAL. | FACADE RESTORATION: ROOFS, PARAPETS, EXTERIOR MASONRY, WINDOWS, DOORS, AND RELATED APPURTANCES (EXTERIOR LIGHTING, WINDOW GUARDS, ETC.,) | 2019 | 4322 | 0 | 613 | 2323 | 715 | 715 | 0 | 0 | 4366 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HW2CR16E | Citywide Milling - Brooklyn, Queens & Staten Island | PRIMARY STREET RESURFACING | 000 | HW-0002Q HW-0002R HW-0002K | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | CITYWIDE MILLING - BROOKLYN, QUEENS & STATEN ISLAND | CITYWIDE MILLING - BROOKLYN, QUEENS & STATEN ISLAND | 2019 | 16109 | 13739.88 | 217 | 0 | 0 | 30 | 0 | 0 | 13986.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HW349FED | Citywide Resurfacing | PRIMARY STREET RESURFACING | 000 | HW-0002K HW-0002Q | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | CITYWIDE RESURFACING | CITYWIDE RESURFACING | 2019 | 20504 | 4913.21 | 0 | 0 | 0 | 0 | 0 | 0 | 4913.21 | 11025.73 | 0 | 0 | 0 | 2399 | 0 | 0 | 13424.73
20190425 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HW349FED2 | Federal NHS Contract Resurfacing | PRIMARY STREET RESURFACING | 000 | HW-0002Q | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | CITYWIDE RESURFACING | CITYWIDE RESURFACING | 2019 | 15321 | 1754.83 | 595 | 0 | 0 | 0 | 0 | 0 | 2349.83 | 10376.97 | 0 | 0 | 0 | 0 | 0 | 0 | 10376.97
20190425 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWBUSPAD6 | Citywide Bus Pad Contract (SIM) | PRIMARY STREET RECONSTRUCTION | 000 | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | CITYWIDE BUS PAD CONTRACT (SIM) | CITYWIDE BUS PAD CONTRACT (SIM) | 2019 | 3222 | 2830.32 | 170 | 0 | 0 | 0 | 0 | 0 | 3000.32 | 2104.9 | 0 | 0 | 0 | 0 | 0 | 0 | 2104.9
20190425 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCPEDLOC | Perimeter Security Measures | PRIMARY STREET RECONSTRUCTION | 000 | HW-0001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | CITYWIDE PEDESTRIAN REFUGE LOCATIONS | CITYWIDE PEDESTRIAN REFUGE LOCATIONS | 2019 | 26970 | 1491.85 | 14052 | 0 | 11426 | 0 | 0 | 0 | 26969.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3B2 | SAFE ROUTES TO SCHOOLS - PHASE 3B2 | PRIMARY STREET RECONSTRUCTION | 000 | HW-0988 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 2019 | 6789 | 3912.88 | 0 | 0 | 0 | 0 | 17 | 0 | 3929.88 | 6776.04 | 0 | 0 | 0 | 0 | 396 | 0 | 7172.04
20190425 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3C | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | PRIMARY STREET RECONSTRUCTION | 099 | HW-D105 HW-0988 WM-0001 SE-0002Q | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CONSTRUCTION | 2019 | 7066 | 4.02 | 0 | 0 | 0 | 27646 | 0 | 0 | 27650.02 | 0 | 0 | 0 | 0 | 217 | 0 | 0 | 217
20190425 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3E | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | PRIMARY STREET RECONSTRUCTION | 000 | HW-0988 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 2019 | 9123 | 2100.37 | 0 | 0 | 0 | 0 | 0 | 0 | 2100.37 | 9614.17 | 915 | 0 | 0 | 0 | 1074 | 0 | 11603.17
20190425 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3E1 | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | PRIMARY STREET RECONSTRUCTION | 000 | HW-0988 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 2019 | 6421 | 1015.42 | 0 | 0 | 0 | 0 | 0 | 0 | 1015.42 | 5155.25 | 0 | 0 | 0 | 0 | 944 | 0 | 6099.25
20190425 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3F1 | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | PRIMARY STREET RECONSTRUCTION | 000 | HW-0988 TF-0002 HW-0944 HW-0200 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 2019 | 10137 | 6183.16 | 1684 | 0 | 0 | 34 | 55 | 0 | 7956.16 | 4473 | 8 | 0 | 0 | 0 | 0 | 0 | 4481
20190425 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3G1 | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | PRIMARY STREET RECONSTRUCTION | 000 | HW-0988 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 2019 | 5890 | 810.89 | 0 | 0 | 0 | 0 | 0 | 0 | 810.89 | 3564.05 | 0 | 0 | 0 | 0 | 1293 | 0 | 4857.05
20190425 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3G2 | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | PRIMARY STREET RECONSTRUCTION | 000 | HW-0988 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 2019 | 7026 | 1534.2 | 0 | 0 | 0 | 0 | 0 | 0 | 1534.2 | 5681.74 | 0 | 0 | 0 | 0 | 663 | 0 | 6344.74
20190425 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3H1 | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | PRIMARY STREET RECONSTRUCTION | 000 | HW-0988 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 2019 | 1718 | 0 | 0 | 0 | 0 | 0 | 228 | 0 | 228 | 0 | 0 | 0 | 0 | 0 | 998 | 0 | 998
20190425 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3H2 | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | PRIMARY STREET RECONSTRUCTION | 000 | HW-0988 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 2019 | 2909 | 914.78 | 0 | 0 | 0 | 0 | 0 | 0 | 914.78 | 932.63 | 0 | 0 | 0 | 0 | 1639 | 0 | 2571.63
20190425 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3MM | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | PRIMARY STREET RECONSTRUCTION | 000 | HW-0988 TF-0002 TF-0502 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 2019 | 9280 | 3425.9 | 277 | 544 | 0 | 0 | 249 | 0 | 4495.9 | 2984.68 | 0 | 0 | 0 | 0 | 3424 | 0 | 6408.68
20190425 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4A | Safe Route to Schools - Phase 4A (MED-635) | PRIMARY STREET RECONSTRUCTION | 000 | HW-0988 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | SAFE ROUTES TO SCHOOLS PHASE 4 - 31 SCHOOLS | SAFE ROUTES TO SCHOOLS PHASE 4 - 31 SCHOOLS | 2019 | 5344 | 1820.49 | 542 | 0 | 0 | 0 | 0 | 0 | 2362.49 | 4635.88 | 815 | 0 | 0 | 0 | 0 | 0 | 5450.88
20190425 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4B1 | Safe Routes to Schools - Phase 4B1 | PRIMARY STREET RECONSTRUCTION | 000 | HW-0988 HW-0944 WM-0001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | SAFE ROUTES TO SCHOOLS - PHASE 4B1 | SAFE ROUTES TO SCHOOLS - PHASE 4B1 | 2019 | 5542 | 4290.9 | 557 | 0 | 0 | 0 | 0 | 0 | 4847.9 | 4401.58 | 10 | 0 | 0 | 0 | 0 | 0 | 4411.58
20190425 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4C2 | Safe Routes to Schools - Phase 4C2 | PRIMARY STREET RECONSTRUCTION | 000 | HW-0988 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | SRTS - PHASE 4C2 | SRTS - PHASE 4C2 | 2019 | 17600 | 7060.98 | 270 | 0 | 0 | 0 | 0 | 0 | 7330.98 | 8799.19 | 0 | 0 | 0 | 0 | 0 | 0 | 8799.19
20190425 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPKR | Safe Routes to Schools - Brooklyn & Staten Island | PRIMARY STREET RECONSTRUCTION | 000 | HW-0001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | SAFE ROUTES TO SCHOOLS - BROOKLYN & STATEN ISLAND | SAFE ROUTES TO SCHOOLS - BROOKLYN & STATEN ISLAND | 2019 | 14060 | 1212.99 | 0 | 0 | 12183 | 0 | 0 | 0 | 13395.99 | 0 | 0 | 0 | 600 | 0 | 0 | 0 | 600
20190425 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPMN | SAFE ROUTES TO SCHOOLS- MANHATTAN | PRIMARY STREET RECONSTRUCTION | 099 | HW-D102 HW-0988 |  | SAFE ROUTES TO SCHOOLS- MANHATTAN | SAFE ROUTES TO SCHOOLS- MANHATTAN | 2019 | 18702 | 1022.71 | 0 | 0 | 12417 | 905 | 0 | 0 | 14344.71 | 0 | 0 | 0 | 4357 | 0 | 0 | 0 | 4357
20190425 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCURB09 | Curb Reconstruction | SIDEWALK RECONSTRUCTION | 000 | HW-0200 HW-D101 |  | CURB RECONSTRUCTION | CURB RECONSTRUCTION | 2019 | 4360 | 135 | 425 | 0 | 0 | 0 | 0 | 0 | 560 | 0 | 2345 | 0 | 0 | 0 | 0 | 0 | 2345
20190425 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP15XMCL | Simple, Complex & Landmark Ped Ramps - Bronx and Manhattan | PEDESTRIAN RAMP CONSTRUCTION | 000 | HW-0200 TF-0502 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | SIMPLE, COMPLEX & LANDMARK PED RAMPS - BRONX AND MANHATTAN | SIMPLE, COMPLEX & LANDMARK PED RAMPS - BRONX AND MANHATTAN | 2019 | 5081 | 7268.74 | 52 | 0 | 0 | 0 | 0 | 0 | 7320.74 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 35
20190425 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP15XMTA | Complex Ped Ramps - Transit Authority - Manhattan | PEDESTRIAN RAMP CONSTRUCTION | 000 | TF-0002 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | COMPLEX PED RAMPS - TRANSIT AUTHORITY - BRONX AND MANHATTAN | COMPLEX PED RAMPS - TRANSIT AUTHORITY - BRONX AND MANHATTAN | 2019 | 4524 | 9778.2 | 192 | 0 | 0 | 0 | 0 | 0 | 9970.2 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 20
20190425 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19CWLM | CITYWIDE COMPLEX PED RAMPS (LANDMARK) - MANHATTAN AND BRONX | PEDESTRIAN RAMP CONSTRUCTION | 000 | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CITYWIDE COMPLEX PED RAMPS (LANDMARK)- MANHATTAN AND BRONX | 2019 | 7290 | 0 | 583 | 0 | 6738 | 0 | 0 | 0 | 7321 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19KQTA | CITYWIDE COMPLEX PED RAMPS (TA) - BROOKLYN AND QUEENS | PEDESTRIAN RAMP CONSTRUCTION | 000 | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CITYWIDE COMPLEX PED RAMPS (TRANSIT AUTHORITY)- BROOKLYN AND QUEENS | 2019 | 5588 | 0 | 535 | 0 | 5165 | 0 | 0 | 0 | 5700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19QRC | Citywide Complex Pedestrian Ramps - Queens and Staten Island | PEDESTRIAN RAMP CONSTRUCTION | 000 | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CITYWIDE COMPLEX PEDESTRIAN RAMPS- QUEENS AND STATEN ISLAND | 2019 | 6687 | 0 | 638 | 0 | 6180 | 0 | 0 | 0 | 6818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2019S | Citywide Simple Pedestrian Ramps | PEDESTRIAN RAMP CONSTRUCTION | 000 | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CITYWIDE SIMPLE PEDESTRIAN RAMPS | 2019 | 6466 | 0 | 6623 | 0 | 0 | 0 | 0 | 0 | 6623 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF1 | Multi-Site Pedestrian Safety | PRIMARY STREET RECONSTRUCTION | 000 | HW-0200 HW-0001M HW-0001Q HW-D103 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | MULTI-SITE PEDESTRIAT SAFETY - NF & EARMARKS | PED SAFETY | 2019 | 3971 | 3134.73 | 1332 | 0 | 0 | 494 | 0 | 0 | 4960.73 | 1082 | 0 | 0 | 0 | 0 | 0 | 0 | 1082
20190425 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF3A | MULTI-SITE PEDESTRIAN SAFETY - 7 LOCATIONS | PRIMARY STREET RECONSTRUCTION | 000 | HW-0988 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | MULTI-SITE PEDESTRIAN SAFETY - 5 LOCATIONS | MULTI-SITE PEDESTRIAN SAFETY - 5 LOCATIONS | 2019 | 5583 | 8681.9 | 50 | 0 | 0 | 0 | 0 | 0 | 8731.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS17CW2 | Prior Notice Sidewalks - Citywide | SIDEWALK RECONSTRUCTION | 000 | HW-0200 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | PRIOR NOTICE SIDEWALKS - CITYWIDE | PRIOR NOTICE SIDEWALKS - CITYWIDE | 2019 | 3000 | 50 | 0 | 0 | 0 | 1082 | 0 | 0 | 1132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2016XM | Prior Notice Sidewalks - Bronx & Manhattan | SIDEWALK RECONSTRUCTION | 000 | HW-0200 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | PRIOR NOTICE SIDEWALKS - BRONX & MANHATTAN | PRIOR NOTICE SIDEWALKS - BRONX & MANHATTAN | 2019 | 3892 | 12319.62 | 4971 | 0 | 0 | 0 | 0 | 0 | 17290.62 | 1019.12 | 0 | 0 | 0 | 0 | 0 | 0 | 1019.12
20190425 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWSRT200C | SAFE ROUTES TO TRANSIT FTA-NF | PRIMARY STREET RECONSTRUCTION | 000 | HW-0988 WM-0001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | SAFE ROUTES TO TRANSIT VARIOUS | SAFE ROUTES TO TRANSIT | 2019 | 10130 | 9575.46 | 75 | 0 | 0 | 49 | 0 | 0 | 9699.46 | 4614.04 | 0 | 0 | 0 | 0 | 0 | 0 | 4614.04
20190425 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRQX1 | Trench Restoration - Queens and Bronx | PRIMARY STREET RECONSTRUCTION |  | HW-0001 |  |  | TRENCH RESTORARTION - QUEENS AND BRONX | 2019 | 14700 | 1278.45 | 0 | 0 | 13066 | 0 | 0 | 0 | 14344.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | JJ1FACREN | FACILITIES RENOVATIONS | CHILD WELFARE FACILITIES | 000 | CS-0005 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | FACILITY RENOVATION | VARIOUS FACILITY RENOVATION | 2019 | 13514 | 55923.36 | 30082 | 0 | 0 | 0 | 0 | 0 | 86005.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA16WH1 | Washington Heights - Third Floor Renovation | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | LN-D008 LN-0008 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | THIRD FLOOR RENOVATION | 2019 | 2701 | 0 | 0 | 0 | 2641 | 0 | 0 | 0 | 2641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PO141-40P | NEW 40TH PRECINCT | POLICE FACILITIES |  | PO-0141 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | EAST 149TH STREET AND SAINT ANNS AVENUE, BRONX | NEW 40TH PCT | 2019 | 68914 | 69701.56 | 0 | 6749 | 0 | 0 | 0 | 0 | 76450.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PO205-PA | CONSTRUCTION OF A NEW POLICE ACADEMY/TRAINING FACILITY | POLICE FACILITIES | 000 | PO-0205 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CONSTRUCTION OF A NEW POLICE ACADEMY AND TRAINING FACILITY, CITYWIDE | 2019 | 1130200 | 876167.45 | 38 | 7342 | 0 | 0 | 0 | 0 | 883547.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79FDCW1 | Front Desk Renovations for 45th, 75th, 105th, 123rd PCTS | POLICE FACILITIES | 000 | PO-0079 |  |  | FRONT DESK RENOVATIONS CITY WIDE | 2019 | 940 | 0 | 179 | 792 | 0 | 0 | 0 | 0 | 971 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79GENER | GENERATOR REPLACEMENT AT VARIOUS PRECINCTS | POLICE FACILITIES | 000 | PO-0079 |  | CITYWIDE | GENERATORS | 2019 | 4421 | 4610.46 | 50 | 284 | 0 | 0 | 0 | 0 | 4944.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79WNDWS | HWY UNIT 3, 67TH, 76TH, 111TH PCT WINDOW RPLCMNT | POLICE FACILITIES | 000 | PO-0079 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | WINDOW REPLACEMENT | 2019 | 2200 | 1477.21 | 0 | 5270 | 0 | 0 | 0 | 0 | 6747.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PROCONTRL | Project Controls Management Services | LEGAL MANDATES AND CORRECTION OF UNSAFE CONDITIONS | 000 | PW-0077 |  |  | PROJECT CONTROLS MANAGEMENT SERVICES | 2019 | 9644 | 0 | 3101 | 3943 | 2600 | 0 | 0 | 0 | 9644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PS-312MX | CITYWIDE REPAIRS & REHAB OF INTERCEPTING SEWERS - MAN & BX | PLANT UPGRADING AND RECONSTRUCTION | 000 | WP-0269 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | CITYWIDE REPAIRS TO AND REHABILITATION OF INTERCEPTING SEWERS THAT HAVE STRUCTURAL DEFECTS THAT MAY RESULT IN PIPE FAILURES IN THE NEAR TERM - MANAHTTAN AND BRONX | CITYWIDE REPAIRS TO AND REHABILITATION OF INTERCEPTING SEWERS THAT HAVE STRUCTURAL DEFECTS THAT MAY RESULT IN PIPE FAILURES IN THE NEAR TERM - MANAHTTAN AND BRONX | 2019 | 13714 | 1748.85 | 0 | 0 | 0 | 51 | 19144 | 0 | 20943.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PS-312Q | Citywide Repairs & Rehab of Intercepting Sewers, Queens | PLANT UPGRADING AND RECONSTRUCTION | 000 | WP-0269 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | CITYWIDE REPAIRS TO AND REHABILITATION OF INTERCEPTING SEWERS THAT HAVE STRUCTURAL DEFECTS THAT MAY RESULT IN PIPE FAILURES IN THE NEAR TERM - QUEENS | CITYWIDE REPAIRS TO AND REHABILITATION OF INTERCEPTING SEWERS THAT HAVE STRUCTURAL DEFECTS THAT MAY RESULT IN PIPE FAILURES IN THE NEAR TERM - QUEENS | 2019 | 21640 | 25577.04 | 44 | 0 | 0 | 0 | 0 | 0 | 25621.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW335ALLS | Asbestos and Lead Abatement Lump Sum | LEGAL MANDATES AND CORRECTION OF UNSAFE CONDITIONS |  | PW-0335 |  |  | ASBESTOS AND LEAD ABATEMENT LUMP SUM | 2019 | 6910 | 1284.63 | 0 | 0 | 2421 | 0 | 0 | 0 | 3705.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW335BSLS | Bulk Sampling Lump Sum | LEGAL MANDATES AND CORRECTION OF UNSAFE CONDITIONS |  | PW-0335 |  |  | BULK SAMPLING LUMP SUM | 2019 | 1200 | 819.51 | 0 | 381 | 0 | 0 | 0 | 0 | 1200.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-71 | FUEL TANK REPLACEMENT | LEGAL MANDATES AND CORRECTION OF UNSAFE CONDITIONS | 000 | PW-0348 |  | FUEL TANKS | FUEL TANKS | 2019 | 12385 | 738 | 4885 | 2500 | 20642 | 0 | 0 | 0 | 28765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-72 | FUEL TANK REPLACEMENT | LEGAL MANDATES AND CORRECTION OF UNSAFE CONDITIONS |  | PW-0348 |  |  | FUEL TANKS | 2019 | 12500 | 5250 | 9250 | 7826 | 0 | 0 | 0 | 0 | 22326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-73 | FUEL TANK REPLACEMENT | LEGAL MANDATES AND CORRECTION OF UNSAFE CONDITIONS |  | PW-0348 |  |  | FUEL TANKS | 2019 | 12500 | 5250 | 7250 | 7681 | 0 | 0 | 0 | 0 | 20181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-81 | FUEL TANK REPLACEMENT | LEGAL MANDATES AND CORRECTION OF UNSAFE CONDITIONS | 000 | PW-0348 |  |  | FUEL TANKS. | 2019 | 27500 | 0 | 2750 | 0 | 8000 | 14250 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-82 | FUEL TANK REPLACEMENT | LEGAL MANDATES AND CORRECTION OF UNSAFE CONDITIONS | 000 | PW-0348 |  |  | FUEL TANKS | 2019 | 27500 | 0 | 2750 | 0 | 8000 | 14250 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-83 | FUEL TANK REPLACEMENT | LEGAL MANDATES AND CORRECTION OF UNSAFE CONDITIONS | 000 | PW-0348 |  |  | FUEL TANK. | 2019 | 27400 | 0 | 2750 | 0 | 8000 | 14250 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-84 | FUEL TANK REPLACEMENT | LEGAL MANDATES AND CORRECTION OF UNSAFE CONDITIONS | 000 | PW-0348 |  |  | FUEL TANKS. | 2019 | 27500 | 0 | 2750 | 0 | 20608 | 1642 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PWCOMPDAT | Comptroller's Office Data Center Replacement at 1 Centre St. | REHABILITATION OF CITY-OWNED OFFICE SPACE | 000 | PW-0077 |  |  | COMPTROLLER'S OFFICE DATA CENTER REPLACEMENT AT 1 CENTRE ST. | 2019 | 1401 | 361.08 | 0 | 0 | 1040 | 0 | 0 | 0 | 1401.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1047 | Area Contract for Water Main Replacement, Queens & Bronx | TRUNK AND DISTRIBUTION MAIN EXTENSION | 000 | WM-0001 EP-0007 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | INSTALL DISTRIBUTION WATER MAINS THROUGHOUT BRONX AND QUEENS AS DIRECTED BY DISTRIBUTION ENGINEER. | 2019 | 3000 | 4722.56 | 6327 | 0 | 0 | 0 | 0 | 0 | 11049.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SAND349F2 | Citywide Resurfacing - Hurricane Sandy Phase 2 (FHWA Funded) | PRIMARY STREET RESURFACING | 000 | HW-0002M HW-0001R HW-0002K | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | CITYWIDE RESURFACING - HURRICANE SANDY PHASE 2 (FHWA FUNDED) | CITYWIDE RESURFACING - HURRICANE SANDY PHASE 2 (FHWA FUNDED) | 2019 | 9904 | 2554.25 | 10 | 0 | 197 | 0 | 0 | 0 | 2761.25 | 6407.81 | 0 | 0 | 3 | 0 | 0 | 0 | 6410.81
20190425 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SAND349FM | Sandy Phase 2 Resurfacing (FEMA Funded) | PRIMARY STREET RESURFACING | 000 | HW-0001X HW-0001K HW-0001M HW-0001Q HW-0001R | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | SANDY PHASE 2 RESURFACING (FEMA FUNDED) | SANDY PHASE 2 RESURFACING (FEMA FUNDED) | 2019 | 26817 | 4280.3 | 545 | 0 | 0 | 0 | 0 | 0 | 4825.3 | 8919.5 | 0 | 0 | 925 | 0 | 0 | 0 | 9844.5
20190425 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SAND350FM | Sandy Phase 2b Resurfacing (FEMA Funded) | PRIMARY STREET RESURFACING | 000 | HW-0002K HW-0001Q HW-0001R | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | SANDY PHASE 2B RESURFACING (FEMA FUNDED) | SANDY PHASE 2B RESURFACING (FEMA FUNDED) | 2019 | 2497 | 638.43 | 27 | 0 | 152 | 0 | 0 | 0 | 817.43 | 1976.41 | 0 | 0 | 0 | 31 | 0 | 0 | 2007.41
20190425 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDCONDC | Sandy Conduit Replacement - Citywide | FACILITY RECONSTRUCTION | 000 | HW-0003 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | SANDY CONDUIT REPLACEMENT - CITYWIDE | SANDY CONDUIT REPLACEMENT - CITYWIDE | 2019 | 5326 | 360.23 | 71 | 0 | 514 | 0 | 0 | 0 | 945.23 | 95.96 | 638 | 0 | 4511 | 0 | 0 | 0 | 5244.96
20190425 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW21 | WHEN AND WHERE HURRICANE SANDY - CITYWIDE | PRIMARY STREET RECONSTRUCTION | 000 | SE-087HW | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | WHEN AND WHERE HURRICANE SANDY - CITYWIDE | RECONSTRUCTION OF THOMAS STREET - HURRICANE SANDY | 2019 | 3147 | 2421.99 | 0 | 0 | 97 | 0 | 0 | 0 | 2518.99 | 1799.56 | 0 | 0 | 0 | 0 | 0 | 0 | 1799.56
20190425 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDISLND | HURRICANE SANDY DAMAGE ROCKAWAY BEACH ENTRY ISLANDS | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION |  | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RECONSTRUCTION OF ROCKAWAY BEACH ENTRY ISLANDS | 2019 | 65009 | 5627.04 | 52 | 20 | 0 | 0 | 65 | 0 | 5764.04 | 48330.32 | 0 | 0 | 0 | 0 | -11 | 0 | 48319.32
20190425 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDPRFAB | HURRICANE SANDY DAMAGE BEACHFRONT RESTORATION PROJECT | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION |  | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | REPLACE MODULAR BUILDING UNITS AT VARIOUS FACILITIES | 2019 | 136680 | 15347.24 | 426 | 0 | 125 | 7004 | 0 | 0 | 22902.24 | 111305.48 | 14 | 0 | 0 | 0 | 0 | 0 | 111319.48
20190425 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRENO | HURRCANE SANDY DAMAGE STATEN ISLAND BEACHES-VARIOUS | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION |  | P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | NEW MODULAR STRUCTURES AT VARIOUS BEACHES IN STATEN ISLAND AND BROOKLYN | 2019 | 13563 | 1254.27 | 0 | 0 | 0 | 1609 | 0 | 0 | 2863.27 | 11179.28 | 0 | 0 | 0 | 0 | 0 | 0 | 11179.28
20190425 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRESM1 | Citywide Reiliency Measures-East Side Coastal Resiliency | MISCELLANEOUS ENERGY EFFICIENCY AND SUSTAINABILITY | 000 | P-0508 PU-0100 |  |  | CITYWIDE RESILIENCY MEASURES-EAST SIDE COASTAL RESILIENCY | 2019 | 510854 | 0 | 3466 | 475027 | 252000 | 230000 | 20357 | 0 | 980850 | 0 | 0 | 258854 | 0 | 0 | 0 | 0 | 258854
20190425 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-813 | WATER MAIN WORK IN JEWEL STREETS AREA | REPLACEMENT OF CHRONICALLY FAILING COMPONENTS | 000 | SE-0200Q SE-0002K SE-0200K WM-0001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | WATER MAIN WORK IN JEWEL STREETS AREA COMMUNITY BOARD 10 IN QUEENS AND CB 5 BROOKLYN | 2019 | 25910 | 1138.2 | 0 | 0 | 0 | 28501 | 0 | 0 | 29639.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SEC20004K | CITYWIDE RECONSTRUCTION | REPLACEMENT OF CHRONICALLY FAILING COMPONENTS | 000 | SE-0002K SE-0002M | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | CITYWIDE RECONSTRUCTION | 2019 | 12668 | 19177.75 | 439 | 0 | 0 | 0 | 0 | 0 | 19616.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SEC20004P | CITYWIDE EMERGENCY SEWER RECONSTRUCTION | REPLACEMENT OF CHRONICALLY FAILING COMPONENTS | 099 | EP-0007 SE-0002R SE-0200R SE-0200X SE-0002Q SE-0200K SE-0200Q SE-0200M | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | CITYWIDE EMERGENCY SEWER RECONSTRUCTION | 2019 | 14500 | 34005.81 | 169 | 2171 | 0 | 0 | 0 | 0 | 36345.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SEC20004Q | Citywide emergency sewer reconstruction | REPLACEMENT OF CHRONICALLY FAILING COMPONENTS | 000 | SE-0002M SE-0002K SE-0002Q SE-0002R SE-0200Q SE-0200R SE-0200X | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | CITYWIDE EMERGENCY SEWER RECONSTRUCTION | 2019 | 21714 | 24525.27 | 165 | 0 | 0 | 0 | 0 | 0 | 24690.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SEC20004R | Citywide Emergency Sewer Reconstruction | REPLACEMENT OF CHRONICALLY FAILING COMPONENTS | 000 | EP-0007 SE-0002Q SE-0002X | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | CITYWIDE EMERGENCY SEWER RECONSTRUCTION | 2019 | 18084 | 38352.7 | 1799 | 0 | 0 | 0 | 0 | 0 | 40151.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SEC20004S | Citywide emergency sewer reconstruction | REPLACEMENT OF CHRONICALLY FAILING COMPONENTS | 000 | SE-0002M SE-0002R SE-0200R | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | ITYWIDE EMERGENCY SEWER RECONSTRUCTION | 2019 | 18600 | 27696.98 | 2459 | 0 | 100 | 0 | 0 | 0 | 30255.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SEC20004T | Citywide emergency sewer reconstruction | REPLACEMENT OF CHRONICALLY FAILING COMPONENTS | 000 | SE-0002M EP-0007 SE-0002K SE-0002Q SE-0002R SE-0002X SE-0200K SE-0200Q SE-0200R SE-0200X |  |  | CITYWIDE EMERGENCY SEWER RECONSTRUCTION | 2019 | 19300 | 28605 | 1710 | 9967 | 0 | 0 | 0 | 0 | 40282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SEC20004U | Citywide Emergency Sewer Reconstruction | REPLACEMENT OF CHRONICALLY FAILING COMPONENTS | 000 | EP-0007 SE-0002K SE-0002M SE-0002Q SE-0002R SE-0002X SE-0200K SE-0200Q SE-0200R SE-0200X |  |  | CITYWIDE EMERGENCY SEWER RECONSTRUCTION | 2019 | 25475 | 0 | 27432 | 0 | 0 | 0 | 0 | 0 | 27432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SEC20004V | Emergency Reconstruction of Sewers | REPLACEMENT OF CHRONICALLY FAILING COMPONENTS |  | EP-0007 SE-0002M SE-0002Q SE-0002R SE-0002X SE-0200K SE-0200Q SE-0200R SE-0200X |  |  | EMERGENCY RECONSTRUCTION OF SEWERS, CITYWIDE | 2019 | 27500 | 0 | 0 | 14167 | 0 | 0 | 0 | 0 | 14167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-GUN-18 | Guniting of Sewers, Citywide | REPLACEMENT OF CHRONICALLY FAILING COMPONENTS | 000 | SE-0758 |  |  | GUNITING OF SEWERS, CITYWIDE | 2019 | 10704 | 9333.83 | 10106 | 0 | 0 | 0 | 0 | 0 | 19439.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-GUN-19 | Emergency Guniting of Sewers, Citywide | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 000 | SE-0758 |  |  | EMERGENCY GUNITING OF SEWERS, CITYWIDE | 2019 | 8100 | 0 | 7627 | 1079 | 0 | 0 | 0 | 0 | 8706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-LC-20 | Emergency lining of sewers citywide | REPLACEMENT OF CHRONICALLY FAILING COMPONENTS | 000 | SE-0002K SE-0002M SE-0002Q SE-0002R SE-0002X |  |  | EMERGENCY LINING OF SEWERS CITYWIDE | 2019 | 9000 | 7151.89 | 2337 | 0 | 0 | 0 | 0 | 0 | 9488.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-LC-21 | Emergency Lining Contract Citywide | REPLACEMENT OF CHRONICALLY FAILING COMPONENTS | 000 | SE-0002M SE-0002K SE-0002Q SE-0002R SE-0002X |  |  | EMERGENCY LINING CONTRACT CITYWIDE | 2019 | 9000 | 0 | 4005 | 0 | 0 | 0 | 0 | 0 | 4005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | WM-LC-17 | Citywide Lining Contract for Water Mains | AUGMENTATION OF WATER SUPPLY SYSTEMS | 000 | WM-0001 |  |  | CITYWIDE LINING CONTRACT FOR LINING OF WATER MAINS ON BRIDGES AND OTHER NECESSARY INSTANCES | 2019 | 1000 | 5213.73 | 82 | 0 | 0 | 0 | 0 | 0 | 5295.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264CADA | CITYWIDE COURTS ADA LUMP SUM | RECONSTRUCTION/RENOVATION OF COURT FACILITIES |  | CO-0264 |  |  | CITYWIDE COURTS ADA REHABILATION | 2019 | 0 | 0 | 0 | 0 | 0 | 2450 | 5900 | 29709 | 38059 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264DCAS | REHABILITATION OF VARIOUS COURT FACILITES | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 000 | CO-0264 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | REHABILITATION OF VARIOUS COURT FACILITIES | REHABILITATION OF VARIOUS COURT FACILITIES | 2019 | 1774 | 0 | 0 | 187 | 0 | 50 | 241 | 0 | 478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264MISC | VARIOUS COURT FACILITIES- REHABILITATION | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 000 | CO-0264 |  | CITYWIDE | COURTS MISCELLANEOUS PROJECTS | 2019 | 42046 | 0 | 34650 | 211542 | 202145 | 162145 | 100000 | 457323 | 1167805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-ADA | VARIOUS COURTS BUILDINGS - ADA WORK | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 000 | CO-0264 |  |  | ACCESSIBILITY COMPLIANCE FOR DCAS MANAGED COURT BUILDINGS | 2019 | 0 | 0 | 0 | 0 | 0 | 3881 | 0 | 0 | 3881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-HVAC | VARIOUS PUBLIC BUILDINGS - COURTS HVAC UPGRADES | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 000 | CO-0264 |  |  | VARIOUS PUBLIC BUILDINGS - COURTS HVAC UPGRADES | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18346 | 18346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-LL11 | VARIOUS PUBLIC BUILDINGS - COURTS LOCAL LAW 11 | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 000 | CO-0264 |  |  | VARIOUS PUBLIC BUILDINGS - COURTS LOCAL LAW 11 | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 183 | 379 | 562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-LL5 | VARIOUS PUBLIC BUILDINGS - COURTS FIRE/LIFE SAFETY | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 000 | CO-0264 |  |  | VARIOUS PUBLIC BUILDINGS - COURTS FIRE/LIFE SAFETY | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 2247 | 27762 | 30009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-LL5FS | VARIOUS PUBLIC BUILDINGS - COURTS FIRE SUPPRESSION | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 000 | CO-0264 |  |  | VARIOUS PUBLIC BUILDINGS - COURTS FIRE DETECTION | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 6235 | 45336 | 51571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-ROOF | VARIOUS PUBLIC BUILDINGS - COURTS ROOF UPGRADES | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 000 | CO-0264 |  |  | VARIOUS PUBLIC BUILDINGS - COURTS ROOF UPGRADES | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 1184 | 2420 | 3604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | ONE-NYC | ONE NYC - ENERGY EFFICIENCY FUNDING | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT |  | PU-0025 |  |  | LUMP SUM | 2019 | 0 | 0 | 0 | 67243 | 305947 | 251879 | 281389 | 1596238 | 2502696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PLANYC | Energy Efficiency Projects (PlaNYC) | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 000 | PU-0025 |  |  | ENERGY EFFICIENT PROJECTS | 2019 | 0 | 444.5 | 0 | 58553 | 20000 | 67615 | 68967 | 144837 | 360416.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PT195-VAR | VARIOUS WATERFRONT PROPERTIES- RECONSTRUCTION | REHABILITATION OF WATERFRONT PROPERTIES | 000 | RE-0025 |  | VARIOUS | RECONSTRUCTION OF EXISTING PIERS & BULKHEADS. | 2019 | 0 | 1778.71 | 0 | 0 | 0 | 3477 | 3921 | 26430 | 35606.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW335ASB4 | VARIOUS PUBLIC BUILDINGS- ENVIRONMENTAL REMEDIATION | LEGAL MANDATES AND CORRECTION OF UNSAFE CONDITIONS | 000 | PW-0335 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | REMEDIATE HAZARDOUS MATERIALS AT VARIOUS CITY SITES | 2019 | 10774 | 7903.27 | 0 | 0 | 0 | 881 | 0 | 0 | 8784.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW340EMAC | BOARD OF ELECTIONS | BOARD OF ELECTIONS MODERNIZATION | 000 | PW-0340 |  |  |  | 2019 | 18110 | 11556.31 | -296 | 266 | 0 | 0 | 6030 | 0 | 17556.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77CJC | Community Justice Center | REHABILITATION OF CITY-OWNED OFFICE SPACE | 000 | PW-0077 |  |  | COMMUNITY JUSTICE CENTER | 2019 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77REHAB | VARIOUS PUBLIC BUILDINGS- REHABILITATION OF CITY-OWNED SPACE | REHABILITATION OF CITY-OWNED OFFICE SPACE | 000 | PW-0077 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | CITYWIDE | INTERIOR RENOVATIONS; PAINTING OF CEILINGS & WALLS; CARPETING; ELECTRICAL, HVAC & PLUMBING MODIFICATIONS; INITIAL OUTFITTING OF NEWLY RENOVATED SPACE | 2019 | 23531 | 8.38 | 121 | 0 | 2786 | 14152 | 1600 | 10160 | 28827.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SECAM | SECURITY CAMERAS - DCAS PUBLIC BUILDINGS | REHABILITATION OF CITY-OWNED OFFICE SPACE | 000 | PW-0077 |  |  | SECURITY CAMERAS - DCAS PUBLIC BUILDINGS | 2019 | 4250 | 108.96 | 0 | 0 | 0 | 792 | 0 | 0 | 900.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWCOMPDA2 | Comptroller's Office Data Center Replacement at 1 Centre St. | REHABILITATION OF CITY-OWNED OFFICE SPACE | 000 | PW-0077 |  |  | COMPTROLLER'S OFFICE DATA CENTER REPLACEMENT AT 1 CENTRE ST. | 2019 | 0 | 0 | 0 | 1166 | 0 | 0 | 0 | 0 | 1166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW-RLS | RENOVATION OF LEASED SPACE | RENOVATION OF LEASED SPACE | 000 | PW-0326 |  |  |  | 2019 | 0 | 0 | 29 | 410 | 0 | 8198 | 12704 | 73913 | 95254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | SOLARGR4 | NYPA - SOLAR PARKING | DISTRIBUTED GENERATION | 000 | PU-0025 |  |  |  | 2019 | 0 | 0 | 0 | 8000 | 0 | 0 | 0 | 0 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | SOLARGR5 | NYPA - RESILIENT SOLAR | DISTRIBUTED GENERATION | 000 | PU-0025 |  |  |  | 2019 | 0 | 0 | 0 | 8900 | 0 | 0 | 0 | 0 | 8900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | TYP-ADA | VARIOUS PUBLIC BUILDINGS - ADA WORK | LEGAL MANDATES AND CORRECTION OF UNSAFE CONDITIONS | 000 | PW-0282 |  |  | ADA WORK | 2019 | 0 | 0 | 0 | 0 | 0 | 12350 | 3215 | 10818 | 26383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | TYP-INT | VARIOUS PUBLIC BUILDINGS - INTERIOR REHAB | REHABILITATION OF CITY-OWNED OFFICE SPACE | 000 | PW-0077 |  |  | VARIOUS PUBLIC BUILDINGS - INTERIOR REHAB | 2019 | 0 | 0 | 0 | 0 | 0 | 4740 | 5520 | 28944 | 39204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | TYP-LL5 | LOCAL LAW 5 FIRE SUPPRESSION | LEGAL MANDATES AND CORRECTION OF UNSAFE CONDITIONS | 000 | PW-0293 |  |  | VARIOUS PUBLIC BUILDINGS - LOCAL LAW 5 FIRE/LIFE SAFETY | 2019 | 0 | 0 | 0 | 0 | 0 | 6192 | 11159 | 134555 | 151906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | TYP-LL5FA | LL5 - FIRE DETECTION | LEGAL MANDATES AND CORRECTION OF UNSAFE CONDITIONS |  | PW-0293 |  |  | TYP LS | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 3200 | 5855 | 9055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | TYP-ROOF | VARIOUS PUBLIC BUILDINGS - ROOF REPLACEMENT | REHABILITATION OF CITY-OWNED OFFICE SPACE | 000 | PW-0077 |  |  | ROOF REPLACEMENT | 2019 | 0 | 0 | 0 | 0 | 0 | 4998 | 1666 | 10579 | 17243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 998 | TRANSIT AUTHORITY CAPITAL | CAPSAP | ADDL MTA CAPITAL FUNDS FOR SUBWAY ACTION PLAN (SAP) | MISCELLANEOUS TRANSIT IMPROVEMENT PROJECTS | 000 | T-0169 |  |  | ADDL MTA CAPITAL FUNDS FOR SUBWAY ACTION PLAN (SAP) | 2019 | 0 | 0 | 164000 | 0 | 0 | 0 | 0 | 0 | 164000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 998 | TRANSIT AUTHORITY CAPITAL | CAPSOL91 | VARIOUS TRANSIT PROJECTS | MISCELLANEOUS TRANSIT IMPROVEMENT PROJECTS | 000 | T-0169 |  | CITYWIDE | THIS IS A FUNDING SOURCE WHERE THE CITY CONTRIBUTES ADDITIONAL FUNDS TNEW YORK CITY TRANSIT AUTHORITY IN CITY FISCAL YEAR 1991 THIS IS AREQUIREMENT IN THE MTA'S FIVE YEAR CAPITAL PROGRAM ENDING IN DECEMBER | 2019 | 0 | 1149741.29 | 232232 | 81240 | 0 | 0 | 0 | 0 | 1463213.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 998 | TRANSIT AUTHORITY CAPITAL | REVRAPD95 | RAPID TRANSIT REVOLVING FUND | MISCELLANEOUS PROJECTS FOR NEW YORK CITY TRANSIT | 000 | T-0005A |  | CITYWIDE | REVOLVING FUND FOR VARIOUS RAPID TRANSIT (SUBWAY) PROJECTS FOR CITY FI1995 | 2019 | 0 | 72000 | 8000 | 4000 | 4000 | 4000 | 4000 | 24000 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | CITYWIDE | 998 | TRANSIT AUTHORITY CAPITAL | TRACK95 | IFA TRACKWORK | IFA TRACKWORK PROJECT FOR NEW YORK CITY TRANSIT | 000 | T-0131 |  | CITYWIDE | FUNDS FOR IN-HOUSE TRACK REHABILITATION FOR CITY FISCAL YEAR 1995 | 2019 | 0 | 669742.1 | 35000 | 35000 | 35000 | 35000 | 35000 | 210000 | 1054742.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LB20DUMBO | DUMBO Branch Fit Out | ESSENTIAL RECONSTRUCTION OF FACILITIES | 201 | LB-0101 LB-0108 LB-0104 |  |  | NEW BRANCH FIT OUT | 2019 | 5000 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBC17DRBR | DYKER INTERIOR RENOVATION | ESSENTIAL RECONSTRUCTION OF FACILITIES | 210 | LB-D104 |  |  | DYKER INTERIOR RENOVATION | 2019 | 1000 | 0 | 0 | 100 | 0 | 807 | 0 | 0 | 907 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBC18CTRF | CORTELYOU ROOF | ESSENTIAL RECONSTRUCTION OF FACILITIES | 214 | LB-D104 |  |  | CORTELYOU ROOF | 2019 | 850 | 0 | 0 | 85 | 681 | 0 | 0 | 0 | 766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBC18FHSG | FT HAMILTON ROOF | ESSENTIAL RECONSTRUCTION OF FACILITIES | 210 | LB-D104 |  |  | FT HAMILTON ROOF | 2019 | 175 | 0 | 18 | 138 | 0 | 0 | 0 | 0 | 156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBC18GSMR | GRAVESEND MEETING ROOM | ESSENTIAL RECONSTRUCTION OF FACILITIES | 215 | LB-D104 |  |  | GRAVESEND MEETING ROOM | 2019 | 300 | 0 | 0 | 30 | 242 | 0 | 0 | 0 | 272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBC18KBFS | KINGS BAY FIRE SAFETY | ESSENTIAL RECONSTRUCTION OF FACILITIES | 215 | LB-D104 |  |  | KINGSBAY FIRE SAFETY | 2019 | 250 | 0 | 0 | 25 | 202 | 0 | 0 | 0 | 227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBC18KBHC | KINGS BAY BOILER | ESSENTIAL RECONSTRUCTION OF FACILITIES | 215 | LB-D104 |  |  | KINGSBAY BOILER | 2019 | 750 | 0 | 0 | 75 | 606 | 0 | 0 | 0 | 681 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBC19CHEL | Clinton Hill Wiring Upgrade | ESSENTIAL RECONSTRUCTION OF FACILITIES | 202 | LB-D104 |  |  | CLINTON HILL WIRING UPGRADE. | 2019 | 0 | 0 | 0 | 30 | 120 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBCENPH2 | CENTRAL RENOVATION - PHASE 2 | ESSENTIAL RECONSTRUCTION OF FACILITIES | 201 | LB-0104 |  |  | CENTRAL RENOVATION - PHASE 2 | 2019 | 0 | 0 | 0 | 0 | 25000 | 1345 | 0 | 0 | 26345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBEM05SWR | SYSTEMWIDE - Renovation/Rehab/Acquisition/Initial Outfitting | ESSENTIAL RECONSTRUCTION OF FACILITIES | 201 | LB-0104 |  |  | RENOVATIONS /REHABILITTION/ACQUISTION/INITAL OUTFITTING - SYSTEM WIDECAPITAL INITIATIVES BROOKYN PUBLIC LIBRARY | 2019 | 0 | 0 | 0 | 0 | 684 | 698 | 2915 | 4801 | 9098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBK16HLRF | Highlawn - Roof Replacement | ESSENTIAL RECONSTRUCTION OF FACILITIES | 211 | LB-K001 LB-D104 LB-0101 |  |  | HIGHLAWN - ROOF REPLACEMENT | 2019 | 0 | 0 | 0 | 86 | 0 | 818 | 0 | 0 | 904 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBK16SCRF | SPRING CREEK ROOF REPLACEMENT | ESSENTIAL RECONSTRUCTION OF FACILITIES | 205 | LB-K001 LB-D104 |  |  | SPRING CREEK ROOF REPLACEMENT | 2019 | 0 | 0 | 170 | 600 | 0 | 0 | 0 | 0 | 770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBM18NLOH | NEW LOTS BRANCH OVERHAUL | ESSENTIAL RECONSTRUCTION OF FACILITIES | 205 | LB-0104 LB-D104 |  |  | NEW LOTS OVERHAUL | 2019 | 28405 | 0 | 0 | 0 | 0 | 28405 | 0 | 0 | 28405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBM19BPLB | Brower Park Library Fit Out | ESSENTIAL RECONSTRUCTION OF FACILITIES | 208 | LB-0107 LB-D107 LB-K107 |  |  | BROWER PARK LIBRARY FIT OUT | 2019 | 0 | 0 | 0 | 3300 | 0 | 0 | 0 | 0 | 3300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBM19CAOH | CANARSIE BRANCH OVERHAUL | ESSENTIAL RECONSTRUCTION OF FACILITIES | 218 | LB-0104 |  |  | CANARSIE BRANCH OVERHAUL | 2019 | 0 | 0 | 0 | 0 | 4000 | 0 | 16000 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBP18BHBR | BROOKLYN HEIGHTS BRANCH FIT OUT | ESSENTIAL RECONSTRUCTION OF FACILITIES | 202 | LB-0101 LB-0108 LB-0104 |  |  | BROOKLYN HEIGHTS BRANCH FIT OUT | 2019 | 0 | 0 | 0 | 11000 | 0 | 0 | 0 | 0 | 11000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBP18LDIN | LEONARD INFRASTRUCTURE UPGRADE | ESSENTIAL RECONSTRUCTION OF FACILITIES | 201 | LB-0101 |  |  | LEONARD INFRASTRUCTURE UPGRADE | 2019 | 0 | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBP18PCAD | PACIFIC ADA COMPLIANCE | ESSENTIAL RECONSTRUCTION OF FACILITIES | 206 | LB-0101 |  |  | PACIFIC ADA COMPLIANCE | 2019 | 0 | 0 | 0 | 350 | 0 | 3150 | 0 | 0 | 3500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 040 | DEPARTMENT OF EDUCATION | ACEDOE804 | DOE - Boiler Controls Installation | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 201 | PU-0025 |  |  | BOILER CONTROLS INSTALLATION | 2019 | 0 | 0 | 0 | 5628 | 0 | 0 | 0 | 0 | 5628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 040 | DEPARTMENT OF EDUCATION | ACEDOE805 | DOE - Steam System Optimization | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 201 | PU-0025 |  |  | STEAM SYSTEM OPTIMIZATION | 2019 | 0 | 0 | 0 | 3723 | 0 | 0 | 0 | 0 | 3723 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 040 | DEPARTMENT OF EDUCATION | ACEDOE807 | DOE - Lighting Upgrade | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 201 | PU-0025 |  |  | DOE - LIGHTING UPGRADE | 2019 | 0 | 0 | 0 | 1107 | 0 | 0 | 0 | 0 | 1107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 042 | CITY UNIVERSITY | BY024-012 | Haitian Studies Institute Initial Outfitting | MISCELLANEOUS RECONSTRUCTION | 200 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | TECHNOLOGY AND CAPITAL IMPROVEMENT | 2019 | 100 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 042 | CITY UNIVERSITY | BY025-012 | Haitian Studies Institute Initial Outfitting | MISCELLANEOUS RECONSTRUCTION | 200 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | TECHNOLOGY AND CAPITAL IMPROVEMENT | 2019 | 100 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 042 | CITY UNIVERSITY | BY026-013 | Renovation of Ingersoll Extension | MISCELLANEOUS RECONSTRUCTION | 214 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RENOVATION OF INGERSOLL EXTENSION | 2019 | 1000 | 5797.2 | 0 | 0 | 0 | 459 | 0 | 0 | 6256.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 042 | CITY UNIVERSITY | BY031-017 | Electrical Upgrades | MISCELLANEOUS RECONSTRUCTION | 200 | HN-K300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ELECTRICAL UPGRADES | 2019 | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 042 | CITY UNIVERSITY | BY032-018 | ADA Upgrades for the Brooklyn College Student Center | MISCELLANEOUS RECONSTRUCTION | 200 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ADA UPGRADES FOR THE BROOKLYN COLLEGE STUDENT CENTER | 2019 | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 042 | CITY UNIVERSITY | BY033-019 | Ingersoll Lecture Halls | MISCELLANEOUS RECONSTRUCTION | 200 | HN-D300 |  |  | INGERSALL LECTURE HALLS | 2019 | 2000 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 042 | CITY UNIVERSITY | BY034-019 | Restoration of Main Quad | MISCELLANEOUS RECONSTRUCTION | 200 | HN-D300 |  |  | RESTORATION OF MAIN QUAD | 2019 | 724 | 0 | 0 | 0 | 0 | 724 | 0 | 0 | 724 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 042 | CITY UNIVERSITY | BY036-020 | Main Quad Restoration | MISCELLANEOUS RECONSTRUCTION | 200 | HN-K300 |  |  | MAIN QUAD RESTORATION | 2019 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 042 | CITY UNIVERSITY | CA034KG13 | Gas Booster Pump Upgrade | MISCELLANEOUS RECONSTRUCTION | 200 | HN-D005 |  |  | GAS BOOSTER PUMP UPGRADE | 2019 | 127 | 28.36 | 0 | 99 | 0 | 0 | 0 | 0 | 127.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 042 | CITY UNIVERSITY | CA134KG13 | College Hall Roof Replacement | MISCELLANEOUS RECONSTRUCTION | 200 | HN-D005 HN-0206 |  |  | COLLEGE HALL ROOF REPLACEMENT | 2019 | 118 | 19.57 | 229 | 0 | 0 | 0 | 0 | 0 | 248.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 042 | CITY UNIVERSITY | CA234KG13 | Library Roof Replacement | MISCELLANEOUS RECONSTRUCTION | 200 | HN-D005 HN-0206 |  |  | LIBRARY ROOF REPLACEMENT | 2019 | 550 | 89.1 | 586 | 0 | 13511 | 0 | 0 | 0 | 14186.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 042 | CITY UNIVERSITY | CA334KG13 | Emergency Medium Temp. Steam Line Replacement | MISCELLANEOUS RECONSTRUCTION | 200 | HN-0206 |  |  | EMERGENCY MEDIUM TEMP. STEAM LINE REPLACEMENT | 2019 | 500 | 0 | 402 | 0 | 0 | 0 | 0 | 0 | 402 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 042 | CITY UNIVERSITY | KG028-011 | Performing Arts Center Renovations | MISCELLANEOUS RECONSTRUCTION | 200 | HN-0206 HN-K250 HN-D002 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | PERFORMING ARTS CENTER RENOVATIONS | 2019 | 3000 | 596.04 | 48 | 0 | 6813 | 0 | 0 | 0 | 7457.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 042 | CITY UNIVERSITY | KG031-013 | Renovation of Pool Facilities | MISCELLANEOUS RECONSTRUCTION | 200 | HN-K250 HN-D002 HN-0206 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RENOVATION OF POOL FACILITIES | 2019 | 1000 | 405 | 0 | 2095 | 0 | 0 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 042 | CITY UNIVERSITY | KG033-017 | Roof Replacements | MISCELLANEOUS RECONSTRUCTION | 200 | HN-D002 |  |  | ROOF REPLACEMENTS | 2019 | 1000 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 042 | CITY UNIVERSITY | KG043-018 | Campus Roadway Improvements | MISCELLANEOUS RECONSTRUCTION | 200 | HN-D004 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CAMPUS ROADWAYS UPGRADES | 2019 | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 0 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 042 | CITY UNIVERSITY | KG201-006 | Additional Roof Replacement | MISCELLANEOUS RECONSTRUCTION | 200 | HN-0206 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CONTINUATION OF ROOF REPLACEMENT AT VARIOUS BUILDINGS. | 2019 | 1500 | 2131.71 | 0 | 203 | 0 | 0 | 0 | 0 | 2334.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 042 | CITY UNIVERSITY | KG203-006 | Gymnasium | ATHLETIC FIELDS, GYMNASIUMS AND EQUIPMENT | 200 | HN-0206 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | THIS PROJECT WILL BRING CHILLED WATER EXTENSION PIPING FROM EXISTING UNDERGROUND UTILITIES TO THE HEALTH AND PHYSICAL EDUCATION BUILDING. IT WILL PROVIDE ALL COILS, PUMPS, AIR HANDLERS, ETC. TO CREATE A NEW CENTRALLY CONTROLLED AIR CONDITIONING SYSTEM. | 2019 | 3030 | 225 | 0 | 302 | 0 | 0 | 0 | 0 | 527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 042 | CITY UNIVERSITY | KG206-006 | T4 Roof Replacement | MISCELLANEOUS RECONSTRUCTION | 200 | HN-D004 HN-0206 |  |  | T4 ROOF REPLACEMENT | 2019 | 1566 | 88.09 | 1783 | 0 | 0 | 0 | 0 | 0 | 1871.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 042 | CITY UNIVERSITY | ME018-005 | LIBRARY EXPANSION | MISCELLANEOUS RECONSTRUCTION | 200 | HN-0206 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NEW | 2019 | 5230 | 9651.32 | 0 | 0 | 0 | 0 | 75 | 0 | 9726.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 042 | CITY UNIVERSITY | ME026-010 | BEDFORD BUILDING ADA COMPLIANCE | MISCELLANEOUS RECONSTRUCTION | 209 | HN-D002 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | TBD | 2019 | 5000 | 1199.3 | 0 | 550 | 0 | 0 | 0 | 0 | 1749.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 042 | CITY UNIVERSITY | ME027-011 | Carroll Street Building Upgrade | MISCELLANEOUS RECONSTRUCTION | 200 | HN-0206 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ADDITIONAL FUNDING FOR UPGRADE OF BUILDING | 2019 | 1000 | 5000 | 0 | 0 | 219 | 0 | 0 | 0 | 5219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 042 | CITY UNIVERSITY | ME031-013 | Virtual Desktop Infrastructure | MISCELLANEOUS RECONSTRUCTION | 200 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | VIRTUAL DESKTOP INFRASTRUCTURE #3 | 2019 | 1400 | 1352.88 | 0 | 0 | 47 | 0 | 0 | 0 | 1399.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 042 | CITY UNIVERSITY | ME033-014 | Gymnasium Upgrades | MISCELLANEOUS RECONSTRUCTION | 209 | HN-K300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | GYMNASIUM UPGRADES | 2019 | 1000 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 042 | CITY UNIVERSITY | ME034-014 | Gym Floor and Bleachers | MISCELLANEOUS RECONSTRUCTION | 200 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | GYM FLOOR AND BLEACHERS | 2019 | 2000 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 042 | CITY UNIVERSITY | ME037-016 | College Prep School Classroom Improvements | MISCELLANEOUS RECONSTRUCTION | 200 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | COLLEGE PREP SCHOOL CLASSROOM IMPROVEMENTS | 2019 | 65 | 0 | 0 | 0 | 0 | 0 | 65 | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 042 | CITY UNIVERSITY | ME038-016 | Child Development Center Upgrades | MISCELLANEOUS RECONSTRUCTION | 200 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CHILD DEVELOPMENT CENTER UPGRADES | 2019 | 1500 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 042 | CITY UNIVERSITY | ME039-017 | Student Lounge Upgrades | MISCELLANEOUS RECONSTRUCTION | 200 | HN-D300 |  |  | STUDENT LOUNGE UPGRADES | 2019 | 1500 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 042 | CITY UNIVERSITY | ME040-018 | Differently-Abled Lab | MISCELLANEOUS RECONSTRUCTION |  | HN-K300 |  |  | DIFERENTLY-ABLED LAB | 2019 | 1000 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 042 | CITY UNIVERSITY | ME041-018 | Art and Historic Space Renovation | MISCELLANEOUS RECONSTRUCTION | 200 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ART AND HISTORIC SPACE RENOVATION | 2019 | 1500 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 042 | CITY UNIVERSITY | ME042-019 | Founder's Auditorium Renovation & Upgrades | MISCELLANEOUS RECONSTRUCTION | 200 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | FOUNDER'S AUDITORIUM RENOVATION & UPGRADES | 2019 | 2250 | 0 | 0 | 0 | 0 | 0 | 2250 | 0 | 2250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 042 | CITY UNIVERSITY | ME043-020 | Open Computer and Lab Digital Interactive Learning Spaces | MISCELLANEOUS RECONSTRUCTION | 200 | HN-K300 |  |  | OPEN COMPUTER AND LAB DIGITAL INTERACTIVE LEARNING SPACES | 2019 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 042 | CITY UNIVERSITY | NY008-010 | Student Lounge/Eating/Study Space Build-out | MISCELLANEOUS RECONSTRUCTION | 202 | HN-K300 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES |  | STUDENT LOUNGE/EATING/STUDY SPACE BUILD-OUT | 2019 | 734 | 0 | 0 | 0 | 734 | 0 | 0 | 0 | 734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 042 | CITY UNIVERSITY | NY010-011 | Library And Student Facilities Upgrade | MISCELLANEOUS RECONSTRUCTION | 202 | HN-K300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | LIBRARY AND STUDENT FACILITIES UPGRADE | 2019 | 750 | 0 | 0 | 0 | 750 | 0 | 0 | 0 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 042 | CITY UNIVERSITY | NY012-011 | Initial Outfitting of the Biological Science Labs | MISCELLANEOUS RECONSTRUCTION | 200 | HN-D300 |  |  | INITIAL OUTFITTING OF THE BIOLOGICAL SCIENCE LABS | 2019 | 217 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 042 | CITY UNIVERSITY | NY014-013 | Upgrade of Hospitality and Culinary Arts Facilities | MISCELLANEOUS RECONSTRUCTION | 202 | HN-K300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | UPGRADE OF HOSPITALITY AND CULINARY ARTS FACILITIES | 2019 | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 0 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 042 | CITY UNIVERSITY | NY018-014 | Dental Hygiene Facilities Upgrade | MISCELLANEOUS RECONSTRUCTION | 200 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | DENTAL HYGIENE FACILITIES UPGRADE | 2019 | 400 | 0 | 0 | 0 | 0 | 400 | 0 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 042 | CITY UNIVERSITY | NY019-015 | Fabrication Laboratory | MISCELLANEOUS RECONSTRUCTION | 200 | HN-K300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | FABRICATION LABORATORY | 2019 | 400 | 0 | 0 | 0 | 400 | 0 | 0 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 042 | CITY UNIVERSITY | NY020-015 | Academic Learning Center Renovations | MISCELLANEOUS RECONSTRUCTION | 200 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ACADEMIC LEARNING CENTER RENOVATIONS | 2019 | 400 | 0 | 0 | 0 | 400 | 0 | 0 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 042 | CITY UNIVERSITY | NY021-016 | Academic Learning Center Renovations and Equipment | MISCELLANEOUS RECONSTRUCTION | 200 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ACADEMIC LEARNING CENTER RENOVATIONS & EQUIPMENT | 2019 | 1290 | 0 | 0 | 0 | 1290 | 0 | 0 | 0 | 1290 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 042 | CITY UNIVERSITY | NY023-017 | Science Lab Renovations | MISCELLANEOUS RECONSTRUCTION | 200 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | SCIENCE LAB RENOVATIONS | 2019 | 2500 | 0 | 0 | 0 | 2500 | 0 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 042 | CITY UNIVERSITY | NY024-018 | Exterior Space Improvements | MISCELLANEOUS RECONSTRUCTION | 200 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | UPGRADE EXTERIOR SPACES AT NEW YORK CITY TECH | 2019 | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 042 | CITY UNIVERSITY | NY025-018 | Pearl Street Building Renovation | MISCELLANEOUS RECONSTRUCTION | 200 | HN-D300 HN-0300 HN-D004 HN-K002 HN-K300 |  |  | PEARL STREET BUILDING RENOVATION | 2019 | 2500 | 0 | 1761 | 0 | 1505 | 0 | 0 | 0 | 3266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 042 | CITY UNIVERSITY | SAND-KG02 | HVAC Repair/Replacement - Sandy Related | MISCELLANEOUS RECONSTRUCTION | 200 | HN-0206 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | HVAC REPAIR/REPLACEMENT - SANDY RELATED | 2019 | 285 | 28.41 | 0 | 0 | 486 | 0 | 0 | 0 | 514.41 | 255.69 | 0 | 0 | 0 | 0 | 0 | 0 | 255.69
20190425 | BROOKLYN | 042 | CITY UNIVERSITY | SAND-KG03 | Marina Reconstruction | MISCELLANEOUS RECONSTRUCTION | 200 | HN-0206 HN-K250 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | MARINA RECONSTRUCTION | 2019 | 2592 | 30 | 13 | 0 | 3770 | 0 | 0 | 0 | 3813 | 270 | 113 | 4139 | 0 | 0 | 0 | 0 | 4522
20190425 | BROOKLYN | 056 | POLICE DEPARTMENT | NDF-PENN | NDF - 127 Pennsylvania Ave Community Center | NEIGHBORHOOD REVITALIZATION | 200 | ED-0384 |  |  | NYPD - 127 PENNSYLVANIA AVENUE COMMUNICATIONS CENTER | 2019 | 4909 | 7997.4 | 2702 | 0 | 0 | 0 | 0 | 0 | 10699.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79 GLEN | 245 GLENMORE RENOVATION | POLICE FACILITIES | 200 | PO-0079 |  |  | BUILDING RENOVATION | 2019 | 20618 | 0 | 0 | 0 | 10072 | 10546 | 0 | 0 | 20618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 056 | POLICE DEPARTMENT | PO7911FR | 11 FRONT STR RENOVATION | POLICE FACILITIES | 200 | PO-0079 |  |  | 11 FRONT STR RENOVATION | 2019 | 3747 | 2109.78 | 3940 | 0 | 0 | 0 | 0 | 0 | 6049.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAHS | FIRING RANGE RECONSTRUCTION AT CONEY ISLAND | POLICE FACILITIES | 200 213 | PO-0079 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 2556 MCDONALD AV, BRROKLYN NY | RANGE RECONSTRUCTION | 2019 | 2591 | 596.26 | 0 | 200 | 1794 | 0 | 0 | 0 | 2590.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAHX | 63RD BATHROOM RENOVATION | POLICE FACILITIES | 200 | PO-0079 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BATHROOM RENOVATION | 2019 | 312 | 251.1 | 0 | 61 | 0 | 0 | 0 | 0 | 312.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79TD32 | TRANSIT DISTRICT 32 ROOF RENOVATION | POLICE FACILITIES | 200 | PO-0079 |  | 960 CAROLL STREET, BROOKLYN | ROOF RENOVATION | 2019 | 480 | 0 | 613 | 0 | 0 | 0 | 0 | 0 | 613 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 056 | POLICE DEPARTMENT | POD73CMRM | 73RD PRECINCT COMMUNITY ROOM | POLICE FACILITIES | 200 | PO-D079 |  |  | ESTIMATE | 2019 | 250 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 056 | POLICE DEPARTMENT | PO-KVEST | PEOPLE'S PRECINCTS VESTIBULE REDESIGN | POLICE FACILITIES | 200 | PO-K079 |  |  | RENOVATION | 2019 | 1000 | 0 | 436 | 564 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDCD13 | PROPERTY CLERK ELECTRICAL CONDUIT | POLICE FACILITIES | 200 | PO-0079 |  | ERIE BASIN PROPERTY CLERK | PROPERTY CLERK | 2019 | 9704 | 0 | 971 | 0 | 0 | 0 | 0 | 0 | 971 | 0 | 8733 | 0 | 0 | 0 | 0 | 0 | 8733
20190425 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDCD3 | POLICE SERVICE AREA 1 (PSA1) | POLICE FACILITIES | 200 | PO-0079 |  | 2860 WEST 23RD STREET BROOKLYN | ELECTRICAL REHABILITATION | 2019 | 322 | 0 | 33 | 0 | 0 | 0 | 0 | 0 | 33 | 0 | 289 | 0 | 0 | 0 | 0 | 0 | 289
20190425 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDCD4 | FLOYD BENNETT FIELD ELECTRICAL | POLICE FACILITIES | 200 | PO-0079 |  |  | ELECTRICAL REHABILITATION | 2019 | 575 | 0 | 58 | 0 | 0 | 0 | 0 | 0 | 58 | 0 | 517 | 0 | 0 | 0 | 0 | 0 | 517
20190425 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDCD5 | TRANSIT DISTRICT 34 ELECTRICAL | POLICE FACILITIES | 200 | PO-0079 |  |  | ELECTRICAL REHABILITATION | 2019 | 1058 | 0 | 106 | 0 | 0 | 0 | 0 | 0 | 106 | 0 | 952 | 0 | 0 | 0 | 0 | 0 | 952
20190425 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDELEC2 | PSA 1 ELECTRICAL SYSTEM REHABILITATION (SANDY) | POLICE FACILITIES | 200 | PO-0079 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | PSA1 | ELECTRICAL REHABILITATION | 2019 | 550 | 133.2 | 250 | 0 | 0 | 0 | 0 | 0 | 383.2 | 1198.84 | 0 | 0 | 0 | 0 | 0 | 0 | 1198.84
20190425 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDWARE | 23RD STR WAREHOUSE RECONSTRUCTION | POLICE FACILITIES | 200 | PO-0079 |  |  | RECONSTRUCTION | 2019 | 8434 | 0 | 0 | 872 | 0 | 0 | 0 | 0 | 872 | 0 | 0 | 7835 | 0 | 0 | 0 | 0 | 7835
20190425 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDWINDO | PSA1 - Windows installment (SANDY) | POLICE FACILITIES | 200 | PO-0079 |  |  | ABOR AND MATERIALS FOR THE WINDOWS INSTALLMENT FOR PSA1 (POLICE SERVICE AREA 1) WHICH WAS DAMAGED DURING HURRICANE SANDY | 2019 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 0 | 0 | 0 | 0 | 0 | 72
20190425 | BROOKLYN | 057 | FIRE DEPARTMENT | ACEFDN703 | FDNY - DESIGN & INSTALLATION OF 37 KW SOLAR SYSTEM AT EC332 | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 201 | PU-0025 |  |  | FDNY - DESIGN & INSTALLATION OF 37 KW SOLAR PHOTOVOLTAIC SYSTEM AT EC3332 | 2019 | 235 | 44.29 | 0 | 191 | 0 | 0 | 0 | 0 | 235.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 057 | FIRE DEPARTMENT | ACEFDN801 | FDNY - Solar Photo-voltaic system at EMS 58 | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 201 | PU-0025 |  |  | SOLAR PHOTO-VOLTAIC SYSTEM AT EMS 58 | 2019 | 257 | 0 | 30 | 227 | 0 | 0 | 0 | 0 | 257 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 057 | FIRE DEPARTMENT | F175237MC | MULTI COMPONENT RENOVATION - EC237 | NEW FACILITIES AND RENOVATIONS | 201 | F-0175 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | MULTI COMPONENT RENOVATION - EC237 | 2019 | 6047 | 7400.71 | 600 | 0 | 0 | 0 | 0 | 0 | 8000.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 057 | FIRE DEPARTMENT | F175DR253 | Doors Replacements - EC 253 | NEW FACILITIES AND RENOVATIONS | 211 | F-0175 |  |  | DOOR REPLACEMENT - EC253 | 2019 | 185 | 0 | 185 | 0 | 0 | 0 | 0 | 0 | 185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 057 | FIRE DEPARTMENT | F175EBT39 | EMS BATT 39 RENOVATIONS | NEW FACILITIES AND RENOVATIONS | 205 | F-0175 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | EMS BATT 39 RENOVATIONS | 2019 | 5136 | 10969.53 | 1002 | 0 | 0 | 0 | 0 | 0 | 11971.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 057 | FIRE DEPARTMENT | F175MC218 | Multi-Component Renovations - EC218 | NEW FACILITIES AND RENOVATIONS | 204 | F-0175 |  |  | MULTI-COMPONENT RENOVATIONS - EC218 | 2019 | 5598 | 0 | 498 | 0 | 5000 | 0 | 0 | 0 | 5498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 057 | FIRE DEPARTMENT | F175MC224 | FLOOR, KITCHEN L-OHD - EC224 | NEW FACILITIES AND RENOVATIONS | 202 | F-0175 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | FLOOR, KITCHEN L-OHD - EC224 | 2019 | 2282 | 630.11 | 360 | 4481 | 0 | 0 | 0 | 0 | 5471.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 057 | FIRE DEPARTMENT | FD175D211 | Door Replacement - EC211 | NEW FACILITIES AND RENOVATIONS | 201 | F-D175 |  |  | DOOR REPLACEMENT - EC211 | 2019 | 150 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 057 | FIRE DEPARTMENT | FD175D243 | Door Replacement - EC243 | NEW FACILITIES AND RENOVATIONS | 211 | F-D175 |  |  | DOOR REPLACEMENT - EC243 | 2019 | 75 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 057 | FIRE DEPARTMENT | FD175D249 | DOOR REPLACEMENT - EC249 | NEW FACILITIES AND RENOVATIONS | 209 | F-D175 F-0175 |  |  | DOOR REPLACEMENT - EC249 | 2019 | 86 | 0 | 86 | 0 | 0 | 0 | 0 | 0 | 86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 057 | FIRE DEPARTMENT | FD175D271 | Door Replacement - EC271 | NEW FACILITIES AND RENOVATIONS | 204 | F-D175 |  |  | DOOR REPLACEMENT - EC271 | 2019 | 150 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 057 | FIRE DEPARTMENT | FD175D309 | Door Replacement - EC309 | NEW FACILITIES AND RENOVATIONS | 218 | F-D175 |  |  | DOOR REPLACEMENT - EC309 | 2019 | 75 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 057 | FIRE DEPARTMENT | FD175D332 | Door Replacement - EC332 | NEW FACILITIES AND RENOVATIONS | 205 | F-D175 |  |  | DOOR REPLACEMENT - EC332 | 2019 | 150 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 057 | FIRE DEPARTMENT | FD175E249 | ROOF REPLACEMENT - EC249 | NEW FACILITIES AND RENOVATIONS | 209 | F-D175 |  |  | ROOF REPLACEMENT | 2019 | 50 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 057 | FIRE DEPARTMENT | FD175LR38 | Lactation Room - EMS38 | NEW FACILITIES AND RENOVATIONS | 209 | F-D175 |  |  | LACTATION ROOM - EMS38 | 2019 | 100 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 057 | FIRE DEPARTMENT | FD175LR44 | Lactation Room - EMS44 | NEW FACILITIES AND RENOVATIONS | 216 | F-D175 |  |  | FD175LR44 | 2019 | 100 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 057 | FIRE DEPARTMENT | FD175W245 | WINDOW REPLACEMENT - EC245 | NEW FACILITIES AND RENOVATIONS | 213 | F-D175 |  |  | WINDOW REPLACEMENT - EC245 | 2019 | 750 | 263.47 | 486 | 0 | 0 | 0 | 0 | 0 | 749.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 057 | FIRE DEPARTMENT | FD175W248 | WINDOW REPLACEMENT - EC248 | NEW FACILITIES AND RENOVATIONS | 217 | F-D175 |  |  | WINDOW REPLACEMENT - EC248 | 2019 | 375 | 160.9 | 214 | 0 | 0 | 0 | 0 | 0 | 374.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 057 | FIRE DEPARTMENT | FD175W330 | Window Replacement - EC330 | NEW FACILITIES AND RENOVATIONS | 211 | F-D175 F-0175 |  |  | WINDOW REPLACEMENT - EC330 | 2019 | 582 | 0 | 564 | 0 | 0 | 0 | 0 | 0 | 564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 068 | ADMIN FOR CHILDREN'S SERVICES | HRC006KCH | LOTS FOR TOTS, KINGS COUNTY HOSPITAL (RESO A COUNCIL) | SOCIAL SERVICES BUILDINGS | 209 | HR-C006 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 451 CLARKSON AVENUE, BROOKLYN BLOCK 3070, LOTS 10, 11, 12, 13 | DESIGN AND CONSTRUCT PLAYLOT AT KINGS COUNTY HOSPITAL FOR HIV POSITCHILDREN | 2019 | 208 | 0 | 139 | 15 | 15 | 16 | 0 | 0 | 185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 068 | ADMIN FOR CHILDREN'S SERVICES | JJZROSSLB | THE CROSSROADS JUVENILE CENTER - LIBRARY RENOVATION | RECONSTRUCTION OF SECURE DETENTION FACILITIES | 216 | CS-K001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RENOVATION OF LIBRARY ROOM AND EQUIPMENT PURCHASE | 2019 | 250 | 144.26 | 0 | 100 | 0 | 0 | 0 | 0 | 244.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112AUBR | AUBURN ADULT RESIDENCE - BATHROOM UPGRADE | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 |  |  | AUBURN ADULT RESIDENCE - ALL ARCHITECTURAL , MECHANICAL AND PLUMBING WORK REQUIRED TO IMPROVE THE DETERIORATED CONDITIONS IN MULTIPLE BATHROOMS THROUGHOUT THE FACILITY | 2019 | 5150 | 8516.49 | 370 | 0 | 0 | 0 | 0 | 0 | 8886.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112BASW | ATLANTIC ARMORY SIDEWALK RECONSTRUCTION | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 |  |  | ATLANTIC ARMORY SIDEWALK RECONSTRUCTION | 2019 | 284 | 0 | 284 | 0 | 0 | 0 | 0 | 0 | 284 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112HWCR | HELP WOMEN'S CENTER ROOF | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 |  |  | HELP WOMEN'S CENTER ROOF | 2019 | 780 | 60 | 0 | 0 | 0 | 720 | 0 | 0 | 780 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112LFER | LINDEN MEN'S SHELTER - ELEVATOR REPLACEMENT | SHELTERS FOR HOMELESS INDIVIDUALS | 205 | HH-0112 |  |  | LINDEN MEN'S SHELTER - ELEVATOR REPLACEMENT | 2019 | 530 | 0 | 0 | 80 | 0 | 450 | 0 | 0 | 530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112LINT | 85 LEXINGTON AVE BATHROOM RECONSTRUCTION | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 |  |  | BATHROOM RECONSTRUCTION | 2019 | 504 | 0 | 0 | 0 | 0 | 42 | 0 | 462 | 504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112LMEP | LINDEN BOILER RECONSTRUCTION | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 |  |  | BOILER RECONSTRUCTION | 2019 | 1950 | 0 | 0 | 150 | 150 | 0 | 1650 | 0 | 1950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112LXEP | 85 LEXINGTON AVE BOILER RECONSTRUCTION | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 |  |  | BOILER RECONS | 2019 | 2040 | 0 | 0 | 170 | 0 | 1870 | 0 | 0 | 2040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112PAFL | PAMOJA HOUSE FLOOR | SHELTERS FOR HOMELESS INDIVIDUALS | 203 | HH-0112 |  |  | RECONSTRUCT DORM FLOORS | 2019 | 1475 | 125 | 0 | 0 | 0 | 1350 | 0 | 0 | 1475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112PJBP | PAMOJA HOUSE INSTALLATION OF BLACK FLOW PREVENTER | SHELTERS FOR HOMELESS INDIVIDUALS | 203 | HH-0112 |  |  | PAMOJA HOUSE-INSTALLATION OF BACK FLOW PREVENTER TO AVOID CONTAMINATION DUE TO BACK FLOW | 2019 | 175 | 175 | 0 | 0 | 0 | 146 | 0 | 0 | 321 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112PJRR | PAMOJA HOUSE - ROOF REPLACEMENT | SHELTERS FOR HOMELESS INDIVIDUALS | 203 | HH-0112 |  |  | PAMOJA HOUSE - ROOF REPLACEMENT | 2019 | 1999 | 2792.49 | 2697 | 750 | 2550 | 0 | 0 | 0 | 8789.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112PREK | RENOVATION AND IMPROVEMENTS TO THE PARK SLOPE ARMORY | SHELTERS FOR HOMELESS INDIVIDUALS | 206 | HH-D025 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | PARK SLOPE ARMORY-REHABILITATION OF ROOMS FOR PRE-K PROGRAM | 2019 | 1500 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112PSR1 | PARK SLOPE - ROOF REPLACEMENT | SHELTERS FOR HOMELESS INDIVIDUALS | 206 | HH-0112 |  |  | PARK SLOPE - ROOF REPLACEMENT | 2019 | 5250 | 2300 | 1619 | 250 | 0 | 0 | 0 | 0 | 4169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH115AUSW | AUBURN SIDEWALK REPLACEMENT | SHELTERS FOR HOMELESS FAMILIES |  | HH-0115 |  |  | AUBURN SIDEWALK REPLACEMENT | 2019 | 68 | 0 | 68 | 0 | 0 | 0 | 0 | 0 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH115BFRR | Bushwick Family Roof Replacement | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0115 |  |  | ROOF REPLACEMENT | 2019 | 2600 | 0 | 0 | 400 | 0 | 2400 | 0 | 0 | 2800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH115BINT | BUSHWICK FAMILY FACADE RECONSTRUCTION | SHELTERS FOR HOMELESS FAMILIES |  | HH-0112 |  |  | RECONSTRUCT FACADE | 2019 | 1920 | 0 | 0 | 0 | 0 | 160 | 0 | 1760 | 1920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH115BMEP | BUSHWICK FAMILY BOILER RECONSTRUCTION | SHELTERS FOR HOMELESS FAMILIES |  | HH-0112 |  |  | BOILER RECONSTRUCTION | 2019 | 2160 | 0 | 0 | 180 | 750 | 1230 | 0 | 0 | 2160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH115FBME | FANNIE BARNES BOILER RECONSTRUCTION | SHELTERS FOR HOMELESS FAMILIES | 216 | HH-0112 |  |  | RECON BOILER | 2019 | 0 | 0 | 84 | 0 | 924 | 0 | 0 | 0 | 1008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH115FLRF | FLATLANDS ROOF REPLACEMENT | SHELTERS FOR HOMELESS FAMILIES | 218 | HH-0115 |  |  | ROOF REPLACEMENT AT FLATLANDS FAMILY RESIDENCE | 2019 | 1950 | 150 | 0 | 900 | 900 | 0 | 0 | 0 | 1950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH115MEXT | WAYSIDE MACDONOUGH FACADE AND WINDOWS | SHELTERS FOR HOMELESS FAMILIES |  | HH-0112 |  |  | EXTERIOR RECONSTRUCTION | 2019 | 240 | 0 | 0 | 20 | 0 | 220 | 0 | 0 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH115MMEP | WAYSIDE MACDONOUGH BOILER RECONS | SHELTERS FOR HOMELESS FAMILIES |  | HH-0112 |  |  | RECONSTRUCT BOILER | 2019 | 300 | 0 | 25 | 0 | 275 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH115RMCX | ROSE MCCARTHY - WINDOW REPLACEMENT AND EXTERIOR RECONSTRUCT | SHELTERS FOR HOMELESS FAMILIES |  | HH-0115 |  |  | ROSE MCCARTHY - WINDOW REPLACEMENT AND EXTERIOR RECONSTRUCTION | 2019 | 0 | 0 | 0 | 0 | 0 | 115 | 368 | 0 | 483 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH115SAEU | FANNIE BARNES EXTERIOR UPGRADE | SHELTERS FOR HOMELESS FAMILIES | 216 | HH-0115 |  |  | FANNIE BARNES EXTERIOR UPGRADE | 2019 | 3900 | 300 | 0 | 0 | 0 | 1600 | 2000 | 0 | 3900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH115SEXT | STOCKHOLM FAMILY CENTER - ROOF AND FACADE RECONSTRUCTION | SHELTERS FOR HOMELESS FAMILIES |  | HH-0112 |  |  | ROOF AND FACADE | 2019 | 1008 | 0 | 0 | 0 | 0 | 84 | 0 | 924 | 1008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH115STEP | STOCKHOLM FAMILY CENTER -BOILER RECONSTRUCTION | SHELTERS FOR HOMELESS FAMILIES |  | HH-0115 |  |  | BOILER RECON | 2019 | 1152 | 0 | 96 | 0 | 1056 | 0 | 0 | 0 | 1152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH115WMRR | MCDONOUGH ROOF AND FACADE RECONSTRUCTION | SHELTERS FOR HOMELESS FAMILIES |  | HH-0115 |  |  | ROOF REPLACEMENT | 2019 | 813 | 0 | 65 | 748 | 0 | 0 | 0 | 0 | 813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HHCN001 | BROOKLYN NEIGHBORHOOD IMPROVEMENT DIST.-BEDFORD AVE. RENOVAT | SHELTERS FOR HOMELESS FAMILIES |  | HH-D025 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | BROOKLYN NEIGHBORHOOD IMPROVEMENT DIST.-BEDFORD AVE. RENOVATION | 2019 | 300 | 0 | 29 | 355 | 0 | 0 | 0 | 0 | 384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HHCN002 | RENOVATION OF BEDFORD ATLANTIC ARMORY INTO RECREATIONAL CTR. | SHELTERS FOR HOMELESS FAMILIES | 208 | HH-D025 |  |  | RENOVATION OF BEDFORD ATLANTIC ARMORY INTO RECREATIONAL CTR. | 2019 | 3000 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HHCN003 | BEDFORD ATLANTIC ARMORY ATHLETIC CENTER | SHELTERS FOR HOMELESS INDIVIDUALS | 209 | HH-D112 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | BEDFORD ATHLETIC ARMORY ATHLETIC CENTER | 2019 | 250 | 0 | 50 | 200 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 072 | DEPARTMENT OF CORRECTION | C75-PLUMB | SEWER PUMPS AND PLUMBING VARIOUS FACILITIES | BUILDING SYSTEMS AND INFRASTRUCTURE | 202 | C-0075 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | 275 ATLANTIC AVE BROOKLYN | BROOKLYN HOUSE OF DETENTION MAIN KITCHEN PLUMBING ANDSEWER PUMPING IN THE BASEMENT-MAJOR WATER LEAK FROMMAIN KITCHEN-- SEWAGE SYSTEM MUST BE PUMPED TO CITYSEWER SYSTEM | 2019 | 558 | 57.81 | 0 | 3000 | 5000 | 5000 | 0 | 0 | 13057.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 096 | HUMAN RESOURCES ADMINISTRATION | HR25BRCS | Brownsville Community Center | SOCIAL SERVICES BUILDINGS |  | HR-0025 |  |  | BROWNSVILLE COMMUNITY CENTER | 2019 | 0 | 0 | 0 | 22165 | 0 | 0 | 0 | 0 | 22165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 096 | HUMAN RESOURCES ADMINISTRATION | HR25FOSF2 | Initial Outfitting of 102-50 Foster Avenue (Warehouse Space) | SOCIAL SERVICES BUILDINGS | 214 | HR-0025 |  |  |  | 2019 | 0 | 0 | 0 | 0 | 256 | 0 | 0 | 0 | 256 | 0 | 0 | 0 | 245 | 0 | 0 | 0 | 245
20190425 | BROOKLYN | 096 | HUMAN RESOURCES ADMINISTRATION | HR25FOST2 | Construction at 102-50 Foster Ave to accomodate warehouses | SOCIAL SERVICES BUILDINGS | 214 | HR-0025 |  |  |  | 2019 | 0 | 0 | 0 | 2294 | 2029 | 0 | 0 | 0 | 4323 | 0 | 0 | 1709 | 1511 | 0 | 0 | 0 | 3220
20190425 | BROOKLYN | 096 | HUMAN RESOURCES ADMINISTRATION | HRCNBDST | Bedford Stuyvesant MSC Boiler Replacement, 1958 Fulton St | SOCIAL SERVICES BUILDINGS | 203 | HR-D002 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES | 1958 FULTON ST//1001 HERKIMER ST BK 11233-3104 | EXTERIOR RENOVATIONS | 2019 | 1070 | 0 | 1070 | 0 | 0 | 0 | 0 | 0 | 1070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | ACEDCA805 | DCA - Brooklyn Children's Museum Energy Efficiency Measures | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 201 | PU-0025 |  |  | BROOKLYN CHILDREN'S MUSEUM GEOTHERMAL SYSTEM UPGRADES | 2019 | 0 | 0 | 0 | 2249 | 0 | 0 | 0 | 0 | 2249 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV209-SEC | JCM - Jewish Childrens Museum Security Cameras | CAPITAL EQUIPMENT | 209 | PV-0467 |  |  |  | 2019 | 306 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV230-SEA | WCS - New York Aquarium Sea Cliffs Exhibit | ESSENTIAL RECONSTRUCTION OF FACILITIES | 213 | PV-0230 PV-K230 PV-D230 PV-D467 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | NY AQUARIUM SEA CLIFF EXHIBIT | 2019 | 1000 | 0 | 0 | 500 | 0 | 4636 | 0 | 0 | 5136 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 1000
20190425 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV235AFAR | BMA - African Art Gallery Renovations | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | PV-D235 PV-0235 |  | 200 EASTERN PARKWAY, BROOKLYN, NY | AFRICAN ART GALLERY IN BROOKLYN MUSEUM. | 2019 | 3711 | 0 | 0 | 0 | 0 | 0 | 843 | 2868 | 3711 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV235BDEV | BMA - Brooklyn Museum - Building Envelope Rehab | ESSENTIAL RECONSTRUCTION OF FACILITIES | 209 | PV-K235 PV-D235 PV-0235 |  |  | BMA - BROOKLYN MUSEUM - BUILDING ENVELOPE REHAB | 2019 | 8600 | 0 | 0 | 0 | 0 | 5555 | 0 | 0 | 5555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV235EDUC | BMA - Education Space | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | PV-K235 PV-0235 PV-D235 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | DESIGN AND CONSTRUCTION OF EDUCATION SPACE IN BROOKLYN MUSEUM'S HALL | 2019 | 3040 | 0 | 0 | 0 | 0 | 6040 | 0 | 0 | 6040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV236AUDI | BBG - Auditorium Renovations | ESSENTIAL RECONSTRUCTION OF FACILITIES | 209 | PV-K236 PV-0236 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 1000 WASHINGTON AVENUE, BROOKLYN NY | BBG AUDITORIUM RENOVATION: UPGRADES TO THE 280-SEAT PUBLIC THEATER. | 2019 | 1878 | 0 | 0 | 0 | 0 | 0 | 1000 | 2439 | 3439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV236BCSG | BBG: Brooklyn Center for Sustainable Gardening | ESSENTIAL RECONSTRUCTION OF FACILITIES | 208 209 | PV-K236 PV-D236 |  |  | BROOKLYN BOTANIC GARDEN: BROOKLYN CENTER FOR SUSTAINABLE GARDENING | 2019 | 1500 | 0 | 0 | 0 | 0 | 0 | 5383 | 0 | 5383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV262PRNG | BCM - FHWA Parking Lot - 906 Prospect Place | ESSENTIAL RECONSTRUCTION OF FACILITIES | 208 | PV-D262 PV-0262 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | MUSEUM, 145 BROOKLYN AVENUE, BROOKLYN. PENDING SITE ACQUISITION AND DEVELOPMENT OF 906 PTROSPECT PLACE. | DEVELOPMENT OF PARKING LOT; PRE-PLANNING STUDIES, DESIGN AND CONSTRUCTION. | 2019 | 6590 | 0 | 0 | 0 | 0 | 0 | 5389 | 0 | 5389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV264ROSE | BAM - Rose Renovation | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | PV-K264 |  |  | BAM - ROSE RENOVATION | 2019 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467BKLN | DCA - Brooklyn Fund | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | PV-0467 |  |  | DCA FUNDS TO SUPPORT NON-PROFIT CULTURAL ORGANIZATIONS IN BROOKLYN | 2019 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 2200 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467SWBB | Spaceworks Brooklyn Bridge Park | ESSENTIAL RECONSTRUCTION OF FACILITIES | 202 | PV-0467 |  | 334 FURMAN STREET, BROOKLYN, NY | RECONSTRUCTION OF TWO FLOORS AT 334 FURMAN STREET IN BROOKLYN BRIDGE PARK FOR ARTIST STUDIOS AND REHEARSAL SPACE. | 2019 | 6200 | 0 | 0 | 0 | 0 | 3000 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PVIPOFWSP | BHS - In Pursuit of Freedom Public Art at Willoughby Sq Park | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | ED-0075 | PROJECT DELAYED RESULTING FROM CONTRACTOR DEFAULT |  | IN PURSUIT OF FREEDOM PUBLIC ART AT WILLOUGHBY SQUARE PARK | 2019 | 794 | 0 | 794 | 0 | 0 | 0 | 0 | 0 | 794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | 979BDWAY | Bushwick Development | MISCELLANEOUS | 200 | ED-0384 |  |  | SITE ACQUISITION AND DEVELOPMENT | 2019 | 0 | 0 | 6500 | 0 | 0 | 0 | 0 | 0 | 6500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BAMNSITEA | BAM Cultural District - North Site Condemnation | MISCELLANEOUS | 202 | ED-0075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BAM LDC - CONDEMNATION OF LIQUOR STORE ON NORTH SITE AND ASSOCIATED COSTS | 2019 | 5128 | 2199.12 | 187 | 0 | 0 | 0 | 0 | 0 | 2386.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BAMPARK | BAM Park Renovation | MISCELLANEOUS | 202 | ED-D075 ED-0384 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BAM PARK RENOVATION | 2019 | 300 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BAMSOSITE | BAM South Site - Cultural Condo Acquisition | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | ED-0075 PV-0467 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ACQUSITION OF CONDO IN TOWER AT BAM SOUTH SITE | 2019 | 4000 | 0 | 2005 | 4580 | 0 | 0 | 0 | 0 | 6585 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BAMSTRTS | BAM Cultural District Streetscapes | MISCELLANEOUS | 200 202 | ED-D380 ED-K075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | DESIGN AND CONSTRUCTION OF BAM STREETSCAPE AND PUBLIC SPACE | 2019 | 1000 | 1710.58 | 0 | 252 | 0 | 0 | 0 | 0 | 1962.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BAT4LAN | BAT Pier 4: Ferry Landing Rehabilitation | WATERFRONT DEVELOPMENT | 207 | ED-0373 ED-0075 ED-0409 ED-0401 ED-0404 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | FERRY LANDING REHABILITATION | 2019 | 500 | 559.64 | 6979 | 0 | 0 | 0 | 0 | 0 | 7538.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATANCHOR | BAT Anchor Tenant Strategy | INDUSTRIAL DEVELOPMENT | 200 | ED-0373 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BAT ANCHOR TENANT STRATEGY - 100K JOBS PLAN | 2019 | 36000 | 0 | 0 | 0 | 0 | 12762 | 2643 | 0 | 15405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATBEYOND | BAT New Needs | INDUSTRIAL DEVELOPMENT | 200 | ED-0075 ED-0373 ED-K075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BAT NEW NEEDS | 2019 | 100000 | 97819.64 | 12742 | 19322 | 0 | 0 | 0 | 0 | 129883.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATIMPRO | BAT Improvements | INDUSTRIAL DEVELOPMENT | 200 | ED-0373 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BAT IMPROVEMENTS | 2019 | 3152 | 12587.34 | 400 | 0 | 0 | 0 | 0 | 0 | 12987.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATLOGIST | Brooklyn Army Terminal Logistics Center | INDUSTRIAL DEVELOPMENT | 200 | ED-0373 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BAT LOGISTICS CENTER | 2019 | 50000 | 0 | 0 | 0 | 0 | 10000 | 40000 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATPLUGIN | BAT Plug-In Industrial Strategy | INDUSTRIAL DEVELOPMENT | 200 | ED-0373 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BAT PLUG-IN INDUSTRIAL STRATEGY - 100K JOBS PLAN | 2019 | 13000 | 0 | 0 | 0 | 0 | 10000 | 3000 | 0 | 13000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BCTBERTH | Brooklyn Cruise Terminal - New Berth and Landside Redevelop | WATERFRONT DEVELOPMENT | 200 | ED-K409 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BROOKLYN CRUISE TERMINAL: NEW BERTH AND LANDSIDE REDEVELOPMENT. | 2019 | 1000 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BCTPIER11 | Brooklyn Cruise Terminal Pier 11 | MISCELLANEOUS | 200 | ED-0409 |  |  | BROOKLYN CRUISE TERMINAL PIER 11 | 2019 | 3000 | 2203 | 0 | 797 | 0 | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BKBRESP | Brooklyn Bridge Esplanade | MISCELLANEOUS | 200 | ED-M075 ED-D075 ED-0075 |  |  | BROOKLYN BRIDGE ESPLANADE | 2019 | 0 | 0 | 0 | 5000 | 1000 | 0 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BKCRUISE | Brooklyn Cruise Terminal Substructre Rehab | PORT DEVELOPMENT | 206 | ED-0409 ED-K409 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BROOKLYN CRUISE TERMINAL SUBSTRUCTRE REHAB | 2019 | 5000 | 0 | 2500 | 2200 | 0 | 0 | 1500 | 0 | 6200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BKCTPIER | Brooklyn Cruise Terminal Pier 12 Substructure Rehab | MISCELLANEOUS | 200 | ED-0409 |  |  | BROOKLYN CRUISE TERMINAL PIER 12 SUBSTRUCTURE REHAB | 2019 | 1500 | 279.67 | 1220 | 0 | 0 | 0 | 0 | 0 | 1499.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BKWMMIMP | Brooklyn Wholesale Meat Markets Building Improvement | MISCELLANEOUS | 200 | ED-0075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BROOKLYN WHOLESALE MEAT MARKETS BUILDING IMPROVEMENTS | 2019 | 2194 | 1985.4 | 40 | 169 | 0 | 0 | 0 | 0 | 2194.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNY5THST | BNYDC 5th Street Reconstruction | INDUSTRIAL DEVELOPMENT | 200 | ED-0319 |  |  | BNYDC 5TH STREET RECONSTRUCTION | 2019 | 1233 | 0 | 1233 | 0 | 0 | 0 | 0 | 0 | 1233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNY910SBB | BNYDC Berths 9, 10 and Small Boat Basin Structural Work | INDUSTRIAL DEVELOPMENT | 200 | ED-0319 |  |  | RECONSTRUCTION OF THE STRUCTURAL FOUNDATIONS OF BERTHS 9, 10 AND THE SMALL BOAT BASIN, LOCATED AT THE BROOKLYN NAVY YARD, | 2019 | 46047 | 0 | 300 | 8925 | 11370 | 10818 | 7191 | 7443 | 46047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYADMIRL | BNYDC Admiral Building | INDUSTRIAL DEVELOPMENT | 202 | ED-0319 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BNYDC - ADMIRAL BUILDING | 2019 | 3825 | 3180.27 | 644 | 0 | 0 | 0 | 0 | 0 | 3824.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYBD132 | BNYDC Building 132 | INDUSTRIAL DEVELOPMENT | 200 | ED-0319 |  |  | BNYDC BUILDING 132 | 2019 | 1055 | 0 | 62 | 331 | 331 | 331 | 0 | 0 | 1055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYBDELEV | BNYDC Elevator Reconstruction and Replacement | INDUSTRIAL DEVELOPMENT | 200 | ED-0319 |  |  | BROOKLYN NAVY YARD-WIDE REPAIRS AND RECONSTRUCTION OF BUILDING ELEVATORS | 2019 | 16500 | 0 | 400 | 4191 | 2191 | 1442 | 2500 | 0 | 10724 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYBLD127 | BNYDC Building 127 Redevelopment | INDUSTRIAL DEVELOPMENT | 200 | ED-0319 |  |  | BNYDC BUILDING 127 REDEVELOPMENT | 2019 | 4000 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYBLD292 | BNYDC Building 292 Roof Replacement | INDUSTRIAL DEVELOPMENT | 200 | ED-0319 |  |  | DESIGN AND RECONSTRUCTION OF ROOFING SSYTEM FOR BUILDING 292 IN BROOKLYN NAVY YARD. | 2019 | 1499 | 1443.44 | 56 | 0 | 0 | 0 | 0 | 0 | 1499.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYBLDG50 | BNYDC Building 50 | INDUSTRIAL DEVELOPMENT | 200 | ED-0319 |  |  | BNYDC BUILDING 50 ROOF REPLACEMENT | 2019 | 1055 | 0 | 64 | 330 | 330 | 331 | 0 | 0 | 1055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYDCSUBF | BNYDC Con Edison Substation F Upgrade | INDUSTRIAL DEVELOPMENT | 200 | ED-0319 |  |  | POWER SUBSTATION UPGRADE | 2019 | 4232 | 0 | 500 | 1744 | 744 | 744 | 500 | 0 | 4232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYDCWELD | BNYDC Welding Lab | INDUSTRIAL DEVELOPMENT | 200 | ED-K319 |  |  | DESIGN AND CONSTRUCTION OF A WELDING LAB AT THE BROOKLYN NAVY YARD | 2019 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYELEV22 | BNYDC Building 22 Elevator Modernization | INDUSTRIAL DEVELOPMENT | 200 | ED-0319 |  |  | BNYDC BUILDING 22 ELEVATOR MODERNIZATION | 2019 | 276 | 0 | 276 | 0 | 0 | 0 | 0 | 0 | 276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYFERPRT | BNYDC Ferry Port | INDUSTRIAL DEVELOPMENT | 200 | ED-D319 ED-0319 |  |  | BNYDC FERRY PORT | 2019 | 1107 | 0 | 1107 | 0 | 0 | 0 | 0 | 0 | 1107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYFNCLIN | BNYDC Fence Line Restructuring | INDUSTRIAL DEVELOPMENT | 200 | ED-D319 ED-K319 ED-0319 |  |  | BNY FENCE LINE RESTRUCTURING - VARIOUS LOCATIONS | 2019 | 1926 | 0 | 426 | 5633 | 583 | 584 | 0 | 0 | 7226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYHARBOR | BNYDC PS 331 NY Harbor School Trailer Installation | INDUSTRIAL DEVELOPMENT | 200 | ED-K319 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NY HARBOR SCHOOL TRAILER INSTALLATION | 2019 | 242 | 0 | 0 | 242 | 0 | 0 | 0 | 0 | 242 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYHITN | BNYDC HITN Eco-Rooftop Production Studio | INDUSTRIAL DEVELOPMENT | 200 | ED-K319 |  |  | BNYDC HISPANIC INFORMATION AND TELECOMMUNICATION NETWORK ECO ROOFTOP PRODUCTION STUDIO | 2019 | 500 | 0 | 0 | 1167 | 167 | 166 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYINF-BD | BNYDC Infrastructure Building Rehab | INDUSTRIAL DEVELOPMENT | 202 | ED-0319 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BNYDC INFRASTRUCTURE BUILDING REHAB | 2019 | 4207 | 2365.58 | 0 | 4600 | 2300 | 4000 | 3234 | 48972 | 65471.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYINFRAW | BNYDC Infrastructure - Water Projects | INDUSTRIAL DEVELOPMENT | 200 | ED-0319 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | WEST 125TH STREET/MANHATTANVILLE | 2019 | 32950 | 32388.83 | 0 | 500 | 3000 | 3997 | 0 | 0 | 39885.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYINF-ST | BNYDC Infrastructure Steam | INDUSTRIAL DEVELOPMENT | 200 | ED-0319 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BNYDC INFRASTRUCTURE STEAM | 2019 | 19169 | 0 | 100 | 599 | 1000 | 13770 | 1300 | 2400 | 19169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYINF-WF | BNYDC Infrastructure Waterfront | INDUSTRIAL DEVELOPMENT | 200 | ED-0319 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BNYDC INFRASTRUCTURE WATERFRONT | 2019 | 29790 | 16806.64 | 0 | 0 | 1290 | 0 | 3309 | 43271 | 64676.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYINWF6B | BNYDC Infrastructure Berth 6B | INDUSTRIAL DEVELOPMENT | 200 | ED-0319 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BNYDC INFRASTRUCTURE BERTH 6B | 2019 | 3331 | 2997.62 | 3331 | 0 | 0 | 0 | 0 | 0 | 6328.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYLIGHT | BNYDC Lighting Replacement | INDUSTRIAL DEVELOPMENT | 200 | ED-0319 |  |  | BNYDC LIGHTING REPLACEMENT | 2019 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYLL11 | BNYDC Local Law 11 Compliance - Buildings 3 and 5 | MISCELLANEOUS | 200 | ED-0319 |  |  | LOCAL LAW 11 COMPLIANCE - BUILDINGS 3 AND 5 | 2019 | 6390 | 0 | 4495 | 1895 | 0 | 0 | 0 | 0 | 6390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYMACRO | BNYDC Macro Sea | MISCELLANEOUS | 200 | ED-D319 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | MACRO SEA DESIGN AND FABRICATION CENTER, A TENANT OF THE GREEN MANUFACTURING CENTER AT THE BROOKLYN NAVY YARD | 2019 | 7000 | 6920.27 | 80 | 0 | 0 | 0 | 0 | 0 | 7000.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYMOVDEV | BNYDC Naval Annex Infra Reconstruction | CULTURAL DEVELOPMENT | 200 | ED-0319 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | FUNDING PROVIDED TO MATCH STATE GRANT FOR INFRASTRUCTURE IN NORTHERN TRIANGLE. | 2019 | 11300 | 0 | 11300 | 0 | 0 | 0 | 0 | 0 | 11300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYNANO | BNYDC TIF Nanotronics | MISCELLANEOUS | 200 | ED-0319 |  |  | BNYDC TIF NANOTRONICS | 2019 | 3250 | 0 | 3250 | 0 | 0 | 0 | 0 | 0 | 3250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYROOF77 | BNYDC - Building 77 Roof | INDUSTRIAL DEVELOPMENT | 200 | ED-D319 |  |  | BUILDING 77 ROOF | 2019 | 500 | 0 | 0 | 167 | 167 | 166 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYRPZBFL | BNYDC Installation of RPZ Backflow Devices | INDUSTRIAL DEVELOPMENT | 200 | ED-0319 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NYCDEP REQUIRES EACH PERIMETER SERVICE CONNECTIONS RETROFITED WITH BACKFLOW PREVENTION DEVICES IN THE FORM OF REDUCED PRESSURE ZONE DEVICES. RPZ DEVICES PREVENT CONTAMINATES PRODUCED BY BUSINESSES OR BUILDINGS FROM FLOWING BACK INTO THE PUBLIC WATER SUPPLY. | 2019 | 3703 | 276.25 | 3427 | 0 | 0 | 0 | 0 | 0 | 3703.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYSANIND | BNYDC Sands Street Industrial Center Renovation | INDUSTRIAL DEVELOPMENT | 200 | ED-0319 |  |  | BNY SANDS STREET INDUSTRIAL CENTER RENOVATION | 2019 | 40000 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYSPKFIR | BNYDC Sprinkler and Fire Alarm System Upgrades | INDUSTRIAL DEVELOPMENT | 200 | ED-0319 |  |  | BNYDC SPRINKLER AND FIRE ALARM SYSTEM UPGRADE | 2019 | 8318 | 0 | 400 | 7450 | 2617 | 2416 | 885 | 0 | 13768 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYSTEAM | BNYDC Brooklyn STEAM Center | INDUSTRIAL DEVELOPMENT | 200 | ED-0319 ED-K319 |  |  | CONSTRUCTION OF THE BROOKLYN STEAM (SCIENCE, TECHNOLOGY, EDUCATION, ARTS, AND MATHEMATICS) CENTER. | 2019 | 10000 | 4027 | 12973 | 0 | 0 | 0 | 0 | 0 | 17000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYTIFUND | BNYDC Tenant Improvement Fund | INDUSTRIAL DEVELOPMENT | 200 | ED-0319 |  |  | BNY TENANT IMPROVEMENT FUND | 2019 | 6179 | 0 | 0 | 750 | 750 | 750 | 750 | 1250 | 4250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYUBFARM | BNYDC Urban Farm Incubator | INDUSTRIAL DEVELOPMENT | 200 | ED-K319 |  |  | ROOFTOP FARMING FOR PUBLIC CONSUMPTION | 2019 | 1000 | 0 | 0 | 0 | 333 | 667 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYUPSTM | BNYDC Above Ground Steam Main | INDUSTRIAL DEVELOPMENT | 200 | ED-0319 |  |  | ABOVE GROUND STEAM MAIN RELOCATION | 2019 | 1313 | 0 | 200 | 371 | 371 | 371 | 0 | 0 | 1313 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BUSHDEVSP | Bush Terminal Development Site Preparation | MISCELLANEOUS ENERGY EFFICIENCY AND SUSTAINABILITY | 200 | ED-0075 |  |  | BUSHDEVSP | 2019 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8847.65 | 8643 | 0 | 0 | 0 | 0 | 0 | 17490.65
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BUSHMINY | Bush Terminal - Made in New York Campus | INDUSTRIAL DEVELOPMENT | 200 | ED-0410 |  |  | BUSH TERMINAL - MADE IN NEW YORK CAMPUS, RENOVATION OF UNIT A AND UNIT C, DEMOLITION AND RECONSTRUCTION OF BUILDING G AND CAMPUSWIDE INFRASTRUCTURE IMPROVEMENTS | 2019 | 142400 | 0 | 15998 | 1000 | 10000 | 10000 | 19000 | 0 | 55998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BUSHTCAFE | Bush Terminal Cafe Building Improvements | MISCELLANEOUS | 200 | ED-0075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BUSH TERMINAL CAFÔ BUILDING IMPROVEMENTS | 2019 | 3000 | 0 | 2400 | 600 | 0 | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BUSHTPARK | Bush Terminal Park | COMMUNITY DEVELOPMENT | 200 | ED-0410 P-D017 |  |  | BUSH TERMINAL PARK | 2019 | 2000 | 976.85 | 1024 | 0 | 0 | 0 | 0 | 0 | 2000.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BUSHUNTAC | Bush Terminal Made in NY Unit A and C | MISCELLANEOUS | 200 | ED-0410 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CONSTRUCTION AND RENOVATION OF UNIT A AT BUSH TERMINAL | 2019 | 53501 | 0 | 6199 | 7302 | 0 | 40000 | 0 | 0 | 53501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BUSHUTIL | Bush Terminal Site and Utility Improvements | MISCELLANEOUS | 200 | ED-0410 ED-0075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BUSH TERMINAL UTILITY IMPROVEMENTS | 2019 | 39301 | 0 | 5000 | 10000 | 5000 | 12901 | 6400 | 0 | 39301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CANTONBLK | Canton Court Bulkhead Replacement | MISCELLANEOUS | 200 | RE-0025 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CANTON COURT BULKHEAD REPLACEMENT BROOKLYN | 2019 | 4400 | 560.4 | 22 | 0 | 3418 | 0 | 0 | 0 | 4000.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CATCCSBI | Caribbean American Chamber of Commerce and Industry - CATCC | MISCELLANEOUS | 202 | ED-D075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CARIBBEAN AMERICAN CHAMBER OF COMMERCE AND INDUSTRY - CARIBBEAN AMERICAN TRADE AND CULTURAL CENTER SMALL BUSINESS INCUBATOR | 2019 | 3000 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CNEDST | CNED - Bedford Stuyvesant | NEIGHBORHOOD REVITALIZATION | 203 | ED-0384 ED-K384 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CNED BEDFORD STUYVESANT | 2019 | 7882 | 7760.67 | 0 | 216 | 0 | 0 | 0 | 0 | 7976.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | COLUMBST | Columbia Street Platform Rehabilitation | MISCELLANEOUS | 200 | RE-0025 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | COLUMBIA STREET PLATFORM REHABILITATION | 2019 | 1375 | 238 | 1762 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CONEYPLAZ | Coney Island Steeplechase Plaza | NEIGHBORHOOD REVITALIZATION | 213 | ED-0404 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CONEY ISLAND STEEPLECHASE PLAZA | 2019 | 34582 | 29717.99 | 89 | 0 | 0 | 0 | 0 | 0 | 29806.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CONEYSIGN | Coney Island Signs | MISCELLANEOUS | 200 | ED-0075 |  |  | ACQUISITION, SITE DEVELOPMENT, CONSTRUCTION & RECONSTRUCTION, CITYWIDE -- CONEY ISLAND SIGNS | 2019 | 0 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CONEYWEST | Coney Island West | MISCELLANEOUS | 200 | SE-0002K ED-0075 SE-0200K WM-0006 WM-0001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CONEY ISLAND WEST | 2019 | 181000 | 101979.81 | 17341 | 12162 | 44162 | 37750 | 0 | 0 | 213394.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CWFSHOMEP | New York City Ferry - Homeport | WATERFRONT DEVELOPMENT | 200 | ED-0409 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | HOMEPORT PIER AT THE BROOKLYN NAVY YARD FOR CITYWIDE FERRY SERVICE | 2019 | 41033 | 42517.24 | 7746 | 0 | 0 | 0 | 0 | 0 | 50263.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | DEO-OWLS | Owls Head Pier Emergency Dredging | PLANT UPGRADING AND RECONSTRUCTION | 200 | WP-0112 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | OWLS HEAD PIER EMERGENCY DREDGING | 2019 | 2200 | 1349.03 | 0 | 0 | 0 | 0 | 0 | 851 | 2200.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | DTBKFLATM | Downtown Brooklyn Redevelopment - Flatbush Myrtle Street | MISCELLANEOUS | 202 | ED-0075 HW-1684 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | DOWNTOWN BROOKLYN: FLATBUSH MYRTLE STREETSCAPE | 2019 | 13000 | 24721.61 | 0 | 7 | 0 | 0 | 0 | 167 | 24895.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | DTBKLYNDV | Downtown Brooklyn Redevelopment | COMMERCIAL DEVELOPMENT | 202 | ED-0075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BROOKLYN | REDEVELOPMENT | 2019 | 57239 | 16495.35 | 0 | 0 | 0 | 0 | 0 | 8341 | 24836.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | DTBKLYNFM | Downtown Brooklyn Redevelopment - Fulton Mall | COMMERCIAL DEVELOPMENT | 203 | HW-0001K ED-0075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | FULTON MALL | 2019 | 11150 | 17798.77 | 0 | 908 | 0 | 0 | 0 | 1352 | 20058.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | EASTNYINC | East New York Incubator Improvements | MISCELLANEOUS | 200 | ED-0404 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | EAST NEW YORK INCUBATOR IMPROVEMENTS | 2019 | 1500 | 318.36 | 1182 | 0 | 0 | 0 | 0 | 0 | 1500.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | ERFERRY | East River Ferry Route | WATERFRONT DEVELOPMENT | 201 | ED-0075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | GREENPOINT & NORTH WILLIAMSBURG FERRIES | 2019 | 4900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1852 | 0 | 0 | 0 | 0 | 1852
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | FLATNOST | Flatbush - Nostrand Avenue Streetscapes | MISCELLANEOUS | 200 203 208 209 | ED-D384 HW-1684 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | FLATBUSH - NOSTRAND AVENUE STREETSCAPES | 2019 | 4500 | 3923.55 | 0 | 0 | 0 | 0 | 0 | 633 | 4556.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | FLATREV | Flatbush Revitalization | NEIGHBORHOOD REVITALIZATION |  | ED-0075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | FLATBUSH REVITALIZATION | 2019 | 50000 | 52549.99 | 0 | 0 | 0 | 0 | 450 | 0 | 52999.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | FREIGHTSP | Freight NYC - Sunset Park Rail | MISCELLANEOUS | 200 | ED-0410 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | FREIGHT NYC - SUNSET PARK RAIL - 100K JOBS PLAN | 2019 | 15800 | 0 | 0 | 0 | 0 | 5719 | 0 | 10080 | 15799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | GK26W5-05 | DSGN & CONS OF ROW GI IN 26W-005 | GREEN INFRASTRUCTURE PROGRAM | 200 | WP-0169 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | GI - DESIGN AND CONSTRUCTION OF RIGHTOF WAY BIOSWALES AND STORMAWATERGREENSTREETS AT CSO TRIBUTARY AREA 26W-005 IN BROOKLYN | 2019 | 45271 | 22458.22 | 20330 | 100000 | 0 | 0 | 0 | 0 | 142788.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | GKCI05-01 | GI - DSGN & CONS OF ROW GREEN INFRASTRUCTURE IN CI-005 PH 1 | GREEN INFRASTRUCTURE PROGRAM | 200 | WP-0169 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | GI - DSGN & CONS OF RIGHT OF WAY GREEN INFRASTRUCTURE IN CI-005, PHASE 1 | 2019 | 11228 | 0 | 6848 | 6000 | 0 | 3741 | 0 | 0 | 16589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | GKCI05-02 | GI - DSGN & CONS OF ROW GREEN INFRASTRUCTURE IN CI-005 PH 2 | GREEN INFRASTRUCTURE PROGRAM | 200 | WP-0169 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | GI - DSGN & CONS OF RIGHT OF WAY GREEN INFRASTRUCTURE IN CI-005, PHASE 2 | 2019 | 13501 | 0 | 7843 | 7000 | 0 | 3741 | 0 | 0 | 18584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | GKCI05-03 | GI - DSGN & CONS OF ROW GREEN INFRASTRUCTURE IN CI-005 PH 3 | GREEN INFRASTRUCTURE PROGRAM | 200 | WP-0169 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | GI - DSGN & CONS OF RIGHT OF WAY GREEN INFRASTRUCTURE IN CI-005, PHASE 3 | 2019 | 11404 | 0 | 6872 | 6000 | 510 | 3741 | 0 | 0 | 17123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | GRAFNYC | Graffiti Free Customized Cargo Truck Purchase | MISCELLANEOUS | 200 | ED-0075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | GRAFFITI FREE CARGO TRUCK PURCHASE | 2019 | 1540 | 1443.45 | 0 | 97 | 0 | 0 | 0 | 0 | 1540.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | GREEN | Green Infrastructure 26W | GREEN INFRASTRUCTURE PROGRAM | 200 | WP-0169 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | GREEN INFRASTRUCTURE 26W | 2019 | 48855 | 41670.87 | 2888 | 9000 | 0 | 0 | 0 | 0 | 53558.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | GREENPNT | Greenpoint Waterfront Esplanade | WATERFRONT DEVELOPMENT | 201 | P-0839 ED-0401 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BROOKLYN | GREENPOINT ESPLANADE | 2019 | 3470 | 9789.2 | 0 | 0 | 0 | 0 | 219 | 0 | 10008.2 | 1502.07 | 0 | 0 | 0 | 0 | 370 | 37 | 1909.07
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | HBPD200KA | PED BRIDGE - WEST 8 ST (BIN 2269260) | COMMUNITY DEVELOPMENT | 213 | HB-0215 HW-0001K | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CONEY ISLAND - WEST 8TH ST PEDESTRIAN BRIDGE DEMOLITION | 2019 | 9335 | 3319.6 | -37 | 0 | 0 | 37 | 0 | 0 | 3319.6 | 3152.83 | 0 | 0 | 0 | 0 | 0 | 42 | 3194.83
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | HHNC004 | COALITION FOR THE HOMELESS- BUILDING RENOVATION (2ND FLOOR) | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-D025 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | COALITION FOR THE HOMELESS- BUILDING RENOVATION (2ND FLOOR) | 2019 | 693 | 0 | 624 | 69 | 0 | 0 | 0 | 0 | 693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | METBIDWAY | FA - Metrotech BID Wayfinding | NEIGHBORHOOD REVITALIZATION | 202 | ED-D384 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | FA - METROTECH BID WAYFINDING | 2019 | 1250 | 409.53 | 0 | 0 | 0 | 0 | 400 | 0 | 809.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | MILLREHAB | Mill Basin - Waterfont Rehabilitation | MISCELLANEOUS | 200 | ED-0409 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | MILL BASIN WATERFRONT REHABILITATION | 2019 | 3250 | 709.74 | 2540 | 0 | 0 | 0 | 0 | 0 | 3249.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | MINYRESIL | MiNY Resiliency | MISCELLANEOUS | 200 | ED-0075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | MINY RESILIENCY | 2019 | 33900 | 0 | 5000 | 0 | 15000 | 13900 | 0 | 0 | 33900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | MOOREROOF | Moore Street Market Roof Rehabilitation | MARKET DEVELOPMENT | 200 | ED-K384 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | MOORE STREET MARKET ROOF REHABILITATION | 2019 | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | MOOREST | Moore Street Market | MISCELLANEOUS | 201 | ED-K075 ED-D384 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | MOORE STREET MARKET PROJECT | 2019 | 200 | 541.94 | 0 | 500 | 0 | 157 | 0 | 0 | 1198.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | MYRTLEBK | Myrtle Ave Acquisition | MISCELLANEOUS | 200 202 203 204 | ED-D384 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | MYRTLE AVE COMMERCIAL REVITALIZATION & DEVELOPMENT | 2019 | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-BROAD | NDF - ENY IBZ Infrastructure - Broadband | NEIGHBORHOOD REVITALIZATION | 200 | ED-0384 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NDF-ENY IBZ BROADBAND | 2019 | 2500 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-CCIMP | NDF - Commercial Corridor Improvements | NEIGHBORHOOD REVITALIZATION | 200 | ED-0384 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NDF - COMMERCIAL CORRIDOR IMPROVEMENTS | 2019 | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-IBMOD | NDF - ENY Industiral Buiding Modernization and Activation | NEIGHBORHOOD REVITALIZATION | 200 | ED-0384 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | INDUSTRIAL BUILDING MODERNIZATION AND ACTIVATION | 2019 | 4500 | 604.81 | 3895 | 0 | 0 | 0 | 0 | 0 | 4499.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | NEWKIRK | FA - Newkirk Plaza Reconstruction | MISCELLANEOUS | 214 | ED-D075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | NEWKIRK | NEWKIRK PLAZA | 2019 | 463 | 463 | 0 | 0 | 0 | 0 | 50 | 0 | 513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | NOSTRAND | FA - Nostrand Avenue Merchants Assoc. (Flatbush Gateway) | COMMERCIAL DEVELOPMENT | 209 | ED-D384 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BOROWIDE | COMMERCIAL REVITALIZATION | 2019 | 850 | 0 | 0 | 0 | 0 | 0 | 850 | 0 | 850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | NWBURGFL | North Williamsburg Ferry Landing | WATERFRONT DEVELOPMENT | 201 | ED-0075 ED-D401 FA-0027 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CONSTRUCTION OF BARGE FERRY LANDING AT THE NORTH 5TH ST PIER IN NORTHWILLIAMSBURG, BROOKLYN | 2019 | 1176 | 535.93 | 0 | 42 | 0 | 1 | 0 | 0 | 578.93 | 1711.73 | 0 | 220 | 0 | 0 | 0 | 0 | 1931.73
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | NYCFHP2 | NYC Ferry Homeport 2 | MISCELLANEOUS | 200 | ED-0409 |  |  | HOMEPORT 2 AT ATLANTIC BASIN | 2019 | 0 | 0 | 10358 | 30000 | 24642 | 0 | 0 | 0 | 65000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-213CNTR | Seaside Park and Community Arts Center Acquisitions | MISCELLANEOUS | 200 | ED-0075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | SEASIDE PARK AND COMMUNITY ARTS CENTER ACQUISITIONS | 2019 | 17168 | 16100 | 1068 | 0 | 0 | 0 | 0 | 0 | 17168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-2GPWB07 | GPWB - Box Street and Newtown Barge Parks | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 201 | P-0839 WP-0283 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | DUPONT ST - BKLYN | GPWB - DUPONT ST NEWTOWN BARGE PLGRD | 2019 | 10670 | 2835.04 | 891 | 0 | 0 | 0 | 0 | 0 | 3726.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-2GPWB08 | GPWB - 65 Commercial St Soccer Pk-MTA Reloc. & Park Develop. | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 201 | P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | 65 COMMERCIAL ST - BKLYN | GPWB - 65 COMMERCIAL ST SOCCER PK | 2019 | 15400 | 7856.11 | 2043 | 100 | 0 | 0 | 0 | 0 | 9999.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-2GPWB24 | GPWB- Bayside Demolition | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 201 | P-0839 |  | GREENPOINT WILLIAMSBURG SECTION OF BROOKLYN | BAYSIDE DEMOLITION | 2019 | 22000 | 495.3 | 13500 | 0 | 0 | 8005 | 0 | 0 | 22000.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-2GPWBOX | GPWB - Box Street Park | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 201 | P-1018 P-0839 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CONSTRUCTION OF BOX STREET PARK | 2019 | 18000 | 0 | 0 | 5735 | 11000 | 0 | 0 | 0 | 16735 | 430.2 | 4570 | 0 | 0 | 0 | 0 | 0 | 5000.2
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-2GPWNB | GPWB - Newtown Barge Park | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 201 | P-0839 WP-0283 P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NEWTOWN BARGE PARK | 2019 | 20608 | 15173.45 | 953 | 0 | 0 | 0 | 0 | 0 | 16126.45 | 4234.29 | 1266 | 0 | 0 | 0 | 0 | 0 | 5500.29
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER69TH | Pier Substructure Rehabilitation - 69th St. Pier | WATERFRONT DEVELOPMENT | 210 | ED-0409 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  |  | 2019 | 6569 | 5200.93 | 0 | 0 | 0 | 0 | 0 | 0 | 5200.93 | 0 | 0 | 0 | 0 | 124 | 600 | 0 | 724
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PROSPPLC | Prospect Park Lakeside Center | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 206 207 208 209 214 200 | P-0245K P-D017 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | PROSPECT PARK LAKESIDE CENTER - ICE RINK AND LANDSCAPING | 2019 | 31313 | 48087.18 | 0 | 0 | 0 | 48 | 0 | 0 | 48135.18 | 2487 | 0 | 0 | 0 | 0 | 0 | 0 | 2487
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV230-SHA | FA - WCS - New York Aquarium | NEW TECHNOLOGY AND CONSTRUCTION | 213 | PV-0230 PV-K230 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BOARDWALK AT WEST 8TH STREET & SURF AVENUE, BROOKLYN NY, 11224 | CONSTRUCTION OF NEW SHARK EXHIBIT ON AQUARIUM GROUNDS | 2019 | 37735 | 117650.84 | 0 | 1250 | 0 | 269 | 0 | 0 | 119169.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV264CINE | BAM - BAM South Site Theaters | MISCELLANEOUS | 299 | PV-0264 PV-K264 PV-D264 |  |  | BAM - BAM SOUTH SITE THEATERS | 2019 | 7500 | 1345.16 | 0 | 19008 | 0 | 0 | 0 | 0 | 20353.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV264HART | Brooklyn Academy of Music (BAM) | ESSENTIAL RECONSTRUCTION OF FACILITIES | 200 | PV-D264 PV-K264 PV-0264 PV-0467 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BAM DEVELOPMENT AND EXPANSION OF HARVEY THEATRE INCLUSING ELEVATOR TOGALLERY, EXTENSION OF LOBBY FOR FOOD SERVICE, EXPANDED REST ROOMS, STORAGE SPACE AND OFFICES. | 2019 | 4426 | 0 | 0 | 22398 | 0 | 0 | 0 | 0 | 22398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV467SOST | DBCD South Site Cultural Condo Fitout | ESSENTIAL RECONSTRUCTION OF FACILITIES | 202 | PV-0467 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 20 LAFAYETTE AVENUE BROOKLYN | DBCD SOUTH SITE CULTURAL CONDO FITOUT OF COMMON AREAS | 2019 | 1000 | 895.55 | 0 | 7524 | 0 | 0 | 0 | 0 | 8419.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV467STFO | 651 Arts South Site Studios Fitout | ESSENTIAL RECONSTRUCTION OF FACILITIES | 202 | PV-0467 PV-D467 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 20 LAFAYETTE AVENUE BROOKLYN | 651 ARTS SOUTH SITE STUDIOS FITOUT | 2019 | 7750 | 952.3 | 0 | 12798 | 0 | 0 | 0 | 0 | 13750.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PWKNTH | Northside Town Hall | MISCELLANEOUS CONSTRUCTION | 201 | PW-D007 PW-K007 |  |  | NORTHSIDE TOWN HALL | 2019 | 0 | 0 | 1092 | 0 | 0 | 0 | 0 | 0 | 1092 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | RE25HC | RECONSTRUCT BULKHEAD 1ST AVE AND 52ND ST, BKLYN | REHABILITATION OF WATERFRONT PROPERTIES | 201 | RE-0025 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RECONSTRUCT BULKHEAD 1ST AVE AND 52ND ST, BROOKLYN | 2019 | 4281 | 2537.51 | 0 | 0 | 463 | 863 | 0 | 0 | 3863.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | REDHOOK | Red Hook Library | MISCELLANEOUS | 206 200 | LB-D104 LB-0104 |  |  | RED HOOK LIBRARY | 2019 | 2835 | 754.49 | 0 | 0 | 7594 | 0 | 0 | 0 | 8348.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND2601C | CIH: RELOCATE OUTPATIENT RADIOLOGIC IMAGING SERVICES | ROUTINE RECONSTRUCTION | 213 | HO-0214 |  | 2601 OCEAN PARKWAY, BROOKLYN, NY 11235 | RENOVATE EXISTING SPACE ON THE 5TH FLOOR OF THE MAIN HOSPITAL BUILDING TO RELOCATE OUTPATIENT RADIOLOGIC IMAGING SERVICES FROM THE FIRST FLOOR OF THE BUILDING THAT WAS DESTROYED BY SEVERE WATER DAMAGES DUE TOEXPOSURE TO SALT WATER FROM HURRICANE SANDY AT CONEY ISLAND HOSPITAL. | 2019 | 7700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7640.09 | 386 | 1373 | 0 | 0 | 0 | 0 | 9399.09
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND2603C | CIH: RENOVATE VACANT SPACE ON FIRST FL MAIN HOSPITAL BLG. | ROUTINE RECONSTRUCTION | 213 | HO-0214 |  | 2601 OCEAN PARKWAY, BROOKLYN, NY 11235 | RENOVATE APPROXIMATELY 11,000 SQ. FT. OF VACANT SPACE ON THE FIRST FLOOR OF THE MAIN HOSPITAL BUILDING TO CREATE OFFICE SPACE THAT WAS DESTROYED BY SEVERE WATER DAMAGES DUE TO EXPOSURE TO SALT WATER FROM HURRICANE SANDY AT CONEY ISLAND HOSPITAL. | 2019 | 3876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6186.81 | 175 | 2013 | 0 | 0 | 0 | 0 | 8374.81
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND2605 | CIH: DESIGN & CONSTRUCTION MANAGEMENT FOR HOSPITAL CAMPUS | MISCELLANEOUS | 200 | HO-0214 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CONEY ISLAND HOSPITAL DESIGN AND CONSTRUCTION | 2019 | 1084343 | 0 | 0 | 0 | 68198 | 0 | 0 | 0 | 68198 | 70643.9 | 199488 | 112006 | 155512 | 105225 | 71268 | 0 | 714142.9
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB3416 | BNYDC - PW 3416 - Berth 6 Concrete Slab | INDUSTRIAL DEVELOPMENT | 200 | ED-0319 |  |  | PW 3416 - CONCRETE SLAB | 2019 | 335 | 0 | 12 | 22 | 0 | 0 | 0 | 0 | 34 | 0 | 107 | 194 | 9 | 0 | 0 | 0 | 310
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB3820 | BNYDC - PW 3820 - Substations - Buildings 127, 275, 293 | INDUSTRIAL DEVELOPMENT | 200 | ED-0319 |  |  | PW 3820 - SUBSTATIONS - BUILDINGS 127, 275, 293 | 2019 | 3191 | 0 | 60 | 133 | 0 | 0 | 0 | 0 | 193 | 0 | 542 | 2456 | 0 | 0 | 0 | 0 | 2998
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4225 | BNYDC - PW 4225 Dry-Dock /Caisson Gate #5,#6, Pump Well #156 | INDUSTRIAL DEVELOPMENT | 200 | ED-0319 |  |  | PW 4225 - DRY-DOCK /CAISSON GATE #5,#6, PUMP WELL #156 - RESTORATION AND MITIGATION | 2019 | 15897 | 0 | 189 | 894 | 0 | 0 | 0 | 0 | 1083 | 0 | 1699 | 13115 | 0 | 0 | 0 | 0 | 14814
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4270 | BNYDC - PW 4270 - BNYDC SITE-WIDE CONDUIT - PAAP | INDUSTRIAL DEVELOPMENT | 200 | ED-0319 |  |  | PW 4270 - BNYDC SITE-WIDE CONDUIT - PAAP - RESTORATION AND MITIGATION | 2019 | 1184 | 0 | 16 | 62 | 0 | 0 | 0 | 0 | 78 | 0 | 145 | 961 | 0 | 0 | 0 | 0 | 1106
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4271 | BNYDC - PW 4271 - Substations No. 292 and No. 542 | INDUSTRIAL DEVELOPMENT | 200 | ED-0319 |  |  | PW 4271 - SUBSTATIONS NO. 292 AND NO. 542 - RESTORATION AND MITIGATION | 2019 | 3071 | 0 | 30 | 170 | 0 | 0 | 0 | 0 | 200 | 0 | 274 | 2597 | 0 | 0 | 0 | 0 | 2871
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4273 | BNYDC - PW 4273 - Steam Generating Back-Up Plant - Bldg #41A | INDUSTRIAL DEVELOPMENT | 200 | ED-0319 |  |  | PW 4273 - STEAM GENERATING BACK-UP PLANT - BLDG #41A - RESTORATION AND MITIGATION | 2019 | 1441 | 0 | 23 | 74 | 0 | 0 | 0 | 0 | 97 | 0 | 203 | 1141 | 0 | 0 | 0 | 0 | 1344
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4274 | BNYDC - PW 4274 - Dry Dock 1 | INDUSTRIAL DEVELOPMENT | 200 | ED-0319 |  |  | PW 4274 - DRY DOCK 1 | 2019 | 2931 | 0 | 116 | 178 | 0 | 0 | 0 | 0 | 294 | 0 | 1039 | 1598 | 95 | 0 | 0 | 0 | 2732
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4275 | BNYDC - PW 4275 - SUB STATION G BUILDING 386 | INDUSTRIAL DEVELOPMENT | 200 | ED-0319 |  |  | PW 4275 - SUB STATION G BUILDING 386 - RESTORATION AND MITIGATION | 2019 | 14243 | 0 | 190 | 707 | 0 | 0 | 0 | 0 | 897 | 0 | 1710 | 11636 | 0 | 0 | 0 | 0 | 13346
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4307 | BNYDC - PW 4307 Substation B | INDUSTRIAL DEVELOPMENT | 200 | ED-0319 |  |  | PW 4307 - SUBSTATION B - RESTORATION AND MITIGATION | 2019 | 8184 | 0 | 95 | 423 | 0 | 0 | 0 | 0 | 518 | 0 | 857 | 6809 | 0 | 0 | 0 | 0 | 7666
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4388 | BNYDC - PW 4388 - Boiler Replacement | INDUSTRIAL DEVELOPMENT | 200 | ED-0319 |  |  | PW 4388 - BOILER REPLACEMENT - RESTORATION AND MITIGATION | 2019 | 1079 | 0 | 30 | 38 | 0 | 0 | 0 | 0 | 68 | 0 | 268 | 743 | 0 | 0 | 0 | 0 | 1011
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4582 | BNYDC - PW 4582 - BERTH 9,9A | INDUSTRIAL DEVELOPMENT | 200 | ED-0319 |  |  | PW 4582 - BERTH 9,9A - RESTORATION AND MITIGATION | 2019 | 10502 | 0 | 21 | 676 | 0 | 0 | 0 | 0 | 697 | 0 | 193 | 9612 | 0 | 0 | 0 | 0 | 9805
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4583 | BNYDC - PW 4583 - BERTH 10 & 10A | INDUSTRIAL DEVELOPMENT | 200 | ED-0319 |  |  | PW 4583 - BERTH 10 & 10A - RESTORATION AND MITIGATION | 2019 | 11538 | 0 | 15 | 708 | 0 | 0 | 0 | 0 | 723 | 0 | 136 | 10679 | 0 | 0 | 0 | 0 | 10815
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDBCT | EDC - Hurricane Sandy - BCT Repairs | MISCELLANEOUS | 206 207 | ED-0404 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | REPAIRS AT THE BCT PROJECT AS A RESULT OF HURRICANE SANDY | 2019 | 3000 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 2700 | 0 | 2700
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDBNYAM | BNYDC Hurricane Sandy Asset Management Repairs | INDUSTRIAL DEVELOPMENT | 200 | ED-0319 |  |  | BROOKLYN NAVY YARD - HURRICANE SANDY RECOVERY LOCAL MATCH | 2019 | 3610 | 0 | 0 | 4545 | 0 | 0 | 0 | 0 | 4545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDBNYEC | BNYDC Hurricane Sandy Electrical Repairs | MISCELLANEOUS | 200 | ED-0319 |  |  | ELECTRICAL REPAIRS IN THE BROOKLYN NAVY YARD AS A RESULT OF HURRICANESANDY | 2019 | 3100 | 0 | 161 | 159 | 0 | 0 | 0 | 0 | 320 | 1118.29 | 1672 | 2307 | 0 | 0 | 0 | 0 | 5097.29
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDBNYWF | BNYDC Hurricane Sandy Waterfront Repair | MISCELLANEOUS | 200 | ED-0319 |  |  | WATERFRONT REPAIRS DUE TO HURRICANE SANDY | 2019 | 24850 | 0 | 205 | 1067 | 0 | 0 | 0 | 0 | 1272 | 0 | 680 | 0 | 0 | 0 | 0 | 0 | 680
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDCD9 | HARBOR CHARLIE | POLICE FACILITIES | 200 | PO-0079 |  |  | HARBOR ELECTRICAL | 2019 | 5368 | 0 | 0 | 572 | 0 | 0 | 0 | 0 | 572 | 0 | 0 | 5141 | 0 | 0 | 0 | 0 | 5141
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDG3BAT | FEMA 428 Projects - Group 3 - Brooklyn Army Terminal BAT | MISCELLANEOUS | 200 | ED-0075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | FEMA 428 PROJECTS - GROUP 3 - BROOKLYN ARMY TERMINAL BAT | 2019 | 6557 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1006.24 | 1000 | 4551 | 0 | 0 | 0 | 0 | 6557.24
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDG3BSH | FEMA 428 Projects - Group 3 - BUSH Terminal | MISCELLANEOUS | 200 | ED-0075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | FEMA 428 PROJECTS - GROUP 3 RESILIENCY PROJECTS - BUSH TERMINAL | 2019 | 13606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1045.18 | 2000 | 10561 | 0 | 0 | 0 | 0 | 13606.18
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDRBCT | FA Resiliency - BCT | MISCELLANEOUS | 200 | FA-0027 |  |  | FA RESILIENCY - BCT | 2019 | 10000 | 0 | 384 | 2000 | 116 | 0 | 0 | 0 | 2500 | 0 | 1154 | 2000 | 4346 | 0 | 0 | 0 | 7500
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDYNYA | WCS - New York Aquarium Sandy Renovation | NEW TECHNOLOGY AND CONSTRUCTION | 213 | PV-0230 PV-0467 |  |  | SANDY RELATED RENOVATION/RESTORATION - WCS NEW YORK AQUARIUM | 2019 | 111256 | 11497.87 | 0 | 11057 | 0 | 0 | 0 | 0 | 22554.87 | 85571.74 | 99502 | 0 | 0 | 0 | 0 | 0 | 185073.74
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SBMT39P | South Brooklyn Marine Terminal 39th Street Pier Rehab | WATERFRONT DEVELOPMENT | 207 | ED-0409 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | SBMT 39TH STREET PIER | 2019 | 725 | 14907.84 | 0 | 0 | 3417 | 0 | 0 | 0 | 18324.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SBMTAUTO | SBMT - Axis | WATERFRONT DEVELOPMENT | 207 | ED-0404 ED-0075 ED-0380 SE-0200K WM-0001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | SOUTH BROOKLYN MARINE TERMINAL | 2019 | 24000 | 48466.23 | 0 | 192 | 0 | 0 | 0 | 25 | 48683.23 | 19808.61 | 0 | 0 | 0 | 0 | 0 | 1492 | 21300.61
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SBMTFRT | Freight - SBMT 33rd Street Pier | MISCELLANEOUS | 200 | ED-0404 |  |  | FREIGHT - SBMT 33RD STREET PIER | 2019 | 39400 | 0 | 0 | 0 | 13000 | 6560 | 3000 | 16840 | 39400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SNSTFRGH2 | Sunset Park Areawide Infrastructure Improvements | NEIGHBORHOOD REVITALIZATION | 200 | ED-0384 |  |  | SUNSET PARK IMPROVEMENTS - AREA IMPROVEMENTS | 2019 | 37500 | 2815.5 | 4684 | 1000 | 1000 | 21500 | 6500 | 0 | 37499.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SPUDBARGE | 69th Street Pier Reconstruction - Spud Barge | MISCELLANEOUS | 207 | ED-D075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | 69TH STREET PIER RECONSTRUCTION-SPUD BARGE | 2019 | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | STRAND2 | Strand Theater Rehab | MISCELLANEOUS | 202 | ED-0075 |  |  | STRAND THEATER REHAB | 2019 | 2000 | 1898.22 | 0 | 102 | 0 | 0 | 0 | 0 | 2000.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SUNSETPAR | Sunset Park Waterfront Redevelopment | WATERFRONT DEVELOPMENT | 207 | ED-0075 S-0216 P-D017 ED-D075 ED-0410 P-1245 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  |  | 2019 | 1382 | 21845.59 | 7747 | 0 | 0 | 0 | 0 | 0 | 29592.59 | 26095.08 | 705 | 0 | 0 | 0 | 0 | 0 | 26800.08
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SUNSETWIF | Sunset Park 5th Avenue Wired - Sunset Park BID Free WiFi | NEIGHBORHOOD REVITALIZATION | 200 | ED-K075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | SUNSET PARK BID WIFI | 2019 | 35 | 0 | 0 | 0 | 35 | 0 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | URBANROOF | URBAN UNION ASSEMBLY--CONSTRUCTION OF ROOF GARDEN. | MISCELLANEOUS | 200 | PW-D005 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | URBAN UNION ASSEMBLY--CONSTRUCTION OF ROOF GARDEN. | 2019 | 1000 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | WILGARAGE | Willoughby Parking Garage | MISCELLANEOUS | 202 | ED-K075 ED-D075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | WILLOUGHBY PARKING GARAGE | 2019 | 2200 | 0 | 3200 | 0 | 0 | 0 | 0 | 0 | 3200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | CYPRESS | Cypress Plaza Mews - 701 Van Siclen Ave, Bklyn | COMMERCIAL DEVELOPMENT | 205 | ED-D075 |  | 701 VAN SICLEN AVE, BROOKLYN | MIXED INCOME PROGRAM (FORMERLY FOR CONSTRUCTION OF MINI-MALL) | 2019 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM06BOBK | BOULEVARD BRICKWORK | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 205 | HA-0001 |  | LINDEN BLVD, ASHFORD ST, WORTMAN AVE, SCHENCK AVE | BRICKWORK | 2019 | 0 | 4275.77 | 2210 | 0 | 0 | 0 | 0 | 0 | 6485.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM10WYCR | WYCKOFF GARDENS COMMUNITY ROOM | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 206 | HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | WYCKOFF GARDENS COMMUNITY ROOM | 2019 | 450 | 0 | 641 | 0 | 0 | 0 | 0 | 0 | 641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM12UPDO | UNITY PLAZA COMMUNITY CENTER UPGRADE | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 205 | HA-D001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | BUILD DOME FOR RECREATION FACILITY | 2019 | 1500 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM12WYCC | WYCKOFF GARDENS COMMUNITY CENTER UPGRADE | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 206 | HA-D001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | UPGRADES TO INCLUDE CLASSROOMS, OPEN SHOP AREA AND OFFICES | 2019 | 150 | 0 | 810 | 0 | 0 | 0 | 0 | 0 | 810 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM13BRKT | BREUKELEN HOUSES KITCHENS, WET WALLS AND PLUMBING | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 218 | HA-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | RENOVATE KITCHENS AT BREUKELEN HOUSES | 2019 | 20900 | 0 | 19091 | 0 | 0 | 0 | 0 | 0 | 19091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM13SURF | SUMNER HOUSES ROOF REPLACEMENT | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 203 | HA-0001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ROOF REPLACEMENT | 2019 | 11476 | 9376.05 | 1057 | 0 | 0 | 0 | 0 | 0 | 10433.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM14GOCC | GOWANUS COMMUNITY CENTER RENOVATIONS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 206 | HA-D001 |  |  | COMMUNITY CENTER RENOVATIONS | 2019 | 150 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM14KBEY | KINGSBOROUGH AND EXTENSION ENERGY IMPROVEMENTS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 208 | HA-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | ENERGY UPGRADES | 2019 | 2290 | 0 | 3302 | 0 | 0 | 0 | 0 | 0 | 3302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM14RHSR | RED HOOK SENIOR CENTER RENOVATION | DEPARTMENT FOR THE AGING BUILDING RECONSTRUCTION | 206 | AG-D001 |  |  | RENOVATE SENIOR CENTER | 2019 | 1800 | 1645.37 | 155 | 0 | 0 | 0 | 0 | 0 | 1800.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15COBC | CONEY ISLAND HOUSES I (SITE 4 & 5) BASKETBALL COURT RENO | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 213 | HA-D001 |  |  | RENOVATE BASKETBALL COURT | 2019 | 75 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15GNCC | GOWANUS COMMUNITY CENTER RENOVATIONS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 206 | HA-D001 |  |  | RENOVATE COMMUNITY CENTER | 2019 | 325 | 0 | 325 | 0 | 0 | 0 | 0 | 0 | 325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15GOGR | GOWANUS HOUSES BASKETBALL COURT AND PLAY AREA | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 206 | HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BASKETBALL COURT AND PLAY AREA | 2019 | 150 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15ODPA | O'DWYER GARDENS PLAYGROUND UPGRADES | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 213 | HA-D001 |  |  | PLAYGROUND UPGRADE | 2019 | 100 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15WAPA | 572 WARREN STREET PLAY AREA UPGRADE | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 206 | HA-D001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | UPGRADE PLAY AREA | 2019 | 100 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15WYPA | WYCKOFF GARDENS TODDLER PLAY AREA UPGRADE | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 206 | HA-D001 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES |  | TODDLER PLAY AREA UPGRADE | 2019 | 150 | 0 | 210 | 0 | 0 | 0 | 0 | 0 | 210 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16BES9 | BERRY STREET SOUTH 9TH STREET HOUSES SECURITY UPGRADES | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 201 | HA-D001 |  |  | SECURITY UPGRADES | 2019 | 125 | 0 | 90 | 0 | 0 | 0 | 0 | 0 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16GWSU | GOWANUS HOUSES SECURITY UPGRADES | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 206 | HA-D001 |  |  | SECURITY UPGRADES | 2019 | 200 | 0 | 172 | 0 | 0 | 0 | 0 | 0 | 172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16HPBR | HOPE GARDENS INSTALLATION OF BOILERS AND RELATED EQUIPMENT | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 204 | HA-D001 HA-0001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | INSTALLATION AND REPAIRS OF BOILERS AND RELATED EQUIPMENT | 2019 | 500 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16HWRD | HOWARD HOUSES TENANTS COUNCIL - SECURITY CAMERAS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 216 | HA-K001 |  |  | HOWARD HOUSES TENANTS COUNCIL - SECURITY CAMERAS | 2019 | 100 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16ITGR | INDEPENDENCE TOWERS GROUNDS IMPROVEMENTS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 201 | HA-D001 |  |  | GROUNDS IMPROVEMENTS | 2019 | 300 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16NHGR | NOSTRAND HOUSES PLAYGROUND RENOVATION | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 215 | HA-D001 |  |  | PLAYGROUND RENOVATION | 2019 | 250 | 0 | 710 | 0 | 0 | 0 | 0 | 0 | 710 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16SURF | SURF GARDENS DEVELOPMENT - PLAYGROUND RENOVATION | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 200 | HA-K001 |  |  | SURF GARDENS DEVELOPMENT - PLAYGROUND RENOVATION | 2019 | 250 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16TWGR | TAYLOR STREET - WYTHE AVENUE GROUNDS IMPROVEMENTS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 201 | HA-D001 |  |  | GROUNDS IMPROVEMENTS | 2019 | 100 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16WIPL | WILLIAMSBURG HOUSES PLAYGROUND RENOVATION | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 201 | HA-D001 |  |  | PLAYGROUND RENOVATION | 2019 | 300 | 0 | 650 | 0 | 0 | 0 | 0 | 0 | 650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM17INSS | INDEPENDENCE TOWERS COMMUNITY CENTER SOUND STUDIO | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 201 | HA-D001 |  |  | CREATE SOUND STUDIO | 2019 | 100 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM17NSTV | NOSTRAND HOUSES SECURITY CAMERAS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 215 | HA-D001 |  |  | INSTALL SECURITY CAMERAS | 2019 | 250 | 204.46 | 46 | 0 | 0 | 0 | 0 | 0 | 250.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM17SBTV | Sheepshead Bay Houses -- Beautification/Security Cameras | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 215 | HA-D001 |  |  | INSTALLATION OF SECURITY CAMERAS AND BEAUTIFICATION AT SHEEPSHEAD BAY | 2019 | 250 | 201.67 | 49 | 0 | 0 | 0 | 0 | 0 | 250.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM17WISR | WHITMAN HOUSES - WILLOUGHBY SENIOR CENTER HVAC | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 202 | HA-K001 |  |  | UPGRADE HVAC SYSTEM | 2019 | 100 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM17WPSC | WILLIAMS PLAZA SECURITY CAMERAS, INTERCOMS, DOORS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 201 | HA-D001 |  |  | NSTALL SECURITY CAMERAS, INTERCOMS, DOORS | 2019 | 100 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18ATBC | ATLANTIC TERMINAL BASKETBALL COURT RENOVATION | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 202 | HA-D001 |  |  | BASKETBALL COURT RENOVATION | 2019 | 400 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18BREV | Brevoort Resident Association - Coliseum Repairs and CCTVs | LOW TO MODERATE INCOME PUBLIC HOUSING CONSTRUCTION | 200 | HA-K001 |  |  | BREVOORT RESIDENT ASSOCIATION - COLISEUM REPAIRS AND CCTVS | 2019 | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18BSVB | BROWNSVILLE AND SARATOGA VILLAGE BOILER REPAIR | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 200 | HA-0001 |  |  | BROWNSVILLE AND SARATOGA VILLAGE BOILER REPAIR | 2019 | 0 | 0 | 12600 | 0 | 0 | 0 | 0 | 0 | 12600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CHBW | CYPRESS HILLS BOILER WORK | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 200 | HA-0001 |  |  | BOILER REPAIR AT CYPRESS HILLS | 2019 | 10500 | 0 | 10500 | 0 | 0 | 0 | 0 | 0 | 10500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18FGSI | FARRAGUT HOUSES SECURITY CAMERAS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 202 | HA-D001 |  |  | SECURITY CAMERAS | 2019 | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18FSBA | Breukelen Bathrooms, Kitchens, and Gas Risers | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 200 | HA-0001 |  |  | BREUKELEN BATHROOMS, KITCHENS, AND GAS RISERS | 2019 | 0 | 0 | 31000 | 0 | 0 | 0 | 0 | 0 | 31000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18HGCC | HOPE GARDENS COMMUNITY CENTER--MODERNIZE GYM. | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 204 | HA-K001 HA-D001 |  |  | RENOVATION OF THE GYM AT HOPE GARDEN'S COMMUNITY CENTER. | 2019 | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18HYEL | HYLAN ELEVATORS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 201 | HA-0001 |  |  | ELEVATOR UPGRADE | 2019 | 0 | 0 | 3700 | 0 | 0 | 0 | 0 | 0 | 3700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18IGIR | INGERSOLL GARDENS INSTALLATION OF IRRIGATION | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 202 | HA-D001 |  |  | INSTALLATION OF IRRIGATION | 2019 | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18INBC | INGERSOLL HOUSES BASKETBALL COURT RENOVATIONS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 202 | HA-D001 |  |  | BASKETBALL COURT RENOVATIONS | 2019 | 400 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18ITPG | RENOVATION OF PLAYGROUND AT INDEPENDENCE TOWERS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 201 | HA-D001 |  |  | REPAIR TODDLER PLAYGROUND AT INDEPENDENCE TOWERS. | 2019 | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18LFSU | LAFAYETTE HOUSES SECURITY UPGRADES | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 203 | HA-D001 |  |  | SECURITY UPGRADES | 2019 | 150 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18OHPG | OCEAN HILL PLAYGROUND | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 216 | HA-D001 |  |  | UPGRADE PLAYGROUND | 2019 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18PKTV | PINK CCTV | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 200 | HA-0001 |  |  | SECURITY UPGRADES AT PINK HOUSES | 2019 | 3000 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18SUBC | RENOVATION OF A BASKETBALL COURT AT SUMNER HOUSES | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 203 | HA-D001 |  |  | RENOVATION OF A BASKETBALL COURT AT SUMNER HOUSES | 2019 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WBCC | PLAYGROUND UPGRADES AT WILLIAMSBURG DAY CARE CENTER | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 201 | HA-D001 |  |  | PLAYGROUND UPGRADES AT WILLIAMSBURG DAY CARE CENTER 222 GRAHAM AVENUE | 2019 | 350 | 0 | 420 | 0 | 0 | 0 | 0 | 0 | 420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WHIT | NYCHA WHITMAN/WILLOUGHBY SENIOR CENTER HVAC UPGRADE | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 200 | HA-D001 |  |  | NYCHA WHITMAN/WILLOUGHBY SENIOR CENTER HVAC UPGRADE | 2019 | 0 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WIPG | WILLIAMSBURG HOUSES PLAYGROUND UPGRADE | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 201 | HA-D001 |  |  | WILLIAMSBURG HOUSES PLAYGROUND UPGRADE AT 176 MAUJER | 2019 | 350 | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WKCC | WYCKOFF GARDENS COMMUNITY CENTER RENOVATION | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 206 | HA-D001 |  |  | WYCKOFF GARDENS COMMUNITY CENTER RENOVATION | 2019 | 0 | 0 | 414 | 0 | 0 | 0 | 0 | 0 | 414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WKLG | WYCKOFF GARDENS LIGHTING | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 206 | HA-D001 |  |  | INSTALLATION OF LIGHTING AT WYCKOFF GARDENS | 2019 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WSEC | WHITMAN BASKETBALL COURT AND SECURITY UPGRADES | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 202 | HA-D001 |  |  | BASKETBALL COURT RENOVATIONS AND SECURITY UPGRADES | 2019 | 400 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WSWT | WOODSON WATER TANK | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 200 | HA-0001 |  |  | WOODSON WATER TANK | 2019 | 1400 | 0 | 1400 | 0 | 0 | 0 | 0 | 0 | 1400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19ALPL | ALBANY HOUSES PLAYGROUND | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 208 | HA-D001 |  |  | BUILD A PLAYGROUND | 2019 | 800 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19BVPU | BAYVIEW HOUSES PLAYGROUND UPGRADE | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 218 | HA-D001 |  |  | PLAYGROUND UPGRADE | 2019 | 250 | 0 | 355 | 0 | 0 | 0 | 0 | 0 | 355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19CSVE | SARATOGA VILLAGE ELEVATORS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 216 | HA-0001 |  |  | FUNDING FOR SARATOGA VILLAGE ELEVATORS | 2019 | 2000 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19FHSE | FARRAGUT HOUSES SECURITY LIGHTING | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 202 | HA-D001 |  |  | FARRAGUT HOUSES-SECURITY LIGHTING FUNDING TO SUPPORT SECURITY LIGHTING | 2019 | 581 | 0 | 581 | 0 | 0 | 0 | 0 | 0 | 581 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19HHTV | HOWARD HOUSES CCTV | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 200 | HA-K001 HA-D001 |  |  | HOWARD HOUSES CCTV | 2019 | 1400 | 0 | 1400 | 0 | 0 | 0 | 0 | 0 | 1400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19SBPU | SHEEPSHEAD BAY HOUSES PLAYGROUND UPGRADE | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 215 | HA-D001 |  |  | PLAYGROUND UPGRADE | 2019 | 0 | 0 | 350 | 0 | 0 | 0 | 0 | 0 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19TCPU | TOMPKINS HOUSES CHILDRENS PARK UPGRADE | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 203 | HA-D001 |  |  | FUNDING FOR CHILDRENS PARK UPGRADE | 2019 | 507 | 0 | 507 | 0 | 0 | 0 | 0 | 0 | 507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19WPLF | WILLIAMS PLAZA LIGHTING AND FENCING IMPROVEMENTS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 201 | HA-D001 |  |  | LIGHTING AND FENCING IMPROVEMENTS | 2019 | 100 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM24VDGR | VAN DYKE I, II GAS RISERS #10 | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 216 | HA-0001 |  |  | INSTALLATION OF GAS RISERS #10 | 2019 | 7150 | 0 | 0 | 0 | 0 | 0 | 0 | 6500 | 6500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-FIOPL | NDF - Fiorentino Plaza Playground Improvements | NEIGHBORHOOD REVITALIZATION | 200 | ED-0384 |  |  | NDF - FIORENTINO PLAZA PLAYGROUND IMPROVEMENTS | 2019 | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | ACEDOH702 | DOHMH - BOILER UPGRADE | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 201 | PU-0025 HL-0082 |  |  | DOHMH - BOILER UPGRADE | 2019 | 400 | 0 | 522 | 0 | 0 | 0 | 0 | 0 | 522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82BRNHC | Brownsville Health Center Renovation of interior space | CLINIC RENOVATION AND REHABILITATION |  | HL-0082 |  |  | BROWNSVILLE HEALTH CENTER RENOVATION OF INTERIOR SPACE | 2019 | 10000 | 0 | 0 | 1000 | 0 | 0 | 5000 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82BUSHC | Bushwick Health Center exterior renovation/interior upgrades | CLINIC RENOVATION AND REHABILITATION |  | HL-0082 |  |  | BUSHWICK HEALTH CENTER EXTERIOR RENOVATION/INTERIOR UPGRADES | 2019 | 6500 | 0 | 0 | 0 | 0 | 0 | 164 | 4000 | 4164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82WLSHC | Williamsburg Health Center Interior Renovation | CLINIC RENOVATION AND REHABILITATION |  | HL-0082 |  |  | WILLIAMSBURG HEALTH CENTER INTERIOR RENOVATION | 2019 | 4400 | 0 | 0 | 1000 | 849 | 2456 | 95 | 0 | 4400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 22200601 | ENY: CAPITAL IMPROVEMENTS | ROUTINE RECONSTRUCTION | 205 | HO-D003 |  | 2094 PITKIN AVENUE, BROOKLYN, N.Y. 11207 | CAPITAL IMPROVEMENTS (SIDEWALK REPAIR, LOBBY UPGRADE, PEDIATRIC CLINIC UPGRADE) AT EAST NEW YORK D&TC | 2019 | 1250 | 1191.98 | 0 | 47 | 0 | 0 | 0 | 0 | 1238.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 22200801 | EAST NEW YORK: RENOVATE THIRD FLOOR CLINICAL AREAS | ROUTINE RECONSTRUCTION | 205 | HO-D003 |  | 2094 PITKIN AVENUE, BROOKLYN, N. Y. 11207 | CONSTRUCT WOMEN'S OPTIONS CENTER | 2019 | 2100 | 2035.65 | 0 | 64 | 0 | 0 | 0 | 0 | 2099.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 22201610 | RENOVATE BROWNSVILLE CHILD HEALTH CLINIC | ROUTINE RECONSTRUCTION | 216 | HO-0214 |  | 259 BRISTOL STREET, BROOKLYN, NY 11212 | RENOVATE THE BROWNSVILLE CHILD HEALTH CLINIC IN ORDER TO EXPAND PRIMARY CARE HEALTH SERVICES. | 2019 | 3870 | 2652.73 | 1218 | 0 | 0 | 0 | 0 | 0 | 3870.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 22201611 | RENOVATE CROWN HEIGHTS CHILD HEALTH CLINIC | ROUTINE RECONSTRUCTION | 208 | HO-0214 |  | 1218 PROSPECT PLACE, BROOKLYN, NY 11213 | RENOVATE THE CROWN HEAIGHTS CHILD HEALTH CLINIC IN ORDER TO EXPAND PRIMARY CARE HEALTH SERVICES. | 2019 | 464 | 831.6 | 115 | 0 | 0 | 0 | 0 | 0 | 946.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 22201901 | ENY: MODERNIZE 2 PASSENGER ELEVATORS | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 2094 PITKIN AVENUE, BROOKLYN, NY 11207 | MODERNIZE 2 PASSENGER ELEVATORS AT NYC HEALTH + HOSPITALS / GOTHAM HEALTH, EAST NEW YORK. | 2019 | 634 | 0 | 538 | 96 | 0 | 0 | 0 | 0 | 634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 23201901 | DSSM: MODERNIZE 3 PASSENGER ELEVATORS | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 594 ALBANY AVENUE, BROOKLYN, NY 11203 | NYC HEALTH + HOSPITALS / MCKINNEY, BRKLYN: MODERNIZE 3 PASSENGER ELEVATORS | 2019 | 909 | 0 | 832 | 37 | 40 | 0 | 0 | 0 | 909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 26201101 | CIH: CONSTRUCT VANDERBILT AVENUE HEALTH CENTER AT S.I. | ROUTINE RECONSTRUCTION | 213 | HO-D003 HO-0214 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 2601 OCEAN PARKWAY, BROOKLYN, N. Y. 11235 | THE PURPOSE OF THIS PROJECT IS TO CONSTRCUT A HEALTH CENTER AT VANDERBILT AVENUE. | 2019 | 23685 | 20373.96 | 1167 | 0 | 0 | 1000 | 5606 | 0 | 28146.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 26201402 | CIH: ADD DEHUMIDICATION & ADD'L COOLING CAPACITY TO THE ORs | ROUTINE RECONSTRUCTION | 213 | HO-D003 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 2601 OCEAN PARKWAY, BROOKLYN, NY 11235 | ADD DEHUMIDICATION AND ADDITIONAL COOLING CAPACITY TO THE ORS AT CONEY ISLAND HOSPITAL, A FUNDING TRANSFER OF $966,000 WAS APPROVED FROM PROJECT ID 26201201 (RENOVATE PSYCH ED) BY THE CITY COUNCIL ON 8/26/13. | 2019 | 966 | 806.63 | 0 | 159 | 0 | 0 | 0 | 0 | 965.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 26201702 | CIH: INSTALL A SECONDARY WATER DISINFECTION SYSTEM - MAIN BG | ROUTINE RECONSTRUCTION | 213 | HO-0214 |  | 2601 OCEAN PARKWAY, BROOKLYN, NY 11235 | CONEY ISLAND HOSPITAL, BROOKLYN, NY: PURCHASE AND INSTALL A SECONDARYWATER DISINFECTION SYSTEM (AKA COPPER-SILVER IONIZATION SYSTEM) FOR THE MAIN BUILDING. | 2019 | 58 | 0 | 58 | 0 | 0 | 0 | 0 | 0 | 58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 26201703 | CIH: INSTALL SECONDARY WATER DISINFECTION SYS-TOWER/HAMMETT | ROUTINE RECONSTRUCTION | 213 | HO-0214 |  | 2601 OCEAN PARKWAY, BROOKLYN, NY 11235 | CONEY ISLAND HOSPITAL, BROOKLYN, NY: PURCHASE AND INSTALL A SECONDARYWATER DISINFECTION SYSTEM (AKA COPPER-SILVER IONIZATION SYSTEM) FOR THE TOWER BUILDING AND THE HAMMET PAVILION. | 2019 | 102 | 0 | 102 | 0 | 0 | 0 | 0 | 0 | 102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 26201902 | CIH: UPGRADE FIRE ALARM SYSTEM | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 2601 OCEAN PARKWAY, BROOKLYN, NY 11235 | CONEY ISLAND HOSPITAL (2601 OCEAN PARKWAY, BK), UPGRADE THE FIRE ALARM SYSTEM THROUGHOUT THE HOSPITAL CAMPUS IN THE MAIN BLDG, TOWER BLDG, HAMMETT PAVILION AND POWERHOUSE BLDG. | 2019 | 268 | 0 | 220 | 48 | 0 | 0 | 0 | 0 | 268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 27201201 | CUMBERLAND: RENOVATE CHEMICAL DEPENDENCY DEPARTMENT | ROUTINE RECONSTRUCTION | 202 | HO-D003 |  | 100 NORTH PORTLAND AVENUE, BROOKLYN, NY 11205 | THE PURPOSE OF THIS PROJECT IS TO RENOVATE CHEMICAL DEPENDENCY DEPARTMENT AT CONEY ISLAND HOSPITAL | 2019 | 273 | 0 | 0 | 273 | 0 | 0 | 0 | 0 | 273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 27201301 | CUMBERLAND: RENOVATE PEDIATRIC PRACTICE DEPARTMENT | ROUTINE RECONSTRUCTION | 202 | HO-K001 |  | 100 NORTH PORTLAND AVENUE, BROOKLYN, NY 111205 | RENOVATE/UPGRADE PEDIATRIC PRACTICE AT CUMBERLAND D&TC TO PROVIDE FORMORE EXAM ROOMS, PATIENT ROOMS, BATHROOMS AND NURSES' STATIONS. | 2019 | 490 | 0 | 0 | 490 | 0 | 0 | 0 | 0 | 490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 27201515 | CUMBERLAND: RENOVATE WOMEN'S HEALTH SVCS DEPT. | ROUTINE RECONSTRUCTION | 202 | HO-D003 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | 100 NORTH PORTLAND AVENUE, BROOKLYN, NY 11206 | RECONIGURE EXISTING WOMEN'S HEALTH SERVICES DEPARTMENT TO MAKE SERVICES ACCESSIBLE FOR WOMEN WITH DISABILITIES. | 2019 | 524 | 67.17 | 133 | 0 | 0 | 0 | 0 | 0 | 200.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 27201610 | RENOVATE BEDFORD HEALTH CLINIC | ROUTINE RECONSTRUCTION | 203 | HO-0214 |  | 485 THROOP AVENUE, BROOKLYN, NY 11221 | RENOVATE THE BEDFORD HEALTH CLINIC IN ORDER TO EXPAND PRIMARY CARE HEALTH SERVICES. | 2019 | 3136 | 2687.77 | 446 | 0 | 0 | 0 | 0 | 0 | 3133.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 27201702 | CUMBERLAND: CONSTRUCT NEW DENTAL FACILITY | ROUTINE RECONSTRUCTION | 202 | HO-D003 |  | 100 NORTH PORTLAND AVENUE, BROOKLYN, NY 11205 | CONSTRUCT NEW DENTAL FACILITY AT NYC HEALTH + HOSPITALS ¦ CUMBERLAND | 2019 | 825 | 0 | 100 | 725 | 0 | 0 | 0 | 0 | 825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 27201803 | CUMBERLAND: FACADE REHABILITATION BUILDING B & C | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 100 NORTH PORTLAND AVENUE | FACADE REHABILITATION, INCLUDING DESIGN, CONSTRUCTION, AND ASBESTOS ABATEMENT | 2019 | 1658 | 0 | 356 | 1026 | 276 | 0 | 0 | 0 | 1658 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29201301 | KCHC: UPGRADE FIRE ALARM SYSTEM IN "ABC" & "T" BLDGS | ROUTINE RECONSTRUCTION | 209 | HO-0214 |  | 451 CLARKSON AVENUE, BROOKLYN, NY 11203 | INSTALL UPDATED FIRE ALARM SYSTEM AT KINGS COUNTY HOSPITAL CENTER. MANY PORTIONS OF THE EXISTING SYSTEM ARE OBSOLETE AND DO NOT MEET CURRENT FDNY CODE REQUIREMENT. | 2019 | 5395 | 4395.17 | 467 | 500 | 0 | 0 | 0 | 0 | 5362.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29201501 | BED-STUY REHAB CTR: FIRE ALARM SYSTEM REPLACEMENT | ROUTINE RECONSTRUCTION | 203 | HO-0214 |  | 722 MYRTLE AVENUE, BROOKLYN, NY 11205 | CURRENT FIRE ALARM SYSTEM AT THE BEDFORD-STUYVESANT ALCOHOLISM TREATMENT CENTER IS OBSOLETE. A COMPLETE REPLACEMENT WILL ENSURE PATIENT ANDSTAFF SAFETY. | 2019 | 200 | 397.19 | 0 | 71 | 0 | 0 | 0 | 0 | 468.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29201610 | KCHC: LOCAL LAW -11 COMPLIANCE - BLDG T | ROUTINE RECONSTRUCTION | 209 | HO-0214 |  | 451 CLARKSON AVENUE, BROOKLYN, N. Y. 11203 | THE PURPOSE OF THIS PROJECT IS TO RENOVATE BUILDING "T" AT KINGS COUNTY HOSPITAL CENTER USING LOCAL LAW 11- FUNDS FOR LOCAL LAW 11 COMPLIANCE. | 2019 | 618 | 558.24 | 60 | 0 | 0 | 0 | 0 | 0 | 618.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29201611 | KCHC: LOCAL LAW 11 COMPLIANCE - BLDG ABC | ROUTINE RECONSTRUCTION | 209 | HO-0214 |  | 451 CLARKSON AVENUE, BROOKLYN, N. Y. 11203 | THE PURPOSE OF THIS PROJECT IS TO RENOVATE BUILDINGS A, B, AND C AT KINGS COUNTY HOSPITAL CENTER USING LOCAL LAW 11- FUNDS FOR LOCAL LAW 11 COMPLIANCE. | 2019 | 1100 | 532.72 | 567 | 0 | 0 | 0 | 0 | 0 | 1099.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29201612 | KCHC: BLDG "P" FACADE REMEDIATION - LOCAL LAW 11 COMPLIANCE | ROUTINE RECONSTRUCTION | 209 | HO-0214 |  | 451 CLARKSON AVENUE, BROOKLYN, N. Y. 11203 | THE PURPOSE OF THIS PROJECT IS TO RENOVATE BLDNG "P" FACADE AT KINGS COUNTY HOSPITAL CENTER USING LOCAL LAW 11- FUNDS FOR LOCAL LAW 11 COMPLIANCE. | 2019 | 17606 | 591 | 4027 | 5903 | 7085 | 0 | 0 | 0 | 17606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29201613 | KCHC: BLDG "K-5 CORNICE REMEDIATION LOCAL LAW 11 COMPLIANCE | ROUTINE RECONSTRUCTION | 209 | HO-0214 |  | 451 CLARKSON AVENUE, BROOKLYN, N. Y. 11203 | THE PURPOSE OF THIS PROJECT IS TO REMEDIATE BLDNG "K-5 "FACADE AT KINGS COUNTY HOSPITAL CENTER USING LOCAL LAW 11- FUNDS FOR LOCAL LAW 11COMPLIANCE. | 2019 | 112 | 1.5 | 110 | 0 | 0 | 0 | 0 | 0 | 111.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29201614 | KCHC: BOILER REPLACEMENT | ROUTINE RECONSTRUCTION | 209 | HO-0214 |  | 451 CLARKSON AVENUE, BROOKLYN, NY 11203 | REPLACE BOILER AT KINGS COUNTY HOSPITAL CENTER, BROOKLYN, NY. | 2019 | 5000 | 4035 | 381 | 584 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29201615 | KCHC: INSTALL A MODULAR COGENERATION HEAT & POWER SYSTEM | ROUTINE RECONSTRUCTION | 201 | HO-0214 |  | 451 CLARKSON AVENUE, BROOKLYN, NY 11203 | INSTALL A MODULAR COGENERATION HEAT & POWER SYSTEM AT KCHC. | 2019 | 1011 | 0 | 779 | 232 | 0 | 0 | 0 | 0 | 1011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29201803 | KINGS, ABC BUILDING ELECTRICAL FEEDER REPLACEMENT | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 451 CLARKSON AVENUE, BROOKLYN, NY 11203 | ABC BUILDING ELECTRICAL FEEDER REPLACEMENT AT KINGS COUNTY HOSPITAL | 2019 | 460 | 0 | 460 | 0 | 0 | 0 | 0 | 0 | 460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48200803 | WOODHULL: OB UNIT EXPANSION | ROUTINE RECONSTRUCTION | 203 | HO-0214 |  | 760 BROADWAY, BROOKLYN, NY 11206 | CREATE 14 PATIENT ROOMS (2 LABOR & DELIVERY ROOMS, 1 BREASTFEEDING RM, 1 MEDICATION/TREATMENT RM, A WELL BABY NURSERY RM, A NURSES STATION,A UTILITY ROOM, ETC. | 2019 | 3578 | 2960.09 | 107 | 0 | 0 | 0 | 0 | 0 | 3067.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48200903 | WOODHULL: EXPAND NEONATAL SPECIAL CARE UNIT (NICU) | ROUTINE RECONSTRUCTION | 203 | HO-0214 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 760 BROADWAY, BROOKLYN, N.Y. 11206 | THE PURPOSE OF THIS PROJECT IS FOR ARCHITECTURAL AND ENGINEERING DESIGN SERVICES FOR THE NEONATAL SPECIAL CARE UNIT EXPANSION PROJECT AT WOODHULL MEDICAL AND MENTAL HEALTH CENTER. . EEL; 20YRS. | 2019 | 741 | 67.61 | 578 | 52 | 0 | 0 | 0 | 0 | 697.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48201402 | WOODHULL: ESTABLISH CPEP | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 760 BROADWAY, BROOKLYN, NY 11206 | RENOVATE THE CPEP DEPARTMENT AT WOODHULL MEDICAL & MENTAL HEALTH CENTER. | 2019 | 1817 | 1665.91 | 0 | 127 | 0 | 0 | 0 | 0 | 1792.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48201506 | WOODHULL: ESTABLISH BURN UNIT | ROUTINE RECONSTRUCTION | 203 | HO-K001 |  | 760 BROADWAY BROOKLYN 11206 | WOODHULL: ESTABLISH BURN UNIT | 2019 | 4150 | 0 | 0 | 0 | 0 | 4150 | 0 | 0 | 4150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48201516 | WOODHULL: RENOVATE WOMEN'S HEALTH PAVILION | ROUTINE RECONSTRUCTION | 203 | HO-D003 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | 760 BROADWAY, BROOKLYN, NY 11206 | RECONIGURE EXISTING WOMEN'S HEALTH PAVILION TO MAKE SERVICES ACCESSIBLE FOR WOMEN WITH DISABILITIES. | 2019 | 256 | 49.3 | 0 | 133 | 0 | 0 | 0 | 0 | 182.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48201602 | WOODHULL: LOCAL LAW 11 COMPLIANCE | ROUTINE RECONSTRUCTION |  | HO-0214 |  | THE PURPOSE OF THIS PROJECT IS TO RENOVATE BUILDINGS AT WOODHULL HOSPITAL CENTER USING LOCAL LAW 11- FUNDS FOR LOCAL LAW 11 COMPLIANCE. | THE PURPOSE OF THIS PROJECT IS TO RENOVATE BUILDINGS AT WOODHULL HOSPITAL CENTER USING LOCAL LAW 11- FUNDS FOR LOCAL LAW 11 COMPLIANCE. | 2019 | 8036 | 0 | 0 | 6389 | 1647 | 0 | 0 | 0 | 8036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48201610 | RENOVATE BUSHWICK COMMUNICARE | ROUTINE RECONSTRUCTION | 204 | HO-0214 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 335 CENTRAL AVENUE, BROOKLYN, NY 11221 | RENOVATE THE BUSHWICK COMMUNICARE HEALTH CLINIC IN ORDER TO EXPAND PRIMARY CARE HEALTH SERVICES. | 2019 | 3319 | 4093.17 | 336 | 0 | 0 | 0 | 0 | 0 | 4429.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48201701 | WOODHULL: AIR HANDLER UNITS UPGRADE | ROUTINE RECONSTRUCTION | 203 | HO-0214 |  | 760 BROADWAY, BROOKLYN, NY 11206 | UPGRADE/REPLACE AIR HANLER UNITS AT WOODHULL MEDICAL & MENTAL HEALTH CENTER | 2019 | 4066 | 0 | 3566 | 500 | 0 | 0 | 0 | 0 | 4066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48201901 | WOODHULL: CPEP RENOVATION | ROUTINE RECONSTRUCTION |  | HO-D003 |  | 760 BROADWAY, BROOKLYN, NY 11203 | CPEP RENOVATION | 2019 | 150 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48201902 | WOODHULL: EMERGENCY DEPARTMENT RENOVATION | ROUTINE RECONSTRUCTION |  | HO-D003 |  | 760 BROADWAY, BROOKLYN, NY 11203 | EMERGENCY DEPARTMENT RENOVATION | 2019 | 5000 | 0 | 279 | 4721 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | ACEHHC402 | KINGS COUNTY HOSPITAL CENTER ENERGY UPGRADE | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 201 | PU-0025 |  |  | KINGS COUNTY HOSPITAL ACE PROGRAM | 2019 | 12759 | 14833.68 | 72 | 0 | 0 | 0 | 0 | 0 | 14905.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | ACEHHC407 | Cumberland : Boiler Plant Replacement | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 205 | HO-0214 |  |  | REPLACE EXISTING HPS BOILERS & ANCILLARY EQUIPMENT WITH NEW HIGH EFFICIENCY LOW EMISSIONS FIRETUBE STEAM BOILERS AND ANCILLARY EQUIPMENT. INSTALL NEW EFFICIENT MODULATING VERTICAL DOMESTIC HOT WATER BOILERS. NEW CONTROLS WILL BE INSTALLED | 2019 | 0 | 7936.63 | 605 | 0 | 0 | 0 | 0 | 0 | 8541.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | CIH1 | CIH: MODERNIZE GENERAL CARE INPATIENT/AMB CARE FACILITIES | MAJOR OR PARTIAL HOSPITAL RECONSTRUCTION | 200 | HO-0377 |  | 2601 OCEAN PARKWAY, BROOKLYN, NY 11235 | CONEY ISLAND HOSPITAL - MAJOR MODERNIZATION PROJECT TO CONSOLIDATE AND MODERNIZE THE FENERAL CARE INPATIENT & AMBULATORY CARE FACILITIES; | 2019 | 92012 | 37912.77 | 0 | 0 | 0 | 1645 | 0 | 0 | 39557.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | GABIHHC | GROUP ATTACHMENT BASED INTERVENTION | CHILD WELFARE FACILITIES | 200 | CS-0003 |  |  | TBD | 2019 | 759 | 0 | 0 | 386 | 0 | 0 | 0 | 0 | 386 | 0 | 0 | 554 | 0 | 0 | 0 | 0 | 554
20190425 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | SAND2601 | CIH: RELOCATE OUTPATIENT RADIOLOGIC IMAGING SERVICES | ROUTINE RECONSTRUCTION | 213 | HO-0214 |  | 2601 OCEAN PARKWAY, BROOKLYN, NY 11235 | RENOVATE EXISTING SPACE ON THE 5TH FLOOR OF THE MAIN HOSPITAL BUILDING TO RELOCATE OUTPATIENT RADIOLOGIC IMAGING SERVICES FROM THE FIRST FLOOR OF THE BUILDING THAT WAS DESTROYED BY SEVERE WATER DAMAGES DUE TOEXPOSURE TO SALT WATER FROM HURRICANE SANDY AT CONEY ISLAND HOSPITAL. | 2019 | 2302 | 32.15 | 0 | 0 | 0 | 0 | 0 | 0 | 32.15 | 1458.33 | 66 | 608 | 170 | 0 | 0 | 0 | 2302.33
20190425 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | SAND2602 | CIH: CONSTRUCT TWO NEW CT & MRI MODULAR BUILDINGS | ROUTINE RECONSTRUCTION | 213 | HO-0214 |  | 2601 OCEAN PARKWAY, BROOKLYN, NY 11235 | CONSTRUCT TWO NEW MODULAR BUILDINGS TO HOUSE CT AND MRI RADIOLOGIC IMAGING SERVICES WHICH WERE ORIGINALLY LOCATED ON THE FIRST FLOOR OF THEMAIN BUILDING AND WERE DESTROYED BY SEVERE WATER DAMAGES DUE TO EXPOSURE TO SALT WATER FROM HURRICANE SANDY AT CONEY ISLAND HOSPITAL. | 2019 | 5500 | 33.51 | 0 | 0 | 0 | 0 | 0 | 0 | 33.51 | 301.64 | 0 | 3873 | 1291 | 0 | 0 | 0 | 5465.64
20190425 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | SAND2604 | CIH: RESTORATION OF PNEUMATIC TUBE SYSTEM 1ST FLOOR ED | ROUTINE RECONSTRUCTION | 213 | HO-0214 |  | 2601 OCEAN PARKWAY, BROOKLYN, NY 11235 | THIS PROJECT RESTORES THE SERVICE PROVIDED BY THE DAMAGED BY HURRICANSANDY PNEUMATIC TUBE SYSTEM AT CONEY ISLAND HOSPITAL BY RELOCATING THE PORTION OF THE SYSTEM SERVING THE ED TO THE SECOND FLOOR AND ABAOVETHE CEILING IN THE ED. | 2019 | 725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 660.64 | 0 | 48 | 16 | 0 | 0 | 0 | 724.64
20190425 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | SAND2605 | CIH: MAJOR MITIGATION PROJECT | ROUTINE RECONSTRUCTION | 213 | HO-0214 |  | 2601 OCEAN PARKWAY, BROOKLYN, NY 11235 | MAJOR MITIGATION PROJECT TO ENSURE THAT CONEY ISLAND HOSPITAL WILL BEPROTECTED FROM FUTURE HURRICANE STORMS LIKE SANDY. DESIGN OPTION YET TO BE SELECTED. FUNDS TO BE USED FOR THE CONSTRUCTION OF A NEW RESILIENT CRITICAL SERVICES BUILDING THAT WILL HOUSE AN EMERGENCY DEPARTMENT ON THE SECOND FLOOR, PLUS CRITICAL MEDICAL SERVICES SUCH AS X-RAY, CATSCAN, MRI, PHARMACY, AND LABS. | 2019 | 85194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 443.22 | 49750 | 28350 | 6650 | 0 | 0 | 0 | 85193.22
20190425 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | SAND2607 | CIH: REPLACEMENT OF BASEMENT LIGHTING IN THE MAIN BLDG. | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 2601 OCEAN PARKWAY, BROOKLYN, NY 11235 | NYC HEALTH + HOSPITALS ¦ CONEY ISLAND: REPLACEMENT OF BASEMENT LIGHTING THAT WAS WATER DAMAGED FROM HURRICANE SANDY. | 2019 | 702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 638 | 64 | 0 | 0 | 0 | 0 | 702
20190425 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | SAND26B | CIH RECONSTRUCTION AS A RESULT OF SANDY - CATEGORY B | ROUTINE RECONSTRUCTION |  | HO-0214 |  |  | 2601 OCEAN PARKWAY, BROOKLYN, NY 11235 | 2019 | 37500 | 3213.14 | 0 | 0 | 0 | 259 | 0 | 0 | 3472.14 | 10999.22 | 0 | 6659 | 2219 | 0 | 0 | 0 | 19877.22
20190425 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | SAND26E | CIH RECONSTRUCTION AS A RESULT OF SANDY - CATEGORY E | ROUTINE RECONSTRUCTION | 213 | HO-0214 |  | 2601 OCEAN PARKWAY, BROOKLYN, NY 11235 | RECONSTRUCTION OF CONEY ISLAND HOSPITAL NECESSITATED BY HURRICANE SANDY. FEMA CATEGORY E: BUILDINGS AND EQUIPMENT (PERMANENT WORK). | 2019 | 0 | 133.62 | 0 | 0 | 0 | 0 | 0 | 0 | 133.62 | 18489.86 | 0 | 3291 | 1097 | 0 | 0 | 0 | 22877.86
20190425 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26-STAB13 | 26th Ward - Emergency Generators | PLANT COMPONENT STABILIZATION | 218 205 216 | WP-0206 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | 26TH WARD - EMERGENCY GENERATORS. STABILIZATION OF THE 26TH WARD WPCP. INCREASE THE RATE OF FLOW THAT THE PLANT CAN PROCESS, & OPTIMIZE THE AMOUNT OF SANITARY FLOW COLLECTED FROM THE DRAINAGE AREA DURING PERIODS OF RAINFALL & REDUCE SLUDGE VOLUME & IMPROVE SLUDGE DISPOSAL. STABILIZATION OF THE 26TH WARD WPCP. | 2019 | 72340 | 9850.38 | 5239 | 0 | 0 | 0 | 0 | 0 | 15089.38 | 29534.65 | -9 | 0 | 0 | 0 | 0 | 0 | 29525.65
20190425 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26-STAB20 | 26th Ward Primary Settling Tank & Solid Handling | PLANT COMPONENT STABILIZATION | 218 205 216 | WP-0206 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | EMERGENCY INSTALLATION OF (3) LOW LEVEL MAIN SEWAGE PUMPS AND MOTOR CONTROLS AT 26TH WARD WPCP | 2019 | 232200 | 166981.22 | 10781 | 0 | 0 | 0 | 0 | 0 | 177762.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-144-L | INSTALLATION OF (13) NEW CENTRIFUGES @ 26TH WARD WPCP | PLANT UPGRADING AND RECONSTRUCTION | 200 | WP-0112 |  | 12266 FLATLANDS AVENUE, BROOKLYN NEW YORK 11270 | INSTALLATION OF (13) NEW CENTRIFUGES ATH THE 26TH WARD WPCP | 2019 | 50850 | 15000.84 | 0 | 0 | 0 | 6005 | 0 | 45686 | 66691.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-146-L | INSTALLATION OF A PERMANENT CAUSTIC SYSTEM @ 26TH WARD WWTP | PLANT UPGRADING AND RECONSTRUCTION | 200 | WP-0112 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | 12266 FLATLANDS AVENUE, BROOKYN, N.Y. 11270 | INSTALLATION OF A PERMANENT CAUSTIC SYSTEM AT THE 26TH WARD WWTP | 2019 | 3200 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-147-L | LIGHTING UPGRADE AT THE 26TH WARD WPCP | PLANT UPGRADING AND RECONSTRUCTION | 200 | WP-0112 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | LIGHTING UPGRADE AT THE 26TH WARD WPCP | 2019 | 100 | 0 | 0 | 0 | 0 | 0 | 8000 | 0 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-148-L | TRC - CONS OF DISINFECTION FACILITIES AT 26TH WARD WPCP | CONSENT DECREE UPGRADING AND CONSTRUCTION | 200 | WP-0282 |  |  | CONSTRUCTION OF DISINFECTION FACILITIES AT 26TH WARD WPCP | 2019 | 33000 | 0 | 0 | 4591 | 0 | 3500 | 13500 | 0 | 21591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-149 | RECONSTRUCT TIDE GATES/EFFLUENT CHAMBERS @ SPRING CREEK | PLANT UPGRADING AND RECONSTRUCTION | 200 | WP-0112 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 122-66 FLATLANDS AVENUE, BROOKLYN, NEW YORK 11207 | RECONSTRUCTION OF EFFLUENT CHAMBERS AND RETROFITTING OF 48 TIDE GATESIN THE EXISTING WALL OPENINGS AT THE 26TH WARD WWTP. | 2019 | 7150 | 300 | 4682 | 0 | 0 | 0 | 0 | 0 | 4982 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-154-L | RECONS ODOR CONTROL & HVAC SYS IN DEWATERING BLDG. 26TH WARD | PLANT UPGRADING AND RECONSTRUCTION | 200 | WP-0112 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 122-66 FLATLANDS AVE., BROOKLYN, N.Y. 11207 | RECONSTRUCTION OF THE ODOR CONTROL AND HVAC SYSTEMS IN THE 26TH WARD DEWATERING BUILDING | 2019 | 35700 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-155-L | REPLACE MAIN INFLUENT GATES AT 26TH WARD WPCP | PLANT UPGRADING AND RECONSTRUCTION | 200 | WP-0112 |  |  | REPLACE MAIN INFLUENT GATES AT 26TH WARD WPCP | 2019 | 2400 | 0 | 0 | 400 | 0 | 0 | 0 | 2000 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-156-L | REPLACE WASTE ACTIVATED SLUDGE PIPING AT 26TH WARD WPCP | PLANT UPGRADING AND RECONSTRUCTION | 200 | WP-0112 |  |  | REPLACE WASTE ACTIVATED SLUDGE PIPING AT 26TH WARD WPCP | 2019 | 6600 | 0 | 0 | 600 | 0 | 6000 | 0 | 0 | 6600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-21 | HIGH LEVEL MAIN SEWAGE PUMP IMPROVEMENTS AT 26TH WARD WPCP | PLANT COMPONENT STABILIZATION | 200 | WP-0206 |  |  | HIGH LEVEL MAIN SEWAGE PUMP IMPROVEMENTS AT 26TH WARD WPCP | 2019 | 18156 | 15850.99 | 1128 | 0 | 0 | 0 | 0 | 0 | 16978.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | ACEDEP801 | DEP - LED lighting - Emergency / Exit / Combo | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 201 | PU-0025 |  |  | LED LIGHTING - EMERGENCY / EXIT / COMBO | 2019 | 221 | 0 | 0 | 221 | 0 | 0 | 0 | 0 | 221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | BED-830 | Rplment WM Park Ave btw Classon Ave & Ryerson (HWD007K03) | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 202 | SE-0002K WM-0001 |  |  | (HW007K03) REPLACEMENT OF WATER MAIN ALONG PARK AVENUE BETWEEN CLASSON AVENUE AND RYERSON STREET, OTHER LOCATIONS AS LISTED ON PAGE 3 "DESIGN SCOPE" AS SHOWN ON ATTACHED SKETCH IN BOROUGH OF BROOKLYN. | 2019 | 2308 | 0 | 0 | 0 | 0 | 2308 | 0 | 0 | 2308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CI-113-L | RECONSTRUCT (4) ENGINE GENERATOR CONTROL SYSTEM | PLANT UPGRADING AND RECONSTRUCTION | 200 | WP-0112 |  | AVENUE "Z" AND KNAPP STREET, BROOKLYN, NEW YORK 11235 | RECONSTRUCTION OF (4) FOUR ENGINE GENERATOR CONTROL SYSTEM AT THE CONEY ISLAND WPCP | 2019 | 70450 | 49.51 | 254 | 0 | 0 | 0 | 0 | 70000 | 70303.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CI-119-L | RECONSTRUCTION OF GATES & MSP MOTORS & CONTROLS @ C.I. | PLANT UPGRADING AND RECONSTRUCTION | 200 | WP-0112 |  | AVENUE Z AND KNAPP STREET, BROOKLYN, N.Y. 11208 | RECONSTRUCTION OF GATES AND MSP MOTORS AND CONTROL AT CONEY ISLAND WWTP | 2019 | 23294 | 0 | 30825 | 0 | 0 | 0 | 146000 | 0 | 176825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CI-124 | RECONSTRUCTION OF HEATING SYSTEM AT CONEY ISLAND WPCP | PLANT UPGRADING AND RECONSTRUCTION | 200 | WP-0112 |  |  | RECONSTRUCTION OF HEATING SYSTEM AT CONEY ISLAND WPCP | 2019 | 10000 | 0 | 0 | 1000 | 1000 | 10000 | 0 | 0 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CI-125-L | RECONS FINAL SETTLING TANKS & RAS/WAS SYSTEM AT CONEY ISLAND | PLANT UPGRADING AND RECONSTRUCTION | 200 | WP-0112 |  |  | RECONS FINAL SETTLING TANKS & RAS/WAS SYSTEM AT CONEY ISLAND | 2019 | 10800 | 0 | 0 | 1800 | 0 | 0 | 0 | 1200 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CI-142-L | RECONSTRUCTION OF BLOWER CONTROL SYSTEMS @ CONEY ISLAND | PLANT UPGRADING AND RECONSTRUCTION | 200 | WP-0112 |  | AVENUE Z AND KNAPP STREET, BROOKLYN, N.Y. 11208 | RECONSTRUCTION OF THE BLOWER CONTROL SYSTEMS AT THE CONEY ISLAND WASTEWATER TREATMENT PLANT, BROOKLYN, NEW YORK. | 2019 | 2763 | 0 | 0 | 2263 | 0 | 0 | 0 | 0 | 2263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CI-LIGHT | LIGHTING UPGRADE AT THE CONEY ISLAND WPCP | PLANT UPGRADING AND RECONSTRUCTION | 200 | WP-0112 |  |  | LIGHTING UPGRADE AR COUNEY ISLAND WASTEWATER TREATMENT PLANT | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CONISPH05 | SAN & STRM SWR, WM1, IN CONEY ISL AREA, PH 5 | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 213 | SE-0200K WM-0006 WM-0001 |  |  | STORM & SANITARY SEWER, DISTRIBUTION WATER MAIN IN CONEY ISLAND AREA,PHASE 5 | 2019 | 13205 | 5 | 0 | 0 | 0 | 13000 | 0 | 0 | 13005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-GC-SFS | CONSTRUCTION OF GOWANUS CSO RETENTION FAC SUPERFUND SITE | WATER QUALITY MANDATES | 299 | WP-0169 |  |  | CONSTRUCTION OF OF TWO IN-LINE SEWAGE/STORMWATER RETENTIONS TANKS TO RETAIN STORMWATER WHICH CURRENTLY DISCHARGES THROUGH OUTFALLS RH-034 AND OH-007 AT THE GOWANUS CANAL SUPERFUND SITE | 2019 | 348000 | 81183.15 | 87135 | 91638 | 125362 | 228000 | 110000 | 90000 | 813318.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-GC | FLUSHING TUNNEL REACTIVATION & GOWANUS CANAL FORCE MAIN | WATER QUALITY MANDATES | 299 | WP-0169 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | GOWANUS CANAL & FLUSHING TUNNEL, BROOKLYN,NY | FLUSHING TUNNEL REACTIVATION AND GOWANUS CANAL FORCE MAIN, (FORMERLY IN WP-152) CONTS. 15 & 16 | 2019 | 126428 | 190124.81 | 5384 | 0 | 0 | 0 | 0 | 0 | 195508.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-GC-SP | CONSTRUCTION OF GOWANUS CANAL PILOT SPONGE PARK | WATER QUALITY MANDATES | 200 | WP-D169 P-D017 |  |  | DESIGN AND CONSTRUCTION OF GOWANUS CANAL PILOT SPONGE PARK | 2019 | 1273 | 621.64 | 146 | 0 | 0 | 0 | 0 | 0 | 767.64 | 535 | 0 | 0 | 0 | 0 | 0 | 0 | 535
20190425 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-PA-ECR | ECOLOGICAL RESTORATION | WATER QUALITY MANDATES | 218 | WP-0169 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | ECOLOGICAL RESTORATION . PAERDEGAT BASIN WATER QUALITY. | 2019 | 12050 | 21995.1 | 349 | 0 | 0 | 0 | 0 | 0 | 22344.1 | 14637.48 | 0 | 0 | 0 | 0 | 0 | 0 | 14637.48
20190425 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-PSPGND | CONSTRUCTION OF PARK SLOPE PLAYGROUND GREEN INFRASTRUCTURE | GREEN INFRASTRUCTURE PROGRAM | 206 | WP-0169 |  |  | CONSTRUCTION OF PARK SLOPE PLAYGROUND GREEN INFRASTRUCTURE | 2019 | 394 | 0 | 394 | 0 | 0 | 0 | 0 | 0 | 394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | GKOH15-1A | GI - CONS OF GI IN GRAVESEND BAY CSO TRIB AREA OH-15 PHASE 1 | GREEN INFRASTRUCTURE PROGRAM | 200 | WP-0169 |  |  | GI - CONSTRUCTION OF GREEN INFRASTRUCTURE IN GRAVESEND BAY CSO TRIB AREA OH-15 PHASE 1 | 2019 | 14000 | 0 | 0 | 0 | 14000 | 0 | 0 | 0 | 14000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | GKOH15-1B | GI - CONS OF GI IN GRAVESEND BAY CSO TRIB AREA OH-15 PHASE 1 | GREEN INFRASTRUCTURE PROGRAM | 200 | WP-0169 |  |  | GI - CONSTRUCTION OF GREEN INFRASTRUCTURE IN GRAVESEND BAY CSO TRIBUTARY AREA OH-15,PHASE 1 | 2019 | 14000 | 0 | 0 | 0 | 14000 | 0 | 0 | 0 | 14000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | GKOH15-2A | GI - CONS OF GI IN GRAVESEND BAY CSO TRIB AREA OH-15 PHASE 2 | GREEN INFRASTRUCTURE PROGRAM | 200 | WP-0169 |  |  | CONSTRUCTION OF ROW GREEN INFRASTRUCTURE IN GRAVESEND BAY CSO TRIBUTARY AREA OH-15, PHASE 2 | 2019 | 14000 | 0 | 0 | 0 | 0 | 14000 | 0 | 0 | 14000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | GKOH15-2B | GI - CONS OF GI IN GRAVESEND BAY CSO TRIB AREA OH-15 PHASE 2 | GREEN INFRASTRUCTURE PROGRAM | 200 | WP-0169 |  |  | GI - CONSTRUCTION OF GREEN INFRASTRUCTURE IN GRAVESEND BAY CSO TRIBUTARY AREA OH-15,PHASE 2 | 2019 | 14000 | 0 | 0 | 0 | 0 | 14000 | 0 | 0 | 14000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | GKOH15-3A | GI - CONS OF GI IN GRAVESEND BAY CSO TRIB AREA OH-15 PHASE 3 | GREEN INFRASTRUCTURE PROGRAM | 200 | WP-0169 |  |  | GI - CONSTRUCTION OF GREEN INFRASTRUCTURE IN GRAVESEND BAY CSO TRIBUTARY AREA OH-15,PHASE 3 | 2019 | 14000 | 0 | 0 | 0 | 0 | 14000 | 0 | 0 | 14000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | GKOH15-3B | GI - CONS OF GI IN GRAVESEND BAY CSO TRIB AREA OH-15 PHASE 3 | GREEN INFRASTRUCTURE PROGRAM | 200 | WP-0169 |  |  | GI - CONSTRUCTION OF GREEN INFRASTRUCTURE IN GRAVESEND BAY CSO TRIBUTARY AREA OH-15,PHASE 3 | 2019 | 14000 | 0 | 0 | 0 | 0 | 14000 | 0 | 0 | 14000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | GKOH15-4A | GI - CONS OF GI IN GRAVESEND BAY CSO TRIB AREA OH-15 PHASE 4 | GREEN INFRASTRUCTURE PROGRAM | 200 | WP-0169 |  |  | GI - CONSTRUCTION OF GREEN INFRASTRUCTURE IN GRAVESEND BAY CSO TRIBUTARY AREA OH-15,PHASE 4 | 2019 | 14000 | 0 | 0 | 0 | 0 | 14000 | 0 | 0 | 14000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | GKOH15-4B | GI - CONS OF GI IN GRAVESEND BAY CSO TRIB AREA OH-15 PHASE 4 | GREEN INFRASTRUCTURE PROGRAM | 200 | WP-0169 |  |  | GI - CONSTRUCTION OF GREEN INFRASTRUCTURE IN GRAVESEND BAY CSO TRIBUTARY AREA OH-15,PHASE 4 | 2019 | 14000 | 0 | 0 | 0 | 0 | 14000 | 0 | 0 | 14000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | GK-PD-A | GI - INSTALL GI AT NYPD PCTS 75, 77 & 115 PARKING LOTS | GREEN INFRASTRUCTURE PROGRAM | 200 | WP-0169 |  |  | GI - INSTALL GREEN INFRASTRUCTURE AT NEW YORK POLICE DEPARTMENT PRECINCTS 75, 77 & 115 PARKING LOTS | 2019 | 1296 | 0 | 0 | 118 | 1178 | 0 | 0 | 0 | 1296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | GK-PD-B | GI - INSTALL GI AT NYPD PCTS 73, 79 & 81 PARKING LOTS | GREEN INFRASTRUCTURE PROGRAM | 200 | WP-0169 |  |  | INSTALL GREEN INFRASTRUCTURE AT NEW YORK POLICE DEPARTMENT PRECINCTS 73, 79 & 81 PARKING LOTS | 2019 | 1804 | 0 | 0 | 164 | 1640 | 0 | 0 | 0 | 1804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | GK-PD-C | GI - INSTALL GI AT NYPD 83 PRECINCT PARKING LOTS | GREEN INFRASTRUCTURE PROGRAM | 200 | WP-0169 |  |  | GI - INSTALL GREEN INFRASTRUCTURE AT NEW YORK POLICE DEPARTMENT PRECINCT 83 PARKING LOTS | 2019 | 1016 | 0 | 0 | 93 | 923 | 0 | 0 | 0 | 1016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | GK-PD-D | GI - INSTALL GI AT NYPD PCTS 43, 71,107 & FLUSHING ARMORY | GREEN INFRASTRUCTURE PROGRAM | 200 | WP-0169 |  |  | GI - INSTALL GREEN INFRASTRUCTURE AT NEW YORK POLICE DEPARTMENT PRECINCTS 43, 71, 107 PARKING LOTS & FLUSHING ARMORY | 2019 | 2379 | 0 | 0 | 217 | 2162 | 0 | 0 | 0 | 2379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | GKRH34-03 | ON-SITE CONS OF GI PRACTICES WYCKOFF GDNS,BOREUM & CARROLL P | GREEN INFRASTRUCTURE PROGRAM | 200 | P-D017 WP-0169 |  |  | ON-SITE CONSTRUCTION OF GI PRACTICES ON RH-034 | 2019 | 1000 | 0 | 250 | 0 | 1000 | 0 | 0 | 0 | 1250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-159 | TRC - NEWTOWN CREEK DECLORINATION FACILITY | CONSENT DECREE UPGRADING AND CONSTRUCTION | 200 | WP-0282 |  | 301 GREEN POINT AVENUE BROOKLYN, N.Y. 11222 | NEWTOWN CREEK DECLORINATION | 2019 | 8974 | 10230.96 | 769 | 0 | 0 | 0 | 0 | 0 | 10999.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-163 | CONSTRUCTION OF PERIMETER FENCE AT NEWTOWN CREEK WPCP | PLANT UPGRADING AND RECONSTRUCTION | 200 | WP-0112 |  |  | CONSTRUCTION OF PERIMETER FENCE AT NEWTOWN CREEK WPCP | 2019 | 4200 | 4897.72 | 128 | 0 | 0 | 0 | 0 | 0 | 5025.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-176-L | RECONSTRUCTION OF CCTV SYSTEM @ THE NEWTOWN CREEK WWTP | PLANT UPGRADING AND RECONSTRUCTION | 200 | WP-0112 |  | 329 GREENPOINT AVENUE BROOKLYN, N.Y. 11222 | RECONSTRUCTION OF THE CCTV SYSTEM AT THE NEWTOWN CREEK WASTEWATER TREATMENT PLANT. THE REMOVAL OF ALL EXISTING ANALOG CAMERAS (APPROX 200 CAMERAS) AND INSTALL APPROXIMATELY 200 DIGITAL IP ADDRESSABLE CAMERAS, NETWORK VIDEO RECORDERS AND MONITORS. | 2019 | 5850 | 0 | 4119 | 0 | 0 | 0 | 0 | 0 | 4119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-36 | MAIN BUILDING NORTH NEWTOWN CREEK WPCP UPGRADING | CONSENT DECREE UPGRADING AND CONSTRUCTION | 200 | WP-0283 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | THE EXISTING WESTERN PORTIONOF MAIN BUILDING WILL BE DEMOLISHED AND RECONSTRUCTED TO HOUSE STORAGE FACILITIES, HEAVY MACHINERY SHOP AND SUPPORT FACILITIES, PERSONNEL FACILITIES, TRAINING FACILITIES AND MECHANICAL & ELECTRICAL ROOMS. REPLACEMENT OF RAW SEWAGE PUMPS WITH HIGHER CAPACITY AND RESISTOR DRIVES. RECONSTRUCTION OF PRIMARY SCREENING FACILITY TO INCLUDE NEW CLIMBER SCREENS, SCREEN HANDLING SYSTEM, GATES, CONTAINERS AND AN ODOR CONTROL SYSTEM. | 2019 | 215884 | 302031.63 | 186 | 0 | 0 | 0 | 0 | 0 | 302217.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-47 | SOUTH BATTERY NEWTOWN CREEK PLANT UPGRADING | CONSENT DECREE UPGRADING AND CONSTRUCTION | 200 | WP-0283 |  |  | RECONSTRUCTION OF EXISTING SOUTH HALF OF THE CENTRAL BATTERY AND SOUTH BATTERY OF GRIT, AERATION AND SEDIMENTATION TANKS. PROCESS AIR SYSTEM UPGRADED TO PROVIDE ADDITIONAL AERATION CAPACITY. AERATION TANKS WILL BE COVERED AND ODOR CONTROLLED. NEW SOUTH CENTRAL BUILDING TO BECONSTRUCTED TO HOUSE PROCESS EQUIPMENT AND ODOR CONTROL SYSTEMS. | 2019 | 664231 | 682637.11 | 816 | 0 | 0 | 0 | 0 | 0 | 683453.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-50 | NEWTOWN CREEK WPCP SLUDGE LOADING DOCKS | CONSENT DECREE UPGRADING AND CONSTRUCTION | 200 | WP-0283 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CONSTRUCTION OF NEWTOWN CREEK WPCP SLUDGE LOADING DOCK AND VESSELS | 2019 | 112624 | 68593.93 | 983 | 0 | 0 | 0 | 0 | 0 | 69576.93 | 83458.4 | 0 | 0 | 0 | 0 | 0 | 0 | 83458.4
20190425 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-110-L | INSTALL VARIABLE FREQ. DRIVES FOR RETURN ACTIVATE SLDG PUMPS | PLANT UPGRADING AND RECONSTRUCTION | 200 | WP-0112 |  |  | INSTALLATION OF VARIABLE FREQUENCY DRIVES FOR THE RETURN ACTIVATE SLUDGE PUMPS AT THE OWLS HEAD WWTP | 2019 | 2650 | 100 | 2400 | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-112-L | REPLACE MAIN SEWAGE PUMPS & PIPING AT OWLS HEAD WPCP | PLANT UPGRADING AND RECONSTRUCTION | 200 | WP-0112 |  | 6700 SHORE ROAD FOOT OF 69TH STREET & THE NARROWS BROOKLYN, N.Y. 11220 | REPLACE MAIN SEWAGE PUMPS & PIPING AT OWLS HEAD WPCP | 2019 | 209700 | 0 | 0 | 23000 | 0 | 0 | 17000 | 169000 | 209000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-88-L | RECONSTRUCTION OF FINAL TANKS AT OWLS HEAD WPCP | PLANT UPGRADING AND RECONSTRUCTION | 200 | WP-0112 |  | 6700 SHORE ROAD, FOOT OF 69TH STREET & NARROWS, BROOKLYN, N.Y. 11220 | RECONSTRUCTION OF FINAL TANKS AT THE OWLS HEAD WPCP | 2019 | 29521 | 0.3 | 0 | 0 | 0 | 0 | 0 | 34500 | 34500.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-91-L | RECONSTRUCTION OF SEA WALL AND DOCK @ OWLS HEAD WWTP | PLANT UPGRADING AND RECONSTRUCTION | 200 | WP-0112 |  | 6700 SHORE ROAD, FOOT OF 69TH STREET & NARROWS, BROOKLYN, N.Y. 11220 | RECONSTRUCTION OF SEA WALL AND DOCK @ OWLS HEAD WWTP | 2019 | 4250 | 6498.07 | 3515 | 1785 | 25801 | 0 | 0 | 0 | 37599.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-92-L | TRC - CONS OF DISINFECTION FACILITIES AT OWLS HEAD WPCP | CONSENT DECREE UPGRADING AND CONSTRUCTION | 200 | WP-0282 |  |  | CONSTRUCTION OF DISINFECTION FACILITEIS AT OWLS HEAD WPCP | 2019 | 12000 | 0 | 0 | 0 | 18991 | 0 | 0 | 0 | 18991 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-95-L | REPLACE #3 ENGINE GENERATOR/SUPPORT SYS. @ OWLS HEAD WPCP | PLANT UPGRADING AND RECONSTRUCTION | 200 | WP-0112 |  | 6700 SHORE ROAD, BROOKLYN, N.Y. 11220 | REPLACEMENT OF #3 ENGINE GENERATOR, SUPPORT SYSTEMS ASSOCIATED SWITCHGEAR AND HEAT RECOVERY UNIT AT OWLS HEAD WPCP. | 2019 | 20500 | 200 | 0 | 0 | 0 | 0 | 20000 | 0 | 20200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-281 | PROSPECT EXPRESSWAY | PLANT UPGRADING AND RECONSTRUCTION | 200 | WP-0269 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | PROSPECT EXPRESSWAY | PROSPECT EXPRESSWAY | 2019 | 19670 | 1500 | 9883 | 0 | 0 | 0 | 0 | 0 | 11383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-316 | RECONSTRUCTION OF AVENUE U PUMPING STATION BROOKLYN | PLANT UPGRADING AND RECONSTRUCTION | 200 | WP-0269 |  | NORTHEAST CORNER OF AVENUE V AND OCEAN PARKWAY BROOKLYN, NEW YORK | RECONSTRUCTION OF AVENUE U PUMPING STATION BROOKLYN, NEW YORK | 2019 | 5300 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-336 | INSTALL ALL ELECTRICAL EQUIPT. ABOVE GROUND @ VAN BRUNT P.S | PLANT UPGRADING AND RECONSTRUCTION | 200 | WP-0269 |  | VAN BRUNT PUMPING STATION - INTERSECTION OF VAN BRUNT STREET AND REEDSTREET, BROOKLYN. N.Y. 11231 | INSTALLATION OF THE CONTROL PANEL, MAIN SEWAGE PUMP STARTERS, FEEDERS, MAIN BREAKERS, TELEMETRY, ETC., ABOVE GROUND AT THE VAN BRUNT PUMPING STATION. ALL THE ELECTRICAL EQUIPMENT SHALL BE INSATLLED ABOVE THE FLOOD ZONE, ABOUT 200 FEET UP REED STREET. THE ENCLOSURES SHALL ADHERE TO PDC RULES. | 2019 | 2350 | 0 | 0 | 1900 | 0 | 0 | 0 | 0 | 1900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-79 | RECONSTRUCT AVE "V" PUMPING STATION | PLANT UPGRADING AND RECONSTRUCTION | 200 | WP-0269 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  |  | 2019 | 178280 | 217981.46 | 2053 | 0 | 0 | 0 | 0 | 0 | 220034.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | REG-30 | REPLACE TIDE GATES AT REGULATOR 26W-02 LOCATED @ 26TH WARD | WATER QUALITY MANDATES | 200 | WP-0169 |  | 12266 FLATLANDS AVENUE, BROOKLYN, N.Y 11270 | RECONSTRUCTION OF 22 TIDE GATES IN REGULATORS LOCATED AT 26TH WARD WWTP. | 2019 | 3250 | 0 | 0 | 2800 | 0 | 0 | 0 | 0 | 2800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | RH-73-L | RECONSTRUCTION OF FINAL TANKS AT RED HOOK WPCP | PLANT UPGRADING AND RECONSTRUCTION | 200 | WP-0112 |  | 63 FLUSHING AVENUE, BROOKLYN, N.Y. 11205 | RECONSTRUCTION OF FINAL TANKS AT THE RED HOOK WPCP | 2019 | 7650 | 0 | 0 | 0 | 0 | 0 | 15000 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | RH-80-L | TRC - DISINFECTION SYSTEM REHABILITATION AT RED HOOK WPCP | CONSENT DECREE UPGRADING AND CONSTRUCTION | 200 | WP-0282 |  | 63 FLUSHING AVENUE, BROOKLYN, NY, 11205-1069 | DISINFECTION SYSTEM REHABILITATION AT RED HOOK WPCP | 2019 | 1076 | 0 | 0 | 0 | 0 | 0 | 0 | 1076 | 1076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | RH-83 | REPLACE MAIN SEWAGE PUMPS AT RED HOOK WPCP | PLANT UPGRADING AND RECONSTRUCTION | 200 | WP-0112 |  |  | REPLACE MAIN SEWAGE PUMPS AT RED HOOK WPCP | 2019 | 25000 | 0 | 0 | 8400 | 0 | 96000 | 0 | 0 | 104400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | RH-90-L | RECONSTRUCT THREE 4160 VOLT MOTOR CONTROL CENTERS @ RED HOOK | PLANT UPGRADING AND RECONSTRUCTION | 200 | WP-0112 |  | 63 FLUSHING AVENUE, UNIT 101, BROOKLYN, NEW YORK 11205-1069 | PROVIDE NECESSARY LABOR, MATERIALS AND EQUIPMENT AS REQUIRED FOR THE UPGRADE/CONSTRUCTION OF THREE (3) 4160 VOLT MCCS AT THE RED HOOK WWTP.WORK INCLUDES, BUT NOT LIMITED TO: DISCONNECT AND REMOVAL OF THREE (3) EXISTING 4160 VOLT MCCS, INSTALL THREE (3) NEW MCCS, INSTALL ONE (1)TEMPORARY MCC FOR CRITICAL LOADS, PERFORM SHORT CIRCUIT/ARC FLASH STUDY, PROVIDE AS-BUILT DRAWINGS, ON-SITE START-UP AND COMMISSIONING. | 2019 | 5433 | 0 | 2995 | 0 | 0 | 0 | 0 | 0 | 2995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | RH-91-L | INSTALL ACCESS CONTROL & DIGITAL VIDEO SURVEILLANCE SYS @ RH | PLANT UPGRADING AND RECONSTRUCTION | 200 | WP-0112 |  |  | DISCONNECT & REMOVE EXISTING VIDEO SURVEILLANCE SYS. THEN INSTALLATION OF FOUR (4) NEW HID CARD READER, ONE (1) DUAL READER INTERFACE, ONE(1) INTELLIGENT DUAL READER CONTROLLER, FOUR (4) CARD READER BACK UP BOX, SIXTEEN (16) PTZ CAMERAS, FOUR (4) 3MP FIXED CAMERAS AND TWO (2) LPR CAMERAS, PROVIDE AS-BUILT DRAWINGS, ON-SITE STRATUP AND COMMISSIONING. THERE ARE TWELVE (12) CAMERAS AND ONE (1) PROXIMITY GATE SYSTEM TO BE REPLACED UNDER THIS PROJECT AT THE RED HOOK WWTP. | 2019 | 1875 | 75 | 1529 | 0 | 0 | 0 | 0 | 0 | 1604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | RH-93-L | RECONSTRUCTION OF TWO ABSORPTION CHILLERS @ RED HOOK WWTP | PLANT UPGRADING AND RECONSTRUCTION | 200 | WP-0112 |  | 63 FLUSHING AVENUE, BROOKLYN, N.Y. 11205 | PROVIDE ALL NECESSARY LABOR, MATERIALS, AND EQUIPMENT FOR DEMOLITION AND REPLACEMENT OF TWO EXISTINGS ABSORPTION CHILLERS, TWO CHILLED WATER PUMPS, TWO EFFLUENT PUMPS, AND ONE HOT WATER PUMP. DEMOLITION OF CORRESPONDING PIPING, PIPE SUPPORTS, VALVES, FITTINGS, ELECTRICAL FEEDERS, AND MONITORING AND CONTROL DEVICES ARE ALSO INCLUDED AT THE RED HOOKWASTEWATER TREATMENT PLANT, BROOKLYN N.Y. | 2019 | 0 | 0 | 0 | 1401 | 0 | 0 | 0 | 0 | 1401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SAND26W | STORM MITIGATION WORK ATTHE 26TH WARD WPCP | PLANT UPGRADING AND RECONSTRUCTION | 200 | WP-0112 |  |  | INSTALLATION OR CONSTRUCTION OF STORM MITIGATION WORK AT 26TH WARD WPCP | 2019 | 20181 | 0 | 0 | 0 | 0 | 0 | 0 | 1718 | 1718 | 0 | 0 | 0 | 0 | 0 | 0 | 15463 | 15463
20190425 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDCI | STORM MITIGATION WORK ATTHE CONEY ISLAND WPCP | PLANT UPGRADING AND RECONSTRUCTION | 200 | WP-0112 |  |  | CONSTRUCTION OF STORM MITIGATION ATTHE CONEY ISLAND WATER POLLUTION CONTROL PLANT | 2019 | 38419 | 0 | 0 | 0 | 0 | 0 | 0 | 3752 | 3752 | 0 | 0 | 0 | 0 | 0 | 0 | 33767 | 33767
20190425 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK002385 | Rehab of Combined brick sewer via guniting 92st & 4 Ave, BK | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 210 | SE-0002K |  |  | REHABILITATION OF 132" COMBINED BRICK SEWER BY GUNITING ALONG 92 ST. B/T RIDGE BLVD. & 4 AVE, BROOKLYN | 2019 | 5645 | 0 | 0 | 0 | 0 | 5645 | 0 | 0 | 5645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK20075 | NEW STORM SEWER IN INDIA ST. | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 200 | SE-0200K |  |  | NEW STORM SEWER IN INDIA ST. | 2019 | 1128 | 0 | 0 | 1128 | 0 | 0 | 0 | 0 | 1128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | WFF-DPR | WATER EFICIENCY UPGRADES AT PROSPECT PARK, BROOKLYN | WATER FOR THE FUTURE | 200 | EP-0009 |  |  | CAPITAL WATER EFICIENCY UPGRADES IN DEPT OF PARKS & RECREATION (DPR) | 2019 | 1407 | 0 | 0 | 836 | 571 | 0 | 0 | 0 | 1407 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-264Y | Brooklyn Cioffe Borough Shop Roof Replacement | GARAGES AND FACILITIES | 200 | S-0136 |  |  | ROOF REPLACEMENT | 2019 | 2300 | 15 | 221 | 0 | 0 | 286 | 2862 | 0 | 3384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-380D | Brooklyn 14 Garage HVAC System Rehabilitation | GARAGES AND FACILITIES | 214 218 | S-0136 |  |  | HVAC REHAB | 2019 | 890 | 0 | 673 | 67 | 0 | 0 | 0 | 0 | 740 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-383G | BROOKLYN CIOFFE SHOP HVAC REPLACEMENT | GARAGES AND FACILITIES | 200 | S-0136 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | HVAC REPLACEMENT | 2019 | 4250 | 5142.17 | 258 | 300 | 0 | 0 | 0 | 0 | 5700.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-427 | Brooklyn 16 922 Georgia Ave Garage Rehabilitation | GARAGES AND FACILITIES | 205 216 | S-0136 |  |  | REHAB | 2019 | 19316 | 0 | 0 | 0 | 999 | 1665 | 16652 | 0 | 19316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-433 | Brooklyn 10 Pier /53rd St Rehab | GARAGES AND FACILITIES | 200 | PU-0200 |  |  | REHAB OF PIER NEEDED FOR SALT STORAGE AND VEHICLE PARKING | 2019 | 3450 | 0 | 0 | 2840 | 14196 | 0 | 0 | 0 | 17036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-451 | Brooklyn Greenpoint Warehouse Pump Replacement | GARAGES AND FACILITIES | 201 | S-0136 |  |  | PUMP REPLACEMENT | 2019 | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-464B | Brooklyn 8 Garage Roof and HVAC Replacement | GARAGES AND FACILITIES | 208 | S-0136 |  |  | ROOF REPLACEMENT | 2019 | 2400 | 55 | 182 | 0 | 0 | 3569 | 0 | 0 | 3806 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-464F | Brooklyn 16 923 Georgia Ave Roof Replacement | GARAGES AND FACILITIES | 205 216 | S-0136 |  |  | ROOF REPLACEMENT | 2019 | 4255 | 217.41 | 17 | 3553 | 0 | 0 | 0 | 0 | 3787.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S186-224 | Brooklyn 3 Garage New Construction | GARAGES AND FACILITIES | 203 | S-0186 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | BEGINNING AT THE INTERSECTION OF NOSTRAND AVE AND MYRTLE AVE, MOVING SOUTH 200' THEN WEST 458' THEN NORTH 200' THEN WEST 508' TO BEGINNING. | NEW DOS GARAGE TO SERVE THE BROOKLYN DISTRICT 3 . | 2019 | 93710 | 17858.89 | 168456 | 0 | 0 | 8356 | 0 | 0 | 194670.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S195-227K | BROOKLYN 7/10 SALT SHED REPLACEMENT | GARAGES AND FACILITIES | 207 210 | S-0195 |  |  | SALT SHED ROOF REPLACEMENT | 2019 | 3226 | 123.23 | 0 | 0 | 3193 | 0 | 0 | 0 | 3316.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S195-228J | Brooklyn Navy Yard Salt Storage Facility Rehabilitation | GARAGES AND FACILITIES | 211 | S-0195 |  |  | REHABILITATION OF ROOF AND FRAME | 2019 | 346 | 0 | 260 | 26 | 0 | 0 | 0 | 0 | 286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S216-403 | MARINE TRANSFER STATION AT HAMILTON AVENUE | SOLID WASTE MANAGEMENT | 200 | S-0216 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES |  | RETROFITTING MARINE TRANSFER STATIONS | 2019 | 104659 | 176668.89 | -54 | 0 | 3326 | 0 | 0 | 0 | 179940.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S216-403A | Hamilton Avenue MTS Bulkhead | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 200 | PU-0200 |  |  | REPLACEMENT OF BULKHEAD WALL BY HAMILTON AVE MTS | 2019 | 6159 | 0 | 1635 | 4524 | 0 | 0 | 0 | 0 | 6159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDBK11C | Hurricane Sandy Brooklyn 11 Conduit Replacement | GARAGES AND FACILITIES | 200 | S-0136 |  |  | CONDUIT | 2019 | 96 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 28
20190425 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDBK4FA | Hurricane Sandy Brooklyn 1/4 Fire Alarm Replacement | GARAGES AND FACILITIES | 201 | S-0136 |  |  | REPLACEMENT OF FIRE ALARM DUE TO HURRICANE SANDY | 2019 | 200 | 50 | 311 | 0 | 0 | 0 | 0 | 0 | 361 | 0 | 688 | 0 | 0 | 0 | 0 | 0 | 688
20190425 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDGPTWH | Hurricane Sandy GRNPT Warehouse R/R & Haz Mitigation | GARAGES AND FACILITIES | 200 | S-0136 |  |  | REPLACE HOT WATER HEATERS, TRANSFORMER BOILER AND OTHER EQUIPMENT ANDRAISE CRITICAL EQUIPMENT TO MITIGATE FLOOD HAZARD | 2019 | 943 | 40 | 29 | 57 | 0 | 0 | 0 | 0 | 126 | 0 | 5 | 310 | 0 | 0 | 0 | 0 | 315
20190425 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDGPWHC | Hurricane Sandy GRNPT Warehouse Conduit Replacement | GARAGES AND FACILITIES | 200 | S-0136 |  |  | REPLACE CONDUIT | 2019 | 295 | 0 | 3 | 74 | 0 | 0 | 0 | 0 | 77 | 0 | 19 | 399 | 0 | 0 | 0 | 0 | 418
20190425 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SOLARDOS3 | PV INSTALLATION ON GARAGE- BROOKLYN | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 201 | PU-0025 |  |  | PV INSTALLATIONS ON A NEW GARAGE CONSTRUCTION | 2019 | 1150 | 0 | 1150 | 0 | 0 | 0 | 0 | 0 | 1150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT601 | DOT - Hamilton Administrative Building | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 201 | PU-0025 |  |  | DOT - HAMILTON ADMINISTRATIVE BUILDING ENERGY EFFICIENT UPGRADES | 2019 | 226 | 17 | 0 | 84 | 0 | 0 | 0 | 0 | 101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT802 | DOT - Parking Garage LED Lighting Upgrade | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 201 | PU-0025 TF-0018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | PARKING GARAGE LED LIGHTING UPGRADE | 2019 | 685 | 0 | 638 | 53 | 0 | 0 | 0 | 0 | 691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | BEDSTLIG | DOT BEDFORD HISTORIC LIGHT RESTORATION | INSTALLATION OF LAMPPOSTS AND LUMINAIRES | 200 | TF-K503 |  |  | DOT BEDFORD HISTORIC DISTRICT LIGHTING RESTORATION: DECORATIVE LIGHTING IN THE BEDFORD DISTRICT | 2019 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | BKBRDGCAM | Brooklyn Bridge Surveillance Cameras | SIGNAL INSTALLATION AND COMPUTERIZATION | 200 | TF-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CAMERAS INSTALLATION FOR BROOKLYN BRIDGE | 2019 | 13447 | 8843.92 | 0 | 0 | 0 | 2209 | 2394 | 0 | 13446.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | BKBRDGITS | Brooklyn Bridge Approaches-DOT ITS | SIGNAL INSTALLATION AND COMPUTERIZATION | 200 | TF-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | ITS FOR BROOKLYN BRIDGE APPROACHES | 2019 | 2276 | 802.21 | 0 | 1474 | 0 | 0 | 0 | 0 | 2276.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBK1023 | MILL BASIN BR / BELT PARKWAY #2-23147-9/TN | FAIR BRIDGES | 218 | HB-1023 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | MILL BASIN BR/BELT PARKWAY, BROOKLYN | RECONSTRUCTION AND REHABILITATION OF THE MILL BASIN BR/ BELT PARKWAY BREPLACEMENT OF DECK INCLUSIVE OF ANY INCIDENTAL STEEL WORK, CURBS ANDSIDEWALKS THE FUNDING FOR THIS PROJECT IS ALL CITY | 2019 | 228336 | 136475.42 | 2871 | 3867 | 10000 | 0 | 0 | 0 | 153213.42 | 183914.13 | 0 | 1306 | 0 | 0 | 0 | 0 | 185220.13
20190425 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBK1201 | ATLANTIC AVENUE/LIRR ATLANTIC AVENUE 2-243569 | FAIR BRIDGES | 202 203 208 216 | HB-1201 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | ATLANTIC AVENUE LIRR | ATLANTIC AVENUE/LIRR | 2019 | 138276 | 29613.19 | 0 | 9377 | 5459 | 0 | 0 | 0 | 44449.19 | 74643.37 | 0 | 7 | 0 | 0 | 0 | 0 | 74650.37
20190425 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBK1205 | RECON OF 5TH AVE BRIDGE OVER LIRR AND SEA BEACH, BR 2-243580 | FAIR BRIDGES | 207 210 | HB-1205 HB-1012 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | RECONS OF 5TH AVE BR OVER LIRR/SEA BEACH, BROOKLYN | RECONS OF 5TH AVE BR OVER LIRR/SEA BEACH, BROOKLYN | 2019 | 12977 | 3532.38 | 0 | 0 | 7544 | 36150 | 0 | 0 | 47226.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBK1213 | RECON UNION ST BRIDGE OVER GOWANUS CANAL, BROOKLYN 2-24027-0 | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 206 | HB-1213 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | RECONSTRUCT UNION STREET BRIDGE OVER GOWANUS CANAL, BROOKLYN | RECONSTRUCT UNION STREET BRIDGE OVER GOWANUS CANAL, BROOKLYN | 2019 | 10839 | 3902.71 | 0 | 2622 | 0 | 45249 | 0 | 0 | 51773.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBK244120 | HILL DR (TERRACE BR) OVER PROSPECT PARK LAKE BIN:2244120 | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 200 | P-0508 |  |  | HILL DR (TERRACE BR) OVER PROSPECT PARK LAKE BIN 2244120 | 2019 | 27776 | 0 | 0 | 855 | 1281 | 3205 | 22435 | 0 | 27776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBK4470 | SEELY STREET OVER PROSPECT AVENUE BIN: 2244470 | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 200 | HB-1070 |  |  | SEELY STREET OVER PROSPECT AVENUE BIN: 2244470 | 2019 | 15815 | 32.22 | 0 | 1647 | 1550 | 4895 | 22617 | 0 | 30741.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBK530 | PARKSIDE AVE AND OCEAN AVE RR BR #2-24302-0 | FAIR BRIDGES | 209 214 | HB-0530 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | REHABILITATION OF THE PARKSIDE AVE AND OCEAN AVE RR BR REPLACEMENT OF, INCLUSIVE OF ANY INCIDENTAL STEEL WORK, RAILING AND SAFETY FENCE THEFOR THIS PROJECT IS 100% CITY | 2019 | 18056 | 8562.4 | 0 | 53 | 10259 | 40328 | 0 | 0 | 59202.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBK643 | BELT PARKWAY OVER GERRITSEN INLET #2-23145-0/X021 39/TRN9020 | FAIR BRIDGES | 215 | HB-0643 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | BELT PARKWAY BR OVER GERRITSEN INLET #2, BROOKLYN | RECONSTRUCTION AND REHABILITATION OF THE BELT PARKWAY OVER GERRITSON IBRIDGE REPLACEMENT OF DECK, INCLUSIVE OF ANY INCIDENTAL STEEL WORK, CUAND SIDEWALK THE FUNDING IS ALL CITY | 2019 | 160696 | 45996.58 | 696 | 304 | 3727 | 0 | 0 | 0 | 50723.58 | 98382.13 | 0 | 0 | 0 | 0 | 0 | 0 | 98382.13
20190425 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA23036 | UNION ST OVER 278I BQE BIN 2230360 | FAIR BRIDGES | 200 | HB-1012 HB-0215 |  | UNION ST OVER 278I BQE BIN 2230360 | UNION ST OVER 278I BQE BIN 2230360 | 2019 | 17111 | 0 | 0 | 0 | 1316 | 0 | 1974 | 13821 | 17111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA23038 | KANE ST/ 278I (BQE) BIN# 2230380 | FAIR BRIDGES | 200 | HB-3038 |  | KANE ST/ 278I (BQE) BIN# 2230380 | KANE ST/ 278I (BQE) BIN# 2230380 | 2019 | 17456 | 0 | 730 | 806 | 0 | 2014 | 14099 | 0 | 17649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA23140 | BSHP over Sheepshead Bay Road BIN 2231409 | FAIR BRIDGES | 200 | HB-1012 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | BSHP OVER SHEEPSHEAD BAY ROAD BIN 22331409 | 2019 | 21822 | 0 | 0 | 699 | 1047 | 0 | 1746 | 18330 | 21822 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA23141 | BSHP over Ocean Ave BIN 2231419 | FAIR BRIDGES | 200 | HB-1012 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | BSHP OVER OCEAN AVE BIN 2231419 | 2019 | 43739 | 0 | 0 | 1505 | 2755 | 0 | 39479 | 0 | 43739 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA23142 | BSHP OVER BEDFORD AVE BIN 2231429 | FAIR BRIDGES | 200 | HB-1012 HB-0215 |  | BSHP OVER BEDFORD AVE BIN 2231429 | BSHP OVER BEDFORD AVE BIN 2231429 | 2019 | 41069 | 0 | 0 | 1764 | 1895 | 0 | 3159 | 33171 | 39989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA23143 | Belt Shore Pkwy over Nostrand Ave 2231439 | FAIR BRIDGES | 200 | HB-1090 |  | BELT SHORE PKWY OVER NOSTRAND AVE 2231439 | BELT SHORE PKWAY OVER NOSTRAND AVE 2231439 | 2019 | 48468 | 0 | 0 | 1976 | 2214 | 0 | 3690 | 5602 | 13482 | 0 | 0 | 0 | 0 | 0 | 0 | 33141 | 33141
20190425 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA23308 | E 14TH ST PED BRIDGE BIN:2233080 | FAIR BRIDGES | 200 | HB-1012 HB-1028 |  | E 14TH ST PED BRIDGE BIN:2233080 | E 14TH ST PED BRIDGE BIN:2233080 | 2019 | 22037 | 805.43 | 0 | 1018 | 0 | 0 | 2543 | 17799 | 22165.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA24310 | Beverly Road over BMT Subway, Brighton BIN 2243100 | FAIR BRIDGES | 200 | HB-4310 |  | BEVERLY ROAD OVER BMT SUBWAY, BRIGHTON BIN 2243100 | BEVERLY ROAD OVER BMT SUBWAY, BRIGHTON BIN 2243100 | 2019 | 47202 | 0 | 0 | 1900 | 2100 | 0 | 5250 | 38452 | 47702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA24382 | 21st Ave RR BR & 64th St #2-24382-1/TN35190 | FAIR BRIDGES | 200 | HB-0061 HB-0548 |  | 21ST AVE RR BR & 64TH ST #2-24382-1/TN35190 | 21ST AVE RR BR & 64TH ST #2-24382-1/TN35190 | 2019 | 110900 | 0 | 0 | 0 | 16338 | 0 | 6000 | 89062 | 111400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBPK17K | 17TH AVENUE PEDESTRIAN BRIDGE OVER BELT PARKWAY 2231300 | FAIR BRIDGES | 210 | P-0956 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | 17TH STREET PEDESTRIAN BRIDGE | 17TH STREET PEDESTRIAN BRIDGE | 2019 | 8006 | 2573.28 | 812 | 20493 | 0 | 0 | 0 | 0 | 23878.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBPK27K | 27TH AVENUE PEDESTRIAN BRIDGE OVER BELT PARKWAY | FAIR BRIDGES | 213 | P-0507 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | 27TH AVENUE PEDESTRIAN BRIDGE | 27TH AVENUE PEDESTRIAN BRIDGE | 2019 | 7473 | 1946.79 | 805 | 20394 | 0 | 0 | 0 | 0 | 23145.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR19C | Citywide Milling - Brooklyn | PRIMARY STREET RESURFACING | 200 | HW-0002K |  |  | CITYWIDE MILLING- BROOKLYN | 2019 | 7478 | 0 | 11239 | 6890 | 0 | 0 | 0 | 0 | 18129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HW349LUM | IN-HOUSE RESURFACING LUMP SUM - ASPHALT | PRIMARY STREET RESURFACING | 299 | HW-0349 HW-D101 HW-D102 HW-D103 HW-D104 HW-0002M HW-0001M | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | RESURFACING ROADWAYS | 2019 | 251043 | 631288.16 | 67989 | 72327 | 33425 | 41841 | 33579 | 226358 | 1106807.16 | 36864.55 | 19624 | 0 | 0 | 0 | 0 | 0 | 56488.55
20190425 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10109 | JORALEMON STREET IMPROVEMENTS | PRIMARY STREET RECONSTRUCTION | 200 | HW-D101 |  | JORALEMON STREET | JORALEMON STREET IMPROVEMENTS | 2019 | 150 | 0 | 0 | 0 | 0 | 0 | 150 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10110 | Strickland Avenue - Reconstruction | PRIMARY STREET RECONSTRUCTION | 200 | HW-D101 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | STRICKLAND AVENUE - RECONSTRUCTION | STRICKLAND AVENUE - RECONSTRUCTION | 2019 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10111 | Intersection Safety Improvements Ocean Parkway & Ave Z | PRIMARY STREET RECONSTRUCTION | 200 | HW-D101 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | INTERSECTION SAFETY IMPROVEMENTS OCEAN PARKWAY & AVE Z | INTERSECTION SAFETY IMPROVEMENTS OCEAN PARKWAY & AVE Z | 2019 | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10113 | Street Reconstruction in Community Board 14 | PRIMARY STREET RECONSTRUCTION | 200 | HW-D101 |  | STREET RECONSTRUCTION IN COMMUNITY BOARD 14 | STREET RECONSTRUCTION IN COMMUNITY BOARD 14 | 2019 | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10115 | Safety Improvements Broadway Corridor | PRIMARY STREET RECONSTRUCTION | 200 | HW-D101 |  | SAFETY IMPROVEMENTS BROADWAY CORRIDOR | SAFETY IMPROVEMENTS BROADWAY CORRIDOR | 2019 | 235 | 0 | 0 | 0 | 0 | 0 | 235 | 0 | 235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10118 | Brighton Beach Avenue Improvements | PRIMARY STREET RECONSTRUCTION | 200 | HW-D101 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | BRIGHTON BEACH AVENUE IMPROVEMENTS | 2019 | 35905 | 0 | 0 | 0 | 0 | 0 | 1905 | 0 | 1905 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10119 | PS 92 SIDE WALK EXTENSION | SIDEWALK RECONSTRUCTION | 200 | HW-D101 |  |  | PS 92 SIDE WALK EXTENSION | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK00502 | 8th Avenue Sunset Park Chinatown Archway | PRIMARY STREET RECONSTRUCTION | 200 | TF-K005 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | 8TH AVENUE SUNSET PARK CHINATOWN ARCHWAY | 8TH AVENUE SUNSET PARK CHINATOWN ARCHWAY | 2019 | 1000 | 0 | 129 | 1871 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK00503 | BQ Green | PRIMARY STREET RECONSTRUCTION | 200 | HW-K005 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | BQ GREEN | BQ GREEN | 2019 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK00504 | Atlantic Avenue - Purchase of WalkNYC Signs | PRIMARY STREET RECONSTRUCTION | 200 202 | HW-K005 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | ATLANTIC AVENUE DISTRICT MANAGEMENT ASSOCIATION, INC.: PURCHASE OF WALKNYC SIGNS | 2019 | 35 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK00512 | Little Red Riding Hood Pre-K Sidewalk Extension | PRIMARY STREET RECONSTRUCTION | 200 | HW-K005 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | LITTLE RED RIDING HOOD PRE-K SIDEWALK EXTENSION | LITTLE RED RIDING HOOD PRE-K SIDEWALK EXTENSION | 2019 | 100 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK00513 | Brooklyn Greenway:Ped Plaza Columbia St Waterfront | PRIMARY STREET RECONSTRUCTION |  | HW-K005 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | COLUMBIA ST WATERFRONT CONSTRUCTION OF PEDESTRIAN PLAZA | 2019 | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK00514 | Brooklyn Greenway:Atlantic Avenue Connector | PRIMARY STREET RECONSTRUCTION |  | HW-K005 HW-0001K HW-D101 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | BIKE LANE CONSTRUCTION | 2019 | 2300 | 0 | 0 | 0 | 0 | 2300 | 0 | 0 | 2300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK1048E | Brooklyn Waterfront Greenway - Commercial Street/Ash Street | PRIMARY STREET RECONSTRUCTION | 200 | HW-D101 HW-0001K | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | BROOKLYN WATERFRONT GREENWAY - COMMERCIAL STREET/ASH STREET | BROOKLYN WATERFRONT GREENWAY - COMMERCIAL STREET/ASH STREET | 2019 | 10300 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 10000
20190425 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK1182 | Belt Parkway Guardrails | PRIMARY STREET RECONSTRUCTION | 200 | HW-0001K |  | BELT PARKWAY GUARDRAILS | BELT PARKWAY GUARDRAILS | 2019 | 0 | 0 | 470 | 0 | 3078 | 0 | 0 | 0 | 3548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK1669B | 4th Ave Safety Improvements - Phase B | PRIMARY STREET RECONSTRUCTION | 200 | HW-0001K |  | 4TH AVE SAFETY IMPROVEMENTS PHASE B - ATLANTIC AVENUE TO 8TH ST | 4TH AVE SAFETY IMPROVEMENTS PHASE B - ATLANTIC AVENUE TO 8TH ST | 2019 | 30000 | 202.59 | 0 | 0 | 0 | 0 | 29813 | 0 | 30015.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK1673 | South Brooklyn Pedestrian and Bicycle Safety Improvements | PRIMARY STREET RECONSTRUCTION | 200 | HW-0001K |  | SOUTH BROOKLYN PEDESTRIAN AND BICYCLE SAFETY IMPROVEMENTS | SOUTH BROOKLYN PEDESTRIAN AND BICYCLE SAFETY IMPROVEMENTS | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 15938 | 0 | 15938 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK1674 | Flatbush Avenue Downtown Brooklyn Safety Improvements | PRIMARY STREET RECONSTRUCTION | 200 | HW-0001K |  | FLATBUSH AVENUE DOWNTOWN BROOKLYN SAFETY IMPROVEMENTS | FLATBUSH AVENUE DOWNTOWN BROOKLYN SAFETY IMPROVEMENTS | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 22563 | 0 | 22563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK715A | VANDERBILT AVE/ATLANTIC INTERS | PRIMARY STREET RECONSTRUCTION | 202 208 | WM-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | VANDERBILT AVENUE AND ATLANTICE AVE INTERSECTION | RECONSTRUCTION AT THE INTERSECTION OF VANDERBILT AND ATLANTIC AVENUES | 2019 | 1908 | 0 | 146 | 0 | 0 | 0 | 0 | 0 | 146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK900 | Brownsville Pedestrian Safety Improvements | PRIMARY STREET RECONSTRUCTION | 200 | HW-0001K |  | BROWNSVILLE PEDESTRIAN SAFETY IMPROVEMENTS | BROWNSVILLE PEDESTRIAN SAFETY IMPROVEMENTS | 2019 | 10400 | 0 | 0 | 0 | 0 | 0 | 10400 | 0 | 10400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKF029Z | FLATLANDS YARD AND STRUCTURES REHABILITATION | FACILITY RECONSTRUCTION | 218 | HW-0003 |  | FLATLANDS YARD AND STRUCTURES REHABILITATION | REBUILD EXISTING 23000 SQ OF GARAGE AND AUTO REPAIR SHOP SPACE | 2019 | 11545 | 0 | 0 | 0 | 1050 | 10495 | 0 | 0 | 11545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKF2514 | 25 14th St Fleet Services Shop Rehabilitation | FACILITY RECONSTRUCTION | 200 | HW-0003 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | 25 14TH ST FLEET SERVICES SHOP REHABILITATION | 2019 | 3300 | 0 | 0 | 3300 | 0 | 0 | 0 | 0 | 3300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKFHAWF | Hamilton Ave - DOT Asphalt Plant (Waterfront) | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 200 | PU-0200 |  | HAMILTON AVE - DOT ASPHALT PLANT (WATERFRONT) | HAMILTON AVE - DOT ASPHALT PLANT (WATERFRONT) | 2019 | 5575 | 0 | 0 | 5068 | 0 | 0 | 0 | 0 | 5068 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWPEDSF4A | Multi-Site Pedestrian Safety - Phase 4A | PRIMARY STREET RECONSTRUCTION | 200 | HW-0001 HW-0001Q | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | MULTI-SITE PEDESTRIAN SAFETY - PHASE 4A | MULTI-SITE PEDESTRIAN SAFETY - PHASE 4A | 2019 | 4123 | 0 | 0 | 3932 | 0 | 0 | 0 | 0 | 3932 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 2500
20190425 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWPR19KC | Complex Upgrades Ped Ramp - Brooklyn | PEDESTRIAN RAMP CONSTRUCTION | 200 | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | COMPLEX UPGRADES PED RAMP - BROOKLYN | COMPLEX UPGRADES PED RAMP - BROOKLYN | 2019 | 7705 | 0 | 545 | 0 | 7238 | 0 | 0 | 0 | 7783 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWSIDEST | RECON OFSIDEWALKS AND STREET LIGHTS IN BROOKLYN(SIM) | PRIMARY STREET RECONSTRUCTION | 200 | HW-0001K | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | SIDEWALKS AND STREET LIGHTS RECONSTRUCTION IN BROOKLYN | 2019 | 181 | 0 | 0 | 181 | 0 | 0 | 0 | 0 | 181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWSRT200E | Safe Routes to Transit: 86th Street | PRIMARY STREET RECONSTRUCTION | 200 | HW-D101 |  | SAFE ROUTES TO TRANSIT: 86TH STREET | SAFE ROUTES TO TRANSIT: 86TH STREET | 2019 | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | PV262FTA1 | BCM - FTA Streetscape Enhancements - DOT Streetlighting | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | PV-D262 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | 145 BROOKLYN AVENUE, BROOKLYN , NY | DOT STREET LIGHT REPLACEMENT | 2019 | 375 | 1.15 | 0 | 0 | 0 | 36 | 0 | 0 | 37.15 | 222 | 0 | 0 | 0 | 0 | 0 | 0 | 222
20190425 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | SANDBULK1 | Reconstruction of Bay & Corbin Bulkheads - Hurricane Sandy | PRIMARY STREET RECONSTRUCTION | 200 | HW-0001K | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | BAY PARKWAY AND CORBIN PLACE IN BROOKLYN | RECONSTRUCTION OF BAY PARKWAY AND CORBIN PLACE BULKHEADS - HURRICANE SANDY | 2019 | 801 | 0 | 0 | 0 | 0 | 0 | 0 | 81 | 81 | 0 | 0 | 0 | 0 | 0 | 0 | 720 | 720
20190425 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TF18-2017 | AVENUE M MUNICIPAL PARKING FIELD | Parking Meters, Lots, and Garages | 200 214 | TF-0018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | RECON OF PARKING FIELD | 2019 | 570 | 0 | 0 | 0 | 0 | 218 | 0 | 0 | 218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TF50311 | Rpl St lg pl Bedford Ave fm Campus Rd to Foster Ave-XMA165.3 | INSTALLATION OF LAMPPOSTS AND LUMINAIRES | 200 | TF-0503 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | REPLACEMENT OF STANDARD STREET LIGHTING WITH BC TYPE LAMP POSTS ON BEDFORD AVENUE FROM CAMPUS ROAD TO FOSTER AVENUE | 2019 | 254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 254 | 0 | 0 | 0 | 0 | 0 | 254
20190425 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TF50313 | Instl lg on Cortelyou Rd&Newkirk XMA193.30 & A835 | INSTALLATION OF LAMPPOSTS AND LUMINAIRES | 200 | TF-0503 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | FURNISH AND INSTALL LIGHT ON CORTELYOU RD & NEWKIRK AVENUE BETWEEN CONEY ISLAND AVE AND OCEAN AVENUE IN BROOKLYN | 2019 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 400
20190425 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TF50315 | Historic St lg poles on Mermaid Avenue bet W21St &W29th St, | INSTALLATION OF LAMPPOSTS AND LUMINAIRES | 200 | TF-0503 |  |  | HISTORIC STREET LIGHT POLES, BENCHES, AND TREE GUARDS ALONG MERMAID AVENUE BETWEEN WEST 21ST STREET AND WEST 29TH STREET. | 2019 | 400 | 0 | 0 | 400 | 0 | 0 | 0 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503K26 | FLATBUSH AVE. ST. PURCHASE AND INSTALLATION OF LAMP POST | INSTALLATION OF LAMPPOSTS AND LUMINAIRES | 200 | TF-D503 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | FLATBUSH AVE. ST. PURCHASE AND INSTALLATION OF LAMP POST | FLATBUSH AVE. ST. PURCHASE AND INSTALLATION OF LAMP POST | 2019 | 450 | 344.75 | 0 | 125 | 0 | 0 | 0 | 0 | 469.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TFK50313 | Historic Lighting on Broadway btw Roebling and Bedford | INSTALLATION OF LAMPPOSTS AND LUMINAIRES | 200 201 | TF-K503 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | HISTORIC LIGHTING ON BROADWAY BTW ROEBLING AND BEDFORD | THE WILLIAMSBURG SAVINGS BANK - 175 BROADWAY HOSPITALITY LLC HAS AGREED TO A MAINTENANCE CONTRACT WITH DOT TO PAY EXTRA WATTAGE - REPLACEMENT OF 18 LAMP POSTS WITH HISTORIC LIGHTING FIXTURES ALONG BROADWAY BETWEEN ROEBLING AND BEDFORD STREETS IN WILLIAMSBURG. | 2019 | 290 | 0 | 0 | 290 | 0 | 0 | 0 | 0 | 290 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TFKVANDMD | VANDERBILT AVE MERCHANTS DISTRICT/PHNDC: ELEGANT STREET LIG | INSTALLATION OF LAMPPOSTS AND LUMINAIRES |  | TF-K503 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | ELEGANT STREET LIGHTING FOR VANDERBILT AVE MERCHANTS DISTRICT | 2019 | 615 | 545.33 | 0 | 70 | 0 | 0 | 0 | 0 | 615.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TFLGAVEU | St Lg on Ave U from Ocean Pkwy to McDonald Ave XMA206.30A | INSTALLATION OF LAMPPOSTS AND LUMINAIRES | 200 | TF-0503 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | FURNISH AND INSTALL ST LIGHT ON AVENUE U | 2019 | 508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 508 | 0 | 0 | 0 | 0 | 508
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | BKPARK | BROOKLYN BRIDGE PARK - PHASE I BG-38150-101M | WATERFRONT DEVELOPMENT | 202 | ED-0075 |  | BROOKLYN BRIDGE PARK - PARKS PHASE I | BROOKLYN BRIDGE PARK - PARKS PROJECT PHASE I | 2019 | 6840 | 6781.94 | 52 | 0 | 0 | 0 | 0 | 0 | 6833.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | GKBKGI-01 | GI - DSGN & CONS OF PARKLAND RETROFITS IN BROOKLYN | GREEN INFRASTRUCTURE PROGRAM | 200 | WP-0169 |  |  | GI - DSGN & CONS OF PARKLAND RETROFITS IN BROOKLYN | 2019 | 3155 | 410.61 | 1713 | 1851 | 0 | 0 | 0 | 0 | 3974.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | GKBKGI-02 | GI - CONS OF BROOKLYN PARKLAND RETROFITS FY20RP | GREEN INFRASTRUCTURE PROGRAM | 200 | WP-0169 P-D017 |  | BROOKLYN | GI - CONS OF BROOKLYN PARKLAND RETROFITS FY20 | 2019 | 0 | 0 | 1672 | 0 | 0 | 11 | 0 | 0 | 1683 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-CLNE | Neighborhood Dev. Fund - East New York - City Line Park | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 205 | ED-0384 |  | ATLANTIC AVENUE, BETWEEN FOUNTAIN AVENUE AND NORTH CONDUIT AVENUE | NEIGHBORHOOD DEVELOPMENT FUND - CITY LINE PARK | 2019 | 7092 | 4943.83 | 728 | 0 | 0 | 0 | 0 | 0 | 5671.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-CLNKY | NDF - Callahan-Kelly Park (B219-117M) | NEIGHBORHOOD REVITALIZATION | 200 | ED-0384 |  |  | CALAHAN KELLY PARK | 2019 | 18893 | 1924.74 | 16161 | 1878 | 0 | 0 | 0 | 0 | 19963.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-HLDN3 | NDF - Highland Park Eastern Playground R/C | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 | ED-0384 |  |  | RECONSTRUCTION OF THE EASTERN PLAYGROUND AT HIGHLAND PARK, BOROUGH OFKINGS | 2019 | 0 | 0 | 60 | 7747 | 0 | 0 | 0 | 0 | 7807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-HLDN4 | NDF - Highland Park Comfort Station R/C | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 | ED-0384 |  |  | RECONSTRUCTION OF THE COMFORT STATION AT HIGHLAND PARK, BOROUGH OF KINGS | 2019 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-HLDN5 | NDF - Highland Park Pedestrian Improvements Q020-118M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 | ED-0384 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | PEDESTRIAN IMPROVEMENTS ALONG HIGHLAND BOULEVARD, IN HIGHLAND PARK, BOROUGH OF QUEENS | 2019 | 1170 | 0 | 0 | 880 | 0 | 0 | 0 | 0 | 880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-HLND | Neighborhood Dev. Fund - East NY - Highland Park Q020-216M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 205 | ED-0384 P-0896 |  | JAMAICA AVENUE, CRESCENT STREET, CYPRESS HILLS - BOROUGH OF BROOKLYN | NEIGHBORHOOD DEVELOPMENT FUND - HIGHLAND PARK | 2019 | 3120 | 2559.32 | 96 | 0 | 0 | 119 | 0 | 0 | 2774.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200CRSL | PPA- Recon. Carousel | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 206 207 208 209 214 | P-D017 |  | PROSPECT PARK WEST , PARKSIDE AVENUE, BETWEEN FLATBUSH AVENUE, OCEAN AVENUE AND PROSPECT PARK SOUTH WEST | PROSPECT PARK - CAROUSEL RECONSTRUCTION | 2019 | 500 | 90 | 50 | 414 | 36 | 0 | 0 | 0 | 590 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200FITS | PPA- Prospect Park Fitness Playground/Equipment (B068-119M) | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 | P-D017 |  | PROSPECT PARK PARADE GROUND | PROSPECT PARK PARADE GROUND - INSTALL ADULT FITNESS EQUIPMENT | 2019 | 1023 | 0 | 69 | 0 | 831 | 0 | 0 | 0 | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200HPPP | PPA - Harmony Playground Improvements B073 | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 | P-D017 |  |  | INSTALL SHADE STRUCTURE OVER SANDBOX AND REPLACE NON WORKING PLAYGROUND STUCTURES WITH VIABLE EQUIPMENT | 2019 | 532 | 0 | 102 | 0 | 321 | 27 | 0 | 0 | 450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200LFHH | PPA- Restor. Lefferts Historic House | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 206 207 208 209 214 | P-D017 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | PROSPECT PARK WEST, PARKSODE AVENUE, BETWEEN FLATBUSH AVENUE, OCEAN AVENUE AND PROSPECT PARK SOUTHWEST. | PROSPECT PARK - LEFFERTS HISTORIC HOUSE | 2019 | 2500 | 29 | 395 | 2105 | 0 | 0 | 0 | 0 | 2529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200LMBF | PPA Long Meadow Ballfields restoration 34 acre ballfield | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-D017 P-0412 |  |  | BALLFIELD | 2019 | 1033 | 11 | 132 | 0 | 1305 | 113 | 0 | 0 | 1561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200LONG | PPA - LONG MEADOW BALLFIELDS RENOV, B073-214M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 206 207 208 209 214 200 | P-D017 | PROJECT DELAYED DUE TO UNFORESEEN HAZARDOUS CONDITION | BROOKLYN | THE RENOVATION OF THE LONG MEADOW BALLFIELD IN PROSPECT PARK | 2019 | 2836 | 2471.48 | -26 | 0 | 210 | 0 | 0 | 0 | 2655.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPBL | PPA- Long Meadow Ballfields 4-5 (B073-215M) | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 206 207 208 209 214 | P-D017 |  | PROSPECT PARK WEST, PARKSIDE AVENUE, BETWEEN FLATBUSH AVENUE, OCEAN AVENUE AND PROSPECT PARK SOUTH WEST. | PROSPECT PARK - LONG MEADOW | 2019 | 750 | 206 | 1250 | 0 | 0 | 0 | 0 | 0 | 1456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPFB | PPA - Flatbush Avenue Park Perimeter B073-315M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 206 207 209 209 214 | P-D017 P-K001 P-K011 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | PROSPECT PARK WEST, PARKSIDE AVENUE, BETWEEN FLATBUSH AVENUE, OCEAN AVENUE & PROSPECT PARK SOUTH. BOROUGH OF BROOKLYN | PROSPECT PARK ALLIANCE-FLATBUSH AVENUE PARK PERIMETER RESTORATION | 2019 | 400 | 2151.78 | 0 | 0 | 284 | 0 | 0 | 0 | 2435.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPMB | PPA-Building Reconstruction | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 | P-D017 P-0412 |  | PROSPECT PARK- BOROUGH OF BROOKLYN | PROSPECT PARK BUILDING | 2019 | 6093 | 78 | 770 | 0 | 4365 | 0 | 0 | 0 | 5213 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPMO | PPA- New M&O Facility & Compound in Prospect Park B073-415M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 206 207 208 209 214 | P-D017 P-K001 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES | PROSPECT PARK WEST, PARKSIDE AVENUE BETWEEN FLATBUSH AVENUE, OCEAN AVENUE, PROSPECT PARK SOUTH. BOROUGH OF BROOKLYN.. | PROSPECT PARK ALLIANCE - NEW MAINTENANCE AND OPERATIONS FACILITY AND COMPOUND IN PROSPECT PARK | 2019 | 2000 | 552.51 | 0 | 2977 | 0 | 0 | 0 | 0 | 3529.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPOC | PROSPECT PARK ALLIANCE: RESTORATION TO OCEAN AVE PERIMETER | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 | P-K011 P-D017 P-K001 P-0412 HW-0001K |  | PPA-OCEAN AVENUE PERIMETER | PROSPECT PARK ALLIANCE: RESTORATION TO OCEAN AVE PERIMETER | 2019 | 1750 | 318 | 809 | 1000 | 2184 | 6471 | 0 | 0 | 10782 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPOP | PPA - Prospect Park Oriental Pavilion B073-416M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 | P-D017 P-C412 P-K001 P-K011 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES | BOROUGH OF BROOKLYN | PROSPECT PARK | 2019 | 2362 | 339.6 | 2152 | 0 | 0 | 0 | 0 | 0 | 2491.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPPH | PPA- PROSPECT PARK PICNIC HOUSE RENOVATION B073-114M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 206 207 208 209 214 200 | P-K001 P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BOROUGH OF BROOKLYN | INSTALLATION OF AIR CONDITIONING IN THE PICNIC HOUSE | 2019 | 1000 | 168.78 | 0 | 400 | 150 | 0 | 0 | 0 | 718.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PRUN | PPA- Multiside, Drinking Fountain, BBQ Pits, Running Land | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 206 207 214 208 209 | P-D017 |  | PROSPECT PARK WEST, PARKSIDE AVENUE, BETWEEN FLATBUSH AVENUE, OCEAN AVENUE AND PROSPECT PARK SOUTH WEST | PROSPECT PARK - CONSTRUCTION OF A RUNNER'S PATH | 2019 | 136 | 15 | 355 | 0 | 0 | 0 | 0 | 0 | 370 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200ROSE | PPA- Prospect Park Rose Garden | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 | P-D017 |  | BOROUGH OF BROOKLYN | PROSPECT PARK ROSE GARDEN | 2019 | 1182 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200STFP | PPA - Parade Ground replace turf field 9 | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-D017 |  |  | PARADE TURF | 2019 | 1011 | 11 | 110 | 0 | 624 | 0 | 0 | 0 | 745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200WCST | PPA-WELLHOUSE COMFORT STATION RENOVATION - (B073-209M) | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 207 | P-D017 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES | PROSPECT PARK, FLATBUSH, OCEAN | RENOVATION OF WELLHOUSE COMFORT STATION IN PROSPECT PARK | 2019 | 900 | 2512.38 | 46 | 50 | 0 | 0 | 0 | 0 | 2608.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200ZO10 | Prospect Park Zoo - Renovation of Discovery Trail | ZOOS | 209 | P-D017 P-0884 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | PROSPECT PARK, BOROUGH OF BROOKLYN | PROSPECT PARK ZOO - RECONSTRUCTION OF THE DISCOVERY TRAIL | 2019 | 337 | 0 | 0 | 100 | 808 | 0 | 0 | 0 | 908 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200ZO17 | PPZ- Building "D" Dome Restoration | ZOOS | 200 | P-K011 P-0887 |  | PPZ- BUILDING"D" DOME RESTORATION | PPZ- BUILDING"D" DOME RESTORATION | 2019 | 164 | 0 | 0 | 175 | 1300 | 0 | 0 | 0 | 1475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200ZO18 | PPZ- Off exhibit primate holding expansion | ZOOS | 200 | P-0887 |  | PPZ- OFF EXHIBIT PRIMATE HOLDING EXPENSION | PPZ- OFF EXHIBIT PRIMATE HOLDING EXPENSION | 2019 | 180 | 0 | 650 | 0 | 0 | 0 | 0 | 0 | 650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200ZO19 | PPZ- Central plaza stairs,benches reconstraction | ZOOS | 200 | P-0887 |  | PPZ- CENTRAL PLAZA STAIRS,BENCHES RECONSTRACTION | PPZ- CENTRAL PLAZA STAIRS,BENCHES RECONSTRACTION | 2019 | 250 | 0 | 0 | 650 | 2800 | 0 | 0 | 0 | 3450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201D17C | ROBERTO CLEMENTE BALLFIELD (FY08 FUNDS) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 201 | P-D017 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | ROBERTO CLEMENTE BALLFIELD, BROOKLYN | ROBERTO CLEMENTE BALLFIELD, BROOKLYN | 2019 | 375 | 0 | 0 | 0 | 0 | 0 | 0 | 290 | 290 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201EYCK | TEN EYCK PLAZA - RENOVATION OF THE PLAZA | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-D017 |  |  | RENOVATION OF PLAZA | 2019 | 591 | 91 | 0 | 0 | 0 | 1331 | 0 | 500 | 1922 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201MCBH | McCarren -RC Bathhouse B058-117M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 201 | P-1018 |  | LOCATED N. 12 STREET, LORIMER STREET, MANHATTAN AVENUE, BETWEEN BAYARD STREET, AND BERRY STREET-NASSAU AVENUE, IN THE BOROUUGH OF BROOKLYN. | MCCARREN | 2019 | 3090 | 312.32 | 711 | 1 | 12111 | 1167 | 0 | 0 | 14302.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201MCC2 | McCarren Park - Brooklyn | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-0819 |  |  | MCCARREN PARK - BROOKLYN | 2019 | 6500 | 0 | 0 | 0 | 5520 | 480 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201MCGK | McGolrick Park - Sidewalk Replacement | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 201 | P-D017 P-1018 |  | RUSSELL STREET, MONITOR STREET, BETWEEN NASSAU AVENUE AND DRIGGS AVENUE | MCGOLRICK PARK - SIDEWALK REPLACEMENT | 2019 | 684 | 249 | 0 | 1854 | 27 | 0 | 0 | 0 | 2130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201MCSF | Mccarren Soccer Field Resurface B058-116M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 | P-0819 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | NORTH 12 STREET, LORIMER STREET, MANHATTAN AVENUE, BETWEEN BAYARD STREET & BERRY STREET- NASSAU | MCCARREN SOCCER FIELD | 2019 | 5080 | 4201.41 | 60 | 0 | 0 | 0 | 0 | 0 | 4261.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201MRCY | Marcy Green Park - Brooklyn | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-0245K |  |  | MARCY GREEN PARK - BROOKLYN | 2019 | 5673 | 0 | 484 | 0 | 0 | 0 | 4716 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201REIN | RIDGEWOOD BUSHW.- BEAVER NOLL PARK BG38500-113M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 201 200 | P-1018 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES | BOROUGH OF BROOKLYN | RIDGEWOOD BUSHWICK SENIOR CITIZENS COUNCIL INC - RHEINGOLD PARK | 2019 | 2000 | 3279.24 | 102 | 0 | 0 | 173 | 0 | 0 | 3554.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201STRN | Sternberg Park Upgrades B055-117M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 201 | P-D017 |  | LORIMER STREET, BETWEEN MONTROSE AVENUE AND BOERUM STREET. BROOKLYN | STERNBERG PARK | 2019 | 2600 | 472 | 0 | 2821 | 279 | 0 | 0 | 0 | 3572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201WILL | William Sheridan - Brooklyn- B124-119M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-0245K |  |  | WILLIAM SHERIDAN - BROOKLYN | 2019 | 8500 | 0 | 0 | 184 | 0 | 7816 | 0 | 0 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202018A | Brooklyn Bridge Park | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 202 | P-K011 P-1200 P-D017 P-K001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BROOKLYN BRIDGE PARK PHASE 3 | BROOKLYN BRIDGE PARK PHASE 3 - FY'16 SECTION 254 ADDS $70K ( P D017)...FY18 ADOPTION ADDS $1,500M (P K011)...FY18 SEPT NYS OPRHP GRANT FOR $500K RECEIVED FOR BBP & $ FY18 SEPT 740K NYS ESD MARKET NY GRANT FOR $740K RECEIVED FOR BBP...FY'19E SECTION 211 ADDS $500K ( P K011)..FY'19 ADOPTION RESCINDS $500K (P K011) SECTION 211 ADD & ADDS $1.5M ( P D017) & $1.0M ( P 1200)..6/28/18 B/L P-1018 CHANGED TO P-1200... | 2019 | 61561 | 273120.85 | 1500 | 5000 | 0 | 0 | 0 | 0 | 279620.85 | 3400 | 1240 | 0 | 0 | 0 | 0 | 0 | 4640
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202BARY | COMMODORE BARRY PARK REHAB (B021-110M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 202 | P-D017 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | FLUSHING AVENUE | RENOVATION OF COMMODORE BARRY PARK | 2019 | 2200 | 2389.53 | 0 | 0 | 0 | 0 | 104 | 0 | 2493.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202BRDG | Bridge Park- Adult Fitness, Multi Purpose Play (B223J-118M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-1018 |  | JAY AND BQE, JAY STREET, PROSPECT STREET, BRIDGE STREET | BRIDGE PARK | 2019 | 8908 | 636 | 0 | 0 | 0 | 0 | 0 | 0 | 636 | 0 | 264 | 6736 | 0 | 0 | 0 | 0 | 7000
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202C974 | FORT GREENE PK PRISONSH MARTYRS MONU&BR EAGL B32-103MA,203MA | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 202 | P-0245K | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | MYRTLE AND DEKALB AVENUES; CUMBERLAND ST CD#35 | FY'15 TRF $27K (P C974) TRF TO P-205LIND...$13K (P C974) TRF TO P-213ASRL...$41K (C974) TRF TO P-2PLG15A...FY'17 SEPT PLAN PER GRANTS UNIT, $7K GRANT ZEROED OUT...$10K PC974 FY17 TRSF TO P-204HOPE...$45K TRF TO P-2PWBFTG...FY'20J ROLLS $76K FR FY'20 TO FY'23... | 2019 | 4655 | 4100.1 | 0 | 0 | 0 | 0 | 0 | 0 | 4100.1 | 267.5 | 0 | 0 | 0 | 0 | 76 | 0 | 343.5
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202CAD2 | Cadman Plaza Park - Brooklyn | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-0245K |  |  | CADMAN PLAZA PARK - BROOKLYN | 2019 | 6900 | 0 | 0 | 0 | 0 | 6400 | 0 | 0 | 6400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202CADM | CADMAN PLAZA (RC L/S SURROND BKLN WAR MEM. BLDG ACCESS) | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 | P-1018 P-K011 P-0245K P-D017 |  | TILLARY, C PLAZA WEST, C PLAZA EAST, PROSPECT STREETS | CADMAN PLAZA - RECONSTRUCT LANDSCAPE SURROUNDING BROOKLYN WAR MEMORIAL INCLUDE BUILDING ACCESS...2/20/19 $80K P-K011 FY23 XFER FROM P-2PLRQ12 | 2019 | 265 | 179.36 | 1805 | 629 | 117 | 0 | 700 | 0 | 3430.36 | 249.67 | 371 | 0 | 0 | 0 | 0 | 0 | 620.67
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202CHAP | CHAPIN PLAYGROUND -RECON. SPRINKLER BG-311M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 202 200 | P-D017 P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | COLUMBIA HTS AT MIDDAGH STREET, BOROUGH OF BROOKLYN | RECONSTRUCTION OF THE SPRINKLER | 2019 | 50 | 21 | 118 | 0 | 0 | 0 | 0 | 0 | 139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202CRIS | CRISPUS ATTUCKS PLGD PH 2 CTS FENC & LGHTS (B102-112M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 202 203 200 | P-D017 | PROJECT DELAYED DUE TO UNFORESEEN HAZARDOUS CONDITION | FULTON STREET AND CLASSON AVENUE | RECONSTRUCTION OF BASKETBALL COURTS, FENCING SECURITY LIGHTING IN CRISPUS ATTUCKS PLAYGROUND | 2019 | 2500 | 2173.68 | 0 | 906 | 0 | 0 | 0 | 0 | 3079.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202D17B | MCLAUGHLIN PARK BALLFIELD,WDG POOL AREA,BSKTBL&HNDB,B61-105M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 202 | ED-0075 |  | MCLAUGHLIN PARK, BROOKLYN | MCLAUGHLIN PARK BASEBALL FIELD | 2019 | 3005 | 2399.66 | 183 | 0 | 0 | 0 | 0 | 0 | 2582.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202FROG | THOMAS CUITE PARK - WATER FOUNTAIN IN PLAYGROUND | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-D017 |  |  | WATER FOUNTAIN | 2019 | 295 | 45 | 0 | 0 | 0 | 150 | 0 | 0 | 195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202FTGP | FT. GREENE PK- PATHS,ENTRANCE RC & DRAINAGE B032-116M) | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 200 202 | P-D017 P-1018 P-K011 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | MYRTLE AVENUE, DE KALB AVENUE, WASHINGTON PARK & ST. EDWARDS STREET IN THE BOROUGH OF BROOKLYN. | THE RECON. OF ENTRANCE TO FT. GREENE PK & DRAINAGE IMPROVE. | 2019 | 500 | 773 | 0 | 4897 | 471 | 0 | 0 | 0 | 6141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202WASH | Washington Hall Playground basketball courts, Brooklyn | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-0245K |  |  | WASHINGTON HALL PLAYGROUND BASKETBALL COURTS, BROOKLYN | 2019 | 1655 | 0 | 0 | 0 | 0 | 1400 | 0 | 0 | 1400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202WPDR | Washington Park Dog Run B111-118M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-K011 P-D017 |  |  | DOG RUN | 2019 | 473 | 73 | 0 | 0 | 100 | 485 | 0 | 0 | 658 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203CHRL | Charlie's Place Reconstruction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-0245K P-D017 |  |  | PARKS - CHARLIE'S PLACE: CONVERT ASPHALT FIELD TO SYNTHETIC TURF; MONDO PERIMETER TRACK, FENCING AND SIDEWALKS ON HOPKINS AND ELLERY. RECONSTRUCT EXISTING BASKETBALL COURT, HANDBALL COURT, COMMUNITY GARDEN, FENCING AND SIDEWALK | 2019 | 1182 | 0 | 0 | 0 | 0 | 1076 | 0 | 0 | 1076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203D17E | Von King cultural arts center - phase 3 B088-111MA | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 203 | P-1018 P-1250 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | HERBERT VON KING PARK CULTURAL ARTS CENTER | VON KING PARK CULTURAL ARTS CENTER PHASE 3 | 2019 | 1000 | 4882.11 | 99 | 57 | 699 | 750 | 0 | 0 | 6487.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203FULT | FULTON PARK - RESTORATION OF COMFORT STATION B038-116M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 203 200 | P-D017 P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | BROOKLYN - FULTON STREET, CHAUNCEY STREETS STUYVESANT AND LEWIS AVENUES | FULTON PARK - RESTORATION OF COMFORT STATION | 2019 | 2820 | 1932.82 | 0 | 0 | 0 | 1395 | 0 | 0 | 3327.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203SRTG | Saratoga Park - Repave Paths & Plaza area - B079 | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 203 | P-D017 |  | HALSEY STREET BETWEEN HOWARD AVENUE AND SARATOGA AVENUE IN THE BOROUGH OF BROOKLYN | SARATOGA PARK- REPAVE ALL PATHS AND PLAZA AREAS, NEW BENCHES, SITTINGAREAS, PICNIC TABLES, DRINKING FOUNTAINS AND GROUND HYDRANTS. IMPROVESECURITY LIGHTING. RECONSTRUCT SMALL PLAYGROUND. PRUNE TREES, IMPROVELANDSCAPING AND CREATE LOW-FENCE ENTRY. | 2019 | 2528 | 0 | 0 | 0 | 0 | 2183 | 0 | 0 | 2183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-204GRCK | Green Central Knoll - Comfort Station B395-115M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-1018 P-D017 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | FLUSHING AVENUE, CENTRAL AVENUE, NOLL STREET, EVERGREEN STREET. BOROUGH OF BROOKLYN | GREEN CENTRAL KNOLL - COMFORT STATION | 2019 | 750 | 3449.17 | 32 | 0 | 426 | 0 | 0 | 0 | 3907.17 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 350
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-204HECK | Heckscher Playground (B139-115M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-D017 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | LINDEN STREET BET. CENTRAL AVE AND WILSON AVE. BOROUGH OF BROOKLYN.. | HECKSCHER PLAYGROUND - SYNTHETIC TURF FIELD ATHLETIC TRAN AND AN ADULT FITNESS AREA | 2019 | 2610 | 2072.2 | 0 | 0 | 0 | 0 | 446 | 0 | 2518.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-204HOPE | Hope Ballfields (B429-116M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 204 | P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | KNICKEBOCKER AVENUE, BETWEEN GROVE STREET AND MENAHAN STREET IN THE BOROUGH OF BROOKLYN | HOPE BALLFIELDS. | 2019 | 4331 | 4012.21 | 150 | 0 | 0 | 1 | 122 | 0 | 4285.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-204RUDD | Rudd Play. - Con. Skate Park & Bask. ball cts | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 204 | P-1018 P-D017 P-K011 |  | ABERDEEN STREET, FURMAN AVENUE, NORTH OF BUSHWICK IN THE BOROUGH OF BROOKLYN | RUDD PLAY | 2019 | 1448 | 355 | 2983 | 0 | 0 | 0 | 0 | 0 | 3338 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205CYPS | Cypress Park - Renovation of Cypress Park B103-116M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-1018 P-K011 P-D017 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | EUCLID AVENUE BETWEEN DUMONT AVENUE & BLAKE AVENUE, BOROUGH OF BROOKLYN | RENOVATION OF CYPRESS PARK | 2019 | 4000 | 5718.58 | 0 | 0 | 0 | 646 | 0 | 0 | 6364.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205GRPG | Grace Playground Park Renovation Phase I B078-119M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-D017 |  |  | GRACE PLAYGROUND PARK RENOVATION PHASE I | 2019 | 1973 | 0 | 173 | 0 | 0 | 1635 | 142 | 0 | 1950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205HLND | Highland Park Basketball Courts R/C Q020-116MA | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 205 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | JAMAICA AVENUE, CRESCENT STREET, CYPRESS HILLS - BOROUGH OF BROOKLYN | HIGHLAND PARK - BASKETBALL COURTS RENOVATION | 2019 | 600 | 1246.32 | 0 | 0 | 0 | 91 | 0 | 0 | 1337.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205HPSB | Highland Park Stone Bridge | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 | P-D019 |  |  | HIGHLAND PARK STONE BRIDGE | 2019 | 5068 | 55 | 0 | 0 | 0 | 4060 | 0 | 0 | 4115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205LION | Lion's Pride Playground - B107-119M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-0245K P-D017 |  |  | LION'S PRIDE PLAYGROUND - BROOKLYN | 2019 | 4727 | 0 | 95 | 0 | 3712 | 340 | 0 | 0 | 4147 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205SBRO | Sperandeo Brothers playground B163-110M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 205 200 | P-D017 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | BOROUGH OF BROOKLYN | NEW PLAY EQUIPMENT AND RECONSTRUCT COMFORT STATION | 2019 | 2200 | 2369.15 | 0 | 0 | 0 | 0 | 105 | 0 | 2474.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205SHNK | Schenk Playground - B261 | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 205 200 | P-D017 P-K011 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | LIVONIA AVENUE BETWEEN BARBEY STREET & SCHENK AVENUE | SCHENK PARK | 2019 | 2527 | 194 | 0 | 194 | 0 | 1945 | 0 | 937 | 3270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206ENIS | Ennis Playground - B095-116M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | BROOKLYN - 11 STREET, 12 STREET, BETWEEN 2 AVNUE & 3RD AVENUE | ENNIS PLAYGROUND | 2019 | 2836 | 3160.96 | 0 | 0 | 0 | 336 | 0 | 0 | 3496.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206GDAM | Restoration of Grand Army Plaza Arch, Bailey Ftn, &SRND AREA | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-1141 |  | RESTORATION OF GRAND ARMY PLAZA ARCH, BAILEY FTN, &SRND AREA | RESTORATION OF GRAND ARMY PLAZA ARCH, BAILEY FTN, &SRND AREA | 2019 | 9495 | 0 | 706 | 0 | 0 | 8289 | 0 | 0 | 8995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206ICKE | HAROLD ICKES PLGRD PH 1 | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-K011 P-D017 |  |  | BIKE, SKATE PARK | 2019 | 3726 | 399.96 | 0 | 0 | 3253 | 0 | 0 | 0 | 3652.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206MARY | St. Mary's Plgd. Play Equip. Recon. Safety Surf. B118-115M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 206 | P-D017 P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | SMITH STREET, BETWEEN NELSON AND HUNTINGTON STREET, BOROUGH OF BROOKLYN | RECONSTRUCTION OF ST MARY'S PLAYGROUND. | 2019 | 850 | 1241.95 | 0 | 0 | 0 | 204 | 0 | 0 | 1445.95 | 850 | 0 | 0 | 0 | 0 | 0 | 0 | 850
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206RH02 | Red Hook - Oversight 9 | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 200 | P-0245K |  | BROOKLYN | RED HOOK - OVERSIGHT 9 | 2019 | 3300 | 0 | 1028 | 1272 | 1000 | 0 | 0 | 0 | 3300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206RHBF | Red Hook - Ball field 9/Soccer 2 (B126-117M) | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 200 | P-0245K |  | BROOKLYN | RED HOOK - BALL FIELD 9/SOCCER 2 | 2019 | 18836 | 2115.77 | 0 | 17035 | 1402 | 0 | 0 | 0 | 20552.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206RHBS | Red Hook Track 1/Soccer 3 & Ballfields 1-4 | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 200 | P-0245K |  |  | REMEDIATION AND RECONSTRUCTION OF TRACK 1, SOCCER 3 AND BALLFIELDS 1-4 AT RED HOOK PARK. | 2019 | 50380 | 4626.02 | 0 | 21974 | 40434 | 0 | 0 | 0 | 67034.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206RHO1 | Red Hook- EPA Oversight 5-8 | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 200 | P-0245K |  | RED HOOK BROOKLYN | RED HOOK | 2019 | 3300 | 0 | 1041 | 1259 | 1000 | 0 | 0 | 0 | 3300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206RHSF | Red Hook - Soccer 1 & 6 | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 200 | P-0245K |  | LOCATED AT HALLECK STREET, BUSH STREET, BETWEEN OTSEGO STREET AND COURT STREET IN THE BOROUGH OF BROOKLYN | RED HOOK RECREATION AREA | 2019 | 21196 | 25 | 0 | 2000 | 0 | 17661 | 1535 | 0 | 21221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206SMRY | St. Mary's Playground (B118-116M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 206 | P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | SMITH STREET BETWEEN NELSON STREET AND HUNTINGTON STREET - BROOKLYN | ST MARY'S PLAYGROUND | 2019 | 927 | 1297.5 | 31 | 0 | 0 | 387 | 0 | 0 | 1715.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206WASH | J.J. Byrne Park - Synthetic Turf (B111-117M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 206 | P-1018 |  | 5 STREET, 4 STREET, BETWEEN 4 AVENUE AND 5 AVENUE | WASHINGTON PARK | 2019 | 300 | 312.96 | 0 | 0 | 160 | 0 | 0 | 0 | 472.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207BTFY | Butterfly Garden - B255G | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 207 | P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | BROOKLYN - 7TH AVENUE, BETWEEN 17 STREET AND 18 STREET | BUTTERFLY GARDEN | 2019 | 650 | 892.38 | 0 | 0 | 0 | 62 | 0 | 0 | 954.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207JAPN | JOHN ALLEN PAYNE PLAYGROUND (B210-115M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-D017 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | 3 AVENUE, BETWEEN 64 STREET AND 65 STREET. BOROUGH OF BROOKLYN | JOHN ALLEN PAYNE PLAYGROUND | 2019 | 1500 | 3499 | 121 | 0 | 0 | 380 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207OPML | Ocean Parkway Malls - RC B065 | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 | P-D017 P-K011 |  |  | OCEAN PARKWAY MALLS - RC | 2019 | 2129 | 0 | 194 | 0 | 0 | 1917 | 0 | 0 | 2111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207RAIN | Rainbow Playground - Playground Update B265 | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 207 | P-D017 |  | 6 AVENUE, BETWEEN 55 STREET AND 56 STREET.. BOROUGH OF BROOKLYN | RAINBOW PLAYGROUND UPGRADE | 2019 | 591 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207SNST | Sunset Park - Benches -B087-116M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 207 200 | P-K011 P-D017 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | BROOKLYN - 41 STREET, 44 STREET BETWEEN 5 AVENUE & 7 AVENUE | SUNSET PARK | 2019 | 1090 | 1368.12 | 252 | 0 | 0 | 206 | 0 | 0 | 1826.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207SPHD | HANDBALL COURT RENOVATIONS AT SUNSET PARK | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-D017 |  |  | HANDBALL COURT RENOVATION | 2019 | 682 | 45 | 23 | 0 | 0 | 477 | 0 | 0 | 545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207SSAF | Sunset Park - Adult Fitness | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 207 200 | P-D017 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | BROOKLYN - 41 STREET, 44 STREET BETWEEN 5TH AND 7TH AVENUE | SUNSET PARK ADULT FITNESS | 2019 | 590 | 497.72 | 0 | 0 | 160 | 0 | 0 | 0 | 657.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207SSPK | Sunset Park - Renovation - B087-117MA | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 207 | P-D017 P-0245K |  | 41STREET 44 STREET, BETWEEN 5 AVENUE AND 7 AVENUE. BROOKLYN | SUNSET PARK RENOVATIONS | 2019 | 500 | 99 | 0 | 534 | 45 | 0 | 0 | 0 | 678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207SUNS | SUNSET PARK PLAYGROUND RC B087-112M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 207 200 | P-1018 P-D017 | PROJECT DELAYED DUE TO UNFORESEEN HAZARDOUS CONDITION | 41 STREET TO 44 STREET, 5TH AVENUE TO 7TH AVENUE IN THE BOROUGH OF BROOKLYN | RECONSTRUCT SUNSET PARK PLAYGROUND | 2019 | 2000 | 4245.54 | 43 | 0 | 0 | 9 | 0 | 0 | 4297.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208BROW | Brower Park - Reconstruction of basketball courts -B012-117M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-D017 P-K011 |  | ST. MARK'S AVENUE, PARK PLACE BETWEEN BROOKLYN AVENUE AND KINGSTON AVENUE. BROOKLYN | BROWER PARK | 2019 | 952 | 126 | 845 | 0 | 0 | 0 | 0 | 0 | 971 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208HVAC | ST. JOHNS HVAC UPGRADE-B245-114M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 208 | P-1250 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 1251 PROSPECT PLACE, BOROUGH OF BROOKLYN | THE UPGRADE OF THE HVAC IN ST JOHNS RECREATION CENTER | 2019 | 2568 | 4168.1 | 45 | 0 | 0 | 332 | 0 | 0 | 4545.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208K11E | St. John's Recreation Center - comfort station (B245-111M) | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 208 200 | P-D017 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | TROY AVENUE, BERGEN, PROSPECT PL, SCHENECTADY AVENUE | IMPROVEMENTS AND RENOVATION OF THE COMFORT STATION IN THE PARK | 2019 | 750 | 2198 | 2 | 0 | 0 | 173 | 0 | 0 | 2373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208LIN2 | Lincoln Terrace Park - Brooklyn | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-0245K |  |  | LINCOLN TERRACE PARK - BROOKLYN | 2019 | 4737 | 0 | 0 | 0 | 3660 | 340 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208LTCS | Lincoln Terrace- Comfort Station B054-115M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 208 | P-D017 P-1018 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES | EASTERN PARKWAY, EAST NEW YORK AVENUE BETWEEN ROCHESTER AVENUE AND PORTAL STREET. BOROUGH OF BROOKLYN. | LINCOLN TERRACE COMFORT STATION | 2019 | 2000 | 386.54 | 0 | 3508 | 351 | 0 | 0 | 0 | 4245.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208STFE | ST. JOHNS REC CENTER - OUTDOOR FITNESS EQUIPMENT | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-D017 |  |  | OUTDOOR FITNESS EQUIPMENT | 2019 | 682 | 10 | 0 | 0 | 460 | 40 | 0 | 0 | 510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208STUD | CPI PH 1- Stroud Playground (B350-115M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 208 200 | P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | BOROUGH OF BROOKLYN | PARK UPGRADES AND RENOVATIONS | 2019 | 100 | 5790.94 | 0 | 0 | 0 | 101 | 0 | 0 | 5891.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-209D017 | PARKSIDE (P.S. 92) PLAYGROUND (B267-109M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 209 | P-D017 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | PARKSIDE (PS 92) PLAYGOUND, BROOKLYN, CB 9 | PARKSIDE (PS 92) PLAYGROUND RECONSTRUCTION | 2019 | 0 | 1744.19 | 0 | 0 | 0 | 0 | 45 | 0 | 1789.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-209WNGE | Wingate Park - Basketball Courts | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 209 | P-D017 P-K011 P-1018 |  | WINTHROP STREET, BROOKLYN AVENUE, RUTLAND ROAD | WINGATE PARK - BASKETBALL COURTS | 2019 | 250 | 401 | 0 | 2203 | 0 | 0 | 0 | 0 | 2604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210245A | OWL'S HEAD PK - GREENWAY CONNECTOR B066-108M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 210 | P-0245K | PROJECT DELAYED DUE TO UNFORESEEN HAZARDOUS CONDITION | BROOKLYN CB 10 AT FORT HAMILTON PARKWAY AND 94TH STREET | JJ CARTY PARK OFFICE | 2019 | 1100 | 346.87 | 0 | 0 | 0 | 0 | 0 | 0 | 346.87 | 1045.53 | 0 | 0 | 0 | 0 | 44 | 0 | 1089.53
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210D17T | SHORE ROAD PATHWAY BICYCLE PATH | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 210 200 | PU-0200 P-D017 P-0501 P-K011 P-1130 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BOROUGH OF BROOKLYN | SHORE ROAD PATHWAY | 2019 | 250 | 18 | 1190 | 0 | 0 | 3320 | 4180 | 0 | 8708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210DBSF | Dyker Beach Park- Soccer Field B028-116M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 210 200 | P-D017 |  | 86 STREET, BELT PARKWAY, BETWEEN BAY 8 STREET 14 AVEUE AND 7TH AVENUE, BROOKLYN | DYKER BEACH SOCCER FIELD | 2019 | 2954 | 2172.43 | 0 | 0 | 672 | 0 | 0 | 0 | 2844.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210FTHM | Ft. Hamilton Courts - RC of Bsktball & Tennis Cts -B192A | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 210 | P-0245K |  | 83 STREET TO 85 STREET, BETWEEN COLONIAL ROAD AND NARROWS AVENUE, IN THE BOROUGH OF BROOKLYN | THE RECONSTRUCTION OF 2 BASKETBALL COURTS; PHASE 3 RECONSTRUCTION OF 3 TENNIS COURTS | 2019 | 2600 | 0 | 0 | 0 | 0 | 2200 | 0 | 0 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210JCAR | John J. Carty Tennis Courts | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 210 | P-1018 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES | FORT HAMILTON PARKWAY, BETWEEN 94 STREET AND 101STREET, BOROUGH OF BROOKLYN | JOHN J. CARTY TENNIS COURTS | 2019 | 1000 | 2891.82 | 75 | 0 | 148 | 0 | 0 | 0 | 3114.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210SHCP | SHORE ROAD CONSERVANCY PARK | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-0973 |  |  | SHORE ROAD PARK | 2019 | 1308 | 0 | 0 | 0 | 0 | 1270 | 0 | 0 | 1270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210SHOR | SHORE ROAD PK - PERIMETER SIDEWALKS (B082A-110M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 210 | P-0245K | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BOROUGH OF BROOKLYN | PARK IMPROVEMENTS AND RENOVATIONS TO THE SIDEWALKS | 2019 | 1800 | 127.08 | 0 | 0 | 0 | 0 | 0 | 0 | 127.08 | 1182.46 | 0 | 0 | 0 | 0 | 122 | 0 | 1304.46
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210SHRD | Shore Road Pk- Rehab C/S -Field House B082-116M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 210 | P-D017 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES | 4TH AVENUE, SHORE ROAD, BELT PARKWAY,. BOROUGH OF BROOKLYN. | SHORE ROAD PARK- REHABILITATE COMFORT STATION/FIELD HOUSE | 2019 | 5250 | 587.13 | 3739 | 0 | 0 | 0 | 0 | 0 | 4326.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210SHRE | Shore Road park- Install. fence erosion contrl. B082 | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 200 210 | P-1018 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES | 4 AVENUE. SHORE RD, BELT PKWY, VERRAZANO BRIDGE | FY'15 INSTALLATION OF STEEL FENCE GATES, VEGETATION REMOVAL, PLANTINGS AND EROSION CONTROL | 2019 | 1364 | 996.29 | 0 | 0 | 173 | 0 | 0 | 0 | 1169.29 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 1000
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-211BBCH | BATH BEACH PARK - PH2 and PH3 | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-D017 |  |  | RECONSTRUCTION | 2019 | 5592 | 82 | 0 | 0 | 0 | 5400 | 0 | 0 | 5482 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-211BNHT | Bensonhurst Park - B007-118M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 211 200 | P-0245K P-D017 P-0742 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BROOKLYN - CROPSEY AVENUE BETWEEN 21 AVENUE AND BAY PARKWAY | BENSONHURST PARK | 2019 | 800 | 675.67 | 1343 | 5917 | 0 | 0 | 0 | 0 | 7935.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-212ALBE | Albemarle Playground - Resurface Soccer Field B297 | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 212 | P-D017 P-K011 |  | ALBEMARLE ROAD, DAHILL ROAD, MCDONALD AVENUE IN THE BOROUGH OF BROOKLYN | ALBEMARLE PLAYGROUND - RESURFACE SOCCER FIELD - REPLACE DAMAGED, HAZARDOUS TURF IN JOP... | 2019 | 591 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-212CLDM | Colonel David Marcus playground - CS B128-115M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-D017 |  | BOROUGH OF BROOKLYN | COMFORT STATION IN COLONEL DAVID MARCUS PLAYGROUND | 2019 | 1000 | 750.74 | 19 | 19 | 391 | 0 | 0 | 0 | 1179.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-212DOME | Dome Playground - phase I (B151-112M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 212 200 | P-D017 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | N E CORNER 38 STREET AND DAHILL ROAD | RECONSTRUCT PLAYGROUND WITH NEW PLAY EQUIPMENT, SWINGS, SAFETY SURFACE, PAVEMENT, FENCES, LIGHTING, BENCHES AND PLANTED AREAS | 2019 | 900 | 2770.06 | 0 | 0 | 0 | 576 | 0 | 0 | 3346.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-212FRFD | Friends Field - B372-116M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 212 | P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | BROOKLYN - AVENUE L, EAST 4 STREET, MCDONALD AVENUE, AVENUE M | FRIENDS FIELD | 2019 | 1680 | 3063.64 | 0 | 0 | 252 | 0 | 0 | 0 | 3315.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-212GRVD | Gravesend Pk - RC parkhouse B042-112M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 212 200 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 18TH AVENUE TO 19TH AVENUE AND 56 STREET TO 58 STREET IN THE BOROUGH OF BROOKLYN | GRAVESEND PARK RECONSTRUCTION | 2019 | 1800 | 2453.91 | 8 | 3 | 0 | 154 | 0 | 0 | 2618.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213ALAE | Asser Levy Park - Adult Exercise Equipment (B080-118M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-D017 |  |  | ADULT EXERCISE EQUIPMENT | 2019 | 914 | 121 | 0 | 0 | 0 | 670 | 0 | 0 | 791 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213ALVY | Asser Levy Park - B080 | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 213 | P-D017 P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | BOARDWALK, SURF AVENUE, SEA BREEZE AVENUE, OCEAN PARKWAY BROOKLYN | ASSER LEVY PARK | 2019 | 3780 | 4357.14 | 38 | 0 | 327 | 321 | 0 | 0 | 5043.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213BABI | BABI YAR Triangle - Reconstruction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-D017 |  |  | RECONSTRUCTION | 2019 | 1636 | 100 | 0 | 0 | 0 | 1200 | 0 | 0 | 1300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213BOIL | ABE STARK BOILERS AND CHILLERS (B169-111M) | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 213 200 | P-D017 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | BOROUGH OF BROOKLYN | ABE STARK BOILERS AND CHILLERS | 2019 | 1000 | 2683.84 | 0 | 0 | 0 | 47 | 1537 | 0 | 4267.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213SCRN | Scarangella Park C/S CONS B106-117M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 213 200 | P-0245K | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES | WEST 13 STREET, STILLWELL AVENUE, BETWEEN AVENUE U & AVENUE V | RECONSTRUCTION OF SCARANGELLA PARK | 2019 | 2400 | 441.5 | 0 | 0 | 2394 | 0 | 0 | 0 | 2835.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213SNPK | PARKS - SCARANGELLA PARK RENOVATION PARKS - SCARANGEll | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-D017 P-K011 |  |  | RECONSTRUCTION | 2019 | 1182 | 182 | 285 | 0 | 0 | 3215 | 0 | 0 | 3682 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213SURF | SURF PLAYGROUND - PLAYGROUND RENOVATION (B315-118M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-D017 |  |  | PLGD RENOVATION | 2019 | 4092 | 545 | 106 | 0 | 0 | 3088 | 0 | 0 | 3739 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213WEST | West Playground | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 213 | P-D017 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES | AVENUE Z, BETWEEN WEST 1 STREET AND WEST STREET, BOROUGH OF BROOKLYN | WEST PLAYGROUND | 2019 | 1800 | 387.35 | 0 | 1519 | 0 | 0 | 0 | 0 | 1906.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214KNDR | PPA-Kensington Dog Run in the Parade Grounds (B068-) | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 214 | P-D017 P-K011 |  | PARADE GROUND- PARKSIDE AVENUE, CATON AVENUE, BETWEEN PARADE PLACE AND CONEY ISLAND AVENUE- BOROUGH OF BROOKLYN | PPA- KENSINGTON DOG RUN | 2019 | 467 | 141.41 | 337 | 0 | 0 | 0 | 0 | 0 | 478.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214KOLB | KOLBERT PLAYGROUND - RC (B150-115M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 214 200 | P-D017 P-K011 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | BOROUGH OF BROOKLYN - AVENUE L, EAST 17 STREET TO E. 18 STREET. | AVENUE L KOLBERT PLAYGROUND - PARK RENOVATION | 2019 | 600 | 3593.68 | 0 | 0 | 484 | 650 | 0 | 0 | 4727.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214KPKP | Kolbert Park RC Perimeter B150 | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-D017 |  | RC PERIMTER SIDEWALKS | KOLBERT PARK RC PERIMETER | 2019 | 473 | 0 | 0 | 0 | 0 | 400 | 0 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214LTFN | Lt. Federico Navaez Tot Lot- RC B397-117M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 214 | P-D017 P-1018 |  | ARGYLE ROAD AND CORTELYOU ROAD. BROOKLYN | LT. FEDERICO NAVAEZ TOT LOT | 2019 | 950 | 173 | 988 | 0 | 0 | 99 | 0 | 0 | 1260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214RIDE | PPA - GALLOPNYC- RIDING RING IN PROSP. PK | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 214 200 | P-D017 P-K001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BROOKLYN - PARKSIDE AVENUE, CATON AVENUEM BETWEEN PARADE PLACE AND CONEY ISLAND AVENUE. | PROJECT TO BUILD A RIDING ARENA IN PROSPECT PARK | 2019 | 2900 | 0.14 | 0 | 800 | 0 | 2740 | 0 | 0 | 3540.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214UMMA | Umma Park & Plg Reconstruction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-K001 P-K011 |  |  | UMMA PARK AND PLAYGROUND REHABILITATION: PARK GROUNDS REHABILITATION | 2019 | 295 | 0 | 0 | 600 | 0 | 0 | 0 | 250 | 850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215BBPG | BILL BROWN PLAYGROUND FLDHSE CMFT ST. FY'10 B109-112M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 215 200 | P-1018 P-D017 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | BEDFORD AVENUE BETWEEN AVENUE X & AVENUE Y | RECONSTRUCT FIELD HOUSE INCLUDING NEW REST ROOMS AND COMMUNITY SPACE. | 2019 | 1400 | 5023.28 | 916 | 0 | 0 | 148 | 0 | 0 | 6087.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215HCPL | HOMECREST PLAYGROUND: RECONSTRUCT/EXPAND PLAYGROUND | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-K011 P-1018 P-D017 |  | HOMECREST PLAYGROUNG | HOMECREST PLAYGROUND: RECONSTRUCT/EXPAND PLAYGROUND | 2019 | 2200 | 650.65 | 749 | 1891 | 398 | 0 | 0 | 0 | 3688.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215KELL | KELLY PARK | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-1072 P-K011 |  |  | KELLY PARY | 2019 | 1761 | 168 | 0 | 0 | 0 | 0 | 0 | 1425 | 1593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215KLLY | Kelly Playground - Renovate | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 215 | P-D017 |  | AVENUE S. MORRE PLACE BETWEEN E 16 STREET AND E17 STREET | KELLY PLAYGROUND - RENOVATION PLAYGROUND | 2019 | 2843 | 0 | 0 | 0 | 0 | 2501 | 0 | 0 | 2501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215MBGD | MANHATTAN BCH. COMM. GARDEN & DOG RUN | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 215 200 | P-D017 P-0245K | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES | BOROUGH OF BROOKLYN | MANHATTAN BEACH COMMUNITY GARDEN & DOG RUN- REPLACE CURRENT DOG RUN WITH COMMUNITY GARDEN & RELOCATE DOG RUN & REDUCE ITS SIZE | 2019 | 500 | 156 | 778 | 0 | 0 | 0 | 0 | 0 | 934 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215MBP2 | Manhattan Beach Park - Ctr Promenade & Beach Entryway Recons | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 | P-1245 |  |  | PHASE 2 | 2019 | 4582 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 0 | 0 | 4582 | 0 | 0 | 0 | 0 | 4582
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215MCDD | McDonald Playground - RC Play Equipment Area B244-118M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 215 | P-D017 P-K011 P-0245K | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BROOKLYN - MCDONALD BETWEEN AVENUE S & AVENUE T | MCDONALD PLAYGROUND | 2019 | 1010 | 499.88 | 0 | 2450 | 244 | 0 | 0 | 0 | 3193.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215MELL | MELLET PLAYGROUND--COMPLETELY RECONSTRUCT PLAYGROUND MELLET | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-D017 |  |  | RECONSTRUCTION | 2019 | 2728 | 30 | 0 | 0 | 0 | 2000 | 0 | 0 | 2030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215MHAT | Manhattan Beach Park B251-115M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 215 | P-0245K P-D017 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | ORIENTAL BLVD, BETWEEN OCEAN AVENUE AND MACKENZIE STREET | MANHATTAN BEACH PARK - PLAYGROUND UPGRADE, FENCING, DOGRUN, BASKETBALL COURTS | 2019 | 1500 | 1716.81 | 0 | 0 | 0 | 168 | 0 | 0 | 1884.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215MHBP | Manhattan Beach promenade | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 | P-D017 P-1018 P-K011 |  | ORIENTAL BLVED BETWEEN OCEAN AVENUE AND MACKENZIE STREET. BROOKLYN | MANHATTAN BEACH PROMENADE | 2019 | 2000 | 400 | 2681 | 262 | 0 | 0 | 0 | 0 | 3343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215PIER | SHEEPSHEAD BAY PIERS | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 200 | PU-0200 P-0501 |  | SHEEPSHEAD BAY PIERS | SHEEPSHEAD BAY PIERS | 2019 | 4096 | 0 | 461 | 0 | 3560 | 75 | 0 | 0 | 4096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216BHFF | Betsy Head - Football Field B008 | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 216 200 | P-D017 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BLAKE AVENUE, DUMONT AVENUE, LIVONIA AVENUE, BETWEEN STRAUSS STREET, HOPKINSON AVENUE & BRISTOL STREET | BETSY HEAD FOOTBALL FIELD | 2019 | 2000 | 182 | 0 | 0 | 2000 | 0 | 0 | 0 | 2182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216BHIP | BETSY HEAD - IMAGINATION PLGD CS B008 | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 | P-0505 P-D017 |  |  | BETSY HEAD - IMAGINATION PLGD CS | 2019 | 2000 | 150 | 0 | 3666 | 334 | 0 | 0 | 0 | 4150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216OCAN | Ocean Hill Playground - Brooklyn | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-0245K |  |  | OCEAN HILL PLAYGROUND - BROOKLYN | 2019 | 5891 | 0 | 479 | 0 | 0 | 4921 | 0 | 0 | 5400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216OSBN | Osborn Playground - Park Renovation | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 216 | P-D017 |  | LINDEN BLVD, OSBORN STREET, ROCKAWAY AVENUE, HEGEMAN AVENUE IN THE BOROUGH OF BROOKLYN | OSBORN PLAYGORUND PARK RENOVATION-CONVERT EXISTING FIELD TO SYNTHETICTURF WITH PERIMETER TRACK AND ACCESS RAMP. | 2019 | 3427 | 0 | 0 | 0 | 0 | 2900 | 0 | 0 | 2900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216PS25 | PS 125 Playground - Brooklyn | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-0245K |  |  | PS 125 PLAYGROUND - BROOKLYN | 2019 | 1064 | 0 | 0 | 0 | 828 | 72 | 0 | 0 | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217D017 | WYCKOFF HOUSE PARK CULT. EDUC. COMPLX B376-113M | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 217 | P-D017 P-K011 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | WYCKOFF HOUSE AND GROUNDS, BROOKLYN | WYCKOFF HOUSE MUSEUM AND SURROUNDING PASSIVE PARK...FY20 JAN PLAN ROLLS: $490K P-K011 TO FY21 FROM FY20 | 2019 | 2250 | 1569.55 | 0 | 0 | 4107 | 357 | 0 | 0 | 6033.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217NOST | Nostrand Playground - B250-117M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 217 200 | P-1018 P-D017 |  | BOROUGH OF BROOKLYN-NOSTRAND AVENUE BETWEEN FOSTER AVENUE AND FARRAGUT PLACE | NOSTRAND PLAYGROUND | 2019 | 3043 | 2067.76 | 0 | 0 | 0 | 645 | 0 | 0 | 2712.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217PAER | PAERDEGAT PK- RECON. BSKT BALL, SIDEWALKS, LIGHTS, B218-112M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 217 200 | P-D017 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | BOROUGH OF BROOKLYN - FOSTER AVENUE, E. 40 -41 STREETS | RECONSTRUCTION OF SIDEWALKS, INSTALLATION OF EQUIPMENT ALONG PATHWAYS. | 2019 | 800 | 1904.16 | 0 | 0 | 0 | 68 | 0 | 0 | 1972.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217PDGT | PAERDEGAT ATHLETIC CLUB - HVAC WORK | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-1018 P-1250 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BOROUGH OF BROOKLYN | PAERDEGAT ATHLETIC CLUB HVAC WORK | 2019 | 1850 | 407.81 | 12 | 10 | 0 | 552 | 0 | 0 | 981.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217PPFR | Paerdegat Park - Field Renovation | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-K011 |  |  | FIELD RENOVATION | 2019 | 840 | 45 | 0 | 0 | 0 | 0 | 0 | 250 | 295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217TILD | TILDEN PLAYGROUND-SHIRLEY CHISHOLM COMM CTR B234 | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-D017 P-K011 P-0245K |  |  | TILDEN PLAYGROUND-SHIRLEY CHISHOLM COMM CTR B234 | 2019 | 7255 | 3012.09 | 0 | 0 | 0 | 48162 | 4187 | 0 | 55361.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217WYKF | WYCKOFF FARMHOUSE - ROOF RESTORATION B376-111M | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 200 | P-0245K | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BOROUGH OF BROOKLYN | FARMHOUSE ROOF RESTORATION | 2019 | 550 | 260.51 | 0 | 0 | 0 | 0 | 0 | 0 | 260.51 | 451.1 | 99 | 0 | 0 | 0 | 0 | 0 | 550.1
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218BILD | Bildersee Playground -B335 | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 218 | P-D017 P-1018 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES | FLATLANDS AVENUE BETWEEN EAST 81 STREET AND EAST 82 STREET, BOROUGH OF BROOKLYN | BILDERSEE PLAYGROUND - MULTIPURPOSE PLAY AREA AND PLAYGROUND | 2019 | 1825 | 3773.62 | 1027 | 1 | 0 | 668 | 0 | 0 | 5469.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218BPLG | Bildersee plgd-new plgd and ph2 | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-K011 P-0245K |  |  | RECONSTRUCTION | 2019 | 3227 | 36 | 0 | 0 | 0 | 0 | 0 | 1367 | 1403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218CCMF | CANARSIE PARK PHASE V- COMFORT STATION B018-214M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 218 200 | P-D017 P-K011 P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | SEAVIEW AVENUE BETWEEN PAERDEGAT BASIN AND EAST 93 STREET, EAST 102 STREET AND FRESH CREEK BASIN | NEW COMFORT STATION FOR CRICKET, SKATE PARK AND PLAYGROUND | 2019 | 850 | 655.48 | 2711 | 0 | 411 | 0 | 0 | 0 | 3777.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218D17S | DR. JOHN'S PLAYGROUND- MARINE PK (B057-114M) | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 218 200 | P-D017 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | BOROUGH OF BROOKLYN -FLATBUSH , GERRITSEN & FILLMORE AVENUES, JAMAICABAY | RECONSTRUCT PLAYGROUND WITH NEW EQUIPMENT, SAFETY SURFACE, ETC. | 2019 | 1200 | 3646.89 | 0 | 0 | 0 | 111 | 0 | 0 | 3757.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218GERT | Marine Park - Gerritsen Ave. Ped. Path PH 2 (B057-117M) | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 218 | P-0245K P-D017 |  | BOROUGH OF BROOKLYN | MARINE PARK GERRITSEN AVENUE PEDESTRIAN PATH PH 2 | 2019 | 500 | 120 | 290 | 0 | 0 | 0 | 0 | 0 | 410 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 500
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218GLEN | Glenwood Playground - recon. multi-purpose area B236-114M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 218 200 | P-D017 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | RALPH AVENUE AND FARRAGUT ROAD, BOROUGH OF BROOKLYN | RECONSTRUCTION ASPHALT MULTI PURPOSE PLAY AREA FOR SOFTBALL, SOCCER AND FOOTBALL. PROJECT WOULD INCLUDE NEW FENCING, DUGOUTS, BENCHES AND DRINKING FOUNTAINS. | 2019 | 1500 | 2045.32 | -280 | 0 | 0 | 280 | 779 | 0 | 2824.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218GOLF | BK Golf Alliance - Marine Pk. Golf Course - B057-415M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 218 200 | P-K011 P-D017 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BOROUGH OF BROOKLYN - FLATBUSH AVENUE, GERRITSEN AVENUE, FILLMORE AVENUE, JAMAICA BAY | BROOKLYN GOLF ALLIANCE INC. - MARINE PARK GOLF COURSE | 2019 | 840 | 262 | 0 | 0 | 1450 | 0 | 0 | 0 | 1712 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218JCOB | Jacob Joffe Playground - B324 | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 218 | P-D017 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | AVENUE K BETWEEN E. 58 STREET & E. 59 STREET. | JACOB JOFFE PLAYGROUND | 2019 | 1064 | 1131.38 | 0 | 0 | 0 | 96 | 0 | 0 | 1227.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218JFEE | Jacob Joffe Playground- Park Renovations | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 | P-D017 P-K011 |  | AVENUE K BETWEEN EAST 58 STREET AND EAST 59 STREET. | JACOB JOFFE PLAYGROUND | 2019 | 3000 | 400 | 2538 | 253 | 0 | 0 | 0 | 0 | 3191 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218LOTT | HENDRICK I. LOTT HOUSE -INTERIOR RESTORATION | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 200 218 | P-D017 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BOROUGH OF BROOKLYN | PHASE 3 - RENOVATION OF THE INTERIOR OF THE HOUSE FOR PUBLIC USE | 2019 | 800 | 131 | 400 | 0 | 1950 | 0 | 0 | 0 | 2481 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218PWMP | Power-Memorial- Seating Area ( B291-) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 218 | P-D017 |  | AVENUE N BETWEEN EAST 49 STREET & UTICA AVENUE | POWER -MEMORIAL PLAYGROUND | 2019 | 250 | 45 | 0 | 0 | 0 | 1350 | 0 | 0 | 1395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218SUNN | Sunners Playground - Renovate Playground | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 218 | P-D017 |  | AVENUE H BETWEEN KINGS HIGHWAY, EAST 49 STREET IN THE BOROUGH OF BROOKLYN | RENOVATION OF PLAYGROUND DEVASTATED BY HURRICANE SANDY - SUNNERS PLAYGROUND | 2019 | 1432 | 0 | 0 | 0 | 0 | 1250 | 0 | 0 | 1250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2ANCH02 | Betsy Head Park Comfort Station Reconstruction | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 | P-0605 |  |  | BETSY HEAD RECONSTRUCTION | 2019 | 4000 | 0 | 0 | 0 | 0 | 2580 | 0 | 0 | 2580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2ANCH03 | Betsy Head Park Syn. Turf, Field, Track, Sport Crts Ft Ctr | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 | P-0605 |  |  | BETSY HEAD | 2019 | 20091 | 0 | 0 | 16650 | 1500 | 0 | 0 | 0 | 18150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2ANCH04 | ANCHOR PARK- Betsy Head Multi-Purpose Play Area Reconst. | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 216 | P-1018 |  |  | BETSY HEAD | 2019 | 7200 | 0 | 5713 | 0 | 0 | 557 | 0 | 0 | 6270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BELTPA | Belt Pkwy Lndscp Restoration & Tree Planting Ph2 B166-113M | LAND ACQUISITION AND TREE PLANTING | 200 | P-0822 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RESTORATION OF LANDSCAPE AND TREE PLANTING ALONG THE BELT PARKWAY | 2019 | 2260 | 8400.36 | 65 | 0 | 0 | 0 | 0 | 0 | 8465.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BELTPC | FY14 Belt Parkway Street Trees | LAND ACQUISITION AND TREE PLANTING | 299 | HB-0643 P-0822 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | BROOKLYN | STREET TREE PLANTING | 2019 | 5826 | 684.23 | 614 | 6264 | 0 | 0 | 0 | 0 | 7562.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BELTPD | CON - BIKE PATH THRU CANARSIE PARK WEST | LAND ACQUISITION AND TREE PLANTING | 200 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BOROUGH OF BROOKLYN | CONSTRUCTION OF BIKE PATH THRU CANARSIE PARK WEST | 2019 | 1550 | 192 | 0 | 0 | 0 | 0 | 0 | 0 | 192 | 1359.89 | 190 | 0 | 0 | 0 | 0 | 0 | 1549.89
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BELTPE | Mill Basin Bridge Trees | LAND ACQUISITION AND TREE PLANTING | 200 | HB-1023 PU-0200 |  | MIL BASIN BRIDGE TREES | MIL BASIN BRIDGE TREES | 2019 | 10429 | 781.95 | 28 | 9710 | 600 | 0 | 0 | 0 | 11119.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BKPAV1 | Brooklyn Multisite Pavement Reconstruction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-1018 |  | BROOKLYN | BROOKLYN MULTISITE PAVEMENT RECONSTRUCTION | 2019 | 2290 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BQGRN | BQ GREEN | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-D017 |  |  | BQ GREEN | 2019 | 11818 | 600 | 0 | 0 | 0 | 0 | 0 | 4400 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BRIGHM | Brigham Park - plgd & passive area B057-212M/512M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 215 218 200 | P-1018 P-D017 P-0245K | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES | BOROUGH OF BROOKLYN | GRIGHAM STREET PARK DESIGN | 2019 | 400 | 5701.21 | 387 | 612 | 0 | 0 | 0 | 0 | 6700.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BWCC04 | BKLYN MULTISITE CMFT STA.- TILDEN & BANNEKER BG-111M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 203 218 | P-D017 P-1018 |  | IN BOROUGH OF BROOKLYN. | RECONSTRUCTION OF COMFORT STATIONS AT BANNEKER AND TILDEN PLAYGROUNDS | 2019 | 1300 | 481.92 | 0 | 0 | 1250 | 0 | 0 | 0 | 1731.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CIBOHQ | Coney Island Beach Operations Headquarters at West 25th St | BEACHES AND BOARDWALKS | 200 | P-0704 |  |  | CONEY ISLAND BEACH OPERATIONS HEADQUARTERS AT WEST 25TH ST | 2019 | 47339 | 0 | 0 | 4588 | 0 | 42751 | 0 | 0 | 47339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CIBWK2 | Coney Island Boardwalk Street Ends (B169-210M) | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 213 | P-0245K | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | CONEY ISLAND BOARDWALK BOROUGH OF BROOKLYN | CONEY ISLAND BOARDWALK STREET ENDS | 2019 | 3098 | 515 | 0 | 0 | 0 | 0 | 0 | 0 | 515 | 2238.27 | 0 | 0 | 1 | 0 | 362 | 0 | 2601.27
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CIBWLK | CONEY ISLAND BOARDWALK (B169-110M) | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 213 | P-0245K | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | CONEY ISLAND BOARDWALK IN THE BOROUGH OF BROOKLYN | CONEY ISLAND BOARDWALK | 2019 | 8745 | 1588.52 | 0 | 0 | 0 | 0 | 0 | 0 | 1588.52 | 7262.23 | 0 | 137 | 0 | 0 | 0 | 0 | 7399.23
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CIGNWY | CONEY ISLAND GREENWAY PROPOSED SAFETEA GRANT | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 213 | P-0007 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | BRIGHTON 15TH STREET & CONEY ISLAND AVE | CONEY ISALAND GREENWAY (AKA BRIGHTON 15TH STREET & CONEY ISLAND AVE | 2019 | 2608 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2560 | 2560
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CIWALK | RECONSTRUCTION OF VARIOUS SEGMENT OF CONEY ISL. BDWLK | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 | P-0007 |  | CONEY ISLAND BOARDWALK IN THE BOROUGH OF BROOKLYN | THE RECONSTRUCTION OF VARIOUS SEGMENTS OF CONEY ISLAND BOARDWALK - KNOWN AS PROPERTY B169.. | 2019 | 9818 | 290.15 | 0 | 0 | 0 | 0 | 0 | 8000 | 8290.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CONYGS | CONEY ISLAND COASTAL RESIL. GREENSTREETS BG-515MA | LAND ACQUISITION AND TREE PLANTING | 200 | P-0822 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BOROUGH OF BROOKLYN | TO STRENGTHEN CONEY ISLAND RESILIENCY THROUHG GREENSTREETS. | 2019 | 990 | 20.97 | 466 | 0 | 0 | 0 | 0 | 0 | 486.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2COOPCS | Cooper Park-Reconstruction of Comfort Station | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-0505 |  |  | COOPER PARK-RECONSTRUCTION OF COMFORT STATION | 2019 | 2243 | 150 | 0 | 0 | 0 | 1645 | 0 | 0 | 1795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIBGB | CPI PH2 - Bergen Beach Reconstruction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 218 | P-1018 |  | BROOKLYN- EAST 71 STREET BETWEEN AVENUE N & AVENUE T | FY'16 PH2. BERGEN BEACH... | 2019 | 5318 | 4344.41 | 147 | 0 | 0 | 0 | 0 | 0 | 4491.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIBN2 | CPI PH1- J. Owens, Stockton & Stroud C/S RC BG-815M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 | P-1018 |  | JESSE OWENS- STUYVESANT & LAFAYETTE AVES.- STOCKTON N- MARCY & PARK AVENUES, STROUD - PARK PLACE, CLASSON AVENUE, STERLING PLACE, WASHINGTON AVENUE, ALL IN THE BOROUGH OF BROOKLYN | THE RECONSTRUCTION OF JESSE OWENS, STOCKTON AND STROUD PLAYGROUND COMFORT STATIONS IN BROOKLYN | 2019 | 315 | 4853.55 | 0 | 0 | 0 | 594 | 0 | 0 | 5447.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIBPG | CPI PH2 - Bartlett Playground | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-1018 |  |  | RECONSTRUCTION OF BARTLETT PLAYGROUND, BOROUGH OF KINGS | 2019 | 9636 | 600 | 0 | 7380 | 670 | 0 | 0 | 0 | 8650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIEPP | CPI PH2 - R/C Epiphany Playground (B405 -116M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 201 | WP-0169 P-1018 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES | BOROUGH OF BROOKLYN - BERRY STREET, BETWEEN SOUTH 9TH STREET, AND SOUTH 10TH STREET (11211) | THE RECONSTRUCTION OF EPIPHANY PLAYGROUND (CPI) | 2019 | 2879 | 260 | 299 | 0 | 0 | 3277 | 0 | 0 | 3836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIJOP | CPI Ph1- RC of Jesse Owens Play. B269-116M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 203 200 | P-1018 P-D017 |  | BROOKLYN- LAFAYETTE AVENUE, BETWEEN STUYVESANT AVENANT & MALCOM X BLVD. | THE RECONSTRUCTION OF JESSE OWENS PLAYGROUND | 2019 | 7472 | 6571.25 | 0 | 0 | 0 | 1219 | 0 | 0 | 7790.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPILAG | CPI ph2. - LaGuardia Playground Ph 2. | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 201 | P-0245K TF-0777 |  | SOUTH 4 STREET BETWEEN ROEBLING STREET AND WILLIAMSBURG GRIDGE RAMP, BOROUGH OF BROOKLYN | RECONSTRUCTION OF LAGUARDIA PLAYGROUND | 2019 | 3545 | 0 | 0 | 0 | 2168 | 732 | 0 | 0 | 2900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPILFT | CPI PH2 - Lafayette Playground Reconstruction (B106B-116M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 213 | P-1018 |  | BROOKLYN - STILLWELL AVENUE, BENSON AVENUE, BAY 43 STREET | FY'16 PH2 RECONSTRUCTION OF OF LAFAYETTE PLAYGROUND... | 2019 | 6086 | 4895.07 | 7 | 0 | 0 | 393 | 0 | 0 | 5295.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPILGD | CPI PH2 - LaGuardia Playground | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 201 | P-0245K |  | SOUTH 4 STREET, BETWEEN ROEBLING STREET AND WILLIAMSBURG BRIDGE RAMP | LA GUARDIA PLAYGROUND | 2019 | 5212 | 461 | 610 | 1980 | 270 | 0 | 0 | 0 | 3321 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPILJP | CPI PH2 - RC- Lt. Joseph Petrosino Park (B099-) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 211 | WP-0169 P-1018 |  | 16TH AVENUE, NEW UTRECHT AVENUE, BETWEEN 70 TH STREET AND 71TH STREET | THE RECONSTRUCTION OF LT. JOSEPH PETROSINO PARK PLAYGROUND | 2019 | 4605 | 4706.49 | 86 | 0 | 0 | 524 | 0 | 0 | 5316.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPINEW | CPI Ph2.- Newport Comfort Station (B339-117M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 216 | P-1018 |  | NEWPORT AVENUE, THATFORD AVENUE AND OSBORN STREET | CPI - PH.2 - NEWPORT COMFORT STATION | 2019 | 1500 | 1187.24 | 52 | 0 | 0 | 350 | 0 | 0 | 1589.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPINPL | CPI-PH2. Newport playground (B339-216M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 216 | WP-0169 P-1018 |  | NEWPORT AVENUE, THATFORD AVENUE AND OSBORN STREET | CPI PH2- NEWPORT PLAYGROUND | 2019 | 3500 | 4193.26 | 39 | 0 | 0 | 668 | 0 | 0 | 4900.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIPEN | CPI PHASE 2 - RC Penn Triangle and Playground B223NC-118M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-1018 |  |  | CPI PHASE 2 PENN TRIANGLE | 2019 | 1520 | 203 | 0 | 1220 | 0 | 0 | 0 | 0 | 1423 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPITEN | CPI Ph1.- Ten Eyck Play. (B311-116M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 201 | WP-0169 P-1018 |  | BROOKLYN- SCHOLES STREET, BETWEEN BUSHWICK AVENUE AND WATERBURY STREET | THE RC OF TEN EYCK PLAYGROUND | 2019 | 5242 | 4356.24 | 201 | 0 | 0 | 100 | 0 | 0 | 4657.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIWKS | CPI PH2- Weeksville Playground | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 203 | P-1018 |  | HOWARD AVENUE, BETWEEN ATLANTIC AVENUE AND HERKIMER STREET | WEEKSVILLE | 2019 | 2061 | 1169.36 | 0 | 0 | 0 | 295 | 0 | 0 | 1464.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2ERSPK1 | E RIVER STATE PARK PARKHOUSE | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 | P-D017 |  |  | EAST RIVER STATE PARK PARKHOUSE: CONSTRUCTION OF A NEW PARKHOUSE COMPLEX | 2019 | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GATE10 | Gateway Estates-Multi-purpose ballfield B548-114M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-0245K |  |  | COMBINING GATEWAY PROJECTS | 2019 | 8377 | 1098.08 | 0 | 0 | 0 | 0 | 7252 | 0 | 8350.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GATEW2 | Gateway Estates - Constru. Plgd & comft. stat. B541-115M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 205 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | GATEWAY ESTATES II - BROOKLYN | GATEWAY ESTATES II | 2019 | 29500 | 6044.61 | 0 | 0 | 77 | 0 | 0 | 0 | 6121.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GATEW6 | Gateway Estates -Cleveland Pk playground (B547- 114M) | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 205 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BOROUGH OF BROOKLYN | CONSTRUCTION OF A PLAYGROUND IN GATEWAY ESTATES- PHASE II | 2019 | 2170 | 10.83 | 0 | 0 | 0 | 0 | 0 | 1678 | 1688.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GPWB25 | Bushwick Inlet Park- Motiva Parcel Remediation | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 200 | P-0839 |  | GREENPOINT WILLIAMSBURG BROOKLYN | GREENPOINT WILLIAMSBURG | 2019 | 11603 | 450 | 990 | 0 | 0 | 8221 | 607 | 0 | 10268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GPWBKT | GPWB- 50 Kent Development | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 | P-0839 |  | BOROUGH OF BROOKLYN | GPWB- KENT DEVELOPMENT | 2019 | 9157 | 1096.24 | 0 | 0 | 6442 | 560 | 0 | 0 | 8098.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GTGRDN | RPZ installation at various sites in Brooklyn | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-1018 P-D017 |  |  | RPZ INSTALLATION | 2019 | 489 | 0 | 0 | 0 | 0 | 724 | 0 | 0 | 724 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2HOOPER | Hooper Street Grove - Install Perimeter Fence | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-D017 |  | BOROUGH OF BROOKLYN | NYC PARKS-HOOPET STREET GROVE - INSTALLING A PERIMETER FENCE AROUND THE GARDEN AT HOOPER STREET | 2019 | 227 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2ISAGRD | ISABAHLIA GARDENS WATER SPIGOT | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-K001 |  |  | CONSTRUCTION OF WATER SPIGOT FOR ISABAHLIA GARDENS IN BROOKLYN. | 2019 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2LINDTF | Linden Park Synthetic Turf Field and Track (B214-117M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-1018 |  | LINDEN PARK | LINDEN PARK SYNTHETIC TURF FIELD AND TRACK | 2019 | 5893 | 4682.03 | 9 | 0 | 0 | 1034 | 0 | 0 | 5725.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2LITCHF | Litchfield Villa - Renovations | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-D017 |  |  | RENOVATION | 2019 | 272 | 3 | 0 | 175 | 0 | 819 | 0 | 0 | 997 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PDBRC2 | Brownsville Rec Ctr RC B270-214M | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 200 | P-1018 |  | BROOKLYN | BROWNSVILLE REC CTR | 2019 | 18000 | 1728.04 | 0 | 0 | 18743 | 0 | 0 | 0 | 20471.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PDSSRC | Sunset Pk Rec Ctr RC B087-115M | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 200 | P-0506 |  | BROOKLYN | SUNSET PK RC | 2019 | 4000 | 654.24 | 0 | 0 | 4354 | 0 | 0 | 0 | 5008.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PEDPLZ | Public Place -Pedestrian Plaza-Eldert & liberty | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-D017 |  | ELDERT LANE BETWEEN LIBERTY AND GLENMORE AVENUES. | PEDESTRIAN PLAZA- ELDERT AVENUE AND LIBERTY AND GLENMORE AVENUE | 2019 | 1000 | 909.52 | 0 | 0 | 0 | 325 | 0 | 0 | 1234.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PGRD11 | MULTISITE- PAVEMTS,TENNIS CTS, BB CTS, FENCING (BG-711M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-D017 P-0245K | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | BOROUGH OF BROOKLYN | MULTISITE- PAVEMENTS, TENNIS COURTS, BASKETBALL COURTS, FENCING , PLANTINGS AND GENERAL SITE WORK AT VARIOUS LOCATIONS IN THE BOROUGH OF BROOKLYN | 2019 | 1576 | 3169.21 | 0 | 0 | 0 | 0 | 631 | 0 | 3800.21 | 192.81 | 0 | 0 | 0 | 0 | 40 | 0 | 232.81
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PLG14D | RECON. CHARLES PINNTRIANGLE - PAVE. CURBS FENCING BG-613M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BOROUGH OF BROOKLYN | CHARLES PINN PLAYGROUND REQUIREMENTS | 2019 | 174 | 250.99 | 0 | 0 | 0 | 74 | 0 | 0 | 324.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PNYC05 | PlaNYC - Calvert Vaux CS/M&O bldg (B125-112M) | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 213 | P-D017 P-0245K P-0507 P-1018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | BOROUGH OF BROOKLYN | CALVERT VAUX | 2019 | 2760 | 848.58 | 4978 | 0 | 4566 | 0 | 0 | 0 | 10392.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PPANEP | Northeast Paths - Prospect Park Alliance | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 | P-0245K |  |  | NORTHEAST PATHS - PROSPECT PARK ALLIANCE | 2019 | 2000 | 33 | 0 | 0 | 219 | 1781 | 0 | 0 | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PPESIT | PROSPECT PARK EXPRESSWAY SITTING AREA RC | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-K001 |  |  | RECONSTRUCT SITTING AREAS INCLUDING WATER SERVICE, BENCHES, SEATING, LANDSCAPING, FENCING, SECURITY LIGHTING, BOLLARDS, FENCING, PAVEMENT. | 2019 | 0 | 0 | 0 | 360 | 0 | 0 | 0 | 0 | 360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PWBFTG | PWOB- Fort Greene | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 | P-1018 P-D017 P-K011 |  | MYRTLE AVENUE, DE KALB AVENUE, BETWEEN WASHINGTON PARK AND ST EDWARDS'S STREET BROOKLYN | FORT GREENE | 2019 | 900 | 737 | 0 | 9373 | 3209 | 0 | 0 | 0 | 13319 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PWBPFB | PWOB- PP Flatbush Avenue (B073-117M) | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 | P-1018 |  | PROSPECT PARK - BOROUGH OF BROOKLYN | PWOB- PROSPECT PARK | 2019 | 3200 | 957.89 | 2580 | 0 | 244 | 0 | 0 | 0 | 3781.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2RHBALL | Red Hook ball fields B126-116M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 206 | P-0245K | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES |  | RED HOOK BALL FIELDS | 2019 | 11690 | 12984.2 | 261 | 0 | 2557 | 0 | 0 | 0 | 15802.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2SANDY | Non FEMA Sandy: Coney Island Coastal Greenstreets, BG-515MA | LAND ACQUISITION AND TREE PLANTING | 200 | P-0822 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | CONEY ISLAND COASTAL RESILIENCE GREENSTREETS (NON-FEMA SANDY), BROOKLYN | CONEY ISLAND COASTAL RESILIENCE GREENSTREETS (NON-FEMA SANDY) | 2019 | 815 | 206 | 0 | 0 | 0 | 0 | 0 | 0 | 206 | 178.98 | 636 | 0 | 0 | 0 | 0 | 0 | 814.98
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2SEAGTE | SEAGATE SHORELINE REMEDIATION | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 213 200 | P-D017 P-0379 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BOROUGH OF BROOKLYN | REMEDIATION OF SHORELINE AT SEAGATE | 2019 | 600 | 0 | 0 | 0 | 0 | 2600 | 0 | 0 | 2600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2SNSTRW | Commodore Barry Park C.S | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-0505 |  |  | COMMODORE BARRY PARK COMFORT STATION | 2019 | 4550 | 0 | 0 | 0 | 0 | 0 | 3574 | 0 | 3574 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2STFHM | Hamilton-Metz Field Synthetic Turf Field Reconstruction | NEIGHBORHOOD PARKS AND PLAYGROUNDS |  | P-0510 |  |  | HAMILTON-METZ FIELD SYNTHETIC TURF FIELD | 2019 | 2133 | 243.47 | 0 | 0 | 0 | 1890 | 0 | 0 | 2133.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2STFMH | Maria Hernandez Park - Synthetic Turf Field (B016-118M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-0510 |  |  | SYNTHETIC TURF FIELD | 2019 | 4642 | 310 | 0 | 0 | 0 | 3404 | 0 | 0 | 3714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2SUCSGN | Success Garden - Park Renovation | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-D017 |  | BOROUGH OF BROOKLYN | SUCCESS GARDEN PARK RENOVATION INCLUDING THE RECONSTRUCTION OF BROKEN ASPHALT AND OVERGROWN SECTION OF PROPERTY | 2019 | 2009 | 0 | 0 | 27 | 0 | 1673 | 0 | 0 | 1700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE17A | FY17 Street Tree Brooklyn1,2,3,4,16, BG- | LAND ACQUISITION AND TREE PLANTING | 200 | P-0822 |  | FY17 STREET TREE BROOKLYN1,2,3,4,16, B | FY17 STREET TREE BROOKLYN1,2,3,4,16, B | 2019 | 1964 | 2211 | 599 | 0 | 0 | 1 | 0 | 0 | 2811 | 379 | 0 | 0 | 0 | 0 | 0 | 0 | 379
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE18A | FY18 Street Tree Brooklyn1,2,3,4,16, BG- | LAND ACQUISITION AND TREE PLANTING | 200 | P-0822 P-1018 |  | FY18 STREET TREE BROOKLYN1,2,3,4,16, BG- | FY18 STREET TREE BROOKLYN1,2,3,4,16, BG- | 2019 | 175 | 23 | 0 | 0 | 0 | 240 | 0 | 0 | 263 | 0 | 0 | 0 | 0 | 1675 | 0 | 0 | 1675
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE18B | FY18 Street Tree Brooklyn1,5,14,18 | LAND ACQUISITION AND TREE PLANTING | 200 | P-0822 |  | FY18 STREET TREE BROOKLYN1,5,14,18 | FY18 STREET TREE BROOKLYN1,5,14,18 | 2019 | 2520 | 2127 | 1190 | 0 | 0 | 0 | 0 | 0 | 3317 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE18C | FY18 Street Tree Brooklyn6,7,9,12 | LAND ACQUISITION AND TREE PLANTING | 200 | P-0822 P-1018 |  | FY18 STREET TREE BROOKLYN6,7,9,12 | FY18 STREET TREE BROOKLYN6,7,9,12 | 2019 | 2057 | 1736 | 0 | 1290 | 0 | 0 | 0 | 0 | 3026 | 231 | 0 | 0 | 0 | 0 | 0 | 0 | 231
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE19B | FY19 Street Tree Brooklyn 8,9,17 BG-416MR | LAND ACQUISITION AND TREE PLANTING | 200 | P-0822 |  | FY19 STREET TREE BROOKLYN 8,9,17 BG-416MR | FY19 STREET TREE BROOKLYN 8,9,17 BG-416MR | 2019 | 1890 | 0 | 990 | 0 | 0 | 0 | 0 | 0 | 990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE19C | FY19 Street Tree Brooklyn11,13,15 BG-516MR | LAND ACQUISITION AND TREE PLANTING | 200 | P-0822 |  | FY19 STREET TREE BROOKLYN11,13,15 BG-516MR | FY19 STREET TREE BROOKLYN11,13,15 BG-516MR | 2019 | 1590 | 0 | 990 | 0 | 0 | 0 | 0 | 0 | 990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE20A | FY20 Street Tree Brooklyn1,2,3,4,, BG-319M | LAND ACQUISITION AND TREE PLANTING | 200 | P-0822 P-D822 P-K822 |  | FY20 STREET TREE BROOKLYN1,2,3,4,, BG-319M | FY20 STREET TREE BROOKLYN1,2,3,4,, BG-319M | 2019 | 2997 | 0 | 0 | 0 | 3207 | 0 | 0 | 0 | 3207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE20B | FY20 Street Tree Brooklyn5,8,16 BG-619M | LAND ACQUISITION AND TREE PLANTING | 200 | P-0822 |  | FY20 STREET TREE BROOKLYN5,8,16 BG-619M | FY20 STREET TREE BROOKLYN5,8,16 BG-619M | 2019 | 2665 | 0 | 0 | 0 | 2665 | 0 | 0 | 0 | 2665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE20C | FY20 Street Tree Brooklyn 6,7,10,12 BG-719M | LAND ACQUISITION AND TREE PLANTING | 200 | SE-0004 P-0822 P-D822 |  | FY20 STREET TREE BROOKLYN 6,7,10,12 BG-719M | FY20 STREET TREE BROOKLYN 6,7,10,12 BG-719M | 2019 | 1275 | 0 | 0 | 231 | 1044 | 0 | 0 | 0 | 1275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE20D | FY20 Street Tree Brooklyn 9,14,17 BG-519M | LAND ACQUISITION AND TREE PLANTING | 200 | P-0822 P-D822 P-K822 |  | FY20 STREET TREE BROOKLYN 9,14,17 BG-519M | FY20 STREET TREE BROOKLYN 9,14,17 BG-519M | 2019 | 3786 | 0 | 0 | 0 | 3450 | 0 | 0 | 0 | 3450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE20E | FY20 Street Tree Brooklyn 11,13 BG-419M | LAND ACQUISITION AND TREE PLANTING | 200 | P-0822 |  | FY20 STREET TREE BROOKLYN 11,13 BG-419M | FY20 STREET TREE BROOKLYN 11,13 BG-419M | 2019 | 1188 | 0 | 0 | 0 | 1188 | 0 | 0 | 0 | 1188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE20F | FY20 Street Tree Brooklyn 15 18 BG-819M | LAND ACQUISITION AND TREE PLANTING | 200 | P-0822 |  | FY20 STREET TREE BROOKLYN 15 18 BG-819M | FY20 STREET TREE BROOKLYN 15 18 BG-819M | 2019 | 2950 | 0 | 0 | 0 | 2950 | 0 | 0 | 0 | 2950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRS19A | BrooklynTree-Damaged Sidewalk R/C CB 7,10-13,15,18 | LAND ACQUISITION AND TREE PLANTING | 200 | P-1331 |  | BROOKLYNTREE-DAMAGED SIDEWALK R/C CB 7,10-13,15,18 | BROOKLYNTREE-DAMAGED SIDEWALK R/C CB 7,10-13,15,18 | 2019 | 1482 | 0 | 1482 | 0 | 0 | 0 | 0 | 0 | 1482 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRSD19 | BrooklynTree-Damaged Sidewalk R/C | LAND ACQUISITION AND TREE PLANTING | 200 | P-1331 |  | BROOKLYNTREE-DAMAGED SIDEWALK R/C | BROOKLYNTREE-DAMAGED SIDEWALK R/C | 2019 | 1524 | 0 | 0 | 1524 | 0 | 0 | 0 | 0 | 1524 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2WPS228 | I.S. 228 Playground Reconstruction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-1018 |  | 228 AVENUE S, BROOKLYN, NY 11223 | I.S. 228 PLAYGROUND RECONSTRUCTION | 2019 | 1508 | 0 | 0 | 1508 | 0 | 0 | 0 | 0 | 1508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-6CADMAR | Recon Marlboro & Cadman Plaza CS | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-0505 P-K011 P-1008 |  | BROOKLYN | RECON MARLBORO & CADMAN PLAZA CS | 2019 | 837 | 0 | 270 | 0 | 2060 | 0 | 0 | 0 | 2330 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-6PNYR01 | PlaNYC-Reforestation:Bklyn-N.Conduit/Atlantic/Sutter BG-608M | LAND ACQUISITION AND TREE PLANTING | 200 | P-0822 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | NORTH CONDUIT BLVD (SUTTER TO ATLANTIC AVES) | PLANYC - REFORESTATION: BKLYN - ATLANTIC/SUTTER (NRG) | 2019 | 520 | 390.9 | 0 | 0 | 49 | 0 | 0 | 0 | 439.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-6WPEBCS | Recon War Mem bldg & Elenor Roosevelt CS | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-0505 P-D017 |  | BROOKLYN | RECON WAR MEM BLDG, PIERREPONT & ELENOR ROOSEVELT CS | 2019 | 1782 | 0 | 0 | 160 | 1400 | 500 | 0 | 0 | 2060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-03 | SANDY-Emergency Clean up & Safe Up - Shore Pkway B166-313M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | BOROUGH OF BROOKLYN | HURRICANE SANDY EMERGENCY WORK AT SHORE PARKWAY | 2019 | 600 | 278.14 | 0 | 0 | 0 | 0 | 1 | 0 | 279.14 | 1920.98 | 0 | 0 | 0 | 0 | 129 | 0 | 2049.98
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-10 | SANDY-North 5th Street pier work (Type 3) B536-113M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 201 | P-1018 |  | SITE IN THE BOROUGH OF BROOKLYN | SANDY RELATED WORK AT NORTH 5TH STREET PIER | 2019 | 650 | 633.16 | 1 | 0 | 0 | 8 | 0 | 0 | 642.16 | 1715.05 | 56 | 0 | 0 | 0 | 0 | 0 | 1771.05
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-12 | SANDY - Brooklyn Plgd requirements (Type 2) BG-1113M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | BOROUGH OF BROOKLYN | STORM SANDY - PLAYGROUND R/C | 2019 | 3168 | 567.69 | 0 | 0 | 0 | 118 | 0 | 0 | 685.69 | 1373.24 | 0 | 1060 | 0 | 0 | 0 | 0 | 2433.24
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-13 | SANDY - PNP Prospect Park Alliance | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 206 207 208 209 214 | P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | BROOKLYN | PROSPECT PARK | 2019 | 548 | 37 | 0 | 0 | 0 | 0 | 0 | 46 | 83 | 0 | 0 | 0 | 0 | 0 | 0 | 410 | 410
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-14 | SANDY- Abe Stark boilers and chillers (B169-111M) | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 200 213 | P-1018 |  | LOCATED ADJACENT TO THE CONEY ISLAND BOARDWALK AT WEST 19TH STREET, IN THE BOROUGH OF BROOKLYN | SANDY RELATED WORK AT ABE STARK SKATING RINK | 2019 | 1852 | 269.74 | 0 | 0 | 0 | 0 | 54 | 0 | 323.74 | 1001 | 0 | 0 | 0 | 0 | 383 | 0 | 1384
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-15 | SANDY-Nautilus Playground (Type 3 ) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 213 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | NAUTILUS PLGR , BROOKLYN | RECONSTRUCTION OF PLGR | 2019 | 540 | 40 | 0 | 0 | 0 | 0 | 0 | 45 | 85 | 0 | 0 | 0 | 0 | 0 | 0 | 405 | 405
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-16 | SANDY-Sheepshead Bay Piers Type 3 | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | SHEEPSHEAD BAY PIERS AT EMMONS AVE, BROOKLYN | R/C OF TRANSFORMERS AND ELECTRICAL COMPONENTS AT SHEEPSHEAD BAY PIERS | 2019 | 653 | 352.94 | 0 | 0 | 694 | 0 | 0 | 0 | 1046.94 | 548.48 | 0 | 5752 | 495 | 0 | 0 | 0 | 6795.48
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-17 | SRU-TYPE 3-MCGUIRE FIELDS SCOREBOARDS | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | BERGEN AVENUE AND AVENUE W. BOROUGH OF BROOKLYN | THE RECONSTRUCTION OF THE SCOREBOARDS AND ELECTRICAL EQUIPMENT AT JOSEPH T. MCGUIRE PARK DUE TO HURRICANE SANDY | 2019 | 480 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 36 | 0 | 0 | 364 | 0 | 0 | 0 | 0 | 364
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-21 | SANDY - Tree removals -Brooklyn CB 7-18 BG-614M | LAND ACQUISITION AND TREE PLANTING | 200 | P-1018 |  | BOROUGH OF BROOKLYN | TREE REMOVALS IN BROOKLYN CB 7-18 RELATED TO SANDY | 2019 | 2100 | 676.05 | 0 | 0 | 0 | 41 | 0 | 0 | 717.05 | 1521.51 | 0 | 0 | 0 | 368 | 0 | 0 | 1889.51
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-25 | Abe Stark - Non-Boiler Repair | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-1018 |  | BOROUGH OF BROOKLYN | SANDY - ABE STARK | 2019 | 2603 | 0 | 0 | 0 | 0 | 0 | 0 | 260 | 260 | 0 | 0 | 0 | 0 | 0 | 0 | 2343 | 2343
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-26 | Prospect Pk - Lily Pond & Pool Viewing Platform Repair | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 | P-1018 |  |  | PROSPECT PK LILY POND POOL PLATFORM REPAIR | 2019 | 294 | 44.07 | 0 | 0 | 0 | 0 | 0 | 25 | 69.07 | 0 | 0 | 0 | 0 | 0 | 0 | 225 | 225
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-27 | CI Beach & Boardwalk - West 25 ST Maint Office Boiler | BEACHES AND BOARDWALKS | 200 | P-1018 |  |  | CI BEACH & BOARDWALK - WEST 25 ST MAINT OFFICE BOILER | 2019 | 563 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 507 | 507
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-28 | Red Hook Recreation Center | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 200 | P-1018 |  |  | RED HOOK RECREATION CENTER | 2019 | 3109 | 0 | 0 | 0 | 0 | 0 | 0 | 311 | 311 | 0 | 0 | 0 | 0 | 0 | 0 | 2798 | 2798
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-30 | Hudson River Yacht Club | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 200 | P-1018 |  |  | HUDSON RIVER YACHT CLUB | 2019 | 440 | 0 | 0 | 0 | 0 | 0 | 0 | 205 | 205 | 0 | 0 | 0 | 0 | 0 | 0 | 1845 | 1845
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-31 | Diamond Point Yacht Club | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 200 | P-1018 |  |  | DIAMOND PONT YACHT CLUB | 2019 | 483 | 0 | 0 | 0 | 0 | 0 | 0 | 166 | 166 | 0 | 0 | 0 | 0 | 0 | 0 | 1485 | 1485
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-32 | Paerdegat Squadron Yacht Club | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 200 | P-1018 |  |  | PAERDEGAT SQUADRON YACHT CLUB | 2019 | 294 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 264 | 264
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-33 | Sandy - Midget Squadron Yacht Club | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 200 | P-1018 |  |  | MIDGET SQUADRON YACHT CLUB | 2019 | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 854 | 854 | 0 | 0 | 0 | 0 | 0 | 0 | 2645 | 2645
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-34 | Paerdegat Athletic Center HVAC recon. B406-114M | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 200 | P-1018 |  |  | PAERDEGAT ATHLETIC CENTER HVAC RECON. B406-114M | 2019 | 2696 | 852.31 | 5 | 0 | 0 | 18 | 0 | 0 | 875.31 | 2216.83 | 210 | 0 | 0 | 0 | 0 | 0 | 2426.83
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-35 | Paerdegat Athletic Center - Remaining Scope | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 200 | P-1018 |  |  | PAERDEGAT ATHLETIC CENTER - REMAINING SCOPE | 2019 | 12797 | 0 | 0 | 0 | 0 | 0 | 0 | 1233 | 1233 | 0 | 0 | 0 | 0 | 0 | 0 | 11098 | 11098
20190425 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-36 | SANDY-BK | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-1018 |  |  | SANDY2-36 | 2019 | 887 | 0 | 0 | 0 | 0 | 0 | 0 | 88 | 88 | 0 | 0 | 0 | 0 | 0 | 0 | 799 | 799
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-768A | WATER MAIN CONNECTIONS TO SHAFT 23B - PHASE I | TRUNK AND DISTRIBUTION MAIN EXTENSION | 200 | WM-0006 WM-0001 EP-0007 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  |  | 2019 | 16277 | 14751.38 | 120 | 0 | 0 | 0 | 0 | 0 | 14871.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-768B | WATER MAIN CONNECTIONS TO SHAFT 23B - PHASE II (HWK700B) | TRUNK AND DISTRIBUTION MAIN EXTENSION | 200 | WM-0001 WM-0006 SE-0002K | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | WATER MAIN CONNECTIONS TO SHAFT 23B - PHASE II | WATER MAIN CONNECTIONS TO SHAFT 23B - PHASE II | 2019 | 7244 | 0 | 0 | 0 | 0 | 52397 | 0 | 0 | 52397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-776 | WM REPLMT EAST NEW YORK AVE B/T HOWARD AV & PACIFIC ST, ETC | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 205 216 | WM-0006 WM-0001 SE-0002K HW-0200 TF-0002 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | WM REPLMT EAST NEW YORK AVE B/T HOWARD AV & PACIFIC ST, IN JAMAICA AVE B/T HERLIMER ST AND VERMONT ST AND ATLANTIC AVE B/T VAN SINDEREN AV AND PENNSYLVANIA | 2019 | 18872 | 1131.44 | 0 | 59071 | 0 | 0 | 0 | 0 | 60202.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-777 | WM REPLMT IN LEONARD STRET B/T DRIGGS AV AND MAUJER ST | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 201 | WM-0006 SE-0002K WM-0105 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | WM REPLMT IN LEONARD STRET B/T DRIGGS AV AND MAUJER ST | 2019 | 10234 | 43881.94 | 635 | 0 | 0 | 5 | 0 | 0 | 44521.94 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 36
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-778 | TRUNK & DIST. W/M REPL IN ATALNTIC AV B/T CARLTON & CLASSON | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 202 | WM-0006 WM-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | TRUNK & DIST. W/M REPL IN ATALNTIC AV B/T CARLTON & CLASSON | 2019 | 5001 | 21499.14 | 76 | 0 | 0 | 0 | 0 | 0 | 21575.14 | 205.76 | 0 | 0 | 0 | 0 | 0 | 0 | 205.76
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-778A | Trunk & Dist WM Rep in Atlantic Ave b/t Carlton & Portland | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 202 | EP-0007 SE-0002K WM-0001 WM-0006 HW-0200 TF-0502 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | TRUNK & DIST. W/M REPL IN ATALNTIC AV B/T CARLTON & S. PORTLAND AVENUES | 2019 | 3700 | 892.12 | 0 | 10041 | 0 | 0 | 0 | 0 | 10933.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-780 | RECON OF WM & SWR IN 5 AVE B/T 65 ST & 34 ST | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 207 | SE-0002K WM-0001 WM-0006 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | RECON OF WM & SWR IN 5 AVE B/T 65 ST & 34 ST | 2019 | 21800 | 0 | 0 | 0 | 0 | 23880 | 0 | 0 | 23880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-782 | Reconstuction of water main and combined sewer, Tillary st. | AUGMENTATION OF WATER SUPPLY SYSTEMS | 202 | WM-0001 SE-0002K | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | RECONSTUCTION OF WATER MAIN AND COMBINED SEWER, TILLARY ST. BETWEEN ADAMS ST. AND PRINCE ST. | 2019 | 3770 | 8396.37 | 90 | 0 | 0 | 100 | 0 | 0 | 8586.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-782A | Reconstuction of water main & combined sewer,Tillary st. PH2 | AUGMENTATION OF WATER SUPPLY SYSTEMS | 202 | WM-0001 SE-0002K |  |  | RECONSTRUCTION OF WATER MAIN & COMBINED SEWER,TILLARY ST. PHASE 2 | 2019 | 14039 | 13435.73 | 571 | 0 | 0 | 0 | 0 | 0 | 14006.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-784 | RECON OF WM I& STORM SWR IN BERGEN AVE AREA | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 218 | WM-0001 SE-0200K | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | RECON OF WM IN BERGEN AVE AREA | 2019 | 11730 | 30918.2 | 5342 | 0 | 0 | 36 | 0 | 16300 | 52596.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-785A | WM & Sewer work in Atlantic Ave (HWD10105, NDF-ATLAV) | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 205 | WM-0001 WM-0006 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RECON WM AND COMB & SAN SEWERS IN ATLANTIC AVE BETW GEORGIA AVE & SCHENCK ST | 2019 | 9230 | 8767.46 | 1776 | 0 | 0 | 2 | 0 | 0 | 10545.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-785B | Recon WM, Comb & San Swrs in Atlantic Ave, Ph 2 (HWD10105A) | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 205 | WM-0001 SE-0002K |  |  | RECON WM & COMB AND SAN SEWERS IN ATLANTIC AVE, PH 2 | 2019 | 4326 | 0 | 0 | 4076 | 0 | 0 | 0 | 0 | 4076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-794 | DUMBO/Vinegar Hill Area Reconstruction & Plaza. | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 202 206 | SE-0004 WM-0006 WM-0001 SE-0002K | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | TRUNK/DIST WM REPLAC. & INSTALLATION, COMBINED SWR REPLACE, HI LEVEL STORM SWR EXTENSION, BKLYN | 2019 | 9413 | 41530.01 | 7382 | 0 | 0 | 0 | 0 | 0 | 48912.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-796 | Trunk & Distribution WM replcmnt in Empire Blvd | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 209 217 | EP-0007 SE-0002K WM-0001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | TRUNK & DISTRIBUTION WM REPLCMNT IN EMPIRE BLVD AT THE INTERSECTION OF EAST NEW YORK AVENUE, UTICA AVENUE, ETC., BOROUGH OF BROOKLYN | 2019 | 6540 | 0 | 10972 | 0 | 0 | 0 | 0 | 0 | 10972 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-802 | WM Replacement Hamilton Ave Gowanus Connector, Brooklyn | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 206 207 | WM-0001 SE-0002K SE-0200K | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | WM REPLACEMENT HAMILTON AVE GOWARNUS CONNECTOR B/T SMITH & 19 ST, BKLYN | 2019 | 1920 | 120 | 0 | 15730 | 0 | 0 | 0 | 0 | 15850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-803 | WM Replacment in Schenck Ave b/t Flatlands & Jamaica Ave, Bk | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 205 | SE-0002K |  |  | WM REPLAC. SCHENCK AVE B/T FLATLANDS & JAMAICA AVES, BKLYN | 2019 | 4600 | 0 | 55 | 0 | 532 | 0 | 0 | 0 | 587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-805 | New Storm & San Swrs & WM-Gateway Estates, Phase E (HD-161E) | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 205 | SE-0002K | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | NEW STORM & SANI SWRS & WM IN GATEWAY ESTATES, PHASE E, BKLY | 2019 | 5776 | 13711.56 | 95 | 0 | 0 | 0 | 0 | 0 | 13806.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-806 | Water Main work in Brooklyn Waterfront Greenway | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 201 | WM-0001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | WATER MAIN WORK IN BROOKLYN WATERFRONT GREENWAY (COMMERCIAL STREET, ASH STREET AND BOX STREET)-BED-806 | 2019 | 1594 | 0 | 0 | 1594 | 0 | 0 | 0 | 0 | 1594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-807 | WM work in Brooklyn Waterfront Greenway. | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 201 | WM-0001 SE-0002K |  |  | WM WORK IN BROOKLYN WATERFRONT GREENWAY. (2ND AVENUE BETWEEN 37TH STREET & 39TH STREET ETC.) | 2019 | 569 | 0 | 0 | 1176 | 0 | 0 | 0 | 0 | 1176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-809 | Replacement of Water Mains in Avenue S | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 215 | WM-0001 EP-0007 WM-0944 HW-0200 |  |  | REPLACEMENT OF WATER MAINS IN AVENUE S BET. CONEY ISLAND AVENUE AND EAST 18TH STREET | 2019 | 14445 | 838 | 26671 | 0 | 0 | 0 | 0 | 0 | 27509 | 0 | 3943 | 0 | 0 | 0 | 0 | 0 | 3943
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-810 | Water Main work in Brooklyn Waterfront Gateway | AUGMENTATION OF WATER SUPPLY SYSTEMS | 201 | WM-0001 SE-0002K |  |  | WATER MAIN WORK IN BROOKLYN WATERFRONT GATEWAY (KENT AVENUE BET. CLYMER ST & TAYLOR ST. ETC) | 2019 | 244 | 8712.43 | 584 | 0 | 0 | 0 | 0 | 0 | 9296.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-819 | WM replacement in Oriental Blvd | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 215 | WM-0001 |  |  | WM REPLACEMENT IN ORIENTAL BLVD BETWEEN CORBIN PLACE AND PEMBROKE ST,ETC MANHATTAN BEACH AREA, BROOKLYN | 2019 | 17750 | 150 | 0 | 0 | 17200 | 0 | 0 | 0 | 17350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BEDA-001 | Accelerated Distribution WM replcmnt & sewer rehab- BKLYN | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 200 | WM-0001 |  |  | ACCELERATED DISTRIBUTION WATER MAIN REPLCMNT & SEWER REHAB/REPLCMNT, BROOKLYN | 2019 | 15000 | 17236.09 | 415 | 0 | 0 | 0 | 0 | 0 | 17651.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BEDA-002 | Accelerated Distribution WM replcmnt & sewer rehab- BKLYN | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 200 | WM-0001 SE-0002K SE-0200K | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ACCELERATED DISTRIBUTION WATER MAIN REPLCMNT & SEWER REHAB/REPLCMNT, BROOKLYN | 2019 | 17900 | 21938.79 | 12720 | 0 | 0 | 0 | 0 | 0 | 34658.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BEDA-003 | Accelerated Distribution WM replcmnt & sewer rehab- BKLYN | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 200 | WM-0001 SE-0002K SE-0200K |  |  | ACCELERATED DISTRIBUTION WATER MAIN REPLCMNT & SEWER REHAB/REPLCMNT, BROOKLYN | 2019 | 17175 | 23151.94 | 486 | 0 | 0 | 0 | 0 | 0 | 23637.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CJCREN | FACIILITY RENOVATIONS AT CROSSROADS JC | CHILD WELFARE FACILITIES | 200 | CS-0005 PU-0026 |  |  | THIS PROJECT ENCOMPASSES THE RENOVATION OF THE SECURE JUVENILE DETENTION CENTER LOCATED AT 17 BRISTOL STREET IN BROOKLYN (CROSSROADS JUVENILE CENTER). THE PROJECT INCLUDES BUT IT IS NOT LIMITED TO: REINFORCEMENT OF BEDROOM WALLS; BATHROOM RECONFIGURATION; FUNCTIONAL CHANGES OF EXISTING DORM SPACE TO PSYCHIATRIC MEDICAL SUITE; UPGRADE OF ALL SYSTEMS: LIGHTING, ROOFING, PLUMBING, MECH., ELECTRICAL, SECURITY, FIRE ALARM AND FIRE SUPPRESSION SYSTEMS; UPGRADE AND UPDATE OF: EXISTING CLASSROOMS, COMMERCIAL KITCHEN AND KITCHEN EQUIPMENT; RENOVATION OF ENTIRE EXTERIOR RECREATIONAL AREA TO REFLECT SHADE AREAS AND UPGRADE OF THE LANDSCAPING. ACS HAS BEEN TAKING TEMPORARY MEASURES TO MAINTAIN THE FACILITY OPERATIONS WITH MATERIALS AND FIXTURES OF THE ORIGINAL CONSTRUCTION WHICH HAVE NOT EXHIBITED THE RESILIENCE AND VANDAL RESISTANCE EXPEC | 2019 | 15205 | 41178.03 | 31181 | 500 | 0 | 0 | 0 | 0 | 72859.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO272DW | 45 MONROE PL. - DRIVEWAY PLACEMENT | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 201 | CO-0272 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | 45 MONROE PL. - DRIVEWAY PLACEMENT | 2019 | 1210 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 0 | 307 | 0 | 0 | 0 | 350
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO272ELC2 | 45 MONROE PL - ELECTRICAL / FA UPGRADE | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 202 | CO-0272 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | BROOKLYN APPELLATE COURT WILL HAVE ITS ELECTRICAL SYSTEM UPGRADED. | 2019 | 7126 | 631.96 | 0 | 0 | 0 | 0 | 0 | 0 | 631.96 | 6668.73 | 859 | 301 | 0 | 0 | 0 | 0 | 7828.73
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO272ELV2 | 45 MONROE PL. - ELEVATOR | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 202 | CO-0272 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | 45 MONROE PL. - ELEVATOR | 2019 | 1056 | 410.69 | 0 | 0 | 0 | 0 | 0 | 0 | 410.69 | 2002.7 | 99 | 450 | 0 | 0 | 0 | 0 | 2551.7
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO278EXT2 | 360 ADAMS ST. - EXTERIOR | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 201 | CO-0278 |  |  | EXTERIOR RESTORATION | 2019 | 3269 | 532.92 | 129 | 318 | 0 | 2286 | 0 | 0 | 3265.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO278FA3 | 360 ADAMS STREET - FIRE ALARM SYSTEM & SPRINKLER UPGRADE | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 202 | CO-0278 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | COMPREHENSIVE FIRE ALARM SYSTEM & SPRINKLER UPGRADE | 2019 | 40820 | 2683.23 | 6257 | 0 | 47483 | 1439 | 0 | 0 | 57862.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO281LL11 | 120 SCHERMERHORN ST - FACADE REPAIRS LOCAL LAW 11 | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 202 | CO-0281 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | 120 SCHERMERHORN ST - FAÝADE REPAIRS LOCAL LAW 11 | 2019 | 3235 | 0 | 0 | 0 | 0 | 0 | 380 | 2557 | 2937 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO281TOIL | 120 SCHERMERHORN ST.- CODE COMPLIANT TOILET UPGRADE | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 202 | C-0075 CO-0281 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | 120 SCHERMERHORN ST.- CODE COMPLIANT TOILET UPGRADE | 2019 | 4000 | 322 | 88 | 4029 | 0 | 0 | 0 | 0 | 4439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CONEYINF | Coney Island Infrastructure (CONISPH3A) | PRIMARY STREET RECONSTRUCTION | 200 | HW-0001K |  | CONEY ISLAND INFRASTRUCTURE | CONEY ISLAND INFRASTRUCTURE | 2019 | 4000 | 1650.2 | 320 | 0 | 0 | 0 | 0 | 0 | 1970.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CONISPH04 | SAN & STRM SWR, WM1, IN CONEY ISL AREA, PH 4 | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 213 | SE-0200K WM-0006 WM-0001 |  | STORM & SANITARY SEWER, DISTRIBUTION WATER MAIN IN CONEY ISLAND AREA,PHASE 4 | STORM & SANITARY SEWER, DISTRIBUTION PWATER MAIN IN CONEY ISLAND AREA, PHASE 4 | 2019 | 27679 | 0 | 0 | 27679 | 0 | 0 | 0 | 0 | 27679 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | E12-0043 | NYPD 84th Precinct - EE Upgrade | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 201 | PO-0079 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | NYPD 84TH PRECINCT & EC 207 ENERGY UPGRADES | 2019 | 694 | 3343.18 | 634 | 0 | 0 | 0 | 0 | 0 | 3977.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | E14-0001 | NYPD-FDNY - 67 PCT AND EC248 ENERGY UPGRADE | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 200 | PU-0025 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | ENERGY UPGRADE | 2019 | 1248 | 2069.65 | -6 | 106 | 0 | 0 | 0 | 0 | 2169.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | E14-0016 | DHS - Atlantic Avenue Men's Shelter | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 201 | PU-0025 HH-0112 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | DHS - ATLANTIC AVENUE MEN'S SHELTER | 2019 | 246 | 1052.34 | -15 | 151 | 0 | 0 | 0 | 0 | 1188.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | E14-0060 | OEM - OEM HEADQUARTERS COMP ENERGY UPGRADE | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 200 | PU-0025 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | ENERGY UPGRADE | 2019 | 563 | 563.66 | 60 | 94 | 0 | 0 | 0 | 0 | 717.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | E17-0006 | DSNY - BROOKLYN NORTH 1 DISTRICT &4 DISTRICT GARAGE | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 201 | PU-0025 |  |  | BROOKLYN NORTH 1 DISTRICT &4 DISTRICT GARAGE | 2019 | 13191 | 0 | 938 | 927 | 0 | 10136 | 0 | 0 | 12001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | EP6-KENT2 | 356 FLUSING, BUILDING REPAIR/UPGRADE | FACILITY PURCHASES AND RECONSTRUCTION | 201 202 | EP-0006 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | BASE BUILDING REPAIRS REQUIRED TO BE DONE AS PART OF MAINTENANCE OF FACILITY | 2019 | 954 | 33959.53 | 1654 | 1469 | 0 | 0 | 0 | 0 | 37082.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | F175RES2 | NEW FIREHOUSE - RESCUE 2 | NEW FACILITIES AND RENOVATIONS | 200 | F-0175 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NEW FIREHOUSE - RESCUE 2 | 2019 | 22525 | 31583.79 | 1378 | 965 | 0 | 0 | 0 | 0 | 33926.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GCNC77-PA | GI - PERMEABLE ASPHALT PAVEMENT PILOT & GI IN CSO AREA NC-77 | GREEN INFRASTRUCTURE PROGRAM | 200 | WP-0169 EP-0007 HW-0200 |  |  | PERMEABLE ASPHALT PAVEMENT PILOT AND GREEN INFRASTRUCTURE N CSO TRIBUTARY AREA NC-077 | 2019 | 5172 | 0 | 5172 | 0 | 0 | 0 | 0 | 0 | 5172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-01 | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO PH 1 | GREEN INFRASTRUCTURE PROGRAM | 200 | WP-0169 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO TIBUTARY AREA PHASE 1 | 2019 | 18817 | 8366.97 | 0 | 0 | 10700 | 0 | 0 | 0 | 19066.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-02 | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO PH 2 | GREEN INFRASTRUCTURE PROGRAM | 200 | WP-0169 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO TIBUTARY AREA PHASE 2 | 2019 | 17234 | 7283.85 | 0 | 0 | 0 | 10000 | 0 | 0 | 17283.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-03 | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO PH 3 | GREEN INFRASTRUCTURE PROGRAM | 200 | WP-0169 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO TIBUTARY AREA PHASE 3 | 2019 | 17982 | 8081.88 | 0 | 0 | 10000 | 0 | 0 | 0 | 18081.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-04 | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO PH 4 | GREEN INFRASTRUCTURE PROGRAM | 200 | WP-0169 |  |  | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO TIBUTARY AREA PHASE 4 | 2019 | 23046 | 0 | 7041 | 0 | 14105 | 2659 | 0 | 0 | 23805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GNCB14-2A | GI-CONSTRUCTION OF GI NIN NCB-014, PHASE II | GREEN INFRASTRUCTURE PROGRAM | 200 | WP-0169 EP-0007 |  |  | GI-CONSTRUCTION OF GREEN INFRASTRUCTURE IN NCB-014, PHASE II | 2019 | 5750 | 0 | 0 | 26275 | 0 | 0 | 0 | 0 | 26275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GRANSTBID | FA - Grand Street BID Renewal Project | NEIGHBORHOOD REVITALIZATION | 299 | HW-K005 TF-D004 HW-0001K | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | GRAND STREET BID PROJECT | 2019 | 100 | 5419.02 | 0 | 0 | 0 | 398 | 0 | 0 | 5817.02 | 19.58 | 0 | 0 | 0 | 0 | 0 | 0 | 19.58
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM17GHSE | MARLBOROUGH HOUSES BSCAH GREENHOUSE | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 213 | HA-K001 |  |  | MARLBOROUGH HOUSES BSCAH GREENHOUSE | 2019 | 2000 | 0 | 16161 | 0 | 0 | 0 | 0 | 0 | 16161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM17MRCC | MARCY HOUSES - RENOVATE 492 MARCY AVE INTO A COMM CENTER | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 203 | HA-D001 HA-K001 HA-0001 |  |  | RENOVATE VACANT SPACE AT 492 MARCY AVENUE TO CREATE A COMMUNITY CENTER | 2019 | 5335 | 948.82 | 8352 | 0 | 0 | 0 | 0 | 0 | 9300.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HD-161C | GATEWAY ESTATE - PHASE C (SEK20056) | OTHER HOUSING SUPPORT INVESTMENT | 205 | HD-0161 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | GATEWAY ESTATE - PHASE C | GATEWAY ESTATE - PHASE C | 2019 | 6271 | 10630.37 | 262 | 0 | 0 | 0 | 0 | 0 | 10892.37 | 12.5 | 0 | 0 | 0 | 0 | 0 | 0 | 12.5
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HD-161E | GATEWAY ESTATE - PHASE E (BED-805) | OTHER HOUSING SUPPORT INVESTMENT | 205 | HD-0161 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | GATEWAY ESTATE - PHASE E | GATEWAY ESTATE - PHASE E | 2019 | 12422 | 17707.91 | 1082 | 0 | 0 | 0 | 0 | 0 | 18789.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112AAFS | ATLANTIC ARMORY FIRE SAFETY | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | ATLANTIC ARMORY FIRE SAFETY | 2019 | 4975 | 434.25 | 506 | 0 | 0 | 0 | 506 | 4035 | 5481.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BATV | BEDFORD ATLANTIC CCTV | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CCTV | 2019 | 829 | 88 | 0 | 78 | 745 | 0 | 0 | 0 | 911 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BVFA | BROWNSVILLE WOMEN FIRE SAFETY | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | BROWNSVILLE WOMEN FIRE SAFETY | 2019 | 598 | 74.15 | 0 | 0 | 0 | 0 | 1144 | 0 | 1218.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112FBFS | FANNIE BARNES FIRE SAFETY | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | FANNIE BARNES FIRE SAFETY | 2019 | 1400 | 166.66 | 168 | 0 | 0 | 0 | 1450 | 0 | 1784.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112HWFS | HELP WOMEN'S CENTER FIRE SAFETY | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | HELP WOMEN'S CENTER FIRE SAFETY | 2019 | 1313 | 159.54 | 0 | 0 | 0 | 0 | 1433 | 0 | 1592.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112LXFA | 85 LEXINGTON FIRE SAFETY SYSTEM | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 |  |  | 85 LEXINGTON AVENUE-FIRE SAFETY SYSTEM | 2019 | 983 | 50.47 | 35 | 875 | 0 | 0 | 0 | 0 | 960.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112PJBO | PAMOJA - BOILER | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 |  |  | PAMOJA - BOILER | 2019 | 2934 | 599.68 | 1055 | 3188 | 6100 | 0 | 0 | 0 | 10942.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112PJFC | PAMOJA HOUSE - FACADE REHABILITATION/RESTORATION | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 |  |  | PAMOJA HOUSE - FACADE REHABILITATION/RESTORATION | 2019 | 1693 | 0 | 0 | 1238 | 0 | 2500 | 2855 | 0 | 6593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112PJPL | PAMOJA HOUSE - PLUMBING UPGRADE | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 |  |  | PAMOJA HOUSE - PLUMBING UPGRADE | 2019 | 2600 | 0 | 208 | 0 | 2997 | 0 | 0 | 0 | 3205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112PJRC | PAMOJA HOUSE FIRE SAFETY | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 |  |  | FIRE SAFETY SYSTEM AND FIRE DOORS | 2019 | 4035 | 262.74 | 0 | 0 | 0 | 0 | 272 | 6192 | 6726.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115BWKF | BUSHWICK - FIRE ALARM SYSTEM UPGRADE | SHELTERS FOR HOMELESS FAMILIES |  | HH-0115 |  |  | BUSHWICK - FIRE ALARM SYSTEM UPGRADE | 2019 | 769 | 905.21 | 139 | 0 | 0 | 0 | 0 | 0 | 1044.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115DSFA | DEAN STREET FIRE SAFETY | SHELTERS FOR HOMELESS FAMILIES |  | HH-0115 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | DEAN STREET FIRE SAFETY | 2019 | 860 | 96.34 | 0 | 0 | 0 | 0 | 184 | 2555 | 2835.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115FFTV | FLATLANDS FAMILY CCTV | SHELTERS FOR HOMELESS FAMILIES |  | HH-0115 |  |  | CCTV | 2019 | 459 | 96 | 54 | 623 | 0 | 0 | 0 | 0 | 773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115LFAU | LINDEN FIRE ALARM UPGRADE | SHELTERS FOR HOMELESS FAMILIES |  | HH-0112 |  |  | FIRE ALARM UPGRADE | 2019 | 1115 | 55.6 | 209 | 800 | 0 | 0 | 0 | 0 | 1064.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115SFFA | Stockholm at 99-103 Stockholm St, 11221 - Fire Alarm Upgrade | SHELTERS FOR HOMELESS FAMILIES |  | HH-0115 |  |  | STOCKHOLM AT 99-103 STOCKHOLM ST, 11221 - FIRE ALARM UPGRADE | 2019 | 335 | 576.54 | 111 | 177 | 0 | 0 | 0 | 0 | 864.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115SRFA | ROSE MCCARTHY - FIRE ALARM SYSTEM UPGRADE | SHELTERS FOR HOMELESS FAMILIES |  | HH-0115 |  |  | ROSE MCCARTHY - FIRE ALARM SYSTEM UPGRADE | 2019 | 583 | 643.97 | 223 | 0 | 0 | 0 | 0 | 0 | 866.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HIFHPD | Housing Infrastructure Fund for HPD Projects | OTHER HOUSING SUPPORT INVESTMENT | 205 | ED-0075 |  | HPD | INFRASTRUCTURE COSTS RELATED TO HPD PROJECTS | 2019 | 3482 | 1859.28 | 1623 | 0 | 0 | 0 | 0 | 0 | 3482.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82BRKLN | Brooklyn Animal Care Center Upgrade | ANIMAL CARE |  | HL-0082 |  |  | BROOKLYN ANIMAL SHELTER HVAC UPGRADE | 2019 | 3500 | 1260.06 | 3095 | 6440 | 1693 | 14591 | 0 | 0 | 27079.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82BUSHX | BUSHWICK HEALTH CENTER - EXTERIOR RENOVATION | CLINIC RENOVATION AND REHABILITATION |  | HL-0082 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | EXTERIOR RENOVATION AND OTHER REHAB PROJECTS AT THE BUSHWICK HEALTH CENTER | EXTERIOR RENOVATION AND OTHER REHAB PROJECTS AT THE BUSHWICK HEALTH CENTER | 2019 | 1736 | 1608.75 | 657 | 5629 | 8632 | 1500 | 0 | 0 | 18026.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD005K01 | FULTON ST IMPROVEMENTS AT GREEN AV, HANSEN PL & GATES AV | PRIMARY STREET RECONSTRUCTION | 202 | HW-0001K WM-0001 HW-D101 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | FULTON ST IMPROVEMENTS AT GREEN AV, HANSEN PL & GATES AV INTERSECTIONS | FULTON ST IMPROVEMENTS AT GREEN AV, HANSEN PL & GATES AV INTERSECTIONS | 2019 | 400 | 4213.49 | 223 | 0 | 0 | 0 | 123 | 0 | 4559.49 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 15
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD007K03 | Park Avenue Pedestrian Safety Improvements at the Crossover | PRIMARY STREET RECONSTRUCTION | 202 203 204 | HW-K005 HW-D101 HW-0001K | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | MYRTLE AVE WORK | 2019 | 300 | 0 | 0 | 0 | 0 | 6105 | 0 | 0 | 6105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD10105 | Ped Safety Upgrades on Atlantic Ave (BED-785A, NDF-ATLAV) | PRIMARY STREET RECONSTRUCTION | 202 203 205 216 | HW-0001K | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | PED SAFETY UPGRADES ON ATLANTIC AVE | PED SAFETY UPGRADES ON ATLANTIC AVE | 2019 | 32000 | 11695.79 | 1740 | 0 | 0 | 4 | 0 | 0 | 13439.79 | 14143.64 | 0 | 0 | 0 | 0 | 0 | 0 | 14143.64
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD10105A | Ped Safety Upgrades on Atlantic Ave - Phase 2 (BED-785B) | PRIMARY STREET RECONSTRUCTION | 200 | HW-0001K HW-K005 HW-0001Q |  | PEDESTIAN SAFETY UPGRADES ON ATLANTIC AVE - PHASE 2 | PEDESTIAN SAFETY UPGRADES ON ATLANTIC AVE - PHASE 2 | 2019 | 31830 | 1597.97 | 296 | 0 | 36237 | 0 | 0 | 0 | 38130.97 | 0 | 0 | 0 | 1320 | 0 | 0 | 0 | 1320
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK100BUS | Utica Ave Bus Priority | TRAFFIC WORK IN CONJUNCTION WITH HIGHWAY RECONSTRUCTION | 200 208 209 217 218 | HW-1684 EP-0007 WM-0001 HW-0001K HW-D101 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | UTICA AVE BROOKLYN | UTICA AVE BUS PRIORITY | 2019 | 6400 | 6990.45 | 3171 | 0 | 300 | 7 | 0 | 0 | 10468.45 | 13966.68 | 0 | 0 | 0 | 0 | 0 | 0 | 13966.68
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK100SBC | South Brooklyn Crosstown SBS | PRIMARY STREET RECONSTRUCTION | 200 | HW-D101 HW-1684 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | SOUTH BROOKLYN CROSSTOWN SBS | SOUTH BROOKLYN CROSSTOWN SBS | 2019 | 7750 | 2487.15 | 0 | 0 | 0 | 74412 | 0 | 0 | 76899.15 | 0 | 0 | 0 | 0 | 4809 | 0 | 0 | 4809
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1048B | FLUSHING AVE - BROOKLYN GREENWAY | PRIMARY STREET RECONSTRUCTION | 202 | HW-0001K HW-0944 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | NAVY YARD - BROOKLYN GREENWAY | NAVY YARD - BROOKLYN GREENWAY | 2019 | 6664 | 6541.01 | 2303 | 0 | 0 | 0 | 0 | 0 | 8844.01 | 4450.34 | 10 | 0 | 0 | 0 | 0 | 0 | 4460.34
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1048C | KENT AVE | PRIMARY STREET RECONSTRUCTION | 200 | HW-0001K TF-0002 TF-0502 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | KENT AVE | KENT AVE | 2019 | 32633 | 5883.77 | 1852 | 0 | 0 | 27 | 0 | 0 | 7762.77 | 2234.35 | 0 | 0 | 0 | 0 | 0 | 0 | 2234.35
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1048D | Brooklyn Waterfront Greenway:Sunset Park / Gowanus Connector | PRIMARY STREET RECONSTRUCTION | 207 | HW-K005 WM-0001 HW-0001K | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | IMPROVEMENTS TO THE PEDESTRIAN AND BICYCLE NETWORK FROM THE HAMILTON AVENUE BRIDGE TO 43RD STREET AND 1ST AVENUE, THE FUTURE LOCATION OF BUSH TERMINAL PIERS PARK | IMPROVEMENTS TO THE PEDESTRIAN AND BICYCLE NETWORK FROM THE HAMILTON AVENUE BRIDGE TO 43RD STREET AND 1ST AVENUE, THE FUTURE LOCATION OF BUSH TERMINAL PIERS PARK | 2019 | 12060 | 718.82 | 165 | 12140 | 0 | 0 | 0 | 0 | 13023.82 | 186.42 | 0 | 5168 | 0 | 0 | 0 | 0 | 5354.42
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1129 | NOSTRAND AVE | PRIMARY STREET RECONSTRUCTION | 203 | HW-1129 TF-0002 HW-0001K | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | NOSTRAND AVE: FLUSHING AVE TO ATLANTIC AVERECONSTRUCTION OF THE EXISTING ROADWAYROADWAY RECONSTRUCTION SHALL INCLUDE NEW CURBS, SIDEWALKS, AND REQUIREREPLACEMENTAMENITIES WILL NOT BE INCLUDEDCITY FUNDEDIN CONJUNCTION WITH DEP | 2019 | 21063 | 18254.84 | 355 | 0 | 0 | 0 | 0 | 0 | 18609.84 | 215.8 | 0 | 0 | 0 | 0 | 0 | 0 | 215.8
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1130B | Williamsburg Bridge Plaza | PRIMARY STREET RECONSTRUCTION | 200 | HW-0001K TF-0002 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | WILLIAMSBURG BUS DEPOT | WILLIAMSBURG BUS DEPOT | 2019 | 5399 | 3266.46 | 383 | 0 | 0 | 0 | 0 | 0 | 3649.46 | 13404.18 | 183 | 0 | 0 | 0 | 0 | 0 | 13587.18
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1148 | JEWEL STREET AREA | PRIMARY STREET RECONSTRUCTION | 205 | HW-0061 WM-0001 HW-1148 HW-0200 TF-0002 TF-0502 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  |  | 2019 | 9274 | 2229.88 | 0 | 1000 | 0 | 0 | 0 | 32902 | 36131.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1170 | Willoughby Street Plaza Reconstruction PINX550.59 | PRIMARY STREET RECONSTRUCTION | 202 | HW-0001K | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | WILLOUGHBY STREET PLAZA RECONSTRUCTION | WILLOUGHBY STREET PLAZA RECONSTRUCTION | 2019 | 3300 | 2708.89 | 0 | 0 | 0 | 0 | 0 | 0 | 2708.89 | 1016.34 | 0 | 0 | 0 | 382 | 0 | 0 | 1398.34
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1669 | 4th Ave Safety Improvements | PRIMARY STREET RECONSTRUCTION | 200 | HW-0001K | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | 4TH AVE SAFETY IMPROVEMENTS - PARK SLOPE | 4TH AVE SAFETY IMPROVEMENTS - PARK SLOPE | 2019 | 40491 | 2984.38 | 0 | 0 | 0 | 0 | 4132 | 0 | 7116.38 | 1049.99 | 0 | 0 | 0 | 0 | 0 | 0 | 1049.99
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1669A | 4th Ave Safety Improvements - Phase A | PRIMARY STREET RECONSTRUCTION | 200 | HW-0001K HW-0200 HW-0944 TF-0002 TF-0502 |  | 4TH AVE FROM 18TH TO 33RD ST | 4TH AVE SAFETY IMPROVEMENTS - PHASE 2 | 2019 | 54835 | 180 | 32947 | 0 | 0 | 0 | 0 | 0 | 33127 | 0 | 25151 | 0 | 0 | 0 | 0 | 0 | 25151
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1670 | Industry City Safety and Streetscape Improvements | PRIMARY STREET RECONSTRUCTION | 200 | HW-0001K HW-K005 HW-D101 HW-0200 TF-0002 TF-0502 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | SUNSET PARK IMPROVEMENTS - INDUSTRY CITY | SUNSET PARK IMPROVEMENTS - INDUSTRY CITY | 2019 | 1870 | 75 | 1040 | 0 | 0 | 1 | 0 | 0 | 1116 | 0 | 749 | 0 | 0 | 0 | 0 | 0 | 749
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1672 | WASHINGTON AVENUE SAFETY IMPROVEMENTS | PRIMARY STREET RECONSTRUCTION | 200 | HW-D101 HW-0001K |  | WASHINGTON AVENUE SAFETY IMPROVEMENTS | WASHINGTON AVENUE SAFETY IMPROVEMENTS | 2019 | 11100 | 0 | 1063 | 516 | 0 | 8807 | 0 | 0 | 10386 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK2013GB | Gerritsen Beach - Street Reconstruction | LOCAL STREET RECONSTRUCTION | 215 | HW-0001K HW-0200 TF-0502 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | GERRITSEN BEACH AREA IN BROOKLYN INCLUDING ABBEY CT, BEACON CT, EATONCT, AND FRANK CT FROM SEBA AVE TO CYRUS AVE; CANTON CT AND DARE CT FROM BARTLETT PL TO CYRUS AVE; AND BARTLETT PL FROM ABBEY CT TO PLUMB BEACH AVE | RECONSTRUCTION OF STREETS WITHIN GERRITSEN BEACH AREA IN BROOKLYN INCLUDING ABBEY CT, BEACON CT, EATON CT, AND FRANK CT FROM SEBA AVE TO CYRUS AVE; CANTON CT AND DARE CT FROM BARTLETT PL TO CYRUS AVE; AND BARTLETT PL FROM ABBEY CT TO PLUMB BEACH AVE. THE PROJECT WILL BRING STREETS TO A STATE-OF-GOOD-REPAIR. | 2019 | 4400 | 740 | 0 | 8287 | 0 | 0 | 0 | 0 | 9027 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 2500
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK2048 | Jamaica Bay Greenway - Paerdegat Ave. North Connector | PRIMARY STREET RECONSTRUCTION | 200 | HW-0001K | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | JAMAICA BAY GREENWAY - PAERDEGAT AVE. NORTH CONNECTOR | JAMAICA BAY GREENWAY - PAERDEGAT AVE. NORTH CONNECTOR | 2019 | 3540 | 536 | 0 | 0 | 2589 | 0 | 0 | 0 | 3125 | 299.9 | 0 | 0 | 840 | 0 | 0 | 0 | 1139.9
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK300-01 | NORTH FLATBUSH AVE - ATLANTIC YARDS AREA | PRIMARY STREET RECONSTRUCTION | 202 | HW-0001K WM-0001 TF-0002 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NORTH FLATBUSH AVENUE D.M.A. RENOVATION OF CARLTON AVENUE | 2019 | 400 | 7445.84 | 1533 | 0 | 0 | 0 | 0 | 0 | 8978.84 | 1814.8 | 0 | 0 | 0 | 0 | 0 | 0 | 1814.8
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK472W | FLUSHING AVENUE (X755 69) | PRIMARY STREET RECONSTRUCTION | 202 204 | WM-0006 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | FLUSHING AVE: NAVY ST TO BEDFORD AVEFLUSHING AVE: PORTER AVE TO CYPRESS AVENASSAU ST: NAVY ST TO FLATBUSH AVE EXTRECONSTRUCTION OF THE EXISTING ROADWAYROADWAY RECONSTRUCTION SHALL INCLUDE NEW CURBS, SIDEWALKS, AND REQUIREREPLACEMENTAMENITIES WILL NOT BE INCLUDEDIN CONJUNCTION WITH DEP | 2019 | 51814 | 44607.46 | 86 | 0 | 0 | 0 | 0 | 0 | 44693.46 | 7341.54 | 0 | 0 | 0 | 0 | 0 | 0 | 7341.54
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK614D | RECONSTRUCTION OF BERGEN AVENUE AREA, BKLYN | PRIMARY STREET RECONSTRUCTION | 218 | HW-0614 HW-0944 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | RECONSTRUCTION OF BERGEN AVENUE AREA, BKLYN | RECONSTRUCTION OF BERGEN AVENUE AREA, BKLYN | 2019 | 30591 | 25108.99 | 3989 | 0 | 0 | 0 | 321 | 0 | 29418.99 | 191.25 | 25 | 0 | 0 | 0 | 0 | 0 | 216.25
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK639W | RECON: TILLARY STREET | PRIMARY STREET RECONSTRUCTION | 202 | HW-0639 HW-0200 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | RECONSTRUCT CADMAN PLAZA EAST: TILLARY STREET TO JOHNSON STREET TILLARY STREET: CADMAN PLAZA WEST TO NAVY STREET SANDS STREET: ADAMS STREET S/R TO JAY STREET RED CROSS PLACE: ADAMS STREET S/R TO CADMAN PLAZA EAST CADMAN PLAZA EAST: TILLARY STREETTO JOHNSON STREET JOHNSON STREET: ADAMS STREET S/R TO CADMAN PLAZA WEST | TILLARY ST: CADMAN PLAZA WEST TO NAVY STRECONSTRUCTION OF THE EXISTING ROADWAYROADWAY RECONSTRUCTION SHALL INCLUDE NEW CURBS, SIDEWALKS, AND REQUIREREPLACEMENTAMENITIES WILL NOT BE INCLUDEDCITY FUNDEDIN CONJUNCTION WITH DEP | 2019 | 16406 | 9850.03 | 287 | 0 | 0 | 0 | 0 | 0 | 10137.03 | 7424.65 | 0 | 0 | 0 | 0 | 0 | 0 | 7424.65
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK639WA | RECON: TILLARY STREET PHASE 2 | PRIMARY STREET RECONSTRUCTION | 200 | HW-0001K TF-0502 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | RECON: TILLARY STREET PHASE 2 | RECON: TILLARY STREET PHASE 2 | 2019 | 17200 | 9190.57 | 1773 | 0 | 0 | 0 | 0 | 0 | 10963.57 | 32070.42 | 821 | 0 | 0 | 0 | 0 | 0 | 32891.42
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK700B | Reconstruction of Columbia Street Area Phase II (BED-768B) | PRIMARY STREET RECONSTRUCTION | 206 | HW-0001K | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | COLUMBIA STREET RECONSTRUCTION (SOUTH OF HAMILTON AVE.) THIS PROJECTIS IN CONJUNCTION WITH NYCDEP PROJECT BED768/SE. | COLUMBIA STREET RECONSTRUCTION (SOUTH OF HAMILTON AVE.) THIS PROJECTIS IN CONJUNCTION WITH NYCDEP PROJECT BED768/SE. | 2019 | 14097 | 1568.58 | 0 | 0 | 0 | 48185 | 0 | 0 | 49753.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK779W | EMPIRE BOULEVARD | PRIMARY STREET RECONSTRUCTION | 209 | HW-0200 HW-0944 HW-0779 TF-0002 TF-0502 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | RECONSTRUCT EMPIRE BOULEVARD | RECONSTRUCTION OF EMPIRE BLVD FROM FRANKLIN AVENUE TO UTICA AVENUERECONSTRUCTION OF THE EXISTING ROADWAYROADWAY RECONSTRUCTION SHALL INCLUDE NEW CURBS, SIDEWALKS, AND REQUIREREPLACEMENTAMENITIES WILL BE INCLUDEDCITY FUNDEDIN CONJUNCTION WITH DEP | 2019 | 20921 | 2018.38 | 2460 | 0 | 0 | 0 | 0 | 0 | 4478.38 | 771.73 | 7964 | 0 | 0 | 0 | 0 | 0 | 8735.73
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK797W | Schenck Avenue | PRIMARY STREET RECONSTRUCTION | 205 | HW-0796 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | SCHENCK AVENUE | SCHENCK AVENUE | 2019 | 4882 | 335 | 0 | 2160 | 0 | 0 | 0 | 0 | 2495 | 0 | 0 | 0 | 0 | 3600 | 0 | 0 | 3600
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK876 | RECONSTRUCTION OF WYCKOFF AVENUE, BROOKLYN | PRIMARY STREET RECONSTRUCTION | 204 | HW-0876 HW-1684 HW-D101 HW-K005 HW-0200 TF-0002 TF-0502 HW-0944 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | WYCKOFF AVENUE FROM FLUSHING AVENUE TO GATES AVENUERECONSTRUCTION OF THE EXISTING ROADWAYROADWAY RECONSTRUCTION SHALL INCLUDE NEW CURBS, SIDEWALKS, AND REQUIREREPLACEMENTAMENITIES WILLL NOT BE INCLUDEDCITY FUNDEDIN CONJUNCTION WITH DEP | 2019 | 19145 | 5195.91 | 19 | 18436 | 0 | 0 | 0 | 0 | 23650.91 | 0 | 0 | 15794 | 0 | 0 | 0 | 0 | 15794
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWKF488R | Hamilton Asphalt Plant Roof Replacement | FACILITY RECONSTRUCTION | 200 | HW-0003 |  | HAMILTON ASPHALT PLANT ROOF REPLACEMENT | HAMILTON ASPHALT PLANT ROOF REPLACEMENT | 2019 | 727 | 445.12 | 228 | 3226 | 0 | 0 | 0 | 0 | 3899.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWKKP005 | DUMBO D.M.A. - VINEGAR HILL AREA | PRIMARY STREET RECONSTRUCTION | 202 | HW-0001K HW-0944 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | DUMBO D.M.A. | DUMBO D.M.A. | 2019 | 2200 | 32672.39 | 9435 | 0 | 0 | 0 | 0 | 0 | 42107.39 | 17978.26 | 4119 | 0 | 0 | 0 | 0 | 0 | 22097.26
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWKP2029 | Reconstruction of Putnam Plaza Triangle | RECONSTRUCTION OF RETAINING WALLS | 202 | HW-1684 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | PUTNAM TRIANGLE STREETSCAPE | PUTNAM TRIANGLE STREETSCAPE | 2019 | 150 | 3519.26 | 981 | 0 | 0 | 0 | 0 | 0 | 4500.26 | 1767.03 | 0 | 0 | 288 | 0 | 0 | 0 | 2055.03
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP15KCL | Simple, Complex, & Landmark Ped Ramps - Brooklyn | PEDESTRIAN RAMP CONSTRUCTION | 200 | HW-0200 |  | SIMPLE, COMPLEX, & LANDMARK PED RAMPS - BROOKLYN | SIMPLE, COMPLEX, & LANDMARK PED RAMPS - BROOKLYN | 2019 | 5721 | 9049.76 | 447 | 0 | 0 | 0 | 0 | 0 | 9496.76 | 84.5 | 0 | 0 | 0 | 0 | 0 | 0 | 84.5
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP15KTA | Complex Ped Ramps - Transit Authority - Brooklyn | PEDESTRIAN RAMP CONSTRUCTION | 200 | HW-0200 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | COMPLEX PED RAMPS - TRANSIT AUTHORITY - BROOKLYN | COMPLEX PED RAMPS - TRANSIT AUTHORITY - BROOKLYN | 2019 | 3575 | 6711.3 | 354 | 0 | 0 | 0 | 0 | 0 | 7065.3 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 135
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19KC1 | Citywide Complex Pedestrian Ramps - Brooklyn | PEDESTRIAN RAMP CONSTRUCTION | 200 | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CITYWIDE COMPLEX PEDESTRIAN RAMPS- BROOKLYN | 2019 | 6687 | 0 | 523 | 0 | 6180 | 0 | 0 | 0 | 6703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19KC2 | Citywide Complex Pedestrian Ramps - Brooklyn | PEDESTRIAN RAMP CONSTRUCTION | 200 | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CITYWIDE COMPLEX PEDESTRIAN RAMPS- BROOKLYN | 2019 | 6687 | 0 | 759 | 0 | 6180 | 0 | 0 | 0 | 6939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19KC3 | Citywide Complex Pedestrian Ramps - Brooklyn | PEDESTRIAN RAMP CONSTRUCTION | 200 | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CITYWIDE COMPLEX PEDESTRIAN RAMPS- BROOKLYN | 2019 | 6687 | 0 | 615 | 0 | 6180 | 0 | 0 | 0 | 6795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF5 | Multi-Site Pedestrian Safety Phase 5 | PRIMARY STREET RECONSTRUCTION | 200 | HW-0200 TF-0002 TF-0502 HW-0944 SE-0002M EP-0007 HW-0001K HW-0001M HW-0001Q HW-0001X HW-D101 HW-K005 HW-D102 HW-D103 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | MULTI-SITE LOCATIONS | MULTI-SITE LOCATIONS | 2019 | 400 | 1480 | 21883 | 5592 | 0 | 0 | 0 | 0 | 28955 | 0 | 365 | 1025 | 0 | 0 | 0 | 0 | 1390
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ009K | NEW LOTS PLAZA | PRIMARY STREET RECONSTRUCTION | 205 | SE-087HW HW-1684 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | NEW LOTS PLAZA | NEW LOTS PLAZA | 2019 | 2500 | 5029.34 | 69 | 0 | 0 | 0 | 8 | 0 | 5106.34 | 2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 2.3
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ010K | FOWLER SQUARE PLAZA | PRIMARY STREET RECONSTRUCTION | 202 | HW-1684 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | FOWLER SQUARE PLAZA | FOWLER SQUARE PLAZA | 2019 | 2500 | 5853.24 | 35 | 0 | 0 | 0 | 0 | 0 | 5888.24 | 23.33 | 0 | 0 | 0 | 0 | 0 | 0 | 23.33
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ016K | Broadway Bedford Plaza | PRIMARY STREET RECONSTRUCTION | 201 | WM-0001 HW-1684 TF-0002 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | BROADWAY BEDFORD PLAZA | BROADWAY BEDFORD PLAZA | 2019 | 3079 | 5710.17 | 37 | 0 | 0 | 0 | 0 | 0 | 5747.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ017K | Osborn Street Plaza | PRIMARY STREET RECONSTRUCTION | 200 | HW-1684 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | OSBORN STREET PLAZA | OSBORN STREET PLAZA | 2019 | 2500 | 0 | 510 | 0 | 0 | 3050 | 0 | 0 | 3560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR18K2 | Pedestrian Ramp Rehabilitation - Brooklyn | PEDESTRIAN RAMP CONSTRUCTION | 200 | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | PEDESTRIAN RAMP REHABILITATION - BROOKLYN | 2019 | 9412 | 1266.44 | 8543 | 0 | 0 | 0 | 0 | 0 | 9809.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19K1 | Pedestrian Ramp Rehabilitation - Brooklyn | PEDESTRIAN RAMP CONSTRUCTION | 200 | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | PEDESTRIAN RAMP REHABILITATION- BROOKLYN | 2019 | 13813 | 0 | 13813 | 0 | 0 | 0 | 0 | 0 | 13813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19K2 | Pedestrian Ramp Rehabilitation - Brooklyn | PEDESTRIAN RAMP CONSTRUCTION | 200 | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | PEDESTRIAN RAMP REHABILITATION- BROOKLYN | 2019 | 13813 | 0 | 13742 | 0 | 0 | 0 | 0 | 0 | 13742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2016K1 | Prior Notice Sidewalks - Brooklyn | SIDEWALK RECONSTRUCTION | 200 | HW-0200 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | PRIOR NOTICE SIDEWALKS - BROOKLYN | PRIOR NOTICE SIDEWALKS - BROOKLYN | 2019 | 5646 | 14154.18 | 8930 | 0 | 0 | 0 | 0 | 0 | 23084.18 | 1473.58 | 80 | 0 | 0 | 0 | 0 | 0 | 1553.58
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2016K2 | Prior Notice Sidewalks - Brooklyn | SIDEWALK RECONSTRUCTION | 200 | HW-0200 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | PRIOR NOTICE SIDEWALKS - BROOKLYN | PRIOR NOTICE SIDEWALKS - BROOKLYN | 2019 | 5646 | 13944.01 | 8785 | 0 | 0 | 0 | 0 | 0 | 22729.01 | 1466.8 | 0 | 0 | 0 | 0 | 0 | 0 | 1466.8
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRK1 | Trench Restoration - Brooklyn | PRIMARY STREET RECONSTRUCTION | 200 | HW-0001K HW-K005 HW-D101 |  |  | TRENCH RESTORATION - BROOKLYN | 2019 | 25278 | 2029.02 | 0 | 0 | 23333 | 965 | 0 | 0 | 26327.02 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 500
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRK883 | Trench Restoration -- Bay Parkway, Brooklyn | PRIMARY STREET RECONSTRUCTION | 200 | HW-0001K |  | TRENCH RESTORATION -- BAY PARKWAY, BROOKLYN | TRENCH RESTORATION -- BAY PARKWAY, BROOKLYN | 2019 | 5129 | 0 | 0 | 0 | 5129 | 0 | 0 | 0 | 5129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LB-104KEN | KENSINGTON - Replacement Facility | REHABILITATION AND RELOCATION OF BRANCH LIBRARIES | 212 | LB-K001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BROOKLYN | THIS PROJECT CONSISTS OF THE DESIGN AND CONSTRUCTION OF THE NEW KENSINGTON BRANCH LIBRARY. THE BUILDING WILL HAVE AN AREA OF 10,000 SQUARE FEET. | 2019 | 12788 | 16617.42 | 0 | 0 | 54 | 0 | 0 | 0 | 16671.42 | 710.34 | 0 | 0 | 0 | 0 | 0 | 0 | 710.34
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC10CDHC | CLARENDON HVAC Replacement | ESSENTIAL RECONSTRUCTION OF FACILITIES | 217 | LB-0104 LB-D104 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BOILER REPLACEMENT | 2019 | 775 | 471.63 | 151 | 2077 | 0 | 0 | 0 | 0 | 2699.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC11BBHC | BRIGHTON BEACH - HVAC Replacement | ESSENTIAL RECONSTRUCTION OF FACILITIES | 213 | LB-D104 LB-0104 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BRIGHTON BEACH ROOF REPLACEMENT | 2019 | 525 | 1799.79 | 101 | 0 | 0 | 0 | 0 | 0 | 1900.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC11UPRF | ULMER PARK - Roof Replacement | ESSENTIAL RECONSTRUCTION OF FACILITIES | 213 | LB-K001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ULMER PARK ROOF REPLACEMENT | 2019 | 520 | 1992.03 | 58 | 0 | 0 | 0 | 0 | 0 | 2050.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC12STHC | SARATOGA BOILER AND HVAC REPLACEMENT | ESSENTIAL RECONSTRUCTION OF FACILITIES | 216 | LB-0104 LB-D104 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | SARATOGA HVAC REPLACEMENT | 2019 | 790 | 249.6 | 223 | 3150 | 0 | 0 | 0 | 0 | 3622.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC13BPRF | BOROUGH PARK INTERIOR AND EXTERIOR REHABILITATION | ESSENTIAL RECONSTRUCTION OF FACILITIES | 210 | LB-0104 LB-D104 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ROOF RENOVATION | 2019 | 3177 | 1549.16 | 0 | 33 | 16392 | 0 | 0 | 0 | 17974.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC14CYHC | CYPRESS HILLS HVAC REPLACEMENT | ESSENTIAL RECONSTRUCTION OF FACILITIES | 205 | LB-D104 LB-0104 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CYPRESS HILLS HVAC REPLACEMENT | 2019 | 1018 | 322.19 | 0 | 0 | 0 | 0 | 673 | 0 | 995.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC14LDRF | LEONARD ROOF REPLACEMENT | ESSENTIAL RECONSTRUCTION OF FACILITIES | 201 | LB-D104 LB-0104 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | LEONARD ROOF REPAIR | 2019 | 975 | 294.83 | 0 | 0 | 766 | 0 | 0 | 0 | 1060.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC15BWHC | Bushwick Heating & Cooling | ESSENTIAL RECONSTRUCTION OF FACILITIES | 201 | LB-D104 LB-0104 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BUSHWICK HEATING & COOLING | 2019 | 750 | 203.08 | 208 | 0 | 2734 | 0 | 0 | 0 | 3145.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC15FBHC | Flatbush Heating & Cooling | ESSENTIAL RECONSTRUCTION OF FACILITIES | 214 | LB-D104 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | FLATBUSH HEATING & COOLING | 2019 | 1680 | 367.26 | -151 | 0 | 0 | 0 | 1545 | 151 | 1912.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC15FLRF | Flatlands Envelope Rehabilitation | ESSENTIAL RECONSTRUCTION OF FACILITIES | 218 | LB-D104 LB-0104 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | FLATLANDS ENVELOPE REHABILITATION | 2019 | 750 | 221.06 | 82 | 0 | 1796 | 0 | 0 | 0 | 2099.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC15MPHC | Mapleton Boiler & BMS | ESSENTIAL RECONSTRUCTION OF FACILITIES | 212 | LB-D104 LB-0104 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | MAPLETON HEATING & COOLING | 2019 | 777 | 146.24 | 0 | 0 | 545 | 0 | 0 | 0 | 691.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC16MD2F | MIDWOOD 2ND FLOOR RENOVATIONS | ESSENTIAL RECONSTRUCTION OF FACILITIES | 214 | LB-D104 LB-0104 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | MIDWOOD 2ND FLOOR RENOVATION | 2019 | 1030 | 250.93 | 288 | 0 | 0 | 6974 | 0 | 0 | 7512.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC16MPHC | MAPLETON HVAC REPLACEMENT | ESSENTIAL RECONSTRUCTION OF FACILITIES | 212 | LB-D104 LB-0104 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | MAPLETON HVAC REPLACEMENT | 2019 | 750 | 269.4 | 0 | 0 | 2296 | 0 | 0 | 0 | 2565.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC17CDOP | CLARENDON OUTDOOR PLAZA | ESSENTIAL RECONSTRUCTION OF FACILITIES | 217 | LB-D104 |  |  | CLARENDON OUTDOOR PLAZA | 2019 | 218 | 0 | 0 | 141 | 631 | 0 | 0 | 0 | 772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC17MPGD | MAPLETON GARDEN RENOVATION | ESSENTIAL RECONSTRUCTION OF FACILITIES | 212 | LB-D104 |  |  | MAPLETON GARDEN RENOVATION | 2019 | 1000 | 0 | 0 | 0 | 907 | 0 | 0 | 0 | 907 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC17MRAD | MARCY AUDITORIUM REHABILITATION | ESSENTIAL RECONSTRUCTION OF FACILITIES | 203 | LB-D104 LB-0104 |  |  | MARCY AUDITORIUM REHABILITATION | 2019 | 422 | 0 | 0 | 378 | 0 | 0 | 0 | 0 | 378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC17PCFS | PACIFIC LIFE & FIRE SAFETY | ESSENTIAL RECONSTRUCTION OF FACILITIES | 206 | LB-D104 LB-0104 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | PACIFIC LIFE & FIRE SAFETY | 2019 | 638 | 122.44 | 259 | 0 | 0 | 0 | 252 | 0 | 633.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBCA06SPK | SUNSET PARK - Partial Interior Renovation | ESSENTIAL RECONSTRUCTION OF FACILITIES | 201 | LB-D104 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | INTERIOR MODIFICATIONS | 2019 | 1435 | 589.01 | 0 | 0 | 962 | 0 | 0 | 0 | 1551.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBCA07FBH | FLATBUSH - Roof and Boiler Replacement | ESSENTIAL RECONSTRUCTION OF FACILITIES | 214 | LB-0104 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | NEW ROOF AND BOILER | 2019 | 800 | 1866.74 | 249 | 0 | 0 | 0 | 0 | 0 | 2115.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBCENPH1 | CENTRAL LIBRARY RENOVATION - PHASE 1 | ESSENTIAL RECONSTRUCTION OF FACILITIES | 201 | LB-0104 LB-D104 LB-K001 |  |  | CENTRAL RENOVATION PHASE 1 | 2019 | 35451 | 0 | 34730 | 0 | 0 | 0 | 0 | 0 | 34730 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBK13EFBR | EAST FLATBUSH - BRANCH RENOVATION | RECONSTRUCTION NECESSARY TO MAINTAIN FACILITIES |  | LB-0104 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | EAST FLATBUSH TECHNOLOGY CENTER | 2019 | 3325 | 10267.54 | 450 | 1254 | 0 | 0 | 0 | 0 | 11971.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBK15BDHC | BEDFORD HEATING & COOLING REPLACEMENT | ESSENTIAL RECONSTRUCTION OF FACILITIES | 203 | LB-K001 LB-D104 LB-0104 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | HEATING AND COOLING | 2019 | 1070 | 314.93 | 45 | 0 | 3027 | 0 | 0 | 0 | 3386.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBK15BRRF | BAY RIDGE ENVELOPE REHAB | ESSENTIAL RECONSTRUCTION OF FACILITIES | 210 | LB-K001 LB-0104 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BAY RIDGE ENVELOPE REHAB | 2019 | 930 | 849.35 | 232 | 0 | 0 | 0 | 0 | 0 | 1081.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBK15WTHC | WINDSOR TERRACE HEATING & COOLING REPLACEMENT | ESSENTIAL RECONSTRUCTION OF FACILITIES | 207 | LB-K001 LB-D104 LB-0104 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | WINDSOR TERRACE HEATING & COOLING REPLACEMENT | 2019 | 750 | 933 | 1924 | 0 | 0 | 0 | 625 | 0 | 3482 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBK16CIBR | Coney Island - 2nd Floor Renovation | ESSENTIAL RECONSTRUCTION OF FACILITIES | 213 | LB-K001 LB-D104 LB-0104 |  |  | BRANCH RENO | 2019 | 1070 | 393.74 | 854 | 0 | 0 | 0 | 678 | 0 | 1925.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBK16STRF | SARATOGA ENVELOPE REHABILITATION | ESSENTIAL RECONSTRUCTION OF FACILITIES | 216 | LB-K001 LB-D104 LB-0104 |  |  | SARATOGA ROOF REPLACEMENT | 2019 | 1260 | 0 | 184 | 0 | 996 | 0 | 0 | 0 | 1180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBKA05RUG | RUGBY - Partial Interior Rehab/Public Service Enhancements | ESSENTIAL RECONSTRUCTION OF FACILITIES | 217 | LB-D104 LB-D001 LB-0104 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | PARTIAL INTERIOR /PUBLIC SERVICE ENHANCEMENTS | 2019 | 1140 | 8330.02 | 1614 | 621 | 0 | 0 | 0 | 0 | 10565.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM08DKRF | DEKALB - Roof Replacment | ESSENTIAL RECONSTRUCTION OF FACILITIES | 204 | LB-0104 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | DYKER ROOF REPLACEMENT | 2019 | 571 | 924.12 | 124 | 0 | 0 | 0 | 0 | 0 | 1048.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM08WBRF | WILLIAMSBURG - Roof Replacment | ESSENTIAL RECONSTRUCTION OF FACILITIES | 201 | LB-0104 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ROOF REPLACEMENT AT WILLIAMSBURG | 2019 | 1114 | 1310.22 | 362 | 0 | 0 | 0 | 0 | 0 | 1672.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM13CGHC | CARROLL GARDENS HVAC REPLACEMENT | ESSENTIAL RECONSTRUCTION OF FACILITIES | 206 | LB-0104 LB-D104 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CARROLL GARDENS HVAC REPLACEMENT | 2019 | 1105 | 525.63 | 193 | 0 | 3053 | 0 | 0 | 0 | 3771.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM13CYFS | CYPRESS HILLS FIRE SAFETY | ESSENTIAL RECONSTRUCTION OF FACILITIES | 205 | LB-0104 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CYPRESS HILLS FIRE SAFETY | 2019 | 200 | 88.74 | 0 | 0 | 0 | 0 | 0 | 582 | 670.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM13FLHC | FLATLANDS BOILER , HVAC, BMS, FIRE SAFETY REPLACEMENT | ESSENTIAL RECONSTRUCTION OF FACILITIES | 218 | LB-0104 LB-D104 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | FLATLANDS BOILER REPLACEMENT | 2019 | 1942 | 537.64 | 0 | 0 | 0 | 0 | 2317 | 0 | 2854.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM13LDHC | LEONARD HVAC REPLACEMENT | ESSENTIAL RECONSTRUCTION OF FACILITIES | 201 | LB-0104 LB-D104 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | LEONARD HVAC REPLACEMENT | 2019 | 965 | 336.04 | 223 | 0 | 1997 | 0 | 0 | 0 | 2556.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM14BWRF | BUSHWICK ROOF REPLACEMENT | ESSENTIAL RECONSTRUCTION OF FACILITIES | 201 | LB-0104 LB-D104 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BUSHWICK ROOF REPLACEMENT | 2019 | 1072 | 235.51 | 40 | 0 | 1115 | 0 | 0 | 0 | 1390.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM14CDRF | CLARENDON ROOF REPLACEMENT | ESSENTIAL RECONSTRUCTION OF FACILITIES | 217 | LB-0104 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CLARENDON ROOF REPLACEMENT | 2019 | 877 | 948.15 | 50 | 0 | 0 | 0 | 0 | 0 | 998.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM14MRHC | MARCY HVAC REPLACEMENT | ESSENTIAL RECONSTRUCTION OF FACILITIES | 203 | LB-0104 LB-D104 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | MARCY HVAC REPLACEMENT | 2019 | 974 | 2179.2 | 229 | 0 | 0 | 0 | 0 | 0 | 2408.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM14WTRF | WINDSOR TERRACE ROOF REPLACEMENT | ESSENTIAL RECONSTRUCTION OF FACILITIES | 207 | LB-0104 WP-0169 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | WINDSOR TERRACE ROOF REPLACEMENT | 2019 | 932 | 1247.12 | 0 | 0 | 0 | 65 | 0 | 0 | 1312.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM14WWRF | WALT WHITMAN ROOF REPLACEMENT | ESSENTIAL RECONSTRUCTION OF FACILITIES | 202 | LB-0104 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | WALT WHITMAN ROOF REPLACEMENT | 2019 | 1077 | 997.49 | 104 | 485 | 0 | 0 | 0 | 0 | 1586.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM15GBRF | GERRITSEN BEACH ENVELOPE REHAB | ESSENTIAL RECONSTRUCTION OF FACILITIES | 215 | LB-0104 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BUILDING ENVELOPE REHAB | 2019 | 827 | 241.41 | 0 | 0 | 0 | 1266 | 0 | 0 | 1507.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM15MPRF | Mapleton Envelope Rehabilitation | ESSENTIAL RECONSTRUCTION OF FACILITIES | 212 | LB-0104 LB-D104 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | MAPLETON ENVELOPE REHABILITATION | 2019 | 870 | 304.29 | 146 | 0 | 2878 | 0 | 0 | 0 | 3328.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM15RDHC | Ryder Heating & Cooling | ESSENTIAL RECONSTRUCTION OF FACILITIES | 212 | LB-0104 LB-D104 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RYDER HEATING & COOLING | 2019 | 827 | 164.79 | 96 | 0 | 2605 | 0 | 0 | 0 | 2865.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM15RDRF | Ryder Envelope Rehabilitation | ESSENTIAL RECONSTRUCTION OF FACILITIES | 212 | LB-0104 LB-D104 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RYDER ENVELOPE REHABILITATION | 2019 | 873 | 241.01 | 0 | 0 | 1578 | 0 | 0 | 0 | 1819.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM15WTFS | WINDSOR TERRACE FIRE SAFETY | ESSENTIAL RECONSTRUCTION OF FACILITIES | 207 | LB-0104 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | WINDSOR TERRACE FIRE SAFETY | 2019 | 210 | 101.57 | 44 | 0 | 0 | 0 | 0 | 0 | 145.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM16GSFC | GRAVESEND FACADE REHAB | ESSENTIAL RECONSTRUCTION OF FACILITIES | 215 | LB-0104 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | GRAVESEND FACADE REHAB | 2019 | 637 | 268.07 | 0 | 122 | 1208 | 0 | 0 | 0 | 1598.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM17ARBR | ARLINGTON BRANCH RENOVATION | ESSENTIAL RECONSTRUCTION OF FACILITIES | 205 | LB-0104 LB-D104 |  |  | ARLINGTON BRANCH RENOVATION | 2019 | 9175 | 0 | 911 | 61 | 0 | 7144 | 0 | 0 | 8116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM17NUOH | NEW UTRECHT BRANCH OVERHAUL | ESSENTIAL RECONSTRUCTION OF FACILITIES | 211 | LB-0104 LB-D104 |  |  | NEW UTRECHT BRANCH OVERHAUL | 2019 | 26333 | 2360.26 | 0 | 0 | 22008 | 0 | 0 | 0 | 24368.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM18BVOH | BROWNSVILLE BRANCH OVERHAUL | ESSENTIAL RECONSTRUCTION OF FACILITIES | 216 | LB-0104 LB-D104 |  |  | BROWNSVILLE BRANCH OVERHAUL | 2019 | 23742 | 2197.52 | 81 | 0 | 0 | 19463 | 0 | 0 | 21741.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM18EPOH | EASTERN PARKWAY BRANCH OVERHAUL | ESSENTIAL RECONSTRUCTION OF FACILITIES | 209 | LB-0104 |  |  | EASTERN PARKWAY BRANCH OVERHAUL | 2019 | 22000 | 0 | 2260 | 0 | 0 | 17740 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBP18WIBR | WASHINGTON IRVING BRANCH RENOVATION | ESSENTIAL RECONSTRUCTION OF FACILITIES | 204 | LB-D104 LB-0101 LB-0108 |  |  | WASHINGTON IRVING BRANCH RENOVATION | 2019 | 10753 | 0 | 1337 | 0 | 0 | 8684 | 0 | 0 | 10021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBP18WWBR | WALT WHITMAN BRANCH RENOVATION | ESSENTIAL RECONSTRUCTION OF FACILITIES | 202 | LB-0101 LB-0108 |  |  | WALT WHITMAN BRANCH RENOVATION | 2019 | 7470 | 0 | 0 | 625 | 0 | 6125 | 0 | 0 | 6750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | NC-61 | NEWTOWN CREEK NATURE WALK PHASES 2 & 3 | CONSENT DECREE UPGRADING AND CONSTRUCTION | 200 | WP-0283 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | PHASE 2 REQUIRES DRIVING DRIVING PILES TO SUPPORT THE WALK OVER THE WATER IN WHALE CREEK. PHASE 3 REQUIRES PILES, A NEW SEWER LINE ALONG WITH ANTICIPATED LANDSCAPING ELEMENTS | 2019 | 18700 | 12685.53 | 114 | 1488 | 0 | 0 | 0 | 0 | 14287.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | NC-61A | NEWTON CREEK NATURE WALK - PHSE 3 | CONSENT DECREE UPGRADING AND CONSTRUCTION | 200 | WP-0283 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | NEWTON CREEK NATURE WALK | CONSTRUCTION OF NEWTON CREEK NATURE WALK | 2019 | 10810 | 2262.14 | 9826 | 283 | 960 | 0 | 0 | 0 | 13331.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | NDF-ATLBB | NDF - Atlantic Avenue Broadband Conduit (HWD10105) | NEIGHBORHOOD REVITALIZATION | 200 | ED-0384 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NDF - ATLANTIC AVENUE BROADBAND CONDUIT | 2019 | 1700 | 0 | 1700 | 0 | 0 | 0 | 0 | 0 | 1700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | NDF-IBZ | NDF - ENY IBZ Improvements | NEIGHBORHOOD REVITALIZATION | 200 | ED-0384 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | IBZ STREET IMPROVEMENTS AND BROADBAND SERVICE | 2019 | 8200 | 1071.47 | 0 | 2197 | 0 | 33 | 5000 | 0 | 8301.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79-77AX | 77TH PRECINCT ANNEX RENOVATION | POLICE FACILITIES | 200 208 | PO-0079 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | 77 ANNEX RENOVATION | 2019 | 800 | 1322.21 | 306 | 133 | 0 | 0 | 0 | 0 | 1761.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79-77FA | 77TH PRECINCT FIRE ALARM SYSTEM | POLICE FACILITIES | 200 208 | PO-0079 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | 77TH PRECINCT FIRE ALARM SYSTEM | 2019 | 835 | 0 | 257 | 1173 | 0 | 0 | 0 | 0 | 1430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79SHOPR | SERVICE SHOP #6 ROOF RENOVATION | POLICE FACILITIES | 200 | PO-0079 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | SERVICE SHOP #3 AND # 6 | SHOP # 3 AND # 6 ROOF RENOVATIONS | 2019 | 4727 | 379.89 | 235 | 4714 | 0 | 0 | 0 | 0 | 5328.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV235ELEV | BMA - Brooklyn Museum - Bldg. Elevators/Electrical Upgrades | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | PV-K235 PV-D235 PV-0235 |  | 200 EASTERN PARKWAY, BROOKLYN, NY | ELEVATOR AND ELECTRICAL WORK | 2019 | 2622 | 0 | 0 | 2570 | 0 | 0 | 0 | 0 | 2570 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV236SGD2 | BBG - Brooklyn Botanic Garden - South Garden Dev. Phase 2 | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | PV-0236 PV-K236 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES |  | BBG WATER GARDEN LANDSCAPING AND EARTHWORK | 2019 | 6050 | 5981 | 0 | 0 | 0 | 50 | 0 | 0 | 6031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV236SGD3 | BBG - Brooklyn Botanic Garden - South Garden Dev. Phase 3 | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | WM-0001 PV-K236 |  |  | BBG SOUTH GARDEN PHASE 3 | 2019 | 700 | 14031.43 | 206 | 0 | 0 | 0 | 1 | 0 | 14238.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV262-AUD | Brooklyn Children's Museum Auditorium | ESSENTIAL RECONSTRUCTION OF FACILITIES | 208 | PV-D262 PV-K262 PV-0262 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES |  | MAIN AUDITORIUM FITOUT. | 2019 | 1000 | 1073.81 | 6960 | 0 | 1184 | 0 | 68 | 0 | 9285.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV262-RTW | BCM - Brooklyn Children's Museum Retaining Wall | ESSENTIAL RECONSTRUCTION OF FACILITIES | 208 | PV-K262 PV-D262 PV-0467 PV-0262 |  |  | BROOKLYN CHILDREN'S MUSEUM: RETAINING WALL CONSTRUCTION | 2019 | 5856 | 659.7 | 0 | 500 | 4648 | 0 | 0 | 0 | 5807.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW322X7 | 345 ADAMS ST. - LL 11 CYCLE 7 FACADE REPAIRS | REHABILITATION OF CITY-OWNED OFFICE SPACE | 202 | PW-0322 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | FACADE REPAIRS AS PER LL 11/98 INSPECTIONS FOR 345 ADAMS STREET | 2019 | 1089 | 0 | 0 | 0 | 0 | 0 | 1189 | 0 | 1189 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77DCA | 245 MESEROLE ST. - DCA TEST STATION REHABILITATION | REHABILITATION OF CITY-OWNED OFFICE SPACE | 201 | PW-0077 PU-0025 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | REHABILITATION OF CRITICAL LIFE AND SAFETY SYSTEMS | 2019 | 249 | 4212.88 | 132 | 1081 | 0 | 0 | 0 | 0 | 5425.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77DCA2 | 245 MESEROLE ST. - DCA STORM SEWER REHAB | REHABILITATION OF CITY-OWNED OFFICE SPACE | 201 | PW-0077 |  |  | STORM SEWER UPGRADE | 2019 | 1164 | 1136.63 | 455 | 0 | 0 | 0 | 0 | 0 | 1591.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77GOWAN | GOWANUS CANAL 1 ST TURNING BASIN | MISCELLANEOUS CONSTRUCTION | 206 | PW-0077 |  |  | GOWANUS CANAL 1ST STREET TURNING BASIN ENVIRONMENTAL REMEDIATION DESIGN | 2019 | 4800 | 3856.07 | 0 | 0 | 444 | 0 | 0 | 0 | 4300.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77OEMS2 | 165 CADMAN PLAZA - CATWALK 3RD FLOOR | REHABILITATION OF CITY-OWNED OFFICE SPACE | 201 | PW-0077 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | 165 CADMAN PLAZA - CATWALK 3RD FLOOR | 2019 | 196 | 0 | 0 | 0 | 587 | 0 | 0 | 0 | 587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PWD308JCI | JCC OF GREATER CONEY ISLAND | RENOVATION OF OTHER CITY-OWNED FACILITIES | 213 | PW-D308 |  | RESCIND $414,207 IN 8/12. | JCC CONEY ISLAND | 2019 | 1635 | 125.73 | 0 | 0 | 1060 | 0 | 0 | 0 | 1185.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PWD30BENC | BENJAMIN BANNEKER ACADEMY FOR COMMUNITY DEVELOPMENT | EQUIPMENT AND INTERAGENCY SERVICES |  | PW-D308 |  |  | BENJAMIN BANNEKER ACADEMY FOR COMMUNITY DEVELOPMENT--TECHNOLOGY UPGRADES | 2019 | 100 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PWKBEFORD | BEDFORD ATLANTIC ARMORY - NENOVATIONS BEDFORD ATLANTIC ARMOR | MISCELLANEOUS CONSTRUCTION |  | PW-K077 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RENOVATIONS OF BEDFORD ATLANTIC ARMORY DRILL SHED AND OTHER SPACES INTO A RECREATIONAL FACILITY. | 2019 | 1060 | 240 | 0 | 0 | 1975 | 0 | 0 | 0 | 2215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | REMPIV | Remsen Yard Reconstruction Phase IV | FACILITY PURCHASES AND RECONSTRUCTION | 218 | EP-0006 |  |  | REMSEN YARD RECONSTRUCTION PHASE 4 | 2019 | 1300 | 0 | 0 | 1742 | 0 | 0 | 0 | 0 | 1742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-383N | Brooklyn 17/18 HVAC and Roof Replacement | GARAGES AND FACILITIES | 217 218 | S-0136 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | REPLACE ROOF TOP HVAC INCLUDING INSTALLATION OF BUILDING MAINTENCE SYSTEM AND FIRE ALARM WORK | 2019 | 7500 | 2877.91 | 212 | 0 | 21064 | 0 | 0 | 0 | 24153.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-436 | Brooklyn 6 Garage Rehabilitation | GARAGES AND FACILITIES | 206 | S-0136 |  |  | REHAB | 2019 | 100 | 2140.57 | 303 | 0 | 10836 | 0 | 0 | 0 | 13279.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | S216-399A | SW BROOKLYN MARINE TRANSFER STATION | SOLID WASTE MANAGEMENT | 200 210 | S-0216 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | MTS | MARINE TRANSFER STATION | 2019 | 111755 | 178384.11 | 3176 | 0 | 0 | 0 | 0 | 0 | 181560.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SAND1048 | BWG - Sunset Park North | PRIMARY STREET RECONSTRUCTION | 200 | HW-0001K |  | BWG - IMPROVED PROJECT | BWG - IMPROVED PROJECT | 2019 | 5795 | 56 | 67 | 0 | 961 | 0 | 0 | 0 | 1084 | 506 | 596 | 0 | 8648 | 0 | 0 | 0 | 9750
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SAND13GB | Reconstruction of Gerritsen Beach - Hurricane Sandy | PRIMARY STREET RECONSTRUCTION | 200 | HW-0001K HW-0200 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | RECONSTRUCTION OF GERRITSEN BEACH - HURRICANE SANDY | RECONSTRUCTION OF GERRITSEN BEACH - HURRICANE SANDY | 2019 | 1484 | 12.65 | 0 | 552 | 0 | 0 | 0 | 0 | 564.65 | 113.88 | 0 | 4949 | 0 | 0 | 0 | 0 | 5062.88
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBRIGH | SANDY - NEW BRIGHTON COMFORT STATION RECONSTRUCTION | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 200 | P-1018 |  |  | NEW BRIGHTON COMFORT STATION RECONSTRUCTION | 2019 | 5453 | 398.18 | 312 | 24 | 0 | 0 | 1263 | 0 | 1997.18 | 424.65 | 2804 | 219 | 0 | 0 | 9 | 0 | 3456.65
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDELEC4 | 60TH PRECINCT ELECTRICAL SYSTEM REPLACEMENT( SANDY) | POLICE FACILITIES | 213 | PO-0079 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | 60TH PRECINCT ELECTRICAL SYSTEM REPLACEMENT( SANDY) | 2019 | 4409 | 453.75 | 334 | 0 | 0 | 0 | 0 | 0 | 787.75 | 1220.49 | 2994 | 0 | 0 | 0 | 0 | 0 | 4214.49
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDELEC7 | AVIATION ELECTRICAL (SANDY) | POLICE FACILITIES | 200 | PO-0079 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | ELECTRICAL SYSTEM REPLACEMENT | 2019 | 1005 | 684.85 | 191 | 0 | 0 | 0 | 0 | 0 | 875.85 | 874.56 | 295 | 0 | 0 | 0 | 0 | 0 | 1169.56
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDELEC8 | ERIE BASIN TOW POUND ELECTRICAL (SANDY) | POLICE FACILITIES | 200 206 | PO-0079 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | ELECTRICAL SYSTEM REPLACEMENT | 2019 | 1990 | 36.11 | 0 | 178 | 0 | 0 | 0 | 0 | 214.11 | 3.11 | 0 | 1592 | 0 | 0 | 0 | 0 | 1595.11
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW04 | Reconstruction of West 37th Street- Hurricane Sandy | PRIMARY STREET RECONSTRUCTION | 200 | HW-0001K WM-0001 SE-0002K | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | RECONSTRUCTION OF WEST 37TH STREET- HURRICANE SANDY | RECONSTRUCTION OF WEST 37TH STREET- HURRICANE SANDY | 2019 | 412 | 0 | 0 | 0 | 467 | 0 | 0 | 0 | 467 | 0 | 0 | 0 | 107 | 0 | 0 | 0 | 107
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW19 | Reconstruction of Downtown Brooklyn - Hurricane Sandy | PRIMARY STREET RECONSTRUCTION | 200 | HW-0001K | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | RECONSTRUCTION OF DOWNTOWN BROOKLYN - HURRICANE SANDY | RECONSTRUCTION OF DOWNTOWN BROOKLYN - HURRICANE SANDY | 2019 | 1607 | 5 | 0 | 0 | 0 | 126 | 0 | 0 | 131 | 0.5 | 0 | 0 | 0 | 1123 | 0 | 0 | 1123.5
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR03 | Jamaica Bay Greenway - Canarsie Pier Connector | PRIMARY STREET RECONSTRUCTION | 200 | HW-0001K |  | CANARSIE PIER | CANARSIE PIER ACCESS IMPROVEMENTS | 2019 | 2000 | 159.2 | 0 | 0 | 1440 | 0 | 0 | 0 | 1599.2 | 474 | 0 | 0 | 1526 | 0 | 0 | 0 | 2000
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRDHK | Red Hook HMGP | MISCELLANEOUS | 200 | PU-0100 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RED HOOK HMGP PROJECT | 2019 | 100000 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 50000
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-797 | Storm & San Sewer in Meeker Ave | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 201 | SE-0002K WM-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | STORM & SAN SEWER IN MEEKER AVE BETW VAN DAM ST AND GARDNER AVE | 2019 | 10053 | 128.1 | 0 | 0 | 6790 | 0 | 0 | 0 | 6918.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-851 | HLSS , STRM, SAN & COMB SWERS & WM IN FRESH CREEK BASIN AREA | PROGRAMMATIC RESPONSE TO REGULATORY MANDATES | 218 | SE-0200K SE-0002K | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | HLSS , STRM, SAN & COMB SWERS & WM IN FRESH CREEK BASIN AREA | 2019 | 32855 | 65748.21 | 2235 | 0 | 0 | 0 | 0 | 0 | 67983.21 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 5
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-856 | HLSS, Strm, San & Comb Swrs, & WM Fresh Creek Basin ,Ph 3A | PROGRAMMATIC RESPONSE TO REGULATORY MANDATES | 205 | SE-0004 SE-0200K SE-0002K WM-0001 |  |  | (CS-FC-SEW) PHASE 3A: H.L.S., STORM & COMBINED SEWERS, & WM WORK IN FRESH CREEK BASIN AREA, FLATLANDS AVE BETWEEN GEORGIA AVE AND VAN SICLEN AVE. ETC., 26TH WARD, BROOKLYN | 2019 | 19643 | 1218 | 3 | 21606 | 0 | 0 | 0 | 0 | 22827 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-857 | HLSS, Strm, San & Comb Swrs, & WM Fresh Creek Basin ,Ph 3B | PROGRAMMATIC RESPONSE TO REGULATORY MANDATES | 205 218 | SE-0004 SE-0200K SE-0002K WM-0001 |  | (CS-FC-SEW) PHASE 3B: H.L.S., STORM, COMBINED & SANITARY SEWERS, AND WM WORKS IN FRESH CREEK BASIN AREA, FOSTER AVE BETWEEN ROCKAWAY PARKWAY AND BANK ST, 26TH WARD, BOROUGH OF BROOKLYN | (CS-FC-SEW) PHASE 3B: H.L.S., STORM, COMBINED & SANITARY SEWERS, AND WM WORKS IN FRESH CREEK BASIN AREA, FOSTER AVE BETWEEN ROCKAWAY PARKWAY AND BANK ST, 26TH WARD, BOROUGH OF BROOKLYN | 2019 | 44952 | 800 | 0 | 42970 | 0 | 0 | 0 | 0 | 43770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-858 | HLSS Installation, Combined Sewer Replmnt (HWK1048A) | REPLACEMENT OF CHRONICALLY FAILING COMPONENTS | 201 | SE-0004 SE-0002K WM-0001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | HIGH LEVEL STORM SEWER INSTALLATION, COMBINED SEWER REPLACEMENT AND WATER MAIN REPLACEMENT IN WEST ST. BETWEEN EAGLE ST. AND QUAY ST., ETC BOROUGH OF BROOKLYN. | 2019 | 18792 | 31448.64 | 329 | 0 | 0 | 30 | 0 | 0 | 31807.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002302 | COMBINED SEWERS AT SHAFT 23B | REPLACEMENT OF CHRONICALLY FAILING COMPONENTS | 200 | SE-0002K | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | COMBINED SEWERS AT SHAFT 23B | COMBINED SEWERS AT SHAFT 23B | 2019 | 3036 | 5675.66 | 40 | 0 | 0 | 0 | 0 | 0 | 5715.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002321 | COMBINED SEWER AT SHAFT 23B IN COLUMBUS ST AREA PHASE II | REPLACEMENT OF CHRONICALLY FAILING COMPONENTS | 206 | SE-0002K | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | COMBINED SEWER AT SHAFT 23B IN COLUMBUS ST AREA PHASE II | COMBINED SEWER AT SHAFT 23B IN COLUMBUS ST AREA PHASE II | 2019 | 1824 | 0 | 0 | 0 | 0 | 6567 | 0 | 0 | 6567 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002351 | Rehab of Comb swrs &w/m in Wycoff Av bet Cooper &Flushing Av | REPLACEMENT OF CHRONICALLY FAILING COMPONENTS | 204 | SE-0002K WM-0001 EP-0007 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | REHAB OF COMB SWRS &W/M IN WYCOFF AV BET COOPER &FLUSHING AV | 2019 | 6020 | 218.05 | 0 | 27652 | 0 | 0 | 0 | 0 | 27870.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002354 | SAN SWRS-GATEWAY ESTATES - PHASE D (HD-161D/SEK20057) | EXTENSIONS TO ACCOMMODATE NEW DEVELOPMENT | 205 | SE-0002K WM-0001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | SANITARY SEWERS IN GATEWAY ESTATES - PHASE D | SANITARY SEWERS IN GATEWAY ESTATES - PHASE D | 2019 | 6300 | 14541.97 | 2929 | 0 | 0 | 0 | 0 | 0 | 17470.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002355 | Combined Sewer in Water St. - Old Fulton St. and Main St. | EXTENSIONS TO ACCOMMODATE NEW DEVELOPMENT | 202 | SE-0002K WM-0001 WM-0006 HW-0001K | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | COMBINED SEWER IN WATER ST - OLD FULTON ST AND MAIN ST | 2019 | 4475 | 28466.7 | 529 | 0 | 0 | 0 | 0 | 0 | 28995.7 | 4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 4.4
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002376 | COMB SWR REPLCMNT & WM WORK IN PRESIDENT ST | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 209 | SE-0002K WM-0001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | COMB SWR REPLCMNT & WM WORK IN PRESIDENT ST, B/T KINGSTON AV & ALBANYAV | 2019 | 3824 | 0 | 0 | 0 | 3477 | 0 | 0 | 0 | 3477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002377 | Santy sewer & WM replmnt in E 72nd St btwn Ave L & Royce Pl | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 218 | SE-0002K WM-0001 HW-0001K |  |  | SANITARY SEWER & WM REPLACEMENT IN EAST 72ND STREET BETWEEN AVE L & ROYCE PLACE | 2019 | 2148 | 0 | 0 | 9166 | 0 | 0 | 0 | 0 | 9166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002380 | Combined relief sewer & WM replac. at 7ST B/T 3 & 4 AV, BKL | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 206 | EP-0007 HW-0200 SE-1000 SE-0200K SE-0944 TF-0002 TF-0502 WM-0001 |  |  | COMBINED RELIEF SEWER & CHAMBERS & WATER MAIN REPLACEMENT AT 7TH STREET B/T 3 & 4 AVENUES, BKLYN | 2019 | 2946 | 591.75 | 0 | 9501 | 0 | 0 | 0 | 0 | 10092.75 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 12
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002382 | Reconstruction of 4th Ave, w/HWK1669 | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 200 | SE-0002X |  |  | GREAT STREETS, RECONSTRUCTION OF 4TH AVE, FUNDED W/HWK1669 DOT PRIORITY FUNDS | 2019 | 3511 | 0 | 0 | 3511 | 0 | 0 | 0 | 0 | 3511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002383 | Combined SE installation & WM replacement in Dean Street | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 208 | SE-0002K | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | COMBINED SEWER INSTALLATION & WATER MAIN REPLACEMENT IN DEAN STREET, BTW 6TH AVE & VANDERBILT AVE, BROOKLYN | 2019 | 11721 | 0 | 0 | 0 | 0 | 11721 | 0 | 0 | 11721 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002386 | Replace combined sewer & WM work,Park Pl & Underhill Ave, BK | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 208 | SE-0002K WM-0001 |  |  | REPLACEMENT OF COMBINED SEWER, BULKHEADING OF EXISTING SEWERS & WATERMAIN WORK, PARK PL. B/T UNDERHILL & FLATBUSH AVES, BROOKLYN | 2019 | 8478 | 500 | 0 | 9197 | 0 | 0 | 0 | 0 | 9697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20056 | STORM SEWERS-GATEWAY ESTATES - PHASE C (HD-161C) | EXTENSIONS TO ACCOMMODATE NEW DEVELOPMENT | 205 | SE-0200K SE-0002K WM-0001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | STORM SEWERS IN GATEWAY ESTATES - PHASE C | STORM SEWERS IN GATEWAY ESTATES - PHASE C | 2019 | 4899 | 11344.79 | 385 | 0 | 0 | 0 | 0 | 0 | 11729.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20057 | STRM SWRS-GATEWAY ESTATES - PHASE D (HD-161D/SEK002354) | EXTENSIONS TO ACCOMMODATE NEW DEVELOPMENT | 205 | SE-0200K | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | STORM SEWERS IN GATEWAY ESTATES - PHASE D | STORM SEWERS IN GATEWAY ESTATES - PHASE D | 2019 | 4900 | 4986.21 | 1219 | 0 | 0 | 0 | 0 | 0 | 6205.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20065 | High level storm sewer Gowanus Canal Area | EXTENSIONS TO ACCOMMODATE NEW DEVELOPMENT | 206 | SE-0004 SE-0002K TF-0002 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | DRAINAGE PLAN HIGH LEVEL STORM SEWER INSTALLATION AND WM-1 REPLACEMENT IN GOWANUS CANAL AREA. | 2019 | 9400 | 36685.68 | 419 | 0 | 0 | 0 | 0 | 0 | 37104.68 | 122.24 | 0 | 0 | 0 | 0 | 0 | 0 | 122.24
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20067 | High level storm sewer Gowanus Canal Area. Phase 2. | EXTENSIONS TO ACCOMMODATE NEW DEVELOPMENT | 206 | SE-0004 SE-0944 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | DRAINAGE PLAN HIGH LEVEL STORM SEWER INSTALLATION AND WM-1 REPLACEMENT IN GOWANUS CANAL AREA. PHASE 2. | 2019 | 9600 | 24831.83 | 101 | 0 | 0 | 183 | 0 | 0 | 25115.83 | 8216.56 | 234 | 0 | 0 | 0 | 0 | 0 | 8450.56
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20068 | New Storm and Combined Sewers and Water Main work in 9th st. | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 206 | SE-0200K SE-0002K WM-0001 HW-0200 TF-0002 TF-0502 EP-0007 SE-1000 SE-0944 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | NEW STORM AND COMBINED SEWERS AND WATER MAIN WORK IN 9TH ST. BETWEEN 2ND. AVE. AND GOWANUS CANAL ETC. | 2019 | 4743 | 2485.37 | 27150 | 0 | 0 | 0 | 0 | 0 | 29635.37 | 0 | 42 | 0 | 0 | 0 | 0 | 0 | 42
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20069 | Storm Sewer installation, & WM replacement, Gerritsen Beach, | EXTENSIONS TO ACCOMMODATE NEW DEVELOPMENT | 215 | WM-0001 EP-0007 SE-0002K SE-0200K |  |  | STORM SEWER INSTALLATION, & WM REPLACEMENT, GERRITSEN BEACH AREA. PHASE 1, BOROUGH OF BROOKLYN | 2019 | 4195 | 174.95 | 1928 | 14819 | 0 | 0 | 0 | 0 | 16921.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20070 | Guniting & exterior repair of the 25th Ave outfall sewer | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 211 | SE-0200K |  |  | GUNITING & EXTERIOR OUTFALL REPAIR OF THE 25TH AVE OUTFALL SEWER AT GRAVESEND BAY, BOROUGH OF BROOKLYN | 2019 | 1013 | 669.11 | 0 | 4385 | 0 | 0 | 0 | 0 | 5054.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK201BN6 | Reconstruction of Existing Sewers, Brooklyn NORTH | REPLACEMENT OF CHRONICALLY FAILING COMPONENTS | 200 | SE-0002K EP-0007 |  |  | EMERGENCY RECONSTRUCTION OF EXISTING SEWERS, BROOKLYN NORTH | 2019 | 6000 | 7982.22 | 991 | 0 | 0 | 0 | 0 | 0 | 8973.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK201BN7 | Reconstruction of Existing Sewers, North Brooklyn | REPLACEMENT OF CHRONICALLY FAILING COMPONENTS | 200 | SE-0002K |  |  | RECONSTRUCTION OF EXISTING SEWERS, NORTH BROOKLYN | 2019 | 6250 | 7465 | 3616 | 0 | 0 | 0 | 0 | 0 | 11081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK201BN8 | Reconstruction of Existing Sewers, North Brooklyn | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 200 | SE-0002K EP-0007 |  |  | RECONSTRUCTION OF EXISTING SEWERS, NORTH BROOKLYN | 2019 | 6650 | 0 | 7465 | 0 | 0 | 0 | 0 | 0 | 7465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK201BS7 | Reconstruction of Existing Sewers, South Brooklyn | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 200 | SE-0002K EP-0007 |  |  | RECONSTRUCTION OF EXISTING SEWERS, NORTH BROOKLYN | 2019 | 7862 | 0 | 7862 | 0 | 0 | 0 | 0 | 0 | 7862 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SOLARDOS1 | Brooklyn 17/18 HVAC AND ROOF REPLACEMENT | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 201 | PU-0025 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  |  | 2019 | 3793 | 497.22 | 0 | 6731 | 0 | 0 | 0 | 0 | 7228.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOE606 | DOE - BMS UPGRADES | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 214 | PU-0025 |  |  | SQ FT | 2019 | 947 | 0 | 791 | 70 | 0 | 0 | 0 | 0 | 861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOE607 | DOE - LIGHTING UPGRADES | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 204 | PU-0025 |  |  | UNIT | 2019 | 1224 | 0 | 1110 | 0 | 0 | 0 | 0 | 0 | 1110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOE608 | DOE - WIRELESS PNEUMATIC THERMOSTADTS - 20 SCHOOLS | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 208 | PU-0025 |  |  | UNIT | 2019 | 2453 | 0 | 0 | 2315 | 0 | 0 | 0 | 0 | 2315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOE702 | DOE - VACANCY SENSORS | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 201 | PU-0025 |  |  | DOE - VACANCY SENSORS | 2019 | 441 | 0 | 0 | 441 | 0 | 0 | 0 | 0 | 441 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEFDN902 | FDNY - Window Replacement at 4 FDNY Fire Houses | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 201 | PU-0025 |  |  | FDNY - WINDOW REPLACEMENT AT 4 FDNY FIRE HOUSES | 2019 | 0 | 0 | 0 | 673 | 0 | 0 | 0 | 0 | 673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEHHC601 | HHC - Woodhull Medical Center - Air Handlers | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 204 | PU-0025 |  |  | HHC - WOODHULL MEDICAL CENTER : UPGRADE AIR HANDLING UNITS | 2019 | 2323 | 0 | 2112 | 0 | 0 | 0 | 0 | 0 | 2112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEHHC607 | HHC - KINGS COUNTY HOSP PH 2 LIGHTING | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 204 | PU-0025 HO-0214 |  |  | UNIT | 2019 | 1229 | 0 | 1135 | 0 | 0 | 0 | 0 | 0 | 1135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264BKCV | 210 JORALEMON ST. OCA RELOCATION | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 201 | CO-0264 |  |  | OCA- RELOCATION FROM 141 LIVINGSTON ST. TO 210 JORALEMON | 2019 | 251438 | 4839.17 | 5942 | 205437 | 18599 | 14645 | 0 | 0 | 249462.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO272CHIL | 45 MONROE PL CHILLER REPLACEMENT | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 201 | CO-0272 |  |  | SQ FT | 2019 | 1958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190 | 1454 | 0 | 0 | 0 | 0 | 1644
20190425 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO278ELV | 360 ADAMS ST.- ELEVATOR MODERNIZATION | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 202 | CO-0278 |  |  | 360 ADAMS ST - ELEVATOR MODERNIZATION | 2019 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 22963 | 23963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO278RF | 360 ADAMS STREET - ROOF | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 201 | CO-0278 |  |  | 360 ADAMS STREET - ROOF | 2019 | 0 | 0 | 0 | 0 | 0 | 43 | 0 | 430 | 473 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO278TOIL | 360 ADAMS ST. - CODE COMPLIANT TOILET UPGRADE | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 202 | CO-0278 |  |  | 360 ADAMS ST. - CODE COMPLIANT TOILET UPGRADE | 2019 | 3350 | 0 | 0 | 0 | 0 | 350 | 0 | 3000 | 3350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E09-00030 | NYPD - 09-064; 69th Precinct; 9720 Foster Avenue | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 208 | PO-0079 |  |  | ENERGY EFFICIENCY UPGRADE AT 69TH PRECINCT; 9720 FOSTER AVENUE | 2019 | 552 | 1116.85 | 0 | 47 | 0 | 0 | 0 | 0 | 1163.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E13-0008 | EDC - BROOKLYN CRUISE TERMINAL | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT |  | PU-0025 |  |  | BROOKLYN CRUISE TERMINAL | 2019 | 1409 | 1347.13 | 0 | 110 | 0 | 0 | 0 | 0 | 1457.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E17-0003 | HHC - Cogeneration Heat and Power -Kings County Hospital | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 201 | PU-0025 |  |  | DCAS - COGENERATION HEAT AND POWER -KINGS COUNTY HOSPITAL | 2019 | 6318 | 1091.52 | 4646 | 0 | 0 | 0 | 0 | 0 | 5737.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E19-0001 | DOHMH - Bedford Health Center | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 201 | PU-0025 |  |  | DOHMH - BROWNSVILLE HEALTH CENTER | 2019 | 269 | 0 | 269 | 0 | 0 | 0 | 0 | 0 | 269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E19-0002 | DOHMH - Brownsville Health Center | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 201 | PU-0025 |  |  | DOHMH - BUSHWICK HEALTH CENTER | 2019 | 182 | 0 | 182 | 0 | 0 | 0 | 0 | 0 | 182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E19-0003 | DOHMH - Bushwick Health Center | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 201 | PU-0025 |  |  | DOHMH - BUSHWICK HEALTH CENTER | 2019 | 273 | 0 | 273 | 0 | 0 | 0 | 0 | 0 | 273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E19-0004 | DOHMH - Crown Heights Health Center | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 201 | PU-0025 |  |  | DOHMH - CROWN HEIGHTS HEALTH CENTER | 2019 | 168 | 0 | 168 | 0 | 0 | 0 | 0 | 0 | 168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E19-0007 | NYPD - 77th Precinct | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 201 | PU-0025 |  |  | NYPD - 77TH PRECINCT | 2019 | 303 | 0 | 303 | 0 | 0 | 0 | 0 | 0 | 303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E19-0008 | NYPD - Brooklyn North Boro Command | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 201 | PU-0025 |  |  | NYPD - BROOKLYN NORTH BORO COMMAND | 2019 | 157 | 0 | 157 | 0 | 0 | 0 | 0 | 0 | 157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0017 | BPL - Bushwick Branch Library | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 201 | PU-0025 |  |  | BPL - BUSHWICK BRANCH LIBRARY | 2019 | 122 | 0 | 122 | 0 | 0 | 0 | 0 | 0 | 122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0020 | NYPD - 71st Precinct | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 201 | PU-0025 |  |  | NYPD - 71ST PRECINCT | 2019 | 350 | 0 | 0 | 350 | 0 | 0 | 0 | 0 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0021 | NYPD - 73rd Precinct | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 201 | PU-0025 |  |  | NYPD - 73RD PRECINCT | 2019 | 475 | 0 | 475 | 0 | 0 | 0 | 0 | 0 | 475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0022 | NYPD - 79th Precinct | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 201 | PU-0025 |  |  | NYPD - 79TH PRECINCT | 2019 | 381 | 0 | 381 | 0 | 0 | 0 | 0 | 0 | 381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0023 | NYPD - 69th Precinct | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 201 | PU-0025 |  |  | NYPD - 69TH PRECINCT | 2019 | 248 | 0 | 0 | 248 | 0 | 0 | 0 | 0 | 248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0027 | DSNY - Cioffe Borough Repair Shop | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 201 | PU-0025 |  |  | DSNY - CIOFFE BOROUGH REPAIR SHOP | 2019 | 266 | 0 | 266 | 0 | 0 | 0 | 0 | 0 | 266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0028 | DSNY - Brooklyn North 9 District Garage | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 201 | PU-0025 |  |  | DSNY - BROOKLYN NORTH 9 DISTRICT GARAGE | 2019 | 145 | 0 | 145 | 0 | 0 | 0 | 0 | 0 | 145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0029 | DSNY - Brooklyn South 16 District Garage | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 201 | PU-0025 |  |  | DSNY - BROOKLYN SOUTH 16 DISTRICT GARAGE | 2019 | 200 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0030 | DSNY-Brooklyn South 7 and 10 District Garage | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 201 | PU-0025 |  |  | DSNY-BROOKLYN SOUTH 7 AND 10 DISTRICT GARAGE | 2019 | 347 | 0 | 0 | 347 | 0 | 0 | 0 | 0 | 347 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0031 | DSNY-Brooklyn North 8 District Garage | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 201 | PU-0025 |  |  | DSNY-BROOKLYN NORTH 8 DISTRICT GARAGE | 2019 | 300 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0032 | DSNY-Queens West 9 District Garage (Leased In) | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 201 | PU-0025 |  |  | DSNY-QUEENS WEST 9 DISTRICT GARAGE (LEASED IN) | 2019 | 333 | 0 | 0 | 333 | 0 | 0 | 0 | 0 | 333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0037 | DOHMH - Fort Greene Health Center | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 201 | PU-0025 |  |  | DOHMH - FORT GREENE HEALTH CENTER | 2019 | 418 | 0 | 418 | 0 | 0 | 0 | 0 | 0 | 418 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79540K | RELOCATION FROM 540 KINGSLAND AVE | POLICE FACILITIES | 200 | PO-0079 |  |  | RELOCATION FROM 540 KINGSLAND AVE | 2019 | 0 | 0 | 1528 | 0 | 0 | 0 | 0 | 0 | 1528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW322PLA5 | 345 ADAMS ST RESTACK - SUPPLEMENTAL NEED | REHABILITATION OF CITY-OWNED OFFICE SPACE | 201 | PW-0077 |  |  | BIDS | 2019 | 0 | 0 | 0 | 19636 | 0 | 0 | 0 | 0 | 19636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW322PLAN | 345 ADAMS RESTACKING PLAN | REHABILITATION OF CITY-OWNED OFFICE SPACE | 202 | PW-0322 |  |  | 345 ADAMS, RESTACKING OF AGENCIES | 2019 | 107049 | 6275 | 0 | 96729 | 3520 | 0 | 0 | 0 | 106524 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW325ELC3 | 210 JORALEMON ST. ELECTRICAL UPGRADE AND EMERGENCY GENERATOR | REHABILITATION OF CITY-OWNED OFFICE SPACE | 201 | PW-0325 |  |  | ELECTRICAL UPGRADE AND EMERGENCY GENERATOR | 2019 | 33358 | 28659.7 | -941 | 0 | 5319 | 0 | 0 | 0 | 33037.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW325EXTR | 210 JORALEMON ST.- EXTERIOR | LEGAL MANDATES AND CORRECTION OF UNSAFE CONDITIONS | 202 | PW-0325 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 210 JORALEMON ST. BROOKLYN, NY 11201 | MASONRY PATCHING; WATERPROOFING & CAULKING | 2019 | 934 | 832.2 | 35 | 0 | 0 | 0 | 0 | 0 | 867.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW325STA3 | 210 JORALEMON STREET STABILIZATION | LEGAL MANDATES AND CORRECTION OF UNSAFE CONDITIONS | 200 202 | PW-0325 |  |  | INSPECTION, PROBING CORE DRILLING AND STABILIZATION REAR OF BUILDING TO DDC | 2019 | 3672 | 2705.77 | 917 | 0 | 0 | 0 | 0 | 0 | 3622.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DOF5 | DOF - RELOCATION FROM 210 JORALEMON AND 345 ADAMS | RENOVATION OF LEASED SPACE | 201 | PW-0326 |  |  | RELOCATION FROM 210 JORALEMON AND 345 ADAMS STREET. TO LEASED SPACE | 2019 | 23523 | 14561.64 | 2618 | 0 | 6343 | 0 | 0 | 0 | 23522.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DOR2 | DORIS - WAREHOUSE RELOCATION - BROOKLYN | RENOVATION OF LEASED SPACE | 201 | PW-0326 |  |  | DORIS LEASE RENEWAL AT 148-19 39TH AVENUE | 2019 | 28291 | 0 | 21791 | 6500 | 0 | 0 | 0 | 0 | 28291 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DYWH | DYCD - DOI BROOKLYN WAREHOUSE RENEWAL | RENOVATION OF LEASED SPACE | 201 | PW-0326 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | DYCD - DOI BROOKLYN WAREHOUSE RENEWAL | 2019 | 928 | 16.42 | 0 | 2805 | 0 | 0 | 0 | 0 | 2821.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326ITWH | DOITT - BROOKLYN WAREHOUSE SPACE | RENOVATION OF LEASED SPACE | 201 | PW-0326 |  |  | DOITT BROOKLYN WAREHOUSE SPACE | 2019 | 840 | 0 | 0 | 840 | 0 | 0 | 0 | 0 | 840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326LAW7 | LAW - 167 41ST - LAW DEPT CONSOLIDATION | RENOVATION OF LEASED SPACE | 201 | PW-0326 |  |  | 167 41ST - LAW DEPT CONSOLIDATION | 2019 | 0 | 0 | 0 | 13182 | 0 | 0 | 0 | 0 | 13182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326OEM3 | OEM Expansion of Leased Space 930 Flushing Avenue | RENOVATION OF LEASED SPACE | 202 | PW-0326 |  |  | OEM EXPANSION FOR WAREHOUSE | 2019 | 85000 | 0 | 0 | 0 | 20000 | 0 | 40000 | 25000 | 85000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RAK | LAW DEPT - RAISE THE AGE - BROOKLYN | RENOVATION OF LEASED SPACE | 201 | PW-0326 |  |  | LAW DEPT - RAISE THE AGE - BROOKLYN | 2019 | 0 | 0 | 0 | 5499 | 0 | 0 | 0 | 0 | 5499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW340BOE | BOE - 345 ADAMS ST.- BATHROOMS RENOVATION | BOARD OF ELECTIONS MODERNIZATION | 202 | PW-0340 |  |  | BOE - 345 ADAMS ST.- BATHROOMS RENOVATION | 2019 | 0 | 0 | 0 | 260 | 0 | 0 | 0 | 0 | 260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77BHCAM | 209 JORALEMON STREET - CCTV | EQUIPMENT AND INTERAGENCY SERVICES | 201 | PW-0077 |  |  |  | 2019 | 1026 | 0 | 931 | 0 | 0 | 0 | 0 | 0 | 931 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77ZK07 | BROOKLYN COMMUNITY BOARD 7- 4201 4TH AVENUE | REHABILITATION OF CITY-OWNED OFFICE SPACE | 200 | PW-0077 |  |  | BROOKLYN CB 7 RENOVATIONS | 2019 | 473 | 0 | 0 | 0 | 473 | 0 | 0 | 0 | 473 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD007HPD | HPD - CONSTRUCTION AND RENOVATION OF NORTHSIDE TOWN HALL | MISCELLANEOUS CONSTRUCTION | 201 | PW-D007 |  |  | 134 WYTHE AVE | 2019 | 0 | 0 | 0 | 550 | 0 | 0 | 0 | 0 | 550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD78BLL | 360 ADAMS STREET- BROOKLYN SUPREME COURT LAW LIBRARY | REHABILITATION OF CITY-OWNED OFFICE SPACE | 201 | PW-D078 |  |  | DCAS - BROOKLYN SUPREME COURT LAW LIBRARY | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD78SSCT | 360 ADAMS ST.- HVAC STATE SUPREME COURT | RENOVATION OF OTHER CITY-OWNED FACILITIES | 201 | PW-D078 |  |  | STATE SUPREME COURT 360 ADAMS HVAC | 2019 | 230 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWK2LEED | Brooklyn Borough Hall - LEED- Funding for LEED | REHABILITATION OF CITY-OWNED OFFICE SPACE | 202 | PW-K002 |  |  | BROOKLYN BOROUGH HALL - LEED- FUNDING FOR LEED | 2019 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWK2MEDIA | 209 JORALEMON ST.- BKLYN BORO HALL MEDIA ROOM | REHABILITATION OF CITY-OWNED OFFICE SPACE | 202 | PW-K002 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BROOKLYN BORO HALL MEDIA ROOM | 2019 | 1627 | 1449.97 | 0 | 0 | 0 | 0 | 398 | 0 | 1847.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | RH-59-L | RECONSTRUCT KEY INTERLOCKING SYSTEM - DIESEL GENERATORS | PLANT UPGRADING AND RECONSTRUCTION | 200 | WP-0112 |  | 63 FLUSHING AVENUE, BROOKLYN, N.Y. 11205 | RECONSTRUCTION OF KEY INTERLOCKING SYSTEM (DIESEL GENERATORS AT THE RED HOOK WPCP) | 2019 | 23904 | 33801.66 | 381 | 0 | 0 | 0 | 0 | 0 | 34182.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | SOLARGR20 | NYPA - Capital 02 Rooftop Solar PV | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT |  | PU-0025 |  |  | NYPA - CAPITAL 02 ROOFTOP SOLAR PV | 2019 | 0 | 0 | 0 | 12000 | 0 | 8000 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | WD77STAR | STAR ENGINEERING LAB | MISCELLANEOUS CONSTRUCTION | 214 | PW-D077 |  |  | TO CONVERT A CLASSROOM AT THE SCIENCE TECHNOLOGY AND REASEARCH EARLYCOLLEGE SCHOOL AT ERASMUS CAMPUS IN BROOKLYN TO AN ELECTRICAL ENGINEERING LAB | 2019 | 350 | 0 | 0 | 350 | 0 | 0 | 0 | 0 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 035 | NEW YORK RESEARCH LIBRARY | LRCE12DOT | SASB:Improvements to the NYPL Vicinity | ESSENTIAL RECONSTRUCTION OF FACILITIES | 300 305 | L-D002 L-0103 L-0101 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | IMPROVEMENTS TO THE NYPL VICINITY | 2019 | 3750 | 0 | 0 | 0 | 0 | 0 | 350 | 323 | 673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LN18FEEL | 58TH STREET BRANCH--ADA COMPLIANCE - NEW ELEVATOR | ESSENTIAL RECONSTRUCTION OF FACILITIES | 305 | LN-D008 |  |  | 58TH STREET BRANCH--ADA COMPLIANCE - NEW ELEVATOR | 2019 | 0 | 0 | 0 | 0 | 0 | 15 | 135 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LN18HGHVA | HAMILTON GRANGE - Replace HVAC | ESSENTIAL RECONSTRUCTION OF FACILITIES | 309 | LN-0008 |  |  | REPLACE HVAC | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 1350 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LN18LBBOI | HEISKELL - Boilers (5) and HVAC replacement (11 units) | ESSENTIAL RECONSTRUCTION OF FACILITIES | 305 | LN-0008 |  |  | HEISKELL - BOILERS (5) AND HVAC REPLACEMENT (11 UNITS) | 2019 | 0 | 0 | 0 | 0 | 300 | 2700 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LN18TSHVA | TOMPKINS SQUARE - HVAC | ESSENTIAL RECONSTRUCTION OF FACILITIES | 303 | LN-0008 |  |  | HVAC | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LNCA16INW | Elevator | ESSENTIAL RECONSTRUCTION OF FACILITIES | 300 | LN-D008 |  |  | ELEVATOR | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LNDMACOMB | MACOMB'S BRIDGE - New Branch | EXPANSION AND CONSTRUCTION OF FACILITIES | 310 | LN-M001 |  | MACOMB'S BRIDGE 2650 ADAM CLAYTON POWELL JR. BLVD, NY, NY 10039 | NEW BRANCH RECONSTRUCTION | 2019 | 797 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LNMA16BLD | Bloomingdale - Roof Renovation | ESSENTIAL RECONSTRUCTION OF FACILITIES | 307 | LN-M001 LN-D008 |  |  | ROOF RENOVATION | 2019 | 0 | 0 | 0 | 0 | 0 | 65 | 479 | 0 | 544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LNMA17CSQ | CHATHAM SQUARE - Boiler Replacement | ESSENTIAL RECONSTRUCTION OF FACILITIES | 303 | LN-D008 LN-M001 |  |  | CHATHAM SQUARE - BOILER REPLACEMENT. | 2019 | 400 | 0 | 0 | 0 | 0 | 43 | 319 | 0 | 362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LNSSEXTFW | 67th Street Building envelope - Fa ade & window restoration | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | LN-D008 |  |  | NYPL EAST 67TH STREET BRANCH BUILDING ENVELOPE -- FAÚADE AND WINDOW RESTORATION. FY19 ADP | 2019 | 0 | 0 | 0 | 0 | 0 | 150 | 1350 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LNWBEXTFA | Webster - Building envelope, Fa ade restoration | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | LN-D008 |  |  | NYPL WEBSTER BRANCH BUILDING ENVELOPE -- FAÚADE RESTORATION | 2019 | 0 | 0 | 0 | 0 | 0 | 200 | 1800 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 040 | DEPARTMENT OF EDUCATION | ACEDOE510 | Condensing Boilers for Indoor Pools | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT |  | PU-0025 |  |  | CONDENSING BOILERS FOR INDOOR POOLS | 2019 | 0 | 0 | 1178 | 102 | 0 | 0 | 0 | 0 | 1280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 040 | DEPARTMENT OF EDUCATION | ACEDOE511 | Dual Fuel Burner Conversion | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT |  | PU-0025 |  |  | THE SCOPE OF WORK INCLUDES, BUT IS NOT LIMITED: REPLACEMENT OF BOILERS EXISTING #4 OIL BURNERS WITH DUAL FUEL BURNERS AND RELATED COMPONENTS. | 2019 | 0 | 0 | 9464 | 106 | 0 | 0 | 0 | 0 | 9570 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 040 | DEPARTMENT OF EDUCATION | ACEDOE512 | Steam System Optimization | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT |  | PU-0025 |  |  | STEAM SYSTEM OPTIMIZATION INCLUDES REPLACEMENT OF STEAM TRAPS THROUGHTOUT THE BUILDING, REPLACEMENT OF PNEUMATIC CONTROL SYSTEM COMPONENTS,REPLACEMENT OF INEFFICIENT /DEFECTIVE VACUUM CONDENSATE RETURN UNIT, AND ALSO INSTALLATION OF AN AUTOMATED BOILER WATER TREATMENT STATION TO ENSURE THAT THE ENTIRE STEAM HEATING SYSTEM WORK EFFICIENTLY TO PROVIDE THE REQUIRED SPACE HEATING. | 2019 | 0 | 0 | 9019 | 799 | 0 | 0 | 0 | 0 | 9818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 040 | DEPARTMENT OF EDUCATION | ACEFIT510 | FIT - C Building Fan Coils Control | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 300 | PU-0025 |  |  | THE PROJECT CONSISTS OF INSTALLATION OF FAN COIL CONTROL VALVES ON THE WATER CIRCUIT AND FAN SPEED CONTROL TO MAINTAIN THE ROOM TEMPERATURE | 2019 | 0 | 520 | 260 | 0 | 0 | 0 | 0 | 0 | 780 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | ACECUN601 | Hunter Campus School HVAC Project | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 308 | PU-0025 |  |  | HUNTER CAMPUS SCHOOL HVAC PROJECT | 2019 | 770 | 0 | 700 | 0 | 0 | 0 | 0 | 0 | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | ACECUN701 | CUNY - BMCC CORRIDOR LIGHTING UPGRADE | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 301 | PU-0025 |  |  | CUNY - BMCC CORRIDOR LIGHTING UPGRADE | 2019 | 598 | 0 | 598 | 0 | 0 | 0 | 0 | 0 | 598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | BA013-013 | Data Center, UPS, and Cooling | MISCELLANEOUS RECONSTRUCTION | 300 306 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | DATA CENTER, UPS AND COOLING | 2019 | 570 | 0 | 0 | 0 | 170 | 400 | 0 | 0 | 570 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | BA019-016 | Library Modernization | MISCELLANEOUS RECONSTRUCTION | 300 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | LIBRARY MODERNIZATION | 2019 | 1000 | 0 | 1600 | 0 | 0 | 0 | 0 | 0 | 1600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | BA024-018 | Modification of Main Entrance at 17 Lexington Avenue | MISCELLANEOUS RECONSTRUCTION | 300 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | MODIFICATION OF MAIN ENTRANCE AT 17 LEXINGTON AVE | 2019 | 250 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | BA025-018 | Marxe Lab/Public Space Upgrades for School of Public Affairs | MISCELLANEOUS RECONSTRUCTION | 300 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | MARXE LAB/PUBLIC SPACE UPGRADES FOOE SCHOOL OF PUBLIC AFFAIRS | 2019 | 500 | 0 | 0 | 0 | 0 | 260 | 0 | 0 | 260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | BA027-019 | Info. & Technology Library Bldg. Door Replacement | MISCELLANEOUS RECONSTRUCTION | 300 | HN-D300 HN-M300 |  |  | DOOR REPLACEMENT | 2019 | 600 | 0 | 0 | 0 | 400 | 200 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | BA030-020 | Mason Hall A/V System | MISCELLANEOUS RECONSTRUCTION | 300 | HN-M300 |  |  | MASON HALL A/V SYSTEM | 2019 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | CA013-008 | WEB VIDEO SYSTEMS FOR HANDICAPPED STUDENTS, CUNYWIDE | MISCELLANEOUS RECONSTRUCTION |  | HN-0206 HN-D002 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | MECHANICAL, ELECTRICAL AND PLUMBING UPGRADES, CUNYWIDE | 2019 | 3998 | 681.99 | 0 | 0 | 0 | 0 | 1317 | 0 | 1998.99 | 528.09 | 1470 | 0 | 0 | 0 | 0 | 0 | 1998.09
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | CA027-012 | Community College Laboratories | MISCELLANEOUS RECONSTRUCTION | 300 | HN-D002 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | COMMUNITY COLLEGE LABORATORY IMPROVEMENTS | 2019 | 2000 | 1321.88 | 0 | 0 | 0 | 669 | 0 | 0 | 1990.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | CA032-013 | Center for Innovation and Entrepreneurship | MISCELLANEOUS RECONSTRUCTION | 300 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CENTER FOR INNOVATION AND ENTREPRENEURSHIP | 2019 | 2000 | 1786.83 | 0 | 0 | 0 | 0 | 213 | 0 | 1999.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | CA049-019 | CUNY In The Heights | MISCELLANEOUS RECONSTRUCTION | 300 | HN-D002 |  |  | CUNY IN THE HEIGHTS | 2019 | 3040 | 0 | 0 | 3040 | 0 | 0 | 0 | 0 | 3040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | CA050-017 | Health, Safety & ADA Projects | MISCELLANEOUS RECONSTRUCTION | 300 | HN-D002 HN-D003 |  |  | HEALTH, SAFETY & ADA PROJECTS | 2019 | 7835 | 0 | 6652 | 250 | 0 | 0 | 0 | 0 | 6902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | CA050-019 | CUNY-Wide Community College Health, Safety & ADA Projects | MISCELLANEOUS RECONSTRUCTION | 300 | HN-D002 |  |  | CUNY-WIDE COMMUNITY COLLEGE HEALTH, SAFETY & ADA PROJECTS | 2019 | 12000 | 0 | 0 | 12000 | 0 | 0 | 0 | 0 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | CA054-017 | CUNY Accelerated Study in Associate Programs Expansion | MISCELLANEOUS RECONSTRUCTION | 300 | HN-0206 |  |  | CUNY ACCELERATED STUDY IN ASSOCIATE PROGRAMS EXPANSION | 2019 | 2000 | 0 | 0 | 3109 | 0 | 0 | 0 | 0 | 3109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | CA054-018 | CUNY Community College Health, Safety and ADA Projects | MISCELLANEOUS RECONSTRUCTION | 300 | HN-D004 |  |  | CUNY COMMUNITY COLLEGE HEALTH, SAFETY AND ADA PROJECTS | 2019 | 10000 | 0 | 0 | 3027 | 0 | 0 | 0 | 0 | 3027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | CA054MC17 | 70 Murray Street Second & Third Floor Expansion | MISCELLANEOUS RECONSTRUCTION | 300 | HN-0206 |  |  | 70 MURRAY STREET SECOND & THIRD FLOOR EXPANSION | 2019 | 3891 | 0 | 3891 | 0 | 0 | 0 | 0 | 0 | 3891 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | CA201MC04 | BMCC RAMP & PLAZA PEDESTAL REPAIRS | MISCELLANEOUS RECONSTRUCTION | 301 | HN-D004 | PROJECT DELAYED DUE TO UNFORESEEN HAZARDOUS CONDITION |  | CHAMBERS ST. RAMP AND PLAZA PEDESTAL REPAIRS | 2019 | 500 | 1060.86 | 0 | 197 | 0 | 0 | 0 | 0 | 1257.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | CA202MC01 | ADA BATHROOM UPGRADES FOR BMCC | MISCELLANEOUS RECONSTRUCTION | 301 | HN-D002 HN-M001 HN-0206 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ADA BATHROOM UPGRADES FOR 199 CHAMBERS ST. | 2019 | 940 | 3581.05 | 0 | 503 | 0 | 0 | 0 | 0 | 4084.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | CC009-007 | Upgrade North Academic Center Classrooms | MISCELLANEOUS RECONSTRUCTION | 300 309 | HN-D004 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | UPGRADE NORTH ACADEMIC CENTER CLASSROOMS | 2019 | 350 | 619.33 | 0 | 0 | 0 | 0 | 40 | 0 | 659.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | CC012-008 | RESTORATION OF LIBRARY AND BLDG, RANGEL CTR FOR PUBLIC SERV | MISCELLANEOUS RECONSTRUCTION |  | HN-D300 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | RESTORATION OF LIBRARY AND BLDG, RANGEL CTR FOR PUBLIC SERVICE | 2019 | 40 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | CC018-009 | ARONOW THEATER UPGRADE | MISCELLANEOUS RECONSTRUCTION | 300 309 | HN-D300 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | AARON DAVIS HALL - IMPROVEMENTS TO LOBBY AND ENTRANCE | 2019 | 1434 | 0 | 0 | 1174 | 0 | 0 | 0 | 0 | 1174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | CC022-012 | Schiff House Day Care Center Upgrades | MISCELLANEOUS RECONSTRUCTION | 300 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | SCHIFF HOUSE DAY CARE CENTER UPGRADES | 2019 | 1600 | 2078 | 0 | 0 | 0 | 322 | 0 | 0 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | CC023-013 | Grove School Expansion Project | MISCELLANEOUS RECONSTRUCTION | 300 309 | HN-M004 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | GROVE SCHOOL EXPANSION PROJECT | 2019 | 440 | 292.4 | 140 | 0 | 0 | 0 | 0 | 0 | 432.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | CC025-013 | Dominican Studies Institute | MISCELLANEOUS RECONSTRUCTION | 300 309 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | DOMINICAN STUDIES INSTITUTE EXPANSION | 2019 | 200 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | CC026-013 | Aaron Davis Hall | MISCELLANEOUS RECONSTRUCTION | 300 309 | HN-M300 HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | AARON DAVIS HALL | 2019 | 400 | 0 | 0 | 0 | 0 | 400 | 5696 | 0 | 6096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | CC027-014 | Max Bond Center | MISCELLANEOUS RECONSTRUCTION | 300 309 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | MAX BOND CENTER/WINGATE POOL RESTORATION/CONT. & PROF. STUDIES | 2019 | 500 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | CC029-014 | Network Infrastructure Modernization | MISCELLANEOUS RECONSTRUCTION | 300 309 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NETWORK INFRASTRUCTURE MODERNIZATION | 2019 | 2500 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | CC032-015 | City College Computer Lab | MISCELLANEOUS RECONSTRUCTION | 300 | HN-M300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CITY COLLEGE COMPUTER LAB | 2019 | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | CC034-016 | Computer Lab Renovation | MISCELLANEOUS RECONSTRUCTION | 300 | HN-M300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | COMPUTER LAB RENOVATION | 2019 | 250 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | CC037-017 | Harlem Rooftop Garden | MISCELLANEOUS RECONSTRUCTION | 300 | HN-M300 |  |  | HARLEM ROOFTOP GARDEN | 2019 | 201 | 0 | 0 | 0 | 201 | 0 | 0 | 0 | 201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | CC038-017 | Technology Infrastructure Upgrade | MISCELLANEOUS RECONSTRUCTION | 300 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | TECHNOLOGY INFRASTRUCTURE UPGRADE | 2019 | 2400 | 0 | 0 | 0 | 0 | 0 | 2400 | 0 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | CC039-017 | Street Improvements | MISCELLANEOUS RECONSTRUCTION | 300 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | STREET IMPROVEMENTS | 2019 | 200 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | CC041-018 | Wireless Network Upgrade Expansion | MISCELLANEOUS RECONSTRUCTION | 300 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CITY COLLEGE WIRELESS NETWORK UPGRADE AXPANSION | 2019 | 1800 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | CC042-018 | Facility Upgrades | MISCELLANEOUS RECONSTRUCTION | 300 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CITY COLLEGE FACILITY UPGRADES | 2019 | 1252 | 0 | 0 | 0 | 0 | 1252 | 0 | 0 | 1252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | CC045-019 | Kitchen Upgrade for the Culinary Program | MISCELLANEOUS RECONSTRUCTION | 300 | HN-D300 |  |  | KITCHEN UPGRADE FOR THE CULINARY PROGRAM | 2019 | 1200 | 0 | 0 | 0 | 1200 | 0 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | GR009-009 | CLASSROOM EXPANSION PROJECT | MISCELLANEOUS RECONSTRUCTION | 300 305 | HN-M004 HN-M005 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CLASSROOM DEVELOPMENT | 2019 | 550 | 130.96 | 0 | 919 | 0 | 0 | 0 | 0 | 1049.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | GR012-011 | Green Roof / Space Conversion | MISCELLANEOUS RECONSTRUCTION | 300 305 | HN-D300 | PROJECT DELAYED PENDING APPROVAL OF NECESSARY PERMITS |  | STUDENT- FACULTY GREEN ROOF | 2019 | 1000 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | GR013-012 | Classroom Expansion Project - Roof | MISCELLANEOUS RECONSTRUCTION | 300 305 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CLASSROOM EXPANSION PROJECT | 2019 | 1000 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | GR014-013 | Classroom Development Project (9th Floor) | MISCELLANEOUS RECONSTRUCTION | 300 305 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NINETH FLOOR BUILD OUT | 2019 | 500 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | GR017-014 | Bathroom and HVAC Upgrades | MISCELLANEOUS RECONSTRUCTION | 300 305 | HN-M300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BATHROOM AND HVAC UPGRADES | 2019 | 1000 | 1486.87 | 0 | 0 | 0 | 88 | 0 | 0 | 1574.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | GR018-015 | Library Renovations | MISCELLANEOUS RECONSTRUCTION | 300 | HN-D300 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | BATHROOM UPGRADES | 2019 | 500 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | GR023-017 | Improvement of Public Spaces | MISCELLANEOUS RECONSTRUCTION | 300 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | IMPROVEMENT OF PUBLIC SPACES | 2019 | 1200 | 0 | 0 | 0 | 0 | 0 | 975 | 0 | 975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | GR029-020 | AUDITORIUM SOUND SYSTEM | MISCELLANEOUS RECONSTRUCTION | 300 305 | HN-M300 |  |  | AUDITORIUM SOUND SYSTEM | 2019 | 0 | 0 | 0 | 125 | 0 | 0 | 0 | 0 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | GU031-013 | New Community College Student Lab Renovations | MISCELLANEOUS RECONSTRUCTION | 300 | HN-D004 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NEW COMMUNITY COLLEGE STUDENT LAB RENOVATIONS | 2019 | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | GU051-015 | Guttman Comm. Coll. Building Canopy | MISCELLANEOUS RECONSTRUCTION | 300 | HN-D002 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | GUTTMAN BUILDING CANOPY | 2019 | 35 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | HC026-011 | Phone System Upgrade And Expansion | MISCELLANEOUS RECONSTRUCTION | 300 308 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | PHONE SYSTEM UPGRADE AND EXPANSION | 2019 | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | HC032-017 | Athletic Facilities Renovation | MISCELLANEOUS RECONSTRUCTION | 300 | HN-M300 HN-D300 |  |  | ATHLETIC FACILITIES RENOVATION | 2019 | 365 | 85 | 1114 | 0 | 0 | 0 | 0 | 0 | 1199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | HC033-019 | Expansive Glass Addition to the Building Facing West | MISCELLANEOUS RECONSTRUCTION | 308 | HN-M300 HN-D300 |  |  | EXPANSIVE GLASS ADDITION TO THE BUILDING FACING WEST | 2019 | 400 | 0 | 0 | 0 | 400 | 0 | 0 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | HC034-018 | Hunter Campus Atrium | MISCELLANEOUS RECONSTRUCTION | 300 | HN-D300 |  |  | HUNTER CAMPUS ATRIUM | 2019 | 100 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | HC075-098 | HVAC Improvements | ELECTRICAL, MECHANICAL AND HVAC SYSTEM UPGRADING | 308 | HN-0244 HN-0206 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  |  | 2019 | 3267 | 13299.99 | 2473 | 0 | 0 | 0 | 0 | 0 | 15772.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | HU007-004 | Restore Roosevelt House | MISCELLANEOUS RECONSTRUCTION | 300 308 | HN-D004 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | OTHER | 2019 | 1000 | 785.92 | 0 | 0 | 207 | 0 | 0 | 0 | 992.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | HU022-009 | EXPERIMENTAL PSYCHOLOGY LAB BUILDOUT | MISCELLANEOUS RECONSTRUCTION | 300 308 | HN-M004 HN-D004 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | EXPAND PSYCHOLOGY LAB | 2019 | 732 | 588.47 | 0 | 0 | 87 | 0 | 0 | 0 | 675.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | HU026-013 | Science and Health Professions Building | NEW SCHOOL CONSTRUCTION | 300 308 | HN-0300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | SCIENCE AND HEALTH PROFESSIONS BUILDING | 2019 | 100000 | 0 | 0 | 0 | 0 | 13875 | 13875 | 0 | 27750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | HU027-013 | SCHOOL OF NURSING/HEALTH SCIENCE RELOCATION TO C3 | MISCELLANEOUS RECONSTRUCTION | 300 | HN-0300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | SCHOOL OF NURSING/HEALTH SCIENCE RELOCATION TO C3 | 2019 | 47150 | 0 | 0 | 0 | 0 | 23575 | 23575 | 0 | 47150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | HU028-015 | Black Box Performance Space | MISCELLANEOUS RECONSTRUCTION | 300 | HN-M300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BLACK BOX PERFORMANCE SPACE | 2019 | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | HU029-015 | Black Box Media & Arts Flex Space Improvements | MISCELLANEOUS RECONSTRUCTION | 300 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BLACK BOX MEDIA & ARTS FLEX SPACE IMPROVEMENTS | 2019 | 375 | 0 | 0 | 0 | 0 | 375 | 0 | 0 | 375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | HU035-016 | Black Box Theater Renovation Black Box Theater Renovation | MISCELLANEOUS RECONSTRUCTION | 308 | HN-M003 HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | THEATER RENOVATION | 2019 | 612 | 0 | 0 | 0 | 0 | 612 | 0 | 0 | 612 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | HU036-017 | Black Box Renovation | MISCELLANEOUS RECONSTRUCTION | 300 | HN-M300 HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BLACK BOX RENOVATION | 2019 | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | HU037-017 | CUNY Performing Arts Hub | MISCELLANEOUS RECONSTRUCTION | 300 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CUNY PERFORMING ARTS HUB | 2019 | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | HU039-018 | Performing Arts Hub - Renovate N Building Auditorium | MISCELLANEOUS RECONSTRUCTION | 300 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RENOVATE "N" BUILDING AUDITORIUM | 2019 | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 0 | 3500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | HU040-018 | Renovate Performing Arts Hub in North Building | MISCELLANEOUS RECONSTRUCTION | 300 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RENOVATE PERFORMING ARTS HUB IN NORTH BUILDING | 2019 | 1900 | 0 | 0 | 0 | 0 | 1900 | 0 | 0 | 1900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | HU040-019 | Computer Science 10th FL. North Expansion | MISCELLANEOUS RECONSTRUCTION | 300 | HN-M300 |  |  | COMPUTER SCIENCE 10TH FL. NORTH EXPANSION | 2019 | 250 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | HU041-019 | Black Box Media Flex Space | MISCELLANEOUS RECONSTRUCTION | 300 | HN-D300 |  |  | HUNTER COLLEGE BLACK BOX MEDIA FLEX SPACE | 2019 | 2285 | 0 | 0 | 0 | 0 | 2285 | 0 | 0 | 2285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | HU042-019 | Thomas Hunter Hall Upgrades | MISCELLANEOUS RECONSTRUCTION | 300 | HN-D300 |  |  | THOMAS HUNTER HALL UPGRADES | 2019 | 950 | 0 | 950 | 0 | 0 | 0 | 0 | 0 | 950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | JJ018-014 | Green IT | MISCELLANEOUS RECONSTRUCTION | 300 304 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | GREEN IT | 2019 | 300 | 0 | 297 | 0 | 0 | 3 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | JJ021-015 | Lloyd Sealy Library Upgrade | MISCELLANEOUS RECONSTRUCTION | 300 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | LLOYD SEALY LIBRARY UPGRADE | 2019 | 250 | 215 | 0 | 0 | 0 | 35 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | JJ024-017 | Locker Rooms and Gym Entrance | MISCELLANEOUS RECONSTRUCTION | 300 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | LOCKER ROOMS AND GYM ENTRANCE | 2019 | 650 | 0 | 0 | 0 | 0 | 650 | 0 | 0 | 650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | JJ029-018 | Theater ADA Upgrades | MISCELLANEOUS RECONSTRUCTION | 300 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | THEATER ADA UPGRADES | 2019 | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | MC020-006 | Exhaust System | MISCELLANEOUS RECONSTRUCTION | 300 301 | HN-M001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | EXHAUST SYSTEM | 2019 | 1642 | 707.63 | 0 | 92 | 0 | 0 | 0 | 0 | 799.63 | 475.9 | 0 | 0 | 0 | 0 | 0 | 0 | 475.9
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | MC028-010 | CUNY: BMCC, 199 Chambers Street - EE Upgrade | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 301 | HN-M001 PU-0025 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | ENERGY EFFICIENCY UPGRADE AT BOROUGH OF MANHATTAN COMMUNITY COLLEGE; 199 CHAMBERS STREET | 2019 | 9900 | 11047.53 | 0 | 249 | 0 | 0 | 0 | 0 | 11296.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | MC029-012 | Gymnasium Air Conditioning System | MISCELLANEOUS RECONSTRUCTION | 300 301 | HN-D004 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | GYMNASIUM AIR CONDITIONING SYSTEM | 2019 | 1400 | 1000 | 0 | 400 | 0 | 0 | 0 | 0 | 1400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | MC030-012 | Egress Upgrades/Ceiling Replacement | MISCELLANEOUS RECONSTRUCTION | 300 301 | HN-0206 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | EGRESS UPGRADES/CEILING REPLACEMENTS | 2019 | 750 | 0 | 0 | 557 | 0 | 0 | 0 | 0 | 557 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | MC034-014 | Rooftop Air Conditioner Replacement | MISCELLANEOUS RECONSTRUCTION | 300 301 | HN-D005 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ROOFTOP AC UNIT REPLACEMENT | 2019 | 750 | 0 | 0 | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | MC036-016 | Perimeter Security Lighting | MISCELLANEOUS RECONSTRUCTION | 301 | HN-D002 HN-M005 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | PERIMETER SECURITY LIGHTING | 2019 | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | MC037-016 | Community Room HVAC Upgrades | MISCELLANEOUS RECONSTRUCTION | 300 | HN-D002 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | COMMUNITY ROOM HVAC UPGRADES | 2019 | 1350 | 0 | 202 | 1148 | 0 | 0 | 0 | 0 | 1350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | MC038-017 | Gymnasium Led Light Replacement | MISCELLANEOUS RECONSTRUCTION | 300 | HN-M005 |  |  | GYMNASIUM LED LIGHT REPLACEMENT | 2019 | 225 | 0 | 0 | 50 | 175 | 0 | 0 | 0 | 225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | MC039-017 | Cooling Tower Replacement | MISCELLANEOUS RECONSTRUCTION | 300 | HN-D004 |  |  | COOLING TOWER REPLACEMENT | 2019 | 1800 | 149.45 | 0 | 1651 | 0 | 0 | 0 | 0 | 1800.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | MC040-018 | LED Conversion in Public Areas | MISCELLANEOUS RECONSTRUCTION |  | HN-D002 HN-M005 HN-D004 |  |  | LED CONVERSION IN PUBLIC AREAS | 2019 | 1325 | 0 | 0 | 325 | 1000 | 0 | 0 | 0 | 1325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | MC042-018 | BMCC Pedestrian Enclosed Extension | MISCELLANEOUS RECONSTRUCTION | 300 | HN-D004 |  |  | BMCC PEDESTRIAN ENCLOSED EXTENSION | 2019 | 900 | 0 | 0 | 0 | 900 | 0 | 0 | 0 | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | MC043-019 | Early Childhood Center HVAC Improvements | MISCELLANEOUS RECONSTRUCTION | 301 | HN-M005 HN-D002 |  |  | BMCC EARLY CHILDHOOD CENTER HVAC UPGRA | 2019 | 1088 | 0 | 0 | 1088 | 0 | 0 | 0 | 0 | 1088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | MC044-019 | New Corridor Access Controls and Doors | MISCELLANEOUS RECONSTRUCTION | 300 | HN-D002 |  |  | NEW CORRIDOR ACCESS AND CONTROLS | 2019 | 925 | 0 | 0 | 925 | 0 | 0 | 0 | 0 | 925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | MC045-020 | Tribeca Performing Arts Center Theater 1 & 2 Lighting Upgra | MISCELLANEOUS RECONSTRUCTION | 300 | HN-M005 |  |  | TRIBECA PERFORMING ARTS CENTER THEATER 1 & 2 LIGHTING UPGRADE INSTALLATION OF NEW LIGHTING FIXTURES | 2019 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | MH040-014 | Macaulay Honors College Classroom Upgrades | MISCELLANEOUS RECONSTRUCTION | 300 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | MACCAULEY HONORS COLLEGE CLASSROOM UPGRADES | 2019 | 285 | 0 | 0 | 0 | 0 | 285 | 0 | 0 | 285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | MH047-015 | Macaulay Honors College - Server Room HVAC Upgrade | MISCELLANEOUS RECONSTRUCTION | 300 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | HVAC UPGRADE | 2019 | 250 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | MH053-016 | Macaulay Honors College - New Media Lab | MISCELLANEOUS RECONSTRUCTION | 300 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NEW MEDIA LAB | 2019 | 100 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | MH059-017 | Macaulay Honors College Data Science Lab | MISCELLANEOUS RECONSTRUCTION | 300 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | DATA SCIENCE LAB | 2019 | 450 | 0 | 0 | 0 | 0 | 450 | 0 | 0 | 450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | SAND-MC01 | Rehabilitation and Improvements due to Hurricane Sandy | MISCELLANEOUS RECONSTRUCTION | 300 | HN-0206 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RESTORATION AND IMPROVEMENTS OF CAPITAL FACILITIES | 2019 | 2173 | 0 | 0 | 0 | 0 | 0 | 110 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 042 | CITY UNIVERSITY | SJ049-015 | School of Journalism - Space Upgrades | MISCELLANEOUS RECONSTRUCTION | 300 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | SPACE UPGRADES | 2019 | 250 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79 PAL | POLICE ATHLETIC LEAGUE MASONRY | POLICE FACILITIES | 302 | PO-0079 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | 24 1/2 EAST 12TH STREET, NY | TO PROVIDE FOR THE FACADE RE POINTING | 2019 | 300 | 144.46 | 0 | 3298 | 0 | 0 | 0 | 0 | 3442.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 056 | POLICE DEPARTMENT | PO791PPDR | One Police Plaza Doors | POLICE FACILITIES | 300 | PO-0079 |  |  | ONE POLICE PLAZA DOORS | 2019 | 1018 | 0 | 0 | 0 | 0 | 1018 | 0 | 0 | 1018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 056 | POLICE DEPARTMENT | PO791PPR2 | ONE POLICE PLAZA & POLICE LAB ROOFS | POLICE FACILITIES | 300 | PO-0079 |  |  | RECONSTRUCTION | 2019 | 9964 | 0 | 0 | 4824 | 5140 | 0 | 0 | 0 | 9964 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAHO | HVAC REPLACEMENT FOR 20TH, 24TH AND 25TH PCTS | POLICE FACILITIES | 300 307 311 | PO-0079 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | HVAC SYSTEMS | 2019 | 2024 | 2422 | 0 | 236 | 0 | 0 | 0 | 0 | 2658 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAIZ | 24th Precinct Facade | POLICE FACILITIES | 300 | PO-0079 |  |  | TO PROVIDE FOR THE FACADE REHABILITATION OF THE 24TH PCT | 2019 | 715 | 0 | 0 | 1083 | 0 | 0 | 0 | 0 | 1083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAJF | 32ND PCT PARKING LOT | POLICE FACILITIES | 300 | PO-0079 |  |  | PARKING LOT REHABILITATION | 2019 | 67 | 0 | 622 | 0 | 0 | 0 | 0 | 0 | 622 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAJJ | 7TH PRECINCT HVAC REPLACEMENT | POLICE FACILITIES | 300 | PO-0079 |  | 19 PITT ST., MANHATTAN | TO PROVIDE FOR THE 7TH PRECINCT HVAC REPLACEMENT, LOCATED AT 19 PITT ST., MANHATTAN | 2019 | 757 | 799 | 149 | 0 | 0 | 0 | 0 | 0 | 948 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAJM | 30TH PRECINCT ACT TOWER | POLICE FACILITIES | 300 | PO-0079 |  | 451 WEST 151 ST., MANHATTAN | TO PROVIDE FOR THE 30TH PRECINCT COOLING TOWER FOR 451 WEST 151 ST., MANHATTAN | 2019 | 98 | 0 | 333 | 0 | 0 | 0 | 0 | 0 | 333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAJQ | 1 Police Plaza Auditorium | POLICE FACILITIES | 300 | PO-0079 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ONE POLICE PLAZA AUDITOIUM | 2019 | 8661 | 0 | 0 | 0 | 3661 | 5000 | 0 | 0 | 8661 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAJV | 1 POLICE PLAZA OFFICE SPACE TRAILER | POLICE FACILITIES | 300 | PO-0079 |  |  | ESTIMATES | 2019 | 748 | 0 | 748 | 0 | 0 | 0 | 0 | 0 | 748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAKC | ELEVATOR REHABILITATION FOR MIDTOWN NORTH PCT | POLICE FACILITIES | 300 | PO-0079 |  |  | ESTIMATE | 2019 | 842 | 0 | 0 | 842 | 0 | 0 | 0 | 0 | 842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79-BMS | BMS PROJECTS | POLICE FACILITIES | 300 | PO-0079 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | NA | LUMP SUM | 2019 | 121310 | 0 | 3215 | 11788 | 14508 | 13263 | 13000 | 92000 | 147774 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMUPS | ONE POLICE PLAZA UPS | POLICE FACILITIES | 300 | PO-0079 |  |  | RECONSTRUCTION | 2019 | 30950 | 0 | 0 | 30950 | 0 | 0 | 0 | 0 | 30950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79CAFE | RENOVATION AND UPGRADE OF ONE POLICE PLAZA CAFETERIA | POLICE FACILITIES | 300 | PO-0079 |  |  | ESTIMATE | 2019 | 1081 | 0 | 1081 | 0 | 0 | 0 | 0 | 0 | 1081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79-FMS | FMS PROJECTS | POLICE FACILITIES | 300 | PO-0079 |  |  | LUMP SUM | 2019 | 375 | 0 | 375 | 0 | 0 | 0 | 0 | 0 | 375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79HQBB | 1 POLICE PLAZA SECURITY BARRIERS & BOOTHS | POLICE FACILITIES | 300 | PO-0079 |  |  | 1POLICE PLAZA SECURITY BARRIERS AND BOOTHS | 2019 | 8940 | 0 | 8940 | 0 | 0 | 0 | 0 | 0 | 8940 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79P76R | PIER 76 ROOF RECONSTRUCTION | POLICE FACILITIES | 300 | PO-0079 |  |  | ROOF REHABILITATION | 2019 | 9633 | 0 | 0 | 7751 | 0 | 0 | 0 | 0 | 7751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79PA13 | RENOVATION OF OLD POLICE ACADEMY/13TH PCT | POLICE FACILITIES | 300 | PO-0079 |  |  | PA RENOVATION | 2019 | 20000 | 0 | 804 | 11000 | 5000 | 0 | 0 | 0 | 16804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79PAAUD | OLD POLICE ACADEMY AUDITORIUM RENOVATION | POLICE FACILITIES | 300 | PO-0079 |  | OLD POLICE ACADEMY AUDITORIUM RENOVATION | OLD POLICE ACADEMY AUDITORIUM RENOVATION | 2019 | 1430 | 156.84 | 3982 | 0 | 0 | 0 | 0 | 0 | 4138.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79PCEL | REHABILITATION OF PC ELEVATOR AT 1PP | POLICE FACILITIES | 300 | PO-0079 |  |  | ESTIMATE | 2019 | 730 | 0 | 0 | 730 | 0 | 0 | 0 | 0 | 730 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79SCIF | UPGRADE OF SCIF AC UNIT AT ONE POLICE PLAZA | POLICE FACILITIES | 300 | PO-0079 |  |  | ESTIMATE | 2019 | 250 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 056 | POLICE DEPARTMENT | SANDCD6 | HARBOR LAUNCH RANDALL'S ISLAND ELECTRICAL | POLICE FACILITIES | 300 | PO-0079 |  | RANDALL'S ISLND | ELECTRICAL REHABILITATION | 2019 | 713 | 0 | 72 | 0 | 0 | 0 | 0 | 0 | 72 | 0 | 641 | 0 | 0 | 0 | 0 | 0 | 641
20190425 | MANHATTAN | 056 | POLICE DEPARTMENT | SANDCD7 | POLICE SERVICE AREA 4 (PSA4) | POLICE FACILITIES | 300 | PO-0079 |  |  | ELECTRICAL REHABILITATION | 2019 | 2192 | 0 | 220 | 0 | 0 | 0 | 0 | 0 | 220 | 0 | 1972 | 0 | 0 | 0 | 0 | 0 | 1972
20190425 | MANHATTAN | 057 | FIRE DEPARTMENT | ACEFDN601 | FDNY - VARIOUS LOCATIONS | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 300 | PU-0025 |  |  | FDNY - VARIOUS LOCATIONS : LED LIGHTING RETROFIT | 2019 | 2287 | 2030.18 | -64 | 125 | 0 | 0 | 0 | 0 | 2091.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 057 | FIRE DEPARTMENT | ACEFDN803 | FDNY - Solar photo-voltaic system at SOC | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 301 | PU-0025 |  |  | SOLAR PHOTO-VOLTAIC SYSTEM AT SOC TACTICAL UNIT FACILITY, ROOSEVELT ISLAND MANHATTAN | 2019 | 142 | 0 | 28 | 114 | 0 | 0 | 0 | 0 | 142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 057 | FIRE DEPARTMENT | F175ASV95 | Apron Replacement - EC95 | NEW FACILITIES AND RENOVATIONS | 312 | F-0175 |  |  | APRON REPLACEMENT - EC95 | 2019 | 291 | 0 | 266 | 0 | 0 | 0 | 0 | 0 | 266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 057 | FIRE DEPARTMENT | F175EXREN | EXTERIOR RENOVATIONS - EC55 | NEW FACILITIES AND RENOVATIONS | 302 | F-0175 | PROJECT DELAYED PENDING APPROVAL OF NECESSARY PERMITS |  | EXTERIOR RENOVATIONS - EC55 | 2019 | 2750 | 2108.39 | 184 | 0 | 0 | 0 | 0 | 0 | 2292.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 057 | FIRE DEPARTMENT | F175KTE22 | KITCHENT RENOVATION - EC22 | NEW FACILITIES AND RENOVATIONS | 308 | F-0175 |  |  | KITCHENT RENOVATION - EC22 | 2019 | 1734 | 0 | 195 | 0 | 1500 | 0 | 0 | 0 | 1695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 057 | FIRE DEPARTMENT | F175MCE33 | Multi-Component Renovations - EC33 | NEW FACILITIES AND RENOVATIONS | 302 | F-0175 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | HVAC AND INTERIORS - EC33 | 2019 | 961 | 0 | 495 | 0 | 0 | 5200 | 0 | 0 | 5695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 057 | FIRE DEPARTMENT | F175MCE44 | MULTI COMPONENT RENOVATIONS - EC44 | NEW FACILITIES AND RENOVATIONS | 308 | F-0175 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | MULTI COMPONENT RENOVATIONS - EC44 | 2019 | 2687 | 6008.66 | 425 | 0 | 0 | 0 | 0 | 0 | 6433.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 057 | FIRE DEPARTMENT | F175MCE74 | Multi-Component Renovations - EC74 | NEW FACILITIES AND RENOVATIONS | 307 | F-0175 |  |  | FLOOR, KITCHEN & TOILETS L-OHD GENERATOR - EC74 | 2019 | 4452 | 0 | 418 | 0 | 3950 | 0 | 0 | 0 | 4368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 057 | FIRE DEPARTMENT | F175MCE91 | Multi-Component Renovations - EC91 | NEW FACILITIES AND RENOVATIONS | 311 | F-0175 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | MULTI-COMPONENT RENOVATIONS - EC91 | 2019 | 14116 | 0 | 930 | 0 | 0 | 13000 | 0 | 0 | 13930 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 057 | FIRE DEPARTMENT | F175MCL20 | FIREHOUSE RENOVATIONS - LC20 | NEW FACILITIES AND RENOVATIONS | 302 | F-0175 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | FIREHOUSE RENOVATIONS - LC20 | 2019 | 2200 | 44.81 | 911 | 0 | 0 | 8520 | 0 | 0 | 9475.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 057 | FIRE DEPARTMENT | F175RFE54 | ROOF AND WATERPROOFING - EC54 | NEW FACILITIES AND RENOVATIONS | 305 | F-0175 |  |  | ROOF AND WATERPROOFING - EC54 | 2019 | 3638 | 0 | 365 | 0 | 3200 | 0 | 0 | 0 | 3565 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 057 | FIRE DEPARTMENT | F2042RAND | RANDALL'S ISLAND BUILDING #2 | NEW FACILITIES AND RENOVATIONS | 300 | F-0204 | PROJECT DELAYED PENDING APPROVAL OF NECESSARY PERMITS |  | RANDALL'S ISLAND BUILDING #2 | 2019 | 1400 | 5917.36 | 441 | 0 | 0 | 0 | 0 | 0 | 6358.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 057 | FIRE DEPARTMENT | F204RIWTR | RANDALL'S ISLAND WATER RECOVERY SYSTEM | NEW FACILITIES AND RENOVATIONS | 300 | F-0204 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | RANDALL'S ISLAND WATER RECOVERY BUILDING | 2019 | 684 | 2672.62 | 0 | 0 | 232 | 0 | 0 | 0 | 2904.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 057 | FIRE DEPARTMENT | FD175DE22 | Door Replacement - EC22 | NEW FACILITIES AND RENOVATIONS | 308 | F-D175 |  |  | DOOR REPLACEMENT - EC22 | 2019 | 150 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 057 | FIRE DEPARTMENT | FD175DE28 | Door Replacement - EC28 | NEW FACILITIES AND RENOVATIONS | 303 | F-D175 |  |  | DOOR REPLACEMENT - EC28 | 2019 | 75 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 057 | FIRE DEPARTMENT | FD175DE95 | Door Replacement - EC95 | NEW FACILITIES AND RENOVATIONS | 312 | F-D175 |  |  | DOOR REPLACEMENT - EC95 | 2019 | 75 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 057 | FIRE DEPARTMENT | FD175DRE5 | Door Replacement - EC5 | NEW FACILITIES AND RENOVATIONS | 303 | F-D175 |  |  | DOOR REPLACEMENT - EC5 | 2019 | 75 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 057 | FIRE DEPARTMENT | FD175GE95 | Generator - EC95 | NEW FACILITIES AND RENOVATIONS | 312 | F-D175 F-0175 |  |  | GENERATOR - EC95 | 2019 | 575 | 0 | 559 | 0 | 0 | 0 | 0 | 0 | 559 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 057 | FIRE DEPARTMENT | FD175LR08 | Lactation Room - EMS8 | NEW FACILITIES AND RENOVATIONS | 306 | F-D175 |  |  | LACTATION ROOM - EMS8 | 2019 | 100 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 057 | FIRE DEPARTMENT | FD175LR10 | Lactation Room - EMS10 | NEW FACILITIES AND RENOVATIONS | 311 | F-D175 |  |  | LACTATION ROOM - EMS10 | 2019 | 100 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 057 | FIRE DEPARTMENT | FD175LR17 | Lactation Room - EMS17 | NEW FACILITIES AND RENOVATIONS | 304 | F-D175 |  |  | LACTATION ROOM - EMS17 | 2019 | 100 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 057 | FIRE DEPARTMENT | FD175WN22 | Windown Replacement - EC22 | NEW FACILITIES AND RENOVATIONS | 308 | F-D175 F-0175 |  |  | WINDOW REPLACEMENT - EC22 | 2019 | 587 | 0 | 570 | 0 | 0 | 0 | 0 | 0 | 570 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 057 | FIRE DEPARTMENT | FD175WN28 | Window Replacement - EC28 | NEW FACILITIES AND RENOVATIONS | 303 | F-D175 F-0175 |  |  | WINDOW REPLACEMENT - EC28 | 2019 | 511 | 0 | 494 | 0 | 0 | 0 | 0 | 0 | 494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 057 | FIRE DEPARTMENT | FD175WN74 | Window Replacement - EC74 | NEW FACILITIES AND RENOVATIONS | 307 | F-D175 |  |  | WINDOW REPLACEMENT - EC74 | 2019 | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 057 | FIRE DEPARTMENT | FM175WN76 | Window Replacement EC76 | NEW FACILITIES AND RENOVATIONS | 307 | F-M175 F-0175 |  |  | WINDOW REPLACEMENT EC 76 | 2019 | 250 | 49.43 | 333 | 0 | 0 | 0 | 0 | 0 | 382.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 068 | ADMIN FOR CHILDREN'S SERVICES | CAPC | CHINESE AMERICAN PLANNING COUNCIL | CHILD WELFARE FACILITIES | 300 303 | CS-D002 |  |  | CONST. | 2019 | 100 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 068 | ADMIN FOR CHILDREN'S SERVICES | JSA61BWYY | JSA RELOCATION TO 61 BROADWAY | CHILD WELFARE FACILITIES |  | CS-0003 |  |  | TBD | 2019 | 0 | 0 | 65 | 1135 | 0 | 0 | 0 | 0 | 1200 | 0 | 88 | 1632 | 0 | 0 | 0 | 0 | 1720
20190425 | MANHATTAN | 068 | ADMIN FOR CHILDREN'S SERVICES | NSCC | Children's Center High Needs Unit | CHILD WELFARE FACILITIES |  | CS-0003 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CHILDREN'S CENTER HIGH NEEDS UNIT | 2019 | 468 | 0 | 0 | 623 | 1450 | 2012 | 1612 | 0 | 5697 | 0 | 0 | 975 | 2269 | 3148 | 2521 | 0 | 8913
20190425 | MANHATTAN | 068 | ADMIN FOR CHILDREN'S SERVICES | SYSUPGRAD | SYSTEM UPGRADES AT HORIZON AND CROSSROADS JUVENILE CENTERS | CHILD WELFARE FACILITIES | 300 | CS-0005 |  |  | THE HORIZON JUVENILE CENTER AND THE CROSSROADS JUVENILE CENTER ARE THE TWO SECURE DETENTION FACILITIES SERVING NEW YORK CITY'S YOUTH. BUILDING SYSTEMS THAT WERE MODERNIZED AND ENHANCED DURING THE PAST SEVERAL YEARS WILL REQUIRE UPGRADING TO PROLONG THEIR LIFE CYCLES. THESE SYSTEMS INCLUDE, BUT ARE NOT LIMITED TO: LIGHTING, ROOFING, PLUMBING, MECH., ELECTRICAL, SECURITY, FIRE ALARM AND FIRE SUPPRESSION SYSTEMS; CLASSROOMS, COMMERCIAL KITCHEN AND KITCHEN EQUIPMENT; RECREATIONAL AREASAND RELATED LANDSCAPING. | 2019 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 24260 | 24260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | DHS-LIGHT | DEPT OF HOMELESS SVCS: INSTALL LIGHTING AT 30TH STR SHELTER | ROUTINE RECONSTRUCTION | 306 | HH-D025 |  | 400-430 EAST 30TH STREET, NEW YORK, NY | DEPARTMENT OF HOMELESS SERVICES: FUNDING WILL SUPPORT THE INSTALLATION OF LIGHTING AT THE 30TH STREET SHELTER. | 2019 | 0 | 0 | 13 | 37 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112BLEX | BELLEVUE MEN'S RESIDENCE- EXTERIOR RENOVATION | SHELTERS FOR HOMELESS INDIVIDUALS | 306 | HH-0112 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | BELLEVUE MEN'S RESIDENCE-EXTERIOR RENOVATION | 2019 | 2302 | 2142.61 | 129 | 0 | 0 | 0 | 0 | 0 | 2271.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112BLIT | BELLEVUE MEN'S RESIDENCE- INTERIOR RENOVATION | SHELTERS FOR HOMELESS INDIVIDUALS | 306 | HH-0112 |  |  | BELLEVUE MEN'S RESIDENCE-INTERIOR RENOVATION | 2019 | 1872 | 1659.55 | 200 | 0 | 0 | 0 | 0 | 0 | 1859.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112BLSB | BELLEVUE BASEMENT STRUCTURAL RECONSTRUCTION | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 |  |  | BELLEVUE BASEMENT STRUCTURAL RECONSTRUCTION | 2019 | 0 | 0 | 0 | 1000 | 4813 | 0 | 8000 | 24937 | 38750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112BLWB | BELLEVUE WEST BANK ELEVATORS | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 |  |  | BELLEVUE WEST BANK ELEVATORS | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 1132 | 6414 | 7546 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112ELPL | BELLEVUE MEN'S RESIDENCE-REDIVERSION CENTER PLUMBING | SHELTERS FOR HOMELESS INDIVIDUALS | 306 | HH-0112 |  |  | BELLEVUE MEN'S RESIDENCE-WATER TANK REPLACEMENT | 2019 | 2269 | 2205.3 | 330 | 0 | 0 | 0 | 0 | 0 | 2535.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112ETEU | 282 East 3rd Street, 10009 - Exterior Upgrade | SHELTERS FOR HOMELESS INDIVIDUALS | 303 | HH-0112 |  |  | 8 EAST 3RD STREET, 10009 - EXTERIOR UPGRADE | 2019 | 2600 | 175.5 | 0 | 0 | 24 | 0 | 2400 | 0 | 2599.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112FWBO | FT. WASHINGTON ARMORY - BOILER UPGRADE | SHELTERS FOR HOMELESS INDIVIDUALS | 312 | HH-0112 |  |  | FT. WASHINGTON ARMORY - BOILER UPGRADE | 2019 | 3586 | 359 | 2988 | 7143 | 0 | 0 | 0 | 0 | 10490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112FWFR | FORT WASHINGTON ARMORY-DORMITORIES FLOOR REPLACEMENT | SHELTERS FOR HOMELESS INDIVIDUALS | 312 | HH-0112 |  |  | FORT WASHINGTON ARMORY - DORMITORIES FLOOR REPLACEMENT | 2019 | 450 | 27 | 273 | 250 | 0 | 2150 | 0 | 0 | 2700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112GDFC | GEORGE DALY FACADE AND WINDOWS | SHELTERS FOR HOMELESS INDIVIDUALS | 303 | HH-0112 |  |  | GEORGE DALY FACADE AND WINDOWS | 2019 | 0 | 185 | 0 | 0 | 0 | 0 | 0 | 2405 | 2590 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112GDRR | GEORGE DALY RESIDENCE - ROOF REPLACEMENT | SHELTERS FOR HOMELESS INDIVIDUALS | 303 | HH-0112 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | GEORGE DALY RESIDENCE-ROOF REPLACEMENT | 2019 | 487 | 592.71 | 260 | 400 | 80 | 0 | 0 | 0 | 1332.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112HBAT | HARLEM 1 BATHROOM RECONSTRUCTION | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 |  |  | RECONSTRUCT BATHROOMS | 2019 | 2080 | 0 | 0 | 160 | 760 | 1000 | 0 | 0 | 1920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112HHAC | HARLEM 1 ROOF AND VENTILATION SYSTEM | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 |  |  | RECONSTRUCT ROOF AND VENTILATION SYSTEMS | 2019 | 3360 | 0 | 0 | 280 | 0 | 3080 | 0 | 0 | 3360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112HINT | HARLEM 1 iNTERIOR RECONSTRUCTION | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 |  |  | RECONSTRUCT INTERIOR | 2019 | 3000 | 0 | 0 | 250 | 0 | 2750 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112HLET | HARLEM 1 ELECTRICAL UPGRADE | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 |  |  | ELECTRICAL UPGRADE | 2019 | 12000 | 0 | 0 | 1000 | 4000 | 7000 | 0 | 0 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112HMBL | HARLEM 1 BOILER REPLACEMENT | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 |  |  | HARLEM 1 BOILER REPLACEMENT | 2019 | 1475 | 125 | 0 | 1350 | 0 | 0 | 0 | 0 | 1475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112HMED | HARLEM 1 - ELECTRICAL PANEL UPGRADE | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 |  |  | HARLEM 1 - ELECTRICAL PANEL UPGRADE | 2019 | 500 | 40 | 0 | 460 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112HSCR | HELP SEC-COTTAGE ROOF REPLACEMENT | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 |  |  | HELP SEC- COTTAGE ROOF REPLACEMENT | 2019 | 2210 | 0 | 170 | 0 | 2040 | 0 | 0 | 0 | 2210 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112HSMR | HELP SEC.-MIAN BLDG.ROOF REPLACEMENT | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 |  |  | HELP SEC.-MIAN BLDG. ROOF REPLACEMENT | 2019 | 2340 | 0 | 180 | 0 | 2160 | 0 | 0 | 0 | 2340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112HSSF | HELP SEC FENCE REPLACEMENT | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 |  |  | HELP SEC FENCE REPLACEMENT | 2019 | 0 | 0 | 1588 | 0 | 0 | 0 | 0 | 0 | 1588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112KITC | PROJECT RENEWAL-EAST 3RD STREET KITCHEN NC#13-260288T82144 | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-D025 HH-0112 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | PROJECT RENEWAL-EAST 3RD STREET SHELTER-KITCHEN RENOVATION | 2019 | 1540 | 61.64 | 25 | 202 | 0 | 0 | 0 | 0 | 288.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112KNUG | KEENER ASSESSMENT SHELTER - BUILDING UPGRADE | SHELTERS FOR HOMELESS INDIVIDUALS | 311 | HH-0112 |  |  | KEENER ASSESSMENT SHELTER - BUILDING UPGRADE | 2019 | 10782 | 0 | 0 | 0 | 0 | 0 | 829 | 9953 | 10782 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112KTEX | KENTON HALL - FACADE RECONSTRUCTION | SHELTERS FOR HOMELESS INDIVIDUALS | 303 | HH-0112 |  |  | KENTON HALL - FACADE RECONSTRUCTION | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 456 | 456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112SEWR | VETERANS SRO - SEWER PIPE REPLACEMENT | SHELTERS FOR HOMELESS INDIVIDUALS | 311 | HH-0112 |  |  | VETERANS SRO - SEWER PIPE REPLACEMENT | 2019 | 1084 | 2616.83 | 1639 | 0 | 0 | 0 | 0 | 0 | 4255.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112SWBU | Schwartz Homeless Shelter | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 |  |  | SCHWARTZ HOMELESS SHELTER - BUILDING UPGRADE | 2019 | 1000 | 0 | 0 | 0 | 0 | 150 | 0 | 850 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112SWTR | SCHWARTZ WARDS ISLAND TRANSFORMER REPLACEMENT | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 |  |  | SCHWARTZ WARDS ISLAND TRANSFORMER REPLACEMENT | 2019 | 0 | 0 | 217 | 0 | 0 | 0 | 0 | 0 | 217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112THBH | 8 EAST THIRD ST BATHROOM RECONSTRUCTION | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 |  |  | BATHROOM RECON | 2019 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 3300 | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112THBR | 282 EAST THIRD ST BOILER RECONSTRUCTION | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 |  |  | BOILER RECONSTRUCTION | 2019 | 0 | 0 | 0 | 100 | 0 | 1100 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112THFC | 8 EAST THIRD ST SHELTER FACADE AND STAIRS | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 |  |  | RECONSTRUCT FACADE AND STAIRS | 2019 | 0 | 0 | 80 | 0 | 400 | 560 | 0 | 0 | 1040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH115CTBU | 78 CATHERINE STREET - BATHROOM UPGRADE | SHELTERS FOR HOMELESS FAMILIES | 303 | HH-0115 |  |  | DESIGN AND CONSTRUCTION SERVICES RE THE RENOVATION OF BATHROOMS AT THE CATHERINE STREET FAMILY SHELTER | 2019 | 7350 | 4870 | 826 | 0 | 0 | 0 | 0 | 0 | 5696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH115CTEF | CATHERINE STREET ELECTRICAL AND FIRE SAFETY UPGRADE | SHELTERS FOR HOMELESS FAMILIES |  | HH-0115 |  |  | CATHERINE STREET ELECTRICAL AND FIRE SAFETY UPGRADE | 2019 | 3950 | 300 | 50 | 0 | 1000 | 2600 | 0 | 0 | 3950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH115JCFA | JENNIE CLARKE BACKFLOW PREVENTER | SHELTERS FOR HOMELESS FAMILIES | 311 | HH-0115 |  |  | 179 - 191 EAST 100TH STREET - FA, PA SYS, BACKFLOW PREVENTION | 2019 | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 0 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH115JCRR | JENNIE CLARKE FAMILY RESIDENCE- ROOF REPLACEMENT | SHELTERS FOR HOMELESS FAMILIES | 311 | HH-0115 |  |  | JENNIE CLARKE FAMILY RESIDENCE- ROOF REPLACEMENT | 2019 | 1606 | 668.72 | 937 | 0 | 0 | 0 | 0 | 0 | 1605.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH115REBO | REGENT BOILER | SHELTERS FOR HOMELESS FAMILIES | 307 | HH-0115 |  |  | REGENT BOILER | 2019 | 1950 | 150 | 0 | 900 | 900 | 0 | 0 | 0 | 1950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH115RECL | REGENT CEILINGS | SHELTERS FOR HOMELESS FAMILIES | 307 | HH-0115 |  |  | REGENT CEILINGS | 2019 | 4707 | 85 | 0 | 0 | 1758 | 0 | 0 | 0 | 1843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH115RFRE | REGENT FAMILY RESIDENCE LIFE SAFETY UPGRADE, FIRE SAFETY | SHELTERS FOR HOMELESS FAMILIES | 307 | HH-0115 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | ELECTRICAL UPGRADE THROUGHOUT THE BUILDING AND TO ADDRESS ANY CODE VIOLATIONS AT THE REGENT FAMILY RESIDENCE. | 2019 | 2174 | 2650.75 | 500 | 334 | 0 | 0 | 0 | 0 | 3484.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH115RGST | REGENT - STAIR B | SHELTERS FOR HOMELESS FAMILIES | 307 | HH-0115 |  |  | REGENT - STAIR B | 2019 | 1000 | 836.9 | 413 | 0 | 0 | 0 | 0 | 0 | 1249.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HHCN007 | INSTALLATION OF BACKUP GENERATOR | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-D025 |  |  | INSTALLATION OF A BACKUP GENERATOR | 2019 | 301 | 0 | 60 | 241 | 0 | 0 | 0 | 0 | 301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HHMNEW1 | PROJECT RENEWAL - RENOVATE FT. WASH. ARMORY | SHELTERS FOR HOMELESS INDIVIDUALS | 312 | HH-M112 |  |  | PROJECT RENEWAL - RENOVATE FT. WASH. ARMORY | 2019 | 101 | 0 | 25 | 76 | 0 | 0 | 0 | 0 | 101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HHNC005 | KITCHEN RENOVATION AT 8 EAST THIRD STREET HOMELESS SHELTER | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-D025 |  |  | KITCHEN RENOVATION AT 8 EAST THIRD STREET HOMELES SHELTER | 2019 | 378 | 0 | 378 | 0 | 0 | 0 | 0 | 0 | 378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HHNC006 | FORT WASHINGTON ARMORY - ENTRYWAY REPAIR | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-D025 |  |  | FORT WASHINGTON ARMORY - ENTRYWAY REPAIR | 2019 | 200 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HLCN014 | PROJECT RENEWAL , INC. - NEW PROVIDENCE BACKUP GENERATOR | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-D112 |  |  | PROJECT RENEWAL , INC. - NEW PROVIDENCE BACKUP GENERATOR | 2019 | 275 | 0 | 55 | 220 | 0 | 0 | 0 | 0 | 275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 072 | DEPARTMENT OF CORRECTION | C75WTRMN | Replace Water Mains on Rikers Island | BUILDING SYSTEMS AND INFRASTRUCTURE | 300 | C-0075 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | REPLACE DOMESTIC WATER AND FIRE MAINS AT RIKERS ISLAND. | 2019 | 6175 | 0 | 410 | 1 | 4814 | 0 | 0 | 0 | 5225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 096 | HUMAN RESOURCES ADMINISTRATION | HR2560LAC | 60 Lafayette Street Construction | SOCIAL SERVICES BUILDINGS |  | HR-0025 |  |  |  | 2019 | 0 | 0 | 0 | 255 | 0 | 0 | 0 | 0 | 255 | 0 | 0 | 495 | 0 | 0 | 0 | 0 | 495
20190425 | MANHATTAN | 096 | HUMAN RESOURCES ADMINISTRATION | HR25CHRYC | 115 Chrystie Street Construction | SOCIAL SERVICES BUILDINGS |  | HR-0025 |  |  |  | 2019 | 0 | 0 | 0 | 578 | 0 | 0 | 0 | 0 | 578 | 0 | 0 | 1122 | 0 | 0 | 0 | 0 | 1122
20190425 | MANHATTAN | 096 | HUMAN RESOURCES ADMINISTRATION | HR25E162C | 109 East 16th Street Construction | SOCIAL SERVICES BUILDINGS |  | HR-0025 |  |  |  | 2019 | 0 | 0 | 0 | 1045 | 2461 | 0 | 0 | 0 | 3506 | 0 | 0 | 518 | 1220 | 0 | 0 | 0 | 1738
20190425 | MANHATTAN | 096 | HUMAN RESOURCES ADMINISTRATION | HR25W125C | 132 W 125th St Construction | SOCIAL SERVICES BUILDINGS |  | HR-0025 |  |  |  | 2019 | 0 | 0 | 0 | 3139 | 0 | 0 | 0 | 0 | 3139 | 0 | 0 | 1622 | 0 | 0 | 0 | 0 | 1622
20190425 | MANHATTAN | 125 | DEPARTMENT FOR THE AGING | AGCBCOV | CARTER BURDEN/LEONARD COVELLO | DEPARTMENT FOR THE AGING BUILDING RECONSTRUCTION | 311 | AG-M001 |  |  | CARTER BURDEN/LEONARD COVELLO SENIOR PROGRAM KITCHEN RELOCATION | 2019 | 0 | 0 | 0 | 0 | 0 | 98 | 0 | 0 | 98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 125 | DEPARTMENT FOR THE AGING | AGCBURDEN | LEONARD COVELLO Kitchen Renovation | DEPARTMENT FOR THE AGING BUILDING RECONSTRUCTION | 311 | AG-D001 |  |  | SEPT 17 PLAN 400K FOR KITCHEN RENOVATION | 2019 | 0 | 0 | 0 | 0 | 0 | 400 | 0 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 125 | DEPARTMENT FOR THE AGING | HAM14CRSR | CARVER HOUSES SENIOR CENTER COMPUTER LAB | DEPARTMENT FOR THE AGING BUILDING RECONSTRUCTION | 311 | AG-D001 |  |  | INSTALL A COMPUTER LAB AT THE SENIOR CENTER | 2019 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | ACEDCA434 | DCLA: AMNH - Lighting Control Upgrade, Rd 4 & Garage Rd 5 | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 307 | PU-0025 |  |  | REMOVAL AND REPLACEMENT OF LIGHTING CONTROLS SYSTEMS IN PUBLIC SPACESFOR 10 EXHIBIT HALLS. THESE UPGRADES WILL PROVIDE CONTROLS NECESSARY TO AUTOMATICALLY TURN OFF LIGHTING FOR EIGHT HOUR PERIODS EACH DAY. | 2019 | 583 | 0 | 0 | 710 | 0 | 0 | 0 | 0 | 710 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV022-SKY | MMA - Metropolitan Museum Skylight Replacement for A, B, C W | ESSENTIAL RECONSTRUCTION OF FACILITIES | 308 | PV-0467 PV-M022 PV-0022 PV-D022 |  |  | METROPOLITAN MUSEUM OF ART: SKYLIGHT REPLACEMENT OF WINGS A, B & C. | 2019 | 19738 | 0 | 0 | 2000 | 0 | 19738 | 0 | 0 | 21738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV034-INF | AMNH - Security & Infrastructure Upgrade | ESSENTIAL RECONSTRUCTION OF FACILITIES | 307 | PV-M034 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | CENTRAL PARK WEST AT 79TH STREET, NEW YORK, NY | SECURITY AND INFRASTRUCTURE UPGRADE | 2019 | 1803 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV034NWCH | AMNH - Northwest Coast Hall Renovation | ESSENTIAL RECONSTRUCTION OF FACILITIES | 307 | PV-0034 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RENOVATION | 2019 | 3060 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV101HVAC | MJH - Museum HVAC | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | PV-M101 |  |  | MJH - MUSEUM HVAC | 2019 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV101-MJH | Museum of Jewish Heritage: Theater Renovation | ESSENTIAL RECONSTRUCTION OF FACILITIES | 301 | PV-M101 PV-D101 PV-0101 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | MUSEUM OF JEWISH HERITAGE: THEATER RENOVATION | 2019 | 1009 | 0 | 0 | 0 | 485 | 0 | 2483 | 0 | 2968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV101SECU | MJH - Building Security | ESSENTIAL RECONSTRUCTION OF FACILITIES | 301 | PV-D101 |  |  | MJH - BUILDING SECURITY | 2019 | 1414 | 0 | 0 | 0 | 0 | 1414 | 0 | 0 | 1414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV241BOIL | MCNY - Boiler Replacement | ESSENTIAL RECONSTRUCTION OF FACILITIES | 311 | PU-0025 PV-D241 PV-0241 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | 1220 5TH AVE, MANHATTAN NY | BOILER SYSTEM REPLACEMENT. | 2019 | 1512 | 0 | 0 | 331 | 0 | 1430 | 0 | 0 | 1761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV279ACON | NYCC - NY City Center Chiller Replacement | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | PV-M279 |  |  | NYCC - NY CITY CENTER CHILLER REPLACEMENT | 2019 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV279-ROO | NYCC - New York City Center Roof and Facade Renovation | ESSENTIAL RECONSTRUCTION OF FACILITIES | 305 | PV-M279 PV-D279 PV-0279 |  |  | RENOVATION OF NEW YORK CITY CENTER FACADE AND ROOF AREAS - DETAILED SCOPE TO BE DETERMINED BASED ON BUDGET AND ELIGIBILITY. | 2019 | 761 | 0 | 0 | 73 | 0 | 604 | 0 | 0 | 677 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV289-DEL | NYSF - DELCORTE Theater Renovation | ESSENTIAL RECONSTRUCTION OF FACILITIES | 307 | PV-M289 PV-0289 PV-D289 |  |  | NYSF - DELCORTE THEATER RENOVATION | 2019 | 9900 | 0 | 0 | 100 | 9800 | 0 | 0 | 0 | 9900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV289NWDA | NYSF - 440 Lafayette Systems | CAPITAL EQUIPMENT | 302 | PV-M289 PV-0289 PV-D289 |  |  |  | 2019 | 1111 | 0 | 0 | 0 | 0 | 1111 | 0 | 0 | 1111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467AREA | DCA AREA - Affordable Real Estate for Artists Initiative | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | PV-0467 |  |  | AREA - AFFORDABLE REAL ESTATE FOR ARTISTS INITITATIVE - IS A MAYORAL PROGRAM TO INCREASE THE AMOUNT OF AFFORDABLE ARTIST STUDIO, REHEARSAL,AND WORKSPACE IN THE CITY. | 2019 | 20700 | 0 | 0 | 0 | 0 | 0 | 0 | 700 | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467-BEY | DCA PFA - Percent for Art Beyond Sims | ESSENTIAL RECONSTRUCTION OF FACILITIES | 301 302 | PV-0467 |  |  | MONUMENT | 2019 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467HOLD | FUND BALANCE 467 EX | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | PV-0467 |  |  | EXCESS FUNDS FROM VARIOUS PROJECTS | 2019 | 1919 | 0 | 0 | 0 | 0 | 0 | 0 | 907 | 907 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467-MON | DCA - Monuments Fund | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | PV-0467 |  |  | FUND FOR CREATION OF NEW MONUMENTS IN ALL BOROUGHS. | 2019 | 48 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467-PCT | DCA PFA - Percent for Art Tito P. | ESSENTIAL RECONSTRUCTION OF FACILITIES | 301 302 | PV-D467 PV-0467 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 31 CHAMBERS STREET, NYC | CONSERVATION OF 3 PUBLIC ART WORKS TO BE IDENTIFIED | 2019 | 992 | 0 | 0 | 0 | 0 | 0 | 250 | 250 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467PCTS | DCA PFA - Percent for Art Conservation of Public Art | ESSENTIAL RECONSTRUCTION OF FACILITIES | 301 302 | PV-0467 |  |  | CONSERVATION | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1992 | 1992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467SPAC | Spaceworks Master Fund | ESSENTIAL RECONSTRUCTION OF FACILITIES | 301 | PV-0467 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CONSTRUCTION OF ARTIST STUDIOS | 2019 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 1703 | 1703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV475ROOF | NYST - NYC Ballet Roof Replacement | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | PV-0475 PV-M475 PV-D475 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | DAVID H. KOCH THEATER ROOF REPLACEMENT | 2019 | 4178 | 0 | 0 | 0 | 0 | 0 | 3714 | 0 | 3714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV489FTA | LCPA - FTA | ESSENTIAL RECONSTRUCTION OF FACILITIES | 307 | PV-0544 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | RENOVATION OF FACITLITY AT1680 LEXINGTON AVENUE | 2019 | 119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119 | 0 | 0 | 0 | 0 | 0 | 119
20190425 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV489-MP2 | LCPA - Master Plan | ESSENTIAL RECONSTRUCTION OF FACILITIES | 307 | PV-0544 PV-0489 PV-M489 PV-D489 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | WEST 65TH STREET BETWEEN COLUMBUS AVENUE AND AMSTERDAM AVENUE | LINCOLN CENTER MASTER PLAN | 2019 | 8509 | 0 | 0 | 0 | 0 | 8398 | 0 | 0 | 8398 | 0 | 5755 | 0 | 0 | 0 | 0 | 0 | 5755
20190425 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV503ELEV | CH- Carnegie Hall Elevators and Sidewalk | ESSENTIAL RECONSTRUCTION OF FACILITIES | 305 | PV-M503 PV-D503 PV-0503 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CH- CARNEGIE HALL ELEVATORS AND SIDEWALK. FY19 EXEC SECTION 211 ADD | 2019 | 2760 | 0 | 0 | 0 | 0 | 1260 | 0 | 1500 | 2760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV503-IT1 | CH - CARNEGIE HALL IMPROVEMENTS | CAPITAL EQUIPMENT | 305 | PV-D503 |  |  |  | 2019 | 356 | 0 | 0 | 0 | 0 | 356 | 0 | 0 | 356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV503SDWK | CH - Carnegie Sidewalk Restoration | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | PV-M503 |  |  | CH - CARNEGIE SIDEWALK RESTORATION | 2019 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV788-TER | 122C - 122 Community Center Roof Terrace | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | PV-M788 PV-D788 PV-0788 |  |  | 122 COMMUNITY CENTER ROOF TERRACE CONSTRUCTION | 2019 | 168 | 0 | 0 | 0 | 0 | 168 | 0 | 0 | 168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 125THPDIM | 125th St & Park Ave - Pedestrian Improvements | MISCELLANEOUS | 300 | ED-D075 ED-0075 HW-0001M | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | 125TH & PARK AVE - EDC PUBLIC REALM PROJECT -- PEDESTRIAN IMPROVEMENTS ON 125TH STREET AND PARK AVENUE, AS PART OF EDC'S LARGER PUBLIC REALM PROJECT | 2019 | 1000 | 229.53 | 1120 | 0 | 0 | 0 | 0 | 0 | 1349.53 | 918.12 | 3282 | 0 | 0 | 0 | 0 | 0 | 4200.12
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 1680LEXSP | 1680 Lexington Sound Proofing | MISCELLANEOUS | 300 | ED-D075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | 1680 LEXINGTON SOUND PROOFING | 2019 | 450 | 381.2 | 0 | 0 | 0 | 69 | 0 | 0 | 450.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 34STHELI | E. 34th Street Heliport Rehabilitation | MISCELLANEOUS | 301 306 308 | ED-0409 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | REHABILITATION OF SUB-STRUCTURE | 2019 | 1900 | 5417.9 | 0 | 250 | 0 | 293 | 0 | 0 | 5960.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 8890PHA3 | Piers 88 & 90 Cluster Encapsulation Project Phase 3 | MISCELLANEOUS | 300 | ED-0409 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | PIERS 88 & 90 CLUSTER ENCAPSULATION PROJECT PHASE 3 | 2019 | 10000 | 7265.49 | 2734 | 0 | 0 | 0 | 0 | 0 | 9999.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 8THSTPAVE | 8th St Bluestone Pavement Replacement | NEIGHBORHOOD REVITALIZATION | 300 302 | ED-D384 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | 8TH ST. BLUESTONE PAVEMENT REPLACEMENT | 2019 | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 8THSTREET | FA - Village Alliance - Reconstruction of St. & Sidewalks | COMMERCIAL DEVELOPMENT | 302 | ED-0075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | MANHATTAN | VILLAGE ALLIANCE - RECONSTRUCTION OF STREET AND SIDEWALKS | 2019 | 1001 | 199.88 | 0 | 0 | 0 | 0 | 0 | 0 | 199.88 | 156.76 | 0 | 0 | 0 | 0 | 429 | 0 | 585.76
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | AHGREEN | Andrew Haswell Green Park - Phase 2B | MISCELLANEOUS | 300 | P-1018 P-0245M |  |  | ANDREW HASWELL GREEN PARK - PHASE 2B | 2019 | 25603 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3518.55 | 22084 | 0 | 0 | 0 | 0 | 0 | 25602.55
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | AIDSMEM | AIDS Memorial | MISCELLANEOUS | 300 302 | ED-M075 ED-D075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | AIDS MEMORIAL: CONSTRUCT A FREE STANDING MEMORIAL TO THE AIDS CRISIS ADJACENT TO ST. VINCENT HOSPITAL | 2019 | 3100 | 0 | 3600 | 0 | 0 | 0 | 0 | 0 | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | C5232 | 34th Street Ferry Landing | RECONSTRUCTION OF FERRY TERMINAL FACILITIES | 301 306 308 | FA-0027 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  |  | 2019 | 22719 | 912.74 | 0 | 0 | 0 | 0 | 0 | 0 | 912.74 | 17574.88 | 0 | 0 | 0 | 0 | 0 | 1532 | 19106.88
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | CMPRENO | Chinatown Manpower Project - 4th Floor Renovation | MISCELLANEOUS CONSTRUCTION | 300 303 | ED-D075 PW-M077 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CHINATOWN MANPOWER PROJECT - 4TH FLOOR RENOVATION | 2019 | 546 | 0 | 0 | 0 | 0 | 0 | 546 | 0 | 546 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | CWFSFERY2 | New York City Ferry - Infrastructure | WATERFRONT DEVELOPMENT | 300 | ED-0409 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CITYWIDE FERRY SERVICE - NEW VESSEL PURCHASE & UPGRADE | 2019 | 84400 | 0 | 152760 | 88500 | 127740 | 0 | 0 | 0 | 369000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | DMECODOCK | Dyckman Pier -- Ferry Access to Eco-Dock | MISCELLANEOUS | 300 | ED-D075 |  |  | DYCKMAN PIER -- FERRY ACCESS TO ECO-DOCK | 2019 | 500 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | E34THPIER | EAST 34TH STREET PIER- NYU PARKING LOT REHAB | REHABILITATION OF NON-WATERFRONT PROPERTIES | 301 | RE-0025 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | EAST 34TH STREET PIER- NYU PARKING LOT | 2019 | 920 | 792.99 | 0 | 0 | 0 | 44 | 0 | 0 | 836.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | EASTPLAZA | East River Plaza | COMMERCIAL DEVELOPMENT | 300 311 | ED-D075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | UPPER EAST SIDE MANHATTAN | 480 SQ FT RETAIL CENTER, 1,248 CAR PARKING GARAGE, FOUR STORY BUILDING TO BENEFIT A NON-PROFIT ORGANIZATION | 2019 | 2000 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | EDCLUMP | EDC Lump Sum | MISCELLANEOUS | 300 | ED-0075 |  |  | EDC LUMP SUM | 2019 | 0 | 0 | 0 | 0 | 0 | 1960 | 4075 | 3690 | 9725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | EDMFPM | FERRY PIER AT DYCKMAN MARINA | MISCELLANEOUS | 300 | P-0501 PU-0200 ED-D401 P-0245M | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | FERRY PIER AT DYCKMAN MARINA | 2019 | 5000 | 0 | 1491 | 11933 | 8491 | 0 | 0 | 0 | 21915 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | ERIVERSPS | East River Science Park - Street work | COMMERCIAL DEVELOPMENT | 300 306 | ED-0075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | EAST RIVER SCIENCE PARK - STREET WORK | 2019 | 9210 | 6713.34 | 0 | 236 | 0 | 0 | 0 | 0 | 6949.34 | 1998.54 | 0 | 0 | 0 | 0 | 0 | 0 | 1998.54
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | ERVRWALL | East River Seawall Rehabilitation (BMB to Pier 16) | MISCELLANEOUS | 300 | ED-0409 |  |  | ERVRWALL | 2019 | 3000 | 2689.41 | 310 | 0 | 0 | 0 | 0 | 0 | 2999.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISBL20 | Governors Island - Building 20 Nolan Park Renovation | MISCELLANEOUS |  | ED-0831 |  |  | BUILDING 20 NOLAN PARK RENOVATION | 2019 | 2727 | 0 | 677 | 2050 | 0 | 0 | 0 | 0 | 2727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISBLD2 | Governors Island Building Stabilization | MISCELLANEOUS | 300 301 | ED-0831 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BUILDING STABILIZATION | 2019 | 4951 | 1638.77 | 299 | 3000 | 3000 | 2000 | 0 | 0 | 9937.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISBLDG | Governors Island Building Stabilization | MISCELLANEOUS | 300 | ED-0831 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | GOVERNORS ISLAND BUILDING STABILIZATION | 2019 | 9435 | 4935.87 | 891 | 0 | 0 | 0 | 0 | 0 | 5826.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISBMB2 | Governors Island BMB Slip5/6 Pile Cluster&Slip 6/7FenderRack | MISCELLANEOUS | 300 301 | ED-0075 |  |  | BMB SLIP 5/6 PILE CLUSTER AND SLIP 6/7 FENDER RACK | 2019 | 6031 | 0 | 3301 | 0 | 895 | 0 | 0 | 0 | 4196 | 0 | 1835 | 0 | 0 | 0 | 0 | 0 | 1835
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISBTRL | Governors Island Trailer Bathroom | MISCELLANEOUS | 301 | ED-D831 |  |  |  | 2019 | 435 | 249.6 | 185 | 0 | 0 | 0 | 0 | 0 | 434.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISCRS3 | Governors Island Ferry Dry Dock & Rehab (Coursen) | MISCELLANEOUS | 300 | ED-0831 |  |  | GOVERNORS ISLAND FERRY DRY DOCK & REHAB - COAST GUARD MANDATED INPSECTION AND REHABILITATION OF FERRY VESSEL SERVING GOVERNORS ISLAND. REHABILITATION/RECONSTRUCTION/REPLACEMENT OF CRTITCAL SYSTEMS, INCLUDING ELECTRICAL, MECHANICAL, LIFE SAFETY, AND EXTERIOR PROTECTION. | 2019 | 2895 | 2583.28 | 312 | 0 | 0 | 0 | 0 | 0 | 2895.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISDEMO | Governors Island Building Demolition | MISCELLANEOUS | 300 | ED-0075 |  |  | GOVERNORS ISLAND BUILDING DEMOLITION. | 2019 | 0 | 877.67 | 1000 | 0 | 0 | 0 | 0 | 0 | 1877.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISELE2 | Governors Island Electric Projects | MISCELLANEOUS |  | ED-0831 |  |  | GOVERNORS ISLAND - DESIGN PORTION OF THE FOLLOWING PROJECTS :NORTH ISLAND ELECTRIC - SECONDARY SYSTEM UPGRADES (GOVISNIEL),; ISLAND WIDE BACK-UP POWER (GOVISGNTR); NORTH ISLAND LIGHTING (GOVISNILI), ISLAND PERIMETER LIGHTING (GOVISPRLI). $1,014,084 TRANSFER FROM THESE PJIDS DURING FY19 PRELIMINARY PLAN. | 2019 | 17000 | 874.21 | 500 | 15626 | 0 | 0 | 0 | 0 | 17000.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISELEC | Governors Island Electrical Infrastructure | MISCELLANEOUS | 300 301 | ED-0075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | GOVERNORS ISLAND ELECTRICAL INFRASTRUCTURE. | 2019 | 27222 | 24669.09 | 444 | 0 | 0 | 0 | 0 | 0 | 25113.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISLND2 | Governors Island Infrastructure Improvements | MISCELLANEOUS | 301 | ED-0831 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RECONSTRUCTION/UPGRADE OF INFRASTRUCTURE ON GOVERNORS ISLAND. | 2019 | 31390 | 0 | 687 | 1000 | 4000 | 7000 | 4000 | 25357 | 42044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISNPCR | Governors Island - Nolan Park & Colonels Row Rehabilitation | MISCELLANEOUS | 300 | ED-0831 |  |  | LEAD PAINT ABATEMENT AT THE INTERIORS OF 18 LANDMARKED BUILDINGS IN NOLAN PARK AND COLONELS ROW. | 2019 | 1500 | 0 | 500 | 1000 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISOPCT | Governors Island Operations Center | MISCELLANEOUS |  | ED-0831 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | GOVERNORS ISLAND - CONSTRUCTION OF AN OPERATIONS CENTER ON THE SOUTH ISLAND TO HOUSE OPERATIONS AND MAINTENANCE STAFF, EQUIPMENT AND SUPPLIES. | 2019 | 3000 | 686.19 | 2313 | 0 | 0 | 0 | 0 | 0 | 2999.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISPUMP | Governors Island Sewage Pump House | MISCELLANEOUS |  | ED-0831 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | GOVERNOR ISLAND SEWAGE PUMP HOUSE | 2019 | 1500 | 387.13 | 1225 | 0 | 0 | 0 | 0 | 0 | 1612.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISSPWK | Governors Island Bldg. 301- Spaceworks | ESSENTIAL RECONSTRUCTION OF FACILITIES | 300 301 | PV-D467 PV-0467 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | GOVERNORS ISLAND - REHABILITATION OF BUILDING 301 FOR USE AS ARTIST STUDIO SPACE, IN COLLABORATION WITH SPACEWORKS AND DCA. | 2019 | 4500 | 2913.3 | 9386 | 0 | 0 | 0 | 0 | 0 | 12299.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISSSN2 | Governors Island Soissons Dock 2 | MISCELLANEOUS | 300 | ED-0831 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RECONSTRUCTION OF SOISSONS DOCK ON GOVERNORS ISLAND | 2019 | 4896 | 170.89 | 7156 | 0 | 0 | 0 | 0 | 0 | 7326.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISUNUT | Governors Island Underground Utilities | MISCELLANEOUS |  | ED-0831 |  |  | GOVERNORS ISLAND UNDERGROUND UTILITIES - NORTH ISLAND, HISTORIC DISTRICT, INSTALLATION. | 2019 | 10000 | 652.05 | 500 | 8848 | 0 | 0 | 0 | 0 | 10000.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISWLL2 | Governors Island Seawall Rehabilitation | MISCELLANEOUS | 300 | ED-0831 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | REHABILITATION OF THE SEAWALL AT GOVERNORS ISLAND | 2019 | 7452 | 0 | 0 | 0 | 0 | 3576 | 3375 | 0 | 6951 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISWTR2 | Governors Island Potable Water System | MISCELLANEOUS | 300 | ED-0831 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | REHABILITATION OF THE POTABLE WATER SYSTEM ON GOVERNORS ISLAND | 2019 | 2000 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HARLEMRY | Harlem River Yards | MISCELLANEOUS | 300 | ED-X075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | HARLEM RIVER YARDS | 2019 | 1000 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HARLESPL | Harlem River Esplanade | WATERFRONT DEVELOPMENT | 310 | P-C018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BULKHEAD IMPROVEMENTS | 2019 | 4500 | 7255.62 | 245 | 0 | 0 | 0 | 0 | 0 | 7500.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HARLMPIER | Harlem Area Piers & Bulkhead Stabilization | WATERFRONT DEVELOPMENT | 309 | ED-0401 P-C018 ED-0075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  |  | 2019 | 14619 | 7702.79 | 178 | 0 | 0 | 0 | 0 | 0 | 7880.79 | 7593.99 | 243 | 0 | 0 | 0 | 0 | 63 | 7899.99
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HBMA4501B | 33rd Street West of 11th Avenue (Hudson Yards) | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 300 | HB-0215 HW-0001M |  |  | REGARDING OF 33RD STREET WEST OF 11TH AVENUE (HUDSON YARDS) LOCATION:33RD STREET BETWEEN 11TH AND 12TH AVENUES | 2019 | 100000 | 0 | 2830 | 2830 | 50000 | 44340 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HIGHLINE | High Line | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 304 | P-0245M P-D018 P-1326 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | HI LINE, MANHATTAN | HIGH-LINE | 2019 | 115644 | 74304.23 | 0 | 0 | 0 | 0 | 0 | 107 | 74411.23 | 6865.96 | 0 | 0 | 0 | 0 | 0 | 684 | 7549.96
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HIGHLINE2 | High Line - Section 2 | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 304 | P-1326 P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | HIGH LINE SECTION 2 | 2019 | 74001 | 39379.87 | 0 | 0 | 0 | 0 | 0 | 0 | 39379.87 | 20143.64 | 0 | 0 | 0 | 0 | 0 | 15973 | 36116.64
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HL82PHL | DOHMH PHL BUILDING CONSTRUCTION | CLINIC RENOVATION AND REHABILITATION |  | HL-0082 HO-0214 |  |  | ESTIMATE | 2019 | 177527 | 0 | 30000 | 22500 | 57102 | 45791 | 22573 | 18061 | 196027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HWD10214 | Hudson Sq Streetscape Improvements | PRIMARY STREET RECONSTRUCTION | 300 302 | HW-D102 HW-0001M | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | HUDSON SQ STREETSCAPE IMPROVEMENTS | HUDSON SQ STREETSCAPE IMPROVEMENTS | 2019 | 11080 | 1755.29 | 4245 | 1000 | 0 | 0 | 0 | 0 | 7000.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HYDCBLVD | HYDC - MID-BLOCK BLVD AND CROSS STREETS-HUDSON YARD VICINITY | NEIGHBORHOOD REVITALIZATION | 304 | HW-1683 P-0245M SE-0200M | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | HUDSON YARDS DEVELOPMENT CORPORATION - BOULEVARD AND STREETSCAPE | 2019 | 31177 | 278.64 | 9 | 0 | 0 | 0 | 0 | 0 | 287.64 | 37275.7 | 1000 | 4074 | 0 | 0 | 0 | 0 | 42349.7
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | INTREPIDC | FA - Intrepid Museum Foundation - cooling tower | MISCELLANEOUS | 304 | ED-0075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | INTREPID MUSEUM | 2019 | 4171 | 4072.05 | 0 | 0 | 0 | 0 | 99 | 0 | 4171.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | JULIABLCC | Julia de Burgos Latino Cultural Center | NEIGHBORHOOD REVITALIZATION | 311 | ED-0075 ED-D075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | JULIA BORGES LATINO CULTURAL CENTER | 2019 | 685 | 541.97 | 0 | 924 | 0 | 0 | 0 | 0 | 1465.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | JULIABREN | JULIA DE BURGOS CULTURAL CENTER RENOVATIONS | NEIGHBORHOOD REVITALIZATION | 300 | ED-D075 |  |  | JULIA DE BURGOS CULTURAL CENTER RENOVATIONS--CAPITAL UPGRADES THROUGHOUT THE BUILDING | 2019 | 500 | 146.06 | 14 | 340 | 0 | 0 | 0 | 0 | 500.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LAMARQPLZ | La Marqueta Plaza Rehabilitation | NEIGHBORHOOD REVITALIZATION | 300 | ED-D408 ED-D075 |  |  | LA MARQUETA PLAZA REHABILITATION | 2019 | 10500 | 5000 | 3200 | 2300 | 0 | 0 | 0 | 0 | 10500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LAMARQUE4 | La Marqueta Building 4 Exterior Envelope Rehab | MISCELLANEOUS | 300 | ED-0075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | LA MARQUETA BUILDING #4 | 2019 | 1400 | 205.04 | 119 | 500 | 0 | 576 | 0 | 0 | 1400.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LIFESCIEN | LIFE SCIENCES HUB | COMMERCIAL DEVELOPMENT | 300 | ED-0075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | LIFE SCIENCES HUB | 2019 | 150000 | 0 | 0 | 0 | 45000 | 75000 | 30000 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LMAQFACIL | La Marqueta GFNYC, IBZ & NYCEDC Operations Facility | MISCELLANEOUS | 300 | ED-0075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | LA MARQUETA GFNYC, IBZ&NYCEDC OPERATIONS FACILITY. 10/28/14 ADDED 1.6M FROM NRELUMP FOR REQUESTED CP. | 2019 | 1600 | 294.76 | 0 | 25 | 0 | 1281 | 0 | 0 | 1600.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LNEA16125 | 125th St: Interior and Exterior Comprehensive Renovation | ESSENTIAL RECONSTRUCTION OF FACILITIES | 300 | LN-0008 LN-D008 LN-M001 |  |  | INTERIOR AND EXTERIOR COMPREHENSIVE RENOVATION | 2019 | 20000 | 0 | 3356 | 13519 | 0 | 0 | 0 | 0 | 16875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LNEA16FWT | FORT WASHINGTON: MAJOR RENOVATION | ESSENTIAL RECONSTRUCTION OF FACILITIES | 300 | LN-0008 LN-D008 |  |  | MAJOR RENOVATION | 2019 | 20000 | 0 | 4454 | 17910 | 0 | 0 | 0 | 0 | 22364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | MANHGREEN | Manhattan Greenway | COMMUNITY DEVELOPMENT | 300 | ED-0075 |  |  | MANHATTAN GREENWAY | 2019 | 100000 | 7066.85 | 29962 | 20000 | 0 | 97811 | 0 | 0 | 154839.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | MCRUISE | Manhattan Cruise Terminal Improvements to Pier 88, 90 | FINANCING COSTS | 300 | ED-0409 |  |  | MANHATTAN CRUISE TERMINAL IMPROVEMENTS | 2019 | 3500 | 0 | 0 | 1000 | 0 | 0 | 2500 | 0 | 3500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | MCTFEND | MCT PIER 90 FENDERING | MISCELLANEOUS | 300 | ED-0409 |  |  | MCT PIER 90 FENDERING | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 8000 | 0 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | MCTPLAT | Manhattan Cruise Terminal Inshore Platform Rehabilitation | WATERFRONT DEVELOPMENT | 300 | ED-0409 |  |  | MANHATTAN CRUISE TERMINAL INSHORE PLATFORM REHABILITATION | 2019 | 5500 | 3213.84 | 2287 | 0 | 0 | 0 | 0 | 0 | 5500.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | MCTROOF | Manhattan Cruise Terminal Roof and Viaduct Traffic Topping | MISCELLANEOUS | 300 | ED-0075 |  |  | MANHATTAN CRUISE TERMINAL ROOF AND VIADUCT TRAFFIC TOPPING | 2019 | 2000 | 1115.85 | 884 | 0 | 0 | 0 | 0 | 0 | 1999.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | MCTROOF2 | Manhattan Cruise Terminal Roof - Phase 2 - Pier 88 | MISCELLANEOUS | 300 | ED-0075 |  |  | MCT ROOF - PHASE 2 - PIER 88 | 2019 | 0 | 474.66 | 1275 | 250 | 0 | 0 | 0 | 0 | 1999.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | MECAFIT | MECA FITNESS CENTER RENOVATION--FITNESS CENTER RENOVATION | MISCELLANEOUS | 300 | PW-D005 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | MECA FITNESS CENTER RENOVATION--FITNESS CENTER RENOVATION | 2019 | 150 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-3HRGL | NDF - Harlem River Greenway Link - New Park Development | MISCELLANEOUS | 300 | ED-0384 |  |  | HARLEM RIVER GREENWAY LINK - NEW PARK DEVELOPMENT | 2019 | 83000 | 0 | 10000 | 1000 | 19150 | 37350 | 15500 | 0 | 83000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-LAMAR | La Marqueta Redevelopment | MARKET DEVELOPMENT | 300 | ED-0384 |  |  | LA MARQUETA REDEVELOPMENT | 2019 | 0 | 0 | 5000 | 1000 | 0 | 19000 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-NWOOD | NDF - Inwood Greenway and New Parks Development | MISCELLANEOUS | 300 | ED-0384 |  |  | INWOOD GREENWAY AND NEW PARKS CONSTRUCTION | 2019 | 0 | 0 | 5558 | 0 | 44442 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NONTDW | Nontraditional Employment for Women - Renovation of HQ | MISCELLANEOUS | 300 | ED-D075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NONTRADITIONAL EMPLOYMENT FOR WOMEN - RENOVATIONS OF CITY-OWNED HEADQUARTERS | 2019 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NYPDHRP76 | Hudson River Park- Segment 6- Pier 76 | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 300 | PU-0200 |  |  | HUDSON RIVER PARK- SEGMENT 6- PIER 76 | 2019 | 18808 | 0 | 3000 | 7000 | 8808 | 0 | 0 | 0 | 18808 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-301BATW | Battery Park - Wharf | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 300 | PU-0200 RE-0025 |  | BOROUGH OF MANHATTAN | BATTERY PARK WHARF | 2019 | 4300 | 4641.62 | 650 | 0 | 15 | 0 | 0 | 0 | 5306.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-309RVP2 | RIVERSIDE PARK 79 ST BOAT BASIN: C DOCK | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 300 | PU-0200 P-1018 |  | RIVERSIDE PARK 79 ST BOAT BASIN: C DOCK | RIVERSIDE PARK | 2019 | 60938 | 0 | 4000 | 13000 | 38973 | 4965 | 0 | 0 | 60938 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-3E103CG | FA - East 103rd street community garden | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 311 | P-D018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | EAST 103RD STREET | EAST 103RD STREET COMMUNITY GARDEN IN MANHATTAN | 2019 | 150 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-3HIGHLL | FRIENDS OF THE HIGH LINE-LIFE SAFETY UPGRADES & CIRCULATION | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 |  |  | MADISON SQ. PARK ETERNAL LIGHT FLAGSTAFF LANDSCAPE, MAHATTAN | 2019 | 617 | 0 | 617 | 0 | 0 | 0 | 0 | 0 | 617 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-3HILIN3 | Highline Phase 3 | MISCELLANEOUS | 304 | P-D018 P-1326 P-1018 P-M245 |  |  | HIGHLINE PHASE 3 | 2019 | 11000 | 10229.72 | 871 | 0 | 0 | 0 | 0 | 0 | 11100.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-3HRP132 | Harlem River Park 132-135 | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 300 | PU-0200 P-0501 |  | HARLEM RIVER PK 132-135 ST. | HARLEM RIVER PK 132-135 ST. | 2019 | 20216 | 0 | 45455 | 90444 | 8759 | 0 | 0 | 0 | 144658 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-3RETWAL | Seawall and Henry Hudson Parkway | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 300 | P-1018 P-1515 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | MANHATTAN | E. RIVER PARK RETAINING WALLS | 2019 | 3286 | 4232.07 | 344 | 0 | 0 | 0 | 0 | 0 | 4576.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PASSSHIP4 | Manhattan Cruise Terminal - Viaduct Concrete Rehabilitation | WATERFRONT DEVELOPMENT | 304 | ED-0075 |  | NEW YORK, NEW YORK 10019 | MANHATTAN CRUISE TERMINAL - VIADUCT CONCRETE REHABILITATION | 2019 | 6000 | 4724.27 | 1275 | 0 | 0 | 0 | 0 | 0 | 5999.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER11DOT | Pier 11 | RECONSTRUCTION OF FERRY TERMINAL FACILITIES | 300 | FA-0027 |  |  | PIER 11 | 2019 | 3750 | 2985.86 | 36 | 708 | 0 | 0 | 0 | 0 | 3729.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER35-36 | Pier 35 and 36 Rehabilitation | WATERFRONT DEVELOPMENT | 303 | SE-0200M ED-0409 WM-0001 S-0136 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | REHABILITATION OF PLATFORM AT PIERS 35 AND 36 | 2019 | 6400 | 15555.29 | 3054 | 0 | 0 | 0 | 0 | 0 | 18609.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER36STR | Pier 36 Structural Rehab | GARAGES AND FACILITIES | 303 | PU-0200 |  |  | STRUCTURRAL REHAB | 2019 | 13630 | 0 | 13630 | 0 | 0 | 0 | 0 | 0 | 13630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER38 | DPR-CON ED Pier-Rehab Pier on East River from 38th to 44th S | MISCELLANEOUS | 300 306 | ED-D401 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | DPR-CON ED PIER-REHAB PIER ON EAST RIVER FROM 38TH TO 44TH ST. | 2019 | 3102 | 3173.49 | 527 | 0 | 0 | 0 | 0 | 0 | 3700.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER4 | PIER 4 Rehabilitation | WATERFRONT DEVELOPMENT | 300 | ED-0409 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | PIER 4 REHABILITATION | 2019 | 1891 | 0 | 400 | 1491 | 0 | 0 | 0 | 0 | 1891 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER42CNT | Pier 42 and East River Park Connector Program | MISCELLANEOUS | 300 | P-1018 P-0245M P-M245 P-D933 ED-0075 PU-0100 P-D018 |  |  | PIER 42 | 2019 | 0 | 0 | 350 | 4554 | 72 | 0 | 0 | 0 | 4976 | 0 | 239 | 18755 | 0 | 0 | 0 | 0 | 18994
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER6PILE | Pier 6 Pile Rehabilitation | PORT DEVELOPMENT | 300 | ED-0409 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | PIER 6 PILE REHABILITATION | 2019 | 4000 | 1754.9 | 0 | 0 | 0 | 560 | 1685 | 0 | 3999.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER79DOT | Pier 79 | RECONSTRUCTION OF FERRY TERMINAL FACILITIES | 300 | FA-0027 |  |  | PIER79 | 2019 | 5500 | 1718.09 | 221 | 719 | 0 | 0 | 0 | 0 | 2658.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIERS35N6 | Pier 35 & 36 Substructure Rehabilitation | MISCELLANEOUS | 300 | ED-0409 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | PIER 35 & 36 SUBSTRUCTURE REHABILITATION | 2019 | 2000 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIERS8890 | Piers 88 & 90 Cluster Encapsulation Project | MISCELLANEOUS | 301 | ED-0409 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | PIERS 88 & 90 CLUSTER ENCAPSULATION PROJECT | 2019 | 20500 | 19195.81 | 1304 | 0 | 0 | 0 | 0 | 0 | 20499.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PROGDOMIN | COMMUNITY ASSOCIATION OF PROGRESSIVE DOMINICANS | MISCELLANEOUS | 300 | ED-D075 ED-M075 |  |  | COMMUNITY ASSOCIATION OF PROGRESSIVE DOMINICANS--CONSTRUCTION RENOVATION | 2019 | 900 | 575.67 | 324 | 0 | 0 | 0 | 0 | 0 | 899.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV034SCED | AMNH - Science & Education Innovation Center Bldg. 17 | ESSENTIAL RECONSTRUCTION OF FACILITIES | 307 | PV-M034 PV-0034 PV-D034 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | RENOVATION TO EXISTING FLOORS, ADD NEW FLOORS AND A ROOF DECK. | 2019 | 3000 | 0 | 78250 | 0 | 0 | 100 | 0 | 0 | 78350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV279-STU | NYCC - New York City Center Studios Renovation | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | PV-0279 PV-D279 PV-M279 |  |  | TBD | 2019 | 1350 | 0 | 2163 | 0 | 0 | 54 | 0 | 0 | 2217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV467ELMB | ELM- El Museo - Gallery Environmental Stabilzation Project | ESSENTIAL RECONSTRUCTION OF FACILITIES | 311 | PV-D018 PV-0103 PV-M467 PV-0467 PV-D467 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 1230 FIFTH AVENUE, MANHATTAN, NY | MUSUEM GALLERY HVAC AND ENVIRONMENTAL STABILIZATION | 2019 | 2718 | 3713.55 | 0 | 0 | 0 | 0 | 1078 | 0 | 4791.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV467M125 | Mart 125 Development | ESSENTIAL RECONSTRUCTION OF FACILITIES | 311 | PV-0467 PV-M467 PV-D467 PV-D999 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | DEVELOPMENT OF MART 125 CULTURAL SPACE | 2019 | 9000 | 0 | 0 | 1755 | 0 | 11839 | 0 | 0 | 13594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | RANDISSF | Randall's Island Sports Fields | MISCELLANEOUS | 311 | P-0944 P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | DESIGN IMPROVEMENTS OF RANDALL'S ISLAND SPORTS FIELDS | 2019 | 3950 | 9915.63 | 0 | 0 | 0 | 0 | 0 | 64 | 9979.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | RISALTMAR | Randall's Island Salt Marsh | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 311 | SE-0200M P-0944 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RI SALT MARSH | 2019 | 4207 | 2471.54 | 0 | 0 | 0 | 0 | 0 | 8 | 2479.54 | 2073.18 | 0 | 0 | 0 | 0 | 0 | 84 | 2157.18
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | ROOSEDOCK | Roosevelt Island Dock | WATERFRONT DEVELOPMENT | 308 | ED-D401 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ROOSEVELT ISLAND DOCK | 2019 | 500 | 0 | 0 | 0 | 0 | 698 | 0 | 0 | 698 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | ROOSEOPER | Roosevelt Island Operating Corp - Blackwell House | MISCELLANEOUS | 308 | ED-D075 |  |  | ROOSEVELT ISLAND OPERATING CORP - BLACKWELL HOUSE -- ADDITION OF A PLAYGROUND AREA - BLACKWELL PARK - NORTHEAST CORNER. | 2019 | 0 | 0 | 144 | 0 | 0 | 0 | 0 | 0 | 144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND1101 | HHC FEMA PMP BELLEVUE: WATER REDUNDANCY A4 | MISCELLANEOUS | 300 | HO-0214 |  |  | BELLEVUE | 2019 | 1316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2995.5 | 30 | 190 | 0 | 0 | 0 | 0 | 3215.5
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND1102 | HHC FEMA PMP BELLEVUE: MEDICAL GAS SYSTEM MITIGATION A5 | MISCELLANEOUS | 300 | HO-0214 |  |  | BELLEVUE | 2019 | 2296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3163.07 | 250 | 399 | 0 | 0 | 0 | 0 | 3812.07
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND1103 | HHC FEMA PMP BELLEVUE: Pipe and Basement Tank Insulation A7 | MISCELLANEOUS | 300 | HO-0214 |  |  | BELLEVUE | 2019 | 678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 678 | 0 | 0 | 0 | 0 | 678
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND1104 | HHC FEMA Bellevue Hospital Center Flood Protection Barrier | MISCELLANEOUS | 300 | HO-0214 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BELLEVUE | 2019 | 314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 496.51 | 7 | 142 | 0 | 0 | 0 | 0 | 645.51
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND1105 | HHC FEMA BELLEVUE HOSPITAL REPLACEMENT GENERATOR | MISCELLANEOUS | 300 | HO-0214 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CONSTRUCTION OF A GENERATOR AT BELLEVUE | 2019 | 11228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7799.26 | 340 | 3089 | 0 | 0 | 0 | 0 | 11228.26
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND1106 | HHC FEMA BELLEVUE HOSPITAL Civil Roadway | MISCELLANEOUS | 300 | HO-0214 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BELLEVUE | 2019 | 3067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1944.93 | 0 | 1122 | 0 | 0 | 0 | 0 | 3066.93
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND1108 | HHC FEMA BELLEVUE HOSPITAL PARKING LOT LIFTS | MISCELLANEOUS | 300 | HO-0214 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | HHC | 2019 | 2388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3123.76 | 253 | 2347 | 0 | 0 | 0 | 0 | 5723.76
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND1110 | HHC FEMA BELLEVUE (MEP/VT | MISCELLANEOUS | 300 | HO-0214 |  |  | BELLEVUE | 2019 | 10877 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10877 | 0 | 0 | 0 | 0 | 10877
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND1112 | HHC FEMA BELLEVUE BASEMENT GENERAL CONSTRUCTION | MISCELLANEOUS | 300 | HO-0214 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BAM | 2019 | 3505 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2144.83 | 173 | 1187 | 0 | 0 | 0 | 0 | 3504.83
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND1113 | HHC FEMA PMP BELLEVUE EXISTING VERTICAL TRANSPORTATION | MISCELLANEOUS | 300 | HO-0214 |  |  | BELLEVUE HOSPITAL VERTICAL TRANSPORTATION | 2019 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14804.06 | 6 | 2592 | 2598 | 0 | 0 | 0 | 20000.06
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND3702 | MHC: REPLACE SWITCHGEAR, PANEL BOXES & ATS - SANDY CTGY E | ROUTINE RECONSTRUCTION | 311 | HO-0214 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 1901 FIRST AVENUE, NEW YORK, NY 10029 | RECONSTRUCTION OF METROPOLITAN HOSPITAL CENTER NECESSITATED BY HURRICANE SANDY. FEMA CATEGORY E: BUILDINGS AND EQUIPMENT (PERMANENT WORK). AS A RESULT OF THE EFFECTS OF HURRICANE SANDY, FLOODING WITHIN THE BASEMENT RESULTED IN IMMEDIATE AND LONG-TEM IMPACTS OF THE BUILDINGS SYSTEMS, INCLUDING EXTENSIVE WATER DAMAGE TO THE NORMAL ELECTRICAL SERVICE ENTANCE CONDUCTORS FOR "SERVICE A" AND "SERVICE B". | 2019 | 3600 | 66.02 | 0 | 0 | 0 | 252 | 0 | 0 | 318.02 | 594.23 | 0 | 2646 | 0 | 0 | 0 | 0 | 3240.23
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND3703 | MHC: REPLACE SRVC ENTRANCE CABLES & DUCTBANK - SANDY CTRY E | ROUTINE RECONSTRUCTION | 311 | HO-0214 |  | 1901 FIRST AVENUE, NEW YORK, NY 10029 | RECONSTRUCTION OF METROPOLITAN HOSPITAL CENTER NECESSITATED BY HURRICANE SANDY. FEMA CATEGORY E: BUILDINGS AND EQUIPMENT (PERMANENT WORK). AS A RESULT OF THE EFFECTS OF HURRICANE SANDY, FLOODING WITHIN THE BASEMENT RESULTED IN IMMEDIATE AND LONG-TEM IMPACTS OF THE BUILDINGS SYSTEMS, INCLUDING EXTENSIVE WATER DAMAGE TO THE NORMAL ELECTRICAL SERVICE ENTANCE CONDUCTORS FOR "SERVICE A" AND "SERVICE B". | 2019 | 5256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 693.94 | 0 | 4562 | 0 | 0 | 0 | 0 | 5255.94
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND3705 | METROPOLITAN HOSPITAL FLOOD MITIGATION SYSTEM | MISCELLANEOUS | 300 | HO-0214 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | METRO HOSPITAL | 2019 | 7597 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5883.79 | 0 | 6713 | 0 | 7875 | 7875 | 0 | 28346.79
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND6701 | COLER : DESIGN & CONSTRUCTION FOR NEW GENERATOR | MISCELLANEOUS | 300 | HO-0214 |  |  | COLER | 2019 | 11023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10052.87 | 0 | 2206 | 0 | 0 | 0 | 0 | 12258.87
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND6702 | COLER : DESIGN & CONSTRUCTION OF NEW LIGHTING | MISCELLANEOUS | 300 | HO-0214 |  |  | COLER | 2019 | 1645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2994.1 | 0 | 560 | 0 | 0 | 0 | 0 | 3554.1
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND6703 | COLER : DESIGN & CONSTRUCTION OF ELECTRICAL PANELS | MISCELLANEOUS | 300 | HO-0214 |  |  | COLER | 2019 | 657 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750.57 | 258 | 117 | 0 | 0 | 0 | 0 | 1125.57
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND6704 | COLER : AUDITORIUM DESIGN AND CONSTRUCTION MANAGEMENT | MISCELLANEOUS | 300 | HO-0214 |  |  | COLER | 2019 | 918 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1183.65 | 0 | 321 | 0 | 0 | 0 | 0 | 1504.65
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND6705 | COLER : Specialty Hospital First Floor Design | MISCELLANEOUS | 300 | HO-0214 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | COLER | 2019 | 1474 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 823.83 | 900 | 762 | 0 | 0 | 0 | 0 | 2485.83
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND6706 | COLER : DESIGN & CONSTRUCTION FOR FIRE PUMP | MISCELLANEOUS | 300 | HO-0214 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | COLER | 2019 | 1107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2264.31 | 60 | 685 | 0 | 0 | 0 | 0 | 3009.31
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDCD14 | PIER 76 ELECTRICAL CONDUIT | POLICE FACILITIES | 300 | PO-0079 |  | PIER 76 ELECTRICAL CONDUIT | PIER 76 ELECTRICAL CONDUIT | 2019 | 2069 | 0 | 0 | 221 | 0 | 0 | 0 | 0 | 221 | 0 | 0 | 1983 | 0 | 0 | 0 | 0 | 1983
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDCD15 | PIER 36 ELECTRICAL CONDUIT | POLICE FACILITIES | 300 | PO-0079 |  |  | PIER36 ELECTRICAL CONDUIT | 2019 | 894 | 0 | 96 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 857 | 0 | 0 | 0 | 0 | 0 | 857
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDFERRY | Repair34th St Ferry Landings as a result of Hurricane Sandy | RECONSTRUCTION OF FERRY TERMINAL FACILITIES | 300 306 | FA-0313 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | REPAIRING THE EAST 34TH STREET EAST RIVER FERRY LANDINGS PROJECT DAMAGE CAUSED BY HURRICANE SANDY | 2019 | 1476 | 0 | 148 | 0 | 0 | 0 | 0 | 0 | 148 | 0 | 1328 | 0 | 0 | 0 | 0 | 0 | 1328
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDHWMO | Reconstruction of Moore Street- Hurricane Sandy | PRIMARY STREET RECONSTRUCTION | 300 | HW-0001M | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | RECONSTRUCTION OF MOORE STREET HURRICANE SANDY | RECONSTRUCTION OF MOORE STREET- HURRICANE SANDY | 2019 | 363 | 0 | 0 | 70 | 0 | 0 | 0 | 0 | 70 | 0 | 0 | 626 | 0 | 0 | 0 | 0 | 626
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDR2BRG | Construction of Flex Barges | RECONSTRUCTION OF FERRY TERMINAL FACILITIES | 300 | FA-0021 |  |  | CONSTRUCTION OF FLEX BARGES | 2019 | 12000 | 0 | 304 | 2500 | 196 | 0 | 0 | 0 | 3000 | 0 | 910 | 2500 | 5590 | 0 | 0 | 0 | 9000
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDRLE34 | FA Resiliency - Land Hardening E 34 street | MISCELLANEOUS | 300 | FA-0027 |  |  | FA RESILIENCY - LAND HARDENING E 34 STREET | 2019 | 1000 | 0 | 35 | 200 | 15 | 0 | 0 | 0 | 250 | 0 | 106 | 200 | 444 | 0 | 0 | 0 | 750
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDTGI | Governors Island Hurricane Sandy Repairs | MISCELLANEOUS | 300 301 | ED-0831 |  |  | CAPITAL PROJECTS EMERGENCY WORK AS A RESULT OF HURRICANE SANDY | 2019 | 3360 | 0 | 115 | 0 | 0 | 0 | 0 | 0 | 115 | 0 | 3039 | 0 | 0 | 0 | 0 | 0 | 3039
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDTGIEL | Governors Island - Hurricane Sandy Electrical Repairs | MISCELLANEOUS | 300 301 | ED-0075 |  |  | TGI HURRICANE SANDY ELECTRICAL REPAIRS | 2019 | 6103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 805.69 | 5298 | 0 | 0 | 0 | 0 | 0 | 6103.69
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDY3-01 | HIghline M&O Facility Sandy Repairs | MISCELLANEOUS | 300 302 304 | P-1018 |  |  | HAZARD MITIGATION WORK TO RELOCATE THE MAINTENANCE & OPERATIONS FACILITY'S ELECTRICAL UTILITIES FROM THE SUB-GRADE VAULT INTO THE GROUND FLOOR OF THE BUILDING, FOLLOWING DAMAGE DONE BY HURRICANE SANDY. | 2019 | 1119 | 104.85 | 0 | 0 | 0 | 0 | 0 | 8 | 112.85 | 943.7 | 0 | 63 | 0 | 0 | 0 | 0 | 1006.7
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SBSRELOCA | SBS FY18 Relocation to 1 Liberty Plaza | MISCELLANEOUS | 300 | ED-0075 |  |  | DESIGN AND CONSTRUCTION COSTS FOR SBS MOVE TO 1 LIBERTY PLAZA | 2019 | 20013 | 284.62 | 21028 | 0 | 0 | 0 | 0 | 0 | 21312.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SKYPORT | Skyport Garage and Marina Rehabilitation | MISCELLANEOUS | 300 306 | ED-0409 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | SKYPORT GARAGE AND MARINA REHABILITATION | 2019 | 5000 | 2310.67 | 269 | 1000 | 0 | 0 | 1420 | 0 | 4999.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SOLAR2 | CEC Stuyvesant Cove Inc.-Construction of Solar 2 | WATERFRONT DEVELOPMENT | 300 306 | ED-D401 PW-0077 PU-0025 ED-D075 ED-M075 ED-0075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CEC STUYVESANT COVE INC.-CONSTRUCTION OF SOLAR 2 | 2019 | 1500 | 1055.57 | 223 | 6350 | 0 | 0 | 0 | 0 | 7628.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SSRECON | South Street Reconstruction | MISCELLANEOUS | 300 301 | HW-0001M | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | SOUTH STREET PEDESTRIAN STREETSCAPE IMPROVEMENTS | 2019 | 8400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7328.26 | 1670 | 0 | 0 | 0 | 0 | 0 | 8998.26
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SSSPIER16 | South Street Seaport - Pier 16 Rehab | WATERFRONT DEVELOPMENT | 301 | ED-0409 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | REHAB OF PIER 16 AND MARGINAL WHARF | 2019 | 1700 | 1635.41 | 0 | 0 | 0 | 60 | 0 | 0 | 1695.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | STUYBULK2 | Stuyvesant Cove Park Bulkhead Park Repair | WATERFRONT DEVELOPMENT | 306 | ED-0409 |  |  | STUYVESANT COVE PARK, 18TH TO 23RD STREETS ALONG THE EAST RIVER | 2019 | 0 | 0 | 654 | 0 | 0 | 0 | 0 | 0 | 654 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | TINMARKET | New Market Tin Building Demolition | MISCELLANEOUS | 300 | ED-0409 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NEW MARKET TIN BUILDING DEMOLITION | 2019 | 4331 | 0 | 4331 | 0 | 0 | 0 | 0 | 0 | 4331 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | W125TRANS | West 125th Street/Manhattanville | COMMERCIAL DEVELOPMENT | 300 309 | ED-0384 ED-0075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | WEST 125TH STREET/MANHATTANVILLE | 2019 | 32978 | 8311.45 | 1957 | 0 | 0 | 0 | 0 | 0 | 10268.45 | 13866.7 | 8342 | 0 | 0 | 0 | 0 | 0 | 22208.7
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | WATERSIDE | WATERSIDE PIER & STUYVESANT COVE AMENITIES | MISCELLANEOUS | 300 | ED-D401 |  |  | WATERSIDE PIER & STUYVESANT COVE AMENITIES--FUNDING WILL SUPPORT AMENITIES AT WATERSIDE PIER AND STUYVESANT COVE | 2019 | 1050 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | WATERST | Water Street Corridor Streetscape Improvements | MISCELLANEOUS | 300 | ED-0075 HW-0001M |  |  | WATER STREET CORRIDOR STREETSCAPE IMPROVEMENTS | 2019 | 10000 | 0 | 0 | 2228 | 0 | 0 | 0 | 0 | 2228 | 1572.44 | 3540 | 13799 | 0 | 0 | 0 | 0 | 18911.44
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | WHARLMPK | West Harlem Piers Park | MISCELLANEOUS | 300 | P-D018 ED-0409 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | REPAIRS TO VARIOUS ASPECTS OF THE PARK | 2019 | 1162 | 0 | 386 | 0 | 0 | 776 | 0 | 0 | 1162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | WHITEHALL | Whitehall Terminal Reconstruction, Manhattan | PORT DEVELOPMENT | 301 | ED-0405 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | WHITEHALL TERMINAL AND PETER MINUIT PLAZA - PETER MINUIT PLACE, STATESTREET, WHITEHALL STREET, U.S. PIERHEAD LINE, MANHATTAN | CONSTRUCTION OF A NEW PERMANENT FACILITY - WHITEHALL TERMINAL, THE MANTERMINUS OF THE STATEN ISLAND FERRY - TO REPLACE THE BUILDING DAMAGEDIN SEPTEMBER, 1991 | 2019 | 261670 | 176071.37 | 0 | 0 | 0 | 0 | 0 | 0 | 176071.37 | 15665.04 | 0 | 0 | 0 | 0 | 0 | 1235 | 16900.04
20190425 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | WTHAMES | West Thames Bridge | MISCELLANEOUS | 300 301 | HB-0215 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | WEST THAMES BRIDGE | 2019 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 5000
20190425 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM02USCC | (WHITE) UNION SETTLEMENT ASSOC. - COMM. CTR. RENOVATION | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 300 311 | HA-D001 HA-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CREATION OF ADDITIONAL CLASSROOMS, PROGRAM SPACE AND RECONFIGURATION OF LOBBY TO MAKE THE CENTER MORE ACCESSIBLE. | 2019 | 1008 | 3117.08 | 108 | 0 | 0 | 0 | 0 | 0 | 3225.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM06CSCP | CLINTON SENIOR CENTER-PROJECT FIND | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 311 | AG-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | KITCHEN REDESIGN AND COMPREHENSIVE UPGRADE, BATHROOM REDESIGN FOR ACCESSIBILITY AND IMPROVEMENTS, ARCHITECTURAL FEES. | 2019 | 495 | 1844 | 250 | 0 | 0 | 0 | 0 | 0 | 2094 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM06MHEL | Manhattanville Houses Elevators | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 309 | HA-0001 |  |  | UPGRADING OF ELEVATORS AT MANHATTANVILLE HOUSES | 2019 | 2970 | 2229.65 | 267 | 0 | 0 | 0 | 0 | 0 | 2496.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM07CIDC | CITIZENS CARE DAY CARE - PLAYGROUND EQUIPMENT AND MATTING | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 310 | HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | PLAYGROUND EQUIPMENT AND MATTING | 2019 | 36 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM08HSST | HENRY STREET SETTLEMENT - GOOD COMPANIONS SR CTR RENOVATIONS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 303 | HA-M001 HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RENOVATION OF THE HENRY STREET SETTLEMENT | 2019 | 750 | 334 | 1816 | 0 | 0 | 0 | 0 | 0 | 2150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM08RUHI | RUTGERS HOUSES ENERGY INITIATIVES | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 303 | HA-0001 |  |  | RUTGERS HOUSES HEATING UPGRADES | 2019 | 7790 | 4875.14 | 275 | 0 | 0 | 0 | 0 | 0 | 5150.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM08VLAD | VLADECK HOUSES - GOOD COMPANIONS SC HVAC, KITCHEN, BATH | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 303 | HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RENOVATE KITCHEN AND BATHROOM AND INSTALL HVAC SYSTEM | 2019 | 250 | 0 | 327 | 0 | 0 | 0 | 0 | 0 | 327 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM09FWSR | FT WASHINGTON SER FOR THE ELDERLY OFFICES, CLASSRM, COMP RM | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 312 | HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RENOVATE CASEWORK OFFICES AND PROGRAM ROOMS TO CREATE MORE OFFICES, PROGRAM SPACE AND COMPUTER LAB | 2019 | 200 | 82.95 | 117 | 0 | 0 | 0 | 0 | 0 | 199.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM11VLFA | VLADECK HOUSES- GOOD COMPANIONS/HENRY ST, FIRE ALARM SYSTEM | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 303 | HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | INSTALL A FIRE ALARM SYSTEM AT GOOD COMPANIONS/ HENRY STREET SETTLEMENT | 2019 | 250 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM13CLEV | CLINTON HOUSES ELEVATOR REHABILITATION | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 311 | HA-0001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ELEVATOR REHABILITATION | 2019 | 5610 | 4452 | 648 | 0 | 0 | 0 | 0 | 0 | 5100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM13HTET | HOLMES TOWER ENTRANCES AND LAYERED ACCESS CONTROLS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 308 | HA-D001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | NEW ENTRANCES AND LAYERED ACCESS CONTROLS | 2019 | 418 | 321.22 | 97 | 0 | 0 | 0 | 0 | 0 | 418.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM14MNSE | METRO NORTH PLAZA SECURITY UPGRADES | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 311 | HA-D001 |  |  | SECURITY UPGRADES | 2019 | 100 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15CVGR | CARVER GARDENS DAY CARE CENTER PLAYGROUND | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 311 | HA-D001 |  |  | UPGRADE DAY CARE CENTER PLAYGROUND | 2019 | 200 | 0 | 343 | 0 | 0 | 0 | 0 | 0 | 343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15ICNB | STANLEY ISAACS UPGRADE OF SENIOR AND YOUTH CENTER COMP. UPGR | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 308 | HA-D001 |  |  | SENIOR AND YOUTH CENTER UPGRADES | 2019 | 680 | 1791.04 | 211 | 0 | 0 | 0 | 0 | 0 | 2002.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15JFSR | JEFFERSON SENIOR CENTER UPGRADE | DEPARTMENT FOR THE AGING BUILDING RECONSTRUCTION | 311 | AG-D001 HA-D001 |  |  | UPGRADE SENIOR CENTER | 2019 | 450 | 0 | 1071 | 0 | 0 | 0 | 0 | 0 | 1071 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15MOGD | METRO NORTH PLAZA DAY CARE CENTER PLAYGROUND RENOVATION | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 311 | HA-D001 |  |  | DAY CARE CENTER RENOVATION | 2019 | 200 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15WSGR | WISE TOWERS PLAY AREA UPGRADE | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 307 | HA-D001 |  |  | UPGRADE PLAY AREA | 2019 | 86 | 85.44 | 526 | 0 | 0 | 0 | 0 | 0 | 611.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15WSPL | WASHINGTON HOUSES DAY CARE CENTER PLAYGROUND UPGRADE | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 311 | HA-D001 |  |  | DAY CARE CENTER PLAYGROUND UPGRADE | 2019 | 200 | 0 | 257 | 0 | 0 | 0 | 0 | 0 | 257 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16AMBL | AMSTERDAM HOUSES BARRELS PLAYGROUND RENO | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 307 | HA-D001 |  |  | BARRELS PLAYGROUND RENO | 2019 | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16AMUP | AMSTERDAM HOUSES NYCHA-UPGRADES | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 307 | HA-D001 |  |  | AMSTERDAM HOUSES NYCHA-UPGRADES | 2019 | 50 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16CRCC | CORSI HOUSES UPGRADES TO LAGUARDIA COMMUNITY CENTER | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 311 | HA-D001 HA-0001 |  |  | CORSI HOUSES UPGRADES TO LAGUARDIA COMMUNITY CENTER | 2019 | 1000 | 0 | 4068 | 0 | 0 | 0 | 0 | 0 | 4068 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16GHPL | GRANT HOUSES MAJOR PLAYGROUND RENOVATIONS-PLAYGROUND REPAIRS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 309 | HA-D001 |  |  | MAJOR PLAYGROUND RENOVATIONS-PLAYGROUND REPAIRS | 2019 | 450 | 358.05 | 92 | 0 | 0 | 0 | 0 | 0 | 450.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16LGSC | 282 CHERRY STREET SECURITY CAMERAS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 303 | HA-D001 |  |  | 282 CHERRY STREET SECURITY CAMERAS | 2019 | 70 | 0 | 170 | 0 | 0 | 0 | 0 | 0 | 170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16LXCG | LEXINGTON HOUSES GROUND UPGRADE COMMUNITY GARDEN | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 311 | HA-D001 |  |  | GROUNDS UPGRADE-COMMUNITY GARDEN | 2019 | 385 | 0 | 385 | 0 | 0 | 0 | 0 | 0 | 385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16SICC | STANLEY ISAACS SECURITY CAMERAS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 301 | HA-D001 |  |  | INSTALL SECURITY CAMERAS | 2019 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16UPGI | UNDERGROUND WATER AND FIRE DISTRIBUTION PIPING | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 300 | HA-D001 |  |  | REPLACEMENT OF UNDERGROUND WATER AND FIRE DISTRIBUTION PIPING. | 2019 | 8000 | 5281.37 | 2719 | 0 | 0 | 0 | 0 | 0 | 8000.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16WRSC | WISE REHAB 54 W. 94TH STREET SECURITY CAMERAS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 307 | HA-D001 |  |  | WISE REHAB 54 W. 94TH STREET SECURITY CAMERAS | 2019 | 75 | 0 | 125 | 0 | 0 | 0 | 0 | 0 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM17CRGR | CORSI HOUSES SITTING AREA FOR SENIORS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 311 | HA-D001 |  |  | RENOVATE GROUNDS TO PROVIDE A SITTING AREA FOR SENIORS | 2019 | 300 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM17HRPL | HERNANDEZ PLAYGROUND RENOVATION AY 189 ALLEN STREET | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 303 | HA-D001 |  |  | PLAYGROUND RENOVATION | 2019 | 165 | 0 | 1087 | 0 | 0 | 0 | 0 | 0 | 1087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM17TBPL | TWO BRIDGES PLAYGROUND RENOVATION | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 303 | HA-D001 |  |  | RENOVATE PLAYGROUND AT 286 SOUTH STREET | 2019 | 350 | 0 | 350 | 0 | 0 | 0 | 0 | 0 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM17THUR | ROOF WORK AT THURGOOD MARSHALL HOUSES | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 300 | HA-0001 |  |  | ROOF WORK AT THURGOOD MARSHALL HOUSES | 2019 | 2200 | 0 | 2200 | 0 | 0 | 0 | 0 | 0 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM17WGPA | WAGNER HOUSES PLAY AREA UPGRADE | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 311 | HA-D001 |  |  | PLAY AREA UPGRADE | 2019 | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM17WHGR | WHITE HOUSES GROUNDS RENOVATIONS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 311 | HA-D001 |  |  | RENOVATE GROUNDS | 2019 | 400 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM17WSCR | WSUR A Community Room Bathroom Installation | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 307 | HA-D001 |  |  | INSTALL A BATHROOM IN THE COMMUNITY ROOM | 2019 | 140 | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM1833SC | 335 EAST 111TH STREET SECURITY CAMERAS AND DOOR | LOW TO MODERATE INCOME PUBLIC HOUSING CONSTRUCTION | 311 | HA-D001 |  |  | INSTALL SECURITY CAMERAS AND A NEW DOOR | 2019 | 400 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18DGLG | DOUGLASS HOUSES LIGHTING UPGRADE | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 307 | HA-D001 |  |  | DOUGLASS HOUSES LIGHTING UPGRADE | 2019 | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18DIGV | DIGITAL VAN | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 300 | HA-D001 |  |  | DIGITAL VAN | 2019 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18ECGR | GROUNDS RENOVATION AT ELLIOT - CHELSEA HOUSES | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 304 | HA-D001 |  |  | GROUNDS RENOVATION | 2019 | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18GOBR | GOMPERS BOILER REPAIR | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 300 | HA-0001 |  |  | GOMPERS BOILER REPAIR | 2019 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18GRLM | GRANT HOUSES LAUNDROMAT RENOVATION | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 309 | HA-D001 HA-M001 |  |  | GRANT HOUSES LAUNDROMAT RENOVATION | 2019 | 1100 | 0 | 1740 | 0 | 0 | 0 | 0 | 0 | 1740 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18HUFC | Hudson Guild Inc. Renovation: Fulton Center Renovation | LOW TO MODERATE INCOME PUBLIC HOUSING CONSTRUCTION | 300 | HA-M001 HA-D001 HA-0001 |  |  | HUDSON GUILD INC. RENOVATION: FULTON CENTER RENOVATION | 2019 | 1900 | 0 | 1900 | 0 | 0 | 0 | 0 | 0 | 1900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18JFBC | JEFFERSON HOUSES BASKETBALL COURT | LOW TO MODERATE INCOME PUBLIC HOUSING CONSTRUCTION | 311 | HA-D001 |  |  | RENOVATE BASKETBALL COURTS | 2019 | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18JFTV | INSTALLATION OF SECURITY CAMERAS AT JEFFERSON HOUSES | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 311 | HA-D001 |  |  | INSTALLATION OF SECURITY CAMERAS AT JEFFERSON HOUSES | 2019 | 259 | 0 | 259 | 0 | 0 | 0 | 0 | 0 | 259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18JOCC | JOHNSON COMM. CTR. STANLEY ISACCS NBRHD ROOF GLASS PANES | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 311 | HA-D001 |  |  | JOHNSON COMM. CTR. STANLEY ISACCS NBRHD ROOF GLASS PANES & SURFACES | 2019 | 626 | 0 | 877 | 0 | 0 | 0 | 0 | 0 | 877 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18LIPG | RENOVATION OF A PLAYGROUND AT LOWER EAST SIDE I INFILL | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 303 | HA-D001 |  |  | RENOVATION OF A PLAYGROUND AT LOWER EAST SIDE I INFILL | 2019 | 266 | 0 | 266 | 0 | 0 | 0 | 0 | 0 | 266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18URBF | URBAN FARMS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 300 | HA-D001 |  |  | URBAN FARMS | 2019 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18VLPG | VLADECK HOUSES PLAYGROUND UPGRADE | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 303 | HA-M001 |  |  | VLADECK HOUSES PLAYGROUND. MADISON STREET BET. JACKSON AND GOUVERNEURSTREETS | 2019 | 500 | 0 | 700 | 0 | 0 | 0 | 0 | 0 | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WAGD | WASHINGTON HOUSES MAKE PLAYGROUND ADA ACCESSIBLE | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 311 | HA-D001 |  |  | MAKE PLAYGROUND ADA ACCESSIBLE | 2019 | 500 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WHTV | WHITE HOUSES SECURITY CAMERAS AND NEW DOOR | LOW TO MODERATE INCOME PUBLIC HOUSING CONSTRUCTION | 311 | HA-D001 |  |  | INSTALL SECURITY CAMERAS AND A NEW DOOR | 2019 | 400 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19AMEL | AMSTERDAM HOUSES ELEVATOR UPGRADE | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 307 | HA-0001 |  |  | UPGRADE ELEVATORS AT AMSTERDAM HOUSES | 2019 | 12392 | 0 | 300 | 465 | 0 | 10500 | 0 | 0 | 11265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19DCCR | DYCKMAN HOUSES COMMUNITY CENTER RAMP | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 312 | HA-D001 |  |  | FUNDING FOR COMMUNITY CENTER RAMP | 2019 | 300 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19DHPR | DYCKMAN HOUSES PLAYGROUND RENOVATION | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 312 | HA-D001 |  |  | FUNDING FOR DYCKMAN HOUSES PLAYGROUND RENOVATION | 2019 | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19ECSC | ELLIOTT-CHELSEA HOUSES SECURITY CAMERAS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 304 | HA-D001 |  |  | ELLIOTT SECURITY CAMERAS | 2019 | 250 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19FHSC | FULTON HOUSES SECURITY CAMERAS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 304 | HA-D001 |  |  | SECURITY CAMERAS | 2019 | 250 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19GHEL | GRANT HOUSES EXTERNAL LIGHTING UPGRADES | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 309 | HA-D001 |  |  | EXTERNAL LIGHTING UPGRADES | 2019 | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19HBBR | HARBORVIEW COMMUNITY/SENIOR CENTER BATHROOM RENOVATIONS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 311 | HA-0001 |  |  | RENOVATION OF BATHROOMS IN COMMUNITY/SENIOR CENTER AT HARVORVIEW HOUSES | 2019 | 0 | 0 | 235 | 0 | 0 | 0 | 0 | 0 | 235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19RCCK | RUTGERS COMMUNITY CENTER KITCHEN RENOVATION | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 303 | HA-D001 |  |  | COMMUNITY CENTER KITCHENETTE, INCLUDING A NEW STOVE AND GAS LINES | 2019 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19RLTV | RANGEL HOUSES SAFE GROUNDS SECURITY INITIATIVE - CCTV | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 300 | HA-M001 |  |  | RANGEL HOUSES CCTV | 2019 | 200 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19STEL | ST NICHOLAS HOUSES ELEVATOR UPGRADE | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 310 | HA-0001 |  |  | UPGRADE ELEVATORS AT ST . NICHOLAS HOUSES | 2019 | 10973 | 0 | 275 | 0 | 0 | 0 | 9700 | 0 | 9975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19VLPR | VLADECK HOUSES: PLAYGROUND REPAVING | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 300 | HA-M001 HA-D001 |  |  | VLADECK HOUSES: PLAYGROUND REPAVING | 2019 | 600 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19WTOC | WISE HOUSES OUTDOOR PLAZA CAMERAS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 307 | HA-D001 |  |  | OUTDOOR PLAZA CAMERAS | 2019 | 275 | 0 | 275 | 0 | 0 | 0 | 0 | 0 | 275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20SISC | STANLEY ISAACS SENIOR CENTER BATHROOM ADA UPGRADE | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 300 | HA-M001 |  |  | STANLEY ISAACS NEIGHBORHOOD CENTER - SENIOR CENTER BATHROOM RENOVATIONS - ADA BATHROOM UPGRADES | 2019 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21DYEL | DYCKMAN HOUSES ELEVATOR REPLACEMENT | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 312 | HA-0001 |  |  | REPLACE ELEVATORS AT DYCKMAN HOUSES | 2019 | 6600 | 0 | 500 | 0 | 6000 | 0 | 0 | 0 | 6500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21MHEL | MELTZER HERNANDEZ HOUSES ELEVATOR REPLACEMENT | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 303 | HA-0001 |  |  | REPLACE ELEVATORS AT MELTZER HERNANDEZ | 2019 | 2295 | 0 | 2400 | 0 | 0 | 0 | 0 | 0 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22SMGR | SMITH HOUSES INSTALLATION OF GAS RISERS #7 | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 303 | HA-0001 |  |  | INSTALLATION OF GAS RISERS #7 | 2019 | 9075 | 0 | 0 | 0 | 0 | 250 | 0 | 8000 | 8250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22TAEL | TAFT HOUSES ELEVATOR REHABILITATION | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 311 | HA-0001 |  |  | ELEVATOE UPGRADES | 2019 | 9075 | 0 | 0 | 0 | 0 | 250 | 0 | 8000 | 8250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22WAGR | WAGNER HOUSES GAS RISER REPLACEMENTS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 311 | HA-0001 |  |  | GAS RISER REPLACEMENT | 2019 | 10230 | 0 | 0 | 0 | 0 | 4000 | 5300 | 0 | 9300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HMFTWASH | ARC FT WASHINGTON SR. CTR Upgrade and Renovation | DEPARTMENT FOR THE AGING BUILDING RECONSTRUCTION | 312 | AG-D001 |  |  | SEPT 2017 PLAN UPGRADE AND RENOVATION 99 FT WASHINGTON AVE NY NY 10032 210K | 2019 | 0 | 0 | 0 | 0 | 210 | 0 | 0 | 0 | 210 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18BOI | Replace boilers at Lehman Village and Wilson Houses | NEIGHBORHOOD REVITALIZATION | 300 | ED-0384 |  |  | REPLACE BOILERS AT LEHMAN VILLAGE AND WILSON HOUSES | 2019 | 0 | 0 | 13200 | 0 | 0 | 0 | 0 | 0 | 13200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18ECC | Renovations at Early Childhood Centers in East Harlem | NEIGHBORHOOD REVITALIZATION | 300 | ED-0384 |  |  | RENOVATIONS AT EARLY CHILDHOOD CENTERS IN EAST HARLEM | 2019 | 0 | 0 | 7700 | 0 | 0 | 0 | 0 | 0 | 7700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18ELV | New Elevators at 335 East 111th Street | NEIGHBORHOOD REVITALIZATION | 300 | ED-0384 |  |  | NEW ELEVATORS AT 335 EAST 111TH STREET | 2019 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18GAS | Install new gas risers at Johnson Houses Install new gas ris | NEIGHBORHOOD REVITALIZATION | 300 | ED-0384 |  |  | INSTALL NEW GAS RISERS AT JOHNSON HOUSES | 2019 | 0 | 0 | 5500 | 0 | 0 | 0 | 0 | 0 | 5500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18ROF | Conduct roof and parapet work at UPACA (Site 5) | NEIGHBORHOOD REVITALIZATION | 300 | ED-0384 |  |  | CONDUCT ROOF AND PARAPET WORK AT UPACA (SITE 5) | 2019 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18VNT | Modernize ventilation systems in 17 East Harlem Developments | NEIGHBORHOOD REVITALIZATION | 300 | ED-0384 |  |  | MODERNIZE VENTILATION SYSTEMS IN 17 EAST HARLEM DEVELOPMENTS | 2019 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NSENDERO | Sendero Verde - 1681 Madison Avenue | NEW FACILITIES | 300 | HD-D021 |  | TO FUND THE REDEVELOPMENT OF THE BLOCK BETWEEN 111TH AND 112TH STREETS, AND PARK AND MADISON AVENUES. A MIXED-USE DEVELOPMENT THAT WILL PROVIDE OVER 650 AFFORDABLE HOUSING UNITS AND COMMUNITY FACILITY SPACE. | A MIXED-USE DEVELOPMENT THAT WILL PROVIDE OVER 650 AFFORDABLE HOUSING UNITS AND COMMUNITY FACILITY SPACE. | 2019 | 0 | 0 | 550 | 0 | 0 | 0 | 0 | 0 | 550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | P-3WAGNER | Wagner Playground, Manhattan | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 |  | WAGNER PLAYGROUND -- TO PROVIDE FUNDING FOR OVERALL PLAYGROUND RENOVATIONS | WAGNER PLAYGROUND -- TO PROVIDE FUNDING FOR OVERALL PLAYGROUND RENOVATIONS | 2019 | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | ACEDOH501 | DOHMH - LIGHTING UPGRADES | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 301 | HL-0082 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | LIGHTING UPGRADES | 2019 | 539 | 421.05 | 69 | 0 | 0 | 0 | 0 | 0 | 490.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | ACEDOH502 | DOHMH - LED LIGHTING UPGRADE | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 301 | HL-0082 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | LED LIGHTING UPGRADE | 2019 | 1456 | 0 | 0 | 410 | 0 | 0 | 0 | 0 | 410 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | ACEDOH701 | DOHMH - DEDICATED CONDENSING HOT WATER HEATER | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 301 | PU-0025 |  |  | DOHMH - DEDICATED CONDENSING HOT WATER HEATER | 2019 | 120 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | CMERECORD | OCME - Records Room Reconfiguration at 421 East 26th St | OCME | 301 | HL-0083 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RECONSTRUCTION OF 4TH FLOOR AT 421 EAST 26TH STREET FOR A NEW RECORDSROOM | 2019 | 458 | 0 | 0 | 108 | 350 | 0 | 0 | 0 | 458 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82ACDOG | DOHMH ANIMAL CARE CENTERS - RECONSTRUCTION OF DOG KENNELS | ANIMAL CARE |  | HL-D001 |  |  | DOHMH ANIMAL CARE CENTERS - RECONSTRUCTION OF DOG KENNELS | 2019 | 250 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82CHRHC | Central Harlem Health Center interior renovation | CLINIC RENOVATION AND REHABILITATION |  | HL-0082 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CENTRAL HARLEM HEALTH CENTER INTERIOR RENOVATION | 2019 | 9500 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82EASTH | EAST HARLEM HEALTH HUB | CLINIC RENOVATION AND REHABILITATION |  | HL-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | EAAT HARLEM HEALTH HUB BUILD OUT OF MAIN BUILDING TO CREATE HUB | 2019 | 600 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82EHRHC | East Harlem Health Center interior renovation | CLINIC RENOVATION AND REHABILITATION |  | HL-0082 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | EAST HARLEM HEALTH CENTER INTERIOR RENOVATION | 2019 | 9000 | 0 | 0 | 1211 | 0 | 1211 | 0 | 0 | 2422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82MACCS | MANHATTAN ANIMAL CARE CENTER SIDEWALK REPLACEMENT | ANIMAL CARE |  | HL-0082 |  |  | MANHATTAN ANIMAL CARE CENTER SIDEWALK REPLACEMENT | 2019 | 339 | 0 | 339 | 0 | 0 | 0 | 0 | 0 | 339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82PHLNB | DOHMH FACILITIES | CLINIC RENOVATION AND REHABILITATION | 300 | HL-0082 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | PUBLIC HEALTH LAB NEW BUILDING | 2019 | 121113 | 294.01 | 0 | 1000 | 0 | 1500 | 0 | 0 | 2794.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82SPCA2 | ANIMAL SHELTER 326 EAST 110 STREET MANHATTAN | CLINIC RENOVATION AND REHABILITATION | 311 | HL-0082 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  |  | 2019 | 914 | 558.68 | 0 | 37 | 0 | 0 | 0 | 0 | 595.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82WASHT | WASHINGTON HEIGHTS HEALTH CENTER FACADE RENOVATION | ADMINISTRATION |  | HL-0082 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | WASHINGTON HEIGHTS HEALTH CENTER FACADE REPAIR PER LOCAL LAW 11 | 2019 | 3234 | 0 | 0 | 1617 | 1617 | 0 | 0 | 0 | 3234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL99ANIC1 | ANIMAL CARE & CONTROL OF NEW YORK CITY | CLINIC RENOVATION AND REHABILITATION | 311 | HL-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RENOVATE GARAGE FACILITY AT 326 EAST 100TH STREET SUPPORT LOCATION | 2019 | 535 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 02200901 | CENTRAL OFFICE: PRIMARY CARE INITIATIVE | ROUTINE RECONSTRUCTION |  | HO-D003 |  | 346 BROADWAY, CSS, 12E | THE PURPOSE OF THIS PROJEC T IS TO RENOVATE PRIMARY CARE INITIATIVE CLINICS THROUGHTOUT THE HHC SYSTEM -CITY WIDE. | 2019 | 1329 | 762.75 | 57 | 750 | 0 | 0 | 0 | 0 | 1569.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 02201805 | LWH: REPLACE COOLING TOWER AND UPGRADES TO CHILLER & BOILER | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 1721-35 AMSTERDAM AVENUE, NEW YORK, NY | REPLACE COOLING TOWER AND UPGRADES TO CHILLER & BOILER AT THE NYC HEALTH + HOSPITALS LOWER WASHINGTON HEIGHTS HEALTH CENTER. | 2019 | 866 | 0 | 866 | 0 | 0 | 0 | 0 | 0 | 866 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 11200912 | BELLEVUE: EMERGENCY PIPE INSTALLATION, 22ND FLOOR | ROUTINE RECONSTRUCTION | 306 | HO-0214 |  | 462 FIRST AVENUE, NEW YORK, NY 10016 | THE FACILITY REQUESTS FUNDING TO REPLACE THE 30 AND 14 INCH CONDENSING PIPING LOCATED ON THE 22ND FLOOR THAT IS OLD, RUSTED AND WEAK AT CERTAIN JOINTS RESULTING IN LEAKS. THE SCOPE OF WORK INCLUDES THE REPLACEMENT OF 70 LF OF 30 INCH AND 150 LF OF 14 INCH PIPES. | 2019 | 577 | 523.82 | 0 | 53 | 0 | 0 | 0 | 0 | 576.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 11201001 | BHC: OR UPGRADE | ROUTINE RECONSTRUCTION | 306 | HO-0214 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 462 FIRST AVENUE, NEW YORK, NY 10016 | UPGRADE OPERATING ROOMS ON THE 11TH FLOOR AT BELLEVUE. | 2019 | 3200 | 2288.34 | 487 | 424 | 0 | 0 | 0 | 0 | 3199.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 11201601 | BELLEVUE: REPLACE TWO INDOOR COOLING TOWERS | ROUTINE RECONSTRUCTION | 306 | HO-0214 |  | 462 FIRST AVENUE, NEW YORK, NY 10016 | REPLACE TWO INDOOR COOLING TOWERS AT BELLEVUE HOSPITAL CENTER. | 2019 | 2033 | 1528.36 | 0 | 505 | 0 | 0 | 0 | 0 | 2033.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 11201705 | BHC: CONSTRUCT NEW CHEMISTRY LABORATORY | ROUTINE RECONSTRUCTION | 306 | HO-0214 |  | 462 FIRST AVENUE, NEW YORK, NY 10016 | BELLEVUE HOSPITAL CENTER: CONSTRUCT NEW CHEMISTRY LABORATORY | 2019 | 886 | 189 | 347 | 350 | 0 | 0 | 0 | 0 | 886 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 11201803 | BHC: EXPAND HEIGHT OF GUARDRAILS IN THE ACB ATRIUM | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 462 FIRST AVENUE, NEW YORK, NY 10016 | EXPAND HEIGHT OF GUARDRAILS IN THE ACB ATRIUM | 2019 | 1046 | 0 | 975 | 71 | 0 | 0 | 0 | 0 | 1046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 11201901 | BHC: CONVERT SPACE TO CREATE 4 PYXIS MEDICATION ROOMS | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 462 FIRST AVENUE, NEW YORK, NY 10016 | CONVERT SPACE TO CREATE 4 PYXIS MEDICATION ROOMS FOR THE INPATIENT PHYCHIATRIC MENTAL HEALTH UNITS AT BELLEVUE HOSPITAL CENTER. | 2019 | 700 | 0 | 636 | 64 | 0 | 0 | 0 | 0 | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 11201903 | BELLEVUE: RENOVATION AND UPGRADE OF TRAUMA SLOTS IN ADULT ED | ROUTINE RECONSTRUCTION |  | HO-M001 |  | 462 FIRST AVENUE, NEW YORK, NY, 10016 | BELLEVUE: RENOVATION AND UPGRADE OF TRAUMA SLOTS IN ADULT ED | 2019 | 0 | 0 | 0 | 325 | 0 | 0 | 0 | 0 | 325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 12201501 | GOUVERNEUR: ROBERTO CLEMENTE CENTER RENOVATION | ROUTINE RECONSTRUCTION | 303 | HO-M001 HO-D003 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 540 EAST 13TH STREET, NEW YORK, NY 10009 | GOUVERNEUR: ROBERTO CLEMENTE CENTER RENOVATION | 2019 | 1000 | 811.16 | 284 | 0 | 0 | 0 | 0 | 0 | 1095.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 12201702 | GHS: INSTALL SECONDARY WATER DISINFECTION SYS-LTACH & SNF | ROUTINE RECONSTRUCTION | 303 | HO-0214 |  | 227 MADISON STREET, NEW YORK, NY 10002 | GOUVERNEUR HEALTHCARE SERVICES, NEW YORK, NY: PURCHASE AND INSTALL A SECONDARY WATER DISINFECTION SYSTEM (AKA COPPER-SILVER IONIZATION SYSTEM) FOR THE LTACH & SNF BUILDINGS. | 2019 | 107 | 0 | 107 | 0 | 0 | 0 | 0 | 0 | 107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 12201801 | GHS: REHABILITATE FACADE - CYCLE 7B AMENDED AND CYCLE 8B | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 227 MADISON STREET, NEW YORK, NY | REHABILITATE FACADE - CYCLE 7B AMENDED AND CYCLE 8B AT GOUVERNEUR HEALTHCARE SERVICES | 2019 | 291 | 246.21 | 45 | 0 | 0 | 0 | 0 | 0 | 291.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 12201804 | JUDSON, REMOVE AND REPLACE FIRE LINE | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 34 SPRING ST, NEW YORK, NY 10012 | REMOVE AND REPLACE FIRE LINE AT JUDSON, A GOTHAM CLINIC | 2019 | 196 | 0 | 196 | 0 | 0 | 0 | 0 | 0 | 196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 12201901 | GHS: ENTRANCE RENOVATION (AIR CURTAIN HEATER INSTALLATIONS) | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 227 MADISON STREET, NEW YORK, NY 10002 | THE SCOPE OF WORK INCLUDES FABRICATION AND INSTALLATION OF FIVE AIR HEATERS TO CREATE AIR CURTAINS AT TWO ENTRANCES AT NYC HEALTH + HOSPITALS / GOUVERNEUR. | 2019 | 130 | 0 | 130 | 0 | 0 | 0 | 0 | 0 | 130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 12201902 | GOUVERNEUR: RENOVATE COURTYARD | ROUTINE RECONSTRUCTION |  | HO-D003 |  | 277 MADISON STREET, NEW YORK, NY 10002 | NA | 2019 | 248 | 0 | 0 | 248 | 0 | 0 | 0 | 0 | 248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13200571 | HARLEM: MURALS REMOVAL AND PRESERVATION | ROUTINE RECONSTRUCTION | 310 | HO-D003 |  | 506 LENOX AVENUE, NEW YORK, N. Y. 10037 | MURALS REMOVAL, PRESERVATION AND RE-INSTALLATION IN LOBBY OF NEW PAVILION AT HARLEM HOSPITAL CENTER | 2019 | 3765 | 2610.66 | 0 | 0 | 303 | 0 | 0 | 0 | 2913.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13200573 | HARLEM: CONSTRUCT NEW PARKING FACILITY | ROUTINE RECONSTRUCTION | 310 | HO-0377 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 506 LENOX AVENUE, NEW YORK, NY 10037 | CONSTRUCT NEW PARKING FACILITY AT HARLEM HOSPITAL CENTER THAT WILL ADD 99 ADDITIOANL CAPACITY. | 2019 | 3500 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13200601 | HARLEM HOUSE RELOCATION AND RENOVATION | ROUTINE RECONSTRUCTION | 310 | HO-C003 |  | WEST 118TH STREET, NEW YORK NY | HARLEM HOUSE PROVIDES COMMUNITY SERVICES FOR PATIENTS WHO REQUIRE PSYCHIATRIC FOLLOW UP TO BE ABLE TO LIVE AND WORK INDEPENDENTLY. THIS PROGRAM IS BEING CONSOLIDATED TO 118TH STREET WHERE THE RENT IS ONLY $2.05/SQ FT COMPARED TO PAYING $24/SQ FT WHERE THE HARLEM HOUSE IS CURRENTLY LOCATED. | 2019 | 945 | 389.46 | 0 | 55 | 0 | 0 | 0 | 0 | 444.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13201101 | HARLEM: RELOCATE SYDENHAM CLINIC FROM 125TH TO 118TH STREET | ROUTINE RECONSTRUCTION |  | HO-D003 HO-0214 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | WEST 118TH STREET, NEW YORK NY | THE FPURPOSE OF THIS PROJECT IS TO RENOVATE SPACE AT 118TH STREET (DCAS BUIDING) IN ORDER TO RELOCATE THE SYDENHAM/RENAISSANCE CLINIC FROM 125TH STREET TO 118TH STREET. SYDENHAM/RENAISSANCE CLINIC IS AN EXTENSION OF HARLEM HOSPITAL CENTER. | 2019 | 2500 | 3027.93 | 166 | 300 | 0 | 0 | 0 | 0 | 3493.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13201301 | HARLEM: RENOVATE POST PARTUM UNIT | ROUTINE RECONSTRUCTION | 310 | HO-D003 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | 506 LENOX AVENUE, NEW YORK, NY 10037 | RENOVATE POST PARTUM UNIT AT HARLEM HOSPITAL CENTER. | 2019 | 600 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13201401 | HARLEM: CONSTRUCT GERIATRICS CENTER | ROUTINE RECONSTRUCTION | 310 | HO-D003 |  | 506 LENOX AVENUE NEW YORK, NY 10037 | CONSTRUCT GERIATRICS CENTER AT HARLEM HOSPITAL CENTER. | 2019 | 3261 | 3131.47 | 0 | 122 | 0 | 0 | 0 | 0 | 3253.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13201501 | HARLEM: UPGRADE VENTILATION SYSTEM IN THE BOILER ROOM | ROUTINE RECONSTRUCTION | 310 | HO-0214 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 506 LENOX AVENUE, NEW YORK, NY 10037 | DESIGN AND INSTALL PROPER VENTILATION FOR BOILER ROOM. HARLEM HOSPITAL CENTER WAS SITED ON TEMPERATURES UNSAFE FOR STAFF, TEMPERATURE IN THE SUMMER EXCEED 140 DEGREES. | 2019 | 300 | 43.2 | 257 | 0 | 0 | 0 | 0 | 0 | 300.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13201502 | HARLEM: UPGRADE ELECTRICAL SYSTEM | ROUTINE RECONSTRUCTION | 310 | HO-0214 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 506 LENOX AVENUE, NEW YORK, NY 10037 | UPGRADE ELECTRICAL SYSTEM AT HARLEM HOSPITAL CENTER TO COMPLY WITH NFPA LIFE SAFETY CODE FOR CRITICAL BRANCH SEPARATION. 95% DRAWINGS ARE COMPLETE AND STOPPED. HHC CONSIDERING IMPLEMENTING EMERGENCY POWER ONLY TO ACHIEVE TYPE 1 SYSTEM (TYPE 1 EES). | 2019 | 8300 | 15180.19 | 238 | 2050 | 1500 | 0 | 0 | 0 | 18968.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13201602 | HARLEM: REHABILITATE THE EXTERIOR FACADE OF MLK BLG - LL 11 | ROUTINE RECONSTRUCTION | 310 | HO-0214 |  | 506 LENOX AVENUE | THEPURPOSE OF THIS PROJECT IS TO REHABILITATE THE EXTERIOR FASCADE OF MILK BUILDING AT HARLEM HOSPITAL CENTER WITH LOCAL LAW 11- FUNDS | 2019 | 15966 | 0 | 1060 | 13218 | 1688 | 0 | 0 | 0 | 15966 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13201603 | HARLEM: WP DECANTING, ONR DEMOLITION, & NEW DATA CENTER | ROUTINE RECONSTRUCTION | 310 | HO-0214 |  | 506 LENOX AVENUE NEW YORK, NY 10037 | THE PURPOSE OF THIS PROJECT IS TO DECANT AND DEMOLISH THE WP ROOM AT HARLEM HOSPITAL CENTER WITH LOCAL LAW 11- FUNDS. | 2019 | 28184 | 124.9 | 499 | 12562 | 12998 | 2000 | 0 | 0 | 28183.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13201701 | HARLEM: CONSTRUCT RESPITE CENTER | ROUTINE RECONSTRUCTION | 310 | HO-D003 |  | 506 LENOX AVENUE, NEW YORK, NY 10037 | RENOVATE SPACE TO CONSTRUCT A RESPITE CENTER FOR FIRST RESPONDERS AT HARLEM HOSPITAL CENTER. | 2019 | 335 | 128.67 | 120 | 87 | 0 | 0 | 0 | 0 | 335.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13201803 | HARLEM: KOUNTZ PAVILION STAIRWELL REHABILITATION | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 506 LENOX AVENUE, NEW YORK, NY 10037 | NYC HEALTH + HOSPITALS ¦ HARLEM: STAIRWELL REHABILITATION IN THE KOUNTZ PAVILION REQUIRED TO CORRECT UNSAFE CONDITIONS. | 2019 | 173 | 0 | 161 | 12 | 0 | 0 | 0 | 0 | 173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13201901 | HARLEM: RENOVATE MP4 SPACE TO CREATE A DIALYSIS UNIT | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 506 LENOX AVENUE, NEW YORK, NY 10002 | THE PROJECT SCOPE IS TO RENOVATE THE MP DIALYSIS UNIT AT NYC HEALTH + HOSPITALS / HARLEM. | 2019 | 450 | 0 | 0 | 0 | 450 | 0 | 0 | 0 | 450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13201902 | HARLEM HOSPITAL: FIRE ALARM SYSTEM UPGRADE | ROUTINE RECONSTRUCTION |  | HO-M001 |  |  | HARLEM HOSPITAL (506 LENOX AVENUE, MANHATTAN), UPGRADE OF THE FIRE ALARM SYSTEM THROUGHOUT THE HOSPITAL CAMPUS | 2019 | 0 | 0 | 0 | 88 | 0 | 0 | 0 | 0 | 88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 18201801 | SYDENHAM: ERODED WALL REPLACEMENT | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 264 WEST 118TH STREET, NEW YORK, NY 10026 | SYDENHAM, A GOTHAM HEALTH CENTER: RECONSTRUCT EXTERIOR WALL. | 2019 | 91 | 0 | 83 | 8 | 0 | 0 | 0 | 0 | 91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37200702 | METROPOLITAN: RENOVATE SPACE FOR DIALYSIS UNIT | ROUTINE RECONSTRUCTION | 311 | HO-0214 |  | 1901 FIRST AVENUE, NEW YORK, NY 10038 | RELOCATE RENAL DIALYSIS UNIT FROM THE 13TH FLOOR TO THE 14TH FLOOR CURRENTLY OCCUPIED BY THE PULMONARY LAB. THE RELOCATED/RENOVATED UNIT WILL HAVE FOUR ADDITIONAL DIALYSIS STATIONS. | 2019 | 2000 | 1231.84 | 0 | 0 | 0 | 194 | 0 | 0 | 1425.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37201301 | MHC: COMPLETE RENOVATION OF SIXTH FLOOR 6C OPD | ROUTINE RECONSTRUCTION | 311 | HO-D003 |  | 1901 FIRST AVENUE, NEW YORK, NY 10029 | RENOVATE/FURNISH CLINIC SPACE THAT IS CURRENTLY IN MAJOR DISREPAIR ONTHE 6TH FLLOR (6C) OPD BUILDING AT METROPOLITAN HOSPITAL CENTER. RENOVATIONS WILL ADDRESS OR IMPROVE PATIENT FLOW/OPERATIONS. THIS SERVICE INCLUDES: AUDIOLOGY, CARDIAC, DIABETES CARE, ENDOCRINOLOGY, OPHTHALMOLOGY AND GI. | 2019 | 2420 | 183.95 | 1000 | 1236 | 0 | 0 | 0 | 0 | 2419.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37201401 | MHC: INSTALL PERIMETER GATE/FENCING & SIGNAGE-LANDSCAPING | ROUTINE RECONSTRUCTION | 311 | HO-D003 |  | 1901 FIRST AVENUE, NEW YORK , NY10029 | THE PURPOSE OF THIS PROJECT IS TO INSTALL PERIMETER FENCING AND A GATE TO PROVIDE A COMPREHENSIVE AND COMPLETE ENCLOSURE TO THE MAIN CAMPUS AT METROPOLITAN HOSPITAL CENTER IN ORDER TO IMPROVE THE HOSPITAL'SSECURITY. IN ADDITION, THE PROJECT SCOPE INCLUDES LANDSCAPING TO BEAUTIFY THE HOSPITAL SURROUNDINGS. | 2019 | 0 | 454.43 | 0 | 445 | 0 | 0 | 0 | 0 | 899.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37201501 | MHC: ESTABLISH A COMPREHENSIVE LBGT FAMILY HEALTH CENTER | ROUTINE RECONSTRUCTION | 311 | HO-D003 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 1901 FIRST AVNUE, NEW YORK, NY 10029 | RENOVATE AND OUTFIT SPACE ON THE FIRST FLOOR OF METROPOLITAN HOSPITAL'S OURPATIENT BUILDING INTO A STATE-OF-THE-ART LGBT COMPREHENSIVE FAMILY HEALTH CENTER. | 2019 | 2100 | 248.88 | 1851 | 0 | 0 | 0 | 0 | 0 | 2099.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37201601 | MHC: EXTERIOR FACADE RESTORATION CAMPUS-WIDE | ROUTINE RECONSTRUCTION | 311 | HO-0214 |  | 1901 FIRST AVENUE, NEW YORK, NY 10029 | RESTORE EXTERIOR FACADE ON THE CAMPUS OF METROPOLITAN HOSPITAL CENTERTO COMPLY WITH LOCAL LAW 11 REGULATIONS. | 2019 | 399 | 0 | 399 | 0 | 0 | 0 | 0 | 0 | 399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 67200901 | COLER: RENOVATE THE NURSING FACILITY DAY ROOM | ROUTINE RECONSTRUCTION |  | HO-D003 |  | 900 MAINS STR. ROOSEVELT NEW YORK , NY 10044 | THE PURPOSE OF THIS PROJECT IS TO RENOVATE THE NURSING FACILITY DAY ROOM AT COLER SPECIIALITY HOSPITAL & NUSING FACILITY. | 2019 | 300 | 3.8 | 0 | 0 | 296 | 0 | 0 | 0 | 299.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 67201070 | COLER: UPGRADE SPRINKLER SYSTEM | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 900 MAIN STREET, ROOSVELT ISLAND, NY 10044 | PROVIDE THE PLANNING, PRE-CONSTRUCTION, ARCHITECTURAL AND ENGINEERINGDESIGN SERVICES, CONSTRUCTION, CONSTRUCTION MANAGEMENT AND PROJECT MANAGEMENT SERVICES NECESSARY FOR THE DESIGN AND INSTALLATION OF AN AUTOMATIC SPRINKLER SYSTEM AS REQUIRED BY THE AMENDMENT OF FEDERAL REGULATION BY THE CENTERS FOR MEDICARE AND MEDICAID SERVICES (CMS). | 2019 | 30497 | 28439.49 | 0 | 0 | 400 | 0 | 0 | 0 | 28839.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | ACEHHC403 | HARLEM HOSPITAL CENTER ENERGY UPGRADE | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 301 | HO-0214 |  |  | HARLEM HOSPITAL CENTER ACE PROGRAM | 2019 | 10682 | 10681.4 | 176 | 0 | 0 | 0 | 0 | 0 | 10857.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | ACEHHC406 | HHC- BELLEVUE HOSPITAL CHILLERS | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 302 | PU-0025 HO-0214 |  |  | CHILLERS | 2019 | 0 | 3794.75 | 589 | 109 | 0 | 0 | 0 | 0 | 4492.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | ACEHHC408 | HHC Coler Hospital Boiler Replacement | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 311 | PU-0025 HO-0214 |  |  | INSTALL NEW LPS BOILER PLANT & ALL ASSOCIATED ANCILLARY EQUIPMENT. INSTALL NEW INDEPENDENT DOMESTIC HOT WATER BOILERS. CONVERT HIGH PRESSURE SYS TO LOW PRESSURE SYS, INSTALL NEW GAS SERVICE & FUEL OIL STORAGE. | 2019 | 0 | 18189.06 | 0 | 1905 | 0 | 0 | 0 | 0 | 20094.06 | 1260.02 | 0 | 0 | 0 | 0 | 0 | 0 | 1260.02
20190425 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | HRLM/MJR | HARLEM HOSPITAL MAJOR MODERNIZATION | MAJOR OR PARTIAL HOSPITAL RECONSTRUCTION | 300 310 | HO-0377 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 506 LENOX AVENUE, NEW YORK, NY 10037 | HARLEM HOSPITAL CENTER - MAJOR MODERNIZATION | 2019 | 279098 | 290955.54 | 200 | 293 | 500 | 0 | 0 | 0 | 291948.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | SAND1117 | BHC: MEP MITIGATION | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 462 FIRST AVENUE, NEW YORK, NY 10016 | MEP MITIGATION PROJECT TO ENSURE THAT NYC HEALTH + HOSPITALS ¦ BELLEVUE WILL BE PROTECTED FROM FUTURE HURRICANE STORMS LIKE SANDY. FUNDS TOBE USED FOR THE RELOCATION OF SWITHGEAR AND AIR HANDKLING UNITS TO A HIGHER FLOOR, | 2019 | 15914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11314 | 4600 | 0 | 0 | 0 | 0 | 15914
20190425 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | SAND11B | BELLEVUE RECONSTRUCTION AS A RESULT OF SANDY | ROUTINE RECONSTRUCTION | 306 | HO-0214 |  | 462 FIRST AVENUE, NEW YORK, NY 10016 | RECONSTRUCTION OF BELLEVUE HOSPITAL CENTER NECESSITATED BY HURRICANE SANDY. | 2019 | 67500 | 5239.69 | 0 | 0 | 0 | 504 | 0 | 0 | 5743.69 | 54219.03 | 0 | 5183 | 1728 | 0 | 0 | 0 | 61130.03
20190425 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | SAND3701 | MHC: CONSTRUCT A CONFERENCE AND TRAINING CTR - SANDY CTGY E | ROUTINE RECONSTRUCTION | 311 | HO-0214 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 1901 FIRST AVENUE, NEW YORK, NY 10029 | RECONSTRUCTION OF METROPOLITAN HOSPITAL CENTER NECESSITATED BY HURRICANE SANDY. FEMA CATEGORY E: BUILDINGS AND EQUIPMENT (PERMANENT WORK). REPLACE CONFERENCE AND TRAINING FACILITIES LOST IN DRAPER HALL DUE TO STORM DAMAGES CAUSED BY HURRICANE SANDY. | 2019 | 3500 | 329 | 0 | 14 | 0 | 0 | 0 | 0 | 343 | 3098.85 | 50 | 0 | 0 | 0 | 0 | 0 | 3148.85
20190425 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | SAND37B | MHC RECONSTRUCTION AS A RESULT OF SANDY - CATEGORY B | ROUTINE RECONSTRUCTION | 311 | HO-0214 |  | 1901 FIRST AVENUE, NEW YORK, NY 10029 | RECONSTRUCTION OF METROPOLITAN HOSPITAL CENTER NECESSITATED BY HURRICANE SANDY. FEMA CATEGORY B: EMERGENCY PROTECTIVE MEASURES (EMERGENCYWORK). | 2019 | 2500 | 156.38 | 0 | 0 | 0 | 0 | 0 | 0 | 156.38 | 1512.66 | 0 | 613 | 205 | 0 | 0 | 0 | 2330.66
20190425 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | SAND67B | COLER RECONSTRUCTION AS A RESULT OF SANDY - CATEGORY B | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 900 MAIN STREET, ROOSEVELT ISLAND, NY 10044 | RECONSTRUCTION OF COLER-GOLDWATER SPECIALTY HOSPITAL AND NURSING FACILITY - COLER CAMPUS NECESSITATED BY HURRICANE SANDY. FEMA CATEGORY B: EMERGENCY PROTECTIVE MEASURES (EMERGENCY WORK). | 2019 | 45000 | 2057 | 0 | 0 | 0 | 379 | 0 | 0 | 2436 | 20486.82 | 0 | 5308 | 1769 | 0 | 0 | 0 | 27563.82
20190425 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | SAND67E | COLER RECONSTRUCTION AS A RESULT OF SANDY - CATEGORY E | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 900 MAIN STREET, ROOSEVELT ISLAND, NY 10044 | RECONSTRUCTION OF COLER-GOLDWATER SPECIALTY HOSPITAL AND NURSING FACILITY - COLER CAMPUS NECESSITATED BY HURRICANE SANDY. FEMA CATEGORY E: BUILDINGS AND EQUIPMENT (PERMANENT WORK). | 2019 | 60000 | 1781.86 | 0 | 0 | 0 | 0 | 0 | 0 | 1781.86 | 16084.43 | 0 | 6572 | 2188 | 0 | 0 | 0 | 24844.43
20190425 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | ACEDEP405 | BOWERY BAY ECM #8 | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 301 | PU-0025 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | BOWERY BAT | 2019 | 604 | 0 | 0 | 0 | 0 | 604 | 0 | 0 | 604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | ACEDEP502 | DEP - WARDS ISLAND SHAFT MIXERS | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 300 | WP-0112 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | WARDS ISLAND SHAFT MIXERS | 2019 | 6568 | 6983.85 | 61 | 0 | 0 | 0 | 0 | 0 | 7044.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | ACEDEP702 | DEP - WARD ISLAND HEATING PLANT LOW PRESSURE BOILERS | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 301 | PU-0025 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | DEP - WARDS ISLAND WWTP HEATIN PLAN UPGRADE - LOW PRESSURE BOILERS | 2019 | 5865 | 0 | 5865 | 0 | 0 | 0 | 0 | 0 | 5865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | C260102B | Betterment Cost for WM replacement, 2nd Ave Subway, 96th st. | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 308 311 | WM-0006 SE-0200M EP-0007 |  |  | BETTERMENT COST FOR WM REPLACEMENT, 2ND AVE SUBWAY, 96TH ST. STATION (NYC TRANSIT CONTRACT NO. C-2601-2B | 2019 | 2216 | 0 | 2216 | 0 | 0 | 0 | 0 | 0 | 2216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | EASTSIDRS | EAST SIDE COASTAL RESILIENCY PROJECT AT EAST RIVER PARK | PLANT UPGRADING AND RECONSTRUCTION | 300 | WP-0112 |  |  | DESIGN & CONSTRUCTION OF THE EAST SIDE COASTAL RESILIENCY PROJECT AT EAST RIVER PARK, MANHATTAN. DRAINAGE IMPROVEMENTS TO FLOODPROOF REGULATORS & MANHOLES, STORAGE TANK, INTERCEPTOR GATES, OUTFALL SLUICE GATE, CONVEYANCE IMPROVEMETNS, AND 25 MGD PUMP STATION. | 2019 | 178000 | 0 | 0 | 0 | 0 | 14368 | 153000 | 0 | 167368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | HUDSONYDS | Reconstruction of Water and Sewers @ Hudson Yards | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 304 | SE-0002M WM-0001 EP-0007 |  |  | IMPROVEMENTS TO WATER AND SEWER LINES AT CURRENT LOCATION OF HUSDON RAIL YARDS, IN COJUCTION WITH LARGER EEONOMIC DEVELOPMENT PROJECT. | 2019 | 34290 | 0 | 0 | 0 | 0 | 34290 | 0 | 0 | 34290 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | MED-NEW | CORE WM AREA CONTRACT, MANHATTAN | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 300 | WM-0001 |  |  | RECONSTRUCTION OF WATER MAINS, MANHATTAN | 2019 | 30000 | 0 | 0 | 0 | 0 | 12000 | 5000 | 3000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-111-L | RECONSTRUCTION OF PRIMARY TANKS AT NORTH RIVER WPCP | PLANT UPGRADING AND RECONSTRUCTION | 300 309 | WP-0112 |  | WEST 135TH STREET & 12TH AVENUE, MANHATTANVILLE STSTION, NEW YORK, N.Y. 10027 | RECONSTRUCTION OF PRIMARY TANKS AT NORTH RIVER WPCP | 2019 | 38154 | 0 | 0 | 0 | 3700 | 0 | 0 | 51750 | 55450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-115-L | RECONSTRUCT POWER DISTRIBUTION EQUIPMENT @ NORTH RIVER WWTP | PLANT UPGRADING AND RECONSTRUCTION | 300 309 | WP-0112 |  | 135TH ST., & 12TH AVENUE, MAHNATTANVILLE STATION, N.Y., N.Y. 10027 | RECONSTRUCT POWER DISTRIBUTION EQUIPMENT @ NORTH RIVER WWTP | 2019 | 36505 | 0 | 2842 | 0 | 0 | 1500 | 0 | 46500 | 50842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-117-L | RECONST OF FIRE PROTECTION SYSTEM @ THE NORTH RIVER WWTP | PLANT UPGRADING AND RECONSTRUCTION | 300 309 | WP-0112 |  | 135TH STREET AND 12TH AVENUE, MANHATTANVILLE STATION, N.Y, N.Y. 10027 | RECONSTRUCTION OF FIRE PROTECTION SYSTEM @ THE NORTH RIVER WWTP | 2019 | 3100 | 0 | 0 | 300 | 0 | 1500 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-120-L | RECONSTRUCT WEST ODOR CONTROL @ NORTH RIVER WWTP | PLANT UPGRADING AND RECONSTRUCTION | 300 | WP-0112 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 135TH STREET & 12TH AVENUE, MANHATTANVILLE STATION, N.Y,.N.Y. 10027 | RECONSTRUCT WEST ODOR CONTROL @ NORTH RIVER WWTP | 2019 | 8839 | 0 | 0 | 0 | 0 | 0 | 0 | 13000 | 13000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-124 | RECONSTRUCT DIGESTER GAS SYSTEM AT NORTH RIVER WPCP | PLANT UPGRADING AND RECONSTRUCTION | 300 | WP-0112 |  |  | RECONSTRUCT DIGESTER GAS SYSTEM AT NORTH RIVER WPCP | 2019 | 15000 | 0 | 0 | 1500 | 1500 | 15000 | 0 | 0 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-131-L | RECONSTRUCTION OF MAIN HYDRAULIC SYSTEM @ NORTH RIVER WWTP | PLANT UPGRADING AND RECONSTRUCTION | 300 | WP-0112 |  | 725 W. 135TH STREET, NEW YORK, N.Y. 10031 | REMOVE EXISTING MAIN HYDRAULIC SYSTEM AND INSTALL TEN (10) INDIVIDUALACTUATORS FOR THE SIX (6) SCREENING SLUICE GATES , AND FOUR (4) FOREBAY GATES. THIS SCOPE INCLUDES NEW PLC, REWIRING ABOVE FLOOD LEVEL PLIAN, PLC RELAY BACKUP BOARDS AND MANUAL OPERATION OPTION. | 2019 | 5665 | 0 | 4915 | 0 | 0 | 0 | 0 | 0 | 4915 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-134-L | RECONS (18) UPS SYSTEM FOR EMERGENCY LIGHTING @ NORTH RIVER | PLANT UPGRADING AND RECONSTRUCTION | 300 | WP-0112 |  | CORNER OF WEST 135TH STREET AND 12TH AVENUE, MANHATTANVILLE STATION ,NEW YORK, N.Y. 10027 | RECONSTRUCTION OF THE UPS SYSTEM FOR THE EMERGENCY LIGHTING AT THE NORTH RIVER WWTP. REMOVAL OF ALL THE EXISTING EIGHTEEN (18) UPS AND BATTERIES FOR THE EMERGENCY LIGHTING AND INSTALL EIGHTEEN (18) NEW UPS AND BATTERIES FOR THE EMERGENCY LIGHTING. | 2019 | 2050 | 100 | 1782 | 0 | 0 | 0 | 0 | 0 | 1882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-33 | PROCESS CONTROL | CONSENT DECREE UPGRADING AND CONSTRUCTION | 399 | WP-0164 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | NA |  | 2019 | 146790 | 191244.57 | 374 | 0 | 0 | 0 | 0 | 0 | 191618.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-99-L | REHAB NORTH RIVER INFLUENT/EFFUENT GATES & BAR SCREENS | PLANT UPGRADING AND RECONSTRUCTION | 300 309 | WP-0112 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | RECONSTRUCTION OF SCREEN CHANNEL INFLUENT GATES AT NORTH RIVER WPCP | 2019 | 8200 | 0 | 0 | 0 | 1200 | 3000 | 0 | 0 | 4200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-COGEN | NORTH RIVER WWTP COGENERATION AND ELECTRIFICATION | PLANT COMPONENT STABILIZATION | 300 309 | WP-0164 PU-0025 |  |  | BASED ON THE FEBRUARY 2012 INVESTMENT GRADE FEASIBILITY STUDY FOR COGENERATION AT THE NORTH RIVER WWTP IT HAS BEEN IDENTIFIED THAT ELECTRIFICATION OF THE PLANT AND INSTALLATION OF COGENERATION FACILITIES SHOULD BE PURSUED TO IMPROVE OPERATIONS AND RELIABILITY, REDUCE GREENHOUSE GAS EMISSIONS, AND PROVIDE COST EFFECTIVE SOLUTIONS OVER THE EXISTING ENGINE DRIVEN PUMP AND BLOWER SYSTEMS. THE MOST COST EFFECTIVE ALTERNATIVE FOR COGENERATION AT THE NORTH RIVER WWTP IS THE 10 MW COGENERATION | 2019 | 319977 | 258926.04 | 9941 | 21699 | 0 | 0 | 0 | 0 | 290566.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-STRUCT | STRUCTURAL IMPROVEMENTS AT NORTH RIVER WPCP | PLANT UPGRADING AND RECONSTRUCTION | 300 309 | WP-0164 |  |  | STRUCTURAL IMPROVEMENTS TO THE ROOF, INTERMEDIATE STRUCTURE AND UNDERDECK OF THE NORTH RIVER WPCP | 2019 | 360000 | 39093.36 | 1500 | 0 | 0 | 0 | 30000 | 285000 | 355593.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | PINX10336 | REPLMT OF WATER MAIN WEST 158 STREET | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 312 | WM-0001 |  |  | REPLMT OF WATER MAIN WEST 158 STREET | 2019 | 338 | 0 | 338 | 0 | 0 | 0 | 0 | 0 | 338 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-278 | PARK DRIVE EAST | PLANT UPGRADING AND RECONSTRUCTION | 300 | WP-0269 |  | PARK DRIVE EAST | PARK DRIVE EAST | 2019 | 5000 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-313 | RECONSTRUCTION OF 235TH STREET PUMPING STATION | PLANT UPGRADING AND RECONSTRUCTION | 300 | WP-0269 |  |  | RECONSTRUCTION OF 235TH STREET PUMPING STATION - MANHATTAN | 2019 | 5750 | 950 | 0 | 0 | 0 | 0 | 3500 | 0 | 4450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-324 | RECONSTRUCTION OF CANAL STREET PUMPING STATION, MANHATTAN | PLANT UPGRADING AND RECONSTRUCTION | 300 | WP-0269 |  | IN FRONT OF 417 CANAL STREET AT VARICK STREET, MANHATTAN, NEW YORK 10013 | RECONSTRUCTION OF CANAL STREET PUMPING STATION, MANHATTAN, NEW YORK | 2019 | 5200 | 0 | 0 | 0 | 0 | 1000 | 5000 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDNR | STORM MITIGATION WORK ATTHE NORTH RIVER WPCP | PLANT UPGRADING AND RECONSTRUCTION | 300 309 | WP-0164 |  |  | INSTALLATION AND CONSTRUCTION OF STORM MITIGATION WORK AT THE NORTH RIVER WATER POLLUTION CONTROL PLANT | 2019 | 3000 | 500 | 0 | 0 | 0 | 0 | 0 | 2574 | 3074 | 8721.28 | 0 | 0 | 0 | 0 | 0 | 12520 | 21241.28
20190425 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEBLM01 | Reconstruction of existing sewers from back log in Manhattan | REPLACEMENT OF CHRONICALLY FAILING COMPONENTS | 300 | SE-0002M |  |  | RECONSTRUCTION OF EXISTING SEWERS FROM BACK LOG IN MANHATTAN | 2019 | 9500 | 0 | 0 | 0 | 0 | 9500 | 0 | 0 | 9500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEN002179 | Sewer replace in Amsterdam Ave btw W 125 & 126 st (HWPEDSF5) | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 309 | SE-0002M |  |  | COMBINED SEWER REPLACEMENT IN AMSTERDAM AVENUE BETWEEN W. 125TH STREET AND W. 126TH STREET | 2019 | 712 | 0 | 0 | 712 | 0 | 0 | 0 | 0 | 712 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | SHAFT21 | RECONSTRUCTION OF SHAFT 21, MANHATTAN, Cont., 602 | FACILITY PURCHASES AND RECONSTRUCTION | 303 | EP-0006 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES |  |  | 2019 | 29116 | 8675.62 | 300 | 0 | 0 | 0 | 0 | 0 | 8975.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WFF-CPR | WATER EFICIENCY UPGRADES AT CENTRAL PARK RECIRCULATION | WATER FOR THE FUTURE | 300 | EP-0009 |  |  | WATER EFFICIENCY UPGRADES AT CENTRAL PARK RECIRCULATION | 2019 | 14246 | 0 | 0 | 7123 | 7123 | 0 | 0 | 0 | 14246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-279-L | INSTALLATION OF EMERGENCY GENERATORS AT WARDS ISAND WPCP | PLANT UPGRADING AND RECONSTRUCTION | 300 | WP-0112 |  | WARDS ISLAND, NEW YORK, N.Y. 10035 | INSTALLATION OF EMERGENCY GENERATORS AT WARDS ISLAND WPCP | 2019 | 96500 | 847.3 | 0 | 0 | 0 | 0 | 0 | 74000 | 74847.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-280-L | RECONSTRUCTION OF MAN/BR GRIT SCREENS AT WARDS ISLAND WPCP | PLANT UPGRADING AND RECONSTRUCTION | 300 311 | WP-0112 |  | WARDS ISLAND, NEW YORK, N.Y. 10035 | RECONSTRUCTION OF MAIN/BR GRIT SCREENS AT WARDS ISLAND WPCP | 2019 | 18979 | 18128.82 | 1589 | 0 | 0 | 0 | 0 | 0 | 19717.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-281-L | RECONSTRUCTION OF (39) FINAL TANKS AT WARDS ISLAND | PLANT UPGRADING AND RECONSTRUCTION | 300 311 | WP-0112 |  | WARDS ISLAND, NEW YORK, N.Y. 10035 | RECONSTRUCTION OF (39) FINAL TANKS AT WARDS ISLAND WPCP | 2019 | 87240 | 138018.13 | 3953 | 0 | 0 | 0 | 0 | 0 | 141971.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-284-L | RECONSTRUCTION OF PRIMARY TANKS AT WARDS ISLAND WPCP | PLANT UPGRADING AND RECONSTRUCTION | 300 311 | WP-0112 |  | WARDS ISLAND NEW YORK, N.Y 10035 | RECONSTRUCTION OF PRIMARY TANKS AT WARDS ISLAND WPCP | 2019 | 35633 | 4894.58 | 0 | 0 | 0 | 4000 | 0 | 35000 | 43894.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-285-L | RECONSTRUCT BOILER AT WARDS ISLAND WPCP | PLANT UPGRADING AND RECONSTRUCTION | 300 311 | WP-0112 |  | WARDS ISLAND NEW YORK , N.Y. 10035 | RECONSTRUCT BOILER AT WARDS ISLAND WPCP | 2019 | 72244 | 5293.04 | 0 | 128000 | 0 | 0 | 0 | 0 | 133293.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-292-L | RECONSTRUCTION OF POWER DISTRIBUTION @ THE WARDS ISLAND WWTP | PLANT UPGRADING AND RECONSTRUCTION | 300 311 | WP-0112 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | WARDS ISLAND , N.Y., N.Y. 10035 | RECONSTRUCTION OF POWER DISTRIBUTION @ THE WARDS ISLAND WWTP | 2019 | 57098 | 8880.6 | 0 | 0 | 7750 | 0 | 0 | 52973 | 69603.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-295-L | REPLACE DEWATERING ODOR CONTROL EQUIPMENT @ WARDS ISLD. WWTP | PLANT UPGRADING AND RECONSTRUCTION | 300 311 | WP-0112 |  | WARDS ISLAND, NEW YORK, N.Y. 10035 | REPLACE DEWATERING ODOR CONTROL EQUIPMENT @ WARDS ISLD. WWTP | 2019 | 16777 | 183.89 | -19 | 0 | 10000 | 0 | 0 | 0 | 10164.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-298-B | CONSULTANT DESIGN FOR CONVERSION OF SHARON DEMO @ WARDS ISL | BIOLOGICAL NUTRIENT REMOVAL | 300 | WP-0285 |  | WARDS ISLAND WPCP - WARDS ISLAND, N.Y. 10035 | CONSULTANT DESIGN FOR THE CONVERSION OF THE SHARON DEMONSTRATION FACILITY AT THE WARDS ISLAND WASTEWAER TREATMENT FACILITY TO AN ANAMMOX MOVING BED BIOLOGICAL REACTOR (MBBR) PROCESS. | 2019 | 57276 | 4738.8 | 0 | 0 | 0 | 0 | 40100 | 0 | 44838.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-305 | RECONSTRUCTION OF FENDER @ WARDS ISLAND WPCP | PLANT UPGRADING AND RECONSTRUCTION | 300 | WP-0112 |  |  | RECONSTRUCTION OF FENDER @ WARDS ISLAND WPCP | 2019 | 12000 | 0 | 0 | 0 | 0 | 12000 | 0 | 0 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-307-L | RECONSTRUCTION OF SLUDGE FEED LINES @ WARDS ISLAND WWTP | PLANT UPGRADING AND RECONSTRUCTION | 300 | WP-0112 |  | WARDS ISLAND, NEW YORK 10035 | RECONSTRUCTION OF THE SLUDGE TRANSFER LINES BETWEEN THE SLUDGE STORAGE BUILDING AND DEWATERING BUILDING USING CLOSED--IN-PLACE-PIPING METHOD AND THE REPLACEMENT OF ALL ASSOCIATED PLUG VALVES AT THE WARDS ISLAND WWTP | 2019 | 4831 | 0 | 3679 | 0 | 0 | 0 | 0 | 0 | 3679 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-EXP | INTERIM FAC & UPGRADING AT WARDS ISLAND WPCP | PLANT COMPONENT STABILIZATION | 311 | WP-0103 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | MANHATTAN | THE FINAL DESIGN FOR WARDS ISLAND EXPANSION | 2019 | 1198376 | 519158.16 | 4682 | 0 | 0 | 0 | 0 | 0 | 523840.16 | 30455.42 | 0 | 0 | 0 | 0 | 0 | 0 | 30455.42
20190425 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | P-300HRP2 | HUDSON RIVER PARK - Gansevoort MOU | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 301 302 304 | P-1246 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES |  | HUDSON RIVER PARK - GANSEVOORT MOU | 2019 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | PIER36 | Pier 36 Structural Rehab | GARAGES AND FACILITIES | 303 | PU-0200 |  |  | CAPITAL REHAB/REPLACEMENT OF PILES, PILE CAPS, SLAB, TOPPING | 2019 | 108594 | 0 | 0 | 108594 | 0 | 0 | 0 | 0 | 108594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-264M | Manhattan 26th St Manhattan Borough Shop Roof Replacement | GARAGES AND FACILITIES | 300 | S-0136 |  |  | REPLACE ROOF | 2019 | 2000 | 165.71 | 2302 | 25 | 0 | 0 | 0 | 0 | 2492.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-380C | Bronx 7/8 Garage Boiler Replacement | GARAGES AND FACILITIES | 301 | S-0136 |  |  | REPLACE BOILER | 2019 | 1682 | 0 | 1256 | 126 | 0 | 0 | 0 | 0 | 1382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-380E | Manhattan 3 Garage HVAC System Rehabilitation | GARAGES AND FACILITIES | 303 | S-0136 |  |  | HVAC SYSTEM REHAB | 2019 | 1133 | 0 | 894 | 89 | 0 | 0 | 0 | 0 | 983 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-385E | MANHATTAN 4/4A/7 GARAGE GLASS FACADE REHABILITATION | GARAGES AND FACILITIES | 304 307 | S-0136 |  |  | REPLACEMENT OF MAJOR SECTIONS OF GLASS FACADE AND PERMANENT INSTALLATION OF SAFETY BARRIERS | 2019 | 1365 | 448.86 | 606 | 728 | 0 | 0 | 0 | 0 | 1782.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-432 | MANHATTAN 44 BEAVER ST REHABILITATION | GARAGES AND FACILITIES | 301 | S-0136 |  |  | HCF RECONSTRUCTION AT 44 BEAVER ST | 2019 | 3075 | 325 | 62 | 802 | 0 | 0 | 0 | 0 | 1189 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-435 | Manhattan 11 2496 Second Ave Rehab & Building Addition | GARAGES AND FACILITIES | 300 | S-0136 |  |  | REHABILITATION OF EXISTING STRUCTURE AND CONSTRUCTION OF ONE STORY ADDITION | 2019 | 20683 | 0 | 30046 | 0 | 0 | 0 | 0 | 0 | 30046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-437 | MANHATTAN 44 BEAVER ST SPRINKLER SYSTEM REPLACEMENT | GARAGES AND FACILITIES | 301 | S-0136 |  |  | INSTALLATION OF SPRINKLERS THROUGHOUT 44 BEAVER STREET | 2019 | 2500 | 80.44 | 608 | 1003 | 10037 | 0 | 0 | 0 | 11728.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-440A | Bronx 7/8 Garage Sidewalk Grating | GARAGES AND FACILITIES | 312 | S-0136 |  |  | GRATING REPLACEMENT | 2019 | 64 | 0 | 65 | 10 | 0 | 0 | 0 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-441 | MANHATTAN 4/4A/7 GARAGE Fireproofing & Exterior Completion | GARAGES AND FACILITIES | 304 307 | S-0136 |  |  | W57TH STREET GARAGE FIREPROOFING AND EXTERIOR COMPLETION | 2019 | 392 | 1575.49 | 121 | 0 | 0 | 0 | 0 | 0 | 1696.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-441B | Manhattan 4/4A/7 Garage Broom Wash Drainage | GARAGES AND FACILITIES | 304 307 | S-0136 |  |  | ADDITION OF CATCH BASIN, SUMP PUMPS, CURBS AND SLAB REHABILITATION. | 2019 | 1048 | 0 | 196 | 712 | 0 | 0 | 0 | 0 | 908 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-441S | MANHATTAN 4/4A/7 GARAGE SPRINKLER SYSTEM UPGRADES | GARAGES AND FACILITIES | 304 307 | S-0136 |  |  | EXPANSION AND UPFRADES OF SPRINKLER SYSTEM | 2019 | 1633 | 131.54 | 547 | 0 | 0 | 0 | 0 | 0 | 678.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-447 | MANHATTAN 44 BEAVER ST ELEVATORS | GARAGES AND FACILITIES | 301 | S-0136 |  |  | REPLACE ELEVATORS | 2019 | 3903 | 0 | 350 | 2000 | 0 | 0 | 0 | 0 | 2350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-464A | Bronx 7/8 Garage Roof Replacement | GARAGES AND FACILITIES | 312 | S-0136 |  |  | ROOF REPLACEMENT | 2019 | 2400 | 100 | 181 | 3186 | 0 | 0 | 0 | 0 | 3467 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-464D | Manhattan Henry St Roof Replacement | GARAGES AND FACILITIES | 303 | S-0136 |  |  | ROOF REPLACEMENT | 2019 | 1325 | 0 | 0 | 1100 | 0 | 0 | 0 | 0 | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-464E | Manhattan 8 215th St Garage Roof and Masonry Replacement | GARAGES AND FACILITIES | 303 | S-0136 |  |  | ROOF AND MASONRY REPLACEMENT | 2019 | 2300 | 0 | 0 | 0 | 0 | 660 | 4300 | 0 | 4960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S195-228E | Manhattan West 55th Salt Shed gate and related work | GARAGES AND FACILITIES | 304 307 | S-0195 |  |  | DESIGN OF NEW TRI-FOLD GATE FOR WEST 55TH SALT SHED M 4/4A/7 | 2019 | 722 | 178.93 | 9 | 493 | 0 | 0 | 0 | 0 | 680.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S236-335A | MANHATTAN 6/6A/8 GARAGE at 545 EAST 73 STREET | GARAGES AND FACILITIES | 306 308 | S-0236 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | CONSTRUCTION OF A NEW DSNY GARAGE COMPLEX SERVING MANHATTAN DISTRICTS6, 8, AND 8A. THIS PROJECT IS 100% CITY FUNDED, NON-EXEMPT. | 2019 | 200000 | 1027.52 | -133 | 0 | 0 | 9037 | 0 | 190677 | 200608.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S244-393 | MANHATTAN 4/4A/7 GARAGE CONSTRUCTION | GARAGES AND FACILITIES | 304 307 | S-0244 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES | W. 57TH STREET/PIER 97 | CONSTRUCTION OF A NEW DOS GARAGE COMPLEX TO SERVE THE DISTRICTS OF MANHATTAN 4, 4A, AND 7. THIS PROJECT IS 100% CITY FUNDED, NON-EXEMPT. | 2019 | 165183 | 192409.98 | -1181 | 0 | 0 | 2560 | 0 | 0 | 193788.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SAND26MBC | Hurricane Sandy 26 St Manh Boro Rpr Shop Conduit Work | GARAGES AND FACILITIES | 300 | S-0136 |  |  | CONDUIT WORK DUE TO SANDY | 2019 | 324 | 2.29 | 0 | 63 | 0 | 0 | 0 | 0 | 65.29 | 20.67 | 0 | 552 | 0 | 0 | 0 | 0 | 572.67
20190425 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SAND26MBS | Hurricane Sandy 26 St Manh Boro R/R & Haz Mitigation | GARAGES AND FACILITIES | 300 | S-0136 |  |  | CAPITAL-ELIGIBLE REPLACEMENTS DUE TO HURRICANE SANDY AND ELEVATING CRIITICAL EQUIPMENT TO MITIGATE FLOOD HAZARD | 2019 | 5988 | 264.55 | 0 | 656 | 0 | 0 | 0 | 0 | 920.55 | 0 | 0 | 3378 | 0 | 0 | 0 | 0 | 3378
20190425 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SAND44BVC | Hurricane Sandy 44 Beaver Street Conduit Replacement | GARAGES AND FACILITIES | 300 | S-0136 |  |  | CONDUIT WORK DUE TO HURRICANE SANDY | 2019 | 14 | 0.05 | 0 | 6 | 0 | 0 | 0 | 0 | 6.05 | 0.45 | 0 | 41 | 0 | 0 | 0 | 0 | 41.45
20190425 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SAND44BVR | Hurricane Sandy 44 Beaver St System Replacement | GARAGES AND FACILITIES | 301 | S-0136 |  |  | PUMPS, ELEVATOR CONTROLS AND OTHER REPLACEMENTS DUE TO HURRICANE SANDY | 2019 | 621 | 59.05 | 0 | 117 | 0 | 0 | 0 | 0 | 176.05 | 81.47 | 0 | 1040 | 0 | 0 | 0 | 0 | 1121.47
20190425 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SANDMAN3C | Hurricane Sandy Manh 3 Garage Conduit Replacement | GARAGES AND FACILITIES | 303 | S-0136 |  |  | CONDUIT REPLACEMENT AT DSNY MANHATTAN 3 GARAGE AT PIER 36 | 2019 | 48 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 42 | 0 | 0 | 0 | 0 | 42
20190425 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SANDMAN3G | Hurricane Sandy Manh 3 Garage Repl & Haz Mitigation | GARAGES AND FACILITIES | 303 | S-0136 |  |  | DSNY MANHATTAN 3 GARAGE REPLACEMENT WORK DUE TO HURRICANE SANDY AND HAZARD MITIGATION INCLUDING RAISING AND RELOCATING CRITICAL EQUIPMENT | 2019 | 3843 | 0 | 0 | 366 | 0 | 0 | 0 | 0 | 366 | 0 | 0 | 3286 | 0 | 0 | 0 | 0 | 3286
20190425 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT504 | Replacement of Park, Highway and Flood Lights with LEDs | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT |  | PU-0025 TF-0503 |  |  | REPLACEMENT OF EXISTING HIGH PRESSURE SODIUM (HPS) IN PARKS, PLAYGROUNDS (FLOOD LIGHTS) AND HIGHWAYS WITH ENERGY EFFICIENT, LONG LIFE LED FIXTURES. | 2019 | 16598 | 0 | 15372 | 0 | 0 | 0 | 3513 | 0 | 18885 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT602 | DOT - Various locations- Rooftop Solar | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 301 | PU-0025 HW-0003 |  |  | DOT - VARIOUS LOCATIONS : ROOFTOP SOLAR PHOTOVOLTAIC SYSTEMS | 2019 | 515 | 0 | 474 | 0 | 0 | 0 | 0 | 0 | 474 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | E34CCTV | East 34th St Ferry Landing CCTV upgrade | RECONSTRUCTION OF FERRY TERMINAL FACILITIES | 300 | FA-0027 |  |  | CCTV UPGRADE | 2019 | 4314 | 0 | 0 | 185 | 0 | 0 | 0 | 0 | 185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | EMIDTWNRZ | East Midtown Rezoning | PRIMARY STREET RECONSTRUCTION | 300 | HW-0001 |  | EAST MIDTOWN REZONING | EAST MIDTOWN REZONING | 2019 | 18730 | 0 | 0 | 0 | 0 | 0 | 18730 | 0 | 18730 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | FAWHTGIRD | WHITEHALL SLIP 1 GIRDER RECONSTRUCTION | RECONSTRUCTION OF FERRY TERMINAL FACILITIES | 300 | FA-0021 |  |  | WHITEHALL SLIP 1 GIRDER RECONSTRUCTION | 2019 | 2200 | 1917.84 | 357 | 0 | 0 | 0 | 0 | 0 | 2274.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | FAWTCCTV | WHT Terminal CCTV Upgrades | RECONSTRUCTION OF FERRY TERMINAL FACILITIES | 300 | FA-0021 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | WHT TERMINAL CCTV UPGRADES | 2019 | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HB1070HR | Protective Coating of West 207th Bridge over Harlem River | BRIDGE PAINTING | 300 | HB-1070 |  | PROTECTIVE COATING OF WEST 207TH BRIDGE OVER HARLEM RIVER | PROTECTIVE COATING OF WEST 207TH BRIDGE OVER HARLEM RIVER | 2019 | 10450 | 2275.18 | 0 | 8472 | 0 | 0 | 0 | 0 | 10747.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HB1070RV | Protective Coating of Riverside Drive / W 125th St Bridge | BRIDGE PAINTING | 300 309 | HB-1070 |  | PROTECTIVE COATING OF RIVERSIDE DRIVER OVER W 125TH ST BRIDGE | PROTECTIVE COATING OF RIVERSIDE DRIVER OVER W 125TH ST BRIDGE | 2019 | 17729 | 6424.14 | 220 | 211 | 0 | 0 | 0 | 0 | 6855.14 | 8699 | 725 | 0 | 0 | 0 | 0 | 0 | 9424
20190425 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBFDR14BP | East 14th St (near ConEd Plant) Bike Path | FAIR BRIDGES | 300 | P-0508 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | EAST 14TH ST (NEAR CONED PLANT) BIKE PATH | EAST 14TH ST (NEAR CONED PLANT) BIKE PATH | 2019 | 39122 | 0 | 0 | 0 | 3337 | 0 | 4473 | 31312 | 39122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBINSPSSC | South Stuy Cove - Captain Brown Walk | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 300 | PU-0200 |  | SOUTH STUY COVE - CAPTAIN BROWN WALK | SOUTH STUY COVE - CAPTAIN BROWN WALK | 2019 | 3394 | 0 | 0 | 3394 | 0 | 0 | 0 | 0 | 3394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM1027 | HARLEM RV DRIVE VIADUCT: 127TH ST - 2ND AVE #2-23305-9/TN,,, | FAIR BRIDGES | 311 | HB-1027 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | HARLEM RIVER DR VIADUCT: 127TH ST TO 2ND AVE, MANHATTAN | RECONSTRUCTION AND REHABILITATION OF THE HARLEM RIVER DRIVE VIADUCTREPLACEMENT OF DECK, INCLUSIVE OF ANY INCIDENTAL STEEL WORK, CURBS ANDSIDEWALK THE FUNDING FOR THIS PROJECT IS ALL CITY | 2019 | 94722 | 42430.65 | 897 | 10815 | 0 | 0 | 0 | 0 | 54142.65 | 116719.15 | 4233 | 2783 | 0 | 0 | 0 | 0 | 123735.15
20190425 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM1056 | FDR DR AT HOUSTON ST OVERPASS BIN 2-23204-0 | FAIR BRIDGES | 303 | HB-1056 HB-0215 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | FDR DRIVE AT HOUSTON STREET OVERPASS, MANHATTAN | REHABILITATION OF FDR AT HOUSTON REPLACEMENT OF DECK INCLUSIVE OF ANYTAL STEEL WORK, CURBS, OR RAILING | 2019 | 6178 | 24973.86 | 224 | 671 | 0 | 0 | 0 | 0 | 25868.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM1120B | 11TH AVENUE VIADUCT NORTH SECTION - 33 ST to 35 ST #2245010 | FAIR BRIDGES | 304 | HB-1120 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | REPLACEMENT (NORTH SECTION) OF THE 11TH AVENUE VIADUCT BETWEEN WEST 33RD AND WEST 35TH STREETS | REPLACEMENT (NORTH SECTION) OF THE 11TH AVENUE VIADUCT BETWEEN WEST 33RD AND WEST 35TH STREETS | 2019 | 85076 | 40 | 300 | 26805 | 49631 | 0 | 0 | 0 | 76776 | 0 | 0 | 0 | 64413 | 0 | 0 | 0 | 64413
20190425 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM1147 | BROADWAY BRIDGE/HARLEM RIVER (BIN 2-24013-7) | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 312 | HB-1147 TF-0002 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | N/A |  | 2019 | 36746 | 29061.44 | 2487 | 16935 | 16000 | 0 | 0 | 0 | 64483.44 | 87436.71 | 0 | 33563 | 2000 | 0 | 0 | 0 | 122999.71
20190425 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM1165 | RIVERSIDE DRIVE BR/WEST 158TH 2-24672-0 | FAIR BRIDGES | 312 | HB-1165 TF-0002 TF-0502 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  |  | 2019 | 23896 | 50444.07 | -1484 | 8021 | 20000 | 0 | 0 | 0 | 76981.07 | 67530.43 | 13454 | 0 | 0 | 0 | 0 | 0 | 80984.43
20190425 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM1171 | W 31ST ST BR/AMTRAK LAYUP TRACKS 2-26672-A | FAIR BRIDGES | 304 | HB-0215 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  |  | 2019 | 21171 | 1066.83 | 32351 | 0 | 0 | 0 | 0 | 0 | 33417.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM1172 | HENRY HUDSON PKWY 72ND ST VIADUCT 2-22928-9 | FAIR BRIDGES | 300 307 | HB-0215 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | HENRY HUDSON PKWY 72ND ST VIADUCT 2-22928-9 | HENRY HUDSON PKWY 72ND ST VIADUCT 2-22928-9 | 2019 | 63009 | 99395.25 | 0 | 999 | 0 | 0 | 0 | 0 | 100394.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM1173 | HENRY HUDSON PKWY 94-98TH ST VIADUCT 2-26725-0 | FAIR BRIDGES | 300 307 | HB-0215 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | RECONSTRUCTION AT HHP 96TH ST VIADUCT | 2019 | 29176 | 22318.49 | 0 | 624 | 0 | 0 | 0 | 0 | 22942.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM1189 | WEST 79TH STREET/ AMTRAK (7 BIN#'S) | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 307 | HB-1189 P-0508 P-1018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | NA |  | 2019 | 59995 | 11338.79 | 5921 | 189941 | 0 | 0 | 0 | 0 | 207200.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM1212 | REHAB OF PARK AVE VIADUCT, NORTH SIDE OF EAST 42ND STREET | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 306 | HB-1212 HW-0200 TF-0002 HW-0001M | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | REHAB OF PARK AVE VIADUCT | REHAB OF PARK AVE VIADUCT | 2019 | 16995 | 25942.01 | 0 | 2279 | 0 | 2 | 0 | 195 | 28418.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM1221 | E25TH STREET PEDESTRIAN BRIDGE OVER FDR | FAIR BRIDGES | 306 | HB-1221 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | E25TH STREET PEDESTRIAN BRIDGE OVER FDR | E25TH STREET PEDESTRIAN BRIDGE OVER FDR | 2019 | 9785 | 2562.96 | 0 | 2050 | 0 | 7926 | 0 | 0 | 12538.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM191TUN | 191st St Pedestrian Tunnel over Broadway & IRT #1 Subway | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 300 | HB-1012 HB-0215 |  | 191ST ST PEDESTRIAN TUNNEL OVER BROADWAY & IRT #1 SUBWAY | 191ST ST PEDESTRIAN TUNNEL OVER BROADWAY & IRT #1 SUBWAY | 2019 | 47000 | 0 | 4000 | 408 | 0 | 5000 | 38000 | 0 | 47408 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM246350 | EAST DR OVER PED PATH OPP EAST 80TH ST BIN 2246350 | FAIR BRIDGES | 300 | P-0508 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | EAST DR OVER PED PATH OPP EAST 80TH ST BIN 2246350 | 2019 | 4598 | 0 | 0 | 200 | 300 | 0 | 512 | 3586 | 4598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM551 | PARK AVE TUNNEL FROM E34TH TO E39TH ST'S #2-24654-0/TN61420 | FAIR BRIDGES | 306 | TF-0502 HB-0551 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | RECON AND REHAB OF THE PARK AVE TUNNEL FROM E34TH TO E39TH ST REPLACEMHE DECK, INCIDENTAL STEEL WORK CURBS AND SIDEWALKS THE FUNDING FOR THIIS ALL CITY | 2019 | 22424 | 36195.63 | 1513 | 3249 | 0 | 0 | 0 | 0 | 40957.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM8650 | REHAB FDR NORTHBOUND FROM EAST 42-49TH ST BIN: 2268650 | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 300 306 | HB-0215 |  |  | REHAB FDR NORTHBOUND FROM EAST 42-49TH ST | 2019 | 97300 | 12015.67 | 190 | 85 | 0 | 85825 | 0 | 0 | 98115.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA22934 | RAMP TO NB HHP OVER AMTRAK WEST SIDE BIN 222934A | FAIR BRIDGES | 300 | HB-2934 |  | RAMP TO NB HHP OVER AMTRAK WEST SIDE BIN 222934A | RAMP TO NB HHP OVER AMTRAK WEST SIDE BIN 222934A | 2019 | 53051 | 0 | 0 | 3843 | 0 | 0 | 0 | 49708 | 53551 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA23216 | Promenade over FDR E81st - 90th St Bin 2232167 | FAIR BRIDGES | 300 | P-1018 |  | PROMENADE OVER FDR E81ST - 90TH ST BIN 2232167 | PROMENADE OVER FDR E81ST - 90TH ST BIN 2232167 | 2019 | 312992 | 35762.42 | 0 | 1185 | 0 | 0 | 276445 | 0 | 313392.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA24501 | WEST 35TH ST/ AMTRAK 30ST BRANCH BIN# 224501E | FAIR BRIDGES | 300 | HB-1012 HB-0215 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | WEST 35TH ST/ AMTRAK 30ST BRANCH | WEST 35TH ST/ AMTRAK 30ST BRANCH | 2019 | 2739 | 0 | 1187 | 1012 | 0 | 2618 | 28124 | 0 | 32941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA24544 | WEST 40TH ST / AMTRAK 30ST BRANCH BIN# 2245440 | FAIR BRIDGES | 300 | HB-1012 HB-0215 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | WEST 40TH ST / AMTRAK 30ST BRANCH BIN# 2245440 | 2019 | 4407 | 0 | 1453 | 2322 | 500 | 3787 | 42842 | 0 | 50904 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA24613 | East Dr (Willowdell Arch) over Ped Path Opp East 67th st | FAIR BRIDGES | 300 | P-0508 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | EAST DR (WILLOWDELL ARCH) OVER PED PATH OPP EAST 67TH ST | 2019 | 2543 | 0 | 345 | 300 | 0 | 255 | 1788 | 0 | 2688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA26724 | Trans-Manhattan Expressway BIN 2267240 | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 300 | HB-1078 |  | REHAB OF TRANS MANHATTAN EXPRESSWAY CONNECTOR | REHAB OF TRANS MANHATTAN EXPRESSWAY CONNECTOR | 2019 | 429583 | 0 | 8035 | 0 | 25471 | 0 | 49510 | 346567 | 429583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMFDNY20 | FDNY/NFPA CODE UPDATE HHP VARIOUS AND PARK AVE TUNNEL | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 300 | HB-0215 |  |  | FDNY/NFPA CURRENT CODE UPDATE HHP VARIOUS SECTIONS AND PARK AVE TUNNEL | 2019 | 61000 | 0 | 2179 | 2221 | 0 | 0 | 5000 | 52200 | 61600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR19D | Citywide Milling - Manhattan | PRIMARY STREET RESURFACING | 300 | HW-0002M |  |  | CITYWIDE MILLING- MANHATTAN | 2019 | 5958 | 0 | 2841 | 6814 | 0 | 0 | 0 | 0 | 9655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10216 | Walk of Fame -- Walk of Fame installation in CD 8 | PRIMARY STREET RECONSTRUCTION | 300 | HW-D102 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | WALK OF FAME -- WALK OF FAME INSTALLATION IN CD 8 | WALK OF FAME -- WALK OF FAME INSTALLATION IN CD 8 | 2019 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10217 | SAFETY IMPROVEMENTS | PRIMARY STREET RECONSTRUCTION | 300 | HW-D102 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | SAFETY IMPROVEMENTS | SAFETY IMPROVEMENTS | 2019 | 50 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10220 | DOT - 3rd Avenue Sidewalks | PRIMARY STREET RECONSTRUCTION | 300 | HW-D102 HW-0001M |  | DOT - 3RD AVENUE SIDEWALKS | DOT - 3RD AVENUE SIDEWALKS | 2019 | 2200 | 0 | 0 | 0 | 0 | 0 | 2200 | 0 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD200-05 | Sidewalk Reconstruction, 125th St & Lexington | PRIMARY STREET RECONSTRUCTION | 300 | HW-D200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | SIDEWALK RECONSTRUCTION, 125TH ST & LEXINGTON | SIDEWALK RECONSTRUCTION, 125TH ST & LEXINGTON | 2019 | 1000 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM100CTN | 23rd St Crosstown SBS | PRIMARY STREET RECONSTRUCTION | 300 | HW-1684 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | 14TH ST OR 23RD ST CROSSTOWN SBS | 14TH ST OR 23RD ST CROSSTOWN SBS | 2019 | 7750 | 0 | 0 | 0 | 0 | 0 | 7750 | 0 | 7750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM100SNC | 79TH STREET SBS | PRIMARY STREET RECONSTRUCTION | 300 | HW-1684 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | 79TH STREET SBS | 79TH STREET SBS | 2019 | 11500 | 0 | 2286 | 0 | 0 | 18286 | 0 | 0 | 20572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM1684 | Allen & Pike Street Malls Phase 2 | PRIMARY STREET RECONSTRUCTION | 300 | HW-0001M |  | ALLEN & PIKE STREET MALLS PHASE 2 | ALLEN & PIKE STREET MALLS PHASE 2 | 2019 | 4000 | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM1687 | Holland Tunnel Area Pedestrian Safety Improvements & Public | PRIMARY STREET RECONSTRUCTION | 300 | HW-0001M |  | HOLLAND TUNNEL AREA PEDESTRIAN SAFETY IMPROVEMENTS & PUBLIC | HOLLAND TUNNEL AREA PEDESTRIAN SAFETY IMPROVEMENTS & PUBLIC | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 12180 | 0 | 12180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM1688 | Harlem Multi-Site | PRIMARY STREET RECONSTRUCTION | 300 | HW-0001M |  | HARLEM MULTI-SITE | HARLEM MULTI-SITE | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 15300 | 0 | 15300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM300 | BLEECKER ST. | PRIMARY STREET RECONSTRUCTION | 300 302 | HW-0001M | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | BLEECKER ST. | BLEECKER ST. | 2019 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 1200
20190425 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMBRT5 | 34th STREET | TRAFFIC WORK IN CONJUNCTION WITH HIGHWAY RECONSTRUCTION | 300 304 305 306 | TF-0777 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | 34TH STREET | 34TH STREET | 2019 | 25000 | 270.34 | 0 | 0 | 0 | 0 | 0 | 1861 | 2131.34 | 2433.09 | 0 | 0 | 0 | 0 | 0 | 0 | 2433.09
20190425 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMBRT6 | 1st & 2nd Avenue | TRAFFIC WORK IN CONJUNCTION WITH HIGHWAY RECONSTRUCTION | 300 | TF-0777 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | 1ST & 2ND AVENUE | 1ST & 2ND AVENUE | 2019 | 33608 | 2237.99 | 0 | 0 | 0 | 0 | 0 | 3171 | 5408.99 | 10260.57 | 0 | 0 | 0 | 0 | 0 | 0 | 10260.57
20190425 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMM009 | GATEWAYS TO CHINATOWN | PRIMARY STREET RECONSTRUCTION | 300 301 302 303 | HW-M002 HW-0001M HW-D102 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | CHINA TOWN PARTNERSHIP LOCAL DEVELOPMENT CORP. I NC. | CHINA TOWN PARTNERSHIP LOCAL DEVELOPMENT CORP. I NC. | 2019 | 314 | 0 | 314 | 0 | 0 | 75 | 0 | 0 | 389 | 0 | 0 | 50 | 0 | 0 | 600 | 0 | 650
20190425 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTC A8 | WORLD TRADE CENTER AREA 8 | PRIMARY STREET RECONSTRUCTION | 300 301 | HW-1670 HW-0200 TF-0002 TF-0502 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | RECONSTRUCTION OF WORLD TRADE CENTER | RECONSTRUCTION OF WORLD TRADE CENTER AREA 8. | 2019 | 12504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8566 | 8566
20190425 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTC A9 | WORLD TRADE CENTER AREA 9. | PRIMARY STREET RECONSTRUCTION | 300 301 | HW-1670 HW-0200 TF-0502 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | RESURFACING WTC AREA 9 | RESURFACING WORLD TRADE CENTER AREA 9. | 2019 | 36299 | 0 | 0 | 0 | 0 | 0 | 0 | 1072 | 1072 | 0 | 0 | 0 | 0 | 0 | 0 | 34695 | 34695
20190425 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTC11 | WORLD TRADE CENTER AREA 11 | PRIMARY STREET RECONSTRUCTION | 301 | HW-1670 HW-0200 TF-0002 TF-0502 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | RECONSTRUCTION OF WORLD TRADE CENTER AREA 11 | RECONSTRUCTION OF WORLD TRADE CENTER AREA 11 | 2019 | 306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186 | 186
20190425 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTCA10 | WORLD TRADE CENTER AREA 10 | PRIMARY STREET RECONSTRUCTION | 301 | HW-1670 HW-0200 TF-0002 TF-0502 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | RECONSTRUCTION OF WORLD TRADE CENTER AREA 10 | RECONSTRUCTION OF WORLD TRADE CENTER AREA 10 | 2019 | 770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 770 | 770
20190425 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTCB3 | Reconstruction of Broadway | PRIMARY STREET RECONSTRUCTION | 300 | HW-0001M |  | RECONSTRUCTION OF BROADWAY | RECONSTRUCTION OF BROADWAY | 2019 | 10640 | 0 | 0 | 0 | 0 | 0 | 0 | 2128 | 2128 | 0 | 0 | 0 | 0 | 0 | 0 | 8512 | 8512
20190425 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTCB4 | Reconstruction of Varick St | PRIMARY STREET RECONSTRUCTION | 300 | HW-0001M |  | RECONSTRUCTION OF VARICK ST | RECONSTRUCTION OF VARICK ST | 2019 | 397 | 0 | 0 | 0 | 0 | 0 | 80 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 317 | 0 | 317
20190425 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTCB8 | Reconstruction of Broadway Phase 2 | PRIMARY STREET RECONSTRUCTION | 300 | HW-0001M |  | RECONSTRUCTION OF BROADWAY PHASE 2 | RECONSTRUCTION OF BROADWAY PHASE 2 | 2019 | 67660 | 0 | 0 | 760 | 0 | 6750 | 0 | 0 | 7510 | 0 | 0 | 2700 | 0 | 20900 | 0 | 0 | 23600
20190425 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ010M | Flatiron Plaza Reconstruction | LOCAL STREET RECONSTRUCTION | 300 305 | HW-0001M HW-1684 HW-D102 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | FLATIRON PLAZA RECONSTRUCTION | FLATIRON PLAZA RECONSTRUCTION | 2019 | 200 | 0 | 0 | 0 | 0 | 9725 | 0 | 0 | 9725 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 300
20190425 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWPR19MC1 | Complex Upgrades Ped Ramps - Manhattan | PEDESTRIAN RAMP CONSTRUCTION | 300 | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | COMPLEX UPGRADES PED RAMPS - MANHATTAN | COMPLEX UPGRADES PED RAMPS - MANHATTAN | 2019 | 8516 | 0 | 591 | 0 | 7815 | 0 | 0 | 0 | 8406 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWPR19MC2 | Complex Upgrades Ped Ramps - Manhattan | PEDESTRIAN RAMP CONSTRUCTION | 300 | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | COMPLEX UPGRADES PED RAMPS - MANHATTAN | COMPLEX UPGRADES PED RAMPS - MANHATTAN | 2019 | 8043 | 0 | 557 | 0 | 7497 | 0 | 0 | 0 | 8054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWWTCLUMP | World Trade Center - Lump Sum | PRIMARY STREET RECONSTRUCTION | 300 | HW-0001M | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | WORLD TRADE CENTER - LUMP SUM | WORLD TRADE CENTER - LUMP SUM | 2019 | 23630 | 0 | 0 | 0 | 0 | 4654 | 0 | 6022 | 10676 | 0 | 0 | 0 | 0 | 0 | 0 | 49504 | 49504
20190425 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | PIER11CTV | Pier 11 CCTV upgrade | RECONSTRUCTION OF FERRY TERMINAL FACILITIES | 300 | FA-0027 |  |  | CCTV UPGRADE | 2019 | 200 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | REALTIMEM | Real Time Traffic Monitoring in Lower Manhattan | SIGNAL INSTALLATION AND COMPUTERIZATION | 300 | TF-0001 |  |  | REAL TIME SYSTEM FOR LOWER MANHATTAN | 2019 | 2800 | 3115.26 | 0 | 892 | 0 | 0 | 0 | 0 | 4007.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | REALTMIDM | Expand Real Time Traffic Monitoring in Midtown Manhattan | SIGNAL INSTALLATION AND COMPUTERIZATION | 300 | TF-0001 |  |  | TRAFFIC MONITORING IN MANHATTAN | 2019 | 9480 | 2904 | 0 | 5869 | 0 | 0 | 0 | 0 | 8773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | SANDHB001 | Battery Park 2-23200 & West St 2-26738 Underpasses- Sandy | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 300 301 | HB-0215 |  |  | REHABILITATION OF BATTERY PARK UNDERPASS (BIN 2-23200-0) AND WEST STREET UNDERPASS (BIN 2-26738-0) - SANDY. NEW ID PER OMB MEMO DEC 2012.WORK RELATED TO DAMAGES DUE TO HURRICANE SANDY. EMERGENCY AND PERMANENT REPAIRS. | 2019 | 23000 | 15717.66 | 778 | 2736 | 0 | 0 | 0 | 0 | 19231.66 | 50883.68 | 3111 | 0 | 0 | 0 | 0 | 0 | 53994.68
20190425 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | SANDHB2U | SANDY ER BETTERMENTS FOR BATTERY PARK & WEST ST UNDERPASSES | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 300 | HB-0215 |  |  | SANDY ER BETTERMENTS FOR BATTERY PARK & WEST ST UNDERPASSES | 2019 | 18850 | 0 | 627 | 0 | 290 | 3045 | 0 | 0 | 3962 | 0 | 2508 | 0 | 1160 | 12180 | 0 | 0 | 15848
20190425 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | SANDHBFDR | SANDY ER FOR FDR 18TH TO 25TH STREET | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 300 | HB-0215 |  |  | SANDY ER BETTERMENTS FOR FDR 18TH TO 25TH STREET | 2019 | 8414 | 295.39 | 1414 | 139 | 0 | 0 | 0 | 0 | 1848.39 | 521.44 | 5654 | 554 | 0 | 0 | 0 | 0 | 6729.44
20190425 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | SANDHW27 | Montgomery to 15th Street - Hurricane Sandy | PRIMARY STREET RECONSTRUCTION | 300 | HW-0001M |  | MONTGOMERY TO 15TH STREET - HURRICANE SANDY | MONTGOMERY TO 15TH STREET - HURRICANE SANDY | 2019 | 16130 | 0 | 0 | 0 | 0 | 0 | 0 | 3226 | 3226 | 0 | 1328 | 0 | 0 | 0 | 0 | 11576 | 12904
20190425 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TF50314 | Rpl lg poles on W47th St bet 5th&6th Ave MA2303.30A | INSTALLATION OF LAMPPOSTS AND LUMINAIRES | 300 | TF-0503 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | MA2303.30A REPLACE LIGHT POLES WITH ENERGY SAVING HIGH ILLUMINATION LIGHT POLES. // W 47TH STREET BETWEEN 5TH - 6TH AVENUES MN-MM $148,000 | 2019 | 148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 148 | 0 | 0 | 0 | 0 | 0 | 148
20190425 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TF50316 | Decor Historic lg on W13th St, from 7th Ave to XMA418.30A | INSTALLATION OF LAMPPOSTS AND LUMINAIRES | 300 | TF-0503 |  |  | FURNISH AND INSTALL DEC LIGHT ON WEST 13RH ST FROM 7TH AVENUE TO GREENWICH AVENUE | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 200
20190425 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFCPARKLG | Central Park Light Infrastructure | REPLACEMENT OF ELECTRICAL DISTRIBUTION SYSTEMS | 300 | TF-0503 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | CENTRA PARK LIGHT INFRASTRUCTURE | CENTRAL PARK LIGHT INFRASTRUCTURE | 2019 | 28000 | 12450.53 | 0 | 6940 | 5063 | 4000 | 0 | 0 | 28453.53 | 12864.12 | 0 | 0 | 1136 | 0 | 0 | 0 | 14000.12
20190425 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503-20 | DOWNTOWN ALLIANCE-HISTORIC LIGHTPOLES | INSTALLATION OF LAMPPOSTS AND LUMINAIRES | 300 301 | TF-M503 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | DOWNTOWN ALLIANCE-HISTORIC LIGHTPOLES | DOWNTOWN ALLIANCE-HISTORIC LIGHTPOLES | 2019 | 383 | 527 | 0 | 0 | 0 | 38 | 0 | 0 | 565 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M29 | Second Avenue Street lights | INSTALLATION OF LAMPPOSTS AND LUMINAIRES | 300 | TF-D503 |  |  | 2ND AVENUD LIGHT | 2019 | 434 | 0 | 434 | 0 | 0 | 0 | 0 | 0 | 434 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M30 | Garment District street light | INSTALLATION OF LAMPPOSTS AND LUMINAIRES | 300 | TF-D503 |  |  | DECORATIVE LIGHTING IN GARMENT DISTRICT | 2019 | 150 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M31 | Historic St lg on 11th St and on 12th St, Manhattan | INSTALLATION OF LAMPPOSTS AND LUMINAIRES | 300 | TF-D503 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | DECORATIVE LIGHT | 2019 | 70 | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M33 | GREENWICH VILLAGE DECORATIVE LIGHTING | INSTALLATION OF LAMPPOSTS AND LUMINAIRES | 300 | TF-D503 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | GREEWICH VILLAGE DECRATIVE LIGHTING | 2019 | 250 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFLGLMANH | Decorative Street light in Lower Manhattan , X759.24 | INSTALLATION OF LAMPPOSTS AND LUMINAIRES | 300 301 | TF-0503 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | FHWA WTC/ER- X759.24 STREETLIGHTING PS&E-LOWER MANHATTAN DECORATIVE LIGHT CONTRACT FROM S.OF MURRY ST AND BET W.ST AND FDR | 2019 | 6289 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 1934.73 | 0 | 0 | 0 | 2354 | 0 | 0 | 4288.73
20190425 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFM503-09 | COOPER SQUARE(61 EAST 4TH STREET)STREETSCAPE-LIGHTING | INSTALLATION OF LAMPPOSTS AND LUMINAIRES | 300 302 303 | TF-M503 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | LIGHTING | 2019 | 65 | 32.25 | 0 | 0 | 0 | 42 | 0 | 0 | 74.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFM50311 | INSTALL S-POLE LIGHTING- VARIOUS STREETS WEST OF BROADWAY | INSTALLATION OF LAMPPOSTS AND LUMINAIRES | 300 301 302 | TF-M503 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | HISTORIC LIGHTING:LINCOLN PLACE BETWEEN 6TH AND 7TH AVENUE | HISTORIC LIGHTING:LINCOLN PLACE BETWEEN 6TH AND 7TH AVENUE | 2019 | 450 | 298.94 | 0 | 0 | 0 | 151 | 0 | 0 | 449.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFM50316 | Frederick Douglas Blvd Street Lamps | INSTALLATION OF LAMPPOSTS AND LUMINAIRES | 300 310 | TF-M503 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | STREET LAMPS LAMPS FOR FREDERICK DOUGLAS BLVD | 2019 | 198 | 305.23 | 0 | 0 | 0 | 41 | 0 | 0 | 346.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | W125STLG | W 125TH ST LG & SIGNAL-5TH AVE TO MORNINGSIDE AVE, MA2288.3 | INSTALLATION OF LAMPPOSTS AND LUMINAIRES | 300 309 310 | TF-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | INSTALLATION OF NEW DECORATIVE ST LIGHT AND STANDARD SIGNALS | 2019 | 2056 | 1196.71 | 0 | 0 | 0 | 0 | 503 | 0 | 1699.71 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 500
20190425 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | W147LIGH | West 147th Street Sugar Hill Historical Street Lights | INSTALLATION OF LAMPPOSTS AND LUMINAIRES | 310 | TF-M503 |  |  |  | 2019 | 0 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | WHTGIRDS2 | Whitehall Ferry Terminal-Slip2 Girder Reconstruction | RECONSTRUCTION OF FERRY TERMINAL FACILITIES | 300 | FA-0021 |  |  | WHITEHALL FERRY TERMINAL - SLIP 2 GIRDER RECONSTRUCTION | 2019 | 0 | 0 | 0 | 0 | 250 | 0 | 2500 | 0 | 2750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | WHTGIRDS3 | Whitehall Ferry Terminal-Slip3 Girder Reconstruction | RECONSTRUCTION OF FERRY TERMINAL FACILITIES | 300 | FA-0021 |  |  | WHITEHALL FERRY TERMINAL - SLIP 3 GIRDER RECONSTRUCTION | 2019 | 0 | 0 | 0 | 0 | 500 | 0 | 2500 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | WHTLBRIDG | Whitehall Slips 1,2,3 Bridge Reconstruction | RECONSTRUCTION OF FERRY TERMINAL FACILITIES | 300 | FA-0021 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | WHITEHALL SLIPS 1,2,3 LOWER BRIDGE RECONSTRUCTION | 2019 | 5300 | 0 | 0 | 1065 | 0 | 4235 | 0 | 0 | 5300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | ACEDPR408 | Centralized HVAC Controls | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT |  | PU-0025 |  |  | INSTALLATION OF BUILDING CONTROLS TO OPTIMIZE HVAC SYSTEMS IN MULTIPLE FACILITES | 2019 | 0 | 0 | 0 | 1412 | 0 | 0 | 0 | 0 | 1412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | ACEDPR601 | DPR - Various locations - Pool Pumping system upgrade | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 301 | PU-0025 |  |  | DPR - VARIOUS LOCATIONS : POOL PUMPING SYSTEM UPGRADE | 2019 | 0 | 0 | 0 | 192 | 0 | 0 | 0 | 0 | 192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | ACEDPR704 | DPR - BMS (Building Management System) INSTALLATION | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 301 | PU-0025 |  |  | DPR - BMS INSTALLATION | 2019 | 0 | 0 | 0 | 234 | 0 | 0 | 0 | 0 | 234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | HRPT | Hudson River Park Trust - Pier 26 | MISCELLANEOUS | 300 | ED-0075 |  |  | HUDSON RIVER PARK TRUST | 2019 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | NDF-DYMAN | NDF - Dyckman Sitting Area in Highbridge Park R/C | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | ED-0384 |  |  | RENOVATE DYCKMAN REST IN HIGHBRIDGE PARK, BOROUGH OF MANHATTAN | 2019 | 5000 | 0 | 437 | 0 | 0 | 0 | 4563 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | NDF-HRPCS | NDF Harlem River Park (M208D) - New Comfort Station | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | ED-0384 |  |  | NDF HARLEM RIVER PARK (M208D) - NEW COMFORT STATION | 2019 | 4716 | 0 | 326 | 0 | 4390 | 0 | 0 | 0 | 4716 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | NDF-IWOOD | NDF - Inwood Hill Park Soccer Field #1 R/C | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 300 312 | ED-0384 P-D018 |  |  | RENOVATE INWOOD HILL PARK SOCCER FIELD #1 (DYCKMAN FIELDS), BOROUGH OF MANHATTAN | 2019 | 6000 | 0 | 0 | 0 | 601 | 222 | 5399 | 0 | 6222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | NDF-MKETT | NDF - Monsignor Kett Playground R/C | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 312 | ED-0384 |  |  | REBUILD MONSIGNOR KETT PLAYGROUND, BOROUGH OF MANHATTAN | 2019 | 15186 | 0 | 1240 | 0 | 12760 | 0 | 0 | 0 | 14000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-300EAST | East River Esplanade Projects | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | PU-0026 PU-0200 P-0501 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BOROUGH OF MANHATTAN | EAST RIVER ESPLANADE | 2019 | 23522 | 2301.31 | 4285 | 0 | 0 | 1634 | 0 | 0 | 8220.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-300ERES | East River Esplanade GLICK PK RC | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-1018 |  |  | EAST RIVER ESPLANADE RECONSTRUCTION (M289-116M) | 2019 | 54 | 18.83 | 0 | 0 | 0 | 35 | 0 | 0 | 53.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-300FDCG | Frederick Douglass Boulevard Community Garden Restoration | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-M245 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | FREDERICK DOUGLAS BOULEVARD COMMUNITY GARDEN | FDB GARDEN COMMITTEE: COMMUNITY GARDEN RESTORATION | 2019 | 119 | 0 | 119 | 0 | 0 | 0 | 0 | 0 | 119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-300LMDC | LOWER MANHATTAN (BUNDLED) PROJECTS MG-703M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 301 302 304 | P-0245M | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES | MANHATTAN | LOWER MANHATTAN PROJECTS | 2019 | 16499 | 2757.29 | 0 | 0 | 0 | 0 | 0 | 0 | 2757.29 | 13478.98 | 0 | 0 | 0 | 0 | 1496 | 0 | 14974.98
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-300ZO18 | Central Park Zoo - Sea Lion Exhibit Renovation | ZOOS | 300 | P-0887 |  | CENTRAL PARK ZOO - SEA LION EXHIBIT RENOVATION | CENTRAL PARK ZOO - SEA LION EXHIBIT RENOVATION | 2019 | 1800 | 0 | 100 | 0 | 150 | 1550 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-300ZO19 | Central Park Zoo - Roofs | ZOOS | 300 | P-0887 |  | CENTRAL PARK ZOO - ROOFS | CENTRAL PARK ZOO - ROOFS | 2019 | 2300 | 0 | 300 | 2000 | 0 | 0 | 0 | 0 | 2300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-300ZO20 | Central Park Zoo - Tractor and attachments | ZOOS | 300 | P-D018 |  | CENTRAL PARK ZOO - TRACTOR AND ATTACHMENTS | CENTRAL PARK ZOO - TRACTOR AND ATTACHMENTS | 2019 | 103 | 0 | 40 | 3 | 0 | 0 | 0 | 0 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301BPBP | BATTERY PARK BIKEWAY PERIMETER M005-111M (SUPERCEDES 308M) | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 301 | P-0828 P-0245M | PROJECT DELAYED PENDING APPROVAL OF NECESSARY PERMITS | BATTERY PARK BIKEWAY PERIMETER | BATTERY PARK BIKEWAY PERIMETER | 2019 | 350 | 1892.57 | 0 | 0 | 0 | 0 | 0 | 0 | 1892.57 | 15166.68 | 980 | 0 | 0 | 0 | 0 | 0 | 16146.68
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301BPCG | Battery Park Coast Guard Memorial Relocation (M005-217M) | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 300 | P-0828 |  | BATTERY PARK COAST GUARD MEMORIAL RELOCATION | BATTERY PARK COAST GUARD MEMORIAL RELOCATION | 2019 | 662 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 0 | 0 | 0 | 553 | 47 | 0 | 0 | 600
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301BPOC | Battery Park Office convert to Comfort station M005 | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 301 | P-D018 P-M245 P-0828 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BATTERY PK OFFICE CONVERT TO COMFORT STATION | BATTERY PK OFFICE CONVERT TO COMFORT STATION | 2019 | 500 | 0 | 0 | 0 | 0 | 4965 | 0 | 0 | 4965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301BURL | BURLING SLIP - IMAGINATION PLGD MG-41100-107M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 301 | SE-0002M | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | BURLING SLIP | BURLING SLIP | 2019 | 4125 | 4367.09 | 288 | 0 | 0 | 0 | 0 | 0 | 4655.09 | 5499.61 | 0 | 0 | 0 | 0 | 0 | 0 | 5499.61
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301EPPK | Elizabeth H. Berger Plaza, Manhattan | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 301 | P-D018 P-M245 HW-0001M P-1018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | EDGAR PLAZA PARK - GREEN STREET | EDGAR PLAZA PARK - GREEN STREET | 2019 | 1000 | 934 | 6691 | 0 | 0 | 0 | 0 | 0 | 7625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301PEAR | PEARL ST PLGD MG-41000-107M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 301 | P-0245M | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | PEARL ST PLGD | PEARL STREET PLAYGROUND | 2019 | 852 | 873.09 | 0 | 0 | 0 | 0 | 0 | 0 | 873.09 | 1868.47 | 0 | 0 | 0 | 0 | 232 | 0 | 2100.47
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301PECK | LMDC-PECK SLIP RECONSTRUCTION M167-106M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 301 | P-0245M | PROJECT DELAYED DUE TO SCHEDULING OF UTILITY WORK | PECK SLIP RECONSTRUCTION, MANHATTAN | PECK SLIP RECONSTRUCTION, MANHATTAN | 2019 | 4030 | 287.04 | 0 | 0 | 0 | 0 | 0 | 0 | 287.04 | 770.27 | 0 | 3147 | 0 | 0 | 0 | 0 | 3917.27
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-302AIDM | NYC AIDS Memorial -- Capital Refurbishment to Memorial | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 300 | P-D018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | NYC AIDS MEMORIAL -- CAPITAL REFURBISHMENT TO MEMORIAL | 2019 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-302CJSC | CORPORAL JOHN A SERAVALLI PLGD CS RC M237-116M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 302 | P-D018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | CORPORAL JOHN A SERAVALLI PLGD COMF STAT RECON | CORPORAL JOHN A SERAVALLI PLGD COMF STAT RECON | 2019 | 1700 | 1215.29 | 0 | 0 | 666 | 0 | 0 | 0 | 1881.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-302DPCA | DESALVIO PLGD RECON - ADULT USE & KID PLAY AREAS M218 | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 302 | P-D018 P-M245 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | DESALVIO PLGD RECON - ADULT USE & KID PLAY AREAS | DESALVIO PLGD RECON - ADULT USE & KID PLAY AREAS | 2019 | 550 | 2208.97 | 11 | 0 | 0 | 160 | 0 | 0 | 2379.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-302DRYD | DRY DOCK PLAYGROUND RECON M270-110M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 302 | P-1018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | DRY DOCK PLAYGROUND RECON | DRY DOCK PLAYGROUND RECON | 2019 | 800 | 2026.5 | 0 | 0 | 0 | 35 | 0 | 0 | 2061.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-302GLAF | DEP Shaft Site -- Grand & Lafayette Streets | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 302 | W-0013 P-D018 P-M245 | PROJECT DELAYED PENDING APPROVAL OF NECESSARY PERMITS |  | DPR - GRAND & LAFAYETTE -- CREATE A NEW PARK AT THE GRAND AND LAFAYETTE STREET DEP WATERSHAFT SITE. DEP HAS TOLD PARKS THEY CAN HAVE 5K SQ. FT. ON THE WESTERN PORTION OF THE SITE. | 2019 | 300 | 140 | 0 | 1000 | 0 | 696 | 0 | 0 | 1836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-302HUHO | DEP shaft site 28B - Hudson and West Houston | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | W-0013 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES |  | DEP SHAFT SITE 28B - HUDSON AND WEST HOUSTON | 2019 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-302MHSA | DEP Shaft Site 31B at Bowery and East 4th Street | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 300 | W-0013 P-D018 P-M245 |  |  | DEP SHAFT SITE 31B AT BOWERY AND EAST 4TH STREET | 2019 | 0 | 50 | 0 | 1000 | 169 | 101 | 0 | 0 | 1320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-302WSQ4 | Washington Sq. Park SIDEWALK (M098-114M) | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 302 | P-0245M | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | WASHINGTON SQUARE PARK, BOROUGH OF MANHATTAN | CONSTRUCTION OF SIDEWALK IN WASHINGTON SQUARE PARK | 2019 | 1966 | 2068.89 | 18 | 0 | 0 | 100 | 0 | 0 | 2186.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303ASCS | ALLEN STREET COMFORT STATION LMDC | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 303 | P-0505 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | ALLEN STREET COMFORT STATION | ALLEN STREET COMFORT STATION | 2019 | 1000 | 174.92 | 0 | 0 | 0 | 0 | 0 | 0 | 174.92 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 1000
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303ASGL | Alfred E Smith Rec Center - Upgrade Gym Lighting | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 300 303 | P-D018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | DPR - ALFRED E SMITH RECREATIONAL CENTER -- UPGRADE GYM LIGHTING | 2019 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303ASRC | Al Smith Rec Cntr-replace a/c & new windows | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-M245 P-D018 |  | AL SMITH REC CENTER | REPLACE A/C & NEW WINDOWS AT AL SMITH REC CENTER | 2019 | 380 | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303BPCS | Baruch Playground C/S Renovations M165A-116M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 303 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BARUCH PLAYGROUND BATHROOM RENOVATIONS -- RECONSTRUCT THE COMFORT STATION, INCLUDING NEW WINDOWS, DOORS, FIXTURES AND PARTITIONS AS WELL ASNEW PLUMBING, ELECTRICAL AND MECHANICAL SYSTEMS. MAKE BATHROOMS ADA COMPLIANT | 2019 | 340 | 1748.23 | 6 | 0 | 0 | 151 | 0 | 0 | 1905.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303CRHP | Corlear's Hook Park- Dod Run, M017-118M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | CORLEAR'S HOOK PARK, MANHATTAN | CORLEAR'S HOOK PARK | 2019 | 250 | 140 | 27 | 476 | 47 | 0 | 0 | 0 | 690 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303DOPG | Downing Playground-renovation plgr &W. Churchill Garden | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 300 | P-D018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | DOWNING PLAYGROUND-RENOVATION PLGR &W. CHURCHILL GARDEN | DOWNING PLAYGROUND-RENOVATION PLGR &W. CHURCHILL GARDEN | 2019 | 400 | 106 | 0 | 0 | 0 | 0 | 0 | 140 | 246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303ERFB | EAST RIVER PK - FIRE BOATHOUSE RENOVATION M144-114MA | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 303 | P-D018 P-M245 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | EAST RIVER PK - FIRE BOATHOUSE RENOVATION | EAST RIVER PK - FIRE BOATHOUSE RENOVATION | 2019 | 913 | 310.6 | -14 | 0 | 419 | 88 | 0 | 0 | 803.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303ERSF | ERP - E 6TH ST SOCCER FLD NEW TURF M144-214m | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 303 | P-D018 P-0510 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | ERP - E 6TH ST SOCCER FLD NEW TURF & LIGHTS | ERP - E 6TH ST SOCCER FLD NEW TURF & LIGHTS | 2019 | 600 | 3389.99 | 0 | 0 | 0 | 136 | 0 | 0 | 3525.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303ERWE | East River Park Composting Facility & Wetland R/C M144-116M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 P-1245 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES | EAST RIVER PK | CONSTRUCT WETLAND | 2019 | 1140 | 395.06 | 0 | 0 | 0 | 705 | 0 | 0 | 1100.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303HFRC | Hamilton Fish Rec.Ctr-replace roof & alarm system | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 300 | P-D018 |  | HAMILTON FISH REC.CTR- | HAMILTON FISH REC.CTR-REPLACE ROOF & ALARM SYSTEM | 2019 | 300 | 27 | 0 | 0 | 0 | 0 | 0 | 300 | 327 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303JACK | Jackie Robinson Rec Center Facades M014-114M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 300 310 | P-1018 |  | JACKIE ROBINSON REC CENTER | MASONRY WORK ON EXTERIOR FACADES | 2019 | 1400 | 2502.06 | 14 | 0 | 0 | 236 | 0 | 0 | 2752.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303LGPK | CPI PH1 - LUTHER GULICK PARK - RECON WEST PORTION | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 303 | P-D018 P-M245 P-0245M P-1018 | PROJECT DELAYED PENDING NON-CITY GRANT APPROVAL | LUTHER GULICK PARK - RECON WEST PORTION | LUTHER GULICK PARK - RECON WEST PORTION | 2019 | 360 | 961.5 | 4450 | 0 | 0 | 1097 | 0 | 0 | 6508.5 | 0 | 3500 | 0 | 0 | 0 | 0 | 0 | 3500
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303MCKY | McKinley Playground renovation | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 P-M245 |  | MCKINLEY PLAYGROUND RE4OVATION. | MCKINLEY PLAYGROUND RENOVATION. | 2019 | 2505 | 317.33 | 82 | 2501 | 217 | 0 | 0 | 0 | 3117.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303SARD | S.D. Roosevelt Pk-plgd&restrooms(Bldg D) M105-107M,108M/208M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 303 | P-0245M | PROJECT DELAYED PENDING APPROVAL OF NECESSARY PERMITS | SARA DELANO ROOSEVELT PARK, MANHATTAN | SARA DELANO ROOSEVELT PARK, MANHATTAN | 2019 | 5077 | 1188.65 | 0 | 0 | 0 | 0 | 0 | 0 | 1188.65 | 4399.59 | 0 | 0 | 0 | 0 | 316 | 0 | 4715.59
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303SDRB | Sara D. Roosevelt PK Store room convert to bathroom M105 | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 303 | P-D018 P-M245 P-1018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | SDR PK STOREROOM CONVERT TO BATHROOM | SDR PK STOREROOM CONVERT TO BATHROOM | 2019 | 500 | 218.92 | 1400 | 0 | 0 | 140 | 0 | 0 | 1758.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303SDRP | Sara D. Roosevelt Park - Pathways, sidewalks, exterior walls | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 P-M245 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | ROOSEVELT PARK, MANHATTAN | SARA. D ROOSEVELT PARK- PATHWAYS, SIDEWALKS, EXTERIOR WALLS | 2019 | 300 | 170 | 0 | 0 | 0 | 0 | 0 | 926 | 1096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303TPS2 | Tompkins Square Park Play Area and Lawn Reconstruction | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 300 | P-0926 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | FY18 TRF $900K (FY20) & $100K (FY21) FROM P-303TPSQ.. | 2019 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303TPSQ | Tompkin's Square Park - Manhattan | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-0926 |  |  | TOMPKIN'S SQUARE PARK - MANHATTAN | 2019 | 4600 | 0 | 0 | 0 | 0 | 4600 | 0 | 0 | 4600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303TSPL | Tompkins Square Plgr-R/c at Ave B/E7 | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 300 | P-1018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | TOMPKINS SQ PK | 2019 | 611 | 2560.49 | 0 | 0 | 231 | 0 | 0 | 0 | 2791.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-30420S2 | West 20th St. Park Construction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | ED-0075 P-D018 |  |  | WEST 20TH ST. PARK CONSTRUCTION | 2019 | 3043 | 2441.79 | 548 | 0 | 389 | 0 | 0 | 0 | 3378.79 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 500
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-304CBBC | Chelsea Basketball Court Renovation, Manhattan | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 |  |  | CHELSEA BASKETBALL COURT RENOVATION -- THIS PROJECT WOULD REPAVE AND REPAINT THE COURT SURFACE, INSTALL NEW HOOPS AND ADD NEW SEATING | 2019 | 943 | 0 | 0 | 0 | 0 | 943 | 0 | 0 | 943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-304CCMP | Clement Clarke Moore Pk R/c of sitting area | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-1018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | CLEMENT CLARKE MOORE PK | CLEMENT CLARKE MOORE PK R/C OF SITTING AREA | 2019 | 400 | 1729.67 | 0 | 0 | 0 | 137 | 0 | 0 | 1866.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-304CRLB | CHELSEA REC CTR ROOF DECK, LOCKER RM & BTHRM M260-114M | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 304 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | WEST 25TH STREET BETWEEN 9TH & 10TH AVENUES | CHELSEA RECREATION CENTER ROOF DECK, LOCKER ROOM AND BATHROOM RECONSTRUCTION | 2019 | 600 | 2847.72 | 19 | 0 | 260 | 0 | 0 | 0 | 3126.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-304DWIT | De Witt Clinton Park | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 P-M245 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | DE WITT CLINTON PARK | DE WITT CLINTON PARK | 2019 | 500 | 207.82 | 0 | 0 | 0 | 1269 | 0 | 0 | 1476.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-304LRSQ | Little Red Square, Manhattan, MG-41350-115M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 302 | P-D018 P-1018 TF-0002 TF-0502 HW-0001M | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NYC PARKS DEPARTMENT -- LITTLE RED TRIANGLE -- RENOVATE EXISTING SITTING AREA AND EXPAND RECREATION SPACE | 2019 | 1140 | 258 | 1525 | 0 | 218 | 0 | 0 | 0 | 2001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-304MPPR | Mathews-Palmer Plgr-R/C North Side of Pk (M154-114M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 304 | P-D018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | MATTHEWS - PALMER PLGD RECON | MATTHEWS - PALMER PLGD RECON | 2019 | 1800 | 3164.09 | 0 | 0 | 0 | 92 | 0 | 0 | 3256.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-305MSEL | Madison Square Park Improvments, Manhattan | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-1011 P-M245 P-D018 |  | MADISON SQUARE PARK | MADISON SQUARE PARK CONSERVANCY : ETERNAL LIGHT FLAGSTAFF LANDSCAPE RENOVATION PROJECT. | 2019 | 3460 | 170 | 0 | 0 | 0 | 1500 | 0 | 0 | 1670 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 500
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-305UNIO | UNION SQUARE RECONSTRUCTION M089-198 | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 305 | WM-0001 WM-0006 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BROADWAY TO 4 AVE, E. 14 TO E 17 STS | EXPAND THE CENTER OVAL INTO UNUSED STREET BEDS, RECONSTRUCTION OF PAVERBS, STONE WALLS, WATER LINES, WATER SERVICE, SECURITY & STREET LIGHTITING. RELOCATE "GANDHI" STATUE | 2019 | 7961 | 6356.33 | 364 | 0 | 0 | 0 | 0 | 0 | 6720.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306ALNP | ASSER LEVY PLACE CONVERT TO PUBLIC PARK M164-113M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 306 | P-D018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | ASSER LEVY PLACE CONVERT TO PUBLIC PARK | ASSER LEVY PLACE CONVERT TO PUBLIC PARK | 2019 | 1500 | 1362.65 | 0 | 0 | 0 | 0 | 380 | 0 | 1742.65 | 499.52 | 0 | 0 | 0 | 0 | 0 | 0 | 499.52
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306APMU | Albano Playground Handball Court Multi-use Conve M265-117M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 306 | P-D018 P-0245M | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES |  | ALBANO PLAYGROUND HANDBALL COURT MULTI USE -- CONVERT HANDBALL COURT INTO MULTI USE SPACE | 2019 | 354 | 66.86 | 0 | 999 | 0 | 0 | 0 | 0 | 1065.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306ASLV | Asser Levy Recreation Center | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 P-M245 P-1250 |  | HVAC AT ASSER LEVY PLAYGROUND, MANHATTAN | HVAC AT ASSER LEVY PLAYGROUND | 2019 | 300 | 0 | 400 | 0 | 0 | 3004 | 296 | 0 | 3700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306GLIC | Glick Park | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | PU-0200 P-0501 |  | GLICK PARK | GLICK PARK | 2019 | 17276 | 0 | 963 | 0 | 13186 | 2877 | 250 | 0 | 17276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306STVA | St. Vartan Park - Manhattan | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-0245M |  |  | ST. VARTAN PARK - MANHATTAN | 2019 | 5613 | 0 | 0 | 0 | 0 | 4940 | 0 | 0 | 4940 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306TRPL | Tramway Plaza Irrigation | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 306 308 | P-D018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | DEPARTMENT OF PARKS & RECREATION -- FUNDING WILL SUPPORT IMPROVEDMENTS AT TRAMWAY PLAZA, ICLUDING IRRIGATION SYSTEM INSTALLATION AND CONSTRUCTION OF A FOUNTAIN | 2019 | 60 | 10 | 0 | 0 | 0 | 0 | 0 | 50 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306TUDO | Tudor Grove Playground - Manhattan | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-0245M P-D018 |  |  | TUDOR GROVE PLAYGROUND - MANHATTAN | 2019 | 500 | 0 | 0 | 0 | 500 | 500 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307BLOC | CPI PH2 - Bloomingdale Comfort Station (CONS) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-1018 P-M245 |  | CPI PH2 - BLOOMINGDALE PLGR COMFORT STATION RECO | CPI PH2 - BLOOMINGDALE PLGR COMFORT STATION RECO | 2019 | 1776 | 1204.9 | 0 | 0 | 0 | 304 | 0 | 0 | 1508.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307BLOP | CPI PH2 - Bloomingdale Playground (construction)- M238-217M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-1018 WP-0169 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | CPI PH2 - BLOOMINGDALE PLAYGROUND | FUNDS TO BE TRANSFERRED FROM P-307BLOO | 2019 | 6138 | 4389.03 | 381 | 566 | 461 | 0 | 0 | 0 | 5797.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307BMAP | BROADWAY MALLS - RECON & UPGRADE BROADWAY MALLS | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 307 309 312 | P-D018 P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BROADWAY MALLS - RECON & UPGRADE 14 MALLS | BROADWAY MALLS - RECON & UPGRADE 14 MALLS | 2019 | 400 | 1341.48 | 116 | 0 | 230 | 0 | 0 | 0 | 1687.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307RPKP | RIVERSIDE PARK - KAYAKING PROJECT: RESTORE KAYAK DOCK | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 300 | P-M245 P-D018 |  | RIVERSIDE PARK KAYAK DOCK 72ND STREET | RESTORE KAYAK DOCK AND RELATED INFRASTRUCTURE USED FOR FREE KAYAKINGPROGRAM AT 72ND ST. | 2019 | 810 | 0 | 0 | 0 | 0 | 195 | 0 | 210 | 405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307RPKS | RIVERSIDE PARK SOUTH - PHASE 5 M353-112M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 300 307 | P-0245M P-0380 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | RIVERSIDE PARK SOUTH - MILLER HGWY RELOC | 2019 | 10496 | 1608.96 | 1251 | 131 | 783 | 0 | 0 | 0 | 3773.96 | 18124.35 | 159 | 0 | 0 | 0 | 0 | 0 | 18283.35
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307RPPI | RVSD PK SOUTH-SHADE STRUCTURES, SOCCER FIELD, REC AREA M071 | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 307 | P-D018 P-0380 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RIVERSIDE PARK RECONSTRUCT TURF BALL FIELD, ADJACENT ACTIVE RECREATION AND SHADE STRUCTURE ON PIER I. | 2019 | 6485 | 1381.34 | 0 | 0 | 0 | 6082 | 0 | 0 | 7463.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307RPSB | Riverside Park South Ph. 5 Building | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 300 307 | P-0380 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RIVERSIDE PARK SOUTH PH. 5 BUILDING | 2019 | 2280 | 108.82 | 0 | 0 | 0 | 0 | 0 | 0 | 108.82 | 0 | 0 | 0 | 2713 | 0 | 0 | 0 | 2713
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307RPTH | Riverside Park RC Pathways 91st-95th Streets | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 P-0380 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | RIVERSIDE PARK RC PATHWAYS 91ST-95TH STREETS, MANHATTAN | RIVERSIDE PARK RC PATHWAYS 91ST-95TH STREETS | 2019 | 500 | 2089 | 0 | 0 | 0 | 436 | 0 | 0 | 2525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307RVSD | RIVERSIDE PK- CANTILEVER 83RD-91ST M071-297A | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 307 | P-0380 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | RIVERSIDE 133RD - 155TH STREET | RECON -FY'19E $1K ( P 0245M) B/L SWITCH TO P 0380... | 2019 | 10058 | 14835.76 | 0 | 0 | 0 | 0 | 43 | 0 | 14878.76 | 297 | 0 | 0 | 0 | 0 | 0 | 0 | 297
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307SAPO | MATTHEW P. SAPOLIN PARK PLAYGROUND: PLAYGROUND EQUIPMENT | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-M245 P-D018 |  | W. 70 BETWEEN W. END AVE AND AMSTERDAM | MATTHEW P. SAPOLIN PARK PLAYGROUND : PLAYGROUND EQUIPMENT UPGRADES | 2019 | 870 | 0 | 0 | 0 | 0 | 50 | 0 | 750 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307STGR | St. Gregory's Park Reconstruction (M301-114M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 307 | P-D018 P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NYC DPR - ST. GREGORY'S PARK -- PARK RECONSTRUCTION | 2019 | 1200 | 1271.3 | 0 | 0 | 111 | 0 | 0 | 0 | 1382.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307TRDR | Theodore Roosevelt Park Dog Run Renovation | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 307 | P-M245 P-D018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | NYC DPR - THEODORE ROOSEVELT PARK -- DOG RUN RENOVATION | 2019 | 300 | 193.14 | 0 | 441 | 242 | 0 | 0 | 0 | 876.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308AG02 | Asphalt Green- Pool Filter Upgrades | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | ASPHALT GREEN POOL FILTER UPGRADES | ASPHALT GREEN - POOL FILTER UPGRADES | 2019 | 713 | 0 | 0 | 713 | 0 | 0 | 0 | 0 | 713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308AG03 | ASPHALT GREEN LOBBY EXPANSION & LOCKER UPGRADES | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 |  |  | EXPANSION OF THE AQUACENTER LOBBY | 2019 | 1665 | 0 | 0 | 1665 | 0 | 0 | 0 | 0 | 1665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308AGDO | Ashphalt Green: Exterior Pedestrian Corridor, Manhattan | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-M245 |  |  | ASHPHALT GREEN: EXTERIOR PEDESTRIAN CORRIDOR, MANHATTAN | 2019 | 272 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308AGEE | Asphalt Green- Energy Efficiency, Manhattan | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 |  |  | FY19 SECT 254 CC ADD $738K (PD018).... | 2019 | 738 | 0 | 0 | 738 | 0 | 0 | 0 | 0 | 738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308AGFB | ASPHALT GREEN BOILER M286-114M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 308 | P-D018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | ASPHALT GREEN BOILER & BULKHEAD | ASPHALT GREEN BOILER & BULKHEAD | 2019 | 1130 | 588.63 | 0 | 80 | 0 | 0 | 0 | 0 | 668.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308AGPF | Asphalt Green Pool Filtration | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 300 | P-D018 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES | ASPHALT GREEN | ASPHALT GREEN-POOL FILTRATION | 2019 | 108 | 0 | 0 | 108 | 0 | 0 | 0 | 0 | 108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308CSPG | Carl Schurz Playground Reconstruction | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 308 | P-D018 P-M245 P-1018 |  |  | RECONSTRUCTION OF CARL SCHURZ PLAYGROUND | 2019 | 2848 | 424 | 3054 | 89 | 216 | 0 | 0 | 0 | 3783 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308CTHN | ST. CATHERINE'S PARK RECONSTRUCTION M079-104M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 308 | P-D018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 1ST AVENUE, EAST 67TH STREET, EAST 68TH STREET | ST CATHERINES PARK IN MANHATTAN - RECONSTRUCTION | 2019 | 665 | 499.06 | 0 | 0 | 0 | 0 | 66 | 0 | 565.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308EPOA | POA East River Esplanade Improvements, Manhattan | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-0501 |  |  | POA EAST RIVER ESPLANADE IMPROVEMENTS, MANHATTAN | 2019 | 15000 | 0 | 0 | 0 | 0 | 15000 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308EREI | East River Esplanade Improvements | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 |  | EAST RIVER ESPLANADE IMPROVEMENTS | EAST RIVER ESPLANADE IMPROVEMENTS | 2019 | 1450 | 264 | 0 | 0 | 1450 | 0 | 0 | 0 | 1714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308ERP2 | East River Esplanade Stabilization And Reconstruction PHASE | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 300 | P-D018 P-0501 |  |  | EAST RIVER ESPLANADE STABILIZATION AND RECONSTRUCTION PHASE | 2019 | 8366 | 0 | 0 | 0 | 3000 | 5366 | 0 | 0 | 8366 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308ERP3 | EAST RIVER ESPLANADE PHASE 3+ | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 300 | PU-0200 P-0501 P-1245 P-D018 |  | EAST RIVER ESPLANADE | EAST RIVER ESPLANADE | 2019 | 74350 | 0 | 696 | 0 | 40582 | 30259 | 0 | 0 | 71537 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308FFHM | ROOSEVELT ISL- 4 FREEDOMS HOPE DISABILITY MG-41250 | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 308 | P-D018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | ROOSEVELT ISL- 4 FREEDOMS HOPE DISABILITY | ROOSEVELT ISL- 4 FREEDOMS HOPE DISABILITY | 2019 | 150 | 35 | 150 | 0 | 0 | 0 | 0 | 0 | 185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308GRA1 | GRACIE MANSION CHILLER RC M081 | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 300 | P-0245M |  |  | GRACIE MANSION CHILLER RC M081 | 2019 | 926 | 858.36 | 0 | 0 | 0 | 66 | 0 | 0 | 924.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308HNYL | 14 HONEY LOCUSTS PARK, Manhattan | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | W-0013 P-0245M |  |  | 14 HONEY LOCUSTS PARK, MANHATTAN | 2019 | 1920 | 0 | 167 | 0 | 583 | 920 | 0 | 0 | 1670 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308JJPK | John Jay Green Space Improvements | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | JOHN JAY PARK GREEN SPACE IMPROVEMENTS | JOHN JAY PARK GREEN SPACE IMPROVEMENTS | 2019 | 50 | 0 | 0 | 0 | 0 | 400 | 0 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308MHM2 | MERCHANT HOUSE MUSEUM- EAST FACADE & SHUTTER RESTO M318 | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 300 302 | P-D018 P-M245 |  | MERCHANT HOUSE MUSEUM- EAST FACADE & SHUTTER RESTORATION, MANHATTAN | MERCHANT HOUSE MUSEUM- EAST FACADE & SHUTTER RESTORATION, MANHATTAN | 2019 | 300 | 28 | 0 | 740 | 0 | 0 | 0 | 0 | 768 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308MHMR | MERCHANT HOUSE MUSEUM RESTORATION M318-109M | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 300 302 | P-D018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | MERCHANT HOUSE MUSEUM RESTORATION | MERCHANT HOUSE MUSEUM RESTORATION | 2019 | 598 | 880.89 | -66 | 111 | 0 | 0 | 0 | 0 | 925.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308SPCS | 24 Sycamores Park C/S Renovation M108-116M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 308 | P-D018 |  |  | 24 SYCAMORES PARK -- RENOVATE BATHROOMS IN THE PARK | 2019 | 2040 | 235.8 | 0 | 1404 | 114 | 0 | 0 | 0 | 1753.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308STCP | St. Catherine's Park -- sportscoating iin the children's p | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | ÝDPRÛ ST. CATHERINE'S PARK -- IMPROVEMENTS TO THE SPORTSCOATING IN THE CHILDREN'S PLAY AREA | 2019 | 460 | 0 | 0 | 0 | 0 | 0 | 0 | 460 | 460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309B125 | PS 125 Playground Synthetic Turf Installation | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 P-M245 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | BASKETBALL COURT REPAIR AT PLAYGROUND 125TH ST | BASKETBALL COURT REPAIR AT PLAYGROUD 125TH ST | 2019 | 500 | 50 | 0 | 0 | 0 | 0 | 0 | 2000 | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309JRRC | Jackie Robinson Recreation Center HVAC System Reconstruction | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 300 309 310 | P-1250 |  | 85 BRADHURST AVENUE NEW YORK, NY 10039, MANHATTAN | JACKIE ROBINSON RECREATION CENTER HVAC SYSTEM RECONSTRUCTION | 2019 | 4000 | 0 | 0 | 0 | 0 | 2000 | 2000 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309JSPL | Jacob Schiff Playground Reconstruction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 P-0245M | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | JACOB SCHIFF PLAYGROUND, MANHATTAN | JACOB SCHIFF PLAYGROUND RECONSTRUCTION | 2019 | 300 | 164 | 0 | 1023 | 0 | 0 | 0 | 0 | 1187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309MOR2 | Morninside Pk- R/C of Plgr Phase 2 M056-116m | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 309 | P-D018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | MORNINGSIDE PARK 123RD ST PLGD PHASE 2 | MORNINGSIDE PARK 123RD ST PLGD PHASE 2 | 2019 | 1000 | 3079.13 | 0 | 0 | 0 | 636 | 0 | 0 | 3715.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309MPMP | Morningside Park: Renovation of Middle Playground | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-M245 P-D018 |  | MORNINGSIDE PARK | RENOVATION OF MIDDLE PLAYGROUND | 2019 | 1450 | 282.68 | 108 | 2964 | 414 | 650 | 0 | 0 | 4418.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309RBUS | RVSD DR -TIEMANN PL TO 97TH ST | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 307 309 | HW-0001M P-0380 P-M245 HW-1684 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | UPGRADE RIVERSIDE DRIVE BETWEEN 97TH ST. AND TIEMANN, NEW YORK CITY | 2019 | 2000 | 501.22 | 1188 | 0 | 309 | 0 | 0 | 0 | 1998.22 | 0 | 1448 | 0 | 0 | 0 | 0 | 0 | 1448
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309SKRP | Sakura Park - Reconstruction of the Staircase | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-M245 P-D018 P-1329 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | SAKURA PARK | RECONSTRUCTION OF THE STAIRCASE | 2019 | 425 | 206.72 | 101 | 0 | 0 | 1667 | 0 | 0 | 1974.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309SSTF | Jacob Schiff Playground Synthetic Turf Field Recon,Manhattan | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-0510 |  |  | JACOB SCHIFF PLAYGROUND SYNTHETIC TURF FIELD RECON,MANHATTAN | 2019 | 2919 | 0 | 0 | 0 | 525 | 2394 | 0 | 0 | 2919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309STNC | ST NICHOLAS NORTH COMFORT STATION M211-110MA2 | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 309 | P-D018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | ST NICHOLAS PARK NORTH COMFORT STATION | ST NICHOLAS PARK NORTH COMFORT STATION | 2019 | 1300 | 1649.07 | 0 | 0 | 0 | 123 | 0 | 0 | 1772.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3107STP | 107TH Street Pier Renovation M108-216M | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 311 | ED-D401 P-M245 P-1018 |  |  | 107TH STREET PIER RENOVATION | 2019 | 250 | 130.21 | 0 | 250 | 0 | 0 | 0 | 387 | 767.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-310CCPG | Courtney Callendar Playground-handball court | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | COURTNEY CALLENDAR PLAYGROUND | R/C OF SITTING AREA AT COURTNEY CALLENDAR PLAYGROUND | 2019 | 100 | 56 | 0 | 378 | 0 | 0 | 0 | 0 | 434 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-310CCYB | COLONEL CHARLES YOUNG PK - BASEBALL FLDS RENOVATION M186 | NEIGHBORHOOD PARKS AND PLAYGROUNDS |  | P-D018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | COLONEL YOUNG PARK - RENOVATION OF BASEBALL FIELDS | 2019 | 1000 | 75 | 0 | 0 | 0 | 0 | 0 | 751 | 826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-310FJTC | FRED JOHNSON TENNIS COURTS RENOVATION M159-111M | NEIGHBORHOOD PARKS AND PLAYGROUNDS |  | P-M245 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES |  | FRED JOHNSON TENNIS COURTS - RENOVATION OF FRED JOHNSON TENNIS COURTS | 2019 | 750 | 768.1 | 0 | 0 | 0 | 0 | 78 | 0 | 846.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-310HCOM | HANSBOROUGH REC CTR COMPUTER PURCHASE M131 | VEHICLES AND EQUIPMENT | 310 | P-M245 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | HANSBOROUGH REC CTR COMPUTER PURCHASE, 35 WEST 134TH STREET | HANSBOROUGH REC CTR COMPUTER PURCHASE | 2019 | 45 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-310HRFT | HANSBORO RC CTR REFURB GYM FL & TRACK SURFACE M131-114M | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 300 310 | P-D018 |  | HANSBORO RC CTR REFURB GYM FL & TRACK SURFACE | HANSBORO RC CTR REFURB GYM FL & TRACK SURFACE | 2019 | 500 | 680.02 | 0 | 0 | 0 | 64 | 0 | 0 | 744.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-310JRGY | Jackie Robinson Rec Ctr-replace gym floor | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 P-M245 |  | JACKIE ROBINSON REC CTR | REPLACE GYM FLOOR | 2019 | 210 | 15 | 0 | 0 | 0 | 0 | 0 | 538 | 553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311HCTR | HIGHBRIDGE RECREATION CTR -RC BOILERS AND HVAC | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-1250 P-D018 |  | MANHATTAN | HIGHBRIDGE RECREATION CTR RC | 2019 | 3272 | 255 | 7 | 0 | 2525 | 468 | 0 | 0 | 3255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311HEL3 | Phase 3 of Hell Gate Pathway, below Viaduct Randalls Island | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | WP-0112 P-X245 | PROJECT DELAYED PENDING NON-CITY GRANT APPROVAL | PH 3 OF HELL GATE PATHWAY | PH 3 OF HELL GATE PATHWAY | 2019 | 3140 | 403.63 | 596 | 0 | 0 | 140 | 0 | 0 | 1139.63 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 3000
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311HWTR | HIGHBRIDGE AQUEDUCT WATER TOWER RESTORATION M037-113M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 312 | P-D018 P-0245M P-1018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | HIGHBRIDGE AQUEDUCT WATER TOWER RESTORATION, MANHATTAN | HIGHBRIDGE AQUEDUCT WATER TOWER RESTORATION INCLUDING ROOF AND WINDOWS | 2019 | 742 | 309.27 | 4798 | 0 | 0 | 0 | 0 | 0 | 5107.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311MGFI | MARCUS GARVEY PK FIRE WATCHTOWER RESTORATION M058-115M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-1018 |  | MARCUS GARVEY PK | FIRE WATCH TOWER RESTORATION | 2019 | 280 | 5953.24 | 69 | 45 | 1126 | 0 | 0 | 0 | 7193.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311MGLL | MARCUS GARVEY CS LITTLE LEAGUE FACILTY M058-116M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 311 | P-0475 P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | MARCUS GARVEY LITTLE LEAGUE BLDG | MARCUS GARVEY LITTLE LEAGUE BLDG | 2019 | 400 | 1580.08 | 154 | 0 | 162 | 0 | 0 | 0 | 1896.08 | 2217.02 | 13 | 0 | 0 | 0 | 0 | 0 | 2230.02
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311PFRI | MARCUS GARVEY PK - PELHAM FRITZ RECREATION CTR CONS M058 | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 300 | P-D018 P-0506 |  |  | MARCUS GARVEY PK - PELHAM FRITZ RECREATION CTR CONS M058 | 2019 | 750 | 136 | 0 | 0 | 0 | 1000 | 0 | 0 | 1136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311PRPL | Poor Richard's Playground Renovations | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 P-0245M | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | POOR RICHARD'S PLAYGROUND RENOVATIONS, MANHATTAN | POOR RICHARDS PLAYGROUND RENOVATIONS | 2019 | 950 | 1387.73 | 0 | 0 | 0 | 207 | 0 | 0 | 1594.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311RIFW | RANDALL'S ISLAND FRESHWATER WETLANDS PATHWAY M104 M107 111M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 300 311 | P-0245M | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES | RANDALL'S ISLAND FRESHWATER WETLANDS PATHWAY | RANDALL'S ISLAND FRESHWATER WETLANDS PATHWAY, MANHATTAN | 2019 | 2208 | 497.92 | 0 | 0 | 0 | 0 | 0 | 0 | 497.92 | 1245.83 | 962 | 0 | 0 | 0 | 0 | 0 | 2207.83
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311RILS | RANDALLS ISLAND LIVING SHORELINE M104-116M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 300 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | RANDALLS ISLAND | PORTION OF RANDALLS ISLAND LIVING SHORELINE | 2019 | 1798 | 1335.17 | 0 | 0 | 0 | 186 | 0 | 0 | 1521.17 | 1317.87 | 0 | 0 | 0 | 0 | 0 | 0 | 1317.87
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311TJHV | THOMAS JEFFERSON PARK REC CTR HVAC M047-109M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 311 | P-0245M | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | THOMAS JEFFERSON PARK REC CTR HVAC | THOMAS JEFFERSON PARK REC CTR HVAC | 2019 | 1000 | 320.4 | 0 | 0 | 0 | 0 | 0 | 0 | 320.4 | 646.92 | 0 | 0 | 123 | 0 | 0 | 0 | 769.92
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311TJPK | Thomas Jefferson Park Renovations | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 P-1018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | THOMAS JEFFERSON PARK RENOVATIONS, MANHATTAN | THOMAS JEFFERSON PARK RENOVATIONS | 2019 | 350 | 103 | 0 | 415 | 232 | 0 | 0 | 0 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311TURF | Harlem River Park field ( at 128th st)- Synthetic Turf, Manh | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-0510 |  |  | HARLEM RIVER PARK FIELD ( AT 128TH ST)- SYNTHETIC TURF, MANHATTAN | 2019 | 6650 | 0 | 0 | 0 | 0 | 6300 | 0 | 0 | 6300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312DFAR | DYCKMAN FARMHOUSE : ADA RAMP AND BATHROOM RENOVATION | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 P-M245 |  | DYCKMAN FARMHOUSE | DYCKMAN FARMHOUSE : ADA RAMP AND BATHROOM RENOVATION | 2019 | 750 | 0 | 0 | 0 | 850 | 0 | 0 | 0 | 850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312DMAR | DYCKMAN MARINA ECO DOCK RC M028 | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 312 | P-M245 P-D018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | DYCKMAN MARINA ECO DOCK RECON | DYCKMAN MARINA ECO DOCK RECON | 2019 | 350 | 62 | 0 | 0 | 458 | 0 | 0 | 0 | 520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312DYC2 | DYCKMAN FARMHOUSE RC | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 300 | P-D018 P-0245M |  |  | DYCKMAN FARMHOUSE RC | 2019 | 5616 | 0 | 900 | 616 | 0 | 4100 | 0 | 0 | 5616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312FTSR | FT TRYON PARK STAIRCASE M029-111M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 312 | P-M245 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | RIVERSIDE DRIVE - WEST 192ND ST. TO DYCKMAN ST. | FT. TRYON PARK STAIRCASE RENOVATION | 2019 | 600 | 1703.39 | 0 | 0 | 0 | 256 | 0 | 0 | 1959.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312IHLL | INWOOD HILL PARK LITTLE LEAGUE BASEBALL FIELD LIGHTING M042 | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 312 | P-D018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | INWOOD HILL PARK LITTLE LEAGUE BASEBALL FIELD LIGHTING | INWOOD HILL PARK LITTLE LEAGUE BASEBALL FIELD LIGHTING | 2019 | 200 | 40 | 0 | 0 | 0 | 0 | 0 | 200 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312IHPB | INWOOD HILL PK SANITARY SEWER FOR NATURE CTR M042-115M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 300 312 | P-D018 P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | INWOOD HILL PARK BATHROOM RECON | INWOOD HILL PARK BATHROOM RECON | 2019 | 250 | 1167.06 | 0 | 0 | 0 | 102 | 0 | 0 | 1269.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312INNC | Inwood Hill Nature Center M042 -116M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 P-1018 |  | INWOOD NATURE CENTER, MANHATTAN | INWOOD NATURE CENTER | 2019 | 100 | 11.67 | 18 | 0 | 0 | 1652 | 0 | 0 | 1681.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312INNG | RIVERSIDE-INWOOD NEIGHBORHOOD GARDENS, INC. | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-M245 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | RIVERSIDE-INWOOD NEIGHBORHOOD GARDENS, INC: RING GARDEN PROJECT | RIVERSIDE-INWOOD NEIGHBORHOOD GARDENS, INC. : RING GARDEN PROJECT | 2019 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312INWD | Inwood Hill Nature Center- Exhibit Display Reconstruction | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 300 | P-1018 |  | INWOOD HILL NATURE CENTER, MANHATTAN | RECONSTRUCTION OF THE EXHIBIT DISPLAY AT INWOOD HILL NATURE CENTER | 2019 | 268 | 0 | 75 | 193 | 0 | 0 | 0 | 0 | 268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312ISA2 | ISHAM PARK IRRIGATION & DRINK FOUNTAINS M043 M43112 | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 312 | P-D018 |  | ISHAM PARK IRRIGATION & DRINK FOUNTAINS | ISHAM PARK IRRIGATION & DRINK FOUNTAINS | 2019 | 750 | 1064.11 | 0 | 0 | 0 | 60 | 0 | 0 | 1124.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312JHRW | J HOOD WRIGHT PARK REC CTR WINDOWS M099 | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 312 | P-D018 |  | J HOOD WRIGHT PARK REC CTR WINDOWS | J HOOD WRIGHT PARK REC CTR WINDOWS | 2019 | 75 | 16 | 0 | 0 | 0 | 0 | 0 | 175 | 191 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312JJPG | Jacob Javits Plgr-renovation | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | JACOB JAVITS PLGR | PLGR RENOVATION | 2019 | 1640 | 2873.54 | 0 | 0 | 0 | 284 | 0 | 0 | 3157.54 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 350
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312MJM2 | Morris Jumel mansion - exterior renovation- ph II M073 | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 300 312 | P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | MORRIS JUMEL MANSION EXTERIOR (PERIMETER STREETSCAPE AND STONE WALLS)PHASE 2 RECONSTRUCTION, MANHATTAN | MORRIS JUMEL MANSION EXTERIOR (PERIMETER STREETSCAPE AND STONE WALLS)RECONSTRUCTION | 2019 | 1500 | 457.21 | 0 | 0 | 0 | 0 | 0 | 0 | 457.21 | 1371.94 | 0 | 128 | 0 | 0 | 0 | 0 | 1499.94
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312MJMR | Morris Jumel mansion - exterior renovation | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 312 | P-D018 P-0245M P-M094 P-M245 |  | MORRIS JUMEL MANSION - | MORRIS JUMEL MANSION - EXTERIOR RENOVATION | 2019 | 1050 | 113 | 162 | 550 | 1020 | 0 | 0 | 0 | 1845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-313CPA2 | CENTRAL PARK - ARSENAL ELEVATOR RC M010-616M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 300 | P-1018 |  |  | CENTRAL PARK - ARSENAL ELEVATOR RC M010 | 2019 | 1546 | 1050.33 | 0 | 0 | 147 | 258 | 0 | 0 | 1455.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-313CPAB | CENTRAL PARK - ARSENAL BRICK FACADE M010-214M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 300 | P-1018 |  |  | RC OF ARSENAL BRICK FACADE ALONG THE 4TH FLOOR SE TURRET 5TH FLOOR ELEVATOR TURRET | 2019 | 1133 | 2368.72 | 401 | 0 | 0 | 1240 | 0 | 0 | 4009.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-313CPSW | Central Park - Swedish Cottage M010-116M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 300 304 305 307 308 310 311 | P-D018 P-D933 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES | CENTRAL PARK - SWEDISH COTTAGE, MANHATTAN | CENTRAL PARK - SWEDISH COTTAGE, MANHATTAN | 2019 | 120 | 13 | 0 | 240 | 819 | 0 | 0 | 0 | 1072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ANCH02 | Highbridge Anchor Park Phase II- Manhattan M037-118M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-0415A |  |  | HIGHBRIDGE ANCHOR PARK PHASE II- MANHATTAN | 2019 | 13740 | 0.54 | 0 | 13540 | 0 | 0 | 0 | 0 | 13540.54 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 500
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ANCH03 | Highbridge Anchor Park Phase III- COMFORT STATION, M037-118M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-0415A |  |  | HIGHBRIDGE ANCHOR PARK PHASE III- COMFORT STATION, MANHATTAN | 2019 | 4364 | 0 | 0 | 0 | 0 | 3200 | 0 | 0 | 3200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ANCH04 | Highbridge Anchor Park Reconstruction Phase I, Manhattan | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-0415A P-1018 P-D018 |  |  | HIGHBRIDGE ANCHOR PARK RECONSTRUCTION PHASE I, MANHATTAN | 2019 | 10260 | 0 | 9166 | 0 | 0 | 1620 | 0 | 0 | 10786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ANNEPG | ANNE LOFTUS PLAYGROUND//WATER PARK, Mahattan | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 |  |  | ANNE LOFTUS PLAYGROUND//WATER PARK, MAHATTAN | 2019 | 5701 | 230 | 0 | 0 | 0 | 4181 | 0 | 0 | 4411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ASGRGN | ASPHALT GREEN: EMERGENCY GENERATOR PROJECT | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-M245 |  |  | ASPHALT GREEN, INC.: EMERGENCY GENERATOR PROJECT | 2019 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BBASIN | Riverside Park- Moving Costs Associated With The 79th Street | VEHICLES AND EQUIPMENT | 300 | P-0245M |  | 698 WEST 135TH STREET, NEW YORK, NEW YORK 10031 | THE RELOCATION OF THE RIVERSIDE PARK DISTRICT M&O OPERATIONS OUT OF THE W79TH ROTUNDA, MANHATTAN | 2019 | 493 | 0 | 387 | 0 | 0 | 0 | 0 | 0 | 387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BBGARD | BATTERY PARK SEAGLASS CAROUSEL M005-208M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 301 | P-0828 P-D018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BATTERY PARK CAROUSEL | BATTERY PARK CAROUSEL | 2019 | 8230 | 5528.52 | 25 | 0 | 0 | 101 | 0 | 0 | 5654.52 | 7050 | 0 | 0 | 0 | 0 | 0 | 0 | 7050
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BELLVU | BELLEVUE PARK SOUTH, Mahattan | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 P-M245 P-0245M |  |  | BELLEVUE PARK SOUTH, MAHATTAN | 2019 | 1500 | 100 | 0 | 0 | 4243 | 368 | 0 | 0 | 4711 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BENNSF | BENNETT PARK SYNTHETIC FIELD | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-M245 |  |  | BENNETT PARK SYNTHETIC FIELD: INSTALLATION OF SYNTHETIC FIELD | 2019 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BOOKTW | BOOKER T WASHINGTON Plg Synthetic Turf Rpl, Mahattan | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 P-0510 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BOOKER T WASHINGTON PLAYGROUND--SYNTHETIC TURF REPLACEMENT | 2019 | 136 | 40 | 0 | 0 | 1845 | 0 | 0 | 0 | 1885 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BPPLGD | BATTERY PARK PLAYGROUND (SOUTH FERRY-MTA) M005 | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 301 | P-0828 P-M245 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | BATTERY PARK PLAYGROUND (SOUTH FERRY-MTA) | BATTERY PARK PLAYGROUND (SOUTH FERRY-MTA) | 2019 | 5100 | 263.37 | 0 | 0 | 350 | 0 | 0 | 0 | 613.37 | 683.6 | 0 | 12227 | 739 | 0 | 0 | 0 | 13649.6
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BWWATE | RPZ - WATER SERVICE INSTALLATION | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 300 | P-1018 P-1250 P-M245 P-D018 |  |  | RPZ - WATER SERVICE INSTALLATION | 2019 | 340 | 59 | 0 | 0 | 199 | 469 | 0 | 0 | 727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CATHE1 | LOCKER ROOM RENOVATION 80 CATHERINE ST. | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 300 | P-D018 |  |  | LOCKER ROOM RENOVATION 80 CATHERINE ST. | 2019 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CENT04 | Central Park - Recon West Side Landscape M010-614M WO# 4 | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 300 | P-1300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CENTRAL PARK - RECON WEST SIDE LANDSCAPE M010-614M WO# 4 | 2019 | 2462 | 2238.12 | 0 | 0 | 0 | 224 | 0 | 0 | 2462.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CENT05 | Central Park - Recon of CPW Perimeter M010-614M WO# 5 | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 300 | P-1300 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CENTRAL PARK - RECON OF CPW PERIMETER M010-614M WO# 5 | 2019 | 2420 | 2200 | 0 | 0 | 0 | 220 | 0 | 0 | 2420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CENT08 | Central Park - Recons of Perimeter E84-E108ST WO# 8 | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 300 | P-1300 |  |  | RECONSTRUCTION OF THE PARK PERIMETER LOCATED BETWEEN E84-E109 ST., CENTRAL PARK | 2019 | 0 | 4395 | 0 | 0 | 0 | 425 | 0 | 0 | 4820 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CENT13 | Recon. of Naumburg Bandshell in Central Park, WO#13, | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 300 | P-1300 |  |  | RECON. OF NAUMBURG BANDSHELL IN CENTRAL PARK, WO#13, | 2019 | 6927 | 0 | 0 | 6297 | 0 | 630 | 0 | 0 | 6927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CENTA | Central Park - Construction for Maintanence & Operation | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 300 | P-1300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | CENTRAL PARK | CENTRAL PARK - CONSTRUCTION SERVICES FOR MAINTANENCE & OPERATION | 2019 | 57378 | 0 | 0 | 0 | 4245 | 9622 | 7824 | 42728 | 64419 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3COLUMB | COLUMBUS PARK - Entrance Renovation, Manhattan | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 P-1018 |  | COLUMBUS PARK - ENTRANCE RENOVATION -- TURN THE MULBERRY ST. ENTRANCESTEPS AT COLUMBUS PARK (MANHATTAN) INTO A RAMP | COLUMBUS PARK - ENTRANCE RENOVATION -- TURN THE MULBERRY ST. ENTRANCESTEPS AT COLUMBUS PARK (MANHATTAN) INTO A RAMP | 2019 | 219 | 53 | 219 | 248 | 0 | 0 | 0 | 0 | 520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPI3A2 | CPI PH2 - ABRAHAM LINCOLN CS RC | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-1018 |  |  | CPI PH3 - ABRAHAM LINCOLN CS RC | 2019 | 1940 | 298 | 1445 | 195 | 0 | 0 | 0 | 0 | 1938 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPI3AB | CPI PH2 - Audubon Plg & Comf Reconstruction (DESIGN) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-1018 |  |  | CPI PH3 - AUDUBON PLAYGROUND RECONSTRUCTION | 2019 | 5909 | 995.28 | 0 | 275 | 0 | 0 | 0 | 0 | 1270.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPI3AC | CPI PH2 - Audubon Comfort Station Recons M240-218M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-1018 |  |  | CPI PH2 - AUDUBON COMFORT STATION RECONSTRUCTION | 2019 | 2100 | 0 | 24 | 1339 | 137 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPI3AL | CPI PH2 - Abraham Lincoln plg .... | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-1018 |  |  | CPI PH3 - ABRAHAM LINCOLN PLG & COMFORT STATION RECONS.. | 2019 | 8932 | 660 | 0 | 0 | 0 | 8080 | 0 | 0 | 8740 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPI3AP | CPI PH2 - Audubon Playground Reconst M240-118M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-1018 |  |  | CPI PH2 - AUDUBON PLAYGROUND RECONSTRUCTION | 2019 | 3320 | 0 | 5882 | 0 | 0 | 1256 | 0 | 0 | 7138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIBBJ | CPI PH2 - Bill Bojangles Playground | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-1018 |  |  | CPI PH2 - BILL BOJANLES PLAYGROUND | 2019 | 1590 | 128 | 0 | 0 | 1590 | 0 | 0 | 0 | 1718 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIBN9 | CPI PH1 Plg 103 and St Nicholas North Plg Recons (MG-216M) | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 300 | P-1018 |  |  |  | 2019 | 10861 | 8797.62 | 12 | 0 | 0 | 0 | 177 | 0 | 8986.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIFGC | CPI PH2 - Frederick Johnson Comfort Station, M141-418M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-1018 |  |  | FY19 PENDING TRANSFER.... | 2019 | 5200 | 0 | 0 | 0 | 3023 | 0 | 0 | 0 | 3023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIFJP | CPI PH2 -Frederick Johnson Playground M159-219M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-1018 |  |  | CPI PH2 -FREDERICK JOHNSON PLAYGROUND M141-218M | 2019 | 5300 | 0 | 0 | 0 | 5740 | 0 | 0 | 0 | 5740 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIHLP | CPI PH2 - Harlem Lane Playground, M141-318M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-0245M P-1018 |  |  | CPI PH2 - HARLEM LANE PLAYGROUND, M141-318M | 2019 | 7930 | 0 | 0 | 0 | 8417 | 0 | 0 | 0 | 8417 | 0 | 0 | 950 | 0 | 0 | 0 | 0 | 950
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIMLK | CPI - Phase 1-Martin L.King Plgr, Manhattan | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-1018 |  | CPI - PHASE 1-MARTIN L.KING PLGR, MANHATTAN | CPI - PHASE 1-MARTIN L.KING PLGR | 2019 | 5588 | 4291.1 | 24 | 0 | 0 | 163 | 0 | 0 | 4478.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIPGI | CPI PH2 -Playground One, M196-118M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-1018 |  |  | CPI PH2 -PLAYGROUND ONE | 2019 | 2801 | 226 | 3118 | 0 | 336 | 0 | 0 | 0 | 3680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPISUR | CPI PH2 - Sauer Playground | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-1018 |  |  | CPI PH2 - SAUER PLAYGROUND | 2019 | 4067 | 300 | 0 | 3579 | 488 | 0 | 0 | 0 | 4367 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3DAGHAM | Dag Hammarskjold Plaza, Manhattan | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | PARKS -- IMPROVEMENTS TO DAG HAMMARSKJOLD PLAZA -- FUNDING WILL PROVIDE CAPITAL IMPROVEMENTS TO DAG HAMMARSKJOLD PLAZA | PARKS -- IMPROVEMENTS TO DAG HAMMARSKJOLD PLAZA -- FUNDING WILL PROVIDE CAPITAL IMPROVEMENTS TO DAG HAMMARSKJOLD PLAZA | 2019 | 920 | 303 | 0 | 0 | 0 | 1030 | 0 | 0 | 1333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3DELURY | Delury Square Renovation- Manhattan | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | PARK REDESIGN -- REDESIGN DELURY SQ. PARK IN LOWER MANHATTAN | PARK REDESIGN -- REDESIGN DELURY SQ. PARK IN LOWER MANHATTAN | 2019 | 77 | 37 | 0 | 0 | 0 | 202 | 0 | 0 | 239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3EMRCPK | Emergency transformer svc to SummerStage at Central Pk | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 300 | P-1018 |  | SUMMERSTAGE AT RUMSEY PLAYFIELD IN CENTRAL PARK IN MANHATTAN | EMERGENCY DECLARATION OF THE RECONSTRUCTION OF SITE TRANSFORMER ELECTRICAL SERVICE TO SUMMERSTAGE AT RUMSEY PLAYFIELD IN CENTRAL PARK, IN THE BOROUGH OF MANHATTAN. | 2019 | 578 | 525.3 | 6 | 0 | 0 | 47 | 0 | 0 | 578.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3EMRTRN | Emergency replace of Randalls Island transformer M104-118M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 300 | P-1018 |  | RANDALS ISLAND | EMERGENCY REPLACEMENT OF RANDALLS ISLAND TRANSFORMER | 2019 | 1062 | 139.77 | 673 | 0 | 0 | 249 | 0 | 0 | 1061.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ESSTAT | ELIZABETH CADY STANTON AND SUSAN B. ANTHONY STATUE FUND INC | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 300 | P-M245 P-D018 |  | ELIZABETH CADY STANTON AND SUSAN B. ANTHONY STATUE FUND INC. : ELIZABETH CADY STANTON AND SUSAN B. ANTHONY WOMAN SUFFRAGE MOVEMENT | ELIZABETH CADY STANTON AND SUSAN B. ANTHONY STATUE FUND INC. : ELIZABETH CADY STANTON AND SUSAN B. ANTHONY WOMAN SUFFRAGE MOVEMENT | 2019 | 635 | 0 | 0 | 0 | 135 | 0 | 0 | 0 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3FFAGAN | FATHER FAGAN PK LANDSCAPE RECON, MG-512M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 302 | P-D018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | FATHER FAGAN PK LANDSCAPE RECON | FATHER FAGAN PK LANDSCAPE RECON | 2019 | 1500 | 2250.19 | 0 | 0 | 0 | 337 | 0 | 0 | 2587.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3FTTRYN | FT. TRYON PARK--UPDATES TO DOG RUN, Manhattan | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | P-3FTTRYN | 2019 | 173 | 0 | 0 | 0 | 0 | 0 | 0 | 127 | 127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3GMHVAC | Gracie Mansion Improvements | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 300 | P-0245M P-1018 |  |  | GRACIE MANSION HVAC M081 | 2019 | 3217 | 0 | 0 | 0 | 600 | 2899 | 0 | 0 | 3499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3GTACQM | Land Acuisition: Green Thumb on 143rd ST, Manhattan | LAND ACQUISITION AND TREE PLANTING | 300 | P-D056 P-M056 P-M245 |  |  | LAND ACUISITION: GREEN THUMB ON 143RD ST, MANHATTAN | 2019 | 300 | 0 | 10 | 0 | 940 | 0 | 0 | 0 | 950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HBCGRD | Highbridge Community Garden | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | HIGHBRIDGE COMMUNITY GARDEN | HIGHBRIDGE COMMUNITY GARDEN | 2019 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HELIP2 | Heliport(Andrew Haswell) Park - phase 2 M108-109M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 308 | P-D018 P-1018 | PROJECT DELAYED DUE TO UNFORESEEN HAZARDOUS CONDITION | HELIPORT PARK CONSTRUCTION PHASE 2 | HELIPORT PARK CONSTRUCTION PHASE 2 | 2019 | 2500 | 3432.62 | 27 | 266 | 0 | 0 | 0 | 0 | 3725.62 | 1550 | 0 | 0 | 0 | 0 | 0 | 0 | 1550
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HELLKT | DEP Shaft Site - Hell's Kitchen Park Construction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | W-0013 P-D018 |  |  | RIVERSIDE PARK--101ST STAIRCASE PROJECT | 2019 | 200 | 0 | 400 | 0 | 900 | 1300 | 0 | 0 | 2600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HIGHL3 | FRIENDS OF THE HIGH LINE- Western Rail Yards, Manhattan | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 |  |  | THE HIGH LINE: LIGHTING AND SECURITY -- WESTERN RAIL YARDS: LIGHTING AND SECURITY; THE HIGH LINE: RUST AND CONCRETE -- WESTERN RAIL YARDS: RUST AND CONCRETE REPAIR; THE HIGH LINE: DRAINAGE -- WESTERN RAIL YARDS: DRAINAGE | 2019 | 2700 | 0 | 0 | 2700 | 0 | 0 | 0 | 0 | 2700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HLNSTR | FRIENDS OF THE HIGHLINE: HIGH LINE STAIR RECONSTRUCTION | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-M245 |  |  | FRIENDS OF THE HIGHLINE: HIGH LINE STAIR RECONSTRUCTION AND RENOVATIONS | 2019 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRCAMR | HRPT- CAMERAS | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 |  | BOROUGH OF MANHATTAN | HUDSON RIVER PARK TRUST--CAMERAS | 2019 | 230 | 32 | 0 | 174 | 0 | 0 | 0 | 0 | 206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRLGBT | HRPT - Christopher St. LGBTQ Memorial, Manhattan | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 300 | P-D018 |  |  | HRPT - CHRISTOPHER ST. LGBTQ MEMORIAL, MANHATTAN | 2019 | 440 | 0 | 426 | 0 | 0 | 0 | 0 | 0 | 426 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRP26U | HRPT: Pier 26 Upland Construction | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 300 | P-1246 |  |  | HRPT | 2019 | 4609 | 0 | 0 | 4609 | 0 | 0 | 0 | 0 | 4609 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRP40W | HRPT: Pier 40 Elevated Walkway Reconstruction | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 300 | P-1246 |  | HRPT: PIER 40 ELEVATED WALKWAY RECONSTRUCTION | HRPT: PIER 40 ELEVATED WALKWAY RECONSTRUCTION | 2019 | 763 | 0 | 0 | 763 | 0 | 0 | 0 | 0 | 763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPCCV | HRPT-Clinton Cove Sculpture/Landscaping | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 |  | HUDSON RIVER PARK TRUST CLINTON COVE LANDSCAPING | HUDSON RIVER PARK TRUST CLINTON COVE LANDSCAPING | 2019 | 65 | 0 | 0 | 465 | 0 | 0 | 0 | 0 | 465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPCWP | HRP - Chelsea Waterside Park Restore Safety Surface | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 |  | CHELSEA WATERSIDE PARK RESTORE SAFETY SURFACE | CHELSEA WATERSIDE PARK RESTORE SAFETY SURFACE | 2019 | 170 | 0 | 0 | 340 | 0 | 0 | 0 | 0 | 340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPDG8 | HUDSON RIVER PARK TRUST PIER 84 DOG RUN | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-M245 |  |  | HUDSON RIVER PARK TRUST RENOVATION TO PIER 84 DOG RUN | 2019 | 0 | 0 | 0 | 175 | 0 | 0 | 0 | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPGRD | HRP- Tree Grinder | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 300 | S-D129 P-1246 |  | BOROUGH OF MANHATTAN | TREE GRINDER -HRP | 2019 | 47 | 0 | 30 | 5 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPLGS | HRPT- Pier 51 Playground Safety Surface | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 P-M245 |  |  | HRPT: PLAYGROUND SURFACE | 2019 | 100 | 0 | 0 | 1121 | 0 | 0 | 0 | 0 | 1121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPP40 | Hudson River Park Trust - Pier 40 Repairs | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 300 | P-1246 |  |  | PIER 40 REPAIRS | 2019 | 10645 | 0 | 0 | 1237 | 8315 | 0 | 0 | 0 | 9552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPP45 | HRP TRUST - PIER 45: HEX PAVER RESTORATION PROJECT | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 300 | P-M245 P-D018 |  | HUDSON RIVER PARK PIER 45 | HUDSON RIVER PARK TRUST - PIER 45 : PIER 45 PROJECT - HEX PAVER RESTORATION PROJECT | 2019 | 230 | 0 | 0 | 800 | 0 | 0 | 0 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPP84 | HRP: Pier 84 Hex Paver Reconstruction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 |  | HUDSON RIVER PARK TRUST WATER FEATURES/DOG RUN PIER 84 | HUDSON RIVER PARK TRUST WATER FEATURES/DOG RUN PIER 84 | 2019 | 89 | 0 | 660 | 0 | 0 | 0 | 0 | 0 | 660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPT34 | HUDSON RIVER PARK | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-1246 |  |  | HUDSON RIVER PARK | 2019 | 3400 | 0 | 0 | 0 | 0 | 3409 | 0 | 0 | 3409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPTHS | Hudson River Park Trust - Pier 25 Playground | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 300 | P-D018 P-M245 |  | HRPT HARRISON ST ENTRANCE OVERLOOK | HRPT HARRISON ST ENTRANCE OVERLOOK | 2019 | 76 | 0 | 90 | 424 | 0 | 0 | 0 | 0 | 514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPTPK | Hudson River Park Trust, Manhattan | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 300 | P-1246 |  | HUDSON RIVER PARK | HUDSON RIVER PARK TRUST | 2019 | 50000 | 0 | 0 | 12900 | 39400 | 20700 | 0 | 0 | 73000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3INHIL3 | INWOOD HILL PARK- Dog run, Manhattan | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | INWOOD HILL PARK- DOG RUN, MANHATTAN | 2019 | 173 | 0 | 0 | 0 | 0 | 0 | 0 | 127 | 127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3INHILL | Inwood Hill Park - baseball field, Manhattan | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 |  |  | INWOOD HILL PARK- BASEBALL, SOCCER, & DOG RUN, MANHATTAN | 2019 | 682 | 0 | 0 | 0 | 0 | 1432 | 0 | 0 | 1432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3JDWACQ | Land Acuisition: JD Wilson Garden Harlem, Manhattan | LAND ACQUISITION AND TREE PLANTING | 300 | P-M056 |  |  | LAND ACUISITION: JD WILSON GARDEN HARLEM, MANHATTAN | 2019 | 1300 | 55 | 0 | 0 | 1300 | 0 | 0 | 0 | 1355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3LASKE1 | Lasker - RC. Pool & Ice Rink M010-516M | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 300 | P-1018 P-1300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | LOCATED AT HARLEM MEER & 110 STREET IN CENTRAL PARK, BOROUGH OF MANHATTAN. | FY'16 NEW NEEDS FOR RC OF LASKET POOL & ICE RINK | 2019 | 15919 | 1443 | -66 | 66 | 44826 | 4482 | 0 | 0 | 50751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3LGBATH | La Guardia Bathhouse Demolition | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 300 | P-1018 |  |  | LA GUARDIA BATHHOUSE DEMOLITION | 2019 | 10000 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3LGGRDN | LAGUARDIA CORNER GARDEN FENCE, Mahattan | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 |  |  | LAGUARDIA CORNER GARDEN FENCE | 2019 | 340 | 45 | 0 | 0 | 322 | 28 | 0 | 0 | 395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3LMDCCH | LMDC - Corlear's Hook Comfort Station M017-216M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-0245M | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | MANHATTAN | COMFORT STATION CONSTRUCTION | 2019 | 2800 | 77 | 0 | 0 | 0 | 0 | 0 | 0 | 77 | 209.97 | 0 | 1790 | 0 | 0 | 0 | 0 | 1999.97
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3LPLZCG | La Plaza Cultural Community Garden: Fence Renovation | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 303 | P-M245 P-D018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | LA PLAZA CULTURAL COMMUNITY GARDEN: FENCE RENOVATION | 2019 | 138 | 26 | 239 | 0 | 0 | 23 | 0 | 0 | 288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3MARGPK | Marcus Garvey Park , Manhattan | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | MARCUS GARVEY PARK -- RECONSTRUCT OF THE PLAZA ON THE ACROPOLIS AS WELL AS PATH, STAIRCASES AND WALLS LEADING UP TO IT. | MARCUS GARVEY PARK -- RECONSTRUCT OF THE PLAZA ON THE ACROPOLIS AS WELL AS PATH, STAIRCASES AND WALLS LEADING UP TO IT. | 2019 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3MORJUM | MORRIS-JUMEL MANSION: TECHNOLOGY/ELECTRICAL UPGRADE | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 300 | P-M094 |  |  | MORRIS-JUMEL MANSION: TECHNOLOGY/ELECTRICAL UPGRADE | 2019 | 0 | 0 | 0 | 38 | 0 | 0 | 0 | 0 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3NYPARK | NY RESTORATION PROJ (SHERMAN CREEK BOATHOUSE) M300-106MA | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 312 | P-D018 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES | MANHATTAN | NY RESTORATION PROJECT IN MANHATTAN | 2019 | 585 | 191.04 | 0 | 0 | 0 | 0 | 0 | 40 | 231.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3NYRS01 | East River Park Composting Facility & Wetland R/C M144-116M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-1245 |  |  | EAST RIVER NEW YORK RISING GRANT, BOROUGH OF MANHATTAN | 2019 | 1052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1052 | 0 | 0 | 1052
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3P40SPR | Hudson River Park Pier 40 Fire Sprinkler Recon | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-1246 |  |  | HUDSON RIVER PARK PIER 40 FIRE SPRINKLER RECON | 2019 | 3455 | 3455 | 100 | 230 | 0 | 0 | 0 | 0 | 3785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PDHBRC | Hansborough Rec Ctr M131-115M | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 300 | P-1018 P-D018 P-1008 P-1250 P-0506 |  | MANHATTAN | HANSBOROUGH REC CTR | 2019 | 4000 | 844.17 | 1395 | 0 | 0 | 20436 | 0 | 0 | 22675.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PDTDRC | Tony Dapolito Rec Ctr RC M103-115M | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 300 | P-0506 |  | MANHATTAN | TONY DAPOLITO REC CTR | 2019 | 4000 | 500.12 | 15 | 0 | 0 | 5902 | 0 | 0 | 6417.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PEDB81 | JOHN FINLEY WALK (EAST RIVER ESPLANADE), M081-118M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 300 | P-0508 |  |  | RECONSTRUCTION OF PEDESTRIAN BRIDGE AT EAST 81 ST OVER FDR DRIVE, MANHATTAN - FY17 TRF $250K (P0245M)FROM DDC TO DPR 03.01.2017 | 2019 | 250 | 0 | 225 | 25 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PGRGYM | Parks Green Gym | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | PARKS GREEN GYM | PARKS GREEN GYM | 2019 | 100 | 403.08 | 0 | 0 | 0 | 36 | 0 | 0 | 439.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PIN181 | PINEHURST AV/181ST - STAIRCASE/GARDEN UPGRADES | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 P-M245 |  | PINEHURST AVENUE STEPS @ 181ST STREET | PINEHURST AVENUE STEPS @ 181ST STREET : STAIRCASE/GARDEN UPGRADES | 2019 | 625 | 0 | 0 | 0 | 0 | 175 | 225 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PL14A6 | Ruppert Park-Install New Irrig.System MG-314M WO6 | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | RUPPERT PARK-INSTALL NEW IRRIGATION SYSTEM | RUPPERT PARK-INSTALL NEW IRRIGATION SYSTEM | 2019 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PL16A1 | Reconstruction of Dekovats, Manhattan | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 300 | P-0245M |  |  | RECONSTRUCTION OF DEKOVATS, MANHATTAN | 2019 | 349 | 0 | 231 | 0 | 0 | 24 | 0 | 0 | 255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PL16A2 | East River Esplanade Con Edison East 74th Street Reconstruct | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 300 | P-0245M |  |  | EAST RIVER ESPLANADE CON EDISON EAST 74TH STREET RECONSTRUCT | 2019 | 196 | 0 | 196 | 0 | 0 | 0 | 0 | 0 | 196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PLG13B | Reconstruction of plgr, Borough of Manhattan MG-213M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 399 | PV-D034 P-D018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | THE RECONSTRUCTION OF PAVEMENTS, FENCING, SAFETY SURFACING, PLUMBING,STONE WALLS, STEPS AND GENERAL SITEWORK, MANHATTAN | 2019 | 1817 | 1620.48 | 0 | 0 | 117 | 349 | 0 | 0 | 2086.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PLG14B | R/C OF Playgrounds multisites FY14 Manhattan (MG-914MA) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-0245M P-D018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | BOROUGHWIDE, MANHATTAN | R/C OF PLAYGROUNDS FY14, MANHATTAN | 2019 | 2135 | 2924.39 | 0 | 0 | 0 | 520 | 0 | 0 | 3444.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PLG14C | R/C OF Playgrounds multisites FY14 Manhattan (MG-315MA1) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-M822 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | BOROUGHWIDE MANHATTAN | R/C OF PLGR IN MANHATTAN | 2019 | 1855 | 1309.23 | 0 | 0 | 0 | 44 | 0 | 0 | 1353.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PLG15B | Playground Requirements MG-714M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-1018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | MULTISITES, BOROUGH OF MANHATTAN | R/C OF PLAYGROUNDS (MULTISITES) FY15 | 2019 | 2277 | 2799.85 | 0 | 0 | 100 | 0 | 0 | 0 | 2899.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PNYC05 | PlaNYC- Ft Washington Pk- Amtrak Pedestrian Bridge M028-110M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 399 | P-0245M P-0861 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | MANHATTAN | PLANYC- FT WASHINGTON PK. - AMTRAK PED BRIDGE | 2019 | 2338 | 139.11 | 0 | 5774 | 0 | 0 | 0 | 0 | 5913.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PNYT12 | FY19 Street Tree Planting, Mn CBs 1-12, PlaNYC (MG-416MR | LAND ACQUISITION AND TREE PLANTING | 300 | P-0822 |  | FY19 STREET TREE PLANTING, MN CBS 1-12, PLANYC (MG-416MR | FY19 STREET TREE PLANTING, MN CBS 1-12, PLANYC (MG-416MR | 2019 | 1208 | 0 | 990 | 0 | 0 | 0 | 0 | 0 | 990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3POORRD | POOR RICHARD'S PLAYGROUND RENOVATIONS, Mahattan | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 |  |  | POOR RICHARD'S PLAYGROUND RENOVATIONS, MAHATTAN | 2019 | 2489 | 31 | 69 | 0 | 0 | 2246 | 0 | 0 | 2346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PS155M | PS155M Playground , Manhattan | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 P-D933 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | PS 155M PLAYGROUND (DPR) -- PLAYGROUND RECONSTRUCTION MANAGED BY PARKS | PS 155M PLAYGROUND (DPR) -- PLAYGROUND RECONSTRUCTION MANAGED BY PARKS | 2019 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 1847 | 1847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PWBJRP | PWB - Jackie Robinson Park stairways, fencing, sidewalks, (M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-1018 |  | PWB - JACKIE ROBINSON PARK (M | PWB - JACKIE ROBINSON PARK STAIRWAYS, FENCING, SIDEWALKS, (M | 2019 | 6000 | 630 | 4441 | 0 | 0 | 279 | 0 | 0 | 5350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PWBSEP | PWB - Seward Park (Manhattan) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | PWB - SEWARD PARK (M | PWB - SEWARD PARK (M | 2019 | 11026 | 600 | 5087 | 0 | 0 | 842 | 0 | 0 | 6529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3QNSOVL | MultiPurpose Fld Queensboro Oval, Manhattan | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | DPR - MULTIPURPOSE FIELD--BUILD A MULTIPURPOSE FIELD AT QUEENSBORO OVAL TO REPLACE PRIVATE TENNIS CLUB. | 2019 | 1364 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3QUISCS | Quisqueya Playground-Reconstruction of Comfort Station | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-0505 |  |  | QUISQUEYA PLAYGROUND-RECONSTRUCTION OF COMFORT STATION | 2019 | 1710 | 155 | 0 | 0 | 1710 | 0 | 0 | 0 | 1865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RIVFTW | Shoreline Work in Riverside and Fort Washington Parks | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-1018 |  |  | ASSOCIATED SANDY ID IS SANDY3-13 | 2019 | 147 | 0 | 147 | 0 | 0 | 0 | 0 | 0 | 147 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RIVJOA | Riverside Park - Joan of Arc Island, Manhattan ( MG-318M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 |  | RIVERSIDE PARK -- JOAN OF ARC ISLAND UPGRADE | RIVERSIDE PARK -- JOAN OF ARC ISLAND UPGRADE | 2019 | 475 | 152 | 666 | 0 | 59 | 0 | 0 | 0 | 877 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RIVSTP | RIVERBANK STATE PARK - Culttural & Auditorium | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 300 | P-M245 P-D018 |  |  | RIVERBANK STATE PARK - CULTTURAL & AUDITORIUM | 2019 | 750 | 0 | 750 | 0 | 0 | 0 | 0 | 0 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RIVSTR | RIVERSIDE PARK--102nd ST Staircase, Manhattan | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 P-M245 P-0380 |  |  | RIVERSIDE PARK--101ST STAIRCASE PROJECT | 2019 | 818 | 0 | 0 | 0 | 0 | 2050 | 0 | 0 | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RNDLOT | Randall's Island PEP Office Trailer Parking Lot M104-118M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-0944 P-1018 |  | RANDALL'S ISLAND | THIS PROJECT IS FOR THE PARKING LOT AT THE RANDALL'S ISLAND PEP OFFICE TRAILER | 2019 | 6954 | 0 | 4703 | 0 | 0 | 0 | 0 | 0 | 4703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RVPSRC | RIVERSIDE PARK STAIRCASE: 83RD STREET STAIR RENOVATIONS | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-M245 |  |  | RIVERSIDE PARK STAIRCASE: 83RD STREET STAIR RENOVATIONS | 2019 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SAFTY1 | Life Safety - Rec Ctr & Nature Ctr - Manhattan | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 300 | P-0506 |  | MANHATTAN | LIFE SAFETY - REC CTR & NATURE CTR - MANHATTAN | 2019 | 1150 | 0 | 0 | 1800 | 0 | 867 | 0 | 0 | 2667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SEWARD | SEWARD PARK- RESTORATION OF SCHIFF FOUNTAIN | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 P-M245 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | RESTORATION OF SCHIFF FOUNTAIN -SEWARD PARK | 2019 | 272 | 36 | 0 | 0 | 0 | 0 | 0 | 400 | 436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SHARCS | Sheltering Arms Playgound Comfort Station | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-0505 |  |  | FUNDING TO BE TRANSFERRED FROM 846 P-6CWCMF... | 2019 | 1493 | 0 | 0 | 0 | 0 | 0 | 0 | 1493 | 1493 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SOHAGS | Green Street Fencing - Amsterdam Ave and 126th St. | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-M245 |  |  | GREEN STREET FENCING - AMSTERDAM AVE AND 126TH ST. | 2019 | 0 | 0 | 0 | 65 | 0 | 0 | 0 | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SOHO | SOHO Square Manhattan (MG25000-116M) | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 300 | HW-D102 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | MANHATTAN | RECONSTRUCTION OF SOHO SQUARE | 2019 | 1512 | 805.64 | 27 | 0 | 0 | 0 | 457 | 0 | 1289.64 | 3467.7 | 0 | 0 | 0 | 0 | 0 | 0 | 3467.7
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3STFWAG | STF - Wagner Playground Synthetic turf field, Manhattan | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-0510 |  |  | SYNTHETIC TURF- WAGNER PLAYGROUND | 2019 | 2376 | 252.04 | 0 | 0 | 189 | 1897 | 0 | 0 | 2338.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SUTTON | ONE SUTTON PLACE PARK CONSTRUCTION (M108-111M) | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 300 306 | P-D018 P-1018 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES | ONE SUTTON PLACE PARK, MANHATTAN | ONE SUTTON PLACE PARK - CONSTRUCT NEW PARK, MANHATTAN | 2019 | 600 | 1258.7 | 153 | 0 | 0 | 0 | 0 | 0 | 1411.7 | 618 | 132 | 0 | 0 | 0 | 0 | 0 | 750
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SUTTPK | SUTTON PLACE PARK.- Fountain & Spray Shower, Mahattan | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | SUTTON PLACE PARK.- FOUNTAIN & SPRAY SHOWER, MAHATTAN | 2019 | 850 | 14 | 0 | 0 | 0 | 0 | 0 | 850 | 864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TOMJPK | Thomas Jefferson Park Plg Reconst. Mahattan (M047-118M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 |  |  | FY18 ADOPTION SECTION 254 ADDS $2.140M (P D018) ... | 2019 | 2920 | 135 | 60 | 0 | 2080 | 0 | 0 | 0 | 2275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TRE17A | FY 17 Street Tree Mnht CB 1-12, MG- | LAND ACQUISITION AND TREE PLANTING | 300 | P-D822 |  | FY 17 STREET TREE MNHT CB 1-12, | FY 17 STREET TREE MNHT CB 1-12, | 2019 | 2204 | 2149.46 | 61 | 0 | 0 | 0 | 0 | 0 | 2210.46 | 550 | 0 | 0 | 0 | 0 | 0 | 0 | 550
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TRE18A | FY 18 Street Tree Mnht CB 2,4,7,9,10,12 | LAND ACQUISITION AND TREE PLANTING | 300 | W-0005 P-1018 |  | FY 18 STREET TREE MNHT CB 2,4,7,9,10,12 | FY 18 STREET TREE MNHT CB 2,4,7,9,10,12 | 2019 | 1942 | 254 | 35 | 0 | 0 | 0 | 0 | 0 | 289 | 0 | 0 | 0 | 0 | 659 | 0 | 0 | 659
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TRE18B | FY 18 Street Tree Mnht CB 1,3,5,6,8,11 | LAND ACQUISITION AND TREE PLANTING | 300 | S-0195 |  | FY 18 STREET TREE MNHT CB 1,3,5,6,8,11 | FY 18 STREET TREE MNHT CB 1,3,5,6,8,11 | 2019 | 2968 | 387 | 0 | 35 | 0 | 0 | 0 | 0 | 422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TRE20A | FY 20 Street Tree Mnht CB 1,3,5,6,8,11 MG-319M | LAND ACQUISITION AND TREE PLANTING | 300 | S-0136 S-0216 P-D822 P-D018 P-0822 |  | FY 20 STREET TREE MNHT CB 1,3,5,6,8,11 MG-319M | FY 20 STREET TREE MNHT CB 1,3,5,6,8,11 MG-319M | 2019 | 3768 | 0 | 0 | 233 | 2979 | 0 | 0 | 0 | 3212 | 0 | 0 | 0 | 556 | 0 | 0 | 0 | 556
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TRE20B | FY 20 Street Tree Mnht CB 2,4,7,9,10,12 MG-219M | LAND ACQUISITION AND TREE PLANTING | 300 | P-0822 P-D822 |  | FY 20 STREET TREE MNHT CB 2,4,7,9,10,12 MG-219M | FY 20 STREET TREE MNHT CB 2,4,7,9,10,12 MG-219M | 2019 | 5250 | 0 | 0 | 0 | 4050 | 0 | 0 | 0 | 4050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3W69SB2 | West 69th Street transverse bridge - phase 2 M353-212M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 307 | P-0380 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | WEST 69TH TRANSVERSE BRIDGE PHASE 2 | WEST 69TH TRANSVERSE BRIDGE PHASE 2 | 2019 | 650 | 164 | 0 | 0 | 786 | 0 | 0 | 0 | 950 | 447.88 | 0 | 2967 | 0 | 0 | 0 | 0 | 3414.88
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-03 | SANDY - John Jay & Tony Dapolito - boilers (MG-113M) | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 300 | P-1018 |  |  | SANDY SAFE-UP MANHATTAN BOILER REPLACEMENTS | 2019 | 862 | 311.14 | 0 | 0 | 0 | 107 | 0 | 0 | 418.14 | 908.56 | 0 | 962 | 0 | 0 | 0 | 0 | 1870.56
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-06 | SANDY - PNP Friends of the Highline | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 300 304 | P-1018 | PROJECT DELAYED PENDING NON-CITY GRANT APPROVAL | MANHATTAN | HIGHLINE | 2019 | 336 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 302 | 302
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-07 | SANDY - PNP Asphalt Green | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 300 308 | P-1018 | PROJECT DELAYED PENDING NON-CITY GRANT APPROVAL | MANHATTAN | ASPHALT GREEN | 2019 | 154 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 139 | 139
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-08 | SANDY - PNP Battery Conservancy | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 301 | P-1018 | PROJECT DELAYED PENDING NON-CITY GRANT APPROVAL | MANHATTAN | BATTERY PARK | 2019 | 650 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 506 | 506
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-09 | SANDY - PNP Riverside Park Conservancy | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 307 309 | P-1018 | PROJECT DELAYED PENDING NON-CITY GRANT APPROVAL | MANHATTAN | RIVERSIDE PARK | 2019 | 446 | 40.27 | 0 | 0 | 0 | 0 | 0 | 45 | 85.27 | 0 | 0 | 0 | 0 | 0 | 0 | 401 | 401
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-11 | Vietnam Vet. Memorial Lighting (M046-114M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-1018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | SOUTH STREET, MANHATTAN | R/C OF LIGHTING & ELECTR. AT VIETNAM VET. PLAZA,MANHATTAN | 2019 | 600 | 89.95 | 60 | 0 | 106 | 0 | 0 | 0 | 255.95 | 0 | 539 | 938 | 0 | 0 | 0 | 0 | 1477
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-12 | SANDY-Inwood Hill Nature Center (Type 3) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-1018 |  | INWOOD HILL PK , MANHATTAN | R/C OF INWOOD HILL NATURE CENTER | 2019 | 1920 | 349.47 | 0 | 0 | 0 | 598 | 0 | 0 | 947.47 | 0 | 0 | 0 | 0 | 872 | 0 | 0 | 872
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-13 | SANDY-Riverside & F. Washington Pk Shoreline (Type 3 ) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-1018 | PROJECT DELAYED PENDING NON-CITY GRANT APPROVAL | RIVERSIDE & F. WASHINGTON PARKS, MANHATTAN | SHORELINE WORK IN RIVERSIDE & F. WASHINGTON PK | 2019 | 1770 | 383.43 | 0 | 141 | 0 | 0 | 0 | 0 | 524.43 | 0 | 0 | 1269 | 0 | 0 | 0 | 0 | 1269
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-14 | SANDY-Dock at 79 Street Boat Basin M071-310M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-1018 |  | WEST 79 STREET BOAT BASIN | DOCK DESIGN | 2019 | 5232 | 887.35 | 0 | 0 | 0 | 7 | 0 | 0 | 894.35 | 4655.07 | 54 | 0 | 0 | 0 | 0 | 0 | 4709.07
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-17 | SANDY- E.River Esplanade (Glick Park)-Elec (Type 3) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-1018 |  | EAST RIVER ESPLANADE (GLICK PARK) , BOROUGH OF MANHATTAN | EAST RIVER ESPLANADE (GLICK PK)- ELECTRICAL REPAIR | 2019 | 239 | 147.25 | 0 | 0 | 0 | 8 | 0 | 0 | 155.25 | 551.3 | 58 | 0 | 0 | 0 | 0 | 0 | 609.3
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-18 | SANDY - Mannahatta Fountains RC (Type 3) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | MANNAHATTA (WALL STREET) , BOROUGH OF MANHATTAN | FOUNTAIN DAMAGE AND ELECTRICAL REPAIR | 2019 | 1640 | 327.75 | 0 | 0 | 352 | 0 | 0 | 0 | 679.75 | 0 | 0 | 0 | 3514 | 0 | 0 | 0 | 3514
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-19 | SANDY - John Jay & Tony Dapolito - Electrical (Balance) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-1018 |  |  | SANDY - JOHN JAY & TONY DAPOLITO - ELECTRICAL (BALANCE) | 2019 | 1018 | 0 | 0 | 0 | 0 | 0 | 0 | 102 | 102 | 0 | 0 | 0 | 0 | 0 | 0 | 916 | 916
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-20 | Playground 103 (CIII) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-1018 |  |  | PLAYGROUND 103 (CIII) | 2019 | 795 | 155.98 | 0 | 0 | 0 | 14 | 0 | 0 | 169.98 | 500 | 113 | 0 | 0 | 12 | 0 | 0 | 625
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-21 | Four Parks Safety Surface | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | FOUR PARKS SAFETY SURFACE | 2019 | 718 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 646 | 646
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-23 | Manhattan B | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-1018 |  |  | MANHATTAN B - IN KIND | 2019 | 354 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 318 | 318
20190425 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-24 | SANDY-Inwood Nature Center Exhibit Displays | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 300 | P-1018 |  | INWOOD HILL NATURE CENTER, MANHATTAN | RECONSTRUCTION OF INWOOD NATURE CENTER EXHIBIT DISPLAY | 2019 | 330 | 7.62 | 25 | 0 | 0 | 0 | 0 | 0 | 32.62 | 67 | 230 | 0 | 0 | 0 | 0 | 0 | 297
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | ACEDCA702 | DCLA - REPLACEMENT OF 7 AIR HANDLING UNITS | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 301 | PU-0025 PV-0022 |  |  | DCLA - REPLACEMENT OF 7 AIR HANDLING UNITS | 2019 | 3020 | 0 | 2000 | 1000 | 0 | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | ACEDCA703 | DCLA - CHILLER PLANT UPGRADE | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 301 | PU-0025 PV-0467 |  |  | DCLA - CHILLER PLANT UPGRADE | 2019 | 3000 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | AGNYCHANG | NYCHANGE PROJECT WITH DFTA | DEPARTMENT FOR THE AGING BUILDING RECONSTRUCTION | 303 | AG-0001 HR-0025 AG-M001 AG-D001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | SEPT 2012 ADD 254 PROJECT. NYCHANGE PROJECT WITH DFTA. SCOPE IS TO UPGRADE THE SENIOR CENTER AND EXTERIOR GARDEN. | 2019 | 1000 | 1609.32 | 0 | 0 | 2460 | 9550 | 1082 | 6652 | 21353.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CC1C3 | 1 CENTRE ST.- OFFICES FROM 49-51 CHAMBERS ST. - 21C3 | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0077 |  |  | 49-51 CHAMBERS AND 346 BROADWAY 21C3 | 2019 | 3740 | 8780.79 | 0 | 220 | 0 | 0 | 0 | 0 | 9000.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CC253B | 100 GOLD- 21C3 | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0077 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | 253 BROADWAY 21C3 | 2019 | 17078 | 16882.58 | 0 | 207 | 0 | 0 | 0 | 0 | 17089.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CMEHVAC | OCME - Evidence Unit HVAC Upgrades at 421 E. 26th St, Manh | OCME | 301 | HL-0083 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | HVAC UPGRADE/INSTALLATION FOR OCME EVIDENCE UNIT AT DNA LAB BUILDING | 2019 | 262 | 482.68 | 3 | 178 | 0 | 0 | 0 | 0 | 663.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO283SID2 | 100 CENTRE STREET - SIDEWALK REPLACEMENT | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 301 | CO-0283 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | 100 CENTRE STREET - SIDEWALK REPLACEMENT | 2019 | 6808 | 6606.01 | 792 | 198 | 0 | 0 | 0 | 0 | 7596.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO283TOIL | 100 CENTRE ST.- CODE COMPLIANT TOILET UPGRADE | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 301 | CO-0283 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | 100 CENTRE ST.- CODE COMPLIANT TOILET UPGRADE | 2019 | 5500 | 744.54 | 0 | 4424 | 0 | 0 | 3198 | 0 | 8366.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO284EXT2 | 111 CENTRE ST.- EXTERIOR | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 301 | CO-0284 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | 111 CENTRE ST.- EXTERIOR | 2019 | 2564 | 6108.51 | 253 | 325 | 0 | 0 | 0 | 0 | 6686.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO285FIRE | 60 LAFAYETTE ST - FIRE ALARM UPGRADE | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 301 | CO-0285 |  |  | 60 LAFAYETTE ST - FIRE ALARM DESIGN & REPLACEMENT | 2019 | 10826 | 0 | 0 | 0 | 0 | 0 | 645 | 10051 | 10696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO304REHB | 60 CENTRE ST. - RECONSTRUCTION | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 301 | CO-0304 |  | 60 CENTRE STREET, NEW YORK, NY | RESTORATION OF THE BUILDING ENVELOPE INTEGRITY - BASEMENT, ROOF & FACADE | 2019 | 15869 | 1681.62 | 0 | 1817 | 0 | 13295 | 0 | 0 | 16793.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO306REHB | 170-74 E 121ST STREET - HARLEM COURT FIRE PROTECTION | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 311 | CO-0306 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | HARLEM COURTHOUSE REHABILITATION | 2019 | 1970 | 0 | 0 | 0 | 0 | 0 | 400 | 3240 | 3640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO80ROOF2 | 27 MADISON AVE - ROOF & MISC. OPERATIONS SPACES UPGRADE | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 305 | CO-0080 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | 27 MADISON AVE - ROOF & MISC. OPERATIONS SPACES UPGRADE | 2019 | 3881 | 1758.2 | 0 | 0 | 0 | 0 | 0 | 0 | 1758.2 | 12454.01 | 1066 | 0 | 0 | 0 | 0 | 0 | 13520.01
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO81ELEC | 31 CHAMBERS ST. - ELECTRICAL AND FA SYSTEM UPGRADE | IMPROVEMENT AND EXPANSION OF COURT FACILITIES | 301 | CO-0081 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | MANHATTAN SURROGATE'S COURT ELECTRICAL AND FIRE ALARM SYSTEM UPGRADESAND DOOR REPLACEMENTS | 2019 | 19090 | 0 | 0 | 0 | 0 | 0 | 0 | 32060 | 32060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO81SKY2 | 31 CHAMBERST ST.- RENOVATE SKYLIGHT | IMPROVEMENT AND EXPANSION OF COURT FACILITIES | 301 | CO-0081 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | SKYLIGHT RESTORATION AND SURROUNDING SPACE | 2019 | 6189 | 8774.67 | 2991 | 0 | 0 | 0 | 0 | 0 | 11765.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E14-0006 | DCAS - HEALTH BUILDING COMP ENERGY UPGRADE | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 300 | PU-0025 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | COMP ENERGY UPGRADE | 2019 | 605 | 1429.2 | 59 | 114 | 0 | 0 | 0 | 0 | 1602.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E14-0008 | DCAS - MANHATTAN SUPREME COURT COMP ENERGY UPGRADE | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT |  | PU-0025 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | ENERGY UPGRADE | 2019 | 9566 | 13411.62 | 276 | 576 | 640 | 0 | 0 | 0 | 14903.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E14-0012 | DCAS - SUN BUILDING ENERGY UPGRADE | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 300 | PU-0025 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | ENERGY UPGRADE | 2019 | 1731 | 1138.74 | 75 | 50 | 0 | 0 | 0 | 0 | 1263.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E14-0017 | DHS - Bellevue Men's Shelter | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 301 | PU-0025 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | DHS - BELLEVUE MEN'S SHELTER | 2019 | 2782 | 4578.84 | 51 | 147 | 0 | 0 | 0 | 0 | 4776.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E14-0018 | DHS - Fort Washington Armory Shelter | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 301 | PU-0025 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | DHS - FORT WASHINGTON ARMORY SHELTER | 2019 | 1115 | 615.27 | 0 | 38 | 0 | 0 | 0 | 0 | 653.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E14-0020 | DHS - Regent Hotel Shelter | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 301 | HH-0115 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | DHS - REGENT HOTEL SHELTER | 2019 | 698 | 1031.77 | 89 | 0 | 0 | 0 | 0 | 0 | 1120.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0003 | DCAS - Manhattan Civil Court | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 301 | PU-0025 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | MANHATTAN CIVIL COURT | 2019 | 3780 | 465.84 | 0 | 4759 | 0 | 0 | 0 | 0 | 5224.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0005 | DSNY -Manhattan 3 District Garage | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 303 | PU-0025 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | MANHATTAN 3 DISTRICT GARAGE | 2019 | 3427 | 260.29 | 2279 | 23 | 0 | 0 | 0 | 0 | 2562.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E17-0001 | DCAS - LOUIS J LEFKOWITZ - ENERGY EFFICIENCY UPGRADE | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 302 | PU-0025 |  |  | ENERGY EFFICIENCY UPGRADE | 2019 | 3422 | 0 | 475 | 48 | 2660 | 0 | 0 | 0 | 3183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0001 | DCAS -City Hall Campus: Tweed Courthouse - Light Upgrade | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 301 | PU-0025 |  |  | DDC -CITY HALL CAMPUS: TWEED COURTHOUSE - LIGHT UPGRADE | 2019 | 300 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0002 | DCAS-Manhattan Municipal Building - Heat Light Installation | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 301 | PU-0025 |  |  | CITY HALL CAMPUS: MANHATTAN MUNICIPAL BUILDING - HEAT LIGHT INSTALLATION | 2019 | 300 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0003 | DFTA-Cypress Hills Senior Center - Lighting Upgrade | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 301 | PU-0025 |  |  | CYPRESS HILLS SENIOR CENTER - LIGHTING UPGRADE AND DHW HEATERS | 2019 | 300 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0004 | DOHMH- Public Health Laboratory - Condensate Heat Recovery | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 301 | PU-0025 |  |  | PUBLIC HEALTH LABORATORY - CONDENSATE HEAT RECOVERY AND VFD INSTALLATION | 2019 | 300 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0016 | DCLA-NYBG Maintenance Buildings - Lighting Upgrade | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 301 | PU-0025 |  |  | NYBG MAINTENANCE BUILDINGS - LIGHTING UPGRADE | 2019 | 300 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | F175LC8 | RENOVATION L8 | NEW FACILITIES AND RENOVATIONS | 301 | F-0175 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | RENOVATION L8 | 2019 | 2859 | 13136.55 | 619 | 0 | 0 | 0 | 0 | 0 | 13755.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | F175MCE23 | ELECTRIC & TOILETS - EC23 | NEW FACILITIES AND RENOVATIONS | 305 | F-0175 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | ELECTRIC & TOILETS - EC23 | 2019 | 1201 | 5107.69 | 1118 | 0 | 0 | 0 | 0 | 0 | 6225.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HBMA24662 | W 128TH ST PED BRIDGE BIN:2246620 | FAIR BRIDGES | 300 | HB-0215 |  | W 128TH ST PED BRIDGE BIN:2246620 | W 128TH ST PED BRIDGE BIN:2246620 | 2019 | 14143 | 1964.61 | 0 | 0 | 12511 | 0 | 0 | 0 | 14475.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HBPED100M | PED BRIDGE - E 81 ST (M) | FAIR BRIDGES | 300 308 | P-0245M | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | PED BRIDGE - E 81 ST (M) | PED BRIDGE - E 81 ST (M) | 2019 | 18118 | 16736.52 | 628 | 300 | 0 | 0 | 0 | 0 | 17664.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BEES | BELLEVUE - ELECT SVC UPGRADE | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 |  |  | BELLEVUE - ELECT SVC UPGRADE | 2019 | 3131 | 1359.36 | 449 | 6827 | 6000 | 6000 | 0 | 0 | 20635.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BLBR | BELLEVUE BATHROOMS RECONSTRUCTION | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 |  |  | RECONSTRUCT ALL BATHROOMS AT BELLEVUE MEN'S SHELTER | 2019 | 18200 | 1441.63 | 0 | 8878 | 0 | 8000 | 0 | 0 | 18319.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BLCY | BELLEVUE COURTYARD | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 |  |  | RECONSTRUCT COURTYARD AT BELLEVUE | 2019 | 5700 | 0 | 0 | 0 | 750 | 0 | 5000 | 0 | 5750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BLEL | BELLEVUE SHELTER - REHABILITATION OF EXISTING ELEVATORS | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | REHABILITATION OF EXISTING PASSENGER AND FREIGHT ELEVATOR CABS , CONTROLS AND MACHINERY. | 2019 | 6676 | 7899 | 581 | 0 | 0 | 0 | 0 | 0 | 8480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BLEN | BELLEVUE MAIN ATRIUM | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 |  |  | RECONSTRUCT MAIN ATRIUM ENTRANCEWAY AT BELLEVUE | 2019 | 11200 | 0 | 1000 | 2777 | 3223 | 5000 | 0 | 0 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BLFS | BELLEVUE MEN'S RESIDENCE- FIRE SAFETY | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 |  |  | UPGRADE AND MODERNIZE FIRE SAFETY SYSTEM | 2019 | 14792 | 1000.98 | 0 | 1560 | 0 | 7300 | 6000 | 0 | 15860.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BLRR | BELLEVUE ROOF/ FACADE | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 |  |  | BELLEVUE ROOF/ FACADE | 2019 | 19139 | 18048.7 | 850 | 10638 | 15948 | 14969 | 0 | 0 | 60453.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BVDV | BELLEVUE DIVERSION INTERIOR RENOVATION | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 |  |  | BELLEVUE DIVERSION INTERIOR RENOVATION | 2019 | 1412 | 1346.02 | 41 | 0 | 0 | 0 | 0 | 0 | 1387.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112CGIU | Keener Assessment Shelter - Fire Alarm Upgrade | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 |  |  | ADULT SHELTER AT 65 CHARLES GAY LOOP - INTERIOR UPGRADE | 2019 | 1320 | 76.14 | 0 | 0 | 0 | 0 | 0 | 1201 | 1277.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112CTFS | CLARKE THOMAS FIRE SAFETY | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CLARKE THOMAS FIRE SAFETY | 2019 | 1855 | 173.49 | 12 | 0 | 0 | 0 | 1785 | 0 | 1970.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112FTRF | FT. WASHINGTON ARMORY ROOF REPLACEMENT | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 |  |  | FORT WASHINGTON ARMORY - ROOF REPLACEMENT | 2019 | 5400 | 0 | 1032 | 748 | 5000 | 5320 | 0 | 0 | 12100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112FWFA | FT. WASHINGTON - FIRE ALARM | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 |  |  | FT. WASHINGTON - FIRE ALARM | 2019 | 639 | 2325.23 | 145 | 0 | 0 | 0 | 3190 | 0 | 5660.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112HMFA | HARLEM 1 FIRE SAFETY | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 |  |  | HARLEM 1 FIRE SAFETY | 2019 | 886 | 0 | 440 | 525 | 0 | 0 | 0 | 0 | 965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112HSFA | HELP SEC - FIRE SAFETY | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | HELP SEC - FIRE SAFETY | 2019 | 2406 | 199.34 | 26 | 0 | 0 | 0 | 2181 | 0 | 2406.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112KEFA | Kenton Hall Fire Safety | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | FIRE SAFETY SYTEM | 2019 | 630 | 111.7 | 0 | 0 | 0 | 25 | 1313 | 0 | 1449.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112KELC | EAST 3RD STREET - ELECTRICAL UPGRADE | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 |  |  | EAST 3RD STREET - KITCHENS AND ELECTRICAL UPGRADE | 2019 | 5000 | 0 | 720 | 100 | 2900 | 2300 | 0 | 0 | 6020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112SWFA | SCHWARTZ WARDS ISLAND FIRE SAFETY | SHELTERS FOR HOMELESS INDIVIDUALS | 311 | HH-0112 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | FIRE SAFETY SYSTEM | 2019 | 2488 | 179.97 | 0 | 0 | 0 | 0 | 850 | 1500 | 2529.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112THFA | THIRD ST SHELTER FIRE SAFETY | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | FIRE SAFETY SYSTEM | 2019 | 1110 | 0 | 0 | 0 | 0 | 0 | 200 | 950 | 1150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112VEFP | VETERAN SRO FIRE PANEL | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | REPLACE FIRE PANEL | 2019 | 1225 | 205.24 | 0 | 0 | 0 | 0 | 6725 | 0 | 6930.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112WBLR | WARDS ISLAND COMPLEX - BOILERS AND FUEL STORAGE TANKS | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | WARDS ISLAND COMPLEX - BOILER AND FUEL STORAGE REPLACEMENT | 2019 | 9251 | 10314.37 | 273 | 0 | 0 | 0 | 0 | 0 | 10587.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115JCEK | Jennie Clarke Elec and Kitchen | SHELTERS FOR HOMELESS FAMILIES |  | HH-0115 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | JENNIE CLARKE ELECTRIC AND KITCHEN | 2019 | 7253 | 0 | 0 | 0 | 0 | 630 | 0 | 7773 | 8403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115JCFB | JENNIE CLARK RESIDENCE - FIRE ALARM UPGRADE | SHELTERS FOR HOMELESS FAMILIES |  | HH-0115 |  |  | JENNIE CLARK RESIDENCE - FIRE ALARM UPGRADE | 2019 | 1598 | 1085.56 | 274 | 126 | 0 | 0 | 0 | 0 | 1485.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115REGX | REGENT FAMILY RESIDENCE EXTERIOR UPGRADE | SHELTERS FOR HOMELESS FAMILIES |  | HH-0115 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | ALL ARCHITECTURAL AND ENGINEERING DESIGN SERVICES DURING CONSTRUCTIONREQUIRED FOR ALL WORK ASSOCIATED WITH THE NECESSARY MASONRY AND APPURTENANCES STABILIZATION AND UPGRADE; REMOVAL OF ALL BUILDING DEPARTMENTVIOLATIONS FOR THE EXTERIOR OF THE FACILITY. | 2019 | 1080 | 12143.74 | 140 | 1150 | 0 | 0 | 0 | 0 | 13433.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115RFEU | REGENT FAMILY APT. ELEC UPGRADE | SHELTERS FOR HOMELESS FAMILIES |  | HH-0115 |  |  | APT. ELECT UPGRADE | 2019 | 7650 | 624.84 | 745 | 2973 | 0 | 5000 | 6000 | 9897 | 25239.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82CHELI | CHELSEA HC INTERIOR REHAB | CLINIC RENOVATION AND REHABILITATION | 304 | HL-0082 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CHELSEA HC INTERIOR REHAB | 2019 | 1650 | 28782.82 | 484 | 16 | 0 | 0 | 0 | 0 | 29282.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82CHNWH | COMMUNITY HEALTHCARE NETWORK-WASHINGTON HEIGHTS | CLINIC RENOVATION AND REHABILITATION | 312 | HL-D999 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES |  | COMMUNITY HEALTHCARE NETWORK-WASHINGTON HEIGHTS | 2019 | 560 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82MANAT | Manhattan Animal Care Center Upgrade | ANIMAL CARE |  | HL-0082 |  |  | MANHATTAN ANIMAL SHELTER UPGRADE EXISTING GARAGE AND PET RECEIVING CENTER | 2019 | 5000 | 983.26 | 400 | 4440 | 0 | 0 | 0 | 0 | 5823.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWBARUCH | Baruch College - 25th Street Plaza (MED-634) | PRIMARY STREET RECONSTRUCTION | 300 305 306 | HW-1684 HW-0200 WM-0001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | BARUCH COLLEGE - 25TH STREET PLAZA (LOCATED BETWEEN LEX AND 3RD AVE) | BARUCH COLLEGE - 25TH STREET PLAZA (LOCATED BETWEEN LEX AND 3RD AVE) | 2019 | 4100 | 4413.99 | 985 | 0 | 0 | 0 | 0 | 0 | 5398.99 | 4771.19 | 415 | 0 | 0 | 0 | 0 | 0 | 5186.19
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD10211 | 185th St. - Streetscape Improvements | PRIMARY STREET RECONSTRUCTION | 300 312 | HW-0001M WM-0001 TF-0002 EP-0007 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | 185TH STREET PUBLIC PLAZA | 185TH STREET PUBLIC PLAZA | 2019 | 1500 | 4327.84 | 1612 | 0 | 0 | 0 | 0 | 0 | 5939.84 | 1611.85 | 0 | 0 | 0 | 0 | 0 | 0 | 1611.85
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM2025 | Delancey Street Safety Improvements | PRIMARY STREET RECONSTRUCTION | 300 | HW-0001M HW-0001 HW-D102 HW-M002 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | DELANCEY STREET SAFETY IMPROVEMENTS | 2019 | 24177 | 550 | 0 | 0 | 16927 | 0 | 0 | 0 | 17477 | 997.39 | 0 | 0 | 5252 | 0 | 0 | 0 | 6249.39
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMBRT5A | 34th STREET SBS | TRAFFIC WORK IN CONJUNCTION WITH HIGHWAY RECONSTRUCTION | 300 304 305 306 | TF-0777 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | 34TH STREET TRANSITWAY | 34TH STREET TRANSITWAY | 2019 | 7085 | 1984.59 | 0 | 0 | 0 | 0 | 0 | 0 | 1984.59 | 6696.36 | 0 | 845 | 0 | 0 | 0 | 0 | 7541.36
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMM008 | EAST 86TH ST STREETSCAPE-225 EAST 79TH ,MADISON TO YORK AVE | PRIMARY STREET RECONSTRUCTION | 300 308 | HW-0001M WM-0001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | EAST 86TH MERCHANT/RESIDENTS ASSOCIATION-STREETSCAPE IMPRV. | EAST 86TH MERCHANT/RESIDENT ASSOCIATION-STREETSCAPE IMPRV. | 2019 | 1000 | 11426.15 | 1058 | 0 | 0 | 0 | 0 | 0 | 12484.15 | 2704 | 0 | 500 | 594 | 0 | 0 | 0 | 3798
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMME43ST | 43rd Street Shared Street | PRIMARY STREET RECONSTRUCTION | 300 | HW-0200 HW-D102 HW-0001M |  | 43RD STREET SHARED STREET | HWMME43ST | 2019 | 11000 | 0 | 1656 | 0 | 0 | 15594 | 0 | 0 | 17250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMNYPL | New York Public Library Pedestrian Improvements | PRIMARY STREET RECONSTRUCTION | 300 | HW-0001M |  | NEW YORK PUBLIC LIBRARY PEDESTRIAN IMPROVEMENTS | NEW YORK PUBLIC LIBRARY PEDESTRIAN IMPROVEMENTS | 2019 | 4832 | 0 | 556 | 1019 | 0 | 0 | 0 | 0 | 1575 | 0 | 0 | 2993 | 0 | 0 | 0 | 0 | 2993
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMP116 | RECON OF ASTOR PLACE AND COOPER SQUARE | PRIMARY STREET RECONSTRUCTION | 303 | HW-0001M P-0245M TF-0002 SE-0002M WM-0001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  |  | 2019 | 5895 | 26485.21 | 279 | 0 | 0 | 0 | 88 | 0 | 26852.21 | 202.12 | 0 | 0 | 0 | 0 | 0 | 0 | 202.12
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMP2012 | TIMES SQUARE (SEN002160) | PRIMARY STREET RECONSTRUCTION | 305 | HW-1666 HW-0001 HW-0944 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | TIMES SQUARE | TIMES SQUARE | 2019 | 24719 | 65096.82 | 5186 | 0 | 0 | 3370 | 0 | 0 | 73652.82 | 14879.6 | 0 | 211 | 0 | 0 | 0 | 0 | 15090.6
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMP2019 | RECONSTRUCTION OF EAST HOUSTON STREET (MED-604) | PRIMARY STREET RECONSTRUCTION | 300 303 | HW-0001M | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | RECONSTRUCTION OF EAST HOUSTON STREET | RECONSTRUCTION OF EAST HOUSTON STREET | 2019 | 3903 | 36741.79 | 764 | 0 | 0 | 0 | 0 | 0 | 37505.79 | 1075.36 | 0 | 0 | 0 | 0 | 0 | 0 | 1075.36
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMP2020 | Reconstruction of Gansevoort Area, Manhattan | PRIMARY STREET RECONSTRUCTION | 300 302 | HW-0001M TF-0002 WM-0001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | RECONSTRUCTION OF GANSEVOORT AREA | RECONSTRUCTION OF GANSEVOORT AREA | 2019 | 14700 | 17300.58 | 1672 | 0 | 0 | 0 | 0 | 0 | 18972.58 | 7975 | 300 | 0 | 0 | 0 | 0 | 0 | 8275
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCA7A | RECONSTRUCTION OF GREENWICH ST, HARRISON ST & LEONARD ST | PRIMARY STREET RECONSTRUCTION | 301 | HW-0944 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | RECONSTRUCTION OF GREENWICH ST, HARRISON ST & LEONARD ST | RECONSTRUCTION OF GREENWICH ST, HARRISON ST & LEONARD ST | 2019 | 5676 | 1477.29 | 0 | 0 | 0 | 0 | 0 | 0 | 1477.29 | 19599.01 | 160 | 0 | 0 | 0 | 0 | 0 | 19759.01
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCA7B | RECONSTRUCTION OF BROADWAY - LEONARD ST TO CORTLANDT ST | PRIMARY STREET RECONSTRUCTION | 301 | HW-1670 HW-0200 TF-0002 TF-0502 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | RECONSTRUCTION OF BROADWAY - LEONARD ST TO CORTLANDT ST | RECONSTRUCTION OF BROADWAY - LEONARD ST TO CORTLANDT ST | 2019 | 5623 | 72.08 | 0 | 0 | 0 | 0 | 0 | 0 | 72.08 | 0 | 0 | 0 | 0 | 5138 | 0 | 0 | 5138
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCA7E | RECONSTRUCTION OF WORTH ST - HUDSON ST TO EAST BROADWAY | PRIMARY STREET RECONSTRUCTION | 301 | HW-1670 TF-0002 HW-0001M HW-0944 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | RECONSTRUCTION OF WORTH ST - HUDSON ST TO EAST BROADWAY | RECONSTRUCTION OF WORTH ST - HUDSON ST TO EAST BROADWAY | 2019 | 7045 | 3406.35 | 421 | 55 | 0 | 0 | 0 | 0 | 3882.35 | 70374.64 | 10377 | 0 | 0 | 0 | 0 | 0 | 80751.64
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCA7F | RECONSTRUCTION OF WARREN ST - WEST ST TO BROADWAY | PRIMARY STREET RECONSTRUCTION | 301 | HW-1670 TF-0502 HW-0944 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | RECONSTRUCTION OF WARREN ST - WEST ST TO BROADWAY | RECONSTRUCTION OF WARREN ST - WEST ST TO BROADWAY | 2019 | 5680 | 1423.85 | 243 | 0 | 0 | 0 | 0 | 0 | 1666.85 | 20039.79 | 4359 | 0 | 0 | 0 | 0 | 0 | 24398.79
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCA7G | RECONSTRUCTION JOHN STREET - NASSAU STREET AND BROADWAY | PRIMARY STREET RECONSTRUCTION | 301 | HW-1670 HW-0200 TF-0002 TF-0502 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | RECONSTRUCTION JOHN STREET - NASSAU STREET AND BROADWAY | RECONSTRUCTION JOHN STREET - NASSAU STREET AND BROADWAY | 2019 | 980 | 385.6 | 0 | 0 | 0 | 0 | 0 | 0 | 385.6 | 0 | 0 | 0 | 0 | 0 | 0 | 820 | 820
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCA8B | RECONSTRUCTION OF FULTON ST & ANCILLARY STREETSCAPE | PRIMARY STREET RECONSTRUCTION | 301 | HW-0001M HW-1670 HW-0944 HW-0200 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | RECONSTRUCTION OF FULTON ST & ANCILLARY STREETSCAPE | RECONSTRUCTION OF FULTON ST & ANCILLARY STREETSCAPE | 2019 | 26563 | 4818.53 | 36 | 0 | 0 | 0 | 5 | 0 | 4859.53 | 39727.53 | 0 | 0 | 0 | 0 | 629 | 0 | 40356.53
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB1 | Reconstruction of Nassau St | PRIMARY STREET RECONSTRUCTION | 300 | HW-0001M | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | RECONSTRUCTION OF NASSAU ST | RECONSTRUCTION OF NASSAU ST | 2019 | 12650 | 215.89 | 32 | 0 | 2782 | 0 | 0 | 0 | 3029.89 | 863.59 | 304 | 0 | 11128 | 0 | 0 | 0 | 12295.59
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB2 | Reconstruction of Greenwich | PRIMARY STREET RECONSTRUCTION | 300 | HW-0001M |  | RECONSTRUCTION OF GREENWICH | RECONSTRUCTION OF GREENWICH | 2019 | 21360 | 277.69 | 0 | 3778 | 0 | 0 | 0 | 0 | 4055.69 | 710.76 | 0 | 16377 | 0 | 0 | 0 | 0 | 17087.76
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB5A | Liberty Street Reconstruction | PRIMARY STREET RECONSTRUCTION | 300 | HW-0001M HW-0944 |  | LIBERTY STREET RECONSTRUCTION | LIBERTY STREET RECONSTRUCTION | 2019 | 3251 | 1311.94 | 908 | 0 | 0 | 0 | 0 | 0 | 2219.94 | 654.39 | 2456 | 0 | 0 | 0 | 0 | 0 | 3110.39
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB6 | Reconstruction of Vesey St | PRIMARY STREET RECONSTRUCTION | 300 | HW-0001M |  | RECONSTRUCTION OF VESEY ST | RECONSTRUCTION OF VESEY ST | 2019 | 23010 | 0 | 0 | 0 | 2802 | 0 | 0 | 0 | 2802 | 0 | 0 | 0 | 11208 | 0 | 0 | 0 | 11208
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB7 | Reconstruction of Trinity Pl | PRIMARY STREET RECONSTRUCTION | 300 | HW-0001M | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | RECONSTRUCTION OF TRINITY PL | RECONSTRUCTION OF TRINITY PL | 2019 | 39140 | 0 | 188 | 0 | 8054 | 0 | 0 | 0 | 8242 | 0 | 749 | 0 | 32219 | 0 | 0 | 0 | 32968
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP14MTA | CITYWIDE COMPLEX PED RAMPS (TRANSIT AUTHORITY) - MANHATTAN | PEDESTRIAN RAMP CONSTRUCTION | 300 | HW-0200 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | CITYWIDE COMPLEX PED RAMPS (TRANSIT AUTHORITY) - MANHATTAN | CITYWIDE COMPLEX PED RAMPS (TRANSIT AUTHORITY) - MANHATTAN | 2019 | 2911 | 5730.2 | 328 | 0 | 0 | 0 | 0 | 0 | 6058.2 | 76.05 | 0 | 0 | 0 | 0 | 0 | 0 | 76.05
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ004M | Pershing Square West Plaza/Streetscape Recon (MED-622) | PRIMARY STREET RECONSTRUCTION | 300 305 | TF-0002 HW-1684 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | PERSHING SQUARE WEST PLAZA/STREETSCAPE RECONSTRUCTION | 2019 | 1689 | 5906.43 | 626 | 0 | 0 | 0 | 0 | 0 | 6532.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ008M | Forsyth Streetscape and Plaza Reconstruction | PRIMARY STREET RECONSTRUCTION | 300 303 | HW-1684 WM-0001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | FORSYTH STREETSCAPE AND PLAZA RECONSTRUCTION | 2019 | 2361 | 8485.85 | 523 | 0 | 0 | 0 | 0 | 0 | 9008.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ012M | Bogardus Plaza Clock Tower | PRIMARY STREET RECONSTRUCTION | 300 301 | HW-1684 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | BOGARDUS PLAZA CLOCK TOWER | BOGARDUS PLAZA CLOCK TOWER | 2019 | 1835 | 7203.82 | 240 | 0 | 0 | 0 | 0 | 0 | 7443.82 | 322.5 | 323 | 0 | 0 | 0 | 0 | 0 | 645.5
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ015M | Pershing Square East Plaza/Streetscape Reconstruction | PRIMARY STREET RECONSTRUCTION | 300 | HW-0001M | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | PERSHING SQUARE EAST PLAZA/STREETSCAPE RECONSTRUCTION | PERSHING SQUARE EAST PLAZA/STREETSCAPE RECONSTRUCTION | 2019 | 13020 | 0 | 1860 | 0 | 0 | 11160 | 0 | 0 | 13020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR18M | Pedestrian Ramp Rehabilitation - Manhattan | PEDESTRIAN RAMP CONSTRUCTION | 300 | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | PEDESTRIAN RAMP REHABILITATION - MANHATTAN | 2019 | 8277 | 1983.53 | 6878 | 0 | 0 | 0 | 0 | 0 | 8861.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19M | Pedestrian Ramp Rehabilitation - Manhattan | PEDESTRIAN RAMP CONSTRUCTION | 300 | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | PEDESTRIAN RAMP REHABILITATION - MANHATTAN | 2019 | 12156 | 0 | 12156 | 0 | 0 | 0 | 0 | 0 | 12156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2019M | Prior Notice Sidewalks- Manhattan | SIDEWALK RECONSTRUCTION | 300 | HW-0200 |  |  | PRIOR NOTICE SIDEWALKS- MANHATTAN | 2019 | 2500 | 0 | 0 | 4341 | 0 | 0 | 0 | 0 | 4341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA0996S | 96TH STREET - Exterior Rehabilitation | ESSENTIAL RECONSTRUCTION OF FACILITIES | 308 | LN-D008 LN-0008 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | EXTERIOR REHABILITATION | 2019 | 670 | 1353.97 | 273 | 66 | 0 | 0 | 0 | 0 | 1692.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA09KIP | KIPS BAY - Exterior Rehabilitation | ESSENTIAL RECONSTRUCTION OF FACILITIES | 306 | LN-D003 LN-D008 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | EXTERIOR REHABILITATION | 2019 | 758 | 349.93 | 0 | 0 | 0 | 0 | 1672 | 0 | 2021.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA10115 | 115TH STREET - Removal and Replacement of Floors | IMPROVEMENTS TO EXISTING FACILITIES | 310 | LN-0008 LN-D008 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | REMOVAL AND REPLACEMENT OF FLOORS | 2019 | 334 | 1239.91 | 877 | 0 | 0 | 0 | 0 | 0 | 2116.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA10AGL | AGUILAR - Facade Restoration | IMPROVEMENTS TO EXISTING FACILITIES | 311 | LN-D008 LN-0008 LN-D003 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | FACADE RESTORATION | 2019 | 525 | 749.7 | 0 | 1218 | 0 | 0 | 0 | 0 | 1967.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA10JMB | JEFFERSON MARKET - ADA Accessibility | IMPROVEMENTS TO EXISTING FACILITIES | 302 | LN-D008 LN-0008 LN-0101M LN-M001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | JEFFERSON MARKET - ADA ACCESSIBILITY | 2019 | 1540 | 1367.86 | 8732 | 992 | 0 | 0 | 0 | 0 | 11091.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA10OTT | OTTENDORFER - New Exit and ADA Access | IMPROVEMENTS TO EXISTING FACILITIES | 303 | LN-D008 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | OTTENDORFER - CREATE NEW EXIT AND ADA ACCESS | 2019 | 555 | 405.75 | 0 | 0 | 0 | 0 | 512 | 0 | 917.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA10RIS | ROOSEVELT ISLAND - NEW BRANCH LIBRARY | EXPANSION AND CONSTRUCTION OF FACILITIES | 308 | LN-0008 |  |  | ROOSEVELT ISL - SITE SLECTION/DESIGN | 2019 | 5700 | 7782.78 | 247 | 592 | 0 | 0 | 0 | 0 | 8621.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA10YRK | YORKVILLE - New Boiler | IMPROVEMENTS TO EXISTING FACILITIES | 308 | LN-D003 LN-0008 LN-D008 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | YORKVILLE - NEW BOILER | 2019 | 420 | 666.09 | 3 | 71 | 0 | 0 | 0 | 0 | 740.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA1167S | 67TH STREET - Partial Interior Renovation | ESSENTIAL RECONSTRUCTION OF FACILITIES | 308 | LN-D008 LN-0008 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | INTERIOR | 2019 | 500 | 516.64 | 2023 | 0 | 0 | 0 | 0 | 0 | 2539.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA11BLD | BLOOMINGDALE - Interior Renovation | ESSENTIAL RECONSTRUCTION OF FACILITIES | 307 | LN-D008 LN-0008 LN-D004 LN-D003 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | INTERIOR | 2019 | 200 | 536.55 | 2661 | 130 | 35 | 0 | 0 | 0 | 3362.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA11CCL | COUNTEE CULLEN - Elevator Replacement | ESSENTIAL RECONSTRUCTION OF FACILITIES | 310 | LN-D008 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ELEVATOR REPLACEMENT | 2019 | 200 | 1089.09 | 122 | 336 | 0 | 0 | 0 | 0 | 1547.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA12EPH | EPIPHANY - FACADE RESTORATION | ESSENTIAL RECONSTRUCTION OF FACILITIES | 300 306 | LN-D008 LN-0008 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | FACADE | 2019 | 700 | 359.6 | 0 | 0 | 0 | 0 | 1558 | 0 | 1917.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA12SWP | SEWARD PARK - Replace sidealk over vault and waterproof | ESSENTIAL RECONSTRUCTION OF FACILITIES | 300 303 | LN-D008 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | REPLACE SIDEALK OVER VAULT AND WATERPROOF | 2019 | 250 | 366.53 | 0 | 0 | 0 | 0 | 69 | 0 | 435.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13CCL | COUNTEE CULLEN: Boiler | ESSENTIAL RECONSTRUCTION OF FACILITIES | 310 | LN-D008 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BOILER | 2019 | 560 | 583.89 | 3 | 257 | 0 | 0 | 0 | 0 | 843.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13GBR | GEORGE BRUCE: Partial Interior/Exterior,/ Roof / Boiler | ESSENTIAL RECONSTRUCTION OF FACILITIES | 309 | LN-D008 LN-0008 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ROOF / BOILER | 2019 | 2650 | 303.75 | 249 | 0 | 3614 | 0 | 0 | 0 | 4166.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13HAM | HAMILTON FISH: REHABILITATION | ESSENTIAL RECONSTRUCTION OF FACILITIES | 300 303 | LN-0008 LN-D008 PU-0025 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | REHABILITATION | 2019 | 2590 | 881.48 | 591 | 258 | 6565 | 0 | 0 | 0 | 8295.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13HUD | HUDSON PARK: Renovation | ESSENTIAL RECONSTRUCTION OF FACILITIES | 300 302 | LN-D008 LN-0008 LN-0101M | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RENOVATION | 2019 | 2550 | 619.12 | 0 | 0 | 85 | 0 | 6144 | 0 | 6848.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13MLB | MUHLENBERG: Elevator | ESSENTIAL RECONSTRUCTION OF FACILITIES | 304 | LN-D008 LN-0101M LN-0008 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | ELEVATOR | 2019 | 709 | 266.41 | 0 | 654 | 0 | 0 | 0 | 0 | 920.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13NAM | NEW AMSTERDAM - HVAC and Cooling Tower | IMPROVEMENTS TO EXISTING FACILITIES | 300 301 | LN-0008 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | HVAC AND COOLING TOWER | 2019 | 3024 | 3638.95 | 514 | 153 | 0 | 0 | 0 | 0 | 4305.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA1458S | Electrical Upgrade | IMPROVEMENTS TO EXISTING FACILITIES | 300 | LN-D008 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | ELECTRICAL UPGRADE | 2019 | 100 | 421.88 | 41 | 0 | 0 | 0 | 0 | 0 | 462.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA14MBG | HVAC and Related Work | ESSENTIAL RECONSTRUCTION OF FACILITIES | 300 | LN-D008 LN-0008 LN-M001 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES |  | HVAC AND RELATED WORK | 2019 | 500 | 294.06 | 0 | 1817 | 0 | 0 | 0 | 0 | 2111.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA15SPK | New Boiler | ESSENTIAL RECONSTRUCTION OF FACILITIES | 300 | LN-D008 LN-M001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | NEW BOILER | 2019 | 963 | 1052.21 | 20 | 45 | 0 | 0 | 0 | 0 | 1117.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCAL15CC | Countee Cullen:Exterior Renovation | ESSENTIAL RECONSTRUCTION OF FACILITIES | 300 | LN-D008 LN-0008 LN-M001 LN-D003 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | COUNTEE CULLEN:EXTERIOR RENOVATION | 2019 | 2593 | 410.24 | 444 | 5393 | 0 | 0 | 0 | 0 | 6247.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCLPCONS | Midtown Campus Project | ESSENTIAL RECONSTRUCTION OF FACILITIES | 300 305 | LN-0008 |  |  | MIDTOWN CAMPUS PROJECT - CONS | 2019 | 142234 | 140817.7 | 942 | 0 | 0 | 0 | 0 | 0 | 141759.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEA08MHV | MANHATTAN (Northern) - HVAC @ Four Branch Libraries | ESSENTIAL RECONSTRUCTION OF FACILITIES | 300 308 309 311 312 | LN-0101M LN-D008 LN-0008 LN-M001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | HVAC @ FOUR BRANCHS - MANHATTAN 125TH STREET BRANCH 96TH STREET BRANCH FORT WASHINGTON BRANCH GEORGE BRUCE BRANCH | 2019 | 4460 | 5513.66 | 57 | 1433 | 0 | 0 | 0 | 0 | 7003.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEA13HGR | HAMILTON GRANGE:Exterior Rehabiliation/ Window | ESSENTIAL RECONSTRUCTION OF FACILITIES | 300 309 | LN-0008 LN-D008 LN-0101X | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | EXTERIOR REHABILIATION/ WINDOW REPLACEMENT | 2019 | 885 | 644.36 | 25 | 0 | 2812 | 0 | 0 | 0 | 3481.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEM12MLB | MUHLENBERG - Sidewalk Vault | ESSENTIAL RECONSTRUCTION OF FACILITIES | 304 | LN-0008 LN-D008 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | VAULT | 2019 | 856 | 309.62 | 0 | 646 | 0 | 0 | 0 | 0 | 955.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEM13JMK | JEFFERSON MARKET: Fire Safety | ESSENTIAL RECONSTRUCTION OF FACILITIES | 300 302 | LN-0101M LN-0008 LN-0101R | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | FIRE | 2019 | 362 | 526.46 | 33 | 97 | 0 | 0 | 0 | 0 | 656.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNMA12WAS | WASHINGTON HEIGHTS - Phase II Renovation | ESSENTIAL RECONSTRUCTION OF FACILITIES | 300 312 | LN-M001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | RENOVAION | 2019 | 1490 | 5609.17 | 0 | 0 | 0 | 609 | 0 | 0 | 6218.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNMNA08LS | MANHATTAN - Life Safety Projects @ 17 Branch Libraries | ESSENTIAL RECONSTRUCTION OF FACILITIES | 300 | LN-D008 LN-0101X LN-0101M LN-D003 LN-M001 LN-0008 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | LIFE SAFETY PROJECTS @ 16 BRANCH LIBRARIES - MANHATTAN | 2019 | 3719 | 5184.65 | 141 | 273 | 0 | 0 | 0 | 0 | 5598.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNRA10STG | ST GEORGE - Boiler Replacement and Elevator Upgrade | ESSENTIAL RECONSTRUCTION OF FACILITIES | 303 | LN-0008 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | BOILER REPLACEMENT AND ELEVATOR UPGRADE AT ST. GEORGE BRANCH LIBRARY. | 2019 | 894 | 1491.19 | 30 | 0 | 8 | 0 | 0 | 0 | 1529.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LRCA13LPA | LPA: Electrical upgrade and Lighting | ESSENTIAL RECONSTRUCTION OF FACILITIES | 300 307 | L-D002 L-0101 |  |  | ELECTRICAL UPGRADE AND LIGHTING | 2019 | 1555 | 1210.49 | 23 | 0 | 0 | 0 | 493 | 14 | 1740.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LRCA17SCH | SCHOMBURG - Renovation Phase II Passthrough | ESSENTIAL RECONSTRUCTION OF FACILITIES | 300 310 | L-0103 L-D001 L-D002 L-D003 L-0101 |  |  | PHASEII | 2019 | 14458 | 0 | 13458 | 0 | 0 | 0 | 0 | 0 | 13458 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LRCM15SSB | Full Replacement of Fire Alarm System | ESSENTIAL RECONSTRUCTION OF FACILITIES | 300 | L-D002 L-0101 |  |  | FULL REPLACEMENT OF FIRE ALARM SYSTEM | 2019 | 18483 | 0 | 18120 | 0 | 0 | 0 | 0 | 0 | 18120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-594 | WM RPLMT IN E 46 ST & E 47 ST B/T MADISON AV & LEXINGTON AV | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 305 | WM-0001 EP-0007 TF-0502 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | WM RPLMT IN E 46 ST & E 47 ST B/T MADISON AV & LEXINGTON AV | 2019 | 772 | 1163.05 | 0 | 0 | 0 | 27824 | 0 | 0 | 28987.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-596 | TRUNK WM IN HUDSON ST FRM LAIGHT ST TO WORTH ST | AUGMENTATION OF WATER SUPPLY SYSTEMS | 301 | SE-0944 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | TRUNK WM IN HUDSON ST FRM LAIGHT ST TO WORTH ST, ETC TO CONNECT TO SHAFT 29B (TUNNEL #3) TO THE DISTRIBUTION SYSTEM | 2019 | 7769 | 48950.34 | 0 | 0 | 0 | 0 | 0 | 0 | 48950.34 | 31015.07 | 1406 | 0 | 0 | 0 | 0 | 0 | 32421.07
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-597 | TRUNK WM IN EAST 31 STREET FRM 5TH AV TO 2ND AV | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 305 306 | WM-0006 WM-0001 SE-0002M | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | TRUNK WM IN EAST 31 STREET FRM 5TH AV TO 2ND AV | 2019 | 6454 | 200.66 | 0 | 0 | 0 | 14944 | 0 | 0 | 15144.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-598 | TRUNK WM IN W. 30 St. FRM 10 AV TO 9TH AV, TO CONN SHAFT 26B | AUGMENTATION OF WATER SUPPLY SYSTEMS | 304 | WM-0006 SE-0002M WM-0001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | TRUNK WM IN W. 30 ST. FRM 10 AV TO 9TH AV, TO CONNECT SHAFT 26B (TUNNEL #3) TO DISTRIBUTION SYSTEM | 2019 | 13470 | 31271.48 | 1600 | 0 | 0 | 0 | 0 | 0 | 32871.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-598B | TRUNK WM IN W 30 ST - 9 AV TO 10 AV (SHAFT 26B) - PHASE B | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 304 305 | WM-0006 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | TRUNK WM IN W 30 ST - 9 AV TO 10 AV (SHAFT 26B) - PHASE B | TRUNK WM IN W 30 ST - 9 AV TO 10 AV (SHAFT 26B) - PHASE B | 2019 | 64919 | 49275.31 | 0 | 3731 | 0 | 0 | 0 | 0 | 53006.31 | 772.04 | 0 | 0 | 0 | 0 | 0 | 0 | 772.04
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-605 | WM REPLMT IN WOOSTER ST B/T WEST HOUSTON & CANAL STREET | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 302 | WM-0001 WM-0006 SE-0002M | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | WM REPLMT IN WOOSTER ST B/T HOUSTON & CANAL STREET | 2019 | 1140 | 351.24 | 0 | 1140 | 0 | 0 | 0 | 0 | 1491.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-606 | TRUNK MAIN CONN TO SHAFT 30B IN GRAND ST B/T B'WAY & ESSEX | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 303 | TF-0002 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | TRUNK MAIN CONN TO SHAFT 30B IN GRANT ST B/T B'WAY & ESSEX | 2019 | 11447 | 72267.19 | 39 | 0 | 0 | 0 | 0 | 0 | 72306.19 | 5080.11 | 0 | 0 | 0 | 0 | 0 | 0 | 5080.11
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-608 | WASHINGTON SQUARE PARK | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 302 | WM-0006 WM-0001 SE-0002M P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | WASHINGTON SQUARE PARK | 2019 | 6179 | 14611.26 | 2439 | 0 | 0 | 0 | 0 | 0 | 17050.26 | 36.79 | 0 | 0 | 0 | 0 | 0 | 0 | 36.79
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-609 | TRUNK MAIN IN W60 ST, W.E. AVE TO COLUMBUS AV | TRUNK AND DISTRIBUTION MAIN EXTENSION | 307 | WM-0006 EP-0007 TF-0002 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | TRUNK MAIN IN W60 ST, WEST END AVE TO COLUMBUS AV, TO CONNECT TO SHAFT 24B | 2019 | 9031 | 100165.08 | 807 | 0 | 0 | 0 | 0 | 0 | 100972.08 | 2804.04 | 0 | 0 | 0 | 0 | 0 | 0 | 2804.04
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-610 | TRUNK MAIN CONNECTION TO SHAFT 27B | TRUNK AND DISTRIBUTION MAIN EXTENSION | 303 | HW-D102 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | TRUNK MAIN CONNECTION TO SHAFT 27B IN HUDSON ST BETW GANSEVOORT ST & W 13 ST | 2019 | 14250 | 30546.66 | 55 | 0 | 0 | 0 | 0 | 0 | 30601.66 | 937.1 | 0 | 0 | 0 | 0 | 0 | 0 | 937.1
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-611 | TRUNK WM REPLACMT IN TRANSVERSE RD 3 | AUGMENTATION OF WATER SUPPLY SYSTEMS | 308 | WM-0006 WM-0001 |  |  | TRUNK WM REPLACMT IN TRANSVERSE RD 3, B/T 85 ST & 86 ST | 2019 | 4158 | 0 | 0 | 0 | 0 | 0 | 4158 | 0 | 4158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-616 | Trunk & dist WM replacement 124st b/t 7 & 2 ave, manh. | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 310 311 | WM-0006 WM-0001 SE-0002M | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RUNK & DIST WM REPLACEMENT 124ST B/T 7 & 2 AVE, MANH | 2019 | 37976 | 415.86 | 0 | 0 | 0 | 33252 | 0 | 0 | 33667.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-619 | Trunk Main replacement, b'way b/t w 93 & 97 st, Manh | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 307 | WM-0006 WM-0001 SE-0002M |  |  | RUNK MAIN REPLACEMENT, B'WAY B/T W 93 & 97 ST, MANH | 2019 | 7751 | 685.5 | 0 | 0 | 9987 | 0 | 0 | 0 | 10672.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-622 | Water Main Replacement Park Ave, Man (HWPLZ004M) | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 305 | WM-0001 WM-0006 SE-0002M | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | PERSHING SQ W PLAZA WM REPLACEMENT PARK AVE B/T E 40 & 42 ST, MANH | 2019 | 2475 | 11646.37 | 2866 | 0 | 0 | 0 | 0 | 0 | 14512.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-625 | WEST 14TH STREET | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 300 | WM-0001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | DISTRIBUTION WATER MAIN EXTENSIONS/REPLACEMENTS: NEW BUILDINGS | 2019 | 3900 | 29994.18 | 1617 | 0 | 0 | 0 | 0 | 0 | 31611.18 | 114.92 | 0 | 0 | 0 | 0 | 0 | 0 | 114.92
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-642 | Distribution water main extensions/replacements | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 300 | WM-0001 |  |  | DISTRIBUTION WATER MAIN EXTENSIONS/REPLACEMENTS; NEW BUILDINGS, MANHATTAN | 2019 | 5152 | 7586.06 | 798 | 0 | 0 | 0 | 0 | 0 | 8384.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-645 | Distribution water main Installation, Manhattan | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 300 | WM-0001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | DISTRIBUTION WATER MAIN INSTALLATION, MANHATTAN | 2019 | 4567 | 3252.72 | 691 | 0 | 0 | 110 | 0 | 0 | 4053.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MEDA-002 | Accelerated Distribution WM replcmnt & sewer rebhab - MAN | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 300 | WM-0001 SE-0002M | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | ACCELERATED DISTRIBUTION WATER MAIN REPLCMNT & SEWER REBHAB/REPLCMNT,MANHATTAN | 2019 | 17900 | 19989.91 | 0 | 21077 | 0 | 4 | 0 | 0 | 41070.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | P-303ERPK | East River Park | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 300 | RE-0025 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | EAST RIVER PARK | EAST RIVER PARK | 2019 | 9274 | 0 | 810 | 37 | 7874 | 0 | 0 | 0 | 8721 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | P-30420SP | West 20th St. Park Demolition & Abatement | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | ED-0075 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | 20TH STREET PARK CONSTRUCTION, MANHATTAN | 20TH STREET PARK CONSTRUCTION | 2019 | 1000 | 2331.81 | 276 | 175 | 0 | 0 | 0 | 0 | 2782.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | P-3RANDAL | Randall's Island Infrastructure, Roadways, Drainage, & CS | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 311 | P-0944 |  | RANDALL'S ISLAND | CONCESSION | 2019 | 16700 | 2198.61 | 0 | 0 | 15171 | 0 | 0 | 0 | 17369.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79-009A | REHAB 9TH PCT | POLICE FACILITIES | 303 | PO-0079 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | 321 EAST 5TH STREET, NEW YORK, NY 10003 | PRECINCT REHABILITATION | 2019 | 33056 | 27854.97 | 49 | 177 | 0 | 0 | 0 | 0 | 28080.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79BMAHQ | ONE POLICE PLAZA PAVING AND LANDSCAPING | POLICE FACILITIES | 300 | PO-0079 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | ONE POLICE PLAZA | ONE POLICE PLAZA | 2019 | 816 | 479.42 | 0 | 1472 | 0 | 0 | 0 | 0 | 1951.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79BMAIU | FRONT DESK RECONSTRUCTION AT 20TH, 25TH, 30TH, 34TH PCTS | POLICE FACILITIES | 300 | PO-0079 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | FRONT DESK RECONSTRUCTION AT 20TH , 25TH, 30TH,34TH PCTS | 2019 | 1029 | 805.26 | 0 | 254 | 0 | 0 | 0 | 0 | 1059.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79BMAJU | 26TH PRECINCT ROOF, WINDOWS & FACADE | POLICE FACILITIES | 300 | PO-0079 |  |  | ROOF, WINDOWS, FACADE | 2019 | 2903 | 0 | 721 | 4085 | 0 | 0 | 0 | 0 | 4806 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV234CSV1 | CSV - Clemente Soto Velez - Interior Code Compliance | ESSENTIAL RECONSTRUCTION OF FACILITIES | 303 | PV-0234 PV-D234 PV-M467 PV-0467 PW-0077 PW-C077 PV-M234 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | 107 SUFFOLK STREET, NY NY 10002 | CSV - CLEMENTE SOTO VELEZ - INTERIOR CODE COMPLIANCE - ADA ACCESS, RESTROOMS, EGRESS, ETC. | 2019 | 1500 | 270 | 0 | 0 | 0 | 7290 | 0 | 0 | 7560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV241EXTR | MCNY - Exterior Facade Rehabilitation | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | PV-D241 PV-0241 PV-M241 PV-0467 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | 1220 FIFTH AVENUE, MANHATTAN, NY | FACADE RENOVATION AND REHABILITATION. | 2019 | 2296 | 421.97 | 0 | 0 | 3947 | 0 | 0 | 0 | 4368.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV467-122 | 122C - 122 Community Center Bldg Reconstruction | ESSENTIAL RECONSTRUCTION OF FACILITIES | 303 | PV-M788 PV-M467 PV-0467 PV-D467 PV-0788 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | 150 1ST AVENUE, NEW YORK NY | PS 122 - BLDG RECONSTRUCTION | 2019 | 16812 | 33126.61 | 1468 | 0 | 0 | 0 | 0 | 0 | 34594.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV467SRA4 | SRAC - Seventh Regiment - Park Ave Facade | ESSENTIAL RECONSTRUCTION OF FACILITIES | 308 | HH-0115 |  |  | PROJECT SCOPE OF WORK IS THE RECONSTRUCTION OF THE PARK AVE, FACADE.AND THE INSTALLATION OF A NEW ROOF DRAINAGE SYSTEM. | 2019 | 6953 | 6875.26 | 62 | 0 | 0 | 0 | 0 | 0 | 6937.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV525STUD | SMH - Studio Museum in Harlem New Building | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | PV-0525 PV-0467 PV-D467 PV-D525 PV-M525 |  |  | NEW BUILDING | 2019 | 59331 | 0 | 58831 | 0 | 0 | 0 | 0 | 0 | 58831 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW195SA | 80 CENTRE ST. - SAFE ACCESS, REPLACEMENT OF CATWALKS | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0195 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | 80 CENTRE ST. - SAFE ACCESS, REPLACEMENT OF SIDEWALKS | 2019 | 186 | 0 | 0 | 0 | 0 | 0 | 195 | 0 | 195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW195SW2 | 80 CENTRE ST. - SIDEWALK REHABILITATION | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0195 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | 80 CENTRE ST. - SIDEWALK REHABILITATION | 2019 | 2240 | 775.08 | 0 | 0 | 2280 | 0 | 0 | 0 | 3055.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW29370M | 70 MULBERRY STREET - FIRE ALARM DESIGN | LEGAL MANDATES AND CORRECTION OF UNSAFE CONDITIONS | 301 | PW-0293 |  |  | 70 MULBERRY STREET - FIRE ALARM DESIGN | 2019 | 858 | 226.6 | 0 | 191 | 1400 | 0 | 0 | 0 | 1817.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW29380FC | 80 CENTRE ST.- FIRE ALARMS/SPRINKLERS | LEGAL MANDATES AND CORRECTION OF UNSAFE CONDITIONS | 301 | PW-0293 |  |  | 80 CENTRE ST.- FIRE ALARMS/SPRINKLERS | 2019 | 44728 | 0 | 0 | 2600 | 3900 | 36954 | 0 | 0 | 43454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW3171C | 1 CENTRE STREET- FACADE REHAB | LEGAL MANDATES AND CORRECTION OF UNSAFE CONDITIONS | 301 | PW-0317 |  |  | 1 CENTRE STREET - FACADE REPAIRS | 2019 | 8334 | 0 | 0 | 1245 | 992 | 2175 | 20399 | 0 | 24811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW3172L | 2 LAFAYETTE STREET - FACADE REPAIRS | LEGAL MANDATES AND CORRECTION OF UNSAFE CONDITIONS | 301 | PW-0317 |  |  | 2 LAFAYETTE STREET - FACADE REPAIRS | 2019 | 4850 | 0 | 0 | 350 | 316 | 0 | 3195 | 0 | 3861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW317WOR | 125 WORTH STREET - FACADE REPAIRS | LEGAL MANDATES AND CORRECTION OF UNSAFE CONDITIONS | 301 | PW-0316 PW-0266 |  |  | 125 WORTH STREET - FACADE REAPIRS | 2019 | 4050 | 0 | 0 | 0 | 863 | 0 | 5037 | 0 | 5900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW357ELEV | 253 BROADWAY- ELEVATOR MODERNIZATION | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0357 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | 253 BROADWAY ELEVATOR MODERNIZATION | 2019 | 2653 | 633.01 | 6718 | 617 | 0 | 0 | 0 | 0 | 7968.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW357FIRE | 253 BROADWAY- FIRE ALARM REPLACEMENT - VAULT RECONSTUCTION | LEGAL MANDATES AND CORRECTION OF UNSAFE CONDITIONS | 301 | PW-0293 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | 253 BROADWAY FIRE ALARM REPLACEMENT | 2019 | 2743 | 1796.54 | 0 | 643 | 15000 | 6194 | 0 | 0 | 23633.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW357MOCS | 253 BROADWAY- 9TH FLOOR REHABILITATION OF MOCS SPACE | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0357 PW-0077 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | 253 BROADWAY 9TH FLOOR REHAB OF MOCS SPACE | 2019 | 3500 | 4003.12 | 0 | 41 | 0 | 0 | 0 | 0 | 4044.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW7722R | 22 READE STREET EXTERIOR | LEGAL MANDATES AND CORRECTION OF UNSAFE CONDITIONS | 301 | PW-0077 |  |  | THE EXTERIOR RECONSTRUCTION OF THE CITY PLANNING BUILDING | 2019 | 21175 | 0 | 0 | 3196 | 0 | 25380 | 0 | 0 | 28576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77CHROT | City Hall Rotunda | REHABILITATION OF CITY-OWNED OFFICE SPACE | 300 301 | PW-0077 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CENTRE STREET | 2019 | 27114 | 24732.14 | 0 | 0 | 442 | 0 | 0 | 0 | 25174.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77GLDA2 | 100 GOLD ST.- MIS HVAC UPGRADES | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0077 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | 100 GOLD ST.- MIS HVAC UPGRADES | 2019 | 2535 | 3603.02 | 91 | 133 | 488 | 0 | 0 | 0 | 4315.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77GLDWN | 100 GOLD ST.- WINDOW REPLACEMENT AND EXTERIOR REHABILITATION | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0077 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | 100 GOLD STREET WINDOW REPLACEMENT AND EXTERIOR REHAB | 2019 | 1655 | 0 | 0 | 0 | 0 | 3828 | 0 | 0 | 3828 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77LYA | 253 BROADWAY- LPC MOVE TO 2nd, 11th, 12th, 13th FLS | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0077 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | 253 BROADWAY- LPC MOVE FROM 1 CENTRE ST, 9TH FLOOR | 2019 | 23714 | 30915.88 | 14653 | 980 | 0 | 0 | 0 | 0 | 46548.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW80DYCD2 | 2 LAFAYETTE STREET- DYCD RELOCATION | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0077 PW-0293 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | DYCD RELOCATION TO 2 LAFAYETTE STREET. | 2019 | 34658 | 61323.54 | 4972 | 732 | 0 | 0 | 0 | 0 | 67027.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW80SA | 2 LAFAYETTE ST.- SAFE ACCESS CATWALK | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0080 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | 2 LAFAYETTE STREET SAFE ACCESS CATWALK | 2019 | 120 | 0 | 0 | 0 | 0 | 95 | 0 | 0 | 95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PWD005FS | FORTUNE SOCIETY | MISCELLANEOUS CONSTRUCTION | 305 | PW-D005 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES |  | STRUCTURAL ISSUES SUCH AS WATER INFLUTRATION | 2019 | 500 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PWD005NEW | NONTRADITIONAL EMPLOYMENT FOR WOMEN | RENOVATION OF OTHER CITY-OWNED FACILITIES | 304 | PW-D005 PW-M077 ED-D075 | PROJECT DELAYED PENDING NON-CITY GRANT APPROVAL |  | NO SCOPE FROM COUNCIL STAFF | 2019 | 870 | 1877.67 | 0 | 30 | 2229 | 0 | 0 | 0 | 4136.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | S195-227S | Spring St Salt Enclosure | GARAGES AND FACILITIES | 301 | S-0195 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CONSTRUCTION OF A SALT ENCLOSURE | 2019 | 10375 | 21888.78 | 0 | 176 | 0 | 0 | 0 | 0 | 22064.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | S216-401A | EAST 91st ST MARINE TRANSFER STATION | SOLID WASTE MANAGEMENT | 300 308 | S-0216 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | E 91ST ST MTS | E 91ST ST MTS | 2019 | 131355 | 239918.69 | 6424 | 3210 | 0 | 0 | 0 | 0 | 249552.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | S216-401R | CONSTRUCTION, E. 92 ST RAMP TO E. 91 ST MTS | SOLID WASTE MANAGEMENT | 300 | S-0216 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | CONSTRUCTION OF A RAMP FROM EAST 92ND STREET TO THE EAST 91ST STREET MARINE TRANSFER STATION, MANHATTAN | 2019 | 19926 | 5537.98 | 18551 | 0 | 0 | 0 | 0 | 0 | 24088.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | S216-404A | GANSEVOORT MARINE TRANSFER STATION | SOLID WASTE MANAGEMENT | 300 302 | S-0216 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | GANSEVOORT MTS SITE | GANSEVOORT MTS | 2019 | 89458 | 38319 | 100 | 0 | 0 | 0 | 0 | 50850 | 89269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | S216-415A | WEST 59th STREET MTS | SOLID WASTE MANAGEMENT | 300 304 307 | S-0216 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | WEST 59TH ST MTS SITE | WEST 59TH ST MTS | 2019 | 60937 | 85723.19 | 7805 | 9307 | 0 | 0 | 0 | 0 | 102835.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | S219-233A | CONSTRUCTION MANHATTAN 1/2/5 GARAGE | GARAGES AND FACILITIES | 301 302 305 | S-0219 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BLOCK 596 LOT 50 MANHATTAN | CONSTRUCTION OF A NEW SANITATION GARAGE TO SERVICE MANHATTAN COMMUNITY DISTRICTS 1, 2, AND 5. | 2019 | 147907 | 213456.54 | 25 | 985 | 0 | 0 | 0 | 0 | 214466.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW06 | Reconstruction of Vestry Street- Hurricane Sandy | PRIMARY STREET RECONSTRUCTION | 300 | HW-0001M HW-0200 TF-0002 TF-0502 HW-0944 HW-D102 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | RECONSTRUCTION OF VESTRY STREET- HURRICANE SANDY | RECONSTRUCTION OF VESTRY STREET- HURRICANE SANDY | 2019 | 2232 | 158.05 | 3238 | 0 | 0 | 0 | 0 | 0 | 3396.05 | 0 | 3209 | 0 | 0 | 0 | 0 | 0 | 3209
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW07 | Reconstruction of E8th Street- Hurricane Sandy | PRIMARY STREET RECONSTRUCTION | 300 | HW-0001M WM-0001 SE-0002M | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | RECONSTRUCTION OF E8TH STREET- HURRICANE SANDY | RECONSTRUCTION OF E8TH STREET- HURRICANE SANDY | 2019 | 476 | 50 | 0 | 0 | 421 | 0 | 0 | 0 | 471 | 0 | 0 | 0 | 144 | 0 | 0 | 0 | 144
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW08 | Reconstruction of Front Street-Hurricane Sandy | PRIMARY STREET RECONSTRUCTION | 300 | HW-0001M HW-0200 HW-0944 TF-0002 TF-0502 P-0245M | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | RECONSTRUCTION OF FRONT STREET-HURRICANE SANDY | RECONSTRUCTION OF FRONT STREET-HURRICANE SANDY | 2019 | 4888 | 1105.33 | 2530 | 0 | 0 | 0 | 0 | 0 | 3635.33 | 757.34 | 11203 | 539 | 0 | 0 | 0 | 0 | 12499.34
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDSLIP | 100 OLD SLIP RESTORATION & SYSTEMS REPLACEMENT | POLICE FACILITIES | 300 | PO-0079 |  |  | 100 OLD SLIP RESTORATION | 2019 | 19124 | 0 | 240 | 14411 | 0 | 0 | 0 | 0 | 14651 | 0 | 2154 | 2238 | 0 | 0 | 0 | 0 | 4392
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SECBRM01 | Reconstruction & installation of Catch Basins, Manhattan | REPLACEMENT OF CHRONICALLY FAILING COMPONENTS | 300 | SE-0001 EP-0007 SE-0750 SE-1000 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | RECONSTRUCTION & INSTALLATION OF CATCH BASINS, MANHATTAN | 2019 | 2000 | 0 | 0 | 0 | 0 | 0 | 2951 | 0 | 2951 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002152 | COMBINE SEWERS IN WORTH ST | PROGRAMMATIC REPLACEMENT AND RECONSTRUCTION | 301 302 | WM-0006 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | REPLACEMENT OF COMBINE SEWER IN WOTH STREET BETWEEN CENTRE ST AND MULBERRY ST, ETC. | 2019 | 8443 | 28252.69 | 504 | 0 | 0 | 0 | 0 | 0 | 28756.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002161 | Water main & Sewer work in Broadway b/t Leonard & Cortlandt | REPLACEMENT OF CHRONICALLY FAILING COMPONENTS | 301 | SE-0002M | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | WATER MAIN & SEWER WORK IN BROADWAY B/T LEONARD & CORTLANDT STREET | 2019 | 489 | 0 | 489 | 0 | 0 | 0 | 0 | 0 | 489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002162 | Sewer Work in John St b/t Broadway & William St | REPLACEMENT OF CHRONICALLY FAILING COMPONENTS | 301 | SE-0002M | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | SEWER WORK IN JOHN ST BETWEEN BROADWAY AND WILLIAM ST. | 2019 | 81 | 0 | 81 | 0 | 0 | 0 | 0 | 0 | 81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002164 | Reconstruction of 7th Avenue (HWM1163) | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 303 | SE-0002M WM-0001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RECONSTRUCTION OF 7TH AVENU. COMBINED SEWER REPLACEMENT AND REHABILITATION, WATER MAIN WORK. | 2019 | 1181 | 0 | 0 | 1183 | 0 | 0 | 0 | 0 | 1183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002165 | Combined Sewers at West 33rd St - 10 Ave & 11 Ave | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 303 | WM-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | COMBINED AND STORM SEWER IN 11TH AVENUE VIADUCT BETWEEN WEST 34TH STREET AND WEST 39TH STREET, ETC...(HUDSON YARDS FUNDING) | 2019 | 16588 | 21.37 | 556 | 0 | 0 | 0 | 0 | 0 | 577.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002169 | RECON OF COMBINED SEWER & WM IN YORK AVE | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 308 | SE-0002M WM-0001 HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | RECON OF COMB SWR & WM IN YORK AV B/T 61 & 63 STREET | 2019 | 1220 | 12218.85 | 4817 | 0 | 0 | 0 | 0 | 0 | 17035.85 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 36
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002178 | Replacement & guniting comb SE in W. Broadway | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 301 | SE-0002M |  |  | COMBINED SEWER REPLACEMENT AND GUNITING IN WEST BROADWAY BETWEEN THOMAS & LEONARD STREET | 2019 | 1069 | 0 | 0 | 1069 | 0 | 0 | 0 | 0 | 1069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | TAVREH | Tavern on the Green Structure | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION |  | P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | RENOVATION OF TAVERN ON THE GREEN STRUCTUE - LANDMARK BUILDING | 2019 | 10894 | 20272.06 | 0 | 0 | 150 | 0 | 0 | 0 | 20422.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | TF18-2007 | DELANCEY AND ESSEX MUNICIPAL PARKING GARAGE,MANHATTAN | Parking Meters, Lots, and Garages | 300 303 | TF-0018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | DELANCEY AND ESSEX MUNICIPAL PARKING GARAGE | DELANCEY AND ESSEX MUNICIPAL PARKING GARAGE | 2019 | 2280 | 8461.17 | 547 | 0 | 0 | 19 | 0 | 0 | 9027.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACECAS801 | Cogeneration Plant for 115 Chrystie | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 301 | PU-0025 |  |  | COGENERATION PLANT FOR 115 CHRYSTIE | 2019 | 300 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOE701 | DOE - STEAM SYSTEM OPTIMIZATION | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 301 | PU-0025 |  |  | DOE - STEAM SYSTEM OPTIMIZATION | 2019 | 5661 | 0 | 0 | 5661 | 0 | 0 | 0 | 0 | 5661 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOT901 | DOT- Boiler for Whitehall Ferry Terminal | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 301 | PU-0025 |  |  | BOILER FOR WHITEHALL FERRY TERMINAL | 2019 | 0 | 0 | 0 | 226 | 0 | 0 | 0 | 0 | 226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEFDN901 | FDNY- Solar PV at FDNY Academy Building 12 | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 301 | PU-0025 |  |  | SOLAR PV AT FDNY ACADEMY BUILDING 12 | 2019 | 0 | 0 | 0 | 868 | 0 | 0 | 0 | 0 | 868 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEFIT701 | FIT -1500 TON ELECTRIC CHILLER | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 301 | PU-0025 |  |  | FIT -1500 TON ELECTRIC CHILLER | 2019 | 6920 | 3000 | 3920 | 0 | 0 | 0 | 0 | 0 | 6920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEFIT901 | FIT - Chiller Optimization at FIT Building D | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 301 | PU-0025 |  |  | FIT - CHILLER OPTIMIZATION AT FIT BUILDING D | 2019 | 0 | 0 | 0 | 896 | 0 | 0 | 0 | 0 | 896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEFIT902 | FIT - Chiller Heat Recovery at FIT Alumni Hall | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 301 | PU-0025 |  |  | FIT - CHILLER HEAT RECOVERY AT FIT ALUMNI HALL | 2019 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEFIT903 | FIT - Solar PV at FIT Building E | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 301 | PU-0025 |  |  | FIT - SOLAR PV AT FIT BUILDING E | 2019 | 0 | 0 | 0 | 180 | 0 | 0 | 0 | 0 | 180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEHHC602 | HHC - BELLEVUE LIGHTING AND CONTROLS AND AHU UPGRADES | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 306 | PU-0025 HO-0214 |  |  | HHC - NYC HEALTH & HOSPITALS : LIGHTING AND CONTOLS UPGRADE | 2019 | 15251 | 0 | 10863 | 3788 | 200 | 0 | 0 | 0 | 14851 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | AGHVACRM | 2 Lafayette 9th floor DFTA IT room HVAC upgrade | DEPARTMENT FOR THE AGING BUILDING RECONSTRUCTION | 301 | AG-0001 |  |  | 2 LAFAYETTE 9TH FLOOR DFTA IT ROOM HVAC UPGRADE | 2019 | 607 | 0 | 457 | 0 | 0 | 0 | 0 | 0 | 457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO283BLR | 100 CENTRE ST.- BOILER BURNERS AND CONTROLS | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 301 | CO-0283 |  |  | SQ FT | 2019 | 0 | 0 | 0 | 0 | 1054 | 0 | 987 | 0 | 2041 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO283CTSP | 100 CENTRE ST- COOLING TOWERS TO REPLACE SPRAY PONDS | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 301 | CO-0283 |  |  | 100 CENTRE - TOWERING SYSTEM TO REPLACE SPRAY PONDS | 2019 | 9716 | 12782.17 | 801 | 0 | 0 | 0 | 0 | 0 | 13583.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO283FIRE | 100 CENTRE ST.- FIRE SAFETY | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 301 | CO-0283 |  | 100 CENTRE ST MANHATTAN | MAKE FIRE SAFETY SYSTEM CODE COMPLIANT | 2019 | 7730 | 8817.52 | 283 | 0 | 0 | 0 | 0 | 0 | 9100.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO283FP | 100 CENTRE ST.- FIRE PUMP | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 301 | CO-0283 |  |  | THE FIRE ALARM SYSTEM AT MANHATTAN CRIMINAL COURT . | 2019 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO283LL11 | 100 CENTRE ST - FACADE RECONSTRUCTION | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 301 | CO-0283 |  |  | 100 CENTRE ST.- FAÝADE REPAIRS LL 11 | 2019 | 0 | 0 | 0 | 0 | 0 | 465 | 0 | 5113 | 5578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO283SG | 100 CENTRE ST. - SAFETY GRATINGS | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 301 | CO-0283 |  |  | 100 CENTRE STREET SAFETY GRATINGS | 2019 | 190 | 0 | 0 | 0 | 0 | 40 | 150 | 0 | 190 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO283WT | 100 CENTRE STREET - WATER TANK | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 301 | CO-0283 |  |  | 100 CENTRE STREET - WATER TANK | 2019 | 0 | 0 | 0 | 0 | 0 | 39 | 3200 | 0 | 3239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO304HEA2 | 60 CENTRE STREET- SPRINKLERS | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 301 | CO-0304 |  |  | 60 CENTRE STREET - HEATING UPGRADE - SPRINKLERS | 2019 | 20210 | 0 | 0 | 0 | 0 | 1700 | 0 | 16365 | 18065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO304HEA5 | 60 CENTRE ST.- HEATING DISTRIBUTION SYSTEM | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 301 | CO-0304 |  |  | 60 CENTRE ST.- HEATING DISTRIBUTION SYSTEM | 2019 | 31293 | 0 | 0 | 0 | 0 | 0 | 1900 | 26462 | 28362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO305REHB | 314 W. 54TH ST.- MIDTOWN COMM COURT EXPANSION | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 304 | CO-0305 CO-0264 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 314 W. 54TH ST. NY, NY 10019 | ROOF REPLACEMENT; INSTALLATION OF FIRE SAFETY SYSTEM; ELECTRICAL & HVAC UPGRADE; FACADE RECONSTRUCTION; WINDOW & SKYLIGHT REPLACEMENT; ELEVATOR MODERNIZATION | 2019 | 17830 | 31456.79 | 197 | 999 | 0 | 0 | 0 | 0 | 32652.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO306EXT2 | 170 E121 ST. EXTERIOR - LL11 | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 311 | CO-0306 |  |  | FACADE | 2019 | 1633 | 0 | 0 | 0 | 0 | 258 | 2581 | 0 | 2839 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO306MHCB | 170 E. 121 ST. - HARLEM COURT BOILER | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 311 | CO-0306 |  |  | BOILER REPLACEMENT | 2019 | 770 | 0 | 0 | 0 | 0 | 885 | 0 | 0 | 885 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO81LL11 | 31 CHAMBERS ST - FACADE REHAB | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 301 | CO-0081 |  |  | 31 CHAMBERS ST - FAÝADE REPAIRS LOCAL LAW 11 | 2019 | 0 | 0 | 0 | 0 | 0 | 635 | 0 | 0 | 635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E09-00006 | DPR - 09-047: Central Park Zoo, 830 5th Avenue | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 308 | PU-0025 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ENERGY EFFICIENCY UPGRADE AT CENTRAL PARK ZOO; 830 5TH AVENUE | 2019 | 3164 | 201.05 | 742 | 0 | 0 | 0 | 0 | 0 | 943.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E13-0002 | NYPD One Police Plaza Comprehensive Upgrade | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 301 | PU-0025 |  |  | NYPD ONE POLICE PLAZA COMPREHENSIVE UPGRADE | 2019 | 15701 | 16145.95 | 0 | 1595 | 0 | 0 | 0 | 0 | 17740.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E19-0009 | NYPD - 20th Precinct | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 301 | PU-0025 |  |  | NYPD - 20TH PRECINCT | 2019 | 1378 | 0 | 381 | 997 | 0 | 0 | 0 | 0 | 1378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0018 | DCLA - Lincoln Center Campus: Damrosch Park/Public Spaces | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 301 | PU-0025 |  |  | DCLA - LINCOLN CENTER CAMPUS: DAMROSCH PARK/PUBLIC SPACES/GARAGES | 2019 | 900 | 0 | 0 | 900 | 0 | 0 | 0 | 0 | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0019 | DCLA - Lincoln Center Campus: Plaza/Public Spaces/Garages | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 301 | PU-0025 |  |  | DCLA - LINCOLN CENTER CAMPUS: PLAZA/PUBLIC SPACES/GARAGES | 2019 | 900 | 0 | 0 | 900 | 0 | 0 | 0 | 0 | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0026 | NYPL - The Library for the Performing Arts | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 301 | PU-0025 |  |  | NYPL - THE LIBRARY FOR THE PERFORMING ARTS | 2019 | 900 | 0 | 0 | 900 | 0 | 0 | 0 | 0 | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0034 | DPR-Central Park Campus: Wollman Rink | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 301 | PU-0025 |  |  | DPR-CENTRAL PARK CAMPUS: WOLLMAN RINK | 2019 | 250 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0036 | DPR - Central Park Campus: CPC 79th St Maintenance Yard | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 301 | PU-0025 |  |  | DPR - CENTRAL PARK CAMPUS: CPC 79TH ST MAINTENANCE YARD | 2019 | 83 | 0 | 83 | 0 | 0 | 0 | 0 | 0 | 83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0039 | NYPD - Police Headquarters | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 301 | PU-0025 |  |  | NYPD - POLICE HEADQUARTERS | 2019 | 874 | 0 | 874 | 0 | 0 | 0 | 0 | 0 | 874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0041 | Manhattan Borough Repair Shop | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 301 | PU-0025 |  |  | MANHATTAN BOROUGH REPAIR SHOP | 2019 | 700 | 0 | 0 | 700 | 0 | 0 | 0 | 0 | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0046 | CUNY - BMCC Campus: Chambers St. Building (Main Campus) | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 301 | PU-0025 |  |  | CUNY - BMCC CAMPUS: CHAMBERS ST. BUILDING (MAIN CAMPUS) | 2019 | 900 | 0 | 0 | 900 | 0 | 0 | 0 | 0 | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79-375P | 375 Pearl Street Renovation | POLICE FACILITIES | 300 | PO-0079 |  |  | COST ESTIMATE | 2019 | 0 | 0 | 11356 | 0 | 0 | 0 | 0 | 0 | 11356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79CEDR | RELOCATION OF WTC COMMAND FROM 130 CEDAR | POLICE FACILITIES | 300 | PO-0079 |  |  | RELOCATION OF WTC COMMAND FROM 130 CEDAR | 2019 | 0 | 0 | 2455 | 195 | 0 | 0 | 0 | 0 | 2650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79CONVT | NYPD move from 3280 Broadway to 32 Convent Avenue | POLICE FACILITIES | 301 | PO-0079 |  |  | FULL TENANT BUILD OUT FOR NYPD MOVE FROM 3280 BROADWAY TO 32 CONVENT AVENUE | 2019 | 10403 | 136.12 | 0 | 0 | 0 | 5847 | 0 | 0 | 5983.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW19325A | 1 CENTRE ST.- 25TH FL BUILDOUT PH1 - SOUTH | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0193 |  |  | DQ FT | 2019 | 0 | 0 | 0 | 3971 | 0 | 0 | 0 | 0 | 3971 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW19325B | 1 CENTRE ST.- 25TH FL BUILDOUT PH 2 - NORTH | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0193 |  |  | SQ FT | 2019 | 0 | 0 | 0 | 0 | 8075 | 0 | 0 | 0 | 8075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW193ALM | 1 CENTRE ST. - FIRE ALARM | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0193 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RECONSTRUCT FIRE ALARM SYSTEM | 2019 | 4410 | 7949.71 | 100 | 0 | 0 | 0 | 0 | 0 | 8049.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW193CHL2 | 1 CENTRE ST.- REHAB AND FRICTIONLESS CHILLER MODERNIZATION | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0193 |  |  | 1 CENTRE ST.- REHAB AND FRICTIONLESS CHILLER MODERNIZATION | 2019 | 618 | 415 | 0 | 60 | 0 | 0 | 0 | 0 | 475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW193FANS | 1 CENTRE ST. - REPLACEMENT OF LOBBY FANS | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0077 |  |  | DEMOLITION OF FANS AND ASSOCIATED EQUIPMENT AND ACCESSORIES; FIELD ERECTION OF FANS, COMPLETE WITH STEAM HEATING COILS, DUCTWORK, PIPING, INSULATION, CONTROL, AND ASSOCIATED ELECTRICAL AND GC WORK. | 2019 | 1575 | 154.62 | 0 | 0 | 0 | 0 | 0 | 1291 | 1445.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW193MOME | MOME - A/C AND ANCILLARY WORK | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0193 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | SQ FT | 2019 | 600 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW195RF | 80 CENTRE ST.- ROOF REPLACEMENT | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0195 |  |  | SQ FT | 2019 | 4925 | 0 | 0 | 0 | 0 | 482 | 4200 | 0 | 4682 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW266TOIL | 125 WORTH ST.- CODE COMPLIANT TOILET UPGRADES | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0077 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CODE COMPLIANT TOILET UPGRADES | 2019 | 2450 | 0 | 0 | 0 | 250 | 2200 | 0 | 0 | 2450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW293125D | 125 WORTH STREET - FIRE ALARM -SPRINKLERS | LEGAL MANDATES AND CORRECTION OF UNSAFE CONDITIONS | 301 | PW-0293 |  |  | 125 WORTH STREET - FIRE ALARM DESIGN | 2019 | 0 | 0 | 0 | 0 | 3612 | 0 | 45145 | 0 | 48757 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW2931C | 1 CENTRE STREET - FIRE SPRINKLERS | LEGAL MANDATES AND CORRECTION OF UNSAFE CONDITIONS | 301 | PW-0293 |  |  | 1 CENTRE STREET - FIRE SPRINKLERS | 2019 | 47865 | 86.41 | 0 | 0 | 4280 | 0 | 42786 | 0 | 47152.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW308PS1 | MAYOR'S OFFICE - 100 GOLD ST - PRINTSHOP UPGRADE | EQUIPMENT AND INTERAGENCY SERVICES | 301 | PW-0308 |  |  |  | 2019 | 0 | 0 | 0 | 704 | 0 | 0 | 0 | 0 | 704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW310COOL | 31 CHAMBERS ST.- COLD STORAGE SYSTEM FOR DORIS | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0310 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 31 CHAMBERS ST. NY, NY 10007 | REPLACEMENT OF 2 COOLING TOWERS; REPLACEMENT OF PUMPS, CONTROLS, & STEEL DUNNAGE | 2019 | 775 | 5.48 | 0 | 0 | 0 | 365 | 0 | 0 | 370.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW310FAN | 31 CHAMBERS ST. - REPLACEMENT OF FAN COIL UNITS ON FIRST FL. | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0310 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | REPLACE EXISITNG 20 FAN COIL UNITS ON FIRST FLOOR, ASSOCIATED EQUIPMENT AND CONTROLS. EQUIPMENT HAS EXCEEDED ITS USEFUL LIFE SPAN. PERFORMALL RELATED MARBLE WORK. | 2019 | 1035 | 284.3 | 0 | 0 | 0 | 0 | 1122 | 0 | 1406.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW324OMIS | DCAS IT LUMP SUM | EQUIPMENT AND INTERAGENCY SERVICES | 301 | PW-0324 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | VARIOUS DCAS FACILITIES |  | 2019 | 22998 | 798.33 | 65 | 616 | 3400 | 4342 | 4429 | 29853 | 43503.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW32671T | OCA LEASE RENEWAL AT 151 WEST BROADWAY/71 THOMAS St | RENOVATION OF LEASED SPACE | 301 | PW-0326 |  |  | OCA LEASE RENEWAL AT 151 WEST BROADWAY/71 THOMAS ST | 2019 | 1518 | 0 | 0 | 0 | 1518 | 0 | 0 | 0 | 1518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DOB4 | DOB - 11 PARK PL RENEWAL | RENOVATION OF LEASED SPACE | 301 | PW-0326 |  |  | SQ FT | 2019 | 1579 | 0 | 1579 | 0 | 0 | 0 | 0 | 0 | 1579 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326LAW6 | LAW - 233 BROADWAY RELOCATE FROM 100 CHURCH | RENOVATION OF LEASED SPACE | 301 | PW-0326 |  |  | SQFT | 2019 | 6243 | 0 | 5122 | 1121 | 0 | 0 | 0 | 0 | 6243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326OLR1 | OLR - 40 RECTOR STREET RELOCATION | RENOVATION OF LEASED SPACE | 301 | PW-0326 |  |  | OLR - 40 RECTOR STREET RELOCATION | 2019 | 5119 | 0 | 5119 | 0 | 0 | 0 | 0 | 0 | 5119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326OMBP | OMB Pantry at 255 Greenwich | RENOVATION OF LEASED SPACE | 301 | PW-0326 |  |  | LEASED SPACE - RENOVATION OF OMB PANTRY AT 255 GREENWICH | 2019 | 0 | 0 | 112 | 75 | 0 | 0 | 0 | 0 | 187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326PDCC | MAYOR'S OFFICE- COMMISSION TO COMBAT NYPD CORRUPTION | RENOVATION OF LEASED SPACE | 301 | PW-0326 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | MAYOR'S OFFICE COMMISSION TO COMBAT NYPD CORRUPTION - RELOCATE FROM 17 BATTERY PLACE | 2019 | 663 | 7.44 | 0 | 0 | 543 | 0 | 0 | 0 | 550.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RAM | LAW DEPT - RAISE THE AGE - MANHATTAN | RENOVATION OF LEASED SPACE | 301 | PW-0326 |  |  | LAW DEPT - RAISE THE AGE - MANHATTAN | 2019 | 0 | 0 | 0 | 4682 | 0 | 0 | 0 | 0 | 4682 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326TOR1 | LAW DEPT TORTS - 233 BROADWAY 5 FL | RENOVATION OF LEASED SPACE | 301 | PW-0326 |  |  | LAW DEPARTMENT TORTS - NEW PROGRAM | 2019 | 5483 | 0 | 2430 | 3053 | 0 | 0 | 0 | 0 | 5483 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326ZM03 | CBMN - RELOCATE COMM BD 3 FROM 59 E. 4TH STREET | RENOVATION OF LEASED SPACE | 301 | PW-0326 |  |  | MANHATTAN COMMUNITY BOARD 3 - RELOCATION FROM 59 EAST 4TH STREET | 2019 | 226 | 0 | 0 | 0 | 226 | 0 | 0 | 0 | 226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326ZM09 | CBMN - MANHATTAN COMMUNITY BOARD 9 | RENOVATION OF LEASED SPACE | 301 | PW-0326 |  |  | MANHATTAN COMMUNITY BOARD 9 | 2019 | 271 | 0 | 0 | 604 | 0 | 0 | 0 | 0 | 604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW327PLZ2 | 1 CENTRE STREET PLAZA REHABILITATION | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0327 |  |  | 1 CENTRE STREET PLAZA REHABILITATION | 2019 | 0 | 0 | 0 | 869 | 0 | 10424 | 0 | 0 | 11293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW340FIP2 | BOE- FACILITIES IMPROVEMENT PROJECT | BOARD OF ELECTIONS MODERNIZATION | 301 | PW-0340 |  |  | FACILITIES IMPROVEMENT PROJECT | 2019 | 0 | 0 | 0 | 394 | 0 | 0 | 0 | 0 | 394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW357ELC2 | 253 BROADWAY- ELECTRICAL UPGRADES PHASE 2 | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0357 |  |  | 253 BROADWAY- ELECTRICAL UPGRADES | 2019 | 5200 | 0 | 0 | 960 | 0 | 11520 | 0 | 0 | 12480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW357EXTR | 253 BROADWAY- EXTERIOR AND ROOF | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0357 PW-0077 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 253 BROADWAY, MANHATTAN | RECONSTRUCT ROOF AND EXTERIOR/FACADE | 2019 | 13208 | 32220.32 | 171 | 6 | 0 | 0 | 141 | 0 | 32538.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW357SA | 253 AND 256 BROADWAY- SAFE ACCESS CATWALK | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0357 |  |  | 253 AND 256 BROADWAY - SAFE ACCESS CATWALK | 2019 | 188 | 0 | 0 | 0 | 0 | 0 | 167 | 0 | 167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW357STM2 | 253 BROADWAY - RECONSTRUCT STEAM STATION | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0357 |  |  | RECONSTRUCT STEAM STATION AT 253 BROADWAY | 2019 | 2364 | 0 | 0 | 200 | 0 | 2164 | 0 | 0 | 2364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW357VAUL | 253 BROADWAY - VAULT RECONSTRUCTION | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0357 |  |  | SQ/IA | 2019 | 10678 | 0 | 0 | 227 | 9480 | 0 | 0 | 0 | 9707 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77102S3 | CITY HALL STEPS RECONSTRUCTION | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0077 |  |  | STEPS | 2019 | 3284 | 0 | 0 | 247 | 0 | 2741 | 0 | 0 | 2988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77115CH | 115 CHRYSTIE ST. - INTERIOR RENOVATIONS | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0077 |  |  | INTERIOR RENOVATIONS | 2019 | 4262 | 0 | 0 | 0 | 0 | 673 | 2689 | 0 | 3362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77117SA | 137 CENTRE ST. - SAFE ACCESS | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0077 |  |  | 137 CENTRE STREET SAFETY GRATINGS | 2019 | 402 | 0 | 0 | 0 | 0 | 40 | 308 | 0 | 348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77136A | DOP - 60 LAFAYETTE ST, 2ND FL RENOVATIONS | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0077 |  |  | SQ/IA | 2019 | 3985 | 0 | 0 | 0 | 3985 | 0 | 0 | 0 | 3985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77137C | 137 CENTRE ST. Renovation | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0077 |  |  | 137 CENTRE ST. RENOVATION | 2019 | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW771C09 | 1 CENTRE ST. - 9th Floor Renovation | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0077 |  |  | 1 CENTRE ST. - 9TH FLOOR RENOVATION | 2019 | 20000 | 0 | 0 | 0 | 0 | 1600 | 0 | 18400 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW771C21 | 1 CENTRE ST. - 21st Floor Renovation | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0077 |  |  | 1 CENTRE ST. - 21ST FLOOR RENOVATION | 2019 | 20000 | 0 | 0 | 0 | 0 | 1600 | 16800 | 1600 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW7722R5 | 22 READE ST.- 5th AND 6th FLOOR BUILDOUT | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0077 |  |  | $390 PER SQ FT | 2019 | 9930 | 0 | 0 | 0 | 820 | 8208 | 0 | 0 | 9028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW7722REV | 22 READE ST.- ELEVATOR MODERNIZATION | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0077 |  |  | DCAS - 22 READE STREET ELEVATOR MODERNIZATION | 2019 | 2976 | 165 | 2581 | 0 | 0 | 0 | 0 | 0 | 2746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77BOC | 2 LAFAYETTE ST.BOC Renovation | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0077 |  |  | BOARD OF CORRECTIONS INTERIOR RENOVATION AT 2 LAFAYETTE STREET, 12TH FLOOR. | 2019 | 0 | 0 | 14 | 1183 | 0 | 0 | 0 | 0 | 1197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77CCSS | CIVIC CENTER SWING SPACE | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0077 |  |  | CIVIC CENTER SWING SPACE | 2019 | 0 | 0 | 0 | 0 | 4800 | 2400 | 2400 | 7200 | 16800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77DAK01 | NY COUNTY DA'S OFFICE FIRE UPGRADES | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0077 PW-0293 |  |  | NY COUNTY DA'S OFFICE - FIRE ALARM SYSTEM UPGRADES AT 80 CENTRE AND 100 CENTRE STREET | 2019 | 308 | 126.99 | 0 | 322 | 0 | 0 | 0 | 0 | 448.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77DATU | DA MANHATTAN - ADA BATHROOM UPGRADE | LEGAL MANDATES AND CORRECTION OF UNSAFE CONDITIONS | 301 | PW-0077 |  |  | ADA AT 100 CENTRE ST | 2019 | 0 | 0 | 0 | 0 | 283 | 2000 | 0 | 0 | 2283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77FL25 | 1 CENTRE ST.- NYC MEDIA FACILITY | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0077 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | 1 CENTRE STREET NYC MEDIA TECHNICAL FACILITY | 2019 | 15440 | 1165.47 | 1885 | 0 | 0 | 0 | 0 | 0 | 3050.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLD2F | 100 GOLD STREET 2 FLOOR - MOCs | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0077 |  |  | 100 GOLD STREET 2 FLOOR - MOCS | 2019 | 0 | 0 | 780 | 7950 | 1936 | 0 | 0 | 0 | 10666 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLDBR | 100 GOLD ST - BATHROOM RENOVATION | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0077 |  |  | 100 GOLD ST - BATHROOM RENOVATION | 2019 | 0 | 0 | 0 | 0 | 0 | 6617 | 0 | 0 | 6617 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLDDR | 100 GOLD ST.- ROOFTOP DAMPER REPLACEMENT | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0077 |  |  | SQ FT | 2019 | 0 | 0 | 0 | 0 | 0 | 438 | 0 | 0 | 438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLDFA | 100 GOLD ST - FIRE ALARM | REHABILITATION OF CITY-OWNED OFFICE SPACE | 300 | PW-0077 |  |  | 100 GOLD ST - FIRE ALARM | 2019 | 0 | 0 | 0 | 1200 | 0 | 14400 | 0 | 0 | 15600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLDRF | 100 GOLD ST. - ROOF RECONSTRUCTION | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0077 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RECONSTRUCT ROOF 100 GOLD ST | 2019 | 2004 | 5217.44 | 113 | 0 | 0 | 0 | 0 | 0 | 5330.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLDSA | 100 GOLD ST. - SAFE ACCESS/CATWALK | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0077 |  |  | 100 GOLD ST.- SAFE ACCESS/CATWALK | 2019 | 67 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77MU8EL | 1 CENTRE ST.- 8TH FL. COMPTROLLERS OFFICE RENOVATIONS | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0077 |  |  | 1 CENTRE STREET 8TH FLOOR ELECTRICAL AND LIGHTING UPGRADE | 2019 | 15094 | 14228.3 | 246 | 380 | 0 | 0 | 0 | 0 | 14854.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77PA16 | 1 CENTRE ST.- PUBLIC ADVOCATE OFFICE | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0077 |  |  | PUBLIC ADVOCATE'S OFFICE -- RENOVATION OF OFFICE SPACE - 1 CENTRE STREET | 2019 | 540 | 0 | 0 | 0 | 604 | 0 | 0 | 0 | 604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SANIT | DSNY - RELOCATE DSNY SPACE FROM 137 CENTRE ST. | RENOVATION OF LEASED SPACE | 301 | PW-0326 |  |  | 137 CENTRE ST. - RELOCATION OF DSNY SPACE | 2019 | 0 | 7135.14 | 1794 | 0 | 900 | 0 | 0 | 0 | 9829.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC1C | 1 CENTRE ST - DCAS POLICE CCTV SYSTEM UPGRADE | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0077 |  |  | SQ/IA | 2019 | 0 | 0 | 370 | 0 | 1623 | 0 | 0 | 0 | 1993 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC22R | 22 READE ST - DCAS POLICE CCTV SYSTEM | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0077 |  |  | SQ/IA | 2019 | 0 | 0 | 0 | 0 | 740 | 0 | 0 | 0 | 740 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC280 | 280 BROADWAY - DCAS POLICE CCTV SYSTEM | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0077 |  |  | SQ/IA | 2019 | 0 | 0 | 0 | 0 | 740 | 0 | 0 | 0 | 740 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC2C | 2 LAFAYETTE ST - DCAS POLICE CCTV SYSTEM | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0077 |  |  | SQ/IA | 2019 | 0 | 0 | 0 | 0 | 835 | 0 | 0 | 0 | 835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW80CT1 | 2 LAFAYETTE ST.- COOLING TOWER | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0080 |  |  | UNIT | 2019 | 0 | 0 | 0 | 0 | 558 | 0 | 0 | 0 | 558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW80ELEC | 2 LAFAYETTE STREET ELECTRICAL UPGRADE | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0080 |  |  | 2 LAFAYETTE STREET ELECTRICAL UPGRADE PHASE 2 | 2019 | 13000 | 0 | 0 | 0 | 1000 | 0 | 12000 | 0 | 13000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWCN001 | Sixth Street compost project | MISCELLANEOUS CONSTRUCTION | 300 303 | PW-D077 |  |  | SIXTH STREET COMPOST PROJECT | 2019 | 68 | 0 | 0 | 68 | 0 | 0 | 0 | 0 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD05CYBR | 80 CENTRE ST. - NY COUNTY DA CYBERCRIME AND IDENTITY THEFT | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-D005 |  |  | NY COUNTY DA'S OFFICE CYBERCRIME AND ID THEFT - CONSTRUCTION/OUTFITTING OF 11,307 SQ FT SPACE | 2019 | 5240 | 3629.75 | 92 | 0 | 0 | 0 | 0 | 0 | 3721.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD05DAHV | 80 CENTRE ST. - NY COUNTY DA HVAC UPGRADE SERVER ROOM | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-D005 |  |  | NEW YORK COUNTY DISTRICT ATTORNEY'S OFFICE -REPLACING THE HVAC SYSTEMIN THREE IT NETWORK ROOMS | 2019 | 0 | 0 | 0 | 479 | 0 | 0 | 0 | 0 | 479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD5BAG | 1 CENTRE ST.- BIG APPLE GREETER | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-D005 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BIG APPLE GREETER AT 1 CENTRE ST. | 2019 | 917 | 213.98 | 0 | 0 | 0 | 0 | 0 | 200 | 413.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWDNTEW | NONTRADITIONAL EMPLOYMENT FOR WOMEN 243 W 20th St | MISCELLANEOUS CONSTRUCTION |  | PW-D005 |  |  | NON-TRADITIONAL EMPLOYMENT FOR WOMEN -- BUILDING RENOVATION OF 243 W 20TH ST | 2019 | 0 | 0 | 0 | 800 | 0 | 0 | 0 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWM77FJC | 80 CENTRE ST. - MANHATTAN FAMILY JUSTICE CENTER | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-M077 PW-D077 PW-0077 |  |  | MANHATTAN FAMILY JUSTICE CENTER AT 80 CENTRE STREET | 2019 | 5000 | 8738.68 | 121 | 0 | 20 | 0 | 0 | 0 | 8879.68 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 100
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWMOCSIT1 | MOCS IT NETWORK INFRASTRUCTURE 100 GOLD STREET 2ND FL | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0077 |  |  | MOCS IT NETWORK INFRASTRUCTURE 100 GOLD STREET 2ND FL | 2019 | 0 | 0 | 0 | 622 | 0 | 0 | 0 | 0 | 622 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | SOLARDCLA | DCLA - David H Koch Theater Rooftop Solar PV | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 301 | PU-0025 |  |  | DCLA - DAVID H KOCH THEATER ROOFTOP SOLAR PV | 2019 | 0 | 0 | 0 | 350 | 0 | 862 | 0 | 0 | 1212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQ122-GEN | SYSTEMWIDE - General Projects/Infrastructure | ESSENTIAL RECONSTRUCTION OF FACILITIES | 400 | LQ-0122 |  |  | GENERAL PROJECTS / INFRASTRUCTURE | 2019 | 5691 | 0 | 0 | 7000 | 5000 | 5988 | 746 | 5029 | 23763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQBCHREAD | BROAD CHANNEL: Library Seating Area | ESSENTIAL RECONSTRUCTION OF FACILITIES | 400 | LQ-D122 |  |  | LIBRARY SEATING AREA | 2019 | 250 | 0 | 0 | 23 | 0 | 207 | 0 | 0 | 230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQBC-ROOF | BROAD CHANNEL: New roof | RECONSTRUCTION NECESSARY TO MAINTAIN FACILITIES | 400 | LQ-0122 |  |  | NEW ROOF | 2019 | 545 | 0 | 0 | 0 | 64 | 426 | 0 | 0 | 490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQBPEXPN | BAISLEY PARK - Branch Renovation | REPLACEMENT BRANCHES | 412 | LQ-D122 LQ-Q122 LQ-Q005 |  |  | BAISLEY PARK - EXPANSION | 2019 | 6500 | 0 | 0 | 649 | 0 | 92 | 5945 | 0 | 6686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQBR-ROOF | BROADWAY - ROOF | ESSENTIAL RECONSTRUCTION OF FACILITIES | 400 | LQ-0122 |  |  | BROADWAY ROOF | 2019 | 1002 | 0 | 0 | 0 | 117 | 783 | 0 | 0 | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQBTRENOV | BAY TERRACE: Branch Renovation and Expansion | ESSENTIAL RECONSTRUCTION OF FACILITIES | 400 | LQ-D122 LQ-0122 LQ-Q122 |  |  | BAY TERRACE RENOVATION | 2019 | 3822 | 0 | 0 | 428 | 0 | 3128 | 0 | 0 | 3556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQBW-EXP | Briarwood: Branch Renovation | ESSENTIAL RECONSTRUCTION OF FACILITIES | 400 | LQ-0122 LQ-D122 |  |  | ROOF AND EXTERIOR UPGRADE | 2019 | 12901 | 0 | 0 | 1370 | 0 | 9344 | 1000 | 0 | 11714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQC122-JH | JACKSON HEIGHTS - Branch Expansion & Renovation | REPLACEMENT BRANCHES | 403 | LQ-D122 LQ-0122 |  | 35-51 81ST ST, JACKSON HEIGHTS 11372 | EXPANSION OF EXISTING BUILDING | 2019 | 2250 | 0 | 0 | 1717 | 0 | 12445 | 14346 | 0 | 28508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQCA19FRH | FOREST HILLS: Site work and drainage | RECONSTRUCTION NECESSARY TO MAINTAIN FACILITIES | 400 | LQ-D122 |  |  | FOREST HILLS: SITE WORK AND DRAINAGE | 2019 | 425 | 0 | 0 | 46 | 0 | 339 | 0 | 0 | 385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQCA19LHS | LANGSTON HUGHES:BMS SYSTEM | RECONSTRUCTION NECESSARY TO MAINTAIN FACILITIES | 400 | LQ-D122 |  |  | BMS SYSTEM | 2019 | 150 | 0 | 0 | 0 | 136 | 0 | 0 | 0 | 136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQCA19QVG | QUEENS VILLAGE: Exterior Rehabilitation, ADA Access, Windows | ESSENTIAL RECONSTRUCTION OF FACILITIES | 400 | LQ-D122 |  |  | EXTERIOR REHABILITATION, ADA ACCESS, WINDOWS | 2019 | 4400 | 0 | 0 | 478 | 0 | 3507 | 0 | 0 | 3985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQCA19WSD | WOODSIDE: Branch Renovation | ESSENTIAL RECONSTRUCTION OF FACILITIES | 400 | LQ-D122 |  |  | BRANCH RENOVATION | 2019 | 16156 | 0 | 0 | 707 | 0 | 9181 | 0 | 0 | 9888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQCELHVAC | CENTRAL LIBRARY BMS/COOLING TOWER | ESSENTIAL RECONSTRUCTION OF FACILITIES | 400 | LQ-D122 |  |  | CENTRAL LIBRARY BMS/COOLING TOWER | 2019 | 2000 | 0 | 0 | 0 | 195 | 1623 | 0 | 0 | 1818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQCLDC-CE | Central Library: Rehabilitation of Ceilings | RECONSTRUCTION NECESSARY TO MAINTAIN FACILITIES | 400 | LQ-0122 LQ-D122 |  |  | CENTRAL LIBRARY: REHABILITATION OF CHILDREN'S LIBRARY DISCOVERY CENTER CEILINGS. | 2019 | 392 | 0 | 0 | 0 | 355 | 0 | 0 | 0 | 355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQCORENOV | CORONA : Branch Expansion and Renovation | REPLACEMENT BRANCHES | 400 | LQ-D122 LQ-0122 LQ-D001 |  |  | CORONA RENOVATION | 2019 | 31064 | 0 | 0 | 0 | 2877 | 0 | 21139 | 957 | 24973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQD122LAE | LAURELTON: Branch Renovation | RECONSTRUCTION NECESSARY TO MAINTAIN FACILITIES | 400 | LQ-D122 LQ-0122 |  |  |  | 2019 | 11233 | 0 | 0 | 1145 | 0 | 9126 | 0 | 0 | 10271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQD122VEN | Breezy Point - Kiosk | SUPPORT SERVICES IMPROVEMENTS | 414 | LQ-D001 LQ-D122 |  |  | VENDING MACHINES | 2019 | 984 | 0 | 0 | 0 | 929 | 0 | 0 | 0 | 929 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQEM19FFA | FLUSHING: FIRE ALARM | ESSENTIAL RECONSTRUCTION OF FACILITIES | 400 | LQ-0122 |  |  | FLUSHING: FIRE ALARM | 2019 | 551 | 0 | 0 | 49 | 0 | 451 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQEM19FLU | FLUSHING:Emergency Functionality | ESSENTIAL RECONSTRUCTION OF FACILITIES | 400 | LQ-0122 |  |  | FLUSHING:EMERGENCY FUNCTIONALITY | 2019 | 1190 | 0 | 0 | 75 | 0 | 1000 | 0 | 0 | 1075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQFHREAD | FOREST HILLS OUTDOOR READING SPACE | SUPPORT SERVICES IMPROVEMENTS | 406 | LQ-D122 |  |  | FOREST HILLS OUTDOOR READING SPACE | 2019 | 275 | 0 | 0 | 0 | 423 | 0 | 0 | 0 | 423 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQFHWIND | FOREST HILLS - Windows and Doors Replacement | RECONSTRUCTION NECESSARY TO MAINTAIN FACILITIES | 406 | LQ-Q122 |  |  | FOREST HILLS - WINDOWS AND DOORS REPLACEMENT | 2019 | 600 | 0 | 65 | 0 | 479 | 0 | 0 | 0 | 544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQFM-HVAC | FRESH MEADOWS: HVAC | RECONSTRUCTION NECESSARY TO MAINTAIN FACILITIES | 400 | LQ-0122 |  |  | HVAC | 2019 | 1057 | 0 | 0 | 124 | 0 | 826 | 0 | 0 | 950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQHBW/D | HOWARD BEACH WINDOWS/DOORS | RECONSTRUCTION NECESSARY TO MAINTAIN FACILITIES | 400 | LQ-D122 LQ-0122 |  |  | HOWARD BEACH WINDOWS/DOORS | 2019 | 607 | 0 | 0 | 72 | 0 | 473 | 0 | 0 | 545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQHILRENO | HILLCREST: Renovation | ESSENTIAL RECONSTRUCTION OF FACILITIES | 400 | LQ-D122 |  |  | LIBRARY ROOM RENOVATION | 2019 | 1450 | 0 | 0 | 158 | 0 | 1156 | 0 | 0 | 1314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQLAHEXTR | LANGSTON HUGHES: Exterior Restoration | RECONSTRUCTION NECESSARY TO MAINTAIN FACILITIES | 400 | LQ-D122 LQ-0122 |  |  | EXTERIOR RESTORATION | 2019 | 1116 | 0 | 0 | 122 | 0 | 887 | 0 | 0 | 1009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQLARENOV | LAURELTON - RENOVATION | SUPPORT SERVICES IMPROVEMENTS | 413 | LQ-D122 |  |  | LAURELTON RENOVATION | 2019 | 345 | 0 | 0 | 0 | 345 | 0 | 0 | 0 | 345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQLFK-INT | Lefrak City Library - Interior renovations | ESSENTIAL RECONSTRUCTION OF FACILITIES | 404 | LQ-Q122 |  |  | LEFRAK CITY LIBRARY - INTERIOR RENOVATIONS | 2019 | 5000 | 0 | 0 | 174 | 0 | 2175 | 0 | 0 | 2349 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQLI-ROOF | LONG ISLAND CITY: New Roof | RECONSTRUCTION NECESSARY TO MAINTAIN FACILITIES | 400 | LQ-0122 |  |  | NEW ROOF | 2019 | 1057 | 0 | 0 | 124 | 0 | 826 | 0 | 0 | 950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQMA-HVAC | MASPETH - HVAC | RECONSTRUCTION NECESSARY TO MAINTAIN FACILITIES | 400 | LQ-D122 LQ-0122 |  |  | MASPETH HVAC | 2019 | 1000 | 0 | 0 | 118 | 0 | 782 | 0 | 0 | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQMAROOF | MASPETH ROOF | ESSENTIAL RECONSTRUCTION OF FACILITIES | 400 | LQ-D122 LQ-0122 |  |  | MASPETH ROOF | 2019 | 1056 | 0 | 0 | 124 | 0 | 826 | 0 | 0 | 950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQNO-HVAC | NORTH HILLS - HVAC | ESSENTIAL RECONSTRUCTION OF FACILITIES | 400 | LQ-D122 |  |  | NORTH HILLS - HVAC | 2019 | 850 | 0 | 0 | 83 | 0 | 690 | 0 | 0 | 773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQPOMHVAC | POMONOK - HVAC System Replacement | RECONSTRUCTION NECESSARY TO MAINTAIN FACILITIES | 408 | LQ-Q122 |  |  | POMONOK - HVAC SYSTEM REPLACEMENT | 2019 | 500 | 0 | 0 | 54 | 0 | 399 | 0 | 0 | 453 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQQ122FAO | FAR ROCKAWAY OUTFITTING | ESSENTIAL RECONSTRUCTION OF FACILITIES | 400 414 | LQ-D122 LQ-0122 |  |  |  | 2019 | 4583 | 0 | 0 | 0 | 0 | 4583 | 0 | 0 | 4583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQQV-TECH | QUEENS VILLAGE: Improvements | SUPPORT SERVICES IMPROVEMENTS | 400 | LQ-D122 |  |  | IMPROVEMENTS | 2019 | 200 | 0 | 0 | 0 | 182 | 0 | 0 | 0 | 182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQRS-EXTR | ROSEDALE: Branch Expansion and Renovation | ESSENTIAL RECONSTRUCTION OF FACILITIES | 400 | LQ-0122 LQ-D122 |  |  | EXPANSION AND RENOVATION | 2019 | 13048 | 0 | 0 | 1329 | 0 | 0 | 10867 | 0 | 12196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQSE-ROOF | SEASIDE: New Roof | RECONSTRUCTION NECESSARY TO MAINTAIN FACILITIES | 400 | LQ-0122 |  |  | NEW ROOF | 2019 | 891 | 0 | 0 | 104 | 0 | 696 | 0 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQSE-WIN | SEASIDE: Windows and Doors | RECONSTRUCTION NECESSARY TO MAINTAIN FACILITIES | 400 | LQ-0122 |  |  | WINDOWS AND DOORS | 2019 | 891 | 0 | 0 | 104 | 0 | 696 | 0 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQSHRENOV | SOUTH HOLLIS - INTERIOR RENOVATION | SUPPORT SERVICES IMPROVEMENTS | 400 | LQ-Q122 LQ-D122 |  |  | SOUTH HOLLIS - INTERIOR RENOVATION | 2019 | 8750 | 0 | 0 | 967 | 0 | 6945 | 0 | 0 | 7912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQSJ-INT | SOUTH JAMAICA: Branch Renovation | ESSENTIAL RECONSTRUCTION OF FACILITIES | 400 | LQ-0122 |  |  | INTERIOR RENOVATION | 2019 | 15195 | 0 | 0 | 946 | 0 | 0 | 7054 | 0 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQSTWSOLR | STEINWAY: Solar Panels | SUPPORT SERVICES IMPROVEMENTS | 400 | LQ-D122 |  |  | SOLAR PANELS | 2019 | 150 | 0 | 0 | 0 | 18 | 116 | 0 | 0 | 134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQSZ-RENO | SOUTH OZONE PARK - Branch Expansion and Renovation | ESSENTIAL RECONSTRUCTION OF FACILITIES | 400 | LQ-0122 |  |  | SOUTH OZONE PARK RENOVATION | 2019 | 12095 | 0 | 0 | 880 | 0 | 0 | 6620 | 0 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQWP-MASO | WINDSOR PARK - MASONRY | ESSENTIAL RECONSTRUCTION OF FACILITIES | 400 | LQ-0122 |  |  | WINDSOR PARK MASONRY | 2019 | 350 | 0 | 0 | 37 | 0 | 313 | 0 | 0 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQWP-TECH | WINDSOR PARK: Improvement | SUPPORT SERVICES IMPROVEMENTS | 400 | LQ-D122 |  |  | BRANCH IMPROVEMENT | 2019 | 200 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQWS-TEEN | WOODSIDE: Renovation | ESSENTIAL RECONSTRUCTION OF FACILITIES | 400 | LQ-D122 |  |  | TEEN SPACE RENOVATION | 2019 | 150 | 0 | 0 | 18 | 0 | 116 | 0 | 0 | 134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQWSTTECH | WHITESTONE: Technology Initiative | SUPPORT SERVICES IMPROVEMENTS | 400 | LQ-D122 |  |  | TECHNOLOGY INITIATIVE | 2019 | 100 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | SANDYLQLS | SANDY DAMAGES - QBPL | RECONSTRUCTION NECESSARY TO MAINTAIN FACILITIES | 400 | LQ-0122 |  |  | HURRICANE SANDY RELATED DAMAGES - QBPL | 2019 | 2963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2963 | 0 | 0 | 0 | 0 | 0 | 2963
20190425 | QUEENS | 040 | DEPARTMENT OF EDUCATION | ACEDOE602 | DOE - REMOTE BOILER FEEDWATER TREATMENT | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 413 | PU-0025 |  |  | UNIT | 2019 | 0 | 0 | 0 | 665 | 0 | 0 | 0 | 0 | 665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 040 | DEPARTMENT OF EDUCATION | ACEDOE801 | DOE - Building Management System Upgrade | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 401 | PU-0025 |  |  | BUILDING MANAGEMENT SYSTEM UPGRADE | 2019 | 0 | 0 | 0 | 1050 | 0 | 0 | 0 | 0 | 1050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 042 | CITY UNIVERSITY | ACECUN801 | CUNY - Building Automation Controls Upgrade @ QCC | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 401 | PU-0025 |  |  | QUEENSBOROUGH COMMUNITY COLLEGE - BUILDING AUTOMATION CONTROLS UPGRADE PROJECT | 2019 | 4674 | 0 | 0 | 4674 | 0 | 0 | 0 | 0 | 4674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 042 | CITY UNIVERSITY | CA034QB13 | Fire Alarm Reconstruction - Phase 3 | MISCELLANEOUS RECONSTRUCTION | 400 | HN-0206 |  |  | FIRE ALARM RECONSTRUCTION - PHASE 3 | 2019 | 1000 | 26.25 | 0 | 974 | 0 | 0 | 0 | 0 | 1000.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 042 | CITY UNIVERSITY | CA052-017 | Flushing Immigration Center | MISCELLANEOUS RECONSTRUCTION | 400 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | FLUSHING IMMIGRATION CENTER | 2019 | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 042 | CITY UNIVERSITY | CA055QB17 | CUNY ASAP Expansion | MISCELLANEOUS RECONSTRUCTION | 400 | HN-D002 HN-Q001 HN-0206 |  |  | CUNY ASAP EXPANSION | 2019 | 4650 | 0 | 4650 | 0 | 0 | 0 | 0 | 0 | 4650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 042 | CITY UNIVERSITY | CA091LG16 | M Building Boiler Plant Replacement | MISCELLANEOUS RECONSTRUCTION | 400 | HN-0206 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | M BUILDING BOILER PLANT REPLACEMENT | 2019 | 2320 | 160 | 4500 | 0 | 0 | 0 | 0 | 0 | 4660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 042 | CITY UNIVERSITY | CA091LG17 | ROOF REPLACEMENT BUILDING E | MISCELLANEOUS RECONSTRUCTION | 400 | HN-0206 HN-D005 HN-D002 |  |  | ROOF REPLACEMENT BUILDING E | 2019 | 818 | 241.85 | 2231 | 0 | 0 | 0 | 0 | 0 | 2472.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 042 | CITY UNIVERSITY | CA091LG19 | Shenker Hall Fire Alarm | MISCELLANEOUS RECONSTRUCTION | 400 | HN-0206 |  |  | SHENKER HALL FIRE ALARM | 2019 | 2250 | 0 | 0 | 2250 | 0 | 0 | 0 | 0 | 2250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 042 | CITY UNIVERSITY | CA134QB13 | BOILER RECONSTRUCTION | MISCELLANEOUS RECONSTRUCTION | 400 | HN-0206 |  |  | BOILER RECONSTRUCTION | 2019 | 210 | 0 | 210 | 0 | 0 | 0 | 0 | 0 | 210 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 042 | CITY UNIVERSITY | CL018-015 | Trial Practice Room | MISCELLANEOUS RECONSTRUCTION | 400 | HN-Q300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | TRIAL PRACTICE ROOM | 2019 | 500 | 216.33 | 14 | 0 | 1020 | 0 | 0 | 0 | 1250.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 042 | CITY UNIVERSITY | CL021-018 | Renovation of Community Room | MISCELLANEOUS RECONSTRUCTION | 411 | HN-Q300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RENOVATION OF COMMUNITY ROOM | 2019 | 650 | 0 | 0 | 0 | 0 | 650 | 0 | 0 | 650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 042 | CITY UNIVERSITY | CL023-019 | Worker Educational and Development Center | MISCELLANEOUS RECONSTRUCTION | 411 | HN-Q300 |  |  | WORKER EDUCATIONAL AND DEVELOPMENT CENTER | 2019 | 850 | 0 | 0 | 0 | 425 | 425 | 0 | 0 | 850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 042 | CITY UNIVERSITY | CL024-019 | Data Center Fire Suppression System | MISCELLANEOUS RECONSTRUCTION | 400 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NON WATERBASED FIRE SUPPRESSION | 2019 | 1100 | 0 | 0 | 0 | 0 | 1100 | 0 | 0 | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 042 | CITY UNIVERSITY | KG037-015 | Science and Resilience Institute at Jamaica Bay | MISCELLANEOUS RECONSTRUCTION | 400 | HN-0206 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | DESCRIPTION: SCIENCE AND RESILIENCE INSTITUTE AT JAMAICA BAY | 2019 | 7500 | 0 | 0 | 0 | 0 | 0 | 7500 | 0 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 042 | CITY UNIVERSITY | LG020-009 | NEW LIBRARY SPACE | MISCELLANEOUS RECONSTRUCTION | 400 402 | HN-Q004 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RENOVATION AND CONSTRUCTION FOR NEW LIBRARY SPACE | 2019 | 5000 | 7008.54 | 0 | 0 | 557 | 0 | 0 | 0 | 7565.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 042 | CITY UNIVERSITY | LG036-014 | Library Expansion and HVAC Upgrade | MISCELLANEOUS RECONSTRUCTION | 400 402 | HN-Q004 HN-D004 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | LIBRARY EXPANSION AND HVAC UPGRADE | 2019 | 1000 | 592.5 | 0 | 0 | 2407 | 0 | 0 | 0 | 2999.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 042 | CITY UNIVERSITY | LG040-016 | Center 3 Infrastr. Upgrade, Fitout | MISCELLANEOUS RECONSTRUCTION | 400 | HN-0206 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CENTER 3 INFRA. UPGRADE, 5TH & 8TH FOORS FITOUT | 2019 | 41000 | 1586.18 | 0 | 9571 | 29843 | 0 | 0 | 0 | 41000.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 042 | CITY UNIVERSITY | LG041-016 | Business and Entrepreneurial Training Center | MISCELLANEOUS RECONSTRUCTION | 402 | HN-Q006 HN-D002 HN-Q004 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BUSINESS AND ENTREPRENEURIAL TRAINING CENTER | 2019 | 3400 | 1115.1 | 0 | 750 | 5672 | 0 | 0 | 0 | 7537.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 042 | CITY UNIVERSITY | LG043-018 | Shenker Hall Lab Renovation | MISCELLANEOUS RECONSTRUCTION | 402 | HN-Q004 HN-D004 |  |  | SHENKAR HALL LAB RENOVATION | 2019 | 1500 | 0 | 796 | 0 | 4304 | 0 | 0 | 0 | 5100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 042 | CITY UNIVERSITY | LG071-019 | Student Success Center: Tutoring Hub | MISCELLANEOUS RECONSTRUCTION | 402 | HN-Q004 HN-D002 |  |  | RENOVATION TO C BLDG - CENTRALIZEDTUTORIN HUB - 5TH FLR | 2019 | 5100 | 0 | 0 | 0 | 4100 | 0 | 0 | 0 | 4100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 042 | CITY UNIVERSITY | LG072-019 | Archive Construction | MISCELLANEOUS RECONSTRUCTION | 400 | HN-D002 |  |  | ARCHIVE CONSTRUCTION | 2019 | 150 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 042 | CITY UNIVERSITY | LG073-020 | LIBRARY PHASE II CONSTRUCTION | MISCELLANEOUS RECONSTRUCTION | 402 | HN-Q004 |  |  | LIBRARY PHASE II CONSTRUCTION | 2019 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 042 | CITY UNIVERSITY | LG202-006 | Center 3 - 8th Floor and Infrastructure | MISCELLANEOUS RECONSTRUCTION | 400 402 | HN-0206 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | THIS PROJECT WILL RENOVATE 80,000 GSF OF SPACE ON THE 7TH AND 8TH FLOORS OF CENTER 3 FOR THE DEPARTMENT OF COMPUTER SYSTEMS. THE PROJECT WILL CONSTRUCT 15 CLASSROOMS, 10 COMPUTER LABS, EIGHT MULTI-PURPOSE ROOMS, FACULTY AND ADMINISTRATIVE OFFICES, AND THE ADDITION OF TWO ELEVATORS. | 2019 | 10500 | 1500 | 0 | 0 | 0 | 120 | 0 | 0 | 1620 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 042 | CITY UNIVERSITY | QB002-010 | Queensborough CC- Bathrooms/Campus Improvements | MISCELLANEOUS RECONSTRUCTION | 411 | HN-0206 HN-Q006 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | QUEENSBOROUGH CC - ART EXHIBIT SPACE BIULD-OUT | 2019 | 400 | 66 | 0 | 362 | 0 | 0 | 0 | 0 | 428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 042 | CITY UNIVERSITY | QB031-007 | Cafeteria and Central Kitchen | MISCELLANEOUS RECONSTRUCTION | 411 | HN-Q004 HN-D004 HN-D002 HN-Q001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CAFETERIA AND CENTRAL KITCHEN | 2019 | 2000 | 5995.83 | 433 | 5321 | 0 | 0 | 0 | 0 | 11749.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 042 | CITY UNIVERSITY | QB040-011 | HVAC Upgrades | MISCELLANEOUS RECONSTRUCTION | 400 | HN-0206 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | COMMUNITY CENTER HVAC | 2019 | 1600 | 1600 | 700 | 0 | 0 | 0 | 0 | 0 | 2300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 042 | CITY UNIVERSITY | QB042-012 | THEATER RENOVATIONS AND ADA UPGRADES | MISCELLANEOUS RECONSTRUCTION | 400 | HN-D002 HN-D005 HN-D004 HN-0206 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | THEATER RENOVATIONS AND ADA UPGRADES | 2019 | 750 | 4750 | 2066 | 0 | 0 | 0 | 0 | 0 | 6816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 042 | CITY UNIVERSITY | QB045-013 | Replace Three Roofs & Renovate Campus Theater | MISCELLANEOUS RECONSTRUCTION | 400 411 | HN-D005 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | REPLACE THREE ROOFS & RENOVATE CAMPUS THEATER | 2019 | 1100 | 0 | 0 | 0 | 0 | 109 | 0 | 0 | 109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 042 | CITY UNIVERSITY | QB054-016 | Refurbishment and Upgrade of Research Labs | MISCELLANEOUS RECONSTRUCTION | 400 | HN-D005 HN-D002 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | REFURBISHMENT & UPGRADE OF RESEARCH LABS | 2019 | 1500 | 157.83 | 0 | 0 | 0 | 1442 | 0 | 0 | 1599.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 042 | CITY UNIVERSITY | QB058-017 | Technology Building Roof Repair | MISCELLANEOUS RECONSTRUCTION | 400 | HN-D002 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | TECHNOLOGY BUILDING ROOF REPAIR | 2019 | 1200 | 145.99 | 0 | 0 | 0 | 1054 | 0 | 0 | 1199.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 042 | CITY UNIVERSITY | QB059-018 | Central Kitchen Upgrade | MISCELLANEOUS RECONSTRUCTION | 411 | HN-Q001 |  |  | CENTRAL KITCHEN UPGRADE | 2019 | 1500 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 042 | CITY UNIVERSITY | QB060-018 | Student Cafeteria Upgrades | MISCELLANEOUS RECONSTRUCTION | 400 | HN-D004 |  |  | STUDENT CAFETERIA UPGRADES | 2019 | 1700 | 0 | 0 | 1700 | 0 | 0 | 0 | 0 | 1700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 042 | CITY UNIVERSITY | QB061-020 | ADA Bathrooms | MISCELLANEOUS RECONSTRUCTION | 411 | HN-Q004 |  |  | ADA BATHROOMS | 2019 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 042 | CITY UNIVERSITY | QB200-006 | Upgrade Electric System | ELECTRICAL, MECHANICAL AND HVAC SYSTEM UPGRADING | 400 411 | HN-D002 HN-Q004 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | THIS PROJECT WILL PROVIDE INCREASED ELECTRICAL SERVICE TO ALL BUILDINGS ON CAMPUS BY REPLACING SWITCHBOARDS, TRANSFORMERS, WIRING, AND HIGHVOLTAGE SUPPLY TO TRANSFORMERS. NEW ELECTRICAL PANELS WILL BE PROVIDED AT VARIOUS LOCATIONS WITHIN THE BUILDINGS. THE INCREASED ELECTRICAL SERVICE IS NEEDED FOR NEW COMPUTERS THAT ARE BEING USED IN LABS, CLASSROOMS AND OFFICES FOR THE COLLEGE'S NETWORK INFRASTRUCTURE PROJECT. | 2019 | 500 | 21050 | 0 | 0 | 0 | 250 | 0 | 0 | 21300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 042 | CITY UNIVERSITY | QC004-013 | Library and Classroom Space Upgrades | MISCELLANEOUS RECONSTRUCTION | 400 407 | HN-D300 HN-Q006 HN-Q300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | LIBRARY AND CLASSROOM SPACE UPGRADES | 2019 | 1500 | 250.21 | 0 | 0 | 1754 | 0 | 0 | 0 | 2004.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 042 | CITY UNIVERSITY | QC039-011 | Louis Armstrong Visitor's Center | MISCELLANEOUS RECONSTRUCTION | 400 408 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CREATE LOUIS ARMSTRONG HOUSE MUSEUM VISITORS CENTER | 2019 | 50 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 042 | CITY UNIVERSITY | QC047-013 | Kupferberg Renovation | MISCELLANEOUS RECONSTRUCTION | 400 407 | HN-Q300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ATRIUM RENOVATION | 2019 | 467 | 0 | 0 | 0 | 0 | 0 | 227 | 0 | 227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 042 | CITY UNIVERSITY | QC054-015 | Speech & Hearing Center Upgrade Ph 2 | MISCELLANEOUS RECONSTRUCTION | 400 | HN-Q300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | SPEECH & HEARING CENTER UPGRADE PH 2 | 2019 | 1500 | 2903.92 | 96 | 0 | 0 | 0 | 0 | 0 | 2999.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 042 | CITY UNIVERSITY | QC061-016 | One Stop Service Center | MISCELLANEOUS RECONSTRUCTION | 408 | HN-Q300 HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | SERVICE CENTER CONSTRUCTION | 2019 | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 042 | CITY UNIVERSITY | QC061-017 | One Stop Center | MISCELLANEOUS RECONSTRUCTION | 400 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ONE STOP CENTER | 2019 | 1326 | 0 | 0 | 0 | 0 | 1326 | 0 | 0 | 1326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 042 | CITY UNIVERSITY | QC065-017 | Recording Studio Renovation in the Music Bldg | MISCELLANEOUS RECONSTRUCTION | 400 | HN-Q300 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | RECORDING STUDIO RENOVATION IN THE MUSIC BLDG | 2019 | 1000 | 0 | 161 | 0 | 0 | 839 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 042 | CITY UNIVERSITY | QC066-017 | Digital Film Center Construction | MISCELLANEOUS RECONSTRUCTION | 400 | HN-D300 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | DIGITAL FILM CENTER CONSTRUCTION | 2019 | 2000 | 0 | 246 | 0 | 0 | 1754 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 042 | CITY UNIVERSITY | QC069-018 | Library Phase III Upgrade | MISCELLANEOUS RECONSTRUCTION | 411 | HN-Q300 HN-D300 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | LIBRARY PHASE III UPGRADE | 2019 | 3300 | 0 | 0 | 0 | 0 | 3300 | 0 | 0 | 3300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 042 | CITY UNIVERSITY | QC070-018 | Psychology and Digital Photography Labs | MISCELLANEOUS RECONSTRUCTION | 400 | HN-D300 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | PSYCHOLOGY AND DIGITAL PHOTOGRAPHY LABS | 2019 | 1900 | 0 | 0 | 0 | 0 | 1900 | 0 | 0 | 1900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 042 | CITY UNIVERSITY | QC071-018 | Athletic Fields | MISCELLANEOUS RECONSTRUCTION | 400 | HN-D300 |  |  | QUEENS COLLEGE ATHLETIC FIELDS | 2019 | 3400 | 0 | 4900 | 0 | 0 | 0 | 0 | 0 | 4900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 042 | CITY UNIVERSITY | QC072-019 | Renovation of Rathaus Hall Arts Center | MISCELLANEOUS RECONSTRUCTION | 400 407 | HN-Q300 |  |  | RENOVATION OF RATHAUS HALL ARTS CENTER | 2019 | 3200 | 0 | 0 | 0 | 2200 | 0 | 0 | 0 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 042 | CITY UNIVERSITY | QC074-019 | Biology Core Facility Upgrade | MISCELLANEOUS RECONSTRUCTION | 400 | HN-D300 |  |  | BIOLOGY CORE FACILITY UPGRADE | 2019 | 1450 | 0 | 0 | 0 | 0 | 1450 | 0 | 0 | 1450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 042 | CITY UNIVERSITY | QC075-020 | Golden Auditorium Renovation and Upgrades | MISCELLANEOUS RECONSTRUCTION | 411 | HN-Q300 |  |  | GOLDEN AUDITORIUM RENOVATION AND UPGRADES | 2019 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 042 | CITY UNIVERSITY | YC001-010 | YORK COLLEGE - DISABLED ACCESS UPGRADE | MISCELLANEOUS RECONSTRUCTION | 400 412 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | DISABLED ACCESS UPGRADE | 2019 | 448 | 0 | 0 | 0 | 448 | 0 | 0 | 0 | 448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 042 | CITY UNIVERSITY | YC022-007 | Financial Aid Office Renovation | MISCELLANEOUS RECONSTRUCTION | 411 | HN-D300 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | FINANCIAL AID OFFICE RENOVATION | 2019 | 411 | 0 | 0 | 0 | 411 | 0 | 0 | 0 | 411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 042 | CITY UNIVERSITY | YC025-008 | SCIENCE FACILITY UPGRADES | DATA PROCESSING AND OTHER EQUIPMENT |  | HN-Q300 HN-D300 |  |  |  | 2019 | 3372 | 325.72 | 3046 | 0 | 0 | 0 | 0 | 0 | 3371.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 042 | CITY UNIVERSITY | YC027-008 | EXTERIOR BEAUTIFICATION, YORK COLLEGE | MISCELLANEOUS RECONSTRUCTION | 400 412 | HN-Q006 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | EXTERIOR BEAUTIFICATION | 2019 | 3698 | 0 | 0 | 0 | 0 | 199 | 0 | 0 | 199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 042 | CITY UNIVERSITY | YC028-008 | IMPROVEMENTS TO THE PERFORMING ARTS CENTER | MISCELLANEOUS RECONSTRUCTION |  | HN-Q300 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | IMPROVEMENTS TO THE PERFORMING ARTS CENTER | 2019 | 145 | 0 | 0 | 0 | 145 | 0 | 0 | 0 | 145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 042 | CITY UNIVERSITY | YC034-010 | UNIVERSITY HEALTH SCIENCE LAB EXPANSION | MISCELLANEOUS RECONSTRUCTION | 400 412 | HN-Q006 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | SCIENCE LAB EXPANSION | 2019 | 1500 | 887.54 | 0 | 0 | 0 | 0 | 611 | 0 | 1498.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 042 | CITY UNIVERSITY | YC035-011 | New Media Lecture Hall | MISCELLANEOUS RECONSTRUCTION | 400 412 | HN-Q300 HN-D300 HN-D004 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CONVERT LECTURE HALL TO MULTIMEDIA LECTURE HALL | 2019 | 1700 | 230.83 | 2739 | 0 | 0 | 0 | 0 | 0 | 2969.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 042 | CITY UNIVERSITY | YC043-013 | Daycare Facility Improvements | MISCELLANEOUS RECONSTRUCTION | 400 412 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | TO INCLUDE LEAP FROG ACADEMY WITHIN DAYCARE FACILITY | 2019 | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 042 | CITY UNIVERSITY | YC049-014 | Renovate/Build 3D Graphics and Printing Lab | MISCELLANEOUS RECONSTRUCTION | 400 412 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RENOVATE/BUILD 3D GRAPHICS AND PRINTING LAB | 2019 | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 042 | CITY UNIVERSITY | YC051-015 | Performing Arts Center Renovations | MISCELLANEOUS RECONSTRUCTION | 400 | HN-D300 HN-D004 HN-Q300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | PERFORMING ARTS CENTER RENOVATIONS | 2019 | 2800 | 0 | 0 | 5089 | 0 | 0 | 0 | 0 | 5089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 042 | CITY UNIVERSITY | YC052-016 | Laboratory and Classroom Upgrades | MISCELLANEOUS RECONSTRUCTION | 412 | HN-Q300 HN-D300 |  |  | LABORATORY AND CLASSROOM UPGRADES | 2019 | 1000 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 042 | CITY UNIVERSITY | YC054-017 | Greenhouse Renovation | MISCELLANEOUS RECONSTRUCTION | 400 | HN-Q300 |  |  | GREENHOUSE RENOVATION | 2019 | 640 | 0 | 0 | 0 | 640 | 0 | 0 | 0 | 640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 042 | CITY UNIVERSITY | YC055-017 | Digital Convergence Center | MISCELLANEOUS RECONSTRUCTION | 400 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | DIGITAL CONVERGENCE CENTER | 2019 | 2000 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 042 | CITY UNIVERSITY | YC056-018 | Renovation of the Performing Arts Center | MISCELLANEOUS RECONSTRUCTION | 411 | HN-Q300 |  |  | RENOVATION OF THE PERFORMING ARTS CENTER | 2019 | 2000 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 042 | CITY UNIVERSITY | YC058-018 | Upgrade York College Performing Arts Center | MISCELLANEOUS RECONSTRUCTION | 400 | HN-D300 |  |  | UPGRADE YORK COLLEGE PERFORMING ARTS CENTER | 2019 | 500 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 042 | CITY UNIVERSITY | YC059-019 | Renonvation to Track | MISCELLANEOUS RECONSTRUCTION | 411 | HN-Q300 HN-D300 |  |  | RENONVATION TO TRACK | 2019 | 1700 | 0 | 0 | 1700 | 0 | 0 | 0 | 0 | 1700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 042 | CITY UNIVERSITY | YC060-019 | Tennis Court Repavement | MISCELLANEOUS RECONSTRUCTION | 400 | HN-D300 |  |  | REPAVE TENNIS COURTS | 2019 | 400 | 0 | 0 | 400 | 0 | 0 | 0 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 042 | CITY UNIVERSITY | YC061-020 | Upgrades tomthe Performing Arts Center | MISCELLANEOUS RECONSTRUCTION | 411 | HN-Q300 |  |  |  | 2019 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 056 | POLICE DEPARTMENT | ACENYP601 | NYPD - Old Police Academy Steam Trap Replacement | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 402 | PU-0025 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NYPD - CENTRAL MOTOR REPAIR | 2019 | 158 | 0 | 0 | 144 | 0 | 0 | 0 | 0 | 144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 056 | POLICE DEPARTMENT | ACEPOL701 | NYPD - CRS STEAM TRAP REPLACEMENT | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 401 | PU-0025 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NYPD - CRS STEAM TRAP REPLACEMENT | 2019 | 135 | 0 | 0 | 135 | 0 | 0 | 0 | 0 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 056 | POLICE DEPARTMENT | PO005PRP1 | NEW PROPERTY CLERK FACILITY | POLICE FACILITIES | 400 | PO-0005 |  |  | NEW PROPERTY CLERK FACILITY | 2019 | 423644 | 0 | 0 | 0 | 109644 | 159830 | 154170 | 0 | 423644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAHH | HWY # 3 SEPTIC TANK | POLICE FACILITIES | 400 | PO-0079 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 198-15 GRAND CENTRAL QUEENS | NEW SEPTIC TANK | 2019 | 98 | 0 | 0 | 98 | 0 | 0 | 0 | 0 | 98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAHM | 101ST PCT HANDICAP RAMP | POLICE FACILITIES | 400 | PO-0079 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 16-12 MOTT AV, FAR ROCKWAY QUEENS NY | HANDICAP RAMP | 2019 | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAIF | 110TH FACADE | POLICE FACILITIES | 400 | PO-0079 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 110TH PCT | FACADE REHAB | 2019 | 259 | 0 | 0 | 259 | 0 | 0 | 0 | 0 | 259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAII | FACADE AT NYPD'S FORENSIC LABORATORY | POLICE FACILITIES | 400 | PO-0079 |  | POLICE LAB | FACADE | 2019 | 67 | 0 | 0 | 0 | 67 | 0 | 0 | 0 | 67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAIJ | 106th pct FACADE | POLICE FACILITIES | 400 | PO-0079 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 106TH PCT | FACADE | 2019 | 790 | 0 | 0 | 150 | 640 | 0 | 0 | 0 | 790 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAKB | REPLACEMENT OF GASOLINE PIPES AT HARBOR GEORGE | POLICE FACILITIES | 400 | PO-0079 |  |  | ESTIMATE | 2019 | 135 | 0 | 135 | 0 | 0 | 0 | 0 | 0 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 056 | POLICE DEPARTMENT | POD106COM | 106TH PCT - UPGRADE COMMUNITY ROOM | POLICE FACILITIES | 400 | PO-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RENOVATION | 2019 | 75 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 056 | POLICE DEPARTMENT | PO-Q106 | 106th Precinct Renovation | POLICE FACILITIES | 400 | PO-Q079 |  |  | RENOVATION | 2019 | 1000 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 056 | POLICE DEPARTMENT | PO-Q107 | 107th Precinct Renovation | POLICE FACILITIES | 400 | PO-Q079 PO-0079 |  | 107TH PCT | RENOVATION | 2019 | 1295 | 0 | 1295 | 0 | 0 | 0 | 0 | 0 | 1295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 056 | POLICE DEPARTMENT | PO-Q109 | 109th Precinct Locker Room Upgrade | POLICE FACILITIES | 400 | PO-Q079 |  |  | RECONSTRUCTION OF THE LOCKER ROOM AT THE 109TH PRECINCT | 2019 | 50 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 056 | POLICE DEPARTMENT | SANDCD08 | TRANSIT DISTRICT 23 ELECTRICAL | POLICE FACILITIES | 400 | PO-0079 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | ELECTRICAL REHABILITATION | 2019 | 854 | 0 | 86 | 0 | 0 | 0 | 0 | 0 | 86 | 0 | 768 | 0 | 0 | 0 | 0 | 0 | 768
20190425 | QUEENS | 056 | POLICE DEPARTMENT | SANDCD10 | HARBOR GEORGE | POLICE FACILITIES | 400 | PO-0079 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | HARBOR GEORGE | ELECTRICAL SYTEM REHABILITATION | 2019 | 748 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 75 | 0 | 673 | 0 | 0 | 0 | 0 | 0 | 673
20190425 | QUEENS | 057 | FIRE DEPARTMENT | ACEFDN704 | FDNY - DESIGN & INSTALLATION OF 97 KW SOLAR SYSTEMS AT EMS45 | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 401 | PU-0025 |  |  | FDNY - DESIGN & INSTALLATION OF 97 KW SOLAR PHOTOVOLTAIC SYSTEMS AT EMS45 | 2019 | 386 | 44.11 | 740 | 0 | 0 | 0 | 0 | 0 | 784.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 057 | FIRE DEPARTMENT | ACEFDN802 | FDNY - Lighting upgrades at 15 buildings at FDNY center | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 401 | PU-0025 |  |  | LIGHTING UPGRADES AT 15 BUILDINGS AT FDNY TRAINING CENTER FORT TOTTEN | 2019 | 1262 | 0 | 0 | 1291 | 0 | 0 | 0 | 0 | 1291 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 057 | FIRE DEPARTMENT | F175DE266 | DOOR REPLACEMENT - EC266 | NEW FACILITIES AND RENOVATIONS | 414 | F-0175 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | DOOR REPLACEMENT - EC266 | 2019 | 120 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 057 | FIRE DEPARTMENT | F175FMHVC | FLEET MAINTENANCE HVAC SYSTEM UPGRADE | NEW FACILITIES AND RENOVATIONS | 402 | F-0175 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES |  | FLEET MAINTENANCE HVAC SYSTEM UPGRADE | 2019 | 3321 | 356.55 | 0 | 0 | 3023 | 0 | 0 | 0 | 3379.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 057 | FIRE DEPARTMENT | F175MC266 | Multi-Component Renovations - EC266 | NEW FACILITIES AND RENOVATIONS | 414 | F-0175 |  |  | MULTI-COMPONENT RENOVATIONS - EC266 | 2019 | 6014 | 0 | 656 | 31 | 5200 | 0 | 0 | 0 | 5887 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 057 | FIRE DEPARTMENT | F175MC285 | MULTI COMPONENT RENOVATIONS - EC285 | NEW FACILITIES AND RENOVATIONS | 410 | F-0175 | PROJECT DELAYED PENDING APPROVAL OF NECESSARY PERMITS |  | MULTI COMPONENT RENOVATIONS - EC285 | 2019 | 4425 | 5307.61 | 407 | 0 | 0 | 0 | 0 | 0 | 5714.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 057 | FIRE DEPARTMENT | F175MC304 | Multi-Component Renovations - EC304 | NEW FACILITIES AND RENOVATIONS | 413 | F-0175 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | MULTI-COMPONENT RENOVATIONS - EC304 | 2019 | 4556 | 0 | 463 | 0 | 0 | 4000 | 0 | 0 | 4463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 057 | FIRE DEPARTMENT | F175MC307 | Multi-Component Renovations - EC307 | NEW FACILITIES AND RENOVATIONS | 403 | F-0175 |  |  | MULTI-COMPONENT RENOVATIONS - EC307 | 2019 | 7535 | 0 | 654 | 0 | 6750 | 0 | 0 | 0 | 7404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 057 | FIRE DEPARTMENT | F175RFS45 | ROOF REPLACEMENT - EMS45 | NEW FACILITIES AND RENOVATIONS | 402 | F-0175 |  |  | ROOF REPLACEMENT - EMS45 | 2019 | 660 | 599.9 | 23 | 37 | 0 | 0 | 0 | 0 | 659.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 057 | FIRE DEPARTMENT | F175SOCVE | SOC Laundry HVAC Work | NEW FACILITIES AND RENOVATIONS | 404 | F-0175 |  |  | SPECIAL OPERATION COMMAND (SOC) LAUNDRY HVAC WORK | 2019 | 143 | 0 | 137 | 6 | 0 | 0 | 0 | 0 | 143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 057 | FIRE DEPARTMENT | F175WN266 | WINDOW REPLACEMENT - EC266 | NEW FACILITIES AND RENOVATIONS | 414 | F-0175 |  |  | WINDOW REPLACEMENT - EC266 | 2019 | 480 | 0 | 0 | 400 | 0 | 0 | 0 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 057 | FIRE DEPARTMENT | F175WN329 | WINDOW REPLACEMENT - EC329 | NEW FACILITIES AND RENOVATIONS | 414 | F-0175 |  |  | WINDOW REPLACEMENT - EC329 | 2019 | 480 | 0 | 0 | 400 | 0 | 0 | 0 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 057 | FIRE DEPARTMENT | F175WP301 | Waterproofing - EC301 | NEW FACILITIES AND RENOVATIONS | 412 | F-0175 |  |  | WATERPROOFING - EC301 | 2019 | 4122 | 0 | 435 | 0 | 3600 | 0 | 0 | 0 | 4035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 057 | FIRE DEPARTMENT | F175WP303 | Waterproofing - EC303 | NEW FACILITIES AND RENOVATIONS | 412 | F-0175 |  |  | WATERPROOFING - EC303 | 2019 | 3041 | 0 | 326 | 0 | 2650 | 0 | 0 | 0 | 2976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 057 | FIRE DEPARTMENT | F204FTREN | Fort Totten Infrastructure and EMS Expansion | NEW FACILITIES AND RENOVATIONS | 400 | F-0204 |  |  | FORT TOTTEN INFRASTRUCTURE AND EMS EXPANSION | 2019 | 0 | 0 | 0 | 8143 | 50118 | 0 | 0 | 0 | 58261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 057 | FIRE DEPARTMENT | F204-PIER | RANDALLS ISLAND PIER | NEW FACILITIES AND RENOVATIONS | 400 | F-0204 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | RANDALLS ISLAND PIER | 2019 | 4702 | 8728.29 | 775 | 0 | 0 | 0 | 0 | 0 | 9503.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 057 | FIRE DEPARTMENT | FD175D251 | APPARATUS DOOR - EC251 | NEW FACILITIES AND RENOVATIONS | 413 | F-D175 |  |  | APPARATUS DOOR - EC251 | 2019 | 75 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 057 | FIRE DEPARTMENT | FD175D262 | Door Replacement - EC262 | NEW FACILITIES AND RENOVATIONS | 401 | F-D175 |  |  | DOOR REPLACEMENT - EC262 | 2019 | 150 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 057 | FIRE DEPARTMENT | FD175D287 | DOOR REPLACEMENT - EC287 | NEW FACILITIES AND RENOVATIONS | 404 | F-D175 |  |  | DOOR REPLACEMENT - EC287 | 2019 | 150 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 057 | FIRE DEPARTMENT | FD175D291 | Door Replacement - EC291 | NEW FACILITIES AND RENOVATIONS | 405 | F-D175 |  |  | DOOR REPLACEMENT - EC291 | 2019 | 150 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 057 | FIRE DEPARTMENT | FD175D302 | Door Replacement - EC302 | NEW FACILITIES AND RENOVATIONS | 412 | F-D175 |  |  | DOOR REPLACEMENT - EC302 | 2019 | 75 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 057 | FIRE DEPARTMENT | FD175D303 | Door Replacement - EC303 | NEW FACILITIES AND RENOVATIONS | 412 | F-D175 |  |  | DOOR REPLACEMENT - EC303 | 2019 | 75 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 057 | FIRE DEPARTMENT | FD175D317 | Door Replacement - EC317 | NEW FACILITIES AND RENOVATIONS | 412 | F-D175 |  |  | DOOR REPLACEMENT - EC317 | 2019 | 75 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 057 | FIRE DEPARTMENT | FD175D319 | Door Replacement - EC319 | NEW FACILITIES AND RENOVATIONS | 405 | F-D175 |  |  | DOOR REPLACEMENT - EC319 | 2019 | 75 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 057 | FIRE DEPARTMENT | FD175D324 | Door Replacement - EC324 | NEW FACILITIES AND RENOVATIONS | 404 | F-D175 |  |  | DOOR REPLACEMENT - EC324 | 2019 | 150 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 057 | FIRE DEPARTMENT | FD175DS52 | Door Replacement - EMS 52 | NEW FACILITIES AND RENOVATIONS | 407 | F-D175 |  |  | DOOR REPLACEMENT - EMS 52 | 2019 | 75 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 057 | FIRE DEPARTMENT | FD175G289 | Generator - EC289 | NEW FACILITIES AND RENOVATIONS | 404 | F-D175 F-0175 |  |  | GENERATOR - EC289 | 2019 | 771 | 0 | 754 | 0 | 0 | 0 | 0 | 0 | 754 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 057 | FIRE DEPARTMENT | FQ175E329 | kitchen renovation-e-c329 | NEW FACILITIES AND RENOVATIONS | 414 | F-Q175 F-0175 | PROJECT DELAYED DUE TO SCHEDULING OF UTILITY WORK |  | KITCHEN RENOVATION-E-C329 402 BEACH 169TH STREET, QUEENS NY 11694 | 2019 | 600 | 659.84 | 51 | 0 | 0 | 0 | 0 | 0 | 710.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 057 | FIRE DEPARTMENT | FQ175G260 | Generator - EC260 | NEW FACILITIES AND RENOVATIONS |  | F-Q175 |  |  | INSTALLATION OF NEW BUILDING GENERATOR AT EC260. | 2019 | 0 | 0 | 0 | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 057 | FIRE DEPARTMENT | FQ175K307 | KITCHEN RENOVATION - EC307 | NEW FACILITIES AND RENOVATIONS | 403 | F-Q175 |  |  | KITCHEN RENOVATION - EC307 | 2019 | 1200 | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 057 | FIRE DEPARTMENT | FQ175W275 | Window Replacement EC275 | NEW FACILITIES AND RENOVATIONS | 412 | F-Q175 |  |  | WINDOW REPLACEMENT AT EC 275 | 2019 | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 071 | DEPT OF HOMELESS SERVICES | ACEDHS801 | DHS - Gas fired condensing hot water systems | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 401 | PU-0025 |  |  | GAS FIRED CONDENSING HOT WATER SYSTEMS FOR DOMESTIC HOT WATER (BRIARWOOD) | 2019 | 0 | 0 | 115 | 0 | 0 | 0 | 0 | 0 | 115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 071 | DEPT OF HOMELESS SERVICES | HH112BARS | Shelter at 21-10 Borden Avenue, 11110 - Roof/Skylight Replac | SHELTERS FOR HOMELESS INDIVIDUALS | 402 | HH-0112 |  |  | SHELTER AT 21-10 BORDEN AVENUE, 11110 - ROOF/SKYLIGHT REPLACEMENT | 2019 | 6650 | 0 | 500 | 750 | 5250 | 0 | 0 | 0 | 6500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 071 | DEPT OF HOMELESS SERVICES | HH112BDKT | BORDEN - NEW BATHROOMS | SHELTERS FOR HOMELESS INDIVIDUALS | 402 | HH-0112 |  |  | BORDEN - CREATE NEW BATHROOMS TO BE CODE COMPLIANT | 2019 | 613 | 165 | 448 | 0 | 0 | 0 | 0 | 0 | 613 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 071 | DEPT OF HOMELESS SERVICES | HH112BOFW | Borden Avenue Flood Mitigation | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 |  |  | FLOOD MITIGATION | 2019 | 2479 | 0 | 170 | 450 | 0 | 0 | 0 | 0 | 620 | 0 | 1859 | 0 | 0 | 0 | 0 | 0 | 1859
20190425 | QUEENS | 071 | DEPT OF HOMELESS SERVICES | HH115BWRF | BRIARWOOD FAMILY RESIDENCE - ROOF AND FACADE UPGRADE | SHELTERS FOR HOMELESS FAMILIES | 408 | HH-0115 |  |  | BRIARWOOD FAMILY RESIDENCE - ROOF AND FACADE UPGRADE | 2019 | 1030 | 0 | 83 | 0 | 947 | 0 | 0 | 0 | 1030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 071 | DEPT OF HOMELESS SERVICES | HH115JAEX | JAMAICA FAMILY EXTERIOR | SHELTERS FOR HOMELESS FAMILIES | 412 | HH-0115 |  |  | JAMAICA FAMILY EXTERIOR | 2019 | 3250 | 250 | 0 | 1000 | 2000 | 0 | 0 | 0 | 3250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 071 | DEPT OF HOMELESS SERVICES | HH115SINT | SPRINGFIELD BLD FACADE RECONSTRUCTION | SHELTERS FOR HOMELESS FAMILIES | 401 | HH-0112 |  |  | FACADE RECONSTRUCTION | 2019 | 0 | 0 | 0 | 0 | 0 | 48 | 0 | 528 | 576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 071 | DEPT OF HOMELESS SERVICES | HH115SMEP | SPRINGFIELD BLD BOILER RECONSTRUCTION | SHELTERS FOR HOMELESS FAMILIES | 401 | HH-0112 |  |  | BOILER RECONST | 2019 | 0 | 0 | 35 | 0 | 385 | 0 | 0 | 0 | 420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 072 | DEPARTMENT OF CORRECTION | C101-SEC | PERIMETER SECURITY & CAMERA REPLACEMENT | BUILDING SYSTEMS AND INFRASTRUCTURE | 400 | C-0101 |  |  |  | 2019 | 1500 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 072 | DEPARTMENT OF CORRECTION | C75HMDREL | Relocate HMD to Bulova Building | SUPPORT SPACE | 400 403 | C-0075 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | NYC WANTS TO USE THE SPACE CURRENTLY UTILIZED BY HMD FOR NYCPD. HMD WILL BE RELOCATED TO BULOVA BUILDING. | 2019 | 250 | 17.13 | 0 | 233 | 0 | 0 | 0 | 0 | 250.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 072 | DEPARTMENT OF CORRECTION | C75HOTWTR | HOT WATER RIKERS ISLAND | BUILDING SYSTEMS AND INFRASTRUCTURE | 401 | C-0075 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | ARDC & GMDC AT R.I.. NY | REPLACEMENT OF PERIMETER HOT WATER HEATING SYSTEMS AT ARDC & GMDC | 2019 | 2300 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 072 | DEPARTMENT OF CORRECTION | C75SEWR | RECONSTRUCTION OF RI SEWER LINES | BUILDING SYSTEMS AND INFRASTRUCTURE | 400 401 | C-0075 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | RIKER ISLAND SEWER LINES HAVE DETERIORATED AND NEED TO BE RECONSTRUCTED. | 2019 | 1550 | 1581.49 | 389 | 0 | 7396 | 0 | 0 | 0 | 9366.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 072 | DEPARTMENT OF CORRECTION | E16-0017 | DOC - Rose M Singer Center-Comprehensive HVAC Energy Upgrade | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 403 | PU-0025 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | COMPREHENSIVE HVAC ENERGY EFFICIENCY UPGRADE | 2019 | 7283 | 451.37 | 0 | 2978 | 0 | 0 | 0 | 0 | 3429.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 096 | HUMAN RESOURCES ADMINISTRATION | HR25QCRT | Renovation of 151-20 Jamaica Ave 4th floor | SOCIAL SERVICES BUILDINGS |  | HR-0025 |  |  |  | 2019 | 0 | 0 | 0 | 653 | 0 | 0 | 0 | 0 | 653 | 0 | 0 | 1268 | 0 | 0 | 0 | 0 | 1268
20190425 | QUEENS | 096 | HUMAN RESOURCES ADMINISTRATION | HRCNSJMS2 | South Jamaica MSC renovation. | SOCIAL SERVICES BUILDINGS |  | HR-D002 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RENOVATION OF SOUTH JAMAICA MSC | 2019 | 190 | 0 | 190 | 0 | 0 | 0 | 0 | 0 | 190 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 096 | HUMAN RESOURCES ADMINISTRATION | HRCNSJMSC | South Jamaica MSC renovation | SOCIAL SERVICES BUILDINGS |  | HR-D002 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RENOVATION | 2019 | 250 | 0 | 298 | 0 | 0 | 0 | 0 | 0 | 298 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 125 | DEPARTMENT FOR THE AGING | AGWOODRE1 | Woodside houses new gym for the elderly | DEPARTMENT FOR THE AGING BUILDING RECONSTRUCTION | 401 | AG-D001 |  |  | WOODSIDE HOUSE NEW GYM FOR THE ELDERLY | 2019 | 65 | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV040BTH1 | FTH - Flushing Town Hall - Bathroom Renovations HLD | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | PV-Q040 |  |  | RENVATIONS TO BATHROOM IN FTH. | 2019 | 1022 | 0 | 0 | 800 | 0 | 0 | 222 | 0 | 1022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV040HVAC | FTH - Flushing Town Hall HVAC System Replacement | ESSENTIAL RECONSTRUCTION OF FACILITIES | 407 | PV-Q040 PV-D040 PV-0040 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | FLUSHING TOWN HALL - ROOFTOP AIR CONDITIONING UNIT: REPLACEMENT ROOFTOP AIR CONDITIONING UNITS: ONE (1) LARGER 50-TON UNIT, AND TWO (2) SMALLER 3-TON UNITS. | 2019 | 809 | 0 | 0 | 96 | 0 | 811 | 0 | 0 | 907 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV050CYLT | MMI - Courtyard Lighting | ESSENTIAL RECONSTRUCTION OF FACILITIES | 401 | PV-D050 PV-Q050 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | INSTALLATION OF NEW LIGHTING IN COURTYARD NEEDED FOR SPECIAL EVENTS AND EMERGENCIES. | 2019 | 750 | 0 | 0 | 72 | 0 | 885 | 0 | 0 | 957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV272KIDS | QBG - Kids Culture Garden Exhibit | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | PV-Q272 PV-D272 |  | 43-5- MAIN STREET FLUSHING QUEENS NY | KIDS CULTURE GARDEN PLAY EXHIBIT | 2019 | 5133 | 0 | 0 | 750 | 0 | 0 | 4383 | 0 | 5133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV274-AH2 | NYHOS - New York Hall of Science - Air Handlers Replacement | ESSENTIAL RECONSTRUCTION OF FACILITIES | 407 | PV-0274 |  |  | AIR HANDLERS | 2019 | 4500 | 0 | 0 | 0 | 0 | 3950 | 0 | 0 | 3950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV274ELV2 | NYHOS - New York Hall of Science - Elevator | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | PV-Q274 |  |  | NYHOS - NEW YORK HALL OF SCIENCE - ELEVATOR | 2019 | 0 | 0 | 0 | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV274PERI | NYHOS - New York Hall of Science, Perimeter Safety | ESSENTIAL RECONSTRUCTION OF FACILITIES | 407 | PV-D274 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NEW PERIMETER FENCE AND SECURITY CAMERAS. | 2019 | 1186 | 0 | 0 | 0 | 0 | 1186 | 0 | 0 | 1186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV466BOIL | QTIP - Queens Theater in the Park Boiler | ESSENTIAL RECONSTRUCTION OF FACILITIES | 400 407 | PV-Q466 PV-0466 |  |  | CONSTRUCTION | 2019 | 0 | 0 | 0 | 815 | 107 | 0 | 892 | 0 | 1814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV466QTP | QTIP - Queens Theater in the Park Next Phase | ESSENTIAL RECONSTRUCTION OF FACILITIES | 400 407 | PV-Q466 PV-D466 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RENOVATION | 2019 | 2846 | 0 | 0 | 0 | 250 | 2584 | 0 | 0 | 2834 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501ATTC | PS1 - Attic Renovation for Studios | ESSENTIAL RECONSTRUCTION OF FACILITIES | 401 | PV-Q501 PV-D501 PV-0501 PV-D467 |  |  | RENOVATION OF PS1'S ATTIC SPACE AND BASEMENT TO CREATE ARTISTS STUDIOS AND EDUCATION SPACE. SCOPE INCLUDES ADA UPGRADES ELEVATOR. | 2019 | 2230 | 0 | 0 | 0 | 445 | 0 | 3436 | 0 | 3881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501ELEV | PS1 - Elevator Renovation | ESSENTIAL RECONSTRUCTION OF FACILITIES | 401 | PV-0501 |  |  | CONSTRUCTION | 2019 | 563 | 0 | 0 | 0 | 54 | 446 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501-PS1 | PS1 - Acquisition for studio and gallery space | ESSENTIAL RECONSTRUCTION OF FACILITIES | 402 | PV-D501 PV-Q501 PV-0501 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES |  | ACQUISITION | 2019 | 4000 | 0 | 0 | 0 | 0 | 5000 | 0 | 2500 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501ROOF | PS1 - Renovation of PS1 roof areas | ESSENTIAL RECONSTRUCTION OF FACILITIES | 402 | PV-D501 PV-Q501 PV-0501 |  |  | RENOVATION OF PS1 ROOF AREAS, SUBSEQUENT PHASE OF PS1'S ROOF ACCESS AND ATTIC PROJECT PV501ATTC | 2019 | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 0 | 3500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV502ELEV | JCAL - Elevator Reconstruction/Modernization Section | ESSENTIAL RECONSTRUCTION OF FACILITIES | 412 | PV-Q502 PV-D502 PV-0502 |  |  | ELEVATOR UPGRADES | 2019 | 3217 | 0 | 0 | 0 | 445 | 0 | 2415 | 0 | 2860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | BEACH20 | Beach 20th St. Plaza Improvements | COMMUNITY DEVELOPMENT | 400 414 | ED-Q384 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BEACH 20TH ST. PLAZA IMPROVEMENTS | 2019 | 811 | 1185.65 | 0 | 0 | 41 | 0 | 0 | 0 | 1226.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | COLPJFK | JFK Site A (COLLEGE POINT Relocation) | PORT DEVELOPMENT | 400 407 | PO-0079 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | JFK SITE A (COLLEGE POINT RELOCATION) | 2019 | 19002 | 26894.65 | 280 | 0 | 0 | 371 | 0 | 0 | 27545.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | COLUMBPL | Columbus Plaza | NEIGHBORHOOD REVITALIZATION | 400 | ED-0075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | COLUMBUS PLAZA | 2019 | 1000 | 0 | 0 | 0 | 0 | 1009 | 0 | 0 | 1009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | CPCDRAIN | College Point - Drainage Rehab | MISCELLANEOUS | 400 407 | ED-0075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | COLLEGE POINT - DRAINAGE REHAB | 2019 | 400 | 125 | 0 | 275 | 0 | 0 | 0 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | ECODOCKHC | ECO-DOCK AT HALLETS COVE | MISCELLANEOUS | 400 | ED-D401 ED-0409 P-Q245 |  |  | ECODOCKHC | 2019 | 1000 | 450.02 | 1550 | 3000 | 0 | 0 | 0 | 0 | 5000.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | FABARGEHP | FA Barge Replacement - Hunters Point South 5307 | MISCELLANEOUS | 402 | FA-0027 ED-0409 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | FA BARGE REPLACEMENT - HUNTS POINT 5307 | 2019 | 2500 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 179 | 2098 | 1723 | 0 | 0 | 0 | 4000
20190425 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | GRANDAVEE | Grand Ave. Commercial Revitalization | COMMERCIAL DEVELOPMENT | 405 | ED-D384 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | GRAND AVE. COMMERCIAL REVITALZATION | 2019 | 500 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQ1186 | ROCKAWAY BEACH BULKHEAD | PRIMARY STREET RECONSTRUCTION | 400 414 | ED-0075 HW-0001Q | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | ROCKAWAY BEACH BULKHEAD BETWEEN RIIS PARK & BEACH 116TH ST | ROCKAWAY BEACH BULKHEAD BETWEEN RIIS PARK & BEACH 116TH ST | 2019 | 21140 | 25118.2 | 0 | 308 | 0 | 0 | 0 | 1015 | 26441.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQ1191 | Vernon Boulevard Bulkhead Replacement | PRIMARY STREET RECONSTRUCTION | 400 | HW-0001Q RE-0025 |  | VERNON BOULEVARD BULKHEAD REPLACEMENT | VERNON BOULEVARD BULKHEAD REPLACEMENT | 2019 | 1750 | 698 | 900 | 0 | 3411 | 0 | 0 | 0 | 5009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQ187A | 132nd St Construction - 20th Ave to Linden Place | PRIMARY STREET RECONSTRUCTION | 407 | ED-0075 HW-0001Q HW-0001 HW-1674 SE-0200Q | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CONSTRUCTION OF 132ND STREET BETWEEN 20TH AVE AND LINDEN PLACE IN THECOLLEGE POINT CORPORATE PARK. PROJECT IS ALSO KNOWN AS THE LINDEN PLACE EXTENSION | 2019 | 7000 | 9823.94 | 5952 | 23508 | 0 | 0 | 0 | 0 | 39283.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQ662D | Springfield Gardens Residential Area, Reconstruction | PRIMARY STREET RECONSTRUCTION | 413 | WM-0006 WM-0001 HW-0662 HW-0792 SE-0727 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | SPRINGFIELD GARDENS RESIDENTIAL AREA, RECONSTRUCTION SITE D. | SPRINGFIELD GARDENS RESIDENTIAL AREA, RECONSTRUCTION SITE D. | 2019 | 23020 | 4740.88 | 962 | 5148 | 0 | 0 | 0 | 0 | 10850.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQ662D1 | Springfield Gardens Residential Area, Reconstruction | PRIMARY STREET RECONSTRUCTION | 413 | WM-0001 SE-0005 EP-0007 HW-0C01Q HW-0662 HW-0792 HW-0200 TF-0002 HW-0001Q | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | SPRINGFIELD GARDENS PHASE D- CONSTRUCTION | 2019 | 66457 | 64892.24 | 25 | 1626 | 0 | 0 | 0 | 0 | 66543.24 | 4087.03 | 0 | 1130 | 0 | 0 | 0 | 0 | 5217.03
20190425 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQ996 | Harper Street Yard Bulkhead Renovation | FACILITY RECONSTRUCTION | 400 407 | HW-0003 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | HARPER STREET YARD BULKHEAD RENOVATION | HARPER STREET YARD BULKHEAD RENOVATION | 2019 | 8000 | 6526.68 | 0 | 0 | 0 | 0 | 0 | 3474 | 10000.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQWILLET | Willets Point - Van Wyck Improvements | PRIMARY STREET RECONSTRUCTION | 400 407 | HW-0001Q | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | WILLETS POINT - VAN WYCK IMPROVEMENTS | 2019 | 61000 | 0 | 0 | 0 | 0 | 0 | 0 | 61000 | 61000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | IDF-GMDC | GMDC Ozone Park Factory Acquisition | INDUSTRIAL DEVELOPMENT | 400 | ED-0404 |  |  | BUILDING ACQUISITION | 2019 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | JAMAAECT | GDJC - Atlantic Avenue Extension - Construction | COMMERCIAL DEVELOPMENT | 400 | ED-0075 ED-Q384 HW-0001Q | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | GDJC - ATLANTIC AVENUE EXTENSION - CONSTRUCTION INCLUDING PM AND CM FEES. | 2019 | 11318 | 6517.56 | 1845 | 483 | 0 | 1000 | 0 | 2 | 9847.56 | 5576.29 | 1 | 0 | 0 | 0 | 0 | 0 | 5577.29
20190425 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | JAMCMFEE | GDJC AAE and Station Plaza CM | COMMERCIAL DEVELOPMENT | 400 412 | ED-0075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | GJDC AAE AND STATION PLAZA CM | 2019 | 6200 | 158.13 | 199 | 0 | 0 | 0 | 0 | 0 | 357.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | JAMSTPLZ | Station Plaza Design & Construction | MISCELLANEOUS | 400 | ED-0075 HW-0001Q |  |  | STATION PLAZA DESIGN & CONSTRUCTION | 2019 | 27212 | 0 | 0 | 0 | 12871 | 0 | 0 | 504 | 13375 | 0 | 300 | 0 | 9431 | 0 | 0 | 0 | 9731
20190425 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | PV050ELMO | MMI - New Gallery for Henson Collection | ESSENTIAL RECONSTRUCTION OF FACILITIES | 401 | PV-0050 PV-Q050 PV-D050 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 36-01 35TH AVENUE | THIS PROJECT WILL CREATE A NEW 2200 SF GALLERY IN THE MUSEUM DEDICATED TO THE WORK, CAREER, AND CREATIVE PROCESS OF JIM HENSON, CREATOR OF THE MUPPETS. | 2019 | 4250 | 3519.41 | 0 | 0 | 0 | 0 | 1006 | 0 | 4525.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | PWD99AERO | FA - College of Aeronautics | MISCELLANEOUS CONSTRUCTION | 403 | ED-0075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NEW LIBRARY, AUDITORIUM, CAFETERIA AND STUDENT CENTER | 2019 | 135 | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | QNSPLGA | Queens Plaza Garage | COMMERCIAL DEVELOPMENT | 400 401 402 | ED-0075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | QUEENS PLAZA GARAGE | 2019 | 30270 | 2435.2 | 0 | 84 | 0 | 0 | 0 | 0 | 2519.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | QUEENSC | Queens Commercial Corridors | COMMERCIAL DEVELOPMENT | 400 | ED-D075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | QUEENS COMMERCIAL CORRIDORS - PHASE I | QUEENS COMMERCIAL CORRIDORS - PHASE I | 2019 | 1378 | 172 | 0 | 0 | 300 | 0 | 0 | 0 | 472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | QUEENSCAS | QUEENS COMMERCIAL CORRIDOR AT ASTORIA | MISCELLANEOUS | 400 | ED-Q384 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | QUEENS COMMERCIAL CORRIDOR AT ASTORIA--GREENSPACE AROUND THE CLOCK BETWEEN 30TH AVENUE AND 31ST AVENUE, AND AT THE MUNICIPAL LOT BETWEEN BROADWAY AND 31ST AVENUE. | 2019 | 200 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | QUEENSCRK | QUEENS COMMERCIAL CORRIDOR AT ROCKAWAY | MISCELLANEOUS | 400 | ED-Q384 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | QUEENS COMMERCIAL CORRIDOR AT ROCKAWAY--STREETSCAPE IMPROVEMENTS, INCLUDING FENCING AND A WAYFINDING KIOSK AT THE ENTRANCE TO THE PARK. (BEACH 116TH STREET, FLIGHT 587 PARK MEMORIAL) | 2019 | 200 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | QUEENSCSA | QUEENS COMMERCIAL CORRIDOR AT ST. ALBANS | MISCELLANEOUS | 400 | ED-Q384 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | QUEENS COMMERCIAL CORRIDOR AT ST. ALBANS--TREES AND PLANTINGS AT THE LOT ON 99TH STREET AND FARMERS BLVD., AND A GREEN STREET AT THE INTERSECTION OF MURDOCH AND FARMERS BLVD. | 2019 | 100 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | QWESTAC | Queens West Acquisition | COMMERCIAL DEVELOPMENT | 402 | HD-0211 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ACQUISITION OF QUEENS WEST/ HUNTER'S POINT SOUTH BY EDC FROM THE PORTAUTHORITY. INCLUDES ACQUISITION AND CLOSING COSTS FOR BLOCK 6, LOTS 2,4; BLOCK 5, LOT 1; BLOCK 1, LOT 1; BLOCK 1, LOT 10. | 2019 | 101286 | 887.88 | 398 | 0 | 0 | 0 | 0 | 0 | 1285.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | QWESTB | Queens West/Hunter's Point South | COMMERCIAL DEVELOPMENT | 402 | P-D019 HD-0211 SE-0002Q | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | QUEEN'S WEST/HUNTER'S POINT SOUTH | 2019 | 86494 | 52123.62 | 0 | 95 | 0 | 0 | 0 | 9249 | 61467.62 | 1552.53 | 0 | 0 | 0 | 0 | 0 | 0 | 1552.53
20190425 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | QWESTC | Hunters Point South Phase II | MISCELLANEOUS | 400 | ED-0075 HD-0211 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | HUNTERS POINT SOUTH PHASE II | 2019 | 99000 | 88488.46 | 3636 | 6237 | 0 | 7875 | 0 | 0 | 106236.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | ROCKBLVD | FA - Rockaway BLVD | NEIGHBORHOOD REVITALIZATION | 400 410 412 413 | ED-0075 ED-D384 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ROCKAWAY BLVD | 2019 | 1000 | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | ROCKBULK | Rockaway Park Bulkhead Rehabilitation | WATERFRONT DEVELOPMENT | 400 414 | ED-0409 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BULKHEAD REHAB | 2019 | 800 | 6577.65 | 0 | 0 | 0 | 573 | 0 | 0 | 7150.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | ROCKINFRA | Rockaways Infrastructure Improvements | NEIGHBORHOOD REVITALIZATION | 400 | ED-0384 |  |  | ROCKAWAYS INFRASTRUCTURE IMPROVEMENTS | 2019 | 91000 | 0 | 0 | 0 | 16250 | 33000 | 9000 | 20750 | 79000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | ROCKOUT | Rockaway Park, Outfall Improvements | MISCELLANEOUS | 400 414 | SE-0200Q | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ROCKAWAY PARK, OUTFALL IMPROVEMENTS | 2019 | 840 | 3728.42 | 227 | 0 | 0 | 0 | 0 | 0 | 3955.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDRLHPS | FA Resiliency - Land Hardening Hunters Point South | MISCELLANEOUS | 402 | FA-0027 |  |  | FA RESILIENCY - LAND HARDENING HUNTS POINTS | 2019 | 1000 | 0 | 36 | 214 | 0 | 0 | 0 | 0 | 250 | 0 | 108 | 642 | 0 | 0 | 0 | 0 | 750
20190425 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | SSFERRY | South Shore Ferry Site Acquisition | WATERFRONT DEVELOPMENT | 400 | ED-D075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | SOUTH SHORE FERRY SITE ACQUISITION | 2019 | 1250 | 0 | 0 | 0 | 1750 | 0 | 0 | 0 | 1750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | SSYARDS | Sunnyside Yards | MISCELLANEOUS | 400 | ED-0075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | SUNNYSIDE YARDS | 2019 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 55000 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | SUNNYARCH | Sunnyside Arch Restoration | NEIGHBORHOOD REVITALIZATION | 402 | ED-Q384 ED-D075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | SUNNYSIDE ARCH RESTORATION | 2019 | 500 | 543.32 | 0 | 136 | 0 | 0 | 0 | 0 | 679.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | WILLETDEM | Willets Point Above Grade Demolition | MISCELLANEOUS | 400 | ED-0075 |  |  | WILLETS POINT ABOVE GRADE DEMOLITION | 2019 | 23425 | 8429.08 | 0 | 0 | 0 | 7198 | 7798 | 0 | 23425.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | WILLETINF | Willets Point Redevelopment Infrastructure | COMMERCIAL DEVELOPMENT | 400 407 | SE-0200Q ED-0075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | WILLETS POINT INFRASTRUCTURE | 2019 | 166402 | 60122.36 | 1891 | 3000 | 3849 | 0 | 0 | 0 | 68862.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | WILLETRMP | Willets Point Ramps | MISCELLANEOUS | 400 407 | ED-0075 |  |  | WILLETS POINT RAMPS | 2019 | 29000 | 0 | 0 | 1000 | 100 | 100 | 100 | 27700 | 29000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | WILLETS | Willets Point Redevelopment | COMMERCIAL DEVELOPMENT | 400 407 | ED-0075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | WILLETS POINT REDEVELOPMENT | 2019 | 394220 | 170824.09 | 0 | 500 | 502 | 0 | 0 | 0 | 171826.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | WILLETSEN | Willets Point Environmental | COMMERCIAL DEVELOPMENT | 400 407 | ED-0075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | WILLETS POINT ENVIRONMENTAL | 2019 | 6000 | 6154.48 | 0 | 0 | 0 | 0 | 0 | 1804 | 7958.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | WILLETURA | FA - Willets Point Urban Renewal Area- Subgrade Improvements | MISCELLANEOUS | 400 | ED-0075 |  |  | FA - WILLETS POINT URBAN RENEWAL AREA- SUBGRADE IMPROVEMENTS | 2019 | 93950 | 0 | 0 | 0 | 0 | 58525 | 0 | 12000 | 70525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | FARMBLVD1 | Farmer's Boulevard Community Development Corp. | MISCELLANEOUS | 400 412 413 | ED-Q384 |  |  | WINDOW REPLACEMENT | 2019 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM01ASCC | ASTORIA HOUSES - COMMUNITY CENTER UPGRADE | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 401 | HA-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | SENIOR CITIZEN CENTER | 2019 | 500 | 1198.67 | 201 | 0 | 0 | 0 | 0 | 0 | 1399.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM15QNGR | QUEENSBRIDGE NORTH PLAY AREA UPGRADE | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 401 | HA-D001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | PLAY AREA UPGRADE | 2019 | 450 | 286.11 | 164 | 0 | 0 | 0 | 0 | 0 | 450.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM15RFGR | REDFERN COMMUNITY CENTER PLAYGROUND | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 414 | HA-D001 |  |  | UPGRADE COMMUNITY CENTER PLAYGROUND | 2019 | 150 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM15SJBC | SOUTH JAMAICA HOUSES BASKETBALL COURT UPGRADES | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 412 | HA-D001 |  |  | UPGRADE BASKETBALL COURTS | 2019 | 50 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM16CMPL | CARLTON MANOR PLAYGROUND RENOVATIONS BASKETBALL COURTS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 414 | HA-D001 |  |  | PLAYGROUND RENOVATIONS, INCLUDING BASKETBALL COURTS | 2019 | 250 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM16LVSC | LEAVITT STREET-34TH AVENUE SECURITY CAMERAS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 407 | HA-D001 |  |  | LEAVITT STREET-34TH AVENUE SECURITY CAMERAS | 2019 | 50 | 273.19 | 77 | 0 | 0 | 0 | 0 | 0 | 350.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM17AHPL | ASTORIA HOUSES PLAYGROUND UPGRADE | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 400 | HA-Q001 |  |  | ASTORIA HOUSES PLAYGROUND UPGRADE | 2019 | 350 | 0 | 350 | 0 | 0 | 0 | 0 | 0 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM17BPSC | BAISLEY PARK INSTALLATION OF SECURITY CAMERAS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 400 | HA-Q001 |  |  | BAISLEY PARK HOUSES INSTALLATION OF SECURITY CAMERAS | 2019 | 500 | 453.23 | 47 | 0 | 0 | 0 | 0 | 0 | 500.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM17HHPL | HAMMEL HOUSES PLAYGROUND UPGRADES | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 400 | HA-Q001 |  |  | HAMMEL HOUSES PLAYGROUND UPGRADES | 2019 | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM17LGPL | LATIMER GARDENS PLAYGROUND UPGRADE | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 400 | HA-Q001 |  |  | LATIMER GARDENS PLAYGROUND UPGRADE | 2019 | 350 | 306.18 | 44 | 0 | 0 | 0 | 0 | 0 | 350.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM17RVBC | RAVENSWOOD HOUSES BASKETBALL COURTS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 401 | HA-D001 |  |  | RENOVATE BASKETBALL COURTS | 2019 | 350 | 287.89 | 62 | 0 | 0 | 0 | 0 | 0 | 349.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM17SHSC | SHELTON HOUSES INSTALLATION OF CCTV'S AND LAC'S | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 412 | HA-Q001 |  |  | SHELTON HOUSES INSTALLATION OF SECURITY CAMERAS | 2019 | 500 | 463.27 | 37 | 0 | 0 | 0 | 0 | 0 | 500.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM18ASBC | RENOVATION OF BASKETBALL COURT AT ASTORIA HOUSES | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 401 | HA-D001 |  |  | RENOVATION OF BASKETBALL COURT AT ASTORIA HOUSES | 2019 | 250 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM18ASLG | LIGHTING INSTALLATION AT ASTORIA HOUSES | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 401 | HA-D001 |  |  | INSTALLATION OF SECURITY CAMERAS AT ASTORIA HOUSES. | 2019 | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM18ASTV | CCTV AT ASTORIA HOUSES | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 401 | HA-D001 |  |  | INSTALLATION OF CCTV'S AT ASTORIA HOUSES | 2019 | 459 | 0 | 459 | 0 | 0 | 0 | 0 | 0 | 459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM18BLGR | BLAND HOUSES GROUNDS BEAUTIFICATION | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 407 | HA-D001 |  |  | BLAND GROUNDS BEAUTIFICATION, INCLUDES BENCHES, SIGNAGE AND GATE AT ENTRANCE | 2019 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM18COTV | LAYERED SECURITY ACCESS AT CONLON LIFHE | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 412 | HA-D001 |  |  | LAYERED SECURITY ACCESS AT CONLON LIFHE | 2019 | 220 | 0 | 220 | 0 | 0 | 0 | 0 | 0 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM18POMO | NYCHA Pomonok: Security System | LOW TO MODERATE INCOME PUBLIC HOUSING CONSTRUCTION | 400 | HA-Q001 |  |  | NYCHA POMONOK: SECURITY SYSTEM | 2019 | 350 | 0 | 350 | 0 | 0 | 0 | 0 | 0 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM19ACCL | ASTORIA COMMUNITY CENTER LIGHTING | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 401 | HA-D001 |  |  | ASTORIA HOUSE COMMUNITY CENTER LIGHTING | 2019 | 150 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM19AHSC | ASTORIA HOUSES SECURITY CAMERAS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 401 | HA-D001 |  |  | INSTALL SECURITY CAMERAS | 2019 | 100 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM19CLHS | CONLON LIFHE HVAC SYSTEM | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 412 | HA-D001 |  |  | FUNDING WILL PROVIDE UPGRADES TO THE HVAC SYSTEM | 2019 | 600 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM19WHRB | WOODSIDE HOUSES RENOVATION OF BOYS AND GIRLS BATHROOMS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 401 | HA-D001 |  |  | RENOVATION OF BOYS AND GIRLS BATHROOM | 2019 | 600 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | CMEQANNEX | OCME - Queens Annex Phase | OCME |  | HL-0083 |  |  | THE OCME ENDEAVORS TO REQUEST THE DESIGN AND CONSTRUCTION OF AN ANNEXFACILITY TO THE EXISTING QUEENS MORGUE TO ACCOMMODATE A SEPARATE CLAIMS-ONLY CASE MANAGEMENT DEPARTMENT AND FAMILY SERVICES CENTER (IN LIEUOF ANY TEMPORARY MEASURES WHICH MAY HAVE ALREADY BEEN IMPLEMENTED AND/OR PLANNED). THE FOLLOWING ARE BRIEF DESCRIPTION OF THE PROGRAMMATICNEEDS | 2019 | 7773 | 0 | 0 | 0 | 490 | 500 | 490 | 458 | 1938 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82CCHIL | CORONA HEALTH CENTER CHILLER REPLACEMENT | CLINIC RENOVATION AND REHABILITATION |  | HL-0082 |  |  | REPLACE THE EXISTING 80 TON YORK CHILLER UNIT WITH HIGH CARRIER 90 TO100 TON UNIT OR THE THE MAXIMUM TONNAGE AVAILABLE FOR 200 AMP SERVICEAND THE CAPACITY OF THE EXISTING DUNNAGE | 2019 | 954 | 0 | 145 | 809 | 0 | 0 | 0 | 0 | 954 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82QUEEN | Queens Animal Shelter | ANIMAL CARE |  | HL-0082 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | CONSTRUCTION | 2019 | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 02201804 | LIC OUTFIT OFFICE SPACE | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 30-30 47TH AVENUE, LIC, NY 11101 | NYC H+H IS OUTFITTING THE NEWLY LEASED SPACE AT 30-30 46TH AVE., LIC,4TH FLOOR, WITH HARDWARE FOR NETWORK INFRASTRUCTURE AND END-USER DEVICES, AND FURNITURE. | 2019 | 2874 | 0 | 2874 | 0 | 0 | 0 | 0 | 0 | 2874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33200501 | EHC: RENOVATION OF THE HIV / INFECTIOUS DISEASE CLINIC | ROUTINE RECONSTRUCTION | 400 404 | HO-D003 |  | 79-01 BROADWAY, ELMHURST, NY 11373 | RENOVATION OF THE HIV / ID CLINIC AT ELMHURST HOSPITAL CENTER IN QUEENS COUNTY. | 2019 | 1000 | 904.91 | 0 | 91 | 0 | 0 | 0 | 0 | 995.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33200801 | ELMHURST: CONSTRUCT WOMEN'S HEALTH PAVILION | ROUTINE RECONSTRUCTION | 404 | HO-D003 |  | 79-01 BROADWAY, ELMHURST, N. Y. 11373 | WOMEN'S HEALTH CENTER (AMBULATORY CARE) AT ELMHURST HOSPITAL CENTER | 2019 | 10800 | 9052.79 | 1 | 0 | 2261 | 0 | 0 | 0 | 11314.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33201301 | EHC: RENOVATION OF ADULT ER | ROUTINE RECONSTRUCTION | 404 | HO-D003 HO-Q378 HO-0214 |  | 79-01 BROADWAY, ELMHURST, NY 11373 | RENOVATE THE ADULT ER INCLUDING THE CONSTRUCTION OF AN ENCLOSED STRETCHER BAY AREA ADJACENT TO THE ER, REDESIGN OF THE TRIAGE/REGISTRATION AREA, AND CONSTRUCTION OF AN EMS RAMP. | 2019 | 20000 | 2032.1 | 6868 | 7000 | 4100 | 0 | 0 | 0 | 20000.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33201505 | ELMHURST: PURCHASE & INSTALL BIPLANE/CT SCANNER | ROUTINE RECONSTRUCTION | 404 | HO-Q378 HO-D003 |  | 79-01 BROADWAY ELMHURST, NY 11373 | ELMHURST: REPLACE ANGIOGRAPHY EQUIPMENT AND SUITE | 2019 | 3363 | 0 | 3363 | 0 | 0 | 0 | 0 | 0 | 3363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33201602 | EHC PARAPET & CORNER FACADE REHAB A,B,D,E, J AND O&G ANNEX. | ROUTINE RECONSTRUCTION | 404 | HO-0214 |  | 79-01 BROADWAY, ELMHURST, N. Y. 11373 | THE PURPOSE OF THIS PROJECT IS TO RENOVATE BUILDINGS A, B, C, F AND G AT ELMHURST HOSPITAL CENTER USING LOCAL LAW 11- FUNDS FOR LOCAL LAW11 COMPLIANCE. | 2019 | 2804 | 0 | 512 | 1700 | 592 | 0 | 0 | 0 | 2804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33201610 | RENOVATE JUNCTION BLVD CHILD HEALTH CLINIC | ROUTINE RECONSTRUCTION | 403 | HO-0214 |  | 34-33 JUNCTION BLVD. CORONA, NY 11372 | RENOVATE THE JUNCTION BLVD CHILD HEALTH CLINIC IN ORDER TO EXPAND PRIMARY CARE HEALTH SERVICES. | 2019 | 0 | 3197.47 | 889 | 0 | 0 | 0 | 0 | 0 | 4086.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33201804 | ELMHURST: REHABILITATE N & S STAIRWELLS IN PARKING GARAGE | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 79-01 BROADWAY, QUEENS, NY | REHABILITATE N & S STAIRWELLS IN PARKING GARAGE | 2019 | 992 | 0 | 876 | 116 | 0 | 0 | 0 | 0 | 992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33201901 | EHC: L&D ROOMS & NURSING STATION RENOVATION | ROUTINE RECONSTRUCTION |  | HO-Q378 |  | 79-01 BROADWAY, ELMHURST, NEW YORK 11373 | CONSTRUCTION OF THE LABOR AND DELIVERY ROOMS AND NURSING STATIONS AT ELMHURST HOSPITAL CENTER | 2019 | 0 | 0 | 400 | 1600 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33201902 | ELMHURST: CONSTRUCT MATERNAL FETAL MEDICINE UNIT | ROUTINE RECONSTRUCTION |  | HO-D003 |  | 79-01 BROADWAY | CONSTRUCT MATERNAL FETAL MEDICINE UNIT | 2019 | 1320 | 0 | 320 | 1000 | 0 | 0 | 0 | 0 | 1320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 34201201 | QHC: "T" BUILDING RELOCATIONS | ROUTINE RECONSTRUCTION | 408 | HO-0214 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 82-68 164 STREET, JAMAICA, NY 11432 | RELOCATE QUEEN HOSPITAL CENTER'S "T" BUILDING PROGRAMS TO MAKE WAY FOR AFFORDABLE/SUPPORTIVE HOUSING. | 2019 | 6500 | 2559.5 | 150 | 1000 | 2790 | 0 | 0 | 0 | 6499.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 34201401 | QHC: RENOVATIONS TO RELOCATE ACUTE DIALYSIS PROG. | ROUTINE RECONSTRUCTION | 400 408 | HO-Q003 |  | 82-68 164TH STREET, JAMAICA, N. Y. 11432 | THE PURPOSE OF THIS PROJECT IS TO RENOVATE SPACE TO SUPPORT RELOCATION OF ACUTE DIALYSIS PROGRAM AT QUEENS HOSPITAL CENTER. | 2019 | 1200 | 101.92 | 0 | 1098 | 0 | 0 | 0 | 0 | 1199.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 34201402 | QHC: RENOVATE/EXPAND ADULT EMERGENCY DEPARTMENT | ROUTINE RECONSTRUCTION | 408 | HO-D003 HO-0214 HO-Q003 |  | 82-68 164TH STREET, JAMAICA, NY 11432 | QUEENS HOSPITAL CENTER PLANS TO EXPAND ITS ED INTO THE VACATED CPEP AND ED ADMINISTRATIVE OFFICES OF APPROXIMATELY 5,865 SQ. FT. OF SPACE IN ORDER TO ADD 20 TREATMENT SPACES. | 2019 | 3480 | 4792.24 | 314 | 781 | 0 | 0 | 0 | 0 | 5887.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 34201501 | QHC: ENDOSCOPY ROOM CONVERSION | ROUTINE RECONSTRUCTION | 408 | HO-D003 |  | 82-68 164TH STREET, JAMAICA, NY 11432 | ENDOSCOPY ROOM CONVERSION AT QUEENS HOSPITAL CENTER. | 2019 | 350 | 0 | 0 | 350 | 0 | 0 | 0 | 0 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 34201502 | QHC: BOILER CONTROLS REPLACEMENT | ROUTINE RECONSTRUCTION | 408 | HO-0214 |  | 82-68 164TH STREET, JAMAICA, NY 11432 | REPLACE END OF LIFE BOILER CONTROLS AT QUEENS HOSPITAL CENTER. | 2019 | 150 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 34201503 | QHC: EXPAND AND RENOVATE PHARMACY | ROUTINE RECONSTRUCTION | 408 | HO-Q003 HO-D003 |  | 82-68 164 STREET JAMAICA, NY 11432 | QHC: EXPAND AND RENOVATE PHARMACY | 2019 | 3600 | 0 | 0 | 3600 | 0 | 0 | 0 | 0 | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 34201901 | QHC: SIDEWALK REPLACEMENT | ROUTINE RECONSTRUCTION |  | HO-0214 |  |  | REPLACE SIDEWALK ON THE CAMPUS OF QUEENS HOSPITAL CENTER | 2019 | 881 | 0 | 881 | 0 | 0 | 0 | 0 | 0 | 881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | ACEHHC803 | NYC Health + Hospitals/Queens Energy Efficiency Upgrade | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 401 | PU-0025 |  |  | NYC HEALTH + HOSPITALS/QUEENS ENERGY EFFICIENCY UPGRADE | 2019 | 0 | 0 | 0 | 3197 | 0 | 0 | 0 | 0 | 3197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | QHC2 | QHC: CONSTRUCT AN AMBULATORY CARE PAVILION (QHC MAJOR 2) | MAJOR OR PARTIAL HOSPITAL RECONSTRUCTION | 400 408 | HO-0377 |  | 82-68 164TH STREET, JAMAICA, NY 11432 | QUEENS HOSPITAL CENTER - MAJOR MODERNIZATION PHASE II TO CONSTRUCT ANAMBULATORY CARE PAVILION. | 2019 | 53554 | 52310.86 | 0 | 0 | 0 | 1142 | 0 | 0 | 53452.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB05-01-A | GI - Cons of ROW Bioswales & Stormwwater GS in BB-005, Ph 1 | GREEN INFRASTRUCTURE PROGRAM | 400 | WP-0169 |  |  | GI - CONSTRUCTION OF RIGHT- OF - WAY BIOSWALES AND STORMWATER GREENSTREETS IN BB-005, PHASE I, STAGE 1 | 2019 | 9636 | 0 | 0 | 0 | 19100 | 0 | 0 | 0 | 19100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB06-01-A | GI - ON SITE CONSTRUCTION FOR GREEN INFRASTRUCTURE IN BB-006 | GREEN INFRASTRUCTURE PROGRAM | 400 | WP-0169 |  |  | GI - ON SITE CONSTRUCTION FOR GREEN INFRASTRUCTURE IN BB-006 | 2019 | 5000 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-205-L | RECONS. CBS/PBS SYSTEM AT BOWERY BAY WPCP (TOC JOB) | PLANT UPGRADING AND RECONSTRUCTION | 400 401 | WP-0112 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | 43-01 BERRIAN BLVD., ASTORIA, N.Y. 11105 | RECONSTRUCTION OF CBS/PBS SYSTEM AT THE BOWERY BAY WPCP | 2019 | 5700 | 8885.38 | 163 | 0 | 0 | 0 | 0 | 0 | 9048.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-215-L | POWER DISTRIBUTION AT BOWERY BAY WPCP | PLANT UPGRADING AND RECONSTRUCTION | 400 401 | WP-0112 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 43-01 BERRIAN BLVD., ASTORIA, N.Y 11105 | POWER DISTRIBUTION AT BOWERY BAY WPCP | 2019 | 37258 | 9496.18 | 516 | 49800 | 0 | 0 | 0 | 0 | 59812.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-216-L | RECONSTRUCTION OF PRIMARY TANKS AT BOWERY BAY WPCP | PLANT UPGRADING AND RECONSTRUCTION | 400 401 | WP-0112 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | 43-01 BERRIAN BL;VD., ASTORIA, N.Y. 11105 | RECONSTRUCTION OF PRIMARY TANKS AT BOWERY BAY WPCP | 2019 | 16726 | 7961.03 | 0 | 0 | 0 | 4000 | 0 | 40000 | 51961.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-220-L | REPLACEMENT OF EXISTING EMERGENCY GENERATORS @ BOWERY BAY | PLANT UPGRADING AND RECONSTRUCTION | 400 401 | WP-0112 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | 43-01 BERRIAN BLVD., ASTORIA, N.Y. 11105 | REPLACEMENT OF EXISTING EMERGENCY GENERATORS AT THE BOWERY BAY WASTEWATER TREATMENT PLANT | 2019 | 30650 | 0 | 0 | 0 | 10000 | 0 | 10000 | 100000 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-61 | Main Sewage Pump Upgrades at Bowery Bay WPCP | PLANT COMPONENT STABILIZATION | 407 | WP-0237 WP-0112 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | INSTALLATION OF MAIN SEWAGE PUMPS / VARIABLE FREQUENCY DRIVES AND GENERATORS AT THE BOWERY BAY WPCP | 2019 | 6988 | 8026.84 | 4368 | 0 | 0 | 0 | 0 | 0 | 12394.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-64 | MSP Discharge Piping/Controls at Bowery Bay WPCP | PLANT UPGRADING AND RECONSTRUCTION | 407 | WP-0112 |  |  | CONTRACT BB-64 IS TO PROVIDE DESIGN SERVICES REQUIRED IN CONNECTION WITH THE NEW MAIN SEWAGE PUMP UPGRADES AT THE BOWERY BAY WASTEWATER TREATMENT PLANT. THE SCOPE OF WORK INCLUDES BUT IS NOT LIMITED TO: DESIGN FOR THE REMOVAL OF (8) EXISTING VARIABLE FREQUENCY DRIVES (VFDS); AND THE TEMPORARY 48 RAW SEWAGE HEADER ; DESIGN FOR THE REMOVAL AND REPLACEMENT OF THE MAIN SEWAGE PUMP DISCHARGE PIPING WITH EIGHT (8) GATE VALVES AND SIX (6) NEW RESISTOR BANK CONTROLLERS. DESIGN FOR THE INSTALLATION OF ONE (1) WOUND ROTOR MOTOR GATE VALVE (LLMSP #1), AND SPECIFY THE PURCHASE OF ONE (1) SPARE; DESIGN FOR THE REPLACEMENT OF SUMP PUMPS AND PIPING IN THE LOW LEVEL AND HIGH LEVEL PUMP STATIONS; THE REPLACEMENT OF LIGHTING IN THE LOW & HIGH LEVEL PUMP STATIONS; AND THE REFURBISHMENT OF TWO (2) EXISTING RESISTER BANK CONTROLLERS IN LOW LE | 2019 | 76843 | 65543.9 | 1298 | 0 | 0 | 0 | 0 | 0 | 66841.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | C540 | Completion of CT3 Stage 2 B/Q Leg & Bklyn Downtake Intercon. | CITY TUNNEL NO. 3, STAGE 2 | 413 | W-0013 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | APPROXIMATE LOCATION: SHAFT 18B - VICINITY OF 30 AV & BROOKLYN-QUEENS EXPRESSWAY | CONSTRUCTION OF SHAFTS 17B AND 18B FOR CITY TUNNEL NO 3, STAGE 2 IN THEBOROUGH OF QUEENS | 2019 | 104830 | 99107.06 | 24275 | 304716 | 0 | 300000 | 0 | 0 | 728098.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-FB-BWR | FLUSHING BAY BENDING WEIRS AT REGULATORS | WATER QUALITY MANDATES | 400 407 | WP-0169 |  |  | FLUSHING BAY BENDING WEIRS AT REGULATORS. FLUSHING BAY WATER QUALITY | 2019 | 11000 | 38386.81 | 1221 | 0 | 0 | 0 | 0 | 0 | 39607.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-JA-BWR | JAMAICA BAY BENDING WEIRS AT REGULATORS | WATER QUALITY MANDATES | 400 410 412 413 414 | WP-0169 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | JAMAICA BAY BENDING WEIRS | 2019 | 14366 | 10055.08 | 244 | 0 | 0 | 0 | 0 | 0 | 10299.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-NC-EKE | ENGLISH KILLS AERATION, ENHANCED ZONE II | WATER QUALITY MANDATES | 400 402 405 | WP-0169 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES |  | ENGLISH KILLS AERATION, ENHANCED ZONE II. WATER QUALITY FACILITY COMBINED SEWER OVERFLOW NEWTOWN CREEK. | 2019 | 97309 | 26273.47 | 2000 | 22897 | 0 | 0 | 0 | 0 | 51170.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-AC-DF | CSO ALLEY CREEK DISINFECTION | WATER QUALITY MANDATES | 400 | WP-0169 |  |  | CSO ALLEY CREEK DISINFECTION | 2019 | 12000 | 2365.48 | 0 | 0 | 0 | 1500 | 0 | 15500 | 19365.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-FBAY | CONSTRUCTION OF THE FLUSHING BAY CSO ABATEMENT FACILITIES | WATER QUALITY MANDATES | 400 407 | WP-0169 |  |  | CONSTRUCTION OF THE FLUSHING BAY CSO ABATEMENT FACILITIES | 2019 | 128250 | 0 | 0 | 0 | 20000 | 0 | 30000 | 72250 | 122250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-FC-DF | CSO FLUSHING CREEK & TI-011 DISINFECTION | WATER QUALITY MANDATES | 400 407 | WP-0169 |  |  | CSO FLUSHING CREEK & TI-011 DISINFECTION | 2019 | 24000 | 1000 | 13731 | 7000 | 0 | 2500 | 56500 | 9000 | 89731 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-JA | JAMAICA WATER QUALITY COMBINED SEWER OVERLOW | WATER QUALITY MANDATES | 400 410 412 413 414 | WP-0169 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  |  | 2019 | 170508 | 17640.4 | 1297 | 0 | 0 | 0 | 0 | 0 | 18937.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | DOT-SEQBO | DOT TASK FORCE PRIORITY PROJECTS, SE QUEENS | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 412 413 | SE-0001 |  |  | DOT TASK FORCE PRIORITY PROJECTS, SE QUEENS | 2019 | 68606 | 0 | 0 | 541 | 0 | 0 | 0 | 0 | 541 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | FCWET | CONSTRUCTION OF FLUSHING CREEK WETLAND PROJECT | WATER QUALITY MANDATES | 400 | WP-0169 |  |  | CONSTRUCTION OF FLUSHING CREEK WETLAND PROJECT | 2019 | 8000 | 0 | 0 | 0 | 0 | 8000 | 0 | 0 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | GCJA03-2C | GI - CONS OF ROW GI IN JAMAICA BAY CSO AREAS JAM-03 & JAM-2C | GREEN INFRASTRUCTURE PROGRAM | 400 | WP-0169 |  |  | CONSTRUCTION OF RIGHT-OF-WAY GREEN INFRASTRUCTURE IN THE JAMAICA BAY CSO AREAS JAM-003 AND JAM-002C | 2019 | 14000 | 0 | 0 | 0 | 14000 | 0 | 0 | 0 | 14000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | GCJA03-3A | GI - CONS OF ROW GI IN CSO TRIBUTARY AREA JAM-003, PH 3A | GREEN INFRASTRUCTURE PROGRAM | 400 410 412 413 414 | WP-0169 |  |  | GI - CONS OF ROW GI IN CSO TRIBUTARY AREA JAM-003, PH 2A | 2019 | 9000 | 0 | 0 | 0 | 9000 | 0 | 0 | 0 | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | GCJA03-3C | GI - CONS OF ROW GI IN JAMAICA BAY CSO AREAS JAM-03 & JAM-3C | GREEN INFRASTRUCTURE PROGRAM | 400 | WP-0169 |  |  | CONSTRUCTION OF RIGHT-OF-WAY GREEN INFRASTRUCTURE IN THE JAMAICA BAY CSO AREAS JAM-003 AND JAM-03C | 2019 | 14000 | 0 | 0 | 0 | 0 | 14000 | 0 | 0 | 14000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | GCTI10-1C | CONS OF ROW GI FLUSHING CREEK CSO TRIB AREA TI-10, ST 1 PH C | GREEN INFRASTRUCTURE PROGRAM | 400 | WP-0169 |  |  | CONSTRUCTION OF ROW GREEN INFRASTRUCTURE IN FLUSHING CREEK CSO TRIBUTARY AREA TI-10, STAGE 1, PHASE C | 2019 | 14000 | 0 | 0 | 0 | 0 | 14000 | 0 | 0 | 14000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | GQBB08-02 | On-Site Construction of GI Practices in BB-008 Stage 1 & 2 | GREEN INFRASTRUCTURE PROGRAM | 400 | WP-0169 |  |  | ON-SITE CONSTRUCTION OF GI PRACTICES IN BB-008 STAGE 1 & 2 | 2019 | 3750 | 0 | 0 | 0 | 3750 | 0 | 0 | 0 | 3750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | GQNC83-03 | On-Site Construction of GI Practices in NCB-083 Stage 1 & 2 | GREEN INFRASTRUCTURE PROGRAM | 400 | WP-0169 |  |  | ON-SITE CONSTRUCTION OF GI PRACTICES IN NCB-083 STAGE 1 | 2019 | 3000 | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | GQTI3-23A | GI - CONS OF ROW GI IN FLUSHING CREEK CSO AREA TI-03 & TI-23 | GREEN INFRASTRUCTURE PROGRAM | 400 | WP-0169 |  |  | GI - CONS OF ROW GI IN FLUSHING CREEK CSO TRIBUTARY AREA TI-03 AND TI-23 | 2019 | 14000 | 0 | 0 | 0 | 14000 | 0 | 0 | 0 | 14000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | GQTI3-23B | GI - CONS OF ROW GI IN FLUSHING CREEK CSO AREA TI-03 & TI-23 | GREEN INFRASTRUCTURE PROGRAM | 400 | WP-0169 |  |  | GI - CONS OF ROW GI IN FLUSHING CREEK CSO TRIBUTARY AREA TI-03 AND TI-23 | 2019 | 14000 | 0 | 0 | 0 | 14000 | 0 | 0 | 0 | 14000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | J-191-L | RECONSTRUCTION OF THE HVAC (CHILLER) SYSTEM @ JAMAICA WWTP | PLANT UPGRADING AND RECONSTRUCTION | 400 | WP-0112 |  | 150-20 134TH STREET, JAMAICA, NEW YORK 11430 | RECONSTRUCTION OF THE HVAC SYSTEM INTHE ADMINISTRATION BUILDING AT THE JAMAICA WWTP. | 2019 | 2117 | 0 | 0 | 1707 | 0 | 0 | 0 | 0 | 1707 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | JA-179-L | INSTALLATION OF EMERGENCY GENERATORS AT JAMAICA WPCP | PLANT UPGRADING AND RECONSTRUCTION | 400 410 | WP-0112 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | 150-2- 134TH STREET, JAMAICA, N.Y. 11430 | INSTALLATION OF EMERGENCY GENERATORS AT JAMAICA WPCP | 2019 | 57768 | 5767.07 | 965 | 3500 | 35000 | 0 | 0 | 0 | 45232.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | JA-STAB | STABILIZATION PROGRAM AT JAMAICA WPCP | PLANT COMPONENT STABILIZATION | 412 | WP-0247 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | QUEENS | FINAL DESIGN TO IMPROVE PROCESS AND TREATMENT OPERATIONS AND TO ALLOWTO ACCEPT FLOW EQUAL TO AT LEAST TWICE THE DRY WEATHER FLOW | 2019 | 638406 | 477067.17 | 1682 | 0 | 0 | 0 | 0 | 0 | 478749.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | MASPETH | RECONSTRUCTION OF BUILDING, MASPETH, QUEENS | FACILITY PURCHASES AND RECONSTRUCTION | 400 | EP-0006 |  | RECONSTRUCTION OF BUILDING, MASPETH, QUEENS | RECONSTRUCTION OF BUILDING, MASPETH, QUEENS | 2019 | 67374 | 5542.88 | 0 | 1000 | 0 | 0 | 0 | 10000 | 16542.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | NAS-EXPWM | Nassau Expressway Water Main with NYSDOT | WATER QUALITY PRESERVATION | 400 | WM-0006 |  |  | DUE TO PROPOSED RECONSTRUCTION OF THE NASSAU EXPRESSWAY BY NYS DOT, DEP WOULD LIKE TO RELOCATE AND UPGRADE THE EXISTING WATER MAIN FROM CONCRETE TO A NEW STEEL MAIN FROM BURNSIDE AVE AND ROCKWAY TURNPIKE TO THE BED OF NASSAU EXPRESSWAY. | 2019 | 4800 | 0 | 4800 | 0 | 0 | 0 | 0 | 0 | 4800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-277 | RECONSTRUCTION AT 108 STREET PUMPING STATION | PLANT UPGRADING AND RECONSTRUCTION | 400 | WP-0269 |  | 108 STREET | RECONSTRUCTION OF 108 STREET P.S. | 2019 | 10990 | 500 | 0 | 1100 | 0 | 0 | 15000 | 0 | 16600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-284 | CLEARVIEW PUMPING STATION | PLANT UPGRADING AND RECONSTRUCTION | 400 407 | WP-0269 |  | CLEARVIEW PUMPING STATION | CLEARVIEW PUMPING STATION | 2019 | 12200 | 1000 | 0 | 0 | 20922 | 0 | 0 | 0 | 21922 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-285 | RIKERS ISLAND NORTH AND SOUTH PUMPING STATION | PLANT UPGRADING AND RECONSTRUCTION | 400 401 | WP-0269 |  | RIKERS ISLAND NORTH | RIKERS ISLAND NORTH & SOUTH PUMPING STATION | 2019 | 9000 | 3532.54 | 0 | 17700 | 0 | 0 | 0 | 0 | 21232.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-286 | ST ALBANS PUMPING STATION | PLANT UPGRADING AND RECONSTRUCTION | 400 412 | WP-0269 |  |  | ST ALBANS PUMPING STATION | 2019 | 8000 | 0 | 0 | 0 | 0 | 2000 | 5000 | 0 | 7000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-291 | 154TH STREET PUMPING STATION | PLANT UPGRADING AND RECONSTRUCTION | 400 407 | WP-0269 |  | 154TH STREET PUMPING STATION | 154TH STREET PUMPING STATION | 2019 | 4551 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-292 | RECONSTRUCTIONOF LINDEN PLACE PUMPING STATION | PLANT UPGRADING AND RECONSTRUCTION | 400 407 | WP-0269 |  | LINDEN PLACE PUMPING STATION | LINDEN PLACE PUMPING STATION | 2019 | 6436 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-293 | RECONSTRUCTION AT HOWARD BEACH PUMPING STATION | PLANT UPGRADING AND RECONSTRUCTION | 400 410 | WP-0269 |  | HOWARD BEACH | RECONSTRUCTION AT HOWARD BEACH PUMPING STATION | 2019 | 8867 | 0 | 0 | 0 | 0 | 1773 | 4000 | 0 | 5773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-304 | RECONSTRUCTION AT GLENDALE PUMPING STATION | PLANT UPGRADING AND RECONSTRUCTION | 400 405 | WP-0269 |  | GLENDALE, QUEENS | RECONSTRUCTION AT GLENDALE PUMPING STATION | 2019 | 6000 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-321 | RECONSTRUCTION OF LITTLE NECK PUMPING STATION, QUEENS, N.Y. | PLANT UPGRADING AND RECONSTRUCTION | 400 411 | WP-0269 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 40TH AVENUE WEST OF 248TH STREET, QUEENS, NEW YORK | RECONSTRUCTION OF LITTLE NECK PUMPING STATION, QUEENS, N.Y. | 2019 | 7000 | 0 | 0 | 2000 | 0 | 3000 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-326 | INSTALLATION OF SE JAMAICA PUMPING STATION | PLANT UPGRADING AND RECONSTRUCTION | 400 | WP-0269 |  | DON AKAMNONU 1943/ 100 MGD 150-20 134TH STREET, JAMAICA QUEENS, N.Y. 11430 | INSTALLATION OF SE JAMAICA PUMPING STATION | 2019 | 21000 | 0 | 0 | 0 | 7500 | 0 | 0 | 53000 | 60500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-335 | RECONSTRUCTION OF TALLMAN ISLAND INTERCEPTOR DAMAGE | PLANT UPGRADING AND RECONSTRUCTION | 400 | WP-0269 |  | 37TH AVENUE & 114TH STREET, FLUSHING N.Y 11368 | RECONSTRUCTION OF TALLMAN ISLAND INTERCEPTOR DUE TO DAMAGE BY CONSTRUCTION COMPANY. APPROXIMATELY 700 FEET OF 87" DIAMETER INTERCEPTING SEWER HAS 69 6" DIAMETER HOLES. DDC WILL PERFORM THE DESIGN WORK, BID THE CONTRACT, AND MANAGE THE CONSRRUCTION | 2019 | 7650 | 0 | 0 | 9240 | 0 | 0 | 0 | 0 | 9240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QED-1049 | Rplmnt WM at 111 St btw 45th & Corona Ave (HWD10311) | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 400 | SE-0002Q WM-0001 |  |  | REPLACEMENT OF DISTRIBUTION WATER MAIN AT 111TH STREET BETWEEN 45TH AVENUE AND CORONA AVENUE. BOROUGH OF QUEENS. | 2019 | 5974 | 0 | 0 | 0 | 5974 | 0 | 0 | 0 | 5974 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QED-NEW | CORE WM AREA CONTRACT, QUEENS | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 400 | WM-0006 |  |  | RECONSTRUCTION OF WATER MAINS IN QUEENS | 2019 | 47200 | 0 | 0 | 0 | 0 | 12000 | 7000 | 4000 | 23000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QNSREPAIR | REHABILITATION OF QUEENS REPAIR FACILITY | FACILITY PURCHASES AND RECONSTRUCTION | 400 | EP-0006 |  |  | REHABILITATION FO QUEENS REPAIR FACILITY | 2019 | 37750 | 0 | 0 | 0 | 4000 | 0 | 0 | 49000 | 53000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | R-009-L | RECONSTRUCT FOUR SODIUM HYPOCHLORITE CBS TANKS @ ROCKAWAY | PLANT UPGRADING AND RECONSTRUCTION | 400 | WP-0112 |  | 106-21 BEACH CHANNEL DRIVE, ROCKAWAY, N.Y. 11694 | RECONSTRUCTION OF FOUR (4) SODIUM HYPOCHLORITE CBS TANKS AT THE ROCKAWAY WASTEWATER TREATMENT PLANT | 2019 | 2480 | 0 | 0 | 0 | 1980 | 0 | 0 | 0 | 1980 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | R-153-L | RECONSTRUCT FINAL SETTLING SYSTEM @ ROCKAWAY WWTP | PLANT UPGRADING AND RECONSTRUCTION | 400 414 | WP-0112 |  | 106-21 BECH CHANNEL DRIVE, ROCKAWAY, N.Y. 11694 | RECONSTRUCT FINAL SETTLING SYSTEM @ ROCKAWAY WWTP | 2019 | 21358 | 0 | 0 | 0 | 0 | 0 | 9000 | 0 | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | R-156-L | RECONSTRUCT POWER DISTRIBUTION EQUIPMENT @ ROCKAWAY WWTP | PLANT UPGRADING AND RECONSTRUCTION | 400 414 | WP-0112 |  | 106-21 BEACH CHANNEL DRIVE, ROCKAWAY, N.Y. 11694 | RECONSTRUCT POWER DISTRIBUTION EQUIPMENT @ ROCKAWAY WWTP | 2019 | 1903 | 0 | 0 | 351 | 0 | 0 | 0 | 1753 | 2104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | RO-2 | REPLACE MAIN SEWAGE PUMPS AT ROCKAWAY WPCP | PLANT UPGRADING AND RECONSTRUCTION | 400 | WP-0112 |  |  | REPLACE MAIN SEWAGE PUMPS AT ROCKAWAY WPCP | 2019 | 25000 | 0 | 0 | 4400 | 0 | 54400 | 0 | 0 | 58800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | RO-3 | REPLACE MAIN INFLUENT GATES & ACTUATORS AT ROCKAWAY WPCP | PLANT UPGRADING AND RECONSTRUCTION | 400 | WP-0112 |  |  | REPLACE MAIN INFLUENT GATES & ACTUATORS AT ROCKAWAY WPCP | 2019 | 15000 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SE-861A | HLSS; Strm, san & comb swers & WM, Borden Ave, Phase 2, Qns | REPLACEMENT OF CHRONICALLY FAILING COMPONENTS | 402 | SE-0004 SE-0200Q SE-9336 SE-0002Q WM-0001 |  |  | NEW HLSS; STRM, SAN & COMB SWERS & WM BORDEN AVE B/T JACKSON AVE & E RIVER, PHASE 2, QNS | 2019 | 27575 | 0 | 0 | 0 | 95000 | 0 | 0 | 0 | 95000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ200592 | Southeast Queens - Rosedale South | EXTENSIONS TO ACCOMMODATE NEW DEVELOPMENT | 413 | WM-0001 SE-0200Q SE-0002Q |  |  | INSTALLATION OF STORM AND SANITARY SEWERS AND WATER MAINS IN THE ROSEDALE AREA OF QUEENS BOUNDED BY HOOK CREEK BLVD, 257TH ST, CRAFT AVE, AND FRANCIS LEWIS BLVD, ETC. THIS PROJECT IS TO BE COMPLETED IN CONJUNCTION WITH DOT. | 2019 | 53282 | 0 | 0 | 0 | 38332 | 0 | 0 | 0 | 38332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQCB1213 | SEWER BUILD-OUT FOR S.E. QUEENS | PROGRAMMATIC REPLACEMENT AND RECONSTRUCTION | 412 413 | SE-0004 |  |  | SEWER BUILD-OUT FOR S.E. QUEENS | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 209611 | 209611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ-DKWPK | CONSTRUCTION FOR DETECTIVE KEITH WILLIAMS PARK | GREEN INFRASTRUCTURE PROGRAM | 412 413 | SE-0005 |  |  | CONSTRUCTION FOR DETECTIVE KEITH WILLIAMS PARK | 2019 | 1250 | 0 | 0 | 0 | 1250 | 0 | 0 | 0 | 1250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQGI-01 | SEQ - CONSTRUCTION OF GREEN INFRASTRUCTURE SOUTHEAST QUEENS | GREEN INFRASTRUCTURE PROGRAM | 412 413 | SE-0005 EP-0007 |  |  | CONSTRUCTION OG RIGHT OF WAY BIOSWALES, RIGHT OF WAY GREENSTRIPS, STORMWATER GREENSTREETS, AND PRECAST POROUS CONCRETE IN SOUTHEAST QUEENS. | 2019 | 7957 | 0 | 8597 | 2410 | 1130 | 0 | 17300 | 0 | 29437 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ-GREEN | HOLDING CODE FOR GI CONSTRUCTION IN SOUTHEAST QUEENS | GREEN INFRASTRUCTURE PROGRAM | 412 413 | SE-0005 |  |  | HOLDING CODE FOR GI CONSTRUCTION IN SOUTHEAST QUEENS | 2019 | 14930 | 0 | 0 | 0 | 1500 | 1000 | 130 | 12300 | 14930 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQNS004 | SEWER WHEN & WHERE CONTRACT IN S.E. QNS | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 412 413 | SE-0200Q SE-0002Q WM-0001 SE-0005 |  |  | STORM SEWERS ANSD ADDTIONAL WORK AS NEEDED, SE QUEENS. | 2019 | 25000 | 0 | 0 | 23309 | 0 | 0 | 0 | 0 | 23309 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ-PGRID | HOLDING CODE FOR GREEN INFRASTRUCTURE IN PRIORITY GRIDS | GREEN INFRASTRUCTURE PROGRAM | 412 413 | SE-0005 |  |  | HOLDING CODE FOR GREEN INFRASTRUCTURE IN PRIORITY GRIDS | 2019 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ-RAILP | CONSTRUCTION FOR RAILROAD PARK | GREEN INFRASTRUCTURE PROGRAM | 412 413 | SE-0005 |  |  | CONSTRUCTION OF RAILROAD PARK | 2019 | 2250 | 0 | 0 | 0 | 2250 | 0 | 0 | 0 | 2250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ-ROYWP | CONSTRUCTION OF GREEN INFRASTRUCTURE AT ROY WILKINS PARK | GREEN INFRASTRUCTURE PROGRAM | 412 413 | WP-0169 |  |  | RESTORATION OF THE ROY WILKINS RECREATION CENTER PONDS AND THE REDUCTION IN AN AVERAGE ANNUAL CSO FROM MERRICK BLVD. | 2019 | 2020 | 0 | 2020 | 0 | 0 | 0 | 0 | 0 | 2020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ-SJH | CONSTRUCTION FOR CLOUDBURST PROJECT AT SOUTH JAMAICA HOUSES | GREEN INFRASTRUCTURE PROGRAM | 412 413 | SE-0005 |  |  | CONSTRUCTION FOR CLOUDBURST PROJECT AT SOUTH JAMAICA HOUSES | 2019 | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ-STA | CONSTRUCTION FOR CLOUDBURST PROJECT AT ST ALBANS | GREEN INFRASTRUCTURE PROGRAM | 412 413 | WP-0169 |  |  | CONSTRUCTION FOR CLOUDBURST PROJECT AT ST ALBANS | 2019 | 2800 | 0 | 400 | 400 | 0 | 2000 | 0 | 0 | 2800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SF-BNR-RK | STEP FEED BNR AT ROCKAWAY | BIOLOGICAL NUTRIENT REMOVAL | 400 414 | WP-0285 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES |  | THIS PROJECT IS TO RETROFIT THE EXISTING ROCKAWAY WWTP FOR THE STEP FEED BNR PROCESS. THIS WORK IS A REQUIREMENT OF THE JAMAICA BAY NEGOTIATIONS WITHT THE DEC AND WILL BE ENFORCEABLE UNDER THE NEW NITROGEN CONSENT JUDGMENT. THE WORK WILL INVOLVE INSTALLING NEW DIFFUSERS, SUBMERSIBLE MIXERS, BAFFLES, FROTH CONTROL AND INSTRUMENTAION IN ALL FOUR AERATION TANKS. | 2019 | 27250 | 18996 | 467 | 0 | 0 | 0 | 0 | 0 | 19463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | STA24TNKS | STATION 24 GROUNDWATER TANKS DEMOLITION | FACILITY PURCHASES AND RECONSTRUCTION | 400 | EP-0006 |  |  | DEMOLITION, REMOVAL AND DISPOSAL OF TWO (2) ON-GROUND WATER TANKS AT STATION 24, BWSO GROUNDWATER FACILITY (THE LOT ALSO INCLUDES FIELD OPERATIONS QUEENS REPAIR AND SOUTH SEWER MAINTENANCE FACILITIES) LOCATED AT 106-36 180TH ST, JAMAICA, NY. REMOVAL OF THE TANKS PRIOR TO THE COMPLETE REHABILITATION OF THE QUEENS REPAIR SITE WILL PROVIDE SPACE TO PARK DEP VEHICLES, AS WELL AS PROVIDE ADDITIONAL STORAGE AREA. | 2019 | 2500 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-167-L | RECONSTRUCTION OF SEAWALL/DOCK @ TALLMAN ISLAND WPCP | PLANT UPGRADING AND RECONSTRUCTION | 400 407 | WP-0112 |  | 127 STREET AND EAST RIVER, COLLEGE POINT, N.Y. 11356 | RECONSTRUCTION OF SEAWALL/DOCK AT THE TALLMAN ISLAND WPCP | 2019 | 14041 | 6007.34 | 0 | 0 | 2671 | 33650 | 0 | 0 | 42328.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-168-L | HEADWORKS IMPROVEMENTS AT THE TALLMAN ISLAND WPCP | PLANT UPGRADING AND RECONSTRUCTION | 400 407 | WP-0112 |  | 127 STREET AND EAST RIVER, COLLEGE POINT, N.Y. 11356 | HEADWORKS IMPROVEMENTS AT THE TALLMAN ISLAND WPCP | 2019 | 11273 | 4699.47 | 0 | 3500 | 20000 | 0 | 0 | 0 | 28199.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-169-L | RECONSTRUCT OF THE POWER DISTRIBUTION AT TALLMAN ISLAND WPCP | PLANT UPGRADING AND RECONSTRUCTION | 400 407 | WP-0112 |  | 127TH STREET & EAST RIVER, COLLEGE POINT, N.Y. 11356 | RECONSTRUCTION OF THE POWER DISTRIBUTION AT TALLMAN ISLAND WPCP | 2019 | 7269 | 6684.95 | 0 | 0 | 0 | 0 | 9700 | 20000 | 36384.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-170-L | RECONSTRUCT SLUDGE HANDLING SYSTEM @ TALLMAN ISLAND WWTP | PLANT UPGRADING AND RECONSTRUCTION | 400 407 | WP-0112 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | 127 STREET & EAST RIVER COLLEGE POINT, N.Y. 11356 | RECONSTRUCT SLUDGE HANDELING SYSTEM AT THE TALLMAN ISLAND WWT | 2019 | 16564 | 0 | 0 | 0 | 0 | 0 | 0 | 7000 | 7000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-172 | HVAC UPGRADE FOR PUMP & BLOWER BLDG AT TALLMAN ISLAND WPCP | PLANT UPGRADING AND RECONSTRUCTION | 400 407 | WP-0112 |  |  | HVAC UPGRADE FOR PUMP & BLOWER BLDG AT TALLMAN ISLAND WPCP | 2019 | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-173 | RECONS OF SLUDGE HANDLING SYSTEM AT TALLMAN ISLAND WPCP | PLANT UPGRADING AND RECONSTRUCTION | 400 407 | WP-0112 |  |  | RECONS OF SLUDGE HANDLING SYSTEM AT TALLMAN ISLAND WPCP | 2019 | 14000 | 0 | 0 | 0 | 0 | 9000 | 0 | 0 | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-174 | TRC- Installation of new outfall at Tallman Island WWTP | CONSENT DECREE UPGRADING AND CONSTRUCTION | 400 | WP-0282 |  |  | A NEW 96" OUTFALL APPROXIMATELY 1000 FEET LONG, A NEW JUNCTION CHAMBER TO TIE THE NEW OUTFALL WITH THE OLD, A NEW BULKHEAD WHERE THE NEW OUTFALL PASSES THROUGH THE EXISTING, AND SUPPORT AND ARMORED COVER FOR THE NEW OUTFALL. | 2019 | 65078 | 0 | 0 | 0 | 8440 | 8440 | 0 | 42198 | 59078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-5 | TALLMAN ISLAND LANDSCAPING UPGRADE & MISC. SITE IMPROVEMENTS | PLANT UPGRADING AND RECONSTRUCTION | 407 | WP-0249 |  |  | NATIVE VEGETATION, INCREASED PARKING CAPACITY, INCORPORATION OF INTERIORLY LOCATED SIDEWALK ACCESS TO BUILDINGS, GENERAL SAFETY MEASURES, SITE BEAUTIFICATION, AND IMPROVED VEHICULAR CIRCULATION. THE WORK WILL SATISFY THE PUBLIC DESIGN COMMISSION NEEDS FOR SIGN OFF ON THE TI-3 CERTIFICATE OF OCCUPANCY | 2019 | 6000 | 540 | 0 | 0 | 10676 | 0 | 0 | 0 | 11216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-STAB | STABILIZATION OF THE TALLMANS' ISLAND WPCP | PLANT COMPONENT STABILIZATION | 407 | WP-0249 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | QUEENS | THE DESIGN FOR THE STABILIZATION OF THE TALLMAN'S ISLAND WPCP | 2019 | 496967 | 511607.34 | 4303 | 0 | 0 | 0 | 0 | 0 | 515910.34 | 14361.31 | 0 | 0 | 0 | 0 | 0 | 0 | 14361.31
20190425 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-251A | Queens CRS Steam Pipe Replacement from CRS to NYPD | GARAGES AND FACILITIES | 403 | S-0136 |  |  | ENGINEER'S ESTIMATE | 2019 | 2160 | 2179.57 | 207 | 0 | 0 | 0 | 0 | 0 | 2386.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-251E | QUEENS CRS AIR COMPRESSORS REPLACEMENT | GARAGES AND FACILITIES | 403 | S-0136 |  |  | AIR COMPRESSORS RUN VARIOUS TYPES OF EQUIPMENT AND FILL TIRES | 2019 | 130 | 0 | 0 | 130 | 0 | 0 | 0 | 0 | 130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-251F | QUEENS CRS FIFTH FLOOR SLAB SECTIONS REPLACEMENT | GARAGES AND FACILITIES | 403 | S-0136 |  |  | REPLACE SECTIONS OF SLAB | 2019 | 1650 | 3579.6 | 9747 | 366 | 0 | 0 | 0 | 0 | 13692.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-251G | QUEENS CRS Dynamometer Test Cell HVAC Replacement | GARAGES AND FACILITIES | 402 | S-0136 |  |  | DYNAMOMETER TEST CELL HVAC | 2019 | 558 | 471.27 | 448 | 0 | 0 | 0 | 0 | 0 | 919.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-251V | QUEENS CRS Elevator Reconstruction | GARAGES AND FACILITIES | 402 | S-0136 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | RECONSTRUCTION OF ELEVATORS | 2019 | 2000 | 3911.82 | 38 | 319 | 0 | 0 | 0 | 0 | 4268.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-264Q | Queens 6 Betts Ave Garage Roof Replacement | GARAGES AND FACILITIES | 406 | S-0136 |  |  | REPLACE ROOF | 2019 | 1226 | 1868.79 | 316 | 66 | 0 | 0 | 0 | 0 | 2250.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-332N | QUEENS 8/10/12 GARAGE REHAB | GARAGES AND FACILITIES | 408 410 412 | S-0136 |  |  | QUEENS 8/10/12 REHAB | 2019 | 23690 | 1387.15 | 0 | 1509 | 0 | 13913 | 0 | 0 | 16809.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-380A | Queens Flushing Ave Enforcement Garage Boiler Replacement | GARAGES AND FACILITIES | 400 | S-0136 |  |  | BOILER REPLACEMENT | 2019 | 225 | 0 | 225 | 0 | 0 | 0 | 0 | 0 | 225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-431 | QUEENS 1 GARAGE | GARAGES AND FACILITIES | 401 | S-0136 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | GARAGE CONSTRUCTION | 2019 | 150650 | 0 | 0 | 9671 | 12088 | 120881 | 0 | 0 | 142640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-442 | Queens Northborough Repair Shop Fire Alarm System Replacemen | GARAGES AND FACILITIES | 400 | S-0136 |  |  | REPLACE FIRE ALARM SYSTEM | 2019 | 808 | 136.67 | 1239 | 0 | 0 | 0 | 0 | 0 | 1375.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-445 | Queens 6 Betts Ave Garage Rehab | GARAGES AND FACILITIES | 406 | S-0136 |  |  | REHAB | 2019 | 26495 | 0 | 0 | 0 | 0 | 1801 | 3003 | 21691 | 26495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-464H | Queens Flushing Ave Enforcement Garage Roof Replacement | GARAGES AND FACILITIES | 400 | S-0136 |  |  | ROOF REPL | 2019 | 1848 | 0 | 205 | 912 | 0 | 0 | 0 | 0 | 1117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 827 | DEPARTMENT OF SANITATION | S216-402 | MARINE TRANSFER STATION AT NORTH SHORE | SOLID WASTE MANAGEMENT | 400 407 | S-0216 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES | NORTH SHORE MTS | RETROFITTING MARINE TRANSFER STATION AT NORTH SHORE | 2019 | 94214 | 201823.74 | -189 | 3769 | 0 | 0 | 0 | 0 | 205403.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 827 | DEPARTMENT OF SANITATION | SANDQ14EL | Hurricane Sandy Queens 14 Electrical Replacement | GARAGES AND FACILITIES | 414 | S-0136 |  |  | REPLACEMENT OF CONDUIT, RAISING OF EQUIPMENT ABOVE FLOOD PLAIN | 2019 | 3797 | 977.83 | 534 | 0 | 0 | 0 | 0 | 0 | 1511.83 | 2455.47 | 1001 | 0 | 0 | 0 | 0 | 0 | 3456.47
20190425 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HB107008Q | Protective Coating of 8 Bridges in Queens | BRIDGE PAINTING | 400 | HB-1070 |  | PROTECTIVE COATING OF 8 BRIDGES | PROTECTIVE COATING OF 8 BRIDGES IN QUEENS | 2019 | 9800 | 9060.3 | 0 | 630 | 1238 | 0 | 0 | 0 | 10928.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ1114 | HEMPSTEAD AVE BR/CIP 2231780 | FAIR BRIDGES | 413 | HB-1114 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | NA |  | 2019 | 24716 | 576 | 0 | 0 | 1365 | 0 | 6740 | 41531 | 50212 | 0 | 0 | 0 | 0 | 0 | 0 | 36237 | 36237
20190425 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ1115 | UNION TURNPIKE / CROSS ISLAND PKWY 2-23185-0 | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 413 | HB-1012 HB-1115 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | NA |  | 2019 | 9031 | 2593.02 | 833 | 467 | 0 | 7019 | 53990 | 0 | 64902.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ1137 | RECON ELLIOT AVE BRIDGE OVER QUEENS BLVD 2-24816-0 | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 406 | HB-1137 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | N/A |  | 2019 | 11529 | 1622.85 | 0 | 0 | 0 | 0 | 0 | 23163 | 24785.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ1203 | RECON ROOSEVELT AVE BR OVER VAN WYCK EXPWY QUEENS 2-240507 | FAIR BRIDGES | 407 | TF-0002 HB-1203 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | RECONS ROOSEVELT AVE BR OVER VAN WYCK EXPWY, QUEENS | RECONS ROOSEVELT AVE BR OVER VAN WYCK EXPWY, QUEENS | 2019 | 71248 | 34893.38 | 5838 | 5552 | 0 | 0 | 0 | 0 | 46283.38 | 59778.72 | 3554 | 0 | 0 | 0 | 0 | 0 | 63332.72
20190425 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ49AV | 49TH AVE OVER LIRR, AMT, CON NE (BIN2247290) | FAIR BRIDGES | 400 402 | HB-1012 HB-0431 |  | 49TH AVE OVER LIRR, AMT, CON NE (BIN2247290) | 49TH AVE OVER LIRR, AMT, CON NE (BIN2247290) | 2019 | 30460 | 11199 | 200 | 850 | 104525 | 0 | 0 | 0 | 116774 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ8019 | WOODHAVEN BLVD OVER ATLANTIC AVE | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 400 405 406 409 | HB-1070 |  |  | REBAH WOODHAVEN BLVD BIN 2248019 | 2019 | 37644 | 0 | 0 | 0 | 0 | 5293 | 0 | 61284 | 66577 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA23081 | ASTORIA BLVD EB/ 278I( BQE WEST LEG) BIN# 2230810 | FAIR BRIDGES | 400 | HB-1012 HB-0215 |  |  | ASTORIA BLVD EB/ 278I( BQE WEST LEG) BIN# 2230810 | 2019 | 29201 | 0 | 1244 | 1791 | 0 | 3369 | 23586 | 0 | 29990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA23176 | BCIP OVER DUTCH BROADWAY-115 AVE BIN 2231760 | FAIR BRIDGES | 400 | HB-1173 |  | BCIP OVER DUTCH BROADWAY-115 AVE BIN 2231760 | BCIP OVER DUTCH BROADWAY-115 AVE BIN 2231760 | 2019 | 24984 | 680.17 | 0 | 1756 | 23062 | 0 | 0 | 0 | 25498.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA24750 | METROPOLITAN AVE OVER CSX TRANSPORT | FAIR BRIDGES | 400 | HB-1141 |  | METROPOLITAN AVE OVER CSX TRANSPORT | METROPOLITAN AVE OVER CSX TRANSPORT | 2019 | 67102 | 7666.39 | 0 | 624 | 56463 | 3274 | 0 | 0 | 68027.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA24815 | WOODHAVEN BLVD/ QUEENS BLVD BIN# 2248159 | FAIR BRIDGES | 400 | HB-1012 HB-0215 |  |  | WOODHAVEN BLVD/ QUEENS BLVD BIN# 2248159 | 2019 | 40560 | 0 | 1177 | 2227 | 6147 | 30885 | 0 | 0 | 40436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA26614 | HEMPSTEAD AVE OVER BCIP RAMP NB BIN 2266149 | FAIR BRIDGES | 400 | HB-1012 HB-0215 |  | HEMPSTEAD AVE OVER BCIP RAMP NB BIN 2266149 | HEMPSTEAD AVE OVER BCIP RAMP NB BIN 2266149 | 2019 | 30911 | 0 | 0 | 0 | 1400 | 0 | 3751 | 26260 | 31411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQC064 | 678I SB TO BCIP EB/ACCESS RD FROM 678I 2-26616-0 | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 400 407 | HB-6622 TF-0502 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | ACCESS RD | ACCESS RD FROM 6781 | 2019 | 2201 | 3539.28 | 3178 | 13556 | 3564 | 0 | 0 | 0 | 23837.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQENB012 | Emergency Fender System Northern Blvd WB/EB | FAIR BRIDGES | 400 | HB-0215 |  | EMERGENCY FENDER SYSTEM NORTHERN BLVD WB/EB | EMERGENCY FENDER SYSTEM NORTHERN BLVD WB/EB | 2019 | 18100 | 1122.86 | 983 | 16044 | 0 | 0 | 0 | 0 | 18149.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR18C | Citywide Milling - Queens | PRIMARY STREET RESURFACING | 400 | HW-0002Q |  | CITYWIDE MILLING - QUEENS | CITYWIDE MILLING - QUEENS | 2019 | 8111 | 7090 | 6749 | 0 | 0 | 0 | 0 | 0 | 13839 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR19B | Citywide Milling - Queens | PRIMARY STREET RESURFACING | 400 | HW-0002Q | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CITYWIDE MILLING- QUEENS | 2019 | 8000 | 0 | 4455 | 6191 | 0 | 0 | 0 | 0 | 10646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWCOINFAC | METER PROCESSING FACILITY REHABILITATION | FACILITY RECONSTRUCTION | 400 | HW-0003 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | COIN COLLECTION FACILITY REHABILITATION | COIN COLLECTION FACILITY REHABILITATION | 2019 | 5750 | 63.38 | 0 | 0 | 0 | 6119 | 0 | 612 | 6794.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD103100 | RECON OF MYRTLE AVE / UNION TURNPIKE ENTRANCE TO FOREST PK | PRIMARY STREET RECONSTRUCTION | 405 | HW-D103 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | RECON OF MYRTLE AVE / UNION TURNPIKE ENTRANCE TO FOREST PK | 2019 | 120 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10312 | Safety Improvements at St. Margaret's School | PRIMARY STREET RECONSTRUCTION | 400 405 | HW-D103 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | SAFETY IMPROVEMENTS AT ST. MARGARET'S SCHOOL | SAFETY IMPROVEMENTS AT ST. MARGARET'S SCHOOL | 2019 | 300 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10323 | Upgrades within the Bayside BID | INSTALLATION OF LAMPPOSTS AND LUMINAIRES | 400 | TF-D503 TF-Q503 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | UPGRADES WITHIN THE BAYSIDE BID | UPGRADES WITHIN THE BAYSIDE BID | 2019 | 350 | 0 | 770 | 0 | 0 | 0 | 0 | 0 | 770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10324 | Parsons Blvd & 84th Ave & Hoover Ave Ped Safety Improvements | PRIMARY STREET RECONSTRUCTION | 400 | HW-D103 HW-Q001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | PARSONS BLVD & 84TH AVE & HOOVER AVE PEDESTRIAN SAFETY IMPROVEMENTS | PARSONS BLVD & 84TH AVE & HOOVER AVE PEDESTRIAN SAFETY IMPROVEMENTS | 2019 | 300 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10326 | Long Island City Bikeway Improvements | PRIMARY STREET RECONSTRUCTION | 400 | HW-D103 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | LONG ISLAND CITY BIKEWAY IMPROVEMENTS | LONG ISLAND CITY BIKEWAY IMPROVEMENTS | 2019 | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10327 | Dutch Kills Pedestrian Safety Project | PRIMARY STREET RECONSTRUCTION | 400 | HW-0001Q |  | DUTCH KILLS PEDESTRIAN SAFETY PROJECT | DUTCH KILLS PEDESTRIAN SAFETY PROJECT | 2019 | 2300 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10328 | A Safer Intersection at 71st Avenue and Austin Street | PRIMARY STREET RECONSTRUCTION | 400 | HW-D103 |  | A SAFER INTERSECTION AT 71ST AVENUE AND AUSTIN STREET | A SAFER INTERSECTION AT 71ST AVENUE AND AUSTIN STREET | 2019 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10330 | Median and Street Reconstruction in Broad Channel | PRIMARY STREET RECONSTRUCTION | 400 | HW-0001Q | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | MEDIAN AND STREET RECONSTRUCTION IN BROAD CHANNEL | MEDIAN AND STREET RECONSTRUCTION IN BROAD CHANNEL | 2019 | 4050 | 0 | 0 | 0 | 0 | 0 | 3750 | 0 | 3750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10332 | Reconstruct Curbs along median of Rockaway Freeway | PRIMARY STREET RECONSTRUCTION | 400 | HW-D103 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | RECONSTRUCT CURBS ALONG MEDIAN OF ROCKAWAY FREEWAY. | RECONSTRUCT CURBS ALONG MEDIAN OF ROCKAWAY FREEWAY | 2019 | 1000 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWDMM011 | Union Street Beautification | PRIMARY STREET RECONSTRUCTION | 400 407 | HW-D103 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | UNION STREET BEATIFICATION | UNION STREET BEATIFICATION | 2019 | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWHARPADM | Harper Street Administration Building Reconstruction | FACILITY RECONSTRUCTION | 400 | HW-0003 |  |  | HARPER STREET ADMINISTRATION BUILDING RECONSTRUCTION | 2019 | 40000 | 0 | 0 | 0 | 2000 | 0 | 0 | 45180 | 47180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWPEDSF4B | Multi-Site Pedestrian Safety - Phase 4B -- Hoyt Avenue | PRIMARY STREET RECONSTRUCTION | 400 | HW-0001Q | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | MULTI-SITE PEDESTRIAN SAFETY - PHASE 4B -- HOYT AVENUE | 2019 | 1152 | 0 | 0 | 1152 | 0 | 0 | 0 | 0 | 1152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ005-01 | Median Updates at Junction/82nd & Ditmars/78-82 | PRIMARY STREET RECONSTRUCTION | 400 | HW-Q005 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | MEDIAN UPDATES AT JUNCTION/82ND & DITMARS/78-82 | MEDIAN UPDATES AT JUNCTION/82ND & DITMARS/78-82 | 2019 | 4000 | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ100SBB | Woodhaven Blvd SBS Phase B | TRAFFIC WORK IN CONJUNCTION WITH HIGHWAY RECONSTRUCTION | 400 | HW-1684 |  | WOODHAVEN BLVD SBS PHASE B | WOODHAVEN BLVD SBS PHASE B | 2019 | 0 | 0 | 3610 | 0 | 0 | 42015 | 0 | 0 | 45625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ100SBS | Woodhaven Blvd SBS | TRAFFIC WORK IN CONJUNCTION WITH HIGHWAY RECONSTRUCTION | 400 405 406 409 | HW-1684 HW-D103 HW-0001Q | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | WOODHAVEN BLVD QUEENS | WOODHAVEN BLVD SBS | 2019 | 3000 | 183.9 | 0 | 0 | 0 | 0 | 12174 | 0 | 12357.9 | 0 | 0 | 0 | 0 | 0 | 112474 | 0 | 112474
20190425 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1190 | Reconstruction of Queens Blvd | PRIMARY STREET RECONSTRUCTION | 400 | HW-0001Q |  | RECONSTRUCTION OF QUEENS BLVD | RECONSTRUCTION OF QUEENS BLVD | 2019 | 98781 | 1891 | 0 | 0 | 0 | 0 | 18963 | 0 | 20854 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1192 | Jewel Ave | PRIMARY STREET RECONSTRUCTION | 400 | HW-0001Q | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | JEWEL AVE | JEWEL AVE | 2019 | 1500 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1196 | Cloudburst Project - St Albans | PRIMARY STREET RECONSTRUCTION | 400 | HW-0001Q | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CLOUDBURST PROJECT - ST ALBANS | 2019 | 31758 | 0 | 0 | 0 | 0 | 0 | 31758 | 0 | 31758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1197 | Astoria Boulevard Safety Improvements | PRIMARY STREET RECONSTRUCTION | 400 | HW-0001Q |  | ASTORIA BOULEVARD SAFETY IMPROVEMENTS | ASTORIA BOULEVARD SAFETY IMPROVEMENTS | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 11433 | 0 | 11433 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ788 | LIC/Hunters Point Area-wide Reconstruction | PRIMARY STREET RECONSTRUCTION | 402 | TF-0502 TF-0002 HW-0200 HW-0788 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | AREA BOUNDED BY 44TH DRIVE, JACKSON AVENUE, BORDEN AVENUE, AND U S PIERHEAD LINE | 21 & 11 STS: 44 DR - JACKSON AVE; VERNON BLVD: 44 DR - BORDEN AVE; 5THBORDEN AVE - POINT 250' +/- N/O 46 AVE; 45 AVE & 45 RD: JACKSON AVE -BLVD; 46 AVE & 46 RD: 5TH ST - JACKSON AVE; 47 AVE: JACKSON AVE - POIN+/- W/O 5TH ST; 47 RD: JACKSON AVE - POINT 650' +/- W/O 5TH ST; 48 AVEJACKSON AVE - POINT 700' +/- W/O 5TH ST; 49 AVE: JACKSON AVE - POINT 4W/O 5TH ST; 50 AVE: JACKSON AVE - 2ND ST; 51 AVE: VERNON BLVD - 2ND ST2ND ST: BORDEN AVE - 50TH AVE; PEARSON ST:THE EXISTING ROADWAY SHALL BE RECONSTRUCTED/ROADWAY RECONSTRUCTION SHAINCLUDE NEW CURBS, SIDEWALKS AND REQUIRED UTILITY REPLACEMENT/THERE ARAMENITIES/THIS PROJECT IS CITY FUNDED/THIS PROJECT IS IN CONJUNCTION W | 2019 | 35743 | 134 | 0 | 0 | 0 | 0 | 0 | 44753 | 44887 | 0 | 0 | 0 | 0 | 0 | 0 | 1920 | 1920
20190425 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ789 | THOMSON AVE. SAFETY IMPROVEMENTS -- LAGUARDIA COMM. COLLEGE | PRIMARY STREET RECONSTRUCTION | 400 | HW-0001Q |  | THOMSON AVE. SAFETY IMPROVEMENTS -- LAGUARDIA COMMUNITY COLLEGE | THOMSON AVE. SAFETY IMPROVEMENTS -- LAGUARDIA COMMUNITY COLLEGE | 2019 | 17000 | 0 | 0 | 0 | 0 | 0 | 22147 | 0 | 22147 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ850 | SEQ PS 123 School Safety, Plus (SE-850) | PRIMARY STREET RECONSTRUCTION | 400 | HW-0001Q |  | SEQ PS 123 SCHOOL SAFETY, PLUS | SEQ PS 123 SCHOOL SAFETY, PLUS | 2019 | 0 | 0 | 0 | 725 | 0 | 0 | 0 | 0 | 725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF031C | Glendale Yard Pre-Engineered Shed | FACILITY RECONSTRUCTION |  | HW-0003 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | GLENDALE YARD, QUEENS | REBUILD EXISTING GARAGE SPACE | 2019 | 348 | 97.57 | 0 | 0 | 0 | 250 | 0 | 0 | 347.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF033 | 28-11 QPN 7TH FL REHABILITATION | FACILITY RECONSTRUCTION | 400 402 | HW-0003 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | QUEENS | COLLEGE POINT WINDOWS | 2019 | 3347 | 0 | 0 | 7320 | 8335 | 0 | 0 | 0 | 15655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF041 | QUEENS SAFETY CITY CONSTRUCTION 2 | FACILITY RECONSTRUCTION | 400 | HW-0003 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | QUEENS SAFTERY CITY CONSTRUCTION 2 | QUEENS SAFETY CITY CONSTRUCTION 2 | 2019 | 7638 | 0 | 0 | 700 | 6938 | 0 | 0 | 0 | 7638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF12ST | 38-21 12th Street Rehabilitation | FACILITY RECONSTRUCTION | 400 | HW-0003 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | 38-21 12TH STREET REHABILITATION | 2019 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF2002V | GLENDALE YARD TRAILERS | FACILITY RECONSTRUCTION | 400 406 | HW-0003 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | SYBILLA STREET FACILITY RENOVATION | SYBILLA STREET FACILITY RENOVATION | 2019 | 5049 | 1927.53 | 0 | 0 | 0 | 758 | 0 | 0 | 2685.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQMASPET | Maspeth Climate Control and Air Quality Improvements | FACILITY RECONSTRUCTION | 400 402 | HW-0003 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | 58-50 57TH ROAD | MASPETH CLIMATE CONTROL AND AIR QUALITY IMPROVEMENTS | 2019 | 5301 | 0 | 0 | 0 | 0 | 35949 | 0 | 8106 | 44055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | JAMASTPLZ | Greater Jamaica Dev Corp Station Plaza Acquisition | COMMERCIAL DEVELOPMENT | 400 412 | ED-0075 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | GJDC STATION PLAZA ACQUISITION | 2019 | 5820 | 2365.64 | 1298 | 0 | 0 | 0 | 0 | 0 | 3663.64 | 7017.43 | 7566 | 0 | 0 | 0 | 0 | 0 | 14583.43
20190425 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | QUEENSCJW | QUEENS COMM CORRIDOR-INTERSECTION OF JAMAICA & WOODHAVEN | MISCELLANEOUS | 400 | ED-Q384 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | QUEENS COMMERCIAL CORRIDOR AT INTERSECTION OF JAMAICA AVE & WOODHAVEN--INSTALLATION OF LIGHTING BENEATH THE SUBWAY TRACKS ALONG JAMAICA AVENUE AT THE INTERSECTION OF JAMAICA AVENUE AND WOODHAVEN BLVD. | 2019 | 250 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | QUEENSCWH | QUEENS COMMERCIAL CORRIDOR AT WOODHAVEN | MISCELLANEOUS | 400 | ED-Q384 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | QUEENS COMMERCIAL CORRIDOR AT WOODHAVEN--GREEN STREET WITH TREES AND PLANTINGS AT THE INTERSECTION OF JAMAICA AVENUE AND WOODHAVEN BLVD. | 2019 | 75 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | SANDHW11B | Reconstruction of Beach Channel Drive -- Phase B | PRIMARY STREET RECONSTRUCTION | 400 | HW-0001Q |  | RECONSTRUCTION OF BEACH CHANNEL DRIVE -- PHASE B | RECONSTRUCTION OF BEACH CHANNEL DRIVE -- PHASE B | 2019 | 36343 | 0 | 0 | 0 | 0 | 38969 | 0 | 0 | 38969 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | SEQPGRD4 | Southeast Queens Priority Grids 31-40 | PRIMARY STREET RECONSTRUCTION | 400 | HW-0001Q |  |  | SOUTHEAST QUEENS PRIORITY GRIDS 31-40 | 2019 | 17695 | 0 | 0 | 0 | 0 | 0 | 17695 | 0 | 17695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | SEQPGRD5 | Southeast Queens Priority Grids 41-50 | PRIMARY STREET RECONSTRUCTION | 400 | HW-0001Q |  |  | SOUTHEAST QUEENS PRIORITY GRIDS 41-50 | 2019 | 17784 | 0 | 0 | 0 | 0 | 0 | 0 | 17784 | 17784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF072017 | Extension of lighting project Woodhaven | INSTALLATION OF LAMPPOSTS AND LUMINAIRES | 400 | TF-Q503 |  |  | EXTENSION OF EXISTNG LIGHTING PROJECT (841 QUEENSCJW) TO INCLUDE JAMAICA AVENUE FROM 102 STREET TO LEFFERTS BLVD | 2019 | 500 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF18-2020 | STEINWAY #1&2 MUNICIPAL PARKING FIELDS | Parking Meters, Lots, and Garages | 400 401 | TF-0018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | RECON OF PARKING FIELDS | 2019 | 950 | 0 | 0 | 0 | 0 | 182 | 0 | 0 | 182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF50308 | St lg Poles:Cross Bay Blvd ,156th to 165th Ave -S4319,MA122. | INSTALLATION OF LAMPPOSTS AND LUMINAIRES | 400 | TF-0503 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | REPLACE/INSTALL STREET LIGHTING POLES: CROSS BAY BLVD. FROM 156TH TO 165TH AVENUES | 2019 | 685 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 685 | 0 | 0 | 0 | 0 | 685
20190425 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF50310 | Rlp lg brackets 102nd St and 159 Ave, -XMA123.30A | INSTALLATION OF LAMPPOSTS AND LUMINAIRES | 400 | TF-0503 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | 102ND STREET (FROM 160TH TO 159TH AVENUE) AND 159TH AVENUE (FROM 102ND TO 103RD STREET) REPLACEMENT OF LIGHTING BRACKETS ON EXISTING WOOD POLES | 2019 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 36
20190425 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF50312 | St lg repl Union Turnpike:Main St to Utopia Pkwy MA2179.30 | INSTALLATION OF LAMPPOSTS AND LUMINAIRES | 400 | TF-0503 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | STREET LIGHTING REPLACEMENT: UNION TURNPIKE: MAIN STREET TO UTOPIA PARKWAY | 2019 | 660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 660 | 0 | 0 | 0 | 0 | 660
20190425 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TFD503-04 | ROOSEVELT AVENUE STREET LIGHTING | INSTALLATION OF LAMPPOSTS AND LUMINAIRES |  | TF-D503 TF-0503 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | ROOSEVELT AVENUE STREET LIGHTING | ROOSEVELT AVENUE STREET LIGHTING | 2019 | 500 | 387.43 | 0 | 173 | 0 | 0 | 0 | 0 | 560.43 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 500
20190425 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TFD503Q30 | Ugrade lighting on Roosevelt Ave betw 82nd and 90th Streets | INSTALLATION OF LAMPPOSTS AND LUMINAIRES | 400 | TF-D503 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | LIGHTING UPGRADE | 2019 | 350 | 0 | 350 | 0 | 0 | 0 | 0 | 0 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TFD503Q32 | MYRTLE AVE DECORATIVE LIGHTING QUEENS | INSTALLATION OF LAMPPOSTS AND LUMINAIRES | 400 | TF-D503 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | MYRTLE AVE DECRATIVE LIGHTING QUEENS | 2019 | 725 | 0 | 725 | 0 | 0 | 0 | 0 | 0 | 725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TFD503Q33 | Lght along Merrick bt. Hook Creek Blvd &Springfield Blvd | INSTALLATION OF LAMPPOSTS AND LUMINAIRES | 400 | TF-D503 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | DECORATIVE LIGHTS | 2019 | 1188 | 0 | 1188 | 0 | 0 | 0 | 0 | 0 | 1188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TFWHSBSRT | SBS - Real Time Totem System | SIGNAL INSTALLATION AND COMPUTERIZATION | 400 | TF-0001 |  | WOODHAVEN SBS - REAL TIME TOTEM SIGNS | WOODHAVEN SBS - REAL TIME TOTEM SIGNS | 2019 | 517 | 1521.41 | 0 | 0 | 0 | 186 | 0 | 0 | 1707.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | WHAMBEACH | HAMILTON BEACH BULKHEADS AND ROADWAYS | PRIMARY STREET RECONSTRUCTION | 410 | HW-D103 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | HAMILTON BEACH AREA BULKHEADS AND ROADWAYS | HAMILTON BEACH AREA BULKHEADS AND ROADWAYS | 2019 | 597 | 0 | 0 | 0 | 0 | 0 | 0 | 597 | 597 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | GQGIKISE | GI - CONS OF PARKLAND RETROFITS IN KISSENA PK | GREEN INFRASTRUCTURE PROGRAM | 400 | WP-0169 P-0822 |  | KISSENA PK AND KISSENA CORRIDOR, QUEENS | GI - CONS OF PARKLAND RETROFITS IN KISSENA PK AND KISSENA CORRIDOR | 2019 | 0 | 0 | 1338 | 0 | 0 | 60 | 0 | 0 | 1398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | GQQNGI-01 | GI - DSGN & CONS OF PARKLAND RETROFITS IN QUEENS | GREEN INFRASTRUCTURE PROGRAM | 400 | WP-0169 |  |  | GI - DSGN & CONS OF PARKLAND RETROFITS IN QUEENS | 2019 | 1861 | 239 | 1383 | 0 | 0 | 0 | 0 | 0 | 1622 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | NDF-NMKE | NDF - New Park & Comfort Station at Nameoke Avenue | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | ED-0384 |  |  | NEIGHBORHOOD DEVELOPMENT FUND - DSNY SITE, NEW PARK AT NAMEOKE STREET, BOROUGH OF QUEENS | 2019 | 10300 | 0 | 831 | 9469 | 0 | 0 | 0 | 0 | 10300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | NDF-RDFR | NDF - Redfern Playground | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | ED-0384 |  |  | NEIGHBORHOOD DEVELOPMENT FUND - REDFERN PLAYGROUND, BOROUGH OF QUEENS | 2019 | 9300 | 0 | 88 | 427 | 8785 | 0 | 0 | 0 | 9300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-218MPNC | MARINE PARK- SALT MARSH CTR B057-115M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | P-1018 P-0506 |  | BROOKLYN | MARINE PARK- SALT MARSH CTR | 2019 | 777 | 451.3 | -159 | 1649 | 326 | 0 | 0 | 0 | 2267.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400LNCP | Challenge Playground R/C Q346-118M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 411 | P-Q245 P-D019 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | CHALLENGE PLAYGROUND: UPGRADE PLAYGROUND | CHALLENGE PLAYGROUND: UPGRADE PLAYGROUND | 2019 | 4165 | 42 | 83 | 0 | 0 | 2992 | 0 | 0 | 3117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZO17 | Queens Zoo - Aviary Mesh Replacement | ZOOS | 400 | P-D019 |  |  | QUEENS ZOO | 2019 | 400 | 0 | 0 | 0 | 0 | 0 | 400 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZO18 | Wildlife Conservation Society Farm Fence | ZOOS | 400 | P-D019 P-0887 |  |  | WILDLIFE CONSERVATION SOCIETY FARM FENCE AND SHED REPLACEMENT | 2019 | 600 | 597.72 | 0 | 256 | 0 | 0 | 0 | 0 | 853.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZO20 | Queens Zoo - Concessions Roof Replacement | ZOOS | 400 | P-0887 |  | QUEENS ZOO - CONCESSIONS ROOF REPLACEMENT | QUEENS ZOO - CONCESSIONS ROOF REPLACEMENT | 2019 | 540 | 0 | 0 | 100 | 440 | 0 | 0 | 0 | 540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZO21 | Queens Zoo - Animal Commis. Refrigerator | ZOOS | 400 | P-0887 |  | QUEENS ZOO - ANIMAL COMMIS. REFRIGERATOR | QUEENS ZOO - ANIMAL COMMIS. REFRIGERATOR | 2019 | 190 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZO22 | Queens Zoo - Bear ExhibitGuest Railing/Bench replacement | ZOOS | 400 | P-0887 |  | QUEENS ZOO - BEAR EXHIBITGUEST RAILING/BENCH REPLACEMENT | QUEENS ZOO - BEAR EXHIBITGUEST RAILING/BENCH REPLACEMENT | 2019 | 83 | 0 | 0 | 0 | 0 | 0 | 0 | 83 | 83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZO23 | Queens Zoo - sh/Eagle Boardwalk/Dance Floor Replacement | ZOOS | 400 | P-0887 |  | QUEENS ZOO - SH/EAGLE BOARDWALK/DANCE FLOOR REPLACEMENT | QUEENS ZOO - SH/EAGLE BOARDWALK/DANCE FLOOR REPLACEMENT | 2019 | 200 | 0 | 20 | 180 | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZOO4 | Queens Zoo - Admnistration Building - roof replacement | ZOOS | 400 | P-0887 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | QUEENS ZOO | REPLACEMENT OF THE ROOF AT THE QUEENS ZOO ADMINISTRATION BUILDING | 2019 | 110 | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZOO8 | Queens Zoo - Education Classroom initiative | ZOOS | 400 | P-D019 |  | QUEENS ZOO | QUEENS ZOO EDUCATION CLASSROOM INITIATIVE -DESIGN | 2019 | 4308 | 381.69 | 0 | 4091 | 0 | 0 | 0 | 0 | 4472.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401APFS | Astoria Pool Filtration System | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-0990 |  | ASTORIA POOL FILTRATION SYSTEM | ASTORIA POOL FILTRATION SYSTEM | 2019 | 18262 | 0 | 1279 | 0 | 0 | 16983 | 0 | 0 | 18262 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401APPS | ASTORIA PK POOL RC Q004-113MA | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 401 | P-0245Q | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ASTORIA POOL RC AMPHITHEATER AND BATHHOUSE | 2019 | 4300 | 5718.75 | 0 | 0 | 0 | 442 | 0 | 0 | 6160.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401ASQP | ATHENS SQUARE PK RC OF PLGDS IN PS17 Q436-107M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 401 | P-D019 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | REDESIGN EXISTING PLAYGROUND, INSTALL NEW EQUIPMENT, FENCING AND LOCKING PARK | 2019 | 1500 | 1637.41 | 0 | 0 | 0 | 0 | 80 | 0 | 1717.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401BSNS | ASTORIA PK- DRAINAGE AT THE TENNIS COURT Q004-102MA1 | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 401 | P-D019 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | QUEENS | REPAIR CATCH BASINS AT FOUR TENNIS COURTS IN ASTORIA PARK | 2019 | 666 | 549.67 | 0 | 0 | 0 | 0 | 89 | 0 | 638.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401DKLL | Dutch Kills Playground R/C Q218-116M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 401 | P-0245Q P-D019 |  |  | DUTCH KILLS PLAYGROUND RECONSTRUCTION | 2019 | 3750 | 3643.58 | 92 | 0 | 0 | 214 | 0 | 0 | 3949.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401HCSW | Hallets Cove Seawall | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-0245Q |  |  | HALLETS COVE SEAWALL | 2019 | 3491 | 291 | 0 | 3200 | 0 | 0 | 0 | 0 | 3491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401JOEM | Joe Michael's Mile Path and Lighting Q135-214M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 411 | P-Q245 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | JOE MICHAELS MILE PATHS AND LIGHTING | 2019 | 2040 | 1506.8 | 91 | 0 | 0 | 257 | 0 | 0 | 1854.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401QBHB | Queensbridge Baby Park Handball Courts | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D019 |  |  | QUEENSBRIDGE BABY PARK UPGRADE 6 HANDBALL COURT WALLS, BOROUGH OF QUEENS | 2019 | 1422 | 0 | 0 | 0 | 0 | 1029 | 89 | 0 | 1118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401QSE2 | QUEENSBRIDGE PARK FIELDHOUSE CONS. Q104-114M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 401 | P-0245Q | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | DEMOLISH OLD C/S AND CONSTRUCT NEW STATION/FIELDHOUSE | 2019 | 2954 | 5951.56 | 236 | 0 | 0 | 650 | 0 | 0 | 6837.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401RAV2 | Ravenswood Playground R/C Q333-118M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-Q245 P-D019 |  |  | RAVENSWOOD PLAYGROUND AND PLAY AREA IMPROVEMENTS | 2019 | 2760 | 100 | 122 | 0 | 6378 | 0 | 0 | 0 | 6600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401SMST | St. Michael's Playground Synthetic Turf Field R/C | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 401 | P-0510 |  |  | ST. MICHAEL'S PLAYGROUND SYNTHETIC TURF FIELD RECONSTRUCTION, BOROUGHOF QUEENS | 2019 | 5825 | 0 | 385 | 0 | 0 | 4482 | 433 | 0 | 5300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401SOC2 | Socrates Sculpture Park Building Expansion | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 401 | P-Q245 P-D019 |  |  | SOCRATES SCULPTURE PARK BUILDING EXPANSION | 2019 | 720 | 282 | 0 | 0 | 0 | 4235 | 0 | 0 | 4517 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401SOC3 | SOCRATES SCULPTURE PARK -REPAIR TO SEAWALL | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-Q245 |  |  | SOCRATES SCULPTURE PARK -REPAIR TO SEAWALL | 2019 | 750 | 0 | 62 | 0 | 0 | 633 | 55 | 0 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401TBDR | Triborough Bridge Plgd C Dog Run & Bball Court Q066-116M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 401 | P-D019 |  |  | CONSTRUCTION/RENOVATION OF DOG RUN AND RECONSTRUCTION OF A BASKETBALLCOURT INTRIBOROUGH BRIDGE PLAYGROUND C | 2019 | 1000 | 1270.58 | 0 | 0 | 0 | 92 | 0 | 0 | 1362.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401WFF | Whitey Ford Field | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-0501 PU-0200 |  |  | WHITEY FORD FIELD | 2019 | 1054 | 0 | 82 | 0 | 0 | 225 | 747 | 0 | 1054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401WFF1 | WHITEY FORD FIELD: R/C OF BASEBALL FIELD Q215-118M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 401 | P-Q245 P-D019 |  | WHITEY FORD FIELD: RECONSTRUCTION OF BASEBALL FIELD | WHITEY FORD FIELD: RECONSTRUCTION OF BASEBALL FIELD | 2019 | 3228 | 143.4 | 0 | 0 | 0 | 1992 | 0 | 0 | 2135.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-402DBOY | Doughboy Plaza Park Seating Area R/C Q031A-118M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D019 |  |  | RECONSTRUCTION OF THE SEATING AREA ADJACENT TO DOUGHBOY MONUMENT, AT DOUGHBOY PLAZA PARK, BOROUGH OF QUEENS | 2019 | 1996 | 200 | 0 | 1620 | 0 | 0 | 0 | 0 | 1820 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-402HART | Hart Playground R/C Q067-117M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 407 | P-D019 P-Q245 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | HART PLGD PLAY EQUIPMENT AND SPRAY SHOWER | 2019 | 600 | 284 | 27 | 0 | 0 | 3173 | 0 | 0 | 3484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4031272 | P. S. 127 EAST ELMHURST PLGD PHASE II Q373-112MA2 | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 499 | P-D019 P-0245Q | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | QUEENS | 2/14/18 CP 65757 CL = $1690K...FY19 EXEC ROLL $1289K PD019 & $390K P0245Q TO FY19...FY'19 TRF $249K ( P 1018) & CHANGED TO P 0245Q FR P-6517CBF...FY'19 TR $20K ( P 0245Q) TO P-6517CBF...1/29/19 $2K P0245Q FY OFFSET W/ P-405EVER FY19 TO FY20...2/1/19 $61K P0245Q FY OFFSET W/ P-415FMC2 FY19 TO FY20... | 2019 | 1300 | 535.28 | 1814 | 94 | 0 | 0 | 0 | 0 | 2443.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-403NORT | Northern Playground Synthetic Field Upgrade | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D019 |  |  | UPGRADE AND RENOVATE SYNTHETIC FIELD AT NORTHERN PLAYGROUND | 2019 | 2328 | 24 | 0 | 0 | 0 | 1750 | 0 | 0 | 1774 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-403TPP4 | Travers Park and Staunton Play Field R/C QG-714M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 403 | HW-1684 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | QUEENS | MULTI USE ASPHALT PLAY FIELD RC AND REDESIGN. | 2019 | 3664 | 7661.32 | 99 | 496 | 0 | 0 | 0 | 0 | 8256.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-403TTOT | Travers Park Tot Lot R/C Q303-117M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-Q245 |  |  | RECONSTRUCTION OF TRAVERS PARK TOT LOT | 2019 | 2000 | 250 | 1818 | 0 | 182 | 0 | 0 | 0 | 2250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404CCPS | Moore Homestead Playground R/C Q361-115M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 404 | P-Q245 P-1018 P-D019 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | C.C, MOORE PLGD & PRE-SCHOOL RC | 2019 | 2160 | 584.67 | 4385 | 87 | 213 | 0 | 0 | 0 | 5269.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404CGSD | Corona Golf Playground Sidewalks R/C | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D019 |  |  | CORONA GOLF PLAYGROUND RENOVATE INTERIOR SIDEWALKS, BOROUGH OF QUEENS | 2019 | 160 | 0 | 0 | 160 | 0 | 0 | 0 | 0 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404CROW | Crowley Playground R/C | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 404 | P-Q245 P-D019 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CROWLEY PLAYGROUND RECONSTRUCTION | 2019 | 300 | 0 | 0 | 700 | 0 | 0 | 0 | 2820 | 3520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404NTPG | Newtown Playground Paths & Plantings R/C Q041-116M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 404 | P-D019 P-0245Q |  |  | ENHANCEMENT OF PASSIVE LAWN AREA, INSTALLATION OF NEW WALKWAYS, DECORATIVE PAVERS, NEW BENCHES AND PLANTINGS, CREATIVE NEW ENTRY, AND REPAIRING RETAINING WALL IN NEWTOWN PLAYGROUND | 2019 | 1400 | 1505.09 | 0 | 0 | 132 | 0 | 0 | 0 | 1637.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404PATF | Park of the Americas Renovation | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D019 |  |  | PARK OF THE AMERICAS (LINDEN PARK) RENOVATION, BOROUGH OF QUEENS | 2019 | 1200 | 0 | 0 | 0 | 0 | 1200 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404PKAM | PARK OF THE AMERICAS BATHROOM IMPROVEMENTS RC Q026 | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D019 |  |  | PARK OF THE AMERICAS BATHROOM IMPROVEMENTS RC | 2019 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404WFMP | William F. Moore Park Renovation | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D019 |  |  | WILLIAM F. MOORE PARK RENOVATION OF PARK, BOROUGH OF QUEENS | 2019 | 700 | 0 | 0 | 0 | 0 | 700 | 0 | 0 | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405EGPK | EVERGREEN PARK (TOT PLGD RC) Q302-112M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 405 | P-D019 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | QUEENS | EVERGREEN PARK (TOT PLGD RC) | 2019 | 1000 | 1396.3 | 0 | 0 | 0 | 62 | 0 | 0 | 1458.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405EVE2 | Evergreen Park R/C Phase II | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 405 | P-D019 P-0938 |  |  | PHASE II OF THE RECONSTRUCTION OF EVERGREEN PARK, BOROUGH OF QUEENS | 2019 | 2100 | 0 | 0 | 0 | 0 | 0 | 0 | 2100 | 2100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405EVER | Evergreen Park - R/C of Playground Q302-116M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 405 | P-0245Q |  |  | EVERGREEN PARK | 2019 | 2400 | 2394.09 | 2 | 0 | 0 | 203 | 0 | 0 | 2599.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405FPCS | FRONTERA PK C/S Q360-104MA2/404M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 405 | P-D019 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | LONG ISLAND EXPRESSWAY, 69TH ST., 58TH AVENUE, QUEENS | FRONTERA PARK COMFORT STATION | 2019 | 716 | 780.78 | 0 | 0 | 0 | 0 | 85 | 0 | 865.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405HPRR | Highland Park Ridgewood Reservoir Site Restoration | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-0896 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | SITE RESTORATION AND IMPROVEMENTS AT THE RIDGEWOOD RESERVOIR IN HIGHLAND PARK | 2019 | 4771 | 100 | 0 | 0 | 0 | 0 | 0 | 1219 | 1319 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405JP75 | JUNIPER PARK - 75TH STREET PLGD Q102-108M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 405 | P-D019 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | QUEENS | JUNIPER PARK 75TH ST. PLGD | 2019 | 750 | 936.47 | 0 | 0 | 0 | 0 | 36 | 0 | 972.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405JPSS | Juniper Valley Park Spray Shower R/C Q102-117M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 405 | P-Q245 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | JUNIPER VALLEY PARK: UPGRADES TO SPRAY SHOWERS | 2019 | 2000 | 150 | 1449 | 0 | 0 | 551 | 0 | 0 | 2150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405JPTK | Juniper Valley Park Track & Syn. Turf Field R/C Q102-118M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | P-D019 |  |  | JUNIPER VALLEY PARK TRACK | 2019 | 2500 | 241 | 0 | 4190 | 419 | 0 | 0 | 0 | 4850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405JVBB | Juniper Valley Park Baseball Fields | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D019 |  |  | JUNIPER VALLEY PARK BASEBALL FIELDS, BOROUGH OF QUEENS | 2019 | 2864 | 0 | 0 | 0 | 0 | 0 | 0 | 2250 | 2250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405MPST | Frank Principe Park (Maurice Pk) Synthetic Fields Q131-115M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 405 | P-D019 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | MAURICE AVENUE, QUEENS | MAURICE PARK SYNTHETIC FIELD Q131 | 2019 | 2050 | 5293.28 | 116 | 0 | 0 | 1549 | 0 | 0 | 6958.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405RRGH | Ridgewood Reservoir Gatehouse Rehab | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-0896 |  |  | GATEHOUSE REHAB AT RIDGEWOOD RESERVOIR, IN HIGHLAND PARK, BOROUGH OF QUEENS | 2019 | 7228 | 150 | 0 | 0 | 4876 | 424 | 0 | 0 | 5450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405RRIV | Ridgewood Reservoir Invasive Removals | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-0896 |  |  | INVASIVE REMOVALS AT RIDGEWOOD RESERVOIR, IN HIGHLAND PARK, BOROUGH OF QUEENS | 2019 | 3250 | 0 | 0 | 0 | 0 | 3250 | 0 | 0 | 3250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405STR2 | Starr Playground R/C Phase II | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 405 | P-D019 |  |  | PHASE II OF THE RECONSTRUCTION OF STARR PLAYGROUND, BOROUGH OF QUEENS | 2019 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405STRR | Starr Playground MPPA R/C Q291-118M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D019 P-Q245 |  |  | STARR PLAYGROUND - UPGRADES | 2019 | 2500 | 277.41 | 0 | 0 | 2082 | 181 | 0 | 0 | 2540.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-406LBA2 | LOST BATTALION HALL GYM FLOOR Q401 | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 406 | P-Q245 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | LOST BATTALION HALL GYM FLOOR Q401 | 2019 | 1020 | 0 | 0 | 0 | 0 | 850 | 0 | 0 | 850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-406PG62 | Playground Sixty Two R/C | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 406 | P-Q245 P-D019 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | PLAYGROUND SIXTY TWO | 2019 | 504 | 0 | 0 | 1100 | 0 | 1280 | 0 | 920 | 3300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-406YPF2 | Yellowstone Park Fencing Pt. 2 R/C | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D019 |  |  | RECONSTRUCTION OF FENCING AT YELLOWSTONE PARK, ALONG 68TH ROAD, BOROUGH OF QUEENS | 2019 | 275 | 0 | 0 | 0 | 0 | 275 | 0 | 0 | 275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-406YPFN | Yellowstone Park Fencing Pt. 1 R/C | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 406 | P-D019 |  |  | RECONSTRUCTION OF FENCING AT YELLOWSTONE PARK, BOROUGH OF QUEENS | 2019 | 550 | 0 | 0 | 0 | 0 | 275 | 0 | 0 | 275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407BAYM | Bayside Marina Electrical Update Q135-115M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | P-1018 P-1245 |  | BAYSIDE MARINA ELECTRICAL UPDATE | BAYSIDE MARINA ELECTRICAL UPDATE | 2019 | 185 | 120.43 | 11 | 0 | 54 | 6 | 0 | 0 | 191.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407BHKS | BOWNE HOUSE KITCHEN AND SHED WING | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 407 | P-D019 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BOWNE HOUSE KITCHEN AND SHED WING | 2019 | 144 | 11 | 0 | 0 | 120 | 0 | 0 | 0 | 131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407BHRE | BOWNE HOUSE RESTORATION Q022-110M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 407 | P-Q245 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BOWNE HOUSE RESTORATION | 2019 | 900 | 3407.24 | -250 | 0 | 728 | 0 | 0 | 0 | 3885.24 | 275.47 | 0 | 0 | 0 | 0 | 0 | 0 | 275.47
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407BLND | Bland Playground Lighting | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-Q245 P-D019 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ADDITION OF LIGHTING AT BLAND PLAYGROUND | 2019 | 682 | 0 | 0 | 3000 | 0 | 1000 | 0 | 500 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407BOWH | BOWNE HOUSE REHAB | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 407 | P-D019 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | QUEENS | RECONSTRUCTION | 2019 | 702 | 0 | 0 | 0 | 452 | 0 | 0 | 0 | 452 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407BOWN | BOWNE HOUSE HISTORICAL SOCIETY | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 407 | P-D019 | PROJECT DELAYED PENDING APPROVAL OF NECESSARY PERMITS | QUEENS | RECONSTRUCTION OF ELECTRICAL HEATING, PLUMBING, SECURITY SYSTEMS OF THE HOUSE. | 2019 | 199 | 0 | 0 | 0 | 176 | 0 | 0 | 0 | 176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407BPFF | BOWNE PK POND R/C Q006-215MA | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | P-D019 P-0245Q |  |  | BOWNE PK FOUNTAINS AND FILTRATION SYSTEMS UPGRADE | 2019 | 1150 | 399.14 | 0 | 1794 | 0 | 0 | 0 | 0 | 2193.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407BTPL | Bay Terrace Playground R/C Q399-118M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-Q245 P-D019 |  | BAY TERRACE PLAYGROUND, QUEENS | REPAVING OF BASKETBALL AND HANDBALL COURTS | 2019 | 1033 | 335.45 | 0 | 0 | 2909 | 0 | 0 | 0 | 3244.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407BWPK | Bowne Park Upgrades | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D019 |  |  | BOWNE PARK UPGRADE PLAZA ADJACENT TO BOCCE AREA, PROVIDE PASSING SITTING AREA, DECORATIVE ELEMENTS, AND ENHANCED PLANTINGS, BOROUGH OF QUEENS | 2019 | 1272 | 0 | 0 | 0 | 0 | 920 | 80 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407CPSC | College Point Fields Cons. of a Football Field Q476-117M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 407 | P-D019 P-0245Q | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CONSTRUCT NEW SYSTHETIC FOOTBALL FIELD, MONDO RUNNING TRACK, PARKING AREA, LIGHTING AND NEW BENCHES AND BEACHES | 2019 | 500 | 647.16 | 0 | 0 | 0 | 6703 | 0 | 0 | 7350.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407FGP2 | Frank Golden Pk - R/C of Athletic Fields Phase II Q445-118M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 407 | P-Q126 P-D019 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | FRANK GOLDEN PK -SHANNON GAELS | 2019 | 1580 | 438.8 | 12 | 3760 | 377 | 0 | 0 | 0 | 4587.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407FLB2 | Francis Lewis Park Bocce Court Renovations | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D019 |  |  | FRANCIS LEWIS PARK BOCCE COURT RENOVATIONS | 2019 | 89 | 0 | 0 | 0 | 0 | 0 | 0 | 65 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407HARV | Harvey Park | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 407 | P-D019 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | HARVEY PARK | 2019 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407MAPL | Maple Playground R/C Q211-117M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 407 | P-D019 P-Q245 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | INSTALL NEW EQUIPMENT, ENTRANCE PAVEMENT, AND SEATING IN MAPLE PLAYGROUND | 2019 | 1200 | 348.98 | 424 | 0 | 0 | 5571 | 474 | 0 | 6817.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407MCN4 | Herman MacNeil Park Entrance and Pathways | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 407 | P-1018 |  |  | IMPOVEMENTS TO THE HERMAN MACNEIL PARK, INCLUDING THE ENTRANCE AND PATHWAYS, BOROUGH OF QUEENS | 2019 | 575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 575 | 0 | 0 | 0 | 0 | 575
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407MCNS | MacNeil Park Steps Construction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D019 P-Q245 |  |  | MACNEIL PARK CONSTRUCTION OF GRANITE STEPS, BOROUGH OF QUEENS | 2019 | 595 | 0 | 0 | 0 | 0 | 595 | 0 | 0 | 595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407MFL2 | Olde Towne of Flushing Burial Ground Monument Cons Q017-118M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 407 | P-Q245 P-0245Q P-D019 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | MARTINS FIELD | THE OLDE TOWNE OF FLUSHING BURIAL GROUND MONUMENT CONSTRUCTION, BOROUGH OF QUEENS | 2019 | 129 | 168 | 0 | 0 | 1499 | 130 | 0 | 0 | 1797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407MPSW | MACNEIL PARK SEAWALL Q009-114MA | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 407 | P-1018 P-Q245 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | MACNEIL PK SEAWALL | 2019 | 1400 | 5250.8 | 19 | 0 | 0 | 641 | 0 | 0 | 5910.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407VELO | KISENNA VALLEY PK RC VELODROME | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D019 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | KISENNA VALLEY PK RC VELODROME | KISENNA VALLEY PK RC VELODROME | 2019 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408BRIA | Briarwood Plgd and Phil Rizzuto Park R/C QG-116MA | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BRIARWOOD PLAYGROUND AND PHIL "SCOOTER" RIZZUTO PARK RECONSTRUCTION | 2019 | 700 | 1930.69 | 0 | 0 | 0 | 152 | 0 | 0 | 2082.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408CPGA | Cunningham Park Garage Space Conversion | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-1018 P-0704 |  |  | CONVERT A PORTION OF CUNNINGHAM PARK GARAGE SPACE INTO A HUB SPACE FOR MNO STAFF | 2019 | 5670 | 619.16 | 1231 | 0 | 0 | 19563 | 1697 | 0 | 23110.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408CPPA | Cunningham Park Picnic Area RC Q021-115M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 408 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | $375K PD019 FY14 ADOPTION SEC 254... | 2019 | 449 | 3010.43 | 39 | 0 | 0 | 1 | 0 | 0 | 3050.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408HOV2 | Hoover Playground | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 408 | P-Q245 P-D019 |  |  | HOOVER PLAYGROUND | 2019 | 960 | 0 | 0 | 0 | 0 | 2300 | 0 | 800 | 3100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408MANT | Hoover-Manton Playgrounds Renovation | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D019 |  |  | RENOVATION OF HOOVER-MANTON PLAYGROUNDS | 2019 | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 700 | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408MLDY | Site for Mother Language Day in Captain Tilly Park | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-Q245 |  |  | COMMEMORATIVE SITE FOR MOTHER LANGUAGE DAY IN CAPTAIN TILLY PARK | 2019 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408VAN2 | Vanderbilt Motor Parkway Repaving Phase II | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | P-0245Q |  |  | PHSE II OF THE REPAVING OF VANDERBILT MOTOR PARKWAY, LOCATED IN CUNNINGHAM PARK, BOROUGH OF QUEENS | 2019 | 4000 | 0 | 0 | 0 | 0 | 4000 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408VAND | Vanderbilt Motor Parkway Repaving QG-718M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | P-D019 |  |  | REPAVING OF VANDERBILT MOTOR PARKWAY, LOCATED IN CUNNINGHAM PARK | 2019 | 1664 | 207 | 0 | 0 | 0 | 1250 | 0 | 0 | 1457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-409EQTY | Equity Park Playground Upgrades | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D019 |  |  | PLAYGROUND EQUIPMENT UPGRADE AT EQUITY PARK | 2019 | 682 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-409FPG3 | FOREST PARK GREENHOUSES Q015-215M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 405 406 409 | P-D019 P-Q245 |  |  | FOREST PARK GREENHOUSES Q015 | 2019 | 1000 | 306.34 | 14 | 0 | 0 | 1661 | 0 | 0 | 1981.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-409MARD | Glendale Entrance to Forest Park Q015-217M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | P-D019 P-Q771 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | MYRTLE AVENUE ROAD IN FOREST PARK | 2019 | 1100 | 423.08 | 0 | 0 | 0 | 2133 | 0 | 0 | 2556.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-409SOB2 | SOBELSOHN C/S | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D019 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | SOBELSOHN C/S | SOBELSOHN C/S | 2019 | 550 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-410ALST | Al Stabile Playground Renovation | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D019 |  |  | AL STABILE PLAYGROUND RENOVATION, BOROUGH OF QUEENS | 2019 | 1988 | 0 | 0 | 0 | 0 | 1750 | 0 | 0 | 1750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-410BYRN | Edward Byrne Park Playground C/S | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-Q245 |  |  | CONSTRUCTION OF A COMFORT STATION AT EDWARD BYRNE PARK PLAYGROUND | 2019 | 3537 | 56 | 0 | 0 | 0 | 3000 | 0 | 0 | 3056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-410FJPG | FREDERICK JUDGE PLAYGROUND AND BB CTS. | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 410 | P-D019 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES | FREDERICK JUDGE PLAYGROUND - COMFORT STATION | FREDERICK JUDGE PLAYGROUND - COMFORT STATION | 2019 | 550 | 870.9 | 0 | 0 | 0 | 0 | 1100 | 0 | 1970.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-410PEBP | Police Officer Edward O'Byrne Park - Queens | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-0245Q |  |  | POLICE OFFICER EDWARD O'BYRNE PARK - QUEENS | 2019 | 2650 | 0 | 0 | 0 | 0 | 2650 | 0 | 0 | 2650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-410SCN2 | Harold Schneiderman Playground Upgrades | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-Q245 P-D019 |  |  | UPGRADE PLAY EQUIPMENT AT HAROLD SCHNEIDERMAN PLAYGROUND | 2019 | 1022 | 0 | 0 | 0 | 0 | 2250 | 0 | 2250 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-411APE2 | ALLEY POND ENVIRONMENTAL CENTER & CONS. OF ANNEX Q001-110M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 411 | P-Q245 WP-0169 P-Q002 P-D019 P-0506 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | CONSTRUCTION OF AN ANNEX AND RC OF APEC | 2019 | 1060 | 2188.67 | 15930 | 0 | 1485 | 6256 | 0 | 0 | 25859.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-411APLS | Alley Pond Park Living Shoreline Construction | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | P-1018 |  |  | CONSTRUCTION OF A LIVING SHORELINE AT ALLEY POND PARK, BOROUGH OF QUEENS | 2019 | 320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 256 | 0 | 0 | 0 | 0 | 256
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-411AURO | AURORA POND - RESTORATION Q452-100MA | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 411 | P-D019 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | UDALLS PARK NORTHERN BLVD, 244-247 STS, DOUGLAS RD | RESTORAATION | 2019 | 1403 | 983.47 | 0 | 0 | 0 | 0 | 200 | 0 | 1183.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-411SWP2 | Saul Weprin Playground R/C Q293-118M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D019 |  |  | SAUL WEPRIN PLAYGROUND RENOVATION | 2019 | 1364 | 181 | 912 | 88 | 0 | 0 | 0 | 0 | 1181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412BAI2 | Baisley Pond Park Track & Field, Syn. Turf, Fitness R/C | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-0245Q |  |  | BAISLEY POND PARK - QUEENS | 2019 | 10275 | 0 | 652 | 0 | 0 | 8358 | 840 | 0 | 9850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412BPP3 | BAISLEY POND PARK PHASE III Q005-113M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 412 | P-D019 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES |  | UPGRADE ASPHALT PARK SYSTEM ADJACENT TO THE LAKE OF ROCKAWAY BLVD AND150 ST. INSTALL NEW LIGHTING AND CREATE NEW WALKWAYS | 2019 | 1300 | 1771.36 | 0 | 0 | 0 | 610 | 0 | 0 | 2381.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412BPP4 | Athletic Courts Multi-Site QG-216M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | P-D019 P-1018 P-Q708 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BAISLEY POND PK ATHLETIC CTS | 2019 | 1000 | 2147.66 | 0 | 0 | 0 | 1046 | 0 | 0 | 3193.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412DOP2 | DANIEL O'CONNELL PLAYGD. C/S Q106-113M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 412 | P-D019 P-1018 P-0505 P-0882 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | DANIEL O'CONNOR C/S | 2019 | 1700 | 781.19 | 2068 | 45 | 0 | 204 | 0 | 0 | 3098.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412JMIC | Jamaica Playground - Queens | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-0245Q |  |  | JAMAICA PLAYGROUND - QUEENS | 2019 | 4650 | 0 | 0 | 0 | 423 | 3832 | 395 | 0 | 4650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412NAUT | Nautilus Playground R/C | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 412 | P-D019 P-Q245 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NAUTILUS PLAYGROUND | 2019 | 600 | 0 | 109 | 0 | 0 | 3000 | 2699 | 0 | 5808 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412NOR2 | Norelli-Hargreaves Playground MPPA R/C Q220B-118M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-Q245 |  |  | NORELLI HARGREAVES PLAYGROUND - RENOVATION TO BASKETBALL COURTS AND MULTI PURPOSE PLAY AREA | 2019 | 3326 | 243 | 0 | 2273 | 227 | 0 | 0 | 0 | 2743 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412NORI | Norelli-Hargreaves Playground R/C Q220-116M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 412 | P-Q245 P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NORELLI-HARGREAVES PARK IMPROVEMENTS | 2019 | 2000 | 364 | 2496 | 0 | 250 | 0 | 0 | 0 | 3110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RK01 | Rufus King Park Cons. of Entrance & R/C of Fence Q023-216M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 412 | P-D019 P-0245Q | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | JAMAICA AVE, QUEENS | CONSTRUCTION OF PARK ENTRANCES & RECONSTRUCTION OF THE PERIMETER FENCE AT RUFUS KING PARK | 2019 | 1700 | 351 | 2870 | 0 | 0 | 0 | 0 | 0 | 3221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RKM2 | RUFUS KING MANOR MUSEUM -HVAC Q23-116M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 412 | P-D019 P-0245Q | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RUFUS KING MANOR MUSEUM | 2019 | 400 | 88.34 | 435 | 67 | 0 | 0 | 0 | 0 | 590.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RWIL | ROY WILKINS REC CTR ROOF & SITE Q448-112M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 412 | P-0245Q P-Q245 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | QUEENS | RC ROOF ROY WILKINS REC CTR, ROOFTOP GYM AC, SITE /GARDEN DRAINAGE | 2019 | 4318 | 5146.39 | -23 | 0 | 0 | 1145 | 0 | 0 | 6268.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RWP3 | ROY WILKINS PARK RECREATION CTR RC Q448-115M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 412 | P-D019 P-Q245 P-0506 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ROY WILKINS PARK RECREATION CTR | 2019 | 1440 | 396.45 | 12 | 2447 | 0 | 0 | 0 | 0 | 2855.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RWP5 | Roy Wilkins Fitness Room Upgrades | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | P-D019 |  |  | ROY WILKINS PARK FITNESS ROOM EXPANSION | 2019 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 1915 | 1915 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RWTT | Roy Wilkins Park Turf and Track Upgrades Q448-116M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 412 | P-D019 |  |  | ROY WILKINS PARK TURF AND TRACK UPGRADES: RENOVATE TRACK TURF AND SYNTHETHIC TURF FIELDS; REPLACE SUB-BASE AND TOP COURSE FIELD. | 2019 | 5160 | 3551.88 | 0 | 0 | 0 | 1148 | 0 | 0 | 4699.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413BPTC | BROOKVILLE PARK ENHANCEMENTS Q008-115M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 413 | P-D019 P-0245Q P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BROOKVILLE PARK TENNIS COURTS | 2019 | 1000 | 2717.16 | 765 | 0 | 0 | 298 | 0 | 0 | 3780.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413BRO3 | Brookville Park Entrance R/C Q008-117M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | P-D019 |  |  | BROOKVILLE PARK UPGRADES | 2019 | 2132 | 325.96 | 1111 | 807 | 0 | 0 | 0 | 0 | 2243.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413BRO4 | Brookville Park Dog Run | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D019 |  |  | BROOKVILLE PARK DOG RUN, BOROUGH OF QUEENS | 2019 | 2000 | 0 | 82 | 0 | 0 | 930 | 88 | 0 | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413BRSY | Brookville Park Synthetic Turf Field R/C | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 413 | P-D019 |  |  | BROOKVILLE PARK SYNTHETIC TURF FIELD RECONSTRUCTION, BOROUGH OF QUEENS | 2019 | 3837 | 0 | 82 | 0 | 0 | 2933 | 0 | 0 | 3015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413CAST | Castlewood Playground - Reconstruction of the MPPA Q327-119M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-Q245 P-D019 |  |  | CASTLEWOOD PLAYGROUND: RECONSTRUCTION OF MPPA | 2019 | 3700 | 0 | 90 | 0 | 0 | 600 | 2410 | 0 | 3100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413COV2 | Sunset Cove Pk Oyster Garden/Boardwalk Cons. Q498-117M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | P-Q003 |  |  | SUNSET COVE PARK PHASE II - CONSTRUCTION OF AN OFFSHORE EDUCATIONAL OYSTER GARDEN AND BOARDWALK | 2019 | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413COVE | Sunset Cove Salt Marsh Restoration Q498-115M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | P-1018 |  | SOUTH OF WEST 19TH STREET BETWEEN JAMAICA BAY AND CROSS BAY BOULEVARD, BOROUGH OF QUEENS | SUNSET COLVE SALT MARSH RESTORATION IN JAMAICA BAY | 2019 | 7106 | 8635.02 | 59 | 0 | 0 | 607 | 0 | 0 | 9301.02 | 400 | 0 | 0 | 0 | 1 | 0 | 0 | 401
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413IDL3 | IDLEWILD PK SITE B Q392 | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 413 | ED-0075 P-0245Q | PROJECT DELAYED PENDING APPROVAL OF STATE REQ CONTRACT | QUEENS | IDLEWILD PK SITE B | 2019 | 2001 | 0 | 0 | 2364 | 0 | 202 | 0 | 0 | 2566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413IDPK | IDLEWILD PK MARSH NATURE CENTER Q392-210M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 413 | P-Q245 P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | IDLEWILD PK MARSH ENVIRONMENTAL CENTER Q392 | 2019 | 100 | 7362.43 | 580 | 0 | 0 | 55 | 0 | 0 | 7997.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413IDSA | Idlewild Park Sediment Application | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 413 | P-1018 |  |  | THIN LAYER SEDIMENT APPLICATION IN IDLEWILD PARK, BOROUGH OF QUEENS | 2019 | 286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 304 | 0 | 0 | 0 | 0 | 304
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413JH72 | VIC HANSON/JHS 72 PLGD RC Q352 | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 413 | P-Q245 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | VIC HANSON/JHS 72 PLGD RC Q352 | 2019 | 420 | 0 | 0 | 0 | 0 | 0 | 0 | 350 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413LPL3 | Laurelton Plgd and Bayswater Park Skate Elements QG-316M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 413 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | LAURELTON PLAYGROUND | 2019 | 300 | 3487 | 0 | 0 | 0 | 84 | 0 | 0 | 3571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413READ | Bellerose Playground (PS 133) Creation of Reading Garden | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-1018 |  |  | CREATION OF A READING GARDEN AT PS 133 (BELLEROSE PLAYGROUND), BOROUGH OF QUEENS | 2019 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 250
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413SPBD | Springfield Park Basketball Courts and BBQ | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D019 P-0245Q |  |  | SPRINGFIELD PARK BASKETBALL COURTS AND BBQ, BOROUGH OF QUEENS | 2019 | 4200 | 0 | 77 | 0 | 0 | 2000 | 1223 | 0 | 3300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413WGPF | WILLIAM GUNN PLAYGROUND EXPANSION | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 413 | P-D019 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | EXPAND MPPA MULTI USE YARD INTO STREET BED AS PER YESHIVA AGREEMENT ADD FENCING AND LANDSCAPING | 2019 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-41417PG | BROAD CHANNEL 17TH STREET PLAYGROUND Q460-118M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 414 | P-Q245 P-D019 |  | BROAD CHANNEL 17TH STREET PLAYGROUND: RENOVATE ENTRY PLAZA | BROAD CHANNEL 17TH STREET PLAYGROUND: RENOVATE ENTRY PLAZA | 2019 | 2678 | 216.5 | 0 | 0 | 2252 | 0 | 0 | 0 | 2468.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414B108 | Beach 108th Esplanade Improvements | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-1018 P-0581 |  |  | IMPROVEMENTS TO THE HARBOR PARK ESPLANADE ALONG BEACH CHANNEL DRIVE, AT BEACH 108TH STREET, BOROUGH OF QUEENS | 2019 | 2276 | 152 | 0 | 0 | 0 | 0 | 0 | 0 | 152 | 0 | 147 | 0 | 1521 | 0 | 0 | 0 | 1668
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414BAY6 | Michaelis-Bayswater Park Reconstruction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 414 | P-1018 |  |  | RECONSTRUCTION OF BAYSWATER PARK, BOROUGH OF QUEENS | 2019 | 4280 | 244.83 | 0 | 0 | 0 | 3713 | 322 | 0 | 4279.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414BC88 | Beach 88th Street Park Construction | BEACHES AND BOARDWALKS | 400 | P-1018 |  |  | CONSTRUCTION OF A PARK ON BEACH 88TH STREET, BOROUGH OF QUEENS | 2019 | 200 | 17.8 | 0 | 0 | 0 | 182 | 0 | 0 | 199.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414LABY | Shorefront Labyrinth and Seating Area | BEACHES AND BOARDWALKS | 400 | P-D019 P-Q003 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | CREATION OF A LABYRINTH/YOGA AREA ALONG SHORE FRONT PARKWAY, IN THE VICINITY OF BEACH 90-102 STREETS, BOROUGH OF QUEENS | 2019 | 332 | 21.15 | 0 | 0 | 402 | 34 | 0 | 0 | 457.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414LAN2 | Lannett Playground Sitting Area R/C Q407-118M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-Q245 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | LANNETT PLAYGROUND | LANNETT PLAYGROUND | 2019 | 250 | 141 | 0 | 1227 | 123 | 0 | 0 | 0 | 1491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414ODON | O'Donohue Park Picnic Grove Construction | BEACHES AND BOARDWALKS | 400 | P-D019 |  |  | O'DONOHUE PARK PICNIC GROVE AND BBQ AREA CONSTRUCTION, AT ROCKAWAY BEACH AND BOARDWALK, BOROUGH OF QUEENS | 2019 | 320 | 0 | 0 | 0 | 0 | 0 | 0 | 320 | 320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414RB59 | Beach 59th Street Playground R/C Q162E-118M | BEACHES AND BOARDWALKS | 400 | P-Q245 P-D019 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BEACH 59 ST PLAYGROUND UPGRADE PK | 2019 | 200 | 56 | 116 | 0 | 0 | 4884 | 0 | 0 | 5056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414RBHD | Rockaway Beach Shorefront Pkwy Handball Courts Q163-315M | BEACHES AND BOARDWALKS |  | P-Q245 P-D019 P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ROCKAWAY BEACH SHOREFRONT PKWY HANDBALL COURTS | 2019 | 500 | 6.23 | 383 | 0 | 0 | 59 | 0 | 0 | 448.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414RBRR | ROCKAWAY BEACH 108 ST ROLLER RINK Q163-114M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 414 | P-D019 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RC OF ROLLER HOCKEY RINK AND INSTALLATION OF RECREATION LIGHTING AT ROCKAWAY BEACH | 2019 | 300 | 659.87 | 0 | 0 | 0 | 203 | 0 | 0 | 862.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414RKSP | ROCKAWAY BEACH SKATE PARK FACILITY- RC Q163-111MA | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ROCKAWAY SKATE PARK | 2019 | 750 | 126.47 | 1122 | 0 | 0 | 0 | 0 | 0 | 1248.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414SRHV | SORRENTINO RECR CTR HVAC Q446-216M | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 400 | P-1250 P-1018 |  |  | SORRENTINO RECR CTR HVAC Q446 | 2019 | 1000 | 1724.56 | 14 | 0 | 0 | 149 | 0 | 0 | 1887.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414THUR | Thursby Basin Park Construction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D019 P-D171 |  |  | CONSTRUCTION OF THURSBY BASIN PARK, AT ROCKAWAY BEACH AND BOARDWALK, IN THE BOROUGH OF QUEENS | 2019 | 583 | 0 | 0 | 0 | 0 | 557 | 26 | 0 | 583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414TRB2 | Tribute Park Reconstruction Q028-116M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 414 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | QUEENS | TRIBUTE PARK | 2019 | 675 | 1748.18 | 0 | 0 | 0 | 266 | 0 | 0 | 2014.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415AQUA | FMCP - Aquatic Center Roof Replacement | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | P-0245Q P-0013 |  |  | REPLACEMENT OF ROOF AT THE AQUATIC CENTER, IN FLUSHING MEADOWS CORONAPARK | 2019 | 12056 | 120 | 823 | 0 | 0 | 11233 | 0 | 0 | 12176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415CAND | FMCP - Reconstruction of Candela Structures | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | P-D019 P-1018 |  |  | RECONSTRUCTION OF CANDELAS AT FLUSHING MEADOWS CORONA PARK, BOROUGH OF QUEENS | 2019 | 3500 | 0 | 596 | 0 | 0 | 1983 | 0 | 0 | 2579 | 0 | 0 | 0 | 2500 | 0 | 0 | 0 | 2500
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415ENTR | FMCP - ROOSEVELT AVENUE ENTRANCE RC - Q099-115M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | P-0245Q | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | FMCP ROOSEVELT AVENUE ENTRANCE RC | 2019 | 2180 | 3166.1 | 0 | 0 | 0 | 236 | 0 | 0 | 3402.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415FMC2 | FMCP - Meadow Lake Promenade R/C Q099-113M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 403 404 406 407 408 | P-0245Q | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | REALIGN ROADWAY AND REPAIR EXISTING SETTLING PATH SYSTEM ADJACENT TO HONG KONG DRAGON BOAT CIRCLE AND SECTIONS OF NORTHEAST CORRIDOR | 2019 | 1200 | 5017.28 | 178 | 0 | 0 | 375 | 0 | 0 | 5570.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415FMWS | FMCP - Adult Fitness Equipment Installation Q099-318M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | P-D019 |  |  | INSTALLATION OF ADULT FITNESS EQUIPMENT AT FLUSHING MEADOWS CORONA PARK, BOROUGH OF QUEENS | 2019 | 266 | 33 | 0 | 200 | 0 | 0 | 0 | 0 | 233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415FOTF | FMCP - Fourtain of the Fairs R/C Q099-117M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | P-0013 |  |  | FLUSHING MEADOWS CORONA PARK - FOUNTAIN OF THE FAIRS RECONSTRUCTION, BOROUGH OF QUEENS | 2019 | 5144 | 548.05 | 6434 | 0 | 0 | 0 | 0 | 0 | 6982.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415FSTF | FMCP - Synthetic Turf Fields 8 & 9 R/C | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | P-0510 |  |  | FLUSHING MEADOWS CORONA PARK - RECONSTRUCTION OF SYNTHETIC TURF FIELDS 8 & 9, BOROUGH OF QUEENS | 2019 | 9973 | 0 | 512 | 0 | 0 | 6789 | 699 | 0 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415LWCS | FMCP - Lawrence Playground Comfort Station R/C Q099-817MA | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-0245Q |  |  | RECONSTRUCTION OF COMFORT STATION IN LAWRENCE PLAYGROUND, IN FLUSING MEADOWS CORONA PARK | 2019 | 1310 | 23.76 | 1086 | 0 | 0 | 0 | 0 | 0 | 1109.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415LWP2 | FMCP - Lawrence Playground R/C Q099-717M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-1018 |  |  | RECONSTRUCTION OF LAWRENCE PLAYGROUND IN FLUSHING MEADOWS CORONA PARK | 2019 | 4999 | 3847 | 127 | 0 | 0 | 257 | 0 | 0 | 4231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415MEA2 | FMCP - MEADOW LAKE- PATHS Q099-215M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 403 404 406 407 408 | P-Q245 P-D019 P-0013 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | FMCP - MEADOW LAKE- PATHS Q099 | 2019 | 900 | 343 | 0 | 750 | 0 | 3000 | 0 | 0 | 4093 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415PAS4 | Passerelle Roof | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | P-0245Q |  |  | PASSERELLE ROOF, BOROUGH OF QUEENS | 2019 | 21280 | 0 | 0 | 0 | 21280 | 0 | 0 | 0 | 21280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415PAVI | FMCP - NYS PAVILION RC Q099-116M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 403 404 406 407 408 | P-Q245 P-0245Q P-D019 P-Q001 P-Q003 P-0013 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | QUEENS | FMCP PAVILLION...11/26/18 $28K P-D019 FY21 XFER FROM P-403127Q..11/26/18 $743K P-D019 FY20 XFER FROM P-403HIN3..11/26/18 $17K P-D019 FY21 XFER FROM P-404LPBF...11/26/18 $35K P-D019 FY20 XFER FROM P-4PLG13D..11/26/18 $15K P-D019 FY20 XFER FROM P-4PLG13K | 2019 | 150 | 1026.72 | 21993 | 855 | 346 | 0 | 0 | 0 | 24220.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415SCHL | Flushing Meadows Corona Park UPK | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | P-0013 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CONSTRUCTION OF A SCHOOL IN FLUSHING MEADOWS CORONA PARK | 2019 | 20000 | 0 | 0 | 0 | 0 | 0 | 28000 | 0 | 28000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415WLNC | WILLOW LAKE NATURE CENTER Q348 | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D019 P-0506 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | WILLOW LAKE NATURE CENTER | WILLOW LAKE NATURE CENTER | 2019 | 750 | 0 | 75 | 0 | 0 | 2226 | 199 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415WRD2 | FMCP - World's Fair Marina Pier 1 & 3 R/C | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | P-1018 |  |  | RECONSTRUCTION OF PIER 1 & 3 AT WORLD'S FAIR MARINA, IN FLUSHING MEADOWS CORONA PARK | 2019 | 35962 | 1752.83 | 0 | 0 | 0 | 34209 | 0 | 0 | 35961.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415WRLD | FMCP - World's Fair Playground Asphalt Field Q099-517M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | P-Q245 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RENOVATE ASPHALT FIELD AT WORLD'S FAIR PLAYGROUND | 2019 | 2400 | 1780.91 | 31 | 0 | 0 | 396 | 0 | 0 | 2207.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4ANCH01 | Anchor Park Site - Astoria Park (DESIGN ONLY - ALL PHASES) | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | P-1018 P-D019 |  |  | ANCHOR PARK SITE - ASTORIA PARK | 2019 | 32730 | 3386.21 | 84 | 300 | 0 | 0 | 0 | 0 | 3770.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4ANCH02 | Anchor Pk - Astoria Park PH1: Synthetic Turf Track Q004-218M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | P-1018 P-Q245 P-D019 |  |  | ANCHOR PARK INITIATIVE AT ASTORIA PARK, PHASE 1, BOROUGH OF QUEENS | 2019 | 13954 | 0.36 | 11898 | 0 | 0 | 0 | 531 | 0 | 12429.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4ANCH03 | Anchor Pk - Astoria Park PH2A: Charybdis Plgd R/C Q004-318M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | P-0848 P-D019 |  |  | RECONSTRUCTION OF CHARYBDIS PLAYGROUND AND ASTORIA POOL PLAY AREA, INASTORIA PARK, BOROUGH OF QUEENS | 2019 | 9546 | 0 | 0 | 12362 | 0 | 0 | 0 | 0 | 12362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4ANCH04 | Anchor Pk - Astoria Pk PH2B: Charybdis Plgd CS R/C Q004-418M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | P-0848 |  |  | RECONSTRUCTION OF THE COMFORT STATION AT CHARYBDIS PLAYGROUND, IN ASTORIA PARK, BOROUGH OF QUEENS | 2019 | 3272 | 0 | 2400 | 0 | 0 | 0 | 0 | 0 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4ANCH05 | Anchor Park - Astoria Park Phase 3 | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | P-0848 |  |  | ANCHOR PARK - ASTORIA PARK PHASE 3, BOROUGH OF QUEENS | 2019 | 4510 | 0 | 0 | 2000 | 2510 | 0 | 0 | 0 | 4510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BASDCS | Bayside Playground-Reconstruction of Comfort Station | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-0505 |  |  | BAYSIDE PLAYGROUND-RECONSTRUCTION OF COMFORT STATION | 2019 | 1645 | 0 | 0 | 0 | 0 | 1645 | 0 | 0 | 1645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BAYMAR | Reconstruction of Bayside Marina | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 400 | P-D019 P-1245 |  |  | RECONSTRUCTION OF BAYSIDE MARINA | 2019 | 1849 | 0 | 0 | 0 | 0 | 1776 | 0 | 0 | 1776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BC94S1 | Beach 94th Street Performance Space Construction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-Q003 P-D019 |  |  | BEACH 94TH STREET PERFORMANCE SPACE - CONSTRUCTION OF A PERFORMANCE SPACE AT SHORE FRONT PARKWAY, IN ROCKAWAY BEACH, BOROUGH OF QUEENS | 2019 | 3326 | 0 | 169 | 12 | 0 | 0 | 0 | 0 | 181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BLSPTH | Black Spectrum Theatre -Interior renovations | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D019 |  |  | BLACK SPECTRUM THEATRE -INTERIOR RENOVATIONS | 2019 | 500 | 0 | 0 | 0 | 0 | 460 | 40 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BRKVBB | BROOKVILLE PARK TWO BASEBALL FIELD | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-Q773 |  |  | BROOKVILLE PARK CONSTRUCTION OF TWO BASEBALL FIELDS IN QUEENS | 2019 | 0 | 0 | 0 | 2000 | 0 | 1000 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BROADC | Broad Channel Playground Expansion | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-Q245 |  |  | BROAD CHANNEL PLAYGROUND EXPANSION | 2019 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BSDWK5 | RECONSTRUCTION OF SIDEWALKS(QUEENS CB 8-14) QG-905M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-1018 |  | QUEENS, CB 8-14 | RECONSTRUCTION OF SIDEWALKS | 2019 | 873 | 768.7 | 0 | 0 | 0 | 92 | 0 | 0 | 860.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BSHIST | Ft. Totten Bayside Historical Society Officers ClubQ458-116M | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 400 407 | P-D019 | PROJECT DELAYED PENDING APPROVAL OF NECESSARY PERMITS |  | FT. TOTTEN BAYSIDE HISTORICAL SOCIETY OFFICERS CLUBQ458-116M | 2019 | 180 | 425.68 | 2 | 0 | 0 | 229 | 0 | 0 | 656.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWALK1 | FY12 Queens Boardwalks (FEMA Funded) Q162-212M | BEACHES AND BOARDWALKS | 400 414 | P-D019 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | ROCKAWAY, QUEENS | ROCKAWAY BEACH BOARDWALK R/C | 2019 | 2940 | 689.75 | 0 | 0 | 0 | 0 | 149 | 0 | 838.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWIDEF | QUEENS - MULTI SITE QG-210M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | P-0245Q | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RC OF PAVEMENTS, HANDBALL AND TENNIS CTS, ROLLER HOCKEY RINKS, FENCES, PLANTINGS AND GENERAL SITE WORK | 2019 | 1582 | 1345.47 | 0 | 0 | 0 | 0 | 0 | 0 | 1345.47 | 347.91 | 0 | 0 | 0 | 0 | 52 | 0 | 399.91
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWIDEK | QUEENS - COUNCIL & BP MULTI SITE (QG-1011M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D019 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | QUEENS - COUNCIL & BP MULTI SITE | 2019 | 1735 | 2002.31 | 0 | 0 | 0 | 0 | 53 | 0 | 2055.31 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 300
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWIDEL | QUEENS - COUNCIL & MAYORAL MULTI SITE QG-1116M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | P-D019 P-1018 |  |  | RECONSTRUCTION OF WATER SUPPLY IN SPRINGFIELD PARK, BROOKVILLE PARK, AND LIBERTY COMMUNITY GARDEN AND LIGHTING IN LITTLE BAY PARK | 2019 | 1398 | 1200.85 | 0 | 0 | 0 | 132 | 0 | 0 | 1332.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWIDEM | QUEENS - MULTI SITE QG-1216M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | P-D019 P-Q245 P-1018 |  |  | RECONSTRUCTION OF BRINKERHOFF MALL, HOFFMAN PLAYGROUND, AND PATHS AT FOREST PARK | 2019 | 2935 | 1157.59 | 0 | 0 | 0 | 258 | 0 | 0 | 1415.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWIDEN | QUEENS - COUNCIL & BP MULTI SITE QG-1316M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | P-D019 P-0245Q |  |  | RECONSTRUCTION OF ONE ROOM SCHOOL HOUSE PLAYGROUND, KISSENA PARK CORRIDOR MEDITATION GARDEN, AND FITNESS EQUIPMENT IN ALLEY POND PARK | 2019 | 1978 | 1874.23 | 7 | 0 | 0 | 154 | 0 | 0 | 2035.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWIDEP | QUEENS - COUNCIL MULTI SITE | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D019 |  |  | QUEENS MULTI-SITE | 2019 | 400 | 332 | 2068 | 0 | 0 | 0 | 0 | 0 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWIDEQ | Roy Wilkins Southern Qns Pk Performance Area R/C Q448-118M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D019 P-0245Q |  |  | RECONSTRUCTION OF BROAD CHANNEL PARK AND IDLEWIDE PARK SITE B | 2019 | 1018 | 284 | 494 | 0 | 0 | 50 | 0 | 0 | 828 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWIDER | QUEENS - COUNCIL MULTISITE QG-618M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | P-D019 |  |  | NEW AND/OR UPGRADED FITNESS EQUIPMENT ALONG SHORE FRONT PARKWAY, AT JUNIPER VALLEY PARK, AT WAYANDA, CAMBRIA, HAGGERTY, AND MONTBELLIER PARKS, AND AT FLUSHING MEADOWS CORONA PARK | 2019 | 1411 | 150 | 0 | 818 | 82 | 0 | 0 | 0 | 1050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWIDES | QUEENS - COUNCIL MULTISITE QG-818M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | P-D019 |  |  | FENCING UPGRADES AT UNDERBRIDGE DOG RUN, THE DOG RUN AT FOREST PARK OVERLOOK, AND YELLOWSTONE PARK | 2019 | 1829 | 153 | 0 | 750 | 75 | 0 | 0 | 0 | 978 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWSTF1 | Grover Cleveland Plgd & Pals Oval Synthetic Turf Field R/C | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | P-0510 |  |  | GROVER CLEVELAND PLAYGROUND AND PALS OVAL SYNTHETIC TURF FIELD RECONSTRUCTION, BOROUGH OF QUEENS | 2019 | 5338 | 0 | 0 | 0 | 4194 | 0 | 0 | 0 | 4194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CARSON | Silent Spring Playground R/C Q300-116M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | QUEENS | SILENT SPRING PLAYGROUND RECONSTRUCTION, IN KISSENA PARK CORRIDOR, ACROSS FROM RACHEL CARSON PLAYGROUND | 2019 | 956 | 2137.99 | 0 | 0 | 0 | 174 | 0 | 0 | 2311.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPIAHP | CPI PH2 - Astoria Health Playground R/C Q123-116M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 401 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 14TH STREET BETWEEN 31 AVENUE AND 31 DRIVE. | ASTORIA HEALTH PLAYGROUND | 2019 | 0 | 2307.96 | 0 | 0 | 0 | 795 | 0 | 0 | 3102.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPIALM | CPI PH2 - Almeda Playground Reconstruction Q443-117M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CPI PHASE 3 - ALMEDA PLAYGROUND RECONSTRUCTION | 2019 | 7152 | 388 | 7442 | 684 | 0 | 0 | 0 | 0 | 8514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPIBN5 | CPI PH1- RC- Astoria Heights & Bowne Plgd C/S QG-1015M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 407 | P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | ASTORIA HEIGHTS - 30RD, 45 TO 46 STREETS - BOROUGH OF QUEENS, BOWNE PLAYGROUND - UNION & SANFORD | ASTORIA HEIGHTS PLAYGROUND & BOWNE PLAYGROUND C/S RECONSTRUCTION | 2019 | 3132 | 4335.61 | 207 | 0 | 0 | 0 | 194 | 0 | 4736.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPIBOW | CPI PH1- Bowne Playground R/C Q308-115M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 407 | P-1018 WP-0169 | PROJECT DELAYED PENDING APPROVAL OF NECESSARY PERMITS | UNION STREET AND SANFORD AVENUE, BOROUGH OF QUEENS | THE RECONSTRUCTION OF BOWNE PLAYGROUND | 2019 | 515 | 5828.02 | 229 | 0 | 0 | 0 | 331 | 0 | 6388.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPICHP | CPI PH2 - Chappetto Square R/C Q066H-118M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-0245Q |  |  | CPI PHASE 2: RECONSTRUCTION OF CHAPPETTO SQUARE, BOROUGH OF QUEENS | 2019 | 0 | 200 | 0 | 3971 | 541 | 0 | 0 | 0 | 4712 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPIP35 | CPI PH2 - Playground Thirty Five XXXV R/C Q296-116M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-1018 |  |  | THE RECONSTRUCTION OF PLAYGROUND THIRTY FIVE XXXV | 2019 | 2532 | 2731.87 | 0 | 0 | 0 | 327 | 0 | 0 | 3058.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPPLGD | Cunningham Park Playground | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-0936 |  |  | CUNNINGHAM PARK PLAYGROUND | 2019 | 4000 | 0 | 262 | 0 | 0 | 3738 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPSLIT | College Point Sports Park - New Lighting | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-Q245 |  |  | COLLEGE POINT SPORTS PARK - NEW LIGHTING | 2019 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPTLCS | Captain Tilly Park Comfort Station | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-0505 |  |  | CAPTAIN TILLY PARK COMFORT STATION | 2019 | 2701 | 0 | 0 | 0 | 0 | 2123 | 0 | 0 | 2123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CROCLL | Crocheron Park Little League Field Upgrades Q012-117M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 411 | P-D019 P-Q245 P-0245Q | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CROCHERON PARK LITTLE LEAGUE FIELD UPGRADES | 2019 | 1700 | 212.92 | 1543 | 0 | 60 | 0 | 0 | 0 | 1815.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CUN210 | CUNNINGHAM PARK 210 ST PLAYGROUND UPGRADE | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-Q936 |  |  | CUNNINGHAM PARK 210TH STREET PLAYGROUND UPGRADE | 2019 | 0 | 0 | 0 | 3000 | 0 | 800 | 0 | 0 | 3800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CUNPLG | Redwood Playground in Cunningham Park R/C Q021-117M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 408 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CUNNINGHAM PARK LOWER PLAYGROUND RENOVATION | 2019 | 1940 | 1956.12 | 0 | 0 | 0 | 169 | 0 | 0 | 2125.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4DITMPG | Ditmars Playground - Upgrade Play Equipment and Spray Shower | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-Q245 |  |  | DITMARS PLAYGROUND - UPGRADE PLAY EQUIPMENT, SAFETY SURFACE, SPRAY SHOWER, BENCHES, AND SECURITY LIGHTING | 2019 | 0 | 0 | 0 | 600 | 0 | 2700 | 0 | 0 | 3300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4DUTCH1 | Dutch Kills Comfort Station Q218-216M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 401 | P-0245Q |  |  | RECONSTRUCTION OF PLAYGROUND AND COMFORT STATION | 2019 | 1681 | 866.72 | 0 | 0 | 0 | 754 | 0 | 0 | 1620.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4EABTRC | Emerald Ash Borer (EAB) Tree Remove Queens | LAND ACQUISITION AND TREE PLANTING | 400 | P-0822 |  | EMERALD ASH BORER (EAB) TREE REMOVE QUEENS | EMERALD ASH BORER (EAB) TREE REMOVE QUEENS | 2019 | 1219 | 0 | 0 | 1219 | 0 | 0 | 0 | 0 | 1219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FLBAY2 | FLUSHING BAY DREDGING & CONSTR OF BOAT RAMP Q099-300M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | WP-0169 |  | EASTERN TERMINUS OF THE FLUSHING BAY PROM. LOCATED IN FLUSHING MEADOWS-CORONA PARK, BOROUGH OF QUEENS | DREDGING AND CONSTR BOAT RAMP | 2019 | 1718 | 1444.66 | 98 | 0 | 0 | 0 | 0 | 0 | 1542.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FMGARG | Flushing Meadows Corona Park Garage | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 400 | P-0245Q |  |  | FLUSHING MEADOWS CORONA PARK GARAGE | 2019 | 8000 | 398.49 | 0 | 7304 | 667 | 0 | 0 | 0 | 8369.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FMMAUR | FMCP Mauro Playground Upgrades Q099-917M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-Q245 P-D019 P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | MAURO PLAYGROUND UPGRADES: INSTALL PLAY EQUIPMENT AND UPGRADE SPRINKLERS | 2019 | 1800 | 351.66 | 5029 | 234 | 64 | 0 | 0 | 0 | 5678.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FRDJPU | FREDERICK JUDGE PLAYGROUND UPGRADES | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-Q245 |  |  | UPGRADES TO FREDERICK JUDGE PLAYGROUND IN QUEENS | 2019 | 0 | 0 | 0 | 2000 | 0 | 300 | 0 | 0 | 2300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FTTOTB | FT. TOTTEN PK CHAPEL & COMMANDER'S HOUSE Q458-112M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 407 | P-1324 P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | QUEENS | FORT TOTTEN BUILDING 422 ADA ACCESSIBILITY, NEW ROOF AND EXTERIOR WORK | 2019 | 3087 | 4457.4 | 16 | 0 | 0 | 653 | 0 | 0 | 5126.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FTTOTC | FT. TOTTEN ELEVATORS Q458 | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | P-D019 |  |  | FT. TOTTEN ELEVATORS Q458 | 2019 | 350 | 0 | 0 | 350 | 0 | 0 | 0 | 0 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4GLNOAK | Tenney Pk (Glen Oaks) Bball Ct./Play Equip. R/C Q310-118M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-Q245 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RECONSTRUCTION OF THE PLAY EQUIPMENT AT TENNEY PARK (GLEN OAKS OVAL)... | 2019 | 1500 | 236.98 | 0 | 1210 | 121 | 0 | 0 | 0 | 1567.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4HCHAND | HALLET'S COVE RENOVATION OF HANDBALL COURT AND FENCING | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-Q245 |  |  | RENOVATION OF THE HANDBALL COURT WALL & ADJACENT FENCING AT HALLET'S COVE IN QUEENS | 2019 | 0 | 0 | 0 | 450 | 0 | 0 | 0 | 0 | 450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4HCOVP2 | Hallet's Cove Playground New MPPA | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D019 |  |  | CREATE A MULTIPURPOSE PLAY AREA AT HALLETS COVE PLAYGROUND | 2019 | 3537 | 41 | 227 | 0 | 2552 | 221 | 0 | 0 | 3041 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4HCOVPG | Hallets Cove Playground R/C Q226-117M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 401 | P-Q245 P-D019 P-0245Q |  |  | HALLETS COVE PLAYGROUND: FULL RENOVATION OF PLAYGROUND | 2019 | 1210 | 281 | 2016 | 0 | 0 | 206 | 0 | 0 | 2503 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4HKRINK | Roller Hockey Rinks Multi-Site QG-416M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-1018 P-D019 |  |  | RECONSTRUCTION OF HOCKEY RINKS AT HARVEY PARK, JUNIPER VALLEY PARK, JOSEPH F. MAFERA PARK, AND COLLEGE POINT FIELDS, BOROUGH OF QUEENS | 2019 | 2850 | 2290.4 | 90 | 0 | 0 | 6 | 0 | 0 | 2386.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4IDLETB | IDLEWILD PARK CONSTRUCTION OF NATURE TRAIL AND BOARDWALK | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 413 | P-Q245 |  |  | IDLEWILD PARK - EASTERN QUEENS ALLIANCE: CONSTRUCTION OF NATURE TRAIL AND BOARDWALK | 2019 | 1000 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4LATRUF | RUFUS KING MANOR & LEWIS H LATIMER HOUSE ROOFS QG-411M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 412 | P-Q245 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | KING MANOR AND LEWIS H LATIMER HOUSE ROOF PROJECTS | 2019 | 1400 | 1876.11 | 0 | 0 | 0 | 741 | 0 | 0 | 2617.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4LINDE2 | Park of the Americas - Plygrd & Synthetic Turf R/C Q026-118M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D019 P-0245Q | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | LINDEN PK BB FIELD, BASKETBALL CT & ADULT FITNESS EQUIP | 2019 | 1000 | 614.09 | 3468 | 748 | 0 | 0 | 0 | 0 | 4830.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4LTLBSH | Nathan Weidenbaum Park Playground R/C Q205B-118M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D019 |  |  | NATHAN WEIDENBAUM (LITTLE BUSH) PARK - PLAYGROUND RENOVATION | 2019 | 500 | 41 | 90 | 0 | 2678 | 232 | 0 | 0 | 3041 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4NNANPG | NOONAN PLAYGROUND | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-0505 |  |  | NOONAN PLAYGROUND | 2019 | 3082 | 0 | 0 | 0 | 0 | 2300 | 200 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4OLMST3 | OLMSTED CTR FURNITURE Q099-808MA1 | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 403 404 406 407 408 | P-0013 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | FMCP, QUEENS | OLMSTED CTR PARKING LOT | 2019 | 1200 | 160.46 | 1098 | 435 | 292 | 0 | 0 | 0 | 1985.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4OLMST4 | OLMSTED CTR RC (BUILDING) Q099-808MA | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 403 404 406 407 408 | P-0013 P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | OLMSTED CTR RC (BUILDING) Q099-808M...2/26/18 $284K (P-0013, FY18) XFER FR P-4OLMST1...2/26/18 $4K (P 0245Q, FY18) XFER FR P-4OLMST2...3/5/2018 $6K (P-0013 FY18) XFER FR P-40013CE...3/7/18 $100K (P-0245Q FY18) XFER FR P-4OLMST6...FY'19E $104K B/L SWITCH FROM P 0245Q TO P 0013...FY'19 TR IN $1.0M FR P-6517CBF...$1.0M TRF BACK TO P-6517CBF..FY20 JAN PLAN ROLLS: $737K P-0013 TO FY20...2/19/19 $57K P-0013 ADVANCED TO FY19 FROM FY20. OFFSET PROVIDED BY P-2PDBRC2 $57K P-1018 TO FY20...$467K P0245Q FR P-6517CBF...2/25/19 $3.4M ($3.1M P-1250 FY21, $300K P-1250 FY22) XFER FR P-6CW1250; $134K P-1018 FY19 XFER FR P-6CWASBR | 2019 | 16483 | 23329.34 | 1431 | 38 | 3837 | 300 | 0 | 0 | 28935.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4OVERLK | Overlook Park R/C Q299-117M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 403 | P-0245Q |  | DITMARS BLVD., 22 DR. BET. 97 ST. AND 100 ST., QUEENS | OVERLOOK PARK EAST ELMHURST DOG RUN | 2019 | 2860 | 190 | 930 | 0 | 0 | 770 | 0 | 0 | 1890 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PDLBRC | Lost Battalion Rec Ctr RC Q401-115M | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 400 | P-1018 P-0506 P-D019 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | QUEENS | LOST BATTALION REC CTR RC | 2019 | 4000 | 1240.55 | 6 | 0 | 0 | 12429 | 0 | 0 | 13675.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PLG12A | Reconstruction of plgr, Borough ofQueens (QG-112M) | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | P-0245Q | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | QUEENS BOROUGHWIDE | PLGR | 2019 | 50 | 146.39 | 0 | 0 | 0 | 0 | 0 | 0 | 146.39 | 0 | 0 | 0 | 0 | 0 | 38 | 0 | 38
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PLG13F | FY13 Queens Plgrd Multisite QG-1313M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-1018 P-D019 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RECONSTRUCTION OF PLAY EQUIPMENT, PAVEMENTS, FENCING, WATER SUPPLY, DRAINAGE, PLANTINGS, AND GENERAL SITE WORK AT CROWLEY PLAYGROUND, REAL GOOD PARK, AND FRANK D O'CONNOR PLAYGROUND | 2019 | 758 | 2710.76 | 0 | 0 | 0 | 259 | 0 | 0 | 2969.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PLG13H | FY13 Queens Plgrd Multisite QG-514MA | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D019 |  |  | RECONSTRUCTION OF PAVEMENT, FENCING, AND SIDEWALKS, NEW ADULT FITNESSEQUIPMENT AND BASKETBALL CTS, AND MISCELLANEOUS SITE WORK AT HOYT PLAYGROUND, TRIBOROUGH BRIDGE PLAYGROUND A, AND THE SIDEWALKS AROUND TRIBOROUGH BRIDGE PLAYGROUND A, B, C, AND D | 2019 | 600 | 2464.7 | 0 | 0 | 0 | 70 | 0 | 0 | 2534.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PNYT29 | PlaNYC FY18 Street Tree Queens CB 7,8,11 QG- | LAND ACQUISITION AND TREE PLANTING | 400 | P-0822 |  | PLANYC FY18 STREET TREE QUEENS CB 7,8,11 | PLANYC FY18 STREET TREE QUEENS CB 7,8,11 | 2019 | 2386 | 318 | 1750 | 1580 | 0 | 0 | 0 | 0 | 3648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PNYT30 | PlaNYC FY18 Street Tree Queens CB 12,13,14 | LAND ACQUISITION AND TREE PLANTING | 400 | P-0822 |  | PLANYC FY18 STREET TREE QUEENS CB 12,13,14 | PLANYC FY18 STREET TREE QUEENS CB 12,13,14 | 2019 | 2365 | 315 | 0 | 2990 | 0 | 0 | 0 | 0 | 3305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PNYT31 | PlaNYC FY19 Street Tree Queens CB 1-5 QG-716MR | LAND ACQUISITION AND TREE PLANTING | 400 | P-0822 |  | PLANYC FY19 STREET TREE QUEENS CB 1-5 QG-716MR | PLANYC FY19 STREET TREE QUEENS CB 1-5 QG-716MR | 2019 | 1618 | 0 | 990 | 0 | 0 | 0 | 0 | 0 | 990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PWOB01 | PWOB - FMCP Henry Hudson Entrance Q099-317M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | P-1018 |  |  | PARKS WITHOUT BORDERS SITE - FLUSHING MEADOWS CORONA PARK 111TH STREET (HENDRY HUDSON) ENTRANCE | 2019 | 3950 | 370 | 4060 | 452 | 0 | 0 | 0 | 0 | 4882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4QMULT2 | QUEENS MULTISITE | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D019 | PROJECT DELAYED DUE TO SCHEDULING OF UTILITY WORK |  | IDLEWILD PK CRICKET PITCH FIELD CONSTRUCTION; JOHN BOWNE HS BASEBALLFIELDS | 2019 | 225 | 0 | 0 | 0 | 0 | 0 | 0 | 225 | 225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4QNHSRC | QUEENS HISTORICAL SOCIETY CONSTRUCTION AND RENOVATION | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-Q245 |  |  | QUEENS HISTORICAL SOCIETY CONSTRUCTION AND RENOVATION IN QUEENS | 2019 | 0 | 0 | 0 | 800 | 0 | 0 | 0 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4QSTORE | QUEENS STOREHOUSE | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 400 | P-0245Q |  | QUEENS | QUEENS STOREHOUSE | 2019 | 14048 | 0 | 0 | 2767 | 0 | 12781 | 0 | 0 | 15548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4QSTRRF | Queens Storehouse Roof Reconstruction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-1249 |  | FLUSHING MEADOWS CORONA PARK | THIS PROJECT WILL BE FOR THE RECONSTRUCTION OF THE ROOF AT THE QUEENSSTOREHOUSE IN FLUSHING MEADOWS CORONA PARK. | 2019 | 2674 | 0 | 0 | 0 | 0 | 2100 | 0 | 0 | 2100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4QWCAMS | Queens Wildlife Center Aviary Mesh Replacement | ZOOS | 400 | P-Q245 |  |  | QUEENS WILDLIFE CENTER AVIARY MESH REPLACEMENT: REPLACE THE VINYL-COATED MESH AND REHABILITATE STRUCTURAL FAME OF DOME. | 2019 | 400 | 0 | 0 | 0 | 0 | 0 | 400 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4RAINE2 | Rainey Park | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 401 | P-D019 P-Q245 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RAINEY PARK | 2019 | 1200 | 0 | 114 | 0 | 0 | 3686 | 0 | 0 | 3800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4RDGEWD | Rosemary's Plgd R/C Q398-117M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D019 P-Q245 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RIDGEWOOD PARK | 2019 | 300 | 462.14 | 3195 | 0 | 0 | 0 | 0 | 0 | 3657.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4RECQNS | RC Sorrentino Rec Ctr in Queens Q446-116MA | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-1018 |  | RECON SORRENTINO REC CTR IN QUEENS | RECON SORRENTINO REC CTR IN QUEENS | 2019 | 735 | 1087.58 | 0 | 0 | 0 | 102 | 0 | 0 | 1189.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SAND02 | SANDY - Spring Creek Pk GI Resiliency Q165-116MA | LAND ACQUISITION AND TREE PLANTING | 400 | P-1018 |  |  | NATURAL AREA RESTORATION AND INSTALLATION OF A BERM/WALL SYSTEM AND STORMWATER GREENSTREETS AT SPRING CREEK PARK ADDITION, QUEENS | 2019 | 3370 | 209 | 0 | 0 | 0 | 0 | 0 | 0 | 209 | 97.92 | 2992 | 0 | 0 | 0 | 0 | 0 | 3089.92
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SHREAC | Shorefront Parkway Adventure Course | BEACHES AND BOARDWALKS | 400 | P-Q003 P-D019 |  |  | CONSTRUCTION OF AN ADVENTURE COURSE ALONG SHOREFRONT PARKWAY, BOROUGHOF QUEENS | 2019 | 408 | 0 | 0 | 0 | 537 | 46 | 0 | 0 | 583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SHREDP | Shorefront Parkway Dog Park | BEACHES AND BOARDWALKS | 400 | P-Q003 |  |  | CONSTRUCTION OF A DOG PARK ALONG SHOREFRONT PARKWAY, BOROUGH OF QUEENS | 2019 | 154 | 0 | 0 | 0 | 142 | 12 | 0 | 0 | 154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SHREPG | Shorefront Tot Playground and Plaza Area Q163-318M | BEACHES AND BOARDWALKS | 400 | P-Q003 |  |  | CONSTRUCTION OF A TOT PLAYGROUND AND PLAZA AREA ALONG SHOREFRONT PARKWAY, BOROUGH OF QUEENS | 2019 | 644 | 0 | 0 | 0 | 593 | 51 | 0 | 0 | 644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SHRESA | Shorefront Parkway Park Amenities | BEACHES AND BOARDWALKS | 400 | P-Q003 |  |  | CONSTRUCTION OF PARK AMENITIES ALONG SHOREFRONT PARKWAY, BOROUGH OF QUEENS | 2019 | 491 | 0 | 54 | 0 | 0 | 281 | 24 | 0 | 359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SHRESF | Shorefront Parkway Multi-Purpose Sports Field Cons. | BEACHES AND BOARDWALKS | 400 | P-Q003 |  |  | CONSTRUCTION OF A MULTI-PURPOSE SPORTS FIELD ALONG SHOREFRONT PARKWAY, BOROUGH OF QUEENS | 2019 | 728 | 51.22 | 0 | 0 | 0 | 677 | 0 | 0 | 728.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SNDPIP | Sandpiper Plgd RC (Q163-215M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | QUEENS | PER VC 10/30/18 $2K P1018 FISCAL YEAR OFFSET W/ P-414TRB2 FY20 TO FY19...FY20 JAN ROLL BACK $178K P1018 TO FY19... | 2019 | 3070 | 5185.95 | 601 | 0 | 0 | 98 | 0 | 0 | 5884.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SUNRSE | Sunrise Stables Acquisition | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D019 |  | SOUTH CONDUIT AND LINDEN | SUNRISE STABLES ACQUISITION | 2019 | 636 | 0 | 10 | 0 | 0 | 490 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRE18A | FY18 Street Tree Queens CBs 1-5 QG- | LAND ACQUISITION AND TREE PLANTING | 400 | P-Q245 |  | FY18 STREET TREE QUEENS CBS 1-5 | FY18 STREET TREE QUEENS CBS 1-5 | 2019 | 2660 | 345 | 0 | 0 | 0 | 500 | 0 | 0 | 845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRE18B | FY18 Street Tree Queens CBs 6,9,10QG- | LAND ACQUISITION AND TREE PLANTING | 400 | P-1018 |  | FY18 STREET TREE QUEENS CBS 6,9,10 | FY18 STREET TREE QUEENS CBS 6,9,10 | 2019 | 931 | 121 | 0 | 0 | 0 | 0 | 0 | 0 | 121 | 0 | 0 | 0 | 0 | 1180 | 0 | 0 | 1180
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRE19A | FY19 Street Tree Queens CBs 6,9,10 QG-816MR | LAND ACQUISITION AND TREE PLANTING | 400 | P-0822 |  | FY19 STREET TREE QUEENS CBS 6,9,10 QG-816MR | FY19 STREET TREE QUEENS CBS 6,9,10 QG-816MR | 2019 | 1608 | 0 | 990 | 0 | 0 | 0 | 0 | 0 | 990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRE19B | FY19 Street Tree Queens CBs 7,8,11 QG-916MR | LAND ACQUISITION AND TREE PLANTING | 400 | P-0822 |  | FY19 STREET TREE QUEENS CBS 7,8,11 QG-916MR | FY19 STREET TREE QUEENS CBS 7,8,11 QG-916MR | 2019 | 1530 | 0 | 990 | 0 | 0 | 0 | 0 | 0 | 990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRE20A | FY20 Street Tree Queens CBs 1-6 QG-419M | LAND ACQUISITION AND TREE PLANTING | 400 | P-0822 P-D822 |  | FY20 STREET TREE QUEENS CBS 1-6 QG-419M | FY20 STREET TREE QUEENS CBS 1-6 QG-419M | 2019 | 2057 | 0 | 0 | 0 | 2057 | 0 | 0 | 0 | 2057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRE20B | FY20 Street Tree Queens CBs 7,8,11 QG-219M | LAND ACQUISITION AND TREE PLANTING | 400 | P-0822 WP-0169 |  | FY20 STREET TREE QUEENS CBS 7,8,11 QG-219M | FY20 STREET TREE QUEENS CBS 7,8,11 QG-219M | 2019 | 1977 | 0 | 0 | 0 | 1977 | 0 | 0 | 0 | 1977 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRE20C | FY20 Street Tree Queens CBs 9,10,14 QG-519M | LAND ACQUISITION AND TREE PLANTING | 400 | P-0822 |  | FY20 STREET TREE QUEENS CBS 9,10,14 QG-519M | FY20 STREET TREE QUEENS CBS 9,10,14 QG-519M | 2019 | 2052 | 0 | 0 | 0 | 2052 | 0 | 0 | 0 | 2052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRE20D | FY20 Street Tree Queens CBs 12-13 QG-319M | LAND ACQUISITION AND TREE PLANTING | 400 | P-0822 |  | FY20 STREET TREE QUEENS CBS 12-13 QG-319M | FY20 STREET TREE QUEENS CBS 12-13 QG-319M | 2019 | 2843 | 0 | 0 | 0 | 2843 | 0 | 0 | 0 | 2843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRS19A | QueensTree-Damaged Sidewalk R/C CB 8,11-14 | LAND ACQUISITION AND TREE PLANTING | 400 | P-1331 |  | QUEENSTREE-DAMAGED SIDEWALK R/C CB 8,11-14 | QUEENSTREE-DAMAGED SIDEWALK R/C CB 8,11-14 | 2019 | 1540 | 0 | 0 | 1540 | 0 | 0 | 0 | 0 | 1540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRSD19 | QueensTree-Damaged Sidewalk R/C CB 1-7,9,10 | LAND ACQUISITION AND TREE PLANTING | 400 | P-1331 P-D019 |  | QUEENSTREE-DAMAGED SIDEWALK R/C | QUEENSTREE-DAMAGED SIDEWALK R/C | 2019 | 1890 | 0 | 1890 | 0 | 0 | 0 | 0 | 0 | 1890 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4VIETNA | VIETNAM VETERAN MEMORIAL - ELMHURST PARK Q492-117M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D019 P-Q245 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | FORMER KEYSPAN GAS TANK PROPERTY ON 57TH AVENUE BETWEEN 74TH AND 80THSTREETS | CONSTRUCT WAR MEMORIAL ON SITE OF FORMER KEYSPAN GAS TANK PROPERTY ON57TH AVE BET 74 AND 80 STREETS. | 2019 | 500 | 2459.11 | 235 | 0 | 564 | 0 | 0 | 0 | 3258.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4WPJAMC | Walk to Park NYCHA Pomonok Houses Construction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-0245Q |  |  | WALK TO PARK NYCHA SOUTH JAMAICA II PLAYGROUND CONSTRUCTION, BOROUGH OF QUEENS | 2019 | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4WPWSDE | Walk to Park NYCHA Woodside Playground Construction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-0245Q |  |  | WALK TO PARK NYCHA WOODSIDE PLAYGROUND CONSTRUCTION, BOROUGH OF QUEENS | 2019 | 1200 | 0 | 0 | 0 | 0 | 1200 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-6BLD14A | FY14 BUILDINGS-RC OF C/S & FACILTIES VAR PKS LOC QG-1613MA | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | P-1018 |  |  | FY14 BUILDINGS-RC OF C/S & FACILTIES AT VAR PKS & RECR LOC | 2019 | 1154 | 2149.13 | 83 | 0 | 0 | 29 | 0 | 0 | 2261.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-6BLD14B | FY14 BUILDINGS-RC OF C/S & FACILTIES AT VAR PKS & RECR LOC | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | P-D019 P-1018 P-Q245 |  |  | FY14 BUILDINGS-RC OF C/S & FACILTIES AT VAR PKS & RECR LOC | 2019 | 1674 | 2512.8 | 0 | 0 | 0 | 133 | 0 | 0 | 2645.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-6BLDG13 | RC OF C/S & FACILITIES AT VARIOUS PKS QG-1413M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | P-1018 |  |  | BOWNE PK CS, SPRINGFIELD NORTH PK PS231 CS, SPRINGFIELD PK CS | 2019 | 1730 | 3229.57 | 265 | 0 | 0 | 135 | 0 | 0 | 3629.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-6ROOFQN | Recon roofs at Forest Pk garage & Oak Ridge QG-918M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-1249 |  | CITYWIDE | RECON ROOFS AT FOREST PK GARAGE & OAK RIDGE IN FOREST PARK | 2019 | 3774 | 0 | 0 | 3075 | 0 | 0 | 0 | 0 | 3075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | RE2544DR2 | RC 44TH DRIVE PIER QG-47250-108MA | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 402 | RE-0025 SE-0002Q | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | LONG ISLAND CITY - QUEENS | 44TH STREET PIER | 2019 | 2020 | 8716.06 | 83 | 0 | 0 | 0 | 0 | 0 | 8799.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-02 | SANDY- Emergency Storm Make Safe - Rockaway Beach Q162-213M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 414 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | EMERGENCY-STORM MAKE SAFE OF ROCKAWAY BEACH | 2019 | 2531 | 912.82 | 0 | 0 | 0 | 46 | 0 | 0 | 958.82 | 7214.87 | 0 | 0 | 0 | 417 | 0 | 0 | 7631.87
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-08 | PNP Socrates Sculpture Park | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 401 | P-1018 |  | QUEENS | QUEENS SOCRATES SCULPTURE PARK | 2019 | 206 | 0 | 6 | 73 | 0 | 24 | 2 | 0 | 105 | 0 | 50 | 658 | 0 | 217 | 18 | 0 | 943
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-10 | Ralph DeMarco Pk, Shoreline R/C Q004-213M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | RALPH DEMARCO PK, QUEENS | SANDY - R/C OF SHORELINE IN RALPH DEMARCO PK, TYPE 3 | 2019 | 92 | 220.1 | 0 | 911 | 0 | 538 | 0 | 0 | 1669.1 | 398.64 | 0 | 5750 | 0 | 0 | 0 | 0 | 6148.64
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-11 | SANDY- R/C of Rockaway Garage | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-1018 |  | ROCKAWAY GARAGE , QUEENS | R/C OF ARCHITECTURAL AND MACHANICAL COMPONENTS AT THE ROCKAWAY GARAGE | 2019 | 843 | 0 | 0 | 0 | 0 | 0 | 0 | 514 | 514 | 0 | 0 | 0 | 0 | 0 | 0 | 321 | 321
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-12 | SANDY- Joe Michael's Mile Promenade Q135-214M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 28 ROAD AND CROSS ISLAND PKWY, QUEENS | R/C OF THE PROMENADE(JOE MICHAEL'S MILE) | 2019 | 222 | 288.73 | 5 | 0 | 5 | 0 | 0 | 0 | 298.73 | 123.83 | 88 | 0 | 0 | 0 | 0 | 0 | 211.83
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-13 | SANDY-Rockaway Beach roller hockey rink - Type 3 Q163-114M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-1018 |  |  | SANDY-ROCKAWAY BEACH: LONG TERM RC | 2019 | 446 | 31.03 | 0 | 0 | 0 | 45 | 0 | 0 | 76.03 | 599.48 | 0 | 0 | 48 | 0 | 0 | 0 | 647.48
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-17 | SANDY - Rockaway Beach Skate Park Q163-111MA | BEACHES AND BOARDWALKS | 400 | P-1018 |  | SANDY -ROCKAWAY BEACH SKATE PK Q163-111M | SANDY -ROCKAWAY BEACH SKATE PK Q163-111M | 2019 | 1584 | 55.11 | 215 | 0 | 0 | 0 | 0 | 0 | 270.11 | 168.38 | 1946 | 0 | 0 | 0 | 0 | 0 | 2114.38
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-18 | SANDY - Tribute Park Reconstruction Q028-116M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-1018 |  | SANDY - TRIBUTE PK AND FLIGHT 587 MEMORIAL | SANDY - TRIBUTE PK AND FLIGHT 587 MEMORIAL | 2019 | 476 | 352.16 | 0 | 0 | 0 | 7 | 0 | 0 | 359.16 | 508.84 | 0 | 0 | 0 | 50 | 0 | 0 | 558.84
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-21 | SANDY-FOREST PARK GREENHOUSE BROKEN GLASS REPLACEMENT | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | P-1018 |  |  | SANDY-FOREST PARK GREENHOUSE BROKEN GLASS REPLACEMENT | 2019 | 253 | 0.28 | 0 | 0 | 0 | 26 | 0 | 0 | 26.28 | 0 | 0 | 0 | 0 | 234 | 0 | 0 | 234
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-22 | SANDY - Rockaway Beach Shorefront Pkwy Handball Ct Q163-315M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BEACH 105 STREET AND BEACH 102 STREET, SOUTH OF SHORE FRONT PARKWAY AT ROCKAWAY BCH | SANDY-ROCKAWAY BCH-R/C OF 8 HANDBALL COURTS | 2019 | 1658 | 52.26 | 277 | 0 | 0 | 34 | 0 | 0 | 363.26 | 161.58 | 2493 | 0 | 0 | 297 | 0 | 0 | 2951.58
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-23 | Rockaway Beach Sports Areas | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 400 | P-1018 |  |  | ROCKAWAY BEACH SPORTS AREAS | 2019 | 10357 | 0 | 0 | 0 | 0 | 0 | 0 | 161 | 161 | 0 | 0 | 0 | 0 | 0 | 0 | 1456 | 1456
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-25 | Bayside Marina Reconstruction (Q135-117M) | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 400 | P-1018 |  |  | BAYSIDE MARINA | 2019 | 1939 | 336.55 | 0 | 0 | 0 | 121 | 0 | 0 | 457.55 | 373.96 | 0 | 1050 | 0 | 37 | 0 | 0 | 1460.96
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-26 | World's Fair Marina | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 400 | P-1018 |  |  | WORLD'S FAIR MARINA | 2019 | 7081 | 263.24 | 0 | 0 | 0 | 768 | 0 | 0 | 1031.24 | 569.24 | 0 | 0 | 0 | 6890 | 0 | 0 | 7459.24
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-27 | Joe Michael's Mile/Little Bay Revetment | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-1018 |  |  | JOE MICHAEL'S MILE/LITTLE BAY REVETMENT | 2019 | 457 | 0 | 0 | 46 | 0 | 0 | 0 | 0 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 411 | 411
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-29 | FMCP Electrical Repairs | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-1018 |  |  | FMCP ELECTRICAL REPAIRS | 2019 | 15440 | 0 | 0 | 0 | 0 | 1421 | 123 | 0 | 1544 | 0 | 0 | 0 | 0 | 12785 | 1111 | 0 | 13896
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-32 | SANDY - Beach 94th Street Performance Space Construction | BEACHES AND BOARDWALKS | 400 | P-1018 |  |  | CONSTRUCTION OF A PERFORMANCE SPACE ON BEACH 94TH STREET, IN ROCKAWAYBEACH, BOROUGH OF QUEENS | 2019 | 3532 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 68 | 313.09 | 30 | 2550 | 0 | 107 | 0 | 0 | 3000.09
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-33 | SANDY - Shorefront Park Multi-Purpose Sports Field Cons. | BEACHES AND BOARDWALKS | 400 | P-1018 |  |  | SHOREFRONT PARK MULTI-PURPOSE SPORTS FIELD CONSTRUCTION | 2019 | 8448 | 76.88 | 0 | 0 | 0 | 25 | 0 | 0 | 101.88 | 494.11 | 0 | 0 | 0 | 6528 | 0 | 0 | 7022.11
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-34 | SANDY - Shorefront Labyrinth and Seating Area | BEACHES AND BOARDWALKS | 400 | P-1018 |  |  | SHOREFRONT LABYRINTH AND SEATING AREA CONSTRUCTION - BOROUGH OF QUEENS | 2019 | 2398 | 55.54 | 0 | 0 | 142 | 12 | 0 | 0 | 209.54 | 183.09 | 0 | 0 | 1481 | 128 | 0 | 0 | 1792.09
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-35 | SANDY - Shorefront Tot Playground and Plaza Area Q163-318M | BEACHES AND BOARDWALKS | 400 | P-1018 |  |  | SHOREFRONT TOT PLAYGROUND AND PLAZA AREA CONSTRUCTION, BOROUGH OF QUEENS | 2019 | 10141 | 360 | 5 | 0 | 0 | 328 | 0 | 0 | 693 | 0 | 111 | 0 | 0 | 6820 | 0 | 0 | 6931
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-36 | SANDY - Shorefront Parkway Adventure Course Q163-218M | BEACHES AND BOARDWALKS | 400 | P-1018 |  |  | SHOREFRONT PARKWAY ADVENTURE COURSE CONSTRUCTION, AT ROCKAWAY BEACH AND BOARDWALK, BOROUGH OF QUEENS | 2019 | 4890 | 204 | 5 | 0 | 0 | 241 | 0 | 0 | 450 | 0 | 79 | 0 | 0 | 3749 | 0 | 0 | 3828
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-37 | SANDY - Beach 88th Street Park Construction | BEACHES AND BOARDWALKS | 400 | P-1018 |  |  | CONSTRUCTION OF A PARK ON BEACH 88TH STREET, BOROUGH OF QUEENS | 2019 | 9172 | 114 | 0 | 0 | 0 | 0 | 0 | 0 | 114 | 691.97 | 0 | 0 | 6521 | 567 | 0 | 0 | 7779.97
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-38 | SANDY - Beach 24th to Beach 25th Street Ramp | BEACHES AND BOARDWALKS | 400 | P-1018 |  |  | CONSTRUCTION OF A RAMP BETWEEN BEACH 24TH AND BEACH 25TH STREETS, BOROUGH OF QUEENS | 2019 | 1473 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 150.27 | 0 | 0 | 1012 | 88 | 0 | 0 | 1250.27
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-39 | SANDY - Rockaway Community Park Shoreline R/C | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 414 | P-1018 |  |  | RECONSTRUCTION OF THE SHORELINE AT ROCKAWAY COMMUNITY PARK, BOROUGH OF QUEENS | 2019 | 13819 | 157 | 0 | 0 | 0 | 0 | 0 | 0 | 157 | 948.34 | 0 | 0 | 9911 | 861 | 0 | 0 | 11720.34
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-40 | SANDY - New Rockaway Operational Headquarters | BEACHES AND BOARDWALKS | 400 | P-1018 |  |  | DEMOLITION AND CONSTRUCTION OF A NEW OPERATIONS HEADQUARTERS AT ROCKAWAY, BOROUGH OF QUEENS | 2019 | 14520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2178 | 12342 | 0 | 0 | 0 | 14520
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-41 | SANDY - Michaelis-Bayswater Park R/C | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 414 | P-1018 |  |  | RECONSTRUCTION OF BAYSWATER PARK, BOROUGH OF QUEENS | 2019 | 55602 | 296 | 0 | 0 | 0 | 0 | 0 | 0 | 296 | 3160.37 | 0 | 0 | 47702 | 4148 | 0 | 0 | 55010.37
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-42 | SANDY - Shorefront Parkway Dog Park | BEACHES AND BOARDWALKS | 400 | P-1018 |  |  | CONSTRUCTION OF A DOG PARK ON SHOREFRONT PARKWAY, BOROUGH OF QUEENS | 2019 | 1885 | 136 | 0 | 0 | 82 | 7 | 0 | 0 | 225 | 0 | 0 | 0 | 1152 | 100 | 0 | 0 | 1252
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-43 | SANDY - Queens B | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-1018 |  |  | SANDY - QUEENS B | 2019 | 1071 | 0 | 0 | 0 | 0 | 0 | 0 | 107 | 107 | 0 | 0 | 0 | 0 | 0 | 0 | 964 | 964
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-44 | SANDY - Shorefront Parkway Park Amenities | BEACHES AND BOARDWALKS | 400 | P-1018 |  |  | CONSTRUCTION OF PARK AMENITIES ALONG SHOREFRONT PARKWAY, BOROUGH OF QUEENS | 2019 | 3611 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 3315 | 288 | 0 | 3603
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-45 | SANDY - Thursby Basin Park Construction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-1018 |  |  | CONSTRUCTION OF THURSBY BASIN PARK, AT ROCKAWAY BEACH AND BOARDWALK, IN THE BOROUGH OF QUEENS | 2019 | 12025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 958 | 0 | 0 | 10093 | 874 | 0 | 11925
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY6-08 | Asser Levy HMP (Hazard Mitigation Plan ) Funding | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-1018 |  |  | SANDY-SAFETY SURFACE & PAVEMENTS (NON-EMERGENCY) | 2019 | 3732 | 0 | 0 | 0 | 0 | 0 | 0 | 75 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 670 | 670
20190425 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY6-19 | Two Park Shoreline Protection | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-1018 |  |  | TWO PARK SHORELINE PROTECTION | 2019 | 532 | 0 | 0 | 0 | 0 | 0 | 0 | 53 | 53 | 0 | 0 | 0 | 0 | 0 | 0 | 479 | 479
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | ACEDOS503 | Betts Boilers Replacement | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 402 | S-0136 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | THE WORKED PLANNED FOR THIS PROJECT WOULD INCLUDE THE REMOVAL OF THE 2 OLD OVERSIZED 2100HP GAS/#6 TAMPELLA BOILERS, AND REPLACE THEM WITH 3 APPROPRIATELY SIZED 750HP CLEAVER BROOKS DRY BACK FIRETUBE GAS/#2 BOILERS (TWO TO RUN UNDER NORMAL OPERATING CONDITIONS, AND ONE FOR BACK UP). BY SWITCHING OVER TO THESE HIGHER EFFICIENCY BOILERS WILL REMOVE OUR DEPENANCY ON #6 FUEL OIL, WHICH THE DEPARTMENT'S WAIVER IS EXPIRING IN APRIL OF THIS YEAR. OUR FAILURE TO BE ABLE TO SWITCH OVER TO OILWHEN NATIONAL GRID REQUIRES US WILL RESULT IN A MORE EXPENSIVE THERM RATE AND POSSIBLE FINES. HAVING THE NEW BOILERS ON #2 OIL IS A DRASTICSTEP IN CLEANING THE CITY'S AIR OF CO2 EMISSIONS. THE NEW BOILERS WILL FEATURE STACK ECONOMIZERS WHICH INCREASE THE SYSTEM'S EFFICIENCY BY +2% BY PREHEATING THE MAKEUP WATER AND ALSO ELIMINATE THE ELECTRIAL HOT | 2019 | 5105 | 7300.34 | 997 | 0 | 0 | 0 | 0 | 0 | 8297.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO277ELV2 | 25-10 COURT HOUSE SQ.- ELEVATORS | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 401 | CO-0264 CO-0277 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | 25-10 COURT HOUSE SQ.- ELEVATORS | 2019 | 1056 | 3370.38 | 150 | 909 | 0 | 0 | 0 | 0 | 4429.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO277FA | 25-10 COURT HOUSE SQ.- FIRE ALARM SYSTEM | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 402 | CO-0277 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | 25-10 COURT HOUSE SQUARE - FIRE ALARM SYSTEM | 2019 | 276 | 0 | 0 | 0 | 0 | 5462 | 0 | 2100 | 7562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO296ELEC | 125-01 QUEENS BLVD - ELECTRICAL UPGRADES | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 409 | CO-0296 |  |  | 125-01 QUEENS BLVD - ELECTRICAL UPGRADES | 2019 | 51044 | 2688.52 | 4923 | 0 | 43076 | 0 | 0 | 0 | 50687.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO296RF | 125-01 QUEENS BLVD.- ROOF | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 409 | CO-0296 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | 125-01 QUEENS BLVD.- ROOF | 2019 | 3359 | 35 | 397 | 0 | 2872 | 0 | 0 | 0 | 3304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO299EXT2 | 89-17 SUTPHIN BLVD.- PLAZA/SIDEWALK RECONSTRUCTION | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 412 | CO-0299 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | PLAZA RENOVATION | 2019 | 7006 | 0 | 557 | 0 | 0 | 0 | 5812 | 0 | 6369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO300ELV2 | 88-11 SUTPHIN BLVD.- ELEVATOR | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 412 | CO-0300 |  |  | 88-11 SUTPHIN BLVD.- ELEVATOR | 2019 | 7445 | 14178.04 | 64 | 0 | 0 | 0 | 0 | 0 | 14242.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CS-FB-LLD | Flushing Bay Low Lying Sewer Diversion | WATER QUALITY MANDATES | 400 403 407 | SE-0002Q WM-0006 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | CONSTRUCTION OF FLUSHING BAY LOW LEVEL SEWER DIVISION | 2019 | 6730 | 7043.99 | 0 | 0 | 0 | 950 | 0 | 0 | 7993.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | DOTSEQ01 | Southeast Queens - DOT Priority Grids Group 1 (SEQPGRD1) | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 400 | SE-0200Q WM-0001 WP-0169 SE-0002Q |  |  | SOUTHEAST QUEENS PROGRAM JOINT PROJECT BETWEEN DOT AND DEP TO IMPROVEDRAINAGE CONDITIONS - GROUP 1, AS DETERMINED BY DOT. | 2019 | 12229 | 0 | 364 | 11324 | 0 | 0 | 0 | 0 | 11688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | DOTSEQ02 | Southeast Queens - DOT Priority Grids Group 2 (SEQPGRD2) | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 400 | SE-0200Q WM-0001 WP-0169 SE-0002Q |  |  | OUTHEAST QUEENS PROGRAM JOINT PROJECT BETWEEN DOT AND DEP TO IMPROVE DRAINAGE CONDITIONS - GROUP 2, AS DETERMINED BY DOT. | 2019 | 11085 | 0 | 384 | 0 | 10702 | 0 | 0 | 0 | 11086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | E12-0037 | DSNY Queens West Cent Repair Shop: Fr.Kills, BK W11G- EE Upg | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 401 | PU-0025 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | QUEENS WEST CENTRAL REPAIR SHOP ENERGY UPGRADES | 2019 | 8252 | 6352.12 | 138 | 589 | 0 | 0 | 0 | 0 | 7079.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0002 | DCAS - Queens Civil Court | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 412 | PU-0025 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | QUEENS CIVIL COURT | 2019 | 3005 | 444.64 | 0 | 3842 | 0 | 0 | 0 | 0 | 4286.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0004 | DSNY - Queens 7 District Garage Annex | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 407 | PU-0025 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | QUEENS 7 DISTRICT GARAGE ANNEX | 2019 | 2162 | 372.2 | 2236 | 24 | 0 | 0 | 0 | 0 | 2632.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0007 | DOT - Brookville Yard (Rosedale Arterials/Fleet Services) | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 401 | PU-0025 |  |  | BROOKVILLE YARD (ROSEDALE ARTERIALS/FLEET SERVICES) - LIGHTING UPGRADE | 2019 | 300 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0009 | NYPD - 620 Circle Drive - Lighting and HVAC Upgrades | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 401 | PU-0025 |  |  | DDC - 620 CIRCLE DRIVE - LIGHTING AND HVAC UPGRADES | 2019 | 300 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | F175EC268 | NEW FIREHOUSE - EC268 | NEW FACILITIES AND RENOVATIONS | 414 | F-0175 |  |  | NEW FIREHOUSE - EC268 | 2019 | 22000 | 0 | 0 | 3600 | 0 | 15937 | 0 | 0 | 19537 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | F175EC293 | GUT REHAB OF ENGINE COMPANY 293 | NEW FACILITIES AND RENOVATIONS | 409 | F-0175 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | GUT REHAB OF ENGINE COMPANY 293 | 2019 | 13272 | 11906.29 | 674 | 0 | 0 | 0 | 0 | 0 | 12580.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCBB26-01 | GI - CONS OF ROW GI IN BOWERY BAY CSO TRIBUTARY AREAS | GREEN INFRASTRUCTURE PROGRAM | 400 | WP-0169 EP-0007 |  |  | CONSTRUCTION OF RIGHT-OF-WAY GREEN INFRASTRUCTURE IN THE BOWERY BAY CSO TRIBUTARY AREAS | 2019 | 9630 | 0 | 9630 | 0 | 0 | 0 | 0 | 0 | 9630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCJA03-2A | GI - CONS OF ROW GI IN CSO TRIBUTARY AREA JAM-003, PH 2A | GREEN INFRASTRUCTURE PROGRAM | 400 410 412 413 414 | EP-0007 WP-0169 |  |  | GI - CONS OF ROW GI IN CSO TRIBUTARY AREA JAM-003, PH 2A | 2019 | 13161 | 0 | 12962 | 0 | 0 | 0 | 0 | 0 | 12962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCJA03-2B | GI - CONS OF ROW GI IN JAMAICA BAY CSO AREAS JAM-03 & JAM-3A | GREEN INFRASTRUCTURE PROGRAM | 400 | WP-0169 EP-0007 |  |  | CONSTRUCTION OF RIGHT-OF-WAY GREEN INFRASTRUCTURE IN THE JAMAICA BAY CSO AREAS JAM-003 AND JAM-003A | 2019 | 20080 | 0 | 0 | 20080 | 0 | 0 | 0 | 0 | 20080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCJA03-3A | GI - Cons of ROW Bioswales & Stormwater GS in JAM-003, 3A | GREEN INFRASTRUCTURE PROGRAM | 400 410 412 413 414 | WP-0169 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | GI - DESIGN & CONSTRUCTION OF RIGHTOF WAY BIOSWALES AND STORMAWATER GREENSTREETS AT CSO TRIBUTARY AREA JAM-003, 003A IN THE QUEENS | 2019 | 16536 | 11044.45 | 2481 | 0 | 0 | 2922 | 0 | 0 | 16447.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCJA03-3B | GI - CONS OF ROW GI IN JAMAICA BAY CSO AREAS JAM-03 & JAM-3A | GREEN INFRASTRUCTURE PROGRAM | 400 | WP-0169 EP-0007 |  |  | CONSTRUCTION OF RIGHT-OF-WAY GREEN INFRASTRUCTURE IN THE JAMAICA BAY CSO AREAS JAM-003 AND JAM-003A | 2019 | 20497 | 0 | 0 | 20497 | 0 | 0 | 0 | 0 | 20497 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCNC77-02 | GI - GREEN INFRASTRUCTURE IN NEWTOWN CREEK AREA | GREEN INFRASTRUCTURE PROGRAM | 402 | WP-0169 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | GI - GREEN INFRASTRUCTURE IN NEWTOWN CREEK AREA | GI - GREEN INFRASTRUCTURE IN NEWTOWN CREEK AREA | 2019 | 6040 | 5899.81 | 404 | 0 | 0 | 0 | 0 | 0 | 6303.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCTI10-02 | CONS OF ROW GI PHASE 2 IN FLUSHING CREEK CSO AREA TI-010 | GREEN INFRASTRUCTURE PROGRAM | 400 | WP-0169 EP-0007 |  |  | GI - CONSTRUCTION OF ROW GREEN INFRASTRUCTURE PHASE 2 OF THE FLUSHINGCREEK CSO TRIBUTARY AREA TI-10, | 2019 | 27799 | 0 | 0 | 27799 | 0 | 0 | 0 | 0 | 27799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCTI10-03 | CONS OF ROW GI PHASE 3 IN FLUSHING CREEK CSO AREA TI-010 | GREEN INFRASTRUCTURE PROGRAM | 400 | EP-0007 WP-0169 |  |  | GI - CONSTRUCTION OF ROW GREEN INFRASTRUCTURE PHASE 3 OF THE FLUSHINGCREEK CSO TRIBUTARY AREA TI-10, | 2019 | 28272 | 0 | 0 | 28272 | 0 | 0 | 0 | 0 | 28272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCTI10-1A | CONS OF ROW GI FLUSHING CRK CSO TRIB AREA TI-10, ST 1, PH A | GREEN INFRASTRUCTURE PROGRAM | 400 | WP-0169 EP-0007 |  |  | CONSTRUCTION OF ROW GREEN INFRASTRUCTURE IN FLUSHING CREEK CSO TRIBUTARY AREA TI-10, STAGE 1, PHASE A | 2019 | 14000 | 0 | 14087 | 0 | 0 | 0 | 0 | 0 | 14087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCTI10-1B | CONS OF ROW GI FLUSHING CRK CSO TRIB AREA TI-10, ST 1, PH B | GREEN INFRASTRUCTURE PROGRAM | 400 | WP-0169 EP-0007 |  |  | CONSTRUCTION OF ROW GREEN INFRASTRUCTURE IN FLUSHING CREEK CSO TRIBUTARY AREA TI-10, STAGE1, PHASE B | 2019 | 18547 | 0 | 0 | 18547 | 0 | 0 | 0 | 0 | 18547 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCTI10-2A | CONS OF ROW GI FLUSHING CRK CSO TRIB AREA TI-10, ST 2, PH A | GREEN INFRASTRUCTURE PROGRAM | 400 | WP-0169 |  |  | CONSTRUCTION OF ROW GREEN INFRASTRUCTURE IN FLUSHING CREEK CSO TRIBUTARY AREA T-10, STAGE 2, PHASE A | 2019 | 14000 | 0 | 0 | 0 | 35500 | 0 | 0 | 0 | 35500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCTI10-3A | CONS OF ROW GI FLUSHING CRK CSO TRIB AREA TI-10, ST 3, PH A | GREEN INFRASTRUCTURE PROGRAM | 400 | WP-0169 |  |  | CONSTRUCTION OF ROW GREEN INFRASTRUCTURE IN FLUSHING CREEK CSO TRIBUTARY AREA TI-10, STAGE 3, PHASE A | 2019 | 14000 | 0 | 0 | 0 | 14000 | 0 | 0 | 0 | 14000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCTI10-4A | CONS OF ROW GI FLUSHING CRK CSO TRIB AREA TI-10, ST 4, PH A | GREEN INFRASTRUCTURE PROGRAM | 400 | WP-0169 EP-0007 |  |  | CONSTRUCTION OF ROW GREEN INFRASTRUCTURE IN FLUSHING CREEK CSO TRIBUTARY AREA TI-10, STAGE 4, PHASE A | 2019 | 10500 | 0 | 0 | 35500 | 0 | 0 | 0 | 0 | 35500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCTI10-4B | CONS OF ROW GI IN PHASE 4 FLUSHING CRK CSO TRIB AREA TI-10 | GREEN INFRASTRUCTURE PROGRAM | 400 | WP-0169 EP-0007 |  |  | CONSTRUCTION OF ROW GREEN INFRASTRUCTURE IN PHASE 4 OF FLUSHING CREEK CSO TRIBUTARY AREA TI-10 | 2019 | 27600 | 0 | 0 | 27600 | 0 | 0 | 0 | 0 | 27600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCTI11-02 | GI-Construct ROW Bioswales Stormwater Greenstreets in TI-011 | GREEN INFRASTRUCTURE PROGRAM | 400 | WP-0169 EP-0007 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | GI - CONSTRUCTION OF RIGHT-OF-WAY BIOSWALES AND STORMWATER GREENSTREETS IN TI-011 | 2019 | 4070 | 9276.96 | 2375 | 192 | 0 | 67 | 0 | 0 | 11910.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GQTI03-23 | GI - GREEN INFRASTRUCTURE IN TI-003 & TI-023 EAST RIVER CSO | GREEN INFRASTRUCTURE PROGRAM | 400 | WP-0169 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | GI - GREEN INFRASTRUCTURE IN TI-003 & TI-023 EAST RIVER CSO | 2019 | 18714 | 8813.61 | 0 | 0 | 0 | 10000 | 0 | 0 | 18813.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HBPED216S | PED BRIDGE - 216 ST (Q) | FAIR BRIDGES | 400 411 | HB-0215 SE-1000 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | PED BRIDGE - 216 ST (Q) | PED BRIDGE - 216 ST (Q) | 2019 | 6321 | 1847.38 | 1503 | 0 | 0 | 0 | 0 | 0 | 3350.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HBPED800Q | PED BRIDGE - PORPOISE BRIDGE AND TIDE GATE | FAIR BRIDGES | 400 | P-0245Q | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | PED BRIDGE - PORPOISE BRIDGE AND TIDE GATE | PED BRIDGE - PORPOISE BRIDGE AND TIDE GATE | 2019 | 65656 | 7652.4 | 0 | 0 | 50692 | 0 | 0 | 0 | 58344.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HD-153C2 | EDGEMERE (PHASE C2) | NEIGHBORHOOD-BASED HOUSING INITIATIVES | 499 | HW-0061 F-0001 HD-0153 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | EDGEMERE (PHASE C2) | EDGEMERE (PHASE C2) | 2019 | 9096 | 14257.37 | 89 | 0 | 0 | 26 | 0 | 0 | 14372.37 | 176.06 | 0 | 0 | 0 | 0 | 0 | 0 | 176.06
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BDFA | BORDEN AVENUE FIRE SAFETY | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 |  |  | BORDEN AVENUE FIRE SAFETY | 2019 | 2008 | 162.58 | 350 | 0 | 0 | 0 | 0 | 0 | 512.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115BWFA | BRIARWOOD - FIRE ALARM UPGRADE | SHELTERS FOR HOMELESS FAMILIES |  | HH-0115 |  |  | BRIARWOOD - FIRE ALARM UPGRADE | 2019 | 1082 | 1003.59 | 235 | 0 | 0 | 0 | 0 | 0 | 1238.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115JCTV | JENNIE CLARKE - CCTV | SHELTERS FOR HOMELESS FAMILIES |  | HH-0115 |  |  | JENNIE CLARKE - CCTV | 2019 | 357 | 0 | 0 | 0 | 557 | 0 | 0 | 0 | 557 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115JWTV | JAMAICA FAMILY SHELTER CCTV | SHELTERS FOR HOMELESS FAMILIES |  | HH-0115 |  |  | CCTV | 2019 | 552 | 45 | 0 | 50 | 457 | 0 | 0 | 0 | 552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115SGFA | SPRINGFIELD GARDEN - FIRE ALARM SYSTEM UPGRADE | SHELTERS FOR HOMELESS FAMILIES |  | HH-0115 |  |  | SPRINGFIELD GARDEN - FIRE ALARM SYSTEM UPGRADE | 2019 | 408 | 709.35 | 107 | 300 | 0 | 0 | 0 | 0 | 1116.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82CORHC | Corona Health Center-Exterior Facade, Basement and Lobby | CLINIC RENOVATION AND REHABILITATION |  | HL-0082 |  |  | CORONA HEALTH CENTER EXTERIOR FACADE, BASEMENT AND LOBBY | 2019 | 8200 | 0 | 916 | 0 | 8994 | 0 | 0 | 0 | 9910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HRC002MPL | A/C UPGRADE OF MONTESSORI PROGRESSIVE LEARNING CTR | SOCIAL SERVICES BUILDINGS | 400 | HR-C002 |  |  | REPLACEMENT OF EXISTING AIR CONDITIONING SYSTEM195-95 LINDEN BLVD QNO LONG TERM LESSOR;DDCM TO USE IN-HSE DSGN TO REDUCE CNSLT PROCUREMENDRP,ACD TO SECURE LONG TERM LESSOR FOR SITE. | 2019 | 1177 | 145.47 | 260 | 29 | 29 | 29 | 0 | 0 | 492.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4B3 | Safe Routes to Schools - Phase 4B3 | PRIMARY STREET RECONSTRUCTION | 400 | HW-K005 HW-D101 HW-0988 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | SAFE ROUTES TO SCHOOLS - PHASE 4B3 | SAFE ROUTES TO SCHOOLS - PHASE 4B3 | 2019 | 7774 | 5274.7 | 0 | 0 | 0 | 200 | 969 | 0 | 6443.7 | 35.5 | 0 | 0 | 0 | 0 | 0 | 0 | 35.5
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPQN | SAFE ROUTES TO SCHOOLS- QUEENS | PRIMARY STREET RECONSTRUCTION | 400 | HW-0988 HW-D103 HW-D105 |  | SAFE ROUTES TO SCHOOLS- QUEENS | SAFE ROUTES TO SCHOOLS- QUEENS | 2019 | 11289 | 825.37 | 0 | 0 | 10189 | 0 | 0 | 0 | 11014.37 | 0 | 0 | 0 | 694 | 0 | 0 | 0 | 694
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD10311 | 111th Street Malls | PRIMARY STREET RECONSTRUCTION | 400 403 404 | HW-D103 HW-0001Q | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | 111TH ST MALLS | 111TH ST MALLS | 2019 | 2700 | 0 | 1083 | 0 | 16259 | 1617 | 0 | 0 | 18959 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWHARPER | Reconstruction of Harper Street Asphalt Plant - Construction | FACILITY RECONSTRUCTION | 400 | HW-0003 |  | RECONSTRUCTION OF HARPER STREET ASPHALT PLANT | RECONSTRUCTION OF HARPER STREET ASPHALT PLANT | 2019 | 37801 | 2984.33 | 14693 | 613 | 1880 | 668 | 18078 | 0 | 38916.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP14QTA | CITYWIDE COMPLEX PED RAMPS (TRANSIT AUTHORITY) - QUEENS | PEDESTRIAN RAMP CONSTRUCTION | 400 | HW-0200 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | CITYWIDE COMPLEX PED RAMPS (TRANSIT AUTHORITY) - QUEENS | CITYWIDE COMPLEX PED RAMPS (TRANSIT AUTHORITY) - QUEENS | 2019 | 3102 | 6122.07 | 125 | 0 | 158 | 0 | 0 | 0 | 6405.07 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 33
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP15QTA | Complex Ped Ramps - Transit Authority - Queens | PEDESTRIAN RAMP CONSTRUCTION | 400 | HW-0200 TF-0002 TF-0502 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | COMPLEX PED RAMPS - TRANSIT AUTHORITY | COMPLEX PED RAMPS - TRANSIT AUTHORITY | 2019 | 2860 | 4594.61 | 734 | 0 | 0 | 0 | 0 | 0 | 5328.61 | 52.5 | 0 | 0 | 0 | 0 | 0 | 0 | 52.5
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ008Q | MYRTLE AVE - COOPER PLAZA, QUEENS | PRIMARY STREET RECONSTRUCTION | 400 405 | WM-0001 HW-1684 TF-0502 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | MYRTLE AVE - COOPER PLAZA | MYRTLE AVE - COOPER PLAZA | 2019 | 2500 | 5971.97 | 687 | 0 | 0 | 0 | 524 | 0 | 7182.97 | 13.4 | 0 | 0 | 0 | 0 | 0 | 0 | 13.4
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ009Q | 71st Ave Plaza | PRIMARY STREET RECONSTRUCTION | 400 405 406 | WM-0001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | 71ST AVE PLAZA | 71ST AVE PLAZA | 2019 | 1000 | 4651.45 | 90 | 0 | 0 | 0 | 0 | 0 | 4741.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ010Q | Corona Plaza | PRIMARY STREET RECONSTRUCTION | 400 403 404 | HW-1684 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | CORONA PLAZA | CORONA PLAZA | 2019 | 3500 | 7846.96 | 850 | 0 | 0 | 48 | 0 | 0 | 8744.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ014Q | 37TH RD PLAZA, PLANYC | PRIMARY STREET RECONSTRUCTION | 400 403 | HW-0200 HW-1684 WM-0001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | 37TH RD PLAZA, QUEENS | 37TH RD PLAZA, PLANYC | 2019 | 2000 | 7200.83 | 671 | 0 | 0 | 0 | 0 | 0 | 7871.83 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 15
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19Q1 | Pedestrian Ramp Rehabilitation - Queens | PEDESTRIAN RAMP CONSTRUCTION | 400 | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | PEDESTRIAN RAMP REHABILITATION - QUEENS | 2019 | 15471 | 250 | 15471 | 0 | 0 | 0 | 0 | 0 | 15721 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19Q2 | Pedestrian Ramp Rehabilitation - Queens | PEDESTRIAN RAMP CONSTRUCTION | 400 | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | PEDESTRIAN RAMP REHABILITATION - QUEENS | 2019 | 15471 | 250 | 15471 | 0 | 0 | 0 | 0 | 0 | 15721 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ100FJM | Flushing - Jamaica (Main St) SBS | PRIMARY STREET RECONSTRUCTION | 400 | HW-1684 WP-0169 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | FLUSHING - JAMAICA (MAIN ST) SBS | FLUSHING - JAMAICA (MAIN ST) SBS | 2019 | 7750 | 14532.32 | 9 | 0 | 0 | 207 | 0 | 0 | 14748.32 | 57 | 0 | 0 | 0 | 0 | 0 | 0 | 57
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ100SBA | Woodhaven Blvd Segment A (QED-1040) | TRAFFIC WORK IN CONJUNCTION WITH HIGHWAY RECONSTRUCTION | 400 | HW-D103 HW-1684 HW-Q001 HW-0001Q |  | WOODHAVEN BLVD SEG A | WOODHAVEN BLVD SEG A | 2019 | 18887 | 2316.07 | 0 | 89 | 16517 | 71 | 0 | 0 | 18993.07 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 200
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1182A | Broad Channel Bulkheads - Phase I (SEQ200582) | PRIMARY STREET RECONSTRUCTION | 400 414 | HW-0001Q | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | BROAD CHANNEL BULKHEADS ON WEST 11 TO WEST 13 ROAD | BROAD CHANNEL BULKHEADS ON WEST 11 TO WEST 13 ROAD | 2019 | 3807 | 12983.4 | 6214 | 3224 | 0 | 0 | 1629 | 0 | 24050.4 | 7.2 | 0 | 0 | 0 | 0 | 0 | 0 | 7.2
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1182B | Broad Channel Bulkheads - Phase II (SEQ200586) | PRIMARY STREET RECONSTRUCTION | 400 | HW-0001Q TF-0002 SE-0200Q WM-0001 HW-0200 TF-0502 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BROAD CHANNEL BULKHEADS PHASE II | BROAD CHANNEL BULKHEADS PHASE II | 2019 | 19167 | 2335.16 | 595 | 35210 | 0 | 0 | 0 | 0 | 38140.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1184A | James Court Roadway & Bulkhead, Queens (Joint Bid) | PRIMARY STREET RECONSTRUCTION | 400 412 | HW-D103 HW-0001Q HW-0944 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | JAMES COURT ROADWAY AND BULKHEAD | JAMES COURT ROADWAY AND BULKHEAD | 2019 | 1948 | 1299.53 | 3368 | 0 | 0 | 270 | 0 | 0 | 4937.53 | 0 | 109 | 0 | 0 | 0 | 0 | 0 | 109
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1187 | Westbourne-Dunbar Roadways & Bulkheads (SAND1187, SEQ200595) | PRIMARY STREET RECONSTRUCTION | 400 414 | HW-0001Q | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | WESTBOURNE - DUNBAR ROADWAYS & BULKHEADS | WESTBOURNE - DUNBAR ROADWAYS & BULKHEADS | 2019 | 5000 | 1312.21 | 0 | 0 | 0 | 17525 | 0 | 0 | 18837.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1190A | Reconstruction of Queens Blvd Phase 1 (QED-1042A) | PRIMARY STREET RECONSTRUCTION | 400 | HW-0001Q |  | RECONSTRUCTION OF QUEENS BLVD PHASE 1 | RECONSTRUCTION OF QUEENS BLVD PHASE 1 | 2019 | 49520 | 9076.1 | 250 | 64871 | 0 | 0 | 0 | 0 | 74197.1 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 2000
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1190B | Reconstruction of Queens Blvd Phase 2 | PRIMARY STREET RECONSTRUCTION | 400 | HW-0001Q | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | RECONSTRUCTION OF QUEENS BLVD PHASE 2 | RECONSTRUCTION OF QUEENS BLVD PHASE 2 | 2019 | 81984 | 2032.22 | 0 | 0 | 39335 | 0 | 0 | 0 | 41367.22 | 0 | 0 | 0 | 29624 | 0 | 0 | 0 | 29624
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1190-C | Reconstruction of Queens Blvd Phase 3 | PRIMARY STREET RECONSTRUCTION | 400 | HW-0001Q HW-D103 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RECONSTRUCTION OF QUEENS BLVD, PHASE 3 | 2019 | 98817 | 2021.64 | 0 | 0 | 0 | 96722 | 0 | 0 | 98743.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1193 | Union Turnpike Curb Repair | PRIMARY STREET RECONSTRUCTION | 400 | HW-0001Q | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | UNION TURNPIKE CURB REPAIR | UNION TURNPIKE CURB REPAIR | 2019 | 24709 | 0 | 0 | 0 | 0 | 5673 | 0 | 0 | 5673 | 0 | 0 | 0 | 0 | 215 | 0 | 0 | 215
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1195 | Colfax and Murdock Street Raising (SEQNS003) | PRIMARY STREET RECONSTRUCTION | 400 | HW-0001Q | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | COLFAX AND MURDOCK STREET RAISING | 2019 | 29735 | 771.33 | 0 | 9317 | 0 | 0 | 0 | 0 | 10088.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ200578 | SEQ - Foch Boulevard Safety Improvements (SEQ200578) | PRIMARY STREET RECONSTRUCTION | 400 | HW-0001Q HW-0200 TF-0002 TF-0502 |  | SE-Q FOCH BOULEVARD SAFETY IMPROVEMENTS | SE-Q FOCH BOULEVARD SAFETY IMPROVEMENTS | 2019 | 6653 | 0 | 503 | 7031 | 0 | 0 | 0 | 0 | 7534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ213C | Main Street Sidewalk Widening | PRIMARY STREET RECONSTRUCTION | 400 407 | HW-0001Q SE-0002Q | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | MAIN STREET SIDEWALK WIDENING | MAIN STREET SIDEWALK WIDENING | 2019 | 4064 | 8947.42 | 808 | 0 | 0 | 1447 | 0 | 0 | 11202.42 | 2484.69 | 0 | 0 | 0 | 0 | 0 | 0 | 2484.69
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ274F2 | RECON OF STREETS IN ROSEDALE AREA - PHASE 2 | PRIMARY STREET RECONSTRUCTION | 400 | HW-0274 |  | RECON OF STREETS IN ROSEDALE AREA - PHASE 2 | RECON OF STREETS IN ROSEDALE AREA - PHASE 2 | 2019 | 22140 | 0 | 481 | 0 | 33553 | 0 | 0 | 0 | 34034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ411B | Reconstruction of Albert Road Area, 94th St, Qns (SEQ002568) | PRIMARY STREET RECONSTRUCTION | 410 | HW-0411 HW-0061 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | 94TH STREET ETC, QUEENSTHE EXISTING ROADWAY SHALL BE RECONSTRUCTEDROADWAY RECONSTRUCTION SHALL INCLUDE NEW CURBS, SIDEWALKS, AND REQUIREREPLACEMENTTHERE ARE NO AMINITIESTHIS PROJECT IS CITY FUNDEDTHIS PROJECT IS IN CONJUNCTION WITH DEP | 2019 | 20836 | 41067.31 | 1702 | 28 | 0 | 0 | 0 | 0 | 42797.31 | 460.6 | 0 | 0 | 0 | 0 | 0 | 0 | 460.6
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ631B-3 | ALMEDA AV - PHASE III | PRIMARY STREET RECONSTRUCTION | 414 | SE-087HW | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | ALMEDA AV - PHASE III | ALMEDA AV - PHASE III | 2019 | 12332 | 25.4 | 0 | 0 | 0 | 1284 | 0 | 0 | 1309.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ662G | Springfield Gardens Phase V (SE-862) | PRIMARY STREET RECONSTRUCTION | 413 | HW-0061 HW-0662 HW-0001Q HW-0200 TF-0002 TF-0502 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | ROCKAWAY BLVD | ROCKAWAY BLVD | 2019 | 24283 | 1345.27 | 276 | 0 | 15355 | 1689 | 0 | 0 | 18665.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ708 | RECONSTRUCTION OF 73RD PLACE | PRIMARY STREET RECONSTRUCTION | 405 | WM-0001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | 73RD PL: METROPOLITAN AVE - DEAD END 200'+/- S/O 70TH AVE; 75TH ST: MEITAN - 71ST AVES; 76TH ST: 68TH - COOPER AVES; 78TH & 79TH STS: METROP- COOPER AVES; 67TH RD, 68TH DR, &68TH AVE: 73RD PL - 80TH ST; 68TH RDAVE, &COOK AVE: 73RD PL - 75TH ST; 68TH RD, & 69TH AVE: 78TH - 80TH ST69TH RD: 73RD PL - COOPER AVE; 69TH DR: 79TH ST TO COOPER AVE; 70TH AV73RD PL - 74TH ST; 74TH ST: 69TH RD - 71ST AVE; 71ST AVE: 74TH - 76THCOOPER AVE: 76TH - 78TH STS; COOPER AVE / SOUTH S/R:THE EXISTING ROADWAY SHALL BE RECONSTRUCTED/ROADWAY RECONSTRUCTION SHAINCLUDE NEW CURBS, SIDEWALKS AND REQUIRED UTILITY REPLACEMENT/THERE ARAMENITIES/THIS PROJECT IS CITY FUNDED/THIS PROJECT IS IN CONJUNCTION W | 2019 | 20809 | 2631.28 | 0 | 0 | 0 | 0 | 0 | 3262 | 5893.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ724B | Recon of Streets in Brookville-Edgewood Triangle (SEQ200519) | PRIMARY STREET RECONSTRUCTION | 413 | HW-0724 HW-0061 HW-0001Q HW-0200 TF-0002 TF-0502 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BROOKVILLE-EDGEWOOD TRIANGE ROSEDALE QUEENS | BROOKVILLE-EDGEWOOD TRIANGE | 2019 | 11889 | 3513.55 | 5483 | 4821 | 0 | 7448 | 0 | 0 | 21265.55 | 0 | 0 | 0 | 0 | 435 | 0 | 0 | 435
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ976 | SEQ - FRANCIS LEWIS BLVD & 93RD AVE (QED-976) | PRIMARY STREET RECONSTRUCTION | 400 | HW-0001Q |  |  | SEQ FRANCIS LEWIS BLVD - BUS PADS AND STEEL-FACED CURBS | 2019 | 725 | 0 | 725 | 0 | 0 | 0 | 0 | 0 | 725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ985 | SHORE ROAD RECONSTRUCTION (SEQ200585) | PRIMARY STREET RECONSTRUCTION | 400 407 | HW-0001Q | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | SHORE ROAD FROM EAST DRIVE TO 36TH AVE, DOUGLASTON | 2019 | 7725 | 6708.51 | 894 | 4000 | 0 | 308 | 0 | 0 | 11910.51 | 213.45 | 0 | 0 | 0 | 0 | 0 | 0 | 213.45
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQF030 | HARPER ST RESTROOMS, WASTE WATER AND STORM WATER CONVEYANCES | FACILITY RECONSTRUCTION | 400 407 | HW-0003 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | WASTE WATER MITIGATION | 2019 | 2000 | 464.78 | 505 | 700 | 4587 | 0 | 0 | 0 | 6256.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2017Q1 | Prior Notice Sidewalks - Queens | SIDEWALK RECONSTRUCTION | 400 | HW-0200 |  | PRIOR NOTICE SIDEWALKS - QUEENS | PRIOR NOTICE SIDEWALKS - QUEENS | 2019 | 4890 | 6662.34 | 86 | 0 | 0 | 0 | 0 | 0 | 6748.34 | 1468.1 | 0 | 0 | 0 | 0 | 0 | 0 | 1468.1
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2019Q1 | Prior Notice Sidewalks- Queens | SIDEWALK RECONSTRUCTION | 400 | HW-0200 |  |  | PRIOR NOTICE SIDEWALKS- QUEENS | 2019 | 5865 | 0 | 0 | 5588 | 0 | 0 | 0 | 0 | 5588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2019Q2 | Prior Notice Sidewalks- Queens | SIDEWALK RECONSTRUCTION | 400 | HW-0200 |  |  | PRIOR NOTICE SIDEWALKS- QUEENS | 2019 | 5865 | 0 | 0 | 5392 | 0 | 0 | 0 | 0 | 5392 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQ122-W | Whitestone - Selected Masonry | RECONSTRUCTION NECESSARY TO MAINTAIN FACILITIES | 407 | LQ-D122 LQ-0122 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | SELECTED MASONRY REPAIR | 2019 | 230 | 551.46 | 37 | 0 | 0 | 0 | 0 | 0 | 588.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQARVEXPN | Arverne Library - Replacement facility | REPLACEMENT BRANCHES | 400 | LQ-D122 LQ-Q122 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | ARVERNE LIBRARY EXPANSION | 2019 | 7600 | 1129.96 | 0 | 0 | 176 | 5675 | 0 | 0 | 6980.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQASADA | ASTORIA - Brach renovation with ADA | RECONSTRUCTION NECESSARY TO MAINTAIN FACILITIES | 400 | LQ-0122 LQ-D122 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | ASTORIA ADA RENOVATION FY16 CM CONSTANTINIDES | 2019 | 1479 | 406.35 | 774 | 0 | 6884 | 315 | 0 | 0 | 8379.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122-AU | Auburndale - Roof Replacement | ESSENTIAL RECONSTRUCTION OF FACILITIES | 407 | LQ-D122 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ROOF REPLACEMENT & RELATED WORK | 2019 | 705 | 653.36 | 0 | 0 | 73 | 0 | 0 | 0 | 726.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122BCE | BROAD CHANNEL EXTERIOR RENOVATION | RECONSTRUCTION NECESSARY TO MAINTAIN FACILITIES | 400 414 | LQ-D001 LQ-0122 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  |  | 2019 | 250 | 0 | 0 | 0 | 0 | 0 | 400 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122BR2 | BROADWAY LIBRARY - RENOVATION (PHASE THREE AND FOUR) | RECONSTRUCTION NECESSARY TO MAINTAIN FACILITIES | 401 | LQ-D122 LQ-0122 LQ-Q122 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  |  | 2019 | 1575 | 483.11 | 113 | 0 | 2347 | 0 | 0 | 0 | 2943.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122-CL | CENTRAL - Fire Alarm, Roof, and Ejector Pumps - Pass-Through | ESSENTIAL RECONSTRUCTION OF FACILITIES | 412 | LQ-D122 LQ-0122 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES |  | FIRE ALARM / ROOF / RENOVATION | 2019 | 4500 | 90 | 7000 | 0 | 0 | 0 | 14153 | 0 | 21243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122-CM | CAMBRIA HEIGHTS - Lower Level Renovation | RECONSTRUCTION NECESSARY TO MAINTAIN FACILITIES | 413 | LQ-D122 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES |  | RENOVATION | 2019 | 2800 | 1366.02 | 0 | 0 | 71 | 0 | 0 | 0 | 1437.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122-F2 | FLUSHING - HVAC & Controls | RECONSTRUCTION NECESSARY TO MAINTAIN FACILITIES | 407 | LQ-0122 LQ-D122 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | HVAC & CONTROLS | 2019 | 400 | 390.42 | 0 | 0 | 18 | 0 | 895 | 0 | 1303.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122GL2 | GLENDALE LIBRARY RENOVATION | ESSENTIAL RECONSTRUCTION OF FACILITIES | 405 | LQ-D122 LQ-0122 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RENOVATION | 2019 | 2803 | 6028.3 | 575 | 96 | 0 | 0 | 0 | 0 | 6699.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122HO1 | Hollis Library - Building Infrastructure | RECONSTRUCTION NECESSARY TO MAINTAIN FACILITIES | 408 | LQ-Q122 LQ-0122 LQ-D122 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BUILDING INFRASTRUCTURE | 2019 | 3125 | 649.16 | 0 | 0 | 2765 | 0 | 0 | 0 | 3414.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122HV3 | MULTIBRANCH (BP, OZ & RS) - HVAC | RECONSTRUCTION NECESSARY TO MAINTAIN FACILITIES | 412 409 413 | LQ-D122 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BP, OZ, RS | 2019 | 1760 | 1763.06 | 100 | 0 | 311 | 0 | 0 | 0 | 2174.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122NF4 | NORTH FOREST PARK - Renovation | RECONSTRUCTION NECESSARY TO MAINTAIN FACILITIES | 406 | LQ-D122 LQ-0122 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NORTH FOREST PARK RENOVATION | 2019 | 1750 | 447.4 | 0 | 0 | 2364 | 0 | 0 | 0 | 2811.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122-QW | QUEENS WEST BRANCH | REPLACEMENT BRANCHES | 401 | LQ-0122 LQ-D122 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | LONG ISLAND CITY | NEW BRANCH FACILITY | 2019 | 2000 | 22477.64 | 5643 | 0 | 771 | 0 | 0 | 0 | 28891.64 | 18591.16 | 63 | 0 | 0 | 0 | 0 | 0 | 18654.16
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122RF3 | MULTIBRANCH (BP, HB, SJ) - Roof Replacement | ESSENTIAL RECONSTRUCTION OF FACILITIES | 410 406 412 | LQ-0122 LQ-D122 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ROOFS | 2019 | 1084 | 2614.41 | 60 | 0 | 70 | 0 | 0 | 0 | 2744.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122RO2 | ROCHDALE VILLAGE - HVAC & Controls | ESSENTIAL RECONSTRUCTION OF FACILITIES | 412 | LQ-D122 LQ-0122 LQ-Q122 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BOILER & CONTROLS | 2019 | 460 | 299.38 | 0 | 717 | 4 | 0 | 0 | 0 | 1020.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122-S2 | STEINWAY - Phase II Renovation | ESSENTIAL RECONSTRUCTION OF FACILITIES | 401 | LQ-D122 LQ-0122 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | STEINWAY RENOVATION | 2019 | 2405 | 4376.2 | 832 | 801 | 0 | 0 | 0 | 0 | 6009.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122-WN | WOODHAVEN - Renovation | RECONSTRUCTION NECESSARY TO MAINTAIN FACILITIES | 409 | LQ-D122 LQ-0122 LQ-Q122 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | REPLACEMENT OF WINDOWS & DOORS | 2019 | 200 | 674.85 | 671 | 0 | 8820 | 0 | 0 | 0 | 10165.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122-WP | WINDSOR PARK - Renovation | REPLACEMENT BRANCHES | 411 | LQ-D122 |  |  | RENOVATION | 2019 | 1650 | 1557.59 | 0 | 0 | 0 | 0 | 102 | 0 | 1659.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122WS3 | WOODSIDE - INTERIOR LIGHTING UPGRADE | REPLACEMENT BRANCHES | 400 | LQ-D122 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | WOODSIDE INTERIOR LIGHTS | 2019 | 165 | 94.4 | 0 | 0 | 87 | 0 | 0 | 0 | 181.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQDL-NEW | DOUGLASTON: Replacement Facility | REPLACEMENT BRANCHES | 400 | LQ-0122 LQ-Q122 LQ-D122 |  |  | REPLACEMENT FACILITY | 2019 | 23968 | 0 | 2035 | 0 | 0 | 20137 | 0 | 1000 | 23172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQEM19BKP | BAISLEY PARK: AC Replacement | ESSENTIAL RECONSTRUCTION OF FACILITIES | 400 | LQ-0122 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BAISLEY PARK: AC REPLACEMENT | 2019 | 1365 | 0 | 1236 | 0 | 0 | 0 | 0 | 0 | 1236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQEM19BPK | BAISLEY PARK: New Boiler | ESSENTIAL RECONSTRUCTION OF FACILITIES | 400 | LQ-0122 |  |  | BAISLEY PARK: NEW BOILER | 2019 | 275 | 0 | 124 | 0 | 626 | 0 | 0 | 0 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQFLELV | FLUSHING LIBRARY - CONSTRUCTION OF SECOND ELEVATOR | RECONSTRUCTION NECESSARY TO MAINTAIN FACILITIES | 400 | LQ-Q122 LQ-0122 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CONSTRUCTION OF SECOND ELEVATOR AT FLUSHING. BP FUNDED FY 16 | 2019 | 2990 | 526.9 | 71 | 0 | 2419 | 0 | 0 | 0 | 3016.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQHIHVAC | HILLCREST - HVAC | RECONSTRUCTION NECESSARY TO MAINTAIN FACILITIES | 400 | LQ-D122 LQ-0122 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | HILLCREST - HVAC FY 16 | 2019 | 798 | 306.63 | 6 | 0 | 623 | 0 | 0 | 0 | 935.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQHIROOF | HILLCREST ROOF | RECONSTRUCTION NECESSARY TO MAINTAIN FACILITIES | 400 | LQ-0122 LQ-D122 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | HILLCREST ROOF - FY 16 | 2019 | 903 | 187.11 | 77 | 0 | 1513 | 0 | 0 | 0 | 1777.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQLAROOF | LAURELTON ROOF | RECONSTRUCTION NECESSARY TO MAINTAIN FACILITIES | 400 | LQ-0122 LQ-D122 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | LAURELTON ROOF - | 2019 | 860 | 289.29 | 56 | 1013 | 0 | 0 | 0 | 0 | 1358.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQMVHVAC | MIDDLE VILLAGE - HVAC | RECONSTRUCTION NECESSARY TO MAINTAIN FACILITIES | 400 | LQ-D122 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | MIDDLE VILLAGE - HVAC FY 16 | 2019 | 790 | 186.45 | 60 | 576 | 0 | 0 | 0 | 0 | 822.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQOZROOF | OZONE PARK ROOF REPLACEMENT | ESSENTIAL RECONSTRUCTION OF FACILITIES | 400 | LQ-0122 LQ-Q122 |  |  | OZONE PARK ROOF REPLACEMENT | 2019 | 800 | 120.1 | 129 | 672 | 0 | 0 | 0 | 0 | 921.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQ122-1E | ELMHURST - Replacement Facility | REPLACEMENT BRANCHES | 404 | LQ-Q122 LQ-0122 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ELMHURST BRANCH LIBRARY EXPANSION | 2019 | 12027 | 33024.13 | 0 | 0 | 0 | 0 | 116 | 0 | 33140.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQ122-BL | Masonry Repairs - Bellerose | RECONSTRUCTION NECESSARY TO MAINTAIN FACILITIES | 413 | LQ-Q122 LQ-0122 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | MASONRY REPAIRS - BL | 2019 | 634 | 819.54 | 161 | 0 | 0 | 0 | 0 | 0 | 980.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQ122-DL | MULTIBRANCH (C, DL, NO, RO, S &SZ) - Roof Replacements | ESSENTIAL RECONSTRUCTION OF FACILITIES | 411 | LQ-0122 LQ-Q122 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | ROOF REPLACEMENT | 2019 | 1620 | 2001.33 | 25 | 0 | 174 | 0 | 0 | 0 | 2200.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQ122EE2 | EAST ELMHURST - Expansion | REPLACEMENT BRANCHES | 403 | LQ-Q122 LQ-0122 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | EAST ELMHURST EXPANSION | 2019 | 2967 | 10019.21 | 868 | 0 | 0 | 0 | 0 | 0 | 10887.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQ122-FA | FAR ROCKAWAY - Replacement Facility | REPLACEMENT BRANCHES | 414 | LQ-Q122 LQ-0122 LQ-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | DESIGN, CONSTRUCTION, OUTFITTING FOR REPLACEMENT FAR ROCKAWAY LIBRARY | 2019 | 1250 | 25173.71 | 1886 | 0 | 4059 | 0 | 0 | 0 | 31118.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQ122-KE | KEW GARDENS HILLS - Renovation and Expansion | REPLACEMENT BRANCHES | 408 | LQ-0122 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | 72-33 VLEIGH PLACE, FLUSHING, NEW YORK 11367 | DESIGN / CONSTRUCTION FOR EXPANSION OF KEW GARDENS HILLS LIBRARY | 2019 | 3100 | 11239.87 | 74 | 0 | 0 | 0 | 207 | 0 | 11520.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQ122-R1 | RICHMOND HILL - Branch Renovation | ESSENTIAL RECONSTRUCTION OF FACILITIES | 409 | LQ-Q122 LQ-D122 LQ-0122 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | HVAC AND CONTROLS. | 2019 | 1650 | 7 | 0 | 0 | 8013 | 0 | 0 | 0 | 8020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQ122-RG | REGO PARK LIBRARY - REPLACEMENT FACILITY | REPLACEMENT BRANCHES | 406 | LQ-Q122 LQ-D122 LQ-0122 |  | 91-41 63RD DRIVE, REGO PARK, NEW YORK 11374 | DESIGN, CONSTRUCTION AND OUTFITTING FOR NEW REPLACEMENT FACILITY | 2019 | 1250 | 0 | 2883 | 0 | 0 | 26075 | 1000 | 0 | 29958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQBHHVAC | QUEENSBORO HILL - HVAC | RECONSTRUCTION NECESSARY TO MAINTAIN FACILITIES | 400 | LQ-D122 LQ-0122 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | QUEENSBORO HILL HVAC | 2019 | 815 | 164.34 | 0 | 1439 | 0 | 0 | 0 | 0 | 1603.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQVHVAC | QUEENS VILLAGE - HVAC | RECONSTRUCTION NECESSARY TO MAINTAIN FACILITIES | 400 | LQ-0122 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | QUEENS VILLAGE HVAC | 2019 | 1000 | 241.79 | 250 | 902 | 0 | 0 | 0 | 0 | 1393.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQVROOF | QUEENS VILLAGE - ROOF | RECONSTRUCTION NECESSARY TO MAINTAIN FACILITIES | 400 | LQ-0122 |  |  | QUEENS VILLAGE ROOF | 2019 | 761 | 185.99 | 0 | 683 | 0 | 0 | 0 | 0 | 868.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQRDMASON | RIDGEWOOD - MASONRY | RECONSTRUCTION NECESSARY TO MAINTAIN FACILITIES | 400 | LQ-0122 |  |  | RIDGEWOOD MASONRY | 2019 | 1718 | 247.37 | 162 | 1703 | 0 | 0 | 0 | 0 | 2112.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQSARENOV | ST. ALBANS RENOVATION | ESSENTIAL RECONSTRUCTION OF FACILITIES | 400 | LQ-Q122 LQ-0122 LQ-D122 LQ-D001 |  |  | ST. ALBANS RENOVATION | 2019 | 2485 | 0 | 0 | 0 | 435 | 48 | 2011 | 0 | 2494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQSAROOF | ST. ALBANS ROOF REPLACEMENT | ESSENTIAL RECONSTRUCTION OF FACILITIES | 400 | LQ-0122 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | ST. ALBANS ROOF REPLACEMENT | 2019 | 669 | 1054.17 | 12 | 21 | 0 | 166 | 0 | 0 | 1253.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQSEHVAC | SEASIDE -HVAC | RECONSTRUCTION NECESSARY TO MAINTAIN FACILITIES | 400 | LQ-D122 LQ-0122 |  |  | SEASIDE HVAC | 2019 | 645 | 55.94 | 0 | 0 | 870 | 0 | 0 | 0 | 925.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQSUADA | SUNNYSIDE ADA | RECONSTRUCTION NECESSARY TO MAINTAIN FACILITIES | 400 | LQ-D122 LQ-0122 |  |  | SUNNYSIDE ADA | 2019 | 145 | 75 | 180 | 0 | 0 | 0 | 0 | 0 | 255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQWSADA | WOODSIDE ADA | RECONSTRUCTION NECESSARY TO MAINTAIN FACILITIES | 400 | LQ-D122 LQ-0122 |  |  | WOODSIDE ADA | 2019 | 196 | 55 | 0 | 0 | 166 | 0 | 0 | 0 | 221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | P-407BHI3 | BOWNE HOUSE INTERIOR RESTORATIONS | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | P-Q245 P-D019 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | QUEENS | BOWNE HOUSE INTERIOR RESTORATIONS | 2019 | 1875 | 524.06 | 380 | 131 | 3398 | 0 | 0 | 0 | 4433.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | P-407BHV4 | BOWNE HOUSE VISITORS CENTER Q022 | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | P-D019 P-Q245 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BOWNE HOUSE VISITORS CENTER Q022 | 2019 | 2465 | 45.74 | 0 | 1069 | 0 | 1513 | 0 | 0 | 2627.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | P-407KIN2 | Kingsland Homestead Roof/Floor Renovations | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 400 | P-Q245 P-D019 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | KINGSLAND HOMESTEAD/QUEENS HISTORICAL SOCIETY (HHT) ROOF AND FLOOR RENOVATIONS | 2019 | 480 | 0 | 455 | 45 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | P-415PAS3 | FMCP-PASSERELLE BRIDGE - Q099 | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | P-0245Q |  |  | FMCP-PASSERELLE BRIDGE - Q099 | 2019 | 125113 | 10688 | 0 | 0 | 8675 | 106250 | 0 | 0 | 125613 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PO002-116 | NEW 116TH PCT | POLICE FACILITIES | 400 | PO-0002 PU-0025 |  |  | NEW PCT | 2019 | 70000 | 0 | 13672 | 73935 | 0 | 0 | 0 | 0 | 87607 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79BMAHW | 114TH PCT PLUMBING SYSTEM REPLACEMENT | POLICE FACILITIES | 400 | PO-0079 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | PLUMBING SYSTEM | 2019 | 436 | 594.53 | 913 | 892 | 0 | 0 | 0 | 0 | 2399.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79FDQNS | QUEENS FRONT DESK REPLACEMENT 104TH, 109TH, 114TH, 115TH | POLICE FACILITIES | 400 | PO-0079 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | VARIOUS IN QUEENS | FRONT DESKS | 2019 | 1018 | 0 | 0 | 970 | 0 | 0 | 0 | 0 | 970 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV001SELM | LAH - Louis Armstrong House - Administration Facility | ESSENTIAL RECONSTRUCTION OF FACILITIES | 403 | PV-0001 PV-D001 PV-Q001 PV-0467 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | SCOPE OF WORK INCLUDES: UPGRADE ELECTRICAL SYSTEMS, NEW MECHANICAL SYSTEMS, ADA COMPLIANT OFFICES ND REST ROOMS. ALL CONSTRUCTION WORK WILL COMPLY WITH ALL BUILDING CODES FOR ADMINISTRATION OFFICES AND STORAGE FACILITIES. | 2019 | 1265 | 653.13 | 0 | 0 | 2776 | 0 | 0 | 0 | 3429.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV040ELEV | FTH - Flushing Town Hall Elevator Replacement | ESSENTIAL RECONSTRUCTION OF FACILITIES | 407 | PV-Q040 PV-D040 PV-0040 PV-Q467 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | FLUSHING TOWN HALL - ELEVATOR: COMPLETE REPLACEMENT OF ELEVATOR. | 2019 | 813 | 0 | 120 | 0 | 0 | 896 | 0 | 0 | 1016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV272EDUC | QBG - Queens Botanical Garden Educ Bldg Renovation | ESSENTIAL RECONSTRUCTION OF FACILITIES | 407 | PV-Q272 PV-D272 PV-0272 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | QUEENS BOTANICAL GARDEN - EDUCATION BUILDING: CONSTRUCTION/RENOVATION OF EDUCATION BUILDING | 2019 | 20152 | 0 | 2138 | 0 | 0 | 16902 | 0 | 0 | 19040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV272SITE | QBG - Site-wide Exterior Improvements | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | PV-D272 PV-0272 |  | 43-50 MAIN STREET, QUEENS, NY | SITEWIDE LANDSCAPE IMPROVEMENTS. | 2019 | 903 | 516.55 | 107 | 0 | 0 | 0 | 0 | 0 | 623.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV274CHLL | NYHOS - New York Hall of Science - Chiller Replacement | ESSENTIAL RECONSTRUCTION OF FACILITIES | 407 | PV-Q274 PV-D274 PV-0274 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | NEW YORK HALL OF SCIENCE CHILLER REPLACEMENT: REPLACEMENT AND MODERNIZATION OF TWO OUTDATED CHILLER UNITS | 2019 | 3083 | 496.06 | 0 | 0 | 5424 | 0 | 0 | 0 | 5920.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV274EXLT | NYHOS - NY Hall of Science Lighting for Outdoor Exhibits | ESSENTIAL RECONSTRUCTION OF FACILITIES | 408 | PV-D467 PV-Q274 PV-0274 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | FUNDING FOR THE INSTALLATION OF LIGHTING FOR THE SCIENCE PLAYGROUND AND ROCKET PARK OUTDOOR EXHIBITS TO ALLOW EVENING EVENTS AND PROVIDE SECURITY MEASURE. | 2019 | 1830 | 902.91 | 959 | 1071 | 0 | 0 | 0 | 0 | 2932.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV274GHIN | NYHOS - NY HALL OF SCIENCE - Great Hall Int. Systems Recon. | NEW TECHNOLOGY AND CONSTRUCTION | 407 | PV-D274 PV-0274 PV-Q274 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | 47-01 111TH STREET CORONA NEW YORK | PROJECT SCOPE OF WORK IS THE INTERIOR RECONSTRUCTION OF THE 1964 WORLD FAIR GREAT HALL. PROJECT INCLUDES THE REPLACEMENT OF ALL ELECTRICAL, HVAC, LIGHTING AND AUDIO SYSTEMS. | 2019 | 4850 | 20747.76 | 0 | 0 | 0 | 5795 | 0 | 0 | 26542.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV274KITR | NYHOS - NY Hall of Science,Great Hall, Kitchen & Restroom | ESSENTIAL RECONSTRUCTION OF FACILITIES | 401 | PV-Q274 PV-D274 PV-0274 | PROJECT DELAYED PENDING RELEASE OF NEW TECHNOLOGY |  | SCOPE OF WORK IS THE RECONSTRUCTION OF THE GREAT HALL KITCHEN AND THERECONSTRUVTION OG THE GREAT HALL RESTROOMS. | 2019 | 2449 | 0 | 0 | 2970 | 0 | 0 | 0 | 0 | 2970 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV291-QM2 | QMA - Queen's Museum of Art Expansion Phase II | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | PV-0291 PV-Q291 PV-D291 PV-D467 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | QMA | 2019 | 2315 | 0 | 0 | 0 | 600 | 0 | 14138 | 0 | 14738 | 0 | 3126 | 0 | 0 | 0 | 0 | 0 | 3126
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV291-QMX | QMA - Queens Museum of Art Expansion | ESSENTIAL RECONSTRUCTION OF FACILITIES | 407 406 | PV-0291 PV-Q291 |  | NYC BUILDING FLUSHING MEADOWS CORONA PARK, CORONA NY 11368 | EXPANSION | 2019 | 32609 | 53026.33 | 0 | 0 | 0 | 283 | 0 | 0 | 53309.33 | 11757.87 | 113 | 0 | 0 | 0 | 0 | 0 | 11870.87
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV501BOIL | PS1 - PS1 Boiler Replacement | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | PV-Q501 PV-0501 PV-D501 PV-Q467 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | REPLACEMENT OF TWO BOILERS AT PS1 | 2019 | 1000 | 509.9 | 0 | 0 | 2910 | 0 | 0 | 0 | 3419.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV655QCFM | QCFM - Queen's County Farm Museum Greenhouse Restoration | ESSENTIAL RECONSTRUCTION OF FACILITIES | 413 | P-Q245 |  |  | ADMNIN BUILDING/GREENYHOUSE RESTORATION. | 2019 | 3706 | 3512.12 | 102 | 0 | 0 | 0 | 0 | 0 | 3614.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PW293QBLV | 120-55 QUEENS BLVD - FIRE ALARM | LEGAL MANDATES AND CORRECTION OF UNSAFE CONDITIONS | 401 | PW-0293 |  |  | 120-55 QUEENS BLVD - FIRE ALARM | 2019 | 3119 | 628.13 | 0 | 0 | 7892 | 0 | 0 | 0 | 8520.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77417DA | 120-55 QUEENS BLVD.- QUEENS DA TRAINING ROOM | REHABILITATION OF CITY-OWNED OFFICE SPACE | 401 | PW-0077 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | 120-55 QUEENS BLVD.- QUEENS DA TRAINING ROOM | 2019 | 1705 | 739.11 | 0 | 1494 | 998 | 0 | 0 | 0 | 3231.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77417P2 | 120-55 QUEENS BLVD - PLAZA, STEPS AND ENTRANCE | REHABILITATION OF CITY-OWNED OFFICE SPACE | 400 409 | PW-0077 |  |  | REPAIRS AND REPLACEMENT OF GRANITE PAVE CRACKED, DISPLACEMENT OF GRANITE, CONCRETE AND BRICKS. REPAIR OF PLAZA CONCRETE MASONRY FOUNDATION | 2019 | 3940 | 0 | 0 | 0 | 3100 | 0 | 0 | 0 | 3100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77ELEV | 120-55 QUEENS BLVD. ELEVATOR MODERNIZATION | REHABILITATION OF CITY-OWNED OFFICE SPACE | 401 | PW-0077 |  |  | SQ FT | 2019 | 1300 | 0 | 0 | 0 | 0 | 2317 | 0 | 0 | 2317 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PWD99WNY1 | CENTER FOR THE WOMEN OF NEW YORK | MISCELLANEOUS CONSTRUCTION | 400 | P-D019 P-Q245 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES |  | RECONSTRUCTION | 2019 | 1100 | 3304.72 | 445 | 0 | 0 | 0 | 0 | 0 | 3749.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PWQ077AT2 | 120-55 QUEENS BLVD- QUEENS BOROUGH HALL ATRIUM | REHABILITATION OF CITY-OWNED OFFICE SPACE | 401 | PW-0077 PW-Q077 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | 120-55 QUEENS BVLD- QUEENS BOROUGH HALL ATRIUM | 2019 | 21854 | 19358.33 | 0 | 0 | 1343 | 0 | 0 | 0 | 20701.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED1002 | WATER MAIN WORK IN VARIOUS LOCATIONS PROJ Q2007-05 | TRUNK AND DISTRIBUTION MAIN EXTENSION | 406 | WM-0006 SE-1000 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | WATER MAIN WORK IN VARIOUS LOCATIONS PROJ Q2007-05 | 2019 | 16900 | 30035.52 | 433 | 0 | 0 | 0 | 0 | 0 | 30468.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1003B | WM Replacement in Jamaica/Richmond Hill Area, Queens | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 409 | WM-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | WM REPLACEMENT IN JAMAICA AVE B/T 111 ST & 129 ST. | 2019 | 18728 | 19944.59 | 1068 | 0 | 0 | 0 | 0 | 0 | 21012.59 | 325.31 | 0 | 0 | 0 | 0 | 0 | 0 | 325.31
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED1005 | DIST WATER MAIN REPLACEMENT LONG ISLAND CITY | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 401 | WM-0001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | DIST WATER MAIN REPLACEMENT LONG ISLAND CITY , ASTORIA AT VARIOUS LOCATIONS | 2019 | 11600 | 36396.78 | 1826 | 0 | 50 | 65 | 0 | 0 | 38337.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1007 | New Trunk Water Main in Rockaway Beach Blvd (SANDHW12) | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 414 | WM-0006 WM-0001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | NEW TRUNK WATER MAIN IN ROCKAWAY BEACH BLVD. B/W B 59 STREET AND B 49STREET | 2019 | 4994 | 27998.82 | 6 | 0 | 0 | 1274 | 0 | 0 | 29278.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1008 | 3WT-TRUNK MAIN CONNECTION IN 54 ST | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 400 401 402 405 | WM-0006 TF-0502 SE-0002Q | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | 3WT-TRUNK MAIN CONNECTION IN 54 ST | 2019 | 60985 | 10101.75 | 336 | 0 | 0 | 0 | 0 | 0 | 10437.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED1013 | Water Main Replacement Cooper & Myrtle ave b/t 70 & 71st, qn | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 405 | WM-0001 |  |  | WM REPLACEMENT COOPER & MYRTLE AVES B/T 70 & 71 ST, QNS | 2019 | 235 | 0 | 235 | 0 | 0 | 0 | 0 | 0 | 235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED1014 | Rehabilitation of Astoria Water Trunk Main by Lining | AUGMENTATION OF WATER SUPPLY SYSTEMS | 401 | WM-0006 SE-0002Q HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | REHABILITATION OF ASTORIA WATER TRUNK MAIN BY LINING IN 41ST STREET BETWEEN 25TH AVENUE AND 28TH AVENUE | 2019 | 3300 | 28197.82 | 2890 | 0 | 0 | 35 | 0 | 0 | 31122.82 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 15
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED1016 | Water Main work in 71 Ave. between Myrtle Ave & 60 St. etc | AUGMENTATION OF WATER SUPPLY SYSTEMS | 405 | WM-0001 SE-0002Q |  |  | WATER MAIN WORK IN 71 AVE. BETWEEN MYRTLE AVE & 60 ST. ETC | 2019 | 308 | 0 | 308 | 0 | 0 | 0 | 0 | 0 | 308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1020 | WM replacement 37th Road b/t 73rd & 74th Street, Qns | AUGMENTATION OF WATER SUPPLY SYSTEMS | 408 | WM-0001 |  |  | WM REPLACEMENT 37TH ROAD B/T 73RD & 74TH STREET, QNS | 2019 | 160 | 0 | 160 | 0 | 0 | 0 | 0 | 0 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1023B | Distr & Trunk WM Replacement Cypress Ave, Queens (Joint Bid) | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 405 | WM-0944 WM-0006 SE-0002Q HW-0200 WM-0001 |  |  | DISTRIBUTION & TRUNK REPLACEMENT CYPRESS AVE B/T WIILLOUGHBY AVE & HIMROD ST, QNS | 2019 | 26150 | 39266.48 | 6647 | 0 | 0 | 0 | 0 | 0 | 45913.48 | 3809.19 | 741 | 0 | 0 | 0 | 0 | 0 | 4550.19
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1027 | Replacement of Dist WM in 222nd St | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 413 | WM-0001 SE-0200Q |  |  | REPLACEMENT OF DIST WM IN 222ND ST BETWEEN JAMAICA AVE AND HEMPSTEAD AVE, ETC. JAMAICA WATER SUPPLU TERRITORY-ZONE 12, QUEENS | 2019 | 34476 | 2215 | 0 | 0 | 0 | 37315 | 0 | 0 | 39530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1036 | Water Main Replacement in Queens Blvd | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 406 | HW-0200 WM-0001 WM-0944 TF-0002 |  |  | WATER MAIN REPLACEMENT IN QUEENS BLVD FROM 63RD RD. TO 69TH AVENUE, ETC | 2019 | 6894 | 758.3 | 1 | 0 | 0 | 10592 | 0 | 0 | 11351.3 | 0 | 0 | 0 | 0 | 23 | 0 | 0 | 23
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1037 | WM Replacement in South Conduit Ave, Queens | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 413 | WM-0001 |  |  | WM REPLACEMENT IN SOUTH CONDUIT AVE BETWEEN 124TH ST AND 134TH ST, ETC QUEENS | 2019 | 12076 | 5753.3 | 2325 | 0 | 0 | 0 | 0 | 0 | 8078.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1038 | Greenpoint Ave b/t 40 & 43 Sts, with HWPS199 | AUGMENTATION OF WATER SUPPLY SYSTEMS | 402 | WM-0001 |  |  | TO REPLACE OLD UNLINED CAST IRON W/M TO IMPROVE WATER QUALITY IN GREENPOINT AVE/48TH AVENUE B/W 40TH STR & 43RD STR. QUEENS | 2019 | 970 | 0 | 820 | 0 | 0 | 0 | 0 | 0 | 820 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1039 | Distribution Water Main Extensions/Replacements, Queens | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 400 | WM-0001 EP-0007 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | DISTRIBUTION WATER MAIN EXTENSIONS/REPLACEMENTS; HYDRANT AND VALVE REPLACEMENTS; NEW BUILDINGS, QUEENS | 2019 | 4400 | 9811.8 | 2022 | 0 | 0 | 0 | 0 | 0 | 11833.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1040 | Select Bus Services Woodhaven Blvd (HWQ100SBA) | AUGMENTATION OF WATER SUPPLY SYSTEMS | 400 | WM-0001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | SELECT BUS SERVICES WOODHAVEN BLVD W/HWQ100SBS | 2019 | 51500 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1042A | Watermain replacement and sewer repair on Queens Blvd | AUGMENTATION OF WATER SUPPLY SYSTEMS | 402 | SE-0002Q WM-0001 WM-0006 |  |  | WATERMAIN REPLACEMENT AND SEWER REPAIR ON QUEENS BLVD FROM 48TH STREET TO 73RD STREET | 2019 | 46661 | 0 | 0 | 87136 | 0 | 0 | 0 | 0 | 87136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1044 | Replacement of Water Mains in Beach 108th Street (SANDR04) | AUGMENTATION OF WATER SUPPLY SYSTEMS | 414 | WM-0001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | REPLACEMENT OF WATER MAINS IN BEACH 108TH STREET BETWEEN BEACH CHANNEL DRIVE AND SHORE FRONT PARKWAY AND OTHER LOCATIONS WITHIN THE AREA. | 2019 | 3428 | 0 | 150 | 3278 | 0 | 0 | 0 | 0 | 3428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1045 | Schl Safety Prog 4 - Replmt of WM 16th Ave bwtn Bell & 212st | AUGMENTATION OF WATER SUPPLY SYSTEMS | 407 | WM-0001 |  |  | SCHOOL SAFETY PROG 4 - REPLACEMENT OF WATER MAIN IN 16TH AVE BETWEEN BELL BOULEVARD & 212TH STREET. INITIATED IN CONJUNCTION WITH DOT PROJECT HWCSCH4C1 | 2019 | 122 | 0 | 122 | 0 | 0 | 0 | 0 | 0 | 122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-976 | SEQ - Trunk Water Main in Francis Lewis Blvd (HWQ976) | TRUNK AND DISTRIBUTION MAIN EXTENSION | 413 | SE-0200Q SE-0002Q TF-0002 TF-0502 HW-0001Q | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | TRUNK MAIN IN FRANCIS LEWIS BLVD - 90 AV TO 99 AV | TRUNK MAIN IN FRANCIS LEWIS BLVD - 90 AV TO 99 AV | 2019 | 38249 | 57397.18 | 910 | 600 | 0 | 0 | 0 | 0 | 58907.18 | 169.22 | 0 | 0 | 0 | 0 | 0 | 0 | 169.22
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-982 | New Trunk WM in Rockaway Beach Blvd (SANDHW13) | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 414 | WM-0006 SE-0002Q | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | NEW TRUNK W/M IN ROCKAWAY BEACH BLVD B/T B 88 ST & B 73 ST | 2019 | 5087 | 12594.37 | 3329 | 0 | 0 | 0 | 0 | 0 | 15923.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED989 | WATER MAIN REPLACEMENT IN VARIOUS LOCATIONS IN QUEENS | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 406 408 409 410 412 | WM-0001 EP-0007 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | NEW WATER MAINS IN VARIOUS LOCATIONS IN QUEENS | 2019 | 13800 | 37622.5 | 4793 | 0 | 0 | 0 | 0 | 0 | 42415.5 | 232.09 | 0 | 0 | 0 | 0 | 0 | 0 | 232.09
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-990 | NEW TRUNK & DISTR WMS IN VERMONT PL B/T CYPRESS & JR | TRUNK AND DISTRIBUTION MAIN EXTENSION | 405 | WM-0006 WM-0001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | NEW TRUNK & DISTR WMS IN VERMONT PL B/T CYPRESS & JACKIE ROBINSON PARKWAY, ETC | 2019 | 6813 | 26912.67 | 0 | 0 | 0 | 290 | 0 | 0 | 27202.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-991 | New WM, Trunk Main Ext, 33 Ave & Francis Lewis Blvd, Queens | TRUNK AND DISTRIBUTION MAIN EXTENSION | 407 411 | WM-0001 WM-0006 TF-0502 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | NEW WM, EXTEND TRUNK MAINS, UPGRADE 33RRD, 37TH & 38 AVE-FRANCIS LEWIS BLVD & UTOPIA PKWY, QNS | 2019 | 44838 | 73222.4 | 662 | 0 | 1500 | 0 | 0 | 0 | 75384.4 | 635.41 | 0 | 0 | 0 | 0 | 0 | 0 | 635.41
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QEDA-001 | Accelerated Distribution WM Replacement & Sewer Rehab - QNS | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 400 | WM-0001 SE-0200Q SE-0002Q | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | ACCELERATED DISTRIBUTION WATER MAIN REPLCMNT & SEWER REBHAB/REPLCMNT,QUEENS | 2019 | 15000 | 16639.72 | 323 | 0 | 0 | 0 | 0 | 0 | 16962.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QEDA-002 | Accelerated Distribution WM Replacement & Sewer Rehab - QNS | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 400 | WM-0001 SE-0200Q |  |  | ACCELERATED DISTRIBUTION WATER MAIN REPLCMNT & SEWER REBHAB/REPLCMNT,QUEENS | 2019 | 22316 | 20577.76 | 1063 | 0 | 0 | 0 | 0 | 0 | 21640.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-383K | QUEENS 5/5A HVAC | GARAGES AND FACILITIES | 405 | S-0136 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | HVAC REPLACEMENT | 2019 | 5150 | 5965.23 | 537 | 0 | 0 | 0 | 0 | 0 | 6502.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-419L | OAU Offices Expansion at CRS | GARAGES AND FACILITIES | 402 | S-0136 PU-0025 |  |  | OFFICE CONSTRUCTION FOR OAU | 2019 | 150 | 411.23 | 157 | 1907 | 0 | 0 | 0 | 0 | 2475.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-423 | Queens 11/13 FLOOR SLAB REPLACEMENT | GARAGES AND FACILITIES | 411 | S-0136 PU-0025 |  |  | FLOOR SLAB REPLACEMENT | 2019 | 11250 | 5425.41 | 1401 | 5264 | 49492 | 0 | 0 | 0 | 61582.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-438 | QUEENS 7 GARAGE REHABILITATION | GARAGES AND FACILITIES | 407 | S-0136 |  |  | REHABILITATION OF QUEENS 7 GARAGE | 2019 | 28680 | 4153.33 | 724 | 18304 | 1816 | 0 | 0 | 0 | 24997.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANBROAD2 | BROAD CHANNEL LIBRARY GUTTERS AND LEADERS | RECONSTRUCTION NECESSARY TO MAINTAIN FACILITIES | 414 | LQ-0122 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | DEMOLISH EXISTING ROOF GUTTER AND DOWNSPOUTS, AND REPLACE WITH NEW-INKIND GUTTER AND DOWNSPOUTS. FINISH AND PAINT GUTTER AND DOWNSPOUTS AS PER EXISTING CONDITIONS. THE ROOF DRAINGE SYSTEM SHALL BE APPROPRIATELY SIZED FOR ROOF LOAD. | 2019 | 36 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 32
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SAND1187 | Recon of Norton Drive - Hurricane Sandy (HWQ1187, SEQ200595) | PRIMARY STREET RECONSTRUCTION | 400 | HW-0001Q | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | RECONSTRUCTION OF NORTON DRIVE - HURRICANE SANDY | RECONSTRUCTION OF NORTON DRIVE - HURRICANE SANDY | 2019 | 1732 | 41.55 | 0 | 0 | 0 | 152 | 0 | 0 | 193.55 | 194 | 0 | 0 | 0 | 1364 | 0 | 0 | 1558
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBROAD | SANDY DAMAGES BROAD CHANNEL BRANCH LIBRARY | RECONSTRUCTION NECESSARY TO MAINTAIN FACILITIES | 414 | LQ-0122 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | HURRICANE SANDY RELATED DAMAGES AT BROAD CHANNEL BRANCH LIBRARY | 2019 | 1095 | 51.67 | 0 | 0 | 0 | 0 | 0 | 0 | 51.67 | 250.05 | 0 | 0 | 216 | 0 | 0 | 0 | 466.05
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDELEC5 | 100 the precint electrical system replacement, Sandy | POLICE FACILITIES | 414 | PO-0079 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES |  | 100 THE PRECINT ELECTRICAL SYSTEM REPLACEMENT, SANDY | 2019 | 1802 | 360.52 | 1215 | 0 | 0 | 0 | 0 | 0 | 1575.52 | 315.23 | 2482 | 0 | 0 | 0 | 0 | 0 | 2797.23
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW10 | Reconstruction of Willets Point - Hurricane Sandy | PRIMARY STREET RECONSTRUCTION | 400 | HW-0001Q | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | RECONSTRUCTION OF WILLETS POINT - HURRICANE SANDY | RECONSTRUCTION OF WILLETS POINT - HURRICANE SANDY | 2019 | 5825 | 25 | 0 | 0 | 448 | 0 | 0 | 0 | 473 | 0 | 0 | 0 | 4015 | 0 | 0 | 0 | 4015
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW11 | Recon of Beach Channel Drive - Hurricane Sandy (QED-1030) | PRIMARY STREET RECONSTRUCTION | 400 | HW-0001Q | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | RECONSTRUCTION OF BEACH CHANNEL DRIVE - HURRICANE SANDY | RECONSTRUCTION OF BEACH CHANNEL DRIVE - HURRICANE SANDY | 2019 | 12427 | 3257.43 | 1803 | 0 | 0 | 4732 | 0 | 0 | 9792.43 | 7733.23 | 7212 | 0 | 0 | 3768 | 0 | 0 | 18713.23
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW12 | Reconstruction of Edgemere - Hurricane Sandy (QED-1007) | PRIMARY STREET RECONSTRUCTION | 400 | HW-0001Q | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | RECONSTRUCTION OF EDGEMERE - HURRICANE SANDY | RECONSTRUCTION OF EDGEMERE - HURRICANE SANDY | 2019 | 5392 | 2293.4 | 4 | 0 | 0 | 26 | 0 | 0 | 2323.4 | 4933.62 | 15 | 0 | 0 | 104 | 0 | 0 | 5052.62
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW13 | Reconstruction of Rockaway Beach - Hurricane Sandy (QED-982) | PRIMARY STREET RECONSTRUCTION | 400 | HW-0001Q HW-0200 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | RECONSTRUCTION OF ROCKAWAY BEACH - HURRICANE SANDY | RECONSTRUCTION OF ROCKAWAY BEACH - HURRICANE SANDY | 2019 | 14603 | 4218.88 | 3815 | 0 | 0 | 3 | 0 | 0 | 8036.88 | 13615.38 | 13202 | 0 | 0 | 11 | 0 | 0 | 26828.38
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW24 | WHEN AND WHERE HURRICANE SANDY - QUEENS | PRIMARY STREET RECONSTRUCTION | 400 | WM-0001 HW-D103 HW-0001Q SE-087HW | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | WHEN AND WHERE HURRICANE SANDY - QUEENS | RECONSTRUCTION OF ROCKAWAY - HURRICANE SANDY | 2019 | 22186 | 7803.94 | 0 | 297 | 829 | 218 | 0 | 0 | 9147.94 | 8319.72 | 0 | 0 | 0 | 0 | 0 | 0 | 8319.72
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW26 | Reconstruction of East 10th Road - Hurricane Sandy | PRIMARY STREET RECONSTRUCTION | 400 | HW-0001Q | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | RECONSTRUCTION OF EAST 10TH ROAD - HURRICANE SANDY | RECONSTRUCTION OF EAST 10TH ROAD - HURRICANE SANDY | 2019 | 620 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 44 | 1.73 | 0 | 382 | 0 | 0 | 0 | 0 | 383.73
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR02 | FAR ROCKAWAY BUSINESS DISTRICT IMPROVEMENTS (SE-830) | PRIMARY STREET RECONSTRUCTION | 400 414 | HW-0001Q ED-0384 HW-0200 TF-0002 TF-0502 HW-0944 HW-D103 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | FAR ROCKAWAY IMPROVEMENTS BUSINESS DISTRICT | FAR ROCKAWAY IMPROVEMENTS BUSINESS DISTRICT | 2019 | 2400 | 2341.73 | 22247 | 0 | 0 | 2269 | 0 | 0 | 26857.73 | 882.93 | 11165 | 0 | 0 | 0 | 0 | 0 | 12047.93
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR04 | Beach 108th Streetscape Improvements (QED-1044) | PRIMARY STREET RECONSTRUCTION | 400 | HW-0001Q | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | BEACH 108TH STREETSCAPE IMPROVEMENTS | BEACH 108TH STREETSCAPE IMPROVEMENTS | 2019 | 8200 | 459.45 | 0 | 3964 | 0 | 0 | 0 | 0 | 4423.45 | 913.19 | 0 | 11292 | 0 | 905 | 0 | 0 | 13110.19
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDY4-30 | Tide Gate - FEMA 406 In-Kind, HMP & 428 Conduit | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | TIDE GATE - FEMA 406 IN-KIND, HMP & 428 CONDUIT | 2019 | 1311 | 20.57 | 2 | 0 | 111 | 0 | 0 | 0 | 133.57 | 185.17 | 2 | 0 | 990 | 0 | 0 | 0 | 1177.17
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDY4-31 | Tide Gate - 404 HMGP | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-1018 |  |  | TIDE GATE - 404 HMGP | 2019 | 5962 | 444.04 | 0 | 0 | 1379 | 0 | 0 | 0 | 1823.04 | 0 | 0 | 0 | 4138 | 0 | 0 | 0 | 4138
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-789B-3 | B 63 ST - BAYFIELD AV & ROCKAWAY FWAY (SOMMERVILLE III) | EXTENSIONS TO ACCOMMODATE NEW DEVELOPMENT | 414 | SE-0789 WM-0001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | B 63 ST - BAYFIELD AV & ROCKAWAY FWAY (SOMMERVILLE III) | B 63 ST - BAYFIELD AV & ROCKAWAY FWAY (SOMMERVILLE III) | 2019 | 6190 | 0 | 0 | 0 | 0 | 4600 | 0 | 0 | 4600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-807 | Storm & San Sewers in 20th Ave b/t 126 St & US Bulkhead Line | PROGRAMMATIC REPLACEMENT AND RECONSTRUCTION | 407 | SE-0002Q WM-0001 SE-0004 |  |  | STORM & SAN SEWERS IN 20TH AVE B/T126 ST & US BULKHEAD LINE, ETC WATER MAIN WORKS. ABANDONED REGULATOR R-5 | 2019 | 18910 | 124811.76 | 5803 | 244 | 0 | 0 | 0 | 0 | 130858.76 | 508.21 | 0 | 0 | 0 | 0 | 0 | 0 | 508.21
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-809 | STORM & SAN SEWERS IN N.B WHITESTONE EXPWY SERV RD PHASE 1 | PROGRAMMATIC REPLACEMENT AND RECONSTRUCTION | 407 | SE-0200Q | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | PHASE 1, STORM & SAN SEWERS IN N.B WHITESTONE EXPWY SERV RD B/T 25TH AV & FLUSHING RIVER, ETC WM WORK. | 2019 | 18869 | 81494.7 | 419 | 0 | 71 | 49 | 0 | 0 | 82033.7 | 179.47 | 0 | 0 | 0 | 0 | 0 | 0 | 179.47
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-810 | STORM & SAN SWR, WILLET PT BLVD WHITESTONE AREA PHASE 2 | PROGRAMMATIC REPLACEMENT AND RECONSTRUCTION | 407 | SE-0002Q SE-0200Q WM-0001 HW-0001Q HW-0200 SE-0944 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | WHITESTONE AREA PHASE 2 STORM & SAN SWR, WILLET PT BLVD (25TH AVENUE)BETWEEN 149TH STREET AND PARSONS BLVD, ETC. WATER MAIN WORKS | 2019 | 13279 | 66456.4 | 16370 | 300 | 0 | 4677 | 0 | 0 | 87803.4 | 4570.76 | 1080 | 168 | 0 | 0 | 0 | 0 | 5818.76
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-811 | STORM & SAN SWR, N.B. WHITESTONE EXPWY SERV RD PHASE 3 | PROGRAMMATIC REPLACEMENT AND RECONSTRUCTION | 407 | SE-0200Q SE-0002Q WM-0001 HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | WHITESTONE AREA PHASE 3, STORM & SAN SWR, N.B. WHITESTONE EXPWY SERV RD BETWEEN 15TH AVENUE AND 25TH AVENUE, ETC WATER MAIN WORKS | 2019 | 11333 | 2722 | 0 | 0 | 0 | 55771 | 0 | 0 | 58493 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-814 | REPL OF COMB SEWER IN CALAMUS AV B/T 74 ST & 69 ST, ETC | EXTENSIONS TO ACCOMMODATE NEW DEVELOPMENT | 402 | SE-0002Q WM-0001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | REPL OF COMB SEWER IN CALAMUS AV B/T 74 ST & 69 ST, ETC | 2019 | 20296 | 32732.87 | 1154 | 0 | 0 | 0 | 0 | 0 | 33886.87 | 29.7 | 0 | 0 | 0 | 0 | 0 | 0 | 29.7
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-823 | SEQ - 229th Street Laurelton Area - Part 1, Phase A (HWQ823) | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 413 | SE-0200Q SE-0002Q WM-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | HI LEVEL STRM & COMB SWRS IN 229 ST, BTW 145 & 147 AVES. SE QUEENS LAURELTON AREA | 2019 | 19793 | 84660.35 | 0 | 0 | 0 | 24830 | 0 | 0 | 109490.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-824 | SEQ - 230th Place Laurelton Area - Part 1, Phase B | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 413 | SE-0200Q SE-0002Q WM-0001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | SOUTH-EAST QUEENS LAURELTON AREA PART 1 PHASE B. STORM, SANITARY AND COMBINES SEWERS IN 230TH PLACE BETWEEN 145TH AVENUE AND 139TH AVENUE, ETC. | 2019 | 105667 | 520 | 0 | 0 | 121155 | 0 | 0 | 0 | 121675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-825 | SEQ - Laurelton Area - Part 1, Phase C | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 413 | SE-0200Q SE-0002Q WM-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | SOUTH-EAST QUEENS LAURELTON AREA PART 1 PHASE C. STORM, SANITARY AND COMBINED SEWERS IN 138TH AVENUE BETWEEN 225TH STREET AND 230TH PLACE, ETC. | 2019 | 74335 | 300 | 0 | 0 | 0 | 0 | 0 | 112857 | 113157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-829 | Storm and Sanitary Sewers in Brundwick Ave, Queens | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 414 | SE-0200Q SE-0002Q WM-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | STORM AND SANIRTATY SEWERS IN BRUNDWICK AVE BETWEEN DOUGHTY BLVD. AND NAMEOKE AVE. ETC. | 2019 | 20701 | 50 | 0 | 0 | 0 | 30865 | 0 | 0 | 30915 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-830 | Storm & Sanitary Sewers, WM Work in Mott Ave, QNS (SANDR02) | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 414 | SE-0200Q SE-0002Q WM-0001 EP-0007 |  |  | STORM & SANITARY SEWERS, WM WORK IN REDFERN AVE B/T MOTT AVE & NAMEOKE AVE, QNS - HWQ1079 | 2019 | 57472 | 850 | 102583 | 0 | 0 | 0 | 0 | 0 | 103433 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-831 | Storm and sanitary sewers in Beach Channel Drive | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 414 | SE-0200Q SE-0002Q WM-0001 |  |  | STORM AND SANITARY SEWERS IN BEACH CHANNEL DRIVE BETWEEN CORNAGA AVE AND HASSOCK ST; ETC. WATER MAIN WORK | 2019 | 8529 | 0 | 0 | 0 | 0 | 7755 | 0 | 0 | 7755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-842A | SEQ - Storm, Sanitary Sewers & WM in 225th Street | REPLACEMENT OF CHRONICALLY FAILING COMPONENTS | 413 | SE-0200Q SE-0002Q WM-0001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | STRM, SAN SWERS & WM 225ST & B/T 145RD & 149AVE QNS | 2019 | 58431 | 820.04 | 0 | 0 | 0 | 0 | 65477 | 0 | 66297.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-842A1 | SEQ - Storm Sewer Outlet in 224th Street | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 413 | SE-0200Q | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | STORM SEWER OUTLET IN 224TH STREET BETWEEN 149TH AVE AND A POINT APPROXIMATELY 200 FEET DUE SOUTH OF ROCKAWAY BLVD | 2019 | 95416 | 1039.35 | 0 | 93717 | 0 | 0 | 0 | 0 | 94756.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-842B | SEQ - Storm & Sanitary Sewers & WM Work in 224th Street | AUGMENTATION OF WATER SUPPLY SYSTEMS | 413 | SE-0200Q SE-0002Q WM-0001 |  |  | STORM & SANITARY & W/M WORK IN 224TH STREET B/W 146TH AVENUE AND SOUTH CONDUIT AVENUE | 2019 | 35618 | 1104.7 | -964 | 0 | 0 | 0 | 57107 | 0 | 57247.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-842C | SEQ - Storm Sewer in South Conduit Ave | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 413 | SE-0200Q WM-0001 SE-0002Q WP-0169 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | STRM SWR ON SO CONDUIT AV,. BTW 224 ST & SPRINGFIELD BLVD | 2019 | 59456 | 2232.55 | 0 | 0 | 0 | 0 | 0 | 59456 | 61688.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE848 | SEQ - Sewer & WM Work in Baisley Blvd, Guy R Brewer Blvd | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 412 | SE-0200Q WM-0001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | STORM EXTENSIONS, CATCH BASINS, SANITARY REPLACEMENTS AND WM WORK IN BAISLEY BLVD., GUY R. BREWER BLVD., AND N. CONDUIT AVENUE AREA IN QUEENS | 2019 | 30786 | 61434.68 | 266 | 0 | 0 | 0 | 0 | 0 | 61700.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-850 | SEQ - Storm & Sani Sewers, Force Main & WM in Liverpool St. | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 412 | SE-0002Q SE-0200Q WM-0001 |  |  | STRM, SAN SWRS, FORCE MAIN AND WM IN LIVERPOOL ST. B/T SHORE AVE AND 119 AVE | 2019 | 79001 | 125 | 0 | 0 | 43317 | 0 | 0 | 0 | 43442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-854 | SEQ - Storm, Sanitary Sewers & WM in 119th Ave, Queens | REPLACEMENT OF CHRONICALLY FAILING COMPONENTS | 412 | SE-0200Q SE-0002Q WM-0001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | TORM & SANI SWR & WM REPLACE. 119 AVE & 192-195 STS, QNS | 2019 | 15783 | 25832.71 | 249 | 0 | 0 | 0 | 0 | 0 | 26081.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-859 | Combined Sewer Replmnt & WM work 70 st & calamus ave, Qns | REPLACEMENT OF CHRONICALLY FAILING COMPONENTS | 402 | SE-0002Q WM-0001 EP-0007 HW-0200 SE-1000 SE-0944 TF-0002 TF-0502 |  |  | OMBINED SEWER REPLACEMENT & WATER MAIN WORK 70TH ST & CALAMUS AVE, QNS | 2019 | 32854 | 1469.16 | 110868 | 0 | 0 | 0 | 0 | 0 | 112337.16 | 0 | 6013 | 0 | 0 | 0 | 0 | 0 | 6013
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-860 | Combined Swr Replac & WM work 71st, QNS | REPLACEMENT OF CHRONICALLY FAILING COMPONENTS | 402 | SE-0002Q WM-0001 |  |  | COMBINED SEWER REPLACEMENT & WATER MAIN WORK 71ST & JUNIPER VALLEY BLVD, QNS | 2019 | 59467 | 0 | 0 | 0 | 55646 | 0 | 0 | 0 | 55646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-862 | SEQ - Storm & Sanitary Sewer Replcmnt/Ext. 146 Ave (HWQ662G) | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 413 | SE-0200Q WM-0001 SE-0002Q WM-0006 |  |  | STORM AND SANITARY SEWER REPLACEMENT AND EXTENSIONS AND WM WORK IN 146TH AVE BETWEEN 153RD PL AND 159TH ST, ETC. QUEENS | 2019 | 80778 | 920 | 98 | 82217 | 0 | 0 | 0 | 0 | 83235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-885 | SEQ - 150th St Spine: Phase I, Outlet at Bergen Basin | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 413 | SE-0200Q |  |  | NEW STORM SEWER OUTLET AT BERGEN BASIN | 2019 | 50976 | 1085.8 | 0 | 0 | 49380 | 0 | 0 | 0 | 50465.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-885A | SEQ - 150th St Spine: Phase II, Trunk Storm Sewer in JFK | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 412 413 | SE-0002Q SE-0200Q |  |  | TRUNK STORM SEWER 150TH STREET SPINE THAT GOES THROUGH JFK, QUEENS | 2019 | 3940 | 0 | 8022 | 0 | 0 | 0 | 199864 | 0 | 207886 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-886 | Storm & Sanitary Sewers in Beach Channel Drive, Qns | EXTENSIONS TO ACCOMMODATE NEW DEVELOPMENT | 414 | SE-0200Q SE-0002Q WM-0001 |  |  | STORM & SANITARY SEWERS, WM WORK, ETC IN BEACH CHANNEL DR BETWEEN REGINA AVE & HASSOCK STREET, QNS | 2019 | 12883 | 200 | 0 | 12883 | 0 | 0 | 0 | 0 | 13083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-887 | Storm & Sanitary Sewers, WM work in Cornaga Ave, Qns | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 414 | SE-0200Q SE-0002Q WM-0001 |  |  | STORM & SANITARY SEWERS, WM WORK IN CORNAGA AVE BETWEEN MOTT AVE & BEACH CHANNEL DRIVE, QNS | 2019 | 25148 | 200 | 0 | 25148 | 0 | 0 | 0 | 0 | 25348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-889 | SEQ - New Storm Sewer N. Conduit Ave | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 412 | SE-0200Q | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | NEW STRM SWR N. CONDUIT AV -BAISLY BLVD S TO GUY BREWER BLVD | 2019 | 112349 | 500 | 35 | 0 | 110829 | 0 | 0 | 0 | 111364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002539 | SEQ - Storm & Sanitary Sewers in 111th Ave (HWQ002539) | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 413 | SE-0944 SE-0002Q SE-0200Q WP-0169 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | STORM AND SANITARY SEWERS IN 111TH AVE BETWEEN COLFAX ST AND 204TH ST; ETC. | 2019 | 25689 | 17688.32 | 5668 | 0 | 0 | 4634 | 0 | 0 | 27990.32 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 15
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002568 | Combined Sewer in Albert Rd, Queens (HWQ411B) | EXTENSIONS TO ACCOMMODATE NEW DEVELOPMENT | 410 | SE-0002Q WM-0001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | COMBINED SEWER IN ALBERT RD - CENTERVILLE ST & N. CONDUIT AV | COMBINED SEWER IN ALBERT RD - CENTERVILLE ST & N. CONDUIT AV | 2019 | 3360 | 26423.88 | 1247 | 0 | 0 | 0 | 0 | 0 | 27670.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002583 | SANITARY SEWERS IN B 54 ST - ALMEDA AV & B CHANNEL DR | REPLACEMENT OF CHRONICALLY FAILING COMPONENTS | 414 | SE-0002Q WM-0001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | SANITARY SEWERS IN B 54 ST - ALMEDA AV & B CHANNEL DR | SANITARY SEWERS IN B 54 ST - ALMEDA AV & B CHANNEL DR | 2019 | 436 | 0 | 0 | 0 | 0 | 436 | 0 | 0 | 436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002681 | SAN & STRM SWR IN B. 72 ST B/T BAYVIEW AV & THURSBY AV | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 414 | SE-0002Q SE-0200Q WM-0001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | SAN & STRM SWR IN B. 72 ST B/T BAYVIEW AV & THURSBY AV IN SOMMERVILLEAREA (HWQ-631B2) | 2019 | 12204 | 3 | 0 | 0 | 0 | 0 | 0 | 13423 | 13426 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002689 | Combined sewer ext. in Barnett Ave. between 48st/Woodside Av | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 402 | SE-0002Q WM-0001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | COMBINED SEWER EXT. IN BARNETT AVE. BETWEEN 48TH STREET AND WOODSIDE AVE | 2019 | 740 | 0 | 0 | 0 | 0 | 616 | 0 | 0 | 616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002693 | Combined Sewer and Water Main Replacements at Penelope Ave. | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 405 | SE-0002Q WM-0001 SE-1000 HW-0200 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | COMBINED SEWER AND WATERMAIN REPLACEMENTS AT PENELOPE AVE. B/T 71STREET AND 74TH STREET, ETC., | 2019 | 8838 | 28393.83 | 8897 | 0 | 0 | 0 | 0 | 0 | 37290.83 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 15
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002700 | REHABILITATION OF COMBINED SEWER AND WATER MAIN | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 405 | SE-0002Q WM-0001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | REHABILITATION OF COMBINED SEWER AND WATER MAIN IN 73RD PLACE AREA INMIDDLE VILLAGE | 2019 | 4893 | 39.69 | 0 | 0 | 0 | 5382 | 0 | 0 | 5421.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002709 | Combined Sewer Installation in 45th Avenue | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 407 | SE-0002Q HW-0200 |  |  | COMBINED SEWER INSTALLATION IN 45TH AVENUE BETWEEN 163RD STREET AND 166ST, ETC, BOROUGH OF QUEENS. | 2019 | 1350 | 2155.13 | 1511 | 300 | 0 | 0 | 0 | 0 | 3966.13 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 7
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002710 | Combined sewer replcmnt & water main work in Selfridge St. | REPLACEMENT OF CHRONICALLY FAILING COMPONENTS | 406 | SE-0002Q WM-0001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | COMBINED SEWER REPLCMNT & WATER MAIN WORK IN SELFRIDGE ST. BET METROPOLITAN AVE & LOUBET ST, ETC, QUEENS | 2019 | 6391 | 0 | 0 | 0 | 5811 | 0 | 0 | 0 | 5811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002711 | Combilned Sewer in Main Street betwwen 40th Road and 41 St. | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 407 | SE-0002Q |  |  | COMBILNED SEWER IN MAIN STREET BETWWEN 40TH ROAD AND 41 ST., QUEENS. | 2019 | 278 | 0 | 278 | 0 | 0 | 0 | 0 | 0 | 278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002714 | Sanitary Sewer & WM Work in 150th Ave, Queens (Joint Bid) | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 410 | SE-0002Q WM-0001 SE-0200Q SE-1000 EP-0007 SE-0944 HW-0200 |  |  | SANITARY SEWER EXTENSION & WATER MAIN WORK 126-129 STS & 150 AVE, QNS | 2019 | 5637 | 400 | 6626 | 0 | 0 | 0 | 0 | 0 | 7026 | 0 | 164 | 0 | 0 | 0 | 0 | 0 | 164
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200426 | STORM SEWERS IN B 54 ST - ALMEDA AV & B CHANNEL DR | REPLACEMENT OF CHRONICALLY FAILING COMPONENTS | 414 | SE-0200Q | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | STORM SEWERS IN B 54 ST - ALMEDA AV & B CHANNEL DR | STORM SEWERS IN B 54 ST - ALMEDA AV & B CHANNEL DR | 2019 | 101 | 0 | 0 | 0 | 0 | 101 | 0 | 0 | 101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200446 | SEQ - Storm Sewers in Hook Creek Blvd (HWQ274F1) | EXTENSIONS TO ACCOMMODATE NEW DEVELOPMENT | 413 | SE-0200Q WM-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | STORM SEWERS IN HOOK CREEK BLVD - 253 ST AND 149 RD | STORM SEWERS IN HOOK CREEK BLVD - 253 ST AND 149 RD | 2019 | 4006 | 12382.93 | 0 | 0 | 0 | 2969 | 0 | 0 | 15351.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200463 | Storm & San Sewers in College point b/t 9 av & US Bulkhead | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 407 | SE-0004 SE-0002Q | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | STORM & SAN SEWERS IN COLLEGE POINT B/T 9 AV & US BULKHEAD | 2019 | 4511 | 20600.56 | 350 | 60 | 0 | 0 | 0 | 0 | 21010.56 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 6
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200467 | STRM & SAN SWRS IN 14 AV B/T 115 ST & US BULKHEAD LINE | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 407 | SE-0004 SE-0002Q WM-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | STRM & SAN SWRS IN 14 AV B/T 115 ST & US BULKHEAD LINE | 2019 | 7417 | 90 | 0 | 0 | 0 | 8158 | 0 | 0 | 8248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200490 | Storm Sewer in 95th Street, Queens | EXTENSIONS TO ACCOMMODATE NEW DEVELOPMENT | 410 | SE-0200Q WM-0001 HW-0200 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | STRM SWR IN 95TH STREET B/T 160TH AVENUE & 162ND AVENUE, ETC | 2019 | 1202 | 12005.34 | 1319 | 0 | 0 | 0 | 0 | 0 | 13324.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200492 | Storm sewer extension and san. replacement @ 41st avenue, | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 411 407 | SE-0200Q WM-0001 |  |  | STORM SEWER EXTENSION AND SAN. REPLACEMENT @ 41ST AVENUE, BET 233RD ST AND 235TH ST. , ETC. BOROUGH OF QUEENS | 2019 | 3685 | 9945.14 | 300 | 80 | 0 | 0 | 0 | 0 | 10325.14 | 8.4 | 0 | 0 | 0 | 0 | 0 | 0 | 8.4
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200519 | SEQ - Brookville-Edgewood Triangle West - Phase II (HWQ724B) | EXTENSIONS TO ACCOMMODATE NEW DEVELOPMENT | 413 | SE-0200Q WM-0001 SE-0002Q SE-0005 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | BROOKVILLE- EDGEWOOD TRIANGLE, WEST (HWQ-724B PAHSE II) STORM AND SANITARY SEWERS IN BROOKVILLE BLVD BETWEEN NEWHALL AVE AND 147TH AVENUE, ETC. WATER MANIN WORKS | 2019 | 10475 | 2405.45 | 42 | 59026 | 0 | 0 | 0 | 0 | 61473.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200524 | Storm & Sanitary Sewers in B. 21st Street, Queens | PROGRAMMATIC REPLACEMENT AND RECONSTRUCTION | 414 | SE-0200Q SE-0002Q WM-0001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | STRM & SAN SWR IN B. 21 ST B/T NEW HAVEN AV & ELK COURTS | 2019 | 6816 | 20740.81 | 3208 | 0 | 0 | 0 | 0 | 0 | 23948.81 | 5.25 | 0 | 0 | 0 | 0 | 0 | 0 | 5.25
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200529 | SEQ - Storm & Combined Sewers in 130th Road (Joint Bid) | EXTENSIONS TO ACCOMMODATE NEW DEVELOPMENT | 413 | SE-0004 HW-0001Q SE-0944 SE-0002Q | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | STORM & COMB SWRS IN 130TH RD B/T 244 ST & BROOKLVILLE BLVD | 2019 | 4033 | 17267.95 | 1043 | 0 | 0 | 1004 | 0 | 0 | 19314.95 | 1067.82 | 437 | 0 | 0 | 0 | 0 | 0 | 1504.82
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200531 | SEQ - Storm Sewer Ext in 239th Street, Queens (Joint Bid) | EXTENSIONS TO ACCOMMODATE NEW DEVELOPMENT | 413 | SE-0200Q WM-0001 SE-0944 HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | STORM SEWER EXT @ 239 ST B/T 87 AV AND 88 AV | 2019 | 8048 | 9783.93 | 513 | 0 | 0 | 2444 | 0 | 0 | 12740.93 | 0 | 656 | 0 | 0 | 0 | 0 | 0 | 656
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200536 | SEQ - Storm Sewer & Water Main in 182nd Street | REPLACEMENT OF CHRONICALLY FAILING COMPONENTS | 412 | SE-0200Q WM-0001 SE-1000 HW-0200 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | STORM SEWER AND WATER MAIN IN 182ND STREET BETW. HILLSIDE AVE AND 90TH AVE. | 2019 | 1025 | 3106.02 | 1752 | 0 | 0 | 0 | 0 | 0 | 4858.02 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 5
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200547 | SEQ - Storm Sewer in Commonwealth Blvd | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 413 | SE-0200Q WM-0001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | STORM SEWER IN: COMMONWEATH BOULEVARD BETWEEN GRAND CENTRAL PARKWAY (SERVICE ROAD SOUTH) AND UNION TURNPIKE. | 2019 | 5590 | 154.2 | 0 | 0 | 0 | 0 | 9254 | 0 | 9408.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200553 | Combined & HLSS & WM Work in Lefferts Blvd | REPLACEMENT OF CHRONICALLY FAILING COMPONENTS | 408 409 | HW-0200 EP-0007 SE-1000 SE-0200Q SE-0944 WM-0001 SE-0004 |  |  | 1.COMB.&HIGH LEVEL STORM SEWER & WM WORK IN LEFFERTS BLVD. BETWEEN METROPOLITAN AVE AND 85TH AVE. 2.STORM SEWER AND WATER MAIN WORK IN 84TH RD. BETWEEN LANDER ST. AND MAIN ST. | 2019 | 4105 | 484.12 | 1242 | 0 | 0 | 0 | 3344 | 0 | 5070.12 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 5
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200561 | SEQ - Storm Sewer Extension in 91st Road | EXTENSIONS TO ACCOMMODATE NEW DEVELOPMENT | 413 | SE-0200Q | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | STORM SEWER EXTENSION IN 91ST ROAD AND 221ST PLACE IN QUEENS | 2019 | 361 | 196.17 | 0 | 0 | 0 | 849 | 0 | 0 | 1045.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200562 | SEQ - Storm Sewer & WM Work in 158th Street (HWQ121B3) | EXTENSIONS TO ACCOMMODATE NEW DEVELOPMENT | 412 | SE-0200Q SE-1000 WM-0001 SE-0002Q | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | STORM EXT, REPLACE & WM WORK, 158 ST B/T 110 & 116 AVE, QNS | 2019 | 291 | 0 | 0 | 16189 | 0 | 0 | 0 | 0 | 16189 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200569 | Construction of Storm Sewers in 204th Street, Queens. | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 411 | SE-0200Q SE-0002Q HW-0200 |  |  | CONSTRUCTION OF STORM SEWERS IN 204TH STREET, QUEENS. | 2019 | 784 | 4262.78 | 223 | 181 | 0 | 0 | 0 | 0 | 4666.78 | 3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200578 | SEQ - Storm & San Sewers, WM Work in Foch Blvd (HWQ200578) | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 412 | SE-0200Q SE-0002Q EP-0007 WM-0001 |  |  | 1-STORM & SANITARY SEWERS & WM IN FOCH BLVD B/T MERRICK BLVD. & 166THST. 2-STORM SEWER AND WATER MAIN IN ILION AVE B/T FARMERS BLVD. & WOOD ST. | 2019 | 12935 | 500 | 17651 | 0 | 0 | 0 | 0 | 0 | 18151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200580 | CULVERT IN 147 AV - 235 ST AND 232 ST | EXTENSIONS TO ACCOMMODATE NEW DEVELOPMENT | 413 | SE-0200Q | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | CULVERT IN 147 AV - 235 ST AND 232 ST | CULVERT IN 147 AV - 235 ST AND 232 ST | 2019 | 4622 | 5587.99 | 113 | 0 | 0 | 0 | 0 | 0 | 5700.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200582 | Storm & Combined Sewer in Cross Bay Blvd (HWQ1182A) | PROGRAMMATIC REPLACEMENT AND RECONSTRUCTION | 414 | SE-0200Q SE-0002Q WM-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | STRM & COMB SWR IN CROSS BAY BLVD, B/T E. 8 RD & W. 13 RD | 2019 | 26495 | 26162.34 | 1818 | 0 | 0 | 218 | 0 | 0 | 28198.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200583 | Storm & Sanitary Sewers in James Court (HWQ1184A) | EXTENSIONS TO ACCOMMODATE NEW DEVELOPMENT | 410 | SE-0200Q SE-0002Q |  |  | STORM & SANITARY SEWERS IN JAMES COURT BETWEEN 104 ST & BULKHEAD, QUEENS (HWQ1184A) | 2019 | 2496 | 100 | 2119 | 0 | 0 | 0 | 0 | 0 | 2219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200584 | Storm and Sanitary Sewers in 119th Road | EXTENSIONS TO ACCOMMODATE NEW DEVELOPMENT | 412 | HW-0200 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | STORM AND SANTITARY SEWERS IN 119TH ROAD BETWEEN 180TH STREET AND 177TH PLACE, ETC. WATER MAIN WORKS. | 2019 | 7345 | 11404.54 | 303 | 0 | 0 | 0 | 0 | 0 | 11707.54 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 6
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200586 | Broad Channel: Storm & San Sewers in W 11th Rd. (HWQ1182B) | EXTENSIONS TO ACCOMMODATE NEW DEVELOPMENT | 414 | SE-0200Q SE-0002Q WM-0001 |  |  | BROAD CHANNEL: STORM AND SAN SEWERS IN W 11TH RD. (198 AV) B/T CROSSBAY BLVD AND BROAD CHANNEL RD. | 2019 | 25000 | 0 | 0 | 55811 | 0 | 0 | 0 | 0 | 55811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200595 | Westbourne Ave-Norton Drive Recon (HWQ1187, SAND1187) | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 414 | WM-0001 SE-0200Q | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | INSTALLATION AND REPLACEMENT OF STORM SEWERS ALONG NORTON DRIVE BETWEEN COLDSPRING ROAD AND WESTBOURNE AVENUE. REPLACEMENT OF WATERMAINS ALONG NORTON DRIVE BETWEEN COLDSPRING ROAD AND WESTBOURNE AVENUE. | 2019 | 16200 | 0 | 116 | 0 | 0 | 16084 | 0 | 0 | 16200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200596 | SEQ - Storm Sewer Installation & WM in 183rd Street | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 412 | SE-0200Q WP-0169 SE-0002Q EP-0007 WM-0001 HW-0200 TF-0002 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | STORM SEWER & WATER MAIN REPLACEMENT IN 183 ST B/T 90TH & JAMAICA AVENUE, QUEENS | 2019 | 9494 | 1058.36 | 10626 | 0 | 0 | 894 | 0 | 0 | 12578.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ201BN8 | Reconstruction of Existing Sewers, Queens | REPLACEMENT OF CHRONICALLY FAILING COMPONENTS | 400 | EP-0007 SE-0002Q |  |  | RECONSTRUCTION OF EXISTING SEWERS, QUEENS | 2019 | 6500 | 13178.3 | 2113 | 0 | 0 | 0 | 0 | 0 | 15291.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ201BN9 | Reconstruction of Existing Sewers, North Queens | REPLACEMENT OF CHRONICALLY FAILING COMPONENTS | 400 | SE-0002Q EP-0007 |  |  | RECONSTRUCTION OF EXISTING SEWERS, NORTH QUEENS | 2019 | 6700 | 7485.68 | 9900 | 0 | 0 | 0 | 0 | 0 | 17385.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ201BS9 | Reconstruction of Existing Sewers, South Queens | REPLACEMENT OF CHRONICALLY FAILING COMPONENTS | 400 | SE-0002Q |  |  | RECONSTRUCTIION OF EXISTING SEWERS, SOUTH QUEENS | 2019 | 7800 | 8538.3 | 0 | 5444 | 0 | 0 | 0 | 0 | 13982.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQBN10 | Reconstruction of Existing Sewers, North Queens | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 400 | EP-0007 SE-0002Q |  |  | RECONSTRUCTION OF EXISTING SEWERS, NORTH QUEENS | 2019 | 7250 | 0 | 7150 | 0 | 0 | 0 | 0 | 0 | 7150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQBS10 | Reconstruction of Existing Sewers, South Queens | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 401 | SE-0002Q EP-0007 |  |  | RECONSTRUCTION OF EXISTING SEWERS, SOUTH QUEENS | 2019 | 7850 | 0 | 8149 | 0 | 0 | 0 | 0 | 0 | 8149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS001 | SEQ - Sewer When & Where Contract in SE Queens | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 412 413 | SE-0200Q SE-0002Q WM-0001 SE-1000 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | SEWER WHEN &NWHERE CONTRACT IN SE QUEENS TO INCLUDE, STORM , SANITARYAND COMBIND SEWERS, WMS AND BORING, SURVEY & GEOTECHNICAL WORK AS REQUIRED | 2019 | 27500 | 36875.9 | 295 | 0 | 0 | 0 | 0 | 0 | 37170.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS002 | SEQ - Sewer When & Where Contract in SE Queens | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 400 | SE-0200Q SE-0002Q WM-0001 HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | STORM, SANITARY,COMBINED SEWERS, WATER MAIN WORK, BORNING, SURGEY, GEOTECHNICAL WORK, SE QUEENS | 2019 | 25570 | 9158.41 | 3840 | 0 | 0 | 0 | 0 | 0 | 12998.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS003 | SEQ - Sewer When & Where Contract in SE Queens (HWQ1195) | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 412 413 | SE-0200Q SE-0002Q WP-0169 WM-0001 |  |  | STORM, SANITARY,COMBINED SEWERS, WATER MAIN WORK, BORNING, SURGEY, GEOTECHNICAL WORK, SE QUEENS | 2019 | 28900 | 500 | 0 | 28900 | 0 | 0 | 0 | 0 | 29400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS005 | SEQ - Sewer When & Where Contract in SE Queens | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 412 413 | SE-0200Q |  |  | STORM SEWERS ANSD ADDTIONAL WORK AS NEEDED, SE QUEENS. | 2019 | 25000 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS006 | SEQ - Neighborhood Storm Sewer Extensions | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 412 413 | WP-0169 |  |  | STORM, SANITARY,COMBINED SEWERS, WATER MAIN WORK SE QUEENS | 2019 | 24932 | 0 | 0 | 0 | 3250 | 0 | 0 | 0 | 3250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQPGRD1 | Southeast Queens Priority Grids -- Group 1 (DOTSEQ01) | PRIMARY STREET RECONSTRUCTION | 400 | HW-0001Q | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | SOUTHEAST QUEENS PRIORITY GRIDS 01-10 | 2019 | 18154 | 1271.3 | -363 | 0 | 18387 | 1291 | 0 | 0 | 20586.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQPGRD2 | Southeast Queens Priority Grids -- Group 2 (DOTSEQ02) | PRIMARY STREET RECONSTRUCTION | 400 | HW-0001Q | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | SOUTHEAST QUEENS PRIORITY GRIDS 11-20 | 2019 | 12837 | 1241.65 | -382 | 0 | 28316 | 1972 | 0 | 0 | 31147.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | TF18-2012 | QUEENSBORO HALL MUNICIPAL PARKING GARAGE, QUEENS | Parking Meters, Lots, and Garages | 400 409 | TF-0018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | QUEENSBORO HALL MUNICIPAL PARKING GARAGE | 2019 | 2710 | 15933.59 | 540 | 500 | 0 | 0 | 0 | 0 | 16973.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | TLCWOOD | TLC - NEW OFFICE FACILITY - 24-55 BQE WEST | RENOVATION OF OTHER CITY-OWNED FACILITIES | 401 | WP-0169 PW-0077 PU-0025 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NEW FACILITY | 2019 | 36000 | 8629.32 | 604 | 62470 | 3456 | 0 | 0 | 0 | 75159.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDEP601 | DEP - LED LIGHTING AT CATSKILL DELAWARE UV FACILITY | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 404 | PU-0025 |  |  | UNIT | 2019 | 960 | 0 | 0 | 873 | 0 | 0 | 0 | 0 | 873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOH901 | DOHMH - Boiler Controls Upgrade at 3 DOHMH Health Centers | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 401 | PU-0025 |  |  | BOILER CONTROLS UPGRADE AT 3 DOHMH HEALTH CENTERS | 2019 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEHHC605 | HHC - ELMHURST HOSPITAL - INSTANTANEOUS HEATERS | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 404 | PU-0025 HO-0214 |  |  | HHC - ELMHURST HOSPITAL | 2019 | 1482 | 0 | 694 | 0 | 688 | 0 | 0 | 0 | 1382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEPOL901 | NYPD - Chiller Replacement at 10 NYPD Precincts | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 401 | PU-0025 |  |  | NYPD - CHILLER REPLACEMENT AT 10 NYPD PRECINCTS | 2019 | 0 | 0 | 0 | 2713 | 0 | 0 | 0 | 0 | 2713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO296EV | 125-01 QUEENS BLVD.- ELEVATORS | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 409 | CO-0296 |  |  | 125-01 QUEENS BLVD.- ELEVATORS | 2019 | 0 | 0 | 0 | 0 | 0 | 1358 | 0 | 24120 | 25478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO296FA | 125-01 QUEENS BLVD.- FIRE ALARMS | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 409 | CO-0296 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | 125-01 QUEENS BLVD. - FIRE ALARMS | 2019 | 2989 | 0 | 0 | 0 | 0 | 350 | 0 | 2600 | 2950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO298CHIL | 151-20 JAMAICA AVE.- CHILLER REPLACEMENT | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 412 | CO-0298 |  |  | SQ FT | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 1534 | 0 | 1534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO299CHIL | 89-17 SUTPHIN BLVD.- CHILLER REPLACEMENT | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 412 | CO-0299 |  |  | SQ FT | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 2435 | 0 | 2435 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO299FIRE | 89-17 SUTPHIN BLVD - FIRE ALARM DESIGN & REPLACEMENT | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 401 | CO-0299 |  |  | 89-17 SUTPHIN BLVD - FIRE ALARM DESIGN & REPLACEMENT | 2019 | 6944 | 0 | 528 | 0 | 0 | 0 | 0 | 6336 | 6864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO300415A | DASNY - 88-11 SUTPHIN BLVD.- RENOVATION | CONSTRUCTION OF NEW COURT FACILITIES | 412 | CO-0300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 88-11 SUTPHIN BLVD. QUEENS, NY 11435 | INTERIOR RENOVATIONS; ELECTRICAL & HVAC DISTRIBUTION; INITIAL OUTFITTING OF NEWLY RENOVATED SPACE | 2019 | 55978 | 9364.15 | 687 | 0 | 0 | 0 | 0 | 0 | 10051.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO300FIRE | 88-11 SUTPHIN BLVD. FIRE ALARM SYSTEM UPGRADE | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 412 | CO-0300 |  |  | 88-11 SUTPHIN BLVD.FIRE ALARM SYSTEM UPGRADE | 2019 | 4030 | 0 | 0 | 0 | 0 | 1116 | 0 | 14928 | 16044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO300RF | 88-11 SUTPHIN BOULEVARD - ROOF | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 412 | CO-0300 |  |  | 88-11 SUTPHIN BOULEVARD - ROOF | 2019 | 0 | 0 | 0 | 0 | 0 | 31 | 310 | 0 | 341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | E12-E027 | DSNY: Betts Avenue Garage, Boiler and Generator Installation | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 401 | PU-0025 |  |  | DSNY BETTS AVENUE GARAGE 58-73 53RD AVE QUEENS COMPREHENSIVE | 2019 | 1200 | 393.2 | 0 | 196 | 0 | 0 | 0 | 0 | 589.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | E19-0005 | DOHMH - Jamaica Health Center | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 401 | PU-0025 |  |  | DOHMH - JAMAICA HEALTH CENTER | 2019 | 354 | 0 | 354 | 0 | 0 | 0 | 0 | 0 | 354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | E19-0006 | NYPD - 102th Precinct | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 401 | PU-0025 |  |  | NYPD - 102TH PRECINCT | 2019 | 160 | 0 | 160 | 0 | 0 | 0 | 0 | 0 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0024 | NYPD - 100th Precinct Campus: 100th Precinct | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 401 | PU-0025 |  |  | NYPD - 100TH PRECINCT CAMPUS: 100TH PRECINCT | 2019 | 167 | 0 | 0 | 167 | 0 | 0 | 0 | 0 | 167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0033 | DSNY - Betts Avenue | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 401 | PU-0025 |  |  | DSNY - BETTS AVENUE | 2019 | 500 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0038 | Central Motor Repair Shop | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 401 | PU-0025 |  |  | CENTRAL MOTOR REPAIR SHOP | 2019 | 900 | 0 | 0 | 900 | 0 | 0 | 0 | 0 | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | HL82WAREH | DOHMH - Relocation Warehouse from 540 Kingsland Ave Brooklyn | CLINIC RENOVATION AND REHABILITATION |  | HL-0082 |  |  | ADDING PROPOSED DESIGN FOR NEW OFFICES, CONFERENCE ROOMS & STORAGE LAYOUT, NEW LED LIGHTS, NEW ADA ELEVATOR, EXTERIOR BRICK WORK AND NEW STONE SILLS, NEW ROOF, MODIFY HVAC & SPRINKLER WORK. | 2019 | 1988 | 0 | 1988 | 0 | 0 | 0 | 0 | 0 | 1988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79QSTD | NYPD QUEENS SOUTH TRAFFIC DIVISION RELOCATION | POLICE FACILITIES | 400 | PO-0079 |  |  | NYPD QUEENS SOUTH TRAFFIC DIVISION RELOCATION | 2019 | 0 | 0 | 5072 | 0 | 0 | 0 | 0 | 0 | 5072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79QTP | NYPD - COLLEGE POINT TOW POUND | POLICE FACILITIES | 400 | PO-0079 |  |  | COLLEGE POINT TOW POUND | 2019 | 3670 | 0 | 4370 | 912 | 0 | 0 | 0 | 0 | 5282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DAQ3 | DA QUEENS - CYBER CRIME UNIT | RENOVATION OF LEASED SPACE | 407 | PW-0326 |  |  | SQFT | 2019 | 2676 | 0 | 2149 | 527 | 0 | 0 | 0 | 0 | 2676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DAQ4 | DA QUEENS - SUPREME COURT TRIAL BUREAU | RENOVATION OF LEASED SPACE | 409 | PW-0326 |  |  | SQFT | 2019 | 7748 | 0 | 6877 | 871 | 0 | 0 | 0 | 0 | 7748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DAQ5 | DA QUEENS - ECONOMIC CRIMES UNIT | RENOVATION OF LEASED SPACE | 409 | PW-0326 |  |  | SQ FT | 2019 | 2681 | 0 | 2190 | 491 | 0 | 0 | 0 | 0 | 2681 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DDC8 | DDC - 30-30 47 AVE EXPANSION | RENOVATION OF LEASED SPACE | 401 | PW-0326 |  | 47 AVE. NOT THOMPSON AVE | DDC - 101 TYRELLAN AVENUE SI EXPANSION | 2019 | 0 | 0 | 0 | 0 | 2491 | 0 | 0 | 0 | 2491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DOF4 | DOF - LEASE RENEWAL FOR 144-06 94TH AVENUE | RENOVATION OF LEASED SPACE | 401 | PW-0326 |  |  | DOF LEASE RENEWAL FOR 144-06 94TH AVENUE, QUEENS | 2019 | 2214 | 80.95 | 0 | 13874 | 2288 | 0 | 0 | 0 | 16242.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326EV | DOHMH - 2 GOTHAM CHARGING STATION INFRASTRUCTURE | RENOVATION OF LEASED SPACE | 401 | PW-0326 |  |  | SQ FT | 2019 | 375 | 0 | 0 | 0 | 375 | 0 | 0 | 0 | 375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326QCB6 | CBQN - QUEENS CB6 OFFICES | RENOVATION OF LEASED SPACE | 406 | PW-0326 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | SITE TBD | INTERIOR RENOVATIONS; VOICE & DATA CABLING | 2019 | 170 | 85.89 | 0 | 55 | 0 | 0 | 0 | 0 | 140.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RAQ | LAW DEPT - RAISE THE AGE - QUEENS | RENOVATION OF LEASED SPACE | 401 | PW-0326 |  |  | LAW DEPT - RAISE THE AGE - QUEENS | 2019 | 0 | 0 | 0 | 4500 | 0 | 0 | 0 | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326TLQ3 | TLC -31-00 47 AVE QUEENS | RENOVATION OF LEASED SPACE | 401 | PW-0326 |  |  | TLC -31-0047 AVE QUEENS -EXPANSION | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1141 | 1141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326ZQ12 | CBQN - QUEENS CB 12 LEASE RENEWAL AT 90-28 161 ST. | RENOVATION OF LEASED SPACE | 401 | PW-0326 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | QUEENS CB 12 LEASE RENEWAL AT 90-28 161ST STREET, QUEENS | 2019 | 102 | 0 | 168 | 66 | 0 | 0 | 0 | 0 | 234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77417SW | 120-55 QUEENS BLVD.- SITE WORK | REHABILITATION OF CITY-OWNED OFFICE SPACE | 409 | PW-0077 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | 120-55 QUEENS BLVD - SITE WORK | 2019 | 4841 | 405.18 | 0 | 0 | 0 | 4370 | 0 | 0 | 4775.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77417TU | 120-55 QUEENS BOULEVARD- CODE COMPLIANT TOILET UPGRADES | REHABILITATION OF CITY-OWNED OFFICE SPACE | 401 | PW-0077 |  |  | CODE COMPLIANT TOILET UPGRADES | 2019 | 4400 | 0 | 0 | 0 | 0 | 400 | 0 | 4000 | 4400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD78415A | 88-11 SUTPHIN BLVD.- FACADE RESTORATION | REHABILITATION OF COURT BUILDINGS | 400 412 | PW-D078 |  |  | QUEENS SUPREME COURT FACADE RESTORATION | 2019 | 125 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWQ77QBH2 | 120-55 QUEENS BLVD.- RENOVATIONS | REHABILITATION OF CITY-OWNED OFFICE SPACE | 401 | PW-Q077 |  |  | QUEENS BORO HALL--RENOVATIONS | 2019 | 0 | 0 | 0 | 186 | 0 | 0 | 0 | 0 | 186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWQ77R213 | 120-55 QUEENS BLVD- QUEENS BORO HALL RENOVATIONS | REHABILITATION OF CITY-OWNED OFFICE SPACE | 401 | PW-0077 |  |  | 120-55 QUEENS BLVD- QUEENS BORO HALL RENOVATIONS-TOPOGRAPHY | 2019 | 847 | 0 | 0 | 0 | 0 | 448 | 0 | 0 | 448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWQMASP | MASPETH TOWN HALL: CONSTRUCTION AND RENOVATION | RENOVATION OF OTHER CITY-OWNED FACILITIES | 405 | PW-Q002 |  |  | MASPETH TOWN HALL: CONSTRUCTION AND RENOVATION FY20 EXE PLAN SECTION211 ADD @1700K | 2019 | 0 | 0 | 0 | 1700 | 0 | 0 | 0 | 0 | 1700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWQMASPWI | MASPETH TOWN HALL : WATER INFILTRATION | RENOVATION OF OTHER CITY-OWNED FACILITIES | 405 | PW-Q002 PW-D005 |  |  | MASPETH TOWN HALL : WATER INFILTRATION FY19 EXE PLAN SECTION 211 ADD@ $1250K | 2019 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | RE25VERN | PLATFORM / BULKHEAD REPLACEMENT | REHABILITATION OF WATERFRONT PROPERTIES | 401 | RE-0025 |  |  | PLATFORM / BULKHEAD REPLACEMENT | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 492 | 0 | 492 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCACIP01 | SCA - P.S.215 Roof Replacement | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 401 | PU-0025 |  |  | SCA - P.S.215 ROOF REPLACEMENT | 2019 | 0 | 0 | 350 | 0 | 0 | 0 | 0 | 0 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | UNIONHALL | CONSTRUCTION AND FURNITURE AT WORKFORCE INSTITUTE UNION HALL | SOCIAL SERVICE BUILDINGS | 400 | CS-0003 |  |  | CONSTRUCTION AND FURNITURE AT WORKFORCE INSTITUTE | 2019 | 18003 | 0 | 0 | 4236 | 1802 | 3291 | 0 | 0 | 9329 | 0 | 0 | 6105 | 2862 | 4887 | 0 | 0 | 13854
20190425 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNCA17THL | TODT HILL: New Lighting | ESSENTIAL RECONSTRUCTION OF FACILITIES | 500 | LN-D008 |  |  | TODT HILL: NEW LIGHTING | 2019 | 0 | 0 | 0 | 0 | 0 | 76 | 558 | 0 | 634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNCM15STB | New Roof - South Beach | ESSENTIAL RECONSTRUCTION OF FACILITIES | 500 | LN-D008 |  |  | ROOF | 2019 | 0 | 0 | 0 | 0 | 0 | 22 | 178 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNEM17RTW | RICHMONDTOWN: Replace HVAC | ESSENTIAL RECONSTRUCTION OF FACILITIES | 500 | LN-D008 LN-0008 |  |  | RICHMONDTOWN: REPLACE HVAC | 2019 | 0 | 0 | 0 | 0 | 162 | 940 | 0 | 0 | 1102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNRA17HUG | HUGUENOT - Site Selection/New Branch Construction | ESSENTIAL RECONSTRUCTION OF FACILITIES | 503 | LN-R001 LN-D008 |  |  | NYPL - HUGUENOT BRANCH LIBRARY: NEW LOCATION FOR HUGUENOT BRANCH LIBRARY; STATEN ISLAND, NY 10312 | 2019 | 1450 | 0 | 650 | 0 | 0 | 0 | 800 | 0 | 1450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNRA17NDP | NEW DORP - HVAC System Replacement | ESSENTIAL RECONSTRUCTION OF FACILITIES | 502 | LN-R001 LN-D008 |  |  | NYPL - NEW DORP BRANCH: NEW HVAC SYSTEM FOR NEW DORP BRANCH LIBRARY;309 NEW DORP LANE, STATEN ISLAND, NY 10306 | 2019 | 700 | 0 | 534 | 0 | 0 | 0 | 100 | 0 | 634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNRA17WNB | WEST NEW BRIGHTON - ADA Compliant Elevators | ACCESS FOR THE HANDICAPPED | 501 | LN-R001 LN-D008 |  |  | NYPL - WEST BRIGHTON BRANCH: ADA ELEVATOR COMPLIANCE AT WEST BRIGHTON BRANCH LIBRARY; 976 CASTLETON AVE, STATEN ISLAND, NY 10310 | 2019 | 1000 | 0 | 406 | 0 | 0 | 0 | 500 | 0 | 906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNRA18GCK | NYPL-Great Kills-ADA Compliant Restrooms | ACCESS FOR THE HANDICAPPED | 503 | LN-R001 |  |  | NYPL-GREAT KILLS-ADA COMPLIANT RESTROOMS | 2019 | 0 | 0 | 350 | 0 | 0 | 0 | 0 | 0 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNRA18RCH | NYPL-Richmondtown Branch-New Boiler | IMPROVEMENTS TO EXISTING FACILITIES | 502 | LN-R001 |  |  | NYPL-RICHMONDTOWN BRANCH-NEW BOILER | 2019 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 042 | CITY UNIVERSITY | ST023-012 | Site Signage | MISCELLANEOUS RECONSTRUCTION | 500 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | SITE SIGNAGE | 2019 | 600 | 0 | 0 | 0 | 0 | 600 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 042 | CITY UNIVERSITY | ST030-015 | Support Center for High Performance Computer | MISCELLANEOUS RECONSTRUCTION | 500 | HN-R300 HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | SUPPORT CENTER FOR HIGH PERFORMANCE COMPUTER | 2019 | 350 | 0 | 350 | 100 | 0 | 0 | 0 | 0 | 450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 042 | CITY UNIVERSITY | ST031-015 | Soccer Field Lighting and Bleachers | MISCELLANEOUS RECONSTRUCTION | 500 | HN-D300 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | SOCCER FIELD LIGHTING AND BLEACHERS | 2019 | 1500 | 1499.91 | 1650 | 0 | 0 | 0 | 0 | 0 | 3149.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 042 | CITY UNIVERSITY | ST032-015 | Media Culture Screening Room | MISCELLANEOUS RECONSTRUCTION | 500 | HN-D300 HN-D005 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | MEDIA CULTURE SCREENING ROOM | 2019 | 510 | 95 | 532 | 0 | 0 | 0 | 0 | 0 | 627 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 042 | CITY UNIVERSITY | ST034-016 | High Performance Computer Center | MISCELLANEOUS RECONSTRUCTION | 500 | HN-D300 |  |  | HIGH PERFORMANCE CENTER | 2019 | 125 | 0 | 125 | 0 | 0 | 0 | 0 | 0 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 042 | CITY UNIVERSITY | ST035-016 | Storage Facility Improvements | MISCELLANEOUS RECONSTRUCTION | 500 | HN-D300 |  |  | MAINTENANCE FACILITY IMPROVEMENTS | 2019 | 700 | 117.13 | 583 | 0 | 0 | 0 | 0 | 0 | 700.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 042 | CITY UNIVERSITY | ST038-018 | Reconstruction of Baseball Field | MISCELLANEOUS RECONSTRUCTION |  | HN-R300 HN-D300 HN-D004 |  |  | RECONSTRUCTION OF BASEBALL FIELD | 2019 | 3150 | 0 | 1800 | 1574 | 0 | 0 | 0 | 0 | 3374 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 042 | CITY UNIVERSITY | ST039-019 | Maker Space Lab | MISCELLANEOUS RECONSTRUCTION | 500 502 | HN-R001 HN-D300 |  |  | MAKER SPACE LAB | 2019 | 1350 | 0 | 300 | 0 | 1050 | 0 | 0 | 0 | 1350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 042 | CITY UNIVERSITY | ST040-019 | NYC Street Extension to CSI Campus | MISCELLANEOUS RECONSTRUCTION | 500 | HN-D300 |  |  | NYC STREET EXTENSION TO CSI CAMPUS | 2019 | 2000 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 056 | POLICE DEPARTMENT | PO79120AC | 120TH PCT - NEW HVAC SYSTEM | POLICE FACILITIES | 500 501 | PO-0079 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NEW HVAC SYSTEM | 2019 | 400 | 1387 | 556 | 0 | 0 | 0 | 0 | 0 | 1943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 057 | FIRE DEPARTMENT | F175162WP | ROOF AND WATERPROOFING - EC162 | NEW FACILITIES AND RENOVATIONS | 503 | F-0175 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | ROOF AND WATERPROOFING - EC162 | 2019 | 1210 | 1527.37 | 0 | 128 | 0 | 0 | 0 | 0 | 1655.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 057 | FIRE DEPARTMENT | F175MC152 | Multi-Component Renovations - EC152 | NEW FACILITIES AND RENOVATIONS | 501 | F-0175 |  |  | MULTI-COMPONENT RENOVATIONS - EC152 | 2019 | 7613 | 0 | 792 | 65 | 3164 | 3436 | 0 | 0 | 7457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 057 | FIRE DEPARTMENT | F175MC159 | Multi-Component Renovations - EC159 | NEW FACILITIES AND RENOVATIONS | 502 | F-0175 |  |  | MULTI-COMPONENT RENOVATIONS - EC159 | 2019 | 5295 | 0 | 454 | 0 | 4750 | 0 | 0 | 0 | 5204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 057 | FIRE DEPARTMENT | F175REM22 | ROOF REPLACEMENT- EMS22 | NEW FACILITIES AND RENOVATIONS | 502 | F-0175 |  |  | ROOF REPLACEMENT- EMS22 | 2019 | 158 | 0 | 131 | 0 | 0 | 0 | 0 | 0 | 131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 057 | FIRE DEPARTMENT | F175SEWER | New Sewer Main and Pumping Station - Outside Plant Garage | NEW FACILITIES AND RENOVATIONS | 500 | F-0175 |  |  | NEW SEWER MAIN - OUTSIDE PLANT GARAGE | 2019 | 837 | 0 | 564 | 0 | 0 | 0 | 0 | 0 | 564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 057 | FIRE DEPARTMENT | FD175G161 | Generator - EC161 | NEW FACILITIES AND RENOVATIONS | 502 | F-D175 F-0175 |  |  | GENERATOR - EC161 | 2019 | 802 | 0 | 786 | 0 | 0 | 0 | 0 | 0 | 786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 057 | FIRE DEPARTMENT | FD175G165 | Generator - EC165 | NEW FACILITIES AND RENOVATIONS | 502 | F-D175 F-0175 |  |  | GENERATOR - EC165 | 2019 | 679 | 0 | 679 | 0 | 0 | 0 | 0 | 0 | 679 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 057 | FIRE DEPARTMENT | FD175W154 | WINDOW REPLACEMENT - EC154 | NEW FACILITIES AND RENOVATIONS | 502 | F-D175 |  |  | WINDOW REPLACEMENT - EC154 | 2019 | 406 | 370.12 | 35 | 0 | 0 | 0 | 0 | 0 | 405.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 057 | FIRE DEPARTMENT | FD175W166 | WINDOW REPLACEMENT - EC166 | NEW FACILITIES AND RENOVATIONS | 502 | F-D175 |  |  | WINDOW REPLACEMENT - EC166 | 2019 | 469 | 432.46 | 36 | 0 | 0 | 0 | 0 | 0 | 468.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 057 | FIRE DEPARTMENT | FR175G166 | Generator - EC166 | NEW FACILITIES AND RENOVATIONS |  | F-R175 F-0175 |  |  | INSTALLATION OF NEW BUILDING GENERATOR AT EC166. | 2019 | 614 | 0 | 614 | 0 | 0 | 0 | 0 | 0 | 614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 071 | DEPT OF HOMELESS SERVICES | HH115HOBU | HOSPITALITY HOUSE BUILDING UPGRADE | SHELTERS FOR HOMELESS FAMILIES | 501 | HH-0115 |  |  | HOSPITALITY HOUSE BUILDING UPGRADE | 2019 | 2250 | 0 | 0 | 0 | 0 | 180 | 0 | 2070 | 2250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV175CLOV | SIZ - Staten Island Zoo Clove Road Restoration | ESSENTIAL RECONSTRUCTION OF FACILITIES | 501 | PV-R175 PV-0175 PV-D175 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | STATEN ISLAND ZOO: RESTORATION OF CLOVE ROAD ENTRANCE AND PATHWAYS; 614 BROADWAY, STATEN ISLAND, 10310 | 2019 | 5332 | 0 | 3008 | 0 | 0 | 0 | 3270 | 0 | 6278 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 44
20190425 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV341SIPA | Historic Richmondtown - Security System and Security Gates | CAPITAL EQUIPMENT | 502 | PV-R341 PV-D341 PV-0341 PV-0467 |  |  |  | 2019 | 2154 | 0 | 479 | 0 | 0 | 0 | 1565 | 0 | 2044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV490-GOV | SHCC - SNUG HARBOR - Governor's House Exterior Renovation | ESSENTIAL RECONSTRUCTION OF FACILITIES | 501 | PV-0490 |  |  | RENOVATION | 2019 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 800 | 0 | 0 | 1000
20190425 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV490-K | SHCC - SNUG HARBOR - BLDG K Matrons House | ESSENTIAL RECONSTRUCTION OF FACILITIES | 501 | PV-R490 PV-0490 PV-D490 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BLDG K MATRONS HOUSE | 2019 | 1628 | 0 | 1028 | 0 | 0 | 0 | 600 | 0 | 1628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | ANNADALE | Annadale Road Streetscape Project - Infrastructure Reno | MISCELLANEOUS | 500 503 | ED-D384 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ANNADALE ROAD STREETSCAPE PROJECT - INFRASTRUCTURE RENOVATIONS | 2019 | 1855 | 0 | 0 | 0 | 1855 | 0 | 0 | 0 | 1855 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | C5215AB2 | St. George Ferry Terminal | RECONSTRUCTION OF FERRY TERMINAL FACILITIES | 501 | FA-0021 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | STATEN ISLAND | ST GEORGE PHASE II IMPROVEMENT | 2019 | 159617 | 132219.82 | 0 | 0 | 0 | 120 | 0 | 0 | 132339.82 | 8467.66 | 0 | 956 | 0 | 0 | 0 | 0 | 9423.66
20190425 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | CMETENT | OCME Relocation of Disaster Cache Equipment to Fresh Kills | OCME | 501 | HL-0083 |  |  | RELOCATION OF OCME DISASTER CACHE RESPONSE EQUIPMENT TO FRESH KILLS, STATEN ISLAND | 2019 | 4160 | 0 | 1660 | 2500 | 0 | 0 | 0 | 0 | 4160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | GE-343 | Replacement of Siphons b/t Brooklyn & SI | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 501 | WM-0006 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | REPLACEMENT OF THE SIPHONS WHICH RUN BETWEEN BROOKLYN AND STATEN ISLAND | 2019 | 74150 | 131177.79 | 2902 | 0 | 0 | 0 | 0 | 0 | 134079.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | HIFNSW | HIF - New Stapleton Waterfront | MISCELLANEOUS | 500 | ED-0075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | HIF - NEW STAPLETON WATERFRONT | 2019 | 60000 | 0 | 0 | 5000 | 22750 | 25000 | 0 | 7250 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | HOMEPORT2 | Stapleton Waterfront Phase II & III | MISCELLANEOUS | 500 | ED-0075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | STAPLETON WATERFRONT PHASE II & III | 2019 | 95000 | 20963.83 | 669 | 5000 | 5000 | 27331 | 15000 | 20694 | 94657.83 | 603.88 | 0 | 0 | 0 | 0 | 0 | 0 | 603.88
20190425 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | LIGHTHOUS | National Lighthouse Museum | MISCELLANEOUS | 500 501 | ED-D075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  |  | 2019 | 8456 | 6221.2 | 250 | 0 | 0 | 0 | 0 | 0 | 6471.2 | 1414.07 | 0 | 0 | 0 | 0 | 0 | 0 | 1414.07
20190425 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | LNC018CHA | CHARLESTON - Site Acquisition and New Branch Construction | EXPANSION AND CONSTRUCTION OF FACILITIES | 503 | LN-D002 LN-R001 PU-0025 LN-0008 LN-D008 |  |  | CHARLESTON - SITE ACQUISITION AND NEW BRANCH CONSTRUCTION | 2019 | 11103 | 0 | 7259 | 5420 | 0 | 0 | 0 | 0 | 12679 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | LNEA16PRT | PORT RICHMOND: MAJOR RENOVATION | ESSENTIAL RECONSTRUCTION OF FACILITIES | 500 | LN-0008 LN-R001 LN-D008 |  |  | PORT RICHMOND: MAJOR RENOVATION | 2019 | 20000 | 0 | 3251 | 9601 | 0 | 0 | 0 | 0 | 12852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | PWDSIBPCT | Van for the Staten Island Borough President's Clean Team -- | MISCELLANEOUS | 500 | PW-D308 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | VAN FOR THE STATEN ISLAND BOROUGH PRESIDENT'S CLEAN TEAM -- VAN PURCHASE | 2019 | 50 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDEDCG5 | Tompkinsville Esplanade - FEMA 428 Group 5 | MISCELLANEOUS | 500 | ED-0075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | TOMPKINSVILLE ESPLANADE - FEMA 428 GROUP 5 | 2019 | 670 | 0 | 0 | 670 | 0 | 0 | 0 | 0 | 670 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDG1HP | FEMA 428 G1 - Homeport Pier | MISCELLANEOUS | 500 | ED-0075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | FEMA 428 G1 - HOMEPORT PIER | 2019 | 13489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1044.96 | 0 | 12444 | 0 | 0 | 0 | 0 | 13488.96
20190425 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDG1HS | FEMA 428 G1 - Homeport Substation | MISCELLANEOUS | 500 | ED-0075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | FEMA 428 G1 - HOMEPORT SUBSTATION | 2019 | 3808 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 454.94 | 0 | 3353 | 0 | 0 | 0 | 0 | 3807.94
20190425 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDG4DOC | FEMA 428 G4- DOCKBUILDERS | MISCELLANEOUS | 500 | ED-0075 FA-0021 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | FEMA 428 GROUP 4 - DOCKBUILDERS | 2019 | 31250 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 250 | 0 | 2995 | 3058 | 24947 | 0 | 0 | 0 | 31000
20190425 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDHOME | Repairs to Homeport as a result of Hurricane Sandy | MISCELLANEOUS | 500 501 | ED-0404 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | REPAIRS TO THE HOMEPORT PROJECT AS A RESULT OF DAMAGE CAUSED BY HURRICANE SANDY | 2019 | 2175 | 0 | 0 | 218 | 0 | 0 | 0 | 0 | 218 | 0 | 0 | 0 | 0 | 0 | 0 | 1957 | 1957
20190425 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDMARC9 | MARINE 9 HURRICANE SANDY RENOVATIONS | NEW FACILITIES AND RENOVATIONS | 500 501 | F-0175 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | MARINE 9 HURRICANE SANDY RENOVATIONS | 2019 | 2153 | 210.94 | 0 | 0 | 5 | 0 | 0 | 0 | 215.94 | 1826.54 | 0 | 0 | 110 | 0 | 0 | 0 | 1936.54
20190425 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDSIHP2 | Stapleton Waterfront Phase II & III - Sandy Repairs | MISCELLANEOUS | 500 | ED-0075 |  |  | STAPLETON WATERFRONT PHASE II & III - FEMA RESILIENCY | 2019 | 3408 | 0 | 0 | 341 | 0 | 0 | 0 | 0 | 341 | 0 | 0 | 2463 | 604 | 0 | 0 | 0 | 3067
20190425 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDSMC | Hurricane Sandy - Saw Mill Creek Marsh Restoration | MISCELLANEOUS | 500 | ED-0075 |  |  | REHABILITATION OF SAW MILL CREEK IN STATEN ISLAND | 2019 | 13000 | 7936.82 | 2735 | 951 | 0 | 0 | 0 | 0 | 11622.82 | 1349.91 | 90 | 0 | 0 | 0 | 0 | 0 | 1439.91
20190425 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SEAVIEW | FA - Seaview Senior Housing - Met Council | MISCELLANEOUS CONSTRUCTION | 502 | PW-D005 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | SEAVIEW SENIOR HOUSING | 2019 | 53650 | 45263.41 | 0 | 0 | 3387 | 0 | 0 | 0 | 48650.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SIBULK | Sandy Staten Island Esplanade Emergency Bulkhead Work | MISCELLANEOUS | 501 | ED-0409 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | STATEN ISLAND ESPLANADE EMERGENCY BULKHEAD WORK | 2019 | 2005 | 35.07 | 0 | 459 | 0 | 0 | 0 | 0 | 494.07 | 226.95 | 543 | 526 | 3189 | 0 | 0 | 0 | 4484.95
20190425 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SIESPLAND | Staten Island North Shore Esplanade | WATERFRONT DEVELOPMENT | 501 | ED-0409 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | SI, NY 10301 | INSTALLATION OF NEW PAVERS; CONCRETE & ASPHALT PAVING; BULKHEAD RECONSTRUCTION | 2019 | 10543 | 6175.11 | 234 | 0 | 0 | 0 | 0 | 0 | 6409.11 | 560.81 | 2481 | 0 | 0 | 0 | 0 | 0 | 3041.81
20190425 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SIHOMEPT | Staten Island Homeport Emergency Bulkhead Work | MISCELLANEOUS | 501 | ED-0409 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | STATEN ISLAND HOMEPORT EMERGENCY BULKHEAD WORK | 2019 | 631 | 42.86 | 0 | 0 | 0 | 36 | 0 | 0 | 78.86 | 300.04 | 0 | 0 | 0 | 252 | 0 | 0 | 552.04
20190425 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SIOUTLET | Staten Island Empire Outlets | MISCELLANEOUS | 500 | ED-0075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | STATEN ISLAND EMPIRE OUTLETS | 2019 | 11800 | 11500 | 0 | 0 | 0 | 0 | 300 | 0 | 11800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SIPIER1A | Staten Island Pier 1 Rehabilitation | PORT DEVELOPMENT | 501 | ED-R075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | OFFSHORE PIER REHABILITATION | 2019 | 2400 | 2147.92 | 0 | 0 | 0 | 0 | 615 | 0 | 2762.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SIWHEEL | St. George Improvements | MISCELLANEOUS | 501 | ED-R075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | STATEN ISLAND WHEEL | 2019 | 1000 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | STGRGEFIT | St. George Ferry Terminal - Fit Out | WATERFRONT DEVELOPMENT | 500 501 | ED-R075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ST. GEORGE FERRY TERMINAL FIT OUT | 2019 | 400 | 332.84 | 0 | 0 | 0 | 68 | 0 | 0 | 400.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | STGSECURE | St. George Ferry Terminal - Security | RECONSTRUCTION OF FERRY TERMINAL FACILITIES | 501 | FA-0021 FA-0027 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | STG SECURITY IMPROVEMENTS | 2019 | 23350 | 13825.54 | 0 | 0 | 0 | 99 | 0 | 0 | 13924.54 | 7197.49 | 0 | 0 | 0 | 0 | 0 | 0 | 7197.49
20190425 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | TOTTENCBD | Tottenville Central Business District | COMMERCIAL DEVELOPMENT | 503 | PW-D005 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  |  | 2019 | 1358 | 1158.99 | 100 | 0 | 0 | 0 | 0 | 0 | 1258.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | TRAVLIFT | Travis Avenue Lift Project -- Elevating section of Travis Av | MISCELLANEOUS | 500 | ED-D075 |  |  | TRAVIS AVENUE LIFT PROJECT -- ELEVATING SECTION OF TRAVIS AVENUE TO PREVENT FLOODING | 2019 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | TRAVSIDEW | TRAVIS AVENUE ELEVATION - FOR SIDEWALK/WALKWAY TO NATURE PRE | MISCELLANEOUS | 500 | ED-0075 |  |  | TRAVIS AVENUE ELEVATION - FOR SIDEWALK/WALKWAY TO NATURE PRESERVE | 2019 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | YMCASOSH | YMCA South Shore - Staten Island | REHABILITATION OF NON-WATERFRONT PROPERTIES | 500 503 | RE-0019 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | YMCA FACILITY. | CONSTRUCTION AT YMCA AT SOUTH SHORE. | 2019 | 290 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM16NLSC | NEW LANE HOUSES - SECURITY CAMERAS AND DOORS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 501 | HA-R001 |  |  | NEW LANE HOUSES - SECURITY CAMERAS AND DOORS | 2019 | 700 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM16THSC | TODT HILL HOUSES SECURITY CAMERAS AND DOORS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 502 | HA-R001 |  |  | TOD HILL HOUSES SECURITY CAMERAS AND DOORS | 2019 | 1800 | 1170.51 | 1729 | 0 | 0 | 0 | 0 | 0 | 2899.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM16WBDR | WEST BRIGHTON HOUSES UPGRADING OF DOORS AND SECURITY CAMERAS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 501 | HA-D001 |  |  | UPGRADING OF DOORS AND SECURITY CAMERAS | 2019 | 3200 | 0 | 83 | 0 | 0 | 0 | 0 | 0 | 83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM17THTV | Todt Hill Cameras -- CCTV Security Cameras | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 502 | HA-D001 |  |  | INSTALLATION OF SECURITY CAMERAS AT TODT HILL | 2019 | 200 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CSLF | CASSIDY LAFAYETTE SECURITY CAMERAS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 501 | HA-D001 |  |  | INSTALL SECURITY CAMERAS | 2019 | 2760 | 0 | 2760 | 0 | 0 | 0 | 0 | 0 | 2760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM18NLAC | NEW LANE SHORES LUNCH ROOM AC | LOW TO MODERATE INCOME PUBLIC HOUSING CONSTRUCTION | 501 | HA-D001 |  |  | AIR CONDITIONING | 2019 | 600 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM18RTBC | RICHMOND TERRACE BASKETBALL COURT LIGHTING | LOW TO MODERATE INCOME PUBLIC HOUSING CONSTRUCTION | 501 | HA-D001 |  |  | UPGRADE LIGHTING AT THE BASKETBALL COURTS BEHIND 71 JERSEY STREET | 2019 | 144 | 0 | 144 | 0 | 0 | 0 | 0 | 0 | 144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM18SBBY | SOUTH BEACH AND BERRY CAMERAS, LIGHTING, PLAYGROUND UPGRADE | LOW TO MODERATE INCOME PUBLIC HOUSING CONSTRUCTION | 500 | HA-D001 |  |  | CAMERAS, LIGHTING, PLAYGROUND UPGRADE | 2019 | 1000 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM18THGR | TODT HILL GROUNDS UPDATES | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 502 | HA-D001 |  |  | UPDATE GROUNDS | 2019 | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM19BHLU | BERRY HOUSES INTERIOR LIGHTING | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 502 | HA-D001 |  |  | INTERIOR LIGHTING-LIGHTING UPGRADES AT BERRY HOUSES | 2019 | 100 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM19MHBC | MARINER HARBOR BASKETBALL COURTS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 501 | HA-D001 |  |  | RENOVATION TO THE BASKETBALL COURT INCLUDING REPAVING THE COURT, NEW BASKETBALL POST, HOOPS, BACKBOARDS AND BLEACHERS | 2019 | 393 | 0 | 393 | 0 | 0 | 0 | 0 | 0 | 393 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM19SBCU | SOUTH BEACH HOUSES CAMERA UPGRADES | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 502 | HA-D001 |  |  | FUNDING FOR SOUTH BEACH HOUSES CAMERA UPGRADES | 2019 | 100 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM19THSS | TODT HILL HOUSES SPRINKLER SYSTEM | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 501 | HA-D001 |  |  | INSTALL A BRAND-NEW LARGE CHILDRENS SPRINKLER SYSTEM | 2019 | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 819 | HEALTH AND HOSPITALS CORP | 75200403 | SEA VIEW: RENOVATE MARINER'S HARBOR HOUSES CHC | ROUTINE RECONSTRUCTION | 500 501 | HO-D003 |  | 142 BRABANT STREET, STATEN ISLAND, NY 10303 | RENOVATE AND UPDATE HHC CHILD HEALTH CLINIC AT MARINER'S HARBOR HOUSES. | 2019 | 0 | 0 | 0 | 108 | 0 | 0 | 0 | 0 | 108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 819 | HEALTH AND HOSPITALS CORP | 75200902 | SEAVIEW: RENOVATION OF ISOLATION BUILDING | ROUTINE RECONSTRUCTION | 502 | HO-D003 HO-R001 HO-0214 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 460 BRIELLE AVENUE, STATEN ISLAND, N. Y. 10314 | THEPURPOSE OF THIS PROJECT IS TO RENOVATE THE ISOLATION BUILDING AT SEAVIEW HOSPITAL REHABILITATION CENTER & HOME. | 2019 | 3950 | 4022.61 | 362 | 155 | 0 | 0 | 0 | 0 | 4539.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 819 | HEALTH AND HOSPITALS CORP | 75201502 | SEA VIEW: EMERGENCY GENERATOR REPLACEMENT | ROUTINE RECONSTRUCTION | 502 | HO-0214 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 460 BRIELLE AVENUE, STATEN ISLAND, NY 10314 | PROJECT WILL REPLACE FUEL TANK AND GENERATOR AT SEA VIEW HOSPITAL REHABILITATION CENTER AND HOME TO COMPLY WITH EPA CODE COMPLIANCE. | 2019 | 2233 | 2468.99 | 235 | 192 | 0 | 0 | 0 | 0 | 2895.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 819 | HEALTH AND HOSPITALS CORP | 75201801 | SEA VIEW: CAMPUS ROAD REPAVING - PHASE 2 | ROUTINE RECONSTRUCTION | 502 | HO-D003 |  | 460 BRIELLE AVENUE, STATEN ISLAND, NY 10314 | SEA VIEW: CAPUS ROAD REPAVING - PHASE 2. | 2019 | 175 | 0 | 172 | 3 | 0 | 0 | 0 | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | NCMCCSG | NEW CLOVE PS: EQUIPMENT REPLACEMENT | WATER QUALITY PRESERVATION | 500 | WM-0105 |  |  | REPLACE SWITCHGEARS A& MCCS AT NEW CLOVE PS | 2019 | 22000 | 0 | 0 | 0 | 1000 | 15000 | 0 | 0 | 16000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-125-L | RECONSTRUCTION OF SUBSTATION AT THE OAKWOOD BEACH WPCP | PLANT UPGRADING AND RECONSTRUCTION | 500 | WP-0112 |  | 751 MILL ROAD STATEN ISLAND, N.Y. 10306 | RECONSTRUCTION OF SUBSTATION AT THE OAKWOOD BEACH WPCP. | 2019 | 13350 | 8334.88 | 45 | 0 | 0 | 0 | 0 | 0 | 8379.88 | 7736.01 | 0 | 0 | 0 | 0 | 0 | 0 | 7736.01
20190425 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-133-L | SLUDGE THICKENING IMPROVEMENT @ OAKWOOD BEACH WPCP | PLANT UPGRADING AND RECONSTRUCTION | 500 | WP-0112 |  | 751 MILL ROAD STATEN ISLAND, NEW YORK 10306 | SLUDGE THICKENING IMPROVEMENT AT OAKEOOD BEACH WPCP | 2019 | 26201 | 4575.76 | 0 | 0 | 0 | 0 | 0 | 36000 | 40575.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-134-L | POWER DISTRIBUTION AT OAKWOOD BEACH WPCP | PLANT UPGRADING AND RECONSTRUCTION | 500 | WP-0112 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | 751 MILL ROAD STATEN ISLAND, N.Y. 10306 | POWER DISTRIBUTION AT OAKWOOD BEACH WPCP | 2019 | 3920 | 600 | 5787 | 0 | 2350 | 23500 | 0 | 0 | 32237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-135-L | HEADWORKS AT OAKWOOD BEACH WPCP | PLANT UPGRADING AND RECONSTRUCTION | 500 | WP-0112 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | 751 MILL ROAD, STATEN ISLAND NEW YORK 10306 | HEADWORKS AT OAKWOOD BEACH WPCP | 2019 | 18610 | 600 | 0 | 9995 | 0 | 33128 | 0 | 0 | 43723 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-136-L | INSTALLATION OF (2) MAIN TRANSFORMERS @ OAKWOOD BEACH WPCP | PLANT UPGRADING AND RECONSTRUCTION | 500 | WP-0112 |  | 751 MILL ROAD STATEN ISLAND, N.Y. 10306 | INSTALLATION OF (2) MAIN TRANSFORMERS AT THE OAKWOOD BEACH WPCP | 2019 | 17676 | 4069.78 | 256 | 0 | 0 | 5000 | 5000 | 0 | 14325.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-137-L | RECONSTRUCT PRIMARY TREATMENT EQUIPMENT @ OAKWOOD BEACH WWTP | PLANT UPGRADING AND RECONSTRUCTION | 500 | WP-0112 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | 751 MILL ROAD, STATEN ISLAND, N.Y. 10306 | RECONSTRUCT PRIMARY TREATMENT EQUIPMENT @ OAKWOOD BEACH WWTP | 2019 | 5990 | 0 | 0 | 590 | 0 | 0 | 2500 | 0 | 3090 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-144-L | TRC - CONS OF DISINFECTION FACILITIES AT OAKWOOD BEACH | CONSENT DECREE UPGRADING AND CONSTRUCTION | 500 | WP-0282 |  |  | CONSTRUCTION OF DISINFECTION FACILITIES AT OAKWOOD BEACH WPCP | 2019 | 11000 | 500 | 0 | 0 | 14834 | 0 | 0 | 0 | 15334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-146 | REPLACE MAIN INFLUENT GATES & ACTUATORS AT OAKWOOD BEACH | PLANT UPGRADING AND RECONSTRUCTION | 500 | WP-0112 |  |  | REPLACE MAIN INFLUENT GATES & ACTUATORS AT OAKWOOD BEACH | 2019 | 15000 | 0 | 0 | 1500 | 1500 | 15000 | 0 | 0 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-132-L | RECONSTRUCTION OF SEA WALL/SLUDGE DOCK IMPROVEMENTS | PLANT UPGRADING AND RECONSTRUCTION | 500 | WP-0112 |  |  | RECONSTRUCTION OF SEA WALL/SLUDGE DOCK IMPROVEMENTS | 2019 | 3188 | 0 | 0 | 548 | 0 | 0 | 1000 | 0 | 1548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-134-L | RECONSTRUCT FINAL SETTLING SYSTEM EQUIPMENT @ PORT RICHMOND | PLANT UPGRADING AND RECONSTRUCTION | 500 | WP-0112 |  | RICHMOND TERRACE & BODINE STREET, STATEN ISLAND, N.Y. 10310 | RECONSTRUCT FINAL SETTLING SYSTEM EQUIPMENT @ PORT RICHMOND | 2019 | 6900 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-135-L | RECONSTRUCT POWER DISTRIBUTION EQUIPMENT @ PORT RICHMOND | PLANT UPGRADING AND RECONSTRUCTION | 500 | WP-0112 |  | RICHMOND TERRACE & BODINE STREET, STATEN ISLAND N.Y. 10310 | RECONSTRUCT POWER DISTRIBUTION EQUIPMENT @ PORT RICHMOND WWTP | 2019 | 10620 | 0 | 3000 | 0 | 0 | 3000 | 0 | 33500 | 39500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-138-L | RECONSTRUCT MAIN SEWAGE PUMP CONTROLS @ PORT RICHMOND WWTP | PLANT UPGRADING AND RECONSTRUCTION | 500 | WP-0112 |  | RICHMOND TERRACE & BODINE STREET, STATEN ISLAND, N.Y. 10310 | RECONSTRUCT MAIN SEWAGE PUMP CONTROLS @ PORT RICHMOND WWTP | 2019 | 2100 | 4621.4 | 0 | 0 | 3000 | 25000 | 0 | 0 | 32621.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-140 | TRC - Dechlorination Facilities at Port Richmond WWTP | CONSENT DECREE UPGRADING AND CONSTRUCTION | 500 | WP-0282 |  |  | INSTALLATION OF SODIUM BISULFITE STORAGE TANKS, EMERGENCY GRAVITY DRIP STORAGE TANK, CHEMICAL DELIVERY OFF-LOADING STATION, METERING PUMPS,TRANSFER PUMPS, DOSING SYSTEM, AND ALL NECESSARY INSTRUMENTATIONS FORAUTOMATIC AND MANUAL CONTROLS. | 2019 | 28833 | 0 | 0 | 4591 | 3652 | 0 | 0 | 14590 | 22833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-AIRPIP | RECONS OF AIR DISTRIBUTION PIPING AT THE PORT RICHMOND WPCP | PLANT UPGRADING AND RECONSTRUCTION | 500 | WP-0112 |  |  | RECONS OF AIR DISTRIBUTION PIPING AT THE PORT RICHMOND WPCP | 2019 | 22000 | 0 | 0 | 0 | 0 | 0 | 22000 | 0 | 22000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-276 | RECONSTRUCTION AT HANNAH STREET PUMPING STATION (BEDC) | PLANT UPGRADING AND RECONSTRUCTION | 500 | WP-0269 |  | HANNAH STREET/MURRAY HULBERT AVENUE, STATEN ISLAND, N.Y. 10301 | RECONSTRUCTION AT HANNAH STREET P.S. (BEDC) | 2019 | 100225 | 13179.1 | 0 | 9994 | 0 | 0 | 0 | 52290 | 75463.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-287 | ELTINGVILLE PUMPING STATION | PLANT UPGRADING AND RECONSTRUCTION | 500 | WP-0269 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | ELTINGVILLE PUMPING STATION | ELTINGVILLE PUMPING STATION | 2019 | 9641 | 500 | 0 | 0 | 0 | 0 | 10000 | 0 | 10500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-295 | RECONSTRUCTION AT MERSEREAU PUMPING STATION | PLANT UPGRADING AND RECONSTRUCTION | 500 | WP-0269 |  | RECONSTRUCTION AT MESEREAU PUMPING STATION | RECONSTRUCTION AT MESEREAU PUMPING STATION | 2019 | 8552 | 0 | 0 | 0 | 0 | 1710 | 4000 | 0 | 5710 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-296 | RECONSTRUCTION AT MELVIN PUMPING STATION | PLANT UPGRADING AND RECONSTRUCTION | 500 | WP-0269 |  | RECONSTRUCTION AT MELVIN PUMPING STATION | RECONSTRUCTION AT MELVIN PUMPING STATION | 2019 | 5000 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-317 | RECONSTRUCT VICTORY BOULEVARD PUMPING STATION STATEN ISLAND | PLANT UPGRADING AND RECONSTRUCTION | 500 | WP-0269 |  | VICTORY VLVD., NEAR CON ED TRAVIS POWER PLANT SOUTH OF WEST SHORE EXTRESSWAY, STATEN ISLAND, NEW YORK | RECONSTRUCTION OF VICTORY BOULEVARD PUMPING STATION STATEN ISLAND, NEW YORK | 2019 | 6000 | 0 | 0 | 0 | 0 | 0 | 12500 | 0 | 12500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-322 | RECONSTRUCT MAYFLOWER AVENUE PUMPING STATION, STATEN ISLAND | PLANT UPGRADING AND RECONSTRUCTION | 500 | WP-0269 |  | MAYFLOWER AVENUE AND SRTHUR KILL ROAD, STATEN ISLAND, NEW YORK, 10309 | RECONSTRUCTION OF THE MAYFLOWER AVENUE PUMPING STATION, STATEN ISLAND, NEW YORK | 2019 | 5200 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-323 | RECONSTRUCT RICHMOND AVENUE PUMPING STATION, STATEN ISLAND | PLANT UPGRADING AND RECONSTRUCTION | 500 | WP-0269 |  | RICHMOND AVENUE AND PROL PLACE, STATEN ISLAND, NEW YORK 10305 | RECONSTRUCTION OF RICHMOND AVENUE PUMPING STATION, STATEN ISLAND, NEWYORK | 2019 | 5200 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | RED-381 | (SANDHWSI) Storm swr replacement ext. in Harold Avenue | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 503 | SE-0200R WM-0001 |  |  | (SANDHWS) STORM SEWER EXTENSIONS IN HAROLD AVE FROM BAYVIEW TERRACE TO OCEAN DRIVEWAY AND IN OCEAN DRIVEWAY FROM HAROLD AVE TO ARDEN AVE; WATER MAIN REPLACEMENTS IN HAROLD AVE FROM HYLAN BLVD TO OCEAN DRIVEWAY. | 2019 | 2880 | 0 | 0 | 2880 | 0 | 0 | 0 | 0 | 2880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | RED-384 | TRUNK AND DISTRIBUTION WATER MAIN IN FRONT ST, SI | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 501 | WM-0006 WM-0001 |  |  | TRUNK AND DISTRIBUTION WATER MAIN IN FRONT ST FROM HANNAH STREET TO VANDERBILT AVENUE, ETC. STATEN ISLAND | 2019 | 16997 | 0 | 0 | 0 | 0 | 0 | 16397 | 0 | 16397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | RED-NEW | CORE WM AREA CONTRACT, S.I. | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 500 | WM-0006 |  |  | RECONSTRUCTION OF RICHMOND WATER MAINS. | 2019 | 36865 | 0 | 0 | 0 | 0 | 8000 | 6000 | 3000 | 17000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDOB | RECONS OF THE OAKWOOD BEACH WPCP DUE TO HURRICANE SANDY | PLANT UPGRADING AND RECONSTRUCTION | 500 | WP-0112 |  |  | RECONSTRUCTION OF THE OAKWOOD BEACH WATER POLLUTION CONTROL PLANT DUETO HURRICANE SANDY | 2019 | 1277 | 0 | 0 | 0 | 0 | 0 | 0 | 6254 | 6254 | 0 | 0 | 0 | 0 | 0 | 0 | 56287 | 56287
20190425 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SER002268 | STORM & SAN SEWER IN BRIELLE AV B/T ROCKLAND AV & WALCOTT AV | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 500 502 | SE-0002R SE-0200R WM-0001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | STORM & SAN SEWER IN BRIELLE AV B/T ROCKLAND AV & WALCOTT AV | 2019 | 2006 | 0 | 0 | 0 | 0 | 2006 | 0 | 0 | 2006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SIBB2-OAK | STATEN ISLAND BLUEBELT - OAKWOOD BEACH | BLUEBELT PROGRAM | 500 503 | SE-0716 |  |  | LAND ACQUISITION FOR THE DEVELOPMENT OF BLUEBELT TYPE STORM SEWERS IN THE OAKWOOD BEACH DRAINAGE AREA. | 2019 | 6814 | 5049.14 | 4149 | 0 | 0 | 0 | 6000 | 0 | 15198.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 827 | DEPARTMENT OF SANITATION | S136-380B | Staten Island Garage 3 Boiler Replacement | GARAGES AND FACILITIES | 501 | S-0136 |  |  | REPLACE BOILERS | 2019 | 1723 | 0 | 1573 | 0 | 0 | 0 | 0 | 0 | 1573 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | C5219FM5 | STATEN ISLAND FMF FACILITY UTILITIES UPGRADES X823.48 | FERRY MAINTENANCE FACILITY CONSTRUCTION | 501 | FA-0026 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | HVAC, ELECTRICAL SYSTEM REPAIR | 2019 | 5280 | 683.62 | 1214 | 0 | 0 | 571 | 0 | 0 | 2468.62 | 0 | 5710 | 0 | 0 | 1428 | 0 | 0 | 7138
20190425 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | C5517B | DOCKBUILDING HARDWOOD TIMBER | RECONSTRUCTION OF FERRY TERMINAL FACILITIES | 500 501 | FA-0021 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | CITYWIDE | HARDWOOD TIMBER REPAIR AT FERRY FACILITIES | 2019 | 1727 | 2999.89 | 405 | 1724 | 1000 | 2812 | 1307 | 0 | 10247.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | C5587 | REPLACEMENT OF OIL BARGE #4 | RECONSTRUCTION OF FERRY BOATS | 500 501 | FA-0313 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | OIL BARGE#4 REPLACE | 2019 | 6800 | 1220.03 | 0 | 0 | 0 | 0 | 0 | 567 | 1787.03 | 1978.05 | 0 | 0 | 0 | 0 | 0 | 422 | 2400.05
20190425 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | C5588 | REPLACEMENT OF OIL BARGE #5 | RECONSTRUCTION OF FERRY BOATS | 500 501 | FA-0313 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | OIL BARGE#5 REPLACE | 2019 | 8050 | 0 | 0 | 0 | 0 | 0 | 0 | 8050 | 8050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | C5590 | DRYDOCK MOLINARI FERRY BOATS | RECONSTRUCTION OF FERRY BOATS | 500 501 | FA-0313 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | DRYDOCK F/BOATS | 2019 | 22550 | 13473.22 | 0 | 1445 | 2730 | 0 | 2650 | 0 | 20298.22 | 8904.91 | 0 | 3865 | 0 | 0 | 0 | 0 | 12769.91
20190425 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FA-AUSLNG | UPGRADE A.AUSTEN FERRYBT TO LIQUEFIED NATURAL GAS, X823.47 | RECONSTRUCTION OF FERRY BOATS | 500 | FA-0313 |  |  | UPGRADE FERRY BOAT TO LNG | 2019 | 5750 | 470.7 | 0 | 0 | 0 | 0 | 0 | 2960 | 3430.7 | 0 | 0 | 0 | 0 | 0 | 0 | 4340 | 4340
20190425 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FABLDG45R | Building 45 Rehabilitation | RECONSTRUCTION OF FERRY TERMINAL FACILITIES | 500 | FA-0021 |  |  | REHABILITATION OF BUILDING 45 | 2019 | 1985 | 670.93 | 0 | 4114 | 0 | 0 | 0 | 0 | 4784.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FAFUELFC | Fuel Facility Centrifuge | FERRY MAINTENANCE FACILITY CONSTRUCTION | 500 | FA-0026 |  |  | FUEL FACILITY CENTRIFUGE | 2019 | 125 | 0 | 125 | 0 | 0 | 0 | 0 | 0 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FAMSCCTV | Molinari Class, Newhouse and Austen Ferryboats CCTV Upgrade | RECONSTRUCTION OF FERRY TERMINAL FACILITIES | 500 | FA-0313 |  |  | MOLINARI CLASS AND SIN CCTV UPGRADE | 2019 | 2000 | 0 | 1843 | 0 | 0 | 0 | 157 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FASGTRCN | St.George Ferry Terminal Waterfront Remediation | RECONSTRUCTION OF FERRY TERMINAL FACILITIES | 500 | FA-0021 |  |  | SGT FERRY TERMINAL BULKHEAD RECONSTRUCTION | 2019 | 20458 | 0 | 85 | 0 | 10000 | 0 | 115 | 0 | 10200 | 0 | 342 | 0 | 5416 | 0 | 0 | 0 | 5758
20190425 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FASGTRHB | SGT Terminal Brick Facade Rehabilitation | RECONSTRUCTION OF FERRY TERMINAL FACILITIES | 500 | FA-0021 |  |  | SGT TERMINAL BRICK FACADE REHABILITATION | 2019 | 750 | 0 | 50 | 700 | 0 | 0 | 0 | 0 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FASTGCCTV | STG Terminal CCTV Upgrade | RECONSTRUCTION OF FERRY TERMINAL FACILITIES | 500 | FA-0021 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | STG TERMINAL CCTV UPGRADE | 2019 | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FAUREABRG | Reonstruction of a SIF Diesel Exhaust Fluid Barge | RECONSTRUCTION OF FERRY TERMINAL FACILITIES | 500 | FA-0313 |  |  | STATEN ISLAND FERRY UREA BARGE | 2019 | 1500 | 0 | 0 | 250 | 1250 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FBENVCOM | Ferryboat Environmental Compliance Upgrades | RECONSTRUCTION OF FERRY TERMINAL FACILITIES | 500 | FA-0021 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | ENVIRONMENTAL COMPLIANCE UPGRADES | 2019 | 5500 | 330.61 | 0 | 0 | 4500 | 0 | 689 | 0 | 5519.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FERRYRACK | CONSTRUCTION OF FERRY RACK | RECONSTRUCTION OF FERRY TERMINAL FACILITIES | 500 501 | FA-0021 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CONST OF NEW FERRY RACK ST.GEORGE/WHITEHALL | 2019 | 15500 | 1611.38 | 0 | 4813 | 13454 | 17354 | 21454 | 0 | 58686.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FMFVARNR | FMF Vehicle Access Ramps and Nose Upgrade | RECONSTRUCTION OF FERRY TERMINAL FACILITIES | 500 | FA-0026 |  |  | RAMPS AND NOSE RACK UPGARDE | 2019 | 4000 | 0 | 418 | 0 | 406 | 0 | 0 | 0 | 824 | 0 | 0 | 0 | 3666 | 0 | 0 | 0 | 3666
20190425 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FVESSGANR | Facility/Vessel Gangways Replacement/Upgrade | RECONSTRUCTION OF FERRY TERMINAL FACILITIES | 500 | FA-0021 |  |  | GANGWAY REPLACEMENT | 2019 | 3300 | 287.02 | 0 | 3013 | 0 | 0 | 0 | 0 | 3300.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HBR249730 | BR OVER DAM OVER NORTH END CLOVE LAKE BIN 2249730 | FAIR BRIDGES | 500 | P-0508 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | BR OVER DAM OVER NORTH END CLOVE LAKE BIN 2249730 | 2019 | 7062 | 0 | 0 | 273 | 270 | 0 | 815 | 5704 | 7062 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HBRA24923 | TRACY AVE PED BRIDGE BIN: 2249230 | FAIR BRIDGES | 500 | HB-0215 HB-1012 |  | TRACY AVE PED BRIDGE BIN: 2249230 | TRACY AVE PED BRIDGE BIN: 2249230 | 2019 | 9853 | 132.83 | 1225 | 0 | 0 | 28 | 0 | 0 | 1385.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HBRA24925 | BETHEL AVE PED BRIDGE BIN:2249250 | FAIR BRIDGES | 500 | HB-0215 HB-1012 |  | BETHEL AVE PED BRIDGE BIN:2249250 | BETHEL AVE PED BRIDGE: 2249250 | 2019 | 8129 | 132.83 | 1971 | 0 | 0 | 28 | 0 | 0 | 2131.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HBRA24939 | CEDARVIEW AVE PED BRIDGE BIN: 2249390 | FAIR BRIDGES | 500 | HB-4939 HB-1012 |  | CEDARVIEW AVE PED BRIDGE BIN:2249390 | CEDARVIEW AVE PED BRIDGE BIN:2249390 | 2019 | 9819 | 1292.36 | 0 | 2182 | 6641 | 125 | 0 | 0 | 10240.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HBRA24982 | ARTHUR KILL RD/ ARTHUR KILL STREAM BIN#2249820 | FAIR BRIDGES | 500 | HB-4982 |  | ARTHUR KILL RD/ ARTHUR KILL STREAM BIN#2249820 | ARTHUR KILL RD/ ARTHUR KILL STREAM BIN#2249820 | 2019 | 10350 | 0 | 415 | 681 | 2000 | 7350 | 0 | 0 | 10446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HBRC039 | REPLACEMENT OF CULVERT @ MIDLAND AVE/HYLAN BLVD - R-00023 | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 502 | HB-0215 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | REPLACEMENT OF CULVERT @ MIDLAND AVE/HYLAN BLVD - R-00023 | REPLACEMENT OF CULVERT @ MIDLAND AVE/HYLAN BLVD - R-00023 | 2019 | 3196 | 2959.42 | 144 | 0 | 0 | 0 | 0 | 0 | 3103.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HBRC041 | REPLACEMENT OF CULVERT @ FOREST AVE/RANDALL AVE - R-00068 | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 502 501 | HB-0215 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | REPLACEMENT OF CULVERT @ FOSTER AVE/RANDALL AVE - R-00068 | REPLACEMENT OF CULVERT @ FOSTER AVE/RANDALL AVE - R-00068 | 2019 | 724 | 2075.65 | 72 | 0 | 0 | 0 | 0 | 0 | 2147.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HBRSGFT17 | ARMAJANI STRUCTURE | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 500 | HB-0215 PV-0467 |  |  | ARMAJANI STRUCTURE | 2019 | 2701 | 673.62 | -96 | 1005 | 0 | 0 | 0 | 0 | 1582.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR19E | Citywide Milling - Staten Island | PRIMARY STREET RESURFACING | 500 | HW-0002R |  |  | CITYWIDE MILLING- STATEN ISLAND | 2019 | 7739 | 0 | 7507 | 7233 | 0 | 0 | 0 | 0 | 14740 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-07 | North Bridge Street/South Bridge Street - Construction | PRIMARY STREET RECONSTRUCTION | 500 | HW-0001R |  | NORTH BRIDGE STREET/SOUTH BRIDGE STREET - CONSTRUCTION OF A CONNECTORROAD | NORTH BRIDGE STREET/SOUTH BRIDGE STREET - CONSTRUCTION OF A CONNECTORROAD | 2019 | 1000 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-08 | Victory CPI | PRIMARY STREET RECONSTRUCTION | 500 | HW-D104 |  | VICTORY CPI | VICTORY CPI | 2019 | 200 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-09 | Pleasant Plains Park and Ride | PRIMARY STREET RECONSTRUCTION | 500 | HW-D104 |  |  | PLEASANT PLAINS PARK AND RIDE FY19 SECTION 254 RESO ADD $895,000 CM BORELLI | 2019 | 2895 | 0 | 0 | 0 | 0 | 0 | 2895 | 0 | 2895 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-10 | Sidewalks along Forest Hill Rd btw Ashworth and Ballfield | PRIMARY STREET RECONSTRUCTION | 500 | HW-D200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | NYC PARKS DEPARTMENT - SIDEWALKS ALONG FOREST HILL ROAD BETWEEN ASHWORTH AVENUE AND THE BALLFIELD | NYC PARKS DEPARTMENT - SIDEWALKS ALONG FOREST HILL ROAD BETWEEN ASHWORTH AVENUE AND THE BALLFIELD | 2019 | 2000 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR700 | St George-Richmond Terrace Intersection Improvements | PRIMARY STREET RECONSTRUCTION | 500 | HW-0001R |  | ST GEORGE-RICHMOND TERRANCE INTERSECTION IMPROVEMENTS | ST GEORGE-RICHMOND TERRANCE INTERSECTION IMPROVEMENTS | 2019 | 11300 | 0 | 0 | 0 | 0 | 0 | 11300 | 0 | 11300 | 0 | 0 | 0 | 0 | 0 | 750 | 0 | 750
20190425 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR703 | Bay Street Area Safety Improvements | PRIMARY STREET RECONSTRUCTION | 500 | HW-0001R |  |  | BAY STREET AREA SAFETY IMPROVEMENTS | 2019 | 15316 | 0 | 2188 | 0 | 0 | 13128 | 0 | 0 | 15316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR72017 | Richmond Ave Ped Safety | PRIMARY STREET RECONSTRUCTION | 500 | HW-R005 |  |  | RICHMOND AVE PEDESTRIAN SAFETY FOR THE INTERSECTION OF RICHMOND AVE AND FOREST HILL ROAD | 2019 | 250 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR920 | Huguenot Park N Ride | PRIMARY STREET RECONSTRUCTION |  | HW-0001R |  |  | HUGUENOT PARK N RIDE | 2019 | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWRLASEWF | Lipsett Avenue Street End (Waterfront) | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 500 | PU-0200 |  | LIPSETT AVENUE STREET END (WATERFRONT) | LIPSETT AVENUE STREET END (WATERFRONT) | 2019 | 900 | 0 | 900 | 0 | 0 | 0 | 0 | 0 | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | ITSKOREAN | Intelligent Transportation Systems on Korean Vet Pky X501.65 | SIGNAL INSTALLATION AND COMPUTERIZATION | 500 | TF-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | PIN X501.65 IMPLEMENTING AN ITS SYSTEM (SMART ZONES) ALONG THE KOREANWAR VETERANS PKWY/RICHMOND AVE | 2019 | 2069 | 0 | 414 | 0 | 0 | 0 | 0 | 0 | 414 | 0 | 1655 | 0 | 0 | 0 | 0 | 0 | 1655
20190425 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | SANDRF09 | FMF Emergency Generator Installation | FERRY MAINTENANCE FACILITY CONSTRUCTION | 500 | FA-0026 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | INSTALLATION OF EMERGENCY GENERATOR AT FMF | 2019 | 1131 | 132.01 | 139 | 50 | 0 | 0 | 0 | 0 | 321.01 | 128.04 | 1410 | 225 | 0 | 0 | 0 | 0 | 1763.04
20190425 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | SANDSIFMF | SIF FACILITIES RESTORATION & REPLACEMENT - HURRICANE SANDY | RECONSTRUCTION OF FERRY TERMINAL FACILITIES | 500 | FA-0021 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | SIF FACILITIES RESTORATION & REPLACEMENT - HURRICANE SANDY | SIF FACILITIES RESTORATION & REPLACEMENT - HURRICANE SANDY | 2019 | 1541 | 277.63 | -104 | 0 | 0 | 0 | 0 | 275 | 448.63 | 1894.26 | -941 | 0 | 0 | 0 | 0 | 2482 | 3435.26
20190425 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | STGTELPAN | St. George Terminal Electrical Panel Upgrade | RECONSTRUCTION OF FERRY TERMINAL FACILITIES | 500 | FA-0021 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | STG TERMINAL ELEC PANEL UPGRADE | 2019 | 1300 | 10 | 606 | 0 | 0 | 0 | 0 | 694 | 1310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | STGTROOF | Reconstruction of St.George Terminal Roof | RECONSTRUCTION OF FERRY TERMINAL FACILITIES | 500 | FA-0021 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | RECON OF ST GEORGE TERMINAL ROOF | 2019 | 4400 | 172.88 | 323 | 6458 | 0 | 0 | 0 | 0 | 6953.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | STGWIRERP | ST. GEORGE FERRY SLIPS WIRE ROPES, X823.66 | RECONSTRUCTION OF FERRY TERMINAL FACILITIES | 500 501 | FA-0021 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | ST. GEORGE FERRY SLIPS WIRE ROPES | ST. GEORGE FERRY SLIPS WIRE ROPES | 2019 | 2750 | 584 | 0 | 1294 | 0 | 0 | 0 | 0 | 1878 | 0 | 0 | 5176 | 0 | 0 | 0 | 0 | 5176
20190425 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | TFD503-07 | GREAT KILLS MUNICIPAL PARKING LOT LIGHTING | INSTALLATION OF LAMPPOSTS AND LUMINAIRES | 500 502 503 | TF-D503 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | TRAFFIC CONTROL ISLAND | TRAFFIC CONTROL ISLAND | 2019 | 60 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | TFR0103 | Smart Lights-various locations Staten Island | SIGNAL INSTALLATION AND COMPUTERIZATION | 500 | TF-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | SMART LIGHTS-VARIOUS LOCATION STATEN ISLAND | TO PURCHASE AND TO INSTALL SMART LIGHTS AT VARIOUS INTERSECTIONS ON STATEN ISLAND | 2019 | 850 | 888.45 | 0 | 0 | 0 | 372 | 0 | 0 | 1260.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | HWPLZ001R | Van Name/Van Pelt Plaza | PRIMARY STREET RECONSTRUCTION | 500 501 | P-0245R HW-1684 |  | VAN NAME/VAN PELT | VAN NAME/VAN PELT | 2019 | 2000 | 4637.86 | 0 | 325 | 0 | 0 | 0 | 0 | 4962.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-500RINK | Recon condenser at WW2 Memorial Rink, SI R005-119M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 500 | P-1018 |  | MEMORIAL RINK IN STATEN ISLAND | RECONSTRUCTION OF THE RINK CONDENSERS AT THE WW2 MEMORIAL RINK | 2019 | 0 | 0 | 0 | 550 | 0 | 0 | 0 | 0 | 550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-500TLOT | Five handicap-accessible tot lots on SI- BW RG-609M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 500 | P-R245 |  |  | CNSTR FIVE HANDICAP-ACCESSIBLE TOT LOTS ON SI-BOROUGHWIDE | 2019 | 2500 | 1761.1 | 271 | 0 | 0 | 0 | 0 | 0 | 2032.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501ALAS | Alice Austen House-Landscape & Site Impr. R117- | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 | P-D020 |  | ALICE AUSTEN HOUSE-LANDSCAPE & SITE IMPR. | ALICE AUSTEN HOUSE-LANDSCAPE & SITE IMPR. | 2019 | 750 | 136 | 0 | 285 | 914 | 0 | 0 | 0 | 1335 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501ALIC | Alice Austen House-Exterior Lighting & Security System | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 500 501 | P-1018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | SI | ALICE AUSTIN LANDSCAPE RESTORATION R117- | 2019 | 175 | 374.47 | 0 | 0 | 0 | 94 | 0 | 0 | 468.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501CLEX | Clove Lakes Pk-Adult Exercise Equipment | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 | P-D020 |  | CLOVE LAKES PK-ADULT EXERCISE EQUIPMENT | CLOVE LAKES PK-ADULT EXERCISE EQUIPMENT | 2019 | 700 | 91 | 0 | 459 | 41 | 0 | 0 | 0 | 591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501CLRT | Clove Lakes Pk-5K cross country trail R005-115M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 | P-1018 | PROJECT DELAYED PENDING APPROVAL OF NECESSARY PERMITS | CLOVE LAKES PK | CLOVE LAKES PK-5K CROSS COUNTRY TRAIL | 2019 | 2100 | 2287.96 | 141 | 0 | 0 | 0 | 0 | 0 | 2428.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501FABB | Faber & Lyons Pools -Boiler & Heater Replacement RG-714M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 | P-1250 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | FABER PARK, STATEN ISLAND | BOILER REPLACEMENT AND HOT WATER HEATER AND ACCESSORIES | 2019 | 1780 | 2669.35 | 10 | 0 | 0 | 148 | 0 | 0 | 2827.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501FABL | Faber Park-Install of active recreation, lighting-R008-117M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 | P-1018 P-D020 |  | FABER PARK, STATEN ISLAND | FABER PARK -ISTALLATION OF ACTIVE RECREATION, LIGHTING | 2019 | 5405 | 629.22 | 6206 | 0 | 0 | 0 | 0 | 0 | 6835.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501GREE | S I GREENBELT/AMUNDSEN TRAIL BIKE PATHS / RG-898 | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 502 503 | P-0245R | PROJECT DELAYED PENDING APPROVAL OF NECESSARY PERMITS | STATEN ISLAND EXPRESSWAY TO PAGE AVE. | CONSTRUCT A BICYCLE PATH FROM G.N.R.A. TO GREENBELT TO INCLUDE NEW PACURBS, TIMBER BARRIER RAILS, WOODEN BOLLARDS, GALVANIZED STEEL GUARDRAAGE, PLANTING, PATHWAY SIGNAGE, TRAIL HEADS, FLAGPOLE, AND ANIMAL ART. | 2019 | 1825 | 328.76 | 0 | 0 | 0 | 0 | 0 | 0 | 328.76 | 218.94 | 133 | 0 | 0 | 0 | 0 | 0 | 351.94
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501MAR2 | MARINERS MARSH | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 501 | P-D020 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | MARINERS MARSH | MARINERS MARSH-PHASE ? | 2019 | 200 | 58.93 | 0 | 0 | 0 | 0 | 0 | 200 | 258.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501NAPL | Naple Plgr-Netting | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 500 | P-D020 |  | NAPLE PLGR-NETTING SI | NAPLE PLGR-NETTING | 2019 | 49 | 7 | 0 | 0 | 0 | 3115 | 0 | 0 | 3122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501WEPE | WesterleighPk-Play Equipment | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 | P-D020 |  | WESTERLEIGHPK-SI | WESTERLEIGHPK-PLAY EQUIPMENT | 2019 | 70 | 10 | 0 | 0 | 0 | 0 | 0 | 50 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501WPFE | Walker Pk-Fence Repair/ReplacementRP | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 500 | P-D020 |  | WALKER PK-FENCE REPAIR/REPLACEMENT | WALKER PK-FENCE REPAIR/REPLACEMENT | 2019 | 232 | 30 | 0 | 0 | 0 | 0 | 0 | 166 | 196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-502CTPK | MIDLAND BEACH PROMENADE ENTRY PLAZA & PARKING LT R046-107MA2 | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 502 | HW-R005 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | TO CONSTRUCT A CHILDRENS THEME PK NEAR THE SOUTH BEACH BOARDWALK | 2019 | 5643 | 6963.14 | 0 | 0 | 121 | 0 | 0 | 0 | 7084.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-502GRBP | Greenbelt Rec.Cntr-Constr. of additional parking R129- | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 | P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | GREENBELT REC.CNTR-CONSTR. OF ADDITIONAL PARKING | GREENBELT REC.CNTR-CONSTR. OF ADDITIONAL PARKING | 2019 | 1000 | 1410.92 | 100 | 0 | 0 | 8 | 0 | 0 | 1518.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-502NDPK | New Dorp Center Kitchen Recon. (R016-214MA) | BEACHES AND BOARDWALKS | 500 | P-D020 P-R245 P-1018 |  | SI | NEW DORP BEACH (126 CEDAR GROVE AVE) KITCHEN RC | 2019 | 989 | 126.36 | 280 | 0 | 0 | 583 | 0 | 0 | 989.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503BFDS | Ballfields in Dugan & Schmul parks | LAND ACQUISITION AND TREE PLANTING | 500 | P-D020 |  | DUGAN AND SCHMUL PARKS | R/C OF BALLFIELDS IN DUGAN & SCHMUL PARKS | 2019 | 1920 | 1540.61 | 0 | 0 | 0 | 77 | 0 | 0 | 1617.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503CHP1 | Conference House Park Pavilion R006-213M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 503 | P-0245R | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | CONFERENCE HOUSE PK PAVILION | CONFERENCE HOUSE PK PAVILION | 2019 | 2750 | 5867.47 | 14 | 0 | 0 | 1011 | 0 | 0 | 6892.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503CHPV | Conference House Park Pavilion | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 503 | P-D020 |  |  | CONFERENCE HOUSE PARK PAVILION | 2019 | 765 | 130.74 | 0 | 0 | 0 | 0 | 104 | 0 | 234.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503CRBP | CONSTR OF CRESCENT BEACH PARK | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 500 503 | P-D020 P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | CRESCENT BEACH PARK, BOROUGH OF S.I. | CONSTRUCTION OF NEW PARK | 2019 | 1200 | 2574.22 | 0 | 0 | 0 | 196 | 0 | 0 | 2770.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503DUPL | DUGAN PLAYGROUND R/C R026- | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 | P-0245R P-D020 |  | DUGAN PLAYGROUND R/C R026- | DUGAN PLAYGROUND R/C R026- | 2019 | 3732 | 0 | 0 | 0 | 0 | 3732 | 0 | 0 | 3732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503GCPL | Greencroft Plgr- R/C of Comfort Station R089-115M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 503 | P-D020 P-R245 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | GREENCROFT PLAYGROUND , BROOKLYN | RECONSTRUCTION OF THE COMFORT STATION AT GREENCROFT PLAYGROUND | 2019 | 3102 | 406.24 | 698 | 2295 | 0 | 0 | 0 | 0 | 3399.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503HUG | HUGEUNOT PONDS PARK EXPANSION | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 500 503 | P-D020 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BILLIOU & COMELY STS B/W HUGENOT & KINGDOM AVES | HUGEUNOT PONDS PARK EXPANSION | 2019 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 153 | 153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503SNCS | Seaside Nature Pk CS construction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 503 | P-D020 P-0505 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | SEASIDE NATURE PARK, SI | THE CONSTRUCTION OF A NEW COMFORT STATION AT SEASIDE NATURE PARK | 2019 | 1207 | 91 | 0 | 0 | 0 | 6765 | 0 | 0 | 6856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503TOTT | Tottenville Shoreline Protection - Staten Island | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 | PU-0200 PU-0100 |  |  | TOTTENVILLE SHORELINE PROTECTION - MANHATTAN | 2019 | 19225 | 0 | 0 | 14400 | 4800 | 0 | 0 | 0 | 19200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5ANCH01 | Anchor Park Site - South Pk Fresh kills DESIGN | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 500 | P-1018 P-1321 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | SOUTH PK FRESH KILS | ANCHOR PARK SITE - SOUTH PK FRESH KILS | 2019 | 4492 | 3467.72 | 224 | 0 | 0 | 33322 | 0 | 0 | 37013.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5ARDTR | Arden Heights Wood -Trails & Parking | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 | P-R245 |  | ARDEN HEIGHTS WOOD -TRAILS & PARKING, SI | ARDEN HEIGHTS WOOD -TRAILS & PARKING | 2019 | 0 | 275.87 | 1197 | 0 | 0 | 0 | 0 | 0 | 1472.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5BBPAV | Multisite SI-Basketball Cours paving R | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 | P-R245 P-D020 P-0245R |  | MULTISITE SI-BASKETBALL COURS PAVING | MULTISITE SI-BASKETBALL COURS PAVING | 2019 | 555 | 101 | 1970 | 631 | 237 | 0 | 0 | 0 | 2939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5BDWK | FDR BOARDWALK RC RAILINGS, BENCHES, MISC R046-105MA | BEACHES AND BOARDWALKS | 502 | P-R245 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | FATHER CAPODANNO BLVD, BETWEEN FORT WADSWORTH AND LIBERTY AVENUE | RC OF RAILINGS, BENCHES AND MISCELLANEOUS WORK ON THE FDR BOARDWALK | 2019 | 2144 | 1856.91 | 385 | 0 | 0 | 0 | 0 | 0 | 2241.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5BEDFGR | Bedford Green-Passive landscape | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 | P-D020 |  | BEDFORD GREEN-PASSIVE LANDSCAPE | BEDFORD GREEN-PASSIVE LANDSCAPE | 2019 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5BLOOJF | Bloomingdale Park Junior Fields Installation | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 | P-R245 P-D020 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BLOOMINGDALE PARK - INSTALLATION OF JUNIOR FIELDS: REMOVE EXISTING SOFTBALL FIELD AND REPLACE WITH TWO SYNTHETIC TURF JUNIOR FIELDS. 1150 CLOVE ROAD, STATEN ISLAND 10301 | 2019 | 4625 | 842.43 | 5269 | 0 | 0 | 0 | 0 | 0 | 6111.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5BUNBCH | Buono Beach-Reconstruction of Fountain | BEACHES AND BOARDWALKS | 500 | P-1018 |  |  | BUONO BEACH-RECONSTRUCTION OF FOUNTAIN | 2019 | 131 | 0 | 0 | 0 | 131 | 0 | 0 | 0 | 131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5BWRECO | STATEN ISLAND BOARDWALK RC | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 | P-0935 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | STATEN ISLAND BOARDWALK RECONSTRUCTION | 2019 | 19500 | 0 | 0 | 0 | 0 | 13779 | 0 | 0 | 13779 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CARLPK | Carlton Park & Ida Court--Basketball Courts and Field | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 503 | P-R245 P-D020 P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | CARLTON PARK REHABILITATION: BASKETBALL COURTS AND FIELD | 2019 | 338 | 2251.25 | 84 | 0 | 0 | 226 | 0 | 0 | 2561.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CHARCS | Fairview Park - Cons. Comfort Station | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 503 | P-D020 P-R245 |  |  | FAIRVEIEW PARK COMFORT STATION RECON | 2019 | 3954 | 0 | 3565 | 0 | 0 | 0 | 0 | 0 | 3565 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CHARLS | Fairview Park Landscape Construction | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 503 | ED-0075 P-D020 P-R245 P-0245R |  |  | FAIRVIEW PARK LANDSCAPE CONSTRUCTION | 2019 | 12299 | 0 | 9115 | 0 | 0 | 2507 | 0 | 0 | 11622 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CLAWS | RENOVATION OF CLAWSON PLAYGROUND | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 503 | P-R245 P-D020 |  | ADELAIDE AVE., CLAWSON ST. | PARKS - CLAWSON PLAYGROUND RENOVATION: RENOVATION OF CLAWSON PLAYGROUND; 1150 CLOVE ROAD, STATEN ISLAND 10301 | 2019 | 1900 | 318 | 1000 | 500 | 0 | 0 | 0 | 0 | 1818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CLAYGE | Clay Pit Pond Pk-Gericke Farm Greenhouse | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 | P-D020 P-R245 |  | CLAY PIT POND PK-GERICKE FARM GREENHOUSE | CLAY PIT POND PK-GERICKE FARM GREENHOUSE | 2019 | 496 | 0 | 496 | 0 | 0 | 0 | 0 | 0 | 496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CPIB12 | CPI PH1- SI COMFORT STATIONS -BUNDLE 3 RG-216MA | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 500 | P-1018 |  |  | CPI - SI COMFORT STATIONS -BUNDLE 3 RG-216M | 2019 | 9676 | 7727.29 | 299 | 0 | 0 | 1649 | 0 | 0 | 9675.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CPIBN6 | CPI - SI Comfort Stations-Bundle 2 RG-515M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 500 | P-1018 |  | CPI-SI COMFORT STATIONS-BUNDLE 6 | CPI-SI COMFORT STATIONS-BUNDLE 2 | 2019 | 8076 | 3800.96 | 91 | 0 | 0 | 73 | 0 | 0 | 3964.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CPIGVP | CPI PH1- Grandview Playground-reconstruction | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 500 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | SI | GRANDVIEW PLGD R/C | 2019 | 1000 | 6029.39 | 0 | 0 | 0 | 100 | 0 | 0 | 6129.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CPIMDP | CPI PH1- McDonald Playground reconstruction | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 500 | P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | STATEN ISLAND CPI-MCDONALD PLAYGROUND | CPI-MCDONALD PLAYGROUND RECONSTRUCTION | 2019 | 4490 | 6033.28 | 0 | 0 | 0 | 100 | 0 | 0 | 6133.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CPIMH | CPI PH2 - Mariner's Harbor Playground-reconstruction R | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 500 | P-1018 P-D020 |  | CPI PH - MARINER'S HARBOR PLAYGROUND-RECONSTRUCTION | CPI PH2 - MARINER'S HARBOR PLAYGROUND-RECONSTRUCTION | 2019 | 2258 | 378 | 46 | 0 | 2254 | 324 | 0 | 0 | 3002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CPISTP | CPI PH2 - Stapleton Playground-reconstruction R | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 500 | P-1018 P-D020 |  | CPI - STAPLETON PLAYGROUND-RECONSTRUCTION | CPI - STAPLETON PLAYGROUND-RECONSTRUCTION | 2019 | 11076 | 1123.8 | 8809 | 1383 | 0 | 0 | 0 | 0 | 11315.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5FABBAS | Faber Park -Remove Equipment & Install Basketball Court | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 500 | P-D020 |  | FABER PARK -REMOVE EQUIPMENT & INSTALL BASKETBALL COURT | FABER PARK -REMOVE EQUIPMENT & INSTALL BASKETBALL COURT | 2019 | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 700 | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5FABRWF | Faber Park Waterfront | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 500 | PU-0200 P-0501 |  |  | FABER PARK WATERFRONT | 2019 | 1505 | 0 | 141 | 0 | 0 | 320 | 1044 | 0 | 1505 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5FRES10 | FRESH KILLS OWL HOLLOW FIELDS C/S | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 500 | P-1321 |  |  | FRESH KILLS OWL HOLLOW FIELDS C/S | 2019 | 9160 | 1085.37 | 0 | 0 | 0 | 8413 | 0 | 0 | 9498.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5FRESH | Fresh Kills - East Park | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 500 503 502 | P-1321 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | STATEN ISLAND | DEVELOP SITE | 2019 | 92680 | 916.56 | 0 | 0 | 0 | 0 | 0 | 0 | 916.56 | 0 | 0 | 0 | 0 | 590 | 0 | 0 | 590
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5FRESH9 | Fresh Kills - construction of North Park R017-115M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 500 502 503 | P-1321 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | STATEN ISLAND | NORTH PARK MULTI-USE PATH AND WETLAND RESTORATION | 2019 | 2080 | 24442.97 | 1233 | 0 | 0 | 3739 | 0 | 0 | 29414.97 | 1650 | 0 | 0 | 0 | 0 | 0 | 0 | 1650
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5FRESHS | Fresh Kills - Springville Greenway bicycle path RG-410M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 500 502 503 | P-1018 | PROJECT DELAYED PENDING APPROVAL OF NECESSARY PERMITS | SECTION OF FRESH KILLS PARK, BOROUGH OF STATEN ISLAND | SECTION OF FRESH KILLS PARK, BOROUGH OF STATEN ISLAND | 2019 | 12250 | 3229.89 | 0 | 0 | 0 | 0 | 0 | 0 | 3229.89 | 7074.91 | 0 | 0 | 796 | 0 | 0 | 0 | 7870.91
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5GBPATH | Greenbelt Perimeter Path R013-112M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 502 | P-1237 | PROJECT DELAYED PENDING APPROVAL OF NECESSARY PERMITS |  | GREENBELT PERMITER PATHWAY | 2019 | 576 | 332 | 0 | 0 | 0 | 0 | 0 | 0 | 332 | 0 | 0 | 0 | 450 | 0 | 0 | 0 | 450
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5GKBIKE | GREAT KILLS BICYCLE PATH R016-204MA | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 503 | P-1322 | PROJECT DELAYED DUE TO UNFORESEEN HAZARDOUS CONDITION | GREAT KILLS PARK, STATEN ISLAND | CONSTRUCTION OF GREAT KILLS BICYCLE PATH | 2019 | 1600 | 500.59 | 0 | 0 | 0 | 0 | 0 | 0 | 500.59 | 1052.32 | 0 | 0 | 147 | 0 | 0 | 0 | 1199.32
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5GRNBRC | Partial Recon of Greenbelt Rec Ctr in SI R129-119M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 | P-0505 P-0506 |  | GREENBELT RECREATION CENTER IN SI | PARTIAL RECONSTRUCTION OF GREENBELT RECREATION CENTER IN SI | 2019 | 1000 | 0 | 0 | 224 | 889 | 111 | 0 | 0 | 1224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5IRENE | IRENE - Wolfe's Pond Park Berm | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 | P-1018 |  | WOLFE'S POND PARK BERM | WOLFE'S POND PARK BERM | 2019 | 943 | 60 | 0 | 0 | 0 | 89 | 0 | 0 | 149 | 606.41 | 20 | 0 | 0 | 0 | 0 | 0 | 626.41
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5LILOPL | Luiz LopezPlgr- Play Equipment | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 | P-D020 |  | LUIZ LOPEZPLGR- PLAY EQUIPMENT SI | LUIZ LOPEZPLGR- PLAY EQUIPMENT | 2019 | 3360 | 480 | 0 | 0 | 2400 | 0 | 0 | 0 | 2880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5MAPLWD | Maple Woods-Passive landscape | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 | P-D020 |  | MAPLE WOODS-PASSIVE LANDSCAPE | MAPLE WOODS-PASSIVE LANDSCAPE | 2019 | 200 | 36 | 0 | 0 | 0 | 0 | 0 | 200 | 236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5MCARPK | Gen. MacArthur Park Baseball Field Renovation | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 502 | P-R245 P-1018 P-D020 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | GEN. MACARTHUR PARK BASEBALL FIELD RENOVATION | 2019 | 2620 | 371.31 | 6156 | 40 | 0 | 0 | 0 | 0 | 6567.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5PL15A2 | $1Contract-R/C of rain garden at Mahoney Plgr WO2 RG-215M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 | P-1018 |  | R/C OF RAIN GARDEN AT MAHONEY PLGR | R/C OF RAIN GARDEN AT MAHONEY PLGR | 2019 | 326 | 204.98 | 83 | 0 | 0 | 21 | 0 | 0 | 308.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5PL15A5 | $1Contract-Silver Lake Pk Path R/C WO# RG-215M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 | P-1018 |  | SILVER LAKE PK PATH R/C WO#5 | $1CONTRACT-SILVER LAKE PK PATH R/C WO#5 | 2019 | 989 | 775.42 | 0 | 0 | 0 | 96 | 0 | 0 | 871.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5PL15A6 | $1Contract-Clove Lake Pk Parking WO#6 RG-215M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 | P-1018 |  | $1CONTRACT-CLOVE LAKE PK PARKING WO#6 RG-215M | $1CONTRACT-CLOVE LAKE PK PARKING WO#6 RG-215M | 2019 | 171 | 0 | 136 | 17 | 0 | 0 | 0 | 0 | 153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5PLG13C | Reconstruction of plgrnds in SI /RG-214M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 | P-1018 | PROJECT DELAYED PENDING APPROVAL OF NECESSARY PERMITS |  | GREENCROFT PLAYGROUND | 2019 | 1851 | 656.59 | 134 | 15 | 0 | 0 | 0 | 0 | 805.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5PLG15B | R/C of parks & plgr in Staten Island RG-315M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 | P-1018 |  | WOLFE'S POND DOG RUN & BLOOMINGDALE BOCCE COURT-R/C | WOLFE'S POND DOG RUN & BLOOMINGDALE BOCCE COURT-R/C | 2019 | 3537 | 2566.51 | 0 | 0 | 0 | 683 | 0 | 0 | 3249.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5PNYC07 | PlaNYC-Ocean Breeze Beach Mainten.Area Fencing | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 500 | P-1018 |  | SEASIDE BLVD, QUINTARD STREET AND MASON AVENUE | BEACH PARKING LOT IN OCEAN BREEZE. | 2019 | 390 | 0 | 72 | 8 | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5PNYC08 | PlaNYC-Ocean Breeze Beach Parking Lot | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 500 | P-1018 |  | PLANYC-OCEAN BREEZE BEACH PARKING LOT | PLANYC-OCEAN BREEZE BEACH PARKING LOT | 2019 | 310 | 0 | 0 | 0 | 0 | 310 | 0 | 0 | 310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5PRALCS | Prall Playground-Reconstruction of Comfort Station | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 | P-0505 |  |  | PRALL PLAYGROUND-RECONSTRUCTION OF COMFORT STATION | 2019 | 1790 | 0 | 0 | 0 | 0 | 1575 | 0 | 0 | 1575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5PRESPL | Prescott Plgr-Creation of Sencory plgr R | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 | P-R245 P-D020 |  | PRESCOTT PLGR-CREATION OF SENCORY PLGR, SI | PRESCOTT PLGR-CREATION OF SENCORY PLGR | 2019 | 5456 | 728 | 3900 | 0 | 100 | 0 | 0 | 0 | 4728 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5RECSI | Recon Greenbelt Rec Ctr in Staten Island | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 | P-0506 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | RECON GREENBELT REC CTR IN STATEN ISLAND | RECON GREENBELT REC CTR IN STATEN ISLAND | 2019 | 965 | 174 | 0 | 0 | 930 | 0 | 0 | 0 | 1104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5REFO20 | Reforestation FY20 Staten Is | LAND ACQUISITION AND TREE PLANTING | 500 | P-0822 |  | REFORESTATION FY20 STATEN IS | REFORESTATION FY20 STATEN IS | 2019 | 1100 | 0 | 0 | 50 | 1100 | 0 | 0 | 0 | 1150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5SIPOOL | Staten Island Indoor Pool | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 500 | P-0632 |  |  | STATEN ISLAND INDOOR POOL | 2019 | 50000 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5TPSBF | Tappen Park & South Beach Fountain Reconstruction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 | P-1018 |  |  | TAPPEN PARK & SOUTH BEACH FOUNTAIN RECONSTRUCTION | 2019 | 166 | 0 | 166 | 0 | 0 | 0 | 0 | 0 | 166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5TRE18A | FY18 Street Trees Staten Island, CB 1-3 RG- | LAND ACQUISITION AND TREE PLANTING | 500 | P-0822 P-1018 |  | FY18 STREET TREES STATEN ISLAND, CB 1-3 | FY18 STREET TREES STATEN ISLAND, CB 1-3 | 2019 | 1687 | 219 | 1905 | 790 | 0 | 0 | 0 | 0 | 2914 | 0 | 295 | 0 | 0 | 0 | 0 | 0 | 295
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5TRE20A | FY20 Street Trees Staten Island, CB 1-3 RG-219M | LAND ACQUISITION AND TREE PLANTING | 500 | P-0822 SE-0200R HW-0001R |  | FY20 STREET TREES STATEN ISLAND, CB 1-3 RG-219M | FY20 STREET TREES STATEN ISLAND, CB 1-3 RG-219M | 2019 | 1864 | 0 | 0 | 0 | 1568 | 0 | 0 | 0 | 1568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5TREEFA | Fairview Pk -Reforestation R153-117MA | LAND ACQUISITION AND TREE PLANTING | 500 | P-0822 |  | FAIRVIEW PK -REFORESTATION | FAIRVIEW PK -REFORESTATION | 2019 | 774 | 136 | 650 | 0 | 0 | 0 | 0 | 0 | 786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5TRSD19 | Staten Island-Tree-Damaged Sidewalk R/C | LAND ACQUISITION AND TREE PLANTING | 500 | P-1331 |  | STATEN ISLAND-TREE-DAMAGED SIDEWALK R/C | STATEN ISLAND-TREE-DAMAGED SIDEWALK R/C | 2019 | 1490 | 0 | 1490 | 0 | 0 | 0 | 0 | 0 | 1490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5WHITEP | White Plgr-Hillside Slide Construction R012- | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 | P-0245R |  | LYMAN AVE | WHITE PLGR-HILLSIDE SLIDE CONSTRUCTION | 2019 | 1236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 1000
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5WPBERM | Wolfe's Pond Park Berm | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 503 | P-1018 | PROJECT DELAYED PENDING APPROVAL OF NECESSARY PERMITS |  | WOLFE'S POND PARK BERM | 2019 | 1800 | 405.33 | 0 | 0 | 0 | 689 | 0 | 0 | 1094.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | PV510-HLG | SIBG -SI BOTANICAL GARDEN Healing Garden R116-506M | ESSENTIAL RECONSTRUCTION OF FACILITIES | 501 | PV-0510 |  | 1000 RICHMOND TERRACE, STATEN ISLAND | DEVELOPMENT OF NEW GARDEN AREA OVERLOOKING THE WETLAND AND NEAR THE NY CHINESE SCHOLAR'S GARDEN. | 2019 | 1217 | 1119.55 | 0 | 0 | 0 | 53 | 0 | 0 | 1172.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | PV510-IRR | SIBG -SI BOTANICAL GARDEN Site Irrigation | ESSENTIAL RECONSTRUCTION OF FACILITIES | 501 | PV-0510 |  | 1000 RICHMOND TERRACE, STATEN ISLAND | PROVIDE THREE WELLS AND UNDERGROUND WATER DISTRIBUTION SYSTEM. | 2019 | 817 | 805.4 | 0 | 0 | 0 | 165 | 0 | 0 | 970.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-05 | SANDY - Blissenbach Marina Demo (Type 3) R160-113M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 | P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | STATEN ISLAND | SANDY- BLISSENBACH MARINA DEMO & R/C | 2019 | 0 | 282.48 | 0 | 0 | 0 | 102 | 0 | 0 | 384.48 | 131.91 | 449 | 0 | 0 | 0 | 0 | 0 | 580.91
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-13 | SANDY - SI Type 2 Plgrd R/C (RG-713M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 | P-1018 | PROJECT DELAYED PENDING APPROVAL OF NECESSARY PERMITS | SI | PLAYGROUNDS | 2019 | 2082 | 506.47 | 0 | 0 | 0 | 6 | 0 | 0 | 512.47 | 2001.09 | 0 | 54 | 0 | 0 | 0 | 0 | 2055.09
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-16 | Conference House Pk landscape (Type 3 ) R006-114M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 | P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | CONFERENCE HOUSE PARK, STATEN ISLAND | SANDY-R/C OF LANDSCAPE AT CONFERENCE HOUSE PARK | 2019 | 2245 | 400.59 | 0 | 0 | 0 | 7 | 0 | 0 | 407.59 | 254.7 | 53 | 0 | 0 | 0 | 0 | 0 | 307.7
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-17 | Tappen Park & Dolphin Fountains (Type3) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 501 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | TAPPEN PK , SI | SANDY- R/C OF FONTAIN AT TAPPEN PK TYPE3 | 2019 | 383 | 287.09 | 225 | 0 | 0 | 0 | 0 | 0 | 512.09 | 0 | 2042 | 0 | 0 | 0 | 0 | 0 | 2042
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-18 | SANDY-Midland Beach Protective Berm Emergency | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 | P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | FROM NEW DORP LANE TO OCEAN BREEZE PK, SI | EMERGENCY TEMP.PROTECTIVE BERM AT MIDLAND BCH | 2019 | 5492 | 548.09 | 0 | 0 | 55 | 0 | 0 | 0 | 603.09 | 4438.29 | 0 | 0 | 491 | 0 | 0 | 0 | 4929.29
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-24 | Sandy-Seaside Wildlife Nature Pk-reconstruction | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 500 | P-1018 |  | SANDY-SEASIDE WILDLIFE NATURE PK- | SANDY-SEASIDE WILDLIFE NATURE PK-RECONSTRUCTION | 2019 | 1135 | 802.12 | 65 | 174 | 0 | 0 | 0 | 0 | 1041.12 | 762.58 | 0 | 0 | 0 | 0 | 0 | 0 | 762.58
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-27 | Sandy-Wolfe's Pond Park-R/C of the berm | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 500 | P-1018 |  | WOLFE'S POND PARK, SI | SANDY-R/C OF THE BERM AT WOLFE'S POND PARK | 2019 | 2964 | 716.6 | 0 | 0 | 0 | 19 | 0 | 0 | 735.6 | 1841.4 | 167 | 0 | 0 | 0 | 0 | 0 | 2008.4
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-28 | Sandy-FDR bdwk & Midland Plgr-R/C of tthe pavements,etc | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 500 | P-1018 |  | SANDY-R/C OF TTHE PAVEMENTS,ETC AT FDR BDWK & MIDLAND PLGR | SANDY-R/C OF TTHE PAVEMENTS,ETC AT FDR BDWK & MIDLAND PLGR | 2019 | 651 | 37.08 | 0 | 0 | 0 | 28 | 0 | 0 | 65.08 | 333.74 | 246 | 0 | 0 | 0 | 0 | 0 | 579.74
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-30 | Sandy-New Dorp Bch Site Restor.R016-115M | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 500 | P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | SANDY-NEW DORP BCH | SANDY-NEW DORP BCH SITE RESTORATION | 2019 | 778 | 208.26 | 0 | 0 | 0 | 59 | 0 | 0 | 267.26 | 0 | 535 | 0 | 0 | 0 | 0 | 0 | 535
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-32 | Sandy-R/C of S. Bch-Playland Plgr, RG-212M WO 1 | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 500 | P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | 300 FATHER CAPODANO BLVD | R/C OF PLAYGROUND | 2019 | 373 | 191.6 | 0 | 0 | 95 | 0 | 0 | 0 | 286.6 | 347.52 | 0 | 0 | 852 | 0 | 0 | 0 | 1199.52
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-36 | SANDY - FDR BOARDWALK | BEACHES AND BOARDWALKS | 500 | P-1018 |  |  | FDR BOARDWALK /BEACH AND SOUTH BEACH FOUNTAIN DOLPIN REPAIR | 2019 | 350 | 47 | 0 | 0 | 0 | 0 | 0 | 26 | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 230 | 230
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-37 | SANDY - BUONO BEACH FOUNTAIN REPAIR | BEACHES AND BOARDWALKS | 500 | P-1018 |  |  | SANDY - BUONO BEACH FOUNTAIN REPAIR | 2019 | 381 | 0 | 0 | 0 | 41 | 0 | 0 | 0 | 41 | 0 | 0 | 340 | 0 | 0 | 0 | 0 | 340
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-43 | Lemon Creek Marina | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 | P-1018 |  |  | LEMON CREEK MARINA | 2019 | 11807 | 0 | 154 | 0 | 0 | 1413 | 122 | 0 | 1689 | 0 | 920 | 0 | 0 | 8463 | 735 | 0 | 10118
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-44 | New Dorp Pk./Corp. Kivlehan Pk. | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 | P-1018 |  |  | NEW DORP PK./CORP. KIVLEHAN PK. | 2019 | 444 | 221.74 | 0 | 1 | 0 | 12 | 0 | 0 | 234.74 | 291.69 | 29 | 0 | 0 | 0 | 0 | 0 | 320.69
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-45 | SANDY-MacArthur Park Reconstruction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 | P-1018 |  |  | TIMOSHENKO FIELD | 2019 | 3342 | 369.52 | 447 | 0 | 0 | 0 | 0 | 0 | 816.52 | 67.76 | 4024 | 0 | 0 | 0 | 0 | 0 | 4091.76
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-47 | Midland Beach Bath House | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 500 | P-1018 |  |  | MIDLAND BEACH BATH HOUSE | 2019 | 872 | 0 | 0 | 0 | 0 | 0 | 0 | 87 | 87 | 0 | 0 | 0 | 0 | 0 | 0 | 785 | 785
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-48 | Five Parks in SI | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 | P-1018 |  |  | FIVE PARKS IN SI | 2019 | 704 | 0 | 0 | 0 | 0 | 0 | 0 | 71 | 71 | 0 | 0 | 0 | 0 | 0 | 0 | 633 | 633
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-49 | Fairview Park Comfort Station Construction | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 503 | P-1018 |  |  | FAIRVIEW PARK COMFORT STATION | 2019 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 70
20190425 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-50 | Fairview Park Landscape Construction | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 503 | P-1018 |  |  | FAIRVIEW PARK LANDSCAPE CONSTRUCTION | 2019 | 0 | 0 | 667 | 0 | 0 | 101 | 0 | 0 | 768 | 0 | 6911 | 0 | 0 | 0 | 0 | 0 | 6911
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | 288CLOVE | REHABILITATION OF 288 CLOVE RD FACILITY | FACILITY PURCHASES AND RECONSTRUCTION | 500 | EP-0006 |  |  | DEMOLITION OF EXISTING UNINHABITABLE BUILDING, CONSTRUCTION OF NEW BUILDING TO HOUSE BOTH STATEN ISLAND SEWER MAINTENANCE UNIT AND REPAIR UNIT, INSTALLATION OF NEW GARAGE FOR WEATHER-SENSITIVE VEHICLES, AND REPLACEMENT OF OLD FUELING STATION. | 2019 | 30000 | 521.11 | 3660 | 3444 | 0 | 35600 | 0 | 0 | 43225.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | CO301LL | 130 STUYVESANT PL - FACADE REPAIRS LOCAL LAW 11 | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 501 | CO-0301 |  |  | 130 STUYVESANT PL - FAÓADE REPAIRS LOCAL LAW 11 | 2019 | 3601 | 391.98 | 82 | 2843 | 0 | 3983 | 0 | 0 | 7299.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | CO301PD | 130 STUYVESANT PL.- PARKING GARAGE DECK | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 501 | CO-0301 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | WATERPROOFING | 2019 | 1401 | 482 | 75 | 0 | 3465 | 0 | 0 | 0 | 4022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | CO302ST | 18 RICHMOND TERRACE - EXTERIOR STEPS RECONSTRUCTION | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 501 | CO-0302 |  |  | DCAS - LANDMARK EXTERIOR STEPS | 2019 | 2421 | 0 | 220 | 2201 | 0 | 0 | 0 | 0 | 2421 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | E14-0011 | DCAS - STATEN ISLAND BOROUGH HALL ENERGY UPGRADE | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 500 | PU-0025 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | COMP UPGRADE | 2019 | 358 | 1028.66 | 113 | 0 | 0 | 0 | 0 | 0 | 1141.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0006 | NYPL - St. George Library Center - Window Upgrades | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 501 | PU-0025 |  |  | DDC - ST. GEORGE LIBRARY CENTER - WINDOW UPGRADES | 2019 | 300 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0008 | DOT - Sign Shop - Lighting Upgrade | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 501 | PU-0025 |  |  | DOT SIGN SHOP - LIGHTING UPGRADE | 2019 | 300 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM18MHCC | Mariner's Harbor Community Center | LOW TO MODERATE INCOME PUBLIC HOUSING CONSTRUCTION | 500 | HA-0001 |  |  | FUNDING TO EXPAND THE COMMUNITY CENTER AT MARINER'S HARBOR | 2019 | 5700 | 0 | 5700 | 0 | 0 | 0 | 0 | 0 | 5700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115HHFA | Hospitality at 100 Central Ave., 10301 - Fire Alarm Upgrade | SHELTERS FOR HOMELESS FAMILIES |  | HH-0115 |  |  | HOSPITALITY AT 100 CENTRAL AVE., 10301 - FIRE ALARM UPGRADE | 2019 | 401 | 523.64 | 40 | 0 | 0 | 0 | 0 | 0 | 563.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82SIABE | REHAB OF THE STATEN ISLAND ANIMAL SHELTER | ANIMAL CARE |  | HL-R001 HL-0082 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | REHAB OF THE STATEN ISLAND ANIMAL SHELTER | 2019 | 2913 | 10607.91 | 594 | 0 | 0 | 0 | 0 | 0 | 11201.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD104-05 | RECON AND IMPROVEMENT OF AMBOY ROAD WITH HUGUENOT AVE SI | PRIMARY STREET RECONSTRUCTION | 500 503 | HW-0001R HW-0061 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | INCREASE BY 12LF THE WIDTH OF AMBOY ROAD ON A LENGTH OF 320LF; INCREASE THE RADIUS OF TURN ON HUGUENOT AVENUE FROM AMBOY ROAD | 2019 | 500 | 5309.82 | 508 | 400 | 0 | 0 | 0 | 0 | 6217.82 | 15.5 | 13 | 0 | 0 | 0 | 26 | 0 | 54.5
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP14RTA | CITYWIDE COMPLEX PED RAMPS (TRANSIT AUTHORITY) - SI | PEDESTRIAN RAMP CONSTRUCTION | 500 | HW-0200 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | CITYWIDE COMPLEX PED RAMPS (TRANSIT AUTHORITY) - SI | CITYWIDE COMPLEX PED RAMPS (TRANSIT AUTHORITY) - SI | 2019 | 4602 | 6582.18 | 220 | 0 | 0 | 18 | 0 | 0 | 6820.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR18R | Pedestrian Ramp Rehabilitation - Staten Island | PEDESTRIAN RAMP CONSTRUCTION | 500 | HW-0200 |  |  | PEDESTRIAN RAMP REHABILITATION - STATEN ISLAND | 2019 | 11025 | 2172.55 | 9330 | 0 | 0 | 0 | 0 | 0 | 11502.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19R | Pedestrian Ramp Rehabilitation - Staten Island | PEDESTRIAN RAMP CONSTRUCTION | 500 | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | PEDESTRIAN RAMP REHABILITATION - STATEN ISLAND | 2019 | 16182 | 250 | 16182 | 0 | 0 | 0 | 0 | 0 | 16432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00505 | VICTORY BLVD AND MANOR ROAD INTERSECTION IMPROVEMENT | PRIMARY STREET RECONSTRUCTION | 500 501 | HW-D104 HW-0061 HW-0001R | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | VICTORY BLVD AND MANOR ROAD | PROJECT WILL IMPROVE THE INTERSECTION OF VICTORY BLVD AND MANOR ROAD | 2019 | 3882 | 12182.65 | 2310 | 849 | 0 | 0 | 0 | 805 | 16146.65 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 15
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00508 | AMBOY ROAD IMPROVEMENTS AT ELTINGVILLE CORRIDOR | PRIMARY STREET RECONSTRUCTION | 500 503 | HW-0061 HW-R005 HW-0001R | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | AMBOY ROAD IMPROVEMENTS | AMBOY ROAD IMPROVEMENTS | 2019 | 3500 | 1408.2 | 5286 | 5342 | 4344 | 0 | 0 | 0 | 16380.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00510 | Woodrow Rd Improvements btw Gladwin Ave & Veterans Rd East | PRIMARY STREET RECONSTRUCTION | 500 503 | HW-0001R HW-R005 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | TO CONDUCT VARIOUS ROAD IMPROVEMENTS AT WOODROW ROAD BETWEEN BLOOMINGDALE ROAD AND VETERANS ROAD EAST | TO CONDUCT VARIOUS ROAD IMPROVEMENTS AT WOODROW ROAD BETWEEN BLOOMINGDALE ROAD AND VETERANS ROAD EAST | 2019 | 1500 | 1371.04 | 219 | 0 | 0 | 6213 | 0 | 0 | 7803.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00511 | Travis Avenue Widening | PRIMARY STREET RECONSTRUCTION | 500 502 | HW-R005 HW-0001R HW-D104 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | TO WIDEN TRAVIS AVE BTWN RICHMOND AVE & PARK DRIVE NORTH | TO WIDEN TRAVIS AVE BTWN RICHMOND AVE & PARK DRIVE NORTH | 2019 | 1700 | 1848.35 | 0 | 4578 | 6380 | 1000 | 0 | 0 | 13806.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00512 | Richmond Valley Road | PRIMARY STREET RECONSTRUCTION | 500 | HW-0061 HW-R005 HW-0001R HW-D104 HW-R988 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | RICHMOND VALLEY ROAD | RICHMOND VALLEY ROAD | 2019 | 3971 | 845.22 | 17 | 1644 | 154 | 4578 | 0 | 0 | 7238.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR005B | TODT HILL ROAD CURVE REHAB, | PRIMARY STREET RECONSTRUCTION | 502 | HW-R005 HW-0001R | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  |  | 2019 | 3324 | 1402.62 | 0 | 500 | 0 | 13538 | 0 | 0 | 15440.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR005B1 | TODT HILL ROAD - CIRCLE RD | PRIMARY STREET RECONSTRUCTION | 500 | WM-0001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | TODT HILL ROAD - CIRCLE RD | TODT HILL ROAD - CIRCLE RD | 2019 | 3150 | 860.09 | 0 | 0 | 0 | 1024 | 0 | 0 | 1884.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR1140A | ARTHUR KILL ROAD (PHASE I) - CLARKE AVE AND RICHMOD AVE | PRIMARY STREET RECONSTRUCTION | 503 | HW-1140 HW-0061 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RECONSTRUCTION OF EXISTING ROADWAYROADWAY RECONSTRUCTION SHALL INCLUDE NEW CURBS, SIDEWALKS AND REQUIREDREPLACEMENTAMENITIES WILL NOT BE INCLUDEDCITY FUNDEDIN CONJUNCTION WITH DEP | 2019 | 55985 | 4865.38 | 91 | 3640 | 0 | 15336 | 0 | 0 | 23932.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR1140B | ARTHUR KILL ROAD (PHASE II) - RICHMOND AVE AND HUGUENOT AVE | PRIMARY STREET RECONSTRUCTION | 503 | WM-0001 SE-0002R | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | ARTHUR KILL ROAD (PHASE II) - RICHMOND AVE AND HUGUENOT AVE | ARTHUR KILL ROAD (PHASE II) - RICHMOND AVE AND HUGUENOT AVE | 2019 | 14575 | 0 | 0 | 0 | 0 | 7598 | 0 | 0 | 7598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR1160 | RE- ALIGN ROCKLAND AVE AT MANOR RD/MEISNER AVE | PRIMARY STREET RECONSTRUCTION | 502 | HW-0001R | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  |  | 2019 | 7020 | 178.45 | 0 | 0 | 0 | 0 | 18689 | 0 | 18867.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR300-03 | ROAD WIDENING AT SOUTH AVENUE AND FOREST AVENUE | PRIMARY STREET RECONSTRUCTION | 501 | HW-R061 SE-0200R HW-D104 HW-0061 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ROAD WIDENING AT SOUTH AVENUE AND FOREST AVENUE | 2019 | 500 | 6195.87 | 823 | 0 | 1494 | 0 | 0 | 0 | 8512.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR669C | RECONSTRUCTION OF ROMA, HETT, ETC | PRIMARY STREET RECONSTRUCTION | 502 | HW-0669 HW-0061 EP-0007 SE-0200R SE-0002R WM-0001 HW-0001R | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  |  | 2019 | 11863 | 50582.85 | 31395 | 88 | 0 | 0 | 190 | 0 | 82255.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR890 | WOODROW RD | PRIMARY STREET RECONSTRUCTION | 503 | HW-0890 TF-0502 TF-0002 HW-0200 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RECONSTRUCTION OF WOODROW ROAD FR BLOOMINGDALE RD TO HUGUENOT AVENUEAND FROM BOULDER STREET TO ARTHUR KILL ROADRECONSTRUCTION OF THE EXISTING ROADWAYROADWAY RECONSTRUCTION SHALL INCLUDE NEW CURBS SIDEWALKS AND REQUIREDREPLACEMENTAMENITIES WILL NOT BE INCLUDEDALL CITY FUNDEDIN CONJUNCTION WITH SEWERS | 2019 | 19212 | 1659.59 | 0 | 0 | 0 | 0 | 18797 | 0 | 20456.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR919 | BLOOMINGDALE ROAD: AMBOY ROAD TO ARTHUR KILL ROAD | PRIMARY STREET RECONSTRUCTION | 503 | HW-0919 TF-0502 TF-0002 HW-0200 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | RECONSTRUCT AND WIDEN BLOOMINGDALE ROAD FROM AMBOY ROAD TO ARTHUR KILL ROAD | RECONSTRUCTION OF BLOOMINGDALE ROADRECONSTRUCTION OF THE EXISTING ROADWAYROADWAY RECONSTRUCTION SHALL INCLUDE NEW CURBS SIDEWALKS AND REQUIREDREPLACEMENTAMENITIES TO BE DETERMINEDALL CITY FUNDEDIN CONJUNCTION WITH SEWERS | 2019 | 10461 | 2320.98 | 0 | 0 | 0 | 35576 | 0 | 0 | 37896.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR986C | CONSTRUCTION AND RECONSTRUCTION OF FOREST HILL ROAD | PRIMARY STREET RECONSTRUCTION | 502 | WM-0001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | FOREST HILL ROAD FROM RICHMOND HILL ROAD TO WILLOWBROOK ROAD AND FROMPLATINUM AVENUE TO YUKON AVENUE, STATEN ISLANDRECONSTRUCTION OF THE EXISTING ROADWAYROADWAY RECONSTRUCTION SHALL INCLUDE NEW CURBS SIDEWALKS AND REQUIREDREPLACEMENTAMENITIES TO BE DETERMINEDALL CITY FUNDINGIN CONJUNCTION WITH SEWERS | 2019 | 10232 | 293.23 | 0 | 0 | 0 | 0 | 0 | 1104 | 1397.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWRF05R | Dubois Yard Roof | FACILITY RECONSTRUCTION | 500 | HW-0003 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | DUBOIS YARD ROOF | DUBOIS YARD ROOF | 2019 | 700 | 610.94 | 580 | 9048 | 0 | 36 | 0 | 0 | 10274.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2016R1 | Prior Notice Sidewalks - Staten Island | SIDEWALK RECONSTRUCTION | 500 | HW-0200 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | PRIOR NOTICE SIDEWALKS - STATEN ISLAND | PRIOR NOTICE SIDEWALKS - STATEN ISLAND | 2019 | 3246 | 9589.22 | 6030 | 0 | 0 | 0 | 0 | 0 | 15619.22 | 970.28 | 0 | 0 | 0 | 0 | 0 | 0 | 970.28
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2016R2 | Prior Notice Sidewalks - Staten Island | SIDEWALK RECONSTRUCTION | 500 | HW-0200 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | PRIOR NOTICE SIDEWALKS - STATEN ISLAND | PRIOR NOTICE SIDEWALKS - STATEN ISLAND | 2019 | 3246 | 9327.09 | 5661 | 0 | 0 | 0 | 0 | 0 | 14988.09 | 935.11 | 150 | 0 | 0 | 0 | 0 | 0 | 1085.11
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRR1 | Trench Restoration - Staten Island | PRIMARY STREET RECONSTRUCTION | 500 | HW-0001R |  |  | TRENCH RESTORARTION - STATEN ISLAND | 2019 | 7011 | 984.61 | 0 | 0 | 6232 | 0 | 0 | 0 | 7216.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | LNC2STAPL | STAPLETON - Renovation and Expansion | EXPANSION AND CONSTRUCTION OF FACILITIES | 501 | LN-D002 LN-D008 LN-0101R | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | STAPLETON BRANCH LIBRARY 132 CANAL STREET STATEN ISLAND, NY 10304 |  | 2019 | 9612 | 12971.2 | 0 | 108 | 0 | 0 | 0 | 0 | 13079.2 | 95.08 | 0 | 0 | 0 | 0 | 0 | 0 | 95.08
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA10TH1 | TODT HILL/WESTERLEIGH - HVAC Replacement | IMPROVEMENTS TO EXISTING FACILITIES | 501 | LN-D002 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | TODT HILL/WEST - HVAC REPLACEMENT | 2019 | 720 | 809.93 | 1 | 99 | 0 | 0 | 0 | 0 | 909.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCAL15TV | Tottenville: New Roof | ESSENTIAL RECONSTRUCTION OF FACILITIES | 500 | LN-D008 LN-D002 LN-0101M | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | TOTTEENVILLE: NEW ROOF | 2019 | 715 | 176.53 | 356 | 228 | 0 | 0 | 0 | 0 | 760.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEA13STG | ST GEORGE: Exterior and Interior renovation | ESSENTIAL RECONSTRUCTION OF FACILITIES | 500 501 | LN-0008 LN-R001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | EXTERIOR AND INTERIOR RENOVATION | 2019 | 3510 | 938.8 | 3874 | 385 | 0 | 0 | 0 | 0 | 5197.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEAL15RT | Richmond town: New Roof | ESSENTIAL RECONSTRUCTION OF FACILITIES | 500 | LN-0008 |  |  | RICHMONDTOWN: NEW ROOF | 2019 | 980 | 1320.2 | 259 | 0 | 0 | 0 | 0 | 0 | 1579.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEM14NDP | New Roof | ESSENTIAL RECONSTRUCTION OF FACILITIES | 500 | LN-0008 LN-D008 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NEW ROOF | 2019 | 783 | 1686.7 | 219 | 75 | 0 | 0 | 0 | 0 | 1980.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC001 | New Creek West Branch Bluebelt, BMPs NC-7 and NC-8. Low Flow | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 502 | SE-0005 SE-0002R WM-0001 SE-0200R | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | NEW CREEK WEST BRANCH BLUEBELT, BMPS NC-7 AND NC-8. LOW FLOW CHANNEL FOR NC-9 AND NC-17, AND 3 CULVERTS. | 2019 | 26043 | 16754.76 | 595 | 0 | 0 | 0 | 0 | 0 | 17349.76 | 18831.1 | 0 | 0 | 0 | 0 | 0 | 0 | 18831.1
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC002 | Last Chance Pond BMP NC 11/12, storm & sanitary sewer constr | BLUEBELT PROGRAM | 500 | SE-0002R SE-0005 SE-0200R |  |  | LAST CHANCE POND BMP NC 11/12, STORM & SANITARY SEWER CONSTRUCTION AND WATER MAIN REPLACEMENT IN HUSSON STREET BETWEEN STOBE AVENUE AND HUNTER AVE, ETC, BOUROUGH OF STATEN ISLAND | 2019 | 47890 | 38927.75 | 200 | 0 | 0 | 0 | 0 | 0 | 39127.75 | 8949.9 | 0 | 0 | 0 | 0 | 0 | 0 | 8949.9
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC003 | Strm & Sani Swr const & WM replac in Mason Ave, SI | BLUEBELT PROGRAM | 502 | SE-0200R SE-0002R SE-0005 WM-0001 EP-0007 HW-0200 SE-0944 TF-0502 |  |  | STORM & SANITARY SWEER CONSTRUCTION & WM REPLACEMENT IN MASON AVE B/TSLATER BLVD & ADAMS AVE, SI, BMP, NC, 16 | 2019 | 29452 | 1803.86 | 21 | 34920 | 0 | 0 | 0 | 0 | 36744.86 | 0 | 0 | 12534 | 0 | 0 | 0 | 0 | 12534
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC005 | BMP 13 and 14 Storm and Sanitary Sewer construction | BLUEBELT PROGRAM | 502 | SE-0200R EP-0007 HW-0200 SE-0002R SE-0005 TF-0002 TF-0502 WM-0001 HW-0001R |  |  | BMP 13, 14 AND 15 STORM AND SANITARY SEWER CONSTRUCTION AND WATER MAIN REPLACEMENT IN HYLAN BLVD B/W SLATER BLVD AND HAMDEN AVE, ETC. STATEN ISLAND | 2019 | 53068 | 0 | 0 | 0 | 48776 | 0 | 0 | 0 | 48776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC04A | BMP NC 6 and 15 storm & sanitary sewer installation | BLUEBELT PROGRAM | 502 | SE-0200R SE-0002R SE-0005 WM-0001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | MIBBNC04A-BMP NC 6, STORM & SANITARY SEWER INSTALLATION & WATER MAINREPLCMNT IN LINCOLN AVE BET. HYLAN BLVD. & MASON AVE, ETC. STATEN ISLAND | 2019 | 34680 | 450 | 0 | 0 | 0 | 31529 | 0 | 0 | 31979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC04B | Storm and sanitary sewer installation | BLUEBELT PROGRAM | 502 | SE-0200R SE-0002R WM-0001 |  |  | MIBBNC04B-BMP NC 6, STORM AND SANITARY SEWER INSTALLATION AND WATER MAIN REPLACEMENT IN LINCOLN AVE BETWEEN S. RAILROAD AVE AND HYLAND BLVD, ETC. BOROUGH STATEN ISLAND | 2019 | 30221 | 0 | 0 | 0 | 0 | 30221 | 0 | 0 | 30221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC05 | BMPs NC-13 & 14: STORM SEWER CONSTRUCTION & WM REPL | BLUEBELT PROGRAM | 502 | SE-0002R SE-0200R SE-0005 WM-0001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | IN HYLAN BLVD. BET STOBE AVE. & SEAVER AVE. | 2019 | 19512 | 782.64 | 0 | 0 | 987 | 14624 | 0 | 0 | 16393.64 | 0 | 0 | 0 | 0 | 8613 | 0 | 0 | 8613
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | P-5PNYC06 | PlaNYC-Ocean Breeze Athletic Fac-Building Fit-Out R149-108M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 500 502 | P-0504 ED-D075 P-R245 P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | OCEAN BREEZE PARK IN STATEN ISLAND | CONSTRUCTION OF THE ATHLETIC FACILITY FIT-OUT | 2019 | 92343 | 105552.15 | 303 | 1303 | 222 | 0 | 0 | 0 | 107380.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV175AQUA | SIZ - Staten Island Zoo - Aquarium Reconstruction | ESSENTIAL RECONSTRUCTION OF FACILITIES | 501 | PV-R175 PV-0175 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES |  | SCOPE OF WORK IS THE INSTALLATION OF NEW TANKS, WATER FILTERS AND NEWELECTRICAL SERVICE. | 2019 | 1375 | 9520.01 | 72 | 0 | 153 | 0 | 0 | 0 | 9745.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV175ROOF | SIZ - Roof Replacement | ESSENTIAL RECONSTRUCTION OF FACILITIES | 501 | PV-0175 PV-R175 PV-D175 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | THE STATEN ISLAND ZOO IS REQUESTING CAPITAL FUNDS TO REPLACE THE ROOFOF THE ZOO'S MAIN BUILDING (EXCLUDING THE REPTILE WING). THE PROJECT WOULD ALSO INCLUDE THE REPLACMENT OF THE ROOF OVER THE AFRICAN SAVANNAH AND TROPICAL FOREST WINGS. THE ROOF OF THE MAIN BUILDING IS OVER FORTY YEARS OLD AND IS SUBSTANTIALLY DETERIORATED. THE ROOF OF THE AFRICAN SAVANNAH AND TROPICAL FOREST WINGS IS ARE OVER TWENTY FIVE YEAR OLD AND ARE ALSO IN DETERIORATED CONDITION. | 2019 | 3450 | 0 | 448 | 3122 | 349 | 0 | 7 | 0 | 3926 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV302BPH1 | SIIAS - Building B at SHCC Phase1 Geo-Thermal & Ground Floor | ESSENTIAL RECONSTRUCTION OF FACILITIES | 501 | PV-R302 PV-D302 PV-0302 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES |  | SCOPE OF WORK IS THE INSTALLATION OF A GEO-THERMAL WELL FIELD WHICH WILL HEAT AND COOL BUILDING "B" AT SHCC. SCOPE OF WORK ALSO INCLUDES THE CONSTRUCTION OF NEW CLASSROOMS AND AN EXHIBITION PREPARATION ROOM/SHOP. | 2019 | 5993 | 1407.3 | 1697 | 0 | 0 | 6681 | 0 | 0 | 9785.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV341BRIT | SIHS - Britton Cottage Restoration | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | PV-0341 PV-R341 PV-D341 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES |  | BRITTON COTTAGE RESTORATION | 2019 | 750 | 333 | 0 | 0 | 0 | 1098 | 0 | 0 | 1431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV477TEMP | SICM -Staten Island Children's Museum Temp Control System | ESSENTIAL RECONSTRUCTION OF FACILITIES | 501 | PV-R477 PV-D477 PV-0477 |  |  | STATEN ISLAND CHILDREN'S MUSEUM: UPGRADE OF TEMPERATURE CONTROL SYSTEM; 1000 RICHMOND TERRACE, STATEN ISLAND 10301 | 2019 | 4406 | 0 | 592 | 0 | 0 | 3673 | 0 | 0 | 4265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490-C | SHCC - SHCC Main Hall Bldg C Roof Reconstruction | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | PV-R490 PV-0490 PV-D490 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES |  | SHCC BUILDING C ROOF RECONSTRUCTION | 2019 | 600 | 277.9 | 498 | 1530 | 0 | 350 | 0 | 0 | 2655.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490ELEC | SHCC - Snug Harbor Cult. Ctr. Site - Wide Electrical Upgrade | ESSENTIAL RECONSTRUCTION OF FACILITIES | 501 | PV-D490 PV-0490 PV-R490 PV-0467 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES | 1000 RICHMOND TERRACE, STATEN ISLAND | PHASE 1 WILL INCLIUDE THE INSTALLATION OF NEW ELECTRICAL SERVICE ROOMWHICH WILL BE CODE COMPLIANT AND SIZED FOR THE NEW SERVICE EQUIPMENT IN BUILDING "G". THIS PHASE WILL PROVIDE TEMPORARY SERVICE FROM EXISTING MANHOLE. PHASE 2 WILL INCLUDE THE INSTALLATION OF TWO SUBSTATIONS IN BUILDING "L" . | 2019 | 5175 | 920.33 | 3224 | 2502 | 0 | 2000 | 0 | 0 | 8646.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490-INF | SHCC - Site-wide Infrastructure Upgrade | ESSENTIAL RECONSTRUCTION OF FACILITIES | 501 | PV-D490 PV-0490 |  |  | SITE-WIDE HVAC UPGRADE FOR SNUG HARBOR CAMPUS, INCLUDING COMPLETE REPLACEMENT OF EQUIPMENT AT THE CENTRAL BOILER AND COOLING PLANT (BUILDING L) AND THE UPGRADE AND CONNECTION OF SYSTEMS AT THE 12 BUILDINGS SERVED BY THE CENTRAL PLANT. | 2019 | 11000 | 1104.27 | 3460 | 614 | 0 | 0 | 0 | 0 | 5178.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490-Q3 | SHCC - Snug Harbor Cult. Ctr. Music Hall, Dressing Rooms | ESSENTIAL RECONSTRUCTION OF FACILITIES | 501 | PV-0490 PV-D490 PV-R490 PV-0467 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES | 1000 RICHMOND TERRACE, STATEN ISLAND NY 10301 | PROJECT SCOPE OF WORK IS TO SECURE FOR SHCC A FDNY CODE COMPLIANT FIRE ALARM FOR THE MUSIC HALL BUILDING "T" | 2019 | 3634 | 2958.15 | 14479 | 1424 | 0 | 0 | 0 | 0 | 18861.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PVC341-M | SIHS - SIHS TYSEN COURT RECONSTRUCTION | ESSENTIAL RECONSTRUCTION OF FACILITIES | 502 | PV-D341 PV-0341 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES | NA |  | 2019 | 2825 | 11663.35 | 172 | 0 | 401 | 0 | 0 | 0 | 12236.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-74 | FUEL TANK REPLACEMENT | LEGAL MANDATES AND CORRECTION OF UNSAFE CONDITIONS |  | PW-0348 |  |  | FUEL TANKS | 2019 | 12500 | 15000 | 3500 | 11993 | 0 | 0 | 0 | 0 | 30493 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77SIFJC | 130 Stuyvesant Pl. - Staten Island Family Justice Center | RENOVATION OF OTHER CITY-OWNED FACILITIES | 500 501 | PW-0077 PW-D077 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | SI FJC | 2019 | 3500 | 8716.27 | -35 | 3 | 136 | 0 | 0 | 0 | 8820.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PWD5SOUTH | SOUTH SHORE LITTLE LEAGUE | MISCELLANEOUS CONSTRUCTION | 503 | PW-D077 P-D020 PW-0077 PW-R077 PW-D005 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | 500K FOR REHAB EXISTING FIELD AND INSTALL STADIUM SEATING, LIGHTS ANDSCOREBOARD. $150K FOR CONSRUCTION OF PRACTICE FACILITY. | 2019 | 1150 | 7925.62 | 1450 | 0 | 0 | 0 | 0 | 0 | 9375.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-366 | WM WORK IN ARTHUR KILL RD BTW RICHMOND & ABINGTON AVES | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 503 | WM-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | WATER MAIN WORK IN ARTHUR KILL RD BETWEEN RICHMOND AVE & ABINGDON AVE | 2019 | 589 | 187.36 | 0 | 0 | 0 | 9652 | 0 | 0 | 9839.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-372 | WM, PART OF RECON TRAVIS AVE FORM PARK DR N TO DRAPER PL | AUGMENTATION OF WATER SUPPLY SYSTEMS | 501 | WM-0001 SE-0002R |  |  | WM, PART OF RECON TRAVIS AVE FORM PARK DR N TO DRAPER PL | 2019 | 901 | 0 | 0 | 3158 | 0 | 0 | 0 | 0 | 3158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-373 | Replcmnt of WM & sanitary sewer spot repairs, Bradley Ave. | AUGMENTATION OF WATER SUPPLY SYSTEMS | 502 | WM-0001 SE-0002R | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | REPLCMNT OF WM & SANITARY SEWER SPOT REPAIRS, BRADLEY AVE. , BETWEEN WILLOWBROOK ROAD & SOUTH GANNON AVENUE ETC IN THE BOROUGH OF STATEN ISLAND. | 2019 | 2288 | 0 | 0 | 0 | 0 | 2275 | 0 | 0 | 2275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-376 | Water Main Replacment and/or Lining in Clove Road | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 501 502 | WM-0001 |  |  | WATER MAIN REPLCMNT AND/OR LINING IN CLOVE RD B/W MOSEL AVE & LAKEVIEW TERR., ETC. | 2019 | 4821 | 10389.72 | 967 | 0 | 0 | 0 | 0 | 0 | 11356.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-377 | Distribution water main extensions/replacements; | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 500 | WM-0001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | DISTRIBUTION WATER MAIN EXTENSIONS/REPLACEMENTS; HYDRANT AND VALVE REPLACEMENTS; NEW BUILDINGS | 2019 | 6123 | 8788.92 | 230 | 0 | 0 | 0 | 0 | 0 | 9018.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-386 | Water Main replacement, South & Arlington Aves, SI | AUGMENTATION OF WATER SUPPLY SYSTEMS | 501 | WM-0001 |  |  | INSTALLATION OF DISTRIBUTION WATER MAINS, SOUTH AVE B/T RICHMOND TERRACE, NETHERLAND AVE & ARLINGTON PLACE, STATEN ISLAND | 2019 | 7197 | 0 | 0 | 0 | 7197 | 0 | 0 | 0 | 7197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | REDA-001 | Accelerated Distribution WM replcmnt & sewer rehab: S.I. | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 500 | WM-0001 SE-0200R SE-0002R | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | ACCELERATED DISTRIBUTION WATER MAIN REPLCMNT & SEWER REHABILITATION/REPLACEMENT, STATEN ISLAND | 2019 | 15000 | 15955.26 | 269 | 0 | 0 | 0 | 0 | 0 | 16224.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | REDA-002 | Accelerated Distribution WM replcmnt & sewer rehab: S.I. | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 500 | WM-0001 |  |  | ACCELERATED DISTRIBUTION WATER MAIN REPLCMNT & SEWER REHABILITATION/REPLACEMENT, STATEN ISLAND | 2019 | 22090 | 21895.44 | 54 | 0 | 0 | 0 | 0 | 0 | 21949.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | REDA-003 | Accelerated Distribution WM replcmnt & sewer rehab: S.I. | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 500 | WM-0001 |  |  | ACCELERATED DISTRIBUTION WATER MAIN REPLCMNT & SEWER REHABILITATION/REPLACEMENT, STATEN ISLAND | 2019 | 17175 | 18288.69 | 12194 | 0 | 0 | 0 | 0 | 0 | 30482.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-367 | Staten Island 1 and 3 Garage Construction + SOLARGR10 | GARAGES AND FACILITIES | 501 503 | S-0136 PU-0025 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | CONSTRUCTION OF NEW GARAGE | 2019 | 143872 | 26861.5 | 1200 | 146071 | 0 | 0 | 0 | 0 | 174132.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-383S | STATEN ISLAND 3 GARAGE HVAC | GARAGES AND FACILITIES | 503 | S-0136 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | HVAC REPLACEMENT | 2019 | 477 | 933.34 | 570 | 17079 | 0 | 0 | 0 | 0 | 18582.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW14 | Reconstruction of South Beach - Hurricane Sandy - RED-375 | PRIMARY STREET RECONSTRUCTION | 500 | HW-0001R TF-0002 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | RECONSTRUCTION OF SOUTH BEACH - HURRICANE SANDY | RECONSTRUCTION OF SOUTH BEACH - HURRICANE SANDY | 2019 | 21204 | 4058.42 | 1562 | 0 | 0 | 0 | 0 | 0 | 5620.42 | 11599.56 | 1594 | 0 | 0 | 0 | 0 | 0 | 13193.56
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW15 | Reconstruction of Midland Beach - Hurricane Sandy | PRIMARY STREET RECONSTRUCTION | 500 | HW-0001R WM-0001 TF-0002 TF-0502 HW-0200 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | RECONSTRUCTION OF MIDLAND BEACH - HURRICANE SANDY | RECONSTRUCTION OF MIDLAND BEACH - HURRICANE SANDY | 2019 | 12825 | 2549.44 | 2418 | 0 | 0 | 11 | 0 | 0 | 4978.44 | 6141.29 | 2543 | 0 | 0 | 1361 | 0 | 0 | 10045.29
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHWSI | Non When & Where - Staten Island - Hurricane Sandy | PRIMARY STREET RECONSTRUCTION | 500 | HW-0061 HW-0001R TF-0002 HW-0200 TF-0502 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | NON WHEN AND WHERE - STATEN ISLAND HURRICANE SANDY | NON WHEN AND WHERE - STATEN ISLAND HURRICANE SANDY | 2019 | 7589 | 317 | 2 | 765 | 0 | 0 | 0 | 0 | 1084 | 0 | 0 | 3147 | 0 | 0 | 0 | 0 | 3147
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR01 | Hylan Blvd Streetscape Improvements | PRIMARY STREET RECONSTRUCTION | 500 | HW-0001R | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | HYLAN BLVD STREETSCAPE IMPROVEMENTS | HYLAN BLVD STREETSCAPE IMPROVEMENTS | 2019 | 1800 | 315 | 0 | 0 | 0 | 0 | 0 | 0 | 315 | 219.28 | 484 | 0 | 2999 | 0 | 0 | 0 | 3702.28
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-208D | SE-208D/SE-362D STM/SAN SWR IN FOREST HILL RD, SI | EXTENSIONS TO ACCOMMODATE NEW DEVELOPMENT | 502 | SE-0362 SE-0208 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | N/A |  | 2019 | 10510 | 246.26 | 0 | 0 | 0 | 5331 | 0 | 0 | 5577.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-413A | STM/SAN IN CEDAR GROVE AV - EBBITTS ST & NEW DROP LANE | EXTENSIONS TO ACCOMMODATE NEW DEVELOPMENT | 502 | SE-0414 WM-0001 SE-0413 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | SE-413A /SE-414A STM/SAN IN CEDAR GROVE AV - EBBITTS ST & NEW DROP LANE | SE-413A /SE-414A STM/SAN IN CEDAR GROVE AV - EBBITTS ST & NEW DROP LANE | 2019 | 17315 | 1197.2 | 0 | 8588 | 0 | 0 | 0 | 0 | 9785.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-414A | SANITRY SEWER IN CEDAR GROVE AV- EBBITS ST & DORPLANE | EXTENSIONS TO ACCOMMODATE NEW DEVELOPMENT | 502 | SE-0414 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | SANITRY SEWER IN CEDAR GROVE AV- EBBITS ST & DROPLANE, ETC (HWR-669C) | 2019 | 5170 | 0 | 0 | 5687 | 0 | 0 | 0 | 0 | 5687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-734 | SE-734 SAN SEWER IN RICHARD AVE, SI | EXTENSIONS TO ACCOMMODATE NEW DEVELOPMENT | 503 | WM-0001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | CONSTRUCTION OF SANITARY SEWERS IN RICHARD AVE FROM EASTWOOD AVE TO CLEARMONT AVE IN STATEN ISLAND. | CONSTRUCTION OF SANITARY SEWERS IN RICHARD AVE FROM EASTWOOD AVE TO CLAVE,IN STATEN ISLAND | 2019 | 5405 | 22640.1 | 0 | 0 | 0 | 132 | 0 | 0 | 22772.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-740B | SANITARY SEWERS IN ROCKLAND AVENUE | EXTENSIONS TO ACCOMMODATE NEW DEVELOPMENT | 502 | SE-0740 WM-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | SANITARY SEWERS IN ROCKLAND AVENUE | SANITARY SEWERS IN ROCKLAND AVENUE | 2019 | 10232 | 744.56 | 0 | 0 | 172 | 9798 | 0 | 0 | 10714.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-751 | CHESTER AV - IRVINGTON ST AND ARBUTUS AVE | EXTENSIONS TO ACCOMMODATE NEW DEVELOPMENT | 503 | WM-0001 SE-0002R SE-0200R | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | CHESTER AV - IRVINGTON ST AND ARBUTUS AVE | CHESTER AV - IRVINGTON ST AND ARBUTUS AVE | 2019 | 15870 | 2737.04 | 0 | 0 | 15598 | 0 | 0 | 0 | 18335.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-796 | SANITARY SEWER IN RICHMOND VALLEY ROAD | EXTENSIONS TO ACCOMMODATE NEW DEVELOPMENT | 503 | SE-0200R | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | SANITARY SEWER IN RICHMOND VALLEY ROAD | 2019 | 18202 | 30173.07 | 180 | 0 | 0 | 0 | 0 | 0 | 30353.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-798 | STRM & SAN SWR IN ROBINSON AV B/T HYLAN BLVD & US BULKHEAD | EXTENSIONS TO ACCOMMODATE NEW DEVELOPMENT | 503 | SE-0200R SE-0002R TF-0002 HW-0200 |  |  | STRM & SAN SWR IN ROBINSON AV B/T HYLAN BLVD & US BULKHEAD | 2019 | 10995 | 49435.28 | 1659 | 0 | 0 | 0 | 0 | 0 | 51094.28 | 3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-803 | SAN & STRM SEWER IN RAMBLE ROAD B/T ADRIENNE PL & DENT ROAD | BLUEBELT PROGRAM | 503 | SE-0200R SE-0005 SE-0002R WM-0001 |  |  | SAN & STRM SEWER IN RAMBLE ROAD B/T ADRIENNE PL & DENT ROAD | 2019 | 12672 | 43399.99 | 5254 | 0 | 0 | 0 | 0 | 0 | 48653.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-812 | Sanitary & Storm swr in Page Av b/t Amboy Rd & Estella Pl | EXTENSIONS TO ACCOMMODATE NEW DEVELOPMENT | 503 | WM-0001 SE-0002R SE-0200R HW-D104 SE-0944 HW-R005 HW-0061 SE-0005 HW-0001R | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | SANITARY & STORM SWR IN PAGE AV B/T AMBOY RD & ESTELLA PL | 2019 | 15518 | 56979.37 | 5090 | 543 | 0 | 0 | 0 | 0 | 62612.37 | 31.8 | 32 | 0 | 0 | 0 | 0 | 0 | 63.8
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-846 | New Storm & Sanitary Sewers Snug Harbor area, SI | BLUEBELT PROGRAM | 501 | SE-0200R SE-0002R WM-0001 SE-0005 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | NEW STORM AND SAITARY SEWER EXTENSION AND REPLACMENT AND WM REPLACEMENT. RICHMOND TERRACE BETWEEN SNUG HARBOR AND BARD AVENUE AND VARIOUS SNUG HARBOR LOCATION, SI | 2019 | 25884 | 600 | 0 | 0 | 0 | 0 | 0 | 23884 | 24484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SECBRKR01 | Reconstruction & installation of new catch basins, SI & BK | REPLACEMENT OF CHRONICALLY FAILING COMPONENTS | 500 | EP-0007 SE-1000 SE-0750 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | RECONSTRUCTION & INSTALLATION OF NEW CATCH BASINS, BK & SI | 2019 | 3000 | 0 | 0 | 0 | 0 | 0 | 4533 | 0 | 4533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002212 | SAN SEWER IN CLOVE LAKE PARK , SI | REPLACEMENT OF CHRONICALLY FAILING COMPONENTS | 501 | SE-0002R | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  |  | 2019 | 2375 | 52.25 | 0 | 1871 | 0 | 0 | 0 | 0 | 1923.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002237 | Sanitary and Storm Sewer in Manee Avenue | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 503 | SE-0002R SE-0200R |  |  | SANITARY AND STORM SEWER IN MANEE AVENUE BETWEEN AMBOY ROAD AND DEAD END, ETC | 2019 | 4113 | 0 | 0 | 0 | 4113 | 0 | 0 | 0 | 4113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002238 | SANITARY SEWER IN FOREST HILL RD - TRAVIS AV & ROCKLAND AV | EXTENSIONS TO ACCOMMODATE NEW DEVELOPMENT | 502 | SE-0002R WM-0001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | SANITARY SEWER IN FOREST HILL RD - TRAVIS AV & ROCKLAND AV | SANITARY SEWER IN FOREST HILL RD - TRAVIS AV & ROCKLAND AV | 2019 | 1164 | 31.52 | 0 | 0 | 0 | 1020 | 0 | 0 | 1051.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002274 | SAN SWR IN TWOMBLEY, HOPKINS, CEBRA, AVENUE | REPLACEMENT OF CHRONICALLY FAILING COMPONENTS | 501 503 | SE-0200R | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | SANITARY SEWER IN TWOMBLEY AVENUE (HOPKINS AVE. BUFFALO AVE) HOPKINS AVENUE (TWOMBLEY AVE) AND CEBRA AVE (CHESTER PI- WARD AVENUE) SEWAGE TREATMENT PLANT TO WHICH PROJ IS TRIBUTE OAKWOOD BEACH. | 2019 | 1071 | 4133.23 | 42 | 0 | 0 | 0 | 0 | 0 | 4175.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002311 | SAN & STRM SWR IN BERTRAM AV B/T ZEPHYR AV & HYLAN BLVD. ETC | EXTENSIONS TO ACCOMMODATE NEW DEVELOPMENT | 503 | SE-0200R | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | SAN & STRM SWR IN BERTRAM AV B/T ZEPHYR AV & HYLAN BLVD. ETC | 2019 | 6526 | 25740.21 | 317 | 0 | 0 | 0 | 0 | 0 | 26057.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002317 | SAN & STRM SEWER IN HALPIN AVE | BLUEBELT PROGRAM | 503 | SE-0002R SE-0200R WM-0001 SE-0005 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | SAN & STRM SEWER IN HALPIN AVE | 2019 | 11969 | 2072.62 | 315 | 0 | 0 | 13165 | 0 | 0 | 15552.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002321 | Sanitary sewer and wm replacement plus force main extension | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 502 | SE-0002R SE-0200R WM-0001 SE-1000 EP-0007 HW-0200 TF-0002 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | SANITARY AND WATER MAIN REPLACEMENT NAUGHTON AVE B/T LACNIA AVE AND MASON AVE AND MASON AVE B/T LIBERTY AVE AND SEAVIEW AVE. NEW FORCE MAINEXTENSION IN MASON AVE BETWEEN SEAVER AVE AND SEAVIEW AVE, STATEN ISLAND. | 2019 | 4736 | 1206.01 | 0 | 0 | 39399 | 0 | 0 | 0 | 40605.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002323 | SAN & STRM SWRS: WALKER ST, ETC. | EXTENSIONS TO ACCOMMODATE NEW DEVELOPMENT | 501 | SE-0002R SE-0200R WM-0001 EP-0007 HW-0200 SE-1000 SE-0944 |  |  | SAN & STRM SWR. CASTLE AVE B/T VAN NAME & SIMONSON AVE, SI | 2019 | 2711 | 625 | 8864 | 0 | 0 | 0 | 0 | 0 | 9489 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 150
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002324 | New sanitary sewers in Camden ave. Staten Island | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 503 | SE-0002R WM-0001 SE-0200R | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | NEW SANITARY SEWERS IN CAMDEN AVE. STATEN ISLAND | 2019 | 2358 | 560.5 | 104 | 0 | 3181 | 0 | 0 | 0 | 3845.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002326 | Storm and Sanitary Sewers in Wardwell Ave. S.I. | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 501 | SE-0200R SE-0002R | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | STORM AND SANITARY SEWERS IN WARDWELL AVE. BETWEEN LEONARD AVE AND DEAD END. PLUS WATER MAIN WORKS. | 2019 | 14281 | 19328.57 | 1028 | 0 | 0 | 0 | 0 | 0 | 20356.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002327 | SANITARY SEWER IN VICTORY BLVD, SI | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 501 | SE-0002R WM-0001 |  |  | SAN SWR IN VICTORY BLVD B/T MANOR RD & RAYMOND AVE, SI | 2019 | 950 | 54.56 | 950 | 0 | 0 | 0 | 0 | 0 | 1004.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002328 | SAN SWR EXTENSION IN CHICAGO AVE | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 501 | SE-0002R |  |  | SAN SWR EXTENSION IN CHICAGO AVE, B/T COLUMBIA AV AND LANDIS AV | 2019 | 824 | 381.6 | 690 | 0 | 0 | 0 | 0 | 0 | 1071.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002329 | SAN, STM & WM IN LANDMARK COLONY | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 500 | SE-0002R WM-0001 |  |  | STORM, SAN & WM IN LANDMARK COLONY | 2019 | 10046 | 0 | 0 | 0 | 10046 | 0 | 0 | 0 | 10046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER0201ZA | Reconstruction of Existing Sewers, Staten Island | REPLACEMENT OF CHRONICALLY FAILING COMPONENTS | 500 | SE-0002R EP-0007 |  |  | RECONSTRUCTION OF EXISTING SEWERS, STATEN ISLAND. | 2019 | 5250 | 0 | 5519 | 0 | 0 | 0 | 0 | 0 | 5519 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER0201ZB | Reconstruction of Existing Sewers, Staten Island | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 500 | SE-0002R EP-0007 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | RECONSTRUCTION OF EXISTING SEWERS, STATEN ISLAND | 2019 | 9500 | 0 | 10245 | 0 | 0 | 0 | 0 | 0 | 10245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200100 | STORM SEWER EXT IN AMSTERDAM AVE | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 502 | SE-0200R HW-0200 SE-1000 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | STORM SEWER EXT IN AMSTERDAM AVE | 2019 | 933 | 4138.67 | 39 | 0 | 0 | 0 | 0 | 0 | 4177.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200127 | STORM SEWER IN ROCKLAND AV - RICHMOND RD AND MEISNER AV | EXTENSIONS TO ACCOMMODATE NEW DEVELOPMENT | 502 | SE-0200R | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | STORM SEWER IN ROCKLAND AV - RICHMOND RD AND MEISNER AV | STORM SEWER IN ROCKLAND AV - RICHMOND RD AND MEISNER AV | 2019 | 3768 | 47.96 | 0 | 0 | 0 | 3721 | 0 | 0 | 3768.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200128 | STORM SEWER (BMP) IN ROCKLAND AV - RICHMOND RD & MEISNER AV | EXTENSIONS TO ACCOMMODATE NEW DEVELOPMENT | 502 | SE-0200R | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | STORM SEWER (BMP) IN ROCKLAND AV - RICHMOND RD & MEISNER AV | STORM SEWER (BMP) IN ROCKLAND AV - RICHMOND RD & MEISNER AV | 2019 | 118 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200151 | Stm & Sani swr ext. & WM replacement Amboy Rd, SI | EXTENSIONS TO ACCOMMODATE NEW DEVELOPMENT | 503 | SE-0200R SE-0944 |  |  | STORM & SANITARY SEWERS & WM REPLACEMNT AMBOY RD & SO. RAILROAD AVE, SI | 2019 | 5654 | 12236.67 | 550 | 0 | 0 | 0 | 0 | 0 | 12786.67 | 553.18 | 5 | 0 | 0 | 32 | 0 | 0 | 590.18
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200153 | STORM SEWER IN FOREST HILL RD - TRAVIS AV & ROCKLAND AV | EXTENSIONS TO ACCOMMODATE NEW DEVELOPMENT | 502 | SE-0200R | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | STORM SEWER IN FOREST HILL RD - TRAVIS AV & ROCKLAND AV | STORM SEWER IN FOREST HILL RD - TRAVIS AV & ROCKLAND AV | 2019 | 409 | 11 | 0 | 0 | 0 | 348 | 0 | 0 | 359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200202 | New Stm. Swr. Ext. in Eagan Ave. S.I. | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 503 | HW-0200 SE-0200R SE-0002R WM-0001 WM-0006 EP-0007 SE-0944 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NEW STM. SWR. EXT. IN EAGAN AVE. AND WATER MAIN REPAIR IN KEEGANS LANE. | 2019 | 4266 | 1323.03 | 33632 | 0 | 0 | 0 | 0 | 0 | 34955.03 | 0 | 207 | 0 | 0 | 0 | 0 | 0 | 207
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200226 | STORM AND SANITARY SEWERS & WM WORK IN TRAVIS AREA | EXTENSIONS TO ACCOMMODATE NEW DEVELOPMENT | 500 502 | SE-0200R WM-0001 SE-0002R | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | STORM, SANITARY AND WATER MAIN WORK IN TRAVIS AREA. | 2019 | 13223 | 30850.32 | 11200 | 0 | 0 | 0 | 0 | 0 | 42050.32 | 375.69 | 0 | 0 | 0 | 0 | 0 | 0 | 375.69
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200235 | Storm Sewer Extension in Richmond Ave & Amboy Rd, SI | EXTENSIONS TO ACCOMMODATE NEW DEVELOPMENT | 503 | SE-0200R |  |  | STRM SWR EXT RICHMOND AVE & AMBOY RD, SI | 2019 | 3143 | 9356.37 | 2275 | 0 | 0 | 0 | 0 | 0 | 11631.37 | 12.5 | 0 | 0 | 0 | 0 | 0 | 0 | 12.5
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200236 | STRM SWR EXT & WM WORK IN NORTH AV, ETC. | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 501 | SE-0200R WM-0001 |  |  | STRM SWR EXT & WM WORK IN NORTH AV, B/T NEAL DOW AV & LIVERMORE AV, STRM SWR EXT IN FOREST AV, B/T LIVERMORE AV & MARIANNE ST | 2019 | 1998 | 0 | 0 | 1998 | 0 | 0 | 0 | 0 | 1998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200241 | STRM & SWR IN BLOOMINGTON RD B/T AUTHUR KILL RD & PITNEY AVE | EXTENSIONS TO ACCOMMODATE NEW DEVELOPMENT | 503 | SE-0200R SE-0002R | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | STRM & SWR IN BLOOMINGTON RD B/T AUTHUR KILL RD & PITNEY AVE, ETC (HWR-919) | 2019 | 4658 | 19718.41 | 101 | 0 | 0 | 0 | 0 | 0 | 19819.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200245 | NEW STRM SWR & WM REPLACEMT IN ACACIA AV, ETC. | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 503 | SE-0002R SE-0200R SE-0005 WM-0001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | NEW STORM SEWER AND WATER MAIN REPLACEMENT IN ACACIA AVENUE BETWEEN DEAD END AND AMBOY ROAD ETC. | 2019 | 21157 | 30669.78 | 3935 | 0 | 0 | 0 | 0 | 0 | 34604.78 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 6
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200247 | New Storm Sewers in King St | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 503 | SE-0200R WM-0001 |  |  | NEW STORM SEWERS IN KING ST BETWEEN PRESTON AVE AND RIDGECREST AVE ETC | 2019 | 3406 | 388.76 | 0 | 0 | 4110 | 0 | 0 | 0 | 4498.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200251 | EXT OF STRM SWR AND WM WORK IN 3RD ST | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 502 | SE-0200R WM-0001 |  |  | EXT OF STRM SWR AND WM WORK IN 3RD ST, B/T NEW DORP LA AND STEELE AV | 2019 | 5354 | 450 | 0 | 0 | 0 | 5154 | 0 | 0 | 5604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200255 | Stm. Swr. Ext. W. Cedarview Ave b/t Wolverine&Gilbert st, SI | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 503 | WM-0001 SE-0200R SE-1000 HW-0200 SE-0002R EP-0007 |  |  | STORM. SWR. EXTENSION AND WATER MAIN REPLACEMENT ON W. CEDARVIEW AVE B/T GILBERT & WOLVERINE STS, SI | 2019 | 1470 | 331 | 790 | 9119 | 0 | 0 | 0 | 0 | 10240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200258 | Sanitary and Storm Sewer in West Castor Place between Alvers | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 503 | SE-0200R SE-0002R | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | SANITARY AND STORM SEWER BETWEEN WEST CASTOR PLACE AND BETWEEN ALVERSON AVENUE AND POWELL STREET, ETC | 2019 | 6587 | 1795.49 | 1344 | 7426 | 0 | 0 | 0 | 0 | 10565.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200261 | Storm sewer in Roma Ave bet Tysens Lane & Ebbits Street | EXTENSIONS TO ACCOMMODATE NEW DEVELOPMENT | 502 | SE-0200R WM-0001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | STORM SEWER IN ROMA AVE BET TYSENS LANE & EBBITS STREET | 2019 | 1976 | 0 | 0 | 0 | 0 | 1976 | 0 | 0 | 1976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200269 | Storm Swr install Park hill Ct b/t vanderbuilt & tomkins ave | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 501 | SE-0200R WM-0001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | TORM SEWER INSTALLATION @PARK HILL CT B/T VANDERBUILT & TOMKINS AVES,SI | 2019 | 1465 | 150 | 0 | 0 | 0 | 1219 | 0 | 0 | 1369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200285 | NEW STM. SWR EXT. & WM REPL IN TODT HILL RD., SI | BLUEBELT PROGRAM | 502 | SE-0200R WM-0001 SE-0005 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | NEW STM. SWR EXT. & WM REPL ACEMENT IN TODT HILL RD BETWEEN WILLOW POND RD & FOUR CORNERS RD. ETC. | 2019 | 7249 | 964.45 | 0 | 0 | 0 | 5587 | 0 | 0 | 6551.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200289 | Storm sewer & WM work, Forest ave, SI | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 501 | WM-0001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | STORM SEWER AND WATER MAIN WORK, FOREST AVE B/T SOUTH AVE & GRANDVIEWAVE, SI | 2019 | 426 | 0 | 909 | 0 | 0 | 0 | 0 | 0 | 909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200290 | New Storm Sewer Ext & Water Main Replacement in Forest Ave | EXTENSIONS TO ACCOMMODATE NEW DEVELOPMENT | 501 | SE-0200R WM-0001 SE-0002R |  |  | NEW STROM SEWER EXT & WATER MAIN REPLACEMENT IN FOREST AVE BETWEEN BROADWAY AND RAYMOND PLACE ETC | 2019 | 3675 | 650 | 0 | 0 | 3675 | 0 | 0 | 0 | 4325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200292 | SAN & STRM SWR REPLACMT & WM WORK IN FLOYD ST | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 501 | SE-0002R SE-0200R WM-0001 |  |  | SAN & STRM SWR REPLACMT & WM WORK IN FLOYD ST | 2019 | 18099 | 600 | 0 | 0 | 0 | 13923 | 0 | 0 | 14523 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200293 | Storm sewer cons and water main replacement | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 501 | SE-0200R WM-0001 |  |  | STORM AND SEWER CONSTRUCTION AND WATER MAIN REPLACEMENT IN GREENFIELDAVE B/T OSGOOD AVE AND THE OUTFALL INTO THE NEW YORK BAY, STATEN ISLAND | 2019 | 11570 | 0 | 0 | 0 | 9601 | 0 | 0 | 0 | 9601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200294 | STM. SWR EXT. & WM REPL., IN WOODROW RD CONNECTOR,SI | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 503 | SE-0005 SE-0200R WM-0001 |  |  | STM. SWR EXTENSION. & WM REPL.ACEMENT IN WOODROW RD CONNECTOR,SI | 2019 | 1603 | 0 | 0 | 1359 | 0 | 0 | 0 | 0 | 1359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200309 | Strm swr R+Ext & WM Work, Maguire Avenue | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 503 | SE-0200R WM-0001 |  |  | REPLACEMENT AND EXTENSION OF STORM SEWER IN MAGURIE AVENUE BETWEEN DEPEW PLACE AND SAGONA COURT. | 2019 | 5047 | 0 | 0 | 0 | 5048 | 0 | 0 | 0 | 5048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200552 | STRM & SAN SWR AND WM WORK IN GRANITE AV | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 501 | SE-0200R SE-0002R WM-0001 |  |  | STRM & SAN SWR AND WM WORK IN GRANITE AV, B/T WALKER ST & DAVID PL | 2019 | 5603 | 381.72 | 0 | 0 | 4313 | 0 | 0 | 0 | 4694.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER20079 | RECON OF STORM SEWER, WILLOW AV(TOMPKINS-EDGEWATER AVS) | REPLACEMENT OF CHRONICALLY FAILING COMPONENTS | 501 | SE-0002R SE-0200R | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | N/A |  | 2019 | 1343 | 0 | 0 | 0 | 0 | 1919 | 0 | 0 | 1919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SOLARDOS2 | Staten Island 3 Garage HVAC | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 503 | PU-0025 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  |  | 2019 | 755 | 37.35 | 0 | 1382 | 0 | 0 | 0 | 0 | 1419.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SOLARGR10 | DSNY - PV INSTALLATION ON NEW GARAGE- STATEN ISLAND 1/3 | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 501 | PU-0025 |  |  | DSNY - PV INSTALLATION ON NEW GARAGE- STATEN ISLAND 1/3 | 2019 | 7601 | 0 | 335 | 7268 | 0 | 0 | 0 | 0 | 7603 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO276EXT2 | 100 Richmond Terrace - Family Court/ Exterior | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 501 | CO-0276 |  |  | EXTERIOR OF COURTHOUSE | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 401 | 4013 | 4414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO287R-1 | DASNY - NEW STATEN ISLAND SUPREME COURT | CONSTRUCTION OF NEW COURT FACILITIES | 501 | CO-0287 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | STATEN ISLAND, NY 10301 | CONSTRUCTION OF AN ENTIRE NEW BUILDING | 2019 | 213781 | 5726.13 | 3435 | 0 | 0 | 0 | 0 | 0 | 9161.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO301FA | 130 STUYVESANT PL.- FIRE ALARM/SPRINKLER | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 501 | CO-0301 |  |  | 130 STUYVESANT PL.- FIRE ALARM/SPRINKLER | 2019 | 13000 | 0 | 0 | 0 | 0 | 1000 | 0 | 12000 | 13000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO301HV1 | 130 STUYVESANT PL.- CHILLER AND BOILER | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 501 | CO-0301 |  |  | 130 STUYVESANT PLACE - CHILLER AND BOILER REPLACEMEN | 2019 | 0 | 0 | 0 | 0 | 0 | 345 | 0 | 5426 | 5771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0035 | DPR-Greenbelt Recreation Center | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 501 | PU-0025 |  |  | DPR-GREENBELT RECREATION CENTER | 2019 | 157 | 0 | 157 | 0 | 0 | 0 | 0 | 0 | 157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW29310R | 10 RICHMOND TERRACE - FIRE ALARM | LEGAL MANDATES AND CORRECTION OF UNSAFE CONDITIONS | 501 | PW-0293 |  |  | 10 RICHMOND TERRACE - FIRE ALARM | 2019 | 0 | 0 | 0 | 2181 | 0 | 8870 | 0 | 0 | 11051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DOFR | DOF - 350 ST. MARK'S PLACE - LEASED SPACE | RENOVATION OF LEASED SPACE | 501 | PW-0326 |  |  | 350 ST. MARK'S PLACE - DOF LEASED SPACE | 2019 | 1544 | 0 | 0 | 0 | 1591 | 0 | 0 | 0 | 1591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RAR | LAW DEPT - RAISE THE AGE -SI | RENOVATION OF LEASED SPACE | 501 | PW-0326 |  |  | LAW DEPT - RAISE THE AGE -SI | 2019 | 0 | 0 | 0 | 2697 | 0 | 0 | 0 | 0 | 2697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RHP | OCA RELOCATION FROM HOMEPORT - STATEN ISLAND | RENOVATION OF LEASED SPACE | 500 501 | ED-0075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RELOCATION FROM HOMEPORT - STATEN ISLAND - DUE TO MAYOR'S REDEVELOPMENT PLAN | 2019 | 1012 | 2766.7 | 160 | 0 | 0 | 0 | 0 | 0 | 2926.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77501BL | 10 RICHMOND TERR.- BOILER REPLACEMENT | REHABILITATION OF CITY-OWNED OFFICE SPACE | 501 | PW-0077 |  |  | SQ FT | 2019 | 1307 | 0 | 0 | 0 | 1185 | 0 | 0 | 0 | 1185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77501DB | 10 RICHMOND TERRACE - RENOVATION | REHABILITATION OF CITY-OWNED OFFICE SPACE | 501 | PW-0077 |  |  | SQ/IA | 2019 | 0 | 0 | 0 | 0 | 417 | 476 | 4909 | 0 | 5802 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77501EL | 10 RICHMOND TERRACE- ELECTRICAL UPGRADE | REHABILITATION OF CITY-OWNED OFFICE SPACE | 500 501 | PW-0077 |  |  | 10 RICHMOND TERRACE ELECTRICAL UPGRADE | 2019 | 5900 | 3800.66 | 110 | 0 | 0 | 0 | 0 | 0 | 3910.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SEC3 | 130 STUYVESANT PLACE- SECURITY BARRIER SI DA | REHABILITATION OF CITY-OWNED OFFICE SPACE | 501 | PW-0077 |  |  | 130 STUYVESANT PLACE SECURITY BARRIER FOR SI DA | 2019 | 292 | 0 | 182 | 0 | 0 | 0 | 0 | 0 | 182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWR077MUR | 18 RICHMOND TERRACE- STATEN ISLAND COURTHOUSE MURALS | REHABILITATION OF COURT BUILDINGS | 501 | PW-R077 |  |  | PERFORM NECESSARY CONSTRUCTION ASSOCIATED WITH THE TRANSFER OF COURTHOUSE MURALS | 2019 | 50 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWR77GRGE | ST. GEORGE COURTHOUSE & HYATT STREET PLAZA | REHABILITATION OF CITY-OWNED OFFICE SPACE | 500 501 | PW-R077 |  |  | ST. GEORGE COURTHOUSE & HYATT STREET PLAZA | 2019 | 1518 | 0 | 0 | 780 | 0 | 0 | 0 | 0 | 780 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | STGESPLND | ST. GEORGE ESPLANADE | WATERFRONT DEVELOPMENT | 501 | PW-R077 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | ST. GEORGE ESPLANADE STATEN ISLAND | RECONSTRUCTION | 2019 | 4760 | 3317.04 | 0 | 0 | 0 | 800 | 0 | 0 | 4117.04 | 3.07 | 0 | 0 | 0 | 0 | 0 | 0 | 3.07
20190425 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LN18ALELE | ALLERTON - Elevator Replacement - 3 stop | ESSENTIAL RECONSTRUCTION OF FACILITIES | 111 | LN-0008 |  |  | *NEW* -ELEVATOR REPLACEMENT - 3 STOP | 2019 | 0 | 0 | 0 | 70 | 630 | 0 | 0 | 0 | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LN18ALRFW | ALLERTON BRANCH--NEW ROOF AND WINDOWS | ESSENTIAL RECONSTRUCTION OF FACILITIES | 111 | LN-X001 |  |  | NYPL ALLERTON BRANCH--NEW ROOF AND WINDOWS 2740 BARNES AVENUE. | 2019 | 0 | 0 | 0 | 0 | 0 | 100 | 900 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LN18BEADA | BELMONT- ADA Bathrooms | ESSENTIAL RECONSTRUCTION OF FACILITIES | 106 | LN-D008 |  |  | BELMONT BRANCH--UPGRADE RESTROOMS TO BECOME ADA COMPLIANT | 2019 | 0 | 0 | 0 | 0 | 0 | 50 | 450 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LN18CPBOI | CLASON'S POINT - New Boiler | ESSENTIAL RECONSTRUCTION OF FACILITIES | 109 | LN-0008 |  |  | NEW BOILER | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LN18DYBHV | SPUYTEN DUYVIL - Boiler and HVAC | ESSENTIAL RECONSTRUCTION OF FACILITIES | 108 | LN-0008 |  |  | SPUYTEN DUYVIL - BOILER AND HVAC | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 652 | 725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LN18MRBOI | New Boiler at Morrisania Branch Library | ESSENTIAL RECONSTRUCTION OF FACILITIES | 103 | LN-D008 |  |  | NEW BOILER AT MORRISANIA BRANCH LIBRARY | 2019 | 0 | 0 | 0 | 0 | 0 | 50 | 450 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LN18RDADA | Bathroom renovation at the Riverdale Branch Library | ESSENTIAL RECONSTRUCTION OF FACILITIES | 108 | LN-D008 |  |  | BATHROOM RENOVATION AT THE RIVERDALE BRANCH LIBRARY (ADA COMPLIANCE) | 2019 | 0 | 0 | 0 | 0 | 0 | 50 | 450 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LN18SVBOI | SOUNDVIEW - New Boiler | ESSENTIAL RECONSTRUCTION OF FACILITIES | 109 | LN-0008 |  |  | NEW BOILER | 2019 | 0 | 0 | 0 | 0 | 50 | 720 | 0 | 0 | 770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LNBEREXRE | Belmont - Exterior Renovation | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | LN-D008 |  |  | BELMONT PUBLIC LIBRARY - EXTERIOR RENOVATION -- BUILDING ENVELOPE/FACILITY PRESERVATION. FY19 ADP | 2019 | 0 | 0 | 0 | 0 | 0 | 100 | 900 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LNBERHVAC | Belmont Library - HVAC Upgrade | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | LN-D008 |  |  | BELMONT PUBLIC LIBRARY - HVAC UPGRADE -- HVAC/MECHANICAL SYSTEMS UPGRADE. FY19 ADP | 2019 | 0 | 0 | 0 | 0 | 0 | 150 | 1350 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LNCA16SDW | New Roof | ESSENTIAL RECONSTRUCTION OF FACILITIES | 100 | LN-D008 |  |  | NEW ROOF | 2019 | 0 | 0 | 0 | 0 | 0 | 30 | 270 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LNCA17PBY | PELHAM BAY: ADA restrooms and New Roof | ESSENTIAL RECONSTRUCTION OF FACILITIES | 100 | LN-D008 |  |  | PELHAM BAY: ADA RESTROOMS AND NEW ROOF | 2019 | 0 | 0 | 0 | 0 | 0 | 141 | 1037 | 0 | 1178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LNGDEXTRO | Grand Concourse New Roof, Building Envelope/Facility Preserv | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | LN-D008 |  |  | GRAND CONCOURSE PUBLIC LIBRARY - NEW ROOF -- BUILDING ENVELOPE/FACILITY PRESERVATION | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LNMPADA01 | Morris Park Branch -- ADA compliant entrance | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | LN-D008 |  |  | NYPL: MORRIS PARK BRANCH -- ADA COMPLIANT ENTRANCE | 2019 | 0 | 0 | 0 | 0 | 0 | 50 | 450 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LNVNADABA | Pelham Pk/Van Nest - ADA Bathroom | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | LN-D008 |  |  | NYPL: PELHAM PARKWAY- VAN NEST BRANCH -- ADA COMPLIANT BATHROOM | 2019 | 0 | 0 | 0 | 0 | 0 | 50 | 450 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LNXA11BXT | Bronx Library Center Network Equipment | ESSENTIAL RECONSTRUCTION OF FACILITIES | 100 | LN-X001 |  |  | BRONX BOROUGHWIDE TECHNOLOGY | 2019 | 0 | 366.66 | 0 | 84 | 367 | 0 | 0 | 0 | 817.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 042 | CITY UNIVERSITY | ACECUN507 | CUNY - Hostos CC Summer Boiler | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 104 | HN-0206 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | HOSTOOS CC SUMMER BOILER | 2019 | 103 | 102.6 | 100 | 0 | 0 | 0 | 0 | 0 | 202.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 042 | CITY UNIVERSITY | BX022-009 | Gould Memorial Lib Rotunda Staircase Installation | MISCELLANEOUS RECONSTRUCTION | 100 105 | HN-D002 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | INSTALLATION OF STAIRCASES FOR GOULD MEMORIAL LIB ROTUNDA | 2019 | 1093 | 427.5 | 665 | 0 | 0 | 0 | 0 | 0 | 1092.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 042 | CITY UNIVERSITY | BX024-011 | Roof Replacement | MISCELLANEOUS RECONSTRUCTION | 100 | HN-0206 HN-D005 HN-D002 HN-X002 HN-D004 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ROOF REPLACEMENT | 2019 | 3000 | 7050 | 8102 | 0 | 0 | 0 | 0 | 0 | 15152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 042 | CITY UNIVERSITY | BX024-019 | Gould Memorial Library Reconstruction | MISCELLANEOUS RECONSTRUCTION | 100 | HN-0206 |  |  | GOULD MEMORIAL LIBRARY RECONSTRUCTION | 2019 | 1500 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 042 | CITY UNIVERSITY | BX026-013 | ADA Entrance Ramps | MISCELLANEOUS RECONSTRUCTION | 100 105 | HN-X002 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ADA ENTRANCE RAMPS | 2019 | 300 | 43.59 | 0 | 256 | 0 | 0 | 0 | 0 | 299.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 042 | CITY UNIVERSITY | BX027-015 | Ohio Track & Field Restoration | MISCELLANEOUS RECONSTRUCTION | 100 | HN-X002 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | OHIO TRACK & FIELD RESTORATION | 2019 | 375 | 75 | 0 | 0 | 425 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 042 | CITY UNIVERSITY | BX032-015 | Monument Hills Restoration | MISCELLANEOUS RECONSTRUCTION | 100 | HN-D002 HN-0206 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | MONUMENT HILLS RESTORATION | 2019 | 200 | 147.11 | 87 | 0 | 0 | 116 | 0 | 0 | 350.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 042 | CITY UNIVERSITY | BX034-015 | Bliss Hall ADA Accessibility Improvements | MISCELLANEOUS RECONSTRUCTION | 100 | HN-D002 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BLISS HAAL ACCESSIBILITY IMPROVEMENTS | 2019 | 300 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 042 | CITY UNIVERSITY | BX038-016 | Lowe Hall ADA Accessibility Improvements | MISCELLANEOUS RECONSTRUCTION | 100 | HN-D002 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | LOWE HALL ADA ACCESSIBILITY IMPROVEMENTS | 2019 | 250 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 042 | CITY UNIVERSITY | BX039-016 | Alumni Gym Locker Room Accessibility Improvements | MISCELLANEOUS RECONSTRUCTION | 100 | HN-D005 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | ALUMNI GYM ADA IMPROVEMENTS | 2019 | 250 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 042 | CITY UNIVERSITY | BX040-017 | Bronx Express | MISCELLANEOUS RECONSTRUCTION | 100 | HN-0206 HN-X002 HN-D002 HN-D003 |  |  | STUDENT SUCCESS CENTER | 2019 | 4500 | 763.26 | 0 | 6272 | 0 | 0 | 0 | 0 | 7035.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 042 | CITY UNIVERSITY | BX041-017 | STEM Resourse Center | MISCELLANEOUS RECONSTRUCTION | 100 | HN-D002 HN-D004 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | STEM RESOURSE CENTER | 2019 | 150 | 28.06 | 28 | 0 | 0 | 94 | 0 | 0 | 150.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 042 | CITY UNIVERSITY | BX042-018 | Renovate Roscoe Brown Student Center | MISCELLANEOUS RECONSTRUCTION | 107 | HN-X002 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RENOVATE ROSCOE BROWN STUDENT CENTER | 2019 | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 042 | CITY UNIVERSITY | BX044-018 | Community Hall First Floor Renovation | MISCELLANEOUS RECONSTRUCTION | 100 | HN-D004 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | COMMUNITY HALL FIRST FLOOR RENOVATION | 2019 | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 042 | CITY UNIVERSITY | BX045-018 | ADA Accessibility for Roscoe C Brown Student Center | MISCELLANEOUS RECONSTRUCTION | 100 | HN-D004 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ADA ACCESSIBILITY FOR ROSCOE C BROWN STUDENT CENTER | 2019 | 400 | 0 | 0 | 0 | 0 | 400 | 0 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 042 | CITY UNIVERSITY | BX046-019 | Alumni Gym HVAC & ADA Improvements | MISCELLANEOUS RECONSTRUCTION | 105 | HN-D002 HN-X002 |  |  | ALUMNI GYM HVAV& ADA UPGRADES | 2019 | 3000 | 0 | 0 | 250 | 0 | 2750 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 042 | CITY UNIVERSITY | BX047-020 | Ohio Track & Field Upgrade | MISCELLANEOUS RECONSTRUCTION | 105 | HN-X002 |  |  | OHIO TRACK & FIELD UPGRADE | 2019 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 042 | CITY UNIVERSITY | CA034BX15 | Snow Hall Elevator | MISCELLANEOUS RECONSTRUCTION | 100 | HN-D002 HN-D004 HN-D005 HN-0206 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | SNOW HALL ELEVATOR | 2019 | 500 | 105 | 796 | 0 | 0 | 0 | 0 | 0 | 901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 042 | CITY UNIVERSITY | CA034HS13 | 500 Grand Concourse 3rd Floor Renovation | MISCELLANEOUS RECONSTRUCTION | 100 | HN-0206 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | 500 GRAND CONCOURSE THIRD FLOOR RENOVATION | 2019 | 6950 | 425 | 5450 | 1075 | 0 | 0 | 0 | 0 | 6950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 042 | CITY UNIVERSITY | CA036-014 | Hostos CC: Allied Health and Sciences Building | MISCELLANEOUS RECONSTRUCTION | 100 101 | HN-X002 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | COMMUNITY COLLEGE IMPROVEMENTS | 2019 | 2003 | 0 | 0 | 0 | 0 | 2003 | 0 | 0 | 2003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 042 | CITY UNIVERSITY | CA091HS96 | Hostos Retaining Wall Project | MISCELLANEOUS RECONSTRUCTION | 100 | HN-0206 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | HOSTOS RETAINING WALL PROJECT | 2019 | 1500 | 0 | 175 | 0 | 0 | 1325 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 042 | CITY UNIVERSITY | CA200BX06 | ALUMNI GYM BRIDGE REPLACEMENT | MISCELLANEOUS RECONSTRUCTION | 100 | HN-0206 |  |  | ALUMNI GYM BRIDGE REPLACEMENT | 2019 | 310 | 175 | 135 | 0 | 0 | 0 | 0 | 0 | 310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 042 | CITY UNIVERSITY | CA202HS04 | ADA Improvements | MISCELLANEOUS RECONSTRUCTION | 105 | HN-D002 HN-0206 | PROJECT DELAYED DUE TO UNAVAILABILITY OF PRODUCT |  | ADA IMPROVEMENTS | 2019 | 750 | 770.12 | 0 | 0 | 0 | 767 | 0 | 0 | 1537.12 | 91.7 | 0 | 0 | 0 | 0 | 0 | 0 | 91.7
20190425 | BRONX | 042 | CITY UNIVERSITY | CA91BX019 | Colston & Community Hall Facade Restoration | MISCELLANEOUS RECONSTRUCTION | 100 | HN-0206 HN-X002 |  |  | COLSTON AND COMMUNITY HALL FACADE RESTORATION | 2019 | 568 | 0 | 568 | 0 | 0 | 0 | 0 | 0 | 568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 042 | CITY UNIVERSITY | CA92BX019 | Colston Emergency Heating Restoration | MISCELLANEOUS RECONSTRUCTION | 100 | HN-0206 |  |  | COLSTON EMERGENCY HEATING RESTORATION | 2019 | 309 | 0 | 309 | 0 | 0 | 0 | 0 | 0 | 309 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 042 | CITY UNIVERSITY | HS007-010 | PEDESTRIAN BRIDGE ROOF REPLACEMENT | MISCELLANEOUS RECONSTRUCTION | 100 101 | HN-D004 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ROOF REPLACEMENT | 2019 | 323 | 150 | 0 | 0 | 0 | 173 | 0 | 0 | 323 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 042 | CITY UNIVERSITY | HS033-007 | Natural Science Lab Renovation | MISCELLANEOUS RECONSTRUCTION | 100 101 | HN-X002 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | NATURAL SCIENCE LAB RENOVATION | 2019 | 2000 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 042 | CITY UNIVERSITY | HS034-007 | 450 Grand Concourse Theater Improvements | MISCELLANEOUS RECONSTRUCTION | 100 | HN-D004 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | 450 GRAND CONCOURSE THEATER IMPROVEMENTS | 2019 | 250 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 042 | CITY UNIVERSITY | HS041-011 | 500 Grand Concourse 4th Floor and Emerg. Generator | MISCELLANEOUS RECONSTRUCTION | 100 101 | HN-X002 HN-0206 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | EMERGENCY GENERATOR | 2019 | 778 | 5807.82 | 0 | 0 | 0 | 38 | 0 | 0 | 5845.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 042 | CITY UNIVERSITY | HS043-011 | Hostos CC - 500 Grand Concourse Renovations | MISCELLANEOUS RECONSTRUCTION | 100 101 | HN-0206 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | 500 GRAND CONCOURSE RENOVATIONS | 2019 | 3970 | 0 | 0 | 535 | 0 | 0 | 0 | 0 | 535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 042 | CITY UNIVERSITY | HS047-013 | Savoy Building Roof Replacement | MISCELLANEOUS RECONSTRUCTION | 100 101 | HN-D002 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | SAVOY BLDG. ROOF REPLACEMENT | 2019 | 600 | 900 | 0 | 0 | 0 | 50 | 0 | 0 | 950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 042 | CITY UNIVERSITY | HS048-013 | Renovation and HVAC Upgrade | MISCELLANEOUS RECONSTRUCTION | 100 101 | HN-0206 HN-D002 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RENOVATION AND HVAC UPGRADE | 2019 | 200 | 122.6 | 2500 | 0 | 0 | 77 | 0 | 0 | 2699.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 042 | CITY UNIVERSITY | HS050-014 | Allied Health and Sciences Building | MISCELLANEOUS RECONSTRUCTION | 100 101 | HN-D005 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ALLIED HEALTH AND SCIENCES BUILDING | 2019 | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 042 | CITY UNIVERSITY | HS054-017 | Create one Stop Center | MISCELLANEOUS RECONSTRUCTION | 100 | HN-X002 HN-D002 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CREATE ONE STOP CENTER | 2019 | 3850 | 0 | 0 | 3850 | 0 | 0 | 0 | 0 | 3850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 042 | CITY UNIVERSITY | HS055-018 | Lighting Electrical Upgrade | MISCELLANEOUS RECONSTRUCTION | 105 | HN-X002 |  |  | LIGHTING ELECTRICAL UPGRADE | 2019 | 375 | 0 | 0 | 375 | 0 | 0 | 0 | 0 | 375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 042 | CITY UNIVERSITY | HS056-018 | Upgrade Electrical service | MISCELLANEOUS RECONSTRUCTION | 105 | HN-X002 |  |  | LIGHTING ELECTRICAL UPGRADE | 2019 | 250 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 042 | CITY UNIVERSITY | HS057-019 | Smart Classroom Conversion | MISCELLANEOUS RECONSTRUCTION | 100 | HN-X002 HN-D002 |  |  | SMART CLASSROOM CONVERSION | 2019 | 1500 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 042 | CITY UNIVERSITY | HS058-019 | Basement Renovations at 500 Grand Concourse | MISCELLANEOUS RECONSTRUCTION | 100 | HN-D002 |  |  | BASEMENT RENOVATIONS AT 500 GRAND CONCOURSE | 2019 | 2000 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 042 | CITY UNIVERSITY | HS058-020 | 2nd Floor & Basement Renovation/Final Phase | MISCELLANEOUS RECONSTRUCTION | 105 | HN-X002 |  |  | 2ND FLOOR & BASEMENT RENOVATION/FINAL PHASE | 2019 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 042 | CITY UNIVERSITY | LM019-010 | Nursing Simulation Lab | MISCELLANEOUS RECONSTRUCTION | 100 | HN-D300 |  |  | NURSING SIMULATION LAB | 2019 | 246 | 0 | 246 | 0 | 0 | 0 | 0 | 0 | 246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 042 | CITY UNIVERSITY | LM019-011 | Concert Hall Lighting Upgrade / Acoustics Upgrade | MISCELLANEOUS RECONSTRUCTION | 100 107 | HN-X005 | PROJECT DELAYED DUE TO UNAVAILABILITY OF PRODUCT |  | LOCKER ROOM LOCKER REPLACEMENT | 2019 | 850 | 809.98 | 0 | 0 | 0 | 39 | 0 | 0 | 848.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 042 | CITY UNIVERSITY | LM029016 | Upgrade and Convert Carman Hall | MISCELLANEOUS RECONSTRUCTION | 107 | HN-X005 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | UPGRADE AND CONVERT CARMAN HALL | 2019 | 550 | 0 | 0 | 0 | 550 | 0 | 0 | 0 | 550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 042 | CITY UNIVERSITY | LM032-017 | Gillet Auditorium Renovation | MISCELLANEOUS RECONSTRUCTION | 100 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | GILLET AUDITORIUM RENOVATION | 2019 | 1700 | 0 | 0 | 0 | 0 | 1700 | 0 | 0 | 1700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 042 | CITY UNIVERSITY | LM034-018 | Convert classrooms into NetworkSmart Rooms | MISCELLANEOUS RECONSTRUCTION |  | HN-X300 |  |  | CONVERT CLASSROOMS INTO NETWORKSMART ROOMS | 2019 | 368 | 0 | 0 | 368 | 0 | 0 | 0 | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 042 | CITY UNIVERSITY | LM035-018 | Gillet Auditorium Renovation | MISCELLANEOUS RECONSTRUCTION | 100 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | GILLET AUDITORIUM RENOVATION | 2019 | 1866 | 0 | 0 | 0 | 0 | 1866 | 0 | 0 | 1866 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 042 | CITY UNIVERSITY | LM036-019 | Concert Hall Fixed Seating | MISCELLANEOUS RECONSTRUCTION | 105 | HN-X300 HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CONCERT HALL FIXED SEATING | 2019 | 1227 | 0 | 1200 | 0 | 0 | 27 | 0 | 0 | 1227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 042 | CITY UNIVERSITY | LM040-020 | Create A Teaching & Learning Innovation Space | MISCELLANEOUS RECONSTRUCTION | 105 | HN-X300 |  |  | CREATE A TEACHING & LEARNING INNOVATION SPACE | 2019 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 042 | CITY UNIVERSITY | LM041-020 | Studio Theatre Lighting & Dimming System | MISCELLANEOUS RECONSTRUCTION | 105 | HN-X300 |  |  | STUDIO THEATRE LIGHTING & DIMMING SYSTEM | 2019 | 0 | 0 | 0 | 175 | 0 | 0 | 0 | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAIC | MOUNTED UNIT INDOOR ARENA | POLICE FACILITIES | 100 | PO-0079 |  | BRONX | INDOOR RIDING ARENA | 2019 | 455 | 0 | 0 | 455 | 0 | 0 | 0 | 0 | 455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAJX | 46th PRECINCT ADA RAMP | POLICE FACILITIES | 100 | PO-0079 |  |  | 46TH ADA RAMP | 2019 | 325 | 0 | 325 | 0 | 0 | 0 | 0 | 0 | 325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAKD | RODMAN'S NECK BATHROOM TRAILERS | POLICE FACILITIES | 100 | PO-0079 |  |  | ESTIAMTE | 2019 | 116 | 0 | 116 | 0 | 0 | 0 | 0 | 0 | 116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAKE | RODMAN'S NECK BURN AND ADMINISTRATIVE OFFICE TRAILERS | POLICE FACILITIES | 100 | PO-0079 |  |  | ESTIMATE | 2019 | 844 | 0 | 149 | 695 | 0 | 0 | 0 | 0 | 844 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 056 | POLICE DEPARTMENT | POD47RENO | Renovate/Upgrade 47th Precinct. | POLICE FACILITIES | 100 | PO-D079 |  |  | RENOVATION | 2019 | 1000 | 64 | 0 | 936 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 056 | POLICE DEPARTMENT | POD50ELGE | 50TH PCT REPLACE ELEVATORS AND GENERATORS | POLICE FACILITIES | 108 | PO-D001 PO-0079 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | 3450 KINGSBRIDGE AV. BRONX | DUE TO A FIRE IN THE ELEVATOR SHAFT IT BECAME NECESSARY TO PROCEED WITH THE ELEVATOR PART OF THE PROJECT THROUGH AN EMERGENCY CONTRACT PROCESS USING NYPD INTERNAL CAPITAL FUNDING. THE GENERATOR PART OF THE PROJECT WAS DONE USING OTHER THAN CAPITAL FUNDING. | 2019 | 325 | 0 | 325 | 335 | 0 | 0 | 0 | 0 | 660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 057 | FIRE DEPARTMENT | F175KIT42 | KITCHEN REPLACEMENT - EC42 | NEW FACILITIES AND RENOVATIONS | 105 | F-0175 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES |  | KITCHEN REPLACEMENT | 2019 | 961 | 179.2 | 0 | 990 | 0 | 0 | 0 | 0 | 1169.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 057 | FIRE DEPARTMENT | F175KIT66 | KITCHEN REPLACEMENT - EC66 | NEW FACILITIES AND RENOVATIONS | 110 | F-0175 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | KITCHEN REPLACEMENT | 2019 | 961 | 860.81 | 583 | 0 | 0 | 0 | 0 | 0 | 1443.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 057 | FIRE DEPARTMENT | F175XIN82 | Exterior and Interior Renovations - EC 82 | NEW FACILITIES AND RENOVATIONS | 103 | F-0175 |  |  | EXTERIOR AND INTERIOR RENOVATIONS - EC 82 | 2019 | 4270 | 503.13 | 0 | 3850 | 0 | 0 | 0 | 0 | 4353.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 057 | FIRE DEPARTMENT | F1TELMPS2 | PSACII Telemetry | COMMUNICATIONS | 111 | F-0001 |  |  |  | 2019 | 6264 | 0 | 6220 | 0 | 0 | 0 | 0 | 0 | 6220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 057 | FIRE DEPARTMENT | FD175DE64 | Door Replacement - EC64 | NEW FACILITIES AND RENOVATIONS | 109 | F-D175 |  |  | DOOR REPLACEMENT - EC64 | 2019 | 150 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 057 | FIRE DEPARTMENT | FD175LROM | Lacation Room EMS Station - Boro -Bronx | NEW FACILITIES AND RENOVATIONS | 100 | F-D175 |  |  | LACATION ROOM EMS STATION - BORO -BRONX | 2019 | 100 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 057 | FIRE DEPARTMENT | FX175GE42 | Generator - EC42 | NEW FACILITIES AND RENOVATIONS |  | F-X175 |  |  | GENERATOR REPLACEMENT AT EC42. | 2019 | 0 | 0 | 0 | 375 | 0 | 0 | 0 | 0 | 375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 057 | FIRE DEPARTMENT | FX175WN46 | Window Replacement - EC46 | NEW FACILITIES AND RENOVATIONS |  | F-X175 |  |  | WINDOW REPLACEMENT AT EC46. | 2019 | 375 | 0 | 375 | 0 | 0 | 0 | 0 | 0 | 375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 057 | FIRE DEPARTMENT | FX175WN48 | Window Replacement EC48 | NEW FACILITIES AND RENOVATIONS | 105 | F-X175 |  |  | WINDOW REPLACEMENT AT ENGINE COMPANY 48 | 2019 | 250 | 0 | 210 | 0 | 0 | 0 | 0 | 0 | 210 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 068 | ADMIN FOR CHILDREN'S SERVICES | BEACH REP | Replacement Site for Beach Non-Secure Detention Site | SOCIAL SERVICE BUILDINGS |  | CS-0005 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  |  | 2019 | 6000 | 0 | 0 | 3664 | 2336 | 0 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 068 | ADMIN FOR CHILDREN'S SERVICES | BXELEVFAR | 1250 E229th Street Elevator and Fire Alarm Replacement | CHILD WELFARE FACILITIES | 112 | CS-0005 |  |  | 1250 E229TH STREET ELEVATOR AND FIRE ALARM REPLACEMENT. | 2019 | 0 | 0 | 0 | 358 | 0 | 0 | 0 | 0 | 358 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 068 | ADMIN FOR CHILDREN'S SERVICES | JJCONS | Adolescent Facility | CHILD WELFARE FACILITIES | 101 | CS-0005 |  | TBD | TBD | 2019 | 170000 | 0 | 0 | 104595 | 56038 | 13097 | 0 | 0 | 173730 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HH112FAFC | FRANKLIN'S WOMEN'S SHELTER - FACADE REHABILITATION | SHELTERS FOR HOMELESS INDIVIDUALS | 103 | HH-0112 |  |  | FRANKLIN'S WOMEN'S SHELTER - FACADE REHABILITATION | 2019 | 1693 | 0 | 0 | 0 | 0 | 135 | 0 | 1558 | 1693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HH115JEXT | UNIVERSITY AVENUE FAMILY FACAD | SHELTERS FOR HOMELESS FAMILIES |  | HH-0112 |  |  | FACADE AND WINDOWS | 2019 | 3600 | 0 | 0 | 0 | 0 | 300 | 0 | 3300 | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HH115NLBR | JAMAICA'S WOMENN'S SHELTER - BATHROOM RECONSTRUCTION | SHELTERS FOR HOMELESS FAMILIES |  | HH-0115 |  |  | JAMAICA WOMEN'S SHELTER - BATHROOM RECONSTRUCTION | 2019 | 3562 | 0 | 0 | 0 | 0 | 281 | 0 | 3281 | 3562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HH115SNRF | SENECA HOUSES - ROOF REPLACEMENT AND FACADE REHABILITATION | SHELTERS FOR HOMELESS FAMILIES | 102 | HH-0115 |  |  | SENECA HOUSES - ROOF REPLACEMENT AND FACADE REHABILITATION | 2019 | 730 | 58 | 0 | 0 | 672 | 0 | 0 | 0 | 730 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HH115UNBT | UNIVERSITY FAMILY KITCHEN BATHROOMS AND VENTILATION | SHELTERS FOR HOMELESS FAMILIES | 104 | HH-0115 |  |  | RECONSTRUCT KITCHENS BATHROOMS AND ASSOCIATED INTERNAL VENTILATION | 2019 | 2130 | 0 | 0 | 0 | 0 | 330 | 0 | 1800 | 2130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HH115UNEU | UNIVERSITY FAMILY RESIDENCE ROOF REPLACEMENT | SHELTERS FOR HOMELESS FAMILIES | 104 | HH-0115 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | RESTORATION OF ROOF AND FACADE AT THE UNIVERSITY AVENUE FAMILY RESIDENCE | 2019 | 1356 | 1194.46 | 0 | 0 | 0 | 150 | 0 | 1200 | 2544.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HH115UNFL | UNIVERSITY AVENUE FOUNDATION RECONSTRUCTION | SHELTERS FOR HOMELESS FAMILIES |  | HH-0112 |  |  | RECONSTRUCT BUILDING FOUNDATION | 2019 | 360 | 0 | 0 | 0 | 0 | 30 | 0 | 330 | 360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HHNC001 | NEW ERA VETERANS SRO- KITCHEN RENOVATION | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-D025 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NEW ERA VETERANS SRO- KITCHEN RENOVATION | 2019 | 400 | 0 | 100 | 300 | 0 | 0 | 0 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 072 | DEPARTMENT OF CORRECTION | C-101WEST | RI WEST PERIMETER EXTERIOR FENCING REPLACEMENT | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0075 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | REPLACE WEST PERIMETER FENCING | 2019 | 11147 | 15578.48 | 0 | 4973 | 0 | 0 | 0 | 0 | 20551.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 072 | DEPARTMENT OF CORRECTION | C130PANEL | REPLACEMENT OF ELECTRICAL DISTRIBUTION PANELS- RI POWERHOUSE | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0130 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | REPLACEMENT OF ELECTRICAL DISTRIBUTION PANELS AT RI POWERHOUSE | 2019 | 715 | 47.49 | 0 | 0 | 607 | 0 | 0 | 0 | 654.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138FEDER | NIC Power Feder Replacement | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0138 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | NIC POWER FEEDER REPLACEMENT. | 2019 | 1000 | 88.26 | 0 | 0 | 1123 | 0 | 0 | 0 | 1211.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138FSPH2 | Fire Life Safety Phase II | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0138 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | FIRE LIFE SAFETY PHASE II AT ALL DOC RIKERS AND BOROUGH FACILITIES | 2019 | 80849 | 0 | 0 | 64247 | 0 | 0 | 0 | 0 | 64247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138FSYS | FIRE SAFETY SYSTEM CONSTRUCTION | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0138 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | FABRICATE AND INTEGRATE FIRE SAFETY SYSTEMS | 2019 | 24000 | 26475.92 | 0 | 9000 | 0 | 0 | 0 | 0 | 35475.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138GRFS2 | GRVC - Fire Life Safety Phase II | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0138 |  |  | GRVC FIRE LIFE SAFETY PHASE II | 2019 | 20469 | 109.9 | 966 | 19008 | 0 | 0 | 0 | 0 | 20083.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138NCFS2 | Fire Life Safety Phase II for NIC Annex | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0138 |  |  | FIRE LIFE SAFETY PHASE II FOR NIC ANNEX | 2019 | 11872 | 103.43 | 622 | 9280 | 0 | 0 | 0 | 0 | 10005.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138OBFS2 | OBCC Main Fire Life Safety Phase II | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0138 |  |  | AFTER COMPLETING THE FIRE ALARM SYSTEMS THE DEPARTMENT WILL NEED TO UPGRADE FIRE PROTECTION SYSTEMS IN ALL DEPARTMENTAL FACILITIES. THIS REQUEST IS BEING MADE TO UPGRADE THE FACILITIES TO 1993 CONSENSUS PLAN AS THE REQUIREMENT BEING IMPOSED BY THROUGH THE BENJAMIN COURT APPOINTED CONSULTANT IS MUCH HIGHER AND COST PROHIBITIVE. AT THIS TIME WE ARE SUGGESTING TO INSTALL ITEMS PREVIOUSLY AGREED WITH FDNY. | 2019 | 25484 | 128.3 | 0 | 21878 | 0 | 0 | 0 | 0 | 22006.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138PROB3 | POST FIRE PURGE SYSTEM UPGRADE AT OBCC 300 BED ADDITION | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0138 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | POST FIRE PURGE SYSTEM UPGRADE AT OBCC 300 BED ADDITION. | 2019 | 1375 | 198.12 | 1730 | 0 | 0 | 0 | 0 | 0 | 1928.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138PURGR | POST FIRE PURGE SYSTEM AT GRVC | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0138 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | POST FORE PURGE SYSTEM FOR 200 AND 300 BED ADDITIONS GRVC | 2019 | 1800 | 235.58 | 0 | 1400 | 0 | 0 | 0 | 0 | 1635.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138PWRHS | DESIGN AND INSTALL FIRE ALARM SYSTEM AT EXISTING POWERHOUSE | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0138 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | DESIGN AND INSTALL FIRE ALARM SYSTEM AT EXISTING POWERHOUSE | 2019 | 2240 | 205 | 0 | 1800 | 0 | 0 | 0 | 0 | 2005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138RMFS2 | RMSC - Fire Life Safety Phase II | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0138 |  |  | AFTER COMPLETING THE FIRE ALARM SYSTEMS THE DEPARTMENT WILL NEED TO UPGRADE FIRE PROTECTION SYSTEMS IN ALL DEPARTMENTAL FACILITIES. THIS REQUEST IS BEING MADE TO UPGRADE THE FACILITIES TO 1993 CONSENSUS PLAN AS THE REQUIREMENT BEING IMPOSED BY THROUGH THE BENJAMIN COURT APPOINTED CONSULTANT IS MUCH HIGHER AND COST PROHIBITIVE. AT THIS TIME WE ARE SUGGESTING TO INSTALL ITEMS PREVIOUSLY AGREED WITH FDNY. THESE SYSTEMS ARE IN VARYING DEGREE OF DETERIORATED CONDITIONS AND MUST BE UPGRADED FOR THE SAFE OCCUPANCY OF OUR FACILITIES. | 2019 | 3570 | 26.98 | 173 | 2805 | 0 | 0 | 0 | 0 | 3004.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138TRANS | DESIGN AND INSTALL FIRE ALARM SYSTEM AT TRANSPORTATION DIV | BUILDING SYSTEMS AND INFRASTRUCTURE |  | C-0138 |  |  | DESIGN AND INSTALL FIRE ALARM SYSTEM AT TRANSPORTATION DIVISION | 2019 | 4380 | 196.51 | 2602 | 1206 | 0 | 0 | 0 | 0 | 4004.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138VCFS2 | VCBC Fire Life Safety Phase II | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0138 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | AFTER COMPLETING THE FIRE ALARM SYSTEMS THE DEPARTMENT WILL NEED TO UPGRADE FIRE PROTECTION SYSTEMS IN ALL DEPARTMENTAL FACILITIES. THIS REQUEST IS BEING MADE TO UPGRADE THE FACILITIES TO 1993 CONSENSUS PLAN AS THE REQUIREMENT BEING IMPOSED BY THROUGH THE BENJAMIN COURT APPOINTED CONSULTANT IS MUCH HIGHER AND COST PROHIBITIVE. AT THIS TIME WE ARE SUGGESTING TO INSTALL ITEMS PREVIOUSLY AGREED WITH FDNY. | 2019 | 2845 | 83.18 | 1327 | 173 | 29874 | 0 | 0 | 0 | 31457.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ADACOM | ADA COMPLIANCE FOR NIC, CENTRAL VISITS, FACILITY VISIT AREAS | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0075 |  |  | ADA COMPLIANCE FOR NIC, CENTRAL VISITS, AND FACILITY VISIT AREAS | 2019 | 33738 | 0 | 0 | 1280 | 0 | 0 | 0 | 0 | 1280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ADACVT | ADA Compliance for Central Visits | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0075 |  |  | ADA COMPLIANCE FOR CENTRAL VISITS | 2019 | 10326 | 197.79 | 444 | 8792 | 0 | 0 | 0 | 0 | 9433.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ADAGRV | ADA Compliance for GRVC | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0075 |  |  | ADA COMPLIANCE FOR GRVC | 2019 | 5679 | 31.59 | 272 | 4434 | 0 | 0 | 0 | 0 | 4737.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ADANIC | NIC SHOWER RECONSTRUCTION DORMS 3/4 TO COMPLY WITH ADA | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0075 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | RECONSTRUCTION OF NIC DORMS 3 &4 TO ENSURE COMPLIANCE WITH THE AMERICANS WITH DISABILITIES ACT (ADA). | 2019 | 200 | 260.61 | 344 | 4600 | 0 | 0 | 0 | 0 | 5204.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ADARMS | ADA Compliance for RMSC | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0075 |  |  | ADA COMPLIANCE FOR RMSC | 2019 | 6352 | 68.05 | 284 | 5000 | 0 | 0 | 0 | 0 | 5352.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ADAVCB | ADA Compliance for VCBC | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0075 |  |  | ADA COMPLIANCE FOR VCBC | 2019 | 3425 | 92.53 | 1139 | 0 | 13600 | 0 | 0 | 0 | 14831.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ASBEST | Asbestos Abatement and Air Monitoring - Various Facilities | BUILDING SYSTEMS AND INFRASTRUCTURE |  | C-0075 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | REMOVAL OF ASBESTOS CONTAINING MATERIALS. | 2019 | 12210 | 8445.28 | 1256 | 0 | 568 | 0 | 0 | 10410 | 20679.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75CELLD | Electronic Cell Door Panels at All Facilities | BUILDING SYSTEMS AND INFRASTRUCTURE |  | C-0075 |  |  | ELECTRONIC CELL DOOR PANELS AT ALL FACILITIES TO FIX NON-OPERABLE DOORS | 2019 | 6900 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75DDECT | Drug Detection Machines | EQUIPMENT | 100 | C-0075 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | DRUG DETECTION MACHINES | 2019 | 3100 | 684.09 | 1455 | 1 | 0 | 0 | 0 | 0 | 2140.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75-ELEV | ELEVATOR REHAB VARIOUS FACILITIES | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0075 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | RIKERS ISLAND BRONX | RECONSTRUCTION OF PASSENGER/FREIGHT ELEVATOR SERVING 3 FLOORS IN THEADMINISTRATION BUILDING INCLUDING ALL CONTROLS AND THE ENTIRE HYDRAULISYSTEM | 2019 | 4556 | 3146.92 | 0 | 8500 | 5000 | 0 | 0 | 0 | 16646.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ENTGRV | Modification of Facility Entrance-GRVC | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0075 |  |  | MODIFICATION OF FACILITY ENTRANCE-GRVC | 2019 | 7946 | 44.57 | 410 | 7301 | 0 | 0 | 0 | 0 | 7755.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ENTNC | Modification for Facility Entries - NIC | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0075 |  |  | MODIFICATION FOR FACILITY ENTRIES - NIC | 2019 | 4131 | 73.79 | 272 | 3685 | 0 | 0 | 0 | 0 | 4030.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ENTOBC | Modification for Facility Entries - OBCC | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0075 |  |  | MODIFICATION FOR FACILITY ENTRIES - OBCC | 2019 | 8651 | 69.3 | 0 | 7952 | 0 | 0 | 0 | 0 | 8021.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ENTRMS | Modification of Facility Entry at RMSC | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0075 |  |  | MODIFICATION OF FACILITY ENTRIES - RMSC | 2019 | 8070 | 55.88 | 400 | 7426 | 0 | 0 | 0 | 0 | 7881.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ENTRY | MODIFICATION OF FACILITY ENTRIES | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0075 |  |  | MODIFICATION OF FACILITY ENTRIES | 2019 | 83920 | 1031.63 | 0 | 11597 | 0 | 0 | 0 | 0 | 12628.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ENTVCB | Modification of Facility Entry at VCBC | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0075 |  |  | MODIFICATION OF FACILITY ENTRY AT VCBC | 2019 | 4305 | 117.14 | 51 | 82 | 588 | 0 | 0 | 0 | 838.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ESUCP | New ESU Compound at Rikers Island | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0075 |  |  | NEW ESU COMPOUND AT RIKERS ISLAND | 2019 | 0 | 0 | 656 | 10344 | 0 | 0 | 0 | 0 | 11000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75FENCE1 | FENCING RECONSTRUCTION | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0075 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | INTERIOR PERIMETER FENCE REPLACEMENT @ VAR. FAC. | 2019 | 3311 | 8714.19 | 2982 | 512 | 0 | 2000 | 2000 | 0 | 16208.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75-GCELL | GANG CELL DOOR RELEASE | BUILDING SYSTEMS AND INFRASTRUCTURE | 101 | C-0075 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | RECONSTRUCT GANG DOORS NOT CURRENTLY SERVED BY ELECTRICAL RELEASE SYSTEMS | 2019 | 4000 | 0 | 0 | 1000 | 1000 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75GRVCHV | GRVC HVAC Upgrades and Related Housing Area Renovations | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0075 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | GRVC (GROUP A) HEATING, VENTILATION AND RELATED SYSTEM COMPONENTS AT ALL DOC FACILITIES ARE IN VARYING DEGREE OF DETERIORATION AS THE SYSTEMS ARE 25 PLUS YEARS OLD AND ARE REACHING AT THE END OF ITS USEFUL LIFE. ADDITIONALLY, DUE TO THE CONTINUOUS OPERATION (24/7) THE SYSTEM'S LIFE SPAN SHORTENS AS SERVICING OF SUCH A SYSTEM OFTEN BECOMES VERY DIFFICULT. THIS PROPOSED PROJECT WILL PERFORM SYSTEMIC AND COMPREHENSIVEEXAMINATION OF ALL VENTILATION, HEATING AND COOLING SYSTEM COMPONENTS. | 2019 | 16717 | 199.36 | 897 | 18040 | 0 | 0 | 0 | 0 | 19136.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75GRVRFW | GRVC Roof Replacement, Exterior Facades, Windows, Court Yard | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0075 |  |  | ALL OF THE DOC FACILITIES ARE 25+ YEARS OLD AND EXTERIOR ENVELOPE SHOWS SIGN OF DETERIORATION WHICH NEEDS FIXING BEFORE CONDITIONS GET BAD WHICH CAN FURTHER DAMAGE THE INTERIOR BUILDING SYSTEM INFRASTRUCTURE.THIS NEW NEEDS ACKNOWLEGES EXISTING FUNDS FOR SIMILAR PROJECTS IN THEAMOUNT OF $53,956,000. THIS REQUEST IS IN ADDITION TO THE EXISTING FUNDS. FOLLOWED BY INSPECTION PHASE A REHABILITATION PLAN AND PRIORITIES WILL BE DEVELOPED FOR DESIGN AND CONSTRUCTION PHASE. | 2019 | 10800 | 896.93 | 0 | 16000 | 0 | 0 | 0 | 0 | 16896.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75IDTRAL | INVESTIGATION TRAILER | SUPPORT SPACE | 100 | C-0075 |  |  | INVESTIGATION TRAILER | 2019 | 921 | 0 | 0 | 767 | 0 | 0 | 0 | 0 | 767 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75K9UNIT | New K 9 Facility at Rikers Island | SUPPORT SPACE | 100 | C-0075 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CONSTRUCT NEW K9 UNIT WITH REQUIRED OFFICES AND SUPPOTY SPACES. | 2019 | 3650 | 573 | 1464 | 1000 | 0 | 0 | 0 | 0 | 3037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75LAUNRF | Central Laundry /Bakery Roof Replacement | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0075 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CENTRAL LAUNDRY ROOF IS DETERIORATING AND LEAKING. NEEDS REPLACEMENT. | 2019 | 968 | 2909.59 | 0 | 163 | 0 | 0 | 0 | 0 | 3072.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75LTVCBC | REHABILITATION LIGHTING PANELS AT VCBC | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0075 |  |  | REHABILITATION LIGHTING PANELS AT VCBC | 2019 | 550 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75-METH | Methane Detection System Replacement and Central Monitoring | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0075 |  |  | METHANE SYSTEM REPLACEMENT AND CENTRAL MONITORING | 2019 | 6197 | 454.24 | 766 | 743 | 11988 | 0 | 0 | 0 | 13951.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75NICADA | NIC Annex Shower-2010 ADA Compliance-Dorm 1& 2B | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0075 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | NIC ANNEX SHOWER-2010 ADA COMPLIANCE-DORM 1& 2B | 2019 | 960 | 22.12 | 0 | 783 | 0 | 0 | 0 | 0 | 805.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75NICFAC | ROOF & FACADE RECONSTRUCTION FOR MAIN AND ANNEX | BUILDING SYSTEMS AND INFRASTRUCTURE | 101 | C-0075 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | ROOF & FACADE RESTORATIONS FOR MAIN AND ANNEX | 2019 | 6248 | 376.23 | 182 | 5044 | 0 | 0 | 0 | 0 | 5602.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75OBCCAT | HV & ATC UPGRADE AT OBCC | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0075 |  |  | HV AND ATC UPGRADE AT OBCC | 2019 | 9600 | 0 | 0 | 8000 | 0 | 0 | 0 | 0 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75OBCHV | OBCC AHU,Duct Work,Heating,Ventilation & Cooling Equipment | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0075 |  |  | OBCC MAIN (GROUP A) HEATING, VENTILATION AND RELATED SYSTEM COMPONENTS AT ALL DOC FACILITIES ARE IN VARYING DEGREE OF DETERIORATION AS THE SYSTEMS ARE 25 PLUS YEARS OLD AND ARE REACHING AT THE END OF ITS USEFUL LIFE. ADDITIONALLY, DUE TO THE CONTINUOUS OPERATION (24/7) THE SYSTEM'S LIFE SPAN SHORTENS AS SERVICING OF SUCH A SYSTEM OFTEN BECOMES VERY DIFFICULT. THIS PROPOSED PROJECT WILL PERFORM SYSTEMIC AND COMPREHENSIVE EXAMINATION OF ALL VENTILATION, HEATING AND COOLING SYSTEM COMPONENTS. | 2019 | 9500 | 46.39 | 0 | 7957 | 0 | 0 | 0 | 0 | 8003.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75OBCRFW | OBCC Roof Replacement, Exterior Facades, Windows, Court Yard | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0075 |  |  | LL OF THE DOC FACILITIES ARE 25+ YEARS OLD AND EXTERIOR ENVELOPE SHOWS SIGN OF DETERIORATION WHICH NEEDS FIXING BEFORE CONDITIONS GET BAD WHICH CAN FURTHER DAMAGE THE INTERIOR BUILDING SYSTEM INFRASTRUCTURE. THIS NEW NEEDS ACKNOWLEGES EXISTING FUNDS FOR SIMILAR PROJECTS IN THE AMOUNT OF $53,956,000. THIS REQUEST IS IN ADDITION TO THE EXISTING FUNDS. FOLLOWED BY INSPECTION PHASE A REHABILITATION PLAN AND PRIORITIES WILL BE DEVELOPED FOR DESIGN AND CONSTRUCTION PHASE. | 2019 | 18000 | 815.87 | 0 | 14184 | 0 | 0 | 0 | 0 | 14999.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75PTREAT | Water Treatment for Powerhouse | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0075 |  |  | WATER TREATMENT FOR POWERHOUSE | 2019 | 8203 | 467.82 | 0 | 6743 | 0 | 0 | 0 | 0 | 7210.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75RDSRNG | New Modular Trailers and Classroom Renovation- Rodman's Neck | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0075 |  |  | NEW MODULAR TRAILERS AND CLASSROOM RENOVATION | 2019 | 3116 | 0 | 8989 | 0 | 0 | 0 | 0 | 0 | 8989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75RMPWR | RMSC Power Upgrades for buildings 1,2,3,4,5,6 & 7 | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0075 |  |  | RMSC POWER UPGRADES FOR BUILDINGS 1,2,3,4,5,6 & 7 | 2019 | 10220 | 65.8 | 479 | 9460 | 0 | 0 | 0 | 0 | 10004.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75RMS-AC | RMSC A/C Power Upgrades for Bldgs 1,2,3,4,5,6 and 7 | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0075 |  |  | A/C AND POWER UPGRADES FOR BUILDINGS 1,2,3,4,5,6 AND 7 | 2019 | 23750 | 123.6 | 829 | 19049 | 0 | 0 | 0 | 0 | 20001.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75RMSCHV | RMSC AHU,Duct Work,Heating,Ventilation & Cooling Equipment | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0075 |  |  | RMSC (GROUP A) HEATING, VENTILATION AND RELATED SYSTEM COMPONENTS AT ALL DOC FACILITIES ARE IN VARYING DEGREE OF DETERIORATION AS THE SYSTEMS ARE 25 PLUS YEARS OLD AND ARE REACHING AT THE END OF ITS USEFUL LIFE. ADDITIONALLY, DUE TO THE CONTINUOUS OPERATION (24/7) THE SYSTEM'S LIFE SPAN SHORTENS AS SERVICING OF SUCH A SYSTEM OFTEN BECOMES VERY DIFFICULT. THIS PROPOSED PROJECT WILL PERFORM SYSTEMIC AND COMPREHENSIVEEXAMINATION OF ALL VENTILATION, HEATING AND COOLING SYSTEM COMPONENTS. | 2019 | 12336 | 73.04 | 575 | 11352 | 0 | 0 | 0 | 0 | 12000.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75RMSRFW | RMSC Roof Replacement, Exterior Facades, Windows, Court Yard | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0075 |  |  | ALL OF THE DOC FACILITIES ARE 25+ YEARS OLD AND EXTERIOR ENVELOPE SHOWS SIGN OF DETERIORATION WHICH NEEDS FIXING BEFORE CONDITIONS GET BAD WHICH CAN FURTHER DAMAGE THE INTERIOR BUILDING SYSTEM INFRASTRUCTURE.THIS NEW NEEDS ACKNOWLEGES EXISTING FUNDS FOR SIMILAR PROJECTS IN THEAMOUNT OF $53,956,000. THIS REQUEST IS IN ADDITION TO THE EXISTING FUNDS. FOLLOWED BY INSPECTION PHASE A REHABILITATION PLAN AND PRIORITIES WILL BE DEVELOPED FOR DESIGN AND CONSTRUCTION PHASE. | 2019 | 13090 | 897.19 | 0 | 16006 | 0 | 0 | 0 | 0 | 16903.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ROOFS | ROOF REPLACEMENT AT ALL RI FACILITIES | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0075 |  | 15-15 HAZEN ST,19-19 HAZEN ST., 11-11 HAZEN ST., 09-09 HAZEN ST., 15-00 HAZEN ST., RIKERS ISLAND | ROOFS NEED TO BE REFURBISHED | 2019 | 14728 | 8718.66 | 0 | 2392 | 0 | 0 | 0 | 0 | 11110.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75SEAWLL | Construction of Sea Wall and Raising of Madanici Road | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0075 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | THE RAISING OF MANDANICI ROAD IS REQUIRED AS THE ROAD OFTEN GETS FLOODED DURING INCLEMENT WEATHER CUTTING OFF TRAFFIC BETWEEN THE EASTSIDE FACILITIES AND HAZEN STREET. THE BUILDING OF THE SEA WALL IS REQUIRED TO PROTECT THE COGEN POWER PLANT FROM STORM SURGES OR FLOODING. | 2019 | 7017 | 649.97 | 0 | 5850 | 0 | 0 | 0 | 0 | 6499.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75STDRN | Replace Storm Water Mains and Outfalls | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0075 |  |  | REPLACE STORM WATER DRAINS ,MAINS AND OUTFALLS AT RIKERS ISLAND. | 2019 | 6000 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75STEAM | Upgrade Steam Lines | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0075 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | STEAM LINES UPGRADE. | 2019 | 6000 | 466.83 | 0 | 0 | 4534 | 0 | 0 | 0 | 5000.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75SUPFC | Exterior Reconstruction for Support Facilities | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0075 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | ALL SUPPORT FACILITIES ARE 25 + YEARS OLD AND HAVE SIGNIFICANT DETERIORATION TO THE EXTERIOR ELEMENTS OF THESE PERMANENT STRUCTURES. THIS WORK RELATES TO PROVIDING SAFE AND SECURED ENVIRONMENT FOR DELIVERINGVARIOUS SUPPORT FUNCTIONS TO ALL JAIL FACILITIES. | 2019 | 5800 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75SWITCH | REPLACEMENT OF ELECTRICAL AUTOMATIC TRANSFER SWITCHES | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0075 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | REPLACEMENT OF ELECTRICAL AUTOMATIC TRANSFER SWITCHES | 2019 | 6600 | 378.16 | 0 | 5122 | 0 | 0 | 0 | 0 | 5500.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75TMTRLR | Design and Installation of new Teams Modular Building | SUPPORT SPACE | 100 | C-0075 |  |  | DESIGN AND CONSTRUCTION WORK FOR NEW TEAMS MEETING MODULAR BUILDINGS AT RIKERS ISLAND. | 2019 | 6532 | 0 | 5842 | 0 | 0 | 0 | 0 | 0 | 5842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75TURB | REPLACEMENT OF CO-GENERATION PLANT TURBINES | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0075 |  |  | REPLACEMENT OF CO-GENERATION PLANT TURBINES | 2019 | 6120 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75VCATC | AHU and ATC Replacement at VCBC | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0075 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | REPLACEMENT OF AHU'S AND AUTOMATIC TEMPERATURE CONTROLS. | 2019 | 6550 | 12197.02 | 0 | 114 | 0 | 0 | 0 | 0 | 12311.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75VCBCGC | VCBC Gang Cell Door Release | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0075 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | VCBC GANGE CELL DOOR RELEASE | 2019 | 3000 | 245.09 | 0 | 2320 | 0 | 0 | 0 | 0 | 2565.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75VCRMP | VCBC Ramp and Site Rehabilitation | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0075 |  |  | VCBC RAMP AND SITE REHABILITATION | 2019 | 11325 | 0 | 727 | 0 | 10571 | 0 | 0 | 0 | 11298 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75VCROOF | VCBC ROOF REPLACEMENT | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0075 |  |  | VCBC ROOF REPLACEMENT | 2019 | 2400 | 0 | 0 | 2400 | 0 | 0 | 0 | 0 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75VLAUND | VCBC Laundry System Installation | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0075 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | VCBC LAUNDRY SYSTEM INSTALLATION | 2019 | 400 | 38.89 | 1656 | 0 | 0 | 0 | 0 | 0 | 1694.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75VRISER | Replacement of Chilled Water Risers at VCBC | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0075 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | REPLACEMENT OF 3-10" CHILLED WATER RISERS | 2019 | 901 | 113.37 | 0 | 4726 | 0 | 0 | 0 | 0 | 4839.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 072 | DEPARTMENT OF CORRECTION | E16-0020 | DOC- VERNON C. BAIN CENTER Lighting & HVAC | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 109 | PU-0025 |  |  | COMPREHENSIVE LIGHTING AND HVAC | 2019 | 7154 | 456.73 | 0 | 2374 | 0 | 0 | 0 | 0 | 2830.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDAMKC | Hurricane Sandy - AMKC Roof Reconstruction | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0075 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | ROOF RECONSTRUCTION AT AMKC REQUIRED DUE TO DAMAGE FROM HURRICANE SANDY. ROOF RECONSTRUCTION WILL BE NECESSARY AT THE FOLLOWING AMIKC LOCATIONS: AMKC BUILDING 3, AMKC BUILDING 2 (HOUSING WING 2 AND HOUSING WING 7), THE ROOF OF AMKC MECHANICAL ROOM IN THE AMKC MAIN BUILDING AND ASSOCIATED CORRIDORS. | 2019 | 2375 | 1463.02 | 0 | 0 | 0 | 0 | 0 | 0 | 1463.02 | 4121.88 | 220 | 0 | 0 | 0 | 0 | 0 | 4341.88
20190425 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDCONDT | Hurricane Sandy Underground Conduits at VCBC | BUILDING SYSTEMS AND INFRASTRUCTURE |  | C-0075 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | HURRICANE SANDY UNDERGROUND CONDUITS AT VCBC | 2019 | 14596 | 0 | 0 | 1219 | 0 | 0 | 0 | 0 | 1219 | 0 | 2250 | 8727 | 0 | 0 | 0 | 0 | 10977
20190425 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDHART | Hurricane Sandy-harts island Reconstruct from storm damage | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0075 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | HURRICANE SANDY-HARTS ISLAND RECONSTRUCT FROM STORM DAMAGE | 2019 | 8749 | 113.84 | 508 | 701 | 0 | 0 | 0 | 0 | 1322.84 | 1024.56 | 10879 | 0 | 0 | 0 | 0 | 0 | 11903.56
20190425 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDRNDC | Hurricane Sandy - RNDC Roof Reconstruction | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0075 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | FUNDING IS REQUIRED TO REPLACE TWO AREAS OF THE ROOF OF RNDC BUILDINGDAMAGED BY HURRICANE SANDY. THE REPLACEMENT WORK IS NEEDED AT THE GYMROOF AND THE ROOF OF THE SOUTHEAST CORNER OF THE ADMINISTRATIVE BUILDING ROOF . | 2019 | 11396 | 243.69 | 0 | 0 | 0 | 0 | 0 | 0 | 243.69 | 2193.24 | 217 | 0 | 0 | 0 | 0 | 0 | 2410.24
20190425 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDSHORE | Hurricane Sandy- RI NShoreline Reconstruct from Storm Damage | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0075 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | RECONSTRUCTION OF RI NORTH SHORELINE DUE TO EXTENSIVE DAMAGE FROM HURRICANE SANDY. | 2019 | 33492 | 1053.59 | 244 | 3843 | 0 | 0 | 0 | 0 | 5140.59 | 7683.99 | 40165 | 0 | 0 | 0 | 0 | 0 | 47848.99
20190425 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDVCBC | Hurricane Sandy - VCBC Reconstruction Due To Storm Damage | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0075 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | ENGINEERING ASSESMENT DESIGN AND RECONSTRUCTION AREAS DAMAGED AT VCBCINCLUDING MOORING ARMS. ELECTRICAL PARKING LOT, FENCING, AND ROADWAY. | 2019 | 2940 | 24.02 | 0 | 264 | 0 | 0 | 0 | 0 | 288.02 | 216.31 | 2376 | 0 | 0 | 0 | 0 | 0 | 2592.31
20190425 | BRONX | 125 | DEPARTMENT FOR THE AGING | AGERMACAV | ERMA -CAVA Senior Center HVAC Upgrade | DEPARTMENT FOR THE AGING BUILDING RECONSTRUCTION | 102 | AG-D001 |  |  | SEPT 18 PLAN 100K HVAC SYSTEM UPGRADE ERMA -CAVA SENIOR CENTER HVAC UPGRADE | 2019 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 125 | DEPARTMENT FOR THE AGING | AGHOGAR | HOGAR SENIOR CENTER--HOGAR SENIOR CENTER RENOVATIONS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 109 | AG-D001 |  |  | SENIOR CENTER RENOVATIONS | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | ACEDCA433 | DCLA: Wildlife Conservation Society: Bronx Zoo Roofs | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 107 | PU-0025 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ROOF REPLACEMENT FOR THE AQUATIC BIRD HOUSE BUILDING AT THE BRONX ZOO. NEW ROOF WILL USE ENERGY EFFICIENT MATERIALS INCL. UP TO 4 INCHES OF INSULATION. | 2019 | 688 | 0 | 0 | 688 | 0 | 0 | 0 | 0 | 688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176-BLR | WCS BRONX ZOO - Boiler Replacement Various Bldgs. | ESSENTIAL RECONSTRUCTION OF FACILITIES | 106 | PV-0176 PV-D176 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | BX ZOO 2300 SOUTHERN BLVD., BRONX NY | REPLACEMENT OF BOILERS IN ZOO BUILDINGS. | 2019 | 5500 | 0 | 0 | 0 | 0 | 3146 | 0 | 0 | 3146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176GELA | WCS - Bronx Zoo - Gelada Exhibit | ESSENTIAL RECONSTRUCTION OF FACILITIES | 106 | PV-X176 PV-D176 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | GELADA PROPAGATION ANNEX TO HOUSE A NEW GROUP FO GELADA BABOONS | 2019 | 1500 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176-REP | WCS - Bronx Zoo - Reptile House Facade Restoration | ESSENTIAL RECONSTRUCTION OF FACILITIES | 106 | PV-X176 PV-D176 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | WCS - BRONX ZOO | 2019 | 1872 | 0 | 0 | 0 | 0 | 1872 | 0 | 0 | 1872 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176WILD | WCS Bronx Zoo - Wildlife Exhibit Center | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | PV-X176 |  |  | WCS BRONX ZOO - WILDLIFE EXHIBIT CENTER | 2019 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV205LIFT | NYBG - Boom Lift | CAPITAL EQUIPMENT | 106 | PV-D205 |  |  |  | 2019 | 140 | 0 | 0 | 0 | 0 | 140 | 0 | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV205WOC | NYBG - Worker's Operation Center Renovation | ESSENTIAL RECONSTRUCTION OF FACILITIES | 106 | PV-D205 PV-0205 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | 2300 SOUTHERN BLVD. BRONX NY | CREATION AND REVOVATION OF WORKERS OPERATION CENTER | 2019 | 5820 | 0 | 0 | 0 | 0 | 0 | 10320 | 0 | 10320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV293-EXT | BCHS - Exterior/Interior Rehab and Tech Upgrade | ESSENTIAL RECONSTRUCTION OF FACILITIES | 107 | PV-X293 PV-D467 |  |  | BRONX COUNTY HISTORICAL SOCIETY  EXTERIOR/INTERIOR REHAB & TECHNOLOGY | 2019 | 198 | 0 | 0 | 0 | 0 | 0 | 198 | 0 | 198 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV464GLYN | WH - Wave Hill - Glyndor Hse. Boiler/Armor Hall AHU | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | PV-D464 PV-X464 PV-0464 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 675 WEST 254TH STREET, BRONX, NY | BOILER REPLACEMENT | 2019 | 987 | 0 | 0 | 0 | 94 | 0 | 1067 | 0 | 1161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV464SITE | WH - Wave Hill - Sitewide Pathway Replacement | ESSENTIAL RECONSTRUCTION OF FACILITIES | 108 | PV-D464 PV-0464 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 675 WEST 252ND STREET. BRONX, NY | SITE WIDE PATHWAY REPLACEMENT | 2019 | 550 | 0 | 0 | 0 | 0 | 0 | 2300 | 0 | 2300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467SWAW | Spaceworks Artist Workspace at Arthur Avenue Bergen Bldg | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | PV-0467 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CONSTRUCTION OF ARTIST WORKSPACE | 2019 | 3600 | 0 | 0 | 0 | 0 | 2200 | 0 | 0 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | AAMARKADA | Arthur Avenue Retail Market ADA Compliant Restrooms | MARKET DEVELOPMENT | 100 | ED-0408 |  |  | ARTHUR AVENUE RETAIL MARKET ADA COMPLIANT RESTROOMS - DE BLASIO TOWN HALL PROMISE | 2019 | 540 | 0 | 0 | 0 | 0 | 54 | 486 | 0 | 540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | AAMARKREN | Arthur Avenue Market Renovations | MARKET DEVELOPMENT | 100 | ED-X075 |  |  | ARTHUR AVENUE MARKET RENOVATIONS | 2019 | 1000 | 0 | 0 | 0 | 0 | 100 | 900 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | AARMRENO | Arthur Avenue Retail Market - Renovation -- Funds will renov | MISCELLANEOUS | 100 | ED-D408 |  |  | ARTHUR AVENUE RETAIL MARKET - RENOVATION -- FUNDS WILL RENOVATE THE ARTHUR AVENUE RETAIL MARKET | 2019 | 0 | 0 | 0 | 0 | 0 | 108 | 0 | 0 | 108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | AGDRAIN | FA - Rain Senior Center Renovation | DEPARTMENT FOR THE AGING BUILDING RECONSTRUCTION | 112 | AG-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RAIN SENIOR CENTER RENOVATION | 2019 | 100 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | ALTFUELS | Hunts Point Alternative Fueling Station | MISCELLANEOUS | 100 | ED-0075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | HUNTS POINT ALTERNATIVE FUELING STATION | 2019 | 1000 | 5449.11 | 551 | 0 | 0 | 0 | 0 | 0 | 6000.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | EDXHPGEN | Hunts Point Cooperative Market | MARKET DEVELOPMENT | 100 | ED-D408 |  |  | HUNTS POINT COOPERATIVE MARKET - TO PURCHASE TWO NEW GENERATORS | 2019 | 3450 | 0 | 2238 | 1212 | 0 | 0 | 0 | 0 | 3450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | FFMDRAIN | New Fulton Fish Market -- Facility Upgrades: New Drainage Sy | MISCELLANEOUS | 100 | ED-D408 |  |  | NEW FULTON FISH MARKET -- FACILITY UPGRADES: NEW DRAINAGE SYSTEM | 2019 | 0 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | FREIGHTHP | Freight NYC - Hunts Point Marine Highway | PORT DEVELOPMENT | 100 | ED-0404 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | FREIGHT NYC - HUNTS POINT MARINE HIGHWAY - 100K JOBS | 2019 | 25000 | 0 | 0 | 0 | 0 | 9000 | 2500 | 13500 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | GXHP07-02 | GI - DSGN & CONS OF ROW BIOSWALES & GREENSTREETS IN HP-007 | GREEN INFRASTRUCTURE PROGRAM | 112 | WP-0169 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | GI - DESIGN AND CONSTRUCTION OF RIGHTOF WAY BIOSWALES AND STORMAWATERGREENSTREETS AT CSO TRIBUTARY AREA HP-007 IN THE BRONX | 2019 | 23154 | 15041.59 | 8762 | 21000 | 0 | 0 | 0 | 0 | 44803.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | GXHP14-01 | GI - Green infrastructure in Westchester Creek HP-14 | GREEN INFRASTRUCTURE PROGRAM | 112 | WP-0169 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | GI - GREEN INFRASTRUCTURE IN WESTCHESTER CREEK HP-14 | 2019 | 41898 | 16007.84 | 10769 | 0 | 15122 | 0 | 0 | 0 | 41898.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | GXHP16-01 | GI - Green infrastructure in Westchester Creek HP-12/HP-16 | GREEN INFRASTRUCTURE PROGRAM | 112 | WP-0169 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | GI - GREEN INFRASTRUCTURE IN WESTCHESTER CREEK HP-12/HP-16 | 2019 | 12561 | 3528.59 | -505 | 9538 | 0 | 0 | 0 | 0 | 12561.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | GXHP33-01 | GI - Green Infrastructure in Westchester Creek - HP-33 | GREEN INFRASTRUCTURE PROGRAM | 112 | WP-0169 |  |  | GI - GREEN INFRASTRUCTURE IN WESTCHESTER CREEK - HP-33 | 2019 | 15388 | 6051.3 | -1607 | 0 | 10944 | 0 | 0 | 0 | 15388.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HPBOILER | HUNTS POINT MEAT MARKET (EDC)--BOILER UPDATES | NEIGHBORHOOD REVITALIZATION | 100 | ED-D408 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | HUNTS POINT MEAT MARKET (EDC)--BOILER UPDATES | 2019 | 1500 | 0 | 1350 | 150 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HPCMFRIDG | Hunts Point Cooperative Market (Efficient Refrigeration Comp | MISCELLANEOUS | 100 | ED-D408 |  |  | HUNTS POINT COOPERATIVE MARKET (EFFICIENT REFRIGERATION COMPRESSOR) - | 2019 | 0 | 0 | 950 | 0 | 0 | 0 | 0 | 0 | 950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HPMRKRAIL | Hunts Point Produce Market Raill Imp. | MARKET DEVELOPMENT | 100 | ED-0075 ED-D075 |  |  | HUNTS RAIL | 2019 | 12729 | 8129.65 | 1416 | 0 | 0 | 0 | 0 | 0 | 9545.65 | 9999.71 | 0 | 0 | 0 | 0 | 0 | 0 | 9999.71
20190425 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HPRAILSBG | HUNTS POINT RAIL SPUR | NEIGHBORHOOD REVITALIZATION | 100 102 | ED-0075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | HUNTS POINT RAIL SPUR | 2019 | 0 | 285.16 | 14 | 0 | 0 | 0 | 0 | 0 | 299.16 | 2507.43 | 193 | 0 | 0 | 0 | 10000 | 0 | 12700.43
20190425 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HTPRODUC2 | Hunts Point Market | MARKET DEVELOPMENT | 102 | ED-D075 ED-X075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | HUNTS POINT MARKET | 2019 | 1500 | 0 | 0 | 0 | 0 | 7683 | 0 | 0 | 7683 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HUNTMEAT2 | Hunts Point Meat Market 2 | MARKET DEVELOPMENT | 100 | ED-0408 |  |  | HUNTS POINT - MEAT MARKET. INFRASTRUCTURE REPAIRS | 2019 | 65000 | 11266.22 | -31 | 0 | 0 | 31 | 10000 | 15965 | 37231.22 | 0 | 495 | 0 | 0 | 0 | 0 | 0 | 495
20190425 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HUNTSAOU2 | Hunts Point AOU-2 and Building G Development | MARKET DEVELOPMENT | 100 | ED-0408 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | HUNTS POINT AOU-2 AND BUILDING G DEVELOPMENT | 2019 | 6768 | 1807.14 | 0 | 0 | 0 | 0 | 1500 | 3461 | 6768.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HUNTSFISH | Hunts Point Fish Market | MARKET DEVELOPMENT | 100 | ED-0408 |  |  | HUNTS POINT - FISH MARKET | 2019 | 10000 | 0 | 1788 | 0 | 2762 | 0 | 3000 | 2450 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HUNTSPROD | Hunts Point Produce Market | MARKET DEVELOPMENT | 100 | ED-0408 |  |  | REDEVELOPMENT PROJECT WITHIN STRATEGIC PLAN FOR MODERNIZATION OF MARKET FACILITIES, BUSINESS GROWTH AND DIVERSIFICATION, RESILIENCY AND INTERMODAL TRANSPORTATION | 2019 | 30000 | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HUNTSPTR2 | Hunts Point Area Wide Improvements | MARKET DEVELOPMENT | 100 | ED-0408 |  |  | HUNTS POINT AREAWIDE IMPROVEMENTS | 2019 | 25000 | 0 | 0 | 0 | 9750 | 4000 | 0 | 11250 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HUNTSPTRR | Hunts Point Infrastructure Improvements | MARKET DEVELOPMENT | 100 | ED-0408 |  |  | HUNTS POINT INFRASTRUCTURE IMPROVEMENTS | 2019 | 15000 | 13205.13 | 1795 | 0 | 0 | 0 | 0 | 0 | 15000.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HWXP2010 | Hunts Point Signage and Streetscape Project | PRIMARY STREET RECONSTRUCTION | 102 | ED-X384 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | HUNTS POINT STREET ENHAMENT ON THE HILL BOROUGH BX | HUNTS POINT STREETSCAPE ENHACEMENT ON THE HILL BOROUGH BX | 2019 | 5938 | 1591.54 | 0 | 51 | 0 | 0 | 0 | 0 | 1642.54 | 4763.22 | 0 | 0 | 0 | 0 | 0 | 0 | 4763.22
20190425 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | LNEA16HPT | HUNTS POINT: MAJOR RENOVATION | ESSENTIAL RECONSTRUCTION OF FACILITIES | 100 | LN-0008 LN-D008 |  |  | HUNTS POINT: MAJOR RENOVATION | 2019 | 20000 | 0 | 3344 | 13471 | 0 | 0 | 0 | 0 | 16815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | LNEA16MLR | Melrose: Major Renovation | ESSENTIAL RECONSTRUCTION OF FACILITIES | 100 | LN-0008 LN-D008 LN-X001 |  |  | MELROSE: MAJOR RENOVATION | 2019 | 20000 | 0 | 4600 | 18494 | 0 | 0 | 0 | 0 | 23094 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | P-1ORCHPA | Orchard Beach Pavillion & Ancillary Reconstruction | BEACHES AND BOARDWALKS | 100 | P-X245 P-0715 P-D021 |  | ORCHARD BEACH | ORCHARD BEACH COMPLETE RENOVATION OF PAVILION & ANCILLARY SPACE | 2019 | 10000 | 0 | 8300 | 14784 | 17070 | 0 | 0 | 0 | 40154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | RICONNECT | Randall's Island Connector | MISCELLANEOUS | 100 | ED-0075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | PEDESTRIAN/BIKE CONNECTOR BETWEEN SOUTH BRONX GREENWAY AND RANDALL'S ISLAND PATHWAYS. | 2019 | 3556 | 4834.03 | 0 | 200 | 0 | 816 | 0 | 0 | 5850.03 | 1733.89 | 200 | 2268 | 0 | 0 | 0 | 0 | 4201.89
20190425 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDHPRX2 | Hunts Point Resiliency Mob-Gen/SP | MISCELLANEOUS | 100 | ED-0408 |  |  | HUNTS POINT RESILIENCY - MOBILE GENERATORS/SOLAR PANELS | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 3697 | 0 | 0 | 0 | 0 | 6197
20190425 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDHPRXD | Hunts Point Energy Resiliency Pilot - DR | MISCELLANEOUS | 100 | ED-0408 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | HUNTS POINT | 2019 | 40844 | 0 | 0 | 0 | 26000 | 0 | 0 | 0 | 26000 | 0 | 2500 | 32147 | 0 | 0 | 0 | 0 | 34647
20190425 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | STHBRXGRN | South Bronx Greenway | NEIGHBORHOOD REVITALIZATION | 100 102 106 109 111 112 | ED-0075 WP-0056 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | SOUTH BRONX GREENWAY | 2019 | 0 | 25001.22 | 454 | 101 | 0 | 0 | 0 | 0 | 25556.22 | 7645.33 | 1 | 15 | 0 | 0 | 0 | 0 | 7661.33
20190425 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | SWBXINFRA | Southwest Bronx Infrastructure Improvements | NEIGHBORHOOD REVITALIZATION | 100 | ED-0384 |  |  | SOUTHWEST BRONX INFRASTRUCTURE IMPROVEMENTS | 2019 | 194300 | 3777.67 | 0 | 0 | 13557 | 68716 | 73522 | 0 | 159572.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | SWBXLCN | Lower Concourse North | NEIGHBORHOOD REVITALIZATION | 100 | ED-0384 |  |  | LOWER CONCOURSE NORTH DEVELOPMENT | 2019 | 0 | 0 | 800 | 0 | 27000 | 0 | 0 | 0 | 27800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | VINCEAVE | Vincent Avenue Seawall Rehabilitation | MISCELLANEOUS | 100 | RE-0025 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | VINCENT AVENUE SEAWALL REHAB | 2019 | 2600 | 0 | 425 | 0 | 2175 | 0 | 0 | 0 | 2600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM06TNIN | THROGGS NECK HOUSES LIGHTING | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 110 | HA-X001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | INSTALLATION OF INTERCOMS AT THROGGS NECK HOUSES | 2019 | 118 | 0 | 118 | 0 | 0 | 0 | 0 | 0 | 118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM07PPCR | PELHAM PARKWAY HOUSES - COMMUNITY ROOM UPGRADE | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 111 | HA-X001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | COMMUNITY ROOM UPGRADE | 2019 | 150 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM07VYSE | VYSE AVENUE FRONT ENTRANCE DOORS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 103 | HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | REPLACE FRONT ENTRANCES | 2019 | 1410 | 26.94 | 3517 | 0 | 0 | 0 | 0 | 0 | 3543.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM11CHPY | CASTLE HILL PLAYGROUND AND OUTDOOR AREA | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 109 | HA-D001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | PLAYGROUND AND OUTDOOR AREA IMPROVEMENTS | 2019 | 450 | 1097.04 | 253 | 0 | 0 | 0 | 0 | 0 | 1350.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM11CPGP | CLASON POINT PLAYGROUND AND OUTDOOR AREA IMPROVEMENTS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 109 | HA-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | PLAYGROUND AND OUTDOOR AREA IMPROVEMENTS | 2019 | 50 | 514.98 | 49 | 0 | 0 | 0 | 0 | 0 | 563.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM11DAVC | DAVIDSON/ SITE 166 RES. ASSN SPORTS DOME AND CULINARY PROG. | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 103 | HA-X001 HA-D001 |  |  | CULINARY KITCHEN | 2019 | 1000 | 0 | 1487 | 0 | 0 | 0 | 0 | 0 | 1487 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM13BRPG | BRONX RIVER HOUSES PLAYGROUND RENOVATION | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 109 | HA-D001 HA-0001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | UPGRADE PLAYGROUNDS | 2019 | 250 | 411.46 | 39 | 0 | 0 | 0 | 0 | 0 | 450.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM14MKGH | MILLBROOK HOUSES SOLAR POWERED GREENHOUSE | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 101 | HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CONSTRUCT A SOLAR POWERED GREENHOUSE | 2019 | 300 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM14MLBQ | MILLBROOK HOUSES - TWO BARBEQUE AREAS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 101 | HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | TWO BARBEQUE AREAS | 2019 | 300 | 868.48 | 93 | 0 | 0 | 0 | 0 | 0 | 961.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM14MRSR | MONROE HOUSES SENIOR CENTER RENOVATION | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 109 | HA-X001 AG-D001 HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RENOVATE SENIOR CENTER | 2019 | 1000 | 0 | 3379 | 0 | 0 | 0 | 0 | 0 | 3379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM14SHPL | STEBBINS AVENUE - HEWITT PLACE PLAYGROUND RENOVATION | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 102 | HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | PLAYGROUND AREA RENOVATION | 2019 | 600 | 750.27 | 100 | 0 | 0 | 0 | 0 | 0 | 850.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM14SMGD | ST. MARY'S PARK PLAYGROUND RENOVATION | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 101 | HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | UPGRADE TO PLAYGROUNDS | 2019 | 500 | 324.29 | 176 | 0 | 0 | 0 | 0 | 0 | 500.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM15FOCC | FOREST HOUSES COMMUNITY CENTER GYM AND LOCKER ROOMS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 103 | HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | UPGRADE GYM AND LOCKER ROOMS | 2019 | 400 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM15SHGC | STEBBINS AVENUE-HEWITT PLACE INFRASTRUCTURE IMPROVEMENTS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 102 | HA-0001 |  |  | INFRASTRUCTURE IMPROVEMENTS | 2019 | 280 | 559.52 | 863 | 0 | 0 | 0 | 0 | 0 | 1422.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM15TNLG | THROGGS NECK HOUSES INSTALL LIGHT POLES AT BALL FIELD | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 110 | HA-X001 |  |  | INSTALL LIGHT POLES AT BALL FIELD | 2019 | 100 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM15TWPK | SECURITY SYSTEMS AT TWIN PARKS CONS AND PARKSIDE | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 100 | HA-D001 |  |  | LAYERED ACCESS CONTROLS AT TWIN PARKS CONSOLIDATED, LAYERED ACCESS CONTROLS AND LOBBY AND EXTERIOR CAMERAS AT PARKSIDE | 2019 | 3408 | 3238.51 | 169 | 0 | 0 | 0 | 0 | 0 | 3407.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM16BSGD | BOSTON SECOR PLAYGROUND RENOVATION | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 112 | HA-D001 |  |  | UPGRADE PLAYGROUNDS | 2019 | 300 | 470.05 | 130 | 0 | 0 | 0 | 0 | 0 | 600.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM16CLGY | CLAREMONT HOUSES GYM RENOVATION FOR CLAREMONT NEIGHBORHOOD | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 103 | HA-D001 HA-X001 |  |  | CLAREMONT HOUSES GYM RENOVATION FOR CLAREMONT NEIGHBORHOOD CENTER | 2019 | 450 | 0 | 1445 | 0 | 0 | 0 | 0 | 0 | 1445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM16FOSC | INSTALLATION OF SECURITY CAMERAS AT FOREST HOUSES | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 103 | HA-D001 |  |  | INSTALLATION OF SECURITY CAMERAS | 2019 | 400 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM16MODC | JAMES MONROE HOUSES RENOVATE COMMUNITY CENTER | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 109 | HA-D001 |  |  | RENOVATE LOCATION AT 816 SOUNDVIEW AVENUE FOR USE OF DAY CARE | 2019 | 1000 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM16VRCA | RECONSTRUCTION OF COMMON AREAS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 100 | HA-D001 |  |  | RECONSTRUCTION OF COMMON AREAS | 2019 | 750 | 0 | 1400 | 0 | 0 | 0 | 0 | 0 | 1400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM17CLTV | COLLEGE AVENUE -EAST 165TH STREET SECURITY CAMERAS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 104 | HA-D001 |  |  | INSTALL SECURITY CAMERAS AT 1020 COLLEGE AVENUE | 2019 | 500 | 374 | 126 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM17FORF | ROOF REPLACEMENT AT FOREST HOUSES | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 103 | HA-0001 |  |  | ROOF REPLACEMENT | 2019 | 11110 | 383.82 | 17297 | 0 | 0 | 0 | 0 | 0 | 17680.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM17MASC | MORRISANIA SECURITY ENHANCEMENTS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 103 | HA-D001 |  |  | SECURITY ENHANCEMENTS AT MORRISANIA HOUSES | 2019 | 700 | 661.4 | 39 | 0 | 0 | 0 | 0 | 0 | 700.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM17MNTV | MONROE HOUSES SECURITY CAMERAS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 109 | HA-D001 |  |  | INSTALL SECURITY CAMERAS | 2019 | 500 | 416.87 | 83 | 0 | 0 | 0 | 0 | 0 | 499.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM17MRPL | MORRIS HOUSES PLAYGROUND RENOVATION | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 103 | HA-D001 |  |  | PLAYGROUND RENOVATION | 2019 | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM17MUGR | MURPHY HOUSES GROUNDS RENOVATION | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 105 | HA-D001 |  |  | GROUNDS RENOVATION | 2019 | 300 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM17PHCC | PATTERSON HOUSES COMMUNITY CENTER REHAB | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 100 | HA-X001 |  |  | PATTERSON HOUSES COMMUNITY CENTER REHABILITATION | 2019 | 200 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM17SOSK | BRONXDALE NURSERY AT SOTOMAYOR HOUSES SPRINKLER SYSTEM | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 109 | HA-D001 |  |  | NSTALL NEW SPRINKLER SYSTEM AT THE BRONXDALE NURSERY SCHOOL | 2019 | 220 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18BRCB | BOSTON ROAD SENIOR CENTER ROOF REPLACEMENT | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 100 | HA-D001 |  |  | BOSTON ROAD SENIOR CENTER ROOF REPLACEMENT | 2019 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18BRCC | Bronx River CC: Children's Arts and Science Workshops | LOW TO MODERATE INCOME PUBLIC HOUSING CONSTRUCTION | 100 | HA-X001 |  |  | BRONX RIVER CC: CHILDREN'S ARTS AND SCIENCE WORKSHOPS | 2019 | 0 | 0 | 55 | 0 | 0 | 0 | 0 | 0 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CCMH | MELROSE HOUSES CCTV AND LAC | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 101 | HA-0001 |  |  | INSTALL CCTV AND LAC | 2019 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CLLG | CLAREMONT REHAB 2 -4 EXTERIOR LIGHTING | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 104 | HA-D001 |  |  | INSTALLATION OF EXTERIOR LED LIGHTING AT CLAREMONT REHAB 2 -4 | 2019 | 400 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18COSC | SECURITY CAMERA INSTALLATION AT 372 EAST 152ND ST COURTLANDT | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 101 | HA-D001 |  |  | SECURITY CAMERA INSTALLATION AT 372 EAST 152ND ST COURTLANDT STREET | 2019 | 50 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18EATR | Renovation of East Tremont Childcare Center Playground | LOW TO MODERATE INCOME PUBLIC HOUSING CONSTRUCTION | 100 | HA-D001 |  |  | RENOVATION OF EAST TREMONT CHILDCARE CENTER | 2019 | 500 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18FSBO | Boiler Replacements at Pelham Parkway | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 111 | HA-0001 |  |  | BOILER REPLACEMENTS AT PELHAM PARKWAY | 2019 | 0 | 0 | 29000 | 0 | 0 | 0 | 0 | 0 | 29000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18HBLG | EXTERIOR LED LIGHTING AT HIGHBRIDGE GARDENS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 104 | HA-D001 |  |  | EXTERIOR LED LIGHTING AT HIGHBRIDGE GARDENS | 2019 | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18MBLT | MILL BROOK EXTERIOR LIGHTING | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 101 | HA-D001 |  |  | IMPROVE EXTERIOR LIGHTING | 2019 | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18MBSS | MILL BROOK HOUSES SPRAY SHOWERS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 101 | HA-D001 |  |  | MILL BROOK HOUSES SPRAY SHOWERS INSTALLATION | 2019 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18MRP1 | MORRIS I PLAYGROUND RENOVATION IN FRONT OF 3606 THIRD AVE | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 103 | HA-X001 |  |  | RENOVATION OF A PLAYGROUND IN FRONT OF 3606 THIRD AVENUE | 2019 | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18MRPG | MORRIS II PLAYGROUND RENOVATION IN FRONT OF 1481 WASHINGTON | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 103 | HA-X001 |  |  | MORRIS II HOUSES PLAYGROUND--PLAYGROUND RENOVATION IN FRONT OF 1481 WASHINGTON AVENUE. | 2019 | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18MTGD | MITCHEL HOUSES EXTERIOR LIGHTING | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 101 | HA-D001 |  |  | UPGRADE EXTERIOR LIGHTING | 2019 | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18PCCK | KITCHEN RENOVATION AT PATTERSON HOUSES COMMUNITY CENTER | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 101 | HA-X001 |  |  | RENOVATION OF THE KITCHEN AT PATTERSON HOUSES COMMUNITY CENTER 340 MORRIS AVE | 2019 | 800 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18PPHL | Pelham Parkway Houses Exterior Lighting Installation | LOW TO MODERATE INCOME PUBLIC HOUSING CONSTRUCTION | 100 | HA-X001 HA-D001 |  |  | PELHAM PARKWAY HOUSES EXTERIOR LIGHTING INSTALLATION | 2019 | 750 | 0 | 750 | 0 | 0 | 0 | 0 | 0 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18RBSC | SECURITY CAMERAS AT THROGGS NECK (RANDALL- BALCOLM) | LOW TO MODERATE INCOME PUBLIC HOUSING CONSTRUCTION | 110 | HA-D001 |  |  | INSTALL SECURITY CAMERAS | 2019 | 285 | 0 | 503 | 0 | 0 | 0 | 0 | 0 | 503 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18SMTV | SOTOMAYOR SECURITY ENHANCEMENTS AT 1055 ROSEDALE AVENURE | LOW TO MODERATE INCOME PUBLIC HOUSING CONSTRUCTION | 100 | HA-X001 |  |  | SOTOMAYOR SECURITY ENHANCEMENTS AT 1055 ROSEDALE AVENURE | 2019 | 1000 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18SOCC | Sotomayor CC Cornerstone Program - Computer Technology | LOW TO MODERATE INCOME PUBLIC HOUSING CONSTRUCTION | 100 | HA-X001 |  |  | SOTOMAYOR CC CORNERSTONE PROGRAM - COMPUTER TECHNOLOGY | 2019 | 0 | 0 | 42 | 0 | 0 | 0 | 0 | 0 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18SOMO | SOTOMAYOR HOUSES/MONTEFIORE BEHAVIOR HC - PSYCH CENTER | LOW TO MODERATE INCOME PUBLIC HOUSING CONSTRUCTION | 100 | HA-X001 HA-D001 |  |  | SOTOMAYOR HOUSES/MONTEFIORE BEHAVIOR HC - PSYCH CENTER | 2019 | 0 | 0 | 5500 | 0 | 0 | 0 | 0 | 0 | 5500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18SVCC | Soundview CC Cornerstone Program - Computer Technology | LOW TO MODERATE INCOME PUBLIC HOUSING CONSTRUCTION | 100 | HA-X001 |  |  | SOUNDVIEW CC CORNERSTONE PROGRAM - COMPUTER TECHNOLOGY | 2019 | 0 | 0 | 42 | 0 | 0 | 0 | 0 | 0 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18TCCK | THROGGS NECK COMMUNITY C ENTER KITCHEN UPDATE | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 110 | HA-X001 |  |  | NYCHA THROGS NECK ADDITION COMMUNITY CENTER--UPDATE KITCHEN 550 BALCOLM AVENUE. | 2019 | 600 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18TCCL | THROGGS NECK COMMUNITY CENTER LIGHTING | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 110 | HA-X001 |  |  | NYCHA THROGS NECK HOUSES COMMUNITY CENTER--LIGHTING THROUGHOUT FACILITY 550 BALCOM AVENUE. | 2019 | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18TCCR | Claremont Consolidated Security Enhancements | LOW TO MODERATE INCOME PUBLIC HOUSING CONSTRUCTION | 100 | HA-X001 |  |  | CLAREMONT CONSOLIDATED SECURITY ENHANCEMENTS | 2019 | 700 | 0 | 700 | 0 | 0 | 0 | 0 | 0 | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18TNCR | THROGGS NECK COMMUNITY - ROOF RENOVATIONS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 110 | HA-X001 |  |  | NYCHA THROGS NECK HOUSES COMMUNITY CENTER--NEW ROOF RENOVATIONS 550 BALCOLM AVENUE. | 2019 | 1000 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19ADEL | ADAMS HOUSES ELEVATOR REPLACEMENT | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 101 | HA-0001 |  |  | REPLACE ELEVATOR AT ADAMS HOUSES | 2019 | 8566 | 0 | 787 | 6600 | 0 | 0 | 0 | 0 | 7387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19BESC | BETANCES SENIOR CENTER COURTYARD RENOVATIONS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 100 | HA-X001 HA-D001 |  |  | BETANCES SENIOR CENTER COURTYARD RENOVATIONS | 2019 | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19BHSC | BAILEY HOUSES SECURITY CAMERAS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 107 | HA-D001 |  |  | FUNDING FOR SECURITY CAMERAS | 2019 | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19BPWS | BUTLER HOUSES PLAYGROUND WATER SPRAYS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 103 | HA-D001 |  |  | PLAYGROUND WATER SPRAY SYSTEMS | 2019 | 200 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19BRSC | BRONX RIVER SENIOR CENTER KITCHEN RENOVATIONS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 100 | HA-X001 HA-D001 |  |  | BRONX RIVER SENIOR CENTER KITCHEN RENOVATIONS | 2019 | 1000 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19CAGR | CASTLE HILL HOUSES GAS RISER REPLACEMENTS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 109 | HA-0001 |  |  | GAS RISER REPLACEMENT | 2019 | 10602 | 0 | 10138 | 0 | 0 | 0 | 0 | 0 | 10138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19CASC | EAST 152ND-COURTLANDT AVENUE SECURITY CAMERAS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 107 | HA-D001 |  |  | FUNDING FOR SECURITY CAMERAS | 2019 | 0 | 0 | 225 | 0 | 0 | 0 | 0 | 0 | 225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19CMHP | MOORE HOUSES PLAYGROUND | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 101 | HA-0001 |  |  | FUNDING FOR MOORE HOUSES PLAYGROUND UPGRADE | 2019 | 1200 | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19MARE | MORRISANIA AIR RIGHTS ELEVATOR REPLACEMENT AT 3135 PARK AVE | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 103 | HA-D001 |  |  | ELEVATOR REPLACEMENT AT 3135 PARK AVENUE | 2019 | 2000 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19MHSE | MARBLE HILL SECURITY ENHANCEMENTS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 108 | HA-D001 |  |  | MARBLE HILL SECURITY ENHANCEMENTS-INSTALLATION OF SECURITY EQUIPMENT | 2019 | 75 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19MHSP | MARBLE HILL PARKING LOT SECURITY POLES | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 108 | HA-D001 |  |  | PARKING LOT SECURITY POLES | 2019 | 100 | 0 | 139 | 0 | 0 | 0 | 0 | 0 | 139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19PHBC | PATTERSON HOUSES BASKETBALL COURT UPGRADE | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 101 | HA-D001 |  |  | BASKETBALL COURT UPGRADE | 2019 | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19UNSC | 1865 UNIVERSITY AVE- SECURITY CAMERAS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 105 | HA-D001 |  |  | SECURITY CAMERAS AT 1865 UNIVERSITY AVENUE | 2019 | 121 | 0 | 121 | 0 | 0 | 0 | 0 | 0 | 121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20MLEL | MELROSE HOUSES ELEVATOR REPLACEMENT | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 101 | HA-0001 |  |  | REPLACE ELEVATORS AT MELROSE HOUSES | 2019 | 8729 | 0 | 600 | 7935 | 0 | 0 | 0 | 0 | 8535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21EWGR | EDENWALD GAS RISERS #6 | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 112 | HA-0001 |  |  | INSTALLATION OF GAS RISERS #6 | 2019 | 9900 | 0 | 0 | 0 | 9000 | 0 | 0 | 0 | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM24CHBR | CASTLE HILL BATHROOMS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 109 | HA-0001 |  |  | INSTALLATION OF CASTLE HILL BATHROOMS | 2019 | 42800 | 0 | 0 | 0 | 0 | 0 | 0 | 38909 | 38909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82BERGN | BERGEN BUILDING RENOVATION - 1932 ARTHUR AVE., BRONX, NY | ADMINISTRATION |  | HL-0082 |  |  | GENERAL CONSTRUCTION, ELECTRICAL POWER, LIGHTING & PLUMBING | 2019 | 800 | 0 | 0 | 800 | 0 | 0 | 0 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82GLEEB | BUILDING RENOVATION - 2527 GLEBE AVE, BRONX, NY | ADMINISTRATION |  | HL-0082 |  |  | BUILDING ROOFING AND EXTERIOR RENOVATION | 2019 | 2500 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82MORHC | Morrisania Health Center interior renovation | CLINIC RENOVATION AND REHABILITATION |  | HL-0082 |  |  | MORRISANIA HEALTH CENTER INTERIOR RENOVATION | 2019 | 4700 | 0 | 0 | 0 | 0 | 0 | 3000 | 1000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82OCMEX | OCME - New Medical Examiner Facility | OCME | 100 111 | HL-0083 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | HL82OCMEX | CONSTRUCTION OF NEW FACILITY | 2019 | 30331 | 2967.38 | 0 | 300 | 2146 | 5496 | 5651 | 4778 | 21338.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82ZERGA | LEASE SPACE RENOVATION - 1235 ZEREGA AVENUE, BRONX, NY | ADMINISTRATION |  | HL-0082 |  |  | LEASE SPACE RENOVATION | 2019 | 2000 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 02201801 | JMC: BUILDING #4 RENOVATIONS | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 1400 PELHAM PARKWAY SOUTH, BRONX, NY 10461 | THIS PROJECT CONSISTS OF THE NECESSARY RELOCATION OF EXISTING JACOBI DEPARTMENTS TO NEW AREAS IN ORDER TO RENOVATE THE VACATED SPACE ON MULTIPLE FLOORS TO HOUSE CENTRAL OFFICE AND EITS ADMINISTRATIVE AND OPERATIONAL UNITS. | 2019 | 7638 | 2214.43 | 2942 | 2482 | 0 | 0 | 0 | 0 | 7638.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 02201802 | JACOBI: CONSTRUCT PLAYGROUND FOR THE PEDIATRIC DEPT | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 1400 PELHAM PARKWAY SOUTH, BRONX | CONSTRUCT PLAYGROUND "PARATE SHIP" FOR THE PEDIATRIC DEPT. AT JACOBI MEDICAL CENTER. | 2019 | 840 | 0 | 840 | 0 | 0 | 0 | 0 | 0 | 840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 20201501 | BELVIS: PEDIATRIC SUITE MODERNIZATION | ROUTINE RECONSTRUCTION | 101 | HO-D003 |  | 545 EAST 142ND STREET, BRONX, BY 10454 | MODERNIZE PEDIATRIC SUITE, INCLUDING NEW PHYSICIAN AND NURSE WORKSTATIONS, EXPANDED SEATING FOR RECEPTION AND SUB-WAITING AREAS, AND RENOVATION OF PUBLIC TOILETS. | 2019 | 92 | 0 | 0 | 92 | 0 | 0 | 0 | 0 | 92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 20201801 | BELVIS: REPLACEMENT OF MAIN ENTRANCE DOORS | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 545 EAST 142ND STREET, BRONX, NY 10454 | BELVIS, A GOTHAM HEALTH CENTER: REPLACE THE MAIN ENTRANC DOORS. | 2019 | 95 | 0 | 87 | 8 | 0 | 0 | 0 | 0 | 95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 21200603 | JACOBI: CENTRALIZE REPRODUCTIVE HEALTH SERVICES | ROUTINE RECONSTRUCTION | 111 | HO-0214 |  | 1400 PELHAM PARKWAY SOUTH, BRONX, NY 10461 | UPON COMPLETION OF THIS PROJECT, JACOBI MEDICAL CENTER WILL OPERATE A WOMEN'S OPTIONS CENTER. | 2019 | 3722 | 3560.59 | 62 | 0 | 0 | 0 | 0 | 0 | 3622.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 21201601 | JACOBI: LOCAL LAW 11 COMPLIANCE | ROUTINE RECONSTRUCTION | 111 | HO-0214 |  | 1400 PELHAM PARKWAY SOUTH, BRONX NY 10461 | THE PURPOSE OF THIS PROJECT IS TO RENOVATE BUILDINGS AT JACOBI HOSPITAL CENTER USING LOCAL LAW 11- FUNDS FOR LOCAL LAW 11 COMPLIANCE. | 2019 | 2034 | 0 | 621 | 1001 | 412 | 0 | 0 | 0 | 2034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 21201703 | JMC: INSTALL A SECONDARY WATER DISINFECTION SYSTEM-BLGS 1&6 | ROUTINE RECONSTRUCTION | 111 | HO-0214 |  | 1400 PELHAM PARKWAY SOUTH, BRONX, NY 10461 | JACOBI MEDICAL CENTER, BRONX, NY: PURCHASE AND INSTALL A SECONDARY WATER DISINFECTION SYSTEM (AKA COPPER-SILVER IONIZATION SYSTEM) FOR BUILDINGS #S 1 & 6. | 2019 | 117 | 0 | 117 | 0 | 0 | 0 | 0 | 0 | 117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 21201704 | JMC: REHABILITATE MAIN LOBBY CEILING IN BUILDING 6 | ROUTINE RECONSTRUCTION | 111 | HO-0377 |  | 1400 PELHAM PARKWAY SOUTH, BRONX, NY 10461 | REHABILITATE MAIN LOBBY CEILING IN BUILDING 6 AT JACOBI MEDICAL CENTER. | 2019 | 905 | 0 | 828 | 77 | 0 | 0 | 0 | 0 | 905 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 21201901 | JMC: ELECTRICAL UPGRADE FOR MAIN KITCHEN | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 1400 PELHAM PKWAY SOUTH, BRONX, NY 10461 | NYC HEALTH + HOSPITALS / JACOBI, BX: ELECTRICAL UPGRADE FOR MAIN KITCHEN | 2019 | 346 | 0 | 346 | 0 | 0 | 0 | 0 | 0 | 346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 24201502 | NCB: OB/GYN NURSING UNIT UPGRADE | ROUTINE RECONSTRUCTION |  | HO-D003 |  |  | RENOVATE THE NURSING AND DELIVERY SUITE AT NORTH CENTRAL BRONX HOSPITAL AND RE-OPEN SERVICE IN FALL OF 2014, | 2019 | 1200 | 0 | 0 | 900 | 300 | 0 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 24201610 | RENOVATE TREMONT HEALTH CLINIC | ROUTINE RECONSTRUCTION | 106 | HO-0214 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 1826 ARTHUR AVENUE, BRONX, NY 10457 | RENOVATE TREMONT HEALTH CLINIC IN ORDER TO EXPAND PRIMARY CARE HEALTHSERVICES. | 2019 | 841 | 949.87 | 265 | 0 | 0 | 0 | 0 | 0 | 1214.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 24201901 | NCB: FACADE REHABILITATION & WINDOW REPLACEMENT | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 3424 KOSUTH AVENUE, BRONX, NY | FACADE REHABILIATION AND WINDOW REPLACEMENT | 2019 | 12448 | 0 | 0 | 6029 | 5000 | 1419 | 0 | 0 | 12448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25201262 | LINCOLN: REPLACE LINEAR ACCELERATOR | MAJOR MEDICAL EQUIPMENT | 101 | HO-0214 |  | 234 EAST 149 STREET, BRONX, NY 10451 |  | 2019 | 7700 | 6724.11 | 248 | 755 | 0 | 0 | 0 | 0 | 7727.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25201401 | LINCOLN: RENOVATE ADOLESCENT CLINIC | ROUTINE RECONSTRUCTION | 101 | HO-D003 HO-X002 |  | 234 149TH STREET, BRONX, NY 10451 | RENOVATE AND MODERNIZE ADOLESCENT AND PEDIATRIC CLINIC AT LINCOLN MEDICAL CENTER. | 2019 | 1248 | 2.06 | 908 | 338 | 0 | 0 | 0 | 0 | 1248.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25201601 | LINCOLN: COOLING TOWER REPLACEMENT | ROUTINE RECONSTRUCTION | 101 | HO-0214 |  | 234 EAST 149TH STREET, BRONX, NY 10451 | REPLACE COOLING TOWER AT LINCOLN MEDICAL & MENTAL HEALTH CENTER | 2019 | 11235 | 10434.37 | 113 | 688 | 0 | 0 | 0 | 0 | 11235.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25201602 | LINCOLN: REPLACE UNDERGROUND FUEL TANKS | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 234 EAST 149TH STREET, BRONX, NY 10451 | REPLACE UNDERGROUND FUEL TANKS AT LINCOLN MEDICAL & MENTAL HEALTH CENTER | 2019 | 9834 | 169.5 | 2065 | 5952 | 1647 | 0 | 0 | 0 | 9833.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25201604 | LINCOLN: EXTERIOR FACADE RESTORATION - LL11 COMPLIANCE | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 234 EAST 149TH STREET, BRONX, NY 10451 | RESTORE EXTERIOR FACADE TO COMPLY WITH LOCAL LAW 11 GUIDELINES. | 2019 | 335 | 0 | 306 | 29 | 0 | 0 | 0 | 0 | 335 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25201701 | LINCOLN: EMERGENCY PANEL UPGRADE | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 234 EAST 149TH STREET, BRONX, NY 10451 | UPGRADE THE ELECTRICAL PANELS AT LINCOLN MEDICAL & MENTAL HEALTH CENTER. | 2019 | 945 | 0 | 234 | 0 | 711 | 0 | 0 | 0 | 945 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25201801 | LINCOLN: REFURBISH BOILER Nos. 1-3 | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 234 EAST 149TH STREET, BRONX, NY 10451 | NYC HEALTH + HOSPITALS ¦ LINCOLN: REFURBISH BOILER NOS. 1-3 | 2019 | 865 | 0 | 865 | 0 | 0 | 0 | 0 | 0 | 865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25201805 | LINCOLN: REHABILITATE ELECTRICAL DISTRIBUTION SYSTEM | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 234 EAST 149TH STREET, BRONX, NY 10451 | REHABILITATE ELECTRICAL DISTRIBUTION SYSTEM AT LINCOLN MEDICAL & MENTAL HEALTH CENTER | 2019 | 411 | 0 | 411 | 0 | 0 | 0 | 0 | 0 | 411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25201806 | LINCOLN: REPLACEMENT OF GENERATORS B1 AND B2 & 6 RADIATORS | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 234 EAST 149TH STREET, BRONX, NY 10451 | NYC HEALTH + HOSPITALS ¦ LINCOLN: REPLACEMENT OF GENERATORS B1 AND B2& 6 RADIATORS | 2019 | 3900 | 0 | 82 | 3436 | 382 | 0 | 0 | 0 | 3900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25201807 | LINCOLN: UPGRADE ELEVATORS 18 & 19 | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 234 EAST 149TH STREET, BRONX, NY 10451 | NYC HEALTH + HOSPITALS ¦ LINCOLN: UPGRADE ELEVATORS 18 & 19 | 2019 | 501 | 0 | 465 | 36 | 0 | 0 | 0 | 0 | 501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25201901 | LINCOLN: RETAIL PHARMACY RENOVATION | ROUTINE RECONSTRUCTION |  | HO-0214 |  | EAST 149TH STREET, BRONX, NY 10451 | RETAIL PHARMACY RENOVATION AT LINCOLN MEDICAL & MENTAL HEALTH CENTER | 2019 | 686 | 0 | 34 | 652 | 0 | 0 | 0 | 0 | 686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 42201301 | MORRISANIA: RENOVATE DENTAL SUITE | ROUTINE RECONSTRUCTION | 104 | HO-D003 |  | 1225 GERARD AVENUE, BRONX, NY 10452 | THE DENTAL SUITE AT MORRISANIA D&TC IS IN NEED OF RENOVATION AND NEW EXAM CHAIRS. | 2019 | 345 | 0 | 0 | 345 | 0 | 0 | 0 | 0 | 345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 42201515 | MORRISANIA: RENOVATE WOMEN'S HEALTH SERVICES - RADIOLOGY | ROUTINE RECONSTRUCTION | 104 | HO-D003 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 1225 GERARD AVENUE, BRONX, NY 10452 | RECONIGURE EXISTING WOMEN'S HEALTH SERVICES/RADIOLOGY DEPARTMENT TO MAKE SERVICES ACCESSIBLE FOR WOMEN WITH DISABILITIES. | 2019 | 588 | 126 | 729 | 0 | 0 | 0 | 0 | 0 | 855 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 42201901 | MORRISANIA: EXTERIOR STRUCTURAL RESTORATIONS | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 1225 GERARD AVENUE, BRONX, NY 10452 | PERFORM EXTERIOR STRUCTURAL RESTORATIONS AT NYC HEALTH + HOSPITALS / GOTHAM HEALTH, MORRISANIA. THE THREE MAIN COMPONENTS OF THE PROJECT INCLUDE: RESURFACE THE PARKING LOT; RESTRUCTURE THE RETAINING WALLS | 2019 | 2425 | 0 | 2425 | 0 | 0 | 0 | 0 | 0 | 2425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 819 | HEALTH AND HOSPITALS CORP | ACEHHC409 | HHC LINCOLN MEDICAL CENTER ENERGY UPGRADE | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT |  | PU-0025 HO-0214 |  |  | ENERGY UPGRADE OF TWENTY (20) AIR HANDLER UNITS. UPGRADE OF FLOURESCENT FIXTURES WITH SUPER EFFICIENNT LED RETROFITS. | 2019 | 0 | 0 | 12558 | 937 | 0 | 0 | 0 | 0 | 13495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 819 | HEALTH AND HOSPITALS CORP | SAND2101 | JMC: RESTORE DAMAGES TO EAST ENTRY SOFFIT - SANDY CTGY E | ROUTINE RECONSTRUCTION | 111 | HO-0214 |  | 1400 PELHAM PARKWAY SOUTH, BRONX, NY 10461 | RECONSTRUCTION OF JACOBI MEDICAL CENTER NECESSITATED BY HURRICANE SANDY. FEMA CATEGOTY E: BUILDINGS AND EQUIPMENT (PERMANENT WORK.) RESTOREDAMAGES TO EAST ENTRY SOFFIT DUE TO STORM DAMAGES CAUSED BU HURRICANESANDY | 2019 | 200 | 13.63 | 0 | 5 | 0 | 0 | 0 | 0 | 18.63 | 122.67 | 58 | 0 | 0 | 0 | 0 | 0 | 180.67
20190425 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-590 | Jerome Park Gate House #7 Sluice Gate and Operator Replacmnt | WATER QUALITY PRESERVATION | 107 | WM-0105 |  |  | JEROME PARK GATE HOUSE #7 SLUICE GATE & OPERATOR REPLACEMENT | 2019 | 3000 | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-593 | INSTALL. MONO CRANE AND HOIST OF SHUTTERS AT JEROME GATE | WATER QUALITY PRESERVATION | 107 | WM-0105 |  |  | INSTALL. MONO CRANE AND HOIST OF SHUTTERS AT JEROME GATE | 2019 | 3000 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-M&A | MITIGATION AND AMENITIES FOR WTP | CROTON FILTER PROJECT | 107 108 | WM-0011 |  |  | MITIGATION AND AMENITIES FOR WTP (IN CONJUNCTION WITH HED-545) | 2019 | 24386 | 0 | 0 | 0 | 0 | 0 | 23386 | 0 | 23386 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-NCA | NEW CROTON AQUEDUCT | CROTON FILTER PROJECT | 107 108 | WM-0011 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | NEW CROTON AQUEDUCT | 2019 | 116162 | 178214.35 | 188 | 0 | 0 | 0 | 0 | 0 | 178402.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-BX-LTP | BRONX RIVER LONG TERM CONTROL PLAN FOR CSO ABATEMENT | WATER QUALITY MANDATES | 100 | WP-0169 |  |  | CITY-WIDE LONG TERM CONTROL PLAN FOR COMBINED SEWER OVERFLOW ABATEMENT | 2019 | 146200 | 0 | 16312 | 0 | 0 | 0 | 17600 | 111000 | 144912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-ER-WCM | WESTCHESTER CSO MODIFICATIONS | WATER QUALITY MANDATES | 100 | WP-0169 |  |  | WESTCHESTER CREEK CSO MODIFICATION @EAST RIVER | 2019 | 48000 | 29406.84 | 1409 | 0 | 0 | 0 | 0 | 0 | 30815.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-HR-DF | CSO HUTCHINSON RIVER DISINFECTION FACILITY | WATER QUALITY MANDATES | 100 | WP-0169 |  |  | CSO HUTCHINSON RIVER OUTFALL & DISINFECTION | 2019 | 131000 | 13472.28 | 0 | 0 | 0 | 0 | 0 | 203678 | 217150.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-NYCHA | GI - NYCHA GREEN INFRASTRUCTURE AT EDENWALD HOUSES - NO & SO | GREEN INFRASTRUCTURE PROGRAM | 100 112 | WP-0169 |  |  | NYCHA EDENWALD PILOT GREEN INFRASTRUCTURE | 2019 | 6500 | 9162.85 | -532 | 630 | 0 | 0 | 0 | 0 | 9260.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HED-545 | CROTON FILTRATION PLANT | CROTON FILTER PROJECT | 107 108 | WM-0011 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | THE BRONX | CONSTRUCTION OF CROTON FILTRATION PLANT WRAP UP | 2019 | 1689115 | 2820427.17 | 11299 | 0 | 0 | 0 | 0 | 0 | 2831726.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HED-CROOS | CROTON FILTRATION PLANT - OFF-SITE FACILITIES | CROTON FILTER PROJECT | 107 108 | WM-0011 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CROTON FILTRATION PLANT - OFF-SITE FACILITIES | 2019 | 168500 | 155672.54 | 167 | 0 | 0 | 0 | 0 | 0 | 155839.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-238-L | REPLACEMENT OF THE DIGESTER @ THE HUNTS POINT WWTP | PLANT UPGRADING AND RECONSTRUCTION | 100 | WP-0112 |  | COSTER STREET AND RYAWA AVENUE, BRONX, N.Y. 10474 | REPLACEMENT OF THE DIGESTER AT THE HUNTS POINT WWTP | 2019 | 100000 | 22829.49 | 0 | 0 | 393000 | 0 | 0 | 0 | 415829.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-239-L | RECONSTRUCT SLUDGE HANDLING EQUIPMENT @ HUNTS POINT WWTP | PLANT UPGRADING AND RECONSTRUCTION | 100 102 | WP-0112 |  | COSTER STREET & RYAWA AVENUE, BRONX, N.Y. 10474 | RECONSTRUCT SLUDGE HANDLING EQUIPMENT @ HUNTS POINT WWTP | 2019 | 57498 | 0 | 0 | 9500 | 0 | 0 | 0 | 20000 | 29500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-244-L | RECONS DEWATERING BLDG HVAC & ODOR CONTROL SYS @ HUNTS POINT | PLANT UPGRADING AND RECONSTRUCTION | 100 | WP-0112 |  | 1270 RYAWA AVENUE, BRONX, N.Y. 10474 | RECONSTRUCTION OF THE HVAC AND ODOR CONTROL SYSTEM AT THE HUNTS POINT DEWATERING BUILDING | 2019 | 41350 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-246-L | RECONSTRUCTION OF WIGGINS GAS HOLDER @ HUNTS POINT WWTP | PLANT UPGRADING AND RECONSTRUCTION | 100 | WP-0112 |  | 1270 RYAWA AVENUE, BRONX, NEW YORK 10474 | RECONSTRUCT WIGGINS GAS HOLDER AT THE HUNTS POINT WWTP. SCOPE OF WORKSHALL INCLUDE FULL STRUCTURAL UPGRADE, BLADDER REPLACEMENT AND ANY ADDITIONAL PARTS TO RETURN THE GAS HOLDER BACK TO SERVICE. | 2019 | 3550 | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-247-L | RECONS FIRE ALARM SYS IN DEWATERING FACILITY @ HUNTS POINT | PLANT UPGRADING AND RECONSTRUCTION | 100 | WP-0112 |  | 1270 RYAWA AVENUE, BRONX, NEW YORK 10474 | RECONSTRUCT FIRE ALARM SYSTEM AT THE HUNTS POINT WWTP DEWATERING FACILITY. | 2019 | 7442 | 0 | 0 | 10996 | 0 | 0 | 0 | 0 | 10996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-252-L | INSTALL (2) MOTOR CONTROL CENTERS (MCCS) @ HUNTS POINT WWTP | PLANT UPGRADING AND RECONSTRUCTION | 100 | WP-0112 |  |  | INSTALLATION OF TWO (2) MOTOR CONTROL CENTERS (MCCS) AT THE HUNTA POINT WWTP. THE SCOPE OF WORK WILL INCLUDE BUT NOT LIMITED TO THE DEMOLOTION AND REMOVAL OF TWO (2) EXISTING MCCS, INSTALLATION OF TWO (2) NEWMCCS, DEMOLITION OF EXISTING CONDUIT SYSTEM AND INSTALLATION OF A NEW CONDUIT SYSTEM AT THE HUNTS POINT WWTP. | 2019 | 2185 | 200 | 4177 | 0 | 0 | 0 | 0 | 0 | 4377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-254-L | TRC - CONS OF DECHLORINATION FACILITY @ HUNTS POINT WWTP | CONSENT DECREE UPGRADING AND CONSTRUCTION | 100 | WP-0282 |  | COSTER STREET & RYAWA AVENUE, BRONX, NEW YORK 10474 | CONSTRUCTION OF DECHLORINATION FACILITY TO UTILIZE SODIUM BISULFITE AT THE EFFLUENT AT THE HUNTS POINT WASTEWATER TREATMENT PLANT, BRONX, NEW YORK. | 2019 | 22552 | 0 | 0 | 3994 | 3528 | 10030 | 0 | 0 | 17552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-3R | RECONSTRUCTION OF EXISTING DIGESTERS AT HUNTS POINT WPCP | PLANT COMPONENT STABILIZATION | 100 102 | WP-0056 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | RECONSTRUCT EXISTING DIGESTERS AT HUNTS POINT WATER POLLUTION CONTROLPLANT | 2019 | 40000 | 17391.58 | 129 | 0 | 0 | 0 | 0 | 0 | 17520.58 | 34055.13 | 0 | 0 | 0 | 0 | 0 | 0 | 34055.13
20190425 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-ULURP | HUNTS POINT ULURP APPLICATION COMMITMENTS | PLANT COMPONENT STABILIZATION | 100 102 | WP-0056 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | HUNTS POINT ULURP APPLICATION COMMITMENTS. STABILIZATION OF HUNTS POINT PLANT IDENTIFICATION OF NEEDS AND RECONSTRUCTION TO OPTIMIZE PLANT FLOW AND TREATMENT EFFICIENCY | 2019 | 20000 | 0 | 0 | 0 | 2300 | 0 | 0 | 0 | 2300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | JRAQ-REH | JEROME RESERVOIR & AQUEDUCT REHABILITATION | WATER QUALITY PRESERVATION | 107 | WM-0105 |  |  | JEROME RESERVOIR & AQUEDUCT REHABILITATION | 2019 | 31000 | 26972.7 | 5414 | 0 | 28013 | 0 | 0 | 0 | 60399.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-236A | Throgs Neck Pumping Station Rehabilitation and Improvements | PLANT UPGRADING AND RECONSTRUCTION | 100 | WP-0269 |  |  | RECONSTRUCTION OF THROGS NECK PS | 2019 | 54000 | 0 | 0 | 0 | 0 | 0 | 42000 | 0 | 42000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-290 | CONNER STREET PUMPING STATION | PLANT UPGRADING AND RECONSTRUCTION | 100 | WP-0269 |  | CONNOR STREET PUMPING STATION | CONNOR STREET PUMPING STATION | 2019 | 9848 | 0 | 0 | 0 | 0 | 2000 | 7848 | 0 | 9848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | REG-HP06 | RECONSTRUCTION OF REGULATOR HP-06 | WATER QUALITY MANDATES | 100 | WP-0169 |  |  | RECONSTRUCTION OF REGULATOR HP-06 | 2019 | 25000 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-264L | Bronx 5 Garage Roof Replacement | GARAGES AND FACILITIES | 105 | S-0136 |  |  | REPLACE ROOF | 2019 | 0 | 50 | 934 | 0 | 0 | 0 | 0 | 0 | 984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-264R | Bronx Lot Cleaning Garage Roof & Truss Replacement | GARAGES AND FACILITIES | 100 | S-0136 |  |  | REPLACE ROOF | 2019 | 1300 | 186.9 | 33 | 1725 | 0 | 0 | 0 | 0 | 1944.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-332M | BRONX 6/6A GARAGE REHAB | GARAGES AND FACILITIES | 106 107 | S-0136 |  |  | BRONX 6/6A GARAGE REHAB | 2019 | 20240 | 44.57 | 310 | 1291 | 2417 | 24172 | 0 | 0 | 28234.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-380 | Bronx 3A Garage Boiler Replacement | GARAGES AND FACILITIES | 100 | S-0136 |  |  | BOILER REPLACEMENT | 2019 | 400 | 0 | 339 | 0 | 0 | 0 | 0 | 0 | 339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-424 | Bronx 12 Rehabilitation (Slabs, Roof, Fueling Enclosure) | GARAGES AND FACILITIES | 112 | S-0136 |  |  | FLOOR SLAB REPLACEMENT | 2019 | 10250 | 830 | 420 | 2135 | 39578 | 0 | 0 | 0 | 42963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-429 | Bronx 3A 1661 West Farms Road Garage Rehab | GARAGES AND FACILITIES | 103 | S-0136 |  |  | REHAB | 2019 | 9891 | 0 | 512 | 853 | 0 | 8526 | 0 | 0 | 9891 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-464G | Bronx 3 Sec 31 Roof Replacement Washington Ave | GARAGES AND FACILITIES | 103 | S-0136 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | ROOF REPLACEMENT | 2019 | 144 | 0 | 0 | 0 | 0 | 0 | 144 | 0 | 144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-464J | Bronx 3A Garage Roof Replacement 1661 W Farms Rd | GARAGES AND FACILITIES | 103 | S-0136 |  |  | REPLACE ROOF | 2019 | 1405 | 0 | 781 | 0 | 0 | 1077 | 0 | 0 | 1858 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 827 | DEPARTMENT OF SANITATION | S248-423 | Bronx 9/10/11 Garage Replacement | GARAGES AND FACILITIES | 100 | S-0248 |  |  | REPLACEMENT OF THE BRONX 9/10/11 GARAGES | 2019 | 266742 | 12220.42 | 16939 | 1219 | 21363 | 0 | 239623 | 0 | 291364.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 827 | DEPARTMENT OF SANITATION | SANDBX12G | Hurricane Sandy Bronx 12 Garage R/R & Haz Mitigation | GARAGES AND FACILITIES | 112 | S-0136 |  |  | REPLACEMENT WORK AND HAZRD MITIGATION DUE TO HURRICANE SANDY | 2019 | 1197 | 118.1 | 0 | 116 | 0 | 0 | 0 | 0 | 234.1 | 0 | 0 | 786 | 0 | 0 | 0 | 0 | 786
20190425 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | BRX2110 | BOSTON ROAD OVER BRONX RIVER BIN: 2242110 | USEFUL LIFE EXTENSION | 100 111 | HB-1070 |  |  | BOSTON ROAD OVER BRONX RIVER ÝBIN: 2242110 | 2019 | 12036 | 0 | 0 | 991 | 930 | 2427 | 17161 | 0 | 21509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | BRX9579 | BOSTON ROAD OVER HUTCHINSON RIVER BIN: 2229579 | USEFUL LIFE EXTENSION | 100 112 | HB-1070 |  |  | BOSTON POST ROAD OVER HUTCHINSON RIVER ÝBIN: 2229579 | 2019 | 185832 | 1628.09 | 500 | 0 | 37600 | 0 | 0 | 0 | 39728.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | BXECONDEV | FA - BX Council for Economic Devel. - Streetscape Furniture | COMMERCIAL DEVELOPMENT | 100 | ED-D384 |  |  | BRONX COUNCIL FOR ECONOMIC DEVELOPMENT-STREETSCAPE FURNITURE | 2019 | 1430 | 754.05 | 88 | 0 | 0 | 0 | 0 | 0 | 842.05 | 38.29 | 0 | 0 | 0 | 0 | 0 | 0 | 38.29
20190425 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | CTYISLBRD | Reconstruction of City Island Access Bridge | RECONSTRUCTION OF FERRY TERMINAL FACILITIES | 100 | FA-0021 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | RECON CITY ISLAND ACCESS BRIDGE | 2019 | 5180 | 955.21 | 5856 | 0 | 0 | 4995 | 0 | 0 | 11806.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HB107003E | HUTCHINSON PKWY BRIDGE/HUTCHINSON - PAINTING | BRIDGE PAINTING | 100 110 | HB-1070 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | HUTCHINSON PKWY - PAINTING | HUTCHINSON PKWY BRIDGE/HUTCHINSON - PAINTING | 2019 | 16477 | 12448.92 | 731 | 178 | 0 | 0 | 0 | 0 | 13357.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA06672 | EAST 174TH ST/SHERIDAN EXPWY AMTRAK BIN# 2066720 | FAIR BRIDGES | 100 | HB-6672 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | EAST 174TH ST/SHERIDAN EXPWY AMTRAK BIN# 2066720 | EAST 174TH ST/SHERIDAN EXPWY AMTRAK BIN# 2066720 | 2019 | 14670 | 0 | 3720 | 6269 | 0 | 0 | 14330 | 116621 | 140940 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA24138 | Pelham Bay Park Equestrian over Amtrak- CSX BIN 2241380 | FAIR BRIDGES | 100 | P-0508 |  | PELHAM BAY PARK EQUESTRIAN OVER AMTRAK- CSX BIN 2241380 | PELHAM BAY PARK EQUESTRIAN OVER AMTRAK- CSX BIN 2241380 | 2019 | 41329 | 0 | 1210 | 1401 | 0 | 3360 | 35358 | 0 | 41329 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA24180 | East 183rd St over MNRR Har BIN 2241800 | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 100 | HB-1139 |  | EAST 183RD ST OVER MNRR HAR BIN 2241800 | EAST 183RD ST OVER MNRR HAR BIN 2241800 | 2019 | 22339 | 0 | 710 | 1054 | 0 | 2100 | 18839 | 0 | 22703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA24181 | East 188th St over MNRR Har BIN 2241810 | FAIR BRIDGES | 100 | HB-1172 |  | EAST 188TH ST OVER MNRR HAR BIN 2241810 | EAST 188TH ST OVER MNRR HAR BIN 2241810 | 2019 | 30967 | 0 | 1092 | 1208 | 8967 | 20000 | 0 | 0 | 31267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA24245 | EAST 233RD ST/ BRONX RIVER BIN # 2242459 | FAIR BRIDGES | 100 | HB-1012 HB-0215 |  | EAST 233RD ST/ BRONX RIVER | EAST 233RD ST/ BRONX RIVER BIN # 2242459 | 2019 | 24927 | 0 | 0 | 1572 | 1150 | 2876 | 20134 | 0 | 25732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX1086 | WESTCHESTER AVE BR OVER HUTCH RIVER PKWY 2-075837 | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 110 111 | HB-1086 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | WESTCHESTER AVE BRIDGE | 2019 | 27909 | 24403.85 | 3094 | 5867 | 2100 | 0 | 0 | 0 | 35464.85 | 44388 | 344 | 0 | 0 | 0 | 0 | 0 | 44732
20190425 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX1103 | CONCOURSE VLGE AVE/ M-N 2-24159-0 | FAIR BRIDGES | 104 | HB-1103 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  |  | 2019 | 10949 | 329.79 | 1088 | 2592 | 0 | 0 | 3342 | 42717 | 50068.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX1127 | RECON PELHAM PKWY BRIDGE OVER HUTCHINSON PKWY 2-07584-9 | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 110 111 | HB-1012 HB-1127 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  |  | 2019 | 10870 | 7999.47 | 0 | 172 | 5543 | 42806 | 0 | 0 | 56520.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX1131 | BRUCKNER EXP / WESTCHESTER CREEK 1-066510 | FAIR BRIDGES | 109 110 | HB-1131 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  |  | 2019 | 57008 | 118450.53 | 1006 | 5168 | 0 | 0 | 0 | 0 | 124624.53 | 162685.7 | 0 | 1513 | 0 | 0 | 0 | 0 | 164198.7
20190425 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX1148B | SHORE ROAD BRIDGE / HUTCHINSON RIVER 2-240200 | FAIR BRIDGES | 110 | HB-1148 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | N/A |  | 2019 | 113110 | 13642.74 | 0 | 266 | 1150 | 42680 | 201731 | 0 | 259469.74 | 0 | 0 | 0 | 0 | 0 | 55269 | 0 | 55269
20190425 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX1164 | CITY ISLAND / EASTCHESTER BAY 2-24021-0 | FAIR BRIDGES | 110 | HB-1164 HB-0061 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | N/A |  | 2019 | 73206 | 35985.13 | 5506 | 1977 | 0 | 0 | 0 | 0 | 43468.13 | 94673.4 | 0 | 0 | 0 | 0 | 0 | 0 | 94673.4
20190425 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX1190 | GRAND CONCOURSE / METRO NORTH RR HUD2-24140-9 | FAIR BRIDGES | 104 | HB-1190 TF-0002 TF-0502 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | NA |  | 2019 | 16514 | 6860.35 | 16816 | 46485 | 0 | 0 | 0 | 0 | 70161.35 | 0 | 0 | 1601 | 0 | 0 | 0 | 0 | 1601
20190425 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX1215 | E. 175TH ST/METRO NORTH RR HAR 2-24174-0 TD PKG 1 | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 100 105 | HB-4174 HB-1012 TF-0002 TF-0502 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | E. 175TH ST/METRO NORTH RR HAR 2-24174-0 | E. 175TH ST/METRO NORTH RR HAR 2-24174-0 TD PKG 1 | 2019 | 5799 | 3759.33 | 14148 | 1872 | 6059 | 0 | 0 | 0 | 25838.33 | 0 | 124 | 0 | 0 | 0 | 0 | 0 | 124
20190425 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX1460 | WEST TREMONT AVENUE OVER METRO NORTH RR BIN:2241460 | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 100 105 | HB-4146 |  |  | WEST TREMONT AVENUE OVER METRO NORTH RR ÝBIN:2241460 | 2019 | 27508 | 6698.17 | 500 | 9147 | 41018 | 0 | 0 | 0 | 57363.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX156 | E 156TH ST BRIDGE OVER ACCESS TO HOUSING (BIN 2270030) | FAIR BRIDGES | 100 101 | HB-7003 |  | RECONSTRUCTION OF E 156TH ST BRIDGE OVER ACCESS TO HOUSING (BIN 2270030) | RECONSTRUCTION OF E 156TH ST BRIDGE OVER ACCESS TO HOUSING (BIN 2270030) | 2019 | 9916 | 0 | 1386 | 4114 | 0 | 0 | 7500 | 52500 | 65500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX163 | 5 Bridges - Melrose, Bronx | FAIR BRIDGES | 100 101 | HB-0163 HD-0098 SE-0002X |  | FIVE BRIDGES - MELROSE, BRONX | FIVE BRIDGES - MELROSE, BRONX | 2019 | 14751 | 17804.84 | 6310 | 406 | 0 | 0 | 0 | 0 | 24520.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX180 | E. 180TH ST OVER METRO NORTH RR HAR (BIN 2-24179-0) | FAIR BRIDGES | 100 106 | HB-1010 TF-0002 TF-0502 WM-0001 |  | E. 180TH ST OVER METRO NORTH RR HAR (BIN 2241790) | E. 180TH ST OVER METRO NORTH RR HAR (BIN 2241790) | 2019 | 8120 | 3452.94 | 24476 | 7499 | 0 | 0 | 0 | 0 | 35427.94 | 0 | 2527 | 0 | 0 | 0 | 0 | 0 | 2527
20190425 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX199 | E153RD ST BR AT PARK AVE OVER RR | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 101 104 | HB-0199 HB-0061 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | THE WORK CONSISTS OF DEMOLITION OF THE EAST 153RD STREET BRIDGE OVER TNORTH COMMUTER RAILROAD IN THE BORO OF THE BRONX THE BRIDGE CONSISTS ORUSS SPANS, ONE OF WHICH IS LOCATED OVER ELECTRIFIED RAILROAD TRACKS TINCLUDES REMOVAL OF THE EXISTING BRIDGE SUBSTRUCTURE, AND CONSTRUCTIONRIDGE APPROACH ALTERATIONS A 6 INCH DIAMETER WATER SUPPLY PIPE TO METRS FACILITIES, WHICH IS ATTACHED TO THE SPAN OVER THE RAILROAD, IS TO BD BY A NEW 6 INCH PIPE INSERTED IN A 12 INCH SLEAVE JACKED UNDER THE RRACKS DEMO IS PHASE 1 AND RECON IS PHASE 2 THE FUNDING IS 100% CITY | 2019 | 121223 | 22109.71 | 0 | 500 | 3000 | 0 | 2155 | 5822 | 33586.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX2370 | REHAB GRAND CONCOURSE BIN 2242370 | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 100 101 104 105 107 | HB-1070 |  |  | REHAB GRAND CONCOURSE BIN 2242370 | 2019 | 17721 | 0 | 0 | 0 | 2077 | 0 | 3298 | 23302 | 28677 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX644S | MADISON AVE BR - REHAB OF ELECTRICAL AND MECHANICAL SYSTEM | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 101 104 | HB-0644 HB-0215 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | MAIDISON AVE BR - SEISMIC RETROFITTING & REHABILITATION | MADISON AVE BR - SEISMIC RETROFITTING & REHABILITATION | 2019 | 43944 | 20981.59 | 3838 | 6836 | 0 | 0 | 0 | 0 | 31655.59 | 21360 | 0 | 40 | 0 | 0 | 0 | 0 | 21400
20190425 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR19A | Citywide Milling - Bronx | PRIMARY STREET RESURFACING | 100 | HW-0002X |  |  | CITYWIDE MILLING- BRONX | 2019 | 5857 | 0 | 2424 | 6084 | 0 | 0 | 0 | 0 | 8508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWCWSTPR | NY RESTORATION PROJECT - DEVELOP & DESIGN STREET PIER | PRIMARY STREET RECONSTRUCTION |  | HW-X001 HW-D105 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | NY RESTORATION PROJECT - DEVELOP & DESIGN STREET PIER | 2019 | 2750 | 0 | 0 | 0 | 0 | 0 | 2750 | 0 | 2750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX006-01 | Henwood Place Step Street | PRIMARY STREET RECONSTRUCTION | 100 | HW-0211 HW-X006 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | HENWOOD PLACE STEP STREET | HENWOOD PLACE STEP STREET | 2019 | 9700 | 0 | 385 | 1000 | 0 | 0 | 8315 | 0 | 9700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX100SBC | South Bronx East-West Crosstown SBS | PRIMARY STREET RECONSTRUCTION | 100 | HW-1684 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | SOUTH BRONX EAST-WEST CROSSTOWN SBS | SOUTH BRONX EAST-WEST CROSSTOWN SBS | 2019 | 7750 | 0 | 0 | 523 | 0 | 48085 | 0 | 0 | 48608 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX402 | Bruner and Ely | PRIMARY STREET RECONSTRUCTION | 100 | HW-0001X | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | BRUNER AND ELY | BRUNER AND ELY | 2019 | 12506 | 0 | 1400 | 0 | 0 | 0 | 11106 | 0 | 12506 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX404 | Southern Bronx Multi-Site Safety Improvements | PRIMARY STREET RECONSTRUCTION | 100 | HW-0001X |  | SOUTHERN BRONX MULTI-SITE SAFETY IMPROVEMENTS | SOUTHERN BRONX MULTI-SITE SAFETY IMPROVEMENTS | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 5128 | 0 | 5128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX405 | Southern Blvd Pedestrian and Bike Improvements | PRIMARY STREET RECONSTRUCTION | 100 | HW-0001X |  | SOUTHERN BLVD PEDESTRIAN AND BIKE IMPROVEMENTS (BEDFORD PARK BLVD TO E 179TH ST) | SOUTHERN BLVD PEDESTRIAN AND BIKE IMPROVEMENTS (BEDFORD PARK BLVD TO E 179TH ST) | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 9482 | 0 | 9482 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX711 | Bronx River Greenway @ 233rd St | PRIMARY STREET RECONSTRUCTION | 100 | HW-0001X | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | BRONX RIVER GREENWAY @ 233RD ST. | BRONX RIVER GREENWAY @ 233RD ST. | 2019 | 750 | 0 | 0 | 0 | 0 | 0 | 2625 | 0 | 2625 | 0 | 0 | 0 | 0 | 0 | 750 | 0 | 750
20190425 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWXJEROME | Jerome Avenue Safety Improvements | PRIMARY STREET RECONSTRUCTION | 100 | HW-0001 |  |  | JEROME AVENUE SAFETY IMPROVEMENTS | 2019 | 0 | 0 | 0 | 0 | 0 | 8553 | 0 | 0 | 8553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWXP136D | Grand Concourse Phase 5 | PRIMARY STREET RECONSTRUCTION | 100 | HW-0001X |  | GRAND CONCOURSE PHASE 5 | GRAND CONCOURSE PHASE 5 | 2019 | 54000 | 0 | 0 | 6443 | 0 | 47728 | 0 | 0 | 54171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | SANDBULK2 | Reconstruction of Vincent Ave Bulkhead - Hurricane Sandy | PRIMARY STREET RECONSTRUCTION | 100 | HW-D105 HW-0001X | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | RECONSTRUCTION OF VINCENT AVE BULKHEAD - HURRICANE SANDY | RECONSTRUCTION OF VINCENT AVE BULKHEAD - HURRICANE SANDY | 2019 | 104 | 0 | 0 | 0 | 0 | 0 | 136 | 12 | 148 | 0 | 0 | 0 | 0 | 0 | 0 | 92 | 92
20190425 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | TFD503X21 | CLAY AV.HISTORIC DISTRICT OLD-STYLE ST LAMP BET. E165& 167TH | INSTALLATION OF LAMPPOSTS AND LUMINAIRES | 100 104 | TF-D503 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | CLAY AV. HSITORIC DISTRICT OLD-STYLE LAMP BET. E165& 167TH | CLAY AV. HSITORIC DISTRICT OLD-STYLE LAMP BET. E165& 167TH | 2019 | 200 | 73.18 | 0 | 127 | 0 | 0 | 0 | 0 | 200.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | TFX50301 | GRAND CONCOURSE DECORATIVE STREET LIGHTING | INSTALLATION OF LAMPPOSTS AND LUMINAIRES | 100 101 104 105 107 | TF-X503 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | GRAND CONCOURSE DECORATIVE STREET LIGHTING | GRAND CONCOURSE DECORATIVE STREET LIGHTING | 2019 | 250 | 654.17 | 0 | 0 | 0 | 177 | 0 | 0 | 831.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | TRANSBCTY | Reconstruction Transfer Bridge Structure at City Island | RECONSTRUCTION OF FERRY TERMINAL FACILITIES | 100 | FA-0021 |  |  | RECONSTRUCT TRANSFER BRIDGE STRUCTURE AT CITY ISLAND | 2019 | 3400 | 0 | 0 | 340 | 0 | 3060 | 0 | 0 | 3400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | GXBXGI-01 | Bronx Parkland Green Infrastructure Retrofits | LAND ACQUISITION AND TREE PLANTING | 100 | WP-0169 P-D021 |  | BRONX PARKLAND GREEN INFRASTRUCTURE RETROFITS | BRONX PARKLAND GREEN INFRASTRUCTURE RETROFITS | 2019 | 2270 | 284.14 | 212 | 1537 | 4216 | 149 | 0 | 0 | 6398.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | HIF-1FSPB | Franz Sigel Park Ballfields-Install BallField Lighting | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | ED-0075 P-D021 |  | GERARD AVE., WALTON AVE., GRAND CONCOURSE BET. E. 151 ST., E. 153 ST.AND E. 158 ST IN THE BRONX | FRANZ SIGEL PARK BALLFIELD LIGHTING | 2019 | 9614 | 0 | 7000 | 0 | 0 | 0 | 2500 | 0 | 9500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | NDF-BRPLG | NDF-Bridge Playground | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 104 105 | ED-0384 P-X245 P-D021 |  | HARLEM RIVER BETWEEN W 175 STREET AND ALEXANDER HAMILTON BRIDGE | BRIDGE PLAYGROUND | 2019 | 1575 | 36 | 106 | 0 | 2267 | 202 | 0 | 0 | 2611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | NDF-CPFSP | NDF-CORPORAL FISCHER PLAYGROUND ( X269) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 104 | ED-0384 |  | NELSON AVE BET. W169 STREET AND W. 170 ST BOROUGH OF THE BRONX | CORPROAL FISHCER PLAYGROUND CONSTRUCTION | 2019 | 4642 | 60 | 384 | 0 | 3455 | 803 | 0 | 0 | 4702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | NDF-DVDSO | Neighborhood Dev. Fund-1801 Davidson | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | ED-0384 |  | BRONX | NEIGHBORHOOD DEV. FUND-1801 DAVIDSON | 2019 | 11233 | 0 | 0 | 919 | 0 | 10314 | 0 | 0 | 11233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | NDF-GRANT | NDF-Grant Park X271-119M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 104 | ED-0384 P-X245 |  | EAST 170 STREET BET SHERIDAN AVENUE AND MORRIS AVENUE | NDF-GRANT PARK -NEW DEVELOPMENT | 2019 | 25717 | 0 | 2103 | 0 | 23614 | 500 | 0 | 0 | 26217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | NDF-MORTN | NDF-MORTON PLAYGROUND RECONSTRUCTION (X001A) | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 100 105 107 | ED-0384 |  | MORTON PL & UNIVERSITY AVE BOROUGH OF BRONX | RECONSTRUCTION OF MORTONPLAYGROUND USIING NDF FUNDS | 2019 | 5216 | 63 | 422 | 0 | 4731 | 0 | 0 | 0 | 5216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-100CDAR | Cedar Playground - RC C/S X111-114M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 105 | P-X245 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | CEDAR PLGD, THE BRONX | CEDAR PLGD RC | 2019 | 1200 | 907.24 | 0 | 0 | 0 | 0 | 150 | 0 | 1057.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-100PBSG | Pelham Bay Park Sensory Garden X039-118M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 100 | P-D021 |  |  | PELHAM BAY PARK SENSORY GARDEN | 2019 | 760 | 100 | 0 | 505 | 45 | 0 | 0 | 0 | 650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-101BPAR | Brook Park - sitting area & comfort station | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 104 | P-D021 P-X245 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | BRONX | BROOK PARK RECON SITTING AREA AND COMFORT STATION. | 2019 | 1850 | 178 | 0 | 0 | 0 | 0 | 0 | 884 | 1062 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-101LZDA | Lozada Park Renovation- New play equip.,spray shower, swings | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 101 | P-0245X |  | E 135 ST BET. ALEXANDER AV AND WILLIS AVE IN THE BRONX | LOZADA PARK RENOVATION - NEW PLAY EQUIPMENT, DRINKING FOUNTAINS, SPRAY SHOWERS, SWINGS | 2019 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-101MAR2 | St. Mary's Plgd West - ADA CS (X045-118M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-D021 P-0505 |  |  | ST MARY'S PLGD WEST - ADA CS | 2019 | 0 | 136 | 0 | 2457 | 243 | 0 | 0 | 0 | 2836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-101MBRO | Millbrook Plgd- basketball & handball courts- X182-115M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 101 | P-X245 P-D021 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | MILLBROOK PLAYGROUND, BRONX | RECONSTRUCT BASKETBALL & HANDBALL COURTS | 2019 | 1160 | 1380.25 | 0 | 0 | 0 | 75 | 0 | 0 | 1455.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-101PULP | Pulaski Park Reconstruction- X041-118M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-D021 P-0510 |  |  | PULASKI PARK RECONSTRUCTION | 2019 | 1750 | 409.77 | 0 | 2260 | 226 | 0 | 0 | 0 | 2895.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-101STMH | ST. MARY'S PK REC CTR HVAC X045-116M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-1250 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | ST. MARY'S PK REC CTR HVAC | 2019 | 1500 | 2343.11 | 34 | 0 | 0 | 149 | 0 | 0 | 2526.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-101STMR | St Mary's plgd (w) ph1 recon w/equip, landscape-X045-215MA | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-X245 P-D021 P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | ST MARY'S PLGD, BRONX | RECON PLGD TO INCLUDE NEW PLDG EQUIP, SAFETY SURFACING, DRINKING WATER, LANDSCAPING AREA, BENCHES AND SWINGS | 2019 | 1500 | 3355.41 | 539 | 0 | 0 | 278 | 0 | 0 | 4172.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-101WLSP | Willis Plgd Renov. New Equipment, Safety Surfacing &Fountain | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-D021 |  |  | WILLIS PLGD RENOV. NEW EQUIPMENT, SAFETY SURFACING &FOUNTAIN | 2019 | 3410 | 227 | 47 | 0 | 0 | 2257 | 196 | 0 | 2727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-102BRPP | Bill Rainey Park--Lights For Baseball Field & Score Board | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-D021 |  |  | BILL RAINEY PARK--LIGHTS FOR BASEBALL FIELD & SCORE BOARD | 2019 | 1364 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-102CEME | Bronx River - Concrete Plant Park - XG-31700-201M, 205M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 102 | WM-0011 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BRONX | CEMENT PLANT | 2019 | 10241 | 6374.89 | 45 | 0 | 0 | 0 | 0 | 0 | 6419.89 | 4000.48 | 0 | 0 | 0 | 0 | 0 | 0 | 4000.48
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-102HNT2 | Hunts Point - Riverside Park - Dock Repair | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 102 | P-D021 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | HUNTS POINT RIVERSIDE PARK | HUNTS POINT RIVERSIDE PARK DOCK REPAIR PH II | 2019 | 100 | 17 | 0 | 0 | 0 | 0 | 350 | 0 | 367 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-102HTRC | Hunts Point Rec Center - Construction of fitness room | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 102 | P-D021 |  | SPOFFORD AV BET. FAILE ST AND HUNTS POINT AVE IN THE BRONX | HUNTS POINT RECREATION CENTER -- CONSTRUCTION OF FITNESS ROOM. | 2019 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-102MNDA | Manida Park-Lighting & Scoreboard Renovation | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-D021 P-0245X |  |  | MANIDA PARK-LIGHTING & SCOREBOARD RENOVATION | 2019 | 382 | 0 | 0 | 0 | 0 | 0 | 1986 | 0 | 1986 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-102PL52 | CPI PH1 - Playground 52 - Reconstruct Kelly Plgd X179-112M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 102 | P-D021 P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | PLAYGROUND 52 | PLAYGROUND 52 - RECONSTRUCT PARK | 2019 | 500 | 3654.73 | 227 | 0 | 0 | 8 | 0 | 0 | 3889.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-102RJPP | Rev. J Polite Plgd-Recon of synthetic turf | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 102 | P-0510 |  | REV JAMES POLITE AV TO INTERVAL AV BET. E 167 ST AND HOME ST BRONX | RECON OF SYNTHETIC TURF AT REV. J. POLITE PLAYGROUND | 2019 | 3736 | 0 | 0 | 0 | 400 | 2900 | 0 | 0 | 3300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103CGJF | CS-134-Fence and Water Supply- (X340-116MA) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 103 | P-D021 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | CS134 COMMUNITY GARDEN AND JACKSON FOREST COMMUNITY GARDEN | ONSTRUCTION OF PERIMETER FENCE & WATER SUPPLY IN CS134 COMMUNITY GARDEN AND WATER SUPPLY IN JACKSON FOREST COMMUNITY GARDEN | 2019 | 841 | 218.9 | 685 | 0 | 81 | 0 | 0 | 0 | 984.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103CPB5 | Crotona Park - ballfield #5 * X010-115M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 100 103 | P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | BOROUGH OF THE BRONX | CROTONA PARK BALLFIELD# 5 | 2019 | 1000 | 3749.47 | 262 | 0 | 0 | 0 | 531 | 0 | 4542.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103CPEW | CROTONA PARK GREENWAY - X010-105M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 103 | P-0697 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | BRONX | CROTONA PARK ENVIRONMENTAL WORK | 2019 | 1035 | 244.92 | 0 | 0 | 0 | 0 | 0 | 0 | 244.92 | 519.05 | 0 | 0 | 0 | 0 | 80 | 0 | 599.05
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103CRCS | CROTONA PK COMFORT STATION X010-214M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 100 103 | P-D021 P-0245X | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | CROTONA PARK | CROTONA PARK: COMFORT STATION # 10 - RENOV TO THE COMFORT STATION IN PLGD# 10 INCLUDING NEW UTILITIES AND ADA ACCESSIBILITY | 2019 | 840 | 233.05 | 1463 | 0 | 0 | 0 | 0 | 0 | 1696.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103CRO1 | CROTONA PK LIGHTING FOR B/F X010-116M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 100 103 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BOROUGH OF THE BRONX | CROTONA PARK | 2019 | 250 | 1678.54 | 0 | 0 | 0 | 0 | 316 | 0 | 1994.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103DPLS | Drew Playground Security Lighting X021-119M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-0245X P-1018 |  |  | SECURITY LIGHTING | 2019 | 420 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103RRP2 | Rock and Roots Park - Estella Diggs Park Phase II X243-111M | NEIGHBORHOOD PARKS AND PLAYGROUNDS |  | P-X245 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | ROCKS & ROOTS PARK | ROCK AND ROOTS PARK - PHASE II INSTALL PERIMETER FENCING, CIRCULATIONPATHS AND LANDSCAPING | 2019 | 1313 | 2151.42 | 14 | 0 | 0 | 0 | 260 | 0 | 2425.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103WPBC | Waring Plgd Basketball Courts Recon (X002-118M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-D021 P-0245X P-X245 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | WARING PLGD BASKETBALL COURTS RECON (X002- | 2019 | 500 | 487 | 46 | 0 | 0 | 3054 | 0 | 0 | 3587 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 500
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104CAGS | Mullaly Park Recr Center- bronze doors X034-108MA OMBP | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 100 104 | P-D021 P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | JEROME AVE., MCCLELLAN ST. | MULLAY PARK REC CENTER CAGES & SPINKLERS PHASE II | 2019 | 176 | 131.76 | 0 | 0 | 0 | 0 | 142 | 0 | 273.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104CLMT | Claremont Park Improvements | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 100 | P-0801 P-D021 |  | CLAY AVE., ANTHONY AVE. BET. MOUNT EDEN PKWY. AND E. 170 ST IN THE BRONX | CLAREMONT PARK IMPROVEMENTS | 2019 | 2418 | 0 | 0 | 0 | 0 | 0 | 0 | 2418 | 2418 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104FIS2 | Cons of Fish Passage Twin Dams | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-X245 |  | CONS OF FISH PASSAGE TWIN DAMS | CONS OF FISH PASSAGE TWIN DAMS | 2019 | 250 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104GBLE | Goble Playground- new BBall equip., swings, handball court | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 104 | P-D021 |  | GOBLE PL BET. INWOOD AV AND MACOMBS RD IN THE BRONX | GOBLE PLAYGROUND -- NEW BASKETBALL EQUIPMENT, SWINGS, AND HANDBALL COURT. | 2019 | 1750 | 0 | 0 | 0 | 0 | 0 | 0 | 1750 | 1750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104GPPV | Grant Avenue Park - Reconst of playground ( X271-115M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 104 | P-0245X | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | BRONX | CHARLTON GARDEN PHASE II PASSIVE AREA | 2019 | 2000 | 3490.86 | 0 | 0 | 352 | 0 | 0 | 0 | 3842.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104HGBG | Highbridge Park - step streets/park ldscape X120-110M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 104 105 | P-D021 P-X245 P-0245X | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | W 170 STREET UNIVERSITY AVE & HIGHBRIDGE | HIGHBRIDGE PARK STEPSTREETS | 2019 | 200 | 320.04 | 206 | 3636 | 376 | 0 | 0 | 0 | 4538.04 | 103 | 0 | 697 | 0 | 0 | 0 | 0 | 800
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104HPRM | Bridge Park-Highbridge Greenway promenade | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 104 | P-X245 P-D021 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | HIGHBRIDGE IN THE BRONX | EXPANSION OF THE GREENWAY TO IMMEDIATE NORTH OF HIGHBRIDGE FOR A SMALL PARK AREA AND EVENTUAL NON-MOTORIZED SMALL BOAT ACCESS TO THE RIVER | 2019 | 600 | 50 | 508 | 0 | 0 | 1692 | 0 | 0 | 2250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104JKIL | Joyce Kilmer Park - Fencing (X028-114M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 104 | P-0245X P-D021 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | JOYCE KILMER PARK, THE BRONX | JOYCE KILMER PARK FENCING | 2019 | 886 | 1114.79 | 0 | 0 | 0 | 17 | 0 | 0 | 1131.79 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 22
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104JRME | Jerome Playground S- Handball courts renovation | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 104 | P-X245 P-D021 |  | S/S CROSS BRONX EXWY BET. TOWNSEND AV AND JEROME AVE IN THE BRONX | JEROME PLAYGROUND SOUTH -- HANDBALL COURTS NEED TO BE RENOVATED | 2019 | 1800 | 0 | 0 | 200 | 0 | 0 | 0 | 1800 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104NELP | Nelson Bleacher Reconstruction-X168-117M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-D021 |  |  | NELSON PLAYGROUND RECONSTRUCTION | 2019 | 500 | 445.21 | 0 | 0 | 0 | 146 | 0 | 0 | 591.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-105DAVD | Davidson Playground renovation | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 105 | P-D021 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | DAVIDSON PLGD, THE BRONX | DAVIDSON PLGD - RENOVATION OF THE ENTIRE PLAYGROUND | 2019 | 1200 | 200 | 0 | 0 | 0 | 0 | 0 | 600 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-105GALO | Galileo Playground - bring surface area to grade | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 105 | P-D021 |  | MACOMBS RD BET. W 176 ST AND W 175 ST. IN THE BRONX | GALILEO PLAYGROUND -- FILL AND COMPACT SUBSIDENCE TO BRING SURFACE AREA TO GRADE. | 2019 | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 1100 | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-105HOPE | Mount Hope Garden (X274-113M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 105 | P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | BORUOGH OF THE BRONX | MOUNT HOPE GARDEN | 2019 | 1000 | 5027.15 | 485 | 0 | 0 | 0 | 0 | 0 | 5512.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-106MAPE | CPI Phase 2-Mapes Ballfield-X289-118M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-0245X P-1018 |  |  | MAPES BALLFIELD | 2019 | 11379 | 897.49 | 0 | 8634 | 1178 | 0 | 0 | 0 | 10709.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-106QUAR | Quarry Ballfield-Cons of synthetic turf soccer fd-X263-119M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-0245X |  |  | QUARRY BALLFIELD - BRONX | 2019 | 7798 | 0 | 531 | 0 | 0 | 6769 | 0 | 0 | 7300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107CPFE | Classic Plgd in Van Cortlandt Park-Install Fitness Equipment | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 100 | P-X245 P-D021 |  |  | CLASSIC PLGD IN VAN CORTLANDT PARK-INSTALL FITNESS EQUIPMENT | 2019 | 272 | 36 | 0 | 525 | 0 | 0 | 0 | 450 | 1011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107DPDR | Devoe Park- Cons of a Dog Run X013-218M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-D021 |  |  | DEVOE PARK-DOG RUN AT ST JAMES PARK AND DEVOE PARK | 2019 | 840 | 109 | 0 | 0 | 600 | 0 | 0 | 0 | 709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107KOSS | Kossuth Playground Recon (X033-118M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-D021 P-X245 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | KOSSUTH PLAYGROUND RECON (X033- | 2019 | 660 | 210 | 0 | 3172 | 288 | 0 | 0 | 0 | 3670 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107PPV1 | Poe Park - Poe Cottage - ADA ramp | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-D021 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | POE ARK, BRONX | POE PARK | 2019 | 444 | 690.09 | 0 | 0 | 307 | 0 | 0 | 0 | 997.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107SJDR | St. James Park--Dog Run- X044-118M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-D021 |  |  | ST. JAMES PARK--DOG RUN | 2019 | 894 | 118 | 0 | 0 | 650 | 0 | 0 | 0 | 768 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107SJHV | ST. JAMES PARK HVAC X044-113M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 107 | P-1250 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | ST. JAMES PARK IN BRONX | HVAC SYSTEM AT ST. JAMES PARK | 2019 | 840 | 449.49 | 1467 | 0 | 0 | 466 | 0 | 0 | 2382.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107WBSK | Williamsbridge Oval const Skate Park- X104-115M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | WILLIAMSBRIDGE OVAL CONST SKATE PARK, BRONX | WILLIAMSBRIDGE OVAL CONST SKATE PARK, BRONX | 2019 | 750 | 1297.92 | 0 | 0 | 0 | 89 | 0 | 0 | 1386.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107WHLN | Whalen Park Construct into Playground- X180-114M | NEIGHBORHOOD PARKS AND PLAYGROUNDS |  | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | WHALEN PARK CONSTRUCT INTO PLAYGROUND | 2019 | 1275 | 2435.34 | 71 | 0 | 0 | 0 | 0 | 0 | 2506.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108EWNP | Ewen Park Installation of adult fitness equipment | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 108 | P-D021 |  | JOHNSON AV, W 232 ST, RIVERDALE AVE IN THE BRONX | ADULT FITNESS EQUIPMENT AT EWEN PARK -- INSTALLATION OF ADULT FITNESSEQUIPMENT AT EWEN PARK | 2019 | 910 | 0 | 0 | 0 | 0 | 801 | 0 | 0 | 801 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108FTFR | Washington's Walk Fort Four Plgd comfort station- X038-118M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-X245 P-D021 P-0505 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | RESERVOIR AVENUE & SEDWICK AVENUE | CONSTRUCT NEW COMFORT STATION | 2019 | 700 | 90 | 0 | 0 | 3331 | 289 | 0 | 0 | 3710 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108HHPK | Henry Hudson Park basketball court renovation (X080-115M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-D021 P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | HENRY HUDSON PARK, BRONX | HENRY HUDSON PARK BASKETBALL COURT RENOVATION | 2019 | 1000 | 393.12 | 549 | 0 | 0 | 205 | 0 | 0 | 1147.12 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 1500
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108RIVE | RIVERDALE PARK-WETLANDS & SLOPES / X142-101M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 108 | P-0245X |  | HUDSON RIVER, W 254 ST, PALISADE AVE, W 232 ST | RECONSTRUCTION OF A FRESHWATER WETLAND AND THE ADJACENT SLOPES | 2019 | 243 | 157.55 | 0 | 0 | 0 | 0 | 0 | 0 | 157.55 | 0 | 0 | 0 | 0 | 0 | 180 | 0 | 180
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108SETN | Seton Park soccer & ball field X201-113M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 108 | P-1018 P-D021 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | AT INDEPENDENCE AVE & W 232ST | SETON PARK SOCCER FIELD RESURFACE OF JR FIELD AT INDEPENDENCE AVE & W232ST | 2019 | 900 | 1062.69 | 0 | 0 | 282 | 0 | 0 | 0 | 1344.69 | 1046.09 | 1 | 0 | 0 | 0 | 0 | 0 | 1047.09
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108SKTE | Van Cortlandt Park - Skate park & Basketballl cou(X092-114M) | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 100 108 | P-D021 P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | SKATE PARK @ VAN CORTLANDT PARK | SKATE PARK PROJECT | 2019 | 1400 | 477.52 | 998 | 0 | 0 | 102 | 0 | 0 | 1577.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108SPBC | Seton Park Basketball Court Recon (X201- | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-0245X P-X245 P-D021 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | SETON PARK BASKETBALL COURT RECON (X201- | 2019 | 210 | 145 | 0 | 0 | 0 | 2040 | 0 | 0 | 2185 | 0 | 0 | 0 | 0 | 210 | 0 | 0 | 210
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108SPDU | Spuyten Duyvil Park - pond restoration- X171-116M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 108 | P-D021 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | PALISADE AVENUE, JOHNSON AVENUE AND EDSALL AVENUES | POND RESTORATION | 2019 | 170 | 747.78 | 0 | 0 | 145 | 0 | 0 | 0 | 892.78 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 600
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108VCBD | Van Cortlandt Pk. Tot Lot Recon (X092-115M) | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 100 | P-D021 P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | VAN CORTLANDT PARK CONST OF PLGD ON BDWAY, BRONX | VAN CORTLANDT PARK CONST OF PLGD ON BDWAY, BRONX | 2019 | 2263 | 549 | 2098 | 0 | 0 | 184 | 0 | 0 | 2831 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 500
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108VCIW | Van Cortlandt Park renovate Indian Fields (X092-215M) | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 100 | P-D021 P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | VAN CORTLANDT PARK RENOVATE INDIAN LAKE & WOODLAWN, BRONX | VAN CORTLANDT PARK RENOVATE INDIAN LAKE & WOODLAWN, BRONX | 2019 | 1500 | 539.13 | 943 | 0 | 0 | 318 | 0 | 0 | 1800.13 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 1000
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108VCPT | Van Cortlandt Park Trails Recon (X092- | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-0088 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | VAN CORTLANDT PARK TRAILS RECON (X092- | 2019 | 543 | 99 | 0 | 0 | 0 | 0 | 0 | 0 | 99 | 0 | 0 | 0 | 0 | 0 | 0 | 543 | 543
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108WWST | Strong Street Plg Reconstruction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-X245 P-D021 |  |  | STRONG STREET PLAYGROUND  RECONSTRUCTION OF PLAYGROUND | 2019 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 870 | 870 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-109NBLE | Noble Playground - RC Comfort Station X123 | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-D021 P-X245 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | NOBLE AVENUE BETWEEN BRONX RIVER AVENUE AND E. 177 STREET, BOROUGH OFBRONX | PHASE 2 RECONSTRUCT COMFORT STATION BUILDING WITH ADA ACCESSIBILITY | 2019 | 700 | 255 | 11 | 0 | 0 | 1389 | 0 | 0 | 1655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-109NOBE | Noble Playground Reconstruction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-D021 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | NOBLE AVE. BET. BRONX RIVER AV AND E 177 ST IN THE BRONX | NYC PARKS - NOBLE PLAYGROUND -- NOBLE PLAYGROUND RECONSTRUCTION | 2019 | 3000 | 0 | 0 | 0 | 0 | 2500 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-109PAR2 | Parque de los Ninos Ph II - track & BField X004A-114M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 109 | P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | PARQUES DE LOS NINOS, BRONX | INSTALLATION OF RUNNING TRACK AND MULTIPURPOSE BALL FIELDS | 2019 | 2000 | 3264.09 | 0 | 0 | 272 | 0 | 0 | 0 | 3536.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110CCCS | Co-Op City Park - Comfort Station | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-0505 |  |  | CO-OP CITY PARK - COMFORT STATION | 2019 | 4772 | 318 | 0 | 0 | 0 | 3220 | 280 | 0 | 3818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110CCTY | Co-Op City Park | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-0245X |  |  | CO-OP CITY PARK | 2019 | 14320 | 25 | 0 | 0 | 0 | 9780 | 720 | 0 | 10525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110CIDR | City Island Dog Run | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-D021 |  |  | CITY ISLAND DOG RUN | 2019 | 840 | 109 | 0 | 0 | 0 | 600 | 0 | 0 | 709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110MAN2 | Bartow Mansioon Structural Stabilization&Carriage House Roof | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-1018 |  |  | BARTOW PELL MANSION STRUCTURAL STABILIZATION AND CARRIAGE HOUSE ROOF RECONSTRUCTION | 2019 | 142 | 0 | 0 | 142 | 0 | 0 | 0 | 0 | 142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110MANS | PDF - BARTOW PELL MANSION - PORTIONS OF BUILDING X039-506M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 110 | P-X245 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BARTOW PELL MANSION, BRONX, NY | BARTOW PELL MANSION IMPROVEMENTS | 2019 | 385 | 2361.32 | 0 | 0 | 500 | 0 | 0 | 0 | 2861.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110PBBL | Pelham Bay Park Svc Bldg. Heating Recon. X039-115M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 100 | P-1018 P-1250 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | PELHAM BAY PARK SVC BLDG. HEATING RECON. X039-115M | PELHAM BAY PARK SVC BLDG. HEATING RECON. X039-115M | 2019 | 987 | 1535.01 | 5 | 0 | 0 | 132 | 0 | 0 | 1672.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110PFIT | Pelham bay Park - construction of fitness area X039-213M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 100 110 | P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | PELHAM BAY PARK, BOROUGH OF THE BRONX | CONSTRUCTION OF FITNESS CENTER IN PELHAM BAY PARK | 2019 | 500 | 1199.18 | 0 | 0 | 0 | 79 | 0 | 0 | 1278.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-111LPFE | Cons. of Adult Fitness Equip in Colucci Pk. (X122-117M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-D021 P-0245X |  |  | CONS. OF ADULT FITNESS EQUIP IN LORETO PK. (X122- | 2019 | 1299 | 415 | 999 | 0 | 0 | 100 | 0 | 0 | 1514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-111LRTO | Loreto Park - Recon Soccer field Asphalt to Turf (X163-118M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-0245X P-X245 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | LORETO PARK - RECON SOCCER FIELD ASPHALT TO TURF (X163- | 2019 | 1500 | 272 | 0 | 0 | 700 | 0 | 0 | 0 | 972 | 0 | 0 | 1300 | 0 | 0 | 0 | 0 | 1300
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-111VCPE | PWOB - Van Cortlandt Park Broadway Entrance Recon- X092-217M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | VAN CORTLANDT PARK BROADWAY ENTRANCE RECON | 2019 | 5040 | 640 | 5313 | 0 | 0 | 633 | 0 | 0 | 6586 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-111ZIMP | Zimmerman Playground Basketball Court Recon.-X087-118M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-D021 |  |  | ZIMMERMAN PLAYGROUND BASKETBALL COURT RECON. | 2019 | 500 | 146 | 0 | 0 | 0 | 0 | 0 | 2102 | 2248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-112AGNS | Agnes Haywood Park - basketball court & park house X169-114M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 112 | P-D021 P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | IN BRONX | AGNES HAYWOOD PK RENOVATE BASKETBALL CT & PKHOUSE | 2019 | 650 | 3625.98 | 42 | 0 | 0 | 175 | 0 | 0 | 3842.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-112LACE | BX River Shoelace Pk- Recon of Paths & Entrance (X004-117M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-X245 P-0963 P-1018 |  |  | THE SHOELACE PARK LINK IS A MULTI-BENEFIT PROJECT TO ENHANCE PEDESTRIAN AND BICYCLE CIRCULATION IN A 1.2-MILE LINK IN THE BRONX RIVER GREENWAY, TREAT STORMWATER RUNOFF FROM ADJACENT ROADWAYS INCLUDING THE BRONX RIVER PARKWAY TO REDUCE POLLUTION IN THE BRONX RIVER, AND COMMEMORATE THE HISTORIC ROUTE OF THE BRONX RIVER PARKWAY, IMPLEMENTING ELEMENTSOF THE MASTER PLAN FOR SHOELACE PARK ON THE BRONX RIVER GREENWAY. | 2019 | 3150 | 616.69 | 2273 | 0 | 0 | 0 | 0 | 0 | 2889.69 | 0 | 2520 | 0 | 0 | 0 | 0 | 0 | 2520
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-112SETW | Seton Falls Park Walkways Renovations X092-113M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 112 | P-D021 P-X245 |  | E. 233 ST. BET. SETON AVE. AND BAYCHESTER AVE. IN THE BRONX | SETON FALLS PARK WALKWAYS RENOVATIONS IN THE BRONX | 2019 | 1181 | 0 | 0 | 0 | 0 | 1181 | 0 | 0 | 1181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-112WKFD | Wakefield Park Reconstruction (X188-116M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-D021 P-X245 P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | WAKEFIELD PARK RECON | 2019 | 200 | 443.4 | 0 | 0 | 0 | 1954 | 0 | 0 | 2397.4 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 1000
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-113LLSF | Resurfacing of little league fields and sports field in CD13 | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-D021 |  | UNKNOWN | RESURFACING OF LITTLE LEAGUE FIELDS AND OTHER SPORTS FIELDS IN COUNCIL DISTRICT 13 | 2019 | 100 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-117CPBM | Crotona Park- Install Bluelight Monitors in CD17 | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 100 103 | P-D021 |  | CROTONA PARK NORTH TO SOUTH, FULTON AV TO SOUTHERN BLVD AND CROTONA PARK EAST IN THE BRONX | NYC PARKS (CROTONA PARK) -- FUNDS WILL GO TO INSTALL BLUELIGHT MONITORS THROUGHOUT CROTONA PARK IN CD17 | 2019 | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-118FOXP | FOX PLAYGROUND C/S X247-118M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-D021 |  |  | FOX PLAYGROUND C/S | 2019 | 3500 | 289 | 0 | 0 | 0 | 3220 | 280 | 0 | 3789 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1ANCH01 | Anchor Pk St.Mary's Park Ballfields &Dog Run Recon X045-318M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 100 | P-0568 |  | ST MARY'S STREET BETWEEN ST ANNS'S AVE AND JACKSON AVE BRONX | ANCHOR PARK ST. MARY'S PARK BALLFIELDS AND DOG RUN RECON | 2019 | 10450 | 0 | 8133 | 0 | 0 | 2189 | 0 | 0 | 10322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1ANCH02 | St. Mary's Anchor Pk Ph. 2-Amphi, Plaza &Pathways X045-218M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-0568 |  |  | ST. MARY'S ANCHOR PARK PHASE 2-AMPHITHEATER, PLAZA &PATHWAYS | 2019 | 17380 | 99.51 | 0 | 15932 | 1448 | 0 | 0 | 0 | 17479.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1ANCR01 | Anchor Parks - St. Mary's Reconstruction (X045-117M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CREATED 8/26/16...$30M (P-1018, FY19) FR. P-6CWANCR PER ANDREW E-MAIL... | 2019 | 31500 | 2897.58 | 169 | 50 | 0 | 0 | 0 | 0 | 3116.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1AQWALK | MLK Triangle/Aqueduct Walk X001-114M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 100 104 101 | WM-0011 P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | IN BRONX | MLK TRIANGLE/AQUEDUCT WALK XG-31950-109M | 2019 | 2000 | 2987.23 | 203 | 0 | 42 | 0 | 0 | 0 | 3232.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1ARAMEZ | Mezzanine dsgn & cons Aramark Bldg Shops & store X360-119M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-1018 P-0505 |  | 850 EAST 138TH STREET, BRONX | MEZZANINE DESIGN AND CONSTRUCTION AT ARAMARK BUILDING (CWS SHOPS AND STOREHOUSE) | 2019 | 559 | 0 | 6 | 0 | 403 | 0 | 0 | 0 | 409 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 150
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BCSPL1 | BRONX - ELEC OFFICIALS BLDG REQ - PLMB XG-308M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | WM-0011 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | BOROUGH OF THE BRONX | BUILDING REQUIREMENTS - PLMB | 2019 | 281 | 238.01 | 0 | 90 | 0 | 0 | 0 | 0 | 328.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BRTPEL | BARTOW PELL MANSION RESTORE THE ORANGERIE | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-X245 |  |  | BARTOW PELL MANSION RESTORATION OF THE ORENGERIE | 2019 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BRUCKN | Bruckner Soundview Greenway Connection - XG-31700-104M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 109 | P-0963 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BRONX RIVER | GREENWAY CONNECTION | 2019 | 2148 | 820.36 | 0 | 0 | 0 | 0 | 0 | 0 | 820.36 | 2086.53 | 238 | 0 | 0 | 0 | 0 | 0 | 2324.53
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BWBXP1 | Reconstruction of plgrs, Borough of Bronx (XG-508M) | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 100 | P-X245 P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | VARIOUS IN THE BRONX | RC OF PLGRDS | 2019 | 1236 | 1609.89 | 0 | 0 | 0 | 0 | 132 | 0 | 1741.89 | 81.5 | 0 | 0 | 0 | 0 | 130 | 0 | 211.5
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BWRCTR | WEST BX RECR CTR HVAC RC- X261-116M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 100 | P-1250 P-1018 |  |  | BX REC CTRS HVAC RC | 2019 | 1228 | 286.92 | 909 | 0 | 133 | 0 | 0 | 0 | 1328.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BXPFIT | Bronx Park - Adult Fitness Equipment Construction- X002-117M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-D021 P-0245X | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | BRONX PARK - ADULT FITNESS EQUIPMENT CONSTRUCTION | 2019 | 0 | 40 | 266 | 0 | 0 | 26 | 0 | 0 | 332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CHARLG | Charlton Garden - Phase II X086-108M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 103 | P-X245 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES | BRONX | CHARLTON GARDEN RECONSTRUCTION | 2019 | 1050 | 1696.74 | 0 | 0 | 0 | 0 | 230 | 0 | 1926.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPI134 | CPI PH2 - Playground 134 Reconstruction (X138-117M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-1018 |  |  | CPI PH3 - PLAYGROUND 134 RECONSTRUCTION (X138- | 2019 | 3270 | 139 | 0 | 3993 | 604 | 0 | 0 | 0 | 4736 | 469.07 | 0 | 31 | 0 | 0 | 0 | 0 | 500.07
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIBPG | CPI PH2 - Blackrock Plgd. Recon. (X205-116M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-1018 |  |  | CPI- RECONSTRUCTION OF BLACKROCK PLAYGROUND. | 2019 | 1500 | 2001.89 | 0 | 0 | 0 | 225 | 0 | 0 | 2226.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIBR2 | CPI PH2-174TH St.Plgd/BX River House-Plgd/Mini Pool X159-118 | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-1018 |  | CPI PH2 - 174TH ST. PLGD/BX RIVER HOUSE-PLAYGROUND/MINI POOL | CPI PH2 - 174TH ST. PLGD/BX RIVER HOUSE-PLAYGROUND/MINI POOL | 2019 | 0 | 0 | 4352 | 0 | 0 | 635 | 0 | 0 | 4987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIBR3 | CPI PH2-174TH St.Plgd/BX River House- Comfort Stat X159-218M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-1018 |  |  | CPI PH2-174TH ST. PLGD/BX RIVER HOUSE- COMFORT STATION | 2019 | 1516 | 0 | 8 | 1309 | 183 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIGAR | CPI PH2 - Garrison Playground (X106-117M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | ED-0075 HD-0098 P-D021 P-1018 P-X245 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | CPI PH 3 - GARRISON PLAYGROUND | 2019 | 7180 | 966 | 4835 | 0 | 0 | 874 | 0 | 0 | 6675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIHNT | CPI PH 1- Hunts Point Playground (X113-115M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | HUNTS POINT PLAYGROUND, BRONX | CPI - HUNTS POINT PLAYGROUND | 2019 | 1500 | 3873.56 | 13 | 0 | 227 | 0 | 0 | 0 | 4113.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPILCM | CPI Phase 1- Little Claremont Pk X299-116M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | WP-0169 P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | CPI PHASE 1- LITTLE CLAREMONT PK , BRONX | CPI PHASE 1- LITTLE CLAREMONT PK X299-116M | 2019 | 3808 | 3680.97 | 358 | 0 | 0 | 19 | 0 | 0 | 4057.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIOPG | CPI PH2 - Ogden Plimpton Plgd. Recons. (X287-116M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-1018 |  | CPI- OGDEN PLIMPTON PLGD. RECONS. (X287- | CPI- OGDEN PLIMPTON PLGD. RECONS. (X287- | 2019 | 1191 | 1642.11 | 0 | 0 | 0 | 238 | 0 | 0 | 1880.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIP52 | CPI - Plgd 52 (LII) Reconstruction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | CPI - RECON PROTION OF PLGD 52 LII, BRONX | CPI - RECON PROTION OF PLGD 52 LII | 2019 | 2500 | 4825.56 | 0 | 0 | 0 | 40 | 0 | 0 | 4865.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIPMT | CPI PH 2 - Plimpton Playground (X148A2-117M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-1018 WP-0169 |  |  | CPI PH 3 - PLIMPTON PLAYGROUND (X1482- | 2019 | 4436 | 485 | 3810 | 0 | 0 | 626 | 0 | 0 | 4921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIPRO | CPI Phase 2- Prospect Playground-X148H1-118M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-1018 |  |  | CPI PHASE 2- PROSPECT PLAYGROUND | 2019 | 6266 | 591.78 | 0 | 0 | 5075 | 693 | 0 | 0 | 6359.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIWPK | CPI PH2 - Walton Park Rcons. (X291- | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-1018 |  | CPI- WALTON PARK RCONS. (X291- | CPI- WALTON PARK RCONS. (X291- | 2019 | 1378 | 1925.89 | 0 | 0 | 0 | 201 | 0 | 0 | 2126.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CRNAPK | Crotona Park RC of the Nature Center X010-114M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 103 | P-D021 P-1018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | CROTONA PARK, BRONX | CROTONA PARK NATURE CTR - PH I EXTER & INTER RENOV | 2019 | 500 | 3491.48 | 21 | 0 | 0 | 517 | 0 | 0 | 4029.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CRO17A | Williamsbridge Oval Park - Recr Bldg X104-207M/507M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 100 107 | WM-0011 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | BX | PORTION OF PARK WORK TO INCLUDE: PERIMETER WALLS & FENCING WITH GATES, TRACK & FIELD, PLAYGROUND #1, PLAYGROUND #3, SENIOR AREA, ROLLER HOCKEY AREA/SKATE PARK, SLOPE STABILIZATION AND PROMENADE AND RECREATION CENTER SITE WORK. | 2019 | 3480 | 6619.42 | 0 | 210 | 0 | 0 | 0 | 0 | 6829.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CRO17B | WILLIAMSBRIDGE OVAL PLGD 1 & 3 AND SPRAY PLAZA X104-107MA | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 100 | WM-0011 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | INTERSECTION OF VAN CORTLANDT AVENUE EAST AND RESERVOIR OVAL | RECONST OF PLGDS 1 & 3, AND THE CENTRAL SPRAY PLAZA, IN WILLIAMSBRIDGE OVAL, LOCATED AT THE INTERSECTION OF VAN CORTLANDT AVENUE EAST AND RESERVOIR OVAL, BOROUGH OF THE BRONX X104-107MA | 2019 | 6100 | 5722.96 | 0 | 384 | 0 | 0 | 0 | 0 | 6106.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CRO19 | Harris Park - Recon perimeter,construct new fence X136-115M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 100 | WM-0011 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RECONSTRUCTION OF PERIMETER, CONSTRUCTION OF FENCE AND SEWER CONNECTION | 2019 | 1761 | 1251.58 | 124 | 220 | 0 | 0 | 0 | 0 | 1595.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CRO42A | STORY PLGD COMFORT STATION X204-105MA1/405M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 109 | WM-0011 | PROJECT DELAYED PENDING APPROVAL OF NECESSARY PERMITS | BOROUGH OF THE BRONX | RECONSTRUCTION OF THE COMFORT STATION | 2019 | 1000 | 639.18 | 65 | 0 | 0 | 0 | 0 | 0 | 704.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CRO66B | Ferry Point Park - Comfort Station Electrical X126-206MA1 | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 100 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | WESTCHESTER CIRCLE, SCHLEY, EMERSON AVENUES, EAST RIVER | WESTCHESTER CIRCLE, SCHLEY, EMERSON AVENUES, EAST RIVER | 2019 | 191 | 182.71 | 0 | 0 | 0 | 42 | 0 | 0 | 224.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROALG | CROTONA PARK INDIAN LAKE ALGAE REDUCTION | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-X245 |  |  | CROTONA PARK ALGAE REDUCTION AT INDIAN LAKE IN THE BRONX | 2019 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT02 | BRONX RIVER GNWAY: BIRCHALL/180TH ST CONNECTION X002-107M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 111 | WM-0011 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | STUDY AND IMPLEMENTATION OF A ONE MILE BRONX RIVER GREENWAY LINK WITHIN BRONX PARK. GREENWAY WILL CONNECT BIRCHALL AVENUE TO 180TH STREET... | 2019 | 3502 | 3245.42 | 75 | 0 | 0 | 0 | 0 | 0 | 3320.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT05 | Putnam Trail - Acquisition of Right-of-Way- XPUTNAM | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 108 | P-0056 WM-0011 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | BX | THE AQUISITION OF THE PUTNAM RAILROAD R.O.W. BETWEEN THE CITY LINE AND THE HARLEM RIVER FOR DEVELOPMENT AS A GREENWAY 3.5 MILES AT APPROX 100 FEET IN WIDTH. | 2019 | 824 | 0 | 10 | 716 | 0 | 4460 | 0 | 0 | 5186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT06 | BRONX RIVER GREENWAY: MULTI USE PATH 233 ST X004-213M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 112 | WM-0011 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | BX | CONSTRUCTION OF A NEW PEDESTRIAN BRIDGE IN BRONX PARK OVER PARKWAY AND RIVER TO PROVIDE KEY BRONX RIVER CONNECTION BETWEEN SHOELACE PARK AND MUSKRAT COVE. | 2019 | 5001 | 3454.91 | 212 | 0 | 0 | 0 | 0 | 0 | 3666.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT09 | Pelham Bay Park: Waterfront Development X039-507MA | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 109 | WM-0011 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | BX | DEVELOPMENT OF WATERFRONT AREA NEAR LANDFILL, PLUS GREENWAY LINK AND SEAWALL REPAIR | 2019 | 8002 | 2339.04 | 0 | 297 | 0 | 0 | 0 | 0 | 2636.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT11 | REGATTA PARK: WATERFRONT ACCESS (XG-31900-115M) | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 107 | WM-0011 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BX | IMPROVEMENT OF 1 ACRE CITY OWNED SITE NORTH OF UNIVERSITY HEIGHTS BRIDGE FOR DEVELOPMENT WITH WATERFRONT ACCESS AND OPEN SPACE. REQUIRES TRANSFER OF DCAS/CDOT PARCEL. IMPLEMENTS A SEGMENT FOR REGATTA PARK. | 2019 | 1801 | 34.74 | 0 | 478 | 0 | 0 | 0 | 0 | 512.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT12 | PUGSLEY CREEK SALT MARSH & BUFFER RESTOR X088-506M&106M OMBP | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 109 | WM-0011 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BX | BOND ACT MATCH TO RESTORE 2.25-ACRE SALT MARSH AREA ON THE NORTHEAST BANK OF PUGSLEY CREEK. | 2019 | 852 | 1134.02 | 142 | 0 | 0 | 0 | 0 | 0 | 1276.02 | 820 | 0 | 0 | 0 | 0 | 0 | 0 | 820
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT13 | VC PK- Recon Headhouse & Demolish Greenhouse X092-207M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 100 107 108 112 | WM-0011 P-0245X | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BX | THE UPGRADE AND EXPANSION OF THE EXISTING NURSERY. WORK TO INCLUDE CONSTRUCTION AND RENOVATION OF COLD FRAMES, GREEN HOUSES, LOADING DOCKS, IRRIGATION LINES, SEWER LINES AND ACCESS WAY... | 2019 | 3001 | 1070.25 | 0 | 2095 | 0 | 5555 | 0 | 0 | 8720.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT14 | AQUEDUCT WALK - COMF. STATION X001-207M/507M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 105 | WM-0011 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BX | CONSTRUCTION OF A COMFORT STATION WITH AN OPERATIONS COMPONENT | 2019 | 1800 | 1742 | 394 | 0 | 0 | 0 | 0 | 0 | 2136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT19 | HARRIS PARK ATHLETIC FIELDS X136-106M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 107 | WM-0011 | PROJECT DELAYED DUE TO UNFORESEEN HAZARDOUS CONDITION | BX | RC OF 9 ATHLETIC FIELDS, 3 NEW STAIRCASES AND ADA ACCESS LEADING TO THE PARK. | 2019 | 9479 | 15568.57 | 169 | 0 | 0 | 0 | 0 | 0 | 15737.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT28 | JEROME PARK RESERVOIR-RECREATIONAL PATHWAY XG-20000-107M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 108 | WM-0011 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | BX | NEW RECREATIONAL PATHWAY TO BE CONSTRUCTED AROUND THE RESERVOIR. | 2019 | 2768 | 4514.61 | 492 | 0 | 0 | 0 | 0 | 0 | 5006.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT32 | RECON PATH & MISC WORK @ AQUEDUCT WALK X001-107M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 107 | WM-0011 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | BX | RC OF FIRST AQUEDUCT SECTION FROM KINGSBRIDGE RD TO MORTON PLACE. SECTION TO INCLUDE NEW PROMENADE PAVEMENT, NEW PLAYGROUNDS, AND NEW PASSIVE SPACES. | 2019 | 7001 | 5077.28 | 137 | 0 | 0 | 0 | 0 | 0 | 5214.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT36 | PELHAM PARKWAY MALLS X003-107M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 111 | WM-0011 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | BX | RC OF THE PELHAM BAY MALLS FROM THE HUTCHINSON RIVER PARKWAY TO BOSTON ROAD. | 2019 | 1502 | 2383.83 | 37 | 0 | 0 | 0 | 0 | 0 | 2420.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT42 | STORY PLAYGROUND RC OF P. S. 100 X204-106M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | WM-0011 | PROJECT DELAYED PENDING APPROVAL OF NECESSARY PERMITS | TAYLOR AND THIERIOT AVENUES, BRONX | RC OF P.S. 100 (STORY) PLAYGROUND | 2019 | 7316 | 5581.33 | 189 | 0 | 0 | 0 | 0 | 0 | 5770.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT44 | PUGSLEY CREEK - FIELD OF DREAMS BFLDS & SITEWORK X088-207M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 102 | WM-0011 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BX | CREATION OF 3 BALLFIELDS WITH APPROPRIATE IRRIGATION. | 2019 | 2201 | 1172.37 | 149 | 0 | 0 | 0 | 0 | 0 | 1321.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT45 | PUGSLEY CREEK PK - Construct basketball court X088-111M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 109 | WM-0011 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | BX | CREATION OF A SMALL PLAYGROUND ALONG WHITE PLAINS ROAD AT PATTERSON AVENUE NEAR I.S. 174... | 2019 | 1202 | 1353.52 | 245 | 0 | 0 | 0 | 0 | 0 | 1598.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT46 | HINES PARK - RECONST OF RETAINING WALL X026-107M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 103 | WM-0011 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | BX | RENOVATION OF PLAYGROUND. | 2019 | 677 | 518.16 | 37 | 0 | 0 | 0 | 0 | 0 | 555.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT48 | CLARK PLAYGROUND RC X200-105M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 101 | WM-0011 |  | BX | PLAYGROUND RC TO INCLUDE NEW PLAY EQUIPMENT, HANDBALL AND BASKETBALL COURT RENOVATIONS WITH COLOR SEAL COATING, PAVEMENT, SWINGS, AND FENCING | 2019 | 1527 | 1346.12 | 225 | 0 | 0 | 0 | 0 | 0 | 1571.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT51 | SEDGWICK PLAYGROUND X158-106M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 105 | WM-0011 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | BX | RC OF ENTIRE PLAYGROUND, INCLUDING COMFORT STATION. | 2019 | 172 | 1940.55 | 227 | 0 | 0 | 0 | 0 | 0 | 2167.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT68 | MULLALY PARK - SKATE BUILDING X034-207M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 199 | WM-0011 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | MULLALY PARK - BOROUGH OF THE BRONX | RECONSTRUCTION OF THE SKATE BUILDING AT MULLALY PARK | 2019 | 1782 | 3140.36 | 537 | 0 | 0 | 0 | 0 | 0 | 3677.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROUL1 | VAN CORT PLGD & COMF. STAT(SACHKERAH WOODS) X092-400MA/700MA | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 107 | WM-0011 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES | BX | ADDITIONAL FACILITIES TO BE DEVELOPED WITH PLAYGROUND RC: DOG RUN, PICNIC AREAS AND RC OF PARK ENTRANCES AT THE SOUTHEAST CORNER OF VAN CORTLANDT PARK | 2019 | 2776 | 2634.83 | 73 | 0 | 0 | 0 | 0 | 0 | 2707.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CRPOFW | Crotona Park -Recon pool perimeter fence & wall X010-314M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 100 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | DEMOLITION OF EXISTING STEEL FENCE WITH WELDED STEEL PLATED AND BARBED WIRE, RECONSTRUCTION OF FOUNDATION WALL AND CONSTRUCTION OF NEW STEEL FENCE. | 2019 | 2448 | 2812.97 | 100 | 0 | 192 | 0 | 0 | 0 | 3104.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CRPOHS | Crotona Park - pool towers X010-210MA3 | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 100 103 | P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | CROTONA PARK POOL HOUSE | CROTONA PARK POOL HOUSE - RENOVATION | 2019 | 500 | 2791.19 | 0 | 0 | 262 | 0 | 0 | 0 | 3053.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CWELEC | FY04 Bronx Elected Official Multi-Site - XG-204M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-X245 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | FY '04 ELECTED OFFICAL PROJECTS - | FY '04 ELECTED OFFICAL PROJECTS - | 2019 | 871 | 547.93 | 0 | 0 | 0 | 0 | 72 | 0 | 619.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1DEPOT | Depot Place - portion of Harlem River greenway XG-31800-106M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 104 | P-1018 | PROJECT DELAYED PENDING APPROVAL OF NECESSARY PERMITS | DEPOT PLACE GREENWAY PROJECT | DEPOT PLACE GREENWAY PROJECT | 2019 | 1015 | 1386.04 | 0 | 0 | 0 | 0 | 0 | 0 | 1386.04 | 2346.42 | 0 | 0 | 0 | 743 | 0 | 0 | 3089.42
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1ECHOPK | Echo Park Playground and Sports Fields- X017-117M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 105 | P-0245X P-D021 |  |  | RECONSTRUCTION OF THE PLAYGROUND AND SPORTS FIELDS AT ECHO PARK IN THE BRONX. | 2019 | 5452 | 727 | 0 | 3956 | 395 | 0 | 0 | 0 | 5078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1EDENPG | Edenwald PLGD - basketball & handball crts (X165-116MA) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 112 | P-X245 P-1018 P-1008 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | EDENWALD PLAYGROUND, BRONX | EDENWALD PLAYGROUND - PHASE1 RECONSTRUCT BASKETBALL & HANDBALL COURTS | 2019 | 700 | 371.65 | 0 | 2068 | 0 | 0 | 0 | 0 | 2439.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1EWENPK | Ewen Park - construct playground X019-112M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 108 | P-D021 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | JOHNSON AVE, W 232 ST, RIVERDALE AVE | CONSTRUCT NEW PLAY AREA | 2019 | 735 | 1792.41 | 0 | 0 | 0 | 135 | 0 | 0 | 1927.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1FERPNT | Ferry Point Community Park - Adult Fitness Area | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-X245 |  |  | CONSTRUCTION OF ADULT FITNESS AREA - FERRY POINT COMMUNITY PARK - THEBRONX | 2019 | 0 | 0 | 0 | 400 | 0 | 0 | 0 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1FERRY8 | Ferry Point Park - Waterfront Park X126-116M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 100 110 | P-0720 P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | FERRY POINT WATERFRONT | FERRY POINT WATERFRONT | 2019 | 20656 | 187.44 | 14803 | 0 | 1346 | 0 | 0 | 0 | 16336.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1GHPCSR | Grove Hill Playground-Comfort Station Reconstruction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-0505 |  |  | RECONSTRUCTION OF GROVE HILL PLAYGROUND COMFORT STATION | 2019 | 2114 | 141 | 0 | 0 | 1550 | 0 | 0 | 0 | 1691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1GIGP01 | St. Mary's Park & Rec Ctr Green Infrastructure XG-413M | LAND ACQUISITION AND TREE PLANTING | 100 | P-0822 P-1018 WP-0169 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | FY13 GREEN INNOVATIONS GRANT PROGRAM - BX | 2019 | 563 | 267.79 | 775 | 0 | 0 | 0 | 0 | 0 | 1042.79 | 20 | 600 | 0 | 0 | 0 | 0 | 0 | 620
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1GRAUER | Conrad Grauer field - demo & const of 20 ft fence X150-113M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 108 | P-D021 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | W 233 STREET, BAILEY AVE, W 234TH ST | FENCING HEIGHTENING | 2019 | 150 | 538.36 | 0 | 0 | 0 | 0 | 36 | 0 | 574.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1HAFFPT | HAFFEN PARK - CONSTRUCT ADULT FITNESS AREA | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-X245 |  |  | CONSTRUCTION OF ADULT FITNESS AREA - HAFFEN PARK - THE BRONX | 2019 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1HCMARI | Hammond Cove Marina | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-D021 P-D721 |  |  | HAMMOND COVE MARIA | 2019 | 14020 | 0 | 0 | 0 | 0 | 420 | 0 | 0 | 420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1HGCVPR | Hugh Grant Circle & Virginia Pk. Recon. XG-117M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-1018 |  |  | HUGH GRANT CIRCLE & VIRGINIA PK. RECON. | 2019 | 7624 | 889.06 | 2727 | 1164 | 5625 | 0 | 151 | 0 | 10556.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1HPLFLT | Highbridge Pool Filter Plant Reconstruction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-1008 |  | CITYWIDE | HIGHBRIDGE POOL FILTER PLANT RECONSTRUCTION | 2019 | 300 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1HUNTPT | HUNTS POINT RECREATION CENTER - REPLACE GYMNASIUM FLOOR | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 100 | P-X245 |  |  | REPLACEMENT OF GYMNASIUM FLOOR AT HUNTS POINT RECREATION CENTER - THEBRONX | 2019 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1HVMRCS | Havemeyer Playground C.S. | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-0505 |  |  | HAVEMEYER PLAYGROUND COMFORT STATION | 2019 | 1698 | 0 | 0 | 0 | 0 | 1494 | 0 | 0 | 1494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1IRRIG | Golf Course Irrigation - XG-200M | VEHICLES AND EQUIPMENT | 100 | WM-0011 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | VAN CORTLANDT, PELHAM BAY, SPLIT ROCK | VAN CORTLANDT, PELHAM BAY, SPLIT ROCK | 2019 | 5962 | 12582.67 | 122 | 0 | 0 | 0 | 0 | 0 | 12704.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1JGRDN2 | Jackson Forest Garden 2 (X319-115M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-D021 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | JACKSON FOREST GARDEN II | JACKSON FOREST GARDEN II | 2019 | 418 | 431.88 | 54 | 0 | 0 | 0 | 0 | 0 | 485.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1JUNIOR | NYS PARKS/JUNIOR'S CAMP - CAMP SITE RENOVATIONS | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 100 | P-X245 |  |  | CAMP SITE RENOVATIONS - NYS PARKS / JUNIOR'S CAMP - THE BRONX | 2019 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1KNGSBR | Kingsbridge Heights Community Center X250-109MA1 | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 107 | P-X245 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | KINGSBRIDGE HEIGHTS COMMUNITY CENTER - MISCELLANEOUS | KINGSBRIDGE HEIGHTS COMMUNITY CENTER - MISCELLANEOUS | 2019 | 1265 | 1329.6 | 0 | 0 | 0 | 0 | 224 | 0 | 1553.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1MELCOM | CPI PH 1- Melrose Commons Site 32 - XG3200-111M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 101 | P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | BX | MELROSE COMMONS SITE 32 | 2019 | 4550 | 7438.39 | 10 | 0 | 0 | 41 | 0 | 0 | 7489.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1MELRO | Melrose Commons URA Site 62 Park Development | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-0245X | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | MELROSE COMMONS URA SITE 62 PARK DEVELOPMENT | 2019 | 5987 | 1104.49 | 0 | 0 | 0 | 8451 | 0 | 0 | 9555.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1ORCHBC | ORCHARD BEACH - RENOVATIONS | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-X245 |  |  | RENOVATIONS AT ORCHARD BEACH | 2019 | 0 | 0 | 0 | 7107 | 0 | 0 | 0 | 0 | 7107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1ORCHMO | Orchard Beach M&O Facility Reconstruction | BEACHES AND BOARDWALKS | 100 | P-D021 P-0715 |  |  | FY17 JAN PLAN NN SUBMISSION $4M IN FY 19 AND $12.4M IN FY20... | 2019 | 35500 | 0 | 0 | 2700 | 0 | 32300 | 0 | 0 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1OWEND2 | OWEN F. DOLEN PK GOLDEN AGE CTR X016-114M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 109 | P-D021 P-X245 P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | OWEN DOLAN REC CRT, BOROUGH OF THE BRONX | INSTALL NEW ROOF AND WATERPROOF OWEN DOLAN RECREATION CENTER | 2019 | 2485 | 427.74 | 1544 | 0 | 0 | 631 | 0 | 0 | 2602.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1OWEND3 | OWEN DOLEN RECREATION CENTER - X016-118M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-X245 P-D021 P-0506 |  |  | OWEN DOLEN RECREATION CENTER | 2019 | 1364 | 91 | 0 | 0 | 1345 | 0 | 0 | 0 | 1436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PDSMRC | PDF -St. Mary's Rec Ctr RC X045-115M | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 100 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BRONX | ST. MARY'S REC CTR | 2019 | 4000 | 744.35 | 34 | 0 | 0 | 5093 | 0 | 0 | 5871.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PELBRV | Pelham parkway -connection to Bronx river greenwayX002-211M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 111 | P-0245X P-X245 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | PELHAM BAY PARKWAY CONNECTION TO BRONX RIVER GREENWAY | PELHAM BAY PARKWAY CONNECTION TO BRONX RIVER GREENWAY | 2019 | 300 | 999.39 | 0 | 0 | 0 | 6 | 0 | 0 | 1005.39 | 2293.98 | 206 | 0 | 0 | 0 | 0 | 0 | 2499.98
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PELDOG | Pelham Parkway Dog Run (X002-116M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 111 | P-X245 P-1018 |  |  | PELHAM PARKWAY DOG RUN | 2019 | 300 | 643.7 | 49 | 0 | 0 | 54 | 0 | 0 | 746.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PELSHO | Pelham Bay Park- Shoreline Recons. (X039-116M) | BEACHES AND BOARDWALKS | 100 | WM-0011 |  |  | THIS PROJECT WILL REMOVE INTRUSIVE INFRASTRUCTURE FROM THE NATURAL ROCKY SHORE OF PELHAM BAY PARK, RESTORE COASTAL HABITATS, AND IMPROVE PUBLIC ACCESS TO THE SCENIC BAY. | 2019 | 2867 | 382 | 3214 | 0 | 0 | 0 | 0 | 0 | 3596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PLG10B | FY10 Playground Requirements (XG-410M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-D021 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | BRONX | FY10 PLAYGROUND REQUIREMENTS | 2019 | 1471 | 1793.71 | 0 | 0 | 0 | 0 | 93 | 0 | 1886.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PLG11B | FY11 Playground Requirements (XG-415M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-D021 | PROJECT DELAYED PENDING APPROVAL OF STATE REQ CONTRACT | BOROUGH OF BRONX XG-311M | FY19 JAN PLAN $250K P-1018 & $84K P-D021 ROLL TO FY20...FY20 APRIL PLAN ROLL $587K P-1018 & $114K P-D021 ROLL TO FY22..$587K P1018 FY21 TRSF TO P-6517CBF... | 2019 | 900 | 2933.36 | 0 | 0 | 0 | 114 | 0 | 0 | 3047.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PNYC03 | PlaNYC - Soundview Pk C/S X118-511MA PlaNYC | LAND ACQUISITION AND TREE PLANTING | 100 109 | P-0060 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BRONX | PLANYC - SOUNDVIEW PK C/S | 2019 | 1440 | 2811 | 0 | 0 | 0 | 51 | 0 | 0 | 2862 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PNYFL5 | PlaNYC- Coop City ballfield - Irrigation Install X251-116M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 110 | P-D021 P-0705 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | COOP CITY BALLFIELD, THE BRONX | COOP CITY BALLFIELD PATH, BLEACHER & GREEN AREA | 2019 | 360 | 91.37 | 786 | 0 | 58 | 0 | 0 | 0 | 935.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PNYR07 | PLANYC- BX PK CHANNEL RESTORATION X002-214M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-0822 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | BOROUGH OF THE BRONX | TO REHABILITATE THE CHANNEL AROUND THE ISLAND IN THE BRONX FOREST TO FACILITATE TREE PLANTING AND FOREST RESTORATION. | 2019 | 1150 | 250.14 | 0 | 0 | 156 | 1800 | 0 | 0 | 2206.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1POECOT | POE COTTAGE - INSTALLATION OF ROOF & EXTERIOR RENOVATIONS | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 100 | P-X245 |  |  | INSTALLATION OF ROOF & EXTERIOR RENOVATIONS AT POE COTTAGE IN THE BRONX | 2019 | 0 | 0 | 0 | 450 | 0 | 0 | 0 | 0 | 450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PTSNPK | Patterson Park (X155-116M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-D021 P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | PATTERSON PARK | 2019 | 2200 | 579 | 4530 | 0 | 0 | 0 | 0 | 0 | 5109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PUGSLY | PUGSLEY CREEK & SOUNDVIEW PARKS INSTALLATION OF BLUE LIGHT | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-X245 |  | PUGSLEY CREEK/ SOUNDVIEW PARK | PUGSLEY CREEK & SOUNDVIEW PARKS  INSTALLATION OF BLUE LIGHT HELP & FLASHCAMS | 2019 | 122 | 0 | 0 | 0 | 0 | 90 | 0 | 0 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PUTNAM | PUTNAM GREENWAY - X092-508M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 111 112 109 | P-1018 P-0245X | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | BRONX | GREENWAY - PUTNAM RAIL TRAIL | 2019 | 3420 | 864.73 | 2005 | 0 | 0 | 0 | 0 | 0 | 2869.73 | 0 | 1305 | 0 | 0 | 0 | 0 | 0 | 1305
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1RCPARK | Roberto Clemente State Park Reconstruction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-X245 P-D021 |  | BRONX | STATE PARK | 2019 | 500 | 0 | 1250 | 0 | 0 | 0 | 0 | 0 | 1250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1RNQARF | Ranaqua Roof Reconstruction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-1249 P-1018 |  | RANAQUA, BOROUGH OF THE BRONX | RECONSTRUCTION OF RNAQUA ROOF | 2019 | 2500 | 0 | 0 | 0 | 2500 | 0 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1RNQRMP | Reconstruction of Ranaqua M&O Storehouse Ramp | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-1018 |  |  | RECONSTRUCTION OF RANAQUA M&O STOREHOUSE RAMP | 2019 | 3275 | 0 | 380 | 0 | 0 | 2895 | 0 | 0 | 3275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1TRAILX | West Farms Park - Construction Continuation X288-114M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 100 | P-0245X P-0963 P-1018 P-D021 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | BRONX RIVER PARK - WEST FARMS ON 179TH STREET BETWEEN 180TH AND EAST TREMONT / 180TH TO MORRIS PARK AVENUE | CONSTRUCTION CONTINUATION OF WEST FARMS PARK INCLUDING CURBS, PAVEMENT, LIGHTING, AND PLANTING. | 2019 | 3045 | 402.97 | 1833 | 0 | 0 | 286 | 0 | 0 | 2521.97 | 0 | 636 | 0 | 0 | 0 | 0 | 0 | 636
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1TRE18A | FY 18 Street Trees Bronx CB's 1-8, XG- | LAND ACQUISITION AND TREE PLANTING | 100 | WM-0011 P-0822 |  | FY 18 STREET TREES BRONX CB'S 1-8, | FY 18 STREET TREES BRONX CB'S 1-8, | 2019 | 2090 | 70 | 385 | 2605 | 0 | 0 | 0 | 0 | 3060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1TRE18B | FY 18 Street Trees Bronx CB's 9-12, XG- | LAND ACQUISITION AND TREE PLANTING | 100 | P-0822 P-1018 |  | FY 18 STREET TREES BRONX CB'S 9-12, | FY 18 STREET TREES BRONX CB'S 9-12, | 2019 | 1432 | 186 | 0 | 0 | 0 | 1022 | 0 | 0 | 1208 | 0 | 0 | 0 | 0 | 678 | 0 | 0 | 678
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1TRE19A | FY 19 Street Trees Bronx CB's 1-8, XG-116MR | LAND ACQUISITION AND TREE PLANTING | 100 | P-0822 |  | FY 19 STREET TREES BRONX CB'S 1-8, XG-116MR | FY 19 STREET TREES BRONX CB'S 1-8, XG-116MR | 2019 | 2088 | 0 | 990 | 0 | 0 | 0 | 0 | 0 | 990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1TRE19B | FY 19 Street Trees Bronx CB's 9-12, XG-216MR | LAND ACQUISITION AND TREE PLANTING | 100 | P-0822 |  | FY 19 STREET TREES BRONX CB'S 9-12, XG-216MR | FY 19 STREET TREES BRONX CB'S 9-12, XG-216MR | 2019 | 1772 | 0 | 990 | 0 | 0 | 0 | 0 | 0 | 990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1TRE20A | FY20 Street Trees Bronx CB's 1-4, XG-119M | LAND ACQUISITION AND TREE PLANTING | 100 | ED-0075 ED-0409 P-0822 P-X822 |  | FY20 STREET TREES BRONX CB'S 1-4, | FY20 STREET TREES BRONX CB'S 1-4, | 2019 | 2260 | 0 | 0 | 747 | 1522 | 0 | 0 | 0 | 2269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1TRE20B | FY20 Street Trees Bronx CB's 5-8 XG-219M | LAND ACQUISITION AND TREE PLANTING | 100 | WM-0011 P-0822 P-D822 |  | FY20 STREET TREES BRONX CB'S 5-8 XG-219M | FY20 STREET TREES BRONX CB'S 5-8 XG-219M | 2019 | 2800 | 0 | 0 | 12 | 2788 | 0 | 0 | 0 | 2800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1TRE20C | FY20 Street Trees Bronx CB's 9-12 XG-319M | LAND ACQUISITION AND TREE PLANTING | 100 | WP-0169 P-0822 |  | FY20 STREET TREES BRONX CB'S 9-12 XG-319M | FY20 STREET TREES BRONX CB'S 9-12 XG-319M | 2019 | 2433 | 0 | 0 | 55 | 2378 | 0 | 0 | 0 | 2433 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1VNFPOL | Van Nest Flag Pole X093-116M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-1018 P-X245 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | VAN NEST FLAG POLE | 2019 | 60 | 619.77 | 0 | 0 | 0 | 51 | 0 | 0 | 670.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1WDLNCS | Woodlawn Playground C.S | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-0505 |  |  | WOODLAWN PLAYGROUND COMFORT STATIONS | 2019 | 1554 | 0 | 0 | 0 | 0 | 1554 | 0 | 0 | 1554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1WDLNSS | Woodlawn Plgd- Recon of Spray Shower X092-118M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 100 | P-X245 P-D021 |  | WOODLAWN PLAYGROUND, VAN CORTLANDT PARK | WOODLAWN PLAYGROUND - SPRAY SHOWER | 2019 | 1296 | 173 | 0 | 0 | 950 | 0 | 0 | 0 | 1123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | SANDY1-03 | SANDY - Bronx Type 2 Playgrounds R/C | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-1018 |  | BOROUGH OF THE BRONX | SUPERVISION OF BRONX DAMAGED SITES | 2019 | 311 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 280 | 280
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | SANDY1-04 | SANDY - Tiffany Street piers - Type 3 X304-113M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-1018 |  | BOROUGH OF THE BRONX | SANDY - EMERGENCY R/C OF BRONX PIERS | 2019 | 2237 | 500.48 | 12 | 0 | 0 | 1 | 0 | 0 | 513.48 | 1795.28 | 110 | 0 | 0 | 0 | 0 | 0 | 1905.28
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | SANDY1-06 | SANDY - Ferry Point Park Type 3 X126-115M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 100 | P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | BRONX | FERRY PT PK TYPE 3 | 2019 | 1924 | 296.71 | 0 | 0 | 0 | 357 | 0 | 0 | 653.71 | 895.89 | 0 | 0 | 1351 | 0 | 0 | 0 | 2246.89
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | SANDY1-09 | SANDY Type 3 Pelham Bay Park - Recon seawall X039-215M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 100 | P-1018 |  | BOROUGH OF THE BRONX | CNYG-514M | 2019 | 1598 | 9.14 | 0 | 0 | 0 | 0 | 0 | 159 | 168.14 | 0 | 0 | 0 | 0 | 0 | 0 | 1430 | 1430
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | SANDY1-10 | Hammond Cove Marina X310-117M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-1018 |  |  | HAMMOND'S COVE MARINA | 2019 | 1187 | 251.93 | 0 | 4 | 79 | 0 | 0 | 0 | 334.93 | 323.43 | 32 | 0 | 713 | 0 | 0 | 0 | 1068.43
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | SANDY1-11 | Pelham Bay Landfill | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 100 | P-1018 |  | HUTCHINSON RIVER, LONG ISLAND SOUND BET. BRONC COUNTY LINE AND MIDDLETOWN RD., WATT AVE. IN THE BRONX | SANDY - PELHAM BAY LANDFILL | 2019 | 10750 | 0 | 100 | 0 | 0 | 897 | 78 | 0 | 1075 | 0 | 880 | 0 | 0 | 8092 | 703 | 0 | 9675
20190425 | BRONX | 846 | DEPT OF PARKS AND RECREATION | SANDY6-11 | SANDY - Park reconstruction (Type 3 ) (Non - Emergency) | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 100 | P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | BRONX | SANDY - PARK RECONSTRUCTION (NON-EMERGENCY) | 2019 | 60019 | 3.19 | 0 | 0 | 0 | 0 | 0 | 65 | 68.19 | 28.41 | 0 | 0 | 0 | 0 | 0 | 182 | 210.41
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | C75-FCAD | FACADE RECONSTRUCTION AT EMTC, NIC,QDC, MDC, and GRVC | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0075 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | FACADE RECONSTRUCTION AT NIC,QDC,BBKC,BKDC | 2019 | 1650 | 18089.12 | -12 | 120 | 0 | 0 | 0 | 0 | 18197.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO290BCHJ | BCHJ-Post Construction Work | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 104 | CO-0290 |  |  | BCHJ-POST CONSTRUCTION WORK | 2019 | 44000 | 38807.02 | 2849 | 0 | 0 | 0 | 0 | 0 | 41656.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO290XSB1 | DASNY - BRONX CRIMINAL CT COMPLEX | CONSTRUCTION OF NEW COURT FACILITIES | 104 | PW-0077 CO-0290 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | TO CONSTRUCT A NEW BUILDING TO HOUSE THE SUPREME COURT/CRIMINAL TERM24 COURT ROOMS ARE TO BE CONSTRUCTED ALONG WITH JUDGES CHAMBERS, CLERIJURY FUNCTIONS, AND ANCILLARY SPACETHIS PROJECT IS PART OFTHE CITY'S COURT MASTER PLAN | 2019 | 415163 | 204685.27 | 4862 | 0 | 0 | 0 | 11787 | 0 | 221334.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO293LL11 | 851 GRAND CONCOURSE - FACADE RECONSTRUCTION | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 101 | CO-0293 |  |  | 851 GRAND CONCOURSE - FAÝADE REPAIRS LOCAL LAW 11 | 2019 | 13057 | 0 | 952 | 0 | 0 | 150 | 1800 | 11955 | 14857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO293SP | 851 GRAND CONCOURSE - FIRE PROTECTION/SPRINKLERS | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 100 | CO-0293 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | 851 GRAND CONCOURSE - FIRE PROTECTION/SPRINKLERS | 2019 | 44850 | 2080.71 | 7040 | 0 | 34500 | 1230 | 0 | 0 | 44850.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO295EXT | 1118 GRAND CONCOURSE - FACADE REPAIRS LOCAL LAW 11 | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 101 | CO-0295 |  |  | 1118 GRAND CONCOURSE - FACADE REPAIRS LOCAL LAW 11 | 2019 | 230 | 0 | 0 | 0 | 0 | 0 | 0 | 230 | 230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CRO-AGS | CROTON ABOVE-GROUND STRUCTURE AND LANDSCAPING | CROTON FILTER PROJECT | 107 108 | WM-0011 |  |  | CONSTRUCTION OF THE ABOVE GROUND STRUCTURES FOR THE DPR PORTION OF THE MOSHULU GOLF COURSE. INCLUDED ARE THE CLUB HOUSE, THE TEEBOXES FOR THE DRIVING RANGE, THE WATER FRATURES, AND A PARKING LOT FOR THE GOLF COURSE. | 2019 | 58786 | 550 | 76589 | 1357 | 0 | 0 | 0 | 0 | 78496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CS-ER-WCP | PARALLEL SEWER-REDUCE CSO DISCHARGE FROM PUGSLEY CREEK | CONSENT DECREE UPGRADING AND CONSTRUCTION | 100 | WM-0001 TF-0002 SE-0002X | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES |  | THIS PROJECT WILL INVOLVE CONSTRUCTING A NEW PARALLEL INTERCEPTOR FROM CSO-24 TO R-6 TO REDUCE CSO DISCHARGE FROM PUGSLEY CREEK AS REQUIREDBY DEC IN ORDER TO APPROVE A MODIFICATION REQUEST TO ELIMINATE A 12-MG CSO TANK ($300M) FROM WESTCHESTER CREEK. | 2019 | 76000 | 99764.25 | 9699 | 0 | 0 | 0 | 0 | 0 | 109463.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | E14-0003 | DCAS - BRONX FAMILY CRIMINAL COURT-ENERGY UPGRADE | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 100 | PU-0025 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | ENERGY UPGRADE | 2019 | 3975 | 7764.18 | 1234 | 188 | 0 | 0 | 0 | 0 | 9186.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | E14-0019 | DHS - Franklin Women's Shelter | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 101 | HH-0112 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | DHS - FRANKLIN WOMEN'S SHELTER | 2019 | 744 | 962.1 | 21 | 50 | 0 | 0 | 0 | 0 | 1033.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0005 | NYPL -Richmondtown Branch Library - Window Upgrades | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 101 | PU-0025 |  |  | DDC -RICHMONDTOWN BRANCH LIBRARY - WINDOW UPGRADES | 2019 | 300 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0015 | DCLA - NY Botanical Garden Campus: ECAG Service Bldg (Round) | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 101 | PU-0025 |  |  | NEW YORK BOTANICAL GARDEN CAMPUS: ECAG SERVICE BLDG (ROUND) - LIGHTING UPGRADE | 2019 | 300 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-553 | WATER MAIN IN SOUTHERN BLVD - WESTCHESTER AV & BOSTON RD | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 102 103 | WM-0001 HW-0200 TF-0002 WM-0006 HW-0001X | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | WATER MAIN IN SOUTHERN BLVD - WESTCHESTER AV & BOSTON RD | WATER MAIN IN SOUTHERN BLVD - WESTCHESTER AV & BOSTON RD | 2019 | 16885 | 53992.13 | 791 | 3318 | 0 | 0 | 0 | 0 | 58101.13 | 516.91 | 0 | 0 | 0 | 0 | 0 | 0 | 516.91
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-556A | UPGRADE WATER MAINS AT NY BOTANICAL GARDENS (BX) | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 100 106 107 111 112 | WM-0006 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | CLEANING, SURVEYIN, LINING AND REPLACING 36" AND 48" WATER MAINS, ANDUPGRADE EXISTING DISTRIBUTION WATER MAINS IN BOTANICAL GARDEN AREA. | 2019 | 1789 | 115.15 | 0 | 0 | 1650 | 0 | 0 | 0 | 1765.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-556B | UPGRADE WATER MAINS AT NY BOTANICAL GARDENS (BX) | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 100 106 107 111 112 | WM-0006 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CLEANING, SURVEYIN, LINING AND REPLACING 36" AND 48" WATER MAINS, ANDUPGRADE EXISTING DISTRIBUTION WATER MAINS IN BOTANICAL GARDEN AREA. | 2019 | 5094 | 0 | 0 | 0 | 5060 | 0 | 0 | 0 | 5060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-559 | WM & SE WORK IN RECON. OF METROPOLITAN AV. | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 106 | WM-0001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | WATER MAIN AND COMB. SEWER REPLACEMENT AND REHAB IN RECONSTRUCTION OFMETROPOLITAN AVE AND UNIONPORT RD IN PARKCHESTER AREA. | 2019 | 10491 | 9922.51 | 120 | 0 | 0 | 0 | 0 | 0 | 10042.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-560 | RECON WM IN WEST FARMS SQUARE (HWXP2007) | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 106 | SE-0002X WM-0006 WM-0001 |  |  | RECON WM IN WEST FARMS SQUARE | 2019 | 8096 | 0 | 0 | 8096 | 0 | 0 | 0 | 0 | 8096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-562 | New 46" Trunk Water Main in E.233rd St. Bronx | AUGMENTATION OF WATER SUPPLY SYSTEMS | 112 | WM-0006 WM-0001 SE-0002X | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | NEW 46" TRUNK WATER MAIN IN E.233RD ST. BRONX, BETWEEN BRONXWOOD AVENUE AND BAYCHESTER AVENUE. | 2019 | 8234 | 708.5 | 0 | 0 | 31143 | 0 | 0 | 0 | 31851.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-568 | New 20" sub-aqueous water main extension to Randall's Island | EXTENSIONS | 101 | WM-0001 SE-1000 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NEW 20" SUB-AQUEOUS WATER MAIN EXTENSION TO RANDALL'S ISLAND | 2019 | 6243 | 31928.25 | 7967 | 0 | 0 | 0 | 0 | 0 | 39895.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-569 | Replacement of Trunk WM in Bainbridge Ave | AUGMENTATION OF WATER SUPPLY SYSTEMS | 108 | WM-0006 WM-0001 SE-0002X | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | REPLACEMENT OF TRUNK WM IN BAINBRIDGE AVE BETWEEN GUN HILL RD & HOLLYLA, AND IN JEROME AVE BETWEEN HOLLY LA AND E. 233RD ST., ETC | 2019 | 19229 | 47714.67 | 10734 | 0 | 0 | 0 | 0 | 0 | 58448.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-570 | Trunk & Dist WM & Comb. Sewer Replacement, bx | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 105 | WM-0006 WM-0001 SE-0002X |  |  | RUNK & DISTRIBUTION WM & COMBINED SEWER REPLACEMENT IN UNIVERSITY AVENUE, BX | 2019 | 12384 | 0 | 0 | 0 | 11589 | 0 | 0 | 0 | 11589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-572 | Rep WM in Westchester Ave (HWPLZ004X) | AUGMENTATION OF WATER SUPPLY SYSTEMS | 108 | SE-0004 WM-0001 EP-0007 |  |  | REPLACE WM IN WESTCHESTER AVE BETWEEN MORRISON AVE AND HARROD PLACE,ETC. | 2019 | 227 | 0 | 5069 | 0 | 0 | 0 | 0 | 0 | 5069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HEDA-002 | Accelerated Distribution WM replcmnt & sewer rehab: BX | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 100 | WM-0001 SE-0002X SE-0200X | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | ACCELERATED DISTRIBUTION WATER MAIN REPLCMNT & SEWER REHAB/REPLACEMENT, BRONX | 2019 | 21446 | 19946.46 | 375 | 0 | 250 | 0 | 0 | 0 | 20571.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HEDA-003 | Accelerated Distribution WM replcmnt & sewer rehab: BX | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 100 | WM-0001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | ACCELERATED DISTRIBUTION WATER MAIN REPLCMNT & SEWER REHAB/REPLACEMENT, BRONX | 2019 | 19516 | 20659.69 | 630 | 630 | 0 | 0 | 0 | 0 | 21919.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112CWFR | COMMONWEALTH AVENUE FIRE SAFETY SYSTEM | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 |  |  | COMMONWEALTH AVENUE FIRE SAFETY SYSTEM | 2019 | 650 | 1230.92 | 259 | 0 | 0 | 0 | 0 | 0 | 1489.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112WLFA | WILLOW AVE FIRE SAFETY | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 |  |  | FIRE SAFETY SYSTEM | 2019 | 750 | 735.56 | 89 | 0 | 0 | 0 | 0 | 0 | 824.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115JCFS | JACKSON FAMILY FIRE SAFETY | SHELTERS FOR HOMELESS FAMILIES |  | HH-0115 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | JACKSON FAMILY FIRE SAFETY | 2019 | 1485 | 1029.69 | 117 | 320 | 0 | 0 | 0 | 0 | 1466.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115NLHP | NELSON AVENUE RESIDENCE - REPLACEMENT OF HEATING PIPING | SHELTERS FOR HOMELESS FAMILIES |  | HH-0115 |  |  | NELSON AVENUE RESIDENCE - REPLACEMENT OF HEATING PIPING | 2019 | 120 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115SNEC | SENECA HOUSES - ELECTRICAL AND KITCHEN UPGRADE | SHELTERS FOR HOMELESS FAMILIES |  | HH-0115 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | SENECA HOUSES - ELECTRICAL AND KITCHEN UPGRADE | 2019 | 1480 | 0 | 0 | 0 | 0 | 318 | 0 | 2634 | 2952 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115SNFA | SENECA HOUSES - FIRE ALARM SYSTEM UPGRADE | SHELTERS FOR HOMELESS FAMILIES |  | HH-0115 |  |  | SENECA HOUSES - FIRE ALARM SYSTEM UPGRADE | 2019 | 665 | 916.78 | 1601 | 0 | 0 | 0 | 0 | 0 | 2517.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115UNFA | UNIVERSITY FAMILY RESIDENCE - FIRE ALARM SYSTEM UPGRADE | SHELTERS FOR HOMELESS FAMILIES |  | HH-0115 |  |  | UNIVERSITY FAMILY RESIDENCE - FIRE ALARM SYSTEM UPGRADE | 2019 | 646 | 900.95 | 720 | 0 | 3908 | 0 | 0 | 0 | 5528.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82BRONX | Bronx Animal Care Center | ANIMAL CARE |  | HL-0082 |  |  | CONSTRUCTION | 2019 | 5000 | 0 | 0 | 8000 | 25500 | 25500 | 0 | 0 | 59000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPBX | SAFE ROUTES TO SCHOOLS- BRONX | PRIMARY STREET RECONSTRUCTION | 100 | HW-0988 HW-D105 |  | SAFE ROUTES TO SCHOOLS- BRONX | SAFE ROUTES TO SCHOOLS- BRONX | 2019 | 9628 | 723.63 | 0 | 0 | 9004 | 0 | 0 | 0 | 9727.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD105-01 | METROPOLITAN AVE & UNIONPORT ROAD IN PARKCHESTER -CENTER IS. | PRIMARY STREET RECONSTRUCTION | 100 109 | HW-X001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | METROPOLITAN AVE & UNIONPORT ROAD IN PARCHESTER CENTER ISLAND MALL | MATROPOLITAN AVE & UNIOPORT ROAD PARCHESTER-CENTER ISLAND MALL | 2019 | 4488 | 7779.68 | 182 | 0 | 0 | 0 | 0 | 0 | 7961.68 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 2200
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD10501A | HUGH GRANT CIRCLE - METROPOLITAN AV AND WESTCHESTER AV | PRIMARY STREET RECONSTRUCTION | 100 109 | WM-0001 TF-0002 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | HUGH GRANT CIRCLE - METROPOLITAN AV AND WESTCHESTER AV | HUGH GRANT CIRCLE - METROPOLITAN AV AND WESTCHESTER AV | 2019 | 298 | 5077.63 | 37 | 0 | 0 | 0 | 0 | 0 | 5114.63 | 5.34 | 0 | 0 | 0 | 0 | 0 | 0 | 5.34
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD105-03 | LIBRARY LANE PROJECT | PRIMARY STREET RECONSTRUCTION | 100 110 | HW-0061 HW-D105 HW-0001X HW-0200 WM-0001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | LIBRARY LANE PROJECT | LIBRARY LANE PROJECT | 2019 | 600 | 945.75 | 0 | 3670 | 0 | 3057 | 0 | 0 | 7672.75 | 400 | 0 | 0 | 0 | 1480 | 0 | 0 | 1880
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ004X | Morrison Avenue Plaza (HED-572) | PRIMARY STREET RECONSTRUCTION | 100 | HW-1684 HW-0200 HW-0944 TF-0002 TF-0502 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | MORRISON AVENUE PLAZA | MORRISON AVENUE PLAZA | 2019 | 2700 | 1403.83 | 1327 | 188 | 0 | 0 | 0 | 0 | 2918.83 | 282 | 2210 | 0 | 0 | 0 | 0 | 0 | 2492
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19X | Pedestrian Ramp Rehabilitation - The Bronx | PEDESTRIAN RAMP CONSTRUCTION | 100 | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | PEDESTRIAN RAMP REHABILITATION - THE BRONX | 2019 | 12472 | 250 | 12543 | 0 | 0 | 0 | 0 | 0 | 12793 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2014X | PRIOR NOTICE SIDEWALKS - BRONX | SIDEWALK RECONSTRUCTION | 100 | HW-0200 HA-D001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | PRIOR NOTICE SIDEWALKS - BRONX | PRIOR NOTICE SIDEWALKS - BRONX | 2019 | 3971 | 3664.04 | 236 | 0 | 0 | 0 | 0 | 0 | 3900.04 | 703 | 0 | 0 | 0 | 0 | 0 | 0 | 703
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2018X | Prior Notice Sidewalks - Bronx | SIDEWALK RECONSTRUCTION | 100 | HW-0200 |  | PRIOR NOTICE SIDEWALKS - BRONX | PRIOR NOTICE SIDEWALKS - BRONX | 2019 | 2924 | 212 | 3488 | 0 | 0 | 0 | 0 | 0 | 3700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2019X | Prior Notice Sidewalks- Bronx | SIDEWALK RECONSTRUCTION | 100 | HW-0200 |  |  | PRIOR NOTICE SIDEWALKS- BRONX | 2019 | 3000 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWSRT2009 | ELS & SIDEWALK TO BUS CONTRACT(SIM) | PRIMARY STREET RECONSTRUCTION |  | HW-0988 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | ELS & SIDEWALK TO BUS CONTRACT | 2019 | 2796 | 5406.07 | 0 | 0 | 0 | 430 | 0 | 0 | 5836.07 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 15
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX100SBS | Webster Ave SBS | TRAFFIC WORK IN CONJUNCTION WITH HIGHWAY RECONSTRUCTION | 100 | WM-0001 TF-0777 TF-0002 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | WEBSTER AVE SBS - PLANYC | WEBSTER AVE SBS - PLANYC | 2019 | 16058 | 10368.25 | 5708 | 509 | 1150 | 185 | 0 | 0 | 17920.25 | 16674.79 | 0 | 0 | 0 | 0 | 0 | 0 | 16674.79
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX1048 | South Bronx Greenway | PRIMARY STREET RECONSTRUCTION | 100 | HW-0001X | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | SOUTH BRONX GREENWAY | SOUTH BRONX GREENWAY | 2019 | 3500 | 728.31 | 0 | 0 | 2284 | 0 | 7975 | 0 | 10987.31 | 429.3 | 0 | 0 | 0 | 0 | 4570 | 0 | 4999.3
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX710A | Pelham Pkwy - West & East and North & South Bounds (Phase A) | PRIMARY STREET RECONSTRUCTION | 111 | HW-0710 SE-0002X HW-0944 HW-1684 TF-0002 TF-0502 WM-0001 WM-0006 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | PELHAM PKWY-WEST & EAST AND NORTH & SOUTH BOUNDS (PHASE A) | PELHAM PKWY-WEST & EAST AND NORTH & SOUTH BOUNDS (PHASE A) | 2019 | 25093 | 128838.15 | 5382 | 1945 | 659 | 2061 | 0 | 0 | 138885.15 | 829.94 | 11 | 0 | 0 | 0 | 0 | 0 | 840.94
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXF2000B | 1400 WILLIAMSBRIDGE RD - HVAC AND FIRE ALARM SYS | FACILITY RECONSTRUCTION | 111 | HW-0003 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | 1400 WILLIAMSBRIDGE ROAD - UPGRADES | 1400 WILLIAMSBRIDGE ROAD - UPGRADES | 2019 | 1340 | 1537.99 | 6944 | 0 | 0 | 19 | 0 | 0 | 8500.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXF2144W | Replacement of HVAC Unit | FACILITY RECONSTRUCTION | 100 | HW-0003 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | REPLACEMENT OF HVAC UNIT | REPLACEMENT OF HVAC UNIT | 2019 | 220 | 384.06 | 50 | 0 | 0 | 0 | 0 | 0 | 434.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP134 | BRONX QUAD (EAST FORDHAM RD) | PRIMARY STREET RECONSTRUCTION | 100 105 106 107 | HW-0001X | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | BRONX QUAD (EAST FORDHAM RD) | BRONX QUAD (MOSHOLU PKWY AND FORDHAM ROAD) | 2019 | 13652 | 17168.72 | 130 | 0 | 0 | 0 | 0 | 0 | 17298.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP136A | GRAND CONCOURSE RECON SERVICE ROAD E.166 TO E171ST | PRIMARY STREET RECONSTRUCTION | 104 | HW-1672 HW-0001X TF-0002 HW-1678 SE-0002X | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RECON SERVICE ROAD WITH WIDENED MALL | 2019 | 13588 | 10402.86 | 2435 | 482 | 0 | 238 | 0 | 0 | 13557.86 | 12853.62 | 89 | 3145 | 0 | 0 | 0 | 0 | 16087.62
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP136B | Grand Concourse Phase 3 | PRIMARY STREET RECONSTRUCTION | 100 | HW-0001X SE-0002X TF-0002 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | GRAND CONCOURSE PHASE 3 | GRAND CONCOURSE PHASE 3 | 2019 | 21136 | 10658.1 | 3413 | 0 | 0 | 2 | 0 | 0 | 14073.1 | 15871.9 | 0 | 0 | 0 | 395 | 0 | 0 | 16266.9
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP136C | Grand Concourse Phase 4 (SEX002268) | PRIMARY STREET RECONSTRUCTION | 100 | HW-X001 HW-0001X HW-0200 HW-0001 HW-0944 TF-0502 TF-0002 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | GRAND CONCOURSE PHASE 4 | GRAND CONCOURSE PHASE 4 | 2019 | 64599 | 4230.7 | 49221 | 0 | 0 | 0 | 0 | 0 | 53451.7 | 0 | 27984 | 0 | 0 | 0 | 0 | 0 | 27984
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP2007 | E.177TH ST/DEVOE AVE BET. SHERIDAN EXP (I-895) AND E.TREMONT | PRIMARY STREET RECONSTRUCTION | 106 | HW-0001X HW-0200 TF-0502 TF-0002 HW-X006 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | NTERSECTION OF E.177TH ST., DEVOE AVE. AND I-895. INTERSECTION OF DEVOE AVE. AND E. TREMONT AVE. (PINX027.05.101) SOUTHERN SEGMENT OF THE BRONX RIVER GREENWAY | INTERSECTION OF E.177TH ST., DEVOE AVE. AND I-895. INTERSECTION OF DEVOE AVE. AND E. TREMONT AVE. (PINX027.05.101) SOUTHERN SEGMENT OF THEBRONX RIVER GREENWAY | 2019 | 4939 | 2402.07 | 0 | 15731 | 0 | 339 | 0 | 0 | 18472.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXPRATT | Pratt Ave Reconstruction and Retaining Wall | PRIMARY STREET RECONSTRUCTION | 100 | HW-0001X | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | PRATT AVE AND RETAINING WALL | 2019 | 8750 | 0 | 1174 | 0 | 6522 | 0 | 0 | 0 | 7696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXRCPLZ | ROBERTO CLEMENTE PLAZA & HUB REDESIGN AND RECONSTRUCTION | PRIMARY STREET RECONSTRUCTION | 100 105 | HW-0001X TF-0502 WM-0001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | RECON OF PLAZA & HUB | 2019 | 2550 | 14235.99 | 1125 | 0 | 0 | 0 | 0 | 0 | 15360.99 | 4396.3 | 0 | 0 | 0 | 0 | 0 | 0 | 4396.3
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXRCPLZA | ROBERTO CLEMENTE PLAZA ARTWORK IN CONNECTION WITH HWXRCPLZ | PRIMARY STREET RECONSTRUCTION | 100 | PV-0467 |  | ROBERTO CLEMENTE PLAZA | ROBERTY CLEMENTE PLAZA ARTWORK | 2019 | 425 | 222.5 | 202 | 0 | 0 | 0 | 0 | 0 | 424.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXS411 | West 229th St Step Street | RECONSTRUCTION OF STEP STREETS | 100 108 | HW-0211 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | WEST 229TH ST STEP STREET | WEST 229TH ST STEP STREET | 2019 | 3725 | 10298.02 | 75 | 0 | 0 | 6 | 0 | 0 | 10379.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXS511 | West Tremont Ave Step Street | RECONSTRUCTION OF STEP STREETS | 100 105 | SE-0002X HW-0944 SE-087HW | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | WEST TREMONT AVE STEP STREET | WEST TREMONT AVE STEP STREET | 2019 | 1617 | 7818.3 | 292 | 26 | 0 | 284 | 0 | 0 | 8420.3 | 1237.51 | 59 | 0 | 0 | 0 | 0 | 0 | 1296.51
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXS611 | RECONSTRUCTION OF STEP STREET AT WEST 231ST ST. | RECONSTRUCTION OF STEP STREETS | 100 | HW-0211 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | RECONSTRUCTION OF STEP STREET AT WEST 231ST ST. | RECONSTRUCTION OF STEP STREET AT WEST 231ST ST. | 2019 | 1954 | 1790.05 | 0 | 0 | 4930 | 0 | 0 | 0 | 6720.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXS711 | RECONSTRUCTION OF STEP STREET AT DAVIDSON AVE | RECONSTRUCTION OF STEP STREETS | 100 | HW-0211 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | RECONSTRUCTION OF STEP STREET AT DAVIDSON AVE | RECONSTRUCTION OF STEP STREET AT DAVIDSON AVE | 2019 | 7260 | 0 | 1209 | 0 | 4697 | 1119 | 0 | 0 | 7025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNBXA08LS | BRONX - Life Safety Projects @ 8 Branch Libraries | ESSENTIAL RECONSTRUCTION OF FACILITIES | 100 | LN-0101X LN-D008 LN-D004 LN-X001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | LIFE SAFETY PROJECTS @ 12 BRANCH LIBRARIES - BRONX | 2019 | 2570 | 1952.2 | 0 | 405 | 0 | 0 | 0 | 0 | 2357.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNC4WLEX | WOODLAWN - Branch Expansion | IMPROVEMENTS TO EXISTING FACILITIES | 112 | LN-X001 LN-D004 LN-D008 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 4355 KATONAH AVENUE, BRONX, NY 10470 | LIBRARY EXPANSION | 2019 | 2312 | 1000.89 | 0 | 0 | 4528 | 0 | 0 | 0 | 5528.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA09BEL | BELMONT - New Boiler | ESSENTIAL RECONSTRUCTION OF FACILITIES | 106 | LN-D004 |  |  | BOILER | 2019 | 420 | 423.43 | 0 | 46 | 0 | 0 | 0 | 0 | 469.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA11BEL | BELMONT - Upper and Lower Roof | ESSENTIAL RECONSTRUCTION OF FACILITIES | 108 | LN-D008 LN-0008 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ROOF REPLACEMENT | 2019 | 400 | 1946.04 | 459 | 0 | 0 | 0 | 0 | 0 | 2405.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA11SNV | SOUNDVIEW - Interior/Exterior Renovation | ESSENTIAL RECONSTRUCTION OF FACILITIES | 109 | LN-D008 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | FIRE ALARM | 2019 | 350 | 700.81 | 0 | 0 | 37 | 0 | 0 | 0 | 737.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13ECH | EASTCHESTER: HVAC Replacement | ESSENTIAL RECONSTRUCTION OF FACILITIES | 100 112 | LN-D008 LN-0008 |  |  | HVAC REPLACEMENT | 2019 | 1010 | 690.28 | 0 | 1280 | 0 | 0 | 0 | 0 | 1970.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13MOR | MORRISANIA: HVAC and Roof | ESSENTIAL RECONSTRUCTION OF FACILITIES | 103 | LN-D008 LN-0008 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES |  | HVAC AND ROOF | 2019 | 569 | 471.73 | 20 | 716 | 0 | 0 | 0 | 0 | 1207.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13MOT | MOTT HAVEN: HVAC | ESSENTIAL RECONSTRUCTION OF FACILITIES | 100 101 | LN-D008 LN-0101M LN-0008 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | HVAC | 2019 | 390 | 543.19 | 20 | 1939 | 0 | 0 | 0 | 0 | 2502.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13TRE | TREMONT: Boiler | ESSENTIAL RECONSTRUCTION OF FACILITIES | 106 | LN-D008 LN-0008 LN-D004 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | BOILER | 2019 | 590 | 1113.49 | 9 | 228 | 36 | 0 | 0 | 0 | 1386.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA14SPD | New Roof | ESSENTIAL RECONSTRUCTION OF FACILITIES | 100 108 | LN-D008 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | NEW ROOF | 2019 | 300 | 1031.41 | 117 | 145 | 0 | 0 | 0 | 0 | 1293.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA15EDW | HVAC Replacement @ Edenwald | ESSENTIAL RECONSTRUCTION OF FACILITIES | 100 | LN-D008 LN-0008 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | HVAC | 2019 | 965 | 315.46 | 2 | 0 | 1349 | 0 | 0 | 0 | 1666.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA15MOT | Window Replacement | ESSENTIAL RECONSTRUCTION OF FACILITIES | 100 | LN-D008 LN-0008 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | WINDOW REPLACEMENT | 2019 | 944 | 216.64 | 51 | 1017 | 0 | 0 | 0 | 0 | 1284.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA15RSD | RIVERDALE BRANCH Exterior / Facades/ Retaining Wall / HVAC | ESSENTIAL RECONSTRUCTION OF FACILITIES | 108 | LN-D008 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | REHABILITATION TO EXTERIOR AND FACADES & RETAINING WALL | 2019 | 1303 | 295.21 | 1160 | 0 | 0 | 0 | 0 | 0 | 1455.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCAL15CP | CLASSONS POINT: ADA Restrooms | ESSENTIAL RECONSTRUCTION OF FACILITIES | 100 | LN-D008 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ADA RESTROOMS | 2019 | 632 | 540.8 | 0 | 0 | 77 | 0 | 0 | 0 | 617.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCL15CAS | CASTLE HILL: Partial Interior Renovation | ESSENTIAL RECONSTRUCTION OF FACILITIES | 100 | LN-D008 LN-X001 LN-D004 LN-0008 LN-0101X | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | CASTLE HILL: INTERIOR RENOVATION | 2019 | 5191 | 658.06 | 83 | 0 | 4669 | 0 | 0 | 0 | 5410.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCM10WCH | WESTCHESTER SQUARE - Replacement Branch Construction | EXPANSION AND CONSTRUCTION OF FACILITIES | 111 | PU-0025 LN-D008 LN-D004 LN-X001 LN-0008 |  |  | NEW BRANCH CONSTRUCTION - LNCM10WCH | 2019 | 9300 | 3622.63 | 0 | 812 | 5 | 0 | 29432 | 0 | 33871.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCM12CPT | CLASON'S POINT - NEW ROOF AND DRAINS | ESSENTIAL RECONSTRUCTION OF FACILITIES | 100 109 | LN-D004 LN-0101M LN-D008 LN-X001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | NEW ROOF AND DRAINS | 2019 | 600 | 1065.79 | 53 | 706 | 0 | 0 | 0 | 0 | 1824.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNDSVRENO | SOUNDVIEW - Branch Renovation | ESSENTIAL RECONSTRUCTION OF FACILITIES | 109 | LN-D004 LN-0008 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | SOUNDVIEWW BRANCH: 660 SOUNDVIEW AVENUE, BRONX, NY 10473 | BRANCH RENOVATION | 2019 | 460 | 1667.09 | 0 | 283 | 0 | 0 | 0 | 0 | 1950.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEA13MHU | Mosholu: New Roof and Exterior Work | ESSENTIAL RECONSTRUCTION OF FACILITIES | 100 107 | LN-0008 LN-D008 LN-0101M LN-D004 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ROOF | 2019 | 1137 | 518.35 | 101 | 1896 | 0 | 0 | 0 | 0 | 2515.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEA13TNK | THROGS NECK: New Roof, HVAC | ESSENTIAL RECONSTRUCTION OF FACILITIES | 100 | LN-0008 LN-D008 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | NEW ROOF, HVAC | 2019 | 550 | 487.85 | 3315 | 0 | 0 | 0 | 0 | 0 | 3802.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEA14VNT | HVAC Replacement | ESSENTIAL RECONSTRUCTION OF FACILITIES | 100 111 | LN-0008 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | HVAC REPLACEMENT | 2019 | 500 | 298.42 | 337 | 0 | 2653 | 0 | 0 | 0 | 3288.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEM13ALL | ALLERTON: Fire Safety | ESSENTIAL RECONSTRUCTION OF FACILITIES | 100 111 | LN-0101X LN-0008 LN-D004 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | FIRE SAFETY | 2019 | 197 | 280.89 | 12 | 91 | 0 | 0 | 0 | 0 | 383.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEMA08WS | WOODSTOCK - Interior Rehabilitation | ESSENTIAL RECONSTRUCTION OF FACILITIES | 101 | LN-0008 LN-D008 LN-X001 LN-D004 LN-0101M | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | WOODSTOCK - INTERIOR REHABILITATION | 2019 | 5425 | 9486.65 | 4 | 0 | 0 | 0 | 2038 | 0 | 11528.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNXA11WFM | WEST FARMS - New Front Entry | ESSENTIAL RECONSTRUCTION OF FACILITIES | 106 | LN-X001 LN-D004 LN-D008 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NEW FRONT ENTRY | 2019 | 150 | 378.65 | 0 | 624 | 0 | 0 | 0 | 0 | 1002.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNXA12GRC | GRAND CONCOURSE - ADA Compliance and Related Work | IMPROVEMENTS TO EXISTING FACILITIES | 100 104 | LN-X001 LN-0101M LN-0008 LN-0101X LN-D008 LN-D004 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | ADA COMPLIANCE AND RELATED WORK | 2019 | 750 | 780.31 | 3325 | 391 | 0 | 0 | 0 | 0 | 4496.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNXA13WKF | WAKEFIELD - Partial Interior Renovation | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | LN-X001 LN-0008 LN-D008 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | WAKEFIELD BOILER REPLACEMENT | 2019 | 3543 | 100 | 0 | 0 | 0 | 1501 | 0 | 1620 | 3221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNXEA08BA | BAYCHESTER: HVAC | ESSENTIAL RECONSTRUCTION OF FACILITIES | 100 112 | LN-0008 LN-0101M LN-0101X | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | HVAC | 2019 | 632 | 0 | 0 | 0 | 0 | 0 | 662 | 0 | 662 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNXEA08CP | CLASONS POINT: HVAC | ESSENTIAL RECONSTRUCTION OF FACILITIES | 100 109 | LN-0008 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | HAVC | 2019 | 338 | 503.89 | 68 | 0 | 0 | 0 | 0 | 0 | 571.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNXEA08FN | FRANCIS MARTIN: HVAC | ESSENTIAL RECONSTRUCTION OF FACILITIES | 100 105 | LN-0008 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | HAVC | 2019 | 975 | 1250.48 | 144 | 0 | 0 | 0 | 0 | 0 | 1394.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-102DELV | Del Valle Square X009-111M | PRIMARY STREET RECONSTRUCTION | 100 | HW-1684 HW-0200 TF-0002 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | TRSNFR $4M (HW 1684) FROM HWPLZ003X...FY'14 ADOPT. ROLLS $3.649M FROMFY'14 TO FY15...$970K XFER FROM 850 HWPLZ011Q (3/14)...$970K NEW NEEDFUND (JAN PLAN FY15) ADDED PER IGOR'S E-MAIL FROM DOT ON 11.20.14 (NEW NEED DENIED)... | TRSNFR $4M (HW 1684) FROM HWPLZ003X...FY'14 ADOPT. ROLLS $3.649M FROMFY'14 TO FY15...$970K XFER FROM 850 HWPLZ011Q (3/14)...$970K NEW NEEDFUND (JAN PLAN FY15) ADDED PER IGOR'S E-MAIL FROM DOT ON 11.20.14 (NEW NEED DENIED)... | 2019 | 16961 | 1953.9 | 250 | 0 | 0 | 12984 | 0 | 0 | 15187.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P109STARA | STARLIGHT PARK COMFORT STATION X147-111M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 109 | P-D021 P-1018 P-X245 P-0245X ED-D075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | STARLIGHT PARK | 2019 | 1881 | 842.44 | 1981 | 272 | 0 | 0 | 0 | 0 | 3095.44 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 600
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P1CROT16A | BRONX RIVER GRWAY RIVER HOUSE IN STARLIGHT PK X147-107M/407M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 109 | P-0245X WM-0011 P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | BX RIVER | 2019 | 14562 | 14355.77 | 1116 | 0 | 0 | 0 | 0 | 0 | 15471.77 | 1034.21 | 13 | 0 | 0 | 0 | 0 | 0 | 1047.21
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-1PBSTAR | Starlight Park Pedestrian Bridge (P-1SAND01) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 109 | P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | BRONX | RECONSTRUCTION OF PEDESTRIAN BRIDGES IN STARLIGHT PARK | 2019 | 16400 | 12193.28 | 274 | 1 | 0 | 190 | 0 | 0 | 12658.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-1STARLP | BRONX RIVER GREENWAY: STARLIGHT PARK PHASE II, STAGE 2, BX | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-1018 P-X245 |  |  | BX RIVER ALLIANCE STARLIGHT PARK (DDC) | 2019 | 658 | 922.09 | 7267 | 0 | 0 | 0 | 0 | 0 | 8189.09 | 867 | 29007 | 0 | 0 | 0 | 0 | 0 | 29874
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-1VCPDBR | Vancortlandt Park pedestrian bridge | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 100 | P-0245X P-0508 WM-0011 |  |  | VANCORTLANDT PARK PEDESTRIAN BRIDGE | 2019 | 9800 | 2673 | 110 | 0 | 11953 | 5500 | 0 | 0 | 20236 | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | 4000
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P1YANK15A | Bronx Children's Museum | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 104 | PV-X467 P-D021 P-1018 PV-D467 P-X245 PV-0467 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | YANKEE STADIUM | 2019 | 5892 | 8790.41 | 1720 | 2070 | 0 | 0 | 0 | 0 | 12580.41 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 2000
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79FDBNX | BRONX FRONT DESK REPLACEMENT 42ND, 44TH, 52ND, 108TH | POLICE FACILITIES | 100 | PO-0079 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | DESK REPLACEMENT | 2019 | 1011 | 0 | 0 | 970 | 0 | 0 | 0 | 0 | 970 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79ROD | NEW FIREARMS TRAINING FACILITY | POLICE FACILITIES | 100 | PO-0079 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | NEW TRAINING FACILITY AT RODMAN'S NECK, BRNX | NEW TRAINING FACILITY | 2019 | 274630 | 0 | 35282 | 0 | 239348 | 0 | 0 | 0 | 274630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PV176CESU | WCS - Bronx Zoo - Con Ed Switchgear Upgrade | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | PV-0176 PV-D176 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES | 2300 SOUTHERN BLVD, FORDAM ROAD BRONX NY | ELECTRICAL SWITCHGEAR UPGRADE AT BRONX ZOO. | 2019 | 5909 | 1133.46 | 725 | 11856 | 1142 | 0 | 4357 | 0 | 19213.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PV176ITF1 | WCS - Bronx Zoo Parking Lot Improvements | ESSENTIAL RECONSTRUCTION OF FACILITIES | 106 107 111 | PV-0545 PV-D176 PV-0176 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES | 2300 SOUTHERN BLVD. BRONX, NY | PARKING LOT IMPROVEMENTS | 2019 | 10440 | 5138.06 | 0 | 0 | 0 | 0 | 670 | 0 | 5808.06 | 7104.87 | 243 | 0 | 0 | 0 | 0 | 0 | 7347.87
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PV205CONS | NYBG - NY Botanical Garden - Conservatory Dome/Boiler Rep. | ESSENTIAL RECONSTRUCTION OF FACILITIES | 106 107 111 112 | PV-X205 PV-D205 PV-0205 |  |  | NY BOTANICAL GARDEN - CONSERVATORY DOME | 2019 | 8000 | 0 | 10843 | 0 | 0 | 0 | 0 | 0 | 10843 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 2000
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PV464PRKG | WH - Wave Hill - Parking Lot Improvements | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | PV-D464 PV-0464 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES | 675 WEST 252ND STREET, BRONX, NY | PARKING LOT IMPROVEMENTS | 2019 | 1581 | 604.24 | 3438 | 0 | 373 | 0 | 0 | 0 | 4415.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PV471-SWA | Bronx Museum of the Arts - South Wing Atrium Fenestration | ESSENTIAL RECONSTRUCTION OF FACILITIES | 104 | PV-X471 PV-D471 PV-0471 PV-X467 PV-0467 PV-D467 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | SOUTH WING ATRIUM FENESTRATION REPLACEMENT. | 2019 | 300 | 1509.47 | 0 | 0 | 14456 | 0 | 0 | 0 | 15965.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PWD05TH1 | THROGS NECK LITTLE LEAGUE BALLFIELD RENOVATION LIGHTING | MISCELLANEOUS CONSTRUCTION | 101 | PW-D005 |  |  | THROGS NECK LITTLE LEAGUE BALLFIELD RENOVATION | 2019 | 405 | 0 | 341 | 14 | 0 | 0 | 0 | 0 | 355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PWXTNLLRE | Throgs Neck Little League- Infrastructure Rehabilitation | MISCELLANEOUS CONSTRUCTION | 110 | PW-X078 |  |  | THROGS NECK LITTLE LEAGUE INFRASTRUCTURE REHABILITATION | 2019 | 453 | 0 | 0 | 0 | 0 | 350 | 0 | 0 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | RWX018 | RETAINING WALL - E 168 ST (EB STEP ST) - TELLER AV & CLAY AV | RECONSTRUCTION OF RETAINING WALLS | 100 104 | HW-1677 HW-0001X | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | RETAINING WALL - EAST 168 STREET EAST BOUND STEP STREET BETWEEN TELLER AVENUE AND CLAY AVENUE | RETAINING WALL - EAST 168 STREET EAST BOUND STEP STREET BETWEEN TELLER AVENUE AND CLAY AVENUE | 2019 | 4752 | 9060.2 | 1215 | 0 | 0 | 309 | 0 | 0 | 10584.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | RWX019 | RETAINING WALL - MACOMBS DAM BR APPROACH SB BEHIND STAIRS | RECONSTRUCTION OF RETAINING WALLS | 100 104 | HW-1677 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | RETAINING WALL - MACOMBS DAM BRIDGE APPROACH SOUTHBOUND BEHIND STAIRS | RETAINING WALL - MACOMBS DAM BRIDGE APPROACH SOUTHBOUND BEHIND STAIRS | 2019 | 3613 | 1610.16 | 49 | 0 | 0 | 0 | 0 | 0 | 1659.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | RWX020 | RETAINING WALL - JEROME AV NB AFTER E 196 ST | RECONSTRUCTION OF RETAINING WALLS | 100 107 | HW-1677 WM-0001 WM-0006 HW-0001X HW-0200 TF-0502 SE-0002X | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | RETAINING WALL - JEROME AV NB AFTER E 196 ST | RETAINING WALL - JEROME AV NB AFTER E 196 ST | 2019 | 7975 | 15371.49 | 5665 | 0 | 0 | 0 | 0 | 0 | 21036.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | RWX022 | RETAINING WALL - Bronx Blvd S/B after Bronx River | RECONSTRUCTION OF RETAINING WALLS | 100 112 | HW-1677 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | RETAINING WALL - BRONX BLVD S/B AFTER BRONX RIVER | RETAINING WALL - BRONX BLVD S/B AFTER BRONX RIVER | 2019 | 1500 | 1560.35 | 190 | 0 | 0 | 0 | 0 | 0 | 1750.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBOMB | Reconstruct Hurricane Sandy Damaged Bomb Sq bldg | POLICE FACILITIES | 110 | PO-0079 PU-0025 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | RECONSTRUCT MULTIPURPOSE BUILDING FOR THE BOMB SQUAD IN RODMAN'S NECKDAMAGED BY HURRICANE SANDY | 2019 | 5000 | 837.8 | 0 | 17 | 1701 | 0 | 0 | 0 | 2555.8 | 1281.32 | 0 | 1441 | 6166 | 0 | 0 | 0 | 8888.32
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-791A | COMBINED SEWERS IN PAULDING AREA - PHASE II | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 112 | SE-0002X | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | COMBINED SEWERS IN PAULDING AREA - PHASE II | COMBINED SEWERS IN PAULDING AREA - PHASE II | 2019 | 11319 | 13346.56 | 469 | 0 | 0 | 0 | 0 | 0 | 13815.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SECBRQX01 | Reconst. & Installation of Catch Basins, BX & Qns | REPLACEMENT OF CHRONICALLY FAILING COMPONENTS | 100 | SE-1000 SE-0750 EP-0007 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | RECONSTRUCTION & INSTALLATION OF CATCH BASINS, QNS & BX | 2019 | 4000 | 0 | 0 | 0 | 0 | 2 | 1790 | 0 | 1792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX002263 | Replcmnt of Combined Sewers/WM Work in Holland Ave, Bx | REPLACEMENT OF CHRONICALLY FAILING COMPONENTS | 107 | SE-0002X |  |  | REPL OF COMB SEWERS IIN HOLLAND AVE & WM WORK, BX | 2019 | 4072 | 7901.65 | 118 | 300 | 0 | 0 | 0 | 0 | 8319.65 | 10.23 | 0 | 0 | 0 | 0 | 0 | 0 | 10.23
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX002266 | Repl & Rehab of Combined swrs 171 to 175 sts, bx | REPLACEMENT OF CHRONICALLY FAILING COMPONENTS | 100 | SE-0002K |  |  | REPL AND REHAB OF COMB SWRS FROM E. 171 ST TO E 175 ST., BRONX | 2019 | 153 | 0 | 153 | 0 | 0 | 0 | 0 | 0 | 153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX002268 | Reconstruction of Grand Concourse - Phase 4 (HWXP136C) | REPLACEMENT OF CHRONICALLY FAILING COMPONENTS | 104 | SE-0002X EP-0007 |  |  | RECONSTRUCTION OF GRAND CONCOURSE - PHASE 4( HWXP136C) - COMBINED SEWER REPLACEMENT FROM EAST 175TH STREET TO EAST FORDHAM ROAD, WORK DONE IN CONJUNCTION WITH NYC DOT PROJECT HWXP136C. | 2019 | 4258 | 0 | 4258 | 0 | 0 | 0 | 0 | 0 | 4258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX0201ZB | Reconstruction of existing sewers, Bronx | REPLACEMENT OF CHRONICALLY FAILING COMPONENTS | 100 | SE-0002X |  |  | RECONSTRUCTION OF EXISTING SEWERS, BRONX | 2019 | 5250 | 7442.69 | 8263 | 0 | 0 | 0 | 0 | 0 | 15705.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX0201ZC | Reconstruction of Existing Sewers, the Bronx | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 100 | SE-0002X |  |  | RECONSTRUCTION OF EXISTING SEWERS, THE BRONX | 2019 | 10100 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX200400 | STORM & SAN SEWERS REPL & EXT IN MININIEFORD AVE AREA | EXTENSIONS TO ACCOMMODATE NEW DEVELOPMENT | 110 | SE-0200X SE-0002X HW-0001X | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | STORM & SAN SEWERS REPL & EXT IN MININIEFORD AVE AREA | 2019 | 1378 | 459.42 | 686 | 1378 | 490 | 0 | 0 | 0 | 3013.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX20042 | STRM SWR IN WILLIAM AVE B/T DITMARS ST AND TIER ST | EXTENSIONS TO ACCOMMODATE NEW DEVELOPMENT | 100 110 | SE-0200X | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | STRM SWR IN WILLIAM AVE B/T DITMARS ST AND TIER ST | 2019 | 413 | 97 | 413 | 0 | 0 | 0 | 0 | 0 | 510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX20047 | Replacement of combined sewer in Burr Ave | REPLACEMENT OF CHRONICALLY FAILING COMPONENTS | 110 | EP-0007 HW-0200 HW-0944 SE-1000 SE-0200X WM-0001 |  |  | REPLACEMENT OF COMBINED SEWER IN BURR AVE BET. PELHAM PKWY S. AND WESTCHESTER AVE, ETC, DISTRIBUTION WATER MAIN REPLACEMENT. | 2019 | 12149 | 300 | 0 | 20628 | 0 | 0 | 0 | 0 | 20928 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 12
20190425 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX-SURV4 | SURVEYS FOR SEWERS IN BRONX | REPLACEMENT OF CHRONICALLY FAILING COMPONENTS | 100 | HW-0348 SE-0002X SE-0432 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | BOROUGH WIDE | SURVEYS FOR SEWER CONSTRUCTION/ RECONSTRUCTION | 2019 | 10564 | 7716.53 | 0 | 1561 | 0 | 0 | 0 | 0 | 9277.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOE601 | DOE - FAN SYSTEMS UPGRADES | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 102 | PU-0025 |  |  | SQ FT | 2019 | 2090 | 0 | 1900 | 0 | 0 | 0 | 0 | 0 | 1900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOE703 | DOE - STEAM TRAPS | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 101 | PU-0025 |  |  | DOE - STEAM TRAPS | 2019 | 228 | 0 | 0 | 228 | 0 | 0 | 0 | 0 | 228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEHHC606 | HHC - Jacobi Campus - EC Measures | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 111 | PU-0025 HO-0214 |  |  | HHC - JACOBI CAMPUS | 2019 | 11951 | 0 | 9207 | 1213 | 631 | 0 | 0 | 0 | 11051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO290EXTR | 265 EAST 161ST STREET- FACADE RECONSTRUCTION | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 104 | CO-0290 |  |  | 265 EAST 161ST STREET- FACADE REPAIRS LOCAL LAW 11 | 2019 | 845 | 0 | 0 | 0 | 0 | 0 | 0 | 705 | 705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293201A | DASNY - 851 GRAND CONCOURSE- RENOVATIONS | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 104 | CO-0293 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 851 GRAND CONCOURSE BRONX, NY 10451 | INTERIOR RENOVATIONS; ELECTRICAL & HVAC DISTRIBUTION; INITIAL OUTFITTING OF NEWLY RENOVATED SPACE | 2019 | 40475 | 1751.1 | 2628 | 0 | 0 | 0 | 0 | 0 | 4379.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293BL2 | 851 GRAND CONCOURSE- RETUBING OF BOILER #2 AND 3 | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 101 | CO-0293 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | 851 GRAND CONCOURSE- RETUBING OF BOILER #2 | 2019 | 717 | 525.25 | 534 | 148 | 0 | 0 | 0 | 0 | 1207.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293CTR | 851 GRAND CONCOURSE -COOLING TOWER REPLACEMENT | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 101 | CO-0293 |  |  | 851 GRAND CONCOURSE - COOLING TOWER REPLACEMENT | 2019 | 0 | 0 | 0 | 0 | 0 | 85 | 945 | 0 | 1030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293EV | 851 GRAND CONCOURSE - ELEVATORS | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 101 | CO-0293 |  |  | 851 GRAND CONCOURSE - ELEVATORS | 2019 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 12000 | 13000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293SA | 851 GRAND CONCOURSE - SAFE ACCESS TO MECHANICAL SYSTEM | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 101 | CO-0293 |  |  | 851 GRAND CONCOURSE - SAFE ACCESS TO MECHANICAL SYSTEM | 2019 | 176 | 42.82 | 0 | 0 | 71 | 0 | 0 | 0 | 113.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO294BACK | DASNY - 215 E. 161ST ST.- BACKFILL | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 104 | CO-0294 CS-0003 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 215 E. 161ST ST. BRONX, NY | EXTENSIVE INTERIOR RENOVATIONS; INITIAL OUTFITTING; VOICE & DATA CABLING | 2019 | 63456 | 1857.04 | 3760 | 926 | 0 | 0 | 0 | 0 | 6543.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO294BOIL | 215 EAST161ST STREET- REPLACEMENT OF BOILER | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 104 | CO-0294 |  |  | 215 EAST161ST STREET- REPLACEMENT OF BOILER | 2019 | 0 | 382.9 | 0 | 0 | 0 | 0 | 3060 | 0 | 3442.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO294RF | 215 E161 ST.- ROOF | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 104 | CO-0294 |  |  | 215 E161 ST.- ROOF | 2019 | 0 | 0 | 0 | 0 | 0 | 460 | 0 | 5272 | 5732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO295EV | 1118 GRAND CONCOURSE - ELEVATORS | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 101 | CO-0295 |  |  | 1118 GRAND CONCOURSE - ELEVATORS | 2019 | 9855 | 0 | 0 | 0 | 0 | 630 | 0 | 9075 | 9705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO295FIRE | 1118 GRAND CONCOURSE - FIRE ALARM UPGRADE | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 101 | CO-0295 |  |  | 1118 GRAND CONCOURSE - FIRE ALARM DESIGN & REPLACEMENT | 2019 | 0 | 0 | 0 | 0 | 0 | 534 | 0 | 5181 | 5715 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO295ROOF | 1118 GRAND CONCOURSE - ROOF | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 101 | CO-0295 |  |  | 1118 GRAND CONCOURSE -ROOF | 2019 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 132 | 152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | DAVIDCC | DAVIDSON COMMUNITY CENTER GYM | MISCELLANEOUS CONSTRUCTION | 103 | PW-D005 |  |  | DAVIDSON COMMUNITY CENTER GYM | 2019 | 750 | 0 | 0 | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | E08-00006 | NYPD - 08-147: Old 41st Precinct, 1086 Simpson Street | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 102 | PU-0025 PO-0079 |  |  | ENERGY EFFICIENCY UPGRADE AT OLD 41ST PRECINCT; 1086 SIMPSON STREET | 2019 | 119 | 123.75 | 235 | 39 | 0 | 0 | 0 | 0 | 397.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | E14-0002 | DCAS - BRONX COUNTY COURT COMP ENERGY UPGRADE | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 100 104 | PU-0025 |  |  | ENERGY UPGRADE | 2019 | 6179 | 5079.87 | 0 | 1117 | 0 | 0 | 0 | 0 | 6196.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0040 | CUNY - Bronx Community College Campus: Meister Hall | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 101 | PU-0025 |  |  | CUNY - BRONX COMMUNITY COLLEGE CAMPUS: MEISTER HALL | 2019 | 700 | 0 | 0 | 700 | 0 | 0 | 0 | 0 | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0042 | CUNY - Bronx Community College Campus: Polowczyk Hall | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 101 | PU-0025 |  |  | CUNY - BRONX COMMUNITY COLLEGE CAMPUS: POLOWCZYK HALL | 2019 | 300 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0043 | CUNY - Bronx Community College Campus: Colston Hall | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 101 | PU-0025 |  |  | CUNY - BRONX COMMUNITY COLLEGE CAMPUS: COLSTON HALL | 2019 | 375 | 0 | 0 | 375 | 0 | 0 | 0 | 0 | 375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0044 | CUNY - Bronx Community College Campus: Loew Hall | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 101 | PU-0025 |  |  | CUNY - BRONX COMMUNITY COLLEGE CAMPUS: LOEW HALL | 2019 | 375 | 0 | 0 | 375 | 0 | 0 | 0 | 0 | 375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0045 | CUNY - Bronx Community College Campus: Nichols Hall | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 101 | PU-0025 |  |  | CUNY - BRONX COMMUNITY COLLEGE CAMPUS: NICHOLS HALL | 2019 | 375 | 0 | 0 | 375 | 0 | 0 | 0 | 0 | 375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW293198X | 198 E 161ST STREET - FIRE ALARM UPGRADE | LEGAL MANDATES AND CORRECTION OF UNSAFE CONDITIONS | 101 | PW-0293 |  |  | 198 E 161ST STREET - FIRE ALARM DESIGN | 2019 | 0 | 0 | 0 | 350 | 0 | 4200 | 0 | 0 | 4550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326ATHX | OATH - 260 EAST 161ST, BRONX - RELOCATION | RENOVATION OF LEASED SPACE | 101 | PW-0326 |  |  | 260 EAST 161ST OATH RELOCATION | 2019 | 5753 | 0 | 4738 | 1015 | 0 | 0 | 0 | 0 | 5753 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326TLQ4 | TLC - BRONX | RENOVATION OF LEASED SPACE | 101 | PW-0326 |  |  | SQFT | 2019 | 5481 | 0 | 0 | 0 | 5481 | 0 | 0 | 0 | 5481 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326XDA1 | DA BRONX - RELOCATION TO 260 EAST 161 STREET | RENOVATION OF LEASED SPACE | 101 | PW-0326 |  |  | BRONX DA RELOCATION TO 260 EAST 161 STREET | 2019 | 16500 | 0 | 7300 | 2300 | 0 | 6900 | 0 | 0 | 16500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77198CT | 198 E161 ST.- COOLING TOWER REPLACEMENT | REHABILITATION OF CITY-OWNED OFFICE SPACE | 104 | PW-0077 |  |  | UNIT | 2019 | 878 | 0 | 0 | 77 | 0 | 711 | 0 | 0 | 788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW772076 | 1932 ARTHUR AVE.- 7th FLOOR BUILDOUT | REHABILITATION OF CITY-OWNED OFFICE SPACE | 106 | PW-0077 |  |  | $490 PER SQ FT | 2019 | 9200 | 0 | 0 | 0 | 0 | 764 | 7600 | 0 | 8364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207DC | 1932 ARTHUR AVENUE RENOVATION - DOB | REHABILITATION OF CITY-OWNED OFFICE SPACE | 101 | PW-0077 |  |  | SQ/IA | 2019 | 6716 | 0 | 0 | 0 | 0 | 550 | 5711 | 455 | 6716 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207EL | 1932 ARTHUR AVE.- ELECTRICAL UPGRADES | REHABILITATION OF CITY-OWNED OFFICE SPACE | 101 | PW-0077 |  |  | 1932 ARTHUR AVE.- ELECTRICAL UPGRADES | 2019 | 3510 | 0 | 0 | 0 | 688 | 0 | 8261 | 0 | 8949 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207RF | 1932 ARTHUR AVE.- ROOF | REHABILITATION OF CITY-OWNED OFFICE SPACE | 106 | PW-0077 |  | 1932 ARTHUR AVE BRONX | RECONSTRUCT ROOF | 2019 | 1482 | 0 | 0 | 0 | 123 | 0 | 1225 | 0 | 1348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207TU | 1932 ARTHUR AVENUE- CODE COMPLIANT TOILET UPGRADES | REHABILITATION OF CITY-OWNED OFFICE SPACE | 101 | PW-0077 |  |  | CODE COMPLIANT TOILET UPGRADES | 2019 | 1550 | 0 | 0 | 0 | 0 | 150 | 0 | 1400 | 1550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207W | 1932 ARTHUR AVE.- WINDOWS AND FACADE | REHABILITATION OF CITY-OWNED OFFICE SPACE | 101 | PW-0077 |  |  | 1932 ARTHUR AVE - WINDOWS AND FACADE | 2019 | 7995 | 0 | 0 | 0 | 662 | 0 | 6606 | 0 | 7268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77208B | 4101 WHITE PLAINS RD - HVAC UPGRADE | REHABILITATION OF CITY-OWNED OFFICE SPACE | 101 | PW-0077 |  |  | 4101 WHITE PLAINS RD - HVAC UPGRADE | 2019 | 399 | 0 | 0 | 0 | 363 | 0 | 0 | 0 | 363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77CTCX4 | 2556 BAINBRIDGE AVE- CIVIL SERVICE EXAM TESTING CENTER | REHABILITATION OF CITY-OWNED OFFICE SPACE | 101 | PW-0077 |  |  | 2556 BAINBRIDGE AVE- CIVIL SERVICE EXAM TESTING CENTER | 2019 | 18675 | 0 | 0 | 0 | 2000 | 0 | 28201 | 0 | 30201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77X215 | 215 E161 ST.- OFFICE RENOVATIONS | REHABILITATION OF CITY-OWNED OFFICE SPACE | 101 | PW-0077 |  |  | COMPLAINT PROCESSING AREA RELOCATION TO 4TH FLR ANNEX. | 2019 | 628 | 0 | 0 | 0 | 0 | 2494 | 0 | 0 | 2494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD5BA1 | 2556 Bainbridge Ave. Community Ctr. | REHABILITATION OF CITY-OWNED OFFICE SPACE | 102 | PW-D005 |  |  | 2556 BAINBRIDGE AVE. COMMUNITY CTR. | 2019 | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD5BA2 | 2556 Bainbridge Ave - Fordham Library renovation | REHABILITATION OF CITY-OWNED OFFICE SPACE | 102 | PW-D005 |  |  | DCAS - OLD FORDHAM LIBRARY RENOVATION -- FUNDS WILL GO TO DCAS TO RENOVATE THE OLD FORDHAM LIBRARY. | 2019 | 1128 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWXDAVDCC | DCAS/DAVIDSON COMMUNITY CENTER - CONSTRUCT 2 ADDITIONAL FLOO | MISCELLANEOUS CONSTRUCTION | 103 | PW-X078 |  |  | DCAS/DAVIDSON COMMUNITY CENTER - CONSTRUCT 2 ADDITIONAL FLOORS & ELEVATOR, FY20 EXE SECTION 211 ADD @$500K | 2019 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | S136-434 | 720-780 East 132 St - Bronx 1 3 4 Garage Rehabilitation | GARAGES AND FACILITIES | 101 | S-0136 |  |  | REHABILITATION | 2019 | 3214 | 0 | 0 | 0 | 7959 | 0 | 0 | 0 | 7959 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190425 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | SOLARDOS5 | DSNY - PV Installation on Garage - Bronx 9/10/11 | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 101 | PU-0025 |  |  | DSNY - PV INSTALLATION ON GARAGE - BRONX | 2019 | 0 | 0 | 0 | 0 | 0 | 3716 | 0 | 0 | 3716 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0