## Bay Street Commitments
BAY STREET COMMITMENTS
CEQR #: 16DCP156R ULURP #: C190113ZMR, N190114 ZRR, C190115PPR, C190179 HAR, N190114(A) ZRR, and C190179(A) HAR
COMMITMENT NAME | AGENCY | TIMELINE | FUNDING
Housing
Keep homes affordable by continuing to offer loans and tax incentives to building owners | HPD | Ongoing | No new funding is required
Host outreach and marketing events to continue promoting programs that help property owners make repairs and preserve affordable housing | HPD | Through December 2021 | No new funding is required
Expand Landlord Ambassadors program to Bay Street rezoning area | HPD | June 2020 - December 2021 | Pending City Council
Promote the Neighborhood Pillars Program to help community organizations acquire rent stabilized buildings | HPD | Through 2021 | No new funding is required
Provide free legal assistance to North Shore tenants | HRA | Summer 2022 | No new funding is required
Educate tenants about their rights and resources to prevent displacement | HPD, HRA | Ongoing | No new funding is required
Host tenant resource fairs to educate tenants about their rights and resources to prevent displacement | HPD | Host two tenant resource fairs by the end of 2020 | No new funding is required
Implement “Certification of No Harassment” (CONH) Pilot Program | HPD | September 2018 - September 2021 | No new funding is required
Launch HomeFix to help low income homeowners make critical repairs and stay in their homes | HPD | 2019 | No new funding is required
Combat Zombie Homes | HPD | Through June 2021 | No new funding is required
Offer financing to incentivize the development of affordable housing that exceeds minimum MIH requirements | HPD | Ongoing | No new funding is required
Proactively engage property owners in the Bay Street Corridor about the City’s resources to develop affordable housing | HPD | Fall 2019 | No new funding is required
Prioritize the development of City owned land at Jersey Street with affordable housing | HPD | RFP by October 2021 | No new funding is required
Prioritize the development of City owned land at the Stapleton Waterfront with affordable housing | HPD | Site A RFP by 2020; Site B1 RFP by 2023 | No new funding is required
Support mission‐driven groups interested in developing affordable housing on underutilized sites | HPD | Event to be held in 2020 | No new funding is required
Study the feasibility of affordable housing and commercial development on the Municipal Parking Lot at 54 Central Avenue | HPD, DOT, EDC | June 2020 | No new funding is required
Make it easier for residents to understand, prepare for, and complete the affordable housing application process | HPD | Ongoing | No new funding is required
Continue to refine tenant selection procedures to reach New Yorkers most in need | HPD | Ongoing | No new funding is required
Dedicated Rental Assistance (DSS) to help move 100 homeless families and individuals out of shelter and into affordable housing | HRA | 2019 | No new funding is required
Improve housing quality through rigorous enforcement of the Housing Maintenance Code | HPD | Ongoing | No new funding is required
Invest in New York City Housing Authority developments within North Shore | NYCHA | 2022 | $15M
Open Space
Reimagine Stapleton Playground to Provide Amenities for Multiple Generations of Users | DPR | 2020 | $11.1M
Make improvements to Tompkinsville Park | DPR | 2019 | No new funding is required
Reconstruct Cromwell Recreation Center at the Lyons Pools Site | DPR | 2025 | $92M
Construct future phases of public open space at New Stapleton Waterfront | DPR, EDC | 2024 | $75M
Repair the Ornamental Fountain at Tappen Park | DPR | 2020 | $930K
Improve Village Hall at Tappen Park | DPR | Design start FY 2020; construction two years after design completion | $5.7M
Complete the Tompkinsville Esplanade | EDC | 2020-2023 | $74M
Economic and Workforce Development
Continue outreach to Bay Street small businesses for access to support services | SBS | Ongoing | No new funding is required
Protect and enhance viability of local businesses (Neighborhood 360°) | SBS | Ongoing through FY 2020 | $500K / year
Support MWBEs | SBS | Ongoing | No new funding is required
SBS will provide its full suite of resources to targeted commercial corridors in and around the rezoning area | SBS | Ongoing | No new funding is required
Continue to provide local hiring incentives in HPD‐financed developments | HPD | Ongoing | No new funding is required
Provide opportunities for M/WBEs in the affordable housing development industry | HPD | Ongoing through 2021 | No new funding is required
Uphold responsible contracting and labor standards for affordable housing projects receiving City subsidy | HPD | Ongoing | No new funding is required
Commitment to good jobs in the rezoning area | DCP, SBS | Ongoing | No new funding is required
Community Resources
Site new school seats in the North Shore | DOE, SCA | PS 13 open in 2020; 357 Targee Street in 2022 | $250M
Fund and construct a public school in the New Stapleton Waterfront | SCA, EDC | Upon completion of infrastructure | No new funding is required
Build a new elementary school at 155 Tompkins Avenue | SCA | FY 2020 - FY 2024 | Proposed FY 2020-2024 Five-Year Capital Plan
Meet Pre-K and 3K need | SCA | FY 2020 - FY 2024 | Proposed FY 2020-2024 Five-Year Capital Plan
Explore feasibility of siting an educational complex at the former Staten Island Hospital Site | SCA | Pending litigation | No new funding is required
Ensure childcare and school planning reflect need as development occurs | DOE | 2020-21 school year | No new funding is required
Transportation and Infrastructure
Make improvements to Bay Street from Richmond Terrace to Swan Street | DOT | FY 2019 design start; FY 2023 construction start | $27.8M
Make public realm improvements around Tompkinsville Station | DOT | FY 2020 design start; FY 2023 construction start | $3.7M
Make improvements to Stapleton Station | DOT | FY 2020 design start; FY 2023 construction start | $500K
Advocate to MTA New York City Transit to provide additional peak hour bus service based on growth in the area | DOT, NYCT | Ongoing | No new funding is required
Implement a Traffic Monitoring Plan | DCP, DOT | Ongoing through 2030 | $1 - $2M
Coordinate with the Board of Standard and Appeals regarding street widths | DOT, DEP | Ongoing | No new funding is required
Implement an off-hour Truck Delivery Pilot | DOT | Through 2021 | No new funding is required
Relieve NYPD parking obstructions at the 120th Precinct | NYPD | Ongoing | No new funding is required
Explore the relocation of Staten Island Central Booking to the Staten Island Court House | DCP | Spring 2020 | No new funding is required
Collaborate with the MTA on planning for a North Shore BRT | MTA | Ongoing | No new funding is required
Monitor intersections that will have unmitigated impacts as a result of the rezoning during weekday rush hours | DOT, NYPD | Ongoing | No new funding is required
Provide real time passenger information at MTA bus stops | DOT | FY 2020 - FY 2022 | 900000
Streetscape improvements along Bay Street | DOT | FY 2020 design start; FY 2023 construction start | $6.7M
Remap portions of key sites and make enhancements to improve connectivity along Bay Street | DCP | FY 2020 design start; FY 2023 construction start | No new funding is required
Build New Stapleton Waterfront Infrastructure | EDC | 2023 | $45M
Create a Drainage Plan for Bay Street | DEP | 2019 | No new funding is required
Update undersized sewers in targeted areas | DEP | FY 2021 design start; FY 2023 construction start | $15M
Monitor quality of Life Complaints Related to Infrastructure | DOT, DEP | Ongoing | No new funding is required
Stormwater Management Study | DEP | 2020 | Study is fully funded
Seek opportunities to expand the Green Infrastructure Grant Program to homeowners and developers throughout Staten Island Community District 1 (DEP) | DEP | Ongoing | No new funding is required
Provide annual updates to Staten Island Community Board 1, Borough President, and local Council Member | DCP | Annual | No new funding is required